| Project Name: | DPI (Dynamic Passenger Information) |
| --- | --- |
| Prepared by: | Keith Roan |
| Date (MM/DD/YYYY): | 04/15/08 |

| Version History (insert rows as needed): |  |  |
| --- | --- | --- |
| Version | Date (MM/DD/YYYY) | Comments |
| 1.0 | 04/15/2008 | Initial – Keith Roan |

Purpose: This project plan documents the project planning process and consists of the following basic tasks:

- Defining the sequence of tasks to be performed

- Identifying all deliverables associated with the project

- Defining the dependency relationship between tasks

- Estimating the resources required to perform each task

- Scheduling all tasks to be performed

- Defining the budget for performing the tasks

- Defining the organization executing the project

- Identifying the known project risks

- Defining the process ensuring quality of the project product

- Defining the process specifying and controlling requirements

This plan documents and defines the objectives of the project, the approach to be taken, and the commitment being assumed. This document contains the details required to successfully execute the project. Once project execution begins, this plan will be reviewed, baselined, and updated on a regular basis.

# Table of Contents

Plan Approval	3

Project Summary	5

Project Summary – Continued	6

Project Summary – Continued	7

Project Charter	8

Project Communication Plan	9

Project Tradeoff Matrix and Status Summary	10

Project Organization	11

Activity List	12

Work Breakdown Structure (WBS)	13

Work Product Identification	14

Project Schedule	15

Estimated Cost at Completion	16

Resource Loading Profiles	17

Project Staffing Plan	17

Project Requirements	18

Risk Identification	41

Configuration Management Planning	44

Quality Plan	45

Top Five Issues	46

Action Item Status	47

## Plan Approval

Project Name: DPI (Dynamic Passenger Information)

Date:

Plan Release #: 1.0

Project Manager: Keith Roan

Approvals:

Keith Roan 						Casey Emoto

Technology Support Services Manager	Deputy Director Program/Project Dev. – CMA

Joonie Tolosa						Jerry Oxsen

Mgr, Ops Analysis, Reporting 			Operations Manager

& Systems

Bill Capps						Art Douwes

Manager, Service & Operations Planning 		Operations Manager, Engineering

Liz French						Patrick Griffin

Sr. Planner Progmg & Grants				Mgr, Public Affairs & Cust. Info

Dino Guevarra						Heidi Samuels

Sales and Promotion and Supervisor	Operations Manager, Bus Mtc Admin

George Tacke						Camille Williams

Operations Manager, Ops, Transportation	Accessible Services Program Manager

## Project Summary

Project Name: DPI (Dynamic Passenger Information System)

Start Date: 1/1/04

Organization: Technology

Submitted By: Keith Roan

Prime Contractor: TBD

Date Awarded: TBD

Current Stage of Project: Planning

Project is on Schedule: No

If no, please provide details: Resource issues have constantly kept project running at a minimum until the last 2.5 years.

Project is within Budget: Yes

If no, please provide details

Yes/No

Is this an update Project Plan? If so, reason for update:		  No

Budget for project by fiscal year and is project funded? 		  Yes

If so, for what amount(s) and period(s):

Budget Amount:	$5.7 m		Year:	2008	Funded?	  Yes

Budget Amount:			Year:	2009	Funded?	  Yes

Budget Amount:					Funded?

Total Amount: 	$5.7 m

## Project Summary – Continued

Points of Contact

This is a list of individuals that will be involved with the project during the execution phase.

| Position | Name/Organization | Phone | E-Mail |
| --- | --- | --- | --- |
| Project Manager | Keith Roan/Tech | 408-321-7109 | keith.roan@vta.org |
| CMA Contact | Casey Emoto/CMA | 408-321-5564 | casey.emoto@vta.org |
| Senior Management Sponsor | Gary Miskell//CIO – Tech | 408-321-7100 | gary.miskell@vta.org |
| Senior Management Sponsor | Bill Lopez/COA – Administration Services | 408-321-5801 | bill.lopez@vta.org |
| Procurement Contact | Tom Smith/CAMM | 408-952-4190 | tom.smith@vta.org |
| Compliance Review Manager | Gary Epstein/Finance | 408-321-5683 | gary.epstein@vta.org |
| Program and Grants Management | Liz French/Grants | 408-321-5737 | liz.french@vta.org |
| Stakeholders (Top 3): |  |  |  |
| Operations | Jerry Oxen/Operations Manager | 408-952-6858 | jerry.oxsen@vta.org |
| Customer Service/Public Affairs | Patrick Griffin/Manager | 408-321-7506 | patrick.griffin@vta.org |

## Project Summary – Continued

Prime Contractor Information Company:

| Position | Name/Organization | Phone | E-Mail |
| --- | --- | --- | --- |

## Project Charter

Business Problem

The lack of real time information provided to VTA’s customers concerning vehicle arrival times of buses and trains.

Statement of work (Goal)

Design, prototype and implement an automated real time information system by December 2009.

Project Objectives:

The primary objective of the DPI System is to provide VTA’s customers with accurate and reliable real-time transit information.  This information includes the real-time location of transit vehicles and the estimated next vehicle arrival and departure times for all transit routes.  It is envisioned that this information would be accessible by way of the Internet and telephone, as well as electronic information display boards at key transit stops within Santa Clara County.  These locations include major bus stops, Bus Rapid Transit (BRT)/Rapid Bus stops, Light Rail Transit (LRT) stations, transit centers, and joint transit stops (e.g. those shared with other transit service providers).  This real-time information would also be disseminated through MTC’s 511 Systems and VTA’s customer service center.

## Project Communication Plan

The intent is to distribute project information to stakeholders in a timely manner. Communications tools for this project are listed below with additional items to be added as needed.

- Work Breakdown Structure

- Scope Statement

- Project Charter, Project Plan

- Resource Matrix

- Meetings/bi-weekly

- Cost Performance Index

- Schedule Performance Index Reports

## Project Tradeoff Matrix and Status Summary

Managing a project requires the balancing of three factors: resources, schedule, and scope. These three factors are interrelated. The project trade off matrix shows the relative importance of each factor:

- Constrained means the factor cannot be changed

- Accepted means the factor is somewhat flexible to the project circumstance

- Improved means that the factor can be adjusted

| Schedule | Scope | Resources |
| --- | --- | --- |
| CONSTRAINED | CONSTRAINED | CONSTRAINED |

Identify variables to be constrained, improved, and accepted

+/- Status

| Team/Phase | Technical | Schedule | Cost | Comment |
| --- | --- | --- | --- | --- |
| Initiating | On | Behind | On | Project was delayed several years due to resource issues and priority rankings of projects |
| Planning | On | Behind | On | Took additional time to provide in depth project management plan and refine RFP |
| Executing | On | Behind | On | Best knowledge due to Independent Cost Estimate |

## Project Organization

The Project Organization defines the persons responsible for the following types of functions: project manager, development, manager, quality assurance, and configuration management. A project manager is required for every project.

## Activity List

This is an activity list (work breakdown structure) that describes each task required by the project.. These work packages describe required schedule, identify requirements to be completed and describe specific work to be performed.

| Activity# | Activity Name | Activity Name Description | # of Days | Start Date | Dependency | Milestone |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Design | System Architecture | 90 | 10/1/08 |  | No |
| 2 | Develop | Development - should be close to off the shelf with required GUI | 120 | 1/21/09 | #1 | No |
| 3 | Integrate | Integrate code | 120 | 4/15/09 | #2 | No |
| 4 | Testing | Test DPI in lab | 60 | 7/8/09 | #3 | Yes |
| 5 | Pilot | Run Pilot test on one sign in field | 15 | 9/2/09 | #4 | Yes |
| 6 | Marketing | Marketing & Outreach | 60 | 10/21/09 | #5 | No |
| 7 | Installation | Install along 522 route | 40 | 10/21/09 | #5 | Yes |
| 8 | Countywide | Install to additional locations | 30 | 10/21/09 | #5 | Yes |
| 9 | Training | Provide User Training | 10 | 10/21/09 | #5 | No |
| 10 | Close-Out | Close-Out and transfer to O&M | 60 | 11/4/09 | #9 | Yes |

## Work Breakdown Structure (WBS)

This activity describes each task required in the project. These work packages describe required schedules, identify requirements to be completed and describe specific work to be performed.

## Work Product Identification

The list of project deliverables that includes the date due and the person responsible for the delivery should be part of the plan. This information is derived from the project activity list, and is expanded to include the assignment of the deliverable to a specific author and tracking of delivery of the document.

List of all deliverables required by the project, the due date and the person responsible

| Deliverable Name | Due Date | Date Delivered | Point of Contact |
| --- | --- | --- | --- |
| Design Document | 12/1/08 |  | Keith Roan |
| Test Plan | 4/1/09 |  | Keith Roan |
| Installation Plan | 7/2/09 |  | Keith Roan |
| Source Code | 7/2/09 |  | Keith Roan |
| Installation | 9/1/09 |  | Keith Roan |
| Training Plan | 8/2/09 |  | Keith Roan |
| Project Closeout | 11/4/09 |  | Keith Roan |

## Project Schedule

The project schedule included in the project plan can either be a GANTT or PERT chart. IT should include milestones, task dependencies, task duration, work product delivery dates, quality milestones (reviews/audits/inspections), configuration management milestones, and action items (with deadlines and responsibilities).

Project Start Date: Wed 10/1/08 
Project Finish Date: Tue 1/12/10

| ID | Task_Name | Duration | Start_Date | Finish_Date | Predecessors | Resource_Names |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | DPI | 335 days | Wed 10/1/08 | Tue 1/12/10 |  |  |
| 2 | Phase II - Software/Hardware/Testing | 275 days | Wed 10/1/08 | Tue 10/20/09 |  |  |
| 3 | Design | 3 mons | Wed 10/1/08 | Tue 12/23/08 |  | Vendor |
| 4 | Develop | 4 mons | Wed 12/24/08 | Tue 4/14/09 | 3 | Vendor |
| 5 | Integration | 4 mons | Wed 4/15/09 | Tue 8/4/09 | 4 | Vendor |
| 6 | Testing | 2 mons | Wed 8/5/09 | Tue 9/29/09 | 5 | Vendor |
| 7 | Pilot | 15 days | Wed 9/30/09 | Tue 10/20/09 | 6 | Vendor |
| 8 | Marketing | 60 days | Wed 10/21/09 | Tue 1/12/10 |  |  |
| 9 | Marketing/Outreach plan | 3 mons | Wed 10/21/09 | Tue 1/12/10 | 7 |  |
| 10 | Phase III - Bus Stop Installation | 30 days | Wed 10/21/09 | Tue 12/1/09 |  |  |
| 11 | Install/test signs down 522 route | 6 wks | Wed 10/21/09 | Tue 12/1/09 | 7 | Vendor |
| 12 | Phase V - LR | 20 days | Wed 10/21/09 | Tue 11/17/09 |  |  |
| 13 | Countywide Installation | 1 mon | Wed 10/21/09 | Tue 11/17/09 | 7 | Vendor |
| 14 | Training | 2 wks | Wed 10/21/09 | Tue 11/3/09 | 7 | Vendor |
| 15 | Phase VI - Project Closeout | 40 days | Wed 11/4/09 | Tue 12/29/09 |  |  |
| 16 | Project Closeout | 2 mons | Wed 11/4/09 | Tue 12/29/09 | 14 | Technology/Finance |

## Estimated Cost at Completion

This estimated cost at completion is an assessment of the total project effort in terms or either time and/or dollars.

| Activity | Analysis in Hours |  |  |  |  | Analysis in Dollars |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Budget Hours | Actual Hours | Est. to Comp | Est. @ Comp | Var. | Budget Hours | Actual Hours | Est. to Comp | Est. @ Comp | Var. |
| Project Management |  |  |  |  |  |  |  |  |  |  |
| Manage Project | 2,048 |  | 1,800 |  |  | 2,048 |  | 200,000 |  |  |
| Design/Dev |  |  |  |  |  |  |  |  |  |  |
| Dev/Imp Base System Software | 1,120 |  | 1120 |  |  | 1,120 |  | 2,168,750 |  |  |
| Integration |  |  |  |  |  |  |  |  |  |  |
| Format for MTC’s 511 system, S/W interface to VMB’s, PA Systems, H/W and peripherals | 640 |  | 640 |  |  | 640 |  | 92,000 |  |  |
| Testing |  |  |  |  |  |  |  |  |  |  |
| System Testing | 320 |  | 320 |  |  | 320 |  | 225,000 |  |  |
| Pilot |  |  |  |  |  |  |  |  |  |  |
| Testing of S/W & H/W to each make of sign | 120 |  | 120 |  |  | 120 |  | 21,000 |  |  |
| Marketing |  |  |  |  |  |  |  |  |  |  |
| Marketing/Outreach plan | 120 |  | 120 |  |  | 120 |  | 23,000 |  |  |
| Installation |  |  |  |  |  |  |  |  |  |  |
| VMS on Rapid 522 Bus Route | 240 |  | 240 |  |  | 240 |  | 450,000 |  |  |
| Countywide |  |  |  |  |  |  |  |  |  |  |
| Countywide Installs | 160 |  | 160 |  |  | 160 |  | 642,500 |  |  |
| Training |  |  |  |  |  |  |  |  |  |  |
| Training/Documentation | 80 |  | 80 |  |  | 80 |  | 162,500 |  |  |
| Total | 4848 |  | 4848 |  |  | 4848 |  | 3,984,750 |  |  |

## Resource Loading Profiles

The staffing plan shows the number of personnel, by type, that are required on the project on a monthly basis. This information should be compared monthly on a planned versus actual basis. VTA will acquire a consultant to assist with the project management responsibilities of this project. Additional resources projected below are expected to be provided by the vendor. It is expected that the vendor will have a project manager, software/hardware developers, installation engineers, transportation engineers/planners, and electricians. The number of individuals in these areas is expected to begin with approximately eight individuals and peak at approximately 14.

## Project Staffing Plan

## Project Requirements

This plan lists the project requirements, with references to the statement of work, work breakdown structure, and specifications.

| No. | Requirement | RFP Reference | Task Reference | Specification Reference | Completed | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Project Requirements are available at VTA as a separate list. They were removed from this copy of the document in the Systems Engineering Guidebook for ITS website. |  |  |  |  |  |  |

## Risk Identification

This plan lists anything that could potentially affect the successful completion of the project. The contractual, management, and technical risks associated are identified and assessed for the probability of the risk occurring, the cost to correct if the risk occurs, the impact of the risk on the project, and the suggested mitigation activities and cost of mitigation.

| Category | Probability | Impact | Risk | Mitigation |
| --- | --- | --- | --- | --- |
| MANAGEMENT |  |  |  |  |
| Integration | High | High | Integrating DPI with vendor 1 | - Risk transference to system integrator. - Work should be done within 1 month for less than 30,000 dollars. - Another option is to post fixed schedule information to the signs (2nd option). - The signs could also be disconnected from the SONET network and connected to the 1Gb network (3rd option). |
| Integration | Low | High | Integrating DPI with Vendor 2 | - Risk transference to integrator. - Work to build the GUI interface for an open system should only take approximately 1 month at a cost of 30,000 dollars (1st option). - Another vendor would have to manipulate the data from the vendor database to build the GUI (2nd option) if Vendor 2 decided not to participate. The 2nd option should only cost 60,000 for two months of work. |
| Software | Low | Medium | Trapeze licenses | - Risk transference to system integrator. Current costs are 1305 dollars each for 11 workstations (2nd option). |
| Integration | Medium | High | 511 system not ready for VTA IVR | - Utilize VTA’s own IVR at additional cost. - Lower number of signs will be installed as a result. - Cost approximately 200,000 from vendors |

## Configuration Management Planning

This plan lists the person responsible for project configuration management, the procedures used, and the planned configuration items, planned release dates for configuration items, and resources required to conduct Configuration Management.

CM Responsibility

Manager: Keith Roan

Additional Staff for CM

No additional staff anticipated at this time

Procedure Reference:

Configuration Items:

| No | Item | Comments |
| --- | --- | --- |
| 1 | System / Management / Project Plan | Project Plan |
| 2 | System / Requirements / System Specifications | System Specifications |
| 3 | System / Test / Testing Plan | Test Plan |
| 4 | System / Management / Testing Plan | Implementation |

QA Audits need to be included on the project schedule

## Quality Plan

This document defines the person responsible for project quality activities, the procedures used, the planned quality activities, and resources required to conduct QA activities.

QA Responsibility

Manager: Keith Roan

Additional Staff for QA

Support will be needed by system integrator, design team, and development members.

Procedure Reference:

Planned Quality Event: Ensure the QA is implemented throughout the project’s life cycle. Dates include QA audits and reviews, design walkthroughs and other project activities that QA staff will participate in.

| No | Item | Comments |
| --- | --- | --- |
| 1 | Requirements Review | Due: |
| 2 | Code Walk Through |  |
| 3 | Interface Prototype |  |
| 4 | Testing Audit |  |

Ensure there is a repository

Ensure QA audits the baselines and CM activities on a regular basis. - describe

## Top Five Issues

This plan list the top five know issues associated with the project, personnel responsible for resolving the issue, and an associated open and close date, with proposed or recommended solutions.

| Issue | Responsible Individual | Open Date | Closure Date | Status |
| --- | --- | --- | --- | --- |
| Vendor 1 Interface | Keith Roan |  |  |  |
| Vendor 2 Interface | Keith Roan |  |  |  |
| IVR Interface – 511 System | Keith Roan |  |  |  |
| Audio Issue with Platforms | Keith Roan |  |  |  |

## Action Item Status

This plan includes a list of action items that are maintained as part of project tracking.

| Action Item # | Description | Responsible Individual | Open Date | Closure Date | Status |
| --- | --- | --- | --- | --- | --- |