## Introduction
SIBC Cost Estimation Tool
Abstract
This spreadsheet was developed as a versatile tool to aid agencies in estimating the cost of Slide-In Bridge Construction (SIBC) both during the planning or initial phase of a project and during the design or bidding document preparation phase. The tool can be used to estimate the cost difference of a SIBC alternative to that of a traditional construction alternative. In addition, the tool can be used to estimate the bridge slide bid item. Initially, the user defines the estimated cost of the SIBC bridge in order to determine the estimated slide cost. When detailed data is unavailable, the user may use an assumed unit cost (average unit cost per deck area) as a starting point. The estimated cost of the SIBC bridge is multiplied by a Base Slide Cost Ratio (B) that has been derived from historic data to provide a base estimated slide cost. This cost is adjusted by several Slide Cost Adjustment Factors (F) that have been shown to affect slide costs in previous SIBC projects. User-defined contingency is then applied. Next, additional known costs such as administrative costs, incentives/disincentives, and specific construction costs or savings are input. These values capture the other costs required by the SIBC alternative. Finally, The Estimated Cost of SIBC (E) is calculated. This value can be used to compare the traditional construction alternative to the SIBC alternative. Note, the E term is the estimated project cost difference between the two alternative and it can be positive or negative. When using the SIBC Cost Estimation Tool to estimate the construction slide bid item, certain parts will not be used. Administrative costs, incentives/disincentives, and additional site and construction costs are not applicable and should be entered as zero. The Estimated Bridge Cost (X) can be taken directly from an engineer's estimate. The SIBC Cost Estimation Tool Guideline (link provided below) provides an in-depth explanation of this tool with examples for reference. Users are encouraged to become familiar with the guideline prior to using this tool. Additional links are provided below for reference on SIBC, user cost information, and historical bridge unit costs.
FHWA Reference Material
SIBC Cost Estimation Guideline Tool
FHWA Home Page
SIBC Website
SIBC Implementation Guide
Life Cycle Cost Analysis (LCCA) and User Cost Information
Work Zone Road User Costs - Concepts and Applications
FHWA Bridge Unit Construction Cost Data
Release Date
2015-02-19

## Estimated Slide Cost
Estimated Slide Cost
Base Estimated Cost
Estimated Bridge Cost |  |  | X | = | 2600000
This is the total estimated cost to construct the SIBC bridge. This estimated cost does not include the costs needed to slide the bridge into place. It also does not include any elements that would increase or decrease the cost of the project as a result of using SIBC methods.
Base Slide Cost Ratio |  |  | B | = | 20%
This percentage should be applied to all bridges considered for SIBC. When multiplied with the Estimated Bridge Cost (without the slide cost), the Base Slide Cost Ratio provides a base estimated slide cost for subsequent calculations.
Base Estimated Slide Cost Subtotal (X*B) |  |  |  |  | 520000
Slide Cost Adjustment Factors
Experience Factor
This factor accounts for the combined level of experience of the owner, designer, and contractor in administrating and constructing a slide-in bridge project.
| Little/No Combined Experience | 1.05
| Some Combined Experience | 1
| Significant Combined Experience | 0.95
Select from the drop-down menu:
| Significant Combined Experience |  | FX | = | 0.95
Cost Adjustment Factors (Cont.)
Site Complexity Factor
This factor accounts for differing site conditions that can affect the cost of SIBC. Site complexities can include soil quality, water, proximity to other structures or natural formations, limited construction staging areas, and other conditions.
| Many/Large Site Complexities | 1.1
| Above Average Site Complexities | 1.05
| Typical Site Complexities | 1
| Below Average Site Complexities | 0.95
| Little to No Site Complexities | 0.9
Select from the drop-down menu:
| Below Average Site Complexities |  | FS | = | 0.95
Temporary Shoring Factor
This factor accounts for the material and labor costs required to support the superstructure prior to and during the slide.
| Large Quantity of Shoring Using New Materials | 1.2
| Average Quantity of Shoring Using New Materials | 1
| Small Quantity of Shoring Using New Materials | 0.8
| Large Quantity of Shoring Using Re-usable Materials | 1
| Average Quantity of Shoring Using Re-usable Materials | 0.8
| Small Quantity of Shoring Using Re-usable Materials | 0.6
Select from the drop-down menu:
| Average Quantity of Shoring Using Re-usable Materials |  | FTS | = | 0.8
Vertical Jacking Factor
This factor is used when vertical jacking is required to move the bridge superstructure into its final position. A small amount of vertical jacking is required on most bridges to place bearings and finish superstructure placement. These small vertical movements should not be considered in this factor.
| Additional Vertical Jacking Required | 1.2
| No Additional Vertical Jacking Required | 1
Select from the drop-down menu:
| No Additional Vertical Jacking Required |  | FJ | = | 1
Cost Adjustment Factors (Cont.)
AADT/Undercrossing Factor
This factor accounts for the effects of the undercrossing on a contractor's ability to slide the bridge into place. Natural ground, water, railroads, and AADT of the undercrossing can all affect the cost of SIBC.
| Bridge Over Small Waterway or Dry Creek Bed | 0.8
| Bridge Over Railroad | 0.9
| Bridge Over Large Waterway or Canyon | 1
| Bridge Over Roadway: AADT = 0 - 10,000 | 0.6-0.9
| Bridge Over Roadway: AADT = 10,000 - 100,000 | 0.9-1.1
| Bridge Over Roadway: AADT = 100,000 + | 1.1
First, select from the drop-down menu:
Bridge Over Roadway: AADT = 100,000 +
Then, enter AADT (if applicable - ranges need to match drop-down menu):
| 100000 |  | FA | = | 1.1
Modified Base Slide Ratio (FX*FS*FTS*FJ*FA) |  |  | F | = | 0.7942
Modified Base Slide Ratio (B*F) |  |  |  |  | 15.88%
Subtotal (X*B*F) |  |  |  |  | 412984
Number of Spans
Number of Spans |  |  |  |  | 1
Contingency
Contingency |  |  | C | = | 20%
A contingency is applied as a percentage of the Estimated Slide Cost. It accounts for unforeseen expenses in the construction of the bridge slide.
Total Estimated Slide Cost
|  | = | 495580.8

## Additional Inputs
Additional Inputs
Provide Additional Calculations as Necessary
Additional Construction Costs
Additional Site Costs |  |  | S | = | -103000
Any additional specific quantifiable site costs or savings that affect the cost of SIBC. Additional site costs include right-of-way costs, utility relocations, cofferdams, and any other costs that can be specifically quantified. Additional site savings include costs that were not incurred as a result of using SIBC.
Additional Bridge Construction Costs |  |  | D | = | -536000
Any additional specific quantifiable bridge construction costs or savings, which affect the cost of SIBC. Additional bridge construction costs include costs incurred through changes to bridge superstructure to accommodate SIBC (i.e., shallower girders, additional girder lines, concrete vs. steel, etc.) Additional bridge construction savings include costs that were not incurred as a result of using SIBC.
Subtotal (S+D) |  |  |  |  | -639000
Additional Project Costs
Additional Administrative Costs |  |  | A | = | -110000
Any additional specific quantifiable administrative costs that affect the cost of SIBC. Additional administrative costs include additional design engineering costs, construction administration costs, DOT administration costs, etc.
Incentives/Disincentives |  |  | I | = | 20000
Incentives and disincentives are determined by the agency at their own discretion.
Subtotal (A+I) |  |  |  |  | -90000
Total Additional Costs
|  | = | -729000

## Summary
SIBC Cost Estimation Summary
Estimated Slide Cost
Estimated Bridge Cost | X | = | 2600000
Base Slide Cost Ratio | B | = | 20%
Experience Factor, FX | FX | = | 0.95
Site Complexity Factor, Fs | FS | = | 0.95
Temporary Shoring Factor, FTS | FTS | = | 0.8
Vertical Jacking Factor, FJ | FJ | = | 1
AADT/Undercrossing Factor, FA | FA | = | 1.1
Slide Cost Adjustment Factor (FX*FS*FTS*FJ*FA) | F | = | 0.7942
Modified Base Slide Ratio (B*F) |  | = | 15.88%
Number of Spans |  |  | 1
Contingency | C | = | 20%
Total Estimated Slide Cost |  | = | 495580.8
Additional Construction Costs
Additional Site Costs | S | = | -103000
Additional Construction Costs | D | = | -536000
Additional Project Costs
Additional Administrative Costs | A | = | -110000
Incentives/Disincentives | I | = | 20000
Estimated Cost of SIBC | E | = | -233419.2