11008 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON | SHERMAN-DENISON | 04 | 2009520 | SPN:0666-01-022-WIDEN EXISTING HIGHWAY TO INCLUDE TURN LANES, TURN BAYS AND RAISED MEDIANS : 1,520` WEST OF US 75 C/L | Pavement Improvement | 2009-08-26 | 2009-09-21 | 2010-11-01 |  | 3000000 | 0.758
11009 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WHARTON |  | 14 | 2009521 | SPN:0027-04-039-SEAL COAT, ACP & SET : 3.3 MI E OF LISSIE | Pavement Improvement | 2009-06-16 | 2009-07-20 | 2009-11-01 | 2009-11-20 | 3184624.51 | 7.157
11010 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | AUSTIN |  | 10 | 2009522 | SPN:1258-01-021-GRADING, BASE, SURFACING : SH 36 | Pavement Improvement | 2009-06-02 | 2009-06-22 | 2009-12-01 | 2010-08-12 | 2540876.78 | 3.755
11011 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | COLORADO, DE WITT, VICTORIA |  | Multiple | 2009523 | SPN:0088-06-003-ASPHALTIC CONCRETE PAVEMENT : GUADALUPE RIVER BRIDGE IN VICTORIA ;SPN:0270-01-047-ASPHALTIC CONCRETE PAVEMENT : SH 119 ;SPN:0270-02-038-ASPHALTIC CONCRETE PAVEMENT : FM 2980 ;SPN:04 | Pavement Improvement | 2009-06-16 | 2009-07-15 | 2009-09-01 | 2009-11-25 | 2562752.28 | 7.310
11012 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MATAGORDA |  | 14 | 2009524 | SPN:0847-01-013-REHABILITATE ROADWAY : FM 457 | Pavement Improvement | 2009-06-23 | 2009-07-14 | 2009-11-01 | 2010-06-15 | 1856668.17 | 3.153
11013 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FAYETTE |  | 25 | 2009525 | SPN:0211-06-053-PAVEMENT REPAIR AND ACP SURFACING : ROITSCH STREET ;SPN:0268-01-052-PAVEMENT REPAIR AND ACP SURFACING : BS 71-E | Pavement Improvement | 2009-06-22 | 2009-07-20 | 2009-08-01 | 2009-09-30 | 789505.41 | 1.672
11014 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARDIN |  | 08 | 2009526 | SPN:0811-01-010-RESTORE EXISTING ROADWAY : US 69, EAST | Pavement Improvement | 2009-06-12 | 2009-06-22 | 2009-09-01 | 2009-09-11 | 619326.17 | 3.807
11015 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | JASPER |  | 08 | 2009527 | SPN:0784-03-014-PROVIDE ADDITIONAL PAVED SURFACE WIDTH : FM 105, SOUTH | Pavement Improvement | 2009-06-22 | 2009-07-24 | 2009-11-01 | 2009-12-01 | 2569366.36 | 7.479
11016 | Completed | C250,C200 | Highway Infrastructure Investment Grant | TEXAS | TYLER |  | 08 | 2009528 | SPN:0200-07-049-OVERLAY EXISTING ROADWAY : US 190 IN WOODVILLE, SOUTH ;SPN:0213-06-039-OVERLAY EXISTING ROADWAY : 3.9 MI W OF US 69 | Pavement Improvement | 2009-06-02 | 2009-07-16 | 2009-09-01 | 2009-11-16 | 2393603.28 | 5.141
11017 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | JEFFERSON |  | 02 | 2009529 | SPN:0508-04-154-OVERLAY EXISTING ROADWAY AND BASE REPAIRS : CHAMBERS COUNTY LINE | Pavement Improvement | 2009-06-16 | 2009-07-22 | 2009-12-01 |  | 4097310.61 | 18.993
11018 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CHAMBERS |  | 14 | 2009530 | SPN:0508-03-090-SPOT LEVEL UP & OVERLAY : 0.278 MI W OF FM 1406, EAST ;SPN:0739-01-044-SPOT LEVEL UP & OVERLAY : SH 73, EAST ;SPN:0762-02-044-OVERLAY EXISTING ROADWAY : US 90, SOUTH | Pavement Improvement | 2009-06-02 | 2009-06-29 | 2009-09-01 | 2009-11-13 | 782288.36 | 3.718
11019 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BELL |  | 31 | 2009531 | SPN:0015-06-071-RECONSTRUCT AND WIDEN FROM FOUR TO SIX LANES TO REDUCE CONGESTION AND ENHANCE SAFETY : AMITY ROAD US 190;SPN:0015-06-078-INSTALL OVERHEAD DYNAMIC MESSAGE SIGNS TO MAKE FREEWAY OPERATIO | Pavement Widening | 2010-06-10 |  |  |  | 102371100.59 | 6.969
11020 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARDIN |  | 08 | 2009532 | SPN:0784-01-043-OVERLAY EXISTING ROADWAY : FM 92 IN SILSBEE, EAST | Pavement Improvement | 2009-06-02 | 2009-06-22 | 2009-09-01 | 2009-09-17 | 352932.9 | 1.688
11021 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | NEWTON |  | 08 | 2009533 | SPN:0304-08-012-UPGRADE BRIDGE RAIL : AT LITTLE COW CREEK ;SPN:0304-09-004-UPGRADE BRIDGE RAIL : AT TWO MILE BRANCH ;SPN:0627-02-017-UPGRADE BRIDGE RAIL : AT LITTLE COW CREEK, DRAW & WHITMAN ;SPN:0 | Safety/Traffic Management | 2009-05-19 | 2009-07-07 | 2010-12-01 | 2010-04-26 | 1043652 | 2.402
11022 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ORANGE |  | 08 | 2009534 | SPN:0784-05-034-MILL & OVERLAY EXISTING ROADWAY, SEAL COAT : SH 12, EAST | Pavement Improvement | 2009-06-03 | 2009-07-06 | 2009-09-01 | 2009-09-29 | 519724.35 | 1.657
11023 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZOS |  | 17 | 2009535 | SPN:0116-04-096-OVERLAY CONSISTING OF A SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : FM 2818 ;SPN:0117-01-043-REHABILITATE EXISTING ROAD CONSISTING OF SPOT REPAIRS, SURFACE TREAT | Pavement Improvement | 2009-06-02 | 2009-07-17 | 2010-02-01 | 2009-10-02 | 621471.9 | 1.587
11024 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZOS |  | 17 | 2009536 | SPN:0506-01-093-OVERLAY CONSISTING OF SPOT REPAIRS, SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : FM 2818 ;SPN:0506-01-094-OVERLAY CONSISTING OF A ONE COURSE SURFACE TREATMENT, HM | Pavement Improvement | 2009-05-19 | 2009-06-12 | 2010-01-01 | 2009-10-06 | 878657.3 | 2.462
11025 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZOS |  | 17 | 2009537 | SPN:1316-01-053-OVERLAY CONSISTING OF A SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : 0.1 MILE EAST OF FM 158 | Pavement Improvement | 2009-05-19 | 2009-06-03 | 2009-12-01 | 2009-09-15 | 298091.9 | 1.000
11026 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | LEON |  | 06 | 2009538 | SPN:0675-03-068-OVERLAY CONSISTING OF CONCRETE PAVEMENT REPAIR, A ONE COURSE SURFACE TREATMENT, HMA OVERLAY AND PAVEMENT MARKINGS : KEECHI CREEK | Pavement Improvement | 2009-06-04 | 2009-08-17 | 2010-03-01 | 2010-06-16 | 6623247.22 | 7.269
11027 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | HOWARD |  | 19 | 2009539 | SPN:0005-05-101-FLEXIBLE PAVEMENT REPAIR & ACP OVERLAY : MARTIN COUNTY LINE | Pavement Improvement | 2009-05-28 | 2009-06-29 | 2009-12-01 | 2009-10-15 | 4997459.67 | 10.284
11028 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | MORRIS |  | 04 | 2009540 | SPN:0222-03-056-WIDEN TO ADD SHOULDERS AND RESURFACE 4-LANE DIVIDED RURAL HIGHWAY : 0.7 MI. E. OF US 259 | Pavement Improvement | 2009-05-28 | 2009-07-01 | 2009-10-01 |  | 991156.2 | 2.021
11029 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZORIA |  | 14 | 2009541 | SPN:0178-03-138-ONE-COURSE SURFACE TREATMENT, ASPHALT CONCRETE PAVEMENT OVERLAY, LOOP DETECTORS AND PAVEMENT MARKERINGS : SOUTH OF SH 35 BYPASS | Pavement Improvement | 2009-06-08 | 2009-07-06 | 2009-11-01 | 2009-11-23 | 3047898.69 | 16.010
11030 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | Multiple | 2009542 | SPN:0502-01-203-FULL DEPTH CONCRETE REPAIR AND REPAIR OF SPALLING IN CONCRETE PAVEMENT : SHELL OVERPASS | Pavement Improvement | 2009-06-29 | 2009-07-30 | 2009-11-01 |  | 882735.48 | 4.397
11031 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 22 | 2009543 | SPN:3223-01-009-BASE REPAIR AND OVERLAY : US 90A | Pavement Improvement | 2009-06-05 | 2009-06-23 | 2009-11-01 | 2009-08-05 | 188597.81 | 1.021
11032 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2009544 | SPN:0912-37-200-FAULT LINE BASE REPAIRS : VARIOUS LOCATIONS ON IH 45, LP 336 | Pavement Improvement | 2009-06-02 | 2009-06-18 | 2009-11-01 | 2009-07-22 | 426244.36 | 0.001
11033 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 22 | 2009545 | SPN:0188-01-036-REPLACE ASPHALT WITH CONCRETE : US 90A | Pavement Improvement | 2009-06-05 | 2009-07-30 | 2009-11-01 | 2009-10-20 | 1269484.81 | 0.369
11034 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON |  | 14 | 2009546 | SPN:0389-11-057-BASE REPAIRS, MILLING & 1.5" ASPHALT OVERLAY : FM 1765 | Pavement Improvement | 2009-06-05 | 2009-07-13 | 2009-11-01 | 2009-09-21 | 646223.04 | 1.770
11035 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZORIA |  | 14 | 2009547 | SPN:1004-02-014-ASPHALT OVERLAY AND PAVEMENT MARKINGS : FM1301 ;SPN:1413-01-016-ASPHALT OVERLAY AND PAVEMENT MARKINGS : SH 35 | Pavement Improvement | 2009-06-02 | 2009-07-21 | 2009-11-01 | 2009-12-07 | 1360458.79 | 11.799
11036 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | Multiple | 2009548 | SPN:0027-06-055-BASE REPAIR AND OVERLAY : WHARTON COUNTY LINE | Pavement Improvement | 2009-06-04 | 2009-07-23 | 2009-11-01 | 2009-11-10 | 1118221.98 | 9.741
11037 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2009549 | SPN:0177-14-026-WIDEN SUBGRADE, OCST AND ACP OVERLAY : US 59 | Pavement Improvement | 2009-06-02 | 2009-06-18 | 2010-07-01 | 2010-06-17 | 4317263.89 | 8.022
11038 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 14 | 2009550 | SPN:1258-02-031-BASE REPAIR AND OVERLAY : FM 1489 | Pavement Improvement | 2009-05-27 | 2009-06-17 | 2009-11-01 | 2009-09-28 | 820473.22 | 4.704
11039 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2009551 | SPN:0523-02-030-ADD SHOULDERS AND ACP OVERLAY : BU US 290 | Pavement Improvement | 2009-06-02 | 2009-11-16 | 2009-12-01 |  | 961664.41 | 0.971
11040 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | 10 | 2009552 | SPN:3050-03-016-GRADING, LIME TREATED SUBGRADE, CEMENT TREATED BASE, ASPHALTIC OVERLAY AND PAVMENT MARKINGS : 0.140 MI N. OF HUFSMITH KUYKENDAHL | Pavement Improvement | 2009-06-12 | 2009-06-28 | 2009-11-01 | 2009-11-02 | 267020.96 | 0.369
11041 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | 07 | 2009553 | SPN:0050-08-088-CRACK & SPALL REPAIR, FULL DEPTH CONCRETE REPAIR (IN SECTIONS) : SH 6 | Pavement Improvement | 2009-06-04 | 2009-06-24 | 2009-11-01 | 2009-08-12 | 118220 | 3.845
11042 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | Multiple | 2009554 | SPN:1258-04-058-2" PLANING, 2" ACP OVERLAY, PAVEMENT MARKINGS : DAIRY ASHFORD | Pavement Improvement | 2009-06-05 | 2009-08-17 | 2009-11-01 | 2009-10-16 | 4459705.68 | 8.923
11043 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2009555 | SPN:0527-02-015-SUBGRADE WIDENING, SEAL COAT, ACP O/L AND PAVEMENT MARKINGS : FM 359 | Pavement Improvement | 2009-06-08 | 2009-09-01 | 2009-11-01 | 2010-05-21 | 2035566.78 | 7.292
11044 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON |  | 14 | 2009556 | SPN:0367-02-073-RAISE, REHABILITATE AND OVERLAY (TO 5 YR. STORM ELEVATION) : INTERSECTION AT SH 124 ;SPN:0367-03-035-REHABILITATE AND OVERLAY (TO 5 YR. STORM ELEVATION) : CRYSTAL BEACH ;SPN:0367-04- | Pavement Improvement | 2009-06-02 | 2009-06-18 | 2009-12-01 | 2010-06-24 | 6167954.73 | 21.338
11045 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | 02 | 2009557 | SPN:0028-02-087-MILL, SEAL COAT, BASE REPAIR AND ACP OVERLAY : W OF KRENEK | Pavement Improvement | 2009-06-08 | 2009-07-06 | 2009-11-01 | 2009-11-02 | 1130908.04 | 2.072
11046 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 22 | 2009558 | SPN:0111-03-054-BASE REPAIR AND OVERLAY : SH 6 | Pavement Improvement | 2009-06-05 | 2009-07-08 | 2009-11-01 | 2009-09-08 | 653888.42 | 4.807
11047 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2009559 | SPN:0523-02-041-SEAL COAT AND 1.5" OVERLAY, PAVEMENT MARKINGS : 0.5 MI N. OF CLAPP RD | Pavement Improvement | 2009-06-04 | 2009-06-22 | 2009-11-01 | 2009-08-25 | 614106.5 | 3.492
11048 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | NACOGDOCHES |  | 01 | 2009560 | SPN:0138-06-039-RESURFACE WITH POROUS FRICTION COURSE : RUSK COUNTY LINE | Pavement Improvement | 2009-06-02 | 2009-07-21 | 2009-09-01 | 2009-11-23 | 3217445.02 | 6.327
11049 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BURLESON |  | 17 | 2009561 | SPN:0648-03-046-WIDEN TO 4 LANE DIVIDED HIGHWAY : FM 50 | Pavement Widening | 2009-06-16 | 2009-06-27 | 2011-01-01 |  | 7505830.38 | 2.752
11050 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SHELBY |  | 01 | 2009562 | SPN:0743-02-022-RECONSTRUCT AND WIDEN EXISTING PAVEMENT : NACOGDOCHES CO LINE | Pavement Improvement | 2009-06-18 | 2009-07-27 | 2010-06-01 | 2010-06-14 | 1161712.34 | 5.457
11051 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | SHELBY |  | 01 | 2009563 | SPN:0175-02-080-REHAB EXISTING PAVEMENT : TENAHA CITY LIMITS | Pavement Improvement | 2009-06-12 | 2009-08-25 | 2010-08-01 |  | 4664748.68 | 9.375
11052 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | HOUSTON |  | 06 | 2009564 | SPN:0937-03-015-RECONSTRUCT AND WIDEN EXISTING PAVEMENT : SH 21 | Pavement Improvement | 2009-06-17 | 2009-06-26 | 2010-08-01 | 2010-07-06 | 2356956.12 | 11.173
11053 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MORRIS, TITUS |  | 04 | 2009565 | SPN:0222-01-046-OVERLAY 4-LANE RURAL HIGHWAY WITH ASPHALTIC CONCRETE : 1.6 MI WEST OF FM 2348 ;SPN:0222-02-051-OVERLAY 4-LANE RURAL HIGHWAY WITH ASPHALTIC CONCRETE : TITUS COUNTY LINE | Pavement Improvement | 2009-07-09 | 2009-07-22 | 2009-11-01 | 2010-08-04 | 4699268.05 | 7.400
11054 | Underway | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | PANOLA |  | 01 | 2009566 | SPN:0247-02-043-WIDEN TO ADD SHOULDERS AND RESURFACE 4-LANE RURAL HIGHWAY : 0.1 MI. S. OF MILL CREEK | Pavement Improvement | 2009-06-12 | 2009-06-30 | 2009-10-01 |  | 2384758.4 | 3.187
11055 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CASS |  | Multiple | 2009568 | SPN:0569-01-048-WIDEN TO ADD SHOULDERS AND RESURFACE 2-LANE RURAL HIGHWAY : SOUTH OF FM 2328 | Pavement Improvement | 2009-06-05 | 2009-07-24 | 2010-06-01 |  | 886614.14 | 3.024
11056 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | CASS |  | 04 | 2009569 | SPN:0277-03-024-WIDEN TO ADD SHOULDERS AND RESURFACE 2-LANE RURAL HIGHWAY : SH 8 IN DOUGLASSVILLE ;SPN:0277-03-025-WIDEN TO ADD SHOULDERS AND RESURFACE 2-LANE RURAL HIGHWAY : FM 96 | Pavement Improvement | 2009-05-22 | 2009-06-15 | 2010-07-01 |  | 2023245.06 | 11.305
11057 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BROWN |  | 11 | 2009570 | SPN:0054-06-090-MILL AND OVERLAY : 0.5 MI. W OF FM 3254 | Pavement Improvement | 2009-06-05 | 2009-08-05 | 2009-10-01 | 2009-11-20 | 1495948.09 | 3.055
11058 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | NAVARRO |  | 06 | 2009571 | SPN:0997-01-038-OV-ASPHALTIC CONCRETE PAVEMENT, OVERLAY, RESTORE PAVEMENT STRUCTURE AND UPGRADE DRAINAGE : FM 744 ;SPN:1289-01-028-OV-ASPHALTIC CONCRETE PAVEMENT, OVERLAY, RESTORE PAVEMENT STRUCTURE A | Pavement Improvement | 2009-06-22 | 2009-07-08 | 2010-12-01 |  | 7287236.14 | 14.329
11059 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LEON |  | 06 | 2009572 | SPN:0426-03-037-RESTORE EXISTING ROAD CONSISTING OF GRADING, FLEXIBLE BASE, SURFACE AND PAVEMENT MARKINGS AND MARKERS : 2.5 MILES NORTH OF SH 7 | Pavement Improvement | 2009-07-06 | 2009-08-17 | 2010-04-01 | 2009-10-14 | 369716.71 | 2.534
11060 | Underway | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | HOPKINS |  | 04 | 2009575 | SPN:0083-02-046-REHAB WITH SHOULDERS : 0.47 MI EAST OF FM 2653 S | Pavement Improvement | 2009-08-21 | 2009-08-31 | 2011-06-01 |  | 4160215 | 3.447
11061 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2009576 | SPN:0510-01-022-REHABILITATE EXISTING ROADWAY : SH 289 | Pavement Improvement | 2009-05-28 | 2009-06-30 | 2010-06-01 | 2009-11-17 | 1876832.4 | 5.895
11062 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LAMAR |  | 04 | 2009577 | SPN:0680-01-012-REHAB EXIST ROAD : 3.38 MILES N OF FM 1497 | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2010-05-01 | 2010-04-23 | 896178.3 | 3.380
11063 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2009578 | SPN:0729-01-034-REHABILITATE EXISTING ROADWAY : US 377 | Pavement Improvement | 2009-06-02 | 2009-06-16 | 2010-11-01 |  | 3701118.28 | 11.354
11064 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | LAMAR |  | 04 | 2009579 | SPN:1320-01-021-REHAB EXIST ROAD : FM 1497 NORTH | Pavement Improvement | 2009-06-02 | 2009-06-04 | 2011-09-01 |  | 2447477.14 | 10.320
11065 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GREGG |  | 01 | 2009580 | SPN:0096-06-071-PLANE & RESURFACE ROADWAY : SP 63/SH 31 IN LONGVIEW, E | Pavement Improvement | 2009-06-05 | 2009-06-22 | 2009-11-01 | 2009-10-21 | 1712304.61 | 2.874
11066 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | ANDERSON |  | 05 | 2009581 | SPN:0123-01-034-ADD SHOULDERS & RESURFACE ROADWAY : 3 MI E OF FM 3266, E OF P`STINE, E | Pavement Improvement | 2009-06-02 | 2009-06-26 | 2010-11-01 |  | 4110707.46 | 5.602
11067 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WOOD |  | 05 | 2009582 | SPN:0190-03-076-PLANE & RESURFACE ROADWAY : FM 564(N) IN MINEOLA, S ;SPN:0190-03-077-PLANE & RESURFACE ROADWAY : US 69/SH 37 SPLIT IN MINEOLA, S | Pavement Improvement | 2009-05-22 | 2009-06-17 | 2009-11-01 | 2009-10-14 | 1637663.52 | 2.377
11068 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2009583 | SPN:0190-05-058-RESURFACE ROADWAY : 0.134 MI N OF IH 20 IN LINDALE, S | Pavement Improvement | 2009-06-02 | 2009-07-20 | 2009-11-01 | 2009-12-28 | 2236906.91 | 7.045
11069 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GREGG |  | 01 | 2009584 | SPN:0393-01-088-PLANE & RESURFACE ROADWAY : IH 20 N FRONTAGE RD, N | Pavement Improvement | 2009-05-19 | 2009-06-16 | 2009-10-01 | 2010-01-07 | 2066492.08 | 3.620
11070 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | VAN ZANDT |  | 05 | 2009586 | SPN:0522-02-028-CONCRETE SURFACE REPAIR OF BRIDGE STRUCTURES : AT CANEY CRK, CANEY CREEK RELIEF | Pavement Improvement | 2009-06-16 | 2009-07-06 | 2009-10-01 | 2009-08-21 | 61344 | 0.133
11071 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BELL |  | 31 | 2009588 | SPN:0015-05-043-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : FM 93 (6TH AVE) IN BELTON, SOUTH ;SPN:0398-04-067-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : 13TH ST IN BELTON, SOUTH | Pavement Improvement | 2009-06-04 | 2009-06-22 | 2009-09-01 | 2009-10-14 | 1287407.66 | 1.607
11072 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | CORYELL |  | 31 | 2009589 | SPN:0055-03-023-REHABILITATE ROADWAY, ADD PASSING LANES AND SHOULDERS : FM 932 | Pavement Improvement | 2009-06-18 | 2009-06-24 | 2011-06-01 |  | 8735023.01 | 10.235
11073 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CORYELL |  | 31 | 2009590 | SPN:0231-02-050-CONSTRUCT OVERPASS FOR FT HOOD ACCESS : @ RAILHEAD RD | New Bridge Construction | 2009-08-10 | 2009-08-24 | 2010-04-01 |  | 2368151.52 | 2.642
11074 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BELL |  | 31 | 2009591 | SPN:3534-02-002-ADD TURN LANES, TRAFFIC SIGNAL AND LIGHTING FOR IMPROVED ACCESS TO WEST FT HOOD : @ MOHAWK DRIVE IN KILLEEN | Pavement Improvement | 2009-06-09 | 2009-06-23 | 2010-04-01 |  | 1220438.55 | 0.800
11075 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WILBARGER |  | 13 | 2009592 | SPN:0043-07-104-SEAL COAT AND HMAC OVERLAY : NEAR US 70 IN OKLAUNION | Pavement Improvement | 2009-06-09 | 2009-08-19 | 2009-12-01 | 2010-05-19 | 2515911.53 | 7.273
11076 | Underway | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | ARCHER |  | 19 | 2009593 | SPN:0137-05-028-EXTEND CULVERTS AND ADD SHOULDERS : FM 368 | Pavement Improvement | 2009-06-09 | 2009-08-12 | 2010-10-01 |  | 3147193.46 | 9.364
11077 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | COOKE |  | 26 | 2009594 | SPN:0194-02-088-HEAVY HOT MIX OVERLAY : NEAR RED RIVER | Pavement Improvement | 2009-06-05 | 2009-08-12 | 2009-11-01 | 2009-11-20 | 2396645.99 | 5.765
11078 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | COOKE |  | Multiple | 2009595 | SPN:1855-01-021-ADD SHOULDERS : FM 372 | Pavement Improvement | 2009-06-22 | 2009-07-14 | 2010-12-01 |  | 2108363.87 | 8.579
11079 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | RUSK |  | 01 | 2009596 | SPN:0138-02-034-PLANE & RESURFACE ROADWAY : US/BU 259 SPLIT, S OF KILGORE, S | Pavement Improvement | 2009-05-22 | 2009-06-10 | 2009-11-01 | 2009-12-11 | 2886918.15 | 5.100
11080 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS |  | Multiple | 2009597 | SPN:3136-01-162-MILL, SEAL & THIN OVERLAY : COLORADO RIVER | Pavement Improvement | 2009-06-12 | 2009-07-28 | 2009-10-01 | 2009-11-03 | 1696542.45 | 2.818
11081 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS |  | 25 | 2009598 | SPN:3136-01-166-MILL, SEAL, AND OVERLAY : GAINES CREEK | Pavement Improvement | 2009-06-16 | 2009-07-06 | 2009-10-01 | 2009-10-13 | 943846.86 | 2.000
11082 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DENTON |  | 26 | 2009599 | SPN:0918-46-217-REPLACE BRIDGE AND APPROACHES : ON FREEMAN RD | Pavement Improvement | 2009-07-02 | 2009-08-26 | 2010-05-01 | 2010-07-12 | 203297 | 0.001
11083 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DALLAS | DALLAS-FORT WORTH | Multiple | 2009600 | SPN:1047-02-044-INTERSECTION APPROACH WIDENING, SIGNAL UPGRADES AND TURN LANES AT STRAUS ROAD : AT STRAUS RD ;SPN:1047-03-062-INTERSECTION APPROACH WIDENING, SIGNAL UPGRADES AND TURN LANES AT STRAUS R | Pavement Improvement | 2009-05-28 | 2009-06-22 | 2009-10-01 | 2010-04-22 | 1388408.1 | 0.167
11084 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | KAUFMAN |  | 05 | 2009601 | SPN:1091-01-016-REPLACE BRIDGE AND APPROACHES : BUFFALO CREEK ;SPN:1091-01-018-REPLACE BRIDGE AND APPROACHES : BUFFALO CREEK RELIEF | Pavement Improvement | 2009-09-28 | 2010-02-16 | 2010-11-01 |  | 2856520.65 | 0.323
11085 | Underway | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | KAUFMAN |  | 05 | 2009602 | SPN:1397-01-021-REPLACE BRIDGE AND APPROACHES : AT BIG COTTONWOOD CREEK ;SPN:1397-01-022-REPLACE BRIDGE AND APPROACHES : AT LITTLE COTTONWOOD CREEK | Pavement Improvement | 2009-06-29 | 2009-09-11 | 2010-06-01 |  | 1708659.34 | 0.402
11086 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | PARKER |  | 12 | 2009603 | SPN:0008-03-096-2 INCH OVERLAY : SPUR 312 | Pavement Improvement | 2009-06-05 | 2009-08-03 | 2009-11-01 | 2010-03-11 | 3224420.39 | 7.517
11087 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 12 | 2009604 | SPN:0008-14-110-PAVEMENT AND BRIDGE JOINT REPAIR WITH 2" HMAC OVERLAY : MARINE CREEK PARKWAY | Pavement Improvement | 2009-05-22 | 2009-06-15 | 2009-12-01 |  | 3967559.84 | 4.983
11088 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2009605 | SPN:0013-08-117-PLANE AND TEXTURIZE CRCP NORTHBOUND LANES : 1355` S OF CR 4840 ;SPN:0013-08-118-PLANE AND TEXTURIZE CRCP NORTHBOUND : NBL 1300` S OF CR 4421 ;SPN:0013-08-120-MILL ASPHALT, CONCRETE R | Pavement Improvement | 2009-06-12 | 2009-07-06 | 2009-11-01 | 2009-11-13 | 1846266.94 | 9.526
11089 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | ERATH, HOOD, JOHNSON |  | Multiple | 2009606 | SPN:0080-03-050-MILL 2" AND HMAC OVERLAY : BRAZOS RIVER BRIDGE ;SPN:0080-05-027-MILL 2" AND HMAC OVERLAY : PARKER COUNTY LINE ;SPN:0250-07-014-MILL AND HMAC OVERLAY : BU 377J ;SPN:0365-02-028-MILL | Pavement Improvement | 2009-06-09 | 2009-07-27 | 2009-10-01 | 2009-10-08 | 1658039.41 | 7.483
11090 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2009607 | SPN:0259-04-036-PAVEMENT REPAIR AND OVERLAY : APPROX. 120 FT WEST OF FM 2331 ;SPN:0422-03-070-PAVEMENT REPAIR AND HOTMIX OVERLAY : PR 21 | Pavement Improvement | 2009-05-22 | 2009-06-15 | 2009-10-01 | 2009-10-07 | 503662.32 | 2.314
11091 | Completed | C250 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2009608 | SPN:0352-01-054-MILL AND HMAC OVERLAY : 0.33 MILE SOUTH OF US 380 INTERSECT | Pavement Improvement | 2009-06-16 | 2009-08-17 | 2009-10-01 | 2009-10-26 | 553102.84 | 1.208
11092 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 26 | 2009609 | SPN:0363-01-133-PAVEMENT REPAIR, 2" MILLING, AND 2" HMAC OVERLAY WITH PAVEMENT MARKINGS : NEAR FM 1938 | Pavement Improvement | 2009-06-02 | 2009-07-01 | 2009-11-01 | 2009-09-16 | 513264.2 | 3.220
11093 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | PARKER |  | 12 | 2009610 | SPN:0365-01-042-MILL 1.5 INCH, FABRIC, HMAC OVERLAY AND TRAFFIC SIGNAL LOOPS : US 180 | Pavement Improvement | 2009-06-04 | 2009-06-15 | 2009-09-01 | 2009-09-28 | 591312.34 | 1.200
11094 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2009611 | SPN:0019-01-135-HMAC OVERLAY : WILLINGHAM STREET ;SPN:0019-02-030-HMAC OVERLAY : AT&SF RAILROAD ;SPN:0519-01-026-HMAC OVERLAY : NORTH OF RIO VISTA | Pavement Improvement | 2009-06-09 | 2009-07-28 | 2009-11-01 |  | 1833526.78 | 8.631
11095 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 06 | 2009613 | SPN:0747-03-076-REPAIR FAILURES AND OVERLAY WITH 2 INCHES : COPELAND ROAD | Pavement Improvement | 2009-06-05 | 2009-07-01 | 2009-09-01 | 2009-08-12 | 420119.98 | 1.393
11096 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | Multiple | 2009614 | SPN:0902-48-745-VARIOUS LOCATIONS FOR EXPANSION JOINT REPAIRS IN NORTH TARRANT COUNTY : VARIOUS LOCATIONS | Pavement Improvement | 2009-06-05 | 2009-06-28 | 2010-02-01 |  | 1065751 | 0.100
11097 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | PARKER |  | 12 | 2009615 | SPN:3516-01-014-REHAB EXISTING ROADWAY WITH PAVEMENT REPAIRS AND OVERLAY : FM 1886 | Pavement Improvement | 2009-10-30 | 2010-03-29 |  | 2010-07-09 | 587643.05 | 3.143
11098 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CHAMBERS |  | 14 | 2009622 | SPN:0242-03-068-OVERLAY EXISTING ROADWAY & SEAL COAT : LIBERTY CO/L, SOUTH | Pavement Improvement | 2009-05-28 | 2009-06-23 | 2009-09-01 | 2009-11-13 | 715086.04 | 4.390
11099 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2009623 | SPN:1048-02-031-REPLACE BRIDGE AND APPROACHES : AT TRIBUTARY OF BEAR CREEK . | Bridge Replacement | 2010-05-03 | 2010-05-03 |  |  | 320650 | 0.090
11100 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | GUADALUPE |  | 28 | 2009624 | SPN:0535-01-065-RESTORE EXISTING ROADWAY WITH CRCP : 0.44 MI W OF SH 46 | Pavement Improvement | 2009-09-18 | 2009-10-04 | 2011-09-01 |  | 1784603.23 | 0.550
11101 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MATAGORDA |  | 14 | 2009625 | SPN:0179-04-089-ASPHALTIC CONCRETE PAVEMENT : SOUTH OF FM 457 | Pavement Improvement | 2009-06-04 | 2009-07-10 | 2009-08-01 | 2009-10-02 | 567067.43 | 1.895
11102 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WHARTON |  | 14 | 2009626 | SPN:2819-02-009-PAVEMENT REPAIR AND ACP SURFACING : 0.14 MI. SOUTHWEST OF SH 71 | Pavement Improvement | 2009-06-12 | 2009-07-06 | 2009-09-01 | 2009-11-25 | 745789.63 | 2.402
11103 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2009627 | SPN:0092-10-007-REHABILITATE EXISTING ROADWAY : DALLAS COUNTY LINE | Pavement Improvement | 2009-08-07 | 2009-08-28 | 2010-10-01 | 2010-07-08 | 1284123.14 | 2.285
11104 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | MASON |  | 11 | 2009632 | SPN:0149-04-015-SEAL COAT : US 87 ;SPN:0396-02-024-SEAL COAT : MENARD C/L | Pavement Improvement | 2009-07-02 | 2009-06-22 | 2009-09-01 | 2009-10-19 | 1045214.63 | 27.578
11105 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2009633 | SPN:0013-08-114-3 INCH OVERLAY AND CONCRETE TEXTURE SOUTHBOUND LANES : SBL FROM 475` S OF US 380 | Pavement Improvement | 2009-06-16 | 2009-08-24 | 2009-10-01 | 2010-06-01 | 1309578.7 | 12.750
11106 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | BURNET |  | 11 | 2009634 | SPN:2206-01-013-OVERLAY : 11.7 MI N OF SH 29 | Pavement Improvement | 2009-06-22 | 2009-06-29 | 2009-10-01 | 2010-02-17 | 1444444 | 9.444
11107 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | CALDWELL |  | 25 | 2009635 | SPN:0286-02-028-PAVEMENT REPAIR,MILL,SEAL & OVERLAY : 0.35 MILES WEST OF HAYS C/L | Pavement Improvement | 2009-07-06 | 2009-08-10 | 2009-10-01 | 2009-09-03 | 3794304.93 | 11.695
11108 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2009636 | SPN:0013-08-116-MILL ASPHALT, CONCRETE REPAIRS, OVERLAY 2 INCHES : 2750` N OF PIONEER ROAD | Pavement Improvement | 2009-06-16 | 2009-08-24 | 2009-10-01 | 2010-06-01 | 732136.28 | 3.289
11109 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | WILSON |  | 28 | 2009637 | SPN:0215-11-020-WIDEN EXISTING ROADWAY TO ADD SHOULDERS : UNION AT CR 448 GONZALES COUNTY LINE | Pavement Improvement | 2010-04-22 | 2010-04-22 |  |  | 1576833.88 | 4.955
11110 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | ATASCOSA |  | 28 | 2009638 | SPN:0517-01-040-WIDEN EXISTING ROADWAY TO PROVIDE PASSING LANES : 0.3 S OF FM 1332 | Pavement Improvement | 2009-10-13 | 2009-10-26 |  |  | 1849585.53 | 17.779
11111 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | HENDERSON |  | 05 | 2009639 | SPN:0163-04-053-PLANE & RESURFACE ROADWAY : 1.2 MI E OF SH 198 IN MALAKOFF, E | Pavement Improvement | 2009-06-02 | 2009-06-25 | 2009-10-01 | 2010-01-13 | 1994407.08 | 4.944
11112 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LEE |  | 10 | 2009640 | SPN:3114-01-010-LEVEL-UP & SEAL COAT : US 290 | Pavement Improvement | 2009-06-22 | 2009-07-27 | 2009-09-01 | 2009-10-06 | 519810.19 | 13.155
11113 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | LIVE OAK |  | 15 | 2009646 | SPN:0542-06-041-CONSTRUCT FOUR LANE BOULEVARD : US 281 ;SPN:0542-07-008-CONSTRUCT 4 LANE BOULEVARD : BU 59 INTERSECTION ;SPN:0542-07-012-CONSTRUCT RAILROAD GRADE SEPARATION STRUCTURE AND APPROACHES | Pavement Widening | 2009-10-21 | 2010-01-04 |  |  | 17155044.24 | 3.953
11114 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | JIM WELLS |  | 15 | 2009647 | SPN:0255-01-074-CONSTRUCT DIAMOND INTERCHANGE : 0.95 MI. N. OF FM 2508 | Pavement Widening | 2009-09-14 | 2009-11-16 | 2011-12-01 |  | 13000000 | 1.840
11115 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2009648 | SPN:0156-14-027-"ULTRA THIN BONDED HOT MIX WEARING COURSE (UTBHMWC)" : LP 11 | Pavement Improvement | 2009-08-04 | 2009-08-26 | 2009-10-01 | 2009-10-08 | 788364.75 | 1.706
11116 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | 25 | 2009650 | SPN:0016-02-104-REPLACE BRIDGE AND APPROACHES & WIDEN FRONTAGE ROADS : 2250 FT N OF MAIN ST | Pavement Improvement | 2009-10-09 | 2009-11-02 |  |  | 7000000 | 0.777
11117 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009651 | SPN:0086-16-002-FOR THE CONSTRUCTION OF A NEW LOCATION 4 LANE DIVIDED ROADWAY : 4.8 MILES SOUTH OF SH 359 ;SPN:0086-16-003-FOR THE CONSTRUCTION OF A NEW LOCATION 4 LANE DIVIDED ROADWAY : 1.0 MILES SOU | New Construction | 2009-10-16 | 2009-11-16 |  |  | 21758949 | 4.701
11118 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009652 | SPN:0086-16-001-FOR THE CONSTRUCTION OF A NEW LOCATION 2 LANE ROADWAY : MANGANA-HEIN ROAD | New Construction | 2009-10-16 | 2009-11-16 |  |  | 9660310.81 | 2.267
11119 | Underway | C240,C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 21 | 2009653 | SPN:0253-04-139-US 281 Fr. AT LP 1604 To. . ; EXPAND INTERCHANGE WITH SOUTHERN DIRECT CONN'S (PHASE 1) | Pavement Improvement | 2010-05-24 | 2010-05-25 | 2013-08-20 |  | 80000000 | 1.610
11120 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | Multiple | 2009655 | SPN:2452-03-103-EXPAND FROM 2 LANES TO 4 LANE DIVIDED : FM 78 GRAYTOWN ROAD | Pavement Widening | 2010-04-11 | 2010-04-12 |  |  | 6631042.98 | 0.001
11121 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZOS |  | 17 | 2009657 | SPN:0050-02-082-CONSTRUCT NEW INTERCHANGE CONSISTING OF GRADING, STRUCTURES, BASE AND SURFACE - FUNDING CSJ FOR 0050-02-094 : AT BARRON ROAD | Pavement Improvement | 2009-06-29 | 2009-07-17 | 2011-03-01 |  | 7907149.79 | 1.676
11122 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | Multiple | 2009658 | SPN:3256-02-074-CONSTRUCT 4 DIRECT CONNECTORS : AT US 59 NORTH | New Bridge Construction | 2009-10-06 | 2009-10-15 |  |  | 29595089.52 | 1.624
11123 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON | MCALLEN-PHARR-EDINBURG | 27 | 2009662 | SPN:0684-01-066-CONSTRUCT TOLLED MAINLANES AND FRONTAGE ACCESS : 0.70 MI N OF FM 3248 OLD PORT ISABEL RD;SPN:3622-01-001-CONSTRUCT TOLLED MAINLANES AND FRONTAGE ACCESS : OLD PORT ISABEL RD, ON NEW L | New Construction | 2010-05-13 |  |  |  | 34161741.4 | 3.926
11124 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BROOKS |  | 15 | 2009663 | SPN:0255-03-026-CONSTRUCT 4 LANE EXPRESSWAY_WITH TOLLED MAIN LANES : BUS 281 NORTH SIDE ;SPN:0255-04-072-CONSTRUCT 4 LANE EXPRESSWAY_WITH TOLLED MAIN LANES : 0.9 MILES SOUTH OF FM 3066 | Pavement Widening | 2009-07-14 | 2009-08-18 | 2012-08-01 |  | 40039527.42 | 5.581
11125 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BROOKS |  | 15 | 2009664 | SPN:0255-14-001-CONSTRUCT 4 LANE EXPRESSWAY WITH TOLLED MAIN LANES : BUS 281 NORTH SIDE | Pavement Widening | 2009-07-14 | 2009-08-18 | 2012-08-01 |  | 25860723.89 | 2.062
11126 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | RUNNELS, TOM GREEN, COLEMAN |  | 11 | 2009665 | SPN:7107-09-001-REHABILITATION OF SOUTH ORIENT RR;SPN:7107-10-001-REHABILITATION OF SOUTH ORIENT RR;SPN:7123-11-001-REHABILITATION OF SOUTH ORIENT RR | Other | 2009-09-01 | 2009-09-15 | 2010-12-01 | 2010-04-30 | 5078194.05 | 0.003
11127 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2009679 | SPN:3487-01-013-INSTALL ELECTRONIC TOLL GANTRIES AND EQUIPMENT FOR NEW 2-LN TOLL ROAD (ULTIMATE 4-LANE FACILITY) : SH 31,2.0 MI E OF FM 2661,S & SE ;SPN:3487-02-010-INSTALL ELECTRONIC TOLL GANTRIES AN | Other | 2009-07-21 | 2009-08-06 | 2013-08-01 |  | 3876000 | 9.019
11128 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON |  | Multiple | 2009681 | SPN:0921-06-230-UPRR SWITCHYARD | Other |  |  | 2011-07-30 |  | 3330881.48 | 17.000
11129 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON |  | 27 | 2009682 | SPN:1425-04-020-WIDEN TO 4 LANE DIVIDED : 1.06 MILES S. OF US 77/83 | Pavement Widening | 2009-08-10 | 2010-03-08 | 2010-06-01 |  | 1887239.52 | 0.800
11130 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2009689 | SPN:0921-02-132-WIDEN TO 4 LANES : ON "I" ROAD FROM US 281 SOUTH | Pavement Widening | 2009-09-17 | 2009-10-13 | 2011-03-01 |  | 4071711.18 | 1.761
11131 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009691 | SPN:2879-02-010-INSTALL NEW TRAFFIC SIGNALS : AT ROBIN LANE IN TEXARKANA . | Safety/Traffic Management | 2010-01-25 | 2010-06-09 |  |  | 31344.75 | 0.001
11132 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009692 | SPN:2879-02-011-INSTALL NEW TRAFFIC SIGNALS : AT COOKS LANE IN TEXARKANA . | Safety/Traffic Management | 2010-01-25 | 2010-06-09 |  |  | 31642.95 | 0.001
11133 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009693 | SPN:2879-02-012-UPGRADE EXISTING TRAFFIC SIGNALS : AT COWHORN CREEK ROAD IN TEXARKANA . | Safety/Traffic Management | 2010-01-25 | 2010-06-09 |  |  | 59415.1 | 0.001
11134 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009694 | SPN:0046-06-073-UPGRADE EXISTING TRAFFIC SIGNALS : AT 14TH STREET IN TEXARKANA . | Safety/Traffic Management | 2010-01-25 | 2010-06-09 |  |  | 84165.2 | 0.001
11135 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009695 | SPN:0046-08-014-UPGRADE EXISTING TRAFFIC SIGNALS : AT COLLEGE DRIVE IN TEXARKANA . | Safety/Traffic Management | 2010-01-25 | 2010-06-09 |  |  | 85770 | 0.001
11136 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | SHELBY |  | 01 | 2009696 | SPN:0064-01-064-RESURFACE WITH HOT MIX ASPHALT : JACKSON STREET ;SPN:0109-11-003-RESURFACE WITH HOT MIX ASPHALT : US 287 (N) ;SPN:0118-09-008-RESURFACE WITH HOT MIX ASPHALT : SH 21 ;SPN:0176-06-010 | Pavement Improvement | 2009-07-28 | 2009-10-06 | 2009-09-04 | 2010-02-23 | 1612585.31 | 6.619
11137 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | BRAZORIA | HOUSTON | 14 | 2009697 | SPN:2523-02-030-WIDEN TO 4 LANE DIVIDED SUBURBAN SECTION : SH 288 ;SPN:2523-02-058-CONSTRUCT RAILROAD-HIGHWAY GRADE SEPARATION : AT CR 288 AND UPRR | Pavement Widening | 2009-09-01 | 2009-10-15 | 2010-10-01 |  | 18452982.51 | 3.092
11138 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 09 | 2009699 | SPN:0598-01-089-FRONTAGE ROAD INTERSECTION IMPROVEMENTS (TSM) : AT BW 8 | Pavement Improvement | 2009-10-06 | 2009-10-27 |  | 2010-03-18 | 635655.19 | 0.603
11139 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | WALLER | HOUSTON | 10 | 2009700 | SPN:0523-01-015-WIDEN TO 4-LANE DIVIDED URBAN SECTION : BU 290 | Pavement Widening | 2009-09-09 | 2009-10-19 | 2010-10-01 |  | 2485857.89 | 0.551
11140 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2009701 | SPN:0543-02-047-RECONSTRUCT 2 LANES TO 4 LANES : W OF FARMER ROAD US 90A | Pavement Widening | 2010-04-01 | 2010-04-19 |  |  | 11849354.25 | 2.370
11141 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2009703 | SPN:1415-02-040-WIDEN 2 LANES TO 4 LANES DIVIDED : SHILOH LAKES DR SH 99 | Pavement Widening | 2010-04-14 | 2010-06-14 |  |  | 13235602 | 2.630
11142 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON | HOUSTON | 14 | 2009704 | SPN:1607-01-029-CONSTRUCT GRADE SEPARATION : AT WILLOW STREET EXTENSION | Pavement Improvement | 2010-01-04 | 2010-01-25 |  |  | 10399818.18 | 1.061
11143 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2009705 | SPN:0912-00-396-GULF COAST FREIGHT RAIL DISTRICT (GCFRD) COMMUTER RAIL STUDY | Other | 2010-03-08 | 2010-03-08 | 2013-03-02 |  | 2000000 | 0.001
11144 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2009706 | SPN:0912-00-397-REAL-TIME HWY PERFORMANCE MONITORING : VARIOUS LOCATIONS DISTRICTWIDE . | Safety/Traffic Management | 2010-05-13 |  |  |  | 4073749 | 0.001
11145 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2009707 | SPN:0912-00-398-TMA FREIGHT ANALYSIS | Other | 2010-02-22 | 2010-03-01 | 2012-01-31 |  | 2500000 | 0.001
11146 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2009708 | SPN:0908-33-086-RECONSTRUCT EXIST ROADWAY | Pavement Improvement | 2010-04-15 |  | 2010-09-15 |  | 583112.33 | 1.008
11147 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2009709 | SPN:0908-33-087-REHAB SURFACE | Pavement Improvement | 2010-04-15 |  | 2010-08-15 |  | 394585.85 | 1.913
11148 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2009710 | SPN:0908-33-088-REHAB SURFACE | Pavement Improvement | 2010-04-15 |  | 2010-09-15 |  | 878041.94 | 3.180
11149 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | STARR |  | 28 | 2009711 | SPN:1103-04-025-REHABILITATION OF PAVEMENT, ADD CURB & GUTTER, STORM SEWER AND RESTRIPE TO ONE WAY PAIR : US 83 NORTH | Pavement Improvement | 2009-08-10 | 2009-10-20 | 2011-02-01 |  | 2521180.59 | 0.921
11150 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON |  | 27 | 2009712 | SPN:1425-03-053-OVERLAY : US 77 | Pavement Improvement | 2009-08-19 | 2009-09-21 | 2009-09-01 | 2009-11-02 | 1449742.58 | 3.463
11151 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | POTTER |  | 13 | 2009713 | SPN:0904-02-033-OVERLAY : ON HASTINGS AVE, FROM RIVER ROAD | Pavement Improvement | 2009-10-22 |  |  | 2010-06-25 | 215909.28 | 1.000
11152 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | RANDALL | AMARILLO | 13 | 2009714 | SPN:2635-03-014-UPGRADE TO URBAN SECTION : SW 83RD AVENUE SW 45TH AVENUE | Pavement Widening | 2010-04-22 |  |  |  | 2083226.09 | 1.988
11153 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | RANDALL |  | 13 | 2009715 | SPN:0904-11-046-OVERLAY : ON S GEORGIA ST, FR .3 MI N OF FARM | Pavement Improvement | 2009-11-02 | 2010-01-25 |  |  | 155676.82 | 1.000
11154 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | RANDALL | AMARILLO | 13 | 2009716 | SPN:0904-11-045-2-LANE REHABILITATION : ON HILLSIDE RD, FR LP 335 WEST NANCY ELLEN DRIVE | Pavement Improvement | 2010-04-22 |  |  |  | 451413.53 | 0.435
11155 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | MIDLAND |  | 11 | 2009717 | SPN:0887-01-032-ROADWAY REHABILITATION : CR 1150 FM 1379 | Pavement Improvement | 2010-01-06 | 2010-01-25 |  |  | 5697710.48 | 7.099
11156 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | ECTOR |  | 11 | 2009719 | SPN:3571-01-005-ROADWAY REHABILITATION : SH 191 MIDLAND COUNTY LINE | Pavement Improvement | 2009-12-07 | 2010-02-09 |  | 2010-07-08 | 344886.18 | 0.432
11157 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | MIDLAND |  | 11 | 2009720 | SPN:3571-02-005-ROADWAY REHABILITATION : ECTOR COUNTY LINE BI 20-E | Pavement Improvement | 2009-12-07 | 2010-02-09 |  | 2010-07-08 | 810232.45 | 1.685
11158 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2009721 | SPN:0903-03-093-HIKE AND BIKE TRAIL- PHASE 3 : HAMILTON PARK SCOTT STREET | Transportation Enhancements | 2010-02-01 | 2010-02-16 |  |  | 2582604.07 | 2.900
11159 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | TOM GREEN |  | 11 | 2009724 | SPN:0077-09-005-ASPHALT CONCRETE PAVEMENT OVERLAY : RED ARROYO US 87 | Pavement Improvement | 2009-12-07 | 2010-03-02 |  |  | 2367545.34 | 3.420
11160 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TOM GREEN |  | 11 | 2009725 | SPN:0555-05-021-ASPHALT CONCRETE PAVEMENT OVERLAY : US 67 IN SAN ANGELO BU 67-H | Pavement Improvement | 2010-05-05 | 2010-05-05 |  | 2010-05-08 | 277891.84 | 0.691
11161 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TOM GREEN | SAN ANGELO | 11 | 2009745 | SPN:0158-02-081-ASPHALT CONCRETE PAVEMENT OVERLAY : 1.18 MILES NORTH OF SMITH BLVD SMITH BLVD | Pavement Improvement | 2010-05-03 | 2010-05-03 |  | 2010-05-24 | 316396.66 | 1.180
11162 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | TOM GREEN | SAN ANGELO | 11 | 2009746 | SPN:0907-24-033-REHABILITATE EXISTING ROADWAY | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2011-02-15 |  | 1103076 | 1.000
11163 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | GREGG | LONGVIEW | 01 | 2009748 | SPN:1385-02-021-INSTALL TRAFFIC SIGNAL IN TWO LOCATIONS : AT FM 2275 AND AT CHERYL ST IN LONGVIEW | Safety/Traffic Management | 2010-04-26 | 2010-04-26 |  |  | 185678.15 | 0.200
11164 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | GONZALES |  | 25 | 2009749 | SPN:0215-12-008-WIDEN NARROW ROADWAY & ADD SHOULDERS : WILSON C/L SH 80 | Pavement Improvement |  |  |  |  | 382109.19 | 1.237
11165 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA | VICTORIA | 14 | 2009755 | SPN:0143-10-042-ASPHALTIC CONCRETE PAVEMENT : US 77 RED RIVER ST. IN VICTORIA | Pavement Improvement | 2010-01-07 | 2010-02-01 |  |  | 1338000 | 3.408
11166 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA | VICTORIA | 14 | 2009762 | SPN:0143-10-043-CONSTRUCT TURN LANES : 0.36 MI. WEST OF TROPICAL DR. US 77 IN VICTORIA | Pavement Improvement | 2010-01-07 | 2010-02-01 |  |  | 531000 | 0.671
11167 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA | VICTORIA | 14 | 2009763 | SPN:0144-01-067-ASPHALTIC CONCRETE PAVEMENT : RED RIVER ST. IN VICTORIA BU 59-T | Pavement Improvement | 2010-01-07 | 2010-02-01 |  |  | 137719.52 | 0.492
11168 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA | VICTORIA | 14 | 2009764 | SPN:2350-01-046-CONSTRUCT TURN LANES : 0.24 MI. WEST OF MOCKINGBIRD LN 0.24 MI. EAST OF MOCKINGBIRD LN | Pavement Improvement | 2010-01-07 | 2010-02-01 |  |  | 350837.02 | 0.486
11169 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009781 | SPN:0922-33-126-VA Fr. SL 20 To. 0.6 MI EAST (TO MPO BOUNDARY); RESURFACE OF EXISTING ROADWAY & ADD SHOULDERS ON EAST DEL MAR BLVD | Pavement Improvement |  |  | 2010-09-30 |  | 288953 | 0.600
11170 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009782 | SPN:0922-33-123-VA Fr. US 83 To. 1.0 MI WEST (TO MPO BOUNDARY); RESURFACE OF EXISTING ROADWAY & ADD SHOULDERS ON ESPEJO-MOLINA ROAD | Pavement Improvement |  |  | 2010-10-31 |  | 434779 | 1.000
11171 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009783 | SPN:0922-33-124-RESURFACE EXISTING ROADWAY | Pavement Improvement |  |  | 2010-11-30 |  | 1751729.8 | 5.000
11172 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO |  | 15 | 2009785 | SPN:0039-17-167-CONSTRUCT OVERPASS : 0.30 MILES WEST OF FM 396 0.30 MILES EAST OF FM 396 | Pavement Improvement | 2010-05-17 |  |  |  | 10000000 | 0.600
11173 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | Multiple | 2009786 | SPN:0915-12-466-INSTALL WARNING DEVICES AT LOW WATER CROSSINGS | Safety/Traffic Management | 2010-06-30 | 2010-06-30 | 2010-10-29 |  | 550000 | 0.001
11174 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 20 | 2009787 | SPN:0915-12-467-CS Fr. EAGLELAND DRIVE To. LONESTAR; EAGLELAND/RIVERWALK LINK TO MISSION TRAILS | Transportation Enhancements |  |  | 2010-11-30 |  | 403073.56 | 0.200
11175 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | NUECES | CORPUS CHRISTI | 27 | 2009789 | SPN:1069-01-030-CONSTR. MEDIAN, CONGEST. MGMT. & ADA IMPROVEMENTS : ON SARATOGA FROM STAPLES ST. RODD FIELD RD. | Pavement Improvement | 2010-07-08 |  |  |  | 3800000 | 2.010
11176 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | NUECES | CORPUS CHRISTI | 27 | 2009790 | SPN:2343-01-031-CONSTR. MEDIAN, CONGEST. MGMT. & ADA IMPROVEMENTS : ON STAPLES ST. FROM SARATOGA BLVD. OSO CREEK BRIDGE | Pavement Improvement | 2010-07-08 |  |  |  | 3464791 | 2.250
11177 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | Multiple | 2009792 | SPN:0912-34-126-WIDEN TO 4 LANES CURB & GUTTER : STAFFORD/STAFFORDSHIRE,HARRIS C/L 5TH STREET | Pavement Widening | 2010-05-11 | 2010-06-07 |  |  | 4500000 | 2.211
11178 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2009801 | SPN:0092-08-015-REHABILITATE EXISTING ROADWAY : SOUTH OF SH 34 IN ENNIS | Pavement Improvement | 2009-08-26 | 2009-09-15 | 2010-08-01 | 2010-05-05 | 1727611.14 | 2.260
11179 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CALLAHAN |  | 19 | 2009804 | SPN:0181-03-024-PLANNING, UNDERSEAL, ASPHALT CONCRETE PAVEMENT OVERLAY, AND METAL BEAM GUARD FENCE : US 283 ;SPN:0452-02-034-PLANNING, UNDERSEAL, ASPHALT CONCRETE PAVEMENT OVERLAY, AND METAL BEAM GUAR | Pavement Improvement | 2009-08-06 | 2009-08-10 | 2010-02-01 | 2009-11-20 | 4960299.07 | 18.082
11180 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN PATRICIO |  | 15 | 2009805 | SPN:0372-01-093-OVERLAY ROADWAY : ODEM N. CITY LIMITS | Pavement Improvement | 2009-09-09 | 2009-09-25 | 2009-02-01 | 2010-04-12 | 1964947.15 | 4.182
11181 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON | DALLAS-FORT WORTH | 17 | 2009834 | SPN:0422-05-001-WIDEN ROADWAY TO FOUR LANE DIVIDED WITH DIAMOND INTERCHANGE AT PROPOSED SH 121/NOLAN RIVER ROAD : 0.6 MI EAST OF FM 4 SH 174 | Pavement Widening | 2010-01-25 | 2010-03-04 |  |  | 7728131 | 2.329
11182 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON | DALLAS-FORT WORTH | 17 | 2009835 | SPN:0259-06-005-CONSTRUCT RAMPS AT INTERCHANGE WITH SH 174 EB/WB AND ADD MEDIAN BARRIER : SH 174 0.9 MI EAST OF SH 174 | Pavement Improvement | 2010-01-25 | 2010-03-04 |  |  | 2271868.44 | 0.909
11183 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2009837 | SPN:0192-01-086-RECONFIGURE AND UPGRADE TRAFFIC SIGNAL SYSTEM AT INTERSECTION (RCTSS) : FM 1092/UNIVERSITY BLVD | Safety/Traffic Management | 2010-02-19 | 2010-03-15 |  |  | 1038548.56 | 0.000
11184 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WILLIAMSON |  | 31 | 2009866 | SPN:2211-02-021-RECONST TO 4-LANE DIVIDED RDWY : CHANDLER RD | Pavement Widening | 2009-10-30 | 2009-12-01 |  |  | 9229357.32 | 2.356
11185 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DALLAS |  | Multiple | 2009874 | SPN:0009-02-058-ACP OVERLAY,CONCRETE FULL DEPTH REPAIR AND PAVEMENT MARKINGS : IH 635 | Pavement Improvement | 2009-09-09 | 2009-10-19 | 2010-01-01 | 2010-07-19 | 1568590.18 | 3.256
11186 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 06 | 2009912 | SPN:0172-02-067-REPAIR FAILURES, MILL, 2" HMAC OVERLAY, PAVEMENT MARKINGS & SIGNALS : OAK STREET IN MANSFIELD ;SPN:0747-04-062-MILL EXISTING 2" AND OVERLAY : 1000 FT SOUTH OF DEBBIE LANE ;SPN:2374-05 | Pavement Improvement | 2010-05-04 | 2010-05-04 |  | 2010-07-21 | 1267997.97 | 3.296
11187 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009921 | SPN:0218-01-070-CONSTRUCT RAILROAD GRADE SEPARATION STRUCTURE AND APPROACHES : AT UNION PACIFIC RR OVERPASS | Pavement Improvement | 2009-11-02 | 2009-11-19 |  |  | 1713000 | 0.506
11188 | Underway | C950 | Highway Infrastructure Investment Grant | TEXAS | NUECES |  | 27 | 2009928 | SPN:2263-02-086-CONSTRUCT 2ND NEW 28 CAR FERRY BOAT PLANS BY NAVAL ARCHITECT : AT THE PORT ARANSAS FERRY LANDING | Other | 2009-08-31 | 2010-01-25 | 2011-05-01 |  | 6506000 | 0.001
11189 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | STEPHENS |  | 19 | 2010003 | SPN:0257-01-038-FLEX BASE AND SEAL COAT : FM 576W, SOUTH | Pavement Improvement | 2009-10-14 | 2009-11-19 |  |  | 1648067 | 4.264
11190 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | Multiple | 2010004 | SPN:0016-02-130-SEAL COAT, MILL&INLAY, OVERLAY W\PFC : 2000 FT N OF FM 2001 | Pavement Improvement | 2009-10-09 | 2009-11-02 |  |  | 431995.37 | 0.379
11191 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | COKE |  | 11 | 2010005 | SPN:0264-04-046-CONCRETE PAVEMENT AT INTERSECTION : 0.353 MI NORTH OF SH 158 (MAIN ST) | Pavement Improvement | 2009-10-21 | 2009-11-09 |  | 2010-02-17 | 360268.38 | 0.001
11192 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2010006 | SPN:2464-01-013-RECONSTRUCT ROADWAY : FM 4 END OF ROADWAY | Pavement Improvement | 2009-11-30 | 2010-03-31 |  |  | 1249457.36 | 6.266
11193 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CASS |  | 01 | 2010007 | SPN:0919-00-064-INSTALLATION AND UPGRADE OF TRAFFIC CONTROL DEVICES : VARIOUS LOCATIONS IN ATL DISTRICT | Safety/Traffic Management | 2009-10-16 | 2010-02-23 |  |  | 399251.94 | 0.001
11194 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MARION |  | 01 | 2010008 | SPN:0632-01-028-RESTORE SECTION AND RESURFACE 2 LANE HIGHWAY : FM 2208 | Pavement Improvement | 2009-11-02 |  |  |  | 267595.18 | 3.047
11195 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2010009 | SPN:0945-01-036-UPGRADE EXISTING TRAFFIC SIGNALS : AT 40TH/KENNEDY LANE IN TEXARKANA | Safety/Traffic Management | 2009-10-16 | 2010-02-22 |  | 2010-07-22 | 134750.78 | 0.066
11196 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | UPSHUR |  | 01 | 2010012 | SPN:0392-02-080-REPAIR PAVEMENT ON EXISTING 4 LANE HIGHWAY : 0.2 MI S OF FM 557 | Pavement Improvement | 2009-10-16 |  |  |  | 715360 | 3.230
11197 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LIBERTY |  | 08 | 2010024 | SPN:1146-01-027-RESTORE EXISTING ROADWAY : SH 146, EAST | Pavement Improvement | 2009-10-14 | 2009-10-12 |  | 2010-05-18 | 994796.57 | 6.000
11198 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MILAM |  | 31 | 2010027 | SPN:0204-08-053-OVERLAY CONSISTING OF MILLING, HMA OVERLAY, SURFACE TREATMENT AND PAVEMENT MARKINGS AND MARKERS : 0.4 MILE WEST OF FM 2095 | Pavement Improvement | 2009-10-30 | 2010-06-01 |  |  | 766187.19 | 5.560
11199 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GRIMES |  | 17 | 2010029 | SPN:0212-04-032-OVERLAY CONSISTING OF HMA LEVEL-UP, HMA OVERLAY AND PAVEMENT MARKINGS AND MARKERS : FM 244 | Pavement Improvement | 2009-10-14 | 2009-11-02 |  | 2010-06-04 | 1849901.76 | 8.067
11200 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | FREESTONE |  | 06 | 2010030 | SPN:0426-02-018-RESTORE EXISTING ROAD CONSISTING OF GRADING, FLEXIBLE BASE, SURFACE AND PAVEMENT MARKINGS AND MARKERS : FM 1848 ;SPN:2144-01-013-RESTORE EXISTING ROAD CONSISTING OF GRADING, FLEXIBLE B | Pavement Improvement | 2009-11-06 | 2010-01-05 |  |  | 1317884.18 | 10.464
11201 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DICKENS |  | 13 | 2010031 | SPN:0651-04-016-SEALCOAT ECONOMIC STIMULUS : FM 2565, SE | Pavement Improvement | 2009-10-15 | 2009-10-27 |  | 2009-11-30 | 90114 | 7.715
11202 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JIM WELLS |  | 15 | 2010032 | SPN:0086-11-041-REHAB. EXISTING ROADWAY : VENTURA ST., IN SAN DIEGO, EAST | Pavement Improvement | 2009-11-12 | 2010-01-20 |  | 2010-07-30 | 3776701.94 | 8.710
11203 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ARANSAS, SAN PATRICIO |  | Multiple | 2010033 | SPN:0180-05-058-MILL,SEAL AND OVERLAY : STAPP ST. ;SPN:0180-06-088-MILL,SEAL AND OVERLAY : ARANSAS/SAN PAT CO. LINE | Pavement Improvement | 2009-10-26 | 2009-11-11 |  | 2010-04-29 | 782350.63 | 1.942
11204 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN PATRICIO |  | 15 | 2010034 | SPN:0371-04-056-OVERLAY AND SEAL EXISTING LANES : ARANSAS RIVER BRIDGE | Pavement Improvement | 2009-11-06 | 2009-12-09 |  |  | 2224860.59 | 5.502
11205 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | COLLIN |  | 04 | 2010037 | SPN:0387-05-019-RECONSTRUCT RURAL 2 LANE HIGHWAY TO 2 LANE URBAN WITH SHOULDERS AND TWLTL : US 380 | Pavement Improvement | 2009-10-26 |  |  |  | 4887963.33 | 1.054
11206 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | PRESIDIO, BREWSTER |  | 23 | 2010040 | SPN:0020-09-017-OVERLAY : 1.286 MI E BREWSTER/PRESIDIO CO LIN ;SPN:0020-10-017-OVERLAY : APPROX 7 MI. W. OF MOSLEY LANE | Pavement Improvement | 2009-09-30 | 2009-10-02 |  | 2009-11-30 | 981994.38 | 2.819
11207 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | EL PASO |  | Multiple | 2010041 | SPN:0924-00-067-UPGRADING OVERHEAD AND LARGE GROUND MOUNTED SIGNS : VARIOUS LOCATIONS DISTRICTWIDE | Safety/Traffic Management | 2009-10-16 | 2010-02-28 |  |  | 635030.08 | 1.000
11208 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | PALO PINTO |  | 13 | 2010043 | SPN:0007-08-026-CEMENT TREAT EXISTING BASE ON NB LANE AND SHOULDER, SEAL COAT AND 2" HMAC OVERLAY ENTIRE ROADWAY : PALO PINTO CREEK | Pavement Improvement | 2009-11-02 |  |  |  | 1473364.87 | 11.262
11209 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2010044 | SPN:0013-08-115-2 INCH OVERLAY NORTHBOUND LANES : NBL 475` S OF US 380 | Pavement Improvement | 2009-11-02 |  |  |  | 837946.86 | 4.092
11210 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2010045 | SPN:0019-01-136-HOTMIX OVERLAY : NORTH OF POINDEXTER ST; IN CLEBURNE | Pavement Improvement | 2009-11-16 | 2010-02-09 |  | 2010-07-12 | 2086653.12 | 2.829
11211 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2010046 | SPN:0019-02-031-SEAL COAT : CLEBURNE CITY LIMITS | Pavement Improvement | 2009-11-12 | 2010-04-07 |  | 2010-07-12 | 1009579.3 | 3.588
11212 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HOOD |  | 17 | 2010047 | SPN:0080-08-024-MILL AND HMAC OVERLAY : US 377 | Pavement Improvement | 2009-11-06 | 2009-12-14 |  | 2010-01-05 | 352322.3 | 2.010
11213 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | ERATH, SOMERVELL |  | Multiple | 2010048 | SPN:0258-01-026-SEAL COATS : FM 847 IN DUBLIN ;SPN:0258-02-050-SEAL COAT : 5.9 MI EAST OF FM 847 ;SPN:0259-02-045-SEAL COATS : ERATH COUNTY LINE | Pavement Improvement | 2009-11-16 | 2010-07-16 |  |  | 1138715.02 | 18.310
11214 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON |  | 14 | 2010051 | SPN:0051-09-023-RAISE ROADWAY AND BASE REPAIRS (PHASE 1) : SAN LUIS PASS TOLL BRIDGE | Pavement Improvement | 2009-11-02 | 2009-11-18 |  |  | 3227313 | 18.273
11215 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010053 | SPN:0110-05-116-PAVEMENT MARKINGS : NORTH OF BW 8 ;SPN:0110-06-130-PAVEMENT MARKINGS : SOUTH OF BW 8 | Safety/Traffic Management | 2009-11-02 | 2010-01-12 |  | 2010-05-18 | 324477.4 | 8.818
11216 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2010055 | SPN:0543-01-059-SEAL COAT, OVERLAY AND PAVEMENT MARKINGS : BU 290 | Pavement Improvement | 2009-10-21 | 2009-11-16 |  | 2010-03-24 | 1657626 | 10.859
11217 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2010056 | SPN:0543-03-059-REPLACE BRIDGE AND APPROACHES : AT SMITHERS LAKE | Bridge Replacement | 2009-10-16 | 2009-09-09 |  | 2010-07-26 | 1288241.82 | 0.124
11218 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010057 | SPN:0912-00-335-UPGRADE/RECONSTRUCT TRAFFIC SIGNALS : VARIOUS LOCATIONS DISTRICTWIDE | Safety/Traffic Management | 2009-11-16 |  | 2009-10-30 |  | 898349.73 | 0.001
11219 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010058 | SPN:0912-00-383-UPGRADE/RECONSTRUCT TRAFFIC SIGNALS : VARIOUS LOCATIONS DISTRICTWIDE | Safety/Traffic Management | 2009-10-30 |  |  |  | 946870.85 | 0.001
11220 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | Multiple | 2010059 | SPN:0912-34-148-LANDSCAPE DEVELOPMENT : VARIOUS LOCATIONS ON US 59 | Transportation Enhancements | 2009-11-16 | 2009-12-18 |  | 2010-03-15 | 186209.34 | 0.001
11221 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | Multiple | 2010061 | SPN:0912-72-181-BRIDGE MAINTENANCE-REPAIRING STEEL MEMBERS, SEALING ACCESS DOORS, CLEANING AND PAINTING CAPS AND OTHER MISC WORK : VARIOUS LOCATIONS | Other | 2009-10-26 | 2009-11-18 |  | 2010-06-03 | 1235010.44 | 0.001
11222 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON |  | Multiple | 2010063 | SPN:0912-73-131-COUNTYWIDE FULL DEPTH CONCRETE REPAIR : VARIOUS LOCATIONS | Pavement Improvement | 2010-01-04 | 2010-03-10 |  | 2010-07-02 | 442388.58 | 25.446
11223 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2010064 | SPN:1418-01-010-SEAL COAT, OVERLAY AND PAVEMENT MARKINGS : IH 10 EB FRONTAGE ROAD | Pavement Improvement | 2009-10-21 | 2009-11-06 |  | 2010-01-22 | 777940 | 4.842
11224 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2010065 | SPN:1986-01-059-DRAINAGE IMPROVEMENTS : 0.212 MI NW OF MILLS ROAD | Other | 2009-11-06 | 2010-02-03 | 2009-11-06 | 2010-06-10 | 330695.52 | 0.338
11225 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | 07 | 2010066 | SPN:3256-01-094-RESHAPE AND STABILIZE EROSION : AT WHITE OAK BAYOU | Other | 2009-11-04 | 2009-12-01 |  | 2010-02-01 | 103293.39 | 0.034
11226 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LA SALLE |  | 28 | 2010067 | SPN:0017-08-070-RECONSTRUCTION OF NORTH BOUND MAINLANES, RAMPS : LA SALLE/FRIO COUNTY LINE | Pavement Improvement | 2009-11-18 | 2009-12-14 |  | 2010-03-05 | 1574216.7 | 8.468
11227 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CROSBY, FLOYD |  | Multiple | 2010074 | SPN:0453-04-021-SEAL COAT ECONOMIC STIMULUS : US 62 ;SPN:0806-01-011-SEAL COAT ECONOMIC STIMULUS : US 62 EAST ;SPN:1143-01-009-SEAL COAT ECONOMIC STIMULUS : US 62 ;SPN:2497-02-005-SEAL COAT ECONOMIC S | Pavement Improvement | 2009-10-15 | 2009-10-27 |  | 2009-11-30 | 816603.44 | 38.637
11228 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN AUGUSTINE, SABINE, SAN JACINTO |  | Multiple | 2010075 | SPN:0177-02-085-MICROSURFACING : 0.61 MI S OF RR OVERPASS ;SPN:0177-02-086-MICROSURFACING : TRINITY RIVER BRIDGE ;SPN:0336-07-060-MICROSURFACING : FM 1751 ;SPN:0336-08-024-MICROSURFACING : SAN AUG | Pavement Improvement | 2009-11-02 | 2009-11-18 |  |  | 1275635.47 | 23.090
11229 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WINKLER |  | 11 | 2010077 | SPN:0463-06-024-ROADWAY REHABILITATION : 1.3 MILES EAST OF SH 18 IN KERMIT | Pavement Improvement | 2009-10-21 | 2009-11-17 |  | 2010-05-27 | 1773715.49 | 16.312
11230 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2010078 | SPN:0045-19-045-OVERLAY EXISTING 2 LANE ROADWAY : BETHANY ROAD | Pavement Improvement | 2010-05-04 | 2010-05-04 |  |  | 2943236.01 | 5.362
11231 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO |  | 15 | 2010080 | SPN:0342-01-080-OVERLAY : 0.163 MI E OF FM 493 ;SPN:1586-01-055-OVERLAY : SH 107 | Pavement Improvement | 2009-11-02 | 2010-02-26 |  | 2010-07-07 | 1569134.89 | 10.155
11232 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON |  | 27 | 2010081 | SPN:0872-04-025-UPGRADE DRAINAGE CULVERT AND RAISE ROAD : 2.96 MI N OF US 83 | Other | 2009-10-15 | 2009-10-16 |  | 2009-12-17 | 854177.32 | 0.920
11233 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | Multiple | 2010083 | SPN:1939-01-049-REHAB SB OUTSIDE LANE & OVERLAY FULL ROADWAY WIDTH : 1250` N. OF TRENTON RD | Pavement Improvement | 2009-11-06 | 2009-12-07 |  | 2010-04-22 | 540908 | 2.377
11234 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | Multiple | 2010087 | SPN:0291-10-097-LANDSCAPE PLANTING, IRRIGATION SYSTEM, & SPECIALIZED PAVING : AT LP 1604 | Transportation Enhancements | 2009-11-02 | 2009-11-18 |  |  | 191565.56 | 0.500
11235 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | UVALDE |  | 23 | 2010088 | SPN:0369-03-028-REHAB EXISTING ROADWAY & ADD SHOULDERS : 0.8 MI. S OF SABINAL RIVER | Pavement Improvement | 2009-10-15 | 2009-11-02 |  | 2010-07-13 | 1280862.14 | 5.566
11236 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 20 | 2010089 | SPN:0521-04-261-LANDSCAPE DEVELOPMENT : AT IH 10 | Transportation Enhancements | 2009-11-02 | 2009-11-18 |  |  | 865906.52 | 0.001
11237 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | ATASCOSA |  | 28 | 2010090 | SPN:0613-02-055-LANDSCAPE PLANTING & IRRIGATION SYSTEM : AT SH 173, N OF JOURDANTON | Transportation Enhancements | 2009-10-21 | 2009-12-02 |  |  | 85788 | 0.700
11238 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | FRIO |  | 28 | 2010091 | SPN:0748-01-028-REHAB AND WIDEN NARROW ROADWAY : 2.2 MI E OF PEARSALL | Pavement Improvement | 2009-10-15 | 2009-10-19 | 2009-10-19 |  | 3097967.34 | 10.700
11239 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | GUADALUPE |  | 28 | 2010092 | SPN:0915-46-036-LANDSCAPE PLANTING AND IRRIGATION : VARIOUS LOCATIONS IN SEGUIN | Transportation Enhancements | 2009-10-16 | 2009-11-01 |  |  | 491794.72 | 0.001
11240 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH | TYLER | 01 | 2010094 | SPN:0191-03-021-PLANE & RESURFACE ROADWAY : LP 323 IN TYLER, S | Pavement Improvement | 2009-10-21 | 2010-05-05 |  | 2010-07-14 | 635945.99 | 1.593
11241 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | ANDERSON |  | 05 | 2010095 | SPN:0205-07-071-PLANE & RESURFACE ROADWAY : 0.4 MI SE OF FM 2394 IN P`STINE, NE ;SPN:0206-01-046-PLANE & RESURFACE ROADWAY : 0.5 MI W OF SH 155 (JACKSON ST), NE | Pavement Improvement | 2009-10-22 | 2010-06-23 |  |  | 1582436.6 | 3.391
11242 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MCLENNAN, LIMESTONE |  | Multiple | 2010097 | SPN:0056-01-032-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : SH 31 ;SPN:0056-02-030-REPAIR AND RESURFACE WITH ASPHALT PAVEMENT : MCLENNAN CO LINE ;SPN:0056-03-057-REPAIR AND RESURFACE WITH ASPHALT P | Pavement Improvement | 2009-11-06 | 2009-12-03 |  |  | 2332820 | 32.206
11243 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WILBARGER |  | 13 | 2010098 | SPN:0124-03-059-PLANING AND NOVACHIP OVERLAY : US 287 | Pavement Improvement | 2009-10-26 | 2010-06-17 |  | 2010-08-05 | 605866.52 | 1.619
11244 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WHARTON |  | 14 | 2010099 | SPN:0089-07-140-PAVEMENT REPAIR & ACP SURFACING : CANEY CREEK ;SPN:0089-08-090-PAVEMENT REPAIR & ACP SURFACING : NORTH OF SH 60 | Pavement Improvement | 2009-11-12 | 2009-12-30 |  |  | 4409900.24 | 7.030
11245 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CALHOUN |  | 14 | 2010100 | SPN:0180-01-074-ASPHALTIC CONCRETE PAVEMENT : MILDRED DR IN PORT LAVACA | Pavement Improvement | 2009-11-24 | 2010-01-25 |  | 2010-04-15 | 1813198.22 | 11.040
11246 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | RANDALL |  | 13 | 2010103 | SPN:0168-09-153-CURB RAMPS AND CONCRETE MEDIAN : AT WESTERN, GEORGIA & REBECCA STRS | Pavement Improvement | 2009-10-30 | 2010-02-15 |  |  | 80828 | 0.414
11247 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | LEE |  | 10 | 2010123 | SPN:1073-02-023-REPLACE BRIDGE AND APPROACHES : 1.390 MILES NE OF FM 619 2.204 MILES NE OF FM 619;SPN:1073-02-024-REPLACE BRIDGE AND APPROACHES : AT PIN OAK BR, 7.2 MI W OF FM 112 STR 1073-2-5 | Pavement Improvement | 2010-01-07 | 2010-01-27 |  |  | 2075715.18 | 1.628
11248 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | NAVARRO |  | 06 | 2010137 | SPN:0162-04-051-REPLACE BRIDGE : WB AT CEDAR CREEK ;SPN:0997-01-033-REPLACE BRIDGE AND APPROACHES : AT TREADWELL BRANCH | Bridge Replacement | 2009-12-07 | 2010-03-01 |  |  | 855639.4 | 0.087
11249 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | GREGG | LONGVIEW | 01 | 2010187 | SPN:0096-04-063-REPAIR AND RESURFACE ROADWAY : 1.3 MI W OF SL 281 (FISHER RD), E FM 1845 IN LONGVIEW;SPN:0096-06-072-REPAIR AND RESURFACE ROADWAY : FM 1845, IN LONGVIEW, E W OF SS 63 | Pavement Improvement | 2010-05-04 | 2010-05-04 |  |  | 1987737.8 | 4.040
11250 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | GREGG | LONGVIEW | 01 | 2010188 | SPN:0392-03-042-RESURFACE ROADWAY : N OF SL 281, IN LONGVIEW, N 0.1 MI N OF FM 1844 | Pavement Improvement | 2010-04-26 | 2010-04-26 |  |  | 1294548.95 | 2.930
11251 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | LA SALLE, VAL VERDE |  | Multiple | 2010199 | SPN:0017-17-006-FOR THE CONSTRUCTION OF MICROSEAL TYPE OF WORK : IH 35/BI-35C NORTH INTERSECTION 1.867 MI SOUTH;SPN:0022-10-056-FOR THE CONSTRUCTION OF MICROSEAL TYPE OF WORK : STRICKLEN DRIVE 17TH | Pavement Improvement | 2009-11-16 |  |  |  | 573297.57 | 4.557
11252 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS |  | 10 | 2010205 | SPN:0151-06-133-MILL SEAL AND THIN OVERLAY (FRTG RD) : SL 1 BURNET RD | Pavement Improvement | 2010-05-05 | 2010-05-05 |  |  | 498163.23 | 0.721
11253 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WILLIAMSON |  | 31 | 2010206 | SPN:0337-01-033-SPOT FULL DEPTH REPAIR : RAILROAD ST AUSTIN AVE;SPN:0337-02-039-SPOT FULL DEPTH REPAIR : AUSTIN AVE HUTTO RD. | Pavement Improvement | 2010-04-05 | 2010-04-05 |  | 2010-07-01 | 501272.5 | 1.250
11254 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | 21 | 2010207 | SPN:0366-01-067-OVERLAY OVERLAY : IH 35 NBFR EBONY STREET | Pavement Improvement | 2010-01-06 | 2010-03-11 |  | 2010-06-30 | 178235.61 | 0.375
11255 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CALDWELL |  | 25 | 2010208 | SPN:0384-01-020-MILL, SEAL, PAV. REPAIR & OVERLAY : BORCHERT LOOP IN LOCKHART US 183 | Pavement Improvement | 2010-05-04 | 2010-05-04 |  | 2010-08-10 | 921349 | 1.838
11256 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | Multiple | 2010211 | SPN:0987-03-009-SEAL COAT AND OVERLAY : SH 123 GUADALUPE COUNTY LINE | Pavement Improvement | 2010-01-07 | 2010-03-09 |  | 2010-06-30 | 408997.68 | 2.935
11257 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LLANO |  | 11 | 2010212 | SPN:3101-01-006-REHAB RDWY : RM 1431 LLANO R | Pavement Improvement | 2010-01-07 | 2010-03-16 |  | 2010-05-24 | 862584.83 | 0.985
11258 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010232 | SPN:0271-07-242-WIDEN AND RECONSTRUCT TO 2 3-LANE FRONTAGE ROADS WITH BRIDGES AT WHITE OAK BAYOU : WASHINGTON AVE. TAYLOR ST.;SPN:0271-07-278-REHABILITATE BRIDGE & APPROACHES : IH 10 WB FR AT WHITE O | Pavement Widening | 2010-04-26 | 2010-04-26 |  |  | 46415172.1 | 3.423
11259 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | COLEMAN |  | 11 | 2010243 | SPN:7123-11-003-GRADE CROSSING AND RAILROAD REHABILITATION : RRMP 0.00 RUNNELS COUNTY LINE RRMP 21.5 | Pavement Improvement | 2010-04-09 | 2010-04-09 |  |  | 646035.93 | 0.001
11260 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | DUVAL |  | Multiple | 2010249 | SPN:0237-05-032-REHABILITATION OF AN EXISTING ROADWAY : SH 16 0.510 MILE EAST;SPN:0542-03-030-REHABILITATION OF EXISTING ROADWAY : 0.316 MILE WEST OF SH 16 SH 16 | Pavement Improvement | 2010-03-09 | 2010-03-29 |  |  | 1109647.67 | 0.826
11261 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | RUNNELS, TOM GREEN |  | 11 | 2010256 | SPN:7107-09-004-GRADE CROSSING AND RAILROAD REHABILITATION : RUNNELS COUNTY LINE RRMP 56.8 DOT CROSSING 18 771 H RRMP 721.52;SPN:7107-10-003-GRADE CROSSING AND RAILROAD REHABILITATION : COLEMAN COUN | Pavement Improvement | 2010-04-09 | 2010-04-09 |  |  | 3669232.96 | 0.002
11262 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ATASCOSA |  | 28 | 2010286 | SPN:0073-10-045-MILL, BASE REPAIR, SEAL COAT, OVERLAY, SIGNS & PAVEMENT MARKINGS : US 281 BEXAR COUNTY LINE | Pavement Improvement | 2010-02-08 | 2010-02-24 |  | 2010-08-02 | 3684661.2 | 14.741
11263 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | COLORADO, FAYETTE |  | 15 | 2010289 | SPN:0535-07-046-ASPHALTIC CONCRETE PAVEMENT : US 77 COLORADO C/L WESTBOUND LANES;SPN:0535-08-082-ASPHALTIC CONCRETE PAVEMENT : FAYETTE C/L HATTERMAN LANE WESTBOUND LANES | Pavement Improvement | 2010-02-16 | 2010-05-17 |  |  | 3455979 | 15.333
11264 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010294 | SPN:0914-00-305-HERO ROADSIDE ASSISTANCE | Other |  |  |  |  | 2000000 | 0.001
11265 | Underway | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | JASPER |  | 08 | 2010301 | SPN:0064-08-050-RUBBLIZE AND OVERLAY EXISTING ROADWAY : 0.7 MI N OF RE 255, SOUTH 2.7 MI N OF US 190 | Pavement Improvement | 2010-02-16 | 2010-04-14 |  |  | 5671802.25 | 8.440
11266 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | Multiple | 2010303 | SPN:0912-34-150-ITS: UPGRADE ALL TRAFFIC SIGNALS TO PROVIDE REGIONALIZED TRAFFIC FLOW : VARIOUS LOCATIONS IN MISSOURI CITY . | Safety/Traffic Management | 2010-04-30 |  |  |  | 2780094.72 | 0.100
11267 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 21 | 2010304 | SPN:0700-03-014-INSTALL 14` CONTINUOUS LEFT TURN LANE AND 10` SHOULDERS : 0.27 MI EAST OF RO DRIVE 1.4 MI WEST OF BEE CREEK | Pavement Improvement | 2010-04-08 | 2010-06-07 |  |  | 2550668.74 | 0.300
11268 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 21 | 2010305 | SPN:0700-03-015-INSTALL 14` CONTINUOUS LEFT TURN LANE AND 10` SHOULDERS : 0.2 MI WEST OF BEE CREEK RD 0.13 MILES WEST OF BEE CREEK RD | Pavement Improvement | 2010-04-08 | 2010-06-07 |  |  | 202557.12 | 0.001
11269 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | HARRISON | LONGVIEW | 01 | 2010313 | SPN:2642-02-022-REHABILITATE PAVEMENT ON EXISTING 4 LANE HIGHWAY : GREGG COUNTY LINE US 80 | Pavement Improvement | 2010-04-27 | 2010-04-27 |  |  | 4656179.97 | 2.480
11270 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HAYS | AUSTIN | Multiple | 2010314 | SPN:0016-02-120-CONST OVERPASS & RECONST FRT RDS : AT CR 132 (CEMENT PLANT RD) . | Pavement Improvement | 2010-05-13 | 2010-06-08 |  |  | 5462987.88 | 0.529
11271 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | BASTROP |  | 25 | 2010317 | SPN:0115-04-041-WIDEN, REHAB, ADD TURN LANE & OVERLAY : SH 71 0.2 MILES NORTH OF FM 535 | Pavement Improvement | 2010-04-13 |  |  |  | 4792710.08 | 2.016
11272 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010320 | SPN:3136-01-167-MILL, SEAL & THIN OVERLAY : RM 2222 LADYBIRD LAKE | Pavement Improvement | 2010-03-18 | 2010-06-22 |  |  | 3400000 | 4.810
11273 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010393 | SPN:0912-00-421-VA Fr. VARIOUS LOCATIONS To. .; CITY-WIDE WIMAX IMPLEMENTATION | Other |  |  |  |  | 5000000 | 0.001
11274 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | DALLAM |  | 13 | 2010394 | SPN:0040-03-052-RECONSTRUCT, ADD 2 LANES : 8.19 MILES SE OF FM 1879 .53 MILES NE OF FM 1727 | Pavement Widening | 2010-03-29 | 2010-03-29 |  |  | 7838956.43 | 7.449
11275 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | NUECES | CORPUS CHRISTI | 27 | 2010395 | SPN:0074-06-202-CONSTRUCT FRONTAGE ROAD AND MODIFY ENTRANCE AND EXIT RAMPS : .25 MI EAST OF CARBON PLANT RD. MCKINZIE RD. | Pavement Improvement | 2010-02-01 | 2010-04-06 |  |  | 7841712.11 | 1.307
11276 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2010398 | SPN:0045-19-041-WIDEN FROM 2-LANE TO 4-LANE, DIVIDED MEDIAN : BETHANY ROAD US 69 | Pavement Widening | 2010-04-30 | 2010-07-01 |  |  | 3467569.48 | 4.718
11277 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 06 | 2010399 | SPN:1330-02-034-WIDEN FROM 2 LANE TO 4 LANE WITH SHOULDERS AND CURB & GUTTER : NEWT PATTERSON BU 287P | Pavement Widening | 2010-05-05 |  |  |  | 6895052.12 | 1.503
11278 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO |  | 15 | 2010400 | SPN:3097-02-013-CONSTRUCT OVERPASS AND FRONTAGE ROADS : 1.6 MI SOUTH OF US 83 0.10 MI SOUTH OF US 83 | Pavement Improvement | 2010-05-17 |  |  |  | 11000000 | 1.500
11279 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | POTTER | AMARILLO | 13 | 2010401 | SPN:0904-02-035-CONSTRUCT RR OVERPASS : ON GRAND ST AND SE 3RD AVE AT BNSF RR | Pavement Improvement | 2010-05-26 |  |  |  | 5073269.94 | 0.442
11280 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | JEFFERSON |  | 02 | 2010402 | SPN:0932-01-076-ADD 2 LANES & LEFT TURN LANE : SP 93, EAST US 69 IN PORT ARTHUR | Pavement Widening | 2010-06-22 |  |  |  | 6775901.16 | 2.400
11281 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 10 | 2010403 | SPN:0271-06-110-CONSTRUCT 2 DIRECT CONNECTORS ___**FUNDING CSJ 0271-06-119** : AT SH 99 . | New Bridge Construction | 2010-06-15 | 2010-07-07 |  |  | 24308770.03 | 0.001
11282 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 2010404 | SPN:0389-13-052-CONSTRUCT DIRECT CONNECTOR (RAMP E DC SB TO WB) : SH 146 (SB) SPUR 330 (WB) | New Bridge Construction | 2010-03-18 | 2010-05-10 |  |  | 4118844.5 | 0.391
11283 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010421 | SPN:0700-03-107-ADD TRAFFIC SIGNAL, LEFT TURN LN, RIGHT TURN LN & SHOULDERS : 0.62 MI E OF BEE CREEK RD 1.49 MI E OF BEE CREEK RD | Pavement Improvement | 2010-01-13 | 2010-02-15 |  |  | 1466792.03 | 0.870
11284 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | EL PASO | EL PASO | 16 | 2010460 | SPN:7224-01-001-RL BNSF Fr. US/MX BORDER To. APPROX 1.5 MILES NORTH; REHABILITATE EXISTING TRACK AND CONSTUCT 550 FEET OF CONNECTING TRACK | Other | 2010-03-04 | 2010-03-04 |  |  | 1200000 | 1.000
11285 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | KIMBLE |  | 11 | 2010484 | SPN:2469-01-007-CONSTRUCT EXTENSION TO EXISTING ROADWAY : CURRENT SOUTH TERMINUS OF FM 2169 US 377 IN JUNCTION | Pavement Widening | 2010-05-03 | 2010-05-21 |  |  | 2561075.41 | 0.661
11286 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | ANDERSON |  | 05 | 2010531 | SPN:0109-01-055-REPAIR PAVEMENT & RESURFACE ROADWAY : 0.1 MI N OF FM 2419, S OF P`STINE,S SH 294 (W) IN ELKHART | Pavement Improvement | 2010-03-11 | 2010-06-14 |  |  | 1541000 | 5.720
11287 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2010533 | SPN:0191-03-078-RESURFACE ROADWAY W/ NOVA CHIP & IMPRV LP 323 INTERSECTION : US 69 (S BROADWAY),SW LP 323 IN TYLER | Pavement Improvement | 2010-03-09 | 2010-04-05 |  | 2010-06-21 | 700000 | 2.257
11288 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | VAN ZANDT |  | 05 | 2010535 | SPN:0495-02-060-REPAIR & RESURFACE ROADWAY (EBL & WBL) VARIOUS LOCATIONS : 3.4 MI W OF FM 47 (KAUFMAN C/L), E 1.5 MI E OF SH 64 (EBL & WBL) | Pavement Improvement | 2010-05-03 | 2010-05-03 |  |  | 2253289.96 | 11.240
11289 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | YOUNG |  | 19 | 2010538 | SPN:0134-02-053-MILL SURFACE AND FILL WITH HMAC : US 380 4TH STREET IN GRAHAM;SPN:0362-01-044-MILL SURFACE AND FILL WITH HMAC : 4TH STREET SOUTH SALEM LOOP | Pavement Improvement | 2010-03-18 | 2010-05-10 |  |  | 2124482.97 | 8.637
11290 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | WHARTON |  | 14 | 2010539 | SPN:0089-15-017-PAVEMENT REPAIR AND ACP SURFACING : US 59 IN EL CAMPO US 59 | Pavement Improvement | 2010-04-05 | 2010-04-05 |  | 2010-06-15 | 1324375 | 5.595
11291 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HAYS | AUSTIN | 21 | 2010543 | SPN:0914-33-059-CS Fr. SPRING BRANCH DR N BURLESON To. SPRING BRANCH LOOP; RESTRIPE TO INCLUDE CTL, PARKING LANE, BICYCLE LANE,& X-WALK | Safety/Traffic Management | 2010-06-07 | 2010-06-14 | 2010-06-22 |  | 22017 | 1.000
11292 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MCLENNAN |  | 17 | 2010545 | SPN:0015-21-010-WIDEN FROM TWO TO FOUR LANES WITH CONTINUOUS LEFT TURN LANE : TEXAS CENTRAL PKWY IN WACO FM 2063 (SUN VALLEY BLVD) IN HEWITT | Pavement Widening | 2010-05-07 | 2010-06-01 |  |  | 3293000 | 2.222
11293 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MCLENNAN |  | 17 | 2010546 | SPN:2506-01-027-WIDEN ROADWAY TO FOUR LANES WITH CONTINUOUS LEFT TURN LANE TO IMPROVE SAFETY AND REDUCE CONGESTION : 0.9 MI N OF FM 2113 WARREN ST | Pavement Widening | 2010-06-04 | 2010-06-21 |  |  | 2895412.76 | 0.796
11294 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2010547 | SPN:0675-08-061-WIDEN TO 8 MAIN LANES AND RECONSTRUCT 2-LANE FRONTAGE ROADS : N OF LP 336 S OF FM 3083;SPN:0675-08-099-WIDEN TO 8 MAIN LANES AND RECONSTRUCT 2-LANE FRONTAGE ROADS : S OF FM 3083 N OF | Pavement Widening | 2010-04-15 |  |  |  | 51235353.1 | 2.747
11295 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | CHAMBERS |  | 14 | 2010550 | SPN:0508-03-092-CONSTRUCT RAMPS FOR NEW TOURIST AND VISITOR CENTER AND MAKE FRONTAGE ROAD ACCOMODATIONS : 2 MI W OF FM 1724 . | Transportation Enhancements | 2010-04-27 | 2010-06-03 |  |  | 1966157.9 | 1.401
11296 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2010552 | SPN:0675-08-092-ROW ACQUISITION, UTILITY ADJUSTMENTS AND RELOCATION ASSISTANCE : LP 336 NORTH FM 830 | Other | 2010-04-15 |  |  |  | 1000000 | 4.015
11297 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | AUSTIN |  | 10 | 2010556 | SPN:0187-02-055-ADD 2-LANE FOR 4-LANE DIVIDED FACILITY (FUNDING CSJ - 0187-02-062) : FM 949 0.2 MI. NORTH OF FM 2429 | New Bridge Construction | 2010-04-15 | 2010-06-11 |  |  | 7348419.15 | 4.929
11298 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | AUSTIN |  | 10 | 2010557 | SPN:0187-03-051-ADD 2-LANES FOR 4-LANE DIVIDED FACILITY : 0.2 MI SOUTH OF FM 2187 FM 949 | Pavement Widening | 2010-04-15 | 2010-06-11 |  |  | 15070823.13 | 5.885
11299 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON | DALLAS-FORT WORTH | 17 | 2010558 | SPN:0422-05-004-WIDEN ROADWAY FROM 2 LANE TO 4 LANE FACILITY : BU 67M 0.6 MILES EAST OF FM 4 | Pavement Widening | 2010-05-13 | 2010-05-21 |  |  | 17260420.68 | 4.168
11300 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010559 | SPN:0006-05-108-UPGRADE SAFETY LIGHTING : 0.9 MILES WEST OF FM 707 0.5 MILES EAST OF FM 707 | Safety/Traffic Management | 2010-05-26 |  |  |  | 162819.65 | 1.406
11301 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE |  | 04 | 2010569 | SPN:0046-06-074-RESURFACE EXISTING HIGHWAY : COWHORN CREEK 0.2 MI W OF US 59;SPN:2878-01-013-RESURFACE EXISTING HIGHWAY : 0.1 MI SOUTH OF FM 989 0.1 MI WEST OF FM 1297;SPN:2879-01-009-RESURFACE EXIS | Pavement Improvement | 2010-03-26 | 2010-05-13 |  | 2010-07-02 | 625744.76 | 3.247
11302 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HAYS | AUSTIN | Multiple | 2010570 | SPN:0285-03-048-ADD CENTER TURN LANE : PIONEER TRAIL BAPTIST ACADEMY | Pavement Improvement | 2010-05-04 | 2010-05-04 |  |  | 998761.29 | 1.042
11303 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010571 | SPN:0914-00-302-INSTALL SIGNALS | Safety/Traffic Management |  |  |  |  | 600000 | 0.100
11304 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010572 | SPN:0914-00-303-ASPHALT OVERLAY | Pavement Improvement | 2010-06-21 | 2010-06-21 | 2010-08-31 |  | 1254171.8 | 1.000
11305 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010573 | SPN:0914-00-304-MILL AND OVERLAY | Pavement Improvement | 2010-06-07 |  | 2010-08-13 |  | 568397.23 | 0.100
11306 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010574 | SPN:0914-00-306-INSTALL ON SYSTEM SIGNALS AT VARIOUS LOCATIONS | Safety/Traffic Management |  |  |  |  | 550000 | 0.100
11307 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010575 | SPN:0914-00-309-INSTALL OFF SYSTEM SIGNALS AT VARIOUS LOCATIONS | Safety/Traffic Management |  |  |  |  | 750000 | 1.000
11308 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010576 | SPN:0914-00-013-INSTALLED AT VARIOUS LOCATIONS THROUGHOUT THE CITY ON SYSTEM | Other |  |  |  |  | 200000 | 3.140
11309 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010577 | SPN:0914-00-014-INSTALLED AT VARIOUS LOCATIONS THROUGHOUT THE CITY OFF SYSTEM | Other |  |  |  |  | 300000 | 0.001
11310 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 25 | 2010578 | SPN:0113-09-068-IMPROVEMENTS TO SIDEWALKS : AT BRODIE LANE . | Transportation Enhancements | 2010-03-26 | 2010-04-20 |  |  | 131080 | 0.100
11311 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2010580 | SPN:0039-04-080-RECONSTRUCT EXISTING 3 LANE TO 4 LANE DIVIDED URBAN : FM 1015 IN WESLACO 0.7 MI E SP 31 IN MERCEDES | Pavement Widening | 2010-05-11 | 2010-06-01 |  |  | 4144356.19 | 1.727
11312 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010590 | SPN:0006-06-096-UPGRADE SAFETY LIGHTING : GRAPE STREET BU 83-D | Safety/Traffic Management | 2010-05-26 |  |  |  | 193328 | 0.523
11313 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | JONES, TAYLOR |  | Multiple | 2010591 | SPN:0033-05-085-UPGRADE SAFETY LIGHTING : 0.26 MI NORTH OF TAYLOR COUNTY LINE TAYLOR COUNTY LINE;SPN:0033-08-037-UPGRADE SAFETY LIGHTING : JONES COUNTY LINE 0.082 MILES SOUTH OF SUMMIT STREET | Safety/Traffic Management | 2010-05-26 |  |  |  | 184225 | 1.057
11314 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010592 | SPN:0033-06-103-PAVEMENT MARKERS AND MARKINGS : NEAR US 277 (S 14TH ST) US 277 (S 14TH ST) | Safety/Traffic Management | 2010-06-15 |  |  |  | 76423.88 | 1.006
11315 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010593 | SPN:0034-01-104-PAVEMENT MARKERS AND MARKINGS : US 277 (S 14TH ST) SOUTH OF FM 89 (BUFFALO GAP RD) | Safety/Traffic Management | 2010-06-15 |  |  |  | 201515.4 | 3.200
11316 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010594 | SPN:0181-01-058-SH 36 Fr. AT JUDGE ELY BLVD To. .; UPGRADE TRAFFIC SIGNALS | Safety/Traffic Management |  |  | 2010-09-15 |  | 126612.5 | 0.100
11317 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010595 | SPN:0908-33-089-CS Fr. ON GRAPE STREET, NORTH 1ST To. AMBLER AVE; PREVENTATIVE MAINTENANCE RESURFACING WITH FULL DEPTH SPOT REPAIR | Pavement Improvement |  |  | 2010-08-15 |  | 354080.76 | 0.001
11318 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | CALLAHAN |  | 19 | 2010602 | SPN:0007-02-047-RESURFACING AND PAVEMENT MARKINGS : EAST OF MEXIA CREEK EASTLAND COUNTY LINE | Pavement Improvement | 2010-04-08 |  |  |  | 2294673.03 | 8.914
11319 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | CASS |  | 04 | 2010605 | SPN:0919-14-020-REMOVE BARRIERS TO COMPLY WITH ADA : VARIOUS LOCATIONS IN CASS COUNTY AND THE CITY OF LINDEN | Transportation Enhancements | 2010-04-27 | 2010-07-15 |  |  | 416406.88 | 0.001
11320 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2010629 | SPN:0675-08-084-WIDEN TO 6 MAIN LANES : NORTH OF CALVARY SOUTH OF FM 830;SPN:0675-08-091-CONSTRUCT 1 NB ENTRANCE RAMP AND 1 SB EXIT RAMP : AT LONGSTREET ROAD IN WILLIS .;SPN:0675-08-101-BRIDGE REPLA | Pavement Widening | 2010-05-07 | 2010-05-25 |  |  | 53027895 | 5.098
11321 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA |  | 14 | 2010652 | SPN:0143-10-045-ACP SURFACING : 0.2 MI. NORTH OF TROPICAL DRIVE 2.0 MI. NORTH IN VICTORIA | Pavement Improvement | 2010-04-13 | 2010-06-11 |  | 2010-07-21 | 540933.46 | 2.000
11322 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2010657 | SPN:0271-07-094-LANDSCAPING : EAST OF MEMORIAL BROOK WASHINGTON AVENUE IN SECTIONS | Transportation Enhancements |  |  |  |  | 651751 | 10.033
11323 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2010658 | SPN:0271-07-095-LANDSCAPING : WEST OF YORKCHESTER LUMPKIN IN SECTIONS | Transportation Enhancements |  |  |  |  | 400000.69 | 1.293
11324 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 25 | 2010669 | SPN:0113-09-067-INSTALL SIDEWALKS & PED SIGNALS : WEST OF BRODIE LN STEARNS LN | Transportation Enhancements | 2010-03-26 | 2010-04-20 |  |  | 39391.25 | 0.100
11325 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON | HOUSTON | 14 | 2010672 | SPN:0912-73-170-23RD STREET Fr. HARBORSIDE DRIVE To. BROADWAY; RESURFACE ROAD;SPN:0912-73-171-21ST STREET Fr. HARBORSIDE DRIVE To. BROADWAY; RESURFACE ROAD | Pavement Improvement |  |  |  |  | 385396.4 | 0.002
11326 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2010673 | SPN:0912-70-029-ASPHALT OVERLAY : GRANT ROAD, LAKEWOOD FOREST DRIVE OLD KLUGE ROAD | Pavement Improvement | 2010-05-18 | 2010-06-07 |  |  | 330160.58 | 0.001
11327 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 2010674 | SPN:0912-70-020-CLINTON DRIVE Fr. IH 610 To. FEDERAL ROAD; REHAB AND OVERLAY | Pavement Improvement |  |  |  |  | 2900406.3 | 0.001
11328 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010675 | SPN:0912-70-022-HARWIN Fr. BW 8 To. US 59; BASE REPAIR;SPN:0912-70-023-ANTOINE Fr. US 290 To. IH 10; BASE REPAIRS AND FULL DEPTH PAVEMENT REPAIRS;SPN:0912-70-024-SHEPHERD Fr. MEMORIAL DRIVE To. IH 10; | Pavement Improvement | 2010-07-19 |  |  |  | 4457032.85 | 0.011
11329 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BELL |  | 31 | 2010688 | SPN:0015-06-082-RIGHT OF WAY ACQUISITION, UTILITY ADJUSTMENTS AND RELOCATION ASSISTANCE : AMITY ROAD US 190 | Other | 2010-06-10 |  |  |  | 2000000 | 5.637
11330 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010690 | SPN:2718-01-009-RECONST TO 4-LANE DIVIDED : RM 620 WEST 0.75 MI PROPOSED ANDERSON MILL RD | Pavement Widening | 2010-05-28 |  |  |  | 3637513.4 | 0.753
11331 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 2010693 | SPN:8004-12-006-CONSTRUCT DETENTION POND : ON LITTLE YORK, ALDINE-WESTFIELD OVER HALLS BAYOU, NW CORNER | Other | 2010-05-24 | 2010-06-09 |  |  | 1825628.71 | 0.001
11332 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GREGG |  | 01 | 2010698 | SPN:0392-08-021-RESURFACE ROADWAY USING NOVA CHIP METHOD : 1.2 MI N OF US 80 IN LONGVIEW NORTH OF US 80 IN LONGVIEW | Pavement Improvement | 2010-04-13 | 2010-05-24 |  | 2010-07-13 | 209734.1 | 1.084
11333 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2010699 | SPN:0043-09-118-UPGRADE HIGHWAY ILLUMINATION : 0.25 MILES EAST OF MAURINE STREET US 287 | Safety/Traffic Management | 2010-06-01 | 2010-07-19 |  |  | 409757.5 | 0.623
11334 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WICHITA | WICHITA FALLS | 13 | 2010700 | SPN:0043-09-119-UPGRADE HIGHWAY ILLUMINATION : IH 44 0.25 MILES NORTH OF LP 11 | Safety/Traffic Management | 2010-06-01 | 2010-07-19 |  |  | 126752.22 | 1.400
11335 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2010701 | SPN:0156-07-106-UPGRADE HIGHWAY ILLUMINATION : US 287 0.25 MILES WEST OF FM 890 | Safety/Traffic Management | 2010-06-01 | 2010-07-19 |  |  | 131103.52 | 0.941
11336 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2010702 | SPN:0685-01-026-UPGRADE HIGHWAY ILLUMINATION : US 287 SH 240 | Safety/Traffic Management | 2010-06-01 | 2010-07-19 |  |  | 218908.71 | 1.706
11337 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MIDLAND |  | 11 | 2010705 | SPN:0887-01-033-ROADWAY REHABILITATION : CR 1150 CR 1140 | Pavement Improvement | 2010-06-10 |  |  |  | 1026131.67 | 1.020
11338 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | DALLAM |  | 13 | 2010707 | SPN:0040-03-056-REHABILITATION (SBL) : 8.19 MILES SE OF FM 1879 0.99 MILES NE OF FM 1727 | Pavement Improvement | 2010-05-17 |  |  |  | 1194872.29 | 6.988
11339 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WICHITA | WICHITA FALLS | 13 | 2010708 | SPN:0156-04-103-CONSTRUCTION OF RAILROAD AT GRADE CROSSING ON FRONTAGE ROAD : ON FRONTAGE RD, 0.5 MI E OF BARNETT 0.4 MI W OF FAIRWAY BLVD (WB) | Safety/Traffic Management | 2010-06-15 |  |  |  | 265000 | 0.065
11340 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | LIBERTY | HOUSTON | 02 | 2010709 | SPN:0920-02-082-OVERLAY EXISTING ROADWAY : SAN JACINTO, WASHINGTON BOOTHE IN CLEVELAND;SPN:0920-02-083-OVERLAY EXISTING ROADWAY : TRAVIS, HANSON BOOTHE IN CLEVELAND | Pavement Improvement | 2010-05-05 | 2010-05-05 |  | 2010-06-25 | 109809.68 | 0.002
11341 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010710 | SPN:0914-00-317-VA Fr. VARIOUS LOCATIONS IN AUSTIN To. .; MESSAGE SIGNS | Safety/Traffic Management |  |  |  |  | 1000000 | 0.100
11342 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MIDLAND |  | 11 | 2010724 | SPN:1718-07-035-NEW LOCATION NON-FREEWAY : FM 1788 CR 60 | New Construction | 2010-05-24 | 2010-06-14 |  |  | 1788000 | 1.496
11343 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | HOUSTON |  | 06 | 2010757 | SPN:1854-01-042-RECONSTRUCT PAVEMENT & ADD CONTINUOUS TWO-WAY LEFT TURN LANE : US 287 (E) SH 19 (S) | Pavement Improvement | 2010-07-08 |  |  |  | 2798478.21 | 1.562
11344 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 14 | 2010844 | SPN:0089-09-068-CONSTRUCT GRADE SEPARATION : AT FM 360 . | Pavement Improvement | 2010-07-15 |  |  |  | 13615501 | 1.077
11345 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2010857 | SPN:0912-34-163-3` SHOULDER WIDENING WITH OVERLAY : OLD RICHMOND ROAD, FM 1464 VOSS ROAD | Pavement Improvement |  |  |  |  | 569871.21 | 1.732
11346 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY | HOUSTON | 08 | 2010859 | SPN:0912-37-210-CS Fr. SORTERS ROAD, FM 1314 To. RIVER RIDGE DRIVE; FULL DEPTH REHABILITATION | Pavement Improvement |  |  |  |  | 562503.92 | 0.001
11347 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 2010860 | SPN:0912-70-035-CS Fr. SOUTHMORE, STRAWBERRY ROAD To. RED BLUFF IN PASADENA; MILL AND OVERLAY | Pavement Improvement |  |  |  |  | 975525 | 0.001
11348 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010861 | SPN:0912-70-036-CS Fr. JESEN, IH 610 To. UP RAILROAD; MILL AND ACP OVERLAY | Pavement Improvement |  |  |  |  | 322828 | 0.001
11349 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2010862 | SPN:0912-70-037-CS Fr. GESSNER, BELLAIRE To. US 59; BASE REP AND FULL DEPTH PAV REP | Pavement Improvement |  |  |  |  | 152369.5 | 0.001
11350 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2010867 | CS Fr. VARIOUS INDUSTRIAL PARKS To. AND TRUCK ROUTE; RECONSTRUCT & OVERLAY INDUSTRIAL PARK STREETS | Pavement Improvement |  |  |  |  | 260217.2
11351 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | CHILDRESS |  | 13 | 2010886 | SPN:0043-01-062-OVERLAY : 335 FT EAST OF FM 2530, EAST HARDEMAN C/L (SBL) | Pavement Improvement | 2010-07-08 |  |  |  | 1837521.22 | 11.658
11352 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY | HOUSTON | 08 | 2010929 | SPN:0912-37-211-CS Fr. FORD ROAD, LP 494 To. MILLS BRANCH DRIVE; FULL DEPTH REHABILITATION | Pavement Improvement |  |  |  |  | 494830.38 | 0.001
11353 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZORIA, FORT BEND | HOUSTON | Multiple | 2010953 | SPN:2105-01-038-RECONSTRUCT AND WIDEN FROM 2 LANES TO 4-LANE DIVIDED RURAL SECTION (RAISED MEDIAN) : FM 521 BRAZORIA C/L;SPN:2105-02-003-RECONSTRUCT AND WIDEN FROM 2 LANES TO 4-LANE DIVIDED RURAL SECT | Pavement Widening | 2010-07-21 |  |  |  | 12653351.89 | 2.703
11354 | Awaiting NTP But Awarded | C200 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2011005 | SPN:0156-04-106-PAVEMENT MARKING AND MARKINGS : 0.630 MILES EAST OF SH 258 US 277/US 287/US 82 INTERCHANGE;SPN:0903-03-095-PAVEMENT MARKINGS AND MARKERS : VARIOUS LOCATIONS IN THE MPO AREA . | Safety/Traffic Management |  |  |  |  | 159827.23 | 23.756
11355 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | RUNNELS, TOM GREEN, COLEMAN |  | 11 | 2011029 | RL SOUTH ORIENT VARIOUS COUTINES IN THE SAN ANGELO DISTRICT AREA. INSTALL RAIL ANCHORAGE | Pavement Improvement |  |  |  |  | 2196123
11356 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | BOWIE |  | 04 | 2011106 | SPN:0945-01-037-UPGRADE EXISTING TRAFFIC SIGNALS : AT INTERSECTION OF FM 2240 . | Safety/Traffic Management |  |  |  |  | 81408.36 | 0.100
11357 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2011148 | SPN:0047-18-065 -REVERSE EXISTING RAMP CONFIGURATION : INTER OF US 82 AND US 75 SB INTER OF LOY LAKE RD AND US 75 SB | Pavement Improvement |  |  |  |  | 1553306 | 0.750
11358 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT | DALLAS-FORT WORTH | 24 | 2011208 | SPN:0363-01-111-RECONSTRUCT FROM 4 LANE TO 6 LANE DIVIDED : BRUMLOW ROAD (GRAPEVINE SECTION) 0.5 MILES SOUTH OF SH 114 | Pavement Widening |  |  | 2012-11-01 |  | 11838846.21 | 1.482
11359 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2011212 | SPN:0912-70-038-CS Fr. WASHINGTON, WESTCOTT STREET To. IH 45; MILL AND OVERLAY; SPN:0912-70-039-CS Fr. LOCKWOOD, IH 610 To. CLINTON DRIVE; MILL AND OVERLAY | Pavement Improvement |  |  |  |  | 2630000 | 0.002
11360 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY | HOUSTON | 08 | 2011213 | SPN:0912-37-212-CS Fr. NICHOLS SAWMILL ROAD, FM 1774 To. ROBERTS CEMETERY ROAD; FULL DEPTH REHABILITATION | Pavement Improvement |  |  |  |  | 1148176.49 | 0.001
11361 | Awaiting NTP But Awarded | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2011214 | SPN:0495-04-063-REPAIR & RESURFACE WEST BOUND LANES AND SHOULDER : VAN ZANDT C/L, E 0.4 MI E OF SH 110 | Pavement Improvement |  |  |  |  | 946710.04 | 3.400
11362 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 10 | 2011272 | SPN:0912-70-040-ASPHALT OVERLAY : KATY HOCKLEY ROAD, NW OF BECKER RD SOUTH OF JACK RD | Pavement Improvement |  |  |  |  | 469533 | 2.054
11363 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2011273 | SPN:0912-70-041-ASPHALT OVERLAY : CLAY ROAD, EAST OF FRY ROAD BARKER CYPRESS | Pavement Improvement |  |  |  |  | 871032 | 2.192
11364 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | LIBERTY | HOUSTON | 02 | 2011285 | SPN:0920-02-085-OVERLAY EXISTING ROADWAY : ON PEACH ST, FROM FM 787 SH 105 | Pavement Improvement |  |  |  |  | 58656 | 0.499
11365 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | HAYS | AUSTIN | 21 | 2011290 | SPN:0471-02-062-ADD LEFT TURN LANE & SHOULDERS : S OF CR 127 N OF CR 127 | Safety/Traffic Management |  |  |  |  | 530000 | 0.322
11366 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2011340 | S. 14TH St Fr. DANVILLE ST To. PIONEER ST; UNDERSEAL AND MICROSURFACING | Pavement Improvement |  |  |  |  | 97623.74 | 0.002
11367 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2011341 | SPN:0034-01-122-DRAINAGE IMPROVEMENTS : NEAR SOUTHWEST DRIVE NEAR BUFFALO GAP ROAD | Pavement Improvement |  |  |  |  | 206347 | 0.909
11368 | Awaiting NTP & Not Awarded | C490 | Highway Infrastructure Investment Grant | TEXAS | STATEWIDE |  |  | 2011392 | 2009 American Recovery and Reinvestment Act A(ARRA) On-the-Job Training & Supportive Services. | Other |  |  |  |  | 213263
11369 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 25 | 2011403 | ON BRODIE LANE FROM US 290 TO SUNSET VALLEY CITY LIMITS. MILL,OVERLAY | Pavement Improvement |  |  |  |  | 250000
11370 | Awaiting NTP & Not Awarded | C240,C230 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | Multiple | 2011421 | US 83 FROM BUS 83 (WEST) TO BUS 83/INSPIRATION RD. FY 2011 OVERLAY PROGRAM | Pavement Improvement |  |  |  |  | 722727.33
11371 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY | HOUSTON | 08 | 2011438 | CR FROM HARDIN STORE ROAD, SH 249 TO FM 2978. FULL DEPTH REHABILITATION | Pavement Improvement |  |  |  |  | 672987
11372 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | COOKE |  | Multiple | 2011441 | VARIOUS LOCATIONS IN COOKE COUNTY. CONSTR RAMP & CONST/CONVERT FRTG ROADS, INST TRF SIGNAL,& REMOVE BR | Pavement Improvement |  |  |  |  | 10284269
11373 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | TEXAS | WILLIAMSON, TRAVIS | AUSTIN | Multiple | 2011450 | FM 734 ALONG THE TRAVIS AND WILLIAMSON COUNTY LINE AREAS. PEDESTRIAN & INTERSECTION IMPRVMTS | Pavement Improvement |  |  |  |  | 656065
11374 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | TEXAS | COOKE | WICHITA FALLS | 13 | 2011455 | ON IH 35 NEAR FM 1202 TO NEAR US 82... RELOCATION & UTILITIES | Other |  |  |  |  | 961440
11375 | Awaiting NTP & Not Awarded | C200 | Highway Infrastructure Investment Grant | TEXAS | COOKE |  | 26 | 2011456 | IH 35 NEAR US 82 TO NORTH ELM FORK TRINITY RIVER. LANDSCAPING. | Transportation Enhancements |  |  |  |  | 100000
11376 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | DUCHESNE |  | 03 | 0040051 | This project widens US 40 to three lanes from West Roosevelt to Ioka Junction | Pavement Widening | 2005-01-21 | 2005-01-21 |  | 2010-06-24 | 3221599.66 | 2.000
11377 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 03 | 0068049 | This project will reconstruct the intersection of 6200 South and Redwood Road to add capacity and improve traffic operations | Other | 2009-03-16 | 2009-03-16 | 2011-07-31 | 2009-10-01 | 11952097.68 | 0.100
11378 | Underway | C240,C230 | Highway Infrastructure Investment Grant | UTAH | DAVIS | OGDEN | 01 | 0108024 | This project reconstructs and widens Syracuse Road (SR 108) from 1000 West to 2000 West in Syracuse | Pavement Widening | 2007-07-12 | 2007-07-12 | 2010-04-30 | 2009-10-01 | 15499849.11 | 1.000
11379 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | 0209013 | This project improves intersection operations at 9000 South and 450 West by adding turn lanes and other improvments | Pavement Improvement | 2006-10-06 | 2006-10-06 |  | 2009-10-01 | 705446.19 | 0.000
11380 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SAN JUAN |  | 03 | 0491005 | This project reconstructs the pavement on SR-491 from milepost 0 to Milepost 1.5 in Monticello, Utah | Pavement Improvement | 2007-12-13 | 2007-12-13 |  |  | 3800000 | 1.500
11381 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 03 | 0846088 | This project rehabilitates the pavement on I-84 form the Morgan County Line to Henefer by removing some of the existing pavement and adding a structural overlay. | Pavement Improvement | 2005-12-12 | 2005-12-12 |  |  | 600000 | 3.000
11382 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | 2172004 | This project adds safety improvements and reconstructs 3900 South from Highland Drive to 2300 East | Pavement Improvement | 2003-10-31 | 2003-10-31 | 2010-07-13 | 2009-09-01 | 5263477.97 | 4.000
11383 | Underway | C200,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | 2896002 | This project reconstructs 50 South in American fork from 700 East to 1100 East | New Construction | 2005-04-26 | 2005-04-26 | 2010-02-26 | 2009-10-01 | 2299000 | 4.000
11384 | Underway | C200 | Highway Infrastructure Investment Grant | UTAH | CACHE |  | 01 | F002726 | This project constructs a new three lane roadway from 800 South to 300 South along new and existing alignments in Logan | New Construction | 2008-02-08 | 2008-02-08 | 2010-09-30 | 2010-09-30 | 2860580 | 5.000
11385 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F003664 | This project reconstructs the pavement and adds pedestrian ramps on Wall Avenue (SR-204) From 23rd Street to US-89 in Ogden | Pavement Improvement | 2009-03-09 | 2009-03-09 | 2009-10-30 | 2010-01-27 | 5482736.55 | 1.000
11386 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 01 | F004135 | This project rehabilitated the pavement on I-80 from Echo Junction to Emory by removal some of the existing asphalt and adding a structural overlay. | Pavement Improvement | 2009-03-16 | 2009-03-16 |  | 2009-10-01 | 14014488 | 12.000
11387 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F004474 | This project constructs a new Bike and Pedestrian Trail in Hooper, Utah | Transportation Enhancements | 2007-12-14 | 2007-12-14 | 2009-11-30 | 2009-10-30 | 311098.3
11388 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F004592 | Install menian and shoulder barrier | Safety/Traffic Management | 2010-04-15 | 2010-04-15 |  |  | 48604.2
11389 | Underway | C240,C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F004615 | This project adds auxillary lanes on I-15 from 10000 South to 7200 South. These lanes will improve traffic operations and capacity. | Pavement Widening | 2009-02-10 | 2009-03-03 | 2009-12-02 | 2009-10-01 | 10993799.59 | 2.000
11390 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WASATCH |  | 02 | F004648 | This project will add passing lanes on US-189 from Heber to Provo Canyon. | Pavement Widening | 2009-07-01 | 2009-07-01 |  | 2009-10-01 | 8693353.12 | 3.000
11391 | Underway | C240,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F004654 | This project reahbilitates the pavement on US-189 from University Parkway to Provo Canyon and improves and widens intersections. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-06-07 | 3030975.01 | 0.500
11392 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F004680 | This project adds an asphalt overlay on SR-92 from SR-74 to SR-146. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2009-09-01 | 1486379.83 | 1.800
11393 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | UTAH | EMERY |  | 02 | F004690 | This project constructs a climbing lane/turn lanes, as well as rest area construction. | Pavement Widening |  |  |  |  | 3956624.66
11394 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 03 | F004864 | This project rehabilitates the concrete pavement on I-215 from 4700 South to SR-201, repairing potholes and grinding to improve rideability. | Pavement Improvement | 2009-03-17 | 2009-03-17 | 2010-03-31 | 2010-05-05 | 3854043.46 | 3.000
11395 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 03 | F004890 | This project rehabilitates the asphalt pavement on SR-111 (8400 West) from 3500 South to SR-201 in Salt Lake county by removing some of the existing asphalt and adding a structural overlay | Pavement Improvement | 2009-03-10 | 2009-03-10 | 2009-10-01 | 2009-10-01 | 931153.47 | 1.900
11396 | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F005122 | This project replaces 3 bridge decks on I-15 in the Payson, Utah area. | Bridge Improvement | 2009-03-03 | 2009-03-03 |  | 2009-10-01 | 5850000 | 1.000
11397 | Underway | C250,C200 | Highway Infrastructure Investment Grant | UTAH | CARBON |  | 03 | F005269 | This project reconstructs the pavement on Carbonville Road near Price, Utah | Pavement Improvement | 2008-10-13 | 2008-10-13 | 2010-06-30 | 2009-10-01 | 2101040.31
11398 | Underway | C250,C200 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 03 | F005667 | This project reconstructs Coalville Main Street and SR-280 in Coalville, Utah | Pavement Improvement | 2008-11-24 | 2008-12-15 | 2010-03-31 | 2009-10-01 | 1211276.5
11399 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 03 | F005671 | This project replaces two bridges on I-80 over Echo Frontage Road near Echo Junction. | Bridge Replacement | 2008-12-23 | 2008-12-23 |  | 2009-10-01 | 3475000 | 1.000
11400 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F005693 | This project provides intersection improvements along 6200 South from 3000 East to I-215. | Pavement Widening | 2009-03-10 | 2009-03-10 | 2010-03-31 | 2009-10-01 | 1567196.3
11401 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER | OGDEN | 01 | F005706 | This project applied a chip seal to various locations on US-89 to improve skid resistance and extend pavement life. It also retrofitted existing and installed new pedestrian ramps. | Pavement Improvement | 2008-06-12 | 2008-06-12 |  | 2010-01-27 | 1027511.25
11402 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | CACHE |  | 01 | F005788 | This project applied a chip seal on SR-101 from SR-23 to SR-165 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2009-05-08 | 2009-12-29 | 1958745.61 | 5.900
11403 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F005828 | This project applied a thin bonded overlay to the pavement on I-15 from the Benjamin interchange to Spanish Fork. This improves skid resistance and extends pavement life. | Pavement Improvement | 2009-01-14 | 2009-01-14 |  | 2010-04-06 | 1522351.89 | 3.950
11404 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 01 | F005952 | This project rehabilitates the asphalt pavement on SR-269 and SR-270 at various locations. | Pavement Improvement | 2009-03-09 | 2009-03-09 |  | 2010-05-10 | 1745728.08
11405 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F005957 | This project rehabilitates the concrete pavement on I-215 from Milepost 5.709 to Milepost 7.585, repairing potholes and grinding to improve rideability. | Pavement Improvement | 2009-01-13 | 2009-01-13 |  | 2009-09-02 | 978427.59 | 1.876
11406 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F005965 | This project is bridge scour repair in various locations of Region 3. | Bridge Improvement | 2009-11-04 | 2009-11-04 |  |  | 236101.14
11407 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | F005966 | This project is bridge scour repair for 7 bridges in Region 4. | Bridge Improvement | 2009-11-04 | 2009-11-04 |  |  | 352000
11408 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SAN JUAN |  | 03 | F005983 | This project applied a chip seal on US-191 from Milepost 73 to Milepost 86 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-01-06 | 2009-01-06 |  | 2010-05-10 | 720852.47 | 13.000
11409 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F005993 | This project entails the deployment of varriable message signs throughout the Salt Lake Valley | Safety/Traffic Management | 2009-11-04 | 2009-11-04 |  |  | 432597.67
11410 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | F005994 | This project applied a chip seal on US-89 from Milepost 227.6 to 267.2 and on SR-132 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-03-11 | 937474.02
11411 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SEVIER |  | 03 | F005996 | This project applied a lane leveling asphalt overlay on SR-118 from Milepost 6.9 to 10.0. | Pavement Improvement | 2009-03-19 | 2009-03-19 |  |  | 822400 | 3.100
11412 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006024 | This project applied a polymer overaly on six bridges, extending the life of the bridge decks. | Bridge Improvement | 2009-04-01 | 2009-04-01 |  | 2010-05-06 | 227937.34
11413 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F006065 | This project applied a 1 1/2 inch overlay on SR-36 from the Junction of SR 73 to Three O'Clock drive in Tooele, Utah to improve ride, skid resistance and extend the life of the pavement. | Pavement Improvement | 2009-06-04 | 2009-06-04 |  |  | 1542398.49 | 9.890
11414 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | MILLARD |  | 03 | F006071 | This project applied a asphalt wearing surface on I-15 from Milepost 158.5 to 169 to improve skid resistance and extend the pavement life. | Pavement Improvement | 2009-03-09 | 2009-03-09 | 2010-03-31 |  | 4956974.61 | 10.500
11415 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SEVIER |  | 03 | F006072 | This project rehabilitated the concrete pavement on I-70 from Mile post 6.8 to 17.7. This rehabilitation included slab replacment and joint sealing. | Pavement Improvement | 2009-03-10 | 2009-03-10 |  |  | 1194720 | 10.900
11416 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | F006073 | This project applied an asphalt wearing surface on SR-9 form Mile post 0 to 4.9 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-03-03 | 2009-03-03 |  |  | 2127812.14 | 4.900
11417 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | F006074 | This project constructs a new bridge over the Santa Clara River in St. George, Utah. | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2010-04-30 | 2009-10-01 | 3570000
11418 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006076 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 1(Northern Utah). | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-04-12 | 179178.82
11419 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006077 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 1 (Northern Utah). | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-05-06 | 153499.04
11420 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006080 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 2 (Salt Lake Area). | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2009-10-01 | 356431
11421 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006082 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 3 (Central Utah). | Transportation Enhancements | 2009-04-01 | 2009-04-01 | 2009-12-31 | 2010-03-18 | 419351.19
11422 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006084 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Cedar City District of Region 4. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2009-10-01 | 124042.28
11423 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006085 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Price District of Region 4. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2009-10-01 | 133996.05
11424 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006086 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Richfield District of Region 4. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2009-10-01 | 132311.86
11425 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006088 | This project constructed safe sidewalks and installed pedestrian ramps in various locatons on SR-171. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2009-10-01 | 173702
11426 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F006089 | This project constructed safe sidewalks and installed pedestrian ramps on US-89; 400 South to 4400 South in Ogden, Utah. | Transportation Enhancements | 2009-03-03 | 2009-03-03 |  | 2010-03-18 | 131840
11427 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006090 | This project constructed safe sidewalks and installed pedestrian ramps on SR-107; 4000 West to 4050 West in West Point, Utah. | Transportation Enhancements | 2009-03-03 | 2009-03-03 |  | 2010-03-11 | 53176.42 | 0.050
11428 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006091 | This project constructed safe sidewalks and installed pedestrian ramps on SR-37; 3500 West to 3550 West, in Clinton, Utah. | Transportation Enhancements | 2009-03-12 | 2009-03-12 |  |  | 145000
11429 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006092 | This project constructed safe sidewalks and installed pedestrian ramps on SR-266; Redwood Road to 550 West in Taylorsville, Utah. | Transportation Enhancements | 2009-03-12 | 2009-03-12 |  | 2009-10-01 | 321287
11430 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | DUCHESNE |  | 02 | F006093 | This project constructed safe sidewalks and installed pedestrian ramps on SR-87; 800 NOrth to 1400 North in Duchesne, Utah. | Transportation Enhancements | 2009-03-03 | 2009-03-03 |  | 2010-03-01 | 181550.79
11431 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006095 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Cedar City District of Region 4. | Transportation Enhancements | 2009-03-17 | 2009-03-17 |  | 2010-05-06 | 46710.32
11432 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006096 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Price District of Region 4. | Other | 2009-03-03 | 2009-03-03 |  | 2009-10-01 | 92331.19
11433 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006097 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Richfield District of Region 4. | Transportation Enhancements | 2009-03-03 | 2009-03-03 |  | 2009-10-01 | 95182.01
11434 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006099 | This project constructed safe sidewalks and installed pedestrian ramps in variouslocations on SR-48. | Transportation Enhancements | 2009-03-12 | 2009-03-12 |  | 2010-06-01 | 94466
11435 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER | LOGAN | 01 | F006109 | This project provided fiber optic connections on US-89 from I-84 to Harrison Blvd to improve traffic signal operations. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 |  |  | 187881.76
11436 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006110 | This project provided traffic signal interconnection on SR-190 & SR-210; Wasatch Boulevard from I-215 to Cottonwood Canyon to improve traffic operations. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 | 2010-06-22 | 2009-10-01 | 929197.12 | 1.000
11437 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 01 | F006118 | This project constructs wildlife fence along I-80 in Parley's Canyon to enhance safety for both drivers and wildlife. | Other | 2009-03-10 | 2009-03-10 |  |  | 420000 | 1.000
11438 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | GARFIELD |  | 02 | F006119 | This project extends the bike path along SR-12 in Garfield County | Transportation Enhancements | 2009-03-31 | 2009-03-31 | 2010-01-25 | 2009-09-01 | 460424.35 | 1.000
11439 | Underway | C200,C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F006120 | This project constructed a new roadway along 1000 North from SR-112 to 600 West in Tooele, Utah. | New Construction | 2009-03-12 | 2009-03-12 | 2010-12-31 | 2009-10-01 | 3500000
11440 | Underway | C220,C240,C230 | Highway Infrastructure Investment Grant | UTAH | DAVIS | OGDEN | 01 | F006121 | This project will reconstruct 500 South into a five-lane roadway with two lanes in each direction and a center turning lane. Additional improvements include 12-foot shoulders to accommodate on street | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2009-12-01 | 6257007.62 | 1.000
11441 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006123 | This project on US-89 widens the shoulders to accomodate bicycles and pedestrians. | Transportation Enhancements | 2009-03-16 | 2009-03-16 |  | 2010-06-03 | 215027.6 | 0.500
11442 | Underway | C200,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006146 | This project Expands and installs computer hardware and software to update the emergency data intregration in Region 3. Enancing the commuter link system and providing better traffic operations. | Safety/Traffic Management | 2009-03-12 | 2009-03-12 |  |  | 605874.99
11443 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | DAVIS | OGDEN | 01 | F006147 | This project provides signal detection upgrades in Weber and Davis Counties | Other | 2009-03-12 | 2009-03-12 |  |  | 524999.57
11444 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | WEBER | OGDEN | 01 | F006148 | This project installs conduit to on I-15 from Layton to Riverdale Road to enhance the commuter link program, improving traffic operations. | Safety/Traffic Management | 2009-03-12 | 2009-03-12 |  | 2009-08-01 | 575289.7 | 7.459
11445 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006149 | This project expands the Advanced Traffic Management System (ATMS) through improvements to the signal interconnection in the Salt Lake County Area. | Safety/Traffic Management | 2009-03-03 | 2009-03-03 | 2010-09-30 | 2009-10-01 | 999091.81
11446 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006150 | This project expands the Variable Message Signs in the downtown Salt Lake Area, enhancing traffic operations. | Safety/Traffic Management | 2009-03-03 | 2009-03-03 |  | 2009-10-30 | 346997.7
11447 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006151 | This project provdes upgrades to the traffic operations systems (signals Variable Message Signs etc.) along Bangerter Highway from 90th South to SR-201. | Safety/Traffic Management | 2009-03-12 | 2009-03-12 |  | 2009-09-01 | 195308.46 | 9.623
11448 | Underway | C250,C200 | Highway Infrastructure Investment Grant | UTAH | EMERY |  | 02 | F006152 | This project reconstructs the Goblin Valley (Temple Mountain Road in Emery County, Utah | Pavement Widening | 2009-03-12 | 2009-03-12 |  | 2009-10-01 | 1691422.3
11449 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 02 | F006161 | This project constructed safe sidewalks and installed pedestrian rampson SR-198 at various locations in Payson and Santaquin, Utah. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-02-18 | 183663.63
11450 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006188 | This project made intersection imporvements at 9000 South and 700 East in Sandy, Utah. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2009-09-01 | 846000 | 0.000
11451 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UINTAH |  | 02 | F006191 | This project made improvements to the signalized intersection on US-40 at 1000 South and 500 East in Vernal, Utah | Other | 2009-04-01 | 2009-04-01 | 2009-12-31 | 2009-09-01 | 220000 | 1.000
11452 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006241 | This project made repairs to the SR-189 bridge at 600 South University AVenue. | Bridge Improvement | 2009-04-01 | 2009-04-01 |  | 2009-10-01 | 2500000 | 1.000
11453 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | DUCHESNE |  | 02 | F006242 | This project repainted the structural steel on the US-40 Bridge over Starvation Reservoir. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-02-18 | 1161940.24 | 1.000
11454 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006243 | This project entails applying a chip seal to the existing SR-109 roadway surface between Fairfield Road (MP 1.07) and US-89 (MP 2.962) in Layton City, UT. After applying the chip seal, traffic contro | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2009-05-20 | 2010-02-18 | 483177.99 | 24.000
11455 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006244 | This project applied microsurfacing to SR-273 From US-89 To 200 South in Kaysville to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2009-05-20 | 2010-02-18 | 606262.9 | 1.400
11456 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006245 | This project applied an asphalt seal coat to SR-190 from 3000 East to the sR-210 in Salt Lake County to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-05-20 | 485074.58 | 1.550
11457 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 03 | F006246 | This project applied a 1 1/2 inch overaly on SR-173 from 3200 West to 1900 West in Salt Lake County | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-04-14 | 667642.96 | 1.280
11458 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 03 | F006247 | This project applied a 1 1/2 inch overaly on SR-173 from 5600 West to 4800 West in Salt Lake County | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-04-06 | 463990.38 | 0.980
11459 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | CARBON |  | 02 | F006248 | This project provided surface treatements on SR-10 and SR-55 in Carbon County to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-06-02 | 2365525.05
11460 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006250 | This project made safety improvements to I-215 from Redwood Road to I-15. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 | 2009-06-01 | 2010-02-18 | 134451.59 | 1.900
11461 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | F006253 | This project applied a slurry seal to US-89; Ephraim, Manti, Panguitch Main Streets and Snow College roads to improve skid resistance and exxtend pavement life | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-04-06 | 486159.52 | 1.200
11462 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | IRON |  | 02 | F006254 | This project applied a wearing course on SR-130 in Iron County from milepost 0 to 5 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  |  | 1052197.26 | 5.000
11463 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006307 | This project applied a polymer overlay on US-89; State Street from 90th South to 106th South and on SR-71; 700 East. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  |  | 397774.24
11464 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006308 | This project installed median cable barrier on SR-154 north of SR-201 in Salt Lake County. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 |  | 2009-09-01 | 400000 | 1.000
11465 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006309 | This project rehabilitated the asphalt pavement on SR-186; Foothill Boulevard from Sunnyside AVenue to 1300 East in Salt Lake City. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2009-09-01 | 1809432.01 | 1.000
11466 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006315 | This project applied a wearing surface on SR-114 from SR-89 in Provo to SR-89 In Pleasant grove to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-03-11 | 1758829.39
11467 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F006316 | This project Removes existing asphalt to a depth of approximately 7 inches, and replaces with 7 inches on SR-204 from SR-26 to 32nd street . Once all paving is complete, the manholes will be raised. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-01-27 | 1135110.35 | 0.924
11468 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | IRON |  | 02 | F006338 | This project rehabilitates the asphalt pavement on SR-143 in Iron County from Milepost 2 to 2.4 and on SR-274 from Milepost 0.57 to 1.3 by removing some of the existing asphalt and adding a structural | Pavement Improvement | 2009-04-01 | 2009-04-01 |  |  | 216297
11469 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F006359 | This is a structures bridge rehabilitation project that includes pothole patching, membrane & overlay for I-15 near clearfield, bridges F-63, F-66, F-80. | Pavement Widening | 2009-09-24 | 2009-09-24 |  |  | 1347445.52 | 4.000
11470 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | F006383 | This is a chip seal project for SR-228; Leed's Main Street; MP 0 TO 1.821. | Pavement Improvement | 2009-09-24 | 2009-09-24 |  |  | 137360 | 1.821
11471 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006400 | ARRA Funded Project Administration - Mountainland Association of Governments MPO. | Other |  |  |  |  | 52578
11472 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | F006412 | This project is prevenative maintenance chip seal on US-89; FAIRVIEW TO COUNTY LINE, MP 284 TO 297 | Pavement Improvement | 2009-09-24 | 2009-09-24 |  |  | 689640.11 | 12.909
11473 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006426 | This project is a pavement preservation chip seal for SR-164; MP 0 TO 2.67 & SR-147; MP 15 TO 17. | Pavement Improvement | 2009-09-24 | 2009-09-24 |  |  | 449226.91
11474 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006429 | This project is a pavement preservation chip seal for US-89; Boys Ranch to Birdseye. | Pavement Improvement | 2009-09-24 | 2009-09-24 |  |  | 255838.07 | 5.200
11475 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | RICH |  | 01 | F006477 | This project is for the scope and design of the US-89; Swan Creek Box Culvert | Safety/Traffic Management | 2010-03-09 |  |  |  | 343274.32
11476 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006481 | This project is a safe sidewalk installation on SR-198 & SR-115 PAYSON; in Various Locations. | Transportation Enhancements | 2009-09-24 | 2009-09-24 |  |  | 322423
11477 | Awaiting NTP & Not Awarded | C490 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006530 | This project is an ARRA statewide contract for on the job training/supportative service program. | Other |  |  |  |  | 373890
11478 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006661 | Install sidewalks and pedestrian features at the Manila Elementry in Pleasant Grove. | Transportation Enhancements | 2010-04-14 |  |  |  | 85684
11479 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | DAVIS | OGDEN | 01 | F006667 | This project is part of the Region 1 Commuterlink Program and will connect the Layton City signal system in Weber County with the Traffic Operations Center in Salt Lake County. | Safety/Traffic Management | 2009-11-04 | 2009-11-04 |  |  | 326305
11480 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | WEBER | OGDEN | 01 | F006668 | This project is part of the Region 1 Commuterlink Program and will connect 8 signals on US-89 in Weber County to the Traffic Operations Center in Salt Lake County. | Other | 2010-01-01 | 2010-01-01 |  |  | 55938
11481 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F006686 | This project is to do surfacing and/or Resurfacing in Various Locations on Grantsville and Wendover Main Streets | Pavement Improvement |  |  |  |  | 2000000
11482 | Underway | C240,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006688 | This project rehabilitates the pavement on US-89 from 100 North to 800 North in Utah County, Region 3. | Pavement Improvement | 2010-01-01 | 2010-01-01 |  |  | 1552925.79
11483 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SEVIER |  | 03 | F006689 | This project is a chip seal on SR-118 from MP 6.893 to 10.042 in Region 4, Sevier County. | Pavement Improvement | 2010-01-01 | 2010-01-01 |  |  | 174000 | 3.149
11484 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | F006690 | This project is a chip seal on SR-132 from Fountain Green to Moroni in Region 4, Sanpete County. | Pavement Improvement | 2010-01-01 | 2010-01-01 |  |  | 615000 | 10.000
11485 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006731 | This project will be to do prevenative maintenene, with bituminous pavement, plant mix seal, on SR-265 & SR-52 in various locations. | Pavement Improvement |  |  |  |  | 774079
11486 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F006764 | I-80; MP 0 TO MP 10 / MICROSURFACE (ORANGE BOOK) | Other |  |  |  |  | 10000
11487 | Awaiting NTP & Not Awarded | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F007033 | Statewide Safe Sidewalk and ADA Installation Program. Construction of pedestrian ramps in various locations within Region 3. | Transportation Enhancements |  |  |  |  | 344353.15
11488 | Awaiting NTP & Not Awarded | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F007034 | Statewide Safe Sidewalk and ADA Installation Program. Construction of pedestrian ramps in various locations within Region 4. | Transportation Enhancements |  |  |  |  | 779640
11489 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F007104 | 1512 ARRA Report Generation and Quality Control - ARRA Project | Other |  |  |  |  | 25000
11490 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | I156172 | This project applies a micro surface seal to the pavement on I-15 from SR-75 to the Provo River, improving and extending the pavement life. | Pavement Improvement | 2008-01-18 | 2008-01-18 |  | 2010-03-11 | 3418222.91 | 5.000
11491 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | I156173 | This project rehabilitates the pavement on I-15 from 800 South, Payson to the Juab County Line by removal of some of the existing asphalt pavement and adding a structural overlay. | Pavement Improvement | 2008-01-18 | 2008-01-18 |  | 2010-01-26 | 1883718.01 | 9.300
11492 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | I803148 | This project replaces the I-80 bridges over 2300 East | Bridge Replacement | 2009-02-23 | 2009-02-23 |  | 2009-10-01 | 5774416 | 1.000
11493 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | I803149 | This project widens the ramps from I-80 East bound to I-215 from a single off ramp to a dual off ramp, improving operations and capacity. | Pavement Widening | 2009-02-05 | 2009-02-05 | 2009-12-04 | 2009-10-01 | 1306273.69 | 0.099
11494 | Underway | C250,C200 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | LC39009 | This project reconstructs the Pigeon Hollow Road from Pigeon Hollow to Spring City | Pavement Improvement | 2005-12-12 | 2005-12-12 |  | 2009-10-01 | 2098832.3
11495 | Underway | C200,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | LC49089 | This project constructs a new trail along the historic Utah South Rail line via the UPRR North Lehi line | Pavement Improvement | 2005-05-27 | 2005-05-27 | 2010-04-10 | 2009-10-01 | 2399999.69
11496 | Underway | C200 | Highway Infrastructure Investment Grant | UTAH | WASATCH |  | 03 | LC51008 | This project reconstructs Center Street in Heber City from Main Street to 1400 East | Pavement Improvement | 2007-04-24 | 2007-04-24 | 2010-06-01 | 2009-08-01 | 1290303.2 | 1.000
11497 | Underway | C200 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 01 | LC53022 | This project reconstructs the roadway from 600 North to SR-9 in Hurricane | Pavement Improvement | 2003-11-24 | 2003-11-24 |  | 2009-09-01 | 1290303.2
11498 | Underway | C200 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | LC53034 | This project reconstructs and widens Washington Fields Road, including the Virgin River Bridge from Indian Springs Drive to Telegraph Road in Washington. | Pavement Widening | 2008-04-24 | 2008-04-24 |  | 2009-10-01 | 1035000
11499 | Underway | C200,C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 01 | LC53042 | This project realigns Hilton Drive and Black Ridge Drive to improve traffic operations | Pavement Improvement | 2007-08-28 | 2007-08-28 | 2010-08-02 | 2009-10-01 | 2069768.89
11500 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | WINDHAM |  |  | 0114005 | This project is for the repair of a bridge on Town Highway 1, approximately 1 mile west of the junction with State Route 100, in Wardsboro. | Bridge Improvement | 2010-03-11 | 2010-03-11 | 2010-10-01 | 2010-10-01 | 509634.18 | 0.020
11501 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 0136001 | Repaving the roadway | Pavement Widening | 2009-04-02 | 2009-04-02 | 2009-10-16 | 2009-10-16 | 2257081.38 | 4.400
11502 | Underway | C240 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 0193495 | Reconstruction of the existing roadway to provide wider shoulders. | Pavement Widening | 2009-11-04 | 2009-11-04 | 2012-06-29 | 2012-06-29 | 11356392.57 | 4.347
11503 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 0209006 | This project replaces deteriorated truss members and aging concrete deck, along with providing a wider and friendlier pedestrian walkway, for this historic steel truss bridge in the town of Richmond. | Bridge Improvement | 2009-02-06 | 2009-02-06 | 2009-07-06 | 2009-07-06 | 1971156.26 | 0.060
11504 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | 0283009 | This project will construct a new concrete bridge deck and clean and paint the structural steel on bridge # 30 on Sate Route 118 in the Town of East Berkshire. This bridge crosses the Missisuoi River | Bridge Improvement | 2010-02-12 | 2010-02-12 | 2011-08-26 | 2011-08-26 | 1918019.36 | 0.056
11505 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 0283036 | This project improves motorist safety by replacing a functionally obsolete 3-span bridge with a long-lasting single-span weathering steel girder bridge utilizing a high performance concrete deck, a ne | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-06-18 | 2010-06-18 | 2062985.62 | 0.027
11506 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | 0302018 | This project replaces an antiquated and deficient bridge on State Route 15 with a fully modern structure. | Bridge Improvement | 2009-06-15 | 2009-06-15 | 2009-11-30 | 2009-11-30 | 874891.15 | 0.018
11507 | Underway | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 0372009 | Replace exisitng Bridge #69 ON VT14 in East Montpelier. | Pavement Improvement | 2009-10-16 | 2009-10-16 | 2010-10-01 | 2010-10-01 | 1345790.97 | 0.038
11508 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 0891054 | Repaving the roadway | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2009-11-13 | 2009-11-13 | 7940855.9 | 7.900
11509 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 0891055 | Repairing the existing pipes by putting new pipes inside the existing pipes. | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-30 | 2009-10-30 | 1201016.35 | 25.800
11510 | Awaiting NTP & Not Awarded | C200,C240 | Highway Infrastructure Investment Grant | VERMONT | WINDHAM |  |  | 0911057 | ROCKINGHAM IM 091-1(57) STABILIZE ROCK FACE ALONG I91 NB | Pavement Improvement |  |  |  |  | 500000 | 2.600
11511 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR, ORANGE |  |  | 0912072 | This is a safety project for the removal of ledge from the edge of the roadway on Interstate I-91 at various locations between milepoint 69 and 110 in both the northbound and southbound lanes | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2010-11-19 | 2010-11-19 | 3024403.49 | 37.900
11512 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 1443039 | Replace Deck Bridge #15 ON TH3 in Clarendon. | Bridge Improvement | 2009-09-14 | 2009-09-14 | 2010-08-20 | 2010-08-20 | 401632.22 | 0.000
11513 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 1443045 | Replace existing Bridge #19 ON TH23 (SHORT STRUCTURE) in Chittenden. | Pavement Improvement | 2009-10-28 | 2009-10-28 | 2010-10-29 | 2010-10-29 | 407255.55 | 0.070
11514 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 1443046 | Replace Bridge #20 ON TH23 (SHORT STRUCTURE) in Chittenden. | Pavement Improvement | 2009-10-28 | 2009-10-28 | 2010-10-29 | 2010-10-29 | 371576.63 | 0.070
11515 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | 1444036 | Replace the TH 23 bridge in Braintree over Ayers Brook located 0.1 mile from SR-12 | Bridge Replacement |  |  |  |  | 338005.57 | 0.000
11516 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | ORLEANS |  |  | 1449028 | This project will replace a severely deteriorated Town Highway bridge for the Town of Brownington | Bridge Replacement | 2009-03-20 | 2009-03-20 | 2009-11-06 | 2009-11-06 | 1056305.4 | 0.000
11517 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 2206001 | This is a paving project for 5 miles of US route 5 between Hartford and Norwich. This project also includes paving the Wilder State highway and safety improvements at the I-91 off ramp with the Wilder | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-10-16 | 2009-10-16 | 2074859.46 | 4.300
11518 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | 2213001 | This project resurfaces 11.2 miles of pavement on Vermont Route 25 between Bradford and Orange | Pavement Improvement | 2009-07-22 | 2009-07-22 | 2009-10-30 | 2009-10-30 | 4596568.65 | 11.330
11519 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | 2217001 | This is a paving project for 11 miles of Vermont Route 104 between the Towns of Fairfax and Saint Albans starting at milepoint 6.8 in the town of Fairfax. | Pavement Improvement | 2009-09-03 | 2009-09-03 | 2010-06-11 | 2010-06-11 | 3225425.65 | 11.653
11520 | Underway | C250,C200 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | 2331001 | Resurface VT113 Chelsea-Vershire. | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-08-25 | 2010-08-25 | 6274795.24 | 7.000
11521 | Underway | C200,C240 | Highway Infrastructure Investment Grant | VERMONT | WINDHAM |  |  | 2401001 | Resurface 11.458 miles of roadway on VT 30 | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-10-15 | 2010-10-15 | 4098051.28 | 11.425
11522 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 2602001 | This project is for paving .8 miles of US Route 5 and the Norwich State Highway and . 5 miles of Vermont Route 10A | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-10-16 | 2009-10-16 | 2265165.04 | 1.600
11523 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 2604001 | This is a paving project for 3 miles of US 2 in Montpelier from Bailey Ave to Granite Street | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-08-26 | 2009-08-26 | 2155563.15 | 2.800
11524 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | ORLEANS |  |  | 2613001 | Repaving the roadway | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-08-19 | 2010-08-19 | 4162711.98 | 5.622
11525 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 2614001 | This project will resurface approximately 5.1 miles along route 4A in the Towns of Fair Haven and Castelton to provide a much smoother and safer ride. In addition key drainage improvements will be ma | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-16 | 2009-10-16 | 2625839.72 | 5.100
11526 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 2615001 | This project will resurface approximately 1.6 miles of deteriorated pavement which will provide for a smoother and safer ride along Route 4A in the Town of Fair Haven. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-16 | 2009-10-16 | 1059910.58 | 1.600
11527 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 2616001 | This project is for paving 2.9 miles of Vermont Route 15 in Colchester and Essex starting at the Winooski/Colchester town Line. | Pavement Improvement | 2009-04-03 | 2009-04-03 | 2009-10-02 | 2009-10-02 | 2652880.86 | 2.900
11528 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 2617001 | This project is for paving .25 miles of Vermont Route 15 from the US Route 7/ Vermont Route 15 intersection to the Winooski/Colchester line. This project aslo includes concrete repair on US Route 7 in | Pavement Improvement | 2009-06-14 | 2009-06-14 | 2009-10-14 | 2009-10-14 | 2619869.02 | 0.800
11529 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 2618001 | This project is for paving of .9 miles US Route 302 in Montpelier starting from the US Route 2/US Route 302 intersection. | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-08-26 | 2009-08-26 | 726917.67 | 0.900
11530 | Underway | C240 | Highway Infrastructure Investment Grant | VERMONT | ADDISON |  |  | 2627001 | This project is for repaving 3 miles of Vermont Route 125 starting at mile point 1.0 in the Town of Middlebury and ending at MP 4.0 in the Town of Middlebury | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-10-05 | 2010-10-05 | 1810299.76 | 3.094
11531 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDHAM, WINDSOR |  |  | 2628001 | Repaving the roadway | Pavement Improvement | 2009-04-24 | 2009-04-24 | 2009-10-16 | 2009-10-16 | 4074870.71 | 9.400
11532 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 2701001 | This is a paving project for 1.5 miles of Vermont Route 14 starting at the US Route 5 intersection.This project also include paving .25miles of US 4 in Hartford. | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-10-16 | 2009-10-16 | 1434807.66 | 1.700
11533 | Underway | C240 | Highway Infrastructure Investment Grant | VERMONT | ESSEX |  |  | 2706001 | Paving roadway | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2010-11-15 |  | 4489718.02 | 10.651
11534 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | 2714001 | This project is for the paving of 9.5 miles of Vermont Route 105 between the towns of Sheldon and Enosburgh. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-07-26 | 2010-07-26 | 2528939.31 | 9.479
11535 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | ESSEX |  |  | 2724001 | REpaving the roadway | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-09-26 | 2010-09-26 | 5839476.04 | 7.781
11536 | Underway | C240 | Highway Infrastructure Investment Grant | VERMONT | ESSEX |  |  | 2725001 | Repaving the roadway | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-09-24 | 2010-09-24 | 5840533.52 | 7.960
11537 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 2726001 | This project is for paving US Route 7 from the South Burlington/Burlington city line and extending north .2 miles to include the intersection of Interstate 189 | Pavement Improvement | 2009-06-14 | 2009-06-14 | 2009-10-14 | 2009-10-14 | 707779.42 | 0.200
11538 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 2727001 | This project is for paving US Route 7 from the Intersate 189 intersection and extending north for .25 miles to Hadley Road | Pavement Improvement | 2009-06-14 | 2009-06-14 | 2009-10-14 | 2009-10-14 | 510443.12 | 0.200
11539 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | ADDISON |  |  | 2803001 | This project is for repaving 6.5 miles of Vermont Route 125 starting at mile point 0.00 in the Town of Ripton and ending at MP 0.750 in the Town of Hancock | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-10-05 | 2010-10-05 | 4193272.08 | 6.536
11540 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 6000015 | This project improves motorist safety by rehabilitating existing bridge abutments and replacing the bridge superstructure with a modern steel beam bridge in Barre City. | Bridge Improvement | 2009-04-15 | 2009-04-15 | 2009-11-27 | 2009-11-27 | 1266081.33 | 0.020
11541 | Underway | C220 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 6400031 | This project will rehabilitate the historic Taylor St. bridge (Bridge #5, Truss Bridge) over the Winooski River in Montpelier. | Transportation Enhancements | 2009-12-16 | 2009-12-16 | 2010-11-12 | 2010-11-12 | 1746920.78 | 0.067
11542 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | AREH001 | In Shelburne install side walk on Mt. Philo Rd. beginning at Wild Granger Rd and ending at Falls Rd. | Transportation Enhancements | 2010-01-11 | 2010-01-11 | 2010-07-01 | 2010-07-01 | 113760 | 0.000
11543 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | AREH002 | In South Burlington repave portions of the bikes paths through out town. | Transportation Enhancements | 2010-05-01 | 2010-05-01 | 2010-07-01 | 2010-07-01 | 163948 | 0.000
11544 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | BENNINGTON, RUTLAND |  |  | AREH004 | On the Delaware and Hudson rail trail replace the decks of ten bridges in the towns of Poultney, Pawlet, and Rupert. | Transportation Enhancements | 2010-02-04 | 2010-02-04 | 2010-08-06 | 2010-08-06 | 189000 | 0.000
11545 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | AREH005 | In Franklin on Square Rd. also know as Town Highway 16 install sidewalk. | Transportation Enhancements | 2010-01-14 | 2010-01-14 | 2010-07-30 | 2010-07-30 | 12000 | 0.000
11546 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | GRAND ISLE |  |  | AREH006 | In North Hero resurface pedestrian path in Knights Point State Park. | Transportation Enhancements | 2010-02-18 | 2010-02-18 | 2010-05-28 | 2010-05-28 | 17000 | 0.000
11547 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | AREH007 | In Montpelier on Vine St. replace existing pedestrian bridge. | Transportation Enhancements | 2010-04-19 | 2010-04-19 | 2010-06-18 | 2010-06-18 | 166200 | 0.000
11548 | Underway | C220 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | AREH008 | In Essex on Rt. 15 install sidewalk, curbing, and pedestrian signs. | Transportation Enhancements | 2010-01-08 | 2010-01-08 | 2010-09-17 | 2010-09-17 | 208503 | 0.197
11549 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | ARPV001 | Repave 1.6 miles of Maple St and 2.4 miles of Wipple Hollow Rd in West Rutland. | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2010-10-01 | 2010-10-01 | 480164 | 2.417
11550 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | GRAND ISLE |  |  | ARPV002 | This is repaving 2.4 miles of (TH 3) West Shore Road and 1.5 miles of (TH 2 0 Alburgh Springs Road | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-10-01 | 2010-10-01 | 416750 | 3.160
11551 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | ORLEANS |  |  | ARPV003 | This project will resurface 5.5 miles of Town Highway 1 in Barton. | Pavement Improvement | 2010-01-05 | 2010-01-05 | 2010-09-10 | 2010-09-10 | 588250 | 5.530
11552 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | ARPV004 | Paving roadway | Pavement Improvement | 2010-05-11 | 2010-05-11 | 2010-07-10 | 2010-07-10 | 248405.14 | 2.086
11553 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | ARPV005 | This project is for the resurfacing of Center Road in Hardwick. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2010-08-07 | 2010-08-07 | 411178.1 | 4.580
11554 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | ADDISON |  |  | ARPV006 | Paving roadway | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-15 | 2010-09-15 | 297113 | 4.674
11555 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | ARPV007 | This is a repaving project for Lake Road in the Town of Milton Vermont | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-06-25 | 2010-06-25 | 287883.14 | 2.538
11556 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | ORLEANS |  |  | ARPV008 | Paving roadway | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-10-01 | 2010-10-01 | 367163 | 2.510
11557 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | ARPV009 | This is repaving 4.6 miles of roadway on VT Route 132 in the Town of Strafford | Pavement Improvement | 2010-01-05 | 2010-01-05 | 2010-08-13 | 2010-08-13 | 703027.26 | 4.630
11558 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | ARPV010 | Paving roadway | Pavement Improvement | 2010-01-11 | 2010-01-11 | 2010-08-27 | 2010-08-27 | 482755.37 | 5.006
11559 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | ARTB002 | This project will rehabilitate the bridge carrying VT 144 (Town Highway 2) over a stream | Bridge Improvement | 2010-06-11 | 2010-06-11 | 2010-09-17 | 2010-09-17 | 373947.84 | 0.000
11560 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | LAMOILLE |  |  | ARTB003 | The Town of Belvidere will replace the deck on this Town highway covered bridge. This will improve the ride quality and extend the life of the bridge This project is on the Mill (Lumber) covered br | Bridge Improvement | 2010-07-09 | 2010-07-09 | 2010-09-17 | 2010-09-17 | 56029.72 | 0.000
11561 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | ARTB004 | Bridge rehabilitation | Pavement Improvement | 2010-06-14 | 2010-04-20 | 2010-09-17 | 2010-09-17 | 185465 | 0.000
11562 | Underway | C240 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | ARTB005 | The Town of Enosburg will remove the top 2" of pavement on this Town highway bridge and place a waterproff membrane and then resurface with new pavement. This will improve the ride quality and extend | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2010-09-17 | 2010-09-17 | 222923.5 | 0.000
11563 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | ARTB007 | This project will rehabilitate the bridge that carries Scotch Hollow Road over Peach Brook. | Pavement Improvement | 2010-06-16 | 2010-06-16 | 2010-09-30 | 2010-09-30 | 164850 | 0.000
11564 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | ARTB008 | This project rehabilitates the bridge that carries Pinnacle Ridge Road over a small tributary of East Creek. | Bridge Improvement | 2010-03-31 | 2010-03-31 | 2010-08-13 | 2010-08-13 | 348355 | 0.000
11565 | Underway | C200 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | ARTB009 | This project is for the rehabilitation of a bridge on US Route 2 (Portland St.) in St. Johnsbury, over the Passumpsic River and the Washington County Railroad. | Bridge Improvement | 2010-06-10 | 2010-06-10 | 2010-12-01 | 2010-12-01 | 776349 | 0.000
11566 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | STATEWIDE |  |  | NWRT001 | Rehab two pedestrian trail surfaces. One in Newport, one running from St. Albans-Richford. | Transportation Enhancements | 2010-02-18 | 2010-02-18 | 2010-07-02 | 2010-07-02 | 855395.29 | 0.000
11567 | Underway | C220,C200 | Highway Infrastructure Investment Grant | VERMONT | STATEWIDE |  |  | RAMP001 | Statewide design and reconstruct existing sidewalk ramps to make them ADA compliant. | Transportation Enhancements | 2010-03-11 | 2010-03-11 | 2010-08-27 | 2010-08-27 | 442336.62 | 0.000
11568 | Underway | C240 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | SURF014 | REPAVING THE ROADWAY WITH A THIN BITUMINOUS SURFACE TREATMENT. | Pavement Improvement | 2009-07-27 | 2009-07-27 | 2010-10-15 | 2010-10-15 | 2286211.49 | 9.420
11569 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON, ORANGE |  |  | SURF015 | This project resurfaces 9.4 miles of pavement on US Route 302 between Barre and Orange. | Pavement Improvement | 2010-06-14 | 2010-06-14 | 2010-08-17 | 2010-08-17 | 1472387.78 | 9.380
11570 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | SURF016 | This project resurfaces 2.2 miles of pavement on US Route 302 between Groton and Ryegate. | Pavement Improvement | 2010-06-14 | 2010-06-14 | 2010-08-17 | 2010-08-17 | 384550.87 | 2.221
11571 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | BOTETOURT | ROANOKE | 06 | FS09001 | This project includes a slab removal on the right travel lane on both the NBL and SBL of I-81. On the SBL it will begin at the South end of Rte 640 overpass (exit 156) moving South for 4.3 miles. On | Pavement Improvement | 2009-07-08 | 2009-08-03 | 2010-10-04 |  | 19457862 | 9.640
11572 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | HENRICO | RICHMOND | Multiple | FS09002 | Conversion of CRCP pavement to composite; extensive pavement rehab. Project underway. Completion date June 2010. | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2010-06-02 |  | 6465729 | 3.280
11573 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09003 | "This project will repair the existing deterioriated concrete pavement and then place 3.5"" inches of asphalt over the existing concrete pavement on I-64 in the City of Chesapeake." | Pavement Improvement | 2009-07-08 | 2009-08-10 | 2011-08-05 |  | 15627101 | 15.600
11574 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | WYTHE |  | 09 | FS09004 | Milling, paving and guardrail upgrade in Wythe County Northbound I-77 from mile posts 24.19 to 25.69 and 26.59 to 29.22; and on Southbound I-77 from mile posts 40.69 to 46.31. | Pavement Improvement | 2009-07-01 | 2010-05-13 | 2010-11-15 |  | 6257313 | 0.000
11575 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | WASHINGTON | BRISTOL (VA-TN) | 09 | FS09005 | Milling, paving and guardrail upgrade on Southbound I-81 from mile post 19.63 to 25.36 in Washington County. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2009-10-10 | 2009-10-09 | 2905650 | 5.730
11576 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE EDWARD |  | 05 | FS09006 | This project includes milling the existing 24 foot wide pavement and existing paved shoulder (approx. 2 inches on each side) of Rte. 460 EBL from 1.35 miles East of Rte. 735 to the Nottoway County Lin | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-04-29 | 2009-12-18 | 2486238 | 2.880
11577 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09007 | Basic bituminous overlay on Routes 360 and 460 in Richmond district. Complete. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-09-22 | 2009-09-22 | 2123382 | 23.080
11578 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09008 | VDOT will patch and seal cracks in the exitsting asphalt on I-464 in the City of Chesapeake then place 1.5 inches of new asphalt over the existing asphalt surface. This project also will upgrade the | Pavement Improvement | 2009-07-08 | 2009-07-22 | 2010-09-03 |  | 5428192 | 5.950
11579 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STAFFORD | FREDERICKSBURG | Multiple | FS09009 | I-95, basic bituminous overlay. Work in Spotsylvania County is complete and work in Stafford to be done next year. | Pavement Improvement | 2009-07-15 | 2009-08-06 | 2010-08-31 |  | 10221032 | 16.700
11580 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND |  | 01 | FS09010 | Basic bituminous overlay, Route 3 and Route 360 in Lancaster and Richmond counties. Complete. | Pavement Improvement | 2009-07-01 | 2009-07-29 | 2009-10-10 | 2009-10-09 | 2325790 | 16.200
11581 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | FAUQUIER |  | 07 | FS09011 | This resurfacing project inludes mill and overlay of 17.21 miles in length on various routes in Warrenton Residency | Pavement Improvement | 2009-06-09 | 2009-09-11 | 2009-12-01 | 2009-11-25 | 3823687 | 17.270
11582 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | CULPEPER |  | 07 | FS09012 | This resurfacing project includes mill and overlay of 18.41 miles on various routes in Culpeper Residency of VDOT | Pavement Improvement | 2009-06-16 | 2009-07-06 | 2009-12-01 | 2009-12-01 | 2586874 | 18.410
11583 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | ALBEMARLE | CHARLOTTESVILLE | 07 | FS09013 | This resurfacing project is in Albemarle County of Culpeper District includes mill and overlay of 20.3 miles on various routes | Pavement Improvement | 2009-07-08 | 2009-08-02 | 2009-12-01 | 2009-11-30 | 3557080 | 20.390
11584 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | WARREN |  | 07 | FS09014 | Asphalt overlay, rumble strips and guardrail upgrade on Westbound I-66 from mile post 6.6 to 10.7 in Warren County. | Pavement Improvement | 2009-06-09 | 2009-08-04 | 2010-06-30 | 2009-10-28 | 1411053 | 4.100
11585 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09015 | Mill existing asphalt 2 inches and overlay with 2 inches of asphalt | Pavement Improvement | 2009-07-06 | 2009-07-09 | 2009-12-01 | 2009-12-01 | 2802064 | 9.000
11586 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | Multiple | FS09016 | Milling existing asphalt 2 inches and overlay with 2 inches of asphalt | Pavement Improvement | 2009-08-16 | 2009-08-16 | 2009-12-01 | 2009-12-01 | 3601047 | 17.500
11587 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09017 | ***There is a statewide 2009 Design-Build contract to rehab 119 structually deficient bridges to make non-deficient. These are not full replacements. This is only for bridges that carry routes with | Pavement Improvement | 2009-11-12 | 2009-11-19 | 2011-09-25 |  | 4101890 | 0.000
11588 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09018 | See above.*** This project is for the rehab of bridges in the Bristol District. | Pavement Improvement | 2009-11-12 | 2009-11-19 | 2011-09-25 |  | 6498250 | 0.000
11589 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09019 | See above.*** This project is for the rehab of culverts in the Lynchburg District. | Pavement Improvement | 2009-11-11 | 2009-11-11 | 2011-09-25 |  | 3961744
11590 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09020 | See above.*** This project is for the replacement of superstructures in the Lynchburg District. | Pavement Improvement | 2009-11-11 | 2009-11-18 | 2011-09-25 |  | 12230600
11591 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | ROANOKE |  | FS09021 | See above.*** This project is for the replacement of culverts in the Salem District. | Pavement Improvement | 2009-11-04 | 2009-11-09 |  |  | 788100 | 0.000
11592 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09022 | See above.*** This project is for the replacement of culverts in the Stauton District. | Pavement Improvement | 2009-11-04 | 2009-11-09 |  |  | 482400 | 0.000
11593 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | FREDERICKSBURG |  | FS09023 | See above.*** This project is part of the bridge rehab for the Fredericksburg District. | Pavement Improvement | 2009-11-04 | 2009-11-09 |  |  | 3274583
11594 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09024 | See above.*** This project is part of the bridge rehab for the Richmond District. | Pavement Improvement | 2009-11-04 | 2009-11-09 |  |  | 5955104 | 0.000
11595 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09025 | See above.*** This project is part of the bridge rehab for the Culpeper District. | Pavement Improvement |  | 2009-11-20 |  |  | 1385649 | 0.000
11596 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09026 | See above.*** This project is part of the bridge rehab for the Northern Virginia District. | Pavement Improvement |  | 2009-11-20 |  |  | 1350268
11597 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | FRANKLIN | ROANOKE | 05 | FS09027 | See above.*** This project is part of the bridge rehab for the Salem District. | Pavement Improvement | 2009-11-11 |  | 2011-09-25 |  | 930200
11598 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09028 | See above.*** This project is part of the bridge rehab for the Stauton District. | Pavement Improvement |  | 2009-11-20 |  |  | 9767218
11599 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | SPOTSYLVANIA | FREDERICKSBURG | 07 | FS09029 | Design Build project to widen Route 3. Project recently awarded and design is proceeding; construction to begin in Spring. | Pavement Widening | 2009-11-10 | 2009-11-10 | 2012-06-15 |  | 25214915 | 1.210
11600 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK |  | FS09030 | This project will widen a 3.15 mile section of Route 105 in the City of Newport News and York County from 2 existing lanes to a 4 lane divided principle arterial.? | Pavement Widening | 2009-10-20 | 2009-11-02 | 2012-04-16 |  | 19795937 | 6.800
11601 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | SMYTH |  | 09 | FS09031 | Milling, paving and guardrail upgrade on Northbound and Southbound I-81 from mile posts 34.25 to 35.35 (on NBL) and 35.35 to 34.32 (on SBL) in Smyth County. | Pavement Improvement | 2009-07-23 | 2009-09-16 | 2010-06-01 | 2010-04-06 | 1795745 | 2.130
11602 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09032 | This project will repair cracks and patch the exisitng deteriorated pavement and then place a thin layer of asphalt of the existing pavement. | Pavement Improvement | 2009-07-08 | 2009-07-24 | 2010-08-06 |  | 7677483 | 12.830
11603 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | JAMES CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09033 | James City: Various Locations on Interstate & primary Routes Resurfacing Schedule | Pavement Improvement |  |  | 2011-06-10 |  | 6417230
11604 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | FREDERICKSBURG |  | FS09035 | ARRA - Resurfacing in Stafford, Spotsylvania, King George | Pavement Improvement | 2010-07-23 |  |  |  | 2331827 | 0.000
11605 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | BOTETOURT |  | 06 | FS09039 | This project will resurface and upgrade the guarrails on a portion of Rte. 220 and Rte. 58. | Pavement Improvement | 2009-08-25 | 2010-02-16 | 2010-06-10 |  | 2919572 | 14.380
11606 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | MADISON |  | 07 | FS09040 | This project will provide smooth surface by milling and overlaying a portion of Route 230, 231 and 29 in Culpeper. | Pavement Improvement | 2009-07-08 | 2009-07-15 | 2009-12-01 | 2009-11-12 | 2253695 | 15.600
11607 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09041 | Districtwide pavement overlay in Lynchburg District. | Pavement Improvement | 2009-10-01 | 2009-10-20 | 2009-12-01 |  | 335869 | 2.970
11608 | Underway | C220 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | Multiple | FS09044 | Construction of walkways at Marine Corps Heritage Center | Transportation Enhancements | 2010-05-25 | 2010-06-03 | 2010-11-17 |  | 500000 | 0.000
11609 | Awaiting NTP & Not Awarded | C220 | Highway Infrastructure Investment Grant | VIRGINIA | SALEM CITY | ROANOKE | 06 | FS09045 | Construction of a trail connection, including a bridge across the Roanoke River, tying Roanoke River Greenway to Tinker Creek Greenway and to the Roanoke County line. | Other |  |  |  |  | 600000 | 0.000
11610 | Awaiting NTP & Not Awarded | C220 | Highway Infrastructure Investment Grant | VIRGINIA | ROANOKE CITY | ROANOKE | 06 | FS09046 | Construction of a trail connection, including a bridge across the Roanoke River, tying Roanoke River Greenway to Tinker Creek Greenway and to the Roanoke County line. | Transportation Enhancements |  |  |  |  | 1400000 | 0.000
11611 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND CITY | RICHMOND | 01 | FS09047 | Relocation of an existing left turn at the Route 36 (Oaklawn Boulevard)/Route 144 (Temple Avenue) intersection and construction of a new ramp. The new ramp will allow drivers to make a double left tur | Pavement Widening | 2010-07-06 |  | 2012-11-12 |  | 9877181
11612 | Awaiting NTP & Not Awarded | C220 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND CITY | RICHMOND | Multiple | FS09048 | NFO trails project, part of series of jobs to connect Richmond with Williamsburg via trails. | Other |  |  |  |  | 8183825 | 11.000
11613 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE EDWARD |  | 05 | FS09049 | Historic High Bridge reconstruction over Appomattox River | Transportation Enhancements |  |  |  |  | 2000000 | 0.000
11614 | Awaiting NTP & Not Awarded | C220 | Highway Infrastructure Investment Grant | VIRGINIA | BRUNSWICK |  | Multiple | FS09050 | ARRA - Tobacco Heritage Trail | Other |  |  |  |  | 6000000 | 0.000
11615 | Awaiting NTP & Not Awarded | C220 | Highway Infrastructure Investment Grant | VIRGINIA | SHENANDOAH |  | 07 | FS09051 | Enhancement project to restore significant remnants of the Historic Valley Turnpike and construction of bicycle/pedestrian trails that will connect the Town of Strasburg, Strasburg Historic District a | Other |  |  |  |  | 850000 | 0.000
11616 | Underway | C240,C230 | Highway Infrastructure Investment Grant | VIRGINIA | SPOTSYLVANIA | STATEWIDE | 01 | FS09053 | This project is for Route 208 - Spotsylvania Courthouse Bypass - Phase II | Pavement Widening | 2010-05-12 | 2010-05-27 | 2012-11-15 |  | 11534887 | 4.416
11617 | Awaiting NTP & Not Awarded | C250,C200,C240 | Highway Infrastructure Investment Grant | VIRGINIA | GILES |  | 09 | FS09054 | The project is located on route 61 in the Town of Narrows, Giles County. The purpose of this project is to replace the existing structurally deficient bridge crossing the New River, Route 460 and Old | Bridge Replacement |  |  |  |  | 24800000
11618 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | VIRGINIA BEACH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09055 | This project consists of widening Witchduct Road in Virginia Beach from 4 lanes to 6 lanes from Bonney Road to Grayson Road. | Pavement Widening |  | 2010-01-18 | 2012-02-02 |  | 9640484 | 0.000
11619 | Underway | C200 | Highway Infrastructure Investment Grant | VIRGINIA | ALBEMARLE | CHARLOTTESVILLE | Multiple | FS09056 | Widen the westbound exit approach lane of Interstate 64 starting at the westbound exit lane for 5th Street and widening to the intersection with Route 631, all in Albemarle County. | Safety/Traffic Management | 2010-06-14 | 2010-06-14 | 2010-08-27 |  | 850271
11620 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | ALBEMARLE | CHARLOTTESVILLE | Multiple | FS09057 | ARRA I-64 Shadwell EBL Exit Install Dual LTL to WB Rte 250 | Pavement Improvement |  |  | 2010-12-02 |  | 1292352
11621 | Underway | C200,C240 | Highway Infrastructure Investment Grant | VIRGINIA | STAFFORD | FREDERICKSBURG | 01 | FS09058 | This project is for ARRA Route 630 - Bridge Over CSX Railroad (Structure #6040) | New Construction | 2010-04-28 | 2010-05-12 | 2011-09-15 |  | 4767194
11622 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | MANASSAS CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09060 | ARRA Rte.28/Wellington Road Grade Crossing | Pavement Widening |  |  |  |  | 18331803
11623 | Awaiting NTP & Not Awarded | C240,C230 | Highway Infrastructure Investment Grant | VIRGINIA | FAIRFAX | WASHINGTON (DC-MD-VA) | Multiple | FS09062 | ARRA Fairfax County Pkwy Fair Lakes Interchange | Pavement Widening |  |  |  |  | 48932492 | 3.180
11624 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09063 | This 1.3 million dollar enhancement project will provide improvement on he Dismal Swamp Canal in the City of Chesapeake. | Other |  | 2009-12-10 |  |  | 1300000 | 0.000
11625 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND CITY | RICHMOND | 03 | FS09064 | Widening of US-60/ German School Road near the western City Limits of Richmond. Project currently being Advertised for bids. | Pavement Improvement |  |  |  |  | 3336660 | 1.103
11626 | Underway | C200 | Highway Infrastructure Investment Grant | VIRGINIA | DANVILLE CITY | DANVILLE | 05 | FS09065 | This work is for improving the Grade, Drainage, Asphalt Pavement and the Robertson Bridge from the Intersection of Memorial Drive to 0.322 mi N. of the Intersection with Memorial Drive in the City of | New Bridge Construction | 2010-06-01 | 2010-06-02 | 2012-08-31 |  | 16892680 | 0.320
11627 | Underway | C200 | Highway Infrastructure Investment Grant | VIRGINIA | ALLEGHANY |  | Multiple | FS09066 | Reconstruction of inside shoulders and installation of high tension cable guardrail in the median of I-64 from MP 18.8 to 24.0 in Alleghany County. Project also includes improvement of drainage syste | Safety/Traffic Management | 2010-05-10 | 2010-05-12 | 2011-12-07 |  | 13694768
11628 | Underway | C200 | Highway Infrastructure Investment Grant | VIRGINIA | ROCKINGHAM | HARRISONBURG | 06 | FS09067 | Widening of Port Republic Road (Route 253) to 4 lanes from about a quarter mile (1150 feet) south of Route 704 (Boyers Road) to approximately 100 feet north of Harrisonburg East City Limits in Rocking | Pavement Widening | 2010-03-16 | 2010-03-16 | 2012-01-27 |  | 13142797
11629 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09068 | Portsmouth: Rail Relocation along 164 Corridor - CN to provide doe an Additional Rail Line along the Rte 164 Median Rail Corridor | Other |  |  |  |  | 9000000
11630 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | HAMPTON CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09069 | This 3.4 mile long maintenance project will remove and replace approximately 2 inches of asphalt from Colliseum Drive to King Street and from Big Bethel Road to the Western City Limits | Other | 2009-09-11 | 2009-09-22 |  | 2010-06-22 | 10000
11631 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | HAMPTON CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09070 | ARRA Mercury Boulevard Resurfacing | Pavement Improvement |  |  |  |  | 3632486
11632 | Awaiting NTP & Not Awarded | C240,C230 | Highway Infrastructure Investment Grant | VIRGINIA | VIRGINIA BEACH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09071 | ARRA Virginia Beach 165 (Princess Anne Road) 4 Lane Widening | New Construction |  |  |  |  | 21702923
11633 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | HAMPTON CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09073 | Purchasing right of way and moving utilities in preparation of widening of Commander Shepard Boulevard from the intersection of Saunders and Big Bethel Roads to approximately 100 feet (0.019miles) we | Other | 2009-12-30 | 2010-01-04 |  |  | 3587296
11634 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK |  | FS09080 | ARRA Chesapeake/Suffolk I664 Paving/Drains/Guardrail | Pavement Improvement |  |  |  |  | 15030123
11635 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09081 | Rail, roadway and infrastructure improvements at the Norfolk International Marine Terminal to improve train loading and unloading capabilities resulting in time savings, costs to shippers and reducing | Other | 2010-02-22 | 2010-03-08 |  |  | 11305958 | 3.920
11636 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | Multiple | FS09082 | Design-build project to complete design and widen Route 1036 (Pacific Blvd) to 4 lanes for 0.61 miles in Loudoun County. | Pavement Improvement |  |  |  |  | 3694403 | 0.400
11637 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | MARTINSVILLE CITY |  | 05 | FS09083 | VDOT aquiring RW to extend Rte. 174/ Liberty Street to 5 lanes | Other |  |  |  |  | 2389384
11638 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09084 | This maintenance project on 12 bridges in the City of Chesapeake will seal cracks in the bridge decks and other preventative maintenance activities as warranted. Only Engineering funding is obligated | Other | 2009-09-25 | 2009-10-05 |  | 2010-04-28 | 4500
11639 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09085 | ARRA - Chesapeake 168/17/407 Bridge Rehab/Deck Resealing | Bridge Improvement |  |  |  |  | 1094512
11640 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09086 | This maintenance project will perform preventative maintenance and help preserve the condition of various roadways in the City of Chesapeake. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 |  | 2010-04-04 | 4500
11641 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09087 | ARRA - CHESAPEAKE CITYWIDE PAVEMENT RESURFACING | Pavement Improvement |  |  |  |  | 3293637
11642 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | GLOUCESTER | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09088 | ARRA Gloucester 17 Crossover Removal/Turn Lane Improvements | New Construction |  |  | 2010-12-01 |  | 893925
11643 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09091 | This maintenance project will remove and replace 2 inches of asphalt on 6.5 miles of various routes in the City of Newport News including: Jefferson Ave. from Hemlock Rd. to 0.32 Mi. S. J. Clyde Morri | Other | 2009-09-25 |  |  |  | 9846
11644 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09092 | ARRA - Newport News 143/60 Pavement Milling/Resurfacing | Pavement Improvement |  |  |  |  | 3077974
11645 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 03 | FS09093 | This project will upgrade various traffic signals and the central signal control center software in the City of Newport News for system compatability. Only Engineering funding is obligated at this ti | Other |  |  |  |  | 50000
11646 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09094 | ARRA - Newport News Signal System Upgrade Integration | Safety/Traffic Management |  |  |  |  | 1000000
11647 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09096 | This project will include repairing cracked and deterioriated beams and piers as well as other maintenance activities on the Norview Avenue Bridge in the City of Norfolk. Only Engineering funding is | Other | 2009-09-24 | 2009-10-01 |  | 2010-04-25 | 5000
11648 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09097 | CN Phase for ARRA - Norview Avenue Bridge Rehab | Bridge Improvement |  |  |  |  | 683343
11649 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09098 | This maintenance project in the City of Norfolk will repave varoius routes within the City limits as determined by the City. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 |  | 2010-04-25 | 5014
11650 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09099 | CN Phase for ARRA - Citywide Repaving Project | Pavement Improvement |  |  |  |  | 4148794
11651 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09100 | This project will remove and replace the asphalt surface on a 1 mile section of Route 172 in the City of Poquosen. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-07 |  | 2010-05-09 | 10023
11652 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09101 | ARRA - Poquoson Route 172 Milling/Resurfacing | Pavement Improvement | 2010-07-23 |  |  |  | 237209
11653 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09103 | This project will study and develop traffic signal standards in the City of Portsmouth | Other | 2009-10-28 | 2009-10-28 | 2010-06-25 | 2010-06-25 | 160000
11654 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09104 | Funding to design and prepare plans for improvements to traffic signals throughout the City of Portsmouth | Other | 2010-10-28 | 2009-10-28 |  |  | 240000
11655 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09105 | ARRA - Portsmouth Traffic Signal System Improvements | Safety/Traffic Management |  |  |  |  | 2023543
11656 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | SUFFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09106 | This project will repave various sections of primary and secondary Routs as determined by the City of Suffolk. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 |  | 2010-05-23 | 3000
11657 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | SUFFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09107 | ARRA - Suffolk Citywide Repaving Project | Pavement Improvement |  |  |  |  | 1994235
11658 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | VIRGINIA BEACH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09108 | ARRA VA Beach 264 Lynnhaven Interchange Improvements/Ramps | New Construction |  |  |  |  | 2030895
11659 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | WILLIAMSBURG CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09109 | This project will repave varoius routes within the City of Williamsburg. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 |  | 2010-05-01 | 9916
11660 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | WILLIAMSBURG CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09110 | ARRA Williamsburg Citywide Resurfacing | Pavement Improvement |  |  |  |  | 315828
11661 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | FALLS CHURCH CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09112 | ARRA Traffic Calming - ARRA Stimulus | Pavement Improvement |  |  |  |  | 75000
11662 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | Multiple | FS09113 | ARRA Rt. 3000 Prince William Parkway (update to six-lanes) | Pavement Widening | 2010-05-12 | 2010-05-12 |  |  | 6771669
11663 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09114 | ARRA-ROW Phase for the Route 15 Widening | Other |  |  |  |  | 1025000
11664 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09122 | This project will replace existing traffic signal lights with LED signal lights to improve safety and reduce maintenance costs in the City of Chesapeake | Other | 2009-09-25 | 2009-10-05 |  | 2010-01-31 | 3285
11665 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09123 | ARRA - Chesapeake - Citywide LED Traffic Signal Conversion | Safety/Traffic Management |  |  |  |  | 350589
11666 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | JAMES CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 03 | FS09124 | ARRA - James City 199/5 Intersection Improvements/Turn Lanes | Safety/Traffic Management |  |  |  |  | 949212
11667 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09127 | This project will extend the left turn and on Route 143 at Tabb Smith Trail in York County to improve safety. Only Engineering funding is obligated at this time. | Other |  |  |  |  | 2350
11668 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09128 | ARRA - York 134 Extend Turn Lane at Tabb Smith Trail | Pavement Improvement |  |  |  |  | 122818
11669 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09129 | This project will repave various routes in York county including Routes 646, 630, 622, 782. Only Engineering funding is obligated at this time. | Other |  | 2009-09-21 |  |  | 2108
11670 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09130 | CN Phase for ARRA - York 646/630/622/782 Pavement Rehab/Overlay | Pavement Improvement |  |  |  |  | 928112
11671 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09131 | This project will construct sidwalks on Routes 134, 716 and 690 in York County. Only Engineering funding is obligated at this time. | Other |  | 2009-09-21 |  |  | 50000
11672 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09132 | CN Phase for ARRA - York 134/716/ 690 Construct Sidewalks | Transportation Enhancements |  |  |  |  | 448544
11673 | Underway | C490 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09133 | Statewide Wounded Veterans Intership Program. | Other | 2009-09-21 | 2009-09-21 |  |  | 1200000
11674 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | GOOCHLAND | RICHMOND | 07 | FS09134 | ARRA - Goochland 250 Widen to 4 Lanes (Manakin to Hockett) | New Construction |  |  |  |  | 4433715
11675 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | HANOVER | RICHMOND | 07 | FS09135 | ARRA - RT 95 - INTERCHANGE MODIFICATION | Pavement Improvement |  |  |  |  | 3209732
11676 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESTERFIELD | RICHMOND | Multiple | FS09136 | ARRA - RT 10 WIDEN TO SIX LANES | Pavement Widening |  |  |  |  | 10055062
11677 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | RICHMOND |  | FS09137 | ARRA - TRI-CITIES RESURFACING PROJECT | Pavement Improvement |  |  |  |  | 2162652
11678 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND CITY | RICHMOND | Multiple | FS09138 | ARRA - COLONIAL HEIGHTS RESURFACING - CN ONLY | Pavement Improvement | 2010-05-11 | 2010-05-16 |  |  | 522573
11679 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09140 | This project will study and modify the coordination and timing of traffic signals in the City of Newport News to improve intersection operations. | Other |  |  |  |  | 350000
11680 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ALEXANDRIA CITY | WASHINGTON (DC-MD-VA) | 08 | FS09142 | N Va District-Fr:Southside of Eisenhower Ave/ under bridge To Northside of Eisenhwr Ave PE for ARRA Eisenhower Ave Trial-Ph1A/C502 | Other |  |  |  |  | 3993
11681 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ALEXANDRIA CITY | WASHINGTON (DC-MD-VA) | 08 | FS09143 | ARRA - Eisenhower Avenue Trail - Phase 1A / C502 | Transportation Enhancements | 2010-06-21 | 2010-06-21 |  |  | 746007
11682 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ALEXANDRIA CITY | WASHINGTON (DC-MD-VA) | 08 | FS09144 | ARRA - Purchase Trolleys | Other |  | 2010-07-23 | 2011-11-30 |  | 2400000
11683 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ARLINGTON | WASHINGTON (DC-MD-VA) | Multiple | FS09148 | ARRA TSM and Communications Plant Upgrade - PH 1 | Safety/Traffic Management |  |  |  |  | 3580000
11684 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | FAIRFAX CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09149 | ARRA - MPO - Reconstruction and Repaving | Pavement Improvement |  |  |  |  | 600000
11685 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | FALLS CHURCH CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09151 | ARRA Reconstruct Sidewalk and Curb and Gutter - City wide | Transportation Enhancements |  |  |  |  | 250000
11686 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | FAIRFAX | WASHINGTON (DC-MD-VA) | 08 | FS09152 | Northern Virginia- ARRA Herndon Streetscape Utility Relocation | Other |  |  |  |  | 800000
11687 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09154 | Loudoun Co. Fr: Inter-x Waxpool Rd and Loudoun Co Pkwy To: Inter-X PE for ARRA Waxpool Rd/Loudon Pkwy turn lane & signal mod | Safety/Traffic Management |  |  |  |  | 1886750
11688 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09156 | ARRA - Loudoun 28 Flashing Beacon Warning System NB Waxpool | Safety/Traffic Management |  |  |  |  | 397056
11689 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09157 | ARRA - Loudoun Misc.LED Signals/Ped Countdowns/Power Sources | Safety/Traffic Management | 2010-06-01 |  |  |  | 599510
11690 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09158 | ARRA - Loudoun Misc. Install UPS for Major Signals | Safety/Traffic Management | 2010-06-01 |  |  |  | 1182116
11691 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09159 | ARRA - Loudoun Misc. Upgrade/Install Pavement Markers | Safety/Traffic Management |  |  | 2010-11-23 |  | 369203
11692 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | MANASSAS CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09160 | ARRA - Wellington Road Construction | Pavement Improvement |  |  |  |  | 900000
11693 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | MANASSAS PARK CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09161 | ARRA - ROW Phase - Intersection Improvements on Manassas Dri | Other |  |  |  |  | 300000
11694 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | JAMES CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 03 | FS09165 | ARRA COUNTY WIDE - PAVEMENT OVERLAY VARIOUS ROADS | Other |  | 2009-12-03 |  |  | 25919
11695 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | JAMES CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09166 | ARRA COUNTY WIDE - PAVEMENT OVERLAY VARIOUS ROADS | Pavement Improvement |  |  |  |  | 492475
11696 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09167 | ARRA - Ped Access Feasibility Study for Windsor Middle | Other |  |  |  |  | 30000
11697 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 03 | FS09168 | ARRA - Route 17 Turn Lane Improvement | Other | 2009-12-16 | 2009-12-18 |  | 2010-05-18 | 5000
11698 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09169 | ARRA - Route 17 Turn Lane Improvement | Safety/Traffic Management |  |  |  |  | 205000
11699 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09170 | ARRA - Isle of Wight 58 Pavement Overlay | Other | 2009-12-16 | 2009-12-22 |  | 2010-04-13 | 1000
11700 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09171 | ARRA - Isle of Wight 58 Pavement Overlay | Safety/Traffic Management |  |  |  |  | 330395
11701 | Awaiting NTP & Not Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09172 | ARRASmithfield Downtown Revitalization-Streetscaping Phase V | Transportation Enhancements |  |  |  |  | 165329
11702 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09173 | ARRA - Sidewalk Installation and Repairs | Other |  |  |  |  | 2000
11703 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09174 | ARRA - Sidewalk Installation and Repairs | Transportation Enhancements |  |  | 2010-08-16 |  | 55631
11704 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09175 | ARRA - Isle of Wight 460 UPS Battery Back-up Systems | Other | 2009-12-16 | 2009-12-22 |  | 2010-04-12 | 1500
11705 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09176 | ARRA - Isle of Wight 460 UPS Battery Back-up Systems | Safety/Traffic Management |  |  |  |  | 7000
11706 | Underway | C200,C240 | Highway Infrastructure Investment Grant | VIRGINIA | WASHINGTON |  | 09 | FS09177 | ARRA Rte. 58 4-Lane Project Abingdon to Damascus | Pavement Widening | 2010-06-21 | 2010-06-22 |  |  | 24320886
11707 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | ROANOKE | ROANOKE | Multiple | FS09179 | ARRA - RTE. 221 - RECONSTRUCT TO 4 LANES - CN ONLY | New Construction |  |  | 2013-08-01 |  | 25364476
11708 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | VIRGINIA BEACH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09180 | Additive Component of Princess Anne Road Project (UPC 93522) | New Construction |  |  |  |  | 5434263
11709 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | VIRGINIA | FAIRFAX | WASHINGTON (DC-MD-VA) | Multiple | FS09181 | ARRA - I66 Pavement | Pavement Improvement |  |  |  |  | 20066412
11710 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 0002300 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-05-28 | 2009-06-01 | 2009-10-12 | 2009-10-12 | 1833769.79 | 5.230
11711 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PEND OREILLE |  | 05 | 0002301 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-24 | 2009-07-20 | 2009-10-07 | 2009-10-07 | 5529554.68 | 12.680
11712 | Underway | C250 | Highway Infrastructure Investment Grant | WASHINGTON | LINCOLN |  | 05 | 0002302 | Construct a new sidewalk and pedestrian crossing that will provide safer passage for pedestrians to cross from Wilbur Street. | Safety/Traffic Management | 2009-07-15 | 2009-08-03 | 2009-12-31 |  | 160000 | 0.360
11713 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 0002821 | Improve the capacity and safety of the intersection by constructing additional traffic lanes and turn lanes. | Pavement Widening | 2010-02-01 |  |  |  | 2292401 | 0.000
11714 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON, GRAYS HARBOR |  | Multiple | 0008012 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2009-11-18 |  | 2010-07-15 | 2010-05-14 | 1500000 | 20.630
11715 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | COLUMBIA |  | 05 | 0012194 | Add landscaping and irrigation system to the West entrance into the City of Dayton along US 12. | Transportation Enhancements | 2009-09-14 |  |  | 2009-10-21 | 144169.27 | 0.166
11716 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KLICKITAT |  | 04 | 0014062 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 2009-06-10 | 2009-07-27 | 2009-08-22 | 2009-08-22 | 412012.96 | 5.360
11717 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK |  | 03 | 0014063 | Construct a pedestrian tunnel underneath State Route 14 to improve pedestrian access and safety. | Transportation Enhancements | 2009-07-06 |  |  | 2010-06-18 | 506783 | 0.020
11718 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 0014068 | Grind pavement and pave with hot-mix asphalt | Pavement Improvement |  |  | 2012-06-29 |  | 2091286
11719 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | JEFFERSON |  | 06 | 0020163 | Construct roundabouts, center median, sidewalks, drainage, bike lanes, and turn lanes. | Pavement Widening | 2009-09-15 |  |  |  | 1959623 | 0.795
11720 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | WASHINGTON | ADAMS |  | Multiple | 0026031 | ARRA - GRANT COUNTY LINE TO OTHELLO - PAVING SR26-5.85 TO 17.06 MILES EAST OF JUNCTION SR262. | Pavement Improvement |  |  |  |  | 1302000
11721 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 0045005 | Construction of a pedestrian and bike trail on the south side of 188th Street between 59th Avenue and 67th Avenue in Arlington. | Transportation Enhancements | 2009-09-08 |  |  | 2010-05-03 | 106823.65 | 0.570
11722 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 0045006 | Construct sidewalks on both sides of Gifford Avenue from 1st Street to 3rd Street will be installed. Facililties within the project limits will be modified to meet ADA standards. | Transportation Enhancements |  |  |  |  | 92000 | 0.160
11723 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | 0051270 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2010-03-17 | 2009-07-01 |  |  | 2394000 | 17.330
11724 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | 0051277 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2009-06-02 | 2009-06-24 | 2009-11-05 | 2009-11-05 | 6741921 | 7.010
11725 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK |  | 03 | 0051278 | Constructs a new interchange that includes a wider bridge across I-5 and reconstruct the I-5 on and off ramps. | Bridge Replacement | 2009-08-25 | 2009-09-09 | 2011-11-15 | 2011-11-15 | 8200000 | 1.210
11726 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK, COWLITZ | PORTLAND-VANCOUVER, OR-WA | 03 | 0051281 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2009-08-17 | 2009-08-17 | 2010-03-12 | 2010-03-12 | 1475000 | 14.760
11727 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | LEWIS, COWLITZ |  | 03 | 0051283 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2010-02-02 |  |  |  | 5136067
11728 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | LEWIS |  | 03 | 0052202 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-05-28 | 2009-06-19 | 2010-06-30 | 2010-06-30 | 2754590.95 | 13.290
11729 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 09 | 0053948 | This project will construct HOV lanes to relieve congestion and reduce the risk of collisions. | Bridge Replacement | 2009-07-23 | 2009-08-06 | 2011-11-11 | 2011-11-11 | 35388653 | 2.890
11730 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON, PIERCE | SEATTLE-TACOMA, WA | 09 | 0053949 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2009-11-23 |  |  |  | 9329697 | 21.940
11731 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | TACOMA | 06 | 0053951 | This project reconstructs the eastbound interchange at I-5 and SR 16. This includes replacing the bridges over Nalley Valley, constructing freeway connections, reconstructing all of the ramp roadways | Other |  |  |  |  | 6227940 | 1.000
11732 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 0054272 | Install fiber, cameras and data stations in the corridor. Compliments conduit installation as part of the median barrier project. | Safety/Traffic Management | 2009-07-07 | 2009-07-27 | 2010-12-03 | 2010-12-03 | 2500000 | 10.580
11733 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT, SNOHOMISH |  | 02 | 0054277 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 2009-06-18 | 2009-07-20 | 2010-05-14 | 2010-05-14 | 6225239.12 | 6.100
11734 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | OKANOGAN |  | 05 | 0097137 | Construct curb; gutter; sidewalk; lighting; and stormwater drainage on US 97, 16th Ave, and Juniper St. | Transportation Enhancements | 2009-09-08 |  |  | 2010-05-06 | 491383 | 1.580
11735 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KLICKITAT |  | 04 | 0097140 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-16 | 2009-07-20 | 2009-09-30 | 2009-09-30 | 3199516 | 23.320
11736 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | DOUGLAS |  | 04 | 0097148 | Overlay roadway pavement with a chip seal | Pavement Improvement | 2010-04-19 |  |  |  | 1885373
11737 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 07 | 0099078 | Construct a bridge to separate railroad and vehicle traffic on Duwamish Avenue South. | New Construction | 2009-11-30 |  |  |  | 2875171 | 0.200
11738 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | GRAYS HARBOR |  | 06 | 0101318 | Remove and replace existing deteriorated curbs and sidewalks, along Heron Street from K Street to F Street. | Transportation Enhancements | 2009-06-18 |  | 2009-08-25 | 2009-08-25 | 614448 | 0.400
11739 | Underway | C250 | Highway Infrastructure Investment Grant | WASHINGTON | MASON |  | 06 | 0101328 | Widen State Route 101; and provide intersection lighting, a pedestrian actuated signal, asphalt overlay of existing pavement, landscaping, road signs, and striping. | Pavement Widening | 2010-05-24 |  |  |  | 541220 | 0.000
11740 | Completed | C220,C250 | Highway Infrastructure Investment Grant | WASHINGTON | GRAYS HARBOR |  | 06 | 0108006 | Construct new sidewalk on the north side of Simpson Avenue, from 5th Street to 10th Street; and reconstruct existing sidewalk on the south side of Simpson Avenue from 6th Street to 10th Street. | Transportation Enhancements | 2010-03-01 |  |  | 2010-08-10 | 234309 | 0.320
11741 | Underway | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 01 | 0110008 | Construct a missing trail link between NE 195th Street and North Creek Parkway, construct pedestrian signals at two locations, and construct a 100-foot pedestrian bridge. | Transportation Enhancements | 2010-01-19 |  |  |  | 500000 | 0.750
11742 | Underway | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 01 | 0110009 | Construct a pedestrian bridge over North Creek north of 228th Street SE, and construct approximately 0.75 miles of an asphalt paved path. | Transportation Enhancements | 2010-01-19 |  |  |  | 600000 | 0.610
11743 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE |  | 08 | 0162017 | Reconstruction of State Route 162 between Calistoga and Bridge Streets. Includes signalization, addition of left turn lanes, installation of street lighting, and landscaping. | Pavement Improvement | 2009-09-08 |  |  | 2010-05-28 | 420000 | 0.260
11744 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 09 | 0167044 | Provide a bypass for surface water draining into the Rainier Ave South pump station. | Other | 2009-09-21 |  |  | 2010-05-05 | 1948674 | 0.220
11745 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | 0170013 | Replacement of 800 feet of multi-modal asphalt trail and trail lighting. | Transportation Enhancements |  |  |  | 2010-02-10 | 66578 | 0.152
11746 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | 0195045 | Hot mix asphalt paving with basic safety restoration | Pavement Improvement | 2010-05-06 |  | 2010-11-01 | 2010-11-01 | 2150000
11747 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | 0195046 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2009-07-17 | 2009-10-05 | 2010-05-12 | 2010-05-12 | 118868 | 17.750
11748 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 0195047 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project also includes some h | Pavement Improvement | 2009-11-10 |  |  |  | 2534112 | 4.560
11749 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 0205002 | Replace existing timber bridge with new concrete bridge. | Pavement Improvement | 2009-09-02 |  |  | 2010-04-28 | 350000 | 0.010
11750 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 0206003 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-17 | 2009-07-31 | 2009-09-01 | 2009-09-01 | 672508.59 | 2.440
11751 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | OKANOGAN |  | 05 | 0215006 | Construct sidewalk along Okoma Drive from Jasmine St. to W. 4th Avenue. Also includes installation of sidewalk ramps at intersections; crosswalks; and new curbs. | Transportation Enhancements | 2009-08-10 |  |  | 2009-10-27 | 166002 | 0.910
11752 | Completed | C250,C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 0278001 | Remove and replace sidewalk on west side of First Street and both sides of Emma Street. Includes curbs, driveway approaches, curb ramps, and crosswalk striping where necessary. | Transportation Enhancements | 2010-04-26 |  |  | 2010-07-08 | 319569 | 0.200
11753 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 0365007 | Pavement repairs and resurfacing of Dayton St. (5th Ave S to Admiral Way), 212th St SW (72nd Ave W to 84th Ave W), 220th St SW (SR 99 to 84th Ave W), and Olympic View Dr (76th Ave to Puget Dr). | Pavement Improvement | 2009-09-21 |  |  | 2010-02-01 | 999985 | 2.000
11754 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 0395081 | Construct sidewalks and drainage improvements along US 395 from Juniper Street to Kettle Falls City limits. | Transportation Enhancements | 2009-09-08 |  |  | 2009-11-24 | 43174 | 0.440
11755 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 0395088 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-22 | 2009-07-27 | 2009-09-08 | 2009-09-08 | 1965828.76 | 6.690
11756 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 0395089 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-30 | 2009-07-22 | 2009-11-02 | 2009-11-02 | 6200426.3 | 22.270
11757 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 0395090 | High tension cable median barrier will be installed to reduce the frequency and severity of crossover collisions. | Safety/Traffic Management | 2010-05-03 |  | 2010-10-22 | 2010-10-22 | 532271
11758 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 0395092 | ARRA - LEE ROAD TO JUNCTION I-90 - PAVING SR395-VICINITY JUNCTION SR395 TO 22.49 MILES SOUTH. | Pavement Improvement |  |  |  |  | 4700000
11759 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON |  | 04 | 03EI001 | Construct new sidewalks on 7th Street from Ellen Avenue to the North City Limits. | Transportation Enhancements | 2009-09-21 |  |  | 2009-11-11 | 207000 | 0.436
11760 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WAHKIAKUM |  | 03 | 0409001 | Replace the existing Puget Island ferry ramp. | Bridge Replacement | 2009-08-18 |  |  |  | 590000 | 0.020
11761 | Underway | C220,C240 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ | LONGVIEW (OR) | 03 | 0433010 | Clean and paint the remaining steel elements on SR 433/Lewis and Clark Bridge. | Bridge Improvement | 2010-06-08 | 2009-04-30 | 2013-10-26 | 2013-10-26 | 12500000 | 0.540
11762 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | 0503023 | Grind, Inlay and overlay pavement with hot-mix asphalt | Pavement Improvement | 2010-05-04 |  |  |  | 2281229
11763 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON |  | 03 | 0507024 | Pedestrian and street lighting improvements on Sussex Avenue from Ritter Street to Ragless Street. | Transportation Enhancements | 2009-09-28 |  |  | 2009-12-22 | 589000 | 0.400
11764 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 09 | 0509020 | Reconstruct 1st Ave SW between SW 192nd and SW 200th Streets to include three vehicle lanes, bike lanes, street lights, landscaping, and sidewalk. | Pavement Improvement | 2009-08-03 |  |  |  | 3834000 | 0.500
11765 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 0520042 | Construct a new bridge over State Route 520. Bridge includes two vehicle lanes, bike lanes, sidewalks, street lighting. | New Bridge Construction | 2009-05-12 |  |  |  | 4594075 | 0.500
11766 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 0529017 | Widen sidewalk along West Marine View Drive to improve pedestrian/bicycle safety. | Transportation Enhancements | 2009-09-28 |  |  | 2010-03-08 | 1288073 | 0.530
11767 | Awaiting NTP & Not Awarded | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | GRAYS HARBOR |  | 06 | 0560006 | New sidewalk and sidewalk ramps on State Route 101 and 7th St, Simpson, 8th St, L St, K St, 6th St, J St, 5th St, H St, Emerson, Jefferson, Grant, Cleveland, 4th St, Riverside, Sumner, 24th St. | Transportation Enhancements |  |  |  |  | 326071
11768 | Underway | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | PACIFIC |  | 03 | 0575004 | Construct beach/ocean scenic overlook at Beards Hollow on State Route 100. | Transportation Enhancements | 2009-10-09 |  |  |  | 100000 | 0.000
11769 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON | OLYMPIA | 03 | 0643005 | Construct missing segments of the Woodland Trail from the Chehalis-Western Regional Trail to the Woodland Creek Community Park through the City of Lacey. | Transportation Enhancements | 2009-06-26 |  |  | 2010-01-11 | 1000000 | 2.400
11770 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 0822128 | This project will rearrange the interchange to increase safety, relieve congestion and improve traffic flow movements. | Bridge Replacement | 2010-03-10 | 2010-04-01 | 2011-10-15 | 2011-10-15 | 18768218 | 1.800
11771 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 0822131 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2009-06-10 | 2009-07-07 | 2009-10-28 | 2009-10-28 | 5952408 | 14.730
11772 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 0822132 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2010-03-19 |  |  |  | 4584688
11773 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS, KING |  | Multiple | 0901476 | Replace the existing traveler information cameras in the Snoqualmie Pass vicinity with low light cameras to provide improved visibility of roadway conditions at night. | Safety/Traffic Management | 2009-05-19 | 2009-08-10 | 2009-11-24 | 2009-11-24 | 60000 | 91.710
11774 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 0901478 | Replacing broken concrete panels, grinding the existing concrete roadway surface and installing dowel bars to extend the service life of the pavement. | Pavement Improvement | 2010-01-08 |  | 2010-05-13 | 2010-05-13 | 7456270
11775 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902259 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-04-15 | 2009-04-27 | 2009-07-09 | 2009-07-09 | 2403340.87 | 3.730
11776 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902260 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-04-15 | 2009-05-06 | 2009-08-03 | 2009-08-03 | 2729838.46 | 4.680
11777 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902283 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2009-06-17 | 2009-07-07 | 2009-10-26 | 2009-10-26 | 3440325.89 | 3.210
11778 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902302 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 2009-06-15 | 2009-07-07 | 2010-07-30 | 2010-06-16 | 15337698.47 | 9.500
11779 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902315 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement |  |  | 2012-10-26 | 2012-10-26 | 16304322 | 5.500
11780 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 0902319 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2009-07-17 | 2009-10-05 | 2010-05-12 | 2010-05-12 | 32751 | 11.840
11781 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | 0904118 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-08-04 | 2009-08-24 | 2009-10-28 | 2009-10-28 | 3754574.74 | 6.170
11782 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 09WA004 | Reconstruct North Parkway Avenue from North Onsdorff Boulevard to N 5th Street. The road will include three traffic lanes, curb & gutter, sidewalks, landscaping, and street lighting. | Pavement Widening | 2009-10-02 |  |  | 2010-04-30 | 43788 | 0.450
11783 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 1073004 | Construct new curb, gutter, and sidewalk along East Valley Highway between S. 212th St. and State Route 167; add a third vehicle lane; and traffic signal improvements. | Pavement Widening | 2009-07-27 |  |  |  | 2000000 | 0.850
11784 | Underway | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 1220021 | Construct a 4.4 mile long trail to connect to an existing trail. Includes the rehabilitation of 5 bridges and trailhead facility. | Transportation Enhancements | 2009-07-07 |  |  |  | 778317 | 4.400
11785 | Underway | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 07 | 1301003 | Construction of sidewalk, bicycle lane, and street lights on the east side of 4th Avenue SW between SW 153rd Street and SW 156th Street. | Transportation Enhancements | 2009-08-17 |  |  |  | 536293 | 0.220
11786 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 1335009 | Construct an approximately 0.6 mile long pedestrian pathway. | Transportation Enhancements | 2009-08-24 |  | 2009-09-11 | 2009-09-11 | 116474.47 | 0.576
11787 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 06 | 1343002 | Transit facility improvements for public parking that include structural improvements, electrical, painting, ventilation, fire protection, and signage. | Other | 2010-05-03 |  |  |  | 798029 | 0.000
11788 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | CHELAN | WENATCHEE | 04 | 1405006 | Cleaning and painting of an historic bridge. | Transportation Enhancements | 2009-09-28 |  |  | 2010-06-15 | 1527749 | 0.208
11789 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 07 | 1482010 | Construct a bridge parallel and connected to the existing Spokane Street Viaduct. Includes the construction of new on and off ramps. | Pavement Widening | 2009-12-09 |  |  |  | 15443000 | 0.750
11790 | Awaiting NTP & Not Awarded | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP | BREMERTON | 01 | 18F3001 | ARRA - Poulsbo, Noll Rd. Improvements - Phase 1 FROM:Poulsbo Elem School TO:Poulsbo Mid. School LEN: 0.500MI | Transportation Enhancements |  |  |  |  | 401128
11791 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 1915008 | Reconstruct roadway to include a center turn lane; two traffic lanes; bike lanes; curb and gutter; sidewalk; and street lighting at intersections. | Pavement Improvement | 2010-04-12 |  |  |  | 3500000 | 0.120
11792 | Underway | C220,C250 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | 2005075 | Construct a multi-use trail along railroad right of way on the north side of Lake Crescent. | Transportation Enhancements | 2009-07-06 |  |  |  | 335000 | 6.400
11793 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | 2005076 | Construct an approximately 0.7 mile long mult-use trail along railroad right of way. | Transportation Enhancements | 2009-07-14 |  | 2009-09-16 | 2009-09-16 | 111000 | 0.682
11794 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | FRANKLIN | SPOKANE | 04 | 2011027 | Improve rail access into and out of the Port of Pasco's 'Big Pasco Industrial Center'. | Other | 2010-03-23 |  |  |  | 220000 | 0.000
11795 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | GARFIELD |  | 05 | 2012017 | Pavement resurfacing on the following roadways: Gould City-Mayview Rd, Iron Springs Rd, Mountain Rd, and Peola Rd. | Pavement Improvement | 2009-05-01 |  | 2009-07-27 | 2009-07-27 | 230915 | 14.990
11796 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | ISLAND |  | 02 | 2015076 | Pavement resurfacing of the following roadways in Island County: Front Street; Alexander Street; Maxwelton Road; 3rd Street; and NE Regatta Drive. | Pavement Improvement | 2009-08-27 |  |  | 2009-09-24 | 325167 | 2.970
11797 | Underway | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 07 | 2017090 | Construct a pedestrian walkway along SW 98th St. corridor between 12th Avenue SW and 11th Avenue SW. | Transportation Enhancements | 2009-06-25 |  |  |  | 1270557 | 0.050
11798 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 2019024 | Improve a visitor center located south of Ellensburg on the Yakima River Canyon Scenic Byway by adding gravel to the parking area, and replacing fencing and restroom facilities. | Transportation Enhancements | 2009-10-19 |  |  | 2009-11-03 | 41754.91 | 0.000
11799 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 2019025 | Installation of guardrail and related safety improvements on roadways within Kittitas County. | Safety/Traffic Management | 2009-09-14 |  |  | 2009-11-25 | 390012.61 | 2.200
11800 | Underway | C950 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT |  | 02 | 2029046 | Construct new ferry terminal main building on Anacortes. | Other | 2010-02-24 |  |  |  | 750000 | 0.000
11801 | Completed | C250,C220 | Highway Infrastructure Investment Grant | WASHINGTON | SKAMANIA |  | 03 | 2030005 | Rehabilitation and resurfacing of an asphalt pathway section along Cascade Drive from Hot Springs to Greenleaf in the City of North Bonneville. | Transportation Enhancements | 2009-07-30 |  | 2009-08-06 | 2009-08-06 | 13719 | 0.253
11802 | Underway | C250 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | 2037096 | Construct approximately 1.7 miles of shared bicycle-pedestrian trail adjacent to Haxton Way between Kwina Road and Slater Road. | Transportation Enhancements | 2010-03-29 |  |  |  | 250000 | 1.799
11803 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2506003 | Reconstruction of the roadway to include asphalt pavement resurfacing, new curb ramps, storm drainage repairs, and new bicycle lanes. | Pavement Improvement | 2009-07-07 |  |  | 2010-04-30 | 856977 | 0.500
11804 | Underway | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2523001 | Modify the existing Interstate 5/196th Street SW interchange to provide a pedestrian route across Interstate 5 and along 196th Street SW. | Transportation Enhancements | 2009-07-17 |  |  |  | 1250000 | 0.300
11805 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2528001 | Reconstruct existing two lane asphalt street. Includes new curb, gutter, sidewalk, drainage facilities, and bike lanes. | Pavement Improvement | 2010-04-01 |  |  |  | 818156 | 0.000
11806 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 01 | 2567001 | Overlay asphalt on Meridian Ave. from 228th St SE to NE 205th. The preservation includes milling, sub-grade repair as required, and pre-leveling. | Pavement Improvement | 2010-08-24 |  |  |  | 488367
11807 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2674004 | This safety project will replace an existing 4-way stop sign controlled intersection with a roundabout. | Pavement Improvement | 2010-01-11 |  |  | 2010-08-03 | 453431 | 0.200
11808 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2699002 | Asphalt resurfacing of 67th Ave from Grove Street to State Route 528 and 8th Street from State Ave to Cedar Ave. Includes replacing sidewalk ramps. | Pavement Improvement | 2009-08-17 |  | 2009-09-25 | 2009-09-14 | 428489.83 | 0.750
11809 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2701004 | Remove existing culvert, construct 600 feet of new stream channel, and install new culvert fully open to fish passage. | Pavement Improvement | 2009-08-17 |  |  | 2009-12-04 | 1403223 | 0.114
11810 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2722001 | Reconstruction of approximately 0.5 miles of roadway serving major residential and industrial areas. | Pavement Improvement | 2009-07-15 |  |  | 2010-05-28 | 888692 | 0.511
11811 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2787001 | Improve Holly Drive with the construction of curbs, gutters, sidewalks, and bike lanes. | Transportation Enhancements | 2009-09-14 |  |  | 2010-02-19 | 385447 | 0.200
11812 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 31BH001 | Reconstruct roadway and construct curb, gutter and sidewalk on 68th Avenue NW between approximately 279th Street NW and at 280th Street NW. | Pavement Improvement | 2009-08-13 |  |  | 2009-10-20 | 641439 | 0.200
11813 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 09 | 3217001 | Construct an extension of Shaw Road from Pioneer to E Main, including a new bridge over the Burlington Northern/Santa Fe railroad tracks. | New Construction | 2009-08-04 |  |  |  | 1201972 | 0.760
11814 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 06 | 3266006 | Construction of a new bridge that will eliminate four existing roadway/railroad crossings. | New Bridge Construction | 2009-07-31 |  |  |  | 15408000 | 0.400
11815 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 32DE001 | Rehabilitate the Rutter Parkway bridge by repairing bridge supports, removing the existing bridge deck, installing a new concrete deck, and resurfacing the adjacent roadway with asphalt. | Bridge Improvement | 2009-07-06 |  | 2009-08-19 | 2009-08-19 | 346837 | 0.044
11816 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON | RICHLAND-KENNEWICK | 04 | 3412007 | Construct approximately 0.5 miles of concrete sidewalk. Includes landscaping of an existing median. | Transportation Enhancements | 2009-06-22 |  | 2009-09-02 | 2009-09-02 | 112217.32 | 0.000
11817 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON | RICHLAND-KENNEWICK | 04 | 3502002 | Reconstruct roadway and construct bike lanes, curb, gutter, and sidewalks. Install traffic signal at George Washington. Add sidewalks along George Washington and 1st Street. | Pavement Widening | 2009-10-01 |  |  |  | 1600000 | 0.500
11818 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | 37A1001 | Asphalt resurfacing of the existing pavement. | Pavement Improvement | 2009-09-11 |  | 2009-09-28 | 2009-09-28 | 112304.45 | 0.720
11819 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3840008 | Asphalt resurfacing of the existing roadway, upgrade curb ramps, and improve the stormwater drainage system. | Pavement Improvement | 2009-07-20 |  |  | 2009-09-20 | 2606469 | 2.000
11820 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3867001 | Construction of a new roadway between Lincoln Road and Ash Street. Includes new sidewalks, curbs, bike lanes, and landscaping. Also includes asphalt resurfacing from Austin Road to Ash Street. | Pavement Improvement | 2009-05-08 |  |  |  | 112720 | 1.300
11821 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3867002 | Replace existing pavement with three inches of asphalt pavement. | Pavement Improvement | 2009-07-06 |  | 2009-08-27 | 2009-08-27 | 859000 | 1.950
11822 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3867003 | Reconstruct a portion of Five Mile Road between Berridae and Waikiki by replacing the existing pavement with a new asphalt pavement. The remaining portions of Five Mile Road will be resurfaced with o | Pavement Improvement | 2009-09-08 |  |  | 2009-10-05 | 331000 | 1.430
11823 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3936003 | Full depth replacement including sidewalk infill. | Pavement Improvement |  |  |  |  | 941642
11824 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 4053858 | Construct on and off ramps to provide relief in a highly congested area of I-405 in the vicinity of downtown Bellevue and the I-405/SR 520 Interchange. | Pavement Improvement | 2009-11-25 |  | 2012-12-31 | 2012-12-31 | 58937553.42 | 1.500
11825 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KING, SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 4053859 | Northbound I-405 will be widened to add an auxiliary (add/drop) lane between NE 195th Street and SR 527. | Pavement Widening | 2009-09-11 |  | 2010-06-18 | 2010-06-17 | 22991402 | 3.000
11826 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 4242022 | Improve rail access into the Port of Vancouver by providing new rail infrastructure within existing facilities, and new track at Terminal 5. | Other | 2009-11-09 |  |  | 2010-06-30 | 2500000 | 0.000
11827 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 4410002 | Widen NE 99th Street to three vehicle lanes, bicycle lanes, and sidewalks between State Route 503 and NE 137th Ave. | Pavement Improvement | 2009-10-19 |  |  | 2010-07-31 | 1831151 | 1.050
11828 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 4566009 | Reconstruct portions of the Nob Hill Boulevard pavement from 64th Avenue to 72nd Avenue. Includes improvements to the curb & gutter, sidewalk, stormwater drainage system, and street lighting. | Pavement Improvement | 2009-09-01 |  |  | 2009-10-28 | 766683 | 0.500
11829 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 4628006 | Asphalt resurfacing of the roadway, and upgrading of the curb ramps. | Pavement Improvement | 2009-07-20 |  | 2009-09-07 | 2009-09-07 | 400000 | 0.990
11830 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 4645001 | Widen and reconstruct approximately 0.3 miles of Beaudry Road, including curb and gutter, sidewalks, stormwater drainage system, and street lighting. | Pavement Improvement | 2009-07-20 |  |  | 2009-09-25 | 499214.46 | 0.284
11831 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 4708001 | Reconstruct approximately 0.7 miles of Speyers Road, from the west City limits to Fremont Avenue, including curb and gutter, sidewalk, stormwater drainage system, and street lighting. | Pavement Improvement | 2009-08-17 |  |  | 2009-12-04 | 1536259.07 | 0.680
11832 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON | OLYMPIA | 03 | 5235012 | Construction of a dedicated five foot wide bicycle path on the east side of the roadway, and relocation of the existing sidewalk to accommodate the new bicycle path. | Transportation Enhancements | 2009-07-29 |  |  | 2009-10-28 | 307144 | 0.660
11833 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON | OLYMPIA | 03 | 5235013 | Asphalt resurfacing of Capitol Blvd. from Dennis Street to Israel Road. | Pavement Improvement | 2009-08-10 |  | 2009-09-16 | 2009-09-16 | 159034 | 0.250
11834 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON | OLYMPIA | 03 | 5346001 | Asphalt resurfacing of Union Avenue from Capitol Way to Plum Street. | Pavement Improvement | 2009-07-28 |  |  |  | 1098824 | 0.440
11835 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON |  | 09 | 5394003 | Construct sidewalks, street lighting, and intersection crossing improvements on Steilacoom Road, between Stonewood Drive and Duterrow Road. | Transportation Enhancements | 2009-07-31 |  | 2009-09-02 | 2009-09-02 | 87360.12 | 0.170
11836 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | LEWIS |  | 03 | 5667003 | Asphalt resurfacing of Jackson Highway. | Pavement Improvement | 2009-07-09 |  | 2009-09-15 | 2009-09-15 | 736524.65 | 1.590
11837 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | ASOTIN |  | 05 | 6005002 | Asphalt resurfacing of Scenic Way from 2nd Avenue to Fleshman Way. | Pavement Improvement | 2009-08-16 |  |  | 2009-11-20 | 585994.82 | 0.980
11838 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | 6061001 | Asphalt resurfacing of the roadway, including improvements to curbs, sidewalks, bike path, and stormwater drainage system. | Pavement Improvement | 2009-08-24 |  |  | 2010-04-15 | 1200000 | 1.000
11839 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | 6065004 | Construction an approximately 0.5 mile long eight foot wide pedestrian path. | Transportation Enhancements | 2009-08-24 |  |  | 2009-11-24 | 28647 | 0.480
11840 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT | SEATTLE-TACOMA, WA | 02 | 6240001 | Reconstruct existing street with new curb, gutter, storm system, and street pavement. | Pavement Improvement | 2010-03-11 |  |  |  | 478806 | 0.000
11841 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 6340003 | Asphalt resurfacing of the intersection located at Yakima Valley Highway and Lincoln Avenue. | Pavement Improvement | 2009-11-09 |  |  | 2009-11-23 | 150000 | 0.200
11842 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 6408004 | Asphalt resurfacing of existing road surface; and reconstruction of driveways, crosswalk accesses, and sidewalks. | Pavement Improvement | 2009-09-14 |  |  | 2009-10-14 | 290839 | 0.210
11843 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP | BREMERTON | 01 | 6683004 | Project will improve safety and mobility on Viking Avenue by constructing a two-way left turn lane, bike lanes, stormwater drainage improvements, curb, sidewalk, and intersection channelization at Fin | Pavement Improvement | 2009-06-23 |  |  | 2009-12-06 | 2573948 | 0.660
11844 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP | BREMERTON | 01 | 6683005 | Construct bike lanes, curbs, gutter and sidewalks along Viking Avenue from Bovela Lane to a point approximately 1,000 ft south of Bovela Lane. Construct approximately 740 ft. of a continuous left tur | Pavement Improvement | 2010-04-19 |  |  |  | 824925 | 0.190
11845 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP | BREMERTON | 01 | 6701001 | Widen roadway shoulders near Blakely Elementary School to improve pedestrian safety. | Transportation Enhancements | 2009-08-03 |  | 2009-09-28 | 2009-09-28 | 150000 | 0.133
11846 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ | LONGVIEW (OR) | 03 | 6739001 | Roadway reconstruction and widening, and improvements to the roadway and intersection alignments to increase safety. | Pavement Widening | 2009-08-10 |  |  | 2009-12-18 | 1056593 | 1.230
11847 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ | LONGVIEW (OR) | 03 | 6763001 | Asphalt resurfacing of approximately 1.0 miles of South 13th Avenue. | Pavement Improvement | 2009-07-20 |  |  |  | 235554 | 0.975
11848 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 6949002 | Asphalt resurfacing and restriping of Canyon Road from Interstate 90 to Umptanum Road. | Pavement Improvement | 2009-06-23 |  | 2009-08-13 | 2009-08-13 | 325347.52 | 0.500
11849 | Awaiting NTP But Awarded | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 6949003 | Rotomill , HMA overlay existing asphalt roadway and placement of permanent pavement markings. | Pavement Improvement |  |  |  |  | 280000
11850 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK |  | 03 | 7042001 | Construct a new three lane roadway, with sidewalks and bicycle lanes. | New Construction | 2010-05-27 |  |  |  | 569529 | 0.760
11851 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | WALLA WALLA |  | 05 | 7166001 | Construct a multi-use pathway connecting major residential development, a local airport, schools, and the existing pedestrian system. | Transportation Enhancements | 2009-09-21 |  |  | 2009-10-10 | 58000 | 0.270
11852 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WALLA WALLA |  | 05 | 7169001 | Reconstruct 13th Avenue from Rose St. to Abadie St. and from Cherry St. to Rees Ave. Includes sidewalks, bike facilities, stormwater drainage facilities, street lighting, and traffic signals. | Pavement Widening | 2009-10-05 |  |  |  | 1980000 | 0.714
11853 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT | MOUNT VERNON | 02 | 7337006 | Construct an extension of Laventure Road extending south from Fowler St. to Blackburn Road. Roadway includes two traffic lanes, turn lane, bike lanes, and sidewalks. | New Construction | 2009-07-27 |  |  | 2010-03-19 | 923769 | 0.250
11854 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT |  | 02 | 7390001 | Reconstruct Fruitdale Road from State Route 20 to McGarigle Road. Includes construction of curbs, gutters, sidewalks, and street lighting. | Pavement Improvement | 2009-06-01 |  |  | 2010-05-10 | 134867 | 1.340
11855 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | 7418002 | Asphalt resurfacing of approximately 0.46 miles of the following roadways: Whitman St from Kamiaken to Maple, Maiden Lane from Whitman to Opal, and Opal from Maiden Lane to Campus. | Pavement Improvement | 2009-07-07 |  | 2009-08-04 | 2009-08-04 | 324566.08 | 0.462
11856 | Underway | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | 7541001 | Reconstruct and widen Mount Pleasant Road. | Pavement Improvement | 2009-08-31 |  |  |  | 568000 | 0.400
11857 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 7690002 | The construction of a turn lane, curb, sidewalk, street lighting and bicycle pathways on Cheney-Spangle Road from State Route 904 to Cheney City limits. | Transportation Enhancements | 2009-09-08 |  |  |  | 576416 | 0.400
11858 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 7690003 | Install concrete pads and sidewalks to accommodate pedestrian access over the rail lines. | Transportation Enhancements | 2010-02-16 |  |  |  | 106000 | 0.070
11859 | Underway | C250 | Highway Infrastructure Investment Grant | WASHINGTON | ISLAND |  | 02 | 7790002 | Widening of Ault Field Road between Oak Harbor Road and Goldie Road to provide an additional travel lane. | Pavement Improvement | 2009-07-23 |  |  |  | 1357704 | 0.240
11860 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | 8037001 | Reconstruction of existing road and construction a new road on 2nd Ave from Washington to Portal Way at the Interstate-5 southbound offramp. | New Construction | 2009-09-01 |  |  | 2010-07-23 | 1541000 | 0.500
11861 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 8051001 | Asphalt resurfacing of Euclid Road from Forsell Road to Stassen Way. | Pavement Improvement | 2009-06-25 |  | 2009-08-21 | 2009-08-21 | 308198.35 | 0.767
11862 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 8057001 | Replace the asphalt pavement, improve storm drainage, construct sidewalks, provide street and pedestrian lighting, and landscaping. | Transportation Enhancements | 2010-03-16 |  |  |  | 2030000 | 0.000
11863 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | 8158001 | Widening and asphalt resurfacing of roadway; and improvements to curb, gutter, and stormwater drainage. | Pavement Improvement | 2009-06-09 |  |  | 2010-05-12 | 981169 | 0.600
11864 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | 9905005 | Asphalt resurfacing of existing street, striping, and curb ramp installation. | Pavement Improvement | 2009-08-10 |  |  |  | 393000 | 0.341
11865 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | STATEWIDE | 03 | 9906026 | Asphalt resurfacing of the following locations: NW 9th Ave, NW 119th St/7th Ave/NW 114th St, NE 72nd Ave, SE Gibson Rd, NW 199th St, NE 20 Ave/Union Rd, NE 78th St/76th St, NW 151st/139th Sts/Tenny R | Pavement Improvement | 2010-04-22 |  |  |  | 668849 | 10.530
11866 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | SPOKANE | 03 | 9906027 | Asphalt resurfacing of the following locations: N. Parkway Ave, NW 25th St, SW 20th Ave, SE Eaton Blvd, S. Parkway Ave, and NW 20th Ave. | Pavement Improvement | 2010-05-18 |  |  | 2010-06-18 | 406212 | 0.000
11867 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 9906028 | Pavement overlays on SE 34th St, NE 112th Ave, Andresen Rd, Columbia Way, Grand Blvd, Hearthwood Blvd, Stapleton Rd, and Mill Plain Blvd. | Pavement Improvement | 2010-05-19 |  |  |  | 2500000 | 0.000
11868 | Completed | C200,C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 08 | 9927049 | Construction of pedestrian amenities to include sidewalks, curb ramps, street lighting, and landscaping. | Pavement Widening | 2009-09-21 |  |  | 2010-05-18 | 632296 | 1.000
11869 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 09 | 9927050 | Provide fiber interconnect between City buildings for traffic signal intelligent transportation system (ITS). Fiber interconnect will be routed via existing utility poles and existing conduit. | Safety/Traffic Management |  |  |  |  | 192704
11870 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 9933001 | Asphalt resurfacing of Williams Lake and Cedonia-Addy Roads. | Pavement Improvement | 2009-06-22 |  | 2009-07-15 | 2009-07-15 | 943262.42 | 33.370
11871 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM | BELLINGHAM | 02 | 9937002 | Installation of enhanced pedestrian crossings on high volume streets to improve safety and connectivity. Improvements include flashing lights, illuminated signage, and concrete pedestrian refuge isla | Transportation Enhancements | 2009-07-22 |  |  | 2009-12-29 | 308596 | 0.100
11872 | Underway | C200,C230 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM | STATEWIDE | 02 | 9937003 | Pavement preservation resurfacing of all-weather arterials. Arterials include East Bakerview Road (Landon Road to Hannegan Road) and Hannegan Road (East Bakerview Road to Sunset Drive). | Pavement Improvement | 2010-05-17 |  |  |  | 1600000 | 2.490
11873 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 9939018 | Asphalt resurfacing of Rudkin Road and the Main Street/Ahtanum Road Intersection. | Pavement Improvement | 2009-09-08 |  |  | 2009-11-13 | 246896.59 | 0.504
11874 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PACIFIC |  | 03 | 9999546 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 2009-04-23 | 2009-05-18 | 2009-07-31 | 2009-07-31 | 394691 | 3.970
11875 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | 9999547 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-05-14 | 2009-06-08 | 2009-11-10 | 2009-11-10 | 5526450.89 | 13.490
11876 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT, OKANOGAN |  | Multiple | 9999548 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 2009-05-13 | 2009-05-28 | 2009-08-30 | 2009-08-30 | 3294919.43 | 68.500
11877 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS, ADAMS, FERRY |  | 05 | 9999549 | Replace portable Highway Advisory Radio (HAR) trailers deployed on SR 20 and US 395 for Sherman Pass with permanent HAR stations and install a new station in the vicinity of the Hatton Coulee Rest Are | Safety/Traffic Management | 2009-07-01 | 2009-10-06 | 2009-11-17 | 2009-11-17 | 239999.93 | 0.000
11878 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STATEWIDE |  |  | 9999550 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Other |  |  |  |  | 187498.16
11879 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STATEWIDE |  |  | 9999551 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Other |  |  |  |  | 365573.7
11880 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT, CHELAN, BENTON, DOUGLAS, LINCOLN, FRANKLIN, YAKIMA, SPOKANE |  | Multiple | 9999554 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2009-08-17 | 2009-08-24 | 2009-09-22 | 2009-09-22 | 581025.58 | 235.740
11881 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PACIFIC, CLARK, KITSAP, LEWIS, MASON, JEFFERSON, THURSTON, GRAYS HARBOR, PIERCE, COWLITZ, CLALLAM |  | Multiple | 9999555 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2010-03-17 |  | 2010-11-19 | 2010-11-19 | 708200 | 180.020
11882 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | ISLAND, SKAGIT, KING, SNOHOMISH, WHATCOM |  | Multiple | 9999556 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2009-08-11 | 2009-08-11 | 2009-11-12 | 2009-11-12 | 822601 | 147.790
11883 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KING, THURSTON, WHATCOM |  | Multiple | 9999557 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2009-08-07 | 2009-08-17 | 2010-03-31 | 2010-03-31 | 946131 | 6.009
11884 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT, KITTITAS |  | 04 | 9999558 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2009-08-17 | 2009-10-05 | 2009-11-09 | 2009-11-09 | 804861.74 | 10.620
11885 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | MASON, KITSAP, THURSTON |  | Multiple | 9999576 | Install high tension cable barrier in the median to prevent crossover collisions. | Safety/Traffic Management | 2010-04-28 |  |  | 2010-09-30 | 330389
11886 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT, OKANOGAN |  | Multiple | 9999577 | Overlay pavement with a chip seal | Pavement Improvement | 2010-04-07 |  |  |  | 2632580
11887 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS, KING, YAKIMA, SNOHOMISH |  | Multiple | 9999578 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2010-04-12 |  | 2010-10-29 | 2010-10-29 | 1183326
11888 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 9999585 | Asphalt overlay of Broadway between 24th Street and 20th Street, and Pacific Avenue between Maple and Fulton. Includes utility adjustments, ADA improvements, and all other associated work. | Pavement Improvement |  |  |  |  | 640290
11889 | Awaiting NTP But Awarded | C200 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON |  | 04 | A031002 | Realign Webber Canyon Road and construct a new Burlington Northern/Santa Fe Railroad underpass to improve safety by eliminating the roadway/railroad crossing. | Pavement Improvement |  |  |  |  | 1000647 | 0.300
11890 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON |  | 04 | A032001 | Reconstruction of Sheridan Avenue from Third Street to Sixth Street including sidewalks, curb and gutter, drainage, and street lighting. | Pavement Improvement | 2009-07-20 |  |  | 2009-10-30 | 473511 | 0.275
11891 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | CHELAN |  | 04 | A045002 | Reconstruct asphalt pavement, increase the vertical clearance at a railroad trestle, and construct a shared-use path through the trestle. | Pavement Improvement | 2009-06-08 |  |  | 2009-10-26 | 1021318 | 0.560
11892 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | A058001 | Asphalt resurfacing and minor roadway widening to add curb, gutter and sidewalk. | Pavement Improvement | 2009-08-12 |  |  | 2009-12-11 | 160000 | 0.510
11893 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | A083002 | Asphalt pavement resurfacing, including improvements to the street lighting, sidewalks, crosswalks, and stormwater drainage. | Transportation Enhancements | 2009-09-08 |  |  |  | 416250 | 0.300
11894 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | LINCOLN |  | 05 | A221003 | Asphalt resurfacing of approximately 4 miles of roadway. | Pavement Improvement | 2009-07-20 |  | 2009-07-30 | 2009-07-30 | 654000 | 4.240
11895 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SKAMANIA |  | 03 | A301006 | Asphalt pavement resurfacing of approximately 1.0 mile of Wind River Road. | Pavement Improvement | 2009-07-30 |  | 2009-08-06 | 2009-08-06 | 306711 | 0.920
11896 | Underway | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON |  | 03 | A341004 | Widen existing two lane roadway to add a two way center left turn lane on Old Highway 99; and replace existing bridge with a new 5 traffic lane bridge, including bike lanes, sidewalks, and illuminatio | Bridge Replacement | 2010-02-22 |  |  |  | 1330000 | 0.800
11897 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | A381004 | Asphalt resurfacing and striping of approximately 5.5 miles of Wawawai Road. | Pavement Improvement | 2009-08-11 |  | 2009-09-04 | 2009-09-04 | 782204.39 | 5.440
11898 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | A393001 | Asphalt resurfacing of Harrah Road from South Town Limits to North Town Limits. | Pavement Improvement | 2009-09-14 |  |  | 2009-10-09 | 340395.33 | 0.625
11899 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | ADAMS |  | 04 | B012002 | Resurface approximately 3.0 miles of roadway with two inches of asphalt. | Pavement Improvement | 2009-07-08 |  | 2009-07-27 | 2009-07-27 | 707273.49 | 3.030
11900 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK |  | 03 | B063002 | Asphalt resurfacing of Hillhurst Road between South 15th Circle and South 22nd Circle. | Pavement Improvement | 2009-08-25 |  | 2009-09-18 | 2009-09-18 | 168054 | 0.560
11901 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | COLUMBIA |  | 05 | B071002 | Resurface existing 24 ft wide road with asphalt. | Pavement Improvement | 2010-06-01 |  |  | 2010-08-02 | 465000 | 0.000
11902 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | COLUMBIA |  | 05 | B074001 | Asphalt resurfacing of East Dayton Avenue from Front Street to US 12. | Pavement Improvement | 2009-08-24 |  | 2009-10-05 | 2009-10-05 | 225000 | 0.250
11903 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | FRANKLIN |  | 04 | B111002 | Relocation of the south 1.1 miles of the R-170 Road outside of the existing roadside slide area. | Pavement Improvement | 2009-09-08 |  |  | 2009-11-06 | 750000 | 1.100
11904 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | PACIFIC |  | 03 | B256007 | Asphalt resurfacing of Sandridge Road from State Route 101 to 67th Place; and install a traffic signal at the intersection of Sandridge Road and Sid Snyder Drive. | Pavement Improvement | 2009-08-03 |  |  | 2009-10-20 | 279396 | 1.620
11905 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | B391002 | Asphalt resurfacing of South Camas Street, from 3rd Street to 9th Street. | Pavement Improvement | 2009-10-07 |  |  | 2009-11-03 | 312000 | 0.400
11906 | Underway | C250 | Highway Infrastructure Investment Grant | WASHINGTON | WAHKIAKUM |  | 03 | C350002 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-17 | 2009-06-29 | 2009-12-28 |  | 200000 | 27.760
11907 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP |  | 06 | D185001 | Construction of approximately 1.5 miles of new roadway, intersection improvements, bicycle lanes, and a separated asphalt pedestrian path. | New Construction | 2009-10-12 |  |  |  | 2623386 | 1.500
11908 | Underway | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | PEND OREILLE |  | 05 | D261001 | Asphalt resurfacing of Deer Valley Road from Coyote Trail to Gray Road. | Pavement Improvement | 2009-09-14 |  |  |  | 465226.3 | 1.170
11909 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | SAN JUAN |  | 02 | D281003 | Asphalt resurfacing of Fisherman Bay Road, and installation of safety fencing. | Pavement Improvement | 2009-08-28 |  | 2009-09-24 | 2009-09-24 | 416620 | 1.760
11910 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT |  | 02 | D291002 | Asphalt resurfacing of Maple Avenue from Morris Street to Caledonia Street, installation of curb ramps. | Pavement Improvement | 2009-08-06 |  | 2009-08-29 | 2009-08-29 | 154800 | 0.502
11911 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | OKANOGAN |  | 05 | F241005 | Asphalt resurfacing of approximately 0.5 miles of Main Street (from south city limits to Lake Street) & East Lake Street (from Main Street east to city limits). | Pavement Improvement | 2009-06-15 |  | 2009-06-19 | 2009-06-19 | 119071.16 | 0.540
11912 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | H310001 | Asphalt pavement resurfacing on 84th Street NE. | Pavement Improvement | 2010-02-03 |  |  | 2010-04-20 | 481976 | 4.720
11913 | Awaiting NTP But Awarded | C200,C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | I329001 | Reconstruct pavement section between existing curbs. Replace ADA non-conforming handicap ramps. | Pavement Improvement |  |  |  |  | 997091
11914 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | I382004 | Asphalt resurfacing of South Main Street from State Route 195 to the Fairview Street and Meadow intersection. | Pavement Improvement | 2009-09-08 |  | 2009-09-21 | 2009-09-21 | 141069 | 0.284
11915 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | MASON |  | 06 | K232001 | Asphalt resurfacing of approximately 1.6 miles of McEwan Prairie Road. | Pavement Improvement | 2009-08-26 |  | 2009-09-04 | 2009-09-04 | 288576.34 | 1.620
11916 | Underway | C220,C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON |  | 03 | K340001 | Widen and provide an asphalt overlay of Minnesota Street, construct sidewalks and crosswalks, and update traffic signs. | Pavement Improvement | 2009-08-25 |  |  |  | 690816.95 | 0.300
11917 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | FERRY |  | 05 | L102009 | Asphalt resurfacing of approximately 9 miles of Bridge Creek Road. | Pavement Improvement | 2010-05-01 |  |  |  | 339046 | 7.110
11918 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | KLICKITAT |  | 03 | L201003 | Asphalt resurfacing of approximately 2.4 miles of South Columbus Street. | Pavement Improvement | 2009-09-04 |  |  | 2009-11-11 | 469572.54 | 2.390
11919 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KLICKITAT |  | 03 | M201002 | Asphalt resurfacing of approximately 1.6 miles of Bickleton Highway. | Pavement Improvement | 2009-09-04 |  |  | 2009-11-11 | 255000 | 1.580
11920 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | P130002 | Construction of a new concrete bridge. | Bridge Replacement | 2009-11-16 |  |  | 2010-04-01 | 750000 | 0.120
11921 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | P137001 | Asphalt resurfacing of approximately 2.0 miles of L-NE Road from Kittleson to 3-NE Road. | Pavement Improvement | 2009-07-06 |  | 2009-07-28 | 2009-07-28 | 487009 | 2.010
11922 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | P368001 | Constructs approximately 0.1 miles of new roadway to provide an improved roadway connector between State Route 543 and the commercial and industrial areas. | New Construction | 2009-08-21 |  |  | 2010-03-21 | 348000 | 0.133
11923 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | JEFFERSON |  | 06 | Q161007 | Asphalt resurfacing of approximately 2.0 miles of Center Road. | Pavement Improvement | 2009-07-20 |  | 2009-08-07 | 2009-08-07 | 358000 | 2.000
11924 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | T371008 | Replace the existing bridge on Hannegan Road over Scott Ditch, south of Lynden, Washington. | Bridge Replacement | 2009-08-03 |  |  | 2009-11-06 | 600000 | 0.050
11925 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | X085001 | Reconstruct roadway to include curb, gutter and sidewalk. Includes channelization improvements to the existing intersection with State Route 504. | Pavement Widening | 2009-07-14 |  |  |  | 330000 | 0.730
11926 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | LEWIS |  | 03 | Y210001 | Reconstruction and asphalt resurfacing of approximately 2.3 miles of Davis Lake Road. | Pavement Improvement | 2009-07-09 |  | 2009-09-15 | 2009-09-15 | 1027000 | 2.290
11927 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | Y329008 | Reconstruction of Crawford Avenue, including the installation of a roundabout, curb and gutter, sidewalk, and stormwater drainage system. | Pavement Improvement | 2009-05-11 |  | 2009-09-15 | 2009-09-15 | 1674431 | 0.610
11928 | Underway | C200 | Highway Infrastructure Investment Grant | WASHINGTON | MASON |  | 06 | Z923001 | Install solar street lights at intersections within Mason County. | Safety/Traffic Management | 2010-03-18 |  |  |  | 150000 | 0.000
11929 | Awaiting NTP But Awarded | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | Z932004 | Arterial Street preservation on N 6th, G, N 2nd, Oakland. Includes asphalt repair and overlay, and sidewalk repair. | Pavement Improvement |  |  |  |  | 500000
11930 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | Z939004 | Asphalt resurfacing of 2nd Street and 3rd Street. Includes replacement of substandard curb, gutter, and sidewalk along 2nd Street, 3rd Street, and Canal Street. | Pavement Improvement | 2009-08-17 |  | 2009-09-24 | 2009-09-24 | 326000 | 0.227
11931 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PLEASANTS |  | 01 | 0002474 | This project will improve safety for motorists by resurfacing 2.72 miles of West Virginia 2 from the City of Waverly to Willow Island Road in Pleasants County. | Pavement Improvement | 2009-04-21 | 2009-05-27 | 2009-10-30 | 2009-07-24 | 799200 | 2.720
11932 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002479 | This project will improve safety for motorists by resurfacing 1.04 miles of West Virginia Route 2 from the Brooke County/Hancock County line to Penn Avenue Road | Pavement Improvement | 2010-02-22 | 2010-04-13 | 2010-06-30 | 2010-06-25 | 614200 | 1.040
11933 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002481 | This project will improve safety for motorists by resurfacing 1.5 miles of deteriorated pavement on West Virginia 2 from the City of Wellsburg to Cross Creek Road in Brooke County. | Pavement Improvement | 2010-02-22 | 2010-05-21 | 2010-06-30 | 2010-06-24 | 586900 | 1.500
11934 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | OHIO | WHEELING (OH) | 01 | 0002482 | This project will improve safety for motorists by resurfacing 0.37 miles of deteriorated pavement on West Virginia 2 at milepoint 0.00 and resurfacing 1.39 miles of West Virginia Route 88 from Peter's | Pavement Improvement | 2010-04-01 | 2010-05-12 | 2010-06-30 |  | 508900 | 0.370
11935 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002483 | This project will improve safety for motorists by resurfacing 1.31 miles of deteriorated pavement on West Virginia Route 2 from the City of Weirton to Kings Creek Road in Hancock County. | Pavement Improvement | 2009-12-01 | 2010-04-13 | 2010-06-30 |  | 482830 | 1.310
11936 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002484 | This project will improve safety for motorists by resurfacing 1.55 miles of deteriorated pavement on West Virginia Route 2 from the City of New Cumberland to Moscow Road in Hancock County. | Pavement Improvement | 2009-12-01 | 2010-04-23 | 2010-06-30 | 2010-06-25 | 378193 | 1.550
11937 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002487 | This project will extend the life of the historic Ohio River Market Street Bridge by repairing bridge components, replacing the lighting and light fixtures on the bridge, cleaning the structrue and re | Bridge Improvement | 2009-12-10 | 2010-01-11 | 2011-11-30 |  | 10594435 | 0.010
11938 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONROE |  | 03 | 0003216 | This project will improve safety for motorists by resurfacing the deck of the Alderson Bridge with Latex Modified Concrete. The bridge is located on West Virginia Route 3 at approximately milepoint 0. | Bridge Improvement | 2009-05-12 | 2009-08-31 | 2009-10-30 | 2009-11-02 | 558200 | 0.170
11939 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BOONE |  | 03 | 0003217 | This project will improve safety for motorists by resurfacing 1.67 miles of deteriorated pavement and replace the existing guardrails on West Virginia Route 3 from the Big Coal River Bridge to West Vi | Pavement Improvement | 2009-04-28 | 2009-05-05 | 2009-10-30 | 2009-08-11 | 576100 | 1.670
11940 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0003218 | This project will extend the life of two bridges, the County Route 3 Turnpike Overpass Bridge and the Camp Creek Overpass Bridge #2, by cleaning the structures and then painting them. The bridges are | Bridge Improvement | 2009-07-21 | 2009-07-25 | 2009-10-15 | 2009-09-03 | 380400 | 0.070
11941 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | SUMMERS |  | 03 | 0003220 | This project will improve safety for motorists by resurfacing 1.60 miles of WV 3 Summers County between Lowell and Pence Spring Road. | Pavement Improvement |  |  | 2010-10-15 |  | 496800 | 1.600
11942 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TAYLOR |  | 01 | 0003221 | This project will improve safety for motorists by replacing the Berry Run Bridge due to condition. The bridge is located on County Route 3 at approximately milepoint 0.16 in Taylor County. | Bridge Replacement | 2010-01-11 | 2010-03-22 | 2010-07-30 |  | 384120 | 0.010
11943 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0003222 | This project will improve safety for motorists by the installation of piling for embankment stabilization on West Virginia Route 3 (Metalton Road) at approximately milepoint 29.13 in Raleigh County. | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2009-10-30 | 2009-06-30 | 311600 | 0.010
11944 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BOONE |  | 03 | 0003223 | This project will improve safety for motorists by resurfacing 1.71 miles of WV 3 in Boone County from Drawdy Creek to Peytona. | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-10-15 |  | 648200 | 1.710
11945 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HARRISON |  | 01 | 0005119 | This project will improve safety for motorists by replacing the Big Arch Bridge due to condition. The bridge is located on County Route 5 at approximately milepoint 2.46 in Harrison County. | Bridge Replacement | 2009-11-13 | 2010-04-22 | 2010-06-30 |  | 517530 | 0.010
11946 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TAYLOR |  | 01 | 0007219 | This project will improve safety for motorists by replacing the Irontown Girder Bridge due to condition. The bridge is located on County Route 7 at approximately milepoint 3.2 in Taylor County. | Bridge Replacement | 2009-09-21 | 2009-11-11 | 2010-06-30 |  | 828900 | 0.010
11947 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WIRT |  | 02 | 0007221 | This project will improve safety for motorists by resurfacing 4.36 miles of deteriorated pavement on County Route 7 (Garfield Road) beginning at milepoint 6.10 in Wirt County. | Pavement Improvement | 2009-09-02 | 2009-09-19 | 2009-10-30 | 2009-11-04 | 760846 | 4.360
11948 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0009194 | This project will extend the life of the 4-U Bridge by cleaning and painting the structure. The bridge is located on County Route 9 at approximately milepoint 9.24 in Pendleton County. | Bridge Improvement | 2009-06-08 | 2010-04-12 | 2009-10-15 | 2010-04-21 | 171500 | 0.010
11949 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | JEFFERSON |  | 02 | 0009196 | This project will reduce traffic congestion and improve access to the area by the upgrade of the existing West Virginia Route 9 to four lanes and the construction of a new bridge. The project is loca | Pavement Widening | 2009-09-22 | 2009-09-22 | 2011-05-31 |  | 18743700 | 0.270
11950 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HARRISON |  | 01 | 0009197 | This project will improve safety for motorists by replacing the West Robey Arch Bridge due to condition. The bridge is located on County Route 9 at approximately milepoint 6.75 in Harrison County. | Bridge Replacement | 2009-11-12 | 2009-11-17 | 2010-06-30 | 2010-06-01 | 557670 | 0.010
11951 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BARBOUR |  | 01 | 0011124 | This project will improve safety for motorists by resurfacing 4.46 miles of deteriorated pavement on County Route 11 (Audra Park Road) in Barbour County. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2009-10-30 | 2009-09-26 | 468496 | 4.460
11952 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0012048 | This project will improve safety for motorists by replacing the Deer Run Park Bridge due to condition. The bridge is located on County Route 12 at approximately milepoint 4.15 in Pendleton County. | Bridge Replacement | 2009-10-13 | 2010-04-06 | 2010-06-10 |  | 416270 | 0.010
11953 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TYLER |  | 01 | 0013056 | This project will improve safety for motorists by replacing the Walnut Fork Bridge due to condition. The bridge is located on County Route 13 at approximately milepoint 6.06 in Tyler County. | Bridge Replacement | 2009-08-05 | 2010-03-02 | 2010-07-30 | 2010-06-28 | 537310 | 0.010
11954 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA |  | 02 | 0015078 | This project will improve safety for motorists by replacing the Middle Fork Bridges due to condition. The bridges are located on County Route 15 at approximately milepoint 13.71 in Kanawha County. | Bridge Replacement | 2009-09-18 | 2010-03-02 | 2010-06-30 |  | 760920 | 0.010
11955 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | DODDRIDGE |  | 01 | 0015079 | This project will improve safety for motorists by replacing Long Run Bridge due to condition. The bridge is located on County Route 15 at approximately milepoint 2.18 in Doddridge County. | Bridge Replacement | 2009-10-09 | 2009-11-02 | 2010-06-30 |  | 720210 | 0.010
11956 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RITCHIE |  | 01 | 0016205 | This project will improve safety for motorists by resurfacing 3.26 miles of deteriorated pavement on West Virginia 16 from the City of Washburn to Harrisville Road in Ritchie County. | Pavement Improvement | 2009-06-18 | 2009-07-11 | 2009-07-30 | 2009-09-05 | 718511 | 3.260
11957 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CALHOUN |  | 02 | 0016206 | This project will improve safety for motorists by resurfacing 1.31 miles of deteriorated pavement on West Virginia Route 16 from the City of Grantsville to Smithville Road in Calhoun County. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2009-09-11 | 2009-09-03 | 401720 | 1.310
11958 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0016207 | This project will improve safety for motorists by resurfacing 0.47 miles of West Virginia Route 16 from South Oakwood Avenue to Bus Station Road in Beckley, Raleigh County. | Pavement Improvement | 2009-07-10 | 2009-07-20 | 2009-10-30 | 2009-10-08 | 516059 | 0.470
11959 | Awaiting NTP But Awarded | C250,C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CLAY |  | 02 | 0016210 | This project will improve safety for motorists by resurfacing 7.63 miles of WV 16 from Lizemore to Clay RD in Clay County. | Pavement Improvement |  |  | 2010-10-15 |  | 1917100 | 7.630
11960 | Awaiting NTP But Awarded | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | STATEWIDE |  |  | 0016215 | This project will improve safety for motorists by the installation or replacement of guardrail along West Virginina Route 16 in Fayette County. | Safety/Traffic Management |  |  | 2010-10-15 |  | 92300 | 1.660
11961 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WETZEL |  | 01 | 0017086 | This project will improve safety for motorists by replacing the McBee Bridge due to condition. The bridge is located on County Route 17 at approximately milepoint 3.68 in Wetzel County. | Bridge Replacement | 2009-12-16 | 2009-12-16 | 2010-07-30 |  | 453800 | 0.010
11962 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TYLER |  | 01 | 0018119 | This project will improve safety for motorists by the installation of piling for embankment stabilization at five locations beginning at milepoint 11.12 and extending 0.50 miles on West Virginia 18 in | Pavement Improvement | 2009-12-01 | 2010-05-11 | 2010-07-30 |  | 962820 | 0.500
11963 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0019337 | This project will improve safety for motorists by resurfacing the deck of the New River Gorge Bridge located in Fayette County on United States Route 19 at the approximate milepoint 15.37 with Latex M | Bridge Improvement | 2010-04-01 | 2010-04-09 | 2010-06-30 |  | 918300 | 0.010
11964 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0019338 | This project will improve safety for motorists by resurfacing 1.94 miles of United States Route 19 from the City of Fockler Branch to Muddlety Road in Nicholas County. | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2009-10-30 | 2009-09-02 | 1301100 | 1.940
11965 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | LEWIS |  | 02 | 0019339 | This project will improve safety for motorists by resurfacing 1.89 miles of deteriorated pavement on United States Route 19 in the City of Weston, Lewis County. | Pavement Improvement | 2009-05-22 | 2009-06-29 | 2009-10-30 | 2009-07-08 | 305396 | 1.890
11966 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0019340 | This project will help eliminate congestion by the relocation and upgrade to four lanes of United States Route 19 beginning at approximately milepoint 15.52 and bridge improvements ending at the South | New Construction | 2009-08-20 | 2009-09-18 | 2011-08-30 |  | 22190000 | 0.890
11967 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0019343 | This project will improve safety for motorists by resurfacing 0.50 miles of deteriorated pavement on United States Route 19 from the City of Prosperity to the Crossroads Mall in Raleigh County. | Pavement Improvement | 2009-09-04 | 2009-10-01 | 2009-10-30 | 2009-10-16 | 347814 | 0.500
11968 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0020254 | This project will improve safety for motorists by replacing the existing and failing piling currently restricting slippage of the embankment on West Virginia Route 20 at approximately milepoint 26.75 | Pavement Improvement | 2009-09-01 | 2009-09-01 | 2009-10-30 | 2009-09-28 | 199389 | 0.010
11969 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | UPSHUR |  | 02 | 0020255 | This project will improve safety for motorists by resurfacing 2.02 miles of West Virginia 20 From the City of French Creek to Adrian Road in Upshur County. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-10-30 | 2009-07-13 | 303578 | 2.020
11970 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0020256 | This project will improve safety for motorists by the construction of a 1.23 mile long truck climbing lane on West Virginia Route 20 in Greenbrier County. | Pavement Widening | 2009-11-25 | 2009-12-10 | 2010-06-30 |  | 2201710 | 1.230
11971 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MASON |  | 02 | 0029022 | This project will improve safety for motorists by replacing the Arlee Slab Bridge due to condition. The bridge is located on County Route 29 at approximately milepoint 5.59 in Mason County. | Bridge Replacement | 2009-07-31 | 2009-11-10 | 2009-10-15 | 2010-05-25 | 317380 | 0.010
11972 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0033320 | This project will improve safety for motorists by resurfacing the deck of the Judy Gap Bridge with Latex Modified Concrete. The bridge is located on United States Route 33 at approximately milepoint 1 | Bridge Improvement | 2009-11-16 | 2010-05-03 | 2010-06-30 |  | 322200 | 0.050
11973 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | UPSHUR |  | 02 | 0033321 | This project will improve safety for motorists by resurfacing 4.53 miles of United States Route 33 from the City of Buckhannon to Elkins Road in Upshur County. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-10-30 | 2009-08-15 | 1399266 | 4.530
11974 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | JACKSON |  | 02 | 0033322 | This project will improve safety for motorists by resurfacing 4.16 miles of deteriorated pavement on United States Route 33 from the City of Ripley to Frozencamp Road in Jackson County. | Pavement Improvement | 2009-07-01 | 2009-07-11 | 2009-09-01 | 2009-09-14 | 1278600 | 4.160
11975 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 0033323 | This project will improve safety for motorists by resurfacing 1.75 miles of deteriorated pavement, drainage improvements and the construcion of a truck climbing lane on United States Route 33 (Shavers | Pavement Widening | 2010-05-07 | 2010-05-21 | 2010-09-30 |  | 2753900 | 1.760
11976 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0033327 | This project will improve safety for motorists by replacing the Rough Run Bridge due to condition. The bridge is located on County Route 3/3 at approximately milepoint 0.73 in Pendleton County. | Bridge Replacement | 2009-10-29 | 2010-02-04 | 2010-06-30 | 2010-05-12 | 502940 | 0.010
11977 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0034067 | This project will improve safety for motorists by replacing the Horse Creek Bridge #5 due to condition. The bridge is located on County Route 3/4 at approximately milepoint 2.12 in Raleigh County. | Bridge Replacement | 2009-09-16 | 2009-09-17 | 2010-06-30 | 2010-05-07 | 459850 | 0.009
11978 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CLAY |  | 02 | 0036040 | This project will improve safety for motorists by resurfacing 5.24 miles of WV 36 from Wallback to Clay RD in Clay County. | Pavement Improvement | 2010-05-03 | 2010-06-02 | 2010-10-15 |  | 1160700 | 5.240
11979 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WAYNE | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0037028 | This project will improve safety for motorists by the installation of piling for embankment stabilization on West Virginia Route 37 at milepoint 18.64 in Wayne County. | Pavement Improvement | 2009-11-12 | 2009-12-01 | 2010-06-30 |  | 209143 | 0.030
11980 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0039406 | This project will improve safety for motorists by resurfacing 1.29 miles of deteriorated pavement on West Virginia 39 (Deer Creek Road) beginning at approximately milepoint 35.12 in Nicholas County. | Pavement Improvement | 2009-05-29 | 2009-06-26 | 2009-10-30 | 2009-09-03 | 388600 | 1.290
11981 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0041072 | This project will improve safety for motorists by resurfacing 2.10 miles of deteriorated pavement on West Virginia 41 from the City of Glade Creek to Nile Road in Nicholas County. | Pavement Improvement | 2009-10-14 | 2009-10-30 | 2010-05-30 | 2009-11-09 | 570700 | 2.010
11982 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RITCHIE |  | 01 | 0050276 | This project will improve safety for motorists by resurfacing 2.18 miles of deteriorated pavement on United States Route 50 between Nutter Farm and Camp Run Road beginning at approximately milepoint 2 | Pavement Improvement | 2009-04-21 | 2009-06-28 | 2009-09-22 | 2009-09-03 | 944561 | 2.180
11983 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RITCHIE |  | 01 | 0050277 | This project will improve safety for motorists by resurfacing 2.23 miles of deteriorated pavement on United States Route 50 between Camp run Road and Ellenboro Road beginning at approximately milepoin | Pavement Improvement | 2009-04-21 | 2009-07-04 | 2009-09-08 | 2009-08-12 | 965687 | 2.230
11984 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HAMPSHIRE |  | 02 | 0050278 | This project will improve safety for motorists by resurfacing 0.86 miles and the construction of a center turning lane on United States Route 50 at approximately milepoint 8.50 in Hampshire County. | Pavement Improvement | 2009-08-31 | 2009-09-10 | 2010-06-30 |  | 3693560 | 1.580
11985 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TAYLOR |  | 01 | 0050279 | This project will improve safety for motorists by the construction of a 1.90 mile truck climbing lane and the realignment of a hazardous curve on United States Route 50 beginning at milepoint 3.46 in | Pavement Widening | 2009-06-22 | 2009-08-10 | 2009-10-30 |  | 2338680 | 1.900
11986 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HARRISON |  | 01 | 0050280 | This project will improve safety for motorists by resurfacing 2.68 miles of US 50 in Harrison County. | Pavement Improvement | 2010-04-01 | 2010-06-07 | 2010-10-29 |  | 2144700 | 2.680
11987 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WAYNE |  | 03 | 0052263 | This project will improve safety for motorists by resurfacing 2.29 miles of United States Route 52 from the City of Stonecoal to the Mingo County line in Wayne County. | Pavement Improvement | 2009-07-01 | 2009-07-08 | 2009-10-30 | 2009-11-01 | 1411700 | 2.290
11988 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0052264 | This project will improve safety for motorists by resurfacing 1.50 miles of deteriorated pavement on United States Route 52 from the City of Pinnacle Rock to Lorton Lick Road in Mercer County. | Pavement Improvement | 2009-05-20 | 2009-06-11 | 2009-10-30 | 2009-08-31 | 612479 | 1.500
11989 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WAYNE | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0052265 | This project will improve safety for motorists by resurfacing 5.42 miles of United States Route 52 from West Virginia Route 75 to Whites Creek Road in Wayne County. | Pavement Improvement | 2009-08-17 | 2009-08-24 | 2009-10-30 | 2009-10-02 | 790000 | 6.420
11990 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0052270 | This project will extend the life of the Tunnel Overpass Bridge by cleaning and repainting the structure. The bridge is located on United States Route 52 at approximately milepoint 18.67 in Mercer Cou | Bridge Improvement | 2009-07-21 | 2009-08-24 | 2009-10-15 | 2009-09-22 | 286500 | 0.040
11991 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0052271 | This project will extend the life of the Madison Avenue Overpass Bridge by cleaning the structure and repainting it. The bridge is located at Milepoint 0.73 on West Virginia Route 52 in Cabell County. | Bridge Improvement | 2009-09-16 | 2009-11-14 | 2009-10-15 |  | 173200 | 0.010
11992 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0060252 | This project will improve safety for motorists by replacing the existing and failing piling currently restricting slippage of the embankment on United States Route 60 at milepoint 14.60 in Fayette Cou | Pavement Improvement | 2009-07-23 | 2009-08-25 | 2009-10-30 | 2009-10-04 | 155100 | 0.010
11993 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0061065 | This project will improve safety for motorists by resurfacing 1.24 miles of deteriorated pavement on West Virginia Route 61 from the City of Kincaid to Page Road in Fayette County. | Pavement Improvement | 2009-05-20 | 2009-07-07 | 2009-10-30 | 2009-09-03 | 357966 | 1.240
11994 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0061066 | This project will improve safety for motorists by resurfacing 0.95 miles of deteriorated pavement on West Virginia Route 61 (Ingram Branch Road) in Fayette County. | Pavement Improvement | 2009-06-23 | 2009-07-10 | 2009-10-30 | 2009-08-31 | 314912 | 0.950
11995 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 0062832 | This project will improve safety for motorists by replacing the Lower Mingo Bridge due to condition. The bridge is located on County Route 62 at approximately milepoint 0.08 in Randolph County. | Bridge Replacement | 2009-10-29 | 2010-05-06 | 2010-06-30 | 2010-07-22 | 524700 | 0.010
11996 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0067005 | This project will improve safety for motorists by resurfacing 4.07 miles of detiorated pavement on West Virginia Route 67 from the City of Wellsburg to Bethany Road in Brooke County. | Pavement Improvement | 2010-02-22 | 2010-04-09 | 2010-06-30 | 2010-06-08 | 789300 | 4.070
11997 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PRESTON |  | 01 | 0068135 | This project will improve safety for motorists by resurfacing the deck of the Laurel Run Bridges (West bound & East bound) with Latex Modified Concrete. The bridge is located on Interstate 68 at appro | Bridge Improvement | 2009-12-07 | 2010-04-05 | 2010-07-30 |  | 660600 | 0.010
11998 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0068137 | This project will improve safety for motorists by resurfacing 2.20 miles of deteriorated pavement on Interstate 68 from the City of Pierpont to the West end of the Cheat Lake Bridge in Monongalia Coun | Pavement Improvement | 2009-07-21 | 2009-07-23 | 2009-10-30 | 2009-10-06 | 1196116 | 2.200
11999 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0068139 | This project will extend the life of the Cheat Lake Bridge by cleaning and repainting the structure. The bridge is located on Interstate 68 at approximately milepoint 9.39 in Monongalia County. | Bridge Improvement | 2009-07-06 | 2010-03-26 | 2010-10-15 |  | 6155000 | 0.020
12000 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | OHIO | WHEELING (OH) | 01 | 0070158 | This project will improve safety for motorists by replacement of the existing bridge approach slabs, concrete repairs and drainage improvements on Interstate 70 beginning at the West Virginia/Ohio sta | Pavement Improvement | 2009-05-27 | 2009-05-27 | 2009-10-30 | 2009-11-01 | 3351655 | 0.050
12001 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MARSHALL | WHEELING (OH) | 01 | 0074051 | This project will improve safety for motorists by replacing the Shepherd Bridge due to condition. The bridge is located on County Route 74 at approximately milepoint 16.8 in Marshall County. | Bridge Replacement | 2009-05-28 | 2009-05-28 | 2010-05-28 |  | 1552180 | 0.050
12002 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MCDOWELL |  | 03 | 0080032 | This project will improve safety for motorists by resurfacing 2.00 miles of West Virginia Route 80 from the City of Beartown to Iaeger Road in McDowell County. | Pavement Improvement | 2009-05-01 | 2009-05-15 | 2009-10-30 | 2009-08-12 | 599234 | 2.000
12003 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0082013 | This project will improve safety for motorists by resurfacing 2.20 miles of WV 82 in Webster County between Birch River and Boggs Road. | Pavement Improvement | 2010-03-30 | 2010-07-03 | 2010-10-15 |  | 379000 | 2.200
12004 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 0094168 | This project will improve safety for motorists by resurfacing 5.52 miles of West Virginia Route 94 beginning at approximately milepoint 1.48 from the City of Hernshaw to the City of Marmet in Kanawha | Pavement Improvement | 2009-05-01 | 2009-05-11 | 2009-10-30 | 2009-08-31 | 2051683 | 5.520
12005 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WYOMING |  | 03 | 0097084 | This project will improve safety for motorists by resurfacing 2.0 miles of WV 97 on Rockhouse Mountain Road in Wyoming County. | Pavement Improvement | 2010-07-22 | 2010-08-02 | 2010-10-15 |  | 625500 | 2.000
12006 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0099099 | This project will improve safety for motorists by replacing the Sinking Creek Bridge due to condition. The bridge is located on County Route 9/9 in Greenbrier County. | Bridge Replacement | 2009-09-30 | 2009-12-01 | 2010-06-30 | 2010-01-18 | 241630 | 0.010
12007 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0109013 | This project will help eliminate congestion and help in the movement of motorists and commerce by the construction of 0.14 miles of four lane highway, an interstate ramp, a box culvert and constructio | New Construction | 2009-07-21 | 2009-08-12 | 2010-10-29 |  | 13378800 | 0.140
12008 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | LINCOLN |  | 03 | 0119339 | This project will extend the life of the Little Coal River Bridges (North & South) by cleaning and repainting the structure. The bridges are located on United States Route 119 at approximately milepoi | Bridge Improvement | 2009-09-16 | 2009-09-12 | 2009-10-15 | 2009-10-26 | 725200 | 0.039
12009 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MINGO |  | 03 | 0119341 | This project will improve safety for motorists by resurfacing 4.26 miles of US 119 between Miller Creek and Belo in Mingo County. | Pavement Improvement | 2010-04-13 |  | 2010-10-15 |  | 2693100 | 4.260
12010 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 0119342 | This project will improve safety for motorists by resurfacing 2.54 miles of deteriorated pavement on United States Route 119 beginning approximately at milepoint 39.13 in Kanawha County. | Pavement Improvement | 2009-09-30 | 2010-05-03 | 2010-05-28 |  | 617620 | 2.540
12011 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MINGO |  | 03 | 0119344 | This project will improve safety for motorists by resurfacing the deck of the West Belo Bridge with Latex Modified Concrete. The bridge is located on United States Route 119 at approximately milepoint | Bridge Improvement | 2009-07-15 | 2009-08-11 | 2009-10-30 | 2009-10-20 | 401400 | 0.050
12012 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0206002 | This project will improve safety for motorists by replacing the Greenbrier Avenue Bridge due to condition. The bridge is located on County Route 20/6 in Rainelle, Greenbrier County. | Bridge Replacement | 2009-07-09 | 2009-07-20 | 2009-11-06 | 2009-10-06 | 480894 | 0.040
12013 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 0219299 | This project will improve safety for motorists by replacing the Jones Run Bridge due to condition. The bridge is located on United States Route 219 at approximately milepoint 28.50 in Randolph County. | Bridge Replacement | 2009-07-15 | 2009-08-19 | 2010-09-10 | 2010-08-03 | 882830 | 0.010
12014 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONROE |  | 03 | 0219300 | This project will improve safety for motorists by resurfacing 2.34 miles of deteriorated pavement on United States Route 219 beginning at approximately milepoint 0.50 in Peterstown, Monroe County. | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-10-30 | 2009-08-21 | 729612 | 2.340
12015 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TUCKER |  | 01 | 0219302 | This project will improve safety for motorists by resurfacing 1.20 miles of deteriorated pavement on United States Route 219 from the City of Parsons to Mackeyville Road in Tucker County. | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2010-05-28 | 2009-12-09 | 785610 | 1.200
12016 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 0219303 | This project will improve safety for motorists by resurfacing 1.20 miles of deteriorated pavement on United States Route 219, construction of turning lanes and the improvement of drainage from the Cit | Pavement Widening | 2009-07-14 | 2009-07-30 | 2009-10-30 | 2009-11-20 | 1616480 | 1.200
12017 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0220182 | This project will improve safety for motorists by the installation of piling on United States Route 220 at approximately milepoint 13.30 between Smith Creek and Franklin Road for embankment stabilizat | Pavement Improvement | 2009-04-13 | 2009-05-21 | 2009-10-30 | 2010-01-20 | 972000 | 0.180
12018 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MINERAL |  | 01 | 0220183 | This project will improve safety for motorists by resurfacing 0.87 miles of deteriorated pavement on United States Route 220 beginning at approximately milepoint 13.96 in Mineral County. | Pavement Improvement | 2009-07-29 | 2009-08-18 | 2009-10-30 | 2009-12-21 | 927632 | 0.970
12019 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONROE |  | 03 | 0238046 | This project will improve safety for motorists by replacing the Indian Creek Bridge due to condition. The bridge is located at approximately milepoint 1.93 on County Route 23/8 in Monroe County. | Bridge Replacement | 2009-11-06 | 2009-11-16 | 2010-06-30 | 2010-07-12 | 677160 | 0.010
12020 | Awaiting NTP But Awarded | C250,C200,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WETZEL |  | 01 | 0250169 | This project will improve safety for motorists by resurfacing 4.47 miles of deteriorated pavement on United States Route 250 between Mannington, West Virginia and Hundred, West Virginia beginning at m | Pavement Improvement |  |  | 2010-10-29 |  | 1951200 | 4.470
12021 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MARSHALL | WHEELING (OH) | 01 | 0250183 | This project will improve safety for motorists by resurfacing the deck of the Bellaire Interchange Bridge with Latex Modified Concrete. The bridge is located on United States Route 250 at approximatel | Bridge Improvement | 2009-07-27 | 2009-10-06 | 2010-06-30 | 2009-12-04 | 556820 | 0.010
12022 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MARSHALL | WHEELING (OH) | 01 | 0250184 | This project will improve safety for motorists by resurfacing 5.44 miles of deteriorated pavement on United States Route 250 in the City of McMechen, Marshall County. | Pavement Improvement | 2009-05-06 | 2009-05-06 | 2009-10-30 | 2009-11-06 | 4459333 | 5.440
12023 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 0271001 | This project will improve safety for motorists by replacing the Eden's Fork Pony Truss Bridge due to condition. The bridge is located on County Route 27/1 at approximately milepoint 1.1 in Kanawha Cou | Bridge Replacement | 2009-08-14 | 2009-09-18 | 2010-04-06 |  | 997319 | 0.030
12024 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0385005 | This project will improve safety for motorists by replacing the Jug Neck Bridge due to condition. The bridge is located on County Route 38/5 at approximately milepoint 0.85 in Mercer County. | Bridge Replacement | 2009-07-24 | 2009-08-04 | 2009-11-06 | 2010-03-29 | 435090 | 0.010
12025 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0385006 | This project will improve safety for motorists by replacing the Blake Bridge due to condition. The bridge is located on County Route 38/5 at approximately milepoint 4.00 in Mercer County. | Bridge Replacement | 2009-08-07 | 2009-08-07 | 2009-11-06 | 2010-03-09 | 449370 | 0.010
12026 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WAYNE |  | 03 | 0411002 | This project will improve safety for motorists by replacing the Turkey Creek Pony Truss Bridge downstream due to condition. The bridge is located on County Route 41/1 at approximately milepoint 0.01 i | Bridge Replacement | 2009-12-11 | 2009-12-07 | 2010-08-31 |  | 916170 | 0.010
12027 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0460038 | This project will improve safety for motorists by resurfacing the deck of both the East bound and West bound Oakvale Bridges with Latex Modified Concrete. The bridges are located on United States Rou | Bridge Improvement | 2009-06-04 | 2009-06-18 | 2009-10-30 | 2009-09-13 | 890900 | 0.100
12028 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0460039 | This project will improve safety for motorists by resurfacing 1.67 miles of deteriorated pavement on United States Route 460 beginning at approximately milepoint 4.29 in Bluefield, Mercer County. | Pavement Improvement | 2009-04-13 | 2009-04-20 | 2009-07-27 | 2009-08-07 | 1407164 | 1.670
12029 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0641332 | This project will improve safety for motorists by resurfacing the deck of three Cabell County bridges, Cedar Crest Bridge and both County Route 26 overpass bridges (East & West), with Latex Modified C | Bridge Improvement | 2009-07-15 | 2010-03-29 | 2010-05-28 |  | 766900 | 5.140
12030 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0641334 | This project will improve safety for motorists by resurfacing 1.59 miles of deteriorated pavement on Interstate 64 from the City of Milton to County Route 60/19 in Cabell County. | Pavement Improvement | 2009-06-16 | 2009-06-24 | 2009-10-30 | 2009-09-11 | 997100 | 1.560
12031 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PUTNAM | HUNTINGTON-ASHLAND (KY-OH) | 02 | 0641335 | This project will improve safety for motorists by resurfacing 4.67 miles of deteriorated pavement on Interstate 64 from the Hurricane Interchange to the Winfield Interchange in Putnam County. | Pavement Improvement | 2009-10-02 | 2009-10-12 | 2010-06-15 |  | 8292800 | 4.670
12032 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0644170 | This project will extend the life of the Mountain Avenue Bridges (North & South) by cleaning the structure and repainting it. The bridges are located at approximately milepoint 179.36 of Interstate 64 | Bridge Improvement | 2009-08-26 | 2009-09-16 | 2009-10-30 | 2009-11-12 | 603606 | 0.179
12033 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0644171 | This project will improve safety for motorists by resurfacing 1.50 miles of deteriorated pavement on Interstate 64 at approximately milepoint 174.61 in Greenbrier County. | Pavement Improvement | 2009-05-15 | 2010-04-05 | 2009-10-30 | 2010-05-20 | 2629450 | 1.500
12034 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0644172 | This project will improve safety for motorists by resurfacing 1.00 miles of deteriorated pavement on Interstate 64 at approximately milepoint 160.00 in Greenbrier County. | Pavement Improvement | 2009-05-15 | 2009-05-27 | 2009-10-30 | 2009-08-28 | 1425900 | 1.000
12035 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0705011 | This project will improve safety for motorists by resurfacing 1.00 miles of deteriorated pavement on West Virginia Route 705 beginning approximately at milepoint 2.55 in Morgantown, Monongalia County. | Pavement Improvement | 2009-09-09 | 2009-09-14 | 2010-05-28 | 2009-10-22 | 1759900 | 1.000
12036 | Awaiting NTP & Not Awarded | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0771061 | This project will improve safety for motorists by resurfacing 2.03 miles of deteriorated pavement on Interstate 77 from the City of Ingleside to Princeton Road in Mercer County. | Pavement Improvement |  |  |  |  | 3316632 | 2.003
12037 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0772083 | This project will improve safety for motorists by the installation of movable barriers at various locations on the West Virginia Turnpike to allow for the opening of lanes, movement of traffic, etc. d | Safety/Traffic Management | 2010-01-29 | 2010-02-01 | 2010-05-14 | 2010-07-30 | 911500 | 6.000
12038 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WOOD | PARKERSBURG (OH) | 01 | 0773399 | This project will improve safety for motorists by resurfacing the decks of four bridges, the County Route 25 Overpass Bridges (North and South), Wolf Run Overpass and the Buck Run Overpass, with Latex | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2010-05-28 |  | 1168400 | 0.010
12039 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WOOD | PARKERSBURG (OH) | 01 | 0773402 | This project will improve safety for motorists by resurfacing the decks of five bridges, the Interstate 77/United States Route 50 Interchange Bridge, Worthington Creek Bridge, West Virginia Route 31 O | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2010-06-18 | 2010-08-11 | 1232000 | 9.450
12040 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | LEWIS |  | 02 | 0792156 | This project will improve safety for motorists by resurfacing two bridges, Stone Coal Creek Bridge and the County Route 14 Overpass Bridge, on Interstate 79 in Lewis County. | Bridge Improvement | 2009-08-05 | 2010-03-04 | 2009-10-30 |  | 1179299 | 0.109
12041 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BRAXTON |  | 02 | 0792158 | This project will improve safety for motorists by resurfacing the deck of three bridges, the Little Kanawha River Bridge and the Oil Creek Bridges (North & South) on Interstate 79 in Braxton County wi | Bridge Improvement | 2009-08-05 | 2010-03-09 | 2010-01-28 |  | 2206800 | 0.439
12042 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | ROANE |  | 02 | 0792160 | This project will improve safety for motorists by resurfacing the deck of the Wallback Interchange Bridge with Latex Modified Concrete. The bridge is located on Interstate 79 at approximately milepoin | Bridge Improvement | 2010-03-10 | 2010-04-28 | 2010-06-30 |  | 581900 | 0.059
12043 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BRAXTON |  | 02 | 0792161 | This project will extend the life of the Kenton Meadows Senior Bridges (North & South) by cleaning the structures and repainting them. The bridges are located on Interstate 79 at approximately milepoi | Bridge Improvement | 2010-04-15 | 2010-04-22 | 2010-07-30 |  | 1270000 | 0.280
12044 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | ROANE |  | 02 | 0792162 | This project will extend the life of the Amma/Big Sandy Bridges (North & South) by cleaning and painting the structures. The bridges are located on Interstate 79 at approximately milepoint 25.79 in Ro | Bridge Improvement | 2009-06-29 | 2009-07-22 | 2009-09-18 | 2009-09-28 | 906542 | 0.180
12045 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BRAXTON |  | 02 | 0792164 | This project will improve safety for motorists by resurfacing 6.99 iles of detiorated pavement, installation of raised pavement markers, guardrail repair/replacement and shoulder pavement/reconstuctio | Pavement Improvement | 2009-07-13 | 2009-07-27 | 2009-10-30 | 2009-09-04 | 2940001 | 6.990
12046 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BRAXTON |  | 02 | 0792167 | This project will extend the life of the Saltlick Creek Bridges (North & South) by cleaning the structures and repainting them. The bridges are located on Interstate 79 at approximately milepoint 78.1 | Bridge Improvement | 2009-09-16 | 2009-09-18 | 2010-10-15 | 2009-11-04 | 638466 | 0.119
12047 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | ROANE |  | 02 | 0792168 | This project will improve Safety for motorists by resurfacing 4.49 miles of deteriorated pavement on Interstate 79 between the City of Amma and Wallback Road in Roane County. | Pavement Improvement | 2009-05-11 | 2009-06-08 | 2009-10-30 | 2009-09-02 | 3009576 | 4.490
12048 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0793222 | This project will improve safety for motorists by resurfacing the deck of the Westover Bridge with Latex Modified Concrete. The bridge is located on Interstate 79 at approximately milepoint 152.53 in | Bridge Improvement | 2009-10-13 | 2010-04-05 | 2010-06-30 |  | 992400 | 0.480
12049 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MARION |  | 01 | 0793223 | This project will improve safety for motorists by resurfacing 2.19 miles of deteriorated pavement on Interstate 79 beginning at approximately milepoint 136.68 in Fairmont, Marion County. | Pavement Improvement | 2009-04-16 | 2009-04-17 | 2009-10-30 | 2009-07-22 | 1245675 | 2.190
12050 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BERKELEY | HAGERSTOWN | 02 | 0811104 | This project will improve safety for motorists by resurfacing 4.65 miles of deteriorated pavement on Interstate 81 from Falling Waters to the Maryland/West Virginia State line in Berkeley County. | Pavement Improvement | 2009-07-01 | 2009-07-12 | 2009-10-30 | 2009-10-06 | 2167300 | 4.650
12051 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BERKELEY | HAGERSTOWN | 02 | 0811105 | This project will improve safety for motorists by resurfacing 4.27 miles of deteriorated pavement on Interstate 81 from the Virginia/West Virginia State Line to Inwood Road, in Berkely County. | Pavement Improvement | 2009-07-01 | 2009-08-11 | 2009-10-30 | 2009-10-30 | 1748260 | 4.270
12052 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | LEWIS |  | 02 | 1191007 | This project will improve safety for motorists by replacing the Sleeths Run Truss Bridge due to condition. The bridge is located on US Route 119 at approximately milepoint 0.09 in Lewis County. | Bridge Replacement | 2009-07-17 | 2009-07-30 | 2010-08-30 |  | 1279500 | 0.020
12053 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 1601001 | This project will improve safety for motorists by replacing the Michigan Avenue Bridge due to condition. The bridge is located at approximately milepoint 0.01 of County Route 160/17 in Fayette County. | Bridge Replacement | 2009-08-21 | 2009-08-21 | 2010-04-06 |  | 660010 | 0.010
12054 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MCDOWELL |  | 03 | 1659001 | This project will improve safety for motorists by replacing the South Roselawn Street Bridge on County Route 16/59 at approximately milepoint 0.01 in McDowell County. | Bridge Replacement | 2009-11-02 | 2010-03-01 | 2010-05-28 | 2010-05-28 | 443120 | 0.001
12055 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 1919002 | This project will improve safety for motorists by replacing the Peters Creek Bridge due to condition. The bridge is located on County Route 19/19 at approximately milepoint 0.03 in Nicholas County. | Bridge Replacement | 2009-08-27 | 2010-03-15 | 2010-11-30 | 2010-06-22 | 457040 | 0.001
12056 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MINERAL |  | 01 | 2009169 | Continuation of rail trail development. Project elements include developing trail from Knobley Tunnel across the Potomac River Bridge to link to the C&O National Park Towpath hiking trail in Mineral C | Transportation Enhancements |  |  | 2010-10-29 |  | 167100 | 0.000
12057 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 2009170 | Construction/reconstruction of sidewalks, curbs and gutters along Main Street (West Virginia Route 100) from Dent's Run Bridge to Everly Street in Granville, Monongalia County. Project elements inclu | Transportation Enhancements | 2010-06-02 | 2010-07-06 | 2010-09-30 |  | 617900 | 0.000
12058 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PLEASANTS |  | 01 | 2009172 | Reconstruction of sidewalks and curbing, installation of lighting , and minor drainage along Washington Street from WV 2 to Second Street in St. Marys, Pleasants County. | Transportation Enhancements | 2010-06-22 |  | 2010-09-30 |  | 152900 | 0.000
12059 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 2009174 | Sidewalk construction, installation of decorative and historic brick pavers and curbing at various intersections along Charles Street, 22nd and 23rd Streets at their intersections with Pleasant Avenue | Transportation Enhancements | 2010-06-17 | 2010-07-14 | 2010-09-30 |  | 135300 | 0.000
12060 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HARRISON |  | 01 | 2009175 | Reconstruction of sidewalks on Traders Avenue, Library Lane and South 2nd Street; installation of lighting, pedestrian amenities, landscaping and minor drainage in Clarksburg, Harrison County. | Transportation Enhancements | 2010-07-09 | 2010-08-11 | 2010-09-30 |  | 425721 | 0.000
12061 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | JEFFERSON | HAGERSTOWN | 02 | 2009177 | Construction of sidewalks, curbs and gutters and minor drainage from Harpers Ferry Middle School to the Bolivar-Harpers Ferry Public Library in Jefferson County. | Transportation Enhancements |  |  | 2010-09-30 |  | 139000 | 0.000
12062 | Awaiting NTP & Not Awarded | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 2009178 | Construction of sidewalks, curbs and gutters, crosswalks, lighting, landscaping and utility relocation as well as other pedestrian amenities from Beatrice Street to Hunt Avenue in Charleston, Kanawha | Transportation Enhancements |  |  |  |  | 200200
12063 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 2009179 | Improvement of pedestrian and community access for two sites on the Davis & Elkins College campus in Randolph County including construction of sidewalks, curbing, minor drainage, new signage, seating, | Transportation Enhancements |  |  | 2010-10-29 |  | 220000 | 0.000
12064 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 2009180 | Construction of sidewalks, curb cuts and crosswalks beginning at the intersection of Martins Branch Road (CO 622) proceeding north on the west dise of CO 21 to Tinny Lane (CO 622/38) in Sissonville, K | Transportation Enhancements | 2010-05-21 | 2010-06-04 | 2010-09-30 |  | 171100 | 0.000
12065 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | ROANE |  | 02 | 2009182 | Construction of sidewalks, crosswalks, curbing, lighting and minor drainage along Main Street from the intersection of US 33/US 119 to Court Street; Market Street from Court Street and along US 33 wes | Transportation Enhancements | 2010-06-22 | 2010-08-18 | 2010-09-30 |  | 84200 | 0.000
12066 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 2009184 | Reconstruction of sidewalks, curbs and gutters, and minor drainage along Mercer Street between Douglas Street and Main Street and on East Main Street between Ingleside Road and North Walker Street in | Transportation Enhancements | 2010-08-02 | 2010-08-02 | 2010-09-30 |  | 252700 | 0.000
12067 | Awaiting NTP & Not Awarded | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 2009185 | Design and construction of rail trail segments beginning near the Holiday Inn Hotel and extending north past Allman Street to Summerlee Road; and beginning at Jones Avenue and extending south toward C | Transportation Enhancements |  |  |  |  | 429800 | 0.000
12068 | Underway | C220,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 2009186 | Construction of sidewalks, curbs and gutters, minor drainage, signage, lighting, pedestrian amenities, and landscaping along US 219 and Frankford Road in Roncerverte, Greenbrier County. | Transportation Enhancements | 2010-05-26 |  | 2010-09-30 |  | 391961 | 0.000
12069 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 2009187 | Reconstruction of sidewalks, curbs and gutters, minor drainage, and pedestrian lighting along both sides of Main Street in Mount Hope, Fayette County. | Transportation Enhancements | 2010-05-26 | 2010-08-04 | 2010-09-30 |  | 209800 | 0.000
12070 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 03 | 2009189 | Construction of pedestrian corridor between 10th Street and 11th Street connecting Huntington's Visitor's Center to Pullman Square in Cabell County. Project includes sidewalks, curbs and gutters, min | Transportation Enhancements |  |  | 2010-09-30 |  | 204751 | 0.000
12071 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 2009190 | construction of sidewalks, curb and gutters, lighting, signage, landscaping, pedestrian amenities, and minor drainage along Chestnut, Locust, Sewell, First, Second and Third Streets in Rainelle, Green | Transportation Enhancements | 2010-05-26 | 2010-07-19 | 2010-09-30 |  | 145500 | 0.000
12072 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WEBSTER |  | 03 | 2009192 | Construction of ADA compliant walking trail and minor drainage improvements to connect the facilities on the island to the facilities at Bakers Island in Webster Springs, Webster County. | Transportation Enhancements | 2010-06-03 | 2010-08-16 | 2010-09-30 |  | 72446 | 0.000
12073 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 2009194 | Installation of fencing, railing and new caging system. Reconstruction of ADA compliant pedestrian approaches, landscaping, pedestrian amenities, lighting,signage, minor bridge repairs and cleaning a | Bridge Improvement | 2010-07-22 |  | 2010-09-30 |  | 431973 | 0.000
12074 | Underway | C200,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | STATEWIDE |  |  | 2009230 | This project will improve safety for motorists by the installation of Dynamic Message Signs and Closed Circuit Television connections along the West Virginia Turnpike for messaging and monitoring by t | Safety/Traffic Management | 2010-07-23 |  | 2010-12-10 |  | 5323100 | 0.000
12075 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | OHIO | WHEELING (OH) | 01 | 2009232 | This project will improve safety for motorists by the installation or replacement of guardrail in various locations throughout WVDOH District 6 area. | Safety/Traffic Management | 2010-06-01 | 2010-07-13 | 2010-11-15 | 2010-07-27 | 126500 | 0.000
12076 | Awaiting NTP & Not Awarded | C490 | Highway Infrastructure Investment Grant | WEST VIRGINIA | STATEWIDE |  |  | 2009234 | This project will provide highway construction industry skills training, tools/equipment, employment counseling and supplemental services, (i.e., child care, remedial education, transportation) to wom | Other |  |  |  |  | 198353 | 0.000
12077 | Awaiting NTP & Not Awarded | C490 | Highway Infrastructure Investment Grant | WEST VIRGINIA | STATEWIDE |  |  | 2009236 | This project will provide an employment-based skilled trade training program at three sites in West Virgina to increase the number of women entering and remaining in the highway construction workforce | Other |  |  |  |  | 292000 | 0.000
12078 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2009242 | This is a bridge replacement project in Portage County on a town road, County Highwy P - Cemetary Road. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-12-11 | 556000 | 0.076
12079 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009244 | This is a bridge replacement project in Wood County on County Highway K, Branch of Mill Creek Crossing. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-11-09 | 277000 | 0.057
12080 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | PRICE |  | 07 | 2009245 | This is a bridge replacement project in Price County on a town road, Holmes Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-28 | 297338.95 | 0.086
12081 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | PRICE |  | 07 | 2009246 | This is a bridge replacement project in Price County on a town road, Douglas Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-28 | 193456.06 | 0.062
12082 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009254 | This is a bridge replacement project in Taylor County on County Highway D, Mondeaux River Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-20 | 512500 | 0.000
12083 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | JEFFERSON |  | 05 | 2009366 | This is a reconstruction project in Jefferson County on State Highway 59, Village of Palmyra, Maple Street. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-30 | 1343575.52 | 0.850
12084 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | JEFFERSON |  | Multiple | 2009367 | This is a restoration and rehabilitation project in Jefferson County on State Highway 59, Whitewater - Palmyra Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-30 | 2002046.04 | 67.050
12085 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009368 | This is a bridge rehabilitation project in Dane County on US Highway 151, Sun Prairie Bypass. | Bridge Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-21 | 524210.55 | 0.020
12086 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 02 | 2009369 | This is a reconstruction project in Rock County on State Highway 11, Footville - Janesville Bypass. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-03 | 3132000 | 22.400
12087 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | VERNON |  | 03 | 2009370 | This is a restoration and rehabilitation project in Vernon County on State Highway 82, LaFarge and Otter Creek Briges. | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-10-01 | 2009-11-18 | 832000 | 0.231
12088 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAUK |  | 02 | 2009371 | This is a bridge rehabilitation project in Sauk County on US Highway 12, Lake Delton, Dell Creek Bridge and approaches. | Bridge Improvement | 2009-05-15 | 2009-05-15 | 2010-06-01 |  | 3038220.19 | 0.133
12089 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009372 | This is a reconstruction project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2010-08-01 |  | 4626581.72 | 0.610
12090 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009373 | This is a reconstruction project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2010-08-01 |  | 6124945.95 | 0.610
12091 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009374 | This is a reconstruction with additional lanes project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Widening | 2009-03-30 | 2009-03-30 | 2010-08-01 |  | 10839551.47 | 0.610
12092 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009375 | This is a fencing project in Racine County on Interstate 94. | Other | 2009-03-30 | 2009-03-30 | 2010-08-01 |  | 95401.9 | 0.610
12093 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009376 | This is a reconstruction with additional lanes project in Kenosha County on Interstate 94, North-South Freeway, County Highway C Interchange, mainline and ramps. | Pavement Widening | 2009-03-30 | 2009-03-30 | 2010-12-01 |  | 27023140.6 | 1.080
12094 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009377 | This is a reconstruction with additional lanes project in Kenosha County on Interstatet 94, North - South Freeway, Illinois State Line to County Highway C, mainline. | Pavement Widening | 2009-03-30 | 2009-03-30 | 2010-12-01 |  | 34193016.87 | 16.500
12095 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009378 | This is a bridge replacement with added lanes project in Kenosha County on Interstate 94, North South Freeway, County Highway C to State Highway 50, mainline. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2010-12-01 |  | 5007480.82 | 0.660
12096 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUPACA |  | 08 | 2009379 | This is a project in Waupaca County on State Highway 49, City of Waupaca. | Safety/Traffic Management | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-22 | 164374.87 | 0.095
12097 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | LINCOLN |  | 07 | 2009380 | This is a bridge rehabilitation project in Lincoln County on US Highway 51, Merrill - Tomahawk. | Bridge Improvement | 2009-03-30 | 2009-03-30 | 2009-11-01 | 2010-07-02 | 1182735.39 | 0.800
12098 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009381 | This is a resurfacing project in Wood County on State Highway 13, Pittsville - Marshfield. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-12-30 | 2009-10-13 | 818600.13 | 7.614
12099 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009382 | This is a resurfacing project in Marathon County on State Highway 153, Mosinee, Crooked Lake Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-06-01 | 2009-07-09 | 776804.13 | 43.596
12100 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | LANGLADE |  | 08 | 2009383 | This is a restoration and rehabilitation project in Langlade County on State Highway 52, Lily, Forest County Line. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-09-01 | 966000 | 22.160
12101 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ST CROIX |  | 03 | 2009384 | This is a resurfacing project in St. Croix County on State Highway 64, New Richmond, Connorsville Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-09 | 3907157.55 | 50.470
12102 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ST CROIX |  | 03 | 2009385 | This is a project in St. Croix County on State Highway 64, New Richmond, Connorsville Road. | Safety/Traffic Management | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-09 | 505495.91 | 0.180
12103 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2009386 | This is a resurfacing project in Polk County on US Highway 8, St. Croix Falls - Turtle Lake. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-11-06 | 3225447.52 | 74.160
12104 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BURNETT |  | 07 | 2009387 | This is a resurfacing project in Burnett County on State Highway 70, Siren - Spooner. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-22 | 3196143.72 | 132.550
12105 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DUNN |  | 03 | 2009388 | This is a restoration and rehabilitation project in Dunn County on State Highway 25, Menomonie - Wheeler Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-04 | 2165000 | 28.900
12106 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DUNN |  | 03 | 2009389 | This is a resurfacing project in Dunn County on State Highway 64, New Richmond - Bloomer. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-11 | 1718368.73 | 38.880
12107 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009390 | This is a reconstruction project in Dane County on County Highway B, Village of Rockdale. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2010-05-01 | 2010-07-28 | 972530.98 | 0.800
12108 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | LAFAYETTE |  | 03 | 2009391 | This is a bridge replacement project in Lafayette County on County Highway H, Fever River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-12-11 | 643416.39 | 0.145
12109 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2009392 | This is a reconstruction project in Crawford County on a town road, Rush Creek Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-09-24 | 413610.67 | 0.100
12110 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | SAUK |  | 03 | 2009393 | This is a bridge replacement project in Sauk County on County Highway G, Baraboo River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-10-02 | 870000 | 0.280
12111 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 01 | 2009394 | This is a bridge rehabilitation with added lanes project in Waukesha County on local streets, Valentine Road, Bridge over Oconomowoc River. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-11-20 | 228238.14 | 0.000
12112 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009395 | This is a bridge replacement project in Washington County on County Highway W, Bridge over Rock River. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-22 | 442426.06 | 0.000
12113 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009396 | This is a reconstruction project in Manitowoc County on a town road, Newton Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-28 | 272330.66 | 0.660
12114 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009397 | This is a reconstruction project in Manitowoc County on a town road, Valley Drive Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-28 | 199108.49 | 0.000
12115 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009398 | This is a reconstruction project in Manitowoc County on a town road, South Cleveland Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-11-03 | 221783.43 | 0.000
12116 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009399 | This is a reconstruction project in Manitowoc County on a town road, County line Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-11-03 | 195139.2 | 0.000
12117 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009400 | This is a bridge replacement project in Fond du Lac County on a town road, Youth Camp Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-22 | 410865.84 | 0.000
12118 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | IRON |  | 07 | 2009401 | This is a bridge replacement project in Iron County on local streets, Montreal River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2010-08-11 | 666325.92 | 0.043
12119 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2009402 | This is a bridge replacement project in Trempealeau County on County Highway D, Bruce Valley Creek Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-07-01 | 2009-08-21 | 429733.64 | 0.071
12120 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2009403 | This is a bridge replacement project in Barron County on a town road, Yellow River Bridge. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-09-10 | 504690.05 | 0.280
12121 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2009404 | This is a bridge replacement project in Douglas County on local streets, Town of Cloverland, McNeil's Landing Road, Brule River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-02 | 387000.5 | 0.000
12122 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2009405 | This is a bridge replacement project in Douglas County on a town road, Town of Oakland, Rice Farm Road, Little Amnicon River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-27 | 360847.17 | 0.000
12123 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009406 | This is a bridge replacement project in Taylor County on local streets, City of Medford, Black River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-08-27 | 657757.63 | 0.000
12124 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MONROE |  | 03 | 2009407 | This is a reconstruction project in Monroe County on a town road, Kettle Road, Town of Wilton. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-07-01 | 2009-07-27 | 183311.19 | 0.038
12125 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | LINCOLN |  | 07 | 2009408 | This is a bridge replacement project in Lincoln County on County Highway H, Little Pine Creek Bridge. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-07-22 | 249000 | 0.081
12126 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009409 | This is a resurfacing project in Taylor County on State Highway 64, Medford - Goodrich. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-24 | 2030000 | 200.102
12127 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUPACA |  | 08 | 2009411 | This is a resurfacing project in Waupaca County on US Highway 45, Winchester - New London. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-22 | 564582.05 | 3.515
12128 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | EAU CLAIRE |  | 03 | 2009412 | This is a resurfacing project in Eau Claire County on US Highway 12, Augusta - Fairchild Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-07-01 | 2009-07-21 | 1027265.12 | 92.600
12129 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009486 | This is a bridge rehabilitation project in Dane County on Interstate 90, Madison - Janesville Road, Drotning Road bridges. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-09-01 | 192000 | 0.030
12130 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009487 | This is a bridge rehabilitation project in Dane County on Interstate 39, Madsion to Janesville Road, County Highway W bridges. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-09-01 | 182316.4 | 0.030
12131 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009488 | This is a bridge rehabilitation project in Dane County on Interstate 39, Madison - Janesville Road, County Highway B bridges. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-09-01 | 175866.4 | 0.030
12132 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 01 | 2009489 | This is a bridge rehabilitation project in Rock County on County Highway A, Blackhawk Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-20 | 166702.97 | 0.057
12133 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009490 | This is a bridge rehabilitation project in Dane County on County Highway N, Edgerton - Stoughton, Yahara River Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2010-04-21 | 685953.16 | 0.100
12134 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RICHLAND |  | 03 | 2009491 | This is a bridge replacement project in Richland County on County Highway I, Gault Hollow Creek Bridge. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-11-01 |  | 416955.73 | 0.150
12135 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | SAUK |  | 03 | 2009492 | This is a bridge rehabilitation project in Sauk County on County Highway PF, Seeley Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-14 | 510000 | 0.070
12136 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | IOWA |  | 03 | 2009493 | This is a bridge rehabilitation project in Iowa County on a town road, River Road Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-11-25 | 425491.06 | 0.110
12137 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2009494 | This is a reconstruction project in Grant County on County Highway C, US Highway 18 - Millville Road, Warner Creek Brige and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-11-23 | 515000 | 0.090
12138 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | LA CROSSE | LA CROSSE (MN) | 03 | 2009495 | This is a reconstruction project in La Crosse County on local streets, Oak Avenue, Onalaska and LaCrosse. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-12-02 | 1029781.66 | 2.640
12139 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009496 | This is a pedestrian and bicycle path project in Dane County, Starkweather Creek Bike and Pedestrian Path. | Transportation Enhancements | 2009-04-17 | 2009-04-17 | 2010-05-01 |  | 2300581.88 | 0.000
12140 | Underway | C250 | Highway Infrastructure Investment Grant | WISCONSIN | DODGE |  | 06 | 2009497 | This is a reconstruction project in Dodge County on County Highway G, Beaver Dam - Randolph. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-08-01 | 2009-09-30 | 950000 | 14.959
12141 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | LA CROSSE | LA CROSSE (MN) | 03 | 2009498 | This is a resurfacing project in La Crosse County on State Highway 16, La Crosse, West Salem and Monegan O'Head. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-09-10 | 690153.14 | 0.080
12142 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009499 | This is a restoration and rehabilitation project in Walworth County on US Highway 12, State Highway 67 to State Highway 50. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-11-01 | 2009-11-06 | 3185000 | 75.670
12143 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009500 | This is a bridge rehabilitation project in Walworth County on Interstate 43, Rock Freeway. | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2009-11-01 | 2009-11-15 | 3305066 | 26.900
12144 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2009501 | This is a reconstruction project in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2010-09-01 |  | 9469411.63 | 79.500
12145 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2009502 | This is a new roadway construction project of 15.9 milesin Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 2009-04-17 | 2009-04-17 | 2010-07-01 | 2010-08-02 | 4600000 | 15.900
12146 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2009503 | This is a new roadway construction project of 2.07 miles in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 2009-04-17 | 2009-04-17 | 2010-08-01 |  | 3582652.15 | 4.140
12147 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009504 | This is a resurfacing project in Manitowoc County on State Highway 147, Two Rivers - Mishicot. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-20 | 1334233.69 | 32.220
12148 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009505 | This is a resurfacing project in Manitowoc County on State Highway 147, Mishicot, and Interstate 43. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-20 | 1394027.81 | 57.280
12149 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DOOR |  | 08 | 2009506 | This is a reconstruction project in Door County on local streets, Michigan Street. | Pavement Improvement | 2009-04-17 | 2009-08-13 | 2009-10-01 | 2009-10-28 | 852000 | 1.150
12150 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009507 | This is a reconstruction project in Fond du Lac County on a town road, Lake Maria Road Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-21 | 219529.54 | 0.030
12151 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009508 | This is a bridge replacement project in Fond du Lac County on a town road, Oak Grove Road Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-21 | 280635.24 | 0.000
12152 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009509 | This is a reconstruction project in Marathon County on Interstate 39, Stevens Point - Wausau. | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2010-07-01 |  | 8694548.76 | 28.400
12153 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON | WAUSAU | 07 | 2009510 | This is a reconstruction project in Marathon County on Interstate 39, Stevens Point - Wausau. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2010-07-01 |  | 2990260.9 | 6.880
12154 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009511 | This is a resurfacing project in Wood County on State Highway 73, Pittsville - Neilsville. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-08-01 | 2009-09-08 | 1414972.87 | 61.146
12155 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | VILAS |  | 08 | 2009512 | This is a resurfacing project in Vilas County on US Highway 45, Eagle River - Land-o-Lakes. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2010-07-07 | 1868628.08 | 47.180
12156 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009513 | This is a bridge replacement project in Marathon County on County Highway F, Stoney Creek Crossing. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-08-01 | 2009-08-20 | 417406.51 | 0.100
12157 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ASHLAND |  | 07 | 2009514 | This is a restoration and rehabilitation project in Ashland County on US Highway 2, Odanah - Saxon, Government Road. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-08-01 | 2009-08-18 | 3170000 | 34.880
12158 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2009515 | This is a bridge rehabilitation project in Polk County on US Highway 8, St. Croix Falls - Turtle Lake. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-29 | 105650.36 | 0.010
12159 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2009516 | This is a bridge rehabilitation project in Trempealeau County on County Highway G, Pine Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-11-01 | 2009-11-20 | 350000 | 0.076
12160 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | JACKSON |  | 03 | 2009517 | This is a reconstruction project in Jackson County on County Highway A, Hixton - Black River Falls. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-29 | 1825000 | 10.150
12161 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2009518 | This is a resurfacing project in Sawyer County on State Highway 77, Ghost Lake - Clam Lake. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-29 | 2815000 | 79.360
12162 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009519 | This is a bridge replacement project in Taylor County on County Highway M, Branch River Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-11-01 | 2009-11-12 | 257871.04 | 0.000
12163 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009520 | This is a reconstruction project in Walworth County on County Highway C, Stateline Road - Pleasant Street. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-12-08 | 992903.18 | 0.490
12164 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | VILAS |  | 08 | 2009521 | This is a resurfacing project in Vilas County on US Highway 45, Eagle River - Land-o-Lakes. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2010-07-07 | 2982710.31 | 58.240
12165 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009523 | This is a reconstruction with additional lanes project in Kenosha County on Interstate 94, North-South Freeway, County Highway C Interchange fencing. | Pavement Widening | 2009-05-14 | 2009-05-14 | 2010-12-01 |  | 155588.13 | 29.150
12166 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SHEBOYGAN |  | 06 | 2009524 | This is a bridge rehabilitation project in Sheboygan County on Interstate 43, Milwaukee, Green Bay Road. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2010-07-01 |  | 2329511.86 | 194.260
12167 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SHEBOYGAN | SHEBOYGAN | 06 | 2009525 | This is a resurfacing project in Sheboygan County on Interstate 43, Port Washington - Manitowoc. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2010-07-01 |  | 14319091.08 | 83.120
12168 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009530 | This is a bridge replacement project in Dane County on Interstate 94, Madison - Milwaukee Road. | Pavement Widening | 2009-05-14 | 2009-05-14 | 2011-12-01 |  | 46925107.6 | 15.600
12169 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009531 | This is a resurfacing project in Washington County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-11-12 | 670965.87 | 1.996
12170 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2009532 | This is a reconstruction with additional lanes project in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 2009-05-14 | 2009-05-14 | 2010-10-01 |  | 17122027.12 | 1.610
12171 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN |  | 08 | 2009533 | This is a bridge replacement project in Brown County on US Highway 41, Green Bay - Suamico. | Bridge Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-06 | 343409.42 | 0.040
12172 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | OCONTO |  | 08 | 2009534 | This is a bridge rehabilitation project in Oconto County on US Highway 41, Suamico - Abrams. | Bridge Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-06 | 142873.75 | 0.020
12173 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009535 | This is a restoration and rehabilitation project in Manitowoc County on Interstate 43, Denmark, Manitowoc River, CN Railroad. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-07-01 | 2011-07-16 | 8410801 | 51.420
12174 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN |  | 08 | 2009536 | This is a resurfacing project in Brown County on Interstate 43, US Highway 12 - County Highway M. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-07-01 | 2010-07-16 | 8146435.56 | 46.500
12175 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009537 | This is a resurfacing project in Fond du Lac County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-11-12 | 2181230.34 | 95.760
12176 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009538 | This is a resurfacing project in Fond du Lac County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-11-12 | 2036702.25 | 64.480
12177 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | GREEN LAKE |  | 06 | 2009539 | This is a bridge rehabilitation project in Green Lake County on County Highway A, Grand River Crossing. | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-12-03 | 370750.73 | 0.057
12178 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON | WAUSAU | 07 | 2009540 | This is a reconstruction project in Marathon County on County Highway NN, Creek Road - Thornapple Road. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-01 | 2009-11-09 | 1730000 | 61.930
12179 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | FOREST |  | 08 | 2009541 | This is a restoration and rehabilitation project in Forest County on County Highway W, County Highway Q - US Highway 8. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-01 | 2009-10-01 | 990000 | 43.560
12180 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MENOMINEE |  | 08 | 2009542 | This is a resurfacing project in Mennominee County on County Highway M, Strawberry Lane. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-10-16 | 3905000 | 35.140
12181 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | CLARK |  | 03 | 2009543 | This is a bridge replacement project in Clark County on a town road, Town of Sherwood Ballard Road, Hay Creek Bridge and approaches. | Bridge Replacement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-10-22 | 207542.32 | 0.000
12182 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON | MILWAUKEE | 05 | 2009592 | This is a reconstruction with additional lanes project in Washington County on County Highway Q, County Line Road, Pilgrim Road. | Pavement Widening | 2009-05-18 | 2009-05-18 | 2009-10-01 |  | 3454459.37 | 10.530
12183 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009594 | This is a bridge rehabilitation project in Milwaukee County on local streets, River Road. | Bridge Improvement | 2009-05-18 | 2009-05-18 | 2010-07-01 | 2010-05-22 | 317315 | 0.000
12184 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE |  | 08 | 2009609 | This is a bridge replacement project in Outagamie County on a town road, Weyers Road Bridge and approaches. | Bridge Replacement | 2009-05-18 | 2009-05-18 | 2009-10-01 |  | 677761 | 0.000
12185 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GREEN LAKE |  | 06 | 2009610 | This is a resurfacing project in Green Lake County on County Highway A, Markesan - Green Lake. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-09-01 | 2009-09-08 | 1150000 | 15.600
12186 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009611 | This is a bridge replacement project in Marathon County on a town road, Huckleberry Road, Fenwood Creek Crossing. | Bridge Replacement | 2009-05-18 | 2009-05-18 | 2009-11-01 | 2009-12-07 | 228000 | 0.038
12187 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2009612 | This is a resurfacing project in Portage County on County Highway W, Kellner - Bankroft Road. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-20 | 2245000 | 153.400
12188 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009613 | This is a resurfacing project in Wood County on County Highway A, Pittsville - Marshfield. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-09-01 | 2009-11-10 | 3110000 | 211.140
12189 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009614 | This is a reconstruction project in Wood County on a town road, Lincoln Avenue, City of Marshfield. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2010-06-01 |  | 1500690 | 1.992
12190 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | LINCOLN |  | 07 | 2009615 | This is a resurfacing project in Lincoln County on County Highway CC, Nick Road to Tannery Road. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-06 | 1140000 | 61.270
12191 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009622 | This is a bridge replacement project in Marathon County on a town road, Badger Road Bridge. | Bridge Replacement | 2009-05-18 | 2009-05-18 | 2010-01-01 |  | 732896 | 0.095
12192 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CLARK |  | 03 | 2009623 | This is a bridge replacement project in Clark County on County Highway OO, Black River Bridge. | Bridge Replacement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2010-04-28 | 1476000 | 0.000
12193 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 02 | 2009624 | This is a bridge replacement project in Rock County on County Highway H, Raccoon Creek Bridge. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-25 | 418310 | 0.190
12194 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ADAMS |  | 06 | 2009680 | This is a reconstruction project in Adams County on County Highway Z, Town of Strongs Prairie and Monroe. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2010-01-01 |  | 4299989 | 89.700
12195 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON | WAUSAU | 07 | 2009681 | This is a reconstruction project in Marathon County on local streets, Village of Weston, Ross Avenue. | Other | 2009-06-25 | 2009-06-25 | 2009-12-01 | 2010-08-03 | 2062007 | 61.640
12196 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON | WAUSAU | 07 | 2009682 | This is a resurfacing project in Marathon County on local streets, Stewart Avenue - Elm Street. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2009-10-01 | 2009-10-16 | 430000 | 0.580
12197 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2009683 | This is a resurfacing project in Portage County on County Highway D, Almond. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2009-11-01 | 2009-11-13 | 1230000 | 92.800
12198 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | FLORENCE |  | 08 | 2009684 | This is a restoration and rehabilitation project in Florence County on County Highway U, Marinette County Line - County Highway N. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-11-01 | 2010-06-03 | 2800000 | 54.900
12199 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WAUPACA |  | 08 | 2009685 | This is a resurfacing project in Waupaca County on local streets, City of Clintonville, North 12th Street. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-10-09 | 375150 | 5.600
12200 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009686 | This is a reconstruction project in Milwaukee County on local streets, West State Street. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2010-07-01 |  | 1638019 | 9.520
12201 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009687 | This is a reconstruction project in Milwaukee County on local streets, West Oklahoma Avenue. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2010-08-01 |  | 2200000 | 12.960
12202 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MONROE |  | 03 | 2009688 | This is a resurfacing project in Monroe County on County Highway O, Warrens. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-10-26 | 990000 | 19.110
12203 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2009689 | This is a resurfacing project in Rock County on local streets, City of Janesville, various streets. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-10-30 | 1575630 | 127.760
12204 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009690 | This is a reconstruction project in Milwaukee County on local streets, West Lisbon Avenue. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2010-06-01 | 2010-08-03 | 2573868 | 15.300
12205 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2009691 | This is a bridge replacement project in Barron County on a town road, Pokegama Creek Bridge. | Bridge Replacement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2010-05-06 | 295200 | 0.000
12206 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009692 | This is a bridge replacement project in Fond du Lac County on local streets, Kiel Road Bridge and approaches. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-12-01 | 342000 | 0.000
12207 | Underway | C250 | Highway Infrastructure Investment Grant | WISCONSIN | WAUPACA |  | 08 | 2009693 | This is a bridge replacement project in Waupaca County on County Highway Q, Waupaca River Crossing. | Bridge Replacement | 2009-06-24 | 2009-06-24 | 2009-11-01 |  | 1257354 | 0.380
12208 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009694 | This is a bridge rehabilitation project in Taylor County on County Highway A, Pine Creek Bridge. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-12-30 | 2009-11-02 | 159900 | 0.000
12209 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2009695 | This is a new roadway construction project of 1.15 miles in Marinette County on County Highway T, Roosevelt Road, City of Marinette. | New Construction | 2009-06-25 | 2009-06-25 | 2010-06-01 | 2010-05-28 | 3382500 | 11.500
12210 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | FOREST |  | 08 | 2009696 | This is a pedestrian and bicycle path project in Forest County, Mole Lake Multi-Use Trail. | Transportation Enhancements | 2009-06-24 | 2009-06-24 | 2009-11-01 |  | 738000 | 0.000
12211 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | VILAS |  | 08 | 2009697 | This is a bicycle path project in Vilas County, Trout Lake Bicycle Trail. | Transportation Enhancements | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2010-06-09 | 279379 | 0.000
12212 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009866 | This is the design engineering effort for a construction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Other | 2009-07-30 | 2009-07-30 | 2010-01-05 | 2010-01-05 | 62040 | 0.000
12213 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2009867 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 51st Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 5300 | 0.000
12214 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009868 | This is the design engineering effort for a construction project in Milwaukee County on local streets, West Vliet Street Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 25000 | 0.000
12215 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009869 | This is the design engineering effort for a construction project in Milwaukee County on local streets, North Sherman Blvd. Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 10600 | 0.000
12216 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009870 | This is the design engineering effort for a construction project in Milwaukee County on local streets, North Sherman Blvd. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 9100 | 0.000
12217 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2009871 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 76th Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 12260 | 0.000
12218 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009872 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 6th Street Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 19025 | 0.000
12219 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009873 | This is the design engineering effort for a construction project in Waukesha County on County Highway ES, Calhoun Road to County Highway O. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8200 | 0.000
12220 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009874 | This is the design engineering effort for a construction project in Milwaukee County on local streets, West National Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4800 | 0.000
12221 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2009875 | This is the design engineering effort for a construction project in Milwaukee County on local streets, Hampton Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 80000 | 0.000
12222 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009876 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South Cesar Chavez Drive. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 75000 | 0.000
12223 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009877 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 6th Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4580 | 0.000
12224 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 05 | 2009878 | This is the design engineering effort for a construction project in Milwaukee County on local streets, 70th Street Brige. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 15800 | 0.000
12225 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | OZAUKEE | MILWAUKEE | 05 | 2009879 | This is the design engineering effort for a construction project in Ozaukee County on County Highway O, North Green Bay Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 15600 | 0.000
12226 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | OZAUKEE | MILWAUKEE | 05 | 2009880 | This is the design engineering effort for a construction project in Ozaukee County on local streets, West Donges Bay Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-15 | 2009-12-15 | 5000 | 0.000
12227 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009881 | This is the design engineering effort for a construction project in Racine County on local streets, North Main Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 31000 | 0.000
12228 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009882 | This is the design engineering effort for a construction project in Racine County on County Highway C, Spring Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 6122 | 0.000
12229 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2009883 | This is the design engineering effort for a construction project in Kenosha County on local streets, 38th Street Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 16180 | 0.000
12230 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009884 | This is the design engineering effort for a construction project in Racine County on local streets, Lathrop Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7073 | 0.000
12231 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009885 | This is the design engineering effort for a construction project in Racine County on local streets, Taylor Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 3122 | 0.000
12232 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009886 | This is the design engineering effort for a construction project in Washington County on local streets, Decorah Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 12284 | 0.000
12233 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009887 | This is the design engineering effort for a construction project in Washington County on local streets, 7th Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 1956 | 0.000
12234 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009888 | This is the design engineering effort for a construction project in Washington County on local streets, Indiana Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8316 | 0.000
12235 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009889 | This is the design engineering effort for a construction project in Washington County on local streets, Vine Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 1976 | 0.000
12236 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009890 | This is the design engineering effort for a construction project in Washington County on local streets, Park Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 1730 | 0.000
12237 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009891 | This is the design engineering effort for a construction project in Washington County on local streets, Jefferson Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4096 | 0.000
12238 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009892 | This is the design engineering effort for a construction project in Waukesha County on local streets, Wisconsin Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 18300 | 0.000
12239 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009893 | This is the design engineering effort for a construction project in Waukesha County on County Highway O, South Moorland Blvd. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 23250 | 0.000
12240 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009894 | This is the design engineering effort for a construction project in Waukesha County on County Highway K, North 132nd Street to North 124th Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 17393 | 0.000
12241 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009895 | This is the design engineering effort for a construction project in Waukesha County on County Highway T, Grandview Blvd.. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4400 | 0.000
12242 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009896 | This is the design engineering effort for a construction project in Waukesha County on County Highway V, Townline Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 16050 | 0.000
12243 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009897 | This is the design engineering effort for a construction project in Waukesha County on County Highway Y, Baker Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 20000 | 0.000
12244 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2009898 | This is the design engineering effort for a construction project in Milwaukee County on County Highway ZZ, West Loomis Road to South 51st Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 18150 | 0.000
12245 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2009899 | This is the design engineering effort for a construction project in Milwaukee County on local streets, Eastbrook Park Drive. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 16200 | 0.000
12246 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009900 | This is the design engineering effort for a construction project in Walworth County on local streets, Wrigley Drive. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 12000 | 0.000
12247 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009901 | This is the design engineering effort for a construction project in Walworth County on local streets, Mohawk Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 3560 | 0.000
12248 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2009902 | This is the design engineering effort for a construction project in Grant County on County Highway D, City of Platteville, Chestnut Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-15 | 2009-12-15 | 40500 | 0.000
12249 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | SHAWANO |  | 08 | 2009903 | This is the design engineering effort for a construction project in Shawano County on County Highway D, North Branch Embarrass River Crossing. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 9900 | 0.000
12250 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2009904 | This is the design engineering effort for a construction project in Trempealeau County, Whitehall Historic Railroad Depot. | Other | 2009-07-30 | 2009-07-30 | 2010-01-05 | 2010-01-05 | 7820 | 0.000
12251 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PIERCE |  | 03 | 2009905 | This is the design engineering effort for a construction project in Pierce County on County Highway P, May Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 6959.42 | 0.000
12252 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2009906 | This is the design engineering effort for a construction project in Polk County, Amery to Dresser Trail. | Other | 2009-07-30 | 2009-07-30 | 2010-01-05 | 2010-01-05 | 13300 | 0.000
12253 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | WASHBURN |  | 07 | 2009907 | This is the design engineering effort for a construction project in Washburn County, Spooner Bicycle and Pedestrian Facility. | Other | 2009-07-30 | 2009-07-30 | 2010-01-05 | 2010-01-05 | 6260 | 0.000
12254 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BAYFIELD |  | 07 | 2009908 | This is the design engineering effort for a construction project in Bayfield County on State Highway 13, Red Cliff streetscape improvement. | Other | 2009-07-30 | 2009-07-30 | 2010-01-05 | 2010-01-05 | 15300 | 0.000
12255 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHBURN |  | 07 | 2009909 | This is the design engineering effort for a construction project in Washburn County on County Highway E, Namekagon River Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4000 | 0.000
12256 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2009910 | This is the design engineering effort for a construction project in Chippewa County on local streets, First Avenue. | Other | 2009-08-26 | 2009-08-26 | 2009-12-15 | 2009-12-15 | 8800 | 0.000
12257 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2009911 | This is the design engineering effort for a construction project in Chippewa County on County Highway X, 57th Avenue West to 184th Street. | Other | 2009-08-26 | 2009-08-26 | 2009-12-01 | 2009-12-01 | 7400 | 0.000
12258 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS | DULUTH-SUPERIOR (MN) | 07 | 2009912 | This is the design engineering effort for a construction project in Douglas County on local streets, East 5th Street, 6th Avenue East to 20th Avenue East. | Other | 2009-08-26 | 2009-08-26 | 2009-12-15 | 2009-12-15 | 7500 | 0.000
12259 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009914 | This is the design engineering effort for a construction project in Milwaukee County on County Highway S, North 84th Street to North 56th Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 211427 | 0.000
12260 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009915 | This is the design engineering effort for a construction project in Milwaukee County, South Cesar Chavez Drive, West National Avenue to Greenfield Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8000 | 0.000
12261 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009916 | This is the design engineering effort for a construction project in Racine County, North Shore Multi-Use Path. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8880 | 0.000
12262 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009917 | This is the design engineering effort for a construction project in Waukesha County, Lake Country Trail. | Other | 2009-07-30 | 2009-07-30 | 2009-12-15 | 2009-12-15 | 17511 | 0.000
12263 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009918 | This is the design engineering effort for a construction project in Milwaukee County on , Kinnickinnic River Bike Trail. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7000 | 0.000
12264 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2009919 | This is the design engineering effort for a construction project in Kenosha County on local streets, 30th Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 16290 | 0.000
12265 | Completed | C200,C230 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 01 | 2009920 | This is the design engineering effort for a construction project in Kenosha County on County Highway Z, Main Street East. | Other | 2009-07-30 | 2009-07-30 | 2009-12-22 | 2009-12-22 | 9520 | 0.000
12266 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009921 | This is the design engineering effort for a construction project in Kenosha County on local streets, Cooper Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 5000 | 0.000
12267 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009922 | This is the design engineering effort for a construction project in Racine County on local streets, Kane Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7120 | 0.000
12268 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KEWAUNEE |  | 08 | 2009924 | This is the design engineering effort for a construction project in Kewaunee County on County Highway A, Town of Luxemburg. | Other | 2009-07-30 | 2009-07-30 | 2009-12-15 | 2009-12-15 | 8325 | 0.000
12269 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009925 | This is the design engineering effort for a construction project in Brown County on County Highway I, Town of Scott. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 6706 | 0.000
12270 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009926 | This is the design engineering effort for a construction project in Brown County on local streets, City of DePere, Jordan Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 3560 | 0.000
12271 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009927 | This is the design engineering effort for a construction project in Brown County, Fox River Recreation Trail. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4140 | 0.000
12272 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009928 | This is the design engineering effort for a construction project in Brown County on local streets, City of Green Bay, Manitowoc Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 13178 | 0.000
12273 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009929 | This is the design engineering effort for a construction project in Brown County, Verlin Road Bike and Pedestrian Facilities. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7447 | 0.000
12274 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | JUNEAU |  | 03 | 2009930 | This is the design engineering effort for a construction project in Juneau County on County Highway A, New Lisbon, Krypton Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 10500 | 0.000
12275 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2009931 | This is the design engineering effort for a construction project in Rock County, Rotamer Road Bike Trail Connector. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8700 | 0.000
12276 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | LA CROSSE | LA CROSSE (MN) | 03 | 2009932 | This is the design engineering effort for a construction project in La Crosse County on State Highway 35, Mormon Coulee Road Bike Path improvement. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8620 | 0.000
12277 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO |  | 06 | 2009933 | This is the design engineering effort for a construction project in Winnebago County on County Highway D, Town of Winneconnie and Town of Poygan. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 11000 | 0.000
12278 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2009934 | This is the design engineering effort for a construction project in Portage County on local streets, City of Stevens Point, Minnesota Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 53000 | 0.000
12279 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009935 | This is the design engineering effort for a construction project in Brown County on County Highway EB, Village of Howard. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 11120 | 0.000
12280 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | FOREST |  | 08 | 2009941 | This is the design engineering effort for a construction project in Forest County, the rebuild and rehabilitation of Laona Northern Railroad Track. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 10240 | 0.000
12281 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | Multiple | 2009942 | This is the design engineering effort for a construction project in Outagamie County, Fox River Navigation, Lock Keeper Houses. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 15391 | 0.000
12282 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2009947 | This is the design engineering effort for a construction project in Douglas County on County Highway C, State Highway 35 to Kronberg Road. | Other | 2009-10-20 | 2009-10-20 | 2009-12-01 | 2009-12-01 | 20000 | 0.000
12283 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | JEFFERSON |  | Multiple | 2009953 | This is the design engineering effort for a construction project in Jefferson County on County Highway F, Sullivan, I-94. | Other | 2009-08-04 | 2009-08-04 | 2009-12-01 | 2009-12-01 | 18900 | 0.000
12284 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2009954 | This is the design engineering effort for a construction project in Grant County on local streets, Village of Bloomington, Mill Street. | Other | 2009-08-04 | 2009-08-04 | 2009-12-15 | 2009-12-15 | 12120 | 0.000
12285 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | IOWA |  | 03 | 2009955 | This is the design engineering effort for a construction project in Iowa County on County Highway X, Village of Linden, Babcock Avenue. | Other | 2009-08-04 | 2009-08-04 | 2009-12-15 | 2009-12-15 | 3860 | 0.000
12286 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 02 | 2009956 | This is the design engineering effort for a construction project in Rock County on County Highway C, North 4th Street and West Main Street. | Other | 2009-08-04 | 2009-08-04 | 2009-12-01 | 2009-12-01 | 9600 | 0.000
12287 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009957 | This is the design engineering effort for a construction project in Dane County on local streets, City of Verona, North Nine Mound Road. | Other | 2009-08-06 | 2009-08-06 | 2009-12-01 | 2009-12-01 | 13200 | 0.000
12288 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 02 | 2009958 | This is the design engineering effort for a construction project in Rock County on Town Road, Town of Beloit, Inman Parkway. | Other | 2009-10-20 | 2009-10-20 | 2010-03-31 |  | 1122.07 | 0.000
12289 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009959 | This is the design engineering effort for a construction project in Dane County on County Highway Q, City of Middleton, Allen Blvd.. | Other | 2009-08-06 | 2009-08-06 | 2009-12-01 | 2009-12-01 | 7860 | 0.000
12290 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009960 | This is the design engineering effort for a construction project in Dane County on County Highway MS, City of Madison, University Avenue. | Other | 2009-08-06 | 2009-08-06 | 2009-12-01 | 2009-12-01 | 24400 | 0.000
12291 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009965 | This is the design engineering effort for a construction project in Dane County on County Highway K, US Highway 12 and County Highway M. | Other | 2009-08-13 | 2009-08-13 | 2009-12-01 | 2009-12-01 | 9600 | 0.000
12292 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | SHEBOYGAN | SHEBOYGAN | 06 | 2010051 | This is the design engineering effort for a construction project in Sheboygan County on local streets, Taylor Drive, Superior Avenue, and Saemann Avenue. | Other | 2009-09-29 | 2009-09-29 | 2009-12-01 | 2009-12-01 | 13266 | 0.000
12293 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010059 | This is a reconstruction project in Barron County on US Highway 53, New Auburn - Spooner. | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-11-01 |  | 9710598.99 | 74.280
12294 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010060 | This is a reconstruction project in Barron County on US Highway 53, New Aubrurn - Spooner. | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-11-01 |  | 8561385.4 | 74.280
12295 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2010061 | This is a bridge rehabilitation project in Crawford County on US Highway 61, Boscobel - Readstownn, Wisconsin River Structure. | Bridge Improvement | 2010-06-28 | 2010-05-13 |  |  | 331552 | 0.220
12296 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010062 | This is a bridge rehabilitation project in Milwaukee County on local streets, West Vliet Street Bridge. | Bridge Improvement | 2009-12-04 | 2009-12-04 | 2010-09-01 |  | 145843.22 | 0.000
12297 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010063 | This is a bridge rehabilitation project in Milwaukee County on local streets, North Sherman Blvd. Bridge. | Bridge Improvement | 2009-12-04 | 2009-12-04 | 2010-09-01 |  | 582424.83 | 0.000
12298 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010064 | This is a resurfacing project in Milwaukee County on local streets, North Sherman Blvd. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-09-01 |  | 417555.48 | 0.000
12299 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2010065 | This is a resurfacing project in Milwaukee County on local streets, South 76th Street. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-07-01 |  | 603990 | 0.000
12300 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010066 | This is a resurfacing project in Milwaukee County on local streets, West National Avenue. | Pavement Improvement | 2009-12-02 | 2009-12-02 | 2010-07-01 |  | 295200 | 0.000
12301 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010067 | This is a resurfacing project in Milwaukee County on local streets, South Cesar Chavez Drive. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-07-01 |  | 707250 | 0.000
12302 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010068 | This is a landscaping and other scenic beautification project in Milwaukee County, South Cesar Chavez Drive. | Transportation Enhancements | 2009-12-04 | 2009-12-04 | 2010-07-01 |  | 492000 | 0.000
12303 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010069 | This is a resurfacing project in Milwaukee County on local streets, South 68th Street. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-07-01 |  | 281670 | 0.000
12304 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010070 | This is a pedestrian and bicycle path project in Racine County, North Shore Multi-use Path. | Transportation Enhancements | 2009-12-04 | 2009-12-04 | 2010-06-01 | 2010-07-15 | 436120 | 0.000
12305 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010071 | This is a resurfacing project in Racine County on local streets, Lathrop Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 435001 | 1.570
12306 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010072 | This is a resurfacing project in Racine County on local streets, Taylor Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 192001 | 0.240
12307 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010073 | This is a restoration and rehabilitation project in Racine County on County Highway G, Union Church Drive. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-06-01 |  | 1398350 | 0.000
12308 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010074 | This is a restoration and rehabilitation project in Racine County on County Highway K, East Wink Lake Rd - Overson Road. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-06-01 |  | 837780 | 0.000
12309 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010075 | This is a bridge rehabilitation project in Milwaukee County on local streets, Jackson Park Drive. | Bridge Improvement | 2009-12-04 | 2009-12-04 | 2010-07-01 |  | 405000 | 0.000
12310 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2010076 | This is a bridge replacement project in Manitowoc County on local streets, Pioneer Road. | Bridge Replacement | 2009-12-07 | 2009-12-07 | 2010-04-01 | 2010-05-07 | 325000 | 0.000
12311 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 2010077 | This is a bridge replacement project in Winnebago County on local streets, City of Neenah, Adams Street. | Bridge Replacement | 2009-12-10 | 2009-12-10 | 2010-04-01 | 2010-04-30 | 415000 | 0.000
12312 | Underway | C250,C200 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2010078 | This is a bridge rehabilitation project in Crawford County on State Highway 60, Bridgeport - Blue River. | Bridge Improvement | 2010-05-13 | 2010-05-13 |  |  | 325000 | 0.010
12313 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MONROE |  | 03 | 2010079 | This is a bridge replacement project in Monroe County on County Highway M, County Higway A - State Highway 16. | Other | 2009-12-04 | 2009-12-04 | 2010-09-01 |  | 383760 | 0.100
12314 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MONROE |  | 03 | 2010080 | This is a bridge replacement project in Monroe County on County Highway M, County Higway A - State Highway 16. | Other | 2009-12-04 | 2009-12-04 | 2010-09-01 |  | 471090 | 0.100
12315 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | VERNON |  | 03 | 2010081 | This is a bridge replacement project in Vernon County on County Highway UU, Victory Creek Bridge and approaches. | Bridge Replacement | 2009-12-04 | 2009-12-04 | 2010-09-01 |  | 348090 | 0.060
12316 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2010082 | This is a bridge replacement project in Crawford County on a town road, Town of Freeman, Buck Creek Bridge. | Bridge Replacement | 2009-12-04 | 2009-12-04 | 2010-07-01 | 2010-06-28 | 258300 | 0.060
12317 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2010083 | This is a reconstruction project in Dane County on County Highway K, US Highway 12 - County Highway M. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-08-01 | 2010-07-14 | 590400 | 11.900
12318 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUSHARA |  | 06 | 2010084 | This is a resurfacing project in Waushara County on State Highway 49, Poysippi - Fremont. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2010-10-01 |  | 1883107.34 | 115.920
12319 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE |  | 08 | 2010085 | This is a bridge replacement project in Outagamie County on a town road, Greiner Road Bridge and approaches. | Other | 2009-12-10 | 2009-12-10 | 2009-10-01 |  | 248200 | 0.025
12320 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE |  | 08 | 2010086 | This is a bridge replacement project in Outagamie County on a town road, Central Valley Road Bridge and approaches. | Bridge Replacement | 2009-12-07 | 2009-12-07 | 2010-07-01 |  | 305900 | 0.040
12321 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUSHARA |  | 06 | 2010087 | This is a reconstruction project in Waushara County on County Highway I, Alder Creek Crossing. | New Bridge Construction | 2009-12-16 | 2009-12-16 | 2010-07-01 |  | 175000 | 0.000
12322 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2010088 | This is a resurfacing project in Portage County on local streets, City of Stevens Point, Minnesota Avenue. | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-09-01 |  | 430500 | 3.200
12323 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BAYFIELD |  | 07 | 2010089 | This is a bridge rehabilitation project in Bayfield County on County Highway D, Namekagon River Bridge. | Bridge Improvement | 2009-12-16 | 2009-12-16 | 2010-07-01 |  | 246000 | 0.000
12324 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MENOMINEE |  | 08 | 2010090 | This is a resurfacing project in Menominee County on State Highway 55, Shawano - Langlade. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2010-12-01 |  | 2600000 | 129.920
12325 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | FOREST |  | 08 | 2010091 | This is an historic preservation project in Forest County, to rebuild and rehabilitate the Laona Northern Railroad Track. | Transportation Enhancements | 2009-12-16 | 2009-12-16 | 2010-06-01 | 2010-05-21 | 629760 | 0.000
12326 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | PRICE |  | 07 | 2010092 | This is a bridge replacement project in Price County on a town road, Sailor Creek Bridge and approaches. | Bridge Replacement | 2009-12-16 | 2009-12-16 | 2010-09-01 | 2010-08-11 | 395660 | 0.010
12327 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | JEFFERSON |  | Multiple | 2010093 | This is a reconstruction project in Jefferson County on County Highway F, Sullivan - Interstate 94. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-06-01 | 2010-06-10 | 1549800 | 15.600
12328 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2010171 | This is a bridge rehabilitation project in Grant County on US Highway 18, Prairie du Chien - Fennimore, Wisconsin River Bridge. | Bridge Improvement | 2010-06-28 | 2010-05-13 |  |  | 678278.39 | 0.130
12329 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 01 | 2010172 | This is a reconstruction project in Rock County on a town road, Town of Turtle. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-30 | 196800 | 6.000
12330 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DODGE |  | 06 | 2010173 | This is a reconstruction project in Dodge County on County Highway DJ, Village of Juneau, East Oak Grove Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-07-01 |  | 372690 | 0.000
12331 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RICHLAND |  | 03 | 2010174 | This is a reconstruction project in Richland County on County Highway C, Vernon County Line, Rolt Lane. | Pavement Improvement | 2010-01-12 | 2010-01-12 | 2010-09-01 |  | 1482150 | 0.000
12332 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RICHLAND |  | 03 | 2010175 | This is a reconstruction project in Richland County on County Highway D, Rockbrook Bridge. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 |  | 1166040 | 0.000
12333 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | JUNEAU |  | 03 | 2010176 | This is a reconstruction project in Juneau County on County Highway A, Monroe County Line - New Lisbon. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-08-18 | 3062700 | 52.000
12334 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 02 | 2010177 | This is a reconstruction project in Rock County on County Highway C, North 4th Street and West Main Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-07-01 | 2010-06-30 | 590400 | 4.000
12335 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 02 | 2010178 | This is a reconstruction project in Rock County on a town road, Town of Beloit, Inman Parkway. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-30 | 670350 | 16.800
12336 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 02 | 2010179 | This is a reconstruction project in Rock County on local streets, Town of Beloit, Cranston Road. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-30 | 129150 | 0.000
12337 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | LA CROSSE | LA CROSSE (MN) | 03 | 2010180 | This is a bicycle path project in La Crosse County on State Highway 35, Mormon Coulee Road Bike Path Improvement. | Transportation Enhancements | 2009-12-31 | 2009-12-31 | 2010-09-01 | 2010-08-20 | 530130 | 2.800
12338 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010181 | This is a reconstruction project in Dane County on County Highway MS, City of Madison, University Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-06-01 |  | 3633800 | 7.200
12339 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DODGE |  | 06 | 2010182 | This is a reconstruction project in Dodge County on various highways, Madison Street and University Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 |  | 956940 | 0.000
12340 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010183 | This is a roundabut project in Milwaukee County on local streets, West Winnebago Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-08-04 | 1044213 | 0.000
12341 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010184 | This is a reconstruction project in Milwaukee County on local streets, East and West Keefe Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-11-01 |  | 3210617.01 | 0.000
12342 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2010185 | This is a resurfacing project in Milwaukee County on local streets, West Grange Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 |  |  | 688800 | 0.000
12343 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010186 | This is a reconstruction project in Milwaukee County on local streets, East and West North Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 |  | 2163949 | 0.000
12344 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2010187 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Hampton Avenue. | Pavement Improvement | 2010-01-12 | 2010-01-12 | 2010-11-01 |  | 773241 | 0.000
12345 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010188 | This is a restoration and rehabilitation project in Milwaukee County on local streets, 15th Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 |  | 799500 | 0.000
12346 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | OZAUKEE | MILWAUKEE | 05 | 2010189 | This is a restoration and rehabilitation project in Ozaukee County on County Highway O, North Green Bay Road. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 |  | 959400 | 0.000
12347 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010190 | This is a bridge rehabilitation project in Kenosha County on local streets, 38th Street Bridge. | Bridge Replacement | 2010-01-13 | 2010-01-13 | 2010-12-01 |  | 945000 | 0.000
12348 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010191 | This is a resurfacing project in Washington County on local streets, Decorah Road. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 |  | 455466 | 0.000
12349 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010192 | This is a resurfacing project in Washington County on local streets, 7th Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 |  | 120294 | 0.000
12350 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010193 | This is a resurfacing project in Washington County on local streets, Indiana Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 |  | 311434 | 0.000
12351 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010194 | This is a resurfacing project in Washington County on local streets, Vine Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 |  | 121524 | 0.000
12352 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010195 | This is a resurfacing project in Washington County on local streets, Park Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 |  | 106395 | 0.000
12353 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010196 | This is a resurfacing project in Washington County on local streets, Jefferson Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 |  | 251904 | 0.000
12354 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2010197 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Eastbrook Park Drive. | Pavement Widening | 2010-01-12 | 2010-01-12 | 2010-11-01 |  | 835580 | 0.000
12355 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010198 | This is a resurfacing project in Kenosha County on local streets, 30th Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 |  | 1035780 | 0.000
12356 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2010199 | This is a pedestrian access and safety project in Kenosha County. | Transportation Enhancements | 2010-01-13 | 2010-01-13 |  |  | 215182 | 0.000
12357 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2010200 | This is a resurfacing project in Kenosha County on local streets, Cooper Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 307500 | 0.000
12358 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010201 | This is a resurfacing project in Kenosha County on local streets, 80th Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 |  | 553500 | 0.000
12359 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010202 | This is a resurfacing project in Racine County on local streets, Kane Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 |  | 387880 | 0.000
12360 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010203 | This is a restoration and rehabilitation project in Racine County on various highways, Market Street, Pine Street - Dodge Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 |  |  | 433575 | 0.000
12361 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010204 | This is a resurfacing project in Racine County on various highways, Grove Street, Oak Street - Briody Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 |  |  | 551110 | 0.000
12362 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | Multiple | 2010205 | This is an historic preservation project in Outagamie County, the rehabilitation of the Fox River Navigation System Lock Keeper houses. | Transportation Enhancements | 2010-01-13 | 2010-01-13 | 2010-10-01 |  | 946576 | 0.000
12363 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | 08 | 2010206 | This is a reconstruction project in Outagamie County on local streets, Village of Little Chute, Washington Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 |  |  | 360390 | 0.300
12364 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010207 | This is a pedestrian and bicycle path project in Brown County, Fox River Recreation Trail. | Transportation Enhancements | 2010-01-13 | 2010-01-13 | 2010-07-01 | 2010-06-04 | 254610 | 0.000
12365 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010208 | This is a pedestrian and bicycle path project in Brown County, Verlin Road Bike Pedestrian Facilities. | Transportation Enhancements | 2010-01-13 | 2010-01-13 | 2010-10-01 |  | 457978 | 0.000
12366 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 2010209 | This is a restoration and rehabilitation project in Winnebago County on local streets, City of Mehasha, Tayco Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-08-11 | 473550 | 9.800
12367 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2010210 | This is a resurfacing project in Winnebago County on local streets, City of Oshkosh, Snell Road. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-08-19 | 717090 | 16.000
12368 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 2010211 | This is a restoration and rehabilitation project in Winnebago County on local streets, City of Neenah, Wisconsin Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-07-01 |  | 450000 | 0.420
12369 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | SHEBOYGAN | SHEBOYGAN | 06 | 2010212 | This is a reconstruction project in Sheboygan County on local streets, Taylor Drive, Superior Avenue, and Saemann Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 |  | 815870 | 6.840
12370 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OCONTO |  | 08 | 2010213 | This is a bridge rehabilitation project in Oconto County on County Highway S, Pensaukee River Bridge. | Bridge Improvement | 2010-01-13 | 2010-01-13 |  |  | 430500 | 0.000
12371 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OCONTO |  | 08 | 2010214 | This is a bridge rehabilitation project in Oconto County on County Highway S, Pensaukee River Bridge. | Bridge Improvement | 2010-01-13 | 2010-01-13 |  |  | 344400 | 0.000
12372 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010215 | This is a reconstruction project in Marinette County on local streets, Cleveland Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-22 | 638370 | 0.000
12373 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010216 | This is a reconstruction project in Marinette County on local streets, Hattie Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-22 | 129150 | 0.000
12374 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010217 | This is a reconstruction project in Marinette County on local streets, Hosmer Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-22 | 116850 | 0.000
12375 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010218 | This is a reconstruction project in Marinette County on local streets, Marinette Mid City Bike and Pedestrian Path. | Transportation Enhancements | 2010-01-13 | 2010-01-13 | 2010-06-01 | 2010-05-26 | 116000 | 0.000
12376 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | IRON |  | 07 | 2010219 | This is a new roadway construction project of 3.96 miles in Iron County on US Highway 51, County Highway C - Hurley. | Pavement Improvement | 2010-05-13 | 2010-05-13 |  |  | 1500000 | 19.800
12377 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DUNN |  | 03 | 2010220 | This is a reconstruction project in Dunn County on County Highway P, Spring Valley - Menomonie. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-06-01 |  | 1184490 | 0.000
12378 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PIERCE |  | 03 | 2010221 | This is a reconstruction project in Pierce County on County Highway P, May Avenue. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-09-01 | 2010-07-09 | 693040.58 | 0.000
12379 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DUNN |  | 03 | 2010222 | This is a resurfacing project in Dunn County on local streets, City of Menomonie, 3M Drive and 9th Street. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-09-01 |  | 1629750 | 0.000
12380 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2010223 | This is a resurfacing project in Sawyer County on State Highway 27, Ojibwa - Stone Lake. | Pavement Improvement | 2010-03-11 | 2010-03-11 |  |  | 954042.66 | 37.350
12381 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2010224 | This is a resurfacing project in Sawyer County on State Highway 27, Ojibwa - Stone Lake. | Pavement Improvement | 2010-03-11 | 2010-03-11 |  |  | 1411182.26 | 121.920
12382 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2010225 | This is a bridge replacement project in Douglas County on a town road, Town of Wascott, Cheever Road, Ounce River Bridge. | Bridge Replacement | 2010-01-14 | 2010-01-14 | 2010-07-01 | 2010-08-13 | 238620 | 0.000
12383 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2010226 | This is a bridge replacement project in Douglas County on a town road, Town of Wascott, East Coppermine Road, Ounce River Bridge. | Bridge Replacement | 2010-01-14 | 2010-01-14 | 2010-07-01 | 2010-08-13 | 252150 | 0.000
12384 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RUSK |  | 07 | 2010227 | This is a restoration and rehabilitation project in Rusk County on County Highway F, Bear Lake, Potato Lake Road. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-07-01 |  | 541200 | 0.000
12385 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHBURN |  | 07 | 2010228 | This is a bridge rehabilitation project in Washburn County on County Highway E, Namekagon River Bridge. | Bridge Improvement | 2010-01-14 | 2010-01-14 | 2010-05-01 | 2010-05-19 | 246000 | 0.000
12386 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2010229 | This is a restoration and rehabilitation project in Chippewa County on local streets, City of Chippewa Falls Bridge Street. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-06-01 | 2010-06-08 | 221400 | 0.000
12387 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS | DULUTH-SUPERIOR (MN) | 07 | 2010230 | This is a resurfacing project in Douglas County on local streets, City of Superior, Hill Avenue and Broadway Street. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-08-01 | 2010-06-30 | 528900 | 0.000
12388 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RICHLAND |  | 03 | 2010269 | This is a bridge replacement project in Richland County on town road, Cortland Lane, Town of Akan. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 302580 | 0.550
12389 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2010270 | This is a reconstruction project in Crawford County on County Highway B, County Highway B, State Highway 35 - State Highway 27 Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 3874500 | 2.000
12390 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2010271 | This is a reconstruction project in Grant County on local streets, Village of Bloomington Mill Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 745380 | 0.280
12391 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 02 | 2010272 | This is a reconstruction project in Rock County on a town road, West Happy Hollow Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 544890 | 2.489
12392 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010273 | This is a reconstruction project in Dane County on local streets, City of Verona, North Nine Mound Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 714800 | 0.440
12393 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2010274 | This is a bicycle path project in Rock County, Rotamer Road Bike Trail connector. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 445000 | 0.975
12394 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2010276 | This is a reconstruction project in Rock County on local streets, Ruger Avenue Bridge and approaches, City of Janesville. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 619920 | 0.040
12395 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2010277 | This is a reconstruction project in Rock County on local streets, City of Janesville Tyler - South Randall. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 415740 | 0.480
12396 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2010278 | This is a reconstruction project in Rock County on local streets, City of Milton, East High Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 584250 | 1.190
12397 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2010279 | This is a bridge replacement project in Grant County on County Highway D, City of Platteville, Chestnut Street, Rountree Branch Bridge. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-11-01 |  | 3321000 | 0.090
12398 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2010280 | This is a reconstruction project in Milwaukee County on local streets, South 51st Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 325950 | 0.390
12399 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2010281 | This is a resurfacing project in Milwaukee County on local streets, South 51st Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 1500600 | 1.020
12400 | Underway | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010282 | This is a reconstruction project in Milwaukee County on local streets, South 1st Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 1959841.35 | 0.690
12401 | Underway | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010283 | This is a bridge replacement project in Milwaukee County on local streets, South 6th Street Bridge. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2011-01-01 |  | 2532695.48 | 0.140
12402 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010284 | This is a restoration and rehabilitation project in Milwaukee County on County Highway NN, South 76th Street to South 72nd Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 496960 | 0.300
12403 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010285 | This is a reconstruction project in Milwaukee County on local streets, South 13th Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 1519230 | 0.620
12404 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 05 | 2010286 | This is a resurfacing project in Milwaukee County on local streets, Burleigh Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 959700 | 0.470
12405 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010287 | This is a restoration and rehabilitation project in Milwaukee County on County Highway S, . | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 2606294 | 1.700
12406 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 05 | 2010288 | This is a bridge replacement project in Milwaukee County on local streets, 70th Street Bridge. | Bridge Replacement | 2010-02-10 | 2010-02-10 |  |  | 971700 | 0.070
12407 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | OZAUKEE | MILWAUKEE | 05 | 2010289 | This is a restoration and rehabilitation project in Ozaukee County on local streets, West Donges Bay Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-01 |  | 307500 | 0.690
12408 | Underway | C220,C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010290 | This is a pedestrian and bicycle path project in Waukesha County, Lake County Trail. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 1435885 | 5.437
12409 | Underway | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010291 | This is a resurfacing project in Waukesha County on local streets, Wisconsin Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 1134970 | 0.500
12410 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010292 | This is a reconstruction project in Waukesha County on County Highway O, South Moorland Blvd. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 1906500 | 0.540
12411 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 05 | 2010293 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Fairy Chasm Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-08-12 | 190650 | 0.100
12412 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010294 | This is a bicycle path project in Milwaukee County, Kinnickinnic River Bike Trail. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-07-01 | 2010-08-12 | 395500 | 0.639
12413 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2010295 | This is a restoration and rehabilitation project in Milwaukee County on County Highway ZZ, . | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 1449208 | 0.760
12414 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010296 | This is a bridge rehabilitation project in Milwaukee County on local streets, Root River Parkway. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 1033738 | 0.700
12415 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010297 | This is a pedestrian and bicycle path project in Milwaukee County, Hank Aaron State Trail. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 1520234 | 0.353
12416 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010298 | This is a streetscape project in Milwaukee County, St. Francis. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-11-01 |  | 952881 | 0.830
12417 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010299 | This is a resurfacing project in Brown County on local streets, City of Depere, Jordan Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-20 | 218940 | 0.900
12418 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010300 | This is a restoration and rehabilitation project in Brown County on local streets, City of Green Bay, Manitowoc Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-01 |  | 810447 | 0.890
12419 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | CALUMET | APPLETON | 06 | 2010301 | This is a bicycle path project in Calumet County, Town of Harrison, Noe Road Bike and Pedestrian Path. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 347635 | 1.580
12420 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 2010302 | This is a restoration and rehabilitation project in Winnebago County on local streets, City and Town of Menasha, Manitowoc Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-01 | 2010-07-07 | 480000 | 1.180
12421 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | 08 | 2010303 | This is a pedestrian and bicycle path project in Outagamie County, Greenville Pedestrian Trail. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 667894 | 0.750
12422 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010304 | This is a reconstruction project in Marinette County, Walk-way connection. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 723988 | 0.268
12423 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARQUETTE |  | 06 | 2010305 | This is a resurfacing project in Marquette County on County Highway CX, Village of Endeavor. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-09-01 |  | 1260750 | 1.470
12424 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | WAUSHARA |  | 06 | 2010306 | This is a pedestrian and bicycle path project in Waushara County, Wild Rose Roberts Park Trail. | Transportation Enhancements | 2010-02-09 | 2010-02-09 | 2010-08-01 |  | 246700 | 0.230
12425 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BUFFALO |  | 03 | 2010307 | This is a bridge replacement project in Buffalo County on a town road, Town of Montana, Buells Valley Road. | Bridge Replacement | 2010-02-09 | 2010-02-09 | 2010-08-01 | 2010-08-04 | 223860 | 0.400
12426 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2010308 | This is a bridge replacement project in Trempealeau County on town road, Town of Chimney Rock, Borst Valley Creek Bridge. | Bridge Replacement | 2010-02-09 | 2010-02-09 | 2010-07-01 | 2010-07-15 | 196800 | 0.450
12427 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2010309 | This is a construction project in Polk County, Amery to Dresser Trail. | Transportation Enhancements | 2010-02-09 | 2010-02-09 | 2010-07-01 | 2010-07-27 | 707950 | 10.385
12428 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2010310 | This is a reconstruction project in Polk County on County Highway Y, County Higway M - County Highway F. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-08-01 |  | 2460000 | 2.360
12429 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2010311 | This is a resurfacing project in Sawyer County on County Highway EE, Draper - Oxbo. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-07-01 | 2010-06-08 | 1261980 | 0.390
12430 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | WASHBURN |  | 07 | 2010312 | This is a pedestrian and bicycle path project in Washburn County, Spooner Bicycle and Pedestrian Facility. | Transportation Enhancements | 2010-02-09 | 2010-02-09 | 2010-08-01 |  | 384990 | 0.735
12431 | Underway | C250,C240 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2010314 | This is a reconstruction project in Douglas County on County Highway C, State Highway 35 to Kronberg Road. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-09-01 |  | 1230000 | 3.650
12432 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2010315 | This is a resurfacing project in Taylor County on County Highway O, Lublin - Medford. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-06-01 |  | 615000 | 3.090
12433 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ASHLAND |  | 07 | 2010316 | This is a resurfacing project in Ashland County on local streets, City of Ashland - 11th Street W. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-08-01 | 2010-07-06 | 307500 | 0.840
12434 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS | DULUTH-SUPERIOR (MN) | 07 | 2010317 | This is a resurfacing project in Douglas County on local streets, East 5th Street. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-07-01 | 2010-06-25 | 461250 | 0.690
12435 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ASHLAND |  | 07 | 2010318 | This is a resurfacing project in Ashland County on County Highway F, Butternut -County Line Road. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-07-01 |  | 916350 | 5.060
12436 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | IOWA |  | 03 | 2010326 | This is a bridge replacement project in Iowa County on County Highway C, Sneed Creek Bridge and approaches. | Bridge Replacement | 2010-02-10 | 2010-02-10 |  |  | 575640 | 0.640
12437 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | IOWA |  | 03 | 2010327 | This is a reconstruction project in Iowa County on County Highway X, Village of Linden, Babcock Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-15 | 237390 | 0.120
12438 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010328 | This is a reconstruction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Pavement Widening | 2010-02-11 | 2010-02-11 | 2011-10-01 |  | 2012280 | 1.080
12439 | Underway | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010329 | This is a reconstruction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Pavement Widening | 2010-02-10 | 2010-02-10 | 2011-10-01 |  | 3075000 | 1.090
12440 | Underway | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010331 | This is a reconstruction project in Dane County on County Highway Q, City of Middleton, Allen Boulevard. | Pavement Improvement | 2010-02-10 | 2010-02-10 |  |  | 277140 | 0.100
12441 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010332 | This is a decorative street lighting project in Milwaukee County, South 2nd Street. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-11-01 |  | 553500 | 0.661
12442 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010333 | This is a resurfacing project in Waukesha County on County Highway ES, Calhoun Road to County Highway O. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-20 | 504300 | 1.320
12443 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010334 | This is a resurfacing project in Racine County on local streets, South Memorial Drive. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-11-01 |  | 667890 | 0.340
12444 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010335 | This is a resurfacing project in Racine County on local streets, North Main Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-11-01 |  | 569490 | 0.459
12445 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010336 | This is a resurfacing project in Racine County on County Highway C, Spring Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 376510 | 0.380
12446 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010337 | This is a resurfacing project in Waukesha County on County Highway K, North 132nd Street to North 124th Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-08-19 | 1044657 | 0.520
12447 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010338 | This is a resurfacing project in Waukesha County on County Highway T, Grandview Blvd. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-20 | 270600 | 0.210
12448 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010339 | This is a resurfacing project in Waukesha County on County Highway V, Townline Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-20 | 816100 | 3.137
12449 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010340 | This is a new roadway construction project in Waukesha County on County Highway Y, Intersection with County Highway M. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 1230000 | 1.000
12450 | Underway | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010341 | This is a resurfacing project in Milwaukee County on various highways, City of Milwaukee. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2010-10-01 |  | 1217932.55 | 0.000
12451 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2010342 | This is a resurfacing project in Milwaukee County on various highways, City of Milwaukee. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 2320859.08 | 2.262
12452 | Underway | C220,C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2010343 | This is a streetscape project in Kenosha County on , East Main Street, County Highway Z. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-11-01 |  | 410820 | 0.140
12453 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 01 | 2010344 | This is a reconstruction project in Kenosha County on County Highway KD, County Highway F to 70th Place. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 571359 | 3.880
12454 | Underway | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 01 | 2010345 | This is a reconstruction project in Kenosha County on County Highway Z, Main Street East. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-11-01 |  | 585500 | 0.140
12455 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010346 | This is a restoration and rehabilitation project in Kenosha County on local streets, Sheridan Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 748400 | 0.490
12456 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2010347 | This is a bridge rehabilitation project in Walworth County on local streets, Wrigley Drive. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2011-06-01 |  | 738000 | 0.130
12457 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2010348 | This is a bridge rehabilitation project in Walworth County on local streets, Mohawk Road. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 218940 | 0.057
12458 | Underway | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2010349 | This is a bridge replacement project in Manitowoc County on a town road, SCL Road. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 378225 | 1.470
12459 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2010350 | This is a bridge replacement project in Manitowoc County on a town road, South Cleveland Road. | Bridge Replacement | 2010-02-10 | 2010-02-10 |  |  | 267279 | 1.660
12460 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KEWAUNEE |  | 08 | 2010351 | This is a restoration and rehabilitation project in Kewaunee County on County Highway A, Town of Luxemburg. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-01 | 2010-08-06 | 512005 | 2.000
12461 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010352 | This is a restoration and rehabilitation project in Brown County on County Highway I, Town of Scott. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 412418 | 1.170
12462 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO |  | 06 | 2010353 | This is a restoration and rehabilitation project in Winnebago County on County Highway C, Town of Winneconnie - Town of Paygan. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 1931100 | 7.850
12463 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010354 | This is a reconstruction project in Marinette County on County T, Roosevelt Road - Gallagher Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 1353000 | 0.310
12464 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010355 | This is a restoration and rehabilitation project in Brown County on County Highway EB, Village of Howard. | Pavement Improvement | 2010-02-10 | 2010-02-10 |  |  | 683855 | 2.240
12465 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010356 | This is a reconstruction project in Marinette County on local streets, Shore Drive. | Pavement Improvement | 2010-02-10 | 2010-02-10 |  |  | 837630 | 0.530
12466 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | SHAWANO |  | 08 | 2010357 | This is a bridge replacement project in Shawano County on County Highway D, North Branch Embarrass River Crossing. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-11-01 |  | 608850 | 0.090
12467 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ONEIDA |  | 07 | 2010358 | This is a reconstruction project in Oneida County on local streets, Phillip Street, City of Rhinelander. | Pavement Improvement | 2010-02-10 | 2010-02-10 |  |  | 682650 | 0.210
12468 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2010359 | This is an historic preservation project in Trempealeau County, Whitehall Historic Railroad Depot. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 480930 | 0.140
12469 | Underway | C220,C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2010361 | This is a pedestrian and bicycle path project in Sawyer County, City of Hayward, various locations. | Transportation Enhancements | 2010-02-10 | 2010-02-10 |  |  | 474780 | 0.809
12470 | Underway | C220,C240 | Highway Infrastructure Investment Grant | WISCONSIN | BAYFIELD |  | 07 | 2010362 | This is a streetscape project in Bayfield County on State Highway 13, Red Cliff - State Highway 13, Streetscape Improvement. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 940950 | 0.230
12471 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2010363 | This is a reconstruction project in Chippewa County on local streets, First Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 |  | 541200 | 0.940
12472 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2010364 | This is a reconstruction project in Chippewa County on County Highway X, 57th Avenue West to 184th Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 |  | 455100 | 0.500
12473 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010365 | This is a reconstruction project in Barron County on local streets, City of Rice Lake, Main Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 |  | 2460000 | 3.250
12474 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010366 | This is a reconstruction project in Barron County on local streets, City of Rice Lake, Pioneer Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-30 | 738000.01 | 1.060
12475 | Underway | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010367 | This is a resurfacing project in Barron County on local streets, City of Rice Lake, Haugen Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 |  |  | 399750 | 0.830
12476 | Underway | C490 | Highway Infrastructure Investment Grant | WISCONSIN | STATEWIDE |  |  | 2010406 | This is an on the job training project included in the Wisconsin Department of Transportation TrANS Program. This project trains individuals for entry into the highway construction industry by placin | Other | 2010-03-24 | 2010-03-24 | 2010-09-01 |  | 200000 | 0.000
12477 | Underway | C490 | Highway Infrastructure Investment Grant | WISCONSIN | STATEWIDE |  |  | 2010407 | This is an on the job training project included in the Wisconsin Department of Transportation TrANS Program. This project trains individuals for entry into the highway construction industry by placin | Other | 2010-03-24 | 2010-03-24 | 2010-09-01 |  | 195148 | 0.000
12478 | Underway | C950 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2010503 | This is the design engineering effort for a ferry boat project in Grant County, the Cassville Ferry. | Other | 2010-03-11 | 2010-03-11 | 2010-06-01 |  | 25000 | 0.000
12479 | Underway | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010848 | This is a reconstruction project in Kenosha County on 14th Ave., City of Kenosha, 25th Street to 31st Street. | Pavement Improvement | 2010-07-28 | 2010-07-28 |  |  | 810630 | 0.365
12480 | Awaiting NTP & Not Awarded | C950 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2010878 | This is a ferry boat project in Grant County, the Cassville Ferry. | Other |  |  |  |  | 1775000 | 1.153
12481 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | 08 | 3009018 | This is the design engineering effort for a construction project in Outagamie County, Greenville Pedestrian Trail. | Other | 2009-09-10 | 2009-09-10 | 2009-12-15 | 2009-12-15 | 10860 | 0.000
12482 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 3009019 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Neenah, Adams Street. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 8200 | 0.000
12483 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | CALUMET | APPLETON | 06 | 3009020 | This is the design engineering effort for a construction project in Calumet County, Town of Harrison, Noe Road, Bike and Pedestrian Facilities. | Transportation Enhancements | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 5653 | 0.000
12484 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 3009021 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Oshkosh, Snell Road. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 11660 | 0.000
12485 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 3009022 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Neenah, Wisconsin Avenue. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 8000 | 0.000
12486 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | 08 | 3009023 | This is the design engineering effort for a construction project in Outagamie County on local streets, Village of Little Chute, Washington Street. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 5860 | 0.000
12487 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 3009024 | This is the design engineering effort for a construction project in Winnebago County on local streets, City and Town of Menasha, Manitowoc Road. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 9252 | 0.000
12488 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 3009025 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Menasha, Tayco Street. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 7700 | 0.000
12489 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 01 | 3009145 | This is the design engineering effort for a construction project in Rock County on Town Road, Town of Turtle Townline. | Other | 2009-09-21 | 2009-09-21 | 2009-12-01 | 2009-12-01 | 3200 | 0.000
12490 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | LINCOLN |  |  | 0007035 | Construction of retaining walls on US 189 in Diamondville in Lincoln County. | Transportation Enhancements | 2009-05-20 | 2009-05-20 | 2010-07-31 | 2009-12-30 | 204160 | 0.000
12491 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | 0200028 | Pavement overlay on approximately 14 miles of WYO 30 between Basin and Burlington in Big Horn County. | Pavement Improvement | 2009-05-06 |  | 2010-06-30 |  | 1528810 | 13.790
12492 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | CAMPBELL |  |  | 0300044 | Pavement overlay of 12 miles of WYO 50 between Gillette and Pine Tree Junction in Campbell County. | Pavement Improvement | 2009-08-21 |  | 2010-10-31 |  | 2334918 | 6.790
12493 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | CAMPBELL |  |  | 0300045 | Pavement overlay of 12 miles of WYO 50 between Gillette and Pine Tree Junction in Campbell County. | Pavement Improvement | 2009-08-21 |  | 2010-10-31 |  | 1520716 | 5.300
12494 | Underway | C200 | Highway Infrastructure Investment Grant | WYOMING | GOSHEN |  |  | 0800010 | Pipe, curb and gutter, and sidewalk replacement on 0.38 miles of WYO 151 in the Town of Lagrange in Goshen County, Wyoming. | Other | 2009-05-19 |  | 2009-09-30 |  | 97770 | 0.530
12495 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | CROOK |  |  | 0904121 | Pavement overlay of 7 miles of I-90 between Sundance and the South Dakota State Line in Crook County. | Pavement Improvement | 2009-05-08 |  | 2010-07-31 |  | 6121771 | 7.000
12496 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | NATRONA |  |  | 1301018 | Drainage repairs of pipe locations on WYO 251 (Casper Mountain Road) in Natrona County. | Other | 2009-05-11 |  | 2009-10-31 |  | 331222.48 | 0.000
12497 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | PARK |  |  | 1501007 | Pavement overlay on approximately 7 miles of WYO 291 between Cody and South Fork in Park County. | Pavement Improvement | 2009-07-14 | 2009-07-14 | 2010-09-15 | 2009-10-21 | 3148344 | 6.660
12498 | Underway | C200 | Highway Infrastructure Investment Grant | WYOMING | SHERIDAN |  |  | 1701013 | Replace right-of-way fence on 2.24 miles of WYO 331 between Sheridan and Beckton in Sheridan County. | Other | 2009-05-11 |  | 2010-10-31 |  | 81527.2 | 2.200
12499 | Awaiting NTP & Not Awarded | C250,C200,C240 | Highway Infrastructure Investment Grant | WYOMING | SWEETWATER |  |  | 1903022 | GRAD, DRAIN, MILL PLANT MIX, PLAC CRUSHED BASE & BIT PAVE SURF, BRIDGE REHAB, SIGN, REMOV & REPLAC OF GRDRL & FENC, & MISC WORK | Pavement Improvement |  |  |  |  | 2461384.93
12500 | Underway | C250,C240 | Highway Infrastructure Investment Grant | WYOMING | WESTON |  |  | 2302011 | Pavement overlay and bridge rehabilitation on WYO 116 north of WYO 450 in Weston County. | Pavement Improvement | 2009-05-06 |  | 2010-10-31 |  | 6252309.28 | 7.290
12501 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | 6598005 | Sidewalk and curb and guter replacement on Harrison Drive in Evanston, Wyoming. | Transportation Enhancements | 2009-08-18 |  | 2010-08-31 |  | 341402 | 0.310
12502 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B045012 | Bridge preventive maintenance at various locations in Wyoming Transportation District 5. | Bridge Improvement | 2009-05-11 | 2009-05-11 | 2009-09-30 | 2010-01-28 | 90753.63
12503 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B082008 | Preventive maintenance (contract patching) and miscellaneous work at various locations in Wyoming Transportation District 2. | Pavement Improvement | 2009-06-24 |  | 2010-09-30 |  | 3291202 | 35.000
12504 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | B085011 | Fence replacement on approximately 11 miles of US 14 east and west of Greybull in Big Horn and Park Counties. | Other | 2009-05-13 |  | 2009-09-30 |  | 460590
12505 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B091005 | Preventive Maintenance, Crack sealing on 85.15 miles of various highways in District 1. | Pavement Improvement | 2009-05-19 |  | 2010-04-30 |  | 569576
12506 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B091008 | Preventive Maintenance, Bituminous Pavement Patches at various locations in District 1. | Pavement Improvement | 2009-05-19 |  | 2009-09-30 |  | 715110
12507 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | B095014 | Preventive maintenance (crack seal) on 125 miles of various roads in Wyoming Transportation District 5. | Pavement Improvement | 2009-05-11 |  | 2010-03-31 |  | 897140
12508 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B151002 | Preventive Maintenance, Chip Seals on various roadways in District 1. | Pavement Improvement | 2009-05-20 |  | 2010-08-31 |  | 3701395
12509 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B152005 | Preventive maintenance (chip seal) and miscellaneous work on approzimately 84 miles of highway in Wyoming Transportation District Two. | Pavement Improvement | 2009-05-11 |  | 2010-08-31 |  | 2529630
12510 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B152006 | Preventive maintenance (crack seal) and miscellaneous work on approximately 367 miles of highway in Wyoming Transporatation District 2. | Pavement Improvement | 2009-08-04 |  | 2010-05-31 |  | 3338509.79
12511 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B152009 | Bridge preventive maintenance and miscellaneous work at various locations in Wyoming Transportation District 2. | Bridge Improvement | 2009-12-03 |  | 2010-10-31 |  | 1267475
12512 | Underway | C220 | Highway Infrastructure Investment Grant | WYOMING | LARAMIE |  |  | I180017 | Install a new pedestrian railing and upgrade the lighting system on I-180 in Cheyenne. | Transportation Enhancements | 2009-05-08 |  | 2009-11-30 |  | 953556 | 0.000
12513 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | PLATTE |  |  | I252157 | Landscaping and miscellaneous work at the Dwyer Junction Rest at the intersection of US 26 and I-25 in Platte County. | Transportation Enhancements | 2009-10-12 |  | 2010-07-31 |  | 144235 | 0.000
12514 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | I801175 | Bridge maintenance and rehabilitation at various location on I-80 in Uinta County. | Bridge Improvement | 2009-08-18 |  | 2010-08-31 |  | 621915 | 0.000
12515 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | I801176 | Preventive pavement maintenance and miscellaneous work on 23.20 miles of I-80 between Carter and LaBarge in Sweetwater and Uinta Counties. | Pavement Improvement | 2009-06-10 |  | 2010-09-30 |  | 2764193
12516 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | I801177 | Preventive pavement maintenance and rehabilitation of 28.10 miles of I-80 beginning at the Utah State Line in Uinta County. | Pavement Improvement | 2009-05-27 |  | 2010-09-30 |  | 10168301 | 28.100
12517 | Underway | C200 | Highway Infrastructure Investment Grant | WYOMING | SWEETWATER |  |  | I802192 | Concrete Pavement Rehabilitation on 15.34 miles of I-80 between Green River and Rock Springs in Sweetwater County. | Pavement Improvement | 2009-06-24 |  | 2010-09-30 |  | 7264004 | 15.370
12518 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | SWEETWATER |  |  | I803140 | Preventive pavement maintenance and miscellaneous work on 33.50 miles of I-80 east of Rock Springs in Sweetwater County. | Pavement Improvement | 2009-05-27 | 2009-05-27 | 2010-09-30 | 2009-09-14 | 3868970 | 34.000
12519 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WYOMING | CARBON |  |  | I804245 | Pavement resurfacing of 6.39 miles of I-80 east of Sinclair in Carbon County. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2010-08-31 | 2009-11-09 | 4888262.2 | 6.229
12520 | Underway | C200,C240 | Highway Infrastructure Investment Grant | WYOMING | ALBANY |  |  | I804250 | Preventive Maintenance, Replace Snow Fence along 23.35 miles of I-80 in Albany and Carbon Counties. | Other | 2009-06-11 |  | 2010-09-15 |  | 5190172 | 23.250
12521 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | CARBON |  |  | I804251 | Pavement resurfacing and bridge repair along 13.04 miles of I-80 near Elk Mountain. | Pavement Improvement | 2009-10-01 |  | 2010-10-31 |  | 2525237 | 5.060
12522 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | ALBANY |  |  | I805165 | Preventive Maintenance, Installation of a friction course on I-80 in Telephone Canyon east of Laramie. | Pavement Improvement | 2009-06-24 |  | 2010-09-30 |  | 2039663 | 5.170
12523 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | JOHNSON |  |  | I902118 | Pavement overlay and surface treatment on 6.2 miles of I-90 between Buffalo and Gillette in Johnson County. | Pavement Improvement | 2009-05-20 | 2009-05-20 | 2010-07-15 | 2010-01-12 | 3541525 | 6.200
12524 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | JOHNSON |  |  | I902119 | Pavement overlay and surface treatment on 6.2 miles of I-90 between Buffalo and Gillette in Johnson County. | Pavement Improvement | 2009-05-20 | 2009-05-20 | 2010-07-15 | 2010-01-12 | 4576050.35 | 8.000
12525 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | CROOK |  |  | I904130 | Pavement preventive maintenance on 12.7 miles of I-90 between Moorcroft and Sundance in Crook County. | Pavement Improvement | 2009-06-10 | 2009-06-10 | 2010-06-30 | 2009-11-30 | 2545187.3 | 12.710
12526 | Underway | C220 | Highway Infrastructure Investment Grant | WYOMING | TETON |  |  | N104084 | Bike path construction along US 26/189/191 north of Jackson, Wyoming. | Transportation Enhancements | 2009-09-28 | 2009-09-28 | 2011-10-30 |  | 1000000 | 1.140
12527 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N202062 | Rest Area rehabilitation of the Sweetwater Station Rest Area between Muddy Gap and Lander. | Other | 2009-06-10 |  | 2010-08-27 |  | 466839
12528 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N202067 | Landscaping in the Lander Highway Park along US 287 in Lander in Fremont County. | Transportation Enhancements |  |  |  |  | 55000 | 0.000
12529 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N203063 | Pavement overlay of approximately 4 miles of US 26 between Riverton and Shoshoni in Fremont County. | Pavement Improvement | 2009-05-20 | 2009-05-20 | 2010-09-30 | 2009-09-11 | 1578018.07 | 4.910
12530 | Underway | C200 | Highway Infrastructure Investment Grant | WYOMING | PARK |  |  | N291036 | Pavement reconstruction and widening of 3.85 miles of US 14A between Cody and Powell in Park County. | Pavement Widening | 2009-06-24 |  | 2010-10-15 |  | 10945393 | 3.620
12531 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N303049 | Rest Area rehabilitation of the Diversion Dam Rest Area between Diversion Dam Junction and Dubois. | Other | 2009-06-10 |  | 2010-08-27 |  | 523873 | 0.000
12532 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N312013 | Safety improvements including slope flattening and guardrail upgrades on 1.48 miles of US 14/16 between Cody and Greybull. | Safety/Traffic Management | 2009-06-10 |  | 2009-10-15 |  | 366818.83 | 1.480
12533 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | HOT SPRINGS |  |  | N331025 | Rest Area rehabilitation of the Gooseberry Creek Rest Area between Thermopolis and Meeteetse. | Other | 2009-06-10 |  | 2010-08-27 |  | 388249 | 0.000
12534 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | NATRONA |  |  | N341105 | Rest Area rehabilitation of the Waltman Rest Area between Casper and Shoshoni. | Other | 2009-06-10 |  | 2010-08-27 |  | 248366 | 0.000
12535 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N342042 | Pavement overlay on 11 miles of US 26 between Casper and Shoshoni in Fremont County. | Pavement Improvement | 2009-08-18 |  | 2010-09-30 |  | 3323603 | 11.000
12536 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345080 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Safety/Traffic Management | 2009-06-11 |  | 2010-10-31 |  | 874253 | 5.099
12537 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345089 | Rest Area rehabilitation of the Greybull Rest Area northwest of Greybull. | Other | 2009-06-10 |  | 2010-08-27 |  | 365613 | 0.000
12538 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345095 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Pavement Improvement | 2009-06-11 |  | 2010-10-31 |  | 1718433 | 4.990
12539 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345096 | Pavement overlay on approximately 6 miles of US 16.20 between Manderson and Basin in Big Horn County. | Pavement Improvement | 2009-08-18 |  | 2010-09-30 |  | 1346404 | 6.049
12540 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345101 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Safety/Traffic Management | 2009-06-11 |  | 2010-10-31 |  | 145171 | 7.000
12541 | Awaiting NTP & Not Awarded | C250,C200,C240 | Highway Infrastructure Investment Grant | WYOMING | WASHAKIE |  |  | N361061 | WORLAND - TEN SLEEP - RATTLESNAKE RIDGE SECTION **RECONSTRUCTION** | Pavement Improvement |  |  |  |  | 5474952
12542 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | NIOBRARA |  |  | N402016 | Pavement widening and overlay on 9.90 miles of US 18/20 between Lusk and Manville in Niobrara County. | Pavement Improvement | 2009-05-27 |  | 2010-10-31 |  | 12017032 | 10.000
12543 | Underway | C220 | Highway Infrastructure Investment Grant | WYOMING | WESTON |  |  | N442066 | Enhancements to US 16 (Upton Main Street) including landscaping, sidewalk, curb and gutter, in Weston County. | Transportation Enhancements | 2009-08-17 |  | 2010-10-31 |  | 150000 | 1.250
12544 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | GOSHEN |  |  | N853084 | Pavement overlay and miscellaneous work on 9.51 miles of US 85 north of Lagrange in Goshen County. | Pavement Improvement | 2009-05-20 |  | 2010-08-31 |  | 3343449 | 9.750
12545 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | NIOBRARA |  |  | N854071 | Pavement overlay and bridge repair of 5 miles of US 85 between Newcastle and Mule Creek Junction in Niobrara County. | Pavement Improvement | 2009-08-04 |  | 2010-10-31 |  | 2021619.73 | 6.650
12546 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | LINCOLN |  |  | P112021 | Construction of retaining walls on US 189 in Diamondville in Lincoln County. | Transportation Enhancements | 2009-05-20 | 2009-05-20 | 2010-07-31 | 2009-12-30 | 250000 | 0.000
12547 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | P142041 | Rest Area rehabilitation of the South Pass Rest Area between Farson and Lander. | Other | 2009-06-10 |  | 2010-08-27 |  | 450785 | 0.000
12548 | Completed | C220,C240 | Highway Infrastructure Investment Grant | WYOMING | CARBON |  |  | P182029 | Pavement rehabilitation and installation of a wildlife underpass on WYO 789 south of Creston Junction. | Pavement Improvement | 2009-06-11 | 2009-06-11 | 2010-10-31 | 2009-12-30 | 1071737 | 4.000
12549 | Underway | C200 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | P341108 | Pavement rehabilitation, sidewalk replacement and curb and gutter replacement, and bridge repair on Casper Streets in Natrona County. | Pavement Improvement | 2009-05-20 |  | 2010-10-31 |  | 2508438 | 1.090
12550 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | P501001 | Pavement overlay and miscellaneous work on 10.45 miles of WYO 89 north of Evanston in Uinta County. | Pavement Improvement | 2009-06-11 |  | 2010-09-30 |  | 3164371.21 | 10.480
12551 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | P511018 | Sidewalk and curb and guter replacement on Harrison Drive in Evanston, Wyoming. | Transportation Enhancements | 2009-08-18 |  | 2010-08-31 |  | 169715 | 0.310
12552 | Underway | C200,C240 | Highway Infrastructure Investment Grant | WYOMING | LARAMIE |  |  | P561028 | Reconstruct West Lincolnway (US-30) in Cheyenne. | Pavement Improvement | 2009-07-20 |  | 2010-10-15 |  | 9289380 | 1.289
12553 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | CONVERSE |  |  | P581025 | Landscaping and miscellaneous work on US 20/26/87 in the City of Douglas. | Transportation Enhancements | 2009-10-12 |  | 2010-07-31 |  | 81558 | 0.759
12554 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | WYOMING | NATRONA |  |  | TL09003 | Construction of an underpass for bikeway/pathway in Casper, Wyoming. | Transportation Enhancements |  |  |  |  | 250000
12555 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | TL09008 | Construction of a travelers information center in Lander, Wyoming in Fremont County. | Transportation Enhancements |  |  |  |  | 350000
12556 | Awaiting NTP But Awarded | C220 | Highway Infrastructure Investment Grant | WYOMING | PARK |  |  | TL09010 | Rehabilitation and landscaping of the Powell Rest Area in Powell, Wyoming in Park County. | Transportation Enhancements |  |  |  |  | 1300000
12557 | Underway | CT10 | Highway Infrastructure Investment Grant | AMERICAN SAMOA | AMERICAN SAMOA |  |  | 0001061 | Resurfacing, Restoration and drainage improvement | Other | 2009-11-16 | 2009-11-16 | 2010-07-13 |  | 4500000
12558 | Awaiting NTP But Awarded | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0002104 | This project replaces culverts at three locations (Sella Bay, Cetti Bay, and Umatac Baseball Field) and installs a concrete safety wall along the side of the road to prevent rocks and debris from fall | Other |  |  |  |  | 1432000
12559 | Awaiting NTP But Awarded | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0004012 | This project is located on Route 4 from Ylig Bridge to Pago Bay. Within the project limits, the road will be repaved and paved shoulders will be installed. | Other |  |  |  |  | 3550000
12560 | Awaiting NTP But Awarded | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0006011 | This project is located at the Masso River Bridge on Assumtion Road near the intersection with Route 6. This project will fix the river embankment and prevent further erosion. | Other |  |  |  |  | 200000
12561 | Awaiting NTP & Not Awarded | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0017102 | This project is located on Route 17 from Route 4 to Route 4A. Within the project limits, the road will be repaved and paved shoulders will be installed. | Other |  |  |  |  | 5200000
12562 | Awaiting NTP But Awarded | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0025101 | This project is located on Route 25 from Bello Road to Route 26. Within the project limits, the road will be repaved and widened to include paved shoulders. For sections of the road, a third lane (t | Other |  |  |  |  | 6000000
12563 | Awaiting NTP & Not Awarded | C490 | Highway Infrastructure Investment Grant | GUAM | GUAM |  |  | JTSS001 | Develop a Sustainable Training Program in highway construction and transportation related fields for Guam. Participants of the Program will receive basic and remedial training, on-the-job training, an | Other |  |  |  |  | 900000
12564 | Awaiting NTP & Not Awarded | C490 | Highway Infrastructure Investment Grant | GUAM | GUAM |  |  | JTSS002 | Provide Pacific Islanders and women specialized training in either highway construction, construction inspection, CADD or other highway careers in order to increase their participation in the Federal- | Other |  |  |  |  | 660000
12565 | Awaiting NTP & Not Awarded | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | TSIS003 | Construction management and inspection services for ARRA projects | Other |  |  |  |  | 1618000
12566 | Underway | CT10 | Highway Infrastructure Investment Grant | N MARIANA | STATEWIDE |  |  | 0031014 | Reconstruction and widening of Route 31, Phase II-A. This project involves reconstructing existing roadway to upgrade the pavement structure. The project includes excavation and backfilling, construct | Other | 2009-11-13 | 2009-11-13 |  |  | 4500000 | 1.500
12567 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  | AGUDILLA |  | 0002040 | This project consists of the replacement of BRIDGE NO. 763 ON PR-2 KM 127.4, over HIGHWAY PR-2R, in the municipality of Aguadilla, PR. | Pavement Improvement | 2009-08-14 | 2009-08-14 | 2010-12-06 |  | 6716258.75 | 0.490
12568 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  | PONCE |  | 0002051 | This project consists of the construction of a new interchange as part of the conversion of PR-2 to expressway. The project is located in the Punto Oro area, Ponce, PR. | Pavement Widening | 2010-02-22 | 2010-02-22 | 2012-08-09 |  | 18131172.55 | 0.618
12569 | Awaiting NTP & Not Awarded | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 0010061 | The project consist in a new bridge construction for PR-10 over Rio Grande de Arecibo and PR-123. The project is in the municipality of Adjuntas. | New Bridge Construction |  |  |  |  | 10601406.94 | 0.162
12570 | Completed | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  | SAN JUAN |  | 0020007 | This project consists of replacing damaged bearing pads under the bridge on PR-20, to raise it to its original grade and elevation. It also includes repairs to the bridge deck. It is located in Guay | Bridge Improvement | 2009-10-30 | 2009-10-30 | 2010-03-18 | 2010-03-30 | 571297 | 0.073
12571 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  | MAYAGUEZ |  | 0102012 | This project consists of reconstructing and widening to four lanes of road PR-64 from PR-2 to PR-102 in "El Mani" sector of the municipality of Mayaguez. | Pavement Widening | 2010-03-26 | 2010-03-26 | 2012-03-14 |  | 10988520.71 | 1.920
12572 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 0173008 | This project consists of the realignment of highway PR-173 at KM 3.0 in the municipality of Cidra. This road was affected by a landslide. | Pavement Improvement | 2009-11-05 | 2009-11-05 | 2010-04-03 |  | 414374.9 | 0.152
12573 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999087 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's North Region Unit I, in | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2011-05-11 |  | 3297142.58 | 9.625
12574 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999088 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region, Unit I in | Bridge Improvement | 2009-08-10 | 2009-08-10 | 2010-08-04 |  | 2480000 | 3.181
12575 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999089 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit I, in t | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-03-09 |  | 3171302.67 | 13.820
12576 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999090 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's West Region Unit I, in t | Pavement Improvement | 2010-04-16 | 2010-04-16 | 2011-04-11 |  | 1890118.15 | 1.758
12577 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999091 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's Metro Region Unit I in | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-01-08 |  | 2433604.7 | 3.900
12578 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999092 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region Unit II in | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-07-25 |  | 3758034.4 | 18.026
12579 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999093 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region Unit III in | Pavement Improvement | 2009-07-13 | 2009-07-13 | 2010-07-07 |  | 3455054.83 | 12.505
12580 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999094 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's North Region Unit II in | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2011-05-04 |  | 3097326.22 | 4.009
12581 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999095 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's North Region Unit III in | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2011-05-04 |  | 4411210.82 | 7.750
12582 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999096 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit II, in | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-03-09 |  | 2856249.25 | 3.622
12583 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999097 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit III in | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-10-19 |  | 2321390 | 7.750
12584 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999098 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit IV in t | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2010-11-09 |  | 1377963.35 | 5.500
12585 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999099 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's West Region Unit II in t | Pavement Improvement | 2010-04-16 | 2010-04-16 | 2011-04-10 |  | 1872894.6 | 1.388
12586 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999100 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's West Region Unit III in | Pavement Improvement | 2010-04-16 | 2010-04-16 | 2011-08-08 |  | 4798316.35 | 4.400
12587 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999101 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's Metro Region Unit II in | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2011-01-18 |  | 2283739 | 10.500
12588 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999102 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's Metro Region Unit III in | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2011-03-19 |  | 3096950 | 9.756
12589 | Awaiting NTP & Not Awarded | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999117 | The project consits in Pavement Rehabilitation and Minor Repairs on Region South Unit IV. Works will be performed on PR-2 from Km. 208.7 to Km. 213.2 in the municipalities of Guayanilla and Peñuelas. | Pavement Improvement |  |  |  |  | 10975672.23 | 2.820
12590 | Underway | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 0032008 | This project proposes to improve pedestrian mobility by constructing sidewalks, installing new crosswalks, new pedestrian crossing signs and installing new roadway striping from the Red Hook Marine Te | Other | 2010-01-11 | 2010-01-11 | 2010-05-21 |  | 1050359.96 | 0.350
12591 | Underway | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 0070011 | This project proposes to repave 2 miles of asphalt roadway along the eastern section of Queen Mary Highway. The project will also make improvements to prevent flooding on the roadway. | New Construction | 2009-10-16 | 2009-10-29 | 2010-10-28 |  | 4859669.4 | 2.050
12592 | Underway | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 0104003 | This project proposes to repave over 2 miles of asphalt roadway. The project will also replace culverts and pipes along the roadway to prevent flooding of the road. The project will install pedestrian | New Construction | 2009-10-05 | 2009-10-05 | 2010-07-02 |  | 4782469 | 2.830
12593 | Awaiting NTP & Not Awarded | C950 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 032M001 | Acquisition of two, 150-300 passenger, Ferry Boats for STT/ STJ Ferry Service | Other |  |  |  |  | 3000000
12594 | Awaiting NTP & Not Awarded | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 9999120 | The replacement of damaged guardrails along Route 66, Melvin Evans Highway, St. Croix, U.S. Virgin Islands | New Construction |  |  |  |  | 819130.75
12595 | Awaiting NTP & Not Awarded | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 9999121 | The replacement of damaged guardrails and signage along Routes 30 & 42 on the islandof St Thomas and along Routes 10 & 107 on the island of St John. | Safety/Traffic Management |  |  |  |  | 951215.89

## Federal Lands
Row | Status | StateProgram | State | State_Code | Division | County | Urban Area | Congressional District | Project Number | Description | FMIS Improvement Category | Proceed Date | Work Start date | Estimated Completion date | Work Complete Date | Recovery Act Obligations
1 | Underway | FEDERAL LANDS | ALABAMA | 1499 | (BIA) IRR | ESCAMBIA | Region S | 1 | S50FER01 | POARCH BAND - JUDSON ROAD | New Construction | 2010-01-28 | 2010-02-24 | 2010-04-30 |  | 220794
2 | Awaiting NTP & Not Awarded | FEDERAL LANDS | ALABAMA | 1499 | (BIA) IRR | ESCAMBIA | Region S | 1 | S50FER11 | POARCH BAND - BUILDING 300 AND 400 | Pavement Improvement |  |  |  |  | 110190
3 | Awaiting NTP & Not Awarded | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | YUKON - KOYUKUK AREA |  | 1 | 000002 | MANLEY VILLAGE COUNCIL - DESIGN & CONSTRUCT TRANSIT SYSTEM FACILITY | New Construction |  |  |  |  | 67465
4 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | MATANUSKA - SUSITNA BOROUGH |  | 1 | 0108102 | CHICKALOON NATIVE VILLAGE - Route 4660 Todd's Road | New Construction | 2009-11-19 | 2010-04-01 | 2011-09-30 | 2011-09-30 | 524420
5 | Underway | FEDERAL LANDS | ALASKA | 1700 | Federal Lands Western Division | ALEUTIANS EAST |  | 00 | 1517020200501 | This project involves upgrading about 4.3 miles of the local street system in the City of King Cove, including a new bridge or fish passage culverts over Ram Creek. The upgrades consist of constructing major traffic safety realignments with increased roa | Pavement Widening | 2009-09-01 | 2009-09-01 |  |  | 1971280
6 | Underway | FEDERAL LANDS | ALASKA | 1700 | Federal Lands Western Division | ALEUTIANS EAST |  | 00 | 1517020200501 | This project involves upgrading about 4.3 miles of the local street system in the City of King Cove, including a new bridge or fish passage culverts over Ram Creek. The upgrades consist of constructing major traffic safety realignments with increased roa | Pavement Widening | 2009-09-01 | 2009-09-01 |  |  | 88020
7 | Underway | FEDERAL LANDS | ALASKA | 1700 | Federal Lands Western Division | PRINCE OF WALES-OUTER KETCHIKAN (CA) |  | 00 | 1517020440008 | Cleanup of acid rock sites that were discoved on a previous project. Project is located near Coffman Cove, AK. | Other | 2009-07-01 | 2009-07-01 | 2010-05-31 |  | 1766392.81
8 | Underway | FEDERAL LANDS | ALASKA | 1700 | Federal Lands Western Division | PRINCE OF WALES-OUTER KETCHIKAN (CA) |  | 00 | 1517020440009 | Cleanup of acid rock sites that were discoved on a previous project. Project is located near Coffman Cove, AK. | Other | 2009-07-01 | 2009-07-01 |  |  | 2253006.19
9 | Underway | FEDERAL LANDS | ALASKA | 1700 | Federal Lands Western Division | DENALI |  | 00 | 1517020701027 | Reconstruct a portion of the Denali Park tour route. Project is located at Denali National Park. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-10-01 |  | 2520061.15
10 | Underway | FEDERAL LANDS | ALASKA | 1700 | Federal Lands Western Division | VALDEZ-CORDOVA (CA) |  | 00 | 1517022003003 | Development of a 12 mile road to the Shotgun Cove ending at Decision Point. Approximately the first 2.7 miles (sections 1 and 2) is a pioneer road. Currently, an environmental assessment is being completed for sections 1 and 2. FY 03 PLHD funds will be | Pavement Improvement | 2009-09-01 | 2009-09-01 |  |  | 3500000
11 | Awaiting NTP & Not Awarded | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | PRINCE OF WALES - OUTER KETCHIKAN (CA) |  | 1 | E00450304 | CRAIG COMMUNITY - HPP - Port Saint Nicholas Road Reconstruction | Other |  |  |  |  | 1000000
12 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | KODIAK ISLAND BOROUGH | Region E | 1 | E01002A1 | AFOGNAK - MUSKOMEE TRAIL IMPROVEMENT/REHAB OF BOAT LANDING DOCK | Other | 2010-04-01 | 2010-04-27 | 2010-12-31 |  | 61532
13 | Awaiting NTP But Awarded | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | ALEUTIAN ISLANDS | Region E | 1 | E01007A1 | AKUTAN - - AKUTAN HARBOR ACCESS ROAD | Other |  |  |  |  | 72777
14 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | VALDEZ - CORDOVA |  | 1 | E0114804 | EYAK VILLAGE - HPP - Whitshed Road-Hayney Bay Subdivision | Pavement Improvement | 2009-12-24 | 2010-02-01 | 2011-05-21 | 2011-05-21 | 1000000
15 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | VALDEZ - CORDOVA |  | 1 | E0114804 | EYAK VILLAGE - WHITSHED ROAD EXTENSION $1,267,760 in RADS | New Construction | 2009-12-24 | 2010-02-01 | 2011-05-21 | 2011-05-21 | 267760
16 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | KODIAK ISLAND BOROUGH | Region E | 1 | E01237A1 | KARLUK - DESIGN OF LANDFILL ROAD (ROUTE 1014) | Other | 2010-04-01 |  | 2010-12-31 |  | 180457
17 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | DILLINGHAM AREA | Region E | 1 | E01259A3 | MANOKOTAK - HEIGHTS ROAD REHABILITATION | Other | 2010-04-09 |  | 2010-12-31 |  | 71418
18 | Awaiting NTP But Awarded | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | MATANUSKA - SUSITNA BOROUGH | Region E | 1 | E01260A1 | KNIK - CHIEF WASILLA WAY ROAD CONSTRUCTION | Other |  |  | 2010-12-31 |  | 114589
19 | Awaiting NTP But Awarded | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | DILLINGHAM AREA | Region E | 1 | E01264A1 | KOKHANUK - MAIN ROAD & OLD SCHOOL ROAD REHABILITATION DESIGN | Other |  |  | 2010-12-15 |  | 50518
20 | Awaiting NTP But Awarded | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | DILLINGHAM AREA | Region E | 1 | E01283A1 | LEVELOCK - FIRST AND SEVENTH STREET DESIGNS | Other |  |  | 2011-03-31 |  | 219607
21 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | KENAI - COOK INLET | Region E | 1 | E01396A1 | PORT GRAHAM - WINDY BAY ROAD PROJECT | Other | 2010-04-02 |  | 2010-09-06 |  | 44626
22 | Awaiting NTP But Awarded | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | BRISTOL BAY BOROUGH | Region E | 1 | E01450A1 | SOUTH NAKNEK - DIAMOND M ROAD | Other |  |  | 2011-06-30 |  | 63760
23 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | KENAI - COOK INLET | Region E | 1 | E01505A2 | TYONEK - ROUTE 2400 - REALIGNMENT & CULVERT RECONSTRUCTION DESIGN | Other | 2010-04-09 | 2010-04-09 | 2010-05-30 |  | 171282
24 | Awaiting NTP But Awarded | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | DILLINGHAM AREA | Region E | 1 | E01506A1 | UGASHIK - UGASHIK ROUTE 0062 & 0063 DESIGN | Other |  |  | 2010-12-31 |  | 81816
25 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | HAINES BOROUGH |  | 1 | E0180001 | CHILKOOT INDIAN ASSOCIATION - CHILKOOT ESTATES | New Construction | 2009-06-17 | 2009-08-24 | 2012-10-31 | 2012-10-31 | 1194726
26 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | BETHEL AREA | Region E | 1 | E02005A1 | AKIACHAK - DESIGN FOR GWEEK ROAD | Other | 2010-04-02 |  | 2010-12-31 |  | 152255
27 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | BETHEL AREA | Region E | 1 | E02006A1 | AKIAK - RECONSTRUCTION & REHABILITATION OF AKIK2 | Other | 2010-04-09 |  | 2010-04-19 |  | 47485
28 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | BETHEL AREA |  | 1 | E0224101 | KASIGLUK TRADITIONAL ELDERS COUNCIL - ARRA Maintenance | Other | 2009-12-24 | 2010-04-01 | 2010-09-30 |  | 8292
29 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | BETHEL AREA |  | 1 | E0224102 | KASIGLUK TRADITIONAL ELDERS COUNCIL - Capital Purchase | Other | 2009-12-24 |  | 2010-09-30 |  | 24879
30 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | BETHEL AREA | Region E | 1 | E02275A1 | KWETHLUK - COMMUNITY BOARDROAD PROJECT | Other | 2010-04-01 |  | 2010-12-31 |  | 54249
31 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | BETHEL AREA |  | 1 | E0249701 | TULUKSAK NATIVE COMMUNITY - Transit Capital Purchase $37,293 in RADS | Other | 2009-12-24 |  | 2010-09-30 |  | 27970
32 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | BETHEL AREA | Region E | 1 | E02841A1 | CHUATHBALUK - LOOP ROAD RECONSTRUCTION | New Construction | 2010-06-04 |  | 2010-12-31 |  | 52098
33 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | KUSKOKWIM |  | 1 | E0302201 | ANVIK VILLAGE - GRAVEL PIT ROAD DESIGN $13,813 in RADS | Other | 2010-01-08 |  | 2010-12-31 |  | 10360
34 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | UPPER YUKON |  | 1 | E0316201 | FORT YUKON TRIBE - RABBIT LINE SUBDIVISION | New Construction | 2009-10-15 | 2009-10-15 |  |  | 121741
35 | Underway | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | YUKON - KOYUKUK AREA | Region E | 1 | E03205A1 | HUGHES - BLUEBERRY ROAD IMPROVEMENTS | Other | 2010-04-01 | 2010-04-01 | 2010-12-31 |  | 66425
36 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | SOUTHEAST FAIRBANKS AREA |  | 1 | E0348301 | TETLIN VILLAGE - ADDITIONAL SPECIAL MAINTENANCE | Other | 2009-12-31 | 2010-02-15 | 2010-06-30 |  | 25000
37 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | SOUTHEAST FAIRBANKS AREA |  | 1 | E0348301 | TETLIN VILLAGE - HPP - Tetlin Road Rehabilitation | New Construction | 2009-12-31 | 2010-02-15 | 2010-06-30 |  | 25000
38 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | SOUTHEAST FAIRBANKS AREA |  | 1 | E0348302 | TETLIN VILLAGE - ARRA TRANSIT PASSENGER SHELTERS | Safety/Traffic Management | 2009-12-31 | 2010-01-19 | 2010-09-30 |  | 90000
39 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | SOUTHEAST FAIRBANKS AREA |  | 1 | E0348302 | TETLIN VILLAGE - HPP - Tetlin Road Rehabilitation | Other | 2009-12-31 | 2010-01-19 | 2010-09-30 |  | 1090000
40 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | SOUTHEAST FAIRBANKS AREA |  | 1 | E0348303 | TETLIN VILLAGE - TETLIN ROAD SAFETY PROJECT | Safety/Traffic Management | 2009-12-31 | 2010-01-19 | 2010-09-30 |  | 113494
41 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | SOUTHEAST FAIRBANKS AREA |  | 1 | E0348303 | TETLIN VILLAGE - HPP - Tetlin Road Rehabilitation | New Construction | 2009-12-31 | 2010-01-19 | 2010-09-30 |  | 113494
42 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | YUKON - KOYUKUK AREA |  | 1 | E0363401 | HEALY LAKE VILLAGE - EROSION / DUST CONTROL | Other | 2010-01-08 |  | 2010-09-30 |  | 150136
43 | Awaiting NTP But Awarded | FEDERAL LANDS | ALASKA | 1499 | (BIA) IRR | NOME AREA |  | 1 | E04167A1 | GAMBLE - GAMBLE COMMUNITY STREET ARRA PROJECT | Other |  |  | 2011-10-15 |  | 6747361
44 | Awaiting NTP But Awarded | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | WRANGELL-PETERSBURG AREA |  | 1 | E0953222 | ANTTC - WRANGELL COOPERATIVE ASSOCIATION - WRANGELL ROAD REHABILITATION | Pavement Improvement |  |  | 2010-09-30 |  | 1182361
45 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | PRINCE OF WALES - OUTER KETCHIKAN (CA) |  | 1 | FY09 IRR 002 | KASAAN , ORGANIZED VILLAGE OF - DOT Facility $1,050,404 in RADS | New Construction | 2010-01-04 |  | 2010-06-01 | 2010-06-01 | 965657
46 | Underway | FEDERAL LANDS | ALASKA | 1462 | (HQFL) IRR | WRANGELL-PETERSBURG AREA |  | 1 | PIA10020 | PETERSBURG INDIAN ASSOCIATION - SIDEWALK RECONS $42,000 in RADS | Other | 2010-04-20 | 2010-04-20 | 2010-05-10 | 2010-05-10 | 724719
47 | Completed | FEDERAL LANDS | ARIZONA | 1600 | Federal Lands Central Division | APACHE |  | 01 | 1516040431003 | Asphalt surfacing of a previously constructed gravel surfaced roadway on Forest Highway 43 from the West Baldy Parking Area (8.5 miles south of State Highway 260) to the intersection with State Highway 261. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-11-01 | 2009-11-01 | 2444472.3
48 | Underway | FEDERAL LANDS | ARIZONA | 1600 | Federal Lands Central Division | APACHE |  | 01 | 1516040431004 | {Project Description} | Pavement Improvement | 2010-01-10 |  | 2010-10-29 |  | 970676.7
49 | Underway | FEDERAL LANDS | ARIZONA | 1600 | Federal Lands Central Division | COCONINO |  | 01 | 1516043050003 | Take the South Rim Visitor Transportation Plan / Environmental Assessment concept forr the Depot Tour Bus Parking area from current approximately 10% design effort to a final 100% plans, specification and estimate (PS&E) set. | Other | 2009-09-16 |  |  |  | 74376.53
50 | Underway | FEDERAL LANDS | ARIZONA | 1600 | Federal Lands Central Division | COCONINO |  | 01 | 1516043050003 | This is a Contract Mod on a NPS project to add train access | Other | 2009-09-16 |  |  |  | 74376.53
51 | Underway | FEDERAL LANDS | ARIZONA | 1600 | Federal Lands Central Division | APACHE |  | 01 | 1516045501002 | Rehabilitate drainage and pavement on the South Rim Drive (route 10) (also known as N7, Navajo route 7) and spur roads off of Route 10 to White House, Spider Rock, Tunnel, and Tsegi overlooks. Spurs paved on the South Rim under the first project will rec | Pavement Improvement | 2010-06-10 |  | 2010-12-03 |  | 427.97
52 | Underway | FEDERAL LANDS | ARIZONA | 1668 | (CFL) BLM | MOHAVE |  | 02 | 1516049300001 | Add a paved right turn lane to US Highway 93 at the driveway to the Monolith Gardens Trailhead | Pavement Improvement | 2010-02-23 |  |  |  | 93294.11
53 | Underway | FEDERAL LANDS | ARIZONA | 1666 | (CFL) NPS | COCONINO |  | 02 | 15K6082008002 | Pavement preservation of the paved surfaces in the North Rim Section of Grand Canyon National Park. The preservation treatments being used are chip seals and modified slurry seals. The project has approximately 430,000 square yards of chip seal and 70,0 | Pavement Improvement | 2010-05-13 |  | 2010-09-03 |  | 1568407
54 | Underway | FEDERAL LANDS | ARIZONA | 1666 | (CFL) NPS | PIMA |  | 01,07,08 | 15L6082008002 | Construct chipseals on all routes within Canyon De Chelly, Chiricahua, Fort Bowie, Organ Pipe, Saguaro, Tonto, and Tumacacori National Monuments. | Pavement Improvement | 2009-09-24 |  | 2009-11-20 |  | 2687747.81
55 | Completed | FEDERAL LANDS | ARIZONA | 1462 | (HQFL) IRR | PINAL |  | 6 | GRIR 103 | GILA RIVER INDIAN COMMUNITY - Vah Ki Rd (IRR 103) Phase I $1,362,231 in RADS | Other | 2010-03-24 | 2010-03-01 | 2010-07-30 | 2010-06-30 | 1365231
56 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | MOHAVE | Region H | 3 | H51A0200 | FORT MOHAVE - PROJECT MOIR 8(1) HULET RD | Other |  |  |  |  | 464980
57 | Underway | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | LA PAZ | Region H | 3 | H51A040 | COLORADO RIVER - PROJECT CRIR 10(1) | Other | 2010-08-02 |  |  |  | 720000
58 | Underway | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | GILA | Region H | 1 | H52A0100 | FORT APACHE - PROJECT FAIR 4(2) | Other | 2010-05-24 | 2010-06-05 | 2010-09-21 |  | 667829.47
59 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | NAVAJO | Region H | 1 | H52A0200 | FORT APACHE - PROJECT FAIR 101(1) - WHITERIVER P.D. STREETS | Other |  |  |  |  | 358004
60 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | NAVAJO | Region H | 1 | H52A0300 | FORT APACHE - PROJECT FAIR 103(1) - DARK SHADOWS AVENUE | Other |  |  |  |  | 256000
61 | Underway | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | PIMA | Region H | 7 | H54A0100 | TOHONA O'ODHAM - PROJECT PIR 232(1) | Other | 2010-06-11 | 2010-06-06 | 2010-10-07 |  | 1414456.84
62 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | PIMA | Region H | 7 | H55A0200 | PASCUA YAQUI - PROJECT PYIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 10000
63 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | PIMA | Region H | 7 | H55A0300 | PASCUA YAQUI - PROJECT PYIR CHIP SEAL NO. 1 | Other |  |  |  |  | 25000
64 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | MARICOPA | Region H | 5 | H55A0400 | FORT MCDOWELL - PROJECT FMIR 102(4) | Other |  |  |  |  | 101296
65 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | GILA | Region H | 6 | H58A0100 | SAN CARLOS - PROJECT SCIR 10(6) | Other |  |  |  |  | 312300
66 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | GRAHAM | Region H | 1 | H58A0200 | SAN CARLOS - PROJECT SCIR 15(2) | Other |  |  |  |  | 312300
67 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | GILA | Region H | 1 | H58A0300 | SAN CARLOS - PROJECT SCIR21(1) | New Construction |  |  |  |  | 105600
68 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | GILA | Region H | 1 | H58A0400 | SAN CARLOS - PROJECT SCIR 26(1) | New Construction |  |  |  |  | 118800
69 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | GRAHAM | Region H | 1 | H58A0500 | SAN CARLOS - PROJECT SCIR 193(1) | Other |  |  |  |  | 473765
70 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | GRAHAM | Region H | 1 | H58A0600 | SAN CARLOS - PROJECT SCIR 194(1) | Other |  |  |  |  | 108900
71 | Completed | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | COCONINO | Region H | 1 | H65A0100 | HOPI - HIR 2(11) | Other | 2010-04-12 | 2010-06-05 | 2010-08-10 | 2010-06-10 | 1074787.5
72 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | MOHAVE | Region H | 3 | H68A0100 | HUALAPAI - PROJECT HUIR 1(31)B | Pavement Improvement |  |  |  |  | 1974024
73 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | GILA | Region H | 4 | H68A0400 | YAVAPAI-TONTO APACHE - PROJECT TAIR SAFETY NO. 1 (STREET LIGHTS) | Safety/Traffic Management |  |  |  |  | 13106
74 | Awaiting NTP But Awarded | FEDERAL LANDS | ARIZONA | 1499 | (BIA) IRR | MOHAVE | Region H | 3 | H69A0300 | KAIBAB - PROJECT CHIP SEAL NO. 2 | Other |  |  |  |  | 84924
75 | Underway | FEDERAL LANDS | ARKANSAS | 1500 | Federal Lands Eastern Division | JOHNSON |  | 03 | 1515050653007 | Route 215 reconstruction | Pavement Improvement | 2010-02-08 | 2010-02-08 |  |  | 807252
76 | Underway | FEDERAL LANDS | CALIFORNIA | 1462 | (HQFL) IRR | DEL NORTE |  | 1 | 52564304 | SMITH RIVER RANCHERIA - NORTH SOUTH INDIAN ROADS | Other | 2010-02-22 | 2010-02-22 | 2011-02-22 | 2011-02-22 | 155339
77 | Underway | FEDERAL LANDS | CALIFORNIA | 1668 | (CFL) BLM | ALPINE |  | 03 | 1516060660001 | Add a new layer of asphalt to the Indian Creek Access Road, Campground Loop and Boat Parking Lot. | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-09-27 |  | 80506.04
78 | Awaiting NTP But Awarded | FEDERAL LANDS | CALIFORNIA | 1668 | (CFL) BLM | ALPINE |  | 03 | 1516060660002 | Construct 200 feet of new roadway access from Airport Road to the trailhead. Construct a new gravel parking lot | New Construction |  |  |  |  | 39247.12
79 | Completed | FEDERAL LANDS | CALIFORNIA | 1600 | Federal Lands Central Division | NEVADA |  | 04 | 1516061231001 | Rehabilitate roadway to a constant 24 feet total width. Spot improvements for drainage and safety. The south project limit begins at the intersection with California State Route (SR) 20, and proceeds northerly 5.3 miles, just before the Town of Washingt | Pavement Improvement | 2009-05-28 | 2009-06-29 | 2009-11-01 | 2009-12-02 | 4651073.51
80 | Completed | FEDERAL LANDS | CALIFORNIA | 1600 | Federal Lands Central Division | EL DORADO |  | 04 | 1516061371004 | Rehabilitate the existing asphalt pavement without modifying the existing roadway bench width on 5.38 miles of the Wentworth Springs Roads (El Dorado County Road 63)from mile post 1.30 to mile post 6.64. The project includes pavement rehabilitation, over | Pavement Improvement | 2009-08-07 | 2009-08-10 | 2009-12-01 | 2009-12-04 | 2498849.27
81 | Underway | FEDERAL LANDS | CALIFORNIA | 1600 | Federal Lands Central Division | MONO |  | 25 | 1516061381001 | The project is to rehabilitate, restore, and resurface the existing roadway pavement. The project work includes minor grading, drainage, pulverization, aggregate base and HACP. Road construction is to be accomplished in two phases with temporary road cl | Pavement Improvement | 2010-06-14 |  | 2010-11-15 |  | 830237.79
82 | Underway | FEDERAL LANDS | CALIFORNIA | 1668 | (CFL) BLM | MONTEREY |  | 17 | 1516061904101 | Add gravel to 5 miles of various roads and replace the bridge over El Toro Creek with a low water crossing within the Ft. Ord Management Area. | Bridge Replacement | 2010-01-21 |  | 2010-08-20 |  | 90687.34
83 | Underway | FEDERAL LANDS | CALIFORNIA | 1668 | (CFL) BLM | MONTEREY |  | 17 | 1516061904301 | Replace 25 culverts in Ft. Ord Management Area | Pavement Improvement | 2010-01-21 |  | 2010-08-20 |  | 34294.66
84 | Underway | FEDERAL LANDS | CALIFORNIA | 1668 | (CFL) BLM | LASSEN |  | 04 | 1516062376001 | Replace the 90 foot portion of the Bizz Johnson Trail Bridge Number 9 that burned in the Devil's Incident Fire in 2000. | Bridge Improvement | 2010-01-21 |  | 2010-10-08 |  | 0
85 | Underway | FEDERAL LANDS | CALIFORNIA | 1666 | (CFL) NPS | SHASTA |  | 02 | 1516063201003 | Project involves pulverizing, hot asphalt concrete pavement, pavement preservation and drainage improvements on 35.6 kilometers of roadway on Lassen Park Road in Lassen Volcanic National Park, Shasta County, California. The primary work consists of 133,3 | Pavement Improvement | 2009-08-26 |  | 2010-11-15 |  | 8686.56
86 | Completed | FEDERAL LANDS | CALIFORNIA | 1600 | Federal Lands Central Division | MARIPOSA |  | 19 | 1516063401501 | Rehabilitate approximately 5.05 miles of roadway, and 2.17 lane miles of paved parking in Yosemite National Park. The project includes the roadway from Chinquapin intersection up to the Badger Pass ski area. Reconstruction and realignment of the Chinqua | Pavement Improvement | 2009-06-02 | 2009-06-03 | 2009-11-30 | 2010-06-10 | 9265616.77
87 | Underway | FEDERAL LANDS | CALIFORNIA | 1600 | Federal Lands Central Division | MARIPOSA |  | 19 | 1516063414004 | The Wawona Road project consists of pulverizing and overlaying 24.4 miles of Wawona Road (Highway 41) through Yosemite National Park. The scope of work includes pulverizing 8" of existing road and overlaying the pulverized materials with 4.5" of asphalt | Pavement Improvement | 2010-05-03 |  | 2009-11-08 |  | 6528563.25
88 | Underway | FEDERAL LANDS | CALIFORNIA | 1600 | Federal Lands Central Division | INYO |  | 25 | 1516063901102 | Rehabilitate roadway pavement and drainage structures on approximately 33.3 mile of the Bonnie Claire Road from mile post 7.4 at the junction of Ubehebe Crater Road to mile post 40.7 at the junction with California State Highway 190. | Pavement Improvement | 2009-07-30 | 2009-08-17 | 2010-05-30 |  | 12548523.42
89 | Completed | FEDERAL LANDS | CALIFORNIA | 1600 | Federal Lands Central Division | DEL NORTE |  | 01 | 1516064710201 | Rehabilitate roadway pavement and drainage structures on approximately 2.18 miles of two-lane roadway between Costal Drive and Klamath Beach Road on Alder Camp Road in Redwood National Park. | Pavement Improvement | 2009-05-13 | 2009-05-18 | 2009-10-30 | 2010-02-02 | 3214936.96
90 | Underway | FEDERAL LANDS | CALIFORNIA | 1668 | (CFL) BLM | LAKE |  | 01 | 1516065403001 | Add gravel and pave 2 miles of Mendo Lake Road. | Pavement Improvement | 2010-01-21 |  | 2010-08-20 |  | 85544.21
91 | Completed | FEDERAL LANDS | CALIFORNIA | 1462 | (HQFL) IRR | HUMBOLT OR SISKIYOU |  | 2 | J5255541 | KARUK TRIBE - KARUK (ANAVKAAM RD) RESERVATION RD | Bridge Replacement | 2010-05-15 | 2010-05-20 | 2010-07-29 | 2010-07-29 | 393642
92 | Underway | FEDERAL LANDS | COLORADO | 1600 | Federal Lands Central Division | MONTEZUMA |  | 03 | 1516080301009 | Rehabilitation of the Main Entrance Road from the park entrance at Highway 160 to the Park Point Overlook. The project also includes adding a chip seal on the Main Entrance Road from the Park Point Overlook (mile post 10.5) to approximately mile post 19. | Pavement Improvement | 2009-06-15 | 2009-06-24 | 2010-08-30 |  | 11957334.51
93 | Awaiting NTP But Awarded | FEDERAL LANDS | COLORADO | 1664 | (CFL) FS | BOULDER |  | 02 | 1516081121001 | Construct a new parking lot for 120 cars, and construct a fee station booth, warming hut, and pit toilet. | New Construction |  |  |  |  | 1551582.95
94 | Underway | FEDERAL LANDS | COLORADO | 1600 | Federal Lands Central Division | CLEAR CREEK |  | 02 | 1516088012023 | Project involves grading, drainage, retaining walls, asphalt surfacing on the 21.2 kilometers of the Guanella Pass Road, Araphaho National Forest, Clear Creek County, Colorado. The primary work consists of 13,900 m2 or roadway excavation, 9,900 m2 or ret | Pavement Widening | 2008-07-07 | 2009-08-06 | 2010-10-01 |  | 4590608.76
95 | Completed | FEDERAL LANDS | COLORADO | 1600 | Federal Lands Central Division | RIO GRANDE |  | 03 | 1516088501002 | Recondition and resurface the existing one-way loop road with aggregate surfacing, formalize existing pullouts, create additional small pullouts where there is room, and perform minor drainage improvements. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-09-01 | 2009-10-31 | 292277.38
96 | Underway | FEDERAL LANDS | COLORADO | 1600 | Federal Lands Central Division | DENVER |  | 01 | 1516350057101 | Design and Environmental services supporting the development of 100% plan sets for the replacement of six small bridges in Cibola National Forest in New Mexico state. Design services are performed in Denver, Colorado. | Other | 2009-05-13 | 2009-05-13 | 2010-03-01 |  | 539949.02
97 | Underway | FEDERAL LANDS | COLORADO | 1600 | Federal Lands Central Division | DENVER |  | 01 | 1516350121009 | Architect/Engineering design services supporting the development of 100% plan set on project NM 12-1(9) and 70% set plan development on NM PFH12-1(10) for the reconstruction and paving of an existing dirt/gravel road in Santa Fe National Forest in New Mex | Other | 2009-06-29 | 2009-06-30 | 2011-09-01 |  | 1138149.98
98 | Underway | FEDERAL LANDS | DISTRICT OF COLUMBIA | 1500 | Federal Lands Eastern Division | DISTRICT OF COLUMBIA |  | 98 | 1515113400014 | Rehabilitate Ohio Drive and Old Constitution Avenue. | Pavement Improvement | 2010-04-12 | 2010-04-12 |  |  | 2305695.5
99 | Awaiting NTP But Awarded | FEDERAL LANDS | DISTRICT OF COLUMBIA | 1500 | Federal Lands Eastern Division | DISTRICT OF COLUMBIA |  | 98 | 1515113400017 | Resurface Madison Drive | Pavement Improvement |  |  |  |  | 1105050.5
100 | Underway | FEDERAL LANDS | IDAHO | 1700 | Federal Lands Western Division | IDAHO |  | 01 | 1517160600005 | Provide for connection between two newly reconstructed segments of road along the Salmon River Road corridor. Project is located near Riggins, ID. | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 5505024
101 | Underway | FEDERAL LANDS | IDAHO | 1764 | (WFL) FS | LEMHI |  | 02 | 1517166030001 | Replace three deficient bridges in the Salmon-Challis NF | Bridge Replacement | 2009-07-01 | 2009-07-01 | 2009-12-06 | 2009-11-23 | 728397.12
102 | Awaiting NTP But Awarded | FEDERAL LANDS | IDAHO | 1499 | (BIA) IRR | BINGHAM | Region P | 2 | P04901R1 | FORT HALL - BENCH / MARSHALL ROAD RECONSTRUCTION | Pavement Improvement |  |  |  |  | 832815
103 | Awaiting NTP But Awarded | FEDERAL LANDS | IDAHO | 1499 | (BIA) IRR | KOOTENAI | Region P | 1 | P05201R1 | COEURD'ALENE - OSPREY ACCESS & RESIDENTIAL STREETS WEST | Other |  |  |  |  | 95150
104 | Awaiting NTP But Awarded | FEDERAL LANDS | IOWA | 1499 | (BIA) IRR | TAMA | Region F | 3 | F51490SA | SAC & FOX TRIBE OF MISSISSIPPI IN IOWA - MESKWAKI ROAD | Other |  |  | 2012-09-30 |  | 101746
105 | Awaiting NTP But Awarded | FEDERAL LANDS | IOWA | 1499 | (BIA) IRR | TAMA | Region F | 3 | F51490SB | SAC & FOX TRIBE OF MISSISSIPPI IN IOWA - RED EARTH ROAD | New Construction |  |  | 2012-09-30 |  | 196000
106 | Awaiting NTP But Awarded | FEDERAL LANDS | IOWA | 1499 | (BIA) IRR | TAMA | Region F | 3 | F51490SC | SAC & FOX TRIBE OF MISSISSIPPI IN IOWA - IRR MAINTENANCE | Other |  |  | 2012-09-30 |  | 99000
107 | Awaiting NTP But Awarded | FEDERAL LANDS | KANSAS | 1499 | (BIA) IRR | DONIPHAN | Region B | 2 | B04R8601 | IOWA TRIBE OF KS & NE - R - SAFETY IMPROVEMENT PROJECT | Safety/Traffic Management |  |  | 2011-12-31 |  | 87962
108 | Awaiting NTP But Awarded | FEDERAL LANDS | KANSAS | 1499 | (BIA) IRR | BROWN | Region B | 2 | B04R8611 | KICKAPOO TRIBE IN KANSAS - DESIGN ROAD 130 | Other |  |  | 2012-09-01 |  | 97624
109 | Underway | FEDERAL LANDS | KANSAS | 1499 | (BIA) IRR | FINNEY | Region B | 2 | B04R8621 | PRAIRIE BAND OF POTAWATOMI R - 126 AND O ROAD | Safety/Traffic Management | 2010-06-18 |  | 2011-12-31 |  | 64296
110 | Underway | FEDERAL LANDS | KANSAS | 1499 | (BIA) IRR | JACKSON | Region B | 2 | B04R8622 | PRAIRIE BAND OF POTAWATOMI - R - 174 RD & H.5 HILL CUT | Safety/Traffic Management | 2010-06-17 |  | 2011-12-31 |  | 169642
111 | Awaiting NTP But Awarded | FEDERAL LANDS | KANSAS | 1499 | (BIA) IRR | BROWN | Region B | 2 | B04R8631 | SAC & FOX OF MISSOURI IN KANSAS - R - CHIP SEAL ROUTE 708 | Other |  |  | 2011-12-31 |  | 35384
112 | Underway | FEDERAL LANDS | LOUISIANA | 1499 | (BIA) IRR | ST. MARY PARISH | Region S | 3 | S5039708 | CHITIMACHA TRIBE - MMR | Other | 2010-03-26 |  |  |  | 966304
113 | Awaiting NTP & Not Awarded | FEDERAL LANDS | LOUISIANA | 1499 | (BIA) IRR | LA SALLE PARISH | Region S | 5 | S5053417 | JENA BAND - MAIN STREET | New Construction |  |  |  |  | 40368
114 | Underway | FEDERAL LANDS | LOUISIANA | 1499 | (BIA) IRR | AVOYELLES PARISH | Region S | 5 | S5053611 | TUNICA-BILOXI INDIAN TRIBE - MULTI-PURPOSE FACILITY PARKING CENTER | New Construction | 2009-12-11 | 2009-12-11 | 2010-09-30 |  | 335512
115 | Underway | FEDERAL LANDS | MAINE | 1499 | (BIA) IRR | AROOSTOOK | Region S | 2 | S5031907 | HOULTON BAND - BIA RT 323 - MALISEET DRIVE | Other | 2009-10-26 | 2009-11-04 | 2010-09-30 |  | 54083
116 | Underway | FEDERAL LANDS | MAINE | 1499 | (BIA) IRR | PENOBSCOT | Region S | 2 | S5051803 | PENOBSCOT TRIBE - ACCESS AND LOOP ROAD | Pavement Improvement | 2009-12-16 |  | 2010-09-30 |  | 428766
117 | Underway | FEDERAL LANDS | MAINE | 1499 | (BIA) IRR | AROOSTOOK | Region S | 2 | S50ARA13 | AROOSTOOK BAND (MICMAC) - SUMMIT DRIVE | New Construction | 2010-03-25 | 2010-03-25 |  |  | 148676
118 | Awaiting NTP But Awarded | FEDERAL LANDS | MAINE | 1499 | (BIA) IRR | HANCOCK | Region S | 2 | S50FER02 | PASSAMAQ. - INDIAN TWP - PIT ROAD | New Construction |  | 2010-07-01 | 2011-09-30 |  | 177347
119 | Awaiting NTP But Awarded | FEDERAL LANDS | MARYLAND | 1500 | Federal Lands Eastern Division | WASHINGTON |  | 06 | 1515243120001 | Mill and overlay approximately 5 miles of tour loop roads within the National Battlefield, including parking areas. Rehabilitate approximately 2 miles of paved walking trails. | Pavement Improvement |  |  |  |  | 2732191.75
120 | Awaiting NTP But Awarded | FEDERAL LANDS | MARYLAND | 1500 | Federal Lands Eastern Division | WASHINGTON |  | 06 | 1515243120001 | This project will add new pavement at the Shull House parking, Maintenance area, replace the asphalt at the Maintenance drive, and surface Piper Lane. | Pavement Improvement |  |  |  |  | 2732191.75
121 | Underway | FEDERAL LANDS | MASSACHUSETTS | 1499 | (BIA) IRR | DUKES | Region S | 10 | S5053003 | WAMPANOAG TRIBE OF GAY HEAD - LORAN STATION ROAD | Other | 2010-04-27 | 2010-04-27 | 2010-12-31 |  | 35060
122 | Awaiting NTP & Not Awarded | FEDERAL LANDS | MASSACHUSETTS | 1499 | (BIA) IRR | BARNSTABLE | Region S | 10 | S50RM350 | MASHPEE WAMPANOAG - MASHPEE WAMPANOAG ROAD MAINTENANCE | Other |  |  |  |  | 116244
123 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | ALGER | Region F | 1 | F60469SC | SAULT STE MARIE BAND OF CHIPPEWA INDIANS - ALGER COUNTY COOP | Pavement Improvement |  |  | 2012-09-30 |  | 105777
124 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | MACKINAC | Region F | 1 | F60469SD | SAULT STE MARIE BAND OF CHIPPEWA INDIANS - MACKINAC TRAIL COOP | Other |  |  | 2012-09-30 |  | 38986
125 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | ALGER | Region F | 1 | F60469SE | SAULT STE MARIE BAND OF CHIPPEWA INDIANS - LEHNEN & CEMETERY ROAD COOP | Pavement Improvement |  |  | 2012-09-30 |  | 444000
126 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | MACKINAC | Region F | 1 | F60469SG | SAULT STE MARIE BAND OF CHIPPEWA INDIANS - CHAMBERS STREET COOP | Pavement Improvement |  |  | 2012-09-30 |  | 41400
127 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | CHIPPEWA | Region F | 1 | F60470SA | BAY MILLS INDIAN COMMUNITY - PLANTATION ROAD | New Construction |  |  | 2012-09-30 |  | 181887
128 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | DELTA | Region F | 1 | F60471SD | HANNAHVILLE INDIAN COMMUNITY - RIDGEVIEW EXTENSION | Pavement Improvement |  | 2010-05-12 | 2012-09-30 |  | 701862
129 | Underway | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | ISABELLA | Region F | 4 | F60472SB | SAGINAW CHIPPEWA INDIAN TRIBE - MISSION ROAD | Pavement Improvement | 2009-09-21 | 2009-08-16 | 2010-12-31 | 2010-12-31 | 540000
130 | Underway | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | ISABELLA | Region F | 4 | F60472SC | SAGINAW CHIPPEWA INDIAN TRIBE - BASELINE ROAD | Pavement Improvement | 2009-09-21 | 2009-08-16 | 2010-12-31 | 2010-12-31 | 270000
131 | Completed | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | GOGEBIC | Region F | 1 | F6047307 | LAC VIEUX DESERT CHIPPEWA INDIANS - RODDIS ROAD | Pavement Improvement | 2009-09-14 | 2009-09-01 | 2009-10-31 | 2009-10-30 | 379000
132 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | GRAND TRAVERSE | Region F | 4 | F60474SA | GRAND TRAVERSE BAND OF OTTAWA - GTB RESORT PHASE 3 | New Construction |  |  | 2012-09-30 |  | 944252
133 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | LEELANAU | Region F | 4 | F60474SE | GRAND TRAVERSE BAND OF OTTAWA - GTB SIDEWALK | New Construction |  |  | 2012-09-30 |  | 1264753
134 | Awaiting NTP & Not Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | GRAND TRAVERSE | Region F | 4 | F60474SI | GRAND TRAVERSE BAND OF OTTAWA - EAST SILVER LAKE ROAD | New Construction |  |  |  |  | 816099
135 | Awaiting NTP & Not Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | GRAND TRAVERSE | Region F | 4 | F60474SJ | GRAND TRAVERSE BAND OF OTTAWA - KEYSTONE ROAD | New Construction |  |  |  |  | 242342
136 | Awaiting NTP & Not Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | GRAND TRAVERSE | Region F | 4 | F60474SL | GRAND TRAVERSE BAND OF OTTAWA - SECOR ROAD | New Construction |  |  |  |  | 235715
137 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | LEELANAU | Region F | 4 | F60474SM | GRAND TRAVERSE BAND OF OTTAWA - ROAD MAINTENANCE ROAD | New Construction |  | 2010-06-24 | 2012-09-30 |  | 90481
138 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | BARAGA | Region F | 1 | F60475SA | KEWEENAW BAY INDIAN COMMUNITY - SKANEE ROAD COOP | Pavement Improvement |  |  | 2012-09-30 |  | 929134
139 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | BERRIEN | Region F | 8 | F60480SC | POKAGON BAND OF POTAWATOMI - MAUDLIN ROAD COOP | Pavement Improvement |  |  | 2012-09-30 |  | 535773
140 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | MASON | Region F | 2 | F60482SC | LITTLE RIVER BAND OF OTTAWA - GOVERNMENT CENTER ROADS | Pavement Improvement |  |  |  | 2010-09-30 | 79978
141 | Underway | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | EMMET | Region F | 1 | F60483SA | LITTLE TRAVERSE BAY BAND OF CHIPPEWA - PLEASANTVIEW ROAD | Pavement Improvement | 2009-12-15 | 2010-05-24 |  | 2012-09-30 | 598660
142 | Underway | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | EMMET | Region F | 1 | F60483SB | LITTLE TRAVERSE BAY BAND OF CHIPPEWA - STATE ROAD | Pavement Improvement | 2009-12-15 | 2010-05-17 |  | 2012-09-30 | 525502
143 | Underway | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | EMMET | Region F | 1 | F60483SD | LITTLE TRAVERSE BAY BAND OF CHIPPEWA - MCDOUGAL ROAD | Pavement Improvement | 2009-12-15 | 2010-05-17 |  | 2012-09-30 | 488579
144 | Awaiting NTP But Awarded | FEDERAL LANDS | MICHIGAN | 1499 | (BIA) IRR | ALLEGAN | Region F | 6 | F60484SB | MATCH-E-BE-NASH-SHE-WISH BAND OF POTAWATOMI - ELDER HOUSING DEV. | New Construction |  |  | 2012-09-30 |  | 36000
145 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | BELTRAMI | Region F | 7 | F52409SI | RED LAKE BAND OF CHIPPEWA INDIANS - JEROME CUTOFF | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2012-09-30 |  | 2629977
146 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | BELTRAMI | Region F | 7 | F52409SJ | RED LAKE BAND OF CHIPPEWA INDIANS - PONEMAH ROAD | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2012-09-30 |  | 83306
147 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | ST. LOUIS | Region F | 8 | F53404SA | BOIS FORTE LAKE SUPERIOR BAND OF CHIPPEWA - TIBBIT'S TRAIL | Pavement Improvement |  |  | 2012-09-30 |  | 195000
148 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | ST. LOUIS | Region F | 8 | F53404SB | BOIS FORTE LAKE SUPERIOR BAND OF CHIPPEWA - DUFFY POINT ROAD | Pavement Improvement |  |  | 2012-09-30 |  | 152000
149 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | ST. LOUIS | Region F | 8 | F53404SC | BOIS FORTE LAKE SUPERIOR BAND OF CHIPPEWA - VILLAGE STREETS | Pavement Improvement |  |  | 2012-09-30 |  | 643300
150 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | ST. LOUIS | Region F | 8 | F53404SD | BOIS FORTE LAKE SUPERIOR BAND OF CHIPPEWA - 25% ROAD MAINTENANCE | Other |  |  | 2012-09-30 |  | 282518
151 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CARLTON | Region F | 8 | F53405SC | FOND DU LAC BAND OF CHIPPEWA INDIANS - MOORHEAD ROAD | Pavement Improvement |  |  | 2012-09-30 |  | 1261448
152 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | COOK | Region F | 8 | F53406SA | GRAND PORTAGE BAND OF CHIPPEWA INDIANS - VILLAGE ROADS | Pavement Improvement |  |  | 2012-09-30 |  | 215000
153 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | COOK | Region F | 8 | F53406SC | GRAND PORTAGE BAND OF CHIPPEWA INDIANS - STEVEN & STORE ROADS | Pavement Improvement |  |  | 2012-09-30 |  | 402887
154 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SA | LEECH LAKE BANDOF CHIPPEWA INDIANS - OAK POINT | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2012-09-30 |  | 2712170
155 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SB | LEECH LAKE BAND OF CHIPPEWA INDIANS - CR 145 | Pavement Improvement |  |  | 2012-09-30 |  | 416828
156 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SC | LEECH LAKE BAND OF CHIPPEWA INDIANS - INGER STREETS | Pavement Improvement | 2010-04-27 | 2010-04-28 | 2012-09-30 |  | 241789
157 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SD | LEECH LAKE BAND OF CHIPPEWA INDIANS - OLD BALL CLUB STREETS | Pavement Improvement | 2010-04-27 | 2010-04-28 | 2012-09-30 |  | 139444
158 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SG | LEECH LAKE BAND OF CHIPPEWA INDIANS - TRIBAL TRACT 33 STREETS | Pavement Improvement | 2010-04-27 | 2010-04-28 | 2012-09-30 |  | 468357
159 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SI | LEECH LAKE BAND OF CHIPPEWA INDIANS - OLD AGENCY ROAD | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2012-09-30 |  | 133713
160 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SJ | LEECH LAKE BAND OF CHIPPEWA INDIANS - CEMETERY ROAD | Pavement Improvement | 2010-04-19 | 2010-04-28 | 2012-09-30 |  | 577960
161 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SK | LEECH LAKE BAND OF CHIPPEWA INDIANS - ONIGUM STREETS | Pavement Improvement | 2010-04-27 | 2010-04-28 | 2012-09-30 |  | 240911
162 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SM | LEECH LAKE BAND OF CHIPPEWA INDIANS - BOY RIVER ROAD & CR 172 | Pavement Improvement | 2010-04-29 | 2010-05-18 | 2012-09-30 |  | 876042
163 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | CASS | Region F | 8 | F53407SN | LEECH LAKE BAND OF CHIPPEWA INDIANS - OTENEAGAN ROAD | Pavement Improvement | 2010-04-27 | 2010-04-28 | 2012-09-30 |  | 248975
164 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | BECKER |  | 7 | F53408SD | WHITE EARTH BAND OF CHIPPEWA INDIANS - REDISCOVERY CENTER ROAD | New Construction | 2010-07-20 | 2010-07-21 | 2012-09-30 |  | 675381
165 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | BECKER |  | 7 | F53408SE | WHITE EARTH BAND OF CHIPPEWA INDIANS - IRR MAINTENANCE | Other | 2010-07-21 | 2010-07-21 | 2012-09-30 |  | 478066
166 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | MAHNOMEN |  | 7 | F53408SF | WHITE EARTH BAND OF CHIPPEWA INDIANS - WHITE EARTH STREETS | Pavement Improvement | 2010-08-02 | 2010-08-03 | 2012-09-30 |  | 597500
167 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | MAHNOMEN |  | 7 | F53408SG | WHITE EARTH BAND OF CHIPPEWA INDIANS - NAYTAHWAUSH STREETS | Pavement Improvement | 2010-08-02 | 2010-08-05 | 2012-09-30 |  | 329500
168 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | MILLE LACS | Region F | 8 | F53410SA | MILLE LACS BAND OF CHIPPEWA INDIANS - WISE OWL | Pavement Improvement |  |  | 2012-09-30 |  | 719910
169 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | YELLOW MEDICINE | Region F | 7 | F57401SC | UPPER SIOUX INDIAN COMMUNITY - NEW WATER SOURCE ROAD | Other |  |  | 2012-09-30 |  | 15000
170 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | YELLOW MEDICINE | Region F | 7 | F57401SF | UPPER SIOUX INDIAN COMMUNITY - MN STATE HWY 67 | Pavement Improvement |  |  | 2010-09-30 |  | 993950
171 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | YELLOW MEDICINE | Region F | 7 | F57401SH | UPPER SIOUX INDIAN COMMUNITY - HAZELWOOD ROAD | Other |  |  | 2012-09-30 |  | 15478
172 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | YELLOW MEDICINE | Region F | 7 | F57401SI | UPPER SIOUX INDIAN COMMUNITY - IRR MAINTENANCE | Other |  |  | 2012-09-30 |  | 341476
173 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | REDWOOD | Region F | 2 | F57402SC | LOWER SIOUX INDIAN COMMUNITY - LIGHTING, LANDSCAPING & SAFETY | Other |  |  | 2012-09-30 |  | 75000
174 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | REDWOOD | Region F | 2 | F57402SC | LOWER SIOUX INDIAN COMMUNITY - LIGHTING, LANDSCAPING & SAFETY | New Construction |  |  | 2012-09-30 |  | 904655
175 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | REDWOOD | Region F | 2 | F57402SD | LOWER SIOUX INDIAN COMMUNITY - IRR MAINTENANCE | Other | 2010-06-30 |  |  |  | 326500
176 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | GOODHUE | Region F | 2 | F57403SA | PRAIRIE ISLAND INDIAN COMMUNITY - HOLMQUIST ROAD | Other |  | 2010-04-05 | 2012-09-30 |  | 25000
177 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | GOODHUE | Region F | 2 | F57403SB | PRAIRIE ISLAND INDIAN COMMUNITY - OTHERDAY & WHIPPLE ROADS | Other |  | 2010-04-05 | 2012-09-30 |  | 20000
178 | Awaiting NTP But Awarded | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | GOODHUE/DAKOTA | Region F | 2 | F57403SE | PRAIRIE ISLAND INDIAN COMMUNITY - PI COMMUNITY STREETS | Other |  | 2010-03-31 | 2012-09-30 |  | 50000
179 | Underway | FEDERAL LANDS | MINNESOTA | 1499 | (BIA) IRR | SCOTT | Region F | 2 | F57411SA | SHAKOPEE MDEWAKANTON SIOUX COMMUNITY - COUNTY ROAD 83 | Pavement Improvement | 2010-03-01 | 2010-04-05 | 2012-09-30 |  | 1104742
180 | Underway | FEDERAL LANDS | MISSISSIPPI | 1500 | Federal Lands Eastern Division | WINSTON |  | 03 | 1515280301002 | Route 954 pavement stabilization | Pavement Improvement | 2010-03-10 | 2010-03-10 |  |  | 430771
181 | Underway | FEDERAL LANDS | MISSISSIPPI | 1500 | Federal Lands Eastern Division | NOXUBEE |  | 03 | 15B5280NXB001 | Resurface Brooksville Road and Section Line Road. | Pavement Improvement | 2009-06-19 | 2009-06-19 | 2011-08-01 |  | 1438282.16
182 | Underway | FEDERAL LANDS | MONTANA | 1700 | Federal Lands Western Division | RAVALLI |  | 00 | 1517300780001 | Preserve 14.513 miles of East Fork Bitterroot Road with HMAC overlay. | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 4682444
183 | Underway | FEDERAL LANDS | MONTANA | 1700 | Federal Lands Western Division | FLATHEAD |  | 00 | 1517302601031 | Reconstruct portion of the Going to the Sun Road in Glacier National Park Phase. | Pavement Improvement | 2009-08-01 | 2009-08-01 | 2011-10-31 |  | 8351171.55
184 | Underway | FEDERAL LANDS | MONTANA | 1700 | Federal Lands Western Division | FLATHEAD |  | 00 | 1517302610023 | Reconstruct portion of the Going to the Sun Road in Glacier National Park Phase. | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2011-07-01 |  | 19229200.32
185 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | GLACIER | Region C | 1 | C51ER006 | BLACKFEET - BOARDING SCHOOL ROAD DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 531024
186 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | GLACIER | Region C | 1 | C51ER008 | BLACKFEET - STARR SCHOOL ROAD DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 916068
187 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | GLACIER | Region C | 1 | C51ER010 | BLACKFEET - AGENCY STREETS DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 184896
188 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | GLACIER | Region C | 1 | C51ER017 | BLACKFEET - BROWNING STREETS I DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 298897
189 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | GLACIER | Region C | 1 | C51ER035 | BLACKFEET - INDUSTRIAL PARK STREETS DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 41167
190 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | GLACIER | Region C | 1 | C51ER041 | BLACKFEET - LAST STARR HOUSING DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 46064
191 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | GLACIER | Region C | 1 | C51ER043 | BLACKFEET - BLACKFOOT STREETS DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 96832
192 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | GLACIER | Region C | 1 | C51ER070 | BLACKFEET - SEVILLE ROAD DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 83053
193 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BIG HORN | Region C | 1 | C52ER014 | CROW - REAL BIRD LOOP | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 141411
194 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BIG HORN | Region C | 1 | C52ER055 | CROW - ST. XAVIER STREETS | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 52120
195 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BIG HORN | Region C | 1 | C52ER088 | CROW - OWL CREEK ROAD | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 347769
196 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BIG HORN | Region C | 1 | C52ER091 | CROW - PRYOR TO ST. XAVIER | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 3007005
197 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BIG HORN | Region C | 1 | C52ER125 | CROW - MULTI-STREET REHAB - LODGEGRASS HOUSING | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 74586
198 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BIG HORN | Region C | 1 | C52ER201 | CROW - MULTI-STREET REHAV - PRYOR STREETS | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 55211
199 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BIG HORN | Region C | 1 | C52ER777 | CROW - GAS CAP ROAD | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 144496
200 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BLAINE | Region C | 1 | C55ER004 | FT BELNAP - AGENCY STREETS DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 286564
201 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BLAINE | Region C | 1 | C55ER006 | FT BELNAP - WHITE BEAR DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 228677
202 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BLAINE | Region C | 1 | C55ER011 | FT BELNAP - LODGEPOLE EAST & WEST DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 824977
203 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BLAINE | Region C | 1 | C55ER021 | FT BELNAP - BEAR BULCH DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 238335
204 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BLAINE | Region C | 1 | C55ER112 | FT BELNAP - LP SOUTH DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 93010
205 | Awaiting NTP But Awarded | FEDERAL LANDS | MONTANA | 1462 | (HQFL) IRR | ROOSEVELT |  | 1 | C5660920 | FORT PECK TRIBE - Route 1 - Box Elder to Blair | Pavement Improvement |  |  |  |  | 3855371
206 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | BIG HORN | Region C | 1 | C57ER005 | NORTHERN CHEYENNE - MUDDY CREEK DIRECT SERVICE CONST. | Pavement Improvement | 2009-09-07 | 2009-09-07 |  | 2010-09-30 | 937453
207 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | ROSEBUD | Region C | 1 | C57ER011 | NORTHERN CHEYENNE - ASHLAND - BIRNEY DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-07 | 2009-09-07 |  | 2010-09-30 | 958004
208 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | ROSEBUD | Region C | 1 | C57ER022 | NORTHERN CHEYENNE - RABBIT TOWN TO MISSION DIR. SER. CONST. | Pavement Improvement | 2009-09-07 | 2009-09-07 |  | 2010-09-30 | 178530
209 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | HILL | Region C | 1 | C59ER001 | ROCKY BOY - MISSION - TAYLOR ROAD | Safety/Traffic Management | 2009-08-14 | 2009-08-14 |  | 2010-09-30 | 115120
210 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | HILL | Region C | 1 | C59ER002 | ROCKY BOY - SANGREY SCHOOL | Safety/Traffic Management | 2009-08-14 | 2009-08-14 |  | 2010-09-30 | 575976
211 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | HILL | Region C | 1 | C59ER101 | ROCKY BOY - ROCKY BOY'S STREEST SAFETY IMPROVEMENT | Safety/Traffic Management | 2009-08-14 | 2009-08-14 |  | 2010-09-30 | 73466
212 | Underway | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | HILL | Region C | 1 | C59ER114 | ROCKY BOY - BEAVER CREEK ROAD | Safety/Traffic Management | 2009-08-14 | 2009-08-14 |  | 2010-09-30 | 453391
213 | Awaiting NTP But Awarded | FEDERAL LANDS | MONTANA | 1499 | (BIA) IRR | LAKE | Region P | 1 | P13002R1 | FLATHEAD - REVAIS CREEK BRIDGE / MAGGIE ASHLEY COURT | Bridge Improvement |  |  |  |  | 388751
214 | Underway | FEDERAL LANDS | NEBRASKA | 1600 | Federal Lands Central Division | SIOUX |  | 06 | 1516310071004 | Preliminary Engineering for a small structure (creek crossing) and resurfacing for approximately 1 mile of roadway. | Other | 2009-09-11 | 2009-09-11 |  |  | 79132
215 | Awaiting NTP & Not Awarded | FEDERAL LANDS | NEBRASKA | 1499 | (BIA) IRR | KNOX | Region A | 3 | A08316ER | PONCA TRIBE - AGENCY PROPERTY ROAD | Other |  |  |  |  | 654216
216 | Completed | FEDERAL LANDS | NEVADA | 1600 | Federal Lands Central Division | WASHOE |  | 02 | 1516320002001 | Construct a left turn lane and pocket and acceleration/deceleration lanes for the Galena Recreation Facilities at approximately mile post 18 on State Highway 28. | Pavement Widening | 2010-05-05 |  | 2010-07-01 | 2010-07-12 | 842787
217 | Underway | FEDERAL LANDS | NEVADA | 1600 | Federal Lands Central Division | CLARK |  | 03 | 1516322800109 | Rehabilitate 17.5 miles of the Northshore Road between mileposts 27.3 to 47.6. The route is entirely within the Lake Mead NRA. Project work includes rehabilitation, restoration, spot reconstruction of 3.3 miles, and resurfacing of the existing roadway, | Pavement Improvement | 2009-11-02 |  | 2010-08-29 |  | 7113052.99
218 | Underway | FEDERAL LANDS | NEVADA | 1600 | Federal Lands Central Division | CLARK |  | 03 | 1516322800109 | Rehabilitate roadway pavement and drainage structures on approximately 17.5 miles of the Northshore Road from the Redstone Parking Area to the North Park Boundary. | Pavement Improvement | 2009-11-02 |  | 2010-08-29 |  | 7113052.99
219 | Underway | FEDERAL LANDS | NEVADA | 1668 | (CFL) BLM | CHURCHILL |  | 02 | 1516323133001 | Pave 1.4 miles of Sand Mountain Access Road. | Pavement Improvement | 2009-12-10 | 2009-12-10 |  |  | 111170.8
220 | Awaiting NTP But Awarded | FEDERAL LANDS | NEVADA | 1499 | (BIA) IRR | CHURCHILL | Region H | 2 | H61A0700 | FALLON - PROJECT FIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 99303
221 | Awaiting NTP But Awarded | FEDERAL LANDS | NEVADA | 1499 | (BIA) IRR | WASHOE | Region H | 2 | H61A0800 | PYRAMID LAKE - PROJECT PLIR 205(1) PELICAN POINT ROAD | Other |  |  |  |  | 120000
222 | Awaiting NTP But Awarded | FEDERAL LANDS | NEVADA | 1499 | (BIA) IRR | WASHOE | Region H | 2 | H61A0900 | PYRAMID LAKE - PROJECT PLIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 130143
223 | Awaiting NTP But Awarded | FEDERAL LANDS | NEVADA | 1499 | (BIA) IRR | NYE | Region H | 2 | H64A0200 | DUCKWATER SHOSHONE TRIBE - PROJECT DWIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 26463
224 | Awaiting NTP But Awarded | FEDERAL LANDS | NEVADA | 1499 | (BIA) IRR | WHITE PINE | Region H | 2 | H64A0300 | ELY SHOSONE TRIBE - PROJECT ELIC SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 10233
225 | Awaiting NTP But Awarded | FEDERAL LANDS | NEVADA | 1499 | (BIA) IRR | CLARK | Region H | 3 | H69A0100 | MOAPA RIVER - PROJECT MIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 16824
226 | Underway | FEDERAL LANDS | NEW MEXICO | 1462 | (HQFL) IRR | SANDOVAL |  |  | 1499 | JEMEZ PUEBLO - SP382 HEAD START ACCESS ROAD | Other | 2010-06-21 | 2010-06-21 | 2010-11-18 | 2010-11-18 | 340468
227 | Completed | FEDERAL LANDS | NEW MEXICO | 1600 | Federal Lands Central Division | SANDOVAL |  | 03 | 1516350121006 | Contract modification to existing project (original project included grading, drainage, surfacing and a new bridge structure) to add roadway drainage improvements to protect the roadway and instream drop-structures to prevent degradation of the stream cha | Other | 2009-06-29 | 2009-06-29 | 2009-07-18 | 2009-07-31 | 700000
228 | Underway | FEDERAL LANDS | NEW MEXICO | 1668 | (CFL) BLM | SANDOVAL |  | 03 | 1516351011001 | Pave 4.69 miles of Tent Rocks Road | Pavement Improvement | 2010-02-23 |  | 2010-10-01 |  | 609760.87
229 | Underway | FEDERAL LANDS | NEW MEXICO | 1666 | (CFL) NPS | SANTA FE |  | 03 | 1516351520001 | Rehabilitate various campgrounds, residential areas, and maintenance locations. Also, improve drainage issues and construction of new sewer lines. | Other | 2010-06-10 |  | 2010-10-01 |  | 59441.14
230 | Awaiting NTP & Not Awarded | FEDERAL LANDS | NEW MEXICO | 1462 | (HQFL) IRR | CIBOLA |  | 2 | 6810E00101 | RAMAH NAVAJO CHAPTER - HPP - MTN. VIEW SUBDIVISION ROAD | Pavement Improvement |  |  |  |  | 1000000
231 | Underway | FEDERAL LANDS | NEW MEXICO | 1462 | (HQFL) IRR | CIBOLA |  | 2 | RN 125 | RAMAH NAVAJO CHAPTER - Veteran's Highway $644,000 in RADS | Other | 2009-05-26 |  | 2009-08-31 |  | 644107
232 | Underway | FEDERAL LANDS | NEW MEXICO | 1462 | (HQFL) IRR | MCKINLEY |  | 3 | Z331 2 2&4 | ZUNI TRIBE - Cedar Street | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2010-10-30 | 2010-10-30 | 856925
233 | Completed | FEDERAL LANDS | NEW YORK | 1499 | (BIA) IRR | FRANKLIN | Region S | 26 | S5030728 | SAINT REGIS MOHAWK TRIBE - IROQUOIS DRIVE | Other | 2010-03-26 | 2010-03-26 | 2010-06-30 | 2010-06-30 | 400719
234 | Awaiting NTP & Not Awarded | FEDERAL LANDS | NEW YORK | 1499 | (BIA) IRR | CATTARAUGUS | Region S | 34 | S50FER04 | CATTARAUGUS - JIMERSON LANE | Other |  |  |  |  | 247033
235 | Awaiting NTP But Awarded | FEDERAL LANDS | NORTH CAROLINA | 1566 | (EFL) NPS | HENDERSON |  | 11 | 1515375140064 | Repairs to Buck Springs Tunnel | Other |  |  |  |  | 368989.18
236 | Underway | FEDERAL LANDS | NORTH CAROLINA | 1500 | Federal Lands Eastern Division | HYDE |  | 03 | 1515370MTK001 | Replace East Canal Bridge & Central Canal Bridge. Repair Entrance Road Bridge. Resurface Lake Landing Road. | Bridge Replacement | 2010-02-15 | 2010-02-15 | 2010-12-01 |  | 856788.2
237 | Underway | FEDERAL LANDS | NORTH CAROLINA | 1500 | Federal Lands Eastern Division | ANSON |  | 00 | 1515370PED001 | Rehabilitate Sullivan Pond Road, Wildlife Road, and Ross Road, plus parking areas. | Pavement Improvement | 2010-03-01 | 2010-03-01 |  |  | 767773.85
238 | Underway | FEDERAL LANDS | NORTH DAKOTA | 1600 | Federal Lands Central Division | MCKENZIE |  | 01 | 1516381701003 | Rehabilitate or chipseal 13.8 miles of the North Unit Scenic Drive of Theodore Roosevelt National Park. The rehabilitation includes full depth reclamation or pulverizing the existing asphalt roadway, resurfacing roadway with 3.5? asphalt overlay, replacin | Pavement Improvement | 2009-06-04 | 2009-06-07 | 2009-10-30 | 2009-11-21 | 7824081.68
239 | Completed | FEDERAL LANDS | NORTH DAKOTA | 1600 | Federal Lands Central Division | WARD |  | 01 | 1516383040111 | Recondition and resurface Route 11, Lower Lake Road, to a uniform 22 feet width and regravel. Additionally, Lower Lake Parking 1 will be regraveled and a quarter mile of the Munch's Coulee Nature Trail will be paved. | Pavement Improvement | 2009-07-06 | 2009-07-28 | 2009-08-01 | 2009-10-02 | 772728.16
240 | Completed | FEDERAL LANDS | NORTH DAKOTA | 1600 | Federal Lands Central Division | MCHENRY |  | 01 | 1516383111201 | Reconstruction of two bridges (Willow Creek and Johnson bridges). One bridge location will include a small parking area adjacent to it for canoe access to the river. | Bridge Replacement | 2009-09-30 |  | 2010-06-30 | 2010-07-09 | 434029.71
241 | Awaiting NTP But Awarded | FEDERAL LANDS | NORTH DAKOTA | 1600 | Federal Lands Central Division | MCHENRY |  | 01 | 1516383111202 | Project begins at the Willow-Upham Road and ends at the intersection of Route 14. The project work consists of the reconstruction of one bridge (Souris River bridge) and 7 low water crossings along this route. | Pavement Improvement |  |  |  |  | 9187.62
242 | Awaiting NTP & Not Awarded | FEDERAL LANDS | NORTH DAKOTA | 1499 | (BIA) IRR | MCKENZIE | Region A | 1 | A04353ER | THREE AFFILIATED TRIBES - ASPHALT PATCH AND CHIP SEAL | Safety/Traffic Management |  |  |  |  | 1016893
243 | Awaiting NTP & Not Awarded | FEDERAL LANDS | NORTH DAKOTA | 1499 | (BIA) IRR | RAMSEY | Region A | 1 | A05660ER | SPIRIT LAKE TRIBE - MULTIROUTE STRIPING | Safety/Traffic Management |  |  |  |  | 49785
244 | Awaiting NTP But Awarded | FEDERAL LANDS | NORTH DAKOTA | 1462 | (HQFL) IRR | ROLETTE |  | 1 | TMBC 0802 | TURTLE MOUNTAIN BAND OF CHIPPEWA INDIANS - Transit Facility | New Construction |  |  |  |  | 1605126
245 | Underway | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | PONTOTOC |  |  | 2401 | CHICKASAW NATION - KULLIHOMA | Pavement Improvement | 2010-09-27 | 2010-09-27 |  | 2011-08-23 | 2450000
246 | Underway | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | PONTOTOC |  |  | 2421 | CHICKASAW NATION - LOVELADY ROAD | Other | 2010-09-07 | 2010-09-07 |  | 2011-07-04 | 2150000
247 | Underway | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | BRYAN |  | 2 | 3808 | CHICKASAW NATION - LEAVENWORTH TRAIL $1,646,042 in RADS | Other | 2010-04-26 | 2010-04-26 | 2011-01-21 |  | 2204947
248 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | CHEROKEE |  | 2 | 090506 | CHEROKEE NATION - Dry Creek Roak | Other |  |  |  |  | 1500000
249 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | POTTAWATOME |  | 4 | 0000408804 | CITIZEN BAND OF POTAWATOMI - GORDON COOPER DRIVE OVERLAY | Pavement Improvement |  |  | 2010-08-31 |  | 1746461
250 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | ADAIR |  | 2 | 000040082807 | CHEROKEE NATION - Greasy Road | Pavement Improvement |  |  |  |  | 1789468
251 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | CHEROKEE |  | 2 | 000040093104 | CHEROKEE NATION - Rice-Woodward Road | Pavement Improvement |  |  |  |  | 3440690
252 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | MAYES |  | 2 | 0616077107 | CHEROKEE NATION - Salina-Kenwood | Other |  |  |  |  | 1980000
253 | Underway | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | SEQUOYAH |  |  | 1608162207 | CHEROKEE NATION - NICUT ROAD (SOUTH) | Other | 2010-07-07 | 2010-07-19 | 2010-10-19 | 2010-10-19 | 911740
254 | Underway | FEDERAL LANDS | OKLAHOMA | 1600 | Federal Lands Central Division | MURRAY |  | 04 | 1516405721502 | Pave 0.87 miles of trails adjacent to Route 215. | Other | 2010-07-14 |  | 2010-10-27 |  | 14010.14
255 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | CUSTER | Region B |  | B05R8012 | CHEYENNE & ARAPAHO TRIBE - IRR ROADWAY DESIGN PROJECTS | Other |  |  | 2011-12-31 |  | 751740
256 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | CADDO | Region B | 6 | B06R8041 | WICHITA AND AFFILIATED TRIBES - R - EAST RIVERSIDE ROAD OVERLAY | Pavement Improvement | 2010-05-17 |  | 2010-09-30 |  | 508857
257 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | CADDO | Region B | 6 | B06R8061 | CADDO NATION - R - PONJO ROAD OVERLAY | Pavement Improvement | 2010-05-25 |  | 2010-09-30 |  | 996390
258 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | COMANCHE | Region B |  | B06R8081 | COMANCHE NATION - EAST CACHE CREEK BRIDGE | Bridge Improvement | 2010-06-30 | 2010-06-30 | 2010-12-27 |  | 745021
259 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | CADDO | Region B | 6 | B06R8091 | APACHE TRIBE OF OKLAHOMA - R - ROAD RESURFACING PROJECT | Pavement Improvement | 2010-05-17 |  | 2010-09-30 |  | 286009
260 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | CADDO | Region B | 6 | B06R8151 | KIOWA TRIBE - TRIBAL COMPLEX ENTRANCE AND PARKING | Other |  |  | 2011-09-30 |  | 205776
261 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | CADDO | Region B | 6 | B06R8152 | KIOWA TRIBE - TAHOE CREEK BRIDGE | Other |  |  |  |  | 489027
262 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | KIOWA | Region B | 3 | B06R8153 | KIOWA OF OKLAHOMA - R - OZARK TRAIL OVERLAY | Pavement Improvement |  |  | 2011-12-31 |  | 414955
263 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | KAY | Region B | 3 | B07R8101 | KAW NATION (KAY COUNTY) - PECAN ROAD | Other | 2010-05-03 |  | 2010-09-30 |  | 798728
264 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | NOBLE | Region B | 5 | B07R8111 | OTOE-MISSOURIA - R - ADJACENT PARKING | Other |  |  | 2011-12-31 |  | 139082
265 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | KAY | Region B | 3 | B07R8131 | PONCA TRIBE OF OKLAHOMA - S STREET RECONSTRUCTION | Other | 2010-05-27 |  | 2010-09-30 |  | 632756
266 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | KAY | Region B | 3 | B07R8141 | TONKAWA TRIBE OF INDIANS - R - GUNN BRIDGE WEST ACCESS ROAD | Other | 2010-05-25 |  | 2010-09-30 |  | 465376
267 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | LINCOLN | Region B |  | B08R8223 | IOWA TRIBE - CHUNA COMMUNITY LOOP ROAD & ROAD 075 OVERLAYS | Pavement Improvement | 2010-05-27 |  | 2010-09-30 |  | 283567
268 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | POTTAWATOME | Region B | 5 | B08R8232 | KICKAPOO TRIBE OF OKLAHOMA - R - HAZEL DELL ROAD OVERLAY | Pavement Improvement | 2010-05-27 |  | 2010-09-30 |  | 577392
269 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | LINCOLN | Region B | 3 | B08R8241 | SAC & FOX NATION - CHAPEL PARKING LOT PROJECT | Other | 2010-05-03 | 2010-05-09 | 2010-10-30 |  | 212626
270 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | LINCOLN | Region B | 3 | B08R8242 | SAC & FOX NATION - TRIBAL CEMETERY ACCESS ROAD PROJECT | Other | 2010-05-03 | 2010-05-09 | 2010-10-30 |  | 523499
271 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | LINCOLN | Region B |  | B08R8243 | SAC & FOX NATION - SPARKS NORTH ACCESS ROAD | Pavement Improvement | 2010-05-27 |  | 2010-09-30 |  | 823806
272 | Underway | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | PAWNEE |  | 3 | FAPBR.CN 037 | PAWNEE NATION OF OKLAHOMA - Black Bear Creek (Skedee Bridge) | Safety/Traffic Management | 2009-12-22 |  |  |  | 649514
273 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | OTTAWA |  | 2 | G04FER07 | QUAPAW TRIBE - S680 ROAD | Other | 2009-12-11 | 2009-12-11 |  |  | 533443
274 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | OTTAWA |  | 2 | G04FER14 | WYANDOTTE - WYANDOTTE ROAD PHASE 2 PART B | Other | 2010-02-18 | 2010-03-31 | 2010-12-31 |  | 222990
275 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | OTTAWA |  | 2 | G04FER22 | OTTAWA TRIBE - ADAWE ROAD | Pavement Improvement |  |  |  |  | 867896
276 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | OTTAWA |  | 2 | G04FER24 | MIAMI - BRIDGE #09369 | Other | 2010-05-17 |  |  |  | 206632
277 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | OTTAWA |  | 2 | G04FER37 | EASTERN SHAWNEE - BIA ROUTE 120 | Other | 2010-05-24 |  |  |  | 103911
278 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | LATIMER |  | 2 | G09FER15 | CHOCTAW NATION - WILBURTON STREETS | Other |  |  |  |  | 643400
279 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | ATOKA |  | 2 | G09FER16 | CHOCTAW NATION - BENTLEY ROAD | Other |  |  |  |  | 2732311
280 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | PUSHMATAHA |  | 2 | G09FER17 | CHOCTAW NATION - COUNCIL HOUSE NORTH | Other |  |  |  |  | 4908720
281 | Awaiting NTP But Awarded | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | SEMINOLE | Region G | 5 | G10FER09 | SEMINOLE NATION - TRANSIT FACILITY | Other |  |  | 2011-09-30 |  | 1400000
282 | Underway | FEDERAL LANDS | OKLAHOMA | 1499 | (BIA) IRR | SEMINOLE | Region G | 5 | G10FER10 | SEMINOLE NATION - NATION'S STOP, ROAD & MARKER SIGNS | Safety/Traffic Management | 2010-03-05 |  |  |  | 222358
283 | Underway | FEDERAL LANDS | OKLAHOMA | 1462 | (HQFL) IRR | OSAGE |  | 3 | ON 1009 | OSAGE TRIBE OF INDIANS OF OKLAHOMA - Prue Road | Pavement Improvement | 2010-04-12 | 2010-05-05 | 2011-10-15 | 2011-05-12 | 4137864
284 | Underway | FEDERAL LANDS | OREGON | 1764 | (WFL) FS | COOS |  | 04 | 1517410330004 | Stablize the road and improve drainage at various locations along a 30 mile segment of the Agness Road located near Gold Beach Oregon. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-08-20 |  | 560362.09
285 | Underway | FEDERAL LANDS | OREGON | 1700 | Federal Lands Western Division | LANE |  | 04 | 1517410470001 | Recondition and Repave the failing pavement surfaced roadway. The project is located near Gold Beach, OR. | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 8304859
286 | Underway | FEDERAL LANDS | OREGON | 1764 | (WFL) FS | COOS |  | 04 | 1517411376001 | Stablize the substructure and repair the superstructure of this bridge over the Upper Chetco River located near Brookings Oregon | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 376434.61
287 | Underway | FEDERAL LANDS | OREGON | 1768 | (WFL) BLM | LANE |  | 04 | 1517412009002 | Replace 11 culverts total on low volume BLM roads, and related road reconstruction at the culvert sites. | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 60.9
288 | Underway | FEDERAL LANDS | OREGON | 1700 | Federal Lands Western Division | WASHINGTON |  | 01 | 1517413001004 | Provide a pervious surface treatment to the entrance road and parking area. The project is located near Tualatin, OR. | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 583602
289 | Awaiting NTP But Awarded | FEDERAL LANDS | OREGON | 1499 | (BIA) IRR | DOUGLAS | Region P | 4 | P01213R1 | COW CREEK - REST AREA | New Construction |  |  |  |  | 236234
290 | Awaiting NTP But Awarded | FEDERAL LANDS | OREGON | 1499 | (BIA) IRR | COOS | Region P | 4 | P01603R1 | COOS TRIBE - MAIN BASE ROAD | Other |  |  |  |  | 86051
291 | Awaiting NTP But Awarded | FEDERAL LANDS | OREGON | 1499 | (BIA) IRR | YAMHILL | Region P | 1 | P01809R1 | GRAND RONDE - FORESTRY WAY / NRD PARKING LOT | Other |  |  |  |  | 509340
292 | Awaiting NTP But Awarded | FEDERAL LANDS | OREGON | 1499 | (BIA) IRR | LINCOLN | Region P | 5 | P01810R1 | SILETZ - HIGHWAY 229 SAFETY PROJECT | Pavement Improvement |  |  |  |  | 293200
293 | Underway | FEDERAL LANDS | OREGON | 1499 | (BIA) IRR | UMATILLA |  | 2 | P07700R | UMATILLA - CAPITOL A.K.A. TI'MINE WAY | New Construction | 2009-09-29 | 2009-10-05 |  |  | 800250
294 | Awaiting NTP But Awarded | FEDERAL LANDS | OREGON | 1499 | (BIA) IRR | JEFFERSON | Region P | 2 | P09111R1 | WARM SPRINGS - WEST HILLS PEDESTRIAN PATH PHASE 1 | Pavement Improvement |  |  |  |  | 372404
295 | Awaiting NTP But Awarded | FEDERAL LANDS | OREGON | 1499 | (BIA) IRR | WASCO | Region P | 2 | P09509R1 | WARM SPRINGS - SIDWALTER FLAT STORM WATER | Pavement Improvement |  |  |  |  | 643879
296 | Awaiting NTP But Awarded | FEDERAL LANDS | PENNSYLVANIA | 1566 | (EFL) NPS | CARBON |  | 11 | 1515420630003 | Repair rock slide with property owned by the National Park Service in the Lehigh Gap area above State Route 248. | Transportation Enhancements |  |  |  |  | 4245997.27
297 | Underway | FEDERAL LANDS | PENNSYLVANIA | 1500 | Federal Lands Eastern Division | PIKE |  | 10 | 1515424320017 | Replacement of Toms Creek Bridge along U.S.Route 209 | Bridge Replacement | 2010-03-01 | 2009-10-01 | 2010-10-01 |  | 2042069.19
298 | Awaiting NTP & Not Awarded | FEDERAL LANDS | PENNSYLVANIA | 1500 | Federal Lands Eastern Division | PIKE |  | 10 | 1515424320021 | Rehabilitation of Raymondskill Bridge along US Route 209 | Bridge Improvement |  |  |  |  | 1380419
299 | Completed | FEDERAL LANDS | PUERTO RICO | 1500 | Federal Lands Eastern Division | RIO GRANDE |  | 00 | 1515720003001 | Repair slide on Route 9966 in the El Yunque National Forest | Pavement Improvement | 2010-01-25 | 2010-01-25 |  | 2010-02-03 | 32883
300 | Completed | FEDERAL LANDS | SOUTH CAROLINA | 1500 | Federal Lands Eastern Division | CLARENDON |  | 06 | 1515450SNT001 | Rehabilitate Center Road, Wildlife Drive, North Loop Spur, and Timber Island Road. | Pavement Improvement | 2009-06-30 | 2009-06-30 | 2010-05-01 | 2009-12-07 | 1304442.75
301 | Underway | FEDERAL LANDS | SOUTH CAROLINA | 1499 | (BIA) IRR | YORK | Region S | 5 | S5053207 | CATAWBA INDIAN NATION - RIVERCREST ROAD | Other | 2010-04-13 | 2010-04-13 | 2011-08-13 |  | 125594
302 | Awaiting NTP But Awarded | FEDERAL LANDS | SOUTH DAKOTA | 1462 | (HQFL) IRR | SHANNON |  | 1 | 0000046 | OGLALA SIOUX TRIBE - BIA Rt. 41 Asphalt | Pavement Improvement |  |  |  |  | 3961018
303 | Underway | FEDERAL LANDS | SOUTH DAKOTA | 1600 | Federal Lands Central Division | PENNINGTON |  | 01 | 1516460171006 | The project provides for pedestrian and bicycle overpasses and associated approaches at two locations on this route to improve pedestrian/ bicycle safety . | Transportation Enhancements | 2010-04-19 |  | 2010-08-16 |  | 595110
304 | Awaiting NTP & Not Awarded | FEDERAL LANDS | SOUTH DAKOTA | 1499 | (BIA) IRR | TODD | Region A | 1 | A07115ER | ROSEBUD SIOUIX TRIBE - SOLDIER CREEK HOUSING STREETS | Pavement Improvement |  |  |  |  | 2314897
305 | Awaiting NTP & Not Awarded | FEDERAL LANDS | SOUTH DAKOTA | 1499 | (BIA) IRR | CHARLES MIX | Region A | 1 | A08351ER | YANKTON SIOUX TRIBE - BIA ROUTE 30 BASE & BLOTTER | Pavement Improvement |  |  |  |  | 952449
306 | Awaiting NTP & Not Awarded | FEDERAL LANDS | SOUTH DAKOTA | 1499 | (BIA) IRR | ROBERTS | Region A | 1 | A09445ER | SISSETON-WAHPETON - BIA 3 BUFFALO LAKE ROAD OVERLAY | Pavement Improvement |  |  |  |  | 943752
307 | Awaiting NTP & Not Awarded | FEDERAL LANDS | SOUTH DAKOTA | 1499 | (BIA) IRR | ROBERTS | Region A | 1 | A09760ER | SISSETON-WAHPETON - PEEVER FLATS ACCESS ROAD | Pavement Improvement |  |  |  |  | 573781
308 | Awaiting NTP But Awarded | FEDERAL LANDS | SOUTH DAKOTA | 1462 | (HQFL) IRR | CORSON |  | 1 | A10-302-3-11 | STANDING ROCK SIOUX TRIBE - Kenel Road Reconstruction | Other |  | 2009-09-22 |  |  | 1169796
309 | Awaiting NTP & Not Awarded | FEDERAL LANDS | SOUTH DAKOTA | 1499 | (BIA) IRR | BUFFALO | Region A | 1 | A14809ER | CROW CREEK SIOUX TRIBE - FT THOMPSON SOUTHEAST | Other |  |  |  |  | 261185
310 | Underway | FEDERAL LANDS | TENNESSEE | 1500 | Federal Lands Eastern Division | BLOUNT |  | 02 | 1515471220011 | Construct Bridge #2 on the Foothills Parkway Section 8E | New Bridge Construction | 2009-05-21 | 2009-05-21 | 2011-12-01 | 2010-01-06 | 25301043.58
311 | Awaiting NTP & Not Awarded | FEDERAL LANDS | TENNESSEE | 1500 | Federal Lands Eastern Division | BLOUNT |  | 02 | 1515471220017 | Construct multiple bridges on the Foothills Parkway Section 8E | New Bridge Construction |  |  |  |  | 7461266.24
312 | Underway | FEDERAL LANDS | TENNESSEE | 1500 | Federal Lands Eastern Division | STEWART |  | 08 | 1515470CRK001 | Rehabilitate seven roads and four parking areas. | Pavement Improvement | 2010-03-16 | 2010-03-16 | 2010-12-01 |  | 871975
313 | Awaiting NTP But Awarded | FEDERAL LANDS | TEXAS | 1666 | (CFL) NPS | BREWSTER |  | 23 | 15C6482010002 | Pavement Preservation at Big Bend NP | Pavement Improvement |  |  |  |  | 29792.94
314 | Completed | FEDERAL LANDS | TEXAS | 1462 | (HQFL) IRR | EL PASO |  | 16 | 6810E00132 01 | YSLETA DEL SUR PUEBLO - FM 258 (SOCORRO RD.) | Safety/Traffic Management | 2010-06-01 | 2010-06-15 | 2010-09-01 | 2010-08-10 | 208525
315 | Awaiting NTP But Awarded | FEDERAL LANDS | TEXAS | 1499 | (BIA) IRR | MAVERICK | Region B | 23 | B00R8261 | KICKAPOO TRADITIONAL TEXAS - R - SUBDIVISION ROAD | New Construction |  |  | 2011-12-31 |  | 76895
316 | Underway | FEDERAL LANDS | TEXAS | 1499 | (BIA) IRR | POLK | Region B | 2 | B00R8301 | ALABAMA-COUSHATTA TEXAS - BLACK LAKE LOOP | Other | 2010-05-17 |  | 2011-12-31 |  | 65321
317 | Completed | FEDERAL LANDS | UTAH | 1600 | Federal Lands Central Division | SEVIER |  | 03 | 1516490391003 | Asphalt surfacing of a previously constructed gravel surfaced roadway on Forest Highway 39 from 5.1 miles south of I-70 from the end of the existing pavement to the Gooseberry Administrative Site. | Pavement Improvement | 2009-06-24 | 2009-07-07 | 2009-09-01 | 2009-11-05 | 1961852
318 | Underway | FEDERAL LANDS | UTAH | 1666 | (CFL) NPS | KANE |  | 02 | 15J6082008002 | Pavement preservation of most paved surfaces in Glen Canyon National Recreation Area. This recreation area lies in Northern Arizona and Southern Utah. The preservation treatments used are chip seals and modified slurry seals. The project has nearly 600 | Pavement Improvement | 2010-04-21 |  | 2010-10-01 |  | 4626753.56
319 | Awaiting NTP But Awarded | FEDERAL LANDS | UTAH | 1499 | (BIA) IRR | UINTAH | Region H | 2 | H62A0200 | UINTAH/OURAY - PROJECT UOIR 47(3) | Other |  |  |  |  | 970000
320 | Completed | FEDERAL LANDS | UTAH | 1499 | (BIA) IRR | UINTAH | Region H | 2 | H62A0300 | UINTAH/OURAY - PROJECT UOIR9061(1) | Other |  |  |  | 2010-05-05 | 407000
321 | Completed | FEDERAL LANDS | UTAH | 1499 | (BIA) IRR | UINTAH | Region H | 2 | H62A0400 | UINTAH/OURAY - PROJECT UOIR 41(1) | Other |  |  |  | 2010-05-05 | 446867
322 | Awaiting NTP But Awarded | FEDERAL LANDS | UTAH | 1499 | (BIA) IRR | IRON | Region H | 1 | H69A0200 | PAIUTE-CEDAR - PROJECT CCIC SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 79471
323 | Awaiting NTP & Not Awarded | FEDERAL LANDS | VERMONT | 1500 | Federal Lands Eastern Division | ADDISON |  | 00 | 1515500141001 | Lincoln Gap Road resurface and replace culverts | Pavement Improvement |  |  |  |  | 112980.8
324 | Underway | FEDERAL LANDS | VIRGIN ISLANDS | 1500 | Federal Lands Eastern Division | ST. JOHN |  | 00 | 1515785360004 | Resurface North Shore Road | Pavement Widening | 2009-09-28 | 2009-09-28 | 2010-12-01 |  | 1397391.4
325 | Awaiting NTP But Awarded | FEDERAL LANDS | VIRGIN ISLANDS | 1500 | Federal Lands Eastern Division | ST. CROIX |  | 00 | 1515780SOP001 | Rehabilitate Tranburg Road | Pavement Improvement |  |  |  |  | 1138738.04
326 | Underway | FEDERAL LANDS | VIRGIN ISLANDS | 1500 | Federal Lands Eastern Division | ST. THOMAS |  | 00 | 151578LONGBAY | Phase 3 of reconstruction and widening of Long Bay Road | Pavement Widening | 2009-11-16 | 2009-11-16 |  |  | 5537155
327 | Underway | FEDERAL LANDS | VIRGINIA | 1500 | Federal Lands Eastern Division | FAIRFAX |  | 08 | 1515513300049 | Rehabilitate Washington Marina Parking Lots and Access Roads. | Pavement Improvement | 2010-06-01 | 2010-06-01 |  |  | 452477
328 | Awaiting NTP & Not Awarded | FEDERAL LANDS | VIRGINIA | 1500 | Federal Lands Eastern Division | ACCOMACK |  | 02 | 1515514190003 | Rehabilitate two bridges on Beach Drive | Bridge Improvement |  |  |  |  | 895000
329 | Underway | FEDERAL LANDS | VIRGINIA | 1500 | Federal Lands Eastern Division | YORK |  | 00 | 1515514290011 | Rehabilitate five bridges | Bridge Improvement | 2009-06-30 | 2009-06-30 |  |  | 165524
330 | Underway | FEDERAL LANDS | VIRGINIA | 1500 | Federal Lands Eastern Division | FAIRFAX |  | 11 | 151551FFXPK05 | Fairfax County Parkway, Phase IV | New Construction | 2009-06-29 | 2009-06-29 | 2011-12-01 |  | 22800000
331 | Underway | FEDERAL LANDS | VIRGINIA | 1500 | Federal Lands Eastern Division | FAIRFAX |  | 11 | 151551FFXPK06 | Fairfax County Parkway, Phase III | New Construction | 2010-01-25 | 2010-01-25 | 2010-01-26 | 2010-01-26 | 22960459
332 | Underway | FEDERAL LANDS | WASHINGTON | 1764 | (WFL) FS | SKAMANIA |  | 03, 04 | 1517532009004 | Design Phase and approval process. Replacing 9 to 12 bridges with fabricatd modular bridges at various sites within the Gifford Pinchot National Forest | Other | 2009-07-01 | 2009-07-01 |  |  | 323343.64
333 | Underway | FEDERAL LANDS | WASHINGTON | 1764 | (WFL) FS | LEWIS |  | 04 | 1517532009005 | Prepare a feasibility study to replace the Jody Mullins Bridge. The bridge provides access to trailheads and other FS?s resources. The Jody Mullins Bridge is located on Milepost 0.6 Forest Road 1270, in the Gifford Pinchot National Forest, | Other | 2009-07-01 | 2009-07-01 |  |  | 40769.09
334 | Underway | FEDERAL LANDS | WASHINGTON | 1764 | (WFL) FS | LEWIS |  | 04 | 1517532009006 | Develop documents to remove the current bridge and replace with a temporary bridge. The temporary bridge will reopen the Skate Creek bridge which currently is closed. | Other | 2009-07-01 | 2009-07-01 |  |  | 94537.09
335 | Underway | FEDERAL LANDS | WASHINGTON | 1700 | Federal Lands Western Division | GRAYS HARBOR |  | 06 | 1517532080002 | Last 7 miles of the reconstruction project for the Grisdale Road. The project is located near Aberdeen, WA. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-11-01 |  | 4446476
336 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | STEVENS | Region P |  | P03602R1 | COLVILLE - GIFFORD FERRY DOCK | Bridge Improvement |  |  |  |  | 1416804.48
337 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | OKANOGAN | Region P |  | P03604R1 | COLVILLE - AGENCY STREETS | Pavement Improvement |  |  |  |  | 1986366
338 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | CLALLAM | Region P | 6 | P06012R1 | QUILEUTE - QUILEUTE CEMETARY ROAD | Pavement Improvement |  |  |  |  | 123312
339 | Underway | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | THURSTON | Region P | 3 | P06013R1 | CHEHALIS - OLD HWY 99 TURN LANE | Other | 2010-02-22 |  |  |  | 212395
340 | Underway | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | MASON | Region P | 6 | P06028R1 | SQAUXIN ISLAND - KLA-CHE-MIN DRIVE IMPROVEMENTS | Pavement Improvement | 2010-07-15 | 2010-07-19 |  | 2010-08-27 | 190755
341 | Underway | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | CLALLAM |  | 6 | P06040R1 | JAMESTOWN S'KLALLAM TRIBE - HIGHWAY 101 GUARDRAILS - ARRA | Safety/Traffic Management | 2010-01-14 | 2010-04-29 |  |  | 92172
342 | Underway | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | MASON |  |  | P06801R1 | SKOKOMISH - T3 BA-DAS PARKWAY | New Construction | 2010-05-21 |  |  |  | 141713
343 | Underway | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | CLALLAM |  | 6 | P06911R1 | LOWER ELWHA - HEALTH CLINIC ACCESS - ARRA | Pavement Improvement | 2010-02-08 | 2010-02-08 |  |  | 107294
344 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | SNOHOMISH | Region P | 2 | P10101R1 | TULALIP - 27TH AVENUE NORTHEAST | Pavement Improvement |  |  |  |  | 1895481
345 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | KITSUP` | Region P | 1 | P10113R2 | PORT GAMBLE - BEAR RIDGE AND LITTLE BOSTON ROADS | Other |  |  |  |  | 132048
346 | Underway | FEDERAL LANDS | WASHINGTON | 1462 | (HQFL) IRR | SNOHOMISH |  | 2 | P10145R1 | STILLAGUAMISH TRIBE - TRANSIT CAPITAL ACQUISITION | Safety/Traffic Management | 2010-02-23 | 2010-03-15 |  |  | 220000
347 | Underway | FEDERAL LANDS | WASHINGTON | 1462 | (HQFL) IRR | SNOHOMISH |  | 2 | P10146R1 | STILLAGUAMISH TRIBE - CAPITAL ACQUISITION | Safety/Traffic Management | 2010-02-23 | 2010-03-15 |  | 2010-04-29 | 45000
348 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | SKAGIT | Region P | 2 | P10265R1 | SWINOMISH - SAHALIE DRIVE DRAINAGE AND ROAD IMPROVEMENT | Pavement Improvement |  |  |  |  | 446802
349 | Underway | FEDERAL LANDS | WASHINGTON | 1462 | (HQFL) IRR | WHATCOM |  | 2 | P10401R1 | LUMMI - ROBERTSON ROAD | Safety/Traffic Management | 2010-05-14 | 2010-08-01 | 2010-09-30 |  | 192005
350 | Underway | FEDERAL LANDS | WASHINGTON | 1462 | (HQFL) IRR | WHATCOM |  | 2 | P10402R1 | LUMMI - BLACKHAWK WAY PEDESTRIAN PATH | Safety/Traffic Management | 2010-05-14 | 2010-06-14 | 2010-09-30 |  | 100000
351 | Underway | FEDERAL LANDS | WASHINGTON | 1462 | (HQFL) IRR | WHATCOM |  | 2 | P10403R1 | LUMMI - KWINA ROAD PEDESTRIAN PATH | Safety/Traffic Management | 2010-05-14 | 2010-05-20 | 2010-07-30 |  | 120000
352 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | PIERCE | Region P | 8 | P10801R1 | PUYALLUP - EAST GRANDVIEW AVENUE | Pavement Improvement |  |  |  |  | 810616
353 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | YAKIMA | Region P | 4 | P11313R1 | YAKAMA - SIGNAL PEAK ROAD AND DRY LOGY ROAD | Pavement Improvement |  |  |  |  | 801554
354 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | PEND OREILLE | Region P | 5 | P12011R1 | KALISPEL - POW WOW ROAD HMA-0002 | Pavement Improvement |  |  |  |  | 42474
355 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | STEVENS | Region P | 5 | P12108R1 | SPOKANE - CHILD DEVELOPMENT CENTER ROAD | Pavement Improvement |  |  |  |  | 142519
356 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | STEVENS | Region P | 5 | P12111R1 | SPOKANE - FORD CLUSTER | Pavement Improvement |  |  |  |  | 534668
357 | Awaiting NTP But Awarded | FEDERAL LANDS | WASHINGTON | 1499 | (BIA) IRR | CLALLAM | Region P | 6 | P16500R1 | MAKAH - BAY VIEW AVENUE GUARDRAIL REPLACEMENT | Safety/Traffic Management |  |  |  |  | 286893
358 | Underway | FEDERAL LANDS | WEST VIRGINIA | 1500 | Federal Lands Eastern Division | PENDLETON |  | 02 | 1515540972001 | Smoke Hole Road paving | Pavement Improvement | 2010-04-01 | 2010-04-01 |  |  | 354775.79
359 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | ASHLAND | Region F | 7 | F55430SA | BAD RIVER BAND OF CHIPPEWA INDIANS - IRR MAINTENANCE | Other |  |  | 2012-09-30 |  | 150000
360 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | ASHLAND | Region F | 7 | F55430SB | BAD RIVER BAND OF CHIPPEWA INDIANS - CHIP SEAL PROJECT | Pavement Improvement |  |  | 2012-09-30 |  | 150813
361 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | ASHLAND | Region F | 7 | F55430SE | BAD RIVER BAND OF CHIPPEWA INDIANS - IRR TRANSIT | Safety/Traffic Management |  |  | 2012-09-30 |  | 97000
362 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | ASHLAND | Region F | 7 | F55430SF | BAD RIVER BAND OF CHIPPEWA INDIANS - ACKLEY ROAD | New Construction |  |  | 2012-09-30 |  | 103013
363 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | ASHLAND | Region F | 7 | F55430SI | BAD RIVER BAND OF CHIPPEWA INDIANS - MCDONALD ROAD | New Construction |  |  | 2012-09-30 |  | 130000
364 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | SAWYER | Region F | 7 | F55431SD | LAC COURTE OREILLES - SUMMIT ROAD | Pavement Improvement |  |  | 2012-06-30 |  | 468073
365 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | SAWYER | Region F | 7 | F55431SH | LAC COURTE OREILLES - IRR MAINTENANCE | Other |  |  | 2010-09-30 |  | 154000
366 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | VILAS | Region F | 8 | F55432SB | LAC DU FLAMBEAU CHIPPEWA - TREE HAVEN LANE | Pavement Improvement |  | 2010-06-21 | 2012-09-30 |  | 368687
367 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | VILAS | Region F | 8 | F55432SD | LAC DU FLAMBEAU CHIPPEWA - LITTLE PINES | Other |  | 2010-06-21 | 2012-09-30 |  | 427000
368 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | VILAS | Region F | 8 | F55432SE | LAC DU FLAMBEAU CHIPPEWA - WEST POKAGAMA ROAD | Pavement Improvement |  | 2010-06-21 | 2012-09-30 |  | 189446
369 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | VILAS | Region F | 8 | F55432SG | LAC DU FLAMBEAU CHIPPEWA - LONG'S POINT | Other |  | 2010-06-21 | 2012-09-30 |  | 211089
370 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | VILAS | Region F | 8 | F55432SH | LAC DU FLAMBEAU CHIPPEWA - OBERLAND ROAD | Other |  | 2010-06-21 | 2012-09-30 |  | 240500
371 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | VILAS | Region F | 8 | F55432SI | LAC DU FLAMBEAU CHIPPEWA - COUNTY D | Other |  | 2010-06-21 | 2012-09-30 |  | 282000
372 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | OUTAGAMIE | Region F | 8 | F55433SD | ONEIDA INDIAN TRIBE - CTH U COOP | Other |  |  |  |  | 65000
373 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | OUTAGAMIE | Region F | 8 | F55433SG | ONEIDA INDIAN TRIBE - ROLLING HILLS SUBDIVISION | Other |  | 2010-06-01 | 2012-09-30 |  | 70000
374 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | OUTAGAMIE | Region F | 8 | F55433SG | ONEIDA INDIAN TRIBE - ROLLING HILLS SUBDIVISION | New Construction |  | 2010-06-01 | 2012-09-30 |  | 677629
375 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | FOREST | Region F | 8 | F55434SA | FOREST COUNTY POTAWATOMI COMMUNITY - LOIS CROWE | Pavement Improvement |  | 2010-06-01 | 2012-09-30 |  | 259383
376 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | FOREST | Region F | 8 | F55434SD | FOREST COUNTY POTAWATOMI COMMUNITY - BLACKWELL SUBDIVISION | Other |  | 2010-06-01 | 2012-09-30 |  | 89095
377 | Underway | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | BAYFIELD | Region F | 7 | F55435SB | RED CLIFF BAND OF CHIPPEWA - BLUEBERRY ROAD | New Construction | 2010-02-24 | 2010-03-01 | 2010-04-30 |  | 90000
378 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | BAYFIELD | Region F | 7 | F55435SD | RED CLIFF BAND OF CHIPPEWA - IRR MAINTENANCE | Other |  |  | 2010-09-30 |  | 127263
379 | Underway | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | BURNETT | Region F | 7 | F55436SA | ST. CROIX TRIBAL COUNCIL - EAGLE FEATHER ROAD | Pavement Improvement | 2010-06-09 | 2010-06-16 | 2010-09-30 |  | 290628
380 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | FOREST | Region F | 8 | F55437SD | SOKAOGON CHIPPEWA COMMUNITY - SAND LAKE ROAD | New Construction |  | 2010-01-29 | 2010-09-30 |  | 94949
381 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | FOREST | Region F | 8 | F55437SE | SOKAOGON CHIPPEWA COMMUNITY - IRR MAINTENANCE | Other |  | 2010-01-29 | 2012-09-30 |  | 31500
382 | Underway | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | SHAWANO | Region F | 8 | F55438SD | STOCKBRIDGE MUNSEE COMMUNITY - CAMP 14 ROAD | Pavement Improvement | 2010-05-24 | 2010-06-01 | 2012-09-30 |  | 738842
383 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | WOOD | Region F | 7 | F55439SP | HO-CHUNK NATION - CTH G COOP | Pavement Improvement |  |  | 2012-09-30 |  | 3500000
384 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | JACKSON | Region F | 3 | F55439SQ | HO-CHUNK NATION - BROCKWAY ROAD | Pavement Improvement |  |  | 2012-09-30 |  | 944823
385 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | JACKSON | Region F | 3 | F55439SR | HO-CHUNK NATION - WEST BAUER ROAD | Other |  |  | 2012-09-30 |  | 25000
386 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | MENOMINEE | Region F | 8 | F58440SA | MENOMINEE INDIAN TRIBE - UPPER BASS LAKE ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 7000
387 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | MENOMINEE | Region F | 8 | F58440SB | MENOMINEE INDIAN TRIBE - COUNTY B ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 10000
388 | Underway | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | MENOMINEE | Region F | 8 | F58440SC | MENOMINEE INDIAN TRIBE - GO AROUND ROAD | Pavement Improvement | 2010-06-24 | 2010-06-01 | 2012-09-30 |  | 1033013
389 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | MENOMINEE | Region F | 8 | F58440SD | MENOMINEE INDIAN TRIBE - WEST BRANCH ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 18000
390 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | MENOMINEE | Region F | 8 | F58440SE | MENOMINEE INDIAN TRIBE - BEAR TRAP FALLS ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 10000
391 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | MENOMINEE | Region F | 8 | F58440SH | MENOMINEE INDIAN TRIBE - IRR MAINTENANCE | Other |  | 2010-08-15 | 2012-09-30 |  | 361371
392 | Awaiting NTP But Awarded | FEDERAL LANDS | WISCONSIN | 1499 | (BIA) IRR | MENOMINEE | Region F | 8 | F58440SI | MENOMINEE INDIAN TRIBE - PONFIL ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 12000
393 | Completed | FEDERAL LANDS | WYOMING | 1600 | Federal Lands Central Division | FREMONT |  | 01 | 1516560231003 | Recondition the existing aggregate surfacing and roadbed by scarifying and reshaping to provide for consistent cross slopes and width. The roadway will then be resurfaced with a new aggregate surface course. | Pavement Improvement | 2009-09-09 | 2009-08-19 | 2009-10-31 | 2009-10-31 | 1239408.75
394 | Underway | FEDERAL LANDS | WYOMING | 1600 | Federal Lands Central Division | CARBON |  | 01 | 1516560261901 | Reconstruction of Wyoming State Route 71, by grading, draining, and paving along the existing alignment to facilitate installation of 2 drainage structures. | Pavement Improvement | 2009-06-30 |  | 2009-10-01 |  | 777995.01
395 | Awaiting NTP But Awarded | FEDERAL LANDS | WYOMING | 1668 | (CFL) BLM | WASHAKIE |  | 01 | 1516561435001 | Construct gravel surfacing on HU Clarks Fork, HU Nowater Road, and HU 2 Mile Hill Roads. | Pavement Improvement |  |  |  |  | 6168.94
396 | Underway | FEDERAL LANDS | WYOMING | 1668 | (CFL) BLM | FREMONT |  | 01 | 1516562302001 | Construct gravel surfacing on Hudson Atlantic Road. | Pavement Improvement | 2009-09-30 |  | 2010-06-30 |  | 1208507.55
397 | Completed | FEDERAL LANDS | WYOMING | 1668 | (CFL) BLM | CARBON |  | 01 | 1516563301001 | Construct gravel surfacing on Bridger Pass and Barrel Springs Roads. | Pavement Improvement | 2009-09-14 | 2009-09-15 | 2009-12-01 | 2009-11-14 | 1565391.07
398 | Underway | FEDERAL LANDS | WYOMING | 1668 | (CFL) BLM | SWEETWATER |  | 01 | 1516564115001 | Construct gravel surfacing on Sand Dunes Recreation Site and White Mountain Petroglphs Roads. | Pavement Improvement | 2010-02-08 |  | 2010-05-30 |  | 322008.92
399 | Underway | FEDERAL LANDS | WYOMING | 1668 | (CFL) BLM | SUBLETTE |  | 01 | 1516565201001 | Construct gravel surfacing on Upper Green and Scab Creek Roads. | Pavement Improvement | 2010-05-28 |  | 2010-09-15 |  | 639691.33
400 | Underway | FEDERAL LANDS | WYOMING | 1700 | Federal Lands Western Division | TETON |  | 00 | 1517561601104 | Repair of eight miles of the Teton Park Road from Spalding Bay to Jackson Lake Junction and repair Signal Mountain Marina Road | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-08-20 |  | 4046973.85
401 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER005 | WIND RIVER - SHAYO LANE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 51194
402 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER015 | WIND RIVER - RAY LAKE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 123468
403 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER016 | WIND RIVER - TROSPER LANE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 233781
404 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER027 | WIND RIVER - OLD WIND RIVER HIGHWAY | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 179818
405 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER028 | WIND RIVER - GOES IN LODGE ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 243359
406 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER049 | WIND RIVER - C'HAIR LANE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 113936
407 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER075 | WIND RIVER - MISSION ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 150061
408 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER077 | WIND RIVER - BEHAN ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 40153
409 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER101 | WIND RIVER - MAIL CAMP ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 1574338
410 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER116 | WIND RIVER - AGENCY STREETS - MULTI ROUTE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 187307
411 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER211 | WIND RIVER - LEFTHAND DITCH ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 393484
412 | Underway | FEDERAL LANDS | WYOMING | 1499 | (BIA) IRR | FREMONT | Region C | 1 | C58ER805 | WIND RIVER - BIA 8050 GIVENS ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 133725

## TIGER 1
Row | Status | Program Code | StateProgram | State | Project# | State Project # | Project Description | Improvement Category | Proceed Date | Work Start date | Estimated Completion date | Work Complete Date | Recovery Act Obligations | Transaction Date
1 | Awaiting NTP & Not Awarded | CTDG | TIGER 1 | COLORADO | 0361098 | '18063' | US 36 CORRIDOR-TRAFFIC AND REVENUE STUDY AND TIFIA RELATED WORK | Other |  |  |  |  | 900000 | 2010-08-16
2 | Awaiting NTP & Not Awarded | CTDG | TIGER 1 | ILLINOIS | 0020054 | 'C-20-045-11' | Construction on CREATE Project B-2 Plan No. B2-UP-TXB-002-AT-BD/Segment 1 Bid Work | Other |  |  |  |  | 18815991 | 2010-08-04
3 | Awaiting NTP & Not Awarded | CTDG | TIGER 1 | ILLINOIS | 0020055 | 'C-20-046-11' | Construction on CREATE Project B-4,B-5 Plan No. B4B5-IHB-TSX-002-T-FA/RR Force Account Work | Other |  |  |  |  | 11696542 | 2010-06-29
4 | Awaiting NTP & Not Awarded | CTDG | TIGER 1 | INDIANA | 0902256 | '0902256' | CORRIDOR 397, US 421, REPLACE SUPERSTRUCTURE, MILTON-MADISON BRIDGE PROJECT, JEFFERSON COUNTY, IB-33023 | Bridge Replacement |  |  |  |  | 10000000 | 2010-07-13
5 | Awaiting NTP & Not Awarded | CTDG | TIGER 1 | KENTUCKY | 4201069 | '05-00135.80' | Replace the US 421 bridge over the Ohio River between Milton, KY and Madison, IN-Grade, drain, and surface for bridge and approach | Bridge Replacement |  |  |  |  | 10000000 | 2010-07-15
6 | Awaiting NTP & Not Awarded | CTDG | TIGER 1 | Montana | *DTFH61-10-G-00002 |  | Lake County MT | Other
7 | Awaiting NTP & Not Awarded | CTDG | TIGER 1 | Montana | *DTFH61-10-G-00009 |  | City of Whitefish MT | Other
8 | Underway | CTDG | TIGER 1 | NORTH CAROLINA | 0853197 | '34156.3.ST2','34156.3.GV3' | I-85 from North of SR 2120(Long Ferry Rd,exit 81) Rowan County-North of NC 150 Davidson County | Pavement Improvement | 2010-05-31 |  | 2013-01-26 |  | 10000000 | 2010-05-14
9 | Underway | CTDG | TIGER 1 | SOUTH DAKOTA | 0018170 | '02KH' | US18-FM Oglala to Pine Ridge; Gradeing, Structure Replacement & Interim Surfacing; Roadway Lighting, Sidewalk, Curb & Gutter..... | Other | 2010-05-14 |  | 2011-07-29 |  | 10000000 | 2010-06-17
10 | Awaiting NTP But Awarded | CTDG | TIGER 1 | WASHINGTON | 0395091 | '00CNA','00PC','600001A' | ARRA - TIGER - SR395 / NORTH SPOKANE CORRIDOR, FREYA TO FARWELL - SB. SR395-24.86 TO 28.49 MILES SOUTHEAST OF JUNCTION SR292. | New Construction |  | 2010-08-30 | 2012-06-29 | 2012-06-29 | 35000000 | 2010-05-27
11 | Underway | CTDG | TIGER 1 | WASHINGTON | 9999580 | ' TIGERHLPCNA','SEA-90' | TIGER - Seattle, S. Lake Union Mercer Corridor FROM:Fairview Ave N TO:Dexter Ave N LEN: 2.000MI | Other | 2010-08-09 |  |  |  | 30000000 | 2010-06-10
12 | Awaiting NTP But Awarded | CTDG | TIGER 1 | WYOMING | HPP0416 | 'HPP0416' | RECONSTRUCTION OF 2.92KM OF BEARTOOTH HWY (US212) BEARTOOTH LAKE OUTLET BRIDGE TO BEARTOOTH LAKE CAMPGROUND | Other |  |  |  |  | 6000000
* Locally administered LPA project - not in Fiscal Management Information System (FMIS).