10844 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | LAWRENCE |  | 04 | 0006070 | This project located on SR-6 FROM BUSBY ROAD TO LEOMA will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of th | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-08-31 | 1851309.86 | 5.000
10845 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | LAWRENCE |  | 04 | 0006072 | This project located on SR-6 FROM LAWRENCEBURG TO ALEXANDER SPRINGS ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ex | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-30 | 1876716.43 | 6.800
10846 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 0006075 | This project is for the construction of a median and addition of roadway lighting on SR-6 (West Main Street) from the Davidson County line to New Shackle Island Road in Hendersonville. | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2011-03-06 |  | 873795 | 4.260
10847 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | GILES |  | 04 | 0007020 | This project located on SR-7 FROM POLLY ROAD TO SR-15 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of th | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 846252.27 | 4.600
10848 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MAURY |  | 04 | 0007021 | This project located on SR-7 FROM GILES COUNTY LINE TO SOUTH OF SR-50 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exten | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 1329965.15 | 11.600
10849 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 0008041 | This project is for improvements to the intersection of SR-8 (Ringgold Road) at Camp Jordan Parkway and including traffic signals | Safety/Traffic Management | 2009-05-14 | 2009-05-14 | 2010-01-15 | 2009-12-31 | 134390 | 0.000
10850 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 0008042 | This project is for the installation of traffic signals on SR-8 (Ridgeway Avenue) at the Intersection at Palisades Drive/Mississippi Avenue in Signal Mountain | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2011-04-30 |  | 107622 | 0.000
10851 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 0008043 | This project is for the construction of bicycle lanes on SR-8/Ringgold Road in East Ridge | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-22 | 2010-11-24 | 126998.19 | 0.000
10852 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | COCKE |  | 01 | 0009059 | This project located on SR-9 FROM SR-35 TO WHITE OAK AVENUE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-11-15 | 2009-09-30 | 1797004.68 | 4.200
10853 | Underway | C200 | Highway Infrastructure Investment Grant | TENNESSEE | CAMPBELL |  | 04 | 0009060 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-9 with a new BRIDGE OVER CSX RAILROAD IN LAFOLLETTE to serve the community for the next | Bridge Replacement | 2009-05-15 | 2009-05-15 | 2011-10-31 |  | 5176486 | 0.360
10854 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | TROUSDALE |  | 06 | 0010037 | This project located on SR-10 FROM SR-141 TO SOUTH OF SR-25 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-10 | 356299.75 | 2.860
10855 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MARSHALL |  | 06 | 0011051 | This project located on SR-11 FROM CHAPEL HILL CITY LIMITS TO WILLIAMSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 998062.46 | 6.100
10856 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | RUTHERFORD |  | 06 | 0011052 | This project located on SR-11 FROM WILLIAMSON COUNTY LINE TO WILLIAMSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will a | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 323707.74 | 2.600
10857 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 0011053 | This project located on SR-11 FROM DAVIDSON COUNTY LINE TO SOUTH OF KASPER WAY will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-10-31 | 189938.94 | 0.600
10858 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WILLIAMSON |  | 07 | 0011054 | This project located on SR-11 FROM MARSHALL COUNTY LINE TO RUTHERFORD COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will als | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-09-30 | 103563.09 | 0.700
10859 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0012038 | This project located on SR-12 FROM I-65 TO SR-112 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the ro | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 1101616.6 | 3.000
10860 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MONTGOMERY | CLARKSVILLE (KY) | 07 | 0012039 | This project located on SR-12 FROM SR-374 TO KENTUCKY STATE LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-12-15 | 2009-11-30 | 1545491 | 4.060
10861 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HUMPHREYS |  | 08 | 0013033 | This project located on SR-13 FROM NORTH OF TUMBLING CREEK ROAD TO SOUTH OF PUMPKIN CREEK will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-11-15 | 2009-09-10 | 953545.52 | 6.910
10862 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | TIPTON |  | 08 | 0014048 | This project will widen SR-14 from 2 lanes to 4 lanes FROM NORTH OF SR-206 TO 1.2 MILES EAST OF SR-384 | Pavement Widening | 2009-04-06 | 2009-04-06 | 2011-12-15 |  | 16047112 | 3.900
10863 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MCNAIRY |  | 07 | 0015141 | This project will widen SR-15 from 2 lanes to 4 lanes FROM NEAR SR-225 TO SANDY FLAT ROAD | Pavement Widening | 2009-04-06 | 2009-04-06 | 2011-11-15 |  | 26292926 | 3.400
10864 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | FRANKLIN |  | 04 | 0015157 | This project located on SR-15 FROM NORTH OF SR-56 TO GRUNDY COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ext | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-31 | 572340.61 | 3.500
10865 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MCNAIRY |  | 07 | 0015158 | This project located on SR-15 FROM SR-5 (US-45 LEFT) TO SR-5 (US-45 RIGHT) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-11-10 | 2009-10-31 | 781974 | 2.500
10866 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MADISON |  | 08 | 0018025 | This project located on SR-18 FROM MERIDIAN CREEK TO BRIDGE OVER ABANDONED R/R will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-31 | 887797.68 | 4.900
10867 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MADISON |  | 08 | 0020045 | This project located on SR-20 FROM POPLAR CORNER ROAD TO BRIDGE OVER OLD SR-20 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 1443123.03 | 4.400
10868 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CARROLL |  | 08 | 0022057 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-22 with a new BRIDGES OVER OVERFLOW BEAVER CREEK, & OVERFLOW IN HUNTINGDON to serve the | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-09-30 | 2010-08-10 | 3172318 | 0.000
10869 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WILSON |  | 05 | 0026029 | This project located on SR-26 FROM NEAR MADDOX-SIMPSON PARKWAY TO EAST OF TAYLOR ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 695892.63 | 7.700
10870 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WHITE |  | 04 | 0026030 | This project located on SR-26 FROM EAST OF SR-136 TO WEST OF SR-111 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-12-15 | 2009-11-30 | 645472.61 | 4.500
10871 | Underway | C200,C230 | Highway Infrastructure Investment Grant | TENNESSEE | WILSON | NASHVILLE-DAVIDSON | 05 | 0026034 | This project on SR-26 will include the purchase of property for the future construction of an intersection at Maddox-Simpson Parkway in Lebanon. | Other | 2009-09-08 | 2009-09-08 | 2015-09-30 |  | 1000000 | 0.000
10872 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CUMBERLAND |  | 04 | 0028039 | This project located on SR-28 FROM NORTH OF WINNINGHAM ROAD TO SR-68 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-08-31 | 551565.06 | 5.000
10873 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SCOTT |  | 04 | 0029069 | This project located on SR-29 FROM WOLF RIVER ROAD TO SOUTH OF GLASSHOUSE ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-31 | 443943.46 | 6.900
10874 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 0029070 | This project located on SR-29 FROM OVERHEAD OVER DAYTON PIKE TO OLD DAYTON PIKE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 1782382.81 | 5.400
10875 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | RHEA |  | 03 | 0029071 | This project located on SR-29 FROM SOUTH OF VANN'S CREEK ROAD/HOYAL ROAD TO SOUTH OF MACEDONIA ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automob | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-31 | 2009-10-31 | 440636.43 | 4.740
10876 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | BLEDSOE |  | 04 | 0030047 | This project located on SR-30 FROM WEST OF CRANWELL ROAD RT TO SR-28 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-11-30 | 2009-11-30 | 658167 | 4.800
10877 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | UNION |  | 03 | 0033075 | This project located on SR-33 FROM KNOX COUNTY LINE TO EAST OF MAIN STREET RIGHT will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-12-15 | 2009-10-31 | 550518.31 | 7.570
10878 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | POLK |  | 03 | 0033076 | This project will widen SR-33 from 2 lanes to 4 lanes FROM BENTON NORTH CITY LIMITS TO SR-30 EAST | Pavement Widening | 2009-04-07 | 2009-04-07 | 2012-11-30 |  | 26667858 | 5.300
10879 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CLAIBORNE |  | 03 | 0033077 | This project located on SR-33 FROM SOUTH OF MOLLY HOLLOW ROAD TO SOUTH OF OLD SR-33 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will a | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-12-15 | 2009-11-30 | 518574.27 | 2.220
10880 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | HAMBLEN | MORRISTOWN | 01 | 0034069 | This project is for traffic signal upgrades on SR-34 at the intersection of SR-34 and SR-160 in Morristown | Safety/Traffic Management | 2009-07-17 | 2009-07-17 | 2010-11-23 | 2011-06-09 | 155927 | 0.000
10881 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | KNOX | KNOXVILLE | 02 | 0034070 | This project located on SR-34 from SR-9 (US-25W) to the Jefferson County line will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also he | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2010-09-15 | 2010-08-05 | 663553 | 3.370
10882 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | CARTER | JOHNSON CITY | 01 | 0037014 | This project located on SR-37 FROM NORTH OF CROOK STREET TO BRIDGE OVER WATAUGA RIVER will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-11-30 | 2526811 | 5.300
10883 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 0041019 | This project located on SR-41 FROM DICKERSON PIKE TO SR-257 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-31 | 2009-10-31 | 823041.34 | 5.300
10884 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | SULLIVAN | BRISTOL TN- VA | 01 | 0044006 | This project located on SR-44 FROM SR-34 TO VIRGINIA STATE LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2009-10-31 | 2009-08-31 | 385588.19 | 2.500
10885 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | DICKSON |  | 08 | 0046012 | This project located on SR-46 FROM ROBIN HOOD ROAD TO SR-1 BYPASS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend th | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-08-31 | 1625263.4 | 4.400
10886 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WILLIAMSON |  | 07 | 0046013 | This project located on SR-46 FROM PEWITT ROAD TO NEAR SR-100 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-11-30 | 419327.73 | 5.210
10887 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DICKSON |  | 08 | 0046018 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-46 with a new bridge over Yellow Creek in Dickson Countyto serve the community for the | Bridge Replacement | 2010-09-17 | 2011-03-07 | 2011-12-31 |  | 900000 | 0.000
10888 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HOUSTON |  | 08 | 0049020 | This project located on SR-49 FROM SR-147 TO SR-13 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-11-15 | 2009-09-15 | 748264.6 | 4.940
10889 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MORGAN |  | 04 | 0052055 | This project located on SR-52 FROM END OF BRIDGE OVER CLEAR FORK RIVER TO SCOTT COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, an | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-10-31 | 725453.2 | 3.900
10890 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SCOTT |  | 04 | 0052056 | This project located on SR-52 FROM MORGAN COUNTY LINE TO SR-29 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-31 | 758926.27 | 5.100
10891 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CLAY |  | 06 | 0052057 | This project located on SR-52 FROM EAST END OF CUMBERLAND RIVER BRIDGE TO SR-53 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 264782.96 | 1.100
10892 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | FENTRESS |  | 04 | 0052058 | This project located on SR-52 FROM EAST OF BRIDGE OVER SR-28 TO SR-296 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-11-15 | 2009-11-30 | 806441.39 | 4.000
10893 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MACON |  | 06 | 0052059 | This project located on SR-52 FROM LAFAYETTE CITY LIMITS TO NEAR BUTLER ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also hel | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-11-15 | 1018931.84 | 5.350
10894 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MACON |  | 06 | 0056057 | This project located on SR-56 FROM JACKSON COUNTY LINE TO SR-262 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-11-15 | 2009-10-31 | 91780.49 | 2.700
10895 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | GRUNDY |  | 04 | 0056058 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-56 with a new BRIDGE OVER FIRESCALD CREEK IN ALTAMONT to serve the community for the ne | Bridge Replacement | 2009-05-12 | 2009-05-12 | 2011-05-31 | 2011-08-30 | 1811111 | 0.000
10896 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | FAYETTE |  | 07 | 0057045 | This project located on SR-57 FROM COWAN LOOP ROAD TO SR-18 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-10-31 | 352747.44 | 5.040
10897 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON |  | 03 | 0058032 | This project located on SR-58 FROM NORTH OF RUNYAN ROAD TO SOUTH OF SR-60 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-11-30 | 543372.71 | 4.730
10898 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | TIPTON |  | 08 | 0059023 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-59 with a new BRIDGE OVER LITTLE BEAVER CREEK INCLUDING A DRAINAGE DITCH to serve the c | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-01-15 | 2010-06-30 | 1247494 | 0.000
10899 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MEIGS |  | 03 | 0060017 | This project located on SR-60 FROM NEAR MCINTRUFF ROAD IN MEIGS COUNTY TO NEAR FIVE POINTS ROAD IN RHEA COUNTY will provide a smoother riding surface for motorists, thus decreasing wear and tear on th | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-11-30 | 641331.92 | 1.460
10900 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | ANDERSON |  | 03 | 0061022 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-61 with a new BRIDGE OVER POPLAR CREEK to serve the community for the next several deca | Bridge Replacement | 2009-05-12 | 2009-05-12 | 2011-05-31 |  | 1736988 | 0.000
10901 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TENNESSEE | SEVIER |  | 01 | 0066039 | This project will widen SR-66 from 4 lanes to 6 lanes FROM NORTH OF NICHOLS STREET IN SEVIERVILLE TO SR-338 (BOYDS CREEK HIGHWAY) | Pavement Widening | 2009-05-15 | 2009-05-15 | 2011-12-31 |  | 40690695 | 4.220
10902 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | HAMBLEN | MORRISTOWN | 01 | 0066042 | This resurfacing project located on SR-66 WEST 1ST NORTH STREET, FROM MARS AVENUE TO NORTH CUMBERLAND STREET IN MORRISTOWN will provide a smoother riding surface for motorists, thus decreasing wear an | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2010-11-23 | 2011-06-09 | 477151.05 | 0.980
10903 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | BENTON |  | 08 | 0069068 | This project located on SR-69 FROM SOUTH OF SR-1 TO SOUTH OF SR-391 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-09-30 | 517345.19 | 1.500
10904 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HENRY |  | 08 | 0069069 | This project located on SR-69A FROM SCARBOROUGH RD TO SR-69 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-15 | 1033658.43 | 6.400
10905 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HARDIN |  | 07 | 0069070 | This project located on SR-69 FROM HOLLAND CREEK ROAD TO SR-226 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-10-31 | 1114952.79 | 7.370
10906 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | GREENE |  | 01 | 0070015 | This project located on SR-70 FROM RAMP TO I-81 TO HAWKINS COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-11-15 | 2009-09-30 | 833011.54 | 5.400
10907 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | BRADLEY | CLEVELAND | 03 | 0074006 | This project located on SR-74 from SR-74 Southbound (Broad Street) to SR-2 (US-11) in Cleveland will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles | Pavement Improvement | 2010-04-30 | 2010-05-15 | 2010-09-15 | 2010-09-15 | 151849 | 2.780
10908 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | WASHINGTON | JOHNSON CITY | 01 | 0075009 | This project located on SR-75 FROM SOUTH OF SHADDEN ROAD TO NORTH OF I-26 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2009-12-15 | 2009-12-15 | 481848.38 | 1.500
10909 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | GIBSON |  | 08 | 0076051 | This project will widen SR-76 from 2 lanes to 4 or 5 lanes FROM SR-43 IN MILAN TO NEAR THE CARROLL COUNTY LINE | Pavement Widening | 2009-06-17 | 2009-06-17 | 2011-12-15 |  | 20600000 | 4.400
10910 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HAYWOOD |  | 08 | 0076058 | This project located on SR-76 FROM FAYETTE COUNTY LINE TO SR-179 RT will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-08-31 | 1242698.91 | 5.600
10911 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | STEWART |  | 08 | 0076059 | This project will widen SR-76 from 2 lanes to 4 lanes FROM SR-120 TO EAST OF MONTGOMERY COUNTY LINE | Pavement Widening | 2009-05-15 | 2009-05-15 | 2011-11-01 |  | 21460607 | 5.800
10912 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | LAKE |  | 08 | 0078015 | This project located on SR-78 FROM SR-21 TO VAN WORKS ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-09-10 | 440794.26 | 4.950
10913 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WASHINGTON | JOHNSON CITY | 01 | 0081017 | This project located on SR-81 FROM SOUTH OF RIDGECREST ROAD TO NORTH OF ANDERSON ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2009-12-15 | 2009-12-15 | 533117.43 | 2.500
10914 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | OBION |  | 08 | 0089016 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-89 with a new BRIDGE OVER GRASSY CREEK to serve the community for the next several deca | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-06-30 | 2010-06-30 | 1086679 | 0.000
10915 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | WASHINGTON | JOHNSON CITY | 01 | 0091033 | This project located on SR-91 FROM LEGION STREET TO SR-34(WB) AND FROM SR-34 TO LEGION STREET (EB) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobi | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2010-05-31 | 2009-12-05 | 827195 | 1.360
10916 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | ANDERSON |  | 03 | 0095007 | This project located on SR-95 FROM MELTON LAKE ROAD TO SR-61 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the lif | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-12-15 | 447717.83 | 1.170
10917 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CANNON |  | 06 | 0096024 | This project located on SR-96 FROM RUTHERFORD COUNTY LINE TO WILSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 775069.8 | 5.000
10918 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DECATUR |  | 07 | 0100045 | This project located on SR-100 FROM SR-69 TO BRIDGE AT RUSHING CREEK will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-08-31 | 440213.53 | 2.400
10919 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HARDEMAN |  | 07 | 0100046 | This project located on SR-100 FROM OLD SR-18 TO CHESTER COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-31 | 557023.56 | 3.900
10920 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | ANDERSON |  | 03 | 0100047 | This project will improve safety and reliability of the transportation system by replacing an older bridge on BINKLEY ACRES ROAD with a new BRIDGE OVER BRUSHY FORK CREEK to serve the community for th | Bridge Replacement | 2009-04-07 | 2009-04-07 | 2010-06-15 | 2010-06-30 | 568838 | 0.000
10921 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | ANDERSON |  | 03 | 0100048 | This project will improve safety and reliability of the transportation system by replacing an older bridge on YARNELL ROAD with a new BRIDGE OVER LITTLE DISMAL CREEK NEAR CLINTON to serve the communi | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-06-30 | 2010-05-09 | 209099 | 0.100
10922 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | ANDERSON |  | 03 | 0100049 | This project will improve safety and reliability of the transportation system by replacing an older bridge on HALF MOON ROAD with a new BRIDGE OVER STONEY FLAT CREE to serve the community for the next | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-07-31 | 2010-01-31 | 212832 | 0.100
10923 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CUMBERLAND |  | 04 | 0101015 | This project will widen SR-101 from 2 lanes to 5 lanes including bike lanes and sidwalks FROM SR-282 TO SR-392 | Pavement Widening | 2009-06-30 | 2009-06-30 | 2011-11-01 |  | 19275020 | 2.800
10924 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | RUTHERFORD |  | 06 | 0102011 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-102 with a new BRIDGES OVER BRANCH AND ROCKY FORK CREEK to serve the community for the | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-08-10 | 2010-12-03 | 1476763 | 0.000
10925 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | RUTHERFORD | MURFREESBORO | 06 | 0102013 | This project located on SR-102 FROM I-24 to SR-266 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-08-31 | 2010-08-05 | 363000 | 5.400
10926 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0106025 | This project located on SR-106 FROM HARDING PLACE TO I-440 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-10-31 | 2009-09-30 | 1845224.73 | 2.680
10927 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WASHINGTON |  | 01 | 0107014 | This project located on SR-107 FROM GREENE COUNTY LINE TO SR-81 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-12-10 | 2291975.55 | 11.340
10928 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER |  | 06 | 0109024 | This paving project will complete SR-109 from the Gallatin bypass to south of Hollis Chapel Road | New Construction | 2009-05-15 | 2009-05-15 | 2010-11-30 | 2010-12-15 | 10611084.19 | 5.200
10929 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | ANDERSON |  | 03 | 0116010 | This project located on SR-116 FROM NORTH OF BRADEN FLATS LANE TO SR-330 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ex | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-31 | 468134.73 | 3.400
10930 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WARREN |  | 04 | 0127012 | This project located on SR-127 FROM OLD SHELLSFORD ROAD TO SR-30 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-07-31 | 494087.42 | 3.000
10931 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | COFFEE |  | 04 | 0127013 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-127 with a new BRIDGE OVER I-24 to serve the community for the next several decades. | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-09-30 | 2010-09-30 | 3890007 | 0.000
10932 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | KNOX | KNOXVILLE | 02 | 0131020 | This project located on SR-131 FROM SR-33 TO SR-331 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-11-15 | 2009-10-31 | 800728.14 | 4.900
10933 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | KNOX | KNOXVILLE | 02 | 0131022 | This project located on SR-131 FROM SR-9 TO WEST OF GILL ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-30 | 453224.38 | 2.250
10934 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | KNOX | KNOXVILLE | 02 | 0131025 | This project will widen SR-131 / LOVELL ROAD from 2 lanes to 5 lanes FROM WEST OF PELLISSIPPI PARKWAY TO SCHAEFFER ROAD | Pavement Widening | 2009-11-13 | 2010-02-28 | 2011-06-30 |  | 2739022 | 0.110
10935 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | PUTNAM |  | 06 | 0135012 | This project located on SR-135 FROM NORTH OF DIXIE AVENUE TO JACKSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-07-31 | 861128.88 | 4.900
10936 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CARTER |  | 01 | 0143006 | This project located on SR-143 FROM NORTH CAROLINA STATE LINE TO SR-37 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-12-15 | 2009-12-15 | 2112341.99 | 12.600
10937 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CANNON |  | 06 | 0146004 | This project located on SR-146 FROM SR-1 TO DEKALB COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-30 | 398036.62 | 9.700
10938 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DE KALB |  | 06 | 0146005 | This project located on SR-146 FROM CANNON COUNTY LINE TO NORTH OF BRIDGE OVER PINE CREEK will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 233612.75 | 5.500
10939 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | BENTON |  | 08 | 0147002 | This project located on SR-147 FROM SR-69A TO PINE GROVE ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-11-30 | 2009-11-30 | 808586 | 5.400
10940 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MARION |  | 04 | 0156006 | This project located on SR-156 FROM MARION-FRANKLIN FOREST TO ORME MOUNTAIN ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 401587.84 | 6.400
10941 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | JOHNSON |  | 01 | 0167004 | This project located on SR-167 FROM LITTLE DRY RUN ROAD TO SR-34 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-30 | 1421706 | 7.590
10942 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WILSON | NASHVILLE-DAVIDSON | 05 | 0171024 | This project will widen SR-171 (MOUNT JULIET ROAD) from 3 lanes to 5 lanes FROM DIVISION STREET TO SR-24 (US-70, LEBANON ROAD) | Pavement Widening | 2009-06-17 | 2009-06-17 | 2011-11-15 |  | 10297296 | 2.200
10943 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CARTER |  | 01 | 0173007 | This project located on SR-173 FROM UNICOI COUNTY LINE TO SR-37 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-12-15 | 327572.17 | 4.280
10944 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WEAKLEY |  | 08 | 0190009 | This project located on SR-190 FROM CARROLL COUNTY LINE TO SR-124 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend th | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-09-30 | 584620.41 | 4.550
10945 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | FAYETTE |  | 07 | 0194011 | This project located on SR-194 FROM SR-15 TO SR-59 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-30 | 588120.99 | 8.430
10946 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DECATUR |  | 07 | 0202015 | This project located on SR-202 FROM SR-114 TO SR-69 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-08-31 | 707782.58 | 5.200
10947 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HENRY |  | 08 | 0218006 | Construction of a new bypass on the northwest side of Paris from SR-54 west of Paris to SR-69 northwest of Paris | New Construction | 2009-04-06 | 2009-04-06 | 2010-11-30 | 2010-12-15 | 8898704 | 3.080
10948 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | MADISON | JACKSON | 08 | 0223009 | This project located on SR-223 FROM SOUTH OF LOWER BROWNSVILLE RD TO BRIDGE OVER I-40 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-31 | 383371.48 | 0.600
10949 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CHESTER |  | 07 | 0225003 | This project located on SR-225 FROM OLD FRIENDSHIP ROAD TO MONTEZUMA ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-30 | 534235.6 | 5.300
10950 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MONTGOMERY |  | 07 | 0238003 | This project located on SR-238 FROM SR-76 TO KENTUCKY STATE LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-12-15 | 2009-11-30 | 569017.07 | 8.250
10951 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MARION |  | 04 | 0242127 | This project located on I-24 FROM SR-27/150 TO TENNESSEE RIVER BRIDGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exten | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-30 | 2473858.4 | 8.230
10952 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | COFFEE |  | 04 | 0242129 | This project located on I-24 FROM RAMP FROM SR-55 (McMINNVILLE HWY) TO RAMP FROM AEDC will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-30 | 4403358.52 | 6.100
10953 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | COFFEE |  | 04 | 0242130 | This project located on I-24 FROM NOAH FORK CREEK TO RAMP FROM SR-2 EB will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-30 | 3404807.34 | 5.320
10954 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 0243083 | This project is for the construction of a new Welcome Center near Tiftonia on I-24 | Transportation Enhancements | 2009-12-15 | 2009-12-15 | 2010-11-30 | 2010-12-22 | 2114760 | 0.000
10955 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CHEATHAM |  | 05 | 0251012 | This project located on SR-251 FROM SR-249 TO DAVIDSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend t | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-06-30 | 543073.15 | 4.000
10956 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | ROBERTSON |  | 06 | 0257004 | This project located on SR-257 FROM SR-49 TO NEAR NEW CUT ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-06-30 | 680158.79 | 5.800
10957 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 0258007 | This project is for the development of design plans for the future widening of New Shackle Island Road from Iris Drive north to SR-386 in Hendersonville | Other | 2009-08-12 | 2009-08-12 | 2015-09-30 |  | 375000 | 0.860
10958 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MACON |  | 06 | 0262009 | This project located on SR-262 FROM SR-56 TO JACKSON COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-11-15 | 2009-10-31 | 93569.27 | 2.810
10959 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | LINCOLN |  | 04 | 0275006 | This project located on SR-275 FROM NEAR 4-WAY STOP TO SR-15 EAST will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend th | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-11-15 | 2009-09-30 | 263249.27 | 7.000
10960 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SEQUATCHIE |  | 04 | 0283010 | This project located on SR-283 FROM MARION COUNTY LINE TO SR-8 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the l | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-12-15 | 2009-11-30 | 548051.67 | 5.500
10961 | Underway | C200 | Highway Infrastructure Investment Grant | TENNESSEE | WARREN |  | 04 | 0286004 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-286 with a new bridge over Big Hickory Creek in McMinnvilleto serve the community for t | Bridge Replacement | 2010-09-17 | 2011-01-31 | 2012-08-31 |  | 2042767.76 | 0.000
10962 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | OVERTON |  | 06 | 0294002 | This project located on SR-294 FROM SR-111 TO OAKLEY-ALLONS ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 508318 | 6.200
10963 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CAMPBELL |  | 04 | 0297002 | This project located on SR-297 FROM WEST OF LICK FORK LANE LEFT TO EAST OF LITTLE ELK CREEK ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobile | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-12-15 | 2009-12-15 | 921605.3 | 6.100
10964 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | BENTON |  | 08 | 0300028 | This streetscape beautification project in Camden includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 2009-07-30 | 2009-07-30 | 2010-08-31 | 2010-08-15 | 556476 | 0.000
10965 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TENNESSEE | BRADLEY |  | 03 | 0308006 | This project located on SR-308 FROM I-75 TO SR-2 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the roa | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 885082.48 | 3.300
10966 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | POLK |  | 03 | 0314004 | This project located on SR-314 FROM SR-40 TO SR-33 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-11-30 | 1096860.25 | 6.080
10967 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | FENTRESS |  | 04 | 0325007 | This project located on SR-325 FROM FENTRESS-PICKETT COUNTY LINE TO SR-28 IN PICKETT COUNTY will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, an | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-11-15 | 2009-10-31 | 241483.77 | 2.530
10968 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | PICKETT |  | 04 | 0325008 | This project located on SR-325 FROM WEST OF HILL ROAD TO FENTRESS COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also he | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-11-30 | 380694.76 | 4.530
10969 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | HAMBLEN | MORRISTOWN | 01 | 0343007 | This project located on SR-343 FROM SR-32 TO SR-34 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the r | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2009-12-01 | 2009-11-30 | 669203.29 | 3.890
10970 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HAWKINS |  | 01 | 0344006 | This project located on SR-344 FROM SR-113 TO HOLSTON RIVER BRIDGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend t | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-10-31 | 401558.13 | 3.800
10971 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | HENRY |  | 08 | 0356001 | This project located on SR-356 FROM SR-69/54 TO SR-76 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of th | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-09-15 | 414186.21 | 1.000
10972 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | CARTER |  | 01 | 0361003 | This project located on SR-361 FROM SR-359 TO SR-37 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2011-03-31 | 1521334.4 | 8.900
10973 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TENNESSEE | MARSHALL |  | 06 | 0373007 | This project will widen SR-373 from 2 lanes to 5 lanes FROM I-65 TO EAST OF SR-417 IN LEWISBURG | Pavement Widening | 2009-04-07 | 2009-04-07 | 2011-12-15 |  | 19252288 | 4.000
10974 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | MONTGOMERY | CLARKSVILLE (KY) | 07 | 0374016 | This project is for the lighting of the interchange at SR-374 and SR-13 in Clarksville | Safety/Traffic Management | 2010-02-18 | 2010-02-18 | 2010-12-30 | 2011-06-13 | 342292 | 0.000
10975 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0386011 | This project will widen the eastbound lane on SR 386 from I-65 to Center Point Road in Davidson and Sumner Counties to improve safety. | Safety/Traffic Management | 2011-01-15 | 2011-01-20 | 2011-10-31 | 2011-11-11 | 105605 | 2.340
10976 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | BENTON |  | 08 | 0391015 | This project located on SR-391 FROM SR-1 TO SR-1 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of the roa | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-09-30 | 1350280.04 | 5.300
10977 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | WASHINGTON | JOHNSON CITY | 01 | 0400023 | This project located on SR-400 FROM NORTH BROADWAY STREET TO WEST MAIN STREET (SB) AND FROM WEST MAIN STREET TO NORTH BROADWAY STREET (NB) will provide a smoother riding surface for motorists, thus de | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-12-15 | 2009-12-05 | 925742.56 | 1.630
10978 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | MADISON | JACKSON | 08 | 0401317 | This project located on I-40 FROM WEST OF EXIT 74 TO EAST OF EXIT 83 (Excludes LM 13.59 to LM 15.57) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automo | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-10-31 | 2951286.29 | 9.500
10979 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HENDERSON |  | 07 | 0402087 | This project located on I-40 FROM MADISON COUNTY LINE TO SR-104 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-08-31 | 2101221.48 | 6.100
10980 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403140 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-155 with a new BRIDGE OVER I-40 AT ROBERTSON ROAD to serve the community for the next s | Bridge Replacement | 2009-04-09 | 2009-04-09 | 2011-09-15 |  | 3570807 | 0.000
10981 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403141 | This project located on I-40 FROM CHARLOTTE PIKE TO OVERHEAD BRIDGE AT WESTBORO DRIVE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-09-30 | 2009-10-31 | 1402438.6 | 2.200
10982 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403142 | This project will complete the second phase of the interchange improvements at Briley Parkway/Robertson Road on Interstate 40 | Safety/Traffic Management | 2009-04-09 | 2009-04-09 | 2011-09-15 |  | 28200000 | 0.400
10983 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0403143 | This project located on I-40 FROM SR-1 TO CHARLOTTE PIKE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life of | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-30 | 1808289.41 | 4.640
10984 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SMITH |  | 06 | 0405135 | This project located on I-40 FROM SR-53 TO PUTNAM COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the li | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-10-31 | 2074075.66 | 8.600
10985 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | PUTNAM |  | 06 | 0406143 | This project located on I-40 FROM SMITH COUNTY LINE TO EAST OF SR-56 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-10-31 | 1832527.46 | 6.600
10986 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | WEAKLEY |  | 08 | 0431011 | This project located on SR-431 FROM CENTRAL STREET TO SR-22 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the life | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-11-30 | 1416450.93 | 2.190
10987 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | BEDFORD |  | 06 | 0437002 | Construction of a new bypass on the northeast side of Shelbyville from SR-10 north of Shelbyville to SR-16 east of Shelbyville | New Construction | 2009-04-07 | 2009-04-07 | 2011-08-31 | 2011-10-31 | 15740454 | 6.300
10988 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | BLEDSOE |  | 04 | 0443002 | This project located on SR-443 FROM 90 DEGREE TURN TO RHEA COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-11-30 | 2009-11-30 | 101375.3 | 1.380
10989 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | RHEA |  | 03 | 0443003 | This project located on SR-443 FROM BLEDSOE COUNTY LINE TO SR-30 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-12-15 | 2009-12-15 | 397097.62 | 6.870
10990 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | SULLIVAN | BRISTOL TN- VA | 01 | 0473002 | This project is for the optimization of traffic signal timing on SR-473/Martin Luther King Jr. Boulevard in Bristol | Safety/Traffic Management | 2009-12-28 | 2009-12-28 | 2010-08-10 | 2011-04-04 | 91211.52 | 0.000
10991 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | BLOUNT |  | 02 | 0500039 | This project will improve safety and reliability of the transportation system by replacing an older bridge on THOMPSON BRIDGE ROAD with a new BRIDGE OVER NINE MILE CREEK to serve the community for th | Bridge Replacement | 2009-04-07 | 2009-04-07 | 2010-11-30 | 2010-12-15 | 1386644 | 0.001
10992 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | BLOUNT |  | 02 | 0500040 | This project will improve safety and reliability of the transportation system by replacing an older bridge on REGAN MILL ROAD with a new BRIDGE OVER NINE MILE CREEK to serve the community for the ne | Bridge Replacement | 2009-04-07 | 2009-04-07 | 2011-08-31 | 2011-11-30 | 357833 | 0.200
10993 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | BLOUNT | KNOXVILLE | 02 | 0500041 | This project will improve safety and reliability of the transportation system by replacing an older bridge on GARLAND ROAD with a new BRIDGE OVER NINE MILE CREEK to serve the community for the next s | Bridge Replacement | 2010-02-11 | 2010-02-11 | 2010-10-31 | 2010-11-18 | 571813 | 0.000
10994 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | GILES |  | 04 | 0651069 | This project is for the construction of a new Welcome Center near Ardmore on I-65 | Transportation Enhancements | 2010-01-11 | 2010-01-11 | 2011-02-28 | 2011-01-25 | 1419811 | 0.000
10995 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | ROBERTSON |  | 06 | 0653116 | This project is for the construction of a new Welcome Center near Mitchellville on I-65 | Transportation Enhancements | 2009-12-15 | 2010-02-01 | 2010-11-30 | 2010-11-19 | 2374533 | 0.000
10996 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | BRADLEY | CLEVELAND | 03 | 0751118 | This project located on I-75 FROM EAST OF SR-60 TO SOUTH OF MCMINN COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also h | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-09-30 | 3730469.92 | 5.600
10997 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 0751126 | This project includes installation of landscaping at the Welcome Center near the Georgia state line on I-75 in Chattanooga | Transportation Enhancements | 2009-05-14 | 2009-05-14 | 2010-05-15 | 2010-05-10 | 130000 | 0.000
10998 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | LOUDON |  | 02 | 0752037 | This project located on I-75 FROM TENNESSEE RIVER BRIDGE TO SR-73 INTERCHANGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also he | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-09-30 | 4915404.62 | 6.900
10999 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | KNOX | KNOXVILLE | 02 | 0753147 | This project located on I-75 FROM I-640 TO SOUTH OF CALLAHAN DRIVE AND ON I-275, FROM CONCRETE PAVEMENT TO I-640 will provide a smoother riding surface for motorists, thus decreasing wear and tear on | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-31 | 2009-10-31 | 2481699 | 3.400
11000 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | SULLIVAN | BRISTOL TN- VA | 01 | 0811107 | This project includes installation of landscaping at the Welcome Center near the Virginia state line on I-81 in Bristol | Transportation Enhancements | 2009-05-14 | 2009-05-14 | 2010-05-15 | 2010-05-31 | 130000 | 0.000
11001 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SULLIVAN | BRISTOL TN- VA | 01 | 0811108 | This project located on I-81 FROM SOUTH OF SR-357 TO NORTH OF SR-394 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2011-01-31 | 2009-11-30 | 4791759 | 7.200
11002 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 0811112 | This project is for the widening of Houston Levee Road from Bailey Station Road to Winchester Road in Collierville from 4 lanes to 6 lanes. | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2010-12-14 | 2010-11-17 | 1400467 | 1.200
11003 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | CARROLL |  | 08 | 0900031 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Westport Road with a new Bridges over the Big Sandy River and Overflow to serve the commu | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2010-06-01 | 2010-05-15 | 1563813 | 0.300
11004 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | CARROLL |  | 08 | 0900034 | This project is for the construction of a bicycle and pedestrian path in Carroll County, including landscaping, pedestrian amenities, lighting, upgrading/rehabilitating sidewalks. | Transportation Enhancements | 2010-07-06 | 2010-07-06 | 2011-03-01 | 2011-04-08 | 45425 | 0.000
11005 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | CARTER |  | 01 | 1000025 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Steel Bridge Road (Wilbur Dam Rd) with a new Bridge over the Watauga River to serve the co | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2010-09-01 | 2010-10-31 | 1782430.75 | 0.100
11006 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | RUTHERFORD | MURFREESBORO | 06 | 1048006 | This resurfacing project located on THOMPSON LANE FROM SR-66 TO SR-1 (US-41/70S) IN MURFREESBORO will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobile | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2010-08-30 | 2010-08-15 | 574996.54 | 4.240
11007 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | CHEATHAM |  | 05 | 1100027 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SPRING CREEK ROAD with a new BRIDGE OVER SPRING CREEK to serve the community for the next | Bridge Replacement | 2009-04-07 | 2009-04-07 | 2010-06-14 | 2010-06-30 | 512092 | 0.100
11008 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 1406002 | This project is for the installation of traffic signals on Dayton Boulevard at the Intersections at Martin Road, Newberry Street, Leawood Avenue and Browntown Road in Red Bank | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-12-22 |  | 271843 | 0.000
11009 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 1406003 | This project is for the construction of sidewalks on Dayton Boulevard From Greenleaf Street to Browntown Road in Red Bank | Transportation Enhancements | 2010-02-16 | 2010-02-16 | 2011-01-23 |  | 186180 | 2.150
11010 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 1406004 | This project located on Dayton Boulevard From the City limits to SR-153 in Chattanooga will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and wi | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-10-30 | 2010-08-19 | 383992.57 | 2.860
11011 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | COCKE |  | 01 | 1500050 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Splashaway Road with a new Bridge over Sinking Creek to serve the community for the next s | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2009-10-01 | 2009-09-30 | 224675.62 | 0.000
11012 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TENNESSEE | COFFEE |  | 04 | 1600016 | This project will improve safety and reliability of the transportation system by replacing an older bridge on MCKELLAR DRIVE with a new BRIDGE OVER LITTLE DUCK RIVER IN MANCHESTER to serve the communi | Bridge Replacement | 2009-05-14 | 2009-05-14 | 2010-08-10 | 2010-11-30 | 1130458 | 0.000
11013 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 1900029 | This project will improve safety and reliability of the transportation system by replacing an older bridge on CHESTNUT STREET with a new BRIDGE OVER CSX RAILROAD IN NASHVILLE to serve the community fo | Bridge Replacement | 2009-06-30 | 2009-06-30 | 2010-07-31 | 2010-05-31 | 2061796 | 0.000
11014 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | ROBERTSON | NASHVILLE-DAVIDSON | 06 | 1953001 | This resurfacing project located on CALISTA ROAD FROM OZZY FULKS ROAD TO SR-41 (US-31W) IN WHITE HOUSE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their auto | Pavement Improvement | 2009-08-13 | 2009-08-13 | 2011-01-01 |  | 562000 | 4.860
11015 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | DECATUR |  | 07 | 2000013 | This project is for the construction of new sidewalks along SR-641 in Decatur County | Transportation Enhancements | 2009-11-12 | 2009-11-12 | 2011-04-30 |  | 251365 | 0.000
11016 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | DECATUR |  | 07 | 2000014 | This streetscape beautification project in Parsons includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 2009-08-21 | 2009-08-21 | 2010-08-14 | 2010-12-01 | 1040896 | 0.000
11017 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 2041001 | This project is for the construction of a new bridge on Big Station Camp Creek Boulevard from 0.2 miles north of SR-6 to 0.2 miles south of SR-6 including realigning the roadway to the new bridge in | Pavement Widening | 2009-11-13 | 2009-11-13 | 2010-12-31 | 2010-10-18 | 1000000 | 0.200
11018 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | FAYETTE |  | 07 | 2400032 | This project will improve safety and reliability of the transportation system by replacing an older bridge on FEATHERS CHAPEL ROAD with a new BRIDGE OVER TREADVILLE CREEK to serve the community for th | Bridge Replacement | 2009-05-13 | 2009-05-13 | 2010-01-15 | 2009-12-31 | 331937 | 0.100
11019 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 2401289 | This project located on I-240 FROM MADISON AVENUE TO I-55 AND ON I-55, FROM NONCONNAH CREEK TO I-240 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automo | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-15 | 2009-11-30 | 3488250.82 | 5.650
11020 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | FENTRESS |  | 04 | 2500024 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Delk Creek Road with a new Bridge over Delk Creek to serve the community for the next seve | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2009-11-01 | 2009-10-31 | 528469.91 | 0.100
11021 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | GIBSON |  | 08 | 2700051 | This project will improve safety and reliability of the transportation system by replacing an older bridge on McMurry Road with a new Bridges over Branch, Davis Creek and Reagan Creek to serve the co | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2010-06-01 | 2010-05-30 | 1016860 | 0.300
11022 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | GILES |  | 04 | 2800032 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Earl Townsend Road with a new Bridge over the West Fork of Shoal Creek to serve the commun | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2009-12-15 | 2009-12-15 | 373318.65 | 0.100
11023 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | GILES |  | 04 | 2800033 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ELLA WEST ROAD with a new BRIDGE OVER EAST FORK OF LYNN CREEK to serve the community for | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2009-12-15 | 2009-12-05 | 189552.55 | 0.000
11024 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 2813009 | This project is for repairing the tunnel under the airport runway at Winchester Road in Memphis | Safety/Traffic Management | 2010-02-11 | 2010-02-11 | 2011-06-18 |  | 378973 | 0.000
11025 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 2814003 | This project located on PERKINS ROAD EXT. FROM SR-57 (POPLAR AVENUE) TO LAURELWOOD DRIVE IN MEMPHIS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automob | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2012-01-31 |  | 267969 | 0.470
11026 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 2861002 | This project located on SOUTHERN AVENUE FROM SR-4 (LAMAR AVENUE) TO COLONIAL ROAD IN MEMPHIS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, a | Pavement Improvement | 2010-02-10 | 2010-02-11 | 2012-01-31 |  | 1525616 | 5.620
11027 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 3300046 | This project located on STANDIFER GAP ROAD FROM BILL REED ROAD TO BANKS ROAD and WOODLAND DRIVE FROM PATTENTOWN ROAD SOUTH TO BILL REED ROAD will provide a smoother riding surface for motorists, thus | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2010-10-30 | 2010-10-13 | 302526.98 | 2.420
11028 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 3300047 | This project located on MOSES ROAD FROM BOY SCOUT ROAD TO GANN ROAD/WEST CRABTREE ROAD FROM MIDDLE VALLEY ROAD TO BOWMAN ROAD/LOVELL ROAD FROM DAISY DALLAS ROAD TO THE SODDY DAISY CITY LIMITS will pro | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2010-12-14 | 2010-10-18 | 436832.35 | 3.140
11029 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 3300048 | This project located on FAIRVIEW ROAD FROM THE CHATTANOOGA CITY LIMITS TO GOLD POINT CIRCLE ROAD and GOLD POINT CIRCLE ROAD FROM HIXSON PIKE TO FAIRVIEW ROADwill provide a smoother riding surface for | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2010-11-02 | 2010-10-13 | 285904.62 | 2.020
11030 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 3300049 | This project located on CHAMPION ROAD FROM THE CHATTANOOGA CITY LIMITS TO HARRISON PIKE and HARRISON-OOLTEWAH ROAD FROM SR-58 TO THE ENTERPRISE SOUTH INDUSTRIAL PARK will provide a smoother riding sur | Pavement Improvement | 2009-12-07 | 2010-06-01 | 2010-08-31 | 2010-08-20 | 248874.87 | 2.020
11031 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HARDEMAN |  | 07 | 3500036 | This project will improve safety and reliability of the transportation system by replacing an older bridge on VAN BUREN ROAD with a new BRIDGE OVER HAMER CREEK to serve the community for the next sev | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-31 | 513939 | 0.100
11032 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | HARDEMAN |  | 07 | 3500037 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Teague Road with a new Bridge over Clover Creek to serve the community for the next severa | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2010-06-01 | 2009-11-05 | 728855.92 | 0.100
11033 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | HARDEMAN |  | 07 | 3500038 | This project will improve safety and reliability of the transportation system by replacing an older bridge on PARK SWAIN ROAD with a new BRIDGE OVER INDIAN CREEK to serve the community for the next s | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-09-30 | 2010-09-25 | 1019302 | 0.300
11034 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 3589004 | This project located on Barton Avenue From Frazier Avenue to Hixson Pike in Chattanooga will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and w | Pavement Improvement | 2010-02-12 | 2010-02-12 | 2010-10-30 | 2010-08-05 | 182164.62 | 0.780
11035 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 3603003 | This project located on Hickory Valley Road From Shallowford Road to SR-317 (Bonny Oaks Drive) in Chattanooga will provide a smoother riding surface for motorists, thus decreasing wear and tear on th | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-10-30 | 2010-08-09 | 290318.02 | 1.850
11036 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | HAWKINS |  | 01 | 3700028 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Okolona Road with a new Bridge over Alexander Creek to serve the community for the next se | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2010-06-01 | 2009-12-31 | 549433 | 0.100
11037 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 3942003 | This project located on Walton Ferry Road From West Main Street to Curtis Cross Roads in Hendersonville will provide a smoother riding surface for motorists, thus decreasing wear and tear on their au | Pavement Improvement | 2009-08-12 | 2009-08-12 | 2010-10-26 | 2010-10-31 | 536572.38 | 5.820
11038 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 3943003 | This project is for the development of design plans for a future bicycle and pedestrian facility project located on INDIAN LAKE BOULEVARD INTERSECTION AT SR-386 IN HENDERSONVILLE | Other | 2009-08-12 | 2009-08-12 | 2015-09-30 |  | 675830 | 0.000
11039 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 4032007 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Sam Cooper Boulevard with a new Bridge over Illinois Central and Union Pacific Railroads | Pavement Improvement | 2010-02-16 |  | 2011-06-18 | 2011-07-19 | 296056 | 0.000
11040 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 4147001 | This project located on North Mack Smith Road From SR-8 (Ringgold Road) in East Ridge to the Georgia State Line will provide a smoother riding surface for motorists, thus decreasing wear and tear on | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-31 | 2010-08-30 | 60867.72 | 0.270
11041 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | HUMPHREYS |  | 08 | 4300024 | This project is for the construction of a Welcome Center at and enhancement of the Interpretive Trail System at the Johnsonville State Historic Park | Transportation Enhancements | 2009-12-28 | 2009-12-28 | 2012-03-01 |  | 1456250 | 0.000
11042 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | JACKSON |  | 06 | 4400052 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Overton Cemetary Road with a new bridge over Roaring River to serve the community for the | Bridge Replacement | 2010-03-15 | 2010-03-15 | 2011-06-30 | 2011-06-08 | 430000 | 0.010
11043 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 4404077 | This project will rehabilitate the concrete pavement on I-440 from I-40 to I-24 in Nashville | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2010-05-31 | 2010-06-30 | 8505642.88 | 7.600
11044 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | JEFFERSON | MORRISTOWN | 03 | 4500025 | This project located on Agricultural Park Boulevard From US-25E to the Railroad Bridge in White Pine will provide a smoother riding surface for motorists, thus decreasing wear and tear on their autom | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2010-11-23 | 2010-11-15 | 57176.09 | 0.580
11045 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | LAKE |  | 08 | 4800012 | This streetscape beautification project includes landscaping, pedestrian amenities, lighting, upgrading/rehabilitating sidewalks and utility relocation in Downtown Ridgely. | Transportation Enhancements | 2010-07-06 | 2010-07-06 | 2011-03-01 |  | 179689 | 0.000
11046 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 4967003 | This project is for the construction of a bridge carrying Nashville and Eastern Railroad over Central Pike in Nashville | Pavement Widening | 2009-09-25 | 2009-09-25 | 2011-01-31 |  | 1000000 | 0.000
11047 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | LAWRENCE |  | 04 | 5000014 | This project will improve safety and reliability of the transportation system by replacing an older bridge on LONG BRANCH ROAD with a new BRIDGE OVER LONG BRANCH to serve the community for the next s | New Bridge Construction | 2009-04-06 | 2009-04-06 | 2010-05-15 | 2010-08-01 | 423673 | 0.000
11048 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | LAWRENCE |  | 04 | 5000015 | This project will improve safety and reliability of the transportation system by replacing an older bridge on PINEY ROAD with a new BRIDGE OVER PINEY BRANCH to serve the community for the next sever | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-01-01 | 2009-12-31 | 412870 | 0.000
11049 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 5012001 | This project located on KNIGHT-ARNOLD ROAD FROM CHERRY STREET TO MT. MORIAH ROAD IN MEMPHIS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, an | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2012-04-19 |  | 2212615 | 4.590
11050 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 5365001 | This project is for preparing and implementing a resurfacing project located on SOUTH WATER AVENUE FROM MAPLE STREET TO BUSH AVENUE IN GALLATIN to provide a smoother riding surface for motorists, thus | Pavement Improvement | 2009-08-12 | 2009-08-12 | 2011-02-19 | 2011-05-06 | 1466523.82 | 1.100
11051 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | MCNAIRY |  | 07 | 5500050 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SULPHUR SPRINGS ROAD with a new BRIDGE OVER MOSSES CREEK to serve the community for the n | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-07-15 | 2010-08-31 | 534583 | 0.100
11052 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | FAYETTE | MEMPHIS (AR-MS) | 07 | 5572001 | This project located on Fisherville Lake Road from Raleigh-LaGrange Road to SR-192 and Monterey Drive from the Shelby County line to Fisherville Lake Road will provide a smoother riding surface for mo | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2010-09-15 | 2010-09-15 | 352566 | 2.340
11053 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | MACON |  | 06 | 5600045 | This project will improve safety and reliability of the transportation system by replacing an older bridge on CARR BRANCH ROAD with a new BRIDGE OVER CARR CREEK to serve the community for the next se | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-05-31 | 2010-05-30 | 320737.22 | 0.000
11054 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | MACON |  | 06 | 5600046 | This project will improve safety and reliability of the transportation system by replacing an older bridge on West Wixtown Road with a new Bridge over the West Fork of Long Creek to serve the communit | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2009-12-01 | 2009-09-30 | 315643.69 | 0.000
11055 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | MADISON |  | 08 | 5700066 | This project will improve safety and reliability of the transportation system by replacing an older bridge on JOHN ANDERSON ROAD with a new BRIDGES OVER BRANCHS to serve the community for the next se | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2009-12-31 | 2009-12-15 | 340941.91 | 0.100
11056 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MEIGS |  | 03 | 6100021 | This project will improve safety and reliability of the transportation system by replacing an older bridge on LAMONTVILLE ROAD with a new BRIDGE OVER PRICE CREEK to serve the community for the next s | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-06-15 | 2010-05-31 | 604463 | 0.000
11057 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | MONROE |  | 02 | 6200022 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Belcher Gap Road with a new Bridge over Notchy Creek to serve the community for the next s | Bridge Replacement | 2009-03-03 | 2009-03-03 | 2009-11-30 | 2009-11-15 | 341498 | 0.100
11058 | Completed | C250 | Highway Infrastructure Investment Grant | TENNESSEE | MONROE |  | 02 | 6200023 | This project will improve safety and reliability of the transportation system by replacing an older bridge on GRIFFITH BRANCH ROAD with a new BRIDGE OVER NOTCHY CREEK to serve the community for the n | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2009-12-31 | 2009-12-31 | 760048 | 0.000
11059 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | PERRY |  | 07 | 6800022 | This streetscape beautification project in Linden includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 2009-09-25 | 2010-03-01 | 2010-12-31 |  | 1602008 | 0.000
11060 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SEVIER |  | 01 | 7800053 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ROARING FORK EXT. ROAD with a new BRIDGE OVER ROARING FORK CREEK IN GATLINBURG to serve t | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-06-15 | 2010-03-31 | 258916 | 0.000
11061 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SEVIER |  | 01 | 7800054 | This project will improve safety and reliability of the transportation system by replacing an older bridge on OLD NEWPORT HIGHWAY with a new BRIDGE OVER EAST FORK LITTLE PIGEON RIVER to serve the com | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-07-15 | 2010-05-31 | 568065 | 0.000
11062 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SEVIER |  | 01 | 7800055 | This project will improve safety and reliability of the transportation system by replacing an older bridge on LECONTE STREET with a new BRIDGE OVER WEST PRONG LITTLE PIGEON RIVER IN GATLINBURG to ser | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-07-31 | 2010-11-30 | 1338750 | 0.000
11063 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SEVIER |  | 01 | 7800056 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ROCKY FLATS ROAD with a new BRIDGE OVER DUNN CREEK to serve the community for the next se | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-07-15 | 2010-06-30 | 611328 | 0.000
11064 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | STEWART |  | 08 | 8100009 | This project is for the construction of a new visitors' center in Stewart County on Highway 79 | Transportation Enhancements | 2009-05-14 | 2009-05-14 | 2010-08-25 | 2010-08-05 | 1045000 | 0.000
11065 | Completed | C950 | Ferryboat | TENNESSEE | STEWART |  | 08 | 8100011 | This project will construct landings at each side of the Cumberland River and also acquire a barge to carry vehicles. A new terminal for docking the ferry barge and tug boat will also be constructed | Other | 2010-07-09 | 2010-08-01 | 2012-09-30 | 2011-05-25 | 3000000 | 0.000
11066 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 8300072 | This project is for the development of design plans for the future construction of a greenway facility on Lower Station Camp Creek Road in Gallatin. | Other | 2010-02-17 | 2010-02-25 | 2011-07-01 |  | 148241 | 0.000
11067 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | TIPTON |  | 08 | 8400067 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ROBERT JOHNSON ROAD with a new BRIDGE OVER DRAINAGE CANAL to serve the community for the | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2009-12-31 | 2009-12-10 | 289775 | 0.000
11068 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | TIPTON |  | 08 | 8400068 | This project will improve safety and reliability of the transportation system by replacing an older bridge on BUCKSNORT ROAD with a new BRIDGE OVER MATHIS CREEK to serve the community for the next se | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-05-15 | 2010-06-30 | 806929.98 | 0.000
11069 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | TIPTON |  | 08 | 8400069 | This project will improve safety and reliability of the transportation system by replacing an older bridge on ANTIOCH HIGHWAY with a new BRIDGE OVER FLAT CREEK to serve the community for the next sev | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-06-15 | 2009-12-24 | 628356.72 | 0.000
11070 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | TIPTON |  | 08 | 8400070 | This project will improve safety and reliability of the transportation system by replacing an older bridge on PORTERSVILLE ROAD with a new BRIDGE OVER HEBRON BRANCH to serve the community for the next | Bridge Replacement | 2009-05-15 | 2009-05-15 | 2010-01-15 | 2009-12-31 | 479572.25 | 0.100
11071 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | TIPTON |  | 08 | 8400073 | This streetscape beautification project includes landscaping, pedestrian amenities, lighting, upgrading/rehabilitating sidewalks and utility relocation in Brighton. | Transportation Enhancements | 2010-07-23 | 2010-07-23 | 2011-06-13 |  | 265288 | 0.000
11072 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | TROUSDALE |  | 06 | 8500018 | This streetscape beautification project in Hartsville includes elevator upgrades in the Hartsville Courthouse, rehabilitating/upgrading sidewalks, installing/upgrading lighting, pedestrian amenities a | Transportation Enhancements | 2009-05-13 | 2009-05-21 | 2010-04-15 | 2010-05-21 | 367083 | 0.000
11073 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WASHINGTON |  | 01 | 9000045 | This project will improve safety and reliability of the transportation system by replacing an older bridge on BOB DAVIS ROAD with a new BRIDGE OVER CSX RAILROAD to serve the community for the next se | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-05-31 | 2010-06-20 | 953845 | 0.000
11074 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | BLOUNT | KNOXVILLE | 02 | 9101010 | This project is for traffic signal system upgrades at various locations in Alcoa/Maryville | Safety/Traffic Management | 2010-02-10 | 2010-02-10 | 2011-08-14 |  | 1211503 | 0.000
11075 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | BLOUNT | KNOXVILLE | 02 | 9101011 | This project is for the construction of a new pedestrian bridge over State Route 115 in Alcoa for the Culton Creek Greenway | Transportation Enhancements | 2009-09-25 | 2009-09-25 | 2010-10-30 |  | 1600000 | 0.000
11076 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | BLOUNT | KNOXVILLE | 02 | 9101012 | This resurfacing project located on CALDERWOOD STREET FROM JOULE STREET TO THE CITY LIMITS OF ALCOA/SINGLETON STATION ROAD FROM SR-115 (ALOCA HWY) TO THE CITY LIMITS OF ALCOA will provide a smoother | Pavement Improvement | 2009-08-07 | 2009-08-07 | 2011-08-14 | 2011-05-08 | 455145.14 | 4.100
11077 | Underway | C200 | Highway Infrastructure Investment Grant | TENNESSEE | SULLIVAN | BRISTOL TN- VA | 01 | 9102007 | This project located on OLD JONESBORO ROAD FROM THE CITY LIMITS TO GALWAY ROAD/EXIDE DRIVE FROM SR-34 (US-11E) TO EDISON CIRCLE/ASH STREET FROM MARTIN LUTHER KING JR. BOULEVARD TO SR-34 (US-421)/BROAD | Pavement Improvement | 2010-01-07 | 2010-01-07 | 2015-09-30 |  | 789911.5 | 5.100
11078 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | CARTER | JOHNSON CITY | 01 | 9103013 | This project will widen LYNN AVENUE from 2 lanes to 5 lanes including bike lanes and sidwalks FROM SR-67 (BROAD STREET) TO EAST ELK AVENUE IN ELIZABETHTON | Pavement Improvement | 2009-07-10 | 2009-07-10 | 2011-01-31 | 2010-12-15 | 1212573 | 0.170
11079 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | GREENE |  | 01 | 9104011 | This project will improve safety and reliability of the transportation system by replacing an older bridge on HANNAH STREET (OLD TUSCULUM ROAD) with a new BRIDGE OVER HOLLEY CREEK IN GREENEVILLE to s | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2009-12-31 | 2009-10-31 | 326823.3 | 0.000
11080 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | JEFFERSON | MORRISTOWN | 03 | 9106011 | This project located on North Russell Avenue From SR-92 to Old Andrew Johnson Highway in Jefferson City/North Chucky Pike From Clearbrook Drive to Old Andrew Johnson Highway in Jefferson City/North S | Pavement Improvement | 2009-08-07 | 2009-08-07 | 2010-11-23 | 2010-11-15 | 316465.77 | 2.940
11081 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | WASHINGTON | JOHNSON CITY | 01 | 9107009 | This project is for the construction of a bicycle and pedestrian path in Johnson City including landscaping and pedestrian amenities | Transportation Enhancements | 2009-09-03 | 2009-09-03 | 2010-07-15 | 2010-10-03 | 400000 | 0.000
11082 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | WASHINGTON | JOHNSON CITY | 01 | 9107025 | This project located on BAXTER STREET FROM SR-400 (EAST WATAUGA AVENUE) TO MOUNTCASTLE DRIVE/EAST FAIRVIEW AVENUE FROM EAST OAKLAND AVENUE TO SR-400 (EAST UNAKA AVENUE)/PEOPLES STREET/BROWNS MILL ROAD | Pavement Improvement | 2010-01-08 | 2010-01-08 | 2010-11-16 | 2010-10-16 | 823368 | 2.910
11083 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | SULLIVAN | KINGSPORT (VA) | 01 | 9108031 | This project located on NORTH EASTMAN ROAD FROM LINCOLN STREET TO EAST STONE DRIVE/CLINCHFIELD STREET FROM WEST CENTER STREET TO WEST STONE DRIVE/EAST CENTER STREET FROM FORT HENRY DRIVE TO MEMORIAL B | Pavement Improvement | 2009-09-22 | 2009-09-22 | 2010-05-30 | 2010-05-25 | 1499133 | 3.750
11084 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | SULLIVAN | KINGSPORT (VA) | 01 | 9108032 | This project located on OREBANK ROAD FROM MEMORIAL BOULEVARD TO LAMBERTH STREET/BLOOMINGDALE PIKE FROM WEST STONE DRIVE TO GRAVELY ROAD IN KINGSPORT will provide a smoother riding surface for motorist | Pavement Improvement | 2009-09-22 | 2009-09-22 | 2010-05-30 | 2010-05-25 | 601184.58 | 3.650
11085 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | KNOX | KNOXVILLE | 02 | 9109130 | This project will widen CAMPBELL STATION ROAD from 4 lanes to 5 lanes FROM PARKSIDE DRIVE TO JAMESTOWN BOULEVARD IN FARRAGUT | Pavement Widening | 2009-05-15 | 2009-05-15 | 2010-12-31 | 2010-12-15 | 2495375 | 0.940
11086 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | KNOX | KNOXVILLE | 02 | 9109132 | This project is for the construction of the Papermill Bluff bicycle/pedestrian pathway from Papermill Road to Weisgarber Road that includes landscaping. | Transportation Enhancements | 2009-07-17 | 2009-07-17 | 2011-03-04 |  | 810882 | 0.000
11087 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | LOUDON | KNOXVILLE | 02 | 9111003 | This resurfacing project located on ADESA BOULEVARD ADESA BOULEVARD, FROM OLD HWY 95 TO SR-73 (US-321) IN LENOIR CITY/BROWDER HOLLOW ROAD/ JOHNSTON DRIVE FROM SR-2 (US-11) TO NEAR JOHNSON CIRCLE IN LE | Pavement Improvement | 2009-09-22 | 2009-09-22 | 2010-10-02 | 2010-11-20 | 399084 | 4.240
11088 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | LOUDON | KNOXVILLE | 02 | 9111005 | This streetscape project is for landscaping and scenic beautification on Creekwood Park Boulevard from SR-73 (US-321) to SR-1 (US-70) in Lenoir City | Transportation Enhancements | 2010-02-08 | 2010-02-08 | 2010-12-24 | 2011-06-21 | 544404.69 | 1.390
11089 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | HAMBLEN | MORRISTOWN | 01 | 9113014 | This resurfacing project located on EAST 2ND NORTH STREET FROM ANDERSON STREET TO NORTH CUMBERLAND STREET IN MORRISTOWN will provide a smoother riding surface for motorists, thus decreasing wear and t | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2010-11-23 | 2011-06-09 | 315334.88 | 0.800
11090 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | ANDERSON |  | 03 | 9117011 | This project will improve safety and reliability of the transportation system by replacing an older bridge on YARNELL ROAD with a new BRIDGE OVER LITTLE DISMAL CREEK IN CLINTON to serve the community | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-07-31 | 2010-05-09 | 286734 | 0.100
11091 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | MCMINN |  | 02 | 9201011 | This streetscape beautification project in Athens includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 2009-09-01 | 2009-09-01 | 2010-12-10 |  | 1133078 | 0.000
11092 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9202095 | This project is for the construction of a new trail and bikeway along South Chickamauga Creek in Chattanooga | Transportation Enhancements | 2009-09-02 | 2010-02-01 | 2010-12-01 |  | 500000 | 0.000
11093 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9202098 | This project is for the replacement of traffic signals at various locations in Chattanooga. | Safety/Traffic Management | 2010-02-09 | 2010-02-09 | 2011-06-29 |  | 900000 | 0.000
11094 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9202101 | This project located on Airport Road From Shepherd Road to Shallowford Road in Chattanooga & Shepherd Road From SR-153 to Airport Road in Chattanooga will provide a smoother riding surface for motori | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2010-10-30 | 2010-09-14 | 650198.25 | 2.510
11095 | Underway | C200 | Highway Infrastructure Investment Grant | TENNESSEE | BRADLEY | CLEVELAND | 03 | 9203013 | This resurfacing project located on FREEWILL ROAD FROM CUMBERLAND HILLS CIRCLE TO NORTH OF COTTONWOOD BEND IN CLEVELAND will provide a smoother riding surface for motorists, thus decreasing wear and t | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2015-09-30 |  | 489143 | 4.760
11096 | Underway | C200 | Highway Infrastructure Investment Grant | TENNESSEE | BRADLEY | CLEVELAND | 03 | 9203014 | This resurfacing project located on RAIDER DRIVE FROM KEITH STREET TO PEERLESS ROAD IN CLEVELAND will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobile | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2015-09-30 |  | 432151 | 0.960
11097 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | BRADLEY | CLEVELAND | 03 | 9203015 | This project is for the construction of a new comfort station that will include restrooms and drinking fountain for the Mouse Creek Greenway | Transportation Enhancements | 2009-11-24 | 2009-11-24 | 2010-11-29 | 2010-12-23 | 92431.94 | 0.000
11098 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | BRADLEY | CLEVELAND | 03 | 9203016 | This project is for the construction of pedestrian amenities on various streets in Cleveland | Transportation Enhancements | 2010-02-08 | 2010-02-08 | 2010-12-19 | 2011-01-25 | 171433.48 | 0.000
11099 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9212001 | This project is for the installation of traffic signals on at the School Zones in Collegedale | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-11-29 | 2010-09-07 | 11850 | 0.000
11100 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9212002 | This project is for the replacement of traffic signals at various locations in Collegedale. | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2011-05-31 |  | 3427 | 0.000
11101 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9212003 | This project is for the installation of sidewalk lighting at various locations in Collegedale. | Safety/Traffic Management | 2010-02-10 | 2010-02-10 | 2010-11-29 | 2011-04-26 | 128918 | 0.000
11102 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9212004 | This project located on multiple projects (Tallant Road From SR-317 (Apison Pike) to McDonald Road in Collegedale/Prospect Church Road From University Drive to Borzoi Lane in Collegedale/Standifer Ga | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2015-09-30 |  | 826424 | 6.000
11103 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9212005 | This project is for the construction of sidewalks and a greenway on Swinyar Drive and University Drive in Collegedale | Transportation Enhancements | 2010-02-16 | 2010-02-16 | 2010-11-29 | 2011-04-26 | 152987 | 0.000
11104 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9213001 | This project is for the installation of traffic signals on at the School Zones in East Ridge | Safety/Traffic Management | 2010-02-10 | 2010-02-10 | 2010-10-15 | 2010-08-16 | 33975.96 | 0.000
11105 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9213003 | This project is for the construction of sidewalks on Camp Jordan Parkway From Camp Jordan Road to near SR-8 (Ringgold Road) in East Ridge | Transportation Enhancements | 2010-02-09 | 2010-02-09 | 2010-09-13 | 2010-09-01 | 157670.74 | 1.390
11106 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9214001 | This project located on Dayton Boulevard Dayton Boulevard from Signal Mountain Boulevard to Memorial Drive in Red Bank & Lupton Drive From Dayton Boulevard to the City Limits in Red Bank will provide | Pavement Improvement | 2010-02-12 | 2010-02-16 | 2010-11-29 |  | 473471 | 4.270
11107 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9214002 | This resurfacing project is located on two roadways in Red Bank: Dayton Boulevard from Signal Mountain Boulevard to Memorial Drive and Lupton Drive from Dayton Boulevard to the city limits. This proj | Transportation Enhancements | 2010-02-16 | 2010-02-16 | 2011-02-22 |  | 691314 | 0.000
11108 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 9215001 | This project located on North Palisades Drive From Wilder Drive to the City Limits in Signal Mountain & Various Sections on James Boulevard will provide a smoother riding surface for motorists, thus | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2010-05-18 | 2011-03-17 | 436531 | 1.780
11109 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WHITE |  | 04 | 9300039 | This project will improve safety and reliability of the transportation system by replacing an older bridge on FANCHER MILL ROAD with a new BRIDGE OVER TAYLOR CREEK to serve the community for the next | Bridge Replacement | 2009-05-15 | 2009-05-15 | 2010-10-10 | 2010-09-28 | 891195 | 0.200
11110 | Underway | C200 | Highway Infrastructure Investment Grant | TENNESSEE | MONTGOMERY | CLARKSVILLE (KY) | 07 | 9301023 | This project located on LAFAYETTE ROAD FROM SR-374 TO THE FT. CAMPBELL BOUNDARY/ CUNNINGHAM LANE FROM LAFAYETTE ROAD TO SR-12 (US-41A)/ CROSSLAND AVENUE FROM S. RIVERSIDE DRIVE TO MADISON STREET/NEEDM | Pavement Improvement | 2010-02-18 | 2010-02-18 | 2015-09-30 |  | 1462580 | 5.780
11111 | Underway | C200 | Highway Infrastructure Investment Grant | TENNESSEE | MONTGOMERY | CLARKSVILLE (KY) | 07 | 9301028 | This project located on NEEDMORE ROAD FROM ELKMONT DRIVE TO TINY TOWN ROAD and TROUGH SPRINGS ROAD FROM SANGO ROAD TO SR-76 IN CLARKSVILLE will provide a smoother riding surface for motorists, thus de | Pavement Improvement | 2010-09-10 | 2010-09-10 | 2015-09-30 |  | 579489 | 3.940
11112 | Underway | C200 | Highway Infrastructure Investment Grant | TENNESSEE | MAURY |  | 04 | 9302016 | This project will improve safety and reliability of the transportation system by replacing an older bridge on INDUSTRIAL PARK ROAD with a new BRIDGE OVER THE DUCK RIVER IN COLUMBIA to serve the commun | Bridge Replacement | 2009-05-15 | 2009-05-15 | 2011-07-31 |  | 2786882 | 0.000
11113 | Completed | C220 | Highway Infrastructure Investment Grant | TENNESSEE | DICKSON |  | 08 | 9303010 | This project includes the construction and installation of transportation exhibits in the Halbrook Hotel Railroad Museum in Dickson | Transportation Enhancements | 2009-11-13 | 2010-01-01 | 2010-06-14 | 2010-08-10 | 171431.18 | 0.000
11114 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | WILLIAMSON | NASHVILLE-DAVIDSON | 07 | 9305024 | This project is for the development of design plans for a future installation of video technology in Franklin to expand the existing traffic monitoring system and to assist incident management and qui | Safety/Traffic Management | 2010-01-07 | 2010-01-07 | 2011-09-05 |  | 1203242 | 0.000
11115 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 9306012 | This project is for the construction of a bicycle and pedestrian path, the Town Creek Greenway, in Gallatin including landscaping, pedestrian amenities, lighting, upgrading/rehabilitating sidewalks an | Transportation Enhancements | 2010-01-05 | 2010-01-07 | 2010-09-30 | 2010-11-11 | 1000000 | 0.000
11116 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 9306014 | This streetscape beautification project in Gallatin includes landscaping, pedestrian amenities, lighting, upgrading/rehabilitating sidewalks and utility relocation | Transportation Enhancements | 2009-10-30 | 2009-10-30 | 2011-03-12 | 2011-06-09 | 517348 | 0.000
11117 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | RUTHERFORD | MURFREESBORO | 06 | 9311020 | This project is for the installation of video technology to expand the existing traffic monitoring system and to assist incident management and quick clearance response | Safety/Traffic Management | 2010-02-18 | 2010-02-18 | 2011-05-11 | 2011-10-20 | 1000000 | 0.000
11118 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312090 | This project located on TROUSDALE DRIVE FROM HARDING PLACE TO HOGAN ROAD/ABBOTT MARTIN ROAD FROM HILLSBORO PIKE TO THE CITY LIMITS/BOWLING AVENUE FROM WEST END AVENUE TO WOODLAWN AVENUE /HICKORY HOLLO | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2011-04-04 | 2011-03-24 | 1502724.89 | 7.460
11119 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312091 | This project located on JEFFERSON STREET FROM RAILROAD BRIDGE TO DR. DB TODD, JR./ELLISTON PLACE FROM WEST END AVENUE TO CHURCH STREET BOULEVARD/CHURCH STREET FROM 21ST AVENUE NORTH TO 16TH AVENUE NOR | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2011-04-04 | 2011-05-20 | 1521321 | 6.460
11120 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312092 | This project located on CENTRAL PIKE FROM DODSON CHAPEL ROAD TO OLD HICKORY BOULEVARD/SOUTH GRAYCROFT AVENUE FROM OLD HICKORY BOULEVARD TO DUE WEST AVENUE/ELM HILL PIKE FROM ATRIUM WAY TO DONELSON PIK | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2011-04-04 | 2011-05-20 | 1728821 | 7.570
11121 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312093 | This project will provide for the signal timing upgrades at various locations in Nashville | Safety/Traffic Management | 2009-11-04 | 2009-11-04 | 2010-12-31 | 2011-06-10 | 762687 | 0.000
11122 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312094 | This project is for the optimization of traffic signal timing at various intersections in Nashville | Safety/Traffic Management | 2009-09-11 | 2009-09-11 | 2011-10-31 |  | 998984 | 0.000
11123 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312095 | This project is for the construction of a new bicycle and pedestrian path from the levee at Metro Center to Clifton Avenue in Nashville | Transportation Enhancements | 2009-09-01 | 2009-09-01 | 2011-07-05 |  | 1074608 | 0.000
11124 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | WILSON | NASHVILLE-DAVIDSON | 05 | 9312096 | This project is for the construction of a new greenway on West Division Street From the Music City Star Station to 4th Street in Mount Juliet. | Transportation Enhancements | 2009-09-23 | 2009-09-23 | 2010-11-15 | 2010-12-13 | 416892.88 | 0.000
11125 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 9312097 | This project is for intersection improvements including traffic light and crosswalk signal upgrades at various intersections on Harding Place (SR-255), Bell Road (SR-254), Nolensville Pike (SR-11), an | Safety/Traffic Management | 2009-11-13 | 2009-11-13 | 2011-01-26 |  | 791707 | 0.000
11126 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | ROBERTSON | NASHVILLE-DAVIDSON | 06 | 9316009 | This project will improve safety and reliability of the transportation system by replacing an older bridge on North Main Street with a new bridge over Sulphur Fork Creek in Springfield to serve the co | Bridge Replacement | 2010-07-01 | 2010-07-01 | 2012-01-15 | 2011-09-27 | 805000 | 0.000
11127 | Underway | C200 | Highway Infrastructure Investment Grant | TENNESSEE | RUTHERFORD | MURFREESBORO | 06 | 9317007 | This project will widen WALDRON ROAD/PARTHENON BOULEVARD from 3 lanes to 5 lanes FROM NORTH OF INDUSTRIAL DRIVE/ENTERPRISE BOULEVARD TO SR-1 | Pavement Widening | 2009-09-17 | 2009-09-17 | 2011-11-30 |  | 1000000 | 2.190
11128 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SUMNER | NASHVILLE-DAVIDSON | 06 | 9319001 | This project located on South Russell Street From Main Street to Lynnwood Drive in Portland will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, a | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-31 |  | 360631.27 | 0.690
11129 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | ROBERTSON | NASHVILLE-DAVIDSON | 06 | 9320001 | This project is for upgrades to traffic signals along SR-75 and SR-41(US-31W) in White House. | Safety/Traffic Management | 2010-02-10 | 2010-02-10 | 2012-01-01 |  | 367127 | 0.000
11130 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | TIPTON |  | 08 | 9403006 | This streetscape beautification project includes landscaping, pedestrian amenities, lighting, and upgrading/rehabilitating sidewalks in Covington Square. | Transportation Enhancements | 2010-07-06 | 2010-07-06 | 2011-04-29 |  | 176860 | 0.000
11131 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | MADISON | JACKSON | 08 | 9406007 | This project is for the construction of curbs and addition of sidewalks on SR-198 (East Chester Street) from US-70 to Holland Avenue in Jackson | Pavement Widening | 2010-02-04 | 2010-06-03 | 2010-12-15 | 2011-06-27 | 1500058 | 0.580
11132 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | MADISON | JACKSON | 08 | 9406008 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SECOND STREET with a new BRIDGE OVER ANDERSON BRANCH IN JACKSON to serve the community f | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-05-20 | 2010-05-16 | 375956 | 0.000
11133 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | WEAKLEY |  | 08 | 9408008 | This streetscape beautification project in Martin includes elevator upgrades in the Hartsville Courthouse, rehabilitating/upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and l | Transportation Enhancements | 2009-09-14 | 2009-09-14 | 2010-08-26 |  | 1374018 | 0.000
11134 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9409135 | This resurfacing project located on HACKS CROSS ROAD FROM STATE LINE ROAD TO THE MEMPHIS CITY LIMITS/HOUSTON LEVEE ROAD FROM THE WOLD RIVER BRIDGE TO WOLF RIVER PARKWAY/WALNUT GROVE ROAD FROM ROCKY PO | Pavement Improvement | 2009-07-17 | 2010-02-11 | 2015-09-30 |  | 2868663 | 28.940
11135 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9409137 | This resurfacing project located on AIRLINE ROAD FROM THE C.S.X. RAILROAD TO I-40 IN ARLINGTON to provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, a | Pavement Improvement | 2010-02-19 | 2010-05-18 | 2015-09-30 |  | 424014 | 4.340
11136 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9409140 | This project is for the construction of a bicycle/pedestrian pathway on Canada Road that includes landscaping. | Transportation Enhancements | 2009-05-27 | 2009-06-09 | 2010-12-01 |  | 1208699 | 2.500
11137 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9409147 | This project located on several locations in Memphis (Millbranch Road from I-240 to Riverbrook Drive; Ball Road from Norris Road to Ketchum Road; Ross Road from Shelby Drive to Winchester Road; Warin | Pavement Improvement | 2009-02-19 | 2010-02-12 | 2012-09-30 |  | 4011120 | 10.450
11138 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9409148 | This resurfacing project located on CHELSEA AVENUE FROM NORTH WATKINS STREET TO FAIRFAX STREET IN MEMPHIS/SEMMES STREET FROM WILDROSE STREET TO WAVERLY AVENUE IN MEMPHIS will provide a smoother ridin | Pavement Improvement | 2009-02-19 | 2010-02-11 | 2012-03-29 |  | 2266064 | 5.400
11139 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9409149 | This resurfacing project located on MADISON AVENUE FROM NORTH CLEVELAND STREET TO EAST PARKWAY IN MEMPHIS/S. PARKWAY EAST FROM SOUTH LAUDERDALE STREET TO SR-3 (ELVIS PRESLEY BOULEVARD) IN MEMPHIS/S. F | Pavement Improvement | 2009-02-19 | 2010-02-11 | 2012-03-21 |  | 2823044 | 5.910
11140 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9409150 | This project is for the construction of hand rails on two bridges, Horn Lake Bridge over Johnston Railroad Yard and Rivergate Bridge over Nonconnah Creek, in Memphis | Safety/Traffic Management | 2009-02-19 | 2010-02-11 | 2011-06-18 | 2011-05-31 | 183355 | 0.000
11141 | Underway | C240,C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9409156 | This project will improve safety and reliability of the transportation system by replacing an older bridge on Holmes Street with a new bridge over the CSX railroad in Memphisto serve the community for | Bridge Replacement | 2010-09-17 | 2010-12-06 | 2011-09-30 |  | 1192481 | 0.000
11142 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9411006 | This resurfacing project located on FROM PAUL BARRET PARKWAY TO THE CITY LIMITS OF MILLINGTON/CHURCH STREET FROM NAVY ROAD TO PAUL BARRET PARKWAY IN MILLINGTON/EASLEY ROAD FROM HWY 51 TO NAVY ROAD IN | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2010-11-30 |  | 1310597 | 6.080
11143 | Underway | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9411007 | This project consists of repairs to the bridge over Big Creek on Raleigh-Millington Road in Millington | Other | 2009-07-17 | 2009-07-17 | 2010-07-30 |  | 7777.75 | 0.000
11144 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9411008 | This resurfacing project located on BIG CREEK CHURCH ROAD FROM HWY 51 TO RALIEGH-MILLINGTON ROAD IN MILLINGTON will provide a smoother riding surface for motorists, thus decreasing wear and tear on th | Other | 2009-07-17 | 2009-07-17 | 2010-07-30 | 2010-03-25 | 31917.5 | 2.440
11145 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9411009 | This streescape project is for landscaping and scenic beautification on Navy Road from US-51 to east of Veterans Parkway in Millington | Transportation Enhancements | 2009-07-17 | 2009-07-17 | 2011-01-01 | 2011-01-29 | 661569 | 2.500
11146 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | HENRY |  | 08 | 9412008 | This project is for the construction of a pedestrian plaza in Paris including landscaping, pedestrian amenities, lighting, upgrading/rehabilitating sidewalks. | Transportation Enhancements | 2010-07-06 | 2010-07-06 | 2011-03-01 |  | 245142 | 0.000
11147 | Underway | C220 | Highway Infrastructure Investment Grant | TENNESSEE | LAUDERDALE |  | 08 | 9418009 | This streetscape beautification project in Ripley includes rehabilitating and upgrading sidewalks, installing/upgrading lighting, pedestrian amenities and landscaping. | Transportation Enhancements | 2009-05-14 | 2009-11-01 | 2010-08-20 |  | 1101917 | 0.000
11148 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9419003 | This resurfacing project located on ST. ELMO ROAD FROM MEMPHIS-ARLINGTON ROAD TO KIRBY WHITTEN ROAD IN BARTLETT/ELMORE PARK ROAD FROM ELMORE PARK TO YALE ROAD IN BARTLETT/SYCAMORE VIEW ROAD FROM STAGE | Other | 2009-07-17 | 2009-07-17 | 2010-06-30 | 2010-05-31 | 42420 | 9.580
11149 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9419004 | This resurfacing project located on BARTLETT BOULEVARD FROM THE SOUTH CITY LIMITS TO MEMPHIS-ARLINGTON ROAD IN BARTLETT/ALTRURIA ROAD FROM SUMMER AVENUE TO YALE ROAD IN BARTLETT will provide a smooth | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2011-02-12 | 2011-01-04 | 1478966.73 | 8.420
11150 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 9420002 | This project is for the preparation and actual replacement of existing roadway pavement including sidewalks on Farmington Boulevard from Allenby Road to Wolf River Boulevard in Germantown. | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2010-11-29 | 2010-10-29 | 1956227.3 | 2.060
11151 | Completed | C490 | OJT/SS | TENNESSEE | STATEWIDE |  |  | 9900013 | The On-the-Job Training/Supportive Services program will train ready, willing and able individuals for entry or re-entry into the workforce. | Other | 2010-02-01 | 2010-02-01 | 2011-01-31 | 2011-01-31 | 615184.16 | 0.000
11152 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | COLLIN |  | 03 | 0094179 | In order to enhance the community, the City of Richardson will construct a sidewalk to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2010-02-22 | 2010-03-08 | 2012-01-31 |  | 558650 | 2.200
11153 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DENTON |  | 26 | 0095067 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge on county road. | Bridge Replacement | 2009-07-02 | 2009-08-26 | 2010-05-01 | 2010-07-12 | 354535.93 | 0.070
11154 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | EL PASO | EL PASO | 16 | 0095154 | In order to enhance the community, the City of El Paso will construct bridge canopies to accommodate bicycle and pedestrians transportation and perform landscaping and other scenic beautification on L | Transportation Enhancements | 2010-08-02 | 2010-08-23 | 2011-09-01 |  | 1717143 | 1.100
11155 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 26 | 0097217 | In order to enhance the community, the City of North Richland Hills will construct a hike and bike trail to accommodate bicycle transportation and pedestrians on city street. | Transportation Enhancements | 2010-08-04 | 2010-08-05 | 2011-04-01 |  | 422000.08 | 0.591
11156 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 18 | 0097224 | In order to enhance the community, the Texas Department of Transportation will construct a hike and bike trail extension to accommodate bicycle transportation and pedestrians on various highways and r | Transportation Enhancements | 2010-06-24 | 2010-07-21 | 2012-02-29 |  | 1622074 | 2.235
11157 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | DALLAS | DALLAS-FORT WORTH | 30 | 0097253 | In order to enhance the community, the City of Dallas will construct a trestle bridge hike and bike trail to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2010-07-01 | 2010-07-12 | 2012-03-31 |  | 3547603 | 0.857
11158 | Completed | C200,C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 10 | 0099026 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will construct a new roadway on county road. | New Construction | 2009-09-28 | 2009-10-28 | 2010-08-16 | 2010-06-29 | 1617670.84 | 0.503
11159 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 0099550 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct to a four lane divided highway on city street. | Pavement Widening | 2010-05-24 | 2010-06-09 | 2012-06-09 | 2011-07-18 | 5491472.07 | 0.917
11160 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | WILLIAMSON | AUSTIN | 31 | 08TX001 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway to widen to four lanes on Ranch-To-Market 1431. | Pavement Improvement | 2010-02-08 | 2010-03-08 |  |  | 5083603.7 | 0.790
11161 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON | BROWNSVILLE | 27 | 1108001 | In order to enhance the transportation system, Cameron County will construct a new railroad at a new location. | Other | 2010-12-06 | 2010-12-13 | 2011-12-28 |  | 7809328 | 6.000
11162 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | CHAMBERS |  | 14 | 2000065 | In order to enhance the community, the Texas Department of Transportation will construct a new visitor center and perform landscaping and other scenic beautification on Interstate Highway 10. | Transportation Enhancements | 2009-10-16 | 2010-02-15 | 2011-02-28 |  | 11039974.07 | 0.001
11163 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 21 | 2000148 | In order to improve mobility in a metropolitan area, the City of San Antonio will reconstruct the roadway to add an additional lane on city street. | Pavement Widening | 2010-03-15 | 2010-03-15 | 2010-11-30 | 2010-11-12 | 500000 | 0.110
11164 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | NAVARRO |  | 06 | 2000293 | In order to improve safety, the Texas Department of Transportation will reconstruct a safety rest area on Interstate Highway 45. | Transportation Enhancements | 2009-09-28 | 2009-10-08 | 2011-09-30 |  | 11770092.74 | 1.231
11165 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | DALLAS |  | 30 | 2000555 | In order to enhance the community, the City of Lancaster will perform landscaping and other scenic beautification on various highways and roads. | Transportation Enhancements | 2010-02-11 | 2010-03-01 | 2011-05-30 | 2011-05-21 | 423839 | 0.001
11166 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 18 | 2000597 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on city street. | Transportation Enhancements | 2009-12-04 | 2009-12-10 | 2011-05-31 | 2010-08-20 | 701486.99 | 0.130
11167 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | Multiple | 2000624 | In order to enhance the community in a metropolitan area, the City of San Antonio will construct a hike and bike trail to accommodate bicycle transportation and pedestrians on city street. | Transportation Enhancements | 2010-06-28 | 2010-06-28 | 2012-01-31 |  | 234905 | 2.900
11168 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | LUBBOCK | LUBBOCK | 19 | 2001597 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will widen the existing roadway to six main lanes on Loop 289. | Pavement Widening | 2010-04-05 | 2010-04-05 | 2011-12-01 | 2011-11-21 | 6546325 | 0.001
11169 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS |  | 10 | 2002109 | In order to enhance the community, the City of Austin will construct a trail to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2010-05-24 | 2010-06-02 | 2011-05-23 |  | 1826571.29 | 0.001
11170 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | WILLIAMSON |  | 31 | 2002110 | In order to enhance the community, the City of Hutto will construct a trail to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2009-06-23 | 2009-10-05 | 2010-12-30 | 2010-01-31 | 331580.8 | 0.001
11171 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | DALLAS | DALLAS-FORT WORTH | Multiple | 2002126 | In order to enhance the community, the Texas Department of Transportation will construct pedestrian bridge on various highways and roads. | Transportation Enhancements | 2010-04-13 | 2010-10-02 |  | 2011-05-27 | 1038717.18 | 0.001
11172 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | DALLAS | DALLAS-FORT WORTH | 32 | 2002128 | In order to enhance the community, the City of Dallas will construct a link between two trails to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2011-02-08 | 2011-02-14 | 2012-01-31 | 2011-12-28 | 343229.68 | 0.789
11173 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | DALLAS | DALLAS-FORT WORTH | 30 | 2002129 | In order to enhance the community, the Texas Department of Transportation will construct a hike and bike trail to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2009-08-19 | 2009-09-10 | 2010-12-01 | 2011-01-19 | 1786702.8 | 2.372
11174 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | PARKER |  | 12 | 2002138 | In order to enhance the community, the City of Weatherford will construct a hike and bike trail to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2010-07-12 | 2010-07-12 | 2011-04-24 |  | 2015200 | 0.100
11175 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2002141 | In order to enhance the community, the Texas Department of Transportation will construct a hike and bike trail to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2010-04-19 | 2010-04-19 | 2010-11-01 | 2011-10-13 | 1059769.58 | 2.419
11176 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 09 | 2002154 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on various highways and roads. | Transportation Enhancements | 2010-04-22 | 2010-06-02 | 2011-09-30 | 2010-09-22 | 438941.6 | 1.760
11177 | Underway | C220,C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2002160 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will construct a facility to accommodate bicycle transportation and pedestrians on county road. | Transportation Enhancements | 2010-12-06 | 2011-04-04 | 2012-02-29 |  | 617646.38 | 1.737
11178 | Underway | C220,C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 20 | 2002184 | In order to enhance the community, the City of San Antonio will construct hike and bike trails to accommodate bicycle transportation and pedestrians on city street. | Transportation Enhancements | 2010-05-26 | 2010-05-26 | 2012-01-31 |  | 1604343.6 | 2.700
11179 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | SHERMAN |  | 13 | 2002207 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on various highways and roads. | Transportation Enhancements | 2009-09-01 | 2009-10-19 | 2010-08-26 | 2011-12-14 | 1558107.81 | 0.001
11180 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | KNOX |  | 13 | 2002209 | In order to enhance the community, the City of Knox will construct a hike and bike trail to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2010-04-25 | 2010-04-25 | 2010-07-01 | 2010-08-26 | 76705.92 | 0.100
11181 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HALL |  | 13 | 2002754 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge at county road. | Bridge Replacement | 2009-06-22 | 2009-07-08 | 2011-05-31 | 2010-09-22 | 248320.15 | 0.066
11182 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 20 | 2003559 | In order to improve mobility in a metropolitan area, the City of San Antonio will reconstruct the roadway to four lanes on city street. | Pavement Widening | 2010-07-12 | 2010-07-12 | 2012-05-31 |  | 3297539 | 0.445
11183 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 20 | 2004424 | In order to improve mobility in a metropolitan area, the City of San Antonio will reconstruct the roadway to four lanes on various highways and roads. | New Construction | 2010-08-09 | 2010-08-09 | 2012-01-31 |  | 11192666.69 | 1.400
11184 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 21 | 2004540 | In order to improve mobility in a metropolitan area, the City of Austin will restore and rehabilitate roadway on various highways and roads. | Transportation Enhancements | 2011-01-31 | 2011-01-31 | 2011-05-29 | 2011-07-29 | 325000 | 0.001
11185 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 10 | 2004693 | In order to improve mobility in a metropolitan area, the City of Manor will improve sidewalks to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2010-06-07 | 2010-05-27 | 2010-10-30 |  | 128748 | 0.001
11186 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | HOUSTON |  | 06 | 2004820 | In order to improve safety of the existing transportation system, the Texas Department of Transportation will construct the roadway to include a two way continuous left turn lane on Loop 304. | Pavement Improvement | 2010-07-08 | 2010-08-16 |  | 2011-10-24 | 80524.62 | 0.694
11187 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BELL |  | 31 | 2005351 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway to add a northbound frontage road on Interstate Highway 35. | New Bridge Construction | 2010-06-10 | 2010-07-28 | 2014-06-30 |  | 181853.65 | 0.940
11188 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 14 | 2005833 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge on county road. | Bridge Replacement | 2009-10-16 | 2009-09-09 | 2010-06-30 | 2010-07-26 | 493945.57 | 0.057
11189 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2005982 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway to widen to four lanes on city street. | Pavement Widening | 2010-05-17 | 2010-07-19 | 2011-09-15 | 2011-11-08 | 3528788.67 | 2.000
11190 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2005996 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a new toll road on Loop 49. | New Construction | 2009-07-21 | 2009-08-06 | 2011-05-15 |  | 29872772.08 | 6.569
11191 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | TOM GREEN |  | 11 | 2006045 | In order to enhance the community, the Texas Department of Transportation will refurbish a historic bridge to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2010-06-04 | 2010-06-22 | 2009-11-01 | 2011-05-31 | 1399601.86 | 0.355
11192 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON | GALVESTON | 22 | 2006063 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge on county road. | Bridge Replacement | 2009-05-28 | 2009-06-29 | 2009-11-30 | 2009-10-12 | 303590.88 | 0.065
11193 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | STARR |  | 28 | 2006304 | In order to preserve the existing transportation system, the Texas Department of Transportation will perform restoration and rehabilitation on city street. | Pavement Improvement | 2009-08-10 | 2009-10-20 | 2011-02-01 |  | 1371513.37 | 0.678
11194 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | RANDALL |  | 13 | 2006439 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will widen the roadway to a four lane arterial on various highways and roads. | Pavement Widening | 2009-11-02 | 2010-01-25 | 2010-06-30 | 2012-01-27 | 1940000 | 0.681
11195 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | COLLIN | DALLAS-FORT WORTH | 03 | 2006470 | In order to mitigate congestion and improve air quality, the City of Plano will reconstruct the roadway to include intersection improvements on State Highway 289. | Pavement Improvement | 2009-09-16 | 2009-09-28 | 2010-10-31 | 2010-10-12 | 1034202.48 | 0.001
11196 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | HARTLEY |  | 13 | 2007003 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 87. | Pavement Improvement | 2009-06-29 | 2009-07-20 | 2010-03-01 | 2009-11-13 | 3815533.36 | 13.647
11197 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BURLESON |  | 10 | 2007109 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 36. | Pavement Improvement | 2009-06-29 | 2009-09-01 | 2010-05-15 | 2010-02-01 | 1921016.47 | 6.001
11198 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | DALLAS | DALLAS-FORT WORTH | 30 | 2007383 | In order to enhance the community, the Texas Department of Transportation will construct a plaza over the freeway to accommodate bicycle transportation and pedestrians on Spur 366. | Transportation Enhancements | 2009-09-22 | 2009-10-19 | 2010-02-17 |  | 16700000 | 0.250
11199 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | VAL VERDE |  | 23 | 2007565 | In order to enhance the community, the Texas Department of Transportation will construct a hike and bike trail to accommodate bicycle transportation and pedestrians on various highways and roads. | Transportation Enhancements | 2009-10-06 | 2009-11-02 | 2010-01-01 | 2010-02-17 | 62000.74 | 0.225
11200 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | COMAL |  | 21 | 2007704 | In order to improve the transportation system at the local level, the Texas Department of Transportation will restore and rehabilitate the roadway by adding shoulders and passing lanes on Farm-To-Mark | Pavement Improvement | 2009-07-10 | 2009-08-06 | 2010-05-01 | 2011-05-16 | 668050.28 | 0.863
11201 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS | DALLAS-FORT WORTH | 06 | 2007710 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace bridge and approaches on city street. | Bridge Replacement | 2009-09-22 | 2009-10-22 | 2010-05-01 | 2010-07-07 | 229500 | 0.071
11202 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | 10 | 2007822 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will construct a railroad-highway grade separation on Farm-To-Market 2978. | New Bridge Construction | 2009-10-14 | 2009-10-19 | 2012-01-31 | 2011-11-08 | 6871970.66 | 0.777
11203 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 2007854 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway by adding turn radius improvements on Belt Way 8. | Pavement Improvement | 2009-11-02 | 2009-12-14 | 2012-02-29 | 2011-04-17 | 2349189.33 | 0.360
11204 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2008119 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will perform reconstruction and widening on city street. | Pavement Widening | 2010-01-04 | 2010-02-09 | 2011-07-08 | 2011-10-12 | 4940668.63 | 3.000
11205 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HALL |  | 13 | 2008245 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge on county road. | Bridge Replacement | 2009-06-22 | 2009-07-08 | 2010-07-01 | 2010-09-22 | 279174.3 | 0.180
11206 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HALL |  | 13 | 2008246 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge on county road. | Bridge Replacement | 2009-06-22 | 2009-07-08 | 2011-01-01 | 2010-09-22 | 218989 | 0.063
11207 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2008341 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on county road. | Bridge Replacement | 2009-06-22 | 2009-07-10 | 2011-01-01 | 2009-11-30 | 78347.06 | 0.051
11208 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2008348 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on county road. | Bridge Replacement | 2009-06-22 | 2009-07-10 | 2011-01-01 | 2009-11-30 | 128146.2 | 0.042
11209 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2008350 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on county road. | Bridge Replacement | 2009-06-22 | 2009-07-10 | 2011-01-01 | 2009-11-30 | 99350.34 | 0.044
11210 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2008351 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on county road. | Bridge Replacement | 2009-06-22 | 2009-07-10 | 2010-07-01 | 2009-11-30 | 185772.3 | 0.068
11211 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CHILDRESS |  | 13 | 2008530 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge on county road. | Bridge Replacement | 2009-06-22 | 2009-07-08 | 2010-07-01 | 2010-09-22 | 134256 | 0.085
11212 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HALL |  | 13 | 2008532 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge on county road. | Bridge Replacement | 2009-06-22 | 2009-07-08 | 2010-05-01 | 2010-09-22 | 173523.7 | 0.227
11213 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2008536 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on county road. | Bridge Replacement | 2009-08-26 | 2009-09-11 | 2010-05-01 | 2010-12-07 | 525000 | 0.074
11214 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2008537 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on county road. | Bridge Replacement | 2009-08-26 | 2009-09-11 | 2010-05-01 | 2010-12-07 | 181000 | 0.650
11215 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2008538 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge on county road. | Bridge Replacement | 2009-08-26 | 2009-09-11 | 2010-05-01 | 2010-12-07 | 208990.25 | 0.001
11216 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2008539 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on county road. | Bridge Replacement | 2009-08-26 | 2009-09-11 | 2010-05-01 | 2010-12-07 | 262000 | 0.001
11217 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2008540 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on county road. | Bridge Replacement | 2009-08-26 | 2009-09-11 | 2010-05-01 | 2010-12-07 | 214992.25 | 0.001
11218 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JEFFERSON | PORT ARTHUR | 02 | 2008658 | In order to improve the transportation system at the local level, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 73. | Pavement Improvement | 2009-11-02 | 2010-08-16 | 2010-07-01 | 2010-10-22 | 308810.16 | 0.321
11219 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HALL |  | 13 | 2008721 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge on county road. | Bridge Replacement | 2009-06-22 | 2009-07-08 | 2011-10-01 | 2010-09-22 | 169359.15 | 0.065
11220 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | MILLS |  | 11 | 2009012 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 84. | Pavement Widening | 2009-07-10 | 2009-08-07 | 2011-10-01 |  | 4605444.97 | 9.848
11221 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2009054 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on Farm-To-Market 126. | Bridge Replacement | 2009-07-06 | 2009-08-17 | 2010-03-01 | 2010-06-02 | 613513.6 | 0.112
11222 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR | ABILENE | 19 | 2009056 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway by modifying cross section and adding a signal on State Highway 36. | Pavement Improvement | 2010-02-01 | 2010-02-17 | 2010-09-30 | 2010-12-22 | 1566608.95 | 1.150
11223 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | RUNNELS |  | 11 | 2009096 | In order to supplement the transportation system, the Texas Department of Transportation will construct rail bridge on various highways and roads. | New Construction | 2010-03-12 | 2010-03-30 | 2011-01-01 | 2011-05-19 | 2734944.78 | 1.000
11224 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LUBBOCK |  | 19 | 2009104 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway by widening to six main lanes and adding a new overpass on Loop 28 | Pavement Widening | 2009-07-21 | 2009-08-06 | 2010-07-01 | 2011-07-15 | 16518640.06 | 2.281
11225 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FREESTONE |  | 06 | 2009153 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 80. | Pavement Improvement | 2009-06-12 | 2009-06-26 | 2010-11-26 | 2010-07-24 | 2942165.21 | 17.333
11226 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ZAVALA |  | 23 | 2009237 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1025,Ranch-To-Market 693,State Highway 359,US Highway 277 a | Pavement Improvement | 2009-11-18 | 2010-04-15 | 2010-11-26 | 2011-08-02 | 2400948.66 | 49.048
11227 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2009377 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconfigure and upgrade traffic signal system at intersection on Farm-To-Market 1092 and State Highway | Safety/Traffic Management | 2010-02-19 | 2010-03-15 | 2010-11-30 | 2010-12-17 | 1319211.99 | 0.000
11228 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | OCHILTREE |  | 13 | 2009455 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 83. | Pavement Improvement | 2009-06-12 | 2009-06-17 | 2010-02-01 | 2009-08-06 | 1362796.41 | 7.761
11229 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ARMSTRONG |  | 13 | 2009456 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 287. | Pavement Improvement | 2009-06-12 | 2009-07-13 | 2010-11-01 | 2011-06-23 | 8895225.05 | 8.646
11230 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | RANDALL |  | 13 | 2009457 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Interstate Highway 27. | Pavement Improvement | 2009-06-04 | 2009-06-09 | 2009-10-01 | 2009-09-18 | 1298560.96 | 2.608
11231 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | HARDEMAN |  | 13 | 2009459 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 287. | Pavement Improvement | 2009-06-22 | 2009-08-04 | 2010-07-01 | 2009-09-11 | 1256628.27 | 9.924
11232 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HALL, CHILDRESS |  | 13 | 2009460 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 94. | Pavement Improvement | 2009-06-09 | 2009-06-25 | 2010-07-01 | 2010-06-24 | 3563608.2 | 6.970
11233 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | BREWSTER |  | 23 | 2009461 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 67. | Pavement Improvement | 2009-06-23 | 2009-08-03 | 2009-09-01 | 2009-10-30 | 1956262.54 | 7.921
11234 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | EL PASO |  | 16 | 2009462 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 2529. | Pavement Improvement | 2009-05-07 | 2009-06-03 | 2009-09-01 | 2009-08-05 | 592762.81 | 2.938
11235 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | EL PASO |  | 23 | 2009463 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1110. | Pavement Improvement | 2009-05-19 | 2009-06-04 | 2009-10-01 | 2009-07-27 | 299899.9 | 1.200
11236 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | EL PASO |  | 16 | 2009464 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a four lane roadway on Loop 375. | Pavement Improvement | 2009-05-06 | 2009-05-30 | 2011-03-01 | 2009-09-21 | 1325044.9 | 1.740
11237 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | CASTRO |  | 19 | 2009465 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 1055 and Farm-To-Market 2943. | Pavement Improvement | 2009-06-02 | 2009-08-20 | 2011-03-01 | 2011-06-30 | 7681000 | 15.607
11238 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | HALE, FLOYD |  | 19 | 2009466 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 2286. | Pavement Improvement | 2009-06-05 | 2009-07-24 | 2010-07-01 | 2009-10-15 | 2416888.83 | 10.230
11239 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SWISHER, HALE, LUBBOCK |  | Multiple | 2009467 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway and bridge on various highways and roads. | Pavement Improvement | 2009-05-19 | 2009-06-15 | 2010-07-01 | 2011-03-31 | 6242469.17 | 90.304
11240 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | MARTIN |  | 11 | 2009468 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 137. | Pavement Improvement | 2009-06-05 | 2009-09-16 | 2009-11-01 | 2010-02-03 | 1435027.95 | 7.000
11241 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | PECOS |  | 23 | 2009469 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 385. | Pavement Improvement | 2009-06-16 | 2009-08-27 | 2010-03-01 | 2010-08-10 | 1498725.45 | 17.914
11242 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | ANDREWS |  | 11 | 2009470 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 115. | Pavement Improvement | 2009-06-29 | 2009-07-14 | 2010-03-01 | 2010-04-05 | 4012108.23 | 1.535
11243 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | IRION |  | 11 | 2009471 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 67. | Pavement Improvement | 2009-06-22 | 2009-07-13 | 2011-09-01 | 2010-05-19 | 2048624.66 | 6.758
11244 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | MENARD, EDWARDS |  | Multiple | 2009472 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will construct a bridge and approaches on Ranch-To-Market 864 and State Highway 55. | Pavement Improvement | 2009-06-18 | 2009-07-27 | 2011-09-01 | 2011-05-13 | 2489936.82 | 1.541
11245 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS |  | 21 | 2009473 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Ranch-To-Market 1431. | Pavement Improvement | 2009-06-22 | 2009-07-08 | 2009-08-01 | 2009-12-03 | 3300717.11 | 7.962
11246 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS |  | Multiple | 2009474 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Loop 1. | Pavement Improvement | 2009-06-04 | 2009-08-25 | 2009-08-01 | 2011-01-10 | 2330028.81 | 9.857
11247 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WILLIAMSON |  | 31 | 2009475 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 79. | Pavement Improvement | 2009-06-08 | 2009-06-24 | 2011-06-01 | 2010-01-04 | 1345917.68 | 1.704
11248 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | Multiple | 2009478 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 2439. | Pavement Improvement | 2009-06-12 | 2009-07-06 | 2010-09-17 | 2009-09-24 | 236568.43 | 2.197
11249 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | LLANO |  | 11 | 2009479 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 71. | Pavement Improvement | 2009-06-09 | 2009-07-15 | 2011-06-01 | 2009-10-19 | 290581.6 | 1.815
11250 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | KAUFMAN |  | 05 | 2009480 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway on Farm-To-Market 598. | Pavement Improvement | 2009-07-14 | 2010-01-04 | 2010-09-17 | 2010-10-27 | 2705889.55 | 2.249
11251 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | Multiple | 2009484 | In order to improve mobility in a metropolitan area, the Alamo Regional Mobility Authority will reconstruct the roadway by reconfiguring intersections and making changes to signals on US Highway 281. | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-07-01 | 2011-06-24 | 5256791.85 | 3.409
11252 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TARRANT | STATEWIDE | 12 | 2009485 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will construct a new roadway interchange on State Highway 121. | New Construction | 2010-02-01 | 2010-03-15 | 2012-09-01 |  | 116646468.88 | 0.100
11253 | Underway | C240,C230 | Highway Infrastructure Investment Grant | TEXAS | NUECES | CORPUS CHRISTI | 27 | 2009486 | In order to preserve the existing transportation system, the Port of Corpus Christi Authority will restore and rehabilitate the roadway on various highways and roads. | Pavement Improvement | 2010-01-18 | 2010-02-04 | 2011-07-26 |  | 6130478.97 | 9.537
11254 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | Multiple | 2009487 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 123. | Pavement Improvement | 2009-06-29 | 2009-07-15 | 2009-08-01 | 2009-09-24 | 292810.93 | 1.172
11255 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | BLANCO |  | 21 | 2009488 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 281. | Pavement Improvement | 2009-06-16 | 2009-08-24 | 2012-06-01 | 2010-02-17 | 610452.84 | 2.377
11256 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2009489 | In order to add additional capacity to the transportation system, the Central Texas Regional Mobility Authority will construct four direct connectors on US Highway 290. | New Bridge Construction | 2010-04-27 | 2010-04-27 | 2012-06-01 |  | 59477545.77 | 0.500
11257 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JIM WELLS |  | 15 | 2009490 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 281 Business Loop R. | Pavement Improvement | 2009-06-09 | 2009-07-20 |  | 2009-08-21 | 650000 | 2.154
11258 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | KLEBERG, JIM WELLS |  | Multiple | 2009491 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 141. | Pavement Improvement | 2009-06-29 | 2009-08-20 |  | 2010-01-28 | 3031983.23 | 12.620
11259 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN PATRICIO |  | 15 | 2009492 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 77 Business Loop T. | Pavement Improvement | 2009-06-22 | 2009-07-29 | 2009-10-01 | 2009-09-03 | 796264.02 | 3.778
11260 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN PATRICIO |  | 15 | 2009493 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 234. | Pavement Improvement | 2009-06-16 | 2009-06-23 | 2009-10-01 | 2009-10-27 | 1222413.27 | 5.737
11261 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | REFUGIO |  | 15 | 2009494 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the northbound roadway lanes on US Highway 77. | Pavement Improvement | 2009-06-29 | 2009-08-03 |  | 2009-11-09 | 1997509.74 | 8.515
11262 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | SAN PATRICIO |  | 15 | 2009495 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore, rehabilitate and widen the roadway on Farm-To-Market 2046. | Pavement Improvement | 2009-06-16 | 2009-07-02 |  | 2009-09-24 | 760634.69 | 3.267
11263 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | BEE |  | 15 | 2009496 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 181. | Pavement Improvement | 2009-06-16 | 2009-08-12 | 2009-09-01 | 2010-03-03 | 2643872.33 | 10.983
11264 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DUVAL |  | 25 | 2009497 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 359. | Pavement Improvement | 2009-06-16 | 2009-07-02 | 2009-11-01 | 2009-10-13 | 729799.75 | 0.792
11265 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | VAL VERDE |  | 23 | 2009498 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 90. | Pavement Improvement | 2009-06-08 | 2009-10-27 | 2009-12-01 | 2010-06-14 | 1765734.28 | 4.023
11266 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | MAVERICK |  | 23 | 2009499 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 277. | Pavement Improvement | 2009-06-22 | 2009-07-13 | 2010-03-01 | 2010-04-23 | 2783552.58 | 5.928
11267 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | MAVERICK |  | 23 | 2009500 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 2644. | Pavement Improvement | 2009-06-04 | 2009-07-06 | 2012-12-30 | 2010-02-15 | 2325707.47 | 12.303
11268 | Underway | C240,C230 | Highway Infrastructure Investment Grant | TEXAS | EL PASO | EL PASO | 16 | 2009501 | In order to add additional capacity to the transportation system, the Camino Real Regional Mobility Authority will reconstruct two flyovers to the roadway on Interstate Highway 10. | New Bridge Construction | 2010-08-31 | 2010-08-31 | 2012-12-30 |  | 95991780 | 0.100
11269 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO |  | Multiple | 2009502 | In order to preserve the existing transportation system, the Texas Department of Transportation will rehabilitate the roadway on State Highway 107. | Pavement Improvement | 2009-06-22 | 2009-07-13 | 2009-12-01 | 2010-06-30 | 2143338.79 | 3.700
11270 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | STARR |  | Multiple | 2009504 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1015,Farm-To-Market 509,State Highway 107,State Highway 16, | Pavement Improvement | 2009-06-22 | 2009-07-15 | 2009-12-01 | 2010-04-30 | 6551273.9 | 34.570
11271 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | ORANGE |  | 08 | 2009507 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the existing four lane roadway on Interstate Highway 10. | Pavement Improvement | 2010-04-22 | 2010-05-17 | 2010-03-01 |  | 32000000 | 2.433
11272 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | KERR |  | 21 | 2009508 | In order to preserve the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on State Highway 39. | New Bridge Construction | 2009-06-09 | 2009-07-08 | 2010-01-01 | 2010-06-21 | 986274.34 | 0.154
11273 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | KERR |  | 21 | 2009509 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on Farm-To-Market 1340. | New Bridge Construction | 2009-06-09 | 2009-08-14 | 2009-11-01 | 2010-06-21 | 464457.35 | 0.085
11274 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | KERR |  | 21 | 2009510 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will remove and replace bridge and reconstruct approaches on Farm-To-Market 1350. | Pavement Improvement | 2009-06-09 | 2009-07-27 | 2010-08-01 | 2010-05-03 | 827437.76 | 0.169
11275 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | UVALDE |  | 23 | 2009511 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Ranch-To-Market 187. | Pavement Improvement | 2009-07-06 | 2009-07-29 | 2010-05-01 | 2011-10-18 | 3596123.51 | 11.420
11276 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MEDINA |  | 23 | 2009512 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate by widening narrow roadway and adding shoulders on Farm-To-Market 462. | Pavement Improvement | 2009-06-18 | 2009-07-20 | 2014-06-04 | 2010-06-25 | 1844944.89 | 4.716
11277 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT | DALLAS-FORT WORTH | 24 | 2009513 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct freeway, frontage roads and ramps on State Highway 114 and State Highway 121. | Pavement Widening | 2009-10-26 | 2009-10-06 | 2014-06-04 |  | 260816297 | 10.452
11278 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 18 | 2009514 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway on Interstate Highway 10. | Pavement Improvement | 2009-10-16 | 2009-11-01 | 2011-05-30 | 2011-05-23 | 18038764.02 | 2.346
11279 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MEDINA |  | 23 | 2009515 | In order to improve the transportation system, the Texas Department of Transportation will reconstruct the roadway by adding a northbound exit ramp on Interstate Highway 35. | Pavement Widening | 2009-06-09 | 2009-09-01 | 2011-11-01 | 2011-03-21 | 2259919.03 | 2.022
11280 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | COMAL |  | 21 | 2009516 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway by widening a narrow roadway to add shoulders and passing lane | Pavement Improvement | 2009-06-08 | 2009-06-29 | 2010-01-01 | 2011-06-21 | 5146936.2 | 5.255
11281 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FRIO |  | 28 | 2009517 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway by installing curb inlets and a storm sewer system on Farm-To- | Pavement Improvement | 2009-06-16 | 2010-01-06 | 2012-02-01 | 2010-08-03 | 656092.55 | 0.568
11282 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | Multiple | 2009519 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway on Interstate Highway 610. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2012-03-30 | 2011-03-16 | 28655986.56 | 2.910
11283 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON | SHERMAN-DENISON | 04 | 2009520 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway by widening existing highway to include turn lanes, t | Pavement Improvement | 2009-08-26 | 2009-09-21 | 2009-11-01 | 2009-10-29 | 3000000 | 0.758
11284 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WHARTON |  | 14 | 2009521 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 90A. | Pavement Improvement | 2009-06-16 | 2009-07-20 | 2009-12-01 | 2009-11-20 | 3184624.51 | 7.157
11285 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | AUSTIN |  | 10 | 2009522 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 1093. | Pavement Improvement | 2009-06-02 | 2009-06-22 | 2009-09-01 | 2010-08-12 | 2436931.87 | 3.755
11286 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | COLORADO, DE WITT, VICTORIA |  | Multiple | 2009523 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 72,US Highway 59 Business Loop T and US Highway 90A. | Pavement Improvement | 2009-06-16 | 2009-07-15 | 2009-11-01 | 2009-11-25 | 2562752.28 | 7.310
11287 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MATAGORDA |  | 14 | 2009524 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 521. | Pavement Improvement | 2009-06-23 | 2009-07-14 | 2009-08-01 | 2010-06-15 | 1856668.17 | 3.153
11288 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FAYETTE |  | 25 | 2009525 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 77. | Pavement Improvement | 2009-06-22 | 2009-07-20 | 2009-09-01 | 2009-09-30 | 789505.41 | 1.672
11289 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARDIN |  | 08 | 2009526 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 420. | Pavement Improvement | 2009-06-12 | 2009-06-22 | 2009-11-01 | 2009-09-11 | 619326.17 | 3.807
11290 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | JASPER |  | 08 | 2009527 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface and widen the roadway on Farm-To-Market 1131. | Pavement Improvement | 2009-06-22 | 2009-07-24 | 2009-09-01 | 2009-12-01 | 2569366.36 | 7.479
11291 | Completed | C250,C200 | Highway Infrastructure Investment Grant | TEXAS | TYLER |  | 08 | 2009528 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 190 and US Highway 69. | Pavement Improvement | 2009-06-02 | 2009-07-16 | 2009-12-01 | 2009-11-16 | 2393603.28 | 5.141
11292 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JEFFERSON |  | 02 | 2009529 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface and rehabilitate the roadway on State Highway 73. | Pavement Improvement | 2009-06-16 | 2009-07-22 | 2009-09-01 | 2011-03-18 | 3948903.36 | 18.993
11293 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CHAMBERS |  | 14 | 2009530 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1409 and Interstate Highway 10. | Pavement Improvement | 2009-06-02 | 2009-06-29 | 2009-09-01 | 2009-11-13 | 782288.36 | 3.718
11294 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BELL |  | 31 | 2009531 | In order to add additional capacity and safety to the transportation system, the Texas Department of Transportation will reconstruct and widen the roadway to six lanes, replace bridge and approaches, | Pavement Widening | 2010-06-10 | 2010-07-28 | 2014-06-30 |  | 102371100.59 | 6.969
11295 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARDIN |  | 08 | 2009532 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 418. | Pavement Improvement | 2009-06-02 | 2009-06-22 | 2010-12-01 | 2009-09-17 | 352932.9 | 1.688
11296 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | NEWTON |  | 08 | 2009533 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade and install bridge rails at various bridges to enhance roadway safety on Farm-To-Market 101 | Safety/Traffic Management | 2009-05-19 | 2009-07-07 | 2010-12-01 | 2010-04-26 | 915924.6 | 2.402
11297 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ORANGE |  | 08 | 2009534 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1132. | Pavement Improvement | 2009-06-03 | 2009-07-06 | 2010-02-01 | 2009-09-29 | 519724.35 | 1.657
11298 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZOS |  | 17 | 2009535 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 21. | Pavement Improvement | 2009-06-02 | 2009-07-17 | 2010-02-01 | 2009-10-02 | 621471.9 | 1.587
11299 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZOS |  | 17 | 2009536 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 2347 and Farm-To-Market 60. | Pavement Improvement | 2009-05-19 | 2009-06-12 | 2010-01-01 | 2009-10-06 | 878657.3 | 2.462
11300 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZOS |  | 17 | 2009537 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1179. | Pavement Improvement | 2009-05-19 | 2009-06-03 | 2010-03-01 | 2009-09-15 | 298091.9 | 1.000
11301 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | LEON |  | 06 | 2009538 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Interstate Highway 45. | Pavement Improvement | 2009-06-04 | 2009-08-17 | 2009-12-01 | 2010-06-16 | 6623247.22 | 7.269
11302 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | HOWARD |  | 19 | 2009539 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Interstate Highway 20. | Pavement Improvement | 2009-05-28 | 2009-06-29 | 2009-10-01 | 2009-10-15 | 4997459.67 | 10.284
11303 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | MORRIS |  | 04 | 2009540 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore, rehabilitate and widen the roadway to a four lane divided rural highway with shoulders on | Pavement Improvement | 2009-05-28 | 2009-07-01 | 2009-11-01 | 2010-09-13 | 923483.46 | 2.021
11304 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZORIA |  | 14 | 2009541 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 35. | Pavement Improvement | 2009-06-08 | 2009-07-06 | 2009-11-23 | 2009-11-23 | 3047898.69 | 16.010
11305 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | Multiple | 2009542 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 225. | Pavement Improvement | 2009-06-29 | 2009-07-30 | 2010-06-15 | 2010-04-13 | 882735.48 | 4.397
11306 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 22 | 2009543 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 3155. | Pavement Improvement | 2009-06-05 | 2009-06-23 | 2009-08-05 | 2009-08-05 | 188597.81 | 1.021
11307 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2009544 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on various highways and roads. | Pavement Improvement | 2009-06-02 | 2009-06-18 | 2009-07-20 | 2009-07-22 | 426244.36 | 0.001
11308 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 22 | 2009545 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 36. | Pavement Improvement | 2009-06-05 | 2009-07-30 | 2009-11-30 | 2009-10-20 | 1269484.81 | 0.369
11309 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON |  | 14 | 2009546 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Loop 197. | Pavement Improvement | 2009-06-05 | 2009-07-13 | 2009-10-08 | 2009-09-21 | 646223.04 | 1.770
11310 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZORIA |  | 14 | 2009547 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1459 and Farm-To-Market 524. | Pavement Improvement | 2009-06-02 | 2009-07-21 | 2010-01-06 | 2009-12-07 | 1360458.79 | 11.799
11311 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | Multiple | 2009548 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 90A. | Pavement Improvement | 2009-06-04 | 2009-07-23 | 2009-09-15 | 2009-11-10 | 1118221.98 | 9.741
11312 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2009549 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Loop 494. | Pavement Improvement | 2009-06-02 | 2009-06-18 | 2010-08-31 | 2010-06-17 | 3785248.11 | 8.022
11313 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 14 | 2009550 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 1093. | Pavement Improvement | 2009-05-27 | 2009-06-17 | 2009-09-01 | 2009-09-28 | 820473.22 | 4.704
11314 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2009551 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway and shoulders on Farm-To-Market 362. | Pavement Improvement | 2009-06-02 | 2009-11-16 | 2010-09-01 | 2010-08-31 | 961664.41 | 0.971
11315 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | 10 | 2009552 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 2978. | Pavement Improvement | 2009-06-12 | 2009-06-28 | 2009-09-21 | 2009-11-02 | 267020.96 | 0.369
11316 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | 07 | 2009553 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 290. | Pavement Improvement | 2009-06-04 | 2009-06-24 | 2009-10-01 | 2009-08-12 | 118220 | 3.845
11317 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | Multiple | 2009554 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1093. | Pavement Improvement | 2009-06-05 | 2009-08-17 | 2010-06-01 | 2009-10-16 | 4459705.68 | 8.923
11318 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2009555 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 1458. | Pavement Improvement | 2009-06-08 | 2009-09-01 | 2010-06-04 | 2010-05-21 | 2035566.78 | 7.292
11319 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON |  | 14 | 2009556 | In order to preserve the existing transportation system, the Texas Department of Transportation will elevate, restore and rehabilitate the roadway on State Highway 87. | Pavement Improvement | 2009-06-02 | 2009-06-18 | 2010-06-15 | 2010-06-24 | 6121521.68 | 21.338
11320 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | 02 | 2009557 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 90. | Pavement Improvement | 2009-06-08 | 2009-07-06 | 2010-01-05 | 2009-11-02 | 1130908.04 | 2.072
11321 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 22 | 2009558 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 521. | Pavement Improvement | 2009-06-05 | 2009-07-08 | 2009-09-01 | 2009-09-08 | 653888.42 | 4.807
11322 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2009559 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 362. | Pavement Improvement | 2009-06-04 | 2009-06-22 | 2010-11-04 | 2009-08-25 | 614106.5 | 3.492
11323 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | NACOGDOCHES |  | 01 | 2009560 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 259. | Pavement Improvement | 2009-06-02 | 2009-07-21 | 2011-01-01 | 2009-11-23 | 3217445.02 | 6.327
11324 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BURLESON |  | 17 | 2009561 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will widen the roadway to a four lane divided highway on Farm-To-Market 60. | Pavement Widening | 2009-06-16 | 2009-06-27 | 2010-06-01 | 2012-01-24 | 7505830.38 | 2.752
11325 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SHELBY |  | 01 | 2009562 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway on Farm-To-Market 138. | Pavement Improvement | 2009-06-18 | 2009-07-27 | 2010-08-01 | 2010-06-14 | 1161712.34 | 5.457
11326 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | SHELBY |  | 01 | 2009563 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 84. | Pavement Improvement | 2009-06-12 | 2009-08-25 | 2010-08-01 | 2011-07-11 | 4664748.68 | 9.375
11327 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | HOUSTON |  | 06 | 2009564 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway on Farm-To-Market 227. | Pavement Improvement | 2009-06-17 | 2009-06-26 | 2009-11-01 | 2010-07-06 | 2356956.12 | 11.173
11328 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MORRIS, TITUS |  | 04 | 2009565 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 49. | Pavement Improvement | 2009-07-09 | 2009-07-22 | 2009-11-01 | 2010-08-04 | 4699268.05 | 7.400
11329 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | PANOLA |  | 01 | 2009566 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway by widening, resurfacing, and adding shoulders on US Highway 7 | Pavement Improvement | 2009-06-12 | 2009-06-30 | 2010-06-01 | 2010-09-14 | 2383873.36 | 3.187
11330 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CASS |  | Multiple | 2009568 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway by widening, resurfacing, and adding shoulders on State Highwa | Pavement Improvement | 2009-06-05 | 2009-07-24 | 2010-07-01 | 2011-04-22 | 789635.66 | 3.024
11331 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | CASS |  | 04 | 2009569 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway by widening, resurfacing, and adding shoulders on State Highwa | Pavement Improvement | 2009-05-22 | 2009-06-15 | 2010-07-01 | 2011-06-27 | 1919822.37 | 11.305
11332 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BROWN |  | 11 | 2009570 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 67. | Pavement Improvement | 2009-06-05 | 2009-08-05 | 2010-12-01 | 2009-11-20 | 1495948.09 | 3.055
11333 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | NAVARRO |  | 06 | 2009571 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1126 and Farm-To-Market 639. | Pavement Improvement | 2009-06-22 | 2009-07-08 | 2010-12-01 | 2011-04-20 | 7287236.14 | 14.329
11334 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LEON |  | 06 | 2009572 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 542. | Pavement Improvement | 2009-07-06 | 2009-08-17 | 2011-06-01 | 2009-10-14 | 369716.71 | 2.534
11335 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | HOPKINS |  | 04 | 2009575 | In order to improve the transportation system at the local level, the Texas Department of Transportation will restore and rehabilitate the roadway and add shoulders on State Highway 11. | Pavement Improvement | 2009-08-21 | 2009-08-31 | 2010-06-01 | 2011-05-02 | 4160215 | 3.447
11336 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2009576 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 902. | Pavement Improvement | 2009-05-28 | 2009-06-30 | 2010-05-01 | 2009-11-17 | 1876832.4 | 5.895
11337 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LAMAR |  | 04 | 2009577 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 196. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2010-11-01 | 2010-04-23 | 896178.3 | 3.380
11338 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2009578 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 121. | Pavement Improvement | 2009-06-02 | 2009-06-16 | 2011-09-01 | 2011-01-28 | 3701118.28 | 11.354
11339 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LAMAR |  | 04 | 2009579 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 1498. | Pavement Improvement | 2009-06-02 | 2009-06-04 | 2010-10-31 | 2010-12-20 | 2447477.14 | 10.320
11340 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GREGG |  | 01 | 2009580 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 80. | Pavement Improvement | 2009-06-05 | 2009-06-22 | 2010-11-01 | 2009-10-21 | 1712304.61 | 2.874
11341 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | ANDERSON |  | 05 | 2009581 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway and add shoulders on US Highway 84. | Pavement Improvement | 2009-06-02 | 2009-06-26 | 2009-11-01 | 2011-03-10 | 4110707.46 | 5.602
11342 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WOOD |  | 05 | 2009582 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 37 and US Highway 69. | Pavement Improvement | 2009-05-22 | 2009-06-17 | 2009-11-01 | 2009-10-14 | 1637663.52 | 2.377
11343 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2009583 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 69. | Pavement Improvement | 2009-06-02 | 2009-07-20 | 2009-10-01 | 2009-12-28 | 2236906.91 | 7.045
11344 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GREGG |  | 01 | 2009584 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 259. | Pavement Improvement | 2009-05-19 | 2009-06-16 | 2009-10-01 | 2010-01-07 | 2066492.08 | 3.620
11345 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | VAN ZANDT |  | 05 | 2009586 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the bridge surface on State Highway 243. | Pavement Improvement | 2009-06-16 | 2009-07-06 | 2009-09-01 | 2009-08-21 | 61344 | 0.133
11346 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BELL |  | 31 | 2009588 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 317. | Pavement Improvement | 2009-06-04 | 2009-06-22 | 2011-06-01 | 2009-10-14 | 1084181.85 | 1.607
11347 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | CORYELL |  | 31 | 2009589 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway by adding additional lanes and shoulders on US Highway 84. | Pavement Improvement | 2009-06-18 | 2009-06-24 | 2010-04-01 |  | 8735023.01 | 10.235
11348 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CORYELL |  | 31 | 2009590 | In order to improve the transportation system to promote statewide goals, the Texas Department of Transportation will construct overpass for Fort Hood access on US Highway 190. | New Bridge Construction | 2009-08-10 | 2009-08-24 | 2010-04-01 |  | 2368151.52 | 2.642
11349 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BELL |  | 31 | 2009591 | In order to improve the transportation system to promote statewide goals, the Texas Department of Transportation will reconstruct the roadway by adding turn lanes, traffic signal and lighting for impr | Pavement Improvement | 2009-06-09 | 2009-06-23 | 2009-12-01 | 2010-08-18 | 1220438.55 | 0.800
11350 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WILBARGER |  | 13 | 2009592 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 287. | Pavement Improvement | 2009-06-09 | 2009-08-19 | 2010-10-01 | 2010-05-19 | 2515911.53 | 7.273
11351 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | ARCHER |  | 19 | 2009593 | In order to preserve the existing transportation system, the Texas Department of Transportation will extend culverts and add shoulders on State Highway 25. | Pavement Improvement | 2009-06-09 | 2009-08-12 | 2009-11-01 | 2010-11-24 | 3147193.46 | 9.364
11352 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | COOKE |  | 26 | 2009594 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Interstate Highway 35. | Pavement Improvement | 2009-06-05 | 2009-08-12 | 2010-12-01 | 2009-11-20 | 2396645.99 | 5.765
11353 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | COOKE |  | Multiple | 2009595 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway to add shoulders on Farm-To-Market 2071. | Pavement Improvement | 2009-06-22 | 2009-07-14 | 2009-11-01 | 2011-03-25 | 2108363.87 | 8.579
11354 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | RUSK |  | 01 | 2009596 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 259. | Pavement Improvement | 2009-05-22 | 2009-06-10 | 2009-10-01 | 2009-12-11 | 2886918.15 | 5.100
11355 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS |  | Multiple | 2009597 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Loop 1. | Pavement Improvement | 2009-06-12 | 2009-07-28 | 2009-10-01 | 2009-11-03 | 1696542.45 | 2.818
11356 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS |  | 25 | 2009598 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Loop 1. | Pavement Improvement | 2009-06-16 | 2009-07-06 | 2009-10-01 | 2009-10-13 | 943846.86 | 2.000
11357 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DENTON |  | 26 | 2009599 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on county road. | Pavement Improvement | 2009-07-02 | 2009-08-26 | 2009-10-01 | 2010-07-12 | 203297 | 0.001
11358 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DALLAS | DALLAS-FORT WORTH | Multiple | 2009600 | In order to mitigate congestion and improve air quality, the Texas Department of Transportation will reconstruct the roadway intersection, turn lanes, and signal upgrades on Farm-To-Market 1382. | Pavement Improvement | 2009-05-28 | 2009-06-22 | 2010-11-01 | 2010-04-22 | 1388408.1 | 0.167
11359 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | KAUFMAN |  | 05 | 2009601 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on Farm-To-Market 740. | Pavement Improvement | 2009-09-28 | 2010-02-16 | 2010-11-01 |  | 2856520.65 | 0.323
11360 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | KAUFMAN |  | 05 | 2009602 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on Farm-To-Market 1836. | Pavement Improvement | 2009-06-29 | 2009-09-11 | 2010-06-01 | 2011-07-01 | 1708659.34 | 0.402
11361 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | PARKER |  | 12 | 2009603 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 180. | Pavement Improvement | 2009-06-05 | 2009-08-03 | 2009-12-01 | 2010-03-11 | 3224420.39 | 7.517
11362 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 12 | 2009604 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Interstate Highway 820. | Pavement Improvement | 2009-05-22 | 2009-06-15 | 2009-11-01 | 2010-08-05 | 3790973 | 4.983
11363 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2009605 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 81. | Pavement Improvement | 2009-06-12 | 2009-07-06 | 2009-11-01 | 2009-11-13 | 1846266.94 | 9.526
11364 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | ERATH, HOOD, JOHNSON |  | Multiple | 2009606 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 108,State Highway 171 and US Highway 377. | Pavement Improvement | 2009-06-09 | 2009-07-27 | 2009-10-01 | 2009-10-08 | 1658039.41 | 7.483
11365 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2009607 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 67. | Pavement Improvement | 2009-05-22 | 2009-06-15 | 2009-10-01 | 2009-10-07 | 503662.32 | 2.314
11366 | Completed | C250 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2009608 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 114. | Pavement Improvement | 2009-06-16 | 2009-08-17 | 2009-11-01 | 2009-10-26 | 462312.04 | 1.208
11367 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 26 | 2009609 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 26. | Pavement Improvement | 2009-06-02 | 2009-07-01 | 2009-09-01 | 2009-09-16 | 513264.2 | 3.220
11368 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | PARKER |  | 12 | 2009610 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 171. | Pavement Improvement | 2009-06-04 | 2009-06-15 | 2009-11-01 | 2009-09-28 | 591312.34 | 1.200
11369 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2009611 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 171 and State Highway 174. | Pavement Improvement | 2009-06-09 | 2009-07-28 | 2009-11-01 | 2011-12-15 | 1629194.33 | 8.631
11370 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 06 | 2009613 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 157. | Pavement Improvement | 2009-06-05 | 2009-07-01 | 2010-02-01 | 2009-08-12 | 420119.98 | 1.393
11371 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | Multiple | 2009614 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway at various highways and roads. | Pavement Improvement | 2009-06-05 | 2009-06-28 | 2010-02-01 | 2010-12-30 | 1065751 | 0.100
11372 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | PARKER |  | 12 | 2009615 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 3325. | Pavement Improvement | 2009-10-30 | 2010-03-31 | 2010-07-09 | 2010-07-09 | 587643.05 | 3.143
11373 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CHAMBERS |  | 14 | 2009622 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 61. | Pavement Improvement | 2009-05-28 | 2009-06-23 | 2010-12-30 | 2009-11-13 | 715086.04 | 4.390
11374 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2009623 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on Farm-To-Market 660. | Bridge Replacement | 2010-05-03 | 2010-05-03 | 2011-09-01 | 2010-12-15 | 320650 | 0.090
11375 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GUADALUPE |  | 28 | 2009624 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Interstate Highway 10. | Pavement Improvement | 2009-09-18 | 2009-10-04 | 2009-08-01 | 2010-10-01 | 1784603.23 | 0.550
11376 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MATAGORDA |  | 14 | 2009625 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 35. | Pavement Improvement | 2009-06-04 | 2009-07-10 | 2009-09-01 | 2009-10-02 | 567067.43 | 1.895
11377 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WHARTON |  | 14 | 2009626 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 2765. | Pavement Improvement | 2009-06-12 | 2009-07-06 | 2010-10-01 | 2009-11-25 | 745789.63 | 2.402
11378 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2009627 | In order to improve the transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Inter State 45 Business Loop J. | Pavement Improvement | 2009-08-07 | 2009-08-28 | 2009-09-01 | 2010-07-08 | 1284123.14 | 2.285
11379 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | MASON |  | 11 | 2009632 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 29 and US Highway 377. | Pavement Improvement | 2009-07-02 | 2009-06-22 | 2009-10-01 | 2009-10-19 | 1045214.63 | 27.578
11380 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2009633 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 81. | Pavement Improvement | 2009-06-16 | 2009-08-24 | 2009-10-01 | 2010-06-01 | 1284370.46 | 12.750
11381 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | BURNET |  | 11 | 2009634 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Ranch-To-Market 2341. | Pavement Improvement | 2009-06-22 | 2009-06-29 | 2009-10-01 | 2010-02-17 | 1444444 | 9.444
11382 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | CALDWELL |  | 25 | 2009635 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 80. | Pavement Improvement | 2009-07-06 | 2009-08-10 | 2009-10-01 | 2009-09-03 | 3794304.93 | 11.695
11383 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2009636 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 81. | Pavement Improvement | 2009-06-16 | 2009-08-24 | 2010-11-30 | 2010-06-01 | 732136.28 | 3.289
11384 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | WILSON |  | 28 | 2009637 | In order to preserve the existing transportation system, the Texas Department of Transportation will widen, restore and rehabilitate the roadway to add shoulders on Farm-To-Market 1681. | Pavement Improvement | 2010-01-06 | 2010-04-22 | 2010-12-31 | 2010-11-01 | 1576833.88 | 4.955
11385 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | ATASCOSA |  | 28 | 2009638 | In order to preserve the existing transportation system, the Texas Department of Transportation will widen, restore and rehabilitate the roadway to add passing lanes on State Highway 16. | Pavement Improvement | 2009-10-13 | 2009-10-26 | 2009-10-01 | 2011-09-19 | 1849585.53 | 17.779
11386 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | HENDERSON |  | 05 | 2009639 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 31. | Pavement Improvement | 2009-06-02 | 2009-06-25 | 2009-09-01 | 2010-01-13 | 1994407.08 | 4.944
11387 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LEE |  | 10 | 2009640 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 180. | Pavement Improvement | 2009-06-22 | 2009-07-27 | 2009-09-01 | 2009-10-06 | 519810.19 | 13.155
11388 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | LIVE OAK |  | 15 | 2009646 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway and repair the bridge deck on US Highway 59. | Pavement Widening | 2009-10-21 | 2010-01-04 | 2011-12-01 |  | 17155044.24 | 3.953
11389 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JIM WELLS |  | 15 | 2009647 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a diamond interchange on US Highway 281. | Pavement Widening | 2009-09-14 | 2009-11-16 | 2009-10-01 | 2011-08-10 | 13000000 | 1.840
11390 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2009648 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 277 Business Loop A. | Pavement Improvement | 2009-08-04 | 2009-08-26 | 2009-10-01 | 2009-10-08 | 788364.75 | 1.706
11391 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | 25 | 2009650 | In order to improve the transportation system, the Texas Department of Transportation will replace bridge and approaches and widen frontage roads on Interstate Highway 35. | Pavement Improvement | 2009-10-09 | 2009-11-02 | 2011-02-05 |  | 7000000 | 0.777
11392 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009651 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a new four lane divided roadway on State Highway Loop 20. | New Construction | 2009-10-16 | 2009-11-16 | 2011-02-05 |  | 21758949 | 4.701
11393 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009652 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a new two lane roadway on State Highway Loop 20. | New Construction | 2009-10-16 | 2009-11-16 | 2013-08-20 |  | 9660310.81 | 2.267
11394 | Underway | C240,C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 21 | 2009653 | In order to improve mobility in a metropolitan area, the Alamo Regional Mobility Authority will reconstruct the roadway by expanding the interchange with direct connectors on US Highway 281. | Other | 2010-05-24 | 2010-05-25 | 2013-08-20 |  | 24710353.44 | 1.610
11395 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | Multiple | 2009655 | In order to improve the transportation system at the local level, the Texas Department of Transportation will expand existing roadway to a four lane divided road on Loop 1604. | Pavement Widening | 2010-04-11 | 2010-04-12 | 2011-03-01 |  | 6881042.98 | 0.001
11396 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZOS |  | 17 | 2009657 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a new interchange on State Highway 6. | Pavement Improvement | 2009-06-29 | 2009-07-17 | 2011-03-01 | 2011-01-07 | 7907149.79 | 1.676
11397 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | Multiple | 2009658 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will construct four direct connectors on Belt Way 8. | New Bridge Construction | 2009-10-06 | 2009-10-15 | 2011-09-30 | 2011-06-08 | 29595089.52 | 1.624
11398 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON | MCALLEN-PHARR-EDINBURG | 27 | 2009662 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct tolled main lanes and frontage access on State Highway 550. | New Construction | 2010-05-13 | 2010-08-02 | 2012-03-01 |  | 34161741.4 | 3.926
11399 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BROOKS |  | 15 | 2009663 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a four lane expressway with tolled main lanes on US Highway 281. | Pavement Widening | 2009-07-14 | 2009-08-18 | 2012-08-01 |  | 40039527.42 | 5.581
11400 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BROOKS |  | 15 | 2009664 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct four lane expressway with tolled main lanes on US Highway 281. | Pavement Widening | 2009-07-14 | 2009-08-18 | 2010-12-01 |  | 25860723.89 | 2.062
11401 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | RUNNELS, TOM GREEN, COLEMAN |  | 11 | 2009665 | In order to supplement the transportation system, the Texas Department of Transportation will rehabilitate the Railroad on South Orient railroad. | Other | 2009-09-01 | 2009-09-15 | 2013-08-01 | 2010-04-30 | 5078194.05 | 0.003
11402 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2009679 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will install electronic toll booths and equipment for a new two lane toll road on Loop 49. | Other | 2009-07-21 | 2009-08-06 | 2013-08-01 |  | 3876000 | 9.019
11403 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON |  | Multiple | 2009681 | In order to supplement the transportation system, Cameron County will add improvements to the Union Pacific Railroad Olmita switchyard. | Other | 2010-07-12 | 2010-07-13 | 2011-05-15 |  | 3330881.48 | 17.000
11404 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON |  | 27 | 2009682 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway by widening to a four lane divided road on Farm-To-Market 1479. | Pavement Widening | 2009-08-10 | 2010-03-08 | 2011-03-01 | 2010-11-24 | 1887239.52 | 0.800
11405 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2009689 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway by widening to a four lane divided on county road. | Pavement Widening | 2009-09-17 | 2009-10-13 | 2011-03-01 | 2011-05-04 | 4071711.18 | 1.761
11406 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009691 | In order to improve the transportation system, the Texas Department of Transportation will install new traffic signals on Farm-To-Market 2240. | Safety/Traffic Management | 2010-01-25 | 2010-06-09 |  | 2011-03-01 | 31344.75 | 0.001
11407 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009692 | In order to improve the transportation system, the Texas Department of Transportation will install new traffic signals on Farm-To-Market 2240. | Safety/Traffic Management | 2010-01-25 | 2010-06-09 |  | 2011-03-01 | 31642.95 | 0.001
11408 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009693 | In order to improve the transportation system, the Texas Department of Transportation will upgrade existing traffic signals on Farm-To-Market 2240. | Safety/Traffic Management | 2010-01-25 | 2010-06-09 |  | 2011-03-01 | 59415.1 | 0.001
11409 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009694 | In order to improve the transportation system, the Texas Department of Transportation will upgrade existing traffic signals on US Highway 82. | Safety/Traffic Management | 2010-01-25 | 2010-06-09 |  | 2011-03-01 | 84165.2 | 0.001
11410 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009695 | In order to improve the transportation system, the Texas Department of Transportation will upgrade existing traffic signals on Loop 14. | Safety/Traffic Management | 2010-01-25 | 2010-06-09 | 2009-09-02 | 2011-03-01 | 85770 | 0.001
11411 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | SHELBY |  | 01 | 2009696 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Loop 500,Loop 547,State Highway 87,US Highway 287 Business Loop V and US H | Pavement Improvement | 2009-07-28 | 2009-10-06 | 2010-10-01 | 2010-02-23 | 1612585.31 | 6.619
11412 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | BRAZORIA | HOUSTON | 14 | 2009697 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will construct a railroad-highway grade separation and widen to a four lane divided suburban section on Farm | Pavement Widening | 2009-09-01 | 2009-10-15 | 2011-10-16 | 2011-09-01 | 18452982.51 | 3.092
11413 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 09 | 2009699 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will restore and rehabilitate the roadway by constructing frontage road intersection improvements on State H | Pavement Improvement | 2009-10-06 | 2009-10-27 | 2010-05-01 | 2010-03-18 | 635655.19 | 0.603
11414 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | WALLER | HOUSTON | 10 | 2009700 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway by widening to four lane divided urban section on Farm-To-Market 1098. | Pavement Widening | 2009-09-09 | 2009-10-19 | 2011-11-15 | 2011-03-24 | 2485857.89 | 0.551
11415 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2009701 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway to a four lane road on Farm-To-Market 359. | Pavement Widening | 2010-04-01 | 2010-04-19 | 2011-09-15 |  | 11849354.25 | 2.370
11416 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2009703 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway to a four lane road on Farm-To-Market 1464. | Pavement Widening | 2010-04-14 | 2010-06-14 | 2012-03-31 |  | 13235602 | 2.630
11417 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON | HOUSTON | 14 | 2009704 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway by constructing a railroad grade separation on Farm-To-Market 1764. | Pavement Improvement | 2010-01-04 | 2010-01-25 | 2011-11-30 | 2011-04-29 | 10399818.18 | 1.061
11418 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2009705 | In order to improve mobility in a metropolitan area, the Gulf Coast Rail District (GCRD) will study the construction of a commuter rail on various highways and roads. | Other | 2010-03-08 | 2010-03-08 | 2013-03-02 |  | 2000000 | 0.001
11419 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2009706 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will install an intelligent traffic system for real-time highway performance monitoring on various highways | Safety/Traffic Management | 2010-05-13 |  | 2012-10-01 |  | 4073749 | 0.001
11420 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2009707 | In order to improve mobility in a metropolitan area, the Houston Galveston Area Council will conduct a freight analysis on various highways and roads. | Other | 2010-02-01 | 2009-10-05 | 2012-03-31 |  | 2500000 | 0.001
11421 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2009708 | In order to preserve the existing transportation system, the City of Abilene will perform reconstruction on city street. | Pavement Improvement | 2010-04-15 | 2010-06-14 | 2010-08-15 | 2010-08-26 | 571045.33 | 1.008
11422 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2009709 | In order to preserve the existing transportation system, the City of Abilene will perform restoration and resurfacing on city street. | Pavement Improvement | 2010-04-15 | 2010-06-10 | 2010-09-15 | 2010-08-25 | 394585.85 | 1.913
11423 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2009710 | In order to preserve the existing transportation system, the City of Abilene will perform restoration and resurfacing on city street. | Pavement Improvement | 2010-04-15 | 2010-05-04 | 2011-02-01 | 2010-08-28 | 878041.94 | 3.180
11424 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | STARR |  | 28 | 2009711 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway; add curb and gutter and storm sewers on Farm-To-Market 755. | Pavement Improvement | 2009-08-10 | 2009-10-20 | 2009-09-01 |  | 2521180.59 | 0.921
11425 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON |  | 27 | 2009712 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Spur 206. | Pavement Improvement | 2009-08-19 | 2009-09-21 | 2009-09-01 | 2009-11-02 | 1449742.58 | 3.463
11426 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | POTTER |  | 13 | 2009713 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on various highways and roads. | Pavement Improvement | 2009-10-22 | 2010-05-20 | 2011-06-01 | 2010-06-25 | 215909.28 | 1.000
11427 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | RANDALL | AMARILLO | 13 | 2009714 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway by upgrading to an urban section on Loop 335. | Pavement Widening | 2010-04-22 | 2010-06-14 | 2011-06-01 | 2011-09-26 | 2083226.09 | 1.988
11428 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | RANDALL |  | 13 | 2009715 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on various highways and roads. | Pavement Improvement | 2009-11-02 | 2010-01-25 |  | 2012-01-27 | 155676.82 | 1.000
11429 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | RANDALL | AMARILLO | 13 | 2009716 | In order to improve the transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on various highways and roads. | Pavement Improvement | 2010-04-22 | 2010-06-14 |  | 2011-09-26 | 451413.53 | 0.435
11430 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | MIDLAND |  | 11 | 2009717 | In order to improve the transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 307. | Pavement Improvement | 2010-01-06 | 2010-01-25 | 2010-11-22 | 2011-05-05 | 5697710.48 | 7.099
11431 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | ECTOR |  | 11 | 2009719 | In order to improve the transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Spur 588. | Pavement Improvement | 2009-12-07 | 2010-02-09 | 2010-07-12 | 2010-07-08 | 344886.18 | 0.432
11432 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | MIDLAND |  | 11 | 2009720 | In order to improve the transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Spur 588. | Pavement Improvement | 2009-12-07 | 2010-02-09 | 2010-07-12 | 2010-07-08 | 810232.45 | 1.685
11433 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2009721 | In order to supplement the transportation system, the Texas Department of Transportation will construct a hike and bike trail to accommodate bicycle transportation and pedestrians on various highways | Transportation Enhancements | 2010-02-01 | 2010-02-16 | 2011-02-10 |  | 2582604.07 | 2.900
11434 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TOM GREEN |  | 11 | 2009724 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 67 Business Loop H. | Pavement Improvement | 2009-12-07 | 2010-03-02 | 2010-06-14 | 2011-03-01 | 2489385.26 | 3.420
11435 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TOM GREEN |  | 11 | 2009725 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Ranch-To-Market 853. | Pavement Improvement | 2010-05-05 | 2010-05-05 | 2010-06-14 | 2010-06-14 | 277891.84 | 0.691
11436 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TOM GREEN | SAN ANGELO | 11 | 2009745 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 67. | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2011-02-15 | 2010-06-14 | 316396.66 | 1.180
11437 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | TOM GREEN | SAN ANGELO | 11 | 2009746 | In order to preserve the existing transportation system, the City of San Angelo will perform restoration and resurfacing on city street. | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2011-02-15 | 2010-10-13 | 1103076 | 1.000
11438 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GREGG | LONGVIEW | 01 | 2009748 | In order to preserve the existing transportation system, the Texas Department of Transportation will install traffic signals on State Highway 300. | Safety/Traffic Management | 2010-04-26 | 2010-04-26 |  | 2010-09-24 | 185678.15 | 0.200
11439 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GONZALES |  | 25 | 2009749 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway by widening the roadway and adding shoulders on Farm-To-Market | Pavement Improvement | 2010-01-06 | 2010-04-22 |  | 2010-11-01 | 382109.19 | 1.237
11440 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA | VICTORIA | 14 | 2009755 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 87. | Pavement Improvement | 2010-01-07 | 2010-02-01 |  | 2010-11-01 | 1338000 | 3.408
11441 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA | VICTORIA | 14 | 2009762 | In order to improve the existing transportation system, the Texas Department of Transportation will construct turn lanes on US Highway 87. | Pavement Improvement | 2010-01-07 | 2010-02-01 |  | 2010-11-01 | 531000 | 0.671
11442 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA | VICTORIA | 14 | 2009763 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 87. | Pavement Improvement | 2010-01-07 | 2010-02-01 |  | 2010-11-01 | 137719.52 | 0.492
11443 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA | VICTORIA | 14 | 2009764 | In order to improve the existing transportation system, the Texas Department of Transportation will construct turn lanes on Loop 463. | Pavement Improvement | 2010-01-07 | 2010-02-01 | 2010-09-30 | 2010-11-01 | 350837.02 | 0.486
11444 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009781 | In order to preserve the existing transportation system, Webb County will reconstruct the roadway without adding capacity on various highways and roads. | Pavement Improvement | 2011-01-24 | 2011-01-24 | 2011-05-03 | 2011-05-03 | 288953 | 0.600
11445 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009782 | In order to preserve the existing transportation system, Webb County will reconstruct the roadway and add shoulders on county road. | Pavement Improvement | 2010-11-24 | 2010-12-04 | 2011-07-15 | 2011-07-15 | 434779 | 1.000
11446 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2009783 | In order to preserve the existing transportation system, Webb County will resurface the roadway on various highways and roads. | Pavement Improvement | 2010-09-27 | 2010-10-08 | 2011-07-15 | 2011-07-15 | 1751729.8 | 5.000
11447 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO |  | 15 | 2009785 | In order to improve the transportation system, the Texas Department of Transportation will construct a new overpass on US Highway 83. | Pavement Improvement | 2010-05-17 | 2010-08-02 | 2012-03-09 |  | 10000000 | 0.600
11448 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | Multiple | 2009786 | In order to improve the transportation system in a metropolitan area, the City of San Antonio will install warning devices at low water crossings on city street. | Safety/Traffic Management | 2010-06-30 | 2010-06-30 | 2010-10-29 | 2010-10-15 | 550000 | 0.001
11449 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 20 | 2009787 | In order to improve mobility in a metropolitan area, the City of San Antonio will construct a hike and bike trail to accommodate bicycle transportation and pedestrians on city street. | Transportation Enhancements | 2010-07-29 | 2010-07-29 | 2011-02-28 | 2011-02-28 | 403073.56 | 0.200
11450 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | NUECES | CORPUS CHRISTI | 27 | 2009789 | In order to improve mobility, mitigate congestion in a metropolitan area, the Texas Department of Transportation will restore and rehabilitate the roadway; construct a median and add improvements to c | Pavement Improvement | 2010-07-08 | 2010-08-31 |  |  | 3800000 | 2.010
11451 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | NUECES | CORPUS CHRISTI | 27 | 2009790 | In order to improve mobility, mitigate congestion in a metropolitan area, the Texas Department of Transportation will restore and rehabilitate the roadway; construct a median and add improvements to c | Pavement Improvement | 2010-07-08 | 2010-08-31 |  |  | 3464791 | 2.250
11452 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | Multiple | 2009792 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway by widening to a four lane road on city street. | Pavement Widening | 2010-05-11 | 2010-06-07 | 2012-02-29 |  | 4500000 | 2.211
11453 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ELLIS |  | 06 | 2009801 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Inter State 45 Business Loop G. | Pavement Improvement | 2009-08-26 | 2009-09-15 | 2010-02-01 | 2010-05-05 | 1727611.14 | 2.260
11454 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CALLAHAN |  | 19 | 2009804 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 36. | Pavement Improvement | 2009-08-06 | 2009-08-10 | 2010-02-01 | 2009-11-20 | 4960299.07 | 18.082
11455 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN PATRICIO |  | 15 | 2009805 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 77. | Pavement Improvement | 2009-09-09 | 2009-09-25 | 2009-02-01 | 2010-04-12 | 1964947.15 | 4.182
11456 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | EL PASO |  | 16 | 2009816 | In order to preserve the existing transportation system, the Texas Department of Transportation will construct features or devices to enhance roadway safety on Farm-To-Market 259. | Safety/Traffic Management | 2010-11-16 | 2011-05-02 | 2010-12-16 | 2011-08-12 | 93011 | 0.200
11457 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON | DALLAS-FORT WORTH | 17 | 2009834 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct roadway by widening to a four lane divided road and constructing a diamond interchange on U | Pavement Widening | 2010-01-25 | 2010-03-04 | 2011-06-01 |  | 7728131 | 2.329
11458 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON | DALLAS-FORT WORTH | 17 | 2009835 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway by constructing ramps at interchange and adding median barrier on US Highway 67 | Pavement Improvement | 2010-01-25 | 2010-03-04 | 2011-06-01 |  | 2271868.44 | 0.909
11459 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2009837 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconfigure and upgrade the intersection traffic signal system on State Highway 6. | Safety/Traffic Management | 2010-02-19 | 2010-03-15 | 2010-11-30 | 2010-12-17 | 1038548.56 | 0.000
11460 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WILLIAMSON |  | 31 | 2009866 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway to a four lane divided road on Farm-To-Market 1460. | Pavement Widening | 2009-10-30 | 2009-12-01 | 2010-01-01 |  | 9229357.32 | 2.356
11461 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DALLAS |  | Multiple | 2009874 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 78. | Pavement Improvement | 2009-09-09 | 2009-10-19 | 2010-01-01 | 2010-07-19 | 1528462.18 | 3.256
11462 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 06 | 2009912 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 157,Interstate Highway 20 and US Highway 287 Business Loop | Pavement Improvement | 2010-05-04 | 2010-05-04 | 2010-07-21 | 2010-07-21 | 1037102.85 | 3.296
11463 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2009921 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a railroad grade separation structure and approaches at the Union Pacific Railro | Pavement Improvement | 2009-11-02 | 2009-11-19 | 2011-05-01 | 2011-06-15 | 1713000 | 0.506
11464 | Completed | C950 | Ferryboat | TEXAS | NUECES |  | 27 | 2009928 | In order to supplement the transportation system, the Texas Department of Transportation will construct a new 28 car ferry boat State Highway 361. | Other | 2009-08-31 | 2010-01-25 | 2011-05-01 | 2011-06-24 | 7200000 | 0.001
11465 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | STEPHENS |  | 19 | 2010003 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 183. | Pavement Improvement | 2009-10-14 | 2009-11-19 |  | 2011-08-02 | 1648067 | 4.264
11466 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | Multiple | 2010004 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Interstate Highway 35. | Pavement Improvement | 2009-10-09 | 2009-11-02 | 2010-02-22 |  | 431995.37 | 0.379
11467 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | COKE |  | 11 | 2010005 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 277. | Pavement Improvement | 2009-10-21 | 2009-11-09 |  | 2010-02-17 | 360268.38 | 0.001
11468 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2010006 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 2415. | Pavement Improvement | 2009-11-30 | 2010-03-31 | 2010-09-01 | 2010-12-14 | 1249457.36 | 6.266
11469 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CASS |  | 01 | 2010007 | In order to improve the transportation system, the Texas Department of Transportation will install and upgrade traffic control devices on various highways and roads. | Safety/Traffic Management | 2009-10-16 | 2010-03-03 |  | 2010-11-18 | 399251.94 | 0.001
11470 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MARION |  | 01 | 2010008 | In order to improve the transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 134. | Pavement Improvement | 2009-11-02 | 2010-08-02 |  | 2010-11-22 | 267595.18 | 3.047
11471 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | BOWIE | TEXARKANA (TX-AR) | 04 | 2010009 | In order to improve the transportation system, the Texas Department of Transportation will upgrade existing traffic signals on State Highway 93. | Safety/Traffic Management | 2009-10-16 | 2010-02-24 |  | 2010-07-22 | 134750.78 | 0.066
11472 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | UPSHUR |  | 01 | 2010012 | In order to improve the transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 259. | Pavement Improvement | 2009-10-16 | 2010-07-16 |  | 2010-10-08 | 715360 | 3.230
11473 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LIBERTY |  | 08 | 2010024 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 834. | Pavement Improvement | 2009-10-14 | 2009-10-12 |  | 2010-05-18 | 948380.57 | 6.000
11474 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MILAM |  | 31 | 2010027 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 79. | Pavement Improvement | 2009-10-30 | 2010-06-01 |  | 2010-08-10 | 766187.19 | 5.560
11475 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GRIMES |  | 17 | 2010029 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 30. | Pavement Improvement | 2009-10-14 | 2009-11-02 | 2010-05-31 | 2010-06-04 | 1849901.76 | 8.067
11476 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FREESTONE |  | 06 | 2010030 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 489. | Pavement Improvement | 2009-11-06 | 2010-01-05 |  | 2010-10-29 | 1317884.18 | 10.464
11477 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DICKENS |  | 13 | 2010031 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 836. | Pavement Improvement | 2009-10-15 | 2009-10-27 |  | 2009-11-30 | 90114 | 7.715
11478 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JIM WELLS |  | 15 | 2010032 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 44. | Pavement Improvement | 2009-11-12 | 2010-01-20 |  | 2010-07-30 | 3743267.84 | 8.710
11479 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ARANSAS, SAN PATRICIO |  | Multiple | 2010033 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 35 Business Loop L. | Pavement Improvement | 2009-10-26 | 2009-11-11 |  | 2010-04-29 | 782350.63 | 1.942
11480 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN PATRICIO |  | 15 | 2010034 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 77. | Pavement Improvement | 2009-11-06 | 2009-12-09 | 2011-03-30 | 2010-08-25 | 2224860.59 | 5.502
11481 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | COLLIN |  | 04 | 2010037 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway from a rural two lane road to a two lane urban highway with shoulders on F | Pavement Improvement | 2009-10-26 | 2010-07-12 |  | 2011-11-28 | 4887963.33 | 1.054
11482 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | PRESIDIO, BREWSTER |  | 23 | 2010040 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 67. | Pavement Improvement | 2009-09-30 | 2009-10-02 | 2010-02-24 | 2009-11-30 | 981994.38 | 2.819
11483 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | EL PASO |  | Multiple | 2010041 | In order to improve the existing transportation system, the Texas Department of Transportation will upgrade various overhead and large ground mounted signs on various highways and roads. | Safety/Traffic Management | 2009-10-16 | 2010-02-28 | 2010-02-24 | 2010-09-10 | 635030.08 | 1.000
11484 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | PALO PINTO |  | 13 | 2010043 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 16. | Pavement Improvement | 2009-11-02 | 2010-08-23 | 2010-10-10 | 2010-10-22 | 1473364.87 | 11.262
11485 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WISE |  | 12 | 2010044 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 81. | Pavement Improvement | 2009-11-02 | 2010-08-18 | 2010-11-01 | 2011-03-03 | 837946.86 | 4.092
11486 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2010045 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 174. | Pavement Improvement | 2009-11-16 | 2010-02-09 | 2010-07-08 | 2010-07-12 | 1996623.31 | 2.829
11487 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON |  | 17 | 2010046 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 171. | Pavement Improvement | 2009-11-12 | 2010-04-07 | 2010-07-12 | 2010-07-12 | 979533.57 | 3.588
11488 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HOOD |  | 17 | 2010047 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 167. | Pavement Improvement | 2009-11-06 | 2009-12-14 | 2009-12-22 | 2010-01-05 | 352322.3 | 2.010
11489 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ERATH, SOMERVELL |  | Multiple | 2010048 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 6 and US Highway 67. | Pavement Improvement | 2009-11-16 | 2010-07-16 | 2010-09-01 | 2011-02-23 | 1038715.02 | 18.310
11490 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON |  | 14 | 2010051 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 3005. | Pavement Improvement | 2009-11-02 | 2009-11-18 | 2010-11-30 | 2010-08-20 | 3227313 | 18.273
11491 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010053 | In order to improve the existing transportation system, the Texas Department of Transportation will apply pavement markings on Interstate Highway 45. | Safety/Traffic Management | 2009-11-02 | 2010-01-12 | 2010-05-14 | 2010-05-18 | 324477.4 | 8.818
11492 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2010055 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 359. | Pavement Improvement | 2009-10-21 | 2009-11-16 | 2010-07-01 | 2010-03-24 | 1657626 | 10.859
11493 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2010056 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace the bridge and approaches on Farm-To-Market 762. | Bridge Replacement | 2009-10-16 | 2009-09-09 | 2010-06-30 | 2010-07-26 | 1288241.82 | 0.124
11494 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010057 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade and reconstruct various traffic signals on various highways and roads. | Safety/Traffic Management | 2009-11-16 | 2010-08-17 | 2012-06-01 |  | 898349.73 | 0.001
11495 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010058 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade and reconstruct various traffic signals on various highways and roads. | Safety/Traffic Management | 2009-10-30 | 2011-01-25 | 2012-06-01 |  | 946870.85 | 0.001
11496 | Completed | C220 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | Multiple | 2010059 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on various highways and roads. | Transportation Enhancements | 2009-11-16 | 2009-12-18 | 2012-05-01 | 2010-03-15 | 186209.34 | 0.001
11497 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | Multiple | 2010061 | In order to preserve the existing transportation system, the Texas Department of Transportation will perform bridge maintenance to include repairing steel members and cleaning and painting on various | Other | 2009-10-26 | 2009-11-18 | 2010-05-30 | 2010-06-03 | 1235010.44 | 0.001
11498 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON |  | Multiple | 2010063 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on various highways and roads. | Pavement Improvement | 2010-01-04 | 2010-03-10 | 2010-06-15 | 2010-07-02 | 442388.58 | 25.446
11499 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WALLER |  | 10 | 2010064 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1489. | Pavement Improvement | 2009-10-21 | 2009-11-06 | 2010-02-01 | 2010-01-22 | 777940 | 4.842
11500 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2010065 | In order to improve the existing transportation system, the Texas Department of Transportation will construct drainage improvements on Farm-To-Market 1314. | Other | 2009-11-06 | 2010-02-03 | 2010-05-30 | 2010-06-10 | 330695.52 | 0.338
11501 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS |  | 07 | 2010066 | In order to improve the existing transportation system, the Texas Department of Transportation will reshape and stabilize erosion at White Oak Bayou on Belt Way 8. | Other | 2009-11-04 | 2009-12-01 | 2010-04-01 | 2010-02-01 | 103293.39 | 0.034
11502 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LA SALLE |  | 28 | 2010067 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway to include reconstruction of north bound main lanes and ramps | Pavement Improvement | 2009-11-18 | 2009-12-14 |  | 2010-03-05 | 1574216.7 | 8.468
11503 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CROSBY, FLOYD |  | Multiple | 2010074 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1471,Farm-To-Market 1958,Farm-To-Market 651 and State Highw | Pavement Improvement | 2009-10-15 | 2009-10-27 | 2009-12-03 | 2009-11-30 | 816603.44 | 38.637
11504 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN AUGUSTINE, SABINE, SAN JACINTO |  | Multiple | 2010075 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 103,US Highway 59 and US Highway 96. | Pavement Improvement | 2009-11-02 | 2009-11-18 | 2010-09-30 | 2010-10-28 | 1236135.47 | 23.090
11505 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WINKLER |  | 11 | 2010077 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 302. | Pavement Improvement | 2009-10-21 | 2009-11-17 | 2010-05-28 | 2010-05-27 | 1773715.49 | 16.312
11506 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2010078 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 82. | Pavement Improvement | 2010-05-04 | 2010-05-04 | 2010-10-31 |  | 2943236.01 | 5.362
11507 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO |  | 15 | 2010080 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 907 and State Highway 107. | Pavement Improvement | 2009-11-02 | 2010-02-26 | 2010-07-07 | 2010-07-07 | 1569134.89 | 10.155
11508 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON |  | 27 | 2010081 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade drainage culvert and raise road on Farm-To-Market 506. | Other | 2009-10-15 | 2009-10-16 | 2010-12-17 | 2009-12-17 | 854177.32 | 0.920
11509 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | Multiple | 2010083 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 2061. | Pavement Improvement | 2009-11-06 | 2009-12-07 | 2010-04-22 | 2010-04-22 | 540908 | 2.377
11510 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | Multiple | 2010087 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on State Highway 16. | Transportation Enhancements | 2009-11-02 | 2009-11-18 | 2010-07-13 |  | 191565.56 | 0.500
11511 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | UVALDE |  | 23 | 2010088 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Ranch-To-Market 187. | Pavement Improvement | 2009-10-15 | 2009-11-02 | 2013-11-30 | 2010-07-13 | 1280003.52 | 5.566
11512 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | 20 | 2010089 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on Interstate Highway 410. | Transportation Enhancements | 2009-11-02 | 2009-11-18 | 2013-05-31 |  | 865906.52 | 0.001
11513 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | ATASCOSA |  | 28 | 2010090 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on State Highway 16. | Transportation Enhancements | 2009-10-21 | 2009-12-02 | 2009-10-19 |  | 85788 | 0.700
11514 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FRIO |  | 28 | 2010091 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore, widen and rehabilitate the roadway on Farm-To-Market 140. | Pavement Improvement | 2009-10-15 | 2009-10-19 | 2012-12-31 | 2010-11-09 | 3097967.34 | 10.700
11515 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | GUADALUPE |  | 28 | 2010092 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on various highways and roads. | Transportation Enhancements | 2009-10-16 | 2009-11-01 |  |  | 491794.72 | 0.001
11516 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH | TYLER | 01 | 2010094 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 2493. | Pavement Improvement | 2009-10-21 | 2010-05-05 |  | 2010-07-14 | 635945.99 | 1.593
11517 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ANDERSON |  | 05 | 2010095 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 79. | Pavement Improvement | 2009-10-22 | 2010-06-23 |  | 2011-03-31 | 1582436.6 | 3.391
11518 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MCLENNAN, LIMESTONE |  | Multiple | 2010097 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 84. | Pavement Improvement | 2009-11-06 | 2009-12-03 | 2010-10-15 | 2011-02-28 | 2534566.15 | 32.206
11519 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WILBARGER |  | 13 | 2010098 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 183. | Pavement Improvement | 2009-10-26 | 2010-06-17 | 2010-08-05 | 2010-08-05 | 605866.52 | 1.619
11520 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WHARTON |  | 14 | 2010099 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 59. | Pavement Improvement | 2009-11-12 | 2009-12-30 |  | 2010-11-01 | 4409900.24 | 7.030
11521 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CALHOUN |  | 14 | 2010100 | In order to improve the transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 35. | Pavement Improvement | 2009-11-24 | 2010-01-25 |  | 2010-04-15 | 1813198.22 | 11.040
11522 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | RANDALL |  | 13 | 2010103 | In order improve the transportation system, the Texas Department of Transportation will construct curb ramps and concrete median on Interstate Highway 27. | Pavement Improvement | 2009-10-30 | 2010-02-15 |  | 2011-01-12 | 80828 | 0.414
11523 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LEE |  | 10 | 2010123 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace bridge and approaches on Farm-To-Market 696. | Pavement Improvement | 2010-01-07 | 2010-01-27 | 2010-10-30 | 2011-05-24 | 2075715.18 | 1.628
11524 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | NAVARRO |  | 06 | 2010137 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will replace bridge and approaches on Farm-To-Market 709 and State Highway 31. | Bridge Replacement | 2009-12-07 | 2010-03-01 | 2010-10-30 | 2010-12-08 | 855639.4 | 0.087
11525 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | GREGG | LONGVIEW | 01 | 2010187 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 80. | Pavement Improvement | 2010-05-04 | 2010-05-04 |  | 2011-04-27 | 1987737.8 | 4.040
11526 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | GREGG | LONGVIEW | 01 | 2010188 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 259. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-09-30 | 2010-08-16 | 1294548.95 | 2.930
11527 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LA SALLE, VAL VERDE |  | Multiple | 2010199 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Interstate 35 Business Loop C and US Highway 90. | Pavement Improvement | 2009-11-16 | 2010-09-21 | 2010-09-30 | 2010-12-21 | 573297.57 | 4.557
11528 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS |  | 10 | 2010205 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 183. | Pavement Improvement | 2010-05-05 | 2010-05-05 | 2010-06-30 | 2010-08-17 | 421090.25 | 0.721
11529 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WILLIAMSON |  | 31 | 2010206 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on State Highway 29. | Pavement Improvement | 2010-04-05 | 2010-04-05 | 2010-08-10 | 2010-07-01 | 501272.5 | 1.250
11530 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | 21 | 2010207 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 123. | Pavement Improvement | 2010-01-06 | 2010-03-11 | 2010-05-24 | 2010-06-30 | 170071.78 | 0.375
11531 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CALDWELL |  | 25 | 2010208 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 142. | Pavement Improvement | 2010-05-04 | 2010-05-04 |  | 2010-08-10 | 921349 | 1.838
11532 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HAYS |  | Multiple | 2010211 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 621. | Pavement Improvement | 2010-01-07 | 2010-03-09 |  | 2010-06-30 | 408997.68 | 2.935
11533 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | LLANO |  | 11 | 2010212 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Ranch-To-Market 2900. | Pavement Improvement | 2010-01-07 | 2010-03-16 |  | 2010-05-24 | 862584.83 | 0.985
11534 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010232 | In order to improve the condition of the existing transportation system, the Texas Department of Transportation will rehabilitate the bridge & approaches and reconstruct the roadway to three-lane fron | Pavement Widening | 2010-04-26 | 2010-04-26 | 2013-04-18 |  | 46415172.1 | 3.423
11535 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | COLEMAN |  | 11 | 2010243 | In order to enhance the safety of the transportation system, the Texas Department of Transportation will improve and rehabilitate railroad highway crossing on South Orient railroad. | Pavement Improvement | 2010-04-09 | 2010-04-09 | 2011-05-15 | 2011-04-05 | 646035.93 | 0.001
11536 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | DUVAL |  | Multiple | 2010249 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 59. | Pavement Improvement | 2010-03-09 | 2010-03-29 | 2011-05-15 | 2010-10-11 | 1109647.67 | 0.826
11537 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | RUNNELS, TOM GREEN |  | 11 | 2010256 | In order to enhance the safety of the transportation system, the Texas Department of Transportation will improve and rehabilitate railroad highway crossing on South Orient railroad. | Pavement Improvement | 2010-04-09 | 2010-04-09 | 2011-05-15 | 2011-04-05 | 3669232.96 | 0.002
11538 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ATASCOSA |  | 28 | 2010286 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Interstate Highway 37. | Pavement Improvement | 2010-02-08 | 2010-02-24 |  | 2010-08-02 | 3684661.2 | 14.741
11539 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | COLORADO, FAYETTE |  | 15 | 2010289 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Interstate Highway 10. | Pavement Improvement | 2010-02-16 | 2010-05-17 |  | 2010-09-17 | 3455979 | 15.333
11540 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010294 | In order to improve the existing transportation system in a metropolitan area, the Central Texas Regional Mobility Authority will establish a roadside assistance program on various highways and roads. | Other | 2010-07-19 | 2010-09-20 | 2011-11-01 |  | 2000000 | 0.001
11541 | Completed | C250,C240 | Highway Infrastructure Investment Grant | TEXAS | JASPER |  | 08 | 2010301 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 96. | Pavement Improvement | 2010-02-16 | 2010-04-14 | 2011-11-01 | 2011-03-07 | 5820209.5 | 8.440
11542 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | Multiple | 2010303 | In order to improve the existing transportation system in a metropolitan area, the Texas Department of Transportation will upgrade all traffic signals to provide regionalized traffic flow on various h | Safety/Traffic Management | 2010-04-30 | 2010-07-01 | 2012-06-30 |  | 2780094.72 | 0.100
11543 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 21 | 2010304 | In order to improve the existing transportation system in a metropolitan area, the Texas Department of Transportation will install continuous left turn lane and shoulders on State Highway 71. | Pavement Improvement | 2010-04-08 | 2010-06-07 | 2011-06-01 |  | 2550668.74 | 0.300
11544 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 21 | 2010305 | In order to improve the existing transportation system in a metropolitan area, the Texas Department of Transportation will install continuous left turn lane and shoulders on State Highway 71. | Pavement Improvement | 2010-04-08 | 2010-06-07 | 2011-03-01 |  | 202557.12 | 0.001
11545 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | HARRISON | LONGVIEW | 01 | 2010313 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Loop 281. | Pavement Improvement | 2010-04-27 | 2010-04-27 |  | 2011-01-05 | 4656179.97 | 2.480
11546 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HAYS | AUSTIN | Multiple | 2010314 | In order to improve the existing transportation system in a metropolitan area, the Texas Department of Transportation will construct overpass and reconstruct frontage roads on Interstate Highway 35. | Pavement Improvement | 2010-05-13 | 2010-06-08 |  |  | 5796648.48 | 0.529
11547 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | BASTROP |  | 25 | 2010317 | In order to preserve the existing transportation system, the Texas Department of Transportation will widen, rehabilitate and add a turn lane to the roadway on Farm-To-Market 20. | Pavement Improvement | 2010-04-13 | 2010-07-08 | 2012-01-01 | 2011-09-09 | 4792710.08 | 2.016
11548 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010320 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Loop 1. | Pavement Improvement | 2010-03-18 | 2010-06-22 | 2012-01-01 |  | 3400000 | 4.810
11549 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010393 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will implement a city-wide advanced traffic management system on various highways and roads. | Other | 2010-08-18 | 2010-08-23 | 2011-06-01 |  | 5000000 | 0.001
11550 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | DALLAM |  | 13 | 2010394 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct and add two lanes to the roadway on US Highway 87. | Pavement Widening | 2010-03-29 | 2010-03-29 |  |  | 7838956.43 | 7.449
11551 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | NUECES | CORPUS CHRISTI | 27 | 2010395 | In order to improve the transportation system at the local level, the Texas Department of Transportation will reconstruct the frontage road and modify entrance and exit ramps on Interstate Highway 37. | Pavement Improvement | 2010-02-01 | 2010-04-06 |  |  | 7841712.11 | 1.307
11552 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2010398 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway to widen to a four lane divided median road on US Highway 82. | Pavement Widening | 2010-04-30 | 2010-07-01 | 2011-10-31 |  | 3467569.48 | 4.718
11553 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 06 | 2010399 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway to widen to a four lane divided median road, with shoulders, on Farm-To-Mar | Pavement Widening | 2010-05-05 | 2011-06-17 | 2012-03-01 |  | 6895052.12 | 1.503
11554 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO |  | 15 | 2010400 | In order to preserve the existing transportation system, the Texas Department of Transportation will construct overpass and frontage roads on Farm-To-Market 396. | Pavement Improvement | 2010-05-17 | 2010-08-02 | 2012-03-09 |  | 11000000 | 1.500
11555 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | POTTER | AMARILLO | 13 | 2010401 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a new railroad overpass on Grand Street and Southeast Third Avenue. | Pavement Improvement | 2010-05-26 | 2010-07-27 |  |  | 5073269.94 | 0.442
11556 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | JEFFERSON |  | 02 | 2010402 | In order to supplement the transportation system, the Texas Department of Transportation will reconstruct the roadway to add two lanes and a left turn lane on Farm-To-Market 365. | Pavement Widening | 2010-06-22 | 2010-08-03 | 2010-10-01 |  | 6775901.16 | 2.400
11557 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 10 | 2010403 | In order to supplement the transportation system, the Texas Department of Transportation will construct two direct connectors on Interstate Highway 10. | New Bridge Construction | 2010-06-15 | 2010-07-07 | 2012-02-29 |  | 24308770.03 | 0.001
11558 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 2010404 | In order to improve the transportation system at the local level, the Texas Department of Transportation will construct direct connector on State Highway 146. | New Bridge Construction | 2010-03-18 | 2010-05-10 | 2011-07-31 | 2011-01-23 | 4118844.5 | 0.391
11559 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010421 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will add a traffic signal, left and right turn lanes, and shoulders on State Highway 71. | Pavement Improvement | 2010-01-13 | 2010-02-15 |  | 2010-11-10 | 1475838.69 | 0.870
11560 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | EL PASO | EL PASO | 16 | 2010460 | In order to preserve the existing transportation system, the Texas Department of Transportation will rehabilitate existing Burlington Northern Santa Fe Railroad track and construct 550 feet of connect | Other | 2010-03-04 | 2010-03-04 | 2010-06-08 | 2010-06-09 | 1200000 | 1.000
11561 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | KIMBLE |  | 11 | 2010484 | In order to improve the transportation system at the local level, the Texas Department of Transportation will extend the roadway on Farm-To-Market 2169. | Pavement Widening | 2010-05-03 | 2010-05-21 |  | 2011-05-31 | 2745670.6 | 0.661
11562 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | ANDERSON |  | 05 | 2010531 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 287. | Pavement Improvement | 2010-03-11 | 2010-06-14 |  | 2010-10-28 | 1541000 | 5.720
11563 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2010533 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 2493. | Pavement Improvement | 2010-03-09 | 2010-04-05 |  | 2010-06-21 | 700000 | 2.257
11564 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | VAN ZANDT |  | 05 | 2010535 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Interstate Highway 20. | Pavement Improvement | 2010-05-03 | 2010-05-03 |  | 2010-08-17 | 2253289.96 | 11.240
11565 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | YOUNG |  | 19 | 2010538 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on State Highway 16. | Pavement Improvement | 2010-03-18 | 2010-05-10 | 2010-10-01 | 2010-10-06 | 2089379.66 | 8.637
11566 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | WHARTON |  | 14 | 2010539 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 59 Business Loop S. | Pavement Improvement | 2010-04-05 | 2010-04-05 | 2010-06-22 | 2010-06-15 | 1324375 | 5.595
11567 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HAYS | AUSTIN | 21 | 2010543 | In order to improve mobility in a metropolitan area, the City of Kyle will restripe the roadway to enhance roadway safety on city street. | Safety/Traffic Management | 2010-06-07 | 2010-06-14 | 2010-06-22 | 2011-08-25 | 22017 | 1.000
11568 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MCLENNAN |  | 17 | 2010545 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway by widening from two to four lanes with a continuous left turn lan | Pavement Widening | 2010-05-07 | 2010-06-01 | 2011-01-01 | 2011-04-11 | 3293000 | 2.222
11569 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MCLENNAN |  | 17 | 2010546 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway by widening from two to four lanes with a continuous left turn lan | Pavement Widening | 2010-06-04 | 2010-06-21 | 2011-06-01 |  | 2895412.76 | 0.796
11570 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2010547 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway by widening to eight main lanes and reconstructing two lane fronta | Pavement Widening | 2010-04-15 | 2010-07-19 | 2014-03-30 |  | 51235353.1 | 2.747
11571 | Completed | C220,C240 | Highway Infrastructure Investment Grant | TEXAS | CHAMBERS |  | 14 | 2010550 | In order to enhance the community, the Texas Department of Transportation will reconstruct the roadway by constructing ramps for a new tourist and visitor center and make frontage road accommodations | Transportation Enhancements | 2010-04-27 | 2010-06-03 |  | 2011-08-25 | 2112561.86 | 1.401
11572 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2010552 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will procure right of way on Interstate Highway 45. | Other | 2010-04-15 | 2010-07-19 | 2014-03-30 |  | 1000000 | 4.015
11573 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | AUSTIN |  | 10 | 2010556 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway from a two lane to four lane road on State Highway 36. | New Bridge Construction | 2010-04-15 | 2010-06-11 |  |  | 7348419.15 | 4.929
11574 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | AUSTIN |  | 10 | 2010557 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway from a two lane to four lane road on State Highway 36. | Pavement Widening | 2010-04-15 | 2010-06-11 |  |  | 15070823.13 | 5.885
11575 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | JOHNSON | DALLAS-FORT WORTH | 17 | 2010558 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway from a two lane to four lane road on US Highway 67. | Pavement Widening | 2010-05-13 | 2010-05-21 | 2010-05-21 |  | 17260420.68 | 4.168
11576 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010559 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade safety lighting on Interstate Highway 20. | Safety/Traffic Management | 2010-05-26 | 2010-08-31 | 2010-12-31 | 2011-02-24 | 162819.65 | 1.406
11577 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | BOWIE |  | 04 | 2010569 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Farm-To-Market 1297,Farm-To-Market 2878 and US Highway 82. | Pavement Improvement | 2010-03-26 | 2010-05-13 |  | 2010-07-02 | 625744.76 | 3.247
11578 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HAYS | AUSTIN | Multiple | 2010570 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway by adding a center turn lane on Ranch-To-Market 12. | Pavement Improvement | 2010-05-04 | 2010-05-04 |  | 2011-05-10 | 998761.29 | 1.042
11579 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010571 | In order to improve mobility in a metropolitan area, the City of Austin will install signals on various highways and roads. | Safety/Traffic Management | 2010-06-21 | 2010-07-06 | 2010-10-19 |  | 600000 | 0.100
11580 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010572 | In order to improve mobility in a metropolitan area, the City of Austin will resurface the roadway on various highways and roads. | Pavement Improvement | 2010-06-21 | 2010-06-21 | 2010-08-13 | 2010-09-24 | 1313096.39 | 1.000
11581 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010573 | In order to improve mobility in a metropolitan area, Travis County will resurface the roadway on various highways and roads. | Pavement Improvement | 2010-06-07 | 2010-07-05 | 2010-08-13 | 2010-08-26 | 655813.78 | 0.100
11582 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010574 | In order to improve mobility in a metropolitan area, the City of Austin will install system signals on various highways and roads. | Safety/Traffic Management | 2010-06-21 | 2010-07-28 | 2010-10-19 |  | 637497.61 | 0.100
11583 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010575 | In order to improve mobility in a metropolitan area, the City of Austin will install system signals on various highways and roads. | Safety/Traffic Management | 2010-06-21 | 2010-06-14 | 2010-10-12 |  | 750000 | 1.000
11584 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010576 | In order to improve mobility in a metropolitan area, the City of Austin will install communication devices to enhance roadway safety on various highways and roads. | Other | 2010-02-03 | 2010-02-03 | 2011-11-01 |  | 200000 | 3.140
11585 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010577 | In order to improve mobility in a metropolitan area, the City of Austin will install communication devices to enhance roadway safety on various highways and roads. | Other | 2010-02-11 | 2010-02-11 | 2011-11-01 |  | 300000 | 0.001
11586 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 25 | 2010578 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will improve sidewalks to accommodate bicycle transportation and pedestrians on US Highway 290. | Transportation Enhancements | 2010-03-26 | 2010-04-20 |  | 2010-10-04 | 131080 | 0.100
11587 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | 15 | 2010580 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway from existing three lane to a four lane divided urban road on US Highway 83 Bus | Pavement Widening | 2010-05-11 | 2010-06-01 | 2010-11-15 |  | 4144356.19 | 1.727
11588 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010590 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade safety lighting to enhance roadway safety on Interstate Highway 20. | Safety/Traffic Management | 2010-05-26 | 2010-08-31 | 2010-12-31 | 2011-02-24 | 193328 | 0.523
11589 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JONES, TAYLOR |  | Multiple | 2010591 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade safety lighting to enhance roadway safety on US Highway 83 and US Highway 83 Business Loop | Safety/Traffic Management | 2010-05-26 | 2010-08-31 | 2010-12-31 | 2011-02-24 | 184225 | 1.057
11590 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010592 | In order to preserve the existing transportation system, the Texas Department of Transportation will place pavement markers and markings to enhance roadway safety on US Highway 83. | Safety/Traffic Management | 2010-06-15 | 2010-09-13 | 2010-10-15 | 2010-11-08 | 73778.88 | 1.006
11591 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010593 | In order to preserve the existing transportation system, the Texas Department of Transportation will place pavement markers and markings to enhance roadway safety on US Highway 83. | Safety/Traffic Management | 2010-06-15 | 2010-09-13 | 2010-10-15 | 2010-11-08 | 195360.4 | 3.200
11592 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010594 | In order to preserve the existing transportation system, the City of Abilene will upgrade traffic signals on State Highway 36. | Safety/Traffic Management | 2010-08-10 | 2010-08-06 | 2010-08-15 | 2010-09-03 | 126612.5 | 0.100
11593 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2010595 | In order to preserve the existing transportation system, the City of Abilene will resurface the roadway on city street. | Pavement Improvement | 2010-06-07 | 2010-07-12 | 2010-08-15 | 2010-08-17 | 354080.76 | 0.001
11594 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | CALLAHAN |  | 19 | 2010602 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Interstate Highway 20. | Pavement Improvement | 2010-04-08 | 2010-07-21 | 2010-10-15 | 2010-10-15 | 2118571.03 | 8.914
11595 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | CASS |  | 04 | 2010605 | In order to enhance the community, the Texas Department of Transportation will remove barriers to comply with the Americans with Disabilities Act at various locations in Cass county and the city of L | Transportation Enhancements | 2010-04-27 | 2010-07-15 |  |  | 416406.88 | 0.001
11596 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2010629 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will replace bridges, widen roadway to six main lanes, construct one northbound entrance ramp a | Pavement Widening | 2010-05-07 | 2010-05-25 | 2014-01-10 |  | 53027895 | 5.098
11597 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | VICTORIA |  | 14 | 2010652 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 87. | Pavement Improvement | 2010-04-13 | 2010-06-11 |  | 2010-07-21 | 540933.46 | 2.000
11598 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2010657 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on Interstate Highway 10. | Transportation Enhancements | 2010-09-27 | 2010-10-13 | 2012-03-01 |  | 651751 | 10.033
11599 | Underway | C220 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2010658 | In order to enhance the community, the Texas Department of Transportation will perform landscaping and other scenic beautification on Interstate Highway 10. | Transportation Enhancements | 2010-09-13 | 2010-10-04 | 2012-11-23 |  | 400000.69 | 1.293
11600 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 25 | 2010669 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will install sidewalks and pedestrian signals on US Highway 290. | Transportation Enhancements | 2010-03-26 | 2010-04-20 |  | 2010-10-04 | 39391.25 | 0.100
11601 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | GALVESTON | HOUSTON | 14 | 2010672 | In order to improve mobility in a metropolitan area, the City of Galveston will perform resurfacing on city street. | Pavement Improvement | 2010-12-06 | 2010-12-13 | 2011-03-14 | 2011-07-06 | 385396.4 | 0.002
11602 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2010673 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will perform resurfacing on city street. | Pavement Improvement | 2010-05-18 | 2010-06-07 | 2010-08-08 | 2010-09-07 | 330160.58 | 0.001
11603 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 2010674 | In order to improve mobility in a metropolitan area, the City of Houston will perform restoration and resurfacing on city street. | Pavement Improvement | 2011-02-21 | 2011-02-21 | 2011-08-18 |  | 2900406.3 | 0.001
11604 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010675 | In order to improve mobility in a metropolitan area, the City of Houston will perform restoration and resurfacing on city street. | Pavement Improvement | 2011-02-28 | 2011-02-28 | 2012-02-28 |  | 4457032.85 | 0.011
11605 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BELL |  | 31 | 2010688 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will procure right of way on Interstate Highway 35. | Other | 2010-06-10 | 2010-07-28 | 2011-01-07 |  | 2000000 | 5.637
11606 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010690 | In order to improve the transportation system, the Texas Department of Transportation will reconstruct the roadway to a four lane divided road on Ranch-To-Market 2769. | Pavement Widening | 2010-05-28 | 2010-08-31 |  |  | 3637513.4 | 0.753
11607 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 2010693 | In order to mitigate flooding and improve water quality in a metropolitan area, the Texas Department of Transportation will construct a detention pond on Metropolitan Highway. | Other | 2010-05-24 | 2010-06-09 | 2012-06-09 | 2011-07-18 | 1825628.71 | 0.001
11608 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | GREGG |  | 01 | 2010698 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on Spur 502. | Pavement Improvement | 2010-04-13 | 2010-05-24 |  | 2010-07-13 | 209734.1 | 1.084
11609 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2010699 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade highway illumination to enhance roadway safety on Interstate Highway 44. | Safety/Traffic Management | 2010-06-01 | 2010-07-19 | 2010-12-31 | 2011-02-14 | 409757.5 | 0.623
11610 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WICHITA | WICHITA FALLS | 13 | 2010700 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade highway illumination to enhance roadway safety on US Highway 287. | Safety/Traffic Management | 2010-06-01 | 2010-07-19 | 2010-12-31 | 2011-02-14 | 126752.22 | 1.400
11611 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2010701 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade highway illumination to enhance roadway safety on Interstate Highway 44. | Safety/Traffic Management | 2010-06-01 | 2010-07-19 | 2010-12-31 | 2011-02-14 | 131103.52 | 0.941
11612 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2010702 | In order to preserve the existing transportation system, the Texas Department of Transportation will upgrade highway illumination to enhance roadway safety on Spur 325. | Safety/Traffic Management | 2010-06-01 | 2010-07-19 | 2010-12-31 | 2011-02-14 | 218908.71 | 1.706
11613 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MIDLAND |  | 11 | 2010705 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Farm-To-Market 307. | Pavement Improvement | 2010-06-10 | 2011-04-11 | 2011-02-28 | 2011-08-23 | 1026131.67 | 1.020
11614 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DALLAM |  | 13 | 2010707 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on US Highway 87. | Pavement Improvement | 2010-05-17 | 2010-10-07 |  | 2011-09-26 | 1194872.29 | 6.988
11615 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | WICHITA | WICHITA FALLS | 13 | 2010708 | In order to preserve the existing transportation system, the Texas Department of Transportation will construct railroad grade crossing on frontage road at US Highway 82. | Safety/Traffic Management | 2010-06-15 | 2010-07-06 | 2010-09-30 | 2010-11-30 | 265000 | 0.065
11616 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | LIBERTY | HOUSTON | 02 | 2010709 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will perform resurfacing on city street. | Pavement Improvement | 2010-05-05 | 2010-05-05 | 2011-09-01 | 2010-06-25 | 109809.68 | 0.002
11617 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2010710 | In order to improve mobility in a metropolitan area, the City of Austin will place dynamic message signs to enhance roadway safety on various highways and roads. | Safety/Traffic Management | 2011-01-10 | 2011-01-17 | 2011-09-01 |  | 1000000 | 0.100
11618 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MIDLAND |  | 11 | 2010724 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will construct a new roadway on State Highway 349. | New Construction | 2010-05-24 | 2010-06-14 | 2010-10-08 | 2011-03-10 | 1788000 | 1.496
11619 | Completed | C200 | Highway Infrastructure Investment Grant | TEXAS | HOUSTON |  | 06 | 2010757 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruct the roadway on Loop 304. | Pavement Improvement | 2010-07-08 | 2010-08-16 |  | 2011-10-24 | 2798478.21 | 1.562
11620 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND |  | 14 | 2010844 | In order to improve the transportation system at the local level, the Texas Department of Transportation will construct a Railroad construct grade separation on US Highway 59. | Pavement Improvement | 2010-07-15 | 2010-08-05 | 2011-12-31 | 2011-11-28 | 13615501 | 1.077
11621 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | FORT BEND | HOUSTON | 22 | 2010857 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway and add shoulders on city street. | Pavement Improvement | 2010-08-17 | 2010-10-25 | 2011-06-01 | 2011-04-20 | 569871.21 | 1.732
11622 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY | HOUSTON | 08 | 2010859 | In order to improve the transportation system in a metropolitan area, Montgomery County will perform restoration and rehabilitation on city street. | Pavement Improvement | 2010-09-13 | 2010-09-13 | 2011-01-21 | 2010-12-22 | 562503.92 | 0.001
11623 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 29 | 2010860 | In order to improve transportation system in a metropolitan area, the City of Pasadena will perform resurfacing on city street. | Pavement Improvement | 2011-02-28 | 2011-03-14 | 2011-05-31 |  | 975525 | 0.001
11624 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2010861 | In order to improve mobility in a metropolitan area, the City of Houston will perform resurfacing on city street. | Pavement Improvement | 2011-03-07 | 2011-03-07 | 2011-07-07 | 2011-07-08 | 322828 | 0.001
11625 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2010862 | In order to improve mobility in a metropolitan area, the City of Houston will perform resurfacing on city street. | Pavement Improvement | 2011-03-07 | 2011-03-07 | 2011-07-07 | 2011-07-08 | 165000 | 0.001
11626 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | WEBB |  | 28 | 2010867 | In order to preserve the existing transportation system, the city of Laredo will perform reconstruction on city street. | Pavement Improvement | 2010-11-22 | 2010-11-22 | 2012-01-31 |  | 524538.2 | 0.100
11627 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | CHILDRESS |  | 13 | 2010886 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 287. | Pavement Improvement | 2010-07-08 | 2010-10-13 |  | 2011-01-13 | 2102521.22 | 11.658
11628 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY | HOUSTON | 08 | 2010929 | In order to improve mobility in a metropolitan area, Montgomery County will perform restoration and resurfacing on city street. | Pavement Improvement | 2010-09-13 | 2010-09-13 | 2011-01-21 | 2010-10-29 | 494830.38 | 0.001
11629 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BRAZORIA, FORT BEND | HOUSTON | Multiple | 2010953 | In order to add additional capacity to the transportation system, the Texas Department of Transportation will reconstruct the roadway and widen from two lanes to four lanes (divided rural section with | Pavement Widening | 2010-07-21 | 2010-08-20 | 2012-03-01 |  | 12653351.89 | 2.703
11630 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | WICHITA |  | 13 | 2011005 | In order to preserve the existing transportation system, the Texas Department of Transportation will apply pavement markings on US Highway 82 and various highways and roads. | Safety/Traffic Management | 2010-08-20 | 2010-09-13 |  |  | 159827.23 | 23.756
11631 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | RUNNELS, TOM GREEN, COLEMAN |  | 11 | 2011029 | In order to supplement the transportation system, the Texas Department of Transportation will install railroad drive-on-type rail anchors on ballasted track bed on South Orient railroad. | Pavement Improvement | 2010-10-20 | 2011-01-17 |  | 2011-09-23 | 2196123 | 0.003
11632 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | BOWIE |  | 04 | 2011106 | In order to improve the transportation system at the local level, the Texas Department of Transportation will upgrade existing traffic signals to enhance roadway safety on Farm-To-Market 1397. | Safety/Traffic Management | 2010-09-13 | 2011-01-21 |  |  | 81408.36 | 0.100
11633 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2011148 | In order to improve the transportation system, the Texas Department of Transportation will reverse existing ramp configuration on US Highway 75. | Pavement Improvement | 2010-10-04 | 2011-01-24 | 2011-04-01 |  | 1385000 | 0.750
11634 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT | DALLAS-FORT WORTH | 24 | 2011208 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will reconstruct the roadway from a four lane to a six lane divided road on State Highway 26. | Pavement Widening | 2010-09-15 | 2011-04-27 | 2012-11-01 |  | 11838846.21 | 1.482
11635 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | OCHILTREE |  | 13 | 2011209 | In order to preserve the existing transportation system, the Texas Department of Transportation will rehabilitate the roadway on US Highway 83. | Pavement Improvement | 2010-12-06 | 2011-01-25 |  |  | 4813991 | 6.535
11636 | Underway | C240,C230 | Highway Infrastructure Investment Grant | TEXAS | BEXAR | SAN ANTONIO | Multiple | 2011210 | In order to preserve the existing transportation system, the Texas Department of Transportation will reconstruction roadway on Loop 1604. | Pavement Improvement | 2010-12-06 | 2011-03-07 |  |  | 2582815.9 | 2.799
11637 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | Multiple | 2011212 | In order to improve mobility in a metropolitan area, the City of Houston will perform resurfacing on city street. | Pavement Improvement | 2011-02-10 | 2011-02-10 | 2011-03-11 | 2011-07-10 | 2526075.5 | 0.002
11638 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY | HOUSTON | 08 | 2011213 | In order to improve mobility in a metropolitan area, Montgomery County will perform restoration and resurfacing on city street. | Pavement Improvement | 2010-11-12 | 2010-11-12 | 2011-01-21 | 2011-01-27 | 985952.75 | 0.001
11639 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2011214 | In order to improve the transportation system, the Texas Department of Transportation will restore and rehabilitate the roadway on Interstate Highway 20. | Pavement Improvement | 2010-09-13 | 2010-10-12 |  |  | 946710.04 | 3.400
11640 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 10 | 2011272 | In order to improve mobility and preserve the existing transportation system in a metropolitan area, the Texas Department of Transportation will perform resurfacing on city street. | Pavement Improvement | 2010-10-28 | 2010-11-22 | 2011-02-01 |  | 308982.35 | 2.054
11641 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 07 | 2011273 | In order to improve mobility and preserve the existing transportation system in a metropolitan area, the Texas Department of Transportation will perform resurfacing on city street. | Pavement Improvement | 2010-10-28 | 2010-11-04 | 2011-03-31 |  | 712114.06 | 2.192
11642 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | LIBERTY | HOUSTON | 02 | 2011285 | In order to improve mobility and preserve the existing transportation system in a metropolitan area, the Texas Department of Transportation will perform resurfacing on city street. | Pavement Improvement | 2010-09-07 | 2010-09-22 |  |  | 59943.9 | 0.499
11643 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HAYS | AUSTIN | 21 | 2011290 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will construct left turn lane and add shoulders to enhance roadway safety on State Highway 21. | Safety/Traffic Management | 2010-09-14 | 2010-11-08 |  |  | 646709.95 | 0.322
11644 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ROBERTSON |  | 17 | 2011315 | In order to preserve the existing transportation system, the Texas Department of Transportation will perform reconstruction on Farm-To-Market 1940. | Pavement Improvement | 2010-11-30 | 2011-03-01 |  | 2011-12-21 | 1737695 | 8.798
11645 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2011340 | In order to preserve the existing transportation system, the City of Abilene will perform resurfacing on city street. | Pavement Improvement | 2010-10-05 | 2010-10-19 | 2010-11-30 | 2010-11-18 | 97623.74 | 0.002
11646 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | TAYLOR |  | 19 | 2011341 | In order to preserve the existing transportation system, the Texas Department of Transportation will construct drainage improvements on US Highway 83. | Pavement Improvement | 2010-09-21 | 2010-10-20 | 2010-12-15 |  | 206347 | 0.909
11647 | Underway | C490 | OJT/SS | TEXAS | STATEWIDE |  |  | 2011392 | The Texas Department of Transportation will provide On-the-Job training and supportive services to underrepresented or disadvantaged people pursuing careers in transportation, engineering or construct | Other | 2010-07-30 | 2010-07-30 |  |  | 213263 | 0.000
11648 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | Multiple | 2011402 | In order to improve mobility in a metropolitan area, the City of Austin will install uninterrupted power supply at 300 intersections to enhance roadway safety on various highways and roads. | Other | 2011-03-10 |  |  |  | 1433000 | 0.100
11649 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | TRAVIS | AUSTIN | 25 | 2011403 | In order to improve mobility in a metropolitan area, the City of Sunset Valley will perform resurfacing on city street. | Pavement Improvement | 2010-11-12 | 2010-11-14 | 2010-12-08 | 2010-12-20 | 250000 | 0.733
11650 | Completed | C240,C230 | Highway Infrastructure Investment Grant | TEXAS | HIDALGO | MCALLEN-PHARR-EDINBURG | Multiple | 2011421 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface the roadway on US Highway 83. | Pavement Improvement | 2010-10-20 | 2011-02-16 |  | 2011-12-28 | 722727.33 | 5.669
11651 | Completed | C230 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY | HOUSTON | 08 | 2011438 | In order to improve mobility in a metropolitan area, Montgomery County will perform restoration and resurfacing on county road. | Pavement Improvement | 2010-12-01 | 2010-12-03 | 2011-04-06 | 2011-02-28 | 509562.5 | 0.001
11652 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | POTTER | AMARILLO | 13 | 2011440 | In order to improve the transportation system, the Texas Department of Transportation will construct a new four lane arterial street. | New Construction | 2010-11-05 | 2010-11-15 |  |  | 504155.38 | 0.430
11653 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | COOKE |  | Multiple | 2011441 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate frontage roads, construct a ramp, construct/convert frontage roads and ins | Pavement Improvement | 2010-11-04 | 2011-02-14 |  |  | 12296908.32 | 5.386
11654 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | WILLIAMSON, TRAVIS | AUSTIN | Multiple | 2011450 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will restore and rehabilitate the roadway by making intersection improvements on Farm-To-Market 734. | Pavement Improvement | 2010-11-02 | 2010-12-03 |  |  | 656065 | 5.249
11655 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MCLENNAN | WACO | 17 | 2011454 | In order to preserve the existing transportation system, the Texas Department of Transportation will repair and resurface roadway on Loop 340. | Pavement Improvement | 2010-11-16 | 2011-04-26 |  | 2011-09-19 | 1028394.24 | 1.666
11656 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | COOKE | WICHITA FALLS | 13 | 2011455 | In order to improve the existing transportation system, the Texas Department of Transportation will acquire right-of-way and relocate utilities on Interstate Highway 35. | Other | 2010-11-04 | 2011-02-14 |  |  | 883052 | 3.137
11657 | Underway | C200 | Highway Infrastructure Investment Grant | TEXAS | COOKE |  | 26 | 2011456 | In order to supplement the transportation system, the Texas Department of Transportation will perform landscaping and other scenic beautification on Interstate Highway 35. | Transportation Enhancements | 2010-11-04 | 2011-02-14 |  |  | 100000 | 2.049
11658 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | DENTON, ROCKWALL, COLLIN | DALLAS-FORT WORTH | Multiple | 2011462 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Farm-To-Market 1515,Farm-To-Market 3286,Farm-To-Market 3364,Inter State 35 Bu | Pavement Improvement | 2010-11-10 | 2011-03-15 |  | 2011-10-24 | 646238 | 18.330
11659 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | KAUFMAN, ELLIS | DALLAS-FORT WORTH | Multiple | 2011466 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Farm-To-Market 1836,Farm-To-Market 2515,Farm-To-Market 416,Farm-To-Market 55,F | Pavement Improvement | 2010-11-10 | 2011-02-15 |  | 2011-10-25 | 1737397 | 44.867
11660 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | DALLAS |  | Multiple | 2011467 | In order to preserve the existing transportation system, the Texas Department of Transportation will construct features or devices to enhance roadway safety on various highways and roads. | Safety/Traffic Management | 2010-11-16 | 2011-03-14 |  |  | 1049797.5 | 0.001
11661 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | KAUFMAN |  | 05 | 2011470 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate roadway on Farm-To-Market 1641. | Pavement Improvement | 2010-12-01 | 2011-02-14 |  |  | 2815482 | 5.239
11662 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | ERATH, WISE, TARRANT |  | Multiple | 2011471 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on State Highway 10,State Highway 199,US Highway 287,US Highway 287 Business Loop | Pavement Improvement | 2010-11-16 | 2011-05-31 |  | 2011-09-29 | 1658249 | 37.368
11663 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | TARRANT |  | 06 | 2011473 | In order to preserve the existing transportation system, the Texas Department of Transportation will construct features or devices to enhance roadway safety on Farm-To-Market 1187. | Safety/Traffic Management | 2010-11-16 | 2011-02-14 |  | 2011-06-22 | 82335 | 0.100
11664 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | GRAYSON |  | 04 | 2011478 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Farm-To-Market 100,Farm-To-Market 120,Farm-To-Market 1417,Farm-To-Market 1487, | Pavement Improvement | 2010-11-10 | 2011-06-20 |  |  | 6306284 | 236.368
11665 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN AUGUSTINE |  | 01 | 2011526 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Farm-To-Market 1,Farm-To-Market 1194,Farm-To-Market 1271,Farm-To-Market 1475,F | Pavement Improvement | 2010-11-10 | 2011-03-15 |  |  | 6072773 | 255.421
11666 | Underway | C230 | Highway Infrastructure Investment Grant | TEXAS | HARRIS | HOUSTON | 02 | 2011543 | In order to improve mobility in a metropolitan area, the Texas Department of Transportation will perform utility adjustments on Farm-To-Market 2100. | Other | 2010-09-01 | 2011-11-28 | 2012-06-17 |  | 335846 | 0.870
11667 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | CORYELL |  | 31 | 2011593 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Farm-To-Market 116,Farm-To-Market 1373,Farm-To-Market 2114,Farm-To-Market 2310 | Pavement Improvement | 2010-11-12 | 2011-04-18 |  |  | 9088883 | 334.257
11668 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | JEFFERSON |  | 02 | 2011621 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on State Highway 124. | Pavement Improvement | 2010-11-12 | 2011-03-07 |  | 2011-09-20 | 1426706 | 6.381
11669 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | SAN PATRICIO |  | 27 | 2011622 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on US Highway 181. | Pavement Improvement | 2010-11-16 | 2011-04-11 |  | 2011-06-16 | 675000 | 0.637
11670 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | MITCHELL |  | 11 | 2011623 | In order to preserve the existing transportation system, the Texas Department of Transportation will restore and rehabilitate roadway on Interstate Highway 20. | Pavement Improvement | 2010-11-10 | 2011-04-19 |  |  | 6170510 | 18.838
11671 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | FREESTONE |  | 06 | 2011624 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Interstate Highway 45. | Pavement Improvement | 2010-11-16 | 2011-03-01 |  | 2011-09-20 | 2201174 | 7.481
11672 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2011626 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Farm-To-Market 1097. | Pavement Improvement | 2010-11-10 | 2011-03-16 | 2011-06-30 | 2011-06-06 | 449995 | 6.257
11673 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | MONTGOMERY |  | 08 | 2011627 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on various highways and roads. | Pavement Improvement | 2010-11-04 | 2011-03-07 | 2011-05-30 | 2011-05-05 | 187313 | 0.001
11674 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | HOPKINS, HUNT |  | 04 | 2011628 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on State Highway 11,State Highway 154 and US Highway 67 Business Loop V. | Pavement Improvement | 2010-11-10 | 2011-07-14 |  | 2012-01-06 | 1722122 | 8.846
11675 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | CAMERON |  | Multiple | 2011629 | In order to preserve the existing transportation system, the Texas Department of Transportation will construct a facility to accommodate bicycle transportation and pedestrians on various highways and | Transportation Enhancements | 2010-11-17 | 2011-01-04 |  | 2011-11-08 | 122615 | 0.001
11676 | Completed | C200,C240 | Highway Infrastructure Investment Grant | TEXAS | SMITH |  | 01 | 2011630 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Loop 323. | Pavement Improvement | 2010-11-10 | 2011-05-23 |  | 2011-10-18 | 843750 | 2.384
11677 | Completed | C240 | Highway Infrastructure Investment Grant | TEXAS | AUSTIN |  |  | 2011631 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Interstate Highway 10. | Pavement Improvement | 2010-11-16 | 2011-06-28 |  | 2011-11-30 | 5048454.4 | 16.077
11678 | Underway | C240 | Highway Infrastructure Investment Grant | TEXAS | FANNIN |  | 04 | 2011632 | In order to preserve the existing transportation system, the Texas Department of Transportation will resurface roadway on Loop 205 and State Highway 78. | Pavement Improvement | 2010-11-10 | 2011-05-16 |  |  | 375515 | 1.967
11679 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | DUCHESNE |  | 03 | 0040051 | This project widens US 40 to three lanes from West Roosevelt to Ioka Junction | Pavement Widening | 2009-03-12 | 2009-03-12 | 2009-12-17 | 2010-06-24 | 3213416.34 | 2.000
11680 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 03 | 0068049 | This project will reconstruct the intersection of 6200 South and Redwood Road to add capacity and improve traffic operations | Other | 2009-03-02 | 2009-03-02 | 2011-07-31 |  | 12418247.68 | 0.100
11681 | Underway | C240,C230 | Highway Infrastructure Investment Grant | UTAH | DAVIS | OGDEN | 01 | 0108024 | This project reconstructs and widens Syracuse Road (SR 108) from 1000 West to 2000 West in Syracuse | Pavement Widening | 2009-03-11 | 2009-03-12 | 2011-01-04 |  | 15499849.11 | 1.000
11682 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | 0209013 | This project improves intersection operations at 9000 South and 450 West by adding turn lanes and other improvments | Pavement Improvement | 2009-03-02 | 2009-03-02 |  |  | 492141.21 | 0.000
11683 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SAN JUAN |  | 03 | 0491005 | This project reconstructs the pavement on SR-491 from milepost 0 to Milepost 1.5 in Monticello, Utah | Pavement Improvement | 2009-03-03 | 2009-03-03 |  | 2011-01-25 | 3842713.93 | 1.500
11684 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 03 | 0846088 | This project rehabilitates the pavement on I-84 form the Morgan County Line to Henefer by removing some of the existing pavement and adding a structural overlay. | Pavement Improvement | 2009-03-04 | 2009-03-04 |  | 2010-10-14 | 530336.55 | 3.000
11685 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | 2172004 | This project adds safety improvements and reconstructs 3900 South from Highland Drive to 2300 East | Pavement Improvement | 2009-03-02 | 2008-04-11 | 2010-07-13 |  | 4892637.93 | 4.000
11686 | Completed | C200,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | 2896002 | This project reconstructs 50 South in American fork from 700 East to 1100 East | New Construction | 2009-03-03 | 2009-03-03 | 2010-02-26 | 2011-01-05 | 2110631.89 | 4.000
11687 | Completed | C200 | Highway Infrastructure Investment Grant | UTAH | CACHE |  | 01 | F002726 | This project constructs a new three lane roadway from 800 South to 300 South along new and existing alignments in Logan | New Construction | 2009-03-03 | 2009-03-03 | 2010-09-30 | 2011-06-21 | 2860580 | 5.000
11688 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F003664 | This project reconstructs the pavement and adds pedestrian ramps on Wall Avenue (SR-204) From 23rd Street to US-89 in Ogden | Pavement Improvement | 2009-03-03 | 2009-03-03 | 2009-10-30 | 2010-01-27 | 5477736.55 | 1.000
11689 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 01 | F004135 | This project rehabilitated the pavement on I-80 from Echo Junction to Emory by removal some of the existing asphalt and adding a structural overlay. | Pavement Improvement | 2009-03-16 | 2009-03-16 |  |  | 14014488 | 12.000
11690 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F004474 | This project constructs a new Bike and Pedestrian Trail in Hooper, Utah | Transportation Enhancements | 2009-03-16 | 2009-03-16 | 2011-01-04 |  | 407719.47
11691 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F004592 | Install Median and Shoulder Barrier | Safety/Traffic Management | 2010-05-06 | 2010-05-06 |  | 2011-05-05 | 711066.4
11692 | Completed | C240,C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F004615 | This project adds auxillary lanes on I-15 from 10000 South to 7200 South. These lanes will improve traffic operations and capacity. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2009-12-02 | 2011-03-08 | 11077243.1 | 2.000
11693 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WASATCH |  | 02 | F004648 | This project will add passing lanes on US-189 from Heber to Provo Canyon. | Pavement Widening | 2009-07-01 | 2009-07-01 |  |  | 8400353.12 | 3.000
11694 | Completed | C240,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F004654 | This project reahbilitates the pavement on US-189 from University Parkway to Provo Canyon and improves and widens intersections. | Pavement Improvement | 2009-03-03 | 2009-03-03 |  | 2010-06-07 | 3030975.01 | 0.500
11695 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F004680 | This project adds an asphalt overlay on SR-92 from SR-74 to SR-146. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-10-18 | 1422955.91 | 1.800
11696 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | EMERY |  | 02 | F004690 | This project constructs a climbing lane/turn lanes, as well as rest area construction. | Pavement Widening | 2010-01-04 | 2010-03-01 | 2011-01-04 |  | 3956624.66
11697 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 03 | F004864 | This project rehabilitates the concrete pavement on I-215 from 4700 South to SR-201, repairing potholes and grinding to improve rideability. | Pavement Improvement | 2009-03-17 | 2009-03-17 | 2010-03-31 | 2010-05-05 | 3844928.9 | 3.000
11698 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 03 | F004890 | This project rehabilitates the asphalt pavement on SR-111 (8400 West) from 3500 South to SR-201 in Salt Lake county by removing some of the existing asphalt and adding a structural overlay | Pavement Improvement | 2009-03-10 | 2009-03-10 | 2009-10-01 |  | 931153.47 | 1.900
11699 | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F005122 | This project replaces 3 bridge decks on I-15 in the Payson, Utah area. | Bridge Improvement | 2009-03-03 | 2009-03-03 |  | 2010-08-18 | 5850000 | 1.000
11700 | Underway | C250,C200 | Highway Infrastructure Investment Grant | UTAH | CARBON |  | 03 | F005269 | This project reconstructs the pavement on Carbonville Road near Price, Utah | Pavement Improvement | 2009-03-03 | 2009-03-03 | 2010-06-30 |  | 2101040.31
11701 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | EMERY |  | 02 | F005336 | Install Passing Lanes | Pavement Widening | 2010-08-17 | 2010-08-17 |  |  | 3900000
11702 | Completed | C250,C200 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 03 | F005667 | This project reconstructs Coalville Main Street and SR-280 in Coalville, Utah | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2010-03-31 | 2011-08-11 | 1211276.5
11703 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 03 | F005671 | This project replaces two bridges on I-80 over Echo Frontage Road near Echo Junction. | Bridge Replacement | 2009-03-02 | 2009-03-02 | 2011-01-04 |  | 3475000 | 1.000
11704 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F005693 | This project provides intersection improvements along 6200 South from 3000 East to I-215. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2011-01-04 |  | 1583371.65
11705 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER | OGDEN | 01 | F005706 | This project applied a chip seal to various locations on US-89 to improve skid resistance and extend pavement life. It also retrofitted existing and installed new pedestrian ramps. | Pavement Improvement | 2009-03-31 | 2009-03-31 |  | 2010-01-27 | 1027336.25
11706 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | CACHE |  | 01 | F005788 | This project applied a chip seal on SR-101 from SR-23 to SR-165 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2009-05-08 | 2009-12-29 | 1958745.61 | 5.900
11707 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F005828 | This project applied a thin bonded overlay to the pavement on I-15 from the Benjamin interchange to Spanish Fork. This improves skid resistance and extends pavement life. | Pavement Improvement | 2009-03-31 | 2009-03-31 |  | 2010-04-06 | 1522351.89 | 3.950
11708 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 01 | F005952 | This project rehabilitates the asphalt pavement on SR-269 and SR-270 at various locations. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-05-10 | 1741040.91
11709 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F005957 | This project rehabilitates the concrete pavement on I-215 from Milepost 5.709 to Milepost 7.585, repairing potholes and grinding to improve rideability. | Pavement Improvement | 2009-03-31 | 2009-03-31 |  | 2009-09-02 | 978427.59 | 1.876
11710 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F005965 | This project is bridge scour repair in various locations of Region 3. | Bridge Improvement | 2009-11-04 | 2009-11-04 |  | 2010-10-21 | 196029.75
11711 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | F005966 | This project is bridge scour repair for 7 bridges in Region 4. | Bridge Improvement | 2009-11-04 | 2009-11-04 |  | 2011-07-11 | 352000
11712 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SAN JUAN |  | 03 | F005983 | This project applied a chip seal on US-191 from Milepost 73 to Milepost 86 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-03-31 | 2009-03-31 |  | 2010-05-10 | 719524.05 | 13.000
11713 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F005993 | This project entails the deployment of varriable message signs throughout the Salt Lake Valley | Safety/Traffic Management | 2009-04-01 | 2009-04-01 |  | 2010-10-28 | 432597.67
11714 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | F005994 | This project applied a chip seal on US-89 from Milepost 227.6 to 267.2 and on SR-132 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-03-11 | 937474.02
11715 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SEVIER |  | 03 | F005996 | This project applied a lane leveling asphalt overlay on SR-118 from Milepost 6.9 to 10.0. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-08-04 | 819895.07 | 3.100
11716 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006024 | This project applied a polymer overaly on six bridges, extending the life of the bridge decks. | Bridge Improvement | 2009-04-01 | 2009-04-01 |  | 2010-05-06 | 227937.34
11717 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F006065 | This project applied a 1 1/2 inch overlay on SR-36 from the Junction of SR 73 to Three O'Clock drive in Tooele, Utah to improve ride, skid resistance and extend the life of the pavement. | Pavement Improvement | 2009-08-17 | 2009-08-17 |  | 2010-10-07 | 1537912.87 | 9.890
11718 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | MILLARD |  | 03 | F006071 | This project applied a asphalt wearing surface on I-15 from Milepost 158.5 to 169 to improve skid resistance and extend the pavement life. | Pavement Improvement | 2009-03-09 | 2009-03-09 | 2010-03-31 | 2010-01-27 | 4956974.61 | 10.500
11719 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SEVIER |  | 03 | F006072 | This project rehabilitated the concrete pavement on I-70 from Mile post 6.8 to 17.7. This rehabilitation included slab replacment and joint sealing. | Pavement Improvement | 2009-03-10 | 2009-03-10 |  | 2010-10-07 | 1153338.43 | 10.900
11720 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | F006073 | This project applied an asphalt wearing surface on SR-9 form Mile post 0 to 4.9 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-03-03 | 2009-03-03 |  | 2010-10-28 | 2130095.6 | 4.900
11721 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | F006074 | This project constructs a new bridge over the Santa Clara River in St. George, Utah. | Bridge Replacement | 2009-03-09 | 2009-03-09 | 2011-01-04 |  | 3570000
11722 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006076 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 1(Northern Utah). | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-04-12 | 176602.3
11723 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006077 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 1 (Northern Utah). | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-05-06 | 152460.65
11724 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006080 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 2 (Salt Lake Area). | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2011-05-05 | 361143.71
11725 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006082 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in Region 3 (Central Utah). | Transportation Enhancements | 2009-04-01 | 2009-04-01 | 2009-12-31 | 2010-03-18 | 410167.78
11726 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006084 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Cedar City District of Region 4. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-07-26 | 98469.89
11727 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006085 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Price District of Region 4. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-07-21 | 133996.05
11728 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006086 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Richfield District of Region 4. | Transportation Enhancements | 2009-04-01 | 2009-04-01 | 2011-03-31 | 2010-07-21 | 122552.13
11729 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006088 | This project constructed safe sidewalks and installed pedestrian ramps in various locatons on SR-171. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2011-02-17 | 142702
11730 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F006089 | This project constructed safe sidewalks and installed pedestrian ramps on US-89; 400 South to 4400 South in Ogden, Utah. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-03-18 | 131840
11731 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006090 | This project constructed safe sidewalks and installed pedestrian ramps on SR-107; 4000 West to 4050 West in West Point, Utah. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-03-11 | 53176.42 | 0.050
11732 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006091 | This project constructed safe sidewalks and installed pedestrian ramps on SR-37; 3500 West to 3550 West, in Clinton, Utah. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-11-10 | 145000
11733 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006092 | This project constructed safe sidewalks and installed pedestrian ramps on SR-266; Redwood Road to 550 West in Taylorsville, Utah. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2011-06-07 | 321287
11734 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | DUCHESNE |  | 02 | F006093 | This project constructed safe sidewalks and installed pedestrian ramps on SR-87; 800 NOrth to 1400 North in Duchesne, Utah. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-03-01 | 181550.79
11735 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006095 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Cedar City District of Region 4. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-05-06 | 46710.32
11736 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006096 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Price District of Region 4. | Other | 2009-04-01 | 2009-04-01 |  | 2010-07-21 | 92331.19
11737 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F006097 | This project constructed safe sidewalks and installed pedestrian ramps in various locations in the Richfield District of Region 4. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-08-04 | 98341.26
11738 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006099 | This project constructed safe sidewalks and installed pedestrian ramps in variouslocations on SR-48. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-06-01 | 94466
11739 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER | LOGAN | 01 | F006109 | This project provided fiber optic connections on US-89 from I-84 to Harrison Blvd to improve traffic signal operations. | Safety/Traffic Management | 2009-03-09 | 2009-03-09 |  | 2010-11-10 | 188058.32
11740 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006110 | This project provided traffic signal interconnection on SR-190 & SR-210; Wasatch Boulevard from I-215 to Cottonwood Canyon to improve traffic operations. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 | 2010-06-22 | 2011-03-02 | 918622.15 | 1.000
11741 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | SUMMIT |  | 01 | F006118 | This project constructs wildlife fence along I-80 in Parley's Canyon to enhance safety for both drivers and wildlife. | Other | 2009-04-01 | 2009-04-01 |  | 2011-03-23 | 407092.66 | 1.000
11742 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | GARFIELD |  | 02 | F006119 | This project extends the bike path along SR-12 in Garfield County | Transportation Enhancements | 2009-04-01 | 2009-04-01 | 2010-01-25 | 2010-10-14 | 434572.33 | 1.000
11743 | Completed | C200,C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F006120 | This project constructed a new roadway along 1000 North from SR-112 to 600 West in Tooele, Utah. | New Construction | 2009-03-17 | 2009-04-01 | 2011-01-04 | 2011-08-31 | 3500000
11744 | Underway | C220,C240,C230 | Highway Infrastructure Investment Grant | UTAH | DAVIS | OGDEN | 01 | F006121 | This project will reconstruct 500 South into a five-lane roadway with two lanes in each direction and a center turning lane. Additional improvements include 12-foot shoulders to accommodate on street | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  |  | 6257007.62 | 1.000
11745 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006123 | This project on US-89 widens the shoulders to accomodate bicycles and pedestrians. | Transportation Enhancements | 2009-04-01 | 2009-04-01 |  | 2010-06-03 | 176357.09 | 0.500
11746 | Completed | C200,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006146 | This project Expands and installs computer hardware and software to update the emergency data intregration in Region 3. Enancing the commuter link system and providing better traffic operations. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 |  | 2011-01-05 | 605874.99
11747 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | DAVIS | OGDEN | 01 | F006147 | This project provides signal detection upgrades in Weber and Davis Counties | Other | 2009-04-01 | 2009-04-01 |  | 2011-03-31 | 524999.57
11748 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | WEBER | OGDEN | 01 | F006148 | This project installs conduit to on I-15 from Layton to Riverdale Road to enhance the commuter link program, improving traffic operations. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 |  | 2011-01-27 | 579225.29 | 7.459
11749 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006149 | This project expands the Advanced Traffic Management System (ATMS) through improvements to the signal interconnection in the Salt Lake County Area. | Safety/Traffic Management | 2009-03-16 | 2009-03-16 | 2011-01-04 | 2011-02-03 | 925074.98
11750 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006150 | This project expands the Variable Message Signs in the downtown Salt Lake Area, enhancing traffic operations. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 |  | 2010-01-27 | 346997.7
11751 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006151 | This project provdes upgrades to the traffic operations systems (signals Variable Message Signs etc.) along Bangerter Highway from 90th South to SR-201. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 |  | 2010-10-07 | 177636.63 | 9.623
11752 | Completed | C250,C200 | Highway Infrastructure Investment Grant | UTAH | EMERY |  | 02 | F006152 | This project reconstructs the Goblin Valley (Temple Mountain Road in Emery County, Utah | Pavement Widening | 2009-03-26 | 2009-03-26 | 2011-01-04 | 2011-01-05 | 1674106.14
11753 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 02 | F006161 | This project constructed safe sidewalks and installed pedestrian rampson SR-198 at various locations in Payson and Santaquin, Utah. | Transportation Enhancements | 2009-03-25 | 2009-03-25 |  | 2010-02-18 | 183663.63
11754 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | F006188 | This project made intersection imporvements at 9000 South and 700 East in Sandy, Utah. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2011-02-10 | 848161.11 | 0.000
11755 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UINTAH |  | 02 | F006191 | This project made improvements to the signalized intersection on US-40 at 1000 South and 500 East in Vernal, Utah | Other | 2009-04-01 | 2009-04-01 | 2009-12-31 |  | 220000 | 1.000
11756 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006241 | This project made repairs to the SR-189 bridge at 600 South University AVenue. | Bridge Improvement | 2009-04-01 | 2009-04-01 |  |  | 2500000 | 1.000
11757 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | DUCHESNE |  | 02 | F006242 | This project repainted the structural steel on the US-40 Bridge over Starvation Reservoir. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-02-18 | 1161940.24 | 1.000
11758 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006243 | This project entails applying a chip seal to the existing SR-109 roadway surface between Fairfield Road (MP 1.07) and US-89 (MP 2.962) in Layton City, UT. After applying the chip seal, traffic contro | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2009-05-20 | 2010-02-18 | 483177.99 | 24.000
11759 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006244 | This project applied microsurfacing to SR-273 From US-89 To 200 South in Kaysville to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2009-05-20 | 2010-02-18 | 606262.9 | 1.400
11760 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006245 | This project applied an asphalt seal coat to SR-190 from 3000 East to the sR-210 in Salt Lake County to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-05-20 | 485074.58 | 1.550
11761 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 03 | F006246 | This project applied a 1 1/2 inch overaly on SR-173 from 3200 West to 1900 West in Salt Lake County | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-04-14 | 667642.96 | 1.280
11762 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 03 | F006247 | This project applied a 1 1/2 inch overaly on SR-173 from 5600 West to 4800 West in Salt Lake County | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-04-06 | 463990.38 | 0.980
11763 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | CARBON |  | 02 | F006248 | This project provided surface treatements on SR-10 and SR-55 in Carbon County to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-06-02 | 2370670.29
11764 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | DAVIS |  | 01 | F006250 | This project made safety improvements to I-215 from Redwood Road to I-15. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 | 2009-06-01 | 2010-02-18 | 134451.59 | 1.900
11765 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | F006253 | This project applied a slurry seal to US-89; Ephraim, Manti, Panguitch Main Streets and Snow College roads to improve skid resistance and exxtend pavement life | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-04-06 | 487364.55 | 1.200
11766 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | IRON |  | 02 | F006254 | This project applied a wearing course on SR-130 in Iron County from milepost 0 to 5 to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-06-02 | 1052197.26 | 5.000
11767 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006307 | This project applied a polymer overlay on US-89; State Street from 90th South to 106th South and on SR-71; 700 East. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-11-22 | 223774.24
11768 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006308 | This project installed median cable barrier on SR-154 north of SR-201 in Salt Lake County. | Safety/Traffic Management | 2009-04-01 | 2009-04-01 |  | 2010-10-14 | 400000 | 1.000
11769 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | F006309 | This project rehabilitated the asphalt pavement on SR-186; Foothill Boulevard from Sunnyside AVenue to 1300 East in Salt Lake City. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-10-28 | 1809432.01 | 1.000
11770 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006315 | This project applied a wearing surface on SR-114 from SR-89 in Provo to SR-89 In Pleasant grove to improve skid resistance and extend pavement life. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-03-11 | 1758829.39
11771 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F006316 | This project Removes existing asphalt to a depth of approximately 7 inches, and replaces with 7 inches on SR-204 from SR-26 to 32nd street . Once all paving is complete, the manholes will be raised. | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-01-27 | 1135110.35 | 0.924
11772 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | IRON |  | 02 | F006338 | This project rehabilitates the asphalt pavement on SR-143 in Iron County from Milepost 2 to 2.4 and on SR-274 from Milepost 0.57 to 1.3 by removing some of the existing asphalt and adding a structural | Pavement Improvement | 2009-04-01 | 2009-04-01 |  | 2010-10-14 | 202116.52
11773 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WEBER |  | 01 | F006359 | This is a structures bridge rehabilitation project that includes pothole patching, membrane & overlay for I-15 near clearfield, bridges F-63, F-66, F-80. | Pavement Widening | 2009-09-24 | 2009-09-24 |  | 2011-01-24 | 1556141.98 | 4.000
11774 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | F006383 | This is a chip seal project for SR-228; Leed's Main Street; MP 0 TO 1.821. | Pavement Improvement | 2009-09-24 | 2009-09-24 |  | 2011-01-05 | 117239.48 | 1.821
11775 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006400 | ARRA Funded Project Administration - Mountainland Association of Governments MPO. | Other | 2009-07-20 | 2009-07-20 | 2010-12-08 | 2010-12-16 | 52578
11776 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | F006412 | This project is prevenative maintenance chip seal on US-89; FAIRVIEW TO COUNTY LINE, MP 284 TO 297 | Pavement Improvement | 2009-09-24 | 2009-09-24 |  | 2011-02-10 | 652651.47 | 12.909
11777 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006425 | Rotomill and Bonded Wearing Coarse Overlay (Surfacing and/or Resurfacing). | Pavement Improvement | 2010-09-20 | 2010-09-20 |  | 2011-01-26 | 208278.45
11778 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006426 | This project is a pavement preservation chip seal for SR-164; MP 0 TO 2.67 & SR-147; MP 15 TO 17. | Pavement Improvement | 2009-09-24 | 2009-09-24 |  | 2011-03-16 | 419226.91
11779 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006429 | This project is a pavement preservation chip seal for US-89; Boys Ranch to Birdseye. | Pavement Improvement | 2009-09-24 | 2009-09-24 |  | 2010-09-21 | 258136.19 | 5.200
11780 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | RICH |  | 01 | F006477 | This project is for the scope and design of the US-89; Swan Creek Box Culvert | Safety/Traffic Management | 2010-01-05 | 2010-01-05 |  | 2010-10-07 | 343274.32
11781 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006481 | This project is a safe sidewalk installation on SR-198 & SR-115 PAYSON; in Various Locations. | Transportation Enhancements | 2009-08-20 | 2009-08-20 |  | 2010-09-20 | 300717.95
11782 | Underway | C490 | OJT/SS | UTAH | STATEWIDE |  |  | F006530 | This project is an ARRA statewide contract for on the job training/supportative service program. | Other | 2009-09-21 | 2009-09-21 |  |  | 373890
11783 | Completed | C220 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | F006661 | Install sidewalks and pedestrian features at the Manila Elementry in Pleasant Grove. | Transportation Enhancements | 2010-01-19 | 2010-01-19 |  | 2011-05-25 | 119284.84
11784 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | DAVIS | OGDEN | 01 | F006667 | This project is part of the Region 1 Commuterlink Program and will connect the Layton City signal system in Weber County with the Traffic Operations Center in Salt Lake County. | Safety/Traffic Management | 2009-11-04 | 2009-11-04 |  | 2011-09-16 | 318184.79
11785 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | WEBER | OGDEN | 01 | F006668 | This project is part of the Region 1 Commuterlink Program and will connect 8 signals on US-89 in Weber County to the Traffic Operations Center in Salt Lake County. | Other | 2009-12-22 | 2009-12-22 |  |  | 52002.41
11786 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F006686 | This project is to do surfacing and/or Resurfacing in Various Locations on Grantsville and Wendover Main Streets | Pavement Improvement | 2010-01-11 | 2010-01-11 |  | 2011-10-06 | 1800026.71
11787 | Completed | C240,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006688 | This project rehabilitates the pavement on US-89 from 100 North to 800 North in Utah County, Region 3. | Pavement Improvement | 2010-01-07 | 2010-01-07 |  | 2011-05-04 | 862505.87
11788 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SEVIER |  | 03 | F006689 | This project is a chip seal on SR-118 from MP 6.893 to 10.042 in Region 4, Sevier County. | Pavement Improvement | 2010-01-07 | 2010-01-07 |  | 2010-12-13 | 140000 | 3.149
11789 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | F006690 | This project is a chip seal on SR-132 from Fountain Green to Moroni in Region 4, Sanpete County. | Pavement Improvement | 2010-01-07 | 2010-01-07 |  | 2011-03-31 | 574200.34 | 10.000
11790 | Underway | C240,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | F006731 | This project will be to do prevenative maintenene, with bituminous pavement, plant mix seal, on SR-265 & SR-52 in various locations. | Pavement Improvement | 2010-06-10 | 2010-06-10 |  |  | 1431825.31
11791 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | JUAB |  | 03 | F006737 | Rotomill and Bonded Wearing Course (Surfacing and/or Resurfacing). | Pavement Improvement | 2010-09-22 | 2010-09-22 |  |  | 293000
11792 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | TOOELE |  | 01 | F006764 | Microsurfacing ~ Pavement Preservation. | Pavement Improvement | 2010-08-10 | 2010-08-10 |  |  | 1600000
11793 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F007033 | Statewide Safe Sidewalk and ADA Installation Program. Construction of pedestrian ramps in various locations within Region 3. | Transportation Enhancements | 2010-06-16 | 2010-06-16 |  |  | 344353.15
11794 | Underway | C220 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F007034 | Statewide Safe Sidewalk and ADA Installation Program. Construction of pedestrian ramps in various locations within Region 4. | Transportation Enhancements | 2010-06-16 | 2010-06-16 |  |  | 779640
11795 | Underway | C240 | Highway Infrastructure Investment Grant | UTAH | STATEWIDE |  |  | F007104 | Administrative - 1512 ARRA Report Generation and Quality Control. | Other | 2010-08-03 | 2010-08-18 |  |  | 25000
11796 | Underway | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 01 | F007106 | Pavement Evaluation - Project Surfacing and/or Resurfacing | Pavement Improvement | 2010-09-23 | 2010-09-23 |  |  | 431252.73
11797 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | I156172 | This project applies a micro surface seal to the pavement on I-15 from SR-75 to the Provo River, improving and extending the pavement life. | Pavement Improvement | 2009-03-03 | 2009-03-03 |  | 2010-03-11 | 3418222.91 | 5.000
11798 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | UTAH |  | 03 | I156173 | This project rehabilitates the pavement on I-15 from 800 South, Payson to the Juab County Line by removal of some of the existing asphalt pavement and adding a structural overlay. | Pavement Improvement | 2009-03-03 | 2009-03-03 |  | 2010-01-26 | 1883718.01 | 9.300
11799 | Completed | C240 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE |  | 02 | I803148 | This project replaces the I-80 bridges over 2300 East | Bridge Replacement | 2009-03-02 | 2009-03-02 |  | 2010-06-14 | 5716949 | 1.000
11800 | Completed | C230 | Highway Infrastructure Investment Grant | UTAH | SALT LAKE | SALT LAKE CITY | 02 | I803149 | This project widens the ramps from I-80 East bound to I-215 from a single off ramp to a dual off ramp, improving operations and capacity. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2009-12-04 | 2011-12-16 | 1306273.69 | 0.099
11801 | Completed | C250,C200 | Highway Infrastructure Investment Grant | UTAH | SANPETE |  | 03 | LC39009 | This project reconstructs the Pigeon Hollow Road from Pigeon Hollow to Spring City | Pavement Improvement | 2009-03-26 | 2009-03-26 |  | 2010-11-18 | 2144679.76
11802 | Completed | C200,C230 | Highway Infrastructure Investment Grant | UTAH | UTAH | PROVO-OREM | 03 | LC49089 | This project constructs a new trail along the historic Utah South Rail line via the UPRR North Lehi line | Pavement Improvement | 2009-03-12 | 2009-04-01 | 2011-01-04 | 2011-03-10 | 2242599.69
11803 | Completed | C200 | Highway Infrastructure Investment Grant | UTAH | WASATCH |  | 03 | LC51008 | This project reconstructs Center Street in Heber City from Main Street to 1400 East | Pavement Improvement | 2009-03-03 | 2009-03-03 | 2011-01-04 | 2011-03-31 | 1290303.2 | 1.000
11804 | Completed | C200 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 01 | LC53022 | This project reconstructs the roadway from 600 North to SR-9 in Hurricane | Pavement Improvement | 2009-03-03 | 2009-03-03 | 2009-08-06 | 2011-03-23 | 1290303.2
11805 | Underway | C200 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 02 | LC53034 | This project reconstructs and widens Washington Fields Road, including the Virgin River Bridge from Indian Springs Drive to Telegraph Road in Washington. | Pavement Widening | 2009-03-03 | 2009-03-03 |  |  | 1035000
11806 | Completed | C200,C240 | Highway Infrastructure Investment Grant | UTAH | WASHINGTON |  | 01 | LC53042 | This project realigns Hilton Drive and Black Ridge Drive to improve traffic operations | Pavement Improvement | 2009-03-03 | 2009-03-03 | 2010-08-02 | 2010-08-05 | 2069768.89
11807 | Completed | C230 | Highway Infrastructure Investment Grant | VERMONT | WINDHAM |  |  | 0114005 | This project is for the repair of a bridge on Town Highway 1, approximately 1 mile west of the junction with State Route 100, in Wardsboro. | Bridge Improvement | 2010-03-11 | 2010-03-11 | 2010-10-01 | 2010-10-01 | 509634.18 | 0.020
11808 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 0136001 | Repaving the roadway | Pavement Widening | 2009-04-02 | 2009-04-02 | 2009-10-16 | 2009-10-16 | 2257081.38 | 4.400
11809 | Underway | C240 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 0193495 | Reconstruction of the existing roadway to provide wider shoulders. | Pavement Widening | 2009-11-04 | 2009-11-04 | 2012-06-29 | 2012-06-29 | 11387836.57 | 4.347
11810 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 0209006 | This project replaces deteriorated truss members and aging concrete deck, along with providing a wider and friendlier pedestrian walkway, for this historic steel truss bridge in the town of Richmond. | Bridge Improvement | 2009-02-06 | 2009-02-06 | 2009-07-06 | 2009-07-06 | 1971156.26 | 0.060
11811 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | 0283009 | This project will construct a new concrete bridge deck and clean and paint the structural steel on bridge # 30 on Sate Route 118 in the Town of East Berkshire. This bridge crosses the Missisuoi River | Bridge Improvement | 2010-02-12 | 2010-02-12 | 2011-08-26 | 2011-08-26 | 1918019.36 | 0.056
11812 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 0283036 | This project improves motorist safety by replacing a functionally obsolete 3-span bridge with a long-lasting single-span weathering steel girder bridge utilizing a high performance concrete deck, a ne | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-06-18 | 2010-06-18 | 2062985.62 | 0.027
11813 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | 0302018 | This project replaces an antiquated and deficient bridge on State Route 15 with a fully modern structure. | Bridge Improvement | 2009-06-15 | 2009-06-15 | 2009-11-30 | 2009-11-30 | 874891.15 | 0.018
11814 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 0372008 | E MONTPLR 118 BRF 037-2(8) BRIDGE REPLACEMENT | Bridge Replacement | 2010-11-08 | 2010-11-08 | 2011-10-28 | 2011-10-28 | 849234.09
11815 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 0372009 | Replace exisitng Bridge #69 ON VT14 in East Montpelier. | Pavement Improvement | 2009-10-16 | 2009-10-16 | 2010-10-01 | 2010-10-01 | 1425433.97 | 0.038
11816 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 0891054 | Repaving the roadway | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2009-11-13 | 2009-11-13 | 7940855.9 | 7.900
11817 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 0891055 | Repairing the existing pipes by putting new pipes inside the existing pipes. | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-10-30 | 2009-10-30 | 1164003.19 | 25.800
11818 | Completed | C200,C240 | Highway Infrastructure Investment Grant | VERMONT | WINDHAM |  |  | 0911057 | ROCKINGHAM IM 091-1(57) STABILIZE ROCK FACE ALONG I91 NB | Pavement Improvement | 2010-08-27 | 2010-08-27 | 2011-06-24 | 2011-06-24 | 500000 | 2.600
11819 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR, ORANGE |  |  | 0912072 | This is a safety project for the removal of ledge from the edge of the roadway on Interstate I-91 at various locations between milepoint 69 and 110 in both the northbound and southbound lanes | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2010-11-19 | 2010-11-19 | 3024403.49 | 37.900
11820 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 1443039 | Replace Deck Bridge #15 ON TH3 in Clarendon. | Bridge Improvement | 2009-09-14 | 2009-09-14 | 2010-08-20 | 2010-08-20 | 401632.22 | 0.000
11821 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 1443045 | Replace existing Bridge #19 ON TH23 (SHORT STRUCTURE) in Chittenden. | Pavement Improvement | 2009-10-28 | 2009-10-28 | 2010-10-29 | 2010-10-29 | 407255.55 | 0.070
11822 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 1443046 | Replace Bridge #20 ON TH23 (SHORT STRUCTURE) in Chittenden. | Pavement Improvement | 2009-10-28 | 2009-10-28 | 2010-10-29 | 2010-10-29 | 371576.63 | 0.070
11823 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | 1444036 | Replace the TH 23 bridge in Braintree over Ayers Brook located 0.1 mile from SR-12 | Bridge Replacement | 2010-09-14 | 2010-09-14 | 2010-11-15 | 2010-11-15 | 338005.57 | 0.000
11824 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | ORLEANS |  |  | 1449028 | This project will replace a severely deteriorated Town Highway bridge for the Town of Brownington | Bridge Replacement | 2009-03-20 | 2009-03-20 | 2009-11-06 | 2009-11-06 | 1056305.4 | 0.000
11825 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 2206001 | This is a paving project for 5 miles of US route 5 between Hartford and Norwich. This project also includes paving the Wilder State highway and safety improvements at the I-91 off ramp with the Wilder | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-10-16 | 2009-10-16 | 2074859.46 | 4.300
11826 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | 2213001 | This project resurfaces 11.2 miles of pavement on Vermont Route 25 between Bradford and Orange | Pavement Improvement | 2009-07-22 | 2009-07-22 | 2009-10-30 | 2009-10-30 | 4596568.65 | 11.330
11827 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | 2217001 | This is a paving project for 11 miles of Vermont Route 104 between the Towns of Fairfax and Saint Albans starting at milepoint 6.8 in the town of Fairfax. | Pavement Improvement | 2009-09-03 | 2009-09-03 | 2010-06-11 | 2010-06-11 | 3225425.65 | 11.653
11828 | Completed | C250,C200 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | 2331001 | Resurface VT113 Chelsea-Vershire. | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-08-25 | 2010-08-25 | 6243795.24 | 7.000
11829 | Completed | C200,C240 | Highway Infrastructure Investment Grant | VERMONT | WINDHAM |  |  | 2401001 | Resurface 11.458 miles of roadway on VT 30 | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-10-15 | 2010-10-15 | 4098051.28 | 11.425
11830 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 2602001 | This project is for paving .8 miles of US Route 5 and the Norwich State Highway and . 5 miles of Vermont Route 10A | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-10-16 | 2009-10-16 | 2265165.04 | 1.600
11831 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 2604001 | This is a paving project for 3 miles of US 2 in Montpelier from Bailey Ave to Granite Street | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-08-26 | 2009-08-26 | 2155563.15 | 2.800
11832 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | ORLEANS |  |  | 2613001 | Repaving the roadway | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-08-19 | 2010-08-19 | 4162711.98 | 5.622
11833 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 2614001 | This project will resurface approximately 5.1 miles along route 4A in the Towns of Fair Haven and Castelton to provide a much smoother and safer ride. In addition key drainage improvements will be ma | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-16 | 2009-10-16 | 2625839.72 | 5.100
11834 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | 2615001 | This project will resurface approximately 1.6 miles of deteriorated pavement which will provide for a smoother and safer ride along Route 4A in the Town of Fair Haven. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-16 | 2009-10-16 | 1059910.58 | 1.600
11835 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 2616001 | This project is for paving 2.9 miles of Vermont Route 15 in Colchester and Essex starting at the Winooski/Colchester town Line. | Pavement Improvement | 2009-04-03 | 2009-04-03 | 2009-10-02 | 2009-10-02 | 2652880.86 | 2.900
11836 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 2617001 | This project is for paving .25 miles of Vermont Route 15 from the US Route 7/ Vermont Route 15 intersection to the Winooski/Colchester line. This project aslo includes concrete repair on US Route 7 in | Pavement Improvement | 2009-06-14 | 2009-06-14 | 2009-10-14 | 2009-10-14 | 2619869.02 | 0.800
11837 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 2618001 | This project is for paving of .9 miles US Route 302 in Montpelier starting from the US Route 2/US Route 302 intersection. | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-08-26 | 2009-08-26 | 726917.67 | 0.900
11838 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | ADDISON |  |  | 2627001 | This project is for repaving 3 miles of Vermont Route 125 starting at mile point 1.0 in the Town of Middlebury and ending at MP 4.0 in the Town of Middlebury | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-10-05 | 2010-10-05 | 1810299.76 | 3.094
11839 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDHAM, WINDSOR |  |  | 2628001 | Repaving the roadway | Pavement Improvement | 2009-04-24 | 2009-04-24 | 2009-10-16 | 2009-10-16 | 4074870.71 | 9.400
11840 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | 2701001 | This is a paving project for 1.5 miles of Vermont Route 14 starting at the US Route 5 intersection.This project also include paving .25miles of US 4 in Hartford. | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-10-16 | 2009-10-16 | 1434807.66 | 1.700
11841 | Underway | C240 | Highway Infrastructure Investment Grant | VERMONT | ESSEX |  |  | 2706001 | Paving roadway | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2010-11-15 |  | 4348946.65 | 10.651
11842 | Underway | C200,C240 | Highway Infrastructure Investment Grant | VERMONT | WINDHAM |  |  | 2707001 | GUILFORD-BRATTLEBORO STP 2707(1) RESURFACE US5 | Pavement Improvement | 2011-05-02 | 2011-05-02 | 2011-08-22 |  | 1786776.77
11843 | Completed | C250 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | 2714001 | This project is for the paving of 9.5 miles of Vermont Route 105 between the towns of Sheldon and Enosburgh. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-07-26 | 2010-07-26 | 2528939.31 | 9.479
11844 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | ESSEX |  |  | 2724001 | REpaving the roadway | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-09-26 | 2010-09-26 | 5839476.04 | 7.781
11845 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | ESSEX |  |  | 2725001 | Repaving the roadway | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-09-24 | 2010-09-24 | 5823803.52 | 7.960
11846 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 2726001 | This project is for paving US Route 7 from the South Burlington/Burlington city line and extending north .2 miles to include the intersection of Interstate 189 | Pavement Improvement | 2009-06-14 | 2009-06-14 | 2009-10-14 | 2009-10-14 | 707779.42 | 0.200
11847 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | 2727001 | This project is for paving US Route 7 from the Intersate 189 intersection and extending north for .25 miles to Hadley Road | Pavement Improvement | 2009-06-14 | 2009-06-14 | 2009-10-14 | 2009-10-14 | 510443.12 | 0.200
11848 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | ADDISON |  |  | 2803001 | This project is for repaving 6.5 miles of Vermont Route 125 starting at mile point 0.00 in the Town of Ripton and ending at MP 0.750 in the Town of Hancock | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-10-05 | 2010-10-05 | 4193272.08 | 6.536
11849 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 6000015 | This project improves motorist safety by rehabilitating existing bridge abutments and replacing the bridge superstructure with a modern steel beam bridge in Barre City. | Bridge Improvement | 2009-04-15 | 2009-04-15 | 2009-11-27 | 2009-11-27 | 1266081.33 | 0.020
11850 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | 6400031 | This project will rehabilitate the historic Taylor St. bridge (Bridge #5, Truss Bridge) over the Winooski River in Montpelier. | Transportation Enhancements | 2009-12-16 | 2009-12-16 | 2010-11-12 | 2010-11-12 | 1799402.05 | 0.067
11851 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | AREH001 | In Shelburne install side walk on Mt. Philo Rd. beginning at Wild Granger Rd and ending at Falls Rd. | Transportation Enhancements | 2010-01-11 | 2010-01-11 | 2010-07-01 | 2010-07-01 | 108940.2 | 0.000
11852 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | AREH002 | In South Burlington repave portions of the bikes paths through out town. | Transportation Enhancements | 2010-05-01 | 2010-05-01 | 2010-07-01 | 2010-07-01 | 157215.53 | 0.000
11853 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | BENNINGTON, RUTLAND |  |  | AREH004 | On the Delaware and Hudson rail trail replace the decks of ten bridges in the towns of Poultney, Pawlet, and Rupert. | Transportation Enhancements | 2010-02-04 | 2010-02-04 | 2010-08-06 | 2010-08-06 | 190153.48 | 0.000
11854 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | AREH005 | In Franklin on Square Rd. also know as Town Highway 16 install sidewalk. | Transportation Enhancements | 2010-01-14 | 2010-01-14 | 2010-07-30 | 2010-07-30 | 10170.86 | 0.000
11855 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | GRAND ISLE |  |  | AREH006 | In North Hero resurface pedestrian path in Knights Point State Park. | Transportation Enhancements | 2010-02-18 | 2010-02-18 | 2010-05-28 | 2010-05-28 | 14715.45 | 0.000
11856 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | AREH007 | In Montpelier on Vine St. replace existing pedestrian bridge. | Transportation Enhancements | 2010-04-19 | 2010-04-19 | 2010-06-18 | 2010-06-18 | 155473.46 | 0.000
11857 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | AREH008 | In Essex on Rt. 15 install sidewalk, curbing, and pedestrian signs. | Transportation Enhancements | 2010-01-08 | 2010-01-08 | 2010-09-17 | 2010-09-17 | 183323.47 | 0.197
11858 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | ARPV001 | Repave 1.6 miles of Maple St and 2.4 miles of Wipple Hollow Rd in West Rutland. | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2010-10-01 | 2010-10-01 | 402127.75 | 2.417
11859 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | GRAND ISLE |  |  | ARPV002 | This is repaving 2.4 miles of (TH 3) West Shore Road and 1.5 miles of (TH 2 0 Alburgh Springs Road | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-10-01 | 2010-10-01 | 404352.09 | 3.160
11860 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | ORLEANS |  |  | ARPV003 | This project will resurface 5.5 miles of Town Highway 1 in Barton. | Pavement Improvement | 2010-01-05 | 2010-01-05 | 2010-09-10 | 2010-09-10 | 581017.34 | 5.530
11861 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON |  |  | ARPV004 | Paving roadway | Pavement Improvement | 2010-05-11 | 2010-05-11 | 2010-07-10 | 2010-07-10 | 365479.2 | 2.086
11862 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | ARPV005 | This project is for the resurfacing of Center Road in Hardwick. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2010-08-07 | 2010-08-07 | 438550.72 | 4.580
11863 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | ADDISON |  |  | ARPV006 | Paving roadway | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-15 | 2010-09-15 | 275744.38 | 4.674
11864 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | CHITTENDEN | BURLINGTON |  | ARPV007 | This is a repaving project for Lake Road in the Town of Milton Vermont | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-06-25 | 2010-06-25 | 295920.33 | 2.538
11865 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | ORLEANS |  |  | ARPV008 | Paving roadway | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-10-01 | 2010-10-01 | 356437.72 | 2.510
11866 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | ARPV009 | This is repaving 4.6 miles of roadway on VT Route 132 in the Town of Strafford | Pavement Improvement | 2010-01-05 | 2010-01-05 | 2010-08-13 | 2010-08-13 | 696182.83 | 4.630
11867 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | ARPV010 | Paving roadway | Pavement Improvement | 2010-01-11 | 2010-01-11 | 2010-08-27 | 2010-08-27 | 455193.23 | 5.006
11868 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | ARTB002 | This project will rehabilitate the bridge carrying VT 144 (Town Highway 2) over a stream | Bridge Improvement | 2010-06-11 | 2010-06-11 | 2010-09-17 | 2010-09-17 | 303447.84 | 0.000
11869 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | LAMOILLE |  |  | ARTB003 | The Town of Belvidere will replace the deck on this Town highway covered bridge. This will improve the ride quality and extend the life of the bridge This project is on the Mill (Lumber) covered br | Bridge Improvement | 2010-07-09 | 2010-07-09 | 2010-09-17 | 2010-09-17 | 49609.74 | 0.000
11870 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | WINDSOR |  |  | ARTB004 | Bridge rehabilitation | Pavement Improvement | 2010-06-14 | 2010-04-20 | 2010-09-17 | 2010-09-17 | 172980.09 | 0.000
11871 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | FRANKLIN |  |  | ARTB005 | The Town of Enosburg will remove the top 2" of pavement on this Town highway bridge and place a waterproff membrane and then resurface with new pavement. This will improve the ride quality and extend | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2010-09-17 | 2010-09-17 | 222944.4 | 0.000
11872 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | ORANGE |  |  | ARTB007 | This project will rehabilitate the bridge that carries Scotch Hollow Road over Peach Brook. | Pavement Improvement | 2010-06-16 | 2010-06-16 | 2010-09-30 | 2010-09-30 | 165988.69 | 0.000
11873 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | RUTLAND |  |  | ARTB008 | This project rehabilitates the bridge that carries Pinnacle Ridge Road over a small tributary of East Creek. | Bridge Improvement | 2010-03-31 | 2010-03-31 | 2010-08-13 | 2010-08-13 | 322179.4 | 0.000
11874 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | ARTB009 | This project is for the rehabilitation of a bridge on US Route 2 (Portland St.) in St. Johnsbury, over the Passumpsic River and the Washington County Railroad. | Bridge Improvement | 2010-06-10 | 2010-06-10 | 2010-12-01 | 2010-12-01 | 767349 | 0.000
11875 | Completed | C220 | Highway Infrastructure Investment Grant | VERMONT | STATEWIDE |  |  | NWRT001 | Rehab two pedestrian trail surfaces. One in Newport, one running from St. Albans-Richford. | Transportation Enhancements | 2010-02-18 | 2010-02-18 | 2010-07-02 | 2010-07-02 | 792679.75 | 0.000
11876 | Completed | C220,C200 | Highway Infrastructure Investment Grant | VERMONT | STATEWIDE |  |  | RAMP001 | Statewide design and reconstruct existing sidewalk ramps to make them ADA compliant. | Transportation Enhancements | 2010-03-11 | 2010-03-11 | 2010-08-27 | 2010-08-27 | 442336.62 | 0.000
11877 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | SURF014 | REPAVING THE ROADWAY WITH A THIN BITUMINOUS SURFACE TREATMENT. | Pavement Improvement | 2009-07-27 | 2009-07-27 | 2010-10-15 | 2010-10-15 | 2286211.49 | 9.420
11878 | Completed | C200 | Highway Infrastructure Investment Grant | VERMONT | WASHINGTON, ORANGE |  |  | SURF015 | This project resurfaces 9.4 miles of pavement on US Route 302 between Barre and Orange. | Pavement Improvement | 2010-06-14 | 2010-06-14 | 2010-08-17 | 2010-08-17 | 1472387.78 | 9.380
11879 | Completed | C240 | Highway Infrastructure Investment Grant | VERMONT | CALEDONIA |  |  | SURF016 | This project resurfaces 2.2 miles of pavement on US Route 302 between Groton and Ryegate. | Pavement Improvement | 2010-06-14 | 2010-06-14 | 2010-08-17 | 2010-08-17 | 384550.87 | 2.221
11880 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | BOTETOURT | ROANOKE | 06 | FS09001 | This project includes a slab removal on the right travel lane on both the NBL and SBL of I-81. On the SBL it will begin at the South end of Rte 640 overpass (exit 156) moving South for 4.3 miles. On | Pavement Improvement | 2009-07-08 | 2009-08-03 | 2010-10-04 |  | 19034256 | 9.640
11881 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | HENRICO | RICHMOND | Multiple | FS09002 | Conversion of CRCP pavement to composite; extensive pavement rehab. Project underway. Completion date June 2010. | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2010-06-02 | 2010-07-27 | 5982880 | 3.280
11882 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09003 | "This project will repair the existing deterioriated concrete pavement and then place 3.5"" inches of asphalt over the existing concrete pavement on I-64 in the City of Chesapeake." | Pavement Improvement | 2009-07-08 | 2009-08-10 | 2011-08-05 | 2011-08-05 | 14376933 | 15.600
11883 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | WYTHE |  | 09 | FS09004 | Milling, paving and guardrail upgrade in Wythe County Northbound I-77 from mile posts 24.19 to 25.69 and 26.59 to 29.22; and on Southbound I-77 from mile posts 40.69 to 46.31. | Pavement Improvement | 2009-07-01 | 2010-05-13 | 2010-11-15 | 2011-06-22 | 5744418 | 0.000
11884 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | WASHINGTON | BRISTOL (VA-TN) | 09 | FS09005 | Milling, paving and guardrail upgrade on Southbound I-81 from mile post 19.63 to 25.36 in Washington County. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2009-10-10 | 2009-10-09 | 2661982 | 5.730
11885 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE EDWARD |  | 05 | FS09006 | This project includes milling the existing 24 foot wide pavement and existing paved shoulder (approx. 2 inches on each side) of Rte. 460 EBL from 1.35 miles East of Rte. 735 to the Nottoway County Lin | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-04-29 | 2009-12-18 | 2486238 | 2.880
11886 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09007 | Basic bituminous overlay on Routes 360 and 460 in Richmond district. Complete. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-09-22 | 2009-09-22 | 1959517 | 23.080
11887 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09008 | VDOT will patch and seal cracks in the exitsting asphalt on I-464 in the City of Chesapeake then place 1.5 inches of new asphalt over the existing asphalt surface. This project also will upgrade the | Pavement Improvement | 2009-07-08 | 2009-07-22 | 2010-09-03 | 2010-09-02 | 4990435 | 5.950
11888 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STAFFORD | FREDERICKSBURG | Multiple | FS09009 | I-95, basic bituminous overlay. Work in Spotsylvania County is complete and work in Stafford to be done next year. | Pavement Improvement | 2009-07-15 | 2009-08-06 | 2010-08-31 | 2010-08-25 | 10221032 | 16.700
11889 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND |  | 01 | FS09010 | Basic bituminous overlay, Route 3 and Route 360 in Lancaster and Richmond counties. Complete. | Pavement Improvement | 2009-07-01 | 2009-07-29 | 2009-10-10 | 2009-10-09 | 2325790 | 16.200
11890 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | FAUQUIER |  | 07 | FS09011 | This resurfacing project inludes mill and overlay of 17.21 miles in length on various routes in Warrenton Residency | Pavement Improvement | 2009-06-09 | 2009-09-11 | 2009-12-01 | 2009-11-25 | 2985888 | 17.270
11891 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | CULPEPER |  | 07 | FS09012 | This resurfacing project includes mill and overlay of 18.41 miles on various routes in Culpeper Residency of VDOT | Pavement Improvement | 2009-06-16 | 2009-07-06 | 2009-12-01 | 2009-12-01 | 2586874 | 18.410
11892 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | ALBEMARLE | CHARLOTTESVILLE | 07 | FS09013 | This resurfacing project is in Albemarle County of Culpeper District includes mill and overlay of 20.3 miles on various routes | Pavement Improvement | 2009-07-08 | 2009-08-02 | 2009-12-01 | 2009-11-30 | 2856813 | 20.390
11893 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | WARREN |  | 07 | FS09014 | Asphalt overlay, rumble strips and guardrail upgrade on Westbound I-66 from mile post 6.6 to 10.7 in Warren County. | Pavement Improvement | 2009-06-09 | 2009-08-04 | 2010-06-30 | 2009-10-28 | 1301178 | 4.100
11894 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09015 | Mill existing asphalt 2 inches and overlay with 2 inches of asphalt | Pavement Improvement | 2009-07-06 | 2009-07-09 | 2009-12-01 | 2009-12-01 | 2802064 | 9.000
11895 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | Multiple | FS09016 | Milling existing asphalt 2 inches and overlay with 2 inches of asphalt | Pavement Improvement | 2009-08-16 | 2009-08-16 | 2009-12-01 | 2009-12-01 | 3601047 | 17.500
11896 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09017 | ***There is a statewide 2009 Design-Build contract to rehab 119 structually deficient bridges to make non-deficient. These are not full replacements. This is only for bridges that carry routes with | Pavement Improvement | 2009-11-12 | 2009-11-19 | 2011-09-25 |  | 3364140 | 0.000
11897 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09018 | See above.*** This project is for the rehab of bridges in the Bristol District. | Pavement Improvement | 2009-11-12 | 2009-11-19 | 2011-09-25 | 2011-10-22 | 5329500 | 0.000
11898 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09019 | See above.*** This project is for the rehab of culverts in the Lynchburg District. | Pavement Improvement | 2009-11-11 | 2009-11-11 | 2011-09-25 |  | 3961744
11899 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09020 | See above.*** This project is for the replacement of superstructures in the Lynchburg District. | Pavement Improvement | 2009-11-11 | 2009-11-18 | 2011-09-25 |  | 10030850
11900 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | ROANOKE |  | FS09021 | See above.*** This project is for the replacement of culverts in the Salem District. | Pavement Improvement | 2009-11-04 | 2009-11-09 | 2011-09-25 |  | 646350 | 0.000
11901 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09022 | See above.*** This project is for the replacement of culverts in the Stauton District. | Pavement Improvement | 2009-11-04 | 2009-11-09 | 2011-09-25 |  | 395650 | 0.000
11902 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | FREDERICKSBURG |  | FS09023 | See above.*** This project is part of the bridge rehab for the Fredericksburg District. | Pavement Improvement | 2009-11-04 | 2009-11-09 | 2011-11-01 | 2011-11-22 | 2685637
11903 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09024 | See above.*** This project is part of the bridge rehab for the Richmond District. | Pavement Improvement | 2009-11-04 | 2009-11-09 | 2011-11-01 | 2011-11-22 | 4884028 | 0.000
11904 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09025 | See above.*** This project is part of the bridge rehab for the Culpeper District. | Pavement Improvement | 2009-10-15 | 2009-11-20 | 2011-11-01 |  | 1385649 | 0.000
11905 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09026 | See above.*** This project is part of the bridge rehab for the Northern Virginia District. | Pavement Improvement | 2009-10-15 | 2009-11-20 | 2011-11-01 |  | 1107329
11906 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | FRANKLIN | ROANOKE | 05 | FS09027 | See above.*** This project is part of the bridge rehab for the Salem District. | Pavement Improvement | 2009-11-11 | 2009-11-18 | 2011-09-25 | 2011-09-25 | 762900
11907 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09028 | See above.*** This project is part of the bridge rehab for the Stauton District. | Pavement Improvement | 2009-10-15 | 2009-11-20 | 2011-11-01 |  | 8010513
11908 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | SPOTSYLVANIA | FREDERICKSBURG | 07 | FS09029 | Design Build project to widen Route 3. Project recently awarded and design is proceeding; construction to begin in Spring. | Pavement Widening | 2009-11-10 | 2009-11-10 | 2012-06-15 |  | 25214915 | 1.210
11909 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK |  | FS09030 | This project will widen a 3.15 mile section of Route 105 in the City of Newport News and York County from 2 existing lanes to a 4 lane divided principle arterial.? | Pavement Widening | 2009-10-20 | 2009-11-02 | 2012-04-16 |  | 18269034 | 6.800
11910 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | SMYTH |  | 09 | FS09031 | Milling, paving and guardrail upgrade on Northbound and Southbound I-81 from mile posts 34.25 to 35.35 (on NBL) and 35.35 to 34.32 (on SBL) in Smyth County. | Pavement Improvement | 2009-07-23 | 2009-09-16 | 2010-06-01 | 2010-04-06 | 1586387 | 2.130
11911 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09032 | This project will repair cracks and patch the exisitng deteriorated pavement and then place a thin layer of asphalt of the existing pavement. | Pavement Improvement | 2009-07-08 | 2009-07-24 | 2010-08-06 | 2010-09-17 | 7048181 | 12.830
11912 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | JAMES CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09033 | James City: Various Locations on Interstate & primary Routes Resurfacing Schedule | Pavement Improvement | 2010-06-24 | 2010-07-12 | 2011-06-10 |  | 5891228
11913 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | FREDERICKSBURG |  | FS09035 | ARRA - Resurfacing in Stafford, Spotsylvania, King George | Pavement Improvement | 2010-07-23 | 2010-09-28 | 2010-12-01 | 2010-12-01 | 2331827 | 0.000
11914 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | BOTETOURT |  | 06 | FS09039 | This project will resurface and upgrade the guarrails on a portion of Rte. 220 and Rte. 58. | Pavement Improvement | 2009-08-25 | 2010-02-16 | 2010-06-10 | 2010-06-10 | 2919572 | 14.380
11915 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | MADISON |  | 07 | FS09040 | This project will provide smooth surface by milling and overlaying a portion of Route 230, 231 and 29 in Culpeper. | Pavement Improvement | 2009-07-08 | 2009-07-15 | 2009-11-12 | 2009-11-12 | 1726640 | 15.600
11916 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE |  |  | FS09041 | Districtwide pavement overlay in Lynchburg District. | Pavement Improvement | 2009-10-01 | 2009-10-20 | 2009-11-30 | 2009-11-30 | 335749 | 2.970
11917 | Completed | C220 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | Multiple | FS09044 | Construction of walkways at Marine Corps Heritage Center | Transportation Enhancements | 2010-05-25 | 2010-06-03 | 2010-11-17 | 2011-04-14 | 500000 | 0.000
11918 | Underway | C220 | Highway Infrastructure Investment Grant | VIRGINIA | SALEM CITY | ROANOKE | 06 | FS09045 | Construction of a trail connection, including a bridge across the Roanoke River, tying Roanoke River Greenway to Tinker Creek Greenway and to the Roanoke County line. | Other | 2011-12-27 | 2011-12-28 | 2012-10-09 |  | 600000 | 0.000
11919 | Underway | C220 | Highway Infrastructure Investment Grant | VIRGINIA | ROANOKE CITY | ROANOKE | 06 | FS09046 | Construction of a trail connection, including a bridge across the Roanoke River, tying Roanoke River Greenway to Tinker Creek Greenway and to the Roanoke County line. | Transportation Enhancements | 2010-12-06 | 2010-12-06 | 2012-01-30 |  | 1400000 | 0.000
11920 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND CITY | RICHMOND | 01 | FS09047 | Relocation of an existing left turn at the Route 36 (Oaklawn Boulevard)/Route 144 (Temple Avenue) intersection and construction of a new ramp. The new ramp will allow drivers to make a double left tur | Pavement Widening | 2010-07-06 | 2010-07-06 | 2012-11-12 |  | 9877181
11921 | Obligated and Not Awarded | C220 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND CITY | RICHMOND | Multiple | FS09048 | NFO trails project, part of series of jobs to connect Richmond with Williamsburg via trails. | Other |  |  |  |  | 8183825 | 11.000
11922 | Underway | C220 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE EDWARD |  | 05 | FS09049 | Historic High Bridge reconstruction over Appomattox River | Transportation Enhancements | 2011-03-07 | 2011-03-07 | 2012-02-01 |  | 2000000 | 0.000
11923 | Obligated and Not Awarded | C220 | Highway Infrastructure Investment Grant | VIRGINIA | BRUNSWICK |  | Multiple | FS09050 | ARRA - Tobacco Heritage Trail | Other |  |  |  |  | 6000000 | 0.000
11924 | Underway | C220 | Highway Infrastructure Investment Grant | VIRGINIA | SHENANDOAH |  | 07 | FS09051 | Enhancement project to restore significant remnants of the Historic Valley Turnpike and construction of bicycle/pedestrian trails that will connect the Town of Strasburg, Strasburg Historic District a | Other | 2011-10-27 | 2011-11-14 | 2012-05-15 |  | 850000 | 0.000
11925 | Underway | C240,C230 | Highway Infrastructure Investment Grant | VIRGINIA | SPOTSYLVANIA | STATEWIDE | 01 | FS09053 | This project is for Route 208 - Spotsylvania Courthouse Bypass - Phase II | Pavement Widening | 2010-05-12 | 2010-05-27 | 2013-02-28 |  | 11534887 | 4.416
11926 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | VIRGINIA | GILES |  | 09 | FS09054 | The project is located on route 61 in the Town of Narrows, Giles County. The purpose of this project is to replace the existing structurally deficient bridge crossing the New River, Route 460 and Old | Bridge Replacement | 2010-11-04 | 2010-12-06 | 2013-12-02 |  | 18209077
11927 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | VIRGINIA BEACH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09055 | This project consists of widening Witchduct Road in Virginia Beach from 4 lanes to 6 lanes from Bonney Road to Grayson Road. | Pavement Widening | 2010-01-18 | 2010-01-18 | 2012-02-02 | 2011-11-23 | 9640484 | 0.000
11928 | Completed | C200 | Highway Infrastructure Investment Grant | VIRGINIA | ALBEMARLE | CHARLOTTESVILLE | Multiple | FS09056 | Widen the westbound exit approach lane of Interstate 64 starting at the westbound exit lane for 5th Street and widening to the intersection with Route 631, all in Albemarle County. | Safety/Traffic Management | 2010-06-14 | 2010-06-14 | 2010-09-02 | 2010-09-02 | 784792
11929 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | ALBEMARLE | CHARLOTTESVILLE | Multiple | FS09057 | ARRA I-64 Shadwell EBL Exit Install Dual LTL to WB Rte 250 | Pavement Improvement | 2010-06-15 | 2010-06-30 | 2010-12-02 | 2010-12-02 | 1202900
11930 | Completed | C200,C240 | Highway Infrastructure Investment Grant | VIRGINIA | STAFFORD | FREDERICKSBURG | 01 | FS09058 | This project is for ARRA Route 630 - Bridge Over CSX Railroad (Structure #6040) | New Construction | 2010-04-28 | 2010-05-12 | 2011-09-15 | 2011-08-22 | 4439102
11931 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | MANASSAS CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09060 | ARRA Rte.28/Wellington Road Grade Crossing | Pavement Widening | 2010-08-30 | 2010-09-07 | 2012-11-09 |  | 18331803
11932 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | ARLINGTON | WASHINGTON (DC-MD-VA) | Multiple | FS09061 | ARRA Interchange at Rte 50 and Courthouse Rd | Pavement Widening | 2011-04-11 | 2011-04-11 | 2013-11-30 |  | 22218100
11933 | Underway | C240,C230 | Highway Infrastructure Investment Grant | VIRGINIA | FAIRFAX | WASHINGTON (DC-MD-VA) | Multiple | FS09062 | ARRA Fairfax County Pkwy Fair Lakes Interchange | Pavement Widening | 2010-09-22 | 2010-09-28 | 2013-10-25 |  | 40815564 | 3.180
11934 | Underway | C220 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09063 | This 1.3 million dollar enhancement project will provide improvement on he Dismal Swamp Canal in the City of Chesapeake. | Other | 2009-12-10 | 2009-12-10 | 2012-05-31 |  | 1300000 | 0.000
11935 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND CITY | RICHMOND | 03 | FS09064 | Widening of US-60/ German School Road near the western City Limits of Richmond. Project currently being Advertised for bids. | Pavement Improvement | 2010-11-09 | 2010-11-09 | 2012-06-30 |  | 3336660 | 1.103
11936 | Underway | C200 | Highway Infrastructure Investment Grant | VIRGINIA | DANVILLE CITY | DANVILLE | 05 | FS09065 | This work is for improving the Grade, Drainage, Asphalt Pavement and the Robertson Bridge from the Intersection of Memorial Drive to 0.322 mi N. of the Intersection with Memorial Drive in the City of | New Bridge Construction | 2010-06-01 | 2010-06-02 | 2012-08-31 |  | 16892680 | 0.320
11937 | Completed | C200 | Highway Infrastructure Investment Grant | VIRGINIA | ALLEGHANY |  | Multiple | FS09066 | Reconstruction of inside shoulders and installation of high tension cable guardrail in the median of I-64 from MP 18.8 to 24.0 in Alleghany County. Project also includes improvement of drainage syste | Safety/Traffic Management | 2010-05-10 | 2010-05-12 | 2011-12-07 | 2011-12-07 | 13404976
11938 | Underway | C200 | Highway Infrastructure Investment Grant | VIRGINIA | ROCKINGHAM | HARRISONBURG | 06 | FS09067 | Widening of Port Republic Road (Route 253) to 4 lanes from about a quarter mile (1150 feet) south of Route 704 (Boyers Road) to approximately 100 feet north of Harrisonburg East City Limits in Rocking | Pavement Widening | 2010-03-16 | 2010-03-16 | 2012-01-27 |  | 12683669
11939 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09068 | Portsmouth: Rail Relocation along 164 Corridor - CN to provide doe an Additional Rail Line along the Rte 164 Median Rail Corridor | Other | 2011-04-11 | 2011-04-11 | 2011-11-15 |  | 9000000
11940 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | HAMPTON CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09069 | This 3.4 mile long maintenance project will remove and replace approximately 2 inches of asphalt from Colliseum Drive to King Street and from Big Bethel Road to the Western City Limits | Other | 2009-09-11 | 2009-09-22 | 2010-12-31 | 2010-06-22 | 10021
11941 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | HAMPTON CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09070 | ARRA Mercury Boulevard Resurfacing | Pavement Improvement | 2010-11-07 | 2010-11-07 | 2011-04-04 |  | 2819158
11942 | Underway | C240,C230 | Highway Infrastructure Investment Grant | VIRGINIA | VIRGINIA BEACH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09071 | ARRA Virginia Beach 165 (Princess Anne Road) 4 Lane Widening | New Construction | 2010-09-14 | 2010-10-04 | 2014-06-05 |  | 21702923
11943 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | HAMPTON CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09073 | Purchasing right of way and moving utilities in preparation of widening of Commander Shepard Boulevard from the intersection of Saunders and Big Bethel Roads to approximately 100 feet (0.019miles) we | Other | 2009-12-30 | 2010-01-04 | 2010-12-31 |  | 3587296
11944 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK |  | FS09080 | ARRA Chesapeake/Suffolk I664 Paving/Drains/Guardrail | Pavement Improvement | 2010-07-21 | 2010-08-16 | 2012-10-15 |  | 14098146
11945 | Completed | C240 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09081 | Rail, roadway and infrastructure improvements at the Norfolk International Marine Terminal to improve train loading and unloading capabilities resulting in time savings, costs to shippers and reducing | Other | 2010-02-22 | 2010-03-08 | 2011-06-30 | 2011-06-22 | 11305958 | 3.920
11946 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | Multiple | FS09082 | Design-build project to complete design and widen Route 1036 (Pacific Blvd) to 4 lanes for 0.61 miles in Loudoun County. | Pavement Improvement | 2010-06-14 | 2010-02-01 | 2011-07-11 |  | 3270797 | 0.400
11947 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | MARTINSVILLE CITY |  | 05 | FS09083 | VDOT aquiring RW to extend Rte. 174/ Liberty Street to 5 lanes | Other | 2010-06-28 | 2010-06-28 | 2012-03-30 |  | 2389384
11948 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09084 | This maintenance project on 12 bridges in the City of Chesapeake will seal cracks in the bridge decks and other preventative maintenance activities as warranted. Only Engineering funding is obligated | Other | 2009-09-25 | 2009-10-05 | 2010-04-28 | 2010-04-28 | 4500
11949 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09085 | ARRA - Chesapeake 168/17/407 Bridge Rehab/Deck Resealing | Bridge Improvement | 2010-09-20 | 2010-10-11 | 2010-12-01 | 2010-11-12 | 1066861
11950 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09086 | This maintenance project will perform preventative maintenance and help preserve the condition of various roadways in the City of Chesapeake. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 | 2010-06-15 | 2010-06-15 | 4159
11951 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09087 | ARRA - CHESAPEAKE CITYWIDE PAVEMENT RESURFACING | Pavement Improvement | 2010-07-22 | 2010-07-22 | 2010-12-31 | 2010-12-31 | 3949087
11952 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | GLOUCESTER | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09088 | ARRA Gloucester 17 Crossover Removal/Turn Lane Improvements | New Construction | 2010-06-09 | 2010-07-28 | 2010-12-01 | 2010-11-29 | 800000
11953 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09091 | This maintenance project will remove and replace 2 inches of asphalt on 6.5 miles of various routes in the City of Newport News including: Jefferson Ave. from Hemlock Rd. to 0.32 Mi. S. J. Clyde Morri | Other | 2009-09-25 | 2009-10-05 | 2010-04-21 | 2010-04-21 | 9909
11954 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09092 | ARRA - Newport News 143/60 Pavement Milling/Resurfacing | Pavement Improvement | 2010-08-30 | 2010-08-30 | 2011-11-11 |  | 3151307
11955 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 03 | FS09093 | This project will upgrade various traffic signals and the central signal control center software in the City of Newport News for system compatability. Only Engineering funding is obligated at this ti | Other | 2009-10-09 | 2009-10-23 | 2010-05-05 | 2010-05-05 | 9377
11956 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09094 | ARRA - Newport News Signal System Upgrade Integration | Safety/Traffic Management | 2010-11-02 | 2010-11-02 | 2012-02-28 |  | 627503
11957 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09096 | This project will include repairing cracked and deterioriated beams and piers as well as other maintenance activities on the Norview Avenue Bridge in the City of Norfolk. Only Engineering funding is | Other | 2009-09-24 | 2009-10-01 | 2010-02-15 | 2010-04-25 | 5000
11958 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09097 | CN Phase for ARRA - Norview Avenue Bridge Rehab | Bridge Improvement | 2010-09-14 | 2010-09-28 | 2011-03-03 | 2011-03-01 | 630555
11959 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09098 | This maintenance project in the City of Norfolk will repave varoius routes within the City limits as determined by the City. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 | 2010-04-25 | 2010-04-25 | 5014
11960 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NORFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09099 | CN Phase for ARRA - Citywide Repaving Project | Pavement Improvement | 2010-08-12 | 2010-10-13 | 2011-12-29 |  | 5211662
11961 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09100 | This project will remove and replace the asphalt surface on a 1 mile section of Route 172 in the City of Poquosen. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-07 | 2010-02-26 | 2010-05-09 | 10067
11962 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09101 | ARRA - Poquoson Route 172 Milling/Resurfacing | Pavement Improvement | 2010-07-23 | 2010-07-31 | 2010-08-31 | 2010-09-20 | 216554
11963 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09103 | This project will study and develop traffic signal standards in the City of Portsmouth | Other | 2009-10-28 | 2009-10-28 | 2010-06-25 | 2010-06-25 | 160000
11964 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09104 | Funding to design and prepare plans for improvements to traffic signals throughout the City of Portsmouth | Other | 2010-10-28 | 2009-10-28 | 2011-08-31 |  | 268000
11965 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | PORTSMOUTH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09105 | ARRA - Portsmouth Traffic Signal System Improvements | Safety/Traffic Management | 2010-11-08 | 2010-12-06 | 2011-11-07 |  | 1907615
11966 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | SUFFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09106 | This project will repave various sections of primary and secondary Routs as determined by the City of Suffolk. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 | 2010-05-23 | 2010-05-23 | 3000
11967 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | SUFFOLK CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09107 | ARRA - Suffolk Citywide Repaving Project | Pavement Improvement | 2010-10-06 | 2010-10-07 | 2011-01-07 | 2011-09-30 | 2264304
11968 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | VIRGINIA BEACH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09108 | ARRA VA Beach 264 Lynnhaven Interchange Improvements/Ramps | New Construction | 2010-08-17 | 2010-09-07 | 2012-10-18 |  | 2030895
11969 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | WILLIAMSBURG CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09109 | This project will repave varoius routes within the City of Williamsburg. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 | 2010-02-26 | 2010-05-01 | 9916
11970 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | WILLIAMSBURG CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09110 | ARRA Williamsburg Citywide Resurfacing | Pavement Improvement | 2010-08-19 | 2010-09-16 | 2011-03-11 | 2011-01-07 | 593080
11971 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | FALLS CHURCH CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09112 | ARRA Traffic Calming - ARRA Stimulus | Pavement Improvement | 2011-03-21 | 2011-04-14 | 2011-06-30 |  | 75000
11972 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | PRINCE WILLIAM | WASHINGTON (DC-MD-VA) | Multiple | FS09113 | ARRA Rt. 3000 Prince William Parkway (update to six-lanes) | Pavement Widening | 2010-05-12 | 2010-05-12 | 2011-08-30 | 2011-08-31 | 6771669
11973 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09114 | ARRA-ROW Phase for the Route 15 Widening | Other | 2010-08-23 | 2011-01-03 | 2011-12-31 |  | 1025000
11974 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09122 | This project will replace existing traffic signal lights with LED signal lights to improve safety and reduce maintenance costs in the City of Chesapeake | Other | 2009-09-25 | 2009-10-05 | 2010-01-24 | 2010-01-31 | 3285
11975 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESAPEAKE CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09123 | ARRA - Chesapeake - Citywide LED Traffic Signal Conversion | Safety/Traffic Management | 2010-11-08 | 2010-11-08 | 2011-04-08 | 2011-06-06 | 298330
11976 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | JAMES CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 03 | FS09124 | ARRA - James City 199/5 Intersection Improvements/Turn Lanes | Safety/Traffic Management | 2010-07-26 | 2010-07-28 | 2010-10-22 | 2011-03-31 | 849764
11977 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09127 | This project will extend the left turn and on Route 143 at Tabb Smith Trail in York County to improve safety. Only Engineering funding is obligated at this time. | Other | 2009-10-05 | 2009-10-05 | 2011-06-03 | 2010-03-05 | 2350
11978 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09128 | ARRA - York 134 Extend Turn Lane at Tabb Smith Trail | Pavement Improvement | 2010-09-07 | 2010-09-13 | 2010-09-28 | 2010-09-23 | 108802
11979 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09129 | This project will repave various routes in York county including Routes 646, 630, 622, 782. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 | 2010-03-02 | 2010-03-05 | 2108
11980 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09130 | CN Phase for ARRA - York 646/630/622/782 Pavement Rehab/Overlay | Pavement Improvement | 2010-09-22 | 2010-10-14 | 2011-06-03 | 2011-04-22 | 1098581
11981 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09131 | This project will construct sidwalks on Routes 134, 716 and 690 in York County. Only Engineering funding is obligated at this time. | Other | 2009-09-25 | 2009-10-05 | 2010-03-02 | 2010-03-05 | 2741
11982 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | YORK | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09132 | CN Phase for ARRA - York 134/716/ 690 Construct Sidewalks | Transportation Enhancements | 2010-09-13 | 2010-10-25 | 2011-06-03 | 2011-04-27 | 343713
11983 | Underway | C490 | OJT/SS | VIRGINIA | STATEWIDE |  |  | FS09133 | Statewide Wounded Veterans Intership Program. | Other | 2009-09-21 | 2009-09-21 | 2015-09-30 |  | 1200000
11984 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | GOOCHLAND | RICHMOND | 07 | FS09134 | ARRA - Goochland 250 Widen to 4 Lanes (Manakin to Hockett) | New Construction | 2010-08-17 | 2010-09-23 | 2011-09-16 |  | 4433715
11985 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | HANOVER | RICHMOND | 07 | FS09135 | ARRA - RT 95 - INTERCHANGE MODIFICATION | Pavement Improvement | 2010-08-02 | 2010-08-30 | 2011-07-11 |  | 3187791
11986 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | CHESTERFIELD | RICHMOND | Multiple | FS09136 | ARRA - RT 10 WIDEN TO SIX LANES | Pavement Widening | 2010-08-16 | 2010-08-16 | 2012-10-12 |  | 10394201
11987 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | STATEWIDE | RICHMOND |  | FS09137 | ARRA - TRI-CITIES RESURFACING PROJECT | Pavement Improvement | 2010-07-06 | 2010-09-26 | 2010-12-01 | 2010-12-01 | 2343635
11988 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | RICHMOND CITY | RICHMOND | Multiple | FS09138 | ARRA - COLONIAL HEIGHTS RESURFACING - CN ONLY | Pavement Improvement | 2010-05-11 | 2010-05-16 | 2010-09-30 | 2010-10-15 | 621032
11989 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | NEWPORT NEWS CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09140 | This project will study and modify the coordination and timing of traffic signals in the City of Newport News to improve intersection operations. | Other | 2011-08-08 | 2011-08-08 | 2014-08-07 |  | 350000
11990 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ALEXANDRIA CITY | WASHINGTON (DC-MD-VA) | 08 | FS09142 | N Va District-Fr:Southside of Eisenhower Ave/ under bridge To Northside of Eisenhwr Ave PE for ARRA Eisenhower Ave Trial-Ph1A/C502 | Other | 2009-10-28 | 2009-11-03 | 2010-02-04 | 2010-02-04 | 3993
11991 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ALEXANDRIA CITY | WASHINGTON (DC-MD-VA) | 08 | FS09143 | ARRA - Eisenhower Avenue Trail - Phase 1A / C502 | Transportation Enhancements | 2010-06-21 | 2010-06-21 | 2011-06-20 |  | 746007
11992 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ALEXANDRIA CITY | WASHINGTON (DC-MD-VA) | 08 | FS09144 | ARRA - Purchase Trolleys | Other | 2010-07-23 | 2011-09-14 | 2011-12-01 |  | 3263775
11993 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ARLINGTON | WASHINGTON (DC-MD-VA) | Multiple | FS09148 | ARRA TSM and Communications Plant Upgrade - PH 1 | Safety/Traffic Management | 2011-03-18 | 2011-04-04 | 2011-11-30 |  | 4193476
11994 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | FAIRFAX CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09149 | ARRA - MPO - Reconstruction and Repaving | Pavement Improvement | 2011-04-03 | 2011-04-03 | 2011-05-29 | 2012-02-10 | 1350000
11995 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | FALLS CHURCH CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09151 | ARRA Reconstruct Sidewalk and Curb and Gutter - City wide | Transportation Enhancements | 2011-04-12 | 2011-04-15 | 2011-12-12 | 2011-11-30 | 300000
11996 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | FAIRFAX | WASHINGTON (DC-MD-VA) | 08 | FS09152 | Northern Virginia- ARRA Herndon Streetscape Utility Relocation | Other | 2010-09-29 | 2010-12-09 | 2011-12-31 | 2012-01-09 | 960000
11997 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09154 | Loudoun Co. Fr: Inter-x Waxpool Rd and Loudoun Co Pkwy To: Inter-X PE for ARRA Waxpool Rd/Loudon Pkwy turn lane & signal mod | Safety/Traffic Management | 2010-03-18 | 2010-03-18 | 2010-12-10 | 2010-12-10 | 1500000
11998 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09156 | ARRA - Loudoun 28 Flashing Beacon Warning System NB Waxpool | Safety/Traffic Management | 2010-08-06 | 2010-08-11 | 2010-11-23 | 2010-12-06 | 326420
11999 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09157 | ARRA - Loudoun Misc.LED Signals/Ped Countdowns/Power Sources | Safety/Traffic Management | 2010-06-01 | 2010-06-16 | 2011-07-29 | 2011-07-29 | 470463
12000 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09158 | ARRA - Loudoun Misc. Install UPS for Major Signals | Safety/Traffic Management | 2010-06-01 | 2010-06-15 | 2011-07-29 | 2011-07-29 | 1006091
12001 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | LOUDOUN | WASHINGTON (DC-MD-VA) | 10 | FS09159 | ARRA - Loudoun Misc. Upgrade/Install Pavement Markers | Safety/Traffic Management | 2010-08-04 | 2010-08-11 | 2011-03-31 | 2011-05-12 | 395257
12002 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | MANASSAS CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09160 | ARRA - Wellington Road Construction | Pavement Improvement | 2010-08-23 | 2010-08-23 | 2012-02-28 |  | 2452849
12003 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | MANASSAS PARK CITY | WASHINGTON (DC-MD-VA) | Multiple | FS09161 | ARRA - ROW Phase - Intersection Improvements on Manassas Dri | Other | 2011-04-11 | 2011-04-11 | 2012-02-29 |  | 300000
12004 | Obligated and Not Awarded | C200,C240 | Highway Infrastructure Investment Grant | VIRGINIA | ROANOKE CITY | ROANOKE | 06 | FS09164 | ARRA RTE. 581 - at Elm Ave. (Design-Build) | Safety/Traffic Management |  |  |  |  | 19446796
12005 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | JAMES CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 03 | FS09165 | ARRA COUNTY WIDE - PAVEMENT OVERLAY VARIOUS ROADS | Other | 2009-12-16 | 2009-12-22 | 2010-06-24 | 2010-06-24 | 2581
12006 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | JAMES CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 01 | FS09166 | ARRA COUNTY WIDE - PAVEMENT OVERLAY VARIOUS ROADS | Pavement Improvement | 2010-10-26 | 2010-11-10 | 2011-03-23 | 2011-03-23 | 745726
12007 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09167 | ARRA - Ped Access Feasibility Study for Windsor Middle | Other | 2010-11-08 | 2010-11-08 | 2011-09-30 |  | 70000
12008 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 03 | FS09168 | ARRA - Route 17 Turn Lane Improvement | Other | 2009-12-16 | 2009-12-18 | 2010-02-15 | 2010-05-18 | 4091
12009 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09169 | ARRA - Route 17 Turn Lane Improvement | Safety/Traffic Management | 2010-10-27 | 2010-11-03 | 2010-12-10 | 2011-02-17 | 99665
12010 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09170 | ARRA - Isle of Wight 58 Pavement Overlay | Other | 2009-12-16 | 2009-12-16 | 2010-04-13 | 2010-04-13 | 1006
12011 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09171 | ARRA - Isle of Wight 58 Pavement Overlay | Safety/Traffic Management | 2010-07-26 | 2010-09-23 | 2010-12-01 | 2010-12-01 | 304980
12012 | Underway | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09172 | ARRASmithfield Downtown Revitalization-Streetscaping Phase V | Transportation Enhancements | 2010-12-03 | 2010-12-06 | 2011-12-29 |  | 165329
12013 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09173 | ARRA - Sidewalk Installation and Repairs | Other | 2010-02-08 | 2010-02-08 | 2010-03-02 | 2010-05-16 | 2135
12014 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09174 | ARRA - Sidewalk Installation and Repairs | Transportation Enhancements | 2010-11-22 | 2010-12-10 | 2011-02-04 | 2011-02-11 | 85642
12015 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 04 | FS09175 | ARRA - Isle of Wight 460 UPS Battery Back-up Systems | Other | 2009-12-19 | 2009-12-22 | 2010-04-12 | 2010-04-12 | 1308
12016 | Completed | C230 | Highway Infrastructure Investment Grant | VIRGINIA | ISLE OF WIGHT | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | Multiple | FS09176 | ARRA - Isle of Wight 460 UPS Battery Back-up Systems | Safety/Traffic Management | 2010-02-11 | 2010-02-11 | 2010-04-12 | 2010-05-10 | 4985
12017 | Underway | C200,C240 | Highway Infrastructure Investment Grant | VIRGINIA | WASHINGTON |  | 09 | FS09177 | ARRA Rte. 58 4-Lane Project Abingdon to Damascus | Pavement Widening | 2010-06-21 | 2010-06-22 | 2012-06-25 |  | 22798005
12018 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | ROANOKE | ROANOKE | Multiple | FS09179 | ARRA - RTE. 221 - RECONSTRUCT TO 4 LANES - CN ONLY | New Construction | 2010-09-14 | 2010-09-14 | 2013-08-01 |  | 25364476
12019 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | VIRGINIA BEACH CITY | NEWP NEWS-HAMPTON-VA BEACH-NORFOLK | 02 | FS09180 | Additive Component of Princess Anne Road Project (UPC 93522) | New Construction | 2010-09-14 | 2010-10-04 | 2014-06-05 |  | 5434263
12020 | Underway | C240 | Highway Infrastructure Investment Grant | VIRGINIA | FAIRFAX | WASHINGTON (DC-MD-VA) | Multiple | FS09181 | ARRA - I66 Pavement | Pavement Improvement | 2011-01-26 | 2011-01-26 | 2012-11-12 |  | 20066412
12021 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 0002300 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-05-28 | 2009-05-07 | 2009-12-31 | 2009-10-12 | 1833769.79 | 5.230
12022 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PEND OREILLE |  | 05 | 0002301 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-24 | 2009-06-09 | 2010-06-15 | 2009-10-07 | 5529554.68 | 12.680
12023 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | LINCOLN |  | 05 | 0002302 | Construct a new sidewalk and pedestrian crossing that will provide safer passage for pedestrians to cross from Wilbur Street. | Safety/Traffic Management | 2009-07-15 | 2009-06-22 | 2010-06-30 | 2010-04-08 | 160000 | 0.360
12024 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 0002821 | Improve the capacity and safety of the intersection by constructing additional traffic lanes and turn lanes. | Pavement Widening | 2010-02-01 |  |  | 2011-07-28 | 2359794.79 | 0.000
12025 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON, GRAYS HARBOR |  | Multiple | 0008012 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2009-11-18 | 2009-11-02 | 2010-08-16 | 2010-05-14 | 1500000 | 20.630
12026 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | COLUMBIA |  | 05 | 0012194 | Add landscaping and irrigation system to the West entrance into the City of Dayton along US 12. | Transportation Enhancements | 2009-09-14 |  |  | 2009-10-21 | 144169.27 | 0.166
12027 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KLICKITAT |  | 04 | 0014062 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 2009-06-10 | 2009-05-22 | 2010-05-10 | 2009-08-22 | 412012.96 | 5.360
12028 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK |  | 03 | 0014063 | Construct a pedestrian tunnel underneath State Route 14 to improve pedestrian access and safety. | Transportation Enhancements | 2009-07-06 |  |  | 2010-06-18 | 506783 | 0.020
12029 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 0014068 | Grind pavement and pave with hot-mix asphalt | Pavement Improvement | 2010-07-26 | 2010-07-13 | 2011-09-30 | 2011-09-30 | 2091286 | 8.520
12030 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | JEFFERSON |  | 06 | 0020163 | Construct roundabouts, center median, sidewalks, drainage, bike lanes, and turn lanes. | Pavement Widening | 2009-09-15 |  |  | 2010-09-10 | 1959623 | 0.795
12031 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | ADAMS |  | Multiple | 0026031 | Apply a Bituminous Surface Treatment. Extend the service life of existing pavement. | Pavement Improvement | 2010-10-28 | 2010-10-04 | 2012-02-06 | 2011-10-01 | 1302000 | 11.210
12032 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 0045005 | Construction of a pedestrian and bike trail on the south side of 188th Street between 59th Avenue and 67th Avenue in Arlington. | Transportation Enhancements | 2009-09-08 |  |  | 2010-05-03 | 106823.65 | 0.570
12033 | Completed | C250,C240 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 0045006 | Construct sidewalks on both sides of Gifford Avenue from 1st Street to 3rd Street will be installed. Facililties within the project limits will be modified to meet ADA standards. | Transportation Enhancements | 2010-08-30 |  |  | 2011-01-18 | 92000 | 0.160
12034 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | 0051270 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2010-03-17 | 2010-02-16 | 2011-05-24 | 2010-11-22 | 2444000 | 17.330
12035 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | 0051277 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2009-06-02 | 2010-01-11 | 2011-04-28 | 2010-11-10 | 6177519 | 7.010
12036 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK |  | 03 | 0051278 | Constructs a new interchange that includes a wider bridge across I-5 and reconstruct the I-5 on and off ramps. | Bridge Replacement | 2009-08-25 | 2009-07-31 | 2012-08-27 | 2011-11-15 | 8200000 | 1.210
12037 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK, COWLITZ | PORTLAND-VANCOUVER, OR-WA | 03 | 0051281 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2009-08-17 | 2009-07-27 | 2010-06-30 | 2010-03-12 | 1445979 | 14.760
12038 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | LEWIS, COWLITZ |  | 03 | 0051283 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2010-02-02 | 2010-01-11 |  | 2010-12-07 | 5136067 | 20.300
12039 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | LEWIS |  | 03 | 0052202 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-05-28 | 2010-01-11 | 2010-04-08 | 2010-11-10 | 2754590.95 | 13.290
12040 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 09 | 0053948 | This project will construct HOV lanes to relieve congestion and reduce the risk of collisions. | Bridge Replacement | 2009-07-23 | 2009-07-13 | 2012-10-01 | 2011-11-11 | 35388653 | 2.890
12041 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON, PIERCE | SEATTLE-TACOMA, WA | 09 | 0053949 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2009-11-23 | 2009-11-02 | 2011-06-30 | 2010-11-01 | 10717996.96 | 21.940
12042 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | TACOMA | 06 | 0053951 | This project reconstructs the eastbound interchange at I-5 and SR 16. This includes replacing the bridges over Nalley Valley, constructing freeway connections, reconstructing all of the ramp roadways | Other | 2011-07-25 | 2011-07-05 | 2011-07-05 | 2013-11-05 | 6227940 | 1.000
12043 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 0054272 | Install fiber, cameras and data stations in the corridor. Compliments conduit installation as part of the median barrier project. | Safety/Traffic Management | 2009-07-07 | 2009-06-15 | 2011-01-03 | 2010-12-03 | 2500000 | 10.580
12044 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT, SNOHOMISH |  | 02 | 0054277 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 2009-06-18 | 2009-06-01 | 2010-12-20 | 2010-05-14 | 6225239.12 | 6.100
12045 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | OKANOGAN |  | 05 | 0097137 | Construct curb; gutter; sidewalk; lighting; and stormwater drainage on US 97, 16th Ave, and Juniper St. | Transportation Enhancements | 2009-09-08 |  |  | 2010-05-06 | 584111 | 1.580
12046 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KLICKITAT |  | 04 | 0097140 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-16 | 2009-05-29 | 2010-05-06 | 2009-11-20 | 3199516 | 23.320
12047 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | DOUGLAS |  | 04 | 0097148 | Overlay roadway pavement with a chip seal | Pavement Improvement | 2010-04-19 | 2010-04-12 | 2010-12-30 | 2010-10-15 | 1523415 | 15.530
12048 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 07 | 0099078 | Construct a bridge to separate railroad and vehicle traffic on Duwamish Avenue South. | New Construction | 2009-11-30 |  |  |  | 2875171 | 0.200
12049 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | GRAYS HARBOR |  | 06 | 0101318 | Remove and replace existing deteriorated curbs and sidewalks, along Heron Street from K Street to F Street. | Transportation Enhancements | 2009-06-18 |  | 2009-08-25 | 2009-08-25 | 614448 | 0.400
12050 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | MASON |  | 06 | 0101328 | Widen State Route 101; and provide intersection lighting, a pedestrian actuated signal, asphalt overlay of existing pavement, landscaping, road signs, and striping. | Pavement Widening | 2010-05-24 |  |  | 2010-12-15 | 541220 | 0.000
12051 | Completed | C220,C250 | Highway Infrastructure Investment Grant | WASHINGTON | GRAYS HARBOR |  | 06 | 0108006 | Construct new sidewalk on the north side of Simpson Avenue, from 5th Street to 10th Street; and reconstruct existing sidewalk on the south side of Simpson Avenue from 6th Street to 10th Street. | Transportation Enhancements | 2010-03-01 |  |  | 2010-10-15 | 334309 | 0.320
12052 | Completed | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 01 | 0110008 | Construct a missing trail link between NE 195th Street and North Creek Parkway, construct pedestrian signals at two locations, and construct a 100-foot pedestrian bridge. | Transportation Enhancements | 2010-01-19 |  |  | 2010-12-08 | 500000 | 0.750
12053 | Completed | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 01 | 0110009 | Construct a pedestrian bridge over North Creek north of 228th Street SE, and construct approximately 0.75 miles of an asphalt paved path. | Transportation Enhancements | 2010-01-19 |  |  | 2010-12-08 | 548237.4 | 0.610
12054 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE |  | 08 | 0162017 | Reconstruction of State Route 162 between Calistoga and Bridge Streets. Includes signalization, addition of left turn lanes, installation of street lighting, and landscaping. | Pavement Improvement | 2009-09-08 |  |  | 2010-05-28 | 420000 | 0.260
12055 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 09 | 0167044 | Provide a bypass for surface water draining into the Rainier Ave South pump station. | Other | 2009-09-21 |  |  | 2010-05-05 | 1948674 | 0.220
12056 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | 0170013 | Replacement of 800 feet of multi-modal asphalt trail and trail lighting. | Transportation Enhancements | 2010-01-05 |  |  | 2010-02-10 | 66578 | 0.152
12057 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | 0195045 | Hot mix asphalt paving with basic safety restoration | Pavement Improvement | 2010-05-06 | 2010-04-01 | 2010-06-15 | 2010-07-13 | 2150000 | 8.610
12058 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | 0195046 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2009-07-17 | 2009-07-01 | 2011-03-29 | 2010-05-12 | 118868 | 17.750
12059 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 0195047 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project also includes some h | Pavement Improvement | 2009-11-10 | 2009-10-12 | 2011-04-01 | 2010-06-15 | 2534112 | 4.560
12060 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 0205002 | Replace existing timber bridge with new concrete bridge. | Pavement Improvement | 2009-09-02 |  |  | 2010-04-28 | 350000 | 0.010
12061 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 0206003 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-17 | 2009-06-03 | 2010-06-15 | 2009-09-01 | 672508.59 | 2.440
12062 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | OKANOGAN |  | 05 | 0215006 | Construct sidewalk along Okoma Drive from Jasmine St. to W. 4th Avenue. Also includes installation of sidewalk ramps at intersections; crosswalks; and new curbs. | Transportation Enhancements | 2009-08-10 |  |  | 2009-10-27 | 166002 | 0.910
12063 | Completed | C250,C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 0278001 | Remove and replace sidewalk on west side of First Street and both sides of Emma Street. Includes curbs, driveway approaches, curb ramps, and crosswalk striping where necessary. | Transportation Enhancements | 2010-04-26 |  |  | 2010-07-09 | 299569 | 0.200
12064 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 0365007 | Pavement repairs and resurfacing of Dayton St. (5th Ave S to Admiral Way), 212th St SW (72nd Ave W to 84th Ave W), 220th St SW (SR 99 to 84th Ave W), and Olympic View Dr (76th Ave to Puget Dr). | Pavement Improvement | 2009-09-21 |  |  | 2010-02-01 | 999985 | 2.000
12065 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 0395081 | Construct sidewalks and drainage improvements along US 395 from Juniper Street to Kettle Falls City limits. | Transportation Enhancements | 2009-09-08 |  |  | 2009-11-24 | 43174 | 0.440
12066 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 0395088 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-22 | 2009-05-27 | 2010-06-15 | 2009-09-08 | 1965828.76 | 6.690
12067 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 0395089 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-30 | 2009-06-12 | 2010-06-28 | 2009-11-02 | 6200426.3 | 22.270
12068 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 0395090 | High tension cable median barrier will be installed to reduce the frequency and severity of crossover collisions. | Safety/Traffic Management | 2010-05-03 | 2010-04-01 | 2012-04-30 | 2010-10-22 | 532271 | 5.420
12069 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 0395092 | Rehabilitate 22.5 miles of roadway with hot mix asphalt pavement and upgrade safety features. | Pavement Improvement | 2010-11-12 | 2010-10-28 | 2012-10-15 | 2011-11-17 | 4700000 | 22.490
12070 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON |  | 04 | 03EI001 | Construct new sidewalks on 7th Street from Ellen Avenue to the North City Limits. | Transportation Enhancements | 2009-09-21 |  |  | 2009-11-11 | 207000 | 0.436
12071 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WAHKIAKUM |  | 03 | 0409001 | Replace the existing Puget Island ferry ramp. | Bridge Replacement | 2009-08-18 |  |  | 2010-11-10 | 590000 | 0.020
12072 | Underway | C220,C240 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ | LONGVIEW (OR) | 03 | 0433010 | Clean and paint the remaining steel elements on SR 433/Lewis and Clark Bridge. | Bridge Improvement | 2010-06-08 | 2010-03-15 | 2012-06-22 | 2013-10-15 | 12597294 | 0.540
12073 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | 0503023 | Grind, Inlay and overlay pavement with hot-mix asphalt | Pavement Improvement | 2010-05-04 | 2010-05-17 | 2011-03-28 | 2010-08-30 | 1675967 | 10.470
12074 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON |  | 03 | 0507024 | Pedestrian and street lighting improvements on Sussex Avenue from Ritter Street to Ragless Street. | Transportation Enhancements | 2009-09-28 |  |  | 2009-12-22 | 589000 | 0.400
12075 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 09 | 0509020 | Reconstruct 1st Ave SW between SW 192nd and SW 200th Streets to include three vehicle lanes, bike lanes, street lights, landscaping, and sidewalk. | Pavement Improvement | 2009-08-03 |  |  | 2010-12-09 | 3834000 | 0.500
12076 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 0520042 | Construct a new bridge over State Route 520. Bridge includes two vehicle lanes, bike lanes, sidewalks, street lighting. | New Bridge Construction | 2009-05-12 |  |  | 2010-12-15 | 4594075 | 0.500
12077 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 0529017 | Widen sidewalk along West Marine View Drive to improve pedestrian/bicycle safety. | Transportation Enhancements | 2009-09-28 |  |  | 2010-03-08 | 1287533.22 | 0.530
12078 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | GRAYS HARBOR |  | 06 | 0560006 | New sidewalk and sidewalk ramps on State Route 101 and 7th St, Simpson, 8th St, L St, K St, 6th St, J St, 5th St, H St, Emerson, Jefferson, Grant, Cleveland, 4th St, Riverside, Sumner, 24th St. | Transportation Enhancements | 2009-09-22 | 2009-09-01 | 2010-04-30 | 2010-03-01 | 326071 | 3.430
12079 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | PACIFIC |  | 03 | 0575004 | Construct beach/ocean scenic overlook at Beards Hollow on State Route 100. | Transportation Enhancements | 2009-10-09 |  |  | 2010-06-14 | 100000 | 0.000
12080 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON | OLYMPIA | 03 | 0643005 | Construct missing segments of the Woodland Trail from the Chehalis-Western Regional Trail to the Woodland Creek Community Park through the City of Lacey. | Transportation Enhancements | 2009-06-26 |  |  | 2010-01-11 | 1000000 | 2.400
12081 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 0822128 | This project will rearrange the interchange to increase safety, relieve congestion and improve traffic flow movements. | Bridge Replacement | 2010-03-10 | 2010-02-19 | 2012-08-24 | 2011-10-15 | 19650477 | 1.800
12082 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 0822131 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2009-06-10 | 2010-03-01 | 2011-02-04 | 2010-10-04 | 5952408 | 14.730
12083 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 0822132 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2010-03-19 | 2010-03-01 | 2011-02-04 | 2010-10-16 | 4584688 | 14.730
12084 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS, KING |  | Multiple | 0901476 | Replace the existing traveler information cameras in the Snoqualmie Pass vicinity with low light cameras to provide improved visibility of roadway conditions at night. | Safety/Traffic Management | 2009-05-19 | 2009-08-10 | 2010-03-19 | 2009-11-24 | 60000 | 91.710
12085 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 0901478 | Replacing broken concrete panels, grinding the existing concrete roadway surface and installing dowel bars to extend the service life of the pavement. | Pavement Improvement | 2010-01-08 | 2009-12-02 | 2010-08-31 | 2010-05-13 | 7456270 | 7.580
12086 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902259 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-04-15 | 2009-04-03 | 2010-04-29 | 2009-07-09 | 2403340.87 | 3.730
12087 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902260 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-04-15 | 2009-04-03 | 2010-04-08 | 2009-08-03 | 2729838.46 | 4.680
12088 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902283 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also restore bas | Pavement Improvement | 2009-06-17 | 2009-06-01 | 2010-05-07 | 2009-10-26 | 3440325.89 | 3.210
12089 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902302 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 2009-06-15 | 2009-06-01 | 2011-04-28 | 2010-06-16 | 15118956.47 | 9.500
12090 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 0902315 | Replaces broken or damaged concrete panels, grinds the existing concrete roadway surface and installs dowel bars extending the service life of the existing pavement. This project will also rebuild th | Pavement Improvement | 2010-08-18 | 2010-07-30 | 2013-04-26 | 2012-10-26 | 16304322 | 5.500
12091 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 0902319 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2009-07-17 | 2009-07-01 | 2011-03-29 | 2010-05-12 | 32751 | 11.840
12092 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | 0904118 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-08-04 | 2009-07-13 | 2010-02-16 | 2009-10-28 | 3754574.74 | 6.170
12093 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 09WA004 | Reconstruct North Parkway Avenue from North Onsdorff Boulevard to N 5th Street. The road will include three traffic lanes, curb & gutter, sidewalks, landscaping, and street lighting. | Pavement Widening | 2009-10-02 |  |  | 2010-04-30 | 43788 | 0.450
12094 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 1073004 | Construct new curb, gutter, and sidewalk along East Valley Highway between S. 212th St. and State Route 167; add a third vehicle lane; and traffic signal improvements. | Pavement Widening | 2009-07-27 |  |  | 2011-01-11 | 2000000 | 0.850
12095 | Completed | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 1220021 | Construct a 4.4 mile long trail to connect to an existing trail. Includes the rehabilitation of 5 bridges and trailhead facility. | Transportation Enhancements | 2009-07-07 |  |  | 2010-05-14 | 778317 | 4.400
12096 | Completed | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 07 | 1301003 | Construction of sidewalk, bicycle lane, and street lights on the east side of 4th Avenue SW between SW 153rd Street and SW 156th Street. | Transportation Enhancements | 2009-08-17 |  |  | 2010-01-27 | 536293 | 0.220
12097 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 1335009 | Construct an approximately 0.6 mile long pedestrian pathway. | Transportation Enhancements | 2009-08-24 |  | 2009-09-11 | 2009-09-11 | 116474.47 | 0.576
12098 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 06 | 1343002 | Transit facility improvements for public parking that include structural improvements, electrical, painting, ventilation, fire protection, and signage. | Other | 2010-05-03 |  |  | 2011-01-06 | 798029 | 0.000
12099 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | CHELAN | WENATCHEE | 04 | 1405006 | Cleaning and painting of an historic bridge. | Transportation Enhancements | 2009-09-28 |  |  | 2010-06-15 | 1527749 | 0.208
12100 | Underway | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 07 | 1482010 | Construct a bridge parallel and connected to the existing Spokane Street Viaduct. Includes the construction of new on and off ramps. | Pavement Widening | 2009-12-09 | 2009-12-09 |  |  | 15443000 | 0.750
12101 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP | BREMERTON | 01 | 18F3001 | Construct bike/ped facilities and stormwater facilities on Noll Rd from Hostmark St to the Poulsbo Elementary School. | Transportation Enhancements | 2011-06-20 |  |  | 2011-09-06 | 401128 | 0.500
12102 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 1915008 | Reconstruct roadway to include a center turn lane; two traffic lanes; bike lanes; curb and gutter; sidewalk; and street lighting at intersections. | Pavement Improvement | 2010-04-12 |  |  | 2010-12-10 | 3500000 | 0.120
12103 | Completed | C220,C250 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | 2005075 | Construct a multi-use trail along railroad right of way on the north side of Lake Crescent. | Transportation Enhancements | 2009-07-06 |  |  | 2010-11-04 | 333834.44 | 6.400
12104 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | 2005076 | Construct an approximately 0.7 mile long mult-use trail along railroad right of way. | Transportation Enhancements | 2009-07-14 |  | 2009-09-16 | 2009-09-16 | 111000 | 0.682
12105 | Completed | C250,C240 | Highway Infrastructure Investment Grant | WASHINGTON | FRANKLIN | SPOKANE | 04 | 2011027 | Improve rail access into and out of the Port of Pasco's 'Big Pasco Industrial Center'. | Other | 2010-03-23 |  |  | 2010-08-25 | 220000 | 0.000
12106 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | GARFIELD |  | 05 | 2012017 | Pavement resurfacing on the following roadways: Gould City-Mayview Rd, Iron Springs Rd, Mountain Rd, and Peola Rd. | Pavement Improvement | 2009-05-01 |  | 2009-07-27 | 2009-07-27 | 230915 | 14.990
12107 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | ISLAND |  | 02 | 2015076 | Pavement resurfacing of the following roadways in Island County: Front Street; Alexander Street; Maxwelton Road; 3rd Street; and NE Regatta Drive. | Pavement Improvement | 2009-08-27 |  |  | 2009-09-24 | 301098.1 | 2.970
12108 | Completed | C220,C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 07 | 2017090 | Construct a pedestrian walkway along SW 98th St. corridor between 12th Avenue SW and 11th Avenue SW. | Transportation Enhancements | 2009-06-25 |  |  | 2010-03-05 | 1270557 | 0.050
12109 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 2019024 | Improve a visitor center located south of Ellensburg on the Yakima River Canyon Scenic Byway by adding gravel to the parking area, and replacing fencing and restroom facilities. | Transportation Enhancements | 2009-10-19 |  |  | 2009-11-03 | 41754.91 | 0.000
12110 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 2019025 | Installation of guardrail and related safety improvements on roadways within Kittitas County. | Safety/Traffic Management | 2009-09-14 |  |  | 2009-11-25 | 390012.61 | 2.200
12111 | Completed | C950 | Ferryboat | WASHINGTON | SKAGIT |  | 02 | 2029046 | Construct new ferry terminal main building on Anacortes. | Other | 2010-02-24 |  |  | 2010-11-01 | 750000 | 0.000
12112 | Completed | C250,C220 | Highway Infrastructure Investment Grant | WASHINGTON | SKAMANIA |  | 03 | 2030005 | Rehabilitation and resurfacing of an asphalt pathway section along Cascade Drive from Hot Springs to Greenleaf in the City of North Bonneville. | Transportation Enhancements | 2009-07-30 |  | 2009-08-06 | 2009-08-06 | 13719 | 0.253
12113 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | 2037096 | Construct approximately 1.7 miles of shared bicycle-pedestrian trail adjacent to Haxton Way between Kwina Road and Slater Road. | Transportation Enhancements | 2010-03-29 |  |  | 2010-11-08 | 250000 | 1.799
12114 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2506003 | Reconstruction of the roadway to include asphalt pavement resurfacing, new curb ramps, storm drainage repairs, and new bicycle lanes. | Pavement Improvement | 2009-07-07 |  |  | 2010-04-30 | 856977 | 0.500
12115 | Completed | C250,C220,C200,C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | STATEWIDE | 01 | 2523001 | Modify the existing Interstate 5/196th Street SW interchange to provide a pedestrian route across Interstate 5 and along 196th Street SW. | Transportation Enhancements | 2009-07-17 |  |  | 2010-09-24 | 2175618.57 | 0.300
12116 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2528001 | Reconstruct existing two lane asphalt street. Includes new curb, gutter, sidewalk, drainage facilities, and bike lanes. | Pavement Improvement | 2010-04-01 |  |  | 2010-10-07 | 818156 | 0.000
12117 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 01 | 2567001 | Overlay asphalt on Meridian Ave. from 228th St SE to NE 205th. The preservation includes milling, sub-grade repair as required, and pre-leveling. | Pavement Improvement | 2010-09-07 |  |  | 2010-10-01 | 457354.67 | 1.300
12118 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2674004 | This safety project will replace an existing 4-way stop sign controlled intersection with a roundabout. | Pavement Improvement | 2010-01-11 |  |  | 2010-08-03 | 453431 | 0.200
12119 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2699002 | Asphalt resurfacing of 67th Ave from Grove Street to State Route 528 and 8th Street from State Ave to Cedar Ave. Includes replacing sidewalk ramps. | Pavement Improvement | 2009-08-17 |  |  | 2009-09-14 | 428489.83 | 0.750
12120 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2701004 | Remove existing culvert, construct 600 feet of new stream channel, and install new culvert fully open to fish passage. | Pavement Improvement | 2009-08-17 |  |  | 2009-12-04 | 1403223 | 0.114
12121 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 2722001 | Reconstruction of approximately 0.5 miles of roadway serving major residential and industrial areas. | Pavement Improvement | 2009-07-15 |  |  | 2010-05-28 | 807812.64 | 0.511
12122 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 2787001 | Improve Holly Drive with the construction of curbs, gutters, sidewalks, and bike lanes. | Transportation Enhancements | 2009-09-14 |  |  | 2010-02-19 | 385447 | 0.200
12123 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH |  | 02 | 31BH001 | Reconstruct roadway and construct curb, gutter and sidewalk on 68th Avenue NW between approximately 279th Street NW and at 280th Street NW. | Pavement Improvement | 2009-08-13 |  |  | 2009-10-20 | 641439 | 0.200
12124 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 09 | 3217001 | Construct an extension of Shaw Road from Pioneer to E Main, including a new bridge over the Burlington Northern/Santa Fe railroad tracks. | New Construction | 2009-08-04 |  |  | 2010-08-03 | 1201972 | 0.760
12125 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 06 | 3266006 | Construction of a new bridge that will eliminate four existing roadway/railroad crossings. | New Bridge Construction | 2009-07-31 |  |  | 2011-06-13 | 15408000 | 0.400
12126 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 32DE001 | Rehabilitate the Rutter Parkway bridge by repairing bridge supports, removing the existing bridge deck, installing a new concrete deck, and resurfacing the adjacent roadway with asphalt. | Bridge Improvement | 2009-07-06 |  | 2009-08-19 | 2009-08-19 | 292321.57 | 0.044
12127 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON | RICHLAND-KENNEWICK | 04 | 3412007 | Construct approximately 0.5 miles of concrete sidewalk. Includes landscaping of an existing median. | Transportation Enhancements | 2009-06-22 |  | 2009-09-02 | 2009-09-02 | 112217.32 | 0.000
12128 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON | RICHLAND-KENNEWICK | 04 | 3502002 | Reconstruct roadway and construct bike lanes, curb, gutter, and sidewalks. Install traffic signal at George Washington. Add sidewalks along George Washington and 1st Street. | Pavement Widening | 2009-10-01 |  |  | 2010-09-07 | 1600000 | 0.500
12129 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | 37A1001 | Asphalt resurfacing of the existing pavement. | Pavement Improvement | 2009-09-11 |  | 2009-09-28 | 2009-09-28 | 112304.45 | 0.720
12130 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3840008 | Asphalt resurfacing of the existing roadway, upgrade curb ramps, and improve the stormwater drainage system. | Pavement Improvement | 2009-07-20 |  |  | 2009-09-20 | 2606469 | 2.000
12131 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3867001 | Construction of a new roadway between Lincoln Road and Ash Street. Includes new sidewalks, curbs, bike lanes, and landscaping. Also includes asphalt resurfacing from Austin Road to Ash Street. | Pavement Improvement | 2009-05-08 |  |  | 2010-07-09 | 112720 | 1.300
12132 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3867002 | Replace existing pavement with three inches of asphalt pavement. | Pavement Improvement | 2009-07-06 |  | 2009-08-27 | 2009-08-27 | 821647.9 | 1.950
12133 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3867003 | Reconstruct a portion of Five Mile Road between Berridae and Waikiki by replacing the existing pavement with a new asphalt pavement. The remaining portions of Five Mile Road will be resurfaced with o | Pavement Improvement | 2009-09-08 |  |  | 2009-10-05 | 329203.62 | 1.430
12134 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3881005 | Reconstruct roadway from 53rd to Perry; including widening of the roadway where needed to make room for bike lanes and left turn lane. Signs and Markings for bike lanes from 43rd to 53rd. | Transportation Enhancements | 2011-04-12 |  |  | 2011-06-22 | 258358 | 1.080
12135 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 3936003 | Full depth replacement including sidewalk infill. | Pavement Improvement | 2010-08-30 |  |  | 2010-10-29 | 941642 | 0.690
12136 | Underway | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KING | SEATTLE-TACOMA, WA | 08 | 4053858 | Construct on and off ramps to provide relief in a highly congested area of I-405 in the vicinity of downtown Bellevue and the I-405/SR 520 Interchange. | Pavement Improvement | 2009-11-25 | 2009-11-09 | 2013-06-28 | 2012-12-31 | 79970425.99 | 1.500
12137 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KING, SNOHOMISH | SEATTLE-TACOMA, WA | 01 | 4053859 | Northbound I-405 will be widened to add an auxiliary (add/drop) lane between NE 195th Street and SR 527. | Pavement Widening | 2009-09-11 | 2009-08-26 | 2011-06-30 | 2010-06-17 | 22991402 | 3.000
12138 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 4242022 | Improve rail access into the Port of Vancouver by providing new rail infrastructure within existing facilities, and new track at Terminal 5. | Other | 2009-11-09 |  |  | 2010-06-30 | 2500000 | 0.000
12139 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 4410002 | Widen NE 99th Street to three vehicle lanes, bicycle lanes, and sidewalks between State Route 503 and NE 137th Ave. | Pavement Improvement | 2009-10-19 |  |  | 2010-07-31 | 1831151 | 1.050
12140 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 4566009 | Reconstruct portions of the Nob Hill Boulevard pavement from 64th Avenue to 72nd Avenue. Includes improvements to the curb & gutter, sidewalk, stormwater drainage system, and street lighting. | Pavement Improvement | 2009-09-01 |  |  | 2009-10-28 | 605372.24 | 0.500
12141 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 4628006 | Asphalt resurfacing of the roadway, and upgrading of the curb ramps. | Pavement Improvement | 2009-07-20 |  | 2009-09-07 | 2009-09-07 | 400000 | 0.990
12142 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 4645001 | Widen and reconstruct approximately 0.3 miles of Beaudry Road, including curb and gutter, sidewalks, stormwater drainage system, and street lighting. | Pavement Improvement | 2009-07-20 |  |  | 2009-09-25 | 499214.46 | 0.284
12143 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 4708001 | Reconstruct approximately 0.7 miles of Speyers Road, from the west City limits to Fremont Avenue, including curb and gutter, sidewalk, stormwater drainage system, and street lighting. | Pavement Improvement | 2009-08-17 |  |  | 2009-12-04 | 1536259.07 | 0.680
12144 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON | OLYMPIA | 03 | 5235012 | Construction of a dedicated five foot wide bicycle path on the east side of the roadway, and relocation of the existing sidewalk to accommodate the new bicycle path. | Transportation Enhancements | 2009-07-29 |  |  | 2009-10-28 | 307144 | 0.660
12145 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON | OLYMPIA | 03 | 5235013 | Asphalt resurfacing of Capitol Blvd. from Dennis Street to Israel Road. | Pavement Improvement | 2009-08-10 |  | 2009-09-16 | 2009-09-16 | 159034 | 0.250
12146 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON | OLYMPIA | 03 | 5346001 | Asphalt resurfacing of Union Avenue from Capitol Way to Plum Street. | Pavement Improvement | 2009-07-28 |  |  | 2010-10-12 | 973198.6 | 0.440
12147 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON |  | 09 | 5394003 | Construct sidewalks, street lighting, and intersection crossing improvements on Steilacoom Road, between Stonewood Drive and Duterrow Road. | Transportation Enhancements | 2009-07-31 |  | 2009-09-02 | 2009-09-02 | 87360.12 | 0.170
12148 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | LEWIS |  | 03 | 5667003 | Asphalt resurfacing of Jackson Highway. | Pavement Improvement | 2009-07-09 |  | 2009-09-15 | 2009-09-15 | 736524.65 | 1.590
12149 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | ASOTIN |  | 05 | 6005002 | Asphalt resurfacing of Scenic Way from 2nd Avenue to Fleshman Way. | Pavement Improvement | 2009-08-16 |  |  | 2009-11-20 | 585994.82 | 0.980
12150 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | 6061001 | Asphalt resurfacing of the roadway, including improvements to curbs, sidewalks, bike path, and stormwater drainage system. | Pavement Improvement | 2009-08-24 |  |  | 2010-04-15 | 1200000 | 1.000
12151 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | 6065004 | Construction an approximately 0.5 mile long eight foot wide pedestrian path. | Transportation Enhancements | 2009-08-24 |  |  | 2009-11-24 | 28647 | 0.480
12152 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT | SEATTLE-TACOMA, WA | 02 | 6240001 | Reconstruct existing street with new curb, gutter, storm system, and street pavement. | Pavement Improvement | 2010-03-11 |  |  | 2010-07-07 | 472306 | 0.000
12153 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 6340003 | Asphalt resurfacing of the intersection located at Yakima Valley Highway and Lincoln Avenue. | Pavement Improvement | 2009-11-09 |  |  | 2009-11-23 | 150000 | 0.200
12154 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 6408004 | Asphalt resurfacing of existing road surface; and reconstruction of driveways, crosswalk accesses, and sidewalks. | Pavement Improvement | 2009-09-14 |  |  | 2009-10-14 | 290839 | 0.210
12155 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP | BREMERTON | 01 | 6683004 | Project will improve safety and mobility on Viking Avenue by constructing a two-way left turn lane, bike lanes, stormwater drainage improvements, curb, sidewalk, and intersection channelization at Fin | Pavement Improvement | 2009-06-23 |  |  | 2009-12-06 | 2561886.03 | 0.660
12156 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP | BREMERTON | 01 | 6683005 | Construct bike lanes, curbs, gutter and sidewalks along Viking Avenue from Bovela Lane to a point approximately 1,000 ft south of Bovela Lane. Construct approximately 740 ft. of a continuous left tur | Pavement Improvement | 2010-04-19 |  |  | 2010-10-04 | 824925 | 0.190
12157 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP | BREMERTON | 01 | 6701001 | Widen roadway shoulders near Blakely Elementary School to improve pedestrian safety. | Transportation Enhancements | 2009-08-03 |  | 2009-09-28 | 2009-09-28 | 60402.76 | 0.133
12158 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP | BREMERTON | 01 | 6713001 | Project provides rehabilitation for portions of Manitou Beach Drive and N. Madison for the purpose of preserving the roadway. Work includes asphalt overlay and other surfacing repairs. | Pavement Improvement | 2011-01-31 |  |  | 2011-04-22 | 90000 | 0.600
12159 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ | LONGVIEW (OR) | 03 | 6739001 | Roadway reconstruction and widening, and improvements to the roadway and intersection alignments to increase safety. | Pavement Widening | 2009-08-10 |  |  | 2009-12-18 | 1056593 | 1.230
12160 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ | LONGVIEW (OR) | 03 | 6763001 | Asphalt resurfacing of approximately 1.0 miles of South 13th Avenue. | Pavement Improvement | 2009-07-20 |  |  | 2010-07-02 | 217853.42 | 0.975
12161 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 6949002 | Asphalt resurfacing and restriping of Canyon Road from Interstate 90 to Umptanum Road. | Pavement Improvement | 2009-06-23 |  | 2009-08-13 | 2009-08-13 | 325347.52 | 0.500
12162 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 6949003 | Rotomill , HMA overlay existing asphalt roadway and placement of permanent pavement markings. | Pavement Improvement | 2010-10-04 |  |  | 2010-11-05 | 280000 | 0.454
12163 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS |  | 04 | 6949004 | Grind existing asphalt roadway and overlay with asphalt. | Pavement Improvement | 2011-06-06 |  |  | 2011-07-15 | 158621 | 0.200
12164 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK |  | 03 | 7042001 | Construct a new three lane roadway, with sidewalks and bicycle lanes. | New Construction | 2010-05-27 |  |  | 2011-01-21 | 569529 | 0.760
12165 | Completed | C220 | Highway Infrastructure Investment Grant | WASHINGTON | WALLA WALLA |  | 05 | 7166001 | Construct a multi-use pathway connecting major residential development, a local airport, schools, and the existing pedestrian system. | Transportation Enhancements | 2009-09-21 |  |  | 2009-10-10 | 58000 | 0.270
12166 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WALLA WALLA |  | 05 | 7169001 | Reconstruct 13th Avenue from Rose St. to Abadie St. and from Cherry St. to Rees Ave. Includes sidewalks, bike facilities, stormwater drainage facilities, street lighting, and traffic signals. | Pavement Widening | 2009-10-05 |  |  | 2011-06-24 | 1980000 | 0.714
12167 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT | MOUNT VERNON | 02 | 7337006 | Construct an extension of Laventure Road extending south from Fowler St. to Blackburn Road. Roadway includes two traffic lanes, turn lane, bike lanes, and sidewalks. | New Construction | 2009-07-27 |  |  | 2010-03-19 | 923769 | 0.250
12168 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT |  | 02 | 7390001 | Reconstruct Fruitdale Road from State Route 20 to McGarigle Road. Includes construction of curbs, gutters, sidewalks, and street lighting. | Pavement Improvement | 2009-06-01 |  |  | 2010-05-10 | 134867 | 1.340
12169 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | 7418002 | Asphalt resurfacing of approximately 0.46 miles of the following roadways: Whitman St from Kamiaken to Maple, Maiden Lane from Whitman to Opal, and Opal from Maiden Lane to Campus. | Pavement Improvement | 2009-07-07 |  | 2009-08-04 | 2009-08-04 | 324566.08 | 0.462
12170 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | 7541001 | Reconstruct and widen Mount Pleasant Road. | Pavement Improvement | 2009-08-31 |  |  | 2010-09-24 | 499120.97 | 0.400
12171 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | 7690002 | The construction of a turn lane, curb, sidewalk, street lighting and bicycle pathways on Cheney-Spangle Road from State Route 904 to Cheney City limits. | Transportation Enhancements | 2009-09-08 |  |  | 2010-09-14 | 576416 | 0.400
12172 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | 7690003 | Install concrete pads and sidewalks to accommodate pedestrian access over the rail lines. | Transportation Enhancements | 2010-02-16 |  |  | 2010-10-30 | 106000 | 0.070
12173 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | ISLAND |  | 02 | 7790002 | Widening of Ault Field Road between Oak Harbor Road and Goldie Road to provide an additional travel lane. | Pavement Improvement | 2009-07-23 |  |  | 2010-05-24 | 1085488.15 | 0.240
12174 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | 8037001 | Reconstruction of existing road and construction a new road on 2nd Ave from Washington to Portal Way at the Interstate-5 southbound offramp. | New Construction | 2009-09-01 |  |  | 2010-07-23 | 1541000 | 0.500
12175 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 8051001 | Asphalt resurfacing of Euclid Road from Forsell Road to Stassen Way. | Pavement Improvement | 2009-06-25 |  | 2009-08-21 | 2009-08-21 | 308198.35 | 0.767
12176 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | 8057001 | Replace the asphalt pavement, improve storm drainage, construct sidewalks, provide street and pedestrian lighting, and landscaping. | Transportation Enhancements | 2010-03-16 |  |  | 2010-10-29 | 2029167.12 | 0.625
12177 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | 8158001 | Widening and asphalt resurfacing of roadway; and improvements to curb, gutter, and stormwater drainage. | Pavement Improvement | 2009-06-09 |  |  | 2010-05-12 | 981169 | 0.600
12178 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | 9905005 | Asphalt resurfacing of existing street, striping, and curb ramp installation. | Pavement Improvement | 2009-08-10 |  |  | 2009-10-06 | 393000 | 0.341
12179 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | STATEWIDE | 03 | 9906026 | Asphalt resurfacing of the following locations: NW 9th Ave, NW 119th St/7th Ave/NW 114th St, NE 72nd Ave, SE Gibson Rd, NW 199th St, NE 20 Ave/Union Rd, NE 78th St/76th St, NW 151st/139th Sts/Tenny R | Pavement Improvement | 2010-04-22 |  |  | 2010-08-05 | 668849 | 10.530
12180 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | SPOKANE | 03 | 9906027 | Asphalt resurfacing of the following locations: N. Parkway Ave, NW 25th St, SW 20th Ave, SE Eaton Blvd, S. Parkway Ave, and NW 20th Ave. | Pavement Improvement | 2010-05-18 |  |  | 2010-06-18 | 406212 | 0.000
12181 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK | PORTLAND-VANCOUVER, OR-WA | 03 | 9906028 | Pavement overlays on SE 34th St, NE 112th Ave, Andresen Rd, Columbia Way, Grand Blvd, Hearthwood Blvd, Stapleton Rd, and Mill Plain Blvd. | Pavement Improvement | 2010-05-19 |  |  | 2010-08-23 | 2500000 | 0.000
12182 | Completed | C200,C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 08 | 9927049 | Construction of pedestrian amenities to include sidewalks, curb ramps, street lighting, and landscaping. | Pavement Widening | 2009-09-21 |  |  | 2010-05-18 | 582296 | 1.000
12183 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | PIERCE | SEATTLE-TACOMA, WA | 09 | 9927050 | Provide fiber interconnect between City buildings for traffic signal intelligent transportation system (ITS). Fiber interconnect will be routed via existing utility poles and existing conduit. | Safety/Traffic Management | 2010-09-09 |  |  | 2010-10-29 | 146837.27 | 0.000
12184 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS |  | 05 | 9933001 | Asphalt resurfacing of Williams Lake and Cedonia-Addy Roads. | Pavement Improvement | 2009-06-22 |  | 2009-07-15 | 2009-07-15 | 943262.42 | 33.370
12185 | Completed | C220,C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM | BELLINGHAM | 02 | 9937002 | Installation of enhanced pedestrian crossings on high volume streets to improve safety and connectivity. Improvements include flashing lights, illuminated signage, and concrete pedestrian refuge isla | Transportation Enhancements | 2009-07-22 |  |  | 2009-12-29 | 308596 | 0.100
12186 | Completed | C200,C230 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM | STATEWIDE | 02 | 9937003 | Pavement preservation resurfacing of all-weather arterials. Arterials include East Bakerview Road (Landon Road to Hannegan Road) and Hannegan Road (East Bakerview Road to Sunset Drive). | Pavement Improvement | 2010-05-17 |  |  | 2010-08-26 | 1450365.08 | 2.490
12187 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA | YAKIMA | 04 | 9939018 | Asphalt resurfacing of Rudkin Road and the Main Street/Ahtanum Road Intersection. | Pavement Improvement | 2009-09-08 |  |  | 2009-11-13 | 246896.59 | 0.504
12188 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PACIFIC |  | 03 | 9999546 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 2009-04-23 | 2009-04-06 | 2010-05-24 | 2009-07-31 | 394691 | 3.970
12189 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | 9999547 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-05-14 | 2009-05-04 | 2010-02-02 | 2009-08-31 | 5443173.89 | 13.490
12190 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT, OKANOGAN |  | Multiple | 9999548 | Resurfaces deteriorating asphalt pavement with an chip seal overlay and restore existing safety features. | Pavement Improvement | 2009-05-13 | 2009-05-04 | 2009-11-06 | 2009-08-30 | 3292808.47 | 68.500
12191 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STEVENS, ADAMS, FERRY |  | 05 | 9999549 | Replace portable Highway Advisory Radio (HAR) trailers deployed on SR 20 and US 395 for Sherman Pass with permanent HAR stations and install a new station in the vicinity of the Hatton Coulee Rest Are | Safety/Traffic Management | 2009-07-01 | 2009-06-24 | 2010-10-15 | 2009-11-17 | 239999.93 | 0.010
12192 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STATEWIDE |  |  | 9999550 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Other | 2009-04-16 | 2009-04-29 | 2009-12-22 | 2010-11-19 | 187498.16 | 0.000
12193 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | STATEWIDE |  |  | 9999551 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Other | 2009-04-16 | 2009-04-29 | 2009-12-22 | 2009-11-09 | 365573.7 | 0.000
12194 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT, CHELAN, BENTON, DOUGLAS, LINCOLN, FRANKLIN, YAKIMA, SPOKANE |  | Multiple | 9999554 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2009-08-17 | 2009-07-27 | 2010-06-30 | 2009-09-22 | 581025.58 | 235.740
12195 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | PACIFIC, CLARK, KITSAP, LEWIS, MASON, JEFFERSON, THURSTON, GRAYS HARBOR, PIERCE, COWLITZ, CLALLAM |  | Multiple | 9999555 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2010-03-17 | 2010-03-04 | 2011-05-19 | 2010-11-19 | 708200 | 180.020
12196 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | ISLAND, SKAGIT, KING, SNOHOMISH, WHATCOM |  | Multiple | 9999556 | Install centerline rumble strips and replacing pavement markings in a section of highway with a high frequency of crossover collisions. This project will reduce this type of collision and improve safe | Safety/Traffic Management | 2009-08-11 | 2009-07-20 | 2010-06-30 | 2009-11-12 | 822601 | 147.790
12197 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KING, THURSTON, WHATCOM |  | Multiple | 9999557 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2009-08-07 | 2009-07-20 | 2010-06-30 | 2010-03-31 | 946131 | 6.009
12198 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT, KITTITAS |  | 04 | 9999558 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2009-08-17 | 2009-07-27 | 2010-06-30 | 2009-11-09 | 804861.74 | 10.620
12199 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | MASON, KITSAP, THURSTON |  | Multiple | 9999576 | Install high tension cable barrier in the median to prevent crossover collisions. | Safety/Traffic Management | 2010-04-28 | 2010-04-09 | 2010-12-01 | 2010-10-06 | 330389 | 12.350
12200 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT, OKANOGAN |  | Multiple | 9999577 | Overlay pavement with a chip seal | Pavement Improvement | 2010-04-07 | 2010-03-23 | 2010-12-30 | 2010-10-01 | 2632580 | 32.840
12201 | Completed | C240 | Highway Infrastructure Investment Grant | WASHINGTON | KITTITAS, KING, YAKIMA, SNOHOMISH |  | Multiple | 9999578 | Install cable median crossover barrier to improve safety. This will reduce the incidences of vehicles crossing through the median into the opposite direction of travel. | Safety/Traffic Management | 2010-04-12 | 2010-03-23 | 2011-04-22 | 2010-07-23 | 1183326 | 11.060
12202 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | 9999585 | Asphalt overlay of Broadway between 24th Street and 20th Street, and Pacific Avenue between Maple and Fulton. Includes utility adjustments, ADA improvements, and all other associated work. | Pavement Improvement | 2010-08-16 |  |  | 2010-10-22 | 640290 | 0.530
12203 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON |  | 04 | A031002 | Realign Webber Canyon Road and construct a new Burlington Northern/Santa Fe Railroad underpass to improve safety by eliminating the roadway/railroad crossing. | Pavement Improvement | 2010-03-01 |  |  | 2010-10-20 | 1000647 | 0.300
12204 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | BENTON |  | 04 | A032001 | Reconstruction of Sheridan Avenue from Third Street to Sixth Street including sidewalks, curb and gutter, drainage, and street lighting. | Pavement Improvement | 2009-07-20 |  |  | 2009-10-30 | 473511 | 0.275
12205 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | CHELAN |  | 04 | A045002 | Reconstruct asphalt pavement, increase the vertical clearance at a railroad trestle, and construct a shared-use path through the trestle. | Pavement Improvement | 2009-06-08 |  |  | 2009-10-26 | 1021318 | 0.560
12206 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | CLALLAM |  | 06 | A058001 | Asphalt resurfacing and minor roadway widening to add curb, gutter and sidewalk. | Pavement Improvement | 2009-08-12 |  |  | 2009-12-11 | 160000 | 0.510
12207 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | A083002 | Asphalt pavement resurfacing, including improvements to the street lighting, sidewalks, crosswalks, and stormwater drainage. | Transportation Enhancements | 2009-09-08 |  |  | 2010-08-27 | 416250 | 0.300
12208 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | LINCOLN |  | 05 | A221003 | Asphalt resurfacing of approximately 4 miles of roadway. | Pavement Improvement | 2009-07-20 |  | 2009-07-30 | 2009-07-30 | 636348.73 | 4.240
12209 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SKAMANIA |  | 03 | A301006 | Asphalt pavement resurfacing of approximately 1.0 mile of Wind River Road. | Pavement Improvement | 2009-07-30 |  | 2009-08-06 | 2009-08-06 | 306711 | 0.920
12210 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON |  | 03 | A341004 | Widen existing two lane roadway to add a two way center left turn lane on Old Highway 99; and replace existing bridge with a new 5 traffic lane bridge, including bike lanes, sidewalks, and illuminatio | Bridge Replacement | 2010-02-22 |  |  | 2010-11-01 | 1330000 | 0.800
12211 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | A381004 | Asphalt resurfacing and striping of approximately 5.5 miles of Wawawai Road. | Pavement Improvement | 2009-08-11 |  | 2009-09-04 | 2009-09-04 | 782204.39 | 5.440
12212 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | A393001 | Asphalt resurfacing of Harrah Road from South Town Limits to North Town Limits. | Pavement Improvement | 2009-09-14 |  |  | 2009-10-09 | 340395.33 | 0.625
12213 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | ADAMS |  | 04 | B012002 | Resurface approximately 3.0 miles of roadway with two inches of asphalt. | Pavement Improvement | 2009-07-08 |  | 2009-07-27 | 2009-07-27 | 707273.49 | 3.030
12214 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | CLARK |  | 03 | B063002 | Asphalt resurfacing of Hillhurst Road between South 15th Circle and South 22nd Circle. | Pavement Improvement | 2009-08-25 |  | 2009-09-18 | 2009-09-18 | 168054 | 0.560
12215 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | COLUMBIA |  | 05 | B071002 | Resurface existing 24 ft wide road with asphalt. | Pavement Improvement | 2010-06-01 |  |  | 2010-08-02 | 615000 | 0.000
12216 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | COLUMBIA |  | 05 | B074001 | Asphalt resurfacing of East Dayton Avenue from Front Street to US 12. | Pavement Improvement | 2009-08-24 |  | 2009-10-05 | 2009-10-05 | 222875.05 | 0.250
12217 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | FRANKLIN |  | 04 | B111002 | Relocation of the south 1.1 miles of the R-170 Road outside of the existing roadside slide area. | Pavement Improvement | 2009-09-08 |  |  | 2009-11-06 | 748315.87 | 1.100
12218 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | PACIFIC |  | 03 | B256007 | Asphalt resurfacing of Sandridge Road from State Route 101 to 67th Place; and install a traffic signal at the intersection of Sandridge Road and Sid Snyder Drive. | Pavement Improvement | 2009-08-03 |  |  | 2009-10-20 | 279396 | 1.620
12219 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | B391002 | Asphalt resurfacing of South Camas Street, from 3rd Street to 9th Street. | Pavement Improvement | 2009-10-07 |  |  | 2009-11-03 | 312000 | 0.400
12220 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | WAHKIAKUM |  | 03 | C350002 | Resurfaces deteriorating asphalt pavement with an hot mix asphalt overlay and restore existing safety features. | Pavement Improvement | 2009-06-17 | 2009-06-01 | 2010-08-23 | 2010-03-25 | 200000 | 27.760
12221 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KITSAP |  | 06 | D185001 | Construction of approximately 1.5 miles of new roadway, intersection improvements, bicycle lanes, and a separated asphalt pedestrian path. | New Construction | 2009-10-12 | 2009-10-12 |  | 2010-10-25 | 2623386 | 1.500
12222 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | PEND OREILLE |  | 05 | D261001 | Asphalt resurfacing of Deer Valley Road from Coyote Trail to Gray Road. | Pavement Improvement | 2009-09-14 |  |  | 2009-10-08 | 465226.3 | 1.170
12223 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | SAN JUAN |  | 02 | D281003 | Asphalt resurfacing of Fisherman Bay Road, and installation of safety fencing. | Pavement Improvement | 2009-08-28 |  | 2009-09-24 | 2009-09-24 | 416620 | 1.760
12224 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | SKAGIT |  | 02 | D291002 | Asphalt resurfacing of Maple Avenue from Morris Street to Caledonia Street, installation of curb ramps. | Pavement Improvement | 2009-08-06 |  | 2009-08-29 | 2009-08-29 | 154800 | 0.502
12225 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | OKANOGAN |  | 05 | F241005 | Asphalt resurfacing of approximately 0.5 miles of Main Street (from south city limits to Lake Street) & East Lake Street (from Main Street east to city limits). | Pavement Improvement | 2009-06-15 |  | 2009-06-19 | 2009-06-19 | 119071.16 | 0.540
12226 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SNOHOMISH | SEATTLE-TACOMA, WA | 02 | H310001 | Asphalt pavement resurfacing on 84th Street NE. | Pavement Improvement | 2010-02-03 |  |  | 2010-04-20 | 481976 | 4.720
12227 | Completed | C200,C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | I329001 | Reconstruct pavement section between existing curbs. Replace ADA non-conforming handicap ramps. | Pavement Improvement | 2011-05-24 |  |  | 2011-07-07 | 559267 | 0.260
12228 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHITMAN |  | 05 | I382004 | Asphalt resurfacing of South Main Street from State Route 195 to the Fairview Street and Meadow intersection. | Pavement Improvement | 2009-09-08 |  | 2009-09-21 | 2009-09-21 | 116579.52 | 0.284
12229 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | MASON |  | 06 | K232001 | Asphalt resurfacing of approximately 1.6 miles of McEwan Prairie Road. | Pavement Improvement | 2009-08-26 |  | 2009-09-04 | 2009-09-04 | 288576.34 | 1.620
12230 | Completed | C220,C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | THURSTON |  | 03 | K340001 | Widen and provide an asphalt overlay of Minnesota Street, construct sidewalks and crosswalks, and update traffic signs. | Pavement Improvement | 2009-08-25 |  |  | 2010-06-17 | 690816.95 | 0.300
12231 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | FERRY |  | 05 | L102009 | Asphalt resurfacing of approximately 9 miles of Bridge Creek Road. | Pavement Improvement | 2010-05-01 |  |  | 2010-06-24 | 317939.15 | 7.110
12232 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | KLICKITAT |  | 03 | L201003 | Asphalt resurfacing of approximately 2.4 miles of South Columbus Street. | Pavement Improvement | 2009-09-04 |  |  | 2009-11-11 | 469572.54 | 2.390
12233 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | KLICKITAT |  | 03 | M201002 | Asphalt resurfacing of approximately 1.6 miles of Bickleton Highway. | Pavement Improvement | 2009-09-04 |  |  | 2009-11-11 | 255000 | 1.580
12234 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | P130002 | Construction of a new concrete bridge. | Bridge Replacement | 2009-11-16 |  |  | 2010-04-01 | 750000 | 0.120
12235 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | GRANT |  | 04 | P137001 | Asphalt resurfacing of approximately 2.0 miles of L-NE Road from Kittleson to 3-NE Road. | Pavement Improvement | 2009-07-06 |  | 2009-07-28 | 2009-07-28 | 487009 | 2.010
12236 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | P368001 | Constructs approximately 0.1 miles of new roadway to provide an improved roadway connector between State Route 543 and the commercial and industrial areas. | New Construction | 2009-08-21 |  |  | 2010-03-21 | 348000 | 0.133
12237 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | JEFFERSON |  | 06 | Q161007 | Asphalt resurfacing of approximately 2.0 miles of Center Road. | Pavement Improvement | 2009-07-20 |  | 2009-08-07 | 2009-08-07 | 358000 | 2.000
12238 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | WHATCOM |  | 02 | T371008 | Replace the existing bridge on Hannegan Road over Scott Ditch, south of Lynden, Washington. | Bridge Replacement | 2009-08-03 |  |  | 2009-11-06 | 600000 | 0.050
12239 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | COWLITZ |  | 03 | X085001 | Reconstruct roadway to include curb, gutter and sidewalk. Includes channelization improvements to the existing intersection with State Route 504. | Pavement Widening | 2009-07-14 |  |  | 2010-09-13 | 330000 | 0.730
12240 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | LEWIS |  | 03 | Y210001 | Reconstruction and asphalt resurfacing of approximately 2.3 miles of Davis Lake Road. | Pavement Improvement | 2009-07-09 |  | 2009-09-15 | 2009-09-15 | 1027000 | 2.290
12241 | Completed | C250 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE |  | 05 | Y329008 | Reconstruction of Crawford Avenue, including the installation of a roundabout, curb and gutter, sidewalk, and stormwater drainage system. | Pavement Improvement | 2009-05-11 |  | 2009-09-15 | 2009-09-15 | 1674431 | 0.610
12242 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | FERRY |  | 05 | Z910001 | Installation of new guardrail or repairs to existing damaged guardrail on Inchelium Highway and West Curlew Lake Road. | Safety/Traffic Management | 2011-04-11 |  |  | 2011-05-11 | 332244 | 8.040
12243 | Completed | C200 | Highway Infrastructure Investment Grant | WASHINGTON | MASON |  | 06 | Z923001 | Install solar street lights at intersections within Mason County. | Safety/Traffic Management | 2010-03-18 |  |  | 2010-06-24 | 150000 | 0.000
12244 | Completed | C230 | Highway Infrastructure Investment Grant | WASHINGTON | SPOKANE | SPOKANE | 05 | Z932004 | Arterial Street preservation on N 6th, G, N 2nd, Oakland. Includes asphalt repair and overlay, and sidewalk repair. | Pavement Improvement | 2010-08-02 |  |  | 2010-09-29 | 488374.28 | 1.050
12245 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WASHINGTON | YAKIMA |  | 04 | Z939004 | Asphalt resurfacing of 2nd Street and 3rd Street. Includes replacement of substandard curb, gutter, and sidewalk along 2nd Street, 3rd Street, and Canal Street. | Pavement Improvement | 2009-08-17 |  | 2009-09-24 | 2009-09-24 | 326000 | 0.227
12246 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PLEASANTS |  | 01 | 0002474 | This project will improve safety for motorists by resurfacing 2.72 miles of West Virginia 2 from the City of Waverly to Willow Island Road in Pleasants County. | Pavement Improvement | 2009-04-21 | 2009-05-27 | 2009-10-30 | 2009-07-24 | 777648 | 2.720
12247 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002479 | This project will improve safety for motorists by resurfacing 1.04 miles of West Virginia Route 2 from the Brooke County/Hancock County line to Penn Avenue Road | Pavement Improvement | 2010-02-22 | 2010-04-13 | 2010-06-30 | 2010-06-25 | 537371 | 1.040
12248 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002481 | This project will improve safety for motorists by resurfacing 1.5 miles of deteriorated pavement on West Virginia 2 from the City of Wellsburg to Cross Creek Road in Brooke County. | Pavement Improvement | 2010-02-22 | 2010-05-21 | 2010-06-30 | 2010-06-24 | 554109 | 1.500
12249 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | OHIO | WHEELING (OH) | 01 | 0002482 | This project will improve safety for motorists by resurfacing 0.37 miles of deteriorated pavement on West Virginia 2 at milepoint 0.00 and resurfacing 1.39 miles of West Virginia Route 88 from Peter's | Pavement Improvement | 2010-04-01 | 2010-05-12 | 2010-06-30 | 2010-06-25 | 438630 | 0.370
12250 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002483 | This project will improve safety for motorists by resurfacing 1.31 miles of deteriorated pavement on West Virginia Route 2 from the City of Weirton to Kings Creek Road in Hancock County. | Pavement Improvement | 2009-12-01 | 2010-04-13 | 2010-06-30 | 2010-06-26 | 459308 | 1.310
12251 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HANCOCK | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002484 | This project will improve safety for motorists by resurfacing 1.55 miles of deteriorated pavement on West Virginia Route 2 from the City of New Cumberland to Moscow Road in Hancock County. | Pavement Improvement | 2009-12-01 | 2010-04-23 | 2010-06-30 | 2010-06-25 | 347361 | 1.550
12252 | Underway | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0002487 | This project will extend the life of the historic Ohio River Market Street Bridge by repairing bridge components, replacing the lighting and light fixtures on the bridge, cleaning the structrue and re | Bridge Improvement | 2009-12-10 | 2010-01-11 | 2011-11-30 |  | 14502951 | 0.010
12253 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONROE |  | 03 | 0003216 | This project will improve safety for motorists by resurfacing the deck of the Alderson Bridge with Latex Modified Concrete. The bridge is located on West Virginia Route 3 at approximately milepoint 0. | Bridge Improvement | 2009-05-12 | 2009-08-31 | 2009-10-30 | 2009-11-02 | 435591 | 0.170
12254 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BOONE |  | 03 | 0003217 | This project will improve safety for motorists by resurfacing 1.67 miles of deteriorated pavement and replace the existing guardrails on West Virginia Route 3 from the Big Coal River Bridge to West Vi | Pavement Improvement | 2009-04-28 | 2009-05-05 | 2009-10-30 | 2009-08-11 | 562570 | 1.670
12255 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0003218 | This project will extend the life of two bridges, the County Route 3 Turnpike Overpass Bridge and the Camp Creek Overpass Bridge #2, by cleaning the structures and then painting them. The bridges are | Bridge Improvement | 2009-07-21 | 2009-07-25 | 2009-10-15 | 2009-09-03 | 372956 | 0.070
12256 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | SUMMERS |  | 03 | 0003220 | This project will improve safety for motorists by resurfacing 1.60 miles of WV 3 Summers County between Lowell and Pence Spring Road. | Pavement Improvement | 2010-09-09 | 2010-09-23 | 2010-10-15 | 2010-12-10 | 393348 | 1.600
12257 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TAYLOR |  | 01 | 0003221 | This project will improve safety for motorists by replacing the Berry Run Bridge due to condition. The bridge is located on County Route 3 at approximately milepoint 0.16 in Taylor County. | Bridge Replacement | 2010-01-11 | 2010-03-22 | 2010-07-30 | 2010-07-31 | 368808 | 0.010
12258 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0003222 | This project will improve safety for motorists by the installation of piling for embankment stabilization on West Virginia Route 3 (Metalton Road) at approximately milepoint 29.13 in Raleigh County. | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2009-10-30 | 2009-06-30 | 302026 | 0.010
12259 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BOONE |  | 03 | 0003223 | This project will improve safety for motorists by resurfacing 1.71 miles of WV 3 in Boone County from Drawdy Creek to Peytona. | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-10-15 | 2010-09-02 | 567309 | 1.710
12260 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HARRISON |  | 01 | 0005119 | This project will improve safety for motorists by replacing the Big Arch Bridge due to condition. The bridge is located on County Route 5 at approximately milepoint 2.46 in Harrison County. | Bridge Replacement | 2009-11-13 | 2010-04-22 | 2010-06-30 | 2010-07-19 | 483732 | 0.010
12261 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TAYLOR |  | 01 | 0007219 | This project will improve safety for motorists by replacing the Irontown Girder Bridge due to condition. The bridge is located on County Route 7 at approximately milepoint 3.2 in Taylor County. | Bridge Replacement | 2009-09-21 | 2009-11-11 | 2010-06-30 | 2010-05-26 | 758773 | 0.010
12262 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WIRT |  | 02 | 0007221 | This project will improve safety for motorists by resurfacing 4.36 miles of deteriorated pavement on County Route 7 (Garfield Road) beginning at milepoint 6.10 in Wirt County. | Pavement Improvement | 2009-09-02 | 2009-09-19 | 2009-10-30 | 2009-11-04 | 760846 | 4.360
12263 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0009194 | This project will extend the life of the 4-U Bridge by cleaning and painting the structure. The bridge is located on County Route 9 at approximately milepoint 9.24 in Pendleton County. | Bridge Improvement | 2009-06-08 | 2010-04-12 | 2009-10-15 | 2010-04-21 | 148962 | 0.010
12264 | Underway | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | JEFFERSON |  | 02 | 0009196 | This project will reduce traffic congestion and improve access to the area by the upgrade of the existing West Virginia Route 9 to four lanes and the construction of a new bridge. The project is loca | Pavement Widening | 2009-09-22 | 2009-09-22 | 2011-05-31 |  | 18743700 | 0.270
12265 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HARRISON |  | 01 | 0009197 | This project will improve safety for motorists by replacing the West Robey Arch Bridge due to condition. The bridge is located on County Route 9 at approximately milepoint 6.75 in Harrison County. | Bridge Replacement | 2009-11-12 | 2009-11-17 | 2010-06-30 | 2010-06-01 | 525208 | 0.010
12266 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BARBOUR |  | 01 | 0011124 | This project will improve safety for motorists by resurfacing 4.46 miles of deteriorated pavement on County Route 11 (Audra Park Road) in Barbour County. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2009-10-30 | 2009-09-26 | 468496 | 4.460
12267 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0012048 | This project will improve safety for motorists by replacing the Deer Run Park Bridge due to condition. The bridge is located on County Route 12 at approximately milepoint 4.15 in Pendleton County. | Bridge Replacement | 2009-10-13 | 2010-04-06 | 2010-06-10 | 2010-06-10 | 377860 | 0.010
12268 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TYLER |  | 01 | 0013056 | This project will improve safety for motorists by replacing the Walnut Fork Bridge due to condition. The bridge is located on County Route 13 at approximately milepoint 6.06 in Tyler County. | Bridge Replacement | 2009-08-05 | 2010-03-02 | 2010-07-30 | 2010-06-28 | 495307 | 0.010
12269 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA |  | 02 | 0015078 | This project will improve safety for motorists by replacing the Middle Fork Bridges due to condition. The bridges are located on County Route 15 at approximately milepoint 13.71 in Kanawha County. | Bridge Replacement | 2009-09-18 | 2010-03-02 | 2010-06-30 | 2010-09-11 | 688684 | 0.010
12270 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | DODDRIDGE |  | 01 | 0015079 | This project will improve safety for motorists by replacing Long Run Bridge due to condition. The bridge is located on County Route 15 at approximately milepoint 2.18 in Doddridge County. | Bridge Replacement | 2009-10-09 | 2009-11-02 | 2010-06-30 | 2010-05-19 | 788650 | 0.010
12271 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RITCHIE |  | 01 | 0016205 | This project will improve safety for motorists by resurfacing 3.26 miles of deteriorated pavement on West Virginia 16 from the City of Washburn to Harrisville Road in Ritchie County. | Pavement Improvement | 2009-06-18 | 2009-07-11 | 2009-07-30 | 2009-09-05 | 718511 | 3.260
12272 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CALHOUN |  | 02 | 0016206 | This project will improve safety for motorists by resurfacing 1.31 miles of deteriorated pavement on West Virginia Route 16 from the City of Grantsville to Smithville Road in Calhoun County. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2009-09-11 | 2009-09-03 | 401720 | 1.310
12273 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0016207 | This project will improve safety for motorists by resurfacing 0.47 miles of West Virginia Route 16 from South Oakwood Avenue to Bus Station Road in Beckley, Raleigh County. | Pavement Improvement | 2009-07-10 | 2009-07-20 | 2009-10-30 | 2009-10-08 | 516059 | 0.470
12274 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CLAY |  | 02 | 0016210 | This project will improve safety for motorists by resurfacing 7.63 miles of WV 16 from Lizemore to Clay RD in Clay County. | Pavement Improvement | 2010-09-15 | 2010-10-14 | 2010-10-15 | 2010-11-14 | 1509879 | 7.630
12275 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | STATEWIDE |  |  | 0016215 | This project will improve safety for motorists by the installation or replacement of guardrail along West Virginina Route 16 in Fayette County. | Safety/Traffic Management | 2010-10-19 | 2010-11-08 | 2010-10-15 | 2010-11-15 | 79492 | 1.660
12276 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WETZEL |  | 01 | 0017086 | This project will improve safety for motorists by replacing the McBee Bridge due to condition. The bridge is located on County Route 17 at approximately milepoint 3.68 in Wetzel County. | Bridge Replacement | 2009-12-16 | 2009-12-16 | 2010-07-30 | 2010-08-25 | 453800 | 0.010
12277 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TYLER |  | 01 | 0018119 | This project will improve safety for motorists by the installation of piling for embankment stabilization at five locations beginning at milepoint 11.12 and extending 0.50 miles on West Virginia 18 in | Pavement Improvement | 2009-12-01 | 2010-05-11 | 2010-07-30 | 2010-07-30 | 962820 | 0.500
12278 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0019337 | This project will improve safety for motorists by resurfacing the deck of the New River Gorge Bridge located in Fayette County on United States Route 19 at the approximate milepoint 15.37 with Latex M | Bridge Improvement | 2010-04-01 | 2010-04-09 | 2010-06-30 | 2010-08-23 | 918300 | 0.010
12279 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0019338 | This project will improve safety for motorists by resurfacing 1.94 miles of United States Route 19 from the City of Fockler Branch to Muddlety Road in Nicholas County. | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2009-10-30 | 2009-09-02 | 1280685 | 1.940
12280 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | LEWIS |  | 02 | 0019339 | This project will improve safety for motorists by resurfacing 1.89 miles of deteriorated pavement on United States Route 19 in the City of Weston, Lewis County. | Pavement Improvement | 2009-05-22 | 2009-06-29 | 2009-10-30 | 2009-07-08 | 305396 | 1.890
12281 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0019340 | This project will help eliminate congestion by the relocation and upgrade to four lanes of United States Route 19 beginning at approximately milepoint 15.52 and bridge improvements ending at the South | New Construction | 2009-08-20 | 2009-09-18 | 2011-08-30 | 2011-11-19 | 22190000 | 0.890
12282 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0019343 | This project will improve safety for motorists by resurfacing 0.50 miles of deteriorated pavement on United States Route 19 from the City of Prosperity to the Crossroads Mall in Raleigh County. | Pavement Improvement | 2009-09-04 | 2009-09-08 | 2009-10-30 | 2009-10-16 | 347814 | 0.500
12283 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0020254 | This project will improve safety for motorists by replacing the existing and failing piling currently restricting slippage of the embankment on West Virginia Route 20 at approximately milepoint 26.75 | Pavement Improvement | 2009-09-01 | 2009-09-01 | 2009-10-30 | 2009-09-28 | 199389 | 0.010
12284 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | UPSHUR |  | 02 | 0020255 | This project will improve safety for motorists by resurfacing 2.02 miles of West Virginia 20 From the City of French Creek to Adrian Road in Upshur County. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-10-30 | 2009-07-13 | 303578 | 2.020
12285 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0020256 | This project will improve safety for motorists by the construction of a 1.23 mile long truck climbing lane on West Virginia Route 20 in Greenbrier County. | Pavement Widening | 2009-11-25 | 2009-12-10 | 2010-06-30 | 2010-09-24 | 1777724 | 1.230
12286 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HARRISON |  | 01 | 0024033 | This project will improve safety for motorists by the installation or replacement of guardrail along WV Route 24 in Harrison County. | Safety/Traffic Management | 2010-12-13 | 2011-02-01 | 2011-05-31 | 2011-05-31 | 124300 | 2.900
12287 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MASON |  | 02 | 0029022 | This project will improve safety for motorists by replacing the Arlee Slab Bridge due to condition. The bridge is located on County Route 29 at approximately milepoint 5.59 in Mason County. | Bridge Replacement | 2009-07-31 | 2009-11-10 | 2009-10-15 | 2010-05-25 | 294872 | 0.010
12288 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0033320 | This project will improve safety for motorists by resurfacing the deck of the Judy Gap Bridge with Latex Modified Concrete. The bridge is located on United States Route 33 at approximately milepoint 1 | Bridge Improvement | 2009-11-16 | 2010-05-03 | 2010-06-30 | 2010-08-14 | 265575 | 0.050
12289 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | UPSHUR |  | 02 | 0033321 | This project will improve safety for motorists by resurfacing 4.53 miles of United States Route 33 from the City of Buckhannon to Elkins Road in Upshur County. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-10-30 | 2009-08-15 | 1399266 | 4.530
12290 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | JACKSON |  | 02 | 0033322 | This project will improve safety for motorists by resurfacing 4.16 miles of deteriorated pavement on United States Route 33 from the City of Ripley to Frozencamp Road in Jackson County. | Pavement Improvement | 2009-07-01 | 2009-07-11 | 2009-09-01 | 2009-09-14 | 1313998 | 4.160
12291 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 0033323 | This project will improve safety for motorists by resurfacing 1.75 miles of deteriorated pavement, drainage improvements and the construcion of a truck climbing lane on United States Route 33 (Shavers | Pavement Widening | 2010-05-07 | 2010-05-21 | 2010-09-30 | 2010-11-11 | 2753900 | 1.760
12292 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0033327 | This project will improve safety for motorists by replacing the Rough Run Bridge due to condition. The bridge is located on County Route 3/3 at approximately milepoint 0.73 in Pendleton County. | Bridge Replacement | 2009-10-29 | 2010-02-04 | 2010-06-30 | 2010-05-12 | 458264 | 0.010
12293 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RALEIGH |  | 03 | 0034067 | This project will improve safety for motorists by replacing the Horse Creek Bridge #5 due to condition. The bridge is located on County Route 3/4 at approximately milepoint 2.12 in Raleigh County. | Bridge Replacement | 2009-09-16 | 2009-09-17 | 2010-06-30 | 2010-05-07 | 423724 | 0.009
12294 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CLAY |  | 02 | 0036040 | This project will improve safety for motorists by resurfacing 5.24 miles of WV 36 from Wallback to Clay RD in Clay County. | Pavement Improvement | 2010-05-03 | 2010-06-02 | 2010-10-15 | 2010-09-14 | 970792 | 5.240
12295 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WAYNE | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0037028 | This project will improve safety for motorists by the installation of piling for embankment stabilization on West Virginia Route 37 at milepoint 18.64 in Wayne County. | Pavement Improvement | 2009-11-12 | 2009-12-01 | 2010-06-30 | 2009-12-29 | 198991 | 0.030
12296 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0039406 | This project will improve safety for motorists by resurfacing 1.29 miles of deteriorated pavement on West Virginia 39 (Deer Creek Road) beginning at approximately milepoint 35.12 in Nicholas County. | Pavement Improvement | 2009-05-29 | 2009-06-26 | 2009-10-30 | 2009-09-03 | 381873 | 1.290
12297 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0041072 | This project will improve safety for motorists by resurfacing 2.10 miles of deteriorated pavement on West Virginia 41 from the City of Glade Creek to Nile Road in Nicholas County. | Pavement Improvement | 2009-10-14 | 2009-10-30 | 2010-05-30 | 2009-11-09 | 479450 | 2.010
12298 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RITCHIE |  | 01 | 0050276 | This project will improve safety for motorists by resurfacing 2.18 miles of deteriorated pavement on United States Route 50 between Nutter Farm and Camp Run Road beginning at approximately milepoint 2 | Pavement Improvement | 2009-04-21 | 2009-06-28 | 2009-09-22 | 2009-09-03 | 944561 | 2.180
12299 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RITCHIE |  | 01 | 0050277 | This project will improve safety for motorists by resurfacing 2.23 miles of deteriorated pavement on United States Route 50 between Camp run Road and Ellenboro Road beginning at approximately milepoin | Pavement Improvement | 2009-04-21 | 2009-07-04 | 2009-09-08 | 2009-08-12 | 965687 | 2.230
12300 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HAMPSHIRE |  | 02 | 0050278 | This project will improve safety for motorists by resurfacing 0.86 miles and the construction of a center turning lane on United States Route 50 at approximately milepoint 8.50 in Hampshire County. | Pavement Improvement | 2009-08-31 | 2009-09-10 | 2010-06-30 | 2010-08-21 | 3693560 | 1.580
12301 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TAYLOR |  | 01 | 0050279 | This project will improve safety for motorists by the construction of a 1.90 mile truck climbing lane and the realignment of a hazardous curve on United States Route 50 beginning at milepoint 3.46 in | Pavement Widening | 2009-06-22 | 2009-08-10 | 2009-10-30 | 2009-11-24 | 2335685 | 1.900
12302 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HARRISON |  | 01 | 0050280 | This project will improve safety for motorists by resurfacing 2.68 miles of US 50 in Harrison County. | Pavement Improvement | 2010-04-01 | 2010-06-07 | 2010-10-29 | 2010-10-21 | 2144700 | 2.680
12303 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WAYNE |  | 03 | 0052263 | This project will improve safety for motorists by resurfacing 2.29 miles of United States Route 52 from the City of Stonecoal to the Mingo County line in Wayne County. | Pavement Improvement | 2009-07-01 | 2009-07-08 | 2009-10-30 | 2009-11-01 | 1415888 | 2.290
12304 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0052264 | This project will improve safety for motorists by resurfacing 1.50 miles of deteriorated pavement on United States Route 52 from the City of Pinnacle Rock to Lorton Lick Road in Mercer County. | Pavement Improvement | 2009-05-20 | 2009-06-11 | 2009-10-30 | 2009-08-31 | 612479 | 1.500
12305 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WAYNE | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0052265 | This project will improve safety for motorists by resurfacing 5.42 miles of United States Route 52 from West Virginia Route 75 to Whites Creek Road in Wayne County. | Pavement Improvement | 2009-08-17 | 2009-08-24 | 2009-10-30 | 2009-10-02 | 774766 | 6.420
12306 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0052270 | This project will extend the life of the Tunnel Overpass Bridge by cleaning and repainting the structure. The bridge is located on United States Route 52 at approximately milepoint 18.67 in Mercer Cou | Bridge Improvement | 2009-07-21 | 2009-08-24 | 2009-10-15 | 2009-09-22 | 280483 | 0.040
12307 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0052271 | This project will extend the life of the Madison Avenue Overpass Bridge by cleaning the structure and repainting it. The bridge is located at Milepoint 0.73 on West Virginia Route 52 in Cabell County. | Bridge Improvement | 2009-09-16 | 2009-11-14 | 2009-10-15 | 2009-12-24 | 173200 | 0.010
12308 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0060252 | This project will improve safety for motorists by replacing the existing and failing piling currently restricting slippage of the embankment on United States Route 60 at milepoint 14.60 in Fayette Cou | Pavement Improvement | 2009-07-23 | 2009-08-25 | 2009-10-30 | 2009-10-04 | 156041 | 0.010
12309 | Underway | C220,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 0060262 | Mill, pave, and construct bike lanes, EB and WB, for 11.0 miles from WV 817 to the mound in South Charleston, Kanawha County. | Transportation Enhancements | 2011-08-25 | 2011-09-06 | 2011-10-21 |  | 2056846 | 11.000
12310 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0061065 | This project will improve safety for motorists by resurfacing 1.24 miles of deteriorated pavement on West Virginia Route 61 from the City of Kincaid to Page Road in Fayette County. | Pavement Improvement | 2009-05-20 | 2009-07-07 | 2009-10-30 | 2009-09-03 | 357966 | 1.240
12311 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0061066 | This project will improve safety for motorists by resurfacing 0.95 miles of deteriorated pavement on West Virginia Route 61 (Ingram Branch Road) in Fayette County. | Pavement Improvement | 2009-06-23 | 2009-07-10 | 2009-10-30 | 2009-08-31 | 314912 | 0.950
12312 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 0062832 | This project will improve safety for motorists by replacing the Lower Mingo Bridge due to condition. The bridge is located on County Route 62 at approximately milepoint 0.08 in Randolph County. | Bridge Replacement | 2009-10-29 | 2010-05-06 | 2010-06-30 | 2010-07-22 | 499272 | 0.010
12313 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 0067005 | This project will improve safety for motorists by resurfacing 4.07 miles of detiorated pavement on West Virginia Route 67 from the City of Wellsburg to Bethany Road in Brooke County. | Pavement Improvement | 2010-02-22 | 2010-04-09 | 2010-06-30 | 2010-06-08 | 723023 | 4.070
12314 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PRESTON |  | 01 | 0068135 | This project will improve safety for motorists by resurfacing the deck of the Laurel Run Bridges (West bound & East bound) with Latex Modified Concrete. The bridge is located on Interstate 68 at appro | Bridge Improvement | 2009-12-07 | 2010-04-05 | 2010-07-30 | 2010-06-30 | 649114 | 0.010
12315 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0068137 | This project will improve safety for motorists by resurfacing 2.20 miles of deteriorated pavement on Interstate 68 from the City of Pierpont to the West end of the Cheat Lake Bridge in Monongalia Coun | Pavement Improvement | 2009-07-21 | 2009-07-23 | 2009-10-30 | 2009-10-06 | 1196116 | 2.200
12316 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WOOD | PARKERSBURG (OH) | 01 | 0068138 | This project will improve safety for motorists by resurfacing 4.05 miles of deteriorated pavement on West Virginia 68 from the City of Belleville to Lubeck Road in Wood County. | Pavement Improvement | 2011-03-21 | 2011-04-04 | 2011-06-30 | 2011-06-14 | 769000 | 4.050
12317 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0068139 | This project will extend the life of the Cheat Lake Bridge by cleaning and repainting the structure. The bridge is located on Interstate 68 at approximately milepoint 9.39 in Monongalia County. | Bridge Improvement | 2009-07-06 | 2010-03-26 | 2010-10-15 | 2010-10-15 | 6155000 | 0.020
12318 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | OHIO | WHEELING (OH) | 01 | 0070158 | This project will improve safety for motorists by replacement of the existing bridge approach slabs, concrete repairs and drainage improvements on Interstate 70 beginning at the West Virginia/Ohio sta | Pavement Improvement | 2009-05-27 | 2009-05-27 | 2009-10-30 | 2009-11-01 | 3290360 | 0.050
12319 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MARSHALL | WHEELING (OH) | 01 | 0074051 | This project will improve safety for motorists by replacing the Shepherd Bridge due to condition. The bridge is located on County Route 74 at approximately milepoint 16.8 in Marshall County. | Bridge Replacement | 2009-05-28 | 2009-05-28 | 2010-05-28 | 2010-07-29 | 1439231 | 0.050
12320 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MCDOWELL |  | 03 | 0080032 | This project will improve safety for motorists by resurfacing 2.00 miles of West Virginia Route 80 from the City of Beartown to Iaeger Road in McDowell County. | Pavement Improvement | 2009-05-01 | 2009-05-15 | 2009-10-30 | 2009-08-12 | 599234 | 2.000
12321 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 0082013 | This project will improve safety for motorists by resurfacing 2.20 miles of WV 82 in Webster County between Birch River and Boggs Road. | Pavement Improvement | 2010-03-30 | 2010-07-03 | 2010-10-15 | 2010-08-13 | 324596 | 2.200
12322 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 0094168 | This project will improve safety for motorists by resurfacing 5.52 miles of West Virginia Route 94 beginning at approximately milepoint 1.48 from the City of Hernshaw to the City of Marmet in Kanawha | Pavement Improvement | 2009-05-01 | 2009-05-11 | 2009-10-30 | 2009-08-31 | 2051683 | 5.520
12323 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WYOMING |  | 03 | 0097084 | This project will improve safety for motorists by resurfacing 2.0 miles of WV 97 on Rockhouse Mountain Road in Wyoming County. | Pavement Improvement | 2010-07-22 | 2010-08-02 | 2010-10-15 | 2011-04-11 | 511966 | 2.000
12324 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0099099 | This project will improve safety for motorists by replacing the Sinking Creek Bridge due to condition. The bridge is located on County Route 9/9 in Greenbrier County. | Bridge Replacement | 2009-09-30 | 2009-12-01 | 2010-06-30 | 2010-01-18 | 224288 | 0.010
12325 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0109013 | This project will help eliminate congestion and help in the movement of motorists and commerce by the construction of 0.14 miles of four lane highway, an interstate ramp, a box culvert and constructio | New Construction | 2009-07-21 | 2009-08-12 | 2010-10-29 | 2011-06-29 | 13378800 | 0.140
12326 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | LINCOLN |  | 03 | 0119339 | This project will extend the life of the Little Coal River Bridges (North & South) by cleaning and repainting the structure. The bridges are located on United States Route 119 at approximately milepoi | Bridge Improvement | 2009-09-16 | 2009-09-12 | 2009-10-15 | 2009-10-26 | 711741 | 0.039
12327 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MINGO |  | 03 | 0119341 | This project will improve safety for motorists by resurfacing 4.26 miles of US 119 between Miller Creek and Belo in Mingo County. | Pavement Improvement | 2010-04-13 | 2010-09-01 | 2010-10-15 | 2010-10-01 | 2233342 | 4.260
12328 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 0119342 | This project will improve safety for motorists by resurfacing 2.54 miles of deteriorated pavement on United States Route 119 beginning approximately at milepoint 39.13 in Kanawha County. | Pavement Improvement | 2009-09-30 | 2010-05-03 | 2010-05-28 | 2010-05-27 | 642366 | 2.540
12329 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MINGO |  | 03 | 0119344 | This project will improve safety for motorists by resurfacing the deck of the West Belo Bridge with Latex Modified Concrete. The bridge is located on United States Route 119 at approximately milepoint | Bridge Improvement | 2009-07-15 | 2009-08-11 | 2009-10-30 | 2009-10-20 | 394401 | 0.050
12330 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | ROANE |  | 02 | 0119354 | This project will improve safety for motorists by the installation or replacement of guardrail along US Route 119 in Walton, Roane County. | Safety/Traffic Management | 2011-02-11 | 2011-04-11 | 2011-05-31 | 2011-04-14 | 44000 | 0.740
12331 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0206002 | This project will improve safety for motorists by replacing the Greenbrier Avenue Bridge due to condition. The bridge is located on County Route 20/6 in Rainelle, Greenbrier County. | Bridge Replacement | 2009-07-09 | 2009-07-20 | 2009-11-06 | 2009-10-06 | 480894 | 0.040
12332 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 0219299 | This project will improve safety for motorists by replacing the Jones Run Bridge due to condition. The bridge is located on United States Route 219 at approximately milepoint 28.50 in Randolph County. | Bridge Replacement | 2009-07-15 | 2009-08-19 | 2010-09-10 | 2010-08-03 | 868138 | 0.010
12333 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONROE |  | 03 | 0219300 | This project will improve safety for motorists by resurfacing 2.34 miles of deteriorated pavement on United States Route 219 beginning at approximately milepoint 0.50 in Peterstown, Monroe County. | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-10-30 | 2009-08-21 | 729612 | 2.340
12334 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | TUCKER |  | 01 | 0219302 | This project will improve safety for motorists by resurfacing 1.20 miles of deteriorated pavement on United States Route 219 from the City of Parsons to Mackeyville Road in Tucker County. | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2010-05-28 | 2009-12-09 | 785610 | 1.200
12335 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 0219303 | This project will improve safety for motorists by resurfacing 1.20 miles of deteriorated pavement on United States Route 219, construction of turning lanes and the improvement of drainage from the Cit | Pavement Widening | 2009-07-14 | 2009-07-30 | 2009-10-30 | 2009-11-20 | 1454253 | 1.200
12336 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PENDLETON |  | 02 | 0220182 | This project will improve safety for motorists by the installation of piling on United States Route 220 at approximately milepoint 13.30 between Smith Creek and Franklin Road for embankment stabilizat | Pavement Improvement | 2009-04-13 | 2009-05-21 | 2009-10-30 | 2010-01-20 | 995631 | 0.180
12337 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MINERAL |  | 01 | 0220183 | This project will improve safety for motorists by resurfacing 0.87 miles of deteriorated pavement on United States Route 220 beginning at approximately milepoint 13.96 in Mineral County. | Pavement Improvement | 2009-07-29 | 2009-08-18 | 2009-10-30 | 2009-12-21 | 927632 | 0.970
12338 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONROE |  | 03 | 0238046 | This project will improve safety for motorists by replacing the Indian Creek Bridge due to condition. The bridge is located at approximately milepoint 1.93 on County Route 23/8 in Monroe County. | Bridge Replacement | 2009-11-06 | 2009-11-16 | 2010-06-30 | 2010-07-12 | 616546 | 0.010
12339 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WETZEL |  | 01 | 0250169 | This project will improve safety for motorists by resurfacing 4.47 miles of deteriorated pavement on United States Route 250 between Mannington, West Virginia and Hundred, West Virginia beginning at m | Pavement Improvement | 2010-08-05 | 2010-08-09 | 2010-10-29 | 2010-10-01 | 1819437 | 4.470
12340 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MARSHALL | WHEELING (OH) | 01 | 0250183 | This project will improve safety for motorists by resurfacing the deck of the Bellaire Interchange Bridge with Latex Modified Concrete. The bridge is located on United States Route 250 at approximatel | Bridge Improvement | 2009-07-27 | 2009-10-06 | 2010-06-30 | 2009-12-04 | 468970 | 0.010
12341 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MARSHALL | WHEELING (OH) | 01 | 0250184 | This project will improve safety for motorists by resurfacing 5.44 miles of deteriorated pavement on United States Route 250 in the City of McMechen, Marshall County. | Pavement Improvement | 2009-05-06 | 2009-05-06 | 2009-10-30 | 2009-11-06 | 4459333 | 5.440
12342 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 0271001 | This project will improve safety for motorists by replacing the Eden's Fork Pony Truss Bridge due to condition. The bridge is located on County Route 27/1 at approximately milepoint 1.1 in Kanawha Cou | Bridge Replacement | 2009-08-14 | 2009-09-18 | 2010-04-06 | 2010-06-25 | 951180 | 0.030
12343 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0385005 | This project will improve safety for motorists by replacing the Jug Neck Bridge due to condition. The bridge is located on County Route 38/5 at approximately milepoint 0.85 in Mercer County. | Bridge Replacement | 2009-07-24 | 2009-08-04 | 2009-11-06 | 2010-03-29 | 413185 | 0.010
12344 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0385006 | This project will improve safety for motorists by replacing the Blake Bridge due to condition. The bridge is located on County Route 38/5 at approximately milepoint 4.00 in Mercer County. | Bridge Replacement | 2009-08-07 | 2009-08-07 | 2009-11-06 | 2010-03-09 | 406947 | 0.010
12345 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WAYNE |  | 03 | 0411002 | This project will improve safety for motorists by replacing the Turkey Creek Pony Truss Bridge downstream due to condition. The bridge is located on County Route 41/1 at approximately milepoint 0.01 i | Bridge Replacement | 2009-12-11 | 2009-12-07 | 2010-08-31 | 2010-08-24 | 916170 | 0.010
12346 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0460038 | This project will improve safety for motorists by resurfacing the deck of both the East bound and West bound Oakvale Bridges with Latex Modified Concrete. The bridges are located on United States Rou | Bridge Improvement | 2009-06-04 | 2009-06-18 | 2009-10-30 | 2009-09-13 | 874619 | 0.100
12347 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0460039 | This project will improve safety for motorists by resurfacing 1.67 miles of deteriorated pavement on United States Route 460 beginning at approximately milepoint 4.29 in Bluefield, Mercer County. | Pavement Improvement | 2009-04-13 | 2009-04-20 | 2009-07-27 | 2009-08-07 | 1407164 | 1.670
12348 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0641332 | This project will improve safety for motorists by resurfacing the deck of three Cabell County bridges, Cedar Crest Bridge and both County Route 26 overpass bridges (East & West), with Latex Modified C | Bridge Improvement | 2009-07-15 | 2010-03-29 | 2010-05-28 | 2010-05-18 | 744252 | 5.140
12349 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 03 | 0641334 | This project will improve safety for motorists by resurfacing 1.59 miles of deteriorated pavement on Interstate 64 from the City of Milton to County Route 60/19 in Cabell County. | Pavement Improvement | 2009-06-16 | 2009-06-24 | 2009-10-30 | 2009-09-11 | 978112 | 1.560
12350 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PUTNAM | HUNTINGTON-ASHLAND (KY-OH) | 02 | 0641335 | This project will improve safety for motorists by resurfacing 4.67 miles of deteriorated pavement on Interstate 64 from the Hurricane Interchange to the Winfield Interchange in Putnam County. | Pavement Improvement | 2009-10-02 | 2009-10-12 | 2010-06-15 | 2010-06-18 | 7416150 | 4.670
12351 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0644170 | This project will extend the life of the Mountain Avenue Bridges (North & South) by cleaning the structure and repainting it. The bridges are located at approximately milepoint 179.36 of Interstate 64 | Bridge Improvement | 2009-08-26 | 2009-09-16 | 2009-10-30 | 2009-11-12 | 603606 | 0.179
12352 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0644171 | This project will improve safety for motorists by resurfacing 1.50 miles of deteriorated pavement on Interstate 64 at approximately milepoint 174.61 in Greenbrier County. | Pavement Improvement | 2009-05-15 | 2010-04-05 | 2009-10-30 | 2010-05-20 | 2484207 | 1.500
12353 | Completed | C250 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 0644172 | This project will improve safety for motorists by resurfacing 1.00 miles of deteriorated pavement on Interstate 64 at approximately milepoint 160.00 in Greenbrier County. | Pavement Improvement | 2009-05-15 | 2009-05-27 | 2009-10-30 | 2009-08-28 | 1391579 | 1.000
12354 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0705011 | This project will improve safety for motorists by resurfacing 1.00 miles of deteriorated pavement on West Virginia Route 705 beginning approximately at milepoint 2.55 in Morgantown, Monongalia County. | Pavement Improvement | 2009-09-09 | 2009-09-14 | 2010-05-28 | 2009-10-22 | 1729738 | 1.000
12355 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 0771061 | This project will improve safety for motorists by resurfacing 2.03 miles of deteriorated pavement on Interstate 77 from the City of Ingleside to Princeton Road in Mercer County. | Pavement Improvement | 2010-09-23 | 2010-09-27 |  | 2010-10-20 | 1600911 | 2.003
12356 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 0772083 | This project will improve safety for motorists by the installation of movable barriers at various locations on the West Virginia Turnpike to allow for the opening of lanes, movement of traffic, etc. d | Safety/Traffic Management | 2010-01-29 | 2010-02-01 | 2010-05-14 | 2010-07-30 | 844612 | 6.000
12357 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WOOD | PARKERSBURG (OH) | 01 | 0773399 | This project will improve safety for motorists by resurfacing the decks of four bridges, the County Route 25 Overpass Bridges (North and South), Wolf Run Overpass and the Buck Run Overpass, with Latex | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2010-05-28 | 2010-09-08 | 1227570 | 0.010
12358 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WOOD | PARKERSBURG (OH) | 01 | 0773402 | This project will improve safety for motorists by resurfacing the decks of five bridges, the Interstate 77/United States Route 50 Interchange Bridge, Worthington Creek Bridge, West Virginia Route 31 O | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2010-06-18 | 2010-08-11 | 1167014 | 9.450
12359 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | LEWIS |  | 02 | 0792156 | This project will improve safety for motorists by resurfacing two bridges, Stone Coal Creek Bridge and the County Route 14 Overpass Bridge, on Interstate 79 in Lewis County. | Bridge Improvement | 2009-08-05 | 2010-03-04 | 2009-10-30 | 2010-08-13 | 1160815 | 0.109
12360 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BRAXTON |  | 02 | 0792158 | This project will improve safety for motorists by resurfacing the deck of three bridges, the Little Kanawha River Bridge and the Oil Creek Bridges (North & South) on Interstate 79 in Braxton County wi | Bridge Improvement | 2009-08-05 | 2010-03-09 | 2010-01-28 | 2010-07-30 | 1917146 | 0.439
12361 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | ROANE |  | 02 | 0792160 | This project will improve safety for motorists by resurfacing the deck of the Wallback Interchange Bridge with Latex Modified Concrete. The bridge is located on Interstate 79 at approximately milepoin | Bridge Improvement | 2010-03-10 | 2010-04-28 | 2010-06-30 | 2010-07-02 | 565896 | 0.059
12362 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BRAXTON |  | 02 | 0792161 | This project will extend the life of the Kenton Meadows Senior Bridges (North & South) by cleaning the structures and repainting them. The bridges are located on Interstate 79 at approximately milepoi | Bridge Improvement | 2010-04-15 | 2010-04-22 | 2010-07-30 | 2010-09-22 | 1194582 | 0.280
12363 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | ROANE |  | 02 | 0792162 | This project will extend the life of the Amma/Big Sandy Bridges (North & South) by cleaning and painting the structures. The bridges are located on Interstate 79 at approximately milepoint 25.79 in Ro | Bridge Improvement | 2009-06-29 | 2009-07-22 | 2009-09-18 | 2009-09-28 | 906542 | 0.180
12364 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BRAXTON |  | 02 | 0792164 | This project will improve safety for motorists by resurfacing 6.99 iles of detiorated pavement, installation of raised pavement markers, guardrail repair/replacement and shoulder pavement/reconstuctio | Pavement Improvement | 2009-07-13 | 2009-07-27 | 2009-10-30 | 2009-09-04 | 2940001 | 6.990
12365 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BRAXTON |  | 02 | 0792167 | This project will extend the life of the Saltlick Creek Bridges (North & South) by cleaning the structures and repainting them. The bridges are located on Interstate 79 at approximately milepoint 78.1 | Bridge Improvement | 2009-09-16 | 2009-09-18 | 2010-10-15 | 2009-11-04 | 638466 | 0.119
12366 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | ROANE |  | 02 | 0792168 | This project will improve Safety for motorists by resurfacing 4.49 miles of deteriorated pavement on Interstate 79 between the City of Amma and Wallback Road in Roane County. | Pavement Improvement | 2009-05-11 | 2009-06-08 | 2009-10-30 | 2009-09-02 | 3009576 | 4.490
12367 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 0793222 | This project will improve safety for motorists by resurfacing the deck of the Westover Bridge with Latex Modified Concrete. The bridge is located on Interstate 79 at approximately milepoint 152.53 in | Bridge Improvement | 2009-10-13 | 2010-04-05 | 2010-06-30 | 2010-08-10 | 992400 | 0.480
12368 | Completed | C200 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MARION |  | 01 | 0793223 | This project will improve safety for motorists by resurfacing 2.19 miles of deteriorated pavement on Interstate 79 beginning at approximately milepoint 136.68 in Fairmont, Marion County. | Pavement Improvement | 2009-04-16 | 2009-04-17 | 2009-10-30 | 2009-07-22 | 1245675 | 2.190
12369 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BERKELEY | HAGERSTOWN | 02 | 0811104 | This project will improve safety for motorists by resurfacing 4.65 miles of deteriorated pavement on Interstate 81 from Falling Waters to the Maryland/West Virginia State line in Berkeley County. | Pavement Improvement | 2009-07-01 | 2009-07-12 | 2009-10-30 | 2009-10-06 | 2175312 | 4.650
12370 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BERKELEY | HAGERSTOWN | 02 | 0811105 | This project will improve safety for motorists by resurfacing 4.27 miles of deteriorated pavement on Interstate 81 from the Virginia/West Virginia State Line to Inwood Road, in Berkely County. | Pavement Improvement | 2009-07-01 | 2009-08-11 | 2009-10-30 | 2009-10-30 | 1633604 | 4.270
12371 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | LEWIS |  | 02 | 1191007 | This project will improve safety for motorists by replacing the Sleeths Run Truss Bridge due to condition. The bridge is located on US Route 119 at approximately milepoint 0.09 in Lewis County. | Bridge Replacement | 2009-07-17 | 2009-07-30 | 2010-08-30 | 2010-07-21 | 1279500 | 0.020
12372 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 1601001 | This project will improve safety for motorists by replacing the Michigan Avenue Bridge due to condition. The bridge is located at approximately milepoint 0.01 of County Route 160/17 in Fayette County. | Bridge Replacement | 2009-08-21 | 2009-08-21 | 2010-04-06 | 2011-03-03 | 660010 | 0.010
12373 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MCDOWELL |  | 03 | 1659001 | This project will improve safety for motorists by replacing the South Roselawn Street Bridge on County Route 16/59 at approximately milepoint 0.01 in McDowell County. | Bridge Replacement | 2009-11-02 | 2010-03-01 | 2010-05-28 | 2010-05-28 | 406996 | 0.010
12374 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | NICHOLAS |  | 03 | 1919002 | This project will improve safety for motorists by replacing the Peters Creek Bridge due to condition. The bridge is located on County Route 19/19 at approximately milepoint 0.03 in Nicholas County. | Bridge Replacement | 2009-08-27 | 2010-03-15 | 2010-11-30 | 2010-06-22 | 422568 | 0.001
12375 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BRAXTON |  | 02 | 1940005 | This project will improve safety for motorists by the replacement, repair or installation of guardrail 1.74 miles along CR 19/40 in Little Birch, Braxton County. | Safety/Traffic Management | 2011-01-20 | 2011-03-28 | 2011-05-31 | 2011-04-06 | 83750 | 1.740
12376 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MINERAL |  | 01 | 2009169 | Continuation of rail trail development. Project elements include developing trail from Knobley Tunnel across the Potomac River Bridge to link to the C&O National Park Towpath hiking trail in Mineral C | Transportation Enhancements | 2010-09-24 | 2010-09-24 | 2010-10-29 |  | 167100 | 0.000
12377 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MONONGALIA |  | 01 | 2009170 | Construction/reconstruction of sidewalks, curbs and gutters along Main Street (West Virginia Route 100) from Dent's Run Bridge to Everly Street in Granville, Monongalia County. Project elements inclu | Transportation Enhancements | 2010-06-02 | 2010-07-06 | 2010-09-30 |  | 617900 | 0.000
12378 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | PLEASANTS |  | 01 | 2009172 | Reconstruction of sidewalks and curbing, installation of lighting , and minor drainage along Washington Street from WV 2 to Second Street in St. Marys, Pleasants County. | Transportation Enhancements | 2010-06-22 | 2010-10-03 | 2010-09-30 |  | 152900 | 0.000
12379 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | BROOKE | STEUBENVILLE-WEIRTON (OH-PA) | 01 | 2009174 | Sidewalk construction, installation of decorative and historic brick pavers and curbing at various intersections along Charles Street, 22nd and 23rd Streets at their intersections with Pleasant Avenue | Transportation Enhancements | 2010-06-17 | 2010-07-14 | 2010-09-30 |  | 135300 | 0.000
12380 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | HARRISON |  | 01 | 2009175 | Reconstruction of sidewalks on Traders Avenue, Library Lane and South 2nd Street; installation of lighting, pedestrian amenities, landscaping and minor drainage in Clarksburg, Harrison County. | Transportation Enhancements | 2010-07-09 | 2010-08-11 | 2010-09-30 |  | 425721 | 0.000
12381 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | JEFFERSON | HAGERSTOWN | 02 | 2009177 | Construction of sidewalks, curbs and gutters and minor drainage from Harpers Ferry Middle School to the Bolivar-Harpers Ferry Public Library in Jefferson County. | Transportation Enhancements | 2010-08-27 | 2010-09-07 | 2010-09-30 | 2010-10-01 | 139000 | 0.000
12382 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 2009178 | Construction of sidewalks, curbs and gutters, crosswalks, lighting, landscaping and utility relocation as well as other pedestrian amenities from Beatrice Street to Hunt Avenue in Charleston, Kanawha | Transportation Enhancements | 2010-11-18 | 2012-01-20 | 2012-06-29 | 2012-06-29 | 200200
12383 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | RANDOLPH |  | 02 | 2009179 | Improvement of pedestrian and community access for two sites on the Davis & Elkins College campus in Randolph County including construction of sidewalks, curbing, minor drainage, new signage, seating, | Transportation Enhancements | 2010-08-17 | 2008-09-03 | 2010-10-29 |  | 365400 | 0.000
12384 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | KANAWHA | CHARLESTON | 02 | 2009180 | Construction of sidewalks, curb cuts and crosswalks beginning at the intersection of Martins Branch Road (CO 622) proceeding north on the west dise of CO 21 to Tinny Lane (CO 622/38) in Sissonville, K | Transportation Enhancements | 2010-05-21 | 2010-06-04 | 2010-09-30 | 2010-08-09 | 171100 | 0.000
12385 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | ROANE |  | 02 | 2009182 | Construction of sidewalks, crosswalks, curbing, lighting and minor drainage along Main Street from the intersection of US 33/US 119 to Court Street; Market Street from Court Street and along US 33 wes | Transportation Enhancements | 2010-06-22 | 2010-08-18 | 2010-09-30 | 2010-10-07 | 84200 | 0.000
12386 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | MERCER |  | 03 | 2009184 | Reconstruction of sidewalks, curbs and gutters, and minor drainage along Mercer Street between Douglas Street and Main Street and on East Main Street between Ingleside Road and North Walker Street in | Transportation Enhancements | 2010-08-02 | 2010-08-02 | 2010-09-30 | 2010-10-29 | 252700 | 0.000
12387 | Underway | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 2009185 | Design and construction of rail trail segments beginning near the Holiday Inn Hotel and extending north past Allman Street to Summerlee Road; and beginning at Jones Avenue and extending south toward C | Transportation Enhancements | 2011-04-19 | 2011-04-19 | 2011-01-28 |  | 429800 | 0.000
12388 | Completed | C220,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 2009186 | Construction of sidewalks, curbs and gutters, minor drainage, signage, lighting, pedestrian amenities, and landscaping along US 219 and Frankford Road in Roncerverte, Greenbrier County. | Transportation Enhancements | 2010-05-26 | 2010-08-16 | 2010-09-30 | 2010-11-19 | 391961 | 0.000
12389 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 2009187 | Reconstruction of sidewalks, curbs and gutters, minor drainage, and pedestrian lighting along both sides of Main Street in Mount Hope, Fayette County. | Transportation Enhancements | 2010-05-26 | 2010-08-04 | 2010-09-30 | 2010-09-16 | 209800 | 0.000
12390 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | CABELL | HUNTINGTON-ASHLAND (KY-OH) | 03 | 2009189 | Construction of pedestrian corridor between 10th Street and 11th Street connecting Huntington's Visitor's Center to Pullman Square in Cabell County. Project includes sidewalks, curbs and gutters, min | Transportation Enhancements | 2010-05-25 | 2010-07-30 | 2010-09-30 | 2010-09-30 | 204751 | 0.000
12391 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | GREENBRIER |  | 03 | 2009190 | construction of sidewalks, curb and gutters, lighting, signage, landscaping, pedestrian amenities, and minor drainage along Chestnut, Locust, Sewell, First, Second and Third Streets in Rainelle, Green | Transportation Enhancements | 2010-05-26 | 2010-07-19 | 2010-09-30 | 2010-08-25 | 145500 | 0.000
12392 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WEBSTER |  | 03 | 2009192 | Construction of ADA compliant walking trail and minor drainage improvements to connect the facilities on the island to the facilities at Bakers Island in Webster Springs, Webster County. | Transportation Enhancements | 2010-06-03 | 2010-08-16 | 2010-09-30 | 2010-09-10 | 55478 | 0.000
12393 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | FAYETTE |  | 03 | 2009194 | Installation of fencing, railing and new caging system. Reconstruction of ADA compliant pedestrian approaches, landscaping, pedestrian amenities, lighting,signage, minor bridge repairs and cleaning a | Bridge Improvement | 2010-07-22 | 2010-08-10 | 2010-09-30 | 2010-10-29 | 431973 | 0.000
12394 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | STATEWIDE |  |  | 2009230 | This project will improve safety for motorists by the installation of Dynamic Message Signs and Closed Circuit Television connections along the West Virginia Turnpike for messaging and monitoring by t | Safety/Traffic Management | 2010-07-23 | 2010-08-02 | 2010-12-10 | 2010-12-01 | 5323100 | 0.000
12395 | Completed | C240 | Highway Infrastructure Investment Grant | WEST VIRGINIA | OHIO | WHEELING (OH) | 01 | 2009232 | This project will improve safety for motorists by the installation or replacement of guardrail in various locations throughout WVDOH District 6 area. | Safety/Traffic Management | 2010-06-01 | 2010-07-13 | 2010-11-15 | 2010-07-27 | 111001 | 0.000
12396 | Underway | C490 | OJT/SS | WEST VIRGINIA | STATEWIDE |  |  | 2009234 | This project will provide highway construction industry skills training, tools/equipment, employment counseling and supplemental services, (i.e., child care, remedial education, transportation) to wom | Other | 2010-06-18 | 2010-06-18 | 2010-11-28 |  | 198353 | 0.000
12397 | Underway | C490 | OJT/SS | WEST VIRGINIA | STATEWIDE |  |  | 2009236 | This project will provide an employment-based skilled trade training program at three sites in West Virgina to increase the number of women entering and remaining in the highway construction workforce | Other | 2010-06-18 | 2010-06-18 | 2010-11-28 |  | 292000 | 0.000
12398 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | JACKSON |  | 02 | 2009238 | Construct ADA compliant ramps along CR 2/19 and CR 33/1 in Ravenswood, Jackson County. | Transportation Enhancements | 2011-01-07 | 2011-05-17 | 2011-06-28 | 2010-06-13 | 75000 | 0.000
12399 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | JACKSON |  | 02 | 2009239 | Construct 6' paved shoulders and 5' sidewalks along WV 68 in Ravenswood, Jackson County. | Transportation Enhancements | 2011-01-07 | 2011-04-20 | 2011-06-28 | 2011-06-18 | 115000 | 0.000
12400 | Completed | C220 | Highway Infrastructure Investment Grant | WEST VIRGINIA | WIRT |  | 02 | 2009240 | Excavate and reconstruct sidewalks along WV 5 from Court Street to Woodyard Street In Elizabeth, Wirt County. | Transportation Enhancements | 2011-01-07 | 2011-06-01 | 2011-06-28 | 2011-06-15 | 85000 | 0.000
12401 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2009242 | This is a bridge replacement project in Portage County on a town road, County Highwy P - Cemetary Road. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-12-11 | 556000 | 0.076
12402 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009244 | This is a bridge replacement project in Wood County on County Highway K, Branch of Mill Creek Crossing. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-11-09 | 277000 | 0.057
12403 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | PRICE |  | 07 | 2009245 | This is a bridge replacement project in Price County on a town road, Holmes Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-28 | 297338.95 | 0.086
12404 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | PRICE |  | 07 | 2009246 | This is a bridge replacement project in Price County on a town road, Douglas Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-28 | 193456.06 | 0.062
12405 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009254 | This is a bridge replacement project in Taylor County on County Highway D, Mondeaux River Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-20 | 488500 | 0.000
12406 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | JEFFERSON |  | 05 | 2009366 | This is a reconstruction project in Jefferson County on State Highway 59, Village of Palmyra, Maple Street. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-30 | 1305000 | 0.850
12407 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | JEFFERSON |  | Multiple | 2009367 | This is a restoration and rehabilitation project in Jefferson County on State Highway 59, Whitewater - Palmyra Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-30 | 1795000 | 67.050
12408 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009368 | This is a bridge rehabilitation project in Dane County on US Highway 151, Sun Prairie Bypass. | Bridge Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-21 | 524210.55 | 0.020
12409 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 02 | 2009369 | This is a reconstruction project in Rock County on State Highway 11, Footville - Janesville Bypass. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-03 | 3132000 | 22.400
12410 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | VERNON |  | 03 | 2009370 | This is a restoration and rehabilitation project in Vernon County on State Highway 82, LaFarge and Otter Creek Briges. | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-10-01 | 2009-11-18 | 832000 | 0.231
12411 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAUK |  | 02 | 2009371 | This is a bridge rehabilitation project in Sauk County on US Highway 12, Lake Delton, Dell Creek Bridge and approaches. | Bridge Improvement | 2009-05-15 | 2009-05-15 | 2010-10-01 | 2011-10-03 | 3038220.19 | 0.133
12412 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009372 | This is a reconstruction project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2010-08-01 | 2010-08-31 | 4626581.72 | 0.610
12413 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009373 | This is a reconstruction project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2010-08-01 | 2010-08-31 | 6024945.95 | 0.610
12414 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009374 | This is a reconstruction with additional lanes project in Racine County on Interstate 94, North South Freeway, County Highway G interchange. | Pavement Widening | 2009-03-30 | 2009-03-30 | 2010-10-01 | 2010-09-30 | 10839551.47 | 0.610
12415 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009375 | This is a fencing project in Racine County on Interstate 94. | Other | 2009-03-30 | 2009-03-30 | 2010-08-01 | 2010-08-31 | 95401.9 | 0.610
12416 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009376 | This is a reconstruction with additional lanes project in Kenosha County on Interstate 94, North-South Freeway, County Highway C Interchange, mainline and ramps. | Pavement Widening | 2009-03-30 | 2009-03-30 | 2010-12-01 | 2010-11-24 | 26523140.6 | 1.080
12417 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009377 | This is a reconstruction with additional lanes project in Kenosha County on Interstatet 94, North - South Freeway, Illinois State Line to County Highway C, mainline. | Pavement Widening | 2009-03-30 | 2009-03-30 | 2010-12-01 | 2010-11-24 | 34193016.87 | 16.500
12418 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009378 | This is a bridge replacement with added lanes project in Kenosha County on Interstate 94, North South Freeway, County Highway C to State Highway 50, mainline. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2010-12-01 | 2010-11-24 | 4932480.82 | 0.660
12419 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUPACA |  | 08 | 2009379 | This is a project in Waupaca County on State Highway 49, City of Waupaca. | Safety/Traffic Management | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-22 | 164374.87 | 0.095
12420 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | LINCOLN |  | 07 | 2009380 | This is a bridge rehabilitation project in Lincoln County on US Highway 51, Merrill - Tomahawk. | Bridge Improvement | 2009-03-30 | 2009-03-30 | 2009-11-01 | 2010-07-02 | 1182735.39 | 0.800
12421 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009381 | This is a resurfacing project in Wood County on State Highway 13, Pittsville - Marshfield. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-12-30 | 2009-10-13 | 818600.13 | 7.614
12422 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009382 | This is a resurfacing project in Marathon County on State Highway 153, Mosinee, Crooked Lake Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-06-01 | 2009-07-09 | 776804.13 | 43.596
12423 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | LANGLADE |  | 08 | 2009383 | This is a restoration and rehabilitation project in Langlade County on State Highway 52, Lily, Forest County Line. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-09-01 | 966000 | 22.160
12424 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ST CROIX |  | 03 | 2009384 | This is a resurfacing project in St. Croix County on State Highway 64, New Richmond, Connorsville Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-09 | 3770387.28 | 50.470
12425 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ST CROIX |  | 03 | 2009385 | This is a project in St. Croix County on State Highway 64, New Richmond, Connorsville Road. | Safety/Traffic Management | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-09 | 400641.47 | 0.180
12426 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2009386 | This is a resurfacing project in Polk County on US Highway 8, St. Croix Falls - Turtle Lake. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-11-06 | 3225447.52 | 74.160
12427 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BURNETT |  | 07 | 2009387 | This is a resurfacing project in Burnett County on State Highway 70, Siren - Spooner. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-22 | 3196143.72 | 132.550
12428 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DUNN |  | 03 | 2009388 | This is a restoration and rehabilitation project in Dunn County on State Highway 25, Menomonie - Wheeler Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-04 | 2153500 | 28.900
12429 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DUNN |  | 03 | 2009389 | This is a resurfacing project in Dunn County on State Highway 64, New Richmond - Bloomer. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-11 | 1718368.73 | 38.880
12430 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009390 | This is a reconstruction project in Dane County on County Highway B, Village of Rockdale. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2010-05-01 | 2010-07-28 | 972530.98 | 0.800
12431 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | LAFAYETTE |  | 03 | 2009391 | This is a bridge replacement project in Lafayette County on County Highway H, Fever River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-12-11 | 643416.39 | 0.145
12432 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2009392 | This is a reconstruction project in Crawford County on a town road, Rush Creek Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-09-24 | 413610.67 | 0.100
12433 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | SAUK |  | 03 | 2009393 | This is a bridge replacement project in Sauk County on County Highway G, Baraboo River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-10-02 | 870000 | 0.280
12434 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 01 | 2009394 | This is a bridge rehabilitation with added lanes project in Waukesha County on local streets, Valentine Road, Bridge over Oconomowoc River. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-11-20 | 228238.14 | 0.000
12435 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009395 | This is a bridge replacement project in Washington County on County Highway W, Bridge over Rock River. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-22 | 442426.06 | 0.000
12436 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009396 | This is a reconstruction project in Manitowoc County on a town road, Newton Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-28 | 272330.66 | 0.660
12437 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009397 | This is a reconstruction project in Manitowoc County on a town road, Valley Drive Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-28 | 199108.49 | 0.000
12438 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009398 | This is a reconstruction project in Manitowoc County on a town road, South Cleveland Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-11-03 | 221783.43 | 0.000
12439 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009399 | This is a reconstruction project in Manitowoc County on a town road, County line Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-11-03 | 195139.2 | 0.000
12440 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009400 | This is a bridge replacement project in Fond du Lac County on a town road, Youth Camp Road Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-22 | 410865.84 | 0.000
12441 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | IRON |  | 07 | 2009401 | This is a bridge replacement project in Iron County on local streets, Montreal River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2010-08-11 | 666325.92 | 0.043
12442 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2009402 | This is a bridge replacement project in Trempealeau County on County Highway D, Bruce Valley Creek Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2011-02-01 | 2010-12-08 | 423733.64 | 0.071
12443 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2009403 | This is a bridge replacement project in Barron County on a town road, Yellow River Bridge. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-09-10 | 504690.05 | 0.280
12444 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2009404 | This is a bridge replacement project in Douglas County on local streets, Town of Cloverland, McNeil's Landing Road, Brule River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-10-02 | 366429.56 | 0.000
12445 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2009405 | This is a bridge replacement project in Douglas County on a town road, Town of Oakland, Rice Farm Road, Little Amnicon River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-10-27 | 353847.17 | 0.000
12446 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009406 | This is a bridge replacement project in Taylor County on local streets, City of Medford, Black River Bridge and approaches. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-08-01 | 2009-08-27 | 657757.63 | 0.000
12447 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | MONROE |  | 03 | 2009407 | This is a reconstruction project in Monroe County on a town road, Kettle Road, Town of Wilton. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-07-01 | 2009-07-27 | 183311.19 | 0.038
12448 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | LINCOLN |  | 07 | 2009408 | This is a bridge replacement project in Lincoln County on County Highway H, Little Pine Creek Bridge. | Bridge Replacement | 2009-03-30 | 2009-03-30 | 2009-10-01 | 2009-07-22 | 249000 | 0.081
12449 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009409 | This is a resurfacing project in Taylor County on State Highway 64, Medford - Goodrich. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-24 | 2030000 | 200.102
12450 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUPACA |  | 08 | 2009411 | This is a resurfacing project in Waupaca County on US Highway 45, Winchester - New London. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-09-01 | 2009-09-22 | 563860.13 | 3.515
12451 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | EAU CLAIRE |  | 03 | 2009412 | This is a resurfacing project in Eau Claire County on US Highway 12, Augusta - Fairchild Road. | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-07-01 | 2009-07-21 | 982650.12 | 92.600
12452 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009486 | This is a bridge rehabilitation project in Dane County on Interstate 90, Madison - Janesville Road, Drotning Road bridges. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-09-01 | 192000 | 0.030
12453 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009487 | This is a bridge rehabilitation project in Dane County on Interstate 39, Madsion to Janesville Road, County Highway W bridges. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-09-01 | 182316.4 | 0.030
12454 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009488 | This is a bridge rehabilitation project in Dane County on Interstate 39, Madison - Janesville Road, County Highway B bridges. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-09-01 | 175866.4 | 0.030
12455 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 01 | 2009489 | This is a bridge rehabilitation project in Rock County on County Highway A, Blackhawk Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-20 | 166702.97 | 0.057
12456 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009490 | This is a bridge rehabilitation project in Dane County on County Highway N, Edgerton - Stoughton, Yahara River Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2010-04-21 | 685953.16 | 0.100
12457 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | RICHLAND |  | 03 | 2009491 | This is a bridge replacement project in Richland County on County Highway I, Gault Hollow Creek Bridge. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-11-01 | 2010-05-10 | 416955.73 | 0.150
12458 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAUK |  | 03 | 2009492 | This is a bridge rehabilitation project in Sauk County on County Highway PF, Seeley Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-14 | 510000 | 0.070
12459 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | IOWA |  | 03 | 2009493 | This is a bridge rehabilitation project in Iowa County on a town road, River Road Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-11-25 | 425491.06 | 0.110
12460 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2009494 | This is a reconstruction project in Grant County on County Highway C, US Highway 18 - Millville Road, Warner Creek Brige and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-11-23 | 515000 | 0.090
12461 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | LA CROSSE | LA CROSSE (MN) | 03 | 2009495 | This is a reconstruction project in La Crosse County on local streets, Oak Avenue, Onalaska and LaCrosse. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-12-02 | 1010616.12 | 2.640
12462 | Completed | C250,C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009496 | This is a pedestrian and bicycle path project in Dane County, Starkweather Creek Bike and Pedestrian Path. | Transportation Enhancements | 2009-04-17 | 2009-04-17 | 2010-05-01 | 2010-07-15 | 2300581.88 | 0.000
12463 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DODGE |  | 06 | 2009497 | This is a reconstruction project in Dodge County on County Highway G, Beaver Dam - Randolph. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-08-01 | 2009-09-30 | 950000 | 14.959
12464 | Completed | C250,C240 | Highway Infrastructure Investment Grant | WISCONSIN | LA CROSSE | LA CROSSE (MN) | 03 | 2009498 | This is a resurfacing project in La Crosse County on State Highway 16, La Crosse, West Salem and Monegan O'Head. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-09-10 | 690153.14 | 0.080
12465 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009499 | This is a restoration and rehabilitation project in Walworth County on US Highway 12, State Highway 67 to State Highway 50. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-11-01 | 2009-11-06 | 3185000 | 75.670
12466 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009500 | This is a bridge rehabilitation project in Walworth County on Interstate 43, Rock Freeway. | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2009-11-01 | 2009-11-15 | 3305066 | 26.900
12467 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2009501 | This is a reconstruction project in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2011-09-01 | 2011-09-09 | 9469411.63 | 79.500
12468 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2009502 | This is a new roadway construction project of 15.9 milesin Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 2009-04-17 | 2009-04-17 | 2010-07-01 | 2010-08-02 | 4600000 | 15.900
12469 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2009503 | This is a new roadway construction project of 2.07 miles in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 2009-04-17 | 2009-04-17 | 2010-08-01 | 2010-08-27 | 3582652.15 | 4.140
12470 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009504 | This is a resurfacing project in Manitowoc County on State Highway 147, Two Rivers - Mishicot. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-20 | 1215000 | 32.220
12471 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009505 | This is a resurfacing project in Manitowoc County on State Highway 147, Mishicot, and Interstate 43. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-20 | 1315000 | 57.280
12472 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DOOR |  | 08 | 2009506 | This is a reconstruction project in Door County on local streets, Michigan Street. | Pavement Improvement | 2009-04-17 | 2009-08-13 | 2009-10-01 | 2009-10-28 | 852000 | 1.150
12473 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009507 | This is a reconstruction project in Fond du Lac County on a town road, Lake Maria Road Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-21 | 219529.54 | 0.030
12474 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009508 | This is a bridge replacement project in Fond du Lac County on a town road, Oak Grove Road Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-21 | 280635.24 | 0.000
12475 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009509 | This is a reconstruction project in Marathon County on Interstate 39, Stevens Point - Wausau. | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2010-07-01 | 2010-06-30 | 8694548.76 | 28.400
12476 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON | WAUSAU | 07 | 2009510 | This is a reconstruction project in Marathon County on Interstate 39, Stevens Point - Wausau. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2010-07-01 | 2010-06-30 | 2990260.9 | 6.880
12477 | Completed | C250,C240 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009511 | This is a resurfacing project in Wood County on State Highway 73, Pittsville - Neilsville. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-08-01 | 2009-09-08 | 1414972.87 | 61.146
12478 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | VILAS |  | 08 | 2009512 | This is a resurfacing project in Vilas County on US Highway 45, Eagle River - Land-o-Lakes. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2010-07-07 | 1825000 | 47.180
12479 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009513 | This is a bridge replacement project in Marathon County on County Highway F, Stoney Creek Crossing. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-08-01 | 2009-08-20 | 417406.51 | 0.100
12480 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ASHLAND |  | 07 | 2009514 | This is a restoration and rehabilitation project in Ashland County on US Highway 2, Odanah - Saxon, Government Road. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-08-01 | 2009-08-18 | 3170000 | 34.880
12481 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2009515 | This is a bridge rehabilitation project in Polk County on US Highway 8, St. Croix Falls - Turtle Lake. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-10-29 | 105650.36 | 0.010
12482 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2009516 | This is a bridge rehabilitation project in Trempealeau County on County Highway G, Pine Creek Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-11-01 | 2009-11-20 | 339236.96 | 0.076
12483 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | JACKSON |  | 03 | 2009517 | This is a reconstruction project in Jackson County on County Highway A, Hixton - Black River Falls. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-29 | 1817000 | 10.150
12484 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2009518 | This is a resurfacing project in Sawyer County on State Highway 77, Ghost Lake - Clam Lake. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2009-10-29 | 2809662.87 | 79.360
12485 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009519 | This is a bridge replacement project in Taylor County on County Highway M, Branch River Bridge and approaches. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-11-01 | 2009-11-12 | 242871.04 | 0.000
12486 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009520 | This is a reconstruction project in Walworth County on County Highway C, Stateline Road - Pleasant Street. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-10-01 | 2009-12-08 | 992903.18 | 0.490
12487 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | VILAS |  | 08 | 2009521 | This is a resurfacing project in Vilas County on US Highway 45, Eagle River - Land-o-Lakes. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2009-09-01 | 2010-07-07 | 2982710.31 | 58.240
12488 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009523 | This is a reconstruction with additional lanes project in Kenosha County on Interstate 94, North-South Freeway, County Highway C Interchange fencing. | Pavement Widening | 2009-05-14 | 2009-05-14 | 2010-12-01 | 2010-11-19 | 136652.44 | 29.150
12489 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SHEBOYGAN |  | 06 | 2009524 | This is a bridge rehabilitation project in Sheboygan County on Interstate 43, Milwaukee, Green Bay Road. | Bridge Improvement | 2009-04-17 | 2009-04-17 | 2010-07-01 | 2010-09-10 | 2329511.86 | 194.260
12490 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SHEBOYGAN | SHEBOYGAN | 06 | 2009525 | This is a resurfacing project in Sheboygan County on Interstate 43, Port Washington - Manitowoc. | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2010-07-01 | 2010-09-10 | 14319091.08 | 83.120
12491 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009530 | This is a bridge replacement project in Dane County on Interstate 94, Madison - Milwaukee Road. | Pavement Widening | 2009-05-14 | 2009-05-14 | 2011-12-01 | 2011-11-22 | 46925107.6 | 15.600
12492 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009531 | This is a resurfacing project in Washington County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-11-12 | 655000 | 1.996
12493 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2009532 | This is a reconstruction with additional lanes project in Winnebago County on US Highway 41, State Higway 26 - Breezewood Lane. | Pavement Widening | 2009-05-14 | 2009-05-14 | 2010-10-01 | 2010-10-29 | 17122027.12 | 1.610
12494 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN |  | 08 | 2009533 | This is a bridge replacement project in Brown County on US Highway 41, Green Bay - Suamico. | Bridge Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-06 | 343409.42 | 0.040
12495 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | OCONTO |  | 08 | 2009534 | This is a bridge rehabilitation project in Oconto County on US Highway 41, Suamico - Abrams. | Bridge Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-06 | 142873.75 | 0.020
12496 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2009535 | This is a restoration and rehabilitation project in Manitowoc County on Interstate 43, Denmark, Manitowoc River, CN Railroad. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-07-01 | 2011-07-16 | 8410801 | 51.420
12497 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN |  | 08 | 2009536 | This is a resurfacing project in Brown County on Interstate 43, US Highway 12 - County Highway M. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-07-01 | 2010-07-16 | 8146435.56 | 46.500
12498 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009537 | This is a resurfacing project in Fond du Lac County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-11-12 | 2181230.34 | 95.760
12499 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009538 | This is a resurfacing project in Fond du Lac County on US Highway 45, Kewaskum - Eden. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-11-12 | 1995000 | 64.480
12500 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | GREEN LAKE |  | 06 | 2009539 | This is a bridge rehabilitation project in Green Lake County on County Highway A, Grand River Crossing. | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-12-03 | 370750.73 | 0.057
12501 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON | WAUSAU | 07 | 2009540 | This is a reconstruction project in Marathon County on County Highway NN, Creek Road - Thornapple Road. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-01 | 2009-11-09 | 1730000 | 61.930
12502 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | FOREST |  | 08 | 2009541 | This is a restoration and rehabilitation project in Forest County on County Highway W, County Highway Q - US Highway 8. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-01 | 2009-10-01 | 990000 | 43.560
12503 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MENOMINEE |  | 08 | 2009542 | This is a resurfacing project in Mennominee County on County Highway M, Strawberry Lane. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-10-16 | 3905000 | 35.140
12504 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | CLARK |  | 03 | 2009543 | This is a bridge replacement project in Clark County on a town road, Town of Sherwood Ballard Road, Hay Creek Bridge and approaches. | Bridge Replacement | 2009-05-14 | 2009-05-14 | 2009-10-01 | 2009-10-22 | 207542.32 | 0.000
12505 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON | MILWAUKEE | 05 | 2009592 | This is a reconstruction with additional lanes project in Washington County on County Highway Q, County Line Road, Pilgrim Road. | Pavement Widening | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2010-05-25 | 3350000 | 10.530
12506 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009594 | This is a bridge rehabilitation project in Milwaukee County on local streets, River Road. | Bridge Improvement | 2009-05-18 | 2009-05-18 | 2010-07-01 | 2010-05-31 | 317315 | 0.000
12507 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE |  | 08 | 2009609 | This is a bridge replacement project in Outagamie County on a town road, Weyers Road Bridge and approaches. | Bridge Replacement | 2009-05-18 | 2009-05-18 | 2009-12-01 | 2010-05-18 | 677761 | 0.000
12508 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GREEN LAKE |  | 06 | 2009610 | This is a resurfacing project in Green Lake County on County Highway A, Markesan - Green Lake. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-09-01 | 2009-09-08 | 1150000 | 15.600
12509 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009611 | This is a bridge replacement project in Marathon County on a town road, Huckleberry Road, Fenwood Creek Crossing. | Bridge Replacement | 2009-05-18 | 2009-05-18 | 2009-11-01 | 2009-12-07 | 228000 | 0.038
12510 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2009612 | This is a resurfacing project in Portage County on County Highway W, Kellner - Bankroft Road. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-20 | 2245000 | 153.400
12511 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009613 | This is a resurfacing project in Wood County on County Highway A, Pittsville - Marshfield. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-10 | 3110000 | 211.140
12512 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WOOD |  | 07 | 2009614 | This is a reconstruction project in Wood County on a town road, Lincoln Avenue, City of Marshfield. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2010-06-01 | 2010-05-28 | 1500690 | 1.992
12513 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | LINCOLN |  | 07 | 2009615 | This is a resurfacing project in Lincoln County on County Highway CC, Nick Road to Tannery Road. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-06 | 1140000 | 61.270
12514 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON |  | 07 | 2009622 | This is a bridge replacement project in Marathon County on a town road, Badger Road Bridge. | Bridge Replacement | 2009-05-18 | 2009-05-18 | 2010-01-01 | 2010-05-06 | 732896 | 0.095
12515 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | CLARK |  | 03 | 2009623 | This is a bridge replacement project in Clark County on County Highway OO, Black River Bridge. | Bridge Replacement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2010-04-28 | 1212672.9 | 0.000
12516 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 02 | 2009624 | This is a bridge replacement project in Rock County on County Highway H, Raccoon Creek Bridge. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-01 | 2009-11-25 | 418310 | 0.190
12517 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ADAMS |  | 06 | 2009680 | This is a reconstruction project in Adams County on County Highway Z, Town of Strongs Prairie and Monroe. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2010-01-01 | 2010-07-16 | 4299989 | 89.700
12518 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON | WAUSAU | 07 | 2009681 | This is a reconstruction project in Marathon County on local streets, Village of Weston, Ross Avenue. | Other | 2009-06-25 | 2009-06-25 | 2009-12-01 | 2010-08-03 | 2062007 | 61.640
12519 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARATHON | WAUSAU | 07 | 2009682 | This is a resurfacing project in Marathon County on local streets, Stewart Avenue - Elm Street. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2009-11-01 | 2009-10-16 | 430000 | 0.580
12520 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2009683 | This is a resurfacing project in Portage County on County Highway D, Almond. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2009-11-01 | 2009-11-13 | 1230000 | 92.800
12521 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | FLORENCE |  | 08 | 2009684 | This is a restoration and rehabilitation project in Florence County on County Highway U, Marinette County Line - County Highway N. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-11-01 | 2010-06-03 | 2800000 | 54.900
12522 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WAUPACA |  | 08 | 2009685 | This is a resurfacing project in Waupaca County on local streets, City of Clintonville, North 12th Street. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-10-09 | 375150 | 5.600
12523 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009686 | This is a reconstruction project in Milwaukee County on local streets, West State Street. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2010-07-01 | 2010-06-18 | 1638019 | 9.520
12524 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009687 | This is a reconstruction project in Milwaukee County on local streets, West Oklahoma Avenue. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2010-08-01 | 2010-09-20 | 2200000 | 12.960
12525 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MONROE |  | 03 | 2009688 | This is a resurfacing project in Monroe County on County Highway O, Warrens. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-10-26 | 990000 | 19.110
12526 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2009689 | This is a resurfacing project in Rock County on local streets, City of Janesville, various streets. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-10-30 | 1575630 | 127.760
12527 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009690 | This is a reconstruction project in Milwaukee County on local streets, West Lisbon Avenue. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2010-06-01 | 2010-11-17 | 2573868 | 15.300
12528 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2009691 | This is a bridge replacement project in Barron County on a town road, Pokegama Creek Bridge. | Bridge Replacement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2010-05-06 | 295200 | 0.000
12529 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | FOND DU LAC |  | 06 | 2009692 | This is a bridge replacement project in Fond du Lac County on local streets, Kiel Road Bridge and approaches. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-12-01 | 342000 | 0.000
12530 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WAUPACA |  | 08 | 2009693 | This is a bridge replacement project in Waupaca County on County Highway Q, Waupaca River Crossing. | Bridge Replacement | 2009-06-24 | 2009-06-24 | 2009-11-01 | 2010-08-19 | 1242354 | 0.380
12531 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2009694 | This is a bridge rehabilitation project in Taylor County on County Highway A, Pine Creek Bridge. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-12-30 | 2009-11-30 | 159900 | 0.000
12532 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2009695 | This is a new roadway construction project of 1.15 miles in Marinette County on County Highway T, Roosevelt Road, City of Marinette. | New Construction | 2009-06-25 | 2009-06-25 | 2010-06-01 | 2010-05-28 | 2340000 | 11.500
12533 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | FOREST |  | 08 | 2009696 | This is a pedestrian and bicycle path project in Forest County, Mole Lake Multi-Use Trail. | Transportation Enhancements | 2009-06-24 | 2009-06-24 | 2009-11-01 | 2010-06-08 | 738000 | 0.000
12534 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | VILAS |  | 08 | 2009697 | This is a bicycle path project in Vilas County, Trout Lake Bicycle Trail. | Transportation Enhancements | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2010-06-09 | 279379 | 0.000
12535 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009866 | This is the design engineering effort for a construction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Other | 2009-07-30 | 2009-07-30 | 2010-06-01 | 2010-07-31 | 32040 | 0.000
12536 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2009867 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 51st Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 5300 | 0.000
12537 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009868 | This is the design engineering effort for a construction project in Milwaukee County on local streets, West Vliet Street Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8513.06 | 0.000
12538 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009869 | This is the design engineering effort for a construction project in Milwaukee County on local streets, North Sherman Blvd. Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7473.59 | 0.000
12539 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009870 | This is the design engineering effort for a construction project in Milwaukee County on local streets, North Sherman Blvd. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 9100 | 0.000
12540 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2009871 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 76th Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 11927.75 | 0.000
12541 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009872 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 6th Street Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 19025 | 0.000
12542 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009873 | This is the design engineering effort for a construction project in Waukesha County on County Highway ES, Calhoun Road to County Highway O. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8200 | 0.000
12543 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009874 | This is the design engineering effort for a construction project in Milwaukee County on local streets, West National Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4800 | 0.000
12544 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2009875 | This is the design engineering effort for a construction project in Milwaukee County on local streets, Hampton Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 80000 | 0.000
12545 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009876 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South Cesar Chavez Drive. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 75000 | 0.000
12546 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009877 | This is the design engineering effort for a construction project in Milwaukee County on local streets, South 6th Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4580 | 0.000
12547 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 05 | 2009878 | This is the design engineering effort for a construction project in Milwaukee County on local streets, 70th Street Brige. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 15800 | 0.000
12548 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | OZAUKEE | MILWAUKEE | 05 | 2009879 | This is the design engineering effort for a construction project in Ozaukee County on County Highway O, North Green Bay Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 15600 | 0.000
12549 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | OZAUKEE | MILWAUKEE | 05 | 2009880 | This is the design engineering effort for a construction project in Ozaukee County on local streets, West Donges Bay Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-15 | 2009-12-15 | 5000 | 0.000
12550 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009881 | This is the design engineering effort for a construction project in Racine County on local streets, North Main Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 31000 | 0.000
12551 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009882 | This is the design engineering effort for a construction project in Racine County on County Highway C, Spring Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 6122 | 0.000
12552 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2009883 | This is the design engineering effort for a construction project in Kenosha County on local streets, 38th Street Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 16180 | 0.000
12553 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009884 | This is the design engineering effort for a construction project in Racine County on local streets, Lathrop Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7073 | 0.000
12554 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009885 | This is the design engineering effort for a construction project in Racine County on local streets, Taylor Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 3122 | 0.000
12555 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009886 | This is the design engineering effort for a construction project in Washington County on local streets, Decorah Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 12284 | 0.000
12556 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009887 | This is the design engineering effort for a construction project in Washington County on local streets, 7th Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 1956 | 0.000
12557 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009888 | This is the design engineering effort for a construction project in Washington County on local streets, Indiana Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7482.19 | 0.000
12558 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009889 | This is the design engineering effort for a construction project in Washington County on local streets, Vine Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 1976 | 0.000
12559 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009890 | This is the design engineering effort for a construction project in Washington County on local streets, Park Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 1730 | 0.000
12560 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2009891 | This is the design engineering effort for a construction project in Washington County on local streets, Jefferson Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4096 | 0.000
12561 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009892 | This is the design engineering effort for a construction project in Waukesha County on local streets, Wisconsin Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 18300 | 0.000
12562 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009893 | This is the design engineering effort for a construction project in Waukesha County on County Highway O, South Moorland Blvd. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 23250 | 0.000
12563 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009894 | This is the design engineering effort for a construction project in Waukesha County on County Highway K, North 132nd Street to North 124th Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 17393 | 0.000
12564 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009895 | This is the design engineering effort for a construction project in Waukesha County on County Highway T, Grandview Blvd.. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4400 | 0.000
12565 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009896 | This is the design engineering effort for a construction project in Waukesha County on County Highway V, Townline Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7632.46 | 0.000
12566 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009897 | This is the design engineering effort for a construction project in Waukesha County on County Highway Y, Baker Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 20000 | 0.000
12567 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2009898 | This is the design engineering effort for a construction project in Milwaukee County on County Highway ZZ, West Loomis Road to South 51st Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 18150 | 0.000
12568 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2009899 | This is the design engineering effort for a construction project in Milwaukee County on local streets, Eastbrook Park Drive. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 16200 | 0.000
12569 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009900 | This is the design engineering effort for a construction project in Walworth County on local streets, Wrigley Drive. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 12000 | 0.000
12570 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2009901 | This is the design engineering effort for a construction project in Walworth County on local streets, Mohawk Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 3560 | 0.000
12571 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2009902 | This is the design engineering effort for a construction project in Grant County on County Highway D, City of Platteville, Chestnut Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-15 | 2009-12-15 | 40500 | 0.000
12572 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | SHAWANO |  | 08 | 2009903 | This is the design engineering effort for a construction project in Shawano County on County Highway D, North Branch Embarrass River Crossing. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 9900 | 0.000
12573 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2009904 | This is the design engineering effort for a construction project in Trempealeau County, Whitehall Historic Railroad Depot. | Other | 2009-07-30 | 2009-07-30 | 2010-01-05 | 2010-01-05 | 7820 | 0.000
12574 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PIERCE |  | 03 | 2009905 | This is the design engineering effort for a construction project in Pierce County on County Highway P, May Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 6959.42 | 0.000
12575 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2009906 | This is the design engineering effort for a construction project in Polk County, Amery to Dresser Trail. | Other | 2009-07-30 | 2009-07-30 | 2010-01-05 | 2010-01-05 | 13300 | 0.000
12576 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | WASHBURN |  | 07 | 2009907 | This is the design engineering effort for a construction project in Washburn County, Spooner Bicycle and Pedestrian Facility. | Other | 2009-07-30 | 2009-07-30 | 2010-01-05 | 2010-01-05 | 6260 | 0.000
12577 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BAYFIELD |  | 07 | 2009908 | This is the design engineering effort for a construction project in Bayfield County on State Highway 13, Red Cliff streetscape improvement. | Other | 2009-07-30 | 2009-07-30 | 2010-01-05 | 2010-01-05 | 15300 | 0.000
12578 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHBURN |  | 07 | 2009909 | This is the design engineering effort for a construction project in Washburn County on County Highway E, Namekagon River Bridge. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4000 | 0.000
12579 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2009910 | This is the design engineering effort for a construction project in Chippewa County on local streets, First Avenue. | Other | 2009-08-26 | 2009-08-26 | 2009-12-15 | 2009-12-15 | 8800 | 0.000
12580 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2009911 | This is the design engineering effort for a construction project in Chippewa County on County Highway X, 57th Avenue West to 184th Street. | Other | 2009-08-26 | 2009-08-26 | 2009-12-01 | 2009-12-01 | 6410.08 | 0.000
12581 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS | DULUTH-SUPERIOR (MN) | 07 | 2009912 | This is the design engineering effort for a construction project in Douglas County on local streets, East 5th Street, 6th Avenue East to 20th Avenue East. | Other | 2009-08-26 | 2009-08-26 | 2009-12-15 | 2009-12-15 | 7500 | 0.000
12582 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009914 | This is the design engineering effort for a construction project in Milwaukee County on County Highway S, North 84th Street to North 56th Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 211427 | 0.000
12583 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009915 | This is the design engineering effort for a construction project in Milwaukee County, South Cesar Chavez Drive, West National Avenue to Greenfield Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8000 | 0.000
12584 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2009916 | This is the design engineering effort for a construction project in Racine County, North Shore Multi-Use Path. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8880 | 0.000
12585 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2009917 | This is the design engineering effort for a construction project in Waukesha County, Lake Country Trail. | Other | 2009-07-30 | 2009-07-30 | 2009-12-15 | 2009-12-15 | 17511 | 0.000
12586 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2009918 | This is the design engineering effort for a construction project in Milwaukee County on , Kinnickinnic River Bike Trail. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7000 | 0.000
12587 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2009919 | This is the design engineering effort for a construction project in Kenosha County on local streets, 30th Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 13054.73 | 0.000
12588 | Completed | C200,C230 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 01 | 2009920 | This is the design engineering effort for a construction project in Kenosha County on County Highway Z, Main Street East. | Other | 2009-07-30 | 2009-07-30 | 2009-12-22 | 2009-12-22 | 21520 | 0.000
12589 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2009921 | This is the design engineering effort for a construction project in Kenosha County on local streets, Cooper Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 5000 | 0.000
12590 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2009922 | This is the design engineering effort for a construction project in Racine County on local streets, Kane Street. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7120 | 0.000
12591 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KEWAUNEE |  | 08 | 2009924 | This is the design engineering effort for a construction project in Kewaunee County on County Highway A, Town of Luxemburg. | Other | 2009-07-30 | 2009-07-30 | 2009-12-15 | 2009-12-15 | 8325 | 0.000
12592 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009925 | This is the design engineering effort for a construction project in Brown County on County Highway I, Town of Scott. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 6351.41 | 0.000
12593 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009926 | This is the design engineering effort for a construction project in Brown County on local streets, City of DePere, Jordan Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 3560 | 0.000
12594 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009927 | This is the design engineering effort for a construction project in Brown County, Fox River Recreation Trail. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 4106.05 | 0.000
12595 | Completed | C950 | Ferryboat | WISCONSIN | BROWN | GREEN BAY | 08 | 2009928 | This is the design engineering effort for a construction project in Brown County on local streets, City of Green Bay, Manitowoc Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 6364.47 | 0.000
12596 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009929 | This is the design engineering effort for a construction project in Brown County, Verlin Road Bike and Pedestrian Facilities. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7447 | 0.000
12597 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | JUNEAU |  | 03 | 2009930 | This is the design engineering effort for a construction project in Juneau County on County Highway A, New Lisbon, Krypton Road. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 9987.66 | 0.000
12598 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2009931 | This is the design engineering effort for a construction project in Rock County, Rotamer Road Bike Trail Connector. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8700 | 0.000
12599 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | LA CROSSE | LA CROSSE (MN) | 03 | 2009932 | This is the design engineering effort for a construction project in La Crosse County on State Highway 35, Mormon Coulee Road Bike Path improvement. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 8620 | 0.000
12600 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO |  | 06 | 2009933 | This is the design engineering effort for a construction project in Winnebago County on County Highway D, Town of Winneconnie and Town of Poygan. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 7005.8 | 0.000
12601 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2009934 | This is the design engineering effort for a construction project in Portage County on local streets, City of Stevens Point, Minnesota Avenue. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2011-02-28 | 53000 | 0.000
12602 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2009935 | This is the design engineering effort for a construction project in Brown County on County Highway EB, Village of Howard. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 5816.33 | 0.000
12603 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | FOREST |  | 08 | 2009941 | This is the design engineering effort for a construction project in Forest County, the rebuild and rehabilitation of Laona Northern Railroad Track. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 10240 | 0.000
12604 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | Multiple | 2009942 | This is the design engineering effort for a construction project in Outagamie County, Fox River Navigation, Lock Keeper Houses. | Other | 2009-07-30 | 2009-07-30 | 2009-12-01 | 2009-12-01 | 9587.93 | 0.000
12605 | Completed | C250 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2009947 | This is the design engineering effort for a construction project in Douglas County on County Highway C, State Highway 35 to Kronberg Road. | Other | 2009-10-20 | 2009-10-20 | 2009-12-01 | 2009-12-01 | 5006.76 | 0.000
12606 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | JEFFERSON |  | Multiple | 2009953 | This is the design engineering effort for a construction project in Jefferson County on County Highway F, Sullivan, I-94. | Other | 2009-08-04 | 2009-08-04 | 2009-12-01 | 2009-12-01 | 7614.92 | 0.000
12607 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2009954 | This is the design engineering effort for a construction project in Grant County on local streets, Village of Bloomington, Mill Street. | Other | 2009-08-04 | 2009-08-04 | 2009-12-15 | 2009-12-15 | 12120 | 0.000
12608 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | IOWA |  | 03 | 2009955 | This is the design engineering effort for a construction project in Iowa County on County Highway X, Village of Linden, Babcock Avenue. | Other | 2009-08-04 | 2009-08-04 | 2009-12-15 | 2009-12-15 | 3860 | 0.000
12609 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 02 | 2009956 | This is the design engineering effort for a construction project in Rock County on County Highway C, North 4th Street and West Main Street. | Other | 2009-08-04 | 2009-08-04 | 2009-12-01 | 2009-12-01 | 7549.06 | 0.000
12610 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009957 | This is the design engineering effort for a construction project in Dane County on local streets, City of Verona, North Nine Mound Road. | Other | 2009-08-06 | 2009-08-06 | 2009-12-01 | 2009-12-01 | 13200 | 0.000
12611 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 02 | 2009958 | This is the design engineering effort for a construction project in Rock County on Town Road, Town of Beloit, Inman Parkway. | Other | 2009-10-20 | 2009-10-20 | 2010-03-31 | 2011-02-22 | 1122.07 | 0.000
12612 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009959 | This is the design engineering effort for a construction project in Dane County on County Highway Q, City of Middleton, Allen Blvd.. | Other | 2009-08-06 | 2009-08-06 | 2009-12-01 | 2009-12-01 | 7860 | 0.000
12613 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2009960 | This is the design engineering effort for a construction project in Dane County on County Highway MS, City of Madison, University Avenue. | Other | 2009-08-06 | 2009-08-06 | 2009-12-01 | 2009-12-01 | 24400 | 0.000
12614 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2009965 | This is the design engineering effort for a construction project in Dane County on County Highway K, US Highway 12 and County Highway M. | Other | 2009-08-13 | 2009-08-13 | 2009-12-01 | 2009-12-01 | 6795.83 | 0.000
12615 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SHEBOYGAN | SHEBOYGAN | 06 | 2010051 | This is the design engineering effort for a construction project in Sheboygan County on local streets, Taylor Drive, Superior Avenue, and Saemann Avenue. | Other | 2009-09-29 | 2009-09-29 | 2009-12-01 | 2009-12-01 | 6994.35 | 0.000
12616 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010059 | This is a reconstruction project in Barron County on US Highway 53, New Auburn - Spooner. | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-11-01 | 2010-11-01 | 9435598.99 | 74.280
12617 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010060 | This is a reconstruction project in Barron County on US Highway 53, New Aubrurn - Spooner. | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-11-01 | 2010-11-01 | 8561385.4 | 74.280
12618 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2010061 | This is a bridge rehabilitation project in Crawford County on US Highway 61, Boscobel - Readstownn, Wisconsin River Structure. | Bridge Improvement | 2010-05-13 | 2010-05-13 | 2010-10-01 | 2010-09-14 | 331552 | 0.220
12619 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010062 | This is a bridge rehabilitation project in Milwaukee County on local streets, West Vliet Street Bridge. | Bridge Improvement | 2009-12-04 | 2009-12-04 | 2010-09-01 | 2010-08-27 | 145843.22 | 0.000
12620 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010063 | This is a bridge rehabilitation project in Milwaukee County on local streets, North Sherman Blvd. Bridge. | Bridge Improvement | 2009-12-04 | 2009-12-04 | 2010-09-01 | 2010-08-27 | 582424.83 | 0.000
12621 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010064 | This is a resurfacing project in Milwaukee County on local streets, North Sherman Blvd. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-09-01 | 2010-08-27 | 417555.48 | 0.000
12622 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2010065 | This is a resurfacing project in Milwaukee County on local streets, South 76th Street. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-07-01 | 2010-09-09 | 515000 | 0.000
12623 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010066 | This is a resurfacing project in Milwaukee County on local streets, West National Avenue. | Pavement Improvement | 2009-12-02 | 2009-12-02 | 2010-07-01 | 2010-09-09 | 295200 | 0.000
12624 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010067 | This is a resurfacing project in Milwaukee County on local streets, South Cesar Chavez Drive. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-07-01 | 2010-10-25 | 707250 | 0.000
12625 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010068 | This is a landscaping and other scenic beautification project in Milwaukee County, South Cesar Chavez Drive. | Transportation Enhancements | 2009-12-04 | 2009-12-04 | 2010-07-01 | 2010-10-25 | 492000 | 0.000
12626 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010069 | This is a resurfacing project in Milwaukee County on local streets, South 68th Street. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-07-01 | 2010-09-09 | 281670 | 0.000
12627 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010070 | This is a pedestrian and bicycle path project in Racine County, North Shore Multi-use Path. | Transportation Enhancements | 2009-12-04 | 2009-12-04 | 2010-06-01 | 2010-07-15 | 436120 | 0.000
12628 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010071 | This is a resurfacing project in Racine County on local streets, Lathrop Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-10-06 | 435001 | 1.570
12629 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010072 | This is a resurfacing project in Racine County on local streets, Taylor Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-10-06 | 192001 | 0.240
12630 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010073 | This is a restoration and rehabilitation project in Racine County on County Highway G, Union Church Drive. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-06-01 | 2010-08-23 | 1398350 | 0.000
12631 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010074 | This is a restoration and rehabilitation project in Racine County on County Highway K, East Wink Lake Rd - Overson Road. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-06-01 | 2010-08-23 | 837780 | 0.000
12632 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010075 | This is a bridge rehabilitation project in Milwaukee County on local streets, Jackson Park Drive. | Bridge Improvement | 2009-12-04 | 2009-12-04 | 2010-07-01 | 2010-08-24 | 405000 | 0.000
12633 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2010076 | This is a bridge replacement project in Manitowoc County on local streets, Pioneer Road. | Bridge Replacement | 2009-12-07 | 2009-12-07 | 2010-06-01 | 2010-05-07 | 325000 | 0.000
12634 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 2010077 | This is a bridge replacement project in Winnebago County on local streets, City of Neenah, Adams Street. | Bridge Replacement | 2009-12-10 | 2009-12-10 | 2010-04-01 | 2010-04-30 | 415000 | 0.000
12635 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2010078 | This is a bridge rehabilitation project in Crawford County on State Highway 60, Bridgeport - Blue River. | Bridge Improvement | 2010-05-13 | 2010-05-13 | 2010-10-01 | 2010-10-04 | 325000 | 0.010
12636 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MONROE |  | 03 | 2010079 | This is a bridge replacement project in Monroe County on County Highway M, County Higway A - State Highway 16. | Other | 2009-12-04 | 2009-12-04 | 2010-09-01 | 2010-08-12 | 383760 | 0.100
12637 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MONROE |  | 03 | 2010080 | This is a bridge replacement project in Monroe County on County Highway M, County Higway A - State Highway 16. | Other | 2009-12-04 | 2009-12-04 | 2010-09-01 | 2010-08-12 | 471090 | 0.100
12638 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | VERNON |  | 03 | 2010081 | This is a bridge replacement project in Vernon County on County Highway UU, Victory Creek Bridge and approaches. | Bridge Replacement | 2009-12-04 | 2009-12-04 | 2010-09-01 | 2010-08-27 | 348090 | 0.060
12639 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2010082 | This is a bridge replacement project in Crawford County on a town road, Town of Freeman, Buck Creek Bridge. | Bridge Replacement | 2009-12-04 | 2009-12-04 | 2010-07-01 | 2010-06-28 | 210000 | 0.060
12640 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DANE |  | 02 | 2010083 | This is a reconstruction project in Dane County on County Highway K, US Highway 12 - County Highway M. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-08-01 | 2010-07-14 | 590400 | 11.900
12641 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUSHARA |  | 06 | 2010084 | This is a resurfacing project in Waushara County on State Highway 49, Poysippi - Fremont. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2010-10-01 | 2010-10-15 | 1883107.34 | 115.920
12642 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE |  | 08 | 2010085 | This is a bridge replacement project in Outagamie County on a town road, Greiner Road Bridge and approaches. | Other | 2009-12-10 | 2009-12-10 | 2010-08-01 | 2010-11-15 | 268000 | 0.025
12643 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE |  | 08 | 2010086 | This is a bridge replacement project in Outagamie County on a town road, Central Valley Road Bridge and approaches. | Bridge Replacement | 2009-12-07 | 2009-12-07 | 2010-07-01 | 2010-11-15 | 305900 | 0.040
12644 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | WAUSHARA |  | 06 | 2010087 | This is a reconstruction project in Waushara County on County Highway I, Alder Creek Crossing. | New Bridge Construction | 2009-12-16 | 2009-12-16 | 2010-07-01 | 2010-07-02 | 175000 | 0.000
12645 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | PORTAGE |  | 07 | 2010088 | This is a resurfacing project in Portage County on local streets, City of Stevens Point, Minnesota Avenue. | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-09-01 | 2010-08-04 | 430500 | 3.200
12646 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | BAYFIELD |  | 07 | 2010089 | This is a bridge rehabilitation project in Bayfield County on County Highway D, Namekagon River Bridge. | Bridge Improvement | 2009-12-16 | 2009-12-16 | 2010-07-01 | 2010-06-30 | 246000 | 0.000
12647 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MENOMINEE |  | 08 | 2010090 | This is a resurfacing project in Menominee County on State Highway 55, Shawano - Langlade. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2010-12-01 | 2010-11-19 | 2600000 | 129.920
12648 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | FOREST |  | 08 | 2010091 | This is an historic preservation project in Forest County, to rebuild and rehabilitate the Laona Northern Railroad Track. | Transportation Enhancements | 2009-12-16 | 2009-12-16 | 2010-06-01 | 2010-05-21 | 629760 | 0.000
12649 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | PRICE |  | 07 | 2010092 | This is a bridge replacement project in Price County on a town road, Sailor Creek Bridge and approaches. | Bridge Replacement | 2009-12-16 | 2009-12-16 | 2010-09-01 | 2010-08-11 | 395660 | 0.010
12650 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | JEFFERSON |  | Multiple | 2010093 | This is a reconstruction project in Jefferson County on County Highway F, Sullivan - Interstate 94. | Pavement Improvement | 2009-12-04 | 2009-12-04 | 2010-06-01 | 2010-06-10 | 1165000 | 15.600
12651 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2010171 | This is a bridge rehabilitation project in Grant County on US Highway 18, Prairie du Chien - Fennimore, Wisconsin River Bridge. | Bridge Improvement | 2010-05-13 | 2010-05-13 | 2010-09-01 | 2010-10-11 | 580000 | 0.130
12652 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 01 | 2010172 | This is a reconstruction project in Rock County on a town road, Town of Turtle. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-30 | 196800 | 6.000
12653 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DODGE |  | 06 | 2010173 | This is a reconstruction project in Dodge County on County Highway DJ, Village of Juneau, East Oak Grove Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-07-01 | 2010-07-02 | 280000 | 0.000
12654 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RICHLAND |  | 03 | 2010174 | This is a reconstruction project in Richland County on County Highway C, Vernon County Line, Rolt Lane. | Pavement Improvement | 2010-01-12 | 2010-01-12 | 2010-09-01 | 2010-10-06 | 1482150 | 0.000
12655 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RICHLAND |  | 03 | 2010175 | This is a reconstruction project in Richland County on County Highway D, Rockbrook Bridge. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-10-06 | 1166040 | 0.000
12656 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | JUNEAU |  | 03 | 2010176 | This is a reconstruction project in Juneau County on County Highway A, Monroe County Line - New Lisbon. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-08-18 | 3062700 | 52.000
12657 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK |  | 02 | 2010177 | This is a reconstruction project in Rock County on County Highway C, North 4th Street and West Main Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-07-01 | 2010-06-30 | 590400 | 4.000
12658 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 02 | 2010178 | This is a reconstruction project in Rock County on a town road, Town of Beloit, Inman Parkway. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-30 | 670350 | 16.800
12659 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 02 | 2010179 | This is a reconstruction project in Rock County on local streets, Town of Beloit, Cranston Road. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-30 | 129150 | 0.000
12660 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | LA CROSSE | LA CROSSE (MN) | 03 | 2010180 | This is a bicycle path project in La Crosse County on State Highway 35, Mormon Coulee Road Bike Path Improvement. | Transportation Enhancements | 2009-12-31 | 2009-12-31 | 2010-09-01 | 2010-08-20 | 530130 | 2.800
12661 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010181 | This is a reconstruction project in Dane County on County Highway MS, City of Madison, University Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-06-01 | 2011-06-29 | 3633800 | 7.200
12662 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DODGE |  | 06 | 2010182 | This is a reconstruction project in Dodge County on various highways, Madison Street and University Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-09-22 | 956940 | 0.000
12663 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010183 | This is a roundabut project in Milwaukee County on local streets, West Winnebago Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2011-09-01 | 2011-10-31 | 1044213 | 0.000
12664 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010184 | This is a reconstruction project in Milwaukee County on local streets, East and West Keefe Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-11-01 | 2010-11-08 | 3210617.01 | 0.000
12665 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2010185 | This is a resurfacing project in Milwaukee County on local streets, West Grange Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-09-03 | 688800 | 0.000
12666 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010186 | This is a reconstruction project in Milwaukee County on local streets, East and West North Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 | 2011-01-17 | 2163949 | 0.000
12667 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2010187 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Hampton Avenue. | Pavement Improvement | 2010-01-12 | 2010-01-12 | 2010-11-01 | 2011-07-27 | 773241 | 0.000
12668 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010188 | This is a restoration and rehabilitation project in Milwaukee County on local streets, 15th Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-08-30 | 799500 | 0.000
12669 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | OZAUKEE | MILWAUKEE | 05 | 2010189 | This is a restoration and rehabilitation project in Ozaukee County on County Highway O, North Green Bay Road. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-11-02 | 959400 | 0.000
12670 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010190 | This is a bridge rehabilitation project in Kenosha County on local streets, 38th Street Bridge. | Bridge Replacement | 2010-01-13 | 2010-01-13 | 2010-12-01 | 2010-12-01 | 945000 | 0.000
12671 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010191 | This is a resurfacing project in Washington County on local streets, Decorah Road. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 | 2010-12-03 | 455466 | 0.000
12672 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010192 | This is a resurfacing project in Washington County on local streets, 7th Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 | 2010-12-03 | 120294 | 0.000
12673 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010193 | This is a resurfacing project in Washington County on local streets, Indiana Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 | 2010-12-03 | 311434 | 0.000
12674 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010194 | This is a resurfacing project in Washington County on local streets, Vine Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 | 2010-12-03 | 121524 | 0.000
12675 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010195 | This is a resurfacing project in Washington County on local streets, Park Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 | 2010-12-03 | 106395 | 0.000
12676 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHINGTON |  | 05 | 2010196 | This is a resurfacing project in Washington County on local streets, Jefferson Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-10-01 | 2010-12-03 | 251904 | 0.000
12677 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2010197 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Eastbrook Park Drive. | Pavement Widening | 2010-01-12 | 2010-01-12 | 2011-10-01 | 2011-10-31 | 835580 | 0.000
12678 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010198 | This is a resurfacing project in Kenosha County on local streets, 30th Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-10-15 | 1035780 | 0.000
12679 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2010199 | This is a pedestrian access and safety project in Kenosha County. | Transportation Enhancements | 2010-01-13 | 2010-01-13 | 2010-11-01 | 2011-10-27 | 215182 | 0.000
12680 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA |  | 01 | 2010200 | This is a resurfacing project in Kenosha County on local streets, Cooper Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-12-04 | 307500 | 0.000
12681 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010201 | This is a resurfacing project in Kenosha County on local streets, 80th Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-10-15 | 553500 | 0.000
12682 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010202 | This is a resurfacing project in Racine County on local streets, Kane Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-08-09 | 387880 | 0.000
12683 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010203 | This is a restoration and rehabilitation project in Racine County on various highways, Market Street, Pine Street - Dodge Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-11-18 | 433575 | 0.000
12684 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE |  | 01 | 2010204 | This is a resurfacing project in Racine County on various highways, Grove Street, Oak Street - Briody Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-11-18 | 551110 | 0.000
12685 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | Multiple | 2010205 | This is an historic preservation project in Outagamie County, the rehabilitation of the Fox River Navigation System Lock Keeper houses. | Transportation Enhancements | 2010-01-13 | 2010-01-13 | 2010-10-01 | 2011-01-03 | 946576 | 0.000
12686 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | 08 | 2010206 | This is a reconstruction project in Outagamie County on local streets, Village of Little Chute, Washington Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-09-01 | 360390 | 0.300
12687 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010207 | This is a pedestrian and bicycle path project in Brown County, Fox River Recreation Trail. | Transportation Enhancements | 2010-01-13 | 2010-01-13 | 2010-07-01 | 2010-06-04 | 254610 | 0.000
12688 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010208 | This is a pedestrian and bicycle path project in Brown County, Verlin Road Bike Pedestrian Facilities. | Transportation Enhancements | 2010-01-13 | 2010-01-13 | 2010-10-01 | 2010-10-01 | 457978 | 0.000
12689 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 2010209 | This is a restoration and rehabilitation project in Winnebago County on local streets, City of Mehasha, Tayco Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-08-11 | 473550 | 9.800
12690 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 2010210 | This is a resurfacing project in Winnebago County on local streets, City of Oshkosh, Snell Road. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-08-19 | 717090 | 16.000
12691 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 2010211 | This is a restoration and rehabilitation project in Winnebago County on local streets, City of Neenah, Wisconsin Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2011-06-01 | 2011-06-01 | 450000 | 0.420
12692 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SHEBOYGAN | SHEBOYGAN | 06 | 2010212 | This is a reconstruction project in Sheboygan County on local streets, Taylor Drive, Superior Avenue, and Saemann Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-10-19 | 815870 | 6.840
12693 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OCONTO |  | 08 | 2010213 | This is a bridge rehabilitation project in Oconto County on County Highway S, Pensaukee River Bridge. | Bridge Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-10-08 | 430500 | 0.000
12694 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OCONTO |  | 08 | 2010214 | This is a bridge rehabilitation project in Oconto County on County Highway S, Pensaukee River Bridge. | Bridge Improvement | 2010-01-13 | 2010-01-13 | 2010-09-01 | 2010-10-08 | 344400 | 0.000
12695 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010215 | This is a reconstruction project in Marinette County on local streets, Cleveland Avenue. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-22 | 638370 | 0.000
12696 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010216 | This is a reconstruction project in Marinette County on local streets, Hattie Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-22 | 129150 | 0.000
12697 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010217 | This is a reconstruction project in Marinette County on local streets, Hosmer Street. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-08-01 | 2010-07-22 | 116850 | 0.000
12698 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010218 | This is a reconstruction project in Marinette County on local streets, Marinette Mid City Bike and Pedestrian Path. | Transportation Enhancements | 2010-01-13 | 2010-01-13 | 2010-06-01 | 2010-05-26 | 116000 | 0.000
12699 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | IRON |  | 07 | 2010219 | This is a new roadway construction project of 3.96 miles in Iron County on US Highway 51, County Highway C - Hurley. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2010-10-01 | 2011-08-09 | 1500000 | 19.800
12700 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DUNN |  | 03 | 2010220 | This is a reconstruction project in Dunn County on County Highway P, Spring Valley - Menomonie. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-06-01 | 2010-07-08 | 1184490 | 0.000
12701 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | PIERCE |  | 03 | 2010221 | This is a reconstruction project in Pierce County on County Highway P, May Avenue. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-09-01 | 2010-07-09 | 565000 | 0.000
12702 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DUNN |  | 03 | 2010222 | This is a resurfacing project in Dunn County on local streets, City of Menomonie, 3M Drive and 9th Street. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-09-01 | 2010-09-02 | 1590000 | 0.000
12703 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2010223 | This is a resurfacing project in Sawyer County on State Highway 27, Ojibwa - Stone Lake. | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2010-09-01 | 2010-09-15 | 900000 | 37.350
12704 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2010224 | This is a resurfacing project in Sawyer County on State Highway 27, Ojibwa - Stone Lake. | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2010-09-01 | 2010-09-15 | 1300000 | 121.920
12705 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2010225 | This is a bridge replacement project in Douglas County on a town road, Town of Wascott, Cheever Road, Ounce River Bridge. | Bridge Replacement | 2010-01-14 | 2010-01-14 | 2010-07-01 | 2010-08-13 | 188620 | 0.000
12706 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2010226 | This is a bridge replacement project in Douglas County on a town road, Town of Wascott, East Coppermine Road, Ounce River Bridge. | Bridge Replacement | 2010-01-14 | 2010-01-14 | 2010-07-01 | 2010-08-13 | 212150 | 0.000
12707 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RUSK |  | 07 | 2010227 | This is a restoration and rehabilitation project in Rusk County on County Highway F, Bear Lake, Potato Lake Road. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-07-01 | 2010-06-22 | 501200 | 0.000
12708 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WASHBURN |  | 07 | 2010228 | This is a bridge rehabilitation project in Washburn County on County Highway E, Namekagon River Bridge. | Bridge Improvement | 2010-01-14 | 2010-01-14 | 2010-05-01 | 2010-05-19 | 246000 | 0.000
12709 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2010229 | This is a restoration and rehabilitation project in Chippewa County on local streets, City of Chippewa Falls Bridge Street. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-06-01 | 2010-06-08 | 171400 | 0.000
12710 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS | DULUTH-SUPERIOR (MN) | 07 | 2010230 | This is a resurfacing project in Douglas County on local streets, City of Superior, Hill Avenue and Broadway Street. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-08-01 | 2010-06-30 | 528900 | 0.000
12711 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RICHLAND |  | 03 | 2010269 | This is a bridge replacement project in Richland County on town road, Cortland Lane, Town of Akan. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-07-13 | 302580 | 0.550
12712 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | CRAWFORD |  | 03 | 2010270 | This is a reconstruction project in Crawford County on County Highway B, County Highway B, State Highway 35 - State Highway 27 Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2011-09-13 | 3874500 | 2.000
12713 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2010271 | This is a reconstruction project in Grant County on local streets, Village of Bloomington Mill Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-27 | 745380 | 0.280
12714 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 02 | 2010272 | This is a reconstruction project in Rock County on a town road, West Happy Hollow Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-21 | 544890 | 2.489
12715 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010273 | This is a reconstruction project in Dane County on local streets, City of Verona, North Nine Mound Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2011-03-01 | 2010-08-05 | 714800 | 0.440
12716 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2010274 | This is a bicycle path project in Rock County, Rotamer Road Bike Trail connector. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2011-06-23 | 445000 | 0.975
12717 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2010276 | This is a reconstruction project in Rock County on local streets, Ruger Avenue Bridge and approaches, City of Janesville. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2011-09-28 | 619920 | 0.040
12718 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2010277 | This is a reconstruction project in Rock County on local streets, City of Janesville Tyler - South Randall. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-27 | 415740 | 0.480
12719 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | JANESVILLE | 01 | 2010278 | This is a reconstruction project in Rock County on local streets, City of Milton, East High Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-27 | 584250 | 1.190
12720 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | GRANT |  | 03 | 2010279 | This is a bridge replacement project in Grant County on County Highway D, City of Platteville, Chestnut Street, Rountree Branch Bridge. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-11-01 | 2011-05-31 | 3321000 | 0.090
12721 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2010280 | This is a reconstruction project in Milwaukee County on local streets, South 51st Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-10-08 | 325950 | 0.390
12722 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2010281 | This is a resurfacing project in Milwaukee County on local streets, South 51st Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-10-15 | 1500600 | 1.020
12723 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010282 | This is a reconstruction project in Milwaukee County on local streets, South 1st Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-11-09 | 1959841.35 | 0.690
12724 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010283 | This is a bridge replacement project in Milwaukee County on local streets, South 6th Street Bridge. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2011-01-01 | 2010-12-23 | 2532695.48 | 0.140
12725 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010284 | This is a restoration and rehabilitation project in Milwaukee County on County Highway NN, South 76th Street to South 72nd Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-30 | 496960 | 0.300
12726 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010285 | This is a reconstruction project in Milwaukee County on local streets, South 13th Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-11-03 | 1519230 | 0.620
12727 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 05 | 2010286 | This is a resurfacing project in Milwaukee County on local streets, Burleigh Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2011-09-15 | 959700 | 0.470
12728 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010287 | This is a restoration and rehabilitation project in Milwaukee County on County Highway S, . | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-09-02 | 2236301.74 | 1.700
12729 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 05 | 2010288 | This is a bridge replacement project in Milwaukee County on local streets, 70th Street Bridge. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2011-01-01 | 2011-07-14 | 971700 | 0.070
12730 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OZAUKEE | MILWAUKEE | 05 | 2010289 | This is a restoration and rehabilitation project in Ozaukee County on local streets, West Donges Bay Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-01 | 2010-06-19 | 307500 | 0.690
12731 | Completed | C220,C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010290 | This is a pedestrian and bicycle path project in Waukesha County, Lake County Trail. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-11-08 | 1334885 | 5.437
12732 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010291 | This is a resurfacing project in Waukesha County on local streets, Wisconsin Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-11-24 | 1134970 | 0.500
12733 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010292 | This is a reconstruction project in Waukesha County on County Highway O, South Moorland Blvd. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2011-08-16 | 1906500 | 0.540
12734 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 05 | 2010293 | This is a restoration and rehabilitation project in Milwaukee County on local streets, Fairy Chasm Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-08-12 | 190650 | 0.100
12735 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010294 | This is a bicycle path project in Milwaukee County, Kinnickinnic River Bike Trail. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-07-01 | 2010-08-12 | 430500 | 0.639
12736 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 01 | 2010295 | This is a restoration and rehabilitation project in Milwaukee County on County Highway ZZ, . | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-11-24 | 1449208 | 0.760
12737 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010296 | This is a bridge rehabilitation project in Milwaukee County on local streets, Root River Parkway. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2011-02-01 | 2011-01-15 | 1033738 | 0.700
12738 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010297 | This is a pedestrian and bicycle path project in Milwaukee County, Hank Aaron State Trail. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-10-27 | 1520234 | 0.353
12739 | Underway | C220 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010298 | This is a streetscape project in Milwaukee County, St. Francis. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-11-01 |  | 952881 | 0.830
12740 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010299 | This is a resurfacing project in Brown County on local streets, City of Depere, Jordan Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-20 | 218940 | 0.900
12741 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010300 | This is a restoration and rehabilitation project in Brown County on local streets, City of Green Bay, Manitowoc Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-01 | 2010-07-12 | 810447 | 0.890
12742 | Completed | C250,C240 | Highway Infrastructure Investment Grant | WISCONSIN | CALUMET | APPLETON | 06 | 2010301 | This is a bicycle path project in Calumet County, Town of Harrison, Noe Road Bike and Pedestrian Path. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-26 | 347635 | 1.580
12743 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 2010302 | This is a restoration and rehabilitation project in Winnebago County on local streets, City and Town of Menasha, Manitowoc Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-01 | 2010-07-07 | 460000 | 1.180
12744 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | 08 | 2010303 | This is a pedestrian and bicycle path project in Outagamie County, Greenville Pedestrian Trail. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-10-06 | 667894 | 0.750
12745 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010304 | This is a reconstruction project in Marinette County, Walk-way connection. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-08-27 | 723988 | 0.268
12746 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MARQUETTE |  | 06 | 2010305 | This is a resurfacing project in Marquette County on County Highway CX, Village of Endeavor. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-09-01 | 2010-08-28 | 1260750 | 1.470
12747 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | WAUSHARA |  | 06 | 2010306 | This is a pedestrian and bicycle path project in Waushara County, Wild Rose Roberts Park Trail. | Transportation Enhancements | 2010-02-09 | 2010-02-09 | 2010-08-01 | 2010-08-03 | 246700 | 0.230
12748 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BUFFALO |  | 03 | 2010307 | This is a bridge replacement project in Buffalo County on a town road, Town of Montana, Buells Valley Road. | Bridge Replacement | 2010-02-09 | 2010-02-09 | 2010-08-01 | 2010-08-04 | 223860 | 0.400
12749 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2010308 | This is a bridge replacement project in Trempealeau County on town road, Town of Chimney Rock, Borst Valley Creek Bridge. | Bridge Replacement | 2010-02-09 | 2010-02-09 | 2010-07-01 | 2010-07-15 | 196800 | 0.450
12750 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2010309 | This is a construction project in Polk County, Amery to Dresser Trail. | Transportation Enhancements | 2010-02-09 | 2010-02-09 | 2010-07-01 | 2010-07-27 | 692950 | 10.385
12751 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | POLK |  | 07 | 2010310 | This is a reconstruction project in Polk County on County Highway Y, County Higway M - County Highway F. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-08-01 | 2010-09-15 | 1775000 | 2.360
12752 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2010311 | This is a resurfacing project in Sawyer County on County Highway EE, Draper - Oxbo. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-07-01 | 2010-06-08 | 781980 | 0.390
12753 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | WASHBURN |  | 07 | 2010312 | This is a pedestrian and bicycle path project in Washburn County, Spooner Bicycle and Pedestrian Facility. | Transportation Enhancements | 2010-02-09 | 2010-02-09 | 2010-08-01 | 2010-09-17 | 384990 | 0.735
12754 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS |  | 07 | 2010314 | This is a reconstruction project in Douglas County on County Highway C, State Highway 35 to Kronberg Road. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-09-01 | 2010-09-01 | 1230000 | 3.650
12755 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | TAYLOR |  | 07 | 2010315 | This is a resurfacing project in Taylor County on County Highway O, Lublin - Medford. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-06-01 | 2010-06-10 | 615000 | 3.090
12756 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ASHLAND |  | 07 | 2010316 | This is a resurfacing project in Ashland County on local streets, City of Ashland - 11th Street W. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-08-01 | 2010-07-31 | 287500 | 0.840
12757 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | DOUGLAS | DULUTH-SUPERIOR (MN) | 07 | 2010317 | This is a resurfacing project in Douglas County on local streets, East 5th Street. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-07-01 | 2010-06-25 | 430000 | 0.690
12758 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ASHLAND |  | 07 | 2010318 | This is a resurfacing project in Ashland County on County Highway F, Butternut -County Line Road. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2010-07-01 | 2010-07-01 | 766350 | 5.060
12759 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | IOWA |  | 03 | 2010326 | This is a bridge replacement project in Iowa County on County Highway C, Sneed Creek Bridge and approaches. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-09-13 | 575640 | 0.640
12760 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | IOWA |  | 03 | 2010327 | This is a reconstruction project in Iowa County on County Highway X, Village of Linden, Babcock Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-15 | 237390 | 0.120
12761 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010328 | This is a reconstruction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Pavement Widening | 2010-02-11 | 2010-02-11 | 2011-10-01 | 2011-09-16 | 2042280 | 1.080
12762 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010329 | This is a reconstruction project in Dane County on County Highway M, City of Madison, Pleasant View Road. | Pavement Widening | 2010-02-10 | 2010-02-10 | 2011-10-01 | 2011-09-16 | 3075000 | 1.090
12763 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | DANE | MADISON | 02 | 2010331 | This is a reconstruction project in Dane County on County Highway Q, City of Middleton, Allen Boulevard. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-11-24 | 277140 | 0.100
12764 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010332 | This is a decorative street lighting project in Milwaukee County, South 2nd Street. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-11-01 | 2011-09-08 | 553500 | 0.661
12765 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010333 | This is a resurfacing project in Waukesha County on County Highway ES, Calhoun Road to County Highway O. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-09-20 | 504300 | 1.320
12766 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010334 | This is a resurfacing project in Racine County on local streets, South Memorial Drive. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-11-01 | 2010-12-31 | 667890 | 0.340
12767 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010335 | This is a resurfacing project in Racine County on local streets, North Main Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-11-01 | 2010-11-17 | 569490 | 0.459
12768 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RACINE | RACINE | 01 | 2010336 | This is a resurfacing project in Racine County on County Highway C, Spring Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-11-17 | 376510 | 0.380
12769 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010337 | This is a resurfacing project in Waukesha County on County Highway K, North 132nd Street to North 124th Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-31 | 1044657 | 0.520
12770 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010338 | This is a resurfacing project in Waukesha County on County Highway T, Grandview Blvd. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-08-31 | 270600 | 0.210
12771 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010339 | This is a resurfacing project in Waukesha County on County Highway V, Townline Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-08-31 | 816100 | 3.137
12772 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010340 | This is a new roadway construction project in Waukesha County on County Highway Y, Intersection with County Highway M. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-08-25 | 1230000 | 1.000
12773 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010341 | This is a resurfacing project in Milwaukee County on various highways, City of Milwaukee. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2011-10-01 | 2011-10-31 | 1217932.55 | 0.000
12774 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | Multiple | 2010342 | This is a resurfacing project in Milwaukee County on various highways, City of Milwaukee. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-09-24 | 2320859.08 | 2.262
12775 | Completed | C220,C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 01 | 2010343 | This is a streetscape project in Kenosha County on , East Main Street, County Highway Z. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-11-01 | 2010-11-12 | 460820 | 0.140
12776 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 01 | 2010344 | This is a reconstruction project in Kenosha County on County Highway KD, County Highway F to 70th Place. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2011-02-01 | 2011-07-22 | 571359 | 3.880
12777 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | ROUND LAKE BEACH-MCHENRY GRAVELAKE | 01 | 2010345 | This is a reconstruction project in Kenosha County on County Highway Z, Main Street East. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-11-01 | 2010-11-12 | 514030 | 0.140
12778 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010346 | This is a restoration and rehabilitation project in Kenosha County on local streets, Sheridan Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2011-02-01 | 2010-12-31 | 748400 | 0.490
12779 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2010347 | This is a bridge rehabilitation project in Walworth County on local streets, Wrigley Drive. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2011-06-01 | 2011-08-04 | 738000 | 0.130
12780 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2010348 | This is a bridge rehabilitation project in Walworth County on local streets, Mohawk Road. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-18 | 218940 | 0.057
12781 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2010349 | This is a bridge replacement project in Manitowoc County on a town road, SCL Road. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-12-01 | 2010-11-16 | 378225 | 1.470
12782 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | MANITOWOC |  | 06 | 2010350 | This is a bridge replacement project in Manitowoc County on a town road, South Cleveland Road. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-09-17 | 267279 | 1.660
12783 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KEWAUNEE |  | 08 | 2010351 | This is a restoration and rehabilitation project in Kewaunee County on County Highway A, Town of Luxemburg. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-01 | 2010-08-06 | 512005 | 2.000
12784 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010352 | This is a restoration and rehabilitation project in Brown County on County Highway I, Town of Scott. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-13 | 412418 | 1.170
12785 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO |  | 06 | 2010353 | This is a restoration and rehabilitation project in Winnebago County on County Highway C, Town of Winneconnie - Town of Paygan. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-23 | 1655000 | 7.850
12786 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010354 | This is a reconstruction project in Marinette County on County T, Roosevelt Road - Gallagher Road. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-09-17 | 1353000 | 0.310
12787 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BROWN | GREEN BAY | 08 | 2010355 | This is a restoration and rehabilitation project in Brown County on County Highway EB, Village of Howard. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-19 | 683855 | 2.240
12788 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MARINETTE |  | 08 | 2010356 | This is a reconstruction project in Marinette County on local streets, Shore Drive. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-10-19 | 837630 | 0.530
12789 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | SHAWANO |  | 08 | 2010357 | This is a bridge replacement project in Shawano County on County Highway D, North Branch Embarrass River Crossing. | Bridge Replacement | 2010-02-10 | 2010-02-10 | 2010-11-01 | 2010-10-29 | 608850 | 0.090
12790 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | ONEIDA |  | 07 | 2010358 | This is a reconstruction project in Oneida County on local streets, Phillip Street, City of Rhinelander. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-09-07 | 515000 | 0.210
12791 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | TREMPEALEAU |  | 03 | 2010359 | This is an historic preservation project in Trempealeau County, Whitehall Historic Railroad Depot. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-10-15 | 480930 | 0.140
12792 | Completed | C220,C240 | Highway Infrastructure Investment Grant | WISCONSIN | SAWYER |  | 07 | 2010361 | This is a pedestrian and bicycle path project in Sawyer County, City of Hayward, various locations. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-08-27 | 425000 | 0.809
12793 | Completed | C220,C240 | Highway Infrastructure Investment Grant | WISCONSIN | BAYFIELD |  | 07 | 2010362 | This is a streetscape project in Bayfield County on State Highway 13, Red Cliff - State Highway 13, Streetscape Improvement. | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2011-06-29 | 940950 | 0.230
12794 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2010363 | This is a reconstruction project in Chippewa County on local streets, First Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-10-01 | 2010-09-02 | 541200 | 0.940
12795 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | CHIPPEWA | EAU CLAIRE | 07 | 2010364 | This is a reconstruction project in Chippewa County on County Highway X, 57th Avenue West to 184th Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-01 | 403073 | 0.500
12796 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010365 | This is a reconstruction project in Barron County on local streets, City of Rice Lake, Main Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-09-23 | 2460000 | 3.250
12797 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010366 | This is a reconstruction project in Barron County on local streets, City of Rice Lake, Pioneer Avenue. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-08-01 | 2010-07-30 | 738000.01 | 1.060
12798 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | BARRON |  | 07 | 2010367 | This is a resurfacing project in Barron County on local streets, City of Rice Lake, Haugen Street. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-09-01 | 2010-09-04 | 399750 | 0.830
12799 | Completed | C490 | OJT/SS | WISCONSIN | STATEWIDE |  |  | 2010406 | This is an on the job training project included in the Wisconsin Department of Transportation TrANS Program. This project trains individuals for entry into the highway construction industry by placin | Other | 2010-03-24 | 2010-03-24 | 2010-09-01 | 2012-02-09 | 200000 | 0.000
12800 | Completed | C490 | OJT/SS | WISCONSIN | STATEWIDE |  |  | 2010407 | This is an on the job training project included in the Wisconsin Department of Transportation TrANS Program. This project trains individuals for entry into the highway construction industry by placin | Other | 2010-03-24 | 2010-03-24 | 2010-09-01 | 2011-10-19 | 195148 | 0.000
12801 | Completed | C950 | Ferryboat | WISCONSIN | GRANT |  | 03 | 2010503 | This is the design engineering effort for a ferry boat project in Grant County, the Cassville Ferry. | Other | 2010-03-11 | 2010-03-11 | 2010-06-01 | 2011-07-31 | 25000 | 0.000
12802 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | WAUKESHA | MILWAUKEE | 05 | 2010785 | This is a restoration and rehabilitation project in Waukesha County on Interstate 94, East West Freeway, State Highway 16 to Milwaukee County Line. | Pavement Improvement | 2010-09-15 | 2010-09-15 | 2011-10-01 | 2011-09-30 | 4045073.87 | 0.000
12803 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | RICHLAND |  | 03 | 2010843 | This is a resurfacing project in Richland County on STH 58, USH 14 - Lavalle, USH 14 to CTH N. | Pavement Improvement | 2010-09-15 | 2010-09-15 | 2011-07-28 | 2011-11-16 | 864000 | 4.970
12804 | Completed | C240 | Highway Infrastructure Investment Grant | WISCONSIN | MONROE |  | 03 | 2010844 | This is a resurfacing project in Monroe County on STH 131, Ontario - Tomah, Midway Ave. to CTH M. | Pavement Improvement | 2010-09-15 | 2010-09-15 | 2011-06-24 | 2011-07-30 | 268549 | 0.540
12805 | Completed | C240,C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010845 | This is a bridge rehabilitation project in Milwaukee County on Interstate 94, East West Freeway, 70th Street to 32nd Street. | Bridge Improvement | 2010-09-15 | 2010-09-15 | 2011-10-01 | 2011-09-30 | 2405266 | 0.000
12806 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WISCONSIN | WALWORTH |  | 01 | 2010846 | This is a bridge rehabilitation project in Walworth County on Intersate 43, Rock Freeway, USH 12 to USH 83 Bridges. | Pavement Improvement | 2010-09-15 | 2010-09-15 | 2011-11-01 | 2011-11-15 | 3589000 | 16.120
12807 | Completed | C230 | Highway Infrastructure Investment Grant | WISCONSIN | MILWAUKEE | MILWAUKEE | 04 | 2010847 | This is a restoration and rehabilitation project in Milwaukee County on CTH ZZ, East College Ave., South Pennsylvania Ave. to South Packard Ave. | Pavement Improvement | 2010-09-15 | 2010-09-15 | 2011-09-01 | 2011-12-20 | 2190925 | 1.033
12808 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | KENOSHA | KENOSHA | 01 | 2010848 | This is a reconstruction project in Kenosha County on 14th Ave., City of Kenosha, 25th Street to 31st Street. | Pavement Improvement | 2010-07-28 | 2010-07-28 | 2011-06-01 | 2011-09-02 | 732924.54 | 0.365
12809 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | LINCOLN |  | 07 | 2010849 | This is a resurfacing project in Lincoln County on USH 8, Prentice-Bradley, McCord Road to Klade Road. | Pavement Improvement | 2010-09-15 | 2010-09-15 | 2011-07-01 | 2011-06-17 | 1336000 | 11.640
12810 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WISCONSIN | FLORENCE |  | 08 | 2010850 | This is a restoration and rehabilitation project in Florence County on USH 2, Brule River - Iron Mountain, Michigan State Line to Pewabic Rd. | Pavement Improvement | 2010-09-15 | 2010-09-15 | 2011-07-16 | 2011-08-05 | 508000 | 4.071
12811 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | VILAS |  | 08 | 2010851 | This is a resurfacing project in Vilas County, STH 47, Woodruff - Manitowish, Country Ln to West Bolton Lake Ln. | Pavement Improvement | 2010-09-15 | 2010-09-15 | 2011-07-26 | 2011-07-14 | 1220000 | 6.760
12812 | Completed | C250,C200 | Highway Infrastructure Investment Grant | WISCONSIN | RUSK |  | 07 | 2010852 | This is a rehabilitation project in Rusk County on STH 73, Thorp - Ingram, South County Line to USH 8. | Pavement Improvement | 2010-09-15 | 2010-09-15 | 2011-08-01 | 2011-07-28 | 1829000 | 9.460
12813 | Underway | C950 | Ferryboat | WISCONSIN | GRANT |  | 03 | 2010878 | This is a ferry boat project in Grant County, the Cassville Ferry. | Other | 2010-12-02 | 2010-12-02 | 2011-07-01 |  | 1775000 | 1.153
12814 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | 08 | 3009018 | This is the design engineering effort for a construction project in Outagamie County, Greenville Pedestrian Trail. | Other | 2009-09-10 | 2009-09-10 | 2009-12-15 | 2009-12-15 | 10860 | 0.000
12815 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 3009019 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Neenah, Adams Street. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 8200 | 0.000
12816 | Completed | C220 | Highway Infrastructure Investment Grant | WISCONSIN | CALUMET | APPLETON | 06 | 3009020 | This is the design engineering effort for a construction project in Calumet County, Town of Harrison, Noe Road, Bike and Pedestrian Facilities. | Transportation Enhancements | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 5653 | 0.000
12817 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | OSHKOSH | 06 | 3009021 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Oshkosh, Snell Road. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 6573.54 | 0.000
12818 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 3009022 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Neenah, Wisconsin Avenue. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 7659.73 | 0.000
12819 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | OUTAGAMIE | APPLETON | 08 | 3009023 | This is the design engineering effort for a construction project in Outagamie County on local streets, Village of Little Chute, Washington Street. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 5860 | 0.000
12820 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 3009024 | This is the design engineering effort for a construction project in Winnebago County on local streets, City and Town of Menasha, Manitowoc Road. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 5539.53 | 0.000
12821 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | WINNEBAGO | APPLETON | 06 | 3009025 | This is the design engineering effort for a construction project in Winnebago County on local streets, City of Menasha, Tayco Street. | Other | 2009-09-10 | 2009-09-10 | 2009-12-01 | 2009-12-01 | 6292.28 | 0.000
12822 | Completed | C200 | Highway Infrastructure Investment Grant | WISCONSIN | ROCK | BELOIT (IL) | 01 | 3009145 | This is the design engineering effort for a construction project in Rock County on Town Road, Town of Turtle Townline. | Other | 2009-09-21 | 2009-09-21 | 2009-12-01 | 2009-12-01 | 3200 | 0.000
12823 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | LINCOLN |  |  | 0007035 | Construction of retaining walls on US 189 in Diamondville in Lincoln County. | Transportation Enhancements | 2009-05-20 | 2009-08-20 | 2010-07-31 | 2009-10-03 | 204160 | 0.000
12824 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | 0200028 | Pavement overlay on approximately 14 miles of WYO 30 between Basin and Burlington in Big Horn County. | Pavement Improvement | 2009-05-06 | 2009-04-08 | 2010-06-30 | 2010-09-03 | 1528810 | 13.790
12825 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | CAMPBELL |  |  | 0300044 | Pavement overlay of 12 miles of WYO 50 between Gillette and Pine Tree Junction in Campbell County. | Pavement Improvement | 2009-08-21 | 2010-04-26 | 2010-10-31 | 2010-10-08 | 2323924.49 | 6.790
12826 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | CAMPBELL |  |  | 0300045 | Pavement overlay of 12 miles of WYO 50 between Gillette and Pine Tree Junction in Campbell County. | Pavement Improvement | 2009-08-21 | 2010-04-26 | 2010-10-31 | 2010-10-08 | 1510815 | 5.300
12827 | Completed | C200 | Highway Infrastructure Investment Grant | WYOMING | GOSHEN |  |  | 0800010 | Pipe, curb and gutter, and sidewalk replacement on 0.38 miles of WYO 151 in the Town of Lagrange in Goshen County, Wyoming. | Other | 2009-05-19 | 2009-09-14 | 2009-09-30 | 2010-12-22 | 96546.21 | 0.530
12828 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | CROOK |  |  | 0904121 | Pavement overlay of 7 miles of I-90 between Sundance and the South Dakota State Line in Crook County. | Pavement Improvement | 2009-05-08 | 2009-04-30 | 2010-07-31 | 2010-05-17 | 6121771 | 7.000
12829 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | NATRONA |  |  | 1301018 | Drainage repairs of pipe locations on WYO 251 (Casper Mountain Road) in Natrona County. | Other | 2009-05-11 | 2009-09-25 | 2009-10-31 | 2010-10-14 | 331222.48 | 0.000
12830 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | PARK |  |  | 1501007 | Pavement overlay on approximately 7 miles of WYO 291 between Cody and South Fork in Park County. | Pavement Improvement | 2009-07-14 | 2009-06-25 | 2010-09-15 | 2010-07-16 | 3143873.48 | 6.660
12831 | Underway | C200 | Highway Infrastructure Investment Grant | WYOMING | SHERIDAN |  |  | 1701013 | Replace right-of-way fence on 2.24 miles of WYO 331 between Sheridan and Beckton in Sheridan County. | Other | 2009-05-11 | 2009-12-22 | 2010-10-31 |  | 81527.2 | 2.200
12832 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | WYOMING | SWEETWATER |  |  | 1903022 | GRAD, DRAIN, MILL PLANT MIX, PLAC CRUSHED BASE & BIT PAVE SURF, BRIDGE REHAB, SIGN, REMOV & REPLAC OF GRDRL & FENC, & MISC WORK | Pavement Improvement | 2010-10-15 | 2010-11-18 | 2011-10-31 |  | 2461384.93
12833 | Completed | C250,C240 | Highway Infrastructure Investment Grant | WYOMING | WESTON |  |  | 2302011 | Pavement overlay and bridge rehabilitation on WYO 116 north of WYO 450 in Weston County. | Pavement Improvement | 2009-05-06 | 2009-05-05 | 2010-10-31 | 2010-10-29 | 6252309.28 | 7.290
12834 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | 6598005 | Sidewalk and curb and guter replacement on Harrison Drive in Evanston, Wyoming. | Transportation Enhancements | 2009-08-18 | 2009-09-14 | 2010-08-31 | 2010-12-01 | 341402 | 0.310
12835 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B045012 | Bridge preventive maintenance at various locations in Wyoming Transportation District 5. | Bridge Improvement | 2009-05-11 | 2009-08-24 | 2009-09-30 | 2009-09-01 | 90753.63
12836 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B082008 | Preventive maintenance (contract patching) and miscellaneous work at various locations in Wyoming Transportation District 2. | Pavement Improvement | 2009-06-24 | 2009-09-14 | 2010-09-30 | 2010-05-27 | 3291202 | 35.000
12837 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | B085011 | Fence replacement on approximately 11 miles of US 14 east and west of Greybull in Big Horn and Park Counties. | Other | 2009-05-13 | 2009-06-29 | 2009-09-30 | 2010-01-05 | 460590
12838 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B091005 | Preventive Maintenance, Crack sealing on 85.15 miles of various highways in District 1. | Pavement Improvement | 2009-05-19 | 2009-11-02 | 2010-04-30 | 2010-04-16 | 569576
12839 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B091008 | Preventive Maintenance, Bituminous Pavement Patches at various locations in District 1. | Pavement Improvement | 2009-05-19 | 2009-06-25 | 2009-09-30 | 2009-10-25 | 680557.08
12840 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | B095014 | Preventive maintenance (crack seal) on 125 miles of various roads in Wyoming Transportation District 5. | Pavement Improvement | 2009-05-11 | 2009-11-16 | 2010-03-31 | 2010-03-03 | 897140
12841 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B151002 | Preventive Maintenance, Chip Seals on various roadways in District 1. | Pavement Improvement | 2009-05-20 | 2009-07-07 | 2010-08-31 | 2010-08-16 | 3701395
12842 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B152005 | Preventive maintenance (chip seal) and miscellaneous work on approzimately 84 miles of highway in Wyoming Transportation District Two. | Pavement Improvement | 2009-05-11 | 2009-06-10 | 2010-08-31 | 2011-02-02 | 2455115.6
12843 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B152006 | Preventive maintenance (crack seal) and miscellaneous work on approximately 367 miles of highway in Wyoming Transporatation District 2. | Pavement Improvement | 2009-08-04 | 2009-09-14 | 2010-05-31 | 2010-05-17 | 3338509.79
12844 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | STATEWIDE |  |  | B152009 | Bridge preventive maintenance and miscellaneous work at various locations in Wyoming Transportation District 2. | Bridge Improvement | 2009-12-03 | 2010-03-09 | 2010-10-31 |  | 1267475
12845 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | LARAMIE |  |  | I180017 | Install a new pedestrian railing and upgrade the lighting system on I-180 in Cheyenne. | Transportation Enhancements | 2009-05-08 | 2009-06-17 | 2009-11-30 | 2010-05-04 | 953556 | 0.000
12846 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | LARAMIE | CHEYENNE |  | I251164 | MILL, GRADE, DRAIN, PLACE CRUSHED BASE & BITUMINOUS PAVE SURFACING, CONCRETE PAVEMENT, STRUCTURE, ELECTRICAL, ENHANCEMENTS & MISC | Transportation Enhancements | 2010-10-28 | 2010-10-27 | 2011-10-31 | 2011-10-31 | 6500
12847 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | PLATTE |  |  | I252157 | Landscaping and miscellaneous work at the Dwyer Junction Rest at the intersection of US 26 and I-25 in Platte County. | Transportation Enhancements | 2009-10-12 | 2010-03-29 | 2010-07-31 | 2010-07-01 | 144235 | 0.000
12848 | Underway | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | I801175 | Bridge maintenance and rehabilitation at various location on I-80 in Uinta County. | Bridge Improvement | 2009-08-18 | 2010-05-10 | 2010-08-31 |  | 621915 | 0.000
12849 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | I801176 | Preventive pavement maintenance and miscellaneous work on 23.20 miles of I-80 between Carter and LaBarge in Sweetwater and Uinta Counties. | Pavement Improvement | 2009-06-10 | 2010-06-07 | 2010-09-30 | 2010-08-21 | 2764193
12850 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | I801177 | Preventive pavement maintenance and rehabilitation of 28.10 miles of I-80 beginning at the Utah State Line in Uinta County. | Pavement Improvement | 2009-05-27 | 2009-07-23 | 2010-09-30 | 2010-10-10 | 10168301 | 28.100
12851 | Completed | C200 | Highway Infrastructure Investment Grant | WYOMING | SWEETWATER |  |  | I802192 | Concrete Pavement Rehabilitation on 15.34 miles of I-80 between Green River and Rock Springs in Sweetwater County. | Pavement Improvement | 2009-06-24 | 2010-04-12 | 2010-09-30 | 2010-08-07 | 7264004 | 15.370
12852 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | SWEETWATER |  |  | I803140 | Preventive pavement maintenance and miscellaneous work on 33.50 miles of I-80 east of Rock Springs in Sweetwater County. | Pavement Improvement | 2009-05-27 | 2009-06-01 | 2010-09-30 | 2009-08-24 | 3868970 | 34.000
12853 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WYOMING | CARBON |  |  | I804245 | Pavement resurfacing of 6.39 miles of I-80 east of Sinclair in Carbon County. | Pavement Improvement | 2009-06-24 | 2009-06-22 | 2010-08-31 | 2009-10-09 | 4888262.2 | 6.229
12854 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WYOMING | ALBANY |  |  | I804250 | Preventive Maintenance, Replace Snow Fence along 23.35 miles of I-80 in Albany and Carbon Counties. | Other | 2009-06-11 | 2009-06-23 | 2010-09-15 | 2010-10-28 | 5190172 | 23.250
12855 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | CARBON |  |  | I804251 | Pavement resurfacing and bridge repair along 13.04 miles of I-80 near Elk Mountain. | Pavement Improvement | 2009-10-01 | 2010-02-08 | 2010-10-31 | 2010-09-14 | 2506893 | 5.060
12856 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | ALBANY |  |  | I805165 | Preventive Maintenance, Installation of a friction course on I-80 in Telephone Canyon east of Laramie. | Pavement Improvement | 2009-06-24 | 2010-07-12 | 2010-09-30 | 2010-08-20 | 2039663 | 5.170
12857 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | JOHNSON |  |  | I902118 | Pavement overlay and surface treatment on 6.2 miles of I-90 between Buffalo and Gillette in Johnson County. | Pavement Improvement | 2009-05-20 | 2009-05-12 | 2010-07-15 | 2009-11-12 | 3541525 | 6.200
12858 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | JOHNSON |  |  | I902119 | Pavement overlay and surface treatment on 6.2 miles of I-90 between Buffalo and Gillette in Johnson County. | Pavement Improvement | 2009-05-20 | 2009-05-12 | 2010-07-15 | 2009-11-12 | 4576050.35 | 8.000
12859 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | CROOK |  |  | I904130 | Pavement preventive maintenance on 12.7 miles of I-90 between Moorcroft and Sundance in Crook County. | Pavement Improvement | 2009-06-10 | 2009-05-28 | 2010-06-30 | 2009-11-03 | 2545187.3 | 12.710
12860 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | TETON |  |  | N104084 | Bike path construction along US 26/189/191 north of Jackson, Wyoming. | Transportation Enhancements | 2009-09-28 | 2010-04-03 | 2011-10-31 | 2010-09-17 | 1000000 | 1.140
12861 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N202062 | Rest Area rehabilitation of the Sweetwater Station Rest Area between Muddy Gap and Lander. | Other | 2009-06-10 | 2009-07-09 | 2010-08-27 | 2010-08-27 | 466839
12862 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N202067 | Landscaping in the Lander Highway Park along US 287 in Lander in Fremont County. | Transportation Enhancements | 2009-11-09 | 2010-05-17 | 2010-06-01 | 2010-05-23 | 48500 | 0.000
12863 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N203063 | Pavement overlay of approximately 4 miles of US 26 between Riverton and Shoshoni in Fremont County. | Pavement Improvement | 2009-05-20 | 2009-06-25 | 2010-09-30 | 2009-08-17 | 1578018.07 | 4.910
12864 | Completed | C200 | Highway Infrastructure Investment Grant | WYOMING | PARK |  |  | N291036 | Pavement reconstruction and widening of 3.85 miles of US 14A between Cody and Powell in Park County. | Pavement Widening | 2009-06-24 | 2009-06-22 | 2010-10-15 | 2010-10-15 | 10906590.22 | 3.620
12865 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N303049 | Rest Area rehabilitation of the Diversion Dam Rest Area between Diversion Dam Junction and Dubois. | Other | 2009-06-10 | 2009-07-09 | 2010-08-27 | 2010-08-27 | 523873 | 0.000
12866 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N312013 | Safety improvements including slope flattening and guardrail upgrades on 1.48 miles of US 14/16 between Cody and Greybull. | Safety/Traffic Management | 2009-06-10 | 2009-07-06 | 2009-10-15 | 2009-10-15 | 366818.83 | 1.480
12867 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | HOT SPRINGS |  |  | N331025 | Rest Area rehabilitation of the Gooseberry Creek Rest Area between Thermopolis and Meeteetse. | Other | 2009-06-10 | 2009-07-09 | 2010-08-27 | 2010-08-27 | 388249 | 0.000
12868 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | NATRONA |  |  | N341105 | Rest Area rehabilitation of the Waltman Rest Area between Casper and Shoshoni. | Other | 2009-06-10 | 2009-07-09 | 2010-08-27 | 2010-08-27 | 248366 | 0.000
12869 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | N342042 | Pavement overlay on 11 miles of US 26 between Casper and Shoshoni in Fremont County. | Pavement Improvement | 2009-08-18 | 2009-10-21 | 2010-09-30 | 2010-09-23 | 3323603 | 11.000
12870 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345080 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Safety/Traffic Management | 2009-06-11 | 2009-06-10 | 2010-10-31 | 2010-11-04 | 874253 | 5.099
12871 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345089 | Rest Area rehabilitation of the Greybull Rest Area northwest of Greybull. | Other | 2009-06-10 | 2009-07-09 | 2010-08-27 | 2010-08-27 | 365613 | 0.000
12872 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345095 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Pavement Improvement | 2009-06-11 | 2009-06-10 | 2010-10-31 | 2010-11-04 | 1718433 | 4.990
12873 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345096 | Pavement overlay on approximately 6 miles of US 16.20 between Manderson and Basin in Big Horn County. | Pavement Improvement | 2009-08-18 | 2009-08-19 | 2010-09-30 | 2010-09-03 | 1345965.96 | 6.049
12874 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | BIG HORN |  |  | N345101 | Pavement overlay, guardrail improvements, and the installation of deer delineators on US 16/20/WYO789 between Basin and Greybull in Big Horn County. | Safety/Traffic Management | 2009-06-11 | 2009-06-10 | 2010-10-31 | 2010-11-04 | 131146.03 | 7.000
12875 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | WYOMING | WASHAKIE |  |  | N361061 | RECONSTRUCTION | Pavement Improvement | 2010-09-10 | 2010-09-16 | 2010-10-31 | 2011-10-31 | 5562062.08
12876 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | NIOBRARA |  |  | N402016 | Pavement widening and overlay on 9.90 miles of US 18/20 between Lusk and Manville in Niobrara County. | Pavement Improvement | 2009-05-27 | 2009-05-19 | 2010-10-31 | 2010-11-20 | 12017032 | 10.000
12877 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | WESTON |  |  | N442066 | Enhancements to US 16 (Upton Main Street) including landscaping, sidewalk, curb and gutter, in Weston County. | Transportation Enhancements | 2009-08-17 | 2009-12-04 | 2010-10-31 | 2010-11-01 | 150000 | 1.250
12878 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | GOSHEN |  |  | N853084 | Pavement overlay and miscellaneous work on 9.51 miles of US 85 north of Lagrange in Goshen County. | Pavement Improvement | 2009-05-20 | 2009-06-09 | 2010-08-31 | 2010-08-31 | 3343449 | 9.750
12879 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | NIOBRARA |  |  | N854071 | Pavement overlay and bridge repair of 5 miles of US 85 between Newcastle and Mule Creek Junction in Niobrara County. | Pavement Improvement | 2009-08-04 | 2010-04-12 | 2010-10-31 | 2010-07-19 | 2021619.73 | 6.650
12880 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | LINCOLN |  |  | P112021 | Construction of retaining walls on US 189 in Diamondville in Lincoln County. | Transportation Enhancements | 2009-05-20 | 2009-08-20 | 2010-07-31 | 2009-10-03 | 250000 | 0.000
12881 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | P142041 | Rest Area rehabilitation of the South Pass Rest Area between Farson and Lander. | Other | 2009-06-10 | 2009-07-09 | 2010-08-27 | 2010-08-27 | 450785 | 0.000
12882 | Completed | C220,C240 | Highway Infrastructure Investment Grant | WYOMING | CARBON |  |  | P182029 | Pavement rehabilitation and installation of a wildlife underpass on WYO 789 south of Creston Junction. | Pavement Improvement | 2009-06-11 | 2009-06-11 | 2010-10-31 | 2009-09-11 | 1071737 | 4.000
12883 | Completed | C200 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | P341108 | Pavement rehabilitation, sidewalk replacement and curb and gutter replacement, and bridge repair on Casper Streets in Natrona County. | Pavement Improvement | 2009-05-20 | 2009-05-18 | 2010-10-31 | 2010-10-14 | 2508438 | 1.090
12884 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | P501001 | Pavement overlay and miscellaneous work on 10.45 miles of WYO 89 north of Evanston in Uinta County. | Pavement Improvement | 2009-06-11 | 2009-08-12 | 2010-09-30 | 2009-12-04 | 3164371.21 | 10.480
12885 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | UINTA |  |  | P511018 | Sidewalk and curb and guter replacement on Harrison Drive in Evanston, Wyoming. | Transportation Enhancements | 2009-08-18 | 2009-09-14 | 2010-08-31 | 2010-12-01 | 169715 | 0.310
12886 | Completed | C200,C240 | Highway Infrastructure Investment Grant | WYOMING | LARAMIE |  |  | P561028 | Reconstruct West Lincolnway (US-30) in Cheyenne. | Pavement Improvement | 2009-07-20 | 2009-07-25 | 2010-10-15 | 2011-01-27 | 9289380 | 1.289
12887 | Completed | C240 | Highway Infrastructure Investment Grant | WYOMING | CONVERSE |  |  | P581025 | Landscaping and miscellaneous work on US 20/26/87 in the City of Douglas. | Transportation Enhancements | 2009-10-12 | 2010-05-10 | 2010-07-31 | 2010-09-24 | 81558 | 0.759
12888 | Underway | C200,C240 | Highway Infrastructure Investment Grant | WYOMING | GOSHEN |  |  | S805006 | GRADING, MILLING PLANT MIX, PLACING CRUSHED BASE & BITUMINOUS PAVEMENT SURFACING, CONCRETE PAVEMENT, FENCING AND MISC WORK | Pavement Improvement | 2010-11-19 | 2011-01-12 | 2011-10-31 |  | 120155.85
12889 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | NATRONA |  |  | TL09003 | Construction of an underpass for bikeway/pathway in Casper, Wyoming. | Transportation Enhancements | 2009-10-23 | 2010-03-17 | 2012-02-16 | 2010-09-07 | 250000
12890 | Completed | C220 | Highway Infrastructure Investment Grant | WYOMING | FREMONT |  |  | TL09008 | Construction of a travelers information center in Lander, Wyoming in Fremont County. | Transportation Enhancements | 2009-11-10 | 2010-04-05 | 2012-02-16 | 2010-09-24 | 350000
12891 | Underway | C220 | Highway Infrastructure Investment Grant | WYOMING | PARK |  |  | TL09010 | Rehabilitation and landscaping of the Powell Rest Area in Powell, Wyoming in Park County. | Transportation Enhancements | 2010-01-22 | 2010-03-29 | 2012-02-16 |  | 1300000
12892 | Completed | CT10 | Highway Infrastructure Investment Grant | AMERICAN SAMOA | AMERICAN SAMOA |  |  | 0001061 | Resurfacing, Restoration and drainage improvement | Pavement Improvement | 2009-11-16 | 2009-11-16 | 2010-07-13 | 2010-07-13 | 4500000
12893 | Underway | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0002104 | This project replaces culverts at three locations (Sella Bay, Cetti Bay, and Umatac Baseball Field) and installs a concrete safety wall along the side of the road to prevent rocks and debris from fall | Other | 2010-05-05 | 2010-05-05 |  |  | 1432000
12894 | Underway | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0004012 | This project is located on Route 4 from Ylig Bridge to Pago Bay. Within the project limits, the road will be repaved and paved shoulders will be installed. | Other | 2010-09-28 | 2010-09-28 |  |  | 4668000
12895 | Underway | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0006011 | This project is located at the Masso River Bridge on Assumtion Road near the intersection with Route 6. This project will fix the river embankment and prevent further erosion. | Other | 2011-05-12 | 2011-05-12 |  |  | 200000
12896 | Underway | CT10 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0017102 | This project is located on Route 17 from Route 4 to Route 4A. Within the project limits, the road will be repaved and paved shoulders will be installed. | Other | 2010-11-08 | 2010-11-08 |  |  | 5200000
12897 | Underway | C230 | Highway Infrastructure Investment Grant | GUAM | STATEWIDE |  |  | 0025101 | This project is located on Route 25 from Bello Road to Route 26. Within the project limits, the road will be repaved and widened to include paved shoulders. For sections of the road, a third lane (t | Other | 2010-05-06 | 2010-05-06 |  |  | 6500000
12898 | Underway | C490 | OJT/SS | GUAM | GUAM |  |  | JTSS001 | Develop a Sustainable Training Program in highway construction and transportation related fields for Guam. Participants of the Program will receive basic and remedial training, on-the-job training, an | Other | 2010-07-30 | 2010-07-30 |  |  | 900000
12899 | Underway | C490 | OJT/SS | GUAM | GUAM |  |  | JTSS002 | Provide Pacific Islanders and women specialized training in either highway construction, construction inspection, CADD or other highway careers in order to increase their participation in the Federal- | Other | 2011-09-22 | 2011-09-22 |  |  | 660000
12900 | Completed | CT10 | Highway Infrastructure Investment Grant | NORTHERN MARIANA | STATEWIDE |  |  | 0031014 | Reconstruction and widening of Route 31, Phase II-A. This project involves reconstructing existing roadway to upgrade the pavement structure. The project includes excavation and backfilling, construct | Other | 2009-11-13 | 2010-08-16 | 2011-08-04 | 2011-08-04 | 3457700 | 1.500
12901 | Obligated and Awarded | CT10 | Highway Infrastructure Investment Grant | NORTHERN MARIANA | STATEWIDE |  |  | 0031015 | CROSS ISLAND ROAD, PHASE IIB, RECON, WIDENING & DRAINAGE IMPR APPR 1.73 MI FROM 500 FT PAST INTXN W/ KAGMAN RD TO INTXN W/TALOFOFO | Other |  |  |  |  | 1042300
12902 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  | AGUDILLA |  | 0002040 | This project consists of the replacement of BRIDGE NO. 763 ON PR-2 KM 127.4, over HIGHWAY PR-2R, in the municipality of Aguadilla, PR. | Pavement Improvement | 2009-08-04 | 2009-08-14 | 2010-12-06 |  | 6250809.76 | 0.490
12903 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  | PONCE |  | 0002051 | This project consists of the construction of a new interchange as part of the conversion of PR-2 to expressway. The project is located in the Punto Oro area, Ponce, PR. | Pavement Widening | 2010-02-10 | 2010-02-22 | 2012-08-09 |  | 18131172.55 | 0.618
12904 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 0010061 | The project consist in a new bridge construction for PR-10 over Rio Grande de Arecibo and PR-123. The project is in the municipality of Adjuntas. | New Bridge Construction | 2010-08-02 | 2010-08-12 | 2012-06-01 |  | 9511801.55 | 0.162
12905 | Completed | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  | SAN JUAN |  | 0020007 | This project consists of replacing damaged bearing pads under the bridge on PR-20, to raise it to its original grade and elevation. It also includes repairs to the bridge deck. It is located in Guay | Bridge Improvement | 2009-10-20 | 2009-10-30 | 2010-03-18 | 2010-03-30 | 571557.5 | 0.073
12906 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  | MAYAGUEZ |  | 0102012 | This project consists of reconstructing and widening to four lanes of road PR-64 from PR-2 to PR-102 in "El Mani" sector of the municipality of Mayaguez. | Pavement Widening | 2010-03-16 | 2010-03-26 | 2012-03-14 |  | 11765492.1 | 1.920
12907 | Completed | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 0173008 | This project consists of the realignment of highway PR-173 at KM 3.0 in the municipality of Cidra. This road was affected by a landslide. | Pavement Improvement | 2009-10-26 | 2009-11-05 | 2010-04-03 | 2010-10-05 | 413820.74 | 0.152
12908 | Completed | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999087 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's North Region Unit I, in | Pavement Improvement | 2010-05-07 | 2010-05-17 | 2011-05-11 | 2011-05-11 | 3594572.19 | 9.625
12909 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999088 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region, Unit I in | Bridge Improvement | 2009-07-29 | 2009-08-10 | 2010-08-04 |  | 2550533.9 | 3.181
12910 | Completed | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999089 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit I, in t | Pavement Improvement | 2010-03-05 | 2010-03-15 | 2011-03-09 | 2011-03-09 | 3421243 | 13.820
12911 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999090 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's West Region Unit I, in t | Pavement Improvement | 2010-04-06 | 2010-04-16 | 2011-04-11 |  | 1890118.15 | 1.758
12912 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999091 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's Metro Region Unit I in | Pavement Improvement | 2010-03-03 | 2010-03-15 | 2011-01-08 |  | 2448298 | 3.900
12913 | Completed | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999092 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region Unit II in | Pavement Improvement | 2009-07-21 | 2009-07-31 | 2010-08-24 | 2010-08-24 | 3754034.4 | 18.026
12914 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999093 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's South Region Unit III in | Pavement Improvement | 2009-07-02 | 2009-07-13 | 2010-07-07 |  | 3450360.2 | 12.505
12915 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999094 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's North Region Unit II in | Pavement Improvement | 2010-04-30 | 2010-05-10 | 2011-05-04 |  | 3209726.22 | 4.009
12916 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999095 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's North Region Unit III in | Pavement Improvement | 2010-04-30 | 2010-05-10 | 2011-05-04 |  | 4537710.83 | 7.750
12917 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999096 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit II, in | Pavement Improvement | 2010-03-05 | 2010-03-15 | 2011-03-09 |  | 3238545 | 3.622
12918 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999097 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit III in | Pavement Improvement | 2010-02-10 | 2010-02-22 | 2010-10-19 |  | 2586975 | 7.750
12919 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999098 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's East Region Unit IV in t | Pavement Improvement | 2010-03-05 | 2010-03-15 | 2010-11-09 |  | 1415929 | 5.500
12920 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999099 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's West Region Unit II in t | Pavement Improvement | 2010-04-06 | 2010-04-16 | 2011-04-10 |  | 2200047.44 | 1.388
12921 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999100 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's West Region Unit III in | Pavement Improvement | 2010-04-06 | 2010-04-16 | 2011-08-08 |  | 4798316.35 | 9.098
12922 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999101 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's Metro Region Unit II in | Pavement Improvement | 2010-03-15 | 2010-03-25 | 2011-01-18 |  | 2300739 | 10.500
12923 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999102 | This project consists of the repair of small landslides, pavement surfaces, drainage, guard rail, pavement markings and miscellaneous items along various routes on the PRHTA's Metro Region Unit III in | Pavement Improvement | 2010-03-15 | 2010-03-25 | 2011-03-19 |  | 3220989 | 9.756
12924 | Underway | CP10 | Highway Infrastructure Investment Grant | PUERTO RICO |  |  |  | 9999117 | The project consits in Pavement Rehabilitation and Minor Repairs on Region South Unit IV. Works will be performed on PR-2 from Km. 208.7 to Km. 213.2 in the municipalities of Guayanilla and Peñuelas. | Pavement Improvement | 2010-11-04 | 2010-11-04 | 2012-02-26 |  | 9726041.84 | 2.820
12925 | Underway | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 0032008 | This project proposes to improve pedestrian mobility by constructing sidewalks, installing new crosswalks, new pedestrian crossing signs and installing new roadway striping from the Red Hook Marine Te | Other | 2010-01-11 | 2010-01-11 | 2010-05-21 |  | 1050359.96 | 0.350
12926 | Underway | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 0070011 | This project proposes to repave 2 miles of asphalt roadway along the eastern section of Queen Mary Highway. The project will also make improvements to prevent flooding on the roadway. | New Construction | 2009-10-16 | 2009-10-29 | 2010-10-28 |  | 4859669.4 | 2.050
12927 | Underway | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 0104003 | This project proposes to repave over 2 miles of asphalt roadway. The project will also replace culverts and pipes along the roadway to prevent flooding of the road. The project will install pedestrian | New Construction | 2009-10-05 | 2009-10-05 | 2010-07-02 |  | 4782469 | 2.830
12928 | Obligated and Not Awarded | C950 | Ferryboat | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 032M001 | Acquisition of two 150 - 300 passenger, Ferry Boats for STT/STJ Ferry Service | Other |  |  |  |  | 3000000
12929 | Obligated and Not Awarded | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 9999120 | The replacement of damaged guardrails along Route 66, Melvin Evans Highway, St. Croix, U.S. Virgin Islands | New Construction |  |  |  |  | 819130.75
12930 | Underway | CT10 | Highway Infrastructure Investment Grant | VIRGIN ISLANDS | VIRGIN ISLANDS |  |  | 9999121 | The replacement of damaged guardrails and signage along Routes 30 & 42 on the islandof St Thomas and along Routes 10 & 107 on the island of St John. | Safety/Traffic Management | 2011-02-07 |  | 2011-08-05 |  | 951215.89

## Federal Lands
Row | Status | Federal Lands Division | Program | State | County | Urban Area | Cong. District | Project # | Project Description | Improvement Type | Proceed Date | Work Start date | Estimated Completion date | Work Complete Date | Recovery Act Obigations
1 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | POTTAWATOME |  | 4 | 0000408804 | CITIZEN BAND OF POTAWATOMI - GORDON COOPER DRIVE OVERLAY | Pavement Improvement |  | 2010-07-19 | 2010-08-31 | 2010-10-15 | 1746461
2 | Completed | (BIA) IRR | Federal Lands | NORTH DAKOTA | MCKENZIE | Region A | 1 | A04353ER | THREE AFFILIATED TRIBES - ASPHALT PATCH AND CHIP SEAL | Safety/Traffic Management | 2010-06-04 | 2010-06-04 | 2010-07-21 | 2010-07-21 | 1016893
3 | Completed | (BIA) IRR | Federal Lands | NORTH DAKOTA | RAMSEY | Region A | 1 | A05660ER | SPIRIT LAKE TRIBE - MULTIROUTE STRIPING | Safety/Traffic Management | 2010-06-30 |  | 2010-11-15 | 2010-11-15 | 49784.84
4 | Underway | (BIA) IRR | Federal Lands | SOUTH DAKOTA | TODD | Region A | 1 | A07115ER | ROSEBUD SIOUIX TRIBE - SOLDIER CREEK HOUSING STREETS | Pavement Improvement | 2010-05-25 |  |  |  | 2314897
5 | Completed | (BIA) IRR | Federal Lands | NEBRASKA | KNOX | Region A | 3 | A08316ER | PONCA TRIBE - AGENCY PROPERTY ROAD | Other | 2010-06-23 | 2010-06-23 | 2010-10-30 | 2010-10-30 | 654216
6 | Completed | (BIA) IRR | Federal Lands | SOUTH DAKOTA | CHARLES MIX | Region A | 1 | A08351ER | YANKTON SIOUX TRIBE - BIA ROUTE 30 BASE & BLOTTER | Pavement Improvement | 2010-05-18 | 2010-05-18 |  | 2010-07-22 | 952449
7 | Completed | (BIA) IRR | Federal Lands | SOUTH DAKOTA | ROBERTS | Region A | 1 | A09445ER | SISSETON-WAHPETON - BIA 3 BUFFALO LAKE ROAD OVERLAY | Pavement Improvement | 2009-10-14 |  |  | 2010-08-18 | 943751.86
8 | Completed | (BIA) IRR | Federal Lands | SOUTH DAKOTA | ROBERTS | Region A | 1 | A09760ER | SISSETON-WAHPETON - PEEVER FLATS ACCESS ROAD | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2011-05-01 | 2010-08-31 | 573781.45
9 | Underway | (BIA) IRR | Federal Lands | SOUTH DAKOTA | BUFFALO | Region A | 1 | A14809ER | CROW CREEK SIOUX TRIBE - FT THOMPSON SOUTHEAST | Other | 2010-06-28 |  |  |  | 1741937.14
10 | Completed | (BIA) IRR | Federal Lands | TEXAS | MAVERICK | Region B | 23 | B00R8261 | KICKAPOO TRADITIONAL TEXAS - R - SUBDIVISION ROAD | New Construction |  | 2010-10-04 | 2011-12-31 | 2010-12-30 | 76895
11 | Underway | (BIA) IRR | Federal Lands | TEXAS | POLK | Region B | 2 | B00R8301 | ALABAMA-COUSHATTA TEXAS - BLACK LAKE LOOP | Other | 2010-05-17 |  | 2011-12-31 |  | 65321
12 | Completed | (BIA) IRR | Federal Lands | KANSAS | DONIPHAN | Region B | 2 | B04R8601 | IOWA TRIBE OF KS & NE - R - SAFETY IMPROVEMENT PROJECT | Safety/Traffic Management |  | 2010-07-26 | 2011-12-31 | 2010-09-30 | 87962
13 | Completed | (BIA) IRR | Federal Lands | KANSAS | BROWN | Region B | 2 | B04R8611 | KICKAPOO TRIBE IN KANSAS - DESIGN ROAD 130 | Other |  |  | 2012-09-01 | 2011-05-31 | 97624
14 | Completed | (BIA) IRR | Federal Lands | KANSAS | FINNEY | Region B | 2 | B04R8621 | PRAIRIE BAND OF POTAWATOMI R - 126 AND O ROAD | Safety/Traffic Management | 2010-06-18 | 2010-07-12 | 2011-12-31 | 2010-10-20 | 64296
15 | Completed | (BIA) IRR | Federal Lands | KANSAS | JACKSON | Region B | 2 | B04R8622 | PRAIRIE BAND OF POTAWATOMI - R - 174 RD & H.5 HILL CUT | Safety/Traffic Management | 2010-06-17 | 2010-07-12 | 2011-12-31 | 2010-09-28 | 169642
16 | Completed | (BIA) IRR | Federal Lands | KANSAS | BROWN | Region B | 2 | B04R8631 | SAC & FOX OF MISSOURI IN KANSAS - R - CHIP SEAL ROUTE 708 | Other |  |  | 2011-12-31 | 2011-07-15 | 35384
17 | Obligated and Awarded | (BIA) IRR | Federal Lands | OKLAHOMA | CUSTER | Region B |  | B05R8012 | CHEYENNE & ARAPAHO TRIBE - IRR ROADWAY DESIGN PROJECTS | Other |  |  | 2011-12-31 |  | 751740
18 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | CADDO | Region B | 03 | B06R8041 | WICHITA AND AFFILIATED TRIBES - R - EAST RIVERSIDE ROAD OVERLAY | Pavement Improvement | 2010-05-17 | 2010-07-15 | 2010-09-30 | 2010-10-14 | 508857
19 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | CADDO | Region B | 03 | B06R8061 | CADDO NATION - R - PONJO ROAD OVERLAY | Pavement Improvement | 2010-05-25 | 2010-08-05 | 2010-09-30 | 2010-09-01 | 996390
20 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | COMANCHE | Region B |  | B06R8081 | COMANCHE NATION - EAST CACHE CREEK BRIDGE | Bridge Improvement | 2010-06-30 | 2010-06-30 | 2010-12-27 | 2011-03-31 | 745021
21 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | CADDO | Region B | 03 | B06R8091 | APACHE TRIBE OF OKLAHOMA - R - ROAD RESURFACING PROJECT | Pavement Improvement | 2010-05-17 | 2010-07-01 | 2010-09-30 | 2010-08-30 | 286009
22 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | CADDO | Region B | 3 | B06R8151 | KIOWA TRIBE - TRIBAL COMPLEX ENTRANCE AND PARKING | Other |  | 2009-07-01 | 2011-09-30 | 2010-08-06 | 205776
23 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | CADDO | Region B | 3 | B06R8152 | KIOWA TRIBE - TAHOE CREEK BRIDGE | Other | 2010-07-26 | 2010-07-28 |  | 2010-12-30 | 489027
24 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | KIOWA | Region B | 3 | B06R8153 | KIOWA OF OKLAHOMA - R - OZARK TRAIL OVERLAY | Pavement Improvement |  |  | 2011-12-31 | 2011-07-06 | 414955
25 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | KAY | Region B | 3 | B07R8101 | KAW NATION (KAY COUNTY) - PECAN ROAD | Other | 2010-05-03 | 2010-07-01 | 2010-09-30 | 2010-08-20 | 798728
26 | Obligated and Awarded | (BIA) IRR | Federal Lands | OKLAHOMA | NOBLE | Region B | 5 | B07R8111 | OTOE-MISSOURIA - R - ADJACENT PARKING | Other |  |  | 2011-12-31 |  | 139082
27 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | KAY | Region B | 3 | B07R8131 | PONCA TRIBE OF OKLAHOMA - S STREET RECONSTRUCTION | Other | 2010-05-27 |  | 2010-09-30 | 2011-06-30 | 632756
28 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | KAY | Region B | 3 | B07R8141 | TONKAWA TRIBE OF INDIANS - R - GUNN BRIDGE WEST ACCESS ROAD | Other | 2010-05-25 |  | 2010-09-30 | 2011-08-30 | 465376
29 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | POTTAWATOME | Region B | 5 | B08R8232 | KICKAPOO TRIBE OF OKLAHOMA - R - HAZEL DELL ROAD OVERLAY | Pavement Improvement | 2010-05-27 |  | 2010-09-30 | 2011-05-31 | 577392
30 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | LINCOLN | Region B | 3 | B08R8241 | SAC & FOX NATION - CHAPEL PARKING LOT PROJECT | Other | 2010-05-03 | 2010-05-09 | 2010-10-30 | 2011-01-31 | 212626
31 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | LINCOLN | Region B | 3 | B08R8242 | SAC & FOX NATION - TRIBAL CEMETERY ACCESS ROAD PROJECT | Other | 2010-05-03 | 2010-05-09 | 2010-10-30 | 2011-03-31 | 523499
32 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | LINCOLN | Region B |  | B08R8243 | SAC & FOX NATION - SPARKS NORTH ACCESS ROAD | Pavement Improvement | 2010-05-27 | 2010-06-28 | 2010-09-30 | 2010-08-23 | 823806
33 | Completed | (BIA) IRR | Federal Lands | MONTANA | GLACIER | Region C | 1 | C51ER006 | BLACKFEET - BOARDING SCHOOL ROAD DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 531024
34 | Completed | (BIA) IRR | Federal Lands | MONTANA | GLACIER | Region C | 1 | C51ER008 | BLACKFEET - STARR SCHOOL ROAD DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 916068
35 | Completed | (BIA) IRR | Federal Lands | MONTANA | GLACIER | Region C | 1 | C51ER010 | BLACKFEET - AGENCY STREETS DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 141633
36 | Completed | (BIA) IRR | Federal Lands | MONTANA | GLACIER | Region C | 1 | C51ER017 | BLACKFEET - BROWNING STREETS I DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 298897
37 | Completed | (BIA) IRR | Federal Lands | MONTANA | GLACIER | Region C | 1 | C51ER035 | BLACKFEET - INDUSTRIAL PARK STREETS DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 41167
38 | Completed | (BIA) IRR | Federal Lands | MONTANA | GLACIER | Region C | 1 | C51ER041 | BLACKFEET - LAST STARR HOUSING DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 46064
39 | Completed | (BIA) IRR | Federal Lands | MONTANA | GLACIER | Region C | 1 | C51ER043 | BLACKFEET - BLACKFOOT STREETS DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 96832
40 | Completed | (BIA) IRR | Federal Lands | MONTANA | GLACIER | Region C | 1 | C51ER070 | BLACKFEET - SEVILLE ROAD DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 83053
41 | Completed | (BIA) IRR | Federal Lands | MONTANA | BIG HORN | Region C | 1 | C52ER014 | CROW - REAL BIRD LOOP | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 141411
42 | Completed | (BIA) IRR | Federal Lands | MONTANA | BIG HORN | Region C | 1 | C52ER055 | CROW - ST. XAVIER STREETS | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 52120
43 | Completed | (BIA) IRR | Federal Lands | MONTANA | BIG HORN | Region C | 1 | C52ER088 | CROW - OWL CREEK ROAD | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 347769
44 | Completed | (BIA) IRR | Federal Lands | MONTANA | BIG HORN | Region C | 1 | C52ER091 | CROW - PRYOR TO ST. XAVIER | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 3007005
45 | Completed | (BIA) IRR | Federal Lands | MONTANA | BIG HORN | Region C | 1 | C52ER125 | CROW - MULTI-STREET REHAB - LODGEGRASS HOUSING | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 74586
46 | Completed | (BIA) IRR | Federal Lands | MONTANA | BIG HORN | Region C | 1 | C52ER201 | CROW - MULTI-STREET REHAV - PRYOR STREETS | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 55211
47 | Completed | (BIA) IRR | Federal Lands | MONTANA | BIG HORN | Region C | 1 | C52ER777 | CROW - GAS CAP ROAD | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 144496
48 | Completed | (BIA) IRR | Federal Lands | MONTANA | BLAINE | Region C | 1 | C55ER004 | FT BELNAP - AGENCY STREETS DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 286564
49 | Completed | (BIA) IRR | Federal Lands | MONTANA | BLAINE | Region C | 1 | C55ER006 | FT BELNAP - WHITE BEAR DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 228677
50 | Completed | (BIA) IRR | Federal Lands | MONTANA | BLAINE | Region C | 1 | C55ER011 | FT BELNAP - LODGEPOLE EAST & WEST DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 824977
51 | Completed | (BIA) IRR | Federal Lands | MONTANA | BLAINE | Region C | 1 | C55ER021 | FT BELNAP - BEAR BULCH DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 238335
52 | Completed | (BIA) IRR | Federal Lands | MONTANA | BLAINE | Region C | 1 | C55ER112 | FT BELNAP - LP SOUTH DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-03 | 2009-09-04 |  | 2010-09-30 | 93010
53 | Completed | (BIA) IRR | Federal Lands | MONTANA | BIG HORN | Region C | 1 | C57ER005 | NORTHERN CHEYENNE - MUDDY CREEK DIRECT SERVICE CONST. | Pavement Improvement | 2009-09-07 | 2009-09-07 |  | 2010-09-30 | 937453
54 | Completed | (BIA) IRR | Federal Lands | MONTANA | ROSEBUD | Region C | 1 | C57ER011 | NORTHERN CHEYENNE - ASHLAND - BIRNEY DIRECT SERVICE CONST. | Safety/Traffic Management | 2009-09-07 | 2009-09-07 |  | 2010-09-30 | 958004
55 | Completed | (BIA) IRR | Federal Lands | MONTANA | ROSEBUD | Region C | 1 | C57ER022 | NORTHERN CHEYENNE - RABBIT TOWN TO MISSION DIR. SER. CONST. | Pavement Improvement | 2009-09-07 | 2009-09-07 |  | 2010-09-30 | 178530
56 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER005 | WIND RIVER - SHAYO LANE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 51194
57 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER015 | WIND RIVER - RAY LAKE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 123468
58 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER016 | WIND RIVER - TROSPER LANE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 233781
59 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER027 | WIND RIVER - OLD WIND RIVER HIGHWAY | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 179818
60 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER028 | WIND RIVER - GOES IN LODGE ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 243359
61 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER049 | WIND RIVER - C'HAIR LANE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 113936
62 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER075 | WIND RIVER - MISSION ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 150061
63 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER077 | WIND RIVER - BEHAN ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 40153
64 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER101 | WIND RIVER - MAIL CAMP ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 1574338
65 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER116 | WIND RIVER - AGENCY STREETS - MULTI ROUTE | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 187307
66 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER211 | WIND RIVER - LEFTHAND DITCH ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2010-09-30 | 393484
67 | Completed | (BIA) IRR | Federal Lands | WYOMING | FREMONT | Region C | 1 | C58ER805 | WIND RIVER - BIA 8050 GIVENS ROAD | Safety/Traffic Management | 2009-09-21 | 2009-09-21 |  | 2011-09-30 | 133725
68 | Completed | (BIA) IRR | Federal Lands | MONTANA | HILL | Region C | 1 | C59ER001 | ROCKY BOY - MISSION - TAYLOR ROAD | Safety/Traffic Management | 2009-08-14 | 2009-08-14 |  | 2010-09-30 | 115120
69 | Completed | (BIA) IRR | Federal Lands | MONTANA | HILL | Region C | 1 | C59ER002 | ROCKY BOY - SANGREY SCHOOL | Safety/Traffic Management | 2009-08-14 | 2009-08-14 |  | 2011-09-30 | 575976
70 | Completed | (BIA) IRR | Federal Lands | MONTANA | HILL | Region C | 1 | C59ER101 | ROCKY BOY - ROCKY BOY'S STREEST SAFETY IMPROVEMENT | Safety/Traffic Management | 2009-08-14 | 2009-08-14 |  | 2011-09-30 | 73466
71 | Completed | (BIA) IRR | Federal Lands | MONTANA | HILL | Region C | 1 | C59ER114 | ROCKY BOY - BEAVER CREEK ROAD | Safety/Traffic Management | 2009-08-14 | 2009-08-14 |  | 2010-09-30 | 453391
72 | Underway | (BIA) IRR | Federal Lands | ALASKA | KODIAK ISLAND BOROUGH | Region E | 1 | E01002A1 | AFOGNAK - MUSKOMEE TRAIL IMPROVEMENT/REHAB OF BOAT LANDING DOCK | Other | 2010-04-01 | 2010-04-27 | 2010-12-31 |  | 61532
73 | Obligated and Awarded | (BIA) IRR | Federal Lands | ALASKA | ALEUTIAN ISLANDS | Region E | 1 | E01007A1 | AKUTAN - - AKUTAN HARBOR ACCESS ROAD | Other |  |  |  |  | 72777
74 | Underway | (BIA) IRR | Federal Lands | ALASKA | KODIAK ISLAND BOROUGH | Region E | 1 | E01237A1 | KARLUK - DESIGN OF LANDFILL ROAD (ROUTE 1014) | Other | 2010-04-01 |  | 2010-12-31 |  | 180457
75 | Underway | (BIA) IRR | Federal Lands | ALASKA | DILLINGHAM AREA | Region E | 1 | E01259A3 | MANOKOTAK - HEIGHTS ROAD REHABILITATION | Other | #N/A | #N/A | #N/A | #N/A | 71418
76 | Obligated and Awarded | (BIA) IRR | Federal Lands | ALASKA | MATANUSKA - SUSITNA BOROUGH | Region E | 1 | E01260A1 | KNIK - CHIEF WASILLA WAY ROAD CONSTRUCTION | Other |  |  | 2010-12-31 |  | 114589
77 | Obligated and Awarded | (BIA) IRR | Federal Lands | ALASKA | DILLINGHAM AREA | Region E | 1 | E01264A1 | KOKHANUK - MAIN ROAD & OLD SCHOOL ROAD REHABILITATION DESIGN | Other |  |  | 2010-12-15 |  | 50518
78 | Obligated and Awarded | (BIA) IRR | Federal Lands | ALASKA | DILLINGHAM AREA | Region E | 1 | E01283A1 | LEVELOCK - FIRST AND SEVENTH STREET DESIGNS | Other |  |  | 2011-03-31 |  | 219607
79 | Underway | (BIA) IRR | Federal Lands | ALASKA | KENAI - COOK INLET | Region E | 1 | E01396A1 | PORT GRAHAM - WINDY BAY ROAD PROJECT | Other | 2010-04-02 |  | 2010-09-06 |  | 44626
80 | Obligated and Awarded | (BIA) IRR | Federal Lands | ALASKA | BRISTOL BAY BOROUGH | Region E | 1 | E01450A1 | SOUTH NAKNEK - DIAMOND M ROAD | Other |  |  | 2011-06-30 |  | 63760
81 | Underway | (BIA) IRR | Federal Lands | ALASKA | KENAI - COOK INLET | Region E | 1 | E01505A2 | TYONEK - ROUTE 2400 - REALIGNMENT & CULVERT RECONSTRUCTION DESIGN | Other | 2010-04-09 | 2010-04-09 | 2010-05-30 |  | 171282
82 | Obligated and Awarded | (BIA) IRR | Federal Lands | ALASKA | DILLINGHAM AREA | Region E | 1 | E01506A1 | UGASHIK - UGASHIK ROUTE 0062 & 0063 DESIGN | Other |  |  | 2010-12-31 |  | 81816
83 | Underway | (BIA) IRR | Federal Lands | ALASKA | BETHEL AREA | Region E | 1 | E02005A1 | AKIACHAK - DESIGN FOR GWEEK ROAD | Other | 2010-04-02 |  | 2010-12-31 |  | 152255
84 | Underway | (BIA) IRR | Federal Lands | ALASKA | BETHEL AREA | Region E | 1 | E02006A1 | AKIAK - RECONSTRUCTION & REHABILITATION OF AKIK2 | Other | 2010-04-09 |  | 2010-04-19 |  | 47485
85 | Underway | (BIA) IRR | Federal Lands | ALASKA | BETHEL AREA | Region E | 1 | E02275A1 | KWETHLUK - COMMUNITY BOARDROAD PROJECT | Other | 2010-04-01 |  | 2010-12-31 |  | 54249
86 | Underway | (BIA) IRR | Federal Lands | ALASKA | BETHEL AREA | Region E | 1 | E02841A1 | CHUATHBALUK - LOOP ROAD RECONSTRUCTION | New Construction | 2010-06-23 | 2010-06-23 | 2010-12-31 |  | 52098
87 | Underway | (BIA) IRR | Federal Lands | ALASKA | YUKON - KOYUKUK AREA | Region E | 1 | E03205A1 | HUGHES - BLUEBERRY ROAD IMPROVEMENTS | Other | 2010-04-01 | 2010-04-01 | 2010-12-31 |  | 66425
88 | Obligated and Awarded | (BIA) IRR | Federal Lands | ALASKA | NOME AREA |  | 1 | E04167A1 | GAMBLE - GAMBLE COMMUNITY STREET ARRA PROJECT | Other |  |  | 2011-10-15 |  | 6747361
89 | Obligated and Awarded | (BIA) IRR | Federal Lands | IOWA | TAMA | Region F | 3 | F51490SA | SAC & FOX TRIBE OF MISSISSIPPI IN IOWA - MESKWAKI ROAD | Other |  |  | 2012-09-30 |  | 101746
90 | Obligated and Awarded | (BIA) IRR | Federal Lands | IOWA | TAMA | Region F | 3 | F51490SB | SAC & FOX TRIBE OF MISSISSIPPI IN IOWA - RED EARTH ROAD | New Construction |  |  | 2012-09-30 |  | 196000
91 | Obligated and Awarded | (BIA) IRR | Federal Lands | IOWA | TAMA | Region F | 3 | F51490SC | SAC & FOX TRIBE OF MISSISSIPPI IN IOWA - IRR MAINTENANCE | Other |  |  | 2012-09-30 |  | 99000
92 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | BELTRAMI | Region F | 7 | F52409SI | RED LAKE BAND OF CHIPPEWA INDIANS - JEROME CUTOFF | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2012-09-30 | 2010-08-16 | 87000
93 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | BELTRAMI | Region F | 7 | F52409SJ | RED LAKE BAND OF CHIPPEWA INDIANS - PONEMAH ROAD | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2012-09-30 | 2010-08-16 | 2626283
94 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | ST. LOUIS | Region F | 8 | F53404SA | BOIS FORTE LAKE SUPERIOR BAND OF CHIPPEWA - TIBBIT'S TRAIL | Pavement Improvement |  | 2010-09-13 | 2012-09-30 | 2010-10-16 | 195000
95 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | ST. LOUIS | Region F | 8 | F53404SB | BOIS FORTE LAKE SUPERIOR BAND OF CHIPPEWA - DUFFY POINT ROAD | Pavement Improvement | 2010-06-30 | 2010-09-13 | 2012-09-30 | 2010-10-16 | 152000
96 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | ST. LOUIS | Region F | 8 | F53404SC | BOIS FORTE LAKE SUPERIOR BAND OF CHIPPEWA - VILLAGE STREETS | Pavement Improvement | 2010-07-16 | 2010-06-21 | 2012-09-30 | 2010-08-19 | 643300
97 | Underway | (BIA) IRR | Federal Lands | MINNESOTA | ST. LOUIS | Region F | 8 | F53404SD | BOIS FORTE LAKE SUPERIOR BAND OF CHIPPEWA - 25% ROAD MAINTENANCE | Other | 2010-06-30 | 2010-11-17 | 2012-09-30 |  | 282518
98 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CARLTON | Region F | 8 | F53405SC | FOND DU LAC BAND OF CHIPPEWA INDIANS - MOORHEAD ROAD | Pavement Improvement | 2010-05-14 | 2010-07-06 | 2012-09-30 | 2011-08-15 | 1261448
99 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | COOK | Region F | 8 | F53406SA | GRAND PORTAGE BAND OF CHIPPEWA INDIANS - VILLAGE ROADS | Pavement Improvement | 2010-07-15 | 2011-07-05 | 2012-09-30 | 2011-12-30 | 952051
100 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | COOK | Region F | 8 | F53406SC | GRAND PORTAGE BAND OF CHIPPEWA INDIANS - STEVEN & STORE ROADS | Pavement Improvement | 2010-07-15 | 2011-07-05 | 2012-09-30 | 2011-12-30 | 402887
101 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SA | LEECH LAKE BANDOF CHIPPEWA INDIANS - OAK POINT | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2012-09-30 | 2010-06-29 | 2712170
102 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SB | LEECH LAKE BAND OF CHIPPEWA INDIANS - CR 145 | Pavement Improvement | 2010-06-16 | 2010-08-04 | 2012-09-30 | 2010-09-30 | 286175
103 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SC | LEECH LAKE BAND OF CHIPPEWA INDIANS - INGER STREETS | Pavement Improvement | 2010-04-27 | 2010-05-24 | 2012-09-30 | 2010-06-29 | 241789
104 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SD | LEECH LAKE BAND OF CHIPPEWA INDIANS - OLD BALL CLUB STREETS | Pavement Improvement | 2010-04-27 | 2010-06-09 | 2012-09-30 | 2010-06-29 | 139444
105 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SG | LEECH LAKE BAND OF CHIPPEWA INDIANS - TRIBAL TRACT 33 STREETS | Pavement Improvement | 2010-04-27 | 2010-04-28 | 2012-09-30 | 2010-06-29 | 468357
106 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SI | LEECH LAKE BAND OF CHIPPEWA INDIANS - OLD AGENCY ROAD | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2012-09-30 | 2010-10-15 | 133713
107 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SJ | LEECH LAKE BAND OF CHIPPEWA INDIANS - CEMETERY ROAD | Pavement Improvement | 2010-04-19 | 2010-04-28 | 2012-09-30 | 2010-06-29 | 577960
108 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SK | LEECH LAKE BAND OF CHIPPEWA INDIANS - ONIGUM STREETS | Pavement Improvement | 2010-04-27 | 2010-05-13 | 2012-09-30 | 2010-07-29 | 240911
109 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SM | LEECH LAKE BAND OF CHIPPEWA INDIANS - BOY RIVER ROAD & CR 172 | Pavement Improvement | 2010-04-29 | 2010-05-18 | 2012-09-30 | 2011-06-29 | 876042
110 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | CASS | Region F | 8 | F53407SN | LEECH LAKE BAND OF CHIPPEWA INDIANS - OTENEAGAN ROAD | Pavement Improvement | 2010-04-27 | 2010-04-28 | 2012-09-30 | 2010-10-15 | 248975
111 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | BECKER |  | 7 | F53408SD | WHITE EARTH BAND OF CHIPPEWA INDIANS - REDISCOVERY CENTER ROAD | New Construction | 2010-07-20 | 2010-07-21 | 2012-09-30 | 2011-08-15 | 675381
112 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | BECKER |  | 7 | F53408SE | WHITE EARTH BAND OF CHIPPEWA INDIANS - IRR MAINTENANCE | Other | 2010-07-21 | 2010-08-23 | 2012-09-30 | 2011-04-15 | 478066
113 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | MAHNOMEN |  | 7 | F53408SF | WHITE EARTH BAND OF CHIPPEWA INDIANS - WHITE EARTH STREETS | Pavement Improvement | 2010-08-02 | 2010-08-03 | 2012-09-30 | 2010-09-21 | 597500
114 | Completed | (BIA) IRR | Federal Lands | MINNESOTA | MAHNOMEN |  | 7 | F53408SG | WHITE EARTH BAND OF CHIPPEWA INDIANS - NAYTAHWAUSH STREETS | Pavement Improvement | 2010-08-02 | 2010-08-10 | 2012-09-30 | 2010-10-22 | 329500
115 | Underway | (BIA) IRR | Federal Lands | MINNESOTA | MILLE LACS | Region F | 8 | F53410SA | MILLE LACS BAND OF CHIPPEWA INDIANS - WISE OWL | Pavement Improvement | 2010-05-10 | 2010-05-13 | 2012-09-30 |  | 719910
116 | Underway | (BIA) IRR | Federal Lands | WISCONSIN | ASHLAND | Region F | 7 | F55430SA | BAD RIVER BAND OF CHIPPEWA INDIANS - IRR MAINTENANCE | Other | 2010-07-15 | 2010-08-23 | 2012-09-30 |  | 150000
117 | Completed | (BIA) IRR | Federal Lands | WISCONSIN | ASHLAND | Region F | 7 | F55430SB | BAD RIVER BAND OF CHIPPEWA INDIANS - CHIP SEAL PROJECT | Pavement Improvement | 2010-08-06 | 2010-07-19 | 2012-09-30 | 2010-10-06 | 150813
118 | Completed | (BIA) IRR | Federal Lands | WISCONSIN | ASHLAND | Region F | 7 | F55430SE | BAD RIVER BAND OF CHIPPEWA INDIANS - IRR TRANSIT | Safety/Traffic Management | 2010-07-15 | 2010-07-19 | 2012-09-30 | 2011-06-15 | 97000
119 | Completed | (BIA) IRR | Federal Lands | WISCONSIN | ASHLAND | Region F | 7 | F55430SF | BAD RIVER BAND OF CHIPPEWA INDIANS - ACKLEY ROAD | New Construction | 2010-08-06 | 2010-08-09 | 2012-09-30 | 2010-11-05 | 103013
120 | Completed | (BIA) IRR | Federal Lands | WISCONSIN | ASHLAND | Region F | 7 | F55430SI | BAD RIVER BAND OF CHIPPEWA INDIANS - MCDONALD ROAD | New Construction | 2010-08-06 | 2010-08-09 | 2012-09-30 | 2010-11-05 | 130000
121 | Underway | (BIA) IRR | Federal Lands | WISCONSIN | SAWYER | Region F | 7 | F55431SD | LAC COURTE OREILLES - SUMMIT ROAD | Pavement Improvement | 2010-06-07 | 2010-06-03 | 2012-06-30 |  | 468073
122 | Completed | (BIA) IRR | Federal Lands | WISCONSIN | SAWYER | Region F | 7 | F55431SH | LAC COURTE OREILLES - IRR MAINTENANCE | Other | 2010-07-08 | 2010-07-08 | 2010-09-30 | 2010-09-30 | 154000
123 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | VILAS | Region F | 8 | F55432SB | LAC DU FLAMBEAU CHIPPEWA - TREE HAVEN LANE | Pavement Improvement |  | 2010-06-21 | 2012-09-30 |  | 368687
124 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | VILAS | Region F | 8 | F55432SD | LAC DU FLAMBEAU CHIPPEWA - LITTLE PINES | Other |  | 2010-06-21 | 2012-09-30 |  | 427000
125 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | VILAS | Region F | 8 | F55432SE | LAC DU FLAMBEAU CHIPPEWA - WEST POKAGAMA ROAD | Pavement Improvement |  | 2010-06-21 | 2012-09-30 |  | 189446
126 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | VILAS | Region F | 8 | F55432SG | LAC DU FLAMBEAU CHIPPEWA - LONG'S POINT | Other |  | 2010-06-21 | 2012-09-30 |  | 572745
127 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | VILAS | Region F | 8 | F55432SH | LAC DU FLAMBEAU CHIPPEWA - OBERLAND ROAD | Other |  | 2010-06-21 | 2012-09-30 |  | 240500
128 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | VILAS | Region F | 8 | F55432SI | LAC DU FLAMBEAU CHIPPEWA - COUNTY D | Other |  | 2010-06-21 | 2012-09-30 |  | 282000
129 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | OUTAGAMIE | Region F | 8 | F55433SD | ONEIDA INDIAN TRIBE - CTH U COOP | Other |  |  |  |  | 65000
130 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | OUTAGAMIE | Region F | 8 | F55433SG | ONEIDA INDIAN TRIBE - ROLLING HILLS SUBDIVISION | Other |  | 2010-06-01 | 2012-09-30 |  | 70000
131 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | OUTAGAMIE | Region F | 8 | F55433SG | ONEIDA INDIAN TRIBE - ROLLING HILLS SUBDIVISION | New Construction |  | 2010-06-01 | 2012-09-30 |  | 677629
132 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | FOREST | Region F | 8 | F55434SA | FOREST COUNTY POTAWATOMI COMMUNITY - LOIS CROWE | Pavement Improvement |  | 2010-06-01 | 2012-09-30 |  | 259383
133 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | FOREST | Region F | 8 | F55434SD | FOREST COUNTY POTAWATOMI COMMUNITY - BLACKWELL SUBDIVISION | Other |  | 2010-06-01 | 2012-09-30 |  | 89095
134 | Underway | (BIA) IRR | Federal Lands | WISCONSIN | BAYFIELD | Region F | 7 | F55435SB | RED CLIFF BAND OF CHIPPEWA - BLUEBERRY ROAD | New Construction | 2010-02-24 | 2010-03-01 | 2010-04-30 |  | 381791
135 | Underway | (BIA) IRR | Federal Lands | WISCONSIN | BAYFIELD | Region F | 7 | F55435SD | RED CLIFF BAND OF CHIPPEWA - IRR MAINTENANCE | Other | 2010-05-15 | 2010-06-15 | 2010-09-30 |  | 127263
136 | Underway | (BIA) IRR | Federal Lands | WISCONSIN | BURNETT | Region F | 7 | F55436SA | ST. CROIX TRIBAL COUNCIL - EAGLE FEATHER ROAD | Pavement Improvement | 2010-06-09 | 2010-06-16 | 2010-09-30 |  | 290628
137 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | FOREST | Region F | 8 | F55437SD | SOKAOGON CHIPPEWA COMMUNITY - SAND LAKE ROAD | New Construction |  | 2010-01-29 | 2010-09-30 |  | 94949
138 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | FOREST | Region F | 8 | F55437SE | SOKAOGON CHIPPEWA COMMUNITY - IRR MAINTENANCE | Other |  | 2010-01-29 | 2012-09-30 |  | 31500
139 | Completed | (BIA) IRR | Federal Lands | WISCONSIN | SHAWANO | Region F | 8 | F55438SD | STOCKBRIDGE MUNSEE COMMUNITY - CAMP 14 ROAD | Pavement Improvement | 2010-05-24 | 2010-06-01 | 2012-09-30 | 2010-07-16 | 738842
140 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | WOOD | Region F | 7 | F55439SP | HO-CHUNK NATION - CTH G COOP | Pavement Improvement |  |  | 2012-09-30 |  | 3500000
141 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | JACKSON | Region F | 3 | F55439SQ | HO-CHUNK NATION - BROCKWAY ROAD | Pavement Improvement |  |  | 2012-09-30 |  | 944823
142 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | JACKSON | Region F | 3 | F55439SR | HO-CHUNK NATION - WEST BAUER ROAD | Other |  |  | 2012-09-30 |  | 25000
143 | Obligated and Awarded | (BIA) IRR | Federal Lands | MINNESOTA | YELLOW MEDICINE | Region F | 7 | F57401SC | UPPER SIOUX INDIAN COMMUNITY - NEW WATER SOURCE ROAD | Other |  |  | 2012-09-30 |  | 15000
144 | Obligated and Awarded | (BIA) IRR | Federal Lands | MINNESOTA | YELLOW MEDICINE | Region F | 7 | F57401SF | UPPER SIOUX INDIAN COMMUNITY - MN STATE HWY 67 | Pavement Improvement |  |  | 2010-09-30 |  | 993950
145 | Obligated and Awarded | (BIA) IRR | Federal Lands | MINNESOTA | YELLOW MEDICINE | Region F | 7 | F57401SH | UPPER SIOUX INDIAN COMMUNITY - HAZELWOOD ROAD | Other |  |  | 2012-09-30 |  | 15478
146 | Obligated and Awarded | (BIA) IRR | Federal Lands | MINNESOTA | YELLOW MEDICINE | Region F | 7 | F57401SI | UPPER SIOUX INDIAN COMMUNITY - IRR MAINTENANCE | Other |  |  | 2012-09-30 |  | 341476
147 | Obligated and Awarded | (BIA) IRR | Federal Lands | MINNESOTA | REDWOOD | Region F | 2 | F57402SC | LOWER SIOUX INDIAN COMMUNITY - LIGHTING, LANDSCAPING & SAFETY | New Construction |  |  | 2012-09-30 |  | 979655
148 | Underway | (BIA) IRR | Federal Lands | MINNESOTA | REDWOOD | Region F | 2 | F57402SD | LOWER SIOUX INDIAN COMMUNITY - IRR MAINTENANCE | Other | 2010-06-30 |  |  |  | 326500
149 | Obligated and Awarded | (BIA) IRR | Federal Lands | MINNESOTA | GOODHUE | Region F | 2 | F57403SA | PRAIRIE ISLAND INDIAN COMMUNITY - HOLMQUIST ROAD | Other |  | 2010-04-05 | 2012-09-30 |  | 275000
150 | Obligated and Awarded | (BIA) IRR | Federal Lands | MINNESOTA | GOODHUE | Region F | 2 | F57403SB | PRAIRIE ISLAND INDIAN COMMUNITY - OTHERDAY & WHIPPLE ROADS | Other |  | 2010-04-05 | 2012-09-30 |  | 170000
151 | Obligated and Awarded | (BIA) IRR | Federal Lands | MINNESOTA | GOODHUE/DAKOTA | Region F | 2 | F57403SE | PRAIRIE ISLAND INDIAN COMMUNITY - PI COMMUNITY STREETS | Other |  | 2010-03-31 | 2012-09-30 |  | 400000
152 | Underway | (BIA) IRR | Federal Lands | MINNESOTA | SCOTT | Region F | 2 | F57411SA | SHAKOPEE MDEWAKANTON SIOUX COMMUNITY - COUNTY ROAD 83 | Pavement Improvement | 2010-03-01 | 2010-04-05 | 2012-09-30 |  | 1104742
153 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | MENOMINEE | Region F | 8 | F58440SA | MENOMINEE INDIAN TRIBE - UPPER BASS LAKE ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 10000
154 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | MENOMINEE | Region F | 8 | F58440SB | MENOMINEE INDIAN TRIBE - COUNTY B ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 10000
155 | Underway | (BIA) IRR | Federal Lands | WISCONSIN | MENOMINEE | Region F | 8 | F58440SC | MENOMINEE INDIAN TRIBE - GO AROUND ROAD | Pavement Improvement | 2010-06-24 | 2010-06-01 | 2012-09-30 |  | 1033013
156 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | MENOMINEE | Region F | 8 | F58440SD | MENOMINEE INDIAN TRIBE - WEST BRANCH ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 15000
157 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | MENOMINEE | Region F | 8 | F58440SE | MENOMINEE INDIAN TRIBE - BEAR TRAP FALLS ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 10000
158 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | MENOMINEE | Region F | 8 | F58440SH | MENOMINEE INDIAN TRIBE - IRR MAINTENANCE | Other |  | 2010-08-15 | 2012-09-30 |  | 361371
159 | Obligated and Awarded | (BIA) IRR | Federal Lands | WISCONSIN | MENOMINEE | Region F | 8 | F58440SI | MENOMINEE INDIAN TRIBE - PONFIL ROAD | Other |  | 2010-06-01 | 2012-09-30 |  | 12000
160 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | ALGER | Region F | 1 | F60469SC | SAULT STE MARIE BAND OF CHIPPEWA INDIANS - ALGER COUNTY COOP | Pavement Improvement |  |  | 2012-09-30 |  | 105777
161 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | MACKINAC | Region F | 1 | F60469SD | SAULT STE MARIE BAND OF CHIPPEWA INDIANS - MACKINAC TRAIL COOP | Other |  |  | 2012-09-30 |  | 38986
162 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | ALGER | Region F | 1 | F60469SE | SAULT STE MARIE BAND OF CHIPPEWA INDIANS - LEHNEN & CEMETERY ROAD COOP | Pavement Improvement |  |  | 2012-09-30 |  | 434000
163 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | MACKINAC | Region F | 1 | F60469SG | SAULT STE MARIE BAND OF CHIPPEWA INDIANS - CHAMBERS STREET COOP | Pavement Improvement |  |  | 2012-09-30 |  | 41400
164 | Underway | (BIA) IRR | Federal Lands | MICHIGAN | CHIPPEWA | Region F | 1 | F60470SA | BAY MILLS INDIAN COMMUNITY - PLANTATION ROAD | New Construction | 2010-07-19 | 2010-07-21 | 2012-09-30 |  | 181887
165 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | DELTA | Region F | 1 | F60471SD | HANNAHVILLE INDIAN COMMUNITY - RIDGEVIEW EXTENSION | Pavement Improvement |  | 2010-05-12 | 2012-09-30 |  | 701862
166 | Completed | (BIA) IRR | Federal Lands | MICHIGAN | ISABELLA | Region F | 4 | F60472SB | SAGINAW CHIPPEWA INDIAN TRIBE - MISSION ROAD | Pavement Improvement | 2009-09-21 | 2009-08-16 | 2010-12-31 | 2010-09-15 | 540000
167 | Completed | (BIA) IRR | Federal Lands | MICHIGAN | ISABELLA | Region F | 4 | F60472SC | SAGINAW CHIPPEWA INDIAN TRIBE - BASELINE ROAD | Pavement Improvement | 2009-09-21 | 2009-08-16 | 2010-12-31 | 2010-12-31 | 270000
168 | Completed | (BIA) IRR | Federal Lands | MICHIGAN | GOGEBIC | Region F | 1 | F6047307 | LAC VIEUX DESERT CHIPPEWA INDIANS - RODDIS ROAD | Pavement Improvement | 2009-09-14 | 2009-09-01 | 2009-10-31 | 2009-10-30 | 379305
169 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | GRAND TRAVERSE | Region F | 4 | F60474SA | GRAND TRAVERSE BAND OF OTTAWA - GTB RESORT PHASE 3 | New Construction |  |  | 2012-09-30 |  | 944252
170 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | LEELANAU | Region F | 4 | F60474SE | GRAND TRAVERSE BAND OF OTTAWA - GTB SIDEWALK | New Construction |  |  | 2012-09-30 |  | 1264753
171 | Completed | (BIA) IRR | Federal Lands | MICHIGAN | GRAND TRAVERSE | Region F | 4 | F60474SI | GRAND TRAVERSE BAND OF OTTAWA - EAST SILVER LAKE ROAD | New Construction | 2010-06-21 | 2010-07-12 | 2012-09-30 | 2010-08-30 | 816099
172 | Completed | (BIA) IRR | Federal Lands | MICHIGAN | GRAND TRAVERSE | Region F | 4 | F60474SJ | GRAND TRAVERSE BAND OF OTTAWA - KEYSTONE ROAD | New Construction | 2010-06-21 | 2010-07-12 | 2012-09-30 | 2010-08-12 | 242342
173 | Completed | (BIA) IRR | Federal Lands | MICHIGAN | GRAND TRAVERSE | Region F | 4 | F60474SL | GRAND TRAVERSE BAND OF OTTAWA - SECOR ROAD | New Construction | 2010-06-21 | 2010-06-30 | 2012-09-30 | 2010-08-05 | 235715
174 | Completed | (BIA) IRR | Federal Lands | MICHIGAN | LEELANAU | Region F | 4 | F60474SM | GRAND TRAVERSE BAND OF OTTAWA - ROAD MAINTENANCE ROAD | New Construction |  | 2010-06-24 | 2012-09-30 | 2010-10-19 | 90481
175 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | BARAGA | Region F | 1 | F60475SA | KEWEENAW BAY INDIAN COMMUNITY - SKANEE ROAD COOP | Pavement Improvement |  |  | 2012-09-30 |  | 929134
176 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | BERRIEN | Region F | 8 | F60480SC | POKAGON BAND OF POTAWATOMI - MAUDLIN ROAD COOP | Pavement Improvement |  |  | 2012-09-30 |  | 535773
177 | Completed | (BIA) IRR | Federal Lands | MICHIGAN | MASON | Region F | 2 | F60482SC | LITTLE RIVER BAND OF OTTAWA - GOVERNMENT CENTER ROADS | Pavement Improvement |  |  |  | 2010-09-30 | 79978
178 | Underway | (BIA) IRR | Federal Lands | MICHIGAN | EMMET | Region F | 1 | F60483SA | LITTLE TRAVERSE BAY BAND OF CHIPPEWA - PLEASANTVIEW ROAD | Pavement Improvement | 2009-12-15 | 2010-05-24 |  | 2012-09-30 | 598660
179 | Underway | (BIA) IRR | Federal Lands | MICHIGAN | EMMET | Region F | 1 | F60483SB | LITTLE TRAVERSE BAY BAND OF CHIPPEWA - STATE ROAD | Pavement Improvement | 2009-12-15 | 2010-05-17 |  | 2012-09-30 | 525502
180 | Underway | (BIA) IRR | Federal Lands | MICHIGAN | EMMET | Region F | 1 | F60483SD | LITTLE TRAVERSE BAY BAND OF CHIPPEWA - MCDOUGAL ROAD | Pavement Improvement | 2009-12-15 | 2010-05-17 |  | 2012-09-30 | 488579
181 | Obligated and Awarded | (BIA) IRR | Federal Lands | MICHIGAN | ALLEGAN | Region F | 6 | F60484SB | MATCH-E-BE-NASH-SHE-WISH BAND OF POTAWATOMI - ELDER HOUSING DEV. | New Construction |  |  | 2012-09-30 |  | 440694
182 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | OTTAWA |  | 2 | G04FER07 | QUAPAW TRIBE - S680 ROAD | Other | 2009-12-11 | 2009-12-11 | 2010-09-30 | 2010-09-30 | 533443
183 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | OTTAWA |  | 2 | G04FER14 | WYANDOTTE - WYANDOTTE ROAD PHASE 2 PART B | Other | 2010-02-18 | 2010-05-01 | 2010-12-31 | 2010-11-30 | 222990
184 | Underway | (BIA) IRR | Federal Lands | OKLAHOMA | OTTAWA |  | 2 | G04FER22 | OTTAWA TRIBE - ADAWE ROAD | Pavement Improvement | 2010-08-17 |  |  |  | 867896
185 | Underway | (BIA) IRR | Federal Lands | OKLAHOMA | OTTAWA |  | 2 | G04FER24 | MIAMI - BRIDGE #09369 | Other | 2010-03-23 | 2010-08-02 | 2011-09-30 |  | 206632
186 | Underway | (BIA) IRR | Federal Lands | OKLAHOMA | OTTAWA |  | 2 | G04FER37 | EASTERN SHAWNEE - BIA ROUTE 120 | Other | 2010-03-31 | 2011-08-15 | 2011-06-30 |  | 103911
187 | Underway | (BIA) IRR | Federal Lands | OKLAHOMA | LATIMER |  | 2 | G09FER15 | CHOCTAW NATION - WILBURTON STREETS | Other | 2010-08-10 |  |  |  | 643400
188 | Completed | (BIA) IRR | Federal Lands | OKLAHOMA | ATOKA |  | 2 | G09FER16 | CHOCTAW NATION - BENTLEY ROAD | Other | 2010-04-06 | 2010-10-04 | 2011-04-01 | 2011-01-15 | 2732311
189 | Underway | (BIA) IRR | Federal Lands | OKLAHOMA | PUSHMATAHA |  | 2 | G09FER17 | CHOCTAW NATION - COUNCIL HOUSE NORTH | Other | 2010-12-06 |  |  |  | 4908720
190 | Underway | (BIA) IRR | Federal Lands | OKLAHOMA | SEMINOLE | Region G | 5 | G10FER09 | SEMINOLE NATION - TRANSIT FACILITY | Other | 2010-02-08 | 2010-11-15 | 2011-10-14 |  | 1400000
191 | Underway | (BIA) IRR | Federal Lands | OKLAHOMA | SEMINOLE | Region G | 5 | G10FER10 | SEMINOLE NATION - NATION'S STOP, ROAD & MARKER SIGNS | Safety/Traffic Management | 2010-09-28 | 2010-11-22 | 2011-03-29 |  | 222358
192 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | MOHAVE | Region H | 3 | H51A0200 | FORT MOHAVE - PROJECT MOIR 8(1) HULET RD | Other |  |  |  |  | 464980
193 | Underway | (BIA) IRR | Federal Lands | ARIZONA | LA PAZ | Region H | 3 | H51A0400 | COLORADO RIVER - PROJECT CRIR 10(1) | Other | 2010-08-02 |  |  |  | 393642
194 | Underway | (BIA) IRR | Federal Lands | ARIZONA | GILA | Region H | 1 | H52A0100 | FORT APACHE - PROJECT FAIR 4(2) | Other | 2010-05-24 | 2010-06-05 | 2010-09-21 |  | 667829.47
195 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | NAVAJO | Region H | 1 | H52A0200 | FORT APACHE - PROJECT FAIR 101(1) - WHITERIVER P.D. STREETS | Other |  |  |  |  | 358004
196 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | NAVAJO | Region H | 1 | H52A0300 | FORT APACHE - PROJECT FAIR 103(1) - DARK SHADOWS AVENUE | Other |  |  |  |  | 256000
197 | Underway | (BIA) IRR | Federal Lands | ARIZONA | PIMA | Region H | 7 | H54A0100 | TOHONA O'ODHAM - PROJECT PIR 232(1) | Other | 2010-06-11 | 2010-06-06 | 2010-10-07 |  | 1414456.84
198 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | PIMA | Region H | 7 | H55A0200 | PASCUA YAQUI - PROJECT PYIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 10000
199 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | PIMA | Region H | 7 | H55A0300 | PASCUA YAQUI - PROJECT PYIR CHIP SEAL NO. 1 | Other |  |  |  |  | 25000
200 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | MARICOPA | Region H | 5 | H55A0400 | FORT MCDOWELL - PROJECT FMIR 102(4) | Other |  |  |  |  | 101296
201 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | GILA | Region H | 6 | H58A0100 | SAN CARLOS - PROJECT SCIR 10(6) | Other |  |  |  |  | 312300
202 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | GRAHAM | Region H | 1 | H58A0200 | SAN CARLOS - PROJECT SCIR 15(2) | Other |  |  |  |  | 312300
203 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | GILA | Region H | 1 | H58A0300 | SAN CARLOS - PROJECT SCIR21(1) | New Construction |  |  |  |  | 105600
204 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | GILA | Region H | 1 | H58A0400 | SAN CARLOS - PROJECT SCIR 26(1) | New Construction |  |  |  |  | 118800
205 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | GRAHAM | Region H | 1 | H58A0500 | SAN CARLOS - PROJECT SCIR 193(1) | Other |  |  |  |  | 473765
206 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | GRAHAM | Region H | 1 | H58A0600 | SAN CARLOS - PROJECT SCIR 194(1) | Other |  |  |  |  | 108900
207 | Obligated and Awarded | (BIA) IRR | Federal Lands | NEVADA | CHURCHILL | Region H | 2 | H61A0700 | FALLON - PROJECT FIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 99303
208 | Obligated and Awarded | (BIA) IRR | Federal Lands | NEVADA | WASHOE | Region H | 2 | H61A0800 | PYRAMID LAKE - PROJECT PLIR 205(1) PELICAN POINT ROAD | Other |  |  |  |  | 120000
209 | Obligated and Awarded | (BIA) IRR | Federal Lands | NEVADA | WASHOE | Region H | 2 | H61A0900 | PYRAMID LAKE - PROJECT PLIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 130143
210 | Obligated and Awarded | (BIA) IRR | Federal Lands | UTAH | UINTAH | Region H | 2 | H62A0200 | UINTAH/OURAY - PROJECT UOIR 47(3) | Other |  |  |  |  | 970000
211 | Completed | (BIA) IRR | Federal Lands | UTAH | UINTAH | Region H | 2 | H62A0300 | UINTAH/OURAY - PROJECT UOIR9061(1) | Other | 2010-06-02 |  |  | 2010-05-05 | 407000
212 | Completed | (BIA) IRR | Federal Lands | UTAH | UINTAH | Region H | 2 | H62A0400 | UINTAH/OURAY - PROJECT UOIR 41(1) | Other | 2010-06-02 |  |  | 2010-05-05 | 446867
213 | Obligated and Awarded | (BIA) IRR | Federal Lands | NEVADA | NYE | Region H | 2 | H64A0200 | DUCKWATER SHOSHONE TRIBE - PROJECT DWIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 26463
214 | Obligated and Awarded | (BIA) IRR | Federal Lands | NEVADA | WHITE PINE | Region H | 2 | H64A0300 | ELY SHOSONE TRIBE - PROJECT ELIC SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 10233
215 | Completed | (BIA) IRR | Federal Lands | ARIZONA | COCONINO | Region H | 1 | H65A0100 | HOPI - HIR 2(11) | Other | 2010-04-12 | 2010-06-05 | 2010-08-10 | 2010-06-10 | 1074787.5
216 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | MOHAVE | Region H | 3 | H68A0100 | HUALAPAI - PROJECT HUIR 1(31)B | Pavement Improvement |  |  |  |  | 1974024
217 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | GILA | Region H | 4 | H68A0400 | YAVAPAI-TONTO APACHE - PROJECT TAIR SAFETY NO. 1 (STREET LIGHTS) | Safety/Traffic Management |  |  |  |  | 13106
218 | Obligated and Awarded | (BIA) IRR | Federal Lands | NEVADA | CLARK | Region H | 3 | H69A0100 | MOAPA RIVER - PROJECT MIR SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 16824
219 | Obligated and Awarded | (BIA) IRR | Federal Lands | UTAH | IRON | Region H | 1 | H69A0200 | PAIUTE-CEDAR - PROJECT CCIC SAFETY NO. 1 | Safety/Traffic Management |  |  |  |  | 79471
220 | Obligated and Awarded | (BIA) IRR | Federal Lands | ARIZONA | MOHAVE | Region H | 3 | H69A0300 | KAIBAB - PROJECT CHIP SEAL NO. 2 | Other |  |  |  |  | 84924
221 | Obligated and Awarded | (BIA) IRR | Federal Lands | OREGON | DOUGLAS | Region P | 4 | P01213R1 | COW CREEK - REST AREA | New Construction |  |  |  |  | 236234
222 | Obligated and Awarded | (BIA) IRR | Federal Lands | OREGON | COOS | Region P | 4 | P01603R1 | COOS TRIBE - MAIN BASE ROAD | Other |  |  |  |  | 86051
223 | Obligated and Awarded | (BIA) IRR | Federal Lands | OREGON | YAMHILL | Region P | 1 | P01809R1 | GRAND RONDE - FORESTRY WAY / NRD PARKING LOT | Other |  |  |  |  | 509340
224 | Obligated and Awarded | (BIA) IRR | Federal Lands | OREGON | LINCOLN | Region P | 5 | P01810R1 | SILETZ - HIGHWAY 229 SAFETY PROJECT | Pavement Improvement |  |  |  |  | 293200
225 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | STEVENS | Region P |  | P03602R1 | COLVILLE - GIFFORD FERRY DOCK | Bridge Improvement |  |  |  |  | 1416804.48
226 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | OKANOGAN | Region P |  | P03604R1 | COLVILLE - AGENCY STREETS | Pavement Improvement |  |  |  |  | 1986366
227 | Obligated and Awarded | (BIA) IRR | Federal Lands | IDAHO | BINGHAM | Region P | 2 | P04901R1 | FORT HALL - BENCH / MARSHALL ROAD RECONSTRUCTION | Pavement Improvement |  |  |  |  | 832815
228 | Obligated and Awarded | (BIA) IRR | Federal Lands | IDAHO | KOOTENAI | Region P | 1 | P05201R1 | COEURD'ALENE - OSPREY ACCESS & RESIDENTIAL STREETS WEST | Other |  |  |  |  | 95150
229 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | CLALLAM | Region P | 6 | P06012R1 | QUILEUTE - QUILEUTE CEMETARY ROAD | Pavement Improvement |  |  |  |  | 123312
230 | Underway | (BIA) IRR | Federal Lands | WASHINGTON | THURSTON | Region P | 3 | P06013R1 | CHEHALIS - OLD HWY 99 TURN LANE | Other | 2010-02-22 |  |  |  | 212395
231 | Completed | (BIA) IRR | Federal Lands | WASHINGTON | MASON | Region P | 6 | P06028R1 | SQAUXIN ISLAND - KLA-CHE-MIN DRIVE IMPROVEMENTS | Pavement Improvement | 2010-07-15 | 2010-07-19 |  | 2010-08-27 | 190755
232 | Underway | (BIA) IRR | Federal Lands | WASHINGTON | CLALLAM |  | 6 | P06040R1 | JAMESTOWN S'KLALLAM TRIBE - HIGHWAY 101 GUARDRAILS - ARRA | Safety/Traffic Management | 2010-01-14 | 2010-04-29 |  |  | 92172
233 | Underway | (BIA) IRR | Federal Lands | WASHINGTON | MASON |  |  | P06801R1 | SKOKOMISH - T3 BA-DAS PARKWAY | New Construction | 2010-05-21 |  |  |  | 141713
234 | Underway | (BIA) IRR | Federal Lands | WASHINGTON | CLALLAM |  | 6 | P06911R1 | LOWER ELWHA - HEALTH CLINIC ACCESS - ARRA | Pavement Improvement | 2010-02-08 | 2010-02-08 |  |  | 107294
235 | Underway | (BIA) IRR | Federal Lands | OREGON | UMATILLA |  | 2 | P07700R | UMATILLA - CAPITOL A.K.A. TI'MINE WAY | New Construction | 2009-09-29 | 2009-10-05 |  |  | 800250
236 | Obligated and Awarded | (BIA) IRR | Federal Lands | OREGON | JEFFERSON | Region P | 2 | P09111R1 | WARM SPRINGS - WEST HILLS PEDESTRIAN PATH PHASE 1 | Pavement Improvement |  |  |  |  | 372404
237 | Obligated and Awarded | (BIA) IRR | Federal Lands | OREGON | WASCO | Region P | 2 | P09509R1 | WARM SPRINGS - SIDWALTER FLAT STORM WATER | Pavement Improvement |  |  |  |  | 643879
238 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | SNOHOMISH | Region P | 2 | P10101R1 | TULALIP - 27TH AVENUE NORTHEAST | Pavement Improvement |  |  |  |  | 1895481
239 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | KITSUP` | Region P | 1 | P10113R2 | PORT GAMBLE - BEAR RIDGE AND LITTLE BOSTON ROADS | Other |  |  |  |  | 132048
240 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | SKAGIT | Region P | 2 | P10265R1 | SWINOMISH - SAHALIE DRIVE DRAINAGE AND ROAD IMPROVEMENT | Pavement Improvement |  |  |  |  | 446802
241 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | PIERCE | Region P | 8 | P10801R1 | PUYALLUP - EAST GRANDVIEW AVENUE | Pavement Improvement |  |  |  |  | 810616
242 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | YAKIMA | Region P | 4 | P11313R1 | YAKAMA - SIGNAL PEAK ROAD AND DRY LOGY ROAD | Pavement Improvement |  |  |  |  | 801554
243 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | PEND OREILLE | Region P | 5 | P12011R1 | KALISPEL - POW WOW ROAD HMA-0002 | Pavement Improvement |  |  |  |  | 42474
244 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | STEVENS | Region P | 5 | P12108R1 | SPOKANE - CHILD DEVELOPMENT CENTER ROAD | Pavement Improvement |  |  |  |  | 142519
245 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | STEVENS | Region P | 5 | P12111R1 | SPOKANE - FORD CLUSTER | Pavement Improvement |  |  |  |  | 534668
246 | Obligated and Awarded | (BIA) IRR | Federal Lands | MONTANA | LAKE | Region P | 1 | P13002R1 | FLATHEAD - REVAIS CREEK BRIDGE / MAGGIE ASHLEY COURT | Bridge Improvement |  |  |  |  | 388751
247 | Obligated and Awarded | (BIA) IRR | Federal Lands | WASHINGTON | CLALLAM | Region P | 6 | P16500R1 | MAKAH - BAY VIEW AVENUE GUARDRAIL REPLACEMENT | Safety/Traffic Management |  |  |  |  | 286893
248 | Completed | (BIA) IRR | Federal Lands | NEW YORK | FRANKLIN | Region S | 26 | S5030728 | SAINT REGIS MOHAWK TRIBE - IROQUOIS DRIVE | Other | 2010-03-26 | 2010-03-26 | 2012-03-30 | 2010-07-30 | 400719
249 | Completed | (BIA) IRR | Federal Lands | MAINE | AROOSTOOK | Region S | 2 | S5031907 | HOULTON BAND - BIA RT 323 - MALISEET DRIVE | Other | 2009-10-26 | 2009-11-04 | 2012-03-31 | 2011-06-30 | 54083
250 | Completed | (BIA) IRR | Federal Lands | LOUISIANA | ST. MARY PARISH | Region S | 3 | S5039708 | CHITIMACHA TRIBE - MMR | Other | 2010-03-26 | 2010-07-02 | 2011-09-30 | 2011-01-20 | 966304
251 | Completed | (BIA) IRR | Federal Lands | MAINE | PENOBSCOT | Region S | 2 | S5051803 | PENOBSCOT TRIBE - ACCESS AND LOOP ROAD | Pavement Improvement | 2009-12-16 | 2010-06-01 | 2010-09-30 | 2010-10-01 | 428766
252 | Underway | (BIA) IRR | Federal Lands | MASSACHUSETTS | DUKES | Region S | 10 | S5053003 | WAMPANOAG TRIBE OF GAY HEAD - LORAN STATION ROAD | Other | 2010-04-27 | 2010-04-27 | 2012-04-30 |  | 35060
253 | Completed | (BIA) IRR | Federal Lands | SOUTH CAROLINA | YORK | Region S | 5 | S5053207 | CATAWBA INDIAN NATION - RIVERCREST ROAD | Other | 2010-04-13 | 2010-04-13 | 2011-08-13 | 2011-04-25 | 125594
254 | Completed | (BIA) IRR | Federal Lands | LOUISIANA | LA SALLE PARISH | Region S | 5 | S5053417 | JENA BAND - MAIN STREET | New Construction | 2010-07-02 | 2010-07-09 | 2012-01-31 | 2012-01-31 | 40368
255 | Completed | (BIA) IRR | Federal Lands | LOUISIANA | AVOYELLES PARISH | Region S | 5 | S5053611 | TUNICA-BILOXI INDIAN TRIBE - MULTI-PURPOSE FACILITY PARKING CENTER | New Construction | 2009-12-11 | 2009-12-11 | 2010-09-30 | 2010-03-11 | 335512
256 | Completed | (BIA) IRR | Federal Lands | MAINE | AROOSTOOK | Region S | 2 | S50ARA13 | AROOSTOOK BAND (MICMAC) - SUMMIT DRIVE | New Construction | 2010-03-25 | 2010-03-25 | 2011-06-30 | 2010-06-01 | 148676
257 | Underway | (BIA) IRR | Federal Lands | ALABAMA | ESCAMBIA | Region S | 1 | S50FER01 | POARCH BAND - JUDSON ROAD | New Construction | 2010-01-28 | 2010-02-24 | 2012-09-30 |  | 220794
258 | Completed | (BIA) IRR | Federal Lands | MAINE | HANCOCK | Region S | 2 | S50FER02 | PASSAMAQ. - INDIAN TWP - PIT ROAD | New Construction | 2010-06-22 | 2010-07-01 | 2011-09-30 | 2011-08-09 | 177347
259 | Completed | (BIA) IRR | Federal Lands | NEW YORK | CATTARAUGUS | Region S | 027 | S50FER04 | CATTARAUGUS - JIMERSON LANE | Other | 2011-04-25 | 2011-05-01 | 2012-09-30 | 2011-10-18 | 247033
260 | Underway | (BIA) IRR | Federal Lands | ALABAMA | ESCAMBIA | Region S | 1 | S50FER11 | POARCH BAND - BUILDING 300 AND 400 | Pavement Improvement | 2010-09-01 | 2010-10-04 | 2012-09-30 |  | 110190
261 | Completed | (BIA) IRR | Federal Lands | MASSACHUSETTS | BARNSTABLE | Region S | 10 | S50RM350 | MASHPEE WAMPANOAG - MASHPEE WAMPANOAG ROAD MAINTENANCE | Other | 2010-03-24 | 2011-01-03 | 2011-09-30 | 2011-09-30 | 116244
262 | Underway | (CFL) BLM | Federal Lands | ARIZONA | MOHAVE |  | 02 | 1516049300001 | Add a paved right turn lane to US Highway 93 at the driveway to the Monolith Gardens Trailhead | Pavement Improvement | 2010-02-23 |  |  |  | 90996.55
263 | Underway | (CFL) BLM | Federal Lands | CALIFORNIA | ALPINE |  | 03 | 1516060660001 | Add a new layer of asphalt to the Indian Creek Access Road, Campground Loop and Boat Parking Lot. | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-09-27 |  | 81582.5
264 | Underway | (CFL) BLM | Federal Lands | CALIFORNIA | ALPINE |  | 03 | 1516060660002 | Construct 200 feet of new roadway access from Airport Road to the trailhead. Construct a new gravel parking lot | New Construction | 2010-07-06 |  | 2010-09-27 |  | 39303.19
265 | Underway | (CFL) BLM | Federal Lands | CALIFORNIA | MONTEREY |  | 17 | 1516061904101 | Add gravel to 5 miles of various roads and replace the bridge over El Toro Creek with a low water crossing within the Ft. Ord Management Area. | Bridge Replacement | 2010-01-21 |  | 2010-08-20 |  | 92352.77
266 | Underway | (CFL) BLM | Federal Lands | CALIFORNIA | MONTEREY |  | 17 | 1516061904301 | Replace 25 culverts in Ft. Ord Management Area | Pavement Improvement | 2010-01-21 |  | 2010-08-20 |  | 33961.02
267 | Underway | (CFL) BLM | Federal Lands | CALIFORNIA | LASSEN |  | 04 | 1516062376001 | Replace the 90 foot portion of the Bizz Johnson Trail Bridge Number 9 that burned in the Devil's Incident Fire in 2000. | Bridge Improvement | 2010-01-21 |  | 2010-10-08 |  | 1566727.14
268 | Underway | (CFL) BLM | Federal Lands | CALIFORNIA | LAKE |  | 01 | 1516065403001 | Add gravel and pave 2 miles of Mendo Lake Road. | Pavement Improvement | 2010-01-21 |  | 2010-08-20 |  | 85869.39
269 | Underway | (CFL) BLM | Federal Lands | NEVADA | CHURCHILL |  | 02 | 1516323133001 | Pave 1.4 miles of Sand Mountain Access Road. | Pavement Improvement | 2009-12-10 | 2009-12-10 |  |  | 108635.22
270 | Underway | (CFL) BLM | Federal Lands | NEW MEXICO | SANDOVAL |  | 03 | 1516351011001 | Pave 4.69 miles of Tent Rocks Road | Pavement Improvement | 2010-02-23 |  | 2010-10-01 |  | 609215.95
271 | Underway | (CFL) BLM | Federal Lands | WYOMING | WASHAKIE |  | 01 | 1516561435001 | Construct gravel surfacing on HU Clarks Fork, HU Nowater Road, and HU 2 Mile Hill Roads. | Pavement Improvement | 2010-09-17 |  |  |  | 6563.62
272 | Underway | (CFL) BLM | Federal Lands | WYOMING | FREMONT |  | 01 | 1516562302001 | Construct gravel surfacing on Hudson Atlantic Road. | Pavement Improvement | 2009-09-30 |  | 2010-06-30 |  | 1205476.6
273 | Completed | (CFL) BLM | Federal Lands | WYOMING | CARBON |  | 01 | 1516563301001 | Construct gravel surfacing on Bridger Pass and Barrel Springs Roads. | Pavement Improvement | 2009-09-14 | 2009-09-15 | 2009-12-01 | 2009-11-14 | 1565391.07
274 | Completed | (CFL) BLM | Federal Lands | WYOMING | SWEETWATER |  | 01 | 1516564115001 | Construct gravel surfacing on Sand Dunes Recreation Site and White Mountain Petroglphs Roads. | Pavement Improvement | 2010-02-08 |  | 2010-05-30 | 2010-06-18 | 317850.58
275 | Underway | (CFL) BLM | Federal Lands | WYOMING | SUBLETTE |  | 01 | 1516565201001 | Construct gravel surfacing on Upper Green and Scab Creek Roads. | Pavement Improvement | 2010-05-28 |  | 2010-09-15 |  | 637680.3
276 | Underway | (CFL) FS | Federal Lands | COLORADO | BOULDER |  | 02 | 1516081121001 | Construct a new parking lot for 120 cars, and construct a fee station booth, warming hut, and pit toilet. | New Construction | 2010-08-20 |  |  |  | 1557340.38
277 | Underway | (CFL) NPS | Federal Lands | ARIZONA | APACHE |  |  | 1516045501002 | {Project Description} | Pavement Improvement | 2010-06-10 |  | 2010-12-03 |  | 427.97
278 | Underway | (CFL) NPS | Federal Lands | CALIFORNIA | SHASTA |  | 02 | 1516063201003 | Project involves pulverizing, hot asphalt concrete pavement, pavement preservation and drainage improvements on 35.6 kilometers of roadway on Lassen Park Road in Lassen Volcanic National Park, Shasta County, California. The primary work consists of 133,3 | Pavement Improvement | 2009-08-26 |  | 2010-11-15 |  | 8686.56
279 | Underway | (CFL) NPS | Federal Lands | NEVADA | CLARK |  |  | 1516322800109 | Rehabilitate roadway pavement and drainage structures on approximately 17.5 miles of the Northshore Road from the Redstone Parking Area to the North Park Boundary. | Pavement Improvement | 2009-11-02 |  | 2010-08-29 |  | 7109015.75
280 | Underway | (CFL) NPS | Federal Lands | NEW MEXICO | SANTA FE |  | 03 | 1516351520001 | Rehabilitate various campgrounds, residential areas, and maintenance locations. Also, improve drainage issues and construction of new sewer lines. | Other | 2010-06-10 |  | 2010-10-01 |  | 43157.48
281 | Underway | (CFL) NPS | Federal Lands | TEXAS | BREWSTER |  | 23 | 15C6482010002 | Pavement Preservation at Big Bend NP | Pavement Improvement | 2010-07-16 |  |  |  | 112518.97
282 | Underway | (CFL) NPS | Federal Lands | UTAH | KANE |  | 02 | 15J6082008002 | Pavement preservation of most paved surfaces in Glen Canyon National Recreation Area. This recreation area lies in Northern Arizona and Southern Utah. The preservation treatments used are chip seals and modified slurry seals. The project has nearly 600 | Pavement Improvement | 2010-04-21 |  | 2010-10-01 |  | 4626127.4
283 | Completed | (CFL) NPS | Federal Lands | ARIZONA | COCONINO |  | 02 | 15K6082008002 | Pavement preservation of the paved surfaces in the North Rim Section of Grand Canyon National Park. The preservation treatments being used are chip seals and modified slurry seals. The project has approximately 430,000 square yards of chip seal and 70,0 | Pavement Improvement | 2010-05-13 |  | 2010-09-03 | 2010-09-28 | 1568407
284 | Underway | (CFL) NPS | Federal Lands | ARIZONA | PIMA |  | 01,07,08 | 15L6082008002 | Construct chipseals on all routes within Canyon De Chelly, Chiricahua, Fort Bowie, Organ Pipe, Saguaro, Tonto, and Tumacacori National Monuments. | Pavement Improvement | 2009-09-24 |  | 2009-11-20 |  | 2687747.81
285 | Underway | (EFL) NPS | Federal Lands | MARYLAND | WASHINGTON |  |  | 1515243120001 | The purpose of this project is to mill and overlay approximately 5 miles of tour loop roads within the National Battlefield, including parking areas. In addition, the project will include rehabilitat | Pavement Improvement | 2010-07-06 | 2010-07-06 |  |  | 2732191.75
286 | Completed | (EFL) NPS | Federal Lands | NORTH CAROLINA | HENDERSON |  | 11 | 1515375140064 | Repairs to Buck Springs Tunnel | Other | 2010-06-01 | 2010-06-01 | 2011-09-02 | 2010-09-30 | 455840.03
287 | Underway | (EFL) NPS | Federal Lands | PENNSYLVANIA | CARBON |  | 11 | 1515420630003 | Repair rock slide with property owned by the National Park Service in the Lehigh Gap area above State Route 248. | Transportation Enhancements | 2010-07-14 | 2010-07-14 |  | 2012-12-14 | 4259937.14
288 | Completed | (HQFL) IRR | Federal Lands | ALASKA | YUKON - KOYUKUK AREA |  | 1 | 000002 | MANLEY VILLAGE COUNCIL - DESIGN & CONSTRUCT TRANSIT SYSTEM FACILITY | New Construction | 2010-06-01 | 2009-05-15 | 2010-01-30 | 2010-01-30 | 67465
289 | Completed | (HQFL) IRR | Federal Lands | SOUTH DAKOTA | SHANNON |  | 1 | 0000046 | OGLALA SIOUX TRIBE - BIA Rt. 41 Asphalt | Pavement Improvement |  |  |  | 2010-06-30 | 3961018
290 | Completed | (HQFL) IRR | Federal Lands | NEW MEXICO | SANDOVAL |  |  | 1499 | JEMEZ PUEBLO - SP382 HEAD START ACCESS ROAD | Other | 2010-06-21 | 2010-06-21 | 2010-11-18 | 2010-11-18 | 340468
291 | Completed | (HQFL) IRR | Federal Lands | OKLAHOMA | PONTOTOC |  |  | 2401 | CHICKASAW NATION - KULLIHOMA | Pavement Improvement | 2010-09-27 | 2010-09-27 |  | 2011-08-23 | 2450000
292 | Completed | (HQFL) IRR | Federal Lands | OKLAHOMA | PONTOTOC |  |  | 2421 | CHICKASAW NATION - LOVELADY ROAD | Other | 2010-09-07 | 2010-09-07 |  | 2011-07-04 | 2150000
293 | Underway | (HQFL) IRR | Federal Lands | OKLAHOMA | BRYAN |  | 2 | 3808 | CHICKASAW NATION - LEAVENWORTH TRAIL $1,646,042 in RADS | Other | 2010-04-26 | 2010-04-26 | 2011-01-21 |  | 2204947
294 | Completed | (HQFL) IRR | Federal Lands | OKLAHOMA | CHEROKEE |  | 2 | 090506 | CHEROKEE NATION - Dry Creek Roak | Other |  |  |  | 2010-08-31 | 1500000
295 | Completed | (HQFL) IRR | Federal Lands | ALASKA | MATANUSKA - SUSITNA BOROUGH |  | 1 | 0108102 | CHICKALOON NATIVE VILLAGE - Route 4660 Todd's Road | New Construction | 2009-11-19 | 2010-04-01 | 2011-09-30 | 2011-09-30 | 524420
296 | Completed | (HQFL) IRR | Federal Lands | OKLAHOMA | ADAIR |  | 2 | 000040082807 | CHEROKEE NATION - Greasy Road | Pavement Improvement |  |  |  | 2010-06-30 | 1789468
297 | Completed | (HQFL) IRR | Federal Lands | OKLAHOMA | CHEROKEE |  | 2 | 000040093104 | CHEROKEE NATION - Rice-Woodward Road | Pavement Improvement |  |  |  | 2011-02-28 | 3440690
298 | Completed | (HQFL) IRR | Federal Lands | CALIFORNIA | DEL NORTE |  | 1 | 52564304 | SMITH RIVER RANCHERIA - NORTH SOUTH INDIAN ROADS | Other | 2010-02-22 | 2010-02-22 | 2011-02-22 | 2011-02-22 | 155339
299 | Completed | (HQFL) IRR | Federal Lands | OKLAHOMA | MAYES |  | 2 | 0616077107 | CHEROKEE NATION - Salina-Kenwood | Other |  |  |  | 2010-08-31 | 1980000
300 | Completed | (HQFL) IRR | Federal Lands | OKLAHOMA | SEQUOYAH |  |  | 1608162207 | CHEROKEE NATION - NICUT ROAD (SOUTH) | Other | 2010-07-07 | 2010-07-19 | 2010-10-19 | 2010-10-19 | 911740
301 | Completed | (HQFL) IRR | Federal Lands | NEW MEXICO | CIBOLA |  | 2 | 6810E00101 | RAMAH NAVAJO CHAPTER - HPP - MTN. VIEW SUBDIVISION ROAD | Pavement Improvement | 2010-08-10 | 2010-08-12 | 2011-02-22 | 2011-02-22 | 1000000
302 | Completed | (HQFL) IRR | Federal Lands | TEXAS | EL PASO |  | 16 | 6810E00132 01 | YSLETA DEL SUR PUEBLO - FM 258 (SOCORRO RD.) | Safety/Traffic Management | 2010-06-01 | 2010-06-15 | 2010-09-01 | 2010-08-10 | 208525
303 | Completed | (HQFL) IRR | Federal Lands | SOUTH DAKOTA | CORSON |  | 1 | A10-302-3-11 | STANDING ROCK SIOUX TRIBE - Kenel Road Reconstruction | Other |  | 2009-09-22 |  | 2010-07-31 | 1169796
304 | Obligated and Awarded | (HQFL) IRR | Federal Lands | MONTANA | ROOSEVELT |  | 1 | C5660920 | FORT PECK TRIBE - Route 1 - Box Elder to Blair | Pavement Improvement |  |  |  |  | 3855371
305 | Completed | (HQFL) IRR | Federal Lands | ALASKA | PRINCE OF WALES - OUTER KETCHIKAN (CA) |  | 1 | E00450304 | CRAIG COMMUNITY - HPP - Port Saint Nicholas Road Reconstruction | Other | 2010-05-10 | 2010-05-10 | 2012-12-31 | 2010-12-30 | 668680
306 | Completed | (HQFL) IRR | Federal Lands | ALASKA | VALDEZ - CORDOVA |  | 1 | E0114804 | EYAK VILLAGE - HPP - Whitshed Road-Hayney Bay Subdivision | Pavement Improvement | 2009-12-24 | 2010-02-01 | 2011-05-21 | 2011-05-21 | 1000000
307 | Completed | (HQFL) IRR | Federal Lands | ALASKA | VALDEZ - CORDOVA |  | 1 | E0114804 | EYAK VILLAGE - WHITSHED ROAD EXTENSION $1,267,760 in RADS | New Construction | 2009-12-24 | 2010-02-01 | 2011-05-21 | 2011-05-21 | 1267760
308 | Underway | (HQFL) IRR | Federal Lands | ALASKA | HAINES BOROUGH |  | 1 | E0180001 | CHILKOOT INDIAN ASSOCIATION - CHILKOOT ESTATES | New Construction | 2009-06-17 | 2009-08-24 | 2012-10-31 | 2012-10-31 | 1194726
309 | Underway | (HQFL) IRR | Federal Lands | ALASKA | BETHEL AREA |  | 1 | E0224101 | KASIGLUK TRADITIONAL ELDERS COUNCIL - ARRA Maintenance | Other | 2009-12-24 | 2010-04-01 | 2010-09-30 |  | 8292
310 | Underway | (HQFL) IRR | Federal Lands | ALASKA | BETHEL AREA |  | 1 | E0224102 | KASIGLUK TRADITIONAL ELDERS COUNCIL - Capital Purchase | Other | 2009-12-24 |  | 2010-09-30 |  | 24879
311 | Underway | (HQFL) IRR | Federal Lands | ALASKA | BETHEL AREA |  | 1 | E0249701 | TULUKSAK NATIVE COMMUNITY - Transit Capital Purchase $37,293 in RADS | Other | 2009-12-24 |  | 2010-09-30 |  | 37293
312 | Underway | (HQFL) IRR | Federal Lands | ALASKA | KUSKOKWIM |  | 1 | E0302201 | ANVIK VILLAGE - GRAVEL PIT ROAD DESIGN $13,813 in RADS | Other | 2010-01-08 |  | 2010-12-31 |  | 13813
313 | Underway | (HQFL) IRR | Federal Lands | ALASKA | UPPER YUKON |  | 1 | E0316201 | FORT YUKON TRIBE - RABBIT LINE SUBDIVISION | New Construction | 2009-10-15 | 2009-10-15 |  |  | 1121741
314 | Underway | (HQFL) IRR | Federal Lands | ALASKA | SOUTHEAST FAIRBANKS AREA |  | 1 | E0348301 | TETLIN VILLAGE - ADDITIONAL SPECIAL MAINTENANCE | Other | 2009-12-31 | 2010-02-15 | 2010-06-30 |  | 25000
315 | Underway | (HQFL) IRR | Federal Lands | ALASKA | SOUTHEAST FAIRBANKS AREA |  | 1 | E0348302 | TETLIN VILLAGE - ARRA TRANSIT PASSENGER SHELTERS | Safety/Traffic Management | 2009-12-31 | 2010-01-19 | 2010-09-30 |  | 1090000
316 | Underway | (HQFL) IRR | Federal Lands | ALASKA | SOUTHEAST FAIRBANKS AREA |  | 1 | E0348303 | TETLIN VILLAGE - TETLIN ROAD SAFETY PROJECT | Safety/Traffic Management | 2009-12-31 | 2010-01-19 | 2010-09-30 |  | 113494
317 | Underway | (HQFL) IRR | Federal Lands | ALASKA | YUKON - KOYUKUK AREA |  | 1 | E0363401 | HEALY LAKE VILLAGE - EROSION / DUST CONTROL | Other | 2010-01-08 |  | 2010-09-30 |  | 150136
318 | Completed | (HQFL) IRR | Federal Lands | ALASKA | WRANGELL-PETERSBURG AREA |  | 1 | E0953222 | ANTTC - WRANGELL COOPERATIVE ASSOCIATION - WRANGELL ROAD REHABILITATION | Pavement Improvement |  |  | 2010-09-30 | 2011-08-31 | 1182361
319 | Completed | (HQFL) IRR | Federal Lands | OKLAHOMA | PAWNEE |  | 3 | FAPBR.CN 037 | PAWNEE NATION OF OKLAHOMA - Black Bear Creek (Skedee Bridge) | Safety/Traffic Management | 2009-12-22 | 2010-01-26 |  | 2011-01-24 | 649514
320 | Completed | (HQFL) IRR | Federal Lands | ALASKA | PRINCE OF WALES - OUTER KETCHIKAN (CA) |  | 1 | FY09 IRR 002 | KASAAN , ORGANIZED VILLAGE OF - DOT Facility $1,050,404 in RADS | New Construction | 2010-01-04 |  | 2010-06-01 | 2010-06-01 | 1050404
321 | Completed | (HQFL) IRR | Federal Lands | ARIZONA | PINAL |  | 6 | GRIR 103 | GILA RIVER INDIAN COMMUNITY - Vah Ki Rd (IRR 103) Phase I $1,362,231 in RADS | Other | 2010-03-24 | 2010-03-01 | 2010-07-30 | 2010-06-30 | 1365231
322 | Completed | (HQFL) IRR | Federal Lands | CALIFORNIA | HUMBOLT OR SISKIYOU |  | 2 | J5255541 | KARUK TRIBE - KARUK (ANAVKAAM RD) RESERVATION RD | Bridge Replacement | 2010-05-15 | 2010-05-20 | 2010-07-29 | 2010-07-29 | 393642
323 | Completed | (HQFL) IRR | Federal Lands | OKLAHOMA | OSAGE |  | 3 | ON 1009 | OSAGE TRIBE OF INDIANS OF OKLAHOMA - Prue Road | Pavement Improvement | 2010-04-12 | 2010-05-05 | 2011-10-15 | 2011-05-12 | 4137864
324 | Underway | (HQFL) IRR | Federal Lands | WASHINGTON | SNOHOMISH |  | 2 | P10145R1 | STILLAGUAMISH TRIBE - TRANSIT CAPITAL ACQUISITION | Safety/Traffic Management | 2010-02-23 | 2010-03-15 |  |  | 220000
325 | Completed | (HQFL) IRR | Federal Lands | WASHINGTON | SNOHOMISH |  | 2 | P10146R1 | STILLAGUAMISH TRIBE - CAPITAL ACQUISITION | Safety/Traffic Management | 2010-02-23 | 2010-03-15 |  | 2010-04-29 | 45000
326 | Underway | (HQFL) IRR | Federal Lands | WASHINGTON | WHATCOM |  | 2 | P10401R1 | LUMMI - ROBERTSON ROAD | Safety/Traffic Management | 2010-05-14 | 2010-08-01 | 2010-09-30 |  | 192005
327 | Underway | (HQFL) IRR | Federal Lands | WASHINGTON | WHATCOM |  | 2 | P10402R1 | LUMMI - BLACKHAWK WAY PEDESTRIAN PATH | Safety/Traffic Management | 2010-05-14 | 2010-06-14 | 2010-09-30 |  | 100000
328 | Underway | (HQFL) IRR | Federal Lands | WASHINGTON | WHATCOM |  | 2 | P10403R1 | LUMMI - KWINA ROAD PEDESTRIAN PATH | Safety/Traffic Management | 2010-05-14 | 2010-05-20 | 2010-07-30 |  | 120000
329 | Completed | (HQFL) IRR | Federal Lands | ALASKA | WRANGELL-PETERSBURG AREA |  | 1 | PIA10020 | PETERSBURG INDIAN ASSOCIATION - SIDEWALK RECONS $42,000 in RADS | Other | 2010-04-20 | 2010-04-20 | 2010-05-10 | 2010-05-10 | 724719
330 | Underway | (HQFL) IRR | Federal Lands | NEW MEXICO | CIBOLA |  | 2 | RN 125 | RAMAH NAVAJO CHAPTER - Veteran's Highway $644,000 in RADS | Other | 2009-05-26 |  | 2009-08-31 |  | 644107
331 | Completed | (HQFL) IRR | Federal Lands | NORTH DAKOTA | ROLETTE |  | 1 | TMBC 0802 | TURTLE MOUNTAIN BAND OF CHIPPEWA INDIANS - Transit Facility | New Construction |  |  |  | 2011-08-31 | 1605126
332 | Completed | (HQFL) IRR | Federal Lands | NEW MEXICO | MCKINLEY |  | 3 | Z331 2 2&4 | ZUNI TRIBE - Cedar Street | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2010-10-30 | 2010-10-30 | 856925
333 | Completed | (WFL) BLM | Federal Lands | OREGON | LANE |  | 04 | 1517412009002 | Replace 11 culverts total on low volume BLM roads, and related road reconstruction at the culvert sites. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2011-10-14 | 2011-10-09 | 60.9
334 | Completed | (WFL) FS | Federal Lands | IDAHO | LEMHI |  | 02 | 1517166030001 | Replace three deficient bridges in the Salmon-Challis NF | Bridge Replacement | 2009-07-01 | 2009-07-01 | 2012-10-31 | 2010-09-30 | 727722.88
335 | Underway | (WFL) FS | Federal Lands | OREGON | COOS |  | 04 | 1517410330004 | Stablize the road and improve drainage at various locations along a 30 mile segment of the Agness Road located near Gold Beach Oregon. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2012-08-03 | 2010-09-30 | 566168.68
336 | Completed | (WFL) FS | Federal Lands | OREGON | COOS |  | 04 | 1517411376001 | Stablize the substructure and repair the superstructure of this bridge over the Upper Chetco River located near Brookings Oregon | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2011-07-22 | 2011-07-22 | 377755.57
337 | Completed | (WFL) FS | Federal Lands | WASHINGTON | SKAMANIA |  | 03, 04 | 1517532009004 | Design Phase and approval process. Replacing 9 to 12 bridges with fabricatd modular bridges at various sites within the Gifford Pinchot National Forest | Other | 2009-07-01 | 2009-07-01 | 2010-09-30 | 2010-09-30 | 326441.51
338 | Completed | (WFL) FS | Federal Lands | WASHINGTON | LEWIS |  | 04 | 1517532009005 | Prepare a feasibility study to replace the Jody Mullins Bridge. The bridge provides access to trailheads and other FS?s resources. The Jody Mullins Bridge is located on Milepost 0.6 Forest Road 1270, in the Gifford Pinchot National Forest, | Other | 2009-07-01 | 2009-07-01 | 2010-09-30 | 2010-09-30 | 41122.91
339 | Completed | (WFL) FS | Federal Lands | WASHINGTON | LEWIS |  | 04 | 1517532009006 | Develop documents to remove the current bridge and replace with a temporary bridge. The temporary bridge will reopen the Skate Creek bridge which currently is closed. | Other | 2009-07-01 | 2009-07-01 | 2010-09-30 | 2010-09-30 | 94933.4
340 | Completed | Federal Lands Central Division | Federal Lands | ARIZONA | APACHE |  |  | 1516040431003 | Near Eagar Arizona, install pavement over a previously constructed gravel road surface on Forest Highway 43 from the West Baldy Parking Area (8.5 miles south of State Highway 260) to the intersection | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-11-01 | 2009-11-01 | 2444472.3
341 | Underway | Federal Lands Central Division | Federal Lands | ARIZONA | APACHE |  |  | 1516040431004 | 4.570 km of grading, drainage and paving and 8.964 km of 3R work. | Other | 2010-01-10 |  | 2010-10-29 |  | 970676.7
342 | Underway | Federal Lands Central Division | Federal Lands | ARIZONA | COCONINO |  |  | 1516043050003 | Design (provide completed plans, drawings and specifications for) the Depot Tour Bus Parking Area at the South Rim Grand Canyon National Park, Arizona (the plans are currently 10% complete). | Other | 2009-09-16 |  |  |  | 998608.84
343 | Completed | Federal Lands Central Division | Federal Lands | CALIFORNIA | NEVADA |  |  | 1516061231001 | Remove existing pavement and repave approximately 5 miles of Washington Road from the intersection of SR 20 to a point just south of the town of Washington. | Pavement Improvement | 2009-05-28 | 2009-06-29 | 2009-11-01 | 2009-12-02 | 4651073.51
344 | Completed | Federal Lands Central Division | Federal Lands | CALIFORNIA | EL DORADO |  |  | 1516061371004 | On Wentworth Springs Road (in El Dorado County, California) remove the existing pavement and repave approximately 5 miles of roadway from mile post 1.30 to mile post 6. | Pavement Improvement | 2009-08-07 | 2009-08-10 | 2009-12-01 | 2009-12-04 | 2499037.7
345 | Underway | Federal Lands Central Division | Federal Lands | CALIFORNIA | MONO |  |  | 1516061381001 | The project is to rehabilitate, restore, and resurface the existing roadway pavement. The project work includes minor grading, drainage, pulverization, aggregate base and HACP. Road construction is | Pavement Improvement | 2010-06-14 |  | 2010-11-15 |  | 830237.79
346 | Completed | Federal Lands Central Division | Federal Lands | CALIFORNIA | MARIPOSA |  |  | 1516063401501 | Remove existing pavement and repave approximately 5.05 miles of roadway, and 2.17 lane miles of paved parking, in Yosemite National Park. The project includes the roadway from Chinquapin intersection | Pavement Improvement | 2009-06-02 | 2009-06-03 | 2009-11-30 | 2010-06-10 | 9227368.48
347 | Underway | Federal Lands Central Division | Federal Lands | CALIFORNIA | MARIPOSA |  |  | 1516063414004 | The Wawona Road project consists of pulverizing and overlaying 24.4 miles of Wawona Road (Highway 41) through Yosemite National Park. The scope of work includes pulverizing 8" of existing road and ov | Pavement Improvement | 2010-05-03 |  | 2009-11-08 |  | 6768783.57
348 | Completed | Federal Lands Central Division | Federal Lands | CALIFORNIA | INYO |  |  | 1516063901102 | Pulverize roadway and overlay with asphalt pavement, and install drainage culverts on approximately 33.3 mile of the Bonnie Claire Road from mile post 7.4 at the junction of Ubehebe Crater Road to mil | Pavement Improvement | 2009-07-30 | 2009-08-17 | 2010-05-30 | 2010-06-22 | 12513474.87
349 | Completed | Federal Lands Central Division | Federal Lands | CALIFORNIA | DEL NORTE |  |  | 1516064710201 | Pulverize existing pavement and overlay with new pavement, and install new draininage ay pavement and drainage structures on approximately 2.18 miles of two-lane roadway between Costal Drive and Klama | Pavement Improvement | 2009-05-13 | 2009-05-18 | 2009-10-30 | 2010-08-10 | 2953114.03
350 | Underway | Federal Lands Central Division | Federal Lands | COLORADO | MONTEZUMA |  |  | 1516080301009 | At Mesa Verde National apark in Colorado, remove existing pavement and repave the main entrance road from the Park entrance at Highway 160 to the Park Point Overlook. The project also includes adding | Pavement Improvement | 2009-06-15 | 2009-06-24 | 2010-08-30 |  | 12083871.14
351 | Underway | Federal Lands Central Division | Federal Lands | COLORADO | CLEAR CREEK |  |  | 1516088012023 | Recondition, regrade and pave approximately seven (7) miles of existing aggregate and chip seal surface on Guanella Pass, near Georgetown, Colorado. This work is near the boundary of Clear Creek and | Pavement Widening | 2008-07-07 | 2009-08-06 | 2010-10-01 |  | 4600749
352 | Completed | Federal Lands Central Division | Federal Lands | COLORADO | RIO GRANDE |  |  | 1516088501002 | Recondition and resurface the existing one-way loop road with aggregate (gravel) surfacing. Construct better defined boundaries for existing pullouts, create additional small pullouts where there is | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-09-01 | 2009-10-31 | 292322.77
353 | Underway | Federal Lands Central Division | Federal Lands | NEBRASKA | SIOUX |  |  | 1516310071004 | Design a box culvert drain structure and resurface approximately 1 mile of roadway. | Other | 2009-09-11 | 2009-09-11 |  |  | 79132
354 | Completed | Federal Lands Central Division | Federal Lands | NEVADA | WASHOE |  |  | 1516320002001 | Construct a left turn lane and acceleration/deceleration lanes for the Galena Recreation Facilities at approximately mile post 18 on State Highway 28. | Pavement Widening | 2010-05-05 |  | 2010-07-01 | 2010-07-12 | 842787
355 | Underway | Federal Lands Central Division | Federal Lands | COLORADO | DENVER |  |  | 1516350057101 | Develop design drawings and specifications, including environmental studies and clearances, for the replacement of six small bridges in Cibola National Forest in New Mexico state. | Other | 2009-05-13 | 2009-05-13 | 2010-03-01 |  | 539949.02
356 | Completed | Federal Lands Central Division | Federal Lands | NEW MEXICO | SANDOVAL |  |  | 1516350121006 | Contract modification to existing project between Cuba and LaCueva, NM, to add roadway drainage improvements to protect the roadway and to enhance stream water quality. | Other | 2009-06-29 | 2009-06-29 | 2009-07-18 | 2009-07-31 | 700000
357 | Underway | Federal Lands Central Division | Federal Lands | COLORADO | DENVER |  |  | 1516350121009 | Design services for the development of 100% plan set on project NM 12-1(9) and 70% set plan development on NM PFH12-1(10) for the reconstruction and paving of an existing | Other | 2009-06-29 | 2009-06-30 | 2011-09-01 |  | 1138149.98
358 | Completed | Federal Lands Central Division | Federal Lands | NORTH DAKOTA | MCKENZIE |  |  | 1516381701003 | This project involves the removal of the existing asphalt pavement and replacement with new asphalt pavement on 13.8 miles of roadway within the North Unit of Theodore Roosevelt National Park. | Pavement Improvement | 2009-06-04 | 2009-06-07 | 2009-10-30 | 2009-11-21 | 7783950.45
359 | Completed | Federal Lands Central Division | Federal Lands | NORTH DAKOTA | WARD |  |  | 1516383040111 | Recondition and resurface Route 11, Lower Lake Road (at Des Lacs National Wildlife Refuge, in North Dakota) to a uniform width of 22 feet and regravel. Additionally, Lower Lake Parking 1 will be regr | Pavement Improvement | 2009-07-06 | 2009-07-28 | 2009-08-01 | 2009-10-02 | 772728.16
360 | Completed | Federal Lands Central Division | Federal Lands | NORTH DAKOTA | MCHENRY |  |  | 1516383111201 | Reconstruction of two bridges (Willow Creek and Johnson bridges). One bridge location will include a small parking area adjacent to it for canoe access to the river. | Bridge Replacement | 2009-09-30 |  | 2010-06-30 | 2010-07-09 | 434029.71
361 | Completed | Federal Lands Central Division | Federal Lands | NORTH DAKOTA | MCHENRY |  |  | 1516383111202 | Project begins at the Willow-Upham Road and ends at the intersection of Route 14. The project work consists of the reconstruction of one bridge (Souris River bridge) and 7 low water crossings along t | Pavement Improvement | 2010-06-29 |  |  | 2010-11-19 | 1622916.36
362 | Underway | Federal Lands Central Division | Federal Lands | OKLAHOMA | MURRAY |  |  | 1516405721502 | Pave 0.87 miles of trails adjacent to Route 215. | Other | 2010-07-14 |  | 2010-10-27 |  | 916470.57
363 | Underway | Federal Lands Central Division | Federal Lands | SOUTH DAKOTA | PENNINGTON |  |  | 1516460171006 | The project constructs pedestrian and bicycle overpasses and associated approaches at two locations on this route between Hill City and Lead. | Transportation Enhancements | 2010-04-19 |  | 2010-08-16 |  | 595110
364 | Completed | Federal Lands Central Division | Federal Lands | UTAH | SEVIER |  |  | 1516490391003 | Construct asphalt pavement surfacing on a previously constructed gravel surface on Forest Highway 39 from 5.1 miles south of I-70 (the end of the existing pavement) to the Gooseberry Administrative Si | Pavement Improvement | 2009-06-24 | 2009-07-07 | 2009-09-01 | 2009-11-05 | 1961852
365 | Completed | Federal Lands Central Division | Federal Lands | WYOMING | FREMONT |  |  | 1516560231003 | Recondition the existing aggregate surfacing and roadbed by scarifying and reshaping to provide for consistent cross slopes and width. The roadway will then be resurfaced with a new aggregate surface | Pavement Improvement | 2009-09-09 | 2009-08-19 | 2009-10-31 | 2009-10-31 | 1240877.68
366 | Underway | Federal Lands Central Division | Federal Lands | WYOMING | CARBON |  |  | 1516560261901 | Construction of two (2) small drainiage structures (box culverts) on Wyoming State Route 71, including grading, draining, and paving along the existing alignment to facilitate installation of 2 draina | Pavement Improvement | 2009-06-30 |  | 2009-10-01 |  | 778076.32
367 | Completed | Federal Lands Eastern Division | Federal Lands | ARKANSAS | JOHNSON |  |  | 1515050653007 | Reconstruct 1.4 miles of Arkansas Route 215 in the Ozark National Forest, Johnson County, Arkansas. Work includes grading, aggregate base, asphalt paving, drainage, curb and gutter, retaining walls, | Pavement Improvement | 2010-02-08 | 2010-02-08 |  | 2011-05-23 | 807252
368 | Completed | Federal Lands Eastern Division | Federal Lands | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA |  |  | 1515113400014 | Rehabilitate Ohio Drive and Old Constitution Avenue. | Pavement Improvement | 2010-04-12 | 2010-04-12 |  | 2010-12-03 | 2450894.72
369 | Completed | Federal Lands Eastern Division | Federal Lands | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA |  |  | 1515113400017 | This project consists of pavement rehabilitation on Madison Drive between 3rd and 14th streets. Primarily, the roadway will require a mill and overlay. However, a portion will require more extensiv | Pavement Improvement | 2010-10-18 | 2010-10-18 | 2012-01-04 | 2011-03-20 | 1003602.98
370 | Underway | Federal Lands Eastern Division | Federal Lands | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA |  |  | 1515113450012 | The primary purpose of this project is to mill and overlay asphalt and implement rehabilitation improvements to Rock Creek Parkway from P Street to Calvert Street. This includes replacing curb and gutter as needed, existing street lights, existing median barrier and adding new guardrail as necessary to protect adjacent multi-use trail. In addition, the project will improve the trail crossing at intersection with Beach Drive and Cathedral Avenue and mill and overlay on Cathedral Avenue from the Parkway to the park boundary. | Pavement Improvement | 2010-10-18 | 2010-10-18 |  |  | 7172264.4
371 | Underway | Federal Lands Eastern Division | Federal Lands | MISSISSIPPI | WINSTON |  |  | 1515280301002 | The Tombigbee National Forest is located in Choctaw County in Mississippi. This project consists of the full depth reconstruction and widening of Forest Highway 30 between Choctaw Lake and Forest Hig | Pavement Improvement | 2010-03-10 | 2010-03-10 | 2011-09-14 | 2010-11-19 | 430771
372 | Completed | Federal Lands Eastern Division | Federal Lands | PENNSYLVANIA | PIKE |  |  | 1515424320017 | The primary purpose of this project is to replacement Toms Creek Bridge along US Route 209. The work will include rehabilitation of US Route 209 from MP 4.3 to 5.3 including milling off the asphalt pa | Bridge Replacement | 2010-03-01 | 2009-10-01 |  | 2010-12-15 | 2306722.69
373 | Underway | Federal Lands Eastern Division | Federal Lands | PENNSYLVANIA | PIKE |  |  | 1515424320021 | Rehabilitation of Raymondskill Bridge along US Route 209 | Bridge Improvement | 2010-09-09 | 2010-10-18 |  |  | 2064760
374 | Completed | Federal Lands Eastern Division | Federal Lands | TENNESSEE | BLOUNT |  |  | 1515471220011 | The purpose of this project is to continue construction of "Missing Link" in the Foothills Parkway. The work will include the construction of one bridge (~800 feet ) and the construction of the roadwa | New Bridge Construction | 2009-05-21 | 2009-05-21 | 2011-12-01 | 2010-09-30 | 25298074.78
375 | Underway | Federal Lands Eastern Division | Federal Lands | TENNESSEE | BLOUNT |  |  | 1515471220017 | Construct multiple bridges on the Foothills Parkway Section 8E | New Bridge Construction | 2010-10-26 | 2010-10-26 |  |  | 7683020.34
376 | Completed | Federal Lands Eastern Division | Federal Lands | VERMONT |  |  | 4 | 1515500141001 | The project consists of the rehabilitation of approximately 0.57 miles of Lincoln Gap Road, and the rehabilitation of five existing pipe culvert crossings on Hapgood Pond Road. The work includes an aphalt overlay and other miscellaneous work. The project is located in Addison and Bennington Counties, Vermont. | Pavement Improvement | 2011-05-16 | 2011-05-16 |  | 2011-08-01 | 112980.8
377 | Completed | Federal Lands Eastern Division | Federal Lands | VIRGINIA | FAIRFAX |  |  | 1515513300049 | The primary purpose of this project is to generally rehabilitate three paved parking lots and the park access road at Daingerfield Island. The areas served include an active sailing marina and boat st | Pavement Improvement | 2010-06-01 | 2010-06-01 |  | 2010-11-08 | 452477
378 | Completed | Federal Lands Eastern Division | Federal Lands | VIRGINIA | ACCOMACK |  |  | 1515514190003 | Rehabilitate two bridges on Beach Drive | Bridge Improvement | 2010-11-29 | 2010-11-29 | 2011-08-10 | 2011-05-17 | 489100
379 | Completed | Federal Lands Eastern Division | Federal Lands | VERMONT |  |  |  | 1515514290001 | The project consists of the rehabilitation of approximately 0.57 miles of Lincoln Gap Road, and the rehabilitation of five existing pipe culvert crossings on Hapgood Pond Road. The work includes an aphalt overlay and other miscellaneous work. The project is located in Addison and Bennington Counties, Vermont. | Other | 2010-09-15 | 2010-09-15 | 2011-06-23 | 2010-11-30 | 373734.6
380 | Completed | Federal Lands Eastern Division | Federal Lands | VIRGINIA | YORK |  |  | 1515514290011 | The purpose of this projects is to rehabilitate five bridges within Colonial National Historical Park - Beaverdam Creek Bridge, Yorktown Creek Bridget, Powhatan Creek Bridget, and College Creek Bridge | Bridge Improvement | 2009-06-30 | 2009-06-30 | 2012-01-06 | 2011-07-20 | 1009734
381 | Completed | Federal Lands Eastern Division | Federal Lands | WEST VIRGINIA | PENDLETON |  |  | 1515540972001 | The Monongahela National Forest is located in Grant and Pendleton Counties in West Virginia. This project consists of paving a portion of Smoke Hole Road. The total construction length is 0.8 miles. | Pavement Improvement | 2010-04-01 | 2010-04-01 | 2010-10-13 | 2010-05-19 | 354775.79
382 | Completed | Federal Lands Eastern Division | Federal Lands | PUERTO RICO | RIO GRANDE |  |  | 1515720003001 | Repair slide on Route 9966 in the El Yunque National Forest | Pavement Improvement | 2010-01-25 | 2010-01-25 | 2011-11-18 | 2010-02-03 | 32883
383 | Completed | Federal Lands Eastern Division | Federal Lands | VIRGIN ISLANDS | ST. JOHN |  |  | 1515785360004 | The primary purpose of this project is to resurface the entire 7.5 miles of North Shore Road along with areas of shoulder reconditioning, drainage improvements, stone masonry edging at selected pull-o | Pavement Widening | 2009-09-28 | 2009-09-28 | 2012-02-21 | 2011-05-16 | 1397391.4
384 | Completed | Federal Lands Eastern Division | Federal Lands | NORTH CAROLINA | HYDE |  |  | 1515370MTK001 | Located in Hyde County, NC, the project will repair of two canal bridges, and resurface Lake Landing Road. The refuge had 90,000 visitors last year. | Bridge Replacement | 2010-02-15 | 2010-02-15 | 2011-09-14 | 2011-03-16 | 856788.2
385 | Completed | Federal Lands Eastern Division | Federal Lands | NORTH CAROLINA | ANSON |  |  | 1515370PED001 | The project consists of the rehabilitation of Wildlife Drive (Route 010), Sullivan Pond Road (Route 011), Ross Road (Route 101), and three parking areas within the Pee Dee National Wildlife Refuge. T | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-12-27 | 2010-08-24 | 767777.04
386 | Completed | Federal Lands Eastern Division | Federal Lands | SOUTH CAROLINA | CLARENDON |  |  | 1515450SNT001 | Located in Clarendon County, SC, the project will rehabilitate Center Road and Wildlife Drive, key access points serving thousands of motorists annually. The refuge is home to endangered species like | Pavement Improvement | 2009-06-30 | 2009-06-30 | 2010-03-22 | 2009-12-07 | 1304442.75
387 | Completed | Federal Lands Eastern Division | Federal Lands | TENNESSEE | STEWART |  |  | 1515470CRK001 | Located 75 miles NW of Nashville, TN, the project will upgrade Routes 12, 102, 104, and 105. The refuge, which receives 45,000 visitors annually, is a feeding and resting area for migratory birds and | Pavement Improvement | 2010-03-16 | 2010-03-16 | 2010-12-20 | 2010-08-25 | 778531.37
388 | Underway | Federal Lands Eastern Division | Federal Lands | VIRGINIA | FAIRFAX |  |  | 151551FFXPK05 | Phase IV of the Fairfax County Parkway Project consists of the construction of the Boudinot Drive Interchange. This new interchange will provide full access to the Parkway from the Fullerton Industri | New Construction | 2009-06-29 | 2009-06-29 | 2011-12-01 |  | 22800000
389 | Completed | Federal Lands Eastern Division | Federal Lands | VIRGINIA | FAIRFAX |  |  | 151551FFXPK06 | Phase III of the Fairfax County Parkway Project is the final segment required to complete the mainline Parkway. The project consists of constructing approximately 0.5 miles of 4-lane divided limited | New Construction | 2010-01-25 | 2010-01-25 | 2010-01-26 | 2010-01-26 | 22960459
390 | Completed | Federal Lands Eastern Division | Federal Lands | VIRGIN ISLANDS | ST. CROIX |  |  | 1515780SOP001 | Rehabilitate Tranburg Road | Pavement Improvement | 2010-08-13 | 2010-10-04 |  | 2011-10-06 | 1232181.67
391 | Completed | Federal Lands Eastern Division | Federal Lands | VIRGIN ISLANDS | ST. THOMAS |  |  | 151578LONGBAY | Reconstruct and widen 0.28 miles of Long Bay Road from Veteran's Drive to Centerline Road on St. Thomas, USVI. | Pavement Widening | 2009-11-16 | 2009-11-16 |  | 2011-08-17 | 5537155
392 | Underway | Federal Lands Eastern Division | Federal Lands | MISSISSIPPI | NOXUBEE |  |  | 15B5280NXB001 | This project consists of the rehabilitation of 18.2 miles of Bluff Lake Road, Brooksville-Louisville Road, and Section Line Road in Noxubee and Winston Counties, Mississippi. Bluff Lake Road and Broo | Pavement Improvement | 2009-06-19 | 2009-06-19 | 2011-08-01 | 2011-09-20 | 1436321.64
393 | Underway | Federal Lands Western Division | Federal Lands | ALASKA | ALEUTIANS EAST BOROUGH |  |  | 1517020200501 | This project involves upgrading about 4.3 miles of the local street system in the City of King Cove, including a new bridge or fish passage culverts over Ram Creek. The upgrades consist of constructi | Pavement Widening | 2009-09-01 | 2009-09-01 |  |  | 2059300
394 | Completed | Federal Lands Western Division | Federal Lands | ALASKA | PRINCE OF WALES-OUTER KETCHIKAN CENSUS AREA |  |  | 1517020440008 | In an effort to protect Tongass National Forest's streams and wildlife from impacts from exposed natural occurring acid rock; this project will cleanup affected areas, replace culverts, and buffer the | Other | 2009-07-01 | 2009-07-01 | 2010-05-31 | 2010-06-05 | 1766392.81
395 | Completed | Federal Lands Western Division | Federal Lands | ALASKA | PRINCE OF WALES-OUTER KETCHIKAN CENSUS AREA |  |  | 1517020440009 | This second project along Alaska's Coffman Cove Road will pave the 4.3 mile section of road within Tongass National Forest after the Acid Rock cleanup project AK PFH 44(8) is complete. | Other | 2009-07-01 | 2009-07-01 |  | 2010-09-10 | 2253006.19
396 | Underway | Federal Lands Western Division | Federal Lands | ALASKA | DENALI |  |  | 1517020701027 | This project will reconstruct unsafe road sections along Denali's National Park tour route enhancing the safety of Alaska's national park visitors. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-10-01 | 2010-10-15 | 2618031.6
397 | Underway | Federal Lands Western Division | Federal Lands | ALASKA | VALDEZ-CORDOVA CENSUS AREA |  |  | 1517022003003 | Development of a 12 mile road to the Shotgun Cove ending at Decision Point. Approximately the first 2.7 miles (sections 1 and 2) is a pioneer road. Currently, an environmental assessment is being co | Pavement Improvement | 2009-09-01 | 2009-09-01 |  |  | 3500000
398 | Underway | Federal Lands Western Division | Federal Lands | IDAHO | IDAHO |  |  | 1517160600005 | Located in Nez Perce National Forest, Oregon; this project will connect two recently constructed segments of Salmon River Road as well as extend the paving from Lake Creek Bridge to Spring Bar. This | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2013-05-23 |  | 5505024
399 | Completed | Federal Lands Western Division | Federal Lands | MONTANA | RAVALLI |  |  | 1517300780001 | Improving visitor safety to our national forest, this project will preserve the pavement on 14.5 miles of Montana's East Fork Bitterroot Road leading into the Bitterroot National Forest. | Pavement Improvement | 2009-07-01 | 2009-07-01 |  | 2010-10-15 | 3908804.72
400 | Completed | Federal Lands Western Division | Federal Lands | MONTANA | FLATHEAD |  |  | 1517302601031 | Reconstruct portion of the Going to the Sun Road in Glacier National Park Phase. | Pavement Improvement | 2009-08-01 | 2009-08-01 | 2011-10-31 | 2011-10-26 | 8351171.55
401 | Underway | Federal Lands Western Division | Federal Lands | MONTANA | FLATHEAD |  |  | 1517302610023 | The work being performed on this project will reconstruct a portion of the multphase historic Going to the Sun Road project, providing access to Glacier National Park's spectacular scenery and ultimat | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2013-09-30 | 2011-04-30 | 24098190.19
402 | Underway | Federal Lands Western Division | Federal Lands | OREGON | "LANE, DOUGLAS" |  |  | 1517410470001 | The purpose of this project is to improve safety for motorists and recreational users on a 14.4 mile section of north Umpqua Highway, located in the Umpqua National Forest in Oregon. This constructio | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2012-09-28 |  | 8304859
403 | Completed | Federal Lands Western Division | Federal Lands | OREGON | WASHINGTON |  |  | 1517413001004 | Located on the out skirts of Portland, Oregon; this project will pave the entrance and parking lot area of the Tualatin River National Wildlife Refuge. This refuge welcomes over 75,000 visitors each | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-11-30 | 2011-10-11 | 488171.03
404 | Underway | Federal Lands Western Division | Federal Lands | WASHINGTON | GRAYS HARBOR |  |  | 1517532080002 | This project, continuation of phase 1, fully reconstructs the remaining 7 miles of road providing improved access the Olympic National Forest in Washington. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-11-01 | 2010-11-05 | 4446476
405 | Completed | Federal Lands Western Division | Federal Lands | WYOMING | TETON |  |  | 1517561601104 | This project will reconstruct and pave 8 miles of Grand Teton National Park roads from Spalding Bay to Jackson Lake Junction, as well as pave Signal Mountain Marina Road providing access of boats to J | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-08-20 | 2010-08-27 | 3705109.43

## TIGER
Row | Status | Program Code | StateProgram | State | County | Transaction Date | State Project # | Project# | Project Description | Improvement Category | Proceed Date | Work Start date | Estimated Completion date | Work Complete Date | Recovery Act Obligations
1 | Obligated and Awarded | CTDG | TIGER 1 | ALABAMA |  | 2010-12-30 |  | DTFH7111G00032 | Crescent Corridor Intermodal Freight Rail Project - Alabama | Other |  |  |  |  | 52500000
2 | Underway | CTDG | TIGER 1 | ARKANSAS |  | 2010-12-22 |  | ARR3001 | Hwy. 72 south - Hwy. 72 North (Bella Vista Bypass) Construct 2 interchanges and 2 lanes of ultimate 4 lanes facility | New Construction | 2011-03-23 | 2011-03-28 | 2014-04-11 |  | 10000000
3 | Underway | CTDG | TIGER 1 | CALIFORNIA |  | 2010-12-30 |  | 6020004 | Alameda Corridor East: Colton Crossing | Other |  |  |  |  | 33800000
4 | Underway | CTDG | TIGER 1 | CALIFORNIA |  | 2010-11-05 |  | A905020 | CA-SD CTY IN SD ON RTE 905 FRM 0.1 KM E TO 1.5 KM E OF RTE 905/805 SEP AND ON RTE, CONSTRUCT NEW FREEWAY PHASE 2 | New Construction | 2011-03-17 | 2011-05-31 |  |  | 17706314
5 | Underway | CTDG | TIGER 1 | CALIFORNIA |  | 2010-11-26 |  | X073092 | CA-SD CTY IN SD ON RTE 905 FRM 0.1 KM E TO 1.5 KM E OF RTE 905/805 SEP AND ON RTE, CONSTRUCT NEW FREEWAY (Preliminary Engineering) | Other | 2011-03-17 | 2011-05-31 |  |  | 200000
6 | Underway | CTDG | TIGER 1 | CALIFORNIA |  | 2010-12-30 |  | X075036 | Doyle Drive Replacement | Pavement Improvement | 2011-04-01 | 2011-04-02 |  |  | 46000000
7 | Underway | CTDG | TIGER 1 | COLORADO |  | 2010-08-16 | '18063' | 0361098 | US 36 CORRIDOR-TRAFFIC AND REVENUE STUDY AND TIFIA RELATED WORK | Other | 2010-09-08 | 2010-09-03 |  |  | 900000
8 | Obligated and Not Awarded | CTDG | TIGER 1 | COLORADO |  | 2011-09-22 |  | 0361102 |  | Other |  |  |  |  | 3900000
9 | Underway | CTDG | TIGER 1 | ILLINOIS |  | 2010-08-04 | 'C-20-045-11' | 0020054 | Construction on CREATE Project B-2 Plan No. B2-UP-TXB-002-AT-BD/Segment 1 Bid Work | Other | 2010-10-01 | 2010-10-26 | 2011-07-30 |  | 12738818
10 | Underway | CTDG | TIGER 1 | ILLINOIS |  | 2010-06-29 | 'C-20-046-11' | 0020055 | Construction on CREATE Project B-4,B-5 Plan No. B4B5-IHB-TSX-002-T-FA/RR Force Account Work | Other | 2010-08-02 | 2010-08-02 | 2012-08-30 |  | 11696542
11 | Underway | CTDG | TIGER 1 | ILLINOIS |  | 2010-09-13 |  | 0020057 | Construction on CREATE Project B-2, Plan No. B2-UP,TSX-003-AT-FA/Segment 1 Force Account Work | Other | 2010-10-07 |  | 2011-09-30 |  | 15939611
12 | Underway | CTDG | TIGER 1 | ILLINOIS |  | 2010-12-06 |  | 0020059 | Constructin on CREATE Project B-15, Plan No. B15-IHB-TSX-001-AT-FA/Force Account Work | Other | 2011-01-26 | 2011-01-31 | 2012-05-30 |  | 11300000
13 | Underway | CTDG | TIGER 1 | ILLINOIS |  | 2010-12-14 | C-20-051-11' | 0020060 | Construction on CREATE Project B-2, Plan No. B2-UP-TSX-006-BT-FA/Segment B Force Account Work | Other | 2011-02-14 | 2011-02-14 | 2012-02-28 |  | 23028487
14 | Underway | CTDG | TIGER 1 | ILLINOIS |  | 2010-10-19 | C-88-002-11 | 6000331 | Miscellaneous Viaduct Improvements | Other | 2011-11-23 |  | 2011-12-30 |  | 5000000
15 | Underway | CTDG | TIGER 1 | ILLINOIS |  | 2010-12-17 |  | 9003709 | Construction of a grade separation structure to replace grade crossing on 71st St at CSX/IHB railroad crossing. | New Bridge Construction | 2011-06-28 | 2011-08-04 | 2012-03-30 |  | 20296542
16 | Underway | CTDG | TIGER 1 | INDIANA |  | 2010-11-26 09:18 |  | 0902003 | Indianapolis Bicycle & Pedestrian Network - Phase 6 | Other | 2011-05-04 | 2011-05-11 | 2012-11-15 |  | 7205545.07
17 | Underway | CTDG | TIGER 1 | INDIANA |  | 2010-11-10 11:16 |  | 0902004 | Indianapolis Bicycle & Pedestrian Network - Phase 7 | Other | 2011-05-13 | 2011-05-27 | 2012-05-31 |  | 4488387.08
18 | Underway | CTDG | TIGER 1 | INDIANA |  | 2010-11-10 |  | 0902007 | Indianapolis Bicycle & Pedestrian Network - Phase 4 (ST 1001, Cultural Trail, Virginia Ave-New Jersey St; & South St starting from Penns St to Prospect, Marion County) | Other | 2011-01-19 | 2011-05-04 | 2011-12-31 |  | 8806067.85
19 | Underway | CTDG | TIGER 1 | INDIANA |  | 2010-07-13 | '0902256' | 0902256 | CORRIDOR 397, US 421, REPLACE SUPERSTRUCTURE, MILTON-MADISON BRIDGE PROJECT, JEFFERSON COUNTY, IB-33023 | Bridge Replacement | 2010-10-28 | 2010-10-28 | 2013-08-31 |  | 10000000
20 | Underway | CTDG | TIGER 1 | IOWA |  | 2010-09-24 |  | DTFH6110G00011 | CITY OF DUBUQUE-Millwork District Multimodal Improvements | Other | 2011-02-24 | 2011-03-04 | 2012-12-31 |  | 5600000
21 | Underway | CTDG | TIGER 1 | KENTUCKY |  | 2010-12-09 |  | 3000902 | Appalachian Regional Short Line Rail Project - Kentucky | Other | 2010-11-10 | 2010-12-03 | 2012-04-30 |  | 12964443
22 | Underway | CTDG | TIGER 1 | KENTUCKY |  | 2010-07-15 | '05-00135.80' | 4201069 | Replace the US 421 bridge over the Ohio River between Milton, KY and Madison, IN-Grade, drain, and surface for bridge and approach | Bridge Replacement | 2010-12-26 | 2010-10-28 | 2012-11-30 |  | 10000000
23 | Underway | CTDG | TIGER 1 | MICHIGAN |  | 2010-12-22 |  | 1177012 | I-94 over the Black River, City of Port Huron, St. Clair Cou Bridge Replacement | Bridge Replacement | 2011-02-25 | 2011-03-03 | 2014-09-15 |  | 30000000
24 | Underway | CTDG | TIGER 1 | MINNESOTA |  | 2010-12-17 |  | M238001 | Saint Paul Union Depot Multi-Modal Transit and Transportation Hub | Other | 2011-03-25 | 2011-04-01 | 2012-10-01 |  | 35000000
25 | Underway | CTDG | TIGER 1 | MONTANA |  | 2010-09-02 |  | DTFH6110G00002A | Lake County MT | Other | 2010-12-10 |  | 2016-09-30 |  | 12000000
26 | Underway | CTDG | TIGER 1 | MONTANA |  | 2010-07-28 |  | DTFH6110G00009 | City of Whitefish MT | Other | 2011-09-19 | 2011-09-19 |  |  | 3499929
29 | Obligated and Awarded | CTDG | TIGER 1 | NEW JERSEY |  | 2010-12-16 |  | C00S124 | Philadelphia Area Pedestrian & Bicycle Network - Pearl Street Bike/Pedestrian Enhancement Project | Pavement Improvement |  |  | 2012-02-17 |  | 5800000
30 | Underway | CTDG | TIGER 1 | NEW MEXICO |  | 2010-09-16 |  | G5B5600 | US 491 MP 45.000 TO MP 59.000 TOHATCHI TO SHIPROCK | New Construction | 2010-12-15 | 2011-01-14 | 2012-09-03 |  | 28892830.64
31 | Underway | CTDG | TIGER 1 | NORTH CAROLINA |  | 2010-05-14 | '34156.3.ST2','34156.3.GV3' | 0853197 | I-85 from North of SR 2120(Long Ferry Rd,exit 81) Rowan County-North of NC 150 Davidson County | Pavement Improvement | 2010-05-31 | 2010-07-02 | 2013-01-26 |  | 10000000
32 | Underway | CTDG | TIGER 1 | OHIO |  | 2010-12-16 |  | DTFH7111G00025 | National Gateway Freight Rail Corridor | Other | 2010-12-22 | 2011-05-24 | 2012-12-29 |  | 98000000
33 | Underway | CTDG | TIGER 1 | OKLAHOMA |  | 2010-12-22 |  | TIGR497 | I-244 OVER ARKANSAS RIVER (WESTBOUND) (IM EARMARK)(ADD TO 02-11; LATE ADD AS PER BRIDGE) | Other | 2011-06-15 | 2011-05-13 |  |  | 49480000
34 | Underway | CTDG | TIGER 1 | PENNSYLVANIA |  | 2010-12-30 |  | U065001 | Philadelphia Area Pedestrian & Bicycle Network -Shawmont to Port Royal | Pavement Improvement | 2012-02-10 |  | 2012-06-20 |  | 1000000
35 | Underway | CTDG | TIGER 1 | PENNSYLVANIA |  | 2010-12-30 |  | U065002 | Philadelphia Area Pedestrian & Bicycle Network - Walnut Street Gateway | Pavement Improvement | 2011-10-03 | 2011-12-05 | 2012-09-06 |  | 1740000
36 | Underway | CTDG | TIGER 1 | PENNSYLVANIA |  | 2010-12-30 |  | U065003 | Philadelphia Area Pedestrian & Bicycle Network -CSX Pedestrian Bridge | Pavement Improvement | 2011-06-20 | 2011-06-27 | 2012-11-25 |  | 4400000
37 | Obligated and Awarded | CTDG | TIGER 1 | PENNSYLVANIA |  | 2010-12-30 |  | U065004 | Philadelphia Area Pedestrian & Bicycle Network -Boardwalk from Locust to South Streets | Pavement Improvement |  |  | 2014-08-09 |  | 6200000
38 | Underway | CTDG | TIGER 1 | PENNSYLVANIA |  | 2010-12-30 |  | U065005 | Philadelphia Area Pedestrian & Bicycle Network -Bartram's Garden | Pavement Improvement | 2012-02-21 |  | 2012-06-29 |  | 1000000
39 | Underway | CTDG | TIGER 1 | PENNSYLVANIA |  | 2010-12-30 |  | U065006 | Philadelphia Area Pedestrian & Bicycle Network - 58th Street Connector Greenway | Pavement Improvement | 2011-11-10 |  | 2012-11-18 |  | 1100000
40 | Obligated and Awarded | CTDG | TIGER 1 | PENNSYLVANIA |  | 2010-12-30 |  | U065007 | Philadelphia Area Pedestrian & Bicycle Network -Delaware Ave Trail, Allegheny Ave to Betsy Ross Bridge | Pavement Improvement |  |  | 2012-12-15 |  | 1760000
41 | Underway | CTDG | TIGER 1 | SOUTH CAROLINA |  | 2010-09-24 |  | DTFH6110G00013 | CITY OF CHARLESTON- U.S. 17 Septima Clark Parkway | Other | 2011-05-20 | 2011-06-13 | 2012-11-20 |  | 10000000
42 | Obligated and Not Awarded | TIGER TIFIA CHALLANGE | TIGER 1 | SOUTH CAROLINA |  | 2010-12-20 |  | SPMC033 | US 501,US 301, S-63 S of proposed I-73 to N of proposed I-73. Widening of approx. 1.0 mile of US 301 and approx. 1.25 miles of | Pavement Improvement |  |  |  |  | 10000000
43 | Underway | CTDG | TIGER 1 | SOUTH DAKOTA |  | 2010-06-17 | '02KH' | 0018170 | US18-FM Oglala to Pine Ridge; Gradeing, Structure Replacement & Interim Surfacing; Roadway Lighting, Sidewalk, Curb & Gutter..... | Other | 2010-05-14 | 2010-07-19 | 2012-06-01 |  | 10000000
44 | Underway | CTDG | TIGER 1 | TENNESSEE |  | 2010-12-29 |  | 0RJC001 | Appalachian Regional Short Line Rail Project - Tennessee | Pavement Improvement | 2011-09-02 |  | 2012-12-31 |  | 2820458
45 | Underway | CTDG | TIGER 1 | TENNESSEE |  | 2010-12-21 |  | 0NFC001 | Crescent Corridor Intermodal Freight Rail Project - Tennessee | Other | 2011-06-21 | 2011-06-23 | 2012-09-30 |  | 52500000
46 | Obligated and Not Awarded | CTDG | TIGER 1 | VERMONT |  | 2010-09-28 |  | DTFH6110G00010 | Burilington-Waterfront North Project | Other |  |  |  |  | 3150000
47 | Underway | CTDG | TIGER 1 | WASHINGTON |  | 2010-05-27 | '00CNA','00PC','600001A' | 0395091 | ARRA - TIGER - SR395 / NORTH SPOKANE CORRIDOR, FREYA TO FARWELL - SB. SR395-24.86 TO 28.49 MILES SOUTHEAST OF JUNCTION SR292. | Pavement Improvement | 2010-08-17 | 2010-07-28 | 2013-10-30 | 2012-10-16 | 35000000
48 | Underway | CTDG | TIGER 1 | WASHINGTON |  | 2010-06-10 | ' TIGERHLPCNA','SEA-90' | 9999580 | TIGER - Seattle, S. Lake Union Mercer Corridor FROM:Fairview Ave N TO:Dexter Ave N LEN: 2.000MI | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2013-04-13 |  | 30000000
49 | Underway | CTDG | TIGER 1 | WEST VIRGINIA |  | 2010-11-15 |  | 2010060 | Appalachian Regional Short Line Rail Project - West Virginia | Other | 2010-11-12 | 2010-03-28 | 2012-03-28 |  | 1766127
50 | Underway | CTDG | TIGER 1 | WISCONSIN |  | 2010-12-29 |  | 2011185 | LOC STR,0.000 MILES,C OF MILWAUKEE,WISCONSIN&JUNEAU AVE,B40-0488REHAB/P40-0880,B40-0757REPL,DESCONST/BR REHAB & BR REPLACEMENT,LET | Bridge Replacement | 2010-12-29 | 2010-12-29 | 2012-12-01 |  | 21500000
51 | Underway | CTDG | TIGER 1 | WYOMING |  | 2010-06-10 | 'HPP0416' | HPP0416 | RECONSTRUCTION OF 2.92KM OF BEARTOOTH HWY (US212) BEARTOOTH LAKE OUTLET BRIDGE TO BEARTOOTH LAKE CAMPGROUND | Other | 2010-07-08 | 2010-07-09 | 2011-12-31 |  | 6000000
52 | Underway | TIGER TIFIA CHALLANGE | TIGER 1 | COLORADO |  |  |  | TBD-Loan | US-36 Managed Lanes/Bus Rapid Transit | Other | 2011-03-29 | 2011-03-29 | 2013-09-30 |  | 4915830
53 | Underway | TIGER TIFIA | TIGER 1 | TEXAS |  |  |  | TBD-Loan | Texas State Highway 161 | Other | 2010-04-07 | 2010-04-07 | 2013-09-11 |  | 9098144.16