## Introduction & TOC
Weekly List of FHWA Recovery Act Projects
As of March 16,2012
Introduction:
This report summarizes all projects that are using or will receive American Recovery and Reinvestment Act of 2009 (Recovery Act) funds. The recipients include Federal Grants to States, including Ferry Boat Discretionary grants and On-the-Job Training/Supportive Services (OJT/SS) grants ; Federal Lands Divisions; Federal land management agencies including the Bureau of Land Management, the USDA Forest Service, and the National Park Service; Indian Reservation Roads (IRR) Program projects; and TIGER grants. The report is produced weekly on Fridays and is organized by the recipients listed above as well as summary tabs by State/Division/Recipient, improvement type, and program. The project lists are split by Obligated and Awarded or Not Awarded, Projects Underway, and Completed Projects (see below for definitions). If you have any questions, please contact Paolo Angulo at paolo.angulo.ctr@dot.gov or 202-366-8030.
Project Summaries: | Definition
Summary by State: | Summary by State of the Highway Infrastructure Investment Grants plus Federal Lands and TIGER projects.
Summary by Type: | Summary by Improvement Type of the Highway Infrastructure Investment Grants (HIIG)plus Federal Lands and TIGER projects.
Summary by Program: | Summary by Program of all Highway Infrastructure Investment Grants plus Federal Lands and TIGER projects.
Project Lists:
Hwy Infra Invest Grant: | List of all State and Territory administered Highway Infrastructure Investment Grant (HIIG) projects. This list includes all projects including Projects Obligated and Awarded/Not Awarded, Projects Underway, and Completed Projects.
Federal Lands: | List of all Federal Land administered projects including ones managed by Federal Land Divisions, National Park Services, Indian Reservation Roads, etc.
TIGER 1: | List of all TIGER Grant projects.

## Summary by State
| Obligated and Not Awarded |  | Obligated and Awarded |  | Underway Projects |  | Completed Projects |  | All Projects
State | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations
ALABAMA |  |  |  |  | 43 | 248922272.09 | 285 | 264135875.16 | 328 | 513058147.25
ALASKA |  |  |  |  | 4 | 21608665 | 24 | 150582901.79 | 28 | 172191566.79
AMERICAN SAMOA | [6 empty] | 1 | 4500000 | 1 | 4500000
ARIZONA |  |  |  |  | 34 | 131189222.88 | 175 | 387849077.95 | 209 | 519038300.83
ARKANSAS |  |  |  |  | 16 | 191357761 | 116 | 160536707 | 132 | 351894468
CALIFORNIA | 1 | 73217 |  |  | 151 | 1551436661.19 | 833 | 979010269.33 | 985 | 2530520147.52
COLORADO |  |  |  |  | 34 | 156025152 | 80 | 229539162 | 114 | 385564314
CONNECTICUT |  |  |  |  | 16 | 164013133.9 | 135 | 133984135.26 | 151 | 297997269.16
DELAWARE |  |  |  |  | 12 | 67523286.28 | 32 | 54305363.72 | 44 | 121828650
DISTRICT OF COLUMBIA |  |  |  |  | 12 | 89697450.02 | 6 | 33810391.82 | 18 | 123507841.84
FLORIDA |  |  |  |  | 194 | 1045133735 | 486 | 293966160 | 680 | 1339099895
GEORGIA |  |  |  |  | 105 | 517702903.17 | 293 | 384024277.3 | 398 | 901727180.47
GUAM |  |  |  |  | 7 | 19560000 |  |  | 7 | 19560000
HAWAII | 1 | 22724978.84 |  |  | 11 | 79273907.1 | 14 | 22812801.84 | 26 | 124811687.78
IDAHO |  |  |  |  | 19 | 60536254.14 | 66 | 118310949.43 | 85 | 178847203.57
ILLINOIS |  |  |  |  | 83 | 219889270.77 | 737 | 715436274.05 | 820 | 935325544.82
INDIANA |  |  |  |  | 28 | 65151616.03 | 1069 | 589597092.7 | 1097 | 654748708.73
IOWA |  |  |  |  | 32 | 26275190.43 | 203 | 330701824.28 | 235 | 356977014.71
KANSAS |  |  |  |  | 55 | 303878967.09 | 97 | 44104390.09 | 152 | 347983357.18
KENTUCKY |  |  |  |  | 33 | 280457414.19 | 77 | 139718294.2 | 110 | 420175708.39
LOUISIANA |  |  |  |  | 65 | 344331355.17 | 56 | 88657317.9 | 121 | 432988673.07
MAINE |  |  |  |  | 3 | 5572821.06 | 73 | 131772175.54 | 76 | 137344996.6
MARYLAND | 2 | 764715 |  |  | 144 | 371212899 | 26 | 43787163 | 172 | 415764777
MASSACHUSETTS | 1 | 25000 |  |  | 58 | 289737133.35 | 35 | 84289856.36 | 94 | 374051989.71
MICHIGAN |  |  | 1 | 938000 | 178 | 510349022.98 | 574 | 343535247.11 | 753 | 854822270.09
MINNESOTA |  |  |  |  | 18 | 104082718.78 | 193 | 402026838 | 211 | 506109556.78
MISSISSIPPI |  |  |  |  | 50 | 131964829 | 123 | 219613849 | 173 | 351578678
MISSOURI |  |  |  |  | 27 | 237476011.51 | 310 | 401195857.96 | 337 | 638671869.47
MONTANA |  |  |  |  | 12 | 60135050.02 | 74 | 152700507.98 | 86 | 212835558
NEBRASKA |  |  |  |  | 16 | 39201458.61 | 113 | 188964342.13 | 129 | 228165800.74
NEVADA |  |  |  |  | 19 | 95265850 | 53 | 105570606.97 | 72 | 200836456.97
NEW HAMPSHIRE |  |  |  |  | 1 | 14717629.33 | 33 | 114722926.67 | 34 | 129440556
NEW JERSEY |  |  |  |  | 55 | 296044661 | 118 | 346720246.49 | 173 | 642764907.49
NEW MEXICO |  |  |  |  | 25 | 70394375.32 | 78 | 180110377.17 | 103 | 250504752.49
NEW YORK |  |  |  |  | 80 | 288852527.47 | 363 | 656363160.53 | 443 | 945215688
NORTH CAROLINA |  |  |  |  | 159 | 373278851 | 243 | 353654989 | 402 | 726933840
NORTH DAKOTA |  |  |  |  | 53 | 55037249.17 | 115 | 109273487.38 | 168 | 164310736.55
NORTHERN MARIANA |  |  | 1 | 1042300 |  |  | 1 | 3457700 | 2 | 4500000
OHIO | 1 | 318416 |  |  | 61 | 450997820.12 | 363 | 465885550.73 | 425 | 917201786.85
OKLAHOMA |  |  |  |  | 54 | 226523498 | 220 | 238227907 | 274 | 464751405
OREGON |  |  |  |  | 67 | 60677478.12 | 266 | 209735663.86 | 333 | 270413141.98
PENNSYLVANIA |  |  |  |  | 46 | 347497983.6 | 276 | 681149974.35 | 322 | 1028647957.95
PUERTO RICO |  |  |  |  | 18 | 93233605.89 | 5 | 11755227.83 | 23 | 104988833.72
RHODE ISLAND |  |  |  |  | 7 | 13169787.16 | 63 | 124121785.49 | 70 | 137291572.65
SOUTH CAROLINA |  |  |  |  | 38 | 240975367.26 | 149 | 222543891.74 | 187 | 463519259
SOUTH DAKOTA |  |  |  |  | 12 | 74316461.3 | 40 | 112108132.96 | 52 | 186424594.26
TENNESSEE |  |  |  |  | 73 | 313336152.95 | 250 | 258640080.66 | 323 | 571976233.61
TEXAS |  |  |  |  | 132 | 1483137064.56 | 395 | 757291344.44 | 527 | 2240428409
UTAH |  |  |  |  | 27 | 90985597.83 | 101 | 122656083.72 | 128 | 213641681.55
VERMONT |  |  |  |  | 3 | 17523559.99 | 70 | 108042870.97 | 73 | 125566430.96
VIRGIN ISLANDS | 2 | 3819130.75 |  |  | 4 | 11643714.25 |  |  | 6 | 15462845
VIRGINIA | 3 | 33630621 |  |  | 57 | 432946264 | 81 | 167533479 | 141 | 634110364
WASHINGTON |  |  |  |  | 6 | 133418152.99 | 219 | 357044885.26 | 225 | 490463038.25
WEST VIRGINIA |  |  |  |  | 13 | 38288171 | 142 | 170442661 | 155 | 208730832
WISCONSIN |  |  |  |  | 2 | 2727881 | 420 | 525656927.78 | 422 | 528384808.78
WYOMING |  |  |  |  | 6 | 5852457.98 | 63 | 151763600.02 | 69 | 157616058
Sub Total (HIIG) | 11 | 61356078.59 | 2 | 1980300 | 2478 | 12564538323.05 | 10433 | 13647942663.92 | 12924 | 26275817365.56
FEDERAL LANDS |  |  | 97 | 47625482.48 | 109 | 182192711.69 | 199 | 237528461.04 | 405 | 467346655.21
TIGER 1 | 3 | 17050000 | 4 | 66260000 | 44 | 727384075.8 |  | 0 | 51 | 810694075.8
Grand Total | 14 | 78406078.59 | 103 | 115865782.48 | 2631 | 13474115110.54 | 10632 | 13885471124.96 | 13380 | 27553858096.57

## Summary By Program
| Obligated and Not Awarded |  | Obligated and Awarded |  | Underway Projects |  | Completed Projects |  | All Projects
Program | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations
Highway Infrastructure Investment Grant | 7 | 57724445.59 | 2 | 1980300 | 2422 | 12518987147.8 | 10407 | 13623804847.87 | 12838 | 26202496741.26
Federal Lands |  |  | 97 | 47625482.48 | 109 | 182192711.69 | 199 | 237528461.04 | 405 | 467346655.21
Ferryboat | 1 | 3000000 |  |  | 23 | 32302800.25 | 14 | 20162480.35 | 38 | 55465280.6
OJT/SS | 3 | 631633 |  |  | 33 | 13248375 | 12 | 3975335.7 | 48 | 17855343.7
TIGER 1 | 3 | 17050000 | 4 | 66260000 | 44 | 727384075.8 |  |  | 51 | 810694075.8
Grand Total | 14 | 78406078.59 | 103 | 115865782.48 | 2631 | 13474115110.54 | 10632 | 13885471124.96 | 13380 | 27553858096.57

## Summary by Type
| Obligated and Not Awarded |  | Obligated and Awarded |  | Underway Projects |  | Completed Projects |  | All Projects
Improvement Type | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations
Bridge Improvement |  |  | 2 | 1805555.48 | 82 | 482890876.87 | 497 | 713887761.71 | 581 | 1198584194.06
Bridge Replacement |  |  |  |  | 102 | 787072891.23 | 571 | 671247497.37 | 673 | 1458320388.6
New Bridge Construction |  |  |  |  | 26 | 448077675.03 | 38 | 147707719.65 | 64 | 595785394.68
New Construction | 1 | 819130.75 | 10 | 5058566 | 98 | 1529071968.12 | 106 | 423942063.02 | 215 | 1958891727.89
Pavement Improvement | 1 | 10000000 | 30 | 37519720 | 1003 | 4124907580.24 | 6761 | 9513952119.72 | 7795 | 13686379419.96
Pavement Widening | 1 | 22724978.84 |  |  | 214 | 3688407017.47 | 211 | 1019362920.92 | 426 | 4730494917.23
Safety/Traffic Management | 3 | 19996511 | 9 | 672436 | 277 | 843056807.21 | 743 | 521476683.33 | 1032 | 1385202437.54
Transportation Enhancements |  |  | 1 | 938000 | 498 | 525387974.36 | 1148 | 581989157.15 | 1647 | 1108315131.51
Other | 8 | 24865458 | 51 | 69871505 | 331 | 1045242320.01 | 557 | 291905202.09 | 947 | 1431884485.1
Grand Total | 14 | 78406078.59 | 103 | 115865782.48 | 2631 | 13474115110.54 | 10632 | 13885471124.96 | 13380 | 27553858096.57

## Hwy Infra Invest Grant
Row | Status | Program Code | Program | State | County | Urban Area | Cong. District | Project # | Project Description | Improvement Type | Proceed Date | Work Start date | Estimated Completion date | Work Complete Date | Recovery Act Obligations | Length
1 | Underway | C240,C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | 0001537 | This project constructs the mainline of US-231/431 with overpasses at Max Luther and Sparkman Drive. The mainline will be four and six lanes with a concrete median divider for approximately 1 mile. | New Construction | 2009-08-10 | 2009-08-25 | 2012-09-30 |  | 23267295.47 | 1.030
2 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 0001538 | This project will upgrade the bridge rails to current safety standards for bridges with inventory number 006900 and 006901 over Big Creek on US Highway 231 in Houston County | Pavement Improvement | 2009-05-13 | 2009-05-26 | 2010-04-01 | 2009-12-07 | 195937.75 | 0.010
3 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 0001539 | This project involve the repaving of approximately 6 miles of US Highway 231 from the Florida State line to just north of County Road 93 (Smithville Road) south of Dothan | Pavement Improvement | 2009-05-13 | 2009-05-29 | 2010-04-01 | 2009-12-07 | 2780419.27 | 6.082
4 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HENRY |  | 02 | 0001543 | This project involves the repaving of about 3 miles of US Highway 431 from the the south city limit of Headland to just north of State Highway 173 | Pavement Improvement | 2009-10-14 | 2009-11-03 | 2010-07-01 | 2010-07-06 | 1786185.94 | 3.060
5 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 0001546 | This project involves the repaving of 10 miles of US Highway 431 from Old Seale Highway to just south of US Highway 280 in Russell County | Pavement Improvement | 2009-09-25 | 2009-11-06 | 2010-04-01 | 2010-10-15 | 4496092.12 | 10.330
6 | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH | GADSDEN | 04 | 0001547 | This project involves the repaving US Highway 31 from the north end of the Meighan Boulevard bridge to Terminal Street in the city of Gadsden | Pavement Improvement | 2010-09-21 |  | 2011-03-03 |  | 1184129 | 0.920
7 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MARSHALL |  | 04 | 0001548 | This project involves the repaving and widening of approximately 7 miles of US Highway 431 from the north end of the Tennessee River Bridge to County Road 5 (Cathedral Caverns Highway) just north of G | Pavement Improvement | 2009-09-10 | 2009-11-24 | 2010-02-14 | 2010-08-30 | 3772979.82 | 6.660
8 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHAMBERS |  | 03 | 0001553 | This project will improve the curves along SR-1(US-431) from one mile south of SR-147 to south of Sturkie and provide new traffic stripe. | Safety/Traffic Management | 2009-10-22 | 2009-12-11 | 2010-02-28 | 2010-06-10 | 228025.03 | 2.000
9 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLEBURNE |  | 03 | 0001554 | This project involves safety improvements at various curves along US-431 | Safety/Traffic Management | 2010-01-28 | 2010-05-07 | 2010-06-30 | 2011-04-11 | 673974.66 | 1.960
10 | Completed | C240,C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 0001555 | This project involves the repaving of US Highway 43 (State Highway 1) from US Highway 80 (State Highway 80) to the north city lilmits of Phenix City in Russell County | Pavement Improvement | 2010-05-27 | 2010-06-28 | 2010-09-30 | 2011-07-07 | 2281860.54 | 1.790
11 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 0002534 | This project involves the repaving and 2 foot safety widening for about 4 miles of US Highway 72 from west of Cane Creek to east of Dry in Colbert County | Pavement Improvement | 2009-05-15 | 2009-07-02 | 2010-04-10 | 2009-08-14 | 1664166.5 | 3.673
12 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LIMESTONE |  | 05 | 0003544 | This project involves the repaving and widening of about 3 miles of US Highway 31 from just south of Cactus Street to Interstate 65 near Athens | Pavement Improvement | 2009-05-04 | 2009-05-19 | 2009-07-31 | 2009-08-19 | 1392476.71 | 2.655
13 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | 0003546 | This project involves the repaving of aproximately 7 miles of the Gulf Shores Parkway from Stapleton to the Bay Minette south city limits | Pavement Improvement | 2009-05-13 | 2009-06-01 | 2009-10-31 | 2009-11-16 | 3005543.44 | 7.380
14 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BUTLER |  | 02 | 0003550 | This project involves the repaving and 2 foot widening of approximately 5 miles of US Highway 31 from the Conecuh County line to a bout a mile north of Persimmon Creek of Butler County | Pavement Improvement | 2009-07-23 | 2009-08-24 | 2009-12-01 | 2010-03-03 | 2005989.47 | 5.215
15 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | 0003551 | This project involves the repaving and 2 foot widening of approximately 10 miles of US Highway 31 near Fort Deposit from the Junction of State Highway 185 to the Montgomery County line | Pavement Improvement | 2009-08-13 | 2009-10-08 | 2010-03-31 | 2011-03-11 | 3938023.53 | 9.637
16 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CONECUH |  | 02 | 0003552 | This project involves the repaving of about 12 miles of US Highway 31 from US Highway 84 to the Butler County Line in Conecuh County | Pavement Improvement | 2009-08-13 | 2009-09-15 | 2009-12-31 | 2010-08-19 | 2943540.58 | 12.127
17 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | 01 | 0005526 | This project involves the repaving of approximately 5 miles of State Highway 5 in Clarke County from US Highway 43 to the Wilcox County Line north of Thomasville | Pavement Improvement | 2009-05-01 | 2009-05-05 | 2009-06-26 | 2009-07-09 | 1385805.21 | 4.795
18 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | AUTAUGA | MONTGOMERY | 02 | 0006538 | This project involves the repaving and 2 foot widening of 12 miles of US Highway 82 from just west of County Road 40 to State Highway 206 in Pratville | Pavement Improvement | 2009-08-14 | 2009-08-31 | 2010-01-30 | 2010-10-27 | 3905909.2 | 12.000
19 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 0007519 | This project involves the repaving of US Highway 11 from the Greene County Line to just south of the Warrior River Bridge in the Fosters. The project also include the repaving of Holly Springs Road f | Pavement Improvement | 2009-09-16 | 2009-10-13 | 2010-03-19 | 2010-10-18 | 3836899.73 | 9.826
20 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | GREENE |  | 07 | 0007520 | This project invovles the repaving and widening of 10 miles US Highway 11 from north of Greentrack Road to Tuscaloosa County Line near Knoxville | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2010-02-10 | 2010-10-27 | 3370826.99 | 9.634
21 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MACON |  | 03 | 0008554 | This project involves the repaving and widening of 9 miles of US Highway 80 in Macon County from near the junction of State Highway 186 to the Lee County line | Pavement Improvement | 2009-08-14 | 2009-09-18 | 2009-12-01 | 2010-06-30 | 2438634.49 | 9.030
22 | Underway | C200,C240 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY |  | 03 | 0009509 | This project will add two additional lanes to the existing two lanes to provide a four-lane facility on US Highway 331 from approximately one-half mile south of State Highway 94 to the end of the pres | Pavement Widening | 2009-11-18 | 2009-12-07 | 2012-01-01 |  | 20160044.36 | 4.210
23 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WILCOX |  | 07 | 0010520 | This project involves the repaving of 2 miles of State Highway 10 (Camden Bypass) from State Highway 28 to State Highway 28 in Camden. Wilcox County | Pavement Improvement | 2009-08-04 | 2009-08-08 | 2009-09-30 | 2009-12-15 | 520425.7 | 1.964
24 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CRENSHAW |  | 02 | 0010521 | This project involves the repaving and widening for 10 miles of State Highway 10 from the Butler County line to US Highway 331 in Crenshaw County | Pavement Improvement | 2009-08-12 | 2009-09-04 | 2010-06-01 | 2010-07-30 | 3058930.46 | 9.872
25 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | 0012536 | This project involves repaving approximately 7 miles of US Highway 84 from about 2 miles north of County Road 6 (Bladon Road) to east end of Tombigbee River Bridge in Choctaw County | Pavement Improvement | 2010-03-02 | 2010-04-22 | 2010-06-30 | 2010-08-27 | 1385021.44 | 6.626
26 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | 07 | 0012537 | This project involves the repaving and widening of 5 miles of US Highway 84 from the east end of the Tombigbee River Bridge to west of County Road 3 in Clarke County | Pavement Improvement | 2010-02-09 | 2010-04-22 | 2010-06-30 | 2010-09-04 | 2128816 | 5.344
27 | Underway | C240 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE |  | 05 | 0013503 | This project will add two additional lanes to the existing two lanes to ultimately provide a four-lane facility from the end of the present four-lane at Killen to State Highway 64. This project will | Pavement Improvement | 2009-12-02 | 2009-12-15 | 2011-08-31 |  | 10355008.35 | 5.066
28 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BULLOCK |  | 02 | 0015515 | This project involves the repaving of a mile of US Highway 29 from State Highway 197 to US Highway 82 in Union Springs | Pavement Improvement | 2009-09-10 | 2009-09-28 | 2010-01-01 | 2010-03-10 | 380050.43 | 1.010
29 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | 0015516 | This project involves the repaving of over 11 miles of US Highway 29 from 1 mile south of Maye Creek to just south of Smith Creek in Escambia County | Pavement Improvement | 2010-01-26 | 2010-03-25 | 2010-04-30 | 2010-08-13 | 1914967.31 | 11.420
30 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | 0015517 | This project involves the repaving of about 2 miles of US Highway 29 from the Macon County Line to Sand Hill Road in Lee County | Pavement Improvement | 2009-07-29 | 2009-08-21 | 2009-10-31 | 2010-02-24 | 938608.39 | 1.860
31 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | 0017525 | This project involves the repaving and widening of approximately 4 miles of State Highway 17 in Chocktaw County from about 1 mile south of County Road 18 to just north of County Road 28 east of Needha | Pavement Improvement | 2009-07-29 | 2009-08-13 | 2009-10-30 | 2010-03-31 | 1098139.91 | 3.571
32 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | 0017526 | This project involves the repaving of 5 miles of State Highway 17 (Mulberry Avenue) from just north of County Road 28 to north of the Butler city limits in Choctaw County | Pavement Improvement | 2009-07-29 | 2009-08-13 | 2009-10-30 | 2010-03-31 | 1105494.64 | 5.541
33 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LAMAR |  | 04 | 0017528 | This project involves the repaving of approximately 8 miles of State Highway 17 from about a mile north of County Road 29 to County Road 30 in Sulligent | Pavement Improvement | 2009-09-11 | 2009-11-13 | 2010-08-08 | 2010-07-20 | 5956216.29 | 8.300
34 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MARION |  | 04 | 0017529 | This project involves the repaving of approximately 7 miles of State Highway 17 from the Lamar County line to State Highway 4 south of Hamilton in Marion County | Pavement Improvement | 2009-05-04 | 2009-07-06 | 2010-04-01 | 2009-08-07 | 1735447.28 | 7.191
35 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | SUMTER |  | 07 | 0017530 | This project involves the repaving of 6 miles of State Highway 17 from State Highway 28 to County Road 24 in Sumter County | Pavement Improvement | 2009-09-14 | 2010-03-30 | 2010-07-01 | 2011-04-07 | 2469090.61 | 5.970
36 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | WASHINGTON |  | 01 | 0017531 | This project involves the repaving of 9 miles of State Highway 17 from about 2 miles south of County Road 20 To State Highway 56 in Chatom | Pavement Improvement | 2009-09-28 | 2010-03-22 | 2009-12-18 | 2010-06-30 | 3191452.24 | 9.042
37 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | PICKENS |  | Multiple | 0017532 | This project involves the repaving of 2.5 miles of State Highway 17 from the Carrollton south city limits to just north of the north city limits in Pickens County | Pavement Improvement | 2009-09-21 | 2009-10-13 | 2010-04-06 | 2011-02-18 | 2045405.03 | 2.400
38 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE |  | 05 | 0020510 | This project involves the repaving of approximately 8 miles of State Highway 20 from the Tennessee State line to south of County Road 22 at the Natchez Trace Parkway in Lauderdale County | Pavement Improvement | 2009-09-23 | 2009-10-09 | 2010-07-01 | 2010-05-26 | 3180129.04 | 7.840
39 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | 0021522 | This project involves the repaving of approximately 6 miles of State Highway 21 in Monroe County from the north end of the Litte River Bridge at the Escambia County line to County Road 8 north of Uria | Pavement Improvement | 2009-08-17 | 2009-09-14 | 2009-10-31 | 2010-06-02 | 2092374.22 | 6.245
40 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | 0021523 | This project involves the repaving of approximately 6 miles of State Highway 21 from north of County Road 8 to south of County Road 10 in Monroe County | Pavement Improvement | 2009-08-17 | 2009-09-14 | 2009-10-31 | 2010-06-02 | 2109032.19 | 6.425
41 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | 0021527 | This project involves the repaving of South Main Street in the town of Atmore from the Florida State line to about 1 mile north | Pavement Improvement | 2009-08-18 | 2009-09-08 | 2009-11-30 | 2009-11-18 | 300690.54 | 0.968
42 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN |  | 03 | 0021528 | This project involves the repaving of 5 miles of Jacksonville State University Highway from Maxwellborn Road to near Foothills Drive in the town of Piedmont | Pavement Improvement | 2009-09-15 | 2010-01-04 | 2010-07-01 | 2010-10-12 | 1586569.53 | 4.760
43 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALLAS |  | 07 | 0022509 | This project involves the repaving and 2 foot widening of approximately 19 miles of State Highway 22 from State Highway 5 to State Highway 219 in Dallas County southwest of Selma | Pavement Improvement | 2009-08-04 | 2009-09-14 | 2010-01-15 | 2010-09-19 | 3936666.24 | 19.181
44 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | RANDOLPH |  | 03 | 0022510 | This project will improve the curves along State Highway 22 from 1 mile north of Randolph County Road 17 to the State Line | Pavement Improvement | 2009-10-15 | 2009-11-06 | 2009-12-31 | 2010-05-06 | 492885.04 | 1.000
45 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LAWRENCE |  | 05 | 0024501 | This project involves the repaving of 5 miles of State Highway 24 from County Road 460 to near County Road 320 in Lawrence County | Pavement Improvement | 2009-10-14 | 2009-11-05 | 2010-07-01 | 2010-05-17 | 3083491.02 | 5.030
46 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HALE |  | 07 | 0025520 | This project involves repaving and widening fro about 5 miles of State Highway 25 in Hale County from County Road 29 to the Bibb County line | Pavement Improvement | 2009-08-19 | 2009-09-15 | 2010-03-03 | 2010-08-19 | 1747864.63 | 4.534
47 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 0027504 | This project involves the repaving and widening of approximately 10 miles of State Highway 27 in Dale County from east of County Road 59 to the Henry County line | Pavement Improvement | 2010-01-20 | 2010-02-11 | 2010-07-19 | 2010-07-19 | 2630054.44 | 9.591
48 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | COFFEE |  | 02 | 0027505 | This project involves the repaving and widening of approximately 5 miles of State Highway 27 northeast of Enterprise from Indego Place to the Dale County line | Pavement Improvement | 2009-08-04 | 2009-09-30 | 2010-06-01 | 2010-08-16 | 1811003.9 | 5.217
49 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WINSTON |  | 04 | 0033502 | This project involves the repaving of 5 miles of State Highway 24 from County Road 460 to near County Road 320 in Lawrence County | Pavement Improvement | 2009-08-18 | 2009-08-31 | 2010-06-01 | 2010-02-03 | 1552575.76 | 4.945
50 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | JACKSON |  | 05 | 0035509 | This project involves the repaving and 2 foot safety widening for approximately 13 miles of State Highway 35 from State Highway 79 westerly through Woodville to US Highway 72 in Jackson County | Pavement Improvement | 2009-05-04 | 2009-06-01 | 2009-08-01 | 2010-01-13 | 1477602.35 | 13.290
51 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | Multiple | 0036504 | This project involves the repaving and widening of over 2 miles of State Highway 36 (Main Street) from the intersection with US Highway 31 in Hartselle to Interstate 65 | Pavement Improvement | 2009-09-24 | 2009-10-19 | 2009-11-30 | 2010-04-07 | 1100964.86 | 2.414
52 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | 0038522 | This project involves the repaving of over 6 miles of US-280 from Hugh Daniel Drive to Old US 280 Highway | Pavement Improvement | 2009-05-14 | 2009-06-05 | 2009-11-15 | 2011-08-26 | 5795544.45 | 6.250
53 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CONECUH |  | 02 | 0041504 | This project involves the repaving of 10 miles of State Highway 41 from Interstate 65 to US Highway 84 in Conecuh County | Pavement Improvement | 2010-07-22 | 2010-08-18 | 2010-11-01 | 2010-12-16 | 3034720.67 | 10.596
54 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | 0041505 | This project involves the repaving of approximately 10 miles of State Highway 41 from south of County 39 to just south of Interstate 65 in Escambia County | Pavement Improvement | 2010-03-02 | 2010-03-23 | 2010-05-31 | 2010-09-29 | 3392321.49 | 10.790
55 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN | PENSACOLA | 01 | 0042518 | This project involves the replacement of traffic signals at the intersection of US Highway 98 and 6th Street in the town of Lillian in Baldwin County | Safety/Traffic Management | 2010-06-24 |  | 2010-12-11 | 2011-04-29 | 66119 | 0.010
56 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLAY |  | 03 | 0049502 | This project involves the repaving of about 8 miles of State Highway 49 fromt the Tallapoosa County line to State Highway 77 near the town of Ashland | Pavement Improvement | 2009-07-21 | 2009-08-09 | 2009-10-13 | 2010-08-03 | 2530360.67 | 7.334
57 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | TALLAPOOSA |  | 03 | 0049503 | This project involves the resurfacing and traffic stripe at various sites on SR-49. | Safety/Traffic Management | 2010-01-07 | 2010-02-04 | 2010-03-24 | 2010-07-27 | 732845.67 | 20.000
58 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | 0051503 | This project involves the repaving and and widening of approximately 10 miles of State Highway 51 in Barbour County from just South of State Highway 239 to the Bullock County line | Pavement Improvement | 2009-08-07 | 2009-09-23 | 2010-06-01 | 2010-07-23 | 2784528.24 | 10.325
59 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 0051504 | This project involves the repaving and widening of 3 miles of State Highway 51 in Dale County from the Coffee County line to US Highway 231 | Pavement Improvement | 2010-01-20 | 2010-02-11 | 2010-07-19 | 2010-07-19 | 899945.52 | 3.107
60 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BULLOCK |  | 02 | 0051505 | This project involves the repaving and 2 foot widening of 13 miles of State Highway 51 in Bullock County from US Highway 82 to the Russell County line | Pavement Improvement | 2010-01-27 | 2010-03-18 | 2010-08-01 | 2010-11-19 | 4911093.75 | 13.000
61 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 0053537 | This project will upgrade the bridge rails to current safety standards for bridges with inventory numbers 005532 and 005533 over Little Claybank Creek and bridges with inventory numbers 005571 and 009 | Bridge Improvement | 2009-05-04 | 2009-06-05 | 2010-04-01 | 2009-10-02 | 149626.25 | 6.390
62 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 0053538 | This project involves the repaving of about 6.5 miles of US Higway 231 from just south of State Highway 27 north to County Road 2 in Ozark | Pavement Improvement | 2009-05-04 | 2009-06-30 | 2010-04-01 | 2009-10-02 | 2723856.06 | 6.390
63 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | BLOUNT |  | 04 | 0053541 | This project involves the repaving of approximately 6 miles of US Highway 231 from US Highway 278 to Cullman County | Pavement Improvement | 2010-04-20 | 2010-04-27 | 2010-06-30 | 2010-10-27 | 1223129.83 | 6.214
64 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BLOUNT |  | 04 | 0053542 | This project involves the repaving of about 4 miles of US Highway 231 from State Highway 79 to County Road 26 in Blount County | Pavement Improvement | 2010-04-20 | 2010-04-27 | 2010-06-30 | 2010-10-27 | 1018632.19 | 3.706
65 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | ST CLAIR |  | 06 | 0053543 | This project involves the repaving of 7.5 miles of US Highway 231 from just north of Interstate 20 to a couple miles north of Wattsville in Ashville. | Pavement Improvement | 2009-07-16 | 2009-07-20 | 2009-09-17 | 2010-05-18 | 1506315.92 | 7.510
66 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | COVINGTON |  | 02 | 0055504 | This project involves the repaving of 7 miles of State Highway 55 from US Highway 84 to the North city limits of Red Level | Pavement Improvement | 2009-10-08 | 2009-10-26 | 2010-08-04 | 2010-08-04 | 3815392.73 | 6.548
67 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BUTLER |  | 02 | 0055505 | This project involves the repaving of a little over 1 mile of State Highway 55 from the Conecuh County Line to US Highway 31 in McKenzie | Pavement Improvement | 2009-07-23 | 2009-08-24 | 2009-12-01 | 2010-03-03 | 518140.62 | 1.169
68 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HALE |  | 07 | 0060500 | This project involves the repaving and widening of approximately 11 miles of State Highway 60 from State Highway 14 to State Highway 69 near Havana | Pavement Improvement | 2010-04-21 | 2010-06-08 | 2010-12-31 | 2011-10-05 | 4719006.63 | 11.310
69 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALLAS |  | 07 | 0066502 | This project involves the repaving and 2 foot widening for approximately 5 miles of State Highway 66 from Marengo County line to State Highway 5 in Dallas County | Pavement Improvement | 2010-02-12 | 2010-03-15 | 2010-05-26 | 2011-03-26 | 1302509.19 | 4.959
70 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MARENGO |  | 07 | 0069521 | This project involves the widening of approximately 12 miles of State Highway 69 in Marengo County from US Highway 43 to the Hale County line | Pavement Improvement | 2009-07-23 | 2009-07-30 | 2009-10-16 | 2010-01-16 | 947089.69 | 11.643
71 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | FRANKLIN |  | 04 | 0069523 | This project involves the repaving of about 4 miles of State Highway 69 from Interstate 65 in Good Hope to the US Highway 31 intersection in Cullman | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-10-31 | 2009-12-07 | 1276909.8 | 3.700
72 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HALE |  | 07 | 0069525 | This project involves the repaving and extension of culvert pipes to improve roadside safety along 2 milesof State Highway 69 from the Marengo County line to US Highway 80 in Hale County | Pavement Improvement | 2009-07-23 | 2009-07-30 | 2009-10-16 | 2010-01-16 | 491005.69 | 1.994
73 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | 01 | 0069526 | This project involves repaving approximately 9 miles of State Highway 69 from north of County Road 23 (Salt Works Road) to about a mile north of County Road 368 (Dalmation Lane) in Clarke County | Pavement Improvement | 2010-03-02 | 2010-04-22 | 2010-06-30 | 2010-09-14 | 2229820.48 | 8.781
74 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MARENGO |  | 07 | 0069529 | This project involves the repaving of about 12 miles of State Highway 69 in Marengo County from US Highway 43 to the Hale County line | Pavement Improvement | 2009-07-23 | 2009-07-30 | 2009-10-16 | 2010-01-16 | 2497955.21 | 11.643
75 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BLOUNT |  | 04 | 0075515 | This project involves the repaving of aprroximately 4 miles of State Highway 75 from from Brooks Lane (County Road 363) in Allgood to 2nd Street (County Road 58) in Oneonta | Pavement Improvement | 2009-09-15 | 2009-10-02 | 2009-12-15 | 2010-08-19 | 1590122.66 | 3.570
76 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DE KALB |  | 04 | 0075516 | The project involves the repaving and widening of 4 miles of State Highway 75 (McCurdy Avenue) from about a half mile north of County Road 50 (Traylor Street) in Fyffe to just south of State Highway 3 | Pavement Improvement | 2009-10-06 | 2009-10-20 | 2010-05-15 | 2010-06-23 | 2723786.54 | 4.030
77 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | Multiple | 0079510 | This project involvesthe repaving of approximately 5 miles of State Highway 79 (Pinson Valley Parkway) from Winewood Road to State Highway 151 just west of Pinson in Jefferson County | Pavement Improvement | 2009-07-21 | 2009-08-10 | 2009-10-31 | 2010-06-02 | 2450035.84 | 5.200
78 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | PIKE |  | 02 | 0093501 | This project involves the repaving of about 2 miles of State Highway 93 from Us Highway 231 to the North city limits of Brundidge | Pavement Improvement | 2009-08-10 | 2009-09-02 | 2010-06-01 | 2009-10-22 | 721163.47 | 2.250
79 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | 03 | 0097503 | This project involves the repaving and 2 foot widening of approximately 1 mile State Highway 97 from Crenshaw County line to north of US Highway 31 near Letohatchee | Pavement Improvement | 2009-08-13 | 2009-10-08 | 2010-03-31 | 2011-03-11 | 572236.14 | 1.187
80 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | 0102530 | This project involves the repaving of about 7 miles of State Highway 102 from the Fayette County Line to the intersection with Old Birmingham Highway in Walker County | Pavement Improvement | 2010-02-02 | 2010-04-15 | 2010-08-01 | 2010-10-18 | 924020.85 | 6.896
81 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | 0103508 | This project involves the repaving and widening of 9 miles of State Highway 103 from the Florida State line to State Highway 52 in Slocomb | Pavement Improvement | 2009-11-16 | 2009-12-04 | 2010-07-20 | 2010-07-20 | 2413628.45 | 8.933
82 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | COOSA |  | 03 | 0115503 | This project involves the repaving of about 3 miles of State Highway 115 from State Highway 9 to US Highway 280 | Pavement Improvement | 2009-07-08 | 2009-07-23 | 2009-09-02 | 2010-10-14 | 1163764.15 | 3.190
83 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | JACKSON |  | 05 | 0117505 | This project involves the repaving of State Highway 117 in Jackson County from the intersection with State Highway 71 north for about 6 miles. | Pavement Improvement | 2010-01-19 | 2010-04-13 | 2010-07-01 | 2010-07-19 | 1717468.17 | 5.730
84 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | 0118508 | This project involves the repaving of about 4 miles of US Highway 78 in Carbon Hill from 4th Street to Ripley Loop Road. | Pavement Improvement | 2009-09-25 | 2009-10-09 | 2009-12-11 | 2010-06-01 | 1378812.75 | 3.676
85 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | AUTAUGA |  | 02 | 0123200 | This project involves the repaving of approximatley 3 miles of Autauga County Road 37 from Autauga County Road 24 to the Chilton County Line and is located North of Billingsley, Alabama. | Pavement Improvement | 2010-01-19 | 2010-03-02 | 2010-03-15 | 2010-06-24 | 265000 | 2.840
86 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | 0124500 | This project involves the repaving of approximately 10 miles of Old Birmingham Highway from US Highway 78 south to the intersection with State Highway 69 in Walker County. | Pavement Improvement | 2010-02-02 | 2010-04-15 | 2010-08-01 | 2010-10-18 | 1566988.39 | 10.896
87 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | FAYETTE |  | 04 | 0129502 | This project involves the repaving of approximately 7 miles of State Highway 129 from US Highway 43 to County Road 49 in Hubbertville | Pavement Improvement | 2009-08-10 | 2009-08-27 | 2009-10-27 | 2010-03-12 | 1620647.41 | 7.260
88 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE |  | 05 | 0133501 | This project involves the repaving of State Highway 133 from State Highway 20 to Magnum Street in the city of Florence | Pavement Improvement | 2010-04-21 | 2010-05-06 | 2010-10-15 | 2010-11-19 | 5086063.39 | 8.386
89 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 0133503 | This project involves the repaving of State Highway 133 from near Old Highway 20 (Colbert County Road 22) to Lincoln Avenue just south of Avalon Avenue | Pavement Improvement | 2010-06-23 | 2010-07-21 | 2010-10-15 | 2010-09-21 | 492906.7 | 2.545
90 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BIBB |  | 06 | 0139502 | This project involves the repaving of 7 miles of State Highway 139 from Six Mile Creek to just north of the Shelby County line | Pavement Improvement | 2009-09-10 | 2009-10-08 | 2010-02-27 | 2010-05-21 | 2244145.93 | 7.104
91 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | TALLADEGA |  | 03 | 0148500 | This project involves the repaving and 2 foot widening of about 2 miles of State Highway 148 from State Highway 21 to the east city limits of Sylacauga | Pavement Improvement | 2009-07-23 | 2009-08-07 | 2009-10-10 | 2009-11-23 | 596730.26 | 1.780
92 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | Multiple | 0154501 | This project involves repaving and widening for about 8 miles on State Highway 154 from 1 mile west of County Road 24 to US Highway 43 in Clarke County | Pavement Improvement | 2010-04-14 | 2010-04-20 | 2010-07-31 | 2011-04-19 | 3392134.11 | 7.600
93 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHILTON |  | 06 | 0155500 | This project involves the repaving and widening of 4 miles of State Highway 155 in Chilton County from near County Road 33 to the Shelby County line | Pavement Improvement | 2009-08-18 | 2009-09-03 | 2009-12-31 | 2010-05-28 | 1739561.92 | 4.076
94 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 0157514 | This project involves the repaving and the upgrade of bridge rails to current safety standards along State Highway 157 from the lawrence County Line to State Highway 20 in Colbert County | Pavement Improvement | 2009-09-15 | 2009-09-30 | 2010-07-01 | 2010-05-30 | 3557416.49 | 7.495
95 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | WILCOX |  | 07 | 0162501 | This project involves the repaving of 3 miles State Highway 162 from west of Dixon Creek to west of County Road 28 in Wilcox County | Pavement Improvement | 2010-02-09 | 2010-05-24 | 2010-07-31 | 2011-03-11 | 634261.27 | 3.141
96 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | PERRY |  | 07 | 0175500 | This project involves the repaving and widening of State Highway 175 from State Highway 14 near Heiberger to State Highway 5 in Perry County | Pavement Improvement | 2009-09-11 | 2010-04-27 | 2010-07-01 | 2011-04-01 | 1730838.95 | 5.382
97 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 0188501 | This project involves the repaving of about 9 miles of State Highway 188 from Franklin Creek to Oddfellows Cemetery in Baldwin County | Pavement Improvement | 2010-01-19 | 2010-02-10 | 2010-04-30 | 2010-06-10 | 1268047.1 | 8.670
98 | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 0192901 | This project provides for grading the road so it can be paved to a four lane roadway from 1500' South of Lake Yahoo to SR-1 (US-431) in Anniston. The project will be partial base and pave wih a bridge | New Construction | 2009-09-21 | 2009-10-09 | 2011-05-13 |  | 36100378.68 | 2.560
99 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | 0196500 | This project involves the repaving of Magnolia Avenue from State Highway 52 to State Highway 27 in Geneva | Pavement Improvement | 2010-01-19 | 2010-02-24 | 2010-04-15 | 2010-04-15 | 463771.24 | 1.690
100 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | 0198500 | This project involves the repaving and widening of approximately 2 miles of State Highway 198 in Barbour County from just east of State Highway 239 to State Highway 30 | Pavement Improvement | 2010-02-03 | 2010-02-22 | 2010-07-23 | 2010-07-23 | 462493.22 | 1.610
101 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | 0210200 | This project involves the repaving of County Road 32 from Sate Highway 59 to County Road 87 in Baldwin County | Pavement Improvement | 2010-05-13 | 2010-06-07 | 2010-08-01 | 2011-01-27 | 265000 | 7.000
102 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 0213502 | This project involves the repaving and widening of about 3 miles of State Highway 213 (Shelton Beach Road) from State Highway 158 (Industrial Parkway) to US Highway 43 (Saraland Boulevard) in Saraland | Pavement Improvement | 2009-07-22 | 2009-09-29 | 2009-11-30 | 2010-04-30 | 666232.44 | 2.880
103 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BULLOCK |  | 02 | 0223501 | This project involves the repaving and 2 foot widening of a bout a mile of State Highway 223 (Baskin Street) from the Bullock County High School to the junction of US Highway 82 in Union Springs | Pavement Improvement | 2009-09-10 | 2009-09-28 | 2010-01-01 | 2010-03-10 | 266301.56 | 0.750
104 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | 0239501 | This project involves the repaving and widening of 2 miles of State Highway 239 from State Highway 51 to State Highway 51 North in Barbour County | Pavement Improvement | 2010-02-03 | 2010-02-22 | 2010-07-23 | 2010-07-23 | 482317.97 | 1.916
105 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | FRANKLIN |  | 04 | 0241501 | This project involves the repaving of about a mile of State Highway 241 from just south of the Marion County line to State Highway 237 in Franklin County | Pavement Improvement | 2009-07-30 | 2009-08-28 | 2010-05-01 | 2009-10-21 | 840274.79 | 1.024
106 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | 0263501 | This project involves the repaving and 2 foot widening of approximately 9 miles of State Highway 263 from the Butler County line to State Highway 21 | Pavement Improvement | 2010-01-26 | 2010-03-03 | 2010-06-30 | 2011-01-11 | 2558166.21 | 8.480
107 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | WILCOX |  | 07 | 0265500 | This project involves the repaving and safety widening for about 7 miles of State Highway 265 from just north of County Road 51 to State Highway 41 in Wilcox County | Pavement Improvement | 2010-02-09 | 2010-05-24 | 2010-07-31 | 2011-03-11 | 1697207.27 | 6.830
108 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHEROKEE |  | 03 | 0273500 | The project involves the repaving and widening of approximately 16 miles of State Highway 273 from State Highway 68 in Leesburg to State Highway 35 near Blanche | Pavement Improvement | 2009-08-12 | 2010-05-21 | 2010-09-30 | 2010-12-06 | 3816700.1 | 15.836
109 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | 0325201 | This project involves the repaving of Barbour County Road 49 from US Highway 82 to Barbour County Road 89 at Springhill | Pavement Improvement | 2010-05-20 | 2010-06-14 | 2010-09-30 | 2010-11-30 | 265000 | 4.203
110 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | BULLOCK |  | 02 | 0621200 | This project will completely rebuild the pavement structure (full depth reclamation) down to the subgrade, then the pavement will be widened and repaved approximately 8 miles of Bullock County Road 2 | Pavement Improvement | 2009-10-22 | 2009-11-18 | 2010-02-03 | 2011-01-28 | 265000 | 7.610
111 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | BUTLER |  | 02 | 0707200 | This project involves the repaving and widening of County Road 15 from State Highway 106 to County Road 38 in Butler County | Pavement Improvement | 2010-05-20 | 2010-06-08 | 2010-08-31 | 2010-09-23 | 265000 | 7.902
112 | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 0800214 | This project involves the repaving of Hillyer Robinson Industrial Parkway from Greenbrier Road to city limits of Anniston | Pavement Improvement | 2010-07-29 | 2010-09-15 | 2011-04-30 |  | 775679.93 | 0.790
113 | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 0800215 | This project involves the repaving of Frank Akers Road from Hillyer Robinson Road to Coleman Road in the city of Anniston in Calhoun County | Other | 2010-07-29 | 2010-09-15 | 2011-04-30 |  | 217672 | 0.370
114 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN |  | 03 | 0800216 | This project involves the replacement of a bridge with an inventory number 1001 and its approaches on Prickett Trail (County Road 553) over Tallassechatchee Creek | Pavement Improvement | 2010-05-25 | 2010-06-09 | 2010-12-01 | 2011-05-05 | 265000 | 0.255
115 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CHAMBERS |  | 03 | 0928200 | This project will completely rebuild the pavement structure (full depth reclamation) down to the subgrade, then the pavement will be repaved approximately 5 miles of County Road 267 in Chambers County | Pavement Improvement | 2009-07-27 | 2009-10-02 | 2009-11-15 | 2010-03-31 | 265000 | 5.571
116 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CHEROKEE |  | 03 | 1006201 | "This project involves the repaving of approximately 4 miles of Cherokee County Road 71 (Centre Rd.) from 0.6 miles north of Cherokee County Road 59 ( to the Terrapin Creek Bridge south of Centre | Pavement Improvement | 2009-12-29 | 2010-05-21 | 2010-06-11 | 2010-06-30 | 265000 | 4.200
117 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | 1205201 | This project involves the repaving and widening of County Road 32 from County Road 9 to State Highway 17 in Choctaw County | Pavement Improvement | 2010-05-18 | 2010-07-02 | 2010-07-12 | 2010-10-07 | 265000 | 6.130
118 | Underway | C250 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | 07 | 1301200 | This project involves the replacement of a bridge on Clarke County Road 15 over Bassetts Creek | Other | 2010-02-11 | 2010-02-11 | 2011-01-01 |  | 265000 | 0.110
119 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CLAY |  | 03 | 1405201 | "This project involves the repaving of approximately 7 miles of Clay County Road 35 (Bluff Springs Road) from the Tallapoosa County Line to the intersection of Clay County Road 132 (Sardis Road) south | Pavement Improvement | 2010-03-02 | 2010-04-20 | 2010-06-18 | 2010-08-06 | 265000 | 6.900
120 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 1709200 | This project involves the repaving of County Road 57 from County Road 61 to the Joe Wheeler Highway (State Highway 20) in Tuscumbia | Pavement Improvement | 2009-08-19 | 2009-09-30 | 2010-06-26 | 2009-12-22 | 330972.08 | 2.727
121 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT |  | 05 | 1710201 | This project involves the replacement of a bridge with inventory number 001173 over Rock Creek on Colbert County Road 1 (Maud Rd.) | Other | 2009-08-27 | 2009-08-27 | 2011-02-15 | 2011-10-12 | 107767.49 | 0.246
122 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 1717200 | This project involves the repaving of 1 mile of River Road from County Road 48 to Brick School Road in Muscle Shoals | Pavement Improvement | 2009-10-13 | 2010-04-22 | 2010-05-19 | 2010-05-19 | 135105.43 | 0.893
123 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CONECUH |  | 02 | 1818202 | "This project involves the repaving of approximately 4 miles of Conecuh County Road 23 from U.S. Highway 31(N. Jackson Street) northwesterly to Interstate 65 (I-65) north of Castleberry | Pavement Improvement | 2009-11-09 | 2009-12-08 | 2010-01-31 | 2010-04-29 | 265000 | 4.160
124 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | COOSA |  | 03 | 1907200 | This project involves the repaving of County Road 85 from County Road 50 at Kellyton to County Road 86 in Coosa County | Pavement Improvement | 2010-05-18 | 2010-06-05 | 2010-08-30 | 2010-10-04 | 265000 | 6.200
125 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COFFEE |  | 02 | 1E34600 | This project involves the repaving of County Road 709 in Enterprise from State Highway 167 to State Highway 134 | Pavement Improvement | 2009-09-11 | 2009-10-12 | 2010-07-01 | 2010-08-27 | 265000 | 2.589
126 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CRENSHAW |  | 02 | 2032200 | "This project involves the widening and repaving of Covington County Road 98 from U.S. Highway 84 to Covington County Road 49 in Covington County. | Pavement Improvement | 2009-10-07 | 2009-11-02 | 2010-07-29 | 2010-07-29 | 265000 | 1.241
127 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CRENSHAW |  | 02 | 2111202 | "This project involves the repaving of approximately 5 miles of Crenshaw County Road 6 (Glenwood Rd./Luverne St.) from the Luverne | Pavement Improvement | 2010-05-18 | 2010-06-22 | 2010-09-30 | 2010-11-09 | 265000 | 3.963
128 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CULLMAN |  | 04 | 2215200 | This project involves the repaving of County Road 1069 from County Road 1043 to County Road 1101 in Cullman County | Pavement Improvement | 2010-05-13 | 2010-07-14 | 2010-09-30 | 2011-02-18 | 265000 | 6.329
129 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2304200 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 31 from U.S. Routhe 84/Alabama Route 12 to Dale County Road 43.in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 62917 | 3.969
130 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2311201 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 73 from Dale County Road 14 to the Henry County Line in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 70257 | 4.432
131 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2311202 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 14 from Dale County Road 67 to Dale County Road 73 in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 20449 | 1.290
132 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2315201 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 83 from Dale County Road 62 to Dale County Road 36 in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 51599 | 3.255
133 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2331200 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 63 from U.S. Routhe 231/Alabama Route 53 to Dale County Road 14.in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 33131 | 2.090
134 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | DALLAS |  | 07 | 2446200 | This projects involves the repaving and widening of county road 81 from State Highway 22 to State Highway 22 at Valley Grande | Pavement Improvement | 2010-06-01 | 2010-07-13 | 2010-08-31 | 2011-03-31 | 265000 | 3.627
135 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE |  | 02 | 2601201 | This projects involed paving the shoulder and traffic striping along Rifle Range Road from Redland Road to Mitchell Creek Road | Pavement Improvement | 2010-01-26 | 2010-02-03 | 2010-03-05 | 2010-04-12 | 297940.2 | 6.610
136 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE |  | 02 | 2606202 | This project involves the repaving andstriping of Main Street from 1st Avenue east to the Eclectic city limits | Pavement Improvement | 2010-02-24 | 2010-03-29 | 2010-05-11 | 2010-05-11 | 265000 | 1.634
137 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | 2710200 | "This project involves the widening and repaving of approximately 5 miles of Escambia County Road 17 (Stanley Rd.) from Escambia County Road 27 (Robinsonville Rd.) to Alabama Highway Route 113 | Pavement Improvement | 2010-01-05 | 2010-02-02 | 2010-04-28 | 2010-06-15 | 265000 | 4.720
138 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH |  | 04 | 2810200 | This proeject involves the milling and repaving of Gilley Road from Centre Road to the Cherokee County line | Pavement Improvement | 2010-01-27 | 2010-09-22 | 2010-10-21 | 2010-10-20 | 265000 | 1.410
139 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DE KALB |  | 04 | 2F07600 | This project involves the widening and repaving of County Road 89 from the Fort Payne city limits to County Road 78. | Pavement Improvement | 2010-05-12 | 2010-06-04 | 2010-08-15 | 2010-08-10 | 265000 | 2.900
140 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | FRANKLIN |  | 04 | 3000209 | The replacement of the bridge with identification number 001134 and the roadway approaches over Bear Creek located on Franklin County Road 93 in Franklin County, Alabama. | Bridge Replacement | 2010-05-25 | 2010-06-24 | 2010-12-01 | 2011-01-19 | 265000 | 0.072
141 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | 3131200 | "This project involves the repaving and widening of approximately 3 miles of Geneva County Road 4 (Goathill Road) from Alabama State Highway 87 to Geneva County Road 120 (Ausley Road) West of Geneva | Other | 2009-11-09 | 2009-12-28 | 2010-02-26 | 2010-07-06 | 265000 | 6.180
142 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | GREENE |  | 07 | 3200205 | This project involves the replacement of bridge over South Needham Creek on County Road 25 | Pavement Improvement | 2010-05-11 | 2010-06-11 | 2010-09-26 | 2010-11-29 | 265000 | 0.060
143 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | HALE |  | 07 | 3314200 | This project involves the widening and resurfacing of County Road 32 from State Highway 69 to State Highway 25 | Pavement Improvement | 2010-04-15 | 2010-05-05 | 2010-11-11 | 2011-12-12 | 530000 | 6.456
144 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | HENRY |  | 02 | 3408200 | "This project involves the widening and repaving of Henry County Road 99 from Henry County Road 41 to Henry County Road 107 in Abbeville | Pavement Improvement | 2009-08-21 | 2009-09-09 | 2010-06-01 | 2010-02-04 | 265000 | 1.706
145 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON |  | 02 | 3500214 | This project will replace the bridge with inventory number 003313 over Cedar Creek on East Cook Road (County Road 438) about a half north of Ed Tolar Road in Houston County | Bridge Replacement | 2009-07-14 | 2009-08-03 | 2010-05-01 | 2010-07-21 | 265000 | 0.038
146 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | JACKSON |  | 05 | 3621201 | The widening and repaving of Jackson County Road 88 from Alabama Route 71 to the Dekalb County Line in Jackson County, Alabama. | Pavement Improvement | 2010-05-12 | 2010-07-09 | 2010-08-15 | 2010-12-21 | 354005 | 4.150
147 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 3713200 | Rex Lake Road is currently a 2 lane county road that serves the Barber Motorsports facility and the recently constructed Bass Pro Shop. The project will convert the existing 2 lane to a 4 lane divide | Pavement Improvement | 2009-10-30 | 2009-11-16 | 2011-05-09 |  | 5497447.75 | 0.956
148 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LAMAR |  | 04 | 3804200 | "This project involves the repaving of approximately 10 miles of Lamar County Road 49 & 20 (Pickens St.) from the Northern Right of Way of the Luxapallila Railroad in Kennedy | Pavement Improvement | 2009-11-04 | 2009-12-03 | 2010-02-20 | 2010-03-08 | 265000 | 9.850
149 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LAWRENCE |  | 05 | 4000219 | The project involves the replacement of a bridge with the inventory number 003222 on County Road 129 over Pool Creek in Lawrence County | Bridge Replacement | 2009-09-14 | 2009-10-28 | 2010-07-31 | 2009-12-22 | 121765.18 | 0.005
150 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LAWRENCE |  | 05 | 4000220 | "This project will replace the bridge for Sandy Creek on Lawrence County Road 150. The bridge has an inventory number of 002345 and wil be replace by a bridge culvert that has 3 barrels that are 10 f | Pavement Improvement | 2009-11-06 | 2009-11-20 | 2010-03-24 | 2010-03-24 | 128994.63 | 0.006
151 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LEE |  | 03 | 4107200 | This project involves the widening and repaving of County Road 401 from County Road 166 to County Road 165 | Pavement Improvement | 2010-05-26 | 2010-08-01 | 2010-09-30 | 2010-12-21 | 234877.27 | 1.288
152 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | 4311200 | This project involves the repaving of County Road 26 from State Highway 21 to west of County Highway 6 | Pavement Improvement | 2010-01-28 | 2010-02-13 | 2010-03-30 | 2010-05-06 | 265000 | 8.989
153 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MACON |  | 03 | 4424203 | This project involves the repaving of County Road 54 from East of the Notasulga city limits to County Road 53 | Pavement Improvement | 2010-01-19 | 2010-02-01 | 2010-04-15 | 2010-04-30 | 265000 | 2.810
154 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | 4500215 | This project will replace a bridge with inventory number 009682 and upgrade the width and safety of the approaching roadway on County Road 50 (Douglass Road) over Douglass Branch approximately a half | Pavement Improvement | 2010-05-18 | 2010-06-22 | 2010-10-15 | 2011-06-08 | 390770 | 0.129
155 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | 4500216 | This project involves he replacement of a bridge on Low Gap Road (County Road 286) over Glover Branch in Madison County | Bridge Replacement | 2010-07-14 | 2010-09-29 | 2010-09-30 | 2011-05-20 | 201278.01 | 0.008
156 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MARENGO |  | 07 | 4606201 | The repaving of Marengo County Road 33 from U.S. 43/Alabama Route 13 to Marengo County Road 47 in Marengo County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-21 | 2010-08-31 | 2010-08-18 | 265000 | 4.100
157 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | MARENGO |  | 07 | 4738200 | This project involves the repaving of County Road 51 from County Road 42 to US Highway 278 (State Highway 74) in Marengo County | Pavement Improvement | 2010-05-19 | 2010-06-17 | 2010-08-31 | 2010-09-21 | 265000 | 1.590
158 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MARSHALL |  | 04 | 4803201 | This project involves repaving County Road 73 (High Point Road) from Old Oneonta Road to Oneonta Cut-off Road | Pavement Improvement | 2010-05-04 | 2010-06-18 | 2010-08-31 | 2010-08-20 | 196513.15 | 0.767
159 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | 5027200 | This project involves the widening and repaving of County Road 45 from State Highway 21 to County Road 7 | Pavement Improvement | 2010-04-28 | 2010-05-17 | 2010-08-12 | 2010-11-10 | 265000 | 1.961
160 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | 5218200 | This project involves the repaving of South Seneca Drive From the Trinity town limits to Deanna Bridge Highway | Pavement Improvement | 2009-06-29 | 2009-07-02 | 2010-07-01 | 2010-08-18 | 55906.97 | 1.000
161 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | 5222200 | This project involves the repaving of less than a mile of Indian Hills Road from Lincoya Circle to Ben Poole Road in the city of Decatur | Pavement Improvement | 2009-07-17 | 2009-08-01 | 2010-07-15 | 2010-12-06 | 84137.1 | 1.520
162 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 05 | 5226200 | This project involves repaving and striping of Finley Road from State Highway 20 to Gate | Pavement Improvement | 2010-04-22 | 2010-06-28 | 2010-10-01 | 2010-08-10 | 566265 | 1.690
163 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | PERRY |  | 07 | 5303200 | This project involves the repaving of about 7 miles of County Road 12 from 2 miles east of State Highway 183 to State Highway 5 in Perry County | Pavement Improvement | 2009-10-13 | 2010-02-02 | 2010-04-08 | 2011-09-13 | 265000 | 6.910
164 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | PICKENS |  | 07 | 5422200 | The project involves the milling, repavaing, and striping of County Road 85 from the Sumter County line to State Highway 17 | Pavement Improvement | 2010-01-27 | 2010-04-02 | 2010-11-11 | 2010-10-28 | 265000 | 4.493
165 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | PIKE |  | 02 | 5505202 | This project involves the repaving of County Road 2276 from the Crenshaw County line to County Road 2290 and also the repaving of County Road 2290 from County Road 2276 to County Road 2262 near Hender | Pavement Improvement | 2009-07-16 | 2009-07-23 | 2010-05-01 | 2010-06-28 | 265000 | 5.565
166 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | RANDOLPH |  | 03 | 5605200 | This project involves the widening and repaving of Randolph County Road 82 from the Meadows Bridge (Little Tallapoosa River) to Randolph County Road 87. | Pavement Improvement | 2009-09-28 | 2009-10-22 | 2010-05-25 | 2010-06-04 | 265000 | 5.642
167 | Underway | C250 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL |  | 03 | 5704200 | This project will relocate and replace a bridge on Russell County Road 4 over Weolustee Creek north of Pitttsview | Pavement Improvement | 2009-09-30 | 2009-10-09 | 2010-08-10 |  | 265000 | 0.056
168 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | ST CLAIR |  | 06 | 5824200 | The project involves the repaving of County Road 12 from County Road 6 to State Highway 174 | Pavement Improvement | 2010-05-04 | 2010-06-14 | 2010-09-14 | 2010-09-24 | 530000 | 7.222
169 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LIMESTONE | DECATUR | 05 | 5A20600 | This project involves the widening and repaving of Lucas Ferry Road (County Road 45) from Harris Station Road (County Road 45) to Nuclear Plant Road (County Road 677). | Pavement Improvement | 2010-06-01 | 2010-07-01 | 2010-08-30 | 2010-08-13 | 265000 | 2.050
170 | Underway | C250 | Highway Infrastructure Investment Grant | ALABAMA | SUMTER |  | 07 | 6020200 | "This project involves the repaving and extending the culvert pipes to improve the roadside safety of approximately 2 miles of Sumter County Road 27 from the Mississippi State line south to Sumter Co | Pavement Improvement | 2009-10-16 | 2009-11-04 | 2010-08-31 |  | 265000 | 7.010
171 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | TALLADEGA |  | 03 | 6111200 | This project involves the repaving of Horn's Lake Road (County Road 209) from State Highway 77 to the Clay County line | Pavement Improvement | 2010-06-01 | 2010-07-15 | 2010-08-10 | 2010-09-22 | 358844.72 | 2.700
172 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | TALLAPOOSA |  | 03 | 6233200 | "This project includes widening and repaving of approximately 7 milles of Tallapoosa County Road 44 (Dudleyville Road) from Tallapoosa County Road 32 (Denver Road) to the Chambers County Line | Pavement Improvement | 2010-01-07 | 2010-03-01 | 2010-05-31 | 2010-07-08 | 265000 | 7.250
173 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 6303200 | This project involves the milling and paving of Hagler Coaling Road (County Road 239) from Serty Boyd Road (County Road 240) to Clements Road (State Highway 566) in Tuscaloosa County | Pavement Improvement | 2010-05-25 | 2010-06-21 | 2010-08-07 | 2011-03-11 | 1221280 | 5.900
174 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 6312200 | The replacement of the bridge and roadway approaches with a triple barrel box bridge culvert with identification number 000864 over Cooley Creek on Tuscaloosa County Road 97 (Eastern Valley Road) near | Pavement Improvement | 2010-06-24 | 2010-08-09 | 2011-03-31 | 2011-04-07 | 769000 | 0.013
175 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | WASHINGTON |  | 01 | 6500206 | The replacement of the bridge over the Escatawpa River with a new Precast Bridge in Washington County, Alabama. | Bridge Replacement | 2010-05-27 | 2010-06-08 | 2011-01-31 | 2011-04-14 | 265000 | 0.098
176 | Underway | C250 | Highway Infrastructure Investment Grant | ALABAMA | WILCOX |  | 07 | 6617200 | The repaving of Wilcox County Road 29 from Gees Bend Landing to 0.47 mile north of Chilatchee Park Road in Wilcox County, Alabama. | Pavement Improvement | 2010-06-02 | 2010-06-22 | 2010-08-09 |  | 265000 | 7.149
177 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | WINSTON |  | 04 | 6721200 | This project involves the repaving of County Road 14 from County Road 41 to County Road 39 in Winston County | Pavement Improvement | 2010-05-18 | 2010-07-12 | 2010-08-15 | 2010-08-17 | 266297.11 | 3.040
178 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7005600 | This project will realign 3 intersections in the City of Hoover and replace the existing signals. The realignments will improve driver's sight distance and visibility. | Pavement Improvement | 2009-12-15 | 2010-01-12 | 2011-06-30 |  | 1878317.89 | 0.166
179 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7020600 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Widening | 2010-05-05 | 2010-06-21 | 2011-03-20 |  | 1375027 | 0.600
180 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7045600 | This project will add a center two way left turn lane to Jefferson Avenue (County Road 18) from the Birmingham City limits to 50th Street. | Other | 2010-02-26 |  | 2011-08-01 |  | 1659402.64 | 1.500
181 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 07 | 7045601 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Improvement | 2009-11-12 |  | 2011-03-27 |  | 2624716.25 | 0.750
182 | Underway | C240 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | 7112604 | This project involves the widening and repaving of County 17 from north of County Road 270 to apprroximately south of Lacey Avenue. This project includes the replacement of the bridge over Beaverdam | Other | 2010-01-29 | 2010-08-23 | 2010-10-10 |  | 265000 | 0.480
183 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 07 | 7173600 | This project will add dual left turn lanes on East Lake Blvd to SR-79 SB. The improvements will help relieve congestion by allowing more vehicles to make a left turn in a shorter amount of time. | Pavement Widening | 2010-05-26 | 2010-08-11 | 2011-12-10 |  | 339737 | 0.170
184 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 07 | 7229601 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Widening | 2009-11-09 | 2010-02-01 | 2010-11-24 |  | 2900626.44 | 1.400
185 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7273600 | The repaving of Jefferson County Road 2133 known as Deefoot Parkway from U.S. Route 11/Alabama Route 7 to Interstate 59. | Pavement Improvement | 2010-05-26 | 2010-06-15 | 2010-08-10 | 2010-09-04 | 265000 | 1.584
186 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7321600 | This project is for the relocation of utilities that conflict with the construction of Chapel Lane Extension from Al Seier Road to Galleria Boulevard in Birmingham. | Other | 2010-02-25 | 2010-06-29 |  |  | 1659402.64 | 0.750
187 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7400600 | This project involves the repaving of approximately 3 miles of Friendship Road in the city of Oxford from SR-21 to Boiling Spring Road | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2010-07-28 | 2011-05-19 | 665600 | 7.200
188 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7401601 | This project involves the installation of a new traffic signal at the intersection of Noble Street (County Road 105) and Greenbrier Dear Road (County Road 198) | Safety/Traffic Management | 2010-04-13 |  | 2011-03-07 | 2010-05-06 | 105726 | 0.000
189 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7425600 | The project will consist of pole replacement, new traffic lights to upgrade the traffic signal at Bill Robinson Parkway. | Safety/Traffic Management | 2010-04-13 |  | 2011-03-07 | 2011-05-06 | 105000 | 0.000
190 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7431600 | This project involves the repaving of Alexandria/Jacksonville Road from Francis Street to South Jacksonville city limits | Pavement Improvement | 2010-04-28 | 2010-06-02 | 2010-09-01 | 2010-11-30 | 400000 | 1.570
191 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7460600 | This project involves the replacement of a bridge on Eulaton Road (County Road 81), north of State Highway 202 near County Road 109 | Pavement Improvement | 2010-05-11 | 2010-06-21 | 2010-08-30 | 2011-02-25 | 409530 | 0.208
192 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7507600 | This project will replace a bridge and upgrade the width and safety of the approaching roadway on Michigan Avenue over the CSX railroad in Mobile | Pavement Improvement | 2010-05-06 | 2010-09-01 | 2011-05-15 |  | 3583781.38 | 0.191
193 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7548600 | This project involves the repaving about a mile of Springhill Avenue from McGregor Avenue to Intersate 65 in the city of Mobile | Pavement Improvement | 2009-08-27 | 2009-09-03 | 2009-11-30 | 2009-12-10 | 309146.29 | 1.300
194 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7548601 | This project involves the repaving of less than a mile of Springhill Avenue from Interstate 65 to Moffet Road in the city of Mobile | Pavement Improvement | 2009-08-27 | 2009-09-03 | 2009-11-30 | 2009-12-10 | 136802.85 | 0.600
195 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7552600 | This project involves the repaving of Howells Ferry Road (County Road 605) from Snow Road (County Road 25) to Cody Road (County Road 429) | Pavement Improvement | 2010-01-28 | 2010-03-10 | 2010-05-31 | 2010-08-30 | 1322100 | 5.000
196 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7560600 | This project involves the repaving of about 3 miles of West Main Street from Prichard Avenue to Branch Avenue in the city of Mobile | Pavement Improvement | 2009-06-22 | 2009-07-24 | 2010-08-31 | 2010-12-27 | 903586.96 | 6.448
197 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7573600 | This project involves traffic stripe, markings, legends and pavement markers on CR-41 (Celeste Road) from SR-13 (US-43) in Saraland to Lafitte Road. | Safety/Traffic Management | 2009-12-30 | 2010-01-18 | 2010-02-28 | 2010-02-11 | 114172.55 | 2.500
198 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MACON | MOBILE | 03 | 7597600 | This project involves the repaving and widening of Viaduct Road from east of Mike Box Bridge to Warrior Gulf and from Mike Box Bridge to Southern Ionix. This project also includes the repaving of via | Pavement Improvement | 2009-07-07 | 2009-08-10 | 2010-07-15 | 2010-09-10 | 535000 | 2.000
199 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7599600 | This project involves the repaving of about 1 mile of Baker from Interstate 64 to US Highway 43 north of Mobile | Pavement Improvement | 2009-06-17 | 2009-07-24 | 2010-07-15 | 2010-10-18 | 274305.19 | 2.000
200 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7614600 | This project involves the repaving of McCrary Road (County Road 604) from US Highway 98 (SR-42) to Lott Road (SR-217) | Pavement Improvement | 2010-02-03 | 2010-02-26 | 2010-04-30 | 2010-12-06 | 813600 | 2.900
201 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7615600 | Mobile County will widen the existing 20 eet width pavement of Half Mile Road 2 feet on each side and then resurface with asphalt the entire 24 feet width from Beverly Road eastwardly approximately 2 | Pavement Improvement | 2009-07-24 | 2009-09-28 | 2009-12-31 | 2010-07-30 | 265000 | 1.837
202 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7616600 | This project involves the repaving of about 6 miles of the Irvington-Bayou La Batre Highway from State Highway 188 to US Highway 90 in the town of Irvington | Pavement Improvement | 2010-04-29 | 2010-05-14 | 2010-08-09 | 2011-06-29 | 1615068.84 | 5.740
203 | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | 02 | 7724601 | The existing two-lanes of Perry Hill Road in Montgomery from Interstate 85 to Harrison Road will be widened to provide an undivided four-lane highway. | Pavement Widening | 2010-04-15 | 2010-09-21 | 2011-04-28 |  | 1949739.91 | 0.511
204 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE | MONTGOMERY | 02 | 7804601 | This project involves the repaving of Alabama River Parkway (County Road 2) from State Highway 143 to Jackson Lake Road (County Road 60) | Pavement Improvement | 2010-05-05 | 2010-06-22 | 2010-07-30 | 2010-09-09 | 500837.88 | 1.690
205 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | AUTAUGA | MONTGOMERY | 02 | 7812601 | This project involves the repaving of McQueen Smith Road (County Road 75) from East Main Street (County Road 2) to State Highway 14 | Pavement Improvement | 2010-04-21 | 2010-05-20 | 2010-07-16 | 2010-08-24 | 740000 | 1.467
206 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | AUTAUGA | MONTGOMERY | 02 | 7899600 | This project involves the repaving of Gin Shop Hill Road (County Road 29) from West 4th Street (State Highway 206) to US Highway 82 (State Highway 6) | Pavement Improvement | 2010-04-15 | 2010-05-17 | 2010-07-06 | 2010-08-24 | 217453.97 | 1.083
207 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 8007601 | "This project involves the repaving of Russell County Road 28 (Sandfort Road) from the West City Limit of Phenix City | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-07-30 | 2011-05-19 | 594180 | 5.120
208 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 8018600 | "This project involves the repaving Russell County Road 427 (Opelika Rd.) from Russell County Road 418 (Crawford Rd.) to 22nd Street and Russell County Road 427 (Opelika Road) from Russell County Road | Pavement Improvement | 2009-07-28 | 2009-07-28 | 2010-07-30 | 2010-10-19 | 321358.24 | 1.820
209 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 8018601 | This project involves the repaving and striping of Opelika Road (County Road 427) from Cut Rate Road (County Road 296) to south of Stafford Raod (County Road 296) | Pavement Improvement | 2009-12-01 | 2009-12-01 | 2010-08-15 | 2010-12-02 | 269827.44 | 1.940
210 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 8041601 | This project involves the repaving and striping of Pierce Road (County Road 427) from US Highway 431/280 in Russell County to Summerville Road in Lee County | Pavement Improvement | 2010-05-11 | 2010-06-25 | 2010-08-02 | 2011-02-09 | 511097.32 | 1.778
211 | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH | GADSDEN | 04 | 8104600 | This project constructs a new 4 lane roadway approximately 1 mile long between the intersections of Steel Station / Sutton Bridge Roads to I-759. | Pavement Improvement | 2009-12-15 | 2010-02-10 | 2010-07-02 |  | 2138433 | 3.360
212 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON, MACON | HUNTSVILLE | Multiple | 8509601 | This project constructs additional turn lanes on both Wall Triana Highway and US-72 (SR-2) with a signal Modification. | Pavement Improvement | 2009-08-27 | 2010-05-26 | 2010-08-14 | 2011-10-31 | 738997 | 1.622
213 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 05 | 9229600 | This project involves the repaving of Austinville Road SW from Carridale Street to 14 th Street SW and 14th Street SW to Central Parkway in the city of Decatur | Pavement Improvement | 2009-07-07 | 2009-07-09 | 2010-07-01 | 2010-12-06 | 133917 | 0.660
214 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 9412601 | This project involves the repaving of Westgate Parkway from US Highway 84 to US Highway 231 in the city of Dothan | Pavement Improvement | 2009-06-22 | 2009-07-01 | 2010-09-15 | 2011-02-17 | 644000 | 4.000
215 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 9412602 | This project involves the repaving of Honeysuckle Road from US Highway 84 to Park Avenue in the city of Dothan | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-09-15 | 2011-02-17 | 763590 | 5.100
216 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 9414601 | This project involves the widening and repaving of Fortner Street (County Road 40) from Brannon Stand Road to Honeysuckle Road | Pavement Improvement | 2010-05-05 | 2010-06-15 | 2010-10-31 | 2011-01-31 | 105968.88 | 3.050
217 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 9440600 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 75 (Alpha Street) from U.S. Routhe 231/Alabama Route 53 to Dale County Road 112. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 26647 | 1.685
218 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 9441604 | This project involves the resurfacing of South Brannon Stand Road (CR-59) from 0.06 mile north of SR-52 to 0.30 mile north of CR-40 (Fortner Street). | Pavement Improvement | 2010-01-13 | 2010-06-01 | 2010-09-15 | 2010-09-16 | 317740 | 2.150
219 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 9628600 | This project involves the repaving of Charlie Shirley Road (County Road 84) from State Highway 69 to US Highway 43( State Highway 13) in the city of Northport in Tuscaloosa County | Pavement Improvement | 2010-09-16 |  | 2010-11-30 | 2011-02-14 | 370851.4 | 2.410
220 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 9642600 | This project involves the repaving of 5th Street (County Road 30) from Main Avenue to Robert Cardinal Airport Road in Tuscaloosa County | Pavement Improvement | 2010-09-16 |  | 2010-11-30 | 2011-02-14 | 175213.53 | 1.425
221 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 9802918 | This project will improve lane widths and turn lane lengths at selected intersections along Lorna Road. The project will also replace the traffic signals with new equipment. These improvements will | Safety/Traffic Management | 2010-05-19 | 2010-09-13 | 2011-05-06 |  | 1246204.81 | 2.900
222 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 07 | 9802920 | This project involves the first phase of modification and upgrade to the traffic management center in the city of Birmingham | Safety/Traffic Management | 2010-05-25 | 2010-06-09 | 2011-02-09 |  | 660387.5 | 0.000
223 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | CN07908 | This project is the first phase of the Hoover Park Avenue Sidewalks project and involves the addition of sidewalks along Rockview lane from the Rockview Lane/ Park Avenue intersection to the Bluff Par | Transportation Enhancements | 2010-05-27 | 2010-07-13 | 2011-02-11 |  | 161055 | 0.000
224 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | CN07909 | This project involves the addition of sidewalks along Park Avenue in Hoover between Chapel Raod and Farlay Road | Transportation Enhancements | 2010-05-27 | 2010-07-13 | 2011-02-11 |  | 442464.08 | 0.000
225 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE, BALDWIN |  | 01 | CN09208 | "This project will repair badly deteriorated pavements at 16 sites located throughout Mobile and Baldwin Counties. The sites are located on various state | Pavement Improvement | 2009-07-27 | 2009-09-09 | 2009-12-31 | 2010-03-31 | 802306.52 | 0.000
226 | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | Multiple | CN09906 | This project involves the repaving of various streets in the central business district of Montgomery | Pavement Improvement | 2010-04-29 | 2010-06-01 | 2011-02-09 |  | 2850260 | 0.000
227 | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE | MONTGOMERY | 02 | CN09908 | This project involves the repaving of the Coosa River Parkway from West Bridge Street to US Highway 231 and the repaving of West Bridge Street from the Coosa River Parkway to North Bridge Street in We | Pavement Improvement | 2009-07-30 | 2009-08-27 | 2009-11-30 | 2010-05-20 | 1147835.61 | 3.459
228 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE |  | 05 | CN10201 | "This project involves the repaving of two different roads. Site 1 is South of Lovelace Crossroads and includes approximately 2 miles of Lauderdale County Road 6 from Lauderdale County Road 219 to Ala | Pavement Improvement | 2009-12-28 | 2010-03-28 | 2010-04-21 | 2010-04-21 | 265000 | 3.561
229 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | CN10204 | This project involves the resurfacing of CR-26 (Jordon Avenue) from North ROW SR-12 (US-84) to 0.22 mile east of Glen Lawrence Int. | Pavement Improvement | 2010-01-13 | 2010-06-01 | 2010-09-15 | 2010-09-16 | 328590 | 2.110
230 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | FAYETTE |  | 04 | CN10208 | This project involves striping various county roads in Fayette County | Safety/Traffic Management | 2010-04-20 |  |  | 2011-05-12 | 265000 | 50.375
231 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE | FLORENCE | 05 | CN10211 | This project involves the repaving of County Road 47 from State Highway 133 to County Road 320 and from County Road 37 to County Road 63 and also the repaving of JC Mauldin Highway from County Road 25 | Pavement Improvement | 2010-05-25 | 2010-06-09 | 2010-08-15 | 2010-08-02 | 617690 | 5.629
232 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | BIBB |  | 06 | CN10213 | This project invovles the traffic striping and sign replacement along various county roads in Bibb County | Safety/Traffic Management | 2010-05-25 | 2010-06-07 | 2010-07-30 | 2010-09-20 | 265000 | 71.000
233 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | MARSHALL |  | 04 | CN10214 | This project involves the repaving of Huntsville Road (County Road 414) from Short Creek Bridge ot State Highway 75 | Pavement Improvement | 2010-05-20 | 2010-06-17 | 2010-08-31 | 2010-08-20 | 68486.85 | 4.000
234 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | CN10215 | The replacement of the bridge with the identification number #2494 over Leslie Branch on Madison County Road 86 (Love Branch Road) near the City of Huntsville, Alabama. | Pavement Improvement | 2010-05-27 | 2010-07-01 | 2010-10-01 |  | 425509.94 | 0.216
235 | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | 03 | CN10216 | This project contains two sites listed as follows: Site #1: The repaving of Montgomery County Road 24 known as Cloverdale/Federal Rd. from the Lowndes County Line to US Route 31/Alabama Route 3. Site | Pavement Improvement | 2010-05-13 | 2010-05-28 | 2010-08-27 | 2010-09-15 | 530000 | 8.020
236 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CLEBURNE |  | 03 | CN10217 | This project contains two sites listed as follows: Site #1 :The widening and repaving of Cleburne County Road 34 from US Route 431/ Alabama Route 1 to County Road 13. Site #2: The widening and repa | Pavement Improvement | 2010-05-27 | 2010-06-10 | 2010-09-09 | 2012-01-04 | 265000 | 3.209
237 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | CN10900 | This project involves the repaving at three different sites in Sheffield. Site #1 is the repaving of Old Jackson Highway from the Tuscumbia city limits to South Montgomery Avenue. Site #2 is South M | Pavement Improvement | 2010-04-28 | 2010-06-04 | 2010-08-15 | 2010-08-19 | 306788.32 | 1.770
238 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | CN10901 | The project involves the restriping of Dead Lake Road from US Highway 43 to Interstate 65 and Radcliff Road from US Highwya 43 to one mile west of Creola city limit | Pavement Improvement | 2010-05-06 | 2010-05-24 | 2010-06-30 | 2010-07-06 | 51304 | 3.550
239 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | CN10902 | This project involves the installation of LED traiffc and pedestrian signals at various intersections in the city of Mobile | Safety/Traffic Management | 2010-04-22 | 2010-08-30 | 2010-12-11 | 2011-06-30 | 911640 | 0.000
240 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | CN10903 | This project involves the repaving of Gusmus Aveneue from 2nd Street (State Highway 184) to Avalon Avenue, South Broadway Avenue from West 6th Street (County Road 24) to Avalon Avenue and West 6th Str | Pavement Improvement | 2010-04-27 | 2010-05-12 | 2010-08-15 | 2010-08-03 | 307214.76 | 2.500
241 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | CN10905 | This project involves the repaving and striping of portions of Danville Road from Chapel Hill Road to 2nd Street Southwest in the city of Decatur | Pavement Improvement | 2010-04-13 | 2010-05-03 | 2010-07-01 | 2010-12-06 | 382187.6 | 1.906
242 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | CN10906 | This project involves the repaving of 8th Street Southeast from 16th Avenue to Point Mallard Drive and Pont Mallard Drive to Point Mallard Circle in the city of Decatur | Pavement Improvement | 2010-04-29 | 2010-05-14 | 2010-07-01 | 2010-12-06 | 429002.6 | 2.043
243 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | CN10907 | This project involves the repaving and striping of Country Club Road from State Highway 67 to Somerville Road in the city of Decatur | Pavement Improvement | 2010-04-14 | 2010-06-07 | 2010-08-15 | 2010-12-06 | 154393.25 | 1.080
244 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | CN10909 | This project involves the repaving of various eligible roads in the city of Auburn | Pavement Improvement | 2010-05-26 | 2010-06-16 | 2010-09-30 | 2011-02-09 | 1247027.47 | 0.000
245 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | CN10915 | This project involves the purchase of 2 vans for the Association of Retarded Citizens | Other | 2009-10-21 | 2009-10-21 | 2010-10-01 | 2012-03-16 | 67860 | 0.000
246 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | CN10916 | This project involves sidewalk improvements along State Highway 188 from Alba School to Arnett Street | Transportation Enhancements | 2010-05-06 | 2010-06-02 | 2010-07-15 |  | 125000 | 1.000
247 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | CN10917 | This project involves the repaving of various eligible roads in the city of Opelika | Pavement Improvement | 2010-07-27 | 2010-08-11 | 2010-10-12 | 2011-10-27 | 832465.57 | 0.000
248 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | CN10918 | This project involves the repaving of North Main Street from 3rd Street to Sheffield city limit and repaving North Cave Street from East Hobson Street to West North Commons Street | Pavement Improvement | 2010-04-28 | 2010-05-13 | 2010-07-20 | 2010-07-20 | 304347.29 | 1.200
249 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE | FLORENCE | 05 | CN10919 | This project involves the repaving of Hermitage Drive from Royla Avenue to Helton Drive and North Pine Street from North Wood Avenue to Kenneth Court and South Pine Street from West Alabama Street to | Pavement Improvement | 2010-04-27 | 2010-05-13 | 2010-08-15 | 2010-08-06 | 448064.17 | 0.820
250 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | CN10920 | This project involves the repaving of various eligilbe streets in the city of Huntsville | Pavement Improvement | 2010-04-13 | 2010-05-07 | 2010-09-21 | 2010-10-20 | 2552451.47 | 0.000
251 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | CN10921 | This project involves the repaving of various eligilbe streets in the city of Huntsville | Pavement Improvement | 2010-05-13 | 2010-06-01 | 2010-10-31 | 2010-10-20 | 1665827.53 | 0.000
252 | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | CN10922 | REVITALIZATION ALONG SR-215 (GREENSBORO AVENUE) FROM 15TH STREET TO HARGROVE ROAD | Pavement Improvement | 2010-12-07 |  |  |  | 1725290
253 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 05 | CN10923 | Repaving of Morgan County Route 103 also known as Hayes Street from US Route 31/Alabama Route 3 to Karl Prince Rd. and the repaving of Sparkman Street from Karl Prince Rd. to US Route 31/Alabama Rout | Pavement Improvement | 2010-06-02 | 2010-06-28 | 2010-08-25 | 2010-09-21 | 253153.61 | 2.321
254 | Completed | C950 | Ferryboat | ALABAMA | WILCOX |  | 07 | CN10928 | ARRA FERRY BOAT DISCRETIONARY - GEES BEND FERRY TERMINAL FACILITIES, ARRA FUNDED | Other | 2011-01-19 |  |  | 2011-12-16 | 1265800
255 | Underway | C200,C240 | Highway Infrastructure Investment Grant | ALABAMA | ST CLAIR |  | 06 | I020324 | "This project will convert an existing 4 lane section of interstate to a 6 lane. The completion of this project will tie an existing 6 lane interstate immediately east and immediately west of the pro | Pavement Widening | 2009-09-25 | 2009-10-13 | 2012-10-01 |  | 72524929.49 | 7.870
256 | Underway | C240 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH | GADSDEN | 04 | I059342 | Reconstructs a portion of existing concrete Interstate 59 near Gadsden by placing a layer of asphalt on the existing roadway and then placing an 11 inch layer of concrete pavement on the asphalt layer | Pavement Improvement | 2009-05-14 | 2009-07-09 | 2010-06-15 |  | 47525423.51 | 10.913
257 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | PE09906 | "This project includes improvements to four different repaving sites in Sheffield | Other | 2009-07-01 | 2009-08-17 | 2010-02-01 | 2010-01-14 | 2056.88 | 2.170
258 | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | PE09907 | This project involves the adjustment of signal time of various traffic signals in the city of Mobile in order to improve traffic flow | Other | 2009-07-07 | 2009-10-01 | 2010-10-01 |  | 154451.16 | 0.000
259 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | PE09908 | This project involves the repaving at three different sites in Muscle Shoals. Site #1 is a mile of repaving of Gusmus Avenue between 2nd Street and Avalon Avenue. Site #2 is 1 mile of South Broadway A | Other | 2009-07-07 | 2009-07-07 | 2010-02-01 | 2010-01-15 | 1630.44 | 2.500
260 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | PE09909 | This project involves the repaving various streets in the city of Huntsville | Other | 2009-07-07 | 2009-07-09 | 2010-02-01 | 2010-06-10 | 64974 | 0.000
261 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | PE09910 | This project involves the repaving various streets in the city of Huntsville | Other | 2009-07-07 | 2009-07-09 | 2011-12-01 | 2010-06-10 | 150726 | 0.000
262 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | PE09911 | "This project involves the restriping Mobile County Road 917 (Dead Lake Road) from U.S. Highway 43 to Interstate 65 and Mobile County Road 933 (Radcliff Road from U.S. Highway 43 to the Creola | Other | 2009-07-22 | 2009-07-31 | 2010-02-01 | 2010-01-31 | 15000 | 3.550
263 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE | FLORENCE | 05 | PE09912 | This project involves the repaving at three differenct sites in Florence. Site #1 is the repaving of about a 1 mile section of Hermitage Drive from Royal Avenue to Helton Drive. Site # 2 is the repa | Other | 2009-07-20 | 2009-08-02 | 2010-02-01 | 2010-01-15 | 26745.69 | 0.820
264 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | PE09913 | This project involves the repaving of 8th Street SE from 16th Avenue to Point Mallard Drive and Point Mallard Drive to Point Mallard Circle in the city of Decatur | Other | 2009-07-17 | 2009-07-18 | 2010-02-01 | 2010-06-10 | 1191.4 | 2.180
265 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | PE09914 | "This project involves the repaving of Country Club Road from Alabama State Highway 67 to Somerville Road in Decatur | Other | 2009-07-17 | 2010-06-07 | 2010-02-01 | 2010-06-10 | 831.46 | 1.080
266 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | PE09915 | "This project involves the repaving of approximately 4 miles of Morgan County Road 41 (Danville Road) from Morgan County Road 191 (Chapel Hill Rd.) to 2nd Street SW in Decatur | Other | 2009-07-17 | 2009-07-18 | 2010-02-01 | 2010-06-10 | 1570.4 | 1.970
267 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 05 | PE09916 | This project involves the repaving of Hayes Street from US Highway 31 to Karl Prince Road and the repaving of Sparkman Street from Karl Prince Road to US Highway 31 in the town of Hartselle | Other | 2009-07-31 | 2009-07-31 | 2010-02-01 | 2010-06-10 | 10398.36 | 2.400
268 | Underway | C950 | Ferryboat | ALABAMA | WILCOX |  | 07 | PE10906 | This project involves improvements to the Gees Bend Ferry Terminal Facility | Other | 2009-12-08 | 2010-04-12 | 2010-10-01 |  | 153200 | 0.000
269 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | PE10907 | This project involves the repaving of various eligible roads in the city of Opelika | Other | 2009-12-16 | 2009-12-16 | 2010-02-01 | 2010-02-26 | 1117.43 | 0.000
270 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | PE10908 | This project involves the repaving of various eligible roads in the city of Auburn | Other | 2009-12-16 | 2009-12-16 | 2010-02-01 | 2010-02-26 | 3347.53 | 0.000
271 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | PE10909 | This project involves the repaving of North Main Street from 3rd Street to Sheffield city limit and repaving North Cave Street from East Hobson Street to West North Commons Street | Other | 2009-12-07 | 2009-12-07 | 2010-02-01 | 2010-02-26 | 701.93 | 1.200
272 | Underway | C490 | OJT/SS | ALABAMA | STATEWIDE |  |  | SP10904 | This project is to provide funding for an internship for juniors and seniors for careers in the surface transportation industry as provided for by Alabama State University OJT/SS Program. | Other | 2010-05-14 |  | 2011-12-30 |  | 269658
273 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | CRENSHAW |  | 02 | TE09900 | This project will add sidewalks to Emment Avenue, Fulton Avenue, U.S. Highway 331 and Sasser Street in Brantley, Alabama in Crenshaw County. | Transportation Enhancements | 2010-01-13 | 2010-02-01 |  | 2010-06-25 | 250090.5 | 0.900
274 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | FRANKLIN |  | 04 | TE09901 | This project will add sidewalks to Jackson Avenue in downtown Russelleville, Alabama in Franklin County. | Transportation Enhancements | 2010-02-09 | 2010-02-23 | 2010-08-15 | 2010-07-27 | 400960 | 0.570
275 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | TE09902 | This project will add sidewalks along Alabama Avenue, 18th Street and 19th Street in downtown Jasper, Alabama in Walker County. | Transportation Enhancements | 2010-06-14 | 2010-06-14 | 2010-11-24 | 2011-05-31 | 366520 | 0.460
276 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | COFFEE |  | 02 | TE09903 | This project will add streetscaping to U.S. Highway 84 (Main Street) in downtown Enterprise, Alabama in Coffee County. This is Phase III of the project. | Transportation Enhancements | 2010-06-12 | 2010-06-28 | 2010-11-30 | 2011-02-11 | 860505 | 0.250
277 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | TE09904 | This project will add sidewalks along Alco Drive, U.S. Highway 31 and Persimmon Street in downtown Brewton, Alabama in Escambia County. | Transportation Enhancements | 2010-06-01 | 2010-06-14 | 2010-09-30 | 2010-11-22 | 290962.25 | 1.750
278 | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | TE09905 | This project involves the additon of sidewalks to Presley Street, Pine Street, Ashley Street, Carver Stree and Alabama State Highway Route 21 in Atmore, Alabama in Covington County. | Transportation Enhancements | 2010-07-20 | 2010-07-22 | 2010-11-19 |  | 468338 | 1.960
279 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | COVINGTON |  | 02 | TE09906 | "This project involves streetscaping along Alabama State Highway Route 55 (Main Street) in Florala | Transportation Enhancements | 2010-03-24 | 2010-04-08 | 2010-08-01 | 2011-10-19 | 317164 | 0.100
280 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | TE09907 | "This project involves the addtion of a sidewalk on University Blvd. from the University Church of Christ to Zeigler Interchange in Mobile | Transportation Enhancements | 2010-02-08 | 2010-03-01 | 2010-05-08 | 2010-03-31 | 62042 | 0.320
281 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | TE09908 | "This project involves the addition of sidewalks along approximately 1 mile of South Mount Pleasant Avenue from Murdock Street to Eagle Point Apartments in Monroeville | Transportation Enhancements | 2010-03-08 | 2010-03-08 |  | 2010-03-31 | 163200 | 0.780
282 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | TE09909 | "This project involves the paving of 2 gravel section of the Hugh Branyon Backcountry Trail | Transportation Enhancements | 2010-04-19 | 2010-04-26 | 2010-08-24 | 2011-11-30 | 296369 | 2.250
283 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | TE09910 | "This project will provide a pedestrian connection called the Amber Isle Connection to the Hugh S. Branyon Backcountry Trail in Orange Beach | Transportation Enhancements | 2010-05-06 | 2010-09-24 | 2010-09-24 | 2011-06-06 | 277138 | 0.290
284 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | TE09911 | This project, located in Baldwin County, Alabama, involves the addition of a sidewalk along Alabama State Highway Route 104 with the purpose to connect the Downtown Area of Silverhill, Alabama with th | Transportation Enhancements | 2010-06-15 | 2010-06-15 | 2010-10-29 | 2011-02-14 | 385314.45 | 0.680
285 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | TE09912 | Place Landscaping along Alabama State Route 119 in front of the American Village, in Montevallo, Shelby County, Alabama | Transportation Enhancements | 2010-03-29 | 2010-04-01 | 2010-07-29 | 2010-08-17 | 376918.88 | 0.640
286 | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | TE09913 | Create enhancements to the online Geographical Information System (GIS) computer Tools for research and planning located at 13075 Moundville Archaeological Park in Moundville, | Other | 2009-11-03 | 2009-11-11 | 2012-11-02 |  | 138650 | 0.000
287 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON |  | 02 | TE09914 | "This project involves streetscaping along Alabama Highway 53 in the Downtown Commercial District of Cottonwood | Transportation Enhancements | 2010-10-08 | 2010-11-01 | 2011-02-25 | 2011-10-03 | 292284.58 | 0.640
288 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | TE09915 | "This project involves adding sidewalks to the east side Lowndes County Road 29 in Lowndesboro | Transportation Enhancements | 2010-02-19 | 2010-02-22 | 2010-06-16 | 2010-06-22 | 220000 | 0.690
289 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | COVINGTON |  | 02 | TE09916 | "This project involves streetscaping (Phase III) of Main Street in Opp | Transportation Enhancements | 2010-06-15 | 2010-06-28 | 2010-11-15 | 2011-01-25 | 309332 | 0.190
290 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | TE09917 | "This project involves streetscaping for 3rd Avenue in Downtown Hartford | Transportation Enhancements | 2010-08-31 | 2010-09-14 | 2010-12-30 | 2011-03-14 | 276851.58 | 0.360
291 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | TE09918 | "This project involves streetscaping (Phase II) along Alabama Highway 27 (Commerce Street) in Geneva | Transportation Enhancements | 2010-07-19 | 2010-08-03 | 2010-11-30 | 2011-02-24 | 539053 | 0.240
292 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | TE09919 | "This project involves downtown streetscape improvements for Broad Street and Merrick Street in Ozark | Transportation Enhancements | 2010-07-08 | 2010-09-09 | 2011-01-19 | 2011-02-28 | 356387 | 0.090
293 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL |  | 03 | TE09920 | "This project involves streetscaping along Main Street in Downtown Hurtsboro | Transportation Enhancements | 2010-06-07 | 2010-06-07 | 2010-11-09 | 2011-04-15 | 100000 | 0.150
294 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | CONECUH |  | 02 | TE09921 | "This project will provide pedestrian improvements along Magnolia Avenue | Transportation Enhancements | 2010-03-22 | 2010-03-23 | 2010-09-30 | 2011-03-15 | 486528.61 | 2.080
295 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | TE09922 | Widen Watkins Creek Bridge for Pedestrians in the City of Mountain Brook, Alabama on Watkins Bridge Road in Jefferson County, Alabama. | Transportation Enhancements | 2010-08-23 | 2010-08-30 | 2010-12-20 | 2011-07-01 | 282000 | 0.020
296 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | TE09923 | "This project will add sidewalks along Parrish Jasper Road from First Street to Parrish Elementary School in the old downtown area of Parrish | Transportation Enhancements | 2010-06-04 | 2010-06-21 | 2010-11-17 | 2011-03-30 | 330220 | 0.490
297 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH | GADSDEN | 04 | TE09924 | "This project will landscape approximately 1.7 miles of U.S. Highway 431 from Keysburg Road to Bank Street in Glencoe | Transportation Enhancements | 2010-06-02 | 2010-06-02 | 2010-10-31 | 2010-10-01 | 160500 | 1.490
298 | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | STATEWIDE |  |  | TE09925 | This projects will conduct an Archaeological Survey of the Old Federal Road Statewide to be done byt the University of South Alabama. This project is a research project and is located at the Universi | Other | 2010-01-20 | 2010-02-15 | 2010-10-22 |  | 48526 | 0.000
299 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | TE09926 | Repave Chief Ladiga Trail in the City of Jacksonville, Alabama parallel and adjacent to Alabama Route 21 for 7.1 miles in Calhoun County, Alabama. | Transportation Enhancements | 2010-06-28 | 2010-09-08 | 2010-09-27 | 2011-08-31 | 254030 | 8.100
300 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN |  | 05 | TE09927 | "This project involves a Historic Downtown Sidewalk and Canopy Restoration for Hartselle | Transportation Enhancements | 2010-02-17 | 2010-02-22 | 2010-11-22 | 2010-10-29 | 457940 | 0.240
301 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BUTLER |  | 02 | TE09928 | "This project involves the addition of sidewalks on U.S. Highway 31 in Georgiana | Transportation Enhancements | 2010-03-15 | 2010-03-15 | 2010-05-04 | 2010-07-20 | 204000 | 0.850
302 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | DE KALB |  | 04 | TE09929 | "This project involves the addition of sidewalks on Alabama Higway 68 in Crossville | Transportation Enhancements | 2010-03-12 | 2010-04-16 | 2010-10-31 | 2010-11-09 | 331700 | 1.820
303 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | TE09930 | "This project involves the addition of sidewalks on Alabama Higway 97 in Hayneville | Transportation Enhancements | 2010-05-07 | 2010-06-04 | 2010-07-29 | 2012-01-07 | 155000 | 1.000
304 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | TE09931 | "This project involves streetscaping approximately x miles of West Slocomb Street- Phase II in Slocumb | Transportation Enhancements | 2010-07-21 | 2010-09-07 | 2010-10-30 | 2011-01-26 | 190000 | 0.060
305 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BIBB |  | 06 | TE09932 | "This project will add sidewalks along Alabama Highway 25 from Creekview Lane to Cooper Avenue in Brent | Transportation Enhancements | 2010-07-14 | 2010-07-26 | 2010-11-10 | 2011-04-18 | 393924.45 | 1.330
306 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | TE09933 | Construct Project AL 204 Sidewalk- Phase II at Jacksonville State University in Jacksonville, AL. along Alabama Route 204 in Calhoun County, Alabama. | Transportation Enhancements | 2010-03-12 | 2010-04-01 | 2010-05-14 | 2010-05-19 | 77038 | 0.250
307 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE | MONTGOMERY | 02 | TE09934 | Construct sidewalks along the southern side of Chapman Rd. from the intesection of Chapman Road & Main Street East to the Millbrook City School, in Elmore County, Alabama. | Transportation Enhancements | 2010-06-18 | 2010-08-19 | 2010-09-08 | 2011-03-18 | 99475 | 0.380
308 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | TE09935 | This project will add sidewalks to approximately 2 miles of U.S. Highway 43 (Saraland Blvd. N.) from Cleveland Road North to 225 Saraland Blvd. N. ) | Transportation Enhancements | 2010-05-11 | 2010-06-07 | 2010-10-30 | 2010-12-15 | 284643.5 | 1.200
309 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | TALLADEGA |  | 03 | TE09936 | This project will add sidewalks to several streets in Linoln, Alabama. Talladega County. The sidewalks will be located along Lock 4 Road to McLain Street and Magnolia Street. | Transportation Enhancements | 2010-09-22 | 2010-10-06 | 2010-12-31 | 2011-04-30 | 147357.6
310 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | PICKENS |  | 04 | TE09937 | "This project will add sidewalks along 5th Street NW and 2nd Avenue NW from 5th Street Northwest to 7th Street Northwest in Reform | Transportation Enhancements | 2010-04-22 | 2010-04-26 | 2010-06-25 | 2010-08-05 | 134066 | 0.450
311 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | GREENE |  | 07 | TE09938 | "This project will add sidewalks along the north side of West End Avenue beginning ath te Elmwood Manor Apartments and proceeding East to US Highwyay 11 in Eutaw | Transportation Enhancements | 2010-08-18 | 2010-08-31 | 2010-11-28 | 2011-06-01 | 458750 | 0.770
312 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | TE09939 | Construct Sidewqlks along Hillcrest High School Patriot Parkway from Remington Parkway to Old Marion Road in South Tucaloosa County, Alabama. | Transportation Enhancements | 2010-06-15 | 2010-06-28 | 2010-10-01 | 2010-09-30 | 379350.5 | 0.950
313 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | TE09940 | "This project will add a pedestrian connector between Alabama Southern Community College and Monroe County High School. This Project is located South of Agricultural Road and East of Veterans Drive in | Transportation Enhancements | 2010-04-27 | 2010-05-11 |  | 2010-10-20 | 387205 | 1.320
314 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | TALLAPOOSA |  | 03 | TE09941 | "This project will add sidewalks along the west side of K Street in Northeast Alexander City | Transportation Enhancements | 2010-06-24 | 2010-06-28 | 2010-10-31 | 2010-11-19 | 503515.98 | 0.550
315 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | TALLADEGA |  | 03 | TE09942 | "This Project involves streetscaping on Broadway Avenue from 3rd Street to 8th Street in Sylacauga | Transportation Enhancements | 2010-08-05 | 2010-08-10 | 2010-12-10 | 2012-01-13 | 410853.5 | 1.330
316 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | TE09943 | This project involves the construction of a sidewalk along South College Street from East University Drive to South Donahue Drive in the city of Auburn. | Transportation Enhancements | 2011-03-07 | 2011-03-21 |  | 2011-08-15 | 91900
317 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | TE09944 | Place Landscaping Enhancements on the Interchange of Interstate 65 and intesection U.S. Highway 31 in the City of Hoover, County of Jefferson, State of Alabama. | Transportation Enhancements | 2011-02-16 | 2011-02-16 | 2011-05-26 | 2011-05-26 | 399150 | 0.380
318 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | 03 | TE09945 | Place Landscaping along Alabama Route 271 known as Taylor Road at the Auburn University at Montgomery Campus Property Border with AL -271. | Transportation Enhancements | 2010-04-22 | 2010-05-01 | 2010-06-16 | 2010-05-10 | 12972 | 0.080
319 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | TE09946 | This Project involves streetscaping on Main Street in Louisville, Alabama. Barbour County | Transportation Enhancements | 2010-01-20 | 2010-02-15 | 2010-01-05 | 2010-05-19 | 214995 | 0.000
320 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT |  | 05 | TE09947 | GUSMUS AVENUE SIDEWALKS IN THE CITY OF MUSCLE SHOALS. THIS PROJECT IS LOCATED ON GUSMUS AVE. FROM THE INTERSECTION OF GUSMUS AVE. AND AVALON AVE. NORTH TO FLORENCE AVE. IN THE CITY OF MUSCLE SHOALS. | Transportation Enhancements | 2010-11-18 | 2010-12-03 | 2011-05-26 | 2011-08-02 | 525775
321 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON |  | 02 | TE09954 | This project involves the streetscape along South Maint Street from Church Street to North Street and small portions of Church Street and North Street in the town of Columbia. | Transportation Enhancements | 2011-02-03 | 2011-02-21 | 2011-05-17 | 2011-06-20 | 73355
322 | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | TE09955 | Construct sidewallks along both sides of Coaling Ridge Road and Stephens Loop Road in the Town of Coaling, Alabama. | Transportation Enhancements | 2010-06-08 | 2010-06-14 | 2010-12-04 | 2011-02-28 | 848963 | 0.000
323 | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | TE09960 | SIDWALKS ALONG OLD BIRMINGHAM HIGHWAY IN THE CITY OF SUMITON. THIS PROJECT IS LOCATED ALONG OLD BIRMINGHAM HIGHWAY IN THE CITY OF SUMITON. | Transportation Enhancements | 2011-12-12 | 2011-12-12 |  |  | 436000
324 | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | TE09961 | This project involves the construction of sidewalks along North Street and Cordova Street connecting the middle school to the high school in the city of Cordova. | Transportation Enhancements | 2011-12-05 | 2011-12-05 |  |  | 332400
325 | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | TE09973 | SIDWALKS ALONG AL 17 IN THE TOWN OF SILAS. THIS PROJECT IS LOCATED ALONG AL 17 IN THE TOWN OF SILAS CONNECTING THE DOWNTOWN AREA BY RUNNING ALONG SECOND AVENUE FROM FIRST STREET TO STATE ROUTE 17. | Transportation Enhancements | 2011-05-24 | 2011-05-25 |  |  | 20419.8
326 | Underway | C220,C240 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | TE09974 | Construct sidewalks along Ballpark Rd. from Bearden Rd. through Pelham Park to U.S.31 in the City of Pelham in Shelby County, Alabama | Transportation Enhancements | 2010-07-07 | 2010-09-07 | 2010-11-02 |  | 222265.11 | 0.000
327 | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MARSHALL |  | 04 | TE09985 | SIDEWALKS & PEDESTRIAN LIGHTING ALONG 2ND ST., 8TH AVENUE & 4TH STREET IN THE CITY OF ARAB. THIS PROJECT IS LOCATED ON 2ND. ST., 8TH AVE. & 4TH ST. IN THE CITY OF ARAB. | Transportation Enhancements | 2011-03-14 | 2011-03-14 | 2011-05-14 | 2011-06-28 | 236050
328 | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | Multiple | TR09900 | This project will provide new buses for the Clastran service area. Clastran is a bus system that covers areas in Jefferson and Shelby Counties not covered by the Birmingham transit system. | Other | 2009-09-22 | 2010-01-06 | 2010-09-01 | 2012-03-15 | 784030 | 0.000
329 | Completed | C220,C240 | Highway Infrastructure Investment Grant | ALASKA | DILLINGHAM |  |  | 0001260 | Reconstruct 2.8 miles of road from the intersection of Kanakanak Road and Wood River Road to the end of the road at Wood River Landing. Realign the road horizontally and vertically to create improved | Pavement Improvement | 2010-04-16 | 2010-04-17 | 2010-08-31 | 2011-09-11 | 12955259 | 2.800
330 | Completed | C230 | Highway Infrastructure Investment Grant | ALASKA | ANCHORAGE | ANCHORAGE |  | 0001359 | Increase capacity and improve safety by reconstructing a high-volume intersection at Tudor Road and Lake Otis Boulvard in Anchorage. In addition to dual left-turn lanes at all four corners of the int | Pavement Widening | 2010-04-07 | 2010-04-12 | 2010-10-30 | 2010-10-27 | 5000000 | 0.710
331 | Underway | C250 | Highway Infrastructure Investment Grant | ALASKA | NORTHWEST ARCTIC |  |  | 0002109 | This project will reconstruct and pave approximately 4,400 lineal feet of Shore Avenue between Lake Street and Crowley Dock Road and armor the tidewater side of the road with a combination of sheet pi | Pavement Improvement | 2009-06-17 | 2009-06-17 | 2011-10-01 |  | 6500000 | 1.077
332 | Completed | C250,C240 | Highway Infrastructure Investment Grant | ALASKA | YUKON-KOYUKUK |  |  | 0002178 | This project will upgrade and improve a 1.2-mile road between the City of Huslia and the recently-opened landfill. The project does not include realignments or widening, but will provide an improved | Pavement Improvement | 2010-09-07 | 2010-09-01 | 2011-08-31 | 2011-12-08 | 1917774 | 1.000
333 | Completed | C250,C240 | Highway Infrastructure Investment Grant | ALASKA | NOME |  |  | 0002185 | Construct drainage improvements and provide dust control on approximately 7,532 linear feet of roads within the City of Nome. The subgrade of the roads will be constructed to prepare for paving and | Pavement Improvement | 2010-06-21 | 2010-08-16 | 2011-07-31 | 2011-07-31 | 3588248 | 17.000
334 | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | SKAGWAY-HOONAH-ANGN |  |  | 0003053 | The project will construct a 1,300 foot, two-lane causeway connected to a 6,000 square-foot dock. A pontoon-supported, tidally-operated transfer bridge and ramp will provide roll-on/roll-off access fo | Bridge Improvement | 2009-04-16 | 2009-04-27 | 2011-05-15 | 2011-05-15 | 7700000 | 0.185
335 | Completed | C220 | Highway Infrastructure Investment Grant | ALASKA | VALDEZ - CORDOVA |  |  | 000S684 | The project will re-pave 7.1 miles of bike and pedestrian path alongside the Richardson Highway between Meals Avenue in downtown Valdez and River Road at the Robe River Subdivision, and improve its sa | Transportation Enhancements | 2009-07-24 | 2009-06-03 | 2010-07-15 | 2010-07-01 | 944038.12 | 7.600
336 | Completed | C250,C220 | Highway Infrastructure Investment Grant | ALASKA | VALDEZ - CORDOVA |  |  | 000S685 | Repave 0.95 miles of Blueberry Lake Road in Valdez at the access to the Blueberry Lake Campground. Pave 1,900 feet of roadway within the Blueberry Lake Campground. The project provides improved acce | Pavement Improvement | 2009-07-27 | 2009-06-03 | 2010-06-30 | 2010-06-18 | 912058.05 | 0.950
337 | Completed | C250,C240 | Highway Infrastructure Investment Grant | ALASKA | SOUTHEAST FAIRBANKS |  |  | 000S686 | This project will rehabilitate and resurface the Richardson Highway between MP 265-267 (Delta Junction area), to include its junction of the Alaska Highway and frontage roads. Work includes pulverizi | Pavement Improvement | 2010-05-15 | 2010-05-26 | 2010-09-30 | 2010-09-29 | 3262637.23 | 1.530
338 | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | KENAI PENINSULA |  |  | 0221054 | The project will resurface the driving lanes and shoulder of 16.75 miles of the Sterling Highway between Kalifornsky Beach Road and South Coho Loop Road in the Kenai Peninsula Borough. The project wi | Pavement Improvement | 2009-07-29 | 2009-05-26 | 2010-07-06 | 2010-07-15 | 6756419 | 17.000
339 | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | KODIAK ISLAND |  |  | 0391014 | Resurface 6.4 miles of urban roadway in the City of Kodiak. The project will include replacement of the waterproof membrane on the Buskin River bridge, paint striping, installation of pedestrian cros | Pavement Improvement | 2009-08-06 | 2009-06-02 | 2009-10-01 | 2009-10-08 | 6532387.48 | 6.950
340 | Completed | C230 | Highway Infrastructure Investment Grant | ALASKA | ANCHORAGE | ANCHORAGE |  | 0515004 | Resurface 1.837 miles of Jewel Lake Road from its intersection with Dimond Boulevard to its intersection with 63rd Avenue. Upgrade the collapsable, energy-absorbing ends of the guardrails to current | Pavement Improvement | 2010-05-14 | 2010-05-18 | 2010-07-31 | 2010-07-31 | 2280000 | 1.837
341 | Completed | C240,C230 | Highway Infrastructure Investment Grant | ALASKA | ANCHORAGE | ANCHORAGE |  | 0558007 | This 4.1-mile project will add 4-foot shoulders and new pavement, construct a paved pathway to connect existing pathways at South and North Birchwood Loop, construct a short truck-climbing lane just n | Pavement Improvement | 2010-04-19 | 2010-05-06 | 2011-09-01 | 2011-09-01 | 13059238 | 4.100
342 | Completed | C220 | Highway Infrastructure Investment Grant | ALASKA | VALDEZ - CORDOVA |  |  | 0750011 | This project will construct a new wayside in the vicinity of Milepost 7 of the Denali Highway. The project includes paved parking, a vault toilet,, litter barrel, table and bench. The project will r | Transportation Enhancements | 2009-09-03 | 2010-05-17 | 2010-07-15 | 2010-07-12 | 441283 | 0.000
343 | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | KETCHIKAN GATEWAY |  |  | 0902034 | This project is the second and final phase of structural rehabilitation and cathodic protection of the elevated Tongass Avenue viaduct in Ketchikan, Alaska. The scope of this project is to repair and | Bridge Improvement | 2010-01-21 | 2010-03-08 | 2011-03-23 | 2011-03-23 | 8591534 | 0.750
344 | Completed | C220 | Highway Infrastructure Investment Grant | ALASKA | KETCHIKAN GATEWAY |  |  | 0902035 | The project will widen and modify existing sidewalks for approximately 2,040 feet, from Chapmen Street to the existing Viaduct Tunnel to improve pedestrian capacity and safety and achieve Americans wi | Transportation Enhancements | 2010-05-12 | 2010-06-05 | 2011-05-01 | 2011-01-13 | 2151911 | 0.360
345 | Completed | C250 | Highway Infrastructure Investment Grant | ALASKA | SKAGWAY-HOONAH-ANGN |  |  | 0918007 | This project will rehabilitate 2.2 miles of road in the City of Hoonah linking the city airport and the state ferry terminal. The rehabilitated road will reduce maintenance efforts, improve ride qual | Pavement Improvement | 2010-01-07 | 2010-04-05 | 2010-09-23 | 2010-09-23 | 2016951 | 2.200
346 | Underway | C950 | Ferryboat | ALASKA | SKAGWAY-HOONAH-ANGN |  |  | 0918009 | The project will include removal and replacement of four or five mooring dolphins, installation of access gangways to two of the mooring dolphins nearest to the bridge float and replacement of the ste | Other | 2010-09-22 | 2011-06-15 | 2011-12-31 |  | 3059507 | 0.000
347 | Underway | C240 | Highway Infrastructure Investment Grant | ALASKA | KETCHIKAN GATEWAY |  |  | 0920025 | The project will reconstruct the highway for approximately two miles to provide a paved width of 36' including 12-foot driving lanes and 6-foot shoulders, from the first junction with D-1 Loop Road to | Pavement Improvement | 2010-04-06 | 2010-05-03 | 2011-06-30 |  | 10014923 | 2.100
348 | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | JUNEAU |  |  | 0933027 | This project will widen and straighten Glacier Highway to a paved width of 30 feet for 4.6 miles between the Amalga Harbor Road and the kayak launch at Eagle Beach. The project will include culvert r | Pavement Improvement | 2009-07-23 | 2009-05-27 | 2010-12-01 | 2010-11-04 | 11273789 | 4.597
349 | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | JUNEAU |  |  | 0933036 | The project will rehabilitate and resurface 4.52 miles of driving lanes on Glacier Highway in Juneau, between the Mendenhall Loop road and the Auke Bay Ferry Terminal, not including a segment between | Pavement Improvement | 2009-08-03 | 2009-05-27 | 2010-06-30 | 2010-09-20 | 3416667 | 4.474
350 | Completed | C250 | Highway Infrastructure Investment Grant | ALASKA | HAINES |  |  | 0956032 | This project will rebuild 0.59 miles of highway between the intersections of Front Street and Union Street including removal and replacement of asphalt, grading and adding material to the subgrade as | Pavement Improvement | 2009-08-12 | 2009-10-19 | 2011-05-26 | 2011-05-26 | 2175989 | 0.590
351 | Completed | C250 | Highway Infrastructure Investment Grant | ALASKA | SOUTHEAST FAIRBANKS |  |  | 0A11011 | This project will remove the existing truck weigh scale, scale house and associated utilities, and replace them with a new multi-platform scale and a scale house. Site work will include construction | New Construction | 2010-02-09 | 2010-02-23 | 2011-06-15 | 2011-12-05 | 3750000 | 0.000
352 | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | MATANUSKA-SUSITNA |  |  | 0A15026 | This project will resurface 5.8 miles of the Glenn Highway between mileposts 34-42 and replace or repair guardrails including the energy-absorbing, collapsable ends of the guardrails. The project wil | Pavement Improvement | 2009-07-16 | 2009-06-04 | 2009-10-01 | 2009-09-12 | 1812582.91 | 5.800
353 | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | MATANUSKA-SUSITNA | ANCHORAGE |  | 0A16039 | This project will resurface 15.188 miles of driving lanes, and all ramps and bridges, on the Glenn Highway between Hiland Road and Artillery Road interchanges. Replace or repair guardrails including | Pavement Improvement | 2009-06-12 | 2002-05-26 | 2009-10-01 | 2010-06-07 | 13318636 | 15.200
354 | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | MATANUSKA-SUSITNA |  |  | 0A16040 | This project will resurface 10.03 miles of the Glenn Highway including driving lanes, ramps, interchages and bridges between Mt. View Drive and the Hiland Interchange. Upgrade or replace guardrails i | Pavement Improvement | 2010-05-03 | 2010-05-06 | 2010-08-01 | 2011-06-29 | 11550500 | 10.030
355 | Underway | C240 | Highway Infrastructure Investment Grant | ALASKA | ANCHORAGE | ANCHORAGE |  | 0A16042 | This project will provide continuous highway lighting on the Glenn Highway for approximately 9.6 miles between the South Birchwood and Eklutna Interchanges. Lighting will consist of approximately 300 | Safety/Traffic Management | 2010-11-19 | 2010-11-19 | 2012-06-15 |  | 2034235 | 8.435
356 | Completed | C250,C220,C240 | Highway Infrastructure Investment Grant | ALASKA | MATANUSKA-SUSITNA |  |  | 0A41022 | Rehabilitate the driving surface and widen the shoulders of 11.1 miles of roadway on the Parks Highway between Willow Creek and the Kashwitna River including 3 passing zones for northbound traffic an | Pavement Improvement | 2009-10-20 | 2009-10-21 | 2011-09-30 | 2011-08-31 | 25175000 | 11.000
357 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | 008A204 | The Arizona Department of Transportation proposes to construct a Chain Link Fence project in Yuma County along I-8; US-95 (16th St) to Araby Rd in YUMA. | Other | 2009-10-08 | 2009-10-19 | 2010-02-08 | 2010-02-18 | 293156.27 | 5.396
358 | Underway | C250,C240 | Highway Infrastructure Investment Grant | ARIZONA | YUMA |  | 07 | 008A206 | The Arizona Department of Transportation proposes pavement preservation from the state line to Fortuna. | Pavement Improvement | 2011-01-25 | 2011-02-14 | 2011-08-01 |  | 14050623.07
359 | Completed | C200,C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 07 | 008B200 | The Arizona Department of Transportation proposes a pavement preservation project in Maricopa County, on I-8, from Milepost 121 to Big Horn, east of Gila Bend. | Pavement Improvement | 2010-07-08 | 2010-08-02 | 2011-02-28 | 2011-05-23 | 1358212 | 13.541
360 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | 010B205 | The Arizona Department of Transportation proposes to reconstruct a traffic interchange in Pima County along I-10, from Cienega Creek (milepost 288.4) to Marsh Station (milepost 290.5). Work will incl | Pavement Widening | 2009-07-27 | 2010-09-11 | 2011-02-15 | 2011-08-16 | 25135071 | 6.054
361 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PINAL |  | 01 | 010C203 | The Arizona Department of Transportation proposes a widen freeway project in Pinal County, on I-10, from I-8 to SR 87. | Pavement Improvement | 2010-06-29 | 2010-08-04 | 2012-01-04 | 2012-02-12 | 40735939 | 10.426
362 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PINAL |  | 01 | 010D204 | The Arizona Department of Transportation proposes to complete a freeway widening project in Pinal County along I-10 from the Town of Picacho to the Picacho Peak traffic interchange. Work will include | Pavement Improvement | 2009-07-29 | 2009-08-14 | 2010-09-10 | 2010-11-22 | 17294637.35 | 5.706
363 | Underway | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 07 | 010D206 | The Arizona Department of Transportation will construct an ITS Freeway Management System project in Pima County along Interstate 10 from milepost 250.2 to milepost 267.2 and along Interstate 19 toward | New Bridge Construction | 2010-01-28 | 2010-02-18 | 2011-03-24 |  | 4476412.62 | 5.378
364 | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | 010E201 | The Arizona Department of Transportation proposes to reconstruct a traffic interchange in Pima County along I-10, from Cienega Creek (milepost 288.4) to Marsh Station (milepost 290.5). Work will incl | Pavement Widening | 2009-07-27 | 2009-07-27 | 2010-12-30 |  | 10122297 | 0.519
365 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | 010E203 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Pima County along I-10, from Rita Rd to Houghton Rd east of TUCSON a total of 4 miles. | Pavement Improvement | 2009-07-08 | 2009-09-10 | 2009-12-24 | 2009-12-21 | 2840742.84 | 3.991
366 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | 010E204 | The Arizona Department of Transportation proposes to replace barbed wire fence in Pima County along I-10; from Vail Rd to Pima/Cochise County Line. | Other | 2009-10-05 | 2009-10-22 | 2010-01-28 | 2010-04-01 | 180294.57 | 16.785
367 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | 010E205 | The Arizona Department of Transportation proposes a pavement preservation project in Pima County, on I-10, from Houghton Rd to Mountain View TI, approximately 20 miles southeast of Tucson. | Pavement Improvement | 2010-06-03 | 2010-06-23 | 2010-10-13 | 2011-03-28 | 4994829 | 5.302
368 | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 07 | 010E206 | The Arizona Department of Transportation proposes a pavement preservation project in Pima County, on I-10, from Kino Parkway to Valencia Rd, in Tucson. | Pavement Improvement | 2010-12-06 | 2011-01-18 | 2011-08-06 |  | 6527200
369 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 010F201 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Cochise County along I-10 (EB), from East Benson to Johnson Rd (milepost 307.68 to milepost 321.60) to | Pavement Improvement | 2009-06-08 | 2009-07-06 | 2009-12-28 | 2010-01-26 | 6718114 | 13.705
370 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 010F203 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Cochise County along I-10 (east bound); from Luzena to Bowie. | Pavement Improvement | 2009-07-29 | 2009-08-24 | 2009-10-19 | 2010-01-12 | 1436353.09 | 4.909
371 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 03 | 017A207 | The Arizona Department of Transportation proposes to construct a Freeway Widening project in Maricopa County along I-17; SR-74 to Anthem Way in PHOENIX to include Major widening along 5 miles to provi | Pavement Widening | 2009-06-30 | 2009-08-05 | 2010-07-08 | 2010-09-27 | 14237477 | 4.831
372 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 02 | 017A210 | The Arizona Department of Transportation proposes to construct a Right-of-way fence replacement project in Maricopa County along Interstate 17 (South Bound); from Table Mesa Interchange to Rock Spring | Other | 2009-06-30 | 2009-07-29 | 2009-09-17 | 2009-12-16 | 95040.01 | 6.105
373 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | 017A211 | The Arizona Department of Transportation proposes a widen roadway project in Maricopa County within the City of Phoenix on SB I-17 beginning at the I-10 stack and extending to Indian School Road. | Pavement Widening | 2010-06-29 | 2010-07-21 | 2010-12-04 | 2010-12-14 | 1237799 | 0.015
374 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | SANTA CRUZ |  | 07 | 019A202 | The Arizona Department of Transportation proposes to replace barbed wire fence in Santa Cruz County along I-19; from Rio Rico Rd to Chaves Siding Road north of NOGALES. | Other | 2009-11-04 | 2010-11-16 | 2010-04-15 | 2010-11-24 | 371785 | 13.297
375 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | 040A208 | The Arizona Department of Transportation proposes to replace barb wire fence in Mohave County along Interstate 40; California State Line to Oatman Hwy Interchange to include Safety. | Other | 2009-08-28 | 2009-09-16 | 2009-12-16 | 2010-01-27 | 205684.07 | 44.328
376 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | 040B205 | The Arizona Department of Transportation proposes to construct a fence replacement project in Mohave County along Interstate 40; Railroad Ave to Rattlesnake Wash in Kingman, AZ, to include chain link | Other | 2009-06-23 | 2009-07-16 | 2009-11-23 | 2010-02-25 | 434779.89 | 4.148
377 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | 040C202 | The Arizona Department of Transportation proposes to replace barb wire fence in Coconino County along Interstate 40 from State Route 64 (milepost (MP) 166) to Volunteer Wash (MP 188). | Other | 2009-08-10 | 2009-08-24 | 2010-01-22 | 2010-10-29 | 428657.23 | 22.157
378 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | 040C203 | The Arizona Department of Transportation proposes to construct a pavement preservation project in Coconino County along Interstate 40 from milepost (MP) 150 to MP 190.8. | Pavement Improvement | 2009-08-04 | 2009-08-17 | 2009-09-21 | 2009-08-26 | 443353.34 | 41.121
379 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | 040D018 | The Arizona Department of Transportation proposes to reconstruct the roadway and alleviate steep grades in Coconino County along Interstate 40 westbound near Walnut Canyon (milepost 205) east of Flag | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2010-08-13 | 2010-08-19 | 6895251.87 | 0.073
380 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | APACHE |  | 01 | 040E201 | The Arizona Department of Transportation proposes to construct features that will protect the Dead River Bridge (Bridge #565) in Apache County along Interstate 40 (Eastbound) from the effects of high | Bridge Improvement | 2009-06-25 | 2009-07-07 | 2009-09-29 | 2009-10-05 | 133371.67 | 0.027
381 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | APACHE |  | 01 | 040E202 | The Arizona Department of Transportation proposes a bridge rehabilitation project in Apache County along Interstate 40 at the Black Creek west of Houck, AZ; project also includes high water protectiv | Bridge Improvement | 2009-06-08 | 2009-07-06 | 2009-10-19 | 2009-10-05 | 401053.08 | 0.036
382 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 02 | 060A204 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Maricopa County along US 60, from MP 107.6 to MP 110.2 in WICKENBURG to include Micro Seal. | Pavement Improvement | 2009-08-24 | 2009-10-12 | 2009-11-11 | 2010-07-08 | 333011.92 | 2.535
383 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | 060B200 | The proposed widen roadway project is located in Maricopa County within the City of Peoria on US 60. The project begins at MP 148.5 and extends to MP 150.3 for a total length of approximately 1.8 mil | Pavement Widening | 2009-06-03 | 2009-06-03 | 2010-12-13 | 2011-09-20 | 8046826.32 | 1.885
384 | Underway | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 060B201 | The Arizona Department of Transportation proposes to construct a Roadway Widening project in Maricopa County along US-60 (Grand Av); SR-303L to 99th Av to include Road Widening. | Pavement Widening | 2010-01-29 | 2010-01-22 | 2011-11-03 |  | 22612061 | 10.140
385 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PINAL | PHOENIX, AZ | Multiple | 060C201 | The Arizona Department of Transportation proposes to construct a Gateway graphics project in Pinal County along US 60 at Tomahawk Rd in APACHE JUNCTION (Graphics) to include Gateway graphics. | Transportation Enhancements | 2009-10-05 | 2009-11-19 | 2011-05-17 | 2010-09-22 | 345067.89 | 0.210
386 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PINAL | PHOENIX, AZ | Multiple | 060C202 | The Arizona Department of Transportation proposes to construct a Transportation Enhancement project in Pinal County along US-60 at Goldfield Rd in APACHE JUNCTION to include Gateway graphics. | Transportation Enhancements | 2009-10-05 | 2009-11-19 | 2011-05-17 | 2010-09-22 | 356311.81 | 0.235
387 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 060D201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along US-60, Miami City Limits to McMillan Wash. | Pavement Improvement | 2009-06-25 | 2009-08-05 | 2010-01-21 | 2010-10-18 | 10615546.44 | 8.250
388 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 060E202 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along US-60, from Timber Mountain (MP 278.8) to Seneca (MP 286.4). | Pavement Improvement | 2009-05-28 | 2009-07-13 | 2009-09-30 | 2009-10-14 | 3020674.22 | 6.822
389 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | YAVAPAI |  | 01 | 069A206 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Yavapai County along SR-69, I-17 to Big Bug Creek. | Pavement Improvement | 2009-06-10 | 2009-06-26 | 2009-09-03 | 2009-09-25 | 2295022.4 | 7.744
390 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GRAHAM |  | 01 | 070A202 | The Arizona Department of Transportation proposes to construct a traffic intersection improvement project in Graham County on US-70 @ 8th Avenue in SAFFORD to include pavement and signal improvements. | Pavement Improvement | 2009-08-03 | 2009-08-31 | 2009-10-26 | 2009-11-03 | 220664 | 0.159
391 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 073A200 | The Arizona Department of Transportation proposes to construct a Replace Barb Wire Fence project in Gila County along SR 73; Cedar Creek to Canyon Day to include Safety. | Other | 2009-09-08 | 2009-09-21 | 2010-02-24 | 2010-04-26 | 350214.61 | 11.420
392 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 02 | 074A200 | The Arizona Department of Transportation proposes to construct a Widen Roadway project in Maricopa County along SR-74; MP 19 - New River Rd to include new construction of passing lanes on both eastbou | Pavement Widening | 2009-11-02 | 2009-11-19 | 2010-06-27 | 2010-11-03 | 2730501 | 1.427
393 | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 02 | 074A201 | The Arizona Department of Transportation proposes a widen roadway project in Maricopa County on SR 74 from Milepost 14 to Milepost 16. | Pavement Widening | 2010-07-21 | 2010-08-18 | 2011-04-06 |  | 3603864 | 2.001
394 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | GREENLEE |  | 01 | 075A001 | The Arizona Department of Transportation proposes to construct a transportation enhancement project in Greenlee County along SR 75 in York Valley to include pathways, railings, and retaining walls. | Transportation Enhancements | 2009-10-27 | 2009-11-19 | 2010-03-18 | 2010-05-07 | 270508 | 0.510
395 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 080A201 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Cochise County along SR-80 through TOMBSTONE. | Pavement Improvement | 2009-06-30 | 2009-08-12 | 2009-10-21 | 2009-09-30 | 772285.57 | 0.962
396 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 080A202 | The Arizona Department of Transportation proposes to replace fence in Cochise County along SR-80; from Double Adobe Road to the Town of Douglas. | Other | 2009-06-16 | 2009-07-13 | 2009-12-21 | 2010-01-14 | 379660.6 | 14.000
397 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | SANTA CRUZ |  | 08 | 083A201 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Santa Cruz County along SR-83, near Sonoita from milepost 31.6 to milepost 43.5, a total of 11.9 miles. | Pavement Improvement | 2009-06-16 | 2009-07-06 | 2009-10-12 | 2011-11-19 | 2277274.63 | 10.293
398 | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 085B200 | The Arizona Department of Transportation proposes to construct a Widen Roadway project in Maricopa County along SR-85; Southern Ave to I-10. | Pavement Widening | 2009-10-06 | 2009-10-22 | 2010-11-26 | 2011-08-03 | 10147270.09 | 0.921
399 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 07 | 086A008 | The Arizona Department of Transportation proposes to construct a shoulder widening project in Pima County along SR-86 west Sells from milepost 73.9 to milepost 77.4. | Pavement Improvement | 2009-07-28 | 2009-09-10 | 2010-01-08 | 2010-07-29 | 2127459.61 | 3.680
400 | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 07 | 086A200 | The Arizona Department of Transportation proposes a widen roadway project in Pima County on SR 86 between milepost 141.1 and the Reservation Boundary, approximately 5 miles west of Robles Junction.? | Pavement Improvement | 2010-06-28 | 2010-07-23 | 2011-09-14 |  | 8512555 | 0.680
401 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 07 | 086A203 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Pima County along SR-86, from Kinney Road to La Cholla Blvd in TUCSON, a total of 3.1 miles. | Pavement Improvement | 2009-08-05 | 2009-08-27 | 2010-02-22 | 2010-10-07 | 2528446.98 | 3.164
402 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 07 | 086A204 | The Arizona Department of Transportation proposes to perform a bridge deck rehabilitation project in Pima County on SR-86 at the Santa Cruz River in TUCSON. Work will include repair of deteriorating | Bridge Improvement | 2009-07-08 | 2009-07-18 | 2009-08-28 | 2009-08-31 | 315844.72 | 0.049
403 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 07 | 086A205 | The Arizona Department of Transportation proposes to complete the widening of SR-86 in Pima County across Brawley Wash west of TUCSON from milepost 145.69 to milepost 148.3. | Pavement Improvement | 2009-08-03 | 2009-09-01 | 2010-02-16 | 2010-11-02 | 1622928.59 | 2.562
404 | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | 087B205 | The Arizona Department of Transportation proposes a reconstruct roadway project in Maricopa County within the Tonto National Forest on SR 87 between New Four Peaks Road and Dos S Ranch Road. | Pavement Widening | 2010-06-01 | 2010-06-24 | 2011-06-09 |  | 13389170 | 5.565
405 | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | 087B206 | The Arizona Department of Transportation proposes a reconstruct and repair roadway cut slopes project in Maricopa County within the Tonto National Forest on SR 87 between MP 211.8 and MP 213. | Pavement Improvement | 2010-06-01 | 2010-06-24 | 2011-06-09 |  | 1220985 | 1.235
406 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 087C002 | The Arizona Department of Transportation proposes to construct a Shoulder Widening project in Gila County along SR-87, PAYSON to PINE. | Pavement Improvement | 2009-05-22 | 2009-06-02 | 2009-12-29 | 2010-11-09 | 5275943.59 | 1.215
407 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 087C201 | The Arizona Department of Transportation proposes to construct a Replace Barb Wire Fence project in Gila County along SR 87; PAYSON to PINE. | Other | 2009-08-18 | 2009-09-01 | 2010-02-16 | 2010-04-29 | 435354.84 | 12.049
408 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO | FLAGSTAFF | 01 | 089C200 | The Arizona Department of Transportation proposes to construct a pavement preservation project in Coconino County along US 89; Townsend (milepost (MP) 420) to Fernwood (MP 426) north of Flagstaff, AZ. | Pavement Improvement | 2009-05-22 | 2009-06-22 | 2009-10-07 | 2009-10-20 | 4463750.62 | 5.119
409 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | 093B201 | The Arizona Department of Transportation proposes to construct new southbound travel lanes, creating a divided highway, in Mohave County along US 93, from milepost (MP) 104.1 to MP 106 (Ranch Rd Secti | New Construction | 2009-07-28 | 2009-08-05 | 2010-07-31 | 2011-05-23 | 7522497 | 2.055
410 | Underway | C220 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | 095A200 | The Arizona Department of Transportation proposes sidewalk, landscaping, irrigation, and pedestrian lighting work on Us 95 Somerton West Gateway Mp 12.36 - Mp 12.51. | Transportation Enhancements | 2011-01-03 | 2011-01-19 | 2011-04-27 |  | 185744.09
411 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | 095A201 | The Arizona Department of Transportation proposes to construct a widening project in Yuma County along US 95 (16th Street), I-8 to Palms Ave. | Pavement Widening | 2009-08-18 | 2009-09-08 | 2010-08-10 | 2011-04-07 | 10906523.66 | 0.709
412 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | LA PAZ |  | 07 | 095B200 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in La Paz County along US-95, from Peligro (MP 63) to Clarks (MP 80). | Pavement Improvement | 2009-09-28 | 2009-10-13 | 2010-04-27 | 2010-06-21 | 8175982 | 28.461
413 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | YUMA |  | 07 | 095B202 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Yuma County along US 95, from MP 44.3 to MP 312.7. | Pavement Improvement | 2009-08-24 | 2009-09-14 | 2009-11-09 | 2009-10-07 | 356808.84 | 9.652
414 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | LA PAZ |  | 07 | 095C203 | The Arizona Department of Transportation proposes to construct a Passing Lanes project in La Paz County along SR 95 South of Bouse Wash. | Pavement Improvement | 2009-06-30 | 2009-07-27 | 2009-10-29 | 2009-11-06 | 1655770 | 2.248
415 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | 0RV0201 | The Town of Oro Valley will perform a pavement preservation project on the following roadways: LaCholla, First, Lamber, Moor,Tan in the Town of Oro Valley. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-07-28 | 2010-07-13 | 1319759 | 0.894
416 | Underway | C250 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | 0RV0202 | The Town of Oro Valley will perform a pavement preservation project on Lacanada Dr. (Lambert Lane To Naranja Dr.) in the Town of Oro Valley. | Pavement Improvement | 2011-01-31 | 2011-02-23 | 2011-04-27 |  | 823000
417 | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 07 | 101A203 | The Arizona Department of Transportation proposes a widen roadway project in Maricopa County, on 99th Avenue between I-10 and Van Buren Street, within the Cities of Avondale and Tolleson. | Pavement Widening | 2010-06-28 | 2010-07-21 | 2011-01-12 | 2011-04-29 | 2141425
418 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 101A204 | The Arizona Department of Transportation proposes to widen Union Hills Road Traffic Interchange in Maricopa County along SR-101L (Aqua Fria Frwy) @ Beardsley Rd/Union Hills Dr in GLENDALE. | New Bridge Construction | 2009-10-26 | 2009-10-26 | 2012-01-01 | 2011-12-12 | 5167374 | 1.213
419 | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | 101A205 | The Arizona Department of Transportation proposes to construct an auxiliary lane project in Maricopa County, on SR 101L, eastbound between 51st Avenue and 35th Avenue within the City of Phoenix. | Pavement Improvement | 2010-05-13 | 2010-06-07 | 2011-03-04 | 2011-03-25 | 1674448 | 2.003
420 | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 101A206 | The Arizona Department of Transportation proposes to construct an auxiliary lane project in Maricopa County, on SR 101L, southbound between Northern Avenue and Grand Avenue within the City of Peoria. | Pavement Improvement | 2010-05-13 | 2010-06-07 | 2011-03-04 | 2011-03-25 | 2001026 | 2.807
421 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 101A207 | The Arizona Department of Transportation proposes an intersection improvement project in Maricopa County, within the City of Peoria on Olive Avenue at the intersection with Agua Fria Freeway (101L). | Pavement Widening | 2010-03-25 | 2010-04-21 | 2010-11-10 | 2011-12-12 | 2172403 | 0.358
422 | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | 143A200 | The Arizona Department of Transportation proposes a reconstruct traffic interchange project in Maricopa County, at the intersection of SR 143 and Sky Harbor Boulevard, within the City of Phoenix. | Pavement Widening | 2010-10-27 | 2010-12-02 | 2012-08-27 |  | 12190454.85
423 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | 160A001 | The Arizona Department of Transportation proposes a pavement preservation project in Coconino County along US 160, from the junction of US 89 and US 160 to Van's Trading Post; west of Tuba City, AZ - | Pavement Improvement | 2009-06-01 | 2009-06-11 | 2009-10-01 | 2009-09-18 | 3062945 | 8.124
424 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 160A200 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County along US 160, in Kayenta, AZ to Navajo Route 59 - 12.5 miles | Pavement Widening | 2009-05-26 | 2009-06-04 | 2009-12-31 | 2009-12-17 | 6338995.79 | 12.502
425 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 160B200 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County along US 160; from Navajo Route 59 to Dennehotso - 14 miles. | Pavement Improvement | 2009-05-26 | 2009-06-04 | 2009-12-31 | 2009-12-17 | 3187272.15 | 14.003
426 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 180B202 | The Arizona Department of Transportation proposes to replace barb wire fence in Navajo County along US 180, east of Holbrook, AZ; from milepost (MP) 307.3 to 324.9, near the Petrified Forest Road. | Other | 2009-08-05 | 2009-09-08 | 2010-03-22 | 2010-06-10 | 576439.86 | 17.393
427 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE | PHOENIX, AZ | 08 | 191A200 | The Arizona Department of Transportation proposes to construct an intersection improvement project in Cochise County along US-191 @ High Street in Sunsites (MP 48.36 to MP 48.94 to include Widen Roadw | Pavement Improvement | 2009-06-16 | 2009-07-20 | 2009-10-26 | 2009-11-25 | 484868.83 | 0.581
428 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | GRAHAM |  | 01 | 191B001 | The Arizona Department of Transportation proposes to construct a transportation enhancement project in Graham County along US 191 from Discovery Blvd. to Relations St. in the Town of Safford. Work wi | Transportation Enhancements | 2010-01-04 | 2010-01-25 | 2010-07-07 | 2010-06-04 | 357650.32 | 1.468
429 | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 191B200 | The Arizona Department of Transportation proposes to construct a parallel road project in Cochise County on US 191 from Dial Wash to Ten Ranch south of SAFFORD. | New Construction | 2010-06-30 | 2010-07-21 | 2011-08-01 |  | 7800624 | 5.636
430 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GREENLEE |  | 01 | 191C202 | The Arizona Department of Transportation proposes an intersection improvement project in Greenlee County along US 191 at Black Hills Rd (Back County Byway) at milepost 159.5. | Pavement Improvement | 2009-07-24 | 2010-09-15 | 2010-01-08 | 2010-04-08 | 790888.89 | 0.142
431 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GREENLEE |  | 01 | 191C203 | The Arizona Department of Transportation proposes to construct a drainage improvement project in Greenlee County along US-191 (Coronado Trail) at milepost 175 to include Lower Coronado Drainage Improv | Other | 2009-09-28 | 2009-10-19 | 2010-02-08 | 2010-07-12 | 373630.3 | 4.747
432 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | APACHE |  | 01 | 191E202 | The Arizona Department of Transportation proposes a pavement preservation project in Apache County along US 191, from milepost (MP) 427 to MP 436 south of Chinle, AZ. | Pavement Improvement | 2009-06-16 | 2009-07-23 | 2009-10-26 | 2009-10-29 | 2710391.11 | 8.381
433 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 260C003 | The Arizona Department of Transportation proposes to construct a Transportation Enhancement project in Navajo County along SR-260; Porter Mtn. Rd to Woodland Rd in PINETOP/LAKESIDE to include Pedestri | Other | 2009-10-28 | 2010-05-03 | 2010-05-06 | 2011-08-29 | 627151 | 0.389
434 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 277A201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Navajo County along SR 277, from MP 305.7 to 312.7. | Pavement Improvement | 2009-08-05 | 2009-08-10 | 2009-09-28 | 2009-09-28 | 315343.25 | 6.831
435 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | STATEWIDE |  |  | 999A238 | The Arizona Department of Transportation proposes to implement a Pavement Micro Seal project Statewide in various Counties in Southeast Arizona. | Pavement Improvement | 2009-08-24 | 2009-09-16 | 2009-12-09 | 2010-12-14 | 1037435.5 | 5.020
436 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | STATEWIDE |  |  | 999A239 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County at various locations. | Pavement Improvement | 2009-08-03 | 2009-08-19 | 2009-10-12 | 2010-10-19 | 662240.92 | 5.508
437 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 999A242 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along Globe District Chip Seals to include Chip Seal. | Pavement Improvement | 2009-07-29 | 2009-08-17 | 2009-10-05 | 2009-09-30 | 397464.4 | 7.284
438 | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | STATEWIDE |  |  | 999A244 | The Arizona Department of Transportation proposes to construct Pipe Liner Inserts (Relining) in VARIOUS Locations Statewide. | Other | 2010-01-05 | 2010-01-20 | 2010-09-01 | 2010-09-22 | 2092408.97 | 9.087
439 | Underway | C490 | OJT/SS | ARIZONA | STATEWIDE |  |  | 999M018 | The Arizona Department of Transportation will be supporting the On-The-Job Training, Support Services Program 2009--Pre-Apprenticeship In Highway Construction Program. | Other | 2010-10-01 | 2010-10-01 |  |  | 509883
440 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PINAL |  | 06 | APJ0200 | The City of Apache Junction, AZ will perform Pavement Preservation along Ironwood Drive from US 60 (Superstition Frwy) to Southern Ave. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-08-11 | 2011-03-30 | 1670913 | 0.773
441 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PINAL | PHOENIX, AZ | 06 | APJ0203 | The City of Apache Junction will perform pavement preservation at Ironwood Drive from 16Th Ave To Broadway Ave. | Pavement Improvement | 2010-11-29 | 2011-02-22 | 2011-08-09 | 2011-09-01 | 688800
442 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 07 | AVN0203 | The City of Avondale will construct an interim Traffic Operations Center. | Safety/Traffic Management | 2012-01-05 | 2012-01-18 | 2012-04-04 |  | 189292
443 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | AVN0206 | The City of Avondale will perform a Preliminary engineering, design and construction along Dysart Rd; I-10 to Indian School Rd in AVONDALE. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-07-05 | 2010-12-09 | 1836835.28 | 0.474
444 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | AVN0207 | The City of Avondale will perform a Preliminary engineering, design and construction for along Dysart Rd; Van Buren St to I-10 in AVONDALE. | Other | 2009-06-23 | 2009-06-23 | 2010-01-29 | 2010-02-23 | 48515 | 0.540
445 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | BKY0201 | The Town of Buckeye will pave shoulders at various locations: Mc-85/Monroe, Southern Ave, Apache Rd. | Pavement Improvement | 2011-03-10 | 2011-03-24 | 2011-05-03 | 2011-07-25 | 249835
446 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | BKY0202 | The Town of Buckeye will perform a Pre-engineering/Design and Pavement Rehabilitation and Preservation along Various Locations on Functionally Classified Roads in BUCKEYE. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-06-23 | 2011-01-27 | 1274037 | 0.992
447 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | BUL0200 | Bullhead City will perform a pavement preservation project of existing deteriorating asphalt pavement along Miracle Mile in Bullhead City, AZ. | Pavement Improvement | 2009-07-02 | 2009-07-02 | 2010-08-30 | 2010-10-08 | 511244 | 1.325
448 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | CCN0204 | The Coconino County will perform a pavement preservation along Lake Mary Road south of Flagstaff, AZ. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-10-27 | 2010-10-27 | 754012 | 0.000
449 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO | FLAGSTAFF | 01 | CCN0205 | The Coconino County will perform a pavement preservation project along State Route B40 (Old US 66), from I-40 to City Limits, west of Flagstaff, AZ. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-08-26 | 2010-08-18 | 855903 | 0.000
450 | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | CFE0201 | The Town of Carefree, AZ will perform Design and construction of repair and restoration of Cave Creek Road from Scopa Trail to Carefree Eastern Border. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2011-05-18 | 2010-12-01 | 588338 | 4.000
451 | Underway | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | CHN0014 | The City of Chandler, AZ will construct a Multi-Use Pathway along Paseo Road. | Transportation Enhancements | 2010-07-20 |  | 2011-03-23 |  | 893595 | 1.500
452 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | CHN0025 | The City of Chandler, AZ will perform Intersection and Capacity Improvement along Chandler Blvd at Dobson Rd, and on Dobson Rd from Chandler Blvd to Frye Rd. | Pavement Widening | 2009-08-24 | 2009-08-24 | 2011-02-04 | 2011-03-04 | 3949421 | 0.500
453 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | CHN0211 | The City of Chandler will perform Design and reconstruction of pavement along Price Road; Germann Road to Queen Creek Road in CHANDLER. | Pavement Improvement | 2009-06-30 | 2009-06-30 | 2011-04-25 |  | 2018178 | 1.000
454 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PINAL |  | 08 | CSG0200 | The City of Casa Grande will install intersection traffic signals at the following intersection Peart Road / McCartney Road and Peart Road / Korsten Road in Casa Grande. | Other | 2009-06-18 | 2009-06-18 | 2009-10-16 | 2010-01-11 | 17562 | 0.000
455 | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | CVK0201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project along Cave Creek Road from Spur Crossing to the Cave Creek Town Limits in CAVE CREEK, AZ. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2011-05-18 | 2010-11-09 | 614666.87 | 1.500
456 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | DGS0005 | The City of Douglas will perform a transportation enhancement project which will include a shared use pathway with ADA ramps over a railroad bridge along Paseo de la Amistad. | Transportation Enhancements | 2009-12-29 | 2010-02-01 | 2010-08-27 | 2011-04-10 | 537968.41 | 0.200
457 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | APACHE |  | 01 | EGR0200 | The City of Eager will perform a Pavement Preservation along Main Street; from US-60 to SR-260 in EAGER. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-07-24 | 2011-05-13 | 867092 | 1.600
458 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | ELM0202 | The City of El Mirage will perform a Pre-Engineer/Design and Mill and Replace Existing Pavement along Various Locations on Functionally Classified Roadways. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-09-01 | 2011-01-27 | 633600 | 1.500
459 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | ELM0203 | The City of El Mirage will micro-seal pavement surface - Cactus To Olive | Pavement Improvement | 2011-03-07 | 2011-03-24 | 2011-05-08 | 2011-07-07 | 167750
460 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO | FLAGSTAFF | 01 | FLA0006 | The City of Flagstaff will perform a improvements along State Route B40 in downtown Flagstaff, AZ; the project includes pathway and landscaping improvements. | Transportation Enhancements | 2009-09-14 | 2009-09-14 | 2010-06-11 | 2010-06-11 | 470119 | 0.000
461 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | FTH0006 | The City of Fountain Hills will construct a median, bike Lanes and perform pavement preservation from Shea Blvd, Fountain Hills Blvd To Saguaro Blvd. | Transportation Enhancements | 2011-04-06 | 2011-04-20 | 2011-08-03 |  | 1133610.5
462 | Completed | C250,C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GBD0200 | The City of Gila Bend will construct Pedestrian and Landscape Improvements along Various Locations along SR-85 (Pima St) in GILA BEND. | Transportation Enhancements | 2009-09-10 | 2009-09-10 | 2011-10-19 | 2011-10-04 | 244147 | 0.000
463 | Underway | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GBD0203 | The City of Gila Bend will design and construct a carpool lane and transit park & ride lot at the Gila Bend Airport on SR85. | Other | 2009-09-10 | 2009-09-10 | 2010-10-25 |  | 298862 | 0.000
464 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GDY0202 | The City of Goodyear will perform a Pre-Engineer/Design to mill, patch and replace pavement along Various Locations on Functionally Classified Roads in GOODYEAR. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-11-15 | 2010-11-15 | 655978.04 | 2.500
465 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | GGI0005 | The Gila County, will perform a Bridge Rehabilitation along Ice House, Bridge and Ice House Wash Bridge and Approaches in GLOBE. | Bridge Replacement | 2009-06-18 | 2009-06-18 | 2010-12-08 | 2011-05-06 | 1732990 | 0.000
466 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | GIL0012 | The City of Gilbert will construct a multi use path along the Eastern Canal: Guadalupe Rd To Elliot Rd (Santan Vista Trail Phase II). | Transportation Enhancements | 2011-03-02 | 2011-05-23 | 2011-08-31 |  | 939703
467 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | GIL0015 | The City of Gilbert will construct Pedestrian bridges across a major Canal within the City. | Transportation Enhancements | 2010-02-22 | 2009-12-14 | 2010-05-06 | 2010-06-30 | 270000 | 0.000
468 | Underway | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | GIL0202 | The City of Gilbert will construct Sidewalks, ADA Handicap Ramps, Landscaping & Irrigation in the Heritage District in Downtown GILBERT. | Transportation Enhancements | 2009-09-24 | 2009-08-25 | 2010-06-03 |  | 421847.85 | 1.300
469 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | GIL0203 | The City of Gilbert, AZ will perform Design and Construction of Chip Seal Overlays on various arterial roadways in GILBERT. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2011-05-18 | 2011-01-27 | 4363842 | 15.000
470 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | GLN0201 | The City of Glendale will perform a Pedestrian corridor enhancements along Old Roma Alley in GLENDALE. | Transportation Enhancements | 2010-03-01 | 2010-02-03 | 2010-06-13 | 2010-10-13 | 467549 | 0.100
471 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GLN0211 | The City of Glendale, will perform a Pre-Engineer/Design for pavement overlay along Glendale Ave; 51st Ave to 66th Ave in GLENDALE. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-09-26 | 2011-01-27 | 1677785 | 2.000
472 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0212 | The City of Glendale will perform a Pre-Engineer/Design and construct pavement surface treatment along Litchfield Rd; Missouri to Northern Ave in GLENDALE. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-11-04 | 2011-06-13 | 638966 | 2.000
473 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0214 | The City of Glendale will Install thermoplastic pavement markings along 25 Miles on Arterial Streets in GLENDALE. | Pavement Widening | 2009-06-12 | 2009-06-12 | 2011-11-22 | 2010-08-24 | 228002.37 | 25.000
474 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GLN0215 | The City of Glendale will install wireless communication devices along Camelback Rd from 47th Ave to 83rd Ave to improve communication with traffic signals. | Safety/Traffic Management | 2009-06-12 | 2009-06-12 | 2010-11-17 | 2010-10-29 | 197388 | 4.500
475 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0216 | The City of Glendale will install wireless communication devices along Bethany Home Rd from 63rd Ave to 83rd Ave to improve communication with traffic signals. | Other | 2009-06-23 | 2009-06-23 | 2010-05-21 | 2010-05-21 | 13332 | 2.500
476 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0217 | The City of Glendale will install CCTV cameras at various locations on their functionally classified roadways to improve traffic operations and management. | Other | 2009-06-23 | 2009-06-23 |  |  | 13282 | 0.000
477 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0218 | The City of Glendale will modernize traffic signals at various locations on functionally classified roadways to improve traffic operations and management. | Other | 2009-06-23 | 2009-06-23 |  |  | 13512 | 0.000
478 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GLN0219 | The City of Glendale will install new traffic signal cabinets and controllers at various locations on functionally classified roadways to improve traffic operations and management. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2011-06-22 | 2011-03-03 | 1251104 | 0.000
479 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | GLN0233 | The City of Glendale will perform pavement preservation on Bell Road - 59Th Ave To 70Th Ave. | Pavement Improvement | 2011-03-29 | 2011-04-20 | 2011-07-04 | 2011-07-15 | 1016837
480 | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GRI0200 | ADOT will perform Design and Construction of Pavement Rehab projects along Various Locations on Functionally Classified Roads within Gila River Indian Community. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-11-15 | 2010-11-15 | 548729 | 1.500
481 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | GUA0200 | The Town of Guadalupe AZ will perform Replacement of existing street lights to improve safety along Various Roadways in GUADALUPE, AZ | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-08-16 | 2010-11-03 | 598668.35 | 0.000
482 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | IT00200 | The Tohono O'odham Indian Reservation will perform a pavement preservation project along San Xavier Road from Mission to Los Reales on the Tohono O'odham Nation. | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-09-30 | 2010-11-30 | 1676996.84 | 0.000
483 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | IT00203 | The Tohono O'odham Indian Reservation will perform a pavement preservation project along Mission Road Bmp 11.3-13.8 on the Tohono O'odham Nation. | Pavement Improvement | 2011-03-28 | 2011-07-05 | 2011-04-11 | 2011-04-01 | 525000
484 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | KNG0202 | The City of Kingman will perform a pavement preservation project along Bank Street Kingman, AZ. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-09-29 | 2010-12-31 | 566339 | 0.500
485 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | LHV0003 | The Lake Havasu City will construct a shared use pathway along Magnolia Drive to Acoma Boulevard (Multi-Use Path) in Lake Havasu City, AZ. | Transportation Enhancements | 2009-08-11 | 2010-01-04 | 2010-05-04 | 2010-04-30 | 410114.89 | 0.500
486 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | LHV0200 | The Lake Havasu City will install traffic signals at the intersection of South Palo Verde and Acoma in Lake Havasu City, AZ. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-10-27 | 2010-11-24 | 205823 | 0.000
487 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | LA PAZ |  | 07 | LLA0201 | The LaPaz County will perform a Pavement Preservation project along Salome Road, from US 60 to MP 5.5. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-08-12 | 2010-09-17 | 600000 | 5.500
488 | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | LPK0201 | The City of Litchfield Park will perform a Pre-Engineer/Design to mill and replace pavement resurfacing/ reconstruction along Various Locations on Functionally Classified Roads in LITCHFIELD PARK. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2011-07-01 | 2011-12-12 | 485812 | 0.700
489 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | MES0021 | The City of Mesa, AZ will construct a Transportation Enhancement along Consolidated Canal Pathway in MESA to include Shared use pathway. | Transportation Enhancements | 2010-07-01 | 2011-02-02 | 2011-06-02 | 2011-06-02 | 665030.85 | 0.000
490 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | MES0206 | The City of Mesa will install fiber, cameras, detection, cabinets, and Controllers for ITS Signal Conversions - Phase 4A . | Safety/Traffic Management | 2011-03-28 |  |  | 2011-08-25 | 549334
491 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | MES0209 | The City of Mesa, AZ will perform Design and Construction of Pavement Preservation and Americans with Disabilities Act (ADA) upgrades along Various Roadways. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-07-28 | 2010-07-28 | 1006459 | 7.500
492 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | MES0210 | The City of Mesa, AZ will perform Design and construction of mill and replace pavement along Various Roadways. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-08-27 | 2010-08-27 | 1321487 | 3.500
493 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | MES0211 | The City of Mesa proposes a pavement preservation project and American with Disabilities Act upgrades in various locations in Mesa, AZ. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2011-02-03 | 2011-02-03 | 2375826 | 2.000
494 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | MES0212 | City of Mesa, AZ proposes a pavement preservation project and upgrades to the American with Disabilities Act features in various locations in Mesa, Arizona. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-07-01 | 2010-07-01 | 2015266 | 2.000
495 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | MES0213 | City of Mesa, AZ proposes a pavement preservation project with Americans with Disabilities Act improvements in various locations in Mesa, Arizona. | Pavement Improvement | 2009-08-06 | 2009-08-06 | 2010-09-15 | 2010-11-23 | 3516407 | 3.000
496 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | MM00001 | The Mohave County will construct a shared use pathway along the Mohave Wash Pathway (County) from Gordon Drive to Bank Street in Kingman, AZ. | Transportation Enhancements | 2009-11-20 | 2009-07-01 | 2010-08-17 | 2010-10-19 | 386219.78 | 0.000
497 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | MM00200 | The Mohave County will construct a shared use pathway along Mohave Wash Pathway (County) from Bank Street to Northern Avenue in Kingman, AZ. | Transportation Enhancements | 2009-11-20 | 2009-10-19 | 2010-04-20 | 2010-04-20 | 190744.33 | 0.600
498 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | MM00203 | The Mohave County will perform a pavement preservation project along Northern Avenue in Kingman, AZ. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-08-22 | 2011-02-16 | 535000 | 1.500
499 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 05 | MMA0201 | Maricopa County, AZ will construct Paved shoulders and add bike lanes along Bush Highway from Usery Pass Rd to Steward Mountain Rd northwest of MESA AZ. | Other | 2009-10-05 | 2009-10-05 | 2010-01-15 | 2010-01-15 | 552383.84 | 4.600
500 | Completed | C250,C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | MMA0210 | Maricopa County, will perform Pre-Engineer/Design and construct Asphalt Rubber Overlay along Various Locations on Functionally Classified Roadways in MARICOPA COUNTY. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2009-12-11 | 2010-12-02 | 6514280 | 31.100
501 | Underway | C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | MRN0202 | The City of Marana will perform various pavement preservation projects: Rattlesnake Pass (2.5 miles); Tangerine Road, I-10 to Thornydale Road; Moore Road, I-10 to Sandario Road; Sandario Road, Trico R | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-08-09 |  | 2769958 | 7.900
502 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | MRN0203 | The City of Marana will perform pavement preservation from I-10 (Sandario) to 1580 Linda Lane. | Pavement Improvement | 2011-03-02 | 2011-03-24 | 2011-05-26 | 2011-08-08 | 853100
503 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | NNA0200 | The Navajo County will perform a pavement preservation project along Bourdon Ranch Road from milepost (MP) 6.5 to MP 10.1 in Navajo County. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-09-02 | 2010-08-06 | 560883 | 3.500
504 | Completed | C250,C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PAS0201 | The Pascua Yaqui Tribe will perform a pavement preservation project along Calle Torim and Ignacio. | Pavement Improvement | 2009-07-14 | 2009-07-14 | 2010-07-29 | 2010-09-23 | 429013 | 2.600
505 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | PE00205 | Major Arterial mill, overlay and re-striping to 5 general purpose lanes and bike lanes along Beardsley Rd; Lake Pleasant Rd to 83rd Av in PEORIA. | Pavement Widening | 2009-06-08 | 2009-06-08 | 2010-11-18 | 2010-11-18 | 1822530.75 | 2.400
506 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | PE00206 | The City of Peoria will Widen the Beardsley Rd Connection: SR-101L (Agua Fria Fwy) to Beardsley Rd at 83rd Av/Lake Pleasant Pkwy in PEORIA, which will include Advance constructing the Beardsley Road | New Construction | 2009-06-08 | 2009-06-08 | 2011-04-15 | 2011-08-19 | 1471776 | 2.000
507 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0209 | The City of Phoenix, AZ will perform Design & Construction of Intersection Improvements along 7th St at McDowell Rd in PHOENIX. | Pavement Widening | 2009-07-01 | 2009-07-01 |  | 2010-06-18 | 99999 | 0.000
508 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0218 | The City of Phoenix will construct a multi use underpass 7Th Ave at the Cads Canal | Transportation Enhancements | 2011-04-04 | 2011-04-04 | 2011-10-31 |  | 900000
509 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0230 | The City of Phoenix, AZ will perform Design & Construction of Removal/Replacement of Existing Americans with Disabilities (ADA) Ramps or Construction of New ADA Ramps along Various Locations in PHOENI | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2010-11-13 | 2010-10-29 | 1361950 | 0.000
510 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0231 | The City of Phoenix, AZ will perform Design & Construction of Bridge Deck Rehabilitations along 11 Locations in PHOENIX. | Bridge Improvement | 2009-07-08 | 2009-07-08 | 2010-12-30 |  | 1623986 | 0.000
511 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0232 | The City of Phoenix, AZ will perform Design & Construction of Bridge Joint Rehabilitations along 6 Locations in PHOENIX. | Bridge Improvement | 2009-07-08 | 2009-07-08 | 2010-12-27 | 2010-12-22 | 678257 | 0.000
512 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0233 | The City of Phoenix will design, procure, and install CCTV along various corridors to improve traffic operations and management. | Safety/Traffic Management | 2009-07-08 | 2009-07-08 | 2010-07-14 |  | 755987 | 0.000
513 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0234 | The City of Phoenix will design, procure and install a fiber optic backbone system along various corridors to improve traffic operations and management. | Safety/Traffic Management | 2009-07-08 | 2009-07-08 | 2010-04-21 |  | 541743 | 0.000
514 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0235 | The City of Phoenix will design, procure, and install wireless communications devices along various corridors to improve communications facilitating better traffic operations and management. | Safety/Traffic Management | 2009-07-09 | 2009-07-09 | 2010-07-07 |  | 398461 | 0.000
515 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0236 | The City of Phoenix will perform an inventory, procure, and install traffic control signs along various corridors to aid in the control and management of traffic. | Safety/Traffic Management | 2009-07-09 | 2009-07-09 | 2011-08-26 |  | 2079819 | 0.000
516 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | PHX0237 | The City of Phoenix will perform a Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (North Area). | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-02-21 | 2011-01-27 | 6798216 | 16.000
517 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0238 | The City of Phoenix, will perform Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (Central Area). | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-02-21 | 2011-12-27 | 6716919 | 16.000
518 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0239 | The City of Phoenix, will perform Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (South Area). | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2010-12-06 | 2010-09-20 | 6797577 | 16.000
519 | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0261 | Pavement Preservation | Pavement Improvement | 2011-03-07 | 2011-03-07 | 2011-10-03 |  | 6683267
520 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0161 | The Pima County will perform a transportation enhancement project which consists of new paved shoulders, shared use driveway improvements, and access ramps near the Hohokam Middle School in Pima Count | Other | 2010-01-11 | 2010-01-11 | 2011-09-30 | 2010-12-31 | 419146.96 | 1.000
521 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0214 | The Pima County will perform pavement preservation projects in various locations throughout Pima County. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2011-09-30 | 2010-05-21 | 1264640.26 | 0.000
522 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0215 | Pima County will complete bridge deck repairs from along Sabino Canyon Rd and Tanque Verde Creek in PIMA COUNTY. | Bridge Improvement | 2009-06-22 | 2009-06-22 | 2011-09-30 | 2010-09-13 | 600000 | 43.000
523 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0218 | The Pima County will perform pavement preservation projects in the La Canadad Area | Pavement Improvement | 2010-04-08 | 2010-04-08 | 2011-09-30 | 2010-06-18 | 818499.94
524 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0219 | The Pima County will perform pavement preservation projects in the Flowing Wells Area | Pavement Improvement | 2010-04-23 | 2010-04-23 | 2011-09-30 | 2010-05-19 | 478600
525 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0220 | The Pima County will perform Countywide Overlay projects in various locations throughout Pima County. | Pavement Improvement | 2010-11-04 | 2010-11-04 | 2011-09-30 | 2010-11-30 | 1308900.06 | 0.000
526 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0221 | The Pima County will perform Countywide Microseal projects in various locations throughout Pima County. | Pavement Improvement | 2010-06-28 | 2010-08-01 | 2011-09-30 | 2011-02-14 | 1531700 | 0.000
527 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0222 | The Pima County will perform Countywide Chipseal projects in various locations throughout Pima County. | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2011-09-30 | 2010-06-29 | 597800 | 0.000
528 | Underway | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | PPM0225 | The City of Tucson will perform a bicycle & pedestrian education progam. & safety enhancements at Pima County Middle Schools. | Other | 2010-11-04 | 2010-11-04 | 2013-01-01 |  | 850000
529 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0226 | Pima County will Replace/Install video detection, striping, and signal lamps for traffic operations. | Pavement Improvement | 2011-03-31 |  | 2012-01-09 | 2011-09-30 | 1380000
530 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | YAVAPAI |  | 01 | PRV0004 | The City of Prescott Valley will perform a Transportation Enhancement project along Bison Lane in PRESCOTT VALLEY to include a shared use pathway. | Other | 2009-08-24 | 2009-08-24 |  | 2009-10-22 | 486218.68 | 0.600
531 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | YAVAPAI | FLAGSTAFF | 01 | PRV0203 | The City of Prescott Valley will perform a Pavement Preservation along Glassford Hill Road in PRESCOTT VALLEY to include Overlay/ 3" AC. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2009-12-18 | 2010-11-16 | 1574155 | 0.000
532 | Completed | C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | PVY0202 | The Town of Paradise Valley, AZ will perform Design and construction of pavement resurfacing along Various Roadways in PARADISE VALLEY. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-11-24 | 2011-03-11 | 823174 | 3.700
533 | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | QCR0205 | The City of Queen Creek, AZ will perform Design and construction of roadway resurfacing and shoulder paving along Various Locations on Rittenhouse Rd in QUEEN CREEK. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-09-22 | 2010-09-07 | 896371.06 | 1.700
534 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | SAH0201 | The Town of Sahuarita will perform a pavement preservation project in Rancho Sahuarita: La Villita to 2 miles north and Traffic signals & signage reflectivity upgrades and Duval Mine Rd: La Canada to | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-08-12 | 2010-10-18 | 1691785 | 2.600
535 | Underway | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | SAH0202 | The Town of Sahuarita will perform pavement preservation and striping on La Canada Dr. - El Toro Rd And Duval Mine Rd (3 Miles) | Pavement Improvement | 2011-01-03 | 2011-01-19 | 2011-04-20 |  | 1996626.9
536 | Completed | C220,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | SCT0200 | The City of Scottsdale, AZ will construct a Shared use pathway along Crosscut Canal, from Thomas Rd to Indian School Rd in SCOTTSDALE to include Shared use pathway and pedestrian bridge. | Other | 2009-11-18 | 2010-02-16 | 2010-08-01 | 2011-05-11 | 750184 | 0.800
537 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | SCT0203 | The City of Scottsdale, AZ will construct a Shared use pathway along Arizona Canal (Sun Circle Trail) at Goldwater Blvd in SCOTTSDALE. | Transportation Enhancements | 2009-09-09 | 2009-12-07 | 2010-08-15 | 2011-06-20 | 337622.87 | 0.100
538 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | SCT0206 | The City of Scottsdale will upgraded traffic controllers and cabinets at various locations in the southern area of Scottsdale to improve traffic operations and management. | Safety/Traffic Management | 2009-08-05 | 2009-08-05 | 2010-12-12 | 2011-02-27 | 476615 | 0.000
539 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | SCT0209 | The City of Scottsdale, will perform Pavement Preservation along Various Roadways in the City of Scottsdale. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-09-14 | 2011-02-17 | 4600000 | 10.500
540 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | SCT0212 | The City of Scottsdale will perform pavement preservation at various locations. | Pavement Improvement | 2011-05-16 | 2011-05-17 |  | 2011-09-14 | 831860
541 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | SLW0201 | The Navajo County will perform a Pavement Preservation along Penrod Road in SHOW LOW. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-08-23 | 2010-10-11 | 687362 | 4.100
542 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | SRI0200 | The Salt River Pima-Maricopa Indian Community, will Design & Construct Pavement Preservation/Chip-Seal along Various Locations on Functionally Classified Roads within Salt River Pima - Maricopa Indian | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2010-07-01 | 2010-12-01 | 653910 | 2.000
543 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | STC0200 | The City of South Tucson will perform a pavement preservation project along 29th Street; from 12th Avenue to the Union Pacific Railroad in SOUTH TUCSON. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-07-12 | 2010-06-28 | 555000 | 0.500
544 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | SUP0200 | The Town of Superior will perform a Pavement Preservation along Main Street. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-05-28 | 2010-08-05 | 496574 | 1.000
545 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | SUR0208 | The City of Surprise will perform a Pre-Engineer/Design and construct pavement Reconstruction and ITS Conduit Installation along Bell Rd; Parkview to West City Limit in SURPRISE. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-10-26 | 2010-10-26 | 2797836 | 4.300
546 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | SVS0200 | The City of Sierra Vista will complete transportation enhancement along Snyder Boulevard multi-use path, Avenida del Sol to SR-92 in SIERRA VISTA to include pathways, landscaping, and irrigation. | Other | 2009-08-31 | 2009-09-21 | 2010-01-21 | 2010-02-17 | 454000 | 0.500
547 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE | PHOENIX, AZ | 08 | SVS0204 | The City of Sierra Vista will perform widening, signal upgrades, drainage, improvements, curb, sidewalk, multi-use pathways on South side along Charleston Road. | Other | 2009-06-11 | 2009-06-11 | 2010-12-26 | 2011-09-15 | 2208506 | 1.200
548 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | GRAHAM |  | 01 | THR0200 | The Town of Thatcher will perform a 2 inch asphalt overlay along Reay Lane in the Town of Thatcher. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-07-14 | 2010-09-30 | 586574 | 2.000
549 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | TMP0202 | The City of Tempe, AZ will construct a Shared Use Pathway along Crosscut Canal from Papago Park to Mouer Park in TEMPE. | Transportation Enhancements | 2010-09-07 | 2010-09-07 | 2011-07-04 | 2011-12-31 | 1698533 | 1.000
550 | Completed | C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | TMP0211 | The City of Tempe, AZ will Construct a replacement bridge over the Western Canal along Baseline Rd (Kyrene Rd to Union Pacific Railroad) in TEMPE. | Bridge Replacement | 2009-08-11 | 2009-08-11 | 2010-11-15 | 2011-04-15 | 2136143 | 0.200
551 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | TMP0216 | The City of Tempe will do milling and fill, ADA ramps, striping, utility adjustments and replacement of signal loops on Broadway Rd. - Mill Ave To Evergreen Rd. | Pavement Improvement | 2011-02-03 | 2011-02-07 | 2011-05-03 | 2011-08-01 | 2087487
552 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0051 | The City of Tucson will install, repair or replace deteriorated sidewalks/driveways along South Fourth Avenue in TUCSON. | Other | 2009-09-14 | 2009-09-14 | 2010-06-08 | 2010-08-15 | 358625 | 0.500
553 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0067 | The City of Tucson will construct a bicycle & pedestrian enhancement at Tyndall Ave., University Blvd. To 6th St. | Transportation Enhancements | 2011-04-16 | 2011-04-16 |  | 2011-08-10 | 800000
554 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0073 | The City of Tucson will perform a transportation enhancement project along Fourth Avenue between 17th and 22nd Streets in Tucson to include construction of sidewalks and driveways to meet ADA standard | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-08-27 | 2010-08-13 | 298800 | 0.000
555 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0215 | The City of Tucson will construct a pedestrian bridge and walkway at Treat Ave., Between Speedway And 22Nd St.. | Transportation Enhancements | 2011-02-07 |  | 2011-05-07 | 2011-05-05 | 295000
556 | Completed | C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0231 | The City of Tucson will perform pavement preservation projects at various locations within the City of Tucson. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-11-24 | 2011-07-22 | 7376691 | 0.000
557 | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0232 | The City of Tucson will complete various pavement preservation projects within the City of Tucson. | New Construction | 2009-09-03 | 2009-09-03 | 2010-07-17 | 2010-12-31 | 3482051 | 0.000
558 | Completed | C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0239 | The City of Tucson will replace sign panels, install video detection, and do striping for Traffic Operations. | Pavement Improvement | 2011-10-10 | 2011-12-05 | 2012-01-07 | 2012-01-24 | 2720000
559 | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | WBG0200 | The Town of Wickenburg, will perform a Pavement Preservation project along North Vulture Mine Rd; from US 60 to Northern Town Limits in WICKENBURG to include Mill and Replace. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2012-05-18 |  | 642619 | 1.600
560 | Completed | C250,C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | YTN0200 | The Town of Youngtown will perform a Pre-Engineer/Design to construct, mill and replace pavement resurfacing along Peoria Ave; 111th Ave to 115th Av in YOUNGTOWN. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-11-09 | 2010-11-09 | 395711 | 0.000
561 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | YUM0200 | The City of Yuma will perform a Transportation Enhancement project in YUMA to include Construction of an interpretative plaza, complete with retaining walls. | Other | 2009-08-01 | 2010-08-01 | 2011-01-01 | 2010-12-07 | 750000 | 0.200
562 | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | YUMA |  | 07 | YUM0201 | The City of Yuma will construct a shared-use pathway/linear park at Yuma Main Canal, E. Of 4Th Ave. At Yuma Siphon | Other | 2010-10-25 | 2011-02-22 |  | 2011-12-14 | 750000
563 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | YUMA |  | 07 | YYU0031 | The Yuma County will perform a Bridge Replacement project for Red Top Wash Bridge in Yuma. | Bridge Replacement | 2009-03-03 | 2009-11-19 | 2010-08-16 | 2011-01-25 | 1325000 | 0.000
564 | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | YYU0200 | The Yuma County will perform a round-about construction project along Avenue E @ Juan Sanchez Blvd within the New San Luis II POE in YUMA COUNTY. | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2010-08-04 | 2010-08-11 | 932000 | 2.000
565 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | YAVAPAI |  | 01 | YYV0202 | The Yavapai County will perform a Cold in place recycle; reconstruction along Cornville Rd; from Aspaas Rd to Beaverhead Flat Rd in YAVAPAI COUNTY. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-09-14 | 2010-09-13 | 894016 | 3.800
566 | Underway | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LAWRENCE |  | 01 | ARR1001 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT THE EMBANKMENT AND BRIDGES FOR 9.89 MILES OF THE NEW LOCATION OF HIGHWAY 67 BETWEEN HIGHWAY 230 AND HIGHWAY 63, SOUTH OF HOXIE IN LAWRENCE COUNTY. WORK INC | New Construction | 2009-06-22 | 2009-07-15 | 2012-12-31 |  | 21094279 | 19.780
567 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI |  | 02 | ARR1003 | THE PURPOSE OF THIS PROJECT IS TO REPLACE FOUR EXISTING BRIDGE STRUCTURES, RECONSTRUCT APPROACHES ON I-430 AND CONSTRUCT WIDENING TO THE I-630 LOOP RAMP CONNECTIONS AT THE I-430/I-630 INTERCHANGE IN | Bridge Improvement | 2009-07-17 | 2009-07-20 | 2010-11-15 | 2011-01-19 | 15991380 | 0.000
568 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | ST FRANCIS |  | 01 | ARR1004 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.30 MILES OF HIGHWAY 1 BETWEEN THE CITIES OF CALDWELL AND COLT IN ST. FRANCIS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE | Pavement Improvement | 2009-06-15 | 2009-07-07 | 2009-08-21 | 2009-09-10 | 1673191 | 4.300
569 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PHILLIPS |  | 01 | ARR1005 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.36 MILES OF HIGHWAY 49B BETWEEN HIGHWAY 49 AND HIGHWAY 242 IN THE CITY OF HELENA-WEST HELENA, PHILLIPS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, | Pavement Improvement | 2009-06-03 | 2009-07-02 | 2009-07-15 | 2009-07-15 | 391184 | 1.360
570 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MONROE |  | 01 | ARR1006 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.45 MILES OF HIGHWAY 49 FROM HIGHWAY 241 NORTH IN THE VICINITY OF THE CITY OF RICH IN MONROE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, MAINTENANCE | Pavement Improvement | 2009-04-22 | 2009-06-19 | 2009-07-09 | 2009-07-09 | 580419 | 2.450
571 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN |  | 01 | ARR1007 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 9.63 MILES OF HIGHWAY 79 IN CRITTENDEN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELL | Pavement Improvement | 2009-04-20 | 2009-04-22 | 2009-07-15 | 2009-07-15 | 2139531 | 9.630
572 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LINCOLN |  | 04 | ARR1008 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.39 MILES OF HIGHWAY 425 NORTH AND SOUTH OF STAR CITY IN LINCOLN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, P | Pavement Improvement | 2009-04-17 | 2009-05-04 | 2009-07-06 | 2009-07-06 | 1256575 | 5.390
573 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CHICOT |  | 04 | ARR1010 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.75 MILES OF HIGHWAY 65 BETWEEN THE CITY OF LAKE VILLAGE AND THE CITY OF MCMILLAN CORNER IN CHICOT COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD | Pavement Improvement | 2009-06-03 | 2009-06-30 | 2009-09-14 | 2009-09-24 | 1175182 | 3.730
574 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | ASHLEY |  | 04 | ARR1011 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 6.09 MILES OF HIGHWAY 82 EAST OF THE CITY OF CROSSETT IN ASHLEY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUTTERS, MAINTENAN | Pavement Improvement | 2009-06-15 | 2009-06-26 | 2009-09-14 | 2009-10-23 | 1863272 | 6.090
575 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | ARKANSAS |  | 01 | ARR1012 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.11 MILES OF SELECTED SECTIONS OF HIGHWAY 79 BETWEEN HIGHWAY 79C AND HIGHWAY 165 NEAR THE CITY OF STUTTGART IN ARKANSAS COUNTY. WORK INCLUDES PAVEMENT | Pavement Improvement | 2009-04-17 | 2009-05-22 | 2009-07-01 | 2009-07-01 | 682688 | 3.110
576 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PIKE |  | 04 | ARR1013 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.06 MILES OF HIGHWAY 70 FROM THE CITY OF KIRBY EAST IN PIKE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEME | Pavement Improvement | 2009-04-22 | 2009-04-30 | 2009-08-10 | 2009-08-07 | 1020068 | 3.060
577 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | NEVADA |  | 04 | ARR1014 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.02 MILES OF HIGHWAY 67 FROM THE CITY OF PRESCOTT SOUTH IN NEVADA COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUTTERS, MAINTE | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2009-09-14 | 2009-09-21 | 953699 | 3.020
578 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD |  | 04 | ARR1015 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.67 MILES OF HIGHWAY 278 BETWEEN HAZEL STREET AND GREENWOOD STREET IN THE CITY OF HOPE, HEMPSTEAD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD M | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-09-14 | 2009-09-09 | 335086 | 1.670
579 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LITTLE RIVER |  | 04 | ARR1016 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.41 MILES OF HIGHWAY 71 BETWEEN THE CITIES OF ASHDOWN AND WILTON IN LITTLE RIVER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENAN | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-07-24 | 2009-07-24 | 833726 | 3.410
580 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SEVIER |  | 04 | ARR1017 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.01 MILES OF HIGHWAY 70 FROM THE CITY OF DEQUEEN WEST IN SEVIER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PA | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-08-20 | 2009-08-06 | 368943 | 1.010
581 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LAFAYETTE |  | 04 | ARR1018 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.08 MILES OF HIGHWAY 82 EAST AND WEST OF THE RED RIVER IN MILLER AND LAFAYETTE COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH | Pavement Improvement | 2009-04-27 | 2009-05-21 | 2009-08-10 | 2009-08-07 | 607701 | 4.160
582 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD |  | 04 | ARR1019 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.45 MILES OF HIGHWAY 278 FROM THE CITY OF OZAN WEST IN HEMPSTEAD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, P | Pavement Improvement | 2009-06-08 | 2009-08-18 | 2009-09-14 | 2009-09-04 | 885084 | 5.450
583 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WASHINGTON |  | 03 | ARR1020 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.78 MILES OF HIGHWAY 412 BETWEEN HIGHWAY 112 AND INTERSTATE 540 IN THE CITY OF SPRINGDALE, WASHINGTON COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, CO | Pavement Improvement | 2009-04-23 | 2009-05-26 | 2009-07-08 | 2009-07-08 | 570814 | 1.780
584 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FRANKLIN |  | 03 | ARR1021 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.09 MILES OF HIGHWAY 22 FROM CHARLESTON EAST IN FRANKLIN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROSION C | Pavement Improvement | 2009-06-15 | 2009-07-27 | 2009-09-14 | 2009-09-11 | 684500 | 3.090
585 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LOGAN |  | 04 | ARR1022 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.77 MILES OF HIGHWAY 22 BETWEEN THE CITIES OF SUBIACO AND MIDWAY IN LOGAN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF T | Pavement Improvement | 2009-04-17 | 2009-04-23 | 2009-05-28 | 2009-05-28 | 691491 | 2.770
586 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SHARP |  | 01 | ARR1023 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.47 MILES OF HIGHWAY 71 SOUTH OF THE CITY OF WALDRON IN SCOTT COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROS | Pavement Improvement | 2009-06-15 | 2009-07-07 | 2009-08-07 | 2009-08-19 | 805350 | 3.470
587 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN |  | 03 | ARR1024 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.74 MILES OF HIGHWAY 22 FROM INTERSTATE 540 EAST IN THE CITY OF FORT SMITH, SEBASTIAN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAIN | Pavement Improvement | 2009-06-08 | 2009-07-31 | 2009-09-07 | 2009-09-20 | 1021316 | 2.740
588 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | POLK |  | 04 | ARR1025 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.65 MILES OF HIGHWAY 71 SOUTH AND NORTH OF HIGHWAY 8 IN THE CITY OF MENA, POLK COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE | Pavement Improvement | 2009-04-27 | 2009-05-29 | 2009-06-24 | 2009-06-24 | 581777 | 1.650
589 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRAWFORD |  | 03 | ARR1026 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.00 MILES OF HIGHWAY 64 FROM ALMA EAST IN CRAWFORD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROSION CONTROL | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2009-07-24 | 2009-07-24 | 524121 | 2.000
590 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR1027 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.67 MILES OF HIGHWAY 167 NORTH OF THE CITY OF BALD KNOB IN WHITE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, P | Pavement Improvement | 2009-06-08 | 2009-07-27 | 2009-09-01 | 2009-09-02 | 1132854 | 3.670
591 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | STONE |  | 01 | ARR1028 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.57 MILES OF HIGHWAY 14 EAST OF THE CITY OF MOUNTAIN HOME IN STONE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 2009-04-17 | 2009-05-04 | 2009-05-19 | 2009-05-19 | 438853 | 1.570
592 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR1029 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.88 MILES OF HIGHWAY 167 FROM THE JACKSON COUNTY LINE NORTH IN WHITE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFI | Pavement Improvement | 2009-06-08 | 2009-07-09 | 2009-09-14 | 2009-08-29 | 862415 | 2.830
593 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE, INDEPENDENCE |  | Multiple | ARR1030 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.64 MILES OF HIGHWAY 167 FROM THE CITY OF PLEASANT PLAINS SOUTH IN INDEPENDENCE AND WHITE COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING | Pavement Improvement | 2009-04-17 | 2009-05-28 | 2009-06-01 | 2009-06-26 | 862046 | 4.780
594 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CLEBURNE |  | 01 | ARR1031 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.66 MILES OF HIGHWAY 25 FROM GREERS FERRY DAM SOUTH IN THE VICINITY OF THE CITY OF HEBER SPRINGS IN CLEBURNE COUNTY. WORK INCLUDES PAVEMENT REHABILITAT | Pavement Improvement | 2009-04-22 | 2009-07-15 | 2009-08-10 | 2009-08-21 | 648533 | 2.660
595 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | INDEPENDENCE |  | 01 | ARR1032 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.14 MILES OF HIGHWAY 69 FROM THE BLACK RIVER WEST IN INDEPENDENCE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 2009-06-03 | 2009-07-06 | 2009-09-14 | 2009-09-28 | 245794 | 1.140
596 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI |  | 02 | ARR1033 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.10 MILES OF INTERSTATE 40 BETWEEN INTERSTATE 30 AND HIGHWAY 67 IN THE CITY OF NORTH LITTLE ROCK, PULASKI COUNTY. WORK INCLUDES CONCRETE PAVEMENT PATCH | Pavement Improvement | 2009-08-04 | 2009-08-17 | 2009-11-13 | 2010-06-08 | 1892346 | 1.100
597 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LONOKE |  | 01 | ARR1034 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.80 MILES OF HIGHWAY 70 FROM THE PULASKI COUNTY LINE EAST IN LONOKE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, TRENCHING AND SHOULDER PREPARATION, | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2009-06-30 | 2009-06-30 | 467972 | 2.800
598 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | HOT SPRING |  | 04 | ARR1035 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.20 MILES OF HIGHWAY 67 FROM THE CITY OF GLEN ROSE SOUTH IN HOT SPRING COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, TRENCHING AND SHOULDER PREPARATIO | Pavement Improvement | 2009-04-17 | 2009-05-05 | 2009-06-17 | 2009-06-17 | 264789 | 1.200
599 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PRAIRIE |  | 01 | ARR1036 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.40 MILES OF HIGHWAY 70 BETWEEN HAZEN AND DEVALLS BLUFF IN PRAIRIE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 2009-04-22 | 2009-04-22 | 2009-06-17 | 2009-06-17 | 993892 | 5.400
600 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LONOKE, PULASKI |  | Multiple | ARR1037 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.25 MILES OF HIGHWAY 165 BETWEEN THE CITIES OF NORTH LITTLE ROCK AND SCOTT IN LONOKE AND PULASKI COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD | Pavement Improvement | 2009-06-01 | 2009-06-08 | 2009-09-14 | 2009-09-11 | 1181822 | 11.250
601 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | OUACHITA |  | 04 | ARR1038 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.60 MILES OF HIGHWAY 79 BETWEEN THE CITIES OF CAMDEN AND EAST CAMDEN IN OUACHITA COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH | Pavement Improvement | 2009-06-03 | 2009-06-22 | 2009-09-14 | 2009-08-26 | 1294334 | 2.600
602 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | DALLAS |  | 04 | ARR1039 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.61 MILES OF HIGHWAY 79 IN DALLAS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEO | Pavement Improvement | 2009-04-17 | 2009-05-07 | 2009-06-24 | 2009-06-24 | 1124559 | 3.610
603 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CLEVELAND |  | 04 | ARR1040 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 9.50 MILES OF HIGHWAY 79 BETWEEN THE CITIES OF KINGLAND AND RISON IN CLEVELAND COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUT | Pavement Improvement | 2009-06-03 | 2009-06-11 | 2009-08-21 | 2009-08-20 | 1354932 | 9.500
604 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CALHOUN |  | 04 | ARR1041 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.12 MILES OF HIGHWAY 167 FROM THE CITY OF HAMPTON SOUTH IN CALHOUN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 2009-04-17 | 2009-05-05 | 2009-06-09 | 2009-06-09 | 1026517 | 4.120
605 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | VAN BUREN |  | 02 | ARR1042 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.87 MILES OF HIGHWAY 65 NORTH OF THE CITY OF CLINTON IN VAN BUREN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, | Pavement Improvement | 2009-06-08 | 2009-08-10 | 2009-09-14 | 2009-10-16 | 1725247 | 5.870
606 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR1043 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.68 MILES OF HIGHWAY 65 NORTH AND SOUTH OF HIGHWAY 25 IN THE CITY OF GREENBRIER, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 2009-04-22 | 2009-07-02 | 2009-08-03 | 2009-08-03 | 778244 | 2.680
607 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | YELL |  | 02 | ARR1044 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.90 MILES OF HIGHWAY 10 EAST AND WEST OF THE CITY OF MICKLES IN YELL COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFI | Pavement Improvement | 2009-04-17 | 2009-04-27 | 2009-07-07 | 2009-07-07 | 1092148 | 5.900
608 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | POPE |  | 03 | ARR1045 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.64 MILES OF HIGHWAY 7 BETWEEN J STREET AND HIGHWAY 326 IN THE CITY OF RUSSELLVILLE, POPE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 2009-06-04 | 2009-09-04 | 2009-09-14 | 2009-10-01 | 467277 | 1.640
609 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR1046 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 0.37 MILE OF HIGHWAY 65 BETWEEN THE INTERSTATE 40 OFF AND ON RAMPS IN THE CITY OF CONWAY, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD M | Pavement Improvement | 2009-04-22 | 2009-07-02 | 2009-08-05 | 2009-08-04 | 182026 | 0.740
610 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR1047 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE HIGHWAY 412 FROM HIGHWAY 59 IN THE CITY OF SILOAM SPRINGS TO THE EAST 5.45 MILES IN BENTON COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 2009-06-01 | 2009-06-22 | 2009-08-27 | 2009-08-24 | 2030641 | 5.450
611 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | BOONE |  | 03 | ARR1048 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.40 MILES OF HIGHWAY 65 FROM THE MISSOURI STATE LINE SOUTH IN BOONE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC | Pavement Improvement | 2009-04-22 | 2009-05-04 | 2009-07-28 | 2009-07-28 | 2871797 | 7.400
612 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | GREENE |  | 01 | ARR1052 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.79 MILES OF HIGHWAY 412 BETWEEN REYNOLDS ROAD AND HIGHWAY 49B IN THE CITY OF PARAGOULD, GREENE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MIL | Pavement Improvement | 2009-06-08 | 2009-08-19 | 2009-09-14 | 2009-09-12 | 770949 | 1.790
613 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MISSISSIPPI |  | 01 | ARR1053 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 0.84 MILE OF HIGHWAY 18 FROM INTERSTATE 55 WEST IN THE CITY OF BLYTHEVILLE, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAI | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-05-28 | 2009-05-28 | 348065 | 0.840
614 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CLAY |  | 01 | ARR1054 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.10 MILES OF HIGHWAY 67 BETWEEN HIGHWAY 328 NORTH OF CORNING AND THE MISSOURI STATE LINE IN CLAY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MI | Pavement Improvement | 2009-06-08 | 2009-07-15 | 2009-09-14 | 2009-09-12 | 1098919 | 4.100
615 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MISSISSIPPI |  | 01 | ARR1055 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.10 MILES OF HIGHWAY 140 WEST AND EAST OF HIGHWAY 119Y IN THE CITY OF OSCEOLA, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 2009-04-27 | 2009-05-15 | 2009-06-09 | 2009-06-09 | 452888 | 1.100
616 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LAWRENCE |  | 01 | ARR1056 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE A 0.26 MILE SECTION OF HIGHWAY 412 BETWEEN HIGHWAY 67B NORTH AND HIGHWAY 67B SOUTH IN THE CITY OF WALNUT RIDGE, LAWRENCE COUNTY. WORK INCLUDES PAVEMENT | Pavement Improvement | 2009-06-01 | 2009-08-11 | 2009-09-14 | 2009-09-21 | 125418 | 0.250
617 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | RANDOLPH |  | 01 | ARR1057 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.05 MILES OF HIGHWAY 67 FROM HIGHWAY 90 NORTH IN THE THE CITY OF POCAHONTAS, RANDOLPH COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAIN | Pavement Improvement | 2009-04-17 | 2009-05-14 | 2009-08-03 | 2009-08-03 | 174441 | 1.050
618 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | POINSETT |  | 01 | ARR1058 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.14 MILES OF HIGHWAY 63 FROM THE CRAIGHEAD COUNTY LINE TO HIGHWAY 69 WEST OF THE CITY OF TRUMANN IN POINSETT COUNTY. WORK INCLUDES PAVEMENT REHABILITAT | Pavement Improvement | 2009-06-01 | 2009-06-04 | 2009-09-14 | 2009-08-14 | 673482 | 2.140
619 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRAIGHEAD |  | 01 | ARR1059 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.59 MILES OF HIGHWAY 63 BETWEEN HIGHWAY 91 AND HIGHWAY 226 IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK INCLUDES CONCRETE PAVEMENT GRINDING AND P | Pavement Improvement | 2009-05-08 | 2009-07-06 | 2009-10-30 | 2009-12-15 | 1182066 | 3.590
620 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | GARLAND |  | 04 | ARR1060 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 0.37 MILE OF HIGHWAY 128 FROM SHADY GROVE ROAD TO NORTH OF HIGHWAY 270 IN THE CITY OF HOT SPRINGS, GARLAND COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADW | Pavement Widening | 2009-09-23 | 2009-10-27 | 2010-06-25 | 2010-06-24 | 1583907 | 0.370
621 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | GRANT |  | 04 | ARR1061 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.1 MILES OF HIGHWAY 167 BETWEEN NORTH MILLERVILLE AND THE SHERIDAN BYPASS IN GRANT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN | Pavement Widening | 2009-09-18 | 2009-09-24 | 2011-07-22 | 2010-12-16 | 8819100 | 4.080
622 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN |  | 03 | ARR1063 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT FOUR MAIN LANE BRIDGES AS PART OF THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49) BETWEEN TAYLOR AVENUE AND HIGHWAY 22 NEAR FT. CHAFFEE IN SEBASTIAN C | New Bridge Construction | 2009-07-06 | 2009-07-09 | 2010-12-30 | 2011-04-19 | 11693084 | 0.660
623 | Underway | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN |  | 03 | ARR1064 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 2.69 MILES OF GRADING AND STRUCTURES OF THE NEW LOCATION HIGHWAY 71 BETWEEN CO ROAD 8 AND CUSTER BLVD. NEAR FORT CHAFFEE IN SEBASTIAN COUNTY. WORK WILL INC | New Construction | 2009-10-16 | 2009-10-15 | 2011-09-30 |  | 10730011 | 5.380
624 | Underway | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MILLER |  | 04 | ARR1065 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 1.77 MILES OF EMBANKMENT AND MINOR DRAINAGE STRUCTURES FOR THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49) BETWEEN COUNTY ROAD 2 AND DODDRIDGE, SOUTH | New Construction | 2009-08-21 | 2009-09-03 | 2011-06-25 |  | 6685747 | 1.770
625 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRAIGHEAD |  | 01 | ARR1066 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 141 AND PARKER ROAD IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK ITEMS INCLUDE TRAFFIC SI | Safety/Traffic Management | 2009-06-08 | 2009-10-20 | 2009-12-18 | 2009-12-17 | 83737 | 0.000
626 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | ARKANSAS |  | 01 | ARR1067 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT APPROXIMATELY 1.30 MILES OF COUNTY ROADS 33 AND 43 NEAR THE CITY OF ALMYRA IN ARKANSAS COUNTY. WORK WILL INCLUDE RECONSTRUCTING THE EXISTING ROADWAY, PAV | Pavement Improvement | 2009-06-15 | 2009-06-26 | 2009-08-14 | 2009-09-01 | 156690 | 1.260
627 | Underway | C220 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN |  | 01 | ARR1068 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A WELCOME CENTER AT THE COMMON SECTION OF INTERSTATE 55 AND INTERSTATE 40 IN WEST MEMPHIS, CRITTENDEN COUNTY. WORK ITEMS INCLUDE EARTHWORK, A WELCOME CENTE | Transportation Enhancements | 2010-04-07 | 2010-05-11 | 2012-07-01 |  | 3830174 | 0.000
628 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2001 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 67B, HIGHWAY 31 AND HIGHWAY 367 INTERSECTION IN THE CITY OF BEEBE IN WHITE COUNTY. WORK ITEMS INCLUDE TRAFFIC S | Safety/Traffic Management | 2010-02-11 | 2010-04-21 | 2010-05-20 | 2010-08-18 | 76337 | 0.000
629 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | VAN BUREN |  | 02 | ARR2002 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 65 AND HIGHWAY 16 EAST IN THE CITY OF CLINTON IN VAN BUREN COUNTY. WORK ITEMS INCLUDE TRAFFIC S | Safety/Traffic Management | 2010-03-25 | 2010-05-06 | 2010-10-08 | 2010-09-29 | 62720 | 0.000
630 | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2003 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A 2-LANE ROUNDABOUT ON PIKE AVENUE IN NORTH LITTLE ROCK, PULASKI COUNTY. THE WORK WILL ALSO INCLUDE CURBS, GUTTERS, SIDEWALKS, DRAINAGE, LANDSCAPING AND EL | Pavement Widening | 2010-01-11 | 2010-01-11 | 2010-10-08 | 2011-01-24 | 1489935 | 0.170
631 | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN | MEMPHIS (TN-MS) | 01 | ARR2004 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND UPGRADE THE PAVEMENT TO CONCRETE WITH NEW CURBS ON GLEN BAILEY DRIVE BETWEEN HIGHWAY 77 AND HIGHWAY 191 IN THE CITY OF WEST MEMPHIS, CRITTENDEN COUNTY | Pavement Improvement | 2010-05-20 | 2010-06-14 | 2010-11-30 | 2010-11-15 | 1300000 | 0.620
632 | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN | MEMPHIS (TN-MS) | 01 | ARR2005 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AN ADDITIONAL LANE TO L.H. POLK DRIVE IN THE CITY OF MARION, CRITTENDEN COUNTY. THIS LANE WILL BE APPROXIMATELY 1,000 FEET LONG AND 12 FEET WIDE TO REMOVE | Pavement Improvement | 2010-07-02 | 2010-07-14 | 2010-09-05 | 2010-09-30 | 197529 | 0.190
633 | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI |  | 02 | ARR2006 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT TWO CONCRETE. BOX CULVERTS AND APPROACHES ON 0.360 MILE OF COUNTY ROAD 67 IN THE VICINITY OF SHERWOOD IN PULASKI COUNTY. WORK INCLUDES CLEARING AND GRUBBI | Bridge Replacement | 2009-09-17 | 2009-09-17 | 2010-09-01 | 2011-03-03 | 770372 | 0.360
634 | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2008 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A BRIDGE AND APPROACHES ON APPROXIMATELY 0.47 MILE OF COUNTY ROAD 9 NEAR SILOAM SPRINGS IN BENTON COUNTY. WORK WILL INCLUDE CLEARING, GRADING, DRAINAGE IMP | Bridge Replacement | 2009-11-20 | 2010-02-03 | 2011-05-14 | 2011-03-28 | 1319151 | 0.460
635 | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | BRADLEY |  | 04 | ARR2009 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT ONE CONCRETE BOX CULVERT AND APPROACHES ON 0.80 MILE OF COUNTY ROAD 2 IN THE VICINITY OF HERMITAGE IN BRADLEY COUNTY. WORK INCLUDES CLEARING AND GRUBBING, | Pavement Improvement | 2009-08-12 | 2009-08-20 | 2009-12-18 | 2010-07-23 | 319946 | 1.600
636 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | RANDOLPH |  | 01 | ARR2010 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT ONE BRIDGE LENGTH STRUCTURE AND APPROACHES ON 0.492 MILE OF COUNTY ROAD 48 NEAR POCAHONTAS IN RANDOLPH COUNTY. WORK INCLUDES GRADING, DRAINAGE IMPROVEMENTS, | Bridge Replacement | 2009-06-22 | 2009-07-09 | 2010-12-22 | 2010-12-21 | 1693838 | 0.490
637 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CLARK |  | 04 | ARR2011 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT TWO BRIDGE LENGTH STRUCTURES AND APPROACHES ON 0.72 MILE OF COUNTY ROAD 38 NEAR ASH FLAT IN SHARP COUNTY. WORK WILL INCLUDE EARTHWORK, DRAINAGE IMPROVEMENT | Pavement Improvement | 2009-07-14 | 2009-07-16 | 2010-12-22 | 2010-12-22 | 985359 | 0.720
638 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | ST FRANCIS |  | 01 | ARR2012 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 1 AND HIGHWAY 306 IN THE CITY OF COLT IN ST. FRANCIS COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 2009-11-06 | 2009-11-30 | 2010-07-23 | 2010-07-30 | 127341 | 0.000
639 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | WASHINGTON |  | 03 | ARR2013 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 16 AND HIGHWAY 74 IN THE CITY OF ELKINS IN WASHINGTON COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 2009-11-06 | 2010-02-17 | 2010-05-17 | 2010-05-17 | 65247 | 0.000
640 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLARK |  | 04 | ARR2014 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL THREE TRAFFIC SIGNALS ON HIGHWAY 67 AT THE INTERSECTIONS OF HENDERSON STREET, HIGHWAY 51 WEST/PINE STREET AND HIGHWAY 51 EAST/CADDO STREET IN TH | Safety/Traffic Management | 2009-11-13 | 2010-01-15 | 2010-07-30 | 2010-07-29 | 203370 | 0.000
641 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2016 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 64, ROOSTER ROAD AND LOWER RIDGE ROAD NEAR THE CITY OF CONWAY IN FAULKNER COUNTY. WORK ITEMS IN | Pavement Improvement | 2009-08-19 | 2009-09-14 | 2010-02-05 | 2010-02-03 | 76248 | 0.000
642 | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | SALINE | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2017 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND WIDEN 1.4 MILES OF MILITARY ROAD FROM INTERSTATE 30 TO CONGO ROAD IN THE CITY OF BENTON, SALINE COUNTY. WORK WILL INCLUDE WIDENING TO A FOUR-LANE DIV | Other | 2009-08-12 | 2009-08-12 | 2011-01-14 | 2011-03-03 | 5519716 | 1.410
643 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD |  | 04 | ARR2018 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 278, HIGHWAY 29 AND SHOVER ROAD IN THE CITY OF HOPE IN HEMPSTEAD COUNTY. WORK ITEMS INCLUDE TRA | Transportation Enhancements | 2009-12-31 | 2010-06-02 | 2010-07-09 | 2010-07-16 | 113093 | 0.000
644 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | HOWARD |  | 04 | ARR2019 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND INSTALL TRAFFIC SIGNALS ON HIGHWAY 371 AT THE INTERSECTIONS OF HIGHWAY 27/HIGHWAY 278 AND HIGHWAY 980/MAIN STREET IN THE CITY OF NASHVILLE, HOWARD COU | Safety/Traffic Management | 2010-01-14 | 2010-03-29 | 2010-07-09 | 2010-07-02 | 207191 | 0.000
645 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | INDEPENDENCE |  | 01 | ARR2021 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE THE TRAFFIC SIGNALS ON HIGHWAY 167 AT THE INTERSECTIONS OF SOUTHERLAND DRIVE, MYERS AVENUE, LAWRENCE STREET, VIRGINIA DRIVE AND COLLEGE AVENUE IN THE CIT | Safety/Traffic Management | 2010-05-26 | 2010-08-05 | 2010-11-12 | 2010-11-01 | 220822 | 0.000
646 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2022 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 16 AND HOLMES ROAD INTERSECTION IN THE CITY OF SEARCY IN WHITE COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPM | Safety/Traffic Management | 2010-02-18 | 2010-04-09 | 2010-05-20 | 2010-12-03 | 94063 | 0.000
647 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLEBURNE |  | 01 | ARR2023 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 25/124 INTERSECTION IN THE CITY OF QUITMAN IN CLEBURNE COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT, REM | Safety/Traffic Management | 2010-04-14 | 2010-08-03 | 2010-11-12 | 2010-11-17 | 165163 | 0.000
648 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLARK |  | 04 | ARR2025 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF INTERSTATE 30 AND HIGHWAY 7 IN THE CITY OF CADDO VALLEY IN CLARK COUNTY. WORK ITEMS INCLUDE TRAFFIC SIG | Safety/Traffic Management | 2010-02-11 | 2010-06-29 | 2010-08-20 | 2010-08-20 | 117523 | 0.000
649 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | HOT SPRING |  | 04 | ARR2027 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE TRAFFIC SIGNALS AT THE INTERSECTIONS OF HIGHWAY 270B/3RD STREET, HIGHWAY 270B/HIGHWAY 67, HIGHWAY 67/ASH STREET AND HIGHWAY 9/5TH STREET IN THE CITY OF M | Safety/Traffic Management | 2010-04-27 | 2010-07-14 | 2010-11-12 | 2010-11-10 | 288770 | 0.000
650 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2029 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 100 AND VESTAL BLVD. INTERSECTION IN THE CITY OF NORTH LITTLE ROCK IN PULASKI COUNTY. WORK ITEMS INCLUDE TRAFFI | Safety/Traffic Management | 2010-02-19 | 2010-07-12 | 2010-08-20 | 2010-08-31 | 101867 | 0.000
651 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2030 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 279, HIGHWAY 340 AND HIGHLANDS BLVD. IN THE CITY OF BELLA VISTA IN BENTON COUNTY. WORK ITEMS I | Safety/Traffic Management | 2010-03-05 | 2010-05-17 | 2010-08-20 | 2010-08-18 | 89105 | 0.000
652 | Underway | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LINCOLN, DESHA |  | 04 | ARR2031 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 5.39 MILES OF HIGHWAY 65 NORTH AND SOUTH OF THE CITY OF GOULD IN LINCOLN AND DESHA COUNTIES. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, DRAINAGE IMPROVEM | Pavement Widening | 2009-09-18 | 2009-12-10 | 2012-10-05 |  | 15776865 | 5.390
653 | Completed | C220 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN | MEMPHIS (TN-MS) | 01 | ARR2032 | THE PURPOSE OF THIS PROJECT IS TO RELOCATE RAMPS AND CONNECTOR ROUTES TO PROVIDE ACCESS TO THE NEW WELCOME CENTER LOCATED IN THE COMMON AREA OF INTERSTATE 55 AND INTERSTATE 40 IN THE CITY OF WEST MEMP | Transportation Enhancements | 2010-05-26 | 2010-06-16 | 2011-06-03 | 2011-08-12 | 6716160 | 0.100
654 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | JEFFERSON |  | 04 | ARR2033 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL THREE TRAFFIC SIGNALS ON HIGHWAY 65B AT THE INTERSECTIONS OF CHERRY STREET, HIGHWAYS 79B/365, AND HIGHWAY 79B/UNIVERSITY DRIVE IN THE CITY OF PI | Safety/Traffic Management | 2010-02-18 | 2010-03-25 | 2010-08-20 | 2010-10-12 | 333713 | 0.000
655 | Underway | C200 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN |  | 03 | ARR2036 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 3.02 MILES OF HIGHWAY 22 BETWEEN HIGHWAY 255 AND HIGHWAY 96 IN THE VICINITY OF CENTRAL CITY, SEBASTIAN COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, | Pavement Widening | 2010-06-03 | 2010-06-03 | 2011-11-23 |  | 12021297 | 3.020
656 | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | POLK |  | 04 | ARR2037 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 1.40 MILES OF A NORTHBOUND PASSING LANE ON HIGHWAY 71 BETWEEN COUNTY ROAD 16 AND HIGHWAY 246 NEAR VANDERVOORT IN POLK COUNTY. WORK WILL INCLUDE PASSING LAN | Pavement Widening | 2010-02-23 | 2010-03-01 | 2011-04-30 | 2011-09-27 | 2015265 | 1.400
657 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN | FORT SMITH (OK) | 03 | ARR2039 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AND PROVIDE OPERATIONAL IMPROVEMENTS AT THE INTERSECTION OF HIGHWAY 271 AND HARVARD AVENUE IN THE CITY OF FT. SMITH IN SEBASTIA | Pavement Improvement | 2010-03-05 | 2010-03-31 | 2010-08-18 | 2010-07-21 | 191963 | 0.160
658 | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2041 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A NORTHBOUND AND A SOUTHBOUND PASSING LANE FOR A DISTANCE OF 2.40 MILES ON HWY . 16, BETWEEN THE CITIES OF PANGBURN AND SEARCY IN WHITE COUNTY. WORK WILL A | Pavement Widening | 2010-04-07 | 2010-04-12 | 2011-05-30 | 2011-08-04 | 3294666 | 2.400
659 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | UNION |  | 04 | ARR2043 | THE PURPOSE OF THIS PROJECT IS TO PROVIDE 3.22 MILES OF BASE AND SURFACING TO COMPLETE WIDENING HIGHWAY 167 BETWEEN CHAMPAGNOLLE ROAD AND HIGHWAY 7 SOUTH IN THE CITY OF EL DORADO, UNION COUNTY. WORK | New Construction | 2009-11-09 | 2009-12-04 | 2011-07-22 | 2011-08-04 | 552587 | 3.220
660 | Underway | C250,C200 | Highway Infrastructure Investment Grant | ARKANSAS | POPE |  | 03 | ARR2044 | THE PURPOSE OF THIS PROJECT IS TO WIDEN HIGHWAY 247 FROM HIGHWAY 7 EAST 5.26 MILES IN THE VICINITY OF POTTSVILLE, POPE COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN 11' CE | Pavement Widening | 2010-07-07 | 2010-07-07 | 2012-05-04 |  | 15252775 | 5.260
661 | Underway | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2045 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A 10.10 MILE HIGHWAY 64 BYPASS OF THE CITY OF VILONIA IN FAULKNER COUNTY. WORK INCLUDES BASE, PAVING , EROSION CONTROL, PAVEMENT MARKINGS AND MISCELLANEOUS | New Construction | 2010-04-28 | 2010-06-02 | 2011-12-15 |  | 23931157 | 10.100
662 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2046 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AND PROVIDE INTERSECTION IMPROVEMENTS AT THE INTERSECTION OF HIGHWAY 112 AND HIGHWAY 264 EAST IN THE CITY OF CAVE SPRINGS IN BE | Pavement Widening | 2010-03-09 | 2010-08-30 | 2011-06-17 | 2011-10-07 | 684470 | 0.000
663 | Underway | C200 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2047 | THE PURPOSE OF THIS PROJECT IS TO RELOCATE THE UTILITIES TO PREPARE FOR THE FUTURE CONSTRUCTION ON NEW LOCATION OF THE 4-LANE DIVIDED BELLA VISTA BYPASS, BENTON COUNTY. | Other | 2010-09-08 | 2010-09-08 | 2011-09-03 |  | 3000000 | 0.000
664 | Underway | C200 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2048 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 1.61 MILES OF HIGHWAY 412 BETWEEN THE OKLAHOMA STATE LINE AND WASHINGTON STREET IN SILOAM SPRINGS, BENTON COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADW | Pavement Widening | 2010-01-14 | 2010-02-10 | 2012-11-20 |  | 7070251 | 1.600
665 | Underway | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CRAIGHEAD |  | 01 | ARR2049 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 3.55 MILES OF HIGHWAY 226 FROM THE NEW LOCATION OF HIGHWAY 67 TO WEST OF CASH IN CRAIGHEAD COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, FOUR BRIDG | Pavement Widening | 2010-04-16 | 2010-05-04 | 2012-08-31 |  | 13764995 | 7.560
666 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WASHINGTON, BENTON |  | 03 | ARR2050 | THE PURPOSE OF THIS PROJECT IS TO WIDEN RAMPS AND ADD AUXILIARY LANES AT FOUR INTERCHANGES IN BENTON AND WASHINGTON COUNTIES. IMPROVEMENTS AT A FIFTH INTERCHANGE (PORTER RD.) IN WASHINGTON COUNTY INV | Pavement Widening | 2009-09-29 | 2009-10-12 | 2010-10-01 | 2010-10-01 | 2013305 | 0.000
667 | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2052 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A RAILROAD OVERPASS BRIDGE WITH APPROACH EMBANKMENTS ON SALEM ROAD IN THE CITY OF CONWAY, FAULKNER COUNTY. WORK INCLUDES CONSTRUCTING THE RAILROAD OVERPASS | New Bridge Construction | 2009-09-30 | 2009-09-30 | 2010-10-25 | 2011-06-10 | 2360595 | 0.310
668 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CHICOT |  | 04 | ARR2053 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 2.2 MILES OF HIGHWAY 65 BETWEEN FAIRVIEW AND THE LAKE VILLAGE TOURIST INFORMATION CENTER IN CHICOT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4 | Pavement Widening | 2010-02-12 | 2010-02-17 | 2010-11-30 | 2011-09-27 | 6697617 | 2.280
669 | Underway | C240 | Highway Infrastructure Investment Grant | ARKANSAS | DALLAS |  | 04 | ARR2054 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.44 MILES OF HIGHWAY 167 BETWEEN FORDYCE AND HIGHWAY 273 IN DALLAS COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, FIVE STRUCTURES, DRAINAGE IMPROVEM | Pavement Widening | 2010-01-12 | 2010-01-20 | 2012-10-12 |  | 19721383 | 4.440
670 | Underway | C230 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2055 | THE PURPOSE OF THIS PROJECT IS TO WIDEN BROCKINGTON ROAD BETWEEN HIGHWAY 176 AND MARYLAND AVENUE IN THE CITY OF SHERWOOD, PULASKI COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4 LANES WI | Pavement Widening | 2010-05-04 | 2009-07-02 | 2011-11-01 |  | 4844503 | 0.730
671 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2056 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 0.851 MILE OF HIGHWAY 107 IN PULASKI COUNTY. WORK INCLUDES GRADING, MINOR DRAINAGE STRUCTURES, PAVING, STORM DRAINS, EROSION CONTROL ITEMS, MAINTENANCE OF TRAF | Pavement Widening | 2009-11-12 | 2009-11-12 | 2011-04-15 | 2011-08-22 | 2669342 | 0.850
672 | Underway | C240 | Highway Infrastructure Investment Grant | ARKANSAS | GRANT |  | 04 | ARR2057 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.91 MILES OF HIGHWAY 167 BETWEEN THE SALINE RIVER AND NORTH MILLERVILLE IN GRANT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN 11 | Bridge Replacement | 2009-11-13 | 2009-12-01 | 2013-05-10 |  | 7244745 | 4.910
673 | Underway | C200 | Highway Infrastructure Investment Grant | ARKANSAS | MILLER |  | 04 | ARR2058 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AN OVERPASS BRIDGE STRUCTURE AND 2.44 MILES OF EMBANKMENT AS PART OF THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49), BETWEEN THE LOUISIANA STATE LINE | New Construction | 2010-01-26 | 2010-04-19 | 2011-12-31 |  | 6856721 | 2.440
674 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI |  | 02 | ARR2059 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND WIDEN 1.57 MILES OF HIGHWAY 67 BETWEEN KIEHL AVENUE AND HIGHWAY 440 IN THE CITY OF SHERWOOD, PULASKI COUNTY. WORK INCLUDES WIDENING THE EXISTING ROAD | Pavement Widening | 2010-03-19 | 2010-03-04 | 2010-12-20 | 2011-04-16 | 8516865 | 1.570
675 | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | CLEBURNE |  | 01 | ARR2060 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.96 MILES OF COUNTY ROAD 79 FROM WILBURN NORTH IN CLEBURNE COUNTY. | Pavement Improvement | 2010-02-19 | 2010-04-06 | 2010-04-21 | 2010-04-21 | 287990 | 2.960
676 | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD |  | 04 | ARR2061 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.83 MILES OF COUNTY ROAD 88 BETWEEN HIGHWAY 78 AND HIGHWAY 174 IN HEMPSTEAD COUNTY. | Pavement Improvement | 2010-03-01 | 2010-03-02 | 2010-03-17 | 2010-03-17 | 225622 | 1.830
677 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN |  | 01 | ARR2062 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 1.0 MILE OF HIGHWAY 118 BETWEEN HIGHWAY 70 AND INTERSTATE 40 IN THE CITY OF WEST MEMPHIS IN CRITTENDEN COUNTY. | Pavement Widening | 2010-02-22 | 2010-04-19 | 2010-11-29 | 2011-06-29 | 2877096 | 0.840
678 | Completed | C250,C240 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD, LAFAYETTE |  | 04 | ARR2063 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 3 NORTHBOUND AND 3 SOUTHBOUND PASSING LANES FOR A DISTANCE OF 7.2 MILES BETWEEN THE CITIES OF HOPE AND LEWISVILLE IN HEMPSTEAD AND LAYFAYETTE COUNTIES. | Pavement Widening | 2010-04-21 | 2010-05-04 | 2011-10-31 | 2011-12-02 | 9452572 | 7.410
679 | Completed | C950 | Ferryboat | ARKANSAS | MARION |  | 03 | ARR2064 | THE PURPOSE OF THIS PROJECT IS TO REPLACE TWO OF THE PEEL FERRY TUGBOATS | Other | 2010-10-08 | 2010-10-01 | 2011-01-15 | 2011-03-09 | 350000 | 0.000
680 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | INDEPENDENCE |  | 01 | ARR2065 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.54 MILES OF HIGHWAY 167 FROM NORTH OF THE CITY OF PLEASANT PLAINS SOUTH IN INDEPENDENCE COUNTY. | Pavement Improvement | 2010-02-16 | 2010-04-05 | 2010-06-25 | 2010-05-13 | 664680 | 1.540
681 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2066 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.64 MILES OF HIGHWAY 64 BETWEEN INTERSTATE 40 AND SQUIRREL HILL IN FAULKNER COUNTY. | Pavement Improvement | 2010-02-03 | 2010-03-01 | 2010-06-25 | 2010-04-20 | 916518 | 2.640
682 | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | YELL |  | 02 | ARR2067 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT 1.25 MILES OF COUNTY ROAD 88 BETWEEN KINGSTON AND HIGHWAY 28 IN YELL COUNTY. | Pavement Improvement | 2010-04-07 | 2010-04-19 | 2011-09-26 | 2011-09-23 | 208241 | 2.500
683 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2068 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 60 AND COUNTRY CLUB ROAD IN THE CITY OF CONWAY IN FAULKNER COUNTY. WORK ITEMS INCLUDE TRAFFIC S | Safety/Traffic Management | 2010-06-04 | 2010-07-22 | 2010-11-12 | 2010-11-09 | 129929 | 0.000
684 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | JEFFERSON | PINE BLUFF | 04 | ARR2069 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL TWO TRAFFIC SIGNALS ON HIGHWAY 65B AT THE INTERSECTIONS OF WALNUT STREET AND CONVENTION CENTER DRIVE IN THE CITY OF PINE BLUFF IN JEFFERSON COUN | Safety/Traffic Management | 2010-08-18 | 2010-12-09 | 2011-02-18 | 2011-04-18 | 219714 | 0.000
685 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | JEFFERSON |  | 04 | ARR2070 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL ON HIGHWAY 190 AT THE INTERSECTION OF OHIO STREET/EAST HARDING AVENUE IN THE CITY OF PINE BLUFF IN JEFFERSON COUNTY. WORK ITEM | Safety/Traffic Management | 2011-02-23 | 2011-03-04 | 2011-09-18 | 2011-08-02 | 84002 | 0.000
686 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLEBURNE |  | 01 | ARR2072 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 25/110 INTERSECTION IN THE CITY OF HEBER SPRINGS IN CLEBURNE COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMEN | Safety/Traffic Management | 2010-08-04 | 2010-10-14 | 2011-02-18 | 2011-02-15 | 96634 | 0.000
687 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | OUACHITA |  | 04 | ARR2073 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 278 AND COUNTRY CLUB ROAD INTERSECTION IN THE CITY OF CAMDEN IN OUACHITA COUNTY. WORK ITEMS INCLUDE TRAFFIC SIG | Safety/Traffic Management | 2010-07-06 | 2010-11-30 | 2011-08-11 | 2011-03-16 | 84304 | 0.000
688 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLARK |  | 04 | ARR2074 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL ON HIGHWAY 51 AT THE INTERSECTION OF 12TH STREET IN THE CITY OF ARKADELPHIA IN CLARK COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 2011-04-04 | 2011-06-11 | 2011-08-11 | 2011-08-11 | 84002 | 0.000
689 | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CRAIGHEAD | JONESBORO | 01 | ARR2075 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 91 AND GEE ST. IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 2010-07-02 | 2010-09-21 | 2011-01-08 | 2011-01-07 | 82409 | 0.000
690 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WASHINGTON | FAYETTEVILLE-SPRINGDALE | 03 | ARR2076 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.74 MILES OF HIGHWAYS 71 AND 71B BETWEEN HIGHWAY 156 AND INTERSTATE 540 IN THE CITY OF FAYETTEVILLE, WASHINGTON COUNTY. WORK INCLUDES PAVEMENT REHABIL | Pavement Improvement | 2010-06-25 | 2010-07-02 | 2010-11-12 | 2010-09-03 | 1042398 | 1.740
691 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | BAXTER, MARION |  | Multiple | ARR2077 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.26 MILES OF HIGHWAY 62 FROM THE TOWN OF GASSVILLE WEST IN BAXTER AND MARION COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GU | Pavement Improvement | 2010-06-25 | 2010-07-19 | 2010-10-03 | 2010-12-09 | 843706 | 3.260
692 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | ARKANSAS | MISSISSIPPI |  | 01 | ARR2078 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.0 MILES OF INTERSTATE 55 FROM SOUTH OF HIGHWAY 61 TO NORTH OF HIGHWAY 18 IN THE CITY OF BLYTHEVILLE, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT RUBBL | Pavement Improvement | 2010-12-16 | 2011-01-24 | 2012-06-20 |  | 19532858 | 10.000
693 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2079 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.7 MILES OF HIGHWAY 65 FROM HWY. 25 NORTH AND SOUTH IN THE CITY OF GREENBRIER, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MA | Pavement Improvement | 2010-09-09 | 2011-02-28 | 2011-04-15 | 2011-04-29 | 1125491 | 9.840
694 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MONTGOMERY |  | 04 | ARR2080 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.51 MILE OF HIGHWAY 27 FROM HWY. 270 SOUTH IN THE CITY OF MOUNT IDA, MONTGOMERY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANC | Pavement Improvement | 2010-09-03 | 2010-10-26 | 2010-12-31 | 2010-12-22 | 1608047 | 7.510
695 | Completed | C200,C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2081 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.66 MILES OF HIGHWAY 65 FROM HWY. 124 NORTH AND SOUTH IN THE CITY OF DAMASCUS, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MA | Pavement Improvement | 2010-09-09 | 2011-04-05 | 2011-06-01 | 2011-04-19 | 488679 | 3.320
696 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2082 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4 RAMPS OFF HIGHWAY 67 IN WHITE COUNTY. WORK WILL INCLUDE PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLAN | Pavement Improvement | 2010-09-13 | 2010-11-23 | 2011-04-15 | 2011-03-31 | 818332 | 0.040
697 | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2083 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 6.56 MILES OF HIGHWAY 67 FROM THE LONOKE COUNTY LINE NORTH IN WHITE COUNTY IN THE CITY OF BEEBE. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MA | Pavement Improvement | 2010-09-03 | 2010-11-10 | 2011-08-01 | 2011-09-16 | 1456205 | 6.560
698 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA, SACRAMENTO, PLACER | SACRAMENTO | Multiple | 000C303 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In Colusa, Placer and Sacramento Counties, at various locations. | Pavement Improvement | 2009-07-02 | 2009-09-18 |  | 2011-03-18 | 6246659 | 1.000
699 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO, SACRAMENTO, PLACER | SACRAMENTO | Multiple | 000C304 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In Sacramento, El Dorado, Yolo and Placer counties, at various locations. | Safety/Traffic Management | 2009-05-18 | 2009-07-27 |  | 2009-12-24 | 1810921 | 1.000
700 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA, PLUMAS |  | Multiple | 000C305 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Tehama and Plumas Counties, as Various Locations. | Pavement Improvement | 2009-06-26 | 2009-07-06 |  | 2009-09-18 | 2629087 | 1.000
701 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 000C306 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Kern and King Counties near Avenal and Devils Den (Sunflower Valley) on State Ro | Pavement Improvement | 2009-07-02 | 2009-07-09 |  | 2009-10-19 | 3891487 | 1.000
702 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO, SAN BERNARDINO |  | 25 | 000C307 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: Shoshone from SR 127 to 0.2 miles E of Chicago Valley in San Bernardino near Baker | Pavement Improvement | 2010-01-28 | 2010-03-17 |  | 2010-09-07 | 1787827 | 5.000
703 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE, SAN BERNARDINO |  | Multiple | 000C313 | This is a Archaeological Planning and Research project by the California Department of Transportation. The project is described as: Various Conventional Routes in Riverside and San Bernardino County | Other | 2010-09-24 | 2010-09-24 |  |  | 1405000 | 1.000
704 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | 0052943 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: In Orange County, on Route 5 from Calle Juanita to 4th Stree | Transportation Enhancements | 2010-05-11 | 2010-09-04 |  |  | 1152094 | 25.100
705 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 0053014 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Sun Valley and Sylmar, from Hollywood Way to north of San Fer | Pavement Improvement | 2009-10-12 | 2009-10-22 |  | 2011-09-28 | 11034118 | 4.900
706 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | STATEWIDE | Multiple | 0053029 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Slab Replacement combined with HOV From Buena Vista to Rte 170 | Safety/Traffic Management | 2010-12-20 | 2011-03-01 |  |  | 39280884 | 4.400
707 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | STATEWIDE | 28 | 0053033 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Slab Replacement Combined with HOV From Rte 170 to Rte 118 | Pavement Improvement | 2010-06-25 | 2010-07-19 |  |  | 31237808 | 3.400
708 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 25 | 0053043 | IN LOS ANGELES COUNTY, IN VALENCIA AND CASTAIC, ROADWAY REHABILITATION (TC) | Pavement Improvement | 2011-02-14 | 2011-02-24 |  |  | 14385735
709 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 0054182 | This is a Safety project by the California Department of Transportation. The project is described as: Near Grapevine, at various locations. | Pavement Improvement | 2009-07-15 | 2009-09-08 |  | 2010-06-30 | 1651958 | 3.800
710 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 0054185 | NEAR BUTTONWILLOW FROM ROUTE 223 TO 7TH STANDARD ROAD, PAVEMENT REHABILITATION (TC) | Pavement Improvement | 2011-01-30 | 2011-02-23 |  |  | 17377362
711 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA |  | 02 | 0058336 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In and near Red Bluff, from 5.3 miles south of Adobe Road Overcr | Pavement Improvement | 2009-07-08 | 2009-08-24 |  | 2011-10-11 | 36407184.43 | 3.400
712 | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | STATEWIDE | 45 | 0103101 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Construct Bob Hope Drive ext and new interchange | Pavement Widening | 2009-12-10 | 2010-02-03 |  |  | 23553000 | 3.000
713 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | Multiple | 0153044 | ON INTERSTATE ROUTE 15 IN SAN BERNARDINO COUNTY ABOUT 25 MILES SOUTH OF THE ***, TRANSPORTATION ENHANCEMENT (LANDSCAPING) (TC) | Transportation Enhancements | 2011-05-11 | 2011-05-16 |  |  | 710010
714 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE |  | 44 | 0155152 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Riverside County in and near Corona, from Temescal Canyon Road to 0.4 mile south | Pavement Improvement | 2009-06-15 | 2009-06-29 |  | 2009-08-05 | 851045 | 5.000
715 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | SAN FRANCISCO-OAKLAND, CA | 03 | 0802356 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Fairfield, from 0.4 mile west of Route 12 to 0.8 mile east of | Pavement Improvement | 2009-04-28 | 2009-05-18 |  | 2010-11-30 | 18312044 | 4.700
717 | Underway | C490 | OJT/SS | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 1002000 | CITY OF LONG BEACH , OJT PACIFIC GATEWAY/CITY LONG BEACH | Other | 2010-10-28 | 2011-06-30 |  |  | 130000
718 | Obligated and Not Awarded | C490 | OJT/SS | CALIFORNIA | STATEWIDE |  |  | 1003000 | STATEWIDE , ASIAN BUSINESS COMMUNITY DEVEL PROG | Other |  |  |  |  | 73217
720 | Underway | C490 | OJT/SS | CALIFORNIA | STATEWIDE |  |  | 1010000 | NORTHERN CA (STATEWIDE), OJT SUPPORTIVE SERVICES TRNG PGM Northern California Teamsters Apprentice Training | Other | 2011-04-04 | 2011-04-04 |  |  | 208543
721 | Underway | C490 | OJT/SS | CALIFORNIA | SACRAMENTO | SACRAMENTO | 05 | 1011000 | OJT SUPPORTIVE SVCS TRNG PGM Sacramento Employment & Training Agency (SETA) | Other | 2011-06-01 | 2011-06-01 |  |  | 338590
723 | Underway | C490 | OJT/SS | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 1014000 | CITY OF LONG BEACH, OJT SUPPORTIVE SERVICES PROGRAM Pacific Gateway | Other | 2011-06-30 | 2011-06-30 |  | 2012-06-29 | 230789
724 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 2056328 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: Near Tracy, on Route 205 from Alameda County line to Route | Transportation Enhancements | 2010-06-10 | 2010-06-14 |  | 2011-04-01 | 1207301 | 12.600
725 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 2101795 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Los Angeles County in and near Pasadena, from State Route 2-A | Pavement Improvement | 2009-09-16 | 2009-11-09 |  | 2010-07-02 | 341883 | 5.400
726 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN FRANCISCO-OAKLAND, CA | Multiple | 2801119 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In San Jose, from Cypress Avenue Pedestrian Overcrossing to Tant | Pavement Improvement | 2009-07-29 | 2009-09-09 |  | 2010-07-14 | 11304295 | 2.700
727 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 2801122 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In San Mateo County from Santa Clara County line to San Francisco County | Safety/Traffic Management | 2009-10-08 | 2009-12-16 |  | 2011-03-28 | 1705293 | 27.400
728 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 2801126 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Ramp Meters at 9 Locations | Safety/Traffic Management | 2010-04-07 | 2010-05-03 |  | 2011-10-26 | 2985656 | 3.000
729 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | Multiple | 2801127 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Ramp Meters at 8 Locations | Safety/Traffic Management | 2010-04-28 | 2010-05-10 |  | 2011-07-13 | 3248320 | 3.500
730 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 2801129 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Ramp Meters at 7 Locations | Safety/Traffic Management | 2010-03-08 | 2010-06-02 |  | 2012-01-06 | 4182612 | 7.000
731 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 4053015 | This is a Design-Build Contract project by the California Department of Transportation. The project is described as: Widen NB I-405 for HOV Lane | Safety/Traffic Management | 2009-06-02 | 2009-06-02 |  |  | 189900000 | 10.200
732 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 05 | 5002138 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sacramento. The project is described as: Rehabilitate various roadways in Sacramento | Pavement Improvement | 2009-08-26 | 2009-08-27 |  | 2010-01-11 | 5246052 | 1.000
733 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5002140 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sacramento. The project is described as: VARIOUS LOCATIONS W/IN THE CITY OF SACRAMENTO , AC OVERLAYS PHASE I | Pavement Improvement | 2009-08-26 | 2009-09-08 |  | 2009-11-30 | 2810571 | 1.000
734 | Underway | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 05 | 5002142 | This is a Transit project by a local agency in the City of Sacramento. The project is described as: Sacramento railyard track relocation | Other | 2011-04-06 | 2011-04-15 |  |  | 21047897 | 0.000
735 | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | STATEWIDE | 07 | 5003023 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Benicia. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2009-12-17 | 2009-12-17 |  | 2010-12-17 | 491800 | 0.200
736 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VALLEJO | 07 | 5003024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Benicia. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-26 | 2009-10-26 |  | 2009-12-04 | 219195.58 | 0.590
737 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5005096 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Jose. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-06 | 2009-10-19 |  | 2010-12-31 | 8502466 | 8.650
738 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | STATEWIDE | 16 | 5005099 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Jose. The project is described as: Rehabilitate Local Streets. | Pavement Improvement | 2010-05-17 | 2010-05-28 |  | 2011-03-01 | 6116534 | 4.380
739 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5006569 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Angeles. The project is described as: LAX HOSPITALITY ZONE STREET AND SIDEWALK REHABILITATION - PHASE II | Pavement Improvement | 2009-07-06 | 2009-07-07 |  |  | 7000000 | 3.850
740 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5006571 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: COMMERCE AVE PEDESTRIAN IMPROVEMENTS: THIS IS A PILOT PROJECT TO I | Pavement Improvement | 2009-07-06 | 2009-07-06 |  | 2010-06-30 | 900000 | 0.500
741 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5006574 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: LAUSD VALLEY REGION HS #4 PEDESTRIAN IMPROVEMENTS: THIS PROJECT WI | Pavement Improvement | 2011-08-29 | 2011-09-19 |  |  | 300000 | 0.500
742 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006577 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES NORTH CENTRAL REGION RESURFACING PROJECT- PHASE II: THIS PROJECT | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 7275000 | 14.000
743 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006578 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES WEST VALLEY REGION RESURFACING PROJECT - PHASE II: THIS PROJECT W | Pavement Improvement | 2009-07-01 | 2009-07-02 |  |  | 7275000 | 18.000
744 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5006579 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES EAST VALLEY REGION RESURFACING PROJECTS - PHASE II: THIS PROJECT | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 7275000 | 16.000
745 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006580 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES BAY HARBOR REGION RESURFACING PROJECTS - PHASE II: THIS PROJECT W | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 7275000 | 16.500
746 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006581 | This is a Safety project by a local agency in the City of Los Angeles. The project is described as: INSTALLATION OF LEFT TURN ARROWS CITYWIDE | Safety/Traffic Management | 2011-01-03 | 2011-01-24 |  | 2011-09-30 | 4000000 | 1.000
747 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006582 | This is a Transit project by a local agency in the City of Los Angeles. The project is described as: TRANSIT PRIORITY SYSTEM (TPS) AND ATSAC COMMUNICATION SYSTEM REHABILITATION | Safety/Traffic Management | 2010-06-01 | 2010-06-08 |  |  | 5598697 | 0.000
748 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006586 | This is a Traffic Management Engineering project by a local agency in the City of Los Angeles. The project is described as: SIGNAL LED RETROFIT PROGRAM - PHASE I. | Safety/Traffic Management | 2009-07-01 | 2009-09-01 |  |  | 9000000 | 1.000
749 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006589 | This is a Safety project by a local agency in the City of Los Angeles. The project is described as: NEW TRAFFIC SIGNALS | Safety/Traffic Management | 2011-01-03 | 2011-01-24 |  | 2011-09-30 | 3500000 | 1.000
750 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006591 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: THE PROJECT IS TO UPGRADE ROADWAYS GRATES NEAR OR ALONG BIKE PATHS | Transportation Enhancements | 2010-04-21 | 2010-06-01 |  | 2011-02-28 | 524780 | 1.000
751 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006592 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: THE PROJECT IS TO UPGRADE ROADWAYS GRATES NEAR OR ALONG BIKE PATHS | Safety/Traffic Management | 2010-03-01 | 2010-03-01 |  |  | 1555275 | 1.000
752 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006593 | This is a Rail/Highway Crossing project by a local agency in the City of Los Angeles. The project is described as: HIGHWAY-RAIL GRADE CROSSING IMPROVEMENT SYSTEM. PROVIDE UPGRADES TO TRAFFIC SIGNAL E | Pavement Improvement | 2010-11-29 | 2010-12-13 |  |  | 2769303 | 1.000
753 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006595 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: CITY OF LOS ANGELES BAY HARBOR REGION RESURFACING PROJECTS - PHASE I: THIS PROJECT WI | Pavement Improvement | 2009-07-01 | 2009-07-01 |  |  | 15588000 | 10.250
754 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5006597 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: Construct bikeway and parkway along Los Angeles River between Vana | Pavement Improvement | 2010-10-26 | 2011-03-07 |  |  | 3700372.56 | 1.000
755 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006598 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: AC resurfacing at 4 locations: Colfax Ave btwn Moorpark St/Ventura | Pavement Improvement | 2010-10-18 | 2010-11-02 |  |  | 2700000 | 1.000
756 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5006601 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: Construct bikeway and parkway along LA River between Tampa Ave and | Pavement Improvement | 2011-02-11 | 2011-05-06 |  |  | 2000000 | 1.000
757 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006602 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Los Angeles. The project is described as: HARRY S BRIDGES BLVD RELOCATION/CONSOLIDATION OF STREETS, STREET I | Pavement Improvement | 2010-03-22 | 2010-03-22 |  |  | 15545200 | 1.110
758 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006674 | CITYWIDE AT RR CROSSINGS / CITY OF LOS ANGELES (SEE ATTACHED FOR LOCATIONS), HIGHWAY-RAIL GRADE CROSSING SURFACE RECONSTRUCTION | Pavement Improvement | 2010-07-02 | 2010-07-02 |  |  | 7932000
759 | Underway | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5007046 | This is a Pavement Resurfacing project by a local agency in the City of Santa Barbara. The project is described as: Overlay and pavement maintenance to streets on Federal list of eligible roads. | Pavement Improvement | 2010-04-15 | 2010-05-24 |  |  | 2674796 | 1.000
760 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5007047 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Barbara. The project is described as: Citywide Pedestrian Countdown Timers: Place new pedestrian count | Transportation Enhancements | 2010-06-03 | 2010-06-03 |  | 2010-12-30 | 300000 | 1.000
761 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5007048 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Barbara. The project is described as: Access ramp and sidewalk maintenance improvements in City ROW (R | Transportation Enhancements | 2010-06-30 | 2010-07-12 |  | 2011-07-11 | 800000 | 1.000
762 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5008087 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Stockton. The project is described as: Rehabilitation of 24 streets in the City of Stockton | Pavement Improvement | 2009-10-01 | 2009-10-20 |  |  | 6141391 | 14.000
763 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5008091 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Stockton. The project is described as: Rubberized cape seal of 72 streets in the City of Stockton. | Pavement Improvement | 2011-08-01 | 2011-08-10 |  |  | 2603160 | 31.000
764 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5008092 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Stockton. The project is described as: Enhancement of existing roadway. | Transportation Enhancements | 2010-06-01 | 2010-06-07 |  | 2010-11-19 | 894955 | 0.400
765 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA | SACRAMENTO | 02 | 5009027 | This is a Traffic Management Engineering project by a local agency in the City of Marysville. The project is described as: Install a new traffic signal, complete pedestrian and landscaping improvemen | Pavement Improvement | 2010-05-18 | 2010-05-24 |  |  | 43000 | 1.000
766 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | 5009028 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Marysville. The project is described as: Rehabilitate 3rd: D-J Sts; J St: 3rd-5th | Pavement Improvement | 2011-10-05 |  |  |  | 1386215 | 1.000
767 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5012098 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Oakland. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-02-15 | 2010-04-12 |  |  | 1118832 | 1.000
768 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5012099 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakland. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-03-01 | 2010-04-12 |  |  | 3857444 | 5.580
769 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5012100 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Oakland. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-04-26 | 2010-05-19 |  |  | 1300000 | 0.500
770 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN JOSE, CA | 09 | 5012101 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakland. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-12-20 | 2010-12-20 |  |  | 1255000 | 9.170
771 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | STATEWIDE | 09 | 5012104 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakland. The project is described as: Resurfacing of several pavement segments plus ADA curb ramps and ancil | Pavement Improvement | 2010-12-22 | 2010-12-22 |  |  | 991725 | 3.010
772 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5013012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Crescent City. The project is described as: Rehabilitate 5th St.: A St. to Wendell St | Pavement Improvement | 2010-06-02 | 2010-06-07 |  | 2010-07-08 | 79750 | 0.060
773 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5013013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Crescent City. The project is described as: ADA improvements on H St. from 11th to Front Streets. | Transportation Enhancements | 2010-06-02 | 2010-06-17 |  | 2010-08-27 | 146044 | 0.570
774 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5014032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alameda. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-07 | 2009-08-07 |  |  | 1304000 | 1.040
775 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | CONCORD | 13 | 5014033 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Alameda. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-05-24 | 2010-05-24 |  | 2011-03-01 | 350000 | 0.440
776 | Completed | C250,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO | SACRAMENTO | 04 | 5015013 | This is a Pavement Resurfacing project by a local agency in the City of Placerville. The project is described as: Cold Springs Road, from Placerville City Limit to Sleepy Hollow Road: Rehabilitate ro | Pavement Improvement | 2009-11-16 | 2009-11-16 |  | 2010-03-09 | 415584 | 0.800
777 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO | SACRAMENTO | 04 | 5015018 | MORRENE DR: HOCKING ST TO GIOVANNI DR AND HOCKING ST: MOSQUITO RD TO MORRENE DR, ROADWAY REHABILITATION / ADA CURB RAMPS (VAR) | Pavement Improvement | 2011-08-15 | 2011-08-16 |  |  | 256179.83
778 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 23 | 5016049 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of San Luis Obispo. The project is described as: Pavement and Sidewalk Replacement on Monterey Street from | Pavement Improvement | 2011-01-04 | 2011-01-31 |  | 2011-05-17 | 1168343.42 | 0.500
779 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5017023 | This is a Pavement Resurfacing project by a local agency in the City of Eureka. The project is described as: Street grind, patch and overlay | Pavement Improvement | 2009-10-29 | 2010-05-10 |  | 2010-10-05 | 656094.99 | 3.530
780 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5017024 | This is a Pavement Resurfacing project by a local agency in the City of Eureka. The project is described as: Rehabilitation and paving | Pavement Improvement | 2010-08-27 | 2010-09-07 |  | 2011-01-31 | 329925 | 0.230
781 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5018017 | This is a Pavement Resurfacing project by a local agency in the City of Nevada City. The project is described as: Broad St. from Union St. to SR 49 | Pavement Improvement | 2010-09-01 | 2010-09-27 |  | 2010-10-01 | 120438 | 0.700
782 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | STATEWIDE | 15 | 5019022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clara. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-11-02 | 2009-11-02 |  | 2010-11-16 | 1110415 | 4.800
783 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5019023 | This is a Traffic Management Engineering project by a local agency in the City of Santa Clara. The project is described as: Install technology improvements | Safety/Traffic Management | 2009-09-28 | 2009-09-28 |  | 2010-09-28 | 404585 | 1.290
784 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5020015 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Yreka. The project is described as: Crosswalk & bike lane striping, bike ped signs on existing posts. Greenh | Transportation Enhancements | 2011-03-28 | 2011-06-06 |  | 2011-06-16 | 82173 | 0.250
785 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5021015 | SAMOA BLVD FROM UNION AVE TO 100FT S OF BUTTERMILK LN (.49MI), AC OVERLAY AND RECONSTRUCTION | Pavement Improvement | 2011-06-27 | 2011-07-28 |  | 2011-10-31 | 136835
786 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5021016 | This is a Pavement Resurfacing project by a local agency in the City of Arcata. The project is described as: Asphalt overlay on Alliance Road, including striping and ADA curb ramp work | Pavement Improvement | 2010-07-23 | 2010-08-10 |  | 2011-01-31 | 390317.89 | 0.700
787 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5021017 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Arcata. The project is described as: Bike and Pedestrian Improvements along Samoa Blvd | Transportation Enhancements | 2011-07-19 | 2011-07-19 |  |  | 1445181 | 1.150
788 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5022044 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Petaluma. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-10 | 2009-09-28 |  | 2010-03-01 | 561046.76 | 1.010
789 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5022045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Petaluma. The project is described as: Rehabilitate Local Streets - Lynch Creek Rd to Dynamic St. | Pavement Improvement | 2010-03-08 | 2010-04-06 |  | 2010-06-21 | 728000 | 0.650
790 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5023009 | This is a Pavement Resurfacing project by a local agency in the City of Grass Valley. The project is described as: S. Auburn St. from Hwy 20/49 to E. Main St. | Pavement Improvement | 2008-10-10 | 2010-05-28 |  | 2010-08-19 | 506565 | 0.220
791 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 07 | 5024023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Martinez. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-14 | 2009-09-14 |  | 2009-12-31 | 850000 | 4.200
792 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 07 | 5024024 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Martinez. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-03-15 | 2010-03-29 |  |  | 756299 | 0.600
793 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: Road repairs: Morrissey Blvd from Soquel Ave to Fairmount | Pavement Improvement | 2009-08-18 | 2009-08-31 |  | 2009-11-16 | 388682 | 0.200
794 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: Road repairs: Market St from Water to SR1 | Pavement Improvement | 2009-08-18 | 2009-09-04 |  | 2009-11-16 | 272210.98 | 0.500
795 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025047 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: Road repairs: West Cliff Dr from Almar Blvd to Bay St | Pavement Improvement | 2009-08-18 | 2009-08-18 |  | 2009-11-20 | 689107 | 1.600
796 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025049 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Cruz. The project is described as: Road Repairs various locations | Pavement Improvement | 2010-04-05 | 2010-04-13 |  | 2010-06-11 | 1000000 | 1.930
797 | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025050 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Cruz. The project is described as: 2 roundabouts - Pacific Ave/Beach St/Wharf intersection and Paci | New Construction | 2010-10-06 | 2010-10-11 |  | 2011-11-15 | 750000 | 0.300
798 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025052 | WITH IN THE CITY OF STANTA CRUZ ON WEST CLIFF DR FROM ALAMAR TO SWANTON BLVD, OVERLAY ROADWAY | Pavement Improvement | 2011-06-09 | 2011-06-13 |  | 2011-10-31 | 300000
799 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5026043 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Buena Ventura. The project is described as: Steet Rehab. Olive Street Phase I | Pavement Improvement | 2010-01-05 | 2010-01-06 |  | 2010-10-01 | 530943 | 1.000
800 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5026044 | This is a Safety project by a local agency in the City of San Buena Ventura. The project is described as: Traffic Signal at intersection of Kimball & Foothill Rd. | Other | 2010-04-29 | 2010-05-03 |  | 2010-10-29 | 207911.97 | 1.000
801 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5026046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Buena Ventura. The project is described as: Street Rehab Olive Street Ph. II and Poli/Foothill | Pavement Improvement | 2010-05-10 | 2010-05-11 |  | 2011-02-15 | 587006.84 | 1.000
802 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5026047 | WELLS ROAD FROM FOOTHILL RD. TO TELEGRAPH RD., STREET OVERLAY | Pavement Improvement | 2011-04-21 | 2011-04-25 |  | 2011-11-03 | 263782.38
803 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5027014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Healdsburg. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-08 | 2009-09-18 |  | 2010-08-20 | 500000 | 2.470
804 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5028053 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Rosa. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-30 | 2009-11-02 |  | 2011-01-01 | 2803347.73 | 2.100
805 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5028054 | This is a Traffic Management Engineering project by a local agency in the City of Santa Rosa. The project is described as: Installation of adaptive traffic control equipment on Mendocino Ave corridor | Safety/Traffic Management | 2010-10-28 | 2010-11-01 |  | 2010-12-07 | 824099.94 | 1.600
806 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5028057 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Rosa. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-10-18 | 2011-03-11 |  | 2011-09-12 | 840920 | 1.000
807 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | Multiple | 5029020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Redwood City. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-08 | 2009-09-10 |  | 2010-06-28 | 688774.6 | 1.500
808 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5029021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Redwood City. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-11-02 | 2009-11-02 |  | 2011-03-07 | 523000 | 0.250
809 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VALLEJO | 07 | 5030048 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Vallejo. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2009-12-14 | 2009-12-14 |  | 2011-08-01 | 2207700 | 0.850
810 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VALLEJO | 07 | 5030049 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Vallejo. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-05 | 2009-10-05 |  | 2010-06-07 | 1020000 | 1.330
811 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5031018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Watsonville. The project is described as: Road repairs: various roadways | Pavement Improvement | 2009-08-13 | 2009-08-18 |  | 2010-01-26 | 1182751.76 | 10.000
812 | Underway | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5031019 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Watsonville. The project is described as: Road repairs and fill gaps in sidewalks and bicycle facilities. | Pavement Improvement | 2010-07-01 | 2010-08-02 |  |  | 2066357 | 0.800
813 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | FAIRFIELD | 10 | 5032022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Suisun City. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-07 | 2009-10-13 |  | 2010-06-15 | 700000 | 0.700
814 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | STATEWIDE | 10 | 5032024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Suisun City. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-08-23 | 2010-09-07 |  | 2011-09-30 | 670000 | 1.000
815 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5034020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Gilroy. The project is described as: Rehabilitate local street | Transportation Enhancements | 2010-01-18 | 2010-02-16 |  | 2010-07-10 | 659603.68 | 9.400
816 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5035010 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Colusa. The project is described as: On Fremont Street from 10th Street (SR20) to 3rd Street in the City of | Transportation Enhancements | 2010-08-09 | 2010-08-09 |  | 2010-11-17 | 130000 | 0.530
817 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5035011 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Colusa. The project is described as: On 5th Street from Webster Street to Oak Street in the City of Colusa, | Transportation Enhancements | 2010-08-09 | 2010-08-09 |  | 2010-11-17 | 236464 | 0.210
818 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5036010 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Trinidad. The project is described as: Sidewalk/Path Improvements to Trinidad Center | Transportation Enhancements | 2010-04-01 | 2010-04-16 |  | 2010-07-15 | 20000 | 0.760
819 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE | CHICO | 02 | 5037016 | This is a Traffic Management Engineering project by a local agency in the City of Chico. The project is described as: Reconstruct Interchange, improve operations | Pavement Widening | 2010-02-01 | 2010-02-18 |  |  | 5500000 | 0.600
820 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE | CHICO | 02 | 5037018 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Chico. The project is described as: Phase 1 - In the City of Chico thru the urbanized area construct class | Transportation Enhancements | 2010-10-04 | 2010-10-04 |  |  | 2425000 | 6.700
821 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10 | 5038021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Antioch. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-14 | 2009-10-01 |  | 2010-08-10 | 1604963.12 | 3.200
822 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA |  | 01 | 5039021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cloverdale. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-25 | 2009-08-31 |  | 2009-10-28 | 399868 | 1.600
823 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5041033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Leandro. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-17 | 2009-09-28 |  | 2010-09-10 | 1029885 | 0.650
824 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5041034 | This is a Pavement Resurfacing project by a local agency in the City of San Leandro. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-04-30 | 2010-05-07 |  | 2010-09-30 | 344274.04 | 0.270
825 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5041035 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Leandro. The project is described as: Reconstruct street surface of Bancroft Ave from 138th Ave to 148th | Pavement Improvement | 2010-10-01 | 2010-10-18 |  | 2011-01-03 | 308115 | 0.600
826 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA | SAN FRANCISCO-OAKLAND, CA | 01 | 5042048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Napa. The project is described as: Widen sidewalk to better accommodate pedestrian and bicycle traffic on N. | Transportation Enhancements | 2010-06-14 | 2010-06-28 |  | 2010-10-26 | 147806 | 1.000
827 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA | STATEWIDE | 01 | 5042049 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Napa. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-04 | 2009-09-14 |  | 2010-11-23 | 1619131.15 | 1.400
828 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5043030 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Rafael. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-23 | 2009-10-07 |  | 2010-01-27 | 1188000 | 3.330
829 | Underway | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE | VISALIA | 21 | 5044051 | This is a Traffic Management Engineering project by a local agency in the City of Visalia. The project is described as: Widening of Ben Maddox Bridge over SR-198 from 5-8 lanes (2 thru lanes each dir | Bridge Improvement | 2010-03-22 | 2010-04-23 |  |  | 5400000 | 0.790
830 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE | VISALIA | 21 | 5044054 | This is a Pavement Resurfacing project by a local agency in the City of Visalia. The project is described as: City of Visalia - Street Rehabilitation - Major Overlays | Pavement Improvement | 2010-07-07 | 2010-07-26 |  | 2010-11-02 | 546207 | 1.920
831 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE | VISALIA | 21 | 5044060 | ON WALNUT AVE AND MOONEY BLVD(SR 63), ROAD WIDENING AND INTERSECTION IMPROVEMENT | Pavement Widening | 2011-06-16 | 2011-06-27 |  |  | 1250000
832 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5045023 | This is a Pavement Resurfacing project by a local agency in the City of Salinas. The project is described as: Reconstruct between Natividad and North Sanborn Roads | Pavement Improvement | 2009-08-31 | 2009-08-31 |  | 2010-04-05 | 2795486.64 | 1.000
833 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5045024 | This is a Historic Preservation project by a local agency in the City of Salinas. The project is described as: Exterior Improvements to Historical Salinas First Mayor House. Located at the Salinas I | Transportation Enhancements | 2010-07-01 | 2010-07-01 |  | 2011-04-12 | 176999.72 | 0.000
834 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5045025 | CONSTITUTION BLVD AND EAST LAUREL DRIVE, ROADWAY REPAIRS AND LANDSCAPING | Pavement Improvement | 2010-11-23 | 2010-11-23 |  | 2011-04-14 | 157321.24
835 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 01 | 5046029 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Woodland. The project is described as: CR 102, from East Beamer St to Hanson Wy: Rehabilitate roadway. | Pavement Improvement | 2009-09-21 | 2009-09-21 |  | 2009-11-18 | 655725 | 1.000
836 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 01 | 5046030 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Woodland. The project is described as: Install street lighting. | Pavement Improvement | 2010-07-02 | 2010-07-19 |  | 2011-03-31 | 541446.92 | 1.000
837 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 01 | 5046033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Woodland. The project is described as: Rehabilitate pavement on Ashley Avenue from El Dorado to Kentucky, Co | Pavement Improvement | 2010-06-22 | 2010-07-06 |  | 2010-08-15 | 327863 | 5.570
838 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BENITO |  | 17 | 5047015 | This is a Pavement Resurfacing project by a local agency in the City of Hollister. The project is described as: Repair and provide asphalt overlay to existing City surface streets | Pavement Improvement | 2010-07-19 | 2010-07-19 |  | 2010-10-13 | 1226091 | 1.540
839 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | 5048004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Wheatland. The project is described as: Rehabilitate Main St: SR 65-Olive St | Pavement Improvement | 2009-10-23 | 2009-11-05 |  | 2010-04-15 | 486258.91 | 1.000
840 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5049022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Ukiah. The project is described as: Rehabilitation of South Dora Street from the northernmost intersection w | Pavement Improvement | 2010-09-30 | 2010-10-18 |  | 2011-06-30 | 438000 | 0.320
841 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5050036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hayward. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-07-24 | 2009-07-27 |  | 2009-11-19 | 2037000 | 3.880
842 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5050037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hayward. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-11-20 | 2009-11-30 |  | 2010-06-07 | 475000 | 2.150
843 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 10 | 5053018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Livermore. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-10 | 2009-08-10 |  | 2009-12-10 | 1322261.59 | 1.130
844 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | CONCORD | 10 | 5053020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Livermore. The project is described as: Rehabilitate local street. | Pavement Improvement | 2010-06-21 | 2010-06-21 |  | 2010-09-14 | 350000 | 0.580
845 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5055155 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Street pavement rehabilitation / reconstruction, including curb ramps, utility adjustment | Pavement Improvement | 2010-04-05 | 2010-04-05 |  | 2010-06-21 | 725390.09 | 0.670
846 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5055156 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Street pavement rehabilitation / reconstruction, including curb ramps, utility adjustment | Pavement Improvement | 2010-03-22 | 2010-03-22 |  | 2010-06-11 | 675796.83 | 0.460
847 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5055157 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Street pavement rehabilitation / reconstruction, including curb ramps, utility adjustment | Pavement Improvement | 2010-04-26 | 2010-04-26 |  | 2010-08-06 | 539193 | 0.800
848 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5055158 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Street pavement rehabilitation / reconstruction, including curb ramps, utility adjustment | Pavement Improvement | 2010-03-22 | 2010-03-22 |  | 2010-05-24 | 276030 | 0.380
849 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | STATEWIDE | 47 | 5055159 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Street pavement rehabilitation / reconstruction, including curb ramps, utility adjustmen | Pavement Improvement | 2011-02-09 | 2011-02-09 |  | 2011-04-28 | 659712.58 | 0.600
850 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5055160 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Street pavement rehabilitation / reconstruction, including curb ramps, utility adjustmen | Pavement Improvement | 2011-01-18 | 2011-01-18 |  | 2011-02-23 | 506168 | 0.190
851 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO |  | 10 | 5056016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Dixon. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-19 | 2009-10-20 |  | 2010-02-23 | 299247.9 | 0.520
852 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | SANTA ROSA | 10 | 5056017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Dixon. The project is described as: Paving Stratford Ave between Pitts school road to Weyard Way. | Pavement Improvement | 2010-07-09 | 2010-07-12 |  | 2010-08-24 | 148860.85 | 0.200
853 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5057032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Berkeley. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-18 | 2009-09-24 |  | 2010-05-21 | 1522313.39 | 0.560
854 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5057033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Berkeley. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-02-05 | 2010-03-01 |  | 2010-06-10 | 400000 | 0.260
855 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | SAN BERNARDINO-RIVERSIDE | 44 | 5058079 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Riverside. The project is described as: Install median landscaping | Transportation Enhancements | 2009-12-21 | 2009-12-21 |  | 2010-05-20 | 348176 | 1.000
856 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | Multiple | 5059160 | This is a Pavement Resurfacing project by a local agency in the City of Modesto. The project is described as: Cape and Slurry Various Streets. | Pavement Improvement | 2010-05-24 | 2010-05-24 |  |  | 2809187 | 30.000
857 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 19 | 5059166 | This is a Pavement Resurfacing project by a local agency in the City of Modesto. The project is described as: Cape and Slurry Various Streets/American Disability Act (ADA) Sidewalk Curb Ramp Improvem | Pavement Improvement | 2010-09-13 | 2010-11-03 |  |  | 3671452 | 10.000
858 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060165 | This is a Safety project by a local agency in the City of Fresno. The project is described as: Various traffic signal installation at various location. Consistent with 40 CFR part 93.126, 127, 128, e | Pavement Improvement | 2010-05-07 | 2010-05-07 |  | 2011-03-01 | 270683.15 | 1.000
859 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5060166 | This is a Traffic Management Engineering project by a local agency in the City of Fresno. The project is described as: Traffic signal installation at various location. Consistent with 40 CFR part 93. | Pavement Improvement | 2010-05-25 | 2010-05-25 |  | 2010-11-02 | 284377.58 | 1.000
860 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5060167 | This is a Traffic Management Engineering project by a local agency in the City of Fresno. The project is described as: Traffic signal installation at various location. Consistent with 40 CFR part 93. | Pavement Improvement | 2010-04-02 | 2010-04-02 |  | 2010-12-10 | 300000 | 1.000
861 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5060168 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent with 40 CFR part 93.126 | Pavement Improvement | 2010-04-07 | 2010-05-24 |  | 2010-08-20 | 663969.6 | 2.000
862 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5060169 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent with 40 CFR part 93.126, | Pavement Improvement | 2010-07-22 | 2010-07-22 |  | 2010-09-15 | 495025 | 1.000
863 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060170 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent with 40 CFR part 93.126, | Pavement Improvement | 2010-07-08 | 2010-07-08 |  | 2010-08-25 | 908021.33 | 1.500
864 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060171 | This is a Safety project by a local agency in the City of Fresno. The project is described as: Various traffic signal installation at various location. Consistent with 40 CFR part 93.126, 127, 128, e | Pavement Improvement | 2010-05-07 | 2010-05-07 |  | 2011-03-03 | 222302.93 | 1.000
865 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060172 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent with 40 CFR part 93.126, | Pavement Improvement | 2010-04-26 | 2010-04-26 |  | 2010-08-22 | 1522297.35 | 3.000
866 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060178 | This is a Safety project by a local agency in the City of Fresno. The project is described as: Various traffic signal installation at various location. Consistent with 40 CFR part 93.126, 127, 128, e | Pavement Improvement | 2010-09-20 | 2010-09-20 |  | 2011-06-02 | 375000 | 1.000
867 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060181 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Fresno. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent wi | Pavement Improvement | 2010-05-28 | 2010-05-28 |  | 2010-09-30 | 1158739.49 | 0.850
868 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5060183 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Fresno. The project is described as: Median Island Landscaping, Clovis Ave. Between SR 180 and McKinley | Transportation Enhancements | 2010-05-24 | 2010-05-24 |  | 2010-08-20 | 137089 | 1.000
869 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5060185 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Lump-Sum Various AC Overlays/Reconstruction on Eligible Routes. Consistent with 40 CFR pa | Pavement Improvement | 2010-08-11 | 2010-08-11 |  | 2010-09-30 | 298772.38 | 0.500
870 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5060189 | HERNDON AVENUE FROM CEDAR TO WILLOW AVENUES, AC OVERLAY | Pavement Improvement | 2010-10-24 | 2010-10-24 |  | 2011-01-07 | 1047000
871 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5060190 | CEDAR AVENUE FROM CLINTON TO GETTYSBURG AVENUES, AC OVERLAY | Pavement Improvement | 2011-08-30 | 2011-08-30 |  | 2011-12-11 | 740000
872 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060191 | N/B FRIANT RD. FROM FRESNO ST. TO CHAMPLAIN AVENUE, AC OVERLAY | Pavement Improvement | 2011-07-11 | 2011-07-11 |  | 2011-10-28 | 654000
873 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5062013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Willows. The project is described as: Road rehabilitation | Pavement Improvement | 2010-06-14 | 2010-06-18 |  | 2010-10-10 | 384095.42 | 0.500
874 | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5062014 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Willows. The project is described as: TE landscaping with walks, bark, weed barriers and irrigation. | Transportation Enhancements | 2010-10-21 | 2010-11-01 |  | 2010-11-19 | 83739.15 | 0.930
875 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5062015 | TEHAMA STREET BETWEEN CR53 AND CEDAR STREET, ROAD REHAB | Pavement Improvement | 2010-10-18 | 2010-10-29 |  | 2010-11-18 | 156993.86
876 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5062016 | TEHAMA STREET FROM CR57 TO SOUTH CITY LIMITS, ROAD REHAB | Pavement Improvement | 2010-10-18 | 2010-10-29 |  | 2010-11-18 | 117460.58
877 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5063131 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Ana. The project is described as: Roadway Rehabilitation Non-capacity Adding | Pavement Improvement | 2010-01-04 | 2010-01-04 |  | 2010-07-02 | 634368 | 0.400
878 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5063132 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Ana. The project is described as: Roadway Rehabilitation Non-capacity Adding | Pavement Improvement | 2010-01-04 | 2010-01-04 |  | 2010-07-02 | 599048 | 0.500
879 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5063133 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Ana. The project is described as: Roadway Rehabilitation Non-capacity Adding | Pavement Improvement | 2010-01-04 | 2010-01-04 |  | 2010-07-02 | 632035 | 0.400
880 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5063138 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Ana. The project is described as: Roadway Rehabilitation Non-capacity Adding | Pavement Improvement | 2010-10-18 | 2010-10-18 |  | 2011-03-11 | 677253 | 1.100
881 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5064061 | This is a Pavement Resurfacing project by a local agency in the City of Pasadena. The project is described as: RESURFACING VARIOUS STREETS WITHIN THE CITY OF PASADENA ON THE SELECT STREET SYSTEM WITH | Pavement Improvement | 2010-04-12 | 2010-04-16 |  | 2011-04-30 | 4331000 | 9.800
882 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5067014 | This is a Traffic Management Engineering project by a local agency in the City of Los Gatos. The project is described as: Intersection improvements and signal upgrade | Safety/Traffic Management | 2009-07-20 | 2010-01-04 |  | 2010-06-21 | 453295 | 0.250
883 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5067015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Gatos. The project is described as: Overlay street Prospect Road (College Ave to Town limit). This inclu | Pavement Improvement | 2010-04-06 | 2010-04-19 |  | 2010-06-21 | 177705 | 0.500
884 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA | REDDING | 02 | 5068028 | This is a New Construction Roadway project by a local agency in the City of Redding. The project is described as: Construct South Bound Loop On-Ramp and Signals | Pavement Widening | 2010-07-12 | 2010-07-15 |  |  | 2746952 | 0.100
885 | Completed | C250,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5068029 | This is a Pavement Resurfacing project by a local agency in the City of Redding. The project is described as: 6.05 miles of Preventative Maintenance on major local streets | Pavement Improvement | 2010-09-09 | 2010-09-20 |  | 2010-11-12 | 849765 | 6.050
886 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 28 | 5069009 | This is a Pavement Resurfacing project by a local agency in the City of Monrovia. The project is described as: 07/11 STREET RESURFACING PROJECT | Pavement Improvement | 2011-03-14 | 2011-03-28 |  | 2011-06-30 | 995000 | 4.400
887 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 28 | 5069011 | This is a Traffic Management Engineering project by a local agency in the City of Monrovia. The project is described as: TRAFFIC SIGNAL IMPROVEMENTS - MYRTLE AND CHESTNUT AND MYRTLE AND HUNTINGTON | Pavement Improvement | 2010-11-17 | 2011-01-10 |  |  | 160999.99 | 1.000
888 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5070017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pomona. The project is described as: STREET IMPROVEMENTS - WHITE AVENUE (ORANGE GROVE AVE TO NORTH CITY LIMI | Pavement Improvement | 2011-12-22 | 2012-01-03 |  |  | 2704719 | 1.500
889 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5070018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pomona. The project is described as: STREET IMPROVEMENTS - TOWNE AVENUE (LEXINGTON AVE TO RIVERSIDE DR.) PH | Pavement Improvement | 2010-02-08 | 2010-04-05 |  | 2010-06-25 | 1016990.63 | 1.250
890 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5071018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South Pasadena. The project is described as: FAIR OAKS AV CORRIDOR & COLUMBIA ST STREET IMPROVEMENTS -- MED | Safety/Traffic Management | 2010-10-12 | 2010-10-25 |  |  | 761000 | 1.300
891 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | 5072047 | This is a Traffic Management Engineering project by a local agency in the City of Tulare. The project is described as: City of Tulare - Resurfacing Prosperity Ave from east of Cherry to Oaks | Pavement Improvement | 2010-07-20 | 2010-08-16 |  | 2011-02-15 | 333000 | 0.600
892 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5072048 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Tulare. The project is described as: Lighting for the City of Tulare Santa Fe Bike/Pedestrian Trail | Transportation Enhancements | 2010-07-26 | 2010-08-02 |  | 2011-05-17 | 186616.87 | 1.000
893 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5073062 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Orange. The project is described as: Street pavement rehabilitation | Pavement Improvement | 2010-05-17 | 2010-07-12 |  | 2010-12-14 | 1465302.32 | 1.170
894 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5073065 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Orange. The project is described as: Construction of a Class I bike trail along the Santiago Creek from Tust | Transportation Enhancements | 2010-09-08 | 2010-10-04 |  |  | 1889000 | 2.000
895 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LAKE |  | 01 | 5076007 | This is a Pavement Resurfacing project by a local agency in the City of Lakeport. The project is described as: Martin Street to Clearlake Ave | Pavement Improvement | 2010-04-15 | 2010-04-15 |  | 2010-07-23 | 643449 | 0.660
896 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5078030 | This is a Pavement Resurfacing project by a local agency in the City of Compton. The project is described as: DEVELOPMENT OF STREET PREVENTIVE PROGRAM. PREVENTIVE MAINTENANCE OF VARIOUS STREETS WITH | Pavement Improvement | 2010-03-30 | 2010-04-12 |  | 2010-06-02 | 552218.83 | 14.000
897 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5078031 | This is a Pavement Resurfacing project by a local agency in the City of Compton. The project is described as: VARIOUS LOCATIONS LOCAL RODS IN THE CITY OF COMPTON.GRINDING AND OVERLAY OF LOCAL ROADS. | Pavement Improvement | 2010-03-30 | 2010-04-12 |  | 2010-10-01 | 2004000 | 4.300
898 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | LOMPOC | 24 | 5080019 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Lompoc. The project is described as: Construct Phase 1 Class 1 bikeway to College. | Transportation Enhancements | 2010-09-27 | 2010-09-27 |  | 2011-04-29 | 568036 | 1.000
899 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | LOMPOC | 24 | 5080021 | This is a Pavement Resurfacing project by a local agency in the City of Lompoc. The project is described as: Street pavement rehabilitation and overlays on V Street, College Avenue, 7th Street, O Str | Pavement Improvement | 2009-09-21 | 2009-09-21 |  | 2009-11-25 | 682161 | 2.700
900 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | LOMPOC | 24 | 5080022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lompoc. The project is described as: Street pavement rehabilitation and overlays on various streets and road | Pavement Improvement | 2010-08-30 | 2010-08-30 |  | 2010-11-23 | 1113464 | 1.900
901 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5082057 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Willits. The project is described as: Reconstruction and rehabilitation of the roadway, including curb exten | Pavement Improvement | 2010-07-09 | 2010-07-19 |  | 2010-11-29 | 432285 | 0.200
902 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | 5084015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Paso Robles. The project is described as: In Paso Robles, at Hwy 46 West, Realign Theatre Drive from existin | New Construction | 2010-10-12 | 2010-10-22 |  |  | 2860000 | 0.750
903 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED | MERCED | 18 | 5085019 | This is a Pavement Resurfacing project by a local agency in the City of Merced. The project is described as: HMA Overlay on 16th St. from G to V St. | Pavement Improvement | 2010-03-03 | 2010-03-15 |  | 2010-07-22 | 1402602.09 | 2.500
904 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED | MERCED | 18 | 5085020 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Merced. The project is described as: Reconstruction of 18th Street from N to G Street, G Street from 16th | Pavement Improvement | 2010-12-15 | 2011-01-03 |  |  | 2454503 | 2.150
905 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5086029 | This is a Pavement Resurfacing project by a local agency in the City of Monterey. The project is described as: Reconstruct between Fremont and Elorado | Pavement Improvement | 2009-08-31 | 2009-09-14 |  | 2010-04-30 | 602716 | 1.000
906 | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | 5086030 | This is a Safety project by a local agency in the City of Monterey. The project is described as: Del Monte/Figueroa; Traffic signal modifications and curb return/ADA/new bike lane improvements, safe | Safety/Traffic Management | 2010-01-04 | 2010-01-11 |  | 2010-08-01 | 375000 | 1.000
907 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5087027 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Pacific Grove. The project is described as: Sidewalk and storm drain improvements | Transportation Enhancements | 2009-11-10 | 2009-11-18 |  | 2010-04-16 | 303000 | 1.000
908 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5088020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fort Bragg. The project is described as: Grinding, Excavating to 13 feet, replace base rock, asphalt concret | Pavement Improvement | 2010-02-16 | 2010-02-16 |  | 2010-07-12 | 209174 | 0.250
909 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5088021 | This is a Pavement Resurfacing project by a local agency in the City of Fort Bragg. The project is described as: Structural digouts, grinding, 2 inch asphalt overlay, and curb ramps installed | Pavement Improvement | 2010-02-22 | 2010-02-22 |  | 2010-08-06 | 482000 | 0.600
910 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5088024 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Fort Bragg. The project is described as: Sidewalk infill and replacement of deteriorated sidewalk. | Transportation Enhancements | 2010-07-28 | 2010-07-28 |  | 2010-09-30 | 87704 | 0.180
911 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS | HANFORD | 20 | 5091037 | This is a Pavement Resurfacing project by a local agency in the City of Hanford. The project is described as: City of Hanford, Hanford-Armona Road, From 11th Avenue to Greenbriar Dr; Rehabilitate Roa | Pavement Improvement | 2009-10-12 | 2009-10-12 |  | 2010-06-30 | 630433 | 1.000
912 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS | HANFORD | 20 | 5091040 | This is a Pavement Resurfacing project by a local agency in the City of Hanford. The project is described as: City of Hanford, 11th Ave. From 3rd St. to Ivy St., Rehabilitate Roadway | Pavement Improvement | 2010-05-31 | 2010-05-31 |  | 2010-09-21 | 692231 | 1.000
913 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS | HANFORD | 20 | 5091044 | This is a Traffic Management Engineering project by a local agency in the City of Hanford. The project is described as: City of Hanford, Douty St. From Cortner St. to Windsor Dr., Rehabilitate Roadwa | Pavement Improvement | 2010-05-31 | 2010-05-31 |  | 2010-09-21 | 458016 | 1.000
914 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5093013 | This is a Pavement Resurfacing project by a local agency in the City of Redondo Beach. The project is described as: PRIORITY 1 INGLEWOOD AVE STREET RESURFACING FROM ARTESIA BLVD TO MANHATTAN BEACH BL | Pavement Improvement | 2009-10-12 | 2009-10-19 |  | 2010-04-20 | 1000904.65 | 1.000
915 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5093014 | This is a Pavement Resurfacing project by a local agency in the City of Redondo Beach. The project is described as: PRIORITY 2 PROSPECT AVENUE STREET RESURFACING FROM PALOS VERDES BLVD TO ANITA ST/19 | Pavement Improvement | 2010-08-17 | 2010-08-20 |  | 2010-11-24 | 920000 | 2.500
916 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VACAVILLE | 07 | 5094049 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Vacaville. The project is described as: Pedestrian Enhancements | Safety/Traffic Management | 2009-06-12 | 2009-06-15 |  | 2009-11-10 | 260000 | 0.270
917 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VACAVILLE | 07 | 5094052 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Vacaville. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-23 | 2009-10-01 |  | 2010-09-29 | 1376000 | 4.700
918 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VACAVILLE | 07 | 5094053 | This is a Traffic Management Engineering project by a local agency in the City of Vacaville. The project is described as: Install technology improvements | Safety/Traffic Management | 2009-10-30 | 2010-02-22 |  | 2010-06-01 | 320000 | 0.000
919 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5095013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rocklin. The project is described as: Rehabilitate Sunset Boulevard from Blue Oaks Blvd to Atherton Road. | Pavement Improvement | 2009-09-14 | 2009-09-14 |  | 2009-12-10 | 1289206 | 1.000
920 | Underway | C220,C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5097007 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Ferndale. The project is described as: Install sidewalks, crosswalks, curbs | Transportation Enhancements | 2011-12-22 | 2012-01-03 |  |  | 400000 | 0.690
921 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5100011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palo Alto. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-11-10 | 2009-11-16 |  | 2010-03-31 | 580000 | 0.600
922 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5100012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palo Alto. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-12-04 | 2009-12-07 |  | 2010-01-27 | 505000 | 1.700
923 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5100013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palo Alto. The project is described as: Removal and replacement of deteriorated concrete curbs, gutters, sid | Pavement Improvement | 2010-06-29 | 2010-08-09 |  | 2010-09-23 | 209000 | 1.100
924 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 10 | 5101022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasanton. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-15 | 2009-10-22 |  | 2010-08-17 | 1047410.32 | 1.200
925 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | Multiple | 5101023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasanton. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-05-03 | 2010-05-10 |  | 2010-07-07 | 370000 | 1.000
926 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 11 | 5101024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasnton. The project is described as: Rehabilitation of approximately eleven additional Federal-aid eligib | Pavement Improvement | 2010-06-25 | 2010-07-08 |  | 2010-08-26 | 371289 | 0.700
927 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5102034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Mateo. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-17 | 2009-08-17 |  | 2010-04-01 | 1095000 | 4.000
928 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5102035 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Mateo. The project is described as: Rehabilitate local streets | Pavement Improvement | 2010-07-27 | 2010-07-27 |  | 2011-03-14 | 452000 | 2.000
929 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5102036 | EL CAMINO REAL, CONCAR, HILLSDALE, DELAWARE, SARATOGA, INSTALL ITS ELEMENTS | Safety/Traffic Management | 2010-10-04 | 2010-10-04 |  |  | 1000000
930 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5107021 | This is a Pavement Resurfacing project by a local agency in the City of Santa Monica. The project is described as: SANTA MONICA BLVD RESURFACING PROJECT PHASE II - MAINTENANCE AND REPAIR TO THE EXIST | Pavement Improvement | 2010-01-05 | 2010-01-05 |  |  | 674638 | 0.700
931 | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5107022 | This is a Pavement Resurfacing project by a local agency in the City of Santa Monica. The project is described as: STREET RESURFACING CITYWIDE- PAVING ON COLLECTOR AND ARTERIAL STREETS INCLUDING MAIN | Pavement Improvement | 2010-01-04 | 2010-01-05 |  |  | 2002183 | 5.500
932 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108094 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 2010-01-04 | 2010-01-04 |  | 2010-06-04 | 3028790 | 4.500
933 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108095 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 2010-01-19 | 2010-01-19 |  | 2010-05-18 | 229342 | 4.500
934 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108096 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 2010-01-04 | 2010-01-04 |  | 2010-06-07 | 487632.99 | 4.500
935 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108097 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 2009-12-07 | 2009-12-07 |  | 2010-05-28 | 634018 | 4.500
936 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108103 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 2010-07-26 | 2010-07-26 |  | 2010-09-09 | 309000.03 | 4.500
937 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108107 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 2010-07-26 | 2010-09-13 |  | 2010-10-18 | 919317 | 4.500
938 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108109 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 2010-07-13 | 2010-07-13 |  | 2010-09-09 | 272694.81 | 4.500
939 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108112 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 2010-07-12 | 2010-07-12 |  | 2011-03-25 | 1720893 | 4.500
940 | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5108115 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Long Beach. The project is described as: CUSTOM BICYCLE RACKS AND PROTECTED BICYCLE PARKING FOR INSTALLATION | Transportation Enhancements | 2010-03-15 | 2010-03-15 |  | 2011-04-30 | 838000 | 1.000
941 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108124 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: REHABILITATION OF VARIOUS STREETS IN THE CITY OF LONG BEACH WHICH I | Pavement Improvement | 2010-06-28 | 2010-06-28 |  | 2011-04-15 | 4234677 | 4.500
942 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5108127 | WARDLOW ROAD: BETWEEN CLARK AVENUE AND PALO VERDE AVENUE, ROAD REHABILITATON | Pavement Improvement | 2010-10-25 | 2010-10-25 |  | 2011-05-09 | 1648678
943 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108129 | PARAMOUNT BLVD: ARTESIA BLVD TO CANDLEWOOD ST, ROAD REHABILITATION | Pavement Improvement | 2011-06-06 | 2011-06-06 |  | 2011-10-31 | 852942
944 | Underway | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5108132 | CITYWIDE PARKING EQUIPMENT, BICYCLE RELATED | Transportation Enhancements | 2012-01-09 | 2012-01-15 |  |  | 212600
945 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109153 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Hughes Lane: White Lane to Planz Rd; Wible Road: White Lane to | Other | 2009-09-02 | 2009-09-17 |  | 2010-05-10 | 1717761.87 | 1.560
946 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109154 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Mt. Vernon Ave: State Route 178 to University Ave; Resurfacing, | Other | 2009-09-03 | 2009-09-08 |  | 2010-02-26 | 1733374.47 | 0.700
947 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109155 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Ashe Rd: White Lane to Ming Ave; Resurfacing, Reconstruction | Other | 2009-09-02 | 2009-09-17 |  | 2010-02-17 | 1473715.42 | 1.120
948 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109157 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Coffee Road: Friant Kern Canal to Riverlakes Drive - Reconstruc | Pavement Improvement | 2010-04-21 | 2010-05-03 |  | 2010-06-29 | 1538102.43 | 0.900
949 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109158 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Ming Avenue: Gosford Road to Ashe Road - Reconstruction Ming Av | Pavement Improvement | 2010-04-22 | 2010-05-03 |  | 2010-08-06 | 4283184.22 | 1.860
950 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 02 | 5110027 | This is a Safety project by a local agency in the City of Winters. The project is described as: Grant Ave.(SR128), east of Railroad Ave., between Dutton St and Morgan St.: widen to accommodate a cont | Pavement Improvement | 2009-09-01 | 2009-09-01 |  | 2009-11-10 | 334955.14 | 1.000
951 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111046 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Whittier. The project is described as: Greenleaf Avenue Overlay and Class II Bike Lanes | Pavement Improvement | 2010-06-04 | 2010-06-21 |  | 2010-10-12 | 581521.5 | 1.000
952 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111049 | This is a Safety project by a local agency in the City of Whittier. The project is described as: Santa Gertrudes Avenue at Starbuck Street Traffic Signal Installation. | Safety/Traffic Management | 2010-04-20 | 2010-08-02 |  | 2010-11-09 | 161230.83 | 1.000
953 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111052 | This is a Safety project by a local agency in the City of Whittier. The project is described as: Painter Avenue Street Light Conversion Project. Conversion of old 6,000 volt series street lighting sy | Other | 2010-03-10 | 2010-06-01 |  | 2011-03-08 | 229794.64 | 1.000
954 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111053 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Whittier. The project is described as: Laurel Avenue from Whittier Boulevard (State Route 72) to Lambert Roa | Pavement Improvement | 2010-06-04 | 2010-06-21 |  | 2010-10-12 | 360673 | 1.000
955 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111054 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Whittier. The project is described as: La Cuarta Street from Whittier Blvd (SR 72) to College Avenue. Remove | Pavement Improvement | 2011-04-25 | 2011-05-02 |  | 2011-08-24 | 760000 | 1.000
956 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111055 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Whittier. The project is described as: Slauson Avenue/Mulberry Drive Resurfacing from West City Limits at Ch | Pavement Improvement | 2010-06-04 | 2010-06-21 |  | 2010-10-12 | 218805.75 | 1.000
957 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111056 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Whittier. The project is described as: Intersection of Mar Vista Street and California Avenue. Reconstru | Pavement Improvement | 2010-04-19 | 2010-05-03 |  | 2010-05-20 | 70058 | 1.000
958 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5112010 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Azusa. The project is described as: RECONSTRUCTION OF FOOTHILL BLVD. FROM TODD AVE. TO ORANGE AVE. (3,716 | Pavement Improvement | 2009-09-23 | 2009-09-28 |  | 2010-01-22 | 879841 | 0.700
959 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5112012 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Azusa. The project is described as: Reconstruction of Citrus Ave. From Alosta Ave. to the northerly City bo | Pavement Improvement | 2010-06-30 | 2010-07-12 |  | 2011-01-18 | 540000 | 1.000
960 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5113010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Mill Valley. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-22 | 2009-10-26 |  | 2009-11-25 | 265521.6 | 0.360
961 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | Multiple | 5114014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sonoma. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-28 | 2009-09-28 |  | 2010-01-12 | 500000 | 0.530
962 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5115019 | This is a Pavement Resurfacing project by a local agency in the City of Lemoore. The project is described as: City of Lemoore, Hanford-Armona Road, From 19th Ave. to SR 41; Overlay Roadway | Pavement Improvement | 2009-10-19 | 2009-10-21 |  | 2009-12-01 | 396422.92 | 1.000
963 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5115021 | This is a Pavement Resurfacing project by a local agency in the City of Lemoore. The project is described as: City of Lemoore, Lemoore Ave. From Cinnamon Ave. to Glendale Ave., Overlay Roadway | Pavement Improvement | 2010-07-27 | 2010-07-28 |  | 2010-08-27 | 355601.19 | 1.000
964 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LASSEN |  | 04 | 5116013 | This is a Pavement Resurfacing project by a local agency in the City of Susanville. The project is described as: 2.5 inch asphalt concrete overlay | Pavement Improvement | 2010-11-09 | 2010-11-24 |  |  | 740720 | 1.200
965 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5117008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hercules. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-29 | 2009-10-29 |  | 2010-04-27 | 576927.55 | 0.830
966 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5118014 | This is a Pavement Resurfacing project by a local agency in the City of Covina. The project is described as: STREET OVERLAYS - CITYWIDE | Pavement Improvement | 2009-12-02 | 2009-12-02 |  | 2010-02-01 | 839828.94 | 2.650
967 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5121017 | This is a Pavement Resurfacing project by a local agency in the City of Santa Paula. The project is described as: 8th Street from Harvard to Santa Paula Street | Pavement Improvement | 2009-10-14 | 2009-10-14 |  | 2010-02-22 | 254000 | 1.000
968 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | THOUSAND OAKS | 24 | 5121019 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Paula. The project is described as: Peck Road from Faulkner Road to Harvard Blvd. | Pavement Improvement | 2010-11-10 | 2011-01-03 |  |  | 242008 | 0.500
969 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE | PORTERVILLE | 21 | 5122062 | This is a Pavement Resurfacing project by a local agency in the City of Porterville. The project is described as: City of Porterville - Resurfacing Olive Ave from Main St to Villa St | Pavement Improvement | 2010-06-15 | 2010-06-15 |  | 2010-07-22 | 318981 | 0.850
970 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5123014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sebastopol. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-11-10 | 2009-11-23 |  | 2010-08-10 | 601341.42 | 0.830
971 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5124027 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Mountain View. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-05 | 2009-10-05 |  | 2010-03-23 | 720325.74 | 0.860
972 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | 5125022 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bishop. The project is described as: Replace asphalt paving, cross gutters & ramps. Install new water and | Pavement Improvement | 2009-08-28 | 2009-09-01 |  | 2010-08-31 | 379417.95 | 0.200
973 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5126010 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Pinole. The project is described as: Pedestrian Enhancements | Pavement Improvement | 2009-10-22 | 2010-03-15 |  | 2010-04-26 | 180375.48 | 1.000
974 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5126012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pinole. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-23 | 2009-09-23 |  | 2010-10-20 | 420000 | 0.600
975 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | ANTIOCH-PITTSBURGH | 07 | 5127023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pittsburg. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-25 | 2009-10-19 |  | 2010-01-02 | 1103000 | 1.020
976 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5129053 | This is a Pavement Resurfacing project by a local agency in the City of Oxnard. The project is described as: Bartolo Square North Street Resurfacing | Pavement Improvement | 2010-05-13 | 2010-05-24 |  | 2010-10-25 | 765229.8 | 1.000
977 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | Multiple | 5129054 | This is a Traffic Management Engineering project by a local agency in the City of Oxnard. The project is described as: Traffic Signal Improvements, various locations | Safety/Traffic Management | 2009-11-02 | 2009-11-02 |  | 2010-06-17 | 681146.74 | 1.000
978 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5129055 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oxnard. The project is described as: Bartolo Square South Street Resurf. | Pavement Improvement | 2009-10-13 | 2009-10-24 |  | 2010-03-31 | 917300.49 | 0.900
979 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | STATEWIDE | 23 | 5129058 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Oxnard. The project is described as: Route 101 at Rice Ave/Santa Clara Ave Intersection Improvement | Pavement Widening | 2009-11-18 | 2009-11-18 |  |  | 5000000 | 1.000
980 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5130014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alhambra. The project is described as: REHABILITATE ALHAMBRA ROAD FROM CITY BOUNDARY EAST TO CITY BOUNDARY W | Pavement Improvement | 2010-08-04 | 2010-08-04 |  | 2011-03-17 | 1146475 | 2.500
981 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5130015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alhambra. The project is described as: REHABILITATE POPLAR BOULEVARD FROM FREMONT AVENUE TO CITY BOUNDARY WE | Pavement Improvement | 2010-04-29 | 2010-05-13 |  | 2010-06-28 | 202318.98 | 0.600
982 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5130016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alhambra. The project is described as: REHABILITATE NEW AVENUE FROM LOS HIGOS/NORTH BOUNDARY TO I-10 FWY. | Pavement Improvement | 2011-03-28 | 2011-03-28 |  | 2011-07-01 | 1242512 | 0.750
983 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5131014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arcadia. The project is described as: DUARTE ROAD BETWEEN EL MONTE AVENUE AND SANTA ANITA AVENUE AND AT WEST | Pavement Improvement | 2010-10-08 | 2010-10-11 |  | 2011-01-04 | 299957.99 | 0.500
984 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5131015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arcadia. The project is described as: SANTA ANITA AVENUE BETWEEN FOOTHILL BLVD. AND GRANDVIEW AVENUE: STREET | Pavement Improvement | 2009-12-14 | 2009-12-29 |  | 2010-03-26 | 757000 | 1.100
985 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5131016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arcadia. The project is described as: SANTA ANITA AVENUE BETWEEN LONGDEN AVENUE AND LIVE OAK AVENUE: STREET | Pavement Improvement | 2009-09-29 | 2009-10-01 |  | 2010-01-05 | 574528.78 | 0.500
986 | Underway | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | SAN FRANCISCO-OAKLAND, CA | 10 | 5132032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: In Fairfield: McGary Rd is a frontage road that parallels I-80 and l | Transportation Enhancements | 2010-05-10 | 2010-05-10 |  |  | 1603000 | 2.000
987 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | FAIRFIELD | 10 | 5132033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-11 | 2009-11-12 |  | 2010-07-20 | 647711.94 | 0.700
988 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | FAIRFIELD | 10 | 5132034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-26 | 2009-11-09 |  | 2010-08-13 | 441890.67 | 0.800
989 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | CONCORD | 10 | 5132036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: Asfault concrete overlay and full depth asphalt repairs. | Pavement Improvement | 2010-06-07 | 2010-06-22 |  | 2010-11-04 | 502905.07 | 0.700
990 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5133038 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Fullerton. The project is described as: Rehabilitate 0.35 Miles of roadway on Harbor Blvd | Pavement Improvement | 2010-05-10 | 2010-05-10 |  | 2010-06-25 | 995873.52 | 0.350
991 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5134006 | This is a Pavement Resurfacing project by a local agency in the City of Imperial. The project is described as: Rehabilitation and Reconstruction of existing pavement on Barioni Road from B Street to | Pavement Improvement | 2010-07-28 | 2010-07-30 |  | 2011-01-18 | 895000 | 1.000
992 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5135036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Concord. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-03 | 2009-10-05 |  | 2010-12-07 | 1110922.64 | 1.200
993 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 07 | 5135037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Concord. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-10 | 2009-09-14 |  | 2010-12-07 | 584000 | 0.500
994 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 07 | 5135038 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Concord. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-04-16 | 2010-04-19 |  |  | 370701 | 1.200
995 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5137037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Richmond. The project is described as: Rehabilitate local street and add bicycle lane | Pavement Improvement | 2010-02-10 | 2010-05-03 |  |  | 1578000 | 0.800
996 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138033 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Maria. The project is described as: Overlay, Phase I (A) E Donovan Rd ? N Carlotti Dr to Suey Rd (B | Pavement Improvement | 2010-04-26 | 2010-04-26 |  | 2010-08-10 | 1657050 | 4.100
997 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138035 | This is a Pavement Resurfacing project by a local agency in the City of Santa Maria. The project is described as: Overlay, Phase II (A) N Railroad Ave ? W Taylor Ave to W Donovan (B) N Western Ave ? | Pavement Improvement | 2010-02-22 | 2010-02-22 |  | 2010-06-14 | 1135112.88 | 2.600
998 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138036 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Maria. The project is described as: Concrete Project I (A) N Broadway ? Preisker Ln to Donovan Rd (B | Transportation Enhancements | 2010-10-08 | 2010-10-08 |  | 2011-02-07 | 196001 | 1.780
999 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138037 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Maria. The project is described as: Concrete Project II (A) N Thornburg St ? W Donovan Rd to W Fesler | Transportation Enhancements | 2010-04-07 | 2010-04-07 |  | 2010-07-28 | 301554 | 1.000
1000 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138038 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Maria. The project is described as: Concrete Project III (A) W Taylor St ? N Blosser Rd to N Railroad | Transportation Enhancements | 2010-03-03 | 2010-03-03 |  | 2010-07-16 | 232089 | 1.070
1001 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138041 | CITY OF SANTA MARIA VARIOUS STREETS, CHIP SEAL AND LIGHTING | Pavement Improvement | 2011-06-14 | 2011-07-13 |  |  | 557519
1002 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 34 | 5139011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Vernon. The project is described as: 26TH STREET IMPROVEMENT FROM ALAMEDA TO EAST OF DOWNEY ROAD. REHABILIT | Pavement Improvement | 2011-02-02 | 2011-02-07 |  | 2011-09-03 | 500000 | 2.000
1003 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 04 | 5142030 | This is a Pavement Resurfacing project by a local agency in the City of Oroville. The project is described as: Roadway Rehabilitation / Overlays | Pavement Improvement | 2009-08-31 | 2009-08-31 |  | 2010-02-10 | 1052369.75 | 2.000
1004 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 04 | 5142031 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Oroville. The project is described as: Beautification of the on and off ramp areas through construction | Transportation Enhancements | 2010-09-07 | 2010-09-13 |  | 2011-10-03 | 213993 | 0.200
1005 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144047 | This is a Safety project by a local agency in the City of Glendale. The project is described as: MONTEREY ROAD NEW TRAFFIC SIGNALS. CONSTRUCT 3 NEW TRAFFIC SIGNALS AT MONTEREY RD./GENEVA ST., MONTERE | Pavement Improvement | 2009-12-07 | 2010-01-25 |  | 2010-11-01 | 616600 | 0.340
1006 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144048 | This is a Pavement Resurfacing project by a local agency in the City of Glendale. The project is described as: STREET REPAIR AND REHABILITATION PROJECT, PHASE VI: PACIFIC AVE. AND ALLEN STREET-THE PR | Pavement Improvement | 2010-03-15 | 2010-03-29 |  | 2010-07-16 | 1233076.11 | 0.820
1007 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144049 | This is a Traffic Management Engineering project by a local agency in the City of Glendale. The project is described as: SOUTH GLENDALE TYPE 2070 TRAFFIC SIGNAL CONTROLLER CONVERSIONS. REPLACE EXIST | Pavement Improvement | 2009-12-07 | 2010-01-25 |  | 2010-06-30 | 149353.3 | 1.000
1008 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144050 | This is a Safety project by a local agency in the City of Glendale. The project is described as: NEW TRAFFIC SIGNAL INSTALLATION AT VARIOUS LOCATIONS. CONSTRUCT 3 NEW TRAFFIC SIGNALS AT CENTRAL AVE./ | Pavement Improvement | 2010-01-26 | 2010-02-01 |  | 2010-11-03 | 639800 | 1.000
1009 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144051 | This is a Pavement Resurfacing project by a local agency in the City of Glendale. The project is described as: STREET REPAIR AND REHABILITATION PROJECT PHASE I: CHEVY CHASE DR. AND CYPRESS ST.-THE PR | Pavement Improvement | 2010-04-05 | 2010-04-05 |  | 2010-12-07 | 895000 | 1.100
1010 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144052 | This is a Traffic Management Engineering project by a local agency in the City of Glendale. The project is described as: NORTH GLENDALE TYPE 2070 TRAFFIC SIGNAL CONTROLLER CONVERSIONS. REPLACE EXIST | Pavement Improvement | 2009-12-07 | 2009-12-07 |  | 2010-06-30 | 318042.05 | 1.000
1011 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144055 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Glendale. The project is described as: Glenoaks Blvd Traffic Signal Upgrades: Upgrade and modernize thirteen | Safety/Traffic Management | 2011-01-03 | 2011-01-10 |  |  | 2198146 | 1.000
1012 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5145011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fortuna. The project is described as: Rehabilitation of approx. 0.5 miles of a principle arterial road. | Pavement Improvement | 2010-08-09 | 2010-08-16 |  | 2011-05-18 | 976000 | 0.500
1013 | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5146009 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Coalinga. The project is described as: Cherry & Elm Ave-Intersection will be re-aligned for future signal | New Construction | 2010-06-22 | 2010-07-26 |  | 2011-04-07 | 355435 | 0.040
1014 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5149005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Verne. The project is described as: COMPLETE REHABILITATION OF 1.3 MILE LENGTH OF GOLDEN HILLS ROAD FROM | Pavement Improvement | 2009-09-14 | 2009-09-14 |  | 2009-10-09 | 598976 | 1.300
1015 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5149006 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of La Verne. The project is described as: Town Center Drive from Foothill Boulevard to White Avenue. Includ | Pavement Improvement | 2009-09-21 | 2009-09-21 |  | 2009-10-23 | 136928.06 | 0.250
1016 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5149011 | EMERALD AVENUE: FOOTHILL BLVD. TO BOWDOIN ST., ASPHALT CONCRETE OVERLAY | Pavement Improvement | 2011-02-01 | 2011-02-07 |  | 2011-03-31 | 241000
1017 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5150008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Huntington Park. The project is described as: STREET IMPROVEMENTS AT BISSELL FROM FLORENCE AVE. TO RANDOLPH | Pavement Improvement | 2010-02-08 | 2010-02-08 |  | 2010-06-30 | 1898000 | 2.780
1018 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5151024 | This is a Pavement Resurfacing project by a local agency in the City of Newport Beach. The project is described as: Pavement rehab. from 44th St. to 22nd St. | Pavement Improvement | 2009-11-09 | 2009-11-09 |  | 2010-04-27 | 1027455.87 | 0.950
1019 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 11 | 5152019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Morgan Hill. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-09 | 2009-09-09 |  | 2010-01-20 | 436393.46 | 0.600
1020 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 19 | 5153028 | This is a Pavement Resurfacing project by a local agency in the City of Oakdale. The project is described as: North Oak Avenue Reconstruction. | Pavement Improvement | 2010-06-07 | 2010-08-24 |  | 2011-08-15 | 180521.83 | 0.500
1021 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 18 | 5153030 | This is a Pavement Resurfacing project by a local agency in the City of Oakdale. The project is described as: Curb, gutter, sidewalk, pavement and intersection improvements | Pavement Improvement | 2010-05-05 | 2010-06-01 |  | 2010-08-31 | 306799 | 1.000
1022 | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | LODI | 11 | 5154036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lodi. The project is described as: Enhancement of existing roadway | Pavement Improvement | 2009-11-11 | 2010-04-19 |  | 2011-03-24 | 2204608.11 | 0.620
1023 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5155006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hermosa Beach. The project is described as: 8TH STREET: STREET IMPROVEMENTS BETWEEN PCH & VALLEY DRIVE. INCL | Pavement Improvement | 2010-03-29 | 2010-04-05 |  | 2010-07-08 | 294433 | 0.120
1024 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5155007 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Hermosa Beach. The project is described as: PIER AVENUE IMPROVEMENT PROJECT. MULTI-FACETED PROJECT WHICH | Pavement Improvement | 2010-03-29 | 2010-04-05 |  | 2010-06-22 | 279077 | 0.110
1025 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157068 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Madera. The project is described as: Widen & reconstruct Lake Street to 4 travel lanes w/bike lane | Pavement Widening | 2010-06-14 | 2010-06-14 |  | 2011-03-16 | 580000 | 0.500
1026 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157069 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Madera. The project is described as: Install trees, stakes, tree wells & minor landscaping tasks | Transportation Enhancements | 2010-08-16 | 2010-08-16 |  | 2011-03-16 | 66000 | 0.300
1027 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157070 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Madera. The project is described as: Street Rehabilitation/Resurfacing: I St. - North of 2nd to South of Cen | Pavement Improvement | 2010-05-03 | 2010-05-03 |  | 2010-07-30 | 203766.23 | 0.400
1028 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157073 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Madera. The project is described as: Lake Street - Cleveland to Kennedy, reconstruct and widen to 4 lanes wi | Pavement Widening | 2009-10-19 | 2009-10-19 |  | 2010-05-14 | 1017000 | 0.500
1029 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157076 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Madera. The project is described as: Overlay & ADA ramps & sidewalks on Sherwood, Austin to Lake, and 'D', R | Pavement Improvement | 2010-10-04 | 2010-10-04 |  | 2011-05-04 | 178000 | 1.200
1030 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5159014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Anselmo. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-20 | 2009-10-20 |  | 2010-01-04 | 228035.19 | 0.300
1031 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5160016 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Banos. The project is described as: The overlay of selected streets | Pavement Improvement | 2010-08-24 | 2010-09-08 |  | 2010-12-08 | 579498.74 | 1.000
1032 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5160017 | This is a Pavement Resurfacing project by a local agency in the City of Los Banos. The project is described as: Overlay and Cape Seal of selected streets | Pavement Improvement | 2010-08-24 | 2010-09-08 |  | 2010-12-08 | 663805 | 3.000
1033 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5162017 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Claremont. The project is described as: ARROW HIGHWAY, FROM CITY LIMIT TO CITY.REHABILITATION, RECONSTRUCTIO | Pavement Improvement | 2010-04-05 | 2010-04-19 |  | 2010-10-27 | 895000 | 1.600
1034 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5162018 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Claremont. The project is described as: &#9658; LOCATION: THROUGHOUT CITY. &#9658; NATURE OF PROJECT (PRO | Transportation Enhancements | 2010-02-18 | 2010-02-22 |  | 2010-10-27 | 1249606 | 1.510
1035 | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER | YUBA CITY | 02 | 5163019 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Yuba City. The project is described as: In Yuba City, from Plumas to Shasta, construct signal-phasing modifi | Pavement Improvement | 2009-08-10 | 2009-08-10 |  | 2010-09-08 | 1900000 | 1.000
1036 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | 5163023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Yuba City. The project is described as: Yuba City, Live Oak Blvd. and Garden Highway: Rehabilitate roadways, | Pavement Improvement | 2010-04-19 | 2010-04-19 |  | 2010-05-21 | 753627 | 1.000
1037 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5164016 | This is a Pavement Resurfacing project by a local agency in the City of Inglewood. The project is described as: MANCHESTER BOULEVARD CORRIDOR ROADWAY IMPROVEMENT PROJECT. TO PRESERVE AND REHABILITAT | Pavement Improvement | 2009-11-02 | 2009-11-02 |  | 2010-09-30 | 2524765 | 2.450
1038 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5164017 | This is a Pavement Resurfacing project by a local agency in the City of Inglewood. The project is described as: LA CIENEGA/LA TIJERA/CENTINELA ROADWAY IMPROVEMENT PROJECT. THIS PROJECT INCLUDES RES | Pavement Improvement | 2011-08-11 | 2011-08-15 |  |  | 952235 | 0.330
1039 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | TURLOCK | 19 | 5165055 | This is a Pavement Resurfacing project by a local agency in the City of Turlock. The project is described as: Streets Preventive Maintenenace. | Pavement Improvement | 2010-06-21 | 2010-06-28 |  | 2011-05-24 | 2389944 | 1.000
1040 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5166022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Larkspur. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-08 | 2009-10-08 |  | 2009-11-30 | 236000 | 0.490
1041 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5167024 | This is a Pavement Resurfacing project by a local agency in the City of Brawley. The project is described as: Asphalt Rehabilitation and Reconstruction of Western Avenue from State Highway 86 to Nort | Pavement Improvement | 2010-03-24 | 2010-03-24 |  | 2010-06-10 | 884922.81 | 0.800
1042 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5167025 | This is a Pavement Resurfacing project by a local agency in the City of Brawley. The project is described as: In Brawley Cattle Call Park. From Willard Avenue, Around Park, ending at Willard Avenue. | Transportation Enhancements | 2010-04-05 | 2010-04-06 |  | 2011-01-10 | 130595 | 1.000
1043 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5168013 | This is a Pavement Resurfacing project by a local agency in the City of Calexico. The project is described as: Street Rehabilitation of Emmerson Avenue from Highway 98 to Third Street | Pavement Improvement | 2010-03-25 | 2010-04-15 |  | 2010-10-20 | 974000 | 0.780
1044 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL | EL CENTRO | 51 | 5169027 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Centro. The project is described as: Removal and Reconstruction of existing 2 lane Dogwood Rd (1.2 miles) | Pavement Improvement | 2010-07-06 | 2010-07-26 |  | 2011-01-24 | 800000 | 1.200
1045 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL | EL CENTRO | 51 | 5169028 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of El Centro. The project is described as: Rehabilitation of Adams Avenue from Imperial Avenue to La Bruche | Pavement Improvement | 2010-08-30 | 2010-09-01 |  | 2011-01-06 | 302000 | 0.520
1046 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | 5170035 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Kingsburg. The project is described as: In the City of Kingsburg, on 18th Avenue, from Kamm Ave to Solig | Transportation Enhancements | 2010-07-26 | 2010-08-02 |  | 2010-09-10 | 127393.45 | 0.200
1047 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | 5170036 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Kingsburg. The project is described as: Construct pedestrian facilities along Sierra Street at the UPRR trac | Transportation Enhancements | 2010-10-06 | 2010-10-06 |  |  | 209884 | 0.100
1048 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5171016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Burlingame. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-13 | 2009-08-17 |  | 2009-09-28 | 551000 | 1.200
1049 | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 19 | 5172018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Newman. The project is described as: Construct Downdown Plaza. | Transportation Enhancements | 2010-07-12 | 2010-07-12 |  | 2011-04-15 | 1821768 | 0.080
1050 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5173020 | This is a Pavement Resurfacing project by a local agency in the City of Folwer. The project is described as: Curb, gutter, sidewalk and AC improvements | Pavement Improvement | 2010-06-14 | 2010-06-14 |  | 2010-07-23 | 160000 | 0.300
1051 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5174007 | This is a Pavement Resurfacing project by a local agency in the City of Holtville. The project is described as: Street Improvements of Rehabilitation and Reconstruction along West side of Holt Avenue | Pavement Improvement | 2010-01-04 | 2010-02-08 |  | 2010-04-02 | 346000 | 0.110
1052 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5174008 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Holtville. The project is described as: Replacement of the City of Holtville entrance monument sign locat | Transportation Enhancements | 2010-03-24 | 2010-04-05 |  | 2010-06-02 | 50000 | 0.060
1053 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5174009 | This is a Pavement Resurfacing project by a local agency in the City of Holtville. The project is described as: Walnut Avenue Rehabilitation between 5th Street (SR 111) and Fourth Street | Pavement Improvement | 2009-12-10 | 2009-12-14 |  | 2010-03-19 | 317868 | 0.110
1054 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5174010 | This is a Pavement Resurfacing project by a local agency in the City of Holtville. The project is described as: Rehabilitation along North side of 9th Street between Cedar Avenue and Holt Avenue | Pavement Improvement | 2010-06-18 | 2010-07-07 |  | 2010-08-19 | 247000 | 0.120
1055 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5176005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Marin. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-09-20 | 2010-10-04 |  | 2010-11-03 | 226436 | 1.000
1056 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5177022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South San Francisco. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-10 | 2009-09-14 |  | 2009-10-07 | 675702.34 | 0.850
1057 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5177023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South San Francisco. The project is described as: Rehabilitate local streets | Pavement Improvement | 2010-08-09 | 2010-08-09 |  | 2010-09-27 | 328300 | 0.800
1058 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5180008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Montague. The project is described as: Rehabilitate 0.9 miles of streets within the City of Montague with as | Pavement Improvement | 2010-06-18 | 2010-06-28 |  | 2010-07-16 | 405500 | 0.900
1059 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5181164 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Huntington Beach. The project is described as: Landscaping and Irrigation, fine grading and adjustment o | Transportation Enhancements | 2010-01-12 | 2010-01-12 |  | 2010-08-04 | 156000 | 0.840
1060 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5181166 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Huntington Beach. The project is described as: Grind pavmt, remove failed roadway, paving of failed areas, o | Pavement Improvement | 2010-03-29 | 2010-03-29 |  | 2010-06-28 | 1120616 | 1.500
1061 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5181168 | GARFIELD AVENUE FROM NEWLAND STREET TO MAGNOLIA STREET, PAVEMENT REHABILITATION | Pavement Improvement | 2011-02-22 | 2011-02-22 |  | 2011-05-19 | 653141
1062 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182041 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: Construct bicycle & pedestrian improvements along Washington Boulevard & place bonded w | Transportation Enhancements | 2010-04-26 | 2010-04-26 |  | 2010-07-30 | 800000 | 0.300
1063 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182046 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: Place hot mix asphalt on Junction Boulevard, Woodcreek Oaks Boulevard & Eureka Road. | Pavement Improvement | 2009-08-24 | 2009-08-24 |  | 2010-11-01 | 1006173 | 5.000
1064 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182048 | This is a Traffic Management Engineering project by a local agency in the City of Roseville. The project is described as: At Douglas & Sierra College Boulevard install E/B & W/B dual left turn lanes, | Other | 2009-08-06 | 2009-08-06 |  | 2010-01-06 | 295436.01 | 0.100
1065 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182049 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: Place hot mix asphalt bonded wearing course to North Sunrise, Eureka Road & to Junctio | Pavement Improvement | 2009-08-17 | 2009-08-17 |  | 2010-01-07 | 844208.46 | 1.000
1066 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182050 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: Pavement overlay to Cirby Way. | Pavement Improvement | 2010-06-28 | 2010-06-28 |  | 2011-01-19 | 1131767 | 1.500
1067 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182051 | This is a Traffic Management Engineering project by a local agency in the City of Roseville. The project is described as: Install CMS on N/B Sunrise Avenue south of Cirby Way per ITS Master Plan. | Safety/Traffic Management | 2009-09-30 | 2009-09-30 |  | 2010-02-11 | 105207.27 | 1.000
1068 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182052 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Roseville. The project is described as: At Sierra College Boulevard & East Roseville Parkway install N/B | Safety/Traffic Management | 2009-09-08 | 2009-09-08 |  | 2009-11-01 | 121208.35 | 0.100
1069 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182054 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: I-inch bonded wearing course placed on Douglas Blvd. | Pavement Improvement | 2010-06-28 | 2010-06-28 |  | 2010-08-30 | 352863 | 1.600
1070 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182055 | CHURCH ST, BASELINE RD, JUNCTION BL, FOOTHILLS BL, ATLANTIC ST & PLEASANT GROVE, MICROPAVE RESURFACING | Pavement Improvement | 2011-09-06 | 2011-09-06 |  |  | 646182
1071 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5184011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Tehachapi. The project is described as: H St and Mill St: Green St to State Route 58; Rehabilitation | Pavement Improvement | 2010-09-01 | 2010-09-06 |  | 2010-12-22 | 479906.43 | 0.950
1072 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5184014 | "This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Tehachapi. The project is described as: South of Tehachapi Blvd., North of ""F"" St between Green St and | Transportation Enhancements | 2010-04-22 | 2010-05-03 |  | 2011-03-21 | 419551.67 | 0.040
1073 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5185005 | This is a Pavement Resurfacing project by a local agency in the City of Orland. The project is described as: Road maintenance | Pavement Improvement | 2009-10-05 | 2009-10-30 |  | 2009-11-20 | 423181 | 1.070
1074 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5190006 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Blue Lake. The project is described as: Solar Crosswalk flashers, striping, ADA ramp installation, and signa | Transportation Enhancements | 2010-06-16 | 2010-06-21 |  | 2010-08-26 | 89000 | 0.100
1075 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5191004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hillsborough. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-29 | 2009-10-01 |  | 2009-12-30 | 392000 | 2.300
1076 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | TRACY | 11 | 5192028 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Tracy. The project is described as: Reconstruct roadway between Carlton Avenue and 11th Street | Pavement Improvement | 2009-10-08 | 2009-10-26 |  | 2011-04-05 | 1614305.99 | 0.500
1077 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5193030 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Taft. The project is described as: 6th St: Kern St to Warren St; Rehabilitation | Pavement Improvement | 2010-02-16 | 2010-02-16 |  | 2010-06-18 | 297881.67 | 0.260
1078 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5194005 | This is a Pavement Resurfacing project by a local agency in the City of King City. The project is described as: Reconstruct between San Lorenzo and Canal Streets | Pavement Improvement | 2009-11-24 | 2009-12-11 |  | 2010-04-07 | 232000 | 1.000
1079 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5194006 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of King City. The project is described as: Infill sidewalks at various locations near schools. | Transportation Enhancements | 2010-05-20 | 2010-05-24 |  | 2010-07-08 | 197500 | 1.000
1080 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5196032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Daly City. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-21 | 2009-09-28 |  | 2010-01-25 | 1045000 | 0.800
1081 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5196033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Daly City. The project is described as: Rehabilitate local streets | Pavement Improvement | 2010-05-10 | 2010-05-10 |  | 2010-10-11 | 318000 | 0.300
1082 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5197018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sanger. The project is described as: Pulverize existing pavement, remix into base, and cap existing street | Pavement Improvement | 2010-04-07 | 2010-04-07 |  | 2010-10-21 | 398112.93 | 0.500
1083 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO | SAN LUIS OBISPO | 22 | 5199021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arroyo Grande. The project is described as: In Arroyo Grande, resurfacing of West Branch Street from East Gr | Pavement Improvement | 2010-07-06 | 2010-07-06 |  | 2010-11-12 | 525000 | 1.500
1084 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5200028 | This is a Rail/Highway Crossing project by a local agency in the City of Burbank. The project is described as: AT-GRADE CROSSING IMPROVEMENTS INCLUDING OUTBOUND PRE-SIGNALS, CHANGEABLE MESSAGE SIGNS, | Safety/Traffic Management | 2010-10-28 | 2010-11-04 |  | 2011-06-22 | 1041842 | 0.090
1085 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5200029 | This is a Traffic Management Engineering project by a local agency in the City of Burbank. The project is described as: MODERNIZE FOUR TRAFFIC SIGNALS ON BUENA VISTA STREET AND ON HOLLYWOOD WAY AND I | Safety/Traffic Management | 2010-01-25 | 2010-04-20 |  | 2010-09-23 | 377754.22 | 1.000
1086 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5200033 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Burbank. The project is described as: SIDEWALK REMOVAL AND REPLACEMENT AND PEDESTRIAN RAMPS | Transportation Enhancements | 2010-04-28 | 2010-05-03 |  | 2011-01-07 | 661318.87 | 3.000
1087 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5202014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Fernando. The project is described as: ECONOMIC STIMULUS PROJECT- NORTH BRAND BOULEVARD STREET IMPROVEME | Pavement Improvement | 2009-10-19 | 2009-10-19 |  | 2011-05-31 | 745000 | 0.580
1088 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5204011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Glendora. The project is described as: GRAND AVENUE PAVING PROJECT FROM ARROW HIGHWAY TO FOOTHILL BOULEVARD. | Pavement Improvement | 2009-12-16 | 2009-12-16 |  | 2010-03-05 | 1181304.4 | 2.000
1089 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5206011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Angels Camp. The project is described as: Overlay 0.54 miles of Stockton Road | Pavement Improvement | 2010-06-21 | 2010-06-23 |  | 2010-10-14 | 109801.15 | 0.540
1090 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208066 | ASHLAN AVE FROM WHITTIER TO TEMPERANCE & ARMSTRONG SO. OF ASHLAN TO GOULD CANAL, LANDSCAPING IMPROVEMENTS | Transportation Enhancements | 2010-11-01 | 2010-11-12 |  | 2011-11-21 | 116325
1091 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208090 | This is a New Construction Roadway project by a local agency in the City of Clovis. The project is described as: Temperance Ave.: Between Gould Canal and Gettysburg; widen from 2 LU to 4 LD. | Pavement Widening | 2009-10-23 | 2009-10-23 |  | 2010-03-15 | 400000 | 0.750
1092 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208091 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent wi | Pavement Improvement | 2009-09-20 | 2009-09-20 |  | 2010-03-15 | 607855 | 0.500
1093 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208092 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent wi | Pavement Improvement | 2009-09-30 | 2009-09-30 |  | 2010-03-15 | 350000 | 0.500
1094 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208093 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes Nees Ave from | Pavement Improvement | 2009-08-10 | 2009-08-10 |  | 2010-03-15 | 400000 | 0.500
1095 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208095 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Lump-Sum Various AC Overlays/Reconstruction on Eligible Routes. Cons | Pavement Improvement | 2010-05-24 | 2010-05-24 |  | 2011-02-22 | 592555.56 | 0.500
1096 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5210016 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of El Monte. The project is described as: CITYWIDE AND TRANSIT VILLAGE PEDESTRIAN IMPROVEMENTS INCLUDING PEDEST | Transportation Enhancements | 2010-07-14 | 2010-07-19 |  | 2010-12-15 | 1192670 | 5.100
1097 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5210018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Monte. The project is described as: CITYWIDE AND TRANSIT VILLAGE IMPROVEMENTS THAT CALL FOR THE OVERLAY, | Pavement Improvement | 2010-07-14 | 2010-07-19 |  | 2010-11-05 | 3217000 | 7.000
1098 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5212003 | This is a Pavement Resurfacing project by a local agency in the City of Manhattan Beach. The project is described as: AVIATION BLVD. RESURFACING (MARINE AVE. TO MANHATTAN BEACH BLVD.) --- COLD MILL A | Pavement Improvement | 2009-12-03 | 2009-12-07 |  | 2010-01-08 | 151414 | 0.500
1099 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5212004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Manhattan Beach. The project is described as: VALLEY DRIVE STREET IMPROVEMENT PROJECT (15TH STREET TO SEPULV | Pavement Improvement | 2009-12-03 | 2009-12-07 |  | 2010-02-05 | 378837 | 1.300
1100 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5212007 | PACIFIC AVE. FROM MANHATTAN BEACH AVE TO ROSECRANS AVE, RESURFACING AND REHABILITATION | Pavement Improvement | 2011-06-14 | 2011-07-05 |  | 2011-08-22 | 543749
1101 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5213032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sunnyvale. The project is described as: Rehabilitate local street | Bridge Improvement | 2009-08-19 | 2009-09-28 |  | 2009-11-20 | 1225635 | 0.300
1102 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5213033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sunnyvale. The project is described as: pavement repair, asphalt overlay, ADA repairs | Pavement Improvement | 2010-10-18 | 2010-10-25 |  | 2011-06-01 | 417509 | 0.300
1103 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN FRANCISCO-OAKLAND, CA | 14 | 5213034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sunnyvale. The project is described as: pavement repair, asphalt overlay, ADA repairs | Pavement Improvement | 2010-09-07 | 2010-09-20 |  | 2011-06-01 | 869365 | 1.000
1104 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 19 | 5216039 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Reedley. The project is described as: Intersection of Dinuba and Buttonwillow Construct a modern roundabout, | Other | 2010-08-18 | 2010-09-07 |  | 2011-02-22 | 477025 | 1.000
1105 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5217011 | This is a Safety project by a local agency in the City of San Gabriel. The project is described as: LAS TUNAS DR. STREET LIGHTING RETROFIT - GREEN/ENERGY SAVING IMPROVEMENT - PEDESTRIAN/SAFETY LIGHTI | Pavement Improvement | 2010-06-17 | 2010-06-30 |  |  | 1257000 | 2.750
1106 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5218007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Marino. The project is described as: HUNTINGTON DRIVE STREET REHABILITATION PROJECT. FROM SAN MARINO AVE | Pavement Improvement | 2010-09-02 | 2010-09-07 |  | 2010-11-17 | 500000 | 0.750
1107 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5221009 | This is a Pavement Resurfacing project by a local agency in the City of Beverly Hills. The project is described as: RESURFACING OF APPROXIMATELY 8.1 MILES OF PRINCIPAL ARTERIAL AND MAJOR COLLECTOR ST | Pavement Improvement | 2009-10-26 | 2009-11-02 |  | 2009-11-23 | 437174 | 1.100
1108 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5221011 | BENEDICT CANYON RD: SUNSET BLVD - N. CITY LIMIT, ASPHALT OVERLAY WITH RUBBERIZED ASPHALT | Pavement Improvement | 2011-06-06 | 2011-06-06 |  | 2011-08-25 | 621826
1109 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5222018 | This is a Pavement Resurfacing project by a local agency in the City of Fillmore. The project is described as: Edge Grinding & Rubberized Asphalt | Pavement Improvement | 2010-05-26 | 2010-05-26 |  |  | 400000 | 0.820
1110 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5223014 | This is a Pavement Resurfacing project by a local agency in the City of Corcoran. The project is described as: City of Corcoran, Orange Ave. From Otis Ave. to Dairy Ave.; Overlay Roadway | Pavement Improvement | 2010-05-17 | 2010-05-26 |  | 2011-01-03 | 1028451 | 1.000
1111 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5224014 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Firebaugh. The project is described as: Reconstruction of sidewalks and curb cut ramps on O Street from 9 | Transportation Enhancements | 2010-09-09 | 2010-09-20 |  | 2010-12-30 | 160000 | 0.170
1112 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5225020 | This is a Safety project by a local agency in the City of Walnut Creek. The project is described as: Widen sidewalk to better accommodate pedestrian and bicycle traffic on N. Side of Ygnacio Valley R | Transportation Enhancements | 2010-08-09 | 2010-08-09 |  | 2011-01-25 | 436864 | 0.600
1113 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5225022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Walnut Creek. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-09 | 2009-09-10 |  | 2009-11-10 | 882211.2 | 0.830
1114 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5226016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Bruno. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-05-19 | 2010-05-26 |  | 2011-05-26 | 659000 | 1.400
1115 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 20 | 5227036 | This is a Pavement Resurfacing project by a local agency in the City of Delano. The project is described as: 11th Ave from Albany St to High St, 9th Ave from High St to Randolph St, Norwalk St from C | Pavement Improvement | 2010-01-07 | 2010-01-19 |  | 2010-08-02 | 934745 | 3.420
1116 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 5227039 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Delano. The project is described as: 11th Ave from High St. to Randolph St; High St .from Garces Hwy to Ceci | Pavement Improvement | 2010-05-10 | 2010-05-10 |  | 2010-12-06 | 1002581 | 3.000
1117 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5229011 | This is a Pavement Resurfacing project by a local agency in the City of Seal Beach. The project is described as: Grind and Cap .31 miles with rubberized AC | Pavement Improvement | 2011-08-08 | 2011-08-08 |  |  | 496413 | 0.310
1118 | Completed | C250,C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5230002 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Gustine. The project is described as: Reconstruction of Sidewalks and Ramps in the Downtown area in the C | Transportation Enhancements | 2010-04-21 | 2010-04-22 |  | 2010-06-07 | 182762 | 0.700
1119 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5231012 | This is a Pavement Resurfacing project by a local agency in the City of Monterey Park. The project is described as: VARIOUS STREET RESURFACING 2009-01 | Pavement Improvement | 2010-03-15 | 2010-03-22 |  | 2010-09-14 | 1589805.8 | 3.100
1120 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5232009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Corte Madera. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-21 | 2009-11-05 |  | 2009-11-25 | 130772.06 | 0.770
1121 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5235010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Segundo. The project is described as: PAVEMENT REHABILITATION OF MARIPOSA AVENUE - SEPULVEDA BOULEVARD TO | Pavement Improvement | 2010-04-15 | 2010-04-19 |  | 2010-06-07 | 210341.65 | 0.510
1122 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5235011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Segundo. The project is described as: Main Street Rehabilitation - Mariposa Avenue to Imperial Highway | Pavement Improvement | 2009-12-08 | 2009-12-10 |  | 2010-01-12 | 199013.38 | 0.500
1123 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | 5237026 | This is a Pavement Resurfacing project by a local agency in the City of Brea. The project is described as: Associated Road - Birch Street to Imperial Highway | Pavement Improvement | 2010-03-15 | 2010-03-15 |  | 2010-09-10 | 479243.25 | 0.470
1124 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 01 | 5238048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Davis. The project is described as: In Yolo County, rehabilitate various roadways. | Pavement Improvement | 2009-08-17 | 2009-08-17 |  | 2009-11-09 | 732903 | 1.000
1125 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 02 | 5238051 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Davis. The project is described as: Rehabilitate various bikeways in Davis | Transportation Enhancements | 2010-08-16 | 2010-08-16 |  | 2011-03-08 | 636998.86 | 1.000
1126 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 01 | 5238052 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Davis. The project is described as: Construct streetscaping: 2nd St, C-F sts. | Transportation Enhancements | 2010-07-06 | 2010-07-06 |  | 2011-06-16 | 650000 | 1.000
1127 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5239014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Cerrito. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-09-28 | 2010-10-11 |  | 2011-02-25 | 678000 | 1.500
1128 | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5240021 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Culver City. The project is described as: NEW LANDSCAPE IMPROVEMENTS ADJACENT TO BALLONA CREEK BIKEWAY B | Transportation Enhancements | 2010-09-08 | 2010-09-20 |  | 2011-02-21 | 476174 | 0.200
1129 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5240023 | This is a Pavement Resurfacing project by a local agency in the City of Culver City. The project is described as: WASHINGTON BOULEVARD RESURFACING PROJECT BETWEEN HELMS AVENUE AND LA CIENEGA BOULEVAR | Pavement Improvement | 2009-10-14 | 2009-10-23 |  | 2009-12-22 | 619279.35 | 0.500
1130 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5240024 | This is a Pavement Resurfacing project by a local agency in the City of Culver City. The project is described as: GRIND AND OVERLAY 3 INCHES OF ASPHALT ON CULVER BOULEVARD FROM COMMONWEALTH AVENUE TO | Pavement Improvement | 2009-10-22 | 2009-10-28 |  | 2010-04-05 | 172982.63 | 0.350
1131 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 18 | 5241031 | This is a Pavement Resurfacing project by a local agency in the City of Ceres. The project is described as: Arterial Street Overlay. | Pavement Improvement | 2010-06-10 | 2010-06-15 |  | 2010-08-06 | 1271586.78 | 1.500
1132 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5242021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Manteca. The project is described as: Rehabilitation of 9 streets in the City of Manteca | Pavement Improvement | 2009-10-16 | 2009-10-26 |  | 2010-05-11 | 1098498.89 | 4.000
1133 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5242025 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: Landscaping at Route 99/120 interchanges. Plant approximate | Transportation Enhancements | 2010-07-23 | 2010-07-31 |  |  | 909570 | 1.900
1134 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | MANTECA | 11 | 5242027 | SR99 & SR120 CORRIDORS TREE PLANTING, LANDSCAPE ENHANCEMENT | Transportation Enhancements | 2011-01-24 | 2011-02-23 |  |  | 2375000
1135 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5243006 | This is a Pavement Resurfacing project by a local agency in the City of Calipatria. The project is described as: Street Improvements of Rehabilitation and Reconstruction of North and South Portion of | Pavement Improvement | 2010-02-26 | 2010-03-08 |  | 2010-09-07 | 895000 | 0.640
1136 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 18 | 5244022 | This is a Pavement Resurfacing project by a local agency in the City of Newman. The project is described as: Curb, sidewalk, street and intersection improvements | Pavement Improvement | 2010-06-03 | 2010-08-16 |  | 2011-11-15 | 637319 | 1.000
1137 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5245009 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of San Joaquin. The project is described as: Main Street from Arizona Ave. to Placer Ave. Remove and replac | Pavement Improvement | 2010-06-07 | 2010-06-07 |  | 2010-08-11 | 160000 | 0.320
1138 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5246004 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Williams. The project is described as: ELECT. PED. X-WALKS, H/C ACCESS, CURB & GUTTER | Safety/Traffic Management | 2010-10-08 | 2010-10-12 |  |  | 220000 | 1.000
1139 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5247015 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Montebello. The project is described as: NEIGHBORHOOD CITYWIDE SIDEWALK REHABILITATION: REMOVAL AND REPLACEM | Transportation Enhancements | 2009-12-01 | 2009-12-08 |  | 2010-05-14 | 1573305.9 | 0.700
1140 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5247016 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Montebello. The project is described as: WHITTIER BLVD REVITALIZATION: PHASE II; RECONSTRUCTION OF CONCRETE | Transportation Enhancements | 2010-06-16 | 2010-06-16 |  | 2010-12-28 | 671821.53 | 0.500
1141 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5248006 | This is a Safety project by a local agency in the City of Soledad. The project is described as: Install new traffic signal at Oak & Front Streets | Safety/Traffic Management | 2009-06-22 | 2009-06-22 |  | 2010-03-03 | 544891 | 0.120
1142 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5249019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Torrance. The project is described as: CRENSHAW BLVD REHABILITATION, MARICOPA ST TO SEPULVEDA BLVD, CITY OF | Pavement Improvement | 2010-02-09 | 2010-02-09 |  |  | 1229322 | 2.000
1143 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5249021 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Torrance. The project is described as: Del Amo Blvd from Madrone Ave to Chrenshaw Blvd. Construct 0 to 4 la | Pavement Improvement | 2010-11-24 | 2010-11-24 |  |  | 3125678 | 1.000
1144 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5250013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: Atlantic Ave work to include pavement improvements, sidewalk, curb ram | Pavement Improvement | 2010-03-11 | 2010-03-29 |  | 2010-08-03 | 435189.74 | 0.300
1145 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5250014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: Martin Luther King Blvd work to include pavement improvements, sidewal | Pavement Improvement | 2010-01-04 | 2010-01-25 |  | 2010-10-05 | 643052.72 | 0.470
1146 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5250015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: OTIS IMPROVEMENT PROJECT TO INCLUDE PAVEMENT, SIDEWALK, CURB & GUTTER, | Pavement Improvement | 2010-01-04 | 2010-01-25 |  | 2010-08-03 | 309403 | 0.230
1147 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5250016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: IMPERIAL HWY WORK TO INCLUDE PAVEMENT, CURB, GUTTER, CURB RAMPS, RAISE | Pavement Improvement | 2010-03-11 | 2010-05-03 |  | 2011-03-01 | 604076.53 | 0.500
1148 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5251020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Ojai. The project is described as: Road Rehabilitation, various locations | Pavement Improvement | 2010-03-10 | 2010-03-24 |  | 2010-04-29 | 400000 | 1.500
1149 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5252013 | This is a Pavement Resurfacing project by a local agency in the City of Parlier. The project is described as: Asphalt concrete pavement reconstruction and resurfacing | Pavement Improvement | 2010-07-12 | 2010-07-12 |  | 2010-08-15 | 248443 | 0.500
1150 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5253014 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Hawthorne. The project is described as: THE PURPOSE OF THE ALTERATIONS IS TO ENHANCE PUBLIC SAFETY ON A RAIL | Pavement Improvement | 2009-09-30 | 2010-03-12 |  | 2010-03-13 | 35000 | 0.100
1151 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5253015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hawthorne. The project is described as: CITYWIDE STREET IMPROVEMENT PROJECT - The work consists of grinding, | Pavement Improvement | 2009-09-20 | 2009-10-15 |  | 2010-02-15 | 2600000 | 1.000
1152 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5254012 | This is a Pavement Resurfacing project by a local agency in the City of Atwater. The project is described as: Shaffer Road - AC Overlay and Partial reconstruction | Pavement Improvement | 2009-12-14 | 2010-01-27 |  | 2010-09-13 | 568275.82 | 0.700
1153 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5254013 | This is a Pavement Resurfacing project by a local agency in the City of Atwater. The project is described as: Juniper Ave. - AC Overlay and Partial reconstruction | Pavement Improvement | 2009-10-05 | 2009-10-05 |  | 2009-11-03 | 323067.76 | 0.400
1154 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5254014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Atwater. The project is described as: Winton Way from Bellevue Rd. to Livingston Canal | Pavement Improvement | 2011-03-15 | 2011-03-15 |  | 2011-05-06 | 551769 | 0.250
1155 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | 5255042 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Riverbank. The project is described as: Downtown Street Improvements. | Pavement Improvement | 2010-06-01 | 2010-07-06 |  | 2011-01-10 | 331425 | 0.500
1156 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 19 | 5255043 | This is a Pavement Resurfacing project by a local agency in the City of Riverbank. The project is described as: Overlay/sidewalk improvements/curb gutter improvements | Pavement Improvement | 2010-06-01 | 2010-06-28 |  | 2010-08-23 | 317559 | 1.000
1157 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5256009 | This is a Pavement Resurfacing project by a local agency in the City of Livingston. The project is described as: Project involves road grinding, replacement of asphalt concrete, crack sealing of road | Pavement Improvement | 2009-10-02 | 2009-10-05 |  | 2010-04-17 | 550803 | 2.620
1158 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5257022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South Gate. The project is described as: REHABILITATION OF PAVEMENT, RECONSTRUCTION OF DAMAGED CURB AND GUTT | Pavement Improvement | 2010-08-09 | 2010-08-09 |  | 2011-09-13 | 1408326 | 1.300
1159 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5257023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South Gate. The project is described as: RECONSTRUCT ATLANTIC AVE AND IMPROVE DRAINAGE FROM FIRESTONE BLVD T | Pavement Improvement | 2009-09-28 | 2009-09-28 |  | 2011-01-25 | 1186674 | 1.250
1160 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5258026 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Madera. The project is described as: Washington Rd. - Road rehabilitation; curb/gutter/sidewalk, utility | Pavement Improvement | 2011-11-14 | 2011-11-28 |  |  | 357259 | 0.150
1161 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5259017 | This is a Traffic Management Engineering project by a local agency in the City of West Covina. The project is described as: PROJECT CONSISTS OF MODIFYING THE TRAFFIC SIGNALS AT THE INTERSECTIONS OF S | Safety/Traffic Management | 2009-11-17 | 2010-02-16 |  | 2010-03-22 | 213198 | 0.250
1162 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5259018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of West Covina. The project is described as: MAJOR STREET REHABILITATION PROJECT - VARIOUS ARTERIAL STREETS CIT | Pavement Improvement | 2009-11-17 | 2009-11-30 |  | 2010-08-25 | 2954577 | 8.600
1163 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5261006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Atherton. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-07-27 | 2009-07-29 |  | 2009-08-31 | 463060.84 | 0.500
1164 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 38 | 5262004 | This is a Pavement Resurfacing project by a local agency in the City of Signal Hill. The project is described as: GRIND AND OVERLAY APPROXIMATELY 12 LANE MILES OF DETERIORATING PAVEMENT ON A MAJOR AR | Pavement Improvement | 2009-09-14 | 2009-09-14 |  | 2010-03-15 | 500000 | 1.500
1165 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5264003 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Colma. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-11 | 2009-09-22 |  | 2009-10-20 | 131000 | 0.500
1166 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5265010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Maywood. The project is described as: SLAUSON AVENUE CORRIDOR IMPROVEMENT PROJECT STREET & MEDIAN IMPROVEMEN | Pavement Improvement | 2009-10-05 | 2009-10-05 |  | 2010-07-05 | 294847.47 | 1.000
1167 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 34 | 5265011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Maywood. The project is described as: ATLANTIC BLVD. SOUTH: PROJECT INCLUDES REMOVAL AND REPLACEMENT OF AC P | Pavement Improvement | 2009-09-21 | 2009-09-21 |  | 2010-03-31 | 588152.53 | 0.300
1168 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | 5266018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Habra. The project is described as: Rehabilitate 0.75 Miles of roadway on Idaho Street | Pavement Improvement | 2010-02-01 | 2010-02-04 |  | 2010-04-05 | 336897 | 0.750
1169 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5267013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Carlos. The project is described as: Rehabilitate local street | Transportation Enhancements | 2009-09-28 | 2009-09-28 |  | 2010-02-22 | 285510.82 | 0.750
1170 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5267014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Carlos. The project is described as: Rehabilitate local streets | Pavement Improvement | 2010-06-21 | 2010-06-21 |  | 2010-09-13 | 264000 | 1.000
1171 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5268004 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Belmont. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-01-21 | 2010-02-01 |  |  | 1952194 | 0.200
1172 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5268015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Belmont. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-31 | 2009-09-09 |  | 2010-06-08 | 464000 | 0.800
1173 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5268016 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Belmont. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-01-01 | 2010-01-01 |  |  | 2493000 | 0.200
1174 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5269021 | This is a Pavement Resurfacing project by a local agency in the City of Placentia. The project is described as: Rehab and construct asphalt concrete pavement and rubberized asphalt overlay | Pavement Improvement | 2010-03-23 | 2010-04-05 |  | 2010-08-17 | 500000 | 0.530
1175 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | 5271020 | This is a Pavement Resurfacing project by a local agency in the City of Tustin. The project is described as: Jamboree Rd Pavement Rehab. 2750 feet north of Tustin Ranch Rd to Northern city limit. | Pavement Improvement | 2010-03-29 | 2010-04-05 |  | 2010-09-05 | 813324 | 1.400
1176 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5272009 | This is a Pavement Resurfacing project by a local agency in the City of Bell. The project is described as: BANDINI BOULEVARD FROM EASTERN AVENUE TO 26TH STREET. THE PROJECT CONSISTS IN AC OVERLAY AND | Pavement Improvement | 2010-05-12 | 2010-05-17 |  | 2010-08-03 | 517574.59 | 0.800
1177 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5272010 | This is a Pavement Resurfacing project by a local agency in the City of Bell. The project is described as: WILCOX AVENUE REHABILITATION FROM GAGE AVENUE TO RANDOLPH AVENUE. THE PROJECT CONSISTS IN AC | Pavement Improvement | 2010-05-12 | 2010-05-17 |  | 2010-08-10 | 507554 | 0.250
1178 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5273020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Menlo Park. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-03 | 2009-09-14 |  | 2010-03-22 | 635000 | 1.300
1179 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | STATEWIDE | 44 | 5274029 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Clemente. The project is described as: South Ola Vista rehabilitation Phase 2 from 63 feet north of Ave | Pavement Improvement | 2010-06-14 | 2010-06-14 |  | 2011-03-10 | 500000 | 0.750
1180 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5276022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Gardena. The project is described as: WESTERN AVENUE STREET IMPROVEMENT - REDONDO BEACH BLVD. TO EL SEGUNDO | Pavement Improvement | 2009-12-14 | 2009-12-14 |  | 2010-03-24 | 838793.21 | 2.000
1181 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5276023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Gardena. The project is described as: 135TH STREET IMPROVEMENT - CRENSHAW BLVD. TO VERMONT AVE. | Pavement Improvement | 2009-12-14 | 2009-12-14 |  | 2010-03-24 | 795294.08 | 2.000
1182 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5277024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfax. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-03-29 | 2010-03-29 |  | 2010-04-23 | 167000 | 0.960
1183 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5278009 | This is a Pavement Resurfacing project by a local agency in the City of Westmorland. The project is described as: Rehabilitation of 7th Street from H Street to Center Street | Safety/Traffic Management | 2009-11-20 | 2009-11-23 |  | 2010-04-06 | 235672.5 | 0.250
1184 | Completed | C250,C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5279003 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Dos Palos. The project is described as: Replace 400 lineal feet of sidewalk, curb and gutter in downtown Dos | Transportation Enhancements | 2010-06-25 | 2010-08-02 |  | 2011-03-07 | 176610.5 | 0.090
1185 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 5281012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Shafter. The project is described as: Lerdo Hwy: Carver St to Driver Rd; Reconstruction, resurfacing and sho | Pavement Improvement | 2010-04-29 | 2010-05-03 |  | 2010-06-16 | 589437 | 1.500
1186 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | INDIA-COACHELLA | 45 | 5282027 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Palm Springs. The project is described as: Install landscaping, gateway park, ped walkwy | Transportation Enhancements | 2009-11-09 | 2009-11-09 |  |  | 1800000 | 0.250
1187 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | INDIA-COACHELLA | 45 | 5282034 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Widen OC, add/widen ramps, improve circulation | Pavement Widening | 2010-08-10 | 2010-08-23 |  |  | 5517500 | 1.100
1188 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 5283006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palos Verdes Estates. The project is described as: PALOS VERDES DRIVE WEST AT BLUFF COVE ROADWAY STABILIZATI | Pavement Improvement | 2009-11-09 | 2009-11-16 |  | 2010-03-19 | 500000 | 0.050
1189 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5284006 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Woodlake. The project is described as: Install irrigation, lighting, fencing, benches and pathway improv | Transportation Enhancements | 2010-09-01 | 2010-11-01 |  | 2011-02-28 | 206563 | 1.140
1190 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5286012 | This is a Traffic Management Engineering project by a local agency in the City of Ripon. The project is described as: Ehancement of existing roundabout | Pavement Improvement | 2009-11-24 | 2009-12-09 |  | 2010-12-21 | 202131 | 1.000
1191 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5286013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Ripon. The project is described as: Rehabilitation of 3 streets in the City of Ripon | Pavement Improvement | 2010-07-26 | 2010-08-17 |  | 2011-08-02 | 100000 | 1.000
1192 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5286016 | IN THE CITY OF RIPON - SEE STATE COMMENTS, ROAD REHAB | Pavement Improvement | 2010-07-26 | 2010-08-01 |  | 2011-08-02 | 393496
1193 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 5287026 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Wasco. The project is described as: Poso Dr: State Route 43 to Griffith Ave; Reconstruction | Pavement Improvement | 2009-10-14 | 2009-10-21 |  | 2010-04-06 | 917067.19 | 0.400
1194 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 03 | 5288026 | VARIOUS STREETS WITHIN CITY LIMITS, SEE SCOMMENTS, ROAD REHAB & ADA REPLACEMENT | Pavement Improvement | 2011-05-23 | 2011-06-06 |  |  | 1382086.37
1195 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 03 | 5288030 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Folsom. The project is described as: Construct Bike/Ped overcrossing of E. Bidwell | Transportation Enhancements | 2010-04-26 | 2010-04-26 |  | 2011-03-15 | 467422 | 1.000
1196 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 23 | 5289009 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Pismo Beach. The project is described as: In Pismo Beach along the ocean frontage. Improve walkway. Part 2. | Transportation Enhancements | 2010-04-26 | 2010-04-26 |  | 2011-03-31 | 1100000 | 0.070
1197 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5291012 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Kerman. The project is described as: West Kearney Blvd from West of Madera Ave. to Del Norte Ave., instal | Pavement Improvement | 2010-07-27 | 2010-08-02 |  | 2011-05-03 | 258753 | 0.500
1198 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO |  | 03 | 5293012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Galt. The project is described as: In Galt, Rehabilitate roadways. | Pavement Improvement | 2009-08-11 | 2009-09-14 |  | 2010-03-09 | 416140 | 1.000
1199 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO |  | 03 | 5293013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Galt. The project is described as: Construct ADA sidewalk repairs in Galt | Pavement Improvement | 2009-09-21 | 2009-09-23 |  | 2010-03-24 | 298833 | 1.000
1200 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | 5295004 | This is a Pavement Resurfacing project by a local agency in the City of Greenfield. The project is described as: Storm drain improvements | Other | 2010-02-03 | 2010-02-16 |  | 2010-12-01 | 340000 | 1.000
1201 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | 5296003 | This is a Pavement Resurfacing project by a local agency in the City of Gonzales. The project is described as: Reconstruct from southerly city limits to 4th Street including sidewalk and bike lanes | Pavement Improvement | 2009-08-12 | 2009-08-12 |  | 2009-12-14 | 171890.35 | 1.000
1202 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | 5297006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Live Oak. The project is described as: Rehabilitate Apricot St: N St-Broadway | Pavement Improvement | 2009-10-12 | 2009-10-13 |  | 2009-12-18 | 205178 | 1.000
1203 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5299011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Millbrae. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-31 | 2009-09-08 |  | 2009-10-23 | 382000 | 0.500
1204 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5300008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Brentwood. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-31 | 2009-08-31 |  | 2009-10-30 | 1040777.16 | 1.000
1205 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | 5301007 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Orange Cove. The project is described as: Center Street: Between Adams and Park; reconstruction. | Pavement Improvement | 2009-09-21 | 2009-09-23 |  | 2010-08-10 | 200866 | 0.500
1206 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5302006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the Port Hueneme. The project is described as: Street Rehabilitation in Port Hueneme | Pavement Improvement | 2010-07-14 | 2010-08-02 |  | 2010-09-03 | 400000 | 1.400
1207 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5303013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Pablo. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-28 | 2009-10-05 |  | 2010-09-20 | 694000 | 0.850
1208 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5304007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Capitola. The project is described as: Road repairs : Capitola Road to Clares | Pavement Improvement | 2009-08-07 | 2009-09-01 |  | 2009-11-25 | 230000 | 0.300
1209 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5305009 | This is a Pavement Resurfacing project by a local agency in the City of Huron. The project is described as: Street Improvements from Los Angeles to Lassen Ave. Overlay existing pavement and construct | Pavement Improvement | 2010-06-01 | 2010-06-04 |  | 2010-09-29 | 160000 | 0.100
1210 | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5306013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Campbell. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-03-22 | 2010-03-22 |  | 2011-12-12 | 2260000 | 0.400
1211 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5306018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Campbell. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-21 | 2009-09-21 |  | 2009-12-04 | 548088.95 | 0.420
1212 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | SAN BERNARDINO-RIVERSIDE | 43 | 5307018 | This is a Preservation of Abandoned Railway Corridors project by a local agency in the City of Fontana. The project is described as: The project will construct a recreational trail in City of Fontan | Transportation Enhancements | 2011-01-18 | 2011-01-18 |  |  | 300001 | 1.000
1213 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5309013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Altos. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-12 | 2009-10-12 |  | 2010-01-12 | 220105.32 | 2.000
1214 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5310031 | This is a Pavement Resurfacing project by a local agency in the City of Buena Park. The project is described as: Rehabilitation of approx 0.53 mi of Knott from La Palma to Crescent, including rehabil | Pavement Improvement | 2010-04-06 | 2010-04-13 |  | 2010-08-03 | 600277 | 0.530
1215 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5310034 | KNOTT AVENUE FROM LINCOLN AVENUE TO CRESCENT AVENUE, PAVEMENT RECONSTRUCTION | Pavement Widening | 2011-06-30 | 2011-07-05 |  | 2012-01-11 | 292313
1216 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5312071 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Costa Mesa. The project is described as: Landscape and beautificaion at Fairview Road/I405 Interchange | Transportation Enhancements | 2009-11-02 | 2009-11-02 |  | 2010-03-17 | 500000 | 2.300
1217 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5312074 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Costa Mesa. The project is described as: Santa Ana Improvement Project,from 17th Street to 22nd Street | Pavement Improvement | 2010-01-20 | 2010-02-03 |  | 2010-05-28 | 1100000 | 1.250
1218 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5312079 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Costa Mesa. The project is described as: Wilson street Rehabilitation Project,from Newport Blvd. to Fairview | Pavement Improvement | 2010-10-20 | 2010-11-01 |  | 2011-01-12 | 291264.85 | 0.120
1219 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5312081 | WILSON STREET FROM ANAHEIM AVENUE TO HARBOR BOULEVARD, PAVEMENT REHABILITATION | Pavement Improvement | 2011-01-19 | 2011-02-14 |  | 2011-05-11 | 300000
1220 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5314007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Milpitas. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-01 | 2009-09-02 |  | 2010-01-05 | 735350.7 | 0.600
1221 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5314008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Milpitas. The project is described as: Roadway Resurfacing on 1) Abbott Avenue between Marylinn Drive and Va | Pavement Improvement | 2010-07-30 | 2010-08-03 |  | 2010-10-25 | 702719 | 1.000
1222 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5315006 | This is a Pavement Resurfacing project by a local agency in the City of Lakewood. The project is described as: BLOOMFIELD AVENUE IMPROVEMENTS FROM SOUTH CITY LIMIT TO DEL AMO BOULEVARD - RESURFACE PA | Pavement Improvement | 2009-09-08 | 2009-09-08 |  | 2010-02-09 | 565245.53 | 0.890
1223 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5315007 | This is a Pavement Resurfacing project by a local agency in the City of Lakewood. The project is described as: SOUTH STREET IMPROVEMENTS FROM EAST CITY LIMIT TO LAKEWOOD BOULEVARD - RESURFACE PAVEMEN | Pavement Improvement | 2009-09-08 | 2009-09-08 |  | 2010-02-09 | 1386695.61 | 0.830
1224 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5315008 | CENTRALIA STREET: BLOOMFIELD AVENUE TO STUDEBAKER ROAD, AC OVERLAY AND OTHER IMPROVEMENTS | Pavement Improvement | 2010-11-29 | 2010-11-29 |  | 2011-06-14 | 493058.86
1225 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5316006 | This is a Pavement Resurfacing project by a local agency in the City of Seaside. The project is described as: Reconstruct between south city limits and Broadway Ave | Pavement Improvement | 2009-09-10 | 2009-09-14 |  | 2010-06-04 | 669839 | 1.000
1226 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5318025 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cupertino. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-05 | 2009-10-09 |  |  | 707000 | 0.810
1227 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5319012 | This is a Pavement Resurfacing project by a local agency in the City of La Palma. The project is described as: Orangethorpe Pavement Rehabilitation - Valley View St to Moody St/WCL | Pavement Improvement | 2010-02-16 | 2010-02-16 |  | 2010-06-04 | 317875.08 | 1.000
1228 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5319013 | ORANGETHORPE AVE.: MOODY ST.-SR 91; VALLEY VIEW STREET: ORANGETHORPE-FRESCA DR., BUS PADS, CURB, GUTTER, SIDEWALK, IRRIGATION | Other | 2011-01-14 | 2011-01-27 |  | 2011-02-28 | 214676.98
1229 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5321015 | This is a Pavement Resurfacing project by a local agency in the City of Anderson. The project is described as: 2.95 miles of Preventative Maintenance on major local streets | Pavement Improvement | 2009-09-03 | 2009-09-21 |  | 2009-10-30 | 413491.59 | 2.940
1230 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5322035 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fremont. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-24 | 2009-08-24 |  | 2010-01-20 | 5907000 | 4.280
1231 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 10 | 5322040 | OSGOOD ROAD - WASHINGTON BLVD TO GRIMMER BLVD., RECONSTRUCT EXIXTING PAVEMENT AND OVERLAY. | Pavement Improvement | 2010-08-16 | 2010-08-16 |  |  | 1022422
1232 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5323018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Baldwin Park. The project is described as: RAMONA BOULEVARD ROADWAY PRESERVATION AND REHABILITATION (A)- INT | Pavement Improvement | 2010-08-11 | 2010-08-24 |  |  | 950000 | 0.500
1233 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5323019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Baldwin Park. The project is described as: RAMONA BOULEVARD ROADWAY PRESERVATION AND REHABILITATION - FRANCI | Pavement Improvement | 2010-08-04 | 2010-08-16 |  | 2011-04-07 | 1430000 | 1.000
1234 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5324005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Altos Hills. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-07-16 | 2009-07-20 |  | 2009-08-04 | 316000 | 1.800
1235 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5325012 | This is a Pavement Resurfacing project by a local agency in the City of Cerritos. The project is described as: BLOOMFIELD AVENUE, BETWEEN ARTESIA BOULEVARD AND ALONDRA BOULEVARD: PAVEMENT REHABILITA | Pavement Improvement | 2010-02-02 | 2010-02-02 |  | 2010-08-12 | 1072424.79 | 1.000
1236 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | SAN BERNARDINO-RIVERSIDE | 26 | 5326013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Montclair. The project is described as: Transportation enhancement activities proposed include the installat | Transportation Enhancements | 2010-06-15 | 2010-06-21 |  | 2011-04-08 | 300000 | 0.500
1237 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5327012 | This is a Pavement Resurfacing project by a local agency in the City of Stanton. The project is described as: Dale St. Rehabilitation - Katella Av to Cerritos Av | Pavement Improvement | 2010-02-25 | 2010-03-08 |  | 2010-04-30 | 363924.03 | 0.500
1238 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5327013 | DALE STREET FROM THE SOUTH CITY LIMITS TO CHAPMAN AVENUE, ROAD REHABILITATION | Pavement Improvement | 2010-10-18 | 2010-10-27 |  | 2010-11-05 | 105233.85
1239 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5328063 | This is a Pavement Resurfacing project by a local agency in the City of Garden Grove. The project is described as: To resurface 0.7 miles of Harbor Boulevard (an arterial highway) from Garden Grove t | Pavement Improvement | 2010-03-18 | 2010-03-22 |  | 2010-08-24 | 884512.1 | 0.700
1240 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5330013 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Cypress. The project is described as: Landscape Median Beautification on Moody Street to replace existin | Transportation Enhancements | 2011-04-07 | 2011-04-11 |  |  | 500000 | 1.500
1241 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5330014 | This is a Pavement Resurfacing project by a local agency in the City of Cypress. The project is described as: Street Rehabilitation (Valley View, Cerritos to Katella) | Pavement Improvement | 2010-05-03 | 2010-05-03 |  | 2010-08-23 | 442870.34 | 0.500
1242 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 38 | 5331011 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of La Puente. The project is described as: HACIENDA BLVD. RECONSTRUCTION: RECONSTRUCTION AND/OR OVERLAY OF R | Pavement Improvement | 2009-10-19 | 2009-10-19 |  | 2010-03-30 | 648601.44 | 0.900
1243 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5331012 | This is a Pavement Resurfacing project by a local agency in the City of La Puente. The project is described as: CITYWIDE OVERLAY PROJECT: OVERLAY OF VARIOUS STREETS CITYWIDE | Pavement Improvement | 2009-11-19 | 2009-11-19 |  | 2010-03-31 | 243828.18 | 0.400
1244 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5331015 | LOUKELTON ST: HACIENDA BLVD TO E OF GREYCLIFF AVE, ROAD REHABILITATION | Pavement Improvement | 2011-01-17 | 2011-01-17 |  | 2011-06-13 | 378568.38
1245 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5332014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Saratoga. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-11-09 | 2009-11-09 |  |  | 714000 | 1.300
1246 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5332015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Saratoga. The project is described as: On Saratoga Ave overlay and rehabilitate the remaining segments exclu | Pavement Improvement | 2010-07-12 | 2010-07-12 |  | 2010-08-20 | 137160 | 0.800
1247 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5334034 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Downey. The project is described as: Lakewood Blvd between Telegraph and 5th Street. Widen sections of La | Pavement Improvement | 2010-10-06 | 2010-10-18 |  |  | 3317000 | 5.800
1248 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5336012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Paramount. The project is described as: STREET IMPROVEMENTS IN DOWNEY AVENUE FROM ROSECRANS AVENUE TO GARDEN | Pavement Improvement | 2009-09-08 | 2009-09-08 |  | 2010-09-01 | 678100.17 | 0.760
1249 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5336013 | This is a Pavement Resurfacing project by a local agency in the City of Paramount. The project is described as: ROSECRANS AVENUE IMPROVEMENTS FROM LA RIVER TO GARFIELD AVENUE - RESURFACE PAVEMENT, CO | Pavement Improvement | 2009-10-12 | 2009-10-12 |  | 2010-06-25 | 586087.8 | 0.720
1250 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5336014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Paramount. The project is described as: Improvements in Somerset Boulevard from Orange Avenue to LA River an | Pavement Improvement | 2010-02-22 | 2010-02-22 |  | 2010-09-07 | 435812.03 | 0.470
1251 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5337009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Escalon. The project is described as: Rehabilitation of West Yosemite Avenue between Escalon Avenue and Stan | Pavement Improvement | 2010-03-15 | 2010-03-29 |  | 2010-06-10 | 149714 | 0.250
1252 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5338041 | This is a Pavement Resurfacing project by a local agency in the City of Westminster. The project is described as: Brookhurst St Improvements from Hazard Avenue to Bolsa Avenue | Pavement Improvement | 2009-11-02 | 2009-11-02 |  | 2010-04-28 | 813214 | 0.500
1253 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5339001 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Monte Sereno. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-10 | 2009-08-17 |  | 2009-11-17 | 94000 | 0.500
1254 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5340012 | This is a Pavement Resurfacing project by a local agency in the City of Santa Fe Springs. The project is described as: RESURFACING AND RECONSTRUCTION OF VARIOUS COMMERCIAL AND INDUSTRIAL STREETS | Pavement Improvement | 2010-01-11 | 2010-01-11 |  | 2010-04-19 | 528000 | 0.530
1255 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5341028 | This is a Pavement Resurfacing project by a local agency in the City of Fountain Valley. The project is described as: Resurface Warner Ave and Bushard St | Pavement Improvement | 2010-04-05 | 2010-04-15 |  | 2010-06-11 | 619157 | 1.000
1256 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 20 | 5343002 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of McFarland. The project is described as: W. Perkins Ave: 50 ft east of 3rd St to 320 ft east of 3rd St and | Pavement Improvement | 2009-11-13 | 2009-11-16 |  | 2010-04-16 | 209870.03 | 0.050
1257 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5345005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Irwindale. The project is described as: GLADSTONE STREET FROM IRWINDALE AVENUE TO THE EAST CITY LIMIT. STREE | Pavement Improvement | 2010-03-15 | 2010-03-17 |  | 2010-06-29 | 500000 | 0.300
1258 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5346009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Duarte. The project is described as: HUNTINGTON DRIVE FROM WEST CITY LIMITS TO EAST CITY LIMITS. REHABILITA | Pavement Improvement | 2010-07-19 | 2010-07-19 |  | 2010-09-15 | 679000 | 2.460
1259 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5347032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Norwalk. The project is described as: REHABILITATE FRONT STREET FROM SAN ANTONIO DRIVE TO ROSECRANS AVENUE. | Pavement Improvement | 2010-01-04 | 2010-01-04 |  | 2010-05-18 | 370772.31 | 0.770
1260 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5347033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Norwalk. The project is described as: REHABILITATE FIRESTONE BOULEVARD FROM HOXIE AVENUE TO IMPERIAL HIGHWAY | Pavement Improvement | 2010-04-01 | 2010-05-03 |  | 2010-12-15 | 623000 | 0.910
1261 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5347034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Norwalk. The project is described as: REHABILITATE STUDEBAKER ROAD FROM IMPERIAL HIGHWAY TO ALONDRA BOULEVAR | Pavement Improvement | 2010-02-01 | 2010-04-12 |  | 2011-01-31 | 1492417.88 | 2.000
1262 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5348016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Bellflower. The project is described as: REHABILITATION OF DOWNEY AVENUE, NORTH CITY LIMIT TO SOUTH CITY LIM | Pavement Improvement | 2010-05-26 | 2010-06-14 |  | 2011-02-14 | 434918.32 | 0.500
1263 | Underway | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5348018 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Bellflower. The project is described as: WEST BRANCH GREENWAY MULTI-MODAL CORRIDOR LANDSCAPING | Transportation Enhancements | 2011-07-21 | 2011-07-21 |  |  | 823313 | 2.500
1264 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 5349005 | This is a Traffic Management Engineering project by a local agency in the City of Rolling Hills Estates. The project is described as: TRAFFIC SIGNAL MODIFICATION AT PALOS VERDES DRIVE NORTH AND CRENS | Safety/Traffic Management | 2010-02-22 | 2010-02-22 |  | 2010-09-13 | 53758.59 | 0.100
1265 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 5349006 | This is a Safety project by a local agency in the City of Rolling Hills Estates. The project is described as: INSTALL LED INTERNALLY ILLUMINATED STREET NAME SIGNS CITYWIDE | Safety/Traffic Management | 2010-07-13 | 2010-10-11 |  | 2010-12-22 | 65472 | 0.100
1266 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 5349007 | This is a Pavement Resurfacing project by a local agency in the City of Rolling Hills Estates. The project is described as: STREET RESURFACING ON PALOS VERDES DRIVE NORTH BETWEEN CRENSHAW BLVD. AND S | Pavement Improvement | 2010-07-13 | 2010-07-26 |  | 2010-12-22 | 380089 | 0.600
1267 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5350016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pacifica. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-21 | 2009-09-28 |  | 2010-12-13 | 677000 | 2.000
1268 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5351017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pico Rivera. The project is described as: BEVERLY BLVD. PAVEMENT REHABILITATION, TRAFFIC SIGNAL MODIFICATION | Pavement Improvement | 2010-05-17 | 2010-05-17 |  | 2011-11-30 | 1960000 | 1.260
1269 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5352011 | This is a Pavement Resurfacing project by a local agency in the City of South El Monte. The project is described as: POTRERO AVENUE FROM RUSH STREET TO SOUTH END (CITY LIMITS)- COLLECTOR 2 INCH OVERL | Pavement Improvement | 2010-09-07 | 2010-09-07 |  | 2010-11-09 | 580641.41 | 0.600
1270 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5353005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Walnut. The project is described as: Nogales Street from southerly city limit to Amar. Rehabilitate pavemen | Pavement Improvement | 2009-12-14 | 2009-12-14 |  | 2010-03-12 | 755431 | 0.500
1271 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5355021 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Artesia. The project is described as: SOUTH STREET PEDESTRIAN BIKEWAY AND TRANSIT IMPROVEMENTS. PROJECT PRO | Transportation Enhancements | 2009-11-09 | 2009-11-09 |  | 2010-05-03 | 402866 | 0.500
1272 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5357005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Half Moon Bay. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-07 | 2009-08-15 |  | 2010-04-20 | 210000 | 0.500
1273 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5358010 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Rosemead. The project is described as: THE PROJECT CONSISTS IN THE CONSTRUCTION AND UPGRADE OF CURB RAMPS AT | Pavement Improvement | 2010-04-19 | 2010-05-10 |  | 2010-10-15 | 1684000 | 5.150
1274 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO | SAN LUIS OBISPO | 23 | 5359015 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Grover Beach. The project is described as: Fourth Street to the Railroad Tracks (Improve and upgrade lan | Transportation Enhancements | 2009-12-22 | 2010-03-23 |  | 2011-01-21 | 856000 | 0.170
1275 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5360008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lawndale. The project is described as: THE PROJECT WILL MAKE VARIOUS STREET IMPROVEMENTS TO ROSECRANS AVENUE | Pavement Improvement | 2009-12-01 | 2009-12-14 |  | 2010-04-19 | 986997 | 1.000
1276 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5361022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Novato. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-19 | 2009-10-19 |  | 2010-09-28 | 1062000 | 6.000
1277 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 38 | 5362014 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Commerce. The project is described as: THIS PROJECT IS AT THE INTERSECTION OF GARFIELD AVENUE AND SLAUSON | Pavement Improvement | 2009-11-28 | 2009-11-28 |  | 2011-02-03 | 500000 | 0.100
1278 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5363010 | This is a Pavement Resurfacing project by a local agency in the City of Los Alamitos. The project is described as: Pavement Rehabilitation | Pavement Improvement | 2010-03-15 | 2010-03-30 |  | 2010-07-21 | 342480.98 | 0.400
1279 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5364005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Mirada. The project is described as: Stage Road from Alondra Boulevard to east City Limit. Selective Rec | Pavement Improvement | 2010-02-01 | 2010-02-01 |  | 2010-05-05 | 731019 | 0.800
1280 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5364006 | This is a Pavement Resurfacing project by a local agency in the City of La Mirada. The project is described as: LA MIRADA BOULEVARD FROM OAKWOOD LANE TO LEFFINGWELL ROAD. SELECTIVE RECONSTRUCTION OF | Pavement Improvement | 2010-05-10 | 2010-06-21 |  | 2010-11-23 | 378109.71 | 1.100
1281 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5365003 | This is a Safety project by a local agency in the City of Temple City. The project is described as: NEW TRAFFIC SIGNAL ON TEMPLE CITY BLVD. AT ELLIS LANE: INSTALLATION OF A NEW SIGNAL. COMPONENTS INC | Safety/Traffic Management | 2010-01-22 | 2010-04-26 |  | 2010-06-14 | 118108.65 | 1.000
1282 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5365004 | This is a Pavement Resurfacing project by a local agency in the City of Temple City. The project is described as: CITY STREETS OVERLAY PROJECT: GRIND AND OVERLAY OF VARIOUS CITY STREETS | Pavement Improvement | 2010-01-26 | 2010-02-15 |  | 2010-04-14 | 599000 | 0.800
1283 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5365005 | This is a Traffic Management Engineering project by a local agency in the City of Temple City. The project is described as: TRAFFIC SIGNAL UPGRADES | Pavement Improvement | 2010-05-10 | 2010-07-12 |  | 2010-12-16 | 124174 | 1.000
1284 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 26 | 5367006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Dimas. The project is described as: SAN DIMAS AVENUE RECONSTRUCTION, REHABILITATION AND LANDSCAPE MEDIAN | Pavement Improvement | 2009-10-26 | 2009-10-29 |  | 2011-12-15 | 1085000 | 0.700
1285 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5369008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cudahy. The project is described as: LIVE OAT STREET STREET REHABILITATION PROJECT FROM WILCOX AVENUE TO SAL | Pavement Improvement | 2010-07-27 | 2010-08-02 |  | 2011-01-14 | 663000 | 1.300
1286 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5370021 | This is a Pavement Resurfacing project by a local agency in the City of Arvin. The project is described as: Campus Drive: State Route 223 to Grapevine Drive; Reconstruction | Pavement Improvement | 2010-07-15 | 2010-08-10 |  | 2010-10-28 | 622882 | 0.250
1287 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5371005 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Weed. The project is described as: Rehabilitate 1.63 miles of streets within the City of Weed with asphal | Pavement Improvement | 2010-04-20 | 2010-06-24 |  | 2010-06-28 | 498591.12 | 1.630
1288 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5372012 | This is a Pavement Resurfacing project by a local agency in the City of San Juan Capistrano. The project is described as: AC Overlay on Camino Capistrano | Pavement Improvement | 2010-05-17 | 2010-05-18 |  |  | 500000 | 1.300
1289 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5373012 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bell Gardens. The project is described as: CITYWIDE STREET REHABILITATION: LOCAL STREET RECONSTRUCTION AN | Pavement Improvement | 2009-11-30 | 2009-11-30 |  | 2010-01-13 | 414700 | 1.000
1290 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5373013 | This is a Pavement Resurfacing project by a local agency in the City of Bell Gardens. The project is described as: CITYWIDE STREET OVERLAY: RAC OVERLAY OF STREETS. | Pavement Improvement | 2009-09-16 | 2009-09-16 |  | 2010-02-02 | 745800 | 0.700
1291 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 10 | 5375021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasant Hill. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-19 | 2009-08-19 |  | 2010-11-01 | 842000 | 0.710
1292 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5376008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Brisbane. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-07-10 | 2009-07-13 |  | 2009-09-29 | 131000 | 0.100
1293 | Underway | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5377006 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Villa Park. The project is described as: Taft Ave Median Improvements from Lemon Street to Cannon Street | Transportation Enhancements | 2010-09-20 | 2010-09-20 |  |  | 223983 | 1.000
1294 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5377012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Villa Park. The project is described as: This is a pavement rehabilitation project on Santiago Blvd. from Pr | Pavement Improvement | 2010-01-20 | 2010-02-03 |  | 2010-03-10 | 435500.96 | 2.200
1295 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5378019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palmdale. The project is described as: 2009 ARTERIAL REHABILITATION AND RECONSTRUCTION PROGRAM | Pavement Improvement | 2009-09-16 | 2009-09-16 |  | 2010-09-01 | 4072751.09 | 24.580
1296 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5379017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rohnert Park. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-13 | 2009-08-27 |  |  | 869000 | 3.210
1297 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5383007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cotati. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-11-09 | 2009-11-09 |  | 2010-03-10 | 492445.74 | 0.340
1298 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5385038 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Ridgecrest. The project is described as: College Heights Blvd: Dolphin Ave to Franklin Ave; Reconstructio | Pavement Improvement | 2010-11-01 | 2010-11-02 |  | 2011-06-17 | 513579 | 0.250
1299 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5385040 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Ridgecrest. The project is described as: College Heights Blvd: China Lake Blvd to Dolphin Ave - Roadway R | Pavement Improvement | 2010-11-01 | 2010-11-02 |  | 2011-06-17 | 521360 | 0.330
1300 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 10 | 5386009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Clayton. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-18 | 2009-08-24 |  | 2009-10-06 | 355854 | 1.100
1301 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 39 | 5387009 | This is a Pavement Resurfacing project by a local agency in the City of Hawaiian Gardens. The project is described as: NORWALK BOULEVARD FROM CENTRALIA STREET TO SOUTH CITY LIMIT - RESURFACE PAVEMENT | Pavement Improvement | 2009-10-05 | 2009-10-05 |  | 2009-12-29 | 428059.66 | 0.560
1302 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5388008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Tiburon. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-21 | 2009-11-02 |  | 2009-12-24 | 203000 | 1.000
1303 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5390004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Portola Valley. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-18 | 2009-09-24 |  | 2009-12-18 | 196000 | 0.600
1304 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO | SAN LUIS OBISPO | 22 | 5391012 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Morro Bay. The project is described as: In North Morro Bay install overlay, widening and striping to provide | Transportation Enhancements | 2010-09-07 | 2010-10-04 |  | 2011-06-14 | 480000 | 1.800
1305 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | THOUSAND OAKS | 23 | 5392039 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Thousand Oaks. The project is described as: Bicycle Path from Janss Rd. to Paige Ln. | Transportation Enhancements | 2010-06-25 | 2010-06-28 |  | 2011-05-19 | 1071356 | 1.320
1306 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | THOUSAND OAKS | 24 | 5392040 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Thousand Oaks. The project is described as: Improvements to lane configurations leading to and from the inte | Other | 2010-01-04 | 2010-01-04 |  |  | 5196325 | 0.750
1307 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | THOUSAND OAKS | 23 | 5392041 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Thousand Oaks. The project is described as: Rehabilitation of Moorpark Road between Wilbur Road and Columbia | Pavement Improvement | 2010-10-04 | 2010-10-19 |  |  | 1091194 | 2.310
1308 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5393020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Camarillo. The project is described as: Annual Pavement Rehab at Various Location | Pavement Improvement | 2009-11-23 | 2009-12-07 |  | 2010-02-24 | 1099966 | 2.450
1309 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5393023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Camarillo. The project is described as: Annual Pavement Rehabilitation at Various Arterial Streets | Pavement Improvement | 2010-08-04 | 2010-09-13 |  | 2011-03-09 | 519192 | 2.700
1310 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA | SAN FRANCISCO-OAKLAND, CA | 01 | 5395001 | This is a Safety project by a local agency in the City of Yountville. The project is described as: Build Class I bike path along E side of Hwy 29. | Transportation Enhancements | 2010-03-17 | 2010-03-29 |  | 2010-11-02 | 1000000 | 0.800
1311 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5396006 | This is a Pavement Resurfacing project by a local agency in the City of Rio Dell. The project is described as: Roadway Rehabilitation, Paving and Pedestrian Improvements on Wildwood Avenue | Pavement Improvement | 2010-06-21 | 2010-07-06 |  | 2010-11-27 | 576000 | 0.300
1312 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5397009 | This is a Pavement Resurfacing project by a local agency in the City of Carpinteria. The project is described as: Pavement Rehabilitation of Various Streets in the City of Carpinteria | Pavement Improvement | 2010-07-20 | 2010-08-09 |  | 2010-12-03 | 596535 | 1.800
1313 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5399014 | This is a Traffic Management Engineering project by a local agency in the City of California City. The project is described as: Intersection of Cal City Blvd, Cal City Blvd South, Proctor Blvd, Rands | Safety/Traffic Management | 2010-04-22 | 2010-05-05 |  | 2010-08-10 | 542341.69 | 1.000
1314 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ |  | 17 | 5400014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Scotts Valley. The project is described as: Road preservation | Pavement Improvement | 2010-04-01 | 2010-04-05 |  | 2010-07-30 | 115000 | 3.100
1315 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5400015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Scotts Valley. The project is described as: Road preservation | Pavement Improvement | 2010-04-05 | 2010-06-01 |  | 2010-08-30 | 160000 | 0.400
1316 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | 5402026 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Yorba Linda. The project is described as: Pavement Rehabilitation on Village Center Drive from Manzanita to | Pavement Improvement | 2010-03-22 | 2010-03-29 |  | 2010-04-30 | 279620 | 1.000
1317 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | 5402028 | YORBA LINDA BOULEVARD FROM EAST OF VAN BUREN STREET TO CASA LOMA AVENUE, PAVEMENT REHABILITATION | Pavement Improvement | 2011-02-04 | 2011-02-04 |  | 2011-03-16 | 199640
1318 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5403014 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Carson. The project is described as: BROADWAY IMPROVEMENTS FROM 168TH ST. TO NORTH CITY LIMIT (ALONDRA B | Pavement Improvement | 2009-11-02 | 2009-11-16 |  |  | 2000000 | 0.400
1319 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 10 | 5404020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lafayette. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-04 | 2009-08-31 |  | 2009-10-16 | 706277.78 | 2.250
1320 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5405050 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Simi Valley. The project is described as: Major Street Rehabilitation, various locations | Pavement Improvement | 2009-08-03 | 2009-08-03 |  | 2010-08-05 | 1080532 | 2.350
1321 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5405056 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Simi Valley. The project is described as: Major Street Rehabilitation, various locations | Pavement Improvement | 2010-03-22 | 2010-03-23 |  | 2010-06-09 | 979779.01 | 1.000
1322 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 19 | 5406019 | This is a Pavement Resurfacing project by a local agency in the City of Waterford. The project is described as: Major collector Street Overlay. | Pavement Improvement | 2010-04-08 | 2010-04-13 |  | 2010-06-25 | 610770 | 2.650
1323 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5409015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Foster City. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-14 | 2009-09-14 |  | 2009-09-30 | 378455.79 | 0.500
1324 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | 5410065 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Irvine. The project is described as: Provide landscaping along the recently graded slopes of the Jeffrey | Transportation Enhancements | 2010-02-04 | 2010-03-15 |  | 2011-05-11 | 344073.08 | 1.000
1325 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5410069 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Irvine. The project is described as: Pavement rehabilitation of Red Hill Avenue from Deere to Reynolds. | Pavement Improvement | 2010-02-01 | 2010-02-01 |  | 2010-05-06 | 1954172.84 | 0.670
1326 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 36 | 5413010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rancho Palos Verdes. The project is described as: STREET IMPROVEMENTS ON HAWTHORNE BLVD FROM INDIAN PEAK ROA | Pavement Improvement | 2009-10-19 | 2009-10-19 |  | 2010-08-27 | 1262000 | 4.470
1327 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 10 | 5415010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Moraga. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-15 | 2009-09-15 |  | 2011-05-07 | 609000 | 1.100
1328 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5416006 | This is a Pavement Resurfacing project by a local agency in the City of Marina. The project is described as: Improvements include bike lanes, sidewalk, landscaping and resurfacing | Pavement Improvement | 2009-07-10 | 2009-07-13 |  | 2009-12-11 | 375548 | 1.000
1329 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5416007 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Marina. The project is described as: Infill sidewalks at various locations near schools. | Transportation Enhancements | 2010-06-04 | 2010-06-14 |  | 2010-08-11 | 259500 | 1.000
1330 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5417015 | This is a Pavement Resurfacing project by a local agency in the City of La Canada Flintridge. The project is described as: RESURFACING OF VARIOUS CITY STREETS. | Pavement Improvement | 2009-10-15 | 2009-10-15 |  | 2010-07-16 | 964700 | 2.160
1331 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5417017 | SIX LOCATIONS - SEE "COMMENTS" TAB FOR DESCRIPTION OF THE SIX PROJECT LOCATIONS., RESURFACING, CURB, GUTTER, SIDEWALK, SIGNING, ET | Pavement Improvement | 2010-11-13 | 2010-11-13 |  | 2011-05-18 | 165300
1332 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5419020 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Lancaster. The project is described as: RECONSTRUCTION OF THE NORTH HALF OF AVENUE K FROM 50TH TO 52ND ST | Pavement Improvement | 2009-10-19 | 2009-10-26 |  | 2010-03-08 | 303338.48 | 0.500
1333 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5419021 | This is a Pavement Resurfacing project by a local agency in the City of Lancaster. The project is described as: 2008 STREET REHABILITATION - PHASE II SHALL PERFORM FULL DEPTH RECLAMATION, COLD IN PLA | Pavement Improvement | 2009-09-21 | 2009-09-21 |  | 2010-09-17 | 2226367.62 | 3.800
1334 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5419023 | This is a Traffic Management Engineering project by a local agency in the City of Lancaster. The project is described as: CONSTRUCTION OF TRAFFIC SIGNALS AND MINOR STREET IMPROVEMENTS AT AVENUE L-8 & | Pavement Improvement | 2009-12-30 | 2010-01-04 |  | 2010-04-13 | 1241603.58 | 0.200
1335 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | SAN BERNARDINO-RIVERSIDE | 43 | 5420018 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Rancho Cucamonga. The project is described as: On Church street install landscape with irrigation contr | Transportation Enhancements | 2010-06-07 | 2010-06-14 |  | 2010-09-03 | 100000 | 0.200
1336 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5422002 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Habra Heights. The project is described as: REHABILITATION OF ROADWAY, RESTORATION OF STREET SHOULDER, HA | Pavement Improvement | 2010-01-04 | 2010-01-04 |  | 2010-07-08 | 500000 | 4.160
1337 | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | 5423026 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Atascadero. The project is described as: In Atascadero, between Route 101 southbound ramps and El Camino | Transportation Enhancements | 2011-05-02 | 2011-05-02 |  | 2011-11-05 | 684999 | 0.250
1338 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | 5423027 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Atascadero. The project is described as: In the City of Atascadero, between El Camino Real and Hwy 41, rehab | Pavement Improvement | 2010-06-10 | 2010-07-05 |  | 2011-09-01 | 513000 | 1.250
1339 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5424007 | This is a Pavement Resurfacing project by a local agency in the City of Avenal. The project is described as: City of Avenal, San Joaquin Street, From 7th Ave. to Skyline Blvd.; Rehabilitate Roadway | Pavement Improvement | 2010-10-04 | 2010-10-04 |  | 2010-12-10 | 231946.4 | 1.000
1340 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5424008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Avenal. The project is described as: City of Avenal, San Joaquin Street, From 7th to 3rd, Roadway Reconstruc | Pavement Improvement | 2010-10-04 | 2010-10-04 |  | 2010-12-10 | 246529 | 1.000
1341 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 02 | 5425020 | This is a Pavement Resurfacing project by a local agency in the City of Paradise. The project is described as: Roadway Rehabilitation / Overlays | Pavement Improvement | 2009-09-25 | 2009-10-20 |  | 2011-07-05 | 1497943.04 | 5.100
1342 | Completed | C250,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LAKE |  | 01 | 5427019 | This is a Pavement Resurfacing project by a local agency in the City of Clearlake. The project is described as: Lakeshore Drive to Old Highway 53/Between Rumsey Road and Woodland Drive | Pavement Improvement | 2009-09-10 | 2009-09-21 |  | 2009-10-23 | 813600 | 1.370
1343 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5431006 | This is a Pavement Resurfacing project by a local agency in the City of Westlake Village. The project is described as: This project consists of pavement repair and structural overlay on major arteria | Pavement Improvement | 2010-05-10 | 2010-05-10 |  | 2010-07-14 | 494220.32 | 1.000
1344 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 11 | 5434018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Danville. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-08 | 2009-10-19 |  | 2010-10-12 | 871614 | 2.100
1345 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5435016 | This is a Bridge Rehabilitation, Added Capacity project by a local agency in the City of Agoura Hills. The project is described as: WIDENING OF THE REYES ADOBE ROAD OVERCROSSING OF THE 101 FREEWAY FR | Pavement Widening | 2009-10-01 | 2009-10-14 |  |  | 690000 | 0.200
1346 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5436015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Moorpark. The project is described as: Pavement rehabilitation from Tierra Rejada to Country Hill | Pavement Improvement | 2010-07-12 | 2010-07-12 |  | 2011-05-04 | 618357.75 | 0.450
1347 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 11 | 5437022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Ramon. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-01 | 2009-10-01 |  | 2010-03-31 | 1122000 | 0.880
1348 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5438008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of East Palo Alto. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-11-04 | 2009-12-21 |  | 2010-05-15 | 421000 | 1.900
1349 | Underway | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONO |  | 25 | 5439023 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Mammoth Lakes. The project is described as: Directional and informational signage along the Bike Path, pavin | Transportation Enhancements | 2010-09-13 | 2010-09-20 |  |  | 184560 | 1.000
1350 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5440008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of West Hollywood. The project is described as: SUNSET BLVD FROM WEST CITY BOUNDARY (WEST OF CORY AVE) TO EAST | Pavement Improvement | 2010-01-12 | 2010-01-12 |  | 2011-01-07 | 1105000 | 1.700
1351 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | 5443006 | This is a Pavement Resurfacing project by a local agency in the City of Solvang. The project is described as: 0.75 miles of pavement overlay on Alisal Road | Pavement Improvement | 2009-10-28 | 2009-11-12 |  | 2009-12-15 | 143988 | 0.750
1352 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5444013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Orinda. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-12 | 2009-10-15 |  | 2009-12-11 | 318538.99 | 0.900
1353 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 01 | 5447025 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of West Sacramento. The project is described as: Sacramento Avenue, Jefferson Boulevard and F Street: Rehabilit | Pavement Improvement | 2010-06-10 | 2010-06-10 |  |  | 635802 | 1.000
1354 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450047 | This is a Safety project by a local agency in the City of Santa Clarita. The project is described as: TRAFFIC CIRCULATION AND SAFETY IMPROVEMENTS AT NEWHALL AVENUE AND SIERRA HIGHWAY | Pavement Improvement | 2009-10-12 | 2009-10-12 |  | 2010-01-25 | 282101 | 0.200
1355 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clarita. The project is described as: ASPHALT ROADWAY REHABILITATION PHASE I | Pavement Improvement | 2009-09-30 | 2009-09-30 |  | 2010-07-13 | 1297493 | 1.500
1356 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450049 | This is a Safety project by a local agency in the City of Santa Clarita. The project is described as: WHITES CANYON ROAD AT SOLEDAD CANYON ROAD RIGHT TURN POCKET TRAFFIC CIRCULATION & SAFETY IMPROVEM | Pavement Improvement | 2010-03-10 | 2010-03-19 |  | 2010-05-14 | 429027 | 0.100
1357 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450050 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clarita. The project is described as: ASPHALT ROADWAY REHABILITATION PHASE II. | Pavement Improvement | 2009-09-30 | 2009-09-30 |  | 2010-07-13 | 1361858 | 1.500
1358 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450051 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clarita. The project is described as: BRIDGE REHABILITATION FOR VARIOUS BRIDGES. | Pavement Improvement | 2009-11-30 | 2009-12-09 |  | 2010-03-11 | 365878 | 0.280
1359 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 42 | 5451026 | This is a Pavement Resurfacing project by a local agency in the City of Mission Viejo. The project is described as: Overlay of Portions of Alicia, Trabuco and Olympiad | Pavement Improvement | 2010-01-04 | 2010-01-04 |  | 2010-06-04 | 898537 | 2.200
1360 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5454022 | This is a Pavement Resurfacing project by a local agency in the City of Dana Point. The project is described as: Roadway Resurfacing | Pavement Improvement | 2010-03-15 | 2010-03-15 |  | 2010-05-27 | 396228 | 0.830
1361 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 42 | 5455013 | This is a Pavement Resurfacing project by a local agency in the City of Diamond Bar. The project is described as: PREVENTIVE STREET MAINTENANCE PROGRAM - APPROXIMATELY 10 MILES OF ARTERIAL ROADWAY S | Pavement Improvement | 2009-09-23 | 2009-09-23 |  | 2010-06-07 | 1748978.99 | 10.000
1362 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5456010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lathrop. The project is described as: Rehabilitate roadway between J Street and Thomsen Road | Pavement Improvement | 2009-11-24 | 2010-04-26 |  | 2010-07-23 | 289337.35 | 0.420
1363 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5456011 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Lathrop. The project is described as: Enhancement of existing roadway. | Transportation Enhancements | 2010-06-08 | 2010-06-08 |  | 2011-03-11 | 969100.53 | 1.000
1364 | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5458010 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Laguna Niguel. The project is described as: Construction of new curb and gutter, landscape planters and | Transportation Enhancements | 2010-07-19 | 2010-07-19 |  | 2010-11-09 | 849339.58 | 1.500
1365 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5458014 | This is a Pavement Resurfacing project by a local agency in the City of Laguna Niguel. The project is described as: Construct AC overlay on Aliso Creek Rd. from Alicia Parkway to La Paz Rd. | Pavement Improvement | 2010-02-22 | 2010-02-22 |  | 2010-04-29 | 549010 | 0.500
1366 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5462012 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Malibu. The project is described as: MALIBU CANYON ROAD IMPROVEMENTS AND RECONSTRUCTION PROJECT; RECONSTR | Pavement Improvement | 2010-02-01 | 2010-03-01 |  | 2010-06-14 | 425058.26 | 1.250
1367 | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5463014 | This is a Traffic Management Engineering project by a local agency in the City of Calabasas. The project is described as: CONNECT ALL TRAFFIC SIGNALS WITHIN THE CITY OF CALABASAS TO THE TRAFFIC MANAG | Other | 2010-04-28 | 2010-05-03 |  | 2011-05-31 | 940744.98 | 3.950
1368 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5463015 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Calabasas. The project is described as: CONSTRUCT A SAFE PEDESTRIAN ROUTE FOR STUDENTS TO PASS OVER LAS VIRG | Transportation Enhancements | 2010-07-30 | 2010-08-02 |  | 2011-02-23 | 649999.99 | 0.100
1369 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | STATEWIDE | 45 | 5464029 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Murrieta. The project is described as: Replace Diamond IC with partial Cloverleaf IC | Bridge Improvement | 2009-12-18 | 2009-12-18 |  |  | 9999981 | 1.100
1370 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5468013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Laguna Hills. The project is described as: Pavement Rehabilitation | Pavement Improvement | 2009-12-07 | 2009-12-14 |  | 2010-06-09 | 500000 | 0.720
1371 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5469013 | This is a Pavement Resurfacing project by a local agency in the City of Lake Forest. The project is described as: Trabuco Road Rehabilitation - Lake Forest Dr to South City Limit | Pavement Improvement | 2009-11-30 | 2009-11-30 |  | 2010-01-06 | 603342.54 | 1.100
1372 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA | STATEWIDE | 01 | 5470007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of American Canyon. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-11-02 | 2009-11-02 |  | 2010-03-19 | 320000 | 0.500
1373 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 01 | 5472012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Windsor. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-25 | 2009-08-26 |  | 2009-09-30 | 388799.24 | 0.750
1374 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | Multiple | 5472014 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Windsor. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-04-01 | 2010-04-26 |  | 2010-08-11 | 245079 | 0.250
1375 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5473009 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Truckee. The project is described as: Legacy Trail Phase 3A | Transportation Enhancements | 2010-06-03 | 2010-06-04 |  | 2010-11-09 | 633332 | 0.740
1376 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5474013 | This is a Pavement Resurfacing project by a local agency in the City of Shasta Lake. The project is described as: 1.51miles of Preventative Maintenance on major local streets | Pavement Improvement | 2009-10-07 | 2009-10-15 |  | 2009-12-23 | 409000 | 1.510
1377 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5475022 | This is a Pavement Resurfacing project by a local agency in the City of Citrus Heights. The project is described as: Fair Oaks Blvd., between Oak Avenue and Old Auburn Road: Minor reconstruction, ove | Pavement Improvement | 2009-09-08 | 2009-09-21 |  | 2010-09-02 | 1404058 | 1.000
1378 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5475023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Citrus Heights. The project is described as: Reconstruction and Rehabilitation of Twin Oaks Avenue between A | Pavement Improvement | 2010-06-01 | 2010-06-01 |  | 2010-07-30 | 525631.78 | 1.000
1379 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5475024 | This is a Safety project by a local agency in the City of Citrus Heights. The project is described as: Greenback Ln Streetscape: Mariposa-Birdcage | Other | 2010-05-10 | 2010-05-10 |  | 2011-04-28 | 1049898.43 | 1.000
1380 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5476007 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Laguna Woods. The project is described as: The project involves reconstruction of failed pavement areas, | Pavement Improvement | 2009-10-12 | 2009-10-26 |  | 2010-01-04 | 500000 | 1.300
1381 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10 | 5477003 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakley. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-28 | 2009-09-28 |  | 2009-12-10 | 347491 | 1.300
1382 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10 | 5477004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakley. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-28 | 2009-09-28 |  | 2009-12-10 | 294540 | 0.980
1383 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 42 | 5478010 | This is a Pavement Resurfacing project by a local agency in the City of Rancho Santa Margarita. The project is described as: Remove and Replace 3? of asphalt with asphalt rubber hot mix on Alicia Pkw | Pavement Improvement | 2010-04-01 | 2010-04-19 |  | 2010-06-23 | 297082.23 | 1.000
1384 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 42 | 5478011 | This is a Pavement Resurfacing project by a local agency in the City of Rancho Santa Margarita. The project is described as: Remove and Replace 3? of asphalt with asphalt rubber hot mix on Robinson R | Pavement Improvement | 2010-08-16 | 2010-08-23 |  | 2010-09-22 | 185000 | 1.000
1385 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5479019 | This is a Traffic Management Engineering project by a local agency in the City of Elk Grove. The project is described as: Install ITS components throughout Elk Grove | Safety/Traffic Management | 2009-10-26 | 2009-10-26 |  | 2010-10-13 | 1000000 | 1.000
1386 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5479024 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Elk Grove. The project is described as: Reconstruct I-5 Elk Grove Blvd On-Ramp | Safety/Traffic Management | 2009-09-14 | 2009-09-14 |  | 2010-02-10 | 181294.95 | 1.000
1387 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5479025 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Elk Grove. The project is described as: Rehabilitate roads in various location in Sacramento County. | Pavement Improvement | 2009-08-28 | 2009-08-28 |  | 2010-11-10 | 1823001 | 1.000
1388 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 05 | 5479028 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Elk Grove. The project is described as: Elk Grove-Florin Road from Elk Grove Blvd to Bond Road: Rehabilitate | Pavement Improvement | 2010-05-24 | 2010-06-07 |  | 2010-11-17 | 660400 | 1.000
1389 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5480003 | This is a Pavement Resurfacing project by a local agency in the City of Aliso Viejo. The project is described as: Pacific Park Dr Rehabilitation - Cheyenne to Aliso Viejo Pkwy | Pavement Improvement | 2010-03-17 | 2010-03-17 |  | 2010-04-29 | 437219.7 | 0.480
1390 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5481007 | This is a Traffic Management Engineering project by a local agency in the City of Goleta. The project is described as: Asphalt overlay (grind and replace) on various FAU streets within the City of Go | Pavement Improvement | 2009-11-19 | 2009-11-23 |  | 2010-06-02 | 1270736 | 1.700
1391 | Underway | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 03 | 5482007 | This is a New Construction Roadway project by a local agency in the City of Rancho Cordova. The project is described as: International Dr extension and bike/ped bridge | New Construction | 2009-10-20 | 2009-11-03 |  |  | 1050000 | 1.000
1392 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5482010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rancho Cordova. The project is described as: Coloma Road, from McGregor Dr to Sunrise Blvd: Rehabilitate roa | Pavement Improvement | 2009-07-20 | 2009-08-04 |  | 2010-04-14 | 1121360 | 1.000
1393 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: Rehabilitate Oceanview Dr.: Mouth of Smith River Rd. to 1100 ft. S | Pavement Improvement | 2009-08-19 | 2009-08-25 |  | 2009-09-08 | 239500.73 | 1.400
1394 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901035 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Del Norte. The project is described as: Improve El Dorado St.: Hamilton Ave. to High School. | Transportation Enhancements | 2009-08-14 | 2009-08-17 |  | 2009-08-31 | 28216.62 | 0.190
1395 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: Rehabilitation of Pebble Beach Dr. from Hemlock Ave. to Washington | Pavement Improvement | 2009-08-19 | 2009-08-24 |  | 2009-09-04 | 150764.19 | 0.860
1396 | Completed | C250,C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: Overlay Lake Earl Drive & Bike lanes (0.95 miles) | Pavement Improvement | 2010-08-27 | 2010-09-07 |  | 2010-11-15 | 292322.35 | 0.950
1397 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901039 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: El Dorado Street Rehabilitation from Hamilton Ave. to High School | Pavement Improvement | 2009-08-24 | 2009-08-25 |  | 2009-09-04 | 74355.83 | 0.190
1398 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5902060 | This is a Pavement Resurfacing project by a local agency in the County of Siskiyou. The project is described as: Near Hornbrook Rehab Copco Rd | Pavement Improvement | 2009-08-18 | 2009-08-21 |  | 2009-10-12 | 1002333.39 | 3.200
1399 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5902061 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Siskiyou. The project is described as: Near Mount Shasta City, along Lake Siskiyou. Construct multi-use tr | Transportation Enhancements | 2010-03-12 | 2010-03-15 |  | 2010-10-14 | 1200000 | 0.100
1400 | Completed | C250,C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MODOC |  | 04 | 5903048 | This is a Pavement Resurfacing project by a local agency in the County of Modoc. The project is described as: Asphalt Concrete Overlay on Modoc County Road 54 and various City streets. Overlay Pedes | Pavement Improvement | 2010-09-20 | 2010-10-04 |  | 2011-06-07 | 789758 | 5.800
1401 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904097 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Rehabilitation and paving | Pavement Improvement | 2009-10-23 | 2009-10-23 |  | 2010-02-16 | 425794.56 | 1.020
1402 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904098 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Rehabilitation and paving | Pavement Improvement | 2009-11-06 | 2009-12-14 |  | 2010-11-09 | 486990.97 | 0.760
1403 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904101 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Rehabilitation and paving | Pavement Improvement | 2009-10-06 | 2009-10-06 |  | 2010-02-01 | 191657 | 0.290
1404 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904104 | REDWOOD DR FROM PM 3.11 (REDWAY) TO PM 4.85 (US HWY 101), AC OVERLAY, RECONSTRUCT RETAINING WALL | Pavement Improvement | 2011-06-06 | 2011-06-13 |  | 2011-11-08 | 740870
1405 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904105 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Humboldt. The project is described as: Rehabilitation and paving | Pavement Improvement | 2010-06-14 | 2010-07-12 |  | 2011-01-04 | 273770.69 | 1.000
1406 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TRINITY |  | 02 | 5905079 | This is a Bridge Rehabilitation, Added Capacity project by a local agency in the County of Trinity. The project is described as: Widen bridge, replace rails, resurface deck, paint. | Bridge Improvement | 2010-01-05 | 2010-04-01 |  | 2010-10-19 | 556248 | 0.300
1407 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5906096 | This is a Pavement Resurfacing project by a local agency in the County of Shasta. The project is described as: 37.7 miles of Preventative Maintenance on major local streets | Pavement Improvement | 2009-07-31 | 2009-09-10 |  | 2009-12-07 | 2595435 | 42.150
1408 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA | REDDING | 02 | 5906097 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Shasta. The project is described as: Construct East Redding Bike Lanes Phase 1 | Transportation Enhancements | 2010-01-14 | 2010-04-19 |  | 2010-07-12 | 680217 | 2.190
1409 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5906102 | DESCHUTES ROAD FROM STATE ROUTE 299 TO BOYLE ROAD, ASPHALT CONCRETE OVERLAY | Pavement Improvement | 2010-10-18 | 2010-11-01 |  | 2010-11-30 | 223565
1410 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LASSEN |  | 04 | 5907055 | This is a Pavement Resurfacing project by a local agency in the County of Lassen. The project is described as: Asphalt Concrete Overlay and shoulder backing | Pavement Improvement | 2009-09-15 | 2009-09-23 |  | 2009-10-15 | 777240 | 3.500
1411 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | LASSEN |  | 04 | 5907056 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Lassen. The project is described as: Right of Way for bicycle path | Transportation Enhancements | 2011-06-14 | 2011-06-24 |  | 2011-08-22 | 48117 | 0.500
1412 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA |  | 02 | 5908083 | This is a Pavement Resurfacing project by a local agency in the County of Tehama. The project is described as: Overlay of San Benito Avenue | Pavement Improvement | 2009-10-12 | 2009-11-09 |  | 2010-07-30 | 1242258 | 4.100
1413 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA |  | 02 | 5908084 | This is a Pavement Resurfacing project by a local agency in the County of Tehama. The project is described as: Overlay two sections of County Road 99W | Pavement Improvement | 2010-12-22 | 2011-04-11 |  | 2011-06-28 | 1155093 | 3.000
1414 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLUMAS |  | 04 | 5909088 | This is a Pavement Resurfacing project by a local agency in the County of Plumas. The project is described as: HMA Overlay - 2.2 lane miles | Pavement Improvement | 2010-09-14 | 2010-09-15 |  | 2010-09-22 | 353632.62 | 1.100
1415 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLUMAS |  | 04 | 5909089 | This is a Pavement Resurfacing project by a local agency in the County of Plumas. The project is described as: HMA Overlay - 2.0 lane miles | Pavement Improvement | 2010-09-17 | 2010-09-20 |  | 2010-10-14 | 415175.82 | 2.000
1416 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5910071 | This is a Pavement Resurfacing project by a local agency in the County of Mendocino. The project is described as: Asphalt Concrete Overlay for designated segment | Pavement Improvement | 2010-05-20 | 2010-05-20 |  | 2010-07-12 | 1593153 | 10.490
1417 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5910079 | COMPTCHE-UKIAH ROAD, ROADWAY REHABILITATION - OVERLAY | Pavement Improvement | 2011-07-05 | 2011-07-07 |  | 2011-07-13 | 578673
1418 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 02 | 5912082 | This is a Pavement Resurfacing project by a local agency in the County of Butte. The project is described as: Roadway Overlay | Pavement Improvement | 2009-10-19 | 2009-10-21 |  | 2009-11-12 | 660000 | 3.300
1419 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | Multiple | 5912083 | This is a Pavement Resurfacing project by a local agency in the County of Butte. The project is described as: Roadway Overlay | Pavement Improvement | 2009-09-11 | 2009-09-24 |  | 2009-10-26 | 620000 | 3.300
1420 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 04 | 5912084 | This is a Landscaping and Other Scenic Beautification project by a local agency in the County of Butte. The project is described as: On Lincoln between Elgin St and Arnold Ave. Adds Landscaping and b | Transportation Enhancements | 2011-10-17 | 2011-10-17 |  | 2011-11-04 | 75000 | 1.000
1421 | Completed | C250,C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SIERRA |  | 04 | 5913045 | This is a Scenic or Historic Highway Programs project by a local agency in the County of Sierra. The project is described as: Multimodal travel information facility- visitor center Highway 49 | Transportation Enhancements | 2009-09-28 | 2009-11-04 |  | 2010-08-06 | 105593.05 | 0.000
1422 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SIERRA |  | 04 | 5913047 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Sierra. The project is described as: Construction of Sidewalk from SR49 to Loyalton High School | Transportation Enhancements | 2010-06-29 | 2010-07-06 |  | 2010-09-03 | 89885.7 | 1.000
1423 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LAKE |  | 01 | 5914060 | This is a Pavement Resurfacing project by a local agency in the County of Lake. The project is described as: Riviera West Drive to State Route 281 | Pavement Improvement | 2010-05-28 | 2010-06-14 |  | 2010-07-16 | 882159.83 | 2.400
1424 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LAKE |  | 01 | 5914062 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Lake. The project is described as: Construction of Bike Lanes at Various Locations | Transportation Enhancements | 2010-08-16 | 2010-08-23 |  | 2010-10-18 | 132254 | 0.660
1425 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5915062 | This is a Pavement Resurfacing project by a local agency in the County of Colusa. The project is described as: Place a 3/8 inch single chip on the existing Asphalt Concrete roadway | Pavement Improvement | 2010-06-21 | 2010-06-28 |  | 2010-08-09 | 176830.96 | 5.720
1426 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5915065 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Colusa. The project is described as: On Hall St From Ninth St to Putnam Wy, Install new Sidewalk and place | Transportation Enhancements | 2010-06-01 | 2010-06-14 |  | 2010-07-24 | 26747 | 0.150
1427 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5915067 | NORMAN ROAD IN TOWN OF PRINCETON, INSTALL DRIVER SPEED FEEDBACK SIGN | Other | 2010-09-07 | 2010-09-16 |  | 2010-10-26 | 79000
1428 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | 5916079 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yuba. The project is described as: La Porte Road from Challenge Cutoff Road to west Butte County Line and | Pavement Improvement | 2009-07-01 | 2009-07-16 |  | 2009-08-12 | 995038 | 1.000
1429 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | 5916083 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yuba. The project is described as: Rehabilitate various roadways in Yuba County | Pavement Improvement | 2009-10-14 | 2009-11-06 |  | 2011-01-11 | 1102834.95 | 1.000
1430 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917059 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Nevada. The project is described as: Hirschdale Rd. from I-80 Exit to bridge over Truckee River & Glenshir | Pavement Improvement | 2009-09-21 | 2009-09-21 |  | 2009-11-05 | 250000 | 1.500
1431 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917061 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Nevada. The project is described as: Along Penn Valley Dr. - Western Gateway Park to Pleasant Valley Rd./H | Transportation Enhancements | 2010-05-07 | 2010-05-28 |  | 2010-08-19 | 258488.73 | 0.800
1432 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917062 | This is a Pavement Resurfacing project by a local agency in the County of Nevada. The project is described as: Magnolia Road - Lake of the Pines entrance construct center turn lane & related roadway | Pavement Improvement | 2010-06-15 | 2010-06-21 |  | 2010-08-13 | 588317 | 1.000
1433 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917063 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the County of Nevada. The project is described as: La Barr Meadows Rd. from Grass Valley City limits to the vicinity | Pavement Improvement | 2010-09-16 | 2010-09-17 |  | 2010-11-10 | 683848 | 3.500
1434 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917064 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the County of Nevada. The project is described as: West of Grass Valley - East Pleasant Valley Rd. North of Ridge Roa | Pavement Improvement | 2010-05-14 | 2010-05-24 |  | 2010-07-09 | 681414.43 | 4.600
1435 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917065 | WOLF ROAD FROM SR 49 TO DUGANS ROAD, ROADWAY RECONSTRUCTION | Pavement Improvement | 2010-10-05 | 2010-10-12 |  | 2010-11-17 | 162800
1436 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | 5918072 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sutter. The project is described as: In Sutter County, rehabilitate various roadways. | Pavement Improvement | 2009-10-19 | 2009-11-16 |  | 2010-01-15 | 651463 | 1.000
1437 | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER | SACRAMENTO | 02 | 5918073 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sutter. The project is described as: Road Rehabilitation - Acacia Ave (South Butte Rd - Butte House Rd), N | Pavement Improvement | 2010-07-19 | 2010-07-26 |  | 2010-08-27 | 425115.3 | 4.020
1438 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER |  | 04 | 5919084 | This is a Pavement Resurfacing project by a local agency in the County of Placer. The project is described as: Overlay segments of following roads: Barton Road; Douglas Boulevard; Sierra College Boul | Pavement Improvement | 2010-05-14 | 2010-05-14 |  | 2010-07-16 | 1970962 | 8.000
1439 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER |  | 04 | 5919089 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Placer. The project is described as: Widen Auburn-Folsom Road to four lanes from Placer / Sacramento Count | Pavement Improvement | 2009-12-11 | 2010-01-04 |  | 2011-10-07 | 2068237 | 6.000
1440 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5919091 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Placer. The project is described as: This project is located on Foresthill Road 4.9 miles East of the inte | Pavement Improvement | 2011-07-07 | 2011-07-25 |  |  | 100000 | 0.250
1441 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA |  | Multiple | 5920116 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sonoma. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-04-19 | 2010-04-19 |  | 2010-10-15 | 6376000 | 60.000
1442 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA |  | Multiple | 5920121 | LEVERONI ROAD, BODEGA HIGHWAY, MARK WEST SPRINGS ROAD, BENNETT VALLEY ROAD., ROAD REHABILITATION | Pavement Improvement | 2010-10-25 | 2011-07-18 |  |  | 2695944
1443 | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | 5921045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Napa. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-19 | 2009-11-09 |  | 2010-02-23 | 471069.89 | 3.800
1444 | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | 5921046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Napa. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-12 | 2009-11-02 |  | 2010-02-23 | 585915.86 | 1.100
1445 | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | 5921048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Napa. The project is described as: Silverado Trail Phase D - Larkmead Lane to Bale Lane | Pavement Improvement | 2010-06-14 | 2010-06-14 |  | 2010-11-09 | 286083.16 | 1.200
1446 | Underway | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | 5921049 | SILVERADO TRAIL PHASE D LARKMEAD TO BALE LANE, REHABILITATION | Pavement Improvement | 2010-08-26 | 2010-09-13 |  |  | 433757
1447 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 01 | 5922084 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Yolo. The project is described as: Bikeways and rehabilitation: CR 99, 29, 99D | Transportation Enhancements | 2009-08-04 | 2009-08-17 |  | 2009-09-15 | 368568 | 1.000
1448 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 02 | 5922085 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yolo. The project is described as: Rehabilitate CR 22 Roadway. | Pavement Improvement | 2009-08-19 | 2009-09-17 |  | 2010-03-16 | 907937 | 1.000
1449 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 02 | 5922087 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yolo. The project is described as: Reconstruct portion of County Rd. 31 from Davis City limits to County R | Pavement Improvement | 2010-07-02 | 2010-07-26 |  | 2010-09-22 | 276234 | 6.000
1450 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO |  | Multiple | 5923088 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Solano. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-06-25 | 2009-06-29 |  | 2009-08-07 | 2000000 | 10.400
1451 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO |  | Multiple | 5923092 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Solano. The project is described as: Construct path, landscaping, historical markers, benches along Cordel | Transportation Enhancements | 2010-01-12 | 2010-02-01 |  |  | 800000 | 0.600
1452 | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO |  | Multiple | 5923093 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Solano. The project is described as: Pavement overlay with minor widening. | Pavement Improvement | 2010-06-10 | 2010-06-15 |  | 2010-06-25 | 388195 | 3.900
1453 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5924159 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sacramento. The project is described as: In Sacramento County, rehabilitate various roadways. | Pavement Improvement | 2009-08-21 | 2009-09-08 |  |  | 10865138.01 | 1.000
1454 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5924161 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Sacramento. The project is described as: ADA sidewalk improvements in Sac. County | Transportation Enhancements | 2009-10-21 | 2009-11-02 |  | 2011-01-17 | 2973695 | 1.000
1455 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5924162 | This is a Traffic Management Engineering project by a local agency in the County of Sacramento. The project is described as: Replace and upgrade traffic signals | Safety/Traffic Management | 2011-06-30 | 2011-07-11 |  |  | 3150000 | 1.000
1456 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925069 | This is a Pavement Resurfacing project by a local agency in the County of El Dorado. The project is described as: Forni Rd from Ray Lawyer Dr to Placerville Dr: rehabilitate roadways | Pavement Improvement | 2009-08-24 | 2009-08-24 |  | 2009-08-27 | 633349.32 | 0.700
1457 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925071 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of El Dorado. The project is described as: Phase 1B includes reconfig of I/C to a 4-lane tight diamond, const | Transportation Enhancements | 2010-01-19 | 2010-01-19 |  |  | 5173967 | 1.500
1458 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925072 | This is a Pavement Resurfacing project by a local agency in the County of El Dorado. The project is described as: Lotus Rd from Wunschel Ln to State Route 49: rehabilitate roadways | Pavement Improvement | 2009-09-25 | 2009-09-25 |  | 2009-10-22 | 1717941.85 | 6.570
1459 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925073 | This is a Pavement Resurfacing project by a local agency in the County of El Dorado. The project is described as: Malcolm Dixon Rd from Salmon Falls Rd to Green Valley Rd: rehabilitate roadways | Pavement Improvement | 2009-10-06 | 2009-10-06 |  | 2009-11-02 | 439255 | 2.040
1460 | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO | SACRAMENTO | 04 | 5925078 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of El Dorado. The project is described as: Latrobe Road from Cothrin Ranch Road to South Shingle Road: rehabi | Pavement Improvement | 2010-10-08 | 2010-10-08 |  | 2010-12-08 | 917206.97 | 3.700
1461 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925080 | "This is a Pavement Restoration and Rehabilitation project by a local agency in the County of El Dorado. The project is described as: Complete 2"" AC Overlay + repair of structural deficient pavement | Pavement Improvement | 2010-08-30 | 2010-08-30 |  | 2010-09-27 | 558320 | 2.020
1462 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | 5926043 | This is a Safety project by a local agency in the County of Amador. The project is described as: Reconstruct Intersection and Approaches | Pavement Improvement | 2010-07-22 | 2010-08-02 |  | 2010-09-07 | 250751.61 | 0.300
1463 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | 5926044 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the County of Amador. The project is described as: Reconstruct failing pavement section from PM 2.12 to 3.12. | Pavement Improvement | 2010-08-10 | 2010-08-19 |  | 2010-09-29 | 355367.33 | 1.000
1464 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | 5926045 | This is a Safety project by a local agency in the County of Amador. The project is described as: Traffic Sign Replacement on various streets throughout the County | Safety/Traffic Management | 2010-02-22 | 2010-04-07 |  | 2010-12-20 | 403868.4 | 1.000
1465 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5927068 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Marin. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-05 | 2009-10-08 |  | 2011-02-15 | 1993434.25 | 3.990
1466 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5927070 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Marin. The project is described as: Atherton Ave - Highway 37 MP 0.12 to 730 ft east of Olive Ave MP 1.27, | Pavement Improvement | 2010-08-25 | 2010-09-08 |  | 2011-05-10 | 1272590 | 1.000
1467 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5928091 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Contra Costa. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-17 | 2009-08-17 |  | 2009-10-28 | 1945770 | 5.100
1468 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | STATEWIDE | 10 | 5928093 | This is a Safety project by a local agency in the County of Contra Costa. The project is described as: Widen and construct a concrete median barrier along Vasco Rd for a 1 mile segment. | Safety/Traffic Management | 2010-04-26 | 2010-04-26 |  |  | 11279083 | 1.000
1469 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | STATEWIDE | 10 | 5928103 | MARSH CREEK ROAD FROM BYRON HIGHWAY TO VASCO ROAD, AND CROSS STREETS, PAVEMENT OVERLAY | Pavement Improvement | 2010-09-29 | 2010-09-29 |  | 2011-03-22 | 1764728.41
1470 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5929197 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Resurface roadway between Jack Tone Road and State Route 120 | Pavement Improvement | 2009-10-02 | 2009-10-13 |  | 2009-11-12 | 784874.26 | 3.400
1471 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5929198 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Resurface roadway between French Camp Road and State Route 120 | Pavement Improvement | 2009-10-12 | 2009-10-30 |  | 2009-11-13 | 472124.56 | 2.000
1472 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5929199 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Resurface roadway between Plymouth Road and Alexandria Place | Pavement Improvement | 2009-10-02 | 2009-10-13 |  | 2009-10-26 | 213437.62 | 0.600
1473 | Completed | C250,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STATEWIDE | 11 | 5929200 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Rubberized chip seal of 10 roadways in San Joaquin County | Pavement Improvement | 2009-10-05 | 2009-10-05 |  | 2011-08-11 | 4168169 | 30.000
1474 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5929204 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Joaquin. The project is described as: Rehabilitate roadway between Airport Way and Austin Road | Pavement Improvement | 2010-05-06 | 2010-06-01 |  | 2010-06-21 | 894126.77 | 4.000
1475 | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 18 | 5929221 | ALPINE AVENUE (WALLACE AVENUE TO RYDE AVENUE), RESURFACE EXISTING RD ,REPLACE CURB,GUTTER,SIDEWA | Pavement Improvement | 2011-06-06 | 2011-06-13 |  |  | 508926
1476 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930043 | This is a Pavement Resurfacing project by a local agency in the County of Calaveras. The project is described as: Rehab of Olive Orchard Rd. | Pavement Improvement | 2010-07-20 | 2010-08-02 |  | 2010-10-01 | 208274 | 1.700
1477 | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930044 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Calaveras. The project is described as: Rehab of Meko Dr. | Pavement Improvement | 2010-07-20 | 2010-08-02 |  | 2010-10-01 | 139058 | 1.100
1478 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Calaveras. The project is described as: Rehab of Pennsylvania Gulch Rd. | Pavement Improvement | 2010-07-20 | 2010-08-02 |  | 2010-10-01 | 150092 | 1.200
1479 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Calaveras. The project is described as: Rehab of Watertown Rd. | Pavement Improvement | 2010-07-20 | 2010-08-02 |  | 2010-10-01 | 217608 | 1.800
1480 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930047 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Calaveras. The project is described as: Rehab of Independence Rd. | Pavement Improvement | 2010-07-20 | 2010-08-02 |  | 2010-10-01 | 273653 | 2.300
1481 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930050 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Calaveras. The project is described as: Class II Bikeway in West-Point | Transportation Enhancements | 2010-09-13 | 2010-09-27 |  | 2011-02-08 | 34762.97 | 0.050
1482 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930052 | PARROT'S FERRY RD, MAIN ST & TWO SECTIONS OF RAILROAD FLAT RD, ROADWAY PREVENTATIVE MAINTENANCE | Pavement Improvement | 2011-07-01 | 2011-07-11 |  |  | 436936
1483 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930057 | CALAVERAS COUNTY, WEST POINT BIKEWAY-BICYCLE SAFETY TRAINING | Transportation Enhancements | 2011-02-16 | 2011-02-16 |  |  | 48993
1484 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALPINE |  | 03 | 5931017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alpine. The project is described as: Rehabilitation of County roads Emigrant Trail and roads in Alpine Vil | Pavement Improvement | 2010-06-21 | 2010-07-09 |  | 2010-08-20 | 158536.56 | 3.600
1485 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TUOLUMNE |  | 19 | 5932055 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Tuolumne. The project is described as: County highway J59 Upgrade (HPP project to upgrade existing county | Pavement Improvement | 2010-04-30 | 2010-05-03 |  | 2011-04-05 | 2146000 | 12.500
1486 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TUOLUMNE |  | 19 | 5932058 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Tuolumne. The project is described as: Sugar Pine Trail ? Phase 1A (In Tuolumne County along the Sugar Pin | Pavement Improvement | 2011-05-02 | 2011-05-09 |  | 2011-09-20 | 249514 | 1.100
1487 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5933098 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alameda. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-12-11 | 2009-12-11 |  | 2011-02-10 | 1383127 | 1.650
1488 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | LIVERMORE | 10 | 5933099 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alameda. The project is described as: ALTAMONT PASS ROAD- GRANT LN TO LANDFILL ENTR , PAVEMENTS REHAB AND | Pavement Improvement | 2009-10-30 | 2009-10-30 |  | 2010-11-16 | 1200000 | 1.650
1489 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5933101 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alameda. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-04-01 | 2010-06-21 |  | 2010-11-16 | 420000 | 1.700
1490 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5933103 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Alameda. The project is described as: Sidewalk improvements along San Miguel Avenue between Castro Valley | Transportation Enhancements | 2010-08-24 | 2010-09-07 |  | 2011-07-22 | 711097 | 0.400
1491 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934147 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-19 | 2009-08-19 |  | 2010-07-29 | 1410277 | 0.700
1492 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934148 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-02 | 2009-09-02 |  | 2010-09-02 | 910742.99 | 0.630
1493 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934149 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street/streetscape improvements | Pavement Improvement | 2009-09-14 | 2009-09-14 |  | 2010-08-11 | 2395831 | 0.700
1494 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 12 | 5934150 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-21 | 2009-09-21 |  | 2010-05-27 | 2787467 | 1.200
1495 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934151 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-10 | 2009-08-10 |  | 2010-04-28 | 415810.57 | 0.080
1496 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934152 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-03-01 | 2010-03-01 |  | 2010-10-17 | 2000000 | 0.700
1497 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934153 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the San Francisco County. The project is described as: Construct ADA compliant curb ramps at various locations | Transportation Enhancements | 2010-02-15 | 2010-02-15 |  | 2011-06-17 | 782592 | 1.000
1498 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934156 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 2010-08-09 | 2010-08-09 |  | 2011-03-11 | 990672 | 1.000
1499 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | STATEWIDE | 08 | 5934157 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Construct ADA compliant curb ramps at various locations | Pavement Improvement | 2010-09-20 | 2010-09-20 |  | 2011-06-24 | 651921 | 1.000
1500 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934158 | HOLLOWAY AVE BETWEEN JULES AVE AND HAROLD AVE, CURBRAMP, SIDEWALK AND GUTTER RECONSTRUCTION | Transportation Enhancements | 2010-11-29 | 2010-11-29 |  | 2011-04-08 | 317208
1501 | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934160 | CORBIN PLACE FROM 17TH STREET TO CORBETT AVENUE, STAIRWAY REHAB | Transportation Enhancements | 2011-02-28 | 2011-02-28 |  | 2011-06-23 | 417339
1502 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5935054 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Mateo. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-25 | 2009-09-29 |  | 2010-04-21 | 1725666.7 | 4.000
1503 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5936076 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Cruz. The project is described as: Road repairs: various roadways | Pavement Improvement | 2009-07-21 | 2009-07-22 |  | 2009-10-30 | 2132931.73 | 4.800
1504 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | Multiple | 5936081 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Cruz. The project is described as: Road repairs: various roadways; cape seals | Pavement Improvement | 2010-07-08 | 2010-07-13 |  | 2011-06-28 | 2545068 | 1.000
1505 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5937132 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Clara. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-07-14 | 2009-07-20 |  | 2009-12-16 | 2676319.99 | 2.700
1506 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5937133 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Clara. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-25 | 2009-09-08 |  | 2010-01-26 | 958999.99 | 2.330
1507 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5937162 | CENTRAL EXPRESSWAY (BETWEEN LAWRENCE EXPRESSWAY AND MARY AVENUE, AUXILLIARY LANES | Pavement Improvement | 2010-07-20 | 2010-08-16 |  | 2011-02-08 | 300000
1508 | Completed | C250,C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | 5938164 | This is a Pavement Resurfacing project by a local agency in the County of Stanislaus. The project is described as: Cape Seal Various Roads. | Pavement Improvement | 2010-08-11 | 2010-08-11 |  | 2010-12-31 | 4798051.7 | 55.000
1509 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | 5938166 | This is a Traffic Management Engineering project by a local agency in the County of Stanislaus. The project is described as: Traffic Signal Improvements. | Safety/Traffic Management | 2010-06-08 | 2010-07-26 |  | 2011-03-14 | 1366675 | 0.530
1510 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | 5938170 | This is a Pavement Resurfacing project by a local agency in the County of Stanislaus. The project is described as: Cape/Seal Streets Preventive Maintenenace | Pavement Improvement | 2010-09-07 | 2010-09-07 |  | 2010-11-11 | 491490.3 | 1.000
1511 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED | MERCED | 18 | 5939066 | This is a Pavement Resurfacing project by a local agency in the County of Stanislaus. The project is described as: Various locations | Pavement Improvement | 2010-05-18 | 2010-06-28 |  | 2010-09-13 | 771264.27 | 20.400
1512 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5939069 | This is a Bridge Rehabilitation, No Added Capacity project by a local agency in the County of Stanislaus. The project is described as: Avenue Two at Canal Creek (BR No. 39C-0278) | Bridge Replacement | 2010-06-30 | 2010-07-26 |  | 2011-05-20 | 1308605.21 | 0.330
1513 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5939073 | HENRY MILLER ROAD FROM SR33 TO SR 165, SCRUB SEAL OF EXISTING AC SURFACE | Pavement Improvement | 2010-10-06 | 2010-10-19 |  | 2010-12-13 | 348109.24
1514 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIPOSA |  | 19 | 5940075 | This is a Pavement Resurfacing project by a local agency in the County of Mariposa. The project is described as: Rehabilitation of various roadways in Mariposa County | Pavement Improvement | 2010-10-04 | 2011-06-22 |  | 2011-11-30 | 197167 | 6.010
1515 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIPOSA |  | 19 | 5940076 | This is a Pavement Resurfacing project by a local agency in the County of Mariposa. The project is described as: Rehabilitation of various roadways in Mariposa County | Pavement Improvement | 2010-10-04 | 2011-06-23 |  | 2011-11-30 | 65592 | 1.750
1516 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIPOSA |  | 19 | 5940080 | This is a Pavement Resurfacing project by a local agency in the County of Mariposa. The project is described as: Rehabilitation of various roadways in Mariposa County. | Pavement Improvement | 2010-10-04 | 2011-06-20 |  | 2011-11-30 | 291756 | 8.050
1517 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5941068 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Madera. The project is described as: Pedestrian sidewalk | Transportation Enhancements | 2010-05-19 | 2010-06-14 |  | 2010-07-03 | 109112 | 1.000
1518 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5941072 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Madera. The project is described as: Avenue 15 - Road 29 to Road 35 alignment | Pavement Improvement | 2009-10-21 | 2009-10-28 |  | 2010-10-22 | 1868824 | 6.000
1519 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5941075 | This is a Pavement Resurfacing project by a local agency in the County of Madera. The project is described as: Maintenance overlay | Pavement Improvement | 2010-09-15 | 2010-09-27 |  | 2010-11-19 | 525000 | 2.000
1520 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5941077 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Madera. The project is described as: Rd 26 from Club Drive to Ave 21 | Pavement Improvement | 2010-09-15 | 2010-09-27 |  | 2010-11-19 | 545679 | 2.000
1521 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5942178 | This is a Pavement Resurfacing project by a local agency in the County of Fresno. The project is described as: AC Overlays on Cedar Avenue btwn Mt. Whitney/Elkhorn, Annadale Ave btwn Riverbend(S)/1.3 | Pavement Improvement | 2010-04-30 | 2010-06-01 |  | 2010-08-02 | 2882548.75 | 10.000
1522 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5942182 | This is a Landscaping and Other Scenic Beautification project by a local agency in the County of Fresno. The project is described as: Plant palm trees on Kearney Boulevard between Marks Avenue & West | Transportation Enhancements | 2010-09-23 | 2010-09-23 |  |  | 473150 | 5.900
1523 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5942189 | VARIOUS LOCATIONS - SEE COMMENT SCREEN, AC OVERLAYS | Pavement Improvement | 2011-04-19 | 2011-04-19 |  | 2011-05-20 | 192671
1524 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BENITO |  | 17 | 5943048 | This is a Pavement Resurfacing project by a local agency in the County of San Benito. The project is described as: On Southside Road from Union Road to Southside Bridge, Roadway Rehabilitation. | Pavement Improvement | 2009-09-08 | 2009-09-28 |  | 2010-04-07 | 851092 | 3.000
1525 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BENITO |  | 17 | 5943049 | This is a Pavement Resurfacing project by a local agency in the County of San Benito. The project is described as: In San Benito County, on Fairview Road from SR 25 to SR 156. | Pavement Improvement | 2010-04-23 | 2010-04-26 |  | 2010-05-13 | 218891.89 | 1.000
1526 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BENITO |  | 17 | 5943050 | This is a Pavement Resurfacing project by a local agency in the County of San Benito. The project is described as: In San Benito County, on Union Road from SR 25 to SR 156. | Pavement Improvement | 2010-04-23 | 2010-04-26 |  | 2010-05-13 | 121419.72 | 1.000
1527 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5944095 | This is a Pavement Resurfacing project by a local agency in the County of Monterey. The project is described as: Overlay Espinosa Road between MP .04 and MP 4.72 | Safety/Traffic Management | 2009-08-10 | 2009-08-14 |  | 2009-12-02 | 2108637.99 | 4.680
1528 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5945075 | This is a Pavement Resurfacing project by a local agency in the County of Kings. The project is described as: Kings County, Kansas Ave., From 4th Ave. to SR 43; Overlay Roadway | Pavement Improvement | 2010-10-07 | 2010-10-12 |  | 2010-11-12 | 1130000 | 1.000
1529 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5945077 | This is a Pavement Resurfacing project by a local agency in the County of Kings. The project is described as: In Kings County, Houston Ave. From 2nd Ave. to 7th Ave., Overlay Roadway | Pavement Improvement | 2010-10-07 | 2010-10-12 |  | 2010-11-12 | 906780.73 | 1.000
1530 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5946094 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Tulare. The project is described as: County of Tulare - Resurfacing Ave 384 from Rd 99 to Rd 80 | Pavement Improvement | 2010-08-02 | 2010-08-16 |  | 2011-01-11 | 2297706 | 7.000
1531 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5946096 | This is a Pavement Resurfacing project by a local agency in the County of Tulare. The project is described as: County of Tulare - Road 124, Diagonal 134 & Avenue 192 from Elk Bayou to Road 152 | Pavement Improvement | 2010-07-12 | 2010-07-13 |  | 2011-01-11 | 2758494.61 | 4.330
1532 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5946097 | This is a Pavement Resurfacing project by a local agency in the County of Tulare. The project is described as: County of Tulare - Avenue 232 from Kings County to City of Tulare | Pavement Improvement | 2010-07-12 | 2010-07-19 |  | 2011-01-11 | 4124000 | 8.000
1533 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONO |  | 25 | 5947037 | This is a Pavement Resurfacing project by a local agency in the County of Mono. The project is described as: Rehabilitation of 1.5 miles of two-lane major collector including a 2 inch overlay with ho | Pavement Improvement | 2010-04-13 | 2010-05-17 |  | 2010-06-11 | 340000 | 1.500
1534 | Underway | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | MONO |  | 25 | 5947038 | This is a Landscaping and Other Scenic Beautification project by a local agency in the County of Mono. The project is described as: The Lee Vining Streetscape Project - is a landscaping and scenic b | Transportation Enhancements | 2010-11-16 | 2010-11-16 |  |  | 174000 | 0.800
1535 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | 5948069 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the County of Inyo. The project is described as: Reconstruct approx 0.5 mi of Barlow and 0.1 miles of Saniger install | Pavement Improvement | 2009-10-01 | 2009-10-06 |  | 2010-08-09 | 988558 | 2.900
1536 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | 5948070 | This is a Establishment of Transportation Museums project by a local agency in the County of Inyo. The project is described as: Scan historic transportation-related photographs, create museum exhibit | Transportation Enhancements | 2010-09-21 | 2010-10-27 |  | 2011-08-31 | 24980.5 | 0.000
1537 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 23 | 5949117 | This is a Pavement Resurfacing project by a local agency in the County of San Luis Obispo. The project is described as: In South San Luis Obispo County (Nipomo), extend Willow Road from Pomeroy Road | New Construction | 2010-06-18 | 2010-07-21 |  | 2011-06-30 | 1709000 | 0.680
1538 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | 5949118 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Luis Obispo. The project is described as: Road repairs : (1) Lopez Dr:Orcutt Rd. to Lopez Lake Dam ( | Pavement Improvement | 2009-10-30 | 2009-11-01 |  | 2010-09-21 | 1757741 | 5.500
1539 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5950307 | This is a Pavement Resurfacing project by a local agency in the County of Kern. The project is described as: Lerdo Highway: State Route 33 to I-5 (portions); Resurfacing, Rehabilitation | Pavement Improvement | 2010-05-06 | 2010-05-20 |  | 2010-09-07 | 1425989 | 6.200
1540 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 20 | 5950308 | This is a Pavement Resurfacing project by a local agency in the County of Kern. The project is described as: Lerdo Highway: Wildwood Rd to CL (Poplar Ave); Resurfacing, Rehabilitation | Pavement Improvement | 2010-01-05 | 2010-02-02 |  | 2010-04-19 | 1054439 | 8.100
1541 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5950310 | This is a Pavement Resurfacing project by a local agency in the County of Kern. The project is described as: Garlock Rd: State Route 395 to 5 miles west; Resurfacing, Rehabilitation | Pavement Improvement | 2009-11-05 | 2010-02-15 |  | 2010-04-05 | 1394715 | 5.000
1542 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 5950312 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Kern. The project is described as: King Rd: Twisselman Road to County Line Rd; Resurfacing, Rehabilitation | Pavement Improvement | 2009-11-05 | 2009-12-04 |  | 2010-01-12 | 928883.12 | 4.500
1543 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5950313 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Kern. The project is described as: Twisselman Road: Interstate 5 to Kings Road - Rehabilitate/Reconstruct | Pavement Improvement | 2010-07-01 | 2010-07-10 |  | 2010-11-24 | 4199241 | 7.400
1544 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5950317 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Kern. The project is described as: In Bakersfield: Inyo St, Tulare St, Kern St, Baker St, King St, Crawfor | Transportation Enhancements | 2010-04-29 | 2010-05-11 |  | 2010-08-25 | 417766.82 | 2.900
1545 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5950328 | LERDO HIGHWAY: SR33 TO I-5 PHASE II, CONST. 6' PAV'D SHLDR & 2' DIRT BAK- SEE COMMENTS | Pavement Improvement | 2011-01-06 | 2011-01-31 |  | 2011-06-30 | 2137162
1546 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | Multiple | 5951124 | This is a Pavement Resurfacing project by a local agency in the County of Santa Barbara. The project is described as: AC Overlay Various Streets and Roads | Pavement Improvement | 2009-06-24 | 2009-07-06 |  | 2009-10-23 | 1522082.74 | 5.000
1547 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | Multiple | 5951125 | This is a Bridge Rehabilitation, No Added Capacity project by a local agency in the County of Santa Barbara. The project is described as: Seal Cracks in the Bridge decks in Santa Barbara County | Bridge Improvement | 2009-06-24 | 2009-07-13 |  | 2009-10-23 | 341154.18 | 1.000
1548 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | Multiple | 5951126 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Barbara. The project is described as: Concrete Sidewalk Installation and Repairs - Various Streets a | Transportation Enhancements | 2009-06-24 | 2009-08-03 |  | 2009-10-23 | 605999.99 | 1.000
1549 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 23 | 5951128 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Santa Barbara. The project is described as: Streetscape repair and installation of circulation improvement | Transportation Enhancements | 2010-01-08 | 2010-02-15 |  | 2010-04-28 | 454837 | 1.000
1550 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | 5951129 | This is a Traffic Management Engineering project by a local agency in the County of Santa Barbara. The project is described as: Intersection Improvements | Pavement Improvement | 2010-06-04 | 2010-06-28 |  | 2010-12-06 | 1103642 | 1.000
1551 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | 5951130 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Santa Barbara. The project is described as: Streetscape repair and installation of circulation improvement | Transportation Enhancements | 2010-04-16 | 2010-06-07 |  | 2010-08-27 | 300000 | 1.000
1552 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | 5951131 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Santa Barbara. The project is described as: Streetscape repair and installation of circulation improvement | Transportation Enhancements | 2010-02-19 | 2010-03-15 |  | 2010-07-19 | 1330000 | 6.000
1553 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | Multiple | 5951132 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Barbara. The project is described as: Road Rehabilitation/surface treatment on various roads | Pavement Improvement | 2009-12-08 | 2010-01-04 |  | 2010-03-30 | 615938 | 1.200
1554 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | Multiple | 5952134 | This is a Safety project by a local agency in the County of Ventura. The project is described as: Add new through right-turn lane in both directions on Rose; add new left-turn lane on Rose SB; length | Pavement Widening | 2009-07-20 | 2009-07-21 |  | 2010-02-04 | 210000 | 0.130
1555 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5952135 | This is a Bridge Rehabilitation, No Added Capacity project by a local agency in the County of Ventura. The project is described as: Bridge Deck Rehab. Various Locations | Pavement Improvement | 2009-07-29 | 2009-08-03 |  | 2009-09-17 | 487273.54 | 0.240
1556 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5952138 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Ventura. The project is described as: High Priority on system roads, various locations | Pavement Improvement | 2009-07-10 | 2009-07-10 |  | 2009-10-08 | 1658662 | 4.980
1557 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5952139 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Ventura. The project is described as: On system roads - Phase A various locations | Pavement Improvement | 2009-08-13 | 2009-08-17 |  | 2010-06-14 | 2335171 | 10.340
1558 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5952143 | This is a Landscaping and Other Scenic Beautification project by a local agency in the County of Ventura. The project is described as: Pavement Rehabilitation of Katherine Road | Pavement Improvement | 2010-02-23 | 2010-03-09 |  | 2010-04-12 | 280000 | 1.060
1559 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5952144 | TIERRA REJADA RD, DEL NORTE RD, AND HARBOR BLVD, PAVEMENT REHABILITATION - STREET OVERLAY | Pavement Improvement | 2010-10-07 | 2010-10-21 |  | 2011-03-18 | 568476
1560 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953595 | This is a Traffic Management Engineering project by a local agency in the County of Los Angeles. The project is described as: TRAFFIC SIGNAL UPGRADES AT WHITTIER BOULEVARD ET. AL. | Safety/Traffic Management | 2009-10-06 | 2009-10-13 |  | 2009-12-31 | 206821 | 1.000
1561 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953596 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: COLIMA RD, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 2010-04-12 | 2010-04-19 |  | 2010-11-29 | 2945874 | 7.360
1562 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 25 | 5953597 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: ANGELES FOREST HIGHWAY, ET AL. FOR LOS ANGELES COUNTY FAS FUNDS | Pavement Improvement | 2010-04-15 | 2010-06-14 |  | 2010-10-15 | 2655815 | 8.010
1563 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5953600 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: MULHOLLAND HIGHWAY, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 2009-11-09 | 2010-04-01 |  | 2011-04-20 | 3291800 | 22.500
1564 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5953603 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: WASHINGTON BL, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 2009-09-18 | 2009-10-30 |  | 2009-12-04 | 343157 | 0.740
1565 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953604 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: GRAVES AV, ET AL. - ROADWAY RESURFACING PROJECT | Pavement Improvement | 2009-10-29 | 2010-01-25 |  | 2010-03-19 | 545166.59 | 0.850
1566 | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LANCASTER | 25 | 5953605 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: AVENUE G, ET AL; FOR LOS ANGELES COUNTY FAS FUNDS (PRIORITY #2 F | Pavement Improvement | 2010-04-15 | 2010-06-15 |  | 2010-10-20 | 4694810 | 18.200
1567 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953610 | This is a Safety project by a local agency in the County of Los Angeles. The project is described as: REIS ET AL- BRIDGE BARRIER RAIL REPLACEMENT PROJECT | Bridge Improvement | 2009-11-09 | 2010-01-04 |  | 2010-04-13 | 229477 | 1.000
1568 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 25 | 5953612 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: AVENUE N, ET AL, ROADWAY RESURFACING PROJECT FOR LOS ANGELES COUNTY FAS FUNDS (PRIO | Pavement Improvement | 2010-04-15 | 2010-05-28 |  | 2010-10-07 | 3825347 | 11.970
1569 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 22 | 5953614 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: GORMAN POST RD, ET AL ROADWAY RESURFACING PROJECT | Pavement Improvement | 2010-04-15 | 2010-06-07 |  | 2010-10-27 | 2755729 | 7.330
1570 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5953617 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: FIRESTONE BL, ET AL ROADWAY RESURFACING | Pavement Improvement | 2009-11-18 | 2010-02-01 |  | 2010-04-07 | 1661054 | 2.630
1571 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5953618 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: 120TH ST, ET AL; ROADWAY RESURFACING PROJECT | Pavement Improvement | 2009-11-05 | 2009-11-30 |  | 2009-12-24 | 179041 | 0.270
1572 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5953619 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: EL SEGUNDO BLVD ET AL. - ROADWAY RESURFACING | Pavement Improvement | 2009-11-05 | 2010-02-01 |  | 2010-03-30 | 741958 | 1.420
1573 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5953620 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: CRENSHAW BL, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 2009-11-05 | 2010-02-24 |  | 2010-03-26 | 726800 | 1.370
1574 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953624 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Los Angeles. The project is described as: Los Angeles River Bike Trail Et Al. (TEA Priority No. 1) | Transportation Enhancements | 2010-02-18 | 2010-05-04 |  | 2010-08-25 | 846465 | 1.000
1575 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953625 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: EMERALD NECKLACE REHABILITATION | Transportation Enhancements | 2010-01-04 | 2010-03-29 |  | 2010-06-18 | 2079200 | 34.620
1576 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953626 | This is a Traffic Management Engineering project by a local agency in the County of Los Angeles. The project is described as: TRAFFIC SIGNAL LED INDICATION AND MASS ARM STREET NAME SIGN UPGRADE - PHA | Other | 2009-10-29 | 2010-07-20 |  | 2011-03-02 | 2815738 | 1.000
1577 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953627 | This is a Traffic Management Engineering project by a local agency in the County of Los Angeles. The project is described as: TRAFFIC SIGNAL LED INDICATION AND MASS ARM STREET NAME SIGN UPGRADE - PHA | Other | 2009-10-29 | 2010-02-16 |  | 2010-12-08 | 2861283 | 1.000
1578 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953631 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: Rosemead Bl-Foothill Bl/566 S/o Ardendale Av (Temple City Bounda | Pavement Improvement | 2009-10-13 | 2010-01-11 |  |  | 8528700 | 2.100
1579 | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | 5954115 | This is a Pavement Resurfacing project by a local agency in the County of San Bernardino. The project is described as: Overlay Amboy Road from 9.35 miles south of National Trails Highway north to Nat | Pavement Improvement | 2010-07-08 | 2010-07-19 |  | 2010-07-30 | 1235552 | 9.400
1580 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | 5955068 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Orange. The project is described as: Pavement Rehabilitation of Newport Avenue - Wass St to Hyde Pk Dr | Pavement Improvement | 2010-05-20 | 2010-06-21 |  | 2010-09-29 | 1837401 | 1.860
1581 | Underway | C250,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | INDIA-COACHELLA | 45 | 5956179 | This is a Bridge Rehabilitation, Added Capacity project by a local agency in the County of Riverside. The project is described as: Reconstruct ramps and widen overcrossing | Pavement Widening | 2010-02-26 | 2010-03-01 |  |  | 10415000 | 0.800
1582 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | SAN BERNARDINO-RIVERSIDE | 44 | 5956187 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Riverside. The project is described as: Ramp modifications | New Construction | 2010-02-19 | 2010-02-22 |  |  | 3915396 | 0.800
1583 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5958064 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Imperial. The project is described as: Baughman Road Reconstruction 0.3 mile of County Road | Pavement Improvement | 2010-08-04 | 2010-09-07 |  | 2011-05-03 | 552000 | 0.640
1584 | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5958065 | This is a Pavement Resurfacing project by a local agency in the County of Imperial. The project is described as: Near Imperial - Worthington Road. Intersection at McConnel Rd. New left turn lane at | Other | 2010-08-10 | 2010-09-02 |  | 2011-08-16 | 157000 | 0.460
1585 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5958066 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Imperial. The project is described as: Resurfacing Drew Road from Ross Road to Evan Hewes Highway in Imper | Pavement Improvement | 2010-06-22 | 2010-07-06 |  | 2011-03-01 | 276822 | 0.400
1586 | Underway | C220,C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | STATEWIDE | 43 | 6053080 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of San Bernardino. The project is described as: HOV and lane addition to relieve traffic congestion | Safety/Traffic Management | 2009-10-01 | 2009-10-01 |  |  | 128585744 | 2.500
1587 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | SAN BERNARDINO-RIVERSIDE | 44 | 6054063 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Perris. The project is described as: Replace/widen OC, realign/widen ramps, improve circulation | Pavement Widening | 2009-11-12 | 2010-07-19 |  |  | 16667604 | 1.500
1588 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | 53 | 6066067 | This is a Transit project by a local agency in the City of San Diego. The project is described as: Pedestrian/disabled user facility improvements | Transportation Enhancements | 2010-01-25 | 2010-03-05 |  | 2011-11-19 | 4002427 | 0.000
1589 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | 6127041 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Amador. The project is described as: Transit Center Landscaping, Pedestrian and Supportive Features | Transportation Enhancements | 2010-11-01 | 2010-11-01 |  | 2010-12-31 | 49927 | 0.200
1590 | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | Multiple | 6149062 | This is a Traffic Management Engineering project by a local agency in the County of Santa Cruz. The project is described as: Motorist aide tow trucks to remove incidents. | Safety/Traffic Management | 2009-07-13 | 2009-07-13 |  | 2011-06-30 | 179999.9 | 7.030
1591 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 6264042 | This is a Traffic Management Engineering project by a local agency in the City of Milpitas. The project is described as: In Milpitas: implement roadway pricing on the carpool lane to carpool lane dir | Other | 2009-09-21 | 2009-09-21 |  |  | 3500000 | 4.170
1592 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | Multiple | 6264044 | This is a Traffic Management Engineering project by a local agency in the County of Santa Clara. The project is described as: The SR 85 Express Lanes project would convert the existing continuous car | Other | 2009-12-04 | 2010-03-11 |  |  | 3300000 | 24.060
1593 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 6273056 | This is a Traffic Management Engineering project by a local agency in the County of Alameda. The project is described as: Convert HOV Lane to HOT Lane | Other | 2010-05-03 | 2010-05-03 |  |  | 7500000 | 11.300
1594 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | Multiple | 6328029 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of San Francisco. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-03-18 | 2010-03-22 |  |  | 243760 | 1.000
1595 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 6328030 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of San Francisco. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-02-22 | 2010-03-12 |  | 2010-09-08 | 296197 | 1.000
1596 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 6349005 | This is a Rail/Highway Crossing project by a local agency in the City of Stockton. The project is described as: Replace storage yard railroad tracks | Other | 2010-06-09 | 2010-06-21 |  | 2010-12-10 | 1000000 | 0.000
1597 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | 50 | 8051608 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Chula Vista, from north of H Street to north of Route 54; als | Pavement Improvement | 2009-07-24 | 2009-10-05 |  | 2011-05-18 | 8525838 | 0.900
1598 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | Multiple | 8051610 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: From Carroll Canyon Road to Interstate 5 - On I-805, constructio | Pavement Widening | 2011-01-29 | 2011-03-15 |  |  | 51816680 | 2.400
1599 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 8801058 | This is a Bridge Rehabilitation, No Added Capacity project by the California Department of Transportation. The project is described as: In Oakland, at Fruitvale Avenue Bridge #33-0041. | Pavement Improvement | 2009-06-25 | 2009-07-20 |  | 2009-12-08 | 8327479.13 | 0.300
1601 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | 51 | A905019 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: From I-805 to Otay Mesa Port of Entry | Pavement Widening | 2009-05-08 | 2009-07-01 |  |  | 73930886 | 3.400
1602 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA |  | 06 | P001540 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Sonoma County near Fort Ross, from 2.5 miles south of Fort Ross Road to Timber C | Pavement Improvement | 2009-09-10 | 2009-09-11 |  | 2009-11-12 | 430451.08 | 7.900
1603 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | P001541 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in and near Laguna Beach, from Dana Point/Laguna Beach City limits | Pavement Improvement | 2009-06-12 | 2009-09-09 |  | 2010-05-04 | 2309355 | 9.500
1604 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | P001545 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Santa Barbara County near Lompoc on Route 1 from the intersection of Harris Gra | Pavement Improvement | 2010-06-01 | 2010-06-16 |  | 2010-12-15 | 1834322 | 25.140
1605 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | P004133 | This is a Safety project by the California Department of Transportation. The project is described as: West of Stockton, from east of Middle River to Trapper Road. Realign curve. | Safety/Traffic Management | 2009-09-21 | 2010-04-15 |  |  | 9512058 | 2.800
1606 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALPINE |  | 03 | P004135 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: Near Markleeville, from west of Raymond Meadow Creek Bridge to Junction Route 89. | Pavement Improvement | 2010-08-16 | 2010-08-23 |  | 2010-11-10 | 1143440 | 14.600
1607 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | P014065 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Kern County near Mojave, from South Junction State Route 58 to 5 miles north of | Pavement Improvement | 2009-06-28 | 2009-07-02 |  | 2009-11-03 | 5129627 | 24.500
1608 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P018037 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County, from 0.1 mile west of Route 18/330 Separation to Lakeview | Pavement Improvement | 2009-06-25 | 2009-07-24 |  | 2010-04-19 | 1360611 | 7.500
1609 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P018038 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County near Big Bear City, from Snubbing Post Grade Road to 0.6 m | Pavement Improvement | 2009-06-04 | 2009-06-19 |  | 2009-08-24 | 859022 | 10.000
1610 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P018039 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Lucerne Valley, at Cushenbury Creek Bridge #54-394. | Pavement Improvement | 2009-10-12 | 2009-12-01 |  | 2010-11-04 | 3998627 | 0.700
1611 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | P020150 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In Williams, from 0.3 mile east to 0.6 mile west of Route 5. | Pavement Improvement | 2009-09-02 | 2009-10-06 |  | 2011-10-07 | 7088950 | 0.900
1612 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | P020151 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Yuba County near Marysville, from 0.2 miles west of Spring Valley Road to 0.1 mi | Pavement Improvement | 2009-07-22 | 2009-08-13 |  | 2009-10-21 | 1227430 | 3.200
1613 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA, CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | Multiple | P024030 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: Construct a 2-lane tunnel | Pavement Improvement | 2009-11-20 | 2010-01-13 |  |  | 175796000 | 2.200
1614 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | P024031 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Realignment of WB Rte 24 to NB Rte 13 | Pavement Improvement | 2010-01-20 | 2010-01-29 |  | 2011-04-20 | 3161086 | 0.100
1615 | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | P024032 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Widening and signalization at Kay Street | Pavement Improvement | 2010-01-27 | 2010-02-09 |  | 2010-07-19 | 483921 | 0.100
1616 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | P029105 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Napa County near Calistoga, from 0.2 miles north of Silverado Trail to Lake Coun | Pavement Improvement | 2009-07-21 | 2009-08-19 |  | 2009-10-23 | 639556.44 | 10.500
1617 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | P033068 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Merced County in and near Dos Palos, from Fresno County Line to State Route 152; | Pavement Improvement | 2009-06-25 | 2009-07-10 |  | 2009-09-02 | 1182595 | 19.900
1618 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | P034004 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Ventura County in and near Camarillo, from Daily Drive to State Route 118. | Pavement Improvement | 2009-06-26 | 2009-07-12 |  | 2009-11-24 | 1377690 | 4.000
1619 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLUMAS |  | 04 | P036086 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Plumas County about 6 miles east of Chester, from 0.8 mile west to 1.2 miles eas | Pavement Improvement | 2009-06-12 | 2009-08-15 |  | 2009-10-06 | 1739616 | 1.700
1620 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | P039021 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In La Habra, from Route 90 to Los Angeles County Line; also on R | Pavement Improvement | 2009-07-17 | 2009-09-21 |  | 2010-11-05 | 5019582.54 | 4.000
1621 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | P041110 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In Fresno - At McKinley Avenue and Shields Avenue | Pavement Improvement | 2009-08-11 | 2009-08-24 |  | 2011-06-23 | 2954313 | 1.400
1622 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | P041115 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: In the city of Fresno, on Route 41 at and near Friant Road. | Transportation Enhancements | 2010-08-19 | 2010-09-02 |  | 2011-08-01 | 1034370 | 1.000
1623 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | P044045 | This is a Safety project by the California Department of Transportation. The project is described as: Near Viola from 2.5 to 1.1 miles west of the Lassen Park entrance. Realign curve, widen shoulder | Safety/Traffic Management | 2010-02-03 | 2010-05-03 |  | 2010-10-22 | 5726722 | 1.400
1624 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | P046042 | This is a Safety project by the California Department of Transportation. The project is described as: Near Shandon - at the Shandon Rest Area - rehabilitate Safety Roadside Rest Area | Safety/Traffic Management | 2009-08-12 | 2009-10-06 |  | 2011-01-31 | 4629688 | 0.000
1625 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | P049143 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near El Dorado, from Ore Court Road to China Hill Road. | Pavement Improvement | 2009-06-26 | 2009-07-07 |  | 2010-10-25 | 6868710 | 1.000
1626 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SIERRA |  | 04 | P049144 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Sierra County on State Route 49 near Sierraville and Loyalton, from South Juncti | Pavement Improvement | 2009-07-09 | 2009-07-27 |  | 2009-09-23 | 901956 | 17.000
1627 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TUOLUMNE |  | 19 | P049145 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Tuolumne County in and near Sonora, from 0.2 mile south of Pesce Way to Calavera | Pavement Improvement | 2009-07-02 | 2009-07-20 |  | 2010-01-14 | 1274809 | 9.100
1628 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | P049148 | IN NEVADA COUNTY NEAR GRASS VALLEY FROM 0.6 KM NORTH OF ALTA SIERRA DRIVE TO 0.9, WIDEN ROADWAY WITH HOT MIX ASPHALT | Pavement Widening | 2011-05-12 | 2011-05-23 |  |  | 2000000
1629 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | P050125 | AT ECHO SUMMIT FROM ECHO SUMMIT ROAD TO 1.1 MILES WEST OF JOHNSON PASS ROAD, ROCK RETAINING GUARD WALL & STORM WATER MITIG.(TC) | Safety/Traffic Management | 2011-03-29 | 2011-04-26 |  | 2011-11-03 | 2079775
1630 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | Multiple | P057053 | This is a Safety project by the California Department of Transportation. The project is described as: In Orange, Anaheim and Fullerton, from West Orangewood Avenue to the Los Angeles County line at v | Pavement Improvement | 2009-08-09 | 2010-02-01 |  | 2011-01-26 | 2953660.5 | 11.000
1631 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P062026 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County, from 4.9 miles west to 0.9 miles west of Rio Mesa Drive. | Pavement Improvement | 2009-06-19 | 2009-08-14 |  | 2009-10-21 | 871963 | 4.000
1632 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLUMAS |  | 04 | P070099 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Quincy (9 miles west), from 0.2 mile west to 0.2 mile east of | Bridge Replacement | 2010-06-24 | 2010-08-23 |  |  | 18613911 | 0.400
1633 | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | SAN BERNARDINO-RIVERSIDE | 42 | P071058 | ON ROUTE 71 IN SAN BERNARDINO AND RIVERSIDE COUNTIES NEAR CHINO HILLS ***, LANDSCAPING (TREE PLANTING) (TC) | Transportation Enhancements | 2011-02-28 | 2011-04-11 |  |  | 661664
1634 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | P073086 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in Laguna Niguel, Laguna Hills, Aliso Viejo, Laguna Beach and Irvi | Pavement Improvement | 2009-08-05 | 2009-08-19 |  | 2011-01-13 | 8790626 | 12.500
1635 | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | 49 | P076024 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: CONSTRUCT 4-LANE HIGHWAY | Pavement Widening | 2010-01-21 | 2010-02-03 |  |  | 75612901 | 5.800
1636 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE |  | 44 | P078108 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Palo Verde, on 32nd Avenue west of South Randalls Avenue Brid | Pavement Improvement | 2009-08-04 | 2009-09-17 |  | 2010-10-01 | 1545437 | 0.200
1637 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR | STOCKTON | 03 | P088052 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Amador County in and near Barton, from 0.1 mile west of Wagon Wheel Drive to 0.1 | Pavement Improvement | 2009-06-25 | 2009-07-06 |  | 2009-11-03 | 995691 | 5.700
1638 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | P088053 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Amador County near Plasse, from 2 miles west of Tragedy Springs Road to 0.3 mile | Pavement Improvement | 2009-07-10 | 2009-07-10 |  | 2009-11-03 | 490501 | 6.100
1639 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | P089094 | This is a Mitigation of Water Pollution due to Highway Runoff project by the California Department of Transportation. The project is described as: Near Meyers, from Alpine County Line to Route 50. | Pavement Improvement | 2009-07-01 | 2009-09-01 |  |  | 16425073 | 8.600
1640 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | P090011 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in Brea and Placentia, from Randolph Avenue to 0.1 mile east of Ro | Pavement Improvement | 2009-06-19 | 2009-07-08 |  | 2009-10-14 | 1768825 | 3.000
1641 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE, ORANGE | LOS ANGELES, CA | Multiple | P091127 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Orange County add one lane on eastbound SR-91 from SR-241 to | Pavement Improvement | 2009-09-16 | 2009-11-10 |  | 2011-05-13 | 47677635 | 5.900
1642 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE |  | 45 | P095020 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: Near Blythe, from 0.4 mile north of Wiley Hill Log Cabin to 0 | Pavement Improvement | 2009-06-26 | 2009-07-12 |  | 2010-02-01 | 2639700 | 8.300
1643 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 02 | P099519 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: SR 99 Near Biggs - Rio Bonito to SR 162. | Pavement Improvement | 2009-07-07 | 2009-08-01 |  | 2012-02-29 | 11331484 | 4.600
1644 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | P099520 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Sutter County, SR 99 near East Nicholas, from Sacramento County | Pavement Improvement | 2009-06-12 | 2009-07-06 |  | 2009-12-31 | 12195645 | 8.700
1645 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED | MERCED | 18 | P099521 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: In Merced County, from north of V Street to Black Rascal Bridge #3 | Pavement Improvement | 2009-10-08 | 2010-01-04 |  |  | 29695432 | 1.500
1646 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | P099522 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: Highway planting in Stanislaus County, in and near the City | Transportation Enhancements | 2010-02-15 | 2010-03-10 |  | 2010-07-19 | 755065 | 7.900
1647 | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA |  | 02 | P099525 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: Irrigation system for landscaping | Transportation Enhancements | 2010-07-12 | 2010-07-12 |  | 2011-01-12 | 79710 | 1.000
1648 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | P099529 | IN SUTTER COUNTY NEAR NICOLAUS FROM POWER LINE ROAD TO 0.1 MILE SOUTH OF LAUREL, WIDEN TO FOUR LANES | Pavement Widening | 2010-08-02 | 2010-09-21 |  |  | 19060691
1649 | Underway | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | P099539 | NEAR TIPTON AT THE PHILIP S. RAINE SAFETY ROADSIDE REST AREA, SAFETY ROADSIDE REST AREA RESTORATION (TC) | Pavement Improvement | 2011-04-25 | 2011-05-11 |  |  | 5536672
1650 | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | STATEWIDE | 24 | P118058 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Simi Valley, from Tapo Canyon Road to the Los Angeles county | Pavement Widening | 2009-12-15 | 2010-01-06 |  | 2011-07-22 | 6507000 | 5.500
1651 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | P134035 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Los Angeles County in Burbank, Glendale and Los Angeles, from Bob Hope Drive Und | Pavement Improvement | 2009-08-06 | 2009-09-03 |  | 2010-08-18 | 1448500 | 6.400
1652 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LASSEN |  | 04 | P139019 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Lassen County about 40 miles north of Susanville, from 7.0 miles north of CDF Fi | Pavement Improvement | 2009-07-14 | 2009-07-27 |  | 2009-10-16 | 1555196 | 13.000
1653 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | P145029 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: Near Madera, from Avenue 5 1/2 to Avenue 11 1/2. | Pavement Improvement | 2009-06-20 | 2009-06-20 |  | 2010-06-25 | 10525615 | 6.100
1654 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | P154018 | This is a Bridge Rehabilitation, No Added Capacity project by the California Department of Transportation. The project is described as: Construct physical barricade on Highway 154/Cold Sping Canyon B | Safety/Traffic Management | 2012-01-18 | 2012-02-01 |  |  | 1499999.43 | 0.240
1655 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 23 | P154019 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Santa Barbara County near Santa Barbara on Route 154 from the intersection of S | Pavement Improvement | 2010-06-03 | 2010-06-03 |  | 2011-01-10 | 1949398 | 18.000
1656 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | P165011 | IN MERCED CO NEAR LOS BANOS FROM HENRY MILLER RD TO 0.1 MI SO OF RTE 140, AC OVERAY & WIDEN / REPLACE STRUCTURES (TC) | Pavement Improvement | 2011-07-05 | 2011-08-08 |  |  | 8139263
1657 | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | P180053 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near Centerville, from Temperance Avenue to Academy Avenue (Qual | Pavement Improvement | 2009-09-21 | 2009-11-30 |  | 2011-11-23 | 18369261 | 6.200
1658 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | P190013 | This is a Scenic or Historic Highway Programs project by the California Department of Transportation. The project is described as: In Death Valley National Park, on Route 190 at Father Crowley Point | Transportation Enhancements | 2010-05-13 | 2010-06-02 |  | 2010-08-17 | 447881.08 | 1.000
1659 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | P222001 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Ukiah, at Russian River Bridge #10-80. | Bridge Replacement | 2009-06-29 | 2009-10-15 |  | 2012-01-06 | 7903106 | 0.010
1660 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE |  | 45 | P243002 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Riverside County near Idyllwild, from 1.1 miles north of State Routes 74/243 Sep | Pavement Improvement | 2009-07-15 | 2009-07-29 |  | 2009-10-08 | 1933265 | 12.200
1661 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | TRINITY |  | 02 | P299157 | This is a Facilities for Pedestrians and Bicycles project by the California Department of Transportation. The project is described as: In Trinity County at Weaverville 0.4 mile west of Miner Street | Transportation Enhancements | 2010-04-29 | 2010-06-14 |  | 2010-09-28 | 296458 | 0.800
1662 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MODOC |  | 04 | P395224 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Modoc County near Alturas, from the Lassen/Modoc County Line to Alturas Overhead | Pavement Improvement | 2009-07-17 | 2009-08-13 |  | 2010-12-31 | 2358462 | 20.800
1663 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P395225 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County on US Highway 395 near Kramer Junction, from Federal Priso | Pavement Improvement | 2009-06-26 | 2009-07-10 |  | 2009-10-22 | 1530677 | 6.000
1664 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONO |  | 25 | P395226 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Mono County near Hilton Creek, from 0.1 mile north of Crooked Creek Bridge to 0. | Pavement Improvement | 2009-07-03 | 2009-07-23 |  | 2009-10-23 | 3273458 | 23.500
1665 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | P710014 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Los Angeles from 0.3 mile south of Firestone Blvd to 0.2 mile | Pavement Improvement | 2009-09-22 | 2009-11-16 |  |  | 52219257 | 2.700
1666 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | Q101151 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near Salinas, from Central Avenue to Gould Avenue at various loc | Pavement Improvement | 2009-08-14 | 2009-08-31 |  | 2011-04-06 | 5942549 | 36.900
1667 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | Q101152 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Mateo County in South San Francisco and Brisbane, from Oyster Point Boulevar | Pavement Improvement | 2009-08-14 | 2009-08-19 |  | 2010-12-17 | 3134512 | 3.100
1668 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | Q101153 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In the City and County of San Francisco on Route 101, Doyle | Pavement Improvement | 2010-04-13 | 2010-04-18 |  |  | 83281437 | 1.800
1669 | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | STATEWIDE | 06 | Q101155 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Construct HOV lanes and bike path | Transportation Enhancements | 2007-08-15 | 2007-08-15 |  | 2011-02-03 | 2701200 | 1.860
1670 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | Q101159 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In and near Atascadero, from Cuesta Grade overhead to north of T | Pavement Improvement | 2010-01-26 | 2010-03-22 |  |  | 36476122 | 10.600
1671 | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | Q101164 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Construct operational & safety improvements as follows: Constru | Pavement Improvement | 2010-11-18 | 2010-11-23 |  |  | 4063550 | 3.900
1672 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | Q101165 | This is a Safety project by the California Department of Transportation. The project is described as: On Route 101 near Prundale construct new interchange at San Juan Road | Other | 2010-03-07 | 2010-03-07 |  |  | 10450000 | 1.300
1673 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | Q101169 | This is a Safety project by the California Department of Transportation. The project is described as: In Mendocino County, at various locations from 0.3 mile south of Russian River Bridge to 0.5 mile | Safety/Traffic Management | 2010-07-05 | 2010-08-02 |  | 2011-09-27 | 2737931 | 101.500
1674 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | Q101170 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Near Ukiah, from 0.2 mile north of Robinson Creek Bridge #10-000 | Pavement Improvement | 2010-08-10 | 2010-08-25 |  |  | 14925447 | 12.600
1675 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | Q101182 | LA CNTY FR 0.2 M E/O LAS VIRGENES RD OC TO LA/VEN CNTY LINE, PAVEMENT REHAB, PAVEMENT REHABILITATION (TC) | Pavement Improvement | 2011-02-16 | 2011-03-18 |  | 2011-09-17 | 8123600
1676 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 18 | S033069 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Newman, from Inyo Street to south of Jensen Road; also in Pat | Pavement Improvement | 2009-08-26 | 2010-06-01 |  | 2010-08-13 | 1846054 | 14.000
1677 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA |  | 15 | S035007 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Santa Clara County near Los Gatos, from Black Road to the State Route 35 separat | Pavement Improvement | 2009-07-21 | 2009-08-19 |  | 2009-10-26 | 1120693.48 | 6.420
1678 | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | S168053 | This is a Facilities for Pedestrians and Bicycles project by the California Department of Transportation. The project is described as: Near Bishop, from Red Hill Road to Ed Powers Road. | Transportation Enhancements | 2010-05-27 | 2010-06-01 |  | 2010-09-16 | 828741.65 | 1.600
1679 | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | Multiple | S204004 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: In Bakersfield, at Chester Avenue Bridge #50-183. | Bridge Replacement | 2009-07-03 | 2009-08-24 |  |  | 15032275 | 1.000
1680 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | X019021 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Fresno County on Route 33 near Harris Ranch, from I-5 to 1.7 miles north of Harl | Pavement Improvement | 2009-06-18 | 2009-07-06 |  | 2009-09-02 | 1519610 | 1.000
1681 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA, LOS ANGELES |  | Multiple | X037145 | This is a Safety project by the California Department of Transportation. The project is described as: In Ventura County in and near Oxnard from Wood Road to Mobil Pier Road and in routes 23,33,101,11 | Safety/Traffic Management | 2009-10-15 | 2010-01-01 |  | 2011-06-23 | 1102845 | 1.000
1682 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | X037146 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles County in Santa Monica from Lincoln Blvd to Palasades pedestrian overcrossing and | Safety/Traffic Management | 2009-10-15 | 2009-11-09 |  | 2010-12-03 | 1245637 | 1.000
1683 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | X037147 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles County from Santa Fe Springs to Los Angeles from Valley-View Avenue to Soto Street | Other | 2009-10-20 | 2009-12-14 |  | 2011-06-03 | 1351521 | 1.000
1684 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | X037148 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles and Long Beach, on various routes. | Safety/Traffic Management | 2009-09-01 | 2009-10-17 |  | 2010-07-28 | 1043832 | 1.000
1685 | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | X053022 | This is a Safety project by the California Department of Transportation. The project is described as: Pacific Grove to Castroville, south of Route 1 to Tembladero Slough; also on Route 68 east of Fai | Safety/Traffic Management | 2009-06-29 | 2009-09-01 |  | 2010-07-08 | 1872022 | 17.100
1686 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | STATEWIDE | Multiple | X059051 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Provide direct HOV Connection between SR-22 and I-405 | Pavement Widening | 2010-06-25 | 2010-09-01 |  |  | 49634873 | 2.100
1687 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 002A003 | Resurfaces 2.4 miles of SH 2 from Vasquez to Quebec, adds curb ramps and safety improvements | Pavement Improvement | 2010-04-23 | 2010-06-14 | 2010-09-22 | 2010-12-30 | 1619093 | 2.485
1688 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WASHINGTON |  | 04 | 0061080 | Resurfaces over 9 miles of SH 6 in Washington and Logan Counties | Pavement Improvement | 2010-03-16 | 2010-07-06 | 2010-10-11 | 2011-04-25 | 3467546 | 9.480
1689 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | MESA |  | 03 | 0063031 | Enhancement Project: constructs bike and pedestrian trail in Fruita along US 6 | Transportation Enhancements | 2009-09-21 | 2009-09-21 | 2010-05-17 | 2010-06-08 | 433399 | 0.630
1690 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | EAGLE |  | 02 | 006A043 | Enhancement Project: constructs bike and pedestrian trail to connect Town of Minutrn to Dowd Junction ECO trail | Transportation Enhancements | 2009-09-21 | 2009-09-22 | 2009-11-04 | 2009-11-12 | 282396 | 0.420
1691 | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | 006A047 | Project to acquire ROW and conduct relocations at US6 and WADSWORTH interchange from 4 to 14TH AVE in preparation for re-construction project to add lanes, improve safety | Other | 2010-08-09 | 2010-08-09 | 2012-03-10 |  | 4946658 | 2.670
1692 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | SUMMIT |  | 02 | 0091032 | Widens SH 9 to two lanes in each direction and constructs a new pedestrian bridge and a retaining wall. The project will also relocate a bike path and improve drainage north of Breckenridge in Summit | Pavement Widening | 2009-06-04 | 2009-06-04 | 2010-01-13 | 2010-12-23 | 8193464 | 1.550
1693 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | RIO BLANCO |  | 03 | 0131055 | Reconstructs five miles of SH 13 in asphalt, adds eight-foot shoulders and climbing and passing lanes at Rio Blanco Hill in Rio Blanco County. The improvements will enhance recreational bicycling in t | Pavement Widening | 2009-07-17 | 2009-07-17 | 2010-10-01 | 2010-11-12 | 10359717 | 5.290
1694 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | JACKSON |  | 03 | 0141020 | Asphalt resurfacing of SH 14 east and est of Cameron Pass in Larimer and Jackson counties. | Pavement Improvement | 2009-06-04 | 2009-06-09 | 2009-11-18 | 2010-06-25 | 5177001 | 13.390
1695 | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | JACKSON |  | 03 | 0141021 | Resurfaces and repairs shoulder on 23 miles of SH 14 east of Muddy Pass. | Pavement Improvement | 2010-04-06 | 2010-07-12 | 2010-10-31 | 2010-10-19 | 6337976 | 23.000
1696 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | CHAFFEE |  | 05 | 0242045 | Resurfaces 12.5 miles of US 24/US 285, north of Johnson Village in Chaffee County, in asphalt. | Pavement Improvement | 2009-05-19 | 2009-08-07 | 2009-11-27 | 2009-11-05 | 3714986 | 12.680
1697 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | EL PASO |  | 05 | 0243076 | Replaces a structurally deficient bridge over Falcon Creek in Falcon in El Paso County and improves drainage. | Bridge Replacement | 2009-09-16 | 2009-09-16 | 2010-08-31 | 2010-09-29 | 3378144 | 0.800
1698 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ELBERT |  | 06 | 0243079 | Resurfaces 11 miles of SH 24 west of Limon. | Safety/Traffic Management | 2010-02-26 | 2010-05-03 | 2010-08-13 | 2010-08-27 | 5496017 | 11.030
1699 | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | LAS ANIMAS | PUEBLO | 03 | 0251335 | Constructs the Purgatoire River Pedestrian Trail, adds street lights, parking lot paving, curb and gutter, drainage inlets, landscaping and sidewalk along I-25 in Trinidad. | Pavement Improvement | 2009-06-16 | 2009-05-29 | 2011-07-03 |  | 6572326 | 3.000
1700 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DENVER | DENVER, CO | 01 | 0252402 | Resurfaces approximately three miles of I-25 in Denver from 6th Avenue to 23rd Avenue, in asphalt. | Pavement Improvement | 2009-04-28 | 2009-06-14 | 2009-11-04 | 2010-06-15 | 3421919 | 2.000
1701 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | 0253206 | Improves five miles of roadway surface on I-25 from the Crossroads Interchange at Loveland to SH 392, the Windsor Interchange. | Pavement Improvement | 2009-07-01 | 2009-07-05 | 2009-10-19 | 2010-05-26 | 4594338 | 4.012
1702 | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | 0253207 | Constructs roundabouts on Crossroads at the I-25 and Crossroads, Loveland interchange to improve mobility and safety. | Safety/Traffic Management | 2009-08-31 | 2009-08-31 | 2010-08-31 |  | 3000000 | 0.950
1703 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WELD |  | 04 | 0342050 | Installs a traffic signal at the intersection of US 34 and Weld County Road 49, west of Kersey. | Safety/Traffic Management | 2009-08-03 | 2009-08-08 | 2009-10-03 | 2010-03-23 | 381589 | 0.200
1704 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WASHINGTON |  | 04 | 0343030 | Resurfaces 15 miles of SH 34 from Brush to Akron with chipseal. | Pavement Improvement | 2010-02-03 | 2010-06-30 | 2010-07-20 | 2010-07-16 | 1625089 | 15.200
1705 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | LARIMER |  | 04 | 0361089 | Chip seals 22 miles of US 36 between Lyons and Estes Park to improve the roadway surface condition. | Pavement Improvement | 2009-06-22 | 2009-07-20 | 2009-08-24 | 2009-09-30 | 1396055 | 21.770
1706 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | 0361090 | Installs a new traffic signal at the intersection of US 36 and Broadway in Boulder. | Safety/Traffic Management | 2009-07-02 | 2009-08-03 | 2009-10-13 | 2010-04-01 | 326771 | 0.270
1707 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LINCOLN | DENVER, CO | 04 | 0405033 | Enhancement Project: Rehabilitate railroad roundhouse in Hugo in Lincoln County, to become a railroad museum. | Transportation Enhancements | 2009-11-18 | 2010-01-26 | 2010-09-10 | 2010-09-03 | 511287 | 0.240
1708 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | PUEBLO | PUEBLO | 03 | 0504060 | Resurfaces US 50 east of Pueblo and makes safety improvements | Pavement Improvement | 2010-03-19 | 2010-04-05 | 2010-09-27 | 2011-02-15 | 5070313 | 11.400
1709 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | CHAFFEE |  | 05 | 050A009 | Enhancement Project: constructs curb, gutter, sidewalk, and ADA ramps in Salida on US 50 | Transportation Enhancements | 2009-09-03 | 2009-09-18 | 2009-12-27 | 2009-12-15 | 491470 | 0.766
1710 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | 052A031 | Replaces the bridge over Boulder Creek on SH 52 at the Boulder - Weld County Line. | Bridge Replacement | 2009-07-16 | 2009-08-31 | 2011-06-30 | 2008-03-07 | 4192992 | 0.511
1711 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WELD |  | 04 | 060A013 | Installs a new traffic signal at the intersection of the I-25 exit ramps and frontage roads with SH 60 (Johnstown Exit).. | Safety/Traffic Management | 2009-07-09 | 2009-08-03 | 2009-09-28 | 2009-10-16 | 409853 | 0.170
1712 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | SAN MIGUEL |  | 03 | 062A013 | Resurface a total of 21.5 miles of SH 62, Dallas Divide in in Ouray and San Migel counties between Placerville and Ridgway, in asphalt and repair embankments. Project includes some work on US 550 at R | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-10-02 | 2009-10-12 | 4000000 | 24.900
1713 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | MESA | GRAND JUNCTION | 03 | 0701197 | Improves safety by widening the acceleration and deceleration lanes at this interchange on I-70 at the Palisade exit in Mesa County. The improvements will upgrade the interchange to current design sta | Pavement Improvement | 2009-06-22 | 2009-09-21 | 2009-12-02 | 2009-12-02 | 1400712 | 1.000
1714 | Completed | C200 | Highway Infrastructure Investment Grant | COLORADO | SUMMIT |  | 02 | 0702283 | Resurfaces 14 miles of I-70 from milepost 190 to 204 as well as the right lane of eastbound I-70 between milepost 180 and 190. Numerous bridges along the I-70 corridor will also be rehabilitated by r | Pavement Improvement | 2009-05-05 | 2009-05-05 | 2009-11-08 | 2010-07-29 | 8000000 | 24.000
1715 | Completed | C200 | Highway Infrastructure Investment Grant | COLORADO | EAGLE |  | 02 | 0702297 | This safety improvement project will construct four roundabouts at the interchange of I-70 in Edwards in Eagle County. | Safety/Traffic Management | 2010-02-26 | 2010-03-22 | 2010-11-19 | 2011-06-06 | 9012955 | 0.770
1716 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | 0703350 | Repairs and replaces concrete slabs on I-70 between Kipling Street and Wadsworth Blvd in Wheatridge. | Pavement Improvement | 2009-04-21 | 2009-05-19 | 2009-08-22 | 2009-10-08 | 1732584 | 2.070
1717 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | EAGLE | DENVER, CO | 02 | 0703353 | Installs various truck parking management components (electronic signs, closed-circuit cameras, power and communications systems), to provide notification during inclement weather. along I-70 between | Safety/Traffic Management | 2009-06-22 | 2009-06-22 | 2009-10-29 | 2010-10-08 | 2199037 | 54.440
1718 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 0704217 | Installs cable guardrailin the median of I-70 between Pena Blvd and Tower Road in Aurora to prevent crossover accidents. | Safety/Traffic Management | 2009-06-22 | 2009-07-13 | 2009-09-07 | 2009-09-30 | 294430 | 2.180
1719 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | KIT CARSON |  | 04 | 0705078 | Concrete slab replacement of various sections of I70 from Agate, CO to KS State Line | Pavement Improvement | 2010-11-02 | 2010-11-08 | 2011-07-31 | 2011-06-10 | 1815122 | 110.088
1720 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 0761200 | Construct two roundabouts on 96th Avenue at the ramps to I-76 in Commerce City. | Safety/Traffic Management | 2009-05-21 | 2009-06-22 | 2009-12-18 | 2010-06-10 | 2222733 | 0.040
1721 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 0761201 | Replaces two bridges on I-76 over the Union Pacific Railroad and SH 224 in Commerce City. | Bridge Replacement | 2009-06-02 | 2009-07-06 | 2011-02-03 | 2010-12-20 | 9843607 | 1.043
1722 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | SEDGWICK |  | 04 | 0762045 | Reconstructs 11 miles of eastbound I-76 in concrete between Sedgwick and the Nebraska state line. | Pavement Improvement | 2009-07-10 | 2009-07-13 | 2010-09-22 | 2010-09-22 | 15570336 | 19.490
1723 | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | GARFIELD |  | 03 | 0821087 | This safety improvement project at the I-70 interchange with US 6 and SH 82 in Glenwood Springs will upgrade traffic signals and improve ramp width and length to benefit both pedestrians and vehicle | Other | 2009-08-03 | 2009-08-17 | 2009-11-24 | 2009-11-20 | 2500000 | 3.020
1724 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DOUGLAS | DENVER, CO | 06 | 0852095 | Widens one mile of US 85 to two lanes in each directions with shoulders and a raised median with controlled access on US 85 between Titan Road and Cook Ranch Road in Douglas County. | Pavement Widening | 2009-08-17 | 2009-09-28 | 2010-09-23 | 2010-10-15 | 5400000 | 7.480
1725 | Underway | C240,C230 | Highway Infrastructure Investment Grant | COLORADO | DOUGLAS | DENVER, CO | 06 | 0852103 | This project is reconstructing the interchange of US85 (Sante Fe) and C470 to include a new southbound US 85 to eastbound C470 flyover ramp. | New Bridge Construction | 2010-05-20 | 2010-06-07 | 2011-12-09 |  | 5864928 | 1.900
1726 | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | WELD |  | 04 | 0853072 | Conducts resurfacing on 8.5 miles of US 85 from mile 301 to mile 309.5 and replaces two bridges. | Bridge Replacement | 2010-07-30 | 2010-08-09 | 2011-08-31 |  | 4986402 | 8.542
1727 | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 0853079 | Projects installs CONDUIT, FIBER, CCTV along SH 85 from I-76 to SH 7, | Safety/Traffic Management | 2010-10-22 | 2010-11-01 | 2011-09-30 |  | 1150000 | 11.112
1728 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ARAPAHOE | DENVER, CO | 06 | 088A026 | Replaces the asphalt surface on SH 88, Belleview Avenue, between Santa Fe Drive and Federal Blvd in Littleton. | Pavement Improvement | 2009-04-28 | 2009-05-18 | 2009-06-29 | 2009-07-17 | 431702 | 0.900
1729 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DELTA |  | 03 | 092A022 | Reconstructs five miles of SH 92 in asphalt and adds passing lanes and shoulders to improve recreational bicycling between Austin and Hotchkiss in Delta County. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2010-10-30 | 2010-10-29 | 8604148 | 4.100
1730 | Underway | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | FREMONT |  | 05 | 1151025 | This project will resurface 20 miles of SH 115 in El Paso and Fremont counties. | Pavement Improvement | 2010-10-05 | 2010-10-12 |  |  | 2015519 | 20.234
1731 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | GUNNISON |  | 03 | 135A025 | Enhancement Project: constructs bike and pedestrian trail and bridge along SH 135 north of Gunnison | Transportation Enhancements | 2010-03-16 | 2010-04-07 | 2010-09-05 | 2011-02-28 | 374515 | 0.170
1732 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | RIO GRANDE |  | 03 | 1602122 | Resurfaces three miles of US 160 west of Del Norte in Rio Grande County, in asphalt. | Pavement Improvement | 2009-06-16 | 2009-10-05 | 2009-11-09 | 2009-11-03 | 1468886 | 3.320
1733 | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | LA PLATA |  | 03 | 1602123 | Relocates the intersection of La Plata County Roads 222 &223 with US 160, east of Durango, and adds auxiliary lanes to improve sight distance. | New Construction | 2010-02-26 | 2010-02-26 | 2011-05-26 | 2011-09-09 | 4300000 | 1.774
1734 | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | RIO GRANDE |  | 03 | 1602125 | Resurfaces with asphalt a second phase of US 160 west to Del Norte in Rio Grande County and constructs ADA ramps. | Pavement Improvement | 2010-03-25 | 2010-04-06 | 2010-07-16 | 2010-06-28 | 7441823 | 14.000
1735 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ALAMOSA |  | 03 | 1603027 | Resurfaces six miles of US 160 east of Alamosa in asphalt. | Pavement Improvement | 2009-06-12 | 2009-07-14 | 2009-09-08 | 2009-09-03 | 2736807 | 6.755
1736 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | LA PLATA |  | 03 | 160A010 | Constructs a new eastbound on-ramp as part of an already scheduled project that will widen US 160 to four lanes and relocate a traffic signal due to the widening east of Durango. | New Construction | 2009-09-03 | 2009-09-03 | 2010-04-21 | 2010-08-27 | 3619600 | 1.490
1737 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DOUGLAS | DENVER, CO | 06 | 177A006 | Resurface in asphalt, SH 177, University Avenue in Centennial, from C-470 to Arapahoe. | Pavement Improvement | 2009-05-12 | 2009-05-26 | 2009-09-08 | 2009-08-14 | 1559083 | 2.000
1738 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ARAPAHOE | DENVER, CO | 07 | 2254078 | Phase 1 of project to reconstruct the I-225 / Colfax interchange in Aurora to rebuild the southbound ramp from Colfax to I-225 | Pavement Widening | 2009-11-23 | 2009-11-30 | 2010-05-12 | 2010-09-24 | 1077890 | 0.096
1739 | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | ARAPAHOE | DENVER, CO | 07 | 2254079 | Phase 2 of the reconstruction of the I-55 / Colfax interchange in Aurora, to provide access from I-225 to 17th Avenue. | Pavement Widening | 2010-03-26 | 2010-03-26 | 2012-02-09 |  | 11300000 | 0.700
1740 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | 257A007 | Installs a new traffic signal at the intersection fo SH 257 and Garden drive in Windsor. | Safety/Traffic Management | 2009-07-16 | 2009-08-10 | 2009-10-05 | 2009-12-01 | 244422 | 0.160
1741 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | SAGUACHE |  | 03 | 2852016 | Resurfaces eight miles of US 285, south of Saguache, in asphalt. | Pavement Improvement | 2009-06-12 | 2009-08-27 | 2009-11-12 | 2009-11-06 | 3660211 | 9.480
1742 | Underway | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 06 | 2854117 | Constructs a grade-separated interchange at Elk Creek Road, new frontage roads and a wildlife crossing underpass. When complete, Elk Creek Rd. will run under US 285. THe project is located in Jefferso | Pavement Widening | 2009-08-26 | 2009-08-26 | 2010-12-08 |  | 9000000 | 0.664
1743 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | PARK |  | 05 | 2854120 | Enhancement Project: constructs pedestrian bridge and trail in Fairplay | Transportation Enhancements | 2010-03-11 | 2010-04-26 | 2010-06-30 | 2010-09-16 | 253010 | 2.000
1744 | Underway | C250,C200 | Highway Infrastructure Investment Grant | COLORADO | BACA |  | 04 | 2871032 | This project will reconstruct US 287 in concrete and improve drainage and shoulder embankments south of Springfield in Baca County. | Pavement Improvement | 2009-10-07 | 2009-10-12 | 2010-10-04 |  | 12200277 | 8.300
1745 | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | MESA |  | 03 | 340A015 | Installs two new traffic signals west of the I-70 interchange on SH 240 in Fruitia in Mesa County.and makes intersection safety improvements for pedestrians and vehicles. | Pavement Widening | 2009-09-21 | 2010-03-08 | 2010-05-24 | 2010-05-26 | 1383153 | 0.890
1746 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DOUGLAS | DENVER, CO | 06 | 4701118 | Repairs or replaces concrete slabs on C-470 and resurfaces C-470 in asphalt between Santa Fe Drive and I-25 in Douglas County. Rehabilitates the C-470 bike path between I-70 and I-25 in Jefferson, Ara | Pavement Improvement | 2009-06-16 | 2009-07-09 | 2010-09-04 | 2011-02-07 | 31215789 | 9.243
1747 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | OURAY |  | 03 | 5502064 | Enhancement Project: constructs wildlife fence and ramps to reduce wildlife collisions along US 550 | Transportation Enhancements | 2010-01-25 | 2010-01-25 | 2010-04-30 | 2010-05-18 | 166666 | 8.910
1748 | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | OURAY |  | 03 | 5502069 | Project resurfaces SH 550 from Colona to Chipeta | Pavement Improvement | 2010-11-05 | 2011-05-02 | 2011-07-27 |  | 915691 | 9.070
1749 | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | DENVER | DENVER, CO | 01 | C010101 | Replaces the Alameda bridge over I-25 in Denver with one that is wider to accommodate an additional lane ion I-25 in each direction. | Bridge Replacement | 2010-02-11 | 2010-04-01 | 2012-03-23 |  | 33447164 | 0.550
1750 | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | DENVER | DENVER, CO | 01 | C010103 | Construct a new interchange at I-70 and Central Park Bvd. in Denver. | New Construction | 2010-01-29 | 2010-01-29 | 2011-10-01 |  | 12000000 | 1.500
1751 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | PUEBLO | PUEBLO | 03 | C020033 | Enhancement Project: Landscaping and irrigation installation for the Eastern Gateway Landscape Project located at the intersection of SH 50 B and SH 47 in Pueblo. | Transportation Enhancements | 2010-02-08 | 2010-04-01 | 2010-06-25 | 2010-10-01 | 381424 | 0.000
1752 | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | C030035 | Resurfaces Weld County Road 74 from Weld County Road 13 to SH 357 in asphalt. | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2009-09-18 | 2009-10-09 | 459627 | 0.000
1753 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | C060049 | Enhancement Project: Constructs a bicycle/pedestrian underpass under SH 392 in Windsor. | Transportation Enhancements | 2009-07-28 | 2009-08-12 | 2009-10-09 | 2010-10-20 | 487037 | 0.369
1754 | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | C060050 | Resurfaces Larimer County Road 17 between Berthoud and Fort Collins in asphalt. | Pavement Improvement | 2009-07-28 | 2009-08-03 | 2009-10-19 | 2010-11-30 | 3582424 | 0.000
1755 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | ARAPAHOE | DENVER, CO | 06 | C100028 | Enhancement Project: Construct an extension to the bicycle and pedestrain bridge over I-25 south of Dry Creek Road to extend over Inverness Drive in Arapahoe County. | Transportation Enhancements | 2009-11-18 | 2009-11-18 | 2010-07-21 | 2011-01-27 | 708947 | 0.000
1756 | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | C120018 | Construct an underpass of Pecos Street under the railroad tracks, south of I-76 in Adams County. | Pavement Improvement | 2009-12-16 | 2010-01-19 | 2012-01-10 |  | 4450000 | 0.000
1757 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | PROWERS |  | 04 | C170006 | Enhancement Project: Designs and constructs a transportation museum in Lamar in Prowers County. | Transportation Enhancements | 2010-06-05 | 2010-07-05 | 2010-11-12 | 2011-06-06 | 330750 | 0.000
1758 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LA PLATA |  | 03 | C200006 | Enhancement Project: constructs shared use path along CR 501 in Bayfield | Transportation Enhancements | 2009-08-24 | 2009-08-24 | 2009-12-07 | 2010-06-11 | 223724 | 0.000
1759 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | BENT |  | 04 | C290007 | Enhancement Project: Historic restoration through Town Square in Las Animas in Bent County, install streetscaping, sidewalks and landscaping. | Transportation Enhancements | 2010-03-17 | 2010-03-17 | 2010-05-01 |  | 121000 | 0.000
1760 | Completed | C220,C240 | Highway Infrastructure Investment Grant | COLORADO | CLEAR CREEK |  | 02 | C510023 | Enhancement Project: constructs asphalt recreation trail from Bakerville to Loveland Basin in Clear Creek County along I70 | Transportation Enhancements | 2010-05-07 | 2010-06-09 | 2010-08-31 | 2010-08-14 | 903625 | 0.000
1761 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | PITKIN |  | 03 | C570017 | Enhancement project to restore highway, intersection, and Pitkin Cty Coke Ovens in Redstone | Transportation Enhancements | 2010-09-16 | 2011-05-01 |  |  | 143089
1762 | Underway | C490 | OJT/SS | COLORADO | STATEWIDE |  |  | HQ00023 | Provides on the job training to construction workers to develop construction skills | Other | 2010-01-01 | 2010-01-01 | 2011-01-30 |  | 250000 | 0.000
1763 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | Multiple | M040017 | Enhancement Project: Construct a bicycle and pedestrian trail on the south side of the West 86th Parkway in Arvada to connect the exisitng trails. | Transportation Enhancements | 2009-10-13 | 2009-10-22 | 2009-12-21 |  | 300000 | 0.000
1764 | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | M040019 | This project widens 74TH AVE from KIPLING to CARR to accommodate bike lanes and add sidewalks. | Transportation Enhancements | 2010-05-03 | 2010-05-03 | 2010-12-15 |  | 281773 | 0.000
1765 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LA PLATA |  | 03 | M065003 | Enhancement Project: constructs sidewalks along US 160 business route in Bayfield | Transportation Enhancements | 2009-08-20 | 2009-08-24 | 2009-11-30 | 2010-06-14 | 200000 | 0.110
1766 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | M070002 | Enhancement Project: Construct bicycle and pedestrian improvements on Main Street in Berthoud. | Transportation Enhancements | 2010-07-06 | 2010-07-12 | 2010-08-25 | 2011-05-20 | 134000 | 0.010
1767 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | PUEBLO | PUEBLO | 03 | M086056 | Enhancement Project:: Pedestrian trail replacement and streetscape on Northern Avenue from Vinewood Lane to Prairie Avenue in Pueblo. | Transportation Enhancements | 2010-04-01 | 2010-04-01 | 2010-06-25 | 2010-10-26 | 165000 | 0.000
1768 | Completed | C220,C240 | Highway Infrastructure Investment Grant | COLORADO | PUEBLO | PUEBLO | 03 | M086058 | Constructs Veteran's memorial pedestrian bridge in Gateway Park at corner of Grand Avenue and S. Main Street in Pueblo | Transportation Enhancements | 2010-03-23 | 2010-03-23 | 2010-12-24 | 2010-12-01 | 600000 | 0.000
1769 | Underway | C220,C230 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | STATEWIDE | 02 | M110065 | Enhancement Project: constructs pedestrian access ramps at various intersections in Boulder to meet Americans with Disability (ADA) requirements. | Transportation Enhancements | 2009-09-08 | 2009-09-14 | 2009-11-09 |  | 732624 | 0.000
1770 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | M110066 | Enhancement Project: Constructs bike/pedestrian crossing treatments including medians, striping, flashing beacons and signage at the Folsom Street and Spruce Street intersection in Boulder. | Transportation Enhancements | 2009-09-08 | 2009-09-08 | 2009-12-08 | 2009-11-21 | 273270 | 0.000
1771 | Underway | C220,C230 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | STATEWIDE | 02 | M110073 | Enhancement project to construct a bike and pedestrian trail along SH 157 from Goose Creek to Valmont in Boulder. | Transportation Enhancements | 2011-01-03 | 2010-08-09 |  |  | 375843 | 0.000
1772 | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | M190003 | Resurfaces in asphalt 4th Avenue(Weld County Road 74) in Severance 2.5 miles west of Weld County Road 25 | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2009-11-30 | 2009-10-28 | 838000 | 0.000
1773 | Underway | C220,C240,C230 | Highway Infrastructure Investment Grant | COLORADO | EL PASO | COLORADO SPRINGS | 05 | M240121 | Widens Woodmen Rd. and constructs a new interchange at Academy Blvd.in Colorado Springs including construction of sidewalks and a bike path. | Pavement Widening | 2009-09-18 | 2009-09-24 | 2011-11-15 |  | 35031818 | 0.000
1774 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | LOGAN |  | 04 | M256012 | Enhancement Project: improves sidewalks and ADA ramps along 7th Street in Sterling | Transportation Enhancements | 2010-06-01 | 2010-06-01 | 2010-08-03 |  | 211000 | 0.000
1775 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | DENVER | DENVER, CO | 01 | M320064 | Enhancement Project: Striping and singage on various designated bikeways on the streets of Denver. | Transportation Enhancements | 2009-10-22 | 2009-10-26 | 2010-07-09 |  | 188726 | 0.000
1776 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 02 | M356024 | Enhancement Project: replace existing 4' sidewalks with 8' sidewalks to serve as a bike and pedestrain train on Bradburn Blvd from 73rd Avenue to Turnpike Drive in Westminster. | Transportation Enhancements | 2009-07-23 | 2009-07-27 | 2009-09-25 | 2009-09-30 | 260000 | 0.000
1777 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | WELD | BOULDER | 02 | M400004 | Enhancement Project: Construct bike pathes on the north and south sides of Leon Wurl Parkway in Erie from Bonanza Drive east to I-25. | Transportation Enhancements | 2009-10-12 | 2009-10-19 | 2010-02-16 |  | 587066 | 0.000
1778 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | M400005 | Enhancement Project: constructs bike lanes on East County Line Road from SH7 to Erie Parkway in Erie | Transportation Enhancements | 2010-03-15 | 2010-03-15 | 2010-06-13 | 2011-05-13 | 388000 | 0.000
1779 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LARIMER |  | 04 | M405013 | Enhancement Project: constructs Fall River Trail/Path in Estes Park | Transportation Enhancements | 2009-10-05 | 2009-10-08 | 2009-12-17 | 2010-03-28 | 140012 | 0.730
1780 | Underway | C220,C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | STATEWIDE | 04 | M415011 | Enhancement Project: Construct bicycle and pedestrian improvements on the US 85 service road in Evans. | Transportation Enhancements | 2010-03-15 | 2010-03-22 | 2010-06-26 |  | 160000 | 0.000
1781 | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | M415012 | Resurfaces 37th Street in Evans in asphalt | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-10-20 | 2009-10-22 | 324629 | 0.000
1782 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | WELD |  | 04 | M465007 | Enhancement Project: constructs bike trail at S. Platte River Bridge in Ft. Lupton | Transportation Enhancements | 2010-05-26 | 2010-05-26 |  |  | 90000 | 0.000
1783 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | MORGAN |  | 04 | M470009 | Enhancement Project: constructs Rainbow Bridge kiosk and makes pedestrian improvements in Ft. Morgan | Transportation Enhancements | 2010-02-05 | 2010-03-22 | 2010-06-02 | 2010-09-01 | 140000 | 0.100
1784 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | GARFIELD |  | 03 | M535004 | Enhancement Project: constructs a pedestrian bridge over I-70 along Devereux Rd in Glenwood Springs | Transportation Enhancements | 2009-09-11 | 2009-09-15 | 2010-07-31 | 2010-07-26 | 50200 | 0.000
1785 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | GRAND |  | 02 | M560002 | Enhancement Project:: Beautification and drainage improvements at the Grand Lake Welcome Center in Grand Lake, Grand County. | Transportation Enhancements | 2010-03-23 | 2010-05-10 | 2010-06-18 | 2010-06-18 | 169000 | 0.000
1786 | Underway | C220,C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | M570040 | Enhancement Project: Constructs bike and pedestrian trail along the Greeley #3 ditch. | Transportation Enhancements | 2010-06-03 |  |  |  | 212000 | 0.000
1787 | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | ROUTT |  | 03 | M615002 | Enhancement Project: improves and extends sidewalks in Hayden | Transportation Enhancements | 2010-04-15 | 2010-07-12 | 2010-10-10 | 2010-10-14 | 256000 | 0.250
1788 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | M760030 | Constructs new bike path from Rooney Rd to Indiana St along US 6 and C470 | Transportation Enhancements | 2010-03-04 | 2010-03-17 | 2010-06-03 |  | 153274 | 0.000
1789 | Completed | C220,C240 | Highway Infrastructure Investment Grant | COLORADO | BENT |  | 04 | M780003 | Enhancement Project: Historic restoration by construction of sidewalks, landscaping, signage, and parking lot rehabilitation of Heritiage Center in Bent County | Transportation Enhancements | 2010-06-09 | 2010-08-16 | 2010-11-24 | 2011-08-03 | 98453 | 0.000
1790 | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | M830046 | Upgrade equipment at the traffic operations center in Loveland. | Other | 2010-01-29 | 2010-01-29 | 2010-05-14 | 2010-06-03 | 129143 | 0.000
1791 | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | M830047 | Intersection improvements at SH 34 and Wilson in Loveland. | Safety/Traffic Management | 2009-09-14 | 2009-09-14 | 2009-12-01 | 2009-11-24 | 250000 | 0.000
1792 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | M835002 | Enhancement Project: streetscape enhancements and recostruction of Main Street (US 36) in Lyons between 3rd and 5th Avenues to include paving, curb and gutter, landscaping and pedestrian amenities. | Transportation Enhancements | 2009-09-28 | 2009-10-12 | 2009-10-13 |  | 689000 | 0.294
1793 | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | M935001 | Enhancement Project: Construct sidewalks on SH 119 between Eldora and @nd in Nederland to connect to the RTD parking. | Transportation Enhancements | 2009-09-08 | 2009-09-14 | 2009-12-12 |  | 385000 | 2.000
1794 | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 02 | M945001 | This project is reconstructing concrete on HURON ST from 104TH TO 112TH. | Pavement Improvement | 2010-04-16 | 2010-04-19 | 2011-03-21 |  | 3903974 | 0.000
1795 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | LINCOLN |  | 04 | R100157 | The project will ireconstruct to concrete pavement 8.7 miles of US 40/US 287 (mileposts 413-422 approximately) south of Hugo in Lincloln County. | Pavement Improvement | 2009-06-02 | 2009-07-16 | 2010-11-30 | 2010-10-26 | 11281493 | 8.700
1796 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 02 | R600340 | Installs ramp metering systems on I-25, US 36, and C470 in various locations | Safety/Traffic Management | 2009-05-19 | 2009-06-01 | 2009-08-24 | 2009-10-06 | 259460 | 0.180
1797 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | DENVER, CO | 02 | R600343 | Replaces traffic signals at the intersection of US6, SH 58 and SH 93 in Golden and at the SH 128 and Simms intersection in Broomfield. | Safety/Traffic Management | 2009-06-04 | 2009-07-20 | 2009-11-02 | 2010-06-07 | 862403 | 4.380
1798 | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | R600346 | Resurface in asphalt approximately three miles of US 40, Colfax Avenue, between Kipling Street and Sheridan Blvd in Lakewood. | Pavement Improvement | 2009-05-01 | 2009-06-01 | 2009-09-09 | 2009-11-09 | 2231905 | 2.829
1799 | Underway | C490 | OJT/SS | COLORADO | STATEWIDE |  |  | SW00836 | This grant will employ wounded veterans in tranportation jobs to provide labor on highway projects and develop construction skills. | Other | 2010-03-29 | 2010-03-29 | 2012-12-31 |  | 150000 | 0.000
1800 | Underway | C490 | OJT/SS | COLORADO | STATEWIDE |  |  | SW00837 | This grant provides on the job training to construction workers to develop construction skills. | Other | 2010-03-29 | 2010-03-29 | 2012-12-31 |  | 210000 | 0.000
1801 | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 0001315 | The project involves the reconstruction and lengthening of the existing AMTRAK bridge over Route 1, as well as the rehabilitation of a portion of Route 1 in the Town of Branford | Bridge Replacement | 2009-08-13 | 2009-08-13 | 2014-09-15 |  | 70815491 | 0.000
1802 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | MERIDEN-NEW HAVEN | 02 | 0001320 | This project involves the installation of sidewalks in Old Saybrook along Rte 1 | Transportation Enhancements | 2010-10-18 | 2010-10-18 | 2011-06-15 | 2011-07-17 | 458762 | 0.430
1803 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | SPRINGFIELD-CHICOPEE-HOLYOKE (MA) | 01 | 0005105 | This project will extend the life of the bridge along Route 5 over Interstate 91 in the Town of Enfield by replacing the existing deteriorated deck, bridge supports, and piers. | Bridge Improvement | 2009-06-22 | 2009-06-22 | 2010-12-13 | 2011-06-01 | 6730000 | 0.000
1804 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R418 | The State of Connecticut will replace overhead sign supports on multiple state highways | Safety/Traffic Management | 2009-08-03 | 2009-08-03 | 2011-07-15 | 2011-11-30 | 5975600 | 0.000
1805 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD |  | 01 | 000R430 | The State of Connecticut will install and revise traffic control signals at various intersections throughout District 1 | Safety/Traffic Management | 2009-07-27 | 2009-07-27 | 2010-08-10 | 2010-08-11 | 1362070 | 0.000
1806 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R442 | The State of Connecticut will install and revise traffic control signals at various intersections in District 2 to improve safety | Safety/Traffic Management | 2009-08-03 | 2009-10-31 | 2011-07-01 | 2011-04-04 | 328970 | 0.000
1807 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R444 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 2 to improve safety | Safety/Traffic Management | 2009-08-03 | 2009-10-31 | 2011-07-01 | 2011-04-04 | 1672716 | 0.000
1808 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 000R447 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 to improve safety | Safety/Traffic Management | 2009-08-03 | 2009-08-10 | 2011-01-24 | 2011-01-24 | 241286 | 0.010
1809 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 000R449 | The State of Connecticut will install and revise traffic control signals at various intersections in District 3 | Safety/Traffic Management | 2009-08-03 | 2009-08-10 | 2011-01-24 | 2011-01-24 | 395498 | 0.000
1810 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R453 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 4 | Safety/Traffic Management | 2009-12-11 | 2010-05-28 | 2010-07-14 | 2010-11-24 | 788940 | 0.000
1811 | Underway | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R458 | This project will install STC traffic signals; District 2 STC signals, maintenance upgrades | Safety/Traffic Management | 2011-02-03 | 2011-07-21 | 2012-11-11 |  | 202379 | 0.000
1812 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R514 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 | Safety/Traffic Management | 2009-08-03 | 2009-08-10 | 2011-01-24 | 2011-01-24 | 1166384 | 0.000
1813 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R538 | This project consists of the replacement of bridge deck joints within District 4 | Bridge Improvement | 2009-07-24 | 2009-08-03 | 2010-01-26 | 2010-05-26 | 6080516 | 32.260
1814 | Underway | C240,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) |  | 000R544 | Install STC traffic signals in District 3 and STC traffic signal maintenance upgrades | Safety/Traffic Management | 2011-02-03 | 2011-02-03 | 2011-11-29 |  | 794763 | 0.000
1815 | Underway | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE | MERIDEN-NEW HAVEN |  | 000R581 | Install STC traffic signals, District 2 STC traffic signal maintenance upgrades | Safety/Traffic Management | 2011-02-03 | 2011-07-21 | 2012-11-11 |  | 269257 | 0.000
1816 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 000R594 | THE STATE OF CONNECTICUT WILL INSTALL TRAFFIC CONTROL SIGNAL CONTROLLERS, CITY OF NEW HAVEN | Other | 2010-09-11 | 2010-09-11 | 2011-10-16 | 2011-10-15 | 3817460 | 0.000
1817 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 03 | 000R596 | This project consists of pavement milling and resurfacing of the travel lanes, new line striping, rumble strips, and NOVACHIPTM Surface treatment that provides improved skid, wear, and rutting resiste | Pavement Improvement | 2009-10-16 | 2009-10-16 | 2010-05-17 | 2010-06-01 | 3390141.16 | 5.880
1818 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R597 | The State of Connecticut will conduct crack sealing and crack filling along major highways including Route 8, I-84, I-91, I-95, and I-384. This effort will help extend the lifetime of the pavements o | Pavement Improvement | 2009-10-01 | 2009-10-01 | 2009-11-14 | 2009-12-04 | 1865912.89 | 22.270
1819 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R598 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists through District 1. | Safety/Traffic Management | 2009-08-31 | 2009-09-08 | 2009-09-30 | 2009-09-30 | 139004.1 | 0.000
1820 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R599 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 2. | Safety/Traffic Management | 2009-09-01 | 2009-10-05 | 2009-10-19 | 2009-10-19 | 124430.28 | 0.000
1821 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R600 | The State of Connecticut will install epoxy pavement markings and Interstae lines for safey of motorists through District 3. | Safety/Traffic Management | 2009-09-01 | 2009-09-20 | 2009-10-14 | 2009-10-14 | 220000 | 0.000
1822 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R601 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 4 | Safety/Traffic Management | 2009-09-02 | 2009-09-08 | 2010-05-17 | 2009-09-11 | 47428 | 0.000
1823 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R602 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 4 | Safety/Traffic Management | 2010-05-01 | 2010-05-01 | 2010-07-01 | 2010-07-08 | 268791 | 0.000
1824 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R603 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 3 | Safety/Traffic Management | 2010-09-01 | 2010-09-12 | 2010-10-08 | 2010-10-08 | 484677 | 0.000
1825 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R604 | The State of Connecticut will install epoxy pavement markings and Interste lines for safety of motorists throughout District 1. | Safety/Traffic Management | 2009-10-16 | 2009-10-25 | 2009-11-10 | 2009-12-01 | 331473 | 0.000
1826 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R605 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 2. | Safety/Traffic Management | 2009-10-06 | 2009-10-19 | 2010-04-23 | 2010-05-09 | 390361.61 | 0.000
1827 | Completed | C220,C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 000R606 | TOWN CENTER PEDESTRIAN AND STREETSCAPE ENHANCEMENTS, TOWN OF NEW FAIRFIELD | Transportation Enhancements | 2010-05-24 | 2010-05-20 | 2010-09-16 | 2011-05-11 | 259754 | 0.130
1828 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R630 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES, AND INTERSECTIONS WITHIN DISTRICT 1 | Safety/Traffic Management | 2010-07-07 | 2010-07-25 | 2010-09-28 | 2010-09-28 | 232525 | 0.000
1829 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R631 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES AND INTERSECTIONS WITHIN DISTRICT 2 | Safety/Traffic Management | 2010-06-07 | 2010-06-07 | 2010-09-15 | 2010-07-16 | 210855 | 0.000
1830 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) |  | 000R632 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES, AND INTERSECTIONS IN DISTRICT 3 | Safety/Traffic Management | 2010-06-18 | 2010-07-06 | 2010-09-09 | 2010-09-15 | 384719.33 | 0.000
1831 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R633 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES, AND INTERSECTIONS IN DISTRICT 4 | Safety/Traffic Management | 2010-07-15 | 2010-08-08 | 2010-10-16 | 2010-10-20 | 174071 | 0.000
1832 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R640 | This project is for the installation of epoxy pavment markings on Interstate routes. The markings will maintain delineation of existing travel lanes abnd shoulder markings, and to maintain the retro- | Safety/Traffic Management | 2011-04-01 | 2011-04-01 | 2011-06-09 | 2011-06-07 | 278147.22 | 18.400
1833 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R644 | This project is for the installation of durable epoxy pavement markings on Interstate routes. The installation will be to maintain the delineation of existing traffic lanes and shoulder markings and t | Safety/Traffic Management | 2011-02-16 | 2011-04-06 | 2011-06-15 | 2011-06-10 | 147500 | 18.420
1834 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R657 | The timely sealing of the cracks in these roadways enhances pavement performance, while extending the pavement life in a cost effective manner. | Pavement Improvement | 2011-04-01 | 2011-04-25 | 2011-07-21 | 2011-06-08 | 641093 | 26.100
1835 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 0012138 | This project will involve the installation of sidewalks on Rte 12 from SR647 to School St and from RR avenue to Academy Hill Rd in Plainfield | Transportation Enhancements | 2010-05-05 | 2010-05-07 | 2010-09-01 | 2010-09-01 | 813543 | 1.200
1836 | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0015103 | This project will provide for median deck repairs on the bridge carrying Route 15 (Merritt Parkway) over Reservoir Avenue in the Town of Trumbull | Bridge Improvement | 2009-06-15 | 2009-06-18 | 2012-07-27 |  | 1195115 | 0.000
1837 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND |  | 02 | 0031118 | This project involves the installation of sidewalks on Main St from Paden Rd to 1000 feet north of Rte 275 in Coventry | Transportation Enhancements | 2010-06-28 | 2010-06-28 | 2010-10-25 | 2010-10-22 | 594852 | 0.000
1838 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | 0032183 | INTERSECTION IMPROVEMENTS AT ROUTE 32, LATHROP RD., AND MAPLE RD., TOWN OF WATERFORD | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-09-28 | 2010-11-24 | 625632 | 0.200
1839 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN |  | 02 | 0032184 | The State of Connecticut will resurface Route 2 in Eastbound and Westbound directions from Colchester to Lebanon | Pavement Improvement | 2009-10-28 | 2009-10-28 | 2009-11-11 | 2010-05-07 | 3380088 | 0.020
1840 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND |  | 02 | 0044133 | This project will provide additional pavement shoulder width to provide a safe turning vehicle with bypassing vehicle movement | Pavement Improvement | 2011-04-28 | 2011-04-28 | 2011-07-28 | 2011-07-28 | 141998 | 0.150
1841 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 0044148 | route 44 and 41 sidewalks and curbing, Salisbury | Transportation Enhancements | 2010-08-09 | 2010-08-16 | 2010-12-06 | 2011-06-02 | 380400 | 0.244
1842 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 0045132 | Project is to replace the concrete crib retaining wall W/ new new structure. Original wall was built in 1929. Wall supports CT Route 45 in Washington CT | Pavement Improvement | 2010-12-16 | 2010-12-16 | 2011-09-05 | 2011-09-22 | 346064 | 0.000
1843 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 0089118 | This project involves the reconstruction of the existing bridge superstructure, including new steel girders and a concrete deck. Additional improvements to the approach pavement and drainage will als | Bridge Improvement | 2009-07-03 | 2009-07-13 | 2010-08-03 | 2010-08-03 | 1173253 | 0.000
1844 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 0091103 | Pavement preservation will be conducted by the State of Connecticut along Interstate 91 from West Street in the Town of Rocky Hill to Route 3 in the Town of Wethersfield. Scope of work includes resur | Pavement Improvement | 2009-10-01 | 2009-10-14 | 2009-11-18 | 2009-11-17 | 4748987 | 4.080
1845 | Underway | C250,C240 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 0097006 | This project involves the replacement of bridge#02594 on Route 97 over the Mashamoquet Brook in the town of Pomfret | Bridge Replacement | 2010-07-17 | 2010-07-17 | 2010-11-02 |  | 1094854 | 0.000
1846 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0111001 | THE STATE OF CONNECTICUT WILL COMPLETE A PAVING PROJECT THAT INCLUDES THE RESURFACING OF WHITNEY AVE. TOWN OF TRUMBULL | Pavement Improvement | 2010-08-12 | 2010-08-26 | 2010-10-24 | 2010-12-13 | 1032849 | 1.480
1847 | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150192 | This project involves the resurfacing of the pavement, along with other bridge and safety improvements, along a section of Route 15 (Merritt Parkway) from Congress Street to Morehouse Highway | Pavement Improvement | 2009-06-15 | 2009-06-18 | 2012-07-27 |  | 23056722 | 44.060
1848 | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150193 | This project will provide for the replacement of the existing Route 15 (Merritt Parkway) bridge over the Mill River in the Town of Fairfield. | Bridge Replacement | 2009-06-15 | 2009-06-18 | 2012-07-27 |  | 10103973 | 0.020
1849 | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150194 | This project involves the resurfacing of the pavement, along with other bridge and safety improvements, along a section of Route 15 (Merritt Parkway) from Morehouse Highway to Route 8 | Pavement Improvement | 2009-06-15 | 2009-06-18 | 2012-07-27 |  | 39278907.9 | 10.730
1850 | Underway | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 0529003 | This project will provide work involving the addition of left turn lanes and median islands for increased safety and streetscape improvements | Pavement Improvement | 2011-04-01 | 2011-04-01 | 2012-10-03 |  | 1414085 | 0.760
1851 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 01 | 0912132 | I-91 PAVEMENT PRESERVATION TOWNS OF CROMWELL AND ROCKY HILL | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-07-31 | 2010-08-18 | 2657549 | 3.620
1852 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | MERIDEN-NEW HAVEN | 02 | 0952111 | This project consists of replacing the bridge deck joints on the Baldwin Bridge on I95 over the Connecticut River | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2009-11-17 | 2009-11-17 | 2631100 | 0.000
1853 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1002105 | RESURFACING OF FORD AND BEAVER ST. ANSONIA | Pavement Improvement | 2010-09-01 | 2010-09-01 | 2010-10-15 | 2010-12-10 | 550935 | 0.000
1854 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1005102 | HILLCREST DR. CRACK SEALING AND 1' OVERLAY TOWN OF BARKHAMSTED | Pavement Improvement | 2010-07-08 | 2010-07-12 | 2010-09-05 | 2010-09-03 | 121000 | 0.000
1855 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 01 | 1005104 | The existing pavement has exceeded its serviceability and is in need of anew surface. The proposed improvement includes a 2" overlay of hot-mix asphalt | Pavement Improvement | 2011-06-06 | 2011-06-06 | 2011-08-04 | 2011-09-08 | 233700 | 0.750
1856 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1007105 | In the Town of Berlin, Episcopal Road will be reconstructed and paved from Deming Road to Rowley Street to improve road and dainage. | Pavement Improvement | 2010-04-05 | 2010-04-12 | 2010-06-03 | 2010-06-01 | 498786 | 0.510
1857 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 1009111 | THIS PROJECT INCLUDES THE MILLING AND PAVING OF HAWLEYVILLE ROAD, TOWN OF BETHEL | Pavement Improvement | 2010-07-16 | 2010-07-19 | 2010-09-16 | 2011-12-09 | 509563 | 1.500
1858 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1015118 | Congress Street Bridge (Phase1 - Partial Demolition), City of Bridgeport | Bridge Replacement | 2010-01-21 | 2010-03-02 | 2010-06-29 | 2010-06-16 | 504348.12 | 0.000
1859 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1015119 | The project involves the pavement rehabilitation of Iranistan Avenue and Capital in the city of Bridgeport | Pavement Improvement | 2010-08-26 | 2010-09-20 | 2011-04-17 | 2011-04-14 | 1640400 | 0.000
1860 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1017106 | THIS PROJECT INVOLVES MIX STREET RECONSTRUCTION AND NORMALIZATION OF INTERSECTION WITH MALBY STREET, BRISTOL | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2010-11-15 | 2010-11-20 | 1065600 | 0.510
1861 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 1018108 | THE STATE OF CONNECTICUT WILL COMPLETE A PAVING PROJECT THAT INCLUDES THE MILLING AND PAVING GRAY'S BRIDGE RD, BROOKFIELD | Pavement Improvement | 2010-06-21 | 2010-06-28 | 2010-10-03 | 2010-09-23 | 413600 | 0.000
1862 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1025003 | THE STATE OF CONNECTICUT WILL COMPLETE THE PAVING OF WEST JOHNSON RD, CHESHIRE | Pavement Improvement | 2010-07-14 | 2010-07-14 | 2010-08-27 | 2010-08-24 | 618408 | 0.000
1863 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 01 | 1029001 | RIVERTON RD. CRACK SEALING AND RUBBERIZED CHIP SEAL, TOWN OF COLEBROOK | Pavement Improvement | 2010-07-09 | 2010-07-28 | 2010-09-06 | 2010-09-22 | 95032.71 | 0.000
1864 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 01 | 1033107 | GEER STREET PAVEMENT PRESERVATION - CROMWELL | Pavement Improvement | 2010-08-02 | 2010-08-02 | 2010-08-31 | 2010-08-31 | 226355 | 0.960
1865 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | Multiple | 1034114 | MILLING AND PAVING OF WHITE STREET, FRANKLIN STREET, AND FRANKLIN STREET EXT. CITY OF DANBURY | Pavement Improvement | 2010-05-27 | 2010-05-27 | 2010-08-24 | 2010-08-31 | 1593000 | 0.000
1866 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1035103 | Replacement of Staircases & Railings at Noroton Heights RR Station, Town of Darien | Transportation Enhancements | 2010-05-20 | 2010-05-20 | 2010-11-16 | 2010-12-20 | 479170 | 0.000
1867 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | STATEWIDE | 04 | 1035104 | THE STATE OF CONNECTICUT WILL COMPLETE THE PAVEMENT RESURFACING OF HOLLOW TREE RIDGE ROAD, WEST AVE. AND LEROY AVE.,TOWN OF DARIEN | Pavement Improvement | 2010-07-21 | 2010-07-21 | 2010-08-19 | 2010-08-13 | 633799 | 0.000
1868 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1036001 | THIS PROJECT INCLUDES THE MILLING AND OVERLAY OF ELIZABETH STREET, TOWN OF DERBY | Pavement Improvement | 2010-07-28 | 2010-07-28 | 2010-09-10 | 2010-09-10 | 600576 | 0.000
1869 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 02 | 1037102 | THE STATE OF CONNECTICUT WILL COMPLETE A CONSTRUCTION PROJECT INVOLVING THE PAVING OF MAIDEN LANE, DURHAM | Pavement Improvement | 2010-10-11 | 2010-10-11 | 2010-11-28 | 2010-11-02 | 260993 | 0.610
1870 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 02 | 1040103 | THE STATE OF CONNECTICUT WILLCOMPLETE THE CONSTRUCTION PROJECT THAT INCLUDES THE PAVING OF LAKE SHORE DRIVE, EAST HADDAM | Pavement Improvement | 2010-10-01 | 2010-10-01 | 2010-10-31 | 2010-11-01 | 104295 | 1.510
1871 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 02 | 1041104 | THIS PROJECT INCLUDES THE RESURFACING OF HADDAM NECK RD, EAST HAMPTON | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2010-07-22 | 2010-06-10 | 174351.01 | 0.682
1872 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1042118 | PAVEMENT REHABILIATION OF PORTIONS OF MAIN STREET AND SCHOOL ST., TOWN OF EAST HARTFORD | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2010-10-27 | 2010-12-17 | 2047715 | 0.000
1873 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1050106 | Various intersection improvements will be completed at the Black Rock Turnpike and Commerce Drive in Fairfield | Other | 2010-04-19 | 2010-04-19 | 2011-04-19 | 2011-04-16 | 1145418 | 0.000
1874 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1054001 | EAST STREET - CRACK SEALING AND MICROSURFACING - GOSHEN/NORFOLK | Pavement Improvement | 2010-07-16 | 2010-07-19 | 2010-08-29 | 2010-08-29 | 232139.63 | 3.600
1875 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1056112 | PAVEMENT RECONSTRUCTION AND OVERLAY OF FIELD POINT ROAD, DEARFIELD DR, BROOKSIDE DR, WEST ELM ST., RAILROAD AVE, PROSPECT ST AND HORSENECK LN., GREENWICH | Pavement Improvement | 2010-05-06 | 2010-05-09 | 2010-06-23 | 2010-06-17 | 918712 | 2.350
1876 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1059107 | PAVEMENT PRESERVATION OF STEPSTONE HILL ROAD, GUILFORD | Pavement Improvement | 2010-09-01 | 2010-09-01 | 2010-12-01 | 2010-12-13 | 632405 | 0.800
1877 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 1068107 | RECONSTRUCTION OF A PORTION OF LAKE RD., KILLINGLY | Pavement Improvement | 2010-08-10 | 2010-08-23 | 2010-10-15 | 2010-12-22 | 484680 | 0.600
1878 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1073104 | WHITE WOOD ROAD OVERLAY , TOWN OF LITCHFIELD | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2010-10-07 | 2010-09-10 | 149723 | 0.000
1879 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1076120 | In the Town of Manchester, a new traffic control signal will be installed at the interesection of Slater Street and the Best Buy driveways to improve safety and traffic flow to and from exisiting stor | Safety/Traffic Management | 2009-09-08 | 2010-04-01 | 2010-05-15 | 2010-05-15 | 252300 | 0.000
1880 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1076124 | In the Town of Manchester, pavement preservation will be conducted along Buckland Hills Road by repaving from Buckland Street eastward to Deming Street. | Pavement Improvement | 2009-11-05 | 2010-04-01 | 2010-06-29 | 2010-07-16 | 2509498 | 0.000
1881 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND |  | 02 | 1077107 | IN THE TOWN OF MANSFIELD, PAVING OF MANSFIELD CITY ROAD WILL BE COMPLETED | Pavement Improvement | 2010-07-07 | 2010-07-07 | 2010-10-13 | 2010-08-31 | 269036 | 0.000
1882 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 03 | 1081001 | THIS PAVEMENT PRESERVATION PROJECT WILL INCLUDE THE PAVING OF CEDAR STREET, DERBY AND JACKSON HILL ROAD, MIDDLEFIELD | Pavement Improvement | 2010-08-16 | 2010-08-16 | 2010-08-31 | 2010-08-31 | 54532.53 | 2.000
1883 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 03 | 1082111 | The contractor will complete the paving/resurfacing of Industrial Park Road in the town of Middletown | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2010-12-06 | 2011-05-19 | 1061915 | 0.740
1884 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1084104 | THIS PROJECT INVOLVES STRATEGIC PAVING ALONG CROSS HILL RD AND WILL BE COMPLETED WITHIN THE TOWN OF MONROE | Pavement Improvement | 2010-08-30 | 2010-08-30 | 2010-10-28 | 2010-10-28 | 866554 | 0.000
1885 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1086102 | THIS PROJECT WILL INCLUDE CRACK SEALING AND MRCROSURFACING OF ALAN WHITE ROAD IN THE TOWN OF MORRIS | Pavement Improvement | 2010-07-19 | 2010-07-21 | 2010-09-01 | 2010-09-01 | 89356.65 | 1.760
1886 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1088109 | This project work inlcudes the milling and overlaying of Corbin Avenue, East Street, and Stanley Street in the city of New Britain | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2010-12-15 | 2011-07-22 | 1734651 | 3.350
1887 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1089102 | THIS PROJECT INCLUDES PAVEMENT RESURFACING OF OLD NORWALK ROAD, FARM ROAD, WEST ROAD AND WEED ROAD, IN THE TOWN OF NEW CANAAN | Pavement Improvement | 2010-06-23 | 2010-06-23 | 2010-08-06 | 2010-08-05 | 883900 | 2.810
1888 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 1090103 | In the Town of New Fairfield, the park and ride lot will be repaved for an improved surface. | Pavement Improvement | 2009-10-13 | 2009-10-13 | 2009-10-27 | 2009-10-27 | 217133.91 | 4.250
1889 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1091107 | THIS PROJECT INCLUDES CRACK SEALING AND MICROSURFACING OF WEST HILL ROADIN THE TOWN OF NEW HARTFORD | Pavement Improvement | 2010-08-02 | 2010-08-16 | 2010-10-11 | 2010-09-28 | 131321 | 1.120
1890 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1092133 | This project will provide for the reconstruction of Quinnipiac Avenue, including pavement, drainage and sidewalks, from south of Ferry Street to Clifton Street in the City of New Haven. | Pavement Improvement | 2010-04-01 | 2010-04-01 | 2011-11-27 | 2011-10-15 | 6503800 | 0.789
1891 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1092135 | This project consists of the pavement rehabilitation of Congress Street in the City of New Haven | Pavement Improvement | 2010-12-27 | 2010-10-27 | 2011-04-25 | 2011-04-26 | 843700 | 0.000
1892 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1092136 | THIS PROJECT INVOLVES THE RECONSTRUCTION AND REHABILITATION OF QUINNIPIAC AVE., PHASE 2 CITY OF NEW HAVEN | Pavement Improvement | 2010-10-10 | 2010-10-10 | 2011-09-30 | 2011-09-30 | 1874700 | 0.197
1893 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | 1094106 | The project will complete roadway improvements to Montauk Avenue in New London | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2010-09-12 | 2011-01-05 | 807572 | 0.830
1894 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | DANBURY (NY) | 05 | 1095114 | This project includes the completion of milling and paving Boardman Road and Grove Street in the town of New Milford | Pavement Improvement | 2010-06-16 | 2010-06-17 | 2010-09-13 | 2010-09-17 | 1043944 | 1.900
1895 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | STATEWIDE | 05 | 1096103 | This project includes the milling and paving of Castle Hill Road with full depth reclamation and paving of Castle Meadow Road in the town of Newtown | Pavement Improvement | 2010-09-20 | 2010-09-20 | 2010-10-29 | 2010-10-19 | 669672 | 0.000
1896 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1100107 | The existing pavement has exceeded its serviceability and appears to be a very good candidate for pavement preservation improvements. The resurfacing of this roadway will help ensure its serviceabili | Pavement Improvement | 2011-04-01 | 2011-04-01 | 2011-04-30 | 2011-05-31 | 376040 | 0.635
1897 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1102109 | THIS PROJECT INCLUDES THE RESURFACING AND PAVING OF DR. MARTIN LUTHER KING JR. DR. BELDEN HILL RD., BUTLER ST. HARBOR AVE., IN THE CITY OF NORWALK | Pavement Improvement | 2010-06-16 | 2010-06-21 | 2010-09-30 | 2010-08-04 | 1399934 | 0.000
1898 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1102110 | The timely resurfacing of these roadways enhance pavement performance while extending the pavement life in a cost effective manner | Pavement Improvement | 2011-05-18 | 2011-05-31 | 2011-08-28 | 2011-08-05 | 364176 | 1.700
1899 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1107004 | THIS PROJECT INVOLVES THE RESURFACING OF CHRISTIAN ST. IN OXFORD | Pavement Improvement | 2010-09-14 | 2010-09-14 | 2010-10-28 | 2010-10-28 | 182734 | 0.150
1900 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1109103 | THE STATE OF CONNECTICUT WILL PROVIDE FOR THE RECONSTRUCTION AND PAVING OF CAMP ST. IN THE TOWN OF PLAINVILLE | Pavement Widening | 2010-09-07 | 2010-09-07 | 2010-11-07 | 2010-11-05 | 707900 | 0.200
1901 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | HARTFORD | 05 | 1110106 | THE VENDOR WILL MILL AND OVERLAY HARWINTON AVE., ROUTE 6 TO ARMBURSTER RD. IN THE TOWN OF PLYMOUTH | Pavement Improvement | 2010-08-13 | 2010-08-25 | 2010-11-20 | 2010-11-09 | 692456 | 0.000
1902 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 01 | 1112001 | THE VENDOR WILL COMPLETE THE PAVEMENT PRESERVATION OF BARTLETT ST, COLLINS HILL RD, HIGH ST, ISINGLASS AND JOBS POND ROAD IN PORTLAND | Pavement Improvement | 2010-05-10 | 2010-06-14 | 2010-07-14 | 2010-06-24 | 234163.09 | 8.270
1903 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 03 | 1114107 | THIS ROAD IMPROVEMENT PROJECT WILL INCLUDE THE RESURFACING OF STRAITSVILLE ROAD IN THE TOWN OF PROSPECT | Pavement Improvement | 2010-08-11 | 2010-08-11 | 2010-09-24 | 2010-09-22 | 282795 | 0.000
1904 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM | WORCESTER (MA) | 02 | 1115105 | THIS ROAD IMPROVEMENT PROJECT WILL INCLUDE THE PAVEMENT PRESERVATION OF CHURCH STREET IN THE TOWN OF PUTNAM | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-11-17 | 2010-12-13 | 497246 | 0.000
1905 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD |  | 04 | 1116102 | This project will provide improvements along Main Street within the Georgetown Village area. Proposed improvements include sidewalks, crosswalks, ornamental lighting and landscaping. | Transportation Enhancements | 2010-10-12 | 2010-10-18 | 2011-08-08 | 2011-06-16 | 903712 | 0.250
1906 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1117108 | THE VENDOR WILL PERFORM MILLING AND PAVING OF FARMINGVILLE RD AND OLD STAGECOACH RD. IN THE TOWN OF RIDGEFIELD | Pavement Improvement | 2010-09-20 | 2010-09-21 | 2010-12-03 | 2010-12-03 | 716563 | 0.000
1907 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1118003 | In the Town of Rocky Hill, pavement preservation will be conducted along Old Main Street by repaving from Glastonbury Avenue extending 50 feet south of the bridge over Goff Brook | Pavement Improvement | 2009-07-29 | 2009-08-10 | 2009-10-18 | 2009-12-16 | 1229806.93 | 0.000
1908 | Underway | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1124001 | THIS PAVEMENT PROJECT WILL INCLUDE THE PAVING AND REHABILITATION OF DERBY AVE.IN THE TOWN OF SEYMOUR | Pavement Improvement | 2011-04-01 | 2011-05-01 | 2011-10-27 |  | 933259 | 0.000
1909 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1126108 | THIS PAVEMENT REHABILITATION PROJECT WILL INCLUDE THE PAVING AND REHABILITATION OF CONSTITUTION BLVD. SOUTH IN THE CITY OF SHELTON | Pavement Improvement | 2010-04-28 | 2010-05-05 | 2010-09-01 | 2010-06-29 | 453730 | 0.000
1910 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1130001 | This project involves the pavement preservation of Main Street in the town of Southbury | Pavement Improvement | 2010-10-12 | 2010-10-12 | 2010-11-25 | 2010-11-25 | 567557 | 2.000
1911 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1131106 | THIS PROJECT INVOLVES THE MILLING AND OVERLAYING OF SOUTH END RD AND MOUNT VERNON RD. IN THE TOWN OF SOUTHINGTON | Pavement Improvement | 2010-08-17 | 2010-08-17 | 2010-11-01 | 2010-12-20 | 819800 | 1.338
1912 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1132104 | In the Town of South Windsor, beginning at the Manchester Town Line and extending north, approximately 4400 feet of Buckland Road will be resurfaced. | Pavement Improvement | 2009-10-02 | 2009-10-02 | 2009-12-30 | 2009-12-03 | 988146.11 | 0.000
1913 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1138104 | IN THE TOWN OF STRATFORD THE VENDOR WILL COMPLETE THE REPAVING OF BRUCE AVE. | Pavement Improvement | 2010-09-07 | 2010-09-20 | 2010-11-18 | 2010-11-18 | 331184 | 0.600
1914 | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | HARTFORD | 05 | 1140001 | Pavement rehabilitaition will be completed on Old Northfield Road in Thomaston | Pavement Improvement | 2010-06-21 | 2010-07-07 | 2010-09-18 | 2010-07-27 | 172797.22 | 0.322
1915 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1143109 | THIS PAVEMENT PROJECT INCLUES THE MILLING AND OVERLAYING OF LITCHFIELD ST., WINTHROP ST. AND WATER ST., IN THE CITY OF TORRINGTON | Pavement Improvement | 2010-06-17 | 2010-08-02 | 2010-09-14 | 2010-10-21 | 1038286 | 0.000
1916 | Underway | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 05 | 1151117 | THIS PROJECT INCLUDES SIDEWALK IMPROVEMENTS ON COOKE ST IN WATERBURY | Transportation Enhancements | 2010-09-16 | 2010-09-16 | 2012-04-25 |  | 2527074 | 1.800
1917 | Underway | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | WATERBURY | 05 | 1153102 | This project will provide full depth reconstruction for deteriorated pavement structure, much needed drainage upgrades and replacement of Turkey Brook's inadequate culvert crossing | Pavement Improvement | 2011-04-01 | 2011-04-01 | 2012-11-01 |  | 1422917 | 0.500
1918 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | WATERBURY | 05 | 1153111 | THIS PROJECT INCLUDES THE RESURFACING OF FRENCH STREET, IN THE TOWN OF WATERTOWN | Pavement Improvement | 2010-09-27 | 2010-09-27 | 2010-11-10 | 2010-11-29 | 645977 | 0.000
1919 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | MERIDEN-NEW HAVEN | 02 | 1154102 | THE VENDOR WILL COMPLETE THE MILLING AND PAVING OF MCVEIGH ROAD FROM ROUTE 153 TO POND MEADOW ROAD, IN THE TOWN OF WESTBROOK | Pavement Improvement | 2010-07-21 | 2010-07-26 | 2010-09-03 | 2010-08-31 | 562400 | 1.040
1920 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1157001 | THE VENDOR WILL COMPLETE THE PAVEMENT PRESERVATION OF OLD HYDE ROAD IN THE TOWN OF WESTON | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-08-03 | 2010-08-03 | 260600 | 0.000
1921 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1158001 | THIS PAVEMENT PRESERVATION PROJECT INCLUDES THE PAVING OF CROSS HIGHWAY, LONG LOTS RD., AND NEWTOWN TPKE, IN THE TOWN OF WESTPORT | Pavement Improvement | 2010-03-29 | 2010-03-29 | 2010-05-03 | 2010-05-03 | 748040 | 0.000
1922 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1158002 | Pavement preservation | Pavement Improvement | 2010-10-18 | 2010-10-18 | 2010-12-27 | 2011-04-25 | 1190373 | 5.080
1923 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1162112 | THIS PROJECT WILL CONSIST OF COMPLETING PAVEMENT OVERLAY ON WETMORE AVE. IN THE TOWN OF WINCHESTER | Pavement Improvement | 2010-08-16 | 2010-09-01 | 2010-10-14 | 2010-10-13 | 370400 | 0.455
1924 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 1163102 | THIS PROJECT WILL INCLUDE THE PAVING OF HIGH ST., VALLEY ST., AND JACKSON ST. IN THE TOWN OF WINDHAM | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2010-08-19 | 2010-08-10 | 445388.88 | 0.850
1925 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1164106 | In the Town of Windsor, pavement preservation will be conducted by along Day Hill Road by milling and paving from Blue Hills Avenue to Great Pond Drive. This will include new drainage and curbing. | Pavement Improvement | 2009-09-28 | 2009-10-01 | 2009-11-29 | 2009-11-19 | 891700 | 0.000
1926 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 05 | 1166001 | This project will include the paving of Long Swamp Road in the town of Wolcott | Pavement Improvement | 2010-08-17 | 2010-08-23 | 2010-12-15 | 2010-12-07 | 585300 | 0.250
1927 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | 3953001 | IN THE TOWNS OF EAST LYME,MONTVILLE AND WATERFORD THIS PROJECT WILL INCLUDE THE PAVEMENT PRESERVATION OF I-395. | Pavement Improvement | 2010-05-14 | 2010-05-14 | 2010-07-28 | 2010-06-25 | 3505035 | 5.600
1928 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 6034007 | This project consists of the replacement of the Backus Avenue Bridge in the city of Danbury | Bridge Improvement | 2010-03-29 | 2010-03-29 | 2010-10-27 | 2010-10-27 | 1055328 | 0.049
1929 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | WATERBURY | 05 | 6080004 | The purpose of this project is to replace the Longmeadow Road Bridge in the Town of Middlebury | Bridge Replacement | 2010-04-01 | 2010-04-01 | 2011-05-26 | 2011-05-26 | 289700 | 0.000
1930 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON |  | 02 | 6085002 | THE PURPOSE OF THIS PROJECT IS TO REPAIR THE BRIDGE ON OLD COLCHESTER RD.IN THE TOWN OF MONTVILLE | Bridge Improvement | 2010-04-05 | 2010-04-05 | 2011-05-19 | 2010-12-06 | 1067200 | 0.094
1931 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 03 | 6087005 | This project consists of the rehabilitation of the Rubber Avenue Bridge, number 03713, town of Naugatuck | Bridge Improvement | 2010-04-12 | 2010-06-16 | 2010-11-07 | 2010-11-04 | 1168891 | 0.000
1932 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 6099012 | THE PURPOSE OF THIS PROJECT IS INSTALL A MEMBRANE AND OVERLAY BRIDGE #5207 ON LOWER RD IN NORTH CANAAN | Bridge Improvement | 2010-07-06 | 2010-07-06 | 2010-09-03 | 2010-12-03 | 448008 | 0.040
1933 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 6119002 | THIS PROJECT CONSISTS OF PAINTING JUDDS BRIDGE IN THE TOWN OF ROXBURY | Other | 2010-07-21 | 2010-07-21 | 2010-11-27 | 2010-12-24 | 233104 | 0.030
1934 | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 6123001 | THE VENDOR WILL REPAIR THE STATION ROAD BRIDGE (BR #4768) IN THE TOWN OF SCOTLAND | Bridge Improvement | 2010-07-19 | 2010-07-19 | 2010-10-23 | 2011-05-11 | 349571 | 0.030
1935 | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 6158006 | This project will provide rehabilitation of th existing Hales Road bridge over Metro North RR in the Town of Westport. Construction will include complete replacement of the bridge superstructure and | Bridge Improvement | 2009-09-28 | 2009-09-28 | 2011-04-28 | 2011-09-07 | 4192758 | 0.000
1936 | Underway | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 02 | H011002 | This project will include the completing the reconstruction of Town Farms Road and Post Office Road in Enfield | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2011-10-27 |  | 3746137 | 1.200
1937 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | H018011 | This project will include streetscape improvements for Mystic within the town of Stonington | Transportation Enhancements | 2010-05-17 | 2010-05-17 | 2010-11-12 | 2010-11-12 | 544172 | 0.340
1938 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | H018012 | This project will provide for streetscape type improvements along Route 1 in the Town of Stonington from the Mystic Bridge easterly to Willow Street. The work includes new curbing, sidewalks, decorti | Transportation Enhancements | 2009-09-14 | 2009-09-14 | 2010-05-01 | 2010-05-01 | 788777 | 0.110
1939 | Underway | C220,C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | H018013 | Mystic Streetscape, Town of Groton | Transportation Enhancements | 2010-09-17 | 2010-09-20 | 2012-06-30 |  | 3561200 | 0.300
1940 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | H135002 | In the Town of Southington, the Linear Park multi-use trail will be constructed along an abandoned rail line from West Main Street to the Cheshire Town line. | Transportation Enhancements | 2010-01-14 | 2010-01-20 | 2011-04-01 | 2011-05-06 | 1902990 | 1.900
1941 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | PEDS102 | THE PROJECT WILL INCLUDE EXTENDING THE CHARTER OAK GREENWAY 4,600 FEET THROUGH THE HIGHLAND PARK SECTION OF MANCHESTER | Transportation Enhancements | 2010-08-02 | 2010-08-02 | 2011-05-29 | 2011-11-30 | 643000 | 0.870
1942 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 01 | PEDS124 | In the City of Torrington, the Still River Greenway multi-use path will be extended 1.8 miles from Princewoods Road north to Harris Drive. | Transportation Enhancements | 2009-07-15 | 2009-07-15 | 2009-11-11 | 2009-12-08 | 900000 | 0.000
1943 | Completed | C220,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | PEDS125 | THE PROJECT WILL INCLUDE CONNECTING THE BURLINGTON TRAIL TO THE FARMINGTON TRAIL IN THE TOWNS OF BURLINGTON AND FARMINGTON | Transportation Enhancements | 2010-07-06 | 2010-08-04 | 2010-10-03 | 2010-11-15 | 305600 | 0.000
1944 | Underway | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | STATEWIDE | 01 | PEDS126 | WITHIN THE CITY OF HARTFFORD IMPROVEMENTS WILL BE COMPLETED ON PARK ST. FROM LAUREL ST. TO I-84/ POPE PARK HIGHWAY #4 | Transportation Enhancements | 2010-09-27 | 2010-09-27 | 2012-01-05 |  | 3597000 | 0.230
1945 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND |  | 02 | PEDS127 | THIS PROJECT WILL CONSIST OF COMPLETING THE BIRCH ROAD BIKEWAY IN THE TOWN OF MANSFIELD | Transportation Enhancements | 2010-09-13 | 2010-09-13 | 2011-07-13 | 2011-07-06 | 251601 | 0.000
1946 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | PEDS128 | THIS PROJECT INCLUDES THE COMPLETION OF PHASE 3 OF THE FARMINGTON RIVER TRAIL IN THE TOWN OF CANTON | Transportation Enhancements | 2010-07-15 | 2010-07-15 | 2011-07-15 | 2011-07-15 | 1171200 | 1.850
1947 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | PEDS129 | THE PROJECT TO BE COMPLETED WILL BE THE HOUSATONIC RIVER GREENWAY BIKE/PEDESTRIAN TRAIL IN THE TOWN OF STRATFORD | Transportation Enhancements | 2010-06-29 | 2010-06-29 | 2010-09-27 | 2010-09-27 | 498644 | 0.189
1948 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | PEDS130 | THE PROJECT WILL INCLUDE THE REPAIR AND IMPROVEMENT OF SECTIONS OF THE I-84 /I-384 MULTI USE TRAIL IN EAST HARFORD AND MANCHESTER | Transportation Enhancements | 2010-05-21 | 2010-05-21 | 2010-08-26 | 2010-09-09 | 683991.88 | 2.600
1949 | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | PEDS133 | THIS PROJECT WILL INCLUDE THE COMPLETION OF PHASE 2 OF THE STREETSCAPE IMPROVEMENTS ALONG BARNUM AVENUE IN STRATFORD | Transportation Enhancements | 2010-09-08 | 2010-10-21 | 2011-08-17 | 2011-08-16 | 1575550 | 3.860
1950 | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | PEDS134 | THIS PROJECT WILL CONSIST OF COMPLETING THE BRIDGE STREET STREETSCAPE IN GROTON | Other | 2010-08-09 | 2010-08-09 | 2011-02-15 | 2011-03-09 | 1730000 | 0.310
1951 | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND | HARTFORD | 02 | TCSP014 | THIS PROJECT WILL INCLUDE THE CONSTRUCTION OF THE HISTORIC TALCOTTVILLE STREETSCAPE IN THE TOWN OF VERNON | Transportation Enhancements | 2010-06-28 | 2010-06-28 | 2010-09-26 | 2011-06-08 | 136118 | 0.000
1952 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009009 | This project will remove and replace hot-mix surface, hot mix patching, and profile improvements at one location in New Castle County. | Pavement Improvement | 2009-05-20 | 2009-05-20 | 2010-04-30 | 2010-03-24 | 4135646.6 | 4.940
1953 | Completed | C250 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2009010 | This project will remove and replace hot-mix surface, hot-mix patching, and curb ramp upgrades at two locations in Sussex County. | Pavement Improvement | 2009-06-03 | 2009-06-08 | 2009-10-01 | 2009-08-07 | 866353.32 | 3.519
1954 | Completed | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009011 | This project replaces the concrete median barrier on I-95 between SR 7 interchange and SR 72 overpass. | Pavement Improvement | 2009-08-13 | 2009-08-13 | 2010-01-01 | 2009-11-30 | 1643027.83 | 4.890
1955 | Completed | C200,C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX, KENT |  |  | 2009012 | This project will improve the long-term condition of the roadway by paving and rehabilitating at various locations | Pavement Improvement | 2009-04-24 | 2009-04-24 | 2010-06-01 | 2010-11-18 | 6106411.3 | 1.000
1956 | Completed | C250,C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2009013 | This project will involve full depth reclamation and hot-mix overlay | Pavement Improvement | 2010-05-10 | 2010-05-17 | 2009-12-01 | 2010-09-08 | 2107574.69 | 7.590
1957 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE |  |  | 2009014 | This project will improve the long-term condition of the roadway by milling, hot-mix patching, and overlaying at 2 locations in New Castle County. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-11-01 | 2009-10-07 | 1076873.59 | 2.630
1958 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009015 | This project will improve the long-term condition of the roadway by milling, hot-mix patching and overlaying at 4 locations in Wilmington. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2010-08-01 | 2010-09-30 | 1992237.69 | 1.000
1959 | Completed | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009016 | This project will improve the long-term condition of the roadway by milling, patching and overlayin at 3 locations in New Castle County. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-08-26 | 1201490.69 | 1.000
1960 | Completed | C220 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2009017 | This project will construct a permanent berth for the historic Lightship Overfalls, listed in the National Register of Historic Places. | Transportation Enhancements | 2010-03-09 | 2010-03-15 | 2010-06-15 | 2010-05-31 | 400000 | 0.060
1961 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009018 | This project involves the rehabilitation of interstate bridges 1-800, 1-831, 1-802, 1-809, 1-811, 1-815, 1-819N, 1-826N and 1-826S. This work includes: replacing expansion joints, joint seals, compre | Bridge Improvement | 2009-05-04 | 2009-05-04 | 2010-04-10 | 2011-02-24 | 2750725 | 1.000
1962 | Completed | C220,C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2009019 | This project involves the Boardwalk restoration - approximately 52,795 square foot section from the Henlopen Hotel to Rehoboth Avenue and the 24,300 square foot section from Laurel Street to Prospect | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2010-06-01 | 2010-06-17 | 5247665.86 | 0.050
1963 | Completed | C250,C200,C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | STATEWIDE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009020 | This project involves various intersections with different scope of works, variously involving new signal installations, reconstruction of aging infrastructure, pedestrian signal enhancements, upgrade | Other | 2009-04-21 | 2009-04-21 | 2009-08-01 | 2010-09-13 | 1535401.84 | 1.000
1964 | Completed | C220,C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009021 | This project will complete an over 4 mile loop recreational trail and will be a segment in an overall cross-county greenway trail system. | Transportation Enhancements | 2009-05-18 | 2009-05-18 | 2010-12-08 | 2010-11-01 | 632285.9 | 0.050
1965 | Completed | C220,C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009022 | This project in the New Castle Industrial Track Rail Trail covers 4.75 miles of corridor running north from Delaware Street in New Castle, across Boulden Boulevard, then crossing the the Christina Riv | Transportation Enhancements | 2009-08-31 | 2009-08-31 | 2009-12-01 | 2010-09-15 | 835845.39 | 0.510
1966 | Completed | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009023 | This project includes miscellaneous work at Bridge 1-701, 703, 703A, 704 and 705. Work includes the replacement of bearings, expansion joints, painting of structural steel, repair of spalled concrete | Other | 2009-05-04 | 2009-05-04 | 2010-12-01 | 2010-01-31 | 134734.73 | 1.000
1967 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009024 | This project involves the rehabilwork at Bridge 1-792 and 829. Work includes the replacement of bearings, expansion joints, painting of structural steel, repair of spalled concrete and replacement of | Other | 2009-04-28 | 2009-04-28 | 2010-12-01 | 2010-01-31 | 176065.92 | 1.000
1968 | Underway | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009025 | This project involves the rehabilitation of interstate bridges 1-804, 1-805, 1-810, 1-811 and 1-812. This work includes cleaning and painting the steel beams,diaphragms and bearings. | Bridge Improvement | 2009-05-08 | 2009-05-08 | 2010-04-01 |  | 2207697.39 | 1.000
1969 | Completed | C220,C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009026 | This streetscape improvement project is along Old Lancaster Pike from Valley Road to Errickson Drive. Improvements include; new sidewalks, upgrades to curb ramps, drainage modifications, decrotive cro | Transportation Enhancements | 2009-05-07 | 2009-05-07 | 2010-12-01 | 2010-09-24 | 2830690.94 | 0.380
1970 | Completed | C220,C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009027 | This project on Route 52 / Old Kennett Pike would replace current temporary traffic calming features with permanent ones. This work would improve safety for motorists and pedestrians. | Transportation Enhancements | 2009-09-29 | 2009-09-29 | 2010-09-04 | 2011-05-03 | 1843264.22 | 0.650
1971 | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009028 | This project will replace non-standard guardrail, guardrail components and end treatments as required for all state-maintained roads in New Castle County. | Safety/Traffic Management | 2009-10-21 | 2009-10-21 | 2012-08-30 |  | 505798.38 | 1.000
1972 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | STATEWIDE |  |  | 2009029 | This project will repaint existing pavement markings statewide. | Safety/Traffic Management | 2009-08-31 | 2009-08-31 | 2010-06-01 | 2009-11-17 | 1251043.23 | 107.410
1973 | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009030 | This project involves the rehabilitation of interstate bridges 1-676, 1- 717, 1-719, 1-720, 1-738, 1-739 and 1-740. Work includes the replacement of bearings, expansion seal and/or joints, painting of | Bridge Improvement | 2009-05-04 | 2009-05-04 | 2010-12-26 |  | 6132527.53 | 1.000
1974 | Completed | C200,C240 | Highway Infrastructure Investment Grant | DELAWARE | KENT | DOVER |  | 2009031 | This project will build the first phase of a DART Dover Transit Center on five acres on Water Street between Queen and West Streets. | Other | 2009-12-08 | 2009-12-08 | 2011-03-08 | 2010-12-15 | 3421196.39 | 0.110
1975 | Completed | C200,C240 | Highway Infrastructure Investment Grant | DELAWARE | KENT | DOVER |  | 2009033 | This project will rotomill, patch, and 2" hot-mox overlay at 3 locations, including miscellaneous concrete work (curb ramps) in Kent County. | Pavement Improvement | 2009-09-29 | 2009-11-09 | 2010-06-01 | 2010-10-01 | 958513.45 | 1.000
1976 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE |  |  | 2010012 | "Project includes improvements to 3 intersections in the Newark area. The improvements include extension of left turn lanes to assist traffic during the I-95 Newark toll plaza project, and other incid | Safety/Traffic Management | 2010-03-23 | 2010-04-26 | 2010-09-30 | 2010-07-16 | 1056729.18 | 0.010
1977 | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2010014 | This project entails patching and an overlay of the roadway surface for; the on and off ramps for the SR273/SR 1 interchange, the US 40/SR 1 interchange, and SR 273 from Harmony Road to Chapman Road. | Pavement Improvement | 2011-01-14 | 2011-05-27 | 2011-11-02 |  | 1368452.7 | 4.090
1978 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010024 | This project involves applying a 2" hot mix overlay on SR 24 from Drane Road to Bayfarm/Autumn Road. | Pavement Improvement | 2010-09-15 | 2010-09-27 | 2010-11-01 | 2010-11-22 | 996807.44 | 3.200
1979 | Underway | C250,C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010025 | This project entails milling, a 2 inch full-width hot-mix overlay, drainage repairs, and curb ramp retrofits on SR 1 from the Maryland line to the northern town limits of Fenwick. | Pavement Improvement | 2011-08-14 | 2011-09-19 | 2011-11-18 |  | 1392277.11 | 2.380
1980 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010026 | This project entails P.C.C. patching and a 2 inch full-width hot-mix overlay on US 113 northbound and southbound from Oak Drive to just south of Wood Branch Road. | Pavement Improvement | 2011-03-01 | 2011-03-01 | 2011-06-30 | 2011-06-29 | 2287200.83 | 9.330
1981 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010027 | This project entails P.C.C. patching and a 2 inch full-width hot-mix overlay on SR 9/US 404 (Lewes-Georgetown Highway) from Gravel Hill Road to Sweetbriar Road. | Pavement Improvement | 2011-03-03 | 2011-03-21 | 2011-05-10 | 2011-05-31 | 1803557.6 | 5.320
1982 | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2010038 | This project entails Patching, mill and overlay the roadway surface, retrofit curb ramps, extend two left turn lanes at the Foulk Road/Shipley Road intersection, and construct a sidewalk along the wes | Other | 2010-11-01 | 2010-11-01 | 2011-07-31 |  | 523875.28 | 3.590
1983 | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010043 | This project entails removing areas of corrosion, the existing coating system, and then applying a new coating system to all of the structural steel on the following bridges; Rehoboth Blvd over Mispil | Bridge Improvement | 2011-04-15 | 2011-04-25 | 2011-10-29 |  | 897048 | 0.086
1984 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | KENT | DOVER |  | K007007 | This project involves installation of a second northbound US 13 left turn lane onto westbound SR 8. The southbound US 13 turn lane will be extended 150 feet to the north to allow additional storage f | Pavement Improvement | 2010-10-14 | 2010-10-22 | 2010-11-10 | 2010-11-14 | 474159.81 | 0.213
1985 | Underway | C200,C240 | Highway Infrastructure Investment Grant | DELAWARE | KENT |  |  | K195003 | This project entails realigning approximately 1500' of Wyoming Mill Road (located in Dover | New Construction | 2010-11-09 | 2011-01-05 | 2011-12-04 |  | 2255891.28 | 0.860
1986 | Completed | C200 | Highway Infrastructure Investment Grant | DELAWARE | KENT | DOVER |  | K356011 | This project improves saftey by channelizing the median at the intersection of SR 10 and Sorghum Mill Road to accommodate eastbound and westbound SR 10 left-turns. | Safety/Traffic Management | 2009-06-17 | 2009-07-20 | 2009-11-01 | 2009-08-24 | 218880.81 | 0.150
1987 | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | N003010 | This project involves a 4" Cold In-Place Recycling with 2" overlay on SR 273 from Chapman Road to SR 7. | Pavement Improvement | 2010-08-19 | 2010-08-19 | 2010-12-28 |  | 2019318.05 | 1.490
1988 | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | N011027 | This project entails a 2 inch profile milling, hot-mix patching, 2 inch warm-mix asphalt Type C overlay on Kirkwood Highway from SR 7 to Prices Corner just west of SR 141 interchange. | Pavement Improvement | 2011-02-03 | 2011-02-03 | 2011-10-06 |  | 2114110.86 | 1.720
1989 | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | WILMINGTON (NJ-MD-PA) |  | N024001 | This project will elevate the roadway, improve shoulders, underground utilities, pave and restripe the hot mix pavement on Market Street from "A" Street to just north of the Market/Walnut St split. | Pavement Improvement | 2009-04-22 | 2009-04-22 | 2012-07-17 |  | 8701733.85 | 1.000
1990 | Underway | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | N056038 | This project entails constructing two highway speed EZ Pass Lanes in both the Northbound and Southbound directions of the Newark Toll Plaza located on I-95 near the DE/MD State Line. | New Construction | 2009-04-17 | 2009-04-17 | 2011-12-01 |  | 39404555.85 | 2.600
1991 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | N059036 | This project will mill and resurface southbound I-95 from the Wilmington Viaduct to just south of the SR 141 interchange. | Pavement Improvement | 2009-04-24 | 2009-04-24 | 2009-12-01 | 2009-11-09 | 2633869.21 | 2.830
1992 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | WILMINGTON (NJ-MD-PA) |  | N397001 | "This project will replace the existing corrugated metal pipes with a double cell precast concrete box culvert. It also will reconstruct the roadway approaches, place guardrail as required, and place | Bridge Replacement | 2010-04-06 | 2010-04-07 | 2010-11-01 | 2010-11-22 | 868157.55 | 0.023
1993 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE |  |  | N438002 | This project will expand the park & ride on along SR 299, west of SR 1. | Other | 2009-06-05 | 2009-06-05 | 2010-05-30 | 2010-04-30 | 932672.49 | 0.290
1994 | Completed | C250 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | S020003 | This project will involve hot-mix patching and 3 1/2" overlay at one location in Sussex County. | Pavement Improvement | 2009-07-08 | 2009-07-20 | 2009-10-01 | 2009-09-16 | 1523946.62 | 5.090
1995 | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | S584003 | This project improves the railroad crossing at SR 404 and Newton Road by installing automatic gates, updating the cantilever lights and controller, and replace pre-cast concrete surface. | Other | 2009-06-08 | 2009-10-19 | 2010-04-01 | 2009-10-30 | 362333.6 | 1.000
1996 | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 1108027 | REPLACEMENT OF THE NEW YORK AVENUE BRIDGE WHICH CROSSES OVER METRO, AMTRACK AND CSX RAILROAD TRACKS | Bridge Improvement | 2009-09-22 |  |  |  | 25823004.7 | 0.100
1997 | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 1121013 | Rehabilitation of Sherman Avenue NW from Florida Avenue to Park Road. Reconfiguration of roadway, widening sidewalk, relocation and upgrading traffic signals, upgrading street lights, construction of | Pavement Improvement | 2010-08-04 |  |  | 2012-09-18 | 1598787 | 0.900
1998 | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 1300015 | CONSTRUCTION WILL INCLUDE SIDEWALK, CURB AND GUTTER, PAVING T, NEW STREETLIGHTS, TRAFFIC SIGNALS, SAFETY IMPROVEMENTS AND LANDSCAPING ALONG PENNSYLVANIA AVENUE FROM THE SOUSA BRIDGE TO SOUTHERN AVENUE | Pavement Improvement | 2009-11-30 |  |  |  | 19553626.19 | 1.400
1999 | Completed | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3000049 | THIS PROJECT IS FOR UPGRADES TO TRAFFIC SIGNALS, STREETLIGHTS, CURB, GUTTER, SIDEWALK WIDENING, AND LANDSCAPING, ALONG WITH AN IMPROVEMENT TO THE STORM SEWERS. THESE IMPORVEMENTS WILL BE COMPLETED ON | Pavement Widening | 2009-10-26 |  |  | 2010-09-20 | 3629384.29 | 0.250
2000 | Underway | C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3000050 | THIS PROJECT IS MAINLY TO REPAVE THE ROADWAY; ALSO MINOR IMPROVEMENTS WILL BE DONE ALONG VARIOUS ROADWAYS WITHIN THE HISTORIC DUPONT CIRCLE BUSINESS DISTRICT | Pavement Improvement | 2009-10-26 |  |  |  | 5383959.4 | 0.480
2001 | Completed | C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3105006 | RECONSTRUCT/RESURFACE ROADWAY, SIDEWALK, CURB, GUTTER AND WHEELCHAIR RAMPS. UPGRADE STREETLIGHT AND TRAFFIC SIGNALS. REPLACE WATER MAIN AND LANDSCAPING .ALONG 18TH STREET, FROM FLORIDA AVENUE TO MASSA | Pavement Improvement | 2009-11-15 |  |  | 2010-12-07 | 5826764.7 | 0.530
2002 | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3207003 | REPLACEMENT OF THE EASTERN AVENUE BRIDGE THAT CROSSES OVER KENNILWORTH AVENUE | Bridge Improvement | 2009-11-29 |  |  |  | 4744844.75 | 0.100
2003 | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3207004 | REPLACEMENT OF THE EASTERN AVENUE BRIDGE THAT CROSSES OVER KENNILWORTH AVENUE | Pavement Improvement | 2009-11-13 |  |  |  | 6237520.22 | 0.100
2004 | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3208006 | Construct improvements to sidewalks, curbs, gutters, streets, tree boxes, replace street trees and install other streetscape elements. Construct facilities to improve reliability and safety of transi | Pavement Improvement | 2010-11-15 |  |  |  | 9201213
2005 | Underway | C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 4116001 | RECONSTRUCT THE ROADWAY AND ADD NEW SIDEWALKS ALONG WESTERN AVENUE FROM CHESTNUT STREET TO OREGON AVENUE IN NORTHWEST DC | Pavement Improvement | 2010-01-26 |  |  |  | 2945683.34 | 0.520
2006 | Underway | C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888323 | THE WORK WILL INCLUDE UPGRADING OF STREETLIGHTS, WHEELCHAIR RAMPS, PLANTING TREES AS WELL AS REPAIRING SIDEWALKS AND GUTTERS AND AND REPAVING THE ROADWAY. THIS WORK WILL OCCUR ALONG 25 BLOCKS OF TH | Safety/Traffic Management | 2009-08-10 | 2009-09-17 |  |  | 6611873.89 | 1.360
2007 | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888327 | INSTALL BATTERY BACKUP POWER SUPPLY FOR CRITICAL TRAFFIC LIGHTS THROUGHOUT THE CITY TO PROVIDE UP TO 8 HOURS OF POWER. | Safety/Traffic Management | 2010-01-01 |  |  |  | 1751131.58
2008 | Underway | C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888328 | REPAVING OF SECTIONS OF THE INTERSTATE HIGHWAY IN DC | Pavement Improvement | 2009-04-24 | 2009-04-24 |  |  | 999999.84 | 14.140
2009 | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888329 | IMPROVE STREETLIGHTS ALONG THE DALECARLIA PARKWAY AND BLADENSBURG ROAD | Safety/Traffic Management | 2009-04-24 | 2009-04-24 |  |  | 4845806.11 | 12.640
2010 | Completed | C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888332 | IMPROVE PEDESTRIAN FACILITIES THAT SERVICE NEIGHBORHOOD SCHOOLS | Transportation Enhancements | 2010-01-07 | 2010-01-07 |  | 2012-01-07 | 2593767.6
2011 | Completed | C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888339 | The work consists of resurfacing roadways along various locations, citywide. In areas of existing asphalt concrete surface, the work will consists of pavement milling to a depth of one (1) to two (2) | Pavement Improvement | 2010-06-02 |  |  | 2011-06-02 | 13836556.17
2012 | Completed | C220,C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888341 | The work consists of installation of new sidewalk or replacement of defective sidewalk along various locations citywide. The sidewalk may be concrete or brick and will be installed per DC Standards. | Transportation Enhancements | 2010-06-02 |  |  | 2011-06-02 | 5111668.72
2013 | Completed | C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888362 | Project implements citywide vehicle detection stations. Determine number of vehicles passing through various permanent count stations, occupancy, speed and classification of vehicles. | Safety/Traffic Management | 2010-11-15 |  |  | 2010-05-15 | 2812250.34
2014 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | Multiple | 1301034 | RESURFACING SR-710/SW WARFIELD F ROM W OF ML KING BLVD. TO W OF VAN BUREN AVE (0001.072 MILES) IN MARTIN COUNTY, FLORIDA. | Pavement Improvement | 2011-02-17 | 2011-03-04 |  | 2011-11-11 | 174620 | 1.072
2015 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA001 | "This Okaloosa County project will improve safety at the existing intersection of State Road 85 South and State Road 123, near the Northwest Florida Regional airport, by providing a flyover ramp for m | Pavement Widening | 2000-12-05 | 2009-07-01 | 2012-06-12 |  | 29689016 | 1.241
2016 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | SANTA ROSA | PENSACOLA | 01 | ARRA002 | This Santa Rosa County project will widen the existing two-lane roadway to four with bike lanes and sidewalks to improve safety and relieve congestion. | Pavement Widening | 2001-04-02 | 2009-07-20 | 2012-03-28 |  | 6916839 | 0.984
2017 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA003 | "This Leon County project will add lanes to Capital Circle SE, relieve congestion and improve safety along the roadway." | Pavement Widening | 2010-10-22 | 2010-10-22 | 2012-06-13 |  | 8300000 | 1.130
2018 | Underway | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | BAY | PANAMA CITY | 02 | ARRA004 | Bay County is building a new bridge over Grand Lagoon for vehicles and pedestrians to improve safety and relieve congestion on Thomas Drive in Panama City Beach. | Bridge Improvement | 2009-09-28 | 2009-09-28 | 2011-03-22 |  | 12802328 | 0.822
2019 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA005 | Barrier walls and culverts will be installed on this Leon County safety improvement project to allow wildlife to pass under the road and improve driver safety along this roadway. | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-31 | 2010-10-05 | 3085365 | 1.074
2020 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA006 | "Franklin County will construct approximately 2,500 feet of five-foot wide sidewalk along Bluff Road in Apalachicola to improve pedestrian safety." | Transportation Enhancements | 2009-11-16 | 2009-11-16 | 2010-02-13 | 2010-01-29 | 116145 | 0.737
2021 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17 | ARRA007 | The City of Hallandale Beach will improve pedestrian safety by installing brick pavers and stamped concrete crosswalks at various locations on West Hallandale Beach Boulevard. | Transportation Enhancements | 2010-02-03 | 2010-04-01 | 2010-06-30 | 2010-09-17 | 234530 | 1.937
2022 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA010 | FDOT will build a new high level bridge over the south fork of the St. Lucie River and the Okeechobee Waterway between Palm City and Stuart to ease congestion and provide faster evacuation from the co | New Bridge Construction | 2009-08-19 | 2009-08-19 | 2012-06-16 |  | 72255919 | 1.420
2023 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 22 | ARRA011 | "The City of Wilton Manors will replace deteriorating pavement, build new sidewalks and bike lanes and plant landscaping to enhance N.E. 15th Avenue." | Transportation Enhancements | 2010-03-16 | 2010-03-16 | 2010-06-16 | 2010-06-16 | 185852 | 0.010
2024 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 23 | ARRA012 | "The City of Fort Lauderdale will improve pedestrian safety by building paved parking, adding sidewalks, installing pedestrian lighting and enhancing landscaping at various locations on NW 7 Street, N | Transportation Enhancements | 2010-06-15 | 2010-06-30 | 2010-10-31 | 2011-05-24 | 500000 | 1.154
2025 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 19 | ARRA013 | The City of Deerfield Beach will improve access to the west entrance of the Deerfield Beach train station that serves Tri-Rail (commuter) and Amtrak customers by building a sidewalk and a pedestrian p | Transportation Enhancements | 2009-12-07 | 2010-01-04 | 2010-08-31 | 2010-08-19 | 359765
2026 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 21 | ARRA014 | "The City of Pembroke Pines will build new sidewalks at several locations along Pembroke Road and 196th Avenue to provide pedestrian access between major roads, subdivisions , schools, shops and to pr | Transportation Enhancements | 2009-12-07 | 2009-12-14 | 2010-04-30 | 2010-05-18 | 519214 | 0.986
2027 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | Multiple | ARRA015 | The City of Ft. Pierce will enhance bicyclist and pedestrian safety by improving three miles of bike lanes and sidewalk on Oleander Boulevard/Sunrise Boulevard from Virginia Avenue to Ohio Avenue. | Transportation Enhancements | 2009-12-31 | 2009-12-31 | 2011-06-30 |  | 646462 | 0.485
2028 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | WEST PALM BEACH | 22 | ARRA016 | Palm Beach County will provide access to bicyclists and pedestrians through the Cypress Creek Natural Area beginning at Indiantown Road West at Jupiter Farms Road by building 2.1 miles of shared-use p | Transportation Enhancements | 2010-11-29 | 2010-11-29 | 2011-04-15 | 2011-07-28 | 458519 | 2.017
2029 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 22 | ARRA017 | The City of Lighthouse Point will build sidewalks and install pedestrian lighting to improve safety on N.E. 44 Street. | Transportation Enhancements | 2010-01-18 | 2010-01-26 | 2010-07-14 | 2010-07-14 | 160000 | 0.212
2030 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA018 | Indian River County will plant additional landscaping to enhance the median of 58th Avenue for 3.05 miles from Oslo Road to 16th Avenue in southern Indian River County. | Transportation Enhancements | 2010-01-04 | 2010-01-06 | 2010-04-16 | 2010-04-22 | 237266 | 3.050
2031 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA019 | Martin County will provide access for bicyclists and pedestrians by building a one mile-long shared-use path from S.E. Grafton Avenue to Seabranch Preserve State Park south of Stuart. | Transportation Enhancements | 2010-04-26 | 2010-04-26 | 2010-07-27 | 2010-07-27 | 172369 | 0.931
2032 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 16 | ARRA020 | The City of Port St. Lucie will add 0.6 miles of sidewalk to improve pedestrian safety on the east side of California Boulevard from Heatherwood Boulevard to Fairway Isles. | Transportation Enhancements | 2010-01-21 | 2010-02-01 | 2010-03-31 | 2010-04-01 | 48189 | 0.611
2033 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | WEST PALM BEACH | Multiple | ARRA021 | Palm Beach County will provide safe access for bicyclists and pedestrians on the eastern levee of the South Florida Water Management drainage canal in the City of Palm Beach Gardens and unincorporated | Transportation Enhancements | 2010-03-01 | 2010-03-08 | 2010-11-03 | 2011-03-19 | 750000
2034 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | Multiple | ARRA022 | "FDOT will improve safety for motorists by replacing the 56-year old structurally deficient Juanita Street Bridge over Taylor Creek in Fort Pierce, as well as improve bicyclist and pedestrian safety b | Bridge Improvement | 2010-04-05 | 2010-04-13 | 2011-02-15 | 2011-03-22 | 1155082 | 0.102
2035 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 16 | ARRA023 | The City of Port St. Lucie will improve a 2.3-mile segment of Westmoreland by rebuilding the road using a new type of pavement that will wear longer and reduce the need for repairs. | Pavement Improvement | 2009-12-31 | 2010-01-01 | 2010-05-28 | 2010-06-28 | 832875 | 2.396
2036 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 23 | ARRA024 | "The City of Fort Pierce will rebuild 13th Street from Orange Avenue to Avenue D using a new type of pavement that will last longer and reduce the need for repairs, reduce flooding by installing a new | Pavement Improvement | 2010-07-12 | 2010-08-02 | 2011-03-08 | 2010-11-23 | 879800 | 0.300
2037 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA025 | The Village of Wellington will repave and add street lights to improve 5.4 miles of Forest Hill Boulevard. | Pavement Improvement | 2010-01-12 | 2010-03-19 | 2011-01-13 | 2011-06-30 | 5221287 | 7.254
2038 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16 | ARRA026 | The Village of Royal Palm Beach will improve two miles of Royal Palm Beach Boulevard by adding sidewalks for pedestrians and resurfacing the road using a new type of pavement that will last longer and | Pavement Improvement | 2010-04-05 | 2010-04-12 | 2011-03-30 |  | 2578922 | 4.051
2039 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 22 | ARRA027 | The City of Riviera Beach will replace deteriorating pavement on 3.3 miles of A1A from U.S. 1 at Blue Heron Boulevard north to Burnt Bridge on Singer Island. | Pavement Improvement | 2010-01-12 | 2010-07-19 | 2012-01-19 |  | 4067290 | 6.688
2040 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16 | ARRA028 | FDOT will restore vehicle traffic by replacing the Tequesta Drive Bridge over the North Fork of the Loxahatchee River. The bridge was recently closed due to its unsafe condition. | Pavement Improvement | 2009-10-28 | 2010-01-05 | 2012-03-26 | 2010-12-28 | 2689633 | 0.230
2041 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 23 | ARRA029 | The City of Boynton Beach will improve 0.6 miles of Seacrest Boulevard by adding street lights and resurfacing the road using a new type of pavement that will last longer and reduce the need for repai | Pavement Improvement | 2010-01-12 | 2010-06-08 | 2011-06-07 | 2011-10-31 | 1161276 | 0.671
2042 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 19 | ARRA030 | Palm Beach County will improve 14.7 miles of Military Trail between Clint Moore Road in Boca Raton and Lake Worth Road in Lake Worth by resurfacing the existing pavement and improve pedestrian safety | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2011-06-13 | 2011-11-10 | 6925674 | 14.664
2043 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 22 | ARRA031 | "FDOT will build a new four-lane bridge between Hillsboro Boulevard/ State Road 810 in Deerfield Beach (Broward County) and S.W. 18th Street in Boca Raton (Palm Beach County), crossing over local stre | Pavement Widening | 2009-10-29 | 2010-03-11 | 2012-10-29 |  | 2574095 | 0.468
2044 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 23 | ARRA032 | "FDOT will replace aging underground sewer and water lines, add sidewalks, curbs, drainage and resurface .316 miles of Southeast 3rd Street in Belle Glade." | Pavement Improvement | 2010-01-12 | 2010-08-02 | 2011-02-19 | 2011-05-23 | 960943 | 0.316
2045 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA033 | Martin County will add a southbound right-turn lane at the intersection of State Road 707 and N.W. Wright Boulevard to ease congestion just north of the Roosevelt Bridge over the St. Lucie River in St | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2010-07-22 | 2010-07-30 | 132834 | 0.122
2046 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA034 | Martin County is replacing the deteriorating pavement on one mile of Baker Road from U.S. 1 to Savannah Road in northeastern Martin County. | Pavement Improvement | 2009-10-05 | 2009-10-12 | 2009-12-01 | 2009-12-01 | 250000 | 1.298
2047 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 23 | ARRA035 | Martin County will improve nine miles of County Road 609 from State Road 710 north of Indiantown north to County Road 714 by replacing aging pavement. | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-03-01 | 2010-03-01 | 2100000 | 9.000
2048 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA036 | FDOT will resurface County Road 507 from the Fellsmere city limits north 3.09 miles to the Indian River/Brevard County line to extend the life of the road. | Pavement Improvement | 2009-11-16 | 2009-11-16 | 2012-04-11 | 2010-05-02 | 651190 | 6.362
2049 | Underway | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | PASCO |  | 05 | ARRA037 | "In Pasco County, this project widens 2.8 miles of U.S. 41 from the existing two lanes to a four-lane divided road with medians and turn lanes to reduce congestion." | Pavement Widening | 2009-07-01 | 2009-07-11 | 2011-06-04 |  | 14745320 | 2.841
2050 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA038 | "In the City of Alachua, in northern Alachua County, a sidewalk and bike lane will be built along Northwest County Road 235A from U.S. 441 to Santa Fe High School which will improve the safety of stud | Transportation Enhancements | 2009-06-15 | 2009-06-15 | 2012-02-10 |  | 67963 | 1.000
2051 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA039 | "In Alachua County, a concrete sidewalk will be built along the north side of Southwest Eighth Avenue between Southwest 75th Street (Tower Road) and end of the road which will provide a safer place fo | Transportation Enhancements | 2009-06-15 | 2010-01-25 | 2012-02-10 |  | 90926 | 1.000
2052 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | LEVY |  | 05 | ARRA040 | "In Levy County, bike lanes will be built along both sides of State Road 320 from Manatee Springs State Park to U.S. 19 to improve recreational options for campers at the state park as well as provide | Transportation Enhancements | 2009-06-15 | 2009-11-15 | 2012-03-08 |  | 1645308 | 5.784
2053 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | 03 | ARRA041 | "In Bradford County, a 12-foot wide, 4-mile long multi-use trail will be built along the old abandoned railroad line along State Road 100 from the Clay County line to County Road 315 to provide recrea | Transportation Enhancements | 2009-06-15 | 2009-06-15 | 2012-02-10 |  | 1139142 | 4.366
2054 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA | GAINESVILLE | 06 | ARRA042 | "In Gainesville, an off-road bicycle path will be built on the abandoned railroad property alongside West Sixth Street from Southeast Second Avenue to Northwest 16th Avenue for recreation and those wh | Transportation Enhancements | 2009-08-04 | 2010-03-15 | 2010-09-15 |  | 427718 | 1.540
2055 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA | GAINESVILLE | 03 | ARRA043 | "In Gainesville, Northeast Eighth Avenue will be repaved between North Main Street (State Road 329) and Northeast Boulevard to improve the road surface." | Pavement Improvement | 2009-08-04 | 2009-12-14 | 2010-02-02 |  | 110761 | 0.311
2056 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA045 | "To promote economic development in the western area of Alachua County, a southbound turn lane will be added to U.S. 41 just south of Newberry onto Southwest 30th Avenue." | Safety/Traffic Management | 2009-06-15 | 2010-01-26 | 2012-02-10 |  | 437093 | 0.001
2057 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA | GAINESVILLE | 03 | ARRA046 | "In Gainesville, North Main Street (County Road 329) will be reconstructed from four to two lanes with a center turn between Northwest Eighth and 16th avenues which will increase safety. It will also | Pavement Improvement | 2009-06-15 | 2009-10-23 | 2012-02-10 |  | 943082 | 1.681
2058 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE |  | Multiple | ARRA047 | "Cash toll collections will be replaced with all-electronic tolling on a 21-mile segment of Florida?s Turnpike located between State Road 836 in Miami and County Line Road in Miramar.? The project wil | Pavement Improvement | 2009-09-30 | 2009-09-30 | 2011-10-03 | 2012-01-26 | 22000000 | 12.000
2059 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA048 | Southwest 122nd Street in Alachua County will be resurfaced and a five-foot paved shoulder added south of Archer Road (State Road 24) to Southwest 89th Avenue which will improve safety. | Pavement Improvement | 2009-06-15 | 2010-01-18 | 2012-02-10 |  | 402911 | 0.343
2060 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | BAKER |  | 04 | ARRA049 | "In Glen St. Mary, County Road 125 will be resurfaced from U.S. 90 to Glen Haven Lane and the culverts will be upgraded to make the roadway a safer route to drive." | Pavement Improvement | 2009-06-15 | 2009-10-15 | 2012-02-10 |  | 589224 | 1.556
2061 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | BRADFORD |  | 06 | ARRA050 | "In Bradford County, Northwest County Road 229 between State Road 16 and Northwest 55th Avenue will be repaved to improve the road surface." | Pavement Improvement | 2009-06-15 | 2009-12-14 | 2012-02-10 |  | 726641 | 2.000
2062 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | CLAY |  | 06 | ARRA051 | "In St. Johns County, County Road 214 will be resurfaced between State Road 100 and County Road 315C to improve the ride." | Pavement Improvement | 2009-06-15 | 2009-12-03 | 2012-03-17 |  | 1496913 | 6.584
2063 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | COLUMBIA |  | 04 | ARRA052 | "In western Columbia County, County Road 250 (Lake Jeffery Road) will be widened from 10 to 12-foot lanes and resurfaced from Interstate 75 to the Suwannee County line to improve the road surface." | Pavement Improvement | 2009-06-15 | 2009-10-12 | 2012-02-10 |  | 1125609 | 2.900
2064 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | COLUMBIA |  | 04 | ARRA053 | "In Lake City, County Road 129 (Northwest Lake Jeffery Road) will be resurfaced between U.S. 90 and the CSX Railroad and a crosswalk added at Parkview Baptist Church to provide additional safety on a | Pavement Improvement | 2009-06-15 | 2009-11-06 | 2012-02-10 |  | 391522 | 0.664
2065 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | DIXIE |  | 02 | ARRA054 | "In Cross City, the intersection of U.S. 19 (State Road 55) and County Road 351A will be improved by widening the intersection to allow log trucks and larger vehicles to safely turn. The road also wil | Safety/Traffic Management | 2009-06-15 | 2009-12-05 | 2012-02-10 |  | 411954 | 0.100
2066 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | MADISON |  | 04 | ARRA055 | "In Madison County, County Road 53 between Interstate 10 and Southeast Roger Sink Road will be resurfaced to improve the ride." | Pavement Improvement | 2009-06-15 | 2009-08-19 | 2012-02-10 |  | 855844 | 1.899
2067 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | 03 | ARRA056 | St. Johns Avenue will be resurfaced between State Road 19 and Palm Avenue which will improve the roadway for traffic headed toward downtown Palatka. | Pavement Improvement | 2009-08-04 | 2009-10-23 | 2010-01-26 |  | 256881 | 1.176
2068 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | Multiple | ARRA057 | Moseley Avenue in Palatka will be resurfaced from U.S. 17 to State Road 100 and the sidewalks will be repaired and made handicap-accessible to provide a safer ride for motorists and a safer way for pe | Pavement Improvement | 2009-12-15 | 2010-04-05 | 2010-07-05 |  | 309219 | 1.610
2069 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | Multiple | ARRA058 | "In Pomona Park in southern Putnam County, a new concrete sidewalk will be built between U.S. 17 and Cisco Road to provide a safer path for pedestrians." | Transportation Enhancements | 2009-08-04 | 2009-10-05 | 2009-10-20 |  | 133948 | 3.835
2070 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | 07 | ARRA059 | "In Putnam County, two culverts will be replaced on Silver Lake Drive over Devall Branch and Two Mile Creek with new concrete culverts to improve the drainage in the area." | Pavement Improvement | 2009-08-04 | 2009-10-05 | 2010-07-02 |  | 454020 | 3.440
2071 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | Multiple | ARRA060 | "In western Putnam County, a concrete sidewalk and asphalt bike path will be built along a section of County Road 315 to improve safety for pedestrians and bicyclists." | Transportation Enhancements | 2009-08-04 | 2009-10-05 | 2010-02-02 |  | 328154 | 2.082
2072 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | SUWANNEE |  | 02 | ARRA061 | "A two mile section of County Road 252 in eastern Suwannee County, between the Columbia County line and County Road 137, will be widened from 10 to 12-foot lanes and repaved to improve the road surfac | Pavement Improvement | 2009-06-15 | 2009-12-11 | 2012-02-10 |  | 878565 | 1.915
2073 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS |  | 07 | ARRA062 | "In St. Johns County, West King Street (County Road 214) between County Road 13 and 13A will have several culverts or pipes replaced and extended to help with drainage issues." | Pavement Improvement | 2009-11-23 | 2009-06-15 | 2010-08-13 |  | 339596 | 3.946
2074 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS |  | 07 | ARRA063 | "In St. Johns County, West King Street (County 214) will be widened to improve safety and the road resurfaced between County 13 and 13A to improve the ride." | Pavement Improvement | 2009-11-23 | 2009-06-15 | 2010-08-13 |  | 659249 | 7.891
2075 | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | GILCHRIST |  | 06 | ARRA064 | "In Gilchrist County, County Road 341 will be repaved between State Road 26 and the Levy County line to improve the road surface." | Pavement Improvement | 2009-06-15 | 2009-09-03 | 2012-02-10 |  | 262290 | 1.482
2076 | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | HAMILTON |  | 04 | ARRA065 | "In Hamilton County, County Road 135 between White Springs and Southeast 177th Court will be repaved to improve the road surface.." | Pavement Improvement | 2009-06-15 | 2009-09-17 | 2012-02-10 |  | 791978 | 2.900
2077 | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | LAFAYETTE |  | 02 | ARRA066 | "In Lafayette County, County Road 354 from U.S. 27 to County Road 361 will be repaved to improve the road surface." | Pavement Improvement | 2009-06-15 | 2009-09-18 | 2012-02-10 |  | 499567 | 2.707
2078 | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | LEVY |  | 05 | ARRA067 | "In Levy County, County Road 40 will be repaved between Park Street in Inglis and the Marion County line to improve the road surface and make it safer." | Pavement Improvement | 2009-06-15 | 2009-11-23 | 2012-03-08 |  | 806971 | 7.413
2079 | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU |  | 04 | ARRA068 | "In Nassau County, County Road 2 will be resurfaced between County Road 121 and the Georgia line and the Agricultural Inspection Station ramps will be repaved to improve safety for motorists." | Pavement Improvement | 2009-06-15 | 2009-10-09 | 2012-02-10 |  | 337858 | 1.381
2080 | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | Multiple | ARRA069 | "In Crescent City in southern Putnam County, a new concrete sidewalk will be built along East Grand Rondo from Central Street to County Road 308 to provide a safer route for pedestrians." | Transportation Enhancements | 2009-08-04 | 2009-10-13 | 2009-11-30 |  | 89817 | 0.100
2081 | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | TAYLOR |  | 02 | ARRA070 | "In Taylor County, County Road 14 will be resurfaced between U.S. 221 in Shady Grove and the Madison County line to provide a safer road." | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-02-10 |  | 964360 | 3.063
2082 | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | UNION |  | 04 | ARRA071 | County Road 231 in Union County will be resurfaced between the Department of Corrections Reception and Medical Center and the Bradford County line to improve the ride. | Pavement Improvement | 2009-06-15 | 2009-08-07 | 2012-02-10 |  | 458012 | 1.009
2083 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 06 | ARRA072 | "In Clay County, Peoria Road (County Road 224A) will be widened to provide a center turn lane from College Drive (County Road 224) to Moody Road to improve traffic flow. An intersection improvement wi | Safety/Traffic Management | 2009-06-15 | 2009-09-09 | 2012-03-17 |  | 796791 | 0.241
2084 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 03 | ARRA073 | "In Orange Park, an additional right turn lane will be added to Kingsley Avenue at U.S. 17 to increase the amount of traffic that can turn onto U.S. 17." | Safety/Traffic Management | 2009-06-15 | 2009-11-25 | 2012-03-17 |  | 388058 | 0.001
2085 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 06 | ARRA074 | Four lanes on Knight Boxx Road (County Road 220B) in Orange Park in Clay County will be resurfaced from Blanding Boulevard (State Road 21) to County Road 220 to provide a safer ride. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-03-17 |  | 476968 | 1.206
2086 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA075 | "In Jacksonville, for Alta Drive and New Berlin Road, the existing pavement will be resurfaced and paved shoulders added to improve the road surface between Zoo Parkway (State Road 105) and State Road | Pavement Improvement | 2009-08-20 | 2009-06-15 | 2010-09-21 |  | 3663856 | 2.012
2087 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA076 | Ninth Street in Jacksonville Beach will be improved by repairing the existing drainage system and resurfacing between Osceola Avenue and First Street. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-04-10 |  | 4198366 | 1.500
2088 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA077 | "In Fernandina Beach, North 14th Street will be resurfaced between Atlantic Avenue and Pogy Place. The bridge railing will be replaced at Egans Creek Bridge to make the crossing safer for motorists, p | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-04-10 |  | 488363 | 1.760
2089 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA078 | North Eighth Street in Fernandina Beach between Dade Street and the Port of Fernandina will be repaved to improve the road surface. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-04-10 |  | 64136 | 0.464
2090 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA079 | "In St. Augustine, West King Street or County Road 214 will be resurfaced between County Road 13 and Palmer Avenue to provide a safer road." | Pavement Improvement | 2009-11-23 | 2009-06-15 | 2010-08-13 |  | 1507822 | 14.979
2091 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA080 | "To improve capacity and safety at the Interstate 95/State Road 207 interchange in St. Johns County, the northbound and southbound ramps will be widened and a turn lane will be added for westbound tra | Safety/Traffic Management | 2009-06-15 | 2009-09-21 | 2012-02-10 |  | 589377 | 0.001
2092 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA081 | "In St. Augustine, concrete sidewalks will be provided along Del Monte, Varella and Durbin Creek Boulevard to increase safety for pedestrians." | Transportation Enhancements | 2009-08-20 | 2009-06-15 | 2010-06-19 |  | 386268 | 5.968
2093 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA082 | "North of St. Augustine, a new traffic signal system along County Road 210 and Racetrack Road between U.S. 1 and County Road 16A will improve traffic flow along county roads." | Safety/Traffic Management | 2009-08-20 | 2009-11-16 | 2010-04-15 |  | 271115 | 16.160
2094 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA083 | "In Citrus County, a new multi-use path is being built along U.S. 19 in Crystal River between NW 19th Street and W. State Park Street to provide an area for both bicyclists and pedestrians to travel s | Transportation Enhancements | 2009-09-04 | 2009-09-14 | 2009-11-30 | 2009-11-30 | 170000 | 0.477
2095 | Completed | C250,C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA084 | "In Citrus County, this project repaves 2.4 miles of Fort Island Trail from North Palm Springs Terrace to U.S. 19/Suncoast Boulevard to improve the road surface." | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2010-03-13 | 2010-03-10 | 313348 | 1.461
2096 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA085 | "In Citrus County, this project repaves 1.5 miles of Ozello Trail from U.S. 19 to Winterset Avenue to improve the road surface." | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-02-27 | 2010-02-06 | 172060 | 1.455
2097 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA086 | "In Citrus County, to enhance the ride ability of the roadway, this project resurfaces 2.7 miles of Croft Ave. from State Road 44 to north of Harley Street." | Pavement Improvement | 2009-11-09 | 2009-11-11 | 2010-02-08 | 2010-02-06 | 367829 | 2.726
2098 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA087 | "In Citrus County, this project repaves one mile of Turner Camp Road from Ella Avenue to Twin Lakes Drive to improve the road surface." | Pavement Improvement | 2009-11-12 | 2009-11-18 | 2010-02-09 | 2010-02-11 | 140757 | 1.530
2099 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA088 | "In Citrus County, this project repaves six miles of Cardinal Street from U.S. 19 to County Road 491 (Lecanto Highway) to improve the road surface." | Pavement Improvement | 2009-12-14 | 2010-01-18 | 2010-07-09 | 2010-06-25 | 709410 | 6.151
2100 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA089 | "In Citrus County, this project resurfaces 2.5 miles of County Road 491 from State Road 44 to County Road 486 due to the poor condition of the road." | Pavement Improvement | 2009-11-22 | 2009-11-22 | 2010-02-19 | 2010-02-16 | 478855 | 2.515
2101 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA090 | FDOT will improve 2.69 miles of Barber Street in Sebastian by repaving the road and installing a new drainage system. | Pavement Improvement | 2009-11-16 | 2009-11-16 | 2012-04-11 | 2011-02-04 | 1806890 | 2.686
2102 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA091 | "In Citrus County, due to the poor condition of the road, this project resurfaces 6.8 miles of County Road 491 from Pine Ridge Boulevard to State Road 200." | Pavement Improvement | 2010-01-04 | 2010-01-13 | 2010-04-03 | 2010-03-19 | 777534 | 7.018
2103 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA093 | "In Citrus County, this project repairs approximately 200 feet of the Withlapopka Causeway shoulders to prevent further erosion along the canal." | Pavement Improvement | 2010-03-29 | 2010-04-05 | 2010-10-24 | 2010-10-18 | 594025 | 0.216
2104 | Completed | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA094 | "In Citrus County, this project repaves 5.6 miles of County Road 480 (Stagecoach Road) from County Road 491 (Lecanto Highway) to County Road 581 (Pleasant Grove Road) to improve the road surface." | Pavement Improvement | 2009-11-09 | 2009-11-10 | 2010-03-06 | 2010-02-20 | 992735 | 5.722
2105 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA095 | "In Citrus County, this project adds a new traffic signal and a right turn lane on State Road 44 at the Citrus County Landfill to ease access and minimize backups at the entrance to the landfill." | Pavement Improvement | 2009-09-15 | 2010-01-11 | 2010-07-25 | 2010-06-08 | 548534 | 0.577
2106 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA096 | "In Citrus County, this project repaves 2.4 miles of Grover Cleveland Boulevard from Tedna Terrace to County Road 491 to improve the road surface." | Pavement Improvement | 2009-12-07 | 2009-12-17 | 2010-03-06 | 2010-03-03 | 246292 | 2.403
2107 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA097 | "In Citrus County, this project repaves 1.6 miles of Halls River Road from the Halls River Bridge to Fishbowl Drive to improve the road surface." | Pavement Improvement | 2009-11-30 | 2009-12-14 | 2010-02-28 | 2010-02-28 | 115327 | 1.067
2108 | Completed | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA099 | "In eastern Hernando County, this project resurfaces 1.8 miles of Cortez Blvd (State Road 50) between U.S. 98 and the railroad tracks to the east to provide a safer ride." | Pavement Improvement | 2009-08-15 | 2009-08-31 | 2009-11-18 | 2009-11-09 | 737444 | 1.844
2109 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA100 | FDOT will resurface 3.5 miles of 20th Avenue from Oslo Road to State Road 60 in Vero Beach to extend the life of the road. | Pavement Improvement | 2009-12-11 | 2009-12-11 | 2012-04-12 |  | 2276800 | 5.543
2110 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA101 | "In Hernando County, this project repaves 2.2 miles of Mariner Boulevard from Maderia Street to Augustine Road to improve the road surface." | Pavement Improvement | 2010-01-04 | 2010-01-17 | 2010-04-23 | 2010-04-23 | 780374 | 2.204
2111 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA102 | "In Hernando County, this project repaves 0.6 miles of Spring Hill Drive from Pinehurst Drive to Deltona Boulevard to improve the road surface." | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2009-12-07 | 2009-11-23 | 277591 | 0.657
2112 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA103 | "In Hernando County, this project repaves 1.5 miles of Deltona Boulevard from State Road 50 to Northcliffe Boulevard to improve the road surface." | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2009-12-04 | 2009-11-25 | 248011 | 1.489
2113 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA104 | "In Hernando County, this project repaves 2.5 miles of Deltona Boulevard from Spring Hill Drive to Philatelic Drive to improve the road surface." | Pavement Improvement | 2010-02-14 | 2010-02-14 | 2010-06-04 | 2010-06-04 | 456863 | 2.508
2114 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA105 | "In Hernando County, this project repaves 2.8 miles of Spring Hill Drive from Mariner Boulevard to Deltona Boulevard to improve the road surface." | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-03-15 | 2010-03-10 | 856722 | 3.038
2115 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA106 | "In Hernando County, due to the poor condition of the road, this project replaces 2.1 miles of the asphalt surface on Burwell Rd. (County Road 575) and widens the 10-foot lanes to 12-foot lanes from S | Pavement Improvement | 2009-10-22 | 2009-10-22 | 2009-12-11 | 2009-11-20 | 270714 | 2.049
2116 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA107 | "In Hernando County, due to the poor condition of the road, this project resurfaces 3.8 miles of Citrus Way and widens the 11-foot lanes to 12-foot lanes from Ft. Dade Avenue to south of Centralia Roa | Pavement Improvement | 2010-01-05 | 2010-01-06 | 2010-08-15 | 2010-03-31 | 758923 | 3.826
2117 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA108 | "In Hernando County, this project repaves 1.4 miles of Yontz Road from U.S. 98 to Howell Avenue to improve the road surface." | Pavement Improvement | 2009-12-15 | 2009-12-15 | 2010-01-14 | 2010-01-21 | 265142 | 1.433
2118 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA109 | "In Hernando County, this project repaves one mile of North Avenue from Howell Avenue to Ponce de Leon Boulevard to improve the road surface." | Pavement Improvement | 2010-02-28 | 2010-03-01 | 2010-05-28 | 2010-05-28 | 241465 | 0.743
2119 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA110 | "In Hernando County, 20 miles of the asphalt surface of the Suncoast Trail is being replaced due to the poor condition of the trail." | Transportation Enhancements | 2009-08-31 | 2009-09-21 | 2010-05-21 | 2010-04-12 | 755009
2120 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HILLSBOROUGH | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 11 | ARRA113 | "In Hillsborough County, this project will add new lighting, landscaping and brick sidewalks for safety purposes on 56th Street from Temple Heights Road to east of 98th Avenue." | Transportation Enhancements | 2009-10-19 | 2009-11-23 | 2010-06-11 | 2010-06-08 | 348298 | 0.146
2121 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PASCO |  | Multiple | ARRA124 | "In Pasco County, this project builds a new three mile, eight-foot wide trail from Congress Street to Starkey Boulevard to accommodate bicyclists and pedestrians." | Transportation Enhancements | 2010-01-27 | 2010-02-08 | 2010-07-22 | 2010-06-07 | 616243
2122 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09 | ARRA129 | "In Pinellas County, this project converts the existing southbound lane of East Avenue to a trail for pedestrians and bicyclists to travel safely between Drew Street and Turner Street." | Transportation Enhancements | 2009-10-19 | 2009-10-19 | 2010-10-31 | 2010-12-22 | 304407 | 0.001
2123 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH, FL | Multiple | ARRA134 | This project is the final and largest section of the 12-part Palmetto Expressway (State Road 826) Improvement Program which consists of major construction along a 16-mile corridor. | Pavement Widening | 2009-11-13 | 2009-11-25 | 2015-01-24 |  | 89175975 | 2.979
2124 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 23 | ARRA135 | "FDOT is widening 4.35 miles of State Road 70 in western St. Lucie County to a four-lane, divided highway and adding shoulders for safety on this major cross-state business and evacuation route." | Pavement Widening | 2009-07-27 | 2009-08-03 | 2012-07-20 |  | 15816857 | 4.356
2125 | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 22 | ARRA136 | "FDOT will build a new four-lane bridge between Hillsboro Boulevard/ State Road 810 in Deerfield Beach (Broward County) and S.W. 18th Street in Boca Raton (Palm Beach County), crossing over local stre | Pavement Widening | 2009-10-29 | 2009-10-29 | 2012-10-29 |  | 38349339 | 0.567
2126 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | GULF |  | 02 | ARRA137 | This pedestrian safety project includes sidewalk and landscape improvements in the City of Port St. Joe in Gulf County. | Transportation Enhancements | 2009-10-23 | 2009-11-02 | 2010-05-01 | 2010-06-28 | 343118 | 0.297
2127 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA138 | This project will repair the existing sidewalk and construct additional sidewalk near Bonifay Middle School to improve pedestrian safety in Holmes County. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 89020 | 0.239
2128 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA139 | The City of Chipley will construct approximately 900 feet of five-foot wide sidewalk along State Road 77 to improve pedestrian safety in Washington County. | Transportation Enhancements | 2009-10-06 | 2009-10-06 | 2010-02-03 | 2010-01-21 | 49922 | 0.172
2129 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA140 | Five-foot wide sidewalks along various streets within the city limits of Midway will be constructed to improve pedestrian safety in Gadsden County. | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2010-03-19 | 448766 | 1.350
2130 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN | TALLAHASSEE | 02 | ARRA141 | A five-foot wide sidewalk along State Road 267 in the City of Quincy has been constructed to improve pedestrian safety in Gadsden County. | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2009-11-02 | 62002 | 0.272
2131 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA142 | "Franklin County will construct approximately 1,600 feet of five-foot wide sidewalk along Franklin Boulevard to improve pedestrian safety." | Transportation Enhancements | 2009-11-09 | 2009-11-09 | 2010-02-07 | 2010-03-31 | 53320 | 0.139
2132 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA143 | Jackson County will construct a five-foot wide sidewalk along Riverforest Road to improve pedestrian safety. | Transportation Enhancements | 2009-10-15 | 2009-10-15 | 2010-02-05 | 2010-03-23 | 42023 | 0.538
2133 | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | COLLIER | NAPLES | 14 | ARRA144 | Build a second two-lane bridge next to the existing Jolley Bridge to give drivers a four-lane bridge that connects Marco Island to U.S. 41 and reduces congestion during heavy travel times. | New Bridge Construction | 2002-11-19 | 2009-09-21 | 2012-03-16 |  | 27661293 | 0.783
2134 | Underway | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | POLK | LAKELAND | Multiple | ARRA145 | Construct a new two-lane road to provide a direct connection between State Road 33 and the Pace Road Interchange at the Polk Parkway for easy access to the new University of South Florida Polytechnic | New Construction | 2009-12-29 | 2010-01-02 | 2012-05-02 |  | 37049661 | 5.200
2135 | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA147 | "Construct Metro Extension (State Road 739), a new six-lane road that connects U.S. 41 and Six Mile Cypress Parkway in Lee County and relieves heavy traffic on U.S. 41. It will also serve as an altern | New Construction | 2009-04-29 | 2009-07-25 | 2012-02-10 |  | 34693474 | 2.772
2136 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA148 | Widen U.S. 301 in Sarasota from four to six lanes to relieve roadway congestion. Improvements to drainage and sidewalks will also enhance safety in the area. | Pavement Widening | 2009-08-28 | 2009-09-16 | 2012-03-28 |  | 9702114 | 2.007
2137 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA149 | Install communications devices at 88 intersections throughout Manatee County and connect them to the Manatee Traffic Management Center to improve traffic congestion and emergency response times. | Safety/Traffic Management | 2009-09-30 | 2009-10-13 | 2012-03-21 |  | 6106640
2138 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA151 | "Replace the old Cape Haze Drive bridge over Amberjack Cove Waterway in Charlotte County with a new bridge with wider lanes, shoulders and sidewalks." | Pavement Improvement | 2009-09-09 | 2009-11-02 | 2012-03-11 | 2010-06-08 | 1064311 | 0.241
2139 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE | PUNTA GORDA | Multiple | ARRA152 | "Construct intersection improvements at State Road 776/Coliseum Boulevard in Charlotte County, including new turn lanes and traffic signals to move traffic more efficiently through this area." | Pavement Improvement | 2009-09-29 | 2009-09-29 | 2012-03-29 | 2010-11-05 | 549865 | 0.207
2140 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA153 | Add two new right turn lanes on Veterans Boulevard to improve traffic flow at the Murdock Circle intersection in Charlotte County. | Pavement Improvement | 2009-09-29 | 2009-09-29 | 2012-03-29 | 2010-11-05 | 229566 | 0.010
2141 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA154 | Lengthen the left turn lane on State Road 776 at the Oriole Boulevard intersection to improve traffic movement through the intersection in Charlotte County. | Pavement Improvement | 2009-09-29 | 2009-09-29 | 2012-03-29 | 2010-11-05 | 100009 | 0.172
2142 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | DE SOTO |  | 13 | ARRA155 | Pave five miles of County Road 760 from County Road 769 to U.S. 17 in Desoto County to improve the road surface. | Pavement Improvement | 2009-09-16 | 2009-10-24 | 2012-03-14 | 2010-06-11 | 1401252 | 3.170
2143 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | GLADES |  | 16 | ARRA156 | Pave County Road 720 in Glades County from the Hendry County line to five miles west to improve the road surface. | Pavement Improvement | 2009-09-21 | 2009-11-25 | 2012-03-22 | 2010-09-01 | 1899401 | 5.000
2144 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA157 | Resurface Main Street (County Road 664) in the city of Bowling Green from Doc Coil Road to east of U.S.17 to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2009-09-21 | 2009-10-24 | 2012-03-21 | 2010-05-02 | 693638 | 3.500
2145 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | HENDRY |  | Multiple | ARRA158 | Pave County Road 832 in Hendry County from State Road 29 to nine miles east to improve the road surface. | Pavement Improvement | 2009-07-22 | 2009-09-15 | 2012-02-24 | 2010-10-29 | 1465030 | 9.000
2146 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA159 | Resurface Memorial Drive (County Road 17A) in Highlands County from Sebring Parkway to Manatee Drive to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2012-03-23 | 2010-03-26 | 365735 | 2.268
2147 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA160 | Resurface County Road 621 in Highlands County from U.S. 27 to Crocket Road to improve the surface of this heavily traveled road. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2012-03-23 | 2010-02-19 | 193020 | 0.600
2148 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA161 | Add sidewalks along West Main Street from Booker T. Washington Avenue to Chester Avenue in the City of Bowling Green to improve safety. | Transportation Enhancements | 2009-09-21 | 2010-01-19 | 2012-03-21 | 2010-02-22 | 73701
2149 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | DE SOTO |  | 13 | ARRA162 | "Construct a sidewalk along Dr. Martin Luther King, Jr. Street from Booker T. Washington Avenue to U.S. 17 to enhance safety for bicyclists and pedestrians." | Transportation Enhancements | 2009-09-16 | 2009-11-22 | 2012-03-14 | 2009-12-23 | 85504
2150 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HENDRY |  | 16 | ARRA163 | Construct a new sidewalk along State Road 29 from the RV park to the post office in the Felda community in Hendry County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 2009-09-09 | 2009-09-09 | 2010-03-28 | 2010-08-04 | 398576 | 2.077
2151 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | OKEECHOBEE |  | 16 | ARRA164 | "Add sidewalks along Southwest 7th Avenue, Southwest 9th Street and Southwest 11th Avenue in the City of Okeechobee to improve pedestrian safety." | Transportation Enhancements | 2009-09-21 | 2010-02-15 | 2012-03-16 | 2010-04-27 | 164378
2152 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | POLK |  | 12 | ARRA165 | "Design and build a 12-foot wide paved trail between State Road 17 and 4th Street as an extension of the existing Lake Wales Trail, improving the connectivity of walking trails in Polk County." | Transportation Enhancements | 2009-09-10 | 2009-12-07 | 2012-03-16 | 2010-03-05 | 136677
2153 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | POLK |  | 12 | ARRA166 | Build a 12-foot wide paved trail connecting the existing Fort Fraser Trail just south of the University of South Florida/Polk State College to the Circle B Bar Reserve located on S.R. 540 to improve t | Transportation Enhancements | 2009-09-10 | 2009-09-29 | 2012-03-16 | 2010-03-10 | 457967
2154 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE | PUNTA GORDA | 16 | ARRA167 | "Construct a paved pathway from Retta Esplande to Olympia Avenue in Punta Gorda to connect parks, schools, and the riverfront and give walkers and bicyclists a recreational route for exercise." | Transportation Enhancements | 2010-02-01 | 2010-02-08 | 2010-06-01 | 2010-10-07 | 417952
2155 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | COLLIER | NAPLES | 25 | ARRA168 | "Construct a paved pathway along Bald Eagle Drive on Marco Island to connect the town center, residential areas, and schools and give walkers and bicyclists a recreational route for exercise." | Transportation Enhancements | 2009-08-19 | 2009-08-24 | 2009-11-22 | 2010-01-04 | 380719 | 1.185
2156 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA169 | Resurface Kenilworth Boulevard from Lakeview Drive to Persimmon Avenue to improve the surface of this heavily traveled road in Highlands County. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2012-03-23 | 2010-03-26 | 153197 | 0.400
2157 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA170 | Add landscaping along State Road 789 through the coastal city of Long Boat Key to enhance the roadway features of this beach community. | Transportation Enhancements | 2009-09-30 | 2009-10-22 | 2012-03-26 | 2010-06-30 | 232666 | 4.557
2158 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA171 | Add landscaping along State Road 789 through the coastal city of Bradenton Beach to enhance the roadway features of this beach community. | Transportation Enhancements | 2009-09-30 | 2009-10-22 | 2012-03-26 | 2010-06-30 | 127040 | 0.902
2159 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA172 | Resurface County Road 17 (S. Main Street) in the town of Lake Placid from Poinsettia Street to West Interlake Boulevard to improve the surface of this heavily traveled road. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2012-03-23 | 2010-02-19 | 204872 | 0.499
2160 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA173 | Add sidewalks along Gulf Front Park from Palm Avenue to Willow Avenue in the City of Anna Maria to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-11-09 | 2012-03-26 | 2009-11-30 | 16250
2161 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA174 | Resurface Home Avenue from Sebring Parkway to State Road 17 (North Gate Drive) to improve the surface of this heavily traveled road in Highlands County. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2012-03-23 | 2010-03-26 | 46730 | 0.168
2162 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA176 | Add sidewalks along North Bay Boulevard from Hibiscus Street to North Shore Drive in the City of Anna Maria to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-11-09 | 2012-03-26 | 2009-12-12 | 42677
2163 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA177 | Add sidewalks along Gulf Drive from Spring Avenue to Pine Avenue in the City of Anna Maria to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-11-09 | 2012-03-26 | 2009-11-30 | 6679
2164 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA178 | Replace a short bridge in Lee County on Cortez Boulevard near Fort Myers High School with a new bridge that has sidewalks. | Pavement Improvement | 2009-10-28 | 2009-12-06 | 2010-01-28 | 2010-03-17 | 247843 | 0.001
2165 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | 13 | ARRA179 | Add sidewalks along North and South Gulf Drive from 57th Street to 84th Street in the City of Holmes Beach to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-09-29 | 2012-03-26 | 2009-11-11 | 9994 | 1.203
2166 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA180 | "Construct a new culvert on Carrel Road to replace an older, rough-riding surface." | Pavement Improvement | 2009-11-23 | 2010-01-18 | 2010-03-23 | 2010-03-05 | 94959 | 0.001
2167 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA181 | Add sidewalks along Holmes Boulevard from 54th Street to 66th Street in the City of Holmes Beach to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-09-28 | 2012-03-26 | 2009-11-05 | 22605
2168 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | 13 | ARRA182 | Add sidewalks along Palm Drive from 66th Street to 85th Street in the City of Holmes Beach to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-09-29 | 2012-03-26 | 2009-11-11 | 10441
2169 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | 13 | ARRA183 | Add sidewalks along 85th Street from Gulf Drive to Marina Drive in the City of Holmes Beach to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-09-29 | 2012-03-26 | 2009-11-11 | 11333
2170 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA184 | Add sidewalks along 21st Avenue from 26th Street West to 27th Street West in Bradenton to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-09-30 | 2012-03-26 | 2009-11-10 | 8532
2171 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA185 | Add sidewalks along 27th Street from 22nd Avenue West to 23rd Avenue West in Bradenton to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-09-30 | 2012-03-26 | 2009-11-10 | 21178
2172 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA186 | Add sidewalks along 23nd Avenue from 26th Street West to 27th Street West in Bradenton to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-09-30 | 2012-03-26 | 2009-11-10 | 7133
2173 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA187 | Add sidewalks along 21st Avenue from 30th Street West to 34th Street West in Bradenton to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-09-30 | 2012-03-26 | 2009-11-10 | 53232
2174 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA189 | Add sidewalks along Thunderbird Road from Lotus Avenue to Red Pine Drive in the City of Sebring to improve pedestrian safety. | Transportation Enhancements | 2009-09-15 | 2010-01-04 | 2012-03-23 | 2010-04-16 | 111538
2175 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA190 | Add paved shoulders that will be designated bike lanes on Buckingham Road from State Road 82 to Neal Road in Lee County to enhance safe riding for cyclists. | Pavement Improvement | 2010-01-14 | 2010-02-16 | 2010-06-14 | 2010-11-04 | 236229 | 1.800
2176 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA191 | Add a second left turn lane on Daniels Parkway westbound at Bell Tower Boulevard in Lee County to improve traffic flow at the intersection. | Pavement Improvement | 2010-03-01 | 2010-03-10 | 2010-09-27 | 2011-02-09 | 419838 | 0.443
2177 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA192 | "Add a bicycle lane on Summerlin Road in Lee County at the toll plaza to give walkers, runners, and bicyclists a connection to the Sanibel causeway bridge." | Transportation Enhancements | 2010-02-08 | 2010-02-08 | 2010-12-31 | 2010-11-04 | 319262
2178 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA193 | Add two new right turn lanes on Sunshine Boulevard at Lee Boulevard in Lee County to move traffic more efficiently at the intersection. | Pavement Improvement | 2010-01-14 | 2010-01-20 | 2010-06-13 | 2010-11-04 | 553432 | 0.014
2179 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA194 | Construct a left turn on Homestead Road South in Lee County at the Milwaukee Boulevard to move traffic more efficiently though the intersection. | Safety/Traffic Management | 2009-09-16 | 2009-09-17 | 2010-01-15 | 2010-01-13 | 70579 | 0.200
2180 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA195 | Rehabilitate the Crescent Avenue bridge and the North Bay Boulevard bridge in the coastal city of Anna Maria Island to extend the use of the bridges by many years. | Pavement Improvement | 2009-09-22 | 2009-10-13 | 2012-03-12 | 2010-09-10 | 665298 | 0.001
2181 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA196 | Resurface Pine Avenue in the city of Anna Maria from Gulf Drive to Bay Boulevard to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2009-09-16 | 2009-11-16 | 2012-03-26 | 2010-01-19 | 80948 | 0.504
2182 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA197 | Resurface Gulf Drive in the city of Anna Maria from Willow Avenue to Pine Avenue to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2009-09-16 | 2009-11-16 | 2012-03-26 | 2010-01-19 | 126368 | 0.276
2183 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA199 | Add landscaping and sidewalks along State Road 789/Gulf Drive from south of 2nd Street to north of 5th Street to improve the safety and enhance the roadway features of this beach community. | Transportation Enhancements | 2009-09-30 | 2009-10-22 | 2012-03-26 | 2010-04-26 | 315085 | 0.371
2184 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA200 | Add pedestrian crosswalks to the intersections of East Bay Drive and Gulf Drive in the city of Holmes Beach to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-11-16 | 2012-03-26 | 2009-12-12 | 20220 | 0.002
2185 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA201 | "Beach Boulevard, (U.S. 90/State Road 212) in Duval County will be widened from four to six lanes for 1? miles between Hodges Boulevard and San Pablo Road in order to complete the six-lane section bet | Pavement Widening | 2009-06-10 | 2009-06-10 | 2012-02-10 |  | 15185135 | 2.760
2186 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | CLAY |  | Multiple | ARRA202 | "In Clay County, a new overpass for Plantation Oaks Boulevard traffic will separate the higher speed and volume of traffic on State Road 23, making it safer and more efficient." | Pavement Widening | 2005-08-03 | 2005-08-03 | 2012-02-16 |  | 8165927 | 0.100
2187 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU |  | 04 | ARRA203 | "In Nassau County, State Road A1A (State Road 200) will be widened from two to four lanes for six miles between Griffin and Stratton roads to improve traffic flow within the corridor." | Pavement Widening | 2009-06-16 | 2009-05-22 | 2012-02-10 |  | 29842828 | 7.890
2188 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA204 | Lengthen two left turn lanes on southbound U.S. 41 in Charlotte County to improve traffic flow at the Midway Boulevard intersection. | Pavement Improvement | 2009-09-30 | 2010-03-24 | 2012-03-29 | 2010-06-17 | 127469 | 0.100
2189 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA205 | Add a left turn lane at Murdock Circle westbound at U.S. 41 to improve traffic movement in this area. | Pavement Improvement | 2009-09-30 | 2010-03-24 | 2012-03-29 | 2010-06-17 | 180690 | 0.100
2190 | Completed | C220,C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA206 | This project in Flagler County will extend the Lehigh Trail and Bike Path by adding 12-foot wide paths and two bridges which benefits trail users and increases safety. | Transportation Enhancements | 2010-02-05 | 2010-02-15 | 2010-09-22 | 2010-09-01 | 838242 | 2.718
2191 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA207 | This project in the City of Palm Coast fixes the bridge over Club House Waterway and includes better guardrails. | Bridge Improvement | 2010-02-28 | 2010-02-28 | 2010-08-25 | 2011-01-06 | 741881 | 0.034
2192 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 08 | ARRA208 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-06 | 2009-11-30 | 2010-03-26 | 2010-04-30 | 294153 | 1.517
2193 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 06 | ARRA209 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-11 | 2010-01-21 | 2010-04-21 | 2010-04-21 | 182075 | 2.291
2194 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA210 | RESURFACING NORTH RIVERSIDE DR FROM SAND PINE RD TO US 192 (0002.950 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-02-23 | 2010-03-05 | 2010-06-13 | 2010-08-26 | 225374 | 2.950
2195 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | Multiple | ARRA211 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-25 | 2010-02-03 | 2010-05-05 | 2010-05-05 | 318511 | 2.773
2196 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LADY LAKE | 05 | ARRA212 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-22 | 2010-02-01 | 2010-06-15 | 2010-06-14 | 1704806 | 8.551
2197 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA213 | This project replaces a bridge on County Road 305 in Flagler County and includes guardrail improvements. | Pavement Improvement | 2010-02-05 | 2010-04-19 | 2010-10-22 | 2010-10-12 | 804600 | 0.010
2198 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 08 | ARRA214 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-06 | 2009-11-10 | 2010-03-06 | 2010-01-26 | 46931 | 0.839
2199 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA215 | This project fixes a drainage pipe at Hall Road in the Town of Malabar in Brevard County. | Safety/Traffic Management | 2010-03-25 | 2010-03-25 | 2010-06-12 |  | 17045 | 0.225
2200 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA216 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-10 | 2009-11-16 | 2010-03-13 | 2010-01-26 | 129783 | 0.922
2201 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA217 | "This project in the City of Melbourne will resurface the road, improve storm water drainage, make turn lanes safer, fix sidewalks and upgrade pedestrian crossings." | Pavement Improvement | 2010-02-16 | 2010-02-22 | 2010-06-22 | 2010-06-11 | 609034 | 1.277
2202 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA218 | This turn lane project in the City of Ocala will improve safety and traffic flow and reduce traffic congestion at intersections. | Safety/Traffic Management | 2009-12-03 | 2009-12-07 | 2010-10-03 | 2010-09-08 | 1068623 | 1.058
2203 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA219 | This repaving project in Marion County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-05 | 2009-11-09 | 2010-03-24 | 2010-04-06 | 963223 | 3.363
2204 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA220 | This project in Brevard County will provide a safer environment for pedestrians with a new asphalt sidewalk on which to walk. | Transportation Enhancements | 2010-03-24 | 2010-03-24 | 2010-04-23 | 2010-04-27 | 41550 | 0.713
2205 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA221 | This repaving project in the City of Palm Bay will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-13 | 2010-01-15 | 2010-06-13 | 2010-07-07 | 871050 | 1.980
2206 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA222 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-06 | 2009-11-10 | 2010-03-06 | 2010-01-23 | 97297 | 0.707
2207 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA223 | This repaving project in Brevard County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-04-28 | 2010-04-27 | 288679 | 0.793
2208 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA224 | This repaving project in Marion County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-23 | 2009-12-14 | 2010-07-12 | 2010-10-15 | 4837445 | 10.849
2209 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA225 | This resurfacing project in the City of Satellite Beach will improve the condition of the existing pavement and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-12-16 | 2009-12-21 | 2010-03-22 | 2010-03-16 | 115775 | 0.275
2210 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA226 | This resurfacing project in the City of Titusville will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2009-11-16 | 2009-12-07 | 2010-02-26 | 2010-03-10 | 51251 | 0.285
2211 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA227 | This resurfacing project in Brevard County will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-05-24 | 2010-08-26 | 301684 | 1.681
2212 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA228 | This resurfacing project in Brevard County will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2010-02-17 | 2010-02-17 | 2010-05-08 | 2010-08-19 | 333359 | 1.018
2213 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA229 | This project fixes a drainage pipe at Atz Road in the Town of Malabar in Brevard County. | Safety/Traffic Management | 2010-03-25 | 2010-03-25 | 2010-06-12 |  | 3445 | 0.230
2214 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA230 | This project fixes storm water drainage problems on Riverside Drive in Brevard County. | Safety/Traffic Management | 2010-03-31 | 2010-03-31 | 2010-04-30 | 2010-04-27 | 24830 | 0.067
2215 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA231 | This repaving project in the City of Palm Bay will improve the road surface. | Pavement Improvement | 2009-11-17 | 2009-11-17 | 2010-04-23 | 2010-03-16 | 682420 | 1.251
2216 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA232 | This resurfacing project in the City of Titusville will improve the condition of the existing pavement as well as provide better guardrails. | Pavement Improvement | 2009-11-16 | 2009-12-07 | 2010-02-26 | 2010-03-10 | 125915 | 0.680
2217 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA233 | This resurfacing project in Brevard County will improve the condition of the road and upgrade pedestrian crossings. | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-05-28 | 2010-09-14 | 501755 | 1.699
2218 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA234 | "This resurfacing project in Brevard County will improve the condition of the existing pavement, provide better traffic signals and sensors, and enhance safety by upgrading pedestrian crossings." | Pavement Improvement | 2010-02-23 | 2010-02-23 | 2010-05-14 | 2010-05-23 | 742561 | 1.949
2219 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA235 | This resurfacing project in Lake County will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2010-02-01 | 2010-02-11 | 2010-03-28 | 2010-03-23 | 19030 | 0.256
2220 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA236 | This resurfacing project in Brevard County will improve the condition of the existing pavement and enhance safety by upgrading pedestrian crossings. | Pavement Improvement | 2010-02-17 | 2010-02-17 | 2010-05-08 | 2010-05-08 | 524419 | 0.995
2221 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 06 | ARRA237 | This resurfacing project in Lake County will improve the condition of the pavement and enhance safety by upgrading pedestrian crossings. | Pavement Improvement | 2010-01-18 | 2010-01-28 | 2010-04-28 | 2010-04-28 | 156704 | 1.269
2222 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA238 | This resurfacing project in the City of Cape Canaveral will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2010-02-08 | 2010-11-15 | 2010-10-15 | 2011-02-08 | 328998 | 0.998
2223 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA239 | This resurfacing project in the Town of Malabar in Brevard County will improve the condition of the area where a paved driveway meets a road. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-06-12 |  | 8175 | 0.103
2224 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA240 | "This resurfacing project in Brevard County will improve the condition of the existing pavement, provide better traffic signals and controls, and enhance safety by providing upgraded pedestrian crossi | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-03-14 | 2010-04-21 | 49243 | 0.161
2225 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA241 | This resurfacing project in the Town of Malabar in Brevard County will improve the condition of the area where a paved driveway meets a road. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-06-12 |  | 9195 | 0.071
2226 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | Multiple | ARRA242 | "This project in the City of Cocoa will improve drainage along School Street, fix sidewalks and upgrade pedestrian crossings." | Safety/Traffic Management | 2010-03-02 | 2010-03-02 | 2010-06-30 | 2010-04-16 | 142678 | 0.247
2227 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA243 | "This project in the City of Cocoa Beach will resurface the road, improve storm water drainage, fix sidewalks and upgrade pedestrian crossings." | Pavement Improvement | 2009-10-22 | 2009-11-02 | 2010-08-29 | 2011-01-18 | 262282 | 0.409
2228 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA244 | "This resurfacing project in Brevard County will improve the condition of the existing pavement, provide better traffic signals and controls, and enhance safety by providing upgraded pedestrian crossi | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-05-28 | 2011-03-11 | 374332 | 1.000
2229 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA245 | This resurfacing project in the Town of Malabar in Brevard County will improve the condition of the area where a paved driveway meets a road. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-06-12 | 2010-08-31 | 6492 | 0.001
2230 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA246 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-25 | 2010-02-03 | 2010-03-21 | 2010-03-15 | 18837 | 0.116
2231 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 06 | ARRA247 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-22 | 2010-02-01 | 2010-05-18 | 2010-05-18 | 209728 | 2.276
2232 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA248 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-11 | 2010-01-21 | 2010-05-21 | 2010-05-18 | 617616 | 4.896
2233 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LADY LAKE | 06 | ARRA249 | This resurfacing project in Lake County will fix the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-11 | 2010-01-21 | 2010-04-21 | 2010-03-23 | 127208 | 0.300
2234 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA250 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-18 | 2010-01-18 | 2010-04-28 | 2010-04-06 | 152316 | 1.854
2235 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA251 | This resurfacing project in Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-11-24 | 2009-12-07 | 2010-03-08 | 2010-02-06 | 876255 | 2.160
2236 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 24 | ARRA252 | This resurfacing project in the City of Oviedo will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-12-11 | 2009-12-11 | 2010-06-10 | 2010-05-13 | 996396 | 1.791
2237 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA253 | This State Road 434 project in the City of Winter Springs will provide turn lanes to help reduce traffic congestion. | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-07-26 | 2010-08-27 | 160197 | 0.050
2238 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA254 | The Rinehart Road project in the City of Lake Mary includes resurfacing which will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-11-19 | 2009-11-20 | 2010-03-12 | 2010-02-26 | 709242 | 2.090
2239 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | Multiple | ARRA255 | The Howell Branch Road resurfacing project in Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2010-02-24 | 2010-01-25 | 497385 | 0.745
2240 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA256 | The International Parkway resurfacing project within the City of Lake Mary will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2010-02-23 | 2010-03-01 | 2010-06-21 | 2010-06-07 | 355291 | 1.139
2241 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA257 | The State Road 419 project in the City of Winter Springs will provide turn lanes to reduce traffic congestion. | Pavement Improvement | 2009-12-01 | 2009-12-01 | 2010-05-24 | 2010-08-18 | 387314 | 0.001
2242 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | Multiple | ARRA258 | The West 25th Street resurfacing project is Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-12-07 | 2009-12-17 | 2010-06-01 | 2010-04-30 | 1440164 | 1.164
2243 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA259 | The 8th Street resurfacing project on a local road in the City of Holly Hill will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2010-01-27 | 2010-02-01 | 2010-03-13 | 2010-03-13 | 29962 | 0.110
2244 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 24 | ARRA260 | The Taylor Creek Bridge project in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 2010-06-01 | 2010-06-01 | 2011-02-25 | 2011-04-18 | 2749828 | 0.049
2245 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | Multiple | ARRA261 | The Campo Way Bridge project located in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 2010-04-09 | 2010-04-12 | 2010-10-08 | 2010-08-20 | 378020 | 0.333
2246 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA262 | The Harrell Road Bridge project located in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 2010-04-02 | 2010-04-05 | 2010-10-31 | 2010-10-27 | 642520 | 0.457
2247 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA263 | The Thorpe Road Bridge project located in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2010-11-05 | 2011-02-02 | 412423 | 1.005
2248 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA264 | The Lake Underhill Road resurfacing project in Orange County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-04-01 | 2010-04-12 | 2010-11-28 | 2010-10-13 | 2334323 | 1.508
2249 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | Multiple | ARRA265 | The Downtown Orlando Intelligent Transportation System (ITS) project will use underground fiber optic cable and video detection equipment to upgrade the regional computerized signal system which will | Safety/Traffic Management | 2010-02-03 | 2010-02-03 | 2010-08-31 | 2010-09-09 | 3154100
2250 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA266 | RESURFACING CLARKE ROAD FROM SILVER STAR ROAD TO CLARCONA-OCOEE ROAD (0002.516 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2010-02-04 | 2010-03-01 | 2010-05-30 | 2010-05-12 | 1157652 | 2.516
2251 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA267 | The Morse Boulevard resurfacing project in Orange County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-01-07 | 2010-02-08 | 2010-05-31 | 2010-05-20 | 225502 | 0.870
2252 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA268 | The General Rees Avenue resurfacing project in Orange County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-04-01 | 2010-04-12 | 2010-12-08 | 2010-11-08 | 975019 | 0.074
2253 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA269 | The Dean Road resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-04-01 | 2010-04-05 | 2010-09-18 | 2010-08-11 | 1147105 | 1.864
2254 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA270 | The Kaley Street resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-04-01 | 2010-04-05 | 2010-10-11 | 2010-09-08 | 394944 | 1.310
2255 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 08 | ARRA271 | The Buenaventura Boulevard resurfacing project in Osceola County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2009-12-22 | 2009-12-22 | 2010-04-07 | 2010-05-25 | 2040113 | 2.573
2256 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 08 | ARRA272 | The John Young Parkway resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2009-12-22 | 2009-12-22 | 2010-05-25 | 2010-04-16 | 1789329 | 1.494
2257 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA273 | The Neptune Road resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2009-12-22 | 2009-12-22 | 2010-05-25 | 2010-04-16 | 206970 | 0.491
2258 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA274 | The County Road 4139 resurfacing project in the City of Lake Helen will be constructed by Volusia County and will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-02-12 | 2010-02-22 | 2010-06-22 | 2010-06-04 | 300000 | 3.794
2259 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA275 | The Riverside Drive resurfacing project in the City of New Smyrna Beach will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2009-11-19 | 2009-11-23 | 2010-04-17 | 2010-04-17 | 284059 | 0.839
2260 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 24 | ARRA276 | The Canal View Boulevard resurfacing project in Port Orange will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2010-01-06 | 2010-01-11 | 2010-04-12 | 2010-03-15 | 103878 | 0.939
2261 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA277 | The Lake Washington Road resurfacing project in the City of Melbourne will extend the usable life of the highway and enhance safety. | Pavement Improvement | 2010-02-16 | 2010-02-22 | 2010-06-22 |  | 418399 | 1.046
2262 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA278 | The Sykes Creek Parkway resurfacing project in Brevard County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-06-08 | 2010-08-26 | 364283 | 1.437
2263 | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | HILLSBOROUGH | TAMPA-ST.PETERSBURG-CLEARWATER,FL | Multiple | ARRA279 | The I-4/Selmon Expressway Connector is a new toll road that will connect Interstate 4 to the Selmon Expressway and provide commercial trucks direct access to the Port of Tampa improving the efficient | Other | 1994-02-16 | 1994-02-16 | 2013-02-05 |  | 105033849 | 0.913
2264 | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | Multiple | ARRA280 | "In Pinellas County, to reduce congestion, this project removes the traffic signals on U.S. 19 between Whitney Road and State Road 60 and replaces them with two new interchanges at Belleair Road and S | Pavement Widening | 2004-05-24 | 2004-05-24 | 2014-08-04 |  | 45071034 | 2.643
2265 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA281 | "This project widens Interstate 95 from Malabar Road to Palm Bay Road in Brevard County, making this section of I-95 three lanes in both directions." | Pavement Widening | 2009-10-01 | 2009-10-19 | 2012-03-25 |  | 21135881 | 4.173
2266 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 05 | ARRA282 | "The U.S. 27 project will add two new lanes, making this a six-lane, divided highway from just north of Lake Louisa Road to Cluster Oaks Drive in the City of Clermont." | Pavement Widening | 2009-10-14 | 2009-10-14 | 2012-03-25 | 2012-01-17 | 20414143 | 3.837
2267 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA283 | "This project will transform Baseline Road, which is primarily a two-lane highway, into a four-lane, divided highway near Ocala in Marion County." | Pavement Widening | 2009-09-11 | 2009-09-17 | 2012-03-26 |  | 27003841 | 5.704
2268 | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA284 | The State Road 50 project in the City of Winter Garden will widen this roadway more than three miles to a six-lane divided roadway. | Pavement Widening | 2007-07-26 | 2009-01-26 | 2012-09-30 |  | 18455641 | 3.056
2269 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 03 | ARRA285 | "The State Road 434 project in the City of Altamonte Springs will make this section of the road a six-lane, divided highway, which is consistent to the rest of State Road 434 in this area." | Pavement Widening | 2009-09-30 | 2009-12-01 | 2012-03-25 | 2010-10-27 | 4628719 | 0.713
2270 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 11 | ARRA288 | Resurface Tenth Street in the city of Palmetto from 8th Avenue to 14th Avenue to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2010-02-01 | 2010-04-29 | 2010-09-30 | 2010-12-21 | 76106 | 0.512
2271 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA289 | Resurface Cattlemen Road in Sarasota County from Bahia Vista to south of Fruitville Road to improve the surface of this heavily traveled road. | Pavement Improvement | 2010-02-18 | 2010-02-18 | 2010-06-30 | 2011-04-19 | 395068 | 1.900
2272 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | OKEECHOBEE |  | 16 | ARRA290 | Replace the bridge at 43rd Avenue in the city of Okeechobee to improve the safety of motorists. | Pavement Improvement | 2009-09-21 | 2009-10-24 | 2012-03-16 | 2010-11-26 | 1201547 | 0.001
2273 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA291 | Resurface Sumter Boulevard in North Port from City Center Boulevard to Hansard Avenue. The project also includes the widening of a bridge and new turn lanes to move traffic more efficiently. | Pavement Improvement | 2010-03-22 | 2010-04-14 | 2011-04-06 |  | 1448068 | 0.267
2274 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA292 | "Install new traffic signals, ramps and asphalt crosswalks at the intersections at Venice Avenue and Harbor Drive in Sarasota County to improve the safety of the area." | Pavement Improvement | 2010-01-11 | 2010-03-31 | 2010-10-01 | 2010-11-10 | 332747 | 0.571
2275 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA293 | Construct improvements to State Road 758 (Siesta Drive) between Siesta Bridge and Henson Bayou Bridge to correct a drainage problem along this entrance onto Siesta Key. | Pavement Improvement | 2010-03-24 | 2010-05-03 | 2010-09-30 |  | 1053068 | 0.502
2276 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA294 | Resurface Venice Avenue in Sarasota County from Ramsey Road to Jacaranda Boulevard to improve the deteriorated surface of this busy road. | Pavement Improvement | 2010-04-21 | 2010-04-26 | 2010-08-31 | 2010-10-05 | 816068 | 1.016
2277 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA295 | Resurface University Parkway in Manatee County from U.S. 41 to U.S. 301 to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2010-04-09 | 2010-04-14 | 2010-08-31 | 2011-04-19 | 753068 | 0.051
2278 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA296 | Resurface University Parkway from U.S. 301 to I-75 to improve the deteriorated surface of this heavily traveled road. This is a joint project by Manatee and Sarasota counties. | Pavement Improvement | 2010-05-04 | 2010-05-11 | 2010-09-30 |  | 1112836
2279 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA297 | Resurface University Parkway from U.S. 301 to I-75 to improve the deteriorated surface of this heavily traveled road. This is a joint project by Manatee and Sarasota counties. | Pavement Improvement | 2010-05-04 | 2010-05-11 | 2010-09-30 |  | 1143956 | 5.235
2280 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA303 | This trail project in Brevard County will create a safe environment for pedestrian and bicyclists. | Transportation Enhancements | 2010-01-06 | 2010-01-16 | 2010-06-08 | 2010-06-14 | 317660
2281 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA304 | This project fixes a drainage pipe at Atz Road in the Town of Malabar in Brevard County. | Safety/Traffic Management | 2010-03-25 | 2010-03-25 | 2010-06-12 |  | 17493 | 0.293
2282 | Completed | C220,C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA305 | "The Downtown Streetscape project within the City of Flagler Beach will include sidewalks, better lighting and accessibility for all pedestrians." | Transportation Enhancements | 2010-02-26 | 2010-03-01 | 2010-09-27 | 2011-05-26 | 1038540 | 0.519
2283 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA306 | "The Lois Drive Bridge project in Lake County replaces an outdated bridge that causes some vehicles to ""bottom out"" when they cross." | Pavement Improvement | 2009-12-17 | 2010-01-26 | 2012-04-26 | 2011-05-27 | 1867969 | 0.044
2284 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA307 | This sidewalk project in Marion County will provide a safer environment for pedestrians and will upgrade pedestrian crossings. | Transportation Enhancements | 2009-10-16 | 2009-10-26 | 2010-03-31 | 2010-03-08 | 416083
2285 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA308 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrians. | Pavement Improvement | 2009-11-06 | 2009-11-30 | 2010-08-25 | 2010-09-03 | 893096 | 1.020
2286 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA309 | The Pine Hills Road/Silver Streetscape project in Orange County will provide a safer environment for pedestrians and bicyclists and enhance the renovation of Evans High School. | Transportation Enhancements | 2010-04-09 | 2010-04-12 | 2010-09-08 | 2010-10-15 | 366132 | 0.576
2287 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | Multiple | ARRA310 | The Cross Seminole County Trail project will repair the Howell Creek Trestle Bridge which is a vital part of the Seminole County trail system. | Transportation Enhancements | 2009-12-07 | 2009-12-07 | 2010-03-26 | 2010-03-01 | 450866
2288 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA311 | The International Parkway resurfacing project in the City of Lake Mary will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2010-02-23 | 2010-03-01 | 2010-06-21 | 2010-06-07 | 391095 | 1.170
2289 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 24 | ARRA312 | This State Road 434 project in the City of Winter Springs will provide safer conditions for making right turns at this intersection. | Pavement Improvement | 2009-12-01 | 2009-12-01 | 2010-05-20 | 2010-07-06 | 167396 | 0.064
2290 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA313 | This repaving project in Osceola County will improve the road surface and upgrade pedestrian crossings. | Pavement Improvement | 2009-11-24 | 2010-01-11 | 2010-05-11 | 2010-07-13 | 661988 | 3.785
2291 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA314 | This sidewalk project in Marion County will provide a safer environment for pedestrians and bicyclists as well as upgraded pedestrian crossings. | Pavement Improvement | 2009-11-24 | 2010-01-11 | 2010-06-10 | 2010-07-13 | 994947 | 7.425
2292 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA315 | "The Lake Panasoffkee Pedestrian Trail, located in Sumter County, will provide a safe environment with a new, five-foot wide, concrete sidewalk for pedestrians and bicyclists." | Transportation Enhancements | 2009-12-10 | 2010-01-11 | 2010-04-10 | 2010-03-25 | 249507
2293 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | Multiple | ARRA316 | The Dunn Avenue project in Daytona Beach will extend this road and includes a bridge over I-95. | New Construction | 2010-02-12 | 2010-03-01 | 2011-08-03 | 2011-06-30 | 5581933 | 0.612
2294 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA318 | The 8th Street resurfacing project in the City of Holly Hill will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-02-03 | 2010-02-08 | 2010-06-18 | 2010-03-12 | 18402 | 0.129
2295 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH, FL | 18 | ARRA319 | This project reconstructs almost three miles of the US 1 corridor known as the 18-mile stretch between Florida City and Key Largo. | Pavement Improvement | 2004-11-16 | 2004-11-16 | 2011-06-08 |  | 18433884 | 2.860
2296 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA320 | "This bridge project will include the repair and safety upgrades of the bridge deck, repaving of the deck and the installation of handrails." | Transportation Enhancements | 2010-01-04 | 2010-01-05 | 2011-01-30 |  | 843134 | 0.243
2297 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH, FL | 21 | ARRA322 | This project will provide improvements for bike paths and trails from Dadeland Station to S.W. 67th Avenue. | Transportation Enhancements | 2010-10-28 | 2011-01-07 | 2012-10-22 | 2012-01-23 | 3000000
2298 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA323 | This project will provide maintenance and repairs to the Palm Drive Bridge in Monroe County. The project will replace the bridge deck and railings. | Bridge Improvement | 2009-11-19 | 2009-11-30 | 2010-03-05 | 2010-03-05 | 136053 | 0.013
2299 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA324 | "This project will resurface the existing roadway, upgrade sidewalks, signing and pavement markings, replace signals and landscape. This project will enhance mobility for the community." | Pavement Improvement | 2010-06-02 | 2010-06-07 | 2011-10-31 |  | 3955017 | 0.743
2300 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA325 | This project will provide maintenance and repairs to the Geiger Creek bridge. These repairs will maintain a higher level of service. | Bridge Improvement | 2010-02-11 | 2010-02-17 | 2010-10-01 | 2011-10-13 | 914056 | 0.125
2301 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA327 | The City of Medley will resurface and install new pavement markings. This project will enhance the efficient and safe flow of vehicular traffic. | Bridge Improvement | 2011-03-28 | 2011-04-08 |  | 2011-10-24 | 42035 | 0.040
2302 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA328 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2011-05-12 | 2011-09-21 | 162382 | 0.833
2303 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA329 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2011-05-12 | 2011-09-21 | 239094 | 0.800
2304 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA330 | This project will repave roadways throughout the Town of Cutler Bay. This project will enhance the ride for users of the town's roadway network. | Pavement Improvement | 2010-01-04 | 2010-01-27 | 2010-10-08 | 2012-02-08 | 205243 | 1.563
2305 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA331 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Transportation Enhancements | 2009-12-01 | 2009-12-01 | 2010-09-30 | 2011-04-14 | 116640
2306 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA332 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Transportation Enhancements | 2009-12-01 | 2009-12-14 | 2010-09-30 | 2011-02-28 | 146586
2307 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA333 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2011-03-01 | 2011-11-03 | 458965
2308 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA334 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2011-03-01 |  | 274051
2309 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA335 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2011-01-16 | 2011-07-28 | 176849
2310 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA336 | The City of Surfside will install solar lighting on this corridor. This project will enhance safety. | Safety/Traffic Management | 2010-07-27 | 2010-08-16 | 2010-09-30 | 2011-11-02 | 47000
2311 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA337 | "This project includes repaving, pavement markings, guardrails and sidewalk improvements." | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-11-01 | 2011-04-18 | 110000 | 1.000
2312 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA338 | "This project will resurface 1.50 miles of road and add new markings, guardrails and sidewalk improvements." | Pavement Improvement | 2010-04-06 | 2010-04-06 | 2010-08-02 | 2010-10-26 | 88014 | 4.561
2313 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA339 | This project will improve safety for motorists by repairing the underside of the bridge deck and bridge railings. | Bridge Improvement | 2010-03-11 | 2010-03-15 | 2010-09-30 | 2011-01-19 | 200753 | 0.080
2314 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA340 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-22 | 2010-03-03 | 2012-03-31 | 2011-10-24 | 136680 | 0.400
2315 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA341 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-22 | 2010-03-03 | 2010-10-22 | 2011-10-24 | 126202 | 0.228
2316 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA342 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2011-01-26 | 2012-01-26 | 50828 | 0.070
2317 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA343 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2011-01-26 | 2012-01-26 | 31172 | 0.250
2318 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA344 | The City of Bal Harbour will provide crosswalk improvements. This project will provide enhancements to the pedestrian. | Safety/Traffic Management | 2010-03-09 | 2010-07-12 | 2010-10-29 |  | 74684
2319 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA345 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2011-02-05 |  | 174050 | 0.556
2320 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA346 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2011-02-05 |  | 32635 | 0.080
2321 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA347 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-05-18 | 2010-05-18 | 2010-11-14 |  | 67985 | 0.080
2322 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA348 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2011-02-10 |  | 467900 | 0.630
2323 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA349 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-05-18 | 2010-05-18 | 2010-11-14 |  | 48726 | 0.255
2324 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA350 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-05-18 | 2010-05-18 | 2010-11-14 |  | 187035 | 0.270
2325 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA351 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-03-02 | 2010-03-02 | 2011-02-25 |  | 234574 | 0.310
2326 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA352 | This project will provide bridge deck improvements to the Yacht Club bridge. | Bridge Improvement | 2010-01-25 | 2010-03-09 | 2010-09-30 | 2011-02-18 | 112553 | 0.200
2327 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA353 | "The United Street corridor project in the City of Key West will repave the existing roadway, restripe the surface, and construct new sidewalks and curbs. This project will enhance safety for the moto | Pavement Improvement | 2010-06-09 | 2010-07-19 | 2011-05-31 | 2012-01-26 | 418466 | 0.266
2328 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA354 | The Village of Biscayne Park will construct median curbs and an irrigation system. The project will enhance pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-10-15 | 2009-12-21 | 2009-12-19 | 74073 | 0.527
2329 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA355 | The Village of El Portal will resurface and enhance drainage at intersections. The project will enhance roadway safety for the traveling public. | Pavement Improvement | 2009-09-16 | 2009-11-09 | 2010-02-03 | 2010-01-20 | 56641 | 0.261
2330 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA356 | "The City of Virginia Gardens will construct new drainage inlets at intersections, and perform pavement resurfacing and restriping. This project will enhance safety for the traveling public." | Pavement Improvement | 2009-09-16 | 2009-11-23 | 2010-02-03 | 2010-01-20 | 37260 | 0.300
2331 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA357 | Larger drainage pipes will be installed under US 29 in the Town of Century as part of an overall community drainage improvement project in Escambia County. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2012-04-15 | 2010-06-02 | 460605 | 0.134
2332 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA358 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2010-09-15 | 2010-09-15 | 2010-11-29 |  | 174361 | 5.558
2333 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA359 | This project will provide sidewalk enhancements along selected corridor. This project will increase pedestrian safety. | Transportation Enhancements | 2009-12-08 | 2010-01-05 | 2010-09-30 | 2010-11-06 | 112290
2334 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA360 | This project will provide illuminated signs throughout various locations in Miami-Dade County to enhance driving conditions. | Safety/Traffic Management | 2010-01-20 | 2010-01-25 | 2010-09-23 | 2011-04-15 | 264345
2335 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA361 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists. | Safety/Traffic Management | 2009-11-10 | 2009-11-12 | 2010-08-16 | 2010-06-04 | 126921
2336 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA362 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists and pedestrians. | Safety/Traffic Management | 2009-11-30 | 2009-12-07 | 2010-09-13 | 2010-08-13 | 103244
2337 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA363 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists. | Safety/Traffic Management | 2010-03-03 | 2010-03-08 | 2011-03-03 | 2011-04-21 | 216474
2338 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA364 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 2009-10-19 | 2009-10-19 | 2010-07-16 | 2010-06-04 | 54724 | 0.260
2339 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA365 | "This project will renovate sidewalks, curbs, pavement, pavement markings and upgrade signage. These enhancements will help maintain a higher level of service." | Pavement Improvement | 2010-02-08 | 2010-03-02 | 2010-10-29 | 2011-03-21 | 199864 | 0.097
2340 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA366 | "This project will add new drainage, lighting, sidewalk, curbs, pavement, pavement markings, signage and signalization. These enhancements will help maintain a higher level of service." | Pavement Improvement | 2010-02-15 | 2010-02-15 | 2010-10-29 | 2011-01-12 | 923920 | 0.524
2341 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA367 | "This project will add new drainage, lighting, sidewalk, curbs, pavement, pavement markings, signage and signalization. These enhancements will help maintain a higher level of service." | Pavement Improvement | 2010-02-08 | 2010-03-01 | 2010-10-29 | 2011-05-06 | 884969 | 0.501
2342 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA368 | "This project will add new drainage, lighting, sidewalk, curb, pavement, pavement markings, signage and signalization. These enhancements will help maintain a high level of service." | Pavement Improvement | 2010-02-08 | 2010-03-15 | 2010-10-29 | 2011-07-08 | 993339 | 0.465
2343 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA369 | "This project will renovate sidewalks, curbs, pavement, pavement markings and upgrade signage. These enhancements will help maintain a higher level of service." | Pavement Improvement | 2010-02-08 | 2010-03-02 | 2010-10-29 | 2011-04-26 | 278218 | 1.488
2344 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA370 | The City of Marianna will repave Milton Avenue to improve the road surface and driving quality in Jackson County. | Pavement Improvement | 2009-12-03 | 2009-12-18 | 2010-05-17 | 2010-08-30 | 219016 | 0.086
2345 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA371 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2011-01-04 | 2011-07-28 | 147561 | 1.002
2346 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA372 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2011-01-04 | 2011-07-28 | 194107 | 0.511
2347 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA373 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-09-26 |  | 263409 | 0.513
2348 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA374 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-09-26 |  | 314525 | 0.786
2349 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA375 | This project will resurface the roadway. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2011-01-04 | 2011-07-28 | 162079 | 0.553
2350 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA376 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 277380 | 1.512
2351 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA377 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 36691 | 0.183
2352 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA378 | This project will resurface the roadway. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 168559 | 0.516
2353 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA379 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 209756 | 0.498
2354 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA380 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2011-05-12 | 2011-09-21 | 375554 | 1.500
2355 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA381 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 139682 | 1.028
2356 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA382 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-03-22 | 2010-03-22 | 2011-01-16 | 2011-10-24 | 436190 | 0.922
2357 | Underway | C250,C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA383 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2011-02-20 |  | 630629 | 2.031
2358 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA384 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-03-22 | 2010-03-22 | 2011-01-16 | 2011-10-24 | 215712 | 1.480
2359 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA385 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-12-19 | 2011-10-25 | 249415 | 1.027
2360 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA386 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-12-19 | 2011-10-25 | 351470 | 1.000
2361 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA387 | This project will resurface the roadway. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-12-19 | 2011-10-25 | 237328 | 1.524
2362 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA388 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-12-19 |  | 96610 | 0.504
2363 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA389 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-12-19 |  | 261261 | 1.524
2364 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA390 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-12-19 |  | 371321 | 0.830
2365 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA391 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-21 | 2010-04-30 | 2011-02-24 | 2012-01-18 | 157697 | 0.500
2366 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA392 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-21 | 2010-04-30 | 2011-02-24 | 2012-01-18 | 125194 | 0.503
2367 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA393 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-21 | 2010-04-30 | 2011-02-24 | 2012-01-18 | 460235 | 0.990
2368 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA394 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-03-01 | 2012-01-26 | 269767 | 0.498
2369 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA395 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-03-01 | 2012-01-26 | 138492 | 0.040
2370 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA396 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2011-02-21 | 2011-07-14 | 741164 | 1.380
2371 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA397 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses a | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-07-30 | 2010-07-22 | 111494 | 0.311
2372 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA398 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses a | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-10-29 | 2011-03-11 | 124240 | 0.160
2373 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA399 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses a | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-10-29 | 2011-07-27 | 178641 | 0.826
2374 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA400 | This Leon County project will add a left turn lane and a traffic signal on Meridian Road at Bannerman Road to improve traffic operations and safety. | Safety/Traffic Management | 2009-08-03 | 2009-08-03 | 2010-07-31 | 2010-05-04 | 662236 | 0.325
2375 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA401 | The City of Homestead will install streetlight poles. Streetlights along the corridor will enhance the safety of all roadway users. | Safety/Traffic Management | 2009-12-01 | 2009-12-07 | 2010-10-29 | 2012-02-14 | 1345064 | 6.127
2376 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA402 | This new project involves the installation of decorative lighting along the Ludlam Drive Bike Path in the City of Miami Springs. The project will provide better visibility for pedestrians. | Safety/Traffic Management | 2010-02-11 | 2010-02-12 | 2010-09-30 | 2011-02-22 | 554812 | 2.000
2377 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA403 | This project will repair the deck of the Brickell Key Bridge over Biscayne Bay. The project will provide necessary repairs to the bridge to enhance mobility. | Bridge Improvement | 2010-09-30 | 2010-10-12 | 2011-06-29 |  | 1713201 | 0.159
2378 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA404 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 2010-02-25 | 2010-04-29 | 2010-11-19 |  | 31122 | 0.191
2379 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA405 | This project will provide lighting enhancements for the City of Homestead. Streetlights along this corridor will enhance safety for all roadway users. | Safety/Traffic Management | 2010-04-01 | 2010-04-01 | 2011-02-28 |  | 230754 | 0.903
2380 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA406 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 2010-02-25 | 2010-04-29 | 2010-11-19 |  | 96809 | 0.255
2381 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA407 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 2010-02-25 | 2010-04-29 | 2010-11-19 |  | 44135 | 0.137
2382 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA408 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 2010-02-25 | 2010-04-29 | 2010-11-19 |  | 69124 | 0.506
2383 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA409 | "The City of South Miami will enhance sections of Sunset Drive by resurfacing, reconstructing sidewalks, upgrading drainage, and installing median landscaping and irrigation. This project will create | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-06-04 | 2010-06-04 | 253166 | 0.219
2384 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA410 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 2010-01-06 | 2010-01-06 | 2010-09-30 | 2010-08-17 | 13204 | 0.119
2385 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA411 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 2010-01-06 | 2010-01-06 | 2010-09-30 | 2010-08-17 | 12805 | 0.160
2386 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA412 | This project will provide sidewalk enhancements along the selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-06-28 | 2010-07-23 | 2010-11-30 | 2011-05-17 | 123750 | 0.630
2387 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA413 | This project will provide sidewalk enhancements along the selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-06-30 | 2010-08-02 | 2010-12-15 |  | 976245 | 0.505
2388 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA414 | The City of North Miami Beach will improve safety for motorists by repairing the underside of the bridge deck. | Bridge Improvement | 2010-06-02 | 2010-06-19 | 2010-09-30 | 2011-06-13 | 250000 | 0.016
2389 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA415 | This project will repave the existing roadway. This project will enhance safety and mobility. | Pavement Improvement | 2010-03-09 | 2010-03-10 | 2011-03-31 | 2011-11-02 | 611940 | 0.424
2390 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA417 | This project will provide sidewalk enhancements along selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-02-15 | 2010-02-18 | 2010-09-27 |  | 154258 | 0.140
2391 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA418 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2011-01-26 | 2012-01-26 | 146521 | 0.394
2392 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA419 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-10-08 | 2012-01-26 | 170422 | 0.447
2393 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA420 | This project will provide sidewalk enhancements along the selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-07-27 | 2010-10-18 | 2010-09-30 | 2011-11-02 | 84054 | 1.049
2394 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA421 | This project will provide improvements for bike paths and trails. | Transportation Enhancements | 2010-02-22 | 2010-03-15 | 2010-10-01 | 2011-05-24 | 299825 | 2.387
2395 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA422 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2011-01-25 | 2011-01-31 | 2010-11-29 | 2011-07-26 | 180804 | 1.666
2396 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA423 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2011-05-23 | 2011-02-14 | 2010-06-25 |  | 129779 | 0.474
2397 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA424 | This project will repave roadways throughout the Town of Cutler Bay. This project will enhance the ride for users of the town's roadway network. | Pavement Improvement | 2010-01-04 | 2010-01-27 | 2010-10-08 | 2012-02-08 | 221388 | 1.682
2398 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA425 | This project will repave roadways throughout the Town of Cutler Bay. This project will enhance the ride for users of the town's roadway network. | Pavement Improvement | 2010-01-04 | 2010-01-27 | 2010-10-08 | 2012-02-08 | 185107 | 1.112
2399 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA426 | "This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network. | Pavement Improvement | 2010-01-04 | 2010-01-27 | 2010-10-08 | 2012-02-08 | 106053 | 1.232
2400 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA427 | "This project will make improvements to sidewalks, concrete curbing, driveways, pavement markings, and partial drainage and roadway repairs. These improvements will enhance safety and mobility." | Pavement Improvement | 2010-09-08 | 2010-10-01 | 2011-03-11 | 2012-02-08 | 342882 | 1.626
2401 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA428 | "This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network. | Pavement Improvement | 2010-01-04 | 2010-01-27 | 2010-10-08 | 2012-02-08 | 51777 | 0.450
2402 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA429 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2011-02-07 | 2011-02-07 | 2010-12-01 | 2011-08-25 | 308420 | 1.188
2403 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA430 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2011-02-07 | 2011-02-07 | 2010-12-01 | 2011-08-25 | 242141 | 2.176
2404 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA431 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-11-01 | 2011-04-18 | 341088 | 1.410
2405 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA432 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Pavement Improvement | 2010-04-06 | 2010-04-06 | 2010-08-02 | 2010-10-26 | 337988 | 1.000
2406 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA434 | "This project includes repaving, pavement markings, guardrails and sidewalk improvements." | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-11-01 | 2011-04-18 | 160109 | 2.500
2407 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA435 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 2010-01-06 | 2010-01-06 | 2010-09-30 | 2010-08-17 | 14508 | 0.120
2408 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA436 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 2010-01-06 | 2010-01-06 | 2010-09-30 | 2010-08-17 | 30971 | 0.500
2409 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA437 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2011-06-09 | 2011-06-09 | 2011-04-15 |  | 742984
2410 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA438 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2011-06-09 | 2011-06-09 | 2011-01-17 |  | 294399
2411 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA439 | This project will repave the existing roadway and reconstruct existing sidewalks. This project will enhance safety and mobility. | Bridge Improvement | 2010-09-20 | 2010-11-15 | 2011-02-15 | 2011-09-13 | 478922 | 0.044
2412 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA440 | This project will repave the existing roadway and repair existing pavement markings. This project will enhance safety and mobility. | Pavement Improvement | 2009-10-30 | 2010-02-11 | 2010-10-22 | 2011-03-01 | 317175 | 0.501
2413 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA441 | The City of West Miami will construct four traffic-calming devices at various locations. This project will reduce the speed of traffic and improve pedestrian safety. | Safety/Traffic Management | 2009-09-14 | 2009-10-20 | 2010-07-12 | 2010-07-12 | 21063 | 0.013
2414 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA442 | The City of West Miami will construct four traffic-calming devices at various locations. This project will reduce the speed of traffic and improve pedestrian safety. | Safety/Traffic Management | 2009-09-14 | 2009-10-20 | 2010-07-12 | 2010-07-12 | 30995 | 0.130
2415 | Completed | C220,C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA444 | This project will repave the existing roadway and repair existing pavement markings. This project will enhance safety and mobility. | Transportation Enhancements | 2009-10-30 | 2009-11-18 | 2010-10-08 | 2011-03-16 | 179282 | 0.470
2416 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA445 | "This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network. | Pavement Improvement | 2010-01-04 | 2010-01-27 | 2010-10-08 | 2012-02-08 | 171716 | 1.708
2417 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA446 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 2009-11-23 | 2009-11-23 | 2010-09-23 | 2010-09-13 | 20860 | 1.000
2418 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA447 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 2009-11-23 | 2009-11-23 | 2010-09-23 | 2010-09-13 | 14781 | 1.174
2419 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA448 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 2009-11-23 | 2009-11-23 | 2010-09-23 | 2010-09-13 | 19806 | 0.504
2420 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA449 | This project involves widening 0.8 miles of a three-lane roadway to five lanes. This project will ease congestion and provide interconnectivity. | Pavement Widening | 2010-01-08 | 2010-01-08 | 2010-12-18 |  | 776997 | 1.017
2421 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA450 | This project will provide sidewalk enhancements and increase pedestrian safety. | Transportation Enhancements | 2010-01-04 | 2010-01-05 | 2010-09-30 | 2011-03-10 | 456640 | 0.707
2422 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA451 | "This project will provide new construction of a new raised landscaped median, new turning bays for left turn movements and new curb bump outs at intersections to provide for improved bus access. This | Pavement Improvement | 2010-03-18 | 2010-04-05 | 2010-12-22 |  | 1036796 | 0.408
2423 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA452 | This project will improve safety for motorists by repaving and adding new striping and pavement markings. | Pavement Improvement | 2011-06-09 | 2011-06-09 | 2011-04-15 |  | 365000 | 0.327
2424 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA453 | "This project will improve safety for motorists by repairing the bridge beams, bridge seawall and repairing the sidewalk approach." | Bridge Improvement | 2010-03-05 | 2010-03-05 | 2010-09-27 | 2011-04-12 | 270310 | 0.026
2425 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA454 | This project will improve safety for motorists by sealing cracks at the bridge deck top and underside. | Bridge Improvement | 2010-03-05 | 2010-03-15 | 2010-09-30 | 2011-04-12 | 255443 | 0.028
2426 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA455 | This project will repave the existing roadway. This project will enhance safety and mobility. | Pavement Improvement | 2009-12-08 | 2010-01-15 | 2010-10-20 |  | 813438 | 0.752
2427 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA456 | "This project will resurface the existing roadway, upgrade sidewalks, signing and pavement markings, replace signals and landscape. This project will enhance mobility for the community." | Pavement Improvement | 2010-05-27 | 2010-06-01 | 2010-11-29 | 2011-05-26 | 510979 | 0.297
2428 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA457 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along sp | Safety/Traffic Management | 2009-10-19 | 2009-10-19 | 2010-07-16 | 2010-06-04 | 69551 | 1.014
2429 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA458 | The City of Fort Walton Beach will repave Memorial Parkway to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-07-31 | 2010-07-31 | 437600 | 1.304
2430 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA459 | The City of Fort Walton Beach will repave Bay Drive Southeast to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-07-31 | 2010-07-31 | 152726 | 1.572
2431 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | CALHOUN |  | 02 | ARRA460 | This safety project will provide roadway striping on city streets in the City of Blountstown to provide safer travel on roads that have little or no existing striping in Calhoun County. | Safety/Traffic Management | 2009-12-14 | 2009-12-24 | 2010-04-13 | 2010-04-02 | 80384 | 3.125
2432 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA461 | This safety project will provide roadway striping on rural roads in Gadsden County to provide safer travel on roads that have little or no existing striping. | Safety/Traffic Management | 2010-05-03 | 2010-05-11 | 2010-08-31 | 2010-06-15 | 519778
2433 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN | TALLAHASSEE | 02 | ARRA462 | This safety project will provide roadway striping on roads in Gadsden County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 2010-03-22 | 2010-04-01 | 2010-08-31 | 2010-04-29 | 268359
2434 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | GULF |  | 02 | ARRA463 | Gulf County will repave County Road 30A to improve the road surface and driving quality. | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-04-30 | 2010-06-15 | 273077 | 0.300
2435 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA464 | This safety project will provide roadway striping on rural roads in Holmes County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 2009-11-06 | 2009-11-12 | 2010-02-16 | 2010-02-05 | 547214 | 16.647
2436 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | LIBERTY |  | 02 | ARRA465 | Liberty County will install guardrail at several locations on county roads to improve the safety of the traveling public. | Safety/Traffic Management | 2009-11-17 | 2009-11-30 | 2010-03-04 | 2010-02-18 | 266006
2437 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA467 | Okaloosa County will replace drainage pipes and existing failing pavement on Hollywood Boulevard in Fort Walton Beach to improve the road surface and driving quality. | Pavement Improvement | 2009-11-19 | 2009-12-01 | 2010-05-15 | 2010-07-19 | 1391467 | 0.187
2438 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA468 | "The City of Destin will add bus stops, public parking and landscaping, improve sidewalks, and replace existing failing pavement on Scenic Highway to improve pedestrian safety and travel in Okaloosa C | Pavement Improvement | 2009-10-06 | 2009-10-19 | 2010-06-25 | 2010-07-10 | 760955 | 0.771
2439 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WAKULLA |  | 02 | ARRA469 | This safety project will provide roadway striping on rural roads in Wakulla County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 2009-10-13 | 2009-11-02 | 2009-12-28 | 2009-11-18 | 64707 | 19.785
2440 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA470 | Walton County will construct a pedestrian bridge over Big Redfish Lake along County Road 30A to improve pedestrian safety. | Transportation Enhancements | 2010-01-07 | 2010-01-17 | 2010-05-18 | 2010-07-19 | 458483 | 0.001
2441 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA471 | This safety project will provide roadway striping on rural roads in Washington County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 2009-11-04 | 2009-11-14 | 2010-03-15 | 2010-04-23 | 449538 | 11.460
2442 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA472 | Washington County will repave State Park Road to improve the road surface and driving quality. | Pavement Improvement | 2009-12-07 | 2009-12-17 | 2010-05-25 | 2010-05-26 | 241313 | 1.035
2443 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA473 | This project involves the design of a traffic circle that will be used as a traffic calming device and improvements at crosswalks. This project will enhance safety and mobility. | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2010-12-10 |  | 409310 | 0.178
2444 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA474 | "This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network. | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2010-09-30 | 2011-03-15 | 160500 | 0.010
2445 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA475 | BIKE PATH/TRAIL SR 5/OVRSEAS HRT.TRL FROM MM 47 TO MM 54 SAFETY IMPROVEMENTS (0005.909 MILES) IN MONROE COUNTY, FLORIDA. | Transportation Enhancements | 2010-04-26 | 2010-05-03 | 2011-01-30 |  | 500000 | 5.909
2446 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA476 | "This project will provide intersection realignment, resurfacing of roadway, new striping, signage and emergency signalization." | Pavement Improvement | 2010-02-05 | 2010-02-15 | 2010-09-03 | 2011-07-05 | 87000 | 0.133
2447 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA478 | "This project will enhance the Sombrero Beach Road extension by installing storm water facilities, renovating the bike path, installing streetlights, and widening, resurfacing and restriping the road. | Pavement Improvement | 2010-01-11 | 2010-01-27 | 2010-10-14 | 2011-03-18 | 1010000 | 0.260
2448 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA479 | This project will repave approximately 0.9 miles of Harbor Drive to improve the ride for the users of this roadway. | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2010-08-30 | 2010-07-12 | 106109 | 0.912
2449 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA480 | This project will install lighting along approximately 0.4 mile of the project corridor providing better visibility to the users of this roadway. | Safety/Traffic Management | 2009-10-19 | 2009-10-19 | 2010-08-30 | 2010-07-12 | 154195 | 0.497
2450 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA481 | This project will provide sidewalk enhancements along the selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-03-09 | 2010-04-05 | 2010-11-12 |  | 116249 | 0.250
2451 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA482 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2010-07-09 | 2010-07-12 | 2010-10-25 | 2011-05-24 | 131889 | 0.210
2452 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA483 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2010-06-07 | 2010-06-28 | 2010-10-25 |  | 179934 | 0.983
2453 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA484 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-11-18 | 2011-06-09 | 582508 | 2.000
2454 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA485 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-04-07 | 2010-04-19 | 2011-04-19 |  | 1280249 | 2.510
2455 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA486 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-04-07 | 2010-04-19 | 2010-09-16 |  | 259496 | 1.540
2456 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA487 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-11-18 | 2011-07-28 | 554999 | 1.320
2457 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA488 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-11-18 | 2011-07-13 | 181784 | 0.509
2458 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA489 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-11-18 | 2011-07-13 | 225723 | 2.039
2459 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA490 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists. | Safety/Traffic Management | 2010-03-29 | 2010-03-29 | 2010-11-29 | 2011-11-23 | 248710 | 1.003
2460 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA491 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2010-12-01 | 2011-07-27 | 471766 | 2.976
2461 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA492 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2010-12-01 |  | 498685 | 1.762
2462 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA493 | The Village of Pinecrest will repave two miles of road. This project will enhance mobility for users of this roadway. | Pavement Improvement | 2009-12-25 | 2010-01-04 | 2010-09-30 | 2011-08-02 | 252822 | 2.042
2463 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA494 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-03-29 | 2010-03-29 | 2010-11-29 | 2012-01-31 | 419806 | 2.770
2464 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA495 | The project will repave the existing roadway. This project will enhance mobility for users of this roadway. | Pavement Improvement | 2009-12-25 | 2010-01-19 | 2010-09-30 | 2011-08-02 | 187586 | 1.331
2465 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA496 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2010-12-01 | 2012-01-06 | 323897 | 1.989
2466 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA497 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2010-12-01 |  | 566110 | 2.001
2467 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA498 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2010-12-01 | 2012-01-06 | 162411 | 1.212
2468 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA499 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2010-10-02 | 2011-10-26 | 643535 | 2.004
2469 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA500 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-26 | 2010-03-01 | 2010-10-01 | 2011-06-22 | 303825 | 1.009
2470 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | CALHOUN |  | 02 | ARRA501 | Guardrail will be installed on several county roads in Calhoun County to improve the safety of the traveling public. | Safety/Traffic Management | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 146937 | 6.302
2471 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | CALHOUN |  | 02 | ARRA502 | This safety project will provide roadway striping on rural roads in Calhoun County to provide safer travel on roads that had little or no existing striping. | Safety/Traffic Management | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2009-11-10 | 214699 | 9.656
2472 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WAKULLA |  | 02 | ARRA503 | Crosswalks and sidewalks were constructed along State Road 363 to improve pedestrian safety in the City of St. Marks. | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2009-11-14 | 31746 | 0.097
2473 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA504 | Five-foot wide sidewalks along various streets within the city limits of Gretna will be constructed to improve pedestrian safety in Gadsden County . | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2010-01-20 | 326817 | 0.777
2474 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA505 | This pedestrian safety project in Holmes County will include the construction of a 600-foot sidewalk in the Town of Noma. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 37573 | 0.117
2475 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA506 | This pedestrian safety project in Holmes County will include the construction of a 900-foot sidewalk in the Town of Esto. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 74565 | 0.336
2476 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | JEFFERSON |  | Multiple | ARRA507 | Existing deficient pavement on North Salt Road in Jefferson County will be replaced to improve the road surface and driving quality. | Safety/Traffic Management | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2010-04-12 | 697642 | 4.889
2477 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA508 | A five-foot wide sidewalk along State Road 69 will be constructed in the City of Grand Ridge to improve pedestrian safety in Jackson County. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 133912 | 0.255
2478 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA509 | A five-foot wide sidewalk along State Road 285 has been constructed in the City of Niceville to improve pedestrian safety in Okaloosa County. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2009-11-06 | 155764 | 0.858
2479 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA510 | A five-foot wide sidewalk along 19th Street will be constructed in the City of DeFuniak Springs to improve pedestrian safety in Walton County. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 164293 | 2.196
2480 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA511 | Walton County will repave County Road 30A to improve the road surface and driving quality. | Pavement Improvement | 2010-01-07 | 2010-01-17 | 2010-05-12 | 2010-08-27 | 1028522 | 1.170
2481 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA512 | The City of Marianna in Jackson County will repave College Street to improve the road surface and driving quality. | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2010-04-17 | 2010-04-15 | 187993 | 0.589
2482 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA513 | The City of Freeport will construct a five-foot wide sidewalk along State Road 20 to improve pedestrian safety in Walton County. | Transportation Enhancements | 2009-11-09 | 2009-11-09 | 2009-12-08 | 2009-12-30 | 49132 | 0.114
2483 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | WAKULLA | TALLAHASSEE | 02 | ARRA514 | This project will improve safety for motorists by providing a left turn lane onto Russell Drive north of the City of Crawfordville. | Pavement Widening | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2009-12-17 | 199036 | 0.214
2484 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA515 | This Jackson County project consists of installing sidewalk along Caverns Road to increase pedestrian safety to Marianna High School. | Transportation Enhancements | 2009-10-15 | 2009-10-15 | 2010-08-15 | 2010-09-15 | 507379 | 1.631
2485 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA516 | This Jackson County project consists of restriping cross-walks and replacing failing sidewalks to improve pedestrian safety in the City of Marianna. | Safety/Traffic Management | 2009-10-15 | 2009-10-15 | 2010-04-27 | 2010-04-30 | 213675 | 0.068
2486 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA517 | "The City of Tallahassee will construct approximately 2,300 feet of sidewalk along Idlewild Drive to improve pedestrian safety in Leon County." | Transportation Enhancements | 2010-03-04 | 2010-03-04 | 2010-10-24 | 2010-10-24 | 272599 | 0.413
2487 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA518 | "The City of Tallahassee will construct approximately 1,800 feet of sidewalk along Lucy Street to improve pedestrian safety in Leon County." | Transportation Enhancements | 2010-03-03 | 2010-03-03 | 2010-08-30 | 2010-10-20 | 91587 | 0.353
2488 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA519 | This City of Tallahassee project will reconstruct curb ramps and pedestrian signal features to improve pedestrian safety in the community. | Transportation Enhancements | 2010-03-29 | 2010-03-29 | 2010-09-21 | 2010-08-10 | 138480 | 1.081
2489 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA520 | "The City of Tallahassee will construct approximately 1,000 feet of sidewalk along Ingleside Avenue to improve pedestrian safety in Leon County." | Transportation Enhancements | 2010-03-03 | 2010-03-03 | 2010-08-30 | 2010-10-22 | 357205 | 0.427
2490 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA521 | The City of Fort Walton Beach will repave Country Club Avenue to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-07-31 | 2010-07-31 | 142948 | 0.850
2491 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN | TALLAHASSEE | 02 | ARRA522 | Gadsden County will repave Glades Road to improve the road surface and driving quality. | Pavement Improvement | 2009-12-14 | 2009-12-24 | 2010-05-31 | 2010-05-27 | 384409 | 1.840
2492 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA523 | Gadsden County will repave South Main Street to improve the road surface and driving quality. | Pavement Improvement | 2010-03-16 | 2010-03-26 | 2010-08-31 | 2010-06-22 | 123790 | 0.250
2493 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA524 | "Leon County will construct approximately 4,700 feet of sidewalk along Dempsey Mayo Road to improve pedestrian safety." | Transportation Enhancements | 2010-01-19 | 2010-01-19 | 2010-03-20 | 2010-04-27 | 125361 | 0.906
2494 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA525 | Leon County will repair the existing sidewalk and construct additional sidewalk along Perkins Road to improve pedestrian safety in the City of Tallahassee. | Transportation Enhancements | 2009-11-23 | 2009-11-23 | 2010-03-22 | 2010-04-21 | 18727 | 0.076
2495 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA526 | Leon County will construct approximately one mile of sidewalk along Velda Dairy Road to improve pedestrian safety. | Transportation Enhancements | 2010-04-13 | 2010-04-13 | 2010-06-25 | 2010-10-21 | 226484 | 1.729
2496 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA |  | Multiple | ARRA527 | Okaloosa County will construct a five-foot sidewalk along Brookmeade Drive to improve pedestrian safety in the City of Crestview. | Transportation Enhancements | 2009-12-16 | 2009-12-21 | 2010-03-30 | 2010-01-29 | 81454 | 0.373
2497 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA528 | "Franklin County will construct approximately 2,700 feet of five-foot wide sidewalk along Pine Avenue to improve pedestrian safety." | Transportation Enhancements | 2009-11-09 | 2009-11-09 | 2010-02-07 | 2010-03-31 | 98745 | 0.227
2498 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA529 | Escambia County will repave Dog Track Road to improve the road surface and driving quality. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-08-25 | 2010-05-28 | 256335 | 1.125
2499 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA530 | Escambia County will repave Old Palafox Road from East Roberts Boulevard to Nine Mile Road to improve the road surface and driving quality in the City of Pensacola. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-08-25 | 2011-01-19 | 428776 | 2.182
2500 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA531 | Escambia County will repave Old Palafox Road from Memory Lane to Nine Mile Road to improve the road surface and driving quality in the City of Pensacola. | Pavement Improvement | 2009-10-29 | 2009-11-02 | 2010-09-04 | 2011-01-18 | 1210430 | 4.342
2501 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA532 | Escambia County will repave Copter Road to improve the road surface and driving quality. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-06-26 | 2010-08-19 | 283170 | 0.428
2502 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA533 | "Along with pedestrian safety improvements, Escambia County will repave ""W"" Street to improve the road surface and driving quality." | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-09-24 | 2011-03-31 | 1645398 | 3.081
2503 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA534 | Escambia County will repave Dog Track Road from Blue Angel Parkway to US 98 to improve the road surface and driving quality. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-07-06 | 2010-06-07 | 473189 | 2.084
2504 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA535 | Escambia County will repave East Johnson Avenue to improve the road surface and driving quality. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-07-06 | 2010-07-06 | 243267 | 0.845
2505 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA536 | Escambia County will repave Beulah Road to improve the road surface and driving quality. | Pavement Improvement | 2010-04-20 | 2010-04-26 | 2011-06-30 | 2010-11-09 | 650715 | 1.350
2506 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA537 | Escambia County will construct a five-foot wide sidewalk along Broad Street to improve pedestrian safety. | Transportation Enhancements | 2009-10-13 | 2009-10-19 | 2010-04-17 | 2010-04-16 | 96201 | 0.468
2507 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA538 | Add Sidewalks along Gulf Front Park from Maple Street to Oak Street in the City of Anna Maria to improve safety for pedestrians in the area. | Transportation Enhancements | 2009-09-16 | 2009-11-09 | 2012-03-26 | 2009-11-30 | 6452
2508 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA539 | BIKE PATH/TRAIL WITHLACOOCHEE TRAIL CONNECTION FROM N TRAIL E ND TO NE OF US 41 & RIVER IN CITRUS COUNTY, FLORIDA. | Transportation Enhancements | 2006-05-05 |  |  |  | 320000
2509 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARION |  | Multiple | ARRA540 | This project was awarded from the Florida Department of Environmental Protection to Marion County and includes improvements to a bicycle/pedestrian trail. | Transportation Enhancements | 2010-03-08 | 2010-03-08 | 2010-12-31 | 2010-12-02 | 2000000
2510 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LIBERTY |  | 02 | ARRA541 | Liberty County will construct approximately one mile of sidewalk along County Road 12 leading to Tolar Elementary School to improve pedestrian safety in the City of Bristol. | Transportation Enhancements | 2009-12-02 | 2009-12-07 | 2010-06-04 | 2010-06-04 | 219582 | 0.809
2511 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | WAKULLA | TALLAHASSEE | 02 | ARRA542 | This project will improve safety for motorists by providing a left turn lane onto Aaron Strickland Road north of the City of Crawfordville. | Pavement Widening | 2010-02-01 | 2010-02-15 | 2010-05-27 | 2010-05-14 | 174680 | 0.287
2512 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA543 | Add a new sidewalk along Cape Coral Parkway from Agualinda Boulevard to 16th Place in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 2009-11-17 | 2009-11-23 | 2010-05-31 | 2010-06-01 | 102495 | 0.846
2513 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA544 | Widen Six Mile Cypress Parkway from two to four lanes from Daniels Parkway to Winkler Extension to reduce congestion and enhance safety. | Pavement Widening | 2010-10-04 | 2010-10-04 | 2011-12-28 |  | 4030000 | 3.080
2514 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA545 | Add a new sidewalk along Nicholas Parkway from State Road 78 to Santa Barbara Boulevard in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 2009-11-17 | 2010-03-29 | 2010-10-31 | 2011-06-29 | 271934 | 1.344
2515 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA546 | Add a new sidewalk along Beach Parkway from Surfside Boulevard to Chiquita Boulevard in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 2009-11-17 | 2010-06-30 | 2011-04-01 | 2011-04-28 | 402282 | 1.935
2516 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA547 | This State Road 40 project in the City of Ormond Beach will provide an eight-foot wide bike/pedestrian trail in a residential community. | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-07-29 | 2010-06-24 | 171063 | 0.969
2517 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA549 | "On the southeast side of Jacksonville, State Road 9B, a new four-lane highway, will relieve congestion on the heavily traveled U.S. 1 and Old St. Augustine Road corridors." | New Construction | 2008-11-20 | 2009-01-01 | 2012-12-31 |  | 64363717 | 3.593
2518 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA550 | "On the southeast side of Jacksonville, State Road 9B, a new four-lane highway, will relieve congestion on the heavily traveled U.S. 1 and Old St. Augustine Road corridors." | New Construction | 2010-02-05 | 2010-01-20 | 2012-08-30 |  | 11435951 | 0.501
2519 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA551 | "In Citrus County, this project repaves 2.4 miles of Independence Highway from State Road 44 to U.S. 41 to improve the road surface." | Pavement Improvement | 2010-04-04 | 2010-04-06 | 2010-06-19 | 2010-05-07 | 424144 | 2.412
2520 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA552 | "In Hernando County, due to the poor condition of the road, this project resurfaces 1.6 miles of County Road 574 from California Street to Broad Street (U.S. 41)." | Pavement Improvement | 2010-05-21 | 2010-10-10 | 2010-11-08 | 2010-11-23 | 434286 | 1.595
2521 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA553 | "In Hernando County, this project repaves 2.5 miles of the asphalt surface of County Road 541 from Mountain View Blvd. to State Road 50 to improve the road surface." | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-11-28 | 2011-04-12 | 1117356 | 2.450
2522 | Completed | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | PASCO | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 05 | ARRA554 | "In Pasco County, this project replaces the asphalt surface and constructs improvements for easier access at the interchange of State Road 54 and the Suncoast Parkway." | Pavement Improvement | 2010-07-26 | 2010-07-26 | 2011-06-24 | 2011-08-04 | 3421749 | 1.243
2523 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | LEE |  | 14 | ARRA555 | Widen Interstate 75 from Colonial Boulevard to State Road 82 in Southwest Florida from four to six lanes to move daily traffic and commerce more efficiently. | Pavement Widening | 2009-12-15 | 2009-12-21 | 2050-07-29 |  | 9699677 | 1.536
2524 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | Multiple | ARRA556 | ADD SPECIAL USE LANE I-95/EXPRESS/HOT LNS FROM DADE/BROWARD CO LINE TO I-595/BROWARD P& R LOT (0007.700 MILES) IN BROWARD COUNTY, FLORIDA. | Pavement Widening | 2010-04-23 | 2010-04-23 | 2012-06-21 |  | 87007359 | 7.700
2525 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA557 | SIDEWALK CITY OF GRETNA FOURTH STREET SIDEWALK 2009 ECONOMIC STIMULUS (0000.285 MILES) IN GADSDEN COUNTY, FLORIDA. | Transportation Enhancements | 2010-03-08 | 2010-03-08 | 2010-05-21 | 2010-05-14 | 39762 | 0.285
2526 | Underway | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | HENDRY |  | Multiple | ARRA558 | WIDEN/RESURFACE EXIST LANES CR 832 (KERI ROAD) FROM SR 29 TO 13.1 MILES E OF SR 29 (0013.100 MILES) IN HENDRY COUNTY, FLORIDA. | Pavement Improvement | 2009-07-22 | 2010-05-10 | 2012-02-24 |  | 2428505 | 13.100
2527 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA559 | RESURFACING HABEN BLVD FROM US 301 TO US 41 (0001.044 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 2009-09-22 | 2010-01-18 | 2012-03-12 |  | 807963 | 1.044
2528 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA560 | SIDEWALK SR 79 SIDEWALKS PHASE II 2009 ECONOMIC STIMULUS (0000.433 MILES) IN HOLMES COUNTY, FLORIDA. | Transportation Enhancements | 2010-02-17 | 2010-02-17 | 2012-05-24 | 2010-06-17 | 85226 | 0.433
2529 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA561 | RESURFACING BRENTWOOD DRIVE FROM FEC RAILROAD TO DERBYSHIRE ROAD (0001.478 MILES) IN VOLUSIA COUNTY, FLORIDA. | Pavement Improvement | 2010-06-04 | 2010-06-14 | 2010-10-13 | 2010-08-30 | 131931 | 1.478
2530 | Completed | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE |  | 06 | ARRA562 | BRIDGE REPLACEMENT PICCIOLA ROAD BRIDGE FROM SABLE PALM DRIVE TO EAST OF LAKE UNITY RD (0000.352 MILES) IN LAKE COUNTY, FLORIDA. | Bridge Replacement | 2010-07-19 | 2010-08-18 | 2011-08-18 | 2011-09-01 | 4296064 | 0.352
2531 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA563 | RESURFACING SE LAKE WEIR AVENUE FROM SE 31ST STREET TO S OF SE 38TH STREET (0000.564 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2010-06-16 | 2010-07-12 | 2010-11-09 | 2010-08-31 | 152901 | 0.564
2532 | Completed | C220,C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA564 | PAVE SHOULDERS SR 300 FRANKLIN BLVD FROM W BAYSHORE DRIVE TO ST GEORGE ISLAND BR (0000.163 MILES) IN FRANKLIN COUNTY, FLORIDA. | Transportation Enhancements | 2010-04-28 | 2010-04-28 | 2012-06-24 | 2011-07-29 | 247925 | 0.163
2533 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA565 | Resurface State Road 64 (Manatee Avenue) from 12th East to 15th Street West to improve the surface of this heavily traveled road. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2011-03-16 |  | 1083242 | 1.321
2534 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | LIBERTY |  | 02 | ARRA566 | SIDEWALK CR 12 SIDEWALK PHASE II 2009 ECONOMIC STIMULUS (0000.358 MILES) IN LIBERTY COUNTY, FLORIDA. | Transportation Enhancements | 2010-03-23 | 2010-03-23 | 2012-06-22 | 2011-02-17 | 67808 | 0.358
2535 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 10 | ARRA567 | BIKE PATH/TRAIL NORTH BAY TRAIL (1ST ST) FROM 30TH AVE N TO 54TH AVE N IN PINELLAS COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-12 | 2010-05-12 | 2011-08-19 |  | 1026823
2536 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA568 | RESURFACING CR490(HOMOSASSA TRL) FROM US 19 TO SR 44 (0006.184 MILES) IN CITRUS COUNTY, FLORIDA. | Pavement Improvement | 2010-05-09 | 2010-05-09 | 2010-08-09 | 2010-06-25 | 857648 | 6.184
2537 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA569 | RESURFACING WISCON RD FROM SR 50 TO US 41 (0004.224 MILES) IN HERNANDO COUNTY, FLORIDA. | Pavement Improvement | 2010-05-23 | 2010-05-23 | 2010-08-15 | 2010-07-08 | 780871 | 4.224
2538 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA570 | RESURFACING SPARTA ROAD FROM SR 66 TO ORDAY ROAD (0001.400 MILES) IN HIGHLANDS COUNTY, FLORIDA. | Pavement Improvement | 2009-09-15 | 2010-03-29 | 2012-03-23 | 2010-10-01 | 377298 | 1.400
2539 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | COLLIER | NAPLES | Multiple | ARRA571 | BRIDGE REHABILITATION MOORINGLINE DRIVE AT BRIDGE #030125 (0000.001 MILES) IN COLLIER COUNTY, FLORIDA. | Pavement Improvement | 2009-07-22 | 2010-07-13 | 2012-02-24 | 2011-04-06 | 540512 | 0.001
2540 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA572 | SIDEWALK DOWNTOWN OCALA BIKE/PED IMPROVEMENTS BROADWAY & SW 1ST AVE IN MARION COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-18 | 2010-06-15 | 2010-12-15 | 2010-11-15 | 225465
2541 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA573 | RESURFACING NW/SW 27TH AVENUE FROM SW 20TH STREET TO NW OLD BLITCHTON ROAD (0001.994 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2010-06-16 | 2010-07-01 | 2010-12-28 | 2010-09-10 | 756147 | 1.994
2542 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA574 | RESURFACING CR 470 FROM LAKE PANASOFKEE OUTF ALL CANAL TO SR 44 (0004.642 MILES) IN SUMTER COUNTY, FLORIDA. | Pavement Improvement | 2010-06-01 | 2010-06-15 | 2010-10-13 | 2010-11-08 | 1010963 | 4.642
2543 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA575 | RESURFACING CR 476 E FROM US 301 TO SR 471 (0003.163 MILES) IN SUMTER COUNTY, FLORIDA. | Pavement Improvement | 2010-06-01 | 2010-06-15 | 2010-11-12 | 2010-09-30 | 733015 | 3.163
2544 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA576 | RESURFACING SE 25TH AVENUE FROM SR 464 TO SR 40 (0001.099 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2010-08-10 | 2010-08-23 | 2011-01-19 | 2010-12-23 | 388072 | 1.099
2545 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA577 | RESURFACING OLD DIXIE HWY FROM HAWTHORNE AVENUE TO RICHARD MARK DR (0001.582 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2010-08-03 | 2010-08-16 | 2010-09-25 | 2010-10-07 | 218889 | 1.582
2546 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 08 | ARRA578 | RESURFACING BOGGY CREEK RD FROM CR 530 (BOGGY CREEK) TO W OF CR15 (NARCOOSEE) (0006.036 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Improvement | 2011-03-18 | 2011-03-21 | 2011-08-31 | 2011-08-22 | 890717 | 6.036
2547 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA579 | RESURFACING CANOE CREEK RD FROM S OF JOE OVERSTREET RD TO S KENANSVILLE RD (0015.122 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Improvement | 2011-03-22 | 2011-04-04 | 2011-08-31 | 2011-10-26 | 1880452 | 15.122
2548 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA580 | RESURFACING CR 318 FROM CR 315 INTERSECTION TO 1.75 W OF CR 315 (0001.735 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2010-07-13 | 2010-08-02 | 2010-10-31 | 2010-11-11 | 648735 | 1.735
2549 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | Multiple | ARRA581 | SIDEWALK SR40 MULTI-USE TRAIL (PHASE II) OLD TOMOKA RD TO BREAKAWAY TRAILS (0001.120 MILES) IN VOLUSIA COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-21 | 2010-06-14 | 2010-11-11 | 2010-09-22 | 172214 | 1.120
2550 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 24 | ARRA582 | INTERSECTION IMPROVEMENT WATERFORD CHASE PARK WAY AT AVALON PARK BLVD INTERSECTION (0000.105 MILES) IN ORANGE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-11-04 | 2010-11-08 | 2011-05-06 | 2011-03-30 | 298887 | 0.105
2551 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SUWANNEE |  | 02 | ARRA583 | BIKE PATH/TRAIL SR 49 (US 129) FR:WM.GUY LEMMON MEM.PARK TO SR 20 (US 27) (0002.706 MILES) IN SUWANNEE COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-25 | 2010-06-25 | 2011-02-19 | 2011-03-04 | 646143 | 2.706
2552 | Underway | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUWANNEE |  | 02 | ARRA584 | WIDEN/RESURFACE EXIST LANES CR 252 FROM US 129 TO CR 137 (0008.493 MILES) IN SUWANNEE COUNTY, FLORIDA. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2011-02-06 |  | 3462504 | 8.493
2553 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA585 | SIDEWALK OLD SPANISH TRAIL FROM LOCKEY AVE TO 3RD AVE (0001.760 MILES) IN JACKSON COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-15 | 2010-07-12 | 2011-01-08 | 2011-01-28 | 320028 | 1.760
2554 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | SANTA ROSA | PENSACOLA | 01 | ARRA586 | ADD LANES & RECONSTRUCT SR 87 FROM N OF FIVE FORKS ROAD TO EGLIN AFB BOUNDARY (0003.025 MILES) IN SANTA ROSA COUNTY, FLORIDA. | Pavement Widening | 2010-07-20 | 2010-08-16 | 2012-10-13 |  | 17182109 | 3.025
2555 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | BAY | PANAMA CITY | 02 | ARRA587 | RESURFACING 11TH STREET RESURFACING (0001.925 MILES) IN BAY COUNTY, FLORIDA. | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2010-12-16 | 2011-02-09 | 1000000 | 1.925
2556 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA588 | RESURFACING SMITH STREET RESURFACING (0000.200 MILES) IN JACKSON COUNTY, FLORIDA. | Pavement Improvement | 2010-07-16 | 2010-07-16 | 2012-08-03 | 2011-09-08 | 78281 | 0.200
2557 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | JEFFERSON |  | Multiple | ARRA589 | RESURFACING NORTH SALT ROAD PHASE II RESURFACING (0000.939 MILES) IN JEFFERSON COUNTY, FLORIDA. | Pavement Improvement | 2010-04-20 | 2010-04-20 | 2012-07-14 | 2011-02-25 | 175992 | 0.939
2558 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH, FL | Multiple | ARRA590 | ADD SPECIAL USE LANE I-95/EXPRESS/HOT LNS FROM N. OF GOLDEN GLADES TO DADE/BROWARD CO LINE (0003.892 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Widening | 2010-04-23 | 2010-04-23 | 2012-06-21 |  | 17642344 | 7.260
2559 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA592 | PUBLIC TRANSPORTATION SHELTER ARRA BROWARD COUNTY CNTYWDE PASNGER SHELTERS VARIOUS LOCATIONS IN BROWARD COUNTY, FLORIDA. | Other | 2010-05-19 | 2010-05-19 | 2012-07-04 |  | 2623316
2560 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA593 | SIDEWALK WEST CASTILLO DRIVE FROM: SR 5 (US 1) TO: SR 5A/SAN MARCO AVE. (0000.277 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Transportation Enhancements | 2009-06-16 | 2009-06-16 | 2012-07-03 |  | 177230 | 0.277
2561 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA594 | TRAFFIC OPS IMPROVEMENT SR 207 @ SR 312 (0000.013 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Safety/Traffic Management | 2009-06-16 | 2009-06-16 | 2012-08-20 |  | 1141965 | 0.013
2562 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA595 | TRAFFIC OPS IMPROVEMENT SR A1A/SR 200 @ BLACKROCK ROAD (0000.001 MILES) IN NASSAU COUNTY, FLORIDA. | Safety/Traffic Management | 2009-06-16 | 2009-06-16 | 2012-07-09 |  | 794513 | 0.001
2563 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 06 | ARRA596 | WIDEN/RESURFACE EXIST LANES CR 220 FROM: CR 209 TO: BLANDING BLVD. (0003.078 MILES) IN CLAY COUNTY, FLORIDA. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2012-06-05 |  | 1608047 | 3.078
2564 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA597 | RESURFACING 9TH STREET FROM: OSCEOLA AVENUE TO: ST. JOHNS C/L (0000.182 MILES) IN DUVAL COUNTY, FLORIDA. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2012-07-09 |  | 1145116 | 0.182
2565 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA598 | RESURFACING OLD DIXIE HIGHWAY FROM: SR 312 TO: SR 207 (0000.227 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Pavement Improvement | 2010-07-23 | 2010-07-23 | 2012-08-20 |  | 352276 | 0.227
2566 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA599 | SIDEWALK CR 107 BLACKROCK RD FROM: WINDSOR DRIVE TO: HERRON ISLES PKWAY (0001.611 MILES) IN NASSAU COUNTY, FLORIDA. | Transportation Enhancements | 2009-06-16 | 2009-06-16 | 2012-07-09 |  | 362537 | 1.611
2567 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 06 | ARRA600 | RESURFACING MOODY AVENUE FROM: DRS. LAKE ROAD TO: PE0RIA (0001.880 MILES) IN CLAY COUNTY, FLORIDA. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2012-06-05 |  | 920147 | 1.880
2568 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 06 | ARRA601 | RESURFACING CAHOON AVENUE FROM: DEVOE STREET TO: CANNON STREET (0000.297 MILES) IN DUVAL COUNTY, FLORIDA. | Pavement Improvement | 2010-05-01 | 2010-03-31 | 2012-07-09 |  | 196936 | 0.297
2569 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA602 | BRIDGE-REPAIR/REHABILITATION CR 214 BRIDGE OVER I-95 (0000.044 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Bridge Improvement | 2009-06-16 | 2009-06-16 | 2012-08-20 |  | 168364 | 0.044
2570 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 03 | ARRA603 | TRAFFIC OPS IMPROVEMENT SR 224/KINGSLEY AVE. FROM: PLAINFIELD AVENUE TO: SMITH STREET (0000.438 MILES) IN CLAY COUNTY, FLORIDA. | Safety/Traffic Management | 2009-06-16 | 2009-06-16 | 2012-06-05 |  | 95099 | 0.438
2571 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA604 | RESURFACING CR 13B/FRUIT COVE RD FROM: SR 13 TO: SR 13 (0002.381 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2012-08-20 |  | 1039151 | 2.381
2572 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA605 | RESURFACING LONGWOOD-LK MARY RD FROM CR 427 TO LAKE MARY BLVD (0002.597 MILES) IN SEMINOLE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-07 | 2011-02-07 | 2011-03-31 | 2011-05-27 | 1050910 | 2.597
2573 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 22 | ARRA606 | LANDSCAPING SE 10TH STREET FROM STATE ROAD A-1-A TO OCEAN WAY (0000.137 MILES) IN BROWARD COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-22 | 2010-06-21 | 2010-12-11 | 2011-05-27 | 358576 | 0.137
2574 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA | GAINESVILLE | 06 | ARRA607 | SIDEWALK SR 121/NW 34TH ST. SR 222/NW 39TH AVE/MP5.86 TO NW 55TH BLVD /MP7.730 (0001.870 MILES) IN ALACHUA COUNTY, FLORIDA. | Transportation Enhancements | 2009-08-04 | 2009-06-15 | 2010-10-19 |  | 288450 | 1.870
2575 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | OKEECHOBEE |  | 16 | ARRA608 | SIDEWALK OKEECHOBEE SIDEWALKS AT VARIOUS LOCATIONS IN OKEECHOBEE COUNTY, FLORIDA. | Transportation Enhancements | 2009-09-21 | 2010-04-14 | 2012-03-16 | 2010-11-06 | 285221
2576 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | DE SOTO |  | 13 | ARRA609 | BRIDGE-ROUTINE MAINTENANCE CR 761 (CR 769) AT BRIDGE #040004 (0000.090 MILES) IN DESOTO COUNTY, FLORIDA. | Pavement Improvement | 2009-09-16 | 2010-05-04 | 2012-03-14 | 2011-05-20 | 389204 | 0.090
2577 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA610 | SIDEWALK 4TH STREET FROM US 17 TO SCHOOL HOUSE RD IN HARDEE COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-04 | 2010-05-04 | 2010-10-26 | 2010-10-28 | 136253
2578 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | DE SOTO |  | 13 | ARRA611 | SIDEWALK POLK STREET FROM MAGNOLIA STREET TO HICKORY STREET IN DESOTO COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-04 | 2010-05-04 | 2010-10-26 | 2010-10-28 | 54484
2579 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | GLADES |  | 16 | ARRA612 | BIKE PATH/TRAIL VANCE WHIDDEN PARK IN GLADES COUNTY, FLORIDA. | Transportation Enhancements | 2010-04-13 | 2010-04-13 | 2010-11-06 | 2010-09-30 | 257476
2580 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA613 | ADD LANES & REHABILITATE PVMNT I-75 FROM S OF SR 82 TO S OF LUCKETT ROAD (0001.529 MILES) IN LEE COUNTY, FLORIDA. | Pavement Widening | 2005-03-16 | 2010-03-09 | 2012-06-10 |  | 8347079 | 1.529
2581 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PASCO |  | 05 | ARRA614 | SIDEWALK US 301/98 (SR35/700) FROM DADE CITY AVE TO US 98 BYPASS (0001.098 MILES) IN PASCO COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-08 | 2010-06-14 | 2011-01-04 | 2011-01-18 | 560740 | 1.098
2582 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA615 | LIGHTING US 17 (SOUTHBOUND) FROM MAIN STREET TO HARDEE STREET (0000.491 MILES) IN HARDEE COUNTY, FLORIDA. | Transportation Enhancements | 2009-09-21 | 2010-04-13 | 2012-03-21 | 2011-03-15 | 369410 | 0.491
2583 | Underway | C220,C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA616 | PEDESTRIAN/WILDLIFE OVERPASS LEGACY TRAIL AT US 41 (0000.100 MILES) IN SARASOTA COUNTY, FLORIDA. | Transportation Enhancements | 2010-03-30 | 2010-09-16 | 2012-06-08 |  | 3015846 | 0.100
2584 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA617 | RESURFACING OLD DIXIE HWY FROM 12TH ST. TO SR-60 (0000.988 MILES) IN INDIAN RIVER COUNTY, FLORIDA. | Pavement Improvement | 2010-09-13 | 2010-11-17 | 2011-01-25 | 2011-05-03 | 411016 | 0.988
2585 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA618 | PAVE SHOULDERS BUCKINGHAM ROAD FROM NEAL ROAD TO GUNNERY ROAD (0002.401 MILES) IN LEE COUNTY, FLORIDA. | Pavement Improvement | 2010-11-08 | 2010-11-09 | 2011-03-09 |  | 390943 | 2.401
2586 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HENDRY |  | Multiple | ARRA619 | SIDEWALK NW/NE EUCALYPTUS BLVD FROM COWBOY WAY TO COLLINSWOOD PKWY IN HENDRY COUNTY, FLORIDA. | Transportation Enhancements | 2010-07-16 | 2010-07-19 | 2010-11-19 | 2011-01-21 | 190165
2587 | Completed | C220,C200 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA620 | SIDEWALK OAK STREET SIDEWALKS (0000.506 MILES) IN FRANKLIN COUNTY, FLORIDA. | Transportation Enhancements | 2010-04-14 | 2010-04-14 | 2012-06-24 | 2011-07-29 | 168606 | 0.506
2588 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA621 | INTERSECTION IMPROVEMENT CITY OF WEST MIAMI FROM S.W. 64 AVENUE @ S.W. 15 STREET (0000.017 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-05-24 | 2010-06-02 | 2010-10-22 | 2011-03-18 | 46171 | 0.017
2589 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA622 | BRIDGE REPLACEMENT CR 305 5.48 MILES SOUTH OF SR 100 (0000.258 MILES) IN FLAGLER COUNTY, FLORIDA. | Bridge Replacement | 2010-10-20 | 2010-11-08 | 2011-05-07 | 2011-03-15 | 908626 | 0.258
2590 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA623 | SIDEWALK MARION OAKS TRAIL FROM SW 63RD TERRACE TO SW 31ST AVENUE IN MARION COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-04 | 2010-06-08 | 2010-11-05 | 2010-09-09 | 241681
2591 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | Multiple | ARRA624 | SIDEWALK COGAN DRIVE SIDEWALK FROM TORRENCE AVENUE TO BABCOCK STREET (0000.950 MILES) IN BREVARD COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-07 | 2010-06-14 | 2010-10-12 | 2010-09-12 | 71904 | 0.950
2592 | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA625 | RESURFACING PALM COAST PARKWAY FROM OLD KINGS ROAD TO PALM HARBOR PARKWAY (0001.818 MILES) IN FLAGLER COUNTY, FLORIDA. | Pavement Improvement | 2010-05-16 | 2010-05-16 | 2010-07-15 | 2010-06-15 | 258117 | 1.818
2593 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA626 | SIDEWALK BELLE TERRE PKWAY MULTI USE PATH FROM PINE GROVE TO PINE LAKES PKWY (0001.936 MILES) IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-10 | 2010-06-11 | 2010-09-21 | 2010-10-22 | 319809 | 1.936
2594 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA627 | SIDEWALK NORTH LOCKWOOD BLVD FROM ASHLAND TRAIL TO CR 426 IN SEMINOLE COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-09 | 2010-06-28 | 2010-11-05 | 2010-08-26 | 180758
2595 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA628 | RESURFACING RINEHART ROAD FROM CR 46-A TO TOWNE CENTER BLVD. (0000.796 MILES) IN SEMINOLE COUNTY, FLORIDA. | Pavement Improvement | 2010-06-18 | 2010-06-21 | 2010-09-18 | 2010-08-19 | 261601 | 0.796
2596 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA629 | RESURFACING US 19 (SR 55) FROM NW SNUG HARBOR RD TO W CORNFLOWER DR (0007.476 MILES) IN CITRUS COUNTY, FLORIDA. | Pavement Improvement | 2010-06-06 | 2010-06-06 | 2011-02-20 | 2011-04-20 | 3084333 | 7.476
2597 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA630 | FLEXIBLE PAVEMENT RECONSTRUCT. WEST 53RD STREET FROM WEST 16TH AVENUE TO WEST 12TH AVENUE (0000.499 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-01-10 | 2011-01-11 |  |  | 836349 | 0.499
2598 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA631 | FLEXIBLE PAVEMENT RECONSTRUCT. WEST 36 AVENUE FROM WEST 76 STREET TO WEST 84 STREET (0000.498 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2010-12-31 | 2011-07-08 | 661394 | 0.498
2599 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA632 | RESURFACING CR 292A GULF BEACH HIGHWAY RESURFACING (0006.842 MILES) IN ESCAMBIA COUNTY, FLORIDA. | Pavement Improvement | 2010-06-21 | 2010-06-21 | 2012-08-14 | 2011-09-14 | 2159733 | 6.842
2600 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA633 | RESURFACING CR 1087 RESURFACING (0008.656 MILES) IN WALTON COUNTY, FLORIDA. | Pavement Improvement | 2011-03-01 | 2011-03-01 |  |  | 1745986 | 8.656
2601 | Underway | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA634 | RESURFACING CR 10A HERITAGE ROAD /OLD COTTONDALE ROAD RESURFACING (0001.696 MILES) IN JACKSON COUNTY, FLORIDA. | Pavement Improvement | 2010-07-16 | 2010-07-16 | 2012-08-03 |  | 328810 | 1.696
2602 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA635 | PEDESTRIAN SAFETY IMPROVEMENT LAFAYETTE STREET PEDESTRIAN SAFETY PROJECT @ CSX R/R OVERPASS (0000.038 MILES) IN LEON COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-24 | 2010-06-24 | 2012-07-31 |  | 1259986 | 0.038
2603 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 10 | ARRA636 | INTERSECTION IMPROVEMENT US 19 (SR 55) FROM S OF MCCORMICK DR TO N OF ENTERPRISE RD (0000.957 MILES) IN PINELLAS COUNTY, FLORIDA. | Safety/Traffic Management | 2010-05-26 | 2010-06-21 | 2011-10-24 |  | 3359263 | 0.957
2604 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA637 | RESURFACING SR 200 (US 301) FROM NE 76TH PLACE TO SR 24 (0011.838 MILES) IN ALACHUA COUNTY, FLORIDA. | Pavement Improvement | 2010-06-07 | 2010-09-07 | 2011-03-27 | 2011-04-25 | 3741760 | 11.838
2605 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | WEST PALM BEACH | 22 | ARRA638 | RESURFACING I-95 PAVEMENT REPAIR FROM S. OF LINTON BLVD TO THE L-30 CANAL BRIDGE (0003.876 MILES) IN PALM BEACH COUNTY, FLORIDA. | Pavement Improvement | 2007-07-01 | 2010-05-24 | 2012-07-06 |  | 2850994 | 3.876
2606 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA639 | RESURFACING SR 5/OVERSEAS HWY. FM N OF 37 ST./MM49.1 TO N OF COCOPLUM DR./MM 54.6 (0005.452 MILES) IN MONROE COUNTY, FLORIDA. | Pavement Improvement | 2010-06-24 | 2011-01-10 | 2011-06-08 |  | 773660 | 5.452
2607 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA640 | RESURFACING BUMBY AVENUE FROM SR15 (SOUTH ST) TO SR 50 (COLONIAL DR) (0000.508 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2010-09-28 | 2010-10-04 | 2011-05-02 | 2011-04-04 | 987971 | 0.508
2608 | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA641 | TRAFFIC CONTROL DEVICES/SYSTEM SR 500 US 192 FROM I-95 SB RAMPS TO E OF WICKHAM/MINTON RD IN BREVARD COUNTY, FLORIDA. | Safety/Traffic Management | 2011-07-11 | 2011-07-11 |  |  | 762730
2609 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 24 | ARRA642 | TRAFFIC OPS IMPROVEMENT MITCHELL HAMMOCK RD AT MANIGAN, EASTBRIDGE AND SHARON (0000.292 MILES) IN SEMINOLE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-09-10 | 2010-10-04 | 2011-02-01 | 2011-01-20 | 183978 | 0.292
2610 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA643 | RESURFACING MURRELL ROAD FROM S OF LUTHER DRIVE TO BARTON BLVD (0000.384 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-02 | 2010-09-02 | 2010-11-02 | 2011-02-08 | 51495 | 0.384
2611 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA644 | RESURFACING DESOTO PARKWAY FROM .17 MI E OF SR 513 TO 100' E OF TEMPLE ST (0000.504 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-01 | 2010-09-07 | 2010-12-06 | 2010-11-06 | 72330 | 0.504
2612 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA645 | RESURFACING HOPKINS AVENUE FROM COUNTY CLUB DRIVE TO HARRISON STREET (0000.535 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-01 | 2010-09-01 | 2010-11-29 | 2011-02-17 | 100865 | 0.535
2613 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA646 | RESURFACING HARRISON STREET FROM FEC RAILROAD TO US 1 (0000.312 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-01 | 2010-09-01 | 2010-11-29 | 2011-02-17 | 59267 | 0.312
2614 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 24 | ARRA647 | TRAFFIC SIGNAL UPDATE KELLER ROAD AT WESTHALL LANE (0000.001 MILES) IN ORANGE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-08-05 | 2010-08-06 | 2011-02-11 | 2011-01-19 | 176029 | 0.001
2615 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA648 | BRIDGE REHABILITATION BOGGY CREEK RD BRIDGE IMPROVEMENT PHASE1 BRIDGE # 754120 (0000.034 MILES) IN ORANGE COUNTY, FLORIDA. | Bridge Improvement | 2011-05-03 | 2011-05-02 | 2011-06-30 | 2012-01-26 | 1232694 | 0.034
2616 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | Multiple | ARRA649 | TRAFFIC CONTROL DEVICES/SYSTEM SR 551 (GOLDENROD) & EDGEWATER DR TRAFFIC CON TROL SYSTEM (2 LOCATIONS) (0002.998 MILES) IN ORANGE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-01-21 | 2011-01-24 | 2011-12-31 | 2011-05-20 | 213226 | 2.998
2617 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA650 | RESURFACING ELLIS ROAD FROM JOHN RODES BLVD TO WEST OF WICKHAM RD (0000.660 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-02 | 2010-09-02 | 2010-11-02 | 2010-11-02 | 307252 | 0.660
2618 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA651 | TRAFFIC SIGNALS BOGGY CREEK ROAD AT TURNBERRY BOULEVARD INTERSECTION (0000.001 MILES) IN OSCEOLA COUNTY, FLORIDA. | Safety/Traffic Management | 2010-08-25 | 2010-08-26 | 2010-03-13 | 2011-03-13 | 197053 | 0.001
2619 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA652 | ADD TURN LANE(S) OSCEOLA PARKWAY ORANGE AVENUE / CR 527 (0000.001 MILES) IN OSCEOLA COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-22 | 2011-03-28 | 2010-12-31 | 2011-07-25 | 321793 | 0.001
2620 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA653 | RESURFACING SYKES CREEK PKWY FROM SR 520 TO MERRITT AVE (0000.291 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-02 | 2010-09-02 | 2011-01-10 | 2010-12-27 | 227862 | 0.291
2621 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA654 | RESURFACING APOLLO BLVD FROM AIRPORT BLVD TO SARNO RD (0001.818 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-08-19 | 2010-08-29 | 2011-01-10 | 2010-12-31 | 440725 | 1.818
2622 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA655 | RESURFACING LAKE WASHINGTON ROAD FROM WICKHAM ROAD TO CROTON ROAD (0001.019 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-08-26 | 2010-08-30 | 2010-12-28 | 2010-12-08 | 463362 | 1.019
2623 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA656 | RESURFACING CONROY-WINDERMERE RD FROM MAIN STREET TO HORIZON CIRCLE (0001.377 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2010-08-02 | 2010-08-02 | 2010-10-30 | 2010-10-01 | 288990 | 1.377
2624 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA657 | RESURFACING AYERS RD FROM US 41 TO CR 581 (CULBREATH RD) (0004.961 MILES) IN HERNANDO COUNTY, FLORIDA. | Pavement Improvement | 2010-11-29 | 2010-11-29 | 2010-12-10 | 2011-02-27 | 862027 | 4.961
2625 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA658 | SIDEWALK SE COMMERCE AVENUE FROM INDIAN STREET TO MONROE STREET (0001.130 MILES) IN MARTIN COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-07 | 2011-02-07 | 2011-12-31 | 2011-05-20 | 79677 | 1.130
2626 | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA659 | RESURFACING CR 476B FROM I-75 RAMPS TO CR 476 (0000.321 MILES) IN SUMTER COUNTY, FLORIDA. | Pavement Improvement | 2010-08-31 | 2010-09-14 | 2011-01-31 | 2011-02-01 | 718577 | 0.321
2627 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA661 | SIDEWALK BELLE TERRE TRAIL SIDEWALKS 2 LOCATIONS IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2010-10-26 | 2010-11-01 | 2011-04-30 | 2011-09-01 | 959797
2628 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA662 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMSN. DIST 1 & 2 - ADA BUS STOP ACCESS (VARIOUS LOCATION) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-11 | 2011-04-25 | 2012-02-28 |  | 522000
2629 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA663 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMMSN DISTRICT 8 & 12 - ADA BUS STOP ACCESS(VARIOUS LOCS) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-04 | 2011-04-12 | 2012-02-28 |  | 354143
2630 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA664 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 1, 2 & 6 PED SIGNAL LED UPGRADE - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-04 | 2011-04-04 | 2012-02-28 | 2011-11-15 | 772796
2631 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA665 | RESURFACING MIAMI-DADE CO COMMSN DISTRICT 11 - RESURFACING AT VARIOUS LOCATIONS IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-03-21 | 2011-03-21 |  |  | 1153415
2632 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA666 | RESURFACING N.W. 67 AVENUE FROM NW 188 TERR. TO NW 202 ST (MIAMI-DADE CMSN DIST 13) (0000.883 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-03-21 | 2010-08-31 | 2012-02-28 |  | 293593 | 0.883
2633 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA667 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMMSN DISTRICT 9 - ADA BUS STOP ACCESS(VARIOUS LOCATIONS) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-14 | 2011-03-28 | 2012-02-28 |  | 534950
2634 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA668 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMMSN DISTRICT 10-ADA BUS STOP ACCESS(VARIOUS LOCATIONS) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-16 | 2011-03-28 | 2012-02-28 |  | 588663
2635 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA669 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMMSN DISTRICT 11-ADA BUS STOP ACCESS(VARIOUS LOCATIONS) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-28 | 2011-04-04 | 2012-02-28 |  | 411838
2636 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA670 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMS DIST 7, 9 & 11 PED SIGNAL LED UPGRADE - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-14 | 2011-03-17 | 2012-02-28 | 2011-08-22 | 115341
2637 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA671 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMS DIST 8, & 10 PED SIGNAL LED UPGRADE - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-08-31 | 2010-08-31 | 2012-02-28 |  | 542129
2638 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA672 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DISTRICT 11 - PAVEMENT MARKINGS @ VAR LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-21 | 2011-03-21 |  |  | 37251
2639 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA673 | DRAINAGE IMPROVEMENTS S.W. 137 AVENUE FROM SW 72 ST. TO SW 56 ST. (MIAMI-DADE CMSN DIST 10) (0001.003 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-28 | 2011-02-28 | 2012-02-28 |  | 592134 | 1.003
2640 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA674 | BRIDGE REPLACEMENT N.W. 42 AVENUE AT NW 179 STREET (BRIDGE # 874023) (0000.017 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Bridge Replacement | 2010-10-19 | 2010-10-19 | 2012-03-01 |  | 667291 | 0.017
2641 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA675 | FLEXIBLE PAVEMENT RECONSTRUCT. N.E. 2 AVENUE FROM N.E. 51 STREET TO N.E. 57 STREET (0000.171 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-04-29 | 2011-05-23 | 2012-03-31 |  | 2220578 | 0.171
2642 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | Multiple | ARRA676 | RESURFACING SUNRISE & OLEANDER FROM OHIO STREET TO VIRGINIA AVENUE (0000.523 MILES) IN ST. LUCIE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2012-02-29 |  | 325601 | 0.523
2643 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | Multiple | ARRA677 | RESURFACING 29TH STREET FROM ORANGE AVENUE TO AVENUE Q (0001.250 MILES) IN ST. LUCIE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2012-02-29 |  | 323846 | 1.250
2644 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 22 | ARRA678 | RESURFACING SR5/US1/FEDERAL HWY FROM BROWARD/PALM BCH C/L TO SE 5TH STREET (0002.868 MILES) IN PALM BEACH COUNTY, FLORIDA. | Pavement Improvement | 2011-01-03 | 2011-04-25 |  | 2011-10-10 | 1004406 | 2.868
2645 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO | SPRING HILL | 05 | ARRA679 | BIKE PATH/TRAIL TOM VARN PARK FROM JB COMMUNITY CENTER TO MCKETHAN PARK IN HERNANDO COUNTY, FLORIDA. | Transportation Enhancements | 2011-05-02 | 2011-05-02 | 2012-12-31 | 2011-12-08 | 110966
2646 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA680 | SIDEWALK SR A1A NAT'L SCENIC BYWAY, BING'S LANDING CORRIDOR ENHANCEMENTS IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2011-03-30 | 2011-04-04 |  | 2011-09-30 | 182500
2647 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA681 | SIDEWALK WHITEVIEW TRAIL PINE LAKES TO RAVENWOOD & BELLE TERRE TO PINE GRV IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-24 | 2011-03-07 | 2011-07-31 | 2011-09-07 | 609925
2648 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA682 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 1,2,3,& 4 ILLUMINATE ST. NAME SIGNS-VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-21 | 2011-03-21 | 2012-02-28 | 2012-01-26 | 578154
2649 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA683 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 6 & 7 ILLUMINATED ST NAME SIGNS - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-28 | 2011-03-28 | 2012-02-28 | 2011-11-14 | 275518
2650 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA684 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 8 & 9 ILLUMINATED ST NAME SIGNS - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-11 | 2011-04-12 | 2012-02-28 | 2011-11-21 | 487128
2651 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA685 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 10,11 & 12 ILLUM ST. NAME SIGNS - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-25 | 2011-04-25 | 2012-02-28 | 2011-11-14 | 290050
2652 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | Multiple | ARRA686 | RESURFACING SLEEPY HOLLOW ROAD FROM SUNNYSIDE DRIVE TO S OF US 441 (0000.660 MILES) IN LAKE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-25 | 2011-03-10 |  | 2011-05-24 | 114549 | 0.660
2653 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA687 | RESURFACING PHELPS AVENUE FROM LOCHBERRY ROAD TO ALOMA AVENUE (0000.511 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2011-05-16 | 2011-05-16 |  | 2011-07-09 | 69961 | 0.511
2654 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 08 | ARRA688 | RESURFACING DYER BOULEVARD FROM US 192 TO COLUMBIA AVENUE (0000.249 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Improvement | 2010-12-29 | 2011-01-04 |  | 2011-03-04 | 84131 | 0.249
2655 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA689 | LIGHTING SR 5/BISCAYNE BLVD. FROM OLETA RIVER TO NE 214 STREET (0000.600 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-10-13 | 2012-01-02 | 2012-03-31 |  | 248549 | 0.600
2656 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA690 | BRIDGE REPLACEMENT ORANGE BLVD BRIDGE #774059 (0000.010 MILES) IN SEMINOLE COUNTY, FLORIDA. | Bridge Replacement | 2011-03-09 | 2011-03-14 | 2011-03-31 | 2011-06-06 | 825000 | 0.010
2657 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA691 | INTERSECTION IMPROVEMENT SW 64TH AVE/W. MIAMI FROM SW 20TH STREET TO SW 8TH ST/WEST MIAMI (0000.773 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-02-18 | 2011-02-21 | 2011-10-30 | 2011-05-17 | 30582 | 0.773
2658 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA692 | RESURFACING CR 318 FROM NE 52ND CT TO 1.75 MI W OF CR 315 (0007.670 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2011-01-26 | 2011-01-31 | 2011-07-31 | 2011-08-04 | 2859714 | 7.670
2659 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA693 | RESURFACING CR 200A FROM NE 100TH STREET TO US 301 (0007.223 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2011-01-26 | 2011-02-21 | 2011-07-31 | 2011-06-21 | 2534658 | 7.223
2660 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA694 | RESURFACING NE 25TH AVENUE FROM SR 40 TO NE 14TH STREET (0000.933 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2011-01-13 | 2011-01-24 | 2011-03-31 | 2011-04-23 | 323096 | 0.933
2661 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA695 | RESURFACING EMERSON DRIVE NW FROM JUPITER BLVD. TO MINTON ROAD (0004.415 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2011-01-04 | 2011-01-05 | 2011-07-31 | 2011-03-06 | 594577 | 4.415
2662 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 05 | ARRA696 | RESURFACING CR 48 FROM SUMTER COUNTY LINE TO CR 33 (0005.555 MILES) IN LAKE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-25 | 2011-03-10 | 2011-05-31 | 2011-05-24 | 1523870 | 5.555
2663 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 05 | ARRA697 | RESURFACING CR 452 FROM 0.1 MI N OF CR 44 TO 1.53 MI N OF CR 44 (0001.053 MILES) IN LAKE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-25 | 2011-03-17 | 2011-05-31 | 2011-06-15 | 400886 | 1.053
2664 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | Multiple | ARRA698 | RESURFACING CR 44 FROM W OF N SILVERLAKE RD TO POE STREET (0002.207 MILES) IN LAKE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-25 | 2011-03-31 | 2011-05-31 | 2011-06-14 | 316908 | 2.207
2665 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 05 | ARRA699 | BRIDGE REPLACEMENT LAKESHORE DRIVE FROM OSPREY POINTE BLVD TO SOUTH CLERMONT CONNECT (0003.585 MILES) IN LAKE COUNTY, FLORIDA. | Bridge Replacement | 2011-03-09 | 2011-03-24 | 2011-10-31 |  | 2412171 | 3.585
2666 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA700 | RESURFACING PLEASANT HILL ROAD FROM 17/92 TO REEDY CREEK BRIDGE N OF CYPRESS PKWY (0007.756 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Improvement | 2011-03-22 | 2011-04-04 | 2011-08-31 | 2011-11-09 | 2153198 | 7.756
2667 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA701 | RESURFACING LAKEMONT AVENUE FROM ALOMA AVENUE TO PINE AVENUE (0000.748 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2011-03-11 | 2011-03-11 | 2011-03-31 | 2011-06-01 | 202373 | 0.748
2668 | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 24 | ARRA702 | SIDEWALK CROSS SEMINOLE TRAIL PEDESTRIAN OVERPASS AT RED BUG AND SR 426 IN SEMINOLE COUNTY, FLORIDA. | Transportation Enhancements | 2011-05-24 | 2011-05-24 | 2012-08-31 | 2011-11-07 | 3520000
2669 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | Multiple | ARRA703 | RESURFACING NORTH WINTER PARK DR FROM RED BUG LAKE RD TO 7TH ST SOUTH (0002.863 MILES) IN SEMINOLE COUNTY, FLORIDA. | Pavement Improvement | 2011-04-04 | 2011-04-04 | 2011-05-31 |  | 1755370 | 2.863
2670 | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | KISSIMMEE | 15 | ARRA704 | ADD LANES & RECONSTRUCT HOAGLAND BLVD FROM 5TH STREET TO US 192 (0001.100 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Widening | 2011-04-28 | 2011-04-28 | 2012-06-30 |  | 4500000 | 1.100
2671 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 16 | ARRA705 | RESURFACING PORT ST. LUCIE BLVD. FROM SW GRECO LANE TO SW SANSOM LANE (0000.138 MILES) IN ST. LUCIE COUNTY, FLORIDA. | Pavement Improvement | 2009-12-31 | 2010-01-02 | 2011-12-31 |  | 520062 | 0.138
2672 | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA706 | BRIDGE REPLACEMENT STYLES CREEK BRIDGE ON PRINCESS PLACE RD REPLACE #734090 (0000.016 MILES) IN FLAGLER COUNTY, FLORIDA. | Bridge Replacement | 2011-09-19 | 2011-09-19 | 2011-09-30 |  | 560895 | 0.016
2673 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA707 | BRIDGE REHABILITATION SR 865 (SAN CARLOS BLVD) FROM ESTERO BLVD TO MAIN STREET (0000.643 MILES) IN LEE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-23 | 2011-02-23 |  |  | 569718 | 0.643
2674 | Underway | C220,C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA708 | SIDEWALK SR 166 CAVERNS RD FROM MARIANNA HIGH SCHOOL TO RUSSELL ROAD (0000.896 MILES) IN JACKSON COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-22 | 2011-02-22 |  |  | 128768 | 0.896
2675 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA709 | SIDEWALK CR 179A & CR 181 FROM NORTH RAILROAD ST TO FERN ARNOLD PARK (0000.429 MILES) IN HOLMES COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-22 | 2011-02-22 |  |  | 94422 | 0.429
2676 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA710 | PAVE SHOULDERS LEGION ROAD FROM SR 10 (US 90) TO WEST OF PARK ENTRANCE (0001.214 MILES) IN JACKSON COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-22 | 2011-02-22 |  |  | 215707 | 1.214
2677 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA711 | SIDEWALK CR 278 PIONEER ROAD FROM SR 77 WASHINGTON ST TO ROGERS REC COMPLEX (0000.634 MILES) IN WASHINGTON COUNTY, FLORIDA. | Transportation Enhancements | 2010-12-07 | 2010-12-07 | 2020-11-18 |  | 120317 | 0.634
2678 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA712 | SIDEWALK CR 279 MOSS HILL RD FROM VERNON HIGH SCHOOL TO SR 79 MAIN STREET (0001.601 MILES) IN WASHINGTON COUNTY, FLORIDA. | Transportation Enhancements | 2010-12-07 | 2010-12-07 | 2020-11-18 |  | 206926 | 1.601
2679 | Underway | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA713 | DRAINAGE IMPROVEMENTS CR 273 ORANGE HILL FROM S OF GILBERT MILL RD TO SR 277 VERNON HWY (0012.743 MILES) IN WASHINGTON COUNTY, FLORIDA. | Pavement Improvement | 2010-12-07 | 2010-12-07 | 2020-11-18 |  | 1376388 | 12.743
2680 | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | SANTA ROSA | PENSACOLA | 01 | ARRA714 | ADD LANES & RECONSTRUCT SR 281 AVALON BLVD FROM SR 8 (I-10) TO S OF MOOR'S LODGE (0000.905 MILES) IN SANTA ROSA COUNTY, FLORIDA. | Pavement Widening | 2011-02-07 | 2011-02-07 |  |  | 4045090 | 0.905
2681 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA715 | RESURFACING WEST 29TH STREET FROM SR 25/OKEECHOBEE RD. TO WEST 4TH AVENUE (0001.488 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2010-02-08 | 2010-03-02 | 2010-12-01 |  | 322084 | 1.488
2682 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA716 | RESURFACING LAKE MARY BOULEVARD FROM RINEHART ROAD TO COUNTRY CLUB ROAD (0001.524 MILES) IN SEMINOLE COUNTY, FLORIDA. | Pavement Improvement | 2011-01-28 | 2011-01-30 | 2011-02-28 | 2011-03-16 | 957405 | 1.524
2683 | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA717 | SIDEWALK PALM HARBOR TRAIL FROM HAMMOCK DUNES BRIDGE TO FERNMILL LANE IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2011-09-26 | 2011-10-11 | 2011-09-30 |  | 1122013
2684 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA718 | RESURFACING SR 61 (US 27) MONROE FROM PERKINS STREET TO SR 61 THOMASVILLE ROAD (0001.387 MILES) IN LEON COUNTY, FLORIDA. | Pavement Improvement | 2011-01-22 | 2011-02-08 | 2011-08-03 | 2011-12-02 | 849971 | 1.387
2685 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | Multiple | ARRA719 | SIDEWALK CR 224A/DRS. LAKE DR FROM: BIRDWOOD DRIVE TO: SR 224/KINGSLEY AVE (0000.368 MILES) IN CLAY COUNTY, FLORIDA. | Transportation Enhancements | 2010-03-30 | 2010-03-30 | 2012-06-05 |  | 166713 | 0.368
2686 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA720 | RESURFACING CR 200A/PAGES DAIRY FR: SR 15(US 17) TO: FELMORE ROAD (0001.235 MILES) IN NASSAU COUNTY, FLORIDA. | Pavement Improvement | 2010-05-01 | 2010-03-31 | 2012-07-09 |  | 781178 | 1.235
2687 | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA721 | BIKE PATH/TRAIL GOOD NEIGHBOR TRAIL PHASE IIA FROM JASMINE DR TO MONDON HILL RD IN HERNANDO COUNTY, FLORIDA. | Transportation Enhancements | 2011-04-01 | 2011-04-04 | 2012-12-31 | 2011-07-07 | 206626
2688 | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA722 | RESURFACING CR 675 (RUTLAND RD) FROM US 301 TO SR 64 (0011.136 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-28 | 2011-02-24 | 2012-03-28 |  | 1697663 | 11.136
2689 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA723 | RESURFACING 34TH STREET WEST FROM 53RD AVENUE WEST TO SR 684 (CORTEZ ROAD) (0000.482 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-28 | 2011-04-13 | 2012-03-28 | 2011-11-18 | 585203 | 0.482
2690 | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA724 | RESURFACING 43RD STREET WEST FROM SR 684 (CORTEZ RD) TO SR 64 (MANATEE AVE) (0001.707 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-28 | 2011-04-13 | 2012-03-28 | 2011-12-23 | 450476 | 1.707
2691 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA725 | FLEXIBLE PAVEMENT RECONSTRUCT. CR 663 FROM SR 62 TO POLK COUNTY LINE (0003.579 MILES) IN HARDEE COUNTY, FLORIDA. | Pavement Improvement | 2011-03-03 | 2011-03-03 |  | 2011-10-01 | 1737473 | 3.579
2692 | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA726 | ADD LANES & REHABILITATE PVMNT SR 50 (CORTEZ BLVD) FROM US 19 (SR 55) TO CR587/W OF MARINER BVD (0003.855 MILES) IN HERNANDO COUNTY, FLORIDA. | Other | 2011-01-24 | 2011-02-02 | 2011-06-28 | 2011-06-28 | 274702 | 3.855
2693 | Underway | C950 | Ferryboat | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRF001 | SEAPORT PRESERVATION PROJECT JACKSONVILLE MAYPORT FERRY TERMINAL IMPROVE. ARRA FUNDING IN DUVAL COUNTY, FLORIDA. | Other | 2009-11-20 | 2009-11-20 |  |  | 658041
2694 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 03 | 0000099 | This is an enhancement project in Muscogee County. The project construction consists of the construction of a 10 to 12 foot multi use trail beginning at Columbus State University and extending northe | Transportation Enhancements | 2009-09-23 | 2009-09-28 | 2011-05-15 |  | 663681 | 12.000
2695 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LANIER |  | 01 | 0000310 | This is a safety improvment project in Lanier County on SR 11/US 129. The project will realign on new location SR 11/US 129 and SR 31, 122/ US 221 to create two 90 degree intersections with SR 37 to | Pavement Widening | 2009-07-27 | 2009-08-03 | 2010-06-30 | 2010-07-27 | 1983740.28 | 1.050
2696 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | 0000424 | This project consists of reconstructing the existing intersection of SR 5 and Rose Avenue, located just north of I-20 in Douglas County. The existing intersection has an undesirable scissor-type confi | Safety/Traffic Management | 2009-07-27 | 2009-08-18 | 2011-02-28 | 2011-04-07 | 2604885.64 | 0.200
2697 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 05 | 0000608 | This project is a safety project in Atlanta in DeKalb County. The project will provide continuous ADA accessible sidewalks along both sides of Memorial Drive (S.R. 154) between Moreland Avenue and Ca | Transportation Enhancements | 2011-07-11 | 2012-01-06 | 2012-06-01 |  | 713600 | 1.010
2698 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | GORDON |  | 09 | 0000683 | This project is a bridge replacement project is Gordon and Murray counties. The bridge is located on County Road 134/County Line Road over Polecat Creek on the Gordon and Murray county line. Also, t | Bridge Replacement | 2009-07-27 | 2009-09-17 | 2013-05-31 | 2010-10-22 | 1482416 | 0.610
2699 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 08 | 0000842 | This project is an intersection improvement project in Newton County. This project will widen SR 162/Salem Road 6 ft. symmetrically to provide a north bound left turn lane. In addition, County Road | Safety/Traffic Management | 2009-11-03 | 2009-11-17 | 2010-12-31 | 2010-08-20 | 820632.7 | 0.320
2700 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MILLER |  | 02 | 0001361 | This project is a bridge replacement project in Miller County. The construction proposes to construct a new 160' x 44' concrete bridge on SR 91 over Dry Creek at the existing bridge site. The roadway | Bridge Replacement | 2009-10-23 | 2009-11-05 | 2010-11-30 | 2010-12-10 | 1956969.84 | 0.320
2701 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TATTNALL |  | 12 | 0001364 | This project is a bridge replacement on S.R. 56/Nail Bridge @ the Ohoopee River, 2 miles west of Reidsville in Tattnall County. The project length is 0.41 miles. | Bridge Replacement | 2009-07-28 | 2009-08-31 | 2010-09-30 | 2010-09-30 | 2831014.42 | 0.410
2702 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CLAY |  | 02 | 0001369 | This project will replace the structurally deficient bridge in Clay County on County Road 76 over Drag Nasty Creek with a new 180' x 28' reinforced concrete bridge. The existing approaches consist of | Bridge Replacement | 2009-07-06 | 2009-07-31 | 2010-09-30 | 2010-08-15 | 1206753.14 | 0.320
2703 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | GLYNN | BRUNSWICK | 01 | 0001558 | This project is the construction of safety turn lanes on SR 520 in Brantley and Glynn Counties. The project begins just west of the Brantley/Glynn County Line at its intersection with County Road 580 | Safety/Traffic Management | 2009-11-23 | 2010-04-23 | 2010-12-31 | 2011-02-11 | 4775607.92 | 11.410
2704 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | DOUGHERTY | ALBANY | 02 | 0001562 | This project is a safety improvement project in Dougherty County. This project consists of median opening improvements on SR 300/US 19 from the Mitchell County line to the Worth County line. At 25 l | Safety/Traffic Management | 2010-02-03 | 2010-05-13 | 2011-09-30 | 2011-08-23 | 7998375.83 | 18.230
2705 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BARTOW | ATLANTA | 11 | 0001574 | "This project is a safety improvement located on SR 3/US 41 in Bartow County. The project begins approximately at the Cobb/Bartow County line and extends north to the SR 293 Connector in Bartow Count | Safety/Traffic Management | 2009-08-18 | 2009-09-16 | 2011-05-31 | 2011-05-31 | 11263039.7 | 15.150
2706 | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | FLOYD | ROME | 11 | 0001575 | This project is a safety improvement that will construct turn lanes on SR 53 in Floyd County. The project will construct left and right turn lanes at fifteen intersections and four median crossovers | Safety/Traffic Management | 2009-11-30 | 2009-12-01 | 2011-09-30 |  | 7015514.31 | 9.930
2707 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0001794 | This project is a road widening in Richmond County. The project consists of the widening and reconstruction of Alexander Drive from Washington Road (SR 28) to Riverwatch Parkway (SR 104) in the City | Pavement Widening | 2010-01-12 | 2010-03-12 | 2012-12-31 |  | 8115912.6 | 0.870
2708 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | UNION |  | 09 | 0001918 | This project is a safety intersection improvement in Union County. SR 11/US 129 in Union County is a rural arterial route that currently consists of one southbound lane and one northbound lane. This | Safety/Traffic Management | 2010-03-23 | 2010-06-03 | 2011-09-30 | 2011-09-15 | 1937353.38 | 0.600
2709 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0002406 | This is a sidewalk construction project in Dekalb County. This project includes construction of sidewalks on both sides of SR 12/US 278/Covington Highway from SR 154/Memorial Drive to County Road 518 | Transportation Enhancements | 2009-07-27 | 2009-08-25 | 2010-08-31 | 2010-08-17 | 886822.43 | 1.580
2710 | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0002487 | This is a lighting project in the City of Macon in Bibb County, Georgia. This project installs 13 High Mast Lighting Towers & 6 wall-mounted luminaries for underpass lighting at the existing I-75 at | New Construction | 2011-04-13 |  | 2014-03-31 |  | 394450
2711 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 13 | 0002638 | This project is a roadway widening project in Henry County. The project is located on Eagle's Landing Parkway, 0.4 miles east of the I-75 interchange in Henry County. This project will continue the | Pavement Widening | 2009-08-31 | 2009-09-29 | 2012-02-27 |  | 23370448.45 | 2.600
2712 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CANDLER |  | 12 | 0002734 | This is a bridge replacement project in Candler County. The project is a bridge replacement on County Road 203/Glisson Road at Wolfe Creek. The existing bridge was constructed in 1955 and is structu | Bridge Replacement | 2009-08-26 | 2009-11-18 | 2011-09-30 | 2010-12-21 | 1208746.26 | 0.490
2713 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CANDLER |  | 12 | 0002841 | This project is a bridge replacement in Candler County. The project will replace the bridge on County Road 223/Portal Highway at Little Stocking Head Creek, 5 miles north of Metter. The existing bri | Bridge Replacement | 2009-07-28 | 2009-09-21 | 2010-12-31 | 2010-12-31 | 968761.6 | 0.350
2714 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CANDLER |  | 12 | 0002842 | This project will replace two bridges in Bulloch and Candler counties. The project will replace the bridge on County Road 223/Portal Highway at Big Branch and the bridge on County Road 223/Portal Hig | Bridge Replacement | 2009-07-28 | 2009-09-21 | 2010-12-31 | 2010-12-31 | 2288929.57 | 0.780
2715 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | 0002923 | This project is a roadway safety improvement in Savannah, Chatham County. ARRA funds will only be used to acquire right of way for this project. The project will improve SR 25 Connector/West Bay Stre | Other | 2010-07-21 | 2010-07-21 | 2012-06-30 |  | 2142593 | 1.100
2716 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | CARROLL |  | 03 | 0003083 | This project is a bridge replacement project on County Road 837 in Carroll County. This project replaces the existing structurally deficient bridge over Big Indian Creek with a 320 ft. x 30 ft. conc | Bridge Replacement | 2010-03-02 | 2010-03-29 | 2011-04-30 |  | 1847683.25 | 0.390
2717 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0003769 | This project is an intersection improvement in Fulton County. The project will reconstruct the intersection on County Road 85/Kimball Bridge Road at County Road 103/Waters Road. The construction wil | Pavement Improvement | 2009-12-01 | 2011-02-01 | 2010-10-31 |  | 849092.42 | 0.200
2718 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0004393 | This is a transportation enhancement project in Atlanta, Fulton County. This project proposes to improve accessibility, mobility and safety by connecting to a bike and pedestrian system that is plann | Transportation Enhancements | 2010-06-18 | 2010-07-26 | 2011-07-01 |  | 1926137.3 | 0.690
2719 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0004456 | This is a new roadway construction project in Gwinnett County. This proposed project will connect to the existing intersection of McGinnis Ferry Road and Satellite Boulevard, with only minor improvem | New Construction | 2009-09-03 | 2009-09-11 | 2011-09-30 | 2011-09-30 | 20412160.25 | 2.670
2720 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0004467 | This project is a safety improvement in the city of Atlanta in Fulton County. The project will construct intersection safety improvements at Barge Road at Campbellton Road. | Safety/Traffic Management | 2012-02-03 | 2012-02-27 | 2012-12-31 |  | 288800 | 0.200
2721 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0004473 | This project is a transportation enhancement in Cobb County. This project is located 1,500 feet east of Cobb Parkway/US 41. The proposed project would construct a 10-foot multiuse path along the eas | Transportation Enhancements | 2010-08-31 | 2010-08-31 | 2011-12-31 |  | 2066335.35 | 0.570
2722 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0004633 | This is a transportation enhancement project in Jonesboro in Clayton County. This project includes enhancements to pedestrian safety and improved near term traffic flow. The project will also addres | Transportation Enhancements | 2010-04-09 | 2010-03-23 | 2011-06-30 | 2011-06-30 | 2862502.49 | 0.870
2723 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0005910 | This project is a transportation enhancement in Fulton County and the City of Sandy Springs. The project consists of the construction of a comprehensive sidewalk system, including new and improved s | Transportation Enhancements | 2010-12-09 |  | 2011-12-31 |  | 402404.1 | 0.310
2724 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0006259 | This project is an enhancement project in Fulton County. This project will construct and improve sidewalks along Piedmont Avenue from the Georgia State University MARTA Station to John Wesley Dobbs A | Transportation Enhancements | 2010-09-01 | 2010-09-01 | 2011-12-31 |  | 820000 | 0.560
2725 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 13 | 0006262 | This is a transportation enhancement project in Cobb County, in the city of Acworth. The project will construct improvements along Senator Russell Avenue, including onstreet parking, curb and gutter, | Pavement Improvement | 2010-03-08 | 2010-03-08 | 2010-12-31 |  | 580000 | 0.850
2726 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | CLINCH |  | 01 | 0006534 | This project is a transportation enhancement in Clinch County. The historic Homerville Railroad Depot, also known as Station 11, will be restored to its original architectural style to the extent pos | Transportation Enhancements | 2009-10-08 | 2009-11-09 | 2011-07-01 | 2010-06-24 | 490753 | 0.000
2727 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | WASHINGTON |  | 12 | 0006562 | This project is a transportation enhancement in Washington County and the City of Sandersville. The project will provide new 5-ft sidewalks along Sun Hill Road, providing pedestrian access to Kaolin | Transportation Enhancements | 2010-06-15 | 2010-08-16 | 2011-12-31 | 2011-09-21 | 433724 | 1.570
2728 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 13 | 0006570 | This project is a transportation enhancement in Fulton County. This project will improve conditions at the intersection of Cascade Road and Benjamin Mays Drive from Beecher Road/Bouldevard Granada to | Transportation Enhancements | 2011-01-26 | 2011-11-01 | 2011-12-31 |  | 625000 | 0.210
2729 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 0006597 | This project is a transportation enhancement in Columbus, Muscogee County. This project consists of streetscape improvements on Veterans Pkwy SR 1/US 27 beginning at 8th Street and extending northerl | Transportation Enhancements | 2009-11-12 | 2010-01-25 | 2011-05-15 |  | 1258958.54 | 0.650
2730 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | PIKE |  | 03 | 0006600 | "This project constructs a walking trail in Molena, in Pike County. Construction includes the aesthetic revitalization of a portion of Georgia Highway 109 east of the Georgia Highway 18 intersection. | Transportation Enhancements | 2009-09-29 | 2009-10-21 | 2011-05-15 | 2010-07-31 | 97307 | 0.100
2731 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | POLK |  | 11 | 0006627 | This project is a transportation enhancement in Polk County. Construction includes streetscape improvements in downtown Rockmart along: State Route 6 (Elm Street) from CSX Railroad right-of-way to S | Transportation Enhancements | 2010-11-16 | 2011-02-07 | 2011-06-01 | 2011-04-04 | 210620 | 0.160
2732 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 13 | 0006647 | This project is an enhancement project in Henry County. This project will construct the Reeves Creek Trail and Greenway, a bicycle and pedestrian trail along the Reeves Creek in the City of Stockbrid | Transportation Enhancements | 2010-04-30 | 2010-09-09 | 2011-12-31 | 2011-09-02 | 625386 | 0.000
2733 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0006657 | This project is a safety and operational improvement project in Fulton County. The proposed project will upgrade six intersections and is located along and adjacent to Mt. Vernon Rd. Intersection up | Safety/Traffic Management | 2011-04-07 | 2011-04-07 | 2012-01-12 |  | 2661626.5 | 1.200
2734 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0006683 | This project is a safety and operational improvement project in Fulton County and the City of Atlanta. This project consists of corridor and intersection improvements on SR 141/Peachtree Road from th | Pavement Improvement | 2010-02-04 | 2010-03-15 | 2012-06-30 |  | 10052474.59 | 1.330
2735 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0006726 | This project is a transportation enhancement in Fayette County in the city of Fayetteville. This project will construct sidewalks in downtown Fayetteville. | Transportation Enhancements | 2010-07-22 | 2010-11-01 | 2011-11-16 |  | 408552.6 | 0.000
2736 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | 0006791 | This project is a safety improvement in Cherokee County. This project consists of signal, roadway, pedestrian, transit and landscaping improvements along SR Bus 5 (Riverstone Pkwy) between North Etow | Safety/Traffic Management | 2010-07-15 | 2010-08-09 | 2011-06-30 | 2011-09-27 | 445710.52 | 1.500
2737 | Underway | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0006793 | This project is a transportation enhancement project in Clayton County. This project consists of constructing a pedestrian/bicycle underpass beneath SR 54/Jonesboro Rd. in Morrow, Georgia. Plans are | Transportation Enhancements | 2010-11-18 | 2011-01-24 | 2012-04-30 |  | 1047895.67 | 0.000
2738 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0006810 | This project provides intersection improvements at 7 locations in Dekalb County. The project consists of the South and North Hairston Road corridors from Kenilworth Drive to Mainstreet Park Drive. T | Safety/Traffic Management | 2010-11-16 | 2010-05-17 | 2011-11-22 |  | 782993.05 | 2.800
2739 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 04 | 0006825 | The proposed project along Buford Highway in Gwinnett County will upgrade signal equipment and install fiber optic interconnect to allow for Intelligent Transporation Systems (ITS). Installation of IT | Safety/Traffic Management | 2009-09-18 | 2010-01-11 | 2011-10-28 |  | 1195798.89 | 11.010
2740 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0006829 | This project, in Gwinnett County, includes the design of fiber optic communications cable and closed-circuit television (CCTV) cameras along Sugarloaf Parkway from Peachtree Industrial Boulevard in Du | Safety/Traffic Management | 2009-09-18 | 2010-01-25 | 2011-10-28 |  | 1384553.27 | 12.300
2741 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | 0006840 | This project is a transportation enhancement in Henry County. The proposed project will construct sidewalks and sidewalk improvements in the Tanger Boulevard area of the city of Locust Grove. | Transportation Enhancements | 2010-05-07 | 2010-07-12 | 2012-03-15 |  | 367650 | 0.000
2742 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0006868 | This project is a safety improvement in Cobb County. This project proposes to increase the safety and operation improvements of the intersection of Sandy Plains Road at East Piedmont Road located in | Safety/Traffic Management | 2010-08-06 |  | 2011-11-30 |  | 1829957.57 | 0.600
2743 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0006869 | This project is new roadway construction in Cobb County. The project consists of the construction of Big Shanty Road Connector (SR 401) from Barrett Lakes Boulevard to George Busbee Parkway for a tot | New Construction | 2010-01-05 | 2010-02-19 | 2012-04-30 |  | 8093954.79 | 1.880
2744 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0006956 | This project is the replacement of a structurally deficient bridge in Coweta County. This project will replace the bridge on County Road 41 over the CSX Railroad, 2.0 miles northeast of Newnan, Georg | Bridge Replacement | 2010-01-05 | 2010-01-15 | 2010-10-31 |  | 1345078.64 | 0.400
2745 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0006957 | This project is the replacement of a structurally deficient bridge in Coweta County. This project will replace the bridge on County Road 130 over White Oak Creek, 3.5 miles northeast of Moreland, Geo | Bridge Replacement | 2010-01-05 | 2010-02-15 | 2010-11-30 | 2010-11-30 | 1055465.1 | 0.250
2746 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0006978 | This project is a transportation enhancement in Fulton County, in downtown Atlanta. The project will construct new and wider sidewalks between the Civic Center MARTA Station and Centennial Olympic Pa | Transportation Enhancements | 2010-09-08 | 2010-11-29 | 2011-12-31 |  | 1200109.58 | 0.360
2747 | Underway | C220,C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0006984 | This project is a transportation enhancement in Fulton County and the City of Sandy Springs. This project is the construction of a comprehensive streetscape/sidewalk system, including new and improve | Transportation Enhancements | 2010-08-16 |  | 2011-03-31 |  | 2687748.67 | 1.330
2748 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0007128 | This project is preliminary engineering and design for a bridge replacement in Chatham County. This project will replace the Bascule Bridges over the Wilmington River with an Intra-Coastal Waterway | Other | 2010-03-08 | 2010-03-08 | 2013-07-31 |  | 1000000.08 | 0.400
2749 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0007130 | This project is a transportation enhancement in Dekalb County. The project will construct streetscape designs and intersection improvements along SR 154/Memorial Drive from SR 155/Candler Road to Mou | Transportation Enhancements | 2009-07-23 | 2009-09-28 | 2012-05-31 |  | 4539202.25 | 3.400
2750 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0007131 | This project is the construction of intersection and pedestrian safety improvements in DeKalb County. This project is on SR 10/Memorial Drive and begins at Woodcroft Road and ends at Goldsmith Road. | Transportation Enhancements | 2009-11-19 | 2010-03-08 | 2011-12-31 |  | 2716982.02 | 3.470
2751 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | 0008065 | This project is a transportation enhancement in Baldwin County. Phase II of the Milledgeville downtown streetscape proposes to construct new sidewalks, ADA compliant access, new and reconstructed str | Transportation Enhancements | 2010-05-17 | 2010-06-07 | 2011-11-01 | 2011-02-04 | 801060.72 | 0.300
2752 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | JACKSON |  | 10 | 0008066 | This project is a transportation enhancement in Banks and Jackson Counties and in the City of Maysville. This project is the second phase of the Maysville Downtown Streetscape. Project construction | Transportation Enhancements | 2010-04-15 | 2010-07-26 | 2011-12-31 | 2011-07-12 | 355914 | 0.700
2753 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | BURKE |  | 12 | 0008080 | This project is a transportation enhancement in Burke County. The project will provide sidewalks and landscaping along State Route 56 from the intersection of Myrick Street along State Route 56 to Ba | Transportation Enhancements | 2010-04-30 | 2010-06-14 | 2011-12-31 |  | 1128500 | 0.200
2754 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0008098 | This is a transportation enhancement project in Clayton County and the City of Morrow. The project will construct phase II of the Jesters Creek Pedestrian Pathway in Morrow. Project construction beg | Transportation Enhancements | 2011-01-04 | 2011-01-25 | 2011-12-31 | 2011-06-23 | 996461.56 | 0.610
2755 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | DECATUR |  | 02 | 0008113 | This project provides streetscape improvements in downtown Bainbridge in Decatur County. The Bainbridge Central Business District is well defined on the north by Calhoun Street and on the south by Sh | Transportation Enhancements | 2009-09-29 | 2009-11-09 | 2011-07-01 | 2010-09-30 | 591411.23 | 0.360
2756 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 05 | 0008115 | This project is a transportation enhancement in Dekalb County. Deepdene Park will be rehabilitated. The Mead at the east end and the West Lawn at the west end of Deepdene Park will have the open, pas | Transportation Enhancements | 2010-01-05 | 2010-06-07 | 2011-05-07 |  | 1137182.6 | 0.400
2757 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0008119 | This project is a transportation enhancement in DeKalb and Rockdale Counties. This project involves clearing, grading, and installing a 10' to 12' wide concrete trail from MLK High School on Snapfinge | Transportation Enhancements | 2010-01-25 | 2010-05-03 | 2011-05-07 | 2010-10-01 | 653274.68 | 1.600
2758 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | 0008124 | This project is a transportation enhancement project in the City of Douglasville in Douglas County. The project will place historicly designed lighting with banners on Campbellton Street from Douglas | Transportation Enhancements | 2011-06-13 |  | 2012-06-30 |  | 500000
2759 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0008126 | The project will provide pedestrian improvements within the City of Fayetteville in Fayette County along Lee Street. This will include construction of a 5 foot sidewalk with a 2 foot grass buffer and | Transportation Enhancements | 2009-09-23 | 2009-11-02 | 2011-05-15 |  | 337500 | 0.590
2760 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0008131 | This is an enhancement project in Fulton County, city of Atlanta. Streetscape improvements within the Farlie Poplar historic district along: 1) Walton Street: between Centennial Olympic Park Drive a | Transportation Enhancements | 2010-05-27 | 2010-09-22 | 2011-12-01 |  | 659609.34 | 0.210
2761 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0008135 | This project is a transportation enhancement project in Fulton County. The project will be a streetscape improvement extending 4,100 linear feet along Old National Parkway and a portion of Godby Road. | Transportation Enhancements | 2011-12-01 | 2012-02-29 | 2013-12-31 |  | 440800
2762 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 13 | 0008140 | This project is a transportation enhancement project in the City of Palmetto in Fulton County. This project will restore the historic Palmetto Train Depot to resmble its original appearance. Work wi | Transportation Enhancements | 2011-07-26 | 2011-09-26 | 2013-12-31 |  | 750400
2763 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | HARALSON |  | 11 | 0008157 | This project is a transportation enhancement in the City of Buchanan in Haralson County. The project will construct sidewalks, curb and gutter, seatwalls, lighting, street furniture and landscaping a | Transportation Enhancements | 2009-10-09 | 2010-02-16 | 2011-06-01 | 2010-12-20 | 438000 | 0.200
2764 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | 0008159 | This project is a transportation enhancement in Henry County. The proposed project will provide a trailhead facility. The project will be constructed on two city owned parcels adjacent to Cleveland | Transportation Enhancements | 2009-10-01 | 2010-03-15 | 2011-05-15 | 2010-09-10 | 241204.1 | 0.910
2765 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | LEE |  | 02 | 0008167 | This project is a transportation enhancement project in Lee County, in the City of Smithville. New sidewalks will be constructed along Main Street to replace the existing broken, non-compliant, and n | Transportation Enhancements | 2010-08-27 | 2010-09-22 | 2011-12-31 |  | 128000 | 0.070
2766 | Underway | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 0008185 | This is a transportation enhancement project in Muscogee County. This project will provide streetscape and beautification along SR 1/Veteran's Parkway in Columbus from 10th Street to SR 22 Spur. The | Transportation Enhancements | 2009-11-12 | 2010-01-25 | 2011-05-15 |  | 1169885.82 | 0.400
2767 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | OGLETHORPE |  | 10 | 0008187 | This is a transportation enhancement project in Oglethorpe County. The Crawford Depot project will include renovation and rehabilitation of the depot and surrounding grounds. Improvements include ne | Transportation Enhancements | 2010-07-28 | 2010-08-30 | 2011-12-01 | 2011-01-06 | 275000 | 0.000
2768 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0008188 | The project will provide a trailhead facility adjacent to downtown Dallas in Paulding County, on an approximate 1 acre site at the intersection of South Main Street and Hardee Street. The trailhead w | Transportation Enhancements | 2009-09-17 | 2009-12-01 | 2011-06-01 |  | 625000 | 0.060
2769 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | SCHLEY |  | 02 | 0008198 | This project is a transportation enhancement in Schley County. The project will construct sidewalks on three locations in Ellaville: 1) east side of Hill Street between West Buena Vista Street and | Transportation Enhancements | 2009-10-08 | 2010-01-18 | 2011-05-14 | 2010-04-04 | 66997.38 | 0.640
2770 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | TELFAIR |  | 01 | 0008202 | This project is a transportation enhancement project in the in the City of Milan in Telfair County. This project is the renovation of the historic Milan Train Depot. Improvements will include front | Transportation Enhancements | 2011-05-23 | 2011-05-31 | 2013-06-30 | 2011-07-26 | 100000
2771 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | WARREN |  | 12 | 0008213 | This is a transportation enhancement project in Warren County. Phase II of the Warren County Historic Depot project will provide streetscape and landscape improvements on the west side of Norwood Str | Transportation Enhancements | 2010-04-13 | 2010-08-02 | 2011-12-31 | 2011-01-14 | 104547 | 0.000
2772 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0008235 | This project will provide traffic signal upgrades in Spalding County. This project will upgrade traffic signal in the City of Griffin at the 12 locations. The signals on Poplar St. between 6th and | Safety/Traffic Management | 2010-02-22 | 2010-04-08 | 2012-03-28 | 2011-02-22 | 1236651.85 | 1.300
2773 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0008236 | This project will provide traffic signal upgrades in Spalding County. This project will upgrade traffic signals at the following intersections: 1) College St. @ 6th St. 2) Hill St. @ Chappell S | Safety/Traffic Management | 2010-02-22 | 2010-04-27 | 2012-03-28 | 2011-02-21 | 326933.55 | 0.000
2774 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0008544 | This is an interchange lighting project in Coweta County. This project shall install 38 High Mast Lighting Towers at two existing interchanges along Interstate 85 in Coweta County. Currently, no road | New Construction | 2010-05-10 | 2010-10-04 | 2010-12-31 | 2011-10-21 | 1109521.11 | 0.800
2775 | Underway | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0008622 | This project is a transportation enhancement project in Cobb County in the City of Marietta. This project will construct pedestrian improvements, including sidewalks, lighting, benches, landscaping, | Transportation Enhancements | 2011-07-30 | 2011-07-30 | 2012-03-31 |  | 672000 | 0.490
2776 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0008902 | This project is a safety and enhancement project in DeKalb County. This project is the construction of sidewalks along South Hairston Road from Rockbridge Road to Wesley Chapel Road. The gross lengt | Transportation Enhancements | 2010-08-26 | 2010-09-06 | 2016-02-26 |  | 1277442.7 | 5.590
2777 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | BARTOW | ATLANTA | 11 | 0008960 | The proposed project will reconstruct a portion of Glade Road from Catfish Court to Sugar Hill Road to improve the horizontal and vertical curves at this location. ARRA funds will only be used to acq | Other | 2010-04-26 | 2010-08-24 | 2011-06-30 | 2011-09-23 | 420200 | 0.200
2778 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | BACON |  | 01 | 0008977 | This project is a transportation enhancement project in Bacon County. This project is the renovation of a portion of a former elementary school built in 1934 to convert the building to a Welcome Cen | Transportation Enhancements | 2011-04-12 | 2011-06-01 | 2013-12-31 |  | 218750
2779 | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | MITCHELL |  | 02 | 0009112 | This is a transportation enhancement project in Mitchell County. This project will improve the streetscape along East Broad Street/ GA S. R. 97/112 in downtown Camilla. Construction includes the dem | Transportation Enhancements | 2010-01-28 | 2010-04-12 | 2011-10-07 | 2011-01-28 | 500000 | 0.100
2780 | Completed | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009127 | This project is a transportation enhancement project in Richmond County. This project will construct a 10 foot wide multi-use trail on the Campus of Augusta State University and will connect to exist | Transportation Enhancements | 2011-02-01 | 2011-03-08 | 2012-12-31 | 2011-10-31 | 600000
2781 | Underway | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 0009288 | This project is a transportation enhancement project in Columbus/Muscogee County. This project will provide landscaping and a gateway entrance at the interchange of I-185 and SR 520/Victory Drive, j | Transportation Enhancements | 2010-09-23 | 2010-11-18 | 2011-12-31 |  | 3059436 | 0.200
2782 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | STATEWIDE | ATLANTA |  | 0009312 | "This project is a planning study in the Atlanta Metropolitan Area. This study will develop a ""Strategic Regional Thoroughfare Plan"" for counties within the Atlanta MPO area. The planning study wi | Other | 2009-12-21 | 2009-12-21 | 2011-03-31 | 2011-12-31 | 1000077.21 | 0.000
2783 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | 0009313 | This project is an engineering study in Chatham County. The SR 21 Corridor Study will develop a congestion relief plan that encompasses several alternatives incorporating but not limited to toll lan | Other | 2010-02-19 | 2010-02-19 | 2012-12-31 |  | 780000 | 0.000
2784 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009314 | This project is an engineering study in Chatham County. The SR 204 Corridor Study will develop a congestion relief plan that encompasses several alternatives incorporating but not limited to toll lan | Other | 2010-02-19 | 2010-02-19 | 2012-12-31 |  | 745000 | 0.000
2785 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | WALKER | CHATTANOOGA (TN) | 09 | 0009317 | This project is a roadway maintenance repaving project in Walker County. This project is the milling and resurfacing of County Road 704/McFarland Avenue from Rossville City limits to SR 1/US 27 for a | Pavement Improvement | 2010-03-02 | 2010-03-03 | 2010-06-30 | 2010-06-30 | 84222.74 | 1.640
2786 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | WALKER | CHATTANOOGA (TN) | 09 | 0009328 | This project is a transportation enhancement project in Walker County in the City of Chickamauga. This project will construct sidewalks at several locations in the City of Chickamauga. Sidewalks will | Transportation Enhancements | 2010-06-23 | 2010-08-26 | 2011-05-15 | 2011-05-05 | 1102000 | 3.310
2787 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0009344 | This project is an intersection improvement in Gwinnett County. The purpose of this project is to improve the operating characteristics of the intersection of SR 8 (Lawrenceville Highway) and Pleasan | Safety/Traffic Management | 2009-08-28 | 2009-09-16 | 2011-06-30 |  | 9328483.55 | 0.210
2788 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 04 | 0009345 | The project is an intersection improvement in Gwinnett County. This project will improve the operation characteristics of the intersection of SR 8 (Lawrenceville Highway) and Beaver Ruin Road/Arcado | Safety/Traffic Management | 2009-08-05 | 2009-11-02 | 2011-06-30 |  | 6285053.8 | 1.100
2789 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | CATOOSA | CHATTANOOGA (TN) | 09 | 0009346 | This project is a safety intersection improvement project in Catoosa County. This project consists of reconstructing the existing left turns lanes on SR 2 from a Type A median crossover to a Type B. | Safety/Traffic Management | 2009-07-27 | 2009-08-26 | 2010-09-30 |  | 1531013.32 | 0.220
2790 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0009347 | This is a transportation enhancement project in Atlanta, Fulton County. This project will construct sidewalk improvements, including the replacement and upgrading of existing sidewalks along portions | Transportation Enhancements | 2010-07-09 | 2010-10-21 | 2011-12-31 |  | 4001548.18 | 0.800
2791 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0009348 | This project is a safety improvement in Fulton County. The proposed project will provide traffic signals at five key intersections in Midtown Atlanta. This project will provide a safer pedestrian an | Pavement Improvement | 2010-01-12 | 2010-05-11 | 2010-12-31 | 2010-12-15 | 427274.66 | 0.000
2792 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0009349 | This project will modify the interchange of SR 120/Roswell Road and SR 120 Alternate (formerly SR 120 Loop) in Cobb County. This project is located in the City of Marietta. The proposed project will | Pavement Improvement | 2009-08-18 | 2009-09-01 | 2011-06-30 | 2011-08-11 | 7573857.03 | 0.750
2793 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0009350 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 809/Corner Road. The construction will con | Pavement Improvement | 2009-08-19 | 2009-09-24 | 2011-04-30 | 2011-04-30 | 1242339.86 | 1.600
2794 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0009351 | This project is a road widening construction project in Gwinnett County. The project will widen and reconstruct the existing two lanes of SR 20 to accommodate 4 lanes beginning approximately 800 feet | Pavement Improvement | 2009-09-08 | 2009-10-22 | 2011-12-31 |  | 12285042.19 | 2.650
2795 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0009352 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 784/Hadaway Road. The construction will co | Pavement Improvement | 2009-08-19 | 2009-09-24 | 2011-04-30 | 2011-04-30 | 956562.38 | 0.400
2796 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0009353 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 55/Mars Hill Church Road. The construction | Pavement Improvement | 2009-08-19 | 2009-09-24 | 2011-04-30 | 2011-04-30 | 884562.14 | 0.400
2797 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 13 | 0009354 | This project will upgrade existing traffic signal equipment and pedestrian facilities for S.R. 138 at various intersections in Clayton and Henry Counties. The intersections are as follows: 1) SR 138 | Safety/Traffic Management | 2010-04-09 | 2010-08-23 | 2013-10-21 |  | 1170283.8 | 2.000
2798 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0009355 | This project will upgrade existing traffic signal equipment and pedestrian facilities for S.R. 314 and S.R. 54 at various intersections in Fayette County. The intersections are as follows: 1) SR 3 | Safety/Traffic Management | 2009-07-20 | 2009-10-26 | 2010-02-28 | 2010-02-28 | 159969.21 | 1.200
2799 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0009356 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at five locations for S.R. 42 in Clayton County. The intersections are as follows: 1) SR 42 @ I-675 NB Ram | Safety/Traffic Management | 2010-04-09 | 2010-08-23 | 2012-01-27 | 2011-05-11 | 560486.24 | 1.600
2800 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009357 | This project is a safety project in Fulton County in the City of Roswell. This project will upgrade existing traffic signal equipment and pedestrian facilities at various locations on Pine Grove Road | Safety/Traffic Management | 2010-02-05 | 2010-06-01 | 2010-10-31 |  | 250129.91 | 1.600
2801 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009358 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations on SR 961/Old Alabama Road in the City of Roswell, Fulton County. The intersections are | Safety/Traffic Management | 2009-07-17 | 2009-10-12 | 2010-07-31 | 2010-07-16 | 739946.39 | 3.000
2802 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 06 | 0009359 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations in DeKalb County on Chamblee Tucker Road, Clairmont Road, & New Peachtree Road. The int | Safety/Traffic Management | 2009-07-20 | 2009-09-22 | 2010-05-31 | 2010-05-24 | 1134216 | 0.000
2803 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0009360 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations on Briarcliff Road & Shallowford Road in Dekalb County. The intersections are as follow | Safety/Traffic Management | 2009-07-20 | 2009-11-04 | 2010-07-31 | 2010-07-21 | 892693.87 | 1.800
2804 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0009361 | This project will upgrade the existing traffic signal equipment and pedestrian facilities at various locations on Chamblee Dunwoody Road and NorthShallowford Road in DeKalb County. The intersections | Safety/Traffic Management | 2009-07-20 | 2010-02-01 | 2010-12-31 |  | 1855080.7 | 0.000
2805 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0009362 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at 21 locations on LaVista Rd, Northlake Pkwy, & Henderson Mill Rd in Dekalb County at the following intersec | Safety/Traffic Management | 2009-07-20 | 2010-05-11 | 2010-12-31 |  | 1984055.69 | 0.000
2806 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 13 | 0009363 | This project consists of the upgrade of the traffic signals at 4 locations on SR 139/Mableton Parkway and 1 location on County Road 2570/Old Alabama Road in Cobb County. Pedestrian improvements will | Safety/Traffic Management | 2009-07-20 | 2009-11-02 | 2010-07-31 |  | 439774.72 | 1.900
2807 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009365 | This project is the replacement of the existing bridge over Euchee Creek on SR 223, 2.2 miles northwest of Grovetown, in Columbia County. The project will widen and correct the structural deficiencie | Bridge Replacement | 2009-11-02 | 2010-02-24 | 2010-12-31 |  | 2397388.95 | 0.220
2808 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | ATKINSON |  | 01 | 0009366 | This project is located approximately four miles northwest of Pearson, Georgia in Atkinson County. This project will construct a bridge replacement over Pudding Creek along County Road 42/Antioch Chur | Bridge Replacement | 2009-07-28 | 2009-08-10 | 2010-06-30 | 2010-04-27 | 1444243.97 | 0.430
2809 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009367 | This project is a bridge replacement on CR 85/Kimball Bridge Road two miles southeast of Alpharetta in Fulton County. The project is 0.554 miles long, consisting of removal of the existing Big Creek B | Bridge Replacement | 2009-12-04 | 2010-01-21 | 2011-09-30 | 2011-10-28 | 4285509.95 | 0.200
2810 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009379 | This project is an engineering and planning study in Chatham County. The study will evaluate the US 80 Bridges and will develop a plan for replacement bridges over the Bull River and Lazaretto Creek. | Other | 2010-02-19 | 2010-02-19 | 2012-12-31 |  | 264961 | 0.000
2811 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009380 | This project is a safety improvement in Chatham County in downtown Savannah. This project consists of upgrading pedestrian countdown signal heads at multiple intersections. | Safety/Traffic Management | 2010-03-19 | 2010-06-28 | 2011-05-31 |  | 450217.07 | 0.000
2812 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009381 | This project is a safety improvement in Chatham County in downtown Savannah. The project will install audible push buttons at 50 signalized intersections. The push buttons emit an audible signal to | Safety/Traffic Management | 2010-03-19 | 2010-06-28 | 2011-05-31 |  | 274621.76 | 0.000
2813 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009382 | This project is a safety improvement in Chatham County in downtown Savannah. This project consists of replacing existing signal heads at eleven signalized intersections along 27th Street, from Montgo | Safety/Traffic Management | 2010-03-19 | 2010-06-28 | 2011-05-31 |  | 70548.86 | 1.200
2814 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009385 | This project is a safety improvement in Chatham County in the City of Savannah. This project consists of installing an emergency vehicle GPS pre-emption system assembly at existing signalized interse | Safety/Traffic Management | 2010-03-19 | 2010-06-28 | 2011-05-31 |  | 1403176.23 | 0.000
2815 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 0009401 | This project is a transportation enhancement in Muscogee County. The 14th Street Bridge pedestrian project will connect the riverwalk projects in Georgia and Alabama. The project consist of rehabili | Transportation Enhancements | 2010-12-02 | 2011-03-28 | 2012-03-15 |  | 3351386 | 0.140
2816 | Completed | C490 | OJT/SS | GEORGIA | STATEWIDE |  |  | 0009416 | This On-the-job Training/Supportive Services (OJT/SS) grant provides academic and occupational skills training to low-income women and minorities and places them in the highway construction industry a | Other | 2009-10-05 | 2009-12-15 | 2010-12-31 | 2010-12-31 | 171095 | 0.000
2817 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0009419 | This project is an intersection improvement in Coweta County. The project will realign the intersection of SR 16/Wells Street at County Road 157/Broad Street & Luther Bailey Road. The project will c | Safety/Traffic Management | 2009-10-06 | 2009-10-15 | 2010-09-30 | 2010-09-30 | 1017617.62 | 0.380
2818 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COFFEE |  | 01 | 0009421 | This project will replace the structurally deficient bridge on SR 135/US 221 over Tiger Creek in Coffee County. The existing 108 X 24' bridge was constructed in 1947 and will be replaced with a new 1 | Bridge Replacement | 2009-09-24 | 2009-10-29 | 2010-08-31 | 2010-09-10 | 1345914.2 | 0.300
2819 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | PIERCE |  | 01 | 0009422 | This is an intersection improvement project in Pierce County. This project will realign the intersection of SR 203/Strickland Street and County Road 309/Old Alma Road and with County Road 236 to impr | Pavement Improvement | 2009-09-28 | 2010-01-11 | 2010-06-30 |  | 1084675.85 | 0.360
2820 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | BARROW | ATLANTA | 07 | 0009423 | This project is a maintenance resurfacing project in Barrow County to repave local roadways. The Barrow resurfacing program includes four roadways: 1) Carl Bethlehem Road from SR 81 to SR 11; 2) Smi | Pavement Improvement | 2010-01-21 | 2010-02-01 | 2010-07-31 | 2010-05-07 | 1026314.51 | 8.590
2821 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | BARTOW | ATLANTA | 11 | 0009424 | This project is a maintenance resurfacing project in Bartow County to repave local roadways. The Bartow resurfacing program includes two roadways: 1) Red Top Mountain Road from 0.24 miles east of I- | Pavement Improvement | 2010-01-19 | 2010-03-16 | 2010-06-30 | 2010-06-03 | 194631.77 | 1.860
2822 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | 0009425 | This project is a maintenance resurfacing project in Cherokee County to repave local roadways. The Cherokee resurfacing program includes a single roadway 1) East Cherokee Drive from 0.16 miles north | Pavement Improvement | 2010-02-02 | 2010-04-27 | 2010-06-30 | 2010-06-30 | 220054.36 | 1.540
2823 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0009426 | This project is a maintenance resurfacing project in Clayton County to repave local roadways. The Clayton resurfacing program includes three roadways: 1) Flint River Road from Glenwoods Drive to Kend | Pavement Improvement | 2010-02-24 | 2010-03-29 | 2010-06-30 | 2010-05-24 | 874930.09 | 3.880
2824 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0009427 | This project is a maintenance resurfacing project in Coweta County to repave local roadways. The Coweta resurfacing program includes three roadways: 1) Poplar Road from I-85 to Yeager Road and from | Pavement Improvement | 2010-02-04 | 2010-05-25 | 2010-07-31 | 2010-07-30 | 749364.77 | 8.620
2825 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 03 | 0009428 | This project is a maintenance resurfacing project in Douglas County to repave local roadways. The Douglas resurfacing program includes three roadways: 1) Liberty Road from North Helton Road to Libert | Pavement Improvement | 2010-02-24 | 2010-04-12 | 2010-06-30 | 2010-06-09 | 822980.05 | 4.460
2826 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0009429 | This project is a maintenance resurfacing project in Fayette County to repave local roadways. The Fayette resurfacing program includes five roadways: 1) SR 85 Connector from SR 85 to Woods Road; 2) H | Pavement Improvement | 2010-02-05 | 2010-05-17 | 2010-07-31 | 2010-06-15 | 856264.2 | 7.460
2827 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | FORSYTH | ATLANTA | 09 | 0009430 | This project is a maintenance resurfacing project in Forsyth County to repave local roadways. The Forsyth resurfacing program includes seven roadways: 1) Old Atlanta Road from James Burgess Road to | Pavement Improvement | 2010-01-19 | 2010-03-31 | 2010-07-31 | 2010-05-17 | 1609403.57 | 9.370
2828 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | 0009431 | This project is a maintenance resurfacing project in Henry County to repave local roadways. The Henry resurfacing program includes two roadways: 1) Thurman Road from East Atlanta Road to Rex Road; | Pavement Improvement | 2010-02-03 | 2010-04-21 | 2010-07-31 | 2010-06-05 | 792128.21 | 3.200
2829 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | ROCKDALE | ATLANTA | 04 | 0009432 | This project is a maintenance resurfacing project in Rockdale County to repave local roadways. The Rockdale resurfacing program includes four roadways: 1) Sigman Road from Gees Mill Road to Old Covi | Pavement Improvement | 2010-02-11 | 2010-02-25 | 2010-06-30 | 2010-06-07 | 1132452.96 | 12.270
2830 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | WALTON | ATLANTA | 07 | 0009433 | This project is a maintenance resurfacing project in Walton County to repave local roadways. The Walton program includes four roadways: 1) Old Monroe Highway from Pannell Road to Nunnally Shoals Roa | Pavement Improvement | 2010-02-05 | 2010-04-07 | 2010-07-31 | 2010-06-11 | 1681770.15 | 15.380
2831 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0009452 | This project is the construction of the widening and improvement of SR 74 in Fayette County, from SR 85 to Cooper Circle Road (approximately 1.85 miles south of Crosstown Drive) for a total length of | Pavement Widening | 2009-10-26 | 2009-11-17 | 2011-12-31 |  | 15925376.13 | 3.000
2832 | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | TROUP |  | 03 | 0009453 | This project will construct phase two of the South LaGrange Loop, a new roadway in Troup County. The roadway will be a bypass around the southern portion of the City of LaGrange. The limits extend f | New Construction | 2009-11-06 | 2009-11-23 | 2011-12-31 |  | 20310819.69 | 4.150
2833 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | CLARKE | ATHENS | 10 | 0009454 | This project is a roadway maintenance repaving project in Clarke County. This project is the milling and resurfacing of County Road 470/MAIN ST from County Road 134/ATHENS ROAD to OGLETHORPE COUNTY L | Pavement Improvement | 2010-02-05 | 2010-04-29 | 2010-07-31 | 2010-06-25 | 216583.46 | 1.500
2834 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | CLARKE | ATHENS | 10 | 0009455 | This project is a roadway maintenance repaving project in Clarke County. This project is the milling and resurfacing of County Road 140/OLD ELBERTON from County Road 477/VOYLES ROAD to MADISON COUNTY | Pavement Improvement | 2010-02-05 | 2010-04-29 | 2010-07-31 | 2010-06-25 | 212885.59 | 1.870
2835 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | CLARKE | ATHENS | 10 | 0009456 | This project is a roadway maintenance repaving project in Clarke County. This project is the milling and resurfacing of County Road 120/SMOKEY ROAD from NOWHERE ROAD to HELICAN SPRINGS ROAD for a tot | Pavement Improvement | 2010-02-05 | 2010-04-29 | 2010-07-31 | 2010-06-25 | 273044.91 | 2.450
2836 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | ELBERT |  | 10 | 0009457 | This project is a roadway maintenance repaving project in Elbert County. This project is the milling and resurfacing of County Road 307/THIRTEEN FORKS ROAD from SR 77 to HART COUNTY LINE for a total | Pavement Improvement | 2010-01-19 | 2010-04-06 | 2010-07-31 | 2010-06-02 | 417391.42 | 4.130
2837 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | FRANKLIN |  | 10 | 0009458 | This project is a roadway maintenance repaving project in Franklin County. This project is the milling and resurfacing of County Road 418/County Road 419/BOLD SPRINGS ROAD from SR 106 to SR 59; EXC S | Pavement Improvement | 2010-02-03 | 2010-04-22 | 2010-07-31 | 2010-06-09 | 566828.91 | 6.840
2838 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HABERSHAM |  | 10 | 0009459 | This project is a roadway maintenance repaving project in Habersham County. This project is the milling and resurfacing of County Road 387/DEMOREST/MT AIRY ROAD from SR 385/US 442 to SR 365 for a tot | Pavement Improvement | 2010-01-19 | 2010-04-19 | 2010-06-30 | 2010-05-29 | 331949.62 | 1.250
2839 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | 0009460 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 367/West Ridge Road from County Road 751/Athens Street to SR 11 for a | Pavement Improvement | 2010-03-02 | 2010-04-16 | 2010-06-30 | 2010-06-30 | 91513.81 | 0.420
2840 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | 0009461 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 367/County Road 1098/West Ridge Road from SR 11 to SR 53 Connector fo | Pavement Improvement | 2010-03-02 | 2010-04-16 | 2010-06-30 | 2010-06-30 | 160727.23 | 1.040
2841 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | 0009462 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 621/Wade Orr Road from SR 13 to County Road 685/Hog Mountain Road for | Pavement Improvement | 2010-03-02 | 2010-04-16 | 2010-06-30 | 2010-06-30 | 187963.85 | 1.100
2842 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | 0009463 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 451/Memorial Park Drive from SR 369 to SR 13 for a total project leng | Pavement Improvement | 2010-03-02 | 2010-04-16 | 2010-06-30 | 2010-06-30 | 255737.14 | 1.600
2843 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | HART |  | 10 | 0009464 | This project is a roadway maintenance repaving project in Hart County. This project is the milling and resurfacing of County Road 505/LIBERTY CHURCH ROAD from SR 172 to ELBERT COUNTY LINE for a total | Pavement Improvement | 2010-01-19 | 2010-04-06 | 2010-07-31 | 2010-06-02 | 226141.92 | 2.380
2844 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JACKSON |  | 10 | 0009465 | This project is a roadway maintenance repaving project in Jackson County. This project is the milling and resurfacing of County Road 426/WAYNE POULTRY from OLD GAINESVILLE HWY to VALENTINE PKY for a | Pavement Improvement | 2010-02-05 | 2010-03-30 | 2010-06-30 | 2010-05-24 | 590755.4 | 2.800
2845 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LUMPKIN |  | 09 | 0009466 | This project is a roadway maintenance repaving project in Lumpkin County. This project is the milling and resurfacing of County Road 134/DAMASCUS CHURCH ROAD from SR 9/US 19 to WHITE COUNTY LINE for | Pavement Improvement | 2010-01-21 | 2010-04-14 | 2010-07-31 | 2010-05-27 | 303783.7 | 3.240
2846 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MADISON |  | 10 | 0009467 | This project is a roadway maintenance repaving project in Madison County. This project is the milling and resurfacing of County Road 394/LEXINGTON ROAD from SR 72 to OGLETHORPE COUNTY LINE for a tota | Pavement Improvement | 2010-01-19 | 2010-04-01 | 2010-06-30 | 2010-05-05 | 171858.1 | 1.630
2847 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RABUN |  | 09 | 0009468 | This project is a roadway maintenance repaving project in Rabun County. This project is the milling and resurfacing of OLD 441 from south of County Road 218 to City Street 514 and from City Street 50 | Pavement Improvement | 2010-02-01 | 2010-03-29 | 2010-07-31 | 2010-06-05 | 1164968.56 | 10.000
2848 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | STEPHENS |  | 10 | 0009469 | This project is a roadway maintenance repaving project in Stephens County. This project is the milling and resurfacing of County Road 538/BROOKHAVEN CIR from County Road 43/E SILVER SHOALS ROAD to SR | Pavement Improvement | 2010-02-01 | 2010-05-19 | 2010-07-31 | 2010-07-27 | 835559.75 | 6.340
2849 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TOWNS |  | 10 | 0009470 | This project is a roadway maintenance repaving project in Towns County. This project is the milling and resurfacing of County Road 172/GUM LOG ROAD from west of WINCHESTER CREEK ROAD to BARNARD ROAD | Pavement Improvement | 2010-01-19 | 2010-04-02 | 2010-07-31 | 2010-05-25 | 129695.44 | 1.400
2850 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | UNION |  | 09 | 0009471 | This project is a roadway maintenance repaving project in Union County. This project is the milling and resurfacing of County Road 341/OLD BLUE RIDGE HWY from County Road 117 to LITTLE YOUNGCANE CREE | Pavement Improvement | 2010-01-19 | 2010-04-02 | 2010-07-31 | 2010-05-25 | 280070.76 | 2.570
2851 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WHITE |  | 09 | 0009472 | This project is a roadway maintenance repaving project in White County. This project is the milling and resurfacing of County Road 68/HULSEY ROAD from SR 75 to SR 11/US 129 for a total project length | Pavement Improvement | 2010-01-21 | 2010-04-14 | 2010-07-31 | 2010-05-27 | 133980.42 | 1.300
2852 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | 0009473 | This project is a roadway maintenance repaving project in Baldwin County. This project is the milling and resurfacing of City Street 701/BLANDY ROAD from SR 49 to SR 22 for a total project length of | Pavement Improvement | 2010-01-29 | 2010-03-13 | 2010-06-30 | 2010-06-30 | 245366.36 | 1.960
2853 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | 0009474 | This project is a roadway maintenance repaving project in Baldwin County. This project is the milling and resurfacing of County Road 69/BROWNS CROSSING ROAD from SR 49 to SR 22 for a total project le | Pavement Improvement | 2010-01-21 | 2010-03-01 | 2010-06-30 | 2010-06-30 | 334141.09 | 3.640
2854 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HANCOCK |  | 12 | 0009475 | This project is a roadway maintenance repaving project in Hancock County. This project is the milling and resurfacing of County Road 180/POWELLTON AVE from HAMILTON ST to SPARTA CITY LIMITS for a tot | Pavement Improvement | 2010-02-03 | 2010-05-26 | 2010-06-30 | 2010-07-05 | 82008.25 | 0.570
2855 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JEFFERSON |  | 12 | 0009476 | This project is a roadway maintenance repaving project in Jefferson County. This project is the milling and resurfacing of City Street 561/MIDVILLE ROAD from SR 4 to SR 24 for a total project length | Pavement Improvement | 2010-02-03 | 2010-03-12 | 2010-06-30 | 2010-05-06 | 121321.74 | 0.800
2856 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JEFFERSON |  | 12 | 0009477 | This project is a roadway maintenance repaving project in Jefferson County. This project is the milling and resurfacing of County Road 59/QUAKER ROAD from SR 17 to SR 80 for a total project length of | Pavement Improvement | 2010-02-03 | 2010-03-12 | 2010-06-30 | 2010-05-06 | 176411.74 | 1.500
2857 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JOHNSON |  | 12 | 0009478 | This project is a roadway maintenance repaving project in Johnson County. This project is the milling and resurfacing of County Road 203/BAY SPRINGS CHURCH ROAD from SR 26 to MT OLIVE CHURCH ROAD for | Pavement Improvement | 2010-01-29 | 2010-04-19 | 2010-06-30 | 2010-05-21 | 292633.57 | 2.880
2858 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LAURENS |  | 08 | 0009479 | This project is a roadway maintenance repaving project in Laurens County. This project is the milling and resurfacing of City Street 768/ROBERSON ST from SR 19/US 80 to City Street 770/KNOX ST for a | Pavement Improvement | 2010-02-01 | 2010-06-08 | 2010-06-30 | 2010-07-16 | 43875.4 | 0.230
2859 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LAURENS |  | 08 | 0009480 | This project is a roadway maintenance repaving project in Laurens County. This project is the milling and resurfacing of County Road 526/OLD MACON ROAD from EVERGREEN ROAD to WILKINSON COUNTY LINE fo | Pavement Improvement | 2010-02-01 | 2010-06-08 | 2010-06-30 | 2010-07-16 | 364548.71 | 4.210
2860 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | MCDUFFIE |  | 10 | 0009481 | This project is a roadway maintenance repaving project in McDuffie County. This project is the milling and resurfacing of City Street 663/RAILROAD STREET from SR 17 to SR 223 for a total project leng | Pavement Improvement | 2010-02-01 | 2010-04-21 | 2010-06-30 | 2010-06-24 | 96225.26 | 0.670
2861 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MCDUFFIE |  | 10 | 0009482 | This project is a roadway maintenance repaving project in McDuffie County. This project is the milling and resurfacing of County Road 309/HAPPY VALLEY ROAD from SR 17 to County Road 297/SAND HILL ROA | Pavement Improvement | 2010-02-01 | 2010-04-21 | 2010-06-30 | 2010-06-24 | 163573.5 | 1.160
2862 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | OGLETHORPE |  | 10 | 0009483 | This project is a roadway maintenance repaving project in Oglethorpe County. This project is the milling and resurfacing of County Road 77/WOLFSKIN ROAD from County Road 240 to CLARKE COUNTY LINE for | Pavement Improvement | 2010-01-21 | 2010-03-30 | 2010-06-30 | 2010-05-06 | 94033.58 | 0.690
2863 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | 0009484 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 1509/KEYSVILLE ROAD from SR 88 to BURKE COUNTY LINE for a total p | Pavement Improvement | 2010-01-29 | 2010-02-26 | 2010-06-30 | 2010-04-20 | 352489.8 | 3.100
2864 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | SCREVEN |  | 12 | 0009485 | This project is a roadway maintenance repaving project in Screven County. This project is the milling and resurfacing of County Road 243/E OGEECHEE ST from SR 73 to SYLVANIA CITY LIMITS for a total p | Pavement Improvement | 2010-01-29 | 2010-03-17 | 2010-06-30 | 2010-04-30 | 180411.65 | 1.000
2865 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WARREN |  | 12 | 0009486 | This project is a roadway maintenance repaving project in Warren County. This project is the milling and resurfacing of County Road 174/FIVE POINTS JEWELL ROAD from SR 16 to SR 123 for a total projec | Pavement Improvement | 2010-02-01 | 2010-04-21 | 2010-06-30 | 2010-06-24 | 66207.8 | 0.540
2866 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | WASHINGTON |  | 12 | 0009487 | This project is a roadway maintenance repaving project in Washington County. This project is the milling and resurfacing of County Road 446/RIDGE ROAD from SR 88 to SR 15 for a total project length o | Pavement Improvement | 2010-02-03 | 2010-05-26 | 2010-06-30 | 2010-07-05 | 217569.42 | 1.990
2867 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WILKES |  | 10 | 0009488 | This project is a roadway maintenance repaving project in Wilkes County. This project is the milling and resurfacing of City Street 612/ANDREWS DRIVE from SR 17/US 78BU to SR 47 for a total project l | Pavement Improvement | 2010-02-05 | 2010-05-05 | 2010-06-30 | 2010-06-11 | 272715.37 | 2.130
2868 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | BUTTS |  | 08 | 0009489 | This project is a roadway maintenance repaving project in Butts County. This project is the milling and resurfacing of County Road 296/BROWNLEE ROAD from SR 36 to County Road 136 at the Monroe County | Pavement Improvement | 2010-02-05 | 2010-04-07 | 2010-07-31 | 2010-04-28 | 615758.83 | 6.630
2869 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | DOOLY |  | 02 | 0009490 | This project is a roadway maintenance repaving project in Dooly County. This project is the milling and resurfacing of County Road 320/ELKO ROAD from HOUSTON COUNTY LINE to SR 7 for a total project l | Pavement Improvement | 2010-01-21 | 2010-05-11 | 2010-06-30 | 2010-06-30 | 116990.98 | 1.200
2870 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JONES |  | 08 | 0009491 | This project is a roadway maintenance repaving project in Jones County. This project is the milling and resurfacing of County Road 292/BOWEN HILL ROAD from County Road 107/SMITH ROAD to SR 49 for a t | Pavement Improvement | 2010-01-29 | 2010-02-27 | 2010-07-31 | 2010-06-30 | 432947.57 | 3.900
2871 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LAMAR |  | 03 | 0009492 | This project is a roadway maintenance repaving project in Lamar County. This project is the milling and resurfacing of County Road 214/HIGH FALLS PARK from SR 36 to MONROE COUNTY LINE for a total pro | Pavement Improvement | 2010-02-01 | 2010-03-09 | 2010-07-31 | 2010-06-30 | 466332.74 | 4.420
2872 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MACON |  | 02 | 0009493 | This project is a roadway maintenance repaving project in Macon County. This project is the milling and resurfacing of County Road 282/DRAYTON ROAD from County Road 22/TWIN CHURCHS ROAD to Dooly Coun | Pavement Improvement | 2010-02-01 | 2010-04-30 | 2010-07-31 | 2010-06-24 | 312475.75 | 5.050
2873 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PIKE |  | 03 | 0009494 | This project is a roadway maintenance repaving project in Pike County. This project is the milling and resurfacing of County Road 161/KINGS ROAD from SR 109 to UPSON COUNTY LINE for a total project l | Pavement Improvement | 2010-02-05 | 2010-06-08 | 2010-07-31 | 2010-07-31 | 471915.7 | 3.930
2874 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PULASKI |  | 08 | 0009495 | This project is a roadway maintenance repaving project in Pulaski County. This project is the milling and resurfacing of County Road 198/BURNT BRIDGE from SR 26 to SR 230 for a total project length o | Pavement Improvement | 2010-01-21 | 2010-05-12 | 2010-06-30 | 2010-06-30 | 369659.52 | 4.100
2875 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TROUP |  | 03 | 0009496 | This project is a roadway maintenance repaving project in Troup County. This project is the milling and resurfacing of County Road 407/BARTLEY ROAD from SHOEMAKER ROAD to SR 1 for a total project len | Pavement Improvement | 2010-02-03 | 2010-03-12 | 2010-07-31 | 2010-05-20 | 911631.44 | 8.350
2876 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TWIGGS |  | 08 | 0009497 | This project is a roadway maintenance repaving project in Twiggs County. This project is the milling and resurfacing of County Road 193/SGODA-HUBER ROAD from SR 87 to County Road 185/RIGGINS MILL ROA | Pavement Improvement | 2010-02-05 | 2010-02-19 | 2010-07-31 | 2010-07-31 | 787351.56 | 4.780
2877 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | UPSON |  | 03 | 0009498 | This project is a roadway maintenance repaving project in Upson County. This project is the milling and resurfacing of County Road 421/BARNESVILLE ROAD from SR 74 to LAMAR COUNTY LINE for a total pro | Pavement Improvement | 2010-01-21 | 2010-02-17 | 2010-07-31 | 2010-06-03 | 627180.86 | 5.270
2878 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BAKER |  | 02 | 0009499 | This project is a roadway maintenance repaving project in Baker County. This project is the milling and resurfacing of County Road 122/PRETORIA ROAD from SR 91 to DOUGHERTY COUNTY LINE for a total pr | Pavement Improvement | 2010-02-03 | 2010-05-12 | 2010-07-31 | 2010-07-28 | 647641.2 | 7.490
2879 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BEN HILL |  | 08 | 0009500 | This project is a roadway maintenance repaving project in Ben Hill County. This project is the milling and resurfacing of County Road 254/OSIERFIELD from SR 206 to IRWIN COUNTY LINE for a total proje | Pavement Improvement | 2010-01-19 | 2010-04-07 | 2010-06-30 | 2010-06-02 | 90941.2 | 1.090
2880 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BERRIEN |  | 01 | 0009501 | This project is a roadway maintenance repaving project in Berrien County. This project is the milling and resurfacing of County Road 359/WYCLIFF ROBERTS ROAD from SR 158 to County Road 238/GLADYS ROA | Pavement Improvement | 2010-01-19 | 2010-03-25 | 2010-07-31 | 2010-05-19 | 451816.03 | 6.870
2881 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | COLQUITT |  | 02 | 0009502 | This project is a roadway maintenance repaving project in Colquitt County. This project is the milling and resurfacing of City Street 759/City Street 1025/WEST BLVD from SR 33/US 319 to City Street 7 | Pavement Improvement | 2010-02-01 | 2010-06-07 | 2010-06-30 | 2010-07-22 | 315921.17 | 1.930
2882 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | COOK |  | 01 | 0009503 | This project is a roadway maintenance repaving project in Cook County. This project is the milling and resurfacing of County Road 247/MASSEE POST ROAD from BOONE ROAD to LONNIE GRIMSLEY ROAD for a to | Pavement Improvement | 2010-01-21 | 2010-06-14 | 2010-06-30 | 2010-07-22 | 163291.52 | 1.530
2883 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | DOUGHERTY | ALBANY | 02 | 0009504 | This project is a roadway maintenance repaving project in Dougherty County. This project is the milling and resurfacing of WEST OAKRIDGE DRIVE from OLD PRETORIA ROAD to LOCKETT STATION for a total pr | Pavement Improvement | 2010-01-21 | 2010-04-26 | 2010-06-30 | 2010-06-15 | 605627.45 | 3.200
2884 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | GRADY |  | 02 | 0009506 | This project is a roadway maintenance repaving project in Grady County. This project is the milling and resurfacing of County Road 315/17TH AVE from SR 93/SR 111 to 0.30 MI east of SR 38/US 84 for a | Pavement Improvement | 2010-02-05 | 2010-06-03 | 2010-07-31 | 2010-07-26 | 59611.55 | 0.460
2885 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LEE | ALBANY | 02 | 0009507 | This project is a roadway maintenance repaving project in Lee County. This project is the milling and resurfacing of County Road 227/PINEWOOD ROAD from KINCHAFOONEE CREEK to County Road 229/BRONWOOD | Pavement Improvement | 2010-02-04 | 2010-05-28 | 2010-07-31 | 2010-07-09 | 119556.7 | 1.160
2886 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LEE |  | 02 | 0009508 | This project is a roadway maintenance repaving project in Lee County. This project is the milling and resurfacing of County Road 231/NORTH PHILEMA ROAD from SR 32 to County Road 232/NEW YORK ROAD for | Pavement Improvement | 2010-02-04 | 2010-05-28 | 2010-07-31 | 2010-07-09 | 404408.7 | 4.680
2887 | Completed | C200,C240 | Highway Infrastructure Investment Grant | GEORGIA | LOWNDES | VALDOSTA | 01 | 0009509 | This project is a roadway maintenance repaving project in Lowndes County. This project is the milling and resurfacing of County Road 779/HOWELL ROAD from County Road 1274/STATENVILLE to SR 7/PERIMETE | Pavement Improvement | 2010-01-21 | 2010-03-25 | 2010-06-30 | 2010-06-10 | 214123.38 | 1.950
2888 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LOWNDES | VALDOSTA | 02 | 0009510 | This project is a roadway maintenance repaving project in Lowndes County. This project is the milling and resurfacing of County Road 782/MORVEN ROAD from SR 122 to BROOKS COUNTY LINE for a total proj | Pavement Improvement | 2010-02-04 | 2010-03-30 | 2010-07-31 | 2010-06-11 | 382144.56 | 4.060
2889 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MILLER |  | 02 | 0009511 | This project is a roadway maintenance repaving project in Miller County. This project is the milling and resurfacing of County Road 189/GRADY COBB ROAD from SHINGLER ROAD to THREE NOTCH ROAD for a to | Pavement Improvement | 2010-02-03 | 2010-05-24 | 2010-07-31 | 2010-06-30 | 343454.18 | 3.970
2890 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MITCHELL |  | 02 | 0009512 | This project is a roadway maintenance repaving project in Mitchell County. This project is the milling and resurfacing of County Road 275/RIVER ROAD from SR 65 to County Road 11/SLASH ROAD for a tota | Pavement Improvement | 2010-02-05 | 2010-06-03 | 2010-07-31 | 2010-07-26 | 689910.75 | 7.350
2891 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RANDOLPH |  | 02 | 0009513 | This project is a roadway maintenance repaving project in Randolph County. This project is the milling and resurfacing of County Road 161/LOWER SHELLMAN from SR 41 to TERRELL COUNTY LINE for a total | Pavement Improvement | 2010-02-05 | 2010-05-19 | 2010-07-31 | 2010-07-26 | 317738.59 | 4.160
2892 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | TIFT |  | 08 | 0009514 | This project is a roadway maintenance repaving project in Tift County. This project is the milling and resurfacing of County Road 418/OLD UNION ROAD from SOUTHWELL BLVD to OMEGA-ELDORADO ROAD for a t | Pavement Improvement | 2010-01-21 | 2010-03-15 | 2010-07-31 | 2010-05-07 | 377064.94 | 4.350
2893 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WORTH |  | 08 | 0009515 | This project is a roadway maintenance repaving project in Worth County. This project is the milling and resurfacing of County Road 415/PHILLIP CAUSEY ROAD from SR 33 to County Road 412/SUMNER ROAD fo | Pavement Improvement | 2010-02-11 | 2010-05-13 | 2010-07-31 | 2010-07-31 | 371356.1 | 5.480
2894 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | BULLOCH |  | 12 | 0009516 | This project is a roadway maintenance repaving project in Bulloch County. This project is the milling and resurfacing of County Road 577/DENMARK-NEVILS ROAD from County Road 584/GROVELAND ROAD to SR | Pavement Improvement | 2010-01-21 | 2010-04-08 | 2010-06-30 | 2010-05-26 | 322159.17 | 2.520
2895 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | CAMDEN |  | 01 | 0009517 | This project is a roadway maintenance repaving project in Camden County. This project is the milling and resurfacing of County Road 141/HARRIETTS BLUFF ROAD from DEEP CREEK to CHEMICAL PLANT for a to | Pavement Improvement | 2010-02-01 | 2010-03-22 | 2010-07-31 | 2010-06-09 | 408522.94 | 3.730
2896 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | EFFINGHAM |  | 12 | 0009518 | This project is a roadway maintenance repaving project in Effingham County. This project is the milling and resurfacing of County Road 307/CLYO-KILDARE ROAD from SR 21 to north of PR 443 for a total | Pavement Improvement | 2010-02-04 | 2010-05-05 | 2010-07-31 | 2010-06-24 | 1105065.17 | 10.257
2897 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | EVANS |  | 12 | 0009519 | This project is a roadway maintenance repaving project in Evans County. This project is the milling and resurfacing of County Road 233/OLD HWY 250 from TATTNALL CO LINE to County Road 204/SUNBURY ROA | Pavement Improvement | 2010-01-19 | 2010-07-01 | 2010-07-31 | 2010-08-21 | 810587.86 | 5.810
2898 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TATTNALL |  | 12 | 0009520 | This project is a roadway maintenance repaving project in Tattnall County. This project is the milling and resurfacing of County Road 509/OLD HWY 250 from SR 73/US 301 to EVANS COUNTY LINE for a tota | Pavement Improvement | 2010-01-19 | 2010-07-01 | 2010-07-31 | 2010-08-21 | 563837.92 | 3.890
2899 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | TOOMBS |  | 12 | 0009521 | This project is a roadway maintenance repaving project in Toombs County. This project is the milling and resurfacing of County Road 335/THOMPSON POND ROAD from SR 292 to VIDALIA CITY LIMITS for a tot | Pavement Improvement | 2010-02-11 | 2010-03-31 | 2010-06-30 | 2010-06-07 | 268408.74 | 1.400
2900 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | WAYNE |  | 01 | 0009522 | This project is a roadway maintenance repaving project in Wayne County. This project is the milling and resurfacing of County Road 392/SUNSET BLVD from SR 169 to north of SR 38/US 84 for a total proj | Pavement Improvement | 2010-01-21 | 2010-05-24 | 2010-06-30 | 2010-07-15 | 309230.77 | 1.500
2901 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATTOOGA |  | 11 | 0009523 | This project is a roadway maintenance repaving project in Chattooga County. This project is the milling and resurfacing of County Road 329/GORE-SUBLIGNA ROAD from SR 1/US 27 to County Road 29/JOHNSTO | Pavement Improvement | 2010-02-04 | 2010-05-13 | 2010-07-31 | 2010-07-09 | 484286.75 | 4.290
2902 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | FLOYD | ROME | 11 | 0009524 | This project is a roadway maintenance repaving project in Floyd County. This project is the milling and resurfacing of City Street 1124/BROAD STREET from SR 1/US 27 to COOSA RIVER for a total project | Pavement Improvement | 2010-02-05 | 2010-06-06 | 2010-06-30 | 2010-06-30 | 244519.69 | 0.750
2903 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | FLOYD | ROME | 11 | 0009525 | This project is a roadway maintenance repaving project in Floyd County. This project is the milling and resurfacing of City Street 642/Charlton Street from SR 1/US 27 to County Road 1050/Division Str | Pavement Improvement | 2010-03-11 | 2010-07-13 | 2010-06-30 | 2010-08-25 | 145684.43 | 1.010
2904 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | GORDON |  | 10 | 0009526 | This project is a roadway maintenance repaving project in Gordon County. This project is the milling and resurfacing of County Road 483/CRAIGTOWN ROAD from SR 225 to SR 3/US 41 for a total project le | Pavement Improvement | 2010-01-19 | 2010-02-03 | 2010-06-30 | 2010-06-17 | 187972.56 | 2.450
2905 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | GORDON |  | 10 | 0009527 | This project is a roadway maintenance repaving project in Gordon County. This project is the milling and resurfacing of County Road 483/NEWTOWN CHURCH ROAD from SR 225 to County Road 21/NEWTOWN ROAD | Pavement Improvement | 2010-02-05 | 2010-04-06 | 2010-06-30 | 2010-06-17 | 122420.55 | 1.130
2906 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0009528 | This project is a roadway maintenance repaving project in Paulding County. This project is the milling and resurfacing of County Road 467/DALLAS NEBO ROAD from SR 61 to County Road 472/FROG ROAD for | Pavement Improvement | 2010-03-03 | 2010-03-04 | 2010-07-31 | 2010-07-20 | 386427.16 | 3.010
2907 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0009530 | This project is a roadway maintenance repaving project in Clayton County. This project is the milling and resurfacing of County Road 1351/REX ROAD from SR 42 to I-675 for a total project length of 0. | Pavement Improvement | 2010-02-05 | 2010-04-19 | 2010-06-30 | 2010-05-26 | 149377.29 | 0.660
2908 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TURNER |  | 08 | 0009531 | This project is a roadway maintenance repaving project in Turner County. This project is the milling and resurfacing of County Road 249/WARWICK HWY from east of County Road 96/OAK GROVE to County Roa | Pavement Improvement | 2010-01-19 | 2010-04-07 | 2010-06-30 | 2010-06-02 | 121085.44 | 1.580
2909 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0009532 | This project is a roadway maintenance repaving project in Cobb County. This project is the milling and resurfacing of County Road 1720/Windy Hill from County Road 1154/Powers Ferry Road to SR 3/US 41 | Pavement Improvement | 2010-02-24 | 2010-04-27 | 2010-06-30 | 2010-06-30 | 727189.84 | 1.570
2910 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 08 | 0009536 | "The proposed safety project is located in Newton County. This project will replace the intersection of Turner Lake Road and Clark Street currently controlled by a traffic signal with a roundabout. T | New Construction | 2010-04-29 | 2010-05-13 | 2010-11-30 | 2010-11-30 | 775622.42 | 0.800
2911 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CATOOSA | CHATTANOOGA (TN) | 09 | 0009540 | This project is a roadway maintenance repaving project in Catoosa County. This project is the milling and resurfacing of County Road 382/LAFAYETTE STREET from SR 151 to SR 3/US 41 for a total project | Pavement Improvement | 2010-02-01 | 2010-03-23 | 2010-06-30 | 2010-05-05 | 125035.57 | 1.780
2912 | Underway | C950 | Ferryboat | GEORGIA | CHATHAM | SAVANNAH | 12 | 0009541 | This project is a Ferry Boat project with the Chatham Area Transit System (CATS) in Savannah. The funds will be used to purchase a new ferry boat for the Sanannah Belles Ferry system operated by CATS | Other | 2010-04-23 | 2010-04-23 |  |  | 1000000 | 0.000
2913 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | POLK |  | 11 | 0009562 | This is a transportation enhancement project in Polk County in the City of Cedartown. Phase II of the Main Street project accomplishes a complete streetscape within the Cedartown Historic District. | Transportation Enhancements | 2011-03-24 | 2011-07-25 | 2012-12-31 |  | 625000 | 0.370
2914 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009563 | This project is an enhancement project in Fulton County. This project will install multi-use trail along the west side of Medlock Bridge Road for a distance of .1 miles just north of Grove Point Road | Transportation Enhancements | 2011-01-18 |  | 2011-08-15 |  | 84359.94 | 0.100
2915 | Underway | C250 | Highway Infrastructure Investment Grant | GEORGIA | WASHINGTON |  | 12 | 0009598 | This project is an intersection improvement in Washington County. This project consists of intersection improvements on State Route 15 at Matthews Road in the City of Tennille. The project begins at | Safety/Traffic Management | 2010-01-19 | 2010-04-06 | 2011-09-30 |  | 2883272.29 | 0.590
2916 | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 03 | 0009601 | This is an enhancement project in Muscogee County. The project construction consists of the construction of a 10 to 12 foot multi use trail beginning at Cooper Creek Park and extending to Psalmond Ro | Transportation Enhancements | 2010-08-27 | 2010-10-21 | 2012-06-30 |  | 1175017.9 | 12.000
2917 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | APPLING |  | 01 | 0009603 | This project will replace two bridges in Appling County. The replacement of the bridges at SR 4/US 1 at Blackwater Creek and Sweetwater Creek will be constructed in conjunction with a roadway widenin | Bridge Replacement | 2010-01-06 | 2010-01-20 | 2012-08-31 |  | 1080619.77 | 1.000
2918 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 08 | 0009604 | This project is a roadway widening project in Newton County. The project is to widen SR 142 from south of SR 12/US 278 to CR 72/Industrial Boulevard. The project ties to I-20 at the SR 142 interchan | Pavement Widening | 2010-01-12 | 2010-03-01 | 2012-10-31 |  | 12486733.91 | 1.110
2919 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | APPLING |  | 01 | 0009605 | This project is a roadway widening project in Appling County. The project will widen and reconstruct US 1/SR 4 from the Bacon County line north to SR 15. From the Bacon County line to CR 493, the US | Pavement Widening | 2010-01-06 | 2010-01-20 | 2012-08-31 |  | 31591082.32 | 9.100
2920 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009606 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 2509/WALTON WAY from SR 4 to SR 10 for a total project length of | Pavement Improvement | 2010-08-30 | 2010-09-29 | 2011-07-31 | 2011-07-12 | 616437.57 | 1.090
2921 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009607 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 1507/WALTON WAY from SR 4 to County Road 2623/JOHNS ROAD for a to | Pavement Improvement | 2010-08-30 | 2010-09-29 | 2011-07-31 | 2011-07-12 | 571012.51 | 1.710
2922 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009608 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 1507/WALTON WAY from County Road 2623/JOHNS RD to County Road 150 | Pavement Improvement | 2010-08-30 | 2010-09-29 | 2011-07-31 | 2011-07-12 | 700801.97 | 3.340
2923 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | 0009609 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 475/LANEY WALKER BLVD from SR 28 to County Road 476/NEW SAVANNAH | Pavement Improvement | 2010-08-30 | 2010-09-29 | 2011-07-31 | 2011-07-12 | 873141.01 | 2.730
2924 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009610 | This project is a safety project in Augusta/Richmond County. This project will upgrade traffic signal equipment and upgrade pedestrian accomodations at the following intersections in the City of Augu | Safety/Traffic Management | 2010-06-25 | 2011-01-11 | 2011-07-31 | 2011-12-15 | 2823816.02 | 1.040
2925 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009621 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 164/FLOWING WELLS ROAD from County Road 573/WHEELER ROAD to SR 10 | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 279472.77 | 1.460
2926 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009622 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 221/SOUTH OLD BELAIR ROAD from SR 383 to SR 232 for a total proje | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 627287.11 | 3.290
2927 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009623 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 1236/EVANS-TO-LOCKS ROAD from SR 104 to SR 28 for a total project | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 516864.85 | 2.590
2928 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009624 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 176/OLD EVANS RD from SR 104 to the CSX Railroad Crossing (Crossi | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 433701.43 | 0.590
2929 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009625 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of SR 28 from County Road 1236/EVANS-TO-LOCKS ROAD to SAVANNAH RIVER for a total | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 694049.06 | 3.920
2930 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | BUTTS |  | 08 | 0009632 | This project will construct pasing lanes on State Route 42 in Butts County. The project will construct two passing lanes along a 3.08-mile stretch of SR 42/US 23 between the cities of Jackson and Jen | New Construction | 2010-01-29 | 2010-03-31 | 2012-01-31 |  | 7308819.57 | 3.079
2931 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TERRELL |  | 02 | 0009634 | This project is a bridge replacement on a county road in Terrell County. Project construction will replace the structurally deficient bridge at Sasser-Herod Road 164, over Chickasawhatchee Creek. T | Bridge Replacement | 2010-01-21 | 2010-02-15 | 2011-09-30 | 2011-05-10 | 1143296.85 | 0.550
2932 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TERRELL |  | 02 | 0009635 | This project is a bridge replacement on a county road in Terrell County. Project construction will replace the structurally deficient bridge at CR 164/Sasser-Herod Road over Brantley Creek. The exist | Bridge Replacement | 2010-01-21 | 2010-02-15 | 2011-09-30 | 2011-05-10 | 960229.2 | 0.470
2933 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | 0009636 | The proposed project will provide sidewalks with curb and gutter drainage, lighting, benches, trash receptacles, thermoplastic striping at cross walks, and bicycle parking. The project limits include | Transportation Enhancements | 2010-08-16 | 2010-06-17 | 2011-12-31 | 2011-12-08 | 965323.8 | 0.630
2934 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0009638 | This project is a roadway widening project in Cobb County. The project will widen SR 120/Roswell Road from SR 120 Alternate to Bridgegate Drive. The initial 22% of the project is located within the | Pavement Improvement | 2010-02-05 | 2010-03-08 | 2012-12-31 |  | 10216130.63 | 1.820
2935 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0009641 | This project will construct a new roadway in DeKalb County. The project consists of extending the existing Lithonia Industrial Boulevard on new location between South Stone Mountain Lithonia Road to | Pavement Widening | 2010-03-11 | 2010-03-17 | 2012-09-30 |  | 18666021.45 | 1.330
2936 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0009642 | This project will replace a structurally deficient bridge on County Road 467 in Paulding County. Construction will replace the bridge and approaches on County Road 467/Bakers Bridge Road over Sweetwa | Bridge Replacement | 2010-03-02 | 2010-03-17 | 2011-05-31 | 2011-11-21 | 2195289.94 | 0.430
2937 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0009680 | This project consists of road resurfacing on East McIntosh Road beginning at Old Atlanta Road and extending to North Hill Street. | Pavement Improvement | 2010-03-19 | 2010-05-12 | 2010-08-31 | 2010-07-19 | 258279.36 | 1.320
2938 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0009682 | This project consists of road resurfacing on Old Atlanta Road beginning at the Griffin City limits and extending to the Henry County line. | Pavement Improvement | 2010-03-19 | 2010-05-12 | 2010-08-31 | 2010-07-19 | 660446.03 | 5.250
2939 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0009683 | This project consists of road resurfacing at the following locations: on Old Atlanta Road from an asphalt joint north of Beatty Street to Griffin City limits, on West Popular Street from New Orleans S | Pavement Improvement | 2010-03-19 | 2010-05-12 | 2010-08-31 | 2010-07-19 | 205197.73 | 1.650
2940 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TIFT |  | 08 | 0009686 | This project is the replacement of a structurally deficient bridge in Tift County. Construction will replace the bridge on County Road 411/Salem Church Road at Ty Ty Creek with a new reinforced concr | Bridge Replacement | 2010-03-02 | 2010-03-04 | 2011-04-30 | 2010-12-15 | 2362947.56 | 0.760
2941 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | PUTNAM |  | 10 | 0009687 | This project is the widening and reconstruction of US 441 (SR 24) in Putnam County beginning just north of CR 245/Cay Road and ending at US 129/SR 44 at the Eatonton Bypass for a distance of 8.3 miles | Pavement Widening | 2010-03-19 | 2010-04-20 | 2012-05-31 |  | 34550070.72 | 8.300
2942 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CATOOSA | CHATTANOOGA (TN) | 09 | 0009692 | This project is a roadway maintenance repaving project in Catoosa County. This project is the milling and resurfacing of County Road 385/KEITH ROAD from SR 2 to LITTLE TIGER CREEK for a total project | Pavement Improvement | 2010-12-29 | 2011-03-04 | 2011-05-31 | 2011-04-13 | 383605.68 | 2.440
2943 | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | CATOOSA | CHATTANOOGA (TN) | 09 | 0009693 | This project is a roadway maintenance repaving project in Catoosa County. This project is the milling and resurfacing of County Road 171/Poplar Springs Rd from County Road 390/Three Notch Rd to SR 15 | Pavement Improvement | 2010-05-27 | 2010-07-12 | 2010-09-30 | 2010-08-25 | 584439.96 | 3.500
2944 | Completed | C250,C240 | Highway Infrastructure Investment Grant | GEORGIA | BROOKS |  | 02 | 0009701 | This project is a bridge replacement project in Brooks County. The proposed project consists of the replacement of a narrow and structurally deficient bridge on CR 305 over Pride Branch. The existin | Bridge Replacement | 2010-03-02 | 2010-03-22 | 2011-04-30 | 2011-03-25 | 1821022.77 | 0.379
2945 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0009703 | This project is a safety improvement in Atlanta. The project will construct a landscaped median along Ponce de Leon Avenue between Peachtree Street and Juniper Street to improve safety for pedestria | Safety/Traffic Management | 2011-03-17 |  | 2012-08-01 |  | 2250000 | 0.000
2946 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009704 | This project is an operational and safety improvement in Fulton County. This project is located at the intersection of S.R. 140/Holcomb Bridge Road and Barnwell Road/C.R. 107 in Roswell. Currently, S | Pavement Improvement | 2010-04-08 | 2010-06-22 | 2010-10-31 | 2011-07-15 | 271111.43 | 0.100
2947 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 07 | 0009706 | This project is a preliminary engineering project in Newton County. This project will perform the engineering plans and environmental analysis for the widening of County Road 43/Almon Road from the R | Other | 2010-06-10 | 2010-08-01 | 2012-12-31 |  | 500000 | 2.200
2948 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 07 | 0009707 | This project is a safety improvement in Newton County. This project will construct signal and intersection improvements at State Route 212 at County Road 19/Oak Hill Road. | Pavement Improvement | 2010-10-25 |  | 2011-09-30 |  | 111875.7 | 0.400
2949 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 07 | 0009708 | This project is a maintenance resurfacing project in Newton County. This project will resurface County Road 510/Gum Creek Road from State Route 81 to County Road 98/Ellis Road. The total project len | Pavement Improvement | 2010-10-25 | 2010-11-17 | 2011-09-30 | 2011-03-08 | 399289.75 | 2.510
2950 | Underway | C200,C240 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0009827 | This project is an Interstate widening project in Bibb County. This project will widen I-75 from two to three 12-foot travel lanes in each direction between Pierce Avenue and Arkwright Road. The proj | Pavement Widening | 2010-06-15 | 2010-08-18 | 2013-05-31 |  | 31168949.25 | 3.300
2951 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0010124 | This project is an operational improvement in Cobb County. This project will construct additional turning capacity at the Wade Green Road exit on I-75. This project will help alleviate congestion at | Pavement Improvement | 2010-06-08 | 2010-07-06 | 2010-10-31 | 2010-10-31 | 663237.12 | 0.400
2952 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 04 | 0010198 | This project is a maintenance resurfacing construction project in Gwinnett County. This project will resurface three local county roads: 1.) COUNTY ROAD 1954/PEACHTREE INDUSTRIAL BOULEVARD FROM PLEA | Pavement Improvement | 2010-09-28 | 2010-10-07 | 2011-07-31 | 2010-11-22 | 2000000
2953 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 13 | 0010239 | This is a bridge construction project in DeKalb County. This project will construct a new bridge and approaches on Linecrest Road over Conley Creek. The new bridge will be 354 ft. long and 49 ft. wid | New Construction | 2010-12-29 | 2011-02-25 | 2012-04-30 |  | 5299298.4
2954 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0010240 | This project is a new roadway in Paulding County. The proposed project is located on new location and begins at the intersection of Bill Carruth Parkway with SR 92 and extends northeast to tie into e | New Construction | 2011-01-25 | 2011-01-27 | 2012-07-15 |  | 13415196.1
2955 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | COOK |  | 01 | 0011061 | This project is a bridge replacement in Cook County. This project will replace the structurally deficient bridge on SR 7/US 41 over Giddens Mill Creek with a new reinforced concrete bridge. The exis | Bridge Replacement | 2009-09-24 | 2009-09-24 | 2010-09-30 | 2010-09-29 | 2009428.44 | 0.209
2956 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | PIKE |  | 03 | 0051034 | This project is a safety intersection improvement in Pike County. The purpose of this project is to improve the safety and operation by realigning the intersection of SR 18/SR 109 and SR 74. Current | Pavement Improvement | 2009-09-30 | 2009-10-29 | 2010-07-31 | 2010-07-30 | 1401078.13 | 0.520
2957 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | 0057017 | This is a bridge replacement project in Cherokee County. This project will replace a narrow and structurally deficient bridge on Howell Bridge Road (CR 107) over Sharp Mountain Creek, 2 miles southwe | Bridge Replacement | 2009-10-26 | 2009-11-30 | 2010-12-31 | 2010-08-12 | 1483456.43 | 0.130
2958 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COLQUITT |  | 02 | 0071028 | This project will replace the structurally deficient bridge on CR 186/Hagin Still Road over the Ochlockonee River in Colquitt County. The bridge is located southeast of the city of Doerun. The 140'x | Bridge Replacement | 2009-09-24 | 2009-09-28 | 2010-08-31 | 2010-08-02 | 1235527.02 | 0.230
2959 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | LOWNDES | VALDOSTA | 01 | 0073033 | This project will acquire right of way for a future construction project in the City of Valdosta in Lowndes County. The project will purchase the necessary land for the future construction of the ove | Other | 2010-09-22 | 2010-09-22 |  |  | 7053399
2960 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 00SW004 | This project will construct sidewalks on Holcomb Bridge Road in Fulton County. The construction proposes to add 5' sidewalks 2' behind the back of the existing curb on both sides of Holcomb Bridge Ro | Transportation Enhancements | 2009-11-16 | 2009-11-16 | 2010-08-31 |  | 1258115.94 | 0.490
2961 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 00TS047 | This project is a safety and operational improvement in the City of Columbus in Muscogee County. This project is the installation of fiber optic communications cable and closed circuit television (CC | Safety/Traffic Management | 2010-02-11 | 2010-07-20 | 2011-06-30 |  | 1034304.2 | 0.000
2962 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 00TS048 | This project is a safety and operational improvement in the City of Columbus in Muscogee County. The Columbus Regional Traffic Control Center (TCC) will provide the core communications and infrastruc | Safety/Traffic Management | 2010-02-11 | 2010-07-20 | 2011-06-30 |  | 689336.84 | 0.000
2963 | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | DOUGHERTY | ALBANY | 02 | 0133005 | This project is a roadway widening in Dougherty County. This project widens and reconstructs SR 234/Gillionville Road from Eight Mile Road to Lockett Station Road. The existing two lane roadway wil | Pavement Widening | 2009-08-19 | 2009-09-25 | 2011-09-30 |  | 7651900.03 | 2.170
2964 | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0161092 | This project will acquire right of way for a future construction project in the City of Macon in Bibb County. The project will purchase the necessary land for the future construction of improvements | Other | 2010-09-22 | 2010-09-22 |  |  | 3833500
2965 | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0161104 | This project will acquire right of way for a future construction project in the City of Macon in Bibb County. The project will purchase the necessary land for the future construction of improvements | Other | 2010-09-22 | 2010-09-22 |  |  | 9182106.65
2966 | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0161131 | This project will acquire right of way for a future construction project in the City of Macon in Bibb County. The project will purchase the necessary land for the future construction of improvements | Other | 2010-09-22 | 2010-09-22 |  |  | 790500
2967 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0181070 | This is an intersection safety project in Paulding County. This intersection improvement is located 8.2 miles southwest of the City of Dallas on SR 61 at the intersection with County Road 472 and Cou | Pavement Improvement | 2010-03-02 | 2010-05-11 | 2010-12-31 | 2011-02-18 | 1441955.14 | 0.550
2968 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | TERRELL |  | 02 | 0291032 | This project is the reconstruction and rehabilitation of SR 49 in Terrell County north of the city of Dawson. The project limits begin at the junction with SR 45 and continue for 3.14 miles. SR 49 cur | Pavement Improvement | 2010-02-04 | 2010-02-11 | 2011-04-30 |  | 3960447.86 | 2.980
2969 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | WILKINSON |  | 08 | 0540019 | This project is the construction of the North Gordon Bypass, a new roadway, from SR 57 at the Twiggs/Wilkinson County Line to SR 243 at Lake Tchucoloako. The total length of project is 7.2 miles. The | New Construction | 2009-09-01 | 2009-10-26 | 2012-07-31 |  | 33387811.03 | 7.200
2970 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | 0641049 | This is a bridge replacement project in Chatham County. This project will replace the US 17/SR 25 bridge over Norfolk Southern Railroad approximately 5.5 miles north of Savannah in Port Wentworth. T | Bridge Replacement | 2009-07-27 | 2009-07-28 | 2012-05-31 |  | 4243981.55 | 0.230
2971 | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0661036 | This project will construct auxiliary lanes on SR 87 in Bibb County. The project will reconstruct SR 87/US 23 from an existing four-lane roadway with a 40-ft depressed median with rural shoulders to | Pavement Improvement | 2009-09-24 | 2009-11-12 | 2011-04-30 |  | 8359335.95 | 2.120
2972 | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0752177 | This project will acquire right of way for a future construction project in the City of Macon in Bibb County. The project will purchase the necessary land for the future construction of improvements | Other | 2010-09-22 | 2010-09-22 |  |  | 136000
2973 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0852176 | This project is the construction of an Advanced Traffic Management System along Interstate 85 in Gwinnett County. The proposed project involves the installation of fiber optic cable and High Density | Safety/Traffic Management | 2009-09-18 | 2010-01-09 | 2010-10-31 | 2010-10-31 | 2164670.45 | 4.910
2974 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0998001 | This project will rehabilitate and improve the safety at the bridge over I-85 and widening of SR 324 approaching the bridge in Gwinett County. This project replaces the two-lane bridge on Gravel Spri | Bridge Replacement | 2009-09-04 | 2009-10-02 | 2012-05-31 |  | 11912476 | 0.800
2975 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | 1631020 | This project is an intersection improvement in Henry County. The project will install signalization of a stop condition intersection and the addition of left and right turn lanes to SR 81 at the inte | Safety/Traffic Management | 2010-01-08 | 2010-01-20 | 2010-11-05 | 2010-11-05 | 564071.31 | 0.250
2976 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 6751001 | This project will install the NaviGAtor system along I-675 from I-75 to I-285 in Clayton, Dekalb and henry Counties. Included in the project will be two changeable message signs, vehicle detection co | Safety/Traffic Management | 2009-08-18 | 2009-08-18 | 2010-12-31 | 2011-04-30 | 1894362.88 | 10.700
2977 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | 7532950 | This project is a bridge replacement in Douglas County. The proposed project consists of replacing the existing structurally deficient bridge (48.43 Suff. Rating) along County Road 815/Anneewakee Roa | Bridge Replacement | 2009-09-24 | 2009-10-23 | 2010-12-31 | 2010-12-16 | 1876015.68 | 0.419
2978 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 9014024 | This project is a culvert replacement in Dekalb County. The proposed project will replace the existing box culvert and wooden pedestrian bridge on SR 155/Candler Road at Shoal Creek with a larger con | Bridge Replacement | 2009-09-23 | 2009-11-12 | 2011-03-31 |  | 1394072.48 | 0.260
2979 | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 9161001 | The proposed project would replace the existing Mitchell Street Bridge located over CSX Railroad between Techwood Drive and Spring Street. The existing bridge is in need of replacement due to inadequa | Bridge Replacement | 2010-01-05 | 2010-03-29 | 2012-05-31 |  | 8559194.8 | 0.578
2980 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | 9398001 | This project is the construction of intersection improvements on Kings Highway at Central Church Road in Douglas County. The project will provide a separate left turn bay for westbound movements onto | Safety/Traffic Management | 2009-09-18 | 2009-11-12 | 2011-04-30 | 2011-03-01 | 709598.68 | 0.330
2981 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | JASPER |  | 08 | M000355 | This project will construct maintenance improvements in Jasper County. This project consists of drainage improvements at the intersection of State Route 83 and Church Street in the City of Monticello | Pavement Improvement | 2010-10-25 | 2011-02-01 | 2011-09-30 | 2011-11-30 | 201098.85
2982 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BULLOCH |  | 12 | M003694 | This project is a maintenance construction project in Bulloch County. This project is the resurfacing of SR 26. This section of SR 26 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2010-01-19 | 2010-07-30 | 2010-10-31 | 2010-10-26 | 2055114.84 | 10.810
2983 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | ROCKDALE | ATLANTA | 04 | M003836 | This is a maintenance construction project in Rockdale County. This project is the milling and resurfacing of SR 162 from the Newton County Line to County Road 666/Dogwood Drive. This section of SR | Pavement Improvement | 2009-07-17 | 2009-08-13 | 2010-05-31 | 2009-10-02 | 375211.24 | 2.390
2984 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | EFFINGHAM |  | 12 | M003841 | This project is a maintenance construction project in Effingham County. This project is the resurfacing of SR 26. This section of SR 26 needs resurfacing because the existing pavement is deterioratin | Pavement Improvement | 2010-01-12 | 2010-06-16 | 2010-08-31 | 2010-08-30 | 1238031.3 | 5.390
2985 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JACKSON |  | 10 | M003862 | This project is a maintenance construction project in Jackson County. This project is the resurfacing of SR 82. This section of SR 82 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2009-07-20 | 2010-01-15 | 2010-05-31 | 2010-05-26 | 919166.88 | 6.200
2986 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | QUITMAN |  | 02 | M003896 | This project is a maintenance construction project in Quitman and Randolph Counties. This project is the milling and resurfacing of SR 50. This section of SR 50 needs resurfacing because the existing | Pavement Improvement | 2009-06-19 | 2010-01-15 | 2010-03-31 | 2010-03-31 | 2400679.95 | 11.260
2987 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COFFEE |  | 01 | M003897 | This is a maintenance construction project in Coffee County. This project is the milling and resurfacing of SR 31/US 441 from SR 135 to City Street 787/McNeal Drive. This section of SR 31 needs resur | Pavement Improvement | 2009-07-06 | 2009-08-26 | 2010-04-30 | 2010-01-27 | 621118.73 | 2.400
2988 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | DOUGHERTY | ALBANY | 02 | M003898 | This project is a maintenance construction project in Dougherty County. The project is the milling and resurfacing of SR 133 from SR 91 to the Lee County Line. This section of SR 133 needs resurfacin | Pavement Improvement | 2009-06-19 | 2009-07-30 | 2010-01-31 | 2009-09-30 | 212840.33 | 1.070
2989 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MADISON |  | 10 | M003906 | This is a maintenance construction project in Madison County. The project is the resurfacing of SR 98 from SR 8/US 29 to SR 72. Ths section of SR 98 needs resurfacing because the existing pavement is | Pavement Improvement | 2009-06-25 | 2009-07-25 | 2010-03-31 | 2009-09-25 | 727428.34 | 7.400
2990 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TOWNS |  | 10 | M003907 | This is a maintenance construction project in Towns County. The project is the milling and rsurfacing of SR 75 from SR 2 to the North carolina State Line. This section of SR 75 needs resurfacing beca | Pavement Improvement | 2009-06-19 | 2009-08-17 | 2010-03-31 | 2009-11-03 | 499471.21 | 3.400
2991 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | M003908 | This is a maintenance construction project in Hall County. The project is the resurfacing of SR 283 from SR 60 to SR 52/Dahlonega Highway. This section of SR 283 needs resurfacing because the existin | Pavement Improvement | 2009-06-25 | 2009-08-24 | 2010-04-30 | 2009-11-20 | 1256437.78 | 9.300
2992 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MONTGOMERY |  | 03 | M003909 | This project is a maintenance construction project in Jeff Davis and Montgomery Counties. This project is the resurfacing of SR 135. This section of SR 135 needs resurfacing because the existing pave | Pavement Improvement | 2009-07-17 | 2010-01-29 | 2010-05-31 | 2010-06-04 | 3005126.83 | 18.570
2993 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | M003910 | This project is a maintenance construction project in Chatham County. This project is the milling and resurfacing of SR 307. This section of SR 307 needs resurfacing because the existing pavement is | Pavement Improvement | 2009-06-30 | 2010-02-10 | 2010-04-30 | 2010-04-30 | 1218927.47 | 5.940
2994 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | M003911 | This project is a maintenance construction project in Chatham County. This project is the milling and resurfacing of SR 30. This section of SR 30 needs resurfacing because the existing pavement is de | Pavement Improvement | 2009-06-30 | 2010-02-10 | 2010-04-30 | 2010-04-30 | 145754.78 | 0.980
2995 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BACON |  | 01 | M003914 | This project is a maintenance construction project in Bacon County. This project is the milling and resurfacing of SR 32. This section of SR 32 needs resurfacing because the existing pavement is dete | Pavement Improvement | 2009-06-30 | 2009-12-17 | 2010-03-31 | 2010-03-31 | 1104555.89 | 4.560
2996 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHARLTON |  | 01 | M003916 | This is a maintenance construction project in Charlton County. The project is the resurfacing of SR 4/US 1 from north of SR 4 to the Ware County Line. This section of SR 4 needs resurfacing because t | Pavement Improvement | 2009-06-25 | 2009-07-13 | 2010-04-30 | 2010-01-15 | 3662131.81 | 11.730
2997 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHARLTON |  | 01 | M003917 | This is a maintenance construction project in Charlton County. This project is the resurfacing of SR 40 Connector from SR 40 to SR 4. This section of SR 40 Connector needs resurfacing because the exis | Pavement Improvement | 2009-06-25 | 2009-07-13 | 2010-04-30 | 2010-01-15 | 184320.81 | 1.330
2998 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WALKER |  | 09 | M003920 | This project is a maintenance construction project in Walker County. This project is the milling and resurfacing of SR 1 Businesss. This section of SR 1 Business needs resurfacing because the existin | Pavement Improvement | 2009-07-06 | 2009-09-10 | 2010-04-30 | 2010-04-30 | 721762.53 | 3.340
2999 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BARTOW |  | 11 | M003921 | This is a maintenance construction project in Bartow County. This project is the milling and resurfacing of SR 3 from south of Peachtree Street to north of MLK Jr. Drive in Cartersville. This sectio | Pavement Improvement | 2009-06-25 | 2009-08-18 | 2010-04-30 | 2010-03-31 | 687940.38 | 1.630
3000 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | M003923 | This project is a maintenance construction project in Cherokee County. This project is the resurfacing on SR 140. This section of SR 140 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 2009-06-25 | 2009-09-08 | 2010-03-31 | 2010-03-31 | 1723372.74 | 10.610
3001 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | SUMTER |  | 02 | M003932 | This is a maintenance construction project in Sumter County. This project is the milling and resurfacing of SR 27 West from SR 27 to SR 3/US 19 in Americus. This section of SR 27 West needs resurfaci | Pavement Improvement | 2009-06-25 | 2009-08-02 | 2009-12-31 | 2009-11-23 | 553607.37 | 2.130
3002 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | SUMTER |  | 02 | M003933 | This is a maintenance construction project in Sumter County. This project is the milling and resurfacing of SR 27 from SR 3/US 19 to SR 27 West/SR 30 in Americus. This section of SR 27 needs resurfac | Pavement Improvement | 2009-06-25 | 2009-08-02 | 2009-12-31 | 2009-11-23 | 587913.19 | 2.136
3003 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | M003935 | This project is a maintenance construction project in Richmond County. This project is the milling and resurfacing of SR 28. This section of SR 28 needs resurfacing because the existing pavement is d | Pavement Improvement | 2009-10-26 | 2010-02-21 | 2010-06-30 | 2010-04-30 | 1321753.67 | 2.720
3004 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DODGE |  | 03 | M003938 | This is a maintenance construction project in Dodge County. This project is the milling and resurfacing of SR 117 from south of Front Street to Sugar Creek Bridge. This section of SR 117 needs resurf | Pavement Improvement | 2009-06-22 | 2009-07-09 | 2010-03-31 | 2009-10-29 | 2143580.71 | 13.620
3005 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JEFFERSON |  | 12 | M003941 | This project is a maintenance construction project in Jefferson County. This project is the milling and resurfacing of SR 4. This section of SR 4 needs resurfacing because the existing pavement is de | Pavement Improvement | 2009-10-26 | 2010-04-29 | 2010-08-31 | 2010-08-26 | 3438984.42 | 13.610
3006 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | M003942 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 9 from the Chattahoochee River to Marietta Highway. This section of SR 9 needs resurfaci | Pavement Improvement | 2009-06-25 | 2009-08-02 | 2010-04-30 | 2010-01-11 | 294065.27 | 1.210
3007 | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | M003943 | This is a maintenance construction project in Clayton and Fulton Counties. This project is the milling and resurfacing of SR 3/US 19 from Interstate 285 to City Street 3096/Cleveland Avenue. This sec | Pavement Improvement | 2009-06-26 | 2009-07-07 | 2010-03-31 | 2009-11-09 | 926853.22 | 4.170
3008 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | M003945 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 9 from Abernathy Road to the Chattahoochee River. This section of SR 9 needs resurfacing | Pavement Improvement | 2009-06-25 | 2009-08-02 | 2010-04-30 | 2010-01-11 | 1380129.96 | 5.200
3009 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | M003946 | This project is a maintenance construction project in DeKalb and Gwinnett Counties. This project is the milling and resurfacing of SR 10. This section of SR 10 needs resurfacing because the existing | Pavement Improvement | 2009-08-14 | 2010-04-16 | 2010-06-30 | 2010-08-25 | 3210565.33 | 3.830
3010 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 13 | M003947 | This project is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 14 Spur. This section of SR 14 Spur needs resurfacing because the existing pavem | Pavement Improvement | 2009-08-07 | 2010-03-05 | 2010-06-30 | 2010-05-20 | 623958.16 | 1.610
3011 | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | M003948 | This is a maintenance construction project in Fulton County. This project is the resurfacing of SR 139 from West Whitehall Street to County Road 4176/Cascade Avenue. This section of SR 139 needs resu | Pavement Improvement | 2009-06-19 | 2009-08-11 | 2010-03-31 | 2009-10-09 | 374760.91 | 1.210
3012 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | M003949 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 54 from north of I-285 to University Avenue. This section of SR 54 needs resurfacing bec | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2010-06-30 | 2010-04-08 | 1249406.17 | 5.870
3013 | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 13 | M003950 | This project is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 92. This section of SR 92 needs resurfacing because the existing pavement is det | Pavement Improvement | 2009-06-25 | 2009-09-23 | 2010-03-31 | 2009-12-03 | 837155.64 | 3.830
3014 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | M003957 | This project is a maintenance construction project in Hall County. This project is the resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 2009-06-25 | 2009-09-10 | 2010-04-30 | 2009-12-16 | 1151859.25 | 3.000
3015 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DAWSON |  | 09 | M003958 | This project is a maintenance construction project in Dawson County. This project is the resurfacing of SR 53. This section of SR 53 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2009-06-25 | 2009-11-19 | 2010-03-31 | 2010-04-29 | 1216249.24 | 6.800
3016 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HABERSHAM |  | 10 | M003959 | This project is a maintenance construction project in Habersham County. This project is the resurfacing of SR 384. This section of SR 384 needs resurfacing because the existing pavement is deteriorat | Pavement Improvement | 2009-06-25 | 2009-11-02 | 2010-03-31 | 2009-12-04 | 607850.87 | 4.200
3017 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FRANKLIN |  | 10 | M003960 | This is a maintenance construction project in Franklin County. This project is the resurfacing of SR 51 from SR 59 to County Road 168/Hale Crossing Road. This section of SR 51 needs resurfacing becau | Pavement Improvement | 2009-06-25 | 2009-08-25 | 2010-03-31 | 2009-10-29 | 956633.95 | 9.900
3018 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WHITE |  | 09 | M003961 | This is a maintenance construction project in Habersham and White Counties. The project is the resurfacing of SR 356 from SR 17 in White County to SR 197 in Habersham County. This section of SR 356 n | Pavement Improvement | 2009-06-25 | 2009-07-20 | 2010-04-30 | 2009-11-03 | 1576840.87 | 10.830
3019 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FORSYTH | ATLANTA | 09 | M003964 | This project is a maintenance construction project in Forsyth County. This project is the milling and resurfacing of SR 9. This section of SR 9 needs resurfacing because the existing pavement is dete | Pavement Improvement | 2009-06-25 | 2009-09-30 | 2010-03-31 | 2010-02-08 | 1863277.68 | 9.800
3020 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | STEPHENS |  | 10 | M003965 | This project is a maintenance construction project in Banks, Franklin and Stephens Counties. This project is the resurfacing of SR 63. This section of SR 63 needs resurfacing because the existing pav | Pavement Improvement | 2009-07-21 | 2009-09-08 | 2010-05-31 | 2010-01-04 | 1766787.98 | 12.630
3021 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BANKS |  | 10 | M003966 | This project is a maintenance construction project in Banks County. This project is the resurfacing of SR 164. This section of SR 164 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2009-06-25 | 2009-11-04 | 2010-04-30 | 2010-01-07 | 698717.04 | 4.800
3022 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | M003967 | This is an Interstate 575 maintenance construction project in Cobb and Cherokee Counties. This project is the milling and resurfacing of I-575/SR 417 from I-75 in Cobb County to the Etowah River in C | Pavement Improvement | 2009-06-25 | 2009-07-13 | 2010-05-31 | 2009-11-12 | 16297046.6 | 19.790
3023 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MARION |  | 02 | M003968 | This is a maintenance construction project in Marion County. This project is the milling and resurfacing of SR 137 from City Street 505/McDuffie Street to the Taylor County line. This section of SR 1 | Pavement Improvement | 2009-06-25 | 2009-09-09 | 2010-04-30 | 2009-12-04 | 1330615.64 | 10.530
3024 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CRAWFORD |  | 02 | M003969 | This is a maintenance construction project in Crawford and Peach Counties. The project is the milling and resurfacing of SR 7 from SR 96 in Peach County to SR 22/US 80 in Crawford County. This sectio | Pavement Improvement | 2009-07-17 | 2009-08-06 | 2010-04-30 | 2009-10-28 | 2363595.66 | 14.370
3025 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | SCHLEY |  | 02 | M003970 | This project is a maintenance construction project in Schley and Sumter Counties. This project is the milling and resurfacing of SR 153. This section of SR 153 needs resurfacing because the existing | Pavement Improvement | 2009-06-25 | 2010-02-11 | 2010-04-30 | 2010-04-30 | 1283555.96 | 8.100
3026 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | M003971 | This is a maintenance construction project in Henry County. This project is the milling and resurfacing of SR 155 from the Spalding County line to SR 20/SR 81. This section of SR 155 needs resurfacin | Pavement Improvement | 2009-06-25 | 2009-08-04 | 2010-04-30 | 2010-02-25 | 1741736.54 | 8.800
3027 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JASPER |  | 08 | M003972 | This project is a maintenance construction project in Jasper County. This project is the milling and resurfacing of SR 83. This section of SR 83 needs resurfacing because the existing pavement is dete | Pavement Improvement | 2009-06-25 | 2009-08-31 | 2010-04-30 | 2010-04-30 | 1854234.74 | 12.790
3028 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | M003973 | This project is a maintenance construction project in Richmond County. This project is the milling and resurfacing of SR 4. This section of SR 4 needs resurfacing because the existing pavement is det | Pavement Improvement | 2009-08-20 | 2009-10-20 | 2010-06-30 | 2010-05-31 | 3651665.3 | 10.200
3029 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JASPER |  | 08 | M003974 | This is a maintenance construction project in Jasper County. This project is the milling and resurfacing of SR 16 from the Butts County line to SR 11 South. This section of SR 16 needs resurfacing be | Pavement Improvement | 2009-06-25 | 2009-08-03 | 2010-04-30 | 2009-10-22 | 1430257.97 | 8.950
3030 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PUTNAM |  | 10 | M003975 | This project is a maintenance construction project in Putnam County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is dete | Pavement Improvement | 2009-06-19 | 2009-09-28 | 2010-04-30 | 2010-04-30 | 1591401.64 | 8.300
3031 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | TWIGGS |  | 08 | M003976 | This project is a maintenance construction project in Bleckley, Laurens and Twiggs Counties. This project is the concrete slab replacement of I-16/SR 404. This slab replacement of I-16 is needed becau | Pavement Improvement | 2009-11-19 | 2010-02-02 | 2011-05-31 |  | 22877913.19 | 15.320
3032 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | M003977 | This project is an interstate resurfacing project in Bryan and Chatham counties on I-95. This section of I-95 needs resurfacing because the existing pavement is deteriorating. I-95/SR 405 was last res | Pavement Improvement | 2010-01-21 | 2010-06-01 | 2010-12-31 | 2011-05-20 | 8428494.63 | 11.700
3033 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WARE |  | 01 | M003978 | This is a maintenance construction project in Ware County. This project is the milling and resurfacing of SR 4 Business/US 1 from south of County Road 341/Short Street to north of County Road 255/Smi | Pavement Improvement | 2009-06-25 | 2009-07-20 | 2010-04-30 | 2009-10-07 | 988515.6 | 5.790
3034 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | EFFINGHAM |  | 12 | M003979 | This project is a maintenance construction project in Effingham County. This project is the resurfacing of SR 17. This section of SR 17 needs resurfacing because the existing pavement is deterioratin | Pavement Improvement | 2009-06-30 | 2009-09-15 | 2010-04-30 | 2009-12-15 | 692915.25 | 4.120
3035 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHARLTON |  | 01 | M003980 | This project is a maintenance construction project in Brantley and Charlton Counties. This project is the resurfacing of SR 23. This section of SR 23 needs resurfacing because the existing pavement is | Pavement Improvement | 2009-07-06 | 2010-02-17 | 2010-04-30 | 2010-08-02 | 3231244.89 | 23.150
3036 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BRYAN |  | 01 | M003981 | This project is a maintenance construction project in Bryan County. This project is the resurfacing of SR 25. This section of SR 25 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 2009-08-20 | 2009-11-19 | 2010-06-30 | 2010-04-26 | 1604170.73 | 4.280
3037 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | ROCKDALE | ATLANTA | 04 | M003983 | This is a maintenance construction project in Rockdale County. This project is the resurfacing of SR 20 from County Road 435/Sigman Road to SR 138. This section of SR 20 needs resurfacing because the | Pavement Improvement | 2009-06-25 | 2009-07-08 | 2010-04-30 | 2009-08-25 | 282533.36 | 1.340
3038 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | ROCKDALE | ATLANTA | 04 | M003984 | This project is a maintenance construction project in Rockdale County. This project is the resurfacing of SR 20. This section of SR 20 needs resurfacing because the existing pavement is deteriorating | Pavement Improvement | 2009-08-07 | 2009-09-08 | 2010-06-30 | 2010-05-20 | 2654949.86 | 6.990
3039 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | M003985 | This project is a maintenance construction project in DeKalb County. This project is the resurfacing of SR 236/LaVista Road. This section of SR 236 needs resurfacing because the existing pavement is | Pavement Improvement | 2009-08-17 | 2009-09-08 | 2010-06-30 | 2010-06-04 | 951396.82 | 2.400
3040 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | M003986 | This project is a maintenance construction project in Cobb County. This project is the resurfacing of SR 360. This section of SR 360 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2009-08-07 | 2010-04-11 | 2010-06-30 | 2010-06-30 | 413662.76 | 2.970
3041 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | M003987 | This project is a maintenance construction project in Bibb County. This project is the resurfacing of SR 87. This section of SR 87 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 2010-01-21 | 2010-03-16 | 2010-08-31 | 2010-09-02 | 2263901.33 | 14.460
3042 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | M003988 | This project is a maintenance construction project in Bibb County. This project is the resurfacing of SR 49. This section of SR 49 needs resurfacing because the existing pavement is deteriorating. SR | Pavement Improvement | 2010-01-21 | 2010-03-16 | 2010-08-31 | 2010-09-02 | 66326.32 | 0.270
3043 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WEBSTER |  | 02 | M003989 | This project is a maintenance construction project in Marion and Webster Counties. This project is the resurfacing of SR 41. This section of SR 41 needs resurfacing because the existing pavement is d | Pavement Improvement | 2009-07-20 | 2010-04-05 | 2010-05-31 | 2010-05-31 | 1679983.13 | 12.570
3044 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TAYLOR |  | 02 | M003990 | This project is a maintenance construction project in Crawford and Taylor Counties. This project is the resurfacing of SR 128. This section of SR 128 needs resurfacing because the existing pavement i | Pavement Improvement | 2009-06-25 | 2010-03-01 | 2010-04-30 | 2010-04-30 | 2281535.24 | 14.090
3045 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HARRIS |  | 03 | M003991 | This is a maintenance construction project in Harris County. This project is the resurfacing of SR 18 from SR 219 to SR 1/US 27. This section of SR 18 needs resurfacing because the existing pavement | Pavement Improvement | 2009-06-25 | 2009-08-06 | 2010-04-30 | 2009-11-10 | 1674600.99 | 11.480
3046 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | GREENE |  | 10 | M003992 | This is a maintenance construction project in Greene County. The project is the resurfacing of SR 44 from the Putnam County line to SR 12. This section of SR 44 needs resurfacing because the existing | Pavement Improvement | 2009-06-19 | 2009-08-11 | 2010-04-30 | 2009-11-16 | 2181083.77 | 11.450
3047 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | M003993 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 56 Spur. This section of SR 56 Spur needs resurfacing because the existing pavement is det | Pavement Improvement | 2009-11-30 | 2010-04-12 | 2010-09-30 | 2010-06-18 | 2342706.9 | 6.580
3048 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON |  | 08 | M003994 | This project is a maintenance construction project in Newton County. This project is the resurfacing of SR 142. This section of SR 142 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2010-01-05 | 2010-02-01 | 2010-08-31 | 2010-09-24 | 1219852.67 | 8.300
3049 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JASPER |  | 08 | M003995 | This project is a maintenance construction project in Jasper County. This project is the resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2010-01-21 | 2010-03-03 | 2010-08-31 | 2010-08-30 | 1495888.73 | 8.600
3050 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LOWNDES | VALDOSTA | 02 | M003998 | This project is an interstate resurfacing project in Lowndes County. This project is the milling and resurfacing of I-75/SR 401. This section of I-75 needs resurfacing because the existing pavement i | Pavement Improvement | 2010-01-14 | 2010-04-26 | 2010-12-31 | 2010-12-31 | 19987728.08 | 18.050
3051 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BRYAN |  | 01 | M004000 | This project is a maintenance construction project in Bryan County. This project is the resurfacing of SR 30/US 280. This section of SR 30 needs resurfacing because the existing pavement is deteriora | Pavement Improvement | 2009-07-20 | 2009-09-16 | 2010-05-31 | 2010-04-30 | 1845487.01 | 8.850
3052 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WHEELER |  | 01 | M004001 | This project is a maintenance construction project in Montgomery and Wheeler Counties. This project is the resurfacing of SR 30. This section of SR 30 needs resurfacing because the existing pavement | Pavement Improvement | 2009-07-17 | 2009-10-09 | 2010-05-31 | 2010-01-12 | 1859265.88 | 11.520
3053 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WHEELER |  | 01 | M004003 | This project is a maintenance construction project in Wheeler County. This project is the resurfacing of SR 126. This section of SR 126 needs resurfacing because the existing pavement is deterioratin | Pavement Improvement | 2009-07-20 | 2010-04-07 | 2010-05-31 | 2010-06-08 | 1653201.91 | 12.090
3054 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WILKES |  | 10 | M004006 | This project is a maintenance construction project in Lincoln and Wilkes Counties. This project is the resurfacing of SR 47. This section of SR 47 needs resurfacing because the existing pavement is d | Pavement Improvement | 2009-09-21 | 2010-04-22 | 2010-07-31 | 2010-07-09 | 2217730.8 | 15.690
3055 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | EMANUEL |  | 12 | M004011 | This project is a maintenance construction project in Emmanuel County. This project is the resurfacing of SR 297. This section of SR 297 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 2010-01-29 | 2010-06-08 | 2010-08-31 | 2010-08-31 | 1869884.29 | 9.930
3056 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | M004012 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 104. This section of SR 104 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 2009-11-23 | 2010-06-02 | 2010-06-30 | 2010-07-27 | 110170.87 | 0.450
3057 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | M004013 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 104 East. This section of SR 104 East needs resurfacing because the existing pavement is d | Pavement Improvement | 2009-11-23 | 2010-06-02 | 2010-06-30 | 2010-07-27 | 83759.02 | 0.440
3058 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | FRANKLIN |  | 10 | M004014 | This projects provides maintenance construction on I-85 in Franklin and Hart Counties. This project is the milling and resurfacing of I-85/SR 403 from south of SR 17 in Franklin County to the South C | Pavement Improvement | 2009-09-03 | 2010-04-12 | 2010-07-31 | 2010-06-03 | 5329099.85 | 7.120
3059 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | M004015 | This project is a maintenance construction project in Hall County. This project is the removal of selected concrete slabs on SR 365. The reason for removal and replacement of the selected concrete sl | Pavement Improvement | 2009-07-29 | 2009-11-12 | 2010-05-31 | 2010-06-09 | 2044514.37 | 7.970
3060 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HOUSTON | WARNER ROBINS | 08 | M004020 | This project is a maintenance construction project in Houston County. This project is the milling and resurfacing of SR 127. This section of SR 127 needs resurfacing because the existing pavement is | Pavement Improvement | 2010-01-19 | 2010-02-19 | 2010-08-31 | 2010-06-29 | 128526.09 | 0.750
3061 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HOUSTON | WARNER ROBINS | 08 | M004021 | This project is a maintenance construction project in Houston County. This project is the resurfacing of SR 11 Business. This section of SR 11 Business needs resurfacing because the existing pavement | Pavement Improvement | 2009-08-17 | 2010-04-05 | 2010-04-30 | 2010-05-13 | 761011.16 | 4.500
3062 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | PULASKI |  | 08 | M004025 | This project is a maintenance construction project in Pulaski County. This project is the resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2009-11-23 | 2010-07-15 | 2010-09-30 | 2010-09-30 | 1689883.06 | 10.580
3063 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MERIWETHER |  | 03 | M004027 | This project is a maintenance construction project in Meriwether County. This project is the resurfacing of SR 85. This section of SR 85 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 2009-12-04 | 2010-06-01 | 2010-09-30 | 2010-08-27 | 1712474.03 | 11.100
3064 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOOLY |  | 02 | M004028 | This project is a maintenance construction project in Dooly County. This project is the resurfacing of SR 27. This section of SR 27 needs resurfacing because the existing pavement is deteriorating. S | Pavement Improvement | 2009-11-23 | 2010-08-16 | 2010-09-30 | 2010-09-30 | 1863860.66 | 11.760
3065 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | M004029 | This project is a maintenance construction project in Fayette County. This project is the resurfacing of SR 85. This section of SR 85 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2009-11-19 | 2010-06-07 | 2010-09-30 | 2010-09-30 | 2220991.05 | 9.880
3066 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | M004030 | This project is a maintenance construction project in Bibb County. This project is the milling and resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deter | Pavement Improvement | 2009-11-19 | 2010-05-18 | 2010-08-31 | 2010-09-02 | 1272250 | 5.330
3067 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | M004031 | This project is a maintenance construction project in Coweta County. This project is the resurfacing of SR 154. This section of SR 154 needs resurfacing because the existing pavement is deteriorating | Pavement Improvement | 2009-11-24 | 2010-04-30 | 2010-09-30 | 2010-08-12 | 1622334.38 | 8.360
3068 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | UPSON |  | 03 | M004032 | This project is a maintenance construction project in Lamar and Upson Counties. This project is the resurfacing of SR 36. This section of SR 36 needs resurfacing because the existing pavement is dete | Pavement Improvement | 2009-11-19 | 2010-08-17 | 2010-09-30 | 2010-10-14 | 2538255 | 15.030
3069 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LAMAR |  | 03 | M004033 | This project is a maintenance construction project in Lamar and Monroe Counties. This project is the resurfacing of SR 7. This section of SR 7 needs resurfacing because the existing pavement is deter | Pavement Improvement | 2009-11-19 | 2010-06-22 | 2010-09-30 | 2010-09-30 | 2262804.83 | 15.000
3070 | Completed | C200,C240 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | M004034 | This project is a maintenance construction project in Spalding County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is d | Pavement Improvement | 2010-01-05 | 2010-07-26 | 2010-06-30 | 2010-08-31 | 1283058 | 4.090
3071 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HOUSTON | WARNER ROBINS | 08 | M004035 | This project is a maintenance construction project in Houston County. This project is the milling and resurfacing of SR 247. This section of SR 247 needs resurfacing because the existing pavement is | Pavement Improvement | 2010-01-19 | 2010-02-19 | 2010-08-31 | 2010-06-29 | 1296822.32 | 8.570
3072 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | PEACH |  | 02 | M004036 | This project is a maintenance construction project in Peach County. This project is the milling and resurfacing of SR 247 Connector. This section of SR 247 Connector needs resurfacing because the exi | Pavement Improvement | 2010-01-20 | 2010-04-19 | 2010-07-31 | 2010-06-14 | 549412.6 | 3.010
3073 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BUTTS |  | 08 | M004037 | This project is a maintenance construction project in Butts County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is dete | Pavement Improvement | 2010-01-05 | 2010-04-19 | 2010-06-30 | 2010-06-30 | 367643.47 | 1.340
3074 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JONES |  | 08 | M004038 | This project is a maintenance construction project in Jones County. This project is the resurfacing of SR 44. This section of SR 44 needs resurfacing because the existing pavement is deteriorating. S | Pavement Improvement | 2010-01-21 | 2010-02-26 | 2010-10-31 | 2010-09-30 | 2265748.5 | 14.580
3075 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TAYLOR |  | 02 | M004039 | This project is a maintenance construction project in Taylor County. This project is the resurfacing of SR 22. This section of SR 22 needs resurfacing because the existing pavement is deteriorating. | Pavement Improvement | 2010-01-05 | 2010-03-01 | 2010-08-31 | 2010-08-13 | 1023496 | 6.180
3076 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BRANTLEY |  | 01 | M004040 | This project is a maintenance construction project in Brantley County. This project is the resurfacing of SR 520. This section of SR 520 needs resurfacing because the existing pavement is deteriorati | Pavement Improvement | 2009-08-07 | 2010-05-03 | 2010-06-30 | 2010-06-30 | 860179.41 | 3.500
3077 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | M004047 | This project is a maintenance construction project in Douglas County. This project is the milling and resurfacing of 1.7 miles of SR 92 from Durelee Lane/City Street 597 to Malone Street/City street | Pavement Improvement | 2010-05-27 | 2010-07-06 | 2011-03-31 | 2010-08-10 | 440596.76 | 1.730
3078 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | M004052 | This project is a maintenance construction project in Gwinnett County. This project is the milling and resurfacing of 5.8 miles of SR 20 from west of Peachtree Industrial Boulevard/County Road 1954 t | Pavement Improvement | 2010-05-21 | 2010-09-07 | 2011-03-31 | 2010-12-03 | 1812083.31 | 5.800
3079 | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | WHEELER |  | 01 | M004078 | This is a maintenance construction project in Telfair and Wheeler counties. This project is the resurfacing of SR 19. This section of SR 19 needs resurfacing because the existing pavement is deterior | Pavement Improvement | 2010-03-19 | 2010-09-13 | 2011-01-31 | 2011-01-21 | 804196.34 | 19.160
3080 | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | M004079 | This project is a maintenance construction project in Cherokee County. This project is the resurfacing of 4.7 miles of SR 369 from SR 20 to the Forsyth County line. This section of SR 369 needs res | Pavement Improvement | 2010-05-27 | 2010-06-27 | 2011-03-31 | 2010-09-30 | 1041773.67 | 4.720
3081 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | M004172 | This project is a maintenance resurfacing project in Baldwin County. This project is the milling and resurfacing of State Route 112 in Milledgeville. This section of State Route 112 needs resurfacing | Pavement Improvement | 2010-11-08 | 2011-03-08 | 2011-06-30 | 2011-06-20 | 900622.27
3082 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | IRWIN |  | 08 | M004199 | This is a maintenance construction project in Irwin County. This project is the resurfacing of SR 32. This section of SR 32 needs resurfacing because the existing pavement is deteriorating. SR 32 was | Pavement Improvement | 2011-01-27 | 2011-06-27 | 2011-11-30 | 2011-10-14 | 967400
3083 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | IRWIN |  | 08 | M004200 | This is a maintenance construction project in Ben Hill and Irwin Counties. This project is the resurfacing of SR 32. This section of SR 32 needs resurfacing because the existing pavement is deteriora | Pavement Improvement | 2011-01-27 | 2011-06-27 | 2011-11-30 | 2011-10-14 | 680784
3084 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MACON |  | 02 | M004210 | This is a maintenance construction project in Macon County. This project is the resurfacing of SR 240. This section of SR 240 needs resurfacing because the existing pavement is deteriorating. SR 240 | Pavement Improvement | 2011-01-27 | 2011-05-02 | 2011-10-31 | 2011-09-05 | 566300
3085 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | M004212 | This is a maintenance construction project in Bibb and Jones Counties. This project is the resurfacing of SR 49. This section of SR 49 needs resurfacing because the existing pavement is deteriorating | Pavement Improvement | 2011-01-26 | 2011-04-20 | 2011-10-31 | 2011-09-19 | 1610000
3086 | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MITCHELL |  | 02 | M004213 | This is a maintenance construction project in Mitchell County. This project is the resurfacing of SR 65. This section of SR 65 needs resurfacing because the existing pavement is deteriorating. SR 65 | Pavement Improvement | 2011-01-18 | 2011-02-17 | 2011-10-31 | 2011-07-29 | 1542000
3087 | Completed | C250,C240 | Highway Infrastructure Investment Grant | GEORGIA | JOHNSON |  | 12 | M004236 | This is a maintenance construction project in Johnson County. This project is the resurfacing of SR 78. This section of SR 78 needs resurfacing because the existing pavement is deteriorating. SR 78 w | Pavement Improvement | 2010-12-29 | 2011-04-19 | 2011-10-31 | 2011-10-10 | 1509053.2
3088 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | M004277 | This is a maintenance construction project in Baldwin County. This project is the resurfacing of SR 299. This section of SR 299 needs resurfacing because the existing pavement is deteriorating. SR 2 | Pavement Improvement | 2010-12-30 | 2011-07-05 | 2011-09-30 | 2011-09-29 | 608338.89
3089 | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOOLY |  | 02 | M004282 | This project is a an interstate rehabilitation project on I-75 in Dooly County. The proposed project involves the replacement of the existing concrete pavement and asphalt shoulders along I-75. The | Pavement Improvement | 2010-10-29 | 2011-01-06 | 2012-12-31 |  | 24277727.35
3090 | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | WAYNE |  | 01 | M004287 | This is a maintenance construction project in Wayne County. This project is the resurfacing of SR 23. This section of SR 23 needs resurfacing because the existing pavement is deteriorating. SR 23 wa | Pavement Improvement | 2010-12-29 | 2011-06-01 | 2011-10-31 | 2011-08-12 | 1064124.74
3091 | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | M004420 | This project is a an interstate rehabilitation project on I-75 in Atlanta in Cobb and Fulton Counties. This project includes resurfacing, bridge joint maintenance and guardrail upgrades along I-75 be | Pavement Improvement | 2010-12-29 | 2011-01-28 | 2011-08-31 | 2011-05-17 | 14000631.39
3092 | Underway | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 01 | 0001036 | Install and Upgrade traffic signals, including ADA improvements, signs, markings and interconnects (Komo Mai St & Hoomalu St, Waiakamilo Rd & McNeil St, N Beretania St & Aala St, Kiluea Ave, Lanikuha | Safety/Traffic Management | 2009-12-21 | 2009-12-21 | 2013-02-01 |  | 3670845.6
3093 | Completed | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 01 | 0001045 | Provide auxiliary power needed to support critical operations during prolonged power outages due to emergencies. | Safety/Traffic Management | 2010-04-30 | 2010-04-30 | 2010-07-28 | 2011-01-20 | 270774
3094 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU |  | 02 | 0011250 | Upgrade the Farrington Highway and Makakilo Separation structures over the H-1 freeway to better resist earthquake damage. (Farrington Hwy Separation) | Bridge Improvement | 2009-07-13 | 2009-07-13 | 2010-01-04 | 2009-12-16 | 834579.19 | 0.000
3095 | Underway | C240,C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 01 | 0011262 | Install longitudinal dowels into concrete sections, repair and smoothen concrete pavement at two major locations on the Interstate Route H-1 freeway from MP 2.4 to 3.46 and MP 24.9 to 26.4. | Pavement Improvement | 2010-01-29 | 2010-01-29 | 2011-08-15 |  | 6350000
3096 | Completed | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 0031079 | Upgrade the H-3 Mokapu Boulevard Interchange structure to better resist earthquake damage. | Bridge Improvement | 2010-11-08 | 2010-11-08 | 2011-06-17 | 2011-06-02 | 393000
3097 | Underway | C240 | Highway Infrastructure Investment Grant | HAWAII | HAWAII |  | 02 | 0191042 | Replacement of non-ADA compliant sidewalks and ramps along Mamalahoa Highway in Waimea, Hawaii. | Transportation Enhancements | 2011-03-18 | 2011-03-18 | 2011-07-27 |  | 841010
3098 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | HAWAII |  | 02 | 0192059 | Remove and dispose of lead-based paint and rust from steel members and paint them. Work also includes repairing/replacing steel members that need repair work. (Kukaiau Bridge MP33.6, Kuwaikahi Bridge | Bridge Improvement | 2009-09-08 | 2009-09-08 | 2011-04-07 | 2010-12-23 | 4301949.3 | 14.200
3099 | Underway | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 01 | 0300112 | Provide left turning lanes on Harding Avenue for traffic turning into the H-1 Freeway on-ramps to reduce congestion relief and improve traffic safety. | Pavement Widening | 2010-11-15 | 2010-11-15 | 2011-10-01 |  | 1921488.27 | 0.510
3100 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0311011 | Extend the life of the pavement and provide a smooth surface in areas that are starting to show distress by removal of the top layer and repaving. | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2010-02-23 | 2010-04-20 | 2757619.06
3101 | Underway | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0321009 | Replace and/or modify the existing bridge girders to provide additional clearance. | Bridge Improvement | 2010-04-02 | 2010-04-02 | 2010-06-02 |  | 1922456
3102 | Completed | C250 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0360010 | Extending the life of the pavement and provide a smooth surface in areas that are starting to show distress by providing a surface seal. | Pavement Improvement | 2009-08-26 | 2009-08-26 | 2009-10-29 | 2009-12-18 | 526005.59 | 3.320
3103 | Completed | C250,C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0460014 | Resurface and reconstruct damaged areas of the pavement. Safety (including guardrail and shoulder improvements) and ADA improvements could be included. | Pavement Improvement | 2009-08-26 | 2009-08-26 | 2009-10-22 | 2009-12-18 | 2688406 | 1.960
3104 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0470006 | Extend the life of the pavement and provide a smooth surface in areas that are starting to show distress by removal of the top pavement layer and repaving. | Pavement Improvement | 2009-08-26 | 2009-08-26 | 2009-10-29 | 2010-01-12 | 1031504.87 | 5.790
3105 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0480003 | Resurface and reconstruct damaged areas of the pavement. Safety (including guardrail and shoulder improvements) on Farrington Avenue (2.44 miles) and Puupeela Avenue (1.21 miles) | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-03-16 | 2010-04-23 | 5311211.67 | 3.650
3106 | Obligated and Not Awarded | C240 | Highway Infrastructure Investment Grant | HAWAII | KAUAI |  | 02 | 0501036 | Kaumualii Highway, Route 50, from just west of the Lihue Mill Bridge to Rice Street will be widened from an undivided two-lane highway to a divided four-lane highway. Improvements include widening t | Pavement Widening |  |  |  |  | 22724978.84
3107 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | KAUAI |  | 02 | 0561052 | Reconstruct weakened pavement areas, cold plane, resurface, adjust utility boxes, & install guardrails, pavement markings, & traffic signs on Kuhio Hwy, Rte 56, between MP 9.0 and MP 10.0. | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2009-10-13 | 2009-11-05 | 774398.04 | 1.000
3108 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | KAUAI |  | 02 | 0583001 | Reconstruct weakened pavement areas, remove existing surface and repave, adjust utilities, and install guardrails, pavement markings, and traffic signs on Maalo Road, Route 583 | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2009-09-29 | 2009-11-12 | 608365.73 | 1.000
3109 | Underway | C220,C200 | Highway Infrastructure Investment Grant | HAWAII | KAUAI |  | 02 | 0700049 | Approximately 2 miles of 12-foot wide, 6-inch thick concrete bike/pedestrian path. Project starts at the south side of the Wailua River bridge on Kuhio Hwy to the intersection of Kuhio Hwy/Kuloloku R | Transportation Enhancements | 2011-11-01 |  | 2012-10-15 |  | 4120000
3110 | Underway | C240,C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 0831042 | Replace existing South Punaluu Stream Bridge with new concrete bridge. | Bridge Replacement | 2009-08-26 | 2009-08-26 | 2011-09-01 |  | 15298509.74 | 0.000
3111 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0900074 | Extend the life of the pavement and provide a smooth surface on Lower Main Street and Kanaloa Avenue by placing a surface seal. Project limits are; Lower Main Street - Waiehu Beach Road to Hala Place | Pavement Improvement | 2011-02-14 | 2011-02-14 | 2011-05-13 | 2011-06-03 | 542998.84
3112 | Underway | C240,C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 0951001 | Widen Kalaeloa Blvd. to six lanes from the O.R. and L. right-of-way to Lauwiliwili Street. Also signalize Lauwiliwili Street/Kalaeloa Blvd intersection. | Pavement Widening | 2010-11-05 | 2010-11-05 | 2012-02-01 |  | 5376455.41 | 0.130
3113 | Underway | C200,C240 | Highway Infrastructure Investment Grant | HAWAII | HAWAII |  | 02 | 1880001 | Construction of a new 1.6 mile, 2 lane, Ane Keohokalole Highway from Palani Road to Puohulihuli Street, reconstruction of 0.4 miles of the existing roadway from Puohulihuli Street to the West Hawaii C | New Construction | 2010-03-29 | 2010-03-29 | 2012-01-20 |  | 33815615.08
3114 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 3190001 | Remove the existing pavement surface on Ohukai Road between Hukulii Place and Hoalike Street and install new pavement. Utility covers will be adjusted and the road will be restriped. | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2010-05-21 | 2010-07-08 | 350000
3115 | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 3405002 | Reconstruction and beautification of Market Street from Kahawai Street to Makuhau Road. Install drainage system, street lights, landscaping and irrigation. | Pavement Improvement | 2009-11-27 | 2009-11-27 | 2010-12-01 | 2011-04-13 | 2421989.55 | 0.170
3116 | Underway | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 7139001 | Construct various improvements including drainage, parking, roadway and pedestrian/bike improvements. | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2011-09-28 |  | 3577527 | 0.520
3117 | Underway | C240,C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 8915002 | This project will consist of roadway improvements along Kamokila Boulevard and Kapolei Parkway. Construction will generally consist of removal and replacement of existing asphalt concrete pavement, r | Pavement Improvement | 2011-07-28 | 2011-07-28 | 2011-11-25 |  | 2380000
3118 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO |  | 01 | 4110137 | This project will add a climbing lane up the Whitebird Grade by widening 2.6 miles of US-95 in Idaho County. | Pavement Widening | 2009-03-03 | 2009-07-17 | 2015-09-30 | 2010-06-30 | 3934403 | 2.619
3119 | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO |  | 01 | 4110138 | This project includes the complete removal and replacement of pavement and base on 12 miles of US-95 north of Grangeville in Idaho County. | Pavement Improvement | 2009-09-15 | 2010-06-08 | 2015-09-30 |  | 3570710 | 9.059
3120 | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI |  | 01 | 5110137 | This project is to reconstruct the last 3.2 mile segment of US-95 in the City of Hayden in Kootenai County | Pavement Widening | 2009-06-02 | 2010-02-23 | 2015-09-30 |  | 9179072 | 4.460
3121 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK | POCATELLO | 02 | 7261100 | This project will repair or replace critical elements of the Custer Street Bridge in Bannock County. Improvements to the bridge deck and girders will extend the surface life of the structure and maint | Bridge Improvement | 2009-11-30 | 2010-04-26 | 2015-09-30 | 2010-09-24 | 370077 | 0.000
3122 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | GEM |  | 01 | 8001100 | This project will reconstruct and overlay 0.1 miles of Main Street and provide handicap accessible sidewalks in the City of Emmett, Gem County. | Pavement Improvement | 2009-09-22 | 2010-04-19 | 2015-09-30 | 2010-10-07 | 629100 | 0.129
3123 | Underway | C220,C250,C240 | Highway Infrastructure Investment Grant | IDAHO | BONNER |  | 01 | A001222 | This project will replace the Dover Bridge, an aging and deficient bridge, on US-95 in Bonner County. | New Bridge Construction | 2009-04-22 | 2009-07-01 | 2015-09-30 |  | 29104823 | 1.660
3124 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A002352 | This project will widen and pave 4 miles of State Highway 11 in Clearwater County between the cities of Wieppe and Pierce. | Pavement Improvement | 2010-02-28 | 2010-06-18 | 2015-09-30 | 2010-11-04 | 4178863 | 4.114
3125 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK |  | 02 | A007806 | This project will upgrade 31 miles of Southbound I-15 in Bannock County by laying an asphalt overlay, seal coat, and fog coat over the existing pavement. The project will also include deck repair at f | Pavement Improvement | 2009-11-30 | 2010-04-19 | 2015-09-30 | 2010-09-28 | 3705784 | 5.000
3126 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK |  | 02 | A007840 | This project will upgrade 31 miles of Northbound I-15 in Bannock County by laying an asphalt overlay, seal coat, and fog coat over the existing pavement. The project will also include deck repair at f | Pavement Improvement | 2009-09-15 | 2010-04-19 | 2015-09-30 | 2010-09-28 | 3957760 | 5.000
3127 | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | FREMONT |  | 02 | A008624 | This project will add passing lanes in a mountainous area near Henry's Lake by widening 6.4 miles of US-20. | Pavement Widening | 2009-04-22 | 2009-07-31 | 2015-09-30 | 2010-08-26 | 2618165 | 6.370
3128 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CANYON, PAYETTE |  | 01 | A008955 | This project will repair the concrete pavement to provide a smooth driving surface on 5 miles of I-84 in Payette and Canyon Counties The project also includes repair and replacement of deficient guar | Pavement Improvement | 2009-09-15 | 2010-05-10 | 2015-09-30 | 2010-10-18 | 8115162 | 5.030
3129 | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | JEFFERSON |  | 02 | A009387 | This project will reconstruct 1.7 miles of SH-48 in Rigby including new curb & gutter and handicap accessible sidewalks to the high school. | Pavement Widening | 2009-04-22 | 2009-08-10 | 2015-09-30 | 2010-08-26 | 4166084 | 1.710
3130 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO, LEWIS |  | 01 | A009795 | This project will repair the bridge deck and seal the driving surface on the bridge crossing Lawyers Creek on US-95 on the county line between Idaho and Lewis County. | Bridge Improvement | 2009-09-15 | 2010-06-07 | 2015-09-30 | 2010-08-02 | 125861.67 | 0.173
3131 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A009796 | This project will repair the bridge deck and preserve the driving surface with skid resistance aggregate and epoxy on State Highway 7 in the City of Orofino in Clearwater County. | Bridge Improvement | 2009-11-30 | 2010-06-07 | 2015-09-30 | 2010-08-02 | 233707.7 | 0.049
3132 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A009797 | This project will repair the bridge deck and seal the driving surface on the bridge crossing the North Fork Clearwater River on State Highway 7 in Clearwater County. | Bridge Improvement | 2009-11-30 | 2010-06-07 | 2015-09-30 | 2010-08-02 | 42310.3 | 0.000
3133 | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA |  | 01 | A010489 | This project consists of constructing continuous sidewalk, to be in complliance with the Americans with Disabilities Act, on the east and west sides of a 0.3 mile section of West 8th Street in the Cit | Transportation Enhancements | 2009-05-28 | 2010-06-22 | 2015-09-30 | 2010-08-06 | 162294 | 0.454
3134 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 01 | A010537 | This project takes place at 7 locations throughout Ada County and will overlay a total of 11 miles of existing roadways including handicap accessible sidewalk ramps. | Pavement Improvement | 2009-11-30 | 2010-06-15 | 2015-09-30 | 2010-11-17 | 2502684 | 12.510
3135 | Underway | C200 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK | POCATELLO | 02 | A010584 | This project will add one additional lane by widening 1.2 miles of congested urban interstate from the Chubbuck Interchange on I-86 to the Pocatello Creek Interchange on I-15 in Bannock County. | Pavement Improvement | 2009-04-22 | 2009-09-29 | 2015-09-30 |  | 10138499 | 1.200
3136 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | TWIN FALLS |  | 02 | A010917 | This project will eliminate traffic congestion in Twin Falls by constructing a new 5.1 mile long, 4-lane US-93 bypass, around the west side of the city. | New Construction | 2009-04-22 | 2009-09-05 | 2015-09-30 | 2010-12-22 | 21280930 | 5.070
3137 | Completed | C250,C220 | Highway Infrastructure Investment Grant | IDAHO | LATAH |  | 01 | A011031 | This project will add passing lanes in the Moscow Mountain area by widening 1.3 miles of US 95 in Latah County. | Pavement Widening | 2009-04-22 | 2009-07-07 | 2015-09-30 | 2010-06-16 | 3372943 | 1.338
3138 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | BINGHAM |  | 02 | A011097 | This project will mill and overlay Bergener, Bridge and Judicial Streets from the Snake river Bridge to Main Street in the City of Blackfoot | Pavement Improvement | 2010-02-17 | 2010-08-02 | 2015-09-30 | 2010-08-19 | 1036492 | 2.286
3139 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | LATAH |  | 01 | A011558 | This project will add a thin lift overlay on 6.2 miles of State Highway 9 in Latah County. | Pavement Improvement | 2009-09-15 | 2010-05-03 | 2015-09-30 | 2010-07-15 | 1618404 | 6.222
3140 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | CANYON |  | 01 | A011584 | This project is to realign and reconstruct the west leg of the intersection of Franklin and 21st Avenue in the City of Caldwell in Canyon County. The project includes curb, gutter and handicap accecs | Pavement Widening | 2009-11-30 | 2010-01-13 | 2015-09-30 | 2010-07-15 | 1198513 | 0.132
3141 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BONNEVILLE, JEFFERSON |  | 02 | A011673 | This project will improve user operating conditions on an 8.5 mile segment of I-15 in Bonneville County by leveling the pavement, adding a plantmix overlay, and finishing with a seal coat and fog coat | Pavement Improvement | 2009-09-15 | 2010-04-26 | 2015-09-30 | 2010-08-25 | 1463958 | 8.475
3142 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI | COEUR D ALENE | 01 | A011867 | This project will widen and completely reconstruct 0.5 miles of Hanley Avenue between Government Way and a new roundabout on 4th Street in the City of Dalton Gardens in Kootenai County. | Pavement Improvement | 2009-11-30 | 2010-06-21 | 2015-09-30 | 2010-08-19 | 499706 | 0.490
3143 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | NEZ PERCE | LEWISTON | 01 | A011917 | This project will seal coat the existing pavement and provide a skid resistant surface on 14 miles of local streets throughout the City of Lewiston. | Pavement Improvement | 2009-11-30 | 2010-06-15 | 2015-09-30 | 2010-08-24 | 691964 | 0.000
3144 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK | POCATELLO | 02 | A011918 | This project will remove and replace existing bridge joints on Gould Street Bridge in the City of Pocatello and improve pavement markings along the roadway. | Bridge Improvement | 2009-11-30 | 2010-04-20 | 2015-09-30 | 2010-09-07 | 401665 | 0.229
3145 | Underway | C200 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A011919 | This project funded the purchase of one van for public transportation in Pocatello. | Other | 2009-11-30 |  | 2015-09-30 |  | 24000 | 0.000
3146 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BONNEVILLE | IDAHO FALLS | 02 | A011920 | This project will seal coat the existing pavement and provide a skid resistant surface on 5.6 miles of local streets throughout Idaho Falls. | Pavement Improvement | 2009-05-28 | 2010-07-19 | 2015-09-30 | 2010-08-05 | 721474 | 5.598
3147 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA |  | Multiple | A011922 | This project takes place at 16 locations throughout Ada County and will overlay a total of 20 miles of existing roadways to improve operating conditions, preserve structural capacity, and extend the u | Pavement Improvement | 2009-11-30 | 2010-05-07 | 2015-09-30 | 2010-08-04 | 3117819 | 20.380
3148 | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA |  | Multiple | A011924 | This project will improve the network for pedestrians throughout Ada County by improving existing sidewalks, pedestrian ramps, and curb & gutter sections at up to 122 intersections within the cities o | Transportation Enhancements | 2009-11-30 | 2010-08-16 | 2015-09-30 | 2010-11-11 | 384109 | 0.000
3149 | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 02 | A011925 | This project will construct a pedestrian bridge across the Boise River east of Veterans Memorial Parkway. | Transportation Enhancements | 2009-11-30 | 2010-08-23 | 2015-09-30 | 2010-11-19 | 581560 | 0.000
3150 | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 02 | A011926 | This project will improve the network for pedestrians within Downtown Boise by improving existing sidewalks, pedestrian ramps, and curb and gutter sections at up to 49 intersections so they are in con | Transportation Enhancements | 2009-11-30 | 2010-06-01 | 2015-09-30 | 2010-08-10 | 490288 | 0.000
3151 | Underway | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 01 | A011932 | This project will provde aesthetically pleasing landscaping to the newly constructed Ten Mile Interchange on I-84 in Canyon County. | Transportation Enhancements | 2009-06-16 | 2010-06-17 | 2015-09-30 |  | 862962 | 1.000
3152 | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | BOUNDARY |  | 01 | A011935 | This project will overlay 3 miles of Deep Creek Loop, a two lane roadway, in Boundary County to provide a safer traveling surface and prolong the life of the asphalt. | Pavement Improvement | 2009-05-11 | 2010-08-30 | 2015-09-30 |  | 542919 | 10.557
3153 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | SHOSHONE |  | 01 | A011936 | This project will overlay the existing pavement to improve roadway surface smoothness and will provide stormwater drainage pathways on 0.8 mile of Nine Mile Road in Shoshone County. | Pavement Improvement | 2009-05-11 | 2010-07-28 | 2015-09-30 | 2010-09-01 | 373054 | 2.273
3154 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BENEWAH |  | 01 | A011937 | This project will pave the existing gravel roadway on 1.3 miles of the Benewah Creek Road corridor in Benewah County. | Pavement Improvement | 2009-05-11 | 2010-09-07 | 2015-09-30 | 2010-09-27 | 382669 | 1.640
3155 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | SHOSHONE |  | 01 | A011938 | This project will include repair of the existing pavement with a new pavement overlay on a 0.5 mile long segment in the City of Wallace in Shoshone County. | Pavement Improvement | 2009-05-11 | 2010-07-28 | 2015-09-30 | 2010-09-01 | 251176 | 0.912
3156 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A011939 | This project includes a pavement seal coat on 14 miles of Cavendish Road in Clearwater County. | Pavement Improvement | 2009-05-11 | 2010-07-27 | 2015-09-30 | 2010-09-30 | 487427 | 14.345
3157 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A011940 | This project will pave on top of existing gravel roadway on 0.8 miles of Musselshell Road in Clearwater County. | Pavement Improvement | 2009-05-11 | 2010-07-06 | 2015-09-30 | 2010-07-19 | 446395 | 1.500
3158 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A011941 | This project will increase the life of the pavement on 2.6 miles of roadway in the City of Orofino in Clearwater County by adding asphalt leveling and a seal coat to provide skid resistance. | Pavement Improvement | 2009-05-11 | 2010-08-24 | 2015-09-30 | 2010-10-01 | 252133 | 6.300
3159 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO |  | 01 | A011942 | This project will remove and replace the pavement and aggregate base on 0.7 mile of local road in the City of Cottonwood, Idaho County, to improve the driving surface and extend the life of the pavem | Pavement Improvement | 2009-05-11 | 2010-07-14 | 2015-09-30 | 2010-08-24 | 586583 | 0.722
3160 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | PAYETTE |  | 01 | A011943 | This project will improve traffic flow and pedestrian safety near local schools in the City of Fruitland in Payette County with a pavement overlay, installing handicap accessible sidewalks, and improv | Pavement Improvement | 2009-05-11 | 2010-06-07 | 2015-09-30 | 2010-07-19 | 453285 | 1.108
3161 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CANYON |  | 01 | A011944 | This project in Canyon County will repair the existing pavement and add a new asphalt overlay on a 1.5 mile segment of Notus Road from State Highway 19 to Red Top Road. | Pavement Improvement | 2009-05-11 | 2010-08-13 | 2015-09-30 | 2010-08-31 | 508472 | 2.000
3162 | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | GEM |  | 01 | A011945 | This project consists of an asphalt overlay on a 4 mile segment of the Ola Highway in Gem County to increase pavement longevity, improve the ride quality, and provide a safer road surface for the trav | Pavement Improvement | 2009-05-11 | 2010-07-26 | 2015-09-30 | 2010-08-08 | 528199 | 7.000
3163 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | ADAMS |  | 01 | A011946 | This project will overlay 1.6 miles and sealcoat 1.2 miles of Indian Valley Road in Adams County to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 2009-05-11 | 2010-06-14 | 2015-09-30 | 2010-07-10 | 496036 | 7.070
3164 | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | LINCOLN |  | 02 | A011947 | This project will overlay 1.7 miles and sealcoat 2.9 miles of 600 West Road in Lincoln County to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 2009-05-11 | 2010-08-09 | 2015-09-30 | 2010-09-17 | 536196 | 4.561
3165 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CASSIA |  | 02 | A011948 | This project will remove and recycle the existing pavement and gravel base on 1.2 miles of Old Highway 81 South Road in Cassia County to provide a safe and durable driving surface. | Pavement Improvement | 2009-05-11 | 2010-08-01 | 2015-09-30 | 2010-08-12 | 516695 | 3.468
3166 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | TWIN FALLS |  | 02 | A011949 | This project will improve 0.2 mile of Center Street in the City of Kimberly, Twin Falls County, by removing the deteriorated roadway, constructing a new base, and laying new pavement. | Pavement Improvement | 2009-05-11 | 2010-04-26 | 2015-09-30 | 2010-06-24 | 437354 | 0.370
3167 | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | CAMAS |  | 02 | A011950 | This project in the City of Fairfield, Camas County, will repair areas of distressed pavement, install an overlay, and perform minor storm drainage improvements at intersections along 0.6 mile of Sold | Pavement Improvement | 2009-05-11 | 2010-05-17 | 2015-09-30 |  | 500650 | 0.610
3168 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK | POCATELLO | 02 | A011951 | This project will remove and recycle the existing pavement and gravel base on a 1.2 mile segment of Mink Creek Road in Bannock County and will include both minor widening and an overlay. | Pavement Improvement | 2009-05-11 | 2010-09-13 | 2015-09-30 | 2010-09-28 | 505800 | 1.933
3169 | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | CARIBOU |  | 02 | A011952 | This project will improve the roadway and increase safety by adding new pedestrian crossing lights, replacing drainage structures, and adding a pavement overlay on 0.4 mile of local road in the City o | Pavement Improvement | 2009-05-11 | 2010-06-07 | 2015-09-30 | 2010-08-26 | 328820 | 0.426
3170 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | POWER |  | 02 | A011953 | This project will remove and recycle the existing pavement and gravel base on a 1 mile section of South Pleasant Valley Road in Power County. | Pavement Improvement | 2009-05-11 | 2010-07-16 | 2015-09-30 | 2010-07-29 | 508545 | 2.029
3171 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK |  | 02 | A011954 | This project will repair and overlay 0.4 mile of local roadway pavement and provide a new pedestrian crossing with crossing lights to improve user operating conditions on East Main Street in the City | Pavement Improvement | 2009-05-11 | 2010-08-09 | 2015-09-30 | 2010-08-26 | 274777 | 0.419
3172 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | FREMONT |  | 02 | A011955 | This project will seal coat the existing pavement and provide a skid resistant surface on a 4.5 mile segment of the Teton Highway in Fremont County. | Pavement Improvement | 2009-05-11 | 2010-07-01 | 2015-09-30 | 2010-07-12 | 249843 | 4.543
3173 | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | CUSTER |  | 02 | A011956 | This project in Custor County will repair a 3.1 mile segment of Trail Creek Road and extend the pavement life by adding a thin overlay to the pavement. | Pavement Improvement | 2009-05-11 | 2010-06-02 | 2015-09-30 | 2010-07-07 | 614906 | 2.000
3174 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | FREMONT |  | 02 | A011957 | This project will repair and overlay 0.5 mile of pavement on Main Street in City of St.Anthony, Fremont County and will include minor drainage improvements, replacement of traffic signal detection loo | Pavement Improvement | 2009-05-11 | 2010-04-28 | 2015-09-30 | 2010-06-28 | 621140 | 1.410
3175 | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | CLARK |  | 02 | A011958 | This project will replace the asphalt gutter with a concrete gutter and will overlay the roadway to improve user operating conditions on a 0.5 mile segment of Main Street in the City of Dubois, Clark | Pavement Improvement | 2009-05-11 | 2010-09-13 | 2015-09-30 |  | 408706 | 0.865
3176 | Underway | C220 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A011960 | This project will provide for curation and management of artifacts including consolidation of the Hatwaii archaeological collection. This project will develop public outreach on archaeological displa | Transportation Enhancements | 2009-06-16 | 2009-09-22 | 2015-09-30 |  | 167929 | 0.000
3177 | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | BOISE |  | 01 | A011961 | This project is to construct a wildlife/game crossing under US-21 in Boise County. | New Bridge Construction | 2009-06-16 | 2010-07-15 | 2015-09-30 | 2010-09-22 | 1122135 | 0.000
3178 | Underway | C220 | Highway Infrastructure Investment Grant | IDAHO | FREMONT |  | 02 | A011963 | This project is a study to determine a solution to numerous wildlife/vehicle collisions on US-20 in Fremont County. | Other | 2009-10-28 |  | 2015-09-30 |  | 624680 | 20.000
3179 | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A011964 | This project will construct 940 handicap ramps in Districts 1, 2, & 3 in accordance with the requirements of the Americans with Disabilities Act. It will be split into five separate projects for cons | Other | 2009-06-16 |  | 2015-09-30 | 2011-02-17 | 196209.99 | 0.000
3180 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI |  | 01 | A011976 | This project is to repair 10 structures on Interstate 90 between Post Falls and the Washington State border in Kootenai County. These structures will have the top of the deck removed and replaced with | Bridge Improvement | 2009-11-30 | 2010-04-26 | 2015-09-30 | 2010-06-22 | 3765219 | 4.600
3181 | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI |  | 01 | A011979 | This project will construct 89 handicap ramps in the Coeur D'Alene area of District 1, in Benewah, Kootenai and Shoshone Counties, in accordance with the requirements of the Americans with Disabilitie | Transportation Enhancements | 2009-11-30 | 2010-05-10 | 2015-09-30 | 2010-09-07 | 622601.77 | 0.000
3182 | Underway | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | BONNER |  | 01 | A011980 | This project will construct 90 handicap ramps in the Sandpoint area of District 1, in Bonner County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-07-06 | 2015-09-30 |  | 796283.78 | 0.000
3183 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | LATAH |  | 01 | A011981 | This project will construct 132 handicap ramps in the northern area of District 2, in Latah County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-05-03 | 2015-09-30 | 2010-09-22 | 908073 | 0.000
3184 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO |  | 01 | A011982 | This project will construct 80 handicap ramps in the southern area of District 2, in Idaho County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-04-26 | 2015-09-30 | 2010-08-02 | 464527 | 0.000
3185 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CANYON, GEM, PAYETTE, ADA |  | 01 | A011983 | This project will construct 127 handicap ramps in District 3, in Canyon, Gem, & Payette Counties, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-03-29 | 2015-09-30 | 2010-08-10 | 345348 | 0.000
3186 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI, SHOSHONE |  | 01 | A011986 | This project is to repair 9 structures on Interstate 90 between Post Falls and the Montana State border in Kootenai & Shoshone Counties. These structures will have the top of the deck removed and repl | Bridge Improvement | 2010-02-03 | 2010-06-11 | 2015-09-30 | 2010-08-27 | 3990339 | 30.783
3187 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BLAINE |  | 02 | A012074 | This project will patch and repair the concrete driving surface of the Big Wood River Bridge in Blaine County south of the City of Ketchum. | Bridge Improvement | 2010-05-24 | 2010-09-20 | 2015-09-30 | 2010-09-27 | 104510 | 0.000
3188 | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A012206 | This project will construct handicap ramps in Districts 5 and 6 in accordance with the requirements of the Americans with Disabilities Act. It will be split into two separate projects for constructi | Other | 2010-02-03 |  | 2015-09-30 |  | 118127.36 | 0.000
3189 | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | Multiple | A012207 | This project will construct 248 handicap ramps in Ada County in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2010-02-28 | 2010-08-30 | 2015-09-30 |  | 740250 | 0.000
3190 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | Multiple | A012208 | This project takes place at 9 locations throughout Ada County and will overlay a total of 7 miles of existing roadways to improve operating conditions, preserve structural capacity, and extend the use | Other | 2010-02-28 | 2010-08-30 | 2015-09-30 | 2010-10-18 | 1298271 | 7.190
3191 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | Multiple | A012209 | This project will improve the network for pedestrians and people with disabilities in Downtown Boise by improving existing sidewalks and 55 pedestrian ramps at up to 14 intersections so they are in co | Transportation Enhancements | 2010-02-03 | 2010-08-09 | 2015-09-30 | 2010-08-31 | 187400 | 0.000
3192 | Underway | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A012217 | This project will construct 122 handicap ramps in the Cities of Aberdeen, Blackfoot, and Grace of District 5 in accordance with the requirements of the Americans with Disabilities Act in Bingham and C | Transportation Enhancements | 2010-05-24 |  | 2015-09-30 |  | 1173708 | 0.000
3193 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A012218 | This project will construct 68 handicap ramps in the Cities of Rigby and Salmon of District 6 in accordance with the requirements of the Americans with Disabilities Act in Lemhi and Jefferson County. | Transportation Enhancements | 2010-05-24 | 2010-09-13 | 2015-09-30 | 2010-11-17 | 744535 | 0.000
3194 | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BONNEVILLE | IDAHO FALLS | 02 | A012227 | This project will seal coat the existing pavement and provide a skid resistant surface on 4.9 miles of local streets throughout Idaho Falls. | Pavement Improvement | 2010-02-03 | 2010-07-22 | 2015-09-30 | 2010-08-05 | 535404 | 4.732
3195 | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | JEROME |  | 02 | A012228 | This project will remove and recycle the existing pavement and gravel base on 1.5 miles of North Road in Jerome County to provide a safe and durable driving surface. | Pavement Improvement | 2010-05-24 |  | 2015-09-30 |  | 661081 | 1.560
3196 | Underway | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI |  | 01 | A012232 | This project will remove and replace the pavement and aggregate base on 5.2 miles of local road near the City of Coeur d'Alene, Kootenai County, to improve the driving surface and extend the life of t | Pavement Improvement | 2010-09-02 | 2011-05-23 | 2015-09-30 |  | 1572524 | 4.358
3197 | Completed | C200 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 01 | A012250 | This project will remove and replace 14 traffic signal controllers between Cole Road and Cloverdale Road on both sides of Ustick Road within Ada County to improve traffic flow and air quality. | Safety/Traffic Management | 2010-09-02 | 2011-08-15 | 2015-09-30 | 2011-09-23 | 225504 | 2.500
3198 | Underway | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | Multiple | A012254 | This project will coordinate 53 traffic signals on six major arterials within Ada County to improve traffic flow and air quality. | Safety/Traffic Management | 2010-06-29 |  | 2015-09-30 |  | 250000 | 30.000
3199 | Completed | C200 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 01 | A012255 | This project will remove and replace 15 traffic signal controllers between Overland Road and Chinden Blvd. on Curtis Road within Ada County to improve traffic flow and air quality. | Safety/Traffic Management | 2010-09-02 | 2011-08-15 | 2015-09-30 | 2011-09-23 | 240789 | 7.000
3200 | Underway | C490 | OJT/SS | IDAHO | CANYON, ADA |  | Multiple | A012260 | This project provides funding for a statewide training program for returning disabled veterans. Vetrans will be trained to drive trucks and obtain a CDL license or become a certified flagger with mar | Other | 2010-01-08 |  | 2015-09-30 |  | 99330 | 0.000
3201 | Completed | C490 | OJT/SS | IDAHO | STATEWIDE |  |  | A012262 | This project provides funding for construction safety training for minority, women, Native American and other disadvantaged individuals working on transportation related construction projects in Idaho | Other | 2010-03-15 |  | 2015-09-30 | 2011-06-03 | 55448 | 0.000
3202 | Completed | C240,C230 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 02 | C009818 | This project, in the City of Boise, the existing I-84 Vista Interchange will be reconstructed into a Single Point Urban Interchange. | Pavement Widening | 2009-04-22 | 2009-07-07 | 2015-09-30 | 2010-09-28 | 22543050 | 1.200
3203 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 17 | 000S617 | This project will extend the pavement life by resurfacing a section of US 30 near the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2009-08-30 | 2009-09-11 | 782424.21 | 2.330
3204 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 000S618 | This project will extend the pavement life by resurfacing a section of US 20 Business Route in the city of Freeport (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-10-30 | 2009-07-16 | 389189.69 | 1.350
3205 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 000S619 | This project will extend the pavement life by resurfacing 12 miles of US 6 between the cities of Geneseo and Atkinson (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-10-30 | 2009-09-11 | 2720252.95 | 29.280
3206 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 000S620 | This project will extend the pavement life by resurfacing sections of US 20 and IL 26 near the city of Freeport (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-09-30 | 2009-11-13 | 1837174.95 | 6.420
3207 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 000S628 | This project will extend the pavement life by resurfacing a section of IL 2 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-26 | 2009-10-30 | 2010-04-20 | 1095782.71 | 17.930
3208 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S630 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 7 (Southeast Illinois). | Safety/Traffic Management | 2009-04-28 | 2009-06-22 | 2009-12-30 | 2009-09-15 | 745277.15 | 0.000
3209 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S631 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 1 (Northeast Illinois). | Safety/Traffic Management | 2009-04-23 | 2009-05-12 | 2010-07-30 | 2010-07-31 | 907824.38 | 0.000
3210 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S633 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 3 (East-Central Illinois). | Safety/Traffic Management | 2009-07-30 | 2009-08-10 | 2010-07-30 | 2010-07-30 | 574011.55 | 0.000
3211 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S634 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout District 4 (West-Central Illinois) | Safety/Traffic Management | 2009-05-06 | 2009-05-16 | 2010-07-30 | 2010-06-19 | 432884 | 0.000
3212 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S637 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 7 (Southeast Illinois). | Safety/Traffic Management | 2009-05-06 | 2009-07-28 | 2010-07-30 | 2009-08-30 | 343186.98 | 0.000
3213 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S639 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 9 (Southern Illinois). | Safety/Traffic Management | 2009-05-06 | 2009-08-31 | 2010-07-30 | 2009-11-02 | 477059.89 | 0.000
3214 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S640 | This project consists of improving safety by upgrading guardrail terminals to current standard throughout IDOT District 1 (Northeast Illinois). | Safety/Traffic Management | 2009-04-30 | 2009-06-23 | 2009-11-30 | 2009-11-16 | 817169.16 | 0.000
3215 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S644 | This project consists of improving safety by upgrading guardrail terminals to current standard throughout District 4 (West-Central Illinois) | Safety/Traffic Management | 2009-04-28 | 2009-05-08 | 2009-12-30 | 2009-11-03 | 721808.89 | 0.000
3216 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S645 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 9 (Southern Illinois). | Safety/Traffic Management | 2009-04-28 | 2009-05-21 | 2009-12-30 | 2010-01-13 | 683695.91 | 0.000
3217 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MONTGOMERY |  | 19 | 000S646 | This project will extend the pavement life by resurfacing various streets in Nokomis, Il in Montgomery County (West-Central Illinois). | Pavement Improvement | 2009-04-30 | 2010-05-03 | 2010-07-30 | 2011-10-21 | 924307.95 | 3.270
3218 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 000S647 | This project will extend the pavement life by resurfacing DesPlaines Avenue from 26th to 31st Street in the Village of Riverside in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-18 | 2009-08-30 | 2009-06-29 | 345016.9 | 0.510
3219 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S648 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 3 (East-Central Illinois). | Safety/Traffic Management | 2009-07-30 | 2009-08-24 | 2009-12-30 | 2009-12-04 | 1031644.46 | 0.000
3220 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S649 | This project will extend the pavement life by resurfacing numerous roadway sections in Southern Cook County (Northeastern Illinois) | Pavement Improvement | 2009-06-01 | 2009-06-23 | 2009-09-30 | 2009-07-31 | 911289.06 | 0.000
3221 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S650 | This project will extend the pavement life by resurfacing numerous roadway sections in Central Cook County (Northeastern Illinois) | Pavement Improvement | 2009-06-01 | 2009-06-29 | 2009-11-30 | 2009-11-13 | 1577940.6 | 0.000
3222 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S651 | This project will extend the pavement life by resurfacing numerous roadway sections in Northern Cook County (Northeastern Illinois) | Pavement Improvement | 2009-06-01 | 2009-06-05 | 2009-10-30 | 2009-12-03 | 1022357.4 | 0.000
3223 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 000S652 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Kane County (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-22 | 2009-09-30 | 2009-08-13 | 453708.18 | 0.000
3224 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 000S653 | This project will extend the pavement life by resurfacing numerous roadway sections in Will County (Northeastern Illinois). | Pavement Improvement | 2009-06-02 | 2009-06-15 | 2009-10-30 | 2009-10-12 | 1397082.45 | 0.000
3225 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S654 | This project will extend the pavement life by resurfacing numerous roadway sections in DuPage County (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-11-30 | 2009-09-30 | 2302963.54 | 0.000
3226 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S655 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout McHenry County (Northeastern Illinois). | Pavement Improvement | 2009-06-02 | 2009-06-09 | 2009-09-30 | 2009-07-24 | 623454.17 | 0.000
3227 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S656 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Lake County (Northeastern Illinois). | Pavement Improvement | 2009-06-02 | 2009-06-12 | 2009-11-30 | 2009-09-29 | 2512642.94 | 0.000
3228 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S657 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Lake County (Northeastern Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-12 | 2009-11-30 | 2009-12-08 | 2010293.64 | 0.000
3229 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 000S658 | This project will substantially improve the roadway, traffic congestion and safety by constructing a new interchange to replace the old interchange in Troy, Illinois (Southwest Illinois) | Pavement Improvement | 2009-08-05 | 2009-08-17 | 2012-07-30 |  | 24594122.19 | 0.010
3230 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 000S659 | This project will improve safety and operations by removal of old ramp structures and extention of existing ramps and other roadway improvements on I-94/90 from Hubbard's Cave to I-290 in the City of | Pavement Improvement | 2009-05-20 | 2009-06-15 | 2009-11-30 |  | 13054148.61 | 1.180
3231 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 000S660 | This project will extend the pavement life by milling, patching and resurfacing 2 miles of Dempster Street from US 41 to McCormick Blvd in Skokie and Chicago Avenue to Judson Avenue in Evanston in Coo | Pavement Improvement | 2009-06-01 | 2009-06-14 | 2009-11-30 | 2010-12-02 | 1564125.3 | 2.070
3232 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S662 | This project will extend the pavement life by resurfacing 3.04 miles of Touhy Ave from Northwest highway to Central Avenue in the Village of Niles and Cities of Chicago and Park Ridge in Cook County, | Pavement Improvement | 2009-06-01 | 2009-06-12 | 2009-09-30 | 2009-10-03 | 2182315.95 | 3.180
3233 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 000S680 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on CH 23 over Jack Creek at Toulon which is approximately 30 miles northwest of the City of | Pavement Improvement | 2009-07-30 | 2009-08-10 | 2009-11-30 | 2009-10-27 | 1873371.58 | 10.570
3234 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENDERSON |  | 17 | 000S681 | This project will extend the pavement life by providing for surface improvements at 2 locations on US Route 34 near the City of Gulfport and the Mississippi River (West-Central Illinois) | Pavement Improvement | 2009-08-11 | 2009-08-13 | 2009-09-30 | 2009-10-06 | 611731.05 | 4.380
3235 | Completed | C250,C220 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 000S685 | This project will extend the pavement life by resurfacing 3.0 miles on US Route 6 in Channahon and Rockdale (Northeast Illinois). | Pavement Improvement | 2009-10-29 | 2010-04-30 | 2010-08-30 | 2010-10-01 | 1807031.55 | 3.940
3236 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MARSHALL |  | 18 | 000S802 | This project will extend the pavement life by resurfacing and adding safety improvements to 15 miles of Illinois Routes 89 and 17 in Marshall and Putnam Counties (West-Central Illinois). | Pavement Improvement | 2010-04-21 | 2010-04-22 | 2010-10-30 | 2010-08-16 | 700000 | 14.940
3237 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 000S829 | Rem & Rep structure carrying IL 251 over Spring Creek Rd & Rem/ repl bridge deck on structure carrying Forest Hills Rd over IL 251 in Rockford. Section 1-HBR & 1-2 HB-D | Pavement Improvement | 2010-12-10 | 2011-03-21 | 2011-10-30 |  | 497380.31 | 0.010
3238 | Completed | C490 | OJT/SS | ILLINOIS | STATEWIDE |  |  | 0011106 | To provide training in highway construction industry trade and life skills, financial assistance (stipends) for transportation/child care, and construction tools/clothing/safety equipment, as identifi | Other | 2010-05-01 | 2010-05-03 | 2011-06-30 | 2011-06-30 | 1189635 | 0.000
3239 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 0022070 | This project will extend the pavement life by providing for 7.21 miles pavement repairs and resurfacing on Illinois Route 78 approximately 20 miles west of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-09-30 | 2009-07-27 | 2133300.98 | 7.540
3240 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA |  | 18 | 0022071 | This project will extend the pavement life by providing for 3.06 miles of pavement repairs and resurfacing on Ilinois Route 78 west of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-08 | 2009-08-30 | 2009-06-13 | 1022359.09 | 3.060
3241 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 0022072 | This project will extend the pavement life by providing for 9.2 miles of pavement repairs and resurfacing on Illinois Route 78 aproximately 20 miles west of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-01 | 2009-09-30 | 2009-07-29 | 1661932.91 | 9.190
3242 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STARK |  | 18 | 0022075 | This project will extend the pavement life by resurfacing 9.7 miles of Illinois Route 78 approximately 20 miles northwest of Peoria (West-Central Illinois) | Pavement Improvement | 2009-07-30 | 2009-08-03 | 2009-12-30 | 2009-10-15 | 2461526.75 | 19.360
3243 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CLINTON |  | 19 | 0027038 | This project will substantially improve the roadway by constructing a new bridge over Lost Creek on Sand Ridge Road near Ferrin, Illinois (Southwest Illinois) | Bridge Replacement | 2009-07-27 | 2009-09-14 | 2009-10-30 | 2009-11-12 | 50000 | 0.200
3244 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0031030 | This project will extend the bridge life by milling, resurfacing and repairing the bridge deck and making other roadway improvements on Winnetka Rd. over the North branch of the Chicago River in Cook | Bridge Improvement | 2010-03-16 | 2010-04-02 | 2010-10-30 |  | 242214 | 0.030
3245 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | BOONE |  | 16 | 0032106 | This project will extend the pavement life by resurfacing sections of Poplar Grove Road in Boone County (Northwest Illinois). | Pavement Improvement | 2009-09-15 | 2009-10-07 | 2009-10-30 | 2009-11-14 | 398954 | 10.780
3246 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE WITT |  | 15 | 0039027 | This project will enhance safety by upgrading signs to current standards throughout DeWitt County (East-Central Illinois). | Safety/Traffic Management | 2010-06-01 | 2010-06-01 | 2011-07-30 | 2010-12-15 | 76193.62 | 0.000
3247 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | DE WITT |  | 15 | 0039028 | Preliminary engineering for the prepaation of a sign inventory in DeWitt county, 09-00000-00-SG | Other | 2009-08-10 | 2009-08-10 | 2010-10-30 | 2009-12-31 | 32550 | 0.000
3248 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041093 | This project consists of providing engineering design for a future township bridge improvement over the Kaskaskia River (East-Central Illinois). | Other | 2009-09-30 | 2009-11-01 | 2010-12-30 | 2011-11-01 | 63525 | 0.010
3249 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041094 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE OVER SCATTERING FORK, SECTION 07-03122-01-EG | Other | 2009-09-30 | 2009-10-01 | 2010-07-30 | 2011-05-05 | 34770 | 0.020
3250 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041095 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE OVER THE KASKASKIA RIVER NEAR FLICKLIN, SECTION 09-05123-01EG | Other | 2009-09-30 | 2009-11-01 | 2010-12-30 | 2011-11-07 | 107005 | 0.000
3251 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041096 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE CARRYING TR 218 OVER BRUSHY FORK, DOUGLAS COUNTY SECTION 07-08119-01-EG | Other | 2009-09-30 | 2009-10-05 | 2010-10-30 | 2011-01-06 | 52019 | 0.030
3252 | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041097 | This project will enhance safety by upgrading signs to current standards throughout Douglas County (East-Central Illinois). | Safety/Traffic Management | 2010-04-15 | 2010-04-15 | 2011-04-30 |  | 72420 | 0.000
3253 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 0041130 | This project will extend the pavement life by resurfacing 7.9 miles of IL 17 in western Kankakee County (East-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-26 | 2009-08-30 | 2009-08-07 | 1744277.41 | 8.100
3254 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | EDWARDS |  | 19 | 0047032 | This project will substantially improve the roadway by constructing a new bridge over Bear Creek on County Highway 4 near Samsville in Edwards County (Southeast Illinois). | Bridge Replacement | 2010-03-01 | 2010-04-30 | 2010-06-30 | 2010-06-30 | 133611.17 | 0.010
3255 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | EDWARDS |  | 19 | 0047033 | This project will substantially improve the roadway by constructing a new bridge over Butter Creek on Township Road 185 near Albion (Southeast Illinois) | Bridge Replacement | 2010-10-18 | 2010-10-25 | 2011-05-30 | 2010-11-29 | 31067 | 0.010
3256 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HAMILTON |  | 19 | 0065051 | This project will extend the pavement life by resurfacing numerous roadway sections in Whtie County. (Southern Illinois) | Pavement Improvement | 2010-02-22 | 2010-05-01 | 2010-05-30 | 2010-07-22 | 264944 | 0.010
3257 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | JO DAVIESS |  | 16 | 0065104 | This project will extend the pavement life by resurfacing 5.3 miles on Stagecoach Trail near the city of Warren (Northwest Illinois). | Pavement Improvement | 2009-10-27 | 2010-05-17 | 2010-12-30 | 2010-06-02 | 375743 | 9.340
3258 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 0067079 | This project will extend the pavement life by milling and resurfacing a portion of Jefferson Street in the City of Springfield (West-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-04-30 | 2009-09-30 | 2009-08-14 | 836639.67 | 2.880
3259 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CASS |  | 18 | 0067080 | This project will substantially improve the roadway by reconstructing two box culverts and repairing another one on Illinois Route 125 near Bluff Springs (West-Central Illinois) | Pavement Improvement | 2009-05-04 | 2009-05-05 | 2010-05-30 | 2010-06-08 | 2042797.98 | 2.700
3260 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | IROQUOIS |  | 15 | 0071115 | This project will extend pavement life by resurfacing 4.2 miles of IL 54 near the city of Thawville (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-07-20 | 2009-10-30 | 2009-08-12 | 880320.15 | 4.570
3261 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LOGAN |  | 18 | 0071116 | This project will extend the pavement life by resurfacing a portion of Illinois Route 54 northeast of Mt. Pulaski in Logan County (West-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-14 | 2009-09-30 | 2009-08-20 | 1442589.51 | 6.890
3262 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SCHUYLER |  | 18 | 0073104 | Pavement reconstruct with brick paver wearing surface sidewalk, lighting, streetscape and lighting improvements in Rushville. Section 05-00017-00-FP | Transportation Enhancements | 2011-01-06 | 2011-03-07 | 2012-05-30 |  | 563972 | 0.000
3263 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CARROLL |  | 16 | 0077103 | This project will extend the pavement life by resurfacing sections of County Highways 4 and 25 in Carroll County (Northwest Illinois). | Pavement Improvement | 2009-09-11 | 2009-09-24 | 2009-10-30 | 2009-10-23 | 309728 | 20.560
3264 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JEFFERSON |  | 19 | 0081059 | This project will extend the pavement life by resurfacing 1.32 miles of County Highway 42/43 in Jefferson County.(Southern Illinois) | Pavement Improvement | 2010-03-01 | 2010-05-03 | 2010-06-30 | 2010-05-19 | 413197 | 1.240
3265 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JERSEY |  | 17 | 0083047 | This project will improve safety by replacing an existing bridge over Otter Creek near Fieldon, Illinois (Southwest Illinois) | Bridge Replacement | 2010-03-01 | 2010-06-01 | 2010-07-30 | 2010-09-03 | 240596 | 0.010
3266 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | EDGAR |  | 15 | 0091071 | This project will extend the pavement life by resurfacing 4.5 miles of Illinois 16 approximately 25 miles southeast of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-08 | 2010-03-30 | 2010-08-30 | 2010-05-18 | 2227813.7 | 29.060
3267 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | Multiple | 0095126 | This project will substantially improve the roadway by constructing a new bridge over Finch Creek on County Highway 16 east of Galesburg (West-Central Illinois) | Bridge Replacement | 2009-08-03 | 2009-08-17 | 2009-11-30 | 2009-10-05 | 255000 | 0.020
3268 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 18 | 0095133 | This project will substantially improve the roadway by constructing a new bridge over Swab Run Creek in eastern Knox County, approximately 20 miles southeast of Galesburg (West-Central Illinois) | Bridge Replacement | 2009-12-17 | 2010-05-17 | 2010-06-30 | 2010-07-08 | 146886.21 | 0.010
3269 | Completed | C220,C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 00D1691 | This project will substantially improve mobility by constructing a new prefabricated pedestrian bridge over Buffalo Creek & construct a 0.14 mile shared use path between Dundee Road & Glendale Rd in t | Transportation Enhancements | 2009-09-15 | 2009-10-05 | 2010-05-30 | 2010-09-02 | 271795 | 0.000
3270 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 00D1701 | This project will provide for pedestrain safety by improving the sidewalk, pedestrain lighting and signage adjacent to Roosevelt Road in Westchester, (Northeastern Illinois) | Transportation Enhancements | 2009-09-10 | 2009-09-17 | 2010-05-30 | 2010-12-03 | 268960 | 0.700
3271 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 00D1710 | This project will provide for pedestrian safety by constructing a new Pedestrain path from Three Oaks Road through Cary Grove Park to District 26 Cary Jr High School (Northeast Illinois). | Transportation Enhancements | 2010-01-26 | 2010-04-01 | 2010-09-30 | 2010-12-11 | 623500 | 0.000
3272 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | ROUND LAKE BEACH | 02 | 00D1761 | This project will provide for pedestrian safety by streetscaping Lake Park Ave from 51st St. to 57th St. in the City of Chicago. (Northeastern Illinois) | Bridge Improvement | 2011-11-26 | 2011-06-11 | 2012-11-30 |  | 2050000 | 0.010
3273 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 00D1779 | This project will provide for pedestrian safety by removing an existing pedestrian path and constructing a new path with lighting and landscaping from Lee St. north for 1.08 miles in the Evanston Lake | Transportation Enhancements | 2010-05-24 | 2010-09-07 | 2011-12-30 | 2011-07-18 | 598867 | 0.000
3274 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 00D1795 | This project consists of a safety and traffic enhancement by installing 1.63 miles of new lighting and streetscape improvements on Miner Street, Oakton Street and Lee Street corridors in Des Plaines, | Transportation Enhancements | 2009-12-10 | 2010-03-16 | 2010-10-30 |  | 800000 | 0.000
3275 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 00D1808 | Install street lighting along FAP 348 (Harlem Ave. / IL 43) from 70th St to 93rd St in Bridgeview. Section 06-00054-00-LT | Transportation Enhancements | 2010-12-01 | 2011-03-12 | 2012-08-30 |  | 1580800 | 2.800
3276 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 00D1809 | This project will enhance the roadway by installing landscape improvements of select medians, embankments, planting of trees, shrubs, and flowers, on 4.1 miles of Harlem Avenue from 191st St. to 159th | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-08-30 |  | 851389 | 0.600
3277 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 00D1810 | This project will substantially improve the roadway by reconstructing a section IL 137 by providing new asphalt pavement and other roadway improvements in Winthrop Harbor. (Northeast Illinois) | Transportation Enhancements | 2010-01-26 | 2010-01-27 | 2011-06-30 |  | 1372162 | 0.130
3278 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 00D2131 | This project consists of a substantial transportation improvement by construction of a new concrete bicycle and pedestrian path and other associated improvements between the cities of Rock Island and | Transportation Enhancements | 2009-11-18 | 2010-05-10 | 2009-05-30 | 2010-10-22 | 446000 | 0.000
3279 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 00D2132 | Sidewalks, landscaping & lighting along River Drive from 25th to 34th in Moline (WIU Rivertech Streetscape) Section 06-00234-00-LS | Transportation Enhancements | 2010-10-20 | 2011-07-19 | 2011-05-30 | 2011-12-12 | 615381 | 0.000
3280 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 00D2133 | Pedestrian Riverwalk, sidewalks (2) Pedestrian structures, amphitheatre area, retaining walls, lighting and landscaping. Section 06-00543-00-BT | Transportation Enhancements | 2011-02-24 | 2011-04-11 | 2015-09-30 |  | 1261230 | 0.000
3281 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 00D2139 | This project will substantially improve pedestrian safety by constructing a new pedestrian bridge over the Pecatonic River in the city of Freeport and repair of a timber bridge in Stephenson County (N | Transportation Enhancements | 2009-12-22 | 2010-03-01 | 2011-10-30 |  | 1141394 | 0.000
3282 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 00D2140 | This project will improve pedestrian and bicycle safety by constructing a multi-use path, sidewalks and other related items at Howell Park in the city of Dixon (Northwest Illinois). | Transportation Enhancements | 2010-04-07 | 2010-04-07 | 2010-08-30 | 2011-10-05 | 341481 | 0.000
3283 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 00D3058 | This project will substantially improve pedestrian trafficabilty by constructing sidewalk and two bridges near Riverfront Park in the city of Marseilles (East-Central Illinois). | Transportation Enhancements | 2010-02-26 | 2010-07-06 | 2011-12-30 |  | 207303 | 0.000
3284 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 00D3059 | This project will improve safety by installing lighting and signing along IL 113 in the village of Diamond (East-Central Illinois). | Transportation Enhancements | 2010-04-23 | 2010-09-09 | 2011-12-30 |  | 301413 | 1.000
3285 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | STARK |  | 18 | 00D4102 | This project will enhance safety and aesthetics by reconstructing sidewalks and installing lighting at the instersection of Illinois Routes 17 and 91 in Stark County (West-Central Illinois). | Transportation Enhancements | 2010-05-04 | 2010-07-19 | 2010-09-30 | 2010-09-29 | 208400 | 0.230
3286 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 00D4103 | This project will enhance pedestrian safety by constructing sidewalks and replacing curb and gutter along 0.75 mile of Pfeiffer Road in Bartonville, Peoria County (West-Central Illinois). | Transportation Enhancements | 2010-05-18 | 2010-05-28 | 2010-08-30 | 2010-08-13 | 533925 | 0.750
3287 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 00D5090 | This project will provide for pedestrian and bicycle safety by constructing a 4-mile multi-use path on the southwest side of Bloomington (Central Illinois). | Transportation Enhancements | 2010-05-18 | 2010-05-20 | 2010-08-30 | 2010-09-17 | 1414447 | 0.000
3288 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 17 | 00D6089 | This project consists of substantial transportation improvement by constructing new pavement with concrete pavers, new sidewalks, decorative lighting, and planting beds on Capital Avenue between 5th | Transportation Enhancements | 2010-03-18 | 2010-03-18 | 2010-08-30 |  | 1796318 | 0.160
3289 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 00D6090 | This project will substantially improve the community by providing a new bicycle and pedestrian path in Sangamon County(West-Central Illinois) | Transportation Enhancements | 2010-06-29 | 2010-07-07 | 2012-07-30 | 2010-08-30 | 2513840 | 0.000
3290 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 17 | 00D7036 | This project will provide landscaping for the Farm Progress Grounds in Decatur (Southeast Illinois). | Transportation Enhancements | 2009-10-29 | 2010-04-12 | 2010-05-30 | 2010-06-13 | 74400 | 0.000
3291 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | CLINTON |  | 19 | 00D8124 | This project will provide pedestrian and bicycle accommodations along old US Route 50 from Memorial Drive to Madison Drive in the town of Breese, IL (Southwest Illinois) | Transportation Enhancements | 2010-12-22 | 2011-07-15 | 2010-07-30 |  | 172045 | 0.000
3292 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 00D8131 | This project will add new sidewalk, replace broken curb and gutter add lighting o the streets and adjust the stop lights to operate more efficiently on various streets throughout the city of East St. | Transportation Enhancements | 2009-12-10 | 2010-05-11 | 2010-10-30 | 2010-11-12 | 676786 | 0.000
3293 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | GALLATIN |  | 19 | 00D9084 | This project will enhance pedestrian and bicycle accommodations by constructing a bike trail accessing the Gallatin County Visitors Center in Gallatin County (Southern Illinois). | Transportation Enhancements | 2010-04-28 | 2010-04-28 | 2010-10-30 |  | 782960 | 0.000
3294 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 00D9094 | This project will enhance pedestrian and bicycle accommodations by constructing a bike trail connection between the cities of Eldorado and Harrisburg (Southern Illinois). | Transportation Enhancements | 2010-04-23 | 2010-04-23 | 2011-05-30 |  | 1256795 | 0.000
3295 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 00D9096 | LAND ACQUISITION FOR THE CONSTRUCTION OF A BIKE/PED TRAIL TO CONNECT ELDORADO TO HARRISBURG, SECTION 06-00082-00-BT | Transportation Enhancements | 2009-09-14 | 2011-03-02 | 2009-10-30 | 2011-03-02 | 22500 | 0.000
3296 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0109052 | This project will extend the structure life by providing new exterior paint on two county highway bridges in McDonough County (West-Central Illinois). | Bridge Improvement | 2010-04-06 | 2010-04-16 | 2010-06-30 | 2010-05-28 | 77947 | 0.020
3297 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 0113029 | This project will provide for pedestrian safety by constructing a 1.13 mile multi-use bike trail in Chenoa, approximately 25 miles north of Bloomington (East-Central Illinois) | Transportation Enhancements | 2009-08-04 | 2009-08-07 | 2009-10-30 | 2009-10-01 | 10685.46 | 0.000
3298 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MASON |  | 18 | 0125018 | This project consists of a safety and traffic enhancement by upgrading pavement markings on various routes throughout Mason County (West-Central Illinois). | Safety/Traffic Management | 2010-04-15 | 2010-06-01 | 2010-05-30 | 2010-07-29 | 80010 | 0.000
3299 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | POPE |  | 19 | 0132130 | This project will extend the pavement life by milling, patching and resurfacing 3.61 miles of IL145 in Pope county, Illinois (Southern Illinois). | Pavement Improvement | 2009-06-02 | 2009-07-01 | 2009-08-30 | 2009-08-31 | 985175.18 | 3.750
3300 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA |  | 18 | 0143050 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on County Highway 15 over Spoon River approximately 30 miles northwest of Peoria (West-Centr | Bridge Improvement | 2009-09-08 | 2009-09-28 | 2010-07-30 | 2010-10-05 | 379741 | 0.020
3301 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | PULASKI |  | 12 | 0153030 | This project will substantially improve the roadway by constructing a new bridge over Pulaski Slough on Morris Road in Pulaski County, Illinois (Southern Illinois Illinois) | Bridge Replacement | 2009-08-27 | 2009-09-21 | 2009-10-30 | 2009-11-16 | 157081 | 0.020
3302 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 0167058 | This project will extend the pavement life by resurfacing a portion of a Sangamon County road near Springfield (West-Central Illinois). | Pavement Improvement | 2009-10-14 | 2009-10-12 | 2010-03-30 | 2010-04-28 | 1636269.35 | 11.200
3303 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 0167059 | This project will substantially improve the roadway by constructing a new intersection and signals along with other roadway improvements at Village Center Drive and Business 55 in Sherman (West-Centra | Pavement Improvement | 2010-04-19 | 2010-06-01 | 2010-07-30 | 2010-12-03 | 280212 | 0.010
3304 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 0169103 | This project will extend the pavement life by resurfacing 3.6 miles of US 52 near the city of Troy Grove (East-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-27 | 2009-09-30 | 2009-08-10 | 682587.86 | 3.630
3305 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 0174118 | This project will substantially improve the roadway by constructing a new bridge over Big Indian Creek on County Highway 6 in Dekalb County (East-Central Illinois). | Bridge Replacement | 2009-07-30 | 2009-08-10 | 2009-12-30 | 2009-11-05 | 314054 | 10.020
3306 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | STARK |  | 18 | 0175023 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on CH 23 over Jack Creek at Toulon which is approximately 30 miles northwest of the City of | Bridge Replacement | 2009-09-15 | 2009-09-16 | 2009-10-30 | 2009-11-12 | 184642 | 0.010
3307 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 0179032 | This project will enhance safety by widening the pavement to accommodate left and right turn lanes into Tazewell County facilities on Illinois Route 9 approximately 10 miles south of Peoria (West-Cent | Pavement Improvement | 2009-12-14 | 2010-04-26 | 2010-07-30 | 2010-08-25 | 420000 | 0.010
3308 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 0179106 | This project will extend the pavement life by resurfacing 3 miles of South 1st Street in Dekalb County (East-Central Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-18 | 2010-05-30 | 2010-06-04 | 547560 | 3.310
3309 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | UNION |  | 12 | 0181048 | This project will substantially improve the roadway by replacing the existing bridge carrying Kratzinger Hollow Rd over Green Creek near Jonesboro, Illinois (Southern Illinois) | Bridge Replacement | 2010-03-10 | 2010-05-06 | 2010-06-30 | 2010-06-07 | 115000 | 0.010
3310 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 0185103 | This project will extend the pavement life by resurfacing sections of Ambot Road and Walton Road in Lee County (Northwest Illinois). | Pavement Improvement | 2009-12-09 | 2010-05-11 | 2010-07-30 | 2010-07-06 | 433493 | 6.350
3311 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WARREN |  | 17 | 0187038 | This project consists of a safety and traffic enhancement by upgrading roadway signs throughout Warren County (West-Central Illinois) | Safety/Traffic Management | 2009-12-14 | 2009-12-24 | 2010-11-30 | 2010-09-29 | 270457.3 | 0.000
3312 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0188120 | This project will extend pavement life by resurfacing 2 miles of County Highway 8 in Bureau County (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-09-30 | 2009-10-07 | 292800 | 4.000
3313 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | OGLE |  | 16 | 0189108 | This project will extend the pavement life by resurfacing sections of Freeport Road in Ogle County (Northwest Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-24 | 2009-09-30 | 2009-10-23 | 574019 | 21.470
3314 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO |  | 16 | 0201027 | This project consists of improving safety by upgrading guardrail to current standards throughout Winnebago County (Northwest Illinois). | Safety/Traffic Management | 2009-10-29 | 2009-11-09 | 2009-12-30 | 2010-01-07 | 220186.31 | 0.000
3315 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MERCER |  | 17 | 0206116 | This project will prepare for a drainage improvement project on County Highway 4 in Henry County (West-Central Illinois). | Other | 2009-10-27 | 2009-10-27 | 2010-03-30 | 2010-03-01 | 65786.28 | 1.310
3316 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MERCER |  | 17 | 0206117 | This project will extend the pavement life by resurfacing and replacing culverts along a section of County Highway 4 in Mercer County (West-Central Illinois). | Pavement Improvement | 2010-04-20 | 2010-04-30 | 2010-08-30 | 2010-07-23 | 286259 | 1.310
3317 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0209003 | This item provides construction engineering service for inspection and oversight for the improvement of I-94 from Martin Luther King Drive to 159th Street in Chicago, Cook County. | Other | 2009-04-30 | 2009-04-30 | 2011-07-30 | 2011-06-05 | 2714990 | 9.000
3318 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0209004 | This item provides design engineering services for the development of plans and specifications for the construction of I-290 from Thorndale Ave to Grand Ave; I-290 from I-88 to I-94/90 and I-355 from | Other | 2009-05-18 | 2009-05-18 | 2011-05-30 | 2011-03-09 | 3874528 | 14.000
3319 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0209005 | This item provides construction engineering service for inspection and oversight of the project on I-57 to replace 7 bridge decks in Cook and Will Counties (Northeast Illinois) | Other | 2009-05-15 | 2009-05-15 | 2010-02-28 | 2011-01-28 | 1300000 | 0.000
3320 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 0209006 | This item provides construction engineering service for inspection and oversight of the ramp modification project on I-94/90 from Hubbard's Cave to I-290 and the bridge deck replacement project at 26t | Other | 2009-05-07 | 2009-05-07 | 2011-02-28 |  | 1189458 | 0.000
3321 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0209007 | This item provides construction engineering service for inspection and oversight of the project for bridge improvement I-90/94 in Chicago (Northeast Illinois) | Other | 2009-05-11 | 2009-05-11 | 2010-12-30 |  | 702536 | 0.000
3322 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0209008 | This item provides construction engineering service for inspection and oversight of the project to resurface 159th Street in Homer Glen (Northeast Illinois) | Other | 2009-06-02 | 2009-06-02 | 2010-02-28 | 2011-06-05 | 573998.67 | 30.000
3323 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0209009 | This item provides construction engineering service for inspection and oversight of the project to resurface Burnham Avenue in Calumet City (Northeast Illinois) | Other | 2009-05-05 | 2009-05-05 | 2010-02-28 | 2011-06-05 | 784742.88 | 0.000
3324 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0209010 | This item provides construction engineering service for inspection and oversight of the project to resurface Lemont Road in Lemont (Northeast Illinois) | Other | 2009-04-30 | 2009-04-30 | 2012-12-30 |  | 710068 | 0.000
3325 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209013 | This item provides preliminary engineering services for the development of projects in the District 1 area (Northeast Illinois) | Other | 2009-06-02 | 2009-06-02 | 2011-12-30 | 2011-06-01 | 3999948.01 | 0.000
3326 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209014 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 2009-05-15 | 2009-05-15 | 2012-12-30 | 2010-12-01 | 399986.3 | 0.000
3327 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209015 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 2009-05-15 | 2009-05-15 | 2012-12-30 | 2010-12-01 | 299479.98 | 0.000
3328 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209016 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 2009-05-12 | 2009-05-12 | 2012-12-30 | 2010-12-01 | 299869.55 | 0.000
3329 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209017 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 4 (West-Central Illinois). | Other | 2009-06-02 | 2009-06-02 | 2011-12-30 |  | 1700000 | 0.000
3330 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209018 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 5 (East-Central Illinois). | Other | 2009-05-18 | 2009-05-18 | 2012-12-30 | 2010-01-05 | 500000 | 0.000
3331 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 0209019 | This project will ensure quality infrastructure by providing engineering oversight during construction of a highway interchange on Interstate 55/70 in Madison County (Southwest Illinois). | Other | 2009-06-25 | 2009-06-25 | 2012-05-30 |  | 2313381 | 0.000
3332 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209020 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 2009-05-20 | 2009-05-20 | 2012-05-30 |  | 500000 | 0.000
3333 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209021 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 2009-06-11 | 2009-06-11 | 2012-05-30 |  | 500000 | 0.000
3334 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209022 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 2009-05-15 | 2009-05-15 | 2012-05-30 |  | 500000 | 0.000
3335 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209023 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 2009-05-15 | 2009-05-15 | 2012-05-30 |  | 500000 | 0.000
3336 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209024 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 2009-05-18 | 2009-05-18 | 2011-12-30 |  | 300000 | 0.000
3337 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209025 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 2009-05-18 | 2009-05-18 | 2011-05-30 |  | 300000 | 0.000
3338 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209026 | This project provides Quality Assurance on pavement resurfacing on projects statewide in Illinois | Other | 2009-05-29 | 2009-05-29 | 2012-05-30 |  | 300000 | 0.000
3339 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 0209027 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 4 (West-Central Illinois). | Other | 2009-06-26 | 2009-06-26 | 2011-12-30 |  | 1599947 | 0.000
3340 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 0236104 | Bridge rehabilitation remove and replace deck beams to the structure carrying FAS 236 (CH 5) over the South.. Section 10-00150-00-BR | Bridge Improvement | 2010-12-15 | 2011-05-02 | 2011-06-30 | 2011-05-31 | 30159.5 | 0.010
3341 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 0239102 | This project will extend the pavement life by resurfacing sections of County Highways 39 and 24 in Henry County (Northwest Illinois). | Pavement Improvement | 2010-03-01 | 2010-06-01 | 2010-06-30 | 2010-06-29 | 375367.45 | 3.460
3342 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0242114 | This project will extend pavement life by providing a surface treatment on 9.5 miles of County Highway 16 in Bureau County (East-Central Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2009-09-30 | 2009-09-15 | 128800 | 28.380
3343 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0244101 | This project will extend pavement life by providing a surface treatment on 7.8 miles of County Highway 9 in Bureau County (East-Central Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-15 | 2009-09-30 | 2009-09-27 | 83792 | 12.780
3344 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL |  | 14 | 0281101 | This project will extend the pavement life by resurfacing a section of County Highway 19 in Kendall County (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-10-05 | 2009-10-30 | 2009-10-20 | 361760 | 3.050
3345 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 0287106 | This project will substantially improve the roadway by constructing a new bridge over the Mazon River on County Highway C29 in Grundy County (East-Central Illinois). | Bridge Replacement | 2010-03-01 | 2010-07-06 | 2010-11-30 | 2011-05-13 | 333347 | 0.010
3346 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 0294108 | This project will extend the pavement life by providing for 13.05 miles of pavement removal and resurfacing on Old U.S. Route 66 north of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-10-30 | 2009-10-29 | 3075370.29 | 16.770
3347 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON, GRUNDY |  | 11 | 0298103 | This project will extend pavement life by resurfacing 7 miles of Old US 66 between the cities of Dwight and Gardener (East-Central Illinois). | Pavement Improvement | 2009-05-11 | 2009-06-15 | 2009-10-30 | 2009-10-19 | 1984380.56 | 14.280
3348 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 0301058 | This project will extend the pavement life by resurfacing a section of US 20 in western Stephenson County (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-07-27 | 2009-11-30 | 2009-11-13 | 1655501.24 | 5.860
3349 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0303042 | This project will extend the pavement life by resurfacing 5.21 miles on IL 173 from Lake County Line to US 12 in the Villages of Fox Lake and Richmond (Northeastern Illinois) | Pavement Improvement | 2009-04-30 | 2009-05-18 | 2009-08-30 | 2009-08-11 | 1861530.67 | 5.460
3350 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 0303043 | This project will extend the pavement life by resurfacing a section of IL 251 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-26 | 2009-10-30 | 2009-07-17 | 498240.41 | 2.960
3351 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 0303044 | This project will extend the pavement life by resurfacing sections of IL 251 in the city of Loves Park (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-09-30 | 2009-08-21 | 963894.35 | 3.180
3352 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JERSEY |  | Multiple | 0304042 | This project will extend the pavement life by milling, patching and resurfacing Grafton, Illinois (Southwest Illinios). | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2009-11-30 | 2009-10-07 | 2671744.35 | 8.360
3353 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JERSEY, MADISON | ST. LOUIS (MO)-IL | Multiple | 0304043 | This project will extend the pavement life by milling, patching and resurfacing near Alton, Illinois (Southwest Illinios). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-11-30 | 2009-10-07 | 2024824.77 | 6.560
3354 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0305038 | This project will substantially improve the roadway by reconstructing a section of Palatine Rd by widening the road, providing new asphalt pavement and other roadway improvements in Palatine (Northeas | Pavement Improvement | 2010-04-28 | 2010-04-28 | 2011-05-30 |  | 7434961.91 | 0.800
3355 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY |  | 16 | 0305041 | This project will extend the pavement life by milling, patching, resurfacing and striping 2.34 miles on US 14 from Bunker Hill Rd to Park Lane Dr in unincorporated McHenry | Pavement Improvement | 2009-05-06 | 2009-05-26 | 2009-09-30 | 2009-07-30 | 631892.25 | 2.350
3356 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND |  | 17 | 0308035 | This project will extend the pavement life by resurfacing 4.4 miles of IL 81 near the city of Cambridge (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-27 | 2010-06-30 | 2011-05-12 | 4145854.26 | 4.410
3357 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 0310130 | Construction of two new structures carrying IL Route 255 over Humbert Road in Godfrey, IL (Southwest Illinois) | Pavement Widening | 2009-07-16 | 2009-09-14 | 2011-10-30 |  | 4892208.46 | 0.770
3358 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | SCHUYLER |  | 18 | 0310131 | This project will extend the pavement life by resurfacing a portion of US Route 67 near Rushville (West-Central Illinois). | Pavement Improvement | 2009-04-17 | 2009-04-23 | 2009-10-30 | 2009-10-29 | 3703886.22 | 9.860
3359 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0310132 | This project will extend the pavement life by resurfacing 3.5 miles of US 67 near the city of Milan (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-20 | 2009-10-30 | 2009-10-09 | 3631151.19 | 3.480
3360 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CASS |  | 18 | 0310134 | This project will extend the pavement life by resurfacing and updating guardrail to a portion of US Route 67 from Beardstown to 3 miles north of Meredosia (West-Central Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-04 | 2009-09-30 | 2009-08-13 | 2447155.29 | 9.960
3361 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0311037 | This project will extend the pavement life by resurfacing 4.1 miles on US Route 34 in the City of Downers Grove (Northeast Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-01 | 2009-10-30 | 2009-09-26 | 2682617.34 | 3.370
3362 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0311039 | This project will extend the pavement life by resurfacing 2.09 miles on US Route 34 in Napreville (Northeast Illinois). | Pavement Improvement | 2009-10-16 | 2010-04-14 | 2010-07-30 | 2010-09-16 | 1341100.45 | 4.300
3363 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0315055 | This project will extend the pavement life by providing surface improvements on a 0.57 mile section of U.S. Route 136 in Macomb (West-Central Illinois) | Pavement Improvement | 2009-07-30 | 2009-08-10 | 2009-11-30 | 2009-11-12 | 599706.52 | 1.140
3364 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | OGLE |  | 16 | 0316035 | This project will extend the pavement life by resurfacing a section of US 52 and IL 26 near the city of Polo (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-18 | 2009-07-30 | 2009-07-21 | 363285.85 | 1.270
3365 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | Multiple | 0317080 | This project will extend the pavement life by providing for 7.3 miles of pavement repairs and resurfacing on U.S. Route 24 north of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-04 | 2009-08-30 | 2009-07-02 | 1696469.4 | 7.280
3366 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS, PIATT |  | 15 | 0323026 | This project will extend the pavement life by providing for 9.6 miles of pavement removal and resurfacing on U.S. Route 36 south of Champaign (East-Central Illinois) | Pavement Improvement | 2009-04-23 | 2009-05-06 | 2009-09-30 | 2009-08-10 | 2479001.73 | 9.780
3367 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 0325051 | This project will extend the bridge life by replacing the bridge deck and making other bridge improvements at the intersection of US Route 45 and Illinois Route 16 in Mattoon (Southeast Illinois). | Bridge Improvement | 2010-02-24 | 2010-03-08 | 2010-11-30 | 2011-06-24 | 2866803.69 | 0.040
3368 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 0326077 | This project will extend the pavement life by resurfacing 10.9 miles of IL 47 near the city of Mazon (East-Central Illinois). | Pavement Improvement | 2009-06-08 | 2009-08-17 | 2009-10-30 | 2009-11-02 | 2355015.69 | 11.020
3369 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON, GRUNDY |  | Multiple | 0326078 | This project will extend the pavement life by resurfacing 15.6 miles of IL 47 between the cities of Dwight and Saunemin (East-Central Illinois). | Pavement Improvement | 2009-06-02 | 2009-06-08 | 2010-05-30 | 2009-11-06 | 3899088.31 | 15.490
3370 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0326079 | This project will extend the pavement life by milling, patching, resurfacing and striping 3.55 miles on US 30/IL 47 from US 30/IL 56 to Kendall County lines in the Village of Sugar Grove (Northeaster | Pavement Improvement | 2009-05-18 | 2009-05-26 | 2009-08-30 | 2009-09-09 | 1955152.42 | 5.880
3371 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 0327043 | This project consists of 2.61 miles of resurfacing which will extend the pavement life by milling, patching and resurfacing in Marion County, Illinois (Southwest Illinios). | Pavement Improvement | 2009-05-04 | 2009-05-13 | 2009-09-30 | 2009-07-30 | 792533.86 | 2.720
3372 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | IROQUOIS |  | 15 | 0329106 | This project will extend the pavement life by resurfacing a section of County Highway 10 in Iroquois County (East-Central Illinois). | Pavement Improvement | 2010-02-22 | 2010-04-13 | 2010-06-30 | 2010-06-25 | 645683 | 5.700
3373 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL |  | 11 | 0330050 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on us Route 45 over Forked Creek 2.1 miles south of Manhattan Monee Road (Northeast Illinoi | Bridge Improvement | 2009-05-11 | 2009-07-13 | 2009-09-30 | 2011-11-19 | 248217.04 | 0.010
3374 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL |  | 11 | 0330051 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 45/52 over south Branch of Forked Creek 0.5 miles south of Joliet Road near Pe | Bridge Improvement | 2009-05-11 | 2009-07-13 | 2009-09-30 | 2009-12-11 | 241853.94 | 0.010
3375 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 0330052 | This project will extend the pavement life by resurfacing a section of IL 17 near the city of Aroma (East-Central Illinois). | Pavement Improvement | 2009-06-01 | 2009-08-03 | 2009-09-30 | 2009-10-13 | 2993807.34 | 4.300
3376 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 04 | 0330053 | This project will extend the pavement life by resurfacing 1.66 miles of Mannheim Rd in theVillages of Hillside, Melrose Park, and Stone Park, (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-08 | 2009-10-30 | 2009-09-18 | 1592173.81 | 1.430
3377 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0330054 | This project will extend the pavement life by resurfacing 1.22 miles of US 12/45 from Prospect Avenue to Walnut Avenue in the City of DesPlaines in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-09-30 | 2009-09-02 | 735694.24 | 1.140
3378 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0330055 | This project will extend the pavement life by resurfacing 1.20 miles of US 12/45 from US 12 (Rand Rd) to Walnut Avenue within the City of DesPlaines in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-09-30 | 2009-09-02 | 912549.95 | 3.210
3379 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 0331048 | This project will substantially improve mobility by constructing a new four lane roadway and new bridge over west Harrisburg drainage ditch which will rerout a protion of IL13 around Harrisburg, Illin | New Construction | 2009-06-01 | 2009-07-13 | 2011-08-30 |  | 14183910.09 | 5.500
3380 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 0331050 | This project will substantially improve the roadway by constructing a new bridge over Mud Creek on IL 13 in Jackson County, Illinois (Southern Illinois) | Bridge Replacement | 2009-10-22 | 2009-11-02 | 2011-10-30 | 2011-09-03 | 1865415.6 | 0.040
3381 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0332091 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on IL 1 over Trim Creek 1 mile south of Beecher (Northeast Illinois). | Pavement Improvement | 2009-05-11 | 2009-06-23 | 2010-07-30 | 2010-10-20 | 665725.4 | 0.010
3382 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0334018 | This project will extend the pavement life by milling, patching and resurfacing 1.13 miles on US Rt. 12 (Main St) from Wisconsin State Line to IL 73 (Kenosha Rd) in the Village of Richmond (Northeaste | Pavement Improvement | 2009-06-01 | 2009-06-22 | 2009-09-30 | 2009-08-14 | 453639.51 | 1.120
3383 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0335011 | This project will extend the pavement life by resurfacing 3.91 miles on IL 176 between Nish Rd and IL 31in the Villages of Crystal Lake and Prairie Grove (Northeastern Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-08-30 | 2009-08-18 | 1288150.05 | 3.890
3384 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0335012 | This project will extend the pavement life by milling, patching, resurfacing and striping 1.44 miles on IL 60 from IL 21(Milwaukee Ave) to west of I-94(Tri-State Tollway) in the Villages of Libertyvil | Pavement Improvement | 2009-06-01 | 2009-06-19 | 2009-11-30 | 2009-09-19 | 970128.99 | 1.700
3385 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0335013 | This project will extend the pavement life by milling, patching and resurfacing 2.96 miles on IL Rt 176 and IL 60/83 from west of Thorngate Dr to IL 60/83 and from IL 176 to Midlothian Rd in Mundelein | Pavement Improvement | 2009-10-23 | 2010-04-14 | 2010-06-30 | 2010-07-29 | 1216777.6 | 5.960
3386 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0338036 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL 59 at four structures in West Chicago (Northeast Illinois). | Bridge Improvement | 2009-05-04 | 2009-06-01 | 2009-10-30 | 2009-12-03 | 1070936.11 | 1.990
3387 | Underway | C200,C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0338037 | This project will improve safety and traffic operations by reconstructing the intersection of IL 59 and US Route 30 in Plainfield (Northeast Illinois) | Pavement Improvement | 2009-06-16 | 2009-06-19 | 2011-05-30 |  | 7903047.94 | 0.010
3388 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0338038 | This project will extend the pavement life by resurfacing 5.80 miles on IL 59 in West Chicago (Northeast Illinois). | Pavement Improvement | 2009-10-28 | 2010-03-17 | 2010-08-30 | 2010-08-31 | 3889619.88 | 12.580
3389 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0338039 | This project will extend the pavement life by milling, patching and resurfacing 2.45 miles on IL Rt 59/Hough street from IL 22 to Lake-Cook Rd in Barrington (Northeastern Illinois). | Pavement Improvement | 2009-10-27 | 2010-04-12 | 2010-07-30 | 2010-09-02 | 906298.26 | 5.000
3390 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | FORD |  | 15 | 0340103 | This project will substantially improve the roadway by constructing new bridges over creeks on County Highway 26 southwest of the city of Paxton (East-Central Illinois). | Bridge Replacement | 2009-09-08 | 2009-09-23 | 2010-05-30 | 2009-12-07 | 319891 | 0.020
3391 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0341045 | This project will extend the pavement life by resurfacing 1.43 miles of Touhy Avenue (IL 72) from Lee Street to the DesPlaines River Road in the Villages of Des Plaines and Rosemont in Cook County. (N | Pavement Improvement | 2009-04-23 | 2009-05-12 | 2009-08-30 | 2009-08-19 | 1312389.16 | 1.700
3392 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0341046 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL 72 over I-90 in Gilberts in Northeastern Illinois | Bridge Improvement | 2009-06-01 | 2009-06-08 | 2009-09-30 | 2009-12-07 | 725497.89 | 0.010
3393 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0341047 | This project will extend the pavement life by milling, patching and resurfacing 0.98 miles of Il 72 in the Village of Hoffman Estates in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-08-07 | 2009-08-14 | 2009-10-30 | 2010-03-12 | 1225099.36 | 2.120
3394 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0347021 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on Il 38 over Kress Creek in West Chicago (Northeast Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-08-30 | 2009-10-29 | 383598.44 | 0.010
3395 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0348042 | This project will extend the bridge life by partial and full depth patching of the bridge deck, bridge deck overlay, joint repair, and making other roadway improvements to the IL 43 bridge over Stoney | Bridge Improvement | 2009-06-01 | 2009-06-22 | 2009-10-30 | 2009-12-01 | 697058.16 | 0.010
3396 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL |  | 14 | 0349013 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on US Rt. 30 over River St in Montgomery (Northeastern Illinois) | Bridge Improvement | 2009-04-23 | 2009-06-25 | 2009-08-30 | 2009-10-29 | 445859.2 | 0.020
3397 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL, KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0349014 | This project will extend the pavement life by milling, resurfacing and striping 2.78 miles on US Rt.30 from IL Rt 47 to Orchard Rd in the Village of Montgomery (Northeastern Illinois) | Pavement Improvement | 2009-05-18 | 2009-05-26 | 2009-08-30 | 2009-10-29 | 1019149.52 | 3.540
3398 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 0349114 | This project will substantially improve the roadway by replacing two bridges on County Highway 10 north of Weston in Livingston County (East-Central Illinois). | Bridge Replacement | 2010-03-02 | 2010-04-01 | 2010-08-30 | 2010-09-10 | 623639 | 0.020
3399 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0350029 | This project will extend the pavement life by resurfacing 1.69 miles of IL 50 (Cicero Avenue) from IL 19 (Irving Road) to I-94 in the City of Chicago. | Pavement Improvement | 2009-04-23 | 2009-05-11 | 2009-09-30 | 2009-11-30 | 1558990.02 | 3.060
3400 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0350030 | This project will extend the pavement life by resurfacing 2.92 miles of US 41/IL 50 from Foster Street to Touhy Avenue in Lincolnwood in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-18 | 2009-10-30 | 2009-12-01 | 2265153.23 | 2.910
3401 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0350031 | This project will extend pavement life by resurfacing 0.847 miles of US 41 from Old Orchard Road to Central Avenue in the Villages of Skokie and Wilmette in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-08-30 | 2009-08-27 | 651426.3 | 0.820
3402 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0350032 | This project will extend the life of the pavement by resurfacing 1.512 miles of Cicero Avenue (IL 50) from 34th Street to 46th Street and drainage improvements at IL 50 under I-55 within Cicero & Chic | Pavement Improvement | 2009-07-27 | 2009-09-15 | 2009-10-30 | 2009-12-02 | 1382759.2 | 1.460
3403 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0351018 | This project will substantially improve the roadway by reconstructing 1.92 miles of US 6 (159th street) from I-294 (Tri-State Tollway) to IL 1 (Halsted Street) in Harvey and Markham in Cook County. (N | Pavement Improvement | 2009-06-11 | 2009-06-12 | 2011-07-30 | 2011-12-12 | 18883703.23 | 2.330
3404 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0351019 | This project will extend the pavement life by resurfacing 4.78 miles on IL 7 in Homer Glen (Northeast Illinois). | Pavement Improvement | 2009-05-21 | 2009-06-09 | 2009-11-30 | 2009-09-29 | 1557324.92 | 5.180
3405 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0351020 | This project will extend the pavement life by milling, patching and resurfacing 2.59 miles of US 6 / IL 7 (159th St) from Will-Cook Rd to US 45 in the Village of Orland Park in Cook County. (Northeas | Pavement Improvement | 2009-05-21 | 2009-06-09 | 2009-10-30 | 2009-07-15 | 808496.85 | 2.980
3406 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0352010 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL Rt 137 over Des Plaines River in Libertyville (Northeastern Illinois) | Bridge Improvement | 2009-04-30 | 2009-05-06 | 2009-09-30 | 2009-09-10 | 604593.79 | 0.010
3407 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0352012 | This project will extend the pavement life by milling, patching, resurfacing, curb and gutter 2.52 miles on IL 137 from Martin Luther King Dr to west of US Rt. 41 in the Village of North Chicago (Nort | Pavement Improvement | 2009-06-01 | 2009-06-23 | 2009-10-30 | 2009-11-09 | 2389866.12 | 2.510
3408 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0353014 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on US 30 over IL 394 in the Village of Ford Heights in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-09-08 | 2010-04-16 | 2010-11-30 | 2011-09-14 | 3441423.77 | 0.020
3409 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WOODFORD |  | 18 | 0358102 | This project will substantially improve the roadway by replacing multiple drainage structures on and reconstructing 2.26 miles of County Highway 1 approximately 25 miles northeast of Peoria (West-Cent | Pavement Improvement | 2009-07-24 | 2009-08-17 | 2010-07-30 | 2010-10-12 | 466776 | 6.000
3410 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KANE, COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0360010 | This project will extend the pavement life by milling, patching and resurfacing 1.95 miles on IL 25 (Dundee ave) from I-90(Northwest Tollway) to IL 72(Higgins Rd) in the Villages of Dundee and Elgin ( | Pavement Improvement | 2009-06-11 | 2009-06-18 | 2009-11-30 | 2009-12-07 | 1762847.87 | 2.030
3411 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WOODFORD |  | 18 | 0367105 | Thie project will extend the pavement life by resurfacing a 2.5 mile section of County Highway 23 east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-03 | 2010-04-19 | 2010-06-30 | 2010-05-05 | 302173 | 3.120
3412 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARSHALL |  | 18 | 0369106 | This project will extend the pavement life by resurfacing 2 miles of County Highway 1 in Marshall County, approximately 25 miles northeast of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-09 | 2010-05-20 | 2010-05-30 | 2010-06-02 | 267610 | 2.000
3413 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0370007 | This project will extend the pavement life by resurfacing 1.52 miles Western Avenue from 87th to 99th Street. (Northeastern Illinois). | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2009-10-30 | 2009-08-28 | 1487273.46 | 2.920
3414 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA |  | 18 | 0386105 | This project will extend the pavement life by resurfacing 3.3 miles of Kickapoo-Edwards Road just west of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-03 | 2010-04-14 | 2010-05-30 | 2010-09-28 | 129720 | 3.270
3415 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 0391018 | This project will extend the pavement life by patching 19 miles of Interstate 39 trhough Lee County (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-08-30 | 2009-08-28 | 1157799.72 | 19.230
3416 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0391026 | This project will extend the bridge life by deck patching, placement of permanent protective shielding and other roadway improvements on 39th Street (Perhing Road) over S. Racine Avenue and Norfolk an | Bridge Improvement | 2009-04-28 | 2009-05-26 | 2009-08-30 | 2009-09-24 | 242959.67 | 0.010
3417 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 0392007 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 26th Street and Frontage Road B over the Franklin Connector which connects Stevenson Expr | Bridge Improvement | 2009-04-23 | 2009-07-20 | 2010-11-30 | 2011-07-01 | 5854169.45 | 0.020
3418 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0415107 | This project will extend the pavement life by resurfacing 0.5 miles of County Highway 13 in McDonough County (West-Central Illinois). | Pavement Improvement | 2010-03-02 | 2010-03-12 | 2010-05-30 | 2010-06-16 | 132000 | 0.510
3419 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HENDERSON |  | 17 | 0418113 | This project will improve the roadway by providing new concrete pavement on a section of County Highway 15 in Henderson County (West-Central Illinois). | Pavement Improvement | 2010-03-30 | 2010-04-09 | 2010-06-30 | 2010-10-05 | 229282 | 3.000
3420 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | HANCOCK |  | 17 | 0428103 | This project will extend the pavement life by resurfacing a portion Hancock County Highway 11 from Basco, IL to five miles west of Basco (West-Central Illinois). | Pavement Improvement | 2009-09-10 | 2009-09-18 | 2009-12-30 | 2010-04-21 | 476459 | 10.000
3421 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0436107 | This project will extend the pavement life by resurfacing 0.5 miles of County Highway 1 in McDonough County (West-Central Illinois). | Pavement Improvement | 2010-03-08 | 2010-03-18 | 2010-05-30 | 2010-06-16 | 132000 | 1.020
3422 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SCHUYLER |  | 18 | 0454104 | This project will substantially improve the roadway by constructing a new bridge over Dutchmans Creek on County Highway 8 near Browning in Schuyler County (West-Central Illinois). | Bridge Replacement | 2010-05-18 | 2010-08-12 | 2010-08-30 | 2010-12-09 | 243160 | 0.010
3423 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 0467106 | This project will extend the pavement life by resurfacing 3 miles of Allentown Rd approximately 10 miles southeast of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-20 | 2010-06-30 | 2010-05-06 | 446467 | 2.840
3424 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 0468102 | This project will extend the pavement life by resurfacing 7 blocks of Minier Avenue in Minier, southeast of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-21 | 2010-05-30 | 2010-04-28 | 155000 | 0.600
3425 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 0470107 | This project will extend the pavement life by providing for 1.4 miles of resurfacing on Dee Mack Road east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-05-01 | 2010-05-30 | 2010-06-09 | 320000 | 3.000
3426 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 0478106 | This project will substantially improve 0.74 mile of County Highway 29 by providing new concrete pavement and other roadway improvements north of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-07-24 | 2009-08-06 | 2010-01-30 | 2010-05-07 | 1080835 | 0.020
3427 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 0494102 | This project will extend the pavement life by providing for 2.42 miles pavement repairs and resurfacing on Horse Farm Road in LeRoy, southeast of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-09-08 | 2009-09-14 | 2009-11-30 | 2009-11-05 | 510000 | 4.840
3428 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 0496106 | This project will substantially improve the roadway by constructing a new bridge on County Highway 14 over the Middle Branch approximately 50 miles northeast of Champaign (East-Central Illinois) | Bridge Replacement | 2009-12-07 | 2010-03-15 | 2010-09-30 | 2010-07-28 | 505094 | 0.010
3429 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO |  | 16 | 0505024 | This project will extend the pavement life and improve drainage by resurfacing and replacing culverts along a section of IL 75 in the city of Rockton (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-25 | 2010-10-30 | 2010-10-15 | 1865419.88 | 11.320
3430 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 0513103 | This project will extend the pavement life with 10.4 miles of pavement repairs on Chicago Street approximately 20 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2009-04-23 | 2009-06-11 | 2009-09-30 | 2009-08-19 | 844802.75 | 9.720
3431 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | BOONE |  | 16 | 0525115 | This project will extend the pavement life by resurfacing 5.4 miles of US 20 near the city of Belvidere (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-10-30 | 2009-08-21 | 1628081.27 | 5.450
3432 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 0531108 | This project will substantially improve the roadway by reconstructing and widening County Highway 18 south of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-10 | 2010-04-05 | 2010-10-30 | 2011-05-14 | 674106 | 13.920
3433 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0535001 | This project will extend the pavement life by milling, patching anfd resurfacing 6.59 miles on IL 60/83 between IL Rt 20(Belvidere Rd) and IL 176 in the Villages of Mundelein, Ivanhoe, Volo and Round | Pavement Improvement | 2009-06-01 | 2009-06-20 | 2010-05-30 | 2009-11-23 | 2092946.58 | 6.880
3434 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | PIATT |  | 15 | 0535102 | This project will extend the pavement life by resurfacing a section of Shady Rest Road approximately 15 miles west of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-22 | 2010-03-29 | 2010-08-30 | 2010-08-13 | 276697 | 1.560
3435 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | DE WITT |  | 15 | 0543105 | This project will substantially improve the roadway by constructing a new bridge on Parnell Road over Salt Creek approximately 25 miles south of Bloomington (East-Central Illinois) | Bridge Improvement | 2009-12-14 | 2010-03-15 | 2010-08-30 | 2010-10-25 | 7515.79 | 0.010
3436 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 18 | 0548103 | This project will substantially improve the roadway by replacing a new bridge over Lake Fork Creek on County Highway 58 west of Maroa (West-Central Illinois) | Bridge Replacement | 2009-12-14 | 2010-04-19 | 2010-06-30 | 2010-08-30 | 328230 | 0.010
3437 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0556233 | This project will address noise issues with the construction of noise walls along I-55 in Romeoville and Planfield (Northeast Illinois) | Transportation Enhancements | 2009-09-14 | 2009-09-24 | 2011-05-30 |  | 8546818.35 | 6.570
3438 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0556234 | This project will address noise issues with the construction of noise walls along I-55 in Joliet and Planfield (Northeast Illinois) | Transportation Enhancements | 2009-10-07 | 2009-10-17 | 2011-05-30 | 2011-06-04 | 8162557.2 | 7.930
3439 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0556238 | Not in FMIS | Pavement Improvement | 2010-05-18 | 2010-06-01 | 2010-11-30 | 2011-09-06 | 4425119.87 | 0.020
3440 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LOGAN |  | 18 | 0559102 | This project will extend the bridge life by rehabilitating the bridge deck and making other improvements on County Highway 2 two miles north of Lincoln (West-Central Illinois). | Bridge Improvement | 2010-04-09 | 2010-04-28 | 2010-08-30 | 2010-08-17 | 368344 | 0.010
3441 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 0561029 | This project will substantially improve the roadway by constructing new bridges over creeks on IL 2 near Sauk Valley College (Northwest Illinois). | Bridge Replacement | 2009-12-08 | 2010-04-05 | 2010-11-30 | 2010-10-15 | 1959537.75 | 0.030
3442 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 16 | 0565003 | This project will extend the pavement life by resurfacing 2.9 miles of IL 136 near the city of Fulton (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-18 | 2009-10-30 | 2009-09-11 | 1284750.45 | 3.210
3443 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 0567098 | This project will extend the pavement life by resurfacing 5.3 miles of IL 38 east of the city of Dekalb (East-Central Illinois). | Pavement Improvement | 2009-06-01 | 2009-07-06 | 2009-09-30 | 2009-09-03 | 1894158.35 | 10.600
3444 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MASON |  | 18 | 0567115 | This project will extend the pavement life by providing a surface treatment on a section of County Highway 20 near Forest City in Mason County (West-Central Illinois). | Pavement Improvement | 2009-08-27 | 2009-09-08 | 2009-09-30 | 2009-10-01 | 229661 | 3.830
3445 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 0567126 | This project will extend the pavement life by resurfacing 2.2 miles of IL 38 in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 2009-08-11 | 2009-08-31 | 2010-07-30 | 2010-05-19 | 1829377.42 | 4.340
3446 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 0572149 | This project will extend the pavement life by milling, rubblizing, patching and resurfacing 8.68 miles of Interstate 57 in Franklin County Illinois (Southern Illinios). | Pavement Improvement | 2009-04-28 | 2009-07-13 | 2009-08-30 | 2009-08-31 | 8982883.85 | 8.680
3447 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 0574128 | This project will extend the pavement life by resurfacing a portion of Interstate 57 from south of Arcola to Mattoon (Southeast Illinois). | Pavement Improvement | 2009-05-20 | 2009-06-09 | 2010-08-30 | 2010-08-24 | 21644677.63 | 10.870
3448 | Underway | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | MENARD |  | 18 | 0574209 | This project will substantially improve the roadway by designing plans for reconstructing a section of County Highway 2 near Petersburg (West-Central Illinois). | Other | 2010-08-01 | 2010-10-01 | 2011-06-30 |  | 224677 | 6.160
3449 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CASS |  | 18 | 0575312 | This project will substantially improve the roadway by constructing a new bridge over Middle Creek on County Highway 12 near Newmansville (West-Central Illinois). | Bridge Replacement | 2010-04-15 | 2010-06-01 | 2010-08-30 | 2010-10-19 | 212157 | 0.010
3450 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK |  | 01 | 0577277 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 112th Place over I-57 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-06-01 | 2009-06-04 | 2009-11-30 | 2010-07-03 | 2814816.26 | 0.010
3451 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577278 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 103rd Street over I-57 in Chicago. (Northeastern Illinois). | Bridge Improvement | 2009-05-04 | 2009-06-01 | 2009-11-30 | 2010-10-28 | 2035725.16 | 0.010
3452 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0577279 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on North Peotone/Joliet Road over I-57in Peotone (Northeast Illinois). | Bridge Improvement | 2009-05-11 | 2009-07-20 | 2009-09-30 | 2009-11-05 | 416352.79 | 0.010
3453 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577280 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the 115th Street over I-57 in Chicago, Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-04-23 | 2009-05-11 | 2009-11-30 | 2010-10-15 | 2814594.65 | 0.010
3454 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577281 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 125th Street over I-57 in Calumet Township. (Northeastern Illinois). | Bridge Improvement | 2009-04-28 | 2009-05-24 | 2009-11-30 | 2010-06-08 | 1559048.19 | 0.010
3455 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577282 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 111th Street over I-57 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-06-01 | 2010-04-01 | 2010-09-30 | 2011-06-18 | 2934155.15 | 0.010
3456 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0577283 | This project will extend the bridge life by repairing the bridge deck and new deck overlay to 0.06 miles of the 167th Street bridge over I-57 in the Cities of Oark Park and Country Club Hills in Cook | Bridge Improvement | 2009-06-22 | 2009-07-17 | 2009-10-30 | 2010-04-27 | 601119.13 | 0.010
3457 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0577285 | This project will extend the pavement life by milling, patching and resurfacing 7.2 miles of I-57 from the Will Co Line to 175th St in the Villages of Country Cub Hills, Matteson, Bremen, and Richton | Pavement Improvement | 2009-10-23 | 2010-03-26 | 2010-08-30 | 2010-10-05 | 12102830.73 | 14.480
3458 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0587024 | This project will extend the pavement life by resurfacing 6.2 miles of IL 92 between the cities of Ohio and Walnut (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-01 | 2009-08-30 | 2009-07-23 | 1872317.64 | 5.910
3459 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 0592052 | This project will extend the pavement life by milling, patching and resurfacing 1.78 miles in St. Clair County, IL (Southwest Illinois) | Pavement Improvement | 2009-05-11 | 2009-05-15 | 2009-10-30 | 2009-09-04 | 808855.39 | 1.780
3460 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PIKE |  | 18 | 0598102 | This project will extend the pavement life by resurfacing a 3.57 mile section of County Highway 2 from Baylis to New Salem in Pike County (West-Central Illinois). | Pavement Improvement | 2010-04-01 | 2010-04-28 | 2010-06-30 | 2010-07-07 | 452500 | 3.060
3461 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SCOTT |  | 18 | 0605107 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on County Highway 3 over Wolf Run Creek northwest of Bluffs (West-Central Illinois). | Bridge Improvement | 2010-04-27 | 2010-07-26 | 2010-06-30 | 2010-12-06 | 162350 | 0.010
3462 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0607078 | This project will extend the pavement life by resurfacing 1.11 miles on US Routes 52/30/6 in Joliet (Northeast Illinois). | Pavement Improvement | 2009-05-11 | 2009-05-21 | 2009-08-30 | 2009-09-26 | 592221.76 | 1.160
3463 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0607079 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 30 over Hickory Creek in Joliet (Northeast Illinois). | Bridge Improvement | 2009-05-11 | 2009-06-15 | 2009-09-30 | 2009-10-15 | 329999.7 | 0.010
3464 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 0611014 | This project will extend the pavement life by resurfacing 4 miles of IL 92 in the city of Rock Island (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-08 | 2009-08-30 | 2009-07-23 | 648677.93 | 2.340
3465 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 0611015 | This project will extend the pavement life by resurfacing a section of IL 81 near the city of Andover (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-08-30 | 2009-06-17 | 384371.34 | 0.720
3466 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MASON |  | 18 | 0614030 | This project will extend the pavement life by milling, patching, and resurfacing a portion of Illinois Route 78 from Havana to Saidora (West-Central Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-08 | 2009-11-30 | 2010-03-24 | 5268038.33 | 13.610
3467 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0618003 | This project will extend pavement life by providing for 6.8 miles of surface improvements on IL Rte. 41 east of the City of Macomb which is approximately 50 miles west of the City of Peoria (West-Cent | Pavement Improvement | 2009-07-30 | 2009-08-13 | 2009-11-30 | 2009-11-02 | 1475854.58 | 12.680
3468 | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | Multiple | 0627106 | This project will extend the pavement life by providing a surface treatment on a section of County Highway 37 and 31 in Sangamon County (West-Central Illinois). | Pavement Improvement | 2010-08-05 | 2010-08-30 | 2010-06-30 | 2010-12-01 | 507319 | 9.250
3469 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 0630006 | This project will extend the pavement life by providing for 4.84 miles of pavement repairs and resurfacing on IL Route 100 near the City of Bryant which is approximately 35 miles southwest of the Cit | Pavement Improvement | 2009-04-28 | 2009-05-04 | 2009-08-30 | 2009-07-18 | 898945.73 | 4.970
3470 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL |  | 11 | 0631015 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on IL 102 over Rayns Creek southeast of Wilmington (Northeast Illinois). | Bridge Improvement | 2009-04-28 | 2009-06-08 | 2009-09-30 | 2009-10-14 | 238149.41 | 0.010
3471 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 0638010 | This project will extend the pavement life by resurfacing a section of US 6 in the city of Geneseo (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-08-30 | 2009-07-31 | 624614.88 | 2.290
3472 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 0638013 | This project will substantially improve the roadway by constructing a new bridge over Hennepin Canal on IL 82 near the city of Geneseo (Northwest Illinois). | Bridge Replacement | 2009-12-08 | 2010-04-05 | 2010-11-30 | 2010-11-05 | 1512229 | 0.020
3473 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 0642123 | This project will substantially improve the roadway by constructing a new section of roadway near Mattoon (Southeast Illinois). | New Construction | 2009-07-22 | 2009-08-10 | 2010-10-30 | 2010-11-04 | 307906 | 2.260
3474 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STARK |  | 18 | 0643204 | This project will extend the pavement life by providing for 3.4 miles of pavement repair and resurfacing on IL Route 17 at Toulon which is approximately 30 miles northwest of the City of Peoria ( West | Pavement Improvement | 2009-07-30 | 2009-08-03 | 2009-09-30 | 2009-08-21 | 502367.71 | 6.940
3475 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHRISTIAN |  | 19 | 0645112 | This project will extend the pavement life by resurfacing and other improvements on approximately six miles of County Highway 1 near Vanderville (West-Central Illinois). | Pavement Improvement | 2010-04-27 | 2010-06-01 | 2010-08-30 | 2010-10-22 | 420098 | 9.190
3476 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 17 | 0646069 | This project will extend the pavement life by resurfacing a section of IL 40 in the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-09-08 | 2009-11-30 | 2010-05-06 | 1119300.53 | 1.250
3477 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MARSHALL, STARK |  | 18 | 0646070 | This project will extend the pavement life by providing for 4.43 miles of pavement repair and resurfacing on IL Route 40 and IL Route 17 approximately 25 miles north of the City of Peoria (West-Centra | Pavement Improvement | 2009-07-30 | 2009-08-10 | 2009-10-30 | 2009-11-10 | 1163946.27 | 8.070
3478 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JO DAVIESS |  | 16 | 0650008 | This project will improve drainage by replacing 2 culverts on IL 78 in Jo Daviess County. | Bridge Improvement | 2010-03-03 | 2010-05-03 | 2010-09-30 | 2010-11-12 | 646110.45 | 0.030
3479 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE, PUTNAM |  | Multiple | 0653028 | This project will extend the pavement life by resurfacing 6.5 miles of IL 18 between the cities of Magnolia and Lostant (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-22 | 2009-09-30 | 2009-08-10 | 1273129.8 | 12.130
3480 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 0662063 | This project will substantially improve the roadway by reconstructing the intersection of IL Route 4 and Monroe/Old Jacksonville Rd. by providing new pavement and other roadway improvements in Springf | Pavement Improvement | 2010-03-01 | 2010-04-15 | 2011-05-30 | 2011-10-26 | 2174000 | 3.370
3481 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CUMBERLAND |  | 15 | 0662102 | This project will extend the pavement life by resurfacing and other improvements on FAS Route 662 in Cumberland County (Southeast Illinois). | Pavement Improvement | 2010-04-09 | 2010-04-20 | 2010-08-30 | 2010-05-14 | 252088 | 1.200
3482 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WARREN |  | 17 | 0665013 | This project will extend the pavement life by providing for 5.08 miles of pavement repair and resurfacing along IL Route 116 near the City of Roseville which is approximately 60 miles west of the City | Pavement Improvement | 2009-07-27 | 2009-08-10 | 2009-10-30 | 2009-09-19 | 1085914.56 | 10.120
3483 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX, FULTON |  | 17 | 0665014 | This project provides for 8.3 miles of pavement repairs and resurfacing, extending the pavement life, on Illinois Route 116 near the City of St. Augustine which is approximately 40 miles west of the C | Pavement Improvement | 2009-07-27 | 2009-08-06 | 2009-11-30 | 2009-11-09 | 2514670.91 | 14.560
3484 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WOODFORD |  | 18 | 0673024 | This project will extend the pavement life by resurfacing of 5.90 miles of IL Routes 116 and 117 near the west city limits of the City of Roanoke which is approximately 20 mile east of the City of Peo | Pavement Improvement | 2009-04-28 | 2009-05-07 | 2009-10-30 | 2009-07-16 | 2207309.24 | 6.120
3485 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 0674111 | This project will substantially improve the roadway by replacing a box culvert on Fish Hatchery Road near Paradise (Southeast Illinois). | Bridge Improvement | 2009-05-21 | 2009-06-17 | 2009-07-30 | 2009-07-02 | 162702.01 | 0.010
3486 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | EDGAR |  | 15 | 0678106 | This project will substantially improve the roadway by reconstructing and resurfacing a section of County Highway 21, approximately 50 miles southeast of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-17 | 2010-07-19 | 2010-06-30 | 2010-09-23 | 336991 | 2.710
3487 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 0681037 | This project wil substantially improve the roadway by reconstructing a section of IL 116 in the village of Cullom. | Pavement Improvement | 2009-04-30 | 2009-06-22 | 2010-05-30 | 2010-06-15 | 3061067.67 | 0.890
3488 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 0681038 | This project will extend the pavement life by resurfacing the road and replacing curb and gutter in the village of Saunemin (East-Central Illinois). | Pavement Improvement | 2010-04-07 | 2010-05-06 | 2011-06-30 | 2010-11-29 | 616988 | 0.650
3489 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HANCOCK |  | 17 | 0685028 | This project will extend the pavement life by resurfacing a portion of Illinois Route 9 in Hancock County from Dallas City to LaHarpe (West-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-10-30 | 2009-10-29 | 3527422.24 | 13.280
3490 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 0693065 | Remvl & repl of structure carrying IL 9 over Mackinaw River Trib 0.3 mil W of Mackinaw inc. pvmnt rem/rep, earthwork, HMA overlay etc. Sect. 119BR-2 BR | Bridge Replacement | 2011-01-03 | 2011-01-13 | 2011-09-30 | 2011-09-15 | 913271.79 | 0.010
3491 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CRAWFORD |  | 15 | 0696107 | This project will substantially improve the roadway by constructing a new bridge over Bennett Creek on County Highway 6 near Robinson in Crawford County (Southeast Illinois). | Bridge Replacement | 2009-12-28 | 2009-12-28 | 2010-07-30 | 2010-06-29 | 186600 | 0.200
3492 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CRAWFORD |  | 15 | 0696108 | Resurface FAS 696 (CH 6) from IL RTE 33 North for 1.55 miles in Crawford County. Section 10-00095-00-RS | Pavement Improvement | 2010-12-16 | 2011-06-10 | 2011-06-30 | 2011-07-14 | 30159.5 | 1.600
3493 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 0697030 | This project will extend the life of the roadway by providing for 6.5 miles of pavement repairs, resurfacing, and bridge deck repairs on Illinois Route 9 in Vermilion County at the Indiana border (Eas | Pavement Improvement | 2009-05-15 | 2009-06-15 | 2009-10-30 | 2009-10-08 | 2085502.67 | 6.630
3494 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | Multiple | 0701184 | This project will extend the pavement life by milling, patching and resurfacing 3. 67 miles of Interstate 55/70 from Canteen Creek to just north of Il 157. In addition this project will include brid | Pavement Improvement | 2010-02-22 | 2010-03-29 | 2010-08-30 | 2011-03-16 | 9577498.24 | 10.930
3495 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | JASPER |  | 19 | 0704138 | This project will substantially improve the roadway by reconstructing a section of County Highway 6 near Gila in Jasper County (Southeast Illinois). | Pavement Improvement | 2009-08-03 | 2009-08-11 | 2009-10-30 | 2009-09-02 | 299807 | 3.500
3496 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 0709024 | This project will extend the pavement life by providing for 3.8 miles of pavement repairs and resurfacing on U.S. Route 136 north of Champaign (East-Central Illinois) | Pavement Improvement | 2009-05-04 | 2009-05-29 | 2009-08-30 | 2009-07-29 | 956727.74 | 3.800
3497 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 0711010 | This project will extend the life of the roadway by providing for 7.6 miles of pavement repairs, resurfacing, and culvert replacement on Illinois Route 119 in Vermilion County at the Indian border (Ea | Pavement Improvement | 2009-05-06 | 2009-05-18 | 2009-10-30 | 2009-10-05 | 1935511.91 | 7.780
3498 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | EFFINGHAM |  | 19 | 0711108 | This project will extend the pavement life by adding new shoulders and resurfacing a portion of County Highway 25 south of Altamont (Southeast Illinois) | Pavement Improvement | 2009-09-16 | 2009-10-07 | 2009-12-30 | 2009-11-09 | 361611 | 8.000
3499 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | FAYETTE |  | 17 | 0712106 | This project will substantially improve the roadway by replacing and repairing several culverts on County Highway 24 in Fayette County (Southeast Illinois). | Bridge Improvement | 2009-08-24 | 2009-09-08 | 2009-12-30 | 2010-08-13 | 410144 | 6.240
3500 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SHELBY |  | 19 | 0713111 | This project will substantially improve the roadway by reconstructing a section of Michigan and Logan Streets by providing new concrete pavement and other roadway improvements in Tower Hill (Southeast | Pavement Improvement | 2009-12-10 | 2010-03-09 | 2010-08-30 | 2010-09-27 | 487714 | 0.820
3501 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MONTGOMERY |  | 17 | 0721219 | This project will substantially improve the roadway by reconstructing a new bridge over East Fork of Shoal Creek on County Highway 8 near Filmore (West-Central Illinois) . | Bridge Replacement | 2009-12-14 | 2010-06-14 | 2010-08-30 | 2011-05-10 | 368721 | 0.010
3502 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 0725005 | This project will extend the pavement life by resurfacing 0.9 miles of Illinois Route 10 in Champaign (East-Central Illinois). | Pavement Improvement | 2010-03-15 | 2010-04-12 | 2010-06-30 | 2010-06-01 | 708435.25 | 2.000
3503 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 0726058 | This project will extend the pavement life by milling, patching and resurfacing 6.58 miles of IL 148 in Franklin County, Illinois (Southern Illinios). | Pavement Improvement | 2009-04-28 | 2009-06-08 | 2009-09-30 | 2009-10-01 | 2446918.04 | 13.450
3504 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 0734042 | This project will extend the pavement life by resurfacing a section of IL 251 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-08-30 | 2009-07-22 | 318933.82 | 0.630
3505 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | GREENE |  | 17 | 0738107 | This project will improve roadway quality by milling and resurfacing County Highway 10 in Greene County (Southwest Illinois). | Pavement Improvement | 2010-03-19 | 2010-05-17 | 2010-05-30 | 2011-04-29 | 336388 | 1.500
3506 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 15 | 0741094 | This project will extend the pavement life by resurfacing a portion of Illinois Route 105 through the City of Decatur (Southeast Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-27 | 2009-10-30 | 2009-11-23 | 2385691.68 | 3.050
3507 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0741096 | This project will extend the structural life by completing repairs on the viaducts carrying Interstate 74 over IL 92 in the city of Moline (Northwest Illinois). | Bridge Improvement | 2009-04-30 | 2009-05-11 | 2009-08-30 | 2009-09-04 | 756407.74 | 0.020
3508 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0741097 | This project will extend the pavement life by resurfacing a section of Interstate 74 and completing bridge repairs on several structures in the city of Moline (Northwest Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-11 | 2010-10-30 | 2010-12-03 | 11442129.66 | 5.750
3509 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | PIATT |  | 15 | 0741098 | This project will extend the pavement life by providing for 12.6 miles of pavement repairs and resurfacing on Illinois Route 105 west of Decatur (East-Central Illinois) | Pavement Improvement | 2009-04-30 | 2009-05-20 | 2009-10-30 | 2009-08-27 | 2921806.75 | 12.660
3510 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 0742127 | This project will substantially improve the roadway by constructing new bridges over Opheim Road on Interstate 74 and other roadway improvements north of the city of Woodhull (Northwest Illinois). | Bridge Improvement | 2009-12-08 | 2010-04-05 | 2010-11-30 | 2010-11-02 | 3466511.46 | 0.610
3511 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | Multiple | 0744238 | This project will extend the pavement life by providing for 4.24 miles of pavement repairs and resurfacing on Interstate 74 in Bloomington (East-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-04 | 2010-08-30 | 2010-05-14 | 7205166.81 | 4.610
3512 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA |  | 18 | 0744239 | This project will extend the pavement life by providing for 6.12 miles of pavement removal and resurfacing on a section of Interstate 74 approximately 7 miles west of the City of Peoria (West-Central | Pavement Improvement | 2009-04-28 | 2009-04-29 | 2009-11-30 | 2009-08-14 | 7967475.6 | 5.720
3513 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 0744240 | This project will extend the pavement life by providing for 6.41 miles of pavement repairs, resurfacing, and other improvements to Interstate 74 just east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2009-11-30 | 2009-08-14 | 7872358.65 | 6.730
3514 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | Multiple | 0745079 | This project will extend the pavement life by resurfacing a portion of Illinois Route 104 to the east from Quincy (West-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-18 | 2009-11-30 | 2009-11-30 | 4666894.14 | 5.870
3515 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN, PIATT |  | 15 | 0745158 | This project will extend the pavement life by providing for 4.6 miles of pavement repairs, resurfacing, safety improvements on Interstate 74 west of Champaign (East-Central Champaign) | Pavement Improvement | 2009-05-06 | 2009-05-28 | 2009-10-30 | 2009-09-02 | 3374493.73 | 10.950
3516 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MOULTRIE, DOUGLAS |  | 15 | 0749022 | This project will extend the pavement life by resurfacing and adding shoulders to Illinois Route 133 through Arthur, Douglas County (East-Central Illinois). | Transportation Enhancements | 2010-04-09 | 2010-05-10 | 2010-08-30 | 2010-07-02 | 113877 | 1.140
3517 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 0753036 | This project will extend the pavement life by resurfacing a portion of Illinois Route 104 near Waverly (West-Central Illinois). | Pavement Improvement | 2009-04-30 | 2009-07-27 | 2009-11-30 | 2010-08-13 | 2118638.78 | 2.100
3518 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CALHOUN |  | 17 | 0754113 | This project will extend the pavement life by milling, patching and resurfacing of County Highway 1 from the Village of Hardin city limits to Lincoln Valley Road in Calhoun County, Illinois (Southwest | Pavement Improvement | 2009-12-29 | 2010-06-01 | 2010-05-30 | 2010-07-01 | 142719 | 0.640
3519 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | SHELBY |  | 19 | 0766005 | This project will extend the pavement life by resurfacing a portion of Illinois Route 32 west of Oblong (Southeast Illinois). | Pavement Improvement | 2009-04-23 | 2009-04-30 | 2009-10-30 | 2009-06-23 | 2075179.07 | 13.000
3520 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CUMBERLAND |  | 15 | 0773008 | This project will extend the pavement life by resurfacing a portion of Illinois Route 121 in Greenup (Southeast Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-18 | 2009-09-30 | 2009-07-03 | 1378480.65 | 5.180
3521 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BOND |  | 19 | 0777114 | This project will extend the pavement life by resurfacing Sorento Road from New Douglas road to Crane Road in Sorento, Illinois (Southwest Illinois). | Pavement Improvement | 2009-11-03 | 2010-03-01 | 2010-05-30 | 2010-07-07 | 197632.86 | 5.650
3522 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CLINTON |  | 19 | 0778106 | This project will improve driving quality by milling and resurfacing County Highway 14 in Clinton County (Southwest Illinois). | Pavement Improvement | 2010-03-01 | 2010-06-02 | 2010-05-30 | 2010-06-18 | 327104 | 4.240
3523 | Completed | C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 0778107 | This project will extend the pavement life by resurfacing St. Rose Road from the city of Highland to the Clinton County line in Madison County (Southwest Illinois). | Pavement Improvement | 2010-05-10 | 2010-05-12 | 2010-06-30 | 2010-06-22 | 422778.23 | 3.110
3524 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BOND |  | 19 | 0779105 | Planning and design engineering to replace the bridge carrying North Pokey Road over Indian Creek in Bond County, IL (Southwest Illinois) | Other | 2010-05-24 | 2010-05-24 | 2010-12-30 | 2011-08-30 | 66520 | 0.010
3525 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CRAWFORD |  | 15 | 0781030 | This project will extend the pavement life by resurfacing a portion of Illinois Route 33 west of Oblong (Southeast Illinois). | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2010-07-30 | 2010-12-10 | 6162844.79 | 2.520
3526 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 0788004 | This project will substantially improve the roadway by reconstructing a section of Illinois Route 3 by providing new pavement and other roadway improvements in Venice (Southwest Illinois). | New Construction | 2009-06-16 | 2009-10-12 | 2011-08-30 | 2011-03-03 | 3755356.36 | 1.260
3527 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WASHINGTON |  | 19 | 0788112 | This project will improve driving quality by patching, resurfacing, and upgrading pavement markings along County Highway 24 near Hoyleton, Illinois (Southwest Illinois). | Pavement Improvement | 2010-03-01 | 2010-07-06 | 2010-07-30 | 2011-06-28 | 340000 | 4.000
3528 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CLAY |  | 19 | 0801230 | Preliminary engineering for a structure replacement over Laws Creek east of Ingram in Clay County. Section 09-00082-00-BR | Other | 2009-06-19 | 2009-06-22 | 2010-04-30 | 2010-05-31 | 47000 | 0.000
3529 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CLAY |  | 19 | 0801231 | This project will substantially improve the roadway by constructing a new bridge over Laws Creek on East Dundas Lane near Ingraham(Southeast Illinois). | Bridge Replacement | 2010-04-19 | 2010-05-20 | 2010-09-30 | 2010-08-18 | 230366 | 0.010
3530 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | RICHLAND |  | 19 | 0801232 | This project will extend the pavement life by resurfacing and other improvements on East Dundas Lane near Dundas (Southeast Illinois). | Pavement Improvement | 2010-04-21 | 2010-05-07 | 2010-05-30 | 2010-05-19 | 229556 | 1.190
3531 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0802064 | This project will extend the pavement life by resurfacing 7.5 miles of Interstate 80 near the city of Seatonville (East-Central Illinois). | Pavement Improvement | 2009-05-21 | 2009-06-08 | 2009-10-30 | 2009-07-16 | 3681905.14 | 7.360
3532 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 0803130 | This project will extend the pavement life by resurfacing 30 miles of Interstate 80 in LaSalle County (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-17 | 2009-08-30 | 2009-06-01 | 1174180.11 | 29.990
3533 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 0803131 | This project will extend the pavement life by providing a surface treatment on 6.3 miles of Interstate 80 in western Grundy County (East-Central Illinois). | Pavement Improvement | 2009-05-11 | 2009-06-15 | 2009-07-30 | 2009-07-16 | 1500910.6 | 6.300
3534 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0805071 | This project will extend the pavement life by resurfacing 6.125 miles of I-80 from 80th Ave to I-290 in the Tinley Park, Country Club Hills, and Hazel Crest. (Northeastern Illinois). | Pavement Improvement | 2009-10-27 | 2010-04-05 | 2010-08-30 | 2010-12-30 | 15821320 | 13.110
3535 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LAWRENCE |  | 19 | 0805108 | This project will extend the pavement life by widening and resurfacing 3.5 miles of County Highway 9 in Lawrence County (Southeast Illinois). | Pavement Improvement | 2010-03-01 | 2010-04-28 | 2010-07-30 | 2010-07-13 | 284790 | 3.590
3536 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CLARK |  | 15 | 0832013 | This project will extend the pavement life by providing a surface treatment on a seven mile section of IL Route 49 from Casey to the Cumberland County Line (Southeastl Illinois). | Pavement Improvement | 2010-03-10 | 2010-06-01 | 2010-06-30 | 2010-07-19 | 405162.69 | 14.000
3537 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 0836028 | This project will extend the pavement life by providing for 5.7 miles of pavement removal and resurfacing on Illinois Route 49 southeast of Champaign (East-Central Illinois) | Pavement Improvement | 2009-05-06 | 2009-05-11 | 2009-08-30 | 2009-07-01 | 1083541.33 | 5.980
3538 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL |  | 11 | 0840061 | This project will extend the pavement life by resurfacing 3.33 miles on IL 50north of Peotone (Northeast Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-05 | 2009-09-30 | 2009-07-31 | 1455187.96 | 4.110
3539 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | IROQUOIS |  | 15 | 0840062 | This project will extend the pavement life by resurfacing 10.7 miles of IL 49 near the city of Crescent City (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-08 | 2009-10-30 | 2009-08-05 | 2099137.03 | 10.800
3540 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0840063 | This project will extend the pavement life by resurfacing 2.06 miles on IL 50 in Monee/Peotone (Northeast Illinois). | Pavement Improvement | 2009-10-16 | 2010-04-12 | 2010-06-30 | 2010-06-18 | 1041653.69 | 2.900
3541 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 0846019 | This project will extend the pavement life by resurfacing 6.4 miles of IL 53 near the city of Gardener (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-13 | 2009-10-30 | 2009-10-09 | 1812639.8 | 6.300
3542 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0852011 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 52 over Jackson Creek 4 miles southeast of IL 53 (Northeast Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-09 | 2009-08-30 | 2009-11-15 | 284272.44 | 0.010
3543 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0856025 | This project will extend the pavement life by resurfacing 2.65 miles on IL 7 in Joliet and Crest Hill (Northeast Illinois). | Pavement Improvement | 2009-10-23 | 2010-06-22 | 2010-07-30 | 2010-08-31 | 1739465.28 | 9.930
3544 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PERRY |  | 12 | 0865106 | This project will extend the pavement life by resurfacing approximately 1 mile of Old DuQuoin Rd in DuQuoin. (Southern Illinois) | Pavement Improvement | 2010-02-22 | 2010-05-01 | 2010-05-30 | 2010-06-14 | 249928 | 2.880
3545 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0866007 | This project will substantially improve the roadway by resurfacing 4.41 miles, widening, installing traffic signals and drainage improvements on IL 83 from Wisconsin State line to Petite Lake Rd in th | Pavement Improvement | 2009-08-24 | 2009-09-08 | 2011-05-30 | 2011-12-06 | 14333988.5 | 9.240
3546 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 0869036 | This project will improve safety by replacing an existing bridge on IL 34 near Benton, Illinois (Southern Illinois) | Bridge Replacement | 2010-02-24 | 2010-05-03 | 2010-11-30 | 2011-08-02 | 730800.14 | 0.040
3547 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 0870011 | This project will extend the pavement life by resurfacing 1.06 miles on IL 53 in the City of Lombard (Northeast Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-18 | 2009-08-30 | 2009-12-12 | 444851.03 | 0.990
3548 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITE |  | 15 | 0877013 | This project will substantially improve the roadway by constructing a new bridge over a tributary of Can Creek on IL 141 in White County, Illinois (Southern Illinois) | Bridge Replacement | 2009-12-10 | 2010-01-18 | 2010-11-30 | 2010-12-10 | 815676.5 | 0.200
3549 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | Multiple | 0881018 | This project will extend the pavement life by resurfacing 7.9 miles of Interstate 88 near the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2009-10-30 | 2009-10-09 | 3890483.19 | 8.450
3550 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JOHNSON |  | 19 | 0885040 | This project will extend the pavement life by milling, patching and resurfacing 8.46 miles of IL 146 in Johnson County, Illinois (Southern Illinios). | Pavement Improvement | 2009-06-02 | 2009-06-25 | 2009-08-30 | 2009-08-26 | 1557257.01 | 8.780
3551 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WHITE |  | 15 | 0887108 | Grade slopes and place riprap to prevent erosion for 0.55 miles on County Highway 7 in White County, Illinois (Southern Illinois) | Pavement Improvement | 2009-09-09 | 2009-10-08 | 2009-10-30 | 2009-11-09 | 234834.84 | 2.000
3552 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WHITE |  | 15 | 0887109 | Grade slopes and place riprap to prevent erosion for 0.26 miles on County Highway 7 in White County, Illinois (Southern Illinois) | Pavement Improvement | 2009-12-10 | 2009-12-15 | 2010-05-30 | 2010-01-26 | 66757 | 0.450
3553 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | GALLATIN |  | 19 | 0888122 | This project will extend the pavement life by resurfacing 4.48 of County Highway 3 in Gallatin Coutny, Illinois (Southern Illinois). | Pavement Improvement | 2009-07-30 | 2009-11-09 | 2009-10-30 | 2009-12-22 | 190041 | 9.000
3554 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 0898107 | This project will extend the pavement life by resurfacing Harco Road from IL 13 to Brushy Creek Road in Saline County (Southern Illinois). | Pavement Improvement | 2009-12-17 | 2010-05-03 | 2010-07-30 | 2010-05-14 | 286154 | 4.390
3555 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0904117 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the Sayre Avenue Bridge over I-90 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-04-23 | 2009-06-08 | 2010-09-30 | 2011-07-09 | 2925184.16 | 0.010
3556 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0904118 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the Central Avenue Bridge over I-90 in the City of Chicago, Cook County. (Northeastern Il | Bridge Improvement | 2009-04-28 | 2009-05-18 | 2009-11-30 | 2011-05-03 | 2788874.83 | 0.010
3557 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 0915102 | This project will extend the pavement life by milling, patching and resurfacing 1.57 miles of Grand Tower Road in Jackson County, Illinois (Southern Illinios). | Pavement Improvement | 2009-07-30 | 2009-08-27 | 2009-10-30 | 2009-10-20 | 382828 | 1.590
3558 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JOHNSON |  | 19 | 0924124 | This project will extend the pavement life by resurfacing 1.99 miles of Lick Creek road south from Williamson county line in Johnson County. (Southern Illinois). | Pavement Improvement | 2010-08-05 | 2010-08-10 | 2010-06-30 | 2010-08-27 | 237061 | 1.400
3559 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | UNION |  | 12 | 0926112 | This project will extend the pavement life by resurfacing St. Johns Road from the city of Dongola to IL127 in Union County (Southern Illinois). | Pavement Improvement | 2010-04-12 | 2010-05-11 | 2010-06-30 | 2010-11-18 | 131915 | 5.680
3560 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MASSAC |  | 19 | 0931110 | This project will extend the pavement life by resurfacing 1.35 miles of County Highway 11 in Massac County, Illinois (Southern Illinois). | Pavement Improvement | 2009-09-10 | 2009-10-05 | 2009-10-30 | 2009-11-04 | 176112 | 2.700
3561 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HARDIN |  | 19 | 0934106 | Resurface FAS 934 (Karbers Ridge Rd) from 3.9 miles east of IL RTE 34 easterly for 4.5 miles to the county line. Section 06-00025-00-RS | Pavement Improvement | 2010-12-16 | 2011-04-05 | 2011-06-30 | 2011-05-31 | 126711 | 4.300
3562 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0943416 | This project will extend the pavement life by resurfacing 6.97 miles of I-94 (Bishop Ford Expressway) from Martin Luther King Drive to 130th Street (south of Dolton Avenue) in Chicago in Cook County. | Pavement Improvement | 2009-05-07 | 2009-05-18 | 2010-08-30 | 2010-09-22 | 14032252.99 | 5.260
3563 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0943417 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on I-94 over the Little Calumet River and Greenwood Ave. Additionally, the project will sub | Pavement Improvement | 2009-04-29 | 2009-05-11 | 2010-05-30 | 2010-09-22 | 12817333.94 | 4.290
3564 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | ALEXANDER |  | 12 | 0946107 | This project will extend the pavement life by resurfacing 3.99 miles of Miller City Road in Alexander County, Illinois (Southern Illinois). | Pavement Improvement | 2009-07-30 | 2009-09-09 | 2009-10-30 | 2009-10-20 | 184896 | 8.000
3565 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 16 | 1225115 | This project will extend the pavement life by resurfacing sections of Albany Road in western Whiteside County (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-10-12 | 2009-11-30 | 2009-11-05 | 505781 | 9.180
3566 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 1238009 | This project will extend the pavement life by resurfacing 2.83 miles on IL 176 from Midlothian to IL 21 in the Villages of Libertyville and Mundelein (Northeastern Illinois) | Pavement Improvement | 2009-10-21 | 2010-04-12 | 2010-07-30 | 2010-09-18 | 1078944.4 | 7.280
3567 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 1238010 | This project will extend the pavement life by resurfacing 1.17 miles on IL 176 from IL Rt. 21 to St. Mary's Rd in the Village of Libertyville (Northeastern Illinois). This project will also improve b | Pavement Improvement | 2009-10-23 | 2010-04-05 | 2010-08-30 | 2010-10-02 | 858704.64 | 2.930
3568 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PUTNAM |  | 18 | 1254110 | This project will extend the pavement life by resurfacing 2 miles of County Highway 16 in Putnam County (West-Central Illinois). | Pavement Improvement | 2010-04-07 | 2010-04-19 | 2010-05-30 | 2010-04-23 | 137702 | 1.920
3569 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE, COOK, MCHENRY |  | Multiple | 1270004 | This project will extend the pavement life by milling, patching and resurfacing 4.25 miles on Lake-cook Rd from Kane, McHenry, cook county line to Old Hart Rd in Barrington Hills (Northeastern Illinoi | Pavement Improvement | 2009-12-07 | 2010-05-03 | 2010-06-30 | 2010-08-16 | 1048072.7 | 9.060
3570 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 1299109 | This project will extend pavement life by resurfacing a section of County Highway 7 in northern Kankakee County (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-14 | 2009-09-30 | 2009-10-08 | 431841 | 6.560
3571 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1319001 | This project will extend the pavement life by 1.45 miles of resurfacing of Ballard Rd from Rand Rd easterly to Greenwood Ave in the Villages of DesPlaines, Glenview, Niles, Park Ridge, Cook County (No | Pavement Improvement | 2009-10-28 | 2010-04-19 | 2010-06-30 | 2010-11-23 | 655227.54 | 3.780
3572 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 1323114 | This project will extend the pavement life by resurfacing 7 miles of IL 115 near the city of Kankakee (East-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-06-08 | 2009-10-30 | 2009-08-07 | 1290092.37 | 9.800
3573 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1332015 | This project will extend the pavement life by resurfacing 3.27 miles of IL 43 (Oakton St) from South DesPlaines Road to US 14 (Caldwell Ave) in Park Ridge & Niles in Cook County. (Northeastern Illinoi | Pavement Improvement | 2009-06-01 | 2009-06-11 | 2009-11-30 | 2009-11-14 | 3101154.93 | 3.270
3574 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1340009 | This project will extend the pavement life by resurfacing 0.8 miles of Touhy Ave from IL50 to US41 and from Lawndale Ave to Kimball Ave in Village of Lincolnwood, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-28 | 2010-06-07 | 2010-06-30 | 2010-10-23 | 623113.94 | 2.260
3575 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1363004 | This project will extend the pavement life by resurfacing 0.98 miles of Gunnison St. from IL 43 (Harlem Ave) to Nagle Ave in Chicago and the Village of Harwood Heights in Cook County (Northeastern Ill | Pavement Improvement | 2009-11-03 | 2010-04-09 | 2010-06-30 | 2010-06-17 | 802260.56 | 2.000
3576 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 1365112 | This project will extend the pavement life by resurfacing 5 miles of County Highway 33 in LaSalle County (East-Central Illinois). | Pavement Improvement | 2010-02-19 | 2010-07-19 | 2010-06-30 | 2010-08-19 | 729886 | 6.030
3577 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 1380106 | This project will extend the pavement life by providing for 3.4 miles of pavement repairs and resurfacing of Illinois Route 91 just north of Peoria (West-Central Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-17 | 2009-11-30 | 2009-10-10 | 1225314.17 | 6.980
3578 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 1395003 | This project will extend the pavement life by resurfacing 1.40 miles of Chicago Avenue from Lake St to Thatcher Rd in Melrose Park & Maywood in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-04 | 2009-08-30 | 2009-07-20 | 718415.48 | 1.470
3579 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 1458103 | This project will extend the pavement life by resurfacing a section of County Highway 6 near the City of Canton, approximately 25 miles southwest of Peoria (West-Central Illinois) | Pavement Improvement | 2010-02-19 | 2010-04-27 | 2010-07-30 | 2010-09-07 | 488725 | 2.000
3580 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 1459004 | This project will extend the pavement life by resurfacing 2.95 miles of 26th Street from IL 43 to IL 50 in Berwyn & Cicero in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-18 | 2009-09-30 | 2009-08-31 | 1271977.9 | 3.110
3581 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 1464103 | This project wil extend the pavement life by providing for 0.41 mile of pavement removal and resurfacing on Locast Street in Delavan, south of Peoria (West-Central Illinois). | Pavement Improvement | 2009-09-14 | 2010-07-06 | 2009-09-30 | 2010-07-08 | 125000 | 0.680
3582 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 1467006 | This project will extend the pavement life by milling, patching and resurfacing 0.55 miles on 31st Street from IL 171 to DesPlaines Avenue and also on 31st St. from Golfview Rd to IL 171 in the Villag | Pavement Improvement | 2009-04-28 | 2009-05-25 | 2009-07-30 | 2009-06-29 | 254965.07 | 0.620
3583 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1467007 | This project will extend the pavement life by milling, patching and resurfacing 3.61 miles of 31st St from Wolf Rd to IL 171 in the Villages of Westchester, Brookfield, LaGrange Park. (Northeastern I | Pavement Improvement | 2009-09-09 | 2009-11-07 | 2010-07-30 | 2010-07-03 | 1888752.09 | 7.380
3584 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 1488004 | This project will extend the pavement life with 2.58 miles of milling, resurfacing, patching, curb & gutter, pavement marking & detector loops on 47th St from DuPage County line to East Ave, Cook Coun | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-08-30 | 2010-10-21 | 1442223.12 | 6.060
3585 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 1527012 | This project will substantially improve the roadway network by constructing four new bridges and rehabilitation of an existing bridge. Two of the new bridges are located at IL Rt 25/Dunham and IL Rt 2 | New Construction | 2009-07-27 | 2009-08-18 | 2011-05-30 | 2011-10-22 | 1100000 | 0.000
3586 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1566002 | This project will extend the life of the pavement by surface removal, pavement patching, guardrail removal and replacement, pavement marking on 2.46 miles of 95th st from IL 171 (Archer Ave) to US 45 | Pavement Improvement | 2009-05-06 | 2009-05-18 | 2009-08-30 | 2009-07-03 | 780486.71 | 2.540
3587 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | BROWN |  | 18 | 1583103 | This project will substantially improve the roadway by constructing a new bridge over Logan Creek on County Highway 3A near Ripley (West-Central Illinois). | Bridge Improvement | 2010-07-30 | 2010-10-04 | 2011-05-30 | 2011-05-19 | 188402 | 0.010
3588 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MASON |  | 18 | 1595103 | FAS 1595 (CH 19) - 4 miles southwest of Mason City at Sleepy Hollow Ditch-Bridge replacement. PE - Phase I | Other | 2009-11-06 | 2009-11-06 | 2010-07-30 | 2011-10-01 | 26681 | 0.010
3589 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 1614104 | This project will extend the pavement life by resurfacing a portion of County Highway 32 in Morgan County and adding lighting at an intersection for a safety improvement near Jacksonville (West-Centra | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-11-30 | 2010-05-07 | 328970 | 3.890
3590 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 1618001 | This project will extend the life of the pavement by resurfacing 0.72 miles of 175th Street from Governor's Highway to the intersection of 175th Street and Dixie Hwy in the Village of Homewood in Cook | Pavement Improvement | 2009-05-06 | 2009-07-15 | 2009-08-30 | 2009-09-12 | 240159.29 | 0.750
3591 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CLARK |  | 15 | 1660105 | This project will substantially improve the roadway by reconstructing a new structure over Hawks Creek one mile west of Dennison in Clark County (Southeast Illinois) | Bridge Improvement | 2010-04-27 | 2010-06-07 | 2010-07-30 | 2010-08-30 | 349298 | 0.020
3592 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | 17 | 1721002 | This project will extend the pavement life by patching and resurfacing a portion Interstate 172 around Quincy, Illinois (West-Central Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-12 | 2010-08-30 |  | 14584587.03 | 9.410
3593 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CLINTON |  | 19 | 1784105 | This project will extend the pavement life by milling, patching and resurfacing 5.5 miles of County Highway 5 near Centralia, Illinois (Southwest Illinios). | Pavement Improvement | 2009-08-12 | 2009-10-01 | 2009-12-30 | 2009-12-04 | 70000 | 11.040
3594 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 1790103 | This project will extend the pavement life by milling, patching and resurfacing County Highway 32 from Jefferson Road to I-57 in Marion County, Illinois (Southwest Illinios). | Pavement Improvement | 2009-08-05 | 2009-08-17 | 2009-10-30 | 2009-10-14 | 367987 | 4.530
3595 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WABASH |  | 15 | 1819107 | This project will extend the pavement life by resurfacing a portion of Goodson Orchard Road in Wabash County (Southeast Illinois). | Pavement Improvement | 2010-01-04 | 2010-04-14 | 2010-06-30 | 2010-05-14 | 147866 | 3.250
3596 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MONROE |  | 12 | 1858103 | This project will extend the pavement life by providing a surface treatment on 2.18 miles of County Highway 12 from IL156 to County Highway 6 near Valmeyer, Illinois (Southwest Illinois) | Pavement Improvement | 2009-08-25 | 2009-08-31 | 2009-09-30 | 2009-10-16 | 149789 | 4.180
3597 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | RANDOLPH |  | 12 | 1870108 | This project will extend the pavement life by resurfacing Wine Hill Road from Welge Road to County Highway 5 near Steelville, Illinois (Southwest Illinois). | Pavement Improvement | 2009-12-14 | 2010-05-03 | 2010-06-30 | 2010-07-14 | 405449 | 2.920
3598 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 1881114 | This project will extend the pavement life by resurfacing approximately 3.75 miles of Park Street Road in Franklin County.(Southern Illinois) | Pavement Improvement | 2010-02-22 | 2010-05-01 | 2010-06-30 | 2010-08-04 | 352969 | 3.720
3599 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 1887106 | This project will extend the pavement life by resurfacing Saraville Road from Crab Orchard road to Ewing Road in Williamson County, Illinois (Southern Illinois). | Pavement Improvement | 2009-12-17 | 2010-04-01 | 2010-06-30 | 2010-05-14 | 373706.16 | 2.800
3600 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 1908001 | This project will extend the pavement life by milling, patching and resurfacing 7.8 miles of IL 151 in Jackson County, Illinois (Southern Illinios). | Pavement Improvement | 2009-04-28 | 2009-05-12 | 2009-10-30 | 2009-08-21 | 2103336.12 | 7.840
3601 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | POPE |  | 19 | 1930119 | This project will extend the pavement life by resurfacing Bay City Road from IL Route 146 south for 4.3 miles in Pope County (Southern Illinois). | Pavement Improvement | 2010-04-12 | 2010-05-10 | 2010-06-30 | 2010-06-23 | 180207 | 4.000
3602 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 2051001 | This project will extend the pavement life by resurfacing 3 miles of Winneshiek Road in Stephenson County (Northwest Illinois). | Pavement Improvement | 2010-03-08 | 2010-06-22 | 2010-05-30 | 2010-07-13 | 393026 | 3.170
3603 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 2356003 | This project will extend the pavement life by resurfacing, improving storm sewers and traffic signals on Sheridan Road from Burnham Place to Chicago Ave in the City of Evanston, Illinois (Northeaster | Pavement Improvement | 2010-08-13 | 2010-08-23 | 2011-06-30 | 2011-08-24 | 202807 | 0.810
3604 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MARSHALL |  | 18 | 2370114 | This project will extend the pavement life by providing for 7.0 miles of removal and replacement of roadway surface on IL Route 26 near the City of Lacon which is approximately 25 miles north of the C | Pavement Improvement | 2009-04-28 | 2009-05-08 | 2009-08-30 | 2009-07-10 | 1388345.16 | 7.010
3605 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | Multiple | 2592102 | This project will extend the pavement life by resurfacing six miles of Adams County Highway near Loraine (West-Central Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-24 | 2009-10-30 | 2009-09-17 | 527967 | 12.000
3606 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 2612002 | This project will extend the bridge life by adding a new deck overlay, new joints, repairing the backwall of the north abutment and making other roadway improvements on Lemont Road over Des Plaines Ri | Bridge Improvement | 2009-04-28 | 2009-05-28 | 2010-01-30 | 2010-01-30 | 4556823.83 | 0.010
3607 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MOULTRIE |  | 15 | 2660101 | This project will substantially improve the roadway by reconstructing a section of County Highway 19 near Sullivan in Moultrie County (Southeast Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-16 | 2009-10-30 | 2009-10-06 | 262058 | 2.540
3608 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2697005 | This project will extend the bridge life by bridge deck patching and overlay on Willow Springs Road over the DesPlaines River and I&M Canal in the Village of Willow Springs in Cook County. (Northeaste | Bridge Improvement | 2009-06-01 | 2009-06-15 | 2009-11-30 | 2010-10-23 | 4877955.21 | 0.010
3609 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 2706103 | This project will extend the pavement life by milling, patching and resurfacing 1.63 miles on IL Rt 43 (Waukegan Rd) from IL Rt 60 to Gage Lane in the Villages of Lake Forest and Lake Bluff (Northeast | Pavement Improvement | 2009-10-23 | 2010-04-13 | 2010-07-30 | 2010-07-12 | 932171.28 | 3.300
3610 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 2711016 | This project will extend the pavement life by resurfacing 3.24 miles on IL Rt 131 from IL Rt 120 to just south of IL Rt 137 in the City of North Chicago (Northeastern Illinois) | Pavement Improvement | 2009-05-06 | 2009-05-18 | 2009-09-30 | 2009-09-16 | 2699345.33 | 3.090
3611 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 2714010 | This project will extend the pavement life by resurfacing 0.55 miles of 25th Avenue from Belmont Ave to Addison Street in the Village of Franklin Park in Cook County. (Northeasern Illinois). | Pavement Improvement | 2009-06-01 | 2009-10-13 | 2009-08-30 | 2009-12-04 | 404669.38 | 0.500
3612 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2719001 | This project will extend the pavement life by milling, patching and resurfacing 0.74 miles of East Avenue between 47th and 55th Streets in Summit (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-25 | 2009-09-30 | 2009-08-29 | 347208.07 | 1.000
3613 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACOUPIN |  | 17 | 2729105 | This project will extend the pavement life by resurfacing and other improvements on County Highway 3 at IL Route 4 east in Macoupin County (West-Central Illinois). | Pavement Improvement | 2010-04-12 | 2010-05-17 | 2011-08-30 | 2011-10-19 | 598281 | 4.480
3614 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 2759003 | This project will extend the pavement life by resurfacing 1.29 miles of DesPlaines Avenue from Randolph Street to Roosevelt Road in Forrest Park in Cook Co. (Northeastern Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-04 | 2009-09-30 | 2009-07-10 | 919906.65 | 1.340
3615 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2759004 | This project will extend pavement life by resurfacing 1.038 miles of Des Plaines Avenue from Roosevelt Road to Cermak Road within the Village of Forest Park in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-28 | 2010-04-15 | 2010-06-30 | 2010-05-28 | 640186.16 | 2.140
3616 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 2806050 | Struct repl/rehab or deck repl from Miss. River to Airport Rd in Milan. Section 81-1(B-1,HB,HB-1,HB-2,VB,VB1)R | Pavement Improvement | 2011-02-24 | 2011-03-21 | 2012-11-30 |  | 174438 | 0.010
3617 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WAYNE |  | 19 | 2821108 | This project will substantially improve the roadway by replacing the bridge over Martin Creek on County Highway 7 near Geff in Wayne County (Southeast Illinois) | Bridge Improvement | 2010-03-15 | 2010-04-06 | 2010-07-30 | 2010-08-22 | 344768.38 | 0.010
3618 | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 2831002 | This project will extend the bridge life by making full depth deck repairs, structural repairs, deck overlay, and other roadway improvements to the Kedzie Avenue bridge over the Cal-Sag Channel in Rob | Bridge Improvement | 2009-10-23 | 2010-03-22 | 2010-08-30 |  | 1315670.06 | 0.030
3619 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 2843006 | This project will extend the life of the pavement by resurfacing 1.07 miles of Dixie Highway just north of 183rd Street to Governor's Highway in Village of Homewood, Cook County (Northeastern Illinois | Pavement Improvement | 2009-06-02 | 2009-07-02 | 2009-10-30 | 2009-10-14 | 485050.98 | 1.080
3620 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 2907002 | This project will extend the pavement life by resurfacing 1.15 miles of State Street from 60th Street to 69th Street within the City of Chicago in Cook County. (Northeastern, Illinois). | Pavement Improvement | 2009-10-16 | 2010-04-12 | 2010-07-30 | 2011-04-23 | 1074300 | 1.440
3621 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 2943016 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements to the Burnham Avenue bridge over State Street, Indiana Harbor Beltway and CSX Railroad and | Bridge Improvement | 2009-05-04 | 2009-05-06 | 2009-10-30 | 2010-08-12 | 5630247.1 | 0.010
3622 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 3033001 | This project will provide for pedestrian & bicyclist safety by constructing the DuPage River Bike & Pedestrian Trail from IL Route 59 & Riverview Park to the Prairie Creek Development in the Plainfiel | Transportation Enhancements | 2010-06-01 | 2010-06-01 | 2010-10-30 |  | 1574949 | 0.000
3623 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 3523006 | This project will extend the pavement life by milling, patching and resurfacing 2.6 miles on US 12 from 3rd Avenue to US 12/45 and along Rand Rd from Des Plaines River Road to Lundgren Ave in Des Plai | Pavement Improvement | 2009-06-02 | 2009-06-13 | 2009-10-30 | 2009-11-06 | 1927842.05 | 2.220
3624 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 3592005 | This project will extend the pavement life by milling, patching and resurfacing 0.94 mile of Brainard Avenue from Burnham Ave to the Indiana State line in the Village of Burnham in Cook County. (North | Pavement Improvement | 2009-06-01 | 2009-06-23 | 2009-09-30 | 2010-10-27 | 365144.42 | 1.080
3625 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 4068002 | This project will extend the pavement life by resurfacing various roads in the village of Manteno (East-Central Illinois). | Pavement Improvement | 2010-05-20 | 2010-09-27 | 2010-10-30 | 2011-09-09 | 246398 | 0.350
3626 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 4097005 | Transportation enhancement and road improvements necessary for Downtown Plaza improvements in Jacksonville, IL * | Transportation Enhancements | 2010-03-15 | 2010-03-16 | 2011-05-30 |  | 1413770 | 0.000
3627 | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACOUPIN |  | 17 | 5001003 | This project will substantially improve the roadway by reconstructing a section of Main Street by providing new concrete pavement and other roadway improvements in Staunton (West-Central Illinois) | Pavement Improvement | 2010-12-13 | 2011-03-14 | 2010-11-30 |  | 25160 | 0.190
3628 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CASS |  | 18 | 5002021 | This project will extend the pavement life by resurfacing a portion of Cass County Highway 7 from western edge of Beardstown for five miles to the west (West-Central Illinois). | Pavement Improvement | 2009-09-15 | 2009-10-19 | 2009-11-30 | 2010-07-09 | 170449 | 1.460
3629 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | BOONE |  | 16 | 5004010 | This project will extend the pavement life by resurfacing a section of Newburg Road and other roadway improvements in the city of Belvidere (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-23 | 2009-11-30 | 2010-05-20 | 500000 | 5.600
3630 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 5005011 | This project will substantially improve the roadway by reconstructing a section of North DuQuoin Street by providing new concrete pavement and other roadway improvements from McFall St. to the Interst | Pavement Improvement | 2010-04-12 | 2010-05-03 | 2011-05-30 | 2010-10-27 | 229732 | 0.720
3631 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 5007022 | This project will extend the pavement life by providing for pavement repairs and resurfacing on Elm Street and Walnut Street in the City of Canton, approximately 25 miles southwest of Peoria (West-Cen | Pavement Improvement | 2009-09-08 | 2009-09-18 | 2009-10-30 | 2010-08-23 | 257027 | 2.250
3632 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 5007023 | This project will provide for pedestrian safety by constructing 6 blocks of new concrete sidewalk along the north side of Ash Street in the City of Canton, approximately 25 miles southwest of Peoria ( | Safety/Traffic Management | 2009-09-22 | 2009-09-22 | 2009-12-30 | 2010-08-30 | 200586 | 1.720
3633 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 5008024 | This project will substantially improve mobility by constructing the missing section that connects Marion Street together by providing new concrete pavement, curb and gutter and sidewalk in the city o | New Construction | 2009-09-10 | 2009-09-23 | 2010-08-30 | 2010-06-02 | 370215.46 | 0.000
3634 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 5008025 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Carbondale, Illinois (Southern Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-03 | 2009-10-30 | 2009-10-28 | 400271.25 | 1.010
3635 | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACOUPIN |  | 17 | 5009005 | This project will extend the pavement life by widening and resurfacing North Broad Street from Haig St. to Shad Rd. in the Carlinville (West-Central Illinois). | Pavement Improvement | 2010-08-19 | 2011-05-11 | 2010-08-30 |  | 183150 | 1.550
3636 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WHITE |  | 15 | 5010010 | This project will extend the pavement life by resurfacing numerous roadway sections in the village of Carmi, Illinois (Southern Illinois). | Pavement Improvement | 2009-10-27 | 2010-05-10 | 2009-12-30 | 2010-07-19 | 160359.29 | 0.740
3637 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011263 | This project will extend the pavement life by resurfacing and repair broken curb and gutter on Lindenthal Ave. from Washington st. to Poplar St. in the City of Highland, IL (Southwest Illinois). | Pavement Improvement | 2009-08-03 | 2009-08-24 | 2009-09-30 | 2009-09-14 | 152387.23 | 0.440
3638 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011267 | Preliminary engineering for the milling and resurfacing of Madison Ave. in Edwardsville. Section 09-00099-00-RS | Other | 2009-06-18 | 2009-06-22 | 2010-04-30 | 2010-04-01 | 33987.55 | 2.000
3639 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011268 | This project consists of milling and resurfacing along Madison Avenue in Edwardsville, Illinois (Southwest Illinois). Other improvements include constructing curbs, sidewalks, and ramps compliant wit | Pavement Improvement | 2010-01-11 | 2010-06-07 | 2011-12-30 | 2010-10-07 | 254182 | 0.510
3640 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011269 | This project consists of patching, resurfacing, and widening of Fosterburg Road in Alton, Illinois (Southwest Illinois) Additionally, the construction of a culvert will improve roadway drainage. | Pavement Improvement | 2010-03-01 | 2010-03-26 | 2010-08-30 | 2010-12-03 | 368968.07 | 0.500
3641 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011270 | This project will extend the pavement life by milling, patching and resurfacing .25 miles of Ostle Dr. from Newport Dr. to Waverly Dr. in Collinsville, Illinois (Southwest Illinios). | Pavement Improvement | 2009-09-23 | 2009-09-23 | 2010-05-30 | 2010-06-29 | 165000 | 0.270
3642 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011271 | This project will extend the pavement life by milling, patching and resurfacing Main St. from Shamrock Ave. to Lakeside Ave. in the city of East Alton, Illinois (Southwest Illinios). | Pavement Improvement | 2009-11-23 | 2009-12-21 | 2010-06-30 | 2010-08-11 | 350662 | 0.500
3643 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011272 | This project will improve driving quality by resurfacing and upgrading pavement markings along Glen Carbon Road in the Village of Glen Carbon, Illinois (Southwest Illinois). | Pavement Improvement | 2010-04-27 | 2010-04-27 | 2010-06-30 | 2010-09-13 | 257920 | 1.050
3644 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011274 | This project will extend the pavement life by resurfacing Maryville Road from St. Clair Ave. to Terminal Ave. in Granite City, Illinois (Southwest Illinois). | Pavement Improvement | 2009-12-29 | 2010-07-05 | 2011-12-30 | 2010-09-27 | 373029.76 | 0.460
3645 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011275 | This project will enhance pedestrian safety by constructing a 10 wide pedestrian walkway with concrete barrier on Ohio Ave. from IL Route 203 to Old Madison Road in the City of Madision, St. Clair Cou | Safety/Traffic Management | 2010-05-03 | 2010-05-10 | 2010-06-30 | 2010-06-24 | 140238 | 0.180
3646 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011276 | Preliminary engineering for the resurfacing of West Main Street (Glen Carbonn Road) in the village of Glen Carbon. Section 09-00018-01-RS | Other | 2009-06-18 | 2009-06-22 | 2009-10-30 | 2010-10-31 | 26905 | 2.000
3647 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011277 | Project consists of concrete pavement widening, construction of concrete curb and gutter and installation of storm sewer along Frank Scott Parkway West from Belleville West Parkway to Concordia Church | Pavement Improvement | 2009-09-10 | 2009-09-21 | 2010-05-30 | 2010-04-30 | 655297 | 4.120
3648 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011278 | This project will extend the pavement life by milling, patching and resurfacing Broadway Ave. from Klein Ave. to State Street in city of Venice (Southwest Illinois). | Pavement Improvement | 2010-05-03 | 2010-05-12 | 2010-06-30 | 2010-07-24 | 312916.77 | 0.600
3649 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011279 | Construct new sidewalk, Replace broken sidewalk and upgrade sidewalk/street crossings to accommodate those with disabilities along Monroe St. from St. Louis St. to Marner Park in the city of Lebanon, | Safety/Traffic Management | 2009-09-14 | 2009-10-05 | 2010-04-30 | 2010-04-15 | 282000 | 1.470
3650 | Completed | C250,C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011280 | This project will extend the pavement life by milling, patching and resurfacing of 9th street from Airline Drive to north of Old Edwardsville Road in the city of Wood River, IL (Southwest Illinois). | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-06-30 | 2010-05-25 | 244542 | 1.430
3651 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011284 | This project will substantially improve the roadway by reconstructing a section of North DuQuoin Street by providing new concrete pavement and other roadway improvements from McFall St. to the Interst | Pavement Improvement | 2010-05-25 | 2010-08-02 | 2011-12-30 |  | 303966 | 0.130
3652 | Completed | C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | MONROE | ST. LOUIS (MO)-IL | 12 | 5011285 | This project consists of patching and resurfacing 0.35 miles of Palmer Road in the City of Columbia, Illinois (Southwest Illinois). Additionally, wider shoulders will improve safety. | Pavement Improvement | 2010-03-02 | 2010-05-24 | 2010-06-30 | 2010-08-02 | 233597 | 0.460
3653 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MONROE | ST. LOUIS (MO)-IL | 12 | 5011286 | This roadway widening project includes 0.27 miles of resurfacing and the addition of a new right turn lane from Maeystown Road onto IL 156 in Waterloo, Illinois (Southwest Illinois) Additionally, new | Pavement Improvement | 2010-03-02 | 2010-04-26 | 2010-06-30 | 2010-07-28 | 220000 | 0.260
3654 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011287 | This project will extend the pavement life by milling, patching and resurfacing 1.36 miles of Doris Ave. from Range Lane to Jerome Lane in the city of Cahokia, IL (Southwest Illinois). | Pavement Improvement | 2010-03-18 | 2010-03-18 | 2010-07-30 | 2010-07-14 | 327200 | 1.400
3655 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011290 | This project will extend the pavement life by milling, patching and resurfacing Pontoon Rd from Breckenridge Ln. to IL111 in Pontoon Beach, Illinois(Southwest Illinios). | Pavement Improvement | 2009-08-25 | 2009-08-25 | 2010-05-30 | 2010-05-10 | 243795 | 1.550
3656 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011291 | This project will improve safety by providing pedestrians a signal to stop traffic and safely cross Monroe St. in the city of Lebenon. (Southwest Illinois) | Safety/Traffic Management | 2010-04-23 | 2010-04-23 | 2010-05-30 | 2010-10-22 | 44832 | 0.010
3657 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011292 | This project will extend the pavement life by milling, patching and resurfacing .44 miles of Frontage Road from Harvestyme Lane to clara Dr. in Troy, Illinois (Northwest Illinios). | Pavement Improvement | 2009-10-29 | 2010-01-26 | 2010-05-30 | 2010-06-08 | 86566 | 0.540
3658 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011293 | This project will extend the pavement life by resurfacing 6th street from IL 143 to Rohm Place in the city of Wood River, Illinois(Southwest Illinois). | Pavement Improvement | 2009-12-22 | 2010-03-23 | 2010-05-30 | 2010-06-04 | 225386 | 0.590
3659 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011294 | This project will extend the pavement life by resurfacing, replace broken curb and gutter and sidewalks on Church Road from IL Route 157 to 50th St. in Centreville, IL (Southwest Illinois) . | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-08-30 |  | 446797 | 1.240
3660 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011295 | This project will extend the pavement life by milling, patching and resurfacing of 17th street from Russell Ave. to East Broadway Ave. in the city of East St. Louis (Southwest Illinois). | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-07-30 | 2010-08-17 | 441427 | 0.780
3661 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011296 | This project consists of milling and resurfacing on a section of Union Hill Road in the City of Fairview Heights, Illinois (Southwest Illinois). Other improvements include constructing new sidewalks | Pavement Improvement | 2010-03-01 | 2010-03-08 | 2010-07-30 | 2010-08-10 | 307200 | 0.440
3662 | Completed | C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011297 | This project will substantially improve the roadway by reconstructing a section of Concordia Church Road from IL route 158 to Frank Scott Parkway by providing new full depth bituminous pavement and ot | Pavement Improvement | 2010-06-30 | 2010-07-12 | 2010-11-30 | 2011-09-08 | 1264080 | 0.930
3663 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011299 | This project enhances the aesthetics of the roadway by planting trees along Governors Parkway from Troy road to IL route 143 in Madison County (Southwest Illinois). | Transportation Enhancements | 2010-08-05 | 2010-11-08 | 2010-05-30 | 2010-11-12 | 32320 | 2.670
3664 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011300 | This project enhances the aesthetics of th eroadway by planting trees along IL Route 3 from Rock Road to 20th Street in Granite City, Madison County (Southwest Illinois). | Transportation Enhancements | 2010-05-18 | 2010-11-01 | 2010-05-30 | 2010-11-03 | 19640 | 0.660
3665 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011324 | Resurfacing of State St., curb and gutter repair, sidewalk repair from 14th St. to Broadway Ave. | Pavement Improvement | 2010-08-05 | 2010-11-01 | 2010-12-30 | 2011-08-30 | 532910 | 1.050
3666 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5012017 | This project will extend the pavement life by resurfacing Brookside Ave. from 15th street to 17th street in Wamac, Illinois (Southwest Illinois). | Pavement Improvement | 2009-11-18 | 2010-04-19 | 2010-05-30 | 2010-04-30 | 41880 | 0.130
3667 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5012018 | Replace broken sidewalk and upgrade sidewalk/street crossings to accommodate those with disabilities at various locations along US Route 51 between Mcbriarty st. and Pearct St in Central City, Illinoi | Safety/Traffic Management | 2010-03-10 | 2010-04-04 | 2010-06-30 | 2010-04-27 | 41370 | 1.540
3668 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5012019 | This project will extend the pavement life by milling, patching and resurfacing various streets in the City of Centralia, Illinois (Southwest Illinois). | Pavement Improvement | 2010-05-07 | 2010-05-03 | 2010-07-30 | 2010-07-30 | 427484 | 1.110
3669 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 5013016 | This project will extend the pavement life by resurfacing numerous roadway sections in the City of Charleston (Southeast Illinois). | Pavement Improvement | 2009-09-10 | 2009-10-21 | 2009-11-30 | 2009-11-17 | 340000 | 0.000
3670 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 5013017 | This project will extend the pavement life by resurfacing numerous roadway sections in Charleston, Coles County (Southeast Illinois). | Pavement Improvement | 2010-06-29 | 2010-08-05 | 2010-06-30 | 2010-10-01 | 319711 | 1.350
3671 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | RANDOLPH |  | 12 | 5014009 | This project will extend the pavement life by resurfacing numerous roadway sections in the City of Chester, Illinois (Southwest Illinois). | Pavement Improvement | 2010-01-13 | 2010-04-28 | 2010-05-30 | 2010-06-09 | 253416 | 0.730
3672 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE WITT |  | 15 | 5015004 | This project will extend the pavement life by resurfacing 5 blocks of Washington Street in Clinton, approximately 25 miles south of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2010-08-30 | 2010-08-18 | 188678.99 | 0.310
3673 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 5016037 | This project will extend the pavement life by resurfacing a section of Denmark Road in Danville, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-10 | 2010-03-30 | 2010-07-30 | 2010-05-18 | 700000 | 2.880
3674 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 5016038 | This project will substantially improve Voorhees Street by constructing a new bridge over the CSX railroad and providing 0.8 mile of resurfacing in Danville, approximately 30 miles east of Champaign ( | Pavement Improvement | 2009-12-14 | 2010-04-05 | 2010-10-30 | 2010-11-18 | 700000 | 1.000
3675 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 5016039 | This project will extend the pavement life by resurfacing 0.8 mile of Main Street in Westville, approximately 35 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2010-01-08 | 2010-04-19 | 2010-06-30 | 2010-06-18 | 217531 | 0.990
3676 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5017040 | This project will extend the pavement life by resurfacing a section of Fairview Drive in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 2009-08-12 | 2009-09-03 | 2009-10-30 | 2009-10-03 | 565839.09 | 2.920
3677 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5017041 | This project will substantially improve the roadway by reconstructing the intersection of Plank Road and Lindgren Road in the city of Sycamore (East-Central Illinois). | Pavement Improvement | 2010-03-19 | 2010-04-19 | 2011-12-30 | 2011-09-30 | 472000 | 0.200
3678 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5017042 | This project will substantially improve the roadway by constructing a new intersection at Dresser Road and Normal Road in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 2010-03-19 | 2010-04-19 | 2010-08-30 | 2010-08-27 | 438589 | 0.010
3679 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 5018015 | This project will substantially improve the roadway by reconstructing a section of Hennepin Avenue by providing new concrete intersections, pavement and other roadway improvements in Dixon (Northwest | Pavement Improvement | 2010-02-24 | 2010-04-28 | 2010-09-30 | 2010-10-01 | 482180 | 0.200
3680 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PERRY |  | 12 | 5019007 | This project will extend the pavement life by milling, patching and resurfacing 0.55 miles of Cole Street from Division St. to Line St. in the city of DuQuoin, Illinois (Southern Illinois). | Pavement Improvement | 2009-10-22 | 2009-11-16 | 2010-12-30 | 2009-12-17 | 196971.02 | 0.520
3681 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | EFFINGHAM |  | 19 | 5021025 | This project will substantially improve the roadway by constructing a section of Veterans Drive by providing new concrete pavement in Effingham (Southeast Illinois). | Pavement Improvement | 2009-12-17 | 2010-03-08 | 2010-09-30 | 2010-10-16 | 374589 | 0.100
3682 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WAYNE |  | 19 | 5022012 | This project will substantially improve the roadway by constructing a new box culvert over a branch of Pond Creek on East 4th Street in Fairfield, Wayne County (Southeast Illinois). | Bridge Replacement | 2010-05-19 | 2010-06-03 | 2010-08-30 | 2010-09-01 | 163973 | 0.010
3683 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CLAY |  | 19 | 5023010 | This project will substantially improve the roadway by reconstructing a section of Worthey Steet by providing new concrete pavement and other roadway improvements in Flora, Clay County (Southeast Ill | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-09-30 | 2010-08-20 | 153840 | 0.250
3684 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 5024026 | This project will extend the pavement life and complete other roadway improvements by resurfacing and sidewalk improvements to numerous sections of streets in the city of Freeport (Northwest Illinois) | Pavement Improvement | 2009-10-07 | 2009-10-13 | 2010-06-30 | 2010-07-07 | 735900 | 3.200
3685 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 5024027 | This project will extend the pavement life by resurfacing Lincoln Boulevard from Whistler Avenue to Saxby Avenue in the city of Freeport (Northwest Illinois). | Pavement Improvement | 2010-09-16 | 2010-09-22 | 2010-10-30 | 2010-10-13 | 39065 | 0.430
3686 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 17 | 5025043 | This project will substantially improve the roadway by reconstructing and providing additional roadway improvements for a 1/4 mile section of Carl Sandburg Drive in the City of Galesburg (West-Central | Pavement Improvement | 2009-07-27 | 2009-07-30 | 2009-10-30 | 2009-09-01 | 249851.17 | 0.720
3687 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 17 | 5025044 | This project will improve a section of Knox Street by providing a new surface, sidewalks, and drainage improvements in the City of Galesburg (West-Central Illinois) | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2009-11-30 | 2009-10-16 | 471930.71 | 1.340
3688 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 17 | 5025046 | This project will improve a 1/2 mile section of South Seminary Street by providing a new surface, sidewalks, and drainage improvements in the City of Galesburg (West-Central Illinois) | Pavement Improvement | 2009-10-20 | 2009-10-30 | 2010-05-30 | 2010-04-30 | 279099 | 1.020
3689 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 17 | 5025047 | This project will substantially improve the roadway by reconstructing 0.25 miles of State Street in the City of Galesburg, Knox County (West-Central Illinois). | Pavement Improvement | 2010-02-24 | 2010-02-19 | 2010-06-30 | 2010-05-23 | 44000 | 0.010
3690 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 5026011 | This project will extend the pavement life by providing a surface treatment on numerous roadway sections in the city of Geneseo (Northwest Illinois). | Pavement Improvement | 2009-08-27 | 2010-05-03 | 2010-05-30 | 2010-05-27 | 186759.61 | 0.000
3691 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 5027012 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Harrisburg. (Southern Illinois) | Pavement Improvement | 2010-03-01 | 2010-04-27 | 2010-06-30 | 2010-06-07 | 298243 | 0.450
3692 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 5029010 | This project will extend the pavement life by milling, patching and resurfacing East Herrin Street from IL route 148 to 5th street in the city of Herrin (Southern Illinois). | Pavement Improvement | 2010-08-15 | 2010-09-01 | 2010-06-30 | 2010-10-22 | 335665 | 0.620
3693 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 5029011 | This project consists of improving safety by upgrading traffic signs to current standard throughout the village of Energy, Illinois (Southern Illinois). | Safety/Traffic Management | 2009-11-13 | 2009-11-13 | 2010-10-30 | 2010-03-01 | 20614 | 0.000
3694 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 5031008 | This project will extend the pavement life by resurfacing 0.8 mile of North Market Street in Hoopeston, approximately 50 miles northeast of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-28 | 2010-04-05 | 2010-09-30 | 2010-08-03 | 180428 | 0.870
3695 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 5032028 | This project will extend the pavement life by resurfacing a portion of the Village of South Jacksonville's East Vandalia Road (West-Central Illinois). | Pavement Improvement | 2009-09-10 | 2009-10-27 | 2010-07-30 | 2010-04-22 | 105111 | 0.880
3696 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 5032029 | This project will extend the pavement life by resurfacing and other improvements on Lafayette Street in Jacksonville, Morgan County (West-Central Illinois). | Pavement Improvement | 2010-04-12 | 2010-05-10 | 2010-07-30 | 2010-07-26 | 603111 | 0.900
3697 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JERSEY |  | 19 | 5033009 | – This project will provide for pedestrian accommodations by constructing a sidewalk along Fairgrounds Ave. from Cemetery Road to June Street and along June Street from Fairgrounds Ave. to East Carpen | Safety/Traffic Management | 2010-04-29 | 2010-06-24 | 2010-07-30 | 2011-04-08 | 194560 | 1.040
3698 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5036025 | This project will extend the pavement life by resurfacing a section of Richard Moyle Sr. Highway in the city of Oglesby (East-Central Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2009-09-30 | 2009-10-12 | 110314 | 2.060
3699 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5036026 | This project will extend the pavement life and improve pedestrian safety by resurfacing and reconstructing sidewalks for numerous roadway sections in the city of Peru (East-Central Illinois). | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-12-30 | 2010-06-29 | 256514.01 | 1.660
3700 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5036027 | This project will extend the pavement life by resurfacing various streets in the city of LaSalle (East-Central Illinois). | Pavement Improvement | 2010-02-24 | 2010-04-19 | 2010-06-30 | 2010-05-12 | 292651 | 0.000
3701 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LOGAN |  | 18 | 5038013 | This project will extend the pavement life by resurfacing College Street from 8th to 11th and State St. from Kickapoo St to 4th Street in Lincoln (West-Central Illinois). | Pavement Improvement | 2010-06-01 | 2010-06-24 | 2010-07-30 | 2011-04-29 | 390507 | 1.530
3702 | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LOGAN |  | 18 | 5038014 | Land acquisition for an improvement to 5th street in Lincoln, Section 10-00081-01-LA | Other | 2011-11-01 | 2010-11-01 | 2010-11-30 |  | 7561.82 | 1.400
3703 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MONTGOMERY |  | 19 | 5039010 | This project will extend the pavement life by resurfacing State St from IL Route 16 to Ferdon St in Litchfield (West-Central Illinois). | Pavement Improvement | 2010-11-04 | 2011-05-04 | 2010-07-30 | 2011-08-10 | 25160 | 0.290
3704 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 5040009 | This project will substantially improve the roadway by reconstructing a section of Ward Street with new concrete pavement and other roadway improvements in the City of Macomb which is approximately 60 | Pavement Improvement | 2009-08-03 | 2009-08-19 | 2010-08-30 | 2010-10-19 | 376800 | 1.020
3705 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 5040010 | This project will substantially improve the roadway by reconstructing a section of Ward Street with new concrete pavement and other roadway improvements, including sidewalk, in the City of Macomb appr | Pavement Improvement | 2009-10-23 | 2009-11-02 | 2010-08-30 | 2010-09-03 | 229517 | 0.260
3706 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 5041022 | LAND ACQUISITION FOR THE WIDENING OF MORGAN AVE. FROM CORBON ST. TO NORTH RUSSELL ST IN MARION, SECTION 08-00105-00-FP | Other | 2009-08-26 | 2009-08-26 | 2009-10-30 | 2011-03-01 | 90000 | 0.000
3707 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 5041023 | This project will extend the pavement life by resurfacing numerous roadway sections in the City of Marion (Southern Illinois). | Pavement Improvement | 2010-08-05 | 2010-08-12 | 2010-06-30 | 2010-09-13 | 428114 | 0.000
3708 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 5042018 | This project will extend the pavement life by resurfacing numerous roadway sections and sidewalks in Mattoon, Coles County (Southeast Illinois). | Pavement Improvement | 2010-04-21 | 2010-05-26 | 2010-07-30 | 2010-07-14 | 553262 | 0.000
3709 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5044011 | This project will extend the pavement life by widening and resurfacing a section of West Main Street in the city of Mendota (East-Central Illinois). | Pavement Improvement | 2010-02-24 | 2010-03-24 | 2010-09-30 | 2010-05-20 | 219962 | 0.620
3710 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MASSAC |  | 19 | 5045008 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Metropolis, Illinois (Southern Illinois). | Pavement Improvement | 2009-09-09 | 2009-10-05 | 2009-10-30 | 2009-11-04 | 196066 | 0.000
3711 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MASSAC |  | 19 | 5045009 | This project will enhance pedestrian and bicycle accommodations by constructing a bike trail from Fort Massac State Park to Strawberry Road in Massac County (Southern Illinois). | Transportation Enhancements | 2010-04-12 | 2010-05-10 | 2012-05-30 |  | 2092088 | 0.340
3712 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WARREN |  | 17 | 5046007 | This project will extend the pavement life by resurfacing 0.60 mile of North Main Street in Monmouth, west of Galesburg (West-Central Illinois) | Pavement Improvement | 2009-09-09 | 2009-09-21 | 2009-12-30 | 2009-11-06 | 297669 | 1.100
3713 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 5047008 | This project will extend the pavement life and complete other roadway improvements by resurfacing numerous roadway sections in the city of Morris (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-28 | 2009-10-30 | 2009-10-08 | 322320.96 | 0.000
3714 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WABASH |  | 15 | 5048020 | This project will extend the pavement life by resurfacing a portion of 3rd Street in Mt. Carmel (Southeast Illinois). | Pavement Improvement | 2009-10-16 | 2009-10-26 | 2009-12-30 | 2009-11-12 | 241438 | 1.520
3715 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JEFFERSON |  | 19 | 5049023 | This project will substantially improve the roadway by reconstructing a section of North Davidson Ave from Illinois Route 15 north approx. 1 mile by providing new concrete pavement and other roadway i | Pavement Improvement | 2010-04-22 | 2010-05-22 | 2010-07-30 | 2011-06-22 | 492101 | 0.300
3716 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 5050013 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Murphysboro, Illinois (Southern Illinois). | Pavement Improvement | 2009-12-10 | 2010-03-04 | 2010-06-30 | 2010-06-04 | 262974 | 0.700
3717 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | RICHLAND |  | 19 | 5051011 | This project will substantially improve the roadway by reconstructing a section of Butler Street by providing new concrete pavement and other roadway improvements in Olney, Richland County (Southeast | Pavement Improvement | 2010-04-29 | 2010-06-15 | 2010-09-30 | 2010-10-21 | 261069 | 0.250
3718 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5052026 | This project will extend the pavement life by resurfacing various streets in the city of Ottawa (East-Central Illinois). | Pavement Improvement | 2010-02-19 | 2010-04-21 | 2010-07-30 | 2010-06-04 | 504448 | 0.000
3719 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHRISTIAN |  | 17 | 5053006 | This project will substantially improve the roadway by reconstructing a section of Chestnett Street by providing new concrete pavement and other roadway improvements in Pana (West-Central Illinois). | Pavement Improvement | 2010-06-10 | 2010-07-13 | 2010-07-30 | 2011-05-19 | 169811 | 0.170
3720 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 5053012 | This project will extend the pavement life and improve pedestrian safety by resurfacing numerous roadway sections and construction of sidewalks in the city of Kewanee (Northwest Illinois). | Pavement Improvement | 2009-10-16 | 2010-05-03 | 2010-05-30 | 2010-06-24 | 389394.12 | 1.140
3721 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | EDGAR |  | 15 | 5054008 | This project will extend the pavement life by resurfacing 1 block of Crawford Street in Paris, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2009-10-14 | 2009-10-14 | 2010-05-30 | 2010-07-06 | 51833 | 0.140
3722 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | EDGAR |  | 15 | 5054009 | This project will extend the pavement life by resurfacing 4 blocks of Wood Street and Court Street in Parkis, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-09 | 2010-04-01 | 2010-06-30 | 2011-03-04 | 195375 | 0.440
3723 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL |  | 14 | 5055001 | This project will extend pavement life by resurfacing a section of Center Street in the city of Plano (East-Central Illinois). | Pavement Improvement | 2009-10-16 | 2010-04-15 | 2010-05-30 | 2010-05-24 | 323440 | 1.210
3724 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 5056016 | This project will extend the pavement life and improve pedestrian safety by resurfacing Aurora Street and construction of sidewalks in the city of Kewanee (East-Central Illinois).” | Pavement Improvement | 2010-09-07 | 2010-09-13 | 2010-11-30 | 2010-11-15 | 125509 | 0.340
3725 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 5056017 | This project will extend pavement life by resurfacing a section of Deerfield Road in the city of Pontiac (East-Central Illinois). | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-12-30 | 2009-12-01 | 221422 | 2.020
3726 | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 5057006 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Princeton (East-Central Illinois). | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2010-07-30 | 2010-04-30 | 194608 | 0.000
3727 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | 17 | 5058030 | This project will extend the pavement life by resurfacing numerous roadway sections in Quicy in Adams County (West-Central Illinois). | Pavement Improvement | 2010-03-02 | 2010-07-06 | 2010-08-30 | 2010-11-08 | 992161.92 | 0.000
3728 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | 17 | 5058031 | This project will extend the pavement life by resurfacing Bonansinga Dr between Cedar St & Kochs Ln in Quincy (West-Central Illinois). | Pavement Improvement | 2010-08-19 | 2010-09-08 | 2010-07-30 | 2010-11-30 | 220982 | 1.320
3729 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5059013 | This project will extend the pavement life by resurfacing approximately 1.5 miles of Flessner Avenue and Pacesetter Drive in Rantoul, north of Champaign (East-Central Illinois) | Pavement Improvement | 2009-09-15 | 2009-09-15 | 2010-06-30 | 2010-05-17 | 350000 | 1.470
3730 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CRAWFORD |  | 15 | 5060008 | This project will substantially improve the roadway by constructing a section of North Allen Street by providing new concrete pavement and other roadway improvements in Robinson (Southeast Illinois). | Pavement Improvement | 2009-12-17 | 2010-04-08 | 2010-08-30 | 2010-06-30 | 206350 | 0.080
3731 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | OGLE |  | 16 | 5061013 | This project will extend the pavement life and improve pedestrian safety by resurfacing and improving sidewalk on sections of Lincoln Highway and 4th Avenue in the city of Rochelle (Northwest Illinois | Pavement Improvement | 2010-06-17 | 2010-07-26 | 2010-06-30 | 2010-10-01 | 320082 | 0.420
3732 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 17 | 5062027 | This project will extend the pavement life and improve pedestrian safety by resurfacing the roadway and replacing the sidewalk for a section of 12th Avenue in the city of Rock Falls (Northwest Illinoi | Pavement Improvement | 2010-02-24 | 2010-06-03 | 2010-08-30 | 2010-08-27 | 291000 | 0.930
3733 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 17 | 5062028 | This project will extend the pavement life by resurfacing sections of Avenue G and 16th Avenue in the city of Sterling (Northwest Illinois). | Pavement Improvement | 2010-09-02 | 2010-09-07 | 2011-05-30 | 2010-11-08 | 461802 | 1.180
3734 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5064014 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Salem, Illinois (Southwest Illinois). | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2009-09-30 | 2009-12-04 | 219353 | 0.000
3735 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5064015 | This project will extend the pavement life by resurfacing South Marion Street from East Lake street to the County Fairgrounds in the city of Salem (Southwest Illinois) | Pavement Improvement | 2010-05-04 | 2010-07-12 | 2010-05-30 | 2010-07-22 | 19877 | 0.240
3736 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 5065006 | This project will extend the pavement life and improve pedestrian safety by resurfacing and reconstructing sidewalks for a section of St. Paul Street in the city of Spring Valley (East-Central Illinoi | Pavement Improvement | 2009-07-24 | 2009-08-01 | 2009-10-30 | 2009-11-01 | 163278 | 0.380
3737 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5066014 | This project will extend the pavement life by resurfacing a section of Oakley Avenue in the city of Streator (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-10-05 | 2010-06-30 | 2010-05-25 | 437897 | 1.520
3738 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHRISTIAN |  | 19 | 5067017 | This project will extend the pavement life by resurfacing and other improvements on Spresser Street in Taylorville, Christian County (West-Central Illinois). | Pavement Improvement | 2010-04-19 | 2010-06-07 | 2010-07-30 | 2010-12-03 | 345641 | 2.280
3739 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FAYETTE |  | 19 | 5068024 | This project will substantially improve the roadway by reconstructing a section of Coles Street by providing new concrete pavement and other roadway improvements in Vandalia (Southeast Illinois). | Pavement Improvement | 2009-12-14 | 2010-04-22 | 2010-07-30 | 2010-07-16 | 210978 | 0.260
3740 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | IROQUOIS |  | 15 | 5069005 | This project will extend the pavement life and improve pedestrian safety by resurfacing the roadway and replacing the sidewalks on sections of 5th Street, 8th Street, and Elm Street in the city of Wat | Pavement Improvement | 2010-02-25 | 2010-02-25 | 2010-08-30 | 2010-05-28 | 171000 | 1.140
3741 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 5071014 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of West Frankfort. (Southern Illinois). | Pavement Improvement | 2010-02-22 | 2010-03-22 | 2010-06-30 | 2010-05-05 | 247911 | 1.190
3742 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074081 | This project will substantially improve the roadway by reconstructing a section of 30th Street in the city of Rock Island (Northwest Illinois). | Pavement Improvement | 2010-03-03 | 2010-04-22 | 2010-09-30 | 2010-09-25 | 877027 | 0.950
3743 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND |  | 17 | 5074082 | This project will extend the pavement life by resurfacing a section of First Street in the city of Coal Valley (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-28 | 2009-10-30 | 2009-11-06 | 174439 | 2.200
3744 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074083 | This project will substantially improve the roadway by reconstructing a section of 5th Avenue and other roadway improvements in the city of Moline (Northwest Illinois). | Pavement Improvement | 2010-03-01 | 2010-04-19 | 2011-05-30 | 2010-11-23 | 967284 | 0.150
3745 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074084 | This project will extend the pavement life by resurfacing a section of 12th Avenue in the city of East Moline (Northwest Illinois). | Pavement Improvement | 2010-03-03 | 2010-04-05 | 2010-07-30 | 2010-06-30 | 473631 | 1.500
3746 | Completed | C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074085 | This project will extend the pavement life by resurfacing a section of 221st Street in Rock Island County (Northwest Illinois). | Pavement Improvement | 2010-03-03 | 2010-06-24 | 2010-07-30 | 2010-08-06 | 555482 | 3.630
3747 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074086 | This project will extend the pavement life by resurfacing a section of 10th Street in the city of Silvis (Northwest Illinois). | Pavement Improvement | 2010-03-03 | 2010-04-22 | 2010-06-30 | 2010-07-15 | 351635 | 1.560
3748 | Completed | C200,C240 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5076007 | This project will extend the pavement life by resurfacing a section of Railroad Street in the city of Sandwich (East-Central Illinois). | Pavement Improvement | 2010-03-10 | 2010-08-09 | 2010-05-30 | 2010-08-19 | 158250 | 0.510
3749 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | BOND |  | 19 | 5078007 | This project will extend the pavement life by resurfacing South Fourth Street from US 40 to Franklin street in the city of Greenville (Southwest Illinois) | Pavement Improvement | 2010-06-17 | 2010-07-19 | 2010-10-30 | 2011-06-07 | 254311 | 1.010
3750 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | UNION |  | 12 | 5080004 | This project will extend the pavement life by milling, patching and resurfacing 0.7 miles ofHeacock Street in the village of Jonesboro, Illinois (Southern Illinios). | Pavement Improvement | 2009-10-22 | 2009-11-02 | 2010-12-30 | 2009-12-30 | 207003.22 | 0.730
3751 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 5082008 | LAND ACQUISITION FOR THE RECONSTRUCTION OF GORDON DRIVE FROM RAMBLEWOOD TO MAU DRIVE IN CHATHAM, SECTION 06-00028-00-WR | Other | 2009-09-29 | 2010-10-01 | 2009-11-30 | 2011-02-01 | 17981 | 0.530
3752 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 5082009 | This project will extend culvert and roadway life by extending the length of the culvert and adding an additional culvert along with drainage improvements on Gordon Drive over Grindstone Creek in Chat | Bridge Improvement | 2010-03-23 | 2010-03-23 | 2010-08-30 | 2011-01-23 | 482019 | 0.010
3753 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PERRY |  | 12 | 5084003 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Pickneyville. (Southern Illinois) | Pavement Improvement | 2010-02-22 | 2010-05-01 | 2010-06-30 | 2010-07-01 | 165274 | 0.520
3754 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PIATT |  | 15 | 5090001 | This project will extend the life of the roadway by replaceing a culvert on Buchanan Street in Monticello, Piatt County (East-Central Illinois). | Bridge Improvement | 2010-03-01 | 2010-04-19 | 2010-06-30 | 2010-05-14 | 113133.15 | 0.100
3755 | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 5092004 | This project wil substantially improve the roadway by reconstructing a section of Burns Road West in the city of Bourbonnais. | New Construction | 2009-08-04 | 2009-08-04 | 2010-07-30 |  | 1875750 | 2.020
3756 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093139 | This project consists of providing engineering design for a future highway improvement on Northmoor Road in the city of Peoria (West-Central Illinois). | Other | 2009-07-16 | 2009-07-16 | 2009-09-30 |  | 173272 | 0.000
3757 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093140 | This project will extend the pavement life by removing existing pavement and resurfacing 0.91 mile of Parkway Drive in Pekin, just south of Peoria (West-Central Illinois) | Pavement Improvement | 2009-10-28 | 2010-04-26 | 2009-12-30 | 2010-05-18 | 432276 | 2.300
3758 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093141 | This project will extend the pavement life by providing for pavement removal and resurfacing on North Main Street in Morton, just east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-10-28 | 2010-06-01 | 2010-07-30 | 2010-06-24 | 212838 | 0.620
3759 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093142 | This project will extend the pavement life by provide for pavement removal and resurfacing of a 0.51 mile section of Heading Avenue in West Peoria (West-Central Illinois) | Pavement Improvement | 2009-09-25 | 2009-09-29 | 2009-09-30 | 2009-10-10 | 60800 | 1.040
3760 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093143 | This project will extend the pavement life by resurfacing a 0.5 mile section of Garfield Avenue in Bartonville, just south of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-26 | 2010-06-30 | 2010-05-06 | 80564 | 0.490
3761 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093144 | This project will extend the pavement life by providing for 0.39 mile of pavement removal and resurfacing on North Prospect Road in Peoria (West-Central Illinois) | Pavement Improvement | 2009-09-25 | 2009-10-05 | 2009-10-30 | 2009-11-18 | 84714 | 0.940
3762 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093145 | This project will extend the pavement life by providing for 0.38 mile of pavement removal and resurfacing on Fischer Avenue just south of Peoria (West-Central Illinois) | Pavement Improvement | 2009-09-14 | 2009-09-23 | 2009-09-30 | 2009-09-30 | 69558 | 0.800
3763 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093146 | This project will extend the pavement life by providing for 0.64 mile of pavement removal and resurfacing on Highview Road in East Peoria (West-Central Illinois) | Pavement Improvement | 2009-08-04 | 2009-09-01 | 2009-09-30 | 2010-12-10 | 294083 | 1.160
3764 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093147 | This project will extend the pavement life by providing for 3 blocks of pavement repairs and resurfacing in South Pekin, just south of Peoria (West-Central Illinois) | Pavement Improvement | 2009-10-28 | 2010-04-19 | 2009-12-30 | 2010-05-15 | 103724.21 | 2.980
3765 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093148 | This project will extend the pavement life by resurfacing 1 mile of Hillcrest Drive and Wilmor Road in the City of Washington, east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-21 | 2010-05-30 | 2010-04-26 | 168113 | 1.130
3766 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093149 | This project will extend the pavement life by resurfacing 0.5 miles of Truitt Avenue in Peoria County (West-Central Illinois). | Pavement Improvement | 2010-02-19 | 2010-04-07 | 2010-06-30 | 2010-04-26 | 181366 | 0.770
3767 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093153 | This project will substantially improve the roadway by reconstructing a section of Northmoor Road by providing new pavement and other roadway improvements in Peoria (West-Central Illinois). | Pavement Improvement | 2010-03-08 | 2010-04-01 | 2010-11-30 | 2011-12-31 | 2391543 | 0.320
3768 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5094001 | This project will extend the pavement life by resurfacing numerous streets in the city of Genoa (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-28 | 2009-11-30 | 2009-10-28 | 162552 | 1.780
3769 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099087 | This project will extend the pavement life by resurfacing a section of West Riverside Boulevard in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-12-15 | 2010-05-03 | 2010-08-30 | 2010-08-20 | 385511.32 | 0.440
3770 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099088 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-10-29 | 2010-05-03 | 2010-06-30 | 2010-09-17 | 825125.28 | 2.560
3771 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099090 | This project will extend the pavement life by resurfacing a section of Mill Road in the city of Cherry Valley (Northwest Illinois). | Pavement Improvement | 2009-12-15 | 2010-05-03 | 2010-05-30 | 2010-05-07 | 48250 | 0.180
3772 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099091 | This project will widen and install traffic signals at the intersection of Ralston Road and Blue Bonnet Drive in Winnebago County (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-27 | 2010-09-30 | 2010-09-30 | 703838 | 0.010
3773 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099092 | This project will extend the pavement life by resurfacing a section of Westfield Road in the city of Winnebago (Northwest Illinois). | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-10-30 | 2009-10-30 | 66750 | 1.000
3774 | Completed | C250,C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099093 | This project will extend the pavement life by resurfacing sections of Willowbrook Road in Winnebago County (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-24 | 2009-10-30 | 2010-06-04 | 188490 | 2.000
3775 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099094 | This project will extend the pavement life by resurfacing a section of McDonald Road in the city of Roscoe (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-14 | 2009-09-30 | 2009-10-07 | 92618.33 | 1.000
3776 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099095 | This project will extend the pavement life by resurfacing sections of Windsor Road and Riverside Boulevard in the city of Loves Park (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-21 | 2009-10-30 | 2009-11-09 | 455689.36 | 1.520
3777 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099096 | This project will extend the pavement life by resurfacing sections of Machesney Road and Mitchell Road in the village of Machesney Park (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-18 | 2010-05-30 | 2010-06-17 | 178714.98 | 1.720
3778 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099097 | This project will extend the pavement life and improve safety by resurfacing the road and replacing the sidewalk on Longwood Street in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-03 | 2010-08-30 | 2010-08-10 | 516086.51 | 0.320
3779 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099098 | This project will extend the pavement life of two roadways by resurfacing sections of Alpine Road, West State Street, and South Central Avenue in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-03 | 2010-10-30 | 2010-09-17 | 971771.39 | 1.860
3780 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099101 | Resurface FAU 5045 (Spring Rock Rd) from Imperial Oaks Dr to Mulford Rd in Rockford. Section 10-00576-00-RS | Pavement Improvement | 2010-10-15 | 2011-05-02 | 2011-06-30 | 2011-07-15 | 436774 | 0.780
3781 | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 5146078 | This project will substantially improve the roadway by reconstructing a section of Meadowbrook Road by providing new concrete pavement and other roadway improvements in Springfield(West-Central Illino | Pavement Improvement | 2011-02-24 | 2011-03-30 | 2011-08-30 |  | 201775 | 0.430
3782 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 17 | 5169042 | This project will extend the bridge life by repairing various bridge piers and making other bridge improvements on Garfield Bridge in the City of Decatur (Southeast Illinois). | Bridge Improvement | 2009-08-03 | 2009-08-10 | 2009-11-30 | 2010-04-14 | 792000 | 0.020
3783 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 15 | 5169043 | This project will substantially improve the roadway by constructing a new section of Fletcher Park Boulevard by providing new concrete pavement in Mt.Zion (Southeast Illinois). | New Construction | 2009-12-14 | 2010-03-31 | 2010-10-30 | 2011-05-18 | 1229600 | 0.570
3784 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 18 | 5169044 | This project will substantially improve the roadway by constructing two new bridges over Stevens Creek and the Tributary on County Highway 20 near Forsyth in Macon County (Southeast Illinois). | Bridge Replacement | 2010-04-19 | 2010-06-07 | 2010-12-30 | 2010-11-19 | 480000 | 0.020
3785 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 17 | 5169045 | This project will substantially improve the roadway by constructing a new bridge over Stevens Creek on MacArthur near Decatur in Macon County (Southeast Illinois). | Bridge Replacement | 2010-03-19 | 2010-04-12 | 2011-05-30 | 2010-11-23 | 447408 | 0.010
3786 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5181040 | This project will substantially improve the roadway by widening 1.5 miles of Windsor Road in Urbana to 4 lanes and providing for other roadway and safety improvements (East-Central Illinois) | Pavement Widening | 2009-06-05 | 2009-07-13 | 2011-06-30 | 2011-10-20 | 2150000 | 2.710
3787 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5181044 | This project will substantially improve the north leg of the 1st Street and Windsor Street intersection with concrete widening and other roadway improvements in Champaign (East-Central Illinois) | Safety/Traffic Management | 2009-08-01 | 2009-08-01 | 2009-11-30 | 2009-12-09 | 337278.19 | 1.530
3788 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5181045 | This project consists of providing engineering design for a future highway improvement on Prospect Avenue in the city of Savoy (East-Central Illinois). | Other | 2009-08-26 | 2009-09-01 | 2010-08-30 | 2011-05-31 | 331226 | 0.880
3789 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5181046 | This project will extend the pavement life by resurfacing 1.25 miles of Kirby Avenue in Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-10 | 2010-06-09 | 2010-08-30 | 2010-08-05 | 1096861.02 | 1.070
3790 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JO DAVIESS |  | 16 | 5206004 | This project will extend the pavement life by resurfacing a section of 2nd Street in the city of East Dubuque (Northwest Illinois). | Pavement Improvement | 2010-03-08 | 2010-04-26 | 2010-06-30 | 2010-05-21 | 88354 | 0.100
3791 | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 5227046 | This project will substantially improve the roadway by reconstructing, widening, and adding other roadway improvements to 0.5 mile of Hamilton Road in Bloomington. | Pavement Improvement | 2009-12-15 | 2010-02-16 | 2011-06-30 |  | 834472 | 0.100
3792 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 5227050 | This project will provide safety enhancements by installing traffic signals at the intersection of Hershey Road and College Avenue in Bloomington (East-Central Illinois) | Safety/Traffic Management | 2009-12-10 | 2010-03-17 | 2010-05-30 | 2010-04-28 | 172835.69 | 0.010
3793 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 5227051 | This project will extend the pavement life by resurfacing 1 mile of Ireland Grove Road in Bloomington (East-Central Illinois) | Pavement Improvement | 2009-12-03 | 2010-04-06 | 2010-10-30 | 2010-07-06 | 470000 | 0.930
3794 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 5227053 | This project will substantially improve 1 block of Virginia Avenue by reconstructing the roadway with concrete pavement, adding other roadway improvements, and replacing the structure over Sugar Creek | Bridge Replacement | 2009-12-14 | 2010-04-05 | 2010-10-30 | 2011-06-01 | 1414977 | 0.010
3795 | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO |  | 16 | 5291011 | This project will extend the pavement life by resurfacing a section of East Union Street in the city of Rockton (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-10 | 2009-10-30 | 2009-10-16 | 279191.55 | 1.840
3796 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5291016 | This project will extend the pavement life by resurfacing a section of Hononegah Road east of IL Route 2 in Winnebago County (Northwest Illinois). | Pavement Improvement | 2010-08-30 | 2010-09-02 | 2011-07-30 | 2011-06-15 | 384467 | 2.120
3797 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5291017 | Resurface FAU 9874 (Rood Ave) from Moore St to South Bluff Rd in South Beloit. Section 10-00037-00-RS | Pavement Improvement | 2011-02-18 | 2011-08-23 | 2011-05-30 | 2011-10-19 | 218505 | 0.340
3798 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5789005 | This project will extend the pavement life by resurfacing a section of US 6 near the city of Colona (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-07 | 2009-08-30 | 2009-05-28 | 289996.23 | 1.060
3799 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 6000201 | This project will extend the pavement life and provide for pedestrian safety by resurfacing, repairing sidewalk, improving traffic signals and streetscaping of Congress Parkway from Wells St. to Michi | Pavement Improvement | 2010-09-17 | 2010-11-20 | 2012-05-30 |  | 9000000 | 0.480
3800 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000282 | Painting of bridges and viaducts (2009 Program) - Contract A Chicago 08-E6106-00-PA | Bridge Improvement | 2011-08-04 | 2011-10-03 | 2011-10-30 |  | 911500 | 0.000
3801 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000284 | This project will extend the pavement life by resurfacing numerous roadway sections in the Far South area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-12-30 |  | 3860000 | 10.000
3802 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000285 | This project will extend the pavement life by resurfacing numerous roadway sections in the South area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 2009-07-08 | 2009-08-03 | 2009-12-30 |  | 9353000 | 22.000
3803 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000286 | This project will extend the pavement life by resurfacing numerous roadway sections in the Central area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 2009-07-08 | 2009-07-07 | 2009-12-30 | 2010-05-29 | 5875000 | 12.000
3804 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000287 | This project will extend the pavement life by resurfacing numerous roadway sections in the North area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 2009-07-01 | 2009-07-07 | 2009-12-30 |  | 9555000 | 18.000
3805 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 6000292 | This project will extend the pavement life by milling, patching and resurfacing Chicago Ave. from Laramie Ave to Grand Ave, in the City of Chicago, IL (Northeastern Illinois). | Pavement Improvement | 2009-11-04 | 2010-03-23 | 2011-11-30 |  | 5753000 | 2.870
3806 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 6000293 | This project will extend the pavement life by resurfacing LaSalle Dr from Clark St. to Lake Shore Dr. (Northeast Illinois) | Pavement Improvement | 2010-04-05 | 2010-06-10 | 2010-09-30 |  | 9356632 | 0.410
3807 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000294 | This project will provide for pedestrian safety by constructing sidewalk ramps that are in compliance with the Americans with Disabilities Act in various locations on the south side of Chicago. (North | Pavement Improvement | 2010-09-17 | 2011-08-06 | 2010-11-30 |  | 4337806 | 0.000
3808 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000295 | This project will provide for pedestrian safety by constructing sidewalk ramps that are in compliance with the Americans with Disabilities Act in various locations on the north side of Chicago. (North | Pavement Improvement | 2010-09-17 | 2011-06-11 | 2010-11-30 |  | 3197721 | 0.000
3809 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000296 | This project will provide for pedestrian safety by constructing sidewalk ramps that are in compliance with the Americans with Disabilities Act in various locations on the far south side of Chicago. (N | Pavement Improvement | 2010-09-17 | 2011-06-11 | 2010-11-30 | 2011-10-15 | 1135807 | 0.000
3810 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000297 | This project will provide for pedestrian safety by constructing sidewalk ramps that are in compliance with the Americans with Disabilities Act in various locations in the central part of the City Chic | Pavement Improvement | 2010-09-17 | 2011-06-11 | 2010-11-30 |  | 1685515 | 0.000
3811 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000310 | Arterial Street Resurfacing Project #56 Central Area in Chicago Section 07-B6117-00-RS | Pavement Improvement | 2011-08-29 | 2011-09-02 | 2012-11-30 |  | 4131092 | 0.000
3812 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | STATEWIDE | Multiple | 6000312 | Arterial street resurfacing Project No 58 - Far South Area in Chicago. Section 07-B6119-00-RS | Pavement Improvement | 2011-09-12 | 2011-09-12 | 2011-08-30 |  | 5531981 | 0.000
3813 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000313 | Arterial Street Resurfacing Project #57 South Area in Chicago section 07-B6116-00-RS | Pavement Improvement | 2011-10-03 | 2011-10-10 | 2011-07-30 |  | 4131093 | 0.000
3814 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000315 | Arterial street resurfacing Project No 55 North Area in Chicago. Section 07-B6116-00-RS | Pavement Improvement | 2011-08-29 | 2011-08-29 | 2011-11-30 |  | 4131092 | 0.000
3815 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000334 | Painting of bridges & viaducts (2009 Program) Contract B in Chicago. Section 08-E9101-00-PA. | Bridge Improvement | 2011-08-04 | 2011-10-03 | 2011-10-30 |  | 1921763 | 0.000
3816 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 6120001 | This project will extend the pavement life by resurfacing a section of IL 178 near the city of Utica (East-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-21 | 2009-08-30 | 2009-06-12 | 290585.59 | 0.780
3817 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 6176002 | This project will substantially improve the roadway by reconstructing a section of Armour Road in the city of Bourbonnais (East-Central Illinois). | Pavement Improvement | 2009-06-01 | 2010-04-05 | 2010-07-30 | 2011-11-21 | 4683342 | 1.250
3818 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 8003322 | This project will substantially improve the roadway by reconstructing Cemetary Rd between Washington St and Tri-State Parkway in the Village of Gurnee (Northeastern Illinois) | Pavement Improvement | 2009-09-15 | 2009-11-01 | 2010-11-30 |  | 4828105 | 2.940
3819 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 8003516 | This project will extend the pavement life by milling, patching and resurfacing 0.16 miles of Ridgewood Rd. in Riverside, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-01 | 2010-06-14 | 2011-05-30 | 2010-08-13 | 158391.11 | 0.130
3820 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 8003593 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to Madison Street in Villa Park (Northeast Illinois). | Safety/Traffic Management | 2009-10-19 | 2009-11-09 | 2010-06-30 | 2009-12-12 | 229134.55 | 0.900
3821 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 8003809 | This project will substantially improve the roadway by reconstructing a section of Wright Blvd by widening the road, providing new pavement and other roadway improvements in the Village of Schaumburg, | Pavement Improvement | 2010-03-03 | 2010-03-26 | 2010-05-30 | 2011-07-02 | 752264 | 0.860
3822 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 8003870 | This project will substantially improve the roadway by reconstructing a section of Wilmot Rd between Gordon Terrace and Deerfield Rd in the Village of Deerfield (Northeastern Illinois) by widening the | Pavement Improvement | 2009-06-12 | 2009-08-01 | 2009-11-30 | 2010-05-19 | 1661505.85 | 2.000
3823 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 8003888 | This project will provide for pedestrian/bicycle safety by constructing a new shared use path adjacent to Washington Street in Naperville (Northeast Illinois). | Transportation Enhancements | 2009-08-18 | 2009-08-31 | 2010-05-30 | 2010-10-19 | 1623500 | 0.000
3824 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003067 | This project will extend the life of the pavement by resurfacing Lawndale Ave from 47th St to Ogden Ave in Lyons in Cook County. | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2010-06-30 | 2010-06-07 | 523818 | 0.730
3825 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003176 | This project will extend the pavement life by resurfacing 0.99 miles of East Ave from Cermak Rd to Roosevelt Rd in Berwyn. (Northeastern Illinois). | Pavement Improvement | 2009-12-10 | 2010-04-01 | 2010-04-30 | 2010-06-16 | 732016.56 | 0.970
3826 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003193 | This project will extend the pavement life by resurfacing, pavement markings, removing and replacing curb, gutter and sidewalks to assist persons with disabilities. This project is located on Deaan St | Pavement Improvement | 2009-08-07 | 2009-09-21 | 2009-11-30 | 2009-11-05 | 258753 | 2.010
3827 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003199 | This project will extend the pavement life by milling, patching and resurfacing Wilson St from Randall Rd to Raddant Rd in the city of Batavia (Northeastern Illinois) | Pavement Improvement | 2009-07-15 | 2009-07-15 | 2009-08-30 | 2009-11-23 | 848648 | 5.140
3828 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003218 | This project will extend the pavement life by resurfacing 0.51 miles of 63rd Street from LaGrange Rd to East Ave in Hodgkins in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-11-10 | 2009-11-10 | 2010-05-30 | 2010-05-11 | 241462.53 | 0.520
3829 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003224 | This project will extend the pavement life by milling, patching, resurfacing and striping McDonald Rd from Burlington Rd to Kendall Rd in the village of Campton Hills (Northeastern Illinois) | Pavement Improvement | 2009-07-01 | 2009-08-24 | 2009-11-30 | 2009-11-04 | 260186.33 | 2.970
3830 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003225 | This project will extend the pavement life by milling, patching, resurfacing and striping on Summit St from Dundee Ave to Hiawatha Drive in the city of Elgin (Northeastern Illinois) | Pavement Improvement | 2009-08-26 | 2009-09-21 | 2009-12-30 | 2009-11-30 | 664549.68 | 1.200
3831 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003252 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Farnsworth Ave from Reckinger Rd to Molitor Rd in the City of Aurora (Northeastern Illinois) | Pavement Improvement | 2009-07-09 | 2009-08-24 | 2009-10-30 | 2010-09-21 | 563238.09 | 1.830
3832 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003254 | This project will extend the pavement life by milling, patching and resurfacing 0.93 mile of Addison Road in the Village of Villa Park, DuPage County (Northeastern Illinois). | Pavement Improvement | 2010-02-22 | 2010-05-03 | 2010-06-30 | 2010-07-19 | 694490 | 1.090
3833 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003278 | This project will extend the pavement life by milling, patching and resurfacing 0.98 miles of Central Park Ave. in Evergreen Park, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-03 | 2010-04-12 | 2010-07-30 | 2010-06-18 | 500000 | 1.000
3834 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003292 | This project will extend the pavement life by resurfacing Blackhawk Trail from Plainfield Rd. to Wolf Rd. in the village of Indian Head Park, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-22 | 2009-10-07 | 2009-11-30 | 2010-07-01 | 324544 | 1.720
3835 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003299 | This project will extend the pavement life by resurfacing, installing relief sewer, patching, curb & gutter, sidewalks, water main replacement on Sheridan Rd. from South Blvd to Main St. in the city o | Pavement Improvement | 2009-08-27 | 2009-09-10 | 2010-06-30 | 2010-11-04 | 1320000 | 1.220
3836 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003301 | This project will extend the pavement life by resurfacing and side walk repairs to accommodate people with disabilties on Washington St from Williams St to Main St in in the Village of Carpentersville | Pavement Improvement | 2009-09-08 | 2009-09-21 | 2009-10-30 | 2009-11-06 | 160000 | 0.840
3837 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003302 | This project will extend the pavement life by resurfacing 1.11 miles of Prairie Ave from 47th St to Burlington Ave, curb & gutter replacement, patching & sanitary sewer replacement all located in the | Pavement Improvement | 2009-12-10 | 2010-01-25 | 2010-06-30 | 2011-06-23 | 749094 | 1.120
3838 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003303 | This project will extend the pavement life by resurfacing 0.53 miles of Brainard Ave. from Harding Ave. to 31st St. in LaGrange Park, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2009-11-30 | 2009-11-12 | 319989 | 1.000
3839 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003304 | This project will extemd the pavement life by resurfacing 0.68 miles of Irving Park Rd. from Madison Dr. to Bartlett Rd. in the village of Streamwood, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-28 | 2009-11-30 | 2009-11-06 | 465000 | 1.680
3840 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003305 | This project will extend the pavement life by resurfacing 0.7 miles of 10th St./Wilmette Ave. from Sheridan Road to Lake Avenue in Wilmette, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-12-10 | 2010-04-20 | 2010-06-30 | 2010-06-26 | 371629 | 0.700
3841 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003306 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Sundown Rd from McLean Bvld to IL 31 in the Village of South Elgin (Northeastern Illinois) | Pavement Improvement | 2009-10-16 | 2009-10-16 | 2010-06-30 | 2011-10-31 | 640844 | 0.990
3842 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003307 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements and repairs to the structure carrying Old Willow Road over the Middle Fork of the north bran | Bridge Improvement | 2009-12-22 | 2010-04-05 | 2010-06-30 | 2010-05-07 | 54807 | 0.020
3843 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003308 | This project will extend the pavement life by milling, patching and resurfacing 0.73 miles of Pfingsten Rd. in Northbrook, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-03 | 2010-07-12 | 2011-05-30 |  | 535474 | 1.070
3844 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003309 | This project will extend the pavement life by resurfacing 1.47 miles of Overlook Drive from Waukegan Road to Golf Road, in the Village of Golf in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-10 | 2009-11-07 | 2009-12-30 | 2009-11-27 | 185093.88 | 1.720
3845 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003311 | This project will extend the pavement life by resurfacing on Bull Valley Rd from Shelby Court to Valley Hill Rd in the Village of Bull Valley (Northeastern Illinois) | Pavement Improvement | 2009-10-16 | 2010-05-03 | 2011-05-30 | 2010-06-19 | 234009 | 5.060
3846 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003313 | This project will substantially improve the roadway by reconstructing a section of US 14 at E. Main Street by providing new pavement and other roadway improvements in the City of Cary (Northeast Illin | Pavement Improvement | 2010-06-08 | 2010-07-29 | 2010-08-30 | 2011-05-27 | 262000 | 0.100
3847 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003315 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on Algonquin Rd between Plum Tree Rd and US 14 in the Village of F | Pavement Improvement | 2009-10-16 | 2009-10-16 | 2010-06-30 | 2010-05-25 | 187560.96 | 0.850
3848 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003316 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement of 1.22 miles onKaneville Rd from Randall Rd to IL Rt 38 in the Village of Geneva(Northeastern Il | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2010-06-30 | 2010-10-14 | 765556.78 | 2.500
3849 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003317 | This project will extend the pavement life by resurfacing on Wondermere Rd from Greenwood Rd to Thompson Rd in the Village of Greenwood (Northeastern Illinois) | Pavement Improvement | 2009-09-01 | 2009-09-01 | 2009-10-30 | 2010-01-31 | 256625 | 3.330
3850 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003318 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on State St from IL Rt 72 to north of Keyes Ave in Hampshire (Nort | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-06-30 | 2011-06-24 | 469794 | 1.600
3851 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003319 | This project will extend the pavement life by resurfacing 0.44 miles of 9th Ave from Roosevelt Rd to Bataan Drive in the Village of Maywood in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2010-05-30 | 2010-07-28 | 470000 | 1.320
3852 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003320 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings and detector loop replacement on Douglas Rd between Montgomery Rd a | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-06-30 | 2010-12-16 | 479143.03 | 1.340
3853 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003321 | This project will extend the pavement life by resurfacing Lehigh Ave from Oakton Street to Lincoln Avenue in the Village of Morton Grove in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-29 | 2010-05-10 | 2010-05-30 | 2010-06-14 | 356937 | 0.780
3854 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003322 | This project will extend the pavement life by resurfacing Montrose Ave from east of Cumberland Ave to Canfield Ave in the Village of Norridge in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-21 | 2009-11-01 | 2009-12-30 | 2010-06-15 | 258577.49 | 0.490
3855 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003323 | This project will extend the pavement life by resurfacing on Prairie St from west of US Rt 30/IL Rt 47 to Gordon Rd in the Village of Sugar Grove (Northeastern Illinois) | Pavement Improvement | 2009-12-22 | 2010-04-26 | 2010-06-30 | 2010-12-16 | 622771.88 | 3.840
3856 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003324 | This project will extend the pavement life by resurfacing 0.51 miles of Westchester Blvd from Canterbury St to Roosevelt Rd in the Village of Westchester in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-08 | 2009-11-01 | 2010-05-30 | 2010-09-19 | 388466.7 | 2.040
3857 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003326 | This project will extend the pavement life by resurfacing 1.2 miles of Central Rd from Huber Lane to Harlem Avenue in Glenview in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-08 | 2009-10-05 | 2009-12-30 | 2010-08-31 | 514416.18 | 2.880
3858 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003327 | This project will extend the pavement life by resurfacing Division St. from 25th Ave to 14th Ave in Melrose Park in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-11-06 | 2009-11-06 | 2010-06-30 | 2010-09-21 | 404463 | 1.010
3859 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003329 | This project will extend the life of the pavement by resurfacing 0.90 miles of Dundee Ave from Lake Cook Rd. to IL Route 59 in Barrington, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-29 | 2009-12-07 | 2010-05-30 | 2010-05-25 | 308000 | 0.900
3860 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003332 | The project consists of improving safety by installing traffic signals and resurfacing the intersection at Chicago-Heights Glenwood Rd and Holbrook Rd in the Village of Glenwood, Illinois (Northeaster | Safety/Traffic Management | 2010-01-26 | 2010-03-01 | 2010-08-30 | 2011-06-02 | 326479 | 0.010
3861 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003333 | This project consists of improving safety by installing street lighting along Broadway Ave in the City of Harvey, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-07-30 | 2011-06-02 | 408345 | 0.540
3862 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003334 | This project consists of improving safety by installing street lighting along 138th St in the Village of Riverdale, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-07-30 | 2011-06-20 | 369505 | 1.260
3863 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003335 | This project consists of improving safety by installing street lighting along Bernice Rd in the City of Lansing, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-01-08 | 2010-01-08 | 2011-05-30 | 2011-05-31 | 283947.39 | 1.350
3864 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003336 | This project consists of improving safety by installing emergency vehicle pre-emption equipment at 13 various intersections in the Village of Dolton, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-07-30 | 2010-08-31 | 114278 | 0.000
3865 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003337 | This project will extend the pavement life by milling, patching and resurfacing 0.99 miles of East End Ave. in Chicago Heights, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-01-08 | 2010-01-01 | 2010-06-30 | 2010-07-01 | 758423 | 1.020
3866 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003338 | This project will substantially improve the roadway by reconstructing a section of Western Ave by providing new concrete pavement and other roadway improvements in Blue Island, Illinois (Northeastern | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-07-30 | 2011-05-31 | 300566 | 0.040
3867 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003340 | This project will substantially improve the roadway by widening IL 43 from 243 ft north of 71st Street for 0.329 miles to the north in the Village of Bridgeview in Cook County (Northeastern Illinois). | Pavement Improvement | 2010-01-20 | 2010-03-15 | 2010-06-30 | 2010-07-10 | 500000 | 0.010
3868 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003341 | This project will improve safety by installing lighting on Ridge Road and McEvilly Road in the village of Minooka (East-Central Illinois). | Safety/Traffic Management | 2010-05-11 | 2010-10-07 | 2011-05-30 | 2011-03-25 | 169800 | 1.220
3869 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003342 | This project will extend the pavement life by patching and resurfacing 173rd St/Elm Dr. in Hazel Crest, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-02-16 | 2010-04-01 | 2010-12-30 | 2011-10-30 | 331000 | 0.630
3870 | Completed | C220,C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003343 | This project will enhance the roadway by installing 1.4 miles of tree planting, sidewalk improvements, pedestrian signals and lighting and signing along 95th St. (US 12/20) from 76th Avenue 88th St. i | Safety/Traffic Management | 2010-02-19 | 2010-02-20 | 2010-11-30 | 2011-06-30 | 745693 | 1.450
3871 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003344 | This project will extend the pavement life by milling, patching and resurfacing Madison St. in the Village of Bellwood, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-02-24 | 2010-04-09 | 2010-06-30 | 2010-07-22 | 258450.91 | 0.510
3872 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003345 | This project will extend the life of the pavement by resurfacing N. Oak Ave from W Bartlett Ave to US 20 & resurfacing W. Bartlett Ave from IL 59 to Western Ave, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-12-14 | 2009-12-17 | 2010-07-30 | 2010-10-16 | 1347367 | 1.740
3873 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003349 | This project will extend the life of the pavement by resurfacing Thatcher Ave. from Central Ave. to Chicago Ave. in the village of River Forest, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2009-10-30 | 2009-11-14 | 267629.81 | 0.980
3874 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003352 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on Ringwood Rd between Spring Grove Rd and Johnsburg Rd in the vill | Pavement Improvement | 2009-10-26 | 2009-10-26 | 2010-06-30 | 2010-06-07 | 253107 | 2.440
3875 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003353 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 0.90 miles on Ridge Rd between Deerwood Trail and IL Rt 120 in t | Pavement Improvement | 2009-10-27 | 2009-10-27 | 2010-06-30 | 2010-05-22 | 242990 | 2.880
3876 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003354 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 1.27 miles on Valley View Rd between Crystal Lake Rd and IL Rt 1 | Pavement Improvement | 2009-09-09 | 2009-09-28 | 2009-10-30 | 2009-10-21 | 213297.59 | 3.900
3877 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003355 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 1.40 miles on Ringwood Rd between McCullom Lake Rd and Devonshir | Pavement Improvement | 2009-10-27 | 2009-10-27 | 2010-06-30 | 2010-05-22 | 236816 | 6.280
3878 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003356 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of on East Wonder Lake Rd between McCullom Lake Rd and Burnard Mill | Pavement Improvement | 2009-12-10 | 2010-05-03 | 2010-05-30 | 2010-06-01 | 258510 | 1.610
3879 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003357 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Huntington Dr North from Stonegate Rd to Hanson Rd in the Village of Algonquin (Northeastern I | Pavement Improvement | 2009-09-08 | 2009-09-21 | 2009-10-30 | 2009-11-21 | 262105 | 2.070
3880 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003358 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement including handicap ramps on 1.0 mile on Kreutzer Rd from Smith Rd to Northwestern Railroad tracks | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-10-30 | 2009-11-19 | 183632.11 | 0.880
3881 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003359 | This project will extend the life of the pavement by resurfacing Fullerton Ave. from Webster St. to 76th Ave. in Elmwood Park, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2009-11-30 | 2010-11-23 | 303000 | 1.000
3882 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003360 | This project will provide for pedestrian safety by constructing a sidewalk extension adjacent to Manhattan Road in the Village of Manhattan, Will County (Northeastern Illinois). | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-06-30 | 2010-07-31 | 94000.22 | 0.350
3883 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003361 | This project will extend the pavement life by resurfacing 0.81 miles on 135th Street in Romeoville (Northeast Illinois). | Pavement Improvement | 2009-12-08 | 2010-01-11 | 2010-06-30 | 2010-05-03 | 355059.47 | 2.020
3884 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003362 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to Rathje Road in Peotone (Northeast Illinois). | Safety/Traffic Management | 2009-12-17 | 2010-01-13 | 2010-06-30 | 2011-05-31 | 37706.85 | 0.230
3885 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003363 | This project will extend the pavement life by resurfacing on Sauk Trail in Frankfort (Northeast Illinois). | Pavement Improvement | 2009-01-13 | 2009-01-13 | 2010-06-30 | 2010-07-26 | 190000 | 1.000
3886 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003364 | This project will extend the pavement life by resurfacing 99th St. from Oak Park Avenue to Ridgeland Avenue in Chicago Ridge in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-08-19 | 2009-10-03 | 2009-12-30 | 2010-04-01 | 332911.12 | 0.280
3887 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003366 | This project will enhance mobility by constructing a 10-foot wide asphalt pedestrian path for the Stony Creek Trail from Austin Ave to Mansfield Ave in Oak Lawn, Cook County (Northeastern Illinois). | Transportation Enhancements | 2010-03-31 | 2010-03-31 | 2011-05-30 | 2011-07-07 | 373434 | 0.000
3888 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003367 | This project consists of improving safety by installing street lighting along Sauk Trail in the City of Lansing, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-03-16 | 2010-07-26 | 2010-08-30 |  | 310171 | 0.890
3889 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003368 | This project will extend the life of the pavement by resurfacing Green Bay Rd. from Park Ave to Scott Ave in Glencoe in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-12-10 | 2010-05-10 | 2010-06-30 | 2010-08-07 | 570587 | 1.280
3890 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003369 | This project will extend the pavement life by resurfacing on Barreville Rd from north village limits to Ames Rd in the Village of Prairie Grove (Northeastern Illinois) | Pavement Improvement | 2009-12-28 | 2010-05-03 | 2010-05-30 | 2010-05-21 | 246401.04 | 0.720
3891 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003370 | This project will improve safety by lighting 0.5 miles of US Route 30 in Mokena (Northeast Illinois) | Safety/Traffic Management | 2009-11-19 | 2010-04-20 | 2011-05-30 | 2011-05-16 | 258742 | 0.030
3892 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003371 | This project will extend the pavement life by resurfacing 0.5 miles on Gaylord Road in Crest Hill (Northeast Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-11 | 2009-10-30 | 2010-04-01 | 133414.38 | 1.530
3893 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003372 | This project will extend the pavement life by resurfacing 0.7 miles of 167th Street from 88th Ave to Hobart Ave in Orland Hills, Cook County (Northeastern Illinois). | Pavement Improvement | 2010-04-19 | 2010-05-10 | 2010-07-30 | 2010-08-07 | 391534 | 0.710
3894 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003373 | This project will extend the pavement life by resurfacing on 151st Street in Homer Glen (Northeast Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-28 | 2009-10-30 | 2010-01-22 | 324520.7 | 3.000
3895 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003374 | This project will extend the life of the pavement by resurfacing 0.80 miles of Tower Road from Hibbard Road to Sheridan Road excluding Green Bay Road & Sheridan Road intersections, minor curb repair a | Pavement Improvement | 2009-10-29 | 2010-05-17 | 2011-05-30 | 2010-12-08 | 341861.61 | 0.890
3896 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003375 | This project will extend the pavement life by milling, patching and resurfacing 0.49 miles of Laramie Ave. in Oak Forest, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-19 | 2010-04-26 | 2010-06-30 | 2010-06-01 | 265202 | 0.500
3897 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003376 | This project will extend the life of the pavement by resurfacing 0.97 miles of Main St. from IL 50 to Crawford Avenue in Skokie in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-12-28 | 2010-04-01 | 2010-06-30 | 2010-09-15 | 764963.74 | 1.000
3898 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003377 | This project will improve mobility and safety by installing traffic signals & interconnections at the intersection of 127th St & Timberline Drive in Lemont in Cook County (Northeastern Illinois). | Safety/Traffic Management | 2009-12-08 | 2010-03-08 | 2010-06-30 | 2010-06-10 | 204073 | 0.010
3899 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003378 | This project will provide for pedestrian safety by removal & replacement of existing sidewalk with ADA ramps, and new curb & gutter along Roberts Road from 97th st to 111th St. and along 111th St from | Safety/Traffic Management | 2009-10-29 | 2009-12-21 | 2010-06-30 | 2010-06-21 | 294000 | 6.940
3900 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003379 | This project will extend the pavement life by milling, patching and resurfacing 0.48 miles of Flossmoor Rd. in Flossmoor, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-30 | 2010-04-21 | 2010-06-30 | 2010-08-11 | 155400 | 0.470
3901 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003380 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to IL 59 in Naperville (Northeast Illinois). | Safety/Traffic Management | 2010-01-04 | 2010-04-21 | 2010-07-30 | 2010-11-20 | 736796.07 | 3.160
3902 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003381 | This project will extend the pavement life by patching and resurfacing Church Road in the Village of Beecher, Will County (Northeastern Illinois). | Pavement Improvement | 2009-12-29 | 2010-03-01 | 2010-06-30 | 2010-05-18 | 89806 | 1.000
3903 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003382 | This project will extend the life of the pavement by resurfacing 0.28 miles of Franklin Ave from Ruby St to Rose St / 25th St in Franklin Park in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2010-05-30 | 2010-06-29 | 367440 | 0.540
3904 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003383 | This project will extend the pavement life by resurfacing on Drauden Road in Plainfield (Northeast Illinois). | Pavement Improvement | 2009-12-08 | 2010-04-06 | 2010-05-30 | 2010-10-11 | 139610 | 0.990
3905 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003384 | This project will extend the pavement life by milling, patching and resurfacing 0.78 miles of 135th St. in Crestwood, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-04-14 | 2010-05-17 | 2010-07-30 | 2010-10-22 | 225000 | 1.010
3906 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003385 | This project will improve mobility by constructing a sidewalk adjacent to Harlem Ave between 119th St and 131st St., on McCarthy Road between 76th Ave and 123rd St., and on 135th St. from Ridgeland to | Safety/Traffic Management | 2010-05-10 | 2010-06-22 | 2010-08-30 | 2011-05-28 | 265303 | 2.070
3907 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003386 | This project will extend the pavement life by milling, patching and resurfacing Burlington Ave from Brainard Ave to Kensington Ave in Lagrange, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-02-22 | 2010-06-07 | 2010-06-30 | 2010-10-17 | 292907 | 0.270
3908 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003387 | This project will extend the pavement life by resurfacing Central Ave from 70th Place to a point 1200 feet south of 73rd St in Bedford Park in Cook County (Northeastern Illinois). | Pavement Improvement | 2010-02-08 | 2010-04-22 | 2010-08-30 | 2010-10-04 | 471971 | 1.010
3909 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003389 | This project will extend the pavement life by resurfacing 1.10 miles on Thomas Dillon Drive in Channahon (Northeast Illinois). | Pavement Improvement | 2009-10-23 | 2010-04-27 | 2009-12-30 | 2010-05-04 | 154769.61 | 1.120
3910 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003390 | This project will enhance mobility by constructing a 0.4 mile multi-use path on the east side of 104th Ave from 167th St to 163rd Place in the Village of Orland Park, Cook County (Northeastern Illinoi | Transportation Enhancements | 2010-04-29 | 2010-05-09 | 2010-08-30 | 2010-11-10 | 261163.61 | 0.000
3911 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003391 | This project will extend the pavement life by milling, patching and resurfacing 0.51 mile of Clarendon Hills Road in the Village of Willowbrook, DuPage County (Northeastern Illinois). | Pavement Improvement | 2010-05-12 | 2010-06-09 | 2010-05-30 | 2010-06-29 | 192039.67 | 0.500
3912 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003392 | This project will provide for pedestrian safety by constructing a new sidewalks adjacent to Harlem Ave, 107th St, and Ridgeland Ave in Worth, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-04-08 | 2010-05-26 | 2010-07-30 | 2010-10-16 | 244710 | 0.830
3913 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003393 | This project will extend the pavement life by milling, patching and resurfacing 0.49 miles of Kostner Ave. in Crestwood, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-03 | 2010-04-15 | 2010-06-30 | 2010-07-09 | 175447.86 | 1.000
3914 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003394 | This project will extend the pavement life by resurfacing 0.39 miles of 34th St. from Union Ave to Holeman Ave in South Chicago Heights, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-17 | 2010-04-26 | 2010-12-30 | 2011-10-30 | 368018 | 0.370
3915 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003395 | This project will improve mobility by constructing 1.0 miles of sidewalk on the east side of Kedzie Ave from 153rd St to 159th St. in the City of Markham, Cook County (Northeastern Illinois). | Safety/Traffic Management | 2010-05-24 | 2010-05-24 | 2011-01-30 | 2011-01-05 | 237663 | 2.640
3916 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003396 | This project will extend the pavement life by resurfacing on Wallin Drive in Plainfield (Northeast Illinois). | Pavement Improvement | 2009-12-08 | 2010-04-06 | 2010-05-30 | 2010-10-11 | 147752 | 1.010
3917 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003397 | This project will extend pavement life by milling, patching and resurfacing an eight block section of Janes Avenue in the City of Woodridge (Northeastern Illinois). | Pavement Improvement | 2010-03-02 | 2010-04-02 | 2010-06-30 | 2010-05-21 | 434085.18 | 2.000
3918 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003398 | This project will extend the pavement life by patching, milling and resurfacing Woodridge Drive from Hobson Road to Center Drive in the Village of Woodridge (Northeastern Illinois). | Pavement Improvement | 2010-10-28 | 2011-04-12 | 2011-05-30 | 2011-05-28 | 119900 | 0.680
3919 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003399 | This project will extend the life of the bridge carrying Whitehall Ave over Addison Creek by removing existing superstructure & replace with wide flange steel beam & concrete deck & roadway improvemen | Bridge Improvement | 2010-03-31 | 2010-03-31 | 2010-07-30 | 2011-10-31 | 494764 | 0.200
3920 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003400 | This project will extend the pavement life by milling, patching and resurfacing 1.02 mile of Lies Road in the Village of Carol Stream, DuPage County (Northeastern Illinois). | Pavement Improvement | 2010-02-19 | 2010-05-03 | 2010-07-30 | 2010-12-18 | 620470 | 1.010
3921 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003403 | This project will extend the pavement life by milling and resurfacing Powis Road from North Avenue to Smith Road in the City of West Chicago (Northeastern Illinois). | Pavement Improvement | 2010-06-10 | 2010-07-06 | 2010-09-30 | 2010-10-01 | 232025.8 | 1.150
3922 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003405 | This project will extend the pavement life by milling and resurfacing Joliet Street from IL Route 59 to Geneva Street in the City of West Chicago (Northeastern Illinois). | Pavement Improvement | 2010-05-18 | 2010-06-28 | 2010-08-30 | 2010-09-25 | 624238 | 2.080
3923 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003406 | This project will extend the pavement life by milling and resurfacing Arbor Avenue from Washington Street to Hawthorne Lane in the City of West Chicago (Northeastern Illinois). | Pavement Improvement | 2010-08-03 | 2010-08-05 | 2010-08-30 | 2010-11-19 | 303786 | 1.040
3924 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003408 | This project will extend the pavement life by milling and resurfacing 1.21 miles of Bruce Road and 163rd Street in the City of Lockport (Northeastern Illinois). | Pavement Improvement | 2010-03-01 | 2010-06-09 | 2010-06-30 |  | 415000 | 1.880
3925 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003410 | This project will extend the pavement life by milling, patching and resurfacing 1.02 mile of St. Charles Road in the City of Elmhurst (Northeastern Illinois). | Pavement Improvement | 2010-02-22 | 2010-05-03 | 2010-06-30 | 2010-07-10 | 348645.69 | 0.510
3926 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003411 | This project will extend the pavement life by patching, milling and resurfacing Vallette Street from Spring Road to Poplar Avenue in the City of Elmhurst, DuPage County (Northeastern Illinois) | Pavement Improvement | 2010-09-16 | 2011-05-02 | 2010-11-30 | 2011-10-27 | 785000 | 0.980
3927 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003412 | This project will substantially improve the roadway by reconstruction a section of First Street from Myrtle Avenue to Clara Place in the City of Elmhurst (Notheastern Illinois). | Pavement Improvement | 2010-04-29 | 2010-06-01 | 2010-06-30 | 2010-12-22 | 310000 | 0.730
3928 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003417 | This project will extend the pavement life by milling and resurfacing 1.13 miles of Park Boulevard and Lambert Road in the Village of Glen Ellyn, DuPage County (Northeastern Illinois). | Pavement Improvement | 2010-05-20 | 2010-06-14 | 2010-07-30 | 2010-09-02 | 626553 | 1.090
3929 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003418 | This project will enhance mobility by constructing a new sidewalk on Governors Highway from Sauk Trail to Maple Ave, from Poplar Ave to north Maple Ave, from 400 feet south of Sauk Trail to Sauk Trail | Safety/Traffic Management | 2010-06-08 | 2010-08-01 | 2011-05-30 | 2011-04-16 | 106823 | 0.630
3930 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003419 | This project consists of improving safety and traffic enhancement by 0.78 miles of traffic signal modernization on US Rt 14 from Dole Ave to Devonshire Lane/Kieth Ave in Crystal Lake (Northeastern Ill | Safety/Traffic Management | 2009-12-03 | 2010-03-02 | 2010-07-30 | 2010-10-26 | 270551 | 0.770
3931 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003420 | This project will extend the pavement life with 3.0 miles of concrete pavement patching, asphalt overlay, shoulder rehabilitation, new pipe underdrains, sidewalk removal & replacement on E. Frontage R | Pavement Improvement | 2009-09-21 | 2009-10-01 | 2010-07-30 | 2010-05-28 | 2822101 | 7.890
3932 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003421 | This project will extend the pavement life by milling, patching and resurfacing 1.1 miles of St. Charles Road from Illinois Route 53 to Grace Street in the Village of Lombard, DuPage County (Northeast | Pavement Improvement | 2010-05-26 | 2010-06-29 | 2010-08-30 |  | 47063 | 1.480
3933 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003422 | This project will extend the pavement life by milling, patching and resurfacing 127th St from 80th Ave to 123rd St and 121st St from Southwest Highway to 80th Ave in Palos Park, Illinois (Northeastern | Pavement Improvement | 2010-02-24 | 2010-02-24 | 2011-05-30 | 2011-03-08 | 216147.92 | 0.640
3934 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003423 | This project will extend the pavement life by milling, patching and resurfacing 0.76 miles of Gilbert Ave. in Western Springs, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-01 | 2010-03-17 | 2010-06-30 | 2010-06-22 | 475372 | 0.780
3935 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003424 | This project will extend the pavement life by resurfacing numerous roadway sections in DuPage County (Northeastern Illinois). | Pavement Improvement | 2009-12-08 | 2010-05-10 | 2010-07-30 | 2010-08-26 | 374795 | 2.210
3936 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003425 | This project will extend the pavement life by resurfacing 1.09 miles on Gardield Street in Hinsdale (Northeast Illinois) | Pavement Improvement | 2009-12-09 | 2010-04-05 | 2010-11-30 | 2011-11-01 | 1335646 | 1.010
3937 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003426 | This project will extend the pavement life by milling, patching and resurfacing 187th St. from Dixie Highway to Riegel Rd in Homewood, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-03 | 2010-04-12 | 2010-06-30 | 2010-06-03 | 210281 | 0.660
3938 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003428 | This project will extend the pavement life by milling, patching and resurfacing 139th St. from Crawford Ave to Coopers Grove Rd in Robbins, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-01-08 | 2010-05-01 | 2010-08-30 | 2010-08-19 | 713000 | 2.420
3939 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003429 | This project will extend the pavement life by milling, patching and resurfacing 0.69 miles of Woodlawn Ave. in Ford Heights, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-01-08 | 2010-03-01 | 2010-07-30 | 2010-09-14 | 441859 | 1.360
3940 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003430 | This project will provide for pedestrian safety by constructing a new sidewalks adjacent to Algonquin Rd from Seymour Ave to Mt. Prospect Rd. in Des Plaines, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-02-24 | 2010-04-05 | 2010-07-30 | 2010-05-17 | 139672.24 | 0.700
3941 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003431 | This project will extend the pavement life by resurfacing University Parkway from Crawford Avenue to Steger-Monee Road in the Village of University Park, Will County (Northeastern Illinois). | Pavement Improvement | 2010-03-31 | 2010-05-06 | 2010-07-30 | 2011-12-05 | 371573 | 2.420
3942 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003436 | This project will extend the pavement life by resurfacing 0.91 miles on Boughton Road in Bolingbrook (Northeast Illinois). | Pavement Improvement | 2009-10-01 | 2009-10-12 | 2009-12-30 | 2009-11-27 | 618177.12 | 3.210
3943 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003438 | This project consists of improving safety by upgrading traffic signals on Schmidt Road at the intersection with Remington Boulevard in the Village of Bolingbrook, Will County (Northeastern Illinois). | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-06-30 | 2011-06-07 | 275450 | 0.010
3944 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003439 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of on Oak St between Crystal Lake Rd and Burr St in the village of | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2010-06-30 | 2010-05-29 | 219105 | 0.720
3945 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003440 | This project will extend the pavement life by resurfacing on Shick Road in Bloomingdale (Northeast Illinois). | Pavement Improvement | 2009-10-29 | 2010-04-15 | 2010-07-30 | 2010-08-07 | 1331335 | 0.930
3946 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003441 | Lake County will add new pavement, curbs and gutters on Pheasant Ridge Rd near Old Mill Rd in Lake Zurich. | Pavement Improvement | 2010-08-19 | 2010-09-29 | 2010-08-30 | 2010-10-11 | 119000 | 0.410
3947 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003442 | This project will extend the pavement life by milling, patching and resurfacing Edina Blvd. from 21st street to Shiloh Blvd. (Northeast Illinios). | Pavement Improvement | 2010-01-12 | 2010-01-12 | 2010-05-30 | 2011-07-29 | 197679 | 0.480
3948 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003443 | This project will extend the pavement life by resurfacing Old Barrington Road from Cuba Rd to IL 22 in the City of North Barrington (Northeastern Illinois). | Pavement Improvement | 2010-03-02 | 2010-04-27 | 2010-06-30 | 2010-06-07 | 235139 | 1.020
3949 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003445 | This project will substantially extend the pavement life by resurfacing, landscaping and improve safety and traffic enhancement by upgrading pavement markings of on Raffel Rd from Il Rt 120 Banford R | Pavement Improvement | 2009-12-10 | 2010-05-03 | 2010-06-30 | 2010-08-21 | 270551 | 0.250
3950 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003449 | This project will extend the pavement life by milling, patching and resurfacing 0.48 miles on Garfield St from McKinley St to Old Orchard Rd in Harvard (Northeastern Illinois). | Pavement Improvement | 2009-12-07 | 2010-03-15 | 2010-03-30 | 2010-06-07 | 212714.24 | 0.450
3951 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003450 | Lake County will add new pavement, curb and gutter and sidewalk on Lake street between IL Rt 120 and Center Street. | Pavement Improvement | 2010-06-17 | 2010-09-20 | 2011-05-30 | 2011-07-12 | 266560 | 0.410
3952 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003452 | This project will extend the pavement life by milling, patching and resurfacing Deerpath Rd near Deer Park, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-02 | 2010-04-27 | 2010-05-30 | 2010-06-07 | 118480 | 0.420
3953 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003453 | Lake County will replace curb and gutter and Sidewalk on Old Checker Rd near Buffalo grove Rd. | Pavement Improvement | 2010-06-17 | 2010-09-16 | 2010-10-30 | 2011-09-30 | 296100 | 0.800
3954 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003454 | This project will extend the pavement life by milling, patching and resurfacing Telegraph Rd near Bannnockburn, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-02 | 2010-05-15 | 2010-06-30 | 2010-09-28 | 248616 | 1.000
3955 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003456 | This project will extend the pavement life by resurfacing a four block section of Laurel Ave in the City of Highland Park (Northeast Illinois). | Pavement Improvement | 2010-03-02 | 2010-05-03 | 2010-06-30 | 2010-06-19 | 136394 | 0.370
3956 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003457 | This project will extend the pavement life by milling, patching and resurfacing Sheridan Rd near Highwood, Illinois (Northeast Illinios). | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-06-30 | 2011-11-30 | 437566 | 1.180
3957 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003458 | This project will extend the pavement life by milling, patching and resurfacing Deerpath Drive near Lindenhurst, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-01 | 2010-05-03 | 2010-05-30 | 2010-12-15 | 169230 | 0.520
3958 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003459 | This project will extend the pavement life by milling, patching and resurfacing Saunders Road near Riverwood, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-02 | 2010-04-28 | 2010-06-30 | 2010-06-10 | 331128 | 1.450
3959 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003461 | Village of Wauconda will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of pavement | Pavement Improvement | 2010-02-19 | 2010-06-01 | 2011-05-30 | 2010-10-22 | 231818 | 1.450
3960 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003462 | This project will extend the pavement life by milling, patching and resurfacing Jackson Street near Waukegan, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-15 | 2010-04-19 | 2010-07-30 | 2010-07-24 | 661320 | 2.600
3961 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003465 | This project will extend the pavement life by milling and resurfacing various roadway sections in the City of Joliet (Northeastern Illinois). | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-07-30 | 2011-10-01 | 1176444.37 | 0.000
3962 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003466 | This project will extend the pavement life by resurfacing 3.65 miles on River Road near Wilmington (Northeast Illinois). | Pavement Improvement | 2009-12-28 | 2010-04-05 | 2010-07-30 | 2010-06-17 | 1260000 | 3.700
3963 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003467 | Lake County will replace pavement and improve shoulders on Fairfield Rd between IL 176 and Old Mchenry Rd. | Pavement Improvement | 2010-06-17 | 2010-08-01 | 2010-09-30 | 2010-11-20 | 1287623 | 3.550
3964 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003471 | This project will extend the pavement life by resurfacing, pavement patching and curb and gutter replacement on Central Ave from Church Street to Golf Road in the Village of Morton Grove, Illinois (No | Pavement Improvement | 2010-08-05 | 2010-09-20 | 2010-08-30 | 2010-11-08 | 222807 | 0.500
3965 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 9003472 | This project consists of improving safety by installation of a complete street lighting system along Algonquin Rd, Golf Rd and New Wilke Road in the City of Rolling Meadows, IL (Northeastern Illinois) | Safety/Traffic Management | 2010-11-30 | 2011-07-16 | 2011-08-30 |  | 979739 | 3.260
3966 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003475 | This project will extend the pavement life by milling, patching and resurfacing Chapel Hill Rd near Johnsburg, Illinois (Northeast Illinois). | Pavement Improvement | 2010-05-12 | 2010-06-14 | 2010-06-30 | 2010-10-13 | 262105 | 2.000
3967 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003476 | This project will extend the pavement life by milling, patching and resurfacing Rawson Bridge Rd near Port Barrington, Illinois (Northeast Illinios). | Pavement Improvement | 2010-04-29 | 2010-04-30 | 2010-06-30 | 2010-10-30 | 214981 | 0.010
3968 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003478 | This project consists of improving safety and traffic enhancement by installing street lighting along IL Route 113 from Center Road to Mitchell Street in the City of Braidwood (Northeastern Illinois). | Safety/Traffic Management | 2010-06-17 | 2011-04-09 | 2010-07-30 | 2011-11-04 | 68000 | 0.250
3969 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003481 | This project will extend the pavement life by milling, patching and resurfacing 0.46 miles of Glenview Road between Waukegan Road and Chatham Road in Glenview, Illinois (Northeastern Illinios). | Pavement Improvement | 2010-11-15 | 2011-04-09 | 2010-10-30 | 2011-07-02 | 179173 | 0.460
3970 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003486 | This project will extend the pavement life by milling and resurfacing various roadway sections in the Village of New Lenox, Will County (Northeastern Illinois). | Pavement Improvement | 2010-04-19 | 2010-05-26 | 2010-06-30 | 2010-06-26 | 247119.24 | 0.000
3971 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003489 | This project will extend pavement life by resurfacing 0.4 miles of Devon Avenue from Higgins Rd to I-294 in the Village of Rosemont in Cook County (Northeastern Illinois). | Pavement Improvement | 2010-03-31 | 2010-03-31 | 2010-06-30 | 2011-01-17 | 428715.38 | 0.360
3972 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003490 | This project will extend pavement life by resurfacing numerous roadway sections in DuPage County including Gary Ave, Naperville Rd, Lemont Rd, Ferry Rd and Diehl Rd. (Northeastern Illinois) | Pavement Improvement | 2010-03-19 | 2010-04-14 | 2010-08-30 | 2010-09-04 | 3443994 | 0.000
3973 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003497 | Lake County will replace pavement on Deerpath Rd Resurface from IL Route 60 to Marimac Lane in the village of Vernon Hills. | Pavement Improvement | 2010-08-19 | 2010-09-07 | 2010-08-30 | 2010-10-15 | 273000 | 1.470
3974 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003498 | This project will provide for pedestrian safety by constructing sidewalks and ramps along various streets in the village of Coal City (East-Central Illinois). | Safety/Traffic Management | 2010-06-29 | 2010-10-11 | 2010-05-30 | 2010-11-16 | 60934.02 | 0.000
3975 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003500 | This project will extend the pavement life by resurfacing 0.5 miles of Montrose Ave from Sayre Ave to Forest Preserve Ave in the Village of Harwood Heights, Cook County (Northeastern Illinois). | Pavement Improvement | 2010-04-09 | 2010-05-27 | 2010-05-30 | 2010-06-12 | 200396 | 0.480
3976 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003505 | This project will extend the pavement life by resurfacing 0.4 miles of Ridgeland Ave from Roosevelt Rd to Garfield St., and 1.0 miles from Division St. to North Ave in Oak Park, Cook County (Northeast | Pavement Improvement | 2010-04-09 | 2010-04-30 | 2010-06-30 | 2010-08-07 | 533231 | 0.920
3977 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003507 | Resurface FAU 2666 (Main St) from IL Route 22 to Buffalo Grove Rd in Buffalo Grove. Section 09-00096-00-RS | Pavement Improvement | 2010-07-27 | 2010-11-10 | 2011-12-30 | 2010-12-19 | 188388 | 0.670
3978 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003513 | This project will provide for pedestrian safety by replacing sidewalks along Kankakee Street from Baltimore Street to Kankakee River Drive in the City of Wilmington (Northeastern Illinois). | Safety/Traffic Management | 2010-03-12 | 2010-04-01 | 2010-05-30 | 2010-06-15 | 52050 | 0.800
3979 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003515 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to County Line Road in Burr Ridge (Northeast Illinois). | Safety/Traffic Management | 2010-01-08 | 2010-08-30 | 2011-05-30 | 2011-05-27 | 201677 | 0.550
3980 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 9003516 | This project substantially improve the roadway by reconstructing Broadway Ave from Iowa Street to Division Street and will extend the pavement life by resurfacing Broadway Ave from Lake Street to Iowa | Pavement Improvement | 2010-08-05 | 2010-09-02 | 2010-09-30 | 2010-11-17 | 592817 | 0.490
3981 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003522 | This project will enhance the roadways by supplying, delivering & installing 324 native trees on Cicero Avenue, Crawford Avenue, Devon Avenue, Lincoln Avenue, Pratt Avenue, Touhy Avenue & McCormick Av | Transportation Enhancements | 2010-04-21 | 2011-05-09 | 2010-06-30 | 2011-05-18 | 140300 | 0.000
3982 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003524 | This project will extend the pavement life by widening, milling and resurfacing Center Road from Laraway Road to Sauk Trail in the Village of Frankfort (Northeastern Illinois). | Pavement Improvement | 2010-08-23 | 2010-10-19 | 2011-06-30 |  | 1000000 | 0.760
3983 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003525 | This project will extend the pavement life by milling, patching and resurfacing 173rd St from Old Brennan Highway to Cicero Ave. in Country Club Hills, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-29 | 2010-04-16 | 2010-05-30 | 2010-04-30 | 180205.1 | 0.360
3984 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003526 | This project will extend the pavement life by resurfacing Raven Road from Seil Road to Valencia Drive in the Village of Shorewood, Will County (Northeastern Illinois). | Pavement Improvement | 2010-04-19 | 2010-05-12 | 2010-06-30 | 2010-09-20 | 143650 | 0.350
3985 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003528 | This project will provide for pedestrian safety by constructing a new Pedestrain path and bridge adjacent to Thornmeadow Rd. in Riverwoods, (Northeast Illinois). | Bridge Improvement | 2010-05-18 | 2010-06-08 | 2010-09-30 |  | 1066350 | 0.250
3986 | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003529 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to IL Route 72 in West Dundee, IL , (Northeast Illinois). | Transportation Enhancements | 2010-05-07 | 2010-07-12 | 2010-08-30 | 2010-11-17 | 133630 | 0.130
3987 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003537 | This project will extend the pavement life by milling, patching and resurfacing 0.63 miles of Orchard Dr. in Park Forest, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-30 | 2010-05-05 | 2010-06-30 | 2010-08-25 | 304504 | 0.670
3988 | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003547 | This project will improve aesthetics by streetscaping 0.47 miles of US 41 including lighting, sidewalk repair, curb and gutter repair and resurfacing in Skokie, Illinois (Northeastern Illinois) | Transportation Enhancements | 2010-04-15 | 2010-09-13 | 2011-08-30 |  | 790336 | 0.490
3989 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003549 | This project will improve aesthetics by planting trees and streetscaping along various routes including Roberts Rd, 111th St, Kean Ave, and 103rd St in Palos Hills, Illinois (Northeastern Illinois). | Transportation Enhancements | 2010-03-25 | 2010-03-17 | 2010-06-30 | 2011-05-14 | 150920 | 5.790
3990 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003550 | This project will extend the pavement life by milling, patching and resurfacing Batavia Road in the City of Warrenville (Norteastern Illinois). | Pavement Improvement | 2010-02-19 | 2010-04-15 | 2010-06-30 | 2010-07-26 | 534920 | 1.150
3991 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003556 | This project will extend the pavement life by resurfacing, curb and gutter replacement, sidewalk replacement and patching on Armitage Ave from Wolf Road to Mannheim Road in the Village of Northlake, I | Pavement Improvement | 2010-07-15 | 2010-09-07 | 2011-12-30 | 2010-12-16 | 450265.66 | 1.050
3992 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003569 | This project will extend the pavement life by resurfacing Biesterfield Rd from Rohlwing Rd to the I-290 Ramps in Elk Grove Village, IL (Northeastern Illinois) | Pavement Improvement | 2010-11-23 | 2011-04-01 | 2011-06-30 | 2011-11-04 | 313517 | 0.010
3993 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003574 | This project will improve safety by installing 0.31 miles of new lighting along Burnham Ave from Brainard Ave north to Burnham Ave bridge in Burnham, Cook County (Northeastern Illinois). | Safety/Traffic Management | 2010-03-31 | 2010-03-31 | 2011-06-30 |  | 187783 | 0.080
3994 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003575 | This project will extend the life of the pavement by resurfacing 0.9 miles of Vincennes Rd from Halsted St. Thornton Rd in the Village of Phoenix in Cook County (Northeastern Illinois). | Pavement Improvement | 2010-08-09 | 2010-09-07 | 2011-06-30 | 2010-11-29 | 475000 | 0.530
3995 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003576 | This project consists of improving safety and traffic enhancement by installing street lighting at the intersection of IL Route 83 and Plainfield Road in the Village of Willowbrook, DuPage County (Nor | Safety/Traffic Management | 2010-05-18 | 2010-07-01 | 2010-07-30 | 2011-05-04 | 185403 | 0.010
3996 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003584 | City of Batavia will resurafce and will add curb & gutter & sidewalk replacement on Western Ave from Mckee St to Fabyan Parkway. | Pavement Improvement | 2010-09-02 | 2010-09-28 | 2010-10-30 | 2010-10-19 | 265321 | 0.720
3997 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003606 | This project will extend the pavement life by patching and resurfacing 0.29 miles of Wentworth/Atlantic Avenue from 142nd Street to 144th Street in Riverdale, IL (Northeastern Illinois) | Pavement Improvement | 2010-09-22 | 2010-10-04 | 2011-12-30 | 2011-08-16 | 181916 | 0.280
3998 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003608 | City of South Elgin will resurface and will add curb & gutter & sidewalk repair on Spring Street | Pavement Improvement | 2010-07-27 | 2010-10-12 | 2011-12-30 | 2010-12-20 | 294293 | 0.610
3999 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003616 | City of Hampshire will add new pavement on Dietrich Rd from US 20 to Hampshire. | Pavement Improvement | 2010-09-14 | 2010-09-30 | 2010-12-30 |  | 126927 | 0.140
4000 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003635 | Mchenry County will improve safety and operations by adding turning lanes at the intersection of Three Oaks Rd and Silver Lake Road in the village of Cary. | Pavement Improvement | 2010-09-16 | 2010-10-21 | 2011-12-30 | 2011-12-30 | 300889 | 0.010
4001 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003640 | This project will extend the pavement life by milling, patching and resurfacing on FAU 184 (Hawthorne Dr) from Cedar Lake Road to Rollins Rd in Round Lake Beach (Northeast-Illinois) | Pavement Improvement | 2010-03-29 | 2010-05-03 | 2010-06-30 | 2010-12-23 | 163435 | 0.950
4002 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003644 | City of Elgin will add new pavement, curb & gutter, sidewalk repair on Big Timber Rd from McLean Blvd to IL 31. | Pavement Improvement | 2010-09-07 | 2010-09-20 | 2010-10-30 | 2011-06-21 | 324263 | 1.070
4003 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 04 | 9003645 | This project will extend the pavement life by resurfacing, curb and gutter, sidewalk and driveway replacement of 0.30 miles of Austin Blvd from Ogden Ave to 29th Street in the Cicero, Illinois (Northe | Pavement Improvement | 2010-07-15 | 2010-07-15 | 2010-09-30 | 2010-12-08 | 536973 | 0.360
4004 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003646 | City of Campton Hills will add new pavement on McDonald Rd from Phar Lap Dr to Cloverfield Circle. | Pavement Improvement | 2010-09-22 | 2010-09-22 | 2010-11-30 | 2011-07-07 | 130813 | 0.890
4005 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003651 | This project will extend the pavement life by milling, patching and resurfacing 0.48 miles of Harwood Avenue in Homewood, Illinois (Northeastern Illinois). | Pavement Improvement | 2010-09-09 | 2010-09-27 | 2010-09-30 | 2010-10-16 | 112492 | 0.570
4006 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003652 | This project will extend the pavement life by milling, patching and resurfacing 0.65 miles of Harwood Avenue and Maple Road between Ashland Avenue and Dixie Highway in Homewood, Illinois (Northeastern | Pavement Improvement | 2010-09-02 | 2010-10-05 | 2011-05-30 | 2011-04-23 | 193979 | 0.630
4007 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003662 | City ofAurora will add new pavement, curb & gutter & sidewalk replacemen on Indian Trail Dr from Highland Ave to Randall Rd. | Pavement Improvement | 2010-08-30 | 2010-09-01 | 2010-12-30 | 2011-12-12 | 70228 | 1.030
4008 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003663 | This project will provide for pedestrian safety by constructing a sidewalk along 119th St. between Pulaksi Rd. and Kostner Ave. in Alsip, IL. (Northeastern Illinois) | Safety/Traffic Management | 2010-08-25 | 2010-10-01 | 2010-11-30 | 2011-07-25 | 102513 | 0.500
4009 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003664 | This project will provide for pedestrian safety by streetscaping Roberts Road, including sidewalk replacement and landscaping from 99th Street to 87th Street in the City of Hickory Hills. (Northeaste | Transportation Enhancements | 2011-02-08 | 2011-04-09 | 2011-05-30 |  | 133000 | 1.640
4010 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003665 | This project will extend the pavement life by patching and resurfacing 88th Avenue from 159th Street to 171st Street in the Village of Orland Park, IL (Northeastern Illinois) | Pavement Improvement | 2010-10-22 | 2011-05-02 | 2011-06-30 | 2011-09-17 | 296000 | 1.500
4011 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003666 | City of Sugar Grove will resurface on Granart Rd from Whildin Rd to Dugan Rd. | Pavement Improvement | 2010-10-22 | 2010-04-30 | 2010-11-30 | 2011-09-03 | 146780 | 0.380
4012 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003667 | This project will provide for pedestrian safety by constructing a sidewalk along McCarthy Road between Woodcrest Lane and Walker Road. in Lemont, IL. (Northeastern Illinois) | Safety/Traffic Management | 2010-08-25 | 2011-05-20 | 2010-11-30 |  | 79545 | 0.360
4013 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003668 | This project will extend the pavement life by patching and resurfacing 1.17 miles of Prince Drive (I-94 frontage road) from 170st Street to Woodlawn East Avenue in the South Holland, IL (Northeastern | Pavement Improvement | 2010-09-10 | 2010-12-01 | 2011-05-30 | 2011-08-07 | 454927 | 1.170
4014 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003669 | This project consists of improving safety and traffic enhancement by installing street lighting along 191st Street from 80th Avenue to Harlem Avenue in the Village of Tinley Park (Northeastern Illinoi | Safety/Traffic Management | 2010-06-17 | 2010-09-07 | 2010-10-30 | 2011-08-30 | 479199 | 0.150
4015 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003670 | This project consists of improving safety by installation of a modern roadway lighting system along Harlem Avenue (IL 43) from 71st Street to the North of 70th Street and also including the East and W | Safety/Traffic Management | 2010-10-27 |  | 2011-05-30 |  | 133000 | 0.780
4016 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003671 | This project will extend the pavement life by patching and resurfacing 103rd Street from Austin Avenue to Central Avenue in Oak Lawn, IL (Northeastern Illinois) | Pavement Improvement | 2010-12-06 | 2011-04-30 | 2010-11-30 | 2011-10-12 | 133000 | 0.490
4017 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003672 | This project consists of improving safety by modernization of traffic signals including removal and replacement of signal heads, pedesrtian signal heads and pedestrian push buttons at the intersection | Safety/Traffic Management | 2010-11-18 | 2011-05-07 | 2010-11-30 | 2011-10-29 | 46190 | 0.010
4018 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003675 | This project will extend the pavement life by patching, milling and resurfacing Burville Road from Dixie Highway to west of State Street in the Village of Crete (Northeastern Illinois). | Pavement Improvement | 2010-10-12 | 2011-04-16 | 2011-05-30 | 2011-07-05 | 361764 | 1.170
4019 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003676 | This project will provide for pedestrian safety by reconstructing a sidewalk including ADA ramps along 103rd Street between 88th Avenue and Harlem Avenue (IL 43) in Palos Hills, IL. (Northeastern Illi | Safety/Traffic Management | 2010-10-18 | 2011-03-30 | 2010-11-30 | 2011-05-14 | 133000 | 2.010
4020 | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003679 | City of Geneva will add new pavement and do sidewalk repair on Anderson Blvd from IL Route 38 to Gray St. | Pavement Improvement | 2010-09-24 | 2010-10-02 | 2010-11-30 | 2010-11-13 | 294314 | 0.650
4021 | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003686 | City of Montgomery will improve the pavement by resurfacing, patching, curb & gutter & sidewalk replacement on Lakewood Creek Dr from Avalon Ln to US 30. | Pavement Improvement | 2010-09-22 | 2010-09-22 | 2010-11-30 |  | 293097 | 0.580
4022 | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 9251010 | This project will extend the pavement life by milling, patching and resurfacing in Belleville, Illinois (Southwestwest Illinios). | Pavement Improvement | 2009-05-11 | 2009-06-03 | 2009-08-30 | 2009-07-02 | 170311.96 | 0.700
4023 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0003610 | This project will add turn lanes, widen the intersection, and install a new signal at SR 56 and Dubois County Rd 500W. | Safety/Traffic Management | 2009-06-18 | 2009-08-03 | 2010-06-30 | 2010-06-29 | 99623.96 | 0.010
4024 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART |  | 03 | 0013180 | This project will improve drainage by replacing the structure on SR 15 over a branch of Preston Miles' ditch in Elkhart County. | Pavement Improvement | 2009-06-18 | 2009-07-14 | 2009-10-23 | 2009-11-11 | 1041816.68 | 0.010
4025 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0014130 | This project will improve drainage by replacing the structure on US 41 over Jane Feddeler Ditch in Lake County. | Pavement Improvement | 2009-05-13 | 2009-06-24 | 2009-08-31 | 2009-08-22 | 576957.31 | 0.010
4026 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SULLIVAN |  | 08 | 0100974 | This project is a bridge rehabilitation where the wearing surface of the deck will be removed and repalced on SR 154 at the bridge over Turman Creek, 2.17 miles W of SR 63 in Sullivan county. | Bridge Improvement | 2010-03-24 | 2010-04-24 | 2010-11-30 | 2010-11-10 | 591309.71 | 0.010
4027 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | VANDERBURGH | EVANSVILLE (KY) | 08 | 0101271 | This is a road reconstruction project that will widen the road on Oak Hill Rd from US 41 to 0.32 mi N of SR 62 at Pigeon Creek in Vanderburgh county. This is Phase one of a multi-phase improvement to | Pavement Improvement | 2010-01-28 | 2010-02-26 | 2011-06-30 | 2011-07-18 | 5016264.34 | 3.000
4028 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HENRY |  | 06 | 0101426 | This project will improve the surface and rebuild sections of the bridge on SR 109 over I-70 in Henry County. | Bridge Improvement | 2009-07-15 | 2009-07-15 | 2010-10-29 | 2010-10-29 | 1773465.75 | 0.010
4029 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0101500 | This project will improve drainage by replacing the structure on US 6 over Kiefer Ditch in Elkhart County. | Pavement Improvement | 2009-09-09 | 2010-07-08 | 2010-10-01 | 2010-09-30 | 531512.95 | 0.100
4030 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0101530 | This project will add turn lanes and imrpove the intersection at US 33 and SR 109 in Noble County. | Pavement Widening | 2009-06-22 | 2009-08-31 | 2009-11-20 | 2009-11-20 | 376701.01 | 0.100
4031 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0173058 | This project will plant wildflowers and native vegetation along US 41at US 41 and Gibson County Road 550. | Transportation Enhancements | 2009-07-21 | 2009-08-24 | 2010-08-01 | 2009-12-02 | 88281.25 | 0.670
4032 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE, STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0196049 | This project will replace the pavement on US 41 in Lake County from 1 mile south of US12/US20 to north of US12/20 and includes sewer replacement and modernization to provide a new road. | Pavement Improvement | 2010-05-05 | 2010-05-18 | 2010-10-01 | 2010-12-27 | 2322827 | 1.010
4033 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0200067 | This project will improve drainage by replacing the structure over Swygman ditch on US 24 in White County. | Safety/Traffic Management | 2009-11-17 | 2010-01-15 | 2010-04-30 | 2010-04-27 | 48172 | 0.100
4034 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0200071 | This project will improve drainage by replacing the structure on US 24 over Winters ditch in White County. | Safety/Traffic Management | 2009-11-17 | 2010-01-15 | 2010-04-30 | 2010-04-27 | 75432 | 0.100
4035 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | UNION |  | 06 | 0200195 | This project will repair and restore the pavement and replace signs on US 27 from the Ohio State line north 3.6 miles in Union county. | Safety/Traffic Management | 2009-04-15 | 2009-08-05 | 2012-02-10 | 2011-11-16 | 29179.07 | 3.560
4036 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0200364 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Safety/Traffic Management | 2009-06-17 | 2009-07-16 | 2010-08-31 | 2010-09-17 | 37742.17 | 0.020
4037 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY, JOHNSON |  | 05 | 0200539 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | Safety/Traffic Management | 2009-05-12 | 2009-07-22 | 2011-07-11 | 2011-08-04 | 26276.41 | 11.550
4038 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 0200606 | This project will extend the traffic management system of closed circuit TV used for traffic management in Indianapolis. | Safety/Traffic Management | 2009-06-11 | 2009-07-16 | 2010-11-15 |  | 3592423.77 | 18.420
4039 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0200884 | This project will add lanes to SR 1 from I-69 in Allen County to Tonkel Road. | Pavement Widening | 2009-06-01 | 2009-07-15 | 2011-08-13 | 2011-09-29 | 396605.83 | 0.100
4040 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0200890 | This project will improve drainage by replacing the small drainage structure on US 27 over Swartz ditch, 2.9 miles north of SR 218 in Adams County. | Pavement Improvement | 2010-01-21 | 2010-06-22 | 2010-10-30 | 2010-10-20 | 652513.98 | 0.100
4041 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0200894 | This project will improve drainage by replacing the small drainage structure on SR 301 over Vera Cruz Sewer, 0.6 miles north of SR 116 in Wells County. | Pavement Improvement | 2009-08-20 | 2010-05-03 | 2010-08-21 | 2010-06-04 | 240955.15 | 0.010
4042 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0200918 | Bridge Replacement, Concrete on SR427, Bridge over Fish Creek, 3.92 miles N of SR 1 | Bridge Replacement | 2010-12-14 | 2011-03-10 | 2011-10-31 | 2011-10-27 | 526607.52 | 0.040
4043 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WABASH |  | 05 | 0200919 | This project will improve drainage by replacing the small drainage structure on SR 13 over Sharp ditch , 1.8 miles north of US 24 in Wabash County. | Pavement Improvement | 2009-04-17 | 2009-06-10 | 2009-08-07 | 2009-08-26 | 397717.32 | 0.010
4044 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0200932 | This is a bridge rehabilitation project, on SR 101 on the bridge over Maumee River, 1.08 miles N of US 24 in Allen county , where the deck surface is removed and replaced to extend the life of the b | Bridge Improvement | 2009-12-11 | 2010-03-18 | 2010-08-21 | 2010-06-29 | 741966.05 | 0.010
4045 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0200934 | This project will replace the existing bridge with a new wider structure for Dekalb county road 11A over I-69, 2.8 miles S of SR 8. | Bridge Improvement | 2009-11-18 | 2010-04-01 | 2010-11-30 | 2011-05-05 | 3177881.13 | 0.010
4046 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0200987 | This is a trail project to proviide facilities for pedestrians and bicycles project in the city of Bloomington Jackson Creek Trail in Monroe county. This is phase one of a multi phase project and use | Transportation Enhancements | 2010-02-22 | 2010-03-31 | 2010-07-16 | 2010-10-14 | 374753.06 | 0.612
4047 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BENTON |  | 01 | 0201203 | This project will improve the surface and rebuild sections of the bridge on US 41 over KB&S Railroad and US 52 in Benton County. | Bridge Replacement | 2009-04-29 | 2009-05-11 | 2009-11-15 | 2010-04-22 | 1738096.18 | 0.040
4048 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BENTON |  | 01 | 0201204 | This project will improve the surface and rebuild sections of the bridge on US 41 over KB&S Railroad and US 52 in Benton County. | Bridge Replacement | 2009-04-29 | 2009-05-11 | 2009-11-15 | 2010-04-22 | 1153115.9 | 0.040
4049 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 0201213 | This project will improve the surface and rebuild sections of the bridge on SR 75 over Kilmore Creek in Clinton County. | Bridge Improvement | 2009-05-27 | 2009-06-15 | 2009-08-31 | 2009-10-02 | 438235.02 | 0.010
4050 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | OHIO |  | 09 | 0201245 | This project will improve the surface and rebuild sections of the bridge on SR 56 over Laughery Creek in Ohio County. | Bridge Improvement | 2009-05-16 | 2009-07-31 | 2011-08-01 | 2011-09-01 | 5423974.97 | 0.180
4051 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0242029 | This project will add turn lanes, widen the intersection, and install a new signal at SR 56 and Dubois County Rd 500W. | Pavement Widening | 2009-06-18 | 2009-08-03 | 2010-06-30 | 2010-06-29 | 639905.85 | 0.010
4052 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | DE KALB, ALLEN | FORT WAYNE | 03 | 0300084 | This project will improve sections and extend the life of I-69 from 0.86 miles North of SR 1 to 9.87 miles North of SR 1 with a pavement surface overlay. | Pavement Improvement | 2009-08-18 | 2009-08-24 | 2009-10-31 | 2009-11-11 | 2474090.6 | 8.680
4053 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0300092 | This project will improve safety and extend the life of the bridge(s) on County Road 68 over I-69 in DeKalb County. | Bridge Improvement | 2009-04-02 | 2009-04-13 | 2009-08-31 | 2009-08-18 | 438945.26 | 0.100
4054 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0300093 | This project will improve safety and extend the life of the bridge(s) on County Road 60 over I-69 in DeKalb County. | Bridge Improvement | 2009-04-02 | 2009-04-13 | 2009-08-31 | 2009-08-18 | 307061.66 | 0.100
4055 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0300556 | This project will build a new bridge over Richland Creek on SR54, 1.32 miles E US 231 in Green county, east of Bloomfield to improve drainage and load carrying capacity. | New Bridge Construction | 2010-03-24 | 2010-04-28 | 2011-11-05 |  | 667110.13 | 0.010
4056 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300758 | This is a safety project, at 121st Street and US 41 in Hammond, Lake county, to modernize the traffic signals . | Safety/Traffic Management | 2010-05-05 | 2010-05-18 | 2010-10-01 | 2010-12-27 | 69253.48 | 0.010
4057 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300759 | This is a safety project, at 119st Street and US 41 in Hammond, Lake county, to modernize the traffic signals in conjunction with the street modernization project. | Safety/Traffic Management | 2010-05-05 | 2010-05-18 | 2010-10-01 | 2010-12-27 | 60730.15 | 0.010
4058 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300760 | This is a safety project ,at 117th Street at US 41 in Lake Co perform Traffic Signals Modernization work in conjunction with the ARRA street modernization contract. | Safety/Traffic Management | 2010-05-05 | 2010-05-18 | 2010-10-01 | 2010-12-27 | 41911.33 | 0.350
4059 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300761 | This is a Safety project,at US 12/20 (Indianapolis Blvd.)/114th Street (Sec V); to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-05-05 | 2010-05-18 | 2010-10-01 | 2010-12-27 | 107604.5 | 0.040
4060 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0300942 | This project will rebuild the US 20 and I-69 interchange in Steuben county to improve traffic flow. | Pavement Widening | 2009-06-01 | 2009-06-12 | 2010-10-15 | 2010-10-12 | 3676824.73 | 0.690
4061 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0301057 | This project will improve safety and extend the life of the bridge(s) on SR 10 over Clarence Baker Ditch in Marshall County. | Bridge Improvement | 2009-04-17 | 2009-06-08 | 2009-11-22 | 2009-07-16 | 214456.84 | 0.010
4062 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0301140 | This is a Reconstruction (no added capacity) project, at SR 19 - Branch of Armey Ditch, 11.1 miles N of US 30; to perform Small Structure Replacement work. | Pavement Improvement | 2009-12-30 | 2010-06-15 | 2010-08-13 | 2010-07-22 | 339672.7 | 0.100
4063 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0301152 | This is a Small Structure project, at Over Dennis Ditch, 1.7 miles N of Lafayette Center interchange; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-09-20 | 2010-10-02 | 2010-10-25 | 161900 | 0.100
4064 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PARKE |  | 08 | 0322001 | This project will improve drainage by repairing pipes in Parke County 3 miles South of SR 234. | Pavement Improvement | 2009-07-22 | 2009-09-11 | 2010-08-30 | 2010-08-27 | 679684.15 | 0.130
4065 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0400133 | This project will replace and restore the pavement on Michigan Road in Jefferson County near the Town of Madison. | Pavement Improvement | 2009-07-15 | 2009-09-09 | 2010-06-07 | 2010-09-20 | 1233716 | 0.750
4066 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 04 | 0400322 | This project will improve the surface and rebuild sections of the bridge on SR 37 over the abandoned Railroad, 3.5 miles South of SR 45 in Monroe County. | Bridge Improvement | 2009-05-13 | 2009-06-12 | 2010-06-26 | 2010-05-10 | 697938.5 | 0.010
4067 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0400324 | This project will improve the surface and rebuild sections of the bridge on SR 37 over the abandoned Railroad, 3.5 miles South of SR 45 in Monroe County. | Bridge Improvement | 2009-05-13 | 2009-06-12 | 2010-06-26 | 2010-05-10 | 671638.17 | 0.010
4068 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | OWEN |  | 08 | 0400568 | This project will correct a slide condition along SR 243 south of the Owen / Putnam County line. | Pavement Improvement | 2009-07-22 | 2009-09-24 | 2010-09-30 | 2010-06-30 | 472233.66 | 0.070
4069 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT, HUNTINGTON |  | 05 | 0400614 | This project will improve sections and extend the life of I-69 from 1.84 mi S of Huntington Co Ln to 1.55 mi South of SR 124 with a pavement surface overlay. | Pavement Improvement | 2009-07-07 | 2009-08-12 | 2009-10-24 | 2009-10-06 | 2012104.66 | 7.320
4070 | Underway | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0400711 | This is a reconstruction project, at Cline Ave from Ridge Rd to 45th St., to perform intersection improvements adding turn lanes for better traffic flow and safety. | Pavement Improvement | 2010-04-15 | 2010-04-27 | 2011-05-31 |  | 4056240.33 | 0.860
4071 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0400997 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 |  | 1288872.55 | 0.010
4072 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0400999 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 |  | 641003.28 | 0.120
4073 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0401000 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2011-11-23 | 1193676.61 | 0.120
4074 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE, BENTON |  | Multiple | 0401007 | This project will improve sections and extend the life of US 52 in Benton county from SR 352 to US 231 with a asphalt preventive maintenance surface overlay. | Pavement Improvement | 2009-03-24 | 2009-04-15 | 2009-11-15 | 2009-11-23 | 3823682.05 | 11.340
4075 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0401105 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge over Perry-Oakley Ditch, 1.09 miles N of US 27; to perform Bridge Rehabilitation Or Repair work. | Bridge Improvement | 2010-03-25 | 2010-05-10 | 2010-10-30 | 2010-10-21 | 207259.77 | 0.100
4076 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0401139 | This project will improve the surface and rebuild sections of the bridge on SR 258 over White River in Jackson County. | Bridge Improvement | 2009-06-05 | 2009-06-08 | 2009-10-16 | 2009-09-15 | 996973.79 | 0.010
4077 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0401149 | This is a Small Structure project, at SR 39 - 1.25 miles N of E jct of SR 10; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-06-08 | 2010-06-30 | 2010-07-14 | 43140 | 0.010
4078 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0401150 | This is a Small Structure project, at SR 39 - 2.25 miles N of E jct of SR 10; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-06-08 | 2010-06-30 | 2010-07-14 | 37500 | 0.010
4079 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | DE KALB, ALLEN | FORT WAYNE | 03 | 0401216 | This project will improve drainage by repairing pipes on I-69 from 0.86 miles North of SR 1 to 9.87 miles North of SR 1 in Allen and Dekalb Counties. | Pavement Improvement | 2009-08-18 | 2009-08-24 | 2009-10-31 | 2009-11-11 | 976353.5 | 8.680
4080 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0401287 | This project will beautify the roadside by planting native grasses and wildflowers along US 52 near the SR 443 bridge and Happy Hollow Road in West Lafayette. | Transportation Enhancements | 2009-06-09 | 2009-07-01 | 2011-06-30 | 2009-12-07 | 30682.26 | 0.010
4081 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0426013 | This project will improve sections and extend the life of US 50 from SR 37 to "E" street in Bedford, Lawrence county with a preventive maiantenance asphalt overlay. | Pavement Improvement | 2009-03-23 | 2009-04-20 | 2009-08-29 | 2009-08-20 | 976603.3 | 1.770
4082 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0431065 | This project will plant wildflowers and native vegetation along SR 67 south of Bruceville in Knox County. | Transportation Enhancements | 2009-07-21 | 2009-08-24 | 2010-08-01 | 2010-05-19 | 29733.7 | 0.280
4083 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0452010 | This project will add lanes to SR 1 from I-69 in Allen County to Tonkel Road. | Pavement Widening | 2009-06-01 | 2009-07-15 | 2011-08-13 | 2011-09-29 | 11015315.64 | 1.850
4084 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0500283 | This project will improve sections and extend the life of SR 39 in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-08-18 | 2009-08-29 | 2009-11-15 | 2009-10-31 | 1341695.75 | 7.110
4085 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0500597 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 |  | 24555851.35 | 0.120
4086 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0500819 | This project will build a new the bike and pedestrian facilities on Tracy Trail from Summerfield Park to Craig Park in the Greenwood area in Johnson county. | Transportation Enhancements | 2009-12-16 | 2010-03-22 | 2010-10-29 | 2010-11-05 | 829013 | 0.010
4087 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | VANDERBURGH | EVANSVILLE (KY) | 08 | 0500938 | This project will plant wildflowers and native vegetation along I-164 at I-164 and SR 62 in Vanderburgh County. | Transportation Enhancements | 2009-07-21 | 2009-08-21 | 2010-08-01 | 2010-04-16 | 51846.75 | 0.170
4088 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0500965 | This project will replace and restore the pavement on Brown Avenue, from Wabash Avenue to Locust Street, in Vigo County. | Pavement Widening | 2009-09-15 | 2009-10-06 | 2010-06-30 | 2011-03-24 | 1536019.28 | 0.380
4089 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0501203 | HMA Overlay, Preventive Maintenance on I469, From I-69 N Jct to 4.25 miles E of I-69 (Bridge over Wheelock Road). | Pavement Improvement | 2010-12-22 | 2011-05-19 | 2011-10-15 | 2011-08-17 | 892857.77 | 4.260
4090 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | BOONE | INDIANAPOLIS | 04 | 0501249 | This is a Maintenance Resurfacing project, at I-65 to I 465; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-02-19 | 2010-05-24 | 2010-10-30 | 2010-09-01 | 2606019 | 4.130
4091 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0565014 | This project will replace a large culvert with a new bridge on SR54 as part of contract SB-30551 reconstruction project at the bridge over Ritter Ditch, East of US 231 in Greene County. | Pavement Widening | 2010-03-24 | 2010-04-28 | 2011-11-05 |  | 923845.75
4092 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLAY |  | 08 | 0600085 | This project will improve sections and extend the life of SR 246 from SR 159 to SR 157 in Clay County with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-05-11 | 2009-06-30 | 2009-07-01 | 815276.57 | 6.620
4093 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0600233 | This project will improve sections and extend the life of Sr 3 with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-06-02 | 2009-08-07 | 2009-07-23 | 1318239.42 | 10.940
4094 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD | KOKOMO | 05 | 0600338 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Construction | 2009-06-01 | 2009-07-10 | 2011-06-15 | 2011-06-15 | 8918680.32 | 2.000
4095 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0600501 | This project repairs a drainage pipe on SR 39 , 1.48 miles south of SR 8 in Starke county by re-lining the culver instead of replacing it. | Other | 2010-04-14 | 2010-06-08 | 2010-06-30 | 2010-07-14 | 37500 | 0.010
4096 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD | KOKOMO | 05 | 0600566 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Bridge Construction | 2009-06-01 | 2009-07-10 | 2011-06-15 | 2011-06-15 | 1734801.49 | 0.010
4097 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0600605 | This project will improve sections and extend the life of SR 48 from Curry Pike to E of SR 37 in Bloomington with a pavement surface overlay. | Pavement Improvement | 2009-04-15 | 2009-05-08 | 2009-08-02 | 2009-08-17 | 512306.74 | 0.560
4098 | Underway | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0600651 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | New Construction | 2009-05-26 | 2009-06-23 | 2010-11-15 |  | 9669603.35 | 0.010
4099 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0600653 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | Bridge Replacement | 2009-05-26 | 2009-06-23 | 2010-11-15 |  | 2431747.71 | 0.070
4100 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0600654 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | Bridge Replacement | 2009-05-26 | 2009-06-23 | 2010-11-15 |  | 2457379.37 | 0.010
4101 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE, BROWN |  | 09 | 0600667 | This is a project repairs drainage pipes under SR 46 in various locations in Seynour district by relining the old culverts instead of replacing them. | Safety/Traffic Management | 2010-03-01 | 2010-03-26 | 2010-07-30 | 2010-05-25 | 144294.15 | 15.000
4102 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0600803 | This project will improve drainage by replacing the structure on US 231, 3 miles South of the South junction with SR 32 in Montgomery County. | Pavement Improvement | 2009-03-24 | 2009-05-18 | 2009-06-13 | 2009-06-09 | 45853.99 | 0.200
4103 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | OWEN |  | 08 | 0621004 | This is a bridge replacement at the bridge over Meadow Brook Creek on US 231 south of SR 46 in Owen county to replace a deficient bridge | Bridge Replacement | 2010-04-09 | 2010-09-27 | 2010-09-17 | 2011-04-18 | 620500 | 0.010
4104 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY, JOHNSON |  | Multiple | 0684011 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | Pavement Widening | 2009-05-12 | 2009-07-22 | 2011-07-11 | 2011-08-04 | 13291723.99 | 11.280
4105 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0710027 | This proejct will extend the pavement life on SR 23 in St Joseph county from SR 933 to Campeau St ; by doing asphalt resurface preventive maintenance work. | Pavement Improvement | 2010-02-22 | 2010-03-29 | 2010-07-31 | 2010-06-30 | 874458 | 2.190
4106 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710031 | This project will improve sections and extend the life of US 20 in East Chicago with a pavement surface overlay. | Pavement Improvement | 2009-06-17 | 2009-07-21 | 2009-09-30 | 2009-11-21 | 1641443.95 | 2.560
4107 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710034 | This project will improve the pavement on SR 149 from the junstion of SR 130 to the junction of US 20. | Pavement Improvement | 2009-04-08 | 2009-05-04 | 2009-11-13 | 2009-07-27 | 1362731.25 | 5.130
4108 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0710040 | This project will improve sections and extend the life of SR-23 from SR 4 to Olive Street in St Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-06-05 | 2009-08-14 | 2009-11-01 | 2009-10-16 | 1593244.25 | 11.790
4109 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PULASKI |  | 02 | 0710042 | This project will improve sections and extend the life of US 35 from SR 14 to SR 10 in Pulaski County with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-05-18 | 2009-10-16 | 2009-08-05 | 1407322.75 | 10.030
4110 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0710043 | This project will improve sections and extend the life of US 24 from the north junction with US 35 to the south junction with US 35 and on SR 29 from US 24 to Burlington Ave. near Logansport in Cass C | Pavement Improvement | 2009-03-23 | 2009-05-07 | 2009-07-31 | 2009-07-29 | 1651219.54 | 1.610
4111 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH |  | 02 | 0710044 | This is a Maintenance Resurfacing project , From Georgia St in Walkerton to US 31 to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-03-04 | 2010-06-15 | 2010-08-31 | 2010-08-31 | 3085070.82 | 9.240
4112 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0710046 | This project will extend the pavement lief on SR 10 - from SR 110 to US 231 by doing asphalt resurface preventive maintenance work. | Pavement Improvement | 2010-04-08 | 2010-04-23 | 2010-06-18 | 2010-06-15 | 647470.4 | 6.210
4113 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710053 | This project will improve sections and extend the life of US 30 in Lake County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-02 | 2009-11-15 | 2010-05-11 | 3318981.34 | 5.390
4114 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710054 | This project will improve sections and extend the life of US 41 from US 231 to 77th Ave with a pavement surface overlay. | Pavement Improvement | 2009-08-27 | 2009-09-04 | 2009-10-31 | 2009-11-16 | 1668661.62 | 3.990
4115 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE |  | 01 | 0710058 | This project will improve sections and extend the life of SR 53 from 93rd Ave to South of 73rd Ave with a pavement surface overlay. | Pavement Improvement | 2009-05-13 | 2009-08-03 | 2009-10-16 | 2009-10-12 | 891077.64 | 2.430
4116 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0710074 | This project will stop erosion and correct a slide occurring on the west side of US 50 south of the East Fork White River Bridge in lawrence County. | Safety/Traffic Management | 2009-06-04 | 2009-07-23 | 2009-08-14 | 2009-08-05 | 162340.8 | 0.100
4117 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0710107 | This project will improve safety and extend the life of the bridge(s) on Hursh Road over I-69 in Allen County. | Bridge Improvement | 2009-04-02 | 2009-04-13 | 2009-08-31 | 2009-08-18 | 277824.96 | 0.010
4118 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0710108 | This is a preventive maintenance resurfacing project, on SR 57 - From 1.32 miles North of junction of US 50/US 150 to the sounth junction of SR 58 to do a thin asphalt resurface to extend the life of | Pavement Improvement | 2009-11-18 | 2010-02-25 | 2010-10-01 | 2010-09-30 | 3378948.72 | 38.320
4119 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0710115 | This project will extend the service life of the pavement on I-65, 2 mile north of US 321 to north of SR 14 in Jasper county with a preventive maintenance resurfacing project. | Pavement Improvement | 2009-09-15 | 2009-10-22 | 2010-08-20 | 2010-07-22 | 3009802.03 | 9.750
4120 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0710141 | This project will improve safety and extend the life of the bridge(s) on I-69 over Wabash River in Huntington County. | Bridge Improvement | 2009-05-13 | 2009-07-07 | 2009-10-31 | 2010-08-06 | 1452773.4 | 0.040
4121 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0710144 | This project will install new cable barrier in the median along I-69 in Dekalb County to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-05-16 | 2009-08-05 | 2009-10-31 | 2009-10-14 | 378646.31 | 4.320
4122 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VIGO, HENDRICKS, MORGAN |  | Multiple | 0710147 | This project will install new cable barrierin the median on I-70 in Vigo, Hendricks, and Morgan Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-06-10 | 2009-07-23 | 2009-09-12 | 2009-10-20 | 1038142.84 | 4.480
4123 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS, MARION |  | Multiple | 0710148 | This project will install new cable barrier in the median along I-74 in Hendricks and Marion Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-04-29 | 2009-06-04 | 2009-07-31 | 2009-07-31 | 546197.09 | 7.780
4124 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK, SHELBY, JOHNSON, JACKSON |  | Multiple | 0710150 | This project will install new cable guardrail in the median along I-65 in Johnson and Shelby Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-06-15 | 2009-06-26 | 2009-10-31 | 2009-10-21 | 3562796.08 | 89.630
4125 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD |  | 09 | 0710151 | This project will install new cable guardrailin the median along I-64 in Floyd County to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-06-15 | 2009-06-26 | 2009-10-31 | 2009-10-21 | 247197.71 | 9.840
4126 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK, FLOYD |  | 09 | 0710152 | This project will install new cable guardrail in the median along I-265 in Clark and Floyd Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-06-15 | 2009-06-26 | 2009-10-31 | 2009-10-21 | 465639.47 | 12.030
4127 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0710163 | This project will improve sections and extend the life of I-465 in Marion county with a pavement surface overlay from 3.23 miles North of I-74 to 5.12 miles North of I-74. | Pavement Improvement | 2009-06-16 | 2009-07-30 | 2009-11-15 | 2009-09-30 | 1453090.31 | 1.900
4128 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SWITZERLAND |  | 09 | 0710169 | This project will improve sections and extend the life of SR 56 from Oday Road to Rio Vista Lane in Switzerland county with a pavement surface overlay. | Pavement Improvement | 2009-10-07 | 2010-05-11 | 2010-08-13 | 2010-08-09 | 2096135.96 | 21.050
4129 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0710203 | This is a Safety project, at Parkside School sidewalk - This is a 2006 Safe Routes to School (SRTS) project that beyond the avaialbe funding of the SRTS program that will provide sidewalks to Parkside | Safety/Traffic Management | 2009-11-30 | 2010-04-26 | 2010-06-19 | 2010-06-18 | 159604.78 | 0.010
4130 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0710285 | This project will extend the pavement life on SR 157 from north of US 231 to the jct with SR 48 in Greene county by doing asphalt resurface with 2 layers | Pavement Improvement | 2009-10-14 | 2009-10-21 | 2009-11-15 | 2009-11-14 | 474251.94 | 2.410
4131 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS, KNOX |  | 08 | 0710390 | This project will improve sections and extend the life of SR 58 from SR 67 to SR 57 in Knox and Daviess Counties with a pavement surface overlay. | Pavement Improvement | 2009-03-23 | 2009-07-08 | 2009-09-20 | 2009-09-17 | 886313.48 | 6.390
4132 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0710394 | This project will improve sections and extend the life of US 231 from just north of US 136 in Crawfordsville to 1/2 mile north of I-74 in Montgomery County with a pavement surface overlay. | Pavement Improvement | 2009-06-03 | 2009-06-23 | 2009-11-06 | 2009-12-05 | 2918726.09 | 3.130
4133 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT, JACKSON |  | 09 | 0710432 | This project will improve sections and extend the life of US 31 from SR 56 to SR 250 in Jackson and Scott Counties with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-04-03 | 2009-11-16 | 2009-09-14 | 1526188.61 | 12.970
4134 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) |  | 0710470 | This project will install new signal loop detectors to improve traffic flow at 5 intersection along US 30 in Northwest Indiana | Safety/Traffic Management | 2009-04-14 | 2009-05-29 | 2009-08-31 | 2009-11-14 | 350684.29 | 0.020
4135 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK, MADISON |  | Multiple | 0710492 | This project will improve sections and extend the life of SR 9 in Hancock and Madison Counties with a pavement surface overlay. | Pavement Improvement | 2009-06-02 | 2009-07-10 | 2009-08-28 | 2009-08-28 | 1556750 | 10.810
4136 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0710502 | This project will improve sections and extend the life of SR 3 from South junction with SR 7 South of Vernon to US 50 with a pavement surface overlay. | Pavement Improvement | 2009-05-13 | 2009-06-20 | 2009-08-31 | 2009-08-14 | 528503.93 | 1.580
4137 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) |  | 0710510 | This project will install new signal loop detectors to improve traffic flow at 5 intersection along US 30 in Northwest Indiana | Safety/Traffic Management | 2009-04-29 | 2009-05-18 | 2009-08-31 | 2009-10-22 | 259019.3 | 0.020
4138 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK |  | 05 | 0710541 | This project will improve sections and extend the life of US 40 with a pavement surface overlay. | Pavement Improvement | 2009-06-02 | 2009-06-27 | 2009-08-07 | 2009-08-06 | 820500 | 3.120
4139 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI |  | 05 | 0710581 | This project will improve the surface and rebuild sections of the bridge on US 31 over the abandoned CSX Railroad, 1 miles South of US 50 in Ohio County. | Bridge Replacement | 2009-04-17 | 2009-04-22 | 2010-06-26 | 2009-11-22 | 302275.53 | 0.010
4140 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI |  | 05 | 0710582 | This project will improve the surface and rebuild sections of the bridge on US 31 over the abandoned CSX Railroad, 1 miles South of US 50 in Ohio County. | Bridge Replacement | 2009-04-17 | 2009-04-22 | 2010-06-26 | 2009-11-22 | 725926.81 | 0.010
4141 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON, BOONE |  | 04 | 0710622 | This project will improve sections and extend the life of I-65 with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-04-20 | 2009-10-31 | 2009-10-30 | 4238380.65 | 9.780
4142 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0710650 | This project will patch deteriorated pavement areas and seal cracks on SR 37 near Mitchell. | Pavement Improvement | 2009-03-31 | 2009-05-05 | 2009-09-18 | 2009-06-30 | 398694.16 | 8.010
4143 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0710670 | This project will improve sections and extend the life of US 31 from SR 252 to Youngs Creek Bridge in Johnson county with a pavement surface overlay. | Pavement Improvement | 2009-08-18 | 2010-03-24 | 2010-08-13 | 2010-07-15 | 1567134.24 | 12.570
4144 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0710694 | This project will improve sections and extend the life of SR 56 in Washington County with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-04-02 | 2009-08-01 | 2009-07-23 | 989946.05 | 9.870
4145 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0710700 | This is a Maintenance Resurfacing project, at US 50 - 6.08 miles W of SR 241 to 1.88 miles E of SR 241; to perform PCCP Cleaning and Sealing Joints work. | Pavement Improvement | 2009-10-23 | 2010-04-01 | 2010-08-28 | 2010-08-18 | 640854.6 | 7.860
4146 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0710823 | This project will improve sections and extend the life of SR 54 from SR 58 to SR 37 with a pavement surface overlay. | Pavement Improvement | 2009-07-07 | 2010-05-10 | 2010-11-01 | 2010-10-04 | 650211.09 | 10.470
4147 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WARRICK |  | 08 | 0710824 | This project will improve sections and extend the life of SR 61 from 0.8 Mi. N of SR 62 to S of SR 68 in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-04-28 | 2009-12-18 | 2009-09-18 | 1531554.06 | 10.130
4148 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0710833 | This project will improve sections and extend the life of SR 1 in Steuben County with a pavement surface overlay. | Pavement Improvement | 2009-06-05 | 2009-08-19 | 2009-10-31 | 2009-10-31 | 1339756.9 | 12.920
4149 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PIKE |  | 08 | 0710835 | This project will improve sections and extend the life of SR 56 from South junction with SR 61 to SR 257 in Pike county with a preventive maintenance pavement surface overlay. | Pavement Improvement | 2009-06-16 | 2009-09-08 | 2010-06-30 | 2010-06-04 | 1266971.48 | 8.310
4150 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0710839 | This is a Maintenance Resurfacing project, From 5.49 miles W of SR 15 -W jct (Middleton Run Rd), to 0.10 miles W of SR 13; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-04-26 | 2010-05-17 | 2010-10-01 | 2010-10-12 | 3807660.75 | 11.890
4151 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0710840 | This is a Safety project, at SR-218 1163' E of CR 600E (EB) 24+64 and 70' E of Maple Street (WB) 25+11; to perform New Flasher Installation work. | Safety/Traffic Management | 2010-02-22 | 2010-03-12 | 2010-04-30 | 2010-03-18 | 12462.5 | 0.470
4152 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HARRISON | LOUISVILLE (KY)-IN | 09 | 0710884 | This project will extend the bridge life by repainting bridge beams at I-64 over Blue River and Blue Road in Harrison County. | Bridge Improvement | 2009-06-19 | 2010-02-19 | 2010-08-28 | 2010-04-15 | 446999.59 | 0.010
4153 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0710886 | This project will improve sections and extend the life of SR 19 near the I-80/I-90 Toll Road in Elkhart Co. with a pavement surface overlay. | Pavement Improvement | 2009-06-05 | 2009-07-16 | 2009-10-02 | 2009-09-30 | 1764668.42 | 2.790
4154 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0710888 | This project will extend the life of the pavement on SR 19 from I-80/90 Toll Road to the Michigan state line by resurfcing the road with 2 lays of asphalt overlay. | Pavement Improvement | 2010-04-08 | 2010-05-10 | 2010-10-08 | 2010-07-29 | 1864577.13 | 1.690
4155 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0710917 | This project will upgrade and improve the traffic signals at US 231 and the SR 32/ SR 47 junction in Montgomery County. | Safety/Traffic Management | 2009-06-09 | 2009-06-30 | 2009-06-27 | 2009-07-14 | 23230.1 | 0.020
4156 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BLACKFORD |  | 06 | 0710921 | This project will improve sections and extend the life of SR 26 from 0.84 mile East of SR 3(Little Lick Creek) to SR 167 with a pavement surface overlay. | Pavement Improvement | 2009-06-02 | 2009-08-24 | 2009-11-13 | 2009-11-13 | 775559.91 | 7.140
4157 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0710928 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge over Limberlost Creek, 2.37 miles N of US 27, East of Bryant; to perform Bridge Deck Reconstruction & Widening work. | Bridge Improvement | 2010-03-25 | 2010-05-10 | 2010-10-30 | 2010-10-21 | 1007811.33 | 0.010
4158 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0710933 | This project will improve sections and extend the life of SR 26 from SR 13 to I-69 with a pavement surface overlay. | Pavement Improvement | 2009-08-27 | 2009-09-15 | 2009-10-16 | 2009-10-26 | 1188917.56 | 14.420
4159 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD | KOKOMO | 05 | 0710943 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Bridge Construction | 2009-06-01 | 2009-07-10 | 2011-06-15 | 2011-06-15 | 774131.29 | 0.010
4160 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL, HOWARD |  | Multiple | 0710948 | This project will improve sections and extend the life of SR 22 from SR 29 to 11.48 miles East of SR 29 with a pavement surface overlay. | Pavement Improvement | 2009-06-16 | 2009-08-07 | 2009-11-13 | 2009-10-17 | 1738179.77 | 11.510
4161 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | HARRISON |  | 09 | 0711000 | This project will move the Historic Rothrock Mill bridge from it's current location to storage for preservation purposes. | Transportation Enhancements | 2009-06-19 | 2009-07-13 | 2009-08-15 | 2009-07-27 | 41800.09 | 0.010
4162 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0711020 | This project will improve sections and extend the life of US 24 with a pavement surface overlay. | Pavement Improvement | 2009-04-15 | 2009-05-30 | 2009-07-31 | 2009-06-25 | 394030 | 1.350
4163 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0711022 | This project will improve sections and extend the life of SR 15 with a pavement surface overlay. | Pavement Improvement | 2009-03-24 | 2009-05-01 | 2009-07-17 | 2009-07-16 | 315308.54 | 0.990
4164 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE, STATEWIDE |  | 03 | 0711024 | This project will improve sections and extend the life of SR 9 with a pavement surface overlay. | Pavement Improvement | 2009-03-31 | 2009-05-26 | 2009-10-31 | 2009-09-17 | 555377.21 | 1.830
4165 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ORANGE |  | 09 | 0800005 | This project will improve drainage by repairing pipes at SR 145, between 1.6 Miles North TO 9.8 Miles North of SR 164 in Orange County. | Pavement Improvement | 2009-04-13 | 2009-05-14 | 2009-10-30 | 2009-06-29 | 258979.75 | 8.180
4166 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0800006 | This project will improve sections and extend the life of SR 164 with a pavement surface overlay. | Pavement Improvement | 2009-04-30 | 2009-06-08 | 2009-09-18 | 2009-08-14 | 173051.83 | 0.930
4167 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0800086 | This project will improve sections and extend the life of SR 62 from IL/IN State line to 1.96 miles East of SR 69 with a pavement surface overlay. | Pavement Improvement | 2009-07-23 | 2010-03-23 | 2010-11-10 | 2010-08-31 | 1571712.39 | 8.760
4168 | Underway | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0800101 | Bridge Replacement, Other Construction on I465, EB 82nd Street over I-465 | Bridge Replacement | 2010-11-01 | 2010-12-28 | 2011-10-15 |  | 1470000 | 0.010
4169 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0800122 | This is a Maintenance Resurfacing project, at SR 56 - Jct with SR 257 to the W jct of US 231; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2010-03-19 | 2010-07-01 | 2010-07-13 | 1187302.65 | 10.120
4170 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0800125 | This project will improve sections and extend the life of US 50 from 4.09 miles East of SR 37 to junction with SR 446 with a pavement surface overlay. | Pavement Improvement | 2009-07-07 | 2010-05-10 | 2010-11-01 | 2010-10-04 | 688431.96 | 5.560
4171 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0800142 | This is a Small Structure project, at Over the ditch at the Interchange, 0.15 miles N of I-469 S jct; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-09-20 | 2010-10-02 | 2010-10-25 | 593400 | 0.010
4172 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0800158 | This project will improve sections and extend the life of US-6 from SR 19 to SR 15 in Elkhart County with a pavement surface overlay. | Pavement Improvement | 2009-06-03 | 2009-07-08 | 2009-10-09 | 2009-10-07 | 956280.17 | 6.970
4173 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0800162 | This project will improve sections and extend the life of US 41 in Huntington County with a pavement surface overlay | Pavement Improvement | 2009-07-06 | 2009-08-19 | 2009-10-23 | 2009-11-04 | 2202419 | 8.800
4174 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WABASH, WHITLEY |  | Multiple | 0800176 | This is a Maintenance Resurfacing project, at SR 114 - From 1.66 miles E of SR 13 (EEL River) to SR 105; to perform asphalt resurface, Functional work. | Pavement Improvement | 2009-12-10 | 2010-04-09 | 2010-08-13 | 2010-08-12 | 1890052.25 | 7.390
4175 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0800177 | This project will improve sections and extend the life of SR 227 from CSX R/R to US 27 with a pavement surface overlay. | Pavement Improvement | 2009-07-22 | 2009-08-20 | 2009-11-20 | 2009-11-04 | 487282.15 | 2.870
4176 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0800191 | This project will improve sections and extend the life of US 27 from. 1.12 miles North of I-70 at East fork of Whitewater River to 5.71 miles North of I-70 at Fountain Circle with a pavement surface o | Pavement Improvement | 2009-07-22 | 2009-08-20 | 2009-11-20 | 2009-11-20 | 895000.12 | 3.960
4177 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0800196 | This project will improve lighting on I-69 at Airport Expressway in Allen County. | Safety/Traffic Management | 2009-07-10 | 2009-08-18 | 2009-11-30 | 2009-11-13 | 71877.05 | 0.760
4178 | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | HENRY |  | 06 | 0800200 | This project is road surface treatment for US 36 in Greenfield District, from 3.67 miles west of State Road 3 to west ramps of State Road 3. | Pavement Improvement | 2009-08-25 | 2009-09-04 | 2009-10-16 | 2009-10-16 | 527700 | 3.590
4179 | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0800203 | This project will improve sections and extend the life of US 27 in the Town of Portland with a pavement surface overlay. | Pavement Improvement | 2009-07-07 | 2009-08-20 | 2009-10-15 | 2009-11-07 | 652936.73 | 5.160
4180 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0800219 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge # 12-64-05413-A (WBL) over Burns Ditch (0.94 miles W of SR 249); to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2010-03-23 | 2010-10-01 | 2011-07-15 | 2011-07-30 | 1843982.32 | 0.010
4181 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0800220 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge # 12-64-05413-A (EBL) over Burns Ditch (0.94 miles W of SR 249); to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2010-03-23 | 2010-10-01 | 2011-07-15 | 2011-07-30 | 1133827.62 | 0.010
4182 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 0800237 | This project will extend the bridge life by repainting bridge beams at various locations in Crawfordsville. | Bridge Improvement | 2009-04-25 | 2009-05-28 | 2009-09-30 | 2009-08-25 | 434958.8 | 0.010
4183 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0800260 | This project will improve sections and extend the life of US 35 from 1.65 miles East of SR 15 (10th St) to 0.24 miles East of I-69 and on SR 22 with a pavement surface overlay. | Pavement Improvement | 2009-06-16 | 2009-08-26 | 2009-10-24 | 2009-10-24 | 739294.69 | 7.200
4184 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0800389 | This project will patch deteriorated pavement areas and seal cracks on US 31 4.11 mi. N of SR 250 in Jackson County. | Pavement Improvement | 2009-03-26 | 2009-06-09 | 2009-07-15 | 2009-07-10 | 146826.45 | 0.960
4185 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0800434 | This project will improve sections and extend the life of SR 10 with a pavement surface overlay. | Pavement Improvement | 2009-04-09 | 2009-05-12 | 2009-06-26 | 2009-06-05 | 332090.99 | 7.990
4186 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL | SOUTH BEND (MI) | 02 | 0800438 | This project will improve sections and extend the life of SR 17 with a pavement surface overlay. | Pavement Improvement | 2009-04-16 | 2009-09-08 | 2009-11-01 | 2009-10-21 | 292790.44 | 1.680
4187 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0800439 | This project will improve sections and extend the life of SR 23 with a pavement surface overlay. | Pavement Improvement | 2009-04-16 | 2009-07-10 | 2009-11-06 | 2009-08-04 | 241745.43 | 6.480
4188 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0800440 | This project will improve sections and extend the life of SR 16 with a pavement surface overlay. | Pavement Improvement | 2009-04-16 | 2009-05-18 | 2009-06-30 | 2009-06-26 | 474528.03 | 14.400
4189 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0800475 | This project will improve sections and extend the life of SR 25 with a pavement surface overlay. | Pavement Improvement | 2009-03-24 | 2009-05-01 | 2009-07-17 | 2009-07-16 | 164391.63 | 0.570
4190 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW | COLUMBUS | 06 | 0800516 | This project will add turn lanes, nodernize the signal, and widen the intersection at SR 11and Bartholomw county Road 450S. | Safety/Traffic Management | 2009-05-06 | 2009-06-01 | 2010-08-15 | 2010-11-01 | 41055.8 | 0.010
4191 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0800517 | This project will install fiber optic lines from the Indianapolis Traffic Management Center to downtown Indianapolis to improve the closed circuit TV system used for traffic management. | Safety/Traffic Management | 2009-06-11 | 2009-06-29 | 2010-05-28 | 2010-03-18 | 714614.44 | 7.620
4192 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0800753 | This project will improve sections and extend the life of SR 245 from junction with SR 70 to 3.50 miles South of SR 162 with a pavement surface overlay. | Pavement Improvement | 2009-07-23 | 2010-03-01 | 2011-11-01 | 2010-10-01 | 640303.87 | 9.030
4193 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0800766 | This project will improve sections and extend the life of SR 161 from Ky State Line to SR 66 with a pavement surface overlay. | Pavement Improvement | 2009-07-23 | 2010-03-01 | 2011-11-01 | 2010-10-01 | 1807885.98 | 8.290
4194 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0800817 | This project will improve sections and extend the life of SR 168 from US 41 to SR 57 with a pavement surface overlay. | Pavement Improvement | 2009-07-23 | 2009-08-26 | 2010-05-31 | 2009-11-04 | 1478864.47 | 9.400
4195 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0800821 | This project will improve sections and extend the life of SR 69 from 2.48 miles South of West junction with SR 66 to 0.1 miles North of I-64 with a pavement surface overlay. | Pavement Improvement | 2009-07-09 | 2009-08-06 | 2010-08-01 | 2009-11-25 | 1307218.59 | 8.840
4196 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE, WHITE | LAFAYETTE-WEST LAFAYETTE | 04 | 0800831 | This project will improve sections and extend the life of SR 43 in Tippecanoe & White Counties with a pavement surface overlay | Pavement Improvement | 2009-04-09 | 2009-08-20 | 2009-07-31 | 2009-10-10 | 373458.7 | 4.760
4197 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WELLS, ALLEN |  | Multiple | 0800939 | This is a Maintenance Resurfacing project, at From 2.44 miles N of US 224 (CR850N, Ossian, Wells Co) to I-469 (Allen Co); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-18 | 2010-09-02 | 2010-11-06 | 2010-11-19 | 1273931.28 | 6.040
4198 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0800962 | This project will extend the bridge life by repainting bridge beams at I-70 in Wayne County. | Bridge Improvement | 2009-08-20 | 2009-09-16 | 2009-11-24 | 2009-10-25 | 335616 | 0.010
4199 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0800967 | This is a pavement resurfacing project on SR15, 2 miles north of US 20 to SR 120 in Bristol in Elkhart county that will lay 2 lays of asphalt to extend the life of the pavement, | Pavement Improvement | 2010-04-26 | 2010-05-17 | 2010-10-01 | 2010-10-12 | 466215.25 | 1.860
4200 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE, DE KALB |  | 03 | 0800974 | This is a Maintenance Resurfacing project, at US 6 - From SR 3 E jct (Kendallville) to I-69; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-05-17 | 2010-10-31 | 2011-05-16 | 2499046.86 | 12.020
4201 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WHITLEY, HUNTINGTON |  | Multiple | 0800975 | This project will improve sections and extend the life of US 24 in Huntington county from 1.66 Miles east of SR 9 est junction (Meridian Rd) to 0.75 miles east of SR 114 with a preventive maintenance | Pavement Improvement | 2009-07-07 | 2009-09-07 | 2009-10-23 | 2009-10-22 | 2710401.31 | 10.640
4202 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0800984 | This project will improve sections and extend the life of US 24 in Allen County with a pavement surface overlay | Pavement Improvement | 2009-03-25 | 2009-08-17 | 2009-09-03 | 2009-09-04 | 619717.05 | 4.180
4203 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0800986 | This is a Maintenance Resurfacing project, at SR 116 N jct to 2.44 miles N of US 224 (CR 850 N); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-03-24 | 2010-06-07 | 2010-08-28 | 2010-11-20 | 1098409.91 | 7.470
4204 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0810040 | This is a Safety project, at US 231 - at Parrish Avenue, Comm No 01-045-388; to perform Traffic Signals, New Or Modernized work. | Safety/Traffic Management | 2010-01-05 | 2010-01-29 | 2010-05-31 | 2010-03-11 | 98595.22 | 0.010
4205 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAGRANGE |  | 03 | 0810097 | This is a Maintenance Resurfacing project, at E US 20 - From 0.20 miles E of SR 9 to 4.28 miles E of SR 3 (Lagrange/Steuben Co Line).; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-29 | 2010-06-29 | 2010-10-31 | 2010-08-30 | 1384101 | 11.350
4206 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JAY, ADAMS |  | 06 | 0810099 | This is a Maintenance Resurfacing project, at Jct of SR 18/67 (Jay Co) to 1.04 miles S of SR 124 (Adams Co).; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-04-13 | 2010-05-04 | 2010-08-14 | 2010-08-13 | 1189917.08 | 13.050
4207 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI, WABASH, HUNTINGTON |  | 05 | 0810100 | This is a Maintenance Resurfacing project, at SR 19 (Miami Co) to SR 5 (Huntington Co).; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-15 | 2010-04-14 | 2010-10-01 | 2010-10-04 | 2840212.5 | 25.450
4208 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 0810108 | This project will improve the pavement markings in the LaPorte Area. | Safety/Traffic Management | 2009-04-16 | 2009-06-15 | 2009-11-12 | 2009-08-21 | 217958.7 | 0.010
4209 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WARRICK |  | 08 | 0810123 | This project will improve drainage by repairing pipes at I-64, 1 mile East of SR 161 in Warrick County. | Pavement Improvement | 2009-05-12 | 2009-06-10 | 2009-11-15 | 2009-07-30 | 116971.2 | 0.010
4210 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CRAWFORD, WARRICK |  | Multiple | 0810124 | This project will improve drainage by repairing pipes at I-64 from 5 miles East of I-164 to 1 mile West of SR 66 in Crawford and Warren Counties. | Pavement Improvement | 2009-05-12 | 2009-06-10 | 2009-11-15 | 2009-07-30 | 103675 | 0.030
4211 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITLEY |  | 03 | 0810228 | This is a Maintenance Resurfacing project, at SR 114 - From SR 105 to SR 9; to perform asphalt resurface, Functional work. | Pavement Improvement | 2009-12-16 | 2010-04-08 | 2010-10-22 | 2010-08-26 | 1909280.99 | 7.890
4212 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0810240 | This project will mitigate the environmental impacts of relocating a stream as part of the US 20 curve correction project, adding 370' of stream length, creating a floodplain and planting native veget | Other | 2009-06-18 | 2009-08-24 | 2010-06-30 | 2011-05-07 | 92975 | 0.010
4213 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0810254 | This project will extend the bridge life by repainting bridge beams at SR 55 over Big Pine Creek in Warren County. | Bridge Improvement | 2009-09-01 | 2009-10-08 | 2009-11-15 | 2009-11-12 | 248875.68 | 0.010
4214 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0810342 | This project will improve sections and extend the life of US-31 from Youngs Creek Bridge to Westview Dr in Johnson County with a pavement surface overlay. | Pavement Improvement | 2009-04-16 | 2009-05-14 | 2009-07-31 | 2009-07-29 | 636472.7 | 0.650
4215 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE, CLINTON |  | 04 | 0810387 | This project will improve drainage by repairing pipes at I-64 in Posey, Spencer and Vanderburgh Counties. | Pavement Improvement | 2009-05-22 | 2009-06-15 | 2009-06-30 | 2009-07-07 | 238601.65 | 1.970
4216 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PUTNAM |  | 08 | 0810388 | This project will improve sections and extend the life of SR 243 in Putnam County with a pavement surface overlay. | Pavement Improvement | 2009-05-13 | 2009-06-09 | 2009-07-01 | 2009-07-06 | 593817.69 | 4.010
4217 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0810390 | This project will improve sections and extend the life of US 421 in Jefferson County with a pavement surface overlay | Pavement Improvement | 2009-05-22 | 2009-06-24 | 2009-10-09 | 2009-08-26 | 596194.04 | 7.900
4218 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0810391 | This project will improve sections and extend the life of SR 57 in Jefferson County with a pavement surface overlay. | Pavement Improvement | 2009-05-22 | 2009-06-25 | 2009-07-31 | 2009-07-28 | 211151.98 | 2.590
4219 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE, BROWN |  | 09 | 0810411 | This project will improve sections and extend the life of SR 46 from SR 446 to SR 135 with a pavement surface overlay. | Pavement Improvement | 2009-05-13 | 2009-06-16 | 2009-08-31 | 2009-08-28 | 1784927.67 | 22.210
4220 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0810412 | This project will improve sections and extend the life ofS R-258 from SR 58 to Elm St in Jackson County with a pavement surface overlay. | Pavement Improvement | 2009-06-01 | 2009-08-04 | 2009-11-13 | 2009-10-06 | 1186796.91 | 12.340
4221 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS, JEFFERSON |  | 09 | 0810413 | This project will improve sections and extend the life of SR 7 from 1.52 miles North of Clifty Creek Drive to SR 3 with a pavement surface overlay. | Pavement Improvement | 2009-05-09 | 2009-08-13 | 2009-11-13 | 2009-10-31 | 1696103.37 | 14.970
4222 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS, JEFFERSON |  | 09 | 0810414 | This project will improve sections and extend the life of SR 250 from SR-3 to SR-7 with a pavement surface overlay. | Pavement Improvement | 2009-10-07 | 2010-03-10 | 2010-06-30 | 2010-05-06 | 678627.24 | 9.940
4223 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0810415 | This project will improve sections and extend the life of SR-46 from SR 1 to US 52 in Dearborn County with a pavement surface overlay. | Pavement Improvement | 2009-07-28 | 2009-08-28 | 2009-10-16 | 2009-09-30 | 513103.76 | 5.300
4224 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0810431 | This project will improve sections and extend the life of US 31 from the Fulton/Miami County Line to Old US 31 with a pavement surface overlay. | Pavement Improvement | 2009-06-09 | 2009-07-14 | 2009-07-18 | 2009-08-11 | 462865.34 | 3.800
4225 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0810432 | This project will improve sections and extend the life of US 35 through the town of Knox with a pavement surface overlay. | Pavement Improvement | 2009-06-17 | 2009-07-18 | 2009-07-31 | 2009-08-29 | 304785.34 | 2.610
4226 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0810453 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Pavement Improvement | 2009-06-17 | 2009-07-16 | 2010-08-31 | 2010-09-17 | 568694.99 | 1.020
4227 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 0810532 | This project will improve pavement markings in the LaPorte Area. | Safety/Traffic Management | 2009-06-19 | 2009-07-06 | 2009-09-11 | 2009-09-03 | 318376 | 0.010
4228 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0810598 | This project will construct canal boat support facilities for the Wabash and Erie Canal in the City of Delphi. | Transportation Enhancements | 2009-06-19 | 2009-11-10 | 2010-05-22 | 2010-04-29 | 398376.28 | 0.010
4229 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 02 | 0818022 | This project will improve the surface and rebuild sections of the bridge on US 421 over Little Monon Creek in White County. | Bridge Replacement | 2009-03-21 | 2009-04-16 | 2009-08-28 | 2009-10-26 | 668112.1 | 0.010
4230 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0887013 | This project will add turn lanes and widen the intersection at SR 32 and Rangeline Road in Madison County. | Pavement Improvement | 2009-07-08 | 2009-08-24 | 2010-07-31 | 2010-08-09 | 1920914 | 0.120
4231 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900008 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | New Bridge Construction | 2009-05-12 | 2009-07-22 | 2011-07-11 | 2011-08-04 | 252212.4 | 0.010
4232 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | POSEY, VANDERBURGH, SPENCER |  | Multiple | 0900048 | This project will improve drainage by repairing pipes at I-64 in Posey, Spencer and Vanderburgh Counties. | Pavement Improvement | 2009-05-12 | 2009-06-10 | 2009-11-15 | 2009-07-30 | 727204.41 | 45.010
4233 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0900049 | This is a Facilities for Pedestrians and Bicycles project, at Jasper Multi-Use Path - Ph 2; from W 20th St to 30th St; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2009-11-23 | 2010-03-17 | 2010-07-15 | 2010-07-09 | 436161.45 | 0.010
4234 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900079 | This project will improve sections and extend the life of US 52 in West Lafayette with a pavement surface overlay. | Pavement Improvement | 2009-06-03 | 2009-06-15 | 2009-11-28 | 2010-03-29 | 3633372.97 | 5.500
4235 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE |  | 02 | 0900082 | This is a Maintenance Resurfacing project, at US 35 - from Severs Rd to East Jct with US 20; to perform asphalt resurface, Functional work. | Pavement Improvement | 2009-10-08 | 2009-10-12 | 2010-08-13 | 2010-08-06 | 1681597.77 | 4.120
4236 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900083 | This project will build a new road from Amos Road to McKay Road in Shelby County. | New Construction | 2009-08-11 | 2009-08-28 | 2010-09-01 | 2010-09-12 | 1925233.13 | 0.763
4237 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NEWTON |  | 01 | 0900084 | This project will improve sections and extend the life of US 41 in Newton County with a pavement surface overlay. | Pavement Improvement | 2009-06-09 | 2009-07-17 | 2009-08-28 | 2009-09-10 | 1468123.44 | 11.880
4238 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900086 | This project will improve sections and extend the life of SR 106 in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-06-17 | 2009-09-09 | 2009-10-16 | 2009-10-16 | 449322.76 | 5.260
4239 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900087 | This project will improve sections and extend the life of US 6 in Marshall County with a pavement surface overlay | Pavement Improvement | 2009-06-17 | 2009-09-02 | 2009-10-02 | 2009-10-12 | 358345.84 | 5.410
4240 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900092 | This project will improve sections and extend the life of old US 52 on Old US-52 from IR-74 to West Harrison Corporate Limitswith a pavement surface overlay. | Pavement Improvement | 2009-07-27 | 2009-08-21 | 2009-11-03 | 2009-10-30 | 310752.1 | 2.420
4241 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900093 | This project will improve sections and extend the life of York Ridge Road from SR-1 to North Dearborn Road with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-04-09 | 2010-06-30 | 2010-06-04 | 650901.55 | 7.440
4242 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900095 | This project will improve sections and extend the life of North Hogan Road from SR 350 to Hogan Road in Dearborn County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-09 | 2010-07-15 | 234751.67 | 11.890
4243 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900096 | This project will improve sections and extend the life of North Dearborn from Ripley county line to SR1 in Dearborn County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-09 | 2010-07-15 | 142476.7 | 7.560
4244 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900119 | This project will replace and restore the pavement on US-40, at Brown Blvd, Terre Haute, in Vigo County. | Pavement Widening | 2009-09-15 | 2009-10-06 | 2010-06-30 | 2011-03-24 | 83633.1 | 0.100
4245 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900122 | This project will improve drainage by repairing pipes at I-70, .10 mile East of SR 46 in Vigo County. | Safety/Traffic Management | 2009-06-25 | 2009-07-01 | 2009-08-15 | 2009-08-24 | 623351.95 | 0.100
4246 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON, HENDRICKS, MARION, BOONE | INDIANAPOLIS | Multiple | 0900129 | This project will install traffic cameras on I-465, I-65, I-70 and I-74. | Other | 2009-06-11 | 2009-08-05 | 2010-05-28 | 2009-11-06 | 475151 | 23.110
4247 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900133 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2011-11-23 | 1464516.93 | 0.010
4248 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900134 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2011-11-23 | 543423.11 | 0.010
4249 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900135 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 |  | 734550.61 | 0.010
4250 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900136 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 |  | 893652.86 | 0.010
4251 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN | CINCINNATI | Multiple | 0900144 | This project will improve sections and extend the life of SR 148 from SR-48 to Maple Street with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-03-22 | 2010-07-16 | 2010-06-29 | 796973.87 | 9.170
4252 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0900145 | This project will improve sections and extend the life of SR 56 from East Junction of SR-62 to Crooked Creek Bridgewith a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-03-05 | 2010-07-16 | 2010-06-01 | 582189.29 | 2.560
4253 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RIPLEY |  | 09 | 0900146 | This is a Maintenance Resurfacing project, at Jefferson/Ripley CL to US-50; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-04-12 | 2010-09-01 | 2010-11-15 | 2010-11-10 | 950393.7 | 12.570
4254 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900147 | This is a Maintenance Resurfacing project, at SR 235 - to US-50; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-07 | 2009-11-02 | 2009-11-15 | 2010-04-13 | 747103.1 | 7.530
4255 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900159 | This project will improve sections and extend the life of Ridge Ave. from Decker Ave to Robinson Avenue with a pavement surface overlay. | Pavement Improvement | 2009-07-15 | 2009-08-07 | 2009-09-30 | 2009-09-23 | 79526.63 | 0.420
4256 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0900176 | This project will improve sections and extend the life of SR 10 in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-08-20 | 2009-09-21 | 2009-11-15 | 2009-11-14 | 1365218.07 | 6.810
4257 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900177 | This is a Reconstruction (no added capacity) project, at 7th Street and Springhill Road; to perform Intersect. Improv. W/ Added Turn Lanes work. | Pavement Improvement | 2010-04-08 | 2010-04-23 | 2010-08-28 | 2011-04-14 | 991533.27 | 0.010
4258 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE, PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900211 | This project will patch deteriorated pavement areas and seal cracks on I-94 from 1.5 mi. E of I-65 to SR 249 in Lake and Porter Counties. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 1134807.66 | 15.760
4259 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CARROLL, CASS |  | 02 | 0900218 | This is a Maintenance Restoration & Rehabilitation project, at SR 25 - from SR 218 in Delphi to Logansport; to perform Crack Sealing work. | Pavement Improvement | 2010-01-22 | 2010-05-20 | 2010-06-30 | 2011-03-30 | 349276.84 | 20.260
4260 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900219 | This project will patch deteriorated pavement areas and seal cracks on US 20 from SR 912 to Bridge St. in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 68420 | 9.880
4261 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0900229 | This is a Maintenance Resurfacing project, at SR-135 to 1.4 miles W Pekin; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-04-12 | 2010-06-30 | 2010-07-07 | 1064631.73 | 6.140
4262 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0900231 | This is a Maintenance Resurfacing project, at East of Jim Day Road to Washington /Scott CL; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-06-24 | 2010-09-30 | 2010-10-11 | 1877561.22 | 10.880
4263 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DECATUR, FRANKLIN |  | 06 | 0900232 | This is a Maintenance Resurfacing project, at 0.7 miles E of US-421 to the Batesville CL; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-04-14 | 2010-07-15 | 2010-07-27 | 1827164.82 | 13.630
4264 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON |  | 05 | 0900238 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | New Bridge Construction | 2009-05-12 | 2009-07-22 | 2011-07-11 | 2011-08-04 | 242787.2 | 0.010
4265 | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | DECATUR |  | 06 | 0900260 | This is a Maintenance Resurfacing project, at I-74 to Seymour District/Greenfield District Line; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-07 | 2010-07-20 | 2010-11-15 | 2010-11-15 | 1217013.89 | 6.020
4266 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0900296 | This project will improve safety and extend the life of the bridge(s) on County Road 211 over I-64 in Perry County. | Bridge Improvement | 2009-07-07 | 2009-09-17 | 2010-06-30 | 2010-07-16 | 419566 | 0.214
4267 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900297 | This project will improve safety and extend the life of the bridge(s) on US 41 over Main Street in Knox County. | Bridge Improvement | 2009-07-10 | 2010-08-04 | 2010-07-31 | 2010-10-29 | 322096.46 | 0.122
4268 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900298 | This project will improve safety and extend the life of the bridge(s) on US 41 over Main Street in Knox County. | Bridge Improvement | 2009-07-10 | 2010-08-04 | 2010-07-31 | 2010-10-29 | 308896.52 | 0.122
4269 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0900299 | This project will improve safety and extend the life of the bridge(s) on SR 157 over White River in Green County. | Bridge Improvement | 2009-07-24 | 2009-09-22 | 2010-06-30 | 2010-07-08 | 961859.92 | 0.742
4270 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | OWEN |  | 08 | 0900300 | This project will improve safety and extend the life of the bridge(s) on US 231 over Fish Creek in Owen County. | Bridge Improvement | 2009-07-24 | 2009-09-22 | 2010-06-30 | 2010-07-08 | 621795 | 0.225
4271 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0900301 | This project will improve safety and extend the life of the bridge(s) on SR 124 over Brock Creek in Huntington County. | Bridge Improvement | 2009-07-07 | 2009-08-21 | 2009-10-30 | 2009-10-22 | 271400.3 | 0.680
4272 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0900302 | This project will improve safety and extend the life of the bridge(s) on County Road 300 South over I-69 in Huntington County. | Bridge Improvement | 2009-07-07 | 2009-08-21 | 2009-10-30 | 2009-10-22 | 421012.07 | 0.208
4273 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW |  | 06 | 0900303 | This project will improve safety and extend the life of the bridge(s) on US 31 over Little Sand Creek in Bartholomew County. | Bridge Improvement | 2009-10-09 | 2010-04-05 | 2010-10-31 | 2010-10-14 | 675666.07 | 0.108
4274 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW |  | 06 | 0900304 | This project will improve safety and extend the life of the bridge(s) on SR 46 over the abandoned Railroad in Bartholomew County. | Bridge Improvement | 2009-10-09 | 2010-04-05 | 2010-10-31 | 2010-10-14 | 660012.93 | 0.010
4275 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BROWN |  | 09 | 0900305 | This project will improve safety and extend the life of the bridge(s) on SR 45 over Beanblossom Creek in Brown County. | Bridge Improvement | 2009-07-07 | 2010-06-07 | 2010-10-29 | 2010-09-15 | 517603 | 0.125
4276 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BROWN |  | 09 | 0900306 | This project will improve safety and extend the life of the bridge(s) on SR 45 over Beanblossom Creek in Brown County. | Bridge Improvement | 2009-07-07 | 2010-06-07 | 2010-10-29 | 2010-09-15 | 468003 | 0.010
4277 | Completed | C250,C240 | Highway Infrastructure Investment Grant | INDIANA | DECATUR |  | 06 | 0900307 | This project will improve safety and extend the life of the bridge(s) on SR 3 over Clifty Creek in Decatur County. | Bridge Improvement | 2009-07-07 | 2010-06-16 | 2010-11-19 | 2010-11-12 | 760685.65 | 0.010
4278 | Completed | C250,C200 | Highway Infrastructure Investment Grant | INDIANA | RIPLEY |  | 09 | 0900308 | This project will improve safety and extend the life of the bridge(s) on US 50 over Laughery Creek in Ripley County. | Bridge Improvement | 2009-08-18 | 2010-04-01 | 2010-11-19 | 2010-07-02 | 730256.8 | 0.010
4279 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900309 | This project will improve safety and extend the life of the bridge(s) on SR 3 over the abandoned Railroad in Scott County. | Bridge Improvement | 2009-07-24 | 2010-04-01 | 2010-09-20 | 2010-08-09 | 500410.02 | 0.217
4280 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VERMILLION |  | 08 | 0900310 | This project will improve safety and extend the life of the bridge(s) on SR 63 over Brouiletts Creek in Vermillion County. | Bridge Improvement | 2009-08-18 | 2010-04-09 | 2010-10-15 | 2010-10-21 | 775788 | 0.421
4281 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900311 | This project will improve safety and extend the life of the bridge(s) on SR 263 over Redwood Creek in Warren County. | Bridge Improvement | 2009-07-17 | 2009-09-10 | 2010-07-18 | 2010-05-19 | 644125.4 | 0.150
4282 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VERMILLION |  | 08 | 0900312 | This project will improve safety and extend the life of the bridge(s) on SR 71 over Little Vermillion River in Vermillion County. | Bridge Improvement | 2009-08-18 | 2010-04-09 | 2010-10-15 | 2010-10-21 | 455103 | 0.150
4283 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900314 | This project will patch deteriorated pavement areas and seal cracks on I-65 from SR 2 to US 231 in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 584240 | 7.380
4284 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE, PORTER, MARSHALL, LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900315 | This project will patch deteriorated pavement areas and seal cracks on US 30 from the Lake/Porter County Line to SR 17 in LaPorte, Marshall, Porter and Starke Counties. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 196604.8 | 50.080
4285 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900316 | This project will patch deteriorated pavement areas and seal cracks on US 30 from US 41 to SR 55 in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 106556.8 | 5.710
4286 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900317 | This project will patch deteriorated pavement areas and seal cracks on I-94 from SR 249 to SR 49 in Porter County. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 154256 | 7.080
4287 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | MICHIGAN CITY | 02 | 0900318 | This project will patch deteriorated pavement areas and seal cracks on I-94 from US 35 to the Michigan State Line in LaPorte County. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 87648 | 5.850
4288 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW | COLUMBUS | 06 | 0900321 | This project will improve sections and extend the life of 25th St. from CR 350 E to SR 9 with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-09 | 2009-11-15 | 2009-10-07 | 496214.92 | 4.300
4289 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | PARKE |  | 08 | 0900322 | This project will improve the surface and rebuild sections of the bridge on SR 47 at Turkey Run in Parke County. | Bridge Improvement | 2009-07-11 | 2009-09-16 | 2009-11-15 | 2009-11-06 | 292449.49 | 0.317
4290 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900323 | This project will improve the surface and rebuild sections of the bridge on US 136 at the Wabash River in Warren County. | Bridge Improvement | 2009-07-07 | 2009-09-10 | 2009-09-30 | 2009-09-30 | 471268.58 | 0.935
4291 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900327 | This project will patch deteriorated pavement areas and seal cracks on US 231 from SR 912 to Bridge St. in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 19543.2 | 6.300
4292 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900329 | This project will patch deteriorated pavement areas and seal cracks on SR 2 from Cline Ave. to SR 53 in Porter County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 55274 | 13.400
4293 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900331 | This project will patch deteriorated pavement areas and seal cracks on US 41 from Huehn St. to 0.25 mi.. N. of Sheffield Ave. in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 32000.5 | 2.570
4294 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900333 | This project will patch deteriorated pavement areas and seal cracks on US 12 from W. of Calumet Ave. to the Illinois State Line. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 29005 | 1.310
4295 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900334 | This project will improve sections and extend the life of Howard County Road 200N from 1350 East to the county line with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 24133.69 | 0.010
4296 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900335 | This project will patch deteriorated pavement areas and seal cracks on US 12 from Schrage Ave. to the lift bridge S. of Riley Road in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 89212.8 | 1.450
4297 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900336 | This project will improve the surface and rebuild sections of the bridge on SR 912 over I-80 in Lake County. | Bridge Improvement | 2009-09-14 | 2010-05-03 | 2010-06-30 | 2010-06-08 | 298381.48 | 0.010
4298 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900337 | This project will improve the surface and rebuild sections of the bridge on SR 912 over I-80 in Lake County. | Bridge Improvement | 2009-09-14 | 2010-05-03 | 2010-06-30 | 2010-06-08 | 300423.28 | 0.010
4299 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900339 | This project will patch deteriorated pavement areas and seal cracks on US 20 from SR 249 to US 20/I-94 in Porter County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 59245.7 | 3.540
4300 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900340 | This project will improve sections and extend the life of Howard County Road 200W from County Road 200North to County Road 325 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 74052.76 | 1.200
4301 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900341 | This project will improve the surface and rebuild sections of the bridge on US 41 over Brown Ditch in Lake County. | Bridge Improvement | 2009-09-14 | 2009-10-12 | 2009-10-31 | 2009-10-21 | 23904.4 | 0.880
4302 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900343 | This project will improve the surface and rebuild sections of the bridge on US 41 over Brown Ditch in Lake County. | Bridge Improvement | 2009-09-14 | 2009-10-12 | 2009-10-31 | 2009-10-21 | 23110 | 0.880
4303 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900344 | This project will patch deteriorated pavement areas and seal cracks on US 31 from US 20 to the Michigan State Line in St. Joseph County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 75948 | 3.840
4304 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900345 | This project will improve the surface and rebuild sections of the bridge on US 41 over Singleton Ditch in Lake County. | Bridge Improvement | 2009-09-14 | 2009-10-12 | 2009-10-31 | 2009-10-21 | 22380 | 0.940
4305 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900346 | This project will improve the surface and rebuild sections of the bridge on US 41 over Singleton Ditch in Lake County. | Bridge Improvement | 2009-09-14 | 2009-10-12 | 2009-10-31 | 2009-10-21 | 22550 | 0.940
4306 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL | SOUTH BEND (MI) | 02 | 0900347 | This project will patch deteriorated pavement areas and seal cracks ON US 6 from 0.5 mi. W of SR 106 to 0.5 mi. E of SR 106 in Marshall County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 27450 | 4.140
4307 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900348 | This project will improve the surface and rebuild sections of the bridge on US 50 at Vernon Fork Muscatatuck River in Jennings County. | Bridge Improvement | 2009-09-17 | 2010-06-10 | 2010-07-31 | 2010-07-27 | 260883.08 | 0.010
4308 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900349 | This project will patch deteriorated pavement areas and seal cracks on US 12 from SR 249 to SR 149 bridge in Porter County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 19910.4 | 1.980
4309 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | HARRISON |  | 09 | 0900350 | This project will improve the surface and rebuild sections of the bridge on SR 135 at Lick Run Creek in Harrison County. | Bridge Improvement | 2009-07-20 | 2009-08-20 | 2009-09-26 | 2009-09-14 | 495227.43 | 0.122
4310 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW |  | 06 | 0900351 | This project will improve the surface and rebuild sections of the bridge on I-65 over Driftwood River in Bartholomew County. | Bridge Improvement | 2009-08-18 | 2010-05-27 | 2010-10-01 | 2010-07-09 | 606321.7 | 0.010
4311 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW |  | 06 | 0900352 | This project will improve the surface and rebuild sections of the bridge on I-65 over Driftwood River in Bartholomew County. | Bridge Improvement | 2009-08-18 | 2010-05-27 | 2010-10-01 | 2010-07-09 | 433965.37 | 0.010
4312 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900353 | This project will improve the surface and rebuild sections of the bridge on US 50 over Wabash River in Knox County. | Bridge Improvement | 2009-07-15 | 2009-08-14 | 2009-10-15 | 2009-08-31 | 52897.74 | 0.010
4313 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | MICHIGAN CITY | 02 | 0900354 | This project will patch deteriorated pavement areas and seal cracks on SR 212 from US 12 to US 20 in LaPorte County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 32000.5 | 3.360
4314 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900355 | This project will improve the surface and rebuild sections of the bridge on US 50 over Wabash River in Knox County. | Bridge Improvement | 2009-07-15 | 2009-08-14 | 2009-10-15 | 2009-08-31 | 52307.59 | 0.010
4315 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0900356 | This project will improve the surface and rebuild sections of the bridge on US 50 over White River in Lawrence County. | Bridge Improvement | 2009-07-15 | 2009-08-14 | 2009-10-15 | 2009-08-31 | 41930.71 | 0.930
4316 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0900357 | This project will improve sections and extend the life of Arba Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2010-04-19 | 2010-06-04 | 2010-05-28 | 350293.36 | 3.580
4317 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0900358 | This project will improve the surface and rebuild sections of the bridge on US 50 over White River in Lawrence County. | Bridge Improvement | 2009-07-15 | 2009-08-14 | 2009-10-15 | 2009-08-31 | 40828.81 | 0.930
4318 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900363 | This project will extend the bridge life by repainting bridge beams at I-64 over SR 111 & Main Street in Floyd County. | Bridge Improvement | 2009-10-29 | 2010-01-04 | 2010-09-25 | 2010-07-26 | 929831.88 | 0.020
4319 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900364 | This is a Maintenance Restoration & Rehabilitation project, at SR 25 - from Logansport to SR 16; to perform Crack Sealing work. | Pavement Improvement | 2010-01-22 | 2010-05-20 | 2010-06-30 | 2011-03-30 | 105991.2 | 11.420
4320 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900365 | This project will extend the bridge life by repainting bridge beams at I-64 over Southern Railroad in Floyd County. | Bridge Improvement | 2009-10-29 | 2010-01-04 | 2010-09-25 | 2010-07-26 | 871470.52 | 0.020
4321 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900366 | This project will extend the bridge life by repainting bridge beams at I-64 over SR 111 & Main Street in Floyd County. | Bridge Improvement | 2009-10-29 | 2010-01-04 | 2010-09-25 | 2010-07-26 | 1498546.9 | 0.020
4322 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NEWTON |  | 01 | 0900367 | This is a Maintenance Restoration & Rehabilitation project, at US 41 - from SR 114 to SR 14; to perform Crack Sealing work. | Pavement Improvement | 2010-01-22 | 2010-05-20 | 2010-06-30 | 2011-03-30 | 54573.04 | 5.310
4323 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0900368 | This project will extend the bridge life by repainting bridge beams at I-65 at Riverside Drive & Market Street in Clark County. | Bridge Improvement | 2009-08-03 | 2009-09-23 | 2009-11-01 | 2009-11-15 | 570539.54 | 0.648
4325 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900371 | This is a Maintenance Restoration & Rehabilitation project, at US 31 - from SR 110 to 0.1mi S of SR 10; to perform Crack Sealing work. | Pavement Improvement | 2010-01-22 | 2010-05-20 | 2010-06-30 | 2011-03-30 | 142797.6 | 4.730
4326 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VANDERBURGH | EVANSVILLE (KY) | 08 | 0900384 | This is a Facilities for Pedestrians and Bicycles project, at Greenway bike/ped trail from Franklin St to Maryland St (Sect 3-C2); to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-01 | 2010-06-01 | 2011-06-15 | 2011-09-22 | 1892569 | 0.010
4327 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0900406 | This project will upgrade and improve the traffic signals at various locations in the town of Westfield. | Safety/Traffic Management | 2009-11-23 | 2009-12-21 | 2010-03-01 | 2010-02-23 | 65210.2 | 0.010
4328 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900423 | This is a Maintenance Resurfacing project, at SR 4 - On Maple Avenue from Monroe Street (SR4) to Rose Street; to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 97094.97 | 0.300
4329 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900424 | This is a Maintenance Resurfacing project, at City of LaPorte on Park Street from Norfolk/Southern RR to McClung Road; to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 50971.96 | 0.270
4330 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900425 | This is a Maintenance Resurfacing project, at 1st Street from Central Avenue to J Street (SR 2); to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 63481.47 | 0.320
4331 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900426 | This is a Maintenance Resurfacing project, at 1st Street from J Street (SR 2) to Indiana Avenue (US 35); to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 219215.5 | 0.580
4332 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900427 | This is a Maintenance Resurfacing project, at Street from 10th Street to 18th Street; to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 97874.83 | 0.500
4333 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900429 | This is a Maintenance Resurfacing project, at 73rd Avenue from Clark Street to I-65 overpass; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-07-16 | 2010-07-31 | 2010-09-03 | 708954.07 | 3.500
4334 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900430 | This is a Maintenance Resurfacing project, at Madison Street/Harrison Street from US 30 to 53rd Avenue; to perform Surface Treatment work. | Pavement Improvement | 2010-01-15 | 2010-03-30 | 2010-06-30 | 2010-05-12 | 327191.87 | 3.610
4335 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CRAWFORD |  | 09 | 0900434 | This project will improve drainage by repairing pipes at I-64 in Crawford County. | Pavement Improvement | 2009-07-16 | 2009-08-31 | 2010-06-01 | 2010-04-14 | 1561004.65 | 11.280
4336 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VANDERBURGH |  | 08 | 0900436 | This project will improve drainage by repairing pipes at SR 66 in Crawford County. | Other | 2009-07-06 | 2009-08-31 | 2009-10-15 | 2009-09-24 | 735970.32 | 3.990
4337 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900441 | This project will complete the restoration of the Bremen Train Depot. | Transportation Enhancements | 2009-12-16 | 2010-01-25 | 2010-10-31 | 2010-10-29 | 289960.37 | 0.010
4338 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900442 | This project will improve the Marshall County Historical Museum. | Transportation Enhancements | 2010-01-08 | 2010-02-24 | 2010-10-31 | 2010-11-23 | 393189.06 | 0.010
4339 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900443 | This is a Historic Preservation project to update and preserve the streetscape on at Central Ave. from 119th to 116th and on Oliver St, from 119th to 117th in the town of Whiting, Lake county. | Transportation Enhancements | 2010-01-14 | 2010-04-13 | 2010-06-30 | 2010-06-02 | 257318.84 | 0.630
4340 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900448 | This project will replace the bridge deck on SR 23 over Mishawaka Ave in St Joseph County. | Bridge Improvement | 2009-08-18 | 2009-10-09 | 2010-05-15 | 2010-05-14 | 727822.5 | 0.146
4341 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 04 | 0900449 | This project will improve safety and extend the life of the bridge(s) on SR 341 over Coal Creek in Fountain County. | Bridge Improvement | 2009-07-17 | 2009-09-10 | 2010-07-18 | 2010-05-19 | 357212.5 | 0.710
4342 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PARKE |  | 08 | 0900450 | This project will improve safety and extend the life of the bridge(s) on US 41 over Big Raccoon Creek in Parke County. | Bridge Improvement | 2009-07-07 | 2010-04-07 | 2010-07-31 | 2010-07-16 | 795594.75 | 0.384
4343 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WABASH |  | 05 | 0900451 | This project will improve safety and extend the life of the bridge(s) on Sr 13 over Paw Paw Creek in Wabash County. | Pavement Improvement | 2009-07-07 | 2009-08-05 | 2009-10-30 | 2009-08-27 | 144530.47 | 0.420
4344 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0900452 | This project will improve safety and extend the life of the bridge(s) on SR 4 over Rock Run Creek in Elkhart County. | Bridge Improvement | 2009-08-18 | 2009-09-14 | 2009-10-23 | 2009-10-21 | 121166.6 | 0.440
4345 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0900453 | This project will improve safety and extend the life of the bridge on SR 218 over Wagley Farlow Ditch in Adams County by removing and replacing the wearing surface of the deck. | Bridge Improvement | 2009-07-07 | 2009-09-03 | 2009-10-30 | 2009-10-29 | 310982.85 | 0.030
4346 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0900469 | This project will improve sections and extend the life of County Road 900North from 200 west to 300 east in Jasper County with a pavement surface overlay. | Pavement Improvement | 2009-12-31 | 2010-04-14 | 2010-06-05 | 2010-06-02 | 469658 | 5.040
4347 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0900470 | This project will improve sections and extend the life of County Road 400West from Northern County limits to intersection at SR 10 in Jasper County with a pavement surface overlay. | Pavement Improvement | 2009-12-31 | 2010-04-14 | 2010-06-05 | 2010-06-02 | 575812.67 | 6.670
4348 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900472 | This is a Maintenance Resurfacing project, at Kennedy Avenue from the Toll Road to Michigan Avenue; to perform Surface Treatment work. | Pavement Improvement | 2010-01-19 | 2010-03-25 | 2010-06-09 | 2010-05-13 | 363065.78 | 2.000
4349 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900473 | This is a Landscaping project, at E Columbus Drive from Cline Avenue to Main Street; to perform Landscaping work. | Transportation Enhancements | 2010-03-26 | 2010-04-02 | 2010-06-15 | 2010-11-11 | 99538.87 | 0.900
4350 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900474 | This is a Safety project, at E Columbus Drive from Cline Avenue to Main Street; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-26 | 2010-04-02 | 2010-06-15 | 2010-11-11 | 329757.93 | 0.900
4351 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900493 | This project will improve sections and extend the life of 9A Road from SR 31 to King Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 16609.25 | 0.733
4352 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900496 | This project will improve sections and extend the life of Lincoln Highway from King Road to Fir Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-06 | 2010-06-30 | 2009-12-14 | 566060.81 | 5.910
4353 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900500 | This project will improve sections and extend the life of 4th Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 5861.81 | 0.254
4354 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900501 | This project will improve sections and extend the life of King Road from Plymouth-Goshen Trail to 4th Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 77825.02 | 3.697
4355 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900502 | This project will improve sections and extend the life of Plymouth-Goshen Trail from Linden Road to King Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 17565.74 | 0.733
4356 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900514 | This project will improve sections and extend the life of Lincoln Highway from Fir Road to Elm Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-06 | 2010-06-30 | 2009-12-14 | 81746.03 | 1.042
4357 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900518 | This is a Maintenance Resurfacing project, at Wisconsin St. from Old Ridge Road to 10th Street; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-06-05 | 2010-06-09 | 350540.74 | 0.970
4358 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900520 | This is a New Construction Roadway project, at Lake Park Avenue from Ridge Road (37th Ave) to Old Ridge Road; to perform Surface Treatment work. | New Construction | 2010-01-08 | 2010-06-28 | 2010-06-30 | 2010-08-09 | 193772.83 | 0.920
4359 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900521 | This is a Maintenance Resurfacing project, at 3rd Street from S LaSalle St to Main Street; to perform Surface Treatment work. | Pavement Improvement | 2009-10-13 | 2009-11-05 | 2009-11-21 | 2009-11-23 | 282412.76 | 1.500
4360 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | BROWN |  | 09 | 0900535 | This project will improve sections and extend the life of Gatesville Rd. from SR 135 to Salt Cree with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-05-03 | 2010-07-01 | 2010-06-11 | 381688.28 | 6.330
4361 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | BROWN |  | 09 | 0900536 | This project will improve sections and extend the life of Christiansburg Rd. Rd from SR 135 S to Bells with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-05-03 | 2010-07-01 | 2010-06-11 | 247456.61 | 4.060
4362 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900537 | This project will improve sections and extend the life of Bicknell Slab Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-24 | 2009-11-30 | 2009-11-22 | 539391.24 | 8.030
4363 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900538 | This project will improve sections and extend the life of Sixth St in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-08 | 2009-11-30 | 2009-11-11 | 139489.1 | 1.530
4364 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900539 | This project will improve sections and extend the life of Sixth Street Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-24 | 2009-11-30 | 2009-11-22 | 196066.53 | 2.900
4365 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0900540 | This project will improve sections and extend the life of Cannelburt Rd in Daviess County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-11-30 | 2009-10-29 | 306500.38 | 3.200
4366 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0900541 | This is a Maintenance Resurfacing project, at NW 11th St to NW 5th St; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-08-31 | 2010-10-18 | 70314.86 | 0.430
4367 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900542 | This is a Maintenance Resurfacing project, at 12th St to Main St; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-08-31 | 2010-10-18 | 127834.08 | 0.730
4368 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0900543 | This is a Maintenance Resurfacing project, at 5th St to 12th St; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-08-31 | 2010-10-18 | 68407.98 | 1.030
4369 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0900545 | This is a Maintenance Resurfacing project, at Kopp Lane from Hallmark Blvd to Eastern Blvd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-09 | 2010-04-07 | 2010-07-19 | 91014.04 | 0.720
4370 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0900546 | This project will improve sections and extend the life of Old SR 245 with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-09-25 | 2009-11-30 | 2009-11-24 | 582496.64 | 3.890
4371 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0900547 | This project will improve the traffic signs in Daviess County. | Safety/Traffic Management | 2009-09-01 | 2010-01-18 | 2009-12-31 | 2010-03-31 | 317221.5 | 0.010
4372 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0900548 | This project will improve sections and extend the life of French Ridge Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-14 | 2009-11-30 | 2009-11-09 | 475602.57 | 5.150
4373 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0900549 | This project will improve sections and extend the life of Leopold Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-14 | 2009-11-30 | 2009-11-09 | 549249.41 | 6.900
4374 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900550 | This project will improve sections and extend the life of South Michigan St. in Marshall County with a pavement surface overlay | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 292820.96 | 4.283
4375 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900551 | This project will improve sections and extend the life of Miami Highway from SR 106 to the county line in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 42123.04 | 2.039
4376 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0900554 | This is a Maintenance Resurfacing project, at North Main Street from TP&W railroad tracks N 2,665 feet; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-02-22 | 2010-03-31 | 2010-07-01 | 2010-06-24 | 268352.11 | 0.500
4377 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0900555 | This is a Maintenance Resurfacing project, at North Illinois Street from TP&W railroad N 2,660 feet; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-02-22 | 2010-03-31 | 2010-07-01 | 2010-06-24 | 206935.48 | 0.400
4378 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900556 | This project will improve sections and extend the life of Monterey Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 36552.76 | 1.687
4379 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0900558 | This is a Small Structure project, at I-69 & I-469 Interchange Ramp"D",Pipe #7, EB to SB I-69, 0.18 Miles S. of I-469; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-09-20 | 2010-10-02 | 2010-10-25 | 44400 | 0.100
4380 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900560 | This project will improve sections and extend the life of Road 600S with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2010-05-18 | 2010-06-30 | 2010-08-12 | 558472.41 | 5.520
4381 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900561 | This project will improve sections and extend the life of Road 75W in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-10-14 | 2010-04-02 | 2009-10-15 | 2010-06-09 | 254296.79 | 1.750
4382 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900562 | This project will improve sections and extend the life of Road 700E with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-10-12 | 2009-12-18 | 702918.62 | 5.500
4383 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900563 | This project will improve sections and extend the life of Road 400S in Cass County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-10-12 | 2009-12-18 | 53499.41 | 0.500
4384 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900564 | This project will improve sections and extend the life of Road 200E in Cass County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2010-05-18 | 2010-06-30 | 2010-06-18 | 330703.46 | 3.000
4385 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0900566 | This project will improve sections and extend the life of Old SR 45 in Spencen County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-09-25 | 2009-11-30 | 2009-11-24 | 387969.28 | 3.790
4386 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0900567 | This project will improve sections and extend the life of Fulda Shortcut Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-09-25 | 2009-11-30 | 2009-11-24 | 220751.47 | 4.180
4387 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0900568 | This project will improve sections and extend the life of Road 800 E in Spencer County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-09-25 | 2009-11-30 | 2009-11-24 | 121839.45 | 2.280
4388 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0900572 | This project will replace and restore the pavement on Nucor Road in Crawfordsville. | Pavement Improvement | 2009-09-03 | 2009-08-03 | 2009-11-15 | 2009-11-18 | 588633.74 | 5.860
4389 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900573 | This project will improve sections and extend the life of Road 350 E in Gibson County with a pavement surface overlay | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-11-30 | 2009-10-19 | 482102.74 | 5.300
4390 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0900574 | This project will replace and restore the pavement on Old SR 55 in Wingate. | Pavement Improvement | 2009-09-03 | 2009-08-03 | 2009-11-15 | 2009-11-18 | 963868.51 | 10.920
4391 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900575 | This project will improve sections and extend the life of Road 550 E in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-11-30 | 2009-10-19 | 400716.23 | 3.510
4392 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900576 | This project will improve sections and extend the life of Road 350 S in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-11-30 | 2009-10-19 | 225187.43 | 2.620
4393 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900577 | This project will improve sections and extend the life of CR 50 S/Old Boonville HWY in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-06 | 2009-11-30 | 2009-11-30 | 201964.34 | 2.100
4394 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900578 | This project will improve sections and extend the life of Road 350S/Vann Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-06 | 2009-11-30 | 2009-11-30 | 355597.27 | 3.900
4395 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900579 | This project will improve sections and extend the life of Road 25w/Yankeetown Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-06 | 2009-11-30 | 2009-11-30 | 59422.22 | 0.700
4396 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900580 | This project will improve sections and extend the life of Old SR 66 in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-06 | 2009-11-30 | 2009-11-30 | 142584.85 | 1.800
4397 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900581 | This project will improve sections and extend the life of CR 800N/Elberfeld Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-16 | 2009-11-30 | 2009-11-30 | 118101.74 | 1.100
4398 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900582 | This project will improve sections and extend the life of Rd 1100S/North Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-16 | 2009-11-30 | 2009-11-30 | 121332.76 | 1.700
4399 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS | INDIANAPOLIS | 04 | 0900584 | This is a Maintenance Restoration & Rehabilitation project, at US 40 - In Plainfield from the East end of the Bridge over White Lick Creek to Carr Rd; to perform Road Reconstruction work. | Pavement Improvement | 2009-09-18 | 2009-10-05 | 2010-11-12 | 2011-05-26 | 2391134.09 | 1.080
4400 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900585 | This project will improve sections and extend the life of 2nd St in Knox County with a pavement surface overlay | Pavement Improvement | 2009-09-15 | 2009-10-30 | 2009-11-30 | 2009-11-19 | 92455.5 | 0.625
4401 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900599 | This project will improve sections and extend the life of Old SR 132 in Madison County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-30 | 2009-10-02 | 333962.38 | 5.220
4402 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900605 | This project will restore the pavement on Madison County Road 600 W with a new surface course. | Pavement Improvement | 2009-09-14 | 2009-09-22 | 2009-10-30 | 2009-10-26 | 336218.82 | 3.830
4403 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900606 | This project will improve sections and extend the life of Northport Rd. from SR 9 to Angling Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-23 | 2009-10-31 | 2009-10-17 | 294529.38 | 2.850
4404 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900607 | This project will improve sections and extend the life of Madison County Road 100E with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-30 | 2009-10-02 | 89002.34 | 1.080
4405 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900608 | This project will improve sections and extend the life of 8th St. in Madison County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-30 | 2009-10-02 | 271010.78 | 4.330
4406 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900609 | This project will improve sections and extend the life of Shelby County Road 400E on the east side of Shelbyville with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-26 | 2009-11-02 | 2009-11-01 | 705434.18 | 0.010
4407 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | PUTNAM |  | 08 | 0900610 | This project will replace and restore the pavement on Indiana Street in Greencastle. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-11-15 | 2009-10-13 | 61850.75 | 0.540
4408 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 04 | 0900612 | This project will improve sections and extend the life of N Perry St in Fountain County with a pavement surface overlay | Pavement Improvement | 2009-09-01 | 2009-09-29 | 2009-11-15 | 2010-06-24 | 260458.14 | 0.520
4409 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON |  | 05 | 0900613 | This is a Maintenance Resurfacing project, at From SR 32 to SR 47 in Washington & Adams Townships IN; to perform Pavement, Other work. | Pavement Improvement | 2009-11-23 | 2010-04-23 | 2010-05-28 | 2010-05-25 | 448756.77 | 6.070
4410 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0900614 | This project will replace and restore the pavement on County Road 800E, from CR-100N to CR-1200N, in Rush County. | Pavement Improvement | 2009-09-01 | 2009-11-16 | 2009-10-30 | 2009-11-25 | 108495.25 | 0.990
4411 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0900615 | This project will replace and restore the pavement on County Road 800E, from CR-600N to CR-900N, in Rush County. | Pavement Improvement | 2009-09-01 | 2009-11-16 | 2009-10-30 | 2009-11-25 | 244409.25 | 3.000
4412 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK |  | 05 | 0900616 | This project will replace and restore the pavement on County Road 1050E, from US-40 to SR-650N, in Hancock County. | Pavement Improvement | 2009-09-01 | 2009-10-13 | 2009-10-30 | 2009-11-06 | 431006.31 | 5.690
4413 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK |  | 05 | 0900617 | This project will replace and restore the pavement on County Road 600E, from US-40 to SR-234, in Hancock County. | Pavement Improvement | 2009-09-01 | 2009-10-13 | 2009-10-30 | 2009-11-06 | 568377.18 | 6.110
4414 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0900624 | This project will improve sections and extend the life of Main St/Hoosier Ave with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-19 | 2009-11-30 | 2009-11-18 | 242821.91 | 0.280
4415 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SULLIVAN |  | 08 | 0900626 | This project will improve sections and extend the life of CR 925N/CR 450W/CR 1100 N with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-07 | 2009-11-30 | 2009-11-30 | 586794.18 | 8.540
4416 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SULLIVAN |  | 08 | 0900628 | This project will improve sections and extend the life of Old US 41 in Sullivan County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-07 | 2009-11-30 | 2009-11-30 | 294187.65 | 4.200
4417 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900635 | This project will restore the pavement on Madison County Road 1100 N with a new surface course. | Pavement Improvement | 2009-09-14 | 2009-09-22 | 2009-10-30 | 2009-10-26 | 221286.77 | 4.000
4418 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900637 | This is a Safety project, at Hausfledt Lane at CSX Railroad Crossing; to perform Railroad Protection work. | Safety/Traffic Management | 2010-01-06 | 2011-05-04 | 2010-05-13 | 2011-05-20 | 471428 | 0.040
4419 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900638 | This project will restore the pavement on Madison County Road 1100 N with a new surface course. | Pavement Improvement | 2009-09-14 | 2009-09-22 | 2009-10-30 | 2009-10-26 | 413430.83 | 5.500
4420 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900639 | This project will improve the traffic signals on Market Street from State St to Vincennes Street. | Safety/Traffic Management | 2010-02-01 | 2010-02-08 | 2010-05-14 | 2010-04-09 | 327809.26 | 1.300
4421 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPTON |  | 05 | 0900642 | This project will improve sections and extend the life of Division Rd. from US 31 to SR 1 with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-10-30 | 2009-10-28 | 529938.85 | 4.960
4422 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPTON |  | 05 | 0900643 | This project will improve sections and extend the life of South Ash St. from SR 28 to Railroad with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-10-30 | 2009-10-28 | 44947.05 | 1.008
4423 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900644 | This project will improve traffic signals from Spring Street to State Street in New Albany, Floyd county. | Safety/Traffic Management | 2010-02-01 | 2010-02-08 | 2010-05-14 | 2010-04-09 | 277980.07 | 1.300
4424 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900647 | This project will improve sections and extend the life of Howard County Road 1350 East from CR 200 North to CR 400 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 154362.09 | 2.000
4425 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900648 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 1000 East to County Road 1200 East with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 103108.36 | 2.000
4426 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900650 | This project will improve sections and extend the life of Road 300 W in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-10-14 | 2010-04-02 | 2009-10-15 | 2010-06-09 | 129189.32 | 1.170
4427 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900651 | This project will improve sections and extend the life of Bicycle Rd with a pavement surface overlay. | Pavement Improvement | 2009-10-14 | 2010-04-02 | 2009-10-15 | 2010-06-09 | 399347.3 | 3.940
4428 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900652 | This project will improve sections and extend the life of Road 100N in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2010-06-15 | 2009-12-23 | 11417.16 | 0.120
4429 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900655 | This project will improve sections and extend the life of Road 700W in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2010-06-15 | 2009-12-23 | 314863.21 | 6.110
4430 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900656 | This project will improve sections and extend the life of Meridian Rd in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2010-06-15 | 2009-12-23 | 411985.15 | 3.010
4431 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900657 | This project will replace and restore the pavement on Loganspot Road, from Longtree to SR-1100E, in Cass County. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-10-12 | 2009-12-18 | 641031.41 | 7.500
4432 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900660 | This is a Maintenance Resurfacing project, at Southeastern Avenue from Columbia to 175th St.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-06 | 2010-09-03 | 2010-09-30 | 2010-10-07 | 668918.21 | 1.330
4433 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900661 | This is a Maintenance Resurfacing project, at 45th Avenue from Kennedy to Kleinman; to perform Surface Treatment work. | Pavement Improvement | 2010-01-20 | 2010-09-03 | 2010-09-30 | 2010-10-05 | 340503.85 | 1.230
4434 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900663 | This is a Maintenance Resurfacing project, at Main Street from Wood Ave to Chase St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-05 | 2010-06-01 | 2010-06-30 | 2010-06-25 | 356171.53 | 2.490
4435 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900671 | This project will improve sections and extend the life of 9A Road from city limits to SR 31 in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-06 | 2010-06-30 | 2009-12-14 | 98051.42 | 1.142
4436 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900672 | This project will improve sections and extend the life of Plymouth-Goshen Trail from city limits to Lilac Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 21436.96 | 0.020
4437 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0900673 | This is a Maintenance Resurfacing project, at CR 700 S from 1200W to 3315' West of CR 900W; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-31 | 2010-04-14 | 2010-06-05 | 2010-05-28 | 242489.4 | 2.410
4438 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900674 | This is a Maintenance Resurfacing project, at Kennedy Avenue from Main Street to Junction Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-06 | 2010-07-15 | 2010-08-15 | 2010-10-20 | 254248.74 | 1.470
4439 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900675 | This is a Maintenance Resurfacing project, at 77th Avenue from US 41 to Austin Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-06 | 2010-07-15 | 2010-08-15 | 2010-10-20 | 164673.77 | 1.230
4440 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900676 | This is a Maintenance Resurfacing project, at Lincolnwood Avenue/Old Lincoln Highway from US 30 to 77th Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-06 | 2010-07-15 | 2010-08-15 | 2010-10-20 | 104863.39 | 0.800
4441 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900681 | This project will improve sections and extend the life of Howard County 850 East from County Road 200 North to County Road 400 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 107399.61 | 2.000
4442 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900682 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 700 West to County Road 710 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 6749.21 | 0.140
4443 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900683 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 750 West to County Road 800 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 24723.93 | 0.500
4444 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900684 | This project will improve sections and extend the life of Howard County Road 1150W from CR 400 North to CR 600 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 94897.52 | 2.000
4445 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900685 | This project will improve sections and extend the life of Howard County Road 750W from SR 22 to County Road 200 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 62101.96 | 1.000
4446 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900686 | This project will improve sections and extend the life of Howard County Road 750W with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 122964.18 | 2.200
4447 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900687 | This project will improve sections and extend the life of Howard County Road 750 West from County Road 220 South to Russiaville town limits with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 72800.66 | 1.500
4448 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900688 | This project will improve sections and extend the life of Howard County Road 600 South from County Road 800 West to County Road 870 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 33972.08 | 0.800
4449 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900689 | This project will improve sections and extend the life of Howard County Road 220 South from County Road 750 West to County Road 766 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 7226.35 | 0.130
4450 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900690 | This project will improve sections and extend the life of Howard County Road 750 West from Russioville Town limits to County Road 500 South with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 35986.76 | 0.700
4451 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900691 | This project will improve sections and extend the life of Howard County Road 250 South from from County Road 600 West to County Road 750 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 77286.7 | 1.500
4452 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLAY |  | 08 | 0900692 | This project will replace and restore the pavement on Bowling Green Poland Road, from SR-46 to SR-42, in Clay County. | Pavement Improvement | 2009-09-01 | 2009-09-30 | 2009-11-15 | 2009-11-13 | 631318.18 | 6.720
4453 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900693 | This project will replace and restore the pavement on Monroe Street, from Franklin Street to South 3rd Street, in Warren County. | Pavement Improvement | 2009-09-01 | 2009-09-22 | 2009-11-15 | 2010-06-24 | 324468.42 | 1.170
4454 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900694 | This project will replace and restore the pavement on Cotton Drive from Singhurst Street to SR-159, in Vigo County. | Pavement Improvement | 2009-09-02 | 2009-10-15 | 2009-11-15 | 2009-11-18 | 207440.79 | 0.750
4455 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900695 | This project will replace and restore the pavement on Rio Grande Avenue, from Baldwin Street to Twin Beach Street, in Vigo County. | Pavement Improvement | 2009-09-02 | 2009-10-15 | 2009-11-15 | 2009-11-18 | 195315.58 | 2.355
4456 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PUTNAM |  | 08 | 0900696 | This project will improve sections and extend the life of Walnut Road from the West Greencastle City Limits to West County Line Road in Putnam County with a pavement surface overlay. | Pavement Improvement | 2009-09-03 | 2009-09-22 | 2009-11-15 | 2009-12-01 | 904903.55 | 8.000
4457 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900697 | This is a preventive maintenance resurfacing project, at CR17 from North of CR18 to South of Verdant road in elkhart county to extend the service life of the pavement. | Pavement Improvement | 2009-12-16 | 2010-07-19 | 2010-08-15 | 2010-09-08 | 182260.32 | 0.600
4458 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900698 | This is a Maintenance Resurfacing project, at CR 17 from 900' N of Verdant to SR 120; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-07-19 | 2010-08-15 | 2010-09-08 | 616681.05 | 1.800
4459 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900699 | This is a Maintenance Resurfacing project, at CR 17 from CR 6 to CR 4; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-07-19 | 2010-08-15 | 2010-09-08 | 247651.21 | 1.000
4460 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900700 | This is a Maintenance Resurfacing project, at CR 45 from Fenmore Ave to CR 13; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-07-19 | 2010-08-15 | 2010-09-08 | 190244.13 | 2.100
4461 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900701 | This project will replace and restore the pavement on Rosedale Road, from Rio Grande Avenue to Lambert Street, in Vigo County. | Pavement Improvement | 2009-09-02 | 2009-10-15 | 2009-11-15 | 2009-11-18 | 335034.96 | 3.710
4462 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0900702 | This is a Facilities for Pedestrians and Bicycles project, at SR 3 from Water St. to Park St.; to perform Enhancement work. | Transportation Enhancements | 2009-12-31 | 2010-03-08 | 2010-10-01 | 2010-09-24 | 634688.66 | 0.040
4463 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VERMILLION |  | 08 | 0900704 | This project will replace and restore the pavement on Main Street, from 50' North of the RR tracks to North of the City limits, in Vermillion County. | Pavement Improvement | 2009-09-11 | 2009-10-05 | 2009-11-15 | 2010-05-14 | 293482.42 | 0.568
4464 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900709 | This is a Maintenance Resurfacing project, at SR 62 to Middle Mt Vernon Rd.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-03-30 | 2010-08-31 | 2010-06-03 | 203274.03 | 2.100
4465 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900710 | This is a Maintenance Resurfacing project, at Creamery Rd to SR 66; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-03-30 | 2010-08-31 | 2010-06-03 | 451941.97 | 4.900
4466 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900711 | This project will improve sections and extend the life of Springfield Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-30 | 2009-10-31 | 735695.82 | 9.300
4467 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0900712 | This project will improve sections and extend the life of Road 210 in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-11-07 | 2009-10-21 | 101416.38 | 1.300
4468 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0900713 | This project will improve sections and extend the life of Road 625E in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-11-07 | 2009-10-21 | 89028.43 | 1.200
4469 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0900714 | This project will improve sections and extend the life of Toto Rd in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-11-07 | 2009-10-21 | 602464.54 | 8.300
4470 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900716 | This is a Maintenance Resurfacing project, at 101st(Joliet St.) from US 41 to Parish Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-02-22 | 2010-08-13 | 2010-09-30 | 2010-09-07 | 255425.56 | 1.150
4471 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900717 | This project will improve sections and extend the life of County Road 600West from US 6 to county road 1200 north in Noble County with a pavement surface overlay. | Pavement Improvement | 2009-09-10 | 2009-09-16 | 2009-09-30 | 2009-09-30 | 138858.13 | 4.800
4472 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900718 | This project will improve sections and extend the life of Baseline Road from SR 3 to county road 1200 East in Noble County with a pavement surface overlay. | Pavement Improvement | 2009-09-10 | 2009-09-16 | 2009-09-30 | 2009-09-30 | 35086.24 | 1.500
4473 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900720 | This project will improve the surface and rebuild sections of the bridge on County Road 900 South over Big Blue River in Shelby County. | Bridge Improvement | 2009-09-15 | 2010-04-09 | 2010-07-30 | 2010-05-13 | 60502.5 | 0.010
4474 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BOONE |  | 04 | 0900721 | This project will improve sections and extend the life of Elizaville Road from the Lebanon City Limits to County Road 500 East in Boone County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-05 | 2009-11-15 | 2009-11-11 | 532719.27 | 6.500
4475 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BOONE |  | 04 | 0900722 | This project will improve sections and extend the life of County Road 1200East from County Road 300 South to SR 32 in Boone County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-05 | 2009-11-15 | 2009-11-11 | 66160.22 | 3.000
4476 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BOONE |  | 04 | 0900723 | This project will improve sections and extend the life of County Road 400East from County Road 300 South to SR 32 in Boone County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-05 | 2009-11-15 | 2009-11-11 | 248995.7 | 2.900
4477 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BOONE |  | 04 | 0900724 | This project will improve sections and extend the life of County Road 25West from the Hendricks County Line to County Road 250 South in Boone County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-05 | 2009-11-15 | 2009-11-11 | 388735.98 | 5.600
4478 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900727 | This project will improve sections and extend the life of Bicknell-Oaktown Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-24 | 2009-11-30 | 2009-11-22 | 70107.97 | 1.280
4479 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900728 | This project will improve sections and extend the life of Hart Street Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-24 | 2009-11-30 | 2009-11-22 | 365159.72 | 5.370
4480 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900735 | This project will improve sections and extend the life of River Rd in Warren County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-15 | 2009-12-03 | 193054.36 | 0.110
4481 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900736 | This project will improve sections and extend the life of Independence Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-15 | 2009-12-03 | 532282.63 | 5.530
4482 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900737 | This project will improve sections and extend the life of Rd 300N in Warren County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-15 | 2009-12-03 | 1341777.4 | 13.430
4483 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900738 | This project will improve sections and extend the life of Angling Road from Northport Road to Kendallville City Limits in Noble County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-03 | 2009-10-16 | 2009-10-24 | 260092.09 | 3.000
4484 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 0900739 | This is a Maintenance Resurfacing project, at Old SR 28 to Mulberry City limits; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-25 | 2010-06-30 | 2010-06-30 | 578218.02 | 5.800
4485 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900740 | This project will improve sections and extend the life of Albion Road from US 33 to the Albion City Line in Noble County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-03 | 2009-10-16 | 2009-10-24 | 549995.39 | 7.000
4486 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900741 | This project will improve the surface and rebuild sections of the bridge on County Road 900 South over Big Blue River in Shelby County. | Bridge Improvement | 2009-09-15 | 2010-04-09 | 2010-07-30 | 2010-05-13 | 32037.49 | 0.010
4487 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 0900742 | This is a Maintenance Resurfacing project, at SR 38 to Kelly Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-25 | 2010-06-30 | 2010-06-30 | 274643.69 | 5.000
4488 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 0900743 | This is a Maintenance Resurfacing project, at CR 100 N to CR 600 N.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-25 | 2010-06-30 | 2010-06-30 | 415432.94 | 3.500
4489 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE |  | 02 | 0900745 | This is a Maintenance Resurfacing project, at CR 500 W from SR 2 to Johnson Rd.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-08 | 2010-03-30 | 2010-05-15 | 2010-04-22 | 481582.56 | 3.700
4490 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900771 | This is a Maintenance Resurfacing project, at CR 150 N/100 N/50N from SR 11 to US 50; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-22 | 2009-11-15 | 2009-11-12 | 322891.51 | 6.650
4491 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900772 | This project will improve the pavement from county road 300 north to county road 100 west. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 172031.99 | 2.990
4492 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900775 | This is a Maintenance Resurfacing project, at 300 N from CR 800 E to CR 850 E; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-03-25 | 2010-06-15 | 2010-06-03 | 45111.96 | 0.500
4493 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900778 | This project will improve sections and extend the life of Lower New Harmony Rd with a pavement surface overlay. | Other | 2009-09-01 | 2009-09-25 | 2009-11-30 | 2009-10-30 | 19953.75 | 1.000
4494 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900779 | This project will improve sections and extend the life of O'Donnel Rd/Brittle Bank Rd in Posey County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-30 | 2009-10-30 | 92811.38 | 0.400
4495 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900780 | This is a Maintenance Resurfacing project, at Co Road 30 - Basher Road from Reliance Rd to US 33.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-30 | 2010-06-08 | 2010-08-06 | 2010-08-07 | 187317.05 | 1.480
4496 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900781 | This project will improve sections and extend the life of Main street (Old SR 69) with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-30 | 2009-10-30 | 8290 | 1.200
4497 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900782 | This is a preventive maintenance resurfacing project, on 8th Street from College Avenue to Lincoln Ave in Goshen to extend the pavement surface life. | Pavement Improvement | 2009-11-30 | 2010-06-08 | 2010-08-06 | 2010-08-07 | 229199.95 | 1.410
4498 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900783 | This project will improve sections and extend the life of Embree St in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-09-30 | 2009-09-29 | 142805.24 | 0.689
4499 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900784 | This project will improve sections and extend the life of Makemson Ave in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-09-30 | 2009-09-29 | 15214.16 | 0.133
4500 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900785 | This project will improve sections and extend the life of Seminary St in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-09-30 | 2009-09-29 | 34381.58 | 0.294
4501 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0900786 | This is a Maintenance Resurfacing project, at Lincoln Avenue from Indiana Avenue to Chicago Ave.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-18 | 2010-08-06 | 2010-08-20 | 94565.25 | 0.229
4502 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0900794 | This is a Maintenance Resurfacing project, at 5th Street to 4th St.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-08-31 | 2010-10-18 | 57510.94 | 0.500
4503 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900796 | This project will improve the pavement on county road 500 south from SR 39 to 830 East. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 228007.19 | 3.810
4504 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0900797 | This project will improve sections and extend the life of County Road 715West from SR 44 to BAse Road in Rush County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-10-14 | 2009-11-14 | 2009-10-20 | 171299.93 | 2.360
4505 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900798 | This project will improve the pavement 0n 600 south from 830 east to 1025 east. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 98526.76 | 1.590
4506 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FAYETTE |  | 06 | 0900799 | This project will improve sections and extend the life of Veterans Memorial Highway from SR 121 to SR 1 in Fayette County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-10-14 | 2009-11-13 | 2009-11-23 | 96258.85 | 0.950
4507 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0900802 | This project will improve sections and extend the life of old US 30 from the west county line to 350W in Kosciusko county with a preventive maintenance asphalt overlay. | Pavement Improvement | 2009-09-14 | 2009-10-07 | 2010-07-16 | 2010-07-12 | 724922.92 | 8.000
4508 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0900803 | This project will improve sections and extend the life of Old US 30 from current US 30 to the east County line road in Kosciusko county | Pavement Improvement | 2009-09-14 | 2009-10-07 | 2010-07-16 | 2010-07-12 | 768649.19 | 8.000
4509 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900806 | This project will improve the pavement on county road 850 east from 410 north to 200 north. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 135130.33 | 2.220
4510 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900807 | This is a Maintenance Resurfacing project, at CR 200 N from US 50 to Bridge 91 over White River; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-03-25 | 2010-06-15 | 2010-06-03 | 55956.1 | 0.870
4511 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900809 | This project will improve the pavement on county road 150 south from SR 7 to county road 250 east. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 67492.94 | 0.580
4512 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900810 | This is a Maintenance Resurfacing project, at Roosevelt Road from Vale Park Road to LaPorte Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-07-01 | 2010-08-11 | 616651.4 | 1.770
4513 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900811 | This is a Maintenance Resurfacing project, at Calumet Avenue from GT&W RR (CN RR) to Vale Park Rd.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-07-01 | 2010-08-11 | 324633.03 | 1.150
4514 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900812 | This is a Maintenance Resurfacing project, at Joliet Road from SR 130 to Hayes Leonard Road (SR 150W); to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-07-01 | 2010-08-11 | 203117.59 | 1.150
4515 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900813 | This is a Safety project, at Valparaiso High School - Campbell St. at Vale Park Rd. & John Glenn Dr. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 21309.27 | 0.010
4516 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900814 | This is a Safety project, at Ben Franklin Middle School - Campbell St. at Ridgeland Ave N & Haas St. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 7046.65 | 0.010
4517 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900815 | This is a Safety project, at Northview Elementary School-Campbell St at Roane Ln N & Roseland Terrace S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 12526.98 | 0.010
4518 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900816 | This is a Safety project, at Parkview Elementary School-Roosevelt Rd. at Oak St N & Chicago St. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 9563.13 | 0.010
4519 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900817 | This is a Safety project, at Thomas Jefferson Middle School-Roosevelt Rd. at Glendale Blv. N & Illinois St. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 9563.13 | 0.010
4520 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900818 | This is a Safety project, at Central Elementary School - Morgan Blvd at Erie St.; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 8947.99 | 0.010
4521 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900819 | This is a Scenic or Historic Highway Programs project, at Indiana Ave. between Lafayette St. & Washington St.; Lafayette-SR 130 to Indiana, to perform Enhancement work. | Transportation Enhancements | 2010-04-06 | 2010-04-23 | 2010-06-30 | 2010-08-27 | 258791.1 | 0.010
4522 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900823 | This is a Maintenance Resurfacing project, at CR 265 W/300 W from CR 70 S to US 50; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 63535.97 | 0.870
4523 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900824 | This is a Maintenance Resurfacing project, at CR 300 N from SR 3 to CR 600 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 234630.92 | 4.480
4524 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0900825 | This project will improve sections and extend the life of Jasper-Dubois Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-11-30 | 2009-12-03 | 748081.44 | 6.940
4525 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0900826 | This project will improve sections and extend the life of Rd 1100S in Dubois County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-11-30 | 2009-12-03 | 439834.62 | 5.330
4526 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900833 | This project will extend the life of the pavement on CR 350 N from CR 75 W to 90 E in Jenning county by doing asphalt resurface as Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 96059.05 | 1.650
4527 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900834 | This project will improve the pavement on CR 500 North from SR 3 to Base Road. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 155070.05 | 1.500
4528 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900835 | This project will improve the pavement on CR 550 East/ 600 East from county road 150 south to US 50. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 284003.6 | 5.230
4529 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900840 | This is a Maintenance Resurfacing project, at Oak Hill Road from US 20 to SR 49; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-04-07 | 2010-05-28 | 2010-05-26 | 201906.9 | 1.100
4530 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | Multiple | 0900841 | This is a Maintenance Resurfacing project, at Waverly Road from I-94 bridge abutment to US 12; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-04-08 | 2010-05-28 | 2010-05-25 | 215299.24 | 1.100
4531 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900842 | This is a Maintenance Resurfacing project, at Meridian Road, from US 6 to CR 1050 N; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-06-01 | 2010-05-07 | 265346.52 | 2.500
4532 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900843 | This is a Maintenance Resurfacing project, at CR 700N from Swanson road to Willowcreek Rd.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-06-01 | 2010-05-07 | 97424.24 | 0.740
4533 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 0900844 | This is a Maintenance Resurfacing project, at North Calumet Road, from US 6 to Chesterton Town Limits; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-03-22 | 2010-07-01 | 2010-04-27 | 275142.94 | 1.230
4534 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 0900846 | This is a Maintenance Resurfacing project, at Division Road from SR 49 to 0.5 mi E of SR 49; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-07-07 | 2010-06-30 | 2010-07-16 | 107519.21 | 0.500
4535 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 0900848 | This is a Maintenance Resurfacing project, at CR 250W from Kankakee River to SR 8; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-06-30 | 2010-07-01 | 2010-07-16 | 286233.96 | 2.520
4536 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 0900849 | This is a Maintenance Resurfacing project, at Division Road from CR 400E to CR 575 E; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-07-07 | 2010-07-02 | 2010-07-16 | 189763.8 | 1.760
4537 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900851 | This is a Maintenance Resurfacing project, at Samuelson Road from 750 ft. South of Indiana Toll Road to Portage Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-15 | 2010-04-13 | 2010-06-01 | 2010-05-27 | 162562.74 | 1.050
4538 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900852 | This is a Maintenance Resurfacing project, at Central Avenue from Bridge over Willowcreek to Elm St.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-15 | 2010-04-13 | 2010-06-01 | 2010-05-27 | 156007.61 | 0.830
4539 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900853 | This is a Maintenance Resurfacing project, at Swanson Road from CR 700N to US 6; to perform Surface Treatment work. | Pavement Improvement | 2010-01-15 | 2010-04-13 | 2010-06-01 | 2010-05-27 | 221096.56 | 0.940
4540 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900855 | This is a Landscaping project, at Intersection of Willowcreek Rd & Country Side Pk Entrance on US 6 - Landscaping; to perform Landscaping work. | Transportation Enhancements | 2010-01-15 | 2010-04-05 | 2010-05-15 | 2010-05-14 | 85511.15 | 0.010
4541 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900856 | This is a Maintenance Resurfacing project, at Fir Road from McKinley Avenue to Spur line of Railroad; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-06-10 | 2010-09-30 | 2010-09-28 | 64603.59 | 0.850
4542 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900857 | This is a Maintenance Resurfacing project, at McKinley Avenue (US 20) from Division Street to Home St.; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-06-10 | 2010-09-30 | 2010-09-28 | 304493.53 | 1.290
4543 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900858 | This is a Safety project, at SR 933 - City Wide Traffic Signal Modernization; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2009-12-31 | 2010-02-01 | 2010-09-30 | 2010-03-23 | 282557.16 | 0.010
4544 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE |  | 01 | 0900860 | This is a Safety project, at Various roadways within the town of Winfield; to perform Signing work. | Safety/Traffic Management | 2010-02-22 | 2010-04-13 | 2010-04-30 | 2010-04-20 | 33561.99 | 0.010
4545 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE |  | 01 | 0900862 | This is a Maintenance Resurfacing project, at Randolph Street from 129th Avenue to 123rd Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-08-11 | 2010-07-31 | 2010-08-30 | 98462.18 | 0.880
4546 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900864 | This is a Maintenance Resurfacing project, at Twyckenham Drive from Rockne Drive to South Bend Avenue (SR 23); to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 174928.66 | 0.706
4547 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900865 | This is a Maintenance Resurfacing project, at Western Avenue from Walnut Street to Chapin St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 238542.75 | 0.400
4548 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900866 | This is a Maintenance Resurfacing project, at McKinley Avenue from 500ft East of Ironwood Drive to Preston Dr.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 145765.73 | 0.638
4549 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900867 | This is a Maintenance Resurfacing project, at Western Avenue from Lombardy Drive to Albert Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 114693.34 | 0.278
4550 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900868 | This is a Maintenance Resurfacing project, at Edison Road from Ironwood Drive to Hickory Rd.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 229667.43 | 0.952
4551 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900869 | This is a Maintenance Resurfacing project, at Ireland Road from East of Miami Street to Ironwood Dr.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 222483.43 | 0.866
4552 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900870 | This is a Maintenance Resurfacing project, at Portage Avenue from 370' N of Cleveland Road to Appaloosa Ln.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 86365.36 | 0.489
4553 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900871 | This is a Maintenance Resurfacing project, at Ireland Road from St. Joseph Street to High St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 128937.28 | 0.492
4554 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900872 | This is a Maintenance Resurfacing project, at Portage Avenue from Elwood Avenue to Lathrop St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 241847.6 | 1.050
4555 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900873 | This is a Maintenance Resurfacing project, at Lincolnway W from Chapin Street to Olive St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 391219.1 | 1.356
4556 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900874 | This is a Maintenance Resurfacing project, at Main Street from Chippewa Street to Sample St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 414470.8 | 1.991
4557 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900876 | This is a Safety project, at Sample Street and Mayflower Road Intersection; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-02-22 | 2010-03-18 | 2010-06-15 | 2010-04-30 | 30497.75 | 0.010
4558 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900877 | This is a Safety project, at Angela Avenue and North Shore Drive Intersection; to perform Traffic Signal Maintenance work. | Safety/Traffic Management | 2010-02-22 | 2010-03-18 | 2010-06-15 | 2010-04-30 | 27775 | 0.010
4559 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900885 | This is a Maintenance Resurfacing project, at CR 800 W from 825 S to SR 250; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 88976.43 | 1.470
4560 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900886 | This is a Maintenance Resurfacing project, at CR 825 S from CR 800 W to CR 900 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 96791.11 | 1.130
4561 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900889 | This project will improve the pavement on County Road 90 west/95 west from county road 115 to Base Road. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 94768.93 | 0.950
4562 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0900890 | This is a Maintenance Resurfacing project, at County Road 10 - John Weaver Parkway from CR 10 to CR 6; to perform Resurface over Asphalt Pavement work. | Pavement Improvement | 2010-01-21 | 2010-04-29 | 2010-08-31 | 2010-08-20 | 427674.32 | 2.250
4563 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0900891 | This is a Maintenance Resurfacing project, at Beardsley Ave from Nappanee St to 100' W of Beech St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-21 | 2010-04-29 | 2010-08-31 | 2010-08-20 | 51041.18 | 1.190
4564 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | OHIO |  | 09 | 0900897 | This is a Maintenance Resurfacing project, at Cass Union Rd from Aberdeen Rd/SR 56 to SR 262; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-05 | 2010-06-30 | 2010-05-24 | 387501.1 | 6.600
4565 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | OHIO |  | 09 | 0900898 | This is a Maintenance Resurfacing project, at Hartford pike from Woods Ridge Road to Nelson Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-08 | 2010-06-30 | 2010-05-24 | 165988.23 | 1.700
4566 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | OHIO |  | 09 | 0900899 | This is a Maintenance Resurfacing project, at Nelson Rd from Hartford Pike to Rising Sun Limits; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-08 | 2010-06-30 | 2010-05-24 | 550595.47 | 3.700
4567 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900900 | This project will improve sections and extend the life of Centenary Rd. from Henderson Ford Road to 1 mile South of SR 144 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 277355.96 | 3.400
4568 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900901 | This project will improve sections and extend the life of old SR 37 from Martinsville City Limits to SR 37 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 111468.8 | 1.700
4569 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900902 | This project will improve sections and extend the life of Paragon Rd. from SR 67 to SR 37 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 286593.27 | 5.700
4570 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0900904 | This is a Maintenance Resurfacing project, at Lancaster St from Adams St to Bond St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-11 | 2010-06-12 | 2010-03-30 | 62063.86 | 1.000
4571 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0900905 | This is a Maintenance Resurfacing project, at Western Ave from Decker Dr.; to Midway St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-11 | 2010-06-12 | 2010-03-30 | 40637.19 | 0.400
4572 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0900906 | This is a Maintenance Resurfacing project, at Midway St from Western Ave.; to W Washington St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-11 | 2010-06-12 | 2010-03-30 | 88840.16 | 0.250
4573 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900911 | This is a project, at Joliet Street (93rd Avenue) at US 41; to perform Storm Sewer Repair Or Replacement work. | Other | 2010-03-04 | 2010-05-26 | 2010-07-31 | 2010-09-03 | 378584.97 | 0.010
4574 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900915 | This is a Safety project, at SR 933 - Various locations City wide; to perform Sign Modernization (Series Of Units) work. | Safety/Traffic Management | 2009-12-31 | 2010-08-24 | 2010-09-30 | 2010-11-09 | 68709.01 | 0.010
4575 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900916 | This project will improve sections and extend the life of Rueben Dr. from Old SR 37 to SR 37 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 33596.3 | 0.500
4576 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900917 | This project will improve sections and extend the life of Rob Hill Rd fROM SR 39 TO SR 67 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 244217.24 | 3.400
4577 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900918 | This project will improve sections and extend the life of Blue Bluff Rd. from Centerton Rd. to Bridge with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 92905.41 | 1.200
4578 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900923 | This is a Maintenance Resurfacing project, at Third St. from Cherry St. to Montgomery St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 65948.04 | 0.562
4579 | Underway | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0900927 | Added Travel Lanes on I465, 82nd St from 0.2 mi W of I-465 to 0.14 mi E of I-465 | Pavement Widening | 2010-11-01 | 2010-12-28 | 2011-10-15 |  | 2347714.92 | 0.010
4580 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900929 | This is a Maintenance Resurfacing project, at Montgomery St from Main St to Third St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 80048.13 | 0.180
4581 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900930 | This project will improve the pavement on county road 500 east from county road 560 north to the county line. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 344662.67 | 6.140
4582 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900931 | This project will improve the pavement on Base Road/ County Road 20 West near North Vernon. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 158550.61 | 3.090
4583 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900932 | This is a Maintenance Resurfacing project, at CR-115S from CR-75W to Vernon; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 65914.15 | 0.010
4584 | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900935 | This project will improve sections and extend the life of Greensburg Street from US 50 to Woodlaen Drive in Jennings County with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-03-08 | 2010-07-15 | 2010-06-18 | 44291.19 | 0.440
4585 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0900937 | This is a Maintenance Resurfacing project, at US 41 to SR 341; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-20 | 2010-07-15 | 2010-07-14 | 485757.43 | 3.000
4586 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0900938 | This is a Maintenance Resurfacing project ,at SR 341 to Fountain/Montgomery County Line; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-20 | 2010-07-15 | 2010-07-14 | 283668.99 | 5.000
4587 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0900939 | This is a Maintenance Resurfacing project, at Covington City Limits to US 41; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-20 | 2010-07-15 | 2010-07-14 | 954086.16 | 7.800
4588 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900940 | This is a Maintenance Resurfacing project, at Main St from Lake Rd to Montgomery St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 175719.49 | 1.500
4589 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0900941 | This project will improve sections and extend the life of Michigan Road from West Street to Green Road in Jefferson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-11-15 | 2009-10-07 | 164209.29 | 1.890
4590 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900944 | This project will improve the traffic signs in the town of Galveston in Cass County. | Safety/Traffic Management | 2009-09-15 | 2009-10-26 | 2009-11-30 | 2009-11-23 | 41888.73 | 0.010
4591 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900945 | This project will improve the traffic signs in the town of Royal Center in Cass County. | Safety/Traffic Management | 2009-09-15 | 2009-10-26 | 2009-11-30 | 2009-11-23 | 5221.19 | 0.010
4592 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900946 | This project will improve the traffic signs in the town of Walton in Cass County. | Safety/Traffic Management | 2009-09-15 | 2009-10-26 | 2009-11-30 | 2009-11-23 | 10075.69 | 0.010
4593 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900948 | This project will improve sections and extend the life of Patterson Rd from Watkins St to Kenilworth Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 74686.15 | 0.700
4594 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900949 | This project will improve sections and extend the life of Beech Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 79231.77 | 0.750
4595 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900950 | This project will improve sections and extend the life of Timothy Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 53896.63 | 0.500
4596 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900952 | This project will improve sections and extend the life of Tamarach Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 396092.45 | 3.600
4597 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900953 | This project will improve sections and extend the life of Kern Rd in St Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 170869.44 | 1.900
4598 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900954 | This project will improve sections and extend the life of Oak Rd from New Rd to Roosevelt Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 195944.75 | 2.000
4599 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900955 | This project will improve sections and extend the life of Walkerton Trail from 0.01 MI S of Georgia St to 0.1 MI S of SR 23 with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 95534.15 | 0.800
4600 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900956 | This project will improve sections and extend the life of Main St in Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 30644.32 | 0.120
4601 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900957 | This project will improve sections and extend the life of Washington St in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 24899.42 | 0.100
4602 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900958 | This project will improve sections and extend the life of Patterson Rd from 0.04 MI E of Beeckler Court to Watkins St with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 21998.43 | 0.090
4603 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900959 | This project will improve sections and extend the life of Walkerton Trail in St. Joseph county from Spruce Rd to 0.1 MI S of Georgia St with a preventive maintenance pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 132570.87 | 0.050
4604 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900960 | This project will improve sections and extend the life of Mayflower Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 26719.91 | 0.300
4605 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900961 | This project will improve sections and extend the life of Sumption Trail in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 46175.6 | 0.800
4606 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900962 | This project will improve sections and extend the life of Oak Rd from Roosevelt Rd to Kern Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 56716.64 | 1.000
4607 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900963 | This project will improve sections and extend the life of Beech Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 149295.99 | 3.200
4608 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900964 | This project will improve traffic signs in Walkerton in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 50414.87 | 0.010
4609 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900965 | This project will improve the traffic signs in North Liberty in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 38045.14 | 0.010
4610 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900966 | This project will improve the signs in New Carlisle in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 48885.14 | 0.010
4611 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900967 | This project will improve the traffic signs in Lakeville in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 35355.85 | 0.010
4612 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900968 | This project will improve the traffic signs in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 148249.03 | 0.010
4613 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900969 | This is a Maintenance Resurfacing project, at Morse Street from 149th to Lowell Corp Limits; to perform Surface Treatment work. | Pavement Improvement | 2010-01-11 | 2010-05-19 | 2010-06-30 | 2010-07-20 | 536728.84 | 3.360
4614 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900970 | This is a Maintenance Resurfacing project, at Cedar Lake Road form 121st to 133rd; to perform Surface Treatment work. | Pavement Improvement | 2010-01-12 | 2010-04-23 | 2010-06-30 | 2010-07-20 | 262314.46 | 1.640
4615 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PIKE |  | 08 | 0900982 | This is a Maintenance Resurfacing project, at E Old SR 64 - SR 257 to CR 1100E; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-04 | 2010-08-31 | 2010-06-25 | 250364.52 | 3.700
4616 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PIKE |  | 08 | 0900983 | This is a Maintenance Resurfacing project, at CR 500E to SR 257; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-04 | 2010-08-31 | 2010-06-25 | 105812.74 | 1.560
4617 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0900987 | This is a trail construction project for pedestrians and bicycles at Tell City Riverfront, 1,800' south of Washington St to 3,400' north of the plaza in Tell City in Perry county using enhancement fun | Transportation Enhancements | 2009-12-18 | 2010-05-19 | 2010-08-31 | 2010-10-19 | 434981.44 | 1.010
4618 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900988 | This project will improve sections and extend the life of Dekalb County Road 48 with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-06 | 2010-10-31 | 2010-06-07 | 231953.6 | 1.600
4619 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900991 | This is a Maintenance Resurfacing project, at Elm St from Lake Rd to SR 56; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 104350.1 | 1.000
4620 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900993 | This project will improve sections and extend the life of Wayne Street from Cedar Street to Walnut Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 145818.95 | 0.770
4621 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0900994 | This is a Maintenance Resurfacing project, at Arlington Ave. from 38th St. to 56th St.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-03-01 | 2010-06-30 | 2010-06-30 | 1643950 | 2.000
4622 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900995 | This is a Maintenance Resurfacing project, at Beechwood and Allen St. from SR 56 to US 31; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 36599.39 | 0.460
4623 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900996 | This project will improve sections and extend the life of N. Commerce Drive in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 36035.67 | 0.210
4624 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900997 | This project will improve sections and extend the life of Center Street from US 6 to Rope Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 52177.97 | 0.480
4625 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900998 | This project will improve sections and extend the life of Rope Street from Center Street to SR 427 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 72891.25 | 0.470
4626 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900999 | This project will improve sections and extend the life of Walnut Street from Albright Street to SR 39 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 43813.57 | 0.250
4627 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901000 | This project will improve sections and extend the life of Walnut Street from Center Street to Wayne Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 45097.81 | 0.250
4628 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901004 | This is a Maintenance Resurfacing project, at Colfax Street from Belshaw Road to 231st Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-06-04 | 2010-06-02 | 608420.42 | 4.900
4629 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901005 | This is a Maintenance Resurfacing project, at 231st Avenue from Monon Road to Colfax St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-06-04 | 2010-06-02 | 300548.26 | 2.850
4630 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0901021 | This is a Maintenance Resurfacing project, at Cherry St. from US 31 to Third St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 40358.15 | 0.610
4631 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0901022 | This is a Maintenance Resurfacing project, at Wardell St from US 31 to Third St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 79478.37 | 0.610
4632 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0901023 | This project will improve sections and extend the life of County Road 400North from County Road 850 East to County Road 900 East in Howard County with a pavement surface overlay. | Transportation Enhancements | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 39469.5 | 0.500
4633 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0901024 | This is a Maintenance Resurfacing project, at Gerald Rd (CR 10) to SR 70; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-04-14 | 2010-08-31 | 2010-07-21 | 376584 | 3.900
4634 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901026 | This project will improve sections and extend the life of New Market Road from SR 3 to Zimmerman Road in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-29 | 2010-04-30 | 2009-11-02 | 202273.16 | 3.100
4635 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901027 | This project will improve sections and extend the life of Camp Creek-Bethlehem Road from Flint Road to Bethlehem New Washington in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-08-20 | 2009-09-29 | 2009-11-13 | 2009-10-22 | 178063.94 | 3.070
4636 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901029 | This project will improve sections and extend the life of Charlestown-Memphis Road from US 31 to SR 160 in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-10-09 | 2009-10-30 | 2010-04-30 | 2009-11-20 | 307001.48 | 5.900
4637 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0901030 | This project will improve sections and extend the life of County Road 750West from County Road 300 North to County Road 400 North in Howard County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 57809.87 | 1.000
4638 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0901031 | This project will improve sections and extend the life of County Road 100North from County Road 400 East to County Road 500 East in Howard County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 68854.09 | 1.000
4639 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON |  | 05 | 0901032 | This is a Maintenance Resurfacing project, at 146th St from Hamilton/Boone County line to Ditch Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-14 | 2010-06-18 | 2010-06-03 | 308907.44 | 3.050
4640 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901036 | This project will improve sections and extend the life of Salisbury Road from Nolands Fork Road to Williamsburg Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-13 | 2009-11-03 | 155421.92 | 0.650
4641 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901037 | This project will improve sections and extend the life of 37th Street from Hodgin Road to US 40 in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-20 | 2009-11-10 | 544186.16 | 1.140
4642 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901038 | This project will improve sections and extend the life of Industries Road from Williamsburg Pike to Union Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-06 | 2009-11-03 | 219725.43 | 0.610
4643 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901039 | This project will improve sections and extend the life of Southway 31 in Fulton County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-05 | 2009-11-25 | 2009-10-16 | 115530.27 | 1.100
4644 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901040 | This is a Maintenance Resurfacing project, at Old US 31 N from CR 350N to SR 110; to perform Surface Treatment work. | Pavement Improvement | 2009-10-14 | 2009-10-26 | 2010-06-30 | 2009-11-23 | 449932.91 | 4.700
4645 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901041 | This is a Maintenance Resurfacing project, at Greenwood Avenue between SR 231 and SR 55; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-16 | 2010-04-14 | 2010-06-01 | 2010-06-01 | 253502.62 | 2.560
4646 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901042 | This is a Maintenance Resurfacing project, at Court Street from the North side of Town Square to 121st. St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-16 | 2010-04-14 | 2010-06-01 | 2010-06-01 | 435566.77 | 1.280
4647 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901043 | This is a Maintenance Resurfacing project, at 49th Avenue from Broadway to Grant; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-03-31 | 2010-06-01 | 2010-06-01 | 336330.85 | 0.750
4648 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901044 | This is a Maintenance Resurfacing project, at 15th Avenue from I-65 to Martin Luther King Dr.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-04-06 | 2010-06-01 | 2010-06-01 | 232517.79 | 0.650
4649 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901045 | This is a Maintenance Resurfacing project, at 35th Avenue from Broadway to Martin Luther King Dr.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-03-31 | 2010-06-01 | 2010-06-01 | 401067.83 | 0.930
4650 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901046 | This is a preventive maintenanc eresurfacing project, at Olson Road from CR 700 W to SR 17 in Fulton county to provide 1 inch of asphalt to extend the pavement life. | Pavement Improvement | 2009-10-14 | 2009-10-26 | 2010-06-30 | 2009-11-23 | 206332.77 | 3.500
4651 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901047 | This project will improve sections and extend the life of Wabash Ave with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-05 | 2009-11-25 | 2009-10-16 | 108235.99 | 1.600
4652 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901048 | This is a Maintenance Resurfacing project, at CR 550 S from CR 1200 W(Fulton/Pulaski Co Line) to SR 17; to perform Surface Treatment work. | Pavement Improvement | 2009-10-14 | 2009-10-26 | 2010-06-30 | 2009-11-23 | 167279.28 | 2.800
4653 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901049 | This is a Maintenance Resurfacing project, at CR 600 S from SR 25 to CR 250 E; to perform Surface Treatment work. | Pavement Improvement | 2009-10-14 | 2009-10-26 | 2010-06-30 | 2009-11-23 | 163888.4 | 2.800
4654 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901050 | This project will improve sections and extend the life of Engle Road from St John Road to Floyd County in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-27 | 2010-04-30 | 2009-11-09 | 107832.81 | 1.220
4655 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901051 | This is a Maintenance Resurfacing project, at Hibernia Rd. from SR 62 to Charlestown Bethlehem Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2009-10-20 | 2009-11-13 | 2009-11-02 | 104312.85 | 1.430
4656 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901052 | This project will improve sections and extend the life of Marble Hill Road from SR 62 to Gill Road in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-29 | 2010-04-30 | 2009-11-02 | 140774.25 | 1.720
4657 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0901057 | This is a Maintenance Resurfacing project, at Old State Rd 62 from US 421 to SR 62; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2009-10-26 | 2009-11-15 | 2009-11-14 | 135612.23 | 1.970
4658 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901059 | This is a Maintenance Resurfacing project, at Main Street from CR 800 to the RR Tracks at the town limit; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-05-28 | 2010-06-25 | 2010-06-25 | 357838.25 | 1.340
4659 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0901060 | This project will improve the pavement with a preventive maintenance resurface on Base Road/County Road 25 East from White River to SR 2 in Jackson county. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 488093.28 | 5.670
4660 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901062 | This project will improve sections and extend the life of Martinsburg Knob Road from Borden Greenville Road to Washington County in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-08 | 2009-11-13 | 2009-11-04 | 187952.67 | 3.690
4661 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901063 | This project will improve sections and extend the life of New Hope Church Road from Bethlehem Road to Jefferson County in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-29 | 2010-04-30 | 2009-11-02 | 83118.28 | 1.100
4662 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901065 | This is a Maintenance Resurfacing project, at 38th Street from 460 feet E of Adams Street/SR 15 to S Todd Street to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 557324.66 | 1.680
4663 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901066 | This is a Maintenance Resurfacing project, at Adams Street from 29th street to 26th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 119170.52 | 0.350
4664 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901067 | This is a Maintenance Resurfacing project, at Nebraska Street from 26th Street to 23rd Street to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 477712.38 | 1.480
4665 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0901068 | This is a Maintenance Resurfacing project, at Adams Street from Railroad Tracks S of 11th Street to 3rd St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 226375.74 | 0.580
4666 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901069 | This is a Maintenance Resurfacing project, at Washington Street from 38th street to Wabash Ave.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 959542.41 | 2.670
4667 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901070 | This project will improve sections and extend the life of Kem Road from Miller Avenue to Wabash Avenue in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-13 | 2009-10-31 | 2009-11-08 | 246550.42 | 1.030
4668 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901071 | This is a Maintenance Resurfacing project, at Allisonville Rd from Fall Creek Rd to 46th St.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-24 | 2010-06-04 | 2010-06-30 | 2010-08-20 | 239371.27 | 0.050
4669 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901072 | This is a Maintenance Resurfacing project, at 62nd St from Keystone Ave to Allisonville Rd.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-03-15 | 2010-06-30 | 2010-07-01 | 521300 | 1.300
4670 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901073 | This is a Maintenance Resurfacing project, at State St from I-265 to Green Valley Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-04-09 | 2010-06-19 | 2010-06-18 | 265600 | 0.730
4671 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901074 | This is a Maintenance Resurfacing project, at Old SR 37 S, from SR 37 to Rogers St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-03-29 | 2010-07-30 | 2010-05-24 | 181380.86 | 0.950
4672 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901076 | This is a preventive maintenance resurfacing project, at Old SR 37 N in Monroe county , from Whisnand Rd to Wylie Rd. to extend the life of the pavement. | Pavement Improvement | 2009-11-23 | 2010-04-08 | 2010-07-30 | 2010-08-18 | 330820.04 | 2.340
4673 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901077 | This is a Maintenance Resurfacing project, at Monroe Dam Rd, from SR 37 to Strain Ridge Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-29 | 2010-07-30 | 2010-05-27 | 117238.04 | 0.773
4674 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901078 | This is a Maintenance Resurfacing project, at Rockport Road from Victor Pike to May Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-06 | 2010-07-30 | 2010-07-29 | 403313.71 | 3.128
4675 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901079 | This is a Maintenance Resurfacing project, at Fairfax Road, from Pointe Rd to Dillman Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-05 | 2010-07-30 | 2010-07-22 | 695947.21 | 4.720
4676 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901080 | This is a Bridge Replacement (no added capacity) project, at Bridge over Lick Creek in Sarah Bolton Park; to perform Bridge Replacement, Special work. | Bridge Replacement | 2010-02-22 | 2010-04-06 | 2010-09-03 | 2010-09-02 | 341363.39 | 0.010
4677 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901081 | This is a preventive maintenance resurfacing project, at Greenfield Avenue (formerly SR 238) in Hamilton county to extend the pavement life. | Pavement Improvement | 2009-12-31 | 2010-05-17 | 2010-06-30 | 2010-06-29 | 311055.35 | 2.880
4678 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901082 | This is a Maintenance Resurfacing project, at Emerson Ave from 38th St to 56th St.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-03-18 | 2010-09-30 | 2010-09-24 | 1490522 | 2.000
4679 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901083 | This is a Maintenance Resurfacing project, at Paoli Pike from Hilltop Rd to 267 feet W of Boe Creek Dr.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-31 | 2010-05-22 | 2010-07-21 | 293500 | 1.970
4680 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901084 | This is a Maintenance Resurfacing project, at Georgetown-Greenville Road from Church Rd.; to Harrison St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-25 | 2010-04-08 | 2010-06-12 | 2010-06-07 | 363000 | 6.500
4681 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901086 | This project will improve sections and extend the life of Garthwaite Road in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 100685.68 | 1.120
4682 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901087 | This project will improve sections and extend the life of County Road 300South from County Road 300 West to SR 37 in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 218205.79 | 3.000
4683 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901088 | This project will improve sections and extend the life of County Road 600East from SR 18 to County Road 700 North in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 467332.26 | 6.760
4684 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901089 | This project will improve sections and extend the life of County Road 200North from County Road 300 East to County Road 600 East in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 218843.62 | 3.000
4685 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901090 | This project will improve sections and extend the life of County Road 400East from Walnut Creek to County Road 200 South in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 98260.27 | 1.500
4686 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901091 | This project will improve sections and extend the life of County Road 950East from Matthews Town Limits to SR 26 in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 224068.95 | 2.270
4687 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0901093 | This project will improve sections and extend the life of Olive Trail from 13th Road to Overmyer Drive in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 66651.01 | 3.709
4688 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BLACKFORD |  | 06 | 0901096 | This project will improve sections and extend the life of Wabash Avenue from Kickapoo Street to Park Avenue in Blackford County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-12 | 2009-10-30 | 2009-10-27 | 73667.35 | 0.300
4689 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901097 | This project will improve sections and extend the life of County Road 40 from SR 1 to State Line in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-01 | 2009-10-30 | 2009-11-04 | 270802.5 | 3.400
4690 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901098 | This project will improve sections and extend the life of Auburn Drive from Diehl Drive to Wayne Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-06 | 2009-10-31 | 2009-11-04 | 153639.84 | 1.420
4691 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901099 | This project will improve sections and extend the life of Main Street from Gates Cove to County Road 36 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-06 | 2009-10-31 | 2009-11-04 | 153688.07 | 1.420
4692 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS | INDIANAPOLIS | 04 | 0901100 | This is a Maintenance Resurfacing project, at From 2500 N. Dan Jones to approx. 3000 S. Dan Jones Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-02-22 | 2010-05-01 | 2010-05-05 | 1062064.84 | 4.200
4693 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS | INDIANAPOLIS | 04 | 0901101 | This is a Safety project, at CR 200 N & Ronald Reagan Pkwy.; to perform Traffic Signals, New Or Modernized work. | Safety/Traffic Management | 2009-10-23 | 2009-11-16 | 2010-06-30 | 2010-03-24 | 169869.75 | 0.010
4694 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901102 | This is a Maintenance Resurfacing project, at Wiggins St. to just south of Robinison St.; to perform Resurface over Asphalt Pavement work. | Pavement Improvement | 2009-11-23 | 2010-05-18 | 2010-06-30 | 2010-07-02 | 272515.74 | 0.530
4695 | Completed | C220,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901106 | This is a Facilities for Pedestrians and Bicycles project, at New trail from Clarendon Dr. to Edgewater Dr. paralled to Carrigan Rd.; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-05-14 | 2010-07-12 | 2010-11-15 | 2011-05-09 | 1263268.75 | 0.305
4696 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901110 | This is a Bridge Rehabilitation (no added capacity) project, at Emerson Ave. over CSX Railroad; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2009-12-30 | 2010-02-22 | 2010-07-31 | 2010-06-23 | 426709.45 | 0.028
4697 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901112 | This is a Maintenance Resurfacing project, between Battleground Town limits & Tyler Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-05 | 2010-03-19 | 2010-06-30 | 2010-05-13 | 247152.52 | 0.040
4698 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901113 | This is a Maintenance Resurfacing project, at Ridge Road from Colfax Avenue to Grant St.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-13 | 2010-04-30 | 2010-06-30 | 2010-07-23 | 967860.55 | 2.990
4699 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0901122 | This is a Maintenance Resurfacing project, at NW 21st St to Front St.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-08-31 | 2010-07-06 | 70179.83 | 0.760
4700 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0901123 | This is a Maintenance Resurfacing project, at US 50 to W Main St.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-08-31 | 2010-07-06 | 43893.86 | 0.380
4701 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0901124 | This is a Maintenance Resurfacing project, at Jackson St to Wykoff Ln.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-08-31 | 2010-07-06 | 40996.12 | 0.380
4702 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0901125 | This is a Maintenance Resurfacing project, at Field Ave to NW 21st St.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-08-31 | 2010-07-06 | 45965.06 | 0.510
4703 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0901126 | This is a Maintenance Resurfacing project, at Leota Rd from Boatman Rd to US 31; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-29 | 2010-05-31 | 2010-05-06 | 156789.65 | 2.200
4704 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901127 | This is a Maintenance Restoration & Rehabilitation project, at 56th St. from Boy Scout Rd. to Ciato Rd.; to perform Pavement, Other work. | Pavement Improvement | 2010-04-01 | 2010-06-03 | 2010-08-15 | 2010-08-05 | 233325 | 0.500
4705 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901128 | This is a Bridge Rehabilitation (no added capacity) project, at Westfield Blvd. over White River; to perform Bridge Deck Overlay work. | Bridge Improvement | 2009-12-30 | 2010-02-22 | 2010-07-31 | 2010-06-23 | 348011.01 | 0.096
4706 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901129 | This is a Maintenance Resurfacing project, at Edwardsville-Galena Rd from Oaks Road to Bridge over Little Indian Creek; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-16 | 2010-05-05 | 2010-07-19 | 191300 | 3.600
4707 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0901130 | This is a Maintenance Resurfacing project at Washington Blvd from Mulberry St. to Market St. to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-30 | 2009-11-02 | 2009-11-30 | 2009-11-19 | 52646.81 | 0.340
4708 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901131 | This is a Maintenance Resurfacing project, at Tibbs Ave. from 16th St. to Lafayette Rd.; to perform Partial 3-R work. | Pavement Improvement | 2009-12-31 | 2010-04-12 | 2010-08-16 | 2010-07-12 | 361104.1 | 1.200
4709 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901132 | This is a Maintenance Resurfacing project, at Thompson Rd. from Emerson Ave. to Franklin Rd.; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-03-03 | 2010-08-16 | 2010-09-22 | 1199315.16 | 3.400
4710 | Underway | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901133 | This is a Maintenance Resurfacing project, at Southeastern Ave. from Raymond St. to Sheridan Ave.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-02 | 2010-10-04 |  | 1275406.63 | 0.080
4711 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901134 | This is a Maintenance Resurfacing project, at Sam Jones Parkway from I-465 to I-70; to perform Partial 3-R work. | Pavement Improvement | 2009-12-31 | 2010-04-12 | 2010-08-16 | 2010-07-12 | 727847.17 | 1.300
4712 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901136 | This is a Maintenance Resurfacing project, at Central Avenue from Benton Street to County Line Rd.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-19 | 2010-04-06 | 2010-06-09 | 2010-08-02 | 486985.59 | 3.000
4713 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE |  | 02 | 0901137 | This is a Maintenance Resurfacing project, at Wozniak Road from SR 2 to CR 400 N; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-06 | 2010-04-06 | 2010-05-15 | 2010-05-05 | 1094730.38 | 7.300
4714 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901138 | This is a Reconstruction (no added capacity) project, at Summit, Between Wirtz Road and Jennings Place; to perform Other Type Project (Miscellaneous) work. | Pavement Improvement | 2010-02-25 | 2010-06-13 | 2010-07-01 | 2010-07-20 | 166804.2 | 0.010
4715 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PULASKI |  | 02 | 0901139 | This project will improve sections and extend the life of County Road 500S outh from Market Street to county road 1050 west in Pulaski County with a pavement surface overlay. | Pavement Improvement | 2009-12-31 | 2010-07-23 | 2010-08-27 | 2010-08-17 | 91016.58 | 3.860
4716 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901140 | This is a Maintenance Resurfacing project, at Wabash Avenue from Calumet Road to Waverly Rd.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-13 | 2010-07-01 | 2010-06-04 | 105466.09 | 0.600
4717 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901141 | This is a Maintenance Resurfacing project, at 11th Street from CR 1100 N to Porter Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-13 | 2010-07-01 | 2010-06-04 | 133054.67 | 0.910
4718 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901142 | This is a Maintenance Resurfacing project, at Porter Avenue from 15th St. to 23rd St.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-13 | 2010-07-01 | 2010-06-04 | 84335.06 | 0.520
4719 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0901145 | This is a Maintenance Resurfacing project, at SR 135 - Market St. from Washington Blvd to Alpine St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-30 | 2009-11-02 | 2009-11-30 | 2009-11-19 | 91557.87 | 0.720
4720 | Underway | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901148 | This is a Maintenance Resurfacing project, at Raymond St. from Shelby St. to Southeastern Ave.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-02 | 2010-10-04 |  | 2847684.79 | 3.600
4721 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901149 | This is a Bridge Rehabilitation (no added capacity) project, at Holt Rd. bridge over Big Eagle Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2009-12-03 | 2010-06-01 | 2010-09-30 | 2010-09-28 | 822708.1 | 0.068
4722 | Underway | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901151 | This is a Maintenance Resurfacing project, at Franklin Way/Rd. from 21st St. to 30th St.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-02 | 2010-10-04 |  | 465877.43 | 1.000
4723 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901152 | This is a Bridge Rehabilitation (no added capacity) project, at Cumberland Rd. over White River; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-02-22 | 2010-06-01 | 2010-09-01 | 2010-07-30 | 425380.09 | 0.095
4724 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901153 | This is a Maintenance Resurfacing project, at Walnut St. from Southport Rd. to Stop 10 Rd.; to perform Resurface PCC Pavement (Partial 3/R Standards) work. | Pavement Improvement | 2010-01-13 | 2010-06-11 | 2010-08-16 | 2010-08-16 | 154466.89 | 0.542
4725 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901154 | This is a Maintenance Resurfacing project, at Lantern Rd. from South St. to Lantern Wood Dr.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 119679.34 | 0.750
4726 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WABASH |  | 05 | 0901155 | This project will improve sections and extend the life of County Road 250South from Old Sr 15 to America Road in Wabash County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2010-05-06 | 2010-06-18 | 2010-06-18 | 441936.72 | 4.940
4727 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901156 | This is a Maintenance Resurfacing project, at Hague Rd. from 96th St. to 116th St.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 204318.61 | 2.000
4728 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901157 | This is a Maintenance Resurfacing project, at Cumberland Rd. from 121st St. to 141st St.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 189960.09 | 2.000
4729 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901159 | This is a Maintenance Resurfacing project, at Cumberland Rd. from 106th St. to High Point Ridge; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 118730.32 | 0.800
4730 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901160 | This is a Maintenance Resurfacing project, at Brooks School Rd. from 96th St. to 116th St.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 137666.98 | 2.000
4731 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901162 | This is a Maintenance Resurfacing project, at 106th St. from Hague Rd. to Cumberland Rd.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 243841.66 | 2.000
4732 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901163 | This is a Maintenance Resurfacing project, at Hazel Dell Blvd. (see project listing for full description); to perform Partial 3-R work. | Pavement Improvement | 2010-03-05 | 2010-03-30 | 2010-09-07 | 2010-10-01 | 1671831.15 | 2.100
4733 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901165 | This is a Maintenance Restoration & Rehabilitation project, at 75th St.-Pennsyl. St. to College Ave. & sign repl. fr. Spring Mill to College Ave.; to perform Road Rehabilitation work. | Pavement Improvement | 2009-12-16 | 2010-06-02 | 2010-06-01 | 2010-09-07 | 91196 | 0.600
4734 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BLACKFORD |  | 06 | 0901166 | This project will improve sections and extend the life of Park Avenue from Gilkey Ave to Mill Street in Blackford County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-26 | 2010-05-29 | 2009-11-13 | 143863.5 | 1.500
4735 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901167 | This is a Maintenance Resurfacing project, at Elmwood Ave. from E. of Emerson Ave. to W. of Arlington Ave.; to perform Pavement, Other work. | Pavement Improvement | 2009-12-31 | 2010-05-11 | 2010-06-30 | 2010-06-16 | 115088.25 | 1.100
4736 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0901168 | This is a Maintenance Resurfacing project, at Greensburg Rd. from 510 East to 450 E; to perform Pavement, Other work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-05-14 | 2010-05-13 | 102996.8 | 0.800
4737 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0901169 | This is a Maintenance Resurfacing project, at Morgantown Rd. from CR 600N to Fairview Rd.; to perform Pavement, Other work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-05-14 | 2010-05-13 | 292854.81 | 3.880
4738 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0901170 | This is a Maintenance Resurfacing project, at CR 144 from CR 500N to Bargersville City limits; to perform Pavement, Other work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-05-14 | 2010-05-13 | 193734.92 | 2.290
4739 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0901171 | This is a Maintenance Resurfacing project, at County Road 800 N - Olive Branch Rd. from 400 West to SR 135; to perform Pavement, Other work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-05-14 | 2010-05-13 | 84675.38 | 0.850
4740 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MORGAN | INDIANAPOLIS | 04 | 0901172 | This is a Maintenance Resurfacing project, at Mann Rd. from Landersdale Rd. to the Marion County Line; to perform Partial 3-R work. | Pavement Improvement | 2009-12-31 | 2010-04-15 | 2010-08-30 | 2010-05-04 | 128564 | 1.260
4741 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901173 | This is a Maintenance Resurfacing project, at McGallliard Rd. from Wheeling Ave. to Riverside Ave.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-07-02 | 2010-10-01 | 2010-10-01 | 863097.34 | 1.550
4742 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901174 | This is a Maintenance Resurfacing project,at Tillotson Ave from Riverside Ave to SR 332/McGalliard Rd.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-06-24 | 2010-10-01 | 2010-10-05 | 769371.87 | 1.270
4743 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901175 | This project will improve sections and extend the life of Kepler Road from Jacksonburg Road to Washington Road in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-06 | 2009-10-22 | 255826.24 | 1.880
4744 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901176 | This project will improve sections and extend the life of Pottershop Road from Abington to US 27 in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-23 | 2009-10-23 | 2009-10-17 | 62448.04 | 0.160
4745 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901177 | This is a Maintenance Resurfacing project, at SR 38 - Centerville Road (S-8189) from SR 38 to We Oler Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-18 | 2010-05-18 | 2010-06-04 | 2010-06-02 | 574791.59 | 4.440
4746 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901178 | This project will improve sections and extend the life of Jacksonburg Road from Swoveland Road to SR 38 in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-23 | 2009-11-13 | 2009-10-30 | 155774.29 | 1.000
4747 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901179 | This project will improve sections and extend the life of Pottershop Road from Pennville Road to Abington in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2010-06-04 | 2009-10-17 | 59092.13 | 0.270
4748 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901180 | This project will improve sections and extend the life of Pennville Road from Fayette County line to US 40 in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-06 | 2009-11-02 | 794659.49 | 6.770
4749 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901181 | This project will improve sections and extend the life of Centerville Road from I-70 to SR 38 with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-12 | 2009-11-13 | 2009-11-09 | 221065 | 1.520
4750 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901182 | This project will improve sections and extend the life of South L Street in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-25 | 2009-11-10 | 637193.83 | 1.520
4751 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901183 | This proejct will extend the life of the bridge by doing bridge maintenance and repair on the deck on Keystone Avenue bridge over Fall Creek in Marion county. | Bridge Improvement | 2010-02-22 | 2010-04-05 | 2010-07-31 | 2010-07-31 | 647694.28 | 0.100
4752 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK |  | 05 | 0901188 | This is a Bridge Rehabilitation (no added capacity) project, at I 70 - 5.75 mi W of SR 9; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2009-10-09 | 2010-05-25 | 2010-08-13 | 2010-08-09 | 407780 | 0.196
4753 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0901198 | This is a Maintenance Resurfacing project, at 300 N from CR 100 W to White River; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-03-25 | 2010-06-15 | 2010-06-03 | 205666.14 | 3.220
4754 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0901200 | This is a Maintenance Resurfacing project, at Deputy Pike from SR 7 to SR 3; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-01 | 2010-07-31 | 2010-08-20 | 937456 | 13.100
4755 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901201 | This project will replace existing sidewalks and place new sidewalks in St. Joe, Indiana . | Safety/Traffic Management | 2009-09-15 | 2009-10-26 | 2010-05-27 | 2010-04-27 | 105294.2 | 0.360
4756 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901203 | This project will improve sections and extend the life of Dekalb County Road 35 with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-06 | 2010-10-31 | 2010-06-07 | 143137.9 | 5.300
4757 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CLAY |  | 08 | 0901208 | This is a Maintenance Resurfacing project, at I-70 - From Center Point to Harmony; to perform Partial 3-R work. | Pavement Improvement | 2009-12-16 | 2010-03-18 | 2010-06-30 | 2010-05-27 | 823382.98 | 8.000
4758 | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901209 | This project will resurface the County Road 350N between Morehouse Road And West Lafayette City Limits in Tippecanoe County. | Pavement Improvement | 2010-04-10 | 2010-06-21 | 2010-06-30 | 2010-06-28 | 83384.14 | 0.260
4759 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901210 | This is a Maintenance Resurfacing project, at Mooresville Rd from Raceway Rd to West Newton; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-05 | 2010-08-09 | 2010-07-06 | 829554.42 | 2.400
4760 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901211 | This is a Maintenance Resurfacing project, at Mooresville Rd from Southport Rd to High School Rd.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-05 | 2010-08-09 | 2010-07-06 | 273333.59 | 0.040
4761 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0901212 | This is a Maintenance Resurfacing project, at SR 29 - Burlington Avenue from Clinton Street to Cliff Dr.; to perform Surface Treatment work. | Pavement Improvement | 2010-02-23 | 2010-03-15 | 2010-06-02 | 2010-06-10 | 362696.44 | 0.940
4762 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0901213 | This is a Maintenance Resurfacing project, at Main Street from Coles Street to US24/35; to perform Surface Treatment work. | Pavement Improvement | 2010-02-23 | 2010-03-15 | 2010-06-02 | 2010-06-10 | 204812.92 | 1.600
4763 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901216 | This is a Maintenance Resurfacing project, at Woodyard Rd from Curry Pike to Vernal Pike; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-24 | 2010-04-06 | 2010-07-30 | 2010-07-29 | 101414.43 | 1.310
4764 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901218 | This is a Maintenance Resurfacing project, at Old SR 37 South, from Rogers St to Rhorer Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-24 | 2010-04-06 | 2010-07-30 | 2010-07-29 | 232525.9 | 1.670
4765 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901220 | This is a Maintenance Resurfacing project, at That Road, from SR 37 to Rogers St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-24 | 2010-04-06 | 2010-07-30 | 2010-07-29 | 163852.75 | 1.360
4766 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 05 | 0901224 | This is a Maintenance Resurfacing project, at Southport Rd. from Sherman Dr. to Gray Rd.; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-03-03 | 2010-08-16 | 2010-09-22 | 286848.1 | 0.400
4767 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901227 | This is a Maintenance Resurfacing project, from 0.15 miles W of SR 19 to 0.1 miles W of SR 13; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-03-24 | 2010-03-26 | 2010-10-01 | 2010-10-13 | 7934392.25 | 19.630
4768 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901228 | This is a Maintenance Resurfacing project, at Lynhurst Dr from Kentucky Ave to I-70; to perform Partial 3-R work. | Pavement Improvement | 2009-12-31 | 2010-04-12 | 2010-08-16 | 2010-07-12 | 211864.21 | 1.200
4769 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901229 | This is a preventive maintenance resurfacing project, at Mendenhall Rd from Camby Rd to SR 67 in Marion county to extend the service life of the pavement. | Pavement Improvement | 2009-11-23 | 2010-04-05 | 2010-08-09 | 2010-07-06 | 338289.39 | 1.200
4770 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901230 | This is a Maintenance Resurfacing project, at Meridian St. from Thompson Rd. to I-465; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-03-03 | 2010-08-16 | 2010-09-22 | 599699.62 | 0.600
4771 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901231 | This is a Maintenance Resurfacing project, at 38th St from German Church Rd to Carroll Rd.; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-05-11 | 2010-06-30 | 2010-09-10 | 237451.28 | 1.000
4772 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901233 | This is a Maintenance Resurfacing project, at Arlington Ave. from Shelbyville Rd.; to Thompson Rd. to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-03-03 | 2010-08-16 | 2010-09-22 | 618488.12 | 1.300
4773 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901234 | This is a Maintenance Resurfacing project, at Carroll Rd from 46th St to 56th St.; to perform Partial 3-R work. | Pavement Improvement | 2010-03-05 | 2010-06-01 | 2010-06-30 | 2010-06-25 | 310676.88 | 1.000
4774 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901235 | This is a Maintenance Resurfacing project, at 116th St from 0.35 mi E. of Eller Rd to 2.4 mi W of I-69; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-05-13 | 2010-07-31 | 2010-08-30 | 157808.07 | 0.020
4775 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901236 | This is a Maintenance Resurfacing project, at Towne Rd from 96th St to 116th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-29 | 2010-07-31 | 2010-08-17 | 140876.94 | 2.050
4776 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901237 | This is a Maintenance Resurfacing project, at 146th St from Ditch Rd to Springmill Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-05-14 | 2010-06-11 | 2010-06-16 | 113419.92 | 0.980
4777 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901238 | This is a Maintenance Resurfacing project, at Cumberland Rd from 96th St to 106th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-29 | 2010-07-31 | 2010-08-17 | 86502.98 | 1.020
4778 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901239 | This is a preventive maintenance resurfacing project, at Olio Rd from the bridge over Geist Reservoir to 126th St. in Hamilotn county to extendthe service life of the pavement. | Pavement Improvement | 2009-12-16 | 2010-05-13 | 2010-07-31 | 2010-08-30 | 393619.79 | 1.020
4779 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 0901240 | This is a Maintenance Resurfacing project, at CR 600W from CR 500N to CR 650N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-08-13 | 2010-10-01 | 2010-09-10 | 215724.58 | 1.470
4780 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 0901241 | This is a Maintenance Resurfacing project, at CR 300N from CR 700W to CR 800W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-08-13 | 2010-10-01 | 2010-09-10 | 89072.4 | 1.000
4781 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901242 | This is a Safety project, at SR 51 - SR 51(Lincoln St) at 10th St (SR 51); to perform Traffic Signals, New Or Modernized work. | Safety/Traffic Management | 2010-01-05 | 2010-02-01 | 2010-05-31 | 2010-03-18 | 76509.8 | 0.010
4782 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901243 | This is a Maintenance Resurfacing project, at County Highway 1100 W - CR-475S from Lagrange County line to CR-500S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 154670.93 | 0.800
4783 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901244 | This is a Maintenance Resurfacing project, at CR 500 S from CR 475 S to SR 327; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 61689.4 | 0.700
4784 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901245 | This is a Maintenance Resurfacing project, at N SR 327 - CR 500 N from SR-327 to CR 900 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 45702.26 | 0.500
4785 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901246 | This is a Maintenance Resurfacing project, at CR 900 W from CR 500 N to Orland Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 13826.59 | 0.100
4786 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901247 | This is a Maintenance Resurfacing project, at Orland Road from CR 900 W to CR 800 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 101475.56 | 1.000
4787 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901248 | This is a Maintenance Resurfacing project, at CR 800 W from Orland Rd (N Junction) to Orland Rd.; (S Junction) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 12872.56 | 0.100
4788 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901249 | This is a Maintenance Resurfacing project, at Orland Rd from CR 800 W to CR 675 N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 160441.5 | 1.400
4789 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901250 | This is a Maintenance Resurfacing project, at Kimble Rd from CR 550 W to Orland Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 27577.22 | 0.350
4790 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901252 | This is a Maintenance Resurfacing project, at Fox Lake Rd from Menges Rd to CR 200 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 259152.5 | 2.100
4791 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901253 | This is a Maintenance Resurfacing project, at CR 200 W from Fox Lake Rd to US 20; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 6615.8 | 0.300
4792 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901254 | This is a Maintenance Resurfacing project, at Menges Rd from Waymire Rd to Fox Lake Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 55508.97 | 0.700
4793 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901255 | This is a Maintenance Resurfacing project, at Waymire Rd from Menges Rd to CR 150W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 117311.16 | 1.300
4794 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901256 | This is a Maintenance Resurfacing project, at E SR 120 - Van Guilder Road from SR-120; to North Baker St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 139414.16 | 1.600
4795 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901271 | This is a Maintenance Restoration & Rehabilitation project, at N Charles Ave from W Water Street to SR 67; to perform Pavement, Other work. | Pavement Improvement | 2009-12-04 | 2010-09-14 | 2010-06-25 | 2010-09-17 | 56993.52 | 0.500
4796 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901272 | This is a Maintenance Resurfacing project, at Lincoln Street from N Franklin Street to US 27 (Meridian Street); to perform Pavement, Other work. | Pavement Improvement | 2009-11-23 | 2010-10-14 | 2010-06-25 | 2010-10-14 | 22926.5 | 0.170
4797 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | Multiple | 0901278 | This is a Maintenance Resurfacing project, at Whiteland Rd from CR 75W to the New Whiteland City limits; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-04-13 | 2010-05-14 | 2010-05-14 | 94201.01 | 0.770
4798 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | Multiple | 0901279 | This is a Maintenance Resurfacing project, at Smokey Row Rd from CR 500W to SR 135; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-04-13 | 2010-05-14 | 2010-05-14 | 208365.43 | 2.000
4799 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | Multiple | 0901280 | This is a Maintenance Resurfacing project, at Stones Crossing Rd from CR 500W to CR 600W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-04-13 | 2010-05-14 | 2010-05-14 | 96502.04 | 1.030
4800 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0901281 | This is a trail project for pedestrians and bicycles on the Rivertown Trail Phase IIA at Old Lock and Dam to Belle Rive Drive in Newburgh in Warrick county using enhancement funds | Transportation Enhancements | 2010-03-08 | 2010-03-15 | 2010-10-01 | 2010-11-29 | 870394.97 | 0.010
4801 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901283 | This is a Facilities for Pedestrians and Bicycles project, at 106th St from Penns Pkwy to Rangeline Rd/ College Ave fr I-465 to 105th St.; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-01 | 2010-07-16 | 2010-08-31 | 2010-10-05 | 219450 | 2.180
4802 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901284 | This is a Maintenance Resurfacing project, at Country Club Rd from Country Club Dr S to Hackleman St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-08-01 | 2010-03-22 | 144895.43 | 0.990
4803 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901285 | This is a Maintenance Resurfacing project, at Harrison St from Sheridan St to Dubois Dr.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-08-01 | 2010-03-22 | 49582.91 | 0.320
4804 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901286 | This is a Maintenance Resurfacing project, at Winona Ave from 200' E of Bronson St to McKinley St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-08-01 | 2010-03-22 | 110450.99 | 0.720
4805 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901287 | This is a Maintenance Resurfacing project, at Rozella Rd from Brookview Ave to SR 15; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-08-01 | 2010-03-22 | 53202.99 | 0.600
4806 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901288 | This is a Facilities for Pedestrians and Bicycles project, at Along 146th St from Cherry Tree Rd to River Rd.; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-01 | 2010-05-26 | 2010-06-30 | 2010-07-09 | 139680.25 | 1.290
4807 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901289 | This is a Maintenance Resurfacing project, at 234th St from the Cicero Corp limits to Overdorf Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-07-30 | 2010-08-17 | 231896.38 | 1.780
4808 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901290 | This is a Maintenance Resurfacing project, at Olio Rd from 126th St to 136th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-05-12 | 2010-06-30 | 2010-08-20 | 274126.63 | 1.000
4809 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901299 | This is a Maintenance Resurfacing project, at Carroll Road from US 33 to Hand Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 298987.49 | 4.350
4810 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901300 | This is a Maintenance Resurfacing project, at Ferguson Rd from Bluffton Road to Winchester Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 138670.29 | 1.880
4811 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901301 | This is a Maintenance Resurfacing project, at Yellow River Road from Hadley Road to O'Day Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 53412.55 | 0.620
4812 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901302 | This is a Maintenance Resurfacing project, at O'Day Road from Yellow River Road to US 33; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 494136.36 | 4.810
4813 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901303 | This is a Maintenance Resurfacing project, at Dawkins Road from Doyle Road to Main Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 1075781.91 | 9.070
4814 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901313 | This project will extedn the life of the road by performing perventive maiantenance resurfacing on Albany St from Miller St to CR 50S in Delaware county. | Pavement Improvement | 2010-03-11 | 2010-07-28 | 2010-08-15 | 2010-10-04 | 52485.11 | 0.250
4815 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901314 | This project will resurface the County Road 600W from SR 332 to Lone Beech Bridge in Delaware County. | Pavement Improvement | 2010-04-13 | 2010-05-14 | 2010-07-30 | 2010-07-01 | 322440.58 | 0.100
4816 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901315 | This is a Maintenance Resurfacing project, at Old SR 67 (Fuson Rd) from SR 67 to Cowan Rd; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-06-29 | 2010-08-15 | 2010-07-19 | 413942.07 | 1.800
4817 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901316 | This is a Maintenance Resurfacing project, at Hart Street from 81st Street N to US 30; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-19 | 2010-05-31 | 2010-06-01 | 579254.81 | 2.100
4818 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901317 | This is a Maintenance Resurfacing project, at Calumet Avenue from US 30 N to intersection of Main Street; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-19 | 2010-05-31 | 2010-06-01 | 17629.06 | 2.030
4819 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0901323 | This project will improve sections and extend the life of County Road 900North from SR 9 to county road 600 east in Huntington County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-29 | 2010-06-12 | 2010-05-04 | 564063.47 | 7.140
4820 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0901324 | This project will improve sections and extend the life of County Road 300West from county road 1200 south to county road 300 south in Huntington County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-29 | 2010-06-12 | 2010-05-04 | 680700.92 | 9.010
4821 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0901325 | This project will improve sections and extend the life of County Road 800North from county road 1000 west to SR 9 in Huntington County with a pavement surface overlay. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-06-12 | 2010-03-24 | 653172 | 9.040
4822 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901336 | This is a Maintenance Resurfacing project, at Kern Road from York Road to Ironwood Road to; perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-02-22 | 2010-10-15 | 2010-10-30 | 2010-10-23 | 95116.89 | 0.500
4823 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901337 | This is a Maintenance Resurfacing project, at Fir Road from Day Road to Brick Road (exluding intersections); to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 195575.51 | 2.700
4824 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901338 | This is a Maintenance Resurfacing project, at Miami Road from Roosevelt Road to 0.7 miles south of Orchard Heights Drive; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 52748.56 | 0.600
4825 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901339 | This is a Maintenance Resurfacing project, at Adams Road from Ironwood Road to Gumwood Road ;to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-03-01 | 2010-08-23 | 2010-10-30 | 2010-10-30 | 223239.69 | 2.000
4826 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901340 | This is a Maintenance Resurfacing project, at Ironwood Road from Auten Road to State Line Road; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-05-20 | 2010-08-15 | 2010-06-30 | 114258.82 | 1.000
4827 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901341 | This is a Maintenance Resurfacing project, at Portage Road from 0.4 miles north of Bendix Drive to IN/MI State Line; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 259988.33 | 1.600
4828 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901342 | This is a Maintenance Resurfacing project, at Ireland Road from SR 23 to Locust Road; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 153261.06 | 2.000
4829 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901343 | This is a Maintenance Resurfacing project, at Brick Road from Gumwood Road to Fir Road; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-06-15 | 2010-10-30 | 2010-07-14 | 116373.37 | 1.000
4830 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901344 | This is a Maintenance Resurfacing project, at Ash Road from SR 933 to Elsie Avenue; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 199887.4 | 1.400
4831 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901345 | This is a Maintenance Resurfacing project, at Ironwood Road from Douglas Road to indiana Toll Road; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 84988.69 | 0.500
4832 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901346 | This is a Maintenance Resurfacing project, at Mayflower Road from the UAB, 0.3 miles north of Sumption Trail, to SR 23; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 33113.49 | 0.500
4833 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901347 | This is a Maintenance Resurfacing project, at Locust Road from Madison Road to Jackson Road to; perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 262227.2 | 2.900
4834 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901348 | This is a Maintenance Resurfacing project, at I-80 - Juniper Road from 0.3 miles north of Douglas Rd. to Cleveland Road; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 64125.26 | 0.700
4835 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901351 | This is a Maintenance Resurfacing project, at Beech Road from 0.5 miles S of Harrison road to .07 miles S of Adams St.; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 78529.76 | 0.500
4836 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901352 | This is a Maintenance Resurfacing project, at Grant Road from US 20/US31 By-Pass to Mayflower Road; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 60090.72 | 0.800
4837 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901353 | This is a Safety project, at County wide (urban areas only) sign replacement; to perform Safety Revisions work. | Safety/Traffic Management | 2009-12-16 | 2010-02-12 | 2010-07-31 | 2010-04-27 | 171299.73 | 0.010
4838 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901354 | This project will improve roadway safety in the town of Osceola. | Safety/Traffic Management | 2009-12-16 | 2010-02-12 | 2010-07-31 | 2010-04-27 | 36517.01 | 0.010
4839 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901355 | This is a Maintenance Resurfacing project, at Edison Road from Quince Road to Sundown Road; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 209393.94 | 2.100
4840 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901356 | This is a Maintenance Resurfacing project, at Township 23 North, Range 4 West; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-10 | 2010-06-30 | 2010-06-25 | 299624.65 | 1.570
4841 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901357 | This is a Maintenance Resurfacing project, at Beech Road from Ireland Road to 0.5 miles S of Harrison Road; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-03-01 | 2010-08-23 | 2010-10-30 | 2010-10-30 | 38853.12 | 1.000
4842 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901358 | This is a Maintenance Resurfacing project, at Beech Road from SR 933 to .07 miles south of Adams Street; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 36104.42 | 0.260
4843 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901362 | This is a Maintenance Resurfacing project, at CR 200 S from Blaine Pike to Boundry Pike; to perform Pavement, Other work. | Pavement Improvement | 2009-10-13 | 2010-05-18 | 2010-07-30 | 2010-08-09 | 218336.18 | 2.080
4844 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901365 | This is a Maintenance Resurfacing project, at CR 300 N from Pennville LIMITS TO US 27; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-07-30 | 2010-07-29 | 771313.38 | 9.132
4845 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901366 | This is a Maintenance Resurfacing project, at CR 400 S from CR 1150 W to SR 1; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-05-18 | 2010-07-30 | 2010-08-09 | 262370.35 | 2.470
4846 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901367 | This is a Maintenance Resurfacing project, at CR 1150 W from Dunkirk to CR 900 S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-07-13 | 2010-07-30 | 2010-08-05 | 341424.82 | 3.820
4847 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901374 | This is a Maintenance Restoration & Rehabilitation project, at West Water Street from Western City Limit to US 27 (Meridian Street); to perform Patch And Rehab Bituminous Pavement work. | Pavement Improvement | 2009-12-30 | 2010-10-11 | 2010-06-28 | 2011-05-20 | 139689.15 | 1.500
4848 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901375 | This is a Maintenance Restoration & Rehabilitation project, at W. High Street from N. Middle Street to US 27 (Meridian Street); to perform Patch And Rehab Bituminous Pavement work. | Pavement Improvement | 2009-12-30 | 2010-10-11 | 2010-06-28 | 2011-05-16 | 68967.54 | 0.370
4849 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901379 | This project will patch and restore and overlay North Wayne St from SR 26 to East Votaw Street in Portland, Jay county to extend the life of the pavement. | Pavement Improvement | 2009-12-30 | 2010-10-11 | 2010-06-25 | 2011-05-18 | 55408.38 | 0.490
4850 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901384 | This is a Maintenance Resurfacing project, at CR 800 E from Glenwood to CR 250 N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2009-11-04 | 2009-10-30 | 2009-11-11 | 126196.38 | 1.320
4851 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901386 | This is a Maintenance Resurfacing project, at CR 800 E from Orange Pike to Glenwood; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-03-17 | 2010-07-30 | 2010-04-29 | 231258.1 | 2.670
4852 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901388 | This is a Maintenance Resurfacing project, at Fort Wayne from E. 3rd St to E. 11th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-03-19 | 2010-06-25 | 2010-04-29 | 168332.25 | 0.900
4853 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901390 | This is a Maintenance Resurfacing project, at Conard-Harcourt Way from SR 3 to E. 11th Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-03-19 | 2010-06-25 | 2010-04-29 | 166626 | 0.840
4854 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901409 | This is a Maintenance Resurfacing project, at From 1.90 Miles West of SR 15 to SR 15; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-03-23 | 2010-07-12 | 2010-08-13 | 2010-08-13 | 369087.7 | 1.870
4855 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI, FULTON |  | Multiple | 0901410 | This is a Maintenance Resurfacing project, at SR 19 - From US 24 to 0.25 miles S of SR 14 (South limits of Akron); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-15 | 2010-04-05 | 2010-10-08 | 2010-10-04 | 2051607.86 | 18.900
4856 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE, ELKHART | ELKHART-GOSHEN | Multiple | 0901411 | This is a Maintenance Resurfacing project, at From jct. US 33/SR 13 to 0.17 miles E of SR 5; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-03-23 | 2010-04-12 | 2010-07-31 | 2010-06-24 | 926767.38 | 5.470
4857 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901416 | This is a Safety project, at Edwardsville-Galena Rd from Old Vincennes Rd to Country Trace Lane; to perform Pavement Markings work. | Safety/Traffic Management | 2010-02-22 | 2010-04-16 | 2010-05-15 | 2010-08-06 | 67033.9 | 0.380
4858 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901418 | This is a Safety project, at Old Vincennes Rd from Partridge Place to Pebble Creek Dr; to perform Pavement Markings work. | Safety/Traffic Management | 2010-02-22 | 2010-04-16 | 2010-05-15 | 2010-08-06 | 37535.3 | 0.840
4859 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0901428 | This is a Facilities for Pedestrians and Bicycles project, at Former Erie RR right of way between North Judson and Town of Ora in Starke Co; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-01 | 2010-05-18 | 2011-10-15 | 2010-12-21 | 1028182.99 | 6.250
4860 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901439 | This is a Maintenance Resurfacing project, at Between CR 800 S & US 52; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-05 | 2010-03-18 | 2010-06-30 | 2010-04-26 | 141907.03 | 0.683
4861 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901441 | This is a Maintenance Resurfacing project, at Between CR 510 S & CR 430 S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-04-21 | 2010-05-29 | 2010-05-28 | 194622.29 | 0.867
4862 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901449 | This is a Maintenance Resurfacing project, at Main St from Ensley Ave to North St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-23 | 2010-04-12 | 2010-08-15 | 2010-11-01 | 457970.85 | 0.950
4863 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0901455 | This is a Facilities for Pedestrians and Bicycles project, at Covington Circle Trail - Ph II; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-24 | 2010-03-23 | 2010-07-10 | 2010-07-10 | 718659 | 3.100
4864 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901458 | This is a Maintenance Resurfacing project, at From Union Township line to Old US 231; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-04-21 | 2010-05-29 | 2010-05-28 | 137332.84 | 1.020
4865 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | PULASKI |  | 02 | 0901465 | This is a trail project on an abandoned RR right of way for pedestrians and bicycles at rail banked corridor along US 35 between Star City and north of Royal Center in Cass/Pulaski Co's using enhancem | Transportation Enhancements | 2009-12-31 | 2010-03-16 | 2010-11-19 | 2010-12-03 | 2263793 | 15.690
4866 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901466 | This is a Maintenance Resurfacing project, at Beverly Drive from Eaton Avenue to US 12 (Mt. Baldy); to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-06-01 | 2010-04-21 | 271350.65 | 3.730
4867 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901468 | This is a preventive maintenance resurfacing project, on North "D" Street from 1st to 10th Streetin Gas City, Grant county to extend the service llife of the pavement. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 222928.14 | 1.010
4868 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901469 | This is a Maintenance Resurfacing project, at 5th Street from South "H" Street to North "D" Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 148395.63 | 0.780
4869 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901470 | This is a Maintenance Resurfacing project, at South "D" Street from 1st to 3rd Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 65330.73 | 0.210
4870 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901471 | This is a preventive maintenance resurfacing project, at 3rd Street from South "H" Street to SR 22 in Gas City, Grant county. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 151437 | 0.510
4871 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901472 | This is a Maintenance Resurfacing project, at 7th Street from SR 22 to North "D" Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 56267.52 | 0.250
4872 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901473 | This is a trail project for pedestrians and bicycles on the over 6500 feet of side walks on Ralph Sechler Dr., Spencer St, School St, Hart St and other streets in the town of St Joe, and is Phase 3 of | Transportation Enhancements | 2010-01-06 | 2010-03-01 | 2010-08-15 | 2010-07-26 | 313344.36 | 0.360
4873 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901480 | This is a Facilities for Pedestrians and Bicycles project, at New York Street from 9th St to 12th Street in Elkhart, Elkart county. This 1 of 3 projects top provide pedestrian facilities under contrac | Transportation Enhancements | 2009-11-30 | 2010-04-26 | 2010-06-19 | 2010-06-18 | 42812.57 | 0.230
4874 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901481 | This is a Facilities for Pedestrians and Bicycles project, at 11th St from New York Ave to East Burdick St in Elkhart, Elkhart county. This 1 of 3 projects to provide pedestrian facilites under contra | Transportation Enhancements | 2009-11-30 | 2010-04-26 | 2010-06-19 | 2010-06-18 | 37792.17 | 0.140
4875 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901482 | This is a preventive maintenance resurfacing project, at Piqua Rd from East of Monroe St to CR 700E (State Line) in Adams county; to perform asphalt resurface, Preventive Maintenance work. This 1 of | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 601726.9 | 7.070
4876 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901483 | This is a pavement preventive maintenance resurfacing project, at CR 1200 S from CR 500 E to CR 700 E (State Line) in Adams county to perform Chip Seal work that will extend the life of the road. This | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 38757.27 | 1.930
4877 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901484 | This is a preventive maintenance resurfacing project, at CR 100 E (High St ) from north of US 33 to north of abandoned RR (City Limits) in Adams county to perform asphalt resurface to extend the lif | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 91269.42 | 1.040
4878 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901485 | This is a preventive maintenance resurfacing project, at CR 500 E (Old SR 116) from CR 1200 South to CR 1100 South to perform Chip Seal work to extend the life of the pavement. This 1 of 5 proejcts | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 21498.24 | 1.050
4879 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901486 | This is a preventive maintenance resurfacing project, on County Road 1050/1100 from south of Hale St (Town Limits) to County Road 500East in Adams county to perform, Chip Seal work to extend the life | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 125902.38 | 6.200
4880 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901487 | This is a Maintenance Resurfacing project,at Centerville Rd from 900 feet S of Temple Dr,N 3.38 miles to the S ramp to I-70 ;to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-18 | 2010-03-25 | 2010-06-11 | 2010-06-11 | 1011110.45 | 3.410
4881 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901494 | This is a Maintenance Resurfacing project, at Quincy Street from N. Peters St to N. 2nd St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-18 | 2010-06-30 | 2010-08-18 | 171935.7 | 0.700
4882 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901495 | This project will extend the pavement life with a preventive maintenance resurfacing project on South Rd from N. 2nd St to 0.1 mile E of Taylor Rd. in Garrett, Dekalb county. | Pavement Improvement | 2010-04-01 | 2010-05-18 | 2010-06-30 | 2010-08-18 | 74456 | 0.560
4883 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901496 | This is a Maintenance Resurfacing project, at Woodburn Road from Hetrick Road to State Road 101 (Main St.) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-09-22 | 2010-10-30 | 2010-11-01 | 157574.85 | 0.500
4884 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901497 | This is a Maintenance Resurfacing project, at Woodburn Road from State Road 101 (Fahlsing Rd.) to Brobst Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-09-22 | 2010-10-30 | 2010-11-01 | 56120.75 | 0.500
4885 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901498 | This is a Maintenance Resurfacing project, at Bull Rapids Rd from SR 101 (Main St.) to 0.33 mile N of Ash St (City limits) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-09-22 | 2010-10-30 | 2010-11-01 | 100975.18 | 0.700
4886 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 0901502 | This is a Maintenance Resurfacing project, at CR 300 N from CR 300 W to CR 200 W, 0.50 miles N of I-70; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-08-23 | 2010-10-01 | 2010-09-30 | 94439.29 | 1.000
4887 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 0901503 | This is a Maintenance Resurfacing project, at CR 300 N from CR 400 W to CR 300 W, 0.5 miles N of I-70; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-08-23 | 2010-10-01 | 2010-09-30 | 92327.76 | 1.000
4888 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | MICHIGAN CITY | 02 | 0901505 | This is a Preventive Maintenance Resurfacing project, at Coolspring Avenue from Roeske Avenue (Michigan City Corp Limit) to Johnson Road in Laprot county to extend the life of the pavement.. | Pavement Improvement | 2010-02-24 | 2010-04-15 | 2010-07-01 | 2010-06-29 | 329390.4 | 0.600
4889 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0901506 | This is a Maintenance Resurfacing project, at S. Walnut St from Wylie to Country Club to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-12 | 2010-06-26 | 2010-06-18 | 707045.75 | 1.690
4890 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901517 | This is a Maintenance Resurfacing project, at Pendleton Ave from High St to Reformatory Rd; to perform Surface Treatment work. | Pavement Improvement | 2009-12-31 | 2010-06-01 | 2010-07-30 | 2010-07-23 | 142600 | 0.760
4891 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901518 | This is a Maintenance Resurfacing project, at Harrison St from 3rd St to Norfolk Southern RR crossing; to perform Surface Treatment work. | Pavement Improvement | 2010-01-06 | 2010-08-19 | 2010-06-30 | 2010-09-02 | 200150 | 0.920
4892 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901519 | This is a Maintenance Resurfacing project, at CR 50 W from SR 38 to Anderson C L; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 281629.13 | 4.100
4893 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901521 | This is a Maintenance Resurfacing project, at CR 100 W from SR 128 to CR 1100 N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 221297.08 | 3.100
4894 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901522 | This is a Maintenance Resurfacing project, at CR 1100 N from SR 9 to CR 100 E; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 56177.6 | 1.100
4895 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901523 | This is a Maintenance Resurfacing project, at CR 1100 N from CR 200 W to CR 100 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 83358 | 1.100
4896 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901524 | This is a Maintenance Resurfacing project, at New Columbus Ave from CR 600S to CR 400S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 169100.19 | 2.100
4897 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901529 | This is a Maintenance Resurfacing project, at Cumberland Rd from Field Dr to Allisonville Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-25 | 2010-06-30 | 2010-08-18 | 116794.02 | 0.970
4898 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901530 | This is a Maintenance Resurfacing project, at Boden Rd between SR 38 and Greenfield Ave to; perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-06 | 2010-07-31 | 2010-07-14 | 113029.07 | 2.080
4899 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901531 | This is a Maintenance Resurfacing project, at Little Chicago Rd between SR 38 and Carrigan Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-08 | 2010-07-31 | 2010-07-16 | 159921.82 | 1.650
4900 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901533 | This is a Maintenance Resurfacing project, at Diamond St from Main St to Sherman St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 234868.67 | 0.610
4901 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901535 | This is a Maintenance Resurfacing project, at Mitchell St from Weston Ave to Orchard St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 106251.51 | 0.470
4902 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901538 | This is a Maintenance Resurfacing project, at Iddings St from Main St to Town St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 42310.1 | 0.280
4903 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901540 | This is a Maintenance Resurfacing project, at Business SR 37 from Old SR 37 North; to SR 37 to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-05-07 | 2010-07-30 | 2010-07-23 | 199088.36 | 1.764
4904 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901542 | This is a Maintenance Resurfacing project, at Fair St from Wayne St to US 6; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 69979.72 | 0.280
4905 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901547 | This is a Maintenance Resurfacing project, at Old SR 62 - Brown Station Way from Randolph Avenue to Silver Creek; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-30 | 2010-06-30 | 2010-06-28 | 617504.42 | 1.800
4906 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901551 | This is a Maintenance Resurfacing project, at Main St from High St to US 6 to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 9602.4 | 0.070
4907 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901552 | This is a Maintenance Resurfacing project, at Hartzell Rd from RR tracks (approx. 1600' south of Rose Ave) to Rose Ave; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 37464.34 | 0.300
4908 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901553 | This is a Maintenance Resurfacing project, at Rose Ave; from Green St. to Linden Rd to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 54110.65 | 0.610
4909 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901554 | This is a Maintenance Resurfacing project, at Landin Rd from N River Rd to Maysville Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 272728.08 | 1.890
4910 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901555 | This is a Maintenance Resurfacing project, at New Haven Ave from Meyer Rd to SR 930; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 90325.99 | 0.730
4911 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901556 | This is a Maintenance Resurfacing project, at Rose Ave from Hartzell Rd to Landin Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 52047.51 | 0.580
4912 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901557 | This is a preventive maintenance resurfacing project on Minnich Rd from Seiler Rd to SR 930 in Fort wayne , Allen county to extend the service life of the road. | Pavement Improvement | 2009-11-23 | 2010-05-15 | 2010-06-26 | 2010-08-18 | 167092.1 | 1.150
4913 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901558 | This is a Maintenance Resurfacing project, at Summit St from Bensman Ave to Linden Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 55587.48 | 0.480
4914 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901559 | This is a Maintenance Resurfacing project, at Lincoln Hwy from 365' E of Green St; to City Limits (1320' W of Doyle St) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 121119.5 | 1.100
4915 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS | INDIANAPOLIS | 04 | 0901561 | This project will resurface the County Road 100N from Richfield Drive to Kinross Drive in Hendricks County. | Pavement Improvement | 2010-04-10 | 2010-05-05 | 2010-07-30 | 2010-05-27 | 215983.5 | 1.500
4916 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901563 | This project is a preventive maintenance resurfacing project, on Old US Hwy 231 - From County Road 500 South to County Road 350 South in Tippecanoe county to extend the life of the pavement. | Pavement Improvement | 2009-12-16 | 2010-04-21 | 2010-05-29 | 2010-05-28 | 238671.89 | 1.443
4917 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901571 | This is a Maintenance Resurfacing project, at 45th Street from State Line east to Highland Line; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-04-06 | 2010-06-01 | 2010-06-03 | 559573.26 | 2.400
4918 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0901600 | This is a Maintenance Resurfacing project, at Schultz Road from CR 600W to CR 400W; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2009-11-24 | 2009-12-01 | 2009-12-17 | 287065.77 | 2.120
4919 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | MICHIGAN CITY | 02 | 0901619 | This proejct replaces and repairs storm sewers, at Michigan Blvd from US 12 to Carroll Avenue in Michigan City, LaPorte county to correct and improve drainage of the road. | Other | 2010-05-05 | 2010-06-18 | 2010-09-01 | 2010-08-18 | 1735143.59 | 1.860
4920 | Completed | C250,C240 | Highway Infrastructure Investment Grant | INDIANA | CRAWFORD |  | 09 | 0901627 | This is a Maintenance Resurfacing project, at SR 164 to SR 56; to perform Surface Treatment, Ultrathin Bonded Wearing Course work. | Pavement Improvement | 2010-04-09 | 2010-06-07 | 2010-07-31 | 2010-07-16 | 1838564.73 | 13.670
4921 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901628 | This is a Maintenance Resurfacing project, at From US 52 to SR 38; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-05 | 2010-03-19 | 2010-06-30 | 2010-05-13 | 243723.82 | 0.696
4922 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901629 | This is a Maintenance Resurfacing project, at Between SR 26 and US 52; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-20 | 2010-07-31 | 2010-08-20 | 1359216 | 1.620
4923 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901631 | This is a Maintenance Resurfacing project, at Aboite Center Rd from West Hamilton Rd to Homestead Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 117466.77 | 1.260
4924 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901632 | This is a Maintenance Resurfacing project, at Bass Road from W Co Ln Road to Scott Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 237786.43 | 3.260
4925 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901633 | This is a preventive maintenance resurfacing project on Covington Road from West County Line Road to Braemar Drivein Allen county to extend the service life of the pavement. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 227247.28 | 1.870
4926 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901634 | This is a Maintenance Resurfacing project, at West Hamilton Road frm US 24 to Bass Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 570440.24 | 5.630
4927 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901635 | This is a Maintenance Resurfacing project, at Leesburg Road from Kroemer Road to Beineke Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 69613.18 | 1.020
4928 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901636 | This project will improve the traffic signs in the town of Indian Village. | Safety/Traffic Management | 2009-12-16 | 2010-02-12 | 2010-07-31 | 2010-04-27 | 3169.67 | 0.010
4929 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901637 | This project will improve the traffic signs in the town of Roseland. | Safety/Traffic Management | 2009-12-16 | 2010-02-12 | 2010-07-31 | 2010-04-27 | 23814.19 | 0.010
4930 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901648 | This is a Maintenance Resurfacing project, at US 36 - From Pendleton Pike to 79th St; to perform Pavement, Other work. | Pavement Improvement | 2010-04-01 | 2010-07-06 | 2010-08-13 | 2010-07-30 | 268699.99 | 2.320
4931 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901649 | This is a Maintenance Resurfacing project, at Carroll Rd. from 75th St. to 79th St.; to perform Pavement, Other work. | Pavement Improvement | 2010-01-13 | 2010-05-07 | 2010-07-10 | 2010-07-12 | 199647.76 | 0.500
4932 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN | CINCINNATI | 09 | 0901652 | This is a Maintenance Resurfacing project, at Nowlin Avenue from Rand Aven. to Meadowcreek Drive; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-02 | 2010-06-25 | 2010-06-04 | 139653.6 | 0.010
4933 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS |  | 04 | 0901655 | This is a Facilities for Pedestrians and Bicycles project, at From SR 267 to CR 300 N and from Ronald Reagan Pkwy; to Raceway Rd to perform Enhancement work. | Transportation Enhancements | 2010-04-13 | 2010-04-26 | 2010-11-15 | 2011-06-14 | 3334104.27 | 0.010
4934 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901656 | This is a Maintenance Resurfacing project, at Liverpool Road from New Jersey Street to Deep River; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-19 | 2010-05-10 | 2010-09-15 | 2010-10-05 | 464343.79 | 0.230
4935 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI, FULTON |  | Multiple | 0901663 | This project will build a trail for pedestrians and bicycles on Nickel Plate Trail: from Lovers Lane north of Peru im Miami county to Wabash Road in Rochester in Fulton County. | Transportation Enhancements | 2010-02-22 | 2010-03-19 | 2010-10-15 | 2010-12-08 | 4413712.7 | 17.000
4936 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0901685 | This project builds new sidewalks in 17 locations in Bloomington, Monroe county using enhancement funds. | Other | 2010-02-22 | 2010-03-15 | 2010-05-14 | 2010-04-30 | 293006.58 | 1.200
4937 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0901686 | This is a Landscaping project, at Madison Riverfront Dev-Phase 2: Bankstab, Scenic, Docking; to perform Landscaping work. | Transportation Enhancements | 2010-02-18 | 2010-03-16 | 2010-12-15 | 2011-05-17 | 915468.75 | 0.010
4938 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | ELKHART |  | 03 | 0901687 | This is a trail project for pedestrians and bicycles project on the Pumpkinvine Trail and is Phase 5C located from 1300' south of CR 22 to US 20 in Elkhart county using enhancement funds. | Transportation Enhancements | 2010-03-04 | 2010-03-31 | 2010-08-20 | 2011-06-08 | 1088731.18 | 0.040
4939 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901689 | This is a Maintenance Resurfacing project, at 34th St from Arlington Avenue to Shadeland Avenue; to perform Partial 3-R work. | Pavement Improvement | 2010-04-07 | 2010-05-21 | 2010-10-31 | 2010-10-04 | 408277.59 | 1.000
4940 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 05 | 0901690 | This is a Maintenance Resurfacing project, at Davis Rd from Vandergriff Rd to Troy Ave; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-07-16 | 2010-11-01 | 2010-10-29 | 191427.53 | 0.700
4941 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901691 | This is a Maintenance Resurfacing project, at Edgewood Ave from Shelbyville Rd to Five Points Rd; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-07-16 | 2010-11-01 | 2010-10-29 | 583175.71 | 1.300
4942 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901692 | This is a Maintenance Resurfacing project, at Five Points Rd from Shelbyville Rd to Southeastern Ave; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-07-16 | 2010-11-01 | 2010-10-29 | 547726.16 | 4.300
4943 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901693 | This proejct will place muliple lays of asphalt to increase strength and extend the life of the pavement on Harding St from Morris St to Oliver Ave in Marion county. | Pavement Improvement | 2010-04-07 | 2010-07-09 | 2010-08-02 | 2010-09-13 | 332158.38 | 0.500
4944 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901694 | This project rebuilds the pavement with multi-lays of asphalt on Lafayette Rd from 71st St to County Line Rd in Indianapolis, Marion county. | Pavement Improvement | 2010-04-10 | 2010-05-11 | 2010-09-11 | 2010-09-21 | 1930481.6 | 3.600
4945 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901695 | This is a Maintenance Resurfacing project, at Morris St from Lynhurst Dr to Westbrook Ave; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-06-25 | 2010-07-01 | 2010-09-07 | 210149 | 0.500
4946 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 05 | 0901697 | This is a Maintenance Resurfacing project, at Senour St from Thompson Rd to Troy Ave; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-07-16 | 2010-11-01 | 2010-10-29 | 242614.61 | 2.000
4947 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901712 | This is a Bridge Rehabilitation (no added capacity) project, at Mann Rd over Dollar Hide Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-05-17 | 2010-10-31 | 2010-09-29 | 276920.99 | 0.100
4948 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901713 | This is a Bridge Rehabilitation (no added capacity) project, at Emerson Avenue over Brookside Creek; to perform Bridge Rehabilitation Or Repair work. | Bridge Improvement | 2010-04-01 | 2010-05-17 | 2010-10-31 | 2010-09-29 | 264201.27 | 0.100
4949 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901714 | This is a Bridge Rehabilitation (no added capacity) project, at Country Club Rd over Cox Ditch; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-04-22 | 2010-10-31 | 2010-07-02 | 248146.66 | 0.100
4950 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901716 | This is a Bridge Rehabilitation (no added capacity) project, at Bridgeport Rd over White Lick Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-04-22 | 2010-10-31 | 2010-07-02 | 247883.69 | 0.100
4951 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901717 | This is a Bridge Rehabilitation (no added capacity) project, at Bridgeport Rd over Salem Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-04-22 | 2010-10-31 | 2010-07-02 | 152878.34 | 0.100
4952 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901718 | This is a Bridge Rehabilitation (no added capacity) project, at Bridgeport Rd over Shiloh Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-04-22 | 2010-10-31 | 2010-07-02 | 103559.57 | 0.100
4953 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901722 | This is a Maintenance Resurfacing project, at Liberty Mills Road frm W Co Ln Road to Amber Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 216179.98 | 1.790
4954 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901723 | This is a Maintenance Resurfacing project, at Muldoon Road frm Ferguson Road to Winchester Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 99462.66 | 1.320
4955 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901724 | This is a Maintenance Resurfacing project, at Smith Road from Airport Expressway to 120 feet N of Knoll Road (N&S Railroad); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 182986.38 | 2.410
4956 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901725 | This is a Maintenance Resurfacing project, at Wallen Road frm Huguenard Road to Hanauer Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 64261.09 | 0.930
4957 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901726 | This is a Maintenance Resurfacing project, at Washington Center Road frm O'Day Road to Kroemer Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 137575.49 | 1.790
4958 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901727 | This is a Maintenance Resurfacing project, at Winchester Road frm Ferguson Road to Lower Huntington Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 142975.24 | 1.970
4959 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901728 | This is a Maintenance Resurfacing project, at Yohne Road frm Branstrator Rd to Smith Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 172322.14 | 2.530
4960 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901731 | This is a Bridge Rehabilitation (no added capacity) project, at 56th St over Indian Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-05-17 | 2010-10-31 | 2010-09-29 | 182156.01 | 0.100
4961 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901733 | This is a Bridge Rehabilitation (no added capacity) project, at Mann Road over Mann Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-05-17 | 2010-10-31 | 2010-09-29 | 237870.92 | 0.100
4962 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901734 | This is a Special Bridge project, on the CF&E Railroad over the St Marys River in Adams County, to replace a steel girder to provide an improved rail line for economic development to an industrial are | Bridge Improvement | 2010-03-05 | 2010-03-23 | 2010-08-28 | 2011-11-11 | 2548764.85 | 0.050
4963 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901738 | This is a preventive maintenance resurfacing project on West 38th St from Raible Ave to Oakwood Blvd in Anderson, in Madison county to extend the service life of the road. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 128458.58 | 0.400
4964 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901739 | This is a Maintenance Resurfacing project, at W 25th St from Raible Ave to Park Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 72248.85 | 1.000
4965 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901740 | This is a Maintenance Resurfacing project, at Raible Ave from W 38th St to W 30th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 97332.64 | 0.700
4966 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901741 | This is a Maintenance Resurfacing project, at Park Rd from W 53rd St to W 25th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 174964.32 | 2.000
4967 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901742 | This is a Maintenance Resurfacing project, at Main St from 53rd St to 65th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 69697.33 | 1.000
4968 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901743 | This is a Maintenance Resurfacing project, at Lindberg Rd from Alexandria Pike to Rangeline Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 176131.43 | 2.020
4969 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901744 | This is a Maintenance Resurfacing project, at E 38th St from SR 9/Scatterfield Rd to Rangeline Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 70076.86 | 1.000
4970 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901745 | This is a Maintenance Resurfacing project, at Cross St from SR 9/Scatterfield Rd to Rangeline Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 120762.71 | 1.400
4971 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901746 | This is a Maintenance Resurfacing project, at Columbus Ave from 53rd St to 67th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 97353.17 | 1.100
4972 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901747 | This is a Maintenance Resurfacing project, at Alexandria Pike from University Blvd. to SR 9/Scatterfield Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 144770.45 | 1.800
4973 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901748 | This is a Maintenance Resurfacing project, at W 53rd St from CSX Railroad Crossing to Layton Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 127703.66 | 1.600
4974 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD |  | 09 | 0901750 | This is a Maintenance Resurfacing project, at Scottsville Rd from Martin Road to the Clark County line; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-04-23 | 2010-05-05 | 2010-07-23 | 368400 | 4.330
4975 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901754 | This is a part of a special project, at the CF&E Railroad crossing on US 27, south of Adams St in Adams county to improve an old railroad crossing to imporve the rail line for an idustiral area. T | Bridge Improvement | 2010-03-05 | 2010-03-23 | 2010-08-28 | 2011-11-11 | 263879.2 | 0.020
4976 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901756 | This is a Safety project, at Approx 70 signalized intersections within Lafayette; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2009-12-31 | 2010-02-18 | 2010-07-31 | 2010-07-13 | 610929.22 | 0.100
4977 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RIPLEY |  | 09 | 0901757 | This is a Bridge Rehabilitation (no added capacity) project, at SR 48 - SR 48 over Laughery Creek, 1.70 miles E of SR 229; to perform Bridge Deck Replacement work. | Bridge Improvement | 2009-12-30 | 2010-03-15 | 2010-09-17 | 2010-09-15 | 523689.1 | 0.010
4978 | Completed | C220,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901776 | This is a Facilities for Pedestrians and Bicycles project, at Covington Rd Trail: from Sycamore Hills Dr to Scott Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-01-06 | 2010-03-18 | 2010-08-14 | 2010-10-29 | 529006.1 | 0.600
4979 | Completed | C220,C250 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901777 | This is a trail construction project, for the Cardinal Greenway Trail: from Troy Ave to CR 400 Wrian Facilities work in th city of Marion in Grant county using enhancement funds | Transportation Enhancements | 2010-01-06 | 2010-04-27 | 2010-09-01 | 2010-10-25 | 434534.1 | 2.000
4980 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RANDOLPH |  | 06 | 0901781 | This is a Maintenance Resurfacing project, at From the Little Mississinewa River to the Ohio State Line; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-04-07 | 2010-08-06 | 2010-08-14 | 2010-08-20 | 157759.01 | 0.920
4981 | Completed | C220,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901783 | This is a Facilities for Pedestrians and Bicycles project, at Covington Rd Trail: from Eggeman Rd to Sycamore Hills Dr; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-22 | 2010-03-18 | 2010-08-14 | 2010-11-22 | 578440.6 | 0.450
4982 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901785 | This is a Maintenance Resurfacing project, at Vermillion Drive/127th Street from Cline Avenue E to Fairbanks Avenue; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-11 | 2010-06-03 | 2010-06-30 | 2010-09-18 | 251128.26 | 0.840
4983 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901786 | This is a Maintenance Resurfacing project, at W Jefferson Blvd from 725' SW of Lutheran Hospital Ent. to 500'. NE of Illinois; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-08 | 2010-03-29 | 2010-06-26 | 2010-08-27 | 993909.84 | 3.950
4984 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901787 | This is a Maintenance Resurfacing project, at Wayne St from Broadway to Coombs St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-29 | 2010-05-27 | 2010-11-18 | 388452.81 | 1.340
4985 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901788 | This is a Maintenance Resurfacing project, at Berry St from Broadway to Coombs St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-29 | 2010-05-27 | 2010-11-18 | 344029.58 | 1.350
4986 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901789 | This is a Maintenance Resurfacing project, at Washington Blvd from Broadway to Clay St to; perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-29 | 2010-05-27 | 2010-11-18 | 226716.37 | 0.820
4987 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901790 | This is a Maintenance Resurfacing project, at Jefferson Blvd from Calhoun St to Clay St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-29 | 2010-05-27 | 2010-11-18 | 92395.17 | 0.330
4988 | Underway | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901793 | This is a trail project on the Cardinal Greenway & Main St, Randolph, Losantville, IN- Cardinal & Davis Meyersin Wayne county using enhancement funds. | Transportation Enhancements | 2010-04-06 | 2010-05-17 | 2011-04-15 |  | 1712258.77 | 0.010
4989 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901795 | This is a Facilities for Pedestrians and Bicycles project, at Cardinal Greenway & Martindale Creek, Wayne County, Economy IN; to perform Enhancement work. | Transportation Enhancements | 2010-02-22 | 2010-05-24 | 2010-09-30 | 2010-11-09 | 323246.65 | 0.010
4990 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901796 | This is a Maintenance Resurfacing project, at Randolph Street from 109th Avenue to 101st Avenue; to perform Surface Treatment work. | Pavement Improvement | 2010-01-27 | 2010-05-10 | 2010-06-01 | 2010-05-20 | 52157.06 | 1.000
4991 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901797 | This is a Maintenance Resurfacing project, at 109th Avenue from Colorado Street to Randolph Street; to perform Surface Treatment work. | Pavement Improvement | 2010-01-27 | 2010-05-10 | 2010-06-01 | 2010-05-20 | 43702.15 | 3.000
4992 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0901808 | This is a Safety project, at Intersection of 4th St and College Ave; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-03-23 | 2010-04-14 | 2010-08-15 | 2011-08-19 | 205727.96 | 0.010
4993 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0901809 | This is a Safety project, at Intersection of 4th St and Walnut St; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-03-23 | 2010-04-14 | 2010-08-15 | 2011-08-19 | 180669.42 | 0.010
4994 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901810 | This is a Maintenance Resurfacing project, at Diebold Rd from Clinton St to SR 1; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-01 | 57074.89 | 0.650
4995 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901811 | This is a Maintenance Resurfacing project, at Hosler Rd frm Tonkel Rd to Halter Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-05-12 | 2010-08-21 | 2010-08-02 | 207662.03 | 2.200
4996 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901812 | This is a Maintenance Resurfacing project, at Hursh Rd frm Auburn Rd to Tonkel Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-01 | 132964.75 | 1.780
4997 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901813 | This is a Maintenance Resurfacing project, at Union Chapel Rd frm Corbin Rd to Coldwater Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-01 | 72353.71 | 0.500
4998 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901814 | This is a Maintenance Resurfacing project, at Union Chapel Rd frm Coldwater Rd to Auburn Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-05-12 | 2010-08-21 | 2010-08-02 | 143994.03 | 0.970
4999 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901815 | This is a Maintenance Resurfacing project, at Union Chapel Rd frm Tonkel Rd to 160' W of Old Union Chapel; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-05-12 | 2010-08-21 | 2010-08-02 | 187064.17 | 2.000
5000 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901818 | This is a Maintenance Resurfacing project, at Central Avenue from I-65 to MLK Drive; to perform Surface Treatment work. | Pavement Improvement | 2010-04-09 | 2010-10-13 | 2010-09-30 | 2010-11-03 | 199796.63 | 1.340
5001 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901820 | This is a Maintenance Resurfacing project, at 35th Avenue from Chase Street to Grant Street; to perform Surface Treatment work. | Pavement Improvement | 2010-04-09 | 2010-10-13 | 2010-09-30 | 2010-11-03 | 124879.84 | 0.730
5002 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901823 | This is a Maintenance Resurfacing project, at CR 200E from SR 32 to CR 800N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-17 | 2010-08-15 | 2010-08-07 | 643595.68 | 8.100
5003 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901824 | This is a Maintenance Resurfacing project, at Old Hobart Road from Miller Avenue to US 20; to perform Surface Treatment work. | Pavement Improvement | 2010-04-09 | 2010-10-13 | 2010-09-30 | 2010-11-03 | 158855.2 | 0.680
5004 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901825 | This is a Maintenance Resurfacing project, at E State Blvd: from Anthony Blvd to Hobson Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-04-02 | 2010-06-26 | 2010-11-07 | 386584.6 | 0.880
5005 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901826 | This is a Maintenance Resurfacing project, at E State Blvd from Hobson Rd to Coliseum Blvd (SR 930); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-04-02 | 2010-06-26 | 2010-11-07 | 221536.04 | 0.520
5006 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901828 | This is a trail project for pedestrians and bicycles ont the Trail along 71st St from Eagle Creek North gate to Twelve Oaks Blvd on Indianapolis west side in Marion county | Transportation Enhancements | 2010-04-23 | 2010-10-15 | 2010-10-31 | 2011-10-06 | 920711.46 | 0.840
5007 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901831 | This is a Facilities for Pedestrians and Bicycles project, at NYC Rail to Trail: Wallen Rd to Till Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-23 | 2010-03-18 | 2010-08-28 | 2010-10-12 | 609068.95 | 0.490
5008 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901833 | This is a preventive maintenance resurfacing project, at East Rudisill Blvd from Calhoun St to South Anthony Blvd Fort Wayne, Allen county to perform asphalt resurface to extend the life of the stree | Pavement Improvement | 2009-12-31 | 2010-03-18 | 2010-06-26 | 2010-11-18 | 452791.05 | 1.050
5009 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901834 | This is a project provide for pedestrians and bicycles on West Rudisill Blvd from Broadway to Calhoun Street in Fort Wayne in Allen county using enhancement money. This is 1 of 2 projects under cont | Transportation Enhancements | 2009-12-31 | 2010-03-18 | 2010-06-26 | 2010-11-18 | 181481.68 | 1.050
5010 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901835 | This is a Maintenance Resurfacing project, at Samuelson Road from Robbins Road to 750 Ft South of Indiana Toll Rd; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-05-25 | 2010-07-01 | 2010-07-20 | 116754.84 | 0.700
5011 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901836 | This is a Safety project, at Various intersections on Campbell St., Calumet Ave, Silhavy and LaPorte Ave; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2009-12-31 | 2010-01-21 | 2010-07-01 | 2010-02-18 | 78205.25 | 0.010
5012 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901837 | This is a Maintenance Resurfacing project, at Nebo Rd from SR 332 to River Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-05-12 | 2010-08-15 | 2010-06-23 | 288668.66 | 2.200
5013 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901839 | This is a Maintenance Resurfacing project, at Doyle Rd frm Dawkins Rd to Edgerton Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-09 | 38690.33 | 0.500
5014 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901840 | This is a Maintenance Resurfacing project, at Halter Rd frm St Joe Rd to Cedar St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-09 | 48803.59 | 0.520
5015 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901841 | This is a Maintenance Resurfacing project, at Wayne Trace frm Tillman Rd to 450' S of Philley Ave (Ft Wayne City Limits); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-09 | 160321.72 | 1.650
5016 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901842 | This is a Maintenance Resurfacing project, at Wheelock Rd frm Flutter Rd to St Joe Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-09 | 192336.57 | 1.780
5017 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 02 | 0901848 | This is a Maintenance Resurfacing project, at Old US 33 from Ash Road to SR 19; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-07-16 | 2010-08-15 | 2010-08-14 | 746837.44 | 3.100
5018 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901849 | This is a Maintenance Resurfacing project, at CR 30 from CR 13 to CR 15; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-07-16 | 2010-08-15 | 2010-08-14 | 104403.54 | 1.000
5019 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901850 | This is a Facilities for Pedestrians and Bicycles project, at Covington Rd Trail: Beal Taylor Ditch to Eggeman Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-22 | 2010-03-18 | 2010-08-14 | 2010-11-09 | 436132 | 0.170
5020 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FAYETTE |  | 06 | 0901862 | Surface Treatment, Thin HMA Overlay on SR1, From South City Limits to North City Limits of Connersville | Pavement Improvement | 2010-10-29 | 2011-04-08 | 2011-08-12 | 2011-07-06 | 315000 | 7.170
5021 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901867 | This is a Maintenance Resurfacing project, at Bypass Road from West Lexington to 550 feet west of Nappanee; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-08 | 2010-05-12 | 2010-07-01 | 2010-07-09 | 134487.51 | 0.490
5022 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901868 | This is a Maintenance Resurfacing project, at Old US 20 from Oak Manor Place to Bypass Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-08 | 2010-05-12 | 2010-07-01 | 2010-07-09 | 66618.64 | 0.360
5023 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901869 | This is a Maintenance Resurfacing project, at Lexington Avenue from Bypass Road to 370' W of 22nd St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-08 | 2010-05-12 | 2010-07-01 | 2010-07-09 | 89873.85 | 0.460
5024 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901870 | This is a Maintenance Resurfacing project, at County Road 13 - Jeanwood from 100' N of East Lake Drive N to C.R. 6; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-06-25 | 2010-08-01 | 2010-07-06 | 135481.25 | 1.080
5025 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901871 | This is a Safety project, at Intersection of Pearl St. and Elm St.; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-03-23 | 2010-04-20 | 2010-06-16 | 2010-07-07 | 140777.04 | 0.010
5026 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901877 | This is a Maintenance Resurfacing project, at Bremen Highway from Ireland Road to US 20 By-Pass; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-05-11 | 2010-09-30 | 2010-06-15 | 158503.46 | 0.450
5027 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901878 | This is a Reconstruction (no added capacity) project, at Middlebury St: from Main St to Zollinger Rd; to perform Other Roadside Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-07-19 | 2010-08-06 | 2010-08-19 | 200657.27 | 0.890
5028 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901879 | This is a PreventiveMaintenance Resurfacing project, at Dierdorff Rd (CR 27) from CR 40 to Kercher Rd in Elkhart county that will exend the life of the pavement. | Pavement Improvement | 2010-02-22 | 2010-07-02 | 2010-08-06 | 2010-08-04 | 119720.51 | 1.010
5029 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901880 | This is a Maintenance Resurfacing project, at Clinton St: from 410' West of Tanglewood Dr to Green Rd; to perform Other Roadside Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-07-13 | 2010-08-06 | 2010-08-18 | 149362.28 | 0.570
5030 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 06 | 0901914 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge # 268 over St Mary's River on Bostick Rd (Pedestrian); to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2010-04-10 | 2010-05-21 | 2010-10-30 | 2010-11-19 | 1226709.6 | 0.040
5031 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901915 | This is a Maintenance Resurfacing project, at 93rd Ave.- Cline to Marquette, Deodor to Hart St and White Oak to W of Columbia; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-04-01 | 2010-08-06 | 2010-08-01 | 2010-09-07 | 320852.9 | 2.770
5032 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0901923 | This is a Maintenance Resurfacing project, at From US 41 to 7th St; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-07-30 | 2010-08-05 | 79737.73 | 0.400
5033 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901926 | This is a Facilities for Pedestrians and Bicycles project, at Fort Wayne Rivergreenway Maintenance-Boardwalk decking & Bridge hand Rails; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-01-06 | 2010-03-15 | 2010-06-26 | 2010-08-06 | 292076.01 | 0.390
5034 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901930 | This is a Maintenance Resurfacing project, at Carroll Rd from 79th St to 86th St; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-04-01 | 2010-07-06 | 2010-08-13 | 2010-08-10 | 320862.52 | 1.000
5035 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901931 | This is a Maintenance Resurfacing project, at Carroll Rd from Pendleton Pike to 75th St; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-04-01 | 2010-07-06 | 2010-08-13 | 2010-08-10 | 93740.04 | 0.200
5036 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901939 | This project is a preventive naintenance resurfacing project on Bluffton Road from Liberty Dr to Old Trail Road in Allen county to extend the service life of the pavement. | Pavement Improvement | 2010-02-22 | 2010-06-01 | 2010-06-26 | 2010-07-01 | 162361.58 | 0.510
5037 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901944 | This is a Maintenance Resurfacing project, at N River Rd from Corporate Limits (1,500' W of Landin Rd) to 570' Wof Landin Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-15 | 2010-08-14 | 2010-08-19 | 31959.5 | 0.180
5038 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901945 | This is a preventive maintenance project which will extend the service life of the road, on Moeller Rd from West of Quail Creek Blvd to the city limits west of Woodland Dr in Allen county. | Pavement Improvement | 2010-04-01 | 2010-07-15 | 2010-08-14 | 2010-08-19 | 56044.16 | 0.410
5039 | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901946 | This project will upgrade the traffic signals on Kossuth Street at 16th Street And 18th Street in Tippecanoe County. | Safety/Traffic Management | 2010-05-21 | 2010-06-24 | 2010-08-31 | 2010-06-30 | 18680.5 | 0.100
5040 | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901947 | This project will upgrade the traffic signals at 26th Street And Earl/hedgewood in Tippecanoe County. | Safety/Traffic Management | 2010-05-21 | 2010-06-24 | 2010-08-31 | 2010-06-30 | 53988.5 | 0.100
5041 | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901948 | This project will upgrade the traffic signals at 36th Street And At Shenandoah in Tippecanoe County. | Safety/Traffic Management | 2010-05-21 | 2010-06-24 | 2010-08-31 | 2010-06-30 | 50718 | 0.100
5042 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RANDOLPH |  | 06 | 0901950 | This proejct clears the right of way in preparation for a major road reconstruction project on Parcels 17 and 35 to remove and demolish buildings on SR 32 in Randolf county on the east side of Winches | Other | 2010-03-24 | 2010-03-30 | 2010-04-15 | 2010-04-14 | 21812.5 | 0.220
5043 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901954 | This is a Facilities for Pedestrians and Bicycles project, at NYC Rail to Trail: Till Rd to 0.4 miles N of Till Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-22 | 2010-04-01 | 2010-08-28 | 2010-09-22 | 536636.34 | 0.400
5044 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901981 | This is a Safety project, at Madison St at 29th St and 26th St; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-04-27 | 2010-05-25 | 2010-06-25 | 2010-08-31 | 193786.4 | 0.010
5045 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901995 | This is a Maintenance Resurfacing project, at North River Rd from Landin Rd to I-469; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 137462.93 | 1.450
5046 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901996 | This is a Maintenance Resurfacing project, at Thomas Rd from RR Xing 3100' North of Illinois Rd to Bass Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 71176.02 | 0.370
5047 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901997 | This is a Maintenance Resurfacing project, at Monroeville Road from US 27 to Marion Center Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 98193.65 | 1.310
5048 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901998 | This is a Maintenance Resurfacing project, at Scott Road from RR Crossing 725' South of Seegar Blvd to Bass Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 41976.39 | 0.350
5049 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901999 | This is a Maintenance Resurfacing project, at Knoll Road from Smith Road to Ardmore Avenue; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 70433.88 | 1.000
5050 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0902000 | This is a Maintenance Resurfacing project, at Seiler Road from Adams Center Road to Green Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 225029.23 | 2.480
5051 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0902011 | Bridge Replacement, Other Construction on I465, WB 82nd St over I465 | Bridge Replacement | 2010-11-01 | 2010-12-28 | 2011-10-15 | 2011-10-15 | 1050000 | 0.010
5052 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0902180 | This is a Safety project, at Guardrail upgrades to various bridges in Northeast Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 2010-04-01 | 2010-05-07 | 2010-08-21 | 2010-06-25 | 229133 | 1.000
5053 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0902181 | This is a Safety project, at Guardrail upgrades to various bridges in Northwest Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 2010-04-01 | 2010-05-06 | 2010-08-21 | 2010-07-12 | 138060.43 | 1.000
5054 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0902182 | This is a Safety project, at Guardrail upgrades to various bridges in Southeast Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 2010-04-01 | 2010-06-03 | 2010-08-21 | 2010-06-21 | 115688.08 | 1.000
5055 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0902183 | This is a Safety project, at Guardrail upgrades to various bridges in Southwest Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 2010-04-01 | 2010-05-05 | 2010-08-21 | 2010-07-08 | 122498.96 | 1.000
5056 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RANDOLPH |  | 06 | 1004017 | This project will replace the bridge on SR 32 over Sparrow Creek in Randolph County.. | Bridge Replacement | 2009-05-13 | 2009-07-29 | 2009-11-20 | 2009-11-20 | 867750 | 0.010
5057 | Underway | C220 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005675 | Roadside Maintenance, Herbicide, Various Counties - at various locations within the Crawfordsville District. | Transportation Enhancements | 2010-10-20 | 2011-08-01 | 2012-09-30 |  | 250760.67 | 0.010
5058 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005726 | Roadside Maintenance, Herbicide, Various Counties - at various locations along two lane roads in the Angola, Elkhart and FtWayne Subdistricts | Transportation Enhancements | 2010-10-12 | 2011-06-02 | 2011-06-15 | 2011-06-27 | 106096.76 | 0.030
5059 | Underway | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005729 | Roadside Maintenance, Landscaping, various counties, at various locations along I-65, I-70, I-74 and SR 63 within the Crawfordsville District | Transportation Enhancements | 2010-10-12 | 2011-03-29 | 2011-07-01 |  | 479792.5 | 0.010
5060 | Underway | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005730 | Roadside Maintenance, Herbicide, Various Counties - at various locations within the LaPorte District. | Transportation Enhancements | 2010-10-20 | 2011-09-13 | 2011-11-30 |  | 307045.12 | 0.030
5061 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005731 | Roadside Maintenance, Herbicide, Various Counties - at various locations within the LaPorte District. | Transportation Enhancements | 2010-10-12 | 2011-09-29 | 2011-11-30 | 2011-11-28 | 120330 | 0.030
5062 | Underway | C220 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005732 | Roadside Maintenance, Landscaping, Marshall County, at various locations along US 31 and US 30 Interchange | Transportation Enhancements | 2010-10-12 | 2011-02-23 | 2012-06-01 |  | 178005 | 0.030
5063 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 1005845 | Railroad Crossing on county roads in Jasonville,Dugger, & Linton in Greene County within a corridor streching 10.6 m | Safety/Traffic Management | 2011-01-20 | 2011-05-02 | 2011-10-15 | 2011-12-31 | 4904255 | 0.010
5064 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 1441044 | This is a Maintenance Resurfacing project, at From 4th St, 1.02 miles W of E jct with US 231, to E jct with US 231; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-05-19 | 2010-07-06 | 2010-10-31 | 2011-06-17 | 2618383.48 | 0.990
5065 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 1475040 | This project will improve drainage by replacing the structure on US 35 ofer Laramore Ditch in Starke County. | Pavement Improvement | 2009-06-04 | 2009-08-04 | 2009-11-01 | 2009-11-30 | 755990.17 | 0.010
5066 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE |  | 02 | 1477002 | This is a Safety project, at US 35 - At Schultz Rd, 0.14 mile N of I-80/90 Underpass; to perform Sight Distance Improvement work. | Safety/Traffic Management | 2009-10-08 | 2009-10-12 | 2010-08-13 | 2010-08-06 | 909249.18 | 0.270
5067 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 1531031 | This is a Bridge Replacement (capacity added) project, at Bridge over Little Buck Creek, 1.16 miles S of I-465; to perform Bridge Replacement, Other Construction work. | Bridge Replacement | 2010-02-20 | 2010-03-15 | 2011-08-02 | 2011-10-12 | 3130889 | 0.110
5068 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 1621002 | This project will add turn lanes and improve the intersection of US 19 and county road 42 in Elkhart County. | Pavement Widening | 2009-08-18 | 2010-04-01 | 2010-06-30 | 2010-07-21 | 812909 | 0.010
5069 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 1810014 | This is a Reconstruction (no added capacity) project, at SR 15 - Over Wolf Lake Drain, 2.65 miles N of US 33; to perform Small Structure, Replacement work. | Pavement Improvement | 2009-10-14 | 2010-07-28 | 2010-10-01 | 2010-09-17 | 479931.03 | 0.010
5070 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 1941018 | This project will improve and widen intersections along SR 8 and SR 49 in Porter County. | Safety/Traffic Management | 2009-08-27 | 2009-10-22 | 2010-06-29 | 2010-11-23 | 1947964 | 0.930
5071 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 2127112 | This project will widn US 6 in Elkhart County with the installation of sidewalks along the North side of the road and a wider median. | Pavement Widening | 2009-07-17 | 2010-03-03 | 2010-10-22 | 2010-11-12 | 4949108 | 0.940
5072 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITLEY |  | 03 | 2192034 | This is a Reconstruction (no added capacity) project, at US 33 - At Clingerman Avenue, 0.5 mile N of SR 205; to perform Curve Correction work. | Pavement Improvement | 2009-09-08 | 2009-10-21 | 2010-06-18 | 2010-06-11 | 302904 | 0.100
5073 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 2195026 | This project will construct a median left turn lane on US 33 near US 20 in Dunlap, Elkhart County. New pavement, drainage structures, signals and signs will be placed and a bridge widened. | New Construction | 2009-03-27 | 2009-07-23 | 2011-10-07 | 2011-11-18 | 10765478.72 | 5.420
5074 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | UNION |  | 06 | 2493013 | This project will repair and restore the pavement and replace signs on US 27 from the Ohio State line north 3.6 miles in Union county. | Pavement Widening | 2009-04-15 | 2009-08-05 | 2012-02-10 | 2011-11-16 | 9345892.93 | 3.580
5075 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 3227023 | This project will improve the sight distance at SR 26 and county road 750 south in Grant County. | Pavement Improvement | 2009-07-07 | 2009-08-21 | 2009-11-13 | 2010-04-19 | 986682.26 | 0.200
5076 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 3325007 | This project will replace the bridge on SR 17 over Starr Ditch in Fulton County. | Bridge Replacement | 2009-04-17 | 2009-07-06 | 2009-11-14 | 2009-09-25 | 556948.74 | 0.010
5077 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 3630005 | This is a trail project for pedestrians and bicycles on the Pennsy Trail from just East of German Church Road to Mt. Comfort Road ( Hancock county road 600 W) using enhanacment funds. | Transportation Enhancements | 2010-03-04 | 2010-03-31 | 2010-11-15 | 2011-04-30 | 1641150 | 2.000
5078 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS |  | 04 | 3632005 | This project will improve the surface and rebuild sections of the bridge on US 40 over White Lick Creek in Hendricks County. | Pavement Improvement | 2009-03-24 | 2009-04-20 | 2009-11-24 | 2010-06-30 | 2847000 | 0.010
5079 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SULLIVAN |  | 08 | 3677012 | This project will improve the intersection on SR 54 and add turn lanes at County Road 50 South, 1 mile West of SR 159. | Pavement Improvement | 2009-05-08 | 2009-07-14 | 2010-04-17 | 2010-03-19 | 717361.6 | 0.110
5080 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 3801006 | This is a Bridge Replacement (no added capacity) project, at Bridge over Smith-Shoemaker Ditch, 2.1 miles E of US 27; to perform Bridge Replacement work. | Bridge Replacement | 2010-03-23 | 2010-07-19 | 2010-10-16 | 2010-09-21 | 684476.62 | 0.010
5081 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 4072004 | This project will replace the bridge on SR 356 over Town Creek in Scott County. | Bridge Replacement | 2009-03-19 | 2009-04-07 | 2009-10-31 | 2009-10-23 | 627953.34 | 0.200
5082 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 04 | 4223005 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Pavement Improvement | 2009-06-17 | 2009-07-16 | 2010-08-31 | 2010-09-17 | 3270050.51 | 1.020
5083 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW | COLUMBUS | 06 | 4303009 | This project will add turn lanes, nodernize the signal, and widen the intersection at SR 11and Bartholomw county Road 450S. | Pavement Improvement | 2009-05-06 | 2009-06-01 | 2010-08-15 | 2010-11-01 | 1202944.2 | 0.010
5084 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 4312005 | This project will improve the sight distance at SR 75 and county road 700 north in Clinton County. | Safety/Traffic Management | 2009-06-03 | 2009-06-24 | 2009-11-15 | 2009-11-21 | 1206807.56 | 0.860
5085 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 4455005 | This project will replace and restore the pavement on SR 42 in Morgan County from Monrovia to Martinsville. | Pavement Improvement | 2009-06-04 | 2009-07-07 | 2010-11-20 | 2011-07-21 | 7339345 | 11.960
5086 | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 4475002 | This project will improve drainage by replacing the structure over Cannon ditch on SR 8 in Starke County | Pavement Improvement | 2009-08-19 | 2009-09-30 | 2009-10-31 | 2009-11-15 | 346456.39 | 0.010
5087 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 04 | 4923003 | This project will improve the surface and rebuild sections of the bridge on SR 341 over I-74 in Fountain County. | Bridge Improvement | 2009-03-23 | 2009-04-03 | 2009-07-31 | 2009-08-05 | 1220119 | 0.010
5088 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HENRY |  | 06 | 5133003 | This is a Bridge New Construction project, at 5.36 miles N of US 40; to perform New Br, Precast 3 Sided Culvert work. | New Bridge Construction | 2010-03-23 | 2010-05-18 | 2010-10-30 | 2011-05-15 | 404395.98 | 0.228
5089 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HENRY |  | 06 | 5133004 | This project replaces a old small drainage culvert on SR 103, 4 miles north of US 40 in Henry county. | Pavement Improvement | 2010-03-23 | 2010-05-18 | 2010-10-30 | 2011-05-15 | 425503.02 | 0.239
5090 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH |  | 02 | 5171008 | This project will improve drainage by replacing the structure on SR 331 over Madison Township Ditch in St. Joseph County. | Pavement Improvement | 2009-03-24 | 2009-06-01 | 2009-08-29 | 2009-08-07 | 618614.21 | 0.010
5091 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI |  | 05 | 5252007 | This project will improve drainage by replacing the structure on SR 16 over Washonis Creek in Miami County. | Pavement Improvement | 2009-09-08 | 2009-10-19 | 2010-09-03 | 2010-07-14 | 397020.7 | 0.100
5092 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 5639005 | This project will improve the sight distance at SR 250 and Scott Ridge Road in Jefferson County. | Safety/Traffic Management | 2009-05-08 | 2009-07-17 | 2009-09-25 | 2009-11-25 | 681704.39 | 0.010
5093 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 8571960 | This is a Reconstruction (no added capacity) project, at US 41 - At 93rd Ave, 1.9 miles N of US 231; to perform Intersection Improvement work. | Pavement Improvement | 2009-06-30 | 2009-07-28 | 2009-10-31 | 2009-12-02 | 2009237.54 | 0.010
5094 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART |  | 03 | 9031815 | This project will improve drainage by replacing the structure on SR 19 over Fisher-Gordon Ditch in Elkhart County. | Pavement Improvement | 2009-05-18 | 2009-07-22 | 2009-10-09 | 2009-10-21 | 526058.11 | 0.100
5095 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | HARRISON |  | 09 | 9032075 | This project will improve drainage by replacing a pipe on SR 11 on the East side of Elizabeth. | Pavement Improvement | 2009-07-09 | 2009-07-31 | 2009-10-17 | 2009-10-08 | 272187.22 | 0.010
5096 | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 9301060 | This project will improve drainage by replacing the structure on SR 5 over Loon Creek in Huntington County. | Pavement Improvement | 2009-08-14 | 2009-09-15 | 2009-10-23 | 2009-11-13 | 491081.17 | 0.010
5097 | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 9381900 | This is a road reconstruction project that will completly reconstruct the road and add lanes to increase the capacity of the road on Miami St from Kern Rd to Jackson Rd in St Joseph county. | Pavement Widening | 2010-04-22 | 2010-05-03 | 2010-10-15 | 2010-11-22 | 1891030.49 | 1.040
5098 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9610820 | This project will replace the bridge on SR 312 over the Indiana Harbor Canal in Lake County. | Bridge Replacement | 2009-06-18 | 2009-07-06 | 2009-10-31 | 2009-11-01 | 2153446.87 | 0.010
5099 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 9803670 | This project will rebuild the US 20 and I-69 interchange in Steuben county to improve traffic flow. | Bridge Replacement | 2009-06-01 | 2009-06-12 | 2010-10-15 | 2010-10-12 | 1994588.32 | 0.490
5100 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 9901720 | This project will replace the bridge on Locust Road over US 20 in St Joseph County. | Bridge Replacement | 2009-06-03 | 2009-06-16 | 2009-09-18 | 2009-11-17 | 2926297.42 | 0.090
5101 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 9901740 | This project will replace the bridge on SR 49 over Pleasant Township Ditch in Porter County. | Bridge Replacement | 2009-05-13 | 2009-06-26 | 2009-10-31 | 2009-10-29 | 758632.98 | 0.010
5102 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARTIN |  | 08 | 9903160 | This is a Reconstruction (no added capacity) project, at 3.38 miles E of SR 650; to perform Small Structure Replacement work. | Pavement Improvement | 2010-03-24 | 2010-04-14 | 2010-07-31 | 2010-09-02 | 681346.01 | 0.100
5103 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FRANKLIN |  | 06 | 9924012 | This is a Bridge Replacement (no added capacity) project, at Bridge #94 over E Fork Blue Creek, carrying Blue Creek; to perform Br Repl, Comp.Cont.Pres.Conc. I-Beam work. | Bridge Replacement | 2010-04-01 | 2010-04-12 | 2010-10-01 | 2010-10-07 | 829328.76 | 0.010
5104 | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 9943052 | This is a Bridge New Construction project, at Bridge over Waubee Drain, 3.39 miles S of US 6; to perform New Bridge, Other Construction work. | New Bridge Construction | 2010-02-20 | 2010-03-26 | 2010-09-25 | 2010-09-28 | 647849.2 | 0.010
5105 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9945111 | This is a trail project for pedestrians and bicycles and is the Phase 1 of the Bike Network in Crown Point, Lake county using enhancement funds. | Transportation Enhancements | 2010-02-24 | 2010-03-22 | 2010-10-15 | 2011-10-28 | 899763.55 | 0.010
5106 | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | Multiple | 9991027 | This project builds a new trail for pedestrians and bicycle, at Tioga Bridge as a bike/ped crossing over Lake Freeman and Tippecanoe River in White county. | Transportation Enhancements | 2010-01-19 | 2010-03-22 | 2010-10-15 | 2010-10-09 | 1082406.81 | 0.010
5107 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999193 | This project will extend the bridge life by repainting bridge beams at SR 49 over US 30 and SR 2 in Porter County. | Bridge Improvement | 2009-05-13 | 2009-06-30 | 2009-09-03 | 2009-09-03 | 346415.56 | 0.010
5108 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999194 | This project will extend the bridge life by repainting bridge beams at Calumet Ave over SR 49 and US 6 in Porter County. | Bridge Improvement | 2009-05-13 | 2009-06-30 | 2009-09-09 | 2009-09-04 | 347985.54 | 0.010
5109 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999228 | This project will upgrade and modernize the traffic signal at US 41 and 93rd Avenue in Lake County. | Safety/Traffic Management | 2009-06-30 | 2009-07-28 | 2009-10-31 | 2009-12-02 | 105696.65 | 0.010
5110 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 9999231 | This project will add turn lanes and improve the intersection of SR 25 at county road 575 west and county road 500 west in Tippecanoe County. | Pavement Widening | 2009-04-15 | 2009-05-04 | 2009-10-31 | 2009-11-05 | 1314059.37 | 1.120
5111 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 9999235 | This project will improve sections and extend the life of SR 11 from SR 250 to US 50 in Jackson County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-09-28 | 2009-11-30 | 2010-05-27 | 1129575.55 | 8.010
5112 | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 9999236 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment o | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 |  | 1025634.93 | 0.010
5113 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 9999241 | This is a Bridge Rehabilitation (no added capacity) project, at 21st Street over Big Eagle Creek; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2009-12-03 | 2010-06-01 | 2010-09-30 | 2010-09-28 | 546435.69 | 0.064
5114 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | A500030 | Bridge Replacement - STR NO 331-71-8899, Precast 3 sided box culvert, one span, total length 20', St Joseph County on US 331 over Grimes Ditch, 4.86 miles south of SR933. | Bridge Replacement | 2010-10-08 | 2011-03-16 | 2011-06-04 | 2011-05-13 | 110869.63 | 0.030
5115 | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | A501115 | Demolition of Bridge and Ramp D, Lake County - on SR 912 at Riley Road | Other | 2010-10-18 | 2010-12-02 | 2011-03-28 | 2011-03-28 | 1020473.75 | 0.010
5116 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD | KOKOMO | 05 | A600560 | This project is the 4th phase of a road reconstruction project that will totally reconstruct the pavement and add travel lanes on Dixon Road from Sycamore to Judson in Kokomo, Howard county. | Pavement Widening | 2010-04-15 | 2010-05-05 | 2012-08-31 | 2011-11-19 | 2107988 | 1.207
5117 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | A710953 | This is a Bridge Rehabilitation (no added capacity) project, at Indiana Ave historic bridge, on Indiana Ave where it crosses Elkhart River; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2010-05-12 | 2010-06-05 | 2010-10-15 | 2011-07-27 | 479577.57 | 0.030
5118 | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | A901422 | This is a Facilities for Pedestrians and Bicycles project, at B-Line Trail phase 2; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-21 | 2010-05-17 | 2011-06-29 | 2011-09-12 | 2057179.92 | 2.400
5119 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW | COLUMBUS | 06 | G195003 | This is a Maintenance Restoration & Rehabilitation project, at 17th St from US 31 to Central Ave; to perform Road Reconstruction work. | Pavement Improvement | 2010-01-13 | 2010-02-22 | 2011-10-31 | 2011-11-23 | 1661117 | 1.000
5120 | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | L720015 | This project will build a new bridge on US 52 over the Norfolk Southern Railroad, 2 miles South of SR 25 in Tippecanoe County. | New Bridge Construction | 2009-06-05 | 2009-08-20 | 2010-11-30 | 2010-11-23 | 6291766.4 | 0.010
5121 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE | OMAHA (NE)-IA | 05 | 000R001 | This project will provide grading, drainage, paving, electrical and lighting for an intermodal facility owned by the Iowa Interstate Railroad in Council Bluffs. The facility is located northeast of th | Other | 2010-02-11 | 2010-04-05 | 2010-12-01 | 2011-01-28 | 2000000 | 0.000
5122 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | FAYETTE |  | 01 | 000R002 | This project will replace track ballast and ties on 14 miles of D&W Railroad track between Dewar and Oelwein to improve operational efficiency and safety. | Other | 2010-01-06 | 2010-05-03 | 2010-12-01 | 2010-08-23 | 764200 | 0.000
5123 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | 000R003 | This ARRA project will construct part of a new rail based industrial park being developed by the Clinton Regional Development Corporation. Rail construction includes: construction of a 10,000 feet pas | New Bridge Construction | 2010-02-23 | 2010-02-23 | 2010-12-01 | 2011-07-06 | 2090186.83 | 0.000
5124 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 000R004 | This project will upgrade the electrical components of the swing span railroad bridge over the Mississippi River between Keokuk, Iowa and Hamilton, Illinois. The project updates the electrical system | Transportation Enhancements | 2010-02-23 |  | 2010-12-01 | 2011-03-17 | 120900 | 0.000
5125 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | PAGE |  | 05 | 0022044 | This project will provide an improved driving surface by widening and resurfacing 2.0 miles of Iowa Highway 2 from W State Street to S 16th Street in Clarinda with hot-mix asphalt. | Pavement Improvement | 2009-03-30 | 2009-04-06 | 2009-11-01 | 2010-01-05 | 848817 | 1.900
5126 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | IOWA | DECATUR, RINGGOLD |  | 05 | 0024043 | This project will provide an improved driving surface by widening and resurfacing 11.51 miles of Iowa Highway 2 from Kellerton east to I-35 with Hot-Mix Asphalt. This project also includes the replac | Pavement Improvement | 2010-11-01 | 2011-03-30 |  | 2011-08-18 | 3076622.76
5127 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | DAVIS |  | 02 | 0028035 | This project will provide an improved driving surface by widening and resurfacing with hot-mix asphalt 4.9 miles of Iowa Highway 2/US Highway 63 through Bloomfield from the west junction of these hig | Pavement Improvement | 2009-06-29 | 2009-07-20 | 2010-07-01 | 2010-05-13 | 3651402.77 | 5.000
5128 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | PLYMOUTH |  | 05 | 0031075 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 3/South Dakota 50 over the Big Sioux River 0.5 miles North and 1.7 miles West of We | Bridge Replacement | 2009-03-06 | 2009-03-30 | 2009-11-01 | 2010-11-19 | 1842961 | 0.000
5129 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | BUENA VISTA |  | 05 | 0032053 | This project will replace a bridge, which is in poor condition and narrow with a new bridge. The bridge is on Iowa 3 over Brooke Creek 6.1 miles West of US 71 or approximately 10 miles Northwest of S | Bridge Replacement | 2009-07-31 | 2010-04-19 | 2010-11-01 | 2011-07-27 | 782441 | 0.000
5130 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 0064152 | This project will reconstruct and widen approximately 900 feet of 111th Street south and west of the intersection with US Highway 6 (Hickman Road) in the City of Clive. The project will include concr | Pavement Improvement | 2010-01-05 | 2010-07-23 | 2010-12-01 | 2011-06-15 | 586698 | 0.250
5131 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | WEBSTER, CALHOUN |  | 04 | 0074017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 11.7 miles of Iowa Highway 7 from 0.5 miles west of the Calhoun County Line to US Highway 1 | Pavement Improvement | 2009-03-26 | 2009-04-13 | 2009-12-01 | 2009-12-28 | 5364499 | 11.900
5132 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | OSCEOLA |  | 05 | 0092021 | This project will improve the driving surface by applying an unbonded portland cement concrete overlay on approximately 8.6 miles of Iowa Highway 9 from just west of Polk Avenue to just east of Tanage | Pavement Improvement | 2009-03-30 | 2009-05-04 | 2009-11-01 | 2010-01-19 | 4865289 | 8.800
5133 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 0132615 | Polk County is constructing a 0.4 mile extension of Adventureland Drive NW. The project will widen Adventureland Drive NW from a 2-lane roadway to a 4-lane roadway with median, sidewalk, and left-tur | Pavement Improvement | 2009-09-14 | 2009-09-22 | 2010-12-01 | 2010-08-30 | 706977 | 0.300
5134 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY | AMES | 04 | 0155662 | This project is in the city of Ames on George W. Carver Avenue from Stange Road to Bloomington Road. The project consists of one inch of hot-mix asphalt stress relief course and six inches of concret | Pavement Improvement | 2009-09-28 | 2009-10-12 | 2010-12-01 | 2011-03-09 | 717794 | 0.900
5135 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY | AMES | 04 | 0155664 | This project is in the city of Ames on Lincoln Way from Hickory Drive to just past Marshall Avenue. The project consists of milling the existing surface, patching problem areas, resurfacing with hot- | Pavement Improvement | 2009-08-27 | 2009-09-18 | 2010-12-01 | 2009-12-29 | 530759.85 | 0.300
5136 | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | STORY | AMES | 04 | 0155665 | This project will provide for the construction of .6 miles of the Skunk River Trail that will run along the west side of South Skunk River from just south of East 13th Street in South River Valley Par | Transportation Enhancements | 2009-08-27 | 2009-09-18 | 2010-12-01 | 2010-11-15 | 175728 | 0.600
5137 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY | AMES | 04 | 0155668 | This project consists of milling and resurfacing with asphalt 0.44 miles of roadway along Duff Avenue from 7th Street N. to 13th Street in Ames, Iowa. | Pavement Improvement | 2010-01-14 | 2010-09-16 | 2010-12-01 | 2011-10-25 | 504231 | 0.440
5138 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | WAPELLO |  | 02 | 0161017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 5.3 miles of Iowa Highway 16 from US Highway 34 to north city | Pavement Improvement | 2009-04-01 | 2009-04-06 | 2009-12-01 | 2009-10-07 | 1837373 | 5.500
5139 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | DAVIS, WAPELLO, VAN BUREN |  | 02 | 0161018 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 0.16 miles of Iowa Highway 16 from north city limit of Eldon t | Pavement Improvement | 2009-04-01 | 2009-04-06 | 2009-12-01 | 2009-10-07 | 1450974.35 | 4.300
5140 | Underway | C200,C240 | Highway Infrastructure Investment Grant | IOWA | CALHOUN |  | 04 | 0203083 | Grading of relocated US 20 in Iowa, from the east Sac County line to County Road N-33 in Calhoun County, 2.6 miles. | New Construction | 2010-03-01 | 2010-04-12 | 2010-12-01 |  | 2874975.12 | 4.200
5141 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CHICKASAW |  | 04 | 0241017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 6.75 miles of Iowa Highway 24 from east city limit of New Hamp | Pavement Improvement | 2009-04-03 | 2009-04-20 | 2009-11-01 | 2010-09-07 | 3200829 | 7.800
5142 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CHICKASAW, WINNESHIEK |  | 04 | 0241020 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 6 miles of Iowa Highway 24 from the west city limit of Lawler | Pavement Improvement | 2009-04-03 | 2009-04-20 | 2009-11-01 | 2010-09-07 | 2566288 | 6.300
5143 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CASS |  | 05 | 0285612 | This project replaces the bridge supports, which are in very poor condition, to extend the service life of the bridge. The bridge is located on Nishna Street over an unnamed creek just South of 29th | Bridge Improvement | 2009-10-12 | 2009-11-02 | 2009-12-01 | 2010-05-20 | 92520 | 0.000
5144 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CASS |  | 05 | 0285613 | This project is in Atlantic, Iowa on South Olive Street from East 14th Street to East 22nd Street. The project consists of pavement rehabilitation which will provide a smoother ride and improved drai | Pavement Improvement | 2010-01-21 | 2010-07-15 | 2010-12-01 | 2010-11-01 | 175000 | 0.500
5145 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | FREMONT |  | 05 | 0291068 | This project will replace two bridges, which are in poor condition, with new bridges. The bridges are on Interstate 29 over Plum Creek 0.5 miles South of Exit #20, or approximately 28 miles South of C | Bridge Replacement | 2009-03-06 | 2009-03-30 | 2009-11-01 | 2010-12-22 | 2085104.95 | 0.000
5146 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | FREMONT |  | 05 | 0291069 | This project will replace two bridges, which are in poor condition with new bridges. The bridges are on Interstate 29 over County Road J24 at Exit #20, approximately 27 miles South of Council Bluffs. | Bridge Replacement | 2009-03-06 | 2009-03-30 | 2009-11-01 | 2010-12-22 | 2797514 | 0.000
5147 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | FREMONT |  | 05 | 0291075 | On Interstate 29 in Fremont County Iowa, from 1.5 mile north of county road J-26 north to 1.5 mile north of county road J-24, a nine-inch concrete overlay will be placed on the northbound lanes and a | Pavement Improvement | 2009-03-06 | 2009-03-30 | 2009-11-01 | 2010-12-22 | 10718757.44 | 4.200
5148 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MILLS |  | 05 | 0292054 | This project will replace two bridges, which are in poor condition, with new bridges. The bridges are on Interstate 29 over St. Mary’s Creek 1 mile South of Exit #42, or approximately 5 miles South of | Bridge Replacement | 2009-03-06 | 2009-03-23 | 2009-11-01 | 2011-01-31 | 1726111 | 0.000
5149 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MILLS |  | 05 | 0292065 | On Interstate 29 in Mills County, Iowa, from 3 miles north of the north junction with US Highway 34 to the Pottawattamie County line, a nine-inch concrete overlay will be placed on the northbound lane | Pavement Improvement | 2009-03-06 | 2009-03-23 | 2009-11-01 | 2011-01-31 | 11742272 | 6.000
5150 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONONA, HARRISON |  | 05 | 0295100 | The Iowa DOT is reconstruction of I-29 from Exit 95, which services Little Sioux, Iowa, to Exit 112, which services Onawa, Iowa. The project includes the reconstruction of the grade and Portland Ceme | Pavement Improvement | 2009-04-23 | 2009-05-04 | 2010-11-01 | 2011-11-08 | 42538509 | 18.100
5151 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONONA |  | 05 | 0296167 | This project provides for a six inch hot-mix asphalt overlay on the north and southbound lanes of Interstate 29 in Monona County, Iowa, from just north of Iowa 175 north to the Woodbury County line. | Pavement Improvement | 2009-06-29 | 2009-07-31 | 2010-09-01 | 2011-01-06 | 21651042 | 13.500
5152 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONONA |  | 05 | 0296182 | This project will replace a bridge, which is in poor condition with a new bridge. The bridge is on Interstate 29 southbound over Robinson Creek approximately 3.5 miles South of Exit#127 near Sloan. | Bridge Replacement | 2009-03-06 | 2009-06-22 | 2009-11-01 | 2010-08-11 | 1150196.78 | 0.000
5153 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | TAMA |  | 03 | 0306151 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 11.9 miles of US Highway 30 from just east of M Avenue to Iow | Pavement Improvement | 2009-06-26 | 2009-07-17 | 2010-07-01 | 2010-07-21 | 4014290.57 | 11.900
5154 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | 0351105 | This project will replace two bridges, which are in poor condition and have inadequate clearance over Interstate 35, with new bridges. The bridges are on US 34 over Interstate 35 in Osceola. | Bridge Replacement | 2009-03-06 | 2009-04-01 | 2009-11-01 | 2011-09-13 | 1736085 | 0.000
5155 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | 0351111 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of the southbound lanes of I-35. The project begins approximately one mile north of Exit 22, which services Van Wert, Iowa, and e | Pavement Improvement | 2009-03-30 | 2009-04-07 | 2009-11-01 | 2011-01-10 | 15304219 | 9.500
5156 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | 0351112 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of the northbound lanes of I-35. The project begins approximately one mile north of Exit 22, which services Van Wert, Iowa, and e | Pavement Improvement | 2009-08-06 | 2010-04-05 | 2010-11-01 | 2011-02-01 | 8471001 | 9.500
5157 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | 0351116 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of US Highway 34 at the interchange of I-35 and US Highway 34; Exit 33 which services Osceola, Iowa. The project is approximately | Bridge Replacement | 2009-03-06 | 2009-04-01 | 2009-11-01 | 2011-09-13 | 1626415 | 0.400
5158 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | WARREN |  | 04 | 0352337 | This project provides for a four inch hot-mix asphalt overlay on the north and southbound lanes of Interstate 35 in Warren County Iowa, from the Clarke County line north to 2 miles south of Iowa 92 ne | Pavement Improvement | 2009-04-13 | 2009-05-05 | 2009-11-01 | 2010-08-02 | 16990416.07 | 11.300
5159 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLAYTON |  | 01 | 0523031 | This project includes performing cracking and seating of the existing portland cement concrete pavement and then applying a hot-mix asphalt overlay on approximately 9.0 miles of US Highway 52 from jus | Pavement Improvement | 2009-08-17 | 2009-08-24 | 2010-09-01 | 2010-12-20 | 3596503.3 | 9.000
5160 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLAYTON |  | 01 | 0523032 | This project will resurface eight miles of US 52 from Guttenberg to Garnavillo with six inches of hot-mix asphalt to improve pavement condition. | Pavement Improvement | 2009-08-17 | 2009-08-24 | 2010-09-01 | 2010-12-20 | 3307754.31 | 7.500
5161 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 0587631 | In Bettendorf, Iowa on 23rd Street from Grant Street to Central Avenue. This project will be constructed in three stages to minimize impact on residents in the area. The street will be graded and pa | Pavement Improvement | 2009-05-29 | 2009-06-08 | 2009-12-01 | 2010-12-22 | 739272 | 0.320
5162 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611122 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 2009-03-06 | 2009-04-08 | 2009-11-01 | 2009-07-07 | 126319 | 0.000
5163 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611124 | The project is part of the grading of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-Pass. This project is for the grading of the new alignment which will be | New Construction | 2009-03-06 | 2009-04-01 | 2010-09-01 | 2011-07-21 | 8245240 | 2.200
5164 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611129 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 2009-03-06 | 2009-04-06 | 2009-11-01 | 2011-02-01 | 519311.63 | 0.000
5165 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611132 | The project is part of the grading of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-Pass. This project is for the grading of the new alignment which will be | New Construction | 2009-03-06 | 2009-04-06 | 2010-09-01 | 2011-02-01 | 4912339 | 1.700
5166 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611162 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 2009-03-06 | 2009-04-06 | 2009-11-01 | 2011-02-01 | 250148.28 | 0.000
5167 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611165 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 2009-03-06 | 2009-03-18 | 2009-11-01 | 2009-06-02 | 295767.6 | 0.000
5168 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MAHASKA |  | 03 | 0633078 | This project will mill, widen, and resurface 9 miles of US 63 from New Sharon south to 210th Street North with five inches of hot-mix asphalt to improve pavement condition and safety. The widening wi | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2010-07-01 | 2010-08-30 | 7302569.2 | 9.200
5169 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | DECATUR, CLARKE |  | 05 | 0691038 | This project will widen and resurface 31 miles of US 69 from Osceola south to Interstate 35 west of Davis City with three inches of hot-mix asphalt to improve pavement condition and safety. | Pavement Improvement | 2009-04-01 | 2009-04-21 | 2009-11-01 | 2009-10-28 | 4892118.84 | 33.000
5170 | Completed | C240,C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 0694092 | This project will mill 1.5 inches and resurface with 4.5 inches of hot-mix asphalt on US 69 from Iowa 160 (Oralabor Road) north1.7 miles to First Street in Ankeny to improve pavement condition. | Pavement Improvement | 2009-10-02 | 2010-05-03 | 2010-12-01 | 2011-01-25 | 1045635.37 | 1.690
5171 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | PAGE, MONTGOMERY |  | 05 | 0711030 | This project will widen and resurface 17 miles of US 71 from Iowa 2 near Clarinda north to the intersection with US 34 north of Villisca with three inches of hot-mix asphalt to improve pavement condit | Pavement Improvement | 2009-03-30 | 2009-04-14 | 2009-11-01 | 2010-03-03 | 6189082 | 17.200
5172 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | SAC, CARROLL |  | 05 | 0715068 | This project will mill and replace two inches of the existing hot mix asphalt surface on approximately 12 miles of US 71 from just north of Carroll to the junction of Iowa 175 in Auburn to improve pav | Pavement Improvement | 2009-04-20 | 2009-05-21 | 2009-11-01 | 2009-10-12 | 1395963.34 | 10.500
5173 | Underway | C220 | Highway Infrastructure Investment Grant | IOWA | POLK |  | 03 | 0747603 | This multi-use path will be constructed as an alternative mode of transportation in the city of Bondurant, in Polk county. The path is along Second Street from 450 ft west of Mallard Point Circle NW | Transportation Enhancements | 2009-08-26 | 2009-08-26 | 2010-12-01 |  | 389313.69 | 0.779
5174 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BOONE |  | 04 | 0750627 | This project consistes of two roadways in Boone, Iowa: South Marshall Street from Hancock Drive to Crestwood Drive and Industrial Park Road from Linn Street to Argo Street. Both projects consist of p | Pavement Improvement | 2010-01-29 | 2010-04-01 | 2010-12-01 | 2011-06-14 | 473410 | 0.600
5175 | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | JOHNSON | IOWA CITY | 02 | 0801600 | This project is in Iowa City, Iowa on Hawkins Drive from the University of Iowa Hospital to Carver Hawkeye Arena. The project consists of pavement rehabilitation and widening which will provide a smo | Pavement Improvement | 2010-02-11 | 2010-02-01 | 2010-12-01 |  | 200000 | 0.400
5176 | Underway | C220,C240 | Highway Infrastructure Investment Grant | IOWA | JOHNSON | IOWA CITY | 02 | 0806285 | Construction of a recreational trail in Iowa City along IA 1 (N. Dodge Street) from Act Circle NE to Northgate Dr., 0.64 miles. The project includes construction of a pedestrian bridge over Interstat | Transportation Enhancements | 2010-03-19 | 2010-04-19 | 2010-12-01 |  | 1252603 | 0.630
5177 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE |  | 05 | 0921059 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 92 over Keg Creek approximately 2.7 miles West of Treynor. | Bridge Replacement | 2009-03-20 | 2009-04-06 | 2009-11-01 | 2010-10-05 | 1139901.2 | 0.000
5178 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE |  | 05 | 0921060 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 92 over Middle Silver Creek approximately 0.1 miles West of Treynor. | Bridge Replacement | 2009-03-20 | 2009-04-06 | 2009-11-01 | 2010-10-05 | 1279850 | 0.000
5179 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | DES MOINES |  | 02 | 0977632 | This project is in Burlington, Iowa on Mt. Pleasant Street from U.S. 61 to Osborn Street. The project consists of milling the existing surface down to the concrete subbase and paving two and a half i | Pavement Improvement | 2009-09-03 | 2009-09-14 | 2010-12-01 | 2010-09-13 | 1364054.71 | 1.500
5180 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | LINN | CEDAR RAPIDS | 02 | 1001061 | IA 922/U.S. Business Route 151 (1st Avenue) and Collins Road will be widened in Cedar Rapids, Iowa. The project will start at 40th Steet Dr. SE for 1.3 miles ending at Tama Street SE. Widening will | Pavement Widening | 2009-12-16 | 2010-04-19 | 2010-12-01 |  | 2832566 | 0.273
5181 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | 1040602 | Camanche, Iowa on Washington Boulevard from US 67 to 22nd Avenue. The project consists of pavement rehabilitation which will provide a smoother ride and improved drainage. | Pavement Improvement | 2010-01-15 | 2010-04-28 | 2010-12-01 | 2010-11-08 | 168623 | 0.600
5182 | Underway | C230 | Highway Infrastructure Investment Grant | IOWA | WARREN | DES MOINES | 04 | 1105603 | Carlisle, Iowa on South 1st Street from Highway 5 to School Street. The project consists of pavement rehabilitation which will provide a smoother ride and improved drainage. Better accommodations fo | Pavement Improvement | 2010-02-24 | 2010-08-02 | 2010-12-01 |  | 446670 | 0.300
5183 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | CARROLL |  | 05 | 1125612 | Carroll, Iowa on Clark Street from extended Anthony Street to 7th Street. The project consists of milling the existing surface and resurfacing with hot-mix asphalt. The three and a half inch overlay | Pavement Improvement | 2009-12-08 | 2010-06-16 | 2010-12-01 |  | 808258 | 0.700
5184 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | DUBUQUE |  | 01 | 1147603 | Cascade, Iowa on Tyler Street Northeast from 1st Avenue to just past Macomber Road. The project consists of milling the existing surface and resurfacing with three-inches of hot-mix asphalt providing | Pavement Improvement | 2009-12-23 | 2010-06-04 | 2010-12-01 | 2011-11-10 | 64456 | 0.700
5185 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK |  | 01 | 1185641 | This project consists of replacing the pavement of multiple roadways in Cedar Falls, Iowa: State Street from East 2nd Street to East 4th Street, East 2nd Street from Main Street to State Street and Ea | Pavement Improvement | 2009-10-19 | 2010-04-01 | 2010-12-01 |  | 700000 | 0.430
5186 | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK |  | 01 | 1185642 | This two phase Trail widening and resurfacing project is located along the North and South sides of the Cedar River in the city of Cedar Falls in Blackhawk County. Phase I, North Riverside Trail , ru | Transportation Enhancements | 2009-10-15 | 2010-08-30 | 2010-12-01 | 2011-04-12 | 207500 | 1.939
5187 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CHEROKEE |  | 05 | 1272618 | Cherokee, Iowa on North River Road from the city limits to the River Road Bridge. The project consists of a four inch hot-mix asphalt overlay with mail box turnouts and driveway/intersection fillets | Pavement Improvement | 2009-06-16 | 2009-07-20 | 2009-12-01 | 2009-12-07 | 180000 | 0.900
5188 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONONA, WOODBURY |  | 05 | 1412041 | To improve safety and winter driving conditions this project will grade four miles along Iowa 141. The project starts at the Woodbury and Monona County Line just southeast of Smithland and ends 4 mil | Pavement Improvement | 2009-03-27 | 2009-04-20 | 2009-11-01 | 2010-06-01 | 2271717 | 2.700
5189 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | 1415619 | Clinton County is extending 19th Avenue, approximately 1.9 miles, in the city of Clinton, Iowa, from Mill Creek Parkway east to Springdale Drive. The project is a new 4-lane Portland Cement Concrete | Pavement Improvement | 2009-12-23 | 2010-05-17 | 2010-12-01 |  | 815053 | 0.350
5190 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | BUCHANAN |  | 01 | 1503058 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 150 over Bear Creek approximately 3.3 mile South of Independence. | Bridge Replacement | 2009-03-06 | 2009-03-26 | 2009-12-01 | 2010-10-14 | 983635 | 0.000
5191 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | JOHNSON | IOWA CITY | 02 | 1557634 | This project is the construction of the .3 mile extension of 1st Avenue Trail along the west side of 1st Avenue from Country Club Drive north to Oakdale Blvd. in the city of Coralville in Johnson Coun | Transportation Enhancements | 2010-02-23 | 2010-05-17 | 2010-12-01 |  | 382549 | 0.289
5192 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1631080 | This project involves improvements at the intersection of Iowa Highway 163 and NE 75th Street in Pleasant Hill in Polk County, including the addition of portland cement concrete turn lanes and signal | Safety/Traffic Management | 2009-06-16 | 2009-06-22 | 2009-12-01 | 2009-12-14 | 750000 | 0.300
5193 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE | OMAHA (NE)-IA | 05 | 1642657 | The city of Council Bluffs, Iowa, is reconstructing College Road from US Highway 6 southeast and west to Valley View Drive. The project will replace approximately 0.96 miles of the existing roadway w | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-12-01 | 2010-08-03 | 2163357 | 1.500
5194 | Completed | C240,C230 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE | OMAHA (NE)-IA | 05 | 1642658 | The city of Council Bluffs, Iowa is repairing the transverse joints on 35th Street from Nebraska Avenue to 23rd Avenue. The project will extend the life of the existing Portland Cement Concrete (PCC) | Pavement Improvement | 2009-12-02 | 2010-04-12 | 2010-12-01 | 2010-07-09 | 478467.01 | 3.000
5195 | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE |  | 05 | 1642659 | The new construction of a Bicycle Pedestrian Trail along the east side of 13th Street between Avenue A and Avenue H in the city of Council Bluffs in Pottawattamie county. This project will increase s | Transportation Enhancements | 2009-10-15 | 2009-10-26 | 2010-12-01 | 2011-07-25 | 200000 | 0.510
5196 | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE | OMAHA (NE)-IA | 05 | 1642660 | For the reconstruction and improvement of multipule segments of a series of bicycle and pedestrian trails connecting the city of Council Bluffs urban and rural areas in Pottawattamie county. The spe | Transportation Enhancements | 2010-02-08 | 2010-04-14 | 2010-12-01 | 2011-05-20 | 471030 | 8.540
5197 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | RINGGOLD |  | 05 | 1691038 | This project is located on US 169 in Ringgold County from the intersection with Iowa 2 in Mount Ayr north 13 miles to the Union County line. The project will recycle three inches of the existing pave | Pavement Improvement | 2009-07-10 | 2010-04-05 | 2010-07-01 | 2011-10-19 | 4382345 | 12.900
5198 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | UNION |  | 05 | 1692021 | This project is located on US 169 in Union County, starting in Afton and proceeding south approximately 9 miles to the Union/Ringgold county line near Shannon City. The project will recycle three inc | Pavement Improvement | 2009-07-10 | 2010-04-05 | 2010-07-01 | 2011-10-19 | 3373398 | 8.700
5199 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | UNION |  | 05 | 1710609 | Creston, Iowa on East Prairie Street from Cherry Street to Mulberry Street. The project consists of a two inch hot-mix asphalt overlay which will provide a smoother ride on the roadway. The Poplar St | Pavement Improvement | 2009-08-27 | 2009-09-10 | 2010-12-01 | 2009-10-29 | 62778 | 0.100
5200 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 1827659 | This project consists of a number of different sections on multiple roadways in Davenport, Iowa: Jersey Ridge Road, Northwest Boulevard, Division Street, Locust Street, and Rockingham Road in three lo | Pavement Improvement | 2009-06-08 | 2009-07-20 | 2009-12-01 | 2012-02-14 | 1183107 | 2.477
5201 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 1827660 | The City of Davenport will patch the existing pavement at the intersection of Eastern Avenue and 53rd Street and Pine Street from 53rd Street to Northwest Boulevard to improve pavement conditions. Th | Pavement Improvement | 2009-06-11 | 2009-06-17 | 2009-12-01 | 2011-05-18 | 800000 | 0.000
5202 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 1827661 | This project will consist of constructing a new raised median along US Highway 67 from Iowa Street to Gaines Street and along US Highway 61 from Gaines Street to Marquette Street in the City of Davenp | Pavement Improvement | 2010-01-26 | 2010-04-19 | 2010-12-01 |  | 267842.79 | 0.900
5203 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | 1855613 | De Witt, Iowa on 11th Street from 6th Avenue to Humeston Road. The roadway will be milled and overlaid with two inches of hot-mix asphalt which will provide a smoother ride. Selected sidewalk ramps a | Pavement Improvement | 2009-06-01 | 2009-06-17 | 2009-12-01 | 2011-03-07 | 201885 | 0.490
5204 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945753 | Des Moines, Iowa on 6th Avenue from University Avenue to the Des Moines River Bridge. The roadway will be milled and problem areas will be patched as necessary. Traffic signal loops will be replaced | Pavement Improvement | 2009-05-27 | 2009-07-26 | 2009-12-01 | 2009-12-15 | 497395.63 | 0.900
5205 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | WARREN | DES MOINES | 04 | 1945754 | Des Moines, Iowa on Fleur Drive/Blue Street from Beardsley Street to Southwest 9th Street. The existing roadway surface will be milled before being overlaid with five inches of asphalt. The five inc | Pavement Improvement | 2009-05-27 | 2009-06-15 | 2009-12-01 | 2009-08-05 | 496951 | 1.200
5206 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945755 | Des Moines, Iowa on McKinley Avenue from Fleur Drive to South Union Street. The existing roadway surface will be milled and the traffic signal loop detectors will be replaced before being overlaid wi | Pavement Improvement | 2009-08-17 | 2009-09-29 | 2010-12-01 | 2010-08-16 | 339405 | 1.500
5207 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945756 | This project is in the city of Des Moines on Southeast 5th Street from East County Line Road to East Army Post Road. Three inches of hot-mix asphalt will be placed to improve driving quality and saf | Pavement Improvement | 2009-08-17 | 2009-09-14 | 2010-12-01 | 2010-08-16 | 442928.36 | 1.000
5208 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945757 | This project is in the city of Des Moines on McKinley Avenue from South Union Street to Southeast 5th Street. The project consists of widening and placement of a 10-inch portland cement concrete surf | Pavement Improvement | 2009-08-17 | 2010-04-01 | 2010-12-01 | 2011-11-15 | 1286228 | 0.300
5209 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945758 | In Polk county, the city of Des Moines will improve safety, driving quality, and capacity through portland cement concrete pavement widening with hot-mix asphalt resurfacing along Army Post Road fro | Pavement Improvement | 2009-12-07 | 2010-04-05 | 2010-12-01 | 2011-10-12 | 1000000 | 0.200
5210 | Underway | C220,C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945759 | The construction of the Principal Riverwalk multi-purpose trail extensions run along the West side of Des Moines River from Grand Avenue south to Walnut Street and from Court Avenue south to Vine Stre | Transportation Enhancements | 2009-10-06 | 2009-12-02 | 2010-12-01 |  | 2849000 | 0.200
5211 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | DUBUQUE | DUBUQUE (IL) | 01 | 2100646 | The city of Dubuque, Iowa, is purchasing the right-of-way for the construction of a new roadway to be known as the Southwest Arterial. The roadway will connect US highway 20 to US Highway 61. The pro | Other | 2009-09-10 | 2009-09-10 | 2010-12-01 | 2009-09-10 | 2909534 | 6.200
5212 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | DUBUQUE |  | 01 | 2160609 | This project replaces the bridge supports, which are in poor condition, to extend the service life of the bridge. The project also improves the aesthetics of the bridge to blend with the 1st Street i | Bridge Improvement | 2009-12-07 | 2010-03-31 | 2010-12-01 | 2011-11-10 | 156901 | 0.000
5213 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | BENTON |  | 03 | 2186045 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on US 218 over Pratt Creek approximately 7.5 miles West of Vinton. | Bridge Replacement | 2009-03-06 | 2009-04-20 | 2009-11-01 | 2010-10-22 | 976593.24 | 0.000
5214 | Completed | C240,C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 2290609 | In Scott county, the city of Eldridge will improve safety and mobility with hot-mix asphalt widening along 1st Street north of Trails Road and south of Fisher Court for .24 miles. | Pavement Improvement | 2009-10-13 | 2009-10-21 | 2010-12-01 | 2010-11-08 | 140000 | 3.100
5215 | Underway | C220 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | 2290610 | This project provides for the design and engineering of a multi-use trail that will run along the east side of County Road Y-64 from north of the city limits of Eldridge to south of the city limits of | Other | 2009-12-08 | 2009-12-08 | 2010-12-01 |  | 90152.21 | 0.000
5216 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JEFFERSON |  | 02 | 2465617 | The city of Fairfield, Iowa is reconstructing Kirkwood Avenue from 5th Street east to 2nd Street which has deteriorated beyond maintenance repairs. The 0.23 mile long project replaces the old roadway | Pavement Improvement | 2009-06-24 | 2009-08-31 | 2009-12-01 | 2010-06-18 | 278789.13 | 0.200
5217 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 2697618 | In Lee county, the city of Fort Madison will improve traffic management, safety, mobility, and carrying capacity. These enhancements will be made with structural improvements to pavement and the addit | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2010-12-01 | 2010-12-16 | 550000 | 0.010
5218 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 3125607 | In Polk county, the city of Grimes will improve driving quality, capacity, and safety along South James Street, beginning south of 6th Street and ending north of Urbandale approximately 2.0 miles. Th | Pavement Improvement | 2009-08-10 | 2009-08-24 | 2010-12-01 | 2011-01-31 | 1000000 | 2.200
5219 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | POWESHIEK |  | 03 | 3127622 | In Poweshiek county, the city of Grinnell will improve driving quality and safety through hot-mix asphalt resurfacing with milling along two sections of road; one along 8th Avenue from West Street (I | Pavement Improvement | 2009-07-06 | 2009-09-10 | 2009-12-01 | 2010-06-28 | 196400 | 1.000
5220 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | IDA |  | 05 | 3650603 | In Ida county, the city of Ida Grove will improve driving quality and safety by patching Moorehead Avenue, from 2nd Street to Ohio Street (Iowa 59), with portland cement concrete before placing a ho | Pavement Improvement | 2009-06-01 | 2009-09-08 | 2009-12-01 | 2010-02-03 | 200000 | 0.000
5221 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WARREN |  | 04 | 3680612 | The City of Indianola will improve approximately ¾ of a mile of North Y Street between Iowa Highway 92 and West Euclid Avenue by replacing the existing granular surface with a new concrete pavement. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2009-12-01 | 2009-10-26 | 494331 | 0.730
5222 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JOHNSON | IOWA CITY | 02 | 3715643 | In Johnson county, the city of Iowa City will improve driving quality and safety through hot-mix asphalt resurfacing with milling along South Riverside Drive (Old Highway 218) beginning south of High | Pavement Improvement | 2009-08-24 | 2009-09-01 | 2010-12-01 | 2010-09-16 | 600000 | 1.600
5223 | Underway | C240,C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 3827611 | This project will involve widening of the existing pavement on approximately 0.8 miles of Northwest 86th Street from Chamberry Boulevard to Northwest 62nd Avenue in the City of Johnston. The new conc | Pavement Improvement | 2010-01-26 | 2010-04-01 | 2010-12-01 |  | 1144528 | 0.800
5224 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARION |  | 03 | 4040606 | In Marion county, the city of Knoxville will improve driving quality and safety through hot-mix asphalt resurfacing with milling along two sections of road. One along South Roche Street from Robinson | Pavement Improvement | 2009-06-11 | 2009-10-05 | 2009-12-01 | 2009-12-14 | 296950 | 0.688
5225 | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | 4252601 | This project provides preliminary and final design engineering for the Mississippi River Trail (MRT) that will run along U.S. Highway 67 from the Eastern most city limits of Bettendorf to the Northern | Other | 2009-12-08 | 2009-12-08 | 2010-12-01 | 2010-08-10 | 214190 | 0.000
5226 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | DELAWARE |  | 01 | 4682621 | In Delaware county, the city of Manchester will improve driving quality and safety through hot-mix asphalt resurfacing along East Main Street from Brewer Street to Bailey Drive. | Pavement Improvement | 2009-11-03 | 2010-05-05 | 2010-12-01 | 2010-07-23 | 210309 | 0.370
5227 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JACKSON |  | 01 | 4742615 | In Jackson county, the city of Maquoketa will enhance safety and drainage with improvements to portland cement concrete curb and gutter along North Main Street from Grove Street to Quarry Street. Imp | Pavement Improvement | 2009-05-29 | 2009-07-22 | 2009-12-01 | 2010-08-13 | 244514 | 0.400
5228 | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775620 | Marion, Iowa intends to improve North 35th Street from Tower Terrace Road to Indian Creek Road. Improvements will include patching of the existing roadway pavement and grading and construction of bic | New Construction | 2010-01-27 | 2010-03-22 | 2010-12-01 |  | 1274994 | 0.686
5229 | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775621 | Marion, Iowa intends to reconstruct North 10th Street from Indian Creek Road to Tower Terrace Road. Reconstruction will include intersection modifications, pavement widening, culvert replacement, tra | Pavement Improvement | 2010-01-27 | 2010-04-05 | 2010-12-01 |  | 1228500 | 0.700
5230 | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775622 | Marion, Iowa will improve the Central Business District between North 10th Street from 7th Avenue to 8th Avenue. Construction includes updating traffic signals and lighting to improve safety and prov | Safety/Traffic Management | 2010-02-25 | 2010-06-07 | 2010-12-01 |  | 280000 | 0.660
5231 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775623 | Marion, Iowa intends to improve the intersection of Armar Drive and Highway 100. Intersection modifications will include traffic signal upgrades and concrete paving/widening. | Safety/Traffic Management | 2010-02-25 | 2010-07-07 | 2010-12-01 | 2011-11-10 | 450000 | 0.000
5232 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775624 | Marion, Iowa intends to improve the safety at the intersection of South 22nd Street and Highway 100 by installing new traffic signals, adding left turn lanes and extending existing left turn lanes. | Pavement Improvement | 2010-02-25 | 2010-07-06 | 2010-12-01 |  | 371360 | 0.000
5233 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARSHALL |  | 04 | 4797612 | In Marshall county, the city of Marshalltown will improve driving quality and safety by resurfacing along Iowa Avenue West, for 70 feet west of Parker Avenue to 648 feet east of south 6th street, wit | Pavement Improvement | 2009-09-09 | 2009-09-24 | 2010-12-01 | 2010-01-11 | 449376.89 | 3.000
5234 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MUSCATINE |  | 02 | 5330619 | In Muscatine county, the city of Muscatine will improve road safety, drainage, capacity and driving quality. Improvements will be obtained through replacement of portland cement concrete pavement, ce | Pavement Improvement | 2009-06-18 | 2009-08-10 | 2009-12-01 | 2010-08-05 | 733544 | 0.600
5235 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY |  | 04 | 5405607 | In Story county, the city of Nevada will improve the driving surface, and extend the service life of the pavement along W 4th Street, at U.S. Highway 30 heading north 1.0 mile to 1st Street, by resur | Pavement Improvement | 2009-05-27 | 2009-08-10 | 2009-12-01 | 2009-11-12 | 245333 | 0.980
5236 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JASPER |  | 03 | 5482611 | This project is on East 31st Street North and North 19th Avenue East from 1st Avenue east to East 19th Street in Newton. The project will improve the driving surface and extend the service life of th | Pavement Improvement | 2009-09-21 | 2009-09-23 | 2010-06-06 | 2010-05-03 | 620472 | 1.910
5237 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | 5557614 | This project will improve traffic flow and safety on Iowa 965 in North Liberty by constructing traffic signals at its intersection with Cherry Street. | Safety/Traffic Management | 2010-02-24 | 2010-04-27 | 2010-12-01 | 2011-10-17 | 285000 | 0.000
5238 | Completed | C240,C230 | Highway Infrastructure Investment Grant | IOWA | WARREN | DES MOINES | 04 | 5587602 | This project will improve access to new development by converting an existing three-way “T” intersection of Colonial Parkway and Iowa Highway 28 within the City of Norwalk into a four-way intersection | Pavement Improvement | 2010-03-15 | 2010-05-11 | 2010-12-01 | 2011-10-11 | 300000 | 0.300
5239 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WAPELLO |  | 02 | 5825637 | This project will increase capacity, improve safety and mobility along Lake Road in the city of Ottumwa in Wapello County. The project begins at the city limits along Lake Road and heads north for | Pavement Improvement | 2009-06-15 | 2009-10-05 | 2009-12-01 | 2010-04-08 | 632498 | 1.500
5240 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WAPELLO |  | 02 | 5825638 | In Wapello county, the city of Ottumwa will conduct structural enhancements including hot-mix asphalt resurfacing and portland cement concrete patching along .74 miles of roadway on Madison Avenue f | Pavement Improvement | 2009-06-15 | 2009-10-05 | 2009-12-01 | 2010-04-08 | 361255.93 | 1.000
5241 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARION |  | 03 | 5947613 | In Marion county, the city of Pella will replace deteriorating pavement on Independence Street heading south along Oskaloosa Street to southeast 9th Street. Smoother longer lasting pavement will be p | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2010-12-01 | 2011-11-16 | 323163 | 1.000
5242 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | DALLAS |  | 04 | 5970610 | This project will be rehabilitating the pavement along three roadways within the City of Perry totaling approximately 0.96 miles: Park Street from 1st Avenue to the east edge of Violet Hill Cemetery, | Pavement Improvement | 2009-05-21 | 2009-06-22 | 2009-12-01 | 2009-11-04 | 269251.35 | 0.900
5243 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | 6247601 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 0.75 miles of Lost Grove Road in the City of Princeton from US Highway 67 west 3960 feet. | Pavement Improvement | 2010-03-29 | 2010-08-04 | 2010-12-01 | 2011-09-06 | 249820 | 0.800
5244 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK | WATERLOO | 01 | 6342600 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 1.1 miles of County Route D-22/ Dubuque Road from the west to | Pavement Improvement | 2009-07-10 | 2009-08-17 | 2009-12-01 | 2010-08-27 | 750000 | 1.131
5245 | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY |  | 05 | 6890606 | The City of Sergeant Bluff will reconstruct approximately 0.3 miles of South Lewis Boulevard from 1st Street to Topaz Drive. The new concrete driving surface will improve ride quality and reduce main | Pavement Improvement | 2009-06-08 | 2009-08-03 | 2009-12-01 |  | 537483.46 | 0.290
5246 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SIOUX | SIOUX CITY (NE-SD) | 05 | 7055621 | This project will be rehabilitating the pavement along three roadways within the City of Sioux Center totaling 0.65 miles: 2nd Avenue from 4th Street SW to 3rd Street NW, 3rd Street NE from 1st Avenue | Pavement Improvement | 2009-05-18 | 2009-09-10 | 2009-12-01 | 2010-03-17 | 370399 | 0.650
5247 | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY | SIOUX CITY (NE-SD) | 05 | 7057662 | The City of Sioux City will reconstruct and widen approximately ½ mile of South Martha Street from Stone Avenue to Gordon Drive. The new concrete driving surface will improve ride quality and capacit | Pavement Improvement | 2009-06-25 | 2009-06-12 | 2009-12-01 |  | 792853 | 0.470
5248 | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY | SIOUX CITY (NE-SD) | 05 | 7057663 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on five sections of roadway within the City of Sioux City totaling 12.5 blocks: 3rd Street from Water Street | Pavement Improvement | 2009-06-09 | 2009-06-29 | 2009-12-01 |  | 495533 | 0.880
5249 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | CLAY |  | 05 | 7170619 | The city of Spencer Iowa is reconstructing West 11th Street from Grand Avenue west to 7th Avenue West, approximately 0.5 miles. The existing Portland Cement Concrete (PCC) roadway will be removed and | Pavement Improvement | 2010-03-08 | 2010-04-05 | 2010-12-01 | 2010-11-29 | 217026 | 0.500
5250 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | 7855606 | This project will replace existing deteriorated pavement with new full-depth portland cement concrete pavement patches on Sunset Street from Koser Avenue to Highland Drive and Melrose Avenue from Suns | Pavement Improvement | 2010-01-29 | 2010-06-09 | 2010-12-01 | 2010-12-16 | 50000 | 0.000
5251 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 7875632 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 1 mile of Iowa 100th Street from Douglas Avenue to Hickman Road in Urbandale. | Pavement Improvement | 2010-01-21 | 2010-07-28 | 2010-12-01 | 2011-01-31 | 1200000 | 0.990
5252 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK | WATERLOO | 01 | 8155708 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on four sections of roadway within the City of Waterloo totalling 1.93 miles: Broadway Street from Donald St | Pavement Improvement | 2009-05-22 | 2009-07-20 | 2009-12-01 | 2009-12-28 | 1431482.09 | 1.900
5253 | Underway | C220 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK | WATERLOO | 01 | 8155709 | This project provides for construction of a bicycle and pedestrian trail on the south bank of the Cedar River from West 6th Street to West 18th Street in the city of Waterloo in Blackhawk County. Thi | Transportation Enhancements | 2010-01-26 | 2010-06-01 | 2010-12-01 |  | 484866.72 | 1.069
5254 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BREMER |  | 01 | 8190623 | This project will upgrade traffic signals on Highway 3 (Bremer Avenue) in Waverly, Iowa at the following intersections; 15th Street West, 10th Street West, 6th Street West, 4th Street West, 1st Street | Safety/Traffic Management | 2009-12-23 | 2010-04-12 | 2010-12-01 | 2011-02-07 | 394997.5 | 0.000
5255 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 8477610 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 1.6 miles of 73rd Street from Center Street to Hickman Road i | Pavement Improvement | 2009-06-16 | 2009-07-08 | 2010-12-01 | 2009-10-30 | 538000 | 1.600
5256 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | ADAIR |  | 05 | C001071 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on 200th street over the West Fork of the Middle Nodaway River 0.5 miles East of Bridgewate | Bridge Replacement | 2009-06-17 | 2009-06-30 | 2009-12-01 | 2010-04-13 | 312195 | 0.100
5257 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | ADAMS |  | 05 | C002054 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2.8 miles of County Route N26 from the town of Nodaway | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-12-01 | 2009-09-08 | 217179 | 2.800
5258 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | APPANOOSE |  | 02 | C004077 | This project consists of applying a hot mix asphalt overlay at two locations in Appanoose County. One location is approximately 2.8 miles on County Route T14 from Iowa Highway 2 to just north of the | Pavement Improvement | 2009-07-08 | 2009-09-21 | 2009-12-01 | 2009-12-02 | 581000 | 3.300
5259 | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | APPANOOSE |  | 02 | C004078 | This project provides for construction of a box culvert extension over Ham Creek on the south side of county road J18 east of Honey Creek Resort State Park, north of Rathbun Lake in Appanoose county. | Transportation Enhancements | 2009-07-08 | 2009-07-20 | 2009-06-01 | 2010-08-30 | 150000 | 0.260
5260 | Underway | C220 | Highway Infrastructure Investment Grant | IOWA | APPANOOSE |  | 02 | C004079 | For the new construction of a 7 mile multi-use trail on the northern border of Rathbun Lake in Appanoose County. The trail will serve as an alternative mode of transportation from county road J18 to | Transportation Enhancements | 2009-08-31 | 2009-08-31 | 2010-12-01 |  | 1188552.5 | 8.294
5261 | Underway | C220 | Highway Infrastructure Investment Grant | IOWA | APPANOOSE |  | 02 | C004086 | This project will improve the Lake Rathbun Trail System in Appanoose County by adding 8.29 miles of granular surface trail as well as benches and a latrine. The proposed improvements will run from be | Transportation Enhancements | 2010-10-10 |  |  |  | 431956.28
5262 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | BENTON |  | 03 | C006078 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 5.7 miles of County Route | Pavement Improvement | 2009-08-24 | 2009-09-21 | 2010-12-01 | 2011-04-29 | 888727 | 5.500
5263 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK |  | 01 | C007116 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 2.8 miles of County Route | Pavement Improvement | 2009-06-11 | 2009-09-28 | 2009-12-01 | 2010-01-04 | 778935.38 | 3.500
5264 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | BOONE |  | 04 | C008053 | The project is located on Boone County Route R-21 which is also known as Nature Road. Boone County is placing Hot Mix Asphalt Resurfacing over Cold In-Place Recycling of the existing asphalt surface | Pavement Improvement | 2009-05-13 | 2009-08-31 | 2009-12-01 | 2009-10-14 | 558263 | 6.500
5265 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BREMER |  | 01 | C009061 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 3.6 miles of County Route | Pavement Improvement | 2009-07-20 | 2009-09-14 | 2009-12-01 | 2009-11-24 | 650000 | 3.500
5266 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | BUCHANAN |  | 01 | C010067 | This project will improve the driving surface and extend the life of the pavement by applying an unbonded concrete overlay on approximately 6.8 miles of County Route D22 from County Route V65 to Golf | Pavement Improvement | 2009-05-13 | 2009-05-26 | 2009-12-01 | 2010-09-09 | 1730000 | 7.000
5267 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BUENA VISTA |  | 05 | C011067 | This project will improve the driving surface and extend the life of the pavement by applying an unbonded concrete overlay on approximately 1.6 miles of 600th Street (East Milwaukee Road) from Geising | Pavement Improvement | 2009-05-14 | 2009-05-26 | 2009-12-01 | 2010-09-09 | 706026.08 | 1.500
5268 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CALHOUN |  | 04 | C013079 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 12 miles of County Route D15 from the Sac/Calhoun Count | Pavement Improvement | 2009-08-24 | 2009-09-21 | 2010-12-01 | 2010-08-23 | 2000000 | 12.000
5269 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CARROLL |  | 05 | C014124 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 7 miles of County Route N41 from US Highway 30 to Count | Pavement Improvement | 2009-05-20 | 2009-07-06 | 2009-12-01 | 2009-10-09 | 1000000 | 9.900
5270 | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | CARROLL |  | 05 | C014126 | For the reconstruction of a 13.5 mile segment of the Sauk Rail Trail from the city of Maple River Junction, which is just north of Highway 30, in Carroll County through the city of Breda towards the c | Transportation Enhancements | 2009-09-24 | 2010-04-13 | 2010-06-12 | 2011-05-17 | 1000000 | 12.900
5271 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CASS |  | 05 | C015050 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 6.4 miles of County Route G35 from County Route N28 to | Pavement Improvement | 2009-07-02 | 2009-07-06 | 2009-12-01 | 2009-10-20 | 1500000 | 6.500
5272 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CEDAR |  | 02 | C016078 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 4.1 miles of County Route | Pavement Improvement | 2009-08-17 | 2010-06-18 | 2010-12-01 | 2010-11-29 | 773396 | 4.500
5273 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CERRO GORDO |  | 04 | C017059 | This project includes performing cracking and seating of the existing concrete pavement and then doing a hot mix asphalt overlay. The work will be done on County Route B30 from the city of Mason City | Pavement Improvement | 2009-05-28 | 2009-09-08 | 2009-12-01 | 2009-10-19 | 1009770.74 | 4.500
5274 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CHEROKEE |  | 05 | C018054 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 3 miles of County Route M | Pavement Improvement | 2009-05-27 | 2009-09-02 | 2009-12-01 | 2010-06-28 | 500000 | 3.000
5275 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | C020071 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2 miles of County Route H45 at three separate locations | Pavement Improvement | 2009-07-10 | 2009-09-08 | 2009-12-01 | 2010-07-19 | 748000 | 1.000
5276 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | C023082 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 10.7 miles of County Route | Pavement Improvement | 2009-06-03 | 2009-08-03 | 2009-12-01 | 2010-10-21 | 524593 | 6.000
5277 | Completed | C250,C200 | Highway Infrastructure Investment Grant | IOWA | CRAWFORD |  | 05 | C024088 | The project is located on Crawford County Route (CCR) M55 (330th Street) and CCR E53 (S Avenue). Crawford County is replacing the existing Portland Cement Concrete roadway surface with a new Portland | Pavement Improvement | 2009-05-14 | 2009-06-22 | 2009-12-01 | 2010-03-23 | 1391865.1 | 6.800
5278 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | DALLAS |  | 04 | C025075 | The project is located on Dallas County Route (DCR) R16 (R Avenue). Dallas County is replacing the existing Portland Cement Concrete roadway surface with a new Portland Cement Concrete roadway surfac | Pavement Improvement | 2009-06-03 | 2009-07-08 | 2009-12-01 | 2009-10-26 | 726674 | 4.200
5279 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | DECATUR |  | 05 | C027042 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 1.9 miles of County Route J14 from Interstate 35 to US | Pavement Improvement | 2009-07-01 | 2009-09-08 | 2009-12-01 | 2009-09-28 | 368000 | 2.000
5280 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | DELAWARE |  | 01 | C028067 | This project will provide an improved driving surface, extension of the life of the pavement, and improved site drainage by applying a hot mix asphalt overlay with cold-in-place recycling and the repl | Pavement Improvement | 2009-05-21 | 2009-07-27 | 2009-12-01 | 2010-07-22 | 525953 | 3.000
5281 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | DICKINSON |  | 05 | C030037 | This project will improve the driving surface and enhance safety by applying an unbonded concrete overlay and doing necessary shoulder work on approximately 4.2 miles of County Route M27 from 190th St | Pavement Improvement | 2009-06-11 | 2009-07-16 | 2009-12-01 | 2010-06-07 | 1417702 | 4.200
5282 | Underway | C220 | Highway Infrastructure Investment Grant | IOWA | DICKINSON |  | 05 | C030039 | This project provides for resurfacing and renovation of various segments of Spine and Poyzer Trails in the cities of Milford, Arnolds Park, Okoboji, Spirit Lake, and Orleans in Dickinson County. The | Transportation Enhancements | 2010-01-11 | 2010-05-04 | 2010-12-01 |  | 186365 | 8.540
5283 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | DUBUQUE |  | 01 | C031061 | This project involves replacement of four bridges along Farley Road from Aitchison Road to the City of Cascade. | Bridge Replacement | 2010-02-18 | 2010-03-22 | 2010-12-01 |  | 506011 | 0.540
5284 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | EMMET |  | 04 | C032038 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2.9 miles of County Route N22 from County Route A17 to | Pavement Improvement | 2009-05-21 | 2009-07-17 | 2009-12-01 | 2009-10-12 | 470749.42 | 2.900
5285 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | EMMET |  | 04 | C032039 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2 miles of Emmet County Route A22 (170th Ave.) from the Dickinson/Emmet County line east to the Es | Pavement Improvement | 2009-05-21 | 2009-07-17 | 2009-12-01 | 2009-10-12 | 597840 | 3.300
5286 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | FAYETTE |  | 01 | C033106 | This project consists of applying a concrete overlay on Fayette County Route V68 (W Ave.) from U.S. Highway 18 northerly to 3rd St. in the city of Waucoma. The project also includes a concrete overla | Pavement Improvement | 2009-05-21 | 2009-05-28 | 2009-12-01 | 2010-11-12 | 1920000 | 8.000
5287 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | FLOYD |  | 04 | C034077 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 7.5 miles of Floyd County Route B60 (270th St.) from the Cerro Gordo/Floyd County line east to Ind | Pavement Improvement | 2009-05-15 | 2009-06-30 | 2009-12-01 | 2009-08-10 | 1268424.36 | 7.400
5288 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | FRANKLIN |  | 04 | C035057 | This project will improve safety along approximately ¾ mile of Franklin County Route S56 (Timber Ave.) from Iowa Highway 3 north to 155th St. on the south limits of the city of Hansell. The existing | Pavement Improvement | 2009-05-20 | 2009-09-21 | 2009-12-01 | 2009-12-28 | 210459.95 | 1.000
5289 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | GRUNDY |  | 03 | C038085 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2 miles of Grundy County Route T19 (F Ave.) from 1st Street in the city of Wellsburg north, past U | Pavement Improvement | 2009-05-21 | 2009-06-01 | 2009-12-01 | 2010-08-10 | 502117.32 | 2.500
5290 | Underway | C220,C240 | Highway Infrastructure Investment Grant | IOWA | GRUNDY |  | 03 | C038086 | This project provides for construction of the East Lake Trail on the east side of Grundy County Lake located SW of interchange U.S. Highway 20 & County Road T-55 (Union Ave.) which is just SW of the c | Transportation Enhancements | 2009-12-02 | 2009-12-02 | 2010-12-01 |  | 433008.94 | 0.780
5291 | Underway | C220 | Highway Infrastructure Investment Grant | IOWA | GUTHRIE |  | 05 | C039052 | This project provides for resurfacing and construction of 5.7 miles of the Raccoon River Valley Trail from Clay Street in the city of Panora to the Trailhead in the city of Yale both in Guthrie county | Transportation Enhancements | 2009-06-04 | 2009-06-04 | 2010-12-01 |  | 782454.72 | 5.340
5292 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HAMILTON |  | 04 | C040052 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road R27 over the Boone River 5 miles North of Webster City. | Bridge Replacement | 2009-05-11 | 2009-05-26 | 2009-12-01 | 2010-04-06 | 600000 | 0.100
5293 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HANCOCK |  | 04 | C041096 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 3.4 miles of Hancock County Route B20 (285th St./Quail Ave./290th St.) from Hancock County Route R | Pavement Improvement | 2009-05-28 | 2009-07-30 | 2009-12-01 | 2009-10-06 | 356466.18 | 3.500
5294 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HARDIN |  | 04 | C042064 | This project will provide an improved driving surface and reduce future roadway maintenance on Hardin County Route S56 from Iowa Highway 175 northerly to Hardin County Route D35 in Steamboat Rock. Th | Pavement Improvement | 2009-05-21 | 2009-06-01 | 2009-12-01 | 2010-08-10 | 699400 | 4.500
5295 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HARRISON |  | 05 | C043068 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Harrison County Route F32 from U.S. Highway 30 in Woodbine east 4.6 miles | Pavement Improvement | 2010-01-08 | 2010-05-10 | 2010-12-01 | 2011-02-10 | 1020000 | 4.100
5296 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HENRY |  | 02 | C044064 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5.8 miles of Henry County Route J20 (Salem Road) from Ash Avenue in the city of Hillsboro easterly | Pavement Improvement | 2009-06-08 | 2009-09-07 | 2009-12-01 | 2009-10-06 | 1138000 | 5.000
5297 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HOWARD |  | 04 | C045059 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5 miles of Howard County Route V26 (Jade Ave.) from Iowa Highway 9 north to Howard County Route A2 | Pavement Improvement | 2009-05-21 | 2009-05-26 | 2009-12-01 | 2009-07-01 | 960000 | 5.000
5298 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | IDA |  | 05 | C047045 | The project is located on Ida County Route (ICR) M15 (240th Street). Ida County is replacing the existing Portland Cement Concrete (PCC) roadway surface with a new PCC roadway surface which includes | Pavement Improvement | 2009-07-02 | 2009-08-03 | 2009-12-01 | 2010-03-31 | 500000 | 1.470
5299 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | IOWA |  | 03 | C048056 | This project will provide an improved driving surface and reduce future roadway maintenance on Iowa County Route F67 (325th St.) from Iowa County Route V52 (H Ave.) easterly to North Knoll Ridge St. i | Pavement Improvement | 2009-06-16 | 2009-06-18 | 2009-12-01 | 2010-09-16 | 773396 | 6.500
5300 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JACKSON |  | 01 | C049046 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 1.3 miles of Jackson County Route Y53 (Hurstville Road) from Pershing Road in the city of Maquoke | Pavement Improvement | 2009-07-20 | 2009-08-06 | 2009-12-01 | 2010-02-05 | 167439 | 2.600
5301 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JACKSON |  | 01 | C049047 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2.6 miles of Jackson County Route D55 (300th St.) from ¼ mile east of U.S. Highway 61 east to 400 | Pavement Improvement | 2009-07-20 | 2009-08-06 | 2009-12-01 | 2010-02-05 | 400000 | 2.500
5302 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JASPER |  | 03 | C050087 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5.2 miles of Jasper County Route T38 from Mahaska/Jasper County line north to the Skunk River Brid | Pavement Improvement | 2009-07-02 | 2009-09-14 | 2009-12-01 | 2011-02-21 | 850142 | 5.100
5303 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JEFFERSON |  | 02 | C051043 | This project will replace a narrow bridge with a new bridge. The bridge is on County Road V64/Douds Road over Lick Creek approximately 3 miles South of Libertyville. | Bridge Replacement | 2009-12-11 | 2010-04-12 | 2010-12-01 | 2010-10-26 | 347681 | 0.100
5304 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | C052090 | This project will reconstruct approximately 0.8 miles of Johnson County Route F12 (120th St.) and 1.1 miles of Iowa Highway 965 near the city of Swisher. County Route F12 will be rebuilt from 925 fee | Pavement Improvement | 2009-12-29 | 2010-04-19 | 2010-12-01 |  | 556302 | 0.600
5305 | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | C052093 | This project consists of applying a concrete overlay on Johnson County Route W64 (Oak Crest Hill Road) from the Washington/Johnson County line northerly to the south city limit of Hills (approximately | Pavement Improvement | 2009-12-14 | 2010-05-04 | 2010-12-01 |  | 556302 | 0.800
5306 | Underway | C220 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | C052094 | This project provides for construction of the 1.5 mile extension of Dubuque Street Trail along Dubuque Street (County Road W-66) from West Overlook Road northwest to 275th Street just southeast of th | Transportation Enhancements | 2009-08-17 | 2009-09-07 | 2009-12-01 |  | 252000 | 1.300
5307 | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | JONES |  | 01 | C053066 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Jones County Route E34 (Fairview Rd.) from Quaker Ln. (just east of the ci | Pavement Improvement | 2009-10-16 | 2010-04-08 | 2010-12-01 |  | 863137 | 2.800
5308 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | KEOKUK |  | 03 | C054082 | This project will improve drainage along and under Keokuk County Route V5G by replacing multiple pipe culverts under the 2.8 miles of roadway from Iowa Highway 149 to Iowa Highway 78 in the city of Ol | Pavement Improvement | 2009-08-24 | 2010-05-06 | 2010-12-01 | 2010-12-03 | 380278 | 11.200
5309 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | KOSSUTH |  | 04 | C055128 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 10 miles of Kossuth County Route R14 (240th Ave.) from U.S. Highway 18 (near the city of Wesley) n | Pavement Improvement | 2009-07-28 | 2009-08-03 | 2009-12-01 | 2009-10-07 | 1428688 | 11.000
5310 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | C057102 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Linn County Route W45 (Troy Mills Rd.) from just north of Linn County Rout | Pavement Improvement | 2009-05-20 | 2009-08-24 | 2009-12-01 | 2010-04-07 | 895052.04 | 2.700
5311 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | LOUISA |  | 02 | C058039 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 12.6 miles of Louisa County Route X99 from just east of the Iowa River Bridge (near the city of Wa | Pavement Improvement | 2009-07-02 | 2009-09-14 | 2009-12-01 | 2009-10-13 | 1300000 | 12.500
5312 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | LUCAS |  | 03 | C059045 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 0.9 miles of Albia Road (475th Lane) in the city of Chariton from S. 5th Street southeasterly to U | Pavement Improvement | 2009-10-21 | 2009-10-27 | 2009-12-01 | 2010-05-25 | 399000 | 1.000
5313 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MADISON |  | 04 | C061083 | This project will provide an improved driving surface by applying an asphalt overlay to various locations on Madison County Route G4R (Cumming Road) between Quail Ridge Trail (approximately 6 miles no | Pavement Improvement | 2009-06-03 | 2009-09-21 | 2009-12-01 | 2011-05-18 | 569170 | 3.500
5314 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MAHASKA |  | 03 | C062066 | This project will replace the existing deteriorating pavement with new concrete pavement on approximately 2.2 miles of Osburn Avenue from Iowa Highway 23 to Iowa Highway 92 in Mahaska County. The new | Pavement Improvement | 2009-06-02 | 2009-08-31 | 2009-12-01 | 2010-02-03 | 852647 | 2.100
5315 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARION |  | 03 | C063096 | This project will provide an improved driving surface by applying an asphalt overlay on Marion County Route G71 from Iowa Highway 5 southeasterly to the approximately ¼ mile north of 2nd Street in the | Pavement Improvement | 2009-05-01 | 2009-05-07 | 2009-12-01 | 2009-06-17 | 314043 | 5.000
5316 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARION |  | 03 | C063097 | This project will provide an improved driving surface by applying an asphalt overlay on Marion County Route G76 from 1.5 miles east of Marion County Route S45 (southeast of the city of Melcher-Dallas) | Pavement Improvement | 2009-05-01 | 2009-05-08 | 2009-12-01 | 2009-06-17 | 311651 | 1.500
5317 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARSHALL |  | 04 | C064109 | Marshall County will resurface 3.5 miles of County Road E-67 with new asphalt between Underwood and Yates Avenue west of the City of Gilman. This project will improve driving quality by providing a mo | Pavement Improvement | 2009-05-14 | 2009-05-25 | 2009-12-01 | 2009-08-03 | 781815.52 | 3.500
5318 | Completed | C220,C240 | Highway Infrastructure Investment Grant | IOWA | MILLS |  | 05 | C065074 | This project provides for reconstruction of two segments of the Wabash Trace Nature Trail through and near the cities of Silver City and Malvern both in Mills County. The first segment begins southea | Transportation Enhancements | 2010-03-09 | 2010-05-24 | 2010-12-01 | 2011-07-25 | 538338.52 | 2.770
5319 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MITCHELL |  | 04 | C066039 | Mitchell County will overlay 2 miles of County Road A-23 with new concrete between Walnut Avenue and Addison Avenue northeast of the City of McIntire. This project will improve driving quality and sig | Pavement Improvement | 2009-05-21 | 2009-09-14 | 2009-12-01 | 2009-12-28 | 400000 | 2.000
5320 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MONONA |  | 05 | C067062 | The project is located on Monona County Road (MCR) E60. Monona County is improving the existing gravel roadway with a drainage system and new gravel surface. The project is located approximately 3.6 | Pavement Improvement | 2009-05-26 | 2009-07-06 | 2009-12-01 | 2010-03-17 | 456691.22 | 1.700
5321 | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | MONROE |  | 03 | C068063 | Monroe County will widen and resurface 1.6 miles of County Road H-35 with new asphalt south of the City of Albia. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2009-06-16 | 2009-09-14 | 2009-12-01 | 2010-06-18 | 624000 | 1.600
5322 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONTGOMERY |  | 05 | C069039 | Montgomery County will overlay 1.7 miles of County Road H-54 with new concrete east of the City of Colburg to Iowa Highway 48. This project will improve driving quality and significantly extend the li | Pavement Improvement | 2009-11-23 | 2010-07-12 | 2010-12-01 | 2011-03-09 | 405610 | 2.200
5323 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MUSCATINE |  | 02 | C070049 | Muscatine County will resurface 2.5 miles of County Road F-70 with new asphalt between County Road X-54 and Iowa Highway 38 north of the City of Muscatine. Four inches of the existing asphalt road wil | Pavement Improvement | 2009-07-17 | 2009-10-26 | 2009-12-01 | 2009-10-28 | 733544 | 2.500
5324 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | PALO ALTO |  | 04 | C074092 | Palo Alto County will widen and resurface 2 miles of County Road N-20 with new asphalt between the northern city limits of Ruthven and the intersection of County Road B-25 and 355th Avenue. This proje | Pavement Improvement | 2009-05-20 | 2009-09-22 | 2009-12-01 | 2010-08-10 | 659874 | 2.000
5325 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | PLYMOUTH |  | 05 | C075120 | Plymouth County will resurface 3 miles of County Road C-12 with new asphalt between County Road K-22 and County Road K-30 east of the City of Craig. Three inches of the existing asphalt road will be r | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2009-12-01 | 2010-03-12 | 375000 | 3.000
5326 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | PLYMOUTH |  | 05 | C075121 | Plymouth County will resurface 1 mile of County Road K-30 with new asphalt between County Road C-12 and 100th Street north of the City of Craig. Three inches of the existing asphalt road will be recyc | Pavement Improvement | 2009-06-05 | 2009-06-01 | 2009-12-01 | 2010-03-12 | 125000 | 1.000
5327 | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | PLYMOUTH |  | 05 | C075122 | Plymouth County will replace 5.4 miles of County Road K-22 with new concrete between the Woodbury County border and County Road C-60 north of the City of Sioux City. This project will improve driving | Pavement Improvement | 2009-11-20 | 2010-04-07 | 2010-12-01 | 2011-02-24 | 1189278 | 5.500
5328 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | C077168 | Polk County will resurface 5.7 miles of Northwest/Northeast 118th Avenue with new asphalt between Northwest Sheldahl Drive and U.S. Highway 69 east of the City of Polk City. This project will improve | Pavement Improvement | 2009-05-06 | 2009-05-14 | 2009-12-01 | 2009-06-18 | 1950000 | 5.500
5329 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | POLK |  | 03 | C077169 | Polk County will resurface 3.5 miles of various city roads with new asphalt. Locations include Northwest 110th Avenue between Iowa Highway 17 and Northeast 121st Street northwest of the City of Des Mo | Pavement Improvement | 2009-05-06 | 2009-05-14 | 2009-12-01 | 2009-06-18 | 418779 | 3.500
5330 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | POWESHIEK |  | 03 | C079041 | Poweshiek County will resurface 2.7 miles of County Road F-62 with new asphalt between the Jasper County border and Iowa Highway 146 west of the City of Searsboro. Four inches of the existing asphalt | Pavement Improvement | 2009-07-06 | 2009-09-21 | 2009-12-01 | 2011-04-21 | 619700 | 3.000
5331 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | RINGGOLD |  | 05 | C080049 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road P64 over a tributary to Lotts Creek 3.7 miles Southwest of Kellerton. | Bridge Replacement | 2009-08-12 | 2009-08-14 | 2010-12-01 | 2010-05-06 | 312555 | 0.000
5332 | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | C082039 | Scott County will resurface 5.1 miles of County Road Y-48 with new asphalt between Iowa Highway 22 and County Road F-65 west of the City of Davenport. This project will improve driving quality by prov | Pavement Improvement | 2009-05-26 | 2009-06-18 | 2009-12-01 | 2010-09-02 | 2100000 | 4.000
5333 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | C082042 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road F33/St. Ann’s Road over Mason Creek approximately 3 miles Northwest of Long | Bridge Replacement | 2009-09-21 | 2009-10-02 | 2010-12-01 | 2010-09-16 | 299524.5 | 0.000
5334 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | C082044 | The project is for the replacement of a Reinforced Concrete Box (RCB) Culvert, Single Box, by Scott County. The existing RCB Culvert had deteriorated, and the structure no longer serves the drainage | New Bridge Construction | 2009-09-21 | 2009-09-26 | 2010-12-01 | 2011-09-01 | 134516 | 0.090
5335 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | C082046 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road Y48/Maysville Road over Hickory Creek approximately 1.5 miles Southeast of M | Bridge Replacement | 2009-09-28 | 2010-03-24 | 2010-06-01 | 2011-05-09 | 288203.93 | 0.020
5336 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SHELBY |  | 05 | C083046 | Shelby County will resurface 5.6 miles of County Road F-58 with new asphalt between Maple Road and County Road M-47 south of the City of Harlen. This project will improve driving quality by providing | Pavement Improvement | 2009-08-17 | 2009-08-24 | 2010-12-01 | 2010-12-14 | 1400000 | 5.600
5337 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SIOUX |  | 05 | C084130 | Sioux County will resurface 4.9 miles of County Road L-14 with new asphalt between U.S. Highway 18 and the Lyon County border north of the City of Boyden. Three inches of the existing asphalt road wil | Pavement Improvement | 2009-05-18 | 2009-07-27 | 2009-12-01 | 2009-12-18 | 985471.84 | 5.000
5338 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SIOUX |  | 05 | C084132 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Harrison Avenue over a small stream 1 mile east and 3.5 miles South of Maurice. | Bridge Replacement | 2009-05-18 | 2009-08-03 | 2009-12-01 | 2009-12-18 | 330396.12 | 0.010
5339 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY |  | 04 | C085102 | Story County will resurface 4 miles of County Road E-29 with new asphalt between U.S. Highway 65 and the Marshall County border north of the City of Colo. This project will improve driving quality by | Pavement Improvement | 2009-05-20 | 2009-07-20 | 2009-12-01 | 2009-09-17 | 858307 | 4.000
5340 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | TAMA |  | 03 | C086074 | Tama County will resurface 9.8 miles of various county roads south of the City of Tama with new asphalt. Locations include County Road E-69 between Iowa Highway 146 and U.S. Highway 63, and County Roa | Pavement Improvement | 2009-06-17 | 2009-08-03 | 2009-12-01 | 2011-04-05 | 966635.42 | 10.000
5341 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | TAYLOR |  | 05 | C087037 | This project will install longitudinal subdrains along both sides of the existing roadway for Taylor County Road N44 from the Missouri State Line north for 4.3 miles to Taylor County Road J55. The su | Pavement Improvement | 2010-01-12 | 2010-07-23 | 2010-12-01 | 2010-08-11 | 199866.48 | 3.500
5342 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | TAYLOR |  | 05 | C087038 | This project will install longitudinal subdrains along both sides of the existing roadway for Taylor County Road P14 from the Missouri State Line north for 2.7 miles to Taylor County Road J55 and on T | Pavement Improvement | 2010-01-12 | 2010-07-13 | 2010-12-01 | 2010-08-11 | 152496 | 3.500
5343 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | UNION |  | 05 | C088040 | Union County will resurface 3 miles of County Road P-33 with new asphalt between County Road H-17 and Adair-Union Street north of the City of Creston. This project will improve driving quality by prov | Pavement Improvement | 2009-05-12 | 2009-05-19 | 2009-12-01 | 2009-08-19 | 437751 | 3.000
5344 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | VAN BUREN |  | 02 | C089057 | Van Buren County will remove the top three inches of existing pavement on County Road V-64 and resurface it with new asphalt between Iowa Highway 16 and the Jefferson-Van Buren County line west of the | Pavement Improvement | 2009-05-14 | 2009-06-03 | 2009-12-01 | 2009-08-20 | 320993 | 3.400
5345 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WAPELLO |  | 02 | C090060 | Wapello County will resurface 3.8 miles of various county roads near the City of Ottumwa with new asphalt. Locations include County Road H-21 between Blackhawk Road and County Road H-27, and County Ro | Pavement Improvement | 2009-05-15 | 2009-05-08 | 2009-12-01 | 2009-09-16 | 423752 | 12.500
5346 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WARREN |  | 04 | C091081 | Warren County will resurface 3.2 miles of County Road S-23 with new asphalt between County Road G-24 and Iowa Highway 5 west of the City of Hartford. This project will improve driving quality by provi | Pavement Improvement | 2009-05-18 | 2009-06-08 | 2009-12-01 | 2009-10-28 | 576146 | 3.200
5347 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WASHINGTON |  | 02 | C092075 | Washington County will overlay 4.2 miles of County Road W-64 with new concrete between 160th Street and Iowa Highway 22 east of the City of Riverside. This project will improve driving quality and sig | Pavement Improvement | 2009-05-14 | 2009-08-24 | 2009-12-01 | 2009-09-28 | 732691 | 5.600
5348 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WEBSTER |  | 04 | C094082 | This project will repair a bridge, which is in poor condition, by replacing the bridge deck. The bridge is on County Road C66 over Lizard Creek 5 miles West of Clare. | Bridge Improvement | 2009-07-01 | 2009-07-20 | 2009-12-01 | 2010-02-11 | 350000 | 0.060
5349 | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | WEBSTER |  | 04 | C094083 | Webster County will resurface 2.4 miles of County Road D-14 with new asphalt between U.S. Highway 169 and County Road P-56 north of the City of Wahkonsa. This project will improve driving quality by p | Pavement Improvement | 2010-02-11 | 2010-05-26 | 2010-12-01 | 2011-03-24 | 934867 | 2.500
5350 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WINNEBAGO |  | 04 | C095055 | Winnebago County will resurface 3.7 miles of County Road R-60 with new asphalt between U.S. Highway 69 and the southern city limits of Scarville. This project will improve driving quality by providing | Pavement Improvement | 2009-05-13 | 2009-06-15 | 2009-12-01 | 2009-07-17 | 532664.81 | 3.700
5351 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WINNESHIEK |  | 04 | C096101 | Winneshiek County will overlay 2.2 miles of County Road V-68 with new concrete between the Fayette County border and Iowa Highway 24 in the City of Jackson Junction. This project will improve driving | Pavement Improvement | 2009-05-21 | 2009-05-28 | 2009-12-01 | 2010-11-12 | 664000 | 2.200
5352 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY |  | 05 | C097107 | This project will mill and place three and a half inches of hot-mix asphalt for 1.6 miles of Correctionville Road from Sioux City’s city limits to just past Buchanan Ave. The project will create a sm | Pavement Improvement | 2009-05-26 | 2009-07-14 | 2009-12-01 | 2010-09-27 | 626318.87 | 1.800
5353 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY |  | 05 | C097108 | This project will mill and place four inches of pavement on county road L-37 for approximately 10.7 miles from near Danbury, IA to county road D-38. The project will improve pavement condition and sa | Pavement Improvement | 2009-06-02 | 2009-08-24 | 2009-12-01 | 2010-09-27 | 500000 | 10.000
5354 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WORTH |  | 04 | C098050 | This project places a concrete overlay on a bridge deck to extend the service life of the bridge. The bridge is located on 410th Street over the Shell Rock River 1.5 miles east of Kensett. | Bridge Improvement | 2009-08-12 | 2010-04-14 | 2010-12-01 | 2010-07-07 | 48417.6 | 0.030
5355 | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WORTH |  | 04 | C098051 | This project places a concrete overlay on a bridge deck to extend the service life of the bridge. The bridge is located on 495th Street over the Shell Rock River approximately 1 mile West and 2.5 mil | Bridge Improvement | 2009-08-12 | 2010-04-14 | 2010-12-01 | 2010-07-07 | 32695.6 | 0.020
5356 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | SHAWNEE | TOPEKA | 02 | 0705215 | This project will plant wildflowers within KDOT R/W at the Topeka: I-70/KTA Interchange to provide beautification along I-70. | Transportation Enhancements | 2010-11-22 | 2010-11-22 | 2010-12-06 | 2010-11-22 | 14670.2
5357 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | 0706047 | This project will plant wildflowers within KDOT right-of-way at the I-70/I-435 interchange Kansas City and Edwardsville. | Transportation Enhancements | 2010-11-22 | 2010-11-23 | 2010-11-29 | 2010-11-23 | 16771.48
5358 | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | 1351209 | This project will reconstruct the I-135/KTA/47th St. interchange and 47th St from Broadway to Lulu St in the city of Wichita. This work will improve traffic capacity, operation and safety on these ro | Pavement Widening | 2009-08-20 | 2009-08-20 | 2011-02-24 |  | 16564397.77 | 0.001
5359 | Completed | C240,C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | 1351214 | This project repairs bridge expansion joints and provides a polymer overlay to bridges 0.22 and 0.23 miles north of Macart Road and the two bridges at I-135/Pawnee Avenue junction in the City of Wichi | Bridge Improvement | 2011-07-05 | 2011-07-05 | 2011-09-04 | 2011-10-13 | 983060.23
5360 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | 2351196 | This project will plant wildflowers within KDOT right-of-way at the I-235/K-96 interchange in Wichita. | Transportation Enhancements | 2010-12-16 | 2010-12-16 | 2010-12-23 | 2010-12-17 | 15959.97
5361 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | 4353359 | This project will widen and reconstruct Woodend Avenue to provide additional turn lanes in the city of Edwardsville in Wyandotte County. This work will improve traffic capacity, operations, and safe | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-09-14 | 2011-11-30 | 775000 | 0.001
5362 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | 4353360 | This project will plant wildflowers within KDOT R/W at the Lenexa: I-435/K-10 Interchange to provide beautification along I-435. | Transportation Enhancements | 2010-11-22 | 2010-11-23 | 2010-12-06 | 2010-11-24 | 27794.19
5363 | Completed | C240,C230 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | 4353363 | Ultrathin Bonded Asphalt Surface (UBAS) on driving lanes and conventional seal on shoulders. This project will include the interchange ramps and pavement markings. | Pavement Improvement | 2011-08-02 | 2011-08-02 | 2011-09-06 | 2011-09-19 | 1000000
5364 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | A004601 | This project provides traffic signals and intersection improvements to the US-54/167th Street intersection in the City of Goddard/Wichita in Sedgwick County – improving both traffic flow and safety. | Safety/Traffic Management | 2011-03-01 | 2011-03-01 | 2011-06-13 |  | 500000
5365 | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | RILEY |  | 02 | A041001 | The State will proceed with Right of Way & Utility Relocation activities and final plan development for this project. K-18 will be improved to a freeway section that will improve traffic capacity, op | Other | 2010-08-30 |  |  |  | 16200000 | 7.344
5366 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | KANSAS | RILEY |  | 02 | A041003 | This project will construct a 4-Lane Freeway Section on K-18 in Riley County with an interchange at K-114. This work will improve traffic capacity, operation and safety along K-18. | Pavement Widening | 2010-02-10 | 2010-02-10 | 2012-12-31 |  | 69598606.36 | 3.866
5367 | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | A100604 | This project will reconstruct 47th Street from Lulu Street to Hydraulic Avenue in the city of Wichita from a 4-lane to 5-lane roadway. This reconstruction will increase both capacity and safety relat | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2011-05-06 |  | 650000
5368 | Underway | C490 | OJT/SS | KANSAS | STATEWIDE |  |  | A116910 | This project will provide skill training for women and minorities in highway construction work in central Kansas for Federal Fiscal Year 2010. | Other | 2009-09-24 | 2009-09-24 |  |  | 224600
5369 | Underway | C220 | Highway Infrastructure Investment Grant | KANSAS | OSAGE |  | 02 | A120102 | This project will replace an abandoned RR bridge with a pedestrian bridge that is part of the KANZA Rails to Trails Conservancy trail network in Osage Co. This work will improve safety for trails use | Transportation Enhancements | 2010-06-01 | 2010-06-01 | 2010-10-19 |  | 901198.03 | 0.001
5370 | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | GOVE |  | 01 | A153401 | This project will replace the pavement on K-23, provide a 28 ft. roadway and replace guardrail as warranted to improve safety along K-23 in Gove County. | Pavement Improvement | 2009-02-23 | 2009-02-23 | 2010-09-06 |  | 4142957.06 | 8.000
5371 | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | GOVE |  | 01 | A153402 | This project will replace the pavement on K-23, provide a 28 ft. roadway and replace guardrail as warranted to improve safety along K-23 in Gove County. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-08-15 | 2010-08-14 | 4813954.26 | 9.600
5372 | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | STATEWIDE |  |  | A181001 | The project will improve defects in approximately 42 bridges along the NKCR route in northwest Kansas and rehabilitate the approach track to these bridges as warranted. | Safety/Traffic Management | 2010-03-15 | 2010-04-19 | 2011-01-07 | 2012-01-23 | 343825.05
5373 | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | REPUBLIC |  | 01 | A181201 | This project construct 2000 ft. of siding and a new switch into the Nesika Energy Plant in the city of Scandia that will enable the Nesika Energy Plant to ship by rail and access national markets for | Safety/Traffic Management | 2010-04-19 | 2010-04-19 | 2011-02-09 | 2010-12-22 | 371000
5374 | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | A181401 | This project will add 7,200 ft. of rail siding/pass track that will improve rail traffic flow and increase operation efficiency for elevators outside the city of Wichita. | Safety/Traffic Management | 2010-04-26 | 2010-04-26 | 2011-04-07 | 2010-12-10 | 967820
5375 | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | RENO |  | 01 | A183901 | This project will construct storage tracks at the Siemens Nachelle Facility in the city of Hutchinson that will enable the company to ship by rail and provide for a more efficient operation. | Safety/Traffic Management | 2010-03-03 | 2010-04-19 | 2012-02-22 |  | 844800
5376 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | CHEROKEE |  | 02 | C000501 | County road surfacing improvements in Cherokee county on hwy 66 from Riverton south to Lowell. | Pavement Improvement | 2010-07-31 | 2010-07-31 | 2011-09-05 | 2011-03-31 | 227294.71
5377 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | COMANCHE |  | 01 | C421801 | This project will replace a bridge on County Road 155, 1.0 mile West of Coldwater in Comanche County - improving structural and/or safety concerns. | Bridge Replacement | 2009-11-01 | 2009-11-01 | 2010-05-05 | 2010-06-12 | 385969.78
5378 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | COWLEY |  | 04 | C422001 | This project will provide a 2 inch asphalt overlay on County Road 164 from Udall to County Road 18 in Cowley County, improving rideability and surface condition. | Pavement Improvement | 2009-08-14 | 2009-08-14 | 2009-11-03 | 2009-10-30 | 877500
5379 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ELLIS |  | 01 | C422801 | This project will replace a bridge 5.6 miles South and 0.8 miles West of the city of Walker in Ellis County - improving structural and/or safety concerns. | Bridge Replacement | 2009-10-28 | 2009-11-16 | 2010-05-24 | 2010-06-30 | 475933.3
5380 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | C424801 | This project will replace a bridge on 143rd Street over Captain Creek in Johnson County - improving structural and/or safety concerns. | Bridge Replacement | 2010-03-01 | 2010-03-01 | 2010-09-27 | 2011-10-08 | 701636.03
5381 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | DICKINSON |  | 01 | C447801 | This project will replace a bridge on Old US Highway 40, 3.5 miles West of Highway 15 in Dickinson County - improving structural and/or safety concerns. | Pavement Improvement | 2010-01-01 | 2010-01-11 | 2010-11-05 | 2011-04-30 | 644400
5382 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | SHAWNEE | TOPEKA | 02 | C448901 | This project is a storm sewer and culvert project on NorthWest 46th Street Between US Highway 75 and NorthWest Fielding Road in Shawnee County that will improve drainage. | Pavement Widening | 2010-03-01 | 2010-03-10 | 2010-11-05 |  | 2170228.23
5383 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ATCHISON |  | 02 | C453901 | This project will replace a bridge 4.0 miles North and 4.4 miles East of the city of Shannon in Atchison County - improving structural and/or safety concerns. | Bridge Replacement | 2009-11-18 | 2009-11-18 | 2010-09-10 | 2010-09-15 | 216000
5384 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | WABAUNSEE |  | 01 | C454901 | This project will replace a bridge 5.0 miles East and 0.9 miles North of Eskridge in Wabaunsee County - improving structural and/or safety concerns. | Bridge Replacement | 2010-03-30 | 2010-03-30 | 2011-06-07 | 2010-12-17 | 332415.01
5385 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | C455101 | This project will redeck a bridge 1.4 miles East of the city of Jarbalo in Leavenworth County - improving surface conditions. | Bridge Replacement | 2009-09-01 | 2009-09-01 | 2011-02-08 | 2010-04-30 | 389138.53
5386 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BARBER |  | 01 | C455201 | This project will replace a bridge 2.0 miles East of the city of Hazelton on Rural Secondary Route 1381 - improving structural and/or safety concerns. | Bridge Replacement | 2009-11-02 | 2009-11-19 | 2011-04-12 | 2010-07-20 | 292272
5387 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | POTTAWATOMIE |  | 02 | C455301 | This project will rehabilitate a bridge 2.0 miles North of the city of Manhattan Over the Big Blue River in Pottawatomie County - improving structural and/or safety concerns. | Bridge Replacement | 2009-12-17 | 2009-12-17 | 2011-04-12 | 2010-09-30 | 472662.1
5388 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ROOKS |  | 01 | C455401 | This project resurfaces 2.6 Miles of Rural Secondary Route 916 and 1729 in the City of Woodston in Rooks County - improving surface conditions. | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2011-02-08 | 2009-12-31 | 310000
5389 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | HARPER |  | 04 | C455501 | This project will provide a 4-inch overlay on NE 160th Road (Rural Secondary Route 641) near the city of Conway Springs in Harper County - improving surface conditions. | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2011-03-08 | 2010-07-09 | 510000
5390 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | KINGMAN |  | 04 | C455601 | This project will provide a 2-inch overlay on Rural Secondary Route 1704 (vicinity of US-54 South) in Kingman County - improving surface conditions. | Pavement Improvement | 2009-11-23 | 2010-05-01 | 2011-04-12 |  | 369381.39
5391 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | RICE |  | 01 | C455701 | This project will provide a 2-inch mill (removal of exiting pavement) and asphalt overlay on Main Street ( Rural Secondary Route 983) in the city of Bushton in Rice County - improving surface conditio | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2011-05-09 | 2010-05-14 | 346547.58
5392 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | BUTLER |  | 04 | C455801 | This project will rehabilitate a bridge 1.5 miles West of the city of Benton and 1.7 miles North over the White Water Creek in Butler County - improving structural and/or safety concerns. | Bridge Replacement | 2010-02-17 | 2010-02-17 | 2011-06-07 |  | 687750
5393 | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | RENO |  | 01 | C455901 | This project will provide an asphalt overlay on 4th Avenue (Rural Secondary Route-636) from K-14 E to K-96 4th Avenue Interchange in Hutchinson in Reno County - improving surface conditions. | Pavement Improvement | 2009-12-02 | 2010-06-18 | 2011-04-12 |  | 517593
5394 | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | HARVEY |  | 04 | C456001 | This project will replace a bridge on Kansas Avenue, 1.1 miles North and 0.5 miles East of Newton, in Harvey County - improving structural and/or safety concerns. | Bridge Replacement | 2010-04-16 | 2010-04-16 | 2011-07-11 |  | 575000
5395 | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | BARTON |  | 01 | C456101 | This project will provide a maintenance resurfacing of Rural Secondary Route 462 from Great Bend West city limits West to NorthWest 60th Avenue in Great Bends in Barton County - improving surface cond | Pavement Improvement | 2010-03-08 | 2010-03-30 | 2011-03-08 |  | 560000
5396 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ANDERSON |  | 02 | C456201 | This project will rehabilitate a bridge on Rural Secondary Route1389 4.0 miles South and 1.7 miles East of the city of Harris in Anderson County - improving structural and/or safety concerns. | Bridge Improvement | 2009-07-31 | 2009-07-31 | 2011-05-17 | 2009-12-31 | 54022.05
5397 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | CHAUTAUQUA |  | 04 | C456301 | This project will provide a 2.5-inch asphalt overlay on Independence Road (Rural Secondary Route 97) for 3.5 Miles in Chautauqua County - improving surface conditions. | Pavement Improvement | 2009-08-27 |  | 2011-01-04 | 2010-12-16 | 413353.05
5398 | Completed | C250,C200 | Highway Infrastructure Investment Grant | KANSAS | CHEROKEE |  | 02 | C456401 | This project will provide a 2-inch asphalt surfacing for 5 miles on Rural Secondary Route 1791 in Cherokee County from US-400 East to the Missouri State - improving surface conditions. | Pavement Improvement | 2010-07-31 | 2010-07-31 | 2011-09-05 | 2011-03-31 | 382429.1
5399 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | FRANKLIN |  | 02 | C456501 | This project will provide a 2-inch asphalt overlay on John Brown Road (Rural Secondary Route 1066/259) Between Kentucky Road and Florida in Franklin County - improving surface conditions. | Pavement Improvement | 2009-08-27 | 2009-08-27 | 2011-01-04 | 2010-04-09 | 481205.76
5400 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | GREENWOOD |  | 01 | C456601 | This project will provide a 2-inch asphalt overlay on Rural Secondary Route 291 from the city of Hamilton to the city of Virgil in Greenwood County - improving surface conditions. | Pavement Improvement | 2009-10-22 | 2009-10-22 | 2011-01-04 | 2009-11-06 | 490000
5401 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ELK |  | 04 | C456701 | This project will provide an asphalt resurfacing of Kansas Street in the city of Longton from US Highway 160 to 6th Street - improving surface conditions. | Pavement Improvement | 2009-08-07 | 2009-11-11 | 2011-01-04 | 2010-07-29 | 104048.15
5402 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | LINCOLN |  | 01 | C456801 | This project will provide grading and drainage structure work on Rural Secondary Route 394 (3.5 miles North of K-18 North of the city of Beverly) in Lincoln County - improving structural and drainage | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-04-12 | 2010-05-27 | 88594.27
5403 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ELLSWORTH |  | 01 | C456901 | This project will provide an asphalt overlay on Low Road from the city of Ellsworth to the city of Kanopolis in Ellsworth County - improving surface conditions. | Pavement Improvement | 2010-01-11 | 2010-01-11 | 2011-03-08 | 2010-07-09 | 493000
5404 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | MORRIS |  | 01 | C457001 | This project will provide a bridge rehabilitation (to include abutment, deck repair, and patching on the Bridge Over Rock Creek, 0.3 Miles North of the city of Dunlap, in Morris County - improving sur | Bridge Replacement | 2010-03-11 | 2010-03-11 | 2011-04-12 | 2010-12-09 | 218500
5405 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | MARION |  | 01 | C457101 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on Cedar Street from Hudson North to US-56 in the city of Marion in Marion County - improving surface conditions. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2011-05-09 | 2010-07-29 | 160433.74
5406 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | MITCHELL |  | 01 | C457201 | This project will provide crack repair and an asphalt overlay of Rural Secondary Routes 466 and 1029 south of the city of Glen Elder - improving surface conditions. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2011-02-08 | 2010-06-02 | 443749.74
5407 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | WASHINGTON |  | 01 | C457301 | This project will provide grading and resurfacing of Rural Secondary Route 1100 through the city of Hanover from K-234 in Washington County - improving surface deficiencies and conditions. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2011-04-12 | 2010-12-07 | 351000
5408 | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | SALINE |  | 01 | C457401 | This project will replace a bridge on Kipp Road 0.1 miles North and 0.5 miles East of the city of Kipp in Saline County - improving structural and/or safety concerns. | Bridge Replacement | 2010-01-01 | 2010-02-01 | 2011-03-08 |  | 315000
5409 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | HAMILTON |  | 01 | C457501 | This project will provide a 3 inch overlay for 2 miles of Rural Secondary Road 308 from US Highway 50 south for 2 miles in Hamilton County -- improving surface conditions. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2011-09-05 | 2010-09-10 | 359303.18
5410 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | GRANT |  | 01 | C457601 | This project will provide surfacing work and railroad crossing improvements in the city of Ulysses on US-160 from the railroad tracks east of K-25 - improving safety and surfacing conditions. | Safety/Traffic Management | 2010-05-27 | 2010-05-27 | 2011-07-11 |  | 478489
5411 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | SEWARD |  | 01 | C457701 | This project will provide turn lanes for US-54 Sallie Road and US-83/Sallie Road in the city of Liberal in Seward County - improving safety. | Pavement Improvement | 2010-07-01 | 2010-07-01 | 2011-06-07 |  | 366179
5412 | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | STANTON |  | 01 | C457801 | This project will provide a 3-inch asphalt overlay on Rural Secondary Route 1664 in Stanton County - improving surface conditions. | Pavement Improvement | 2010-09-13 | 2010-09-13 | 2010-10-25 |  | 448000
5413 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | SCOTT |  | 01 | C457901 | This project will provide a 4-inch overlay of Federal Aid Secondary route 1898 2 miles West of K-95 Highway in Scott County - improving surface conditions. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2011-02-08 | 2009-11-23 | 453333.41
5414 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | NEOSHO |  | 02 | C458001 | This project will provide grading, surfacing, and bridge work on Rural Secondary Route 168 East of Shaw Road for 3.5 miles in Neosho County - improving surface and structural conditions. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2011-05-09 |  | 500000
5415 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | C458101 | This project will provide milling and asphalt overlay on Rock Road from Oak Knoll 5.5 miles North of 63rd Street South in Wichita area in Sedgwick County - improving surface conditions. | Pavement Improvement | 2010-05-20 | 2010-05-20 | 2011-04-12 | 2011-01-31 | 1335163.31
5416 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | C458401 | This project will provide a mill and overlay to 295th Street in Sedgwick County west from 21st Street to 61st Street north - improving surface condition | Pavement Improvement | 2010-05-20 | 2010-06-14 | 2011-09-06 | 2011-02-04 | 698414.37
5417 | Underway | C490 | OJT/SS | KANSAS | STATEWIDE |  |  | K507010 | This project will provide skill training for women and minorities in highway construction work in northeast Kansas for Federal Fiscal Year 2010. | Other | 2009-11-03 | 2009-11-03 |  |  | 200402
5418 | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | K825107 | This project will add two lanes, reconstruct the 95th Street interchange and add noise walls to selected section in the city of Overland Park. This work will improve traffic capacity, operation and s | Pavement Widening | 2009-06-05 | 2009-06-05 | 2012-01-10 |  | 29793303.63 | 1.841
5419 | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | K825111 | This project will add two lanes & reconstruct US-69 and widen I-35 in the city of Overland Park. This work will improve traffic capacity, operation and safety on US-69 and I-35. | Pavement Widening | 2001-06-26 | 2001-06-26 | 2012-01-11 |  | 55461425.11 | 1.137
5420 | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | MCPHERSON |  | 01 | K825301 | This project will construct a 4-Lane partial access controlled improvement with a bypass at the city of Inman. This work will improve traffic capacity, operation and safety along K-61. | Pavement Widening | 2009-05-06 | 2009-05-06 | 2011-11-23 |  | 33111588.91 | 7.430
5421 | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | MCPHERSON |  | 01 | K825302 | This project will construct a 4-Lane partial access controlled improvement. This work will improve traffic capacity, operation and safety along K-61. | Pavement Widening | 2009-05-06 | 2009-05-06 | 2011-11-23 |  | 33068299.42 | 7.060
5422 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | K921806 | This project will extend operation of the Operation Green Light System to improve intersection traffic signal coordination on regional arterial routes in the bi-state Kansas City Metropolitan area. I | Other | 2009-07-28 | 2009-07-28 | 2011-07-04 |  | 950000
5423 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N037301 | This project will widen College Blvd from 4 to 6 lanes from Pflumm Road to US-69 in Overland Park in Johnson County - improving both capacity and safety. | Pavement Widening | 2009-06-25 | 2009-06-25 | 2009-09-08 | 2010-11-24 | 1000000
5424 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | BUTLER | WICHITA | 04 | N039001 | This project will improve Andover Road to 5 lanes with a center turn lane, curb and gutter, and a 10-ft bide/ped sidewalk from Harry Street to 1100 Feet South of US-54 in the city of Andover in Butler | Pavement Widening | 2009-09-18 | 2009-09-18 | 2010-07-09 |  | 1234800
5425 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N046701 | This project will widen 87th Street from 4 to 6 lanes from Renner Blvd. to Ridgeview Road in the city of Lenexa in Johnson County - improving capacity and safety. | Pavement Widening | 2009-12-07 | 2009-12-15 | 2010-09-10 |  | 3000000
5426 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N047801 | This project will reconstruct the existing 127th Street from 2 lanes to 4 lanes from Mur-Len to Black Bob in the city of Olathe in Johnson County - improving both capacity and safety. | Pavement Widening | 2010-02-16 | 2010-02-16 | 2011-02-03 |  | 3500000
5427 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N047901 | This project will remove and replace curb and sidewalks, mill and overlay, and replace traffic loops on 103rd Road from State Line Road to Mission Road in the city of Leawood in Johnson County - impro | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2011-09-05 |  | 925305.34
5428 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N048001 | This project will convert 4-lane cross section to 3-lane, install sidewalks & curbs, mill and resurface Roe Avenue from West 63rd Street North to Shawnee Mission Parkway in the city of Mission in John | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-06-07 |  | 921921
5429 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N048101 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on College Blvd From Benson Street to Nall Avenue in the city of Overland Park in Johnson County - improving surface | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2011-03-08 |  | 2800000
5430 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N048201 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on Merriam Drive from Johnson Drive to Shawnee Mission Parkway in the city of Merriam in Johnson County -- improving | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2011-09-05 |  | 150000
5431 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N048301 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on Merriam Drive From 57th Street to Antioch Road in the city of Merriam in Johnson County -- improving surface cond | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2011-09-05 | 2011-05-27 | 245294.56
5432 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | N048501 | This project will remove and replace curbs, inlets, guardrails, concrete medians and rehabilitate the pavement on State Avenue from 69th Street to 47th Street - improving surface conditions, drainage, | Pavement Improvement | 2010-01-19 | 2010-03-15 | 2011-05-09 |  | 4239055.77
5433 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N048601 | This project will replace the Ford Street Bridge, made roadway improvements, and provide pedestrian sidewalks in the city of Valley Center in Sedgwick County - improving structural and safety concerns | Bridge Replacement | 2010-10-04 | 2010-10-04 | 2011-06-07 |  | 838604.65
5434 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N048701 | This project will replace 148-ft bridge with flood wall across Chisholm Creek N of 49th Street N of Broadway Avenue in the city of Park city in Sedgwick County. | Bridge Replacement | 2010-02-02 | 2010-02-04 | 2011-05-09 | 2011-05-12 | 1297647.96
5435 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N048801 | This project will provide a full-depth reconstruction of the roadway to the bottom of the base, adding 7 inches of pavement, and striping of West Grand Ave. from Meridian Ave. to North Main Street in | Pavement Improvement | 2009-08-12 | 2010-04-02 | 2011-05-09 |  | 707659.82
5436 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | N049001 | This is a roadway reconstruction project with curb and gutter, storm drainage, and sidewalks on South 138th Street From Metro Avenue North to Kansas in the city of Bonner Springs in Wyandotte County - | New Construction | 2010-04-01 | 2010-04-01 | 2011-05-09 | 2010-07-31 | 145920.92
5437 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N049101 | This project will provide improvements (signals, raised medians, markings, etc.) to the existing Intersection of US56 and Old 56 Highway in the city of Gardner in Johnson County - improving safety. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-05-09 |  | 414537.49
5438 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N049701 | This project will provide a mill (removal of existing pavement) and overlay of Broadway-Central to 12th Street in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2011-04-25 | 2011-02-28 | 433349
5439 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N049801 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on 55th Street from Merriam Drive to Switzer Road in the city of Merriam in Johnson County -- improving surface con | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2011-09-05 | 2011-05-27 | 50000
5440 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N049901 | This project will resurface Madison Avenue Between K-15 and Rock Road in the city of Derby in Sedgwick County - improving surface conditions. | Pavement Improvement | 2010-05-05 | 2010-05-05 | 2011-03-08 | 2011-01-31 | 367517.87
5441 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N050001 | This project will provide concrete pavement replacement on Hillside from 9th Street to 12 Street in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 2009-12-01 | 2009-12-01 | 2011-04-25 | 2011-02-28 | 758347
5442 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N050101 | This project will provide concrete pavement replacement on Washington from 1st Street to Central Avenue in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 2009-12-01 | 2010-01-11 | 2011-04-25 | 2011-02-28 | 412406
5443 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N050201 | This project will reconstruct the existing 2-lane asphalt mat to a 5-lane road (including sidewalks, signals, and drainage) on Maize Road from Pawnee Avenue to Kellogg in the city of Wichita in Sedgwi | New Construction | 2010-02-01 | 2010-02-01 | 2011-06-08 |  | 3324598
5444 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N050301 | This project will reconstruct the existing 2-lane facility to a 3-lane road (including sidewalks and drainage) on Hydraulic Avenue from Harry Street to Kellogg in city of Wichita in Sedgwick County - | New Construction | 2010-02-02 | 2010-02-02 | 2011-06-06 |  | 2724651
5445 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N050401 | This project will provide a mill (removal of existing pavement) and overlay (to include curbs, sidewalks, ADA ramps) on Nieman Road from 59th Street to Shawnee Mission Parkway in the city of Shawnee i | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2011-05-11 |  | 227151.54
5446 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N050501 | This project will provide a mill (removal of existing pavement) and overlay (to include curbs, sidewalks, ADA ramps, repairing bridge approaches on 83rd Street from Hedge Lane Terrace to Monticello Te | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2011-05-11 |  | 158560.64
5447 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N050601 | This project will provide a mill (removal of existing pavement) and overlay (to include curbs, sidewalks, ADA ramps) on Quivira Road From 64th Street to 77th Street in the city of Shawnee in Johnson | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2011-05-11 |  | 642641.24
5448 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N051001 | This project will provide a mill (removal of existing pavement) and overlay on Woodlawn Avenue from Harry Street to Lincoln Street in the city of Wichita in Sedgwick County - improving surface conditi | Pavement Improvement | 2011-03-19 | 2011-03-19 | 2012-04-18 |  | 150000
5449 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N051101 | This project provides one mile of surfacing overlay to 13th Street from Maize Road to Tyler Road in the city of Wichita in Sedgwick County – improving ride. | Pavement Improvement | 2011-07-05 | 2011-07-05 | 2011-09-15 |  | 250000
5450 | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N051401 | This project will be providing surfacing improvements to Harry Street from Greenwich Road to 127th Street in the City of Wichita -- improving rideability and safety. | New Construction | 2010-05-10 | 2010-05-10 | 2011-09-05 |  | 999836.86
5451 | Underway | C220 | Highway Infrastructure Investment Grant | KANSAS | COWLEY |  | 04 | T028301 | This project will construct a pedestrian/bike path in Arkansas City along the levee from Paris Park to S. Summit and ACPC Park. | Transportation Enhancements | 2010-04-04 | 2010-04-04 | 2011-12-12 |  | 1500000
5452 | Underway | C220 | Highway Infrastructure Investment Grant | KANSAS | SHAWNEE | TOPEKA | 02 | T032301 | This project will construct a ten-foot bike/pedestrian path on the Landon Trail from 26th Street to 45th Street in the city of Topeka, Kansas. | Transportation Enhancements | 2011-03-15 | 2011-03-15 | 2011-08-25 |  | 780302.92
5453 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | FORD |  | 01 | T032501 | This project will construct a pedestrian/bike path along US-50 from 14th Street East to 6th Avenue in Dodge City in Ford County. | Transportation Enhancements | 2010-05-14 | 2010-05-14 | 2011-04-25 | 2011-05-25 | 373703.8
5454 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | NEOSHO |  | 02 | T033101 | This project will provide improvements to downtown Erie, KS along Main St from Fourth St, north to State St, then west on State St to US Highway 59, to include brick paver accents, curb and gutter, li | Transportation Enhancements | 2009-10-16 | 2009-10-16 | 2010-11-03 | 2011-02-28 | 618985.5
5455 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | GREENWOOD |  | 04 | T033401 | Restore part of the interior and exterior and establish a transportation museum/welcome center in the former bus depot of the Greenwood Hotel at 300 N Main | Transportation Enhancements | 2009-09-10 | 2009-09-10 | 2011-01-04 | 2011-09-16 | 1246246.43
5456 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | FRANKLIN |  | 02 | T033801 | This project will rehabilitate six railroad trestles, in various stages of disrepair, on the Midland Railway track located between Montana and Pawnee Roads in Franklin County. | Transportation Enhancements | 2010-02-03 | 2010-02-03 | 2010-10-04 | 2010-12-23 | 291760
5457 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | DOUGLAS | LAWRENCE | 03 | T033901 | This project will remove an existing asphalt overlay, provide restoration of historic brick streets and reconstruction of four intersections on New York Street from 9th Street to 12th Street in Lawren | Transportation Enhancements | 2009-12-21 | 2009-12-21 | 2010-10-04 | 2010-10-31 | 674778.32
5458 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | RILEY |  | 02 | T034001 | Restore portions of interior of the historic Isaac Goodnow house in Manhattan, KS including stabilization work on the stairs & interior walls & surface restoration with historically appropriate plaste | Transportation Enhancements | 2009-11-19 | 2009-11-19 | 2010-10-04 | 2011-06-23 | 113519
5459 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | RICE |  | 01 | T034101 | This project will install 2 brick masonry Welcome Portal Signs on the north & south entrances to the city on Broadway (K-14, K-96) with landscaping & a concrete walkway along the west side of Broadway | Transportation Enhancements | 2010-04-09 | 2010-04-09 | 2010-12-02 | 2010-09-22 | 69390
5460 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | STEVENS |  | 01 | T034201 | Project to provide new sidewalks w/ brick pavers, lighting, raised planters, ADA ramps, crosswalks, landscaping, irrigation, fence, benches & trash cans along Main St (US Hwy 56) from 5th to 7th St & | Transportation Enhancements | 2009-11-20 | 2009-11-20 | 2010-10-04 | 2010-11-26 | 1208858.41 | 0.001
5461 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | T034401 | This project will provide streetscape improvements from the Kansas Highway 7 off ramp, along Front Street (Kansas Highway 32) to Elm Street, in Bonner Springs, Kansas, and will include decorative stre | Transportation Enhancements | 2009-12-14 | 2009-12-14 | 2010-11-03 | 2011-03-04 | 226056.5
5462 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | MIAMI |  | 02 | T034501 | Project will include concrete & concrete paver sidewalk surface w/ retaining wall, trash cans, bike rack, lighting, signing, pavement markings and landscape improvements to downtown Osawatomie, KS alo | Transportation Enhancements | 2010-01-14 | 2010-01-14 | 2010-10-04 | 2010-11-17 | 649940
5463 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | FRANKLIN |  | 02 | T034601 | This project will provide lighting along the Prairie Spirit Rail Trail between 5th and 23rd Streets a distance of up to approximately 11,300 linear feet, in Ottawa, KS, with the installation of L.E.D | Transportation Enhancements | 2010-02-08 | 2010-02-08 | 2010-11-03 | 2010-08-02 | 153500
5464 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | DOUGLAS | LAWRENCE | 03 | T034701 | This project will remove an existing six-foot asphalt path and construct a ten-foot concrete path on the south side of Clinton Parkway from east of Wakarusa Drive to K-10 highway in Lawrence, Kansas. | Transportation Enhancements | 2009-12-18 | 2009-12-18 | 2010-10-04 | 2010-11-23 | 800750
5465 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | T034801 | This project will construct a concrete ped/bike path from 111th St, along the Mulvane Sports Complex (MSC), then connect to existing path & another path section from 111th St south along Webb Road to | Transportation Enhancements | 2009-10-19 | 2009-10-19 | 2010-10-04 | 2010-04-07 | 158485.69
5466 | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | T035001 | This project will construct a 1.3 mile extension of the South Indian Creek Trail, from Southdowns Park, to Hampton Park & an extension of 159th St trail to connect to Chisholm Trail Jr High, & include | Transportation Enhancements | 2010-01-26 | 2010-01-26 | 2010-12-02 | 2010-12-28 | 569445.55
5467 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | HARVEY |  | 04 | U000401 | This project will provide resurface and rehabilitation on the Main Street Bridge in Halstead in Harvey County - improving structural and surface conditions. | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2010-07-12 | 2010-07-08 | 323557.65
5468 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | DOUGLAS | LAWRENCE | 02 | U204101 | This project will be a reconstruction of the Intersection of North 2nd Street and Locust Street in the City of Lawrence in Douglas County - improving surface condition and safety. | Safety/Traffic Management | 2009-07-20 | 2009-07-28 | 2010-10-13 |  | 2000000
5469 | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | U214201 | This project will remove and replace concrete approach lanes, provide a mill (removal of existing pavement) and overlay, and make ADA modifications on US-56 to 47th Street on US-169 (Rainbow BLVD) in | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-06-01 | 2010-09-30 | 1204006.53
5470 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | U223201 | This project will provide a variable mill (removal of existing pavement) and overlay on RS-348 (Nelson/ West 8th Street) From RailRoad to Morgan Street in the city of Edgerton in Johnson County - impr | Pavement Improvement | 2009-10-22 | 2009-10-24 | 2011-03-08 | 2010-03-12 | 139352.07
5471 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | U223301 | This project will provide a 2-inch mill (removal of existing pavement) and overlay (to include signage and markings) on Kill Creek Road (RS-346) from 83rd to K-10 in the city of Desoto in Johnson Coun | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2011-04-12 | 2010-07-28 | 330102.09
5472 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223401 | This project will provide a surface overlay, aggregate shoulders, pavement markings, storm sewer improvements on 147th Street from South of Cottonwood Drive North to 4H Road in the city of Lansing in | Pavement Improvement | 2009-10-01 | 2009-10-01 | 2011-03-08 | 2011-03-31 | 231528.6
5473 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223501 | This project will provide a pedestrian signal on US Highway 24 at NorthStar Drive in the city of Tonganoxie in Leavenworth County - improving safety. | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2011-02-08 | 2010-08-31 | 23800
5474 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | JEFFERSON |  | 02 | U223601 | This project will provide an overlay to Jefferson Street from Walnut to City Limits in the city of Oskaloosa in Jefferson County - improving surface conditions. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2009-11-09 | 2009-11-03 | 30801.32
5475 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | DONIPHAN |  | 02 | U223701 | This project will provide surfacing and culvert work (replacing the Reinforced Concrete Bridge) on Old US-36 (RS-2128) just west of Elm Street in the city of Highland in Doniphan County - improving su | Pavement Improvement | 2009-11-18 | 2009-11-18 | 2011-04-12 | 2010-07-31 | 208726.54
5476 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223901 | This project will provide storm sewer improvements on 4th Street at K-7/73and Spruce K-92 in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2011-04-12 | 2011-07-31 | 226263.56
5477 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U224001 | This project will provide storm sewer improvements on 5th Ave and Doniphan in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2011-04-12 | 2011-03-31 | 89586
5478 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U224101 | This project will provide storm sewer improvements on 10th Street and Wellington in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2011-04-12 | 2011-03-31 | 124435
5479 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | POTTAWATOMIE |  | 02 | U224201 | This project will provide realignment of the intersection, surfacing, adding double left-turn lanes, and upgrading the traffic signals at the Intersection of US 24 and McCall Road in the city of Manha | Safety/Traffic Management | 2010-02-15 | 2010-02-15 | 2011-06-13 |  | 1000000
5480 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | RUSSELL |  | 01 | U224301 | This project will provide a reconstruction of US 281 Highway (Fossil Street) from East 9th to Union Pacific RR in the city of Russell in Russell County - improving surface conditions. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-04-12 | 2011-03-17 | 291438.36
5481 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | WALLACE |  | 01 | U224401 | This project will provide a mill (removal of existing pavement) and overlay on Highway K-27 from North Front Street to Third Street in the city of Sharon Springs in Wallace County - improving surface | Pavement Improvement | 2010-05-06 | 2010-05-31 | 2011-04-12 | 2010-06-24 | 120555.18
5482 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | PAWNEE |  | 01 | U224501 | This project will provide a 1-inch mill (removal of existing pavement) and 2 inch overlay on Northeast Trail Street from the US-56 junction east to 11th Street in the city of Larned in Pawnee County - | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2011-07-11 | 2011-04-05 | 209947.62
5483 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BARTON |  | 01 | U224601 | This project will provide grading and concrete pavement surfacing on US 281 (Main Street) from 3rd Street to the RailRoad Tracks in the city of Hoisington in Barton County - improving surface conditio | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2011-07-11 | 2010-12-16 | 476588.21 | 0.234
5484 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | RENO |  | 01 | U224701 | This project will provide a bridge replacement on 4th Ave. over Monroe Street in the city of Hutchinson in Reno County - improving structural concerns. | Bridge Replacement | 2010-02-01 | 2010-03-08 | 2011-05-09 | 2011-02-15 | 480558.62
5485 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | BARTON |  | 01 | U224801 | This project will provide a reconstruction of McKinley Street in the city of Great Bends in Barton County - improving structural and surface conditions. | Pavement Improvement | 2010-02-15 | 2010-03-22 | 2011-05-09 |  | 488000
5486 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | PRATT |  | 01 | U224901 | This project will provide a 4-inch mill (removal of existing pavement) and overlay between the railroad crossing at US-281 and Maple Street and the north city limits of the city of Pratt in Pratt Coun | Pavement Improvement | 2010-01-21 | 2010-03-20 | 2011-06-06 | 2010-05-21 | 122672.08
5487 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | BUTLER |  | 04 | U225001 | This project will provide an asphalt overlay on 6th Avenue and Boyer Avenue from K-254 to Metcalf Road in the city of El Dorado in Butler County - improving surface conditions. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2011-06-07 |  | 750000
5488 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BARBER |  | 01 | U225101 | This project will provide curb and gutter replacement on K-2 and East Main in the city of Kiowa in Barber County - improving drainage. | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2011-10-10 | 2010-11-30 | 253655.06
5489 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | SUMNER |  | 04 | U225201 | This project will provide culvert replacement and surfacing work at the Hillside Street Bridge over the Rock Island Slough in the city of Wellington in Sumner County - improving drainage and surface c | New Bridge Construction | 2010-03-05 | 2010-03-05 | 2011-06-07 | 2010-09-27 | 289157.61
5490 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | MONTGOMERY |  | 04 | U225301 | This project will provide an asphalt overlay on 4th Avenue (RS-809) from US 75 to Wood Street in the city of Caney in Montgomery County - improving surface conditions. | Pavement Improvement | 2009-08-07 | 2009-10-12 | 2011-01-04 | 2010-06-21 | 111174.35
5491 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BOURBON |  | 02 | U225401 | This project will provide an asphalt overlay and curb work on SW National Street from Linker Street to Wall Street in the city of Fort Scott in Bourbon County - improving surface conditions. | Pavement Improvement | 2009-10-01 | 2009-10-06 | 2011-01-04 | 2010-12-01 | 228180
5492 | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | MIAMI |  | 02 | U225501 | This project will provide an asphalt overlay on 8th Street from the North City Limits to Main Street in the city of Osawatomie in Miami County - improving surface conditions. | Pavement Improvement | 2009-10-01 | 2009-10-30 | 2011-01-04 |  | 72243.91
5493 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | CRAWFORD |  | 02 | U225601 | This project will provide an asphalt overlay on Broadway Street from Centennial to Williams in the city of Pittsburg in Crawford County - improving surface conditions. | Pavement Improvement | 2009-08-27 | 2009-08-27 | 2011-01-04 | 2010-07-31 | 205982.81
5494 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | CHASE |  | 01 | U225701 | This project will provide an asphalt overlay on 5th Street from West of Cedar Street to State Street in the city of Concordia in Cloud County - improving surface conditions. | Pavement Improvement | 2010-02-11 | 2010-03-01 | 2011-06-07 |  | 425283
5495 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | DICKINSON |  | 01 | U225801 | This project will provide a mill (removal of existing pavement) and overlay on US-56B from the South City Limits to 4th Street in the city of Herington in Dickinson County - improving surface conditio | Pavement Improvement | 2010-07-20 | 2010-07-20 | 2011-05-09 | 2010-08-11 | 331835.48
5496 | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | FORD |  | 01 | U225901 | This project will provide expansion joint replacement on the bridge on 14th Ave. over the Arkansas River in the city of Dodge City - improving structural conditions. | Bridge Replacement | 2010-05-03 | 2010-05-03 | 2011-07-11 |  | 99000
5497 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LABETTE |  | 02 | U226001 | This project will provide intersection improvements at US 59 and Flynn Drive in the city of Parsons in Labette County - improving safety and economic development associated with the Flynn Industrial P | Safety/Traffic Management | 2010-03-17 | 2010-03-17 | 2011-06-07 | 2011-03-05 | 400346.26
5498 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | GRAY |  | 01 | U226101 | This project provide concrete pavement on US-50 from Fifth Street east for 2.5 blocks in the city of Cimarron in Gray County - improving surface conditions. | Pavement Improvement | 2010-05-24 | 2010-06-09 | 2011-05-10 | 2010-10-13 | 742833.23 | 0.959
5499 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | OTTAWA |  | 01 | U226201 | This project will provide a mill (removal of existing pavement) and overlay on Rock Street from Intersection K-106 to North City Limits of city of Minneapolis in Ottawa County - improving surface cond | Pavement Improvement | 2010-06-09 | 2010-06-09 | 2011-04-11 | 2010-11-08 | 135913.82
5500 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | MARION |  | 01 | U226301 | This project will provide an asphalt overlay on Ash Street 1st Street to 3rd Street in the city of Hillsboro in Marion County - improving surface conditions. | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2011-06-07 | 2011-02-07 | 412900
5501 | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | OSAGE |  | 02 | U226401 | This project will provide a mill (removal of existing pavement) and overlay and curb & gutter work on US-56 from the South City Limit to Santa Fe Avenue West on K-31 in the city of Burlingame in Osage | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-04-12 | 2010-06-28 | 493465
5502 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | SHERMAN |  | 01 | U226501 | This project will provide roadway reconstruction/surfacing of K-27/US- 24 Business North of I-70 in the city of Goodland in Sherman County - improving structural and surface conditions. | Pavement Improvement | 2010-06-02 | 2010-06-02 | 2011-09-06 | 2011-03-29 | 491395.9
5503 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | HODGEMAN |  | 01 | U226601 | This project will provide a mill (removal of existing pavement) and overlay on RS226 in the city of Hanston in Hodgeman County - improving surface conditions. | Pavement Improvement | 2010-01-29 | 2010-04-12 | 2011-05-10 | 2010-05-28 | 99206.95
5504 | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | MORTON |  | 01 | U226701 | This project will provide a mill (removal of existing pavement) and inlay on North Street from Baca Ave. East to Border Ave. in the city of Elkhart in Morton County - improving surface conditions. | Pavement Improvement | 2010-09-13 | 2010-09-13 | 2010-10-04 |  | 355615
5505 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | PHILLIPS |  | 01 | U226801 | This project will provide reconstruction of the intersection at State Street and 2nd Street in the city of Phillipsburg in Phillips County -- improving surface condition and safety. | Pavement Improvement | 2010-02-02 | 2010-02-02 | 2011-06-07 | 2010-08-13 | 318200
5506 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | DONIPHAN |  | 02 | U226901 | This project will provide a mill (removal of existing pavement) and overlay on RS-2163 (Locust) from Last Chance to the North City Limits in the city of Troy in Doniphan County - improving surface con | Pavement Improvement | 2010-03-29 | 2010-03-29 | 2011-05-10 | 2011-02-23 | 706369.13
5507 | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | WOODSON |  | 02 | U227001 | This project will provide an asphalt overlay on US-75 from the South City Limits 700 feet North in the city of Yates Center in Woodson County - improving surface conditions. | Pavement Improvement | 2010-03-26 | 2010-03-26 | 2011-06-07 | 2011-01-28 | 345778
5508 | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | EDMONSON |  | 02 | 0051031 | WIDENING OF 2.4 MILES OF EXISTING KY 101 ROADWAY IN EDMONSON COUNTY BETWEEN RHODA AND CHALYBEATE, BEGINNING AT MILEPOINT 0.485 AND EXTENDING TO MILEPOINT 2.85. | Pavement Improvement | 2009-10-30 | 2010-04-07 | 2010-12-01 |  | 4980238 | 2.365
5509 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE |  | 06 | 0114004 | CONSTRUCTION OF NEWTOWN PIKE ROADWAY EXTENSION FROM MAIN STREET TO VERSAILLES ROAD IN LEXINGTON, KENTUCKY. | New Construction | 2009-07-10 | 2009-07-10 | 2010-12-01 | 2011-02-09 | 12100000 | 0.519
5510 | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 0114005 | UTILITY RELOCATION FUNDING FOR THE CONSTRUCTION OF NEWTOWN PIKE ROADWAY EXTENSION FROM MAIN STREET TO VERSAILLES ROAD IN LEXINGTON, KENTUCKY. | Other | 2009-12-08 | 2010-10-01 | 2010-12-31 |  | 1000000 | 0.519
5511 | Underway | C250 | Highway Infrastructure Investment Grant | KENTUCKY | CLINTON |  | 05 | 0139002 | PHASE I OF THE CONSTRUCTION OF THE ALBANY BYPASS IN CLINTON COUNTY; (BRIDGE AND CULVERT SECTION) BEGINNING AT BATES DELK ROAD AND EXTENDING NORTHWARD 1.53 MILES TO 450 FEET SOUTH OF CHURNTOP ROAD. | New Construction | 2010-03-24 | 2010-03-24 | 2011-05-31 |  | 3182233.6 | 1.534
5512 | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | BREATHITT |  | 05 | 0151065 | RECONSTRUCTION AND RELOCATION OF KY 15 ROADWAY FROM KY-15 AT JACKSON, KENTUCKY TO A POINT 0.43 MILES NORTH OF KY 15 IN BREATHITT COUNTY. | Pavement Improvement | 2009-10-30 | 2009-10-30 | 2012-05-01 |  | 11073292.84 | 0.430
5513 | Underway | C250,C240 | Highway Infrastructure Investment Grant | KENTUCKY | BREATHITT |  | 05 | 0151066 | RECONSTRUCTION AND RELOCATION OF KY 15 ROADWAY FROM 0.43 MILES NORTH OF KY 15 AT JACKSON, KENTUCKY TO 0.31 MILES SOUTH OF STILL HOUSE HOLLOW IN BREATHITT COUNTY. | Pavement Improvement | 2009-05-21 | 2009-08-31 | 2011-02-01 |  | 23059255.94 | 1.700
5514 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | LETCHER |  | 05 | 0151067 | CONSTRUCTION OF LEFT TURN LANE ON KY-15 AT THE END OF EXISTING WHITESBURG BYPASS WEST OF WHITESBURG, KENTUCKY IN LETCHER COUNTY. | Safety/Traffic Management | 2009-05-20 | 2009-08-06 | 2010-07-30 | 2010-08-31 | 1780000 | 0.270
5515 | Underway | C250 | Highway Infrastructure Investment Grant | KENTUCKY | MONROE |  | 01 | 0159006 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-90 ROADWAY FROM 0.34 MILES SOUTH OF BUSHONG ROAD MILEPOINT 12.75 AND EXTENDING NORTHERLY TO 0.68 MILES SOUTH OF CYCLONE ROAD AT MILEPOINT 17.45 IN MONROE C | Pavement Improvement | 2009-05-04 | 2009-06-29 | 2011-11-15 |  | 6950972.87 | 4.700
5516 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | LYON, CALDWELL |  | 01 | 0242066 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-24 EAST BOUND AND WEST BOUND LANES FROM 0.5 MILE EAST OF KY-293 AT MILEPOINT 45.133 IN LYON COUNTY TO KY-139 AT MILEPOINT 65.300 IN CALDWELL COUNTY. | Pavement Improvement | 2009-04-03 | 2009-05-18 | 2009-11-09 | 2009-11-09 | 11526812 | 20.167
5517 | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | CAMPBELL | CINCINNATI (OH) | 04 | 0272109 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF US 27 ROADWAY FROM SOUTH OF KY-154 AT MILEPOINT 1.9 TO CAMPBELL COUNTY PARK AT MILEPOINT 5.0 IN CAMPBELL COUNTY. | Pavement Widening | 2009-05-04 | 2009-08-25 | 2011-11-30 |  | 27620000 | 3.200
5518 | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | KENTON | CINCINNATI (OH) | 04 | 0273013 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF 12TH STREET ROADWAY FROM I-75 TO SCOTT STREET IN COVINGTON, KENTUCKY IN KENTON COUNTY. | Pavement Improvement | 2009-05-22 | 2009-08-31 | 2011-11-01 |  | 7586554 | 0.470
5519 | Underway | C240,C230 | Highway Infrastructure Investment Grant | KENTUCKY | KENTON | CINCINNATI (OH) | 04 | 0273014 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF 12TH STREET ROADWAY FROM I-75 TO SCOTT STREET IN COVINGTON, KENTUCKY IN KENTON COUNTY. | Pavement Improvement | 2009-07-02 | 2009-10-19 | 2011-07-01 |  | 2175306 | 0.220
5520 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | HARDIN | RADCLIFF-ELIZABETHTOWN | 02 | 0401068 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-144 ROADWAY TO PROVIDE HORIZONTAL AND VERTICAL REALIGNMENT OF EXISTING ROADWAY BETWEEN MILEPOINTS 0.8 TO MILEPOINT 1.1 JUST WEST OF KY-1500 AT VINE GROVE, | Safety/Traffic Management | 2009-09-16 | 2010-03-01 | 2010-06-30 | 2010-07-10 | 223819.4 | 0.300
5521 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | HARDIN | RADCLIFF-ELIZABETHTOWN | 02 | 0401071 | Safety improvements along KY 220 between milepoint 13.2 to milepoint 13.3 in Hardin county, Kentucky at the southeast intersection of KY 220 and KY 1600 in Rineyville, Kentucky. | Safety/Traffic Management | 2010-02-23 | 2010-02-23 | 2010-08-30 | 2010-10-07 | 557814.95 | 0.100
5522 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON |  | 03 | 0655098 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-65 IN JEFFERSON COUNTY FROM FERN VALLEY ROAD AT MILEPOINT 128.13 TO MILEPOINT 131.89. | Pavement Improvement | 2009-07-02 | 2009-07-02 | 2010-12-15 | 2011-03-16 | 18000000 | 3.160
5523 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | TRIGG |  | 01 | 0801075 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF US 68/KY 80 ROADWAY BETWEEN MILEPOINT 0.243 TO MILEPOINT 8.284 IN THE LAND BETWEEN THE LAKES AREA OF TRIGG COUNTY. | Pavement Widening | 2009-04-30 | 2009-05-30 | 2010-11-15 | 2010-11-30 | 30000000 | 7.791
5524 | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | CLINTON |  | 05 | 1271100 | RECONSTRUCTION OF 3.5 MILES OF US 127 IN CLINTON COUNTY BEGINNING AT THE ALBANY BYPASS AND EXTENDING NORTH TO KY 90. | Pavement Improvement | 2009-11-19 | 2010-03-10 | 2011-10-01 |  | 17940774.45 | 4.240
5525 | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | WASHINGTON |  | 02 | 1501096 | CONSTRUCTION OF NEW SPRINGFIELD NORTHWEST BYPASS FROM KY 555 TO US 150 NORTHWEST OF SPRINGFIELD, KENTUCKY. | New Construction | 2009-05-05 | 2009-08-12 | 2011-06-01 |  | 13421653.83 | 3.475
5526 | Underway | C200,C240 | Highway Infrastructure Investment Grant | KENTUCKY | ROCKCASTLE |  | 05 | 1501097 | RECONSTRUCTION OF 6 MILES OF US 150 IN ROCKCASTLE COUNTY BEGINNING AT BRODHEAD, KY AND EXTENDING EAST TO US 461 AT MT. VERNON, KY. | Pavement Improvement | 2009-10-29 | 2010-02-08 | 2011-12-01 |  | 23088172.4 | 6.310
5527 | Underway | C200 | Highway Infrastructure Investment Grant | KENTUCKY | NELSON |  | 02 | 1501098 | RECONSTRUCTION/RELOCATION OF 3 MILES OF US 31E IN NELSON COUNTY NORTH OF BARDSTOWN, KY BEGINNING AT KY 509 AND EXTENDING NORTH TO WHITESIDE DRIVE. | Pavement Improvement | 2009-12-29 | 2010-04-01 | 2011-07-31 |  | 7114802.28 | 3.070
5528 | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | ROCKCASTLE, LINCOLN |  | 05 | 1501099 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF APPROXIMATELY 7.2 MILES OF US-150 ROADWAY FROM CRAB ORCHARD, KENTUCKY IN LINCOLN COUNTY TO BRODHEAD, KENTUCKY IN ROCKCASTLE COUNTY. | Pavement Improvement | 2009-04-07 | 2009-06-08 | 2010-12-01 |  | 25448598 | 14.300
5529 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 2641164 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-264 IN LOUISVILLE, KENTUCKY FROM NEWBURG ROAD AT MILEPOINT 13.710 TO BRECKINRIDGE LANE AT MILEPOINT 18.410 IN JEFFERSON COUNTY. | Pavement Improvement | 2009-09-04 | 2009-10-13 | 2010-06-15 | 2010-11-08 | 11778000 | 5.700
5530 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON |  | 03 | 2641166 | PAVEMENT REHABILITATION TO MILL 1"" OF EXISTING PAVEMENT AND TO RESURFACE WITH THIN OVERLAY ON I-264 EAST BOUND & WEST BOUND FROM MILEPOINT 22.61 TO I-71 AT MILEPOINT 22.97. | Pavement Improvement | 2009-07-01 | 2010-05-03 | 2010-06-30 | 2010-10-18 | 301574.28 | 0.360
5531 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 2652023 | REPAIR AND GRIND EXISTING PAVEMENT ON I-265 IN JEFFERSON COUNTY FROM MILEPOINT 18.8 NEAR EXIT 19 AND EXTENDING NORTH TO MILEPOINT 23.4 NEAR EXIT 23. | Pavement Improvement | 2009-12-30 | 2010-04-07 | 2010-10-31 | 2010-11-05 | 3846696.7 | 4.560
5532 | Completed | C200 | Highway Infrastructure Investment Grant | KENTUCKY | MARION |  | 02 | 3000786 | CONSTRUCTION OF A NEW ROADWAY CONNECTOR FROM THE INTERSECTION OF THE US-68/LEBANON NORTHERN BYPASS (KY 2154) AND EXTENDING SOUTHEAST TO INDUSTRIAL DRIVE IN LEBANON, KENTUCKY IN MARION COUNTY, BEING AP | New Construction | 2009-04-07 | 2009-05-21 | 2010-07-01 | 2010-06-22 | 4000000 | 1.300
5533 | Completed | C950 | Ferryboat | KENTUCKY | CRITTENDEN |  | 01 | 3000807 | The project will reduce service delays by providing construction and rehabiliation of the ferry landing at Cave-in-Rock Ferry which crosses the Ohio river at KY91 NW of the City of Marion in Crittende | Other | 2010-11-18 | 2010-11-22 | 2010-12-22 | 2010-12-15 | 81204.72
5534 | Underway | C950 | Ferryboat | KENTUCKY | MONROE |  | 01 | 3000808 | The project will replace the aging ferry tugboat and trailer for the Turkey Neck Bend Ferry which crosses the Cumberland River on KY 214 east of Tompkinsville in Monroe County. | Other | 2010-09-15 | 2010-09-15 |  |  | 300000
5535 | Underway | C950 | Ferryboat | KENTUCKY | BUTLER |  | 01 | 3000809 | The project will provide a new ferry barge at the Reeds Ferry which carried KY269 over the Green River approvimately 25 miles NW of Bowling Green in Butler County. | Other | 2011-12-01 |  |  |  | 300000
5536 | Underway | C220 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001329 | CONSTRUCT A PEDESTRIAN CROSSWALK INTERSECTING 2ND STREET AND 3RD STREET, CROSSING THROUGH FREEDOM PARK, PART OF THE UNIVERSITY OF LOUISVILLE BELKNAP CAMPUS, AT CARDINAL BOULEVARD AND THIRD AND SECOND | Transportation Enhancements | 2009-08-27 | 2009-08-27 | 2010-06-01 |  | 1612000 | 0.000
5537 | Completed | C220 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON |  | 03 | 3001339 | CONSTRUCTION OF PEDESTRIAN AND SAFETY IMPROVEMENTS INCLUDING SIDEWALKS, LANDSCAPING, AND SIGNAL IMPROVEMENTS ALONG US 60A (EASTERN PARKWAY) AT 3RD STREET IN LOUISVILLE, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 2009-07-02 | 2009-08-18 | 2010-06-01 | 2010-06-15 | 2888182.29 | 0.200
5538 | Completed | C240,C230 | Highway Infrastructure Investment Grant | KENTUCKY | BULLITT | LOUISVILLE (IN) | 02 | 3001343 | PAVEMENT REHABILITATION TO MILL AND GRIND EXISTING PAVEMENT, AND RESURFACE KY-1526 (KNOB CREEK ROAD) FROM KY-44 TO OLD BROOKS HILL ROAD (KY 2672) IN BULLITT COUNTY BEING APPROXIMATELY 4.9 MILES IN LEN | Pavement Improvement | 2009-10-01 | 2010-05-17 | 2010-05-31 | 2010-06-02 | 315996 | 4.900
5539 | Completed | C240,C230 | Highway Infrastructure Investment Grant | KENTUCKY | BULLITT | LOUISVILLE (IN) | 02 | 3001344 | PAVEMENT REHABILITATION TO MILL AND GRIND EXISTING PAVEMENT, AND RESURFACE KY 1526 (BELLS MILL ROAD) FROM KY 44 TO KY 61 IN BULLITT COUNTY BEING APPROXIMATELY 3.9 MILES IN LENGTH. | Pavement Improvement | 2009-10-01 | 2010-05-17 | 2010-05-31 | 2010-06-02 | 322930 | 3.972
5540 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001346 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-06-07 | 2010-11-15 | 2010-12-03 | 420832.03 | 0.000
5541 | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001347 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-03-22 | 2010-03-22 | 2010-10-10 |  | 1750000
5542 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001348 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-09-01 | 2010-09-20 | 197528 | 0.000
5543 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001349 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-08-24 | 2010-11-01 | 2010-11-15 | 80234 | 0.000
5544 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001350 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-06-25 | 2010-11-01 | 2010-11-15 | 87373 | 0.000
5545 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001351 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-10-29 | 131098 | 0.000
5546 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001352 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-08-02 | 152185 | 0.000
5547 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001353 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-08-09 | 129008 | 0.000
5548 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001354 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-05-28 | 2010-11-15 | 2010-12-15 | 110662.5 | 0.000
5549 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001355 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-10-20 | 2010-11-01 | 2010-11-15 | 74302.8 | 0.000
5550 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001356 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-10-13 | 2010-11-01 | 2010-11-15 | 89434.89 | 0.000
5551 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001357 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-09-14 | 2010-11-01 | 2010-11-15 | 74289.87 | 0.000
5552 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001358 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-08-31 | 116726.5 | 0.000
5553 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001359 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-05-19 | 2010-08-19 | 2010-09-15 | 121005.5 | 0.000
5554 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001360 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-08-10 | 107651.5 | 0.000
5555 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001361 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-05-11 | 2010-11-01 | 2010-10-04 | 101035 | 0.000
5556 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001362 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-06-01 | 2010-11-15 | 2010-12-15 | 130259 | 0.000
5557 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001363 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisvill | Transportation Enhancements | 2010-02-05 | 2010-08-23 | 2010-11-15 | 2011-01-31 | 493530 | 0.000
5558 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001364 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-03-26 | 2010-03-26 | 2010-11-15 | 2010-11-15 | 193410.79 | 0.000
5559 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001365 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-06-29 | 2010-11-01 | 2010-11-15 | 101788.6 | 0.000
5560 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001366 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-07-19 | 2010-11-01 | 2010-11-06 | 130187.73 | 0.000
5561 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001367 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-05-18 | 2010-11-01 | 2010-11-15 | 88899.03 | 0.000
5562 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001368 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-12-02 | 2010-11-01 | 2010-12-31 | 80996.44 | 0.000
5563 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001369 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-12-31 | 26919.47 | 0.000
5564 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001370 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-10-08 | 2010-11-15 | 2011-02-21 | 71434.99 | 0.000
5565 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001371 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-12-31 | 33517.28 | 0.000
5566 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001372 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-10-07 | 2010-11-15 | 2010-11-15 | 109073.18 | 0.000
5567 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001373 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-06-23 | 2010-11-01 | 2010-11-15 | 88367.17 | 0.000
5568 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001374 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2011-01-24 | 98327.5 | 0.000
5569 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001375 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-03-26 | 2010-03-26 | 2010-11-15 | 2010-12-20 | 173489.28 | 0.000
5570 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001376 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-05-17 | 2010-11-15 | 2010-12-15 | 144659 | 0.000
5571 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001377 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-05-19 | 2010-11-15 | 2010-12-15 | 131975 | 0.000
5572 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001378 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-07-30 | 2010-11-01 | 2010-11-15 | 79446.4 | 0.000
5573 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001379 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-09-21 | 2010-11-01 | 2010-11-15 | 79723.04 | 0.000
5574 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001380 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-03-26 | 2010-03-26 | 2010-11-15 | 2010-12-15 | 178751.5 | 0.000
5575 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001381 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-06-07 | 2010-11-15 | 2010-12-15 | 121714.81 | 0.000
5576 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001382 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-09-01 | 2010-10-29 | 144523.28 | 0.000
5577 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001383 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-05-03 | 2010-11-15 | 2010-12-15 | 751784.8 | 0.000
5578 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001384 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2011-01-07 | 855189.41 | 0.000
5579 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001385 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1710) | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-11-10 | 667518.39 | 0.000
5580 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001386 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1711) | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2011-02-16 | 551169.64 | 0.000
5581 | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001387 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1712) | Pavement Improvement | 2010-02-05 | 2010-06-03 | 2010-09-01 |  | 528090.19 | 0.000
5582 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001388 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1713) | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-08-31 | 2010-11-02 | 585151.54 | 0.000
5583 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001389 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1714) | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-08-31 | 2010-08-28 | 512143.55 | 0.000
5584 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 3001390 | RECONSTRUCTION OF APPROXIMATELY 1,443 HANDICAP RAMPS AND 1,570 FEET OF SIDEWALKS IN THE CITY OF JEFFERSONTOWN, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2011-04-29 | 1338238 | 0.000
5585 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001391 | The Jefferson County- Louisville Metro Government will construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the city of Louisville (KIPDA ID # 1671). | Transportation Enhancements | 2010-03-26 | 2010-03-26 | 2010-11-15 | 2010-12-15 | 243099.32 | 0.000
5586 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 3001392 | PAVEMENT REHABILITATION BY MILLING THE EXISTING SURFACE, AND REPLACING WITH A MINIMUM OF 1.5 INCHES OF ASPHALT SURFACE TO EXTEND THE PAVEMENT LIFE OF PLANTSIDE DRIVE FROM BLUEGRASS PARKWAY TO KY 1819 | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-10-01 | 2010-07-28 | 246167.08 | 0.000
5587 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | OLDHAM | LOUISVILLE (IN) | 04 | 3001393 | CONSTRUCT 1,400 FEET OF SIDEWALK ALONG NORTH SIDE OF KY 22 FROM KY 329 TO KY 329 BYPASS, AND CONSTRUCT 400 FEET OF SIDEWALK ALONG KY 146 FROM FLOYDSBURG ROAD TO THE NEW CRESTWOOD ELEMENTARY SCHOOL, IN | Transportation Enhancements | 2010-02-05 | 2010-07-08 | 2010-10-15 | 2010-09-10 | 114211.81 | 0.000
5588 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | OLDHAM | LOUISVILLE (IN) | 04 | 3001394 | INSTALL GUARDRAILS ALONG ROADWAYS AT VARIOUS LOCATIONS IN OLDHAM COUNTY KENTUCKY. | Safety/Traffic Management | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-11-27 | 52164.6 | 0.000
5589 | Completed | C220 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 3001395 | Streetscape project in Jefferson county, Kentucky in downtown Louisville, Kentucky along Second Street for improvements to traffic intersections, sidewalks, accessibility/mobility, landscaping, lighti | Transportation Enhancements | 2010-02-19 | 2010-02-19 | 2010-12-31 | 2010-10-07 | 2400000 | 0.000
5590 | Underway | C220 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 3001397 | Bikeway and safety improvement project in Jefferson county, Kentucky in downtown Louisville, Kentucky along Third Street and Eastern Parkway for: (1) construction of new University of Louisville entr | Transportation Enhancements | 2010-02-19 | 2010-02-19 | 2010-12-31 |  | 2000000 | 0.000
5591 | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001399 | Transit project in Jefferson county for the Transit Authority of River City (TARC) to purchase paratransit vehicles; purchase 18 cut-away paratransit vehicles, and purchase 7 paratransit mini-vans. | Other | 2011-02-24 | 2011-03-01 | 2012-12-31 |  | 1820244.69 | 0.000
5592 | Underway | C220 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE |  | 06 | 3003241 | STRUCTURAL REPAIRS AND INSTALLATION OF COMPONENTS FOR THE RESTORATION AND CONVERSION OF THE KENTUCKY HORSE PARK'S ""BIG BARN"" TO SERVE AS VISITOR CENTER AND CARRIAGE MUSEUM AT THE KENTUCKY HORSE PARK | Transportation Enhancements | 2010-07-27 | 2010-08-05 | 2011-01-02 |  | 993667.71 | 0.000
5593 | Underway | C220,C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 3003243 | Transportation Enhancement project in Fayette county, Kentucky at Lexington, Kentucky for the construction of Legacy Trail Phase I from Berea road at Ironworks Pike to Newtown Pike at Citation Bouleva | Transportation Enhancements | 2010-03-03 | 2010-03-18 | 2010-08-31 |  | 3275371.5 | 6.400
5594 | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 3003244 | Transportation Enhancement project at Fayette county, Kentucky in Lexington, Kentucky for the construction of Legacy Trail phase 2 from Citation Boulevard to Loudon Avenue. | Transportation Enhancements | 2010-03-03 | 2010-03-03 | 2010-08-31 |  | 2004632.5 | 2.100
5595 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 3003245 | Transportation Enhancement project in Fayette county, Kentucky at Lexington, Kentucky for the construction of the downtown streetscape project to improve mobility along Vine street from South Broadway | Pavement Improvement | 2010-02-05 | 2010-04-05 | 2010-08-20 | 2012-01-12 | 1295000 | 0.000
5596 | Underway | C200 | Highway Infrastructure Investment Grant | KENTUCKY | BARREN |  | 02 | 3013012 | CONSTRUCTION OF NEW GLASGOW OUTER LOOP ROADWAY FROM US-68 TO THE LOUIE B. NUNN PARKWAY EAST OF GLASGOW, KENTUCKY. | New Construction | 2009-05-21 | 2009-07-22 | 2011-04-01 |  | 15678931 | 1.200
5597 | Underway | C200,C240 | Highway Infrastructure Investment Grant | KENTUCKY | DAVIESS |  | 02 | 3023014 | RECONSTRUCTION AND RELOCATION OF THE EXISTING EAST US-60 BYPASS AT OWENSBORO, KENTUCKY (EAST COUNTY CORRIDOR) BEGINNING AT REID ROAD AND EXTENDING NORTHEAST TO EXISTING US 60 EAST OF OWENSBORO, KENTUC | Pavement Improvement | 2009-07-02 | 2009-08-24 | 2013-02-15 |  | 35535419.92 | 2.200
5598 | Underway | C220 | Highway Infrastructure Investment Grant | KENTUCKY | NELSON |  | 02 | 3025006 | Transportation Enhancement project in Nelson county, Kentucky at Bardstown, Kentucky for Phase I and Phase II construction of streetscape improvements including sidewalks, curb ramps, and widening the | Transportation Enhancements | 2010-02-19 | 2010-02-19 | 2011-04-15 |  | 2539000 | 0.000
5599 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | BULLITT | LOUISVILLE (IN) | 02 | 5116024 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-61 ROADWAY FROM SOUTH OF JOHN HARPER HIGHWAY (BROOKS ROAD MILEPOINT 19.33) TO THE EXISTING 4-LANE SECTION SOUTH OF CARDINAL AVENUE AT MILEPOINT 210.5 IN BU | Pavement Widening | 2009-05-04 | 2009-06-30 | 2010-05-15 | 2010-05-14 | 5875912.18 | 0.720
5600 | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | NELSON |  | 02 | 5121010 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-245 ROADWAY FROM MILEPOINT 6.5 AT INTERSECTION OF KY-332 NORTH OF BARDSTOWN AND EXTENDING NORTHWEST TO MILEPOINT 7.6 TO THE FLAGET HOSPITAL SITE IN BARDSTO | Pavement Widening | 2009-05-20 | 2009-08-12 | 2010-07-15 |  | 3815760.2 | 1.193
5601 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | WHITLEY |  | 05 | 5147019 | ASPHALT SURFACING FOR THE RECONSTRUCTED SECTION OF KY 92 ROADWAY FROM CORNBREAD BRANCH NEAR OLD JELLICO ROAD AT MILEPOINT 4.4 AND EXTENDING EAST TO BRIER CREEK BRIDGE AT MILEPOINT 8.4 IN WHITLEY COUNT | Pavement Improvement | 2009-05-01 | 2009-07-13 | 2010-06-30 | 2010-06-16 | 6020000 | 5.500
5602 | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | MCCREARY |  | 05 | 5147020 | RECONSTRUCTION AND RELOCATION OF KY 92 ROADWAY BETWEEN MILEPOINT 16.6 TO MILEPOINT 21.5 IN MCCREARY COUNTY. | Pavement Improvement | 2009-10-30 | 2010-02-22 | 2011-08-15 |  | 14670000 | 4.900
5603 | Underway | C200 | Highway Infrastructure Investment Grant | KENTUCKY | KNOX, WHITLEY |  | 05 | 5155009 | CONSTRUCTION OF A NEW ROADWAY CONNECTOR FROM KY-6 AT WOODBINE IN WHITLEY COUNTY EXTENDING NORTHEAST TO THE CORBIN BYPASS IN KNOX COUNTY, BEING APPROXIMATELY 1.2 MILES IN LENGTH. | New Construction | 2009-05-01 | 2009-05-01 | 2010-09-01 |  | 6790000 | 0.000
5604 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | OLDHAM | LOUISVILLE (IN) | 04 | 5162019 | CONSTRUCT 1,644 FEET OF SIDEWALKS, WHICH WILL BE 4 FEET IN WIDTH WITH FIVE-FOOT PASSING AREAS TO MEET ADA STANDARDS, ALONG THE SOUTH SIDE OF KY 146 FROM DOGWOOD LANE EXTENDING WEST TO FOLEY AVENUE IN | Transportation Enhancements | 2010-02-05 | 2010-06-10 | 2010-11-01 | 2010-11-15 | 107994.85 | 0.310
5605 | Completed | C250 | Highway Infrastructure Investment Grant | KENTUCKY | GALLATIN |  | 04 | 5170014 | SAFETY IMPROVEMENTS, REHABILITATION OF PAVEMENT, AND CONSTRUCT NEW BRIDGE DECK WITH BARRIER WALLS ON EXISTING US 127 BIG SUGAR BRIDGE BETWEEN MILEPOINT 3.88 TO MILEPOINT 3.98 IN GALLATIN COUNTY. | Bridge Improvement | 2009-04-03 | 2009-06-15 | 2009-08-13 | 2009-08-13 | 447986.93 | 0.100
5606 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | MADISON |  | 06 | 5192004 | CONSTRUCTION OF LEFT TURN LANES AT THE US25 AND KY1156 INTERSECTION AT RICHMOND, KENTUCKY IN MADISON COUNTY. | Safety/Traffic Management | 2009-06-30 | 2009-09-10 | 2010-06-18 | 2010-06-18 | 910000 | 0.020
5607 | Completed | C200 | Highway Infrastructure Investment Grant | KENTUCKY | FRANKLIN |  | 06 | 5196010 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF APPROXIMATELY 2.3 MILES OF US 421 ROADWAY FROM EXISTING US-60/KY 676 INTERCHANGE TO 1600 FEET EAST OF CHENAULT INDUSTRIAL ROAD IN FRANKLIN COUNTY. | Pavement Widening | 2009-05-04 | 2009-07-14 | 2010-08-26 | 2010-11-15 | 9934478.4 | 1.790
5608 | Completed | C250 | Highway Infrastructure Investment Grant | KENTUCKY | KNOTT |  | 05 | 5339006 | CONSTRUCT LEFT TURN LANE AND IMPROVE SIGHT DISTANCE ON KY 160 AT THE INTERSECTION OF KY 3391 NEAR THE KNOTT COUNTY CENTRAL HIGH SCHOOL IN KNOTT COUNTY, KENTUCKY. | Safety/Traffic Management | 2009-12-30 | 2010-03-16 | 2010-08-15 | 2010-09-28 | 1495000 | 0.236
5609 | Completed | C240,C230 | Highway Infrastructure Investment Grant | KENTUCKY | HENDERSON | EVANSVILLE (IN) | 01 | 7970012 | Provide safety improvements by widening of us 41a at Henderson, Kentucky in Henderson County between milepoint 14.48 to 14.68 to construct two-way left turn lane. | Pavement Improvement | 2009-11-20 | 2010-03-19 | 2010-08-14 | 2010-09-02 | 1134685.09 | 0.200
5610 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | HENDERSON |  | 01 | 7997004 | Provide safety improvement by widening of Watson lane at us 41a at Henderson, Kentucky in Henderson County between milepoint 1.098 to 1.167 to accommodate two approach lanes and one receiving lane. | Pavement Improvement | 2009-11-19 | 2010-03-03 | 2010-06-04 | 2010-06-04 | 287961.36 | 0.069
5611 | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | BOONE | CINCINNATI (OH) | 04 | 8200009 | RECONSTRUCTION OF 1.6 MILES OF KY 237 IN BOONE COUNTY FROM US 42 AT GUN POWDER BEGINNING AT MILEPOINT 1.581 AND EXTENDING NORTHWEST TO WOODCREEK DRIVE NEAR MILEPOINT 3.166. | Pavement Widening | 2010-05-10 | 2010-06-10 | 2012-05-01 |  | 5731742.27 | 1.605
5612 | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 8591002 | PHASE 1B OF THE WIDENING OF 0.7 MILES OF LIBERTY ROAD/TODDS ROAD IN LEXINGTON, KENTUCKY BEGINNING AT THE INTERSECTION OF MAN O'WAR BLVD AND EXTENDING EAST TO FOREST HILL DRIVE. | Pavement Improvement | 2009-10-30 | 2010-03-22 | 2010-09-15 |  | 470000 | 0.696
5613 | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 8723011 | EXTENDING EXISTING BLANKENBAKER PARKWAY (KY 913) AS 5 LANE ROADWAY IN JEFFERSON COUNTY FROM THE BLANKENBAKER ACCESS ROAD TO TAYLORSVILLE ROAD (KY 155). | Pavement Widening | 2009-11-20 | 2010-02-08 | 2011-07-15 |  | 6000700 | 0.600
5614 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 8724018 | INSTALLATION OF BICYCLE LANES ALONG TAYLORSVILLE ROAD BETWEEN MCMAHAN BOULEVARD AND HURSTBOURNE PARKWAY IN LOUISVILLE, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-06-23 | 63709.72 | 1.582
5615 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 8738031 | The Jefferson County- Louisville Metro Government will construct new sidewalks to meet ADA (American Disabilities Act) compliance along the east side of the Preston Highway from Gilmore Lane to Kremer | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-11-18 | 111265 | 0.358
5616 | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 8893001 | WIDEN EXISTING ROADS (NO ADDITIONAL TRAVEL LANES), ADD SIDEWALKS, CONSTRUCT DRAINAGE IMPROVEMENTS, AND INSTALL LANDSCAPING ALONG MAIN STREET FROM KY 1819 (WATTERSON TRAIL) TO THE WESTERN CITY LIMIT AN | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-09-15 | 2010-11-15 | 200072.11 | 0.108
5617 | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | GRAYSON |  | 02 | 9001011 | PAVEMENT REHABILITATION OF THE EASTBOUND LANES OF THE WESTERN KENTUCKY PARKWAY IN GRAYSON COUNTY FROM 0.9 MILES EAST OF CROW HOLLOW ROAD BRIDGE, BEGINNING AT MILEPOINT 114.9 AND EXTENDING EAST TO THE | Pavement Improvement | 2009-05-20 | 2009-08-04 | 2009-09-13 | 2009-09-13 | 1100000 | 2.150
5618 | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | CADDO | SHREVEPORT | 04 | 0021013 | This project will build 5.5 miles of new interstate highway from LA 173 to LA 1. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas State Line in C | New Construction | 2010-09-01 | 2010-09-28 | 2013-02-23 |  | 5636916.71
5619 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | CADDO |  | 04 | 0021021 | This project will build 3.2 miles of new interstate highway from US 71(S) to LA 2. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas State Line in | New Construction | 2009-11-16 | 2010-02-14 | 2011-11-26 |  | 9658943.61 | 3.153
5620 | Underway | C250 | Highway Infrastructure Investment Grant | LOUISIANA | WASHINGTON |  | 01 | 002S613 | These Washington Parish projects near Bogalusa will replace four existing structurally deficient timber bridges located on Burt Road and Claiborne Street. | Bridge Replacement | 2009-08-03 | 2009-08-05 | 2010-04-17 |  | 1857946.8
5621 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | JEFFERSON | NEW ORLEANS | 03 | 0105370 | This project is Phase 2 of 2 for the imporvement of the existing Interstate 10/Causeway Blvd interchange. The project includes the construction of new flyover ramps to improve the flow of traffic bet | Pavement Widening | 2009-08-04 | 2009-11-09 | 2012-04-27 |  | 51729364.18 | 0.380
5622 | Completed | C220,C240 | Highway Infrastructure Investment Grant | LOUISIANA | ASCENSION | BATON ROUGE | 03 | 0302505 | This project will construct a sidewalk near East Ascension High School in the city of Gonzales to provide pedestrian access to parks, businesses, civic facilities as well as Bayou Francois in Ascensio | Transportation Enhancements | 2010-03-22 | 2010-03-22 | 2010-06-14 | 2010-08-03 | 481610.32 | 0.511
5623 | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ASCENSION | BATON ROUGE | 03 | 0309511 | This project includes patching deteriorated pavement and placing an asphalt overlay along LA 73 in Ascension Parish from US61(N) to the East Baton Rouge Parish Line. | Pavement Improvement | 2010-06-05 | 2010-07-08 | 2010-09-16 | 2010-09-24 | 1529344.84 | 2.880
5624 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ASSUMPTION | HOUMA | 03 | 0409500 | This project will construct left turn lanes on LA 1 to turn onto LA 1247 in Assumption Parish, LA. | Pavement Improvement | 2010-05-21 | 2010-06-21 | 2010-08-02 | 2010-07-22 | 242031.22 | 0.590
5625 | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | BOSSIER | SHREVEPORT | 04 | 0809508 | This project will rebuild 2.1 miles of pavement on Stockwell Road in Bossier Parish. | Pavement Improvement | 2010-06-01 | 2010-06-25 | 2010-09-10 | 2010-09-17 | 1179268.41 | 2.100
5626 | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | BOSSIER | SHREVEPORT | 04 | 0809509 | This project will replace cracked and deteriorated concrete along Green Acres Boulevard in Bossier Parish from La.3 (Benton Road) east to La. 3105 (Airline Drive). | Pavement Improvement | 2010-08-23 | 2010-09-22 | 2010-11-10 | 2010-11-17 | 367928.69 | 0.590
5627 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | CADDO | SHREVEPORT | 04 | 0905504 | This project will build 4.6 miles of new interstate highway from Mira-Myrtis Road to LA 168. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas Sta | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2010-08-11 |  | 32554028.02 | 4.660
5628 | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | CADDO | SHREVEPORT | 04 | 0909507 | This project will remove the deteriorated asphalt, make repairs,and place a new asphalt overlay Woolworth Road from Colquitt Road to the Shreveport City Limits in Caddo Parish. | Pavement Improvement | 2010-08-09 | 2010-08-24 | 2010-10-12 | 2010-10-14 | 757497.19
5629 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1008534 | This project will rehabilitate approximately 9.6 miles of Intetstate 210 from the east end of the Calcasieu River Bridge to Interstate 10 on the east side of Lake Charles in Calcasieu Parish. The fir | Pavement Improvement | 2009-11-09 | 2010-02-17 | 2010-12-19 | 2011-05-31 | 19842022.7 | 9.580
5630 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1009516 | The City of Lake Charles will repair 2 miles of Broad Street from Entreprise to Interstate 210 by placing new asphalt on the exisitng pavement in Calcasieu Parish. | Pavement Improvement | 2010-07-07 | 2010-07-29 | 2010-10-07 | 2010-12-17 | 1751513.23 | 2.236
5631 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1009517 | The City of Lake Charles will repair approximately a half mile of West McNesse Street from Weaver Street to Nelson Street and 2 miles of the pavement on Weaver Street from Sale Street to Ham Reid Stre | Pavement Improvement | 2010-06-08 | 2010-06-08 | 2011-04-14 |  | 2935232.84
5632 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1009521 | The City of Lake Charles will repair 1 mile of pavement by placing new asphalt on the existing pavement from Hodge Street to 7th Street in Calcasieu Parish. | Pavement Improvement | 2010-06-08 | 2010-06-08 | 2010-09-25 |  | 579387.17
5633 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1009522 | This project will remove the existing pavement and construct 1.25 miles of new concrete pavement on the 5 lane segment of LA 14 from LA 3092 to LA 3186 in Calcasieu Parish. | Pavement Improvement | 2010-07-28 | 2010-08-16 | 2010-12-20 | 2011-09-12 | 4359560.19
5634 | Underway | C250,C240 | Highway Infrastructure Investment Grant | LOUISIANA | IBERIA |  | 03 | 1104011 | This project will build a new bridge on US 90 at LA 85 in Iberia Parish as part of the upgrading of US 90 to become part of I-49 from Lafayette to New Orleans. | New Construction | 2009-03-03 | 2009-03-03 | 2012-09-06 |  | 29440823.1 | 1.170
5635 | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | CATAHOULA |  | 05 | 1308502 | This project is located at the northern and southern city limits of Sicily Island in Catahoula Parish along LA 15 and will providie landscaping along the reconstructed section of LA 15 through Sicily | Transportation Enhancements | 2009-07-11 | 2009-10-21 | 2009-12-23 | 2011-04-15 | 177680.83 | 0.231
5636 | Completed | C250 | Highway Infrastructure Investment Grant | LOUISIANA | CONCORDIA |  | 05 | 1508500 | This project will remove approximately 7 miles of the deteriorated pavement along US 425 and place new asphalt from US 65 to Foules in Concordia and Catahoula Parishes. | Pavement Improvement | 2009-09-12 | 2009-10-06 | 2009-12-29 | 2010-03-19 | 1938770.5 | 0.266
5637 | Completed | C220,C240 | Highway Infrastructure Investment Grant | LOUISIANA | DE SOTO |  | 04 | 1602501 | This project will establish a trailhead with informational signage and parking area for automobiles and bicycles along LA 191 (approx. 650? south of the intersection of US 84 and LA 191) in the Toled | Transportation Enhancements | 2010-06-28 | 2010-06-28 | 2010-08-16 | 2010-08-12 | 269235.53 | 0.020
5638 | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | EAST BATON ROUGE | BATON ROUGE | 06 | 1704507 | This project located near Central, LA in East Baton Rouge Parish includes clearing, removing trees and buildings and placing soil, and two new bridges over Beaver Bayou for the new Central Thruway fro | New Construction | 2010-03-01 | 2010-03-31 | 2011-08-17 |  | 7947257.26
5639 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | EAST BATON ROUGE |  | 06 | 1709503 | The project is located in Baton Rouge and consists of widening Interstate-10 from four to six lanes from the Seigen Lane Interchange to the Highland Road Interchange. | Pavement Widening | 2009-03-03 | 2009-03-10 | 2013-01-12 |  | 68404999.99 | 2.000
5640 | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | EAST BATON ROUGE | BATON ROUGE | 06 | 1709523 | This project consists of constructing the Central Thruway which will be a concrete roadway in East Baton Rouge Parish from Florida Blvd. to the South end of Sullivan Rd. | Pavement Improvement | 2010-06-14 | 2010-07-14 | 2011-01-10 |  | 1599471.18 | 0.010
5641 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | EVANGELINE |  | 07 | 2002502 | These Evangeline Parish projects on Red Fox Lane and 1st Street in Chataignier will replace the existing deficient timber bridges with a new concrete box culvert and a new concrete bridge. | Bridge Replacement | 2009-06-22 | 2009-06-22 | 2010-11-26 |  | 637190.85
5642 | Completed | C250 | Highway Infrastructure Investment Grant | LOUISIANA | JACKSON |  | 05 | 2508503 | This Jackson Parish project will place new asphalt along 6 miles of the existing two lanes on US 167 lanes from Quitman to the Lincoln Parish line. | Pavement Improvement | 2009-08-01 | 2009-08-18 | 2010-02-02 | 2010-03-22 | 2954273.33 | 6.060
5643 | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | JEFFERSON | NEW ORLEANS | 03 | 2602528 | This Jefferson Parish project will remove the deteriorated pavement and place new asphalt along approximately 0.34 miles of Lapalco Boulevard beginning at Manhattan Boulevard and ending at Bayou Fatma | Pavement Improvement | 2010-07-06 | 2010-07-19 | 2010-09-13 | 2010-10-25 | 1233867.36
5644 | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | JEFFERSON | NEW ORLEANS | 03 | 2603521 | This project will overlay Segnette Blvd. from Lapalco Blvd. to US 90B in Jefferson Parish. | Pavement Improvement | 2010-11-22 | 2010-11-29 | 2011-04-18 |  | 2166809.76
5645 | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2803519 | This project will construct a shared use path with landscaping and lighting. The project begins near the Ira Nelson Horticulture Center proceeds to Cajundome Blvd then parallels Cajundome Blvd to Eras | Transportation Enhancements | 2010-11-04 | 2010-12-06 | 2011-07-18 | 2011-11-30 | 61589.48 | 0.000
5646 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2804512 | This project will construct dedicated right and left turning lanes at the intersection of LA 3184 and Banks Street in the City of Lafayette. | Pavement Improvement | 2010-11-08 | 2010-12-01 | 2011-01-12 | 2011-02-21 | 278460 | 0.145
5647 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2808504 | This project will stabilize the roadway base and resurface the roadway on LA 733 from the junction at US 167 to the junction at LA 92. This project is located in Lafayette Parish. | Pavement Improvement | 2010-06-15 | 2010-08-02 | 2011-01-17 | 2011-07-13 | 2496470.96 | 4.426
5648 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809500 | This project will overlay University Ave. (La. 182) from Pinhook Road (La. 182) to Cameron St.(U.S. 90) in the City of Lafayette. | Pavement Improvement | 2011-05-06 | 2011-10-03 | 2011-11-21 |  | 724183.11 | 1.845
5649 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809507 | This Lafayette Parish project includes removing the exisiting deteriorated pavement, repairs, and placing new asphalt and shoulders along approximately 2 miles of LA 724 from Althea Drive to US 90. | Pavement Improvement | 2010-06-19 | 2010-09-30 | 2010-11-25 | 2011-03-02 | 1232187.36 | 1.948
5650 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809508 | This project will construct an addditional westbound left-turn lane at Pinhook and Carmel (LA 94) in Lafayette, LA. | Pavement Widening | 2010-06-02 | 2010-09-21 | 2010-10-19 | 2010-10-28 | 246604.16 | 0.001
5651 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809511 | This Lafayette Parish project will remove the deteriorated pavement, make repairs, and place new asphalt at the intersection of University Avenue (LA 182) and Cameron (US 90). | Pavement Improvement | 2010-07-06 | 2010-09-01 | 2010-12-22 |  | 2503458.6
5652 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809513 | This Lafayette Parish project will remove the deteriorated pavement, make repairs, and place new asphalt at the intersection of North University (LA 182) at Cameron (US 90). | Pavement Improvement | 2010-07-06 | 2010-09-01 | 2010-12-22 |  | 187586.23 | 0.157
5653 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809519 | This Lafayette Parish project will build a traffic roundabout at the intersection of Bonin Road and Milton Avenue (LA 92). | New Construction | 2010-06-05 | 2010-06-14 | 2010-08-09 | 2011-02-18 | 570987.84
5654 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2810504 | This project will overlay University Ave. (La. 182) from Railroad St. (Carencro) to I-49 in the City of Lafayette. | Pavement Improvement | 2010-10-11 | 2010-10-18 | 2010-12-20 | 2011-01-31 | 1385755.17 | 2.190
5655 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE |  | 03 | 2909501 | This Lafourche Parish project will construct a new vertical lift bridge with concrete towers to replace the existing deficient pontoon bridge. The new bridge will be constructed on a realigned section | Bridge Replacement | 2009-05-20 | 2009-05-20 | 2013-05-15 |  | 34069662.58 | 0.570
5656 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909504 | This project provides for the placement of new asphalt and new roadway striping along the existing 2 lane highway of LA 1 from just south of US 90 to Mathews in Lafourche Parish. The roadway will hav | Pavement Improvement | 2010-06-17 | 2010-08-11 | 2010-11-03 | 2011-01-18 | 1961153.54 | 2.450
5657 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909505 | Turn lanes will be installed at intersection of LA 1 and LA 308 in Lafourche Parish. | Pavement Improvement | 2010-06-27 | 2010-07-08 | 2010-08-05 | 2010-08-15 | 487429.56 | 0.001
5658 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909506 | The project consists of repairs and new ashpalt on the following streets in Lafourche Parish: Audubon Ave. (S. Acadia - Erwin Dr.), Menard St. (Audubon - Goode St.), Ridgefield Road (LA 1 - Plantation | Pavement Improvement | 2010-05-19 | 2010-06-01 | 2010-08-25 | 2010-08-26 | 1367241.87 | 3.500
5659 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909507 | New lighting and signs will be installed along LA 1 in the Town of Lockport in Lafourche Parish. | Safety/Traffic Management | 2010-05-26 | 2010-08-10 | 2010-09-28 | 2010-12-08 | 101586.9 | 0.001
5660 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909513 | This project consists of a new 6 foot bike and walking path in the city of Thibodaux from Bayou Lane to LA 648 (Percy Brown Rd.) in Lafourche Parish. The project will provide pedestrian access to a m | Transportation Enhancements | 2010-05-18 | 2010-05-18 | 2010-07-20 | 2010-08-05 | 208727.45 | 0.001
5661 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | LIVINGSTON | BATON ROUGE | 06 | 3207500 | This project consists of the removal of existing concrete sidewalks and replacement with decorative concrete pavers and is located on LA 15 (Range Road) from East Railroad Avenue and LA 1032 (Centervi | Transportation Enhancements | 2010-06-10 | 2010-07-12 | 2010-10-04 | 2011-03-07 | 257932.3 | 0.163
5662 | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | LIVINGSTON | BATON ROUGE | 06 | 3207506 | This project provides for pavement repair and new asphalt along portions of LA 1024 in Livingston Parish. | Pavement Improvement | 2010-03-30 | 2010-03-31 | 2010-09-01 | 2010-11-15 | 2336000 | 5.440
5663 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | LIVINGSTON | BATON ROUGE | 06 | 3209505 | This Design-Build project consists of widening the mainline of I-12 in Denham Spring, LA from four lanes to six lane from Pete's Hwy. to Juban Interchange in the eastbound direction, and from the Amit | New Construction | 2009-03-03 | 2009-11-08 | 2012-09-06 |  | 28756162.74 | 2.080
5664 | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | 3602513 | This project consists of the reconstruction of the existing roadway with new concrete pavement on Fleur De Lis Blvd from from Veterans Memorial Blvd to North of 30th St in Orleans Parish. | Pavement Improvement | 2009-11-11 | 2010-01-09 | 2010-10-16 |  | 7238577.42
5665 | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | 3609501 | This project will replace deteriorated and missing sections of fence and landscaping along the fence line along portions of Interstate 10 in New Orleans East, Orleans Parish. | Transportation Enhancements | 2010-09-13 | 2010-10-13 | 2011-03-02 |  | 1575194.16 | 5.010
5666 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA |  | 05 | 3701525 | This Ouachita Parish project on Caples Road will replace the existing deficient timber bridge over Longs Creek with a new concrete bridge. | Bridge Replacement | 2009-07-31 | 2009-07-31 | 2010-02-07 |  | 577623.46
5667 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA |  | 05 | 3701526 | This Ouachita Parish project on Sam Head Road will replace the existing deficient timber bridge over Bogaloosa Creek with a new concrete bridge. | Bridge Replacement | 2009-09-08 | 2009-10-10 | 2010-01-08 | 2010-06-23 | 326869.34
5668 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3707516 | The scope of the project is to patch the concrete pavement from the junction of LA 143 and LA 34 to the junction of LA 143 and US 80 and the junction of LA 143 and US 80 to the junction of LA 143 and | Pavement Improvement | 2010-11-22 | 2011-01-03 | 2011-04-04 | 2011-10-20 | 2033530.93 | 1.558
5669 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709503 | This Ouchita Parish project will widen Oliver Road from two lanes to three lanes and place new asphalt pavement, beginning at LA 840-6 to Tower Drive. The project will also fill a 7 foot deep ditch a | Pavement Improvement | 2010-06-20 | 2010-07-20 | 2010-11-23 | 2011-03-31 | 1749886.62 | 0.000
5670 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709504 | This work will repair and place new asphalt and striping along approximately 5.4 miles of the following streets in Ouachita Parish: Crosely St. - between Cypress and Black Bayou Canal. Downing Pines | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2010-09-27 |  | 1959694.07 | 4.210
5671 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709505 | This project will reconstruct and place new asphalt on Good Hope Road from LA 616 (Arkansas Road) to T. John Road in Ouachita Parish. | Pavement Improvement | 2010-06-09 | 2010-06-10 | 2010-07-22 |  | 740224.97 | 0.777
5672 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709506 | This project will place new asphalt of Dellwood Drive in the town of Richwood (Ouachita Parish) from US 165 to Blackwood Drive. | Pavement Improvement | 2010-08-11 |  | 2010-09-29 |  | 462291.29 | 0.538
5673 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709507 | This project will place new ashpalt on Louisiana Avenue in Ouachita Parish from Wallace Dean Road to Wallace Road. | Pavement Improvement | 2010-06-09 | 2010-06-09 | 2010-07-21 |  | 235618.75 | 0.250
5674 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709508 | This project in Ouachita Parish will place new asphalt pavement on Vancil Road from LA 838 to US 80. | Pavement Improvement | 2010-06-09 | 2010-06-14 | 2010-07-26 |  | 746224.96 | 1.184
5675 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709509 | This project will plalce new asphalt on Hadley Street in Ouachita Parish from Nutland Road to approximately 0.5 miles west. | Pavement Improvement | 2010-08-11 | 2010-08-08 | 2010-09-05 |  | 419774.71 | 0.482
5676 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709512 | Riverside Dr. (Park Ave. to Louisville Ave.) - Repair roadway and place new asphalt from Bres St. to Louisville. Washington St.- (Walnut to North 14 th St.) Remove deteriorated concrete and replace | Pavement Improvement | 2010-07-09 | 2010-08-08 | 2010-10-17 |  | 683497.16 | 0.880
5677 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709513 | The City of Monroe will place new asphalt on approximately 1.4 miles of Riverside Drive from Park Avenue to Louisiville in Ouachita Parish. | Pavement Improvement | 2010-07-09 | 2010-08-18 | 2010-09-15 |  | 652679.95 | 0.001
5678 | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | PLAQUEMINES | NEW ORLEANS | 03 | 3809500 | This project will widen the roadway and place new asphalt along portions of Woodland Hwy (LA 406) in Plaquemines Parish. | Pavement Widening | 2010-06-01 | 2010-07-06 | 2010-08-24 | 2011-10-21 | 1190336.45 | 1.858
5679 | Underway | C950 | Ferryboat | LOUISIANA | STATEWIDE |  |  | 3809504 | This project will replace the Plaquemine Parish Ferry boat engines with energy efficient and alternative fuel engines. These engines will improve emissions from the ferry. | Other | 2011-10-10 | 2011-10-12 | 2012-04-09 |  | 1936097.25
5680 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | RAPIDES | ALEXANDRIA | 05 | 4003530 | This project will construct sidewalks in the Town of Woodworth along Castor Plunge Road from Mason Rue Drive to Langston Drive, US 165 from Castor Plunge Road to a point approximately 1700' south of C | Transportation Enhancements | 2010-06-12 | 2010-06-24 | 2010-08-19 | 2010-11-08 | 262448.67 | 0.200
5681 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | RAPIDES | ALEXANDRIA | 05 | 4007507 | The scope of the project is to remove 6 in of the asphalt pavement and overlay the travelway with 6 inches of asphaltic concrete from the junction of US 167 and the southern junction of LA 3225 to the | Other | 2010-10-28 | 2011-04-11 | 2011-10-10 |  | 1064598.29 | 4.187
5682 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | RAPIDES | ALEXANDRIA | 05 | 4008508 | This project will remove and upgrade with new impacts attenuator in four sites in Alexandria, LA. The locations of the sites are I-49 (2 sites), US 167 (1 site)), and US 71 (1 site). | Safety/Traffic Management | 2010-05-10 | 2010-06-09 | 2010-07-28 | 2010-07-27 | 308975.34 | 0.000
5683 | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | 4409500 | This St. Bernard Parish project will improve drainage on LA 46 near Fortification Canal and ends at Paris Road. | Pavement Improvement | 2010-08-08 | 2010-10-13 | 2011-03-09 |  | 2235726.96 | 1.250
5684 | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST CHARLES | NEW ORLEANS | 03 | 4502500 | This project will construct a bike and walking path on the St. Charles Parish West Bank Mississippi River levee between Davis Drive in Luling to Elm Street in Hahnville. | Transportation Enhancements | 2009-09-08 | 2009-10-08 | 2009-12-10 | 2010-10-12 | 1761764.79
5685 | Completed | C240,C230 | Highway Infrastructure Investment Grant | LOUISIANA | ST CHARLES | NEW ORLEANS | 03 | 4508502 | This poject will place new asphalt along 1.4 miles of LA 3127 in Saint Charles Parish between Log mile 9.7 and Interstate 310 in St. Charles Parish. | Pavement Improvement | 2010-01-25 | 2010-02-24 | 2010-04-07 | 2010-04-14 | 861400.98 | 1.210
5686 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST MARTIN |  | 03 | 5003501 | This St. Martin Parish project in the City of Breaux Bridge on Refinery Road will replace the existing deficient timber bridge over Bayou Teche with a new concrete bridge. | Bridge Replacement | 2009-06-15 | 2009-06-15 | 2010-03-15 |  | 1970496.09
5687 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5204526 | This project will construct sidewalks in the Town of Abita Springs along LA 435 (Main Street) from Hickory Street to Pine Street, Level Street from LA 36 to Magnolia Street and along the old railroad | Transportation Enhancements | 2010-08-06 | 2010-08-31 | 2010-12-14 | 2011-11-02 | 238941.19 | 0.343
5688 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5204528 | This St. Tammany Parish project will improve access at the LA 59 and Interstate 12 interchange by providing new turn lanes on LA 59 and widening of the ramp onto I-12. | Pavement Improvement | 2009-08-22 | 2009-11-02 | 2010-03-22 | 2010-08-16 | 2792816.87 | 0.530
5689 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5207509 | This project will construct of a new two-lane roadway along I-10 between US190B and LA 433 in Slidell. | New Construction | 2010-12-07 | 2010-12-10 | 2011-12-30 |  | 3140785.84 | 1.015
5690 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5208511 | This project located in the City of Covington, LA in St. Tammany Parish involve milling and overlaying the asphalt section of the roadway and cleaning and sealing the joints and cracks in the concrete | Pavement Improvement | 2010-05-14 | 2010-06-08 | 2010-08-03 | 2010-10-08 | 798019.28 | 1.595
5691 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209503 | This St. Tammany Parish project located near Pearl River will widen the existing I-59 exit and entrance ramps and portions of LA 1090 at I-59. The project will provide additional turn lanes at the ex | Pavement Improvement | 2009-09-08 | 2009-09-17 | 2009-10-29 | 2010-12-16 | 1360168.24 | 0.440
5692 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5209504 | This St. Tammany Parish project will improve traffic operations by constructing turn lanes and widening ramps at the US 11/I-12 interchange in Slidell, LA. | Pavement Improvement | 2009-09-25 | 2009-10-26 | 2010-06-13 |  | 5486782.65 | 1.430
5693 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5209505 | This St. Tammany Parish project is located in Covington and will construct an additional left turn lane for Northbound US 190 traffic turning onto westbound Park Drive. | Pavement Widening | 2010-07-06 | 2010-07-06 | 2011-05-12 |  | 402363.6 | 0.380
5694 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209506 | This St. Tammansy Parish project located in Slidell will construct a right turn lane from LA 1090 on to Brownswitch Road. | Pavement Improvement | 2010-06-24 | 2010-06-24 | 2011-05-23 |  | 817013.29 | 0.194
5695 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209507 | This St. Tammany Parish project located in Slidell will convert the existing intersection of LA 1091 and Brownswitch Road into a traffic roundabout. | Pavement Widening | 2010-06-24 | 2010-06-24 | 2011-01-07 |  | 1260101.2 | 0.110
5696 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5209508 | This project is located in the Covington/ Madisonville area of St. Tammany Parish. The project will construct additional left and right turn lanes at LA 21 and Brewster Road. | Pavement Widening | 2010-07-26 | 2010-07-26 | 2010-11-08 | 2011-10-14 | 1575045.82 | 0.000
5697 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209509 | This St. Tammany Parish project is located in Slidell and includes widening LA 433 to provide additional right turn lanes onto I-10 and Voters Road. | Pavement Widening | 2010-07-06 | 2010-08-09 | 2011-08-03 |  | 1824168.37
5698 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5209511 | This St. Tammany Parish project is located near Covington and includes new pavement and turn lanes at the I-12/ LA 21 interchange. | Pavement Widening | 2010-07-26 | 2010-07-26 | 2011-02-11 | 2011-10-14 | 5096119.07 | 0.680
5699 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209528 | This project in Slidell, LA in St. Tammany Parish will overlay LA 433 from 3.4 Mi South of US 190 to 1.06 Mi North US 11. This project is joint with federal project number ERP1(149)(150)(151) & ARR-52 | Pavement Improvement | 2010-07-13 | 2010-08-12 | 2010-12-30 | 2011-08-01 | 1916541.4 | 6.460
5700 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209529 | This project in Slidell, LA in St. Tammany Parish will overlay LA 1090 from 0.15 Mi North of US 190 to the I-59 Ramps. This project is joint with federal project number ERP1(149)(150)(151) & ARR-5209( | Pavement Improvement | 2010-07-13 | 2010-08-12 | 2010-12-30 | 2011-08-01 | 991470.86 | 4.300
5701 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | TANGIPAHOA |  | 01 | 5302508 | The Tangipahoa Parish project in the City of Hammond on J.W. Davis Road will replace the existing deficient timber bridge over a canal with a concrete bridge. | Bridge Replacement | 2009-06-29 | 2009-06-29 | 2010-03-10 |  | 1110196.58
5702 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | TANGIPAHOA |  | 01 | 5302509 | This Tangipahoa Parish project on Little Italy Road will replace the existing deficient timber bridge over a creek with a concrete bridge. | Bridge Replacement | 2009-06-29 | 2009-08-17 | 2010-02-08 | 2010-02-03 | 509169.94
5703 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | TANGIPAHOA |  | 01 | 5302510 | This project in Tangipahoa Parish on Bennett Road will replace the existing deficient concrete bridge over Natalbany Creek with a new concrete bridge. | Bridge Replacement | 2009-07-09 | 2009-07-09 | 2010-01-04 |  | 661884.18
5704 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | TANGIPAHOA |  | 01 | 5302511 | This project in Tangipahoa Parish on Cooper Road will replace the existing deficient timber bridge over Cooper Creek with a new concrete bridge. | Bridge Replacement | 2009-07-13 | 2009-07-28 | 2009-12-05 | 2010-01-28 | 473240.56
5705 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | TERREBONNE | HOUMA | 03 | 5509505 | This Terrebonne Parish project will repair and place new asphalte along approximately 5.4 miles of the following streets: Alma Street, Country Drive, Klondyke Road, Southdown Mandalay Road, Westside B | Pavement Improvement | 2010-06-04 | 2010-07-08 | 2010-08-26 | 2010-08-30 | 965547.61 | 4.510
5706 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | TERREBONNE | HOUMA | 03 | 5509506 | This project in Terrebonne Parish will repair and replace 7.3 miles of existing concrete pavement on the following roads: Acadian Avenue , Alma Street , Bayou Gardens Blvd., Corporate Drive, and Dunn | Pavement Improvement | 2010-07-28 | 2010-08-27 | 2010-12-24 |  | 1695458.33 | 0.001
5707 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | TERREBONNE | HOUMA | 03 | 5509507 | This project in Terrebonne Parish will construct turn lanes at the following 10 intersections: Bayou Gardens at West Park, Corporate Dr. at MLK Blvd., Corporate Dr. at West Tunnel Blvd., Coteau Rd. at | Pavement Improvement | 2010-06-02 | 2010-06-02 | 2011-02-24 |  | 1084116.71 | 0.001
5708 | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | TERREBONNE | HOUMA | 03 | 5510501 | This project in Terrebonne Parish will repair and replace 4.2 miles of existing concrete pavement on various roads in Terrebonne parish. | Pavement Improvement | 2010-10-15 | 2010-11-15 | 2011-04-11 |  | 1628084.53 | 0.010
5709 | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | 6033009 | This Orleans Parish project consists of reconstructing and widening of Earhart Boulevard from Hamilton St to Fern St. | Pavement Improvement | 2009-11-11 | 2010-01-04 | 2011-02-18 |  | 12622195.91
5710 | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | WEST BATON ROUGE | BATON ROUGE | 06 | 6109503 | In West Baton Rouge Parish, a ramp will be added to the LA 1 northbound acceleeration lane at Emily Drive. | Pavement Widening | 2010-04-20 | 2010-04-26 | 2010-06-07 | 2010-09-30 | 382928.79 | 0.240
5711 | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | WEST CARROLL |  | 05 | 6204500 | This West Carroll Parish project on Lingo Loop Road will replace the existing deficient timber bridge over Mill Bayou with a new concrete bridge. | Bridge Replacement | 2009-08-05 | 2009-08-05 | 2010-03-06 |  | 400743.18 | 0.157
5712 | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | WEST CARROLL |  | 05 | 6204501 | This West Carroll Parish project on Wood Road will ieplace the existing deficient timber bridge over Alligator Bayou with a new concrete bridge. | Bridge Replacement | 2009-09-02 | 2009-10-12 | 2010-02-04 | 2010-05-19 | 385020.95 | 0.000
5713 | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | RAPIDES | ALEXANDRIA | 05 | 7869002 | Susek Drive is an existing two lane roadway in the northeast portion of Pineville, Louisiana in Rapides Parish. 2.2 miles of the roadway is to be reconstructed to two 12 foot lanes with curbs. The pro | Pavement Improvement | 2009-09-14 | 2009-10-14 | 2010-11-18 | 2011-02-25 | 9508463.65 | 0.151
5714 | Underway | C950 | Ferryboat | LOUISIANA | STATEWIDE |  |  | 9909525 | This Iberville Parish project will replace the existing landing barge of the Plaquemine/Sunshine Ferry winch system with a hydraulically actuated ramps to provide a more reliable operation. | Other | 2012-01-23 |  | 2012-05-28 |  | 615000
5715 | Completed | C240,C950 | Highway Infrastructure Investment Grant | LOUISIANA | STATEWIDE |  |  | 9909526 | This project will replace the existing navigational radar systems on both the Plaquemine/Sunshine Ferry and the St. Francisville/New Roads Ferry with a modern systems that will provide a safer operati | Other | 2010-01-25 | 2010-01-25 | 2010-06-24 | 2010-09-30 | 300000
5716 | Completed | C950 | Ferryboat | LOUISIANA | STATEWIDE |  |  | 9909527 | This Iberville Parish project will replace the existing main engine reduction gears on the M/V Ascension and will provide improved vessel speed and reliability. | Other | 2010-03-15 | 2010-07-29 | 2010-09-09 | 2010-09-15 | 305832.75
5717 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1048 | This Orelans Parish project consists of removing deteriorated pavement and placing new asphalt and striping on Leon C Simon Dr from London Ave Canal to Elysian Fields Ave. in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 |  | 95456.18
5718 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1050 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Mirabeau Ave from St. Bernard Ave to Elysian Fields Ave. in New Orlea | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 |  | 607341.22
5719 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1051 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Filmore Ave from St. Bernard Ave to Elysian Fields Ave. in New Orlean | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 |  | 662825
5720 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1052 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on St. Bernard Ave from I-610 to Filmore Ave. in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 |  | 531334.23
5721 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1053 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Paris Ave from I-610 to Mirabeau Ave. in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 |  | 560927.71
5722 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1054 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Elysian Fields from Lakeshore Dr to US 90 in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 |  | 1003155.45
5723 | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1056 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Carrolton Avenue at I-10 and Claiborne Avenue (US 90) in the City of New Orleans. | Transportation Enhancements | 2010-01-08 | 2010-01-17 | 2010-06-16 | 2010-09-29 | 492080.83
5724 | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1057 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Carrolton Avenue at Claiborne (US 90) and St. Charles Avenues in the City of New Orleans. | Transportation Enhancements | 2010-01-08 | 2010-01-17 | 2010-06-16 | 2010-09-29 | 814802.06
5725 | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1063 | This Orleans Parish project will construct sidewalks on Nashville from Claiborne to Tchoupitoulas in New Orleans. | Transportation Enhancements | 2009-10-06 | 2009-11-09 | 2010-05-28 | 2010-12-04 | 974878
5726 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1067 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Lasalle St. from Poydras St. to Tulane Ave. in New Orleans, LA. The project will overlay the street and add | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 428346.32
5727 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1068 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Gravier St. from Loyola Ave. to St. Peters St. in New Orleans, LA. | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 22036.72
5728 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1069 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Common St. from Loyola Ave. to St. Peters St. in New Orleans, LA. The project will overlay the street and p | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 776930.93
5729 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1071 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Magazine St. from Canal St. to US 90 Hwy. in New Orleans, LA. The project will overlay the street and parki | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 270462.51
5730 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1072 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Camp St.. from Canal St. to US 90 Hwy. in New Orleans, LA. The project will overlay the street and parking | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 334956.83
5731 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1075 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Loyola Ave. from Canal Street to US 90 Hwy. in New Orleans, LA. The project will overlay the street and par | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 1607566.25
5732 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1076 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Poydras St. from Lasalle St. to Loyola Ave. in New Orleans, LA. The project will overlay the street. T | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 3772.32
5733 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1084 | This project will provide for the construction of sidewalks on Mehle Avenue in the city of Arabi (St. Bernard Parish) from LA 46 to LA 39. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 103019.91
5734 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1120 | This project will provide for the construction of sidewalks on Rowley Boulevard in the city of Arabi (St. Bernard Parish) from LA 46 to LA 39. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 164364.32
5735 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1122 | This project will provide for the construction of sidewalks on Cougar Drive in the city of Arabi (St. Bernard Parish) from Benjamin Street to Genet Drive. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 238095.66
5736 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1124 | This project will provide for the construction of sidewalks on East Genie Street in the city of Chalmette (St. Bernard Parish) from Golden Drive to Palmisano Boulevard. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 158820.61
5737 | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1125 | This project will provide for the construction of sidewalks on Packenham Drive in the city of Chalmette ( St. Bernard Parish) from North Derbigny Street to West Genie Street. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 125304.41
5738 | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | STATEWIDE |  |  | LA03003 | This project will provide four informational kiosks in the towns of Vivian, Plain Dealing, Sarepta, and Homer in Caddo, Bossier, Webster, Claiborne Parishes. | Transportation Enhancements | 2009-08-18 | 2009-09-28 | 2010-06-07 | 2010-03-11 | 204285.98 | 0.001
5739 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1001700 | Lisbon, Sabattus, Rt 9. Reconstruction of 6.75 miles of Route 9 beginning 0.33 of a mile northerly of Route 196 and extending northeasterly 6.75 miles to the Maine Turnpike Overpass. Work involves g | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2011-07-31 | 2011-07-31 | 9445926.63 | 6.750
5740 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1015800 | Portland, Veranda Street Bridge, Replacement of Veranda Street Overpass Bridge over Canadian Railroad | Bridge Improvement | 2009-05-06 | 2009-05-06 | 2010-02-28 | 2010-02-28 | 1440783.72 | 0.000
5741 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | HANCOCK |  | 02 | 1107200 | Ellsworth, Route 1A. Reconstruction of 2.67 miles of Route 1A beginning at the Rabbit Road and extending southeasterly 2.67 miles to 0.15 of a mile northerly of the Old Bangor Road. Work includes gra | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2011-06-30 | 2011-06-30 | 6920925.54 | 2.670
5742 | Completed | C220 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND | PORTLAND | 01 | 1184400 | Portland, Bayside Trail. This project will design an extension of the Portland Trails system through the Bayside area of Portland along the abandoned Union Branch Rail Line extending from the Eastern | Transportation Enhancements | 2009-08-11 | 2009-08-11 | 2009-09-30 | 2009-09-30 | 800000
5743 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | WALDO |  | 01 | 1267600 | Lincolnville, Knights Hill Culvert Replacement on Route 52 over Meservy Brook | Bridge Improvement | 2009-05-21 | 2009-05-21 | 2009-10-12 | 2009-10-12 | 250875.15 | 0.000
5744 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1273700 | Auburn, Joline Drive Intersection Improvement with a signal at the intersection of Center Street, Joline Street, and Stetson Street | Safety/Traffic Management | 2009-05-28 | 2009-05-28 | 2009-12-31 | 2009-12-31 | 567134.95 | 0.000
5745 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1277700 | Turner, Route 117. Reconstruction of 2.39 miles of Route 117 including grading, paving, drainage and guardrail improvements. | Pavement Improvement | 2009-07-22 | 2009-07-22 | 2009-09-20 | 2009-09-20 | 2626122.1 | 2.390
5746 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1305900 | Auburn, Joline Drive. Reconstruction of 0.18 of a mile beginning at Center Street and extending westerly to Turner Street. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-11-30 | 2009-11-30 | 375053.37 | 0.180
5747 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1306100 | Lewiston, Russell Street. Reconstruction of 0.51 miles beginning at the convergence of the ramps to Main Street, extending easterly to Robinson Gardens. This project will include construction of left | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-11 | 2009-10-11 | 2319473.41 | 0.510
5748 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1308500 | Biddeford, Route 111. Highway resurfacing beginning at Main Street (Route 9) and extending westerly 0.97 of a mile to 0.10 of a mile easterly of Marshall Avenue. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 480144.37 | 0.970
5749 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1308600 | Biddeford, Route 9. Highway resurfacing beginning at Parkside and extending 0.95 of a mile to Alfred Street. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 402115.46 | 0.950
5750 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1310400 | Portland, Auburn Street. Intersection improvement with signal located at the intersection of Auburn Street and Lyseth Moore Drive. | Safety/Traffic Management | 2009-07-02 | 2009-07-02 | 2009-12-31 | 2009-12-31 | 249274.85 | 0.000
5751 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1311100 | Saco, North Street. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile northerly of Park Street and extending 1.00 mile to 0.34 of a mile southerly of Hillview Avenue. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 261078.23 | 1.000
5752 | Completed | C220 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1334100 | Biddeford-Kennebunk, Eastern Trail, Construct a bicycle/pedestrian trail from Rt. 111 in Biddeford to Route 35 in Kennebunk. | Transportation Enhancements | 2009-09-14 | 2009-09-14 | 2010-07-31 | 2010-07-31 | 1466570.32
5753 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1480600 | Portland, Cumberland Avenue. Highway resurfacing beginning at Franklin Arterial and extending 0.29 of a mile to Elm Street. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-09-30 | 2009-09-30 | 135249.13 | 0.290
5754 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1480700 | Westbrook, Eisenhower Drive. Highway resurfacing beginning at Saco Street and extending 0.88 of a mile to Spring Street. Includes shoulder resurfacing. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-08-31 | 2009-08-31 | 571096.46 | 0.870
5755 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1480800 | Saco, Beach Street-Ferry Road. Pave a 3/4" hot mix asphalt overlay beginning at North Street and extending 1.11 miles to Pine Ridge Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 220068.84 | 1.110
5756 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1480900 | Falmouth, Brook Road. Pave a 1 1/4" hot mix asphalt overlay beginning at the Westbrook town line and extending 0.74 of a mile to the Leighton Road. The project will include drainage and the installa | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-08-31 | 2009-08-31 | 510643.74 | 0.480
5757 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1481100 | Portland, Westbrook Street. Pave a 1 1/4" hot mix asphalt overlay beginning at the Westbrook town line and extending 0.89 miles to Congress Street. Project includes alteration of 24 catch basins and | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-09-30 | 2009-06-16 | 270039.73 | 0.890
5758 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | SAGADAHOC |  | 01 | 1511450 | Interstate I-295 Northbound, Brunswick to Gardiner. This project involves reconstruction of the roadway including grinding and rubblizing the existing concrete roadway, grading and paving, drainage a | Pavement Improvement | 2009-03-03 | 2009-03-03 | 2009-10-10 | 2009-10-10 | 33454719.51 | 23.880
5759 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1511460 | Interstate I-295 Northbound, Topsham to Gardiner. This project involves building the crossovers from the northbound lanes to the southbound lanes as part of the traffic detour for the I-295 northboun | Safety/Traffic Management | 2009-03-30 | 2009-03-30 | 2009-10-06 | 2009-10-06 | 1750713.75
5760 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | LINCOLN |  | 01 | 1561300 | Damariscotta, Salt Bay Steel Culvert Bridge Replacement over Oyster Creek, located on Belvedere Road at the Damariscotta-Nobleboro town line. | Bridge Replacement | 2009-05-29 | 2009-05-29 | 2009-10-08 | 2009-10-08 | 556041.3 | 0.000
5761 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1561400 | Hallowell, Second Street Bridge Rehabilitation over Maine Central Railroad. Replace existing deck and repair concrtete bridge abutments and retaining walls. | Bridge Replacement | 2009-05-05 | 2009-05-05 | 2010-03-30 | 2010-03-30 | 1141869.82 | 0.000
5762 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1562700 | Township 2 Region 8, Lincoln Spur Bridge Deck Replacement located over Interstate 95 northbound and southbound. Replace existing deck and install new safety barriers. | Bridge Improvement | 2009-04-24 | 2009-04-24 | 2009-10-11 | 2009-10-11 | 1381645.06 | 0.000
5763 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | HANCOCK |  | 02 | 1568900 | Sullivan, Route 1. Intersection Improvements including construction of a bypass lane located at the intersection of Route 1 and the Ashville Road. | Safety/Traffic Management | 2009-06-24 | 2009-06-24 | 2009-08-31 | 2009-08-31 | 333762.89 | 0.000
5764 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | OXFORD |  | 02 | 1571600 | Lovell, Main Street. Pave a 3/4" hot mix asphalt overlay beginning 0.82 of a mile north of Christian Hill Road and extending northerly 1.66 miles to 0.12 of a mile south of West Lovell Road. | Pavement Improvement | 2009-04-14 | 2009-04-14 | 2009-10-09 | 2009-10-09 | 314135.24 | 1.660
5765 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1571900 | Sebago, Sebago Road. Pave a 3/4" hot mix asphalt overlay beginning at Shore Road and extending northerly 0.90 miles to 0.17 of a mile northerly of Woodland Road. | Pavement Improvement | 2009-04-14 | 2009-04-14 | 2009-10-09 | 2009-10-09 | 256174.01 | 0.910
5766 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1572000 | Standish, Route 114. Pave a 3/4" hot mix asphalt overlay eginning 0.16 of a mile north of Route 35 and extending northerly 6.50 miles to 0.94 of a mile south of the Standish-Sebago town line. | Pavement Improvement | 2009-04-14 | 2009-04-14 | 2009-10-09 | 2009-10-09 | 1113743.39 | 6.500
5767 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1573700 | Clinton, Baker Street. Pave a 3/4" hot mix asphalt overlay beginning at Route 11 and extending northerly 1.16 miles. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-05 | 2009-10-05 | 412622.83 | 1.160
5768 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1573900 | Fairfield, Route 23. Pave a 3/4" hot mix asphalt overlay beginning at Route 201 and extending northerly 0.65 of a mile to 0.19 of a mile northerly of Pishon Ferry Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 109772.21 | 0.650
5769 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1574600 | Oakland, Fairfield Street. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile northerly of Greeley Street and extending northerly 0.85 of a mile to 0.30 of a mile northerly of Municipal Dri | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-06 | 2009-10-06 | 149679.76 | 0.850
5770 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1574700 | Oakland, Pleasant Street. Pave a 3/4" hot mix asphalt overlay beginning at Oak Street and extending easterly 0.37 of a mile to Route 11. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 84434 | 0.370
5771 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1575000 | Randolph, Route 9. Pave a 3/4" hot mix asphalt overlay beginning 0.05 of a mile westerly of the Chelsea-Randolph town line and extending easterly 3.67 miles to 0.10 of a mile easterly of the Augusta- | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-05 | 2009-10-05 | 644358.28 | 3.590
5772 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1575700 | Waterville, Oak Street. Pave a 3/4" hot mix asphalt overlay beginning at Main Street and extending easterly 0.46 of a mile to College Avenue. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-05 | 2009-10-05 | 118203.23 | 0.460
5773 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | FRANKLIN |  | 02 | 1576500 | Eustis, Route 27. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile south of Route 16 and extending northerly 1.26 miles. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-09-30 | 2009-09-30 | 225493.06 | 1.260
5774 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1577000 | Jackman, Route 6. Pave a 3/4" hot mix asphalt overlay beginning 2.19 miles westerly of the Long Pond Twp town line and extending easterly 2.19 miles. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 610508.12 | 2.190
5775 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | PISCATAQUIS |  | 02 | 1577400 | Sapling Township., Rockwood Road. Pave a 3/4" hot mix asphalt overlay beginning 0.05 of a mile westerly of the Sapling Township-Big Moose Township town line and extending easterly 6.10 miles to 0.46 | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 1108456.26 | 6.100
5776 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1579000 | Palmyra, Ell Hill Road. Pave a 3/4" hot mix asphalt overlay beginning at Somerset Avenue and extending northerly 6.27 miles to 0.03 of a mile northerly of Ford Hill Road. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-10 | 2009-10-10 | 1200725.15 | 6.270
5777 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | AROOSTOOK |  | 02 | 1579700 | Caswell, Van Buren Road. Pave a 3/4" hot mix asphalt overlay beginning 0.29 of a mile southerly of the Hamlin town line and extending northerly 5.69 miles to 1.18 miles southerly of Albert Cyr Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-08 | 2009-10-08 | 1626515.89 | 5.620
5778 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1581400 | Auburn, Turner Street. Pave a 3/4" hot mix asphalt overlay beginning at Center Street and extending northerly 1.08 miles to 0.30 of a mile southerly of Mount Auburn Avenue. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-07-31 | 2009-07-31 | 441956.29 | 1.080
5779 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1583000 | Gardiner, Water Street. Pave a 3/4" hot mix asphalt overlay beginning at Cobbossee Avenue and extending easterly 1.10 miles to Route 201. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-09 | 2009-10-09 | 278105.84 | 1.100
5780 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1583100 | Litchfield, Route 9. Pave a 3/4" hot mix asphalt overlay beginning 0.17 of a mile westerly of the Huntington Hill Road and extending easterly 3.99 miles to 0.06 of a mile westerly of the Bog Hill Roa | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-09 | 2009-10-09 | 710362.86 | 4.010
5781 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1583200 | Oakland, Route 11. Grind and remove 1 1/4" of existing pavement and replace with a 1 1/4" hot mix asphalt overlay beginning at Route 23 and extending northerly 4.46 miles to 0.01 of a mile northerly | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 832344.31 | 4.460
5782 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1584000 | West Gardiner, Lewiston Road. Pave a 1 1/4" hot mix asphalt overlay beginning 0.42 of a mile westerly of the I-95 Exit 102 On-ramp and extending easterly 1.69 miles to 0.11 of a mile westerly of the | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-09 | 2009-10-09 | 694099.47 | 1.690
5783 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1584300 | Fairfield, Norridgewock Road. Grind and remove 1 1/4" of the existing pavement and replace with a 1 1/4" hot mix asphalt overlay beginning 1.87 miles west of Routes 104/139 and extending westerly 4.75 | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-07 | 2009-10-07 | 982929.08 | 4.750
5784 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | FRANKLIN |  | 02 | 1584900 | New Sharon, Route 27. Pave a 3/4" hot mix asphalt overlay beginning 0.38 of a mile southerly of York Hill Road and extending northerly 2.65 miles to Route 2. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-10 | 2009-10-10 | 503054.29 | 2.650
5785 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1585100 | Bangor, Broadway. Pave a 3/4" hot mix asphalt overlay beginning at the Interstate 95 southbound Exit 185 ramps and extending northerly 0.65 of a mile to Grandview Avenue. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-08 | 2009-10-08 | 195400.46 | 0.560
5786 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1585300 | Bangor, Hogan Road. Grind and remove 1 1/4" of existing asphalt and replace with a 1 1/4" of hot mix asphalt overlay beginning 0.10 miles southerly of the intersection of Mt. Hope and extending north | Pavement Improvement | 2009-07-08 | 2009-07-08 | 2009-08-31 | 2009-08-31 | 365424.16 | 1.240
5787 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | WASHINGTON |  | 02 | 1586200 | East Machias, Route 1. Pave a 3/4" hot mix asphalt overlay beginning 0.37 of a mile northerly of Chase Mills Road and extending northerly 1.00 mile to 0.47 of a mile northerly of the Whiting town lin | Pavement Improvement | 2009-07-21 | 2009-07-21 | 2010-06-30 | 2010-06-30 | 248400.68 | 1.000
5788 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1587500 | Pittsfield, Park Street. Grind and remove 1 1/4" of existing asphalt and replace with a 1 1/4" hot mix asphalt overlay beginning at North Main Street and extending northerly 0.19 of a mile to Somerse | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-10 | 2009-10-10 | 59466.89 | 0.190
5789 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1588200 | Auburn, Route 202. Pave a 3/4" hot mix asphalt overlay beginning at Minot Avenue and extending northerly 0.68 of a mile to Lisbon Street. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-07-31 | 2009-07-31 | 326182.83 | 0.680
5790 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1588500 | Auburn, Minot Avenue. Pave a 3/4" hot mix asphalt overlay beginning at High Street and extending northerly 0.51 of a mile to Court Street. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-07-31 | 2009-07-31 | 237075.93 | 0.510
5791 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1589100 | Interstate I-295 Southbound, Freeport. Work involves replacing culvert underneath I-295 Exit 22 on and off ramps. | Bridge Improvement | 2009-07-07 | 2009-07-07 | 2009-10-31 | 2009-10-31 | 157702.76 | 0.060
5792 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1590100 | Portland, Forest Avenue. Grind and remove 1 1/4" existing asphalt and replace with 1 1/4" hot mix asphalt beginning at Warren Avenue and extending northerly 1.15 miles to Castine Avenue. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-09-30 | 2009-09-30 | 622405.85 | 0.980
5793 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1590300 | Interstate I-295 Southbound, Portland. Paving 0.42 miles beginning 0.13 of a mile north of the Washington Avenue Southbound on-ramp. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-08-31 | 2009-08-31 | 78623.69 | 0.420
5794 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | LINCOLN |  | 01 | 1591800 | Edgecomb, Route 1. Pave a 3/4" hot mix asphalt overlay beginning 0.08 of a mile northerly of Eddy Road and extending northerly 1.02 miles to 0.05 of a mile northerly of Cochran Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-07 | 2009-10-07 | 468887.16 | 1.020
5795 | Underway | C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1593200 | Caratunk, Route 201. Pave a 3/4" hot mix asphalt overlay beginning 3.74 miles southerly of the The Forks Plantation town line and extending northerly 3.77 miles. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 |  | 591821.06 | 3.770
5796 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | FRANKLIN |  | 02 | 1593300 | Farmington, Route 2. Grind and remove 1 1/4" of existing pavement and replace with 1 1/4" of hot mix as[halt beginning 500 feet west of the bridge to Prescott Street; Route 2/4/27 intersection to Hil | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-10 | 2009-10-10 | 524745.26 | 2.870
5797 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1593600 | Moose River, Route 201. Pave a 3/4" hot mix asphalt overlay beginning 0.26 of a mile northerly of Sandy Stream Road and extending northerly 13.65 miles to the Canadian border. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 2219537 | 13.650
5798 | Completed | C250 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1594100 | West Forks Plantation., Route 201. Pave a 3/4" hot mix asphalt overlay beginning 0.16 of a mile southerly of the Parlin Pond Township town line and extending northerly 13.62 miles to 2.60 miles north | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 2181878.85 | 13.620
5799 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1594300 | Bangor, Broadway (Route 15). Pave a 3/4" hot mix asphalt overlay beginning 325' easterly of the I-95 northbound Exit 185 ramps and extending northerly 0.23 of a mile to the I-95 southbound Exit 185 r | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-08 | 2009-10-08 | 81914.56 | 0.230
5800 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1594800 | Hampden, Route 202. Pave a 3/4" hot mix asphalt overlay beginning at Western Avenue and extending northerly 4.02 miles to the Interstate 395 Exit 2 eastbound ramps. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-08 | 2009-10-08 | 875407.88 | 4.020
5801 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1595300 | Interstate I-95 Southbound, Mattamiscontis Township to Howland. 10.37 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-07 | 2009-10-07 | 4388130.22 | 10.370
5802 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1595400 | Interstate I-95 Southbound, Township 2 Region 8 NWP to Mattamiscontis Township. 7.06 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-06 | 2009-10-06 | 2486534.02 | 7.060
5803 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | MAINE | HANCOCK |  | 02 | 1669600 | Deer Isle-Sedgwick Bridge Substructure Rehabilitation over Eggemoggin Reach, located on the Deer Isle-Sedgwick town line. Repair bridge tower piers. | Bridge Improvement | 2009-09-16 | 2009-09-16 | 2010-10-31 | 2010-10-31 | 10259705.39 | 0.000
5804 | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | KNOX |  | 01 | 1674500 | South Thomaston, Spruce Head Bridge Replacement on Island Road. | Bridge Replacement | 2009-08-19 | 2009-08-19 | 2010-05-31 | 2010-05-31 | 2222968.88 | 0.000
5805 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1677500 | Interstate I-95 Southbound, Howland to Old Town. 15.6 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2010-10-07 | 2010-10-07 | 4436476.21 | 15.600
5806 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | MAINE | AROOSTOOK |  | 02 | 1681910 | Interstate I-95 Northbound - highway resurfacing beginning 2.86 miles north of the Oakfield/Smryna town line and extends northerly 13.64 miles to the Canadian border. | Pavement Improvement | 2010-02-04 | 2010-05-15 | 2010-10-31 | 2010-10-31 | 6493467.9
5807 | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1682200 | Interstate I-95 Southbound, Township 2 Region 9 NWP to Township 2 Region 8 NWP. 8.22 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2010-10-07 | 2010-10-07 | 2426558.11 | 8.220
5808 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | WASHINGTON |  | 02 | 1698300 | Lubec, Route 189. Pave a 1-1/4" hot mix asphalt overlay beginning at the intersection of Route 1 and extending easterly approximately 6.7 miles. | Pavement Improvement | 2009-07-21 | 2009-07-21 | 2010-06-30 | 2010-06-30 | 3697666.25 | 11.190
5809 | Completed | C220 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1700800 | South Portland-Portland, Long Creek Watershed. Pavement treatment on Maine Mall Road designed to enhance treatment of stormwater runoff in an urban impaired stream watershed as recommended by the Lon | Other | 2009-06-29 | 2009-06-29 | 2009-12-31 | 2009-12-31 | 1655990.68
5810 | Completed | C490 | OJT/SS | MAINE | STATEWIDE |  |  | 1736501 | On the Job Training/Support Services to fund apprenticeships and training centers for underrepresented or disadvantaged people pursuing careers in transportation, engineering or construction. | Other | 2010-04-28 | 2010-04-29 | 2010-09-30 | 2010-09-30 | 351409
5811 | Underway | C950 | Ferryboat | MAINE | CUMBERLAND |  | 01 | 1745500 | Capital Equipment Purchase of a new ferry vessel that will be used by the Casco Bay Island Transit District. | Other | 2010-11-19 | 2009-11-20 | 2011-12-30 | 2013-06-30 | 4531000
5812 | Underway | C950 | Ferryboat | MAINE | CUMBERLAND |  | 01 | 1745510 | Replacement of the fender systems for the CBITD piers. | Other | 2010-09-23 | 2011-09-21 |  | 2012-09-30 | 450000
5813 | Completed | C950 | Ferryboat | MAINE | WALDO |  | 01 | 1763400 | Rehabilitation of the Maine State Ferry Service's pier structure and the Islesboro and Lincolnville locations. | Other | 2009-11-19 | 2009-11-20 | 2011-12-30 | 2011-12-30 | 1819000
5814 | Completed | C250,C200 | Highway Infrastructure Investment Grant | MAINE | PISCATAQUIS |  | 02 | A001000 | Dover-Foxcroft, Route 15. Reconstruction of 1.29 miles of Route 15 including drainage, paving, re-alignment of side roads, guardrail and safety improvements. | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2010-06-30 | 2010-06-30 | 2542213.02 | 1.290
5815 | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | TALBOT |  | 01 | 0003124 | Talcot County will be replacing the concrete box culvert and reconstructing the approach roadway on Dutchman's Lane. | Pavement Improvement | 2009-12-01 |  |  |  | 885000
5816 | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 06 | 0003125 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This project is in Ha | Pavement Improvement | 2010-05-17 | 2010-05-17 |  |  | 908000
5817 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | QUEEN ANNES |  | 01 | 0003126 | Queen Anne's County will remove the existing pavement and resurface. They will also widen the roadway shoulders. This work will be done on Tanyard Road from MD 305 to Whitemarsh Road. | Safety/Traffic Management | 2010-02-20 |  |  |  | 715306
5818 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY | CUMBERLAND (WV) | 06 | 0003127 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This project is on Ca | Pavement Improvement | 2009-09-17 |  |  |  | 691347
5819 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ST MARYS |  | 05 | 0003129 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This project is on Pe | Pavement Improvement | 2009-09-17 |  |  |  | 330150
5820 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 0003130 | This project willrepair Allegheny Highland Trail Bridge over New Hope Road in Allegheny County. | Bridge Improvement | 2009-09-17 |  |  |  | 130000
5821 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 0003132 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This project is on Ro | Pavement Improvement | 2009-09-18 |  |  |  | 399652
5822 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 0003134 | Maryland State Highway will be replacing the deteriorated Berwyn Creek concrete bridge deck with a new deck under their bridge system preseveration program. | Bridge Improvement | 2010-03-18 | 2010-03-18 |  |  | 671987
5823 | Underway | C950 | Ferryboat | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 03 | 0003141 | Baltimore City will purchase two new ferry boats and rehabilitate the existing pier to accomodate these two new boats in the Inner Harbor area of Baltimore. | Other | 2010-06-04 |  |  |  | 1400000
5824 | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 01 | 0003146 | Harford County will be constructing a roundabout at Wheel Road and Laurel Bush Road. In additon to the roundabout work on 500 feet of Wheel Road will be done which includes culvert replacement, retai | Safety/Traffic Management | 2010-02-05 |  |  |  | 780000
5825 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | QUEEN ANNES |  | 01 | 0003150 | Queen Anne's County will remove and resurface the existing pavement. They will also widen the shoulders of the roadway. This work will be on Carmichael Road from Arrington Road to Overlook Drive. | Safety/Traffic Management | 2010-02-02 |  |  |  | 203669
5826 | Obligated and Not Awarded | C490 | OJT/SS | MARYLAND | STATEWIDE |  |  | 0003169 | ARRA - OJT / SS Program | Other |  |  |  |  | 240000
5827 | Underway | C950 | Ferryboat | MARYLAND | BALTIMORE CITY |  | 07 | 0003180 | ARRA Ferry Boat Discretionary Grant - Right of Way Acquistion | Other | 2010-08-18 | 2010-08-18 | 2035-08-18 |  | 190000
5828 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ANNE ARUNDEL |  | 01 | 000A368 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-06-22 | 2009-09-29 | 2011-11-01 |  | 4612024
5829 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | CALVERT |  | 05 | 000A369 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-05 | 2009-05-14 | 2011-11-01 |  | 5117038
5830 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 000A370 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-04-29 | 2009-05-20 | 2011-11-01 |  | 4612050
5831 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ST MARYS |  | 05 | 000A371 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-20 | 2009-06-11 | 2011-12-01 |  | 6140665
5832 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ANNE ARUNDEL |  | 05 | 000A373 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-07-16 | 2009-10-15 | 2011-12-01 |  | 6938533
5833 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A375 | This is a signalization project. Signals and Reconstructs in District 3. This contract is required for routine capital signal improvement efforts in District 3. | Safety/Traffic Management | 2009-08-20 | 2009-09-30 |  |  | 5251090
5834 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CECIL |  | 01 | 000A379 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-06-09 | 2009-09-20 | 2011-12-01 |  | 3408022
5835 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | KENT |  | 01 | 000A380 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-20 | 2009-06-15 | 2011-11-01 |  | 2306012
5836 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | QUEEN ANNES |  | 01 | 000A381 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-20 | 2009-06-09 | 2011-12-01 |  | 3828006
5837 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | TALBOT |  | 01 | 000A382 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-05 | 2009-06-10 | 2011-11-01 |  | 2288019
5838 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A385 | This project will improve interstate lighting and enhance safety at various interchanges. | Safety/Traffic Management | 2010-01-16 | 2010-02-26 |  |  | 7691200
5839 | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A386 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Dorchester, Somerset, Wicomico, and Worcester Coun | Transportation Enhancements | 2009-06-24 | 2009-10-05 | 2012-06-01 |  | 4088800
5840 | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A387 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Montgomery and Prince George’s Counties. This work | Transportation Enhancements | 2009-06-16 | 2009-07-22 | 2012-07-01 |  | 3612818
5841 | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A388 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Baltimore and Harford Counties. This work will add | Transportation Enhancements | 2009-06-23 | 2009-08-11 | 2011-06-01 |  | 2623097
5842 | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A389 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Anne Arundel, Calvert, Charles, and St. Mary’s Cou | Transportation Enhancements | 2009-07-14 | 2009-08-03 | 2011-06-01 |  | 1904467
5843 | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A390 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Carroll, Frederick, and Howard Counties. This work | Transportation Enhancements | 2009-07-16 | 2009-07-27 | 2011-06-01 |  | 1987656
5844 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | DORCHESTER |  | 01 | 000A395 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. Various locations in | Pavement Improvement | 2009-03-11 | 2009-03-30 | 2010-12-01 |  | 2903015
5845 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | SOMERSET |  | 01 | 000A396 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Somerset County that will enhance pavement life and provide | Pavement Improvement | 2009-03-11 | 2009-03-30 | 2010-12-01 |  | 3106037
5846 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | WICOMICO |  | 01 | 000A397 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Wicomico County that will enhance pavement life and provide | Pavement Improvement | 2009-04-08 | 2009-06-28 | 2010-12-01 |  | 3623001
5847 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | WORCESTER |  | 01 | 000A398 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Worcester County that will enhance pavement life and provid | Pavement Improvement | 2009-03-11 | 2009-05-10 | 2010-12-01 |  | 3606058
5848 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A400 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Dorchester, Somerset, Wicomico, and Worcester Counties. The work may als | Safety/Traffic Management | 2009-06-09 | 2009-12-16 | 2011-12-01 |  | 379808
5849 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A401 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Caroline, Cecil, Kent, Queen Anne’s and Talbot Counties. The work may al | Safety/Traffic Management | 2009-06-09 |  | 2012-01-01 |  | 299042
5850 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A402 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Montgomery County and Prince George’s Counties. The work may also includ | Safety/Traffic Management | 2009-06-03 |  | 2011-12-01 |  | 468485
5851 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A403 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Baltimore and Harford Counties. The work may also include installation o | Safety/Traffic Management | 2009-05-20 | 2009-12-01 | 2012-01-01 |  | 441541
5852 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A404 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Anne Arundel, Calvert, Charles, and St Mary’s Counties Counties. The wor | Safety/Traffic Management | 2009-05-20 | 2009-06-08 | 2011-12-01 |  | 597345
5853 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A405 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Carroll, Frederick, and Howard Counties. The work may also include instal | Safety/Traffic Management | 2009-05-21 | 2009-09-14 | 2012-01-01 |  | 580636
5854 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 000A406 | This project involves resurfacing and pavement preservation of various locations in Allegheny County. The project will improve ride and improve deterirating sections of the highway. Work will be dod | Pavement Improvement | 2009-06-09 | 2009-07-17 | 2012-01-30 |  | 3471080
5855 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE |  | 02 | 000A407 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-10-07 |  |  |  | 5112046
5856 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE |  | 03 | 000A408 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-10-07 | 2010-03-23 |  |  | 5412023
5857 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | CARROLL |  | 06 | 000A409 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-18 | 2009-07-06 | 2011-12-01 |  | 2958005
5858 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 02 | 000A410 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-06-09 | 2009-08-05 | 2011-12-01 |  | 6612006
5859 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 08 | 000A411 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-20 | 2009-06-15 | 2011-12-01 |  | 8476015
5860 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 000A412 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-27 | 2009-07-16 | 2011-12-01 |  | 8677714
5861 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES |  | 04 | 000A413 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-06-15 | 2009-10-09 | 2011-12-01 |  | 8166050
5862 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 000A414 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-20 | 2009-06-29 | 2011-12-01 |  | 7640063
5863 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | WASHINGTON |  | 06 | 000A415 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-20 | 2009-07-17 | 2011-12-01 |  | 3078053
5864 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 000A416 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-21 | 2009-06-29 | 2011-12-01 |  | 7026051
5865 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 000A417 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-06-09 | 2009-08-03 | 2011-12-01 |  | 2623007
5866 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | HOWARD |  | 07 | 000A418 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. At some locations, i | Pavement Improvement | 2009-05-18 | 2009-07-26 | 2011-12-01 |  | 6372010
5867 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A419 | This project will repair concrete pavement and curb at Truck Weigh/Inspection Stations due to severely cracked roadway surface. Project will also improve geometric and drainage. This is a statewide | Pavement Improvement | 2009-06-09 | 2009-07-28 | 2012-07-01 |  | 844595
5868 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 000A420 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-06-09 | 2009-06-22 | 2011-12-01 |  | 2516042
5869 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 000A421 | Maryland State Highway will clean and paint ten bridges in Prince George's County as part of its bridge system preservation program. This project will extend the life of the existing bridges. | Bridge Improvement | 2009-03-11 | 2009-05-18 | 2010-06-01 |  | 1789806
5870 | Completed | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | Multiple | 000A422 | Cleaning and painting bridges for longer service life on US 1, MD201, MD202, MD212 and MD500 | Bridge Improvement | 2009-03-30 | 2009-05-11 | 2010-05-01 | 2009-12-03 | 1742046
5871 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A423 | This project will improve safety for the travelling public. Maryland State Highway will rehabilitate existing substandard traffic barrier at various locations in Baltimore and Harford Counties. InB | Safety/Traffic Management | 2009-06-10 | 2009-07-13 | 2011-01-01 | 2010-02-02 | 729530
5872 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A424 | Maryland State Highway will upgrade guard rails at various locations in Anne Arundel, Calvert, Charles and St. Mary's Counties. This project will will improve safety for the travelling public. In An | Safety/Traffic Management | 2009-06-15 | 2009-06-29 | 2011-01-01 | 2010-03-16 | 823241
5873 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A425 | This project will improve safety for motorists by upgrading existing guardrails at various locations in Garrett, Washington, Carroll, Frederick and Howard Counties. | Safety/Traffic Management | 2009-06-09 | 2009-08-24 | 2011-01-01 |  | 1904760
5874 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A426 | This project will improve safety for motorists by upgrading existing guardrails at various locations in Montgomery and prince George's Counties. | Safety/Traffic Management | 2009-06-15 | 2009-08-17 | 2011-01-01 | 2010-06-29 | 852738
5875 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A427 | This project will install and upgrade signing at various locations. This project will improve safety of motorist. | Safety/Traffic Management | 2009-03-16 | 2009-07-01 | 2012-04-01 |  | 5677537
5876 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A428 | Maryland State Highway will install new median traffic barrier and rehabilitate non-compliance traffic barrier on approximately 17 mile section of US50 in Dorchester, Somerset, Wicomico and Worcester | Safety/Traffic Management | 2009-06-15 | 2010-01-04 | 2011-01-01 |  | 1530969
5877 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A429 | Maryland State Highway will rehabilitate existing substandard traffic barrier at various locations in Cecil (along 17 miles of US40), Queen Anne's (along 15.5 miles of US50) and Talbot (along 21 miles | Safety/Traffic Management | 2009-07-13 | 2009-07-27 | 2011-01-01 |  | 2283767
5878 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A430 | This contract will provide for upgrades to camera video detection for the traffic control timing of the different phases of operation. It will install traffic detection at signalized intersections in | Safety/Traffic Management | 2009-06-16 | 2009-06-30 | 2011-07-01 |  | 1824752
5879 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A431 | This project is for dynamic message signs deployment to ncrease CHART's (Maryland State's traffic operation's center) information dissemmation capibilities. | Safety/Traffic Management | 2009-07-28 | 2010-04-07 | 2012-08-01 |  | 3410470
5880 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A432 | This project will install battery backups and other signal improvements throughout the state districts. | Safety/Traffic Management | 2009-10-21 | 2010-03-17 | 2011-08-31 |  | 5370992
5881 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A433 | This contract will provide for upgrades to camera video detection for the traffic control timing of the different phases of operation. | Safety/Traffic Management | 2009-06-25 | 2009-07-13 | 2011-08-01 |  | 1672809
5882 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A434 | This project will install battery backups and other signal improvements throughout the state districts. | Safety/Traffic Management | 2009-08-13 | 2009-09-07 | 2011-09-01 |  | 5141587
5883 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A443 | This project will install containerized trees and seedlings at various locations including, but not limited to 34 sites throughout Baltimore, | Transportation Enhancements | 2009-07-13 | 2009-09-10 | 2011-09-30 |  | 367839
5884 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A445 | This project will install sign lighting system at various locations to improve safety for motorists. | Safety/Traffic Management | 2009-08-25 | 2009-09-02 | 2011-09-01 |  | 2443595
5885 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A446 | This project will install and establish trees at various locations in Anne Arundel, Calvert, Charles and Saint Mary Counties. This work involves the removal of dead or invasive species, as well as, | Transportation Enhancements | 2009-12-23 |  |  |  | 245907
5886 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A447 | This project will plant trees and bare root seedlings at various locations including, but not limited to 25 sites throughout Caroline, Dorchester, Kent, Queen Anne’s, Talbot, Wicomico and Worcester Co | Transportation Enhancements | 2009-10-07 | 2009-11-09 | 2011-09-01 |  | 251958
5887 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A448 | This project will install and establish reforestation trees and shrubs at various locations throughout Prince Georges's and Montgomary Counties. Project will remove dead or invasive plants and install | Transportation Enhancements | 2009-08-05 | 2009-09-29 | 2010-08-01 |  | 221260
5888 | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK | FREDERICK | 06 | 000A452 | This project, located in Frederick County, is for vegetation management, invasive species removal, and installation, care, and establishment of reforestation and landscape plantings in the interchange | Transportation Enhancements | 2009-08-05 | 2010-01-07 | 2011-08-01 |  | 496980 | 0.280
5889 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | HOWARD |  | 07 | 000A455 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Howard County that will enhance pavement life and provide s | Pavement Improvement | 2010-04-22 | 2010-04-22 |  |  | 2993000
5890 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE | BALTIMORE,MD | 02 | 000A481 | This project involves traffic signal reconstruction in Baltimore County at MD7, MD157 and MD7. | Safety/Traffic Management | 2009-10-14 | 2009-10-28 | 2011-11-30 |  | 1720765
5891 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | ANNE ARUNDEL | BALTIMORE,MD | 02 | 000A486 | This project involves traffic signal reconstruction in Anne Arundel County at MD 2 and MD210. | Safety/Traffic Management | 2009-11-25 | 2010-01-04 | 2011-12-31 |  | 1621285
5892 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CALVERT |  | 05 | 000A487 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. The project is for re | Pavement Improvement | 2009-09-11 |  |  |  | 1343000
5893 | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 06 | 000A488 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Harford County that will enhance pavement life and provide | Pavement Improvement | 2009-12-22 | 2010-05-17 |  |  | 1464000
5894 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | QUEEN ANNES |  | 01 | 000A490 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them or install new guard rails at various locations in Queen Anne's County. This project wil limprov | Safety/Traffic Management | 2009-09-17 |  |  |  | 194025
5895 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES |  | Multiple | 000A491 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Prince George's County that will enhance pavement life and | Pavement Improvement | 2009-09-17 |  |  |  | 3870485
5896 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES |  | Multiple | 000A492 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Prince George's County that will enhance pavement life and | Pavement Improvement | 2009-09-17 |  |  |  | 3526515
5897 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 000A494 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Frederick County that will enhance pavement life and provid | Pavement Improvement | 2010-04-12 | 2010-04-12 |  | 2009-08-01 | 2406346
5898 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 000A495 | This project involves cleaning and painting bridges in Frederick County for longer service life. | Bridge Improvement | 2009-09-17 |  |  |  | 492148
5899 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CARROLL |  | 06 | 000A497 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Carroll County that will enhance pavement life and provide | Pavement Improvement | 2009-09-17 |  |  |  | 2715000
5900 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | WASHINGTON |  | 06 | 000A499 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Washington County that will enhance pavement life and provi | Pavement Improvement | 2009-09-03 | 2010-04-27 |  |  | 2303000
5901 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | SOMERSET |  | 01 | 000A500 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Somerset County that will enhance pavement life and provide | Pavement Improvement | 2010-04-05 | 2010-04-05 |  |  | 642000
5902 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 000A502 | This Baltimore City Citywide project will furnish all the labor and materials needed for the reconstruction of various traffic signals at existing intersections throughout the City. | Safety/Traffic Management | 2010-09-07 |  |  |  | 3878542
5903 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | WORCESTER |  | 01 | 000A503 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Worcester County that will enhance pavement life and provid | Pavement Improvement | 2009-09-17 |  |  |  | 1319000
5904 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ANNE ARUNDEL | BALTIMORE,MD | Multiple | 000A504 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Anne Arundel County that will enhance pavement life and pro | Pavement Improvement | 2009-09-17 |  |  |  | 6043000
5905 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE |  | Multiple | 000A505 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Baltimore County that will enhance pavement life and provid | Pavement Improvement | 2009-09-17 | 2010-04-28 |  |  | 8129000
5906 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 000A507 | This project will install Signs in Various Locations in Caroline County to improve safety. | Safety/Traffic Management | 2009-09-17 |  |  |  | 136419
5907 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 000A508 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Garrett County that will enhance pavement life and provide | Pavement Improvement | 2009-09-17 |  |  |  | 1204000
5908 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | DORCHESTER |  | 01 | 000A509 | This project will install pavement markings at various locations in Dorchester County to improve safety. | Safety/Traffic Management | 2009-09-18 |  |  |  | 47762
5909 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | DORCHESTER |  | 01 | 000A510 | Maryland State Highway will resurface at various locations in Dorchester County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Widening | 2009-09-17 |  |  |  | 1015238
5910 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | CECIL | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 000A511 | Maryland State Highway will resurface at various locations in Cecil County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2010-05-17 |  |  |  | 1504000
5911 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 000A512 | This project will install pavement markings at various locations in Caroline County to improve safety. | Safety/Traffic Management | 2009-09-17 |  |  |  | 192691
5912 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 000A514 | Maryland State Highway will resurface at various locations in Charles County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-18 |  |  |  | 1228000
5913 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY |  | Multiple | 000A515 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them or install new guardrails at various locations in MOntgomery County. This project will improve s | Safety/Traffic Management | 2009-09-17 |  |  |  | 248220
5914 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY |  | Multiple | 000A516 | This project wil upgrade traffic signals at various locations in Montgomery County. This project will improve safety for motorists. | Safety/Traffic Management | 2009-09-17 |  |  |  | 441981
5915 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY |  | Multiple | 000A517 | This project wil install traffic signs at various locations in Montgomery County. This project will improve safety for motorists. | Safety/Traffic Management | 2009-09-17 |  |  |  | 236104
5916 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | Multiple | 000A518 | Maryland State Highway will resurface at various locations in Montgomery County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-17 |  |  |  | 6744000
5917 | Obligated and Not Awarded | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A520 | Maryland State Highway through our Maryland Transit Authority will be replacing eight existing railroad crossings at various locations throughout the State. | Safety/Traffic Management |  |  |  |  | 524715
5918 | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 000A522 | This project wil install ADA Sidewalks at various locations in the Town of La Plata and address ADA non-compliance elements along Charles County's roadway system. | Safety/Traffic Management | 2009-09-07 |  |  |  | 96425
5919 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | WICOMICO |  | 01 | 000A523 | Maryland State Highway will resurface at various locations in Wicomico County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-21 |  |  |  | 1795000
5920 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | KENT |  | 01 | 000A524 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Kent County that will enhance pavement life and provide smo | Pavement Improvement | 2009-09-21 |  |  |  | 540000
5921 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 000A525 | Town of Indian Head will be replacing existing sidewalks and upgrading to meet ADA compliance. The town is working through Charles County in the use of the County's ARRA funds. | Safety/Traffic Management | 2009-10-15 |  |  |  | 42963
5922 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A526 | This project will clean and paint 12 bridges on various routes in Anne Arndel, Calvert, Charles, and St Mary's Counties. These processes will extend the life of the structures. | Bridge Improvement | 2010-01-21 |  |  |  | 1800277
5923 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 000A529 | Maryland State Highway will mill, resurface, line stripe, and install guardrail on I-95/I495 from MD 5 to South of D'Arcy Road and MD 4 to South of Old Marlboro Road. | Pavement Improvement | 2010-04-20 |  |  |  | 4105745
5924 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 000A537 | Baltimore City will be milling and resurfacing various routes within the city limits. They will also be replacing curb and gutter, sidewalks, and pedestrian ramps. New pavement markings and striping | Pavement Improvement | 2016-08-16 |  |  |  | 2465406
5925 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 000A539 | Baltimore City will be installing updated street and pedestrian lightings with minor curb and sidewalk replacement work done where necessary. | Safety/Traffic Management | 2010-09-07 |  |  |  | 786651
5926 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 0682033 | Maryland State Highway will perfrom patching and install a new layer that will enhance pavement life and provide smoother surface. In addition, the project will enhance safety by upgrading guradrails | Pavement Improvement | 2009-06-08 | 2009-07-07 | 2009-12-01 | 2009-11-10 | 3208302 | 3.420
5927 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 0682034 | Maryland State Highway will Maryland State Highway will either replace guardrails not meeting the current standards or repair them or install new guardrails as needed. This project will improve safety | Safety/Traffic Management | 2009-04-20 | 2009-05-11 | 2009-12-01 | 2009-07-10 | 1251301 | 9.400
5928 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 0682035 | Maryland State Highway will replace existing substandard weatherized traffic barrier along the roadside and median with galvanized traffic barrier on 17 mile section of Interstate 68 (from west of Hil | Safety/Traffic Management | 2009-07-07 | 2009-08-10 | 2011-01-01 | 2010-06-14 | 3474459 | 17.000
5929 | Completed | C200 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 0682036 | This project will establish turfgrass in selected bare and eroded areas on MD 36 to Garrett County Line. | Transportation Enhancements | 2009-08-25 | 2009-09-14 | 2009-11-30 | 2009-10-30 | 344651 | 3.230
5930 | Completed | C200 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 0703055 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. In addition, the proj | Pavement Improvement | 2009-06-15 | 2009-08-12 | 2009-10-01 | 2009-11-13 | 3550530 | 6.860
5931 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE |  | 03 | 0832214 | Maryland State Highway will improve sections of Interstate 83 (from MOunt Carmel Road to PA State line) and associated ramps in Baltimore County by removing few inches of existing roadway and adding | Pavement Improvement | 2009-06-24 | 2009-07-13 | 2010-08-01 | 2009-12-01 | 3734298 | 2.800
5932 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 0952267 | This project includes work to remove invasive species and install reforestation and landscape plantings along roadsides and within median and quadrant sections of the US 50 / I-495/95 Interchange, loc | Transportation Enhancements | 2009-08-13 | 2009-10-22 | 2011-10-01 |  | 638968
5933 | Underway | C220 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 0953182 | Lanscaping using invasive plant control and native plant establishment on I-95 from I-495 to MD212 and from MD109 to MD100. Invasive plant species will be removed and native meadow plants will be pla | Transportation Enhancements | 2009-04-29 | 2009-05-11 | 2011-06-01 |  | 414357
5934 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 1015005 | This project in Allegheny County will widen the roadway to a minium 18' width, perfrom surface overlay, construct two retaining walls to minimize grading impacts, and complete drainage improvements on | Pavement Improvement | 2010-02-16 | 2010-04-01 |  |  | 3057478
5935 | Completed | C200 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 1016006 | Maryland State Highway will resurface at various locations in Allegany County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Improvement | 2009-07-23 | 2009-08-24 | 2010-02-01 | 2009-11-17 | 752460 | 0.790
5936 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 1051025 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. The project is locate | Pavement Improvement | 2009-06-09 | 2009-07-27 | 2009-11-01 | 2009-10-09 | 2386657 | 10.200
5937 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 1074009 | This project will improve roadway characterstics (geometrics improvements) in Frederick County at Fingerboard Rd and Ijamsville Rd/Big Woods Rd toimprove safety. | Pavement Improvement | 2009-04-23 | 2009-07-24 | 2010-03-01 |  | 1768873 | 0.300
5938 | Completed | C230 | Highway Infrastructure Investment Grant | MARYLAND | HOWARD | BALTIMORE,MD | 07 | 1091062 | Maryland State Highway will resurface in Howard County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Improvement | 2009-08-14 | 2009-09-09 | 2010-05-01 | 2010-03-19 | 2352421 | 2.630
5939 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 1194004 | This a bridge replacement project in Prince George's County. | Bridge Replacement | 2009-10-07 | 2010-06-25 | 2010-12-31 |  | 1461126
5940 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MARYLAND | ST MARYS |  | 05 | 1216001 | Saint Mary's County will replace the existing hydraulically and structurally inadequate culverts, (4) with aluminum box culverts, with greater hydraulic capacity culverts on the Mechanicsville Road ov | Bridge Improvement | 2009-09-17 |  |  |  | 1165850
5941 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 07 | 1251034 | Baltimore City will resurface Orleans Street from Central Avenue to Wolfe Street for pavement preservation. This project will include updating sidewalks, traffic barriers, storm drains, and roadway l | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2010-07-01 |  | 7082521
5942 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CECIL | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 1251044 | Maryland State Highway is correcting inadequate drainage then resurfacing and restriping the roadway on the southern approach to Big Elk Creek. | Pavement Improvement | 2010-02-18 |  |  |  | 403461
5943 | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD | ABERDEEN-HAVRE DE GRACE-BEL AIR | 02 | 1257001 | Maryland State Highway will mill and resurface the existing roadway, repair existing drainage, upgrade the existing traffic barrier and end treatments, and then restripe the roadway on MD 462 from MD | Pavement Improvement | 2010-01-12 | 2010-07-08 |  |  | 610784
5944 | Completed | C250 | Highway Infrastructure Investment Grant | MARYLAND | CECIL |  | 01 | 1266003 | This project, located in Cecil County, is for the construction of a 121’ x 77’ expansion of the ride sharing facility at MD 222 and Blythedale Road.This carpool lot in Cecil County has reached 85% cap | Pavement Widening | 2009-06-22 | 2009-07-13 | 2009-12-01 | 2009-12-11 | 330214 | 0.000
5945 | Underway | C220 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 1271048 | This project will eradicate or control invasive plants on US 301 in Queen Anne's, Kent and Cecil Counties from US50/301 split to the Delaware line. Native meadow plants will be planted in place of in | Transportation Enhancements | 2009-06-15 | 2009-07-16 | 2011-07-01 |  | 115953
5946 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | DORCHESTER |  | 01 | 1301141 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with the new layer that will enhance pavement life and provide smoother surface. This project is | Pavement Improvement | 2009-06-15 | 2009-09-09 | 2009-10-01 | 2009-11-13 | 1048512 | 4.490
5947 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | TALBOT |  | 01 | 1301142 | Maryland State Highway will improve sections of US 50 (from MD 662B to MD 309) in Talbot County by removing few inches of existing roadway and adding a new pavement layer that will wear longer and min | Pavement Improvement | 2009-07-06 | 2009-07-20 | 2010-08-01 | 2009-12-11 | 2507804 | 4.090
5948 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 1311003 | This project will reconstruct 5th Avenue from Market Street to .89 miles South in Town of Denton in Caroline County. This project will enhance pavement life and improve ride. | Pavement Widening | 2009-09-17 |  |  |  | 631890
5949 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 2011027 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. In addition, the pr | Pavement Improvement | 2009-06-15 | 2009-08-17 | 2010-03-01 | 2009-11-16 | 1066347 | 1.580
5950 | Completed | C250 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 2011028 | This project will resurface US219 from .15 Miles North of MD 42 to Bumble Bee Rd to enhance roadway life and improve ride. | Pavement Improvement | 2009-03-11 | 2009-03-25 | 2009-10-01 | 2009-07-28 | 1581985 | 2.170
5951 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 2061022 | Maryland State Highway will resurface MD135 from Chestnut Grove Road to Lee Road in Garrett County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-04-01 | 2009-05-09 | 2010-02-01 | 2009-10-07 | 1858550 | 3.260
5952 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 2111011 | Maryland State Highway and West Virgina DOT are working on this project together with West Virginia being the lead state. Maryland State Highway portion of this project is to provide a new lift stati | Other | 2009-11-03 |  |  |  | 750000
5953 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | WASHINGTON |  | 06 | 2211014 | This project will add a right turn lane on MD65 at MD63 (lower vertical crest) to facilitate traffic movement and improve safety. | Pavement Improvement | 2009-09-03 | 2009-09-29 | 2010-06-30 | 2010-06-18 | 769980 | 0.150
5954 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY |  | 08 | 2331009 | This project will install street lighting on MD 124 - Air Park Road and Rosewood Manor Lane to imprve safety. | Other | 2009-09-17 |  |  |  | 819695
5955 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | CARROLL |  | 06 | 2341039 | Maryland State Highway is doing this project in Carroll County. It is a geometric improvement project that involves the construction of separate left turn and deceleration lanes, traffic signal upgra | Pavement Improvement | 2009-10-07 | 2009-10-20 | 2010-06-30 | 2010-06-15 | 1438087
5956 | Completed | C200 | Highway Infrastructure Investment Grant | MARYLAND | CARROLL |  | 06 | 2371018 | Ramp widening (geometric improvement) at MD27 at MD140 ramps. This project will improve safety. | Pavement Improvement | 2009-09-11 | 2009-09-28 | 2010-06-30 | 2010-06-08 | 740740 | 0.230
5957 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 2451032 | MD 410 to wayne Avenue - Traffic Signal Reconstruction for safety. | Safety/Traffic Management | 2009-12-23 | 2010-01-11 |  |  | 1103573
5958 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 2491025 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD650 from Milestone Drive to Venice Drive to enhance roadway life and smoothness. | Pavement Improvement | 2009-03-03 | 2009-03-16 | 2010-02-01 |  | 2149158 | 1.170
5959 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE | WASHINGTON (DC-MD-VA) |  | 2491026 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD650 from MD410 to Holton Lane to enhance roadway life and smoothness. | Pavement Improvement | 2009-09-29 | 2009-11-18 |  |  | 1444164 | 0.830
5960 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 2491027 | Maryland State Highway will widen and resurface MD 650 from the DC line to MD 140 to enhance the pavement life, provide higher degree of safety, and provide smoother ride surface. | Pavement Improvement | 2010-03-18 | 2010-04-19 |  |  | 1893497
5961 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 2511062 | Maryland State will perfrom patching, removal of surface (as needed) and resurface US 1 from MD410 to Albion Road to enhance roadway life, safety and smoothness. | Pavement Improvement | 2010-03-02 | 2010-04-30 | 2010-06-30 |  | 839177 | 0.520
5962 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 2541010 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD214 from Cindy lane to Brightseat Road to enhance roadway life, safety and smoothness. | Pavement Improvement | 2009-06-24 | 2009-09-29 | 2010-08-01 |  | 1925417 | 1.980
5963 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 2707175 | Maryland State will perfrom patching, removal of surface (as needed) and resurface Northbound I270 from Structure 1007901 Bennett Creek to Structure 1007801 MD 80 to enhance roadway life, safety and s | Pavement Improvement | 2009-03-26 | 2009-05-11 | 2009-09-01 | 2009-08-01 | 895503 | 1.260
5964 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 3001044 | Pennington Avenue over Curtis Creek Bascule Repair | Bridge Improvement | 2010-08-31 | 2010-08-31 |  | 2012-01-31 | 3022193
5965 | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 3001045 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 2009-06-09 | 2009-06-23 | 2010-01-01 | 2010-05-11 | 918268 | 2.470
5966 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 3001046 | Maryland State Highway will widen 1.3 mile section of MD 404 in Caroline County. The project will add two westbound lanes, aa 34 foot median and will reconstruct existing lanes. Project will add lef | Pavement Widening | 2009-09-09 | 2009-09-28 |  |  | 2437935 | 1.320
5967 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 07 | 3009010 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Hilton Street from Frederick Avenue to Mulberry Street to enhance roadway life and smoot | Pavement Improvement | 2009-07-15 | 2009-07-13 | 2009-12-01 |  | 1092705
5968 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 07 | 3019006 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Park Heights Avenue from NorthernPArkway to Garrison Bulevard to enhance roadway life an | Pavement Improvement | 2009-10-15 | 2009-10-05 |  |  | 1619916
5969 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 3200001 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Frankford Avenue from Sinclair Lane to Moravia Park Drive to enhance roadway life and sm | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-12-01 |  | 1051681
5970 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 3206005 | Baltimore City will rehabilitate (make it to last longer) Argonne Drive Bridge. | Bridge Improvement | 2010-01-10 | 2010-02-15 |  |  | 6528294
5971 | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | WORCESTER |  | 01 | 3311012 | Maryland State Highway will resurface MD 528 from 9th Street to 28th Street in Ocean City to eenhance the pavement life and provide smoother ride surface. | Pavement Improvement | 2010-04-02 | 2010-04-22 |  |  | 832716
5972 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | Multiple | 3341002 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Northern Parkway from Falls Road to Park Heights Avenue to enhance roadway life and smoo | Pavement Improvement | 2009-06-22 | 2009-07-15 | 2010-05-01 |  | 7572091
5973 | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 01 | 3631001 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 2009-06-22 | 2009-07-28 | 2009-12-01 |  | 1340539 | 2.140
5974 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 08 | 4952276 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In ad | Pavement Improvement | 2009-07-16 | 2009-08-03 | 2010-06-01 |  | 7609004 | 3.920
5975 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 5008021 | This project will add second left turn lane on Southbound MD410 at MD 500 to facilitate traffic movement and reduce congestions and enhance safety. | Pavement Improvement | 2010-01-08 | 2010-02-01 |  |  | 1120639 | 0.500
5976 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 5008022 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. This p | Pavement Improvement | 2009-10-14 | 2010-03-09 | 2010-03-31 |  | 1921697 | 1.120
5977 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 5010013 | Maryland State Highway is doing this project in Montgomery County. It is a geometric improvement that will extend left tun lanes on MD 28, as well as add another turning lane on MD 28. The project i | Pavement Improvement | 2009-10-14 | 2009-12-07 | 2010-09-30 |  | 1066445
5978 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 5018026 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 2009-06-09 | 2009-07-16 | 2011-12-01 |  | 3434916 | 1.760
5979 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 5019021 | MAryland State Highway will be replacing the deteriorating concrete bridge decks on MD 201 ND and MD 201 SB with new decks as part of its bridge system preservation program. | Bridge Improvement | 2010-02-22 | 2010-03-15 |  |  | 5878653
5980 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 06 | 5035004 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 2009-08-11 | 2009-10-11 | 2010-03-01 |  | 1865847 | 1.540
5981 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | Multiple | 5067010 | This project will replace existing deteriorating pavement surface ( MD 212, Riggs Road from Washington D.C. line to Sargent Road) in Prince George's County with new pavement surface. It will also mak | Pavement Improvement | 2009-10-23 | 2009-11-06 | 2010-09-30 |  | 1835894 | 0.930
5982 | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 5067011 | This project will improve safety at MD212 at Allview Drive/Evans Trail by making Geometric improvements. | Pavement Improvement | 2009-09-22 | 2009-11-02 |  |  | 1250441
5983 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 5096001 | Maryland State Highway will replace the deteriorating concrete bridge deck on Forestville Raod over I-95 with a new deck as part of its bridge sytem preservation program. | Bridge Improvement | 2010-05-05 | 2010-06-17 |  |  | 1720857
5984 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE | BALTIMORE,MD | 07 | 6956346 | Maryland State Highway will replace the deteriorated bridge at I-695 over MD 26 (Liberty Road) with a new one as part of its bridge system preservation program. | Bridge Replacement | 2010-02-08 | 2010-04-01 |  |  | 21788103
5985 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY | CUMBERLAND (WV) | 06 | 7509004 | Maryland State Highway Will reconstruct Maryland Avenue from Jefferson Street to Short Street in Allegany County. | Pavement Improvement | 2009-09-17 | 2009-11-15 |  |  | 562653
5986 | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 8502004 | This project will improve safety on Smallwood Drive Westbound at McDaniel Road in Charles County by making geometric improvements. | Pavement Improvement | 2009-09-18 |  |  |  | 180960
5987 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | STATEWIDE | Multiple | 001S899 | The project includes the construction of a new interchange (Exit 8 1/2) on Route 24 in Freetown and construction of new access roadways east to the proposed Fall River Executive Park and west to South | Pavement Improvement | 2009-11-30 | 2009-11-30 |  |  | 32686850
5988 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | PLYMOUTH | TAUNTON | 09 | 001S917 | This project will resurface Route 18/28 from Bridgewater Center to the Middleborough Rotary (intersection of Route 44) and make drainage improvements. | Pavement Improvement | 2009-04-23 | 2009-04-23 |  | 2010-07-17 | 2516982.17
5989 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 001S918 | The project will begin at the Adams/Cheshire town boundary (MM 66.3) and will end just north of Commonwealth Avenue (MM 67.8) for a project length of approximately 1.5 miles. MassHighway will resurfac | Pavement Improvement | 2009-04-23 | 2009-04-23 |  | 2010-08-26 | 2199456 | 1.500
5990 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BARNSTABLE | HYANNIS | 10 | 001S919 | This project will resurface Route 6 (Scenic Highway) from the intersection with Nightingale Pond Road to just east of the intersection with Bourndale Road in the Town of Bourne. | Pavement Improvement | 2009-04-23 | 2009-04-23 |  | 2009-12-03 | 1756160 | 2.410
5991 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | NEW BEDFORD | 04 | 001S920 | Resurface Route 6 from west of the Dartmouth town line (milemarker 20.9±) to the Fall River city line (milemarker 16.3±), a distance of approximately 4.6 miles. | Pavement Improvement | 2009-04-30 | 2009-04-30 |  | 2010-10-08 | 5074035 | 4.650
5992 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 001S921 | In the Town of Barre, this project will resurface Route 122 and a section of Rte 62. The state highway section of the project begins just west of Pleasant Street (milemarker 48.265) and proceeds weste | Pavement Improvement | 2009-05-14 | 2009-05-22 | 2009-11-04 | 2010-05-31 | 2268246
5993 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BARNSTABLE | HYANNIS | 10 | 001S922 | In Barnstable: Perform resurfacing and related work on the state-owned sections of Route 6A, from milemarker 8.12 to milemarker 16.56, a distance of approximately 8.5 miles. Also included in the proj | Pavement Improvement | 2009-07-02 | 2009-07-02 |  | 2010-11-17 | 3283638 | 8.430
5994 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX |  | 07 | 001S923 | This project will resurface a section of Route 2 in Lincoln. Work includes guardrail, painting and signage. | Pavement Improvement | 2009-05-14 | 2009-05-14 |  | 2009-10-16 | 1348853.49 | 3.050
5995 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 001S924 | This project will resurface Route 2 in Concord from Walden to the Sudbury town line and from Nine Acre Corner road to Elm Street. Work includes guardrail, painting and signage. | Pavement Improvement | 2009-05-07 | 2009-05-07 |  | 2010-10-29 | 4313468 | 1.050
5996 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 03 | 001S925 | Mill and resurface Route 6 in Swansea from the Somerset town line to the Rehoboth town line. Work on this project also includes the repair of frost heaves and the reconstruction of existing sidewalks. | Pavement Improvement | 2009-04-23 | 2009-04-23 |  | 2010-06-18 | 4159044 | 5.500
5997 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BARNSTABLE | HYANNIS | 10 | 001S926 | Mill and resurface Route 6A in Dennis from the Yarmouth Town Line to the Brewster Town Line, a distance of approximately 4.3 miles. | Pavement Improvement | 2009-06-25 | 2009-06-25 |  | 2010-05-30 | 1331843.51 | 4.280
5998 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK |  | 09 | 001S927 | This is a Pavement Preservation Project for Route 24 in Avon and Stoughton. | Pavement Improvement | 2009-07-31 | 2009-07-31 |  |  | 5718302.23 | 4.000
5999 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 07 | 001S931 | Replace traffic and guide signs on Interstate 95 (Route 128) between US 3 (Exit 32) in Lexington and I-93 (Exit 37) in Reading, including applicable signage on intersecting roadways. | Safety/Traffic Management | 2009-04-23 | 2009-04-23 | 2011-04-23 | 2011-04-23 | 3168470
6000 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 001S932 | Mill and resurface Route 32 (Main Street) from the Ware/New Braintree town line (milemarker 22.383) to just past the New Braintree/Hardwick town line (milemarker 23.38), a distance of approximately 1 | Pavement Improvement | 2009-05-14 | 2009-05-14 |  | 2009-11-30 | 657048 | 0.940
6001 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | FRANKLIN | FITCHBURG-LEOMINSTER | 01 | 001S933 | In Gill and Wendell: Work under this project will consist of milling the existing paved surface and repaving with 2" of HMA modified top course material. Work will also include repairs/upgrades to gua | Pavement Improvement | 2009-04-30 | 2009-04-30 |  | 2010-07-31 | 3590569
6002 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | Multiple | 001S934 | This project takes place in a number of locations between Westfield and Easthampton. The project will consist of milling the existing paved surface of Route 5 & 10 and repaving with 2" of HMA modified | Pavement Improvement | 2009-05-21 | 2009-05-21 |  | 2010-09-30 | 3891211
6003 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 03 | 001S935 | This project will commence at Route 140 in Shrewsbury and continue in a westerly direction to Massasoit Road in Worcester, a distance of approximately 3.5 miles. | Pavement Improvement | 2009-11-27 | 2009-11-27 |  |  | 2775064 | 3.230
6004 | Underway | C220 | Highway Infrastructure Investment Grant | MASSACHUSETTS | FRANKLIN |  | 01 | 001S936 | The focus of the Northfield Street Improvement Project is to reconstruct sidewalks on Main Street and Parker Avenue in Northfield from a point north of the intersection with River Street continuing no | Transportation Enhancements | 2009-05-07 | 2009-05-07 |  |  | 1100620
6005 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE | PITTSFIELD | 01 | 001S937 | In Lenox: Reconstruction of State Highway from the Route 7 intersection north for approximately 1.25 miles to the end of the State Highway just south of the intersection with Route 183. Included in th | Pavement Improvement | 2009-06-25 | 2009-06-25 |  |  | 3670203.6 | 1.300
6006 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 001S938 | The proposed project consists of improvements to the Route 7/Route 8 Connector Road (formerly Berkshire Mall Drive), from the vicinity of the intersection with Route 7 to the vicinity of the intersect | Pavement Improvement | 2010-02-25 | 2010-02-25 |  |  | 7914429
6007 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NANTUCKET |  | 10 | 001S941 | This project in Nantucket consists of the mill and resurface of Milestone Road from just west of rotary that intersects Orange Street, Sparks Avenue, and Old South Road, to just east of rotary that in | Pavement Improvement | 2009-05-21 | 2009-05-21 |  | 2010-11-29 | 4748670
6008 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | 01 | 001S942 | The purpose of this project is to resurface portions of Route 9 in Belchertown and Ware. Work will also include repairs/upgrades to guardrail end treatments as needed and new pavement markings. Beche | Pavement Improvement | 2009-05-21 | 2009-05-21 |  | 2010-12-03 | 5150691
6009 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 001S945 | The proposed scope for this project consists of micro-milling Route 8 shoulders and partially into travel lanes, installing a stress absorbing interlayer (SAMI) over the travel lanes, and applying a h | Pavement Improvement | 2009-05-14 | 2009-05-14 |  | 2009-11-30 | 994619.91
6010 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | PLYMOUTH |  | Multiple | 001S946 | In Brockton: Reconstruct Route 27, Pleasant Street, West Street and Westgate Mall Road. Work includes minor widening, geometric improvements, new traffic signals and interconnection of signalized int | Pavement Improvement | 2009-07-30 | 2009-07-30 |  |  | 2811883
6011 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 001S947 | This project proposes to resurface Route 7 in New Ashford and Lanesborough with hot-mix asphalt, and would also include repairing/improving the drainage system, resetting guardrail, upgrading guardrai | Pavement Improvement | 2009-05-07 | 2009-05-07 |  | 2009-11-03 | 1878942.31
6012 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | WORCESTER, MA-CT | 03 | 001S949 | The proposed work under this project consists of bridge reconstruction, widening, guardrail installation and all other work on Water Street from its intersection with Bolton Street and Harris Street t | Bridge Replacement | 2009-09-10 | 2009-09-10 |  |  | 3514426
6013 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 001S952 | Resurface Route 2 in Harvard and Littleton from the vicinity of the Littleton Road Bridge to the Boxborough town line, a distance of approximately 4.4 miles. Work includes minor box widening to extend | Pavement Improvement | 2009-04-30 | 2009-04-30 |  | 2010-08-23 | 5175866 | 4.550
6014 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | 01 | 001S953 | The project involves roadway and sidewalk rehabilitation on town-owned Elm Street in the Town of Hatfield, and includes coldplaning, roadway reclamation, hot mix asphalt paving, replacement of sidewal | Pavement Improvement | 2009-07-09 | 2009-07-09 |  | 2009-11-30 | 700710.08
6015 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 001S954 | The proposed expansion of the Newburyport Park & Ride facility will add 105 parking spaces. Work will include the construction of a soil nail retaining wall, upgrades to the existing lighting, as well | Safety/Traffic Management | 2009-08-13 | 2009-08-13 |  |  | 3958204 | 0.000
6016 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN |  | 02 | 001S955 | This project consists of demolishing and replacing the Red Bridge Road Bridge over the Utilities Canal in Wilbraham. The new bridge will be a superstructure replacement constructed on an improved alig | Bridge Improvement | 2009-07-23 | 2009-07-23 |  | 2010-09-01 | 1838194
6017 | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 001S959 | ERP-001S(959)X, Lawrence - Bridge Reconstruction #L-04-009, Hampshire Street over the Spicket River. | Bridge Replacement | 2009-10-01 | 2009-10-01 | 2011-10-01 | 2011-10-01 | 2522939
6018 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | FITCHBURG-LEOMINSTER | 01 | 001S961 | The Project limits are Route 2 in Westminster from Wyman Road/Village Inn Road (Exit 26), easterly into Fitchburg, to the Junction of Route 31 in Fitchburg, a distance of approximately 2.6 miles. The | Pavement Improvement | 2009-08-07 | 2009-08-07 |  |  | 7485002 | 2.260
6019 | Underway | C220 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | Multiple | 001S962 | This multi-use recreational rail trail project starts at Ferry Street in Easthampton and ends at Earle Street in Northampton, for a total length of 4,400 Meters. It links the Manhan Bike Trail in Eas | Transportation Enhancements | 2009-09-03 | 2009-09-03 |  |  | 4211726.4
6020 | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 001S963 | ERP-001S(963)X, Somerville - Magoun Square Signals & Intersection Improvements. | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2011-03-27 | 2011-03-27 | 2218828
6021 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX |  | 05 | 001S964 | The Town of Westford is proposing to widen approximately 3,000 feet of Littleton Road (Route 110). The existing cross section contains one lane in each direction with an additional left turn lane for | Pavement Improvement | 2009-08-06 | 2009-08-06 |  |  | 2955042.35
6022 | Underway | C220,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 001S965 | This project will make safety and mobility improvements at four major intersections along the Dorchester Avenue corridor; Andrews Square, Glover's Corner, Fields Corner and Peabody Square. Improvemen | Pavement Improvement | 2009-11-17 | 2009-11-17 |  |  | 15274303
6023 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 001S966 | Work consists of resurfacing and related work in various locations in the city Boston | Pavement Improvement | 2010-01-28 | 2010-01-28 |  |  | 3695619
6024 | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 001S967 | The purpose of this project is to improve access to the Jackson Street School by constructing new sidewalks, constructing a new access ramp to the nearby bikepath, installing 4' chain link fence at sc | Transportation Enhancements | 2009-10-01 | 2009-10-01 |  | 2010-09-30 | 613114
6025 | Completed | C200,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | DUKES, BARNSTABLE | HYANNIS | 10 | 001S989 | Replace and realign the existing ferry slip at the Hyannis Terminal, including constructing a new dedicated berth for the Authority’s high-speed passenger vessel. Other work under this project includ | Other | 2009-06-13 | 2009-06-13 | 2010-04-01 | 2010-04-01 | 5019950.19
6026 | Underway | C250 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 001S995 | The scope of work for the proposed project is to reconstruct Athol Richmond Road in the Town of Royalston from Elm Avenue in Royalston to the New Hampshire state border. The length of the roadway is a | Pavement Improvement | 2009-11-27 | 2009-11-27 |  |  | 1000000
6027 | Underway | C220,C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S015 | MassHighway proposes to construct the North Bank Bridge over the MBTA Commuter Rail tracks providing a bicycle/pedestrian connection from East Cambridge to City Square Charlestown and the Boston Harbo | Transportation Enhancements | 2009-11-30 | 2009-11-30 |  |  | 29557203
6028 | Completed | C200 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 002S022 | This project proposes to utilize pavement preservation techniques to resurface approximately 11.4 miles of various Federal-Aid eligible roadways (NHS and non-NHS) in North Adams. | Pavement Improvement | 2010-01-14 | 2010-01-14 |  | 2010-10-21 | 2972254
6029 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 002S026 | This project proposes to reconstruct Bridge Street (Route 1A) from the Beverly Salem Bridge to Washington Street. The project includes, sidewalks, curbing, trees and pavement markings. | Pavement Improvement | 2009-12-17 | 2009-12-17 |  |  | 7381521
6030 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 02 | 002S034 | This Footprint Road project in Southbridge involves milling and resurfacing, selected full-depth construction and minor box widening to provide a uniform width. (3.25 mi) | Pavement Improvement | 2009-12-10 | 2009-12-10 |  |  | 2000290
6031 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 002S053 | Fiber optic connectivity at three locations. Dist 4 via Rte 2 to MBTA Alewife station in Cambridge, Newton rest area on Rte 128 to MBTA riverside station, MEMA bunker to MTA toll plaza in Framingham | Safety/Traffic Management | 2009-12-17 | 2009-12-17 |  |  | 1400000
6032 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S055 | Upgrade of the TOC and BTD video systems to IP based virtual matrix switching system. | Safety/Traffic Management | 2009-12-10 | 2009-12-10 |  |  | 1000000
6033 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK |  | Multiple | 002S056 | The design of communication equipment at five locations to increase bandwidth and allow for single CCTV connections for viewing for the City of Boston. | Safety/Traffic Management | 2009-12-10 | 2009-12-10 |  |  | 402958
6034 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK |  | Multiple | 002S057 | The design of up to 37 CCTV at signalized intersections throughout the city of Boston. | Safety/Traffic Management | 2009-12-17 | 2009-12-17 |  |  | 681576
6035 | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 002S071 | Projects ERP-002S(071)X & STP-002S(071)X Ludlow, Sigal & Intersection Improvements at East St & Chapin St. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-10-11 | 2010-10-11 | 220028
6036 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | PLYMOUTH | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S072 | The purpose of this project is to reconstruct North Street from Pleasant Street to Village Gate Drive. The project will involve full depth reconstruction of North Street with approximately a four foot | Pavement Improvement | 2010-01-21 | 2010-01-21 |  |  | 1026713
6037 | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | PLYMOUTH | HYANNIS | 04 | 002S073 | The purpose of this project is to rehabilitate the existing pavement surface on Routes 6 & 28 in Wareham from just east of Mogan Way easterly to the Wareham/Bourne Town Line. | Pavement Improvement | 2010-01-28 | 2010-01-28 |  | 2010-09-05 | 603016
6038 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | PROVIDENCE-PAWTUCKET-WARWICK (RI) | Multiple | 002S074 | The work for the Route 24 bridge over Bedford Street shall consist of reconstructing the bridge and approach wearing surface; replacing the reinforced concrete deck slab; extending the proposed deck a | Bridge Improvement | 2010-01-28 | 2010-01-28 |  |  | 3067718
6039 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 002S075 | The work consists of the landscape improvements along the side slopes and embankments along I-91, from Broad Street to State Street; the design of an irrigation system; and sidewalk and landscaping im | Transportation Enhancements | 2010-02-18 | 2010-02-18 |  |  | 1460945
6040 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S076 | This project involves the installation of a new fully actuated traffic signal system with appropriate phasing and timing for peak hour demands, including an exclusive pedestrian phase, to improve safe | Safety/Traffic Management | 2010-02-04 | 2010-02-04 |  |  | 938075
6041 | Completed | C200 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | 01 | 002S077 | Work under this project will consist of micromilling 1.5” from the existing paved surface and repaving with a 1.5” asphalt standard top course and a 0.75" paver placed friction course. Work will also | Pavement Improvement | 2010-02-11 | 2010-02-11 |  | 2010-09-23 | 1177737.73
6042 | Underway | C250 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 002S078 | The work for this project shall consist of a superstructure replacement with safety upgrades. | Bridge Improvement | 2010-01-14 | 2010-01-14 |  |  | 1084664
6043 | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 002S079 | Project will consist of milling and resurfacing Burnett Road from New Lombard Road (near the Turnpike entrance) to the Ludlow Town Line for a total length of 1.7 miles. | Pavement Improvement | 2010-01-21 | 2010-01-21 |  | 2010-07-20 | 1005092.97
6044 | Underway | C200 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 002S080 | The project limits are Route 140 in Gardner from 1000 feet north of Route 101 and continuing 1.6 miles north to Stone Street. The project consists of milling and resurfacing, and related work. | Pavement Improvement | 2010-02-11 | 2010-02-11 |  |  | 1588212.62
6045 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | 01 | 002S081 | This project begins at the Westhampton Town Line and proceeds north-westerly for 3.08 miles to the intersection of South Street. The roadway currently exhibits potholes, alligator and block cracking, | Pavement Improvement | 2010-02-11 | 2010-02-11 |  |  | 2435594
6046 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 10 | 002S082 | This 1900-foot project includes roadway and sidewalk reconstruction and new traffic signals along the new alignment from the end of the Highway Division's Phase I project to the project limit west of | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 5077840
6047 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S083 | An 8'-10'-wide stabilized aggregate path, asphalt and elevated boardwalk are planned on both the eastern and western sides of Alewife Brook between Route 2 and Mystic Valley Parkway. In order to avoid | Transportation Enhancements | 2010-03-25 | 2010-03-25 |  |  | 4576901
6048 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 07 | 002S084 | Clippership Drive is currently two lanes with a sweeping alignment that encourages excessive speeds near an elderly housing complex. The master plan for Medford Square proposes to reduce the roadway | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2010-11-26 | 2010-11-26 | 726145
6049 | Underway | C220,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 002S085 | The City of Somerville is proposing a series of transportation improvements to address vehicular access and public safety associated with new development opportunities planned within Assembly Square. | Pavement Improvement | 2010-03-31 | 2010-03-31 |  |  | 14902367.6
6050 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 01 | 002S086 | The purpose of this project is to improve vehicular and pedestrian safety and promote efficient traffic operation along Main Street, Broad Street, South Broad Street and Park Square. | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 5440281
6051 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 002S087 | The project will resurface Route 47 (Hadley Street) in South Hadley from Ferry Street northerly to the Hadley Town Line. Work will include new pavement markings and the reconstruction of approximately | Pavement Improvement | 2010-02-11 | 2010-02-11 |  |  | 1210451
6052 | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 01 | 002S088 | This project consists of resurfacing Westfield Road (Rte 202) from the Westfield City Line at Old County Road to Ashley Road for a total length of approximately 2.1 miles. | Pavement Improvement | 2010-02-18 | 2010-02-18 |  | 2010-07-10 | 1211241
6053 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S089 | The proposed Nonantum Road project will narrow the roadway to two 11-foot travel lanes for most of the stretch between Galen Street in Watertown and the Brook Street/North Beacon Street intersection | Pavement Improvement | 2010-03-11 | 2010-03-11 |  |  | 6360344
6054 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE | PITTSFIELD | 01 | 002S090 | The proposed project consists of pavement preservation measures to resurface approximately 8.5 miles of roadways curb to curb on First Street, Baker Road, Holmes Road and Valentine Road. The limits o | Pavement Improvement | 2010-03-18 | 2010-03-18 |  | 2010-10-01 | 2801653
6055 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 07 | 002S091 | Route 9 will be resurfaced from approximately the Southborough/Framingham Line easterly to the Natick/Wellesley Line. The work is to include milling & resurfacing; wheelchair ramp upgrades; additional | Pavement Improvement | 2010-03-25 | 2010-03-25 |  |  | 12175608
6056 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 002S092 | This project will reconstruct Washington Street, including traffic signal upgrades, landscaping and sidewalks/wheelchair ramps. | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 1258737
6057 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 03 | 002S096 | This project consists of resurfacing, reconstruction and safety improvements on city-owned Route 152 in the City of Attleboro. This project is Phase II of the city's plans to reconstruct Route 152 fr | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 1450398
6058 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S099 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 2010-01-28 | 2010-01-28 |  |  | 3786018
6059 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S100 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 2010-02-04 | 2010-02-04 |  |  | 3745027
6060 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S101 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 2010-02-04 | 2010-02-04 |  |  | 2965713
6061 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S102 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 2010-02-04 | 2010-02-04 |  |  | 3384433
6062 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 02 | 002S103 | The purpose of this project is to improve traffic safety and operations for motorists and pedestrians. The proposed improvements for Pulaski Boulevard include widening the roadway, rehabilitating the | Pavement Improvement | 2010-01-28 | 2010-01-28 |  |  | 9871571.3
6063 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S104 | This is a State Highway resurfacing project including new pavement, guardrail, painting and signage. | Pavement Improvement | 2010-01-21 | 2010-01-21 |  |  | 1880221
6064 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | FRANKLIN |  | 01 | 002S106 | This project consists of safety improvements and upgrades along Route 2 in the Town of Orange for a length of approximately 5 miles. This project includes widening the shoulder, extending the existin | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 14872734
6065 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 002S107 | The project includes realignment and signal installation at the following locations; Walnut Street at I-95 Southbound Ramps and Colonial Golf Club Site Drive (Exit 43); Walnut Street at I-95 Northboun | Pavement Improvement | 2010-03-11 | 2010-03-11 |  |  | 5815090.75
6066 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 10 | 002S112 | Work will consist of the demolition of two separate buildings. Parcel C-5, 1565 – 1597 Hancock Street, will be completely demolished and removed. Parcel C-6, 1570 Hancock Street, will be partially dem | Other | 2010-03-25 | 2010-03-25 |  |  | 1846656
6067 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 002S113 | The project consists of coldplaning and resurfacing sections of Route 32 from Upper Church Street northerly to the Barre Town Line for an approximate distance of 6 miles. | Pavement Improvement | 2010-02-25 | 2010-02-25 |  | 2010-09-23 | 1603370
6068 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | WORCESTER, MA-CT | 02 | 002S114 | The Project extends along Route 146 in Uxbridge, from just north of the Chocolog Road interchange, northerly about 4.4 miles to the Douglas Town Line, then continuing another 0.3± miles in Douglas to | Pavement Improvement | 2010-03-04 | 2010-03-04 |  |  | 9122436.5
6069 | Obligated and Not Awarded | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | STATEWIDE |  |  | 002S116 | This project will add equipment at existing facilities to create a shared Wide Area Network (WAN) to transport voice, video and data for all transportation agencies. The technology employed will be e | Safety/Traffic Management |  |  |  |  | 25000
6070 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 002S118 | Resurfacing the pavement and related work on Route 114 from Route 1 in Danvers to Route 128 in Peabody for an approximate project length of 2.078 miles. | Pavement Improvement | 2010-03-25 | 2010-03-25 |  |  | 2481065
6071 | Underway | C200 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 002S155 | PROJECT ERP / STP-002S(155)X Lenox, reconstruction of Rte 183 (West St) & Rtes 7A / 183 including culvert repair L-07-008 | Pavement Improvement | 2010-09-01 | 2010-09-01 |  |  | 612000
6072 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 002S158 | PROJECT ERP-002S(158)X, Chelmsford, reconstruction of Parkhurst St. | Pavement Improvement | 2010-08-26 | 2010-08-26 |  |  | 1825531
6073 | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 002S170 | PROJECT ERP-002S(170)X, Lynn, Intersection Improvements, Lynnfield St (Rte 129) @ Millard & Parker Hill Aves. & Den Quarry Rd. | Pavement Improvement | 2010-09-17 | 2010-09-17 |  |  | 740829
6074 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 07 | 002S175 | ERP-002S(175)X, Arlington - Reconstruction and related work on Forest Street. | Pavement Improvement | 2010-09-30 | 2010-09-30 |  |  | 1683076
6075 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S183 | PROJECT ERP-002S(183)X, Braintree, reconstruction of Union St. | Pavement Improvement | 2010-09-30 | 2010-09-30 |  |  | 3493440
6076 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S185 | PROJECT ERP-002S(185)X Canton, roadway improvements Rte 138 (Turnpike St.) | Pavement Improvement | 2010-10-07 | 2010-10-07 |  |  | 1272430
6077 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 002S214 | PROJECTS ERP-002S(214)X & STP-002S(214)X, Peru, Skyline Trail (Middlefield Rd.) reconstruction | Pavement Improvement | 2010-11-26 | 2010-11-26 |  |  | 3343280
6078 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 002S219 | Project ERP-002S(219)X, Tewksbury, reconstruction of River Rd | Pavement Improvement | 2010-11-26 | 2010-11-26 |  |  | 4997198
6079 | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | STATEWIDE |  |  | 002S220 | PROJECT ERP-002S(220), Districts 1, 2, 3, & 6 Fiber Enhancement Rte I-90 (ITS) | Safety/Traffic Management | 2010-11-18 | 2010-11-18 | 2011-06-27 | 2011-06-27 | 1547770
6080 | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | WORCESTER, MA-CT | 03 | 002S230 | PROJECT ERP-002S(230)X, Worcester, Blackstone Canal District Streetscape | Transportation Enhancements | 2010-11-04 | 2010-11-04 |  |  | 6748312
6081 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0833038 | 1.25 miles of roadway reconstruction of North Williamston Road from Sherwood Road to the city limits of Williamston in Ingham County. This project includes tree removals and drainage improvements. | Other | 2009-03-23 | 2009-03-26 | 2009-08-21 | 2009-08-21 | 23000 | 1.250
6082 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0833039 | 2.0 miles of pavement resurfacing of North Williamston Road from Sherwood Road to Haslett Road just north of the city of Williamston in Ingham County. This project will improve pavement rideability a | Pavement Improvement | 2009-03-23 | 2009-03-26 | 2009-08-21 | 2009-08-21 | 200000 | 1.999
6083 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | ALCONA |  | 01 | 0901004 | MDOT will resurface 5 miles of US-23 from Everett Rd to Black River Rd in the vicinity of Ossineke. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-05-05 | 2009-08-05 | 3267100.18 | 9.832
6084 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | ALCONA |  | 01 | 0901005 | MDOT will resurface 4.5 miles of M-72 from M-65 to west of O'Donnell Rd in the Huron National Forest. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2009-10-10 | 2009-10-14 | 1248007.56 | 4.310
6085 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALCONA |  | 01 | 0901006 | The Alcona County Road Commission will resurface 2.5 miles of East Black River Rd from US-23 to Lakeshore Rd east of the village of Lost Lake Woods. This will improve the driving quality by making th | Other | 2009-07-09 | 2009-07-09 | 2015-12-31 |  | 331618 | 2.949
6086 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 0902006 | This pavement project in Alger County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-14 | 2009-06-01 | 2010-04-01 |  | 93591 | 4.901
6087 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 0902007 | This pavement project in Alger County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-14 | 2009-06-01 | 2010-04-01 |  | 93591 | 5.039
6088 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 0902008 | This pavement project on Rock River Road in the Village of Chatham will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-14 | 2009-06-01 | 2010-04-01 |  | 27765.54 | 1.519
6089 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903321 | MDOT will resurface 7 miles of I-196, from 71st Street to 118th Avenue in Allegan County, just north of South Haven. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2012-12-31 | 2010-06-04 | 19479645.08 | 13.961
6090 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN | HOLLAND | 06 | 0903322 | MDOT is installing median cable guardrail on 7 miles of I-196, from 71st Street to 118th Avenue in Allegan County, just north of South Haven, to improve safety. | Safety/Traffic Management | 2009-04-02 | 2009-04-02 | 2010-12-31 | 2010-06-04 | 640856.27 | 6.980
6091 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903323 | MDOT will renovate the Glenn Rest Area on I-196 in Allegan County, to improve convenience and service to stopping motorists. | Other | 2009-04-02 | 2009-04-02 | 2011-05-30 | 2010-06-04 | 2040721.74 | 0.939
6092 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903324 | MDOT will make repairs on the bridge carrying I-196 over 71st Street in Allegan County, just north of South Haven, to make the bridge last longer. | Bridge Replacement | 2009-04-02 | 2009-04-02 | 2011-05-30 | 2010-06-04 | 353286.56 | 0.000
6093 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903327 | "The City of Allegan will resurface 2.3 miles of Babylon Road from River Street to M-40 in the city. This will improve the driving quality by making the road smoother. | Other | 2009-08-12 | 2009-09-22 | 2009-10-24 | 2009-10-17 | 120000 | 2.305
6094 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903333 | "The Allegan County Road Commisssion will resurface 4.2 miles of 109th Avenue from 48th Street to 56th Street, in the southwest part of Allegan County. | Pavement Improvement | 2009-10-06 | 2009-10-11 | 2009-11-13 | 2009-11-07 | 831422.52 | 4.209
6095 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALPENA |  | 01 | 0904009 | The Alpena County Road Commission resurface 3 miles of Leer Rd from Mellon Rd to Carr Rd in south of the village of Posen. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-28 | 2010-06-09 | 2011-06-30 | 2010-06-28 | 309392 | 3.013
6096 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ANTRIM |  | 01 | 0905006 | MDOT will resurface 1.4 miles of M-88 from South Eckhardt Rd to South Central Lake in the vicinity of Bellaire. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-09-11 |  | 627752.67 | 1.361
6097 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ANTRIM |  | 01 | 0905007 | MDOT will resurface 12 miles of M-66 from US-131 west to Lillac Creek in the vicinity of Mancelona. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2011-03-03 | 2010-08-23 | 535347.32 | 11.977
6098 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ARENAC |  | 01 | 0906004 | West of the City of Pinconning on M-65/Maple Ridge Road southeast quadrant and on M-61/I-75 southwest quadrant, there was the improvement to the park and ride lot to encourage ridesharing and reduce t | Other | 2009-04-02 | 2009-04-02 | 2010-12-01 |  | 78116.25 | 0.000
6099 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ARENAC |  | 01 | 0906005 | Repairs will be made at the US-23 bridge over Big Creek North of the City of Standish to make the bridge last longer. | Bridge Improvement | 2009-04-03 | 2009-04-03 | 2010-04-01 |  | 61671.16 | 0.000
6100 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | BARAGA |  | 01 | 0907010 | This paving of road and shoulders and installed rumble strips project on US-41 south of the City of L'Anse will improve safety and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-10-21 | 2009-10-14 | 179863.05 | 1.503
6101 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | BARAGA |  | 01 | 0907011 | This paving of road and shoulders and installed rumble strips project south of the City of L'Anse will improve safety and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-10-20 | 2009-10-14 | 1799533.59 | 11.355
6102 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 0909009 | There is 52.76 miles of shoulder widening within the Cities of Standish, Omer, and Augres to improve mobility and reduce congestion. | Transportation Enhancements | 2009-04-23 | 2009-04-23 | 2011-01-01 | 2009-09-17 | 3850080.15 | 52.875
6103 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 0909012 | Bay City is perfoming 0.19 miles of roadway realignment and intersection modifications on Marquette Avenue to improve safety. | Pavement Improvement | 2009-06-02 | 2009-08-24 | 2010-06-01 | 2010-05-28 | 480000 | 0.486
6104 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 0909018 | Within Bay City, MDOT will replace I-75 from Squaconning Creet to Hotchkiss to improve safety and increase mobility. | Pavement Improvement | 2009-09-03 | 2009-09-03 | 2013-09-19 |  | 15825489.51 | 3.687
6105 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BAY |  | 01 | 0909019 | Within Bay City, MDOT will replace I-75 from Squaconning Creet to Hotchkiss to improve safety and increase mobility. | Bridge Improvement | 2010-01-25 | 2010-02-09 | 2013-09-19 |  | 2613680.91 | 0.000
6106 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 0909020 | Within Bay City, MDOT will replace M-84 over Squaconning Creek and Dutch Creek to improve safety and increase mobility. | Bridge Replacement | 2009-04-13 | 2009-04-13 | 2013-09-19 |  | 3060406.05 | 0.000
6107 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | SAGINAW | 01 | 0909021 | This is reconstructing 4.49 miles on 6 bridges to improve safety and increase capacity. | Pavement Widening | 2003-01-28 | 2003-01-28 | 2013-12-08 |  | 13617172.4 | 3.261
6108 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 0911332 | "The City of St. Joseph will resurface 0.13 miles of Park St. from Lake Boulevard to Main Street in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-13 | 2009-09-08 | 2011-07-27 | 2009-10-30 | 204996.7 | 0.134
6109 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 0911335 | MDOT is installing median cable guardrail on 18 miles of I-94, from US-12 to I-94 BL near Bridgeman in Berrien County, just south of the Benton Harbor - St. Joseph metropolitan area, to improve safety | Safety/Traffic Management | 2009-05-29 | 2009-05-29 | 2010-11-08 |  | 3307031.67 | 36.096
6110 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 0911351 | "The Berrien County Road Commisssion will resurface 1.8 miles of Glenlord Road from I-94 BL to Cleveland Avenue and from Lincoln to M-139, through Stevensville and Shoreham, on the south side of the B | Pavement Improvement | 2009-06-30 | 2009-08-03 | 2009-09-01 |  | 75559.85 | 3.538
6111 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0911352 | "The Berrien County Road Commisssion will resurface 4 miles of Range Line Rd. from Walton Road north, between Buchanan and Berrien Springs in Berrrien County. This will improve the driving quality by | Pavement Improvement | 2009-06-30 | 2009-07-14 | 2009-09-01 |  | 68534.59 | 4.044
6112 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911353 | "The Berrien County Road Commisssion will resurface sections of Coloma Road and Range Line Road totalling 5 miles in northwest and southern Berrrien County. This will improve the driving quality by m | Pavement Improvement | 2009-06-30 | 2009-07-20 | 2010-03-01 |  | 91004.42 | 5.044
6113 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911354 | "The Berrien County Road Commisssion will resurface sections of Red Arrow Highway, Warren Woods Road and Shawnee Road totalling 4.2 miles in the southern part of Berrrien County. This will improve th | Pavement Improvement | 2009-06-30 | 2009-08-03 | 2010-03-01 |  | 89165.81 | 4.221
6114 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911355 | "The Berrien County Road Commisssion will resurface sections of Hagar Shore, Blue Star Highway and Paul Avenue totalling 5.5 miles in the northwest corner of Berrrien County. This will improve the dr | Pavement Improvement | 2009-06-30 | 2009-07-20 | 2010-03-01 |  | 77153.97 | 4.828
6115 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 0911359 | "The Berrien County Road Commisssion will resurface 8 miles of Pipestone Road, Nickerson Avenue, Sodius Parkway and Red Arrow Highway in the area south and east of the Benton Harbor - St. Joseph metro | Pavement Improvement | 2010-01-14 | 2010-07-13 | 2011-07-27 | 2010-07-18 | 610228.95 | 7.982
6116 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911363 | "The City of Watervliet will resurface 0.41 miles of East St. Joseph Avenue from M-140 to Lewis in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-02 | 2010-06-14 | 2010-08-15 |  | 153914.67 | 0.414
6117 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911364 | "The village of Baroda will resurface 0.21 miles of Hills Road. from the village limits to 1st Street in the village. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-05 | 2010-04-12 | 2011-07-27 | 2010-06-01 | 93494.14 | 0.214
6118 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911368 | "The Berrien County Road Commisssion will resurface 0.46 miles of Cleveland Avenue from Rocky Weed Rd. northward near Stevensville, just south of the Benton Harbor - St. Joseph metropolitan area. Thi | Pavement Improvement | 2010-02-24 | 2010-07-06 |  | 2010-09-08 | 198625.46 | 0.462
6119 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0911373 | MDOT will resurface 0.31 miles of US-12 BR, from Grant Street to the St. Joseph River in Niles. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2010-06-04 | 2010-06-04 | 327187.17 | 0.603
6120 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912010 | "The Branch County Road Commisssion will resurface 5.5 miles of Jonesville Road from Fremont Road to the Hillsdale County Line, east of Coldwater. This will improve the driving quality by making the | Pavement Improvement | 2009-06-04 | 2009-08-01 | 2010-03-01 |  | 85200 | 5.462
6121 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912011 | "The Branch County Road Commisssion will resurface 3.6 miles of North Fremont Road from Corless Road to US-12, just east of Coldwater. This will improve the driving quality by making the road smoothe | Pavement Improvement | 2009-06-04 | 2009-08-01 | 2010-03-01 |  | 35365.93 | 3.606
6122 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912012 | "The Branch County Road Commisssion will resurface 5.6 miles of Burr Oak Road from Bronson city limits to the St. Joseph County Line, in Branch County. This will improve the driving quality by making | Pavement Improvement | 2009-06-04 | 2009-07-27 | 2010-03-01 |  | 79182.79 | 5.629
6123 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912013 | "The Branch County Road Commisssion will resurface sections of Dunks Rd., Creamery Rd. and Railroad Rd. totalling 6.1 miles in the northwest corner of the county. This will improve the driving qualit | Pavement Improvement | 2009-06-04 | 2009-08-01 | 2010-03-01 |  | 85500 | 6.086
6124 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912014 | The Branch County Road Commisssion will resurface 5.6 miles of Orland Road and Southern Road, from Rierson Road to Dewsenberry Road, in the southwest part of the county. This will improve the driving | Pavement Improvement | 2009-06-09 | 2009-07-16 | 2010-04-01 |  | 57378 | 5.565
6125 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912015 | "The Branch County Road Commisssion will resurface 4 miles of Marshall Road from Newton Road to Girard Rd, just north of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-24 | 2009-09-23 | 2010-09-15 |  | 68522 | 4.036
6126 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912016 | "The Branch County Road Commisssion will repair one mile of Marshall Road from Newton Road to State Rd, just north of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-29 | 2009-09-22 | 2009-09-30 |  | 13055 | 1.004
6127 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912018 | "The City of Coldwater will repair various sections of W. Pearl Street totalling 8.9 miles in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-13 | 2009-09-22 | 2009-10-12 | 2009-10-12 | 52133 | 8.982
6128 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912019 | "The Branch County Road Commisssion will resurface 2.5 miles of River road from Garfield Road to US-12 and from US-12 to Narrows Road, in the city of Coldwater. This will improve the driving quality | Pavement Improvement | 2009-08-13 | 2009-08-27 | 2009-10-05 | 2009-10-05 | 47550.54 | 2.516
6129 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913222 | "The City of Battle Creek will resurface 1 mile of Beckley Road from Helmer Road to Stone Jug Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-04 | 2009-09-15 | 2011-07-27 | 2009-10-29 | 178650.2 | 1.012
6130 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913223 | "The City of Battle Creek will resurface 1 mile of Capital Avenue SW from Beckley Road to the city limits. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-04 | 2009-09-15 | 2009-10-29 | 2009-10-29 | 187342.47 | 1.001
6131 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913224 | "The City of Battle Creek will resurface 1.7 miles of Jackson Street from M-37 to Bedford Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-04 | 2009-09-15 | 2009-10-29 | 2009-10-29 | 361852.38 | 1.692
6132 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 0913225 | The Calhoun County Road Commission is building sidewalks and ADA ramps on 1.5 miles of M-96 from Columbia Avenue to I-94 BL in the city of Battle Creek, to improve pedestrian mobility and safety. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-25 | 2010-06-25 | 268455.06 | 1.463
6133 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 0913229 | The Calhoun County Road Commission will resurface 3 miles ofN Drive N from 12 Mile Road to 15 Mile Road, east of Battle Creek. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2011-07-27 | 2009-10-07 | 441159.36 | 2.976
6134 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913231 | The Calhoun County Road Commission will resurface 1.9 miles of Bellevue Road from Verona Road to McAllister, in the Battle Creek urbanized area. This will improve the driving quality by making the ro | Pavement Improvement | 2009-09-02 | 2009-10-16 | 2011-07-27 | 2009-11-18 | 270981.98 | 1.869
6135 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913232 | The Calhoun County Road Commission will resurface 0.6 miles of Beadle Lake Road from B Drive N to Division Drive, in the Battle Creek urbanized area. This will improve the driving quality by making t | Pavement Improvement | 2009-09-17 | 2009-09-30 | 2011-07-27 | 2009-10-29 | 167331.71 | 0.600
6136 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 0913233 | "The City of Marshall will resurface 0.56 miles of North Kalamazoo Avenue from Brewer Street to Linden Street in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-23 | 2009-10-01 | 2009-11-15 | 2009-11-13 | 122215.07 | 0.559
6137 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913234 | "The City of Springfield will resurface 1.3 miles of Harmonia Road from M-37 to Evergreen in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-28 | 2009-09-08 | 2011-07-27 | 2010-10-29 | 312218.59 | 1.344
6138 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914019 | The Cass County Road Commission will resurface 1.8 miles of Ironwood Drive from Redfield Street to Bell Road, in the Niles urbanized area. This will improve the driving quality by making the road smo | Pavement Improvement | 2009-07-09 | 2010-08-02 | 2010-08-30 |  | 38423.52 | 1.760
6139 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914020 | The Cass County Road Commission will resurface 0.2 miles of Redfield Road from Adamsville Road to Mason Township, in the Niles urbanized area. This will improve the driving quality by making the road | Pavement Improvement | 2009-07-09 | 2010-08-02 | 2010-08-30 |  | 11715.31 | 0.192
6140 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914021 | The Cass County Road Commission will resurface 0.5 miles of Matthews Street from Dailey Road to Cherry Grove Road, in the Dowagiac urbanized area. This will improve the driving quality by making the | Pavement Improvement | 2009-07-07 | 2009-10-01 | 2009-10-31 |  | 50000 | 0.503
6141 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914022 | The Cass County Road Commisssion will resurface 3.7 miles of Decatur Road from M-60 to Kelsey Lake Road, near Cassopolis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-08-31 | 2010-04-01 |  | 87279.15 | 3.717
6142 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914023 | The Cass County Road Commisssion will resurface 3 miles of Brownsville Street from M-62 to Crooked Creek Road,south of Cassopolis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-08-31 | 2010-04-01 |  | 73916 | 2.962
6143 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914024 | "The Cass County Road Commission will resurface various sections of Pine Lake, Monette and Dailey Streets totalling 7.3 miles in the southwest part of the county. This will improve the driving quality | Pavement Improvement | 2009-06-30 | 2009-08-31 | 2010-04-01 |  | 77650 | 2.640
6144 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914025 | The Cass County Road Commisssion will resurface 1.7 miles of Indian Lake Road fromCrystal Springs to Smith Lake Road, between Niles and Dowagiac. This will improve the driving quality by making the r | Pavement Improvement | 2009-06-30 | 2009-08-31 | 2010-05-01 |  | 32041 | 1.716
6145 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914026 | "The Cass County Road Commission will resurface various sections of Marcellus Highway totalling 0.9 miles in thenorth part of the county. This will improve the driving quality by making the road smoot | Pavement Improvement | 2009-06-30 | 2009-08-31 | 2010-04-01 |  | 82515.97 | 3.845
6146 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914027 | The Cass County Road Commission will resurface 0.18 miles of Middle Crossing Road from Yaw Street to the city limits, in the Dowagiac urbanized area. This will improve the driving quality by making t | Pavement Improvement | 2009-07-08 | 2010-08-02 | 2010-08-27 | 2009-09-28 | 20000 | 0.180
6147 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914031 | The Cass County Road Commission will resurface 1.4 miles of Huntly Road from Holly Street to Barron Lake Road, in the Niles urbanized area. This will improve the driving quality by making the road sm | Pavement Improvement | 2009-07-20 | 2009-08-31 | 2009-09-15 |  | 27500 | 1.360
6148 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914032 | The Cass County Road Commission will resurface 2.7 miles of Beebe Road from US-12 to Runkle Road and from Redfield Street to US-12, in the Niles urbanized area. This will improve the driving quality | Pavement Improvement | 2009-07-20 | 2009-08-31 | 2009-09-15 |  | 61948 | 2.798
6149 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914033 | The Cass County Road Commisssion will resurface 4 miles of Dewey Lake Street from M-51 to Glenwood road, in the northeast part of the county. This will improve the driving quality by making the road | Pavement Improvement | 2009-07-20 | 2010-07-19 | 2010-07-30 |  | 64625.83 | 3.959
6150 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914034 | The Cass County Road Commission will resurface 2.5 miles of Pine Lake Road from M-60 to Anderson Road, in the Niles urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-21 | 2009-08-31 | 2009-09-15 |  | 31578 | 1.584
6151 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 0916011 | MDOT will resurface 1.2 miles of US-23 from M-27 to the Little Black River in the village of Cheboygan. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-27 | 2009-05-27 | 2009-09-18 | 2009-11-06 | 748233.49 | 1.172
6152 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 0916013 | One and a quarter miles of Trowbridge Rd will be resurfaced from the Sturgeon River bridge to South Straights Hwy in the Village of Wolverine. This will improve the driving quality by making the road | Pavement Improvement | 2009-12-10 | 2010-05-12 | 2010-06-11 | 2010-05-20 | 14440.65 | 1.258
6153 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 0916014 | Four tenths of a mile of South Straights Hwy will be resurfaced from Cedar St to the north village limits of the Village of Wolverine. This will improve the driving quality by making the road smoothe | Pavement Improvement | 2009-12-10 | 2010-05-12 | 2010-06-11 | 2010-05-20 | 52250.24 | 0.408
6154 | Underway | C250 | Highway Infrastructure Investment Grant | MICHIGAN | CLARE |  | 04 | 0918007 | There will be 5.41 miles of paved pathway in the village of Farwell on the Pere Marquette Rail Trail for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-04-02 | 2009-04-02 | 2010-04-30 |  | 804661.79 | 5.409
6155 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON | LANSING | 08 | 0919009 | Near the city of Bath in Clinton County, MDOT will improve the driving surface of 6.5 miles of I-96 with a concrete restoration project. | Pavement Improvement | 2009-05-01 | 2009-05-01 | 2011-06-16 | 2009-10-09 | 1706751.76 | 16.097
6156 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 0919010 | Near the City of Dewitt, The Clinton County Road Commission is resurfacing 1 mile of West Alward Road from US-127BR to Williams Road to improve driving quality and make the road smoother. | Pavement Improvement | 2009-08-03 | 2009-08-11 | 2009-09-18 | 2009-09-18 | 159489.66 | 1.004
6157 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON | LANSING | 08 | 0919011 | In the city of Dewitt, over 1/2 mile of West Main Street will be resurfaced from Norris Road to Scott Street to improve ride quality and make the roadway smoother. Improvements include new sidewalk t | Pavement Improvement | 2009-08-03 | 2009-08-24 |  | 2009-10-02 | 190414.02 | 0.602
6158 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON | LANSING | 08 | 0919012 | Near the city of Dewitt, The Clinton County Road Commission is resurfacing 1 mile of East Clark Road from US-127BR to Wood Road to improve driving quality and make the road smoother. | Pavement Improvement | 2009-08-03 | 2009-08-19 | 2009-09-18 | 2009-09-18 | 276430.83 | 1.003
6159 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 0919013 | Close to the villages of Hubbardston and Pewamo, the Clinton county Road Commission will improve 4 miles of pavement on West Colony Road from the West Clinton County Line to Tallman Road. | Pavement Improvement | 2009-06-02 | 2009-06-22 | 2009-09-01 |  | 65955.65 | 3.945
6160 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 0919014 | In Bath Township, the Clinton County Road Commission will resurface 1/2 mile of East Clark Road from Webster Road to the east to improve driving quality and make the road smoother. | Pavement Improvement | 2009-08-14 | 2009-09-01 | 2009-09-18 | 2009-09-18 | 118367.91 | 0.500
6161 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON | LANSING | 08 | 0919015 | MDOT is reconstructing nearly 7 miles of I-96 in Clinton and Eaton Counties to improve driver mobility and make the roadway safer and smoother. This project is the 5000th Recovery Act project and is | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2013-06-30 |  | 44809061.06 | 15.835
6162 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 0919021 | 4 miles of East Colony Road is being resurfaced north of St. Johns to make the roadway smoother and improve ride quality. | Pavement Improvement | 2009-08-05 | 2009-08-11 | 2009-08-31 | 2009-08-31 | 68354.97 | 4.013
6163 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CRAWFORD |  | 01 | 0920009 | The Crawford County Road Commission will resurface 1.7 miles of South Wakely Bridge Rd from M-72 to The Au Sable River in the Huron National Forest near Grayling. This will improve the driving qual | Pavement Improvement | 2009-09-03 | 2009-09-21 | 2009-10-30 | 2009-11-10 | 194524.15 | 1.664
6164 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CRAWFORD |  | 01 | 0920010 | MDOT will resurface 2.4 miles of M-93 from Camp Grayling to M-72 in the vicinity of Grayling. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2010-06-25 | 2010-06-25 | 371766.66 | 2.606
6165 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CRAWFORD |  | 01 | 0920013 | MDOT will resurface 5 miles of I-75 from south of the NYC RR to north of M-93 in the vicinity of Grayling. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-02 | 2009-06-02 | 2011-05-05 | 2010-10-05 | 3332348.34 | 5.319
6166 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 0921011 | This intersection project at US-2 and US-41 in the City of Rapid River will increase safety and improve the pavement condition which will make for a smoother ride. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-10-18 | 2010-10-01 | 1480559.11 | 1.165
6167 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 0921014 | This pavement project on County Road 513 in Delta County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-19 | 2010-01-04 | 2010-10-31 | 2010-08-27 | 244861 | 11.418
6168 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 0922007 | This Center Left-Turn lane project on M-95 in Sagola will improve safety and increase mobility. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2010-10-18 | 2009-10-09 | 373727.53 | 0.363
6169 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 0922008 | This pavement project on Balsam Street in the City of Kingsford will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-09-01 | 2009-09-28 | 2009-10-20 | 2009-10-19 | 222475.03 | 0.497
6170 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | EATON | LANSING | 07 | 0923010 | In Eaton County just outside of city of Lansing limits , 2.41 miles of Creyts Road is to be resurfaced from Lansing Road to I-496. This work will improve driving quality and make the road smoother. | Pavement Improvement | 2009-06-29 | 2009-07-13 | 2009-10-30 | 2009-07-30 | 667891.65 | 2.414
6171 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | EATON | LANSING | 07 | 0923012 | In the City of Grand Ledge, just over 1/4 miles of Brookside Drive from Timbercreek Street to South Street will be reconstructed to improve rideability and make the roadway smoother. | Pavement Improvement | 2009-07-31 | 2009-08-03 | 2009-09-14 | 2009-09-17 | 204723.78 | 0.349
6172 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | EATON | LANSING | 07 | 0923013 | In the City of Grand Ledge, 1/4 miles of Timber Creek Drive from Saginaw highway to Brookside Drive will be reconstructed to improve rideabilty and make the roadway smoother. | Pavement Improvement | 2009-07-31 | 2009-08-03 | 2009-09-14 | 2009-09-17 | 188445.44 | 0.284
6173 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 0923015 | In the City of Eaton Rapids, MDOT is working on building a streetscape project on South Clinton Trail and South Main Street (State Routes M-99 & M-50) The work will be from just west of Hallawood Lan | Pavement Improvement | 2009-06-17 | 2009-06-17 | 2012-09-20 |  | 2503080.71 | 1.385
6174 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 0923016 | The City of Eaton Rapids in Eaton County will beautify its downtown by building this streetscape. The streetscape will include new brick pavers, lighting, decorative sidewalk and and additional lands | Transportation Enhancements | 2009-06-10 | 2009-06-10 | 2012-09-20 |  | 842075.88 | 0.397
6175 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | EATON | LANSING | 07 | 0923017 | In Eaton County just outside of city of Lansing limits , 1/2 mile of Creyts Road is to be resurfaced from Saginaw highway to the north. This work will improve driving quality and make the road smooth | Pavement Improvement | 2009-10-07 | 2010-07-23 | 2010-05-31 |  | 116714.16 | 0.499
6176 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EMMET |  | 01 | 0924008 | The Emmet County Road Commission will resurface three quarters of a mile of Mitchell Rd from Division Rd east 3900 ft in the vicinity of Petoskey. This will improve the driving quality by making the | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2009-10-19 | 2009-10-19 | 155000 | 0.654
6177 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EMMET |  | 01 | 0924009 | The Emmet County Road Commission will resurface 2.3 miles of W Conway Rd from Heydey St to Clayton Rd in Little Traverse Township. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-01 | 2009-05-01 | 2009-11-15 | 2009-11-06 | 348268.4 | 2.331
6178 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 0925015 | Just west of the city of Flint, MDOT will repair M-13 over Mistequay Creek to make the bridge last longer. | Bridge Improvement | 2009-04-02 | 2009-04-02 | 2011-04-01 |  | 187704.94 | 0.000
6179 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 0925016 | Just west of the city of Flint, MDOT will repair 12.2 miles of M-13 to extend the service life of the existing pavement. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-01-15 |  | 4980018.63 | 12.395
6180 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 0925018 | Within the City of Fenton, MDOT will resurface parking lot on US-23 to improve the quality of the parking surface and extend the life of the road pavement. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2010-12-31 | 2009-08-25 | 94674.25 | 0.000
6181 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925021 | The MDOT will design roadway and bridge improvements to I-475 from the I-75 and I-69 interchange south of Flint north 6.6 miles. | Other | 2009-05-14 | 2009-05-14 | 2009-12-31 |  | 825251.03
6182 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925023 | Near the city of Flint, MDOT is upgrading 1.16 miles of pavement on Pasadena Avenue from I-75 to the Flint city limits, Genesee County. This will improve the ride quality of the road. | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2010-08-15 |  | 1536295 | 1.087
6183 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925024 | There will be 1.10 miles of pavement repair on Clio Road from Pierson Road to Carpenter Road to improve safety and increase mobility. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-08-15 |  | 1356636.75 | 0.997
6184 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 0925032 | Genesee County is resurfacing 0.99 miles on Irish Road from Richfield Road northerly to Carpenter Road to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-08-15 | 2010-06-30 | 624753 | 0.925
6185 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925038 | Genesee County will repair the pavement of 0.83 miles on Morrish Road from I-69 to the Canadian National Railway railroad tracks in the city of Swartz Creek to improve the driving quality of the road. | Pavement Improvement | 2009-07-02 | 2009-07-02 | 2010-08-15 | 2009-12-31 | 251247.76 | 0.918
6186 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925041 | In the City of Fenton in Genesee County there is 1.16 miles of resurfacing on Silver Parkway from Owen Road to Silver Lake Road to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-10-23 | 2009-10-26 | 2010-10-30 | 2010-06-30 | 1180758.17 | 0.912
6187 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925046 | In the city of Flint there is 0.95 miles of road reconstruction on Kettering Gateway from I-69 to Chevrolet Avenue to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2011-05-27 |  | 2315955.02 | 0.640
6188 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925054 | In Genesee County, MDOT will perform a Design Build reconstruction of 4 bridge structures on I-475 from the south interchange to I-69 including Hill road and Bristol Road over I-475 and I-475 over Map | Pavement Improvement | 2009-09-18 | 2009-09-18 | 2012-12-31 |  | 19523521.35 | 14.929
6189 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GLADWIN |  | 01 | 0926009 | The County of Gladwin is resurfacing 2.02 miles of roadway to improve the driving quality of the Knox Road from Shock Road easterly to Dundas Road. | Pavement Improvement | 2009-09-02 | 2009-10-05 | 2009-11-07 | 2009-11-11 | 387200 | 1.987
6190 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 0927008 | This pavement project on US-2 in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-01 | 2009-05-01 | 2010-10-18 | 2009-10-02 | 1843722.08 | 16.204
6191 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 0927014 | This pavement and guardrail project on US-45 in Gogebic County will improve the safety and ride quality of the road. | Pavement Improvement | 2009-08-13 | 2009-08-13 | 2010-10-18 | 2010-07-15 | 1874469.38 | 12.415
6192 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0928008 | East 8th St in Traverse City will be resurfaced for over a half mile from garfield to Woodmere St. This will improve the driving quality by making the road smoother. | Other | 2009-10-19 | 2010-04-12 | 2010-06-23 | 2010-07-14 | 210000 | 0.605
6193 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0928010 | The Grand Traverse County Road Commission will place new pavement markings at various locations on county roads in the county to provide more visible markings. | Safety/Traffic Management | 2009-10-08 | 2010-05-18 | 2010-06-18 | 2010-05-26 | 277500 | 1.434
6194 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0928011 | The Grand Traverse County Road Commission will place new pavement symbols at various locations on county roads in the county to provide safer roadways. | Safety/Traffic Management | 2009-08-13 | 2009-09-18 | 2010-08-30 | 2010-08-27 | 80032.6 | 1.434
6195 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0928012 | The Grand Traverse County Road Commission will resurface 3.2 miles of karlin Rd from M-137 to Nessen Rd south of the village of Green Lake. This will improve the driving quality by making the road sm | Pavement Improvement | 2009-12-17 | 2010-06-01 | 2010-07-02 | 2010-06-29 | 404957.82 | 3.000
6196 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRATIOT |  | 04 | 0929208 | Near the city of Alma there will be 4.05 miles of resurfacing on Lumberjack Road from M-46 northerly to North County Line Road to improve driving quality by making the road smoother. | Other | 2009-12-22 | 2010-04-27 | 2010-08-13 | 2010-08-13 | 446327 | 4.057
6197 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GRATIOT |  | 04 | 0929210 | The city of Alma is resurfacing 8.92 miles on M-46 from the Gratiot/Montcalm County line easterly to west of US-127BR to improve driving quality by making the road smoother. | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2012-02-01 | 2010-11-01 | 1648382.16 | 8.920
6198 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930012 | 5.29 miles of South Waldron Road from Territorial Road northerly to Prattville Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness through the community | Pavement Improvement | 2009-05-28 | 2009-06-30 | 2010-03-01 |  | 69889.47 | 5.291
6199 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930013 | 2.75 miles of Church Road from Waldon Road to US-127 will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness east of the city of Hillsdale, Hillsdale County. | Pavement Improvement | 2009-05-28 | 2009-06-29 | 2010-03-01 |  | 44312.91 | 2.754
6200 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930014 | 2.91 miles of North Adams Road from the Village of Jonesville to Mimes Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness in Hillsdale County. | Pavement Improvement | 2009-05-28 | 2009-06-11 | 2010-03-01 |  | 93387.72 | 2.914
6201 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930015 | 3.0 miles of North Adam Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, South of the City of Jackson in Hillsdale County. | Pavement Improvement | 2009-05-28 | 2009-06-01 | 2010-03-01 |  | 91506.45 | 3.004
6202 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930016 | 3 miles of East Bacon Road will have a Chip and Seal treatment from Peterson Road to Osseo Road east of the village of Hillsdale, Hillsdale County. The work will preserve the pavement life and improv | Pavement Improvement | 2009-05-28 | 2009-06-29 | 2010-03-01 |  | 83859 | 2.993
6203 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930017 | 5 miles of South Allen Road from Bankers Road to US-12 will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness. This proejct is located just west of the city of | Pavement Improvement | 2009-06-02 | 2009-06-29 | 2010-03-01 |  | 93791.85 | 4.960
6204 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931007 | This paving project on US-41 east of the City of Houghton will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2009-06-22 | 2009-06-22 | 353754.39 | 2.046
6205 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931008 | This pavement project on US-41 in Houghton County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-10-18 | 2009-06-22 | 328382.32 | 2.654
6206 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931009 | This shoulder paving and guardrail installation project on M-26 in Houghton County will serve cyclists, joggers and other non-motorized users and will improve safety. | Transportation Enhancements | 2009-04-02 | 2009-04-02 | 2009-08-18 | 2009-08-18 | 176732.89 | 2.443
6207 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931010 | This paving project on M-26 in the Village of Lake Linden will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-10-18 | 2009-08-18 | 472359 | 2.577
6208 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931014 | This pavement project on Erickson Drive in the Houghton Urban Area will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-31 | 2009-09-23 | 2009-10-15 | 2009-10-15 | 90000 | 0.450
6209 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931015 | This pavement project on 6th Street in the City of Larium will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-31 | 2009-09-23 | 2009-10-15 | 2009-10-15 | 115000 | 0.361
6210 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931017 | This pavement project on Sharon Ave. in the Houghton Urban Area will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-09-01 | 2009-09-22 | 2009-10-15 | 2009-10-15 | 88521.77 | 0.480
6211 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 0932213 | North of Sebewaing, MDOT is upgrading 3.6 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-04-14 | 2009-04-14 | 2011-03-31 |  | 140515.08 | 3.588
6212 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 0932214 | West of Port Austin, MDOT is upgrading 4.8 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-04-16 | 2009-04-16 | 2011-03-31 | 2010-05-21 | 293993.36 | 4.886
6213 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 0932219 | There will be 2.68 miles of resurfacing on Atwater Road from Parisville Road easterly to west of Ruth Road to improve the driving quality of the road by making the road smoother. | Pavement Improvement | 2009-07-22 | 2009-08-29 | 2009-09-30 | 2009-09-16 | 355560.72 | 2.940
6214 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 0932220 | Near the city of Sebewaing there are 16.28 miles sidewalk improvements on M-25 from south of Huron Line Road northeasterly to south of Myers Road, from south of Orchard Street northerly to south of De | Transportation Enhancements | 2009-05-29 | 2009-05-29 | 2010-03-31 | 2009-09-19 | 324892.76 | 3.793
6215 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933024 | Near the community of Haslett MI, just over 1/4 miles of Marsh Road will be resurfaced from Baker Street to the north Ingham County Line. This project will improve rideabilty and make the roadway smo | Pavement Improvement | 2009-07-02 | 2009-07-27 | 2009-07-31 | 2010-07-28 | 85831.39 | 0.340
6216 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0933025 | Between the cities of Leslie and Eaton Rapids in Ingham County, 6.0 miles of Bellevue Road will have Chip and Seal treatment to preserve pavement life and improve pavement rideabilty. | Pavement Improvement | 2009-05-05 | 2009-07-07 | 2009-09-01 |  | 93999.72 | 6.149
6217 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0933026 | South of Mason in Ingham County, Barnes Road will have Chip and Seal treatment from South College Road to South Meridian Road to preserve pavement life and improve pavement rideability. This project | Pavement Improvement | 2009-05-05 | 2009-07-20 | 2009-09-01 |  | 93999.85 | 6.474
6218 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933028 | 0.95 miles of South Washington Road from West Jolly Road to Miller Road will be resurfaced in the City of Lansing. Improvements include ADA sidewalk ramp upgrades for increased pedestrian access and | Pavement Improvement | 2009-08-05 | 2009-08-05 |  | 2009-09-25 | 307900.69 | 0.948
6219 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933029 | In the City of East Lansing, 1 mile of East Mount Hope Avenue will be reconstructed along the southern limits of the city. The new roadway will improve rideablity and improve drainage features. | Pavement Improvement | 2009-07-22 | 2009-07-29 | 2009-10-02 | 2009-10-08 | 681219.99 | 1.471
6220 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0933030 | West of the Village of Stockbridge, 4.75 miles of Morton and Heeney Roads will have Chip and Seal treatment to preserve pavement life and improve rideability. | Pavement Improvement | 2009-05-21 | 2009-07-20 | 2009-09-01 |  | 62576.43 | 4.079
6221 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933032 | 0.45 miles of Michigan Avenue from US-127 to Friendship Court will be resurfaced in the City of Lansing. Improvements include concrete curb & gutter and sidewalk replacement. The work will improve r | Pavement Improvement | 2009-08-05 | 2009-08-17 | 2009-09-21 | 2010-08-25 | 456655.26 | 0.788
6222 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933034 | Near Williamston in Ingham county, MDOT will resurface about 8 miles of I-96 to improve driving quality by making the road smoother. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2012-03-01 | 2009-11-15 | 3259504.55 | 17.302
6223 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933036 | In the community of Holt in Ingham County, 1.37 miles of West Holt Road from Heatherton Drive to Thornburn Street will be resurfaced to improve rideabilty and make the roadway smoother. | Pavement Improvement | 2009-07-07 | 2009-09-01 | 2009-11-15 | 2010-10-19 | 766216.73 | 1.329
6224 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933037 | Near the community of Haslett MI, 1/2 miles of Marsh Road will be resurfaced from Tihart Road to just north of Franklin Street in Ingham County. This project will improve rideabilty and make the road | Pavement Improvement | 2009-09-21 | 2009-10-01 | 2010-05-31 | 2010-12-08 | 502319.43 | 0.789
6225 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 0934011 | The MDOT will resurface 4 miles of M-66 near the City of Ionia. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-12-31 | 2009-06-29 | 894235.57 | 3.902
6226 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 0934014 | The City of Ionia will resurface over a half mile of West Adams Street from M-66 to Jackson Street in the City of Ionia. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-08-31 |  | 2009-09-25 | 259020.75 | 0.691
6227 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 0937007 | Within the City of Mt. Pleasant, MDOT will repair 4.85 miles of US-127 south of the Blanchard Road interchange to extend the service life of the existing road as well as make repairs to the bridge to | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2011-12-01 |  | 10705176.85 | 10.526
6228 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 0937012 | The City of Rosbush is reconstructing 3.00 miles on Vernon Road from Winn Road easterly to Vandecar Road and from Lincoln Road easterly to Mission Road to improve driving quality by making the road sm | Pavement Improvement | 2009-10-05 | 2009-10-09 | 2009-11-06 | 2009-11-12 | 472051 | 3.004
6229 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON |  | 07 | 0938221 | In Jackson County, the County Road Commission will reconstruct East Michigan Avenue from Fox Road to Gillett's Lake Road to improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-04 | 2009-08-17 |  | 2009-11-03 | 624776.04 | 0.755
6230 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 0938222 | In the city of Jackson, Jackson County, the city will resurface 1/2 mile of Ganson Street from Cooper Street to East Avenue. The project will include sidewalk repairs and new ADA ramps to improve ped | Pavement Improvement | 2009-08-26 | 2009-09-08 |  | 2009-11-03 | 286346.77 | 0.461
6231 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 0938223 | In the city of Jackson, Jackson County, the city will resurface 1/2 mile of West Morrell Street from Brown Street to West Avenue. The project will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-09-08 |  | 2009-11-03 | 300068.85 | 0.502
6232 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 0938224 | In the city of Jackson, Jackson County, the city will reconstruct just under 1/2 mile of North Jackson Street from Glick Highway to Ganson Street to improve driving quality by making the road smoother | Pavement Improvement | 2009-12-23 | 2010-04-05 | 2010-07-30 | 2010-07-26 | 532421.84 | 0.371
6233 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 0938241 | In Jackson County, the County Road Commission will resurface Springport Road from Shirley Drive to Airport Road to improve just over a mile of road to improve drive quality by making the road smoother | Pavement Improvement | 2010-02-03 | 2010-05-05 |  | 2010-07-09 | 617319.23 | 1.273
6234 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939011 | MDOT will reconstruct the interchange of I-94 at Westnedge Avenue to a new design and will reconstruct and add a lane in each direction to 1.9 miles of I-94, between Oakland Drive and Lovers Lane, in | Pavement Widening | 2009-04-07 | 2009-04-07 | 2012-12-31 |  | 46802075.36 | 5.516
6235 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939012 | "The City of Portage will resurface 1.6 miles of E. Centre Avenue from Portage Road to Westnedge Avenue in the Kalamazoo urbanized area. This will improve the driving quality by making the road smooth | Pavement Improvement | 2009-06-22 | 2009-07-08 | 2011-07-27 | 2009-09-10 | 900000 | 1.612
6236 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939013 | "The City of Portage will resurface 0.75 miles of E. Kilgore Road from Westnedge Avenue to Grand Elk RR in the Kalamazoo urbanized area. This will improve the driving quality by making the road smooth | Pavement Improvement | 2009-06-30 | 2009-07-20 | 2011-07-27 | 2009-10-16 | 647541.67 | 0.743
6237 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939015 | The Kalamazoo County Road Commisssion will resurface 2.6 miles of S Avenue from Sprinkle Road to 29th Street, in the Kalamazoo urbanized area. This will improve the driving quality by making the road | Pavement Improvement | 2009-07-31 | 2009-08-24 | 2011-07-27 | 2009-10-21 | 940291.85 | 2.579
6238 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939016 | The Kalamazoo County Road Commisssion will resurface 1 mile of S. 8th Street from R Avenue to Q Avenue, in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoot | Pavement Improvement | 2009-08-03 | 2009-08-24 | 2011-07-27 | 2009-10-19 | 320496.79 | 1.001
6239 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO |  | 06 | 0939017 | The Kalamazoo County Road Commisssion will resurface 1 mile of N. 12th Street from D Avenue to C Avenue, in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoo | Pavement Improvement | 2009-08-03 | 2009-08-24 | 2011-07-27 | 2009-10-19 | 395590.35 | 1.005
6240 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939022 | "The City of Kalamazoo will resurface 1.15 miles of E. Cork Street from Westnedge Avenue to Lovers Lane in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-10 | 2009-09-21 |  |  | 493397.75 | 1.151
6241 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939023 | "The City of Kalamazoo will resurface 0.6 miles of Reed Street from Burdick Avenue to Portage Avenue in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-10 | 2009-09-21 |  |  | 194445.25 | 0.606
6242 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939024 | "The City of Kalamazoo will resurface 0.4 miles of S. Burdick Street from Cork Street to Crescent in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-10 | 2009-09-21 |  |  | 179661.5 | 0.434
6243 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939025 | "The City of Kalamazoo will resurface 1.1 miles of Lovers Lane from Cork Street to Kilgore Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-10 | 2009-09-21 |  |  | 254334.05 | 1.073
6244 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939026 | "The City of Kalamazoo will resurface 0.25 miles of N. Edwards Street from South Street to Kalamazoo Avenue in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-15 | 2009-09-22 | 2010-05-14 |  | 330192.5 | 0.252
6246 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939032 | "The village of Schoolcraft will resurface 1 mile of E. Eliza Street from west village limits to 14th Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-10-20 | 2009-10-21 | 2011-07-27 | 2010-06-14 | 221992.58 | 0.987
6247 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALKASKA |  | 04 | 0940007 | The Kalkaska County Road Commission will resurface 5 miles of County Highway 612 from the east county line to Blue Lake Rd and Darke to Rogers Rd . This will improve the driving quality by making the | Pavement Improvement | 2009-12-18 | 2010-06-07 | 2010-06-11 | 2010-06-12 | 285637.3 | 4.687
6248 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941141 | The City of Wyoming will resurface one mile of Prairie Parkway from Byron Center to Burlingame Avenue in the City of Wyoming. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-13 | 2009-07-13 | 2009-09-30 | 2009-10-01 | 461140.4 | 1.000
6249 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941142 | The City of Wyoming will resurface two miles of Burlingame Avenue from 52 Street to 36th Street in the City of Wyoming. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-13 | 2009-07-13 | 2009-09-30 | 2009-10-01 | 847806.13 | 2.030
6250 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941143 | The City of Walker will resurface a half mile of Veteran's Memorial Drive from Riverbend to Maynard Avenue in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-02 | 2009-07-06 | 2009-08-31 | 2009-08-11 | 107983.75 | 0.499
6251 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941144 | The City of Walker will resurface 0.1 of a mile of Three Mile Road from Alpine Avenue to the I-196 exit ramp in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-29 | 2009-07-15 | 2009-08-31 | 2009-08-11 | 269634.14 | 0.130
6252 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941146 | The Kent County Road Commission will resurface two and three quarters of a mile of 5 Mile Road from Gavin Lake Road to Lincoln Lake Road in Kent County. This will improve the driving quality by makin | Pavement Improvement | 2009-08-14 | 2009-09-14 | 2009-09-25 | 2009-10-16 | 672341.54 | 2.745
6253 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941147 | The MDOT will make repairs to the bridges at US-131and Pine Island Drive, Post Road, and 10 Mile Rd to make the bridges last longer. | Bridge Improvement | 2009-04-23 | 2009-04-23 | 2010-12-31 | 2009-11-12 | 1651287.13 | 0.000
6254 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941149 | The City of Grand Rapids will resurface a half mile of Leonard Street from Nixon Street to Collingsdale Avenue in the City of Walker. This will improve the driving quality by making the road smoother | Pavement Improvement | 2009-06-30 | 2009-07-13 | 2011-06-15 | 2010-11-13 | 1273577.98 | 0.535
6255 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941150 | The City of Grandville will resurface 0.2 of a mile of Potomac Avenue from 44th Street to Century Center in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-22 | 2009-09-14 | 2009-09-30 | 2009-10-21 | 68678.74 | 0.224
6256 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941151 | The City of Grandville will resurface 0.2 of a mile of Kenowa Avenue from the south City limits to Stonehenge Drive in the City of Grandville. This will improve the driving quality by making the road | Pavement Improvement | 2009-07-22 | 2009-09-14 | 2009-09-30 | 2009-10-21 | 76696 | 0.170
6257 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941152 | The City of Grandville will resurface 0.4 of a mile of 44th Street from Potomac Avenue to Rivertown Parkway in the City of Grandville. This will improve the driving quality by making the road smoothe | Pavement Improvement | 2009-07-22 | 2009-09-14 | 2009-09-30 | 2009-10-21 | 79502 | 0.373
6258 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941153 | The City of Grandville will resurface 0.1 of a mile of 44th Street from Kenowa Avenue to the I-196 ramp in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-22 | 2009-09-14 | 2009-09-30 | 2009-10-21 | 79502 | 0.114
6259 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941156 | The City of East Grand Rapids will resurface a 0.3 miles of Lake Drive from the west city limits to Plymouth Road in the City of East Grand Rapids. This will improve the driving quality by making t | Pavement Improvement | 2009-07-30 | 2009-08-03 | 2009-10-31 | 2009-10-30 | 332036 | 0.330
6260 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941158 | The Kent County Road Commission will resurface over 1.5 miles of Patterson Avenue from 44th Street to M-37 in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-11 | 2009-08-13 | 2010-05-15 | 2009-11-04 | 1100000 | 1.596
6261 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941159 | The Kent County Road Commission will resurface two and half miles of 84th Street from Cherry Valley Avenue to Whitneyville Avenue in Kent County. This will improve the driving quality by making the r | Pavement Improvement | 2009-07-17 | 2009-08-04 | 2009-10-31 | 2009-10-19 | 606650.43 | 2.508
6262 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941162 | The City of East Grand Rapids will resurface a quarter of a mile of Breton Avenue from the norht city limits to Burton Street in East Grand Rapids. This will improve the driving quality by making the | Pavement Improvement | 2009-08-03 | 2009-08-10 | 2010-06-11 | 2010-06-11 | 300000 | 0.251
6263 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941166 | The MDOT will make repairs to the bridge at M-57 over the White Pine Trail north of Grand Rapids to make the bridge last longer. | Bridge Improvement | 2009-05-28 | 2009-05-28 | 2011-03-31 | 2010-05-21 | 532283.83 | 0.000
6264 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 0941172 | The MDOT is deploying ITS technology on M-6 at I-196, I-96 and at M-11 and M-6 in Kent County, Grand Rapids area to improve mobility and reduce congestion | Safety/Traffic Management | 2009-06-15 | 2009-06-15 | 2011-01-01 |  | 958408.89 | 46.718
6265 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941176 | The MDOT is integrating ITS technoligies on US-131, I-96 and I-196 at 31 locations around Kent County in the Grand Rapids area to improve mobility and reduce congestion. | Safety/Traffic Management | 2009-06-23 | 2009-06-23 | 2012-07-15 |  | 307584.59 | 0.000
6266 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 0941177 | The MDOT will make repairs to the bridge at M-11 over the Grand River in the City of Walker to make the bridge last longer. | Bridge Improvement | 2009-06-23 | 2009-06-23 | 2010-12-31 | 2010-05-01 | 699844.45 | 0.000
6267 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941179 | The City of Grand Rapids will beautify Madison Avenue and Hall Street in the vicinity of Adams St and in the vicinity of Jefferson Ave by building this streetscape. | Pavement Improvement | 2009-10-15 | 2009-11-16 | 2012-09-30 |  | 744772.43 | 1.373
6268 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941187 | The MDOT will widen almost 4 miles of I-196 freeway from the Grand River East to Fuller Avenue in the Grand Rapids area to improve mobility and reduce congestion | Pavement Widening | 2009-08-18 | 2009-08-18 | 2013-01-31 |  | 28687610.13 | 13.090
6269 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941188 | The MDOT will replace 2 miles of I-196 freeway lighting from the Grand River East to Fuller Avenue in the Grand Rapids area to improve driver visibility. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2011-09-21 |  | 541784.06 | 3.876
6270 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941189 | The MDOT will replace the I-196 bridges over Lafayette Avenue in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 2009-09-30 | 2009-09-30 | 2011-06-01 |  | 2489775.9 | 0.000
6271 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941190 | The MDOT will replace the Coit Avenue bridge over I-196 in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 2009-08-18 | 2009-08-18 | 2012-12-31 |  | 2679687.79 | 0.000
6272 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 0941203 | The City of Kent City will resurface 0.2 miles of South Main Street from Ball Creek Road to M-46/17 Mile Road in the City of Kent City. This will improve the driving quality by making the road smooth | Pavement Improvement | 2010-06-22 | 2010-07-06 | 2010-09-10 | 2010-09-09 | 70000 | 0.161
6273 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941206 | The Kent County Road Commission will resurface one and a half miles of Leonard Street from M-44 to Crahen Street in Grand Rapids Township. This will improve the driving quality by making the road smo | Pavement Improvement | 2010-01-14 | 2010-06-14 | 2010-07-30 | 2010-07-30 | 477806.86 | 1.494
6274 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941211 | The City of Grand Rapids will resurface 0.2 miles of Lake Drive from Cherry Street to Fuller Avenue in the City of Grand Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-21 | 2010-04-19 | 2010-06-30 | 2010-06-30 | 167553.5 | 0.212
6275 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KEWEENAW |  | 01 | 0942131 | This pavement project on Eagle Harbor Road in Keweenaw County will improve the drive quality and make the road smoother. | Other | 2010-01-14 | 2010-06-10 | 2010-07-01 | 2010-06-24 | 164462 | 3.510
6276 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAKE |  | 02 | 0943229 | The Lake County Road Commission will resurface 5 miles of South Hawkins Rd from US-10 south in the vicinity of Reed City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-02 | 2009-08-03 | 2010-03-01 |  | 91940 | 4.987
6277 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAKE |  | 02 | 0943230 | The Lake County Road Commission will resurface 6 miles of W Star Lake Drive around Star Lake in the Manistee National Forest southwest of the village of Baldwin. This will improve the driving qualit | Pavement Improvement | 2009-06-02 | 2009-08-03 | 2010-03-01 |  | 93284.61 | 6.047
6278 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAKE |  | 02 | 0943231 | The Lake County Road Commission will resurface 5 miles of E 92nd St and S BroadwayRd from S Forman to 96th and from 72nd to 92nd St in the Manistee National Forest. This will improve the driving qua | Pavement Improvement | 2009-06-02 | 2009-08-03 | 2010-03-01 |  | 88948.07 | 4.797
6279 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAKE |  | 02 | 0943232 | The Lake County Road Commission will resurface 4 miles of West 52nd St from the Baldwin Village limits westward. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-04 | 2009-08-03 | 2010-03-01 |  | 73501 | 3.629
6280 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 0944088 | In the city of Fenton, MDOT is resurfacing existing car pool lots at the US-23 exit to Silver Lake Road, on M-24 north of Barnes Lake Road, on M-90 between Brush Street and Baldwin Avenue, and on M-24 | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2010-12-31 |  | 61606.17 | 0.000
6281 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 0944089 | Within the City of North Branch, MDOT will resurface parking lot on M-90 to improve the quality of the parking surface and extend the life of the road pavement. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2010-12-31 |  | 22729.22 | 0.000
6282 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 0944092 | The city of Lapeer will reconstruct 0.31miles on N Saginaw Street to improve the driving quality by making the road smoother. | Other | 2010-02-10 | 2010-04-05 | 2010-08-13 | 2010-07-28 | 240000 | 0.215
6283 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LEELANAU |  | 04 | 0945329 | MDOT will resurface 16.5 miles of M-72 from the Village of Empire to Bugai Rd. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-09 | 2009-06-09 | 2011-05-05 | 2010-06-24 | 932630.33 | 16.401
6284 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LEELANAU |  | 04 | 0945330 | The MDOT will construct a passing relief lane on M-72 from Cedar Run Rd to Goodrick Rd west of Traverse City. This will allow safer driving operations on M-72. | Pavement Widening | 2009-06-30 | 2009-06-30 | 2011-05-05 | 2010-07-09 | 1409246.4 | 1.124
6285 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LEELANAU |  | 04 | 0945332 | The Leelanau County Road Commission will resurface 1.5 miles of County Road 651 from Hohnke Rd to M-22 in the vicinity of Empire. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2010-06-04 | 2010-06-03 | 271725 | 1.585
6286 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON |  | 08 | 0947010 | 8.3 miles of resurfacng of US-23 from I-96 to M-59 just north of Brighton in Livingston County. This project will provide for improved rideability and increased pavement smoothness. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-02-09 | 2009-10-10 | 3118815.4 | 16.563
6287 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON |  | 08 | 0947011 | A new Carpool lot will be constructed at Burkhart Road just west of M-59 near the I-96 Interchange west of Howell. This lot will encourage ridesharing and reduce the number of cars on the roadway. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-30 | 2010-09-30 | 164813.91 | 0.020
6288 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947012 | MDOT will improve mobility and reduce congestion with installation of an Intelligent Transportation System (ITS) along I-96 from the city of Fowlerville easterly to the Oakland/Livingston County line | Safety/Traffic Management | 2009-06-15 | 2009-06-15 | 2010-12-31 |  | 533441.41 | 69.774
6289 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947015 | This project will provide for 1.5 miles of pavement resurfacing on East Grand River Avenue from Lake Chemung to 1/3 of a mile east of Hughes Road between the cities of Howell and Brighton in Livingsto | Pavement Improvement | 2009-09-18 | 2009-09-22 | 2010-06-30 | 2009-11-16 | 1157821.59 | 1.517
6290 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947016 | This project will provide for 0.40 miles of pavement resurfacing on Main Street from Third Avenue to Grand River Avenue in the city of Brighton, Livingston County. This will provide for improved pave | Pavement Improvement | 2009-09-21 | 2009-10-13 |  | 2009-11-03 | 254732.5 | 0.402
6291 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON |  | 08 | 0947018 | This project will provide for 2 miles of pavement resurfacing on Old US-23 from Dean Road to Faussett, north of the city of Brighton in Livingston County. This will provide for improved pavement ride | Pavement Improvement | 2010-01-14 | 2010-05-10 |  | 2010-07-09 | 387535.68 | 2.056
6292 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947020 | This project will provide for 1.1 miles of pavement resurfacing on North Michigan Avenue from Grand River Avenue to M-59 in the city of Howell, Livingston County. This will provide for improved pavem | Pavement Improvement | 2009-10-07 | 2009-10-16 | 2009-11-14 | 2009-11-25 | 289075.98 | 1.104
6293 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947021 | 1/3 of a mile of Walnut Street is being resurfaced from Maple Street to Clinton Street in the City of Howell, Livingston County to make the roadway smoother and improve ride quality. | Pavement Improvement | 2009-10-07 | 2009-10-16 | 2009-11-14 | 2009-11-25 | 100587.13 | 0.349
6294 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACKINAC |  | 01 | 0949011 | This pavement and Rumble Strip project on US-2 in Mackinac County will improve safety and make the road smoother. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-10-18 | 2009-10-01 | 2541340.8 | 6.012
6295 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950035 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of 12 Mile Road in Macomb County. | Pavement Improvement | 2009-07-27 | 2009-08-03 | 2009-09-30 | 2010-10-05 | 477842.61 | 0.465
6296 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB |  | 10 | 0950036 | Resurfacing to maintain the pavement condition and improve ride quality of ramps at I-94 at 9 Mile Road, 10 Mile Road, and 23 Mile Road, and on M-19 in the city of St. Clair Shores by MDOT. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2011-06-30 | 2009-11-20 | 523547.97 | 0.897
6297 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950037 | Resurfacing to maintain the pavement condition and improve ride quality of Ten Mile Road in Eastpointe. | Pavement Improvement | 2009-08-04 | 2009-08-15 | 2009-11-30 | 2009-11-30 | 318522.68 | 0.505
6298 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950038 | One mile of resurfacing to maintain the pavement condition and improve ride quality of 10 Mile Road in East Pointe and Center Line. | Pavement Improvement | 2009-08-04 | 2009-08-15 | 2009-11-30 | 2009-11-30 | 468171.04 | 0.839
6299 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB |  | 10 | 0950040 | Resurfacing to maintain the pavement condition and improve ride quality of M-19 near Richmond by MDOT. | Pavement Improvement | 2009-05-29 | 2009-05-29 | 2011-06-30 | 2009-11-20 | 2093831.25 | 4.112
6300 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB |  | 10 | 0950041 | Three miles of microsurfacing to preserve the pavement condition and improve ride quality of North Avenue and 26 Mile Road in Macomb County. | Pavement Improvement | 2009-09-08 | 2009-09-16 | 2009-10-30 | 2009-10-08 | 293071.55 | 3.321
6301 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950045 | 2 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along 15 Mile Road in Sterling Heights by MDOT. | Pavement Improvement | 2009-09-10 | 2009-09-14 | 2010-06-30 | 2010-09-21 | 2089235.2 | 2.226
6302 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950046 | Two and a half miles of resurfacing to maintain the pavement condition and improve ride quality of M-3 in Mount Clemens by MDOT. | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-06-01 |  | 4278652.53 | 1.705
6303 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950051 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Schoenherr Road in Macomb County. | Pavement Improvement | 2009-10-06 | 2009-10-14 | 2009-11-01 | 2009-11-05 | 282091.8 | 1.002
6304 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950058 | 2 mile application of a preventive maintenace treatment to improve safety, smoothness, and extend the service life of the existing pavement on Washington Street in New Baltimore by MDOT. | Pavement Improvement | 2009-12-23 | 2010-05-12 | 2010-05-28 | 2010-05-28 | 267913.12 | 2.094
6305 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950059 | 2 miles of resurfacing to maintain the pavement condition and improve ride quality of 14 Mile Road in Sterling Heights. | Pavement Improvement | 2010-02-02 | 2010-04-21 | 2010-07-31 | 2010-07-26 | 1402973.96 | 0.940
6306 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950060 | Resurfacing to maintain the pavement condition and improve ride quality of 14 Mile Road in Clinton. | Pavement Improvement | 2010-02-02 | 2010-04-21 | 2010-07-31 | 2010-07-26 | 1116941.32 | 1.370
6307 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MANISTEE |  | 02 | 0951308 | The Mainistee County Road Commission will resurface 4 miles of Stronach Rd from M-55 to Eastlake Rd in the vicinity of the Village of Eastlake in the Manistee National Forest. This will improve the d | Pavement Improvement | 2009-09-17 | 2009-09-26 | 2009-11-01 | 2010-10-08 | 362028 | 3.564
6308 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MANISTEE |  | 02 | 0951309 | The Mainistee County Road Commission will resurface 1 miles of Stronach Rd from US-31 to Grant south of the the City of Manistee. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-17 | 2009-09-26 | 2009-11-01 | 2010-10-08 | 56829.78 | 0.927
6309 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952006 | This pavement project on US-41 in the City of Marquette will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 |  | 2009-06-10 | 512700.28 | 2.056
6310 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952007 | This pavement resurfacing and rumble strip project on US-41 in the City of Marquette will improve safety and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-10-18 | 2009-06-03 | 475729.45 | 1.930
6311 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952009 | This roundabout project in Marquette County at the intersection of US-41/M-28 and Front Street will improve safety. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2011-10-21 | 2010-08-20 | 3433920.95 | 4.224
6312 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952014 | This paving project on County Road 557 in Marquette County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-09-28 | 2010-06-21 | 2010-08-01 | 2010-07-31 | 641383.21 | 2.207
6313 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952016 | This pavement project on Champion Street in the City of Marquette will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-28 | 2009-09-08 | 2010-08-15 | 2010-07-03 | 465000 | 0.360
6314 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952020 | This pavement project on M-94 in Marquette County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-04 | 2009-08-04 |  | 2011-07-28 | 730059.32 | 9.499
6315 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952025 | This pavement project on M-28 BR in the City of Ishpeming will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-11 | 2009-05-11 |  | 2010-06-30 | 406520.44 | 3.901
6316 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MASON |  | 02 | 0953021 | MDOT will resurface 0.5 miles of US-10 at Dowland St in the vicinity of the Lake Michigan Car Ferry in Ludington. This will improve the driving quality by making the road smoother and provide better | Pavement Improvement | 2009-06-04 | 2009-06-04 | 2011-05-05 | 2009-11-06 | 349651.65 | 0.470
6317 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MASON |  | 02 | 0953024 | The City of Ludington will design improvements to 0.2 miles of South Williams St from Ludington Ave to Filer St in Ludington so as to improve the driving quality by making the road smoother. | Other | 2009-08-18 | 2009-08-25 | 2010-06-25 | 2010-01-25 | 13248
6318 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954007 | The MDOT will resurface 2 miles of US-131BR/M-20 from US-131 east to Northland Drive near the City of Big Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-03-30 | 2009-09-25 | 440527.94 | 3.630
6319 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954008 | The MDOT will resurface 2 miles of US-131BR/M-20 from US-131 east to Northland Drive near the City of Big Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-03-30 | 2009-08-05 | 810015.65 | 4.356
6320 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954009 | The MDOT will make repairs to the bridge at Old State Road over US-131 near the Village of Stanwood to make the bridge last longer. | Bridge Improvement | 2009-05-21 | 2009-05-21 | 2010-12-31 |  | 597081.11 | 0.000
6321 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954010 | The Mecosta County Road Commission will resurface 20 Mile Road from 60th Ave to 50th Ave west of the Village of Barryton. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-24 | 2009-10-01 | 2009-11-14 | 2009-11-14 | 87420.72 | 1.008
6322 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954011 | Improvements will be made to guard rail on Arthur Road from 10th Avenue to Costabella Road west of the Village of Lake Isabella to improve safety. | Pavement Improvement | 2009-06-24 | 2009-10-01 | 2009-11-14 | 2009-11-14 | 121716.85 | 1.002
6323 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954012 | The Mecosta County Road Commission will resurface Pierce Road from front St to 110th Ave in the village of Stanwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-24 | 2009-10-01 | 2009-11-14 | 2009-11-14 | 233284 | 7.333
6324 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 0956007 | Within the cities of Midland, Auburn and Bay, MDOT will be upgrading 16 bridge decks on US-10 from Sturgeon Road easterly to I-75 and on M-20/US-10BR from Saginaw Road easterly to Waldo Road to make t | Bridge Improvement | 2009-05-29 | 2009-05-29 | 2011-04-11 |  | 277823.6 | 0.000
6325 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 0956009 | The city of Midland will resurface 2.8 miles on Gordonville Road to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-24 | 2009-07-24 | 2009-10-30 | 2010-09-15 | 548649.37 | 9.392
6326 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 0956010 | In the city of Midland there is 17.20 miles of resurfacing on Smith Crossing Road, Freeland Road, Pine River Road, Nine Mile Road, Shepherd Road, Gordonville Road, Jefferson Road, Prairie Road, Eastma | Pavement Improvement | 2009-07-30 | 2009-07-30 | 2009-10-30 | 2010-09-15 | 441633 | 8.757
6327 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 0956011 | The city of Midland will resurface 4.16 miles on M-20 from west of Meridian Road easterly to east of Vance Road to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-29 | 2009-09-29 | 2012-02-01 | 2010-08-05 | 1837630.28 | 4.015
6328 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MISSAUKEE |  | 04 | 0957004 | The Missaukee Couth Road Commission willl resurface 5.5 miles of Falmouth/Hildebrand/Cadilac/Lucas Rds between M-66 and Dikerson Rd in the vicinity of Cadilac. This will improve the driving quality b | Pavement Improvement | 2009-10-12 | 2009-10-19 | 2010-06-12 | 2009-10-27 | 277431.16 | 5.530
6329 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 0958011 | 0.39 miles of pavement resurfacing on West 7th Street from Telegraph Road to Union Street in the city of Monroe, Monroe County. This project will improve pavement rideability and increase pavement sm | Pavement Improvement | 2009-09-17 | 2009-10-05 | 2009-11-01 | 2009-11-01 | 154753.89 | 0.780
6330 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 0958012 | 0.17 miles of pavement resurfacing on Riverview Avenue from Scottwood Street to Maywood Street in the city of Monroe, Monroe County. This project will improve pavement rideability and increase paveme | Pavement Improvement | 2009-09-15 | 2009-09-28 | 2009-11-15 | 2009-11-03 | 184262.69 | 0.173
6331 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959004 | The MDOT will resurface seven and a half miles of M-91 from north of Colby Rd to north of Kedalville Rd near the village of Lakeview. This will improve the driving quality by making the road smoothe | Pavement Improvement | 2009-06-22 | 2009-04-02 | 2009-11-14 | 2009-08-04 | 406541.43 | 7.455
6332 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959008 | The Moncalm County Road Commission will resurface South Youngman Rd from M-57 to Harlow Rd east of Greenville. This will improve the driving quality by making the road smoother. | Pavement Widening | 2009-08-12 | 2009-08-13 | 2009-09-18 | 2009-11-02 | 85143.78 | 0.757
6333 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959009 | The MDOT will resurface seven miles of M-57 from Berridge Rd to east of M-66 near the City of Greenville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-26 | 2009-07-01 | 2010-03-30 | 2009-07-31 | 874005.49 | 7.053
6334 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959010 | The MDOT will resurface six miles of M-46 from US-131 to west of Amble Rd near the village of Lakeview. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-04 | 2009-06-04 | 2010-03-30 | 2009-09-02 | 746003.4 | 5.945
6335 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959011 | The Montcalm County Road Commission will resurface South Vickeryville Rd from Stanton Rd to Sidney Rd. near the village of Stanton. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-17 | 2009-09-22 | 2009-10-30 | 2009-10-27 | 440419.07 | 2.689
6336 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON |  | 02 | 0961134 | The MDOT will make repairs to the bridge at Fruitport Rd over I-96 and the bridge at Russell Rd over US-31in Muskegon County to make the bridges last longer. | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2011-09-21 | 2010-08-30 | 1414742.12 | 0.000
6337 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON |  | 02 | 0961135 | The MDOT will build a roundabout at M-37 and M-46 intersection and resurface M-37 from M-46 to Moon Rd for 2 miles west of the village of Casanovia to improve safety and road smoothness. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2012-12-31 |  | 3396704.86 | 3.977
6338 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961138 | The City of Muskegon will resurface a half mile of Laketon Ave from Peck St to Wood St. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-27 | 2009-08-18 | 2009-11-15 | 2009-11-21 | 800000 | 0.504
6339 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961139 | The City of Whitehall will resurface 3 tenths of a mile of Mears Ave from Lincoln Rd to Misco Drive. This will improve driving quality by making the road smoother. Needed utility work will also be d | Pavement Improvement | 2009-09-03 | 2009-09-08 | 2009-10-16 | 2009-11-06 | 200000 | 0.285
6340 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961140 | The City of Montague will resurface a block of Old Channel Trail from Dowling St to Church St. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-09-02 | 2009-09-30 | 2009-09-26 | 35539.31 | 0.073
6341 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961141 | The City of Montegue will resurface a one tenth of a mile of Dowling St from Meade St to Ferry St. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-09-02 | 2010-12-31 | 2009-09-26 | 50000 | 0.111
6342 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961142 | The City of Muskegon will resurface 0.4 mile of Summit Ave from west of Henry St to Coolidge Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-31 | 2009-09-08 | 2010-12-31 | 2009-09-30 | 178180.35 | 0.355
6343 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961143 | The City of Norton Shores will resurface 0.8 miles of Pontaluna Rd Grand Haven Rd to Wood Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-25 | 2009-09-08 | 2010-12-31 | 2010-11-13 | 503211 | 0.769
6344 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961150 | The City of North Muskegon will resurface 0.6 miles of Ruddiman Drive from Center St to Whitehall Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 2010-02-16 | 2010-04-27 | 2010-05-28 | 2010-06-11 | 200000 | 0.599
6345 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963182 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Crooks Road in Oakland County. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-11-15 | 2010-11-23 | 802000 | 1.145
6346 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963183 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Campbell Road in Madison Heights and Royal Oak. | Pavement Improvement | 2009-05-14 | 2009-07-27 | 2012-09-01 |  | 1153712.67 | 0.990
6347 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963184 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Orchard Lake Road in Oakland County. | Pavement Improvement | 2009-07-31 | 2009-08-18 | 2009-10-23 | 2009-11-24 | 415000 | 1.012
6348 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND |  | 09 | 0963185 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Square Lake Road in Bloomfield Township by MDOT. | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2012-12-31 | 2010-05-10 | 5706880.5 | 2.563
6349 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963196 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of 10 Mile Road in Oakland County. | Pavement Improvement | 2009-08-10 | 2009-08-13 | 2009-10-09 | 2009-10-27 | 512000 | 0.536
6350 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963197 | Resurfacing to maintain the pavement condition and improve ride quality of Rochester Road in Clawson. | Pavement Improvement | 2009-07-31 | 2009-08-17 | 2009-10-02 | 2009-10-16 | 350000 | 0.510
6351 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963199 | 5.6 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along M-59 in Rochester Hills by MDOT. | Pavement Widening | 2009-06-02 | 2009-06-02 | 2013-01-19 |  | 56150066.45 | 11.892
6352 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963208 | 2 miles of resurfacing to maintain the pavement condition and improve ride quality of M-59 in Pontiac. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-06-30 |  | 11372044.48 | 6.259
6353 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963209 | Resurfacing to maintain the pavement condition and improve ride quality of East Progress Drive in Madison Heights by MDOT. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2010-12-15 | 2010-11-13 | 405273.61 | 0.832
6354 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963211 | Two miles of resurfacing to maintain the pavement condition and improve ride quality of Orchard Lake Road in Oakland County. | Pavement Improvement | 2009-09-03 | 2009-09-08 | 2010-06-15 | 2010-06-15 | 1749000 | 2.095
6355 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963212 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Crooks Road in Oakland County. | Pavement Improvement | 2009-08-28 | 2009-09-10 | 2015-12-31 | 2010-06-22 | 879000 | 1.235
6356 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963215 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Novi Road in Novi. | Pavement Improvement | 2009-09-10 | 2009-09-16 | 2009-11-02 | 2009-11-17 | 827000 | 1.004
6357 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963220 | 2 miles of concrete pavement repairs to maintain the pavement condition and improve ride quality of Halsted Road in Farmington Hills. | Pavement Improvement | 2009-07-22 | 2009-07-22 | 2010-09-25 | 2010-10-12 | 1155577.61 | 1.622
6358 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963224 | Resurfacing to maintain the pavement condition and improve ride quality of Nine Mile Road in Novi. | Pavement Improvement | 2009-09-24 | 2009-10-03 | 2010-06-15 | 2010-07-17 | 328000 | 1.026
6359 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963225 | Three miles of resurfacing to maintain the pavement condition and improve ride quality of Meadowbrook Road in Novi. | Pavement Improvement | 2009-09-24 | 2009-10-03 | 2010-06-15 | 2010-07-17 | 340000 | 1.000
6360 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963226 | Resurfacing to maintain the pavement condition and improve ride quality of Nine Mile Road in Novi. | Pavement Improvement | 2009-09-24 | 2009-10-03 | 2010-06-15 | 2010-07-17 | 340000 | 1.038
6361 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963239 | Bridge replacement to improve safety and maintain mobility of Opdyke Road over M-59 in Pontiac by MDOT. | Bridge Improvement | 2009-08-18 | 2009-08-18 | 2013-01-19 | 2010-07-30 | 2774492.05 | 0.000
6362 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963240 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Cass Avenue in Pontiac by MDOT. | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-05-05 | 2010-09-01 | 1832013.03 | 1.183
6363 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963264 | One mile of resurfacing to maintain the pavement condition and improve ride quality of John R Road in Troy. | Pavement Improvement | 2010-02-04 | 2010-04-01 | 2010-07-02 | 2010-07-08 | 837000 | 1.028
6364 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OCEANA |  | 02 | 0964332 | The MDOT will make repairs to the bridge at Taylor Rd over US-131 in Oceana County to make the bridge last longer. | Bridge Improvement | 2009-05-29 | 2009-05-29 | 2011-03-31 | 2010-05-17 | 676421.28 | 0.000
6365 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OCEANA |  | 02 | 0964340 | The Oceana County Rd Commission will resurface 3 miles of West Shelby Rd from 52nd Ave to 40th Ave west of the Village of Shelby. This will improve the driving quality of the raodway | Other | 2010-02-26 | 2010-05-03 | 2010-05-28 | 2010-06-03 | 446345 | 3.026
6366 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 0965009 | MDOT will repair 10.6 miles of I-75 from the south Ogemaw County line to Cook Rd and from Ski Park Rd to the north county linein Ogemaw County to extend the service life of the existing roadway. | Pavement Improvement | 2008-12-30 | 2008-12-30 | 2009-06-18 | 2009-06-18 | 897731.5 | 11.057
6367 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 0965010 | MDOT will design repairs to drainage culverts along I-75 in Ogemaw County to improve drainage and extend the life of the roadway drainage structures. | Other | 2009-04-23 | 2009-04-23 |  |  | 9046.69
6368 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 0965011 | MDOT will fix drainage culverts along I-75 in Ogemaw County to improve drainage and extend the life of the roadway drainage structures. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-06-01 | 2010-06-01 | 1104499.82 | 10.034
6369 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ONTONAGON |  | 01 | 0966008 | This paving project on M-64 from Silver City to The City of Ontonagon will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-10-18 | 2009-10-02 | 2576015.29 | 11.840
6370 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 0967010 | MDOT will design the resurfacing of 2 miles of US-10 from the west county line of Osceola to the US-131 interchange in the vicinity of Reed City. This will improve the driving quality by making the | Other | 2009-04-29 | 2009-04-29 |  |  | 46696.66
6371 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 0967011 | MDOT will resurface 2 miles of US-10 from the west county line of Osceola to the US-131 interchange in the vicinity of Reed City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2011-03-03 | 2010-10-15 | 1257647.3 | 1.890
6372 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 0967015 | The Osceola County Road Commission will resurface 4 and a quarter miles of 200th Ave from 20 Mile Rd to the county line in the vicinity of the village of Tustin. This will improve the driving quality | Other | 2009-07-29 | 2009-10-27 | 2010-10-30 | 2011-03-24 | 146233 | 4.263
6373 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 0968003 | The Oscoda County Road Commission will replace the bridge on Waterwheel Court over Big Creek to improve safety and increase mobility. | Bridge Replacement | 2009-09-23 | 2010-03-17 | 2010-07-30 | 2010-08-03 | 87616.5 | 0.309
6374 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTSEGO |  | 01 | 0969014 | MDOT will resurface 5 miles of M-32 from east of Krys Rd to Turtle Lake Rd east of Gaylord. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2009-10-08 | 2009-10-08 | 385285.55 | 9.855
6375 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTSEGO |  | 01 | 0969016 | The Otsego County Road Commission will reconstruct 1.5 miles of Charles Brink Rd from E of Championship Dr to Opal Lake Rd in the vicinity of Otsego Lake. This will improve the driving quality by mak | Other | 2009-09-18 | 2009-09-21 | 2009-11-13 | 2009-11-13 | 331098 | 1.565
6376 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | HOLLAND | 02 | 0970019 | Almost 2 miles of Lakewood Blvd from River Ave to 120th Ave will be resurfaced in Holland Township. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-25 | 2009-07-01 | 2009-07-31 | 2009-07-29 | 580277.36 | 1.704
6377 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970020 | Five miles of 48th Ave will be resurfaced near the City of Hudsonville and in Georgetown Township from Chicago Drive to Bauer Rd. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-26 | 2009-07-01 | 2009-08-14 | 2009-08-26 | 1144923.47 | 4.672
6378 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 0970022 | The City of Holland will resurface almost 2 miles of Lakewood Blvd from River Ave to 120th Ave. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-26 | 2009-07-01 | 2009-08-14 | 2009-07-30 | 439912.71 | 1.965
6379 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 0970024 | The MDOT will make repairs to the I-196 bridges over 48th St near the City of Grandville to make the bridges last longer. | Bridge Improvement | 2009-04-28 | 2009-04-28 | 2010-12-31 | 2010-08-26 | 622318.66 | 0.000
6380 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 0970026 | The MDOT will resurface 6 miles of I-96 from M-104 to 68th Ave in the vicinity of Spring Lake. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2011-04-01 | 2009-09-01 | 1558066.92 | 11.106
6381 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0970034 | The Ottawa County Road Commission will resurface 2 miles of Lake michigann Dr from Lakeshore Ave to US-31. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-23 | 2009-07-30 | 2009-09-11 | 2009-08-13 | 342132.32 | 1.960
6382 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970037 | The MDOT will resurface 1 mile of I-196 BL from US-31 east to the Macatawa River near the City of Holland. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-09 | 2009-06-09 | 2010-03-30 | 2009-11-30 | 358122.14 | 1.355
6383 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970038 | The MDOT will resurface 9 miles of I-196 from 64th Ave to Kenowa Ave near Hudsonville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-10 | 2009-06-10 | 2011-09-21 | 2010-06-08 | 2406902.54 | 13.499
6384 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970039 | The MDOT will resurface 11 miles of M-45 from US-31 east to 68th Ave near the city of Grand Haven. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-10 | 2009-06-10 | 2010-03-30 | 2009-10-02 | 1428909.36 | 11.095
6385 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0970040 | The City of Grand Haven will resurface three quarters of a mile of Robbins Rd from just east of US-31 to Beechtree St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-22 | 2009-09-25 | 2010-12-31 | 2010-06-29 | 230691 | 0.721
6386 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0970041 | The City of Spring Lake will resurface 0. 2 miles of West Springlake Rd from Smith's Bridge to Bayberry Dr. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-09-08 | 2009-10-31 | 2009-11-30 | 200000 | 0.220
6387 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 0970044 | The MDOT will resurface a half mile of US-31 south bound from the Grand River bascule bridge to 3rd St including M-104 in the city of Ferrysburg. This will improve the driving quality by making the r | Pavement Improvement | 2009-07-10 | 2009-07-10 | 2010-06-30 | 2009-10-05 | 264725.75 | 0.905
6388 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0970051 | The City of Spring Lake will resurface 0. 2 miles of Jackson St at Exchange St and at West Savidge (M-104). This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-19 | 2010-04-05 | 2010-06-25 | 2010-06-15 | 183407.05 | 0.162
6389 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970053 | The MDOT will make repairs to the I-96 bridge over west bound M-11 near the City of Grand Rapids to make the bridge last longer. | Bridge Improvement | 2010-02-16 | 2010-03-02 | 2011-03-31 | 2010-07-01 | 239412.06 | 0.000
6390 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ROSCOMMON |  | 04 | 0972006 | The MDOT is upgrading the guard rail along 17.5 miles of US-127 in Roscommon County from Snow Bowl Rd north to I-75 to improve safety. | Safety/Traffic Management | 2009-04-02 | 2009-04-02 | 2009-07-10 | 2009-07-10 | 232098.65 | 30.285
6391 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973027 | In the city of Saginaw, MDOT is making repairs on M-46 to make the bridge last longer. | Bridge Improvement | 2009-05-11 | 2009-05-11 | 2011-02-20 | 2010-11-15 | 996127.45 | 0.000
6392 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973028 | Within the city of Saginaw, MDOT will reconstruct 1.20 miles of M-13 to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-29 | 2009-05-29 | 2012-09-19 |  | 5789128.68 | 1.258
6393 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973030 | The City of Saginaw is resurfacing 1.48 miles on Outer Drive to improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-14 | 2009-08-17 | 2009-11-13 | 2009-11-23 | 1844073 | 1.484
6394 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973033 | The City of Chesaning is resurfacing 7 miles on S Hemlock Road to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 80000 | 10.750
6395 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973034 | The Saginaw County Road Commission is resurfacing 5.105 miles on Ditch Road south of Chesaning to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 80716.1 | 5.105
6396 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973035 | The City of Frankenmuth is resurfacing 5.03 miles on S Dehmel Road to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 80000 | 4.949
6397 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973036 | The City of Bridgeport is resurfacing 5.37 miles on Busch Rd & Moorish Rd to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 85000 | 5.348
6398 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973037 | The Saginaw County Road Commission is resurfacing 3.9 miles on Fergus Road from Sharon Rd to Bishop Rd near the Village of St. Charles to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-05-01 |  | 67368.88 | 3.943
6399 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973038 | In Tittabawassee Township there is 5 miles of resurfacing on Mackinaw Rd & Lawndale Rd to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 80000 | 4.996
6400 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973041 | In the city of Saginaw there will be 0.98 miles reconstruction on East Genesee Avenue from Franklin Street to Janes Street to improve the driving quality and make the road smoother. | Pavement Improvement | 2009-12-22 | 2010-03-08 | 2012-09-18 |  | 934074 | 0.427
6401 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973042 | The city of Saginaw will beautify 0.45 miles along W Genesee Avenue. | Transportation Enhancements | 2009-12-22 | 2010-03-08 | 2012-09-18 |  | 510000 | 0.427
6402 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973051 | The city of Saginaw will reconstruct 0.51 miles on North Woodbridge Street from Houghton Avenue to Davenport Avenue to improve the driving quality by making the road smoother. | Other | 2010-02-01 | 2010-04-26 | 2010-10-23 |  | 400000 | 0.555
6403 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973053 | There is 15.39 miles of resurfacing on M-46 from Towerline Road easterly to west of M-15 and on M-84 from M-58 (State Street) northerly to north of Pierce Road to improve the driving quality by making | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2012-03-01 | 2010-10-08 | 3374881.08 | 15.434
6404 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | SANILAC |  | 10 | 0974004 | North of Port Sanilac, MDOT is upgrading 6.8 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-05-29 | 2009-05-29 | 2010-03-31 | 2009-09-19 | 402983.46 | 6.824
6405 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 0975013 | This shoulder paving project on County Road 498 in Schoolcraft County will improve safety. | Pavement Improvement | 2009-05-11 | 2009-07-27 | 2010-03-01 |  | 91271 | 3.958
6406 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 0975014 | This shoulder paving project on Thunder Lake Road in Schoolcraft County will improve safety. | Pavement Improvement | 2009-05-11 | 2009-08-17 | 2010-03-01 |  | 91680 | 10.314
6407 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 0975016 | This shoulder paving project on County Road 436 in Schoolcraft County will improve safety. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2010-09-30 | 2010-08-31 | 93904 | 2.998
6408 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 0976208 | Near the city of Perry in Shiawausee county, MDOT will improve the driving surface of nearly 8 miles of I-96 with a resurfacing project. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2011-06-16 |  | 3682328.68 | 15.748
6409 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 0976211 | 0.2 of a mile of pavement resurfacing of East King Street from North Dewey Street to North Gould Street, in the city of Owosso, Shiawausee County. This project will improve pavement rideability and i | Pavement Improvement | 2009-08-28 | 2009-10-02 | 2009-11-01 | 2009-11-05 | 100000 | 0.250
6410 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 0976212 | 0.14 miles of pavement resurfacing of North Park Street from M-21 to Mason Street, in the city of Owosso, Shiawausee County. This project will improve pavement rideability and increase pavement smoot | Pavement Improvement | 2009-08-28 | 2009-10-02 | 2009-11-01 | 2009-11-05 | 100000 | 0.135
6411 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 0976213 | 0.24 miles of pavement resurfacing on Maple Street from M-71 to Main Street near the City of Durand, Shiawausee County. Improvements will enhance pavement rideability and increase pavement smoothness | Pavement Improvement | 2009-09-25 | 2009-09-28 | 2009-11-30 | 2009-10-28 | 52000 | 0.244
6412 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 0977015 | The Michigan Department of Transportation will realign and make improvements to numerous local streets that cross under the Blue Water Bridge in Port Huron. The project will improve local traffic move | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2011-10-01 |  | 850834.81 | 0.618
6413 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 0977029 | 0.3 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along Collard Drive in Marysville. | Pavement Improvement | 2010-01-06 | 2010-06-15 | 2011-05-30 | 2010-10-07 | 409478.11 | 0.288
6414 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR |  | 10 | 0977031 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Dryden Road in St. Clair County. | Pavement Improvement | 2009-09-03 | 2009-10-21 | 2009-10-30 | 2009-11-13 | 213948 | 1.031
6415 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 0977035 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of Riverside Drive in Port Huron. | Pavement Improvement | 2009-08-25 | 2009-09-03 | 2009-10-30 | 2009-10-19 | 279566.02 | 0.573
6416 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 0977040 | 10 miles of resurfacing to maintain the pavement condition and improve ride quality of M-25 in St. Clair by MDOT. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2011-04-11 | 2010-10-15 | 6196432.86 | 10.708
6417 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR |  | 10 | 0977042 | Bridge replacement to improve safety and maintain mobility of I-94 over the Belle River in St. Clair County by MDOT. | Bridge Replacement | 2009-12-02 | 2009-12-02 | 2012-10-08 |  | 6401261.78 | 0.000
6418 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR |  | 10 | 0977044 | 3.6 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty on I-94 in St. Clair County. | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2013-01-19 |  | 19217011.84 | 4.479
6419 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 0979010 | MDOT is upgrading 6.0 miles to create a paved pathway on M-15 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-06-02 | 2009-06-02 | 2010-03-31 | 2009-09-19 | 417499.15 | 6.047
6420 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 0979014 | In the village of Mayville, Tuscola County there will be 0.20 miles of roadway reconstruction on Industrial Park Road at M-24 to improve the driving quality and make the road smoother. | Pavement Improvement | 2009-09-28 | 2009-10-05 | 2010-06-01 | 2010-11-17 | 49790.9 | 0.120
6421 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 0980009 | "The City of Hartford will resurface 0.5 miles of W. Main Street from the city limits to Center Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-20 | 2009-09-21 | 2011-07-27 | 2009-10-21 | 178400.27 | 0.501
6422 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 0980013 | "The village of Decatur will resurface 0.4 miles of N. Phelps Street (CR 653) from the village limits to Cedar Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-28 | 2009-09-16 | 2011-07-27 | 2010-05-25 | 295294.75 | 0.417
6423 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 0980020 | "The village of Paw Paw will resurface 0.9 miles of East Michigan Avenue from the E. village limits to Kalamazoo Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-10-02 | 2009-10-09 | 2011-07-27 |  | 135000 | 0.933
6424 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW |  | 07 | 0981027 | 5.50 miles of pavement resurfacing on I-94 from the Freer Road easterly to Parker Road, west of Ann Arbor in Washtenaw County. This project includes ramp reconstruction, drainage improvements and fre | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2012-12-31 | 2011-09-19 | 14711194.72 | 11.000
6425 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW |  | 07 | 0981028 | 6.62 miles of pavement resurfacing on I-94 from the west Washtenaw County line easterly to Freer Road. This project includes ramp reconstruction, drainage improvements and freeway shoulder widening. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2012-12-31 | 2011-09-19 | 3476957.68 | 13.240
6426 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981031 | 0.35 miles of pavement resurfacing and drainage improvements on North Ann Arbor Street from US-12 to Bennett Street in the City of Saline, Washtenaw County. | Pavement Improvement | 2009-08-04 | 2009-08-31 | 2009-10-02 |  | 202053.33 | 0.350
6427 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981035 | Throughout Washtenaw County the cracks in the pavement will be sealed to extend the life of the pavement. | Pavement Improvement | 2009-07-29 | 2009-09-01 | 2010-09-01 |  | 27220 | 7.795
6428 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981036 | 6.56 miles of roadway will be resurfaced in Washtenaw county, north of the City of Ann Arbor at multiple locations. North Territorial Road from Webster Church to Whitmore Lake, North Territorial Road | Pavement Improvement | 2009-07-29 | 2009-07-29 | 2010-09-01 | 2010-09-01 | 616691.99 | 6.146
6429 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981037 | 5.44 miles of pavement repair in the city of Ann Arbor area. This project will provide for improved rideability and increased pavement smoothness on Jackson Road from Honey Creek Drive to Wagner Road | Pavement Improvement | 2009-07-29 | 2010-06-01 | 2010-08-01 | 2010-08-01 | 88259.15 | 5.435
6430 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981038 | 11 miles of pavement resurfacing at various locations thourghout Washtenaw County to improve pavement rideability and pavement smoothness. Locations include Ann Arbor Road from Zeeb Road to West Ann | Pavement Improvement | 2009-07-29 | 2010-01-13 | 2010-09-01 | 2010-12-23 | 1007882.17 | 13.065
6431 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981039 | 2.36 miles of Loer Road from Textile Road to W Ellsworth Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, south of the City of Ann Arb | Pavement Improvement | 2009-07-29 | 2009-09-01 | 2010-09-01 |  | 43026 | 2.364
6432 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981040 | 2.43 miles of pavement resurfacing on Huron River Drive along the scenic Huron River between the Village of Dexter and the City of Ann Arbor in Washtenaw County. Improvements will provide for increas | Pavement Improvement | 2009-07-29 | 2009-07-20 | 2010-09-01 | 2010-12-23 | 250000 | 2.426
6433 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981042 | 2.0 miles of Baker Road from I-94 to Dan Hoey Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, West of the City of Ann Arbor in Washte | Pavement Improvement | 2009-08-04 | 2009-09-01 | 2010-09-01 | 2010-09-01 | 49700 | 2.055
6434 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981043 | 1.78 miles of Ann Arbor-Saline Road from Oak Valley Drive to Maple Road and Maple Road from Ann Arbor-Saline Road to Saline City limits will have a Chip and Seal treatment to preserve pavement life an | Pavement Improvement | 2009-08-04 | 2009-09-01 | 2010-09-01 | 2010-09-01 | 82098 | 1.778
6435 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981044 | 2.0 miles of Dexter Ann Arbor Road from Dan Hoey Road to Zeeb Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, West of the City of Ann | Pavement Improvement | 2009-08-04 | 2009-09-01 | 2010-09-01 | 2010-09-01 | 48387 | 2.112
6436 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981050 | 2.23 miles of Miller Road from Dexter Ann Arbor Road to Wagner Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, west of the City of An | Pavement Improvement | 2009-08-13 | 2009-09-01 | 2010-09-01 | 2010-09-01 | 45554.16 | 2.229
6437 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981061 | This project will provide for traffic signal upgrades on Packard Road from the East Eisenhower Parkway to East Stadium Blvd. This work will improve traffic safety, ease congestion and increase traffi | Safety/Traffic Management | 2009-09-21 | 2010-03-15 | 2010-09-19 | 2010-08-27 | 185242.62 | 1.309
6438 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982054 | MDOT will repair and resurface . 9 miles of US-24 in Redford Township in Wayne County to improve driving quality and increase service life | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2011-12-31 | 2009-09-17 | 1008279.66 | 0.921
6439 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982055 | MDOT will resurface .8 miles of US-24 in the City of Flat Rock to improve the driving quality and extend the service life of the road | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-01 | 2009-09-24 | 360996.73 | 0.816
6440 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982057 | MDOT will landscape and replace fence on . 6 miles of I-75 in the City of Hamtamck Wayne County which will beautify the drive and make it safer. | Transportation Enhancements | 2009-05-14 | 2009-05-14 | 2011-09-19 |  | 746902.79 | 1.553
6441 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982058 | MDOT will rehabilitate 7 bridges in the City of Detroit on I-96 to make the bridges last longer | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2012-12-31 |  | 11857012.74 | 0.000
6442 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982059 | MDOT will repair the I-96 under Underwood Avenue bridge in the City of Detroit to make the bridge last longer | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2010-12-17 |  | 1179301.38 | 0.000
6443 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982060 | MDOT will rehabilitate 3 bridges in the City of Detroit on I-96 to make the bridges last longer | Bridge Improvement | 2009-05-19 | 2009-05-19 | 2010-12-31 |  | 3657578.71 | 0.000
6444 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982061 | The City of Westland will reconstruct the Newburgh and Warren intersection in the City of Westland to improve the driving quality and safety | Pavement Improvement | 2009-05-19 | 2009-05-19 | 2010-07-31 | 2010-07-12 | 681745.36 | 0.005
6445 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982064 | MDOT is removing 2 railroad bridges over I-96 in the City of Detroit because they are no longer used | Bridge Improvement | 2009-05-21 | 2009-05-21 | 2010-12-31 |  | 942473.11 | 0.000
6446 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982066 | 1 mile of Warren Road in the City of Dearborn Heights will be resurfaced by Wayne County to improve the driving quality and increase the road service life | Pavement Improvement | 2009-05-21 | 2009-05-21 | 2011-01-15 | 2009-11-24 | 883108.26 | 0.994
6447 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982067 | MDOT will construct a sound will at I-96 and US-24 to reduce road sounds to adjacent properties | Other | 2009-05-29 | 2009-05-29 | 2012-09-20 |  | 4568501.39 | 1.615
6448 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982076 | The City of Grosse Point will resurface .4 miles of St Clair Road to improve driving quality and increase road service life | Pavement Improvement | 2009-07-31 | 2009-08-22 | 2009-10-30 | 2009-11-09 | 324883.76 | 0.388
6449 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | ANN ARBOR | 13 | 0982082 | MDOT will repair and resurface the ramps on I-94 at Belleville road in Van Buren Township Wayne County to improve the driving quality and increase service life | Pavement Improvement | 2009-06-04 | 2009-06-04 | 2010-12-31 | 2009-11-01 | 640238.13 | 0.944
6450 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | STATEWIDE | 13 | 0982083 | MDOT will repair and resurface the ramps on I-94 at Haggerty Road in Van Buren Township Wayne County to improve the driving quality and increase service life | Pavement Improvement | 2009-06-04 | 2009-06-04 | 2010-12-31 | 2009-11-01 | 589436.5 | 0.839
6451 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE |  | 13 | 0982098 | MDOT will repair and resurface 6.3 miles of non motorized path along I-275 in Wayne County for cyclists, walkers and joggers to promote alternate modes of transportation | Transportation Enhancements | 2009-04-01 | 2009-04-01 | 2013-01-19 |  | 4655955.12 | 12.530
6452 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982100 | The City of Grosse Point Shores will resurface .4 miles of Vernier Road to improve driving quality and increase service life | Pavement Improvement | 2009-07-07 | 2009-10-14 | 2010-10-30 | 2010-09-15 | 263330.54 | 0.364
6453 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982108 | MDOT will replace pumping equipment on I-94 in the City of Dearborn Wayne County to insure rainwater will not interfere with traffic | Pavement Improvement | 2009-07-21 | 2009-07-21 | 2010-12-31 | 2011-07-12 | 1039988.17 | 0.324
6454 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982113 | MDOT will rehabilitate the M-8 under Joseph Campau bridge to make the bridge last longer | Bridge Improvement | 2009-09-16 | 2009-09-16 | 2011-12-31 |  | 1724905.14 | 0.226
6455 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982114 | MDOT will repair the M-8 under Charest Avenue walkover bridge to make the bridge last longer | Bridge Improvement | 2009-05-11 | 2009-05-11 | 2011-12-31 |  | 194264.47 | 0.048
6456 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982115 | MDOT will rehabilitate the M-8 under Goddard Avenue bridge to make the bridge last longer | Bridge Improvement | 2009-07-24 | 2009-07-24 | 2011-12-31 |  | 1714610.1 | 0.262
6457 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982116 | MDOT will resurface 1.4 miles of M-8 in the City of Detroit to improve driving quality and extend service life of the road | Pavement Improvement | 2009-07-24 | 2009-07-24 | 2013-12-31 |  | 13260674.38 | 2.722
6458 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982117 | MDOT will rehabilitate 5 bridges on M-8 to make the bridges last longer | Bridge Improvement | 2009-09-16 | 2009-09-16 | 2011-12-31 |  | 583657.03 | 0.000
6459 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982121 | Wayne County will resurface .5 Miles of Merriman Road in the Cities of Westland and Livonia to improve driving quality and increase service life | Pavement Improvement | 2009-07-29 | 2009-12-18 | 2010-08-31 | 2010-08-27 | 795644.91 | 0.516
6460 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982122 | The City of Livonia will resurface .5 miles of Lyndon Road to improve driving quality and increase service life | Pavement Improvement | 2009-07-29 | 2010-06-18 | 2010-09-01 | 2010-09-30 | 675000 | 0.502
6461 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982123 | Wayne County will resurface .6 miles of 7 Mile Road to improve driving quality and increase service life | Pavement Improvement | 2009-07-30 | 2009-07-30 | 2010-09-30 | 2010-09-24 | 653456.8 | 0.625
6462 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982124 | MDOT will repair and resurface .4 miles of US-12 in the City of Dearborn to improve the driving quality and increase service life | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2011-12-31 |  | 2449807.27 | 3.025
6463 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982130 | MDOT will install an active speed warning system on the I-94 Ebd ramp to I-96 in the City of Detroit which will improve safety | Safety/Traffic Management | 2009-10-06 | 2009-10-06 | 2012-11-15 |  | 476061.37 | 0.070
6464 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982131 | MDOT will install an active speed warning system on the I-94 Wbd ramp to I-96 in the City of Detroit which will improve safety | Safety/Traffic Management | 2009-10-06 | 2009-10-06 | 2012-11-15 |  | 395535.08 | 0.108
6465 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982136 | MDOT will repair 2 railroad bridges over M-85 in the City of Detroit to make the bridges last longer | Bridge Improvement | 2009-05-11 | 2009-05-11 | 2010-12-17 |  | 819792.14 | 0.000
6466 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982141 | MDOT will repair and resurface 6 miles of M-39 in the cities of Detroit and Dearborn to improve driving quality and increase service life | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2011-12-31 | 2010-05-24 | 3161887.26 | 11.939
6467 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982152 | The City of Detroit is resurfacing portions of Seven Mile, Conner, McNichols, East Vernor, Mt Elliot, Mack and Warren Roads to improve driving quality and increase service life | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2010-11-02 |  | 4562400.24 | 0.360
6468 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982153 | The City of Detroit is resurfacing portions of E. Congress, E. Lafayette, E. Larned, Clark, Chicago and Puritan Roads to improve driving quality and increase service life | Pavement Improvement | 2009-08-20 | 2010-04-15 | 2010-11-02 |  | 2870051.21 | 6.576
6469 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982154 | The City of Detroit is resurfacing portions of Meyers, Burt, Southfield Service Drive, Lodge Service Drive and Livernois Roads to improve driving quality and increase service life | Pavement Improvement | 2009-08-20 | 2010-03-03 | 2010-11-02 |  | 3942896.29 | 7.267
6470 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982170 | Wayne County will resurface 1.5 Miles of Middlebelt Road in the City of Romulus to improve driving quality and increase service life | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-11-30 | 2010-11-28 | 1558682.52 | 1.501
6471 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982173 | Wayne County will will reconstruct and widen to 5 lanes 1.4 miles of Canton Center Road in Canton Township to improve safety and ease congestion | Pavement Widening | 2009-09-16 | 2009-09-16 | 2010-11-19 | 2011-09-21 | 3867492 | 1.000
6472 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WEXFORD |  | 02 | 0983019 | The MDOT is replacing the US-131 bridge over the Manistee River in the City of Manistee to improve safety and increase mobility. | Bridge Replacement | 2009-06-04 | 2009-06-04 | 2010-07-02 | 2010-06-18 | 168088.04 | 0.110
6473 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984075 | The MDOT is undertaking areawide pavement repairs on 14 miles of roadway in Howard City area to improve the pavement condition and extend pavement life. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2009-11-14 | 2009-09-03 | 202569.95 | 19.420
6474 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984076 | The MDOT is undertaking areawide pavement repairs on nearly 18 miles of roadway in the Grand Region area to improve the pavement condition and extend pavement life. | Pavement Improvement | 2009-05-05 | 2009-05-05 | 2010-06-30 | 2009-10-07 | 289336.54 | 23.773
6475 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984084 | The 8 weather towers, called an Environmental Sensor Station are designed to aid motorists and the Michigan Department of Transportation (MDOT), and are expected to be particularly helpful in the wint | Safety/Traffic Management | 2009-05-05 | 2009-05-05 | 2009-10-30 | 2009-10-30 | 1049296.51 | 1.600
6476 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE | DETROIT,MI |  | 0984088 | Throughout the Detroit Metropolitan Freeway System the automated traffic control system will receive upgrades to its equipment. This will lessen freeway congestion and improve safety. | Other | 2009-06-04 | 2009-06-04 | 2015-12-31 |  | 7000000 | 0.000
6477 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0984100 | MDOT will repair 27 miles of M-37, US-131, and US-31 at various locations in Grand Traverse Countyto extend the service life of the existing roadways. | Pavement Improvement | 2009-04-17 | 2009-04-17 |  | 2010-05-28 | 166419.94 | 27.206
6478 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984103 | At numerous Statewide locations along US-23 and M-55 the guardrail will be replaced with upgraded guardrail to improve safety | Safety/Traffic Management | 2009-06-17 | 2009-06-17 | 2010-05-28 | 2010-06-10 | 332305.86 | 29.150
6479 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984107 | The weather tower and message sign project will consist of 12 Environmental Sensor Stations and 10 Dynamic Message Signs in 4 Counties and will improve safety and mobility. | Safety/Traffic Management | 2009-07-07 | 2009-07-07 | 2010-12-31 | 2011-07-13 | 1697447.25 | 7.711
6480 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984108 | The MDOT is installing environmental sensors in the North Region at various locations to monitor environmental conditions in the Region. | Safety/Traffic Management | 2009-07-07 | 2009-07-07 | 2010-12-31 | 2011-07-13 | 1478323.2 | 13.966
6481 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE | DETROIT,MI |  | 0984133 | Establishing a protective security fence around five towers in Oakland, Macomb and St. Clair Counties by MDOT. | Safety/Traffic Management | 2009-08-17 | 2009-08-17 | 2009-11-15 | 2009-12-02 | 45999.75 | 0.001
6482 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 1002010 | This pavement project near Wetmore on road FF 13 at M28 S will smooth the road and improve ride quality | Pavement Improvement | 2010-02-09 | 2010-05-01 | 2010-09-15 | 2010-07-31 | 51386 | 2.626
6483 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 1002012 | This project will improve safety by replacing the guardrail on M-94 Chatham to Munising in Alger County | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2010-08-27 | 2010-08-27 | 400560.13 | 10.200
6484 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN | HOLLAND | 06 | 1003005 | The Allegan County Road Commisssion will resurface one mile of 40th Street from Washington Avenue to Lincoln Avenue, in the city of Holland. This will improve the driving quality by making the road | Pavement Improvement | 2010-03-11 | 2010-03-29 | 2010-09-15 | 2010-10-06 | 797585 | 1.987
6485 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN | HOLLAND | 06 | 1003007 | The Allegan County Road Commisssion will resurface 2.8 miles of 136th Avenue from 58th Street to Blue Star Highway just north of the ciy of Saugatuck in Allegan county. | Pavement Improvement | 2010-03-26 | 2010-05-03 | 2010-07-01 | 2010-06-14 | 476387.5 | 2.785
6486 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 1003008 | This 1.4 mile long pavement project on in Plainwell on Main Street from South City Limits to Norfolk Southern Rail will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-29 | 2010-05-14 | 2011-07-27 | 2010-06-29 | 205000 | 1.252
6487 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALPENA |  | 01 | 1004003 | The Alpena County Road Commission will resurface 1.5 miles of Misery Bay Rd from the Lafarge property to the east city limits of Alpena. This will improve the driving quality by making the road smoot | Pavement Improvement | 2010-02-26 | 2010-03-02 | 2011-06-30 | 2010-06-07 | 290000 | 0.764
6488 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ANTRIM |  | 01 | 1005006 | This 8 mile long pavement project on E Torch Lake/Alden Rd/Comfort South County Line to M8 8will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-22 | 2010-05-19 | 2010-06-30 | 2010-06-21 | 366683 | 8.679
6489 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ARENAC |  | 01 | 1006005 | Arenac County will repave 3 miles of Turner Rd from Herr Rd-Tonkey Rd Arenac County | Pavement Improvement | 2010-05-05 | 2010-06-21 | 2010-07-23 | 2010-09-07 | 234154 | 3.012
6490 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BARAGA |  | 01 | 1007003 | This 1.6 mile long pavement project on Skanee Road in Baraga County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-04-02 | 2010-07-27 | 2010-08-22 | 2010-08-22 | 330310 | 1.525
6491 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BARAGA |  | 01 | 1007004 | MDOT will relocate 1.6 miles of US-41 in rural Baraga County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-24 | 2010-02-24 | 2010-10-22 | 2010-10-08 | 2518599.21 | 1.621
6492 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BARRY |  | 03 | 1008007 | This tenth mile long pavement project in Hastings on South Jefferson Street from Green Street to Grand Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-27 | 2010-07-06 | 2011-07-27 | 2010-09-15 | 107000 | 0.126
6493 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BARRY |  | 03 | 1008009 | This pavement project near Middleville on Finkbeiner Road from Cherry Valley Road to M-37 will make the pavement smoother and improve ride quality. | Pavement Improvement | 2010-02-24 | 2010-07-01 | 2011-07-01 |  | 950833.04 | 1.250
6494 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 1009009 | The City of Essexville will resurface 0.4 mile of Borton Ave from Caroline St to Scheurmann St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-04-29 | 2010-06-14 | 2010-07-30 | 2010-07-30 | 221319 | 0.392
6495 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 1009013 | This 2 mile long pavement project on Wilder Road from I-75 to M-13 and M-13 to Patterson Road in the City of Bay City will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-28 | 2010-06-01 | 2010-08-13 | 2010-11-10 | 450000 | 4.042
6496 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 1009015 | This 2 mile long pavement project in Bay City on Truman Parkway/Woodside Avenue from Saginaw River to Woodside/McEwan will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-28 | 2010-06-01 | 2010-08-13 | 2010-11-10 | 707085 | 0.657
6497 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY |  | 01 | 1009016 | This pavement project near Bay City on S 7 Mile Rd from Hotchkiss Rd to Salzburg Rd will smooth the road and improve ride quality. | Pavement Improvement | 2010-02-17 | 2010-06-03 | 2010-09-17 | 2010-09-10 | 305483.41 | 1.009
6498 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY |  | 01 | 1009017 | This pavement project near Bay City on Hotchkiss Rd from 7 Mile Rd to Carter Rd will smooth the road and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-07-01 | 2010-09-03 | 2010-08-16 | 65887 | 4.871
6499 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 1009020 | About 1 mile of pavement resurfacing of Bay-Arenac Drive from Monitor Road to 2 Mile Road outside of Bay City. This project will improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2010-08-31 | 2010-09-14 | 2011-06-30 | 2010-10-11 | 78681 | 1.442
6500 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BENZIE |  | 02 | 1010003 | About 2 miles of County Road 708 from M22 to Platte River near the City of Honor in Benzie County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 2010-02-10 | 2010-07-14 | 2010-07-30 | 2010-07-30 | 77134.29 | 2.146
6501 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BENZIE |  | 02 | 1010004 | Aboutt 5 miles of River Rd from M22 to Benzonia West Village Limit in Benzie County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 2010-02-10 | 2010-07-14 | 2010-07-30 | 2010-07-30 | 157013.47 | 5.241
6502 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BENZIE |  | 02 | 1010009 | Benzie County will resurface six miles of N Manistee County Line Rd from US31 to Kurick Road | Other | 2010-02-10 | 2010-07-14 | 2010-07-30 | 2010-07-30 | 23634 | 6.214
6503 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 1011003 | "The village of Eau Claire will resurface 0.84 miles of E. Main Street throughout the limits of the village. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-05 | 2010-09-02 | 2010-06-18 |  | 92500 | 0.837
6504 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 1011005 | The Allegan County Road Commisssion will resurface one mile of 40th Street from Washington Avenue to Lincoln Avenue, in the city of Holland. This will improve the driving quality by making the road | Pavement Improvement | 2010-02-26 | 2010-03-29 | 2013-08-07 | 2010-10-08 | 671000 | 0.229
6505 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 1011007 | A quarter mile of Lake St from Fifth Street to Eleventh Street in the city of Niles will be repaved to improve smoothness and ride quality. | Pavement Improvement | 2010-03-04 | 2010-04-26 |  | 2010-09-17 | 64677.93 | 0.289
6506 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 1011008 | The Berrien County Road Commisssion will resurface 0.63 miles of E. Main Street from Maple Street to 17th Street in the city of Niles. This will improve the driving quality by making the road smoother | Pavement Improvement | 2010-03-04 | 2010-04-26 | 2011-07-27 | 2010-09-17 | 159112.05 | 0.629
6507 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 1011013 | This quarter mile long pavement project in St. Joseph on Broad St from Lake Blvd. to State St. will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-01 | 2010-04-19 | 2011-07-27 | 2010-06-16 | 42626 | 0.270
6508 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 1011014 | This 4 mile long pavement project in Berrien County on W Shawnee Rd from Burgoyne Road to Cleveland Avenue will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-06-29 | 2010-09-15 | 2010-08-06 | 47665.8 | 3.961
6509 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 1011015 | The Berrien County Road Commisssion will resurface 0.19 miles of North Main Street from Mars Street to Hamilton Street in the Niles metropolitan area. This will improve the driving quality by making | Pavement Improvement | 2010-06-14 | 2010-06-21 | 2011-07-27 | 2010-08-20 | 92500 | 0.191
6510 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 1011043 | A new surface will be put on Niles-Buchanan Road near Niles Michigan. This will improve the ride quality. | Pavement Improvement | 2010-08-18 | 2011-06-01 | 2011-07-01 | 2011-08-09 | 66268.18 | 3.875
6511 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 1012004 | The Branch County Road Commisssion will resurface 0.28 miles of North Michigan Avenue from Smith Street to Seeley Street in the city of Coldwater. This will improve the driving quality by making the | Pavement Improvement | 2010-04-09 | 2010-05-14 | 2011-07-27 | 2010-05-26 | 146979 | 0.278
6512 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 1012005 | A pavement improvement project in Branch County near the city of Colwater on Central road from Bloack Road to South Angola Road and on Warren Road from Lake Drive to Fremont road will smooth the road | Pavement Improvement | 2010-02-17 | 2010-08-10 | 2010-09-15 | 2010-08-19 | 71993.32 | 5.471
6513 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 1013012 | The Calhoun County Road Commission will resurface 0.8 miles of Meachem Road from Upton to Capital in the Battle Creek urbanized area. This will improve the driving quality by making the road smoother | Pavement Improvement | 2010-04-28 | 2010-05-03 | 2011-07-27 | 2010-06-15 | 189830.75 | 0.781
6514 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 1013013 | This half mile pavement project on Riverside Dr Burnham St. Territorial Rd. will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-28 | 2010-05-03 |  | 2010-06-15 | 92237.61 | 0.288
6515 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 1013014 | This half mile long pavement project on Watson Street from Eaton to Maple Street in Albion will make the road smoother and improve ride quality. | Pavement Improvement | 2010-03-25 | 2010-07-12 | 2011-07-27 | 2010-09-02 | 185000 | 0.503
6516 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 1013017 | The Calhoun County Road Commission will resurface 0.7 miles of 6 1/2 Mile Road from B Drive N to Christian Drive | Pavement Improvement | 2010-05-28 | 2010-06-01 | 2011-07-27 | 2010-07-06 | 176098.36 | 0.774
6517 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 1013020 | This mile long pavement project in Calhoun County on N Dr N from 15 Mile Rd to 16 Mile Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-28 | 2010-06-01 | 2011-07-27 | 2010-06-22 | 109313.64 | 1.028
6518 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 1013034 | "Resurface, curb & gutter/0.06 mi of hot mix asphalt resurfacing, storm sewer, and concrete curb, gutter, sidewalks, and ADA ramps on Hamblin Road at Jackson Road in the city of Battle Creek, Calho | Pavement Improvement | 2010-09-23 | 2010-10-07 | 2011-07-27 | 2010-11-11 | 43028 | 0.187
6519 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 1014003 | The Cass County Road Commisssion will resurface 1.2 miles of Dixon Road from Indian Lake Road to M-152, in the northwest part of the county. This will improve the driving quality by making the road s | Pavement Improvement | 2009-10-21 | 2010-07-19 | 2010-07-30 | 2010-07-29 | 20682.78 | 1.197
6520 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 1014004 | City of Dowagiac will repave Middle Crossing Road from West Prairie Ronde to City Limits | Pavement Improvement | 2010-02-08 | 2010-09-15 | 2010-10-15 | 2010-10-15 | 50000 | 0.270
6521 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 1014005 | The Cass County Road Commission will resurface 0.6 miles of Gumwood Road from the state line to Redfield Street | Pavement Improvement | 2010-02-17 | 2010-07-06 | 2011-07-27 | 2010-08-24 | 241685.41 | 0.630
6522 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHARLEVOIX |  | 01 | 1015003 | The Charlevoix County Road Commission will resurface 2.5 miles of Peninsula Rd from Advance Rd to Reich Rd in the vicinity of East Jordane. This will improve the driving quality by making the road s | Pavement Improvement | 2010-05-06 | 2010-05-26 | 2010-07-02 | 2010-07-22 | 340911 | 2.438
6523 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 1016006 | Four tenths of a mile of West Central Ave will be resurfaced from Nicolet to Huron in the Village of Mackinaw City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-22 | 2010-04-26 | 2010-05-27 | 2010-05-21 | 284181.11 | 0.352
6524 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 1016008 | The Village of Mackinaw City will build a paved pathway on the Mackinaw City Rail to Trail route for cyclists walkers and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2010-06-15 | 2010-06-30 | 2010-08-13 |  | 805648.8 | 0.082
6525 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 1016012 | This pavement project in Cheboygan on S Western Ave from city line to Lincoln Ave will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-09 | 2010-06-28 | 2010-07-16 | 2010-07-16 | 63911.72 | 1.016
6526 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017003 | This pavement project on Riverside Drive in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-01-05 | 2010-05-17 | 2010-07-02 | 2010-06-24 | 573808.58 | 4.986
6527 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017007 | This pavement project at Kincheloe AFB in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-03-26 | 2010-05-06 | 2010-07-30 | 2010-07-27 | 135000 | 0.572
6528 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017009 | This pavement project on Oak Street in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-04-01 | 2010-05-24 | 2010-07-15 | 2010-07-13 | 288244.98 | 0.969
6529 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017011 | This pavement and Rumble Strip project on M-129 in Chippewa County will improve safety and make the road smoother. | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2012-12-31 | 2010-11-05 | 4099773 | 7.251
6530 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017013 | This pavement project in Chippewa County on H40 (Main & Albert) from M63 Westerly-S of South Street will smooth the road and improve ride quality | Pavement Improvement | 2010-04-22 | 2010-05-12 | 2010-10-29 | 2010-08-13 | 108457.42 | 0.578
6531 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017014 | This guardrail installation project on M-48 in Chippewa County will improve safety. | Other | 2009-05-11 | 2009-05-11 | 2010-06-25 | 2010-06-28 | 158391.49 | 24.000
6532 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017015 | This shoulder paving project on M-28 in Chippewa County will improve safety. | Pavement Improvement | 2010-04-22 | 2010-07-14 | 2010-09-03 | 2010-09-03 | 1191547.56 | 10.769
6533 | Underway | C950 | Ferryboat | MICHIGAN | CHIPPEWA |  | 01 | 1017029 | Dock Upgrades | Other | 2010-07-12 |  | 2012-07-16 |  | 1175000 | 2.135
6534 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLARE |  | 04 | 1018007 | Just outside the City of Clare in Clare County there will be 2.0 miles of resurfacing on E. Beaverton Rd to improve driving quality by making the road smoother. | Pavement Improvement | 2010-03-12 | 2010-04-26 | 2010-06-11 | 2010-06-08 | 449771 | 2.001
6535 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | CLARE |  | 04 | 1018011 | A bike trail will be built on the Pere Marquette Rail Trail east of Evart for walkers and cyclists. | Transportation Enhancements | 2010-02-23 | 2010-02-23 | 2012-02-01 | 2010-11-18 | 753890.46 | 15.620
6536 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 1019004 | This pavement project on N Lansing St BR 127 to Walker in St. Johns will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-01 | 2010-06-28 | 2010-07-02 | 2010-08-12 | 78215.65 | 0.117
6537 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 1019005 | This pavement project on W Howe Rd Grange to Wacousta will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-09-07 | 2010-09-17 | 2010-09-17 | 67457 | 4.887
6538 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 1019006 | In the City of St. Johns | Pavement Improvement | 2010-06-10 | 2010-06-19 | 2010-08-10 | 2010-08-12 | 47000 | 0.436
6539 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CRAWFORD |  | 01 | 1020006 | This pavement project near Grayling on W County Road from east of North Stephan Bridge Rd to west of KP Rd will smooth the road and improve ride quality. | Pavement Improvement | 2010-01-01 | 2010-01-01 | 2010-06-25 | 2010-07-13 | 67316.58 | 0.978
6540 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 1021011 | This pavement prjoect from Ludington St to 8th Avenue in the City of Escanaba will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-06-11 | 2010-07-06 | 2010-09-24 | 2010-11-04 | 300000 | 0.733
6541 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 1021012 | This pavement improvement project in Delta County near the town of Gulliver on County Road 432 will rebuild a little over one mile of pavment and improve the ride quality. | Pavement Improvement | 2010-06-30 | 2010-08-16 | 2010-10-15 | 2010-09-28 | 199394.58 | 1.207
6542 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 1021023 | Resurface, Crack Fill and Chip | Pavement Improvement | 2010-08-18 | 2011-05-01 | 2011-06-30 | 2011-08-12 | 94000 | 5.371
6543 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 1022006 | This pavement project on County Road 569 in Dickinson County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-02-26 | 2010-05-12 | 2010-08-28 | 2010-07-29 | 277036.3 | 1.465
6544 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 1022009 | This pavement project on West Ludington Street in the City of Iron Mountain will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-05-25 | 2010-06-01 | 2010-09-20 | 2010-10-19 | 92100.6 | 0.185
6545 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 1022018 | Culvert Replacement | Pavement Improvement | 2010-07-30 | 2010-09-13 | 2010-10-31 | 2010-11-04 | 32785.7 | 5.516
6546 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023004 | In the City of Eaton Rapids just under 1/2 mile of State Street will be reconstructed from West of Miller Drive to the City Limits. Work will include reconstructing the roadway and building a left tu | Pavement Improvement | 2010-04-02 | 2010-06-14 |  | 2010-07-02 | 110000 | 0.389
6547 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023005 | This pavement project on S Cochran Rd Butterfield to Five Point Highway will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-07-14 | 2010-07-12 | 71300 | 5.047
6548 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023006 | This pavement project on E Five Point Hwy Freeman to Narrow Lake Road will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-08-31 | 2010-08-30 | 66400 | 4.552
6549 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023007 | This pavement project on W Five Point Hwy Lacey Lake Road to Battle Creek Road will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-08-31 | 2010-08-16 | 68200 | 4.808
6550 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023008 | This pavement project on W Vermontville Hwy Hager Road to Vertmontville will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-08-05 | 2010-08-02 | 34600 | 2.373
6551 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023009 | This pavement project on N Cochran Rd M-50 to Pinch Street will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-07-31 | 2010-07-21 | 47180 | 3.293
6552 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023010 | This pavement project on N Canal Rd Bentley to Vermontville Highway will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-08-31 | 2010-08-23 | 79300 | 5.526
6553 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023011 | This pavement project on Mulliken Rd M-50 to Cochran will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-07-31 | 2010-07-22 | 76440 | 5.423
6554 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023012 | This pavement project on N Cochran Rd Mt. Hope to M-43; M-43 to Eaton Highway will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-07-21 | 2010-07-21 | 59000 | 4.030
6555 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023013 | In the City of Potterville in Eaton County 1/4 mile of East Main Street will be reconstructed from Hartel Road (State Route M-100) to Dawn Court. Work will include sidewalk improvements and drainage | Pavement Improvement | 2010-03-11 | 2010-06-21 | 2010-08-27 | 2010-08-27 | 220000 | 0.218
6556 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EMMET |  | 01 | 1024013 | Resurfacing | Pavement Improvement | 2010-09-13 | 2010-09-21 | 2010-10-29 | 2010-10-08 | 62878.19 | 2.996
6557 | Completed | C200,C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 1025003 | In Genesee County, MDOT will repair 8.11 miles on M-15 from the Oakland County line northerly to south of I-69 to extend the service life of the existing road. | Pavement Improvement | 2009-03-31 | 2009-03-31 | 2011-01-21 | 2010-06-25 | 1299810.28 | 8.243
6558 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 1025009 | The MDOT will make repairs to the bridge at M-11 over the Grand River in the City of Walker to make the bridge last longer. | Transportation Enhancements | 2010-04-19 | 2010-04-29 | 2011-09-15 |  | 935890.15 | 0.182
6559 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025020 | Four tenths of a mile of Elms Rd from River Rd to Flusing Rd in the City of Flushing will be resurfaced. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-03-31 | 2009-03-31 | 2011-04-01 | 2010-09-03 | 607702.56 | 0.524
6560 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025021 | One mile of Davison Rd from Genesee Rd to Belsay Rd in the City of Burton will be resurfaced. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-22 | 2009-12-22 | 2010-08-15 | 2010-06-29 | 725856.48 | 0.999
6561 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025024 | This pavement project in Flint on Perry Road From Terrace Drive to City Limits will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-28 | 2010-05-06 | 2010-09-01 | 2010-08-24 | 140861 | 0.336
6562 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025026 | The City of Flushing is resurfacing 0.3 miles of Terrace Street from River Road to Main Street. This project will improve the pavement condition and ride quality. | Pavement Improvement | 2010-06-29 | 2010-07-02 | 2010-10-10 | 2010-08-25 | 152280 | 0.242
6563 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025075 | Resurface | Pavement Improvement | 2010-12-14 | 2011-04-13 | 2011-07-01 | 2011-05-30 | 111607.49 | 0.169
6564 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 1027004 | About 1/2 mile of Johnson Rd from Colby St to Bessemer City Limits, in Gogebic County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 2010-04-14 | 2010-06-21 | 2010-08-20 | 2010-07-13 | 63728.76 | 0.315
6565 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 1027006 | This paving project on Prison Camp Road in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-04-08 | 2010-06-28 | 2010-10-15 | 2010-07-08 | 241062.5 | 1.606
6566 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 1027007 | This pavement project on North Lake Street in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-06-18 | 2010-08-30 | 2010-10-15 | 2010-11-09 | 120000 | 0.250
6567 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 1028008 | New pavement markings will be placed in Traverse City on various roadways to improve roadway delineation. | Safety/Traffic Management | 2010-05-25 | 2010-08-23 | 2010-09-30 | 2010-09-28 | 127870.92 | 1.090
6568 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 1028011 | This project will improve safety by renewing the pavement striping throughout Grand Traverse County. | Safety/Traffic Management | 2010-06-03 | 2010-06-07 | 2010-07-02 | 2010-06-08 | 36217.91 | 1.154
6569 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRATIOT |  | 04 | 1029006 | From the St. Louis north city limit northerly to McGregor Road in Gratiot County there will be 0.76 miles reconstruction on Riverside Drive to improve the driving quality of the roadway. | Pavement Improvement | 2010-01-22 | 2010-04-06 | 2010-08-13 | 2010-06-18 | 299266.73 | 0.790
6570 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRATIOT |  | 04 | 1029015 | Resurface | Pavement Improvement | 2010-06-10 | 2010-08-23 | 2010-08-31 | 2010-08-31 | 17000 | 1.001
6571 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 1030004 | 10.43 miles of South Meridian Road (US-127) from the Ohio State line north to M-34 will be resurfaced to improve pavement rideability and increase pavement smoothness. This project will include drain | Pavement Improvement | 2009-10-29 | 2009-10-29 | 2011-04-01 | 2010-11-12 | 6229866.88 | 10.430
6572 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 1030008 | This pavement project in Hillsdale on East Fayette Street from Hillsdale to Oake will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-02 | 2010-06-11 | 2010-07-24 | 2010-08-19 | 170000 | 0.213
6573 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 1030010 | This pavement project on Squawfield Road from US-127 to Waldron Road in rural Hillsdale County will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-08-12 | 2010-09-30 | 2010-09-14 | 41679.54 | 2.987
6574 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 1031008 | This pavement project in Owosso on Pike River Rd from Chassell/Painesdale Rd- to Lower Worham Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-01 | 2010-05-06 | 2010-09-24 | 2010-09-24 | 434256.37 | 1.565
6575 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 1031009 | This pavement project in Houghton on Campus Drive from Poplar Street to Elevation Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-23 | 2010-04-28 | 2010-10-15 | 2010-08-16 | 90000 | 0.123
6576 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 1031011 | This guardrail installation project on M-26 in Houghton County will improve safety. | Other | 2010-02-23 | 2010-02-23 |  | 2010-09-15 | 59094.52 | 0.789
6577 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 1032008 | The Huron County Road Commission will resurface 2 and a quarter miles of French Line Rd from the east Village limits of Ubly to Verona Rd. This will improve the driving quality by making the road smo | Pavement Improvement | 2010-04-01 | 2010-08-30 | 2010-09-15 | 2010-09-15 | 278144 | 2.237
6578 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 1033005 | 0.20 miles of North Williamston Road from I-96 to the north in Ingham County near the city of Williamston will be resurfaced to improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2010-04-23 | 2010-05-10 |  | 2010-05-28 | 92000 | 0.200
6579 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 1033009 | This pavement project on W Holmes Rd Berwick to Plesant Grove will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-08 | 2010-06-14 | 2010-08-27 | 2010-08-16 | 551424.39 | 0.841
6580 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 1033010 | 1.33 Miles of Edgewood Blvd will be reconstructed in the city of Lansing from South Washington Avenue to South Cedar Street Improvements will improve roadway rideability and make the roadway smoother | Pavement Improvement | 2010-01-20 | 2010-06-28 | 2010-11-30 | 2011-11-11 | 731384.29 | 2.463
6581 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 1033011 | 1.7 miles of North Waverly Road from West Willow Street to North Grand River Avenue will be resurfaced in Lansing. The roadway will have improved rideablity and the improved smoothness. | Bridge Improvement | 2010-05-19 | 2010-06-02 | 2010-09-03 | 2010-10-22 | 996268.14 | 1.487
6582 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 1033046 | mill and resurface | Pavement Improvement | 2010-09-10 | 2011-05-09 | 2011-06-12 | 2011-06-10 | 102189.79 | 0.511
6583 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 1034004 | The Ionia County Road Commission will resurface three quarters of a of Mill Street from Bridge Street to the Village of Saranac. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-24 | 2010-05-04 | 2010-06-12 | 2010-06-25 | 239737 | 0.754
6584 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 1034005 | At various loacation on Hall Street in Belding | Pavement Improvement | 2010-04-14 | 2010-07-06 | 2010-07-30 | 2010-07-30 | 110000 | 0.359
6585 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 1034011 | 1.7 miles of North Waverly Road from West Willow Street to North Grand River Avenue will be resurfaced in Lansing. The roadway will have improved rideablity and the improved smoothness. | Pavement Improvement | 2010-01-01 | 2010-01-01 | 2010-11-12 |  | 239736 | 1.001
6586 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 1034014 | This two and a half mle long pavement project on M-21 from east of the Kent / Ionia County line to Pinckney Road will make the pavement smoother and improve ride quality | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2012-03-31 | 2010-10-07 | 1003691.7 | 2.759
6587 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IOSCO |  | 01 | 1035003 | The Iosco County Road Commission will resurface three quarters of a mile of North Skeel Ave from F-41 to Arrow St in the Huron National Forest. This will improve the driving quality by making the roa | Pavement Improvement | 2010-02-08 | 2010-06-03 | 2011-06-30 | 2010-06-24 | 135000 | 0.719
6588 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IOSCO |  | 01 | 1035004 | The Iosco County Road Commission will resurface 2.5 miles of Rollway Rd from M-65 to Liberty Rd in the Huron National Forest west of Oscoda. This will improve the driving quality by making the road s | Pavement Improvement | 2010-03-09 | 2010-05-18 | 2011-06-30 | 2010-06-21 | 353290 | 2.419
6589 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IRON |  | 01 | 1036006 | A little over 2 miles of CR651 from W Sunset Lake Rd-Noren Rd near the city of Iron River in Iron County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 2010-04-26 | 2010-06-01 | 2010-06-30 | 2010-06-30 | 213058.22 | 2.210
6590 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IRON |  | 01 | 1036007 | This pavement project on Lay Ave. in the City of Iron River will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-03-23 | 2010-06-25 | 2010-08-13 | 2010-08-06 | 183884.27 | 0.675
6591 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 1037004 | The City of Mt. Pleasant is resurfacing 1.01 miles on South Mission Street to improve driving quality by making the road smoother. | Pavement Improvement | 2010-03-10 | 2010-05-03 | 2010-05-28 | 2010-05-24 | 188041.91 | 1.010
6592 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 1037005 | The City of Rosbush is resurfacing 0.94 miles on E. Broomfield Road to improve driving quality by making the road smoother. | Pavement Improvement | 2010-03-23 | 2010-06-08 | 2010-06-25 | 2010-06-14 | 50000 | 0.940
6593 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 1037006 | The City of Mt. Pleasant is resurfacing 0.219 miles on East Michigan Street to improve driving quality by making the road smoother. | Pavement Improvement | 2010-06-11 | 2010-06-28 | 2010-09-01 | 2010-09-02 | 311637.68 | 0.219
6594 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON |  | 07 | 1038005 | I-94 near the city of Jackson in Jackson County from East of Sargent Road to the Washtenaw County Line will be rebuilt to improve mobility and reduce congestion | Pavement Improvement | 2009-10-26 | 2009-10-26 | 2012-05-02 |  | 31470300 | 22.952
6595 | Obligated and Awarded | C220 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 1038006 | The Amtrak Depot in Jackson will be rehabilitated.. | Transportation Enhancements |  |  | 2012-09-30 |  | 938000 | 0.000
6596 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 1038010 | This pavement project on W Argyle St from Wisner Street to West Avenue | Pavement Improvement | 2010-05-18 | 2010-08-02 |  | 2010-09-09 | 297511.96 | 0.253
6597 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 1038014 | This pavement project near the city of Jackson on Spring Arbor Rd., from Mc Cain Road to west of Robinson Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-01 | 2010-06-21 |  | 2010-08-22 | 236975.07 | 1.211
6598 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO |  | 06 | 1039009 | A path for walkers and cyclists will be built on Kalamazoo River Valley Trail | Transportation Enhancements | 2009-11-18 | 2010-04-05 | 2012-10-31 |  | 1708230.65 | 6.105
6599 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 1039011 | To improve safety this project will realign the intersection of Texas Drive @ 8th Street | Pavement Improvement | 2010-04-09 | 2010-04-19 | 2011-07-27 | 2010-05-27 | 268563.4 | 0.062
6600 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO |  | 06 | 1039012 | This pavement project on Mercury Dr From MN Avenue to East County Line will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-27 | 2010-08-04 | 2010-08-19 | 2010-09-09 | 32384.65 | 2.185
6601 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO |  | 06 | 1039013 | This pavement project on C Avenue 24th Street and AB Avenue from D Avenue to AB Aven will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-27 | 2010-07-26 | 2010-08-06 | 2010-09-09 | 88089.66 | 3.375
6602 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 1039015 | This pavement project in Kalamazoo on W Michigan Ave Sprague to the west line of Section 21 will smooth the road and improve ride quality. | Pavement Improvement | 2010-06-25 | 2010-07-26 |  |  | 129441 | 0.270
6603 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 1039042 | Mill and resurface | Pavement Improvement | 2010-09-10 | 2011-07-07 | 2010-09-15 | 2011-07-11 | 17931 | 1.007
6604 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALKASKA |  | 04 | 1040205 | This pavement project in Kalkaska County on County Highway 612 from Darke Rd W 1/2 Mile will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-17 | 2010-06-08 | 2010-06-11 | 2010-06-11 | 27944.53 | 0.499
6605 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041007 | About a mile of Lake Drive From Fuller Avenue to Calton Avenue in the City of Gran in Kent County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 2009-10-26 | 2010-04-19 | 2010-07-31 | 2010-07-16 | 147293.63 | 0.190
6606 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 1041017 | The MDOT will resurface a half mile of the John J. Oostema Boulevard from Patterson Avenue to Gateway Drive at the Gerald Ford International Airport in the City of Kentwood. This will improve the dri | Pavement Improvement | 2010-03-26 | 2010-04-26 | 2010-06-30 | 2010-06-30 | 764860.66 | 1.178
6607 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041018 | The MDOT will replace the Diamond Avenue bridge over I-196 in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 2009-12-01 | 2009-12-01 | 2013-09-09 |  | 2331959.13 | 0.000
6608 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041020 | The MDOT will repair almost 2 miles of M-11 from Division Avenue to kalamazoo Avenue in the City of Grand Rapids to extend the service life of the existing road. | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2012-03-30 | 2010-03-29 | 2023440.1 | 1.849
6609 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041021 | The City of Grand Rapids is building sidewalks to improve pedestrian mobility along M-11 from Division Avenue to Kalamazoo Avenue | Pavement Improvement | 2010-03-24 | 2010-03-24 | 2012-03-31 | 2010-03-29 | 1369375.31 | 1.924
6610 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041022 | The Kent County Road Commission will widen three quarters of a West River Drive from Jupitor Road to the Rogue River Bridge in Kent County. This will improve mobility and the driving quality. | Pavement Improvement | 2010-04-16 | 2010-04-19 | 2010-08-15 | 2010-07-13 | 1510820.41 | 0.754
6611 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041024 | The City of Kentwood will resurface a 0.8 miles of East Paris Avenue from Sparks Drive to Burton Street in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-29 | 2010-05-03 | 2010-06-19 | 2010-09-25 | 537967.7 | 0.792
6612 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041027 | The City of Rockford will resurface a quarter mile Main Street from Division Street to Courtland Street in the City of Rockford. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-04-16 | 2010-05-14 | 2010-05-28 | 2010-05-28 | 127500 | 0.238
6613 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041028 | The City of Kentwood will resurface a 0.4 miles of Barden Drive from East Paris Avenue to M-37 in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-26 | 2010-05-03 | 2010-06-11 | 2010-06-01 | 238505 | 0.353
6614 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041033 | This pavement project in Grand Rapids on Scribner Avenue From US-131 off ramp to Webster Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-23 | 2010-05-10 | 2010-07-01 | 2010-07-01 | 131395.23 | 0.438
6615 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041034 | This pavement project in Grand Rapids on Turner Avenue From Leonard Street to 6th Street. Grand Rapids will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-23 | 2010-05-10 | 2010-07-01 | 2010-07-01 | 79929.14 | 0.551
6616 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 1041036 | This pavement project in Kent County on Cannonsburg Road from From Giles Avenue to Meyers Lake Avenue will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-29 | 2010-05-04 | 2010-07-30 | 2010-06-10 | 142761 | 2.860
6617 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 1041037 | This pavement project on _will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-29 | 2010-05-06 | 2010-06-18 | 2010-08-28 | 120000 | 0.903
6618 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041038 | Grand Rapids will repave Hall Street From US-131 SB ramps to Grandville Avenue GR | Pavement Improvement | 2010-06-15 | 2010-06-17 | 2010-06-30 | 2010-06-30 | 110121.77 | 0.162
6619 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041039 | The MDOT will make repairs to the bridge at 44th Street over I-196 in the City Grandville area to make the bridge last longer. | Bridge Improvement | 2009-05-11 | 2009-04-21 | 2010-12-31 | 2010-06-17 | 463317.5 | 0.000
6620 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041040 | The City of Walker will resurface a half mile of Veteran's Memorial Drive from Riverbend to Maynard Avenue in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-06-10 | 2010-06-28 | 2010-08-11 | 2010-08-30 | 852998.39 | 1.338
6621 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041053 | This pavement project in Jackson on W Argyle St from West to Wisner will smooth the road and improve ride quality | Pavement Improvement | 2010-06-22 | 2010-07-06 | 2010-07-30 | 2010-07-30 | 213925.38 | 3.951
6622 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041115 | Rotomill/resurface | Pavement Improvement | 2011-01-06 | 2011-05-02 | 2011-06-10 | 2011-06-10 | 402996 | 0.506
6623 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041127 | Bridge Replacement, Add Lanes | Bridge Replacement | 2010-09-20 | 2010-09-20 | 2013-01-31 |  | 4600000 | 0.324
6624 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 1044006 | From the southern Macomb County line northerly to the northern village limit of Almont and from the northern village limit northerly to just south of I-69 in Lapeer County there will be 6.20 miles of | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2012-02-01 | 2010-11-19 | 1284955.19 | 6.570
6625 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 1044011 | The city of Imlay will reconstruct 0.94 miles on Imlay City road to improve the driving quality by making the road smoother. | Pavement Improvement | 2010-06-15 | 2010-07-09 | 2010-10-15 | 2010-10-07 | 721039 | 1.371
6626 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046006 | This pavement project in Adrian on Sutton Road form Occidental to Green will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-10 | 2010-04-05 | 2010-09-03 | 2010-08-31 | 258333 | 1.144
6627 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046007 | 1/4 of a mile of North Ottawa Street is being resurfaced from M-50 to Evans Street in the City of Tecumseh | Pavement Improvement | 2010-06-11 | 2010-07-08 | 2010-08-13 | 2010-08-17 | 80333 | 0.284
6628 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046008 | This pavement project in Adrian on McKenzie Street from Maumee Street to Maple Avenue will smooth the road and improve ride quality. | Pavement Improvement | 2010-06-24 | 2010-07-12 | 2010-07-30 | 2010-07-26 | 215313.83 | 0.376
6629 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046009 | 1.0 miles of pavement resurfacing of North Evan Street from Burt Road to the city limits of Tecumseh | Pavement Improvement | 2010-06-11 | 2010-07-08 | 2010-08-13 | 2010-08-17 | 151072.5 | 0.572
6630 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046010 | The community of Clinton will reconstruct 1 mile of Tecumseh/Clinton Road. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-07-01 | 2010-07-12 | 2011-06-01 | 2011-07-07 | 573122.96 | 1.322
6631 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON |  | 08 | 1047018 | Rehabilitate Roadway | Pavement Improvement | 2010-12-15 | 2011-05-10 |  | 2011-06-03 | 466134 | 1.007
6632 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LUCE |  | 01 | 1048006 | This pavement project on County Road 405 in Luce County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-04-28 | 2010-06-08 | 2010-10-08 | 2010-07-12 | 279120.54 | 2.283
6633 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | LUCE |  | 01 | 1048007 | This shoulder paving project on M-28 in Luce County will improve safety. | Pavement Improvement | 2010-02-23 | 2010-02-23 | 2010-10-18 | 2010-09-03 | 1062349.03 | 5.977
6634 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACKINAC |  | 01 | 1049003 | This pavement project on M-134 from east of the I-75 Overpass to west of 3 M will make the road smoother and improve ride quality | Pavement Widening | 2009-10-15 | 2009-10-15 | 2010-10-18 | 2010-09-02 | 2479770.79 | 13.535
6635 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MACKINAC |  | 01 | 1049012 | This pavement project in Mackinac County on Borgstrom Rd US2-H40 will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-05 | 2010-06-01 | 2010-08-17 | 2010-08-30 | 400284 | 4.740
6636 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050006 | MDOT will rebuild concrete barrier and landscaping along I-696 from Gratiot Road to I-75 in Metro Detroit in Macomb County to improve safety | Pavement Improvement | 2010-01-25 | 2009-04-28 | 2013-12-31 |  | 10593585.3 | 17.407
6637 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050007 | Pavement patching to extend the service life of the existing road throughout Macomb County. | Pavement Improvement | 2010-03-11 | 2010-04-06 | 2010-07-31 | 2010-08-04 | 2862651.74 | 15.494
6638 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050008 | Resurfacing to maintain the pavement condition and improve ride quality of Calahan Road in Roseville. | Pavement Improvement | 2010-03-25 | 2010-04-05 | 2010-06-15 | 2010-06-16 | 380182.8 | 0.508
6639 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB |  | 10 | 1050009 | This pavement project on Division Street M-19 to Grand Trunk Railroad will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-03 | 2010-08-09 | 2010-08-30 | 2010-08-30 | 95000 | 0.406
6640 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050010 | Complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along North Fulton in Macomb County. | Pavement Improvement | 2010-04-14 | 2010-04-27 | 2011-09-16 | 2011-09-16 | 512672.23 | 0.427
6641 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050012 | Resurfacing to maintain the pavement condition and improve ride quality of South Main Street in Mt. Clemens. | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-06-01 | 2010-06-18 | 318321.95 | 0.348
6642 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050013 | Resurfacing to maintain the pavement condition and improve ride quality of Rathbone Street in Mt. Clemens. | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-06-01 | 2010-06-18 | 161280.32 | 0.264
6643 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050014 | Resurfacing to maintain the pavement condition and improve ride quality of Hayes Avenue in Eastpointe. | Pavement Improvement | 2010-05-13 | 2010-05-12 | 2010-08-28 | 2010-10-21 | 790606.02 | 0.510
6644 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050015 | Resurfacing to maintain the pavement condition and improve ride quality of | Pavement Improvement | 2010-06-03 | 2010-06-10 | 2011-05-30 | 2011-03-03 | 1250000 | 0.515
6645 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050016 | Macomb County will reconstruct Kelly SB from Toepfer to 8 Mile to improve driving quality by making the road smoother | Pavement Improvement | 2010-05-24 | 2010-06-01 | 2010-09-18 |  | 1128751.38 | 1.642
6646 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050039 | Resurface road | Pavement Improvement | 2011-02-15 | 2011-04-15 | 2011-06-30 |  | 776818 | 0.449
6647 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050040 | Resurface road | Pavement Improvement | 2011-02-15 | 2011-04-15 | 2011-06-30 |  | 249183 | 0.323
6648 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050053 | Resurface road | Pavement Improvement | 2010-10-27 | 2011-05-02 |  | 2011-06-01 | 187339.74 | 0.997
6649 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MANISTEE |  | 02 | 1051009 | The City truck route in the City of Mainistee will be resurfaced for 1 mile from 10th St to 16th St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-04-14 | 2010-06-01 | 2010-07-02 | 2010-07-02 | 110000 | 0.900
6650 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MANISTEE |  | 02 | 1051011 | The Manistee County Road Commission is replacing a bridge on 9 Mile Road east of the Village of Kaleva. This will improve safety and mobility. | Pavement Improvement | 2010-02-24 | 2010-06-01 | 2010-10-01 | 2010-09-30 | 36296 | 0.080
6651 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 1052005 | This pavement project on County Road 545 US41 South 0.5 will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-14 | 2010-07-21 | 2010-10-01 | 2010-09-29 | 90650.41 | 0.540
6652 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 1052006 | This pavement project on Croix Street in the City of Negaunee will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-07-23 | 2010-07-29 | 2010-08-28 | 2010-09-03 | 222944.66 | 0.486
6653 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MASON |  | 02 | 1053003 | This pavement project on Qrtrlne/SgrGrv/Reek/Bnsn/Hwly County Line to .25 Mi S of Lak will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-22 | 2010-07-21 | 2010-08-31 | 2010-08-13 | 342215.76 | 18.239
6654 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MASON |  | 02 | 1053004 | This pavement project in Ludington on South Williams Street from Ludington Avenue to Filer Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-29 | 2010-05-10 | 2010-06-25 | 2010-06-25 | 171252 | 0.144
6655 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 1054007 | The City of Big Rapids will resurface a half mile of Bronson Ave from Maple to Milton in the City of Big Rapids. This will improve the driving by making the road smoother. | Pavement Improvement | 2010-04-08 | 2010-07-13 | 2010-08-20 | 2010-08-10 | 206951.98 | 1.358
6656 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055006 | Almost 2 miles of County Road 352 from CR577 to Hallfrisch Road near the city of Stephenson in Menominee County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 2010-02-22 | 2010-08-10 | 2010-09-03 | 2010-09-03 | 268649.11 | 1.871
6657 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055008 | This pavement project on River Road in the Village of Stephenson will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-03-09 | 2010-08-17 | 2010-08-31 | 2010-08-31 | 95700 | 0.359
6658 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055009 | Menominee County will repave County Road 581 from 0.17 Mi W of River Rd to CR577 | Pavement Improvement | 2010-02-22 | 2010-08-12 | 2010-09-03 | 2010-09-03 | 65700 | 1.274
6659 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055012 | This pavement project in Menominee on 14th Avenue from 1st Street to 13th Street will smooth the road and improve ride quality | Pavement Improvement | 2010-06-01 | 2010-08-16 | 2010-08-15 | 2010-11-12 | 175000 | 0.456
6660 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055019 | Resurface | Pavement Improvement | 2010-08-25 | 2010-09-02 | 2010-10-01 | 2010-10-01 | 81000 | 1.464
6661 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 1056008 | This pavement project in Midland on North Saginaw Road from S.B.S. RR Xing to 3752 Feet North and Austin to J will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-09 | 2010-06-14 | 2010-09-03 | 2010-09-03 | 470000 | 0.630
6662 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MISSAUKEE |  | 04 | 1057008 | This pavement project in Missaukee County on N Lucas Rd from Manistee River to County Line will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-30 | 2010-06-15 | 2010-06-25 | 2010-06-16 | 60072.5 | 1.884
6663 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058010 | There will be a culvert rehabilitation of the culvert at the Springbrook Drain at Sterns Road in southern Monroe county south of the city of Luna Pier. This project will provide to effect county drai | Pavement Improvement | 2010-01-27 | 2010-05-10 | 2010-07-16 | 2010-07-01 | 334074.86 | 0.037
6664 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058012 | This pavement project in Monroe County on LaPlaisance Road from Sixth Street to Jones Avenue will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-06 | 2010-07-26 | 2010-07-31 | 2010-10-25 | 280000 | 0.348
6665 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058013 | Monroe County will repave Erie Road from US-24 to M-125 | Pavement Improvement | 2010-02-08 | 2010-02-10 | 2010-09-30 | 2010-12-06 | 9600 | 0.557
6666 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058014 | This project near Temperance will smooth the pavement at the intersection of Jackman Road and Smith Road to improve the ride quality. | Pavement Improvement | 2010-02-17 | 2010-03-05 | 2010-10-07 | 2010-10-14 | 102970.49 | 0.048
6667 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058015 | Various pavements county wide will be resurfaced in Monroe County to smooth the roads and improve ride quality. | Pavement Improvement | 2010-02-17 | 2010-03-05 | 2010-10-07 | 2010-09-01 | 39747.7 | 1.651
6668 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058016 | This project will resurface the roadway at 2 locations; on Laplaissance Road from Dunbar Road to Jones Avenue in the city of Monroe | Pavement Improvement | 2010-02-17 | 2010-04-30 | 2010-11-25 | 2010-10-15 | 243064.72 | 1.593
6669 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | DETROIT,MI | 15 | 1058017 | 0.14 miles of pavement resurfacing on Fort Road from South Huron River Drive to the Wayne County Line in northern Monroe County. This project will improve pavement rideability and increase pavement s | Pavement Improvement | 2010-02-17 | 2010-05-04 | 2010-11-25 | 2010-10-15 | 30106.02 | 0.137
6670 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE |  | 15 | 1058018 | Various pavements county wide will be resurfaced in Monroe County to smooth the roads and improve ride quality. | Pavement Improvement | 2010-02-17 | 2010-03-05 | 2010-10-07 | 2010-11-09 | 161805.13 | 5.009
6671 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE |  | 15 | 1058019 | This project will provide for 1/2 mile of pavement resurfacing on North Dixie Highway from the Fermi Railroad crossing to Post Road north of the city of Monroe in Monroe County. This will provide for | Pavement Improvement | 2010-02-17 | 2010-03-05 | 2010-09-30 | 2010-10-14 | 72376.84 | 0.503
6672 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058020 | Various pavements county wide will be resurfaced in Monroe County to smooth the roads and improve ride quality. | Pavement Improvement | 2010-02-17 | 2010-06-21 | 2010-10-07 | 2010-09-01 | 5384 | 6.135
6673 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058021 | This project will provide for 3/4 of a mile of pavement resurfacing on Albain Road from the Railroad crossing to M-125 in the city of Monroe in Monroe County. This will provide for improved pavement | Pavement Improvement | 2010-02-17 | 2010-05-04 | 2010-11-25 | 2010-10-15 | 81451.16 | 0.735
6674 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058022 | This project will provide for 1.29 miles of pavement resurfacing on North Dixie Highway from Ternes Drive to Hurd Road in the city of Monroe | Pavement Improvement | 2010-07-12 | 2010-07-20 | 2010-11-12 | 2010-10-28 | 219000 | 1.288
6675 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE |  | 15 | 1058023 | Chip and Seal treatment at 3 locations in Monroe County. Sterns Road from M-125 to Summit Raod | Pavement Improvement | 2010-02-19 | 2010-02-23 | 2010-09-30 |  | 75047.31 | 5.635
6676 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE |  | 15 | 1058024 | This project will provide for 1.94 miles of pavement resurfacing on Luna Pier Road from M-125 to I-75 west of the city of Luna Pier in southern Monroe County. This will provide for improved pavement | Pavement Improvement | 2010-02-19 | 2010-03-05 | 2010-09-13 | 2010-08-12 | 166214.87 | 1.939
6677 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058025 | MDOT is resurfacing the pavement and shoulders of 1.43 miles of M-125 from the Michigan/Ohio State Line to Sterns Road. This project will improve the pavement condition and ride quality. | Pavement Improvement | 2010-02-23 | 2010-02-23 | 2010-09-02 | 2010-09-01 | 173748.17 | 1.430
6678 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058026 | The Monroe County Road Commission will be resurfacing 0.6 miles of Lewis Avenue from the Ann Arbor Railroad Crossing to Pickard Avenue. This project will improve the pavement condition and ride quali | Pavement Improvement | 2010-02-23 | 2010-03-05 | 2010-10-13 | 2010-10-14 | 151197.72 | 0.602
6679 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | STATEWIDE | 15 | 1058031 | Resurface | Pavement Improvement | 2010-04-07 | 2010-04-20 | 2010-11-25 | 2010-10-15 | 180241.21 | 2.040
6680 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059009 | This pavement project in Montcalm County on Newcosta/Mt Hope/Sidney Rds from Pakes-Cond;M66-Derby;M82-Kndvlle will improve the drive quality and make the road smoother | Pavement Improvement | 2010-07-09 | 2010-07-21 | 2010-07-30 | 2010-07-28 | 25364.9 | 13.545
6681 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059010 | This pavement project in Montcalm County on County Road 510/Sidney Rd from Derby Rd to Sheridan Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-08-16 | 2010-08-27 | 2010-08-19 | 53622.42 | 3.015
6682 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059011 | This pavement project in Montcalm County on Lake Montcalm Rd NW from Sheridan Road to Wyman Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-07-12 | 2010-08-27 | 2010-08-05 | 36397.33 | 2.050
6683 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059012 | This pavement project in Montcalm County on S Mount Hope Rd from Stanton Rd to Condensary Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-07-29 | 2010-08-27 | 2010-08-19 | 70877 | 6.186
6684 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059013 | This pavement project in Greenvile on Hillcrest Street from north M-57 to Grove Street will smooth the road and improve ride quality. | Pavement Improvement | 2010-05-20 | 2010-07-12 | 2010-07-31 | 2010-08-14 | 65120 | 0.309
6685 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059014 | This project in rural Montcalm County will resurface 3.3 miles of pavement on N. Lakeview Rd./Newcosta Rd. improving the ride quality. | Pavement Improvement | 2010-02-23 | 2010-07-21 | 2010-08-27 | 2010-08-24 | 55732 | 3.388
6686 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTMORENCY |  | 01 | 1060006 | Over 3 miles of County Road 624 from CR459 to Ess Lake Road near the city of Hillman in Montmorency County will be repaved to improve ride quality and make the road smoother | Other | 2009-10-23 | 2009-11-01 | 2010-08-15 | 2010-06-11 | 11000
6687 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTMORENCY |  | 01 | 1060008 | This pavement project in Montmorency County on County Road 624 from CR459 to Ess Lake Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-04-05 | 2011-06-30 | 2011-06-11 | 266568.37 | 3.051
6688 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTMORENCY |  | 01 | 1060009 | This countywide Pavement Marking project in rural Montmorency County will improve traffic operations. | Safety/Traffic Management | 2010-06-29 | 2010-09-17 | 2011-06-30 | 2010-09-21 | 34356 | 1.289
6689 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 1061305 | The MDOT is installing cable guard rail on US-31 from Airline Rd north to Marquette Ave in the Cities of Norton Shores and Muskegon to improve safety. | Safety/Traffic Management | 2009-10-15 | 2009-10-15 | 2011-06-30 | 2011-09-13 | 717712.24 | 10.075
6690 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 1061308 | The City of Norton Shores will resurface a half mile of Sherman Ave from Peck St to Riordan St. This will improve driving quality by making the road smoother. | Pavement Improvement | 2010-03-11 | 2010-04-29 | 2010-06-11 | 2010-06-07 | 199133.92 | 0.442
6691 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 1061314 | The City of Whitehall will resurface a 0.8 miles of White Lake Dr from Whitehall Rd to Hyde Park Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 2010-05-21 | 2010-05-25 |  | 2010-06-04 | 124318.75 | 0.794
6692 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON |  | 02 | 1061316 | Eight miles of Scenic Drive in the City of North Muskegon will be resurfaced from Fenner Rd to South Shore Drive. This will improve driving quality by making the road smoother. | Pavement Improvement | 2010-06-17 | 2010-06-28 |  | 2010-11-05 | 1276972.65 | 9.527
6693 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 1061349 | Resurface | Pavement Improvement | 2010-10-29 | 2011-04-20 |  | 2011-05-09 | 102632 | 0.500
6694 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | NEWAYGO |  | 02 | 1062006 | A little over 3 miles of Alger Road from 128th Street to Moore Road near the city of Grant in Newaygo County will be repaved to improve ride quality and make the road smoother | Other | 2009-10-23 | 2010-03-23 | 2010-07-30 | 2010-08-06 | 20253.11
6695 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | NEWAYGO |  | 02 | 1062007 | North Stone Rd will be resurfaced for one half mile from Main St to 44th St in the village of Fremont.. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-24 | 2010-05-17 | 2010-06-11 | 2010-05-26 | 95000 | 0.500
6696 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | NEWAYGO |  | 02 | 1062009 | Newaygo County will do a pavement project on Alger Road 128th from Street to Moore Road to improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-03-23 | 2010-07-30 | 2010-08-06 | 587372.46 | 2.013
6697 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063003 | Complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along US-24 in Bloomfield Township by MDOT. | Pavement Improvement | 2010-01-19 | 2010-01-19 | 2013-01-19 | 2011-08-29 | 7849832.73 | 1.930
6698 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063008 | This pavement project on Joslyn Ave Walton to North City Limits will improve the drive quality and make the road smoother | Pavement Improvement | 2010-03-24 | 2010-07-07 | 2010-10-01 | 2010-10-01 | 263000 | 0.540
6699 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063009 | Resurfacing to maintain the pavement condition and improve ride quality of Wayne Street in Pontiac. | Pavement Improvement | 2010-03-24 | 2010-05-26 | 2010-07-02 | 2010-07-01 | 187000 | 0.321
6700 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063010 | New pedestrian bridge to improve safety and pedestrian access over US-24 in Pontiac. | Transportation Enhancements | 2010-07-15 | 2010-07-27 | 2010-11-15 |  | 2022628.85 | 0.125
6701 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063011 | Resurfacing to maintain the pavement condition and improve ride quality of 12 Mile Road in Lathrup Village. | Pavement Improvement | 2010-03-30 | 2010-05-10 | 2010-09-30 | 2010-09-10 | 1031000 | 0.987
6702 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063013 | Resurfacing to maintain the pavement condition and improve ride quality of Centerpoint Parkway in Pontiac. | Pavement Improvement | 2010-04-20 | 2010-05-10 | 2010-08-25 | 2010-08-25 | 638489.58 | 1.282
6703 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063014 | Resurfacing to maintain the pavement condition and improve ride quality of Opdyke Road in Auburn Hills. | Pavement Improvement | 2010-04-14 | 2010-04-17 | 2010-08-01 | 2010-07-28 | 1125833.4 | 1.059
6704 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063015 | Resurfacing to maintain the pavement condition and improve ride quality of Middlebelt Road in Farmington Hills. | Pavement Improvement | 2010-04-01 | 2010-04-19 | 2010-08-30 | 2010-10-08 | 1033000 | 1.982
6705 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063016 | Resurfacing to maintain the pavement condition and improve ride quality of Middlebelt Road in Farmington Hills. | Pavement Improvement | 2010-04-01 | 2010-04-19 | 2010-08-30 | 2010-10-08 | 673000 | 2.003
6706 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063017 | This pavement project on Inkster Road from 9 Mile to 11 Mile in the City of Southfield will improve the drive quality and make the road smoother | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2010-10-15 |  | 1964000 | 1.000
6707 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | SOUTH LYON-HOWELL-BRIGHTON | 09 | 1063019 | This pavement project in South Lyonon Nine Mile Road from Dean Drive to Pontiac Trail will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-26 | 2010-06-18 | 2010-09-30 | 2010-09-16 | 509000 | 0.473
6708 | Completed | C200,C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063020 | This pavement project in Oakland County Countywide at 3 locations in Oakland County will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-06 | 2010-07-08 | 2010-08-25 | 2010-09-10 | 817280.24 | 6.233
6709 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND |  | 09 | 1063021 | This pavement project in Oakland County on Grange Hall Road from West Village Limits to North Holly Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-06 | 2010-07-08 | 2010-08-25 | 2010-09-10 | 91737.8 | 0.622
6710 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063022 | This pavement project in Ferndale on Fern Avenue From Chesterfield to Intermodal Ave will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2010-09-13 | 2010-09-26 | 290699.33 | 0.187
6711 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063023 | This pavement project in Ferndale on Chesterfield From Fair to Fern will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2010-09-13 | 2010-09-26 | 173533.06 | 0.526
6712 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063024 | Resurfacing to maintain the pavement condition and improve ride quality of Cooley Lake Road in Waterford. | Pavement Improvement | 2010-05-06 | 2010-05-07 | 2010-11-12 | 2010-11-09 | 1121451.71 | 0.472
6713 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063025 | Resurfacing to maintain the pavement condition and improve ride quality of White Lake Road in Clarkston. | Pavement Improvement | 2010-05-13 | 2010-05-19 | 2010-09-01 | 2010-10-15 | 986000 | 0.937
6714 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063026 | Paving Ray Road east of M-24 to Oxford Road in Oakland County. | Pavement Improvement | 2010-06-11 | 2010-06-21 | 2010-10-15 | 2010-10-15 | 1284335.47 | 0.704
6715 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063027 | Resurfacing to maintain the pavement condition and improve ride quality of Hilton Road in Detroit. | Pavement Improvement | 2010-05-20 | 2010-06-29 | 2010-09-01 | 2010-09-07 | 475000 | 0.518
6716 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063029 | This pavement project near Farmington on Orchard Lake Road from 12 Mile Road to 13 Mile Road will smooth the road and improve ride quality | Pavement Improvement | 2010-05-12 | 2010-05-19 | 2010-08-20 | 2010-08-13 | 864000 | 0.372
6717 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063030 | This pavement project in Pontiac on Walton Road from Joslyn to East City Limits will smooth the road and improve ride quality | Pavement Improvement | 2010-05-20 | 2010-07-06 | 2010-10-29 | 2010-10-29 | 716000 | 1.487
6718 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063031 | This pavement project in Farmington Hills on Grand River Avenue from Haggerty to Ten Mile Road will smooth the road and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-06-24 | 2010-09-25 | 2010-12-02 | 1253938.76 | 0.260
6719 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063032 | This pavement project on Main Street from 13 Mile Road to Chippewa in Royal Oak will smooth the road and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-08-02 | 2010-10-30 | 2011-09-09 | 391000 | 0.462
6720 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063033 | This pavement project on Lincoln Street from Campbell to Stephenson in Royal Oak will smooth the road and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-06-16 | 2010-11-30 | 2010-11-24 | 506000 | 0.499
6721 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063035 | The City of Hazel Park in Metro Detroit will be resurfacing 2.56 miles of the Chrysler Service Drive between 8 Mile Rd. and 9 Mile Rd. This project will improve pavement condition and ride quality. | Pavement Improvement | 2010-02-23 | 2010-07-12 | 2010-11-14 | 2011-05-11 | 1168000 | 2.539
6722 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063044 | Resurface, Rehab, or Restore | Pavement Improvement | 2010-04-01 | 2010-07-12 | 2010-11-14 | 2011-05-11 | 1017000 | 2.117
6723 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 1065006 | The Ogemaw County Road Commission will resurface a half mile of Sage Lake Rd from Harrison Rd to the village limits of Prescott. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-24 | 2010-08-02 | 2010-08-27 | 2010-08-06 | 27757.04 | 0.370
6724 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 1065007 | The Ogemaw County Road Commission will resurface 5.5 miles of West State Rd from Fairview Rd to M-33 east of West Branch. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-10 | 2010-07-23 | 2010-08-27 | 2010-08-05 | 270234.93 | 5.490
6725 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 1065015 | Resurface | Pavement Improvement | 2011-02-18 | 2011-02-18 | 2011-06-24 | 2011-06-24 | 40096 | 0.601
6726 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ONTONAGON |  | 01 | 1066007 | This pavement project on East Shore Rd 4.0 Mi S of M28 to 7.5 Mi S will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-02 | 2010-09-01 | 2010-10-15 | 2010-10-08 | 335005.56 | 3.559
6727 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ONTONAGON |  | 01 | 1066008 | This guardrail installation project on M-26 in Ontonagon County will improve safety. | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2010-09-17 | 2010-09-30 | 506702.94 | 31.324
6728 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ONTONAGON |  | 01 | 1066009 | The culvert project on M-28 in Ontonagon and Dickinson Counties will improve drainage and safety | Pavement Improvement | 2010-02-17 | 2010-02-17 | 2010-07-30 | 2010-07-15 | 160624.63 | 0.000
6729 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 1067006 | A little over 4 miles of River/115th/4 Mile Rpad snear the city of Evart in Osceola County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 2009-10-21 | 2010-05-17 | 2010-07-01 | 2011-04-04 | 228703.25 | 4.143
6730 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 1067016 | HMA Paving of Rail Trail | Transportation Enhancements | 2011-01-13 | 2011-01-13 | 2012-02-01 | 2011-07-22 | 119470.94 | 10.981
6731 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 1068005 | The Oscoda County Road Commission will replace a drainage culvert on Cherry Creek Rd 200 ft west of West Camp Ten Rd to improve drainage and extend the life of the roadway. | Pavement Improvement | 2010-02-09 | 2010-03-19 | 2010-07-30 | 2010-08-03 | 59083 | 0.384
6732 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 1068006 | The Oscoda County Road Commission will replace a drainage culvert on East Kittle Rd 100 ft east of Caldwell Rd to improve drainage and extend the life of the roadway. | Pavement Improvement | 2010-02-09 | 2010-04-08 | 2010-08-30 | 2010-08-03 | 24610 | 0.565
6733 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 1068007 | The Oscoda County Road Commission will replace a drainage culvert on East Kittle Rd 800 ft east of M-33 to improve drainage and extend the life of the roadway. | Pavement Improvement | 2010-02-09 | 2010-04-08 | 2010-10-31 | 2010-10-11 | 55413 | 0.786
6734 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 1068008 | The Oscoda County Road Commission will replace a drainage culvert on Zimowske Rd 900 ft east of Mishler Rd to improve drainage and extend the life of the roadway. | Pavement Improvement | 2010-02-17 | 2010-04-08 | 2010-07-30 | 2010-08-03 | 20945 | 1.043
6735 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTSEGO |  | 01 | 1069003 | 0.3 miles of Meecher Rd from Anna Dr to Buddy Ave will be resurfaced west of Gaylord . This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2010-06-04 | 2010-06-02 | 150000 | 0.304
6736 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | HOLLAND | 02 | 1070006 | Zeeland County will repave 104th Avenue from Paw Paw Drive to I-196 BL in Holland | Pavement Improvement | 2010-03-23 | 2010-04-19 | 2010-07-16 | 2010-10-07 | 506085 | 0.284
6737 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 1070008 | The MDOT will resurface 3.5 miles of M-104 from 144th Ave east to I-96 near Spring Lake. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2012-03-31 | 2010-09-20 | 895094.03 | 3.468
6738 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 1070009 | This pavement project near Eastmanville on 68th Ave from Leonard Street to I-96 will smooth the road and improve ride quality | Pavement Improvement | 2010-06-01 | 2010-06-15 | 2010-07-09 | 2010-07-10 | 163866 | 2.731
6739 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 1070013 | The MDOT will resurface 2 miles of M-121 from 40th Ave to Rush Creek near Hudsonville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-17 | 2010-02-17 | 2012-03-31 | 2011-08-08 | 2593899.65 | 4.029
6740 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | HOLLAND | 02 | 1070064 | Resurface | Pavement Improvement | 2010-12-14 | 2011-05-03 | 2011-06-10 | 2011-06-16 | 246572.47 | 1.009
6741 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | PRESQUE ISLE |  | 01 | 1071003 | The Presque Isle County Road Commission will resurface 1.5 miles of East Heythaler Highway from US-23 to County Road 451 south of Rogers City. This will improve the driving quality by making the road | Pavement Improvement | 2010-03-24 | 2010-05-10 | 2011-06-30 | 2010-06-04 | 352152 | 1.442
6742 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | PRESQUE ISLE |  | 01 | 1071009 | HMA Reconstruction | Pavement Improvement | 2010-09-20 | 2010-09-20 | 2012-03-20 |  | 154118.74 | 1.380
6743 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ROSCOMMON |  | 04 | 1072006 | Over 2 miles of US Old 27 from Mary Road to Yeager Road near the city of Houghton Lake in Roscommon County will have its shoulder widened to improve safety and improve mobility | Pavement Improvement | 2009-10-26 | 2009-10-26 | 2010-07-15 | 2010-06-28 | 118487.28 | 2.218
6744 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ROSCOMMON |  | 04 | 1072014 | Rosscommon County will repave M 76 from Madision St-Artesia Beach Rd | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-11-12 |  | 398714.07 | 1.884
6745 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ROSCOMMON |  | 04 | 1072015 | The Roscommon County Road Commission is resurfacing 0.8 miles of Loxley Road in the community of Houghton Lake to improve the ride quality of the road. | Pavement Improvement | 2010-06-17 | 2010-08-17 | 2010-09-01 | 2010-08-25 | 44289.61 | 0.819
6746 | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073006 | In the city of Saginaw, MDOT will resurface 8.78 miles on M-81 from Indiantown Road easterly to Wadsworth Avenue to improve the driving quality of the roadway. | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2012-12-31 | 2010-07-02 | 1168846.36 | 8.780
6747 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073007 | This pavement project on Ditch Rd Briggs Rd to Sheridan Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-10 | 2010-08-05 | 2010-08-12 | 2010-08-12 | 65000 | 3.972
6748 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073008 | In Thomas Township there is 5.31 miles of resurfacing on Brant Fordney & Ring Roads to improve driving quality by making the road smoother. | Pavement Improvement | 2009-11-10 | 2010-08-04 | 2010-08-11 | 2010-08-11 | 66000 | 4.287
6749 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073009 | In Thomas Township there is 4.18 miles of resurfacing on Fordney & Hemlock Roads to improve driving quality by making the road smoother. | Pavement Improvement | 2009-11-10 | 2010-08-03 | 2010-08-05 | 2010-08-05 | 70000 | 4.188
6750 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073010 | The City of SaginawThomas Township & Saginaw Township is resurfacing 5.33 miles on various locations from River through Midland Road to improve driving quality by making the road smoother. | Pavement Improvement | 2009-11-10 | 2010-08-02 | 2010-08-04 | 2010-08-04 | 80993.12 | 5.131
6751 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SANILAC |  | 10 | 1074006 | This pavement project on West French Line Road over the Elk Creek Bridge in Sanilac County will improve the drive quality and make the road smoother | Bridge Replacement | 2010-04-02 | 2010-05-19 | 2010-07-16 | 2010-07-12 | 357422 | 0.865
6752 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SANILAC |  | 10 | 1074007 | This pavement project in Sandusky on Cambell Road from Industrial Road to Miller Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-01 | 2010-06-22 | 2010-07-31 | 2010-08-09 | 293769.33 | 0.098
6753 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 1075003 | This shoulder paving project on County Road 442 in Schoolcraft County will improve safety. | Pavement Improvement | 2009-10-21 | 2010-06-14 | 2010-09-30 | 2010-09-30 | 94000 | 4.039
6754 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 1075006 | Schoolcraft county will resurface County Road 442 from US-2 to M-149 to make the road smoother and improve the ride quality. | Pavement Improvement | 2009-12-11 | 2010-07-01 | 2010-09-30 |  | 11952 | 6.410
6755 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 1076003 | Almost 3 miles of S Delaney Rd near the city of Owosso in Shiawassee County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 2010-02-19 | 2010-04-26 | 2010-05-29 | 2010-05-25 | 508914 | 2.681
6756 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 1076007 | This pavement project near Ann Arbor on Shiawassee Street from Walnut Street to 100' south of St Mary Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-17 | 2010-06-14 |  | 2010-08-05 | 180000 | 0.120
6757 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 1076008 | This pavement project near Ann Arbor on Shiawassee Street from Walnut Street to 100' south of St Mary Street will improve the drive quality and make the road smoother | Transportation Enhancements | 2010-06-08 | 2010-06-09 | 2010-08-30 | 2010-11-11 | 50000 | 0.202
6758 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 1076009 | 0.26 miles of pavement resurfacing on East Main Street from the Mercer Street to the East City limits of Durand | Pavement Improvement | 2010-06-08 | 2010-06-14 |  | 2010-10-14 | 52000 | 0.258
6759 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077216 | Resurfacing to maintain the pavement condition and improve ride quality of Scott Avenue in Port Huron. | Pavement Improvement | 2010-02-19 | 2010-05-03 | 2010-07-31 | 2010-06-15 | 152704.07 | 0.101
6760 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077223 | Resurfacing to maintain the pavement condition and improve ride quality of Fred W. Moore Highway in St. Clair. | Pavement Improvement | 2010-03-30 | 2010-04-26 | 2010-07-02 | 2010-07-08 | 241538.02 | 0.277
6761 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077227 | This project will improve drainage by replacing a culvert at Ravenswood Road At Michigan Avenue to Huffman Drain | Pavement Improvement | 2010-04-23 | 2010-05-10 | 2010-08-20 | 2010-08-20 | 264882.59 | 0.160
6762 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077229 | This pavement project in St. Clair on St. Clair Highway from Oak Street to Palmer Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-03 | 2010-05-14 | 2010-07-31 | 2010-09-01 | 314607.27 | 0.311
6763 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077230 | Resurfacing to maintain the pavement condition and improve ride quality of Fred W. Moore Highway in St. Clair. | Pavement Improvement | 2010-06-08 | 2010-07-29 | 2010-10-10 | 2010-09-17 | 423922.72 | 0.051
6764 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077247 | Resurface | Pavement Improvement | 2010-11-17 | 2011-05-11 | 2012-05-31 |  | 1100000 | 0.711
6765 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078004 | The St. Joseph County Road Commisssion is installing pavement marking to improve safety on 223 miles of roads throughout the county. | Pavement Improvement | 2010-04-20 | 2010-04-30 | 2011-07-27 | 2010-10-12 | 142091.33 | 8.070
6766 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078006 | The St. Joseph County Road Commisssion will resurface 3 miles of Bent Road from M-216 to Dutch Settlement Road in the northwest corner of the county. This will improve the driving quality by making t | Pavement Improvement | 2009-12-22 | 2010-07-22 | 2010-08-02 | 2010-08-02 | 41760 | 3.048
6767 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078007 | The St. Joseph County Road Commisssion will resurface 7.8 miles of Featherstone Road from M-66 to Engle Road north of Sturgis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-22 | 2010-07-22 | 2010-08-03 | 2010-08-03 | 86117 | 7.790
6768 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078008 | The City of Sturgis will resurface 0.6 miles of North Centerville Road from West Lafayette Road to Haines Boulevard in the city. This will improve the driving quality by making the road smoother. | Other | 2010-04-16 | 2010-04-27 | 2011-07-27 | 2010-06-11 | 125000 | 0.622
6769 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078009 | The St. Joseph County Road Commisssion will resurface 0.5 miles of Big Hill Road from M-12 to Lafayette Road in Sturgis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-01-27 | 2010-03-01 | 2011-07-27 | 2010-08-26 | 130000 | 0.532
6770 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078010 | This pavement project on Spring Street from West Michigan to Millard Street will make the road smoother and improve ride quality | Pavement Improvement | 2010-06-01 | 2010-06-28 | 2011-07-27 | 2010-10-01 | 185000 | 0.181
6771 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 1079006 | The Tuscola County Road Commission will replace the West Cass City Rd bridge over the Allen drain to improve safety and mobility. | Bridge Replacement | 2010-02-01 | 2010-04-05 | 2010-08-28 | 2010-06-25 | 342711 | 0.489
6772 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 1079007 | The Tuscola County Road Commission will resurface 2 miles of Irish Rd from Willard to Birch Run south of the Village of Millington. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-04 | 2010-08-12 | 2010-08-31 | 2010-08-27 | 288453.37 | 2.027
6773 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 1079009 | The community of Caro is resurfacing 0.94 miles of Hooper Street to improve the pavement condition and ride quality of the road. | Pavement Improvement | 2010-05-03 | 2010-07-06 | 2010-09-30 | 2010-08-23 | 100000 | 0.943
6774 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 1079010 | The community of Mayville is resurfacing 0.5 miles of Fulton Street to improve the pavement condition and ride quality of the road. | Pavement Improvement | 2010-06-01 | 2010-06-14 | 2010-08-15 | 2010-07-14 | 90198 | 0.504
6775 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 1080008 | The Van Buren County Road Commisssion is building a paved pathway for 0.33 miles along the Kal-Haven State Trail from 10th Street (Kalamazoo Street) to CR 655 in Bloomingdale for cyclists walkers and | Transportation Enhancements | 2009-12-23 | 2010-05-03 | 2011-07-27 |  | 900000 | 0.333
6776 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 1080009 | MDOT will resurface 1.5 miles of M-40 from St. Joseph Avenue to Power Plant Road in Paw Paw. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-01-19 | 2010-01-19 | 2011-11-22 |  | 2308760.33 | 1.460
6777 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 1080011 | The Van Buren County Road Commisssion will resurface 0.3 miles of 73rd Street from Phoenix Street to the Tractor Supply Store in South Haven. This will improve the driving quality by making the road | Pavement Improvement | 2010-07-20 | 2010-08-16 | 2013-08-07 | 2010-10-22 | 125000 | 0.280
6778 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 1080014 | This project Van Buren County will replace the culbert on CR653/29th St Over North Branch of Paw Paw River to improve drainage and safety. | Bridge Replacement | 2010-04-23 | 2010-07-07 | 2013-08-07 | 2010-08-30 | 164336.25 | 0.219
6779 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081002 | 2.28 miles of nonmotorized path expansion at various location throughout the city of Ann Arbor. This project will enhance nonmotorized and pedestrian mobilty and safety throughout 34 locations throug | Safety/Traffic Management | 2009-12-09 | 2010-08-02 | 2011-05-06 |  | 250000 | 2.278
6780 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | DETROIT,MI | 07 | 1081003 | The Historic Freighthouse in Ypsilant will receive a makeover. | Transportation Enhancements | 2010-03-01 | 2010-03-19 | 2010-05-28 | 2010-07-05 | 270465.81 | 0.000
6781 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW |  | 07 | 1081004 | This pavement project in Milan on Marvin Street from the County Street to Michigan Miller Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-16 | 2010-06-30 | 2010-07-30 | 2010-08-13 | 125000 | 0.362
6782 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081005 | This pavement project in Ann Arbor on Wagner Road from Ann Arbor-Saline Road to Liberty Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 82600 | 2.412
6783 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081006 | This pavement project in Ypsilanti on Textile Road from Deer Creek Drive to Stony Creek Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 34100 | 1.468
6784 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081007 | This pavement project in Ann Arbor on Scio Church Road from Zeeb Road to Tessmer Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 19198.65 | 0.752
6785 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081008 | This pavement project in Ann Arbor on Zeeb Road from Pratt Road to Scio Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 40600 | 0.595
6786 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081009 | This pavement project will improve the drive quality and make the road smoother at four locations in the Ann Arbor area. | Pavement Improvement | 2010-01-12 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 409200 | 1.380
6787 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081010 | This pavement project on Ellsworth from Maple Road to State will make the road smoother and improve ride quality | Pavement Improvement | 2010-01-12 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 387700 | 2.040
6788 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081011 | Washtenaw County will repave Dexter Ann Arbor Road From Kensington to Meadow View in Dexter | Pavement Improvement | 2010-04-01 | 2010-06-14 | 2010-07-26 |  | 100000 | 0.241
6789 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081014 | This pavement project in Washtenaw County on Mansfield Street from Westmoorland Street to Congress Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-04-02 | 2010-09-20 | 2010-11-01 | 502469.15 | 0.321
6790 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081015 | This pavement project in Washtenaw County on College Place from West Cross to Forest will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-04-02 | 2010-08-27 | 2010-09-16 | 204000 | 0.105
6791 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081017 | Ann Arbor will repave Plymouth and Green Roads from Nixon to US-23 & Plymouth to Hubbard | Pavement Improvement | 2010-02-08 | 2010-06-03 | 2010-11-15 |  | 2232914.38 | 1.756
6792 | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | DETROIT,MI | 07 | 1081027 | Historic Preservation | Transportation Enhancements | 2010-08-03 | 2010-08-16 | 2010-10-15 | 2010-10-20 | 124863.42 | 0.000
6793 | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW |  | 07 | 1081038 | Overlay | Pavement Improvement | 2010-09-02 | 2011-04-01 | 2011-12-31 |  | 49377 | 0.500
6794 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081044 | Overlay and Mill | Pavement Improvement | 2010-09-10 | 2011-04-01 | 2011-12-31 |  | 497457.02 | 14.623
6795 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082009 | Detroit is building a mile of paved pathway for cyclists, walkers, and joggers to promote alternative modes of transportation | Transportation Enhancements | 2009-10-26 | 2009-10-26 | 2012-11-15 |  | 1946988.29 | 0.824
6796 | Underway | C950 | Ferryboat | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082012 | This project is for the design of an off-shore wharf to receive ferryboat passengers on the Detroit river at the ferryboat terminal | Other | 2009-04-01 | 2010-01-31 | 2010-12-15 |  | 599205
6797 | Underway | C950 | Ferryboat | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082013 | This project is for the design of a terminal building expansion to receive ferryboat passengers on the Detroit River | Other | 2009-04-01 | 2010-01-19 | 2010-10-01 |  | 210250
6798 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082014 | The City of Romulus will resurface 4.7 miles of Huron River Drive to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2009-11-18 | 2010-09-15 | 2010-09-15 | 643000 | 3.670
6799 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082015 | The City of Dearborn will resurface .7 miles of the Southfield Service Drive SBd to improve driving quality and increase service life | Pavement Improvement | 2009-11-25 | 2010-03-22 | 2010-10-31 | 2010-10-31 | 282787.5 | 0.464
6800 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082016 | The City of Grosse Point Farms will resurface .2 miles of Fisher Road to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2010-06-21 | 2010-10-30 | 2011-08-01 | 99643.95 | 0.213
6801 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082017 | The City of Detroit is resurfacing portions of Dickerson Van Dyke Antoinette. Fourteenth Trumbull Schaeffer Wyoming Southfield Service West Vernor Fullerton Hayes Dequindre and East Forest Roads to im | Pavement Improvement | 2009-11-18 | 2010-04-15 | 2010-11-02 |  | 5103729 | 10.093
6802 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082018 | The City of Romulus will resurface .1 miles of Shook Road to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2009-11-18 | 2010-09-15 | 2010-10-01 | 669683.12 | 0.897
6803 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082019 | The City of Wayne will resurface .6 miles of Newburgh Road to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2009-11-18 | 2010-07-01 | 2010-07-01 | 512208.86 | 0.558
6804 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082020 | The City of Dearborn will resurface .2 miles of the Southfield Service Drive SBd to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2010-03-22 | 2010-10-31 | 2010-10-31 | 148323.91 | 0.180
6805 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082021 | The City of Dearborn will resurface .5 miles of Miller Road to improve driving quality and increase service life | Pavement Improvement | 2010-03-12 | 2010-03-22 | 2010-10-31 | 2010-10-31 | 402000 | 0.502
6806 | Underway | C950 | Ferryboat | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082022 | This project is for the construction of a terminal building expansion to receive ferryboat passengers on the Detroit River | Other | 2009-04-01 | 2010-01-19 | 2010-10-01 |  | 1000000 | 0.129
6807 | Underway | C950 | Ferryboat | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082023 | This project is for the construction of an off-shore wharf to receive ferryboat passengers on the Detroit river at the ferryboat terminal | Other | 2009-04-01 | 2010-01-31 | 2010-12-15 |  | 5305000 | 0.129
6808 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082024 | The City of Grosse Point Farms will resurface .5 miles of Jefferson Avenue to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2010-03-22 | 2010-10-30 | 2011-08-01 | 311942.24 | 0.456
6809 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082025 | The City of Wyandotte will resurface .2 miles of Oak Street in Wyandotte to improve the driving quality and increase the road service life | Pavement Improvement | 2009-11-25 | 2009-11-25 | 2010-10-15 | 2010-10-01 | 206918.13 | 0.225
6810 | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082026 | The City of Detroit will beautify .4 miles of its downtown on Monroe and Brush Streets by building a streetscape | Transportation Enhancements | 2010-03-23 | 2010-04-05 | 2012-09-30 |  | 1489002.77 | 0.401
6811 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082035 | The City of Detroit will rehabilitate the Larned Street over Dequindre Cut bridge to make the bridge last longer | Bridge Replacement | 2010-01-06 | 2010-04-15 | 2011-05-02 |  | 1200000 | 0.100
6812 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082036 | 2 Miles of Five Mile Road in the City of Detroit will be resurfaced to improve driving quality and increase service life | Pavement Improvement | 2010-01-12 | 2010-06-11 | 2010-11-30 | 2010-11-01 | 1300000 | 1.997
6813 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082037 | Wayne County in Canton Township will resurface the Warren Road and Lilley Road intersection to improve the driving quality and increase the road service life | Pavement Improvement | 2010-01-12 | 2010-05-24 | 2010-11-15 | 2010-11-08 | 881000 | 0.012
6814 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082038 | Wayne County will resurface 1.0 Miles of Van Born Road fromTelegraph Road to Monroe Road to improve driving quality and increase service life | Pavement Improvement | 2010-01-12 | 2010-04-28 | 2010-09-30 | 2010-09-28 | 1272440.41 | 1.001
6815 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082040 | Wayne County will replace the Goddard Extension over Merriman Road bridge to improve safety and increase moblility | Bridge Replacement | 2010-01-27 | 2010-01-27 | 2010-11-30 | 2011-06-30 | 1070230.04 | 0.020
6816 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082045 | MDOT will repave US-12 in Wayne County from 28th Street to Rosa Parks to improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-05 | 2010-04-26 | 2011-12-31 |  | 4561259.68 | 1.779
6817 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082046 | MDOT will repave US-12 in Wayne County from Livernois to 28th Street to improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2012-12-31 |  | 2909719.02 | 0.835
6818 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE |  | 13 | 1082048 | This pavement project in Wayne County on Judd from at Haggerty will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-08 | 2010-05-18 | 2010-11-30 | 2011-05-25 | 231808.67 | 0.518
6819 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082050 | This pavement project on Lake Shore Drive from Moross Road to Vernier Road will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-10 | 2010-08-02 | 2010-11-30 |  | 2163906.49 | 4.163
6820 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082052 | This pavement project on Third Street from Vinewood to Northline will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-06-23 | 2010-10-29 | 2011-10-19 | 255410.75 | 0.451
6821 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082053 | This pavement project on Wayne Road Ramps At Michigan Avenue will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-05-11 | 2010-11-30 | 2010-11-08 | 173129.55 | 0.136
6822 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082054 | This pavement project on Edward N. Hines Drive from Ann Arbor Trail to Merriman Road will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-08-23 | 2010-11-30 | 2010-10-27 | 954872.94 | 3.339
6823 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082055 | This pavement project on Middlebelt Road from Cherry Hill Road to Warren in Garden City will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-08-02 | 2010-11-30 | 2011-11-04 | 2504684.12 | 0.968
6824 | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082057 | This pavement project on Joy Road from Inkster to Beech Daly will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-07-19 | 2010-09-30 | 2010-09-17 | 1030039.34 | 0.911
6825 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082058 | This project in Detroit will upgrade the traffic signal at 29 locations on Jefferson Avenue to improve traffic flow and enhance safety. | Safety/Traffic Management | 2010-06-25 | 2010-08-02 | 2010-12-15 |  | 1384609.62 | 2.188
6826 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082129 | "Streetscape improvements 0.29 mi of pavement removal, cold milling, curb and gutter, storm sewer, hot mix asphalt paving, concrete sidewalks, concrete building vault reconstruction, street lighting | Pavement Improvement | 2010-06-21 | 2010-07-15 | 2012-09-30 |  | 1950000 | 0.289
6827 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082204 | Mid-block crossing | Safety/Traffic Management | 2011-06-20 | 2011-06-27 | 2011-09-30 |  | 277357.53 | 0.978
6828 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082205 | Construct concrete median | Safety/Traffic Management | 2011-06-20 | 2011-06-27 | 2011-09-30 |  | 87671 | 0.398
6829 | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082206 | Constuct Concrete median | Safety/Traffic Management | 2011-06-20 | 2011-06-27 | 2011-09-30 |  | 155121 | 0.496
6830 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082208 | Reconstruct | Pavement Improvement | 2010-09-20 | 2010-09-20 | 2013-11-15 |  | 5027105.37 | 6.467
6831 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WEXFORD |  | 02 | 1083006 | This pavement project in Wexford County on Various Roads at Various Locations will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-05 | 2010-08-16 | 2010-08-01 | 2010-09-22 | 364707.22 | 27.243
6832 | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WEXFORD |  | 02 | 1083007 | This pavement project on Boon Road from Mitchell Street to the west will make the road smoother and improve ride quality | Pavement Improvement | 2010-06-15 | 2010-06-21 | 2010-07-01 | 2010-06-29 | 185948.44 | 0.933
6833 | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 1084044 | At various locations in metropolitan Detroit this project will install protective fences and security for power towers to improve safety. | Safety/Traffic Management | 2009-05-11 | 2009-05-11 | 2013-01-31 |  | 2606740 | 0.000
6834 | Underway | C490 | OJT/SS | MICHIGAN | STATEWIDE |  |  | JT10001 | TRAC Pipeline | Other | 2010-05-05 | 2010-05-05 | 2011-09-01 |  | 960584 | 0.004
6835 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | TODD, WADENA |  | Multiple | 09ES001 | Remove and replace pavement on State Highway 10 from Wadena to Staples. Add turn lanes, replace signs, pave shoulders, install rumble strips and lighting and improve pedestrian crossings. | Pavement Improvement | 2009-03-23 | 2009-05-01 | 2009-07-15 | 2009-07-16 | 7312124 | 21.757
6836 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BIG STONE |  | 07 | 09ES002 | Placement of asphalt pavement on State Highway 75 form Graceville to Ortonville. | Pavement Improvement | 2009-04-23 | 2009-05-04 | 2009-07-31 | 2009-07-02 | 5143074 | 19.036
6837 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MILLE LACS |  | 08 | 09ES003 | Remove and replace pavement on State Highway 169 from Princeton to Milaca. | Pavement Improvement | 2009-03-11 | 2009-05-01 | 2009-09-25 | 2009-10-15 | 4163703 | 13.696
6838 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | RICE |  | 02 | 09ES004 | Replace pavement, add new median guardrail and improve water drainage pipes on northbound and southbound lanes of I-35 through Faribault. | Pavement Improvement | 2009-05-04 | 2009-05-11 | 2009-09-11 | 2009-09-22 | 4769068 | 4.875
6839 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES006 | Construct guardrail improvements on State Highways throughout south central and western Minnesota to improve safety. | Safety/Traffic Management | 2009-04-16 | 2009-05-04 | 2009-08-04 | 2009-07-09 | 471228.93 | 78.092
6840 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES007 | Replace guardrail on State Highways throughout southeast Minnesota. | Safety/Traffic Management | 2009-04-17 | 2009-05-11 | 2009-10-01 | 2009-11-10 | 1600639 | 217.325
6841 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MOWER, OLMSTED |  | 01 | 09ES008 | Replace pavement, upgrade guardrail and improve water drainage pipes on eastbound I-90 from Stewartville to 8.6 miles west. | Pavement Improvement | 2009-04-17 | 2009-05-04 | 2009-07-05 | 2009-06-24 | 2108897 | 8.633
6842 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | FREEBORN |  | 01 | 09ES009 | Replace pavement on I-90, upgrade guardrail and improve water drainage pipes from Albert Lea to Alden. | Pavement Improvement | 2009-03-23 | 2009-05-01 | 2009-09-30 | 2010-07-14 | 17117366 | 10.045
6843 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WINONA |  | 01 | 09ES010 | Replace existing pavement, upgrade guardrail and improve water drainage pipes on westbound I-90 from east of State Highway 74 to west of State Highway 43. | Pavement Improvement | 2009-06-10 | 2009-06-22 | 2009-08-28 | 2009-08-24 | 4511492 | 14.099
6844 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS, TODD |  | Multiple | 09ES011 | Install cable median barrier on I-94 from Sauk Centre to the Douglas/Todd County Line. | Safety/Traffic Management | 2009-03-23 | 2009-05-01 | 2009-09-20 | 2011-07-25 | 1493013.22 | 11.955
6845 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES012 | Install hazardous curve signs at various locations on State Highways 1, 38, 65, and 217 in Itasca, Koochiching and St Louis Counties in Northeast Minnesota. | Safety/Traffic Management | 2009-04-23 | 2009-05-11 | 2009-06-21 | 2009-05-21 | 45740 | 48.909
6846 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WINONA |  | 01 | 09ES013 | Replace existing pavement, upgrade guardrail and improve water drainage pipes on eastbound and westbound I-90 from Nadine to Dakota. | Pavement Improvement | 2009-04-27 | 2009-07-13 | 2009-10-23 | 2009-10-08 | 3016818 | 4.996
6847 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SIBLEY |  | 07 | 09ES014 | Remove and replace pavement on State Highway 93 from Liqueur to Highway 169. | Pavement Improvement | 2009-04-15 | 2009-05-11 | 2009-08-07 | 2009-07-15 | 437312 | 0.830
6848 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | KANDIYOHI |  | 07 | 09ES015 | Resurface Highway 23 from County Road 31 near New London to County Road 6 near Paynesville in Kandiyohi County. | Pavement Improvement | 2009-03-23 | 2009-05-01 | 2009-10-12 | 2009-10-09 | 1202117 | 6.652
6849 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | AITKIN |  | 08 | 09ES016 | Resurfacing and safety improvements on State Highway 65 from State Highway 210 in McGregor to south of Big Sandy River Bridge. | Pavement Improvement | 2009-06-10 | 2009-06-17 | 2009-08-21 | 2009-09-03 | 5161594 | 11.395
6850 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | LAKE |  | 08 | 09ES017 | Skid prevention in Silver Cliff and Lafayette Tunnels on Highway 61 north of Two Harbors. | Safety/Traffic Management | 2009-04-24 | 2009-04-27 | 2009-05-26 | 2009-05-02 | 78722 | 3.720
6851 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | CARLTON |  | 08 | 09ES018 | Install plantings to create a living snow fence to prevent blowing snow from crossing two bridges on I-35 South of Carlton. | Transportation Enhancements | 2009-03-19 | 2009-06-01 | 2009-07-01 | 2009-09-21 | 77971 | 0.000
6852 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 09ES019 | Reinforced concrete pavement on State Highway 169 from South of County Road 5 to west of County Road 67 near Chisholm where underground mining had occurred. | Pavement Improvement | 2009-06-04 | 2009-06-08 | 2010-06-25 | 2009-10-26 | 7799584 | 0.740
6853 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BELTRAMI, CASS, STATEWIDE |  | Multiple | 09ES020 | Replace traffic signal at State Highway 197 and Ridgeway Avenue in Bemidji and at State Highway 2 and Grant Utley Avenue in Cass Lake. | Safety/Traffic Management | 2009-07-07 | 2009-08-10 | 2009-08-15 | 2009-09-29 | 317685 | 0.000
6854 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | PENNINGTON, MARSHALL |  | 07 | 09ES021 | Resurface State Highway 1 from Warren to Thief River Falls. | Pavement Improvement | 2009-03-11 | 2009-05-01 | 2009-10-01 | 2010-02-28 | 6632798 | 26.896
6855 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | BELTRAMI |  | 07 | 09ES022 | Lowering roadway by removal of bridges over abandoned railroad tracks along with additional safety improvements on State Highway 2 in Bemidji. | Pavement Improvement | 2009-07-23 | 2009-07-23 | 2009-09-30 | 2009-09-30 | 2251659 | 0.863
6856 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS, WRIGHT |  | 06 | 09ES023 | Repair pavement on I-94 from Clearwater to Monticello. | Pavement Improvement | 2009-03-18 | 2009-05-01 | 2009-08-19 | 2009-08-08 | 6312466 | 47.868
6857 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS |  | 06 | 09ES024 | Remove and replace pavement and paint bridge at County Road 143 and I-94. Remove and replace pavement and paint bridge at County road 186 and I-94. | Bridge Improvement | 2009-03-18 | 2009-05-01 | 2009-10-15 | 2009-09-24 | 1592142 | 48.949
6858 | Completed | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | OTTER TAIL, GRANT |  | 07 | 09ES025 | Concrete resurfacing and rest area preservation on I-94 north of Fergus Falls to Grant County line. | Pavement Improvement | 2009-05-04 | 2009-05-11 | 2010-06-18 | 2010-06-10 | 8762711 | 20.797
6859 | Underway | C200 | Highway Infrastructure Investment Grant | MINNESOTA | MOWER |  | 01 | 09ES026 | Replace west bound exit ramp bridge on I-90 into Austin. | Bridge Replacement | 2009-05-08 | 2009-07-17 | 2010-09-01 |  | 5075891 | 19.229
6860 | Underway | C220,C200 | Highway Infrastructure Investment Grant | MINNESOTA | NICOLLET |  | 01 | 09ES029 | Replace utilities, reconstruct pavement and install signal and pedestrian crossing on State Highway 169 in St. Peter. | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2010-07-25 |  | 16422468 | 1.594
6861 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | JACKSON |  | 01 | 09ES031 | Parking lot and sidewalk improvements at two rest areas on I-90 near Jackson. | Pavement Improvement | 2009-09-11 | 2009-09-21 | 2009-09-27 | 2009-10-10 | 344287.42 | 0.556
6862 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHIPPEWA |  | 07 | 09ES033 | Resurface Highway 7 from Montevideo to Clara City in Chippewa County. | Pavement Improvement | 2009-03-18 | 2009-05-01 | 2009-08-28 | 2009-09-18 | 8897248 | 15.238
6863 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES034 | Guardrail replacement at various locations in Southwest Minnesota | Safety/Traffic Management | 2009-06-30 | 2009-06-30 | 2010-06-30 | 2009-10-23 | 921855 | 33.993
6864 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | REDWOOD |  | 07 | 09ES035 | Resurface Highway 68 from Milroy to Wabash in Redwood County. | Pavement Improvement | 2009-03-11 | 2009-08-01 | 2009-11-02 | 2009-10-20 | 2219889 | 15.322
6865 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO, ISANTI |  | 08 | 09ES036 | Remove and replace pavement on State Highway 95 from east of Cambridge to the Isanti/Chisago County Line, including culvert replacement. | Pavement Improvement | 2009-03-11 | 2009-05-01 | 2009-08-07 | 2009-07-22 | 2771586 | 9.669
6866 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | DULUTH-SUPERIOR (WI) | 08 | 09ES039 | Resurface State Highway 194 from northwest of Anderson Road to northwest of Masada Ave in the Duluth Heights neighborhood of Duluth. | Pavement Improvement | 2009-05-06 | 2009-05-26 | 2009-07-15 | 2009-07-02 | 1572086 | 1.857
6867 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | DULUTH-SUPERIOR (WI) | 08 | 09ES040 | Roadway Resurfacing, curb & gutter removal and replacement, sidewalks, lighting and safety improvements on Highway 23 from East of 130th Street to North of County Road 3 in the Gary and Fond Du Lac ne | Pavement Improvement | 2009-06-05 | 2009-06-15 | 2009-09-30 | 2009-10-20 | 3469216 | 3.881
6868 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 09ES041 | Pavement reconstruction and bridge rehabilitation on State Highway 53 from north of Highway 194 to north of Highway 33. | Pavement Improvement | 2009-06-05 | 2009-06-11 | 2009-10-30 | 2010-06-12 | 12582156 | 13.632
6869 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES042 | Rest area sign replacement at five locations on Highway 2. | Safety/Traffic Management | 2009-06-01 | 2009-07-06 | 2009-08-28 | 2009-07-16 | 115134.4 | 0.000
6870 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ITASCA |  | 08 | 09ES043 | Resurfacing on Highway 2 west of Deer River from County Road 18 to west of Highway 6, and on Highway 6 north of Deer River. | Pavement Improvement | 2009-04-16 | 2009-06-01 | 2009-10-30 | 2010-06-30 | 4031685 | 16.960
6871 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MILLE LACS |  | 08 | 09ES046 | Remove and replace pavement on Highway 169 from Rum River rest area to south of Omani. | Pavement Improvement | 2009-04-08 | 2009-05-01 | 2009-07-24 | 2009-08-13 | 4788587 | 7.686
6872 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MILLE LACS |  | 08 | 09ES047 | Replace bridge on Highway 23 over the Rum River in Milaca. | Bridge Replacement | 2009-04-20 | 2009-06-01 | 2009-11-13 | 2009-11-13 | 1692300 | 0.598
6873 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ISANTI |  | 08 | 09ES048 | Replace bridge on Highway 95 over the Rum River west of Cambridge. | Bridge Replacement | 2009-04-20 | 2009-05-01 | 2009-11-13 | 2009-11-06 | 1410631 | 0.042
6874 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | KANABEC |  | 08 | 09ES049 | Remove and replace bridge on State Highway 107 over the Snake River in Garston. | Bridge Replacement | 2009-04-20 | 2009-06-01 | 2009-11-13 | 2009-11-04 | 1322178 | 0.034
6875 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES050 | Improve road safety and operations by coordinating 85 traffic signals in Big Lake, Brainerd, Baxter, Elk River, Monticello, St. Cloud and St. Michael. | Safety/Traffic Management | 2009-08-26 | 2009-08-26 | 2011-04-27 | 2011-04-27 | 413094
6876 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DOUGLAS |  | 07 | 09ES052 | Install a traffic signal at I-94 and State Highway 27 in Alexandria. | Safety/Traffic Management | 2009-04-10 | 2009-07-01 | 2009-09-07 | 2009-08-21 | 227909 | 0.000
6877 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | OTTER TAIL |  | 07 | 09ES053 | Install a traffic signal at State Highway 210 and Redwood Lane in Fergus Falls. | Safety/Traffic Management | 2009-08-19 | 2009-09-12 | 2009-10-28 | 2010-05-20 | 380084 | 0.000
6878 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | WILKIN |  | 07 | 09ES054 | Install railroad gates and signals at State Highway 9 west of Nashua. | Safety/Traffic Management | 2009-06-10 | 2009-08-03 | 2010-06-15 | 2010-04-30 | 115403 | 0.000
6879 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEVENS |  | 07 | 09ES055 | Install railroad gates, signals cantilevers at State Highway 28 southwest of Morris. | Safety/Traffic Management | 2009-05-06 | 2009-08-03 | 2010-05-12 | 2010-04-09 | 263338 | 0.001
6880 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | FARIBAULT, FREEBORN |  | 01 | 09ES059 | Remove and replace pavement on I-90 between Alden and State Highway 22. | Pavement Improvement | 2009-06-10 | 2009-06-16 | 2009-09-30 | 2009-11-17 | 3831474 | 7.111
6881 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | ROCK |  | 01 | 09ES060 | Build new state entrance sign at the South Dakota border on I-90 at the Beaver Creek rest area. | Transportation Enhancements | 2009-04-28 | 2009-08-01 | 2009-10-01 | 2009-11-10 | 66806 | 0.000
6882 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MORRISON |  | 08 | 09ES061 | Plant living snow fence on Highway 371 in Crow Wing and Morrison Counties. | Transportation Enhancements | 2009-04-08 | 2009-05-01 | 2009-07-01 | 2009-06-18 | 119698 | 1.340
6883 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | DULUTH-SUPERIOR (WI) | 08 | 09ES063 | Preserve the historic Aerial lift bridge over the Duluth Shipping Canal on Park Point, replacing lead based paint, structural steel and concrete elements. | Transportation Enhancements | 2009-08-19 | 2009-09-22 | 2011-03-20 | 2011-04-06 | 4900000 | 0.100
6884 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | MINNEAPOLIS-ST. PAU, MN | 08 | 09ES064 | Resurfacing, curb and drainage repairs on the Rice Lake Road from Arrowhead Road to Masada Avenue in Duluth. | Pavement Improvement | 2009-07-21 | 2009-08-06 | 2009-09-18 | 2009-09-18 | 1178846 | 2.330
6885 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | AITKIN |  | 08 | 09ES066 | Replace bridge on County Road 14 northeast of Highway 65, north of McGregor in Aitkin County. | Bridge Replacement | 2009-06-18 | 2009-07-01 | 2009-10-23 | 2010-07-07 | 1180574 | 0.100
6886 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HUBBARD |  | 08 | 09ES067 | Replacement of bridge on County Road 9 over the Schoolcraft River, about 10 miles southwest of Bemidji in Hubbard County. | Bridge Replacement | 2009-07-01 | 2009-06-16 | 2009-10-16 | 2009-09-28 | 416683.9 | 0.100
6887 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | KITTSON |  | 07 | 09ES068 | Replacement of bridge on County Road 1 over the North Branch of Two Rivers, north of Hillock in Kittson County. | Bridge Replacement | 2009-06-16 | 2009-06-22 | 2009-11-01 | 2009-11-04 | 798862.3 | 0.100
6888 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BELTRAMI |  | 07 | 09ES069 | Rehabilitate surface, new curb and gutter, replace sewers and fix water lines on Irvine Ave from 3rd St. to State Highway 197 in Bemidji. | Pavement Improvement | 2009-06-30 | 2009-07-06 | 2009-11-01 | 2010-05-26 | 1453985.36 | 1.400
6889 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MARSHALL |  | 07 | 09ES070 | West of Grille on County Road 7, replace bridge with a box culvert in Marshall County. | Bridge Replacement | 2009-06-03 | 2009-08-05 | 2009-08-07 | 2009-08-25 | 65352.5 | 0.050
6890 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MARSHALL |  | 07 | 09ES071 | Replace timber bridge on County Road 15 over the Snake River with two culverts, West of Warren in Marshall County. | Bridge Replacement | 2009-07-17 | 2009-08-03 | 2009-09-04 | 2009-09-23 | 537484.97 | 0.100
6891 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | MORRISON |  | 08 | 09ES072 | Reconstruction of Lindbergh Drive from State Highway 27 to the North city limits in Little Falls. | Pavement Improvement | 2009-08-21 | 2009-08-24 | 2009-11-15 | 2009-11-02 | 894237 | 0.997
6892 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | ISANTI |  | 08 | 09ES073 | Replace bridge on County Road 6 over Stanch field Creek West of Grandee in Isanti County. | Bridge Replacement | 2009-08-17 | 2009-08-26 | 2009-12-25 | 2009-11-20 | 369849 | 0.100
6893 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MORRISON |  | 08 | 09ES074 | Reconstruct County Road 203 beginning at Highway 10 and add additional asphalt surface on County Road 203 to County Road 2 in Morrison County, south of Motley. | Pavement Improvement | 2009-05-27 | 2009-06-15 | 2009-10-10 | 2009-09-02 | 626164 | 3.980
6894 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BECKER |  | 07 | 09ES075 | Replace existing bridge with three culverts on County Highway 7, north of Lake Park in Becker County. | Bridge Replacement | 2009-08-31 | 2009-08-28 | 2009-09-09 | 2009-09-17 | 296085.97 | 0.100
6895 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DOUGLAS |  | 07 | 09ES076 | Resurface County Road 7 from the north city limits of Brandon to the south city limits of Millersville in Douglas County. | Pavement Improvement | 2009-05-29 | 2009-05-29 | 2009-07-31 | 2009-06-19 | 813899 | 6.730
6896 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SWIFT |  | 07 | 09ES077 | Replace bridge with two culverts on County Road 33 over Mud Creek, North East of Murdock in Swift County. | Bridge Replacement | 2009-07-01 | 2009-07-13 | 2009-08-15 | 2009-08-10 | 244039.21 | 0.040
6897 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | TRAVERSE |  | 07 | 09ES078 | Place asphalt pavement and gravel shoulders on County Road 6 from the South Dakota State line to Highway 75, north of Wheaton in Traverse County. | Pavement Improvement | 2009-06-16 | 2009-06-18 | 2009-09-15 | 2009-08-09 | 1441828 | 1.390
6898 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | STEELE |  | 01 | 09ES079 | Replace Cedar Avenue bridge over Maple Creek in Owatonna; also replace two railroad crossing signals. | Pavement Improvement | 2009-07-15 | 2009-08-04 | 2010-07-16 | 2009-11-25 | 1365638 | 0.100
6899 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | GOODHUE |  | 02 | 09ES080 | Reconstruct County Highway 1 in Red Wing, including bridge replacement, new pavement, drainage pipe replacement, and new storm sewer in Goodhue County. | Pavement Improvement | 2009-06-09 | 2009-06-09 | 2009-11-30 | 2010-07-08 | 1784727 | 1.160
6900 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | JACKSON |  | 01 | 09ES081 | Replace bridge on County Road 20 southwest of Kabana in Jackson County. | Bridge Replacement | 2009-07-16 | 2009-07-27 | 2009-10-02 | 2009-12-08 | 326354.34 | 0.100
6901 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASECA |  | 01 | 09ES082 | Replace bridge on County Road 3 over the Liqueur River south of Janesville in Waseca County. | Bridge Replacement | 2009-07-21 | 2009-07-23 | 2009-11-15 | 2009-11-05 | 609994 | 0.100
6902 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASECA |  | 01 | 09ES083 | Replace bridge with culvert to carry Loco Creek under County Road 3, northeast of Janesville in Waseca County. | Bridge Replacement | 2009-07-21 | 2009-09-21 | 2009-10-30 | 2009-11-03 | 328827.47 | 0.110
6903 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | NOBLES |  | 01 | 09ES084 | Resurface County Road 1 from Brewster to Kin brae in Nobles County. | Pavement Improvement | 2009-06-04 | 2009-08-24 | 2009-09-21 | 2009-09-18 | 1521460.06 | 8.310
6904 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | BLUE EARTH |  | 01 | 09ES085 | Construct a new bridge on a new roadway on County Road 12 over the DM&E RR in east Mankato in Blue Earth County | New Bridge Construction | 2009-08-19 | 2009-08-24 | 2010-09-24 | 2010-11-11 | 3073031 | 0.570
6905 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHIPPEWA |  | 07 | 09ES086 | Replace bridge on County Road 32, southeast of the City of Milan in Chippewa County. | Bridge Replacement | 2009-06-08 | 2009-07-27 | 2009-10-23 | 2009-11-05 | 476489 | 0.100
6906 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | LYON |  | 07 | 09ES087 | Replace bridge on County Road 3 over the south branch of the Yellow Medicine River, south of Minnesota in Lyon County. | Bridge Replacement | 2009-06-19 | 2009-06-24 | 2009-11-15 | 2009-09-01 | 305095.31 | 0.050
6907 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MCLEOD |  | 07 | 09ES088 | Replace timber bridge on County Road 7 over High Island County Road south of Stewart in McLeod County. | Bridge Replacement | 2009-06-01 | 2009-06-15 | 2009-08-24 | 2009-09-10 | 317742.12 | 0.100
6908 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | LINCOLN |  | 07 | 09ES089 | Resurface County Road 6 from South County Line to Highway 14, 3 miles south of Tyler. Resurface County Road 9 from County Road 1 to County Road 2, West of Verdi. Resurface County Road 11 from County R | Pavement Improvement | 2009-05-21 | 2009-05-19 | 2009-06-16 | 2009-06-05 | 792677.8 | 4.010
6909 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RENVILLE |  | 07 | 09ES090 | Replace bridge on County Road 9 over Chetamba Creek in Renville County. | Bridge Replacement | 2009-06-24 | 2009-06-24 | 2009-09-30 | 2009-10-02 | 332116.25 | 0.100
6910 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | YELLOW MEDICINE |  | 07 | 09ES091 | Replace bridge on County Road 3 over Lac Qui Parle River in Yellow Medicine County. | Bridge Replacement | 2009-06-10 | 2009-08-10 | 2009-08-21 | 2009-11-10 | 209872 | 0.100
6911 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ITASCA |  | 08 | 09ES092 | Complete reconstruction, including utilities on 7th Avenue Southeast from 17th Street Southeast to 33rd Street Southeast in Grand Rapids. | Pavement Improvement | 2009-06-03 | 2009-06-04 | 2010-07-15 | 2009-10-15 | 1498036.33 | 1.535
6912 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BELTRAMI |  | 07 | 09ES093 | Resurface County Road 23 from County Highway 29 to County Highway 32 in Beltrami County. | Pavement Improvement | 2009-06-18 | 2009-06-22 | 2009-07-10 | 2009-07-10 | 776124.27 | 4.820
6913 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CLEARWATER |  | 07 | 09ES094 | Resurfacing County Road 5 from Clearbrook to the Red Lake Reservation line in Clearwater County. | Pavement Improvement | 2009-06-19 | 2009-06-22 | 2009-07-09 | 2009-07-09 | 1240119.69 | 8.830
6914 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | TODD |  | 07 | 09ES095 | Resurfacing on County Road 2 from Highway 28 to County Road 11 northeast of Sauk Center in Todd County. | Pavement Improvement | 2009-06-18 | 2009-06-25 | 2009-09-11 | 2009-08-21 | 866884.64 | 10.600
6915 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SHERBURNE |  | 06 | 09ES096 | Replace bridge on County Road 5 over St. Francis River south of Sherburne County Road 3. | Bridge Replacement | 2009-06-04 | 2009-06-04 | 2009-10-02 | 2009-09-16 | 469472 | 0.110
6916 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | WRIGHT |  | 06 | 09ES097 | Reconstruction and widening including curb and gutter and recreational trail on Jamison Ave from County Road 119 to County Road 18 in St. Michael. | Pavement Improvement | 2009-06-22 | 2009-06-23 | 2009-10-16 | 2009-11-05 | 2136106 | 1.451
6917 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | OTTER TAIL |  | 07 | 09ES098 | Resurface and add shoulders to County Road 1 from Sophus Anderson Rd to County Road 10 east of Fergus Falls in Ottertail County. | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2009-09-30 | 2009-09-02 | 1206813.06 | 5.080
6918 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | OTTER TAIL |  | 07 | 09ES099 | Replace bridge over Otter Tail River on Concord Street in Fergus Falls. | Bridge Replacement | 2009-06-30 | 2009-07-06 | 2010-06-26 | 2010-05-24 | 776855 | 0.100
6919 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | YELLOW MEDICINE |  | 07 | 09ES100 | Resurface County Road 8 from Highway 67 to County Road 5, north of Clarkfield in Yellow Medicine County. | Pavement Improvement | 2009-06-03 | 2009-07-08 | 2009-09-18 | 2009-08-27 | 907551.7 | 3.990
6920 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | KANDIYOHI, RENVILLE |  | 07 | 09ES101 | Resurface County Road 2, south of County Road 77 to Highway 7 in Renville and Kandiyohi Counties. | Pavement Improvement | 2009-05-28 | 2009-06-30 | 2010-08-01 | 2009-11-12 | 2254661.99 | 1.920
6921 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 09ES103 | Resurfacing on St. Louis County Road 4 from Arrowhead Road to Martin Road in Duluth. | Pavement Improvement | 2009-06-26 | 2009-07-29 | 2009-10-09 | 2009-09-23 | 1838992.37 | 3.420
6922 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS |  | 06 | 09ES104 | Reconstruction and widening of Pinecone road from County Road 120 to County Road 134 in St. Cloud, including roundabouts. | Pavement Improvement | 2009-08-17 | 2009-08-20 | 2010-05-30 | 2009-11-12 | 1509238 | 0.600
6923 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS |  | 06 | 09ES105 | Extending 28th Ave from State Highway 23 to County Road 137 in the City of Waite Park. | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2010-07-16 | 2010-09-03 | 2433666 | 1.300
6924 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | OLMSTED | ROCHESTER | 01 | 09ES106 | Replace 4th Street bridge over Bear Creek in Rochester. | Bridge Replacement | 2009-08-26 | 2009-09-01 | 2010-10-15 | 2010-11-15 | 2742179.39 | 0.100
6925 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES107 | Replace deteriorated landscaping at the state entry signs at the US/Canada border on Highway 61 near Grand Portage, and the Minnesota/Wisconsin border on I-535 and Highway 2 in Duluth. | Transportation Enhancements | 2009-04-16 | 2009-06-01 | 2011-11-15 | 2010-03-23 | 132579 | 0.000
6926 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | FREEBORN |  | 01 | 09ES122 | Replacing landscaping around Entering and Leaving Minnesota Signs on I-35 at the Iowa Border near Albert Lea. | Transportation Enhancements | 2009-05-13 | 2009-08-01 | 2009-10-01 | 2010-07-21 | 60642 | 0.000
6927 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 08 | 09ES124 | Plant living snow fence on I-35 at County Road 17 south of North Branch. | Transportation Enhancements | 2009-04-24 | 2009-04-24 | 2010-11-01 | 2010-11-01 | 79895 | 0.000
6928 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 08 | 09ES125 | Remove and replace pavement on I-35 north of North Branch; repair drainage and replace lighting and pavement at the Goose Creek Rest Area. | Pavement Improvement | 2009-07-08 | 2009-07-09 | 2009-10-30 | 2009-11-11 | 9096643 | 7.113
6929 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 09ES126 | Reconstruct State Highway 5 from south of State Highway 36 to Manning Avenue. Drainage improvements were made through this section and west to I-694. | Pavement Improvement | 2009-04-24 | 2009-08-04 | 2009-10-03 | 2010-05-30 | 2066476 | 7.414
6930 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA, HENNEPIN | MINNEAPOLIS-ST. PAU, MN | Multiple | 09ES127 | Replace lighting on Highway 100 from 50th in Edina to Excelsior Boulevard in St. Louis Park. Replace lighting on Highway 100 from I-494 to Vernon Avenue in Edina. Replace lighting on I-35W from Cliff | Safety/Traffic Management | 2009-04-24 | 2009-06-01 | 2010-05-20 | 2009-11-02 | 2296429 | 5.137
6931 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA, STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES128 | Remove and replace 2 traffic signals on State Highway 13 in Burnsville. | Safety/Traffic Management | 2009-05-22 | 2009-08-01 | 2009-11-06 | 2009-11-06 | 493780 | 0.262
6932 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 09ES130 | Rebuild the cable median barrier on I-94 from I-494 in Maple Grove to the Crow River. | Safety/Traffic Management | 2009-04-24 | 2009-06-01 | 2009-09-07 | 2009-09-09 | 1239274 | 10.873
6933 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES131 | Remove and replace pavement at the north junction of I-35E and I-35W, including extending a merge lane on I-35. | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-10-30 | 2009-10-30 | 5793909 | 25.670
6934 | Underway | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES132 | Plant landscaping on I-494 from State Highway 5 to I-394. | Other | 2009-05-28 | 2009-08-01 | 2012-10-30 |  | 573664 | 7.522
6935 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MINNESOTA | POLK |  | 07 | 09ES133 | Replace the bridge over the Red River and approaches on County Road 9 in Polk County. | Bridge Replacement | 2009-09-11 | 2009-09-02 | 2010-10-01 | 2011-10-05 | 6763057 | 0.010
6936 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | CASS |  | 08 | 09ES134 | Resurface Sucker Bay Road in Cass County and install Rail Road crossing signal and gates at BNSF Rail Road. | Safety/Traffic Management | 2010-01-15 | 2010-01-20 | 2010-09-30 | 2010-10-15 | 300000
6937 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | CLAY | FARGO-MOORHEAD (ND) | 07 | 09ES135 | Restore landscaping at state entry sign in Moorhead. | Transportation Enhancements | 2009-06-04 | 2009-08-01 | 2009-10-19 | 2009-11-05 | 65879 | 0.300
6938 | Underway | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES136 | Construct State Highway 610 from County Road 81 to State Highway 169 in Maple Grove and Brooklyn Park. | Pavement Widening | 2009-05-14 | 2009-08-01 | 2012-06-01 |  | 28440763 | 3.226
6939 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES137 | Remove and replace traffic signals and lighting on state highways and interstate throughout the Twin Cities region. | Safety/Traffic Management | 2009-05-27 | 2009-07-01 | 2009-12-28 | 2009-12-03 | 1927016 | 25.444
6940 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES138 | Add a traffic lane to the ramp from westbound I-494 to westbound US 212. | Pavement Improvement | 2009-07-23 | 2009-08-17 | 2009-09-23 | 2009-11-08 | 1275463 | 0.758
6941 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES139 | Separate existing westbound and eastbound I-494 interchange ramps as they merge onto I-35E southbound. | Safety/Traffic Management | 2009-07-23 | 2009-08-07 | 2009-09-21 | 2009-09-12 | 836447 | 0.386
6942 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES140 | Install Fiber Optic cable throughout the Twin Cities region on state highways and interstate. | Safety/Traffic Management | 2009-05-27 | 2009-08-01 | 2010-10-31 | 2010-10-31 | 1246688
6943 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES141 | Install pavement markings throughout the Twin Cities region on state highways and interstate. | Pavement Improvement | 2009-05-27 | 2009-08-01 | 2009-11-15 | 2010-07-30 | 1140008 | 14.581
6944 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 09ES143 | Remove and replace lighting on US 169 from I-494 to I-94. | Safety/Traffic Management | 2009-05-27 | 2009-08-01 | 2010-06-19 | 2010-05-01 | 4525919 | 15.652
6945 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES145 | In Rosemount and Inver Grove Heights, resurface road and repair four bridges on Highway 52 from County Road 42 to Highway 55 in Dakota County. | Pavement Improvement | 2009-10-06 | 2009-10-13 | 2010-06-04 | 2010-05-01 | 3882696 | 3.613
6946 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 09ES146 | Remove and replace pavement on State Highway 95 from Stillwater 16 to State Highway 97. | Pavement Improvement | 2009-06-22 | 2009-09-08 | 2010-06-04 | 2010-06-01 | 4971163 | 15.320
6947 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES147 | Installation of changeable message signs in the Minneapolis-St. Paul Metro area. | Safety/Traffic Management | 2009-09-03 | 2009-09-09 | 2010-05-13 | 2010-05-13 | 1470917 | 0.000
6948 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 09ES148 | Storm tunnel restoration on I-35E at Shepard Road in St. Paul. | Pavement Improvement | 2009-10-21 | 2009-10-21 | 2010-05-31 | 2010-05-12 | 1592665 | 0.475
6949 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA, RAMSEY | MINNEAPOLIS-ST. PAU, MN | 06 | 09ES149 | Resurfacing of US 10 from State Highway 65 in Blaine to North of junction with I-35W in Shoreview. | Pavement Improvement | 2010-03-04 | 2010-04-19 | 2010-09-03 | 2010-09-17 | 8684334 | 2.975
6950 | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES155 | Landscaping along I-94 from I-494 in Maple Grove to Brooklyn Blvd in Brooklyn Park, Hennepin County. | Transportation Enhancements | 2009-08-03 | 2009-08-03 | 2012-10-31 |  | 210494 | 5.510
6951 | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES156 | Landscape Highway 212 interchange at State Highway 101 and at Carver County Road 17 (Powers Blvd) in Chanhassen in Carver County. | Transportation Enhancements | 2009-08-03 | 2009-08-03 | 2012-10-30 |  | 236776 | 0.000
6952 | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES157 | Landscape Highway 212 interchange at Carver County Road 10 (Engler Blvd) and Carver County Road 11 in Chaska, Carver County. | Transportation Enhancements | 2009-08-03 | 2009-08-03 | 2012-10-30 |  | 358078 | 0.000
6953 | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES158 | Landscape Highway 212 at Hennepin County Road 4 and Dell Road in Eden Prairie. | Transportation Enhancements | 2009-08-03 | 2009-08-03 | 2012-10-30 |  | 201631 | 0.000
6954 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 08 | 09ES159 | Reconstruct interchange of Highway 95 and I-35 in North Branch, Chisago County. | Pavement Improvement | 2009-11-16 | 2009-11-19 | 2010-11-20 | 2010-11-13 | 3765286 | 1.045
6955 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES161 | In Rosemount and Inver Grove Heights of Dakota County, resurface, revise signals and improve accessibility on 6 miles of Highway 3 from County Road 42 to Highway 149 in northbound and southbound lanes | Pavement Improvement | 2010-03-03 | 2010-05-10 | 2010-06-30 | 2010-11-04 | 2898337 | 6.341
6956 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES162 | Replace concrete, replace lighting, and add acceleration lane to I-94 from the Crow River in Rogers to I-494 in Maple Grove. | Pavement Improvement | 2010-02-17 | 2010-05-03 | 2010-09-24 | 2010-11-11 | 2636508 | 4.245
6957 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES163 | Resurface shoulders on Highway 252 from I-694 to Highway 610 in Brooklyn Park, to accommodate buses. Project also replaced curb and gutter and updated pedestrian facilities. | Safety/Traffic Management | 2009-10-14 | 2010-02-01 | 2010-10-01 | 2010-10-15 | 2848375 | 4.456
6958 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES165 | Replace lighting on Highway 62 from State Highway 212 in Eden Prairie to Gleason Road in Edina. | Safety/Traffic Management | 2009-10-19 | 2010-02-01 | 2010-05-28 | 2010-12-09 | 827898 | 1.212
6959 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES166 | Guardrail upgrades at various locations around the east Minneapolis-St. Paul Metro area. | Safety/Traffic Management | 2009-09-12 | 2010-05-01 | 2010-07-17 | 2010-07-12 | 288884
6960 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES167 | Guardrail upgrades at various locations around the west Minneapolis-St. Paul Metro area. | Safety/Traffic Management | 2009-08-24 | 2010-04-01 | 2010-07-03 | 2010-05-11 | 232723
6961 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT |  | 02 | 09ES168 | Preserve historic bridge in downtown Shakopee as non-motorized Minnesota River crossing in Scott County. | Transportation Enhancements | 2009-10-26 | 2010-02-01 | 2010-09-17 | 2011-08-01 | 5557690
6962 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA | MINNEAPOLIS-ST. PAU, MN | 06 | 09ES169 | Reconstruct interchange at I-35 and County Road 14. | Pavement Improvement | 2009-12-04 | 2010-01-26 | 2011-06-30 | 2011-06-30 | 6825000 | 1.041
6963 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 09ES171 | Construct interchange at Highway 7 & Wooddale Avenue including pedestrian walkway and trail in St. Louis Park. | New Bridge Construction | 2009-09-25 | 2009-09-29 | 2010-11-01 | 2010-11-10 | 3465000 | 0.129
6964 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | CLAY | FARGO-MOORHEAD (ND) | 07 | 09ES173 | Reconstruct 20th Street between 12th Avenue South and 24th Avenue South replacing pavement, curb and gutter and storm sewer. | Other | 2009-08-26 | 2009-08-28 | 2009-11-13 | 2010-07-02 | 1098380 | 0.420
6965 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | CLAY | FARGO-MOORHEAD (ND) | 07 | 09ES174 | Repair and repaint bridge over the Red River on Center Avenue in Moorhead. | Bridge Improvement | 2009-09-21 | 2009-10-05 | 2010-07-01 | 2010-08-18 | 909806 | 0.100
6966 | Underway | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 09ES175 | Construct asphalt pavement on the Mesabi Trail system from the Giants Ridge recreation area near Biwabik to State Highway 135. Including pedestrian bridge over Narrows between Sabin Lake and Wynne. | Transportation Enhancements | 2009-12-22 | 2010-04-26 | 2010-09-15 |  | 1407835
6967 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES176 | Realign and widen County Road 10 from County Road 101 to West of Peony Lane in Maple Grove. | Pavement Widening | 2009-09-02 | 2009-09-03 | 2010-11-15 | 2011-07-01 | 3064000 | 0.610
6968 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES179 | Constructing a paved surface on a new alignment for County Road 21 from County Road 42 in Prior Lake to County Road 16 in Shakopee in Scott County. | Pavement Improvement | 2009-11-12 | 2009-11-16 | 2011-11-11 | 2011-09-20 | 7324000 | 4.761
6969 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES001 | Construct pedestrian and bike trail connections to Anderson Memorial Trail in Arden Hills. | Transportation Enhancements | 2010-03-24 | 2010-03-29 | 2010-06-25 | 2010-09-03 | 288326
6970 | Completed | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES002 | Provide a wider pedestrian path from the Cedar Lake Bike Trail system to the new downtown Minneapolis ballpark. | Transportation Enhancements | 2009-11-05 | 2009-11-06 | 2010-05-31 | 2009-11-30 | 695067
6971 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER |  | 02 | 10ES005 | Construct a pedestrian and bike Dakota Rail Trail from East County Line to City of Mayer in Carver County. | Transportation Enhancements | 2010-03-26 | 2010-04-06 | 2010-12-31 | 2011-08-10 | 550680
6972 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES006 | Construct Sam Morgan Trail, a pedestrian and bike trail, from I-35E to State Highway 5 in St. Paul. | Transportation Enhancements | 2010-05-26 | 2010-06-01 | 2010-08-30 | 2010-09-10 | 448800
6973 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN |  | 05 | 10ES007 | Improve the Bryant Avenue Pedestrian Bridge over Minnehaha Creek in Minneapolis. | Transportation Enhancements | 2010-05-05 | 2010-05-05 | 2010-09-02 | 2010-12-02 | 382000
6974 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY, WASHINGTON | MINNEAPOLIS-ST. PAU, MN | Multiple | 10ES009 | Provide bridge for Gateway State Trail users over Highway 120 in the Cities of North St. Paul and Oakdale. | Transportation Enhancements | 2010-03-11 | 2010-05-17 | 2010-08-22 | 2010-12-10 | 1257903
6975 | Completed | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES010 | Construct a pedestrian and bike trail along County Road 10 from Brooklyn Blvd to State Highway 100 in Brooklyn Center. | Transportation Enhancements | 2010-03-17 | 2010-04-19 | 2010-10-15 | 2010-08-15 | 2000000
6976 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES011 | Construct turn lanes on County Road 30 at the Compost Site Access in Mayer. | Safety/Traffic Management | 2010-05-07 | 2010-05-10 | 2010-07-31 | 2010-07-09 | 96000 | 0.200
6977 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES012 | Install a signal at intersection of State Highway 41 and 2nd Street and concrete median at 1st, 3rd, and 5th streets in Chaska. | Safety/Traffic Management | 2010-02-25 | 2010-05-24 | 2010-09-03 | 2010-10-22 | 485272 | 0.215
6978 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON |  | 06 | 10ES015 | Construct bridge and retaining walls for County Road 83 on the overpass of I-35 in Washington County. | Pavement Improvement | 2010-04-06 | 2010-04-12 | 2011-06-01 | 2010-11-22 | 5000000 | 0.200
6979 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA |  | 05 | 10ES016 | Reconstruct pedestrian bridge crossing State Highway 65 and approaches in the vicinity of 49th Avenue in Columbia Heights. | Bridge Replacement | 2010-04-12 | 2010-04-12 | 2011-06-15 | 2010-10-22 | 1925678
6980 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES017 | Construct intersection control at Mendota Heights Road at Vistation Drive and at Lake Drive in Mendota Heights. | Safety/Traffic Management | 2010-02-16 | 2010-06-14 | 2011-07-01 | 2010-08-20 | 310000 | 0.690
6981 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES018 | Resurface and stripe for bike lanes on 61st Avenue from Main Street to Central Avenue in Fridley. | Pavement Improvement | 2010-04-20 | 2010-05-03 | 2010-06-18 | 2010-07-30 | 262500 | 1.270
6982 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES019 | Resurface four sections of county roads in Carver County: County Road 10, County Road 15 and County Road 17. | Pavement Improvement | 2009-09-10 | 2009-11-01 | 2009-11-01 | 2009-11-16 | 856368 | 0.330
6983 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES020 | Reconstruct State Highway 25 from White Street to State Street in Watertown. | Pavement Improvement | 2010-03-23 | 2010-05-10 | 2010-07-31 | 2010-07-09 | 704000 | 0.230
6984 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES021 | Construct overpass from I-94 westbound to Highway 101 northbound over South Diamond Lake Road in Rogers. | New Bridge Construction | 2010-03-11 | 2010-04-06 | 2010-10-29 | 2010-11-16 | 3780000 | 0.348
6985 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 10ES023 | Minor road improvements including curb repair, utility repair, and resurfacing at various locations of Public Road 101 in Woodbury. | Pavement Improvement | 2010-02-02 | 2010-05-20 | 2010-09-30 | 2010-09-13 | 1250250 | 2.660
6986 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES024 | Resurface 140th Street West from 134th Street to Guild Avenue and Garden View Drive from 140th Street to Walnut Street. This project will also include spot repair of deteriorated storm sewer, sanitar | Pavement Improvement | 2010-06-11 | 2010-06-14 | 2010-09-16 | 2010-08-27 | 561000 | 1.201
6987 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES025 | Rehabilitate bridge on 42nd Ave. North/37th Avenue northeast from Lyndale Avenue north to St. Anthony Parkway in Minneapolis. | Bridge Improvement | 2010-03-08 | 2010-04-05 | 2011-08-31 | 2010-08-24 | 9539619 | 0.331
6988 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES026 | Upgrade 56 existing signal systems in Coon Rapids, including new lenses, pedestrian lights with count down timers and revised pedestrian signs. | Safety/Traffic Management | 2009-10-07 | 2009-11-23 | 2010-03-01 | 2010-04-26 | 180000
6989 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES027 | Reconstruct County Road 73 from County Road 42 to Bonaire Path. | Pavement Improvement | 2010-04-02 | 2010-04-07 | 2010-10-07 | 2010-08-28 | 2146506.35 | 1.000
6990 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES028 | Campus Drive/26th Avenue from County Road 61 to Sycamore Lane in Plymouth: Resurface from County Road 61 to Teakwood Lane and reconstruct from Teakwood lane to Sycamore Lane. | Pavement Improvement | 2010-02-23 | 2010-05-07 | 2010-06-10 | 2010-06-04 | 346560 | 0.395
6991 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES029 | Resurface and stripe Hadley Avenue from Hudson Boulevard North to 11th Street North in Oakdale. | Pavement Improvement | 2010-02-26 | 2010-04-26 | 2010-05-06 | 2010-05-10 | 273766.1 | 1.118
6992 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES030 | Resurface Holyoke/Highview Avenue from Heritage Drive to Dodd Boulevard in Lakeville. | Pavement Improvement | 2009-10-06 | 2009-10-07 | 2010-08-01 | 2009-11-20 | 812121.7 | 1.252
6993 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES031 | Street lighting replacement, reconstruction of sidewalk on Shoreline Boulevard and Commerce Boulevard from east city limits to west city limits in Mound. | Safety/Traffic Management | 2010-05-25 | 2010-06-01 | 2010-10-15 | 2010-11-01 | 630000 | 2.040
6994 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES032 | Resurfacing of Terrance Road from County Road 8 to Sanburnol Drive and Able Street from County Road 8 to County Road 10. | Pavement Improvement | 2010-04-15 | 2010-04-26 | 2010-10-08 | 2010-10-25 | 1468480 | 1.160
6995 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES033 | Construct right lane and bypass lane on State Highway 244 at Old Wildwood Road in Mahtomedi. | Safety/Traffic Management | 2010-02-16 | 2010-05-03 | 2010-07-30 | 2010-06-10 | 156000 | 0.051
6996 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 10ES034 | Resurfacing and storm sewer work on Washington Avenue from State Highway 36 to Orleans in Stillwater. | Pavement Improvement | 2010-02-16 | 2010-05-19 | 2010-06-30 | 2010-06-17 | 265968.28 | 0.529
6997 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES035 | Reconstruct the pavement, improve and construct additional storm sewer, replace failing water main, complete spot repair of sanitary sewer, replace portions of curb and gutter and widen portions of ex | Pavement Improvement | 2009-10-28 | 2010-04-12 | 2011-07-01 | 2010-10-08 | 778723 | 0.490
6998 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES036 | Construct a pedestrian bridge over Highway 169 and trail connection from Appolossa Ave to Vierling Drive on Fuller Street in Shakopee. | Transportation Enhancements | 2010-01-22 | 2010-05-26 | 2010-07-01 | 2010-08-20 | 700000
6999 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES037 | Construct two trail bridges over State Highway 7 and County Road 92 and connection of paved regional trail between bridges and the Carver County/Hennepin County Line. | Transportation Enhancements | 2010-03-03 | 2010-03-03 | 2010-08-16 | 2011-07-29 | 2717408
7000 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA |  | 02 | 10ES038 | Reconstruct Dakota County Road 96 from West of 11th Avenue to State Highway 3, with paved shoulders and right turn lanes at intersections. | Pavement Improvement | 2009-10-19 | 2009-10-23 | 2010-08-01 | 2010-07-02 | 1677105 | 0.490
7001 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES039 | Construction of South Frontage Road from County Road 5 to County Road 3 and South Street from US 169 to O'Brien Parkway in Belle Plaine. | Pavement Improvement | 2010-03-11 | 2010-03-18 | 2011-07-11 | 2010-09-03 | 1555923 | 0.200
7002 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES040 | Install new traffic control signal system at the intersection of County Road 42 and McKenna Road in Prior Lake. | Safety/Traffic Management | 2009-12-14 | 2010-04-09 | 2010-07-01 | 2010-05-05 | 154486.51 | 0.020
7003 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 10ES041 | Roadway resurfacing and drainage improvements on US 2 west of Duluth. | Pavement Improvement | 2009-09-29 | 2009-10-07 | 2010-07-15 | 2010-07-17 | 3677037 | 14.556
7004 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | AITKIN |  | 08 | 10ES042 | Replace a deficient and deteriorated bridge located north of Aitkin on County Highway 1 in Aitkin County. | Bridge Replacement | 2009-11-18 | 2010-04-05 | 2010-10-11 | 2010-08-12 | 869880 | 0.240
7005 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MINNESOTA | SIBLEY |  | 07 | 10ES043 | Upgrade railroad from Green Isle to Gaylord. | Safety/Traffic Management | 2010-03-03 | 2010-05-11 | 2010-07-31 | 2010-09-23 | 2675000
7006 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | PINE |  | 08 | 10ES044 | Replace failed piers on closed St Croix Valley railroad bridge over Snake river in Pine County. | Bridge Improvement | 2009-10-05 | 2009-10-05 | 2010-01-31 | 2010-06-16 | 1030026
7007 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES045 | Reconstruct County Road D from Flandrau Street to White Bear Avenue in Ramsey County including, dedicated turn lanes, and traffic signals. | Pavement Improvement | 2009-12-02 | 2010-04-19 | 2010-10-15 | 2010-09-29 | 2449882 | 0.560
7008 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | MARSHALL |  | 07 | 10ES046 | Replace bridge on County Road 5 over the Tamarac River in Stephen in Marshall County. | Bridge Replacement | 2009-12-29 | 2010-04-12 | 2010-11-20 | 2010-09-17 | 1115117.5 | 0.080
7009 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES047 | Curb ramps, sidewalk, pedestrian crossings on State Highway 47 from I-35W to 27th Avenue Northeast in Minneapolis. | Transportation Enhancements | 2010-02-08 | 2010-06-21 | 2010-08-01 | 2010-07-30 | 437563 | 2.811
7010 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES048 | Curb ramps, sidewalk, pedestrian crossings on State Highway 5 from Davern St. in St. Paul to McKnight Road in Maplewood and on US 61 from State Highway 5 to Wheelock Parkway in St. Paul. | Transportation Enhancements | 2010-02-09 | 2010-04-14 | 2010-08-15 | 2010-09-14 | 1191786 | 11.470
7011 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 10ES049 | Minneapolis-St. Paul metrowide upgrades to comply with the Americans with Disabilities Act. | Safety/Traffic Management | 2010-03-17 | 2010-05-03 | 2010-07-15 | 2010-07-30 | 795332 | 16.583
7012 | Completed | C490 | OJT/SS | MINNESOTA | STATEWIDE |  |  | 10ES050 | Provide Commercial Drivers License training and certification for women and minorities. | Other | 2009-09-22 | 2009-12-15 | 2010-09-06 | 2010-11-30 | 286812
7013 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SIBLEY |  | 07 | 10ES051 | Resurface Sibley County Road 2 from County Road 7 to Gibbon north. | Pavement Improvement | 2010-06-09 | 2010-07-01 | 2010-08-20 | 2010-10-12 | 2744704.85 | 0.210
7014 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | WADENA |  | 08 | 10ES052 | Replace bridge on County Road 2 over the Patridge River in Wadena County. | Bridge Replacement | 2010-01-04 | 2010-06-07 | 2010-09-01 | 2010-09-03 | 352680 | 0.133
7015 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES053 | Resurface and update existing guardrail and drainage systems on I-94 from the Crow River in Rogers to I-494 in Maple Grove. | Pavement Improvement | 2010-02-08 | 2010-04-12 | 2010-10-29 |  | 17705371 | 7.798
7016 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | FILLMORE |  | 01 | 10ES054 | Resurfacing of Root River Trail from Fountain to Lanesboro. | Transportation Enhancements | 2010-03-29 | 2010-06-07 | 2010-07-30 | 2010-07-28 | 700000
7017 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BLUE EARTH |  | 01 | 10ES055 | Construct New Roadway On County Road 12 from County Highway 26 to County Highway 3 including County Highway 3 intersection in Mankato. | New Construction | 2010-05-19 | 2010-05-20 | 2010-11-01 | 2011-11-04 | 2000000 | 6.654
7018 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES056 | Change lane configuration on northbound to westbound 35E/694 Ramp. | Safety/Traffic Management | 2010-01-13 | 2010-06-01 | 2010-06-21 | 2010-06-15 | 133515 | 0.000
7019 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES057 | US 61 from Cannon St to 4th St in Hastings - replace pavement and install Americans with Disabilities Act pedestrian improvements. | Pavement Improvement | 2010-02-18 | 2010-05-17 | 2010-07-23 | 2010-08-24 | 822185 | 2.027
7020 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES058 | Pedestrian & bike trail pavement replacement from Minnehaha Avenue to Century Avenue in Maplewood. | Transportation Enhancements | 2010-04-30 | 2010-05-17 | 2010-09-16 | 2011-06-09 | 1291544 | 1.336
7021 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES059 | 5 separate Paving ramp meter bypass lanes at 5 separate locations on State Highway 100 from the south limits of Robbinsdale to France Avenue North. | Pavement Improvement | 2010-01-20 | 2010-07-19 | 2010-08-27 | 2010-08-27 | 541407 | 0.792
7022 | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 10ES060 | Metrowide - Put in new LED lamps and refurbish control room video wall. | Safety/Traffic Management | 2010-01-20 | 2010-02-03 | 2010-05-17 | 2010-05-17 | 669614
7023 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES061 | Design and build of interchange and over pass of State Highway 13 from State Highway 169 to just east of Louisiana Avenue. | New Bridge Construction | 2011-03-30 | 2011-05-10 | 2012-06-15 |  | 4319117.1 | 0.972
7024 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN |  | 03 | 10ES062 | Resurface both bridges, westbound off ramp over Light Rail Transit and City Street and over I35W in Minneapolis on I-94. | Bridge Improvement | 2010-03-04 | 2010-06-21 | 2010-08-19 | 2010-08-19 | 1405126.71 | 0.169
7025 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES063 | Modify ramps and widen two bridges on I-694 at I-35W in New Brighton and Arden Hills. | Pavement Improvement | 2009-11-20 | 2010-02-01 | 2010-10-11 | 2010-10-22 | 2713667 | 0.436
7026 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 10ES065 | Unbonded concrete overlay, guardrail, rehabilitate bridges, cable median barrier, drainage improvements on I-694 from I-94 to 50th Street. | Pavement Improvement | 2010-03-17 | 2010-04-19 | 2010-10-01 | 2010-10-21 | 13395746 | 4.939
7027 | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 10ES066 | Resurface Highway 61 from Highway 10 to St. Paul Park Road in Cottage Grove and St. Paul Park. | Pavement Improvement | 2010-06-10 | 2010-06-14 | 2010-10-15 |  | 17323825 | 8.373
7028 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 10ES069 | Permanent repairs to failing sheet piling at the Port of Duluth. | Other | 2010-04-13 | 2010-05-25 | 2011-06-20 | 2010-11-03 | 1595090
7029 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES070 | Replace pavement, drainage, shoulder reconstruction on I-94 From State Highway 280 to Western Avenue in St. Paul. | Pavement Improvement | 2010-04-28 | 2010-05-10 | 2010-08-20 | 2010-10-25 | 10900606 | 4.338
7030 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES071 | North of Cannon Falls on US 52 replace existing RR signals and add advance warning signs. | Safety/Traffic Management | 2009-11-23 | 2009-11-23 | 2009-12-30 | 2010-01-26 | 285193 | 0.500
7031 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RICE |  | 02 | 10ES072 | Replace bridge over Falls Creek on County Road 23 north of State Highway 60. | Bridge Replacement | 2010-04-21 | 2010-05-19 | 2010-08-27 | 2010-08-12 | 363816 | 0.090
7032 | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | LE SUEUR, RICE |  | 02 | 10ES074 | Pavement replacement on State Highway 60 from State Highway 13 to State Highway 21. | Pavement Improvement | 2009-12-29 | 2010-04-01 | 2010-10-29 | 2010-11-03 | 3697823 | 15.064
7033 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CROW WING |  | 08 | 10ES075 | On County Road 20 from North Ahrens Hill Rd to County Highway 49 in Crow Wing Co. Reconstruct to urban standards that include grading, surfacing, storm sewer & slope reinforcement. | Pavement Improvement | 2010-04-07 | 2010-04-19 | 2010-09-03 | 2010-08-30 | 1913731 | 0.935
7034 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO |  | 08 | 10ES076 | Overly State Highway 243 from State Highway 95 to the St. Croix River and also rehabilitate the St. Croix River Bridge and approaches. | Pavement Improvement | 2010-01-12 | 2010-03-01 | 2010-07-31 | 2010-07-28 | 685352
7035 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | CASS |  | 08 | 10ES077 | Resurface State Highway 84 from State Highway 371 to County Road 2, including upgrading pedestrian ramps in Pine River. | Transportation Enhancements | 2010-03-25 | 2010-04-26 | 2010-05-27 | 2010-05-20 | 150672.38 | 0.346
7036 | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | AITKIN |  | 08 | 10ES078 | Replace sidewalks and pedestrian ramps to meet the Americans with Disabilities Act requirements. | Transportation Enhancements | 2010-04-20 | 2010-05-03 | 2010-05-28 | 2010-06-03 | 210044 | 0.440
7037 | Completed | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | DULUTH-SUPERIOR (WI) | 08 | 10ES079 | Restoration of Lester River Bridge on State Highway 61 between 60th and 61st Avenues in East Duluth. | Transportation Enhancements | 2010-06-10 | 2010-06-14 | 2010-10-01 | 2010-09-05 | 100000 | 0.132
7038 | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | WRIGHT |  | 06 | 10ES081 | Resurface and replace deteriorating curbs and gutters on State Highway 25 from Interstate 94 to the Mississippi river in Monticello. | Pavement Improvement | 2010-06-15 | 2010-08-01 | 2010-10-15 | 2010-12-14 | 792826 | 0.851
7039 | Underway | C200 | Highway Infrastructure Investment Grant | MINNESOTA | OLMSTED | ROCHESTER | 01 | 10ES082 | Repair median and resurface pavement on State Highway 14 from State Highway 52 to Marion Road in Rochester. Improve intersection of State Highway 14 and County Road 36; revise signals at 3rd Avenue SE | Pavement Improvement | 2011-03-30 | 2011-05-02 | 2011-09-02 |  | 679937.68 | 3.185
7040 | Underway | C490 | OJT/SS | MINNESOTA | STATEWIDE |  |  | 10ES083 | Provide heavy construction training for women and minorities. | Other | 2010-06-23 | 2010-06-28 | 2011-06-30 |  | 739200
7041 | Underway | C490 | OJT/SS | MINNESOTA | STATEWIDE |  |  | 10ES084 | Provide Roads Opportunities and Diversity Success training program. | Other | 2010-09-15 | 2011-09-15 |  |  | 173232
7042 | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO |  | 08 | 10ES085 | Reconstruct pavement on County Road 15 from south of 240th Street to south of 253rd Street in Chisago city. | Pavement Improvement | 2010-09-15 | 2010-09-20 | 2011-06-24 | 2011-09-01 | 2837597.65 | 1.080
7043 | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO |  | 08 | 10ES086 | Pavement preservation and safety improvements to Interstate 35 north of State Highway 8 to State Highway 95 in North Branch. | Pavement Improvement | 2010-11-18 | 2011-05-08 | 2011-07-25 |  | 9529596 | 15.416
7044 | Underway | C200 | Highway Infrastructure Investment Grant | MINNESOTA | REDWOOD |  | 07 | 10ES087 | Restoration of Historic Retaining wall and Guardrail on State Highway 19 in Redwood County. | Transportation Enhancements | 2010-08-09 | 2011-02-01 | 2011-09-16 |  | 310300 | 0.031
7045 | Underway | C220,C250 | Highway Infrastructure Investment Grant | MINNESOTA | CROW WING |  | 08 | 10ES088 | Construct dewatering system to allow repair of the Historic Garrison Concourse’s overlook wall along Trunk Highway 169 in Garrison. | Transportation Enhancements | 2010-08-27 | 2010-09-01 | 2011-11-30 |  | 374540 | 0.000
7046 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | ATTALA |  | 02 | 0004017 | "This project will resurface and extend the life of the pavement on two sites in Attala county. The first site 25.6 miles in length on Vaiden French Camp Road just south of French Camp and the other | Pavement Improvement | 2009-07-20 | 2009-08-20 | 2010-02-11 | 2009-11-10 | 1183400 | 31.000
7047 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0012024 | The city of Batesville will install traffic signals and make other improvements at various locations. MS Hwy 6 at Lakewood/Power Dr.; MS Hwy 6 at Keating/Woodland Rd.; and MS Hwy 6 at US Hwy 51. This | Safety/Traffic Management | 2010-02-11 | 2010-02-11 | 2010-12-31 |  | 255255 | 0.066
7048 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 0013040 | In Rankin county the city of Brandon resurface Crossgates Drive from Crossgates Blvd. east 1000 feet, resurface Marquette Road from Highway 80 to Region 8 Building, resurface North College Street from | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-02-23 | 490044 | 0.196
7049 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | COPIAH |  | 02 | 0015029 | This project will resurface and extend the life of the pavement on Carter Hill Road from Old Port Gibson Road to Dentville Road and on Browns Wells Road from Sylvarena Road to 0.7 miles south of Highw | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-08-31 | 2009-11-23 | 456620 | 12.800
7050 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0018026 | The county of Forrest will resurface Monroe Rd, 42 Bypass to Travis Rd, Elks Lake Road, Hwy 98 to Hwy 49, Glendale ve/Eatonville Rd to Monroe Rd to I-59. This project will make the road smoother and | Pavement Improvement | 2010-03-01 | 2010-03-09 | 2010-05-05 | 2010-05-13 | 650906 | 15.008
7051 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | NOXUBEE |  | 03 | 0023071 | This project will resurface and extend the life of the pavement on US 45 from the Kemper County Line to Brooksville in Noxubee county. | Pavement Improvement | 2009-04-10 | 2009-06-01 | 2010-07-06 | 2010-07-13 | 11987698 | 22.188
7052 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0024041 | This project will construct additional lanes on US 45 from Carson Raod to 4 miles south of US 82 in Lowndes county. | New Construction | 2010-11-12 | 2011-01-19 | 2012-09-28 |  | 5395447 | 6.500
7053 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 0025033 | The city of Clinton will replace 4 bridges: Kickapoo Road over Bogue Chitto Creek, Clinton-Tennin Road over Straight Fence Creek, McRaven Road over Smith creek, and Magnolia Road over Branch-Bogue Chi | Bridge Replacement | 2009-12-23 | 2009-12-23 | 2010-12-31 | 2011-04-18 | 1722106 | 0.000
7054 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE |  | 01 | 0025065 | This project will resurface and extend the life of the pavement for approximately 8 miles on US Highway 45 between New Wren and the Lee County Line, Monroe county. | Pavement Improvement | 2009-07-09 | 2009-09-22 | 2010-03-30 | 2010-05-03 | 3508915 | 7.233
7055 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 0025068 | The county of Hinds will resurface Siwell Road from Raymond Road to McCluer Road, resurface Terry Road from Siwell Road to Gary Road, resurface West Northside Drive from I-20 to Norrell Road, resurfa | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-23 | 2011-02-23 | 1487257 | 7.592
7056 | Underway | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | HOLMES |  | 02 | 0026007 | This project will replace a bridge on Old Highway 49 over Tchula Lake near the town of Tchula, Holmes county. | Bridge Replacement | 2010-03-15 | 2010-03-16 | 2011-01-27 |  | 816866 | 0.160
7057 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS |  | 02 | 0027012 | The town of Bolton will resurface Bolton-Brownsville Road from I-20 South 1300 feet. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2011-06-30 |  | 128713 | 1.166
7058 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | ALCORN |  | 01 | 0028014 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas on the Alcorn County Welcome Center, Alcorn county. | Transportation Enhancements | 2009-10-08 | 2011-03-03 | 2010-07-16 | 2011-05-02 | 186700 | 0.000
7059 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | ITAWAMBA |  | 01 | 0029027 | This project will replace a bridge over Cummings Creek on Cummings Street north of Fulton, Itawamba county. | Bridge Replacement | 2010-02-12 | 2010-02-16 | 2010-09-18 | 2011-05-18 | 666900 | 0.300
7060 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | PASCAGOULA-MOSS POINT | 04 | 0031086 | This project will widen, add turn lanes and resurface US 90 from SR 57 to the West Pascagoula River Bridge in Jackson county. | Pavement Improvement | 2009-08-06 | 2009-08-10 | 2010-08-31 | 2011-03-01 | 10799800 | 3.230
7061 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON |  | 04 | 0031144 | This project will construct walking trails, parking, landscaping, and lighting to connect with the multi use path on the Bay St. Louis Bridge, Harrison county. | Transportation Enhancements | 2010-03-11 | 2010-03-11 | 2010-12-31 | 2011-01-21 | 1351000 | 0.413
7062 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON |  | 04 | 0031145 | This project will construct walking trails, parking, landscaping, and lighting to connect with the multi use path for the Biloxi Bay Bridge, Jackson county. | Transportation Enhancements | 2010-03-11 | 2010-03-11 | 2010-12-31 | 2011-01-21 | 329500 | 0.299
7063 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 0031147 | The city of Pass Christian will install street lighting along US 90 from Market Street to Davis Avenue. This project will improve traffic operations and safety. | Safety/Traffic Management | 2010-03-03 | 2010-03-03 | 2010-12-31 | 2011-05-03 | 128541 | 0.315
7064 | Underway | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 0031148 | The city of Gulfport will install street lighting along US 90 from Cowan Road to Debuys Road. This project will improve traffic and safety. | Safety/Traffic Management | 2010-05-01 | 2010-05-28 | 2010-12-31 |  | 796118 | 1.585
7065 | Underway | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | MARSHALL |  | 01 | 0047320 | This project will reconstruct and add new pavement for 0.9 miles on the Chickasaw Trail Industrial Park Access Road approx. 6 miles north of Byhalia, Marshall county. | Pavement Improvement | 2009-11-23 | 2009-11-23 | 2010-05-17 |  | 242645 | 1.000
7066 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0054032 | This project will replace the bridge over McLvor Canal on Mt. Level Road in Panola county. This project is located approx. 4 miles west of Sardis. | Bridge Replacement | 2009-07-02 | 2009-07-02 | 2009-12-22 | 2010-07-15 | 712698 | 0.200
7067 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0054034 | This project will replace the bridge over Bobo Creek on Benson Herron Road 1.5 miles southwest from the town of Courtland, Panola county. | Bridge Replacement | 2009-07-02 | 2009-07-02 | 2009-11-08 | 2010-04-29 | 295986 | 0.190
7068 | Underway | C200,C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 0061035 | The county of Rankin will resurface Spillway Road from Mill Creek Bridge to Eagle Point, Overlay Thomasville Road from Monterey Road east for 2.2 miles, Old Hwy 49 from Cleary Road north for 2.87 mile | Pavement Improvement | 2010-02-26 | 2010-02-26 | 2010-06-30 |  | 1324847 | 8.904
7069 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | SHARKEY |  | 02 | 0063010 | This project will resurface various roads in the town of Anguilla, Sharkey county. | Pavement Improvement | 2009-05-04 | 2009-05-05 | 2010-09-10 | 2009-08-04 | 102200 | 5.600
7070 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ITAWAMBA |  | 01 | 0063036 | This project will upgrade US 78 to interstate standards from the east end of the Tenn-Tom Bridge to the Alabama State Line. This includes shoulder paving, guardrail upgrade, rumble strips and fencing. | Pavement Improvement | 2009-04-09 | 2009-04-20 | 2009-08-28 | 2009-08-21 | 3878121 | 13.050
7071 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LEE |  | 01 | 0063037 | This project will upgrade approximately 5 miles of US Highway 78 in Tupelo to interstate standards McCullough Boulevard @ Belden to US 45. This includes shoulder paving, guardrail upgrade, rumble stri | Pavement Improvement | 2009-06-11 | 2009-06-26 | 2009-09-16 | 2009-11-06 | 2976283 | 4.657
7072 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | ITAWAMBA |  | 01 | 0063038 | This project will add new landscaping to the US 78 Tremont Welcome Center on the North Bound Lane in Itawamba county. | Transportation Enhancements | 2010-09-09 | 2010-09-14 | 2011-06-24 | 2011-06-16 | 100000 | 0.000
7073 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | TALLAHATCHIE |  | 02 | 0068100 | This project will resurface and extend the life of the pavement on 14 different roads in the town of Webb, Tallahatchie county: Main Street Extension, 5th Street, Deere Avenue, Plow Street, John Stree | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2009-12-29 | 2010-02-16 | 47000 | 2.900
7074 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON |  | 02 | 0070017 | The city of Canton will resurface North Old Canton Road from the City Limits to US 51; Walnut Street from Dinkins Street to Peace Street; and West North Street from Canal Street to MLK Drive. This pro | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2010-12-31 | 2011-04-08 | 352421 | 1.591
7075 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ALCORN |  | 01 | 0071074 | This project will resurface and extend the life of the pavement for approximately 15 miles on US Highway 72 between the Tippah County Line and State Route 2, Alcorn county. | Pavement Improvement | 2009-07-09 | 2009-08-07 | 2009-11-30 | 2010-05-20 | 6927600 | 14.778
7076 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | COAHOMA |  | 02 | 0080026 | The city of Clarksdale will resurface Florence Avenue, Martin Luther King, Jr. Boulevard, New Africa Road, Oakridge Road, and Maple Street. This project will make the road smoother and extend the life | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-12-31 |  | 742361 | 4.492
7077 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | COVINGTON |  | 03 | 0082093 | This project will resurface and extend the life of the pavement on approximately 18 miles of US Highway 49 northbound lanes from Seminary to the Simpson County Line in Covington county. | Pavement Improvement | 2009-04-09 | 2009-04-20 | 2009-09-29 | 2009-11-04 | 3872279 | 16.782
7078 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | SIMPSON |  | 03 | 0082094 | This project will resurface and extend the life of the pavement for approximately 6 miles of US Highway 49 beginning 15.9 miles north of the Covington county line then running north for 5.6 miles near | Pavement Improvement | 2009-08-06 | 2009-08-13 | 2009-11-25 | 2010-03-08 | 2588614 | 5.611
7079 | Underway | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | SIMPSON |  | 03 | 0082095 | This project will resurface and extend the life of the pavement for approximately 16 miles on US Highway 49 beginning at the Covington county line and continuing north, Simpson county. Northbound lane | Pavement Improvement | 2009-08-06 | 2009-08-11 | 2010-12-31 |  | 3611542 | 15.892
7080 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | YAZOO |  | 02 | 0084061 | This project will resurface and extend the life of the pavement on US Highway 49 between the Madison County Line and Bentonia in Yazoo county. | Pavement Improvement | 2009-04-08 | 2009-05-12 | 2009-08-07 | 2009-09-24 | 2377574 | 5.005
7081 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LEFLORE |  | 02 | 0085028 | This project will resurface and extend the life of the pavement for approximately 11 miles on US 49 from US 82 to SR 8, Leflore County. | Pavement Improvement | 2009-08-06 | 2009-08-06 | 2009-12-07 | 2010-03-16 | 3907605 | 15.650
7082 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON |  | 04 | 0101133 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-10 East rest area, Jackson county. | Transportation Enhancements | 2010-03-11 | 2010-03-11 | 2010-03-31 | 2011-04-27 | 1011100 | 0.000
7083 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PONTOTOC |  | 01 | 0102008 | The city of Pontotoc will resurface Industrial Drive/South Industrial Circle east of First National Bank on Hwy 15 to intersection of Bolton Street. This project will make the road smoother and extend | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 | 2011-03-17 | 169993 | 0.951
7084 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0110023 | The city of Columbus will resurface Military Rd between 18th & 3rd; 7th between Bluecutt and 18th; Willowbrook between 5th & 7th; MS 12 between Lehmberg & US 82; Island between W Br. End & Dead End; W | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2011-06-30 | 2011-05-12 | 716183 | 4.396
7085 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0110024 | This project will stripe and resurface Military Road between Ridge Rd. and Hwy 82 and Bell Ave/ Airline Rd. between Hwy 69 and S. 25th St./Martin Luther King Jr. Drive in the city of Columbus, Lowndes | Pavement Improvement | 2010-03-31 | 2010-03-31 | 2011-06-30 |  | 383785 | 0.000
7086 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0113076 | This project will resurface and extend the life of the pavement for approximately 9 miles on US Highway 82 between near Military Road in Columbus and the Alabama State Line, Lowndes county. | Pavement Improvement | 2009-07-09 | 2009-07-20 | 2009-10-13 | 2009-11-06 | 3334125 | 8.249
7087 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | ALCORN |  | 01 | 0120015 | The city of Corinth will resurface and stripe Fulton Drive from Linden to Shiloh Rd; Fulton Drive from Hwy 72 south to city limits; and Alcorn Drive from Hwy 72 to Linden Street. This project will mak | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-04-26 | 2010-05-20 | 589662 | 1.635
7088 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | PEARL RIVER |  | 04 | 0124040 | This project will replace four bridges over Hobolochito Creek on Burned Bridge-Pine Grove Road west of Picayune, Pearl River county. | Bridge Replacement | 2009-08-24 | 2009-08-24 | 2010-04-06 | 2011-02-09 | 2199700 | 0.900
7089 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | WALTHALL |  | 03 | 0142060 | This project will resurface and extend the life of the pavement on approximately 6 miles of U.S. Highway 98 between the Pike County Line and Tylertown in Walthall county. | Pavement Improvement | 2009-04-09 | 2009-04-13 | 2009-08-12 | 2009-09-24 | 3061304 | 6.081
7090 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | WALTHALL |  | 03 | 0142061 | This project will resurface and extend the life of the pavement on approximately 5 miles of US Highway 98 from the west end of the Tylertown bypass to the east end of the Tylertown bypass, Walthall co | Pavement Improvement | 2009-06-11 | 2009-08-14 | 2009-09-02 | 2009-10-29 | 1702338 | 4.391
7091 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAMAR |  | 04 | 0142063 | This project will resurface and improve the safety of US 98 from State Route 589 to Weathersby Road in Lamar county. | Pavement Improvement | 2009-10-08 | 2009-11-03 | 2010-09-30 | 2011-09-14 | 7811200 | 5.878
7092 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ADAMS |  | 03 | 0151054 | This project will resurface and extend the life of the pavement on US 84 from US 61 Intersection to the Franklin county line, Adams county. | Pavement Improvement | 2009-07-24 | 2009-07-30 | 2009-11-30 | 2009-12-08 | 4207644 | 10.053
7093 | Underway | C220,C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ADAMS |  | 03 | 0151060 | This project will install aesthetic street and bridge lighting and traffic cameras on the bridge over the Mississippi River in Natchez in Adams county. | Transportation Enhancements | 2009-07-09 | 2009-07-22 | 2010-12-31 |  | 1702600 | 2.496
7094 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | FRANKLIN |  | 03 | 0151063 | This project will resurface and extend the life of the pavement on approximately 8 miles of U.S. Hwy 84 west the Bude/Meadville By-Pass in Franklin county. | Pavement Improvement | 2009-03-31 | 2009-04-28 | 2009-09-30 | 2009-08-13 | 4239662 | 8.715
7095 | Underway | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | BOLIVAR, SUNFLOWER |  | 02 | 0161029 | This project will construct 2 additional lanes on State Route 8 between Cleveland and Ruleville in Bolivar and Sunflower Counties. | Pavement Widening | 2009-06-11 | 2009-06-19 | 2010-07-09 |  | 8630000 | 7.872
7096 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | BOLIVAR, SUNFLOWER |  | 02 | 0161033 | This project will resurface and extend the life of the pavement on State Route 8 from the Bolivar county Hospital to Ruleville, Bolivar and Sunflower county. | Pavement Improvement | 2009-07-09 | 2009-08-06 | 2009-10-09 | 2009-12-15 | 2626200 | 8.654
7097 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | AMITE, PIKE |  | 03 | 0168010 | This project will reconstruct the existing pavement, replace utilities, and improve safety on State Route 570 from .58 miles west of the Pike county line to the Pike county line and on State Route 570 | Pavement Improvement | 2009-07-30 | 2009-08-26 | 2011-05-17 | 2011-06-03 | 6372500 | 3.553
7098 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LEFLORE |  | 02 | 0180017 | The city of Greenwood will resurface Claiborne Street from US 82 to Grand Boulevard, Poplar Street from Claiborne to Park, and Garrard Avenue from US 82 to Sycamore Street. This project will make the | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-04-18 | 659169 | 2.350
7099 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | GRENADA |  | 01 | 0190005 | The city of Grenada will resurface Vance Road from Townes Ave to Browns Creek Bridge and Jackson Avenue from US 51 to Monroe St. This project will make the road smoother and extend the life of the pav | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-01-28 | 517732 | 3.433
7100 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0193008 | The city of Petal will resurface Hillcrest Loop and Carterville Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-01 | 2010-03-10 | 2010-04-30 | 2010-05-13 | 554497 | 4.084
7101 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | SCOTT |  | 03 | 0202079 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the rest area on I-20 East and West Bound Rest Areas, Scott County. | Transportation Enhancements | 2009-11-05 | 2009-10-26 | 2010-07-31 | 2011-08-03 | 1056100 | 0.000
7102 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST, LAMAR |  | 04 | 0210017 | This project will install overhead message signs, traffic cameras, and other traffic monitoring devices on US 49, US 98 & I-59 in Hattiesburg, Forrest county. | Other | 2009-11-05 | 2010-02-08 | 2011-06-30 | 2011-06-07 | 3878600 | 21.422
7103 | Underway | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0210021 | The city of Hattiesburg will construct a bikepath beginning Construction of a park along the Leaf River and construction of a multi-use trail. This project will improve bike access. | Transportation Enhancements | 2010-05-10 | 2010-05-10 | 2011-06-30 |  | 507742 | 0.080
7104 | Underway | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0210022 | This project will add a new bikeway from US 49 to the University of Southern Mississippi. Forrest County | Transportation Enhancements | 2010-03-25 | 2010-03-25 | 2011-06-30 |  | 880400 | 0.047
7105 | Underway | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 0211105 | The city of Horn Lake will construct a sidewalk along Goodman Rd. from Horn Lake Rd. to Hurt Rd. and pave Tulane Rd. from Nail Rd to Goodman Rd. This project will improve pedestrian access along Goodm | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-12-31 |  | 434689 | 2.550
7106 | Underway | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 0211106 | The city of Horn Lake will install a traffic signal and make other improvements at Goodman Road and Windchase Drive. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 2010-02-22 | 2010-02-22 | 2010-12-31 |  | 173445 | 0.010
7107 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JONES |  | 04 | 0221072 | This project will resurface and extend the life of the pavement approximately 2 miles in length on State Route 15 from 115th Street to Old Highway 15 in Laurel, Jones. | Pavement Improvement | 2009-04-08 | 2009-04-09 | 2009-06-04 | 2009-05-11 | 1202383 | 2.287
7108 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 0221073 | This project will resurface and extend the life of the pavement for approximately 6.2 miles on State Route 15 from the intersection of State Route 67 going north. Harrison county. | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2010-06-07 | 2008-07-01 | 940000 | 6.143
7109 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | CHICKASAW |  | 01 | 0223023 | This project will resurface and extend the life of the pavement for approximately 9 miles on State Route 15 between Houston and the Pontotoc county line, Chickasaw county. | Pavement Improvement | 2009-07-09 | 2009-07-16 | 2009-09-25 | 2009-11-06 | 2222728 | 9.385
7110 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | PERRY |  | 04 | 0224034 | This project will replace a bridge on State Route 29 over Black Creek in Perry county. | Bridge Improvement | 2009-06-01 | 2009-06-01 | 2010-12-31 | 2011-05-26 | 4258100 | 0.092
7111 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MARSHALL |  | 01 | 0230008 | The city of Holly Springs will resurface College Street from Boundary to Memphis Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 |  | 261488 | 0.672
7112 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ATTALA |  | 02 | 0232047 | This project will resurface and extend the life of the pavement on State Route 35 multilane section in Kosciusko from Natchez Trace Parkway to State Route 12, approximately 3 miles, Attala county. | Pavement Improvement | 2009-09-10 | 2009-10-22 | 2010-02-26 | 2010-02-02 | 1250021 | 2.444
7113 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | WAYNE |  | 04 | 0233013 | This project is a base repair, leveling, and overlay project along Clara-Buckatuna Road for 4.92 miles, Wayne county. This project will make the road smoother and will extend the life of the pavement | Pavement Improvement | 2010-06-01 | 2010-07-07 | 2010-09-29 | 2011-04-29 | 192139 | 4.920
7114 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | SUNFLOWER |  | 02 | 0240009 | The city of Indianola will resurface BB King, Westside Avenue, and Wiggins Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-06-30 | 2011-07-18 | 577010 | 2.744
7115 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 0250034 | The city of Jackson will resurface Northside Drive from Medgar Evers Boulevard to Jackson City Limits and Maddox Road from MS 18 to John R. Lynch Street. This project will make the road smoother and e | Pavement Improvement | 2010-04-28 | 2010-04-28 | 2011-06-30 | 2011-10-28 | 2763700 | 10.541
7116 | Underway | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | NEWTON, NESHOBA |  | 03 | 0261076 | This project will construct additional lanes on State Route 19 between the Lauderdale County Line and SR 492 in Newton and Neshoba county. | Pavement Widening | 2009-04-06 | 2009-04-15 | 2012-02-01 |  | 34406000 | 7.147
7117 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LINCOLN |  | 03 | 0275017 | This project will resurface, improve drainage, and extend the life of the pavement on approx. 7.2 miles of the Eddiceton-Caseyville Road in the Homochitto National Forrest located approx. ten miles we | Pavement Improvement | 2009-11-09 | 2009-11-30 | 2011-02-24 |  | 1668230 | 8.000
7118 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 0291004 | The city of Flowood will resurface 1.95 miles of Old Brandon Road from Hwy 80 to Pearl River Bridge and the addition of a left-turn lane along Treetops Blvd. at the existing intersection with Top Stre | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-02-23 | 510808 | 1.992
7119 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PIKE |  | 03 | 0310013 | The city of McComb will resurface and perform sidewalk Improvements to Pearl River Avenue, South Magnolia Street and Summit Street. This project will make the road smoother and extend the life of the | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2011-06-30 | 2011-05-12 | 760469 | 1.830
7120 | Underway | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO |  | 01 | 0311018 | This project will replace 4 bridges on MS Highway 305 from Cockrum to Lewisburg in Desoto county. | Bridge Replacement | 2009-07-09 | 2009-07-09 | 2011-08-03 |  | 7551300 | 1.430
7121 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HANCOCK | BILOXI-GULFPORT | 04 | 0321034 | The city of Bay St. Louis will install street lighting along Hwy 43 from Longfellow Road to I-10. This project will improve traffic operations and safety along this section of roadway. | Safety/Traffic Management | 2010-02-08 | 2010-02-08 | 2010-12-31 | 2011-05-03 | 732709 | 4.889
7122 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | ADAMS |  | 03 | 0340034 | The city of Natchez will resurface Pearl Street, Commerce Street, Rankin Street, Washington Street, Canal Street, State Street and Melrose Avenue. This project will make the road smoother and extend t | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-06-30 |  | 565281 | 2.101
7123 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | UNION |  | 01 | 0350012 | The city of New Albany will resurface and stripe Carter Ave. between Camp Ave. and Main St; on Bankhead Street between Camp Ave. and Glade Ave.; and replace a box culvert on Carter Avenue. This projec | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-06-30 | 2011-03-23 | 200921 | 0.483
7124 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAFAYETTE |  | 01 | 0360009 | The city of Oxford will resurface Jackson Avenue, Old Taylor Road (8601), Old Taylor Road (9426) and Belk Drive. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 | 2011-05-12 | 421873 | 1.363
7125 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | JEFFERSON DAVIS |  | 03 | 0371051 | This project will resurface and extend the life of the pavement on State Route 13 from north of the Marion County Line to US 84, Jefferson Davis county. | Pavement Improvement | 2009-07-09 | 2009-07-06 | 2009-09-30 | 2009-10-08 | 1642149 | 9.334
7126 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | NESHOBA |  | 03 | 0390009 | The city of Philadelphia will resurface Herman Alford Blvd. from Pecan Ave to 250 feet South of Saxon Airport Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2011-06-30 |  | 279334 | 0.565
7127 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | SIMPSON |  | 03 | 0392050 | This project will replace a bridge over the Middle Prong- Silver Creek on the Rockport-Shivers and Mount Zion Road 2.5 miles north of the Jefferson Davis/Simpson county line, Simpson County. | Bridge Replacement | 2009-07-07 | 2009-08-07 | 2009-12-01 | 2010-09-16 | 525400 | 0.300
7128 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PEARL RIVER |  | 04 | 0400023 | The city of Picayune will resurface North Main Street between West Canal Street and E. 4th Street' Beech Street between Will Street and Palentine Rd., and Palestine Rd and Crosby St. between West Cana | Pavement Improvement | 2010-03-01 | 2010-03-02 | 2010-04-22 | 2010-05-11 | 378056 | 4.081
7129 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | OKTIBBEHA |  | 03 | 0420017 | The city of Starkville will resurface: N. Montgomery St., University Drive, Jackson Street, Louisville Street, Yellow Jacket Drive and S. Montgomery Street. This project will make the road smoother an | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-06-30 |  | 603987 | 4.405
7130 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | OKTIBBEHA |  | 03 | 0420018 | This project will stripe and resurface Whitfield St. between Greensboro St. and Ave. of Patriots; and Louisville St. between Lynn Lane and Industrial Park Road in the city of Starkville, Oktibbeha co | Pavement Improvement | 2010-03-31 | 2010-03-31 | 2011-06-30 |  | 157713 | 0.000
7131 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | BOLIVAR |  | 02 | 0432015 | This project will resurface and extend the life of the pavement on approximately 11 miles of State Route 1 north of Rosedale in Bolivar county. | Pavement Improvement | 2009-05-19 | 2009-05-21 | 2009-07-24 | 2009-08-07 | 2959122 | 10.736
7132 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WARREN |  | 02 | 0440010 | The city of Vicksburg will resurface Wisconsin Avenue Overlay from Bazinsky Road to Interstate 20 and will resurface Clay Street from Cherry Street to Mission 66. This project will make the road smoot | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-02-23 | 644013 | 1.732
7133 | Underway | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | WARREN |  | 02 | 0440011 | The city of Vicksburg conduct interior renovations and make purchases of museum exhbits, Warren County. | Transportation Enhancements | 2010-08-27 | 2010-08-27 | 2011-12-31 |  | 1808881 | 0.000
7134 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONTGOMERY |  | 02 | 0470010 | The city of Winona will resurface Fairgrounds Street from Railroad Crossing to a point 1250 feet North of Railroad Crossing and Pecan Street from Fairgrounds St. to US Hwy 82 (begin State Maintenance) | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-02-23 | 158869 | 1.083
7135 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | YAZOO |  | 02 | 0480036 | The city of Yazoo will resurface Grady Ave from Mike Espy Dr to 9th, Lamar Ave from W 2nd St to 15th St., MLK Dr from 1st to 9th St. This project will make the road smoother and extend the life of the | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2011-06-30 |  | 470640 | 2.174
7136 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | COPIAH |  | 02 | 0541050 | This project will resurface and extend the life of the pavement on approximately 10 miles of State Route 27 north of Georgetown in Copiah county. | Pavement Improvement | 2009-04-09 | 2009-04-28 | 2009-07-15 | 2009-07-31 | 3193584 | 9.969
7137 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | PIKE |  | 03 | 0551094 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 welcome center, Pike County | Transportation Enhancements | 2010-03-11 | 2009-12-16 | 2010-10-13 | 2010-10-14 | 396000 | 0.000
7138 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | COPIAH |  | 02 | 0551095 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Rest Area in Copiah County - North Bound Lanes. | Transportation Enhancements | 2009-12-03 | 2009-12-03 | 2010-08-31 | 2011-05-20 | 760900 | 0.000
7139 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | HOLMES |  | 02 | 0552201 | This project will resurface and extend the life of the pavement on approximately 22.4 miles of I-55 between State Route 17 and the Carroll County Line, Holmes county. | Pavement Improvement | 2010-05-06 | 2010-08-12 | 2011-10-21 | 2010-12-08 | 10570800 | 22.871
7140 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | HOLMES |  | 02 | 0552210 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the rest area on I-55 Northbound north of Durant, Holmes county. | Transportation Enhancements | 2009-10-01 | 2009-10-22 | 2010-07-30 | 2011-05-05 | 467600 | 0.000
7141 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | CARROLL |  | 02 | 0553083 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Rest Area near Vaiden, Carroll county. | Transportation Enhancements | 2009-10-08 | 2009-10-12 | 2010-07-12 | 2010-06-30 | 257119 | 0.000
7142 | Underway | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO |  | 01 | 0554091 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Desoto County Rest Area, Desoto county. | Transportation Enhancements | 2009-12-03 | 2009-12-18 | 2010-10-15 |  | 498300 | 0.000
7143 | Underway | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0554092 | This project will add new landscaping onto the Interstate 55 Rest Area on the North and South Bound Lanes in Panola county. | Transportation Enhancements | 2011-03-10 | 2011-03-14 | 2012-02-01 |  | 90958 | 0.000
7144 | Underway | C220,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | STATEWIDE |  |  | 0554093 | This project will add new landscaping to along ths side of the I-55 North and South Bound lanes throughout the Mississippi Deparment of Transportation's District 2. This includes the counties of ..... | Transportation Enhancements | 2010-06-10 | 2010-08-17 | 2011-06-30 |  | 374700 | 248.347
7145 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN |  | 03 | 0561068 | This project will resurface and extend the life of the pavement on State Route 25 from State Route 471 to State Route 43 in Rankin county. | Pavement Improvement | 2009-04-10 | 2009-06-27 | 2010-05-07 | 2010-07-07 | 8833500 | 10.195
7146 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | COAHOMA |  | 02 | 0571004 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the Delma Furniss Hospitality Station, Coahoma county. | Transportation Enhancements | 2009-10-08 | 2009-10-14 | 2010-09-14 | 2010-09-23 | 263800 | 0.000
7147 | Underway | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | PEARL RIVER |  | 04 | 0591105 | This is a design build project which will add shoulders to 12 bridges on I-59 from the Louisiana state line to Poplarville, Pearl River County. | Bridge Improvement | 2009-08-10 | 2009-08-11 | 2010-12-31 |  | 10000000 | 0.633
7148 | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | PEARL RIVER |  | 04 | 0591106 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-59 welcome center, Pearl River Co. | Transportation Enhancements | 2009-05-07 | 2009-05-07 | 2011-12-31 | 2010-11-17 | 439900 | 0.000
7149 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE |  | 03 | 0593084 | This project will build a new interchange at I-20/59 and Hawkins Rd. & 23rd Ave in Meridian in Lauderdale county. This project will add new pavement, street lights, and bridge construction. | New Construction | 2009-07-09 | 2009-07-09 | 2011-07-29 |  | 15311899 | 0.064
7150 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE, NEWTON |  | 03 | 0593090 | This project is a design build project which will extend the I-59/I-20 merge lanes in Lauderdale county. Also, this project will add shoulders to 6 bridges on I-20 in Newton county. | Bridge Improvement | 2009-01-16 | 2009-01-16 | 2010-12-15 |  | 9999999 | 6.335
7151 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | WASHINGTON |  | 02 | 0622027 | This project will resurface and extend the life of the pavement for approximately 10 miles on State Route 438 from US 61 through Arcola to Highway 1, Washington county. | Pavement Improvement | 2009-06-11 | 2009-06-17 | 2009-09-04 | 2009-09-24 | 2418334 | 9.673
7152 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | WINSTON |  | 01 | 0679004 | This project will resurface and extend the life of the pavement on Ellison Ridge Road for approx 4 miles in length located 7 miles northeast of Noxapater, Winston county. | Pavement Improvement | 2009-06-26 | 2009-07-09 | 2009-10-01 | 2009-10-05 | 409900 | 4.150
7153 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0681017 | State Route 69 from Plymouth Road to Highway 69 south and SR 182 from State Route 69 to the Alabama state line for 9.67 miles, Lowndes county. This project will resurface and extend the life of the p | Pavement Improvement | 2010-05-10 | 2010-05-25 | 2010-11-19 |  | 3534132 | 0.000
7154 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0703016 | This project will resurface and extend the life of the pavement for approximately 11 miles on eastbound lanes for State Route 6 east of Batesville, Panola county. | Pavement Improvement | 2009-08-04 | 2009-08-06 | 2009-12-14 | 2010-02-24 | 2979976 | 11.916
7155 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE |  | 03 | 0741010 | This project will resurface and extend the life of the pavement on State Route 39 From I-20 to 52nd Street in Meridian, Lauderdale county. | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-11-24 | 2010-01-22 | 3638275 | 3.864
7156 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE, CLAY |  | 01 | 0791029 | This project will resurface and extend the life of the pavement on US 45 Alternative from West Point to one mile north of State Route 25, Monroe and Clay county. | Pavement Improvement | 2009-07-09 | 2009-07-14 | 2009-11-09 | 2009-12-01 | 4257606 | 8.187
7157 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0791030 | This project will resurface and extend the life of the pavement on US 45 Alternative from 9 miles north of the Noxubee County Line to the Clay county line, Lowndes county. | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-10-19 | 2010-01-11 | 2533578 | 6.625
7158 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE, CHICKASAW |  | 01 | 0792015 | This project will resurface and extend the life of the pavement on approximately 9 miles of US 45 Alternative between State Route 8 and the northern Monroe county line, Monroe and Chickasaw county. | Pavement Improvement | 2009-07-09 | 2009-07-29 | 2009-11-23 | 2010-01-11 | 3694157 | 8.847
7159 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAFAYETTE |  | 01 | 0793002 | This project will replace a bridge on State Route 331 over Yocona River near State Route 334 in Lafayette county. | Bridge Replacement | 2009-07-09 | 2009-07-09 | 2011-04-08 | 2011-05-18 | 3960000 | 1.109
7160 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0801015 | This project will resurface and extend the life of the pavement on US 49 from Edwards St. to 31st. Avenue in Hattiesburg, Forrest county. | Pavement Improvement | 2009-07-09 | 2009-07-10 | 2009-11-30 | 2010-03-12 | 7545174 | 5.835
7161 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | TISHOMINGO |  | 01 | 0948008 | This project will resurface and extend the life of the pavement on State Route 365 from the Prentiss/Tishomingo County Line to US 72 in Tishomingo county | Pavement Improvement | 2009-07-09 | 2009-07-03 | 2009-09-02 | 2009-09-10 | 1418166 | 6.569
7162 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | PERRY |  | 04 | 1152001 | This project will replace the existing bridge on State Route 198 over Dickey Creek near Beaumont in Perry county. | Bridge Replacement | 2009-07-09 | 2009-07-13 | 2010-03-31 | 2010-05-21 | 1469900 | 0.038
7163 | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | OKTIBBEHA |  | 03 | 2714001 | This project will replace two bridges, first bridge over Glen Creek and second bridge over Tobacco Juice Creek, along Poorhouse Road 3 miles south of Starkville, Oktibbeha county. | Pavement Improvement | 2009-12-21 | 2010-01-05 | 2010-09-21 | 2011-11-02 | 1309000 | 1.300
7164 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | YALOBUSHA, CALHOUN |  | 01 | 2791008 | This project will replace 9 bridges on State Route 32 from Water Valley to State Route 330 in Yalobusha and Calhoun county. | Bridge Replacement | 2009-08-06 | 2009-08-14 | 2011-02-18 | 2011-05-24 | 5923600 | 0.137
7165 | Underway | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | TATE |  | 01 | 2920001 | This project will construct two additional lanes on US 51 between Senatobia and Coldwater in Tate county. | New Construction | 2009-10-08 | 2009-10-08 | 2012-02-01 |  | 10497777 | 2.999
7166 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | TATE |  | 01 | 5512002 | The city of Senatobia will resurface East Main Street from SR 4 to Park Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 | 2011-03-17 | 217140 | 0.489
7167 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WAYNE |  | 04 | 5583001 | The city of Waynesboro will resurface West Avenue from MS 184 to Turner Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-01 | 2010-03-04 | 2010-04-27 | 2010-06-15 | 176421 | 0.856
7168 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | COPIAH |  | 02 | 5604001 | The city of Crystal Springs will resurface and add sidewalk ramps on Newton Street between Georgetown Street and Harmony Road. This project will make the road smoother and extend the life of the pave | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-06-30 | 2011-02-23 | 210757 | 0.380
7169 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | TIPPAH |  | 01 | 5659002 | The city of Ripley will resurface a section of Main Street from Highway 15 and extending northerly, approximately 0.75 miles to Highway 15. This project will make the road smoother and extend the life | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2010-06-30 |  | 143707 | 0.579
7170 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MARION |  | 04 | 6034005 | The city of Columbia will resurface and stripe Main Street beginning approx. 500 feet west of the intersection of Broad St. and High School Ave. and then west and north to Lafayette Street. This proje | Pavement Improvement | 2009-11-17 | 2010-03-08 | 2010-06-30 |  | 236954 | 0.519
7171 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WASHINGTON |  | 02 | 6922001 | The city of Greenville will resurface Tennessee Gas Road from Main Street to Highway 1. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-12-31 | 2011-05-12 | 1083959 | 1.135
7172 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON | JACKSON | 02 | 6980001 | The city of Flora will resurface First Street from US 49 to US 49. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-08-29 | 344483 | 2.663
7173 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON | JACKSON | 02 | 6988001 | The city of Madison will resurface North Old Canton Road from Sowell Road to Canton City Limits. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2010-12-31 | 2011-05-11 | 337949 | 1.870
7174 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 03 | 7037001 | The town of Terry will resurface Cunningham Avenue from I-55 to Railroad Avenue. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-05-11 | 267604 | 0.677
7175 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE |  | 01 | 7163001 | The city of Aberdeen will resurface Chestnut Street from Hwy 45/25 to Hwy 145. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-06-30 |  | 166973 | 0.650
7176 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WASHINGTON |  | 02 | 7221002 | The city of Greenville will add left turn lanes at the intersection of Reed Road and Main Street. This project will improve traffic operations and safety. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-12-31 | 2011-05-12 | 523897 | 0.020
7177 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 7272006 | The city of Pearl at Old Brandon Road will install a traffic signal and make other improvements at the intersection at Bierdeman Road and at Patton Drive. This project will improve traffic operations | Safety/Traffic Management | 2010-02-22 | 2010-02-22 | 2011-06-30 | 2011-10-28 | 181433 | 0.008
7178 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 7314022 | This project will improve safety and traffic operations by installing a traffic signal installation at the intersection of US Hwy 80 and Shaw Road in Hinds county. | Safety/Traffic Management | 2009-06-11 | 2009-09-08 | 2009-09-25 | 2009-11-23 | 130456 | 0.001
7179 | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 7314023 | This project will resurface and extend the life of the pavement on US 80 from Springridge Road to Terry Road, Hinds county. | Pavement Improvement | 2009-07-09 | 2009-07-22 | 2009-11-24 | 2009-05-07 | 5826874 | 7.909
7180 | Underway | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 7336004 | The city of Pearl will resurface Pirates Cove Road from Hwy 80 to Pearl High School Entrance. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2011-06-30 |  | 341053 | 1.060
7181 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON | JACKSON | 03 | 7354001 | The city of Madison will resurface Highland Colony Parkway -South Bound - between Madison Avenue and Broadmoor Baptist Church. This project will make the road smoother and extend the life of the pavem | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 | 2011-04-08 | 387782 | 1.006
7182 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON | JACKSON | 03 | 7354002 | The city of Ridgeland will resurface Highland Colony Parkway from Steed Road north 3000 feet. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-07-18 | 433024 | 0.559
7183 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PIKE |  | 03 | 7570004 | This project will reconstruct the existing pavement and replace utilities and improve safety on State Route 570 from West limits of McComb East .9 miles in Pike county. | Pavement Improvement | 2009-07-30 | 2009-08-26 | 2011-05-17 | 2011-06-03 | 1889000 | 0.876
7184 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 7829002 | The city of Biloxi will construct a right turn lane and intersection and signal upgrades on Division Street at Bohn Avenue and the I-110 on-ramp. This project will improve traffic operations and safet | Safety/Traffic Management | 2010-04-15 | 2010-04-15 | 2010-12-31 | 2011-09-21 | 561323 | 0.013
7185 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 7861002 | The city of Southaven will improve safety and traffic operations by installing traffic signals at two intersections along Getwell Road. Getwell Road at Central Parkway and Getwell Road at Nail Road in | Safety/Traffic Management | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-03-22 | 278733 | 0.022
7186 | Underway | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 7862003 | The city of Olive Branch will widen Stateline Road from two to three lanes, between Alexander Road and Hacks Cross Road. This project will improve traffic operations and safety. | Pavement Widening | 2010-02-26 | 2010-02-26 | 2010-12-31 |  | 715781 | 1.004
7187 | Underway | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 7868005 | The city of Southaven will resurface Airways Boulevard from Hwy 302 to the Mississippi/Tennessee state line. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 |  | 645419 | 2.232
7188 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO |  | 01 | 7886001 | The city of Hernando will resurface Commerce Street from US 51 east to the Illinois Central Railroad Crossing. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 |  | 196357 | 1.233
7189 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 7904001 | The city of Olive Branch will install a traffic signal and make other improvements at the intersection of Pigeon Roost Road and Hwy 305. This project will improve traffic operations at this intersecti | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2010-12-31 | 2011-05-12 | 215436 | 0.011
7190 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | CLAY |  | 01 | 7950001 | The city of West Point will resurface Lone Oak Drive from approximately East Oak Ridge Drive to Lone Oak Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-06-30 |  | 306944 | 0.749
7191 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | BOLIVAR |  | 02 | 8032005 | The city of Cleveland will construct sidewalks along Court Street and North Street. This project will improve pedestrian access along these roads. | Safety/Traffic Management | 2010-02-11 | 2010-02-11 | 2010-12-31 |  | 1001016 | 0.606
7192 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JONES |  | 04 | 8063001 | The city of Laurel will replace a bridge on 5th Avenue over Gardiner Creek. | Bridge Replacement | 2010-02-19 | 2010-02-19 | 2011-06-30 | 2011-03-24 | 132829 | 0.013
7193 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JONES |  | 04 | 8077001 | The city of Laurel will install a traffic signal and make other improvements at the intersection of Beacon Street and Mason Street. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 2010-02-22 | 2010-02-22 | 2011-06-30 | 2011-03-24 | 151341 | 0.017
7194 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JONES |  | 04 | 8093001 | The city of Laurel will resurface 16th Avenue from King Street to Ferrill Street and will resurface 16th Ave from Ellisville Boulevard to Lee Street. This project will make the road smoother and exten | Pavement Improvement | 2010-03-03 | 2010-03-04 | 2010-04-16 | 2010-04-30 | 146087 | 0.123
7195 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE |  | 03 | 8134001 | The city of Meridian will replace a bridge over Sowashee Creek. This project will improve traffic safety. | Bridge Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-04-14 | 994222 | 0.014
7196 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE |  | 03 | 8161001 | The city of Meridian will make safety upgrades, replace lighting, and other enhancements to the 26th Avenue viaduct. This project willextend the life of the structure and improve safety. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 |  | 912796 | 0.149
7197 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LEE |  | 01 | 8193007 | The city of Tupelo will build a new bridge to extend Eason Boulevard over Town Creek and Kings Creek. | Bridge Improvement | 2009-09-15 | 2009-09-15 | 2011-06-30 | 2011-08-15 | 1227688 | 0.145
7198 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 8762002 | The city of Hattiesburg will resurface W. Pine Street from Broadway Drive to Hwy 49S. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-04-30 | 2010-05-13 | 553842 | 1.113
7199 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | ATTALA |  | 02 | 8930001 | The city of Kosciusko will resurface Love Road from South Natchez Street to South Huntington Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2011-06-30 |  | 201425 | 0.719
7200 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | PASCAGOULA-MOSS POINT | 04 | 8943002 | The city of Pascagoula will replace a bridge and resurface the pavement on Old Mobile Highway between 14th Street and Chicot Street. This project will make the road smoother and extend the life of the | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2010-12-31 | 2011-05-12 | 816189 | 0.794
7201 | Underway | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | MARSHALL |  | 01 | 9025100 | This project will add pavement to 2.1 miles of the North Holly Springs Industrial Bypass Road just north of Holly Springs. This project will make the road smoother and extend the life of the pavement. | New Construction | 2009-09-28 | 2009-09-28 | 2010-06-16 |  | 1637100 | 2.100
7202 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9044001 | The city of Biloxi will install street lighting along MS Hwy 67 from the Tchoutacabouffa River north to the City Limits. This project will improve traffic operations and safety. | Safety/Traffic Management | 2010-02-11 | 2010-02-11 | 2010-12-31 | 2011-05-12 | 249486 | 0.906
7203 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | BILOXI-GULFPORT | 04 | 9064008 | The county of Jackson will add a right turn lane and make sidewalk improvements on Beachview Rd and Old Spanish Trail; and install traffic signals on Old Spanish Trail at Beachview Drive and at Hansha | Safety/Traffic Management | 2010-02-26 | 2010-02-26 | 2010-12-31 | 2011-07-11 | 522479 | 0.035
7204 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9082002 | The city of Long Beach will replace a bridge on Klondyke Road, which crosses Canal No. 1. This project will improve traffic safety. | Bridge Replacement | 2010-02-19 | 2010-02-19 | 2010-12-31 | 2011-07-08 | 599524 | 0.013
7205 | Underway | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9082003 | The city of Long Beach will install traffic signals and make other intersection improvements at the intersection of Klondyke Road and 28th Street. This project will improve traffic operations and saf | Safety/Traffic Management | 2010-03-30 | 2010-03-30 | 2011-01-30 |  | 492824 | 0.013
7206 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HANCOCK | BILOXI-GULFPORT | 04 | 9137002 | The county of Hancock will resurface and make other repairs to Kiln-Waveland Cutoff Road from US 90 to Hwy 603. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-09-01 | 2010-09-07 | 2011-01-31 | 2011-06-08 | 798064 | 1.431
7207 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9183001 | The city of D'Iberville will replace a bridge over the bayou on Gorenflo Road, south of Borries Street. This project will improve traffic safety. | Bridge Replacement | 2010-03-30 | 2010-03-30 | 2010-12-31 | 2011-05-12 | 430420 | 0.013
7208 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | PASCAGOULA-MOSS POINT | 04 | 9192001 | The city of Gautier will install a traffic signal at the intersection of Ladnier Road and Old Spanish Trail. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 2010-02-26 | 2010-02-26 | 2010-12-31 | 2011-01-10 | 131030 | 0.009
7209 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9371011 | The city of Gulfport will replace a bridge over Fritz Creek on Old Lorraine Road. This project will improve traffic safety. | Bridge Improvement | 2010-02-19 | 2010-02-19 | 2010-12-31 | 2011-05-12 | 173388 | 0.058
7210 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9375005 | The city of Biloxi will resurface Beauvoir Road, from US 90 to Pass Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-05-03 | 2010-05-11 | 2010-06-16 | 2010-08-06 | 181524 | 0.744
7211 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | PASCAGOULA-MOSS POINT | 04 | 9393001 | The city of Moss Point will resurface Amoco Road from Hwy 63 west 1000 feet. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2011-03-01 | 2011-03-24 | 2011-04-07 | 2011-04-27 | 84500 | 1.191
7212 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LINCOLN |  | 03 | 9518003 | The city of Brookhaven will resurface Brookway Boulevard beginning at the east end of State Maintenance just east of I-55 and then east to US Hwy 51. This project will make the road smoother and exten | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-06-30 |  | 342652 | 0.990
7213 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE |  | 01 | 9569003 | The city of Amory will resurface Waterway Drive from Hwy 278 to 5th Ave. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-06-30 |  | 249621 | 0.832
7214 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PRENTISS |  | 01 | 9629002 | The city of Booneville will install a traffic signal and make other improvements at the intersection along N. 2nd Street at Hwy 4, College Street, Veterans (George E. Allen Drive) and Cunningham Boule | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2010-10-01 | 2011-11-09 | 441425 | 0.110
7215 | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WASHINGTON |  | 02 | 9670003 | The city of Leland will resurface North Broad Street from 8th Street to the City Limits. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-06-30 | 2011-03-16 | 158583 | 0.566
7216 | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WINSTON |  | 01 | 9674008 | The city of Louisville will resurface South Church Street from Hwy 15 to Armstrong Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-06-30 |  | 267133 | 1.553
7217 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN, HINDS, MADISON | JACKSON | 03 | 9999510 | This project takes place in the following three counties: Hinds, Madison, and Rankin. This project will resurface and extend the lives of Louis Wilson Drive in Brandon from US Highway 80 to MS Hwy 18; | Pavement Improvement | 2010-08-05 | 2010-08-19 | 2010-10-29 | 2010-11-09 | 876732 | 0.000
7218 | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON, JACKSON | BILOXI-GULFPORT | 04 | 9999610 | This project will resurface and extend the life of the pavement on various sites in Jackson and Harrison county. City of Gulfport - Mill & Overlay 14th St from 27th Ave to 28th Ave & from 21st Ave to | Pavement Improvement | 2010-11-08 | 2010-11-09 | 2011-07-15 | 2011-09-14 | 1001409
7219 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CASS |  | 04 | 0021032 | This project consist of a thin lift asphalt overlay from Commercial Street to Route ZZ in Cass and Johnson counties | Pavement Improvement | 2009-09-08 | 2009-07-29 | 2009-12-01 | 2009-08-19 | 546942.61 | 14.656
7220 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | LACLEDE |  | 04 | 0052029 | This project consists of constucting a five lane roadway on Route 5, Laclede County to improve safety and improve capacity. | Pavement Widening | 2010-03-01 | 2010-03-01 | 2010-11-15 | 2010-11-12 | 2809319.52 | 2.250
7221 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | CAMDEN |  | 04 | 0053053 | This project consist of widening Route 5 to three lanes through Sunrise Beach in Camden county | Pavement Widening | 2009-06-15 | 2009-06-15 | 2010-05-28 | 2010-08-26 | 835469.39 | 0.900
7222 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PUTNAM |  | 06 | 0054025 | This project consist of resurfacing roadway from Iowa State line to Route 136 - Putnam county | Pavement Improvement | 2010-02-08 | 2010-04-01 | 2010-11-01 | 2010-06-11 | 490711.37 | 8.435
7223 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BENTON |  | 04 | 0072039 | This project consist of rehabilitation of bridges on Route 7 over Truman Lake (Osage Arm Bridge and Grand River Arm Bridge) in Benton county | Bridge Improvement | 2009-06-15 | 2009-06-18 | 2010-10-15 | 2010-10-26 | 5153860.63 | 2.000
7224 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | 0091014 | This project consists of rehabilitation of the Heart of America bridge over the Missouri River, including addition of a bicycle and pedistrian facility, on Route 9 in Clay county. | Pavement Improvement | 2010-02-01 | 2010-06-07 | 2010-12-01 | 2010-10-28 | 455549.99 | 0.400
7225 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE | KANSAS CITY (KS)-MO | 06 | 0091015 | This project consists of interchange improvements, building ramps and roundabout from SB Rte. 9 to Briarcliff in Clay county. | Pavement Improvement | 2010-01-04 | 2010-01-25 | 2011-12-01 | 2011-10-14 | 2500000 | 0.941
7226 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE | KANSAS CITY (KS)-MO | 06 | 0091016 | This project consists of a bridge replacement on Route 9 over the White Aloe Branch in Platte county south of Route FF. | Bridge Replacement | 2010-01-04 | 2010-06-09 | 2011-12-01 | 2011-05-16 | 105000 | 0.113
7227 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | RAY |  | 04 | 0134027 | This project consist of resurfacing roadway from the Caldwell county Line to Route 10 at the City of Richmond - Ray county | Pavement Improvement | 2010-03-08 | 2010-08-17 | 2010-11-01 | 2010-12-20 | 1149943.86 | 18.597
7228 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CALDWELL |  | 06 | 0134028 | This project consist of replacing bridge deck over Route 36 in Hamilton - Caldwell county | Bridge Replacement | 2010-03-08 | 2010-06-02 | 2010-08-01 | 2010-07-30 | 596676.92 | 0.081
7229 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MONROE |  | 09 | 0151011 | This project consist of pavement and shoulder improvements from Route 154 north junction to 1.1 miles north of Route 22 in Monroe and Audrain counties | Pavement Improvement | 2009-05-18 | 2009-09-15 | 2009-12-01 | 2009-11-30 | 2433862.06 | 24.572
7230 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | AUDRAIN |  | 09 | 0151012 | This project consist of pavement improvements from 1.1 miles north of Route 22 to 0.2 miles north of Route 54 in Audrain county | Pavement Improvement | 2009-07-06 | 2009-08-18 | 2009-12-01 | 2009-10-17 | 796130.05 | 5.038
7231 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | TEXAS |  | 08 | 0171009 | This project consist of a thin lift asphalt overlay from Route 106 in Summersville to Route 60 in Mt. View in Texas and Howell counties | Pavement Improvement | 2009-06-08 | 2009-07-09 | 2009-12-01 | 2009-07-27 | 564176.21 | 13.251
7232 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | HOWELL |  | 08 | 0171010 | This project consist of a thin lift asphalt overlay from Route 60 in Mt. View to Route 160 in Howel county | Pavement Improvement | 2009-06-08 | 2009-07-08 | 2009-12-01 | 2009-09-15 | 860642.49 | 19.349
7233 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MILLER |  | 09 | 0172010 | This project consist of replacement of bridge over the Osage River one mile east of Tuscumbia in Miller county, project involves bridge J0719 | Bridge Replacement | 2009-02-17 | 2009-02-23 | 2010-10-01 | 2010-11-05 | 8277485 | 0.591
7234 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MILLER |  | 09 | 0172011 | This project consist of a thin lift asphalt overlay from Route 54 to Brush Creek in Cole and Miller counties | Pavement Improvement | 2009-06-08 | 2009-06-12 | 2009-12-01 | 2009-07-23 | 831658.73 | 19.266
7235 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | SHANNON |  | 08 | 0191008 | This project consist of roadway resurfacing on Route 19 from Route 106 to .4 miles north of Route F in Eminence and on Route 106 from Route 19 to 1.3 miles west of Route 19 - Shannon county | Pavement Improvement | 2010-02-08 | 2010-04-05 | 2010-12-01 | 2010-11-10 | 149724.18 | 2.230
7236 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | CRAWFORD |  | 09 | 0192017 | This project consist of resurfacing roadway from .6 miles north of Route 8 to Route 19 South in Steelville - Crawford county | Pavement Improvement | 2010-03-08 | 2010-07-14 | 2010-12-01 | 2010-07-30 | 111960.35 | 1.200
7237 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | MONTGOMERY |  | 09 | 0194012 | This project consists of asphalt resurfacing from near Route B (just north of Montgomery City) to 1.7 miles south of Route I-70. | Pavement Improvement | 2010-01-04 | 2010-04-15 | 2010-12-01 | 2010-07-29 | 2140300 | 8.792
7238 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WASHINGTON |  | 08 | 0211018 | This project consist of pavement improvements from 1.7 miles south of Route 8 in Potosi to Route N in Iron county | Pavement Improvement | 2009-06-08 | 2009-06-24 | 2009-11-01 | 2010-05-12 | 2264378.25 | 21.247
7239 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MARION |  | 09 | 0243033 | This project consists of bridge rehabilitation over the North fabius river .9 miles north of Route 6 near Taylor. | Bridge Improvement | 2010-03-08 | 2010-04-05 | 2010-12-01 | 2010-10-28 | 1843000 | 0.200
7240 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MARIES |  | 09 | 0281009 | This project consist of a thin lift asphalt overlay from Route 63 to Dixon in Maries and Pulaski counties | Pavement Improvement | 2009-04-06 | 2009-06-09 | 2009-12-01 | 2009-07-02 | 815732.51 | 16.964
7241 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | 0291111 | This project consists of extensive pavement repair, hot in place recycle and asphalt resurfacing from Rte. 273 near Platte City for 18 miles (North and South) to Vivion Road, new rumble strip and pave | Pavement Improvement | 2009-05-04 | 2009-05-18 | 2009-11-01 | 2009-09-29 | 11834247 | 34.857
7242 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | 0292155 | This project consist of resurfacing roadway from Route 169 (Belt Highway) to Route 371 (22nd Street) in St. Joseph - Buchanan county | Pavement Improvement | 2010-03-18 | 2010-04-01 | 2010-11-01 | 2010-04-19 | 373642.1 | 1.773
7243 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | 0311005 | This project consist of a thin lift asphalt overlay from Route 36 to Route 169 in Buchanan county | Pavement Improvement | 2009-07-06 | 2009-10-28 | 2010-10-01 | 2009-11-24 | 308549.72 | 6.222
7244 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | DENT |  | 08 | 0322017 | This project consist of resurfacing roadway from .2 mile west of Route 72 to 2.5 miles east of Route 72 in the City of Salem - Dent county | Pavement Improvement | 2010-03-08 | 2010-03-23 | 2010-12-01 | 2010-04-28 | 488236.2 | 2.700
7245 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | ST FRANCOIS |  | 08 | 0323019 | This project consist of rehabilitation of the existing pavement on Route 32 (Karsh Blvd) from Route OO to Route 67 in the City of Farmington - St. Francois county | Pavement Improvement | 2010-03-08 | 2010-04-26 | 2010-12-01 | 2010-12-02 | 1069447.24 | 2.823
7246 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WAYNE |  | 08 | 0341035 | The project consists of adding shoulders, repaving, and several new alignments between Piedmont and Patterson. The alignment will change several curves and eliminate at least one 's' curve. A three | Pavement Widening | 2008-11-17 | 2008-11-17 | 2011-12-01 | 2011-07-06 | 12735200 | 13.349
7247 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BOLLINGER |  | 08 | 0341036 | This project consist of resurfacing roadway in Marble Hill - Bollinger county | Pavement Improvement | 2010-03-08 | 2010-06-21 | 2010-09-01 | 2010-12-02 | 513735.61 | 2.589
7248 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CLINTON |  | 06 | 0352082 | This project consists of asphalt resurfacing on I-35 north of Shoal Creek to north of Route 116 near Lathrop. | Pavement Improvement | 2009-02-17 | 2009-02-17 | 2009-12-15 | 2010-08-30 | 14754615 | 7.057
7249 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | LINN |  | 06 | 0362077 | This project consist of a thin lift asphalt overlay from Route 36 to Route 11 in Linn county | Pavement Improvement | 2009-06-08 | 2009-08-06 | 2009-12-01 | 2009-09-09 | 197445.03 | 1.772
7250 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LAWRENCE |  | 07 | 0391022 | This project consist of a thin lift asphalt overlay from Route 60 to 1.5 miles north of Route 248 in Barry and Lawrence county | Pavement Improvement | 2009-04-06 | 2009-04-14 | 2009-12-01 | 2009-11-20 | 475300.14 | 12.113
7251 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CARROLL |  | 06 | 0411003 | This project consist of pavement and shoulder improvements from Route 24 to Route 240 in Saline and Carroll counties | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-12-01 | 2009-06-30 | 1575664.74 | 17.680
7252 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | SALINE |  | 04 | 0411004 | This project consist of a thin lift asphalt overlay from Route 240 to Route TT in Saline county | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-12-01 | 2009-05-26 | 511733.26 | 10.268
7253 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | PHELPS |  | 08 | 0442223 | This project consist of major pavement rehabilitation/reconstruction on westbound lanes from Business Loop 44 (Rolla) to Sugartree Road Interchange in Phelps county | Pavement Improvement | 2009-07-06 | 2009-09-08 | 2009-12-01 | 2009-12-01 | 10378900.69 | 8.213
7254 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PULASKI |  | 04 | 0442224 | This project consist of an asphalt mill and fill from SP 44 to Route H/I-44 in St. Robert/Waynesville in Pulaski county | Pavement Improvement | 2009-07-06 | 2009-10-16 | 2009-12-01 | 2009-11-09 | 911377.3 | 5.620
7255 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CRAWFORD |  | 09 | 0443100 | This project consist of pavement rehabilitation on westbound lanes from 0.6 miles west of Route H to the Phelps County line in Crawford county | Pavement Improvement | 2009-06-08 | 2009-09-21 | 2009-12-01 | 2009-11-14 | 888525.09 | 12.507
7256 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN |  | 09 | 0443101 | This project consist of rebuilding of pavement from Viaduct Street to Route 100 West in Franklin county | Pavement Widening | 2009-08-10 | 2009-08-21 | 2010-10-01 | 2010-11-02 | 16945578.18 | 5.072
7257 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | 0451025 | This project consist of a thin lift asphalt overlay from Route 273 to Spur 45 south in Platte county | Pavement Improvement | 2009-06-08 | 2009-10-05 | 2009-12-01 | 2009-10-21 | 507200 | 11.890
7258 | Completed | C240,C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 04 | 0501042 | This project will complete a diamond interchange at Route 50 and Bynum Road in Jackson county. | New Construction | 2010-03-29 | 2010-03-29 | 2010-12-01 | 2010-12-01 | 4157306.95 | 0.100
7259 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | COLE |  | 04 | 0503078 | This project consist of pavement treatment on westbound lanes from Truman Blvd. To west of Truman Blvd. - Cole county | Pavement Improvement | 2010-03-08 | 2010-04-13 | 2010-12-01 | 2010-05-03 | 328862.64 | 1.539
7260 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PERRY |  | 08 | 0512016 | This project consist of pavement improvements from I-55 to Route 72 in Perry and Bollinger counties | Pavement Improvement | 2009-06-08 | 2009-06-24 | 2009-11-01 | 2010-05-04 | 1766282.57 | 16.297
7261 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | HENRY |  | 04 | 0521007 | This project consist of a thin lift asphalt overlay from the St. Clair county line to Route 13 in Henry county | Pavement Improvement | 2009-06-08 | 2009-07-29 | 2009-12-01 | 2009-10-30 | 566857.15 | 15.143
7262 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BATES |  | 04 | 0521008 | This project consist of a thin lift asphalt overlay from Route BB to 1.6 miles east of Route W in Bates county | Pavement Improvement | 2009-06-08 | 2009-07-29 | 2009-12-01 | 2009-11-30 | 194615.17 | 5.268
7263 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST CLAIR |  | 04 | 0521009 | This project consist of a thin lift asphalt overlay from 1.0 miles west of Route P to 1.8 miles east of Route A in St. Clair county | Pavement Improvement | 2009-06-08 | 2009-07-29 | 2009-12-01 | 2009-11-30 | 213769.83 | 4.741
7264 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | COLE |  | 04 | 0543155 | This project consist of pavement improvements from the Missouri River Bridge to .25 miles west of Stadium Blvd. in Jefferson City. Project includes ramps at Route 50-54-63 interchange (tri- level) - C | Pavement Improvement | 2010-03-08 | 2010-04-13 | 2010-12-01 | 2010-05-24 | 935730.6 | 3.300
7265 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CALLOWAY |  | 09 | 0543156 | This project consist of resurfacing westbound lanes from Holts Summit to the Missouri River Bridge in Jefferson City - Callaway county | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2010-12-01 | 2010-11-29 | 1219596.6 | 5.184
7266 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | NEW MADRID |  | 08 | 0551134 | This project consist of pavement rehabilitation of north and south bound lanes from Route 84 to Scott county in New Madrid county | Pavement Improvement | 2009-02-17 | 2009-05-12 | 2010-10-31 | 2010-10-30 | 15743400 | 46.834
7267 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PEMISCOT |  | 08 | 0551135 | This project consist of pavement rehabilitation on the northbound lanes from the Arkansas state line to I-155 in Pemiscot county | Pavement Improvement | 2009-06-08 | 2009-06-24 | 2010-07-30 | 2010-07-28 | 16220964 | 15.282
7268 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | NEW MADRID |  | 08 | 0551136 | The construction of a new Welcome Center on I-55 at Marston | Transportation Enhancements | 2009-01-23 | 2009-01-23 | 2011-11-15 | 2011-07-05 | 5768950 | 0.300
7269 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON |  | 03 | 0552086 | This project consists of adding lands and widening or rplacing two bridges on Route 55 between north of Route M and north of Route Z in Jefferson county. | Pavement Widening | 2010-03-08 | 2010-03-08 | 2011-12-01 | 2011-05-13 | 13539119.84 | 4.509
7270 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ATCHISON |  | 06 | 0591025 | This project consist of a thin lift asphalt overlay from the Iowa state line to Route 136 in Atchison county | Pavement Improvement | 2009-06-08 | 2009-06-29 | 2009-12-01 | 2009-09-30 | 713109.87 | 9.908
7271 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARRY |  | 07 | 0601030 | The jobs combine to provide new surface and alternating passing lane improvements for 22 plus miles of a 25 mile stretch of Route 60 in Barry, Lawrence, Christian, and Greene Counties. As designed, J | Pavement Improvement | 2009-02-17 | 2009-07-08 | 2009-11-01 | 2010-11-20 | 222135.57 | 17.617
7272 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARRY |  | 07 | 0601031 | The jobs combine to provide new surface and alternating passing lane improvements for 22 plus miles of a 25 mile stretch of Route 60 in Barry, Lawrence, Christian, and Greene Counties. As designed, J | Pavement Improvement | 2009-02-17 | 2009-07-08 | 2009-11-01 | 2010-11-20 | 8392901.26 | 15.894
7273 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | 0602067 | This project consists of improvements at the James River Freeway and National Avenue interchange. | Pavement Widening | 2009-09-23 | 2009-09-23 | 2011-12-01 | 2010-09-23 | 4569532 | 0.474
7274 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CARTER |  | 08 | 0603095 | This project consist of ADA sidewalk improvements on Business 60 from Oliver Street to Alexander Street in Van Buren, 0.98 miles. | Transportation Enhancements | 2010-01-04 | 2010-03-01 | 2010-05-14 | 2010-03-18 | 101771 | 0.098
7275 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | TEXAS |  | 08 | 0603096 | This project consist of resurfacing roadway from Route 181 to Route 60 in Cabool - Texas county | Pavement Improvement | 2010-02-08 | 2010-09-17 | 2010-12-01 | 2010-09-17 | 147400 | 2.666
7276 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LEWIS |  | 09 | 0614137 | This project consist of a thin lift asphalt overlay from Route 961 to Route B in LaGrange - Lewis county | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-11-01 | 2010-09-15 | 93900 | 1.776
7277 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MISSISSIPPI |  | 08 | 0621022 | This project consist of a thin lift asphalt overlay from Route B in Bertrand to the City of Charleston in Mississippi county | Pavement Improvement | 2009-06-08 | 2009-06-16 | 2009-12-01 | 2009-07-27 | 325653.65 | 5.856
7278 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | HOWELL |  | 08 | 0631029 | This project consist of an asphalt mill and fill from Route 63 North to Broadway in West Plains in Howell county | Pavement Improvement | 2009-07-06 | 2009-10-28 | 2009-12-01 | 2009-11-23 | 526470.69 | 1.801
7279 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | ADAIR |  | 09 | 0634066 | This is the first in a series of two projects to construct an Alternate Route 63 around Kirksville Missouri. This project runs from the North edge of Kirksville to Route 6, just east of Kirksville. | New Construction | 2009-08-03 | 2009-08-12 | 2011-12-01 | 2011-11-23 | 17491350.38 | 8.500
7280 | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | 0652063 | This project consist of widening route to six lanes from Business 65 (Chestnut Expressway) to Route D (Sunshine Street) in Greene County | Pavement Widening | 2009-08-24 | 2009-08-24 | 2011-12-01 |  | 8475485.52 | 2.027
7281 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | 0652064 | This project consist of widening route to six lanes from Route D (Sunshine Street) to Route 60 (James River Freeway) in Greene County | Pavement Widening | 2009-08-24 | 2009-08-24 | 2011-12-01 | 2011-09-02 | 2985865.5 | 3.466
7282 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | 0652065 | This project consist of widening route to six lanes from Business 65 (Chestnut Expressway) to Route D (Sunshine Street) in Greene County | Pavement Widening | 2009-08-24 | 2009-08-24 | 2011-12-01 |  | 9701900 | 2.027
7283 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | DALLAS |  | 04 | 0652066 | This project consist of adding a center turn lane for 1.0 mile north of Route 32 in Dallas county | Pavement Widening | 2010-01-04 | 2010-09-21 | 2010-12-01 | 2010-10-28 | 1016100 | 1.000
7284 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BENTON |  | 04 | 0653088 | This project consist of rehabilitation of bridge on Route 65 over the Osge River near Warsaw in Benton county | Bridge Improvement | 2009-06-15 | 2009-06-18 | 2010-10-15 | 2010-10-26 | 1386858.25 | 0.144
7285 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | JASPER |  | 07 | 0661017 | This project consist of resurfacing disconnected section from Geneva Avenue to Duquesne Road in Joplin - Jasper county | Pavement Improvement | 2010-03-08 | 2010-10-27 | 2010-12-01 | 2010-12-07 | 226846.87 | 0.887
7286 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUTLER |  | 08 | 0671018 | This project consist of intersection improvements at Business Route 67, OR 67 and Industrial Park Bypass - Butler county | Pavement Improvement | 2010-03-08 | 2010-06-03 | 2010-11-01 | 2010-08-17 | 671400.58 | 0.200
7287 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS |  | 01 | 0673109 | This project consists of ADA sidwalk improvements from I-270 to Old St. Charles Rd and on Route AC from Route 67 (Lindbergh) to I-270 in St. Louis county | Transportation Enhancements | 2009-09-08 | 2009-09-28 | 2010-05-01 | 2010-06-23 | 1912955.05 | 7.500
7288 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | 0691013 | This project consist of a thin lift asphalt overlay from the Clinton county line to Route 92 in Clay county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-11-25 | 328587.39 | 6.017
7289 | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON |  | 06 | 0701179 | This project consist of constructing a new half diamond interchange at Route 40 - I435, replacement of Blue Ridge cut off bridge over I-70, add lanes to I-70, and modification to some ramps in Jackson | New Construction | 2009-10-07 | 2009-10-07 | 2012-03-01 |  | 34077640.17 | 5.437
7290 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON |  | 04 | 0701190 | This project consist of rehabilitating eastbound bridges from Troost to Route 40 in Jackson county | Bridge Improvement | 2010-03-08 | 2010-03-08 | 2011-12-01 | 2011-08-23 | 6673400 | 26.000
7291 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LAFAYETTE |  | 04 | 0702101 | This project consists of resurfacing of the roadway and shoulders on eastbound and westbound Interstate 70 from the Lafayette County line to Odessa. | Pavement Improvement | 2009-05-04 | 2009-06-15 | 2009-12-01 | 2010-03-01 | 7178338.73 | 20.230
7292 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | COOPER |  | 06 | 0703217 | This project consist of pavement improvements on the westbound lanes from 0.3 miles east of Route B to the Saline county line in Cooper county | Pavement Improvement | 2009-04-06 | 2009-06-12 | 2009-12-01 | 2009-11-12 | 8262515.78 | 17.100
7293 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | 0703218 | This project consist of a thin lift asphalt overlay from Route 63 north connector to Route Z in Boone county | Pavement Improvement | 2009-06-08 | 2009-08-10 | 2009-12-01 | 2009-09-30 | 283369.62 | 5.340
7294 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | 0703220 | This project consist of a thin lift resurfacing from Route E west to the end of state maintenance in the City of Columbia - Boone county | Pavement Improvement | 2010-03-08 | 2010-04-06 | 2010-12-01 | 2010-07-16 | 142257.35 | 2.000
7295 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY |  | 01 | 0705314 | This project consist of pavement improvements from I-44/I-55 to Washington Ave. in St. Louis City | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2009-12-01 | 2010-06-18 | 5092700 | 0.570
7296 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARTON |  | 04 | 0712061 | This project consists of constructing a new interchange at Route 71 and 126. Work includes grading, asphalt pavement and new bridge. | New Construction | 2009-06-22 | 2009-06-22 | 2010-10-01 | 2010-07-07 | 4643989 | 3.805
7297 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARTON |  | 04 | 0712062 | This project consists of constructing a new interchange at Route 71 and DD/EE. Work includes grading, asphalt pavement and new bridge. | New Construction | 2009-07-06 | 2009-07-13 | 2010-10-01 | 2010-08-09 | 3667300 | 3.059
7298 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARTON |  | 04 | 0712063 | This project consists of constructing a new interchange at Route 71 and V/C. Work includes grading, asphalt pavement and new bridge. | New Construction | 2009-07-06 | 2009-07-13 | 2010-10-01 | 2010-07-21 | 3744287 | 6.200
7299 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BATES |  | 04 | 0713045 | This project consists of the construction of an overpass with on and off ramps at the junction of Highway 71 and Highway 52 East. Two other bridges will be built as part of this project. One will re | New Construction | 2009-07-06 | 2009-08-18 | 2010-10-01 | 2010-09-30 | 5063473.34 | 2.904
7300 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | MADISON |  | 08 | 0722020 | This project consist of resurfacing roadway through the City of Fredricktown - Madison county | Pavement Improvement | 2010-03-08 | 2010-04-26 | 2010-12-01 | 2010-12-02 | 481500 | 1.995
7301 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | TANEY |  | 07 | 0761014 | This project consist of ADA sidewalk improvements from Roark Valley Road to Gretna (Branson) in Taney county | Transportation Enhancements | 2009-07-27 | 2009-08-19 | 2009-12-01 | 2009-11-19 | 675976.35 | 2.864
7302 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | TANEY |  | 07 | 0761015 | This project consists of construction of a roundabout and new bridge over Lake Taneycomo. | New Bridge Construction | 2009-06-23 | 2009-06-23 | 2011-12-01 | 2011-12-16 | 8943704.39 | 0.210
7303 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | TANEY |  | 07 | 0761017 | This project consist of ADA ramps from Shepherd of the Hills Expressway to Gretna Road I the City of Branson - Taney county | Transportation Enhancements | 2010-10-04 | 2010-11-01 | 2011-05-26 | 2011-05-09 | 39419.33 | 1.233
7304 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BENTON |  | 04 | 0831001 | This project consist of rehabilitation of bridge on Route 83 over Truman Lake near Mockingbird Road in Benton county | Bridge Improvement | 2009-06-15 | 2009-06-18 | 2010-10-15 | 2010-10-26 | 2364845.86 | 0.500
7305 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | NEWTON |  | 07 | 0861007 | This project consist of improvements on existing pavement and shoulders with the addition of rumble strips from Route P to 0.2 miles west of Route 71 in Newton county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-11-02 | 802960.38 | 9.952
7306 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARRY |  | 07 | 0861008 | This project consist of improvements on existing pavement and shoulders with the addition of rumble strips from Route F to 2.9 miles east of Route H in Barry county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-11-02 | 922994.44 | 11.596
7307 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PULASKI |  | 04 | 1037004 | This project consist of roadway resurfacing on Route 133 from Route 7 to the railroad tracks and resurfacing Route 7 from Route 133 to Route A in Richland - Pulaski county | Pavement Improvement | 2010-03-08 | 2010-09-30 | 2010-12-01 | 2010-09-30 | 100380.81 | 1.303
7308 | Completed | C250,C200 | Highway Infrastructure Investment Grant | MISSOURI | WEBSTER |  | 04 | 1045005 | This project consist of a thin lift asphalt overlay from Route 60 to south of railroad in Webster county | Pavement Improvement | 2009-06-08 | 2009-09-09 | 2009-12-01 | 2009-10-10 | 32417.41 | 1.190
7309 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | RIPLEY |  | 08 | 1098007 | This project consist of resurfacing roadway from Route 160 to Route E in Doniphan - Ripley county | Pavement Improvement | 2010-03-08 | 2010-04-21 | 2010-07-01 | 2010-06-01 | 336848.84 | 4.064
7310 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CAPE GIRARDEAU |  | 08 | 1130006 | This project consist of rehabilitating pavement surface from I-55 to Kingshighway in Cape Girardeau county | Pavement Improvement | 2009-07-06 | 2009-07-24 | 2009-08-14 | 2009-09-04 | 520520.09 | 1.703
7311 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUTLER |  | 08 | 1200003 | This project consist of a thin lift asphalt overlay from County Road 462 to Route 67 in Butler county | Pavement Improvement | 2009-04-06 | 2009-06-09 | 2009-12-01 | 2009-06-29 | 362742.14 | 8.183
7312 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RIPLEY |  | 08 | 1206005 | This project consist of a thin lift asphalt overlay from Route V west of Doniphan to Route 160 in Doniphan in Ripley county | Pavement Improvement | 2009-04-06 | 2009-08-31 | 2009-12-01 | 2009-10-15 | 762576.55 | 14.548
7313 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUTLER |  | 08 | 1221003 | This project consist of a thin lift asphalt overlay from Route WW in Poplar Bluff to Route 158 in Butler county | Pavement Improvement | 2009-04-06 | 2009-06-09 | 2009-12-01 | 2009-06-29 | 267090.49 | 5.628
7314 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CAPE GIRARDEAU |  | 08 | 1271004 | This project consist of resurfacing roadway from the Jackson city limits to Route 61 - Cape Girardeau county | Pavement Improvement | 2010-03-08 | 2010-06-21 | 2010-09-01 | 2010-08-27 | 392852.67 | 2.277
7315 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CAPE GIRARDEAU |  | 08 | 1277002 | This project consist of resurfacing and improving shoulders from Lasalle Ave to Lexington Ave. in Cape Girardeau county | Pavement Improvement | 2009-11-09 | 2010-03-15 | 2010-12-01 | 2011-02-22 | 2357519.01 | 4.200
7316 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PEMISCOT |  | 08 | 1286003 | This project consist of a thin lift asphalt overlay from Route 164 to the Arkansas state line in Pemiscot county | Pavement Improvement | 2009-05-08 | 2009-05-08 | 2009-12-01 | 2009-06-05 | 364909.97 | 6.465
7317 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PEMISCOT |  | 08 | 1321002 | This project consist of a thin lift asphalt overlay from Route U to Route 164 in Pemiscot county | Pavement Improvement | 2009-05-08 | 2009-05-08 | 2009-12-01 | 2009-06-05 | 467598.93 | 6.091
7318 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | HOLT |  | 06 | 1324003 | This project consist of a thin lift asphalt overlay on Spur 113 in Holt County from Route 113 to Route A and on Route A in Nodaway County from Spur 113 to Route 71 | Pavement Improvement | 2009-07-06 | 2009-08-24 | 2010-07-01 | 2009-09-24 | 680396.98 | 11.702
7319 | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | ATCHISON |  | 06 | 1361059 | This project involves painting, redeck and bridge repairs of the Missouri River brige at Brownville, NE | Bridge Improvement | 2009-08-31 | 2009-08-31 | 2011-12-01 |  | 4868280 | 0.600
7320 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PUTNAM |  | 06 | 1362025 | This project consist of a thin lift asphalt overlay from Route 63 to Route N in Schuyler and Putnam counties | Pavement Improvement | 2009-04-06 | 2009-04-10 | 2009-12-01 | 2009-05-06 | 842800.72 | 8.334
7321 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PUTNAM |  | 06 | 1362026 | This project consist of resurfacing roadway from Route 5 to Route N - Putnam county | Pavement Improvement | 2010-02-08 | 2010-04-01 | 2010-11-01 | 2010-06-11 | 1024836.77 | 17.839
7322 | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS |  | 02 | 1411029 | This project consist of right of way acquisition to relocate and construct Route 141 from Route 40 to Route 340 (Olive Blvd). In cooperation with St. Louis County, construct Route 141 from Route 340 | New Construction | 2009-08-19 | 2009-08-19 | 2012-03-01 |  | 56700078 | 2.700
7323 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS |  | 01 | 1411034 | This project consist of grading for the utility relocation at Route 340 in St. Louis county | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2010-05-01 | 2010-04-30 | 743385.45 | 0.500
7324 | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON |  | 04 | 1501010 | This project consists of grading, drainage and new concrete pavement to construct a divided 4 lane highway on Route 9 from Horridge Road to Route 291 in Lee's Summit. | Pavement Widening | 2009-09-08 | 2009-09-08 | 2011-11-01 |  | 14101900 | 3.426
7325 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE |  |  | 1600706 | This project consist of resurfacing in communities with populations less than 5,000 in Barton and Jasper | Pavement Improvement | 2010-03-15 | 2010-05-03 | 2010-10-01 | 2010-10-08 | 266916.67 | 0.000
7326 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BATES |  | 04 | 1600707 | This project consist of resurfacing in communities with populations less than 5,000 in Bates County. Project split from 7S0010B. | Pavement Improvement | 2010-03-15 | 2010-10-18 | 2010-10-01 | 2010-10-29 | 173083.46 | 0.000
7327 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | ST CLAIR |  | 04 | 1600708 | This project consist of resurfacing in communities with populations less than 5,000 in St. Clair county. | Pavement Improvement | 2010-03-15 | 2010-06-10 | 2010-10-01 | 2010-06-30 | 214405.4 | 0.000
7328 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BARRY |  | 07 | 1600709 | This project consist of resurfacing in communities with populations less than 5,000 in Barry County. | Pavement Improvement | 2010-03-15 | 2010-05-11 | 2010-10-01 | 2010-06-02 | 123123.57 | 0.000
7329 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | PEMISCOT |  | 08 | 1641008 | This project consist of a thin lift asphalt overlay from Route D to Route DD in Pemiscot county | Pavement Improvement | 2009-05-08 | 2009-05-08 | 2009-12-01 | 2009-06-01 | 99361.37 | 1.725
7330 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | 1691086 | A $1.1 million contract awarded to St. Joseph Fuel Oil & Manufacturing Company for two miles of sidewalk improvements. Included are new upgrades to the existing sidewalk and adding curb ramps to accom | Transportation Enhancements | 2009-08-10 | 2009-08-10 | 2009-12-01 | 2009-12-04 | 1133856.23 | 2.023
7331 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ANDREW |  | 06 | 1692021 | This project consist of pavement and shoulder improvements from Route 31 to I-29 in Dekalb, Andrew, and Buchanan counties | Pavement Improvement | 2009-07-06 | 2009-09-25 | 2009-12-01 | 2009-11-30 | 2787343.94 | 21.438
7332 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | SALINE |  | 04 | 2401019 | This project consist of a thin lift asphalt overlay from east of Route 65 to Route 41 in Saline county | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-12-01 | 2009-06-30 | 73420.03 | 0.391
7333 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | HOWARD |  | 06 | 2401020 | This project consist of pavement and shoulder improvements from Route 5 to Route 40 in Howard county | Pavement Improvement | 2009-06-08 | 2009-09-28 | 2009-12-01 | 2009-12-01 | 1072711.37 | 12.800
7334 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | STONE |  | 07 | 2651001 | This project consist of a thin lift asphalt overlay from Route 76 to Route 165 in Stone and Taney counties | Pavement Improvement | 2009-04-06 | 2009-04-14 | 2009-12-01 | 2009-05-04 | 282036.46 | 5.364
7335 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | 2661012 | This project consist of a thin lift asphalt overlay from Route AB to Farm Road 107 in Greene county | Pavement Improvement | 2009-06-08 | 2009-07-14 | 2009-12-01 | 2009-08-19 | 64386.58 | 1.324
7336 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 06 | 3372402 | City of Independence - 39th Street Improvements from Noland to Chrysler, three lane, curb and guttering and sidewalks | Pavement Widening | 2010-11-22 | 2010-11-22 | 2012-03-01 |  | 1088224.81
7337 | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES |  | 02 | 3641032 | This project consist of extending Page Ave. from 0.3 miles west of Harvester to 0.6 miles east of Central School Road at Woodstream in St. Charles county | New Construction | 2009-10-05 | 2009-10-22 | 2011-12-01 |  | 20063948.85 | 0.300
7338 | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES |  | 02 | 3641033 | This project consist of extending Page Ave. from 0.6 miles east of Central School Road at Woodstream to 0.3 miles wet of Central School Road in St. Charles county | New Construction | 2009-10-05 | 2009-10-22 | 2011-12-01 |  | 22795858.16 | 0.900
7339 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | 3641034 | This project consist of grading, paving, bridge and one-way outer roads from .3 miles west of Central School Road to Mid Rivers Mall Drive - St. Charles county | Pavement Improvement | 2010-03-01 | 2010-03-10 | 2011-12-01 | 2011-08-15 | 6065000 | 1.300
7340 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE |  |  | 4500205 | This project consist of cold in Place Recycling on various routes in Nodaway, Caldwell, Harrison, DeKalb, Daviess,Worth, Andrew and Gentry counties | Pavement Improvement | 2009-06-08 | 2009-06-23 | 2009-10-01 | 2009-11-09 | 3490059.09 | 0.000
7341 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | 5417603 | St. Louis City will be street enhancements on Cherokee Street from Nebraska to Jefferson. This consist of streetscape improvements, sidewalk reconstruction w/landscaping, pedestrian lighting, and stre | Transportation Enhancements | 2010-07-06 | 2010-07-16 | 2010-12-01 | 2011-05-24 | 705556.89 | 0.400
7342 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | 5421602 | This project consist of a design study for the Goodfellow Blvd. roadway. | Pavement Widening | 2010-09-03 | 2010-09-03 | 2011-12-01 |  | 1966365.76 | 0.000
7343 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY |  | 01 | 5500664 | "St.Louis City will be doing enhancements on Manchester Road from Taylor Ave. to Sarah Ave. This consist of sidewalk widening, removal and relocation of curbs to create four 11'-6"" lanes, pedestrian | Transportation Enhancements | 2010-01-07 | 2010-01-07 | 2011-12-01 | 2011-07-13 | 1311873.89 | 0.700
7344 | Completed | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | 5595611 | St.Louis City will be doing Phase 2 of the Salisbury Street enhancements from N. Florissant to 11th Street. This consist of reconstructing sidewalks and ramps, new pedestrian lighting, curb repair, la | Transportation Enhancements | 2010-01-08 | 2010-01-08 | 2011-05-15 | 2011-01-26 | 870681 | 0.400
7345 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | 5602602 | St. Louis City will be widening bridge over Union Pacific RR tracks, including iimprovements to intersections with southbound I-55 off ramp (Loughborough Ave over Union Pacific Railroad) | Bridge Replacement | 2010-05-24 | 2010-07-12 | 2011-12-01 | 2011-08-30 | 631032 | 0.110
7346 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | 5603602 | St. Louis City will be doing asphalt resurfacing and constructing retaining walls and culverts on the Tucker Street Bridge from O'Fallon St. to Washington Avenue | Pavement Widening | 2010-01-08 | 2010-01-08 | 2011-12-01 |  | 17387181 | 0.665
7347 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | 6201602 | The City of Union has received additional funds for improvments on the Church Street project including sidewalks, paved approaches, curb and gutter, utility adjustments and retaining walls from Route | Transportation Enhancements | 2009-05-04 | 2009-07-01 | 2009-10-30 | 2009-10-30 | 207932 | 1.200
7348 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | 6202601 | This project consist of a bridge replacement over Boone Creek at Sapsucker Road in Franklin County. | Bridge Replacement | 2010-11-01 | 2010-11-01 | 2011-12-01 | 2011-07-25 | 444309.03 | 0.150
7349 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | 7203601 | Jefferson County will be doing roadway improvemetns from Lion's Den Camp Rd to Binning Road. | Pavement Widening | 2010-07-19 | 2010-07-19 | 2011-12-01 | 2011-07-31 | 1296516.83 | 0.820
7350 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | 7305604 | The City of St. Peters will be installing new traffic signals and pedestrian facilities at St. Peters-Howell Road / Toelle Road. | Safety/Traffic Management | 2010-11-03 | 2011-01-17 | 2011-04-15 | 2011-05-18 | 208832.47 | 0.100
7351 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | 7401020 | This project consist of pavement improvements on westbound and eastbound lanes from Broadway to Route 63 in Boone county | Pavement Improvement | 2009-07-13 | 2009-07-13 | 2009-10-05 | 2009-09-10 | 1916857.02 | 5.303
7352 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | 7591001 | This project consists of pavement repair and resurfacing the roadway and shoulders on Route 759 Buchanan county. | Pavement Improvement | 2010-02-01 | 2010-04-26 | 2010-12-01 | 2010-07-29 | 2045965.47 | 2.118
7353 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | STONE |  | 07 | 9900832 | In Gelena, the city will be doing sidewalk improvements around the square along 4th Street, Maple Street, and Main Street | Transportation Enhancements | 2009-10-15 | 2009-11-01 | 2010-09-01 | 2010-08-20 | 249971.43 | 0.150
7354 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | OZARK |  | 08 | 9900840 | In Gainsville, the city will be doing sidewalk rehabilitation and construction near the square and along various city streets | Transportation Enhancements | 2010-01-29 | 2010-02-16 | 2010-09-01 | 2010-10-11 | 113780 | 0.350
7355 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | 9900860 | This project will provide scoping and final design to improve safety and capacity of Route CC from Main Street in the City of Nixa to Route NN/J in the City of Ozark. | Other | 2009-09-21 | 2009-09-28 | 2011-12-01 |  | 900000 | 3.700
7356 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN | ST. JOSEPH (KS) | 06 | ES01001 | This project consist of constructing a new truck staging area along Stockyard Expressway and intersections improvements in the St. Joseph Regional Port area | Pavement Widening | 2009-07-17 | 2009-08-27 | 2010-11-01 | 2010-10-20 | 1097188.28 | 0.000
7357 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | NODAWAY |  | 06 | ES01002 | The City of Maryville will be constructing Phase A-II, which is a walking/biking trail located within the city limits of Maryville. This trail will be 3760 ft. in length and 6' to 8' in wide with a co | Transportation Enhancements | 2009-09-11 | 2009-09-11 | 2010-10-15 | 2010-08-29 | 284421.34 | 0.712
7358 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN | ST. JOSEPH (KS) | 06 | ES01003 | "The Urban Trail System incorporates the construction of 10' wide, 6"" thick concrete pavement for use as a high-volume, shared-use trail. This specific phase constitutes the first component of a two | Transportation Enhancements | 2010-04-05 | 2010-04-05 | 2010-10-15 | 2010-09-30 | 186902.41 | 0.316
7359 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CHARITON |  | 06 | ES02002 | The City of Brunswick will be replacing existing sidewalks along Route 24 from Polk Street to Adams Street | Transportation Enhancements | 2009-10-13 | 2009-10-14 | 2010-07-01 | 2010-07-27 | 412126.01 | 0.712
7360 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | WARREN |  | 09 | ES03002 | City will construct a new ADA (Americans with Disabilities Act) compliant sidewalk, which will provide connectivity of Marthasville?s ?Uptown? section to the ?Downtown? section. There will be replace | Transportation Enhancements | 2009-09-23 | 2009-10-01 | 2010-07-31 | 2010-07-31 | 57549.52 | 0.150
7361 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | LEWIS |  | 09 | ES03003 | City will remove old, deteriorated existing sidewalks with safe new sidewalks, which will be constructed to American with Disabilities Act (ADA) Standards. The five-foot-wide sidewalk will connect th | Transportation Enhancements | 2009-08-07 | 2009-08-07 | 2010-12-31 | 2011-01-31 | 64706.96 | 0.090
7362 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | PIKE |  | 09 | ES03004 | City will install historic/ornamental lighting in the downtown district. The new lighting will be in the vicinity of Lewis Street, Clark Street and 4th Street (State Route B) | Transportation Enhancements | 2009-09-14 | 2009-09-14 | 2010-12-15 | 2010-12-15 | 96035 | 0.400
7363 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | MONROE |  | 09 | ES03005 | The City of Paris will replace existing sidewalk with new sidewalk that will be constructed to American with Disabilities Act (ADA) Standards. There will also be the installation of historic lightin | Transportation Enhancements | 2009-08-20 | 2009-08-20 | 2010-12-15 | 2011-01-03 | 76026.24 | 0.600
7364 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | MONTGOMERY |  | 09 | ES03007 | The City of Jonesburg proposes to remove 982 linear feet of existing sidewalk and construct 4? concrete sidewalk that will be constructed to American with Disabilities Act (ADA) Standards. The sidewa | Transportation Enhancements | 2009-10-19 | 2009-10-19 | 2010-07-31 | 2010-07-31 | 59048.69 | 0.190
7365 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CLAY | KANSAS CITY (KS)-MO | 06 | ES04001 | The City of Gladstone will be doing landscaping, decorative lighting, crosswalks and other scenic corridor improvements along North Oak Trafficway from NE 69th Street to NE 71st Street | Pavement Improvement | 2009-09-18 | 2009-09-22 | 2009-10-24 | 2009-10-24 | 305097.35 | 1.510
7366 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | Multiple | ES04002 | The City of Blue Springs will be doing mill, asphalt overlay, and curb pavement markings at Adams Dairy Parkway from Duncan to Moreland School Road | Pavement Improvement | 2009-10-21 | 2009-10-21 | 2009-11-16 | 2009-11-16 | 378061 | 0.400
7367 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CLAY | KANSAS CITY (KS)-MO | 06 | ES04003 | The City of Liberty will be putting in additional curbs, lane width and improvements of medians of Kansas Street, Liberty Drive, and Mill Street | Pavement Improvement | 2009-10-12 | 2009-10-13 | 2009-11-18 | 2009-11-18 | 378061 | 0.803
7368 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04004 | The City of Raytown will be doing removal and replacement of deteriorated curbs and sidewalk. There will also be construction of new curbs and sidewalks at varius location throughout Raytown | Pavement Improvement | 2010-06-09 | 2010-06-10 | 2010-12-01 | 2011-01-13 | 377971.28 | 2.745
7369 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE | KANSAS CITY (KS)-MO | 06 | ES04005 | This project consist of construction of left turn lanes at Route AA in the City of Riverside - Platte county | New Construction | 2010-03-08 | 2010-03-24 | 2010-06-11 | 2010-07-21 | 303942 | 0.304
7370 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 04 | ES04006 | In Pleasant Hill, the city will be doing milling and overlay work on Business Route 7, Country Club Drive, and Sugarland Drive | Pavement Improvement | 2010-06-01 | 2010-06-03 | 2010-12-01 | 2010-07-01 | 186131.95 | 1.500
7371 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 06 | ES04007 | Jackson County will be replacing failing deck and upgrading guardrail system on Blue Mills Bridge | Bridge Improvement | 2010-02-15 | 2010-02-15 | 2010-12-01 | 2010-07-27 | 378061 | 0.049
7372 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 04 | ES04008 | In Harrisonville, the city will be doing milling and overlay work on North Independence, South Street, North Commercial Street, and South Independence | Pavement Improvement | 2010-03-01 | 2010-04-12 | 2010-08-01 | 2010-11-21 | 280051.93 | 1.760
7373 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04009 | The City of Grandview will be reconstruction 2000 ft of the rural section of 2nd Street to connect with 1600 ft long 3rd Street being constructed on a new alignment | Pavement Widening | 2010-06-15 | 2010-06-16 | 2011-06-11 | 2011-07-18 | 378061 | 0.340
7374 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 05 | ES04010 | In Belton, the city will be doing milling and overlay work on Cambridge Road, Prospect Avenue, Kentucky Street, 163rd Street, and North Scott Avenue | Pavement Improvement | 2010-07-29 | 2010-07-29 | 2010-12-01 | 2010-08-25 | 350328.06 | 2.468
7375 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04011 | The City of Lee's Summit will be constructing Todd George Road between two existing arterials and as an outer road associated with the Strother Road Interchange currently under construction | New Construction | 2010-07-12 | 2010-07-16 | 2011-12-01 | 2011-10-30 | 1183191.48 | 2.600
7376 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 04 | ES04012 | In Raymore, the city will be doing milling and overlay work on M-58 Highway | Pavement Improvement | 2010-06-01 | 2010-07-15 | 2010-08-30 | 2010-11-10 | 342672.2 | 0.010
7377 | Underway | C240,C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04015 | Kansas City will be replacing Troost Bridge at Volker Blvd. | Pavement Widening | 2010-05-10 | 2010-05-10 | 2012-03-01 |  | 8876831.5 | 0.490
7378 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE | KANSAS CITY (KS)-MO |  | ES04016 | Signal retiming/synchronization, vehicle detection on creitical intersection, cameras added, Operation Green Light location expansion, new communication tower and upgrades to the wireless backbone. | Safety/Traffic Management | 2009-08-26 | 2009-08-27 | 2011-12-31 |  | 3595750.5 | 0.000
7379 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 06 | ES04017 | The City of Independence will be creating a Major North-South divided four lane street. The new roadway will have open ditches, sidewalk, and a shared bicycle/pedestrian path to reconnect city and so | New Construction | 2010-03-15 | 2010-03-29 | 2011-12-01 | 2011-05-02 | 2630191.66 | 0.800
7380 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04019 | The City of Independence will be widening Jackson Drive from Holke Road to M-78 Highway from the existing 2 lanes to 4. There will also be installation of curb, gutter, sidewalk, and shared use path | Pavement Widening | 2010-02-01 | 2010-02-03 | 2011-12-01 | 2011-08-23 | 1015161.45 | 0.604
7381 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04020 | Kansas City will be constructing traffic signals at five intersections: 31st Street at Southwest Trafficway, The Paseo, Benton Blvd, Cleveland Avenue, and Jackson Avenue | Safety/Traffic Management | 2010-04-26 | 2010-04-26 | 2010-12-01 | 2010-07-12 | 749388.4 | 0.000
7382 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04021 | Kansas City will be rehabilitating the current Traffic Operation buidling and purchase of equipment for Traffic Operations activities | Safety/Traffic Management | 2010-09-27 | 2010-09-27 | 2010-12-01 | 2011-06-05 | 750000 | 0.000
7383 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04022 | The City of Blue Springs will be construction traffic signals at two intersections: 39th Street and Broadway Blvd and 39th Street and Roanake Road | Safety/Traffic Management | 2010-03-15 | 2010-03-15 | 2010-12-01 | 2011-01-12 | 400000 | 0.000
7384 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE | KANSAS CITY (KS)-MO |  | ES04023 | A planning study to develop detailed transit implementation, phasing, and costing information to support expanded local, county, and retional service implementation. | Other | 2009-08-12 | 2009-08-12 | 2011-12-31 |  | 258820 | 0.000
7385 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04024 | "The City of Kansas City will be constructing a 10"" wide 1600 ft trail, which will connect to the existing trail " | Transportation Enhancements | 2010-04-15 | 2010-04-15 | 2010-12-01 | 2010-12-15 | 313753.73 | 0.490
7386 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04025 | The City of Raytown will be replacing sidewalks and will be doing construction of new 5' wide sidewalks | Transportation Enhancements | 2010-10-26 | 2010-10-26 | 2010-12-01 | 2011-05-11 | 514488.43 | 4.000
7387 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04026 | The City of Blue Springs will be doing an expansion of Ward Park Trail. This will consist of removal and reasphalt of the existing 1 mile long trail, extending trail 500 ft and widen existing trail 4 | Transportation Enhancements | 2010-09-01 | 2010-09-07 | 2010-12-01 | 2010-12-23 | 56458.85 | 1.000
7388 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 04 | ES04027 | The City of Raytown will be reconstructing a 6.2 mile bicycle and pedestrian trail at Longview Lake | Transportation Enhancements | 2010-02-15 | 2010-02-15 | 2010-12-01 | 2011-07-21 | 250000 | 6.200
7389 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04028 | The City of Lee's Summit will be construction 0.7 miles of multi-use 10' wide trail along Todd George Road to connect to existing multi-use trail on both north and south | Transportation Enhancements | 2010-05-03 | 2010-05-14 | 2010-12-01 | 2011-03-25 | 148502.44 | 0.460
7390 | Completed | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | CLAY | KANSAS CITY (KS)-MO | 06 | ES04029 | The City of Gladstone will be doing mill and overlay work on Broadway from Englewood Road to north city limits | Transportation Enhancements | 2010-10-12 | 2010-10-21 | 2010-12-01 | 2011-06-12 | 272963.65 | 0.250
7391 | Completed | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04030 | The City of Independence will be connecting the 1.6 mile asphalt multi-use train in Waterfall Park with the 14 mile multi-use 10' wide Little Blue Trace Trail | Transportation Enhancements | 2010-07-12 | 2010-07-13 | 2010-12-01 | 2011-04-15 | 420000 | 0.490
7392 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 04 | ES04031 | The City of Cleveland will be doing construction and replacement of 5' wide sidewalks along the north and south sides of Main Street/State Highway Y | Transportation Enhancements | 2010-07-12 | 2010-07-14 | 2010-12-31 | 2011-04-15 | 146156.38 | 0.660
7393 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | ES04032 | The City of Weston will be constructing new 5' wide sidewalks on 5th Street | Transportation Enhancements | 2009-09-17 | 2009-09-17 | 2010-12-01 | 2011-02-14 | 74423.82 | 0.090
7394 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | LAFAYETTE |  | 04 | ES04034 | The City of Higginsville will be constructing new 5' wide sidewalks on Fairground Park/Grandview Elementary Sidewalks | Transportation Enhancements | 2009-08-19 | 2009-08-19 | 2010-12-01 | 2010-12-17 | 150587.83 | 0.570
7395 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | HENRY |  | 04 | ES04035 | This project consist of sidewalk improvements on Route 18 from east of 9th Street to west of Pawnee Street in the City of Clinton | Transportation Enhancements | 2009-09-11 | 2009-09-21 | 2010-08-15 | 2010-07-30 | 137910.8 | 0.428
7396 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | ES04036 | City of Kearney will be installing street lights, 5' sidewalks, fence handrail landscape along Main Street | Transportation Enhancements | 2009-09-25 | 2009-09-25 | 2010-12-01 | 2011-01-24 | 116539.3 | 0.220
7397 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04037 | Enhancements to channel & roadway project at Brush Creek & Troost, including: landscaping, signage, lighting, benches, trash receptacles, trail connection from creek to street @ NW corner of Paseo & V | Transportation Enhancements | 2010-10-07 | 2010-10-12 | 2011-12-01 | 2011-04-21 | 1359832.4 | 1.000
7398 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04038 | The improvements for West Front Street will be a 4-lane divided roadway built to boulevard standards. The project limits will be the Grand Boulevard Diamond Interchange (I-29/35 under construction) to | New Construction | 2010-10-13 | 2010-10-13 | 2011-12-01 | 2011-06-24 | 2314441.33 | 0.700
7399 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE | COLUMBIA | 09 | ES05003 | In Columbia, the city will be building a raiload bridge over Route 63 north of Route B in Boone county | Safety/Traffic Management | 2009-07-30 | 2009-08-17 | 2010-10-01 | 2010-10-07 | 3350137.6 | 0.200
7400 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BENTON |  | 04 | ES05004 | Construction of the Steamboat Landing Trail in the City of Warsaw. This project includes a pedestrian trail, landscaping, and lighting along the north side of the harbor connecting Drake Harbor to th | Transportation Enhancements | 2010-03-10 | 2010-03-10 | 2010-10-01 | 2010-10-29 | 260476 | 0.000
7401 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | ES05005 | The City of Hallsville will be constructing sidewalks along Ricketts Road, Sunrise Drive, Fairview Street, and Route OO | Transportation Enhancements | 2010-06-28 | 2010-07-01 | 2010-10-01 | 2011-04-28 | 288528.75 | 0.000
7402 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | MARIES |  | 09 | ES05006 | The City of Belle will be replacing old broken sidewalk on Third St. from Tellman Ave. to Linn Ave. Also included are new sidewalks on Third St. from Johnson Ave. to Apple Ave and along Fourth St. be | Transportation Enhancements | 2010-02-10 | 2010-03-01 | 2010-10-01 | 2010-04-22 | 66467 | 0.000
7403 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CAMDEN |  | Multiple | ES05007 | The City of Osage Beach will be constructing new sidewalks along the west side of Rte 54 from Redbud Road to Zebra Road and along the east side of Rte 54 from Zebra Road to Hatchery Road | Transportation Enhancements | 2010-02-17 | 2010-02-18 | 2010-10-01 | 2010-06-10 | 319605 | 0.760
7404 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | ES05008 | This project consist of MDNR bridge rehabilitation on Katy Trail over Moniteau Creek near Rocheport - Boone county | Transportation Enhancements | 2010-03-15 | 2011-01-10 | 2011-12-01 | 2012-02-03 | 504701 | 0.000
7405 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | COOPER |  | 06 | ES05009 | This project consist of MDNR culvert rehabilitation on Katy Trail over an unnamed creek, near Pleasant Green - Cooper county | Transportation Enhancements | 2010-03-15 | 2010-10-12 | 2010-10-01 | 2010-11-09 | 199700 | 0.000
7406 | Underway | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES |  | 02 | ES05010 | This project consist of MDNR bridge replacement on Katy Trail over Little Femme Osage Creek, near Defiance - St. Charles county | Transportation Enhancements | 2010-03-15 | 2011-09-09 | 2012-01-01 |  | 249000 | 0.000
7407 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES |  | 02 | ES05011 | This project consist of MDNR construction of approximately 2.5 miles of new Katy Trail from St. Charles to Machens - St. Charles County | Transportation Enhancements | 2010-03-15 | 2010-09-21 | 2010-10-01 | 2010-11-29 | 370000 | 0.000
7408 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06001 | Goodfellow-Skinker Asphalt Overlay and Pedestrian Improvements . Design Study - Engineering Design Study -pedestrian facilities,streetscaping elements, and reconfiguration of the MO T / Front Street i | Other | 2009-07-10 | 2009-07-10 | 2010-12-01 | 2010-09-10 | 327404.08 | 0.200
7409 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06002 | Franklin County will be doing a pedestrian/bike path along the west side of Route T from Great Oaks Drive to Labadie Elementary School | Transportation Enhancements | 2009-07-10 | 2009-07-10 | 2011-11-29 | 2011-08-26 | 277897.1 | 0.600
7410 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06003 | The City of Pacific will be doing sidewalk and lighting improvements on West Osage Street. This will consist of street lighting, street trees, retaining walls from Indian Warpath Drive to North 7th S | Safety/Traffic Management | 2010-08-15 | 2010-09-20 | 2011-11-29 |  | 709891.25 | 1.700
7411 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06004 | The City of Sullivan will be doing Phase 2 on East Vine Street, which consist of asphalt resurfacing, curb and gutter, sidewalks from McKinley Street to Hughes Ford Road | Pavement Improvement | 2010-09-27 | 2010-09-28 | 2011-11-29 | 2011-05-31 | 750236.22 | 0.500
7412 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06006 | The City of Washington will be doing asphalt resurfacing on various streets: W. Eighth Street, W. Main Street, Grand Avenue, Pottery Road, Old Route 100, Route 47 to Stafford Street | Pavement Improvement | 2009-08-07 | 2009-08-07 | 2009-10-01 | 2009-10-02 | 659355.23 | 3.000
7413 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06007 | The City of Crystal City will be doing aphalt resurfacing on Crystal City Heights Road from Missouri Ave. to Commercial Blvd | Pavement Improvement | 2009-08-19 | 2009-08-19 | 2010-02-10 | 2010-02-10 | 369773.76 | 1.400
7414 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06008 | Washington Special Road Distrct will be doning asphalt resurfacing on Bieker Road from S. Pointe Road to the Washington City limits. | Pavement Improvement | 2009-08-27 | 2009-08-27 | 2010-07-31 | 2010-07-30 | 192368 | 4.000
7415 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06009 | Jefferson County will be doing asphalt resurfacing on Antire Road from High Ridge Blvd. to the St. Louis County line | Pavement Improvement | 2009-12-15 | 2010-05-11 | 2010-08-27 | 2010-07-06 | 310289 | 3.960
7416 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06010 | Jefferson County will be installing guradrail on Old Lemay Ferry Road from Route M to Wedde Road | Safety/Traffic Management | 2010-05-10 | 2010-05-11 | 2010-12-01 | 2010-05-24 | 118646.97 | 0.430
7417 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06011 | Jefferson County will be doing asphalt resurfacing on River Street Road from Route K to Route 61/67 | Pavement Improvement | 2009-11-19 | 2009-11-23 | 2010-03-24 | 2010-03-24 | 50120.52 | 0.220
7418 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06012 | The City of De Soto will be doing asphalt resurfacing, concrete slab replacement, curb ramp replacement, curb and gutter, and street trees on Amvets Drive from S. Main Street to Route 21 | Pavement Improvement | 2010-02-24 | 2010-03-03 | 2010-08-31 | 2010-08-15 | 855706.1 | 1.100
7419 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06013 | Jefferson County will be doing asphalt resurfacing on Flucom Road from Route 67 to De Soto city limits | Pavement Improvement | 2010-03-30 | 2010-03-30 | 2010-06-25 | 2010-04-21 | 444224.57 | 4.380
7420 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06014 | Jefferson County will be doing asphalt resurfacing on Klondike (South) Road from Route E to McClain Street | Pavement Improvement | 2010-01-20 | 2010-03-29 | 2010-10-01 | 2010-04-20 | 441823 | 1.800
7421 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06015 | Festust Special Road District will be doing asphalt resurfacing on Scenic Dr., County Road, Cherry Ln., Scenic - Herculaneum city limits to Festus city limit, Cherry - Route Z to County Rd., County Ro | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2010-10-01 | 2009-10-05 | 419493.88 | 3.000
7422 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06016 | Jefferson County will be reconstructing and adding a center turn lane on Little Brennan Road from Route 30 to Gravois Road | Pavement Widening | 2010-05-10 | 2010-05-10 | 2011-04-01 | 2010-07-07 | 191719.39 | 0.100
7423 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS | ST. LOUIS (IL) | 02 | ES06017 | St. Louis County will be construction and completing the Maryland Heights Expressway Connector (4 lane freeway) from Page Ave. (Rte. 364) to Olive Blvd. (Rte. 340) | New Bridge Construction | 2010-04-19 | 2010-04-19 | 2012-09-01 |  | 20000000 | 2.500
7424 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06018 | The City of Cottleville will be constructing a new traffice signal at Route N and Brittany Cove | Pavement Widening | 2009-08-21 | 2009-08-21 | 2010-12-01 | 2010-08-30 | 157553.96 | 0.100
7425 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06019 | The City of O'Fallon will be doing asphalt Resurfacing on Main (Rte.M), Sonderen, East Pitman: Main St. (Rte. M) - I-70 to 3rd St., Sonderen - Wabash Ave. to I-70, East Pitman St. - Main St. to Sonde | Pavement Improvement | 2009-09-01 | 2009-09-01 | 2010-05-28 | 2010-05-05 | 599433.15 | 1.320
7426 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06020 | The City of St. Charles will be doing Phase 2 on the Fifth Street Corridor, which consist of widen lanes from three to five from First Capiol to Tompkins Street | Pavement Widening | 2010-03-10 | 2010-03-10 | 2010-08-01 | 2010-11-09 | 318002 | 0.120
7427 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 09 | ES06021 | St. Charles County will be installing a shared use lane on Route 94 from Defiance Road to Walnut Springs Road | Pavement Widening | 2009-09-08 | 2009-09-08 | 2010-10-01 | 2010-08-10 | 430000 | 0.500
7428 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06022 | The City of St. Peters will be doing traffic signal improvements on Mid Rivers Mall Drive from Cottleville Rd. to Cottleville Parkway. This will consist of installing video detection amd sidewalk rep | Pavement Improvement | 2010-10-07 | 2010-11-29 | 2011-03-31 | 2011-03-18 | 321307.77 | 0.740
7429 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS | ST. LOUIS (IL) | 02 | ES06023 | Great Streets Demonstration Project - Manchester Road - Rte. 141 to Rte. 109Engineering Planning and Design Study of entrances and exits and traffic flow. | Other | 2009-09-08 | 2009-09-10 | 2010-09-08 | 2011-02-23 | 1100000 | 5.000
7430 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS | ST. LOUIS (IL) | 01 | ES06024 | Engineering Design Study of Great Streets Demonstration Project - Natural Bridge Rd. - Lucas & Hunt Rd. to UMSL South Metrolink Station in Normandy | Other | 2009-10-13 | 2009-10-19 | 2012-01-31 |  | 998644.49 | 0.750
7431 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06025 | Great Streets Demostration Project on South Grand from Arsenel to McDonald in City of St. Louis to improve entrances and exits and traffic flow. | Other | 2009-07-10 | 2009-07-10 | 2011-12-01 |  | 890000 | 0.400
7432 | Underway | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06026 | Grand Center/Grand Blvd. Streetscape- Lindell to Page Ave.Sidewalk improvements, new pedestrian signs, crosswalks and traffic calming | Transportation Enhancements | 2009-08-12 | 2009-08-12 | 2011-12-01 |  | 2000000 | 0.660
7433 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06027 | St. Louis City will be doing improvements to South Grand from Arsenal to McDonald by installing a pedestrian signal and update sidewalks | Pavement Widening | 2010-01-15 | 2010-01-15 | 2011-12-01 |  | 1503740.28 | 0.400
7434 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06028 | St. Louis City will be doing streetscapes on Vandeventer Avenue, Kingshighway to Shaw; segment of Accomac. They will be adding pedestrian signal, solar powered lighting, and rain garden | Pavement Widening | 2009-08-12 | 2009-08-12 | 2010-12-01 | 2011-04-28 | 763777.67 | 0.450
7435 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06029 | The Land Clearance for Development Authority for the City of St. Louis will be doing reconstruction, reconstruct and new construction of sidewalks, improved railroad crossings, signal improvements at | Pavement Widening | 2009-07-29 | 2009-07-29 | 2011-12-01 |  | 2694079.5 | 0.600
7436 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06030 | St. Louis City will be doing repairs to Compton Avenue over Union Pacific Railroad from Chouteau to Spruce and bridge repairs | Bridge Improvement | 2010-01-08 | 2010-01-08 | 2011-08-01 | 2011-03-01 | 1255915.02 | 0.500
7437 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06031 | St. Louis City will be doing pedestrian lighting enhancements on Dr. Martin Luther King Road from Arlington West to city limits | Transportation Enhancements | 2010-06-07 | 2010-08-02 | 2011-12-01 |  | 949875.15 | 1.600
7438 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06032 | St. Louis City will be adding new pedestrian lighting on Manchester Road from Taylor Ave. to Sarah Ave. | Transportation Enhancements | 2010-01-07 | 2010-01-07 | 2011-07-01 | 2011-05-13 | 981044.13 | 0.670
7439 | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06033 | St. Louis City will be doing signal interconnect/Upgrade on Morgan Ford Road. This will consist of 11 signalized intersections from Arsenal Street to City limits. Interconneect traffic signals, signa | Safety/Traffic Management | 2009-07-24 | 2009-07-24 | 2011-12-31 |  | 1477016.57 | 3.740
7440 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06034 | The Land Clearance for Development Authority of the City of St. Louis will be doing mill/resurfacesurfacing and new curbs, bumpouts, sidewalks, ramps, lighting, and signals on North Sarah Street from | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2011-12-31 | 2011-07-29 | 1101252.57 | 0.260
7441 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06035 | St. Louis City will be doing overlay and pedestrian improvements on Good Fellow/Skinker. This will consist of asphalt mill and overlay, sidewalk improvements, new ADA compliant curb ramps, and stripin | Pavement Improvement | 2009-08-12 | 2009-08-12 | 2011-12-31 | 2011-09-16 | 3371273 | 7.300
7442 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06036 | South Broadway Streetscape - Courtois to Upton St..Traffic calming measures, access management, new lighting, sidewalks | Pavement Widening | 2009-08-12 | 2009-08-12 | 2010-03-01 | 2011-03-31 | 1025690.19 | 0.280
7443 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06037 | The City of Dardenne Prairie will be doing an intersection realignment at Post/Hanley and MO N | Pavement Widening | 2010-04-05 | 2010-05-17 | 2010-12-01 | 2010-08-26 | 371662.43 | 0.100
7444 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 09 | ES06038 | City of Lake St. Louis will be connecting the pedestrian and bike pathway from Northshire Lane to Prospect Village Drive | Transportation Enhancements | 2010-02-18 | 2010-03-30 | 2010-06-01 | 2010-05-21 | 41590.2 | 0.210
7445 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06040 | This project invovles the stabilization of the existing port muncipal dock at the St. Louis City Regional Port | Other | 2009-09-23 | 2009-09-23 | 2011-04-01 | 2011-03-16 | 400000 | 0.000
7446 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JASPER | JOPLIN | 07 | ES07001 | In Joplin, the city will be constructing a pedestrian and bicycle trail connecting the Frisco Greenway Trail to the intersection of Florida Avenue and Newman Road | Transportation Enhancements | 2010-02-11 | 2010-02-15 | 2010-09-01 | 2010-08-27 | 439500 | 1.500
7447 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JASPER | JOPLIN | 07 | ES07002 | In Carl Junction, the city will be doing the design and construction of a pedestrian and bicycle trail from Briarbrook Drive to Copper Oaks Drive. The beginning of this project starts where the previ | Transportation Enhancements | 2009-08-06 | 2009-08-06 | 2010-09-01 | 2010-08-12 | 172999.58 | 0.670
7448 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JASPER | JOPLIN | 07 | ES07003 | In Webb City, the city will be purchasing materials for the establishment of the Route 66 themed Welcome Center in Webb City | Transportation Enhancements | 2009-11-20 | 2009-11-20 | 2010-08-31 | 2010-08-24 | 25790.98 | 0.000
7449 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08001 | The City of Strafford will be constructing sidewalks along McCabe St. from Washington Avenue to just west of Cedar Drive in front of Strafford Schools. | Transportation Enhancements | 2010-02-16 | 2010-03-01 | 2010-06-16 | 2010-06-01 | 65074 | 0.000
7450 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | ES08002 | In Ozark, the city will be doing surface improvements by paving the existing Frisco Highline Trail from Springfield to Willard | Transportation Enhancements | 2009-12-11 | 2010-01-14 | 2010-01-01 | 2010-05-04 | 77475.65 | 0.200
7451 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08003 | This project includes the construction of sidewalks along Highway Z from the existing Frisco Highline trail to the Willard Recreation Center in the City of Willard. | Transportation Enhancements | 2009-10-16 | 2009-10-19 | 2010-01-01 | 2009-12-14 | 78375 | 0.600
7452 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08004 | This project will pave an existing segment of the Frisco Highline Trail from Willard to 3 miles north of Springfield | Transportation Enhancements | 2009-11-05 | 2009-11-06 | 2010-06-01 | 2009-11-24 | 186482 | 0.000
7453 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | ES08006 | This project will provide an analysis of existing and projected traffic in order to develop an efficient traffic plan on 3rd Street from Jackson St. to Church St. | Other | 2009-09-08 | 2009-09-08 | 2010-09-01 | 2010-03-25 | 13188 | 0.200
7454 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | ES08007 | This project consists of a Transportation Planning Study to determine priority corridors and priority projects with some prelminary scoping of transportation projects within the boundaries of the City | Other | 2009-09-23 | 2009-09-23 | 2010-09-01 | 2010-07-26 | 38039 | 0.000
7455 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08008 | In Battlefield, the city will be constructing sidewalks along Cloverdale from Elm North | Transportation Enhancements | 2009-11-04 | 2009-11-30 | 2010-09-01 | 2010-01-27 | 57691 | 0.000
7456 | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | ES08009 | This project will provide final design to improve safety and capacity at the intersection of Highway 160 & Highway 14 in the City of Nixa. | Other | 2009-08-11 | 2009-08-25 | 2010-11-01 | 2010-10-08 | 119913 | 5.700
7457 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | POLK |  | 07 | ES08010 | This project will pave a segment of the existing Frisco Highline Trail near Bolivar and pave the Wishart trailhead. | Transportation Enhancements | 2009-11-05 | 2009-11-06 | 2010-06-01 | 2010-04-19 | 151753.7 | 1.000
7458 | Completed | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08011 | Ozark Greenways will be paving the current aggregate Frisco Highline Trail from Farm Road 115 to the trailhead in Springfield. | Transportation Enhancements | 2010-05-18 | 2010-06-21 | 2010-06-01 | 2010-07-20 | 136782.9 | 0.000
7459 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | PHELPS |  | 08 | ES09001 | The City of St. James will replace inadequate and unsafe sidewalk and extend sidewalk where none exists, along Highway 68 from the downtown south to the city limits and on east and west Scioto Streets | Transportation Enhancements | 2009-12-12 | 2009-12-18 | 2010-01-12 | 2010-04-11 | 114166.3 | 0.750
7460 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | TEXAS |  | 08 | ES09002 | The City of Houston is constructing 1.1 miles of new five foot sidewalk along Airport Road, Lone Star Drive, and Westwood Drive on city owned property at the Houston Memorial Airport. The sidewalk is | Transportation Enhancements | 2009-10-23 | 2009-11-12 | 2009-12-01 | 2009-12-23 | 142096.84 | 1.100
7461 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CAPE GIRARDEAU |  | 08 | ES10001 | This project involves the construction of a high-water rail line that will allow port rail to operate during high-water events | Other | 2009-11-16 | 2009-11-16 | 2011-12-01 | 2012-02-24 | 890960.02 | 0.000
7462 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | NEW MADRID |  | 08 | ES10002 | This project involves extending a rail spur to a site for a new tenant. This includes rail extension, switch, crossings, and siding. | Safety/Traffic Management | 2009-09-30 | 2009-11-16 | 2010-07-01 | 2010-04-01 | 687888.2 | 0.000
7463 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STE GENEVIEVE |  | 03 | ES10003 | This project involves construction of phase 1 on a new port, which involves excavation and site developments. | Other | 2009-04-01 | 2009-04-01 | 2011-12-01 | 2012-02-28 | 931816.81 | 0.000
7464 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST FRANCOIS |  | 08 | ES10004 | The City of Farmington will be doing constructing on sidewalks on North Fleming Ave., St. Genevieve Ave., Forster Street, Franklin Street, and Walton Drive | Transportation Enhancements | 2010-06-01 | 2010-07-17 | 2010-08-29 | 2010-10-05 | 208807.77 | 1.740
7465 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | DUNKLIN |  | 08 | ES10005 | The City of Malden will be doing Phase II, which consists of renovation of downtown of sidewalks. This consist of Main St. from Douglas to Marion, main St from Madison to Decatur, and Laclede from Ma | Transportation Enhancements | 2010-05-21 | 2010-05-26 | 2010-10-13 | 2010-07-16 | 85988.16 | 0.500
7466 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | NEW MADRID |  | 08 | ES10006 | The City of New Madrid will be doing sidewalk construction on Crisler Street, Mott Street, Capitol Street, Waters Street, Main Street | Transportation Enhancements | 2010-04-29 | 2010-06-01 | 2010-09-28 | 2010-09-29 | 103111.19 | 0.600
7467 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | PERRY |  | 08 | ES10007 | The City of Perryville will be doing sidewalk construction on Schindler Road, State Street, Bredall Street, Waters Street, Rosati Court, Zeno Street, Bruce Street, Drury Lane | Transportation Enhancements | 2010-05-06 | 2010-06-01 | 2010-09-02 | 2010-09-08 | 207040.45 | 1.000
7468 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BUTLER |  | 08 | ES10008 | The City of Poplar Bluff will be doing sidewalk construction on Poplar Street, Fifth Street, and Vine Street. There will be curb and gutter improvements on Vine Street. Construction of trail connecti | Transportation Enhancements | 2010-05-25 | 2010-06-10 | 2010-09-28 | 2010-10-05 | 154629 | 1.000
7469 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | STODDARD |  | 08 | ES10009 | The City of Puxico will be doing sidewalk improvements on South East L. Hawks Street, East Owen Ave., South Hickman Street, and West Richard Ave. | Transportation Enhancements | 2010-04-19 | 2010-06-09 | 2010-08-26 | 2010-08-27 | 79045.95 | 0.280
7470 | Underway | C950 | Ferryboat | MISSOURI | LEWIS |  | 09 | FB03006 | This project involves port capital improvements. These improvements include making the existing road and staging area concrete, installing public restrooms and storage depot, and improving existing d | Other | 2010-01-05 | 2010-01-05 | 2012-03-01 |  | 188000 | 0.000
7471 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STE GENEVIEVE |  | 03 | FB08001 | This project is located at the Port of New Bourbon and consit of a ferry boat berthing, bank stabiization an construction of a mooring structure in Ste. Genevieve C | Other | 2009-04-01 | 2010-04-18 | 2012-03-01 | 2012-02-28 | 68183.19 | 0.000
7472 | Underway | C950 | Ferryboat | MISSOURI | MISSISSIPPI |  | 08 | FB10010 | This project invovles the installation of new enginees and coolers on an existing tug, and the purchase of a new barge. | Other | 2010-02-08 | 2010-02-22 | 2012-03-12 |  | 957500 | 0.000
7473 | Completed | C490 | OJT/SS | MISSOURI | STATEWIDE |  |  | FY09005 | The project is part of an ongoing program that is designed to increase participation among minorities, women and disadvantaged individuals in the highway construction workforce and train and prepare i | Other | 2010-01-13 | 2010-01-13 | 2011-12-31 | 2011-08-16 | 145000 | 0.000
7474 | Completed | C490 | OJT/SS | MISSOURI | BOONE |  | 09 | FY09006 | The project is part of an ongoing program that provides minorities, women and disadvantaged individuals the educational experiences to enhance work maturity skills, GED attainment, tools, equipment an | Other | 2010-01-13 | 2010-01-13 | 2011-12-31 | 2011-08-24 | 190433.54 | 0.000
7475 | Completed | C490 | OJT/SS | MISSOURI | JACKSON |  | 04 | FY10005 | This project consist of on the job training, supportive services, OJT/SS program in Kansas C | Other | 2010-07-27 | 2010-07-27 | 2011-12-31 | 2011-11-01 | 240851 | 0.000
7476 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ATCHISON |  | 06 | S001011 | This project consist of a thin lift asphalt overlay from Route 136 to I-29 in Atchison county | Pavement Improvement | 2009-06-08 | 2009-06-29 | 2009-10-01 | 2009-09-30 | 267860.32 | 3.750
7477 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | NODAWAY |  | 06 | S004007 | This project consist of a thin lift asphalt overlay from Route 148 to Route E in Nodaway county | Pavement Improvement | 2009-07-06 | 2009-08-24 | 2010-07-01 | 2009-09-24 | 395140.08 | 8.133
7478 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | NODAWAY |  | 06 | S006009 | This project consist of resurfacing roadway from Maryville west city limits to east city limits - Nodaway county | Pavement Improvement | 2010-03-08 | 2010-05-28 | 2010-12-01 | 2010-08-25 | 493913.06 | 2.299
7479 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ATCHISON |  | 06 | S007006 | This project consist of a thin lift asphalt overlay from Route C to Route 136 in Atchison county | Pavement Improvement | 2009-06-08 | 2009-06-29 | 2009-10-01 | 2009-09-30 | 593013.14 | 9.881
7480 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ANDREW |  | 06 | S029004 | This project consist of a thin lift asphalt overlay from Route 48 to Route E in Andrew county | Pavement Improvement | 2009-07-06 | 2009-08-24 | 2010-07-01 | 2009-10-21 | 420917.25 | 7.984
7481 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | S042005 | This project consist of a thin lift asphalt overlay to improve pavement condition from Route 6 to Route OO, near Clarksdale - Buchanan/Dekalb county | Pavement Improvement | 2010-03-08 | 2010-04-01 | 2010-11-01 | 2010-04-08 | 412652.93 | 8.253
7482 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | S058005 | This project consist of a thin lift asphalt overlay from Route 371 to Route MM in Buchanan county | Pavement Improvement | 2009-07-06 | 2009-09-25 | 2010-07-01 | 2009-11-30 | 213527.81 | 4.036
7483 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | CLINTON |  | 06 | S067011 | This project consist of a thin lift asphalt overlay from Route 69 to Route H in Clinton county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-12-03 | 599812.81 | 11.022
7484 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | S083013 | "This project consists of concrete pavement repair to the existing concrete roadway and a 3-3/4"" asphalt overlay over the existing concrete roadway along with a 3-3/4"" asphalt overlay of the existin | Pavement Improvement | 2009-08-10 | 2009-09-10 | 2009-12-01 | 2009-11-30 | 1886410.39 | 2.400
7485 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LIVINGSTON |  | 06 | S111009 | This project consist of a thin lift asphalt overlay from the Daviess County line to Route 65 in Livingston county | Pavement Improvement | 2009-06-08 | 2009-08-06 | 2009-11-01 | 2009-09-09 | 1228044.9 | 12.130
7486 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | MACON |  | 09 | S116007 | This project consist of a thin lift asphalt overlay from Route 63 to Route 156 in LaPlata in Macon county | Pavement Improvement | 2009-04-06 | 2009-04-10 | 2009-12-01 | 2009-04-15 | 74654.59 | 0.916
7487 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MACON |  | 09 | S124007 | This project consist of a thin lift asphalt overlay in Macon County from Route 63 to the Knox county line | Pavement Improvement | 2009-04-06 | 2009-04-10 | 2009-12-01 | 2009-04-24 | 541918.62 | 8.989
7488 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S148003 | This project consist of resurfacing roadway from Business 63 to Route 63 - Randolph county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-06-08 | 148171.91 | 1.067
7489 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S152001 | This project consist of resurfacing roadway from Business 63 to Route 63 - Randolph county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-07-21 | 115390.4 | 1.096
7490 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LEWIS |  | 09 | S182010 | This project consist of a thin lift asphalt overlay from Route 67 in Ewing to Route 61 - Lewis county | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-11-01 | 2010-09-28 | 560300 | 12.576
7491 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | SCHUYLER |  | 06 | S189007 | This project consist of a thin lift asphalt overlay from the Iowa state line to Route 63 in Schuyler county | Pavement Improvement | 2009-04-06 | 2009-04-10 | 2009-12-01 | 2009-04-25 | 547629.5 | 8.502
7492 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MARION |  | 09 | S192003 | This project consist of a thin lift asphalt overlay on Route W from Route 61 north junction to Route 61 south junction, and Route 61 outer road from Route W to 0.3 miles south of Route W in Marion cou | Pavement Improvement | 2009-04-06 | 2009-05-12 | 2009-12-01 | 2009-06-02 | 179958.87 | 3.378
7493 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S197005 | This project consist of resurfacing roadway from Macon county line to Route JJ - Randolph county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-06-28 | 885200 | 13.515
7494 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S203003 | This project consist of resurfacing roadway from County Road 103 to Route 24 - Randolph county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-06-08 | 141559.17 | 2.225
7495 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S205005 | This project consist of a thin lift asphalt overlay from Business Route 63 to Route B in Randolph county | Pavement Improvement | 2009-06-08 | 2009-10-23 | 2009-12-01 | 2009-10-28 | 577607.51 | 9.560
7496 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MONROE |  | 09 | S206007 | This project consist of a thin lift asphalt overlay from Route 24 to Route J in Ralls and Monroe counties | Pavement Improvement | 2009-04-06 | 2009-05-12 | 2009-12-01 | 2009-05-28 | 228386.46 | 4.006
7497 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | S209017 | This project consist of resurfacing roadway from Route TT to I-70 Drive SW in the City of Columbia - Boone county | Pavement Improvement | 2010-03-08 | 2010-04-06 | 2010-12-01 | 2010-07-16 | 47499.67 | 1.113
7498 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | SHELBY |  | 09 | S233005 | This project consist of a thin lift asphalt overlay from Business Route 36 to Route 24 in Shelby and Monroe counties | Pavement Improvement | 2009-06-08 | 2009-10-23 | 2009-12-01 | 2009-11-10 | 1123546.94 | 22.130
7499 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MONROE |  | 09 | S249007 | This project consist of a thin lift asphalt overlay from Route 24 in Madison to the Audrain county line - Monroe county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-06-08 | 434212.05 | 9.725
7500 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LINCOLN |  | 02 | S258009 | This project consist of a thin lift asphalt overlay from Route O to north junction to Route UU in Silex - Lincoln county | Pavement Improvement | 2010-02-08 | 2010-05-24 | 2010-11-01 | 2010-06-08 | 478200 | 10.886
7501 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LINCOLN |  | 02 | S264004 | This project consist of a thin lift asphalt overlay from Old Route 61 to Route W in Lincoln county | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-01 | 2009-07-13 | 305352.49 | 6.361
7502 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LINCOLN |  | 02 | S270004 | This project consist of a thin lift asphalt overlay from Route Y to Route 47 in Lincoln county | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-01 | 2009-06-25 | 261982.39 | 5.259
7503 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | AUDRAIN |  | 09 | S273003 | This project consist of a thin lift asphalt overlay from Route V in Vandalia to Roue K east junction - Audrain county | Pavement Improvement | 2010-02-08 | 2010-05-24 | 2010-11-01 | 2010-07-15 | 375800 | 10.886
7504 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LEWIS |  | 09 | S283005 | This project consist of a thin lift asphalt overlay from Route E to Route 6 in LaBelle - Lewis county | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-11-01 | 2010-04-08 | 377400 | 8.183
7505 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | S286005 | This project consist of pavement improvements on Route 273 from Route JJ to I-29 and Spur 92 from Route 273 to Route 92 in Platte county | Pavement Improvement | 2009-06-08 | 2009-10-05 | 2009-12-01 | 2009-11-30 | 566545.02 | 4.907
7506 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | S290005 | This project consist of a bridge replacement over I-29 in Platte City. Project involves bridge A0200 | Bridge Replacement | 2010-03-08 | 2010-04-01 | 2010-10-01 | 2010-07-22 | 1117203.88 | 0.010
7507 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RALLS |  | 09 | S301018 | This project consist of a thin lift asphalt overlay from Route EE to Route 154 in Ralls county | Pavement Improvement | 2009-04-06 | 2009-05-12 | 2009-12-01 | 2009-05-20 | 414988.04 | 7.713
7508 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RALLS |  | 09 | S301019 | This project consist of a thin lift asphalt overlay from Route J to Route 19 in Ralls county | Pavement Improvement | 2009-04-06 | 2009-05-12 | 2009-12-01 | 2009-05-19 | 248345.13 | 4.684
7509 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | S304023 | A $1.2 million contract awarded to Musselman and Hall Contractors, LLC for nearly three miles of sidewalk improvements. Included are new upgrades to the existing sidewalk and adding curb ramps to acco | Transportation Enhancements | 2009-08-10 | 2009-08-10 | 2010-02-01 | 2009-12-01 | 1373073.14 | 2.623
7510 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE |  |  | S321005 | This project consist of a thin lift asphalt overlay from Route 47 to the Warren County line in Lincoln County, and from the Lincoln County line to I-70 north outer road in Warren county | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-01 | 2009-09-30 | 542103.37 | 11.537
7511 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LINCOLN |  | 02 | S321006 | This project consist of a thin lift asphalt overlay from Route Z to Route E in Silex - Lincoln county | Pavement Improvement | 2010-02-08 | 2010-05-24 | 2010-11-01 | 2010-05-27 | 198700 | 4.456
7512 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PIKE |  | 09 | S328004 | This project consist of a thin lift asphalt overlay from Business 61 in Bowling Green to County Road 486 - Pike county | Pavement Improvement | 2010-02-08 | 2010-05-24 | 2010-11-01 | 2010-09-10 | 130700 | 2.360
7513 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | S340011 | This project consist of resurfacing roadway from North Fork Creek in the City of Columbia to Route J in Boone county | Pavement Improvement | 2010-03-08 | 2010-04-06 | 2010-12-01 | 2010-07-16 | 474752.55 | 8.900
7514 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | S342002 | This project consist of resurfacing roadway from Route K to the end of maintenance in the City of Columbia - Boone county | Pavement Improvement | 2010-03-08 | 2010-04-06 | 2010-12-01 | 2010-07-16 | 98189.77 | 18.597
7515 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | RAY |  | 04 | S349005 | This project consist of a thin lift asphalt overlay from Route C to Route 10 in Ray county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-12-03 | 281304.36 | 5.763
7516 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RAY |  | 04 | S351005 | This project consist of a thin lift asphalt overlay from Route U to Route 10 in Ray county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-12-03 | 231387.71 | 5.117
7517 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | S375003 | This project consist of a thin lift asphalt overlay from Route 124 to I-70 | Pavement Improvement | 2009-06-08 | 2009-08-10 | 2009-12-01 | 2009-11-03 | 856658.77 | 19.186
7518 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CALLOWAY |  | 09 | S383010 | This project will widen Route OO in Callaway couty to three lanes to add capacity and improve safty in holts Summit. | Pavement Widening | 2009-09-15 | 2009-09-15 | 2010-12-01 | 2010-11-17 | 449716.85 | 0.841
7519 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | LAFAYETTE |  | 04 | S388005 | This project consist of a thin lift asphalt overlay from Gillespie Drive to Route O in LaFayette county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-12-03 | 552746.39 | 12.287
7520 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WARREN |  | 09 | S417004 | This project consist of improvements on intersection and outer road, which is located 0.2 miles south of I-70 in Warren county | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-12-01 | 2010-09-30 | 509306.58 | 0.631
7521 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WARREN |  | 09 | S429007 | This project consist of a thin lift asphalt overlay from Route T to Route 94 in Warren and St. Charles counties | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-01 | 2009-07-23 | 179695.27 | 3.500
7522 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S434005 | This project consist of intersection improvements at Winchester Road in Sedalia in Pettis county | Pavement Improvement | 2010-01-04 | 2010-04-01 | 2010-12-01 | 2010-06-10 | 354059.03 | 0.300
7523 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S434006 | This project consist of resurfacing roadway from the railroad tracks to Route 65 in Sedalia in Pettis county | Pavement Improvement | 2010-03-08 | 2010-04-13 | 2010-12-01 | 2010-10-22 | 326363.51 | 1.336
7524 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S434007 | This project consist of resurfacing roadway from west of Route 65 to Quisenberry Road in the City of Sedalia - Pettis county | Pavement Improvement | 2010-03-08 | 2010-04-14 | 2010-12-01 | 2010-05-21 | 86346.1 | 2.000
7525 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S434008 | This project consist of resurfacing various roadways within the Missouri State fairgrounds in the City of Sedalia - Pettis county | Pavement Improvement | 2010-03-08 | 2010-04-14 | 2010-12-01 | 2010-05-06 | 212019.54 | 0.003
7526 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | JOHNSON |  | 04 | S467005 | This project consist of pavement improvements from Route 50 to Route 2 in Johnson county | Pavement Improvement | 2009-06-08 | 2009-08-18 | 2009-12-01 | 2009-10-14 | 1258926.82 | 16.143
7527 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | COLE |  | 04 | S490010 | This project consists of improvements at the intersection of Route 50 and Route 179 in Jefferson City. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-07-01 | 2010-11-01 | 6806623.77 | 0.300
7528 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | MONITEAU |  | 04 | S498006 | This project consist of pavement improvements from Route AA to Route 52 in Cole, Moniteau, and Morgan counties | Pavement Improvement | 2009-05-26 | 2009-06-10 | 2009-12-01 | 2009-08-28 | 2071328.66 | 21.100
7529 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S539008 | This project consist of a thin lift resurfacing from the intersection of 28th street and Ingrm Avenue to Route V, south of Sedalia - Pettis county | Pavement Improvement | 2010-03-08 | 2010-04-14 | 2010-12-01 | 2010-05-03 | 319800 | 8.010
7530 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | COOPER |  | 06 | S567005 | This project consist of a thin lift resurfacing from Route 135 to old Route 50 - Cooper county | Pavement Improvement | 2010-03-08 | 2010-04-14 | 2010-12-01 | 2010-05-14 | 306439.9 | 7.838
7531 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | COOPER |  | 06 | S573009 | This project consist of pavement improvements from I-70 to Main Street (old Route B) in the City of Booneville - Cooper county | Pavement Improvement | 2010-02-08 | 2010-03-22 | 2010-11-01 | 2010-07-06 | 1644521.53 | 3.406
7532 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | MONITEAU |  | 04 | S579017 | This project consist of a thin lift asphalt overlay from Route O to Route C in Moniteau county | Pavement Improvement | 2009-06-08 | 2009-06-12 | 2009-12-01 | 2009-10-19 | 552815.17 | 10.500
7533 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | MILLER |  | 09 | S579018 | This project consist of resurfacing roadway from Salem Road to Route 54 in the City of Eldon - Miller county | Pavement Improvement | 2010-03-08 | 2010-05-03 | 2010-12-01 | 2010-06-04 | 122219.51 | 2.331
7534 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | MILLER |  | 09 | S583009 | This project consist of resurfacing roadway from Salem Road to Route 52 in the City of Eldon - Miller county | Pavement Improvement | 2010-03-03 | 2010-05-03 | 2010-12-01 | 2010-06-04 | 79907.87 | 1.301
7535 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | ST FRANCOIS |  | 08 | S638004 | This project consist of a thin lift asphalt overlay from the Washington County line to the City of Bonne Terre in St. Francois county | Pavement Improvement | 2009-06-08 | 2009-09-03 | 2009-12-01 | 2009-09-16 | 181075 | 5.219
7536 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST FRANCOIS |  | 08 | S638005 | This project consist of a thin lift asphalt overlay from the City of Bonne Terre to Route 67 in St. Francois county | Pavement Improvement | 2009-06-08 | 2009-09-03 | 2009-12-01 | 2009-09-16 | 104275.83 | 1.788
7537 | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | IRON |  | 08 | S670010 | This project consistes of ADA sidewalk improvements on Route M from Shepherd Mountain Road to Burnett Street in Ironton, 0.275 miles. | Transportation Enhancements | 2010-01-04 | 2010-03-29 | 2010-06-01 | 2010-04-20 | 122869.5 | 0.282
7538 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | VERNON |  | 04 | S706003 | This project consist of a thin lift asphalt overlay from Route 54 to 0.9 mile north of Highland in Vernon county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-04-27 | 111147.54 | 2.377
7539 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | VERNON |  | 04 | S708004 | This project consist of a thin lift asphalt overlay from Business 71 to County Road 507 in Vernon county | Pavement Improvement | 2009-04-20 | 2009-04-18 | 2009-12-01 | 2009-05-07 | 110527.8 | 2.489
7540 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | VERNON |  | 04 | S710009 | This project consist of a thin lift asphalt overlay from Route 54 to Route F in Vernon county | Pavement Improvement | 2009-04-18 | 2009-04-20 | 2009-12-01 | 2009-04-27 | 259900.93 | 5.913
7541 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | POLK |  | 04 | S736004 | This project consist of a thin lift asphalt overlay from Route 123 to Route 13 in Polk county | Pavement Improvement | 2009-06-08 | 2009-07-14 | 2009-12-01 | 2009-09-14 | 333600 | 10.900
7542 | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | WASHINGTON |  | 08 | S755002 | This project consist of resurfacing roadway from Route 8 to Route 21 in Potosi - Washington county | Pavement Improvement | 2010-03-08 | 2010-04-26 | 2010-12-01 | 2010-10-28 | 90998.66 | 1.518
7543 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | JASPER |  | 07 | S770004 | This project consist of a thin lift asphalt overlay from Route J to Route 66 in Jasper county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-06-18 | 208244.24 | 4.446
7544 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | JASPER |  | 07 | S776011 | This project consist of widening Route FF to include a center two-way left turn lane form US 71 to Prigmor Avenue in Jasper/Newton counties | Pavement Improvement | 2009-08-03 | 2009-09-30 | 2010-11-01 | 2010-07-01 | 1939830.56 | 1.169
7545 | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | JASPER | JOPLIN | 07 | S776012 | This project consists of constructing new signalized intersection and turn lanes on route FF, one mile east of Route 71. Work includes grading, asphalt pavement and new signals. | Pavement Improvement | 2009-05-29 | 2009-05-29 | 2010-11-01 | 2010-07-01 | 1376841.2 | 0.200
7546 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STE GENEVIEVE |  | 03 | S805002 | This project consists of bridge replacement, asphalt overlay and shoulder widening on Route B in Ste Genevieve county. | Pavement Widening | 2010-02-25 | 2010-02-25 | 2010-12-01 | 2010-11-19 | 2924762.15 | 13.756
7547 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STE GENEVIEVE |  | 03 | S811005 | This project consist of a thin lift asphalt overlay from Route 51 to Route 61 in Ste. Genevieve and Perry counties | Pavement Improvement | 2009-06-08 | 2009-09-03 | 2009-12-01 | 2009-09-12 | 329807.35 | 6.844
7548 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | JASPER |  | 07 | S853002 | This project consist of a thin lift asphalt overlay from Route Z to Route P in Jasper county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-06-18 | 169926.73 | 3.959
7549 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WRIGHT |  | 08 | S926008 | This project consist of a thin lift asphalt overlay from Hartville to Route 95 - Wright county | Pavement Improvement | 2010-02-08 | 2010-09-17 | 2010-12-01 | 2010-09-17 | 568200 | 12.949
7550 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | S938008 | This project consist of a thin lift asphalt overlay from Route AB to Route 160 in Greene county | Pavement Improvement | 2009-06-08 | 2009-07-14 | 2009-12-01 | 2009-08-19 | 260617.29 | 5.417
7551 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | WEBSTER |  | 04 | S946008 | This project consist of a thin lift asphalt overlay from Route 60 to 1.0 mile west of Route FF in Webster county | Pavement Improvement | 2009-06-08 | 2009-09-09 | 2009-12-01 | 2009-09-25 | 51870.58 | 1.780
7552 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | S947011 | This project consist of a thin lift asphalt overlay from south of Route KK to north of Valley Water Mill Road in Greene county | Pavement Improvement | 2009-06-08 | 2009-09-11 | 2009-12-01 | 2009-12-01 | 158145.83 | 3.857
7553 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | POLK |  | 04 | S947012 | This project consist of pavement and shoulder improvements from Route 32 to Route WW in Polk and Greene counties | Pavement Improvement | 2009-06-08 | 2009-09-11 | 2009-12-01 | 2009-12-01 | 1273000 | 20.570
7554 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | S953005 | This project consist of a thin lift asphalt overlay from Route 160 to Route 266 in Greene county | Pavement Improvement | 2009-06-08 | 2009-07-14 | 2009-12-01 | 2009-08-19 | 297598.83 | 6.121
7555 | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WEBSTER |  | 04 | S967004 | This project consist of a thin lift asphalt overlay from Route AD to Business Route 60 in Webster county | Pavement Improvement | 2009-06-08 | 2009-09-09 | 2009-12-01 | 2009-09-25 | 163937.35 | 5.683
7556 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | MCCONE, CARTER, PHILLIPS, DAWSON, PRAIRIE, WIBAUX, VALLEY |  | 01 | 0002874 | Glendive District multiple location culvert replacement, abandonment, and major maintenance project. | Bridge Improvement | 2010-02-22 | 2010-04-09 | 2011-01-20 | 2011-12-07 | 2545862
7557 | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 0015090 | Construct New Bypass segment - US 93 to Airport Road | New Construction | 2009-12-21 | 2009-12-28 | 2011-12-20 | 2012-02-24 | 8148323
7558 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 0015091 | Construct New Bypass segment - Airport Road to Foys Lake Road | New Construction | 2009-11-30 | 2010-02-03 | 2011-12-20 | 2011-11-29 | 5361624
7559 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 0015092 | Construct New Bypass segment - Foys Lake Road to US 2 | New Construction | 2009-11-30 | 2010-02-03 | 2011-12-20 | 2011-11-29 | 7780165
7560 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 0016073 | Wetland mitigation in the NW quadrant of the I-90 East Main Street Interchange in Bozeman. | Other | 2009-07-06 | 2009-08-03 | 2009-12-01 | 2010-01-04 | 297781.83
7561 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 0025050 | Reconstruction of existing Wylie Drive in Lewis & Clark County. | Safety/Traffic Management | 2009-08-03 | 2009-08-03 | 2010-12-20 | 2010-10-26 | 1160898
7562 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | TETON |  | 01 | 0032033 | Replacement of the US 89 Big Muddy Creek Bridge, North of Bynum | Bridge Replacement | 2009-07-20 | 2009-09-10 | 2010-12-20 | 2011-12-14 | 2571581 | 0.400
7563 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | GLACIER |  | 01 | 0034013 | Overlay, Slope Flattening & Widening on US 89 within the Blackfeet Reservation | Pavement Improvement | 2009-07-06 | 2009-07-13 | 2010-12-20 | 2011-09-19 | 10519169.04 | 8.930
7564 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | PARK |  | 01 | 0034026 | Off site wetland mitigation reserve for Watershed #13 - Upper Yellowstone in Park County | Other | 2009-07-20 | 2009-09-09 | 2009-12-01 | 2010-06-10 | 390806.9
7565 | Completed | C220,C240 | Highway Infrastructure Investment Grant | MONTANA | LAKE |  | 01 | 0052152 | Construct a Bicycle/Pedestrian Overcrossing Bridge over US 93 in Pablo. | Transportation Enhancements | 2010-04-26 | 2010-05-03 | 2011-01-01 | 2011-07-26 | 2732433.36 | 0.000
7566 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | RAVALLI |  | 01 | 0071118 | Reconstruct and widen approximately 1.8 miles of US-93 near Stevensville | Pavement Widening | 2009-08-12 | 2009-08-17 | 2010-12-20 | 2010-12-09 | 5405512 | 1.855
7567 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MONTANA | ROOSEVELT |  | 01 | 0110062 | Reconstructing 6.8 miles of US 2, starting 6.69 miles east of Brockton in Roosevelt County. | Pavement Improvement | 2010-11-16 | 2010-11-17 | 2012-12-20 |  | 6802132.02 | 6.790
7568 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MONTANA | PARK |  | 01 | 0111051 | 4.7 mile mill and ovelay of P-11 northeast of Livingston | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-12-20 | 2011-01-31 | 2762413 | 4.700
7569 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | MADISON |  | 01 | 0131045 | Replacement of an existing irrigation siphon with a culvert on US 287 south of Cameron | Pavement Improvement | 2009-10-05 | 2009-10-21 | 2010-06-01 | 2010-05-25 | 349126.76 | 0.000
7570 | Underway | C200 | Highway Infrastructure Investment Grant | MONTANA | SILVER BOW |  | 01 | 0152081 | Replace I-15 Structures near Butte. | Pavement Improvement | 2010-04-05 | 2010-04-12 | 2012-12-20 |  | 7302564 | 1.311
7571 | Underway | C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 0154089 | I 15 Dearborn Rest Area Replacement | Safety/Traffic Management | 2009-08-14 | 2010-01-08 | 2010-12-20 |  | 3698786
7572 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | CARTER |  | 01 | 0271009 | Bridge Replacement Project on MT 7 North of Ekalaka | Pavement Improvement | 2009-08-03 | 2009-09-15 | 2010-12-20 | 2011-12-29 | 2236426 | 0.000
7573 | Underway | C240 | Highway Infrastructure Investment Grant | MONTANA | FALLON |  | 01 | 0272019 | Reconstruction of the existing roadway and structure work on MT 7 | Pavement Improvement | 2009-09-21 | 2009-09-28 | 2011-12-20 |  | 7061998 | 5.321
7574 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | DANIELS |  | 01 | 0322016 | 14.2 mile chip seal on MT 13 in Daniels County north of Scoby | Pavement Improvement | 2009-06-15 | 2009-06-29 | 2009-12-20 | 2009-12-21 | 450273.2 | 14.292
7575 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | SHERIDAN |  | 01 | 0341009 | 15.3 mile overlay on MT 16 between Plentywood and the Port of Raymond in Sheridan County. | Pavement Improvement | 2009-08-17 | 2010-06-01 | 2010-12-20 | 2010-11-19 | 2612251 | 15.300
7576 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | LAKE, SANDERS, FLATHEAD |  | 01 | 0361011 | Reconstruct a 10 mile segment of MT-28, beginning at milepost 26.1 and ending approximately 10 miles west of Dayton. | Pavement Improvement | 2010-03-01 | 2010-03-02 | 2012-12-20 | 2011-12-27 | 6465635 | 10.000
7577 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | BIG HORN |  | 01 | 0371033 | Mill and fill 5.5 miles of US 212 in Big Horn County and within the Northern Cheyenne Reservation. | Pavement Improvement | 2009-07-17 | 2009-07-21 | 2010-12-20 | 2009-12-04 | 2144398.99 | 5.580
7578 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | ROSEBUD |  | 01 | 0391039 | 8.1 mile pavement preservation, minor widening & pavement marking/guardrail upgrade on MT 39 in Rosebud County, just north of the Northern Cheyenne Reservation. | Pavement Improvement | 2009-06-08 | 2009-06-12 | 2009-12-20 | 2009-12-08 | 1360255.2 | 8.168
7579 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | DAWSON |  | 01 | 0512004 | 9 mile overlay on MT 200 west of Richey, in Dawson County | Pavement Improvement | 2009-06-22 | 2009-07-13 | 2009-12-20 | 2009-12-21 | 1989865.8 | 9.030
7580 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 0602073 | Reconstruct 0.65 mile segment of 10th Avenue South - between 26th and 20th St in Great Falls | Pavement Widening | 2010-03-15 | 2010-03-15 | 2011-12-20 | 2012-01-05 | 3870925 | 0.650
7581 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | JEFFERSON |  | 01 | 0691027 | Widen and overlay the existing MT 69 roadway south of Elk Horn Road, south east of Boulder. | Pavement Improvement | 2010-03-08 | 2010-04-05 | 2011-12-20 | 2011-11-16 | 7195220 | 9.500
7582 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 0861040 | 14.6 mile chip seal on MT 86 northeast of Bozeman in Gallatin County. | Pavement Improvement | 2009-07-06 | 2009-07-13 | 2009-12-20 | 2009-10-22 | 830804.85 | 14.630
7583 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 0906087 | Reconstruction of the I-90 East Three Forks Interchange | Pavement Improvement | 2009-10-05 | 2009-10-19 | 2011-12-20 | 2011-02-02 | 3437768 | 0.265
7584 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | SWEET GRASS |  | 01 | 0907089 | 5 mile mill and resurface of I 90 in Sweet Grass County | Pavement Improvement | 2009-08-17 | 2010-04-05 | 2010-12-20 | 2010-11-22 | 2703657 | 5.003
7585 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 0908157 | Cold mill and overlay I -90 at the Pinehills Interchange and 3.2 miles to the west. | Pavement Improvement | 2009-08-05 | 2009-08-08 | 2009-12-20 | 2009-12-04 | 1152304.1 | 3.285
7586 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE, BIG HORN |  | 01 | 0909098 | 13.3 mile full width overlay of I 90. Ramps will be cold milled and overlaid. The rest area parking lot will be crack sealed and s&c. | Pavement Improvement | 2009-06-01 | 2009-08-13 | 2010-12-20 | 2010-12-01 | 8170364 | 13.300
7587 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE |  | 01 | 0941068 | Mill, overlay, and seal & cover a 12.1 mile segment of the I-94 roadway and bridge decks fromPompey's Pillar to Waco, east of Billings | Pavement Improvement | 2010-07-06 | 2010-09-21 | 2011-12-20 | 2011-12-27 | 4307668 | 12.122
7588 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | CUSTER, ROSEBUD, DAWSON, WIBAUX |  | 01 | 0943059 | I 94 Bridge Deck Rehabilitation In Rosebud County | Bridge Improvement | 2009-08-03 | 2009-08-10 | 2010-12-20 | 2011-11-01 | 5498221 | 0.000
7589 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | WIBAUX |  | 01 | 0947028 | 6.2 mile mill and fill on I 94 east of Wibaux, in Wibaux County. | Pavement Improvement | 2009-07-20 | 2009-07-21 | 2009-12-20 | 2009-10-22 | 1078036.68 | 6.298
7590 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 1011004 | Reconstruction of the Smelter Ave. & 10th St. North Intersection | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-12-20 | 2010-11-23 | 1920221 | 0.000
7591 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 1028004 | 1.4 mile overlay on Hardin Road in Billings | Pavement Improvement | 2009-06-01 | 2009-06-26 | 2010-06-01 | 2010-09-14 | 484031 | 1.460
7592 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 1031009 | Reconstruct an approximate 1.7 mile segment of Shilo Road from 2 lane to 4 lane - Billings | Pavement Widening | 2009-06-01 | 2009-06-15 | 2010-12-20 | 2011-09-20 | 9301727 | 1.714
7593 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 1031011 | Reconstruct the remaining 2.11 mile segment of Shiloh Road - Billings | Pavement Widening | 2009-11-02 | 2009-11-13 | 2011-12-20 | 2011-12-08 | 5356482 | 2.117
7594 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 1099068 | Includes constructing a 200 foot long tunnel and approximately 300 feet of hard surface for a bike/ped facility under Main Street at Alkali Creek in Billings. | Transportation Enhancements | 2010-07-07 | 2010-07-07 | 2011-01-01 | 2010-12-13 | 1000000 | 0.001
7595 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | SILVER BOW |  | 01 | 1806008 | 0.7 mile mill and fill on Front Street in Butte | Pavement Improvement | 2009-06-22 | 2009-06-23 | 2010-12-20 | 2010-12-20 | 1531273 | 0.700
7596 | Underway | C200,C240 | Highway Infrastructure Investment Grant | MONTANA | SILVER BOW |  | 01 | 1810004 | Seal and Cover existing roadway on Grand Avenue -between Florence and Continental in Butte | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2010-12-20 |  | 1293112 | 1.300
7597 | Underway | C240 | Highway Infrastructure Investment Grant | MONTANA | PHILLIPS |  | 01 | 2081006 | Reconstruction of 9.4 miles of Secondary 208 between Whitewater and US 191 | Pavement Improvement | 2009-11-30 | 2010-03-29 | 2012-12-20 |  | 5849877 | 9.424
7598 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 2351009 | Reconstruct the remaining section of State Secondary 235 east of MT 85, from mile point 0.00 to 1.95 (Love Lane), Gallatin County. | Pavement Improvement | 2010-11-16 | 2010-12-20 | 2012-12-20 |  | 4220424 | 1.950
7599 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 2351011 | Reconstruct existing State Secondary 235 east of MT 85 | Pavement Improvement | 2009-10-05 | 2009-10-29 | 2010-12-20 |  | 5199155 | 2.550
7600 | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | LINCOLN |  | 01 | 2601005 | 3.5 mile chip seal on S 260 north of Libby | Pavement Improvement | 2009-07-06 | 2009-07-07 | 2009-12-20 | 2009-10-05 | 167705.45 | 3.500
7601 | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | GRANITE |  | 01 | 2711010 | 2.3 mile chip seal on S 271 northeast of Drummond in Powell County | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2009-12-20 | 2009-09-11 | 98178.62 | 2.300
7602 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 2791013 | Installing post mounted flashers at the intersection of S-279 & S 231 north of Helena | Safety/Traffic Management | 2009-08-03 | 2009-08-20 | 2009-11-01 | 2010-04-19 | 29952.02 | 0.800
7603 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 2801019 | Installing post mounted flashers on York Road northeast of Helena | Safety/Traffic Management | 2009-08-03 | 2009-08-20 | 2009-11-01 | 2010-04-19 | 31339.73 | 0.200
7604 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | MEAGHER |  | 01 | 2941008 | Reconstruction of the roadway and structure work on State Secondary 294 | Pavement Improvement | 2010-01-04 | 2010-03-02 | 2011-12-20 | 2012-01-11 | 4001426 | 2.120
7605 | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | CARBON |  | 01 | 3081026 | 7.7 mile overlay on S-308 in Carbon County west of Belfry | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-12-20 | 2009-12-23 | 1271776.2 | 7.700
7606 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | CARTER |  | 01 | 3231029 | Pave State Secondary 323 from RP 24.83 to 37.1 This is the section that is currently under contract with a total reconstruct to a all weather gravel surface. | Pavement Improvement | 2009-07-06 | 2009-07-16 | 2010-12-20 |  | 8103869 | 12.274
7607 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 3275813 | 2.6 mile seal and cover on a state highway west of Missoula. | Pavement Improvement | 2009-07-06 | 2009-07-07 | 2009-12-20 | 2009-10-27 | 254647.34 | 2.600
7608 | Completed | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | STILLWATER |  | 01 | 4211004 | Reconstruction of the existing roadway and constructing bus turn arounds on State Secondary 421 7 km E. of Columbus | Pavement Improvement | 2009-10-05 | 2009-10-23 | 2010-12-20 | 2011-11-08 | 3404820 | 2.732
7609 | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 4241008 | 4.6 mile chip seal on S 424 west of Kalispell | Pavement Improvement | 2009-06-29 | 2009-06-30 | 2009-12-20 | 2009-08-20 | 164937.05 | 4.610
7610 | Underway | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 4301008 | Reconstruction of the existing roadway and structure work on Canyon Ferry Road | Pavement Improvement | 2009-10-05 | 2009-10-09 | 2011-12-20 |  | 7387082 | 4.200
7611 | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 5031010 | 3.5 mile chip seal on S 503 southwest of Kalispell | Pavement Improvement | 2009-06-29 | 2009-06-30 | 2009-12-20 | 2009-08-20 | 125547.93 | 3.500
7612 | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | MINERAL, MISSOULA |  | 01 | 5071008 | 2.4 mile mill and fill on S 507 east of Alberton, Missoula County | Pavement Improvement | 2009-06-22 | 2009-07-22 | 2009-12-20 | 2009-10-26 | 418403.68 | 2.498
7613 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5205024 | 0.9 mile overlay on River Drive in Great Falls | Pavement Improvement | 2009-07-20 | 2009-08-17 | 2009-12-20 | 2010-02-10 | 532924.54 | 0.940
7614 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5208002 | 0.7 mile overlay of Park Drive in Great Falls. | Pavement Improvement | 2009-07-20 | 2009-08-10 | 2009-12-20 | 2010-02-10 | 323973.6 | 0.700
7615 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5209005 | 0.6 mile overlay of 6th Street in Great Falls. | Pavement Improvement | 2009-07-20 | 2009-08-10 | 2009-12-20 | 2010-02-10 | 258322.6 | 0.610
7616 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5210018 | 0.18 mile mill and fill on 1st Avenue NW of River Drive in Great Falls | Pavement Improvement | 2009-07-20 | 2009-08-17 | 2009-12-20 | 2010-02-10 | 277683.91 | 0.180
7617 | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5299080 | Multiple Location sidewalk Improvment Project - Great Falls | Transportation Enhancements | 2009-06-22 | 2009-07-06 | 2010-02-01 | 2010-09-08 | 1045346.64
7618 | Completed | C220,C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5299081 | Phase 3 of a Multiple Location sidewalk Improvment Project - Great Falls | Transportation Enhancements | 2009-09-14 | 2009-09-17 | 2010-07-01 | 2011-01-10 | 500455.83
7619 | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5299086 | Construction of approx. 2300 ln ft of asphalt and concrete paths including fencing, drainage culverts, signing, striping and retaining wall in Great Falls. | Transportation Enhancements | 2009-10-16 | 2009-10-16 | 2010-09-01 | 2010-03-30 | 340275.96
7620 | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5299087 | Construction of approx. 1800 ln ft of asphalt bicycle/pedestrian pathway along the Missouri River in Great Falls. | Transportation Enhancements | 2010-06-01 | 2010-06-02 | 2010-11-01 | 2010-12-15 | 659724.04
7621 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 5802012 | Widneing 1.09 mile segment of Custer Avenue in Helena | Pavement Improvement | 2009-07-06 | 2009-08-03 | 2009-12-20 | 2010-09-09 | 623101 | 1.090
7622 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 5805013 | 0.3 mile mill and fill on Benton Ave in Helena | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2009-12-20 | 2010-02-09 | 226091.31 | 0.300
7623 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 5822002 | 0.83 mile overlay on Hauser Blvd in Helena | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2009-12-20 | 2010-02-09 | 403276.24 | 0.830
7624 | Underway | C200 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE |  | 01 | 6905002 | Reconstruct the existing 8th Ave Roadway in Laurel | Pavement Improvement | 2009-11-16 | 2010-01-22 | 2011-12-20 |  | 2508204 | 0.640
7625 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | PARK |  | 01 | 7406007 | 0.7 mile mill and fill on Chinook and Gallatin Street in Livingston | Pavement Improvement | 2009-06-15 | 2009-06-18 | 2009-12-20 | 2009-11-23 | 214020.37 | 0.710
7626 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8105014 | 0.8 mile mill and fill on Russell Street in Missoula | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-12-20 | 2009-11-05 | 143343.5 | 0.800
7627 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8107019 | 0.17 mile mill and fill on Orange Street in Missoula | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-12-20 | 2009-11-05 | 78367.49 | 0.173
7628 | Completed | C200,C240 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8109002 | On the Scott Street overpass in Missoula, Bridge deck repair and replacing the surface with a high strength epoxy concrete. | Bridge Improvement | 2009-07-13 | 2009-07-22 | 2010-07-01 | 2010-06-07 | 1974836.74 | 0.000
7629 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8113006 | 0.3 mile mill and fill on Higgins Street in Missoula | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-12-20 | 2009-11-05 | 115275.18 | 0.340
7630 | Completed | C220,C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8117006 | Higgins/Hill/Beckwith Intersection & Signal Improvement in Missoula | Pavement Improvement | 2009-06-15 | 2009-06-17 | 2009-12-20 | 2009-12-18 | 693643.94 | 0.000
7631 | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8119001 | Design and construction of sidewalks, bike lanes, and period lighting. The proejct is in Missoula along both sides of Higgins Avenue between Broadway and Railroad Streets. | Transportation Enhancements | 2010-04-26 | 2010-04-26 | 2010-12-01 | 2010-10-15 | 1250000
7632 | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8120005 | 2 mile mill and fill on South Avenue in Missoula | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-12-20 | 2009-11-05 | 624945.36 | 2.000
7633 | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8123001 | Design and construct a bicycle and pedstrian path in the Missoula Urbanized Area along the south side of Mullan Road between Flyn Lane and Cote Lane. | Transportation Enhancements | 2010-04-12 | 2010-04-12 | 2010-10-01 | 2010-08-04 | 600000
7634 | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8199088 | Installation of accessible curb ramps on existing sidewalks at multiple locations within the City of Missoula. | Transportation Enhancements | 2010-06-14 | 2010-06-24 | 2010-10-01 | 2010-10-21 | 350000
7635 | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8199089 | Design and construct sidewalks and bike paths in Missoula - on both sides of Greenough Drvie between Madison St and Wateworks Hill Trailhead. | Transportation Enhancements | 2010-05-25 | 2010-06-15 | 2010-10-01 | 2010-08-06 | 189570
7636 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | BLAINE |  | 01 | 9003032 | Replacement of an off system bridge & approaches in Blaine County. | Bridge Replacement | 2009-06-22 | 2009-07-10 | 2010-12-20 | 2010-10-28 | 2402036
7637 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | BLAINE |  | 01 | 9003039 | Bridge Replacement 7 KM west of Harlem | Bridge Replacement | 2010-01-04 | 2010-02-04 | 2011-12-20 | 2010-11-18 | 2364675
7638 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | DEER LODGE |  | 01 | 9012131 | Replace existing structure over the Clark Fork, 2 KM East of Warm Springs | Bridge Replacement | 2009-11-02 | 2010-03-22 | 2010-12-20 | 2010-10-13 | 397816 | 0.000
7639 | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | FALLON |  | 01 | 9013015 | Off-system Bridge Replacement Project North West of Baker in Fallon County | Pavement Improvement | 2009-08-03 | 2009-09-15 | 2010-12-20 | 2011-12-29 | 684245 | 0.000
7640 | Underway | C490 | OJT/SS | MONTANA | LAKE |  | 01 | STWD016 | Purchase, transport and set up equipment and software that will be used to provide and support state of the art training. | Other | 2009-09-01 |  | 2010-09-01 |  | 707847
7641 | Completed | C490 | OJT/SS | MONTANA | ROOSEVELT |  | 01 | STWD017 | Provide on the job training in highway construction industry, equipment operating, and transportation to targeted groups in highway construction workforce. | Other | 2009-09-01 |  | 2010-09-01 | 2011-05-01 | 334320
7642 | Underway | C220 | Highway Infrastructure Investment Grant | NEBRASKA | BUFFALO |  | 03 | 0010060 | Restore a historic depot in the park in Pleasanton. Exterior work to include new foundation, windows, roof, gutters, and siding. Interior work to include new insulation, repair of floors, wall and tr | Transportation Enhancements | 2010-04-22 |  | 2010-12-11 |  | 312118
7643 | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | DAKOTA | SIOUX CITY (IA-SD) | 01 | 0022028 | This projects constructs an 8' concrete trail as a safe crossing from the Tri-State Trail under the Missouri River bridge on US-77 | Transportation Enhancements | 2010-04-28 | 2010-09-13 | 2010-08-07 | 2011-08-24 | 396223
7644 | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | DODGE |  | 01 | 0027052 | This project will replace existing street lights located on Main Street from 5th to 1st Streets with historic replica lighting in Fremont. | Transportation Enhancements | 2010-01-15 | 2011-01-17 | 2010-10-30 | 2011-05-23 | 132804
7645 | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 0028091 | This project restores the brick pavement and replaces granite curbs in the historic Old Market District of downtown Omaha, bringing back the original historical flavor of this popular shopping and ent | Transportation Enhancements | 2010-04-29 | 2010-09-22 | 2010-11-27 | 2011-05-11 | 829359
7646 | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | KEARNEY |  | 03 | 0050035 | This project will construct an 8-foot-wide pedestrian and bicycle trail connecting the Axtell City Park and Axtell School at the edge of downtown, with the Natures Mosaic Recreation Area 3,000 feet no | Transportation Enhancements | 2010-04-06 | 2010-10-05 | 2010-10-30 | 2011-04-14 | 208516
7647 | Underway | C220 | Highway Infrastructure Investment Grant | NEBRASKA | KNOX |  | 01 | 0054015 | Construct a 10' wide crushed concrete trail between Gavin's Point Dam and the community of Aten. | Transportation Enhancements | 2011-02-17 | 2011-11-15 | 2011-11-05 |  | 13670.61
7648 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 0064125 | 12.1 miles of asphalt resurfacing and bridge repair west of Hastings, including the spurs to Juniata and the Hastings Regional Center. | Pavement Improvement | 2009-05-07 | 2009-05-14 | 2009-11-28 | 2010-05-04 | 3665228 | 9.860
7649 | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | PLATTE |  | 03 | 0071030 | This project will construct a 10-foot-wide concrete pedestrian and bicycle trail approximately one mile in length, connecting the existing Wilderness Park Trail and the Robert Bob White Trail on the o | Transportation Enhancements | 2009-11-19 | 2010-09-27 | 2010-06-19 | 2011-04-01 | 366930
7650 | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | THURSTON |  | 01 | 0087010 | This project constructs a one mile long, 8' wide concrete trail connecting the Heritage Store and the Thunder Way subdivision in Winnebago, providing a safe and efficient route for pedestrians and bic | Transportation Enhancements | 2010-12-29 | 2011-03-28 | 2011-07-11 | 2011-11-14 | 559438
7651 | Underway | C220 | Highway Infrastructure Investment Grant | NEBRASKA | WASHINGTON |  | 02 | 0089024 | Construct 10' wide concrete trail from the Blair Deerfield Lions Trail to the Dana College recreation fields, a distance of 0.9 mile | Transportation Enhancements | 2010-03-04 | 2010-08-23 | 2010-10-30 |  | 435371
7652 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | BUFFALO |  | 03 | 0102115 | This resurfacing project will bring this roadway to a state of good repair. It will address pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-09-22 | 2010-06-21 | 2010-10-30 | 2010-11-02 | 1282168.59 | 10.000
7653 | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | HALL |  | 03 | 0112116 | This project provides for installation of landscaping along Highway N-11 along the Loup River Scenic Byway. It includes landscape areas in the downtown corridor (2.5 blocks); and a 20-foot wide lands | Transportation Enhancements | 2010-01-27 | 2010-04-01 | 2010-05-29 | 2011-05-10 | 149078 | 0.000
7654 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | JEFFERSON |  | 03 | 0151113 | Replacement of 2 deficient bridges south of Fairbury on N-15. The structure at reference post 3.07 is over a stream. The second structure at R.P 4.53 is over Rose Creek. | Bridge Replacement | 2009-05-04 | 2009-05-18 | 2011-04-30 | 2010-06-14 | 2966171 | 0.000
7655 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | HOLT |  | 03 | 0204117 | The project consists of resurfacing the existing 24 foot roadway and 8 foot surfaced shoulders on US-20 just southeast of the city of O'Neill and continuing southeast 5.14 miles. The project will mill | Pavement Improvement | 2009-11-25 | 2010-07-22 | 2010-10-30 | 2010-09-10 | 1347689 | 5.020
7656 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | ANTELOPE |  | 03 | 0205111 | The project consists of resurfacing the existing 24 foot roadway and 8 foot surfaced shoulders of US-20 from Royal to Plainview and for a short length on S-2B. The project along US-20 will mill off f | Pavement Improvement | 2009-12-11 | 2010-07-06 | 2010-10-30 | 2010-10-20 | 5274390 | 14.150
7657 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | PHELPS |  | 03 | 0233105 | Asphalt resurfacing of the 6.96 miles of N-23 between Loomis and Holdrege. The existing 4' shoulders will be widened to 6' with 2' being surfaced. | Pavement Improvement | 2009-07-17 | 2009-09-14 | 2010-07-31 | 2010-05-26 | 2594512 | 6.960
7658 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEBRASKA | BUFFALO |  | 03 | 0304148 | This project is on US-30 from Avenue B to Avenue E and from Avenue I to Avenue L in the city of Kearney. The existing narrorw raised median will be widened to 15 feet to accommodate turn lanes. To acc | Pavement Improvement | 2009-06-08 | 2009-07-13 | 2010-07-24 | 2010-07-27 | 2294674.97 | 0.220
7659 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | WASHINGTON |  | 02 | 0307116 | This project consists of concrete repair and diamond grinding on US-30 from US-75 in Blair east 1.8 miles to the Missouri River Bridge | Pavement Improvement | 2010-04-16 | 2010-07-06 | 2010-10-02 | 2010-11-30 | 460750
7660 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | MADISON |  | 01 | 0325106 | "Improvements of this project east of Madison will include the vertical realignment of N-32 at the bridge over Union Creek at R.P. 36.73, which will be replaced along with raising the highway grade 9 | Bridge Replacement | 2009-09-23 | 2010-03-01 | 2010-11-13 | 2010-12-03 | 3643201 | 0.740
7661 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEBRASKA | HALL |  | 03 | 0344131 | "This project is located on US-34 and US-281 just south of and in the city of Grand Island. It extends from just north of the I-80 interchange to just south of Capital Avenue for a total lenth of 8.33 | Pavement Improvement | 2009-06-03 | 2009-07-13 | 2010-07-31 | 2011-05-24 | 6504399 | 5.060
7662 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 0346139 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement, bridge and guardrail deficiencies with an asphalt overlay, bridge repair and new guardrail. | Pavement Improvement | 2009-07-13 | 2009-07-27 | 2010-06-19 | 2010-07-07 | 2049649 | 2.490
7663 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 0346140 | Urban asphalt resurfacing on ""O"" Street from 15th St. to 25th St.; from 29th St. to 44th St. and from Wedgewood Dr. to 84th St. in Lincoln" | Pavement Improvement | 2010-03-18 | 2010-05-03 | 2011-05-13 | 2011-10-11 | 1711546
7664 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DAKOTA |  | 01 | 0354118 | This bridge replacement project will bring this roadway to a state of good repair. It will replace two deficient bridges and rehabilitate another bridge. | Bridge Replacement | 2009-06-03 | 2009-06-22 | 2010-10-30 | 2010-12-03 | 1944384 | 0.000
7665 | Underway | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 0387106 | This project reconstructs the busy West Center Road between 156th St. and 148th St. in Omaha to a 4-lane divided roadway in Omaha, providing a safer and more efficient segment. | Pavement Widening | 2010-04-26 | 2010-05-10 | 2011-10-31 |  | 7470191
7666 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | OTOE |  | 01 | 0502128 | This resurfacing and bridge project will bring this roadway to a state of good repair. It will improve safety by eliminating surface and bridge deficiencies through an asphalt overlay and bridge reha | Pavement Improvement | 2009-03-25 | 2009-03-31 | 2010-07-31 | 2010-09-28 | 4907360 | 9.460
7667 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | VALLEY |  | 03 | 0704107 | This project is located on N-70 near Arcadia. The existing 275' bridge with a 28' roadway will be widened and rehabilitated with a new south span and new superstructure. The rehabilitated bridge will | Bridge Improvement | 2009-05-11 | 2009-05-18 | 2010-08-21 | 2010-11-19 | 1717017 | 0.000
7668 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | KIMBALL |  | 03 | 0712109 | This resurfacing project will bring this roadway to a state of good repair by providing a new, wider driving surface. | Pavement Improvement | 2009-06-03 | 2009-06-29 | 2009-11-21 | 2010-02-02 | 4357760.11 | 14.860
7669 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | WASHINGTON |  | 01 | 0753115 | This urban project in Blair adds a 2' curb and gutter section with storm sewer and inlets. This will allow for the future construction of a 10' sidewalk / bike trail on the south side of US-75 from De | Pavement Improvement | 2010-04-07 | 2010-06-28 | 2010-09-10 | 2010-10-01 | 458420 | 0.250
7670 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | THURSTON |  | 01 | 0754108 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. It also includes new lighting to improve safety at the Macy | Bridge Replacement | 2010-03-02 | 2010-03-15 | 2011-09-17 | 2011-10-19 | 1995848 | 0.910
7671 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DEUEL |  | 03 | 0802090 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies through an asphalt overlay. | Pavement Improvement | 2009-05-04 | 2009-06-15 | 2010-07-24 | 2010-06-01 | 6317477.58 | 9.820
7672 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | CHEYENNE |  | 03 | 0802093 | This rehabilitation and restoration project will bring this roadway to a state of good repair. It will extend the life and improve the surface condition of the existing pavement. | Pavement Improvement | 2009-05-11 | 2009-06-15 | 2009-10-03 | 2009-09-21 | 1296575.95 | 24.850
7673 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DEUEL |  | 03 | 0803119 | The improvements on this project will consist of concrete pavement repairs to the existing dual 24' roadway, plus the 3' inside and 10' outside shoulders. The existing inside shoulders and roadway wil | Pavement Improvement | 2009-12-02 | 2010-05-03 | 2010-10-30 | 2011-05-15 | 4074809 | 4.220
7674 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | KEITH |  | 03 | 0803135 | This project rehabilitates Interstate 80 between the Brule and Ogallala interchanges by milling the surface and placing new asphaltic concrete. | Pavement Improvement | 2009-12-17 | 2010-04-26 | 2010-10-09 | 2010-11-01 | 3894955.12 | 10.810
7675 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | KEITH |  | 03 | 0803139 | This project rehabilitates Interstate 80 between the Ogallala and Roscoe interchanges by milling the surface and placing new asphaltic concrete. | Pavement Improvement | 2010-01-20 | 2010-03-11 | 2010-08-28 | 2010-10-21 | 3200876.7 | 6.680
7676 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | LINCOLN |  | 03 | 0804104 | This rehabilitation project will bring this roadway to a state of good repair, by preserving the structure (the interchange over I-80) and providing an improved driving surface. | Bridge Improvement | 2009-03-23 | 2009-05-18 | 2009-10-03 | 2009-12-02 | 1315548 | 0.000
7677 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DAWSON |  | 03 | 0804129 | This rehabilitation project will bring this roadway to a state of good repair, by preserving the structure (the interchange over I-80) and providing an improved driving surface. | Bridge Improvement | 2009-04-28 | 2009-06-08 | 2009-10-03 | 2010-04-14 | 1050940 | 0.000
7678 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | LINCOLN |  | 03 | 0804133 | This restoration and rehabilitation project will bring this roadway to a state of good repair. It will extend the life and improve the surface condition of the existing pavement. | Pavement Improvement | 2009-07-23 | 2009-09-08 | 2010-08-07 | 2010-06-22 | 1743620.93 | 5.870
7679 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DAWSON |  | 03 | 0805069 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-03-25 | 2009-06-15 | 2009-09-05 | 2010-05-04 | 6137997.94 | 10.490
7680 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | HALL |  | 03 | 0806097 | This project will resurface 11.61 miles of I-80 between the Wood River and West Grand Island Interchanges. Improvements consist of joint repair, pavement repair, milling and resurfacing with asphalt a | Pavement Improvement | 2009-06-08 | 2009-07-06 | 2010-06-26 | 2010-08-16 | 5255421 | 11.630
7681 | Underway | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 0809889 | This reconstruction project will bring this roadway to a state of good repair and will improve the level of service (traffic flow). This expansion of I-80 on the Nebraska side is occurring in conjunct | Pavement Widening | 2009-07-09 | 2009-08-10 | 2012-06-02 |  | 16486652 | 2.230
7682 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | YORK |  | 03 | 0812142 | The project begins 0.6 miles north of US-34 north of York and continues 7.2 miles north, including 0.6 miles at the S-93 junction. It consists of asphaltic concrete resurfacing of the roadway and shou | Pavement Improvement | 2010-01-06 | 2010-04-05 | 2010-10-30 | 2010-10-19 | 2712263
7683 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | THOMAS |  | 03 | 0833106 | This bridge project will bring this roadway to a state of good repair and will improve mobility and safety, by eliminating existing at-grade rail and highway crossings (over the BNSF RR) in close prox | Bridge Replacement | 2009-04-01 | 2009-05-04 | 2010-07-17 | 2011-05-23 | 6943648 | 1.660
7684 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | CHERRY |  | 03 | 0834113 | The scope of this project consists of resurfacing US Highway 83 (US-83) for approximately 10 miles. The project will be milled and constructed using 4 inches of High RAP Base which contains a high Rec | Pavement Improvement | 2009-11-25 | 2010-07-12 | 2010-10-02 | 2010-11-18 | 3442996 | 10.050
7685 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | LOUP |  | 03 | 0913107 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-06-08 | 2009-08-24 | 2009-10-31 | 2009-11-05 | 1980080.52 | 8.470
7686 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | PLATTE |  | 03 | 0915121 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-05-14 | 2009-06-01 | 2009-09-05 | 2009-09-01 | 3436352.76 | 11.950
7687 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | COLFAX |  | 01 | 0916111 | This resurfacing project brought this roadway to a state of good repair. It addressed pavement deficiencies with an asphalt overlay, including milling off 2" of old asphalt surfacing and replacing wi | Pavement Improvement | 2009-05-14 | 2009-06-22 | 2009-10-31 | 2009-08-21 | 2395805.74 | 16.710
7688 | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | BANNER |  | 03 | 1035006 | This project is on a county road 5.55 miles north and 10.5 miles west of Harrisburg, continuing north 4.0 miles to the county line. It consists of an asphalt resurfacing of the 22' roadway and rehabil | Pavement Improvement | 2010-03-25 | 2010-08-23 | 2010-10-16 | 2010-10-09 | 1170489
7689 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DIXON |  | 01 | 1164102 | This bridge replacement project will bring this roadway to a state of good repair. It is replacing a 52-year old structure. | Bridge Replacement | 2009-05-04 | 2009-05-18 | 2009-10-31 | 2009-12-04 | 328419.66 | 0.000
7690 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | THAYER |  | 03 | 1365111 | Milling and asphalt resurfacing of 4.2 miles of US-136 from 1.7 miles west of Gilead to the Thayer/Jefferson county line. | Pavement Improvement | 2009-03-25 | 2009-06-03 | 2009-10-31 | 2009-09-30 | 1444929.28 | 5.020
7691 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | GAGE |  | 01 | 1366116 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-04-29 | 2009-06-25 | 2009-10-31 | 2010-05-08 | 3059751.25 | 9.410
7692 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | JEFFERSON |  | 01 | 1366118 | This project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-03-25 | 2009-06-19 | 2009-10-31 | 2009-10-21 | 2762944.64 | 8.100
7693 | Underway | C240 | Highway Infrastructure Investment Grant | NEBRASKA | NEMAHA |  | 01 | 1367122 | This bridge rehabilitation project will bring this roadway to a state of good repair. It will extend the life and improve the safety of the existing bridge by repairing and rehabilitating the structu | Bridge Improvement | 2009-10-05 | 2009-08-31 | 2011-12-01 |  | 3245529 | 0.000
7694 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | FRONTIER |  | 03 | 1575003 | This project is on a county road 9.5 miles south and 9.0 miles east of Stockville, continuing north 3.1 miles. It consists of an asphalt resurfacing of the 22' roadway and rehabilitation of the 4' ear | Pavement Improvement | 2010-01-25 | 2011-06-21 | 2010-10-30 | 2011-08-24 | 906458
7695 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | KEYA PAHA |  | 03 | 1710004 | This project is on a county road 4.7 miles north and 2.8 miles west of Springview, extending 3.0 miles east. It consists of an asphalt resurfacing of the 22.5' roadway and rehabilitation of the 4' ear | Pavement Improvement | 2010-03-09 | 2010-08-12 | 2010-10-02 | 2010-10-13 | 939271
7696 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | THOMAS |  | 03 | 1755013 | This project is on a county road 3.5 miles north of Halsey, extending 4.2 miles north. It consists of an asphalt resurfacing of the 20' roadway and rehabilitation of the 4' earth shoulders. | Pavement Improvement | 2010-05-04 | 2011-05-09 | 2010-10-30 | 2011-07-25 | 1067830
7697 | Underway | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ROCK |  | 03 | 1810005 | Asphalt resurfacing of a county road 8.4 miles south and 4.9 miles east of Bassett, continuing 4.7 miles southeasterly. | Pavement Improvement | 2011-01-18 | 2011-08-10 | 2011-10-29 |  | 893517
7698 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | HALL |  | 03 | 2235005 | This project consists of the paving of the northbound lanes of Locust Street from I-80 north 2.9 miles to Grand Island. | Pavement Improvement | 2010-04-22 | 2010-05-13 | 2010-08-21 | 2010-10-28 | 3355633
7699 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | HOLT |  | 03 | 2280005 | Replace a deficient bridge on a county road 14.2 miles east of O'Neill, crossing the middle branch of Verdigris Creek with a twin 9' x 8' x 88' concrete box culvert. | Pavement Improvement | 2010-01-25 | 2010-03-29 | 2010-06-19 | 2010-07-09 | 252522
7700 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | HOLT |  | 03 | 2814118 | The scope of this project consists of resurfacing the existing 24' asphalt roadway and 8' surfaced shoulders of US-281 near the city of O'Neill (approximately 7.5 miles in length). The project will m | Pavement Improvement | 2009-11-25 | 2010-07-12 | 2010-10-09 | 2010-09-03 | 2065563.47 | 7.410
7701 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | JEFFERSON |  | 01 | 3005008 | This project consists of a 3 inch asphaltic concrete overlay of an existing bituminous road. The project includes earth shoulder construction to match the pavement rise along both sides of the road. T | Pavement Improvement | 2010-01-07 | 2011-03-31 | 2010-10-30 | 2011-05-05 | 756007
7702 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | GAGE |  | 01 | 3265004 | New 30' x 28' concrete slab bridge over Plum Creek 0.7 miles south of Barneston. | Bridge Replacement | 2010-01-26 | 2010-03-22 | 2010-11-27 | 2011-06-06 | 837486
7703 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 3340007 | This project consists of replacing a deficient bridge box culvert. This bridge is a 4-barrel 10 foot by 26 foot concrete box culvert. It will be replaced with a 4-barrel 14 foot by 61 foot concrete | Bridge Replacement | 2010-04-20 | 2010-06-21 | 2010-10-02 | 2010-10-28 | 310884
7704 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | SAUNDERS |  | 01 | 3430006 | The project is the replacement of a deficient bridge with a triple 16' x 16' x 18' concrete box culvert. It is located on a county road (Highway Avenue) on the southern edge of Prague, crossing Cotton | Bridge Replacement | 2010-02-03 | 2010-03-29 | 2010-11-27 | 2011-08-05 | 567100
7705 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 3770003 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2010-03-09 | 2010-09-20 | 2010-10-30 | 2010-10-21 | 560000
7706 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | Multiple | 3772001 | This project improves safety and mobility by reconfiguring the intersection and installing traffic signals. | Safety/Traffic Management | 2010-07-27 | 2010-10-04 | 2010-10-30 | 2010-11-08 | 242268
7707 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 01 | 3787003 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with joint repair and an asphalt overlay. | Pavement Improvement | 2010-03-09 | 2010-08-30 | 2010-10-30 | 2010-10-20 | 610700
7708 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | BOX BUTTE |  | 03 | 3854129 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-04-29 | 2009-08-10 | 2009-10-31 | 2009-11-23 | 3022607.93 | 7.910
7709 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 4809776 | This is a new 311' x 58' bridge on US-75 southbound over 30th St. and the exit ramps in Omaha. | Bridge Replacement | 2009-08-19 | 2009-08-31 | 2011-06-11 | 2011-06-11 | 1680143 | 0.000
7710 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 4809777 | Rehabilitation of the I-480 183' x 72' steel girder bridge over 24th St. in Omaha | Bridge Improvement | 2009-08-19 | 2009-08-31 | 2011-06-11 | 2011-06-11 | 1600854 | 0.000
7711 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 4809778 | This project is the reconstruction of the I-480 / US-75 southbound interchange in Omaha. Work consists of grading, mechanically stabilized earth walls, culverts, three bridge removals, guardrail, fenc | Pavement Improvement | 2009-08-19 | 2009-08-31 | 2011-06-11 | 2011-06-11 | 13146340 | 0.880
7712 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 4809787 | This project is the widening and rehabilitiation of the southbound US-75 bridge over Burt St. and Cuming St. in Omaha. The new structure will be 532' long and 58' wide. | Bridge Improvement | 2009-08-19 | 2009-08-31 | 2011-06-11 | 2011-06-11 | 3262610 | 0.000
7713 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5003008 | This project improves safety and mobility by constructing a 4-lane divided roadway. | Pavement Widening | 2010-03-16 | 2010-03-22 | 2010-10-08 | 2010-10-29 | 2592465
7714 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5006005 | This project is to replace the 50+ year old traffic signals, poles and mast arms at the intersection of Harvell Drive and Fort Crook Road in the City of Bellevue. The work included is to install new s | New Construction | 2010-02-18 | 2010-09-27 | 2010-10-30 | 2010-11-01 | 135800
7715 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5011013 | This project is to install traffic warning signals for the intersection of 108th Street and Chandler Road in La Vista. | New Construction | 2010-02-25 | 2010-10-04 | 2010-10-30 | 2011-02-14 | 30000
7716 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5012009 | The scope of the project consists of dowel bar retrofitting, diamond grinding, and texturing on Giles Road, beginning at 108th St and ending approximately 200 feet southeast of Southport Parkway in th | Pavement Improvement | 2010-02-25 | 2010-08-09 | 2010-10-30 | 2011-04-07 | 970700
7717 | Underway | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5027001 | This reconstruction project will bring this urban street to a state of good repair. | Pavement Improvement | 2010-12-16 | 2011-03-21 | 2011-06-25 |  | 765864
7718 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5049004 | Resurfacing urban streets at city-wide locations in Omaha | Pavement Improvement | 2010-12-09 | 2011-05-09 | 2011-09-10 | 2011-11-17 | 354725
7719 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5052003 | This project improves safety and mobility by installing traffic signals. | Safety/Traffic Management | 2010-03-25 | 2010-08-10 | 2010-10-08 | 2010-09-30 | 252654
7720 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5093001 | This project improves safety and mobility by installing traffic signals. | Safety/Traffic Management | 2010-03-25 | 2011-04-04 | 2010-11-19 | 2011-06-16 | 332605
7721 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5095003 | This asphalt resurfacing project will bring urban streets at city-wide locations to a state of good repair. | Pavement Improvement | 2010-03-01 | 2010-05-17 | 2010-10-29 | 2010-09-07 | 3000000
7722 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5097002 | This project improves safety and mobility by installing traffic signals. | Safety/Traffic Management | 2010-03-25 | 2010-06-14 | 2010-09-01 | 2010-08-06 | 276944
7723 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5106001 | This project improves safety and mobility for pedestrians by replacing sidewalks and adding ADA-approved ramps. | Pavement Improvement | 2010-04-28 | 2010-06-01 | 2010-10-02 | 2010-11-24 | 837240
7724 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5106002 | This asphalt resurfacing project will bring this urban street to a state of good repair. | Pavement Improvement | 2010-03-22 | 2010-09-20 | 2010-10-30 | 2011-06-24 | 309154
7725 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5109007 | This project is to replace the 50+ year old traffic signals, poles and mast arms at the intersection of Harvell Drive and Galvin Road in the City of Bellevue. The work included is to install new signa | New Construction | 2010-02-16 | 2010-09-07 | 2010-10-30 | 2010-10-07 | 136531
7726 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5145001 | This asphalt resurfacing project will bring these urban roadways into a good state of repair. | Pavement Improvement | 2010-03-24 | 2010-08-02 | 2010-09-18 | 2011-07-07 | 1190700
7727 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5220003 | Asphalt resurfacing on A Street between 63rd St. and Imperial Drive and on Van Dorn St. from Normal Blvd. to 70th St. in Lincoln. | Pavement Improvement | 2010-01-26 | 2010-04-12 | 2010-09-30 | 2011-10-11 | 662985
7728 | Underway | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5236002 | Asphalt resurfacing on P St. between 18th St. and 27th St., P St. between 17th St. and 27th St. and on Northwest 1st St. between Highland Blvd. and West Fletcher Ave. in Lincoln." | Pavement Improvement | 2010-02-28 | 2010-04-27 | 2011-09-30 |  | 926670
7729 | Underway | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5239008 | Pavement markings at various locations city-wide in Lincoln | Safety/Traffic Management | 2010-12-01 | 2011-06-20 | 2011-09-30 |  | 754507
7730 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5244007 | Asphalt resurfacing and ADA approved curb ramps on Holdrege Street from 33rd St. to 47th St. in Lincoln | Pavement Improvement | 2010-02-28 | 2011-05-31 | 2011-08-12 | 2011-09-29 | 916546
7731 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5244008 | Asphalt resurfacing and ADA approved curb ramps on Holdrege Street from 70th St. to 79th St. in Lincoln | Pavement Improvement | 2010-02-28 | 2011-04-11 | 2011-08-12 | 2011-10-31 | 809396
7732 | Underway | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5247011 | Asphalt resurfacing on Holdrege St. from 19th St to 25th St; on Cornhusker Hwy from Russell Dr. to 70th St.; on 70th St. from Adams St. to Aylesworth St.; on Vine St. from 70th St. to Sierra Dr. and o | Pavement Improvement | 2010-02-28 | 2010-05-17 | 2011-09-30 |  | 1129378
7733 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5247012 | 0.64 mile of asphalt resurfacing and curb ramp replacement on 70th St. from Aylesworth St. south to Vine St. in Lincoln | Pavement Improvement | 2010-02-28 | 2011-05-23 | 2011-08-12 | 2011-10-31 | 740069
7734 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5250003 | Asphalt resurfacing on Adams St. from 57th St. to 62nd St. in Lincoln | Pavement Improvement | 2010-02-02 | 2010-06-07 | 2010-07-23 | 2011-11-14 | 463377
7735 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5254009 | This project consists of bridge rehabilitation for the Superior Street Bridge over Salt Creek just west of 40th Street in Lincoln. The existing steel girder structure is 293 feet long and 50 feet wid | Bridge Improvement | 2010-01-27 | 2010-03-22 | 2010-08-15 | 2011-06-20 | 271922
7736 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5280001 | This asphalt resurfacing project will bring the roadway into a good state of repair. It is located on Saltillo Rd., from Highway US-77 to South 70th St. in Lincoln, Nebraska. | Pavement Improvement | 2010-06-15 | 2010-08-02 | 2010-10-30 | 2010-10-05 | 884155
7737 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | DAKOTA | SIOUX CITY (IA-SD) | 01 | 5305008 | This project improves safety by providing new intersection lighting. | New Construction | 2010-04-06 | 2010-09-13 | 2010-11-27 | 2011-04-21 | 950657
7738 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | DAKOTA | SIOUX CITY (IA-SD) | 01 | 5305009 | This project improves safety and mobility by installing traffic signals at urban intersections. | Safety/Traffic Management | 2010-03-04 | 2010-10-19 | 2010-11-27 | 2011-04-22 | 177781
7739 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 5505003 | 0.81 mile of asphalt resurfacing, four intersections and curb ramps on Baltimore Avenue from 2nd St. to 12th st. in Hastings | Pavement Improvement | 2010-02-28 | 2010-06-07 | 2010-08-28 | 2010-10-01 | 651357
7740 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 5512008 | 0.24 mile of asphalt resurfacing and curb ramp replacements on 7th Street, from Baltimore Ave. to Oswego Ave. in Hastings | Pavement Improvement | 2010-02-18 | 2010-05-17 | 2010-10-30 | 2010-06-15 | 137328.84
7741 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 5514003 | 0.49 mile of asphalt resurfacing, three intersections and curb ramps on 9th Street from Burlington Ave. to Baltimore Ave. in Hastings. | Pavement Improvement | 2010-02-18 | 2010-05-20 | 2010-10-30 | 2010-06-26 | 347025.15
7742 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 5527001 | 0.56 mile of asphalt resurfacing on Showboat Blvd. between 7th and 12th Streets in Hastings. | Pavement Improvement | 2010-01-29 | 2010-04-12 | 2010-10-30 | 2010-05-25 | 265260
7743 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | SCOTTS BLUFF |  | 03 | 5709003 | Urban reconstruction of 0.43 mile of Avenue B from South Beltline Highway to Overland Drive in Scottsbluff | Pavement Improvement | 2010-04-27 | 2010-07-26 | 2010-11-27 | 2010-11-22 | 950808
7744 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | SCOTTS BLUFF |  | 03 | 5724002 | Concrete reconstruction of 0.34 mile of D Street between Rundell Rd. and Lockwood Rd. in Gering | Pavement Improvement | 2010-04-19 | 2010-08-23 | 2010-10-30 | 2010-11-22 | 432976
7745 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | BUFFALO |  | 03 | 5922003 | Urban reconstruction of 39th St. between Pony Express and Avenue M in Kearney | Pavement Improvement | 2010-04-15 | 2010-06-01 | 2010-11-27 | 2011-05-03 | 2418216
7746 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | PLATTE |  | 03 | 6074005 | Construct 2 lanes of concrete pavement for 1.6 miles on Lost Creek Parkway between US-81 and 48th Ave. in Columbus | New Construction | 2010-04-26 | 2010-08-23 | 2011-07-01 | 2011-08-23 | 2398778
7747 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | REDWILLOW |  | 03 | 6156002 | Reconstruction of 0.72 mile of West J Street from West 10th St. to Norris Ave. in McCook. Project inlcudes storm sewers, sidewalks, ADA ramps and traffic signals. | Pavement Improvement | 2009-07-22 | 2009-07-27 | 2009-12-05 | 2009-11-13 | 1071992
7748 | Underway | C200 | Highway Infrastructure Investment Grant | NEBRASKA | OTOE |  | 01 | 6204004 | Reconstruction of 0.24 mile of 11th Corso between 10th and 11th Streets in Nebraska City. | Pavement Improvement | 2010-04-19 | 2010-05-03 | 2010-07-17 |  | 575330
7749 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | OTOE |  | 01 | 6210003 | Asphalt resurfacing and installation of decorative crosswalks for 0.49 mile of Central Ave. between 11th and 6th Streets in Nebraska City. | Pavement Improvement | 2010-02-16 | 2010-07-14 | 2010-10-30 | 2011-08-02 | 603601
7750 | Underway | C200 | Highway Infrastructure Investment Grant | NEBRASKA | OTOE |  | 01 | 6218001 | Urban widening and reconstruction of 11th Street between 10th and 14th Corsos in Nebraska City | Pavement Improvement | 2010-04-19 | 2010-05-03 | 2010-09-11 |  | 1249502
7751 | Underway | C200 | Highway Infrastructure Investment Grant | NEBRASKA | YORK |  | 01 | 6305001 | 0.5 mile of urban reconstruction on Nebraska Ave. between 4th and 14th Streets in York. | Pavement Improvement | 2010-04-22 | 2010-04-28 | 2011-12-03 |  | 2198101
7752 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | CASS |  | 01 | 6403002 | 0.16 mile of asphalt resurfacing on 15th St. between Ave. A and Ave. C in Plattsmouth. | Pavement Improvement | 2010-03-18 | 2010-10-18 | 2010-10-30 | 2010-11-04 | 131467
7753 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | CASS |  | 01 | 6403003 | Urban reconstruction on 15th St. between 1st Ave. and Main St. in Plattsmouth | Pavement Improvement | 2010-03-18 | 2010-10-25 | 2010-11-20 | 2010-11-12 | 76963
7754 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | DAWSON |  | 03 | 6556004 | 0.7 mi of urban reconstruction on 13th St., from Hampton St. to Airport Rd. in Lexington | Pavement Improvement | 2010-11-22 | 2011-06-06 | 2011-11-19 | 2011-11-07 | 1292608
7755 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | PHELPS |  | 03 | 6602001 | Urban reconstruciton of 0.52 mile of 11th ave. between Sherman St. and Lincoln St. in Holdrege. | Pavement Improvement | 2010-04-19 | 2010-07-12 | 2010-11-27 | 2011-08-19 | 1623819
7756 | Underway | C200 | Highway Infrastructure Investment Grant | NEBRASKA | SALINE |  | 01 | 6904001 | Urban reconstruction of 0.95 mile of East 13th St. between Hawthorn St. and the east city limits of Crete. | Pavement Improvement | 2010-04-19 | 2010-10-25 | 2010-11-27 |  | 2213114
7757 | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | COLFAX |  | 01 | 6954001 | Asphalt resurfacing of 0.44 mile of 9th St. between B St. and G St. in Schuyler | Pavement Improvement | 2010-02-25 | 2010-11-08 | 2010-11-27 | 2011-07-29 | 432349
7758 | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 7001014 | Replacement of a deficient bridge with a new 83' x 28' steel girder structure. The project is located 4 miles south and 0.8 mile west of Juniata, crossing the west branch of 32 mile Creek | Bridge Replacement | 2010-01-27 | 2010-09-07 | 2010-11-27 | 2011-05-03 | 481073
7759 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | DODGE |  | 01 | 7027008 | The project entails a new 140' x 28' concrete slab bridge over Cuming Creek, 2.5 miles north and 0.8 mile east of Scribner. | Bridge Replacement | 2010-02-17 | 2010-09-09 | 2010-11-27 | 2011-08-01 | 673908
7760 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 7028044 | New bridge over Thomas Creek on a county road 2.1 miles east and 0.5 mile north of Bennington. | Bridge Replacement | 2010-03-18 | 2010-09-07 | 2010-11-27 | 2011-03-22 | 534791
7761 | Completed | C250,C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 7028045 | New bridge over a stream on a county road 2.0 miles north and 0.1 mile east of Valley. | Bridge Replacement | 2010-03-18 | 2010-12-13 | 2010-11-27 | 2011-10-10 | 469421
7762 | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | FILLMORE |  | 01 | 7030033 | New bridge over a tributary of Turkey Creek on a county road 2.6 miles east of Geneva. | Bridge Replacement | 2010-04-13 | 2010-05-17 | 2010-11-27 | 2011-07-28 | 442906
7763 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | FRANKLIN |  | 03 | 7031012 | New twin 9' x 9' x 52' concrete box culvert on the Bostwick irrigation canal 1.5 miles east of Naponee | Bridge Replacement | 2010-01-26 | 2010-12-05 | 2010-11-20 | 2011-04-04 | 100216
7764 | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | JOHNSON |  | 01 | 7049021 | New 232' x 28' pre-stressed concrete girder bridge over the middle branch of the Big Nemaha River on a county road 2.0 miles west of Sterling. | Bridge Replacement | 2010-01-21 | 2010-03-22 | 2010-11-27 | 2011-04-13 | 904229
7765 | Underway | C200 | Highway Infrastructure Investment Grant | NEBRASKA | NANCE |  | 03 | 7063006 | New bridge over Horse Creek 1.8 miles south and 8.6 miles west of Fullerton | Bridge Replacement | 2010-11-23 | 2011-08-15 | 2011-11-26 |  | 531944
7766 | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | NUCKOLLS |  | 03 | 7065021 | Triple 3.66m x 18.5m concrete box culvert on Oak Creek 1.0 mile south of Oak on a county road. | Bridge Replacement | 2010-02-02 | 2010-08-30 | 2010-11-27 | 2010-12-15 | 302190
7767 | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | PHELPS |  | 03 | 7069015 | Triple 10' x 8' concrete box culvert on the Central Nebraska Public Power Irrigation District canal on a county road 1 miles west of Funk | Bridge Replacement | 2010-01-25 | 2010-10-18 | 2010-11-27 | 2011-04-13 | 151854
7768 | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 7941001 | The project consists of the removal of the upper 2 inches of the existing asphaltic concrete (asphalt) pavement to remove rutting on seven segments of 2 and 3-lane rural roadways, including turn lanes | Pavement Improvement | 2010-02-12 | 2010-10-06 | 2010-10-30 | 2010-11-16 | 1860020
7769 | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | CLAY |  | 03 | S18B104 | This project is on the Edgar Spur from N-14 to the city of Edgar, a length of 4.0 miles. The scope consists of resurfacing and widening the existing roadway to provide a 24' roadway with 1' surfaced s | Pavement Improvement | 2009-04-07 | 2009-05-11 | 2009-10-31 | 2010-08-21 | 1947585 | 3.990
7770 | Completed | C250,C220,C200,C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS, LANCASTER, STATEWIDE | STATEWIDE | Multiple | STWD093 | This project assists counties, municipalilties and metropolitan planning organizations in completing requirements for environmental documentation on ARRA projects. Six consulting engineering firms ar | Other | 2009-07-09 | 2009-07-09 | 2013-07-30 | 2010-03-01 | 997500 | 0.000
7771 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CHURCHILL |  | 02 | 0001097 | The Nevada Department of Transportation in coordination with Churchill County will resurface the existing asphalt with three inches of new asphalt and fog seal. This will improve driving quality by re | Pavement Improvement | 2010-08-23 | 2010-08-23 | 2010-09-13 | 2010-09-08 | 316096
7772 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CHURCHILL |  | 02 | 0001098 | The Nevada Department of Transportation in coordination with the City of Fallon will microsurface Baily Street, Whitaker Street, West Fifth Street East Street, Stillwater Avenue and Center Street. Thi | Pavement Improvement | 2010-08-23 | 2010-08-23 | 2010-09-13 | 2010-09-08 | 153055
7773 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003115 | The City of Boulder City will resurface approximately 1.3 miles of the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-06-20 | 2010-06-20 | 1000000
7774 | Underway | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003116 | The City of Las Vegas will construct intersection improvements including traffic signals, lighting, median islands and sidewalk improvements at various intersections within the city to provide safer a | Safety/Traffic Management | 2010-08-09 | 2010-09-20 | 2011-07-18 |  | 1314752
7775 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003117 | The City of North Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-06-29 | 2010-10-08 | 2752865
7776 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003118 | The City of Henderson will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-03-29 | 2010-03-30 | 2010-08-01 | 2010-07-13 | 840814
7777 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | Multiple | 0003119 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-01-19 | 2010-01-25 | 2010-09-17 | 2010-09-08 | 1209550
7778 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | Multiple | 0003120 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-01-19 | 2010-01-25 | 2010-09-17 | 2010-09-08 | 942171
7779 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003121 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-01-19 | 2010-01-25 | 2010-09-17 | 2010-09-08 | 647543
7780 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003122 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-01-19 | 2010-01-25 | 2010-09-17 | 2010-09-08 | 1150411
7781 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003123 | The City of Henderson will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-12-13 | 2010-09-16 | 2582000
7782 | Completed | C200 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003124 | The City of Henderson will reconstruct approximately 1.7 miles of the existing roadway. This will improve driving quality by widening the road, which will make the road safer and extend Volunteer Blvd | Pavement Improvement | 2010-04-14 | 2010-05-03 | 2010-10-14 | 2010-11-18 | 1084976
7783 | Underway | C200 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003125 | Clark County will resurface the top four inches of approximately 3.5 miles of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smo | Pavement Improvement | 2010-09-20 | 2010-09-27 | 2011-01-18 |  | 2893198
7784 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003126 | The City of Mesquite will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-01-28 | 2010-02-26 | 749979.1
7785 | Underway | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003127 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-01-24 |  | 1390263
7786 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003129 | Clark County will resurface the top four inches of approximately 1.8 miles of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smo | Pavement Improvement | 2010-07-12 | 2010-07-26 | 2010-10-31 | 2010-09-01 | 1903000
7787 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003130 | Clark County will resurface the top four inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing approximately eight miles. This extends the life of Lamb Blvd, T | Pavement Improvement | 2010-08-17 | 2010-08-17 | 2010-12-15 | 2011-01-20 | 5438550
7788 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003131 | Clark County will reconstruct 15 existing bus stops along Maryland Parkway between east Reno and Sahara. | Transportation Enhancements | 2010-01-24 | 2010-01-24 | 2010-02-25 | 2010-03-10 | 329814
7789 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | Multiple | 0003133 | Clark County will resurface the top four inches of approximately 3.2 miles of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smo | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2010-10-04 | 2010-10-08 | 3574342
7790 | Underway | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | Multiple | 0003134 | The City of Las Vegas will construct intersection improvements including traffic signals, lighting, median islands and sidewalk improvements at the intersections of Bonanza Road and Tonopah Ave. and S | Safety/Traffic Management | 2010-10-11 | 2010-10-20 | 2011-04-09 |  | 775671
7791 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 02 | 0003140 | The City of Mesquite will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 2010-04-26 | 2010-05-18 | 2010-06-25 | 2010-06-30 | 202658.4
7792 | Completed | C950 | Ferryboat | NEVADA | CLARK | LAS VEGAS | 01 | 0003141 | The City of North Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-08-02 | 2010-08-24 | 2010-10-31 | 2010-11-23 | 2135830
7793 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003142 | The City of Las Vegas will resurface the three inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 2010-05-17 | 2010-05-28 | 2010-09-20 | 2010-09-08 | 1609058
7794 | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003143 | The City of Henderson will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2010-07-21 | 2010-07-06 | 337230
7795 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | DOUGLAS |  | 02 | 0005018 | The Nevada Department of Transportation in coordination with Douglas County will resurface the existing asphalt with a two inches of new asphalt. This will improve driving quality by resurfacing the r | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-09-30 | 2010-08-31 | 511571
7796 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0007033 | The City of Elko will resurface the top inche of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of | Pavement Improvement | 2010-05-05 | 2010-05-05 | 2010-08-09 | 2010-08-18 | 868135
7797 | Underway | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | ESMERALDA |  | 02 | 0009005 | The Nevada Department of Transportation will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-12-06 |  | 2011-05-31 |  | 582401
7798 | Completed | C250 | Highway Infrastructure Investment Grant | NEVADA | EUREKA |  | 02 | 0011036 | Eureka County will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of 11th Street from | Pavement Improvement | 2010-05-19 | 2010-07-19 | 2010-08-06 | 2010-08-19 | 370980.2
7799 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0013019 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade sur | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2010-01-04 | 2010-05-03 | 1588585
7800 | Underway | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0013021 | The Nevada Department of Transportation will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-10-25 | 2010-10-26 | 2011-06-30 |  | 414766
7801 | Underway | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0013022 | The Nevada Department of Transportation will coldmill 3 inches depth of existing asphalt pavement and place a 5 inch plantmix asphalt overlay with cape seal. This will improve driving quality by resur | Pavement Improvement | 2010-10-25 | 2010-10-26 | 2011-06-30 |  | 1122236
7802 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | LANDER |  | 02 | 0015015 | The Nevada Department of Transportation will resurface the existing asphalt with new asphalt, replace substandard street lights and repair damaged curb. This will improve driving quality by updating t | Pavement Improvement | 2010-08-23 | 2010-08-23 | 2010-10-01 | 2010-09-23 | 343332.03
7803 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | LINCOLN |  | 02 | 0017019 | The Nevada Department of Transportation will Place a chip seal on 6.2 miles of Rose Valley Rd,West of Ursine in Lincoln County, Nevada. to extend its service life. | Pavement Improvement | 2010-10-12 | 2011-06-06 | 2011-05-31 | 2011-06-30 | 426960
7804 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | LYON |  | 02 | 0019019 | The Nevada Department of Transportation will place Geotextile Fabric and a 2.5 inch overlay with fog seal on 1.9 miles of Six Mile Canyon Rd. to restore the pavement structure and extend its service l | Pavement Improvement | 2010-11-01 | 2011-06-13 | 2010-12-31 | 2011-07-08 | 641720
7805 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | LYON |  | 02 | 0019020 | The Nevada Department of Transportation in coordination with the City of Fernley will preserve and extend the pavement life of various city streets by placing a slurry seal over the existing roadway. | Pavement Improvement | 2010-09-13 | 2010-09-14 | 2010-09-28 | 2010-09-17 | 132568.68
7806 | Completed | C250 | Highway Infrastructure Investment Grant | NEVADA | MINERAL |  | 02 | 0021045 | Nye County will preserve and extend the pavement life of a section of Gamebird Rd. by placing a 3.5 inch asphalt overlay on the existing roadway. | Safety/Traffic Management | 2010-12-13 | 2010-12-13 | 2011-12-31 | 2011-03-30 | 167001.44
7807 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | NYE |  | 02 | 0023011 | Nye County will preserve and extend the pavement life of a section of Gamebird Rd. by placing a 3.5 inch asphalt overlay on the existing roadway. | Pavement Improvement | 2010-10-04 | 2010-10-27 | 2010-10-15 | 2010-11-03 | 533738
7808 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEVADA | CARSON CITY | CARSON CITY | 02 | 0025016 | Carson City will preserve and extend the pavement life of several city streets by placing a thin asphalt/slurry overlay on the existing roadways | Pavement Improvement | 2010-05-03 | 2010-05-12 | 2010-10-01 | 2010-07-01 | 664415
7809 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | PERSHING |  | 02 | 0027016 | The Nevada Department of Transportation will add sidewalks to increase the safety of pedestrians and make routes ADA compliant on 0.71 miles of roads in Lovelock, Nevada. | Transportation Enhancements | 2010-08-02 | 2010-08-02 | 2010-08-31 | 2010-08-27 | 118742.17
7810 | Underway | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | PERSHING |  | 02 | 0027017 | The Nevada Department of Transportation in coordination with Pershing County will preserve and extend the pavement life of about 1.5 miles of Grass Valley Rd. south of Dutchman Dr. by placing a 3 inch | Pavement Improvement | 2010-10-25 | 2010-10-26 | 2011-06-30 |  | 451058
7811 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | STOREY |  | 02 | 0029013 | The Nevada Department of Transportation in coordination with Storey County will preserve and extend the pavement life of about 2.7 miles of Six Mile Canyon Rd. in various locations by placing a 2.5 in | Pavement Improvement | 2010-11-01 | 2011-06-13 | 2010-12-31 | 2011-07-08 | 538439
7812 | Completed | C220 | Highway Infrastructure Investment Grant | NEVADA | CARSON CITY, LYON |  | 02 | 0032071 | The Nevada Commission for the Reconstruction of the V&T Railway will construct just over one mile of railroad track along of the historic Virginia and Truckee Railway roadbed on existing railroad grad | Transportation Enhancements | 2009-07-16 | 2009-07-21 | 2009-11-04 | 2009-11-06 | 2033873.63
7813 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | WHITE PINE |  | 02 | 0033014 | The Nevada Department of Transportation will place a slurry seal on 3 miles of streets in Ely, Nevada to extend their service life. | Pavement Improvement | 2010-05-24 | 2010-06-28 | 2010-10-11 | 2010-11-17 | 191503
7814 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | WHITE PINE |  | 02 | 0033015 | The Nevada Department of Transportation will construct curb, gutter, sidewalk on the south side of the street on SR 221 Chestnut St. from 6th St. to 10th St to provide pedestrian enhancements in Carli | Pavement Improvement | 2010-05-24 | 2010-06-28 | 2010-10-11 | 2010-11-17 | 593083
7815 | Underway | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK |  | 02 | 0151140 | NDOT will use asphalt overlay on I-15 From CA/NV Stateline to Milepost 17.00 (CL0.00 to CL17.00) as part of the pavement preservation program. | Pavement Improvement | 2009-11-23 | 2010-05-17 | 2010-09-06 |  | 8379233 | 16.000
7816 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 02 | 0152039 | NDOT will use asphalt overlay on I-15 from .369 MN of East Mesa Intg. To 1.033 MW of the Bunkerville Intg. from 1.033 MW of Bunkerville Intg. To 1.889 MS of West Mesquite Intg. as part of the pavemen | Pavement Improvement | 2010-05-10 | 2010-05-17 | 2010-09-10 | 2010-11-08 | 5016680.5
7817 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0221004 | The Nevada Department of Transportation in coordination with the City of Carlin will construct curb, gutter, sidewalk on the south side of the street on SR 221 Chestnut St. from 6th St. to 10th St. | Transportation Enhancements | 2010-07-27 | 2010-07-27 | 2010-08-24 | 2010-08-15 | 213766.45
7818 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0223002 | The Nevada Department of Transportation in coordination with the City of Wells will construct pedestrian improvements including curb, gutter, sidewalk on the east side of the street on SR 223 Humboldt | Transportation Enhancements | 2010-07-26 | 2010-07-26 | 2010-08-27 | 2010-09-02 | 175500
7819 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0289001 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2010-01-04 | 2010-05-03 | 1011170
7820 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | STATEWIDE |  |  | 0318013 | The Nevada Department of Transportation will generally cold in place recycle 3 inches depth of existing asphalt pavement, a 3 inch plantmix asphalt overlay with open grade surface course, or 8 inch ro | Pavement Improvement | 2009-07-13 | 2009-07-27 | 2010-02-22 | 2010-09-24 | 14016262
7821 | Underway | C240 | Highway Infrastructure Investment Grant | NEVADA | CHURCHILL |  | 02 | 0801165 | The Nevada Department of Transportation will cold mill 1.5 inches depth of existing asphalt pavement and place a plantmix asphalt overlay with open grade surface course. This will improve driving qual | Pavement Improvement | 2009-12-21 | 2010-05-17 | 2010-06-21 |  | 10820369
7822 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | PERSHING |  | 02 | 0802052 | NDOT will preserve and extend the pavement life of about 14 miles of I-80 by milling 1 inch of existing pavement and replacing it with 3 inches of new asphalt and an open-graded wearing course. | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-12-07 | 2010-09-16 | 12349915
7823 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | LANDER |  | 02 | 0803059 | The Nevada Department of Transportation will construct 8 inch roadbed modification with 5.5 inches of plantmix asphalt with open grade surface course. This will improve driving quality by resurfacing | Pavement Improvement | 2009-07-20 | 2009-08-17 | 2009-10-26 | 2009-11-30 | 2007907.83
7824 | Underway | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK |  | 02 | 0932002 | NDOT will use asphalt overlay on US93 from 15.82 miles N of I15 at Garnet Interchange to the CL/LN County Line (CL67.83 to CL86.59) as part of the pavement preservation program. | Pavement Improvement | 2009-09-14 | 2010-04-05 | 2010-09-13 |  | 6609682 | 19.000
7825 | Completed | C250 | Highway Infrastructure Investment Grant | NEVADA | LINCOLN |  | 02 | 0932004 | The Nevada Department of Transportation will construct will pedestrian improvements including curb, gutter and sidewalk on US 93 from .50 MW of SR 317 to .05 MW of SR 317. | Transportation Enhancements | 2009-11-20 | 2009-11-20 | 2010-10-08 | 2010-10-10 | 136017
7826 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | WHITE PINE |  | 02 | 0934016 | The Nevada Department of Transportation will resurface the top three inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road sm | Pavement Improvement | 2010-05-24 | 2010-06-28 | 2010-10-11 | 2010-11-17 | 9921759
7827 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0935006 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 3 inch plantmix asphalt overlay with open grade surface course. This will imp | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-07 | 2010-08-10 | 10645650
7828 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0935007 | The Nevada Department of Transportation will construct a approximately 66 feet wide by 162 feet long precast concrete arch overpass in a location with a history of many animal/vehicle collisions and a | New Bridge Construction | 2009-08-10 | 2009-09-09 | 2009-11-28 | 2010-08-09 | 1075515
7829 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 093A004 | The Nevada Department of Transportation in coordination with the City of West Wendover will construct curb, gutter, sidewalk on the east side of the street on US 93A from W. Wendover Blvd to I 80 WB O | Transportation Enhancements | 2010-08-16 | 2010-08-16 | 2010-09-16 | 2010-09-15 | 183090
7830 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK |  | 03 | 0951041 | NDOT will build a Visitor's Center on US 95 to enhance the experience of the travelling public. | Transportation Enhancements | 2009-07-15 | 2009-07-15 | 2011-02-16 |  | 3389007 | 0.000
7831 | Underway | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0952054 | NDOT will use asphalt overlay on US 95 from 0.737 MN of SR157, Charleston Park Road, to 7.716 MN of SR156, Lee Canyon Road, as part of the pavement preservation program. | Pavement Improvement | 2010-05-10 | 2010-05-17 | 2011-03-17 |  | 29772969
7832 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0952055 | NDOT will perform landscaping on US95 from Martin Luther King Blvd. to Rainbow Blvd. | Transportation Enhancements | 2009-09-21 | 2009-09-29 | 2010-07-05 | 2009-11-30 | 3477042
7833 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | NYE |  | 02 | 0952056 | NDOT will use asphalt overlay on US 95 from 1.63 mi S of Jackass Flat to 0.62 mi N of SR 160. MP NY6.98 - NY14.38 as part of the pavement preservation program. | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2009-11-23 | 2009-11-16 | 2161370.54 | 7.000
7834 | Completed | C250 | Highway Infrastructure Investment Grant | NEVADA | MINERAL |  | 02 | 0954015 | The Nevada Department of Transportation in coordination with Mineral County expects to improve traffic management and pedestrian safety at the intersection of US 95 and SR 359 in Hawthorne by upgradin | Safety/Traffic Management | 2010-12-13 | 2010-12-20 | 2011-12-31 | 2011-03-30 | 46561
7835 | Underway | C240 | Highway Infrastructure Investment Grant | NEVADA | MINERAL |  | 02 | 0954016 | 3 inch cold in place recycle, 3 inch PBS overlay | Pavement Improvement | 2011-01-18 |  | 2011-06-30 |  | 3301774
7836 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0956007 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2010-01-04 | 2010-05-03 | 1191458
7837 | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0956008 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2010-01-04 | 2010-05-03 | 3256353
7838 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NEVADA | DOUGLAS, CARSON CITY | CARSON CITY | 02 | 3951021 | The Nevada Department of Transportation in coordination with Douglas County will widen US 395 in the northbound direction for approximately 6000 feet from Sunridge Dr. east to Lupin Dr. This will all | Pavement Widening | 2010-04-26 | 2010-04-26 | 2010-10-08 |  | 3018798
7839 | Underway | C220,C200,C240 | Highway Infrastructure Investment Grant | NEVADA | CARSON CITY | CARSON CITY |  | 3951022 | NEVADA DEPARTMENT OF TRANSPORTATION WILL PERFORM LANDSCAPING ON US395, CARSON CITY BYPASS, AT 5TH STREET GRADE SEPARATION AND FAIRVIEW INTERCHANGE. | Transportation Enhancements | 2010-07-12 | 2010-10-25 | 2010-09-10 |  | 1314644
7840 | Underway | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 5151036 | Landscaping | Transportation Enhancements | 2010-12-20 | 2011-01-31 | 2011-04-22 |  | 1001178
7841 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEVADA | WASHOE | RENO | 02 | 5801029 | The NDOT and the Regional Transportation Commission (RTC) of Washoe County will reconfigure the existing Neil Rd. Interchange to a split diamond configuration with Meadowood Mall Way and extend Meadow | New Construction | 2010-05-17 | 2010-06-14 | 2012-02-21 |  | 18473423
7842 | Underway | C490 | OJT/SS | NEVADA | STATEWIDE |  |  | FY09002 | Work necessary to train minorities, women and disadvantaged individuals to become commercial vehicle operators | Other | 2011-04-12 | 2011-04-12 | 2012-12-31 |  | 240428
7843 | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000091 | The Winnipesaukee River Trail Phase 2B project extends an existing 3 mile bicycle and pedestrian trail facility by providing signs for a temporary connection from Park Street in Northfield to Morrison | Transportation Enhancements | 2010-02-09 | 2010-05-17 | 2010-08-30 | 2010-11-16 | 429646.25 | 1.000
7844 | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH |  | 02 | A000094 | In Hillsborough, on route US 202/NH 9, a historic stone arch bridge will be preserved and resurfaced to better accommodate pedestrians and bicycles | Transportation Enhancements | 2009-10-20 | 2010-05-10 | 2010-06-14 | 2010-07-23 | 150045 | 0.000
7845 | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH | NASHUA | 02 | A000095 | In Hudson, the town will be building almost a mile of new sidewalk and a nearly mile long bicycle lane on Route 102 between Evergreen Drive and Megan. | Transportation Enhancements | 2009-07-17 | 2010-07-19 | 2010-07-01 | 2010-09-30 | 357000 | 0.000
7846 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 02 | A000127 | On I-93 near Exit 3 in the Salem and Windham area, new northbound and southbound travel lanes will be constructed to improve safety and relieve congestion. | New Construction | 2009-05-07 | 2009-06-17 | 2011-11-01 | 2012-03-15 | 27885145.95 | 2.200
7847 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH |  | 01 | A000258 | This project will widen the FE Everett Turnpike to provide improved access to and from the Manchester-Boston Regional Airport. | Pavement Widening | 2009-04-16 | 2009-05-11 | 2011-06-01 | 2011-07-06 | 9615508.68 | 2.900
7848 | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH |  | 02 | A000341 | In Bennington, this project will provide over a half-mile of sidewalk with crosswalks, and will clearly separate these facilities from vehicular traffic and parking to improve pedestrian access and sa | Transportation Enhancements | 2009-07-22 | 2009-08-10 | 2010-05-01 | 2010-09-30 | 601600.1 | 0.000
7849 | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000342 | This project in Boscawen will provide new sidewalks on Main Street through the route US3/4 intersection and along King Street. New crosswalks and pedestrian signals will enhance pedestrian safety at t | Transportation Enhancements | 2009-08-19 | 2009-09-24 | 2010-05-01 | 2010-05-27 | 440231.5 | 0.000
7850 | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STRAFFORD |  | 01 | A000345 | On Durham's Main Street near the downtown area and the University of New Hampshire, this project will improve bicycle and pedestrian access and mobility by providing over a mile of new sidewalks, sepa | Transportation Enhancements | 2009-11-13 | 2009-12-08 | 2010-09-30 | 2010-08-30 | 758258.55 | 0.000
7851 | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | BELKNAP |  | 01 | A000349 | This project will provide around 1.5 miles of trail within an active rail corridor for bicyclists and pedestrians that will run from Main Street in Laconia to Elm Street in Lakeport. Improvements will | Transportation Enhancements | 2009-08-31 | 2009-09-03 | 2009-12-01 | 2010-06-22 | 575980.5 | 0.000
7852 | Completed | C200 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH | MANCHESTER | 01 | A000390 | This project consists of earthwork west of the Merrimack River for Manchester Airport Access Road. | New Construction | 2009-07-17 | 2009-08-05 | 2011-06-01 | 2010-11-08 | 4110519.37 | 0.620
7853 | Completed | C220,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM |  | 02 | A000558 | The Windham Depot project will provide a restored historic train depot that will function as a combined visitor center, museum and way station at the head of a 4 mile bicycle and pedestrian trail from | Transportation Enhancements | 2010-03-02 | 2010-03-15 | 2010-07-15 | 2010-07-15 | 219755 | 0.000
7854 | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH |  | 02 | A000566 | This project in Litchfield will help improve pedestrian and bicycle access and mobility by building nearly 2 miles of pedestrian and bike trail along Albuquerque Avenue. | Transportation Enhancements | 2009-09-10 | 2009-09-25 | 2010-05-15 | 2010-05-17 | 372477.25 | 0.000
7855 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM |  | 01 | A000620 | In Epping and Exeter, this project will provide new pavement on a 9.5 mile section of State Route 101 between Exit 6 and the Squamscott River Bridge in Exeter. | Pavement Improvement | 2009-04-02 | 2009-04-10 | 2009-08-01 | 2009-11-03 | 7073670.8 | 9.740
7856 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000837 | This project will provide a thin layer of new pavement on about 7 miles of I-89 roadway from Exit 12A to Exit 13 in the New London and Grantham area. | Pavement Improvement | 2009-05-07 | 2009-06-04 | 2009-09-01 | 2009-09-22 | 1032533.01 | 6.086
7857 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000838 | This project will provide crack filling and will provide a thin layer of new pavement on 4.9 miles of I-393 from I-93 to it's ending point in the Concord area. | Pavement Improvement | 2009-06-18 | 2009-06-24 | 2009-09-01 | 2009-11-03 | 817740 | 3.197
7858 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000839 | This project provides new pavement to 5.4 miles of I-93 from Exit 14 to Exit 17 from the Concord area to Canterbury. Guardrail posts will also be replaced to improve safety. | Pavement Improvement | 2009-06-18 | 2009-06-24 | 2010-10-01 | 2010-09-29 | 5356186 | 6.170
7859 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000840 | This project in the Sanbornton area provides new pavement on a 4 mile section of I-93 from north of Exit 19 in Northfield to Exit 22 in Sanbornton. The project also includes some bridge rehabilitation | Pavement Improvement | 2009-05-21 | 2009-06-29 | 2010-06-01 | 2010-07-28 | 2188626 | 6.270
7860 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | GRAFTON |  | 02 | A000841 | This project provides new pavement on 7 miles of I-93 from Plymouth to Thornton, just south of the Exit 27 interchange north to the railroad bridge. | Pavement Improvement | 2009-05-21 | 2009-06-09 | 2009-10-01 | 2009-10-14 | 747127.22 | 7.830
7861 | Completed | C200 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 01 | A000842 | This Portsmouth area project provides new pavement and some bridge deck and guardrail improvements for safety on about 1 and a half miles of I-95 from the Portsmouth traffic circle to the bridge over | Pavement Improvement | 2009-07-17 | 2009-07-30 | 2010-08-01 | 2010-09-01 | 3470149.15 | 12.966
7862 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | GRAFTON |  | 02 | A000843 | This project provides new pavement and bridge improvements on 5.4 miles of I-93 from Exit 30 to Exit 32 in the Woodstock and Lincoln areas. | Pavement Improvement | 2009-07-17 | 2009-07-30 | 2011-08-26 | 2011-09-02 | 9082359.5 | 58.275
7863 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000845 | This project is located in the New Hampton and Ashland and will provide new pavement and bridge improvements on about 6 miles of I-93. | Pavement Improvement | 2009-05-21 | 2009-06-04 | 2010-06-01 | 2010-08-11 | 3924108.25 | 6.083
7864 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000846 | This New London area project on 5 miles of I-89 provides new pavement from Exit 11 north to Exit 12A. | Pavement Improvement | 2009-04-02 | 2009-04-21 | 2010-08-01 | 2010-09-24 | 5315917 | 6.310
7865 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000871 | This project provides new pavement on various roadways in the counties of Coos, Carroll, and Grafton. | Pavement Improvement | 2009-04-02 | 2009-05-05 | 2009-09-01 | 2009-11-04 | 3297522.19 | 56.580
7866 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000872 | This project is located along multiple sections of roadway within the counties of Grafton, Sullivan, and Merrimack. The project involves the resurfacing of approx. 48 miles of various roadways.; all | Pavement Improvement | 2009-04-02 | 2009-05-14 | 2009-09-02 | 2009-11-02 | 3161306.53 | 47.180
7867 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000873 | This project provides about 48 miles of new pavement along many sections of roadway in Carroll, Grafton, and Belknap counties. | Pavement Improvement | 2009-04-16 | 2009-05-27 | 2009-09-03 | 2009-10-26 | 3118908.13 | 47.260
7868 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000874 | This project provides new pavement and safety improvements on about 41 miles of multiple sections of roadway in Cheshire and Hillsborough counties. | Pavement Improvement | 2009-05-07 | 2009-05-20 | 2009-09-01 | 2010-07-13 | 2710153.4 | 40.630
7869 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000875 | This project provides about 28 miles of new pavement on various sections of roadway in Merrimack, Hillsborough and Rockingham counties. | Pavement Improvement | 2009-05-07 | 2009-05-28 | 2009-09-01 | 2009-08-26 | 3009237.13 | 35.320
7870 | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI |  | A000876 | This project provides new pavement and intersection safety improvements on various roadways in Rockingham and Strafford counties. | Pavement Improvement | 2009-05-07 | 2009-06-11 | 2009-09-01 | 2009-11-09 | 2941966.74 | 43.380
7871 | Underway | C200 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | GRAFTON |  | 02 | A000947 | This project on I-89 provides a more efficient I-89/NH 12A interchange at Exit 20 in Lebanon. The project includes bridge and ramp improvements for the interchange, including the bridge over the K-Mar | Pavement Widening | 2009-10-08 | 2009-10-13 | 2011-10-28 |  | 14717629.33 | 0.900
7872 | Completed | C200 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A001014 | This project consists of 18 miles of roadway resurfacing in Cheshire, Hillsborough, and Sullivan counties. | Pavement Improvement | 2010-03-11 | 2010-04-08 | 2010-08-20 | 2010-06-28 | 973593 | 18.550
7873 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A001015 | This project consists of 42 miles of roadway resurfacing in Hillsborough, Merrimack, and Rockingham counties. | Pavement Improvement | 2010-03-11 | 2010-04-13 | 2010-08-20 | 2010-09-23 | 2118692 | 41.490
7874 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM |  | 01 | A001016 | This project consists of 41 miles of raodway resurfacing in Strafford and Rockingham counties. | Pavement Improvement | 2010-03-11 | 2010-06-11 | 2010-08-20 | 2010-08-12 | 1243349 | 41.280
7875 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | COOS |  | 02 | A001031 | This project consists of 72 miles of roadway resurfacing in Coos, Carroll, Grafton, Merrimack, and Sullivan counties. | Pavement Improvement | 2010-04-14 | 2010-04-23 | 2009-09-10 | 2010-10-13 | 4336142.4 | 72.700
7876 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM |  | 01 | A001049 | This project provides about 8 miles of roadway resurfacing, new guardrail and drainage improvements from Exeter to Hampton. | Pavement Improvement | 2010-02-09 | 2010-03-09 | 2010-09-10 | 2010-11-10 | 3287471.07 | 8.836
7877 | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | CAPE MAY |  | 02 | 0007109 | The Route 52 Causeway Contract B project replaces the two bridges located closest to Somers Point and Ocean City at Ship Channel and Beach Thorofare, respectively, with high level (55' clearance) brid | Bridge Replacement | 2009-07-10 | 2009-08-11 | 2012-01-25 |  | 73141235 | 1.090
7878 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 02 | 0012110 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2010-05-10 | 2010-08-02 | 2012-02-17 | 2010-11-19 | 843907 | 2.000
7879 | Completed | C200 | Highway Infrastructure Investment Grant | NEW JERSEY | ATLANTIC |  | 02 | 0016157 | This project will replace deteriorated pavement with new pavement along 4.5 miles of Route 30 in Hammonton and Mullica Townships in Atlantic County NJ. | Pavement Improvement | 2009-07-08 | 2009-08-24 | 2009-12-01 | 2009-09-28 | 2219021.71 | 4.400
7880 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 0016158 | This project will relieve flooding on Route 30 for 1.5 miles by upgrading pavement and replaceing the inlets, pipes and basins in Township of Pennsauken and City of Camden, Camden County. | Pavement Improvement | 2009-08-24 | 2009-09-21 | 2010-09-14 | 2010-11-10 | 9969216 | 1.650
7881 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 13 | 0018154 | The project will provide some full depth repairs, milling and overlay to either match existing grade or provide an increase in profile grade | Pavement Improvement | 2010-11-30 | 2011-04-15 | 2011-09-09 | 2011-08-22 | 6000000 | 8.050
7882 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN |  | 03 | 0019110 | The project will extend the life of the bridge by including deck repair and curb repair on the entire deck (2.75 miles) of Rt.72 over the Manhawkin Bay in Townships of Stafford and Ship Bottom, Ocean | Bridge Improvement | 2009-09-04 | 2009-09-16 | 2010-07-23 | 2010-04-22 | 4863700 | 2.150
7883 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN |  | 03 | 0022105 | This project provides for the preservation of pavement on this section of Route 37. It consists of milling and overlay to either match the existing grade or will provide a two to three inch increase | Pavement Improvement | 2010-07-29 | 2010-08-25 | 2011-01-24 | 2010-11-24 | 4692264 | 5.950
7884 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN |  | 03 | 0022106 | This section of Route 37 has a bridge structure that crosses over Barnegat Bay. This project will provides for patching the existing deck as required and will preserve the exiting deck with an overla | Pavement Improvement | 2010-07-28 | 2010-09-17 | 2011-06-28 | 2011-04-29 | 3689892 | 2.030
7885 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 04 | 0025101 | The project includes full depth repairs, milling and overlay to match existing grade. | Pavement Improvement | 2010-12-22 | 2011-03-04 | 2011-07-25 | 2011-05-24 | 1756199 | 3.910
7886 | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 06 | 0029163 | This project will design the work to replace the bridge deck of Route 18 over Route 1 in the city of New Brunswick, Middlesex County. | Other | 2009-09-01 | 2009-09-01 | 2012-05-08 |  | 1231172 | 0.500
7887 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | 04 | 0029166 | Project provides for milling and resurfacing within exiting pavement limits. | Pavement Improvement | 2011-01-14 | 2011-02-07 | 2011-11-18 | 2011-10-19 | 4141796 | 11.600
7888 | Completed | C200,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 12 | 0031124 | This project will replace deteriorated pavement with new pavement and improve water drainage along 1 one mile of Route 29 in West Amwell Township & City of Lambertville in Hunterdon County. | Pavement Improvement | 2009-08-19 | 2009-09-14 | 2010-10-04 | 2010-07-23 | 3247858 | 1.020
7889 | Completed | C200 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON |  | 12 | 0031125 | This project is the utility relocaitons associated with the Route 29 project in West Amwell Township & City of Lambertville in Hunterdon County. | Other | 2009-08-19 | 2009-09-14 | 2010-10-04 | 2010-07-23 | 168405 | 1.020
7890 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON |  | 09 | 0033274 | This project will paint two Route 1&9(Truck) movable bridges over the Hackensack and Passaic Rivers in the cities of Newark, Jersey City and Kearny, Hudson and Essex County. | Pavement Improvement | 2009-07-16 | 2009-11-02 | 2011-12-31 | 2011-11-30 | 31117257 | 1.060
7891 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER |  | 12 | 0033277 | This project will replace deteriorated pavement with new pavement along 2 miles of Route 1 in both northbound and southbound directions located in the Townships of Lawrence and West Windsor, Mercer Co | Pavement Improvement | 2009-07-30 | 2009-08-04 | 2009-10-30 | 2010-03-18 | 4192559 | 2.020
7892 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 06 | 0034109 | This project will replace the bridge decks of Rt 440 NB over Ramp WI and Ramp WK over CR 514. Both bridges are within the interchange of RT 440, CR 514 and NJTA exit 10. in the township of Edison, Mi | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2010-06-01 | 2010-07-26 | 4804851 | 0.270
7893 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 13 | 0034110 | This project will design the work to replace the bridge deck of Route 440 Ramp V over Boggs Street, West Side Avenue, State Street and NJ transit in the city of Perth Amboy, Middlesex County. | Other | 2009-07-30 | 2009-10-09 | 2010-09-01 | 2011-04-05 | 1038189 | 0.230
7894 | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION |  | 10 | 0040168 | This project will replace the Route 22 bridge over the Conrail railroad and Liberty Avenue and improve safety by eliminating the substandard roadway features in Hillside Township, Union County. | Bridge Replacement | 2010-04-26 | 2010-05-26 | 2013-02-15 |  | 25556508 | 0.460
7895 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 09 | 0056151 | This project will design the work for a bridge deck replacement for Route 4 over Flat Rock Road in Englewwod City Bergen County | Other | 2009-08-31 | 2009-08-31 | 2010-09-30 | 2011-11-22 | 410961 | 0.200
7896 | Completed | C200,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CAPE MAY | ATLANTIC CITY | 02 | 0102113 | Cape May County will be preserving two of it's bridges structural integrity and extend their useful life by re-painting the crossings. | Bridge Improvement | 2010-08-16 | 2010-08-23 | 2012-02-17 | 2011-11-30 | 4395971 | 0.000
7897 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SALEM | ATLANTIC CITY | 02 | 0145101 | Salem County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on 2 miles | Pavement Improvement | 2010-08-30 | 2010-10-02 | 2012-02-17 | 2010-11-16 | 595605 | 4.180
7898 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0158104 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 2009-11-11 | 2009-11-19 | 2012-02-17 | 2009-11-30 | 338079.49 | 1.500
7899 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0158105 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-04-05 | 2010-04-05 | 2012-02-17 | 2010-04-21 | 415976.08 | 1.090
7900 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0158106 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-07-06 | 2010-07-06 | 2012-02-17 | 2010-08-10 | 290420.16 | 1.000
7901 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0160109 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2012-02-17 | 2010-05-04 | 314326 | 1.550
7902 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0160110 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-07-01 | 2010-07-19 | 2012-02-17 | 2010-08-20 | 199354.71 | 0.570
7903 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 02 | 0161103 | Gloucester County will install a new traffic signal to reduce travel delays, provide pedestrian crossings, and allow emergency access for the Fire Department. The project will also provide a new pave | Other | 2010-04-14 | 2010-04-17 | 2012-02-17 | 2010-09-24 | 286861 | 0.060
7904 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 0164101 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2010-09-27 | 2010-09-27 | 2010-02-17 | 2010-12-02 | 512445 | 1.400
7905 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0165101 | Morris County will improve two intersections along Ridgedale Ave to improve traffic flow, increase safety for pedestrians, and provide emergency access for the fire department. | Other | 2010-06-14 | 2010-06-28 | 2012-02-17 |  | 262561 | 0.200
7906 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 0169101 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2009-11-09 | 2009-11-09 | 2012-02-17 | 2010-05-07 | 454516.08 | 1.100
7907 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | Multiple | 0169102 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2010-06-21 | 2010-07-06 | 2012-02-17 | 2010-08-27 | 1281241 | 2.500
7908 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 0177106 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2009-11-02 | 2009-11-23 | 2012-02-17 | 2010-05-05 | 2618616 | 7.200
7909 | Underway | C250,C200 | Highway Infrastructure Investment Grant | NEW JERSEY | ATLANTIC |  | 02 | 0181112 | This project will replace the Tuckahoe Road Bride over the NJ Tranist Cape May Branch in the City of Estell Manor, Atlantic County. | Bridge Replacement | 2010-03-02 | 2010-03-08 | 2012-02-17 |  | 4779469 | 0.200
7910 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN | ALLENTOWN-BETHLEHEM-EASTON (PA) | 05 | 0378108 | Warren County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Other | 2010-03-18 | 2010-04-01 | 2012-02-17 | 2010-06-10 | 682081 | 3.040
7911 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN | NEW YORK-NORTHEASTERN NJ (NY) | 05 | 0378109 | Warren County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Other | 2010-03-18 | 2010-04-01 | 2012-02-17 | 2010-06-10 | 2191581.01 | 0.000
7912 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 05 | 0386103 | Sussex County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Pavement Improvement | 2010-05-11 | 2010-05-19 | 2012-02-17 | 2010-07-06 | 1013716.23 | 5.100
7913 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 05 | 0393108 | Sussex County will be rehabilitating the roadway to provide structural improvements and a new driving surface. This will improve driving quality by rehabilitating the road, which will make the road | Pavement Improvement | 2010-06-28 | 2010-07-01 | 2012-02-17 | 2010-08-13 | 734257 | 3.540
7914 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX |  | 10 | 0785101 | This project will replace deteriorated pavement with new pavement and improve safety along nearly 2 miles of I-78 in the City of Newark, Essex County. | Pavement Improvement | 2009-07-20 | 2009-08-31 | 2010-11-10 | 2011-04-01 | 15323524 | 1.430
7915 | Completed | C200 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON |  | 07 | 0785102 | This project will design the work to replace the bridge deck of I-78 ramp A, over I-78 in Township of Clinton Hunterdon County. | Other | 2009-08-31 | 2009-08-31 | 2010-09-01 | 2010-09-09 | 407158.89 | 0.500
7916 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN |  | 05 | 0785103 | This project will remove the existing concrete slabs and replace with new pavement for nearly 1 mile on I-78 in Greenwich Township, Warren County. | Pavement Improvement | 2009-08-18 | 2009-09-14 | 2010-08-01 | 2010-05-11 | 4176488 | 0.540
7917 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 07 | 0785104 | The project will replace the existing deck on the I-78 Ramp 'A' over I-78 structure (Str. #1018-150) | Bridge Improvement | 2010-12-14 | 2011-02-01 | 2011-10-18 | 2011-07-26 | 1324369 | 0.060
7918 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC |  | 08 | 0805087 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 6 miles on I-80 Eastbound from West of Madison Ave to Polifly Road | Pavement Improvement | 2009-07-16 | 2009-08-19 | 2011-09-02 | 2010-11-01 | 17443515 | 6.500
7919 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX |  | 11 | 0805088 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 8 miles on I-80 westbound form East of South Beverwyck Road to West | Pavement Improvement | 2009-06-02 | 2009-06-24 | 2010-03-12 | 2010-06-30 | 9670759 | 7.700
7920 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS |  | 11 | 0805090 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and repairing bridge supports for the I-80 EB and WB bridges over Berkshire Valley Road i | Bridge Improvement | 2009-07-07 | 2009-07-29 | 2010-06-11 | 2011-12-22 | 10752697 | 0.590
7921 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC |  | 08 | 0805091 | This project will paint 5 bridges on Route I-80 in the Counties of Bergen, Essex, Passaic, Warren and Essex. | Pavement Improvement | 2009-09-14 | 2009-11-05 | 2010-12-05 | 2011-07-26 | 8099115 | 0.280
7922 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CUMBERLAND | ATLANTIC CITY | 02 | 1019113 | Cumberland County will repair the concrete joints and concrete sections along the curbs to allow for an asphalt overlay. This will improve driving quality by resurfacing the road, which will make the | New Construction | 2010-03-17 | 2010-03-17 | 2012-02-17 | 2011-01-04 | 742481 | 0.480
7923 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER |  | 04 | 1958056 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 5 miles on I-195 from the New Jersey Turnpike to just East of Imlay | Pavement Improvement | 2010-04-09 | 2010-04-21 | 2010-11-12 | 2010-10-14 | 10580678 | 7.540
7924 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX |  | 08 | 2806103 | This project will paint 16 bridges on Route I-280 between mile points 12.7 to 14.5 in the Cities of Newark, Orange, East and West Orange, Essex County | Pavement Improvement | 2009-07-28 | 2009-09-21 | 2011-08-15 | 2010-12-31 | 9000754 | 1.720
7925 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX |  | 10 | 2806105 | This project will paint 17 bridges on Route I-280 between mile points 7.5 to 11.1 in the Cities of Newark, Orange, East and West Orange, Essex County | Pavement Improvement | 2009-07-27 | 2009-11-02 | 2011-08-15 | 2011-08-05 | 6833569 | 3.620
7926 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 06 | 2873080 | This project will replace existing deteriorating bridge decks and pavement with new pavement, upgrade guardrails and improve water drainage on nearly 7 miles on I-287 NB and SB in Piscataway, Middlese | Pavement Improvement | 2009-09-14 | 2009-09-17 | 2011-11-09 | 2011-05-31 | 35871958 | 7.000
7927 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS |  | 11 | 2873081 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck for the I-287 NB bridge over Route 46 in Parsippany-Troy Hills, Morris County. | Pavement Improvement | 2009-07-10 | 2009-08-03 | 2009-09-30 | 2009-11-23 | 1967842 | 0.000
7928 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | SALEM |  | 02 | 2952121 | This project will address the painting needs for 49 bridges on the Route I-295 corridor in Gloucester and Salem Counties. | Pavement Improvement | 2009-08-31 | 2009-10-19 | 2010-09-01 | 2010-06-20 | 1924745 | 0.000
7929 | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 2952123 | This project will replace existing deteriorating bridge decks and pavement with new pavement, upgrade guardrails and improve water drainage on nearly 8 miles on I-295 NB and SB in West Deptford, Deptf | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2012-07-20 |  | 78835000 | 7.900
7930 | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 2952124 | This project provides the funding for the ROW acquisition to allow for the construction of a new alignment that carries I-295 mainline through the interchange of Route 42 and I-76 in Bellmawr and Mt. | Other | 2010-05-18 | 2010-05-18 | 2012-03-06 |  | 4807500 | 3.620
7931 | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER |  | 01 | 4001161 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-07-19 | 2010-07-19 | 2012-02-17 |  | 299040 | 0.000
7932 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | TRENTON (PA) | 01 | 4037107 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2012-02-17 | 2010-09-27 | 408495 | 0.900
7933 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 4145110 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-04-05 | 2010-05-07 | 2012-02-17 | 2010-12-13 | 290540 | 0.000
7934 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 4184101 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-05-17 | 2010-06-16 | 2012-02-17 | 2011-05-15 | 303447 | 0.000
7935 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 4187101 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-06-09 | 2010-07-26 | 2012-02-17 | 2011-05-15 | 359234 | 0.000
7936 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON |  | 04 | 4395101 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and repairing bridge supports for the Main St. (CR 543) over Rt. 206 bridge in Townships | Pavement Improvement | 2009-08-26 | 2009-10-28 | 2010-11-09 | 2010-08-18 | 1778130 | 0.020
7937 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | TRENTON (PA) | 04 | 5020111 | City of Trenton will resurface the top three inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and exte | Transportation Enhancements | 2010-11-25 | 2010-12-01 | 2012-02-17 | 2011-10-08 | 870404 | 0.450
7938 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 12 | 5036109 | Mercer County will improve the safety of three intersections by removing traffic signal poles from the center of the road, pedestrian enhancements, and operation improvements. | Safety/Traffic Management | 2010-11-12 | 2010-12-15 | 2010-02-17 | 2011-06-03 | 421324 | 0.360
7939 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | TRENTON (PA) | 04 | 5094101 | City of Trenton will resurface the top three inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and exte | Transportation Enhancements | 2010-10-08 | 2010-11-01 | 2012-02-17 | 2011-07-29 | 130091 | 0.210
7940 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 04 | 5094102 | City of Trenton will resurface the top three inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and exte | Transportation Enhancements | 2010-10-08 | 2010-11-09 | 2012-02-17 | 2011-04-29 | 205554 | 0.000
7941 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | 7044101 | This project will resurface 4 miles of roadway and improve water drainage from mile point 0 to mile point 4 on Route 35 in Berkely Township, Seside Heights, Seaside Park and Toms River, Ocean County. | Other | 2009-06-17 | 2009-08-31 | 2010-11-01 |  | 1491129 | 4.000
7942 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | 7044102 | This project will resurface 5 miles of roadway and improve water drainage from mile point 4 to mile point 9 on Route 35 in Toms River, Lavallette and Mantoloking, Ocean County. | Other | 2009-05-20 | 2009-05-20 | 2010-10-01 |  | 1498266 | 5.000
7943 | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | 12 | 7207103 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-09-22 | 2010-09-22 | 2012-02-17 |  | 901246 | 0.500
7944 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 07 | 7269101 | This project will extend the life of the bridge and improve safety replacing the existing deteriorated deck and in the Township of Woodbridge, Middlesex County. | Bridge Improvement | 2009-08-28 | 2009-08-27 | 2010-09-01 | 2010-08-20 | 2949930 | 0.300
7945 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 06 | 7390103 | Union County will replace signal equipment and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicle traffic. | Safety/Traffic Management | 2010-08-17 | 2010-11-08 | 2012-02-17 |  | 565805 | 0.060
7946 | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION |  | Multiple | 7510101 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-04-23 | 2011-06-01 | 2012-02-17 |  | 1015894 | 0.000
7947 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 07 | 7543104 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicl | Safety/Traffic Management | 2010-06-08 | 2010-06-21 | 2012-02-17 |  | 341694 | 0.300
7948 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | 7675115 | This project will design the work for a new bridge over the Hackensack River in Jersey City and Kearny, Hudson County. | Other | 2009-04-14 | 2009-08-27 | 2010-12-23 |  | 3471845 | 0.300
7949 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | 7675116 | This project will design the work for the approaches and a new bridge and over the Hackensack River in Jersey City and Kearny, Hudson County. | Other | 2009-08-04 | 2009-08-04 | 2011-03-23 |  | 9716313 | 0.600
7950 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS |  | 11 | 7741139 | This project will design the work to replace the bridge deck of County route 665 (Salem Street) over Route 10 over Randolph, Morris County. | Other | 2009-08-31 | 2009-08-31 | 2011-06-01 | 2011-08-02 | 611284.72 | 0.110
7951 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS |  | 11 | 7789102 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and is located in the Township of Montville, Morris County. in addition this project will | Bridge Improvement | 2009-07-14 | 2009-07-31 | 2010-04-26 | 2009-12-23 | 1338510 | 0.010
7952 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 09 | 7802160 | This project will replace two bridges at the intersection of Route 46 over Main Street , improve safety and drainage in the Borough of Lodi, Bergen County. | Pavement Improvement | 2009-05-28 | 2009-06-15 | 2012-09-01 | 2011-10-30 | 30817985 | 0.420
7953 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 09 | 7802163 | This project is the utility relocaitons associated with the Route 46 over Main Street in the Borough of Lodi, Bergen County. | Other | 2009-05-28 | 2009-06-18 | 2012-09-01 | 2011-10-30 | 2644220 | 0.420
7954 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON |  | 10 | 7811116 | This project will replace deteriorated pavement with new pavement along 1.5 miles of Route 440 in both northbound and southbound directions from JFK Blvd. to 22nd street. The project is located in the | Pavement Improvement | 2009-07-28 | 2009-08-11 | 2009-11-19 | 2010-02-03 | 3271515 | 1.400
7955 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | 7851102 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at mult | Pavement Improvement | 2011-03-22 | 2011-03-22 | 2012-02-17 |  | 3630361 | 0.000
7956 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 09 | 8112137 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck of the Roff Avenue Bridge over Route 46 in Palisades Park, Bergen County. | Bridge Improvement | 2009-08-17 | 2009-11-02 | 2010-11-05 | 2010-08-06 | 2052177 | 0.000
7957 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC |  | 08 | 8112138 | This project will improve safety and extend the life of the Grove Street (CR 623) bridge over Route 46 in Clifton Passaic County, by replacing the existing deteriorated deck, and repairing bridge supp | Pavement Improvement | 2009-08-26 | 2009-10-14 | 2010-10-20 | 2010-11-12 | 3967255 | 0.100
7958 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 09 | 8112139 | This project is the utility relocaitons associated with the Roff Avenue bridge over Route 46 in Palisades Park, Bergen County. | Other | 2009-08-17 | 2009-11-04 | 2010-11-05 | 2010-08-06 | 261101 | 0.020
7959 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 05 | 8669101 | This project will extend the life of the bridge and improve safety and drainage by replacing the existing deteriorated deck and repairing bridge supports in Township of Mahwah, Bergen County NJ. | Bridge Improvement | 2009-06-18 | 2009-06-18 | 2009-08-14 | 2009-08-31 | 634674.85 | 0.030
7960 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | A00S961 | This project will improve the park appearance, promote and enhance pedestrian activities, and beautify the landscape. | Other | 2010-05-18 | 2010-05-18 | 2012-02-17 | 2010-06-17 | 111863.16 | 0.000
7961 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | STATEWIDE |  |  | B00S688 | The Statewide project will provide safety enhancement at hazardous highway-rail grade crossings to improve rail road crossing safety, improve visibility of traffic stripes and pavement markings, and i | Safety/Traffic Management | 2010-01-11 | 2010-02-26 | 2011-12-28 | 2011-11-18 | 1197121 | 0.000
7962 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON |  | 13 | B00S719 | This project will improve the walkway appearance, promote and enhance pedestrian activities, and beautify the landscape. | Transportation Enhancements | 2010-01-28 | 2010-01-28 | 2012-02-17 | 2011-02-11 | 1959312 | 0.000
7963 | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | STATEWIDE |  |  | B00S785 | This project (Contract #10) will provide guiderail down the middle of the roadway on 5.14 miles of Route 18 and 4.64 miles of Route I-95 in the Counties of Mercer, Middlesex, Monmouth. | Safety/Traffic Management | 2009-08-17 | 2009-09-30 | 2010-07-01 | 2010-07-22 | 3337794 | 8.220
7964 | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | STATEWIDE |  |  | B00S786 | This project (Contract #11) will provide guiderail down the middle of the roadway on 5.14 miles of Route 18 and 4.64 miles of Route I-95 in the Counties of Mercer, Middlesex, Monmouth. | Other | 2009-08-24 | 2009-09-14 | 2010-11-01 |  | 1203889 | 6.600
7965 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 05 | B00S793 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-20 | 2010-05-21 | 2012-02-17 | 2011-11-29 | 1122024 | 7.790
7966 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S794 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-07-01 | 2010-07-06 | 2012-02-17 | 2011-12-21 | 717055 | 3.760
7967 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S795 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-08-02 | 2010-08-03 | 2012-02-17 |  | 526642 | 3.500
7968 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S796 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-31 | 2010-08-04 | 2012-02-17 |  | 421770 | 1.760
7969 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S797 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-17 | 2010-05-19 | 2012-02-17 |  | 473998 | 2.030
7970 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S798 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-21 | 2010-05-21 | 2012-02-17 | 2011-12-09 | 679886 | 3.590
7971 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S799 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2012-02-17 |  | 559538 | 5.050
7972 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S800 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-06-21 | 2010-07-06 | 2012-02-17 |  | 416506 | 1.370
7973 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S801 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-06-07 | 2011-07-22 | 2012-02-17 |  | 904327 | 4.640
7974 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S802 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-08-09 |  | 2012-02-17 |  | 547322 | 3.390
7975 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S803 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-19 | 2010-06-17 | 2012-02-17 |  | 2265243 | 10.300
7976 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S804 | Sussex County will improve safety over Glen Brook by replacing the bridge. | New Bridge Construction | 2010-06-02 | 2010-08-09 | 2012-02-17 | 2010-10-20 | 449510 | 0.050
7977 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S805 | Sussex County will improve safety over the Sparta Glen Brook by replacing the bridge. | Bridge Replacement | 2010-06-08 | 2010-06-11 | 2012-02-17 | 2011-06-14 | 901238 | 0.090
7978 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S806 | Sussex County will extend the service life of the existing pavement and improve safety by providing a new asphalt surface. Additionally, new pavement markings will be installed to aid in night-time dr | Pavement Improvement | 2010-07-15 | 2010-10-25 | 2012-02-17 | 2010-11-15 | 55800 | 0.930
7979 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S814 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-04-12 | 2010-04-12 | 2012-02-17 | 2010-04-23 | 288685.87 | 1.300
7980 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S815 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-04-12 | 2010-04-12 | 2012-02-17 | 2010-04-23 | 382145.76 | 1.730
7981 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SOMERSET | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S816 | Somerset County will resurface the existing asphalt roadway with new asphalt on multiple County roads. This will improve driving quality by resurfacing the road, which will make the road smoother and | Transportation Enhancements | 2009-10-19 | 2009-10-21 | 2012-02-17 | 2010-07-31 | 4171290 | 15.300
7982 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | Multiple | B00S826 | Gloucester County will upgrade over 100 traffic signals to include new pedestrian signals. These signals will include count down timer displays. Count down timer displays provide additional informat | Other | 2010-05-10 | 2010-06-01 | 2012-02-17 | 2010-12-03 | 852080 | 0.000
7983 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S827 | Hunterdon County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and exten | Pavement Improvement | 2010-06-29 | 2010-06-29 | 2012-02-17 | 2010-08-26 | 1204869 | 6.850
7984 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S828 | Hunterdon County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and exten | Pavement Improvement | 2010-06-29 | 2010-07-06 | 2012-02-17 | 2010-10-28 | 1207278.05 | 6.600
7985 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CUMBERLAND | ATLANTIC CITY | 02 | B00S829 | Cumberland County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2012-02-17 | 2010-12-31 | 2350000 | 10.000
7986 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S830 | Ocean County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother and | Pavement Improvement | 2010-03-18 | 2010-02-18 | 2012-02-17 | 2010-07-23 | 2633333.03 | 9.500
7987 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S831 | Ocean County will upgrade the existing end treatments of the guide rails on 82 bridges to extruder end sections. This will bring each bridge with guide rail to current standards and enhances the safet | Safety/Traffic Management | 2010-01-18 | 2010-01-19 | 2012-02-17 | 2010-03-23 | 744896 | 1.000
7988 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S832 | Middlesex County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother | Pavement Improvement | 2010-06-14 | 2010-06-07 | 2012-02-17 |  | 5570022 | 16.000
7989 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S833 | Middlesex County will upgrade or install guiderail along many of the County's roadways to prevent vehicles from leaving the roadside and becoming involved in more hazardous collisions which in turn pr | Safety/Traffic Management | 2010-07-06 | 2010-07-06 | 2012-02-17 |  | 4185748 | 8.300
7990 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S834 | Essex County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at multi | Pavement Improvement | 2010-04-01 | 2010-04-14 | 2012-02-17 |  | 10134682 | 17.500
7991 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S835 | Morris County will upgrade the intersection to improve traffic flow and increase safety for pedestrians. | Other | 2010-06-04 | 2010-06-28 | 2012-02-17 | 2010-12-15 | 178819 | 0.100
7992 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S836 | Morris County will improve two intersections along Littleton Road to improve traffic flow and increase safety for pedestrians. | Other | 2010-06-14 | 2010-06-28 | 2012-02-17 | 2010-10-25 | 153537 | 0.050
7993 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 04 | B00S837 | City of Trenton will provide accessibility to all users at many intersections within the City by installing 145 curb ramps at intersections that meet the American with Disabilities Act regulations. | Safety/Traffic Management | 2010-08-30 | 2010-12-15 | 2010-02-17 | 2011-07-22 | 555541 | 0.000
7994 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | TRENTON (PA) | 04 | B00S838 | Mercer County will upgrade the pavement markings to regulate and guide traffic movements which in turn promotes safety. | Transportation Enhancements | 2011-01-30 | 2011-02-15 | 2012-02-17 | 2011-06-03 | 276718 | 0.000
7995 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN | TRENTON (PA) | 01 | B00S839 | Camden County will upgrade guiderail along many of the County's roadways to prevent vehicles from leaving the roadside and becoming involved in more hazardous collisions which in turn promotes safety. | Safety/Traffic Management | 2010-09-30 | 2010-09-27 | 2012-02-17 | 2011-08-15 | 1083401 | 0.000
7996 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | B00S840 | The City of Camden will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at | Safety/Traffic Management | 2010-08-09 | 2010-08-09 | 2012-02-17 | 2011-05-30 | 1681602 | 1.900
7997 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S846 | Monmouth County will resurface the existing asphalt roadway with new asphalt on multiple County roads. This will improve driving quality by resurfacing the road, which will make the road smoother and | Pavement Improvement | 2010-08-25 | 2010-08-30 | 2012-02-17 |  | 4960878 | 19.000
7998 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | 12 | B00S847 | Monmouth County will extend the life of the bridge and improve safety over the Manalapan Brook by reconstructing the bridge, rehabilitating the Millhurst Dam, and re-aligning CR 527. | Bridge Replacement | 2010-10-07 | 2010-10-11 | 2012-02-17 |  | 3261000 | 0.140
7999 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S848 | Monmouth County will upgrade the traffic signal equipment at multiple intersections within the County. The project will benefit vehicular and pedestrian traffic, reduce total vehicle delay, reduce ga | Pavement Improvement | 2010-10-29 | 2010-11-01 | 2012-02-17 |  | 3193298 | 0.000
8000 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | TRENTON (PA) | 12 | B00S849 | This project will replace existing outdated Walk/Don't Walk signals with Manual of Uniform Traffic Control Devices compliant pedestrian indications. These indications will provide users with better i | Transportation Enhancements | 2010-10-22 | 2010-10-25 | 2012-02-17 | 2011-05-15 | 274800 | 0.000
8001 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 04 | B00S850 | Mercer County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at 12 d | Pavement Improvement | 2010-08-30 | 2010-10-25 | 2012-02-17 | 2011-07-29 | 2157900 | 0.000
8002 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S857 | City of Elizabeth will upgrade the intersection traffic signal equipment. The project will benefit vehicular and pedestrian traffic. | Safety/Traffic Management | 2010-08-17 | 2010-09-21 | 2012-02-17 |  | 696003 | 0.000
8003 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S858 | Bergen County will extend the life of the bridge and improve safety over the Hackensack River by rehabilitating the bridge, reconstructing the approach spans, and upgrading the electrical equipment. | Bridge Improvement | 2010-06-23 | 2010-06-24 | 2012-02-17 |  | 17788000 | 0.000
8004 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S862 | Hudson County will realign and widen the roadway to accommodate increased traffic and improve safety. | Pavement Widening | 2010-09-01 | 2010-09-03 | 2012-02-17 |  | 500000 | 0.000
8005 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S863 | Hudson County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 2010-07-28 | 2010-08-11 | 2012-02-17 |  | 977034 | 0.000
8006 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | B00S864 | Ocean County will replace the Beach Boulevard Bridge along the existing alignment. | Bridge Replacement | 2010-02-01 | 2010-02-01 | 2012-02-17 | 2010-11-30 | 4658943 | 0.250
8007 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 04 | B00S865 | Ocean County will be preserving its bridge's structural integrity and extend its useful life by re-painting the crossing. | Bridge Improvement | 2010-03-08 | 2010-03-08 | 2012-02-17 | 2010-06-24 | 487726.96 | 0.100
8008 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S870 | Union City will beautify the roadway environment by providing a new driving surface, sidewalks, pedestrian crossings and curb ramps, landscaping, and new pavement markings. | Safety/Traffic Management | 2010-05-17 | 2010-08-16 | 2012-02-17 |  | 912988 | 0.000
8009 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S878 | Hudson County will upgrade 9 traffic signals to include new pedestrian signals. These signals will include count down timer displays. Count down timer displays provide additional information to pede | Safety/Traffic Management | 2010-07-28 | 2010-10-12 | 2012-02-17 | 2011-01-03 | 321932 | 0.000
8010 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S879 | Hudson County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 2010-07-28 | 2010-08-23 | 2012-02-17 |  | 849910 | 0.000
8011 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S890 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at mult | Pavement Improvement | 2010-06-02 | 2010-06-29 | 2012-02-17 | 2011-08-11 | 153301 | 0.000
8012 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S895 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Pavement Improvement | 2010-05-03 | 2010-05-10 | 2012-02-17 | 2010-07-23 | 718953 | 0.000
8013 | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | B00S898 | This project will restore and rehabilitate the historic Glassboro Train Station. | Transportation Enhancements | 2012-07-09 | 2012-07-10 | 2013-05-30 |  | 810834 | 0.000
8014 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER |  | 04 | B00S901 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-07-30 | 2010-08-30 | 2012-02-17 | 2011-05-31 | 994646 | 0.630
8015 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON | TRENTON (PA) | 04 | B00S909 | Burlington County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and exte | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2012-02-17 | 2011-07-30 | 2237000 | 11.900
8016 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 05 | B00S914 | Morris County will upgrade four miles of railroad track to improve safety and efficiency. | Other | 2010-05-28 | 2010-06-02 | 2012-02-17 | 2011-05-11 | 5411450 | 0.000
8017 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S915 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicl | Safety/Traffic Management | 2010-08-17 | 2010-10-25 | 2012-02-17 |  | 366019 | 0.000
8018 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S916 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicl | Safety/Traffic Management | 2010-08-17 | 2010-10-22 | 2012-02-17 |  | 245100 | 0.400
8019 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S918 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicl | Safety/Traffic Management | 2010-08-17 | 2010-10-29 | 2012-02-17 |  | 420325 | 0.000
8020 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S933 | Union County will extend the service life of the existing pavement and improve safety by providing a new asphalt surface. Additionally, new pavement markings will be installed to aid in night-time dri | Pavement Improvement | 2010-06-25 | 2010-06-30 | 2012-02-17 |  | 3745500 | 0.000
8021 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN |  | 05 | B00S936 | This project will promote and enhance pedestrian activities including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-09-08 | 2010-09-24 | 2012-02-17 | 2010-11-10 | 62604 | 0.290
8022 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S946 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-05-18 | 2010-06-14 | 2012-02-17 | 2011-11-16 | 283691 | 0.380
8023 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX |  | 11 | B00S949 | This project will improve and beautify appearance, promote and enhance pedestrian activities, and include sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-08-09 | 2010-09-23 | 2012-02-17 | 2011-08-04 | 337121 | 0.260
8024 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN |  | 03 | B00S950 | This project will promote and enhance pedestrian activities including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-10-01 | 2010-10-04 | 2012-02-17 | 2011-06-02 | 444481 | 0.300
8025 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S952 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Pavement Improvement | 2010-07-20 | 2010-07-22 | 2012-02-17 |  | 554804 | 0.000
8026 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | CUMBERLAND | ATLANTIC CITY | 02 | B00S953 | This project will restore the Bivalve Shipping Sheds. | Transportation Enhancements | 2010-05-24 | 2010-05-25 | 2012-02-17 | 2011-02-08 | 1250000 | 0.000
8027 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S958 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicl | Safety/Traffic Management | 2010-07-18 | 2010-09-22 | 2012-02-17 |  | 1118000 | 0.000
8028 | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | SOMERSET | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S959 | This project will improve, promote, and enhance pedestrian/bicycle activities. | Transportation Enhancements | 2010-06-08 | 2010-07-19 | 2012-02-17 |  | 2591113 | 0.540
8029 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 05 | B00S967 | This project will improve the historic train station on Garber Square and Franklin Avenue. | Transportation Enhancements | 2010-09-14 | 2010-09-14 | 2012-02-17 | 2011-04-28 | 376000 | 0.000
8030 | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON |  | 07 | B00S969 | This project will facilitate additional trail corridor through the acquisition of right of way to promote and enhance pedestrian activities. | Transportation Enhancements | 2010-02-18 |  | 2012-02-17 |  | 636000 | 0.000
8031 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | B00S983 | Camden County will upgrade guiderail along many of the County's roadways to prevent vehicles from leaving the roadside and becoming involved in more hazardous collisions which in turn promotes safety. | Safety/Traffic Management | 2010-10-15 | 2010-12-01 | 2012-02-17 | 2011-12-15 | 1158803 | 0.000
8032 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC |  | 08 | B00S984 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-05-19 | 2010-07-06 | 2012-02-17 | 2011-11-16 | 323937 | 0.660
8033 | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S986 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-10-22 | 2010-11-23 | 2012-02-17 |  | 446247 | 0.200
8034 | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON |  | 13 | B00S987 | Construction of the continuation of the Hudson River Waterfront Walkway in Jersey City | Transportation Enhancements | 2012-03-07 | 2012-03-08 | 2013-03-08 |  | 2861476 | 0.000
8035 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 05 | B00S989 | This project will restore and rehabilitate the historic Demarest Railroad Depot. | Transportation Enhancements | 2010-10-26 | 2010-12-02 | 2012-02-17 | 2011-10-03 | 186500 | 0.000
8036 | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S990 | City of Newark will resurface the existing asphalt roadway with new asphalt on multiple City roadways. This will improve driving quality by resurfacing the road, which will make the road smoother and | Pavement Improvement | 2010-11-12 | 2010-11-15 | 2012-02-17 |  | 4199085 | 9.910
8037 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S992 | City of Newark will upgrade the intersection traffic signal equipment. The project will benefit vehicular and pedestrian traffic, reduce total vehicle delay, reduce gasoline consumption, reduce air p | Safety/Traffic Management | 2011-03-11 | 2011-03-08 | 2012-02-17 |  | 331539 | 0.000
8038 | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S993 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2011-02-24 | 2011-03-09 | 2012-02-17 |  | 1839583 | 0.250
8039 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 12 | B00S994 | Mercer County will provide accessibility to all users along various roadways within the County by installing curb ramps to meet the American with Disabilities Act regulations. | Safety/Traffic Management | 2010-10-22 | 2010-10-25 | 2012-02-17 | 2011-07-29 | 359500 | 0.000
8040 | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN | ALLENTOWN-BETHLEHEM-EASTON (PA) | 05 | B00S995 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-06-28 | 2010-07-12 | 2012-02-17 | 2011-05-11 | 868424 | 0.320
8041 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | B00S999 | Gloucester County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of the | Pavement Improvement | 2010-09-20 | 2010-09-27 | 2012-02-17 | 2011-05-16 | 890452 | 1.700
8042 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 04 | C00S001 | Burlington County will improve vehicular and pedestrian traffic by upgrading 15 intersections. This work will include replacing the traffic signal equipment, timing and phasing improvements, and link | Safety/Traffic Management | 2010-07-26 | 2010-08-02 | 2012-02-17 | 2011-08-30 | 4368450 | 0.000
8043 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | C00S014 | Gloucester County will improve safety over Great Egg Harbor River by replacing the bridge. | Bridge Replacement | 2010-09-20 | 2010-09-27 | 2012-02-17 | 2011-03-18 | 1069840 | 0.020
8044 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON | STATEWIDE | 04 | C00S060 | Delaware River Heritage Trail | Transportation Enhancements | 2011-07-22 |  | 2012-02-17 |  | 1385200 | 0.000
8045 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | C00S109 | Resurfacing and various safety improvements | Pavement Improvement | 2011-04-28 | 2011-05-03 | 2012-02-17 | 2011-06-06 | 900000 | 2.300
8046 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | C00S110 | Resurfacing and various safety improvements | Pavement Improvement | 2011-08-01 | 2011-08-01 | 2012-02-17 |  | 1500000 | 3.500
8047 | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | C00S111 | Resurfacing and various safety improvements | Pavement Improvement | 2011-10-10 | 2011-10-10 | 2012-02-17 |  | 1100000 | 1.300
8048 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 04 | PLHD001 | Ocean County will improve the intersection to improve traffic flow and increase safety. | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2012-02-17 | 2010-09-21 | 188345.73 | 0.400
8049 | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 12 | TCSP004 | Reconstruction of Park Avenue | Other | 2010-09-27 | 2010-09-27 | 2012-02-17 | 2011-08-05 | 1023000 | 0.000
8050 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | EDDY |  | 02 | 0062004 | Project consists of construction of two new lanes on US62/180 (northbuond lanes) between White City and Carlsbad to allow for a four lane highway. Project consists of new roadway, shoulders, striping, | Pavement Widening | 2009-04-08 | 2009-04-08 | 2010-10-07 | 2010-08-25 | 14038283.54 | 10.000
8051 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA | LAS CRUCES | 02 | 0102111 | The I-10 six lane project will provide a total of (3) lanes for both east and west bound traffic, the additional lanes will be constructed within NMDOT ROW, this project is 18.3 miles in length, sta | Pavement Widening | 2009-11-30 | 2009-12-23 | 2011-07-13 | 2011-07-11 | 10000000 | 20.400
8052 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | GRANT |  | 02 | 0356005 | The project will include rebuilding and aligning of the curb and gutter, sidewalks, lighting and improvements so that people with disabilities will be able to use the sidewalks. It will, also, includ | Pavement Improvement | 2010-02-02 | 2010-03-08 | 2010-06-16 | 2010-08-12 | 349999.99
8053 | Completed | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO | ALBUQUERQUE | 03 | 0403104 | The City of Albuquerque proposes to construct a trail which would connect existing facilities to enhance the multi-modal transportation network | Transportation Enhancements | 2009-10-26 | 2009-10-26 | 2010-07-26 | 2011-01-18 | 4056007.91
8054 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 01 | 0403168 | Reconstruction of I-40 and West Central consists of construction of a new overpass over I-25, new on and off ramps, new construction of Paseo Del Volcan and Central Avenue, and re-alignment of Central | Pavement Widening | 2009-04-28 | 2009-04-28 | 2010-10-24 | 2010-06-10 | 14800000 | 1.000
8055 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | 0511097 | This project will reconstruction the four lanes of US 84/285 from Arroyo Seco to La Puebla and adds a two-way frontage road on both sides of the highway. | Pavement Widening | 2009-05-27 | 2009-05-27 | 2010-10-10 | 2010-10-27 | 13400652.8 | 2.900
8056 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | 0511098 | This project will reconstruct the four lanes of US 84/285 highway and adds medians from Dandy Burger South to the Dreamcatcher Theater. It will also add a new traffic signal at the Upper San Pedro in | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2010-06-15 | 2010-08-25 | 9108141.5 | 1.500
8057 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | 0649036 | This project will construct 2 new lanes on US64/87 from Des Moines to Capulin, converting this portion of US64/87 to a 4-lane facility. This is Phase Vi of a seven Phase project to widen US64/87 to 4 | New Construction | 2009-08-12 | 2009-08-12 | 2011-01-26 | 2011-09-22 | 25662731.53 | 16.000
8058 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | OTERO |  | 02 | 0821026 | Structural evaluation, preservation of sound timbers and replacement of decayed/missing timbers. | Transportation Enhancements | 2009-08-26 | 2009-08-26 | 2009-09-29 | 2009-09-29 | 249747
8059 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | 1271015 | Project consists of total reconstruction of a 14.4 mile segment of NM128 between Carlsbad and Jal on an offset new alignment. Project will consist of new roadway, shoulders, striping, permanent signin | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2010-05-19 | 2010-05-13 | 8076093.46 | 14.110
8060 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | LINCOLN |  | 02 | 3801206 | Bridge Replacement of the Priest Gulch Bridge on US380 at Milepost 96.3 in the Lincoln Historic District In Lincoln County approximately 60 miles west of Roswell | Pavement Improvement | 2010-03-16 | 2010-04-05 | 2010-10-08 | 2010-12-15 | 1175028.91
8061 | Underway | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL | ALBUQUERQUE | 03 | 4007003 | This project will complete Stage II of the Paseo Del Volcan corridor within the city of Rio Rancho. The project will consist of a new 2-lane facility including lighting, bridges, and various drainage | Pavement Widening | 2009-08-06 | 2009-08-10 | 2011-02-11 |  | 14000000
8062 | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | 4911011 | This project will provide two new traveling lanes to make the US 491 roadway a four lane facility. This is one segment of 9 segments to four lane US 491 from MP 15.7 to MP 84.7. | New Construction | 2009-06-30 | 2009-06-30 | 2010-05-04 |  | 21624989 | 8.000
8063 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | 4911031 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. Project will also provide intersection improvements for better t | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2010-03-04 | 2010-07-09 | 7904666.11 | 13.900
8064 | Completed | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL | ALBUQUERQUE | 03 | 5119001 | Reconstruct 2 lanes & add/improve sidewalks. Add center double left turn lanes & add deceleration lane for new school bus access. | Pavement Improvement | 2010-01-11 | 2010-01-25 | 2010-07-24 | 2010-06-25 | 1852573.23
8065 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | RIO ARRIBA |  | 03 | 5348002 | To construct road improvements to Industrial Park Road for its entire length of 1.1 miles in Espanola that includes added lanes, drainage improvements, pedestrian facilities, utilities, curb and gutte | Pavement Improvement | 2009-10-07 | 2009-10-07 | 2010-06-16 | 2010-07-07 | 1250000
8066 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | GRANT |  | 02 | 7517010 | This project will consist of improving (paving) the roadway on Diaz Avenue from Cul de Sac North to E. Street. In addition, it will include inspection and oversight. | Pavement Improvement | 2010-02-16 | 2010-03-01 | 2010-08-29 | 2010-09-24 | 390000
8067 | Underway | C220,C200,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES02107 | The work to be completed on this project will rehabilitate & reconstruct a highly deteriorated roadway to include; pavement, curb, gutter, sidewalks, storm drain systems, roadway lighting & traffic si | Pavement Improvement | 2011-03-16 | 2011-04-01 | 2012-02-20 |  | 1280406.61
8068 | Underway | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO | ALBUQUERQUE | 01 | ES03184 | "The City of Albuquerque proposes to expand its Advanced Transportation Management System with the installation of the communication infrastructure for the following corridors: 1) Alameda Blvd. from | Safety/Traffic Management | 2009-12-09 | 2010-01-11 | 2010-07-10 |  | 2651176
8069 | Underway | C250,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SOCORRO |  | 02 | ES03966 | Interstate 25 Bridge/Roadway Reconstruction; The purpose of the project is to replace bridge superstructure components and decks that are showing signs of wear. Currently, the existing bridges that | Pavement Improvement | 2011-01-13 | 2011-02-03 | 2011-10-26 |  | 898393.76
8070 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | ROOSEVELT |  | 02 | ES04049 | Enhancements such as; Bushes, Trees Sidewalks & ADA Ramps | Transportation Enhancements | 2010-04-05 | 2010-04-06 | 2010-07-06 | 2010-05-27 | 236588.86
8071 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | LUNA |  | 02 | ES11140 | Installation of a left turning lane | Pavement Widening | 2010-02-15 | 2010-04-05 | 2010-08-02 | 2010-06-10 | 143503.76
8072 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SIERRA |  | 02 | ES11150 | Landscaping, pedestrian facilities, & base course. | Transportation Enhancements | 2010-02-15 | 2010-02-15 | 2010-04-08 | 2010-04-15 | 87252.98
8073 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11160 | Installation of landscaping materials and erosion control measures | Transportation Enhancements | 2010-02-17 | 2010-03-10 | 2010-05-19 | 2010-07-08 | 178881.23
8074 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11170 | Construct eight bus shelters | Transportation Enhancements | 2010-02-09 | 2010-03-01 | 2010-04-14 | 2010-07-21 | 71000
8075 | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11180 | Project will consist of milling & removing 2.5" of old asphalt on driving & passing lanes and replace with 2.5" Hot Mix Asphalt, Open Graded Friction Course and fog seal shoulders. | Pavement Improvement | 2010-03-09 | 2010-03-18 | 2010-06-11 |  | 3462816.28
8076 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | HIDALGO |  | 02 | ES11200 | This project will include making roadway improvements to NM 494 from mile post 0 to mile post 1.7. Existing old pavement will be removed and replaced with new pavement. Sidewalks, curb and gutter, d | Pavement Improvement | 2010-02-04 | 2010-02-16 | 2010-04-27 | 2010-05-24 | 400000
8077 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11210 | This project will include roadway improvements by adding more pavement on top of the existing pavement on Calle del Norte from NM 28 to Tres Sendas. In addition, it will include inspection and oversi | Pavement Improvement | 2010-02-23 | 2010-03-15 | 2010-04-30 | 2010-06-09 | 500000
8078 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LUNA |  | 02 | ES11220 | Reconstruction to include pedestrian facilities | Pavement Improvement | 2009-12-22 | 2010-01-03 | 2010-11-08 | 2011-03-24 | 850000
8079 | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11230 | Sidewalks, curb & gutter, drainage structures, storm drains, bike lanes & pedestrian facilities. | Pavement Improvement | 2010-02-10 | 2010-03-15 | 2010-11-30 |  | 2000000
8080 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | GRANT |  | 02 | ES11240 | This project will include grinding down existing old pavement and replacing with new pavement on 12th Street from Gold Street to Mississippi Street. In addition, it will include inspection and oversi | Pavement Improvement | 2010-02-02 | 2010-02-03 | 2010-05-03 | 2010-08-26 | 503315.66
8081 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SOCORRO |  | 02 | ES11250 | This project will include inspection and oversight of pavement rehabilitation and maintenance, grinding down existing asphalt and replacing with new material on California Street from mile post 0 to m | Pavement Improvement | 2010-04-01 | 2010-04-01 | 2010-11-26 | 2010-09-21 | 704080
8082 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SIERRA |  | 02 | ES11260 | This project will include new pavement on the I-25 Business Loop (Old US 85) from Ashbaugh at mile post 0 to Morgan at mile post 3.9. Construction will include management and pedestrian facilities. | Pavement Improvement | 2010-02-22 | 2010-03-01 | 2010-07-28 | 2010-06-30 | 604305
8083 | Completed | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA | EL PASO, TX-NM | 02 | ES11270 | Project will improve the roadway surface on NM 213 which is a heavily traveled route between El Paso, Chaparral, White Sands Missile Range, and Jct. NM 404 to Interstate 10 and Anthony, NM | Pavement Improvement | 2010-02-25 | 2010-03-10 | 2010-04-21 | 2010-03-18 | 940288.3
8084 | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | HIDALGO |  | 02 | ES11400 | This seven mile maintenance project includes removing 2 inches of the existing pavement and replacing it with new pavement. The purpose of this project is to improve the quality of the roadway surface | Pavement Improvement | 2010-04-06 | 2010-06-01 | 2010-08-03 |  | 1851727.18
8085 | Underway | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA | EL PASO, TX-NM | 02 | ES11420 | Work on the project will include placing a hot mix asphalt overlay on an existing roadway with tapered edges to create a smooth transition surface from the roadway onto the shoulders. It also include | Pavement Improvement | 2011-01-13 | 2011-02-03 | 2011-03-31 |  | 157040.59
8086 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21070 | This project will include downtown beautification consisting of new pavement, lighting, crosswalks, sidewalks, curb and gutter and landscaping on NM 176 from mile post 34.9 to milepost 35.4 and on NM | Transportation Enhancements | 2010-02-05 | 2010-02-08 | 2010-06-27 | 2010-08-30 | 249747
8087 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | OTERO |  | 02 | ES21190 | This project will include the removal of an old bridge and construction of a new bridge to replace the old bridge on 9th Street and Washington Street. | Pavement Improvement | 2010-01-13 | 2010-01-19 | 2010-03-10 | 2010-03-31 | 139291.52
8088 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CHAVES |  | 02 | ES21200 | This project will include grinding down old pavement and replacing with new pavement along an existing paved road. The project is located on West Brasher Road from the entrance of the City’s municipal | Pavement Improvement | 2010-02-19 | 2010-03-15 | 2010-06-04 | 2010-07-01 | 831489
8089 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21210 | This project includes new pavement on Ninth Street from Avenue D to Polk Avenue. | Pavement Improvement | 2010-01-18 | 2010-01-19 | 2010-08-19 | 2010-04-22 | 559365.66
8090 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21220 | Mill, check sub-base, relay and add 4 inches of asphalt. | Pavement Improvement | 2010-03-16 | 2010-03-29 | 2010-06-27 | 2010-08-19 | 789914.56
8091 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21230 | 10 feet wide concrete multi-use trail with landscape, pedestrian lighting and americans with disabilites act intersection improvements | Transportation Enhancements | 2010-02-08 | 2010-02-15 | 2010-03-26 | 2010-03-31 | 249747
8092 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LINCOLN |  | 02 | ES21240 | This project will consist of new pavement on Paradise Canyon from Suddeth Drive to Country Club Drive. | Pavement Improvement | 2010-04-28 | 2010-05-03 | 2010-06-02 | 2010-05-12 | 295523.78
8093 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CHAVES |  | 02 | ES21250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-03-22 | 2010-03-29 | 2010-05-28 | 2010-04-28 | 813504.77
8094 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | EDDY |  | 02 | ES21260 | This project will include new pavement on Greene Street from Canal to Moore Drive. | Pavement Improvement | 2010-02-18 | 2010-03-03 | 2010-07-21 | 2010-07-15 | 831489
8095 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | OTERO |  | 02 | ES21270 | This project will include the construction of accessible sidewalks and ramps, and driveways for people with disabilities on 1st Street from White Sands to Florida and 10th Street from Cuba to College. | Transportation Enhancements | 2010-02-02 | 2010-05-09 | 2010-02-08 | 2010-06-18 | 196509.23
8096 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 03 | ES21280 | Bridge replacement on Hull Street spanning over Burlington Northern Santa Fe Railroad | Bridge Replacement | 2009-11-24 | 2010-01-04 | 2010-10-31 | 2010-11-19 | 831489 | 0.300
8097 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 03 | ES21300 | Project consists of landscaping at the intersection of US60/70/84 intersection at the New Mexico/Texas State Line in the Town of Texico in Curry County. Project will include trees, shrubs, flowers, Am | Transportation Enhancements | 2010-04-20 | 2010-05-05 | 2010-07-30 | 2010-07-27 | 293709.22 | 1.000
8098 | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 02 | ES21310 | Project will rehabilitate a section of NM 209 between Broadview and Grady in Curry County. Project consists of milling full width the existing roadway and a Hot mix asphalt overlay. | Pavement Improvement | 2010-04-28 | 2010-05-20 | 2010-08-12 | 2010-11-22 | 1684912.45 | 6.000
8099 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21320 | Pavement reconstruction including milling excavation, subgrade base course, asphalt treated base, hot-mix asphalt and minor concrete. | Pavement Improvement | 2010-01-15 | 2010-01-25 | 2010-07-24 | 2010-10-29 | 831489 | 1.000
8100 | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | ROOSEVELT |  | 03 | ES21330 | Project consists of rehabilitating a four-mile section of NM 88 east of the City of Portales in Roosevelt County. The typical section will be process, placed and compacted and then overlayed with a 2. | Pavement Improvement | 2010-04-01 | 2010-04-23 | 2010-09-10 | 2010-06-28 | 1504718.88 | 5.400
8101 | Underway | C220,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES21350 | This project will consist of improving the road pavement and drainage on East Berino Road from NM 478 to Stern Drive. It will, also, include curb and gutter, sidewalks, storm drainage installation an | Pavement Improvement | 2010-04-26 | 2010-05-10 | 2011-02-03 |  | 2168207
8102 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 03 | ES21360 | Project will consist of full lane width milling and removal of the existing pavement and replacing full width Hot Mix Asphalt overlay south of Portales in Roosevelt County. | Pavement Improvement | 2010-02-05 | 2010-02-25 | 2010-06-18 | 2010-07-14 | 4242583.9
8103 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 02 | ES21420 | The project will include grinding the existing pavement, putting it back in place and compacting it. Then the existing roadway will receive a new asphalt pavement overlay. | Pavement Improvement | 2010-03-15 | 2010-04-04 | 2010-06-25 | 2010-07-15 | 2354145.7
8104 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | EDDY |  | 02 | ES21560 | The project consists of approximately one (1) mile of Project Pavement Reconstruction of deteriorated roadway on 26th Street in Artesia which begins at junction of NM 82 and 26th Street and proceeds n | Pavement Improvement | 2011-01-17 | 2011-01-17 | 2011-07-16 | 2011-05-28 | 831488.51
8105 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 02 | ES31110 | The Village of Bosque Farms proposes to enhance 21 side street accesses onto Bosque Loop Road by providing road improvements by re-aligning, resurfacing with Hot mix Asphalt , and constructing a secti | Pavement Improvement | 2010-04-28 | 2010-05-03 | 2010-06-18 | 2010-06-03 | 63000
8106 | Underway | C220,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 01 | ES31120 | This project is a joint effort between the City of Belen and The Mid Region Council of Governments. The project will provide Pedestrian Access to the Rail Runner Station by constructing an Americans | Transportation Enhancements | 2010-06-16 | 2010-06-21 | 2011-01-14 |  | 2410012.2 | 14.000
8107 | Underway | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 03 | ES31130 | This project will improve safety for motorists by resurfacing with Hot Mix Asphalt, widening travel lanes, providing acceleration/deceleration lanes, providing lighting and improving access to busine | Pavement Improvement | 2010-07-08 | 2010-07-23 | 2011-03-27 |  | 2000000
8108 | Underway | C250,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 03 | ES31140 | This project will improve safety for motorists within the limits of Cochiti Pueblo by resurfacing with Hot Mix Asphalt, providing roadside safety enhancements, constructing an offset multi-use trail w | Pavement Improvement | 2010-07-08 | 2010-07-23 | 2010-09-03 |  | 1500000
8109 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 03 | ES31150 | This project will provide a new signalized/lighted intersection for the Pueblo of Isleta’s Service Center. The Service Center is the Pueblo’s main housing of emergency personnel and other support staf | Pavement Improvement | 2010-07-15 | 2010-08-06 | 2011-01-23 | 2010-12-10 | 878722
8110 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 01 | ES31160 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-04-06 | 2010-04-05 | 2010-06-04 | 2010-06-16 | 4915479.95
8111 | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 02 | ES31200 | This project will mill a portion of the surfacing, and overlay with new pavement, for a distance of 4 miles. New signing and striping will be installed. NM 6 is a rural two lane highway | Pavement Improvement | 2010-12-14 | 2010-12-31 | 2011-02-14 |  | 1007628.49
8112 | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 03 | ES31210 | This project will mill a portion of the surfacing, and overlay with new pavement, for a distance of 5 miles. New signing and striping will be installed. NM 16 is a 2 lane rural highway. | Pavement Improvement | 2010-12-14 | 2010-12-31 | 2011-02-14 |  | 1161692.04
8113 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | ES41170 | The project will provide parking capacity, land and street scaping that will promote the heritage and tourism benefits along US 64 for approximately 1/2 mile. | Transportation Enhancements | 2010-06-29 | 2010-06-29 | 2010-08-27 | 2010-08-04 | 125000
8114 | Underway | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN MIGUEL |  | 03 | ES41180 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Transportation Enhancements | 2010-10-19 | 2010-10-25 | 2011-05-31 |  | 937015
8115 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | ES41190 | The project will upgrade signing, striping, curb and gutter, sidewalk, drainage structures, and pavement that will enhance safety and improve existing pavement. | Pavement Improvement | 2010-06-02 | 2010-06-21 | 2010-09-21 | 2010-10-05 | 762000
8116 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | GUADALUPE |  | 01 | ES41200 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 2010-09-29 | 2010-10-11 | 2011-11-09 | 2011-02-18 | 312355.26
8117 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN MIGUEL |  | 03 | ES41210 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-08-13 | 2010-08-13 | 1944135.31
8118 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | ES41220 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 2010-07-07 | 2010-07-22 | 2010-09-22 | 2010-09-22 | 763077.01
8119 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | ES41230 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 2010-09-20 | 2010-09-21 | 2010-11-21 | 2010-10-29 | 600000
8120 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | QUAY |  | 03 | ES41240 | The project will upgrade signing, striping, curb and gutter, sidewalk, drainage structures, and pavement that will enhance safety and improve existing pavement. | Pavement Improvement | 2010-03-08 | 2010-03-08 | 2010-08-23 | 2010-10-03 | 1785000
8121 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | UNION |  | 03 | ES41250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-02-04 | 2010-02-25 | 2010-05-21 | 2010-09-25 | 3387428.67
8122 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | GUADALUPE |  | 01 | ES41360 | This project will crack seal 28.5 miles of Interstate 40 in Quay County, 30.7 miles of US 54 in Quay County, and 5.6 miles of US 84 in Guadalupe County | Pavement Improvement | 2010-03-15 | 2010-04-05 | 2010-06-25 | 2010-06-08 | 1211432.17
8123 | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | GUADALUPE |  | 01 | ES41370 | Project will include the rehabilitation with spot reconstruction of I-40 from MP 248.3 to MP 255.3. Work will include: milling of existing roadway full-width; Full depth and partial depth reconstruct | Pavement Improvement | 2010-11-08 | 2010-11-24 | 2010-03-18 |  | 2231007
8124 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LOS ALAMOS |  | 03 | ES51140 | Rehabilitate & reconstruct highly deteriorated roadway to include; pavement, curb, gutter, sidewalks, storm drain systems & roadway lighting. | Pavement Widening | 2009-04-29 | 2009-05-11 | 2010-03-01 | 2009-11-06 | 1901033.83
8125 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | ES51260 | The New Mexico Department of Transportation will resurface the top three inches of existing asphalt in the southbound driving lanes of US 491 with 3” of new Hot Mix Asphalt. This will improve driving | Pavement Improvement | 2010-02-04 | 2010-02-25 | 2010-10-01 | 2010-10-18 | 3815204.58
8126 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | TORRANCE |  | 01 | ES51270 | Repair cracks in pavement and repave roadway | Pavement Improvement | 2010-03-02 | 2010-03-25 | 2010-10-01 | 2010-10-01 | 1720849.16
8127 | Underway | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | CATRON |  | 02 | ES61150 | This project will beautify the downtown area of the Village of Reserve and will also install a needed drainage system. | Transportation Enhancements | 2010-07-14 | 2010-07-26 | 2010-12-22 |  | 1033609
8128 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 01 | ES61160 | This project will replace the existing old bridge with a new prefabricated bridge. | Bridge Improvement | 2010-03-11 | 2010-03-11 | 2010-05-31 | 2010-05-28 | 166645.61
8129 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 03 | ES61170 | This project will replace the existing old bridge with a new prefabricated bridge. | Bridge Improvement | 2010-03-11 | 2010-03-11 | 2010-05-31 | 2010-07-02 | 180288.37
8130 | Underway | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61180 | This project will widen an existing bridge on a Zuni Reservation route near the city of Zuni, New Mexico. | Bridge Improvement | 2010-07-12 | 2010-07-12 | 2011-01-08 |  | 736582
8131 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61190 | This project will replace the existing old bridge with a new concrete bridge. | Pavement Widening | 2010-03-19 | 2010-03-29 | 2010-11-29 | 2010-10-18 | 1636194.71
8132 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CIBOLA |  | 02 | ES61200 | This project will replace the existing old bridge with a new concrete bridge. | Bridge Replacement | 2009-12-28 | 2010-01-04 | 2010-05-04 | 2010-09-30 | 780516.18
8133 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 02 | ES61250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-01-13 | 2010-02-03 | 2010-04-04 | 2010-07-17 | 3967200.35
8134 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61260 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-03-16 | 2010-04-05 | 2010-06-25 | 2010-08-18 | 1811053.07
8135 | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | CIBOLA |  | 02 | ES61320 | This project will remove the existing asphalt paved section and replace it with a new asphalt overlay. | New Construction | 2010-06-30 | 2010-07-19 | 2010-10-26 | 2010-09-01 | 1200000
8136 | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61330 | This project will replace the existing old bridge with a new concrete bridge. | Bridge Replacement | 2010-04-06 | 2010-04-23 | 2010-09-10 | 2010-11-04 | 1717198.73
8137 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61340 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. This project is located in on NM 264 in McKinley County from mi | Pavement Improvement | 2010-12-02 | 2010-12-02 | 2011-01-18 | 2011-12-14 | 1600000
8138 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 02 | ES61350 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. This project is located in on NM 118 in McKinley County from mi | Pavement Improvement | 2010-12-22 | 2010-12-31 | 2011-02-25 | 2011-10-24 | 1594137.5
8139 | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 03 | ESA3310 | Construction of an asphalt multiuse asphalt trail on the East frontage of NM 314 to connect the Rail Runner Station with NM 6. The project also involves the construction of a Bike/Pedestrian RR crossi | Transportation Enhancements | 2010-09-19 | 2010-10-04 | 2011-03-04 |  | 1092715
8140 | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 03 | ESA3312 | Intersection Pedestrian Improvements to Court house Road, including the construction of new ramps, new pedestrian push button stations, enhanced crosswalk markings. It also includes a concrete walkwa | Transportation Enhancements | 2010-09-20 | 2010-09-27 | 2010-03-25 |  | 722345.64
8141 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 01 | ESA3320 | The purpose of the project will consist of the installation of lighting between the Southern Boulevard intersection and US 550 within the City of Rio Rancho and the town of Bernalillo. The lighting w | Transportation Enhancements | 2010-03-15 | 2010-03-25 | 2010-06-18 | 2010-09-08 | 846422.86
8142 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 01 | ESA3330 | The project will consist of the repaving of the Multi use trail from Central to Montgomery. The project will also consist of various improvements from Central to Tramway Terrace which include the upgr | Transportation Enhancements | 2010-04-20 | 2010-05-05 | 2010-08-19 | 2010-12-23 | 770784.35
8143 | Underway | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 01 | ESA3331 | This project will reconstruct and improve sections of an existing Bike/Pedestrian Trail within the City of Albuquerque. The safety of the trail will be improved by widening the rail to 12’, building r | Transportation Enhancements | 2011-01-18 | 2011-02-03 | 2011-07-17 |  | 482984.43
8144 | Completed | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO | ALBUQUERQUE | 01 | ESA3550 | This project will reconstruct the existing Bike/Pedestrian Trail along the Rio Grande within the City of Albuquerque. The improvements involve the removal and replacement of the existing pavement, on | Transportation Enhancements | 2011-01-06 | 2011-01-10 | 2011-03-25 | 2011-07-06 | 1240264.24
8145 | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | ESF1050 | The City of Aztec is developing an East Arterial to alleviate heavy truck traffic through it's Main Street (US 550). The arterial will intersect at the south end of town and will traverse east and the | Pavement Improvement | 2010-04-05 | 2010-04-05 | 2010-10-02 |  | 1700000
8146 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | ESF1070 | This project is a widening and intersection improvements for Wildflower Parkway from Browning Parkway to Yarrow Street in Farmington that includes bike paths, new sidewalks and turning lanes. | Transportation Enhancements | 2010-03-25 | 2010-04-12 | 2010-09-09 | 2010-11-30 | 1347265.7
8147 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | ESF1080 | For reconstruction of West Maple Street in Bloomfield to include removal of existing pavement, adding curb and gutter, lighting, sidewalk, new asphalt, and removal and replacement of utilities from US | Pavement Improvement | 2010-04-28 | 2010-05-10 | 2010-10-16 | 2010-12-15 | 900000
8148 | Underway | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL | ALBUQUERQUE | 01 | ESL3311 | This project will resurface and reconstruct the multi-use trail along Camino Don Tomas Road in the Town of Bernalillo. Also it will relocate and provide a water system to include irrigation lines to t | Pavement Improvement | 2012-01-23 | 2012-01-30 | 2012-04-30 |  | 1062005.77
8149 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | ESS1010 | This project will provide landscaping of all medians on Rodeo Road from Galisteo Street to Camino Carlos Rey. | Transportation Enhancements | 2009-09-22 | 2009-09-22 | 2009-11-30 | 2010-06-11 | 132313.01
8150 | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | ESS1020 | This project will pave a small portion of the Santa Fe Rail Trail in Santa Fe County from Interstate Highway 25 southerly to Rabbit Road. | Transportation Enhancements | 2010-04-07 | 2010-04-07 | 2010-08-13 | 2010-05-04 | 67159.58
8151 | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | ESS1030 | This project will involve cold milling the existing pavement on Airport Road from Cerrillos Road to Calle Debra, inlaying a new pavement, sidewalk and Americans with Disabilities Act ramp improvements | Pavement Improvement | 2010-05-21 | 2010-06-01 | 2010-10-30 |  | 2222022.33
8152 | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | F100030 | A complete bridge replacement for Bridge #8116 located on San Juan County Road 2900 at mile marker 6.20 situated between the City of Aztec and the community of Cedar Hill. | Bridge Replacement | 2010-04-05 | 2010-04-05 | 2010-08-05 | 2010-12-15 | 903955.02
8153 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0016263 | Completely renovating 3.5 miles of New York Route 112 in Brookhaven, Suffolk County to improve the safety for the approximately 20,000 motorists, pedestrians and bicyclists who use the roadway daily. | Pavement Improvement | 2009-08-06 | 2009-08-06 | 2011-11-10 | 2011-12-23 | 40151314 | 3.000
8154 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0757523 | A project to construct the ferry terminal bulkhead and make site improvements at the Glen Cove Ferry Terminal in the City of Glen Cove, Town of North Hempstead, Nassau County. | Other | 2010-04-26 | 2010-04-26 | 2011-05-02 |  | 10743372 | 0.000
8155 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 02 | 0758463 | Provide new bike lanes and improved pedestrian facilities, including new sidewalks and crosswalks, on Prospect Avenue between Brush Hollow Road and Cantiague Rock Road in New Cassel, in the Town of No | Safety/Traffic Management | 2009-11-17 | 2009-11-17 | 2011-12-23 | 2011-12-23 | 5000000 | 0.000
8156 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 02 | 0758583 | Reconstruct Walt Whitman Road in the Town of Huntington | Pavement Improvement | 2010-01-01 | 2010-01-01 | 2010-11-04 |  | 5409198 | 0.000
8157 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759353 | Further expand Nassau County central computerized traffic signal system. | Safety/Traffic Management | 2011-03-21 | 2011-03-21 | 2012-03-01 |  | 2609826 | 0.000
8158 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759373 | A project to clean, paint, and thereby preserve the integrity of four bridges accessing Hempstead Lake Park in the Village of Rockville Centre, Nassau County. | Bridge Improvement | 2010-03-31 | 2010-03-31 | 2011-04-22 | 2011-04-22 | 3068016 | 0.000
8159 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 03 | 0759383 | A project to provide safety, pavement and drainage improvements on Cedar Swamp Road in Glen Cove, Town of North Hempstead, Nassau County. | Pavement Improvement | 2010-03-26 | 2010-03-26 | 2010-11-01 |  | 1803415 | 0.000
8160 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759393 | Resurface select local roads in Nassau County. The existing deteriorated pavement surface will be removed and replaced with new asphalt and pavement markings. | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-06-08 | 2010-04-19 | 3247150 | 0.000
8161 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759403 | Resurface select local roads in Nassau County. The existing deteriorated pavement surface will be removed and replaced with new asphalt and pavement markings. | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-06-08 | 2010-04-19 | 3156305 | 0.000
8162 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759413 | A project to construct a seven-mile shared-use bike path in Mitchell Park, Nassau County. The new, shared-use path will provide a non-motorized transportation facility that connects multiple recreat | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-12-02 | 2010-12-02 | 2234972 | 0.000
8163 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 02 | 0759423 | Recondition, preserve asphalt pavement and improve drainage on Commack Road, County Road 4, between Nicolls Road and Polo Street in the towns of Babylon and Huntington, Suffolk County. | Pavement Improvement | 2009-09-07 | 2009-09-07 | 2011-04-20 | 2010-12-15 | 3497737 | 0.000
8164 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 02 | 0759433 | Rehabilitate the roadway pavement and make needed drainage improvements on County Route 67 between the Long Island Expressway (LIE/I495) and County Route 17 in the Town of Islip, Suffolk County. | Pavement Improvement | 2009-09-24 | 2009-09-24 | 2010-08-23 |  | 3839003 | 3.650
8165 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759443 | A project to remove the top layer of worn, distressed pavement on Long Island Expressway service roads between Exit 59 and 63 in the towns of Islip and Brookhaven, Suffolk County, and replace it w | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2011-11-18 | 2011-11-18 | 6473513 | 6.800
8166 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759453 | A project to remove the top layer of worn, distressed pavement on Long Island Expressway service roads between Exit 54 and 59 in the towns of Islip and Brookhaven, Suffolk County, and replace it w | Pavement Improvement | 2009-09-22 | 2009-09-22 | 2010-10-13 | 2010-10-13 | 7583701 | 7.500
8167 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759483 | A pavement marking project in Nassau County. | Safety/Traffic Management | 2011-05-25 | 2011-05-25 | 2012-03-01 |  | 1075800 | 0.000
8168 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 01 | 0759543 | Implementing an alternative transportation path for bicycle and pedestrian use to connect the areas of activity centers throughout the town of Riverhead. | Transportation Enhancements | 2009-09-15 |  | 2013-04-25 |  | 3158000 | 0.000
8169 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759553 | A pavement marking project in Nassau County on Atlantic Avenue and Merrick Road. | Safety/Traffic Management | 2011-05-25 | 2011-05-25 | 2012-03-01 |  | 2066680 | 0.000
8170 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759563 | A pavement marking project in Nassau County on Old Country Road in Mineola and Garden City and Glen Cove Road, Main Street, and Forest Avenue in Oyster Bay. | Safety/Traffic Management | 2011-05-25 | 2011-05-25 | 2012-03-01 |  | 2142800 | 0.000
8171 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808183 | Improve roadway storm water run off, clean and repair or replace drainage basins to locations on NY25A, Nassau County, NY RT102, Nassau County, NY RT25A, Suffolk County, & Robert Moses Causeway, Suffo | Other | 2009-08-12 | 2009-08-12 | 2010-05-24 | 2010-05-17 | 743417 | 0.510
8172 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808193 | Resurface approximately nine miles of State roadways in Nassau and Suffolk counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement marki | Pavement Improvement | 2009-06-26 | 2009-06-26 | 2010-10-29 | 2010-12-03 | 9192216 | 7.710
8173 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808393 | Much-needed concrete pavement repairs to sections of distressed, aging roadway systems throughout Nassau and Suffolk counties to improve pavement smoothness, reduce accidents and maintain pavement int | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-11-16 | 2009-12-22 | 2014395 | 23.590
8174 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0808503 | Clean the steel of 10 bridges in Babylon, Brookhaven and Islip in Suffolk County to eliminate corrosion and rust and to paint the structures. These preventative-maintenance repairs will maintain the b | Bridge Improvement | 2009-06-15 | 2009-06-15 | 2010-09-30 | 2010-09-30 | 5309630 | 0.000
8175 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0808541 | Designing pavement repairs of State highways in Nassau and Suffolk counties, in the towns of Babylon, Islip, Hempstead, Riverhead, Brookhaven and North Hempstead. | Other | 2010-03-05 | 2010-03-05 | 2011-12-16 |  | 205380 | 15.110
8176 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808543 | Designing pavement repairs of State highways in Nassau and Suffolk counties, in the towns of Babylon, Islip, Hempstead, Riverhead, Brookhaven and North Hempstead. | Pavement Improvement | 2010-03-05 | 2010-03-05 | 2011-12-16 | 2012-02-09 | 20043945 | 15.110
8177 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 0808551 | Upgrade approximately 900 traffic signals in Nassau and Suffolk counties by replacing existing incandescent lights with more energy efficient Light Emitting Diode (LED) bulbs to reduce energy use and | Safety/Traffic Management | 2009-08-20 | 2009-08-20 | 2011-04-25 |  | 100000 | 0.000
8178 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 0808553 | Upgrade approximately 900 traffic signals in Nassau and Suffolk counties by replacing existing incandescent lights with more energy efficient Light Emitting Diode (LED) bulbs to reduce energy use and | Safety/Traffic Management | 2009-08-20 | 2009-08-20 | 2011-04-25 | 2011-10-18 | 4951041 | 0.000
8179 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808561 | Upgrade the outdated, 22-year-old original technology that operates 53 out of 190 motorist information signs operated by NYSDOT INFORM's transportation management center. The project will increase the | Other | 2010-03-30 | 2010-03-30 | 2011-03-31 | 2011-08-26 | 5366 | 0.000
8180 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 0808563 | Upgrade the outdated, 22-year-old original technology that operates 53 out of 190 motorist information signs operated by NYSDOT INFORM's transportation management center. The project will increase the | Safety/Traffic Management | 2010-03-30 | 2010-03-30 | 2011-08-26 | 2011-08-26 | 2611165 | 0.000
8181 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0808621 | Designing pavement repairs of State highways in Nassau and Suffolk counties, targeting sections of the NY 231 and the Sagtikos Parkway. | Other | 2010-03-18 | 2010-03-18 | 2011-01-21 |  | 30423 | 19.500
8182 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0808643 | Preserve the Stony Brook Mill Pond as a fragile aquatic resource and better protect motorists from roadway flooding conditions on NY Route 25A (North Country Road) in Stony Brook, Town of Brookhaven, | Other | 2009-10-01 | 2009-10-01 | 2010-06-30 | 2010-06-30 | 922963 | 1.600
8183 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 01 | 0935613 | Calverton Enterprise Park Rail Spur in the Town of Riverhead. Rehabilitate Freight rail access to Calverton Industrial Park from the LIRR Main line. The rail spur is 2.3 miles from the LIRR main line | Other | 2010-01-27 | 2010-01-27 | 2012-02-17 |  | 4800000 | 0.000
8184 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1753373 | Relocate the Maxwell Road intersection with Albany Shaker Road in the town of Colonie, Albany County 800 feet to the east, away from the existing intersection. The existing intersection will remain, b | Pavement Widening | 2009-09-23 | 2009-09-23 | 2010-11-30 | 2010-10-11 | 5158409 | 0.000
8185 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 1754523 | A project to provide pedestrian and bicycle access to the Troy-Menands Bridge. | Transportation Enhancements | 2010-04-09 | 2010-04-09 | 2011-03-14 | 2010-10-27 | 1107534 | 0.010
8186 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ESSEX |  | 22 | 1755123 | Replace the bridge carrying Haselton Road over West Branch Ausable River, Town of Wilmington. | Bridge Replacement | 2009-11-16 | 2009-11-16 | 2010-09-25 | 2010-11-15 | 1510000 | 0.000
8187 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | WASHINGTON |  | 20 | 1755153 | Replace the bridge carrying Clinton Street, Saunders Street and Division Street over the Delaware and Hudson Railroad in the Village of Whitehall in Washington County. This rail line serves the area a | Bridge Replacement | 2009-09-01 | 2009-09-01 | 2011-11-03 | 2011-06-30 | 5167794 | 0.000
8188 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 22 | 1755213 | Replace the County Route 3/Warrensburg Road Bridge over Stony Creek in the Town of Stony Creek, Warren County. | Bridge Replacement | 2009-06-05 | 2009-06-05 | 2010-04-30 | 2010-12-07 | 1458010 | 0.010
8189 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1755933 | A project to construct Spring Run Trail, a multi-use path, from Congress Park to I-87 in the City of Saratoga Springs. | Transportation Enhancements | 2010-03-05 | 2010-03-05 | 2010-06-30 | 2010-11-15 | 2070003 | 0.000
8190 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756353 | Replace the bridge over the Fifth Branch of the Mohawk River in the City of Cohoes, Albany County. A new five-span steel bridge will be constructed on existing bridge alignment, including reconstructi | Bridge Replacement | 2009-07-28 | 2009-07-28 | 2010-11-04 | 2010-12-31 | 7883000 | 0.090
8191 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756593 | Reconstruction of 19th Street in the City of Watervliet in Albany County. 19th Street carries New York State Touring Route 2 through the City between the Congress Street Bridge and the City Line and s | Pavement Improvement | 2009-07-29 | 2009-07-29 | 2010-11-30 | 2010-11-24 | 6639194 | 1.170
8192 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756613 | Reconstruct Delaware Avenue for the 1.6 miles between Madison Avenue and the bridge over the New York State Thruway linking Albany and Delmar, Albany County. The project will include curb, drainage an | Pavement Improvement | 2009-04-09 | 2009-04-09 | 2010-10-31 | 2011-04-15 | 15525612 | 1.630
8193 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RENSSELAER | ALBANY-SCHENECTADY-TROY | 21 | 1756623 | Reconstruction of NY Route 2 from 5th Avenue to 11th Street in the City of Troy | Pavement Widening | 2009-09-28 | 2009-09-28 | 2010-12-22 | 2011-06-10 | 6982070 | 0.000
8194 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 22 | 1757073 | A bridge replacement project of County Road 43 (Geyser Road) over the D and H Railroad. | Bridge Improvement | 2010-02-12 | 2010-02-12 | 2010-11-01 | 2010-10-29 | 1766000 | 0.000
8195 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RENSSELAER |  | 22 | 1757083 | Replace the bridge carrying Caretaker Road over the Walloomsac River in the town of Hoosick, Rensselaer County. This bridge, built in 1900, accesses a historic site, the Bennington Battlefield. Withou | Bridge Replacement | 2009-08-11 | 2009-08-11 | 2009-12-31 | 2010-05-21 | 1178732 | 0.000
8196 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GREENE |  | 20 | 1757123 | Replacement of the bridge carrying New Baltimore Road over Hannacrois Creek in the Town of New Baltimore in Greene County. The existing box-beam bridge, built in 1972 and owned by Greene County, conti | Bridge Replacement | 2009-07-29 | 2009-07-29 | 2009-12-31 | 2009-12-03 | 1210932 | 0.010
8197 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 22 | 1757143 | Reconstruct a portion of Church Street -- State Touring Route 9N -- in the city of Saratoga Springs, Saratoga County. The project will improve Church Street between West Avenue and North Van Rensselae | Pavement Improvement | 2009-09-11 | 2009-09-11 | 2010-11-19 | 2010-11-19 | 2705782 | 0.000
8198 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 20 | 1757173 | Replace the Grist Mill Road Bridge over Stony Creek in the Town of Stony Creek, Warren County. | Bridge Replacement | 2009-06-05 | 2009-06-05 | 2010-04-30 | 2010-04-21 | 987827 | 0.010
8199 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | ESSEX |  | 20 | 1758333 | Rehabilitation of Essex County Route 84, Blue Ridge Road, between the Adirondack Northway and State Route 28N in the towns of Newcomb, Minerva and North Hudson in Essex County. This county road, measu | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2009-08-01 | 2009-10-15 | 3372180 | 17.360
8200 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 20 | 1758613 | The second phase of the reconstruction of Bay Street in the City of Glens Falls in Warren County. This deteriorating city street is a major north-south route linking the City and the Town of Queensbur | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2010-06-30 | 2010-07-23 | 2509672 | 1.030
8201 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 22 | 1758623 | A project to complete the Zim Smith Trail in the towns of Ballston and Malta in Saratoga County. The project will construct 2 miles of pedestrian trail and connect two existing trails between Oak St | Transportation Enhancements | 2009-11-24 | 2009-11-24 | 2010-06-30 | 2010-11-21 | 660896 | 0.000
8202 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 1758633 | Convert a historic 1921 Canal Motorship into a floating museum with exhibits that will travel to ports across New York State. | Transportation Enhancements | 2011-09-13 | 2011-09-13 | 2012-08-10 |  | 3139000 | 0.000
8203 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | ESSEX |  | 22 | 1758643 | Ticonderoga Train Trestle Conversion and Historic Trail Conversion in the Town of Ticonderoga. | Transportation Enhancements | 2011-04-27 | 2011-04-27 | 2014-05-14 |  | 325000 | 0.000
8204 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1758673 | Washington Avenue Pavement Resurfacing, Washington Avenue, Fuller Road to I-90, Jermain Street to North Main Avenue, Ontario Streen to Lark Street. | Pavement Improvement | 2009-09-25 | 2009-09-25 | 2009-11-30 | 2009-11-30 | 2313725 | 0.000
8205 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1758683 | Resurfacing and American's With Disabilities Act Compliance on County Road 52, Elm Avenue, Delmar Bypass and Feura Bush Road in the Town Of Bethlehem. | Pavement Improvement | 2009-11-05 | 2009-11-05 | 2009-11-30 | 2009-11-19 | 202842 | 0.000
8206 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RENSSELAER | ALBANY-SCHENECTADY-TROY | 21 | 1758693 | Pavement Resurfacing of County Route 145, Oakwood Avenue. | Pavement Improvement | 2009-09-25 | 2009-09-25 | 2009-11-30 | 2010-06-30 | 847655 | 1.320
8207 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758703 | River Road / Providence Avenue Resurfacing, River Road/Rosendale Road to General Electric Circle, General Electric Circle to Route 146, Route 146 to Schenectady City Line, Town of Niskayuna. | Pavement Improvement | 2010-05-18 | 2010-05-18 | 2009-11-30 | 2010-11-11 | 1035147 | 0.000
8208 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758713 | Resurfacing of Rosendale Road/River Road in the Town of Niskayuna. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2009-11-30 | 2010-07-16 | 346571 | 0.000
8209 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758723 | Pavement resurfacing of Van Vanken Avenue, Nott Street to Maxon Road in the City of Schenectady. | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-11-30 | 2010-09-23 | 1051513 | 0.000
8210 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1758733 | Resurface Saratoga County Route 108, Dunning Street, between State Route 9 and State Route 9P in the town of Malta, Saratoga County. The project will remove and replace deteriorating pavement and cons | Pavement Improvement | 2009-10-07 | 2009-10-07 | 2009-11-30 | 2009-11-05 | 312472 | 0.000
8211 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GREENE |  | 20 | 1758743 | Resurface Greene County Route 28, Schoharie Turnpike, between U.S. Route 9W in the town of Athens and Second Street in the village of Athens. The project will remove and replace deteriorating pavement | Pavement Improvement | 2009-10-02 | 2009-10-02 | 2009-12-02 | 2009-11-20 | 291576 | 0.000
8212 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 20 | 1758753 | Road Resurfacing and Americans With Disabilities Act Compliance on County Route 34, Glenwood Avenue, Glen Street to Bay Road in the Town of Queensbury. | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2010-04-30 | 2010-07-03 | 159000 | 0.000
8213 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 20 | 1758763 | Resurfacing And Americans With Disabilities Act Compliance on County Route 28, Corinth Road, Indiana Avenue to Vandusen Drive in the Town of Queensbury. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2010-04-30 | 2010-06-11 | 206500 | 0.000
8214 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WASHINGTON | GLENS FALLS | 20 | 1758773 | Resurfacing project along county Route 42 (Basin Road), State Rt 196 to State R7 197. Resurfacing and Americans with disabilities Act. Town of Kingsbury and Fort Edward. | Pavement Improvement | 2010-05-19 | 2010-05-19 | 2010-09-20 | 2010-06-11 | 444375 | 0.000
8215 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WASHINGTON | GLENS FALLS | 20 | 1758783 | Sumpter and Allen Streets Resurfacing. Village of Hudson Falls. | Pavement Improvement | 2010-05-19 | 2010-05-19 | 2010-09-20 | 2010-06-18 | 87518 | 0.000
8216 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 1807993 | Pavement improvements on Route 5 in Albany, Schenectady and the towns of Colonie, Albany County, and Niskayuna, Schenectady County. Work also will include the installation at 159 intersections of ramp | Pavement Improvement | 2009-09-15 | 2009-09-15 | 2010-09-15 | 2010-12-02 | 7382043 | 6.840
8217 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 1808173 | Resurface Albany, Rensselaer, Saratoga and Schenectady counties. Locations include: State Route 9 in Halfmoon, Clifton Park and Malta between State Route 146 and Crescent Avenue; State Route 20 in Gui | Pavement Improvement | 2009-08-27 | 2009-08-27 | 2009-11-16 | 2010-10-31 | 9030380 | 24.070
8218 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1935773 | Wharf and dock repairs at the Port of Albany in the City of Albany. | Other | 2009-12-14 | 2009-12-14 | 2011-08-08 | 2011-11-11 | 5021041 | 0.000
8219 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1941253 | Rehabilitation of the Existing Schenectady Trail | Transportation Enhancements | 2009-11-18 | 2009-11-18 | 2010-10-29 | 2010-09-30 | 1230000 | 0.000
8220 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | HERKIMER |  | 24 | 2012043 | Rehabilitate the bridge carrying Route 169 over the CSX railroad and the Erie Canal in the City of Little Falls, Herkimer County. The project will include repairing deteriorated concrete and repaving | Bridge Improvement | 2009-05-27 | 2009-05-27 | 2010-06-30 | 2010-06-30 | 1310466 | 0.000
8221 | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | ONEIDA |  | 23 | 2650303 | Sylvan Beach Pedestrain Connection Project, ARRA Transportation Enhancement Project, Village of Sylvan Beach. | Transportation Enhancements | 2011-08-04 | 2011-08-04 | 2011-11-10 | 2011-11-10 | 731000 | 0.000
8222 | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | HERKIMER |  | 24 | 2650313 | Mohawk Streen Beautification Enhancement Project, ARRA Transportation Enhancement Project, Village of Herkimer. | Transportation Enhancements | 2010-07-26 | 2010-07-26 | 2010-10-29 | 2010-10-29 | 800000 | 0.000
8223 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | HERKIMER |  | 24 | 2650323 | Main Street Streetscape Enhancement Project, ARRA Transportation Enhancement Project, Village of Dolgville. | Transportation Enhancements | 2011-07-21 | 2011-07-21 | 2012-06-01 |  | 1000000 | 0.370
8224 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | MONTGOMERY |  | 21 | 2650333 | CHURCH AND MAIN STREETSCAPE ENHANCEMENT PROJECT, VI LLAGE OF CANAJOHARIE. | Transportation Enhancements | 2010-10-21 | 2010-10-21 | 2012-06-29 |  | 1000000 | 0.180
8225 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2804843 | Paint and wash bridges carrying state highways in Oneida, Madison, Herkimer, Hamilton, Fulton and Montgomery counties. These preventative maintenance treatments will inhibit deterioration and extend t | Bridge Improvement | 2009-04-29 | 2009-04-29 | 2009-11-30 | 2009-11-30 | 2119629 | 0.000
8226 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2804853 | Paint and wash bridges carrying state highways in Oneida, Madison, Herkimer, Hamilton, Fulton and Montgomery counties. These preventative maintenance treatments will inhibit deterioration and extend t | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2009-11-30 | 2009-11-30 | 311357 | 0.000
8227 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | ONEIDA | UTICA-ROME | 24 | 2804893 | Resurface Routes 5A and 69 in the City of Rome, Town of Whitestown and villages of Oriskany, Yorktown and Whitesboro in Oneida County. The project will include repaving, traffic signal replacement and | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-18 | 2009-12-18 | 2688900 | 14.760
8228 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ONEIDA | UTICA-ROME | 24 | 2805083 | Replace the bridge joints on five structures along Interstate 790 in the City of Utica, Oneida County. This preventative maintenance project will maintain the bridges structural reliability. | Bridge Improvement | 2009-05-19 | 2009-05-19 | 2009-11-30 | 2009-07-09 | 420485 | 0.000
8229 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST0043 | Paint 14 bridges, one in Fulton County, four in Herkimer County, two in Montgomery County and seven in Oneida County. The structural steel elements of each bridge will be commercially sandblasted to e | Bridge Improvement | 2010-03-15 | 2010-03-15 | 2010-05-14 | 2010-07-30 | 2472409 | 0.000
8230 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST0123 | Repair or replace deficient sidewalks in 20 municipalities in Fulton, Hamilton, Herkimer, Madison, Montgomery and Oneida counties. New, concrete sidewalks will be installed and ramps will be upda | Safety/Traffic Management | 2010-02-10 | 2010-02-10 | 2010-11-19 | 2010-11-19 | 2643708 | 13.990
8231 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | HAMILTON |  | 23 | 2ST0343 | Replace the bridge carrying Big Brook Road over Lake Abanake in the town of Indian Lake, Hamilton County. The existing structure will be replaced with a higher bridge to accommodate boat traffic in th | Bridge Replacement | 2009-09-17 | 2009-09-17 | 2010-12-13 | 2010-12-13 | 694178 | 0.000
8232 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST0413 | A project to provide various safety improvements in the cities of Amsterdam, Johnstown, Gloversville, Little Falls, Oneida, Sherrill, Rome and Utica, in Montgomery, Fulton, Herkimer, Madison and Oneid | Safety/Traffic Management | 2010-02-15 | 2010-02-15 | 2010-09-28 | 2010-09-28 | 555357 | 2.430
8233 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST1003 | Resurface approximately three miles of Route 5S from the Herkimer County Line to Sanders Road in the town of Minden, Montgomery County and resurface approximately 5.5 miles of Route 29 from Vail Mills | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-11-30 | 2009-10-08 | 767497 | 8.900
8234 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | HERKIMER | UTICA-ROME | 24 | 2ST1013 | Resurface highways in Herkimer County, including approximately 1.5 miles of Route 5S from Main Street in Frankfort to Route 51 in Ilion; approximately three miles of Route 28 from Route 8 to Comstock | Pavement Improvement | 2010-04-01 | 2010-04-01 | 2010-07-23 | 2010-07-23 | 1510958 | 4.350
8235 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | ONEIDA | UTICA-ROME | Multiple | 2ST1023 | Rehabilitate several state highways in Oneida County, including resurfacing approximately 16 miles of various highways and approximately five miles of shoulders along I-790 in Oneida County. In the ur | Pavement Improvement | 2009-10-01 | 2009-10-01 | 2010-09-10 | 2010-09-10 | 4186448 | 35.580
8236 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST2003 | Rehabilitate pavement at 14 sites in the cities of Amsterdam, Montgomery County; Johnstown and Gloversville, Fulton County; and Little Falls, Herkimer County. Work will consist primarily of milling an | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2010-10-01 | 2010-10-01 | 3416317 | 0.000
8237 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONTGOMERY |  | 21 | 2V09513 | Resurface Route 67 through the towns of Amsterdam and Mohawk in Montgomery County. This preventive maintenance project will seal the asphalt surface to prevent water from entering cracks in the paveme | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2010-06-30 | 2009-09-03 | 131680 | 3.070
8238 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2V09613 | Resurface approximately 15 miles of Routes 8, 12 and 20 through the towns of Trenton, Steuben, Forestport and Cazenovia in Oneida County and the Town of Brookfield, Madison County. This preventive mai | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2010-06-30 | 2009-09-10 | 774881 | 11.510
8239 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2V09713 | Resurface approximately nine miles of Route 12B in the towns of Marshall and Kirkland, Oneida County, and the towns of Madison and Augusta, Madison County. This preventive maintenance project will sea | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-30 | 2009-10-05 | 553650 | 9.000
8240 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3155243 | Replace two bridges on State Route 90 in Cayuga County. One bridge is over Little Salmon Creek in the Town of Genoa and the other is over Paines Creek in the Town of Ledyard. This project will remove | Bridge Replacement | 2009-10-13 | 2009-10-13 | 2010-12-01 | 2010-11-16 | 3332044 | 0.010
8241 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA |  | 25 | 3501423 | Replacement of the bridge carrying Bartell Road over Interstate 81 in the Town of Cicero, Onondaga County. The new bridge will increase safety and capacity. | Bridge Replacement | 2009-05-21 | 2009-05-21 | 2010-01-28 | 2010-12-16 | 7078130 | 0.100
8242 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA | SYRACUSE | 25 | 3601923 | Resurface almost five miles of Interstate 690 eastbound and westbound from the Teall Avenue interchange to the Interstate 481 interchange. This essential maintenance in the City of Syracuse, Onondaga | Pavement Improvement | 2009-05-25 | 2009-05-25 | 2010-09-01 | 2010-08-26 | 8820468 | 11.320
8243 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA | SYRACUSE | 25 | 3602033 | Resurface Route 20 in Madison County and Onondaga County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2009-07-28 | 2010-10-28 | 1135629 | 8.600
8244 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3602043 | Paving Route 11 in the Town of Hastings, Onondaga County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-09-02 | 2009-09-02 | 303719 | 2.500
8245 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 24 | 3602063 | Resurface Route 79 from the Tioga County line to Besner Hill in the Town of Caroline, Tompkins County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fr | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-01 | 2009-09-09 | 1230176 | 7.000
8246 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 24 | 3602073 | Resurface Route 79 through the towns of Ithaca and Enfield, Tompkins County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-06-24 | 2010-06-24 | 981857 | 8.460
8247 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3602106 | Paving Route 34, Cayuga County | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-08-17 | 2010-08-17 | 468447 | 3.600
8248 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3602113 | Paving Route 104A, Cayuga County Line To Oswego County | Pavement Improvement | 2010-05-08 | 2010-05-08 | 2010-05-22 | 2010-05-22 | 371960 | 2.780
8249 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SENECA |  | 24 | 3602313 | Paving Route 96 to Village of Waterloo, Seneca County | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2009-07-28 | 2010-06-18 | 673157 | 6.240
8250 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3602353 | Paving Route 34, County Route 43B at Venice Center to Skillet/Mosher Road. Towns of Scipio and Venice, Cayuga County | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2009-07-28 | 2010-09-07 | 858711 | 5.970
8251 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3602393 | Paving Route 38, Hamlet of Cascade to Wyckoff Road, Towns of Venice & Scipio, Cayuga County | Pavement Improvement | 2010-07-15 | 2010-07-15 | 2009-07-28 | 2010-07-29 | 836536 | 6.950
8252 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CORTLAND |  | 24 | 3602403 | Paving Route 11/41, City of Cortland to Village of McGraw, Town of Cortlandville, Cortland County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-10-19 | 844054 | 5.660
8253 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SENECA |  | 24 | 3602493 | Paving Route 414, Fayette South Town Line to Village of Seneca Falls, Towns of Fayette and Seneca Falls, Seneca County | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2009-07-28 | 2010-06-25 | 691645 | 5.790
8254 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA |  | 25 | 3752893 | Rehabilitate the Dorwin Avenue bridge over Onondaga Creek in the City of Syracuse, Onondaga County. The bridge deck and superstructure will be removed and replaced with a new multi-girder steel supers | Bridge Improvement | 2009-08-03 | 2009-08-03 | 2010-07-16 | 2010-07-16 | 1296269 | 0.020
8255 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA | SYRACUSE | 25 | 3752983 | Reconstruct Taft Road from South Bay Road to Northern Boulevard in the town of Clay and Cicero, Onondaga County. The project will rehabilitate and widen Taft Road from South Bay Road to Church Street | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2011-08-19 | 2011-06-13 | 8434943 | 3.100
8256 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 24 | 3753733 | Reconstruct County Route 121, Warren Road, from Route 13 to North Asbury Road in the Village and Town of Lansing, Tompkins County. The safety-improvement project will include new asphalt and fresh pav | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-03-01 | 2010-10-30 | 5306318 | 2.970
8257 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SENECA |  | 24 | 3754223 | A project sponsored by Seneca County to replace the Brewer Road bridge over Black Brook. This project will remove this bridge from the deficient bridge inventory. | Bridge Replacement | 2009-09-01 | 2009-09-01 | 2011-02-01 | 2010-05-04 | 350000 | 0.000
8258 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SENECA |  | 24 | 3754273 | County Route 43, Dawson Corners over Boardman Creek in Seneca County. | Bridge Replacement | 2010-02-01 | 2010-02-01 | 2010-09-03 | 2010-09-02 | 716400 | 0.000
8259 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CORTLAND |  | 24 | 3754543 | A project sponsored by Cortland County to reconstruct 1.7 miles of Page Green Road (County Route 122) from Congden Lane to New York Route 392. This project is the third phase of an effort to rebuild P | Pavement Improvement | 2010-07-08 | 2010-07-08 | 2012-04-02 | 2011-10-21 | 1617000 | 0.000
8260 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3754923 | A project sponsored by the Town of Mentz, Cayuga County, to replace the Haiti Road Bridge over the Seneca River. This project will remove this bridge from the deficient bridge inventory. | Bridge Replacement | 2010-03-11 | 2010-03-11 | 2011-05-02 | 2010-10-20 | 1271760 | 0.000
8261 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 22 | 3755043 | Replace and Upgrade the traffic signal at the College Ave/Dryden Rd Intersection, City Of Ithaca. | Safety/Traffic Management | 2010-02-24 | 2010-02-24 | 2010-09-13 |  | 220000 | 0.000
8262 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 3804963 | Clean and paint nine different state bridges in Cayuga, Oswego, and Onondaga counties. This project will protect the structural integrity of the steel and improve the aesthetic appearance of each brid | Bridge Improvement | 2009-07-23 | 2009-07-23 | 2010-05-14 | 2010-05-15 | 1774117 | 0.010
8263 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 24 | 3950423 | A Transportation Enhancement Program (TEP) project to reinforce the structural integrity of the pedestrian bridge across Six Mile Creek between Columbia Street and Ferris Street in the city of Ithaca, | Transportation Enhancements | 2010-08-16 | 2010-08-16 | 2011-11-03 |  | 1077628 | 0.000
8264 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | CORTLAND |  | 24 | 3950463 | A Transportation Enhancement Program (TEP) project to complete the restoration of a former rail depot, including interior and exterior renovations, such as installation of parking, sidewalks and, cons | Transportation Enhancements | 2009-06-26 |  | 2012-06-27 |  | 409734 | 0.000
8265 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CORTLAND |  | 24 | 3M07283 | Paving Route 222, Cortlandville, Cortland/Tompkins County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-09-21 | 541845 | 3.500
8266 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3M07293 | Paving Route 11, Town of Parish- Oswego County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-09-08 | 369775 | 0.000
8267 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3M07303 | Paving Route 104, Towns of Sterling & Victory, Cayuga County | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2009-07-28 | 2010-09-05 | 1048002 | 4.000
8268 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3M07323 | Paving Route 104, Town and Village of Hannibal, Oswego County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-10-14 | 468560 | 0.000
8269 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3M07333 | Paving Route 104, Village of Hannibal, Oswego County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-10-30 | 864098 | 3.100
8270 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 3M09043 | Rehabilitate multiple state-owned bridges in Cayuga, Cortland, Onondaga, Oswego and Seneca counties. This project will improve the overall condition and safety of multiple state-owned bridges. | Bridge Improvement | 2009-11-03 | 2009-11-03 | 2010-02-26 |  | 2140952 | 0.000
8271 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4005503 | Resurfacing of Route 5 from the Village of Lima to Ontario County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-28 | 206212 | 2.170
8272 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4005573 | Resurfacing of Route 5 from the Village of Avon to the Village of Lima | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-09-07 | 531400 | 5.530
8273 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4015343 | Resurface a portion of State Route 15 from Route 252 to I-390 in the towns of Brighton and Henrietta, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new | Pavement Improvement | 2009-07-24 | 2009-07-24 | 2009-11-30 | 2009-11-30 | 2077780 | 1.800
8274 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4019563 | Resurfacing of Route 19 from Route 78 to Route 19a - Town of Gainseville | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-14 | 275426 | 2.030
8275 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4021223 | Resurfacing of Route 21 from Route 332 to Route 96 - City of Canandaigua | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2010-06-30 | 2010-08-11 | 857104 | 7.200
8276 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4021243 | Resurfacing of Route 21 from Griesha Hill Road to Bopple Hill Road | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2010-06-30 | 2010-07-29 | 621768 | 10.920
8277 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4031393 | Replace the Route 31F bridge over Irondequoit Creek in the Town of Perinton. (BIN 1022120) | Bridge Replacement | 2009-12-17 | 2009-12-17 | 2011-01-11 |  | 1260000 | 0.000
8278 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORLEANS |  | 26 | 4031763 | Resurfacing of Route 31 from Niagara County to Salt Works Road | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-09-08 | 269285 | 2.400
8279 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | Multiple | 4031793 | Resurface a portion of State Route 31F from Route 250 in the village of Fairport to the Wayne County line in the town of Perinton, Monroe County. The top layer of worn, deteriorated pavement will be r | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2009-10-29 | 2009-10-31 | 1212139 | 3.780
8280 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | Multiple | 4031823 | RESURFACING OF VARIOUS FA ROUTES REGIONWIDE RT 31 | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-21 | 658620 | 7.560
8281 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4036173 | Construction of a Genesee Valley Greenway Trail bridge over the Genesee River at Route 36 in the towns of Mt. Morris and Leicester, Livingston County. This new pedestrian bridge will make continuous a | Bridge Improvement | 2009-08-12 | 2009-08-12 | 2011-01-05 | 2011-11-10 | 1875478 | 0.000
8282 | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4036183 | Resurface a portion of State Route 36 from the Steuben County line to Route 63 and from Route 63 to Route 436 in town of Dansville, Livingston County. The top layer of worn, deteriorated pavement will | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-19 | 2009-10-19 | 696345 | 2.320
8283 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4036213 | Resurfacing of Route 36 from Route 20 to Route 5 | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-19 | 592182 | 7.380
8284 | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4039493 | Install edge drain on State Route 39 from Route 98 to Eagle Road in towns of Arcade and Eagle, Wyoming County. Edge drain will improve the proper draining of storm-water runoff and aid in prevention o | Pavement Improvement | 2009-05-26 | 2009-05-26 | 2009-07-10 | 2009-08-31 | 676473 | 6.190
8285 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4039523 | Resurfacing of Route 39, Wyoming County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-11 | 550525 | 5.650
8286 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4064103 | Resurfacing of Route 64 from Route 5 & 20 in Ontario/Monroe County | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2011-03-25 | 2010-08-24 | 651608 | 14.450
8287 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4064113 | Resurfacing of Route 64 from Dugway Road To Route 5&20 | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2009-10-30 | 2009-08-04 | 671961 | 7.010
8288 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | GENESEE |  | 26 | 4077063 | Resurface a portion of State Route 77 from Route 20 to Route 5 and on Route 5 from Route 33 to the Corfu village line in the towns of Darien and Pembroke and the village of Corfu, Genesee County. The | Pavement Improvement | 2009-05-26 | 2009-05-26 | 2009-12-14 | 2009-12-14 | 3461434 | 16.040
8289 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4088183 | Resurfacing of Route 88 from Village of Newark to Route 104 | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2009-10-30 | 2009-10-05 | 393185 | 12.250
8290 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4096513 | Resurface a portion of State Route 96 from Kreag Road in the town of Perinton, Monroe County, to Route 64 in the town of Pittsford, Monroe County. The top layer of worn, deteriorated pavement will be | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2009-11-19 | 2009-11-19 | 1002454 | 2.610
8291 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 26 | 4096523 | Resurface a portion of State Route 96 from Rt. 88 to Lester Road in the village of Phelps, Ontario County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt an | Pavement Improvement | 2009-07-23 | 2009-07-23 | 2009-09-03 | 2009-09-03 | 374949 | 1.800
8292 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GENESEE | ROCHESTER | 26 | 4098393 | Repave Rt. 98 between Rt. 5 (Main St.) and Noonan Drive in the City of Batavia, Genesee County. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-18 | 2009-09-18 | 484184 | 1.180
8293 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 26 | 4104423 | Resurface a portion of State Route 104 from Route 259 to Route 261 in the towns of Greece and Parma, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new a | Pavement Improvement | 2009-07-14 | 2009-07-14 | 2009-10-12 | 2009-10-12 | 1316452 | 2.010
8294 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4246083 | Resurfacing of Route 246 from Route 39 to the North Village Line | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2009-10-30 | 2009-08-06 | 136309 | 1.010
8295 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4256063 | Paving on Route 256 from Sliker Hill Road to Route 20A | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-10-26 | 1074321 | 9.830
8296 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 26 | 4259063 | Resurface a portion of State Route 259 from Colby Street to Big Ridge Road in town of Ogden and village of Spencerport, Monroe County. The top layer of worn, deteriorated pavement will be removed and | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2009-10-29 | 2009-10-08 | 1518780 | 1.670
8297 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 26 | 4261063 | Resurfacing of Route 261 from Route 104 to Route 18 | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2009-10-30 | 2009-08-31 | 249623 | 2.620
8298 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GENESEE |  | 26 | 4262063 | Resurfacing of Route 262 from Route 98 to Route 237 | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-09-17 | 502595 | 6.510
8299 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO | ROCHESTER | 24 | 4332053 | Repave Rt. 332 from Rt. 5 & 20 to Chapel Street in the City of Canandaigua, Ontario County. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-10-31 | 2009-09-24 | 1825407 | 3.420
8300 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4354063 | Resurfacing of Route 354 from Erie County Line to Route 98 | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2009-10-30 | 2009-08-18 | 1111548 | 11.210
8301 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4364023 | Resurfacing of Route 364 from Gateway Road to Route 5/20 | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-20 | 365998 | 5.290
8302 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4390553 | Resurface a portion of Interstate 390 from the New York State Thruway to the interchange of Interstate 590 in the town of Henrietta, Monroe County. The top layer of worn, deteriorated pavement will be | Pavement Improvement | 2009-08-25 | 2009-08-25 | 2010-08-31 | 2010-08-05 | 2150005 | 5.070
8303 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4488043 | Resurfacing of Route 488 from Route 21 To Route 96, Ontario County. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2011-03-25 | 2009-09-16 | 265423 | 9.130
8304 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | Multiple | 4531063 | Resurface a portion of State Route 531 from Route 36 in the town of Ogden, Monroe County, to I-490 in the town of Gates, Monroe County. The top layer of worn, deteriorated pavement will be removed and | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2010-11-20 | 2009-11-02 | 2099046 | 7.560
8305 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4754183 | An enhancement project to create Artwalk on University Avenue from Goodman St. to Union St and on Goodman St. from East Ave. to Circle St. and for Artwalk 2- Urban Trail Extension on University Avenue | Transportation Enhancements | 2011-05-31 | 2011-05-31 | 2011-05-17 |  | 3839000 | 0.000
8306 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | ROCHESTER |  | 4805653 | Apply a preventative maintenance treatment to seal cracks in the pavement along various state highways in Genesee and Monroe counties. This type of work keeps the highway system in a state of good rep | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2010-03-10 | 2009-08-25 | 271710 | 0.000
8307 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | ROCHESTER |  | 4805693 | Wash bridges and seal bridge decks at selected locations in Wayne, Ontario, Monroe, Livingston, Orleans, Genesee and Wyoming counties. This type of work keeps the system in a state of good repair. | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2009-08-26 | 2009-08-27 | 433412 | 0.000
8308 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | ROCHESTER |  | 4805733 | Regionwide Resurfacing Of Rural/Low Volume Highways | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2011-02-25 | 2010-06-02 | 513066 | 0.000
8309 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 26 | 4947213 | Resurfacing of Route 947A -Lake Ontario State Parkway | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2010-08-30 | 2010-09-08 | 755877 | 6.790
8310 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GENESEE |  | 26 | 4LS0003 | A Genesee County project to resurface a portion of Batavia-Stafford Town Line Road from Route 33 to Assemblyman R. Steven Hawley Drive, and a portion of Assemblyman R. Steven Hawley Drive from Bank St | Pavement Improvement | 2009-08-01 | 2009-08-01 | 2009-12-30 | 2009-08-21 | 298185 | 0.000
8311 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4LS0023 | A Livingston County project to resurface a portion of Sliker Hill Road from Route 256 to Route 15 in the town of Conesus, and a portion of Perry Road from Route 36 to Route 20A in the town of Leiceste | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2009-12-31 | 2009-11-30 | 1355329 | 0.000
8312 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4LS0043 | A village of Dansville project to resurface a portion of Maple Avenue from Route 63 to Route 36 in the village of Dansville, Livingston County. The top layer of worn, deteriorated pavement will be rem | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2010-06-04 | 2010-10-29 | 370500 | 0.000
8313 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4LS0073 | A village of Geneseo project to resurface a portion of Lima Road from North Street to Geneseo village line in the village of Geneseo, Livingston County. The top layer of worn, deteriorated pavement wi | Pavement Improvement | 2009-10-12 | 2009-10-12 | 2010-04-30 | 2009-11-10 | 195050 | 0.000
8314 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0083 | Upgrade bridges on Driving Park, East Main Street, Main Street, Court Street, Elmwood Avenue, Lake Avenue, Andrews Street and Ford Street in the City of Rochester, Monroe County, with appropriate prev | Bridge Improvement | 2009-07-20 | 2009-07-20 | 2010-01-06 | 2009-12-31 | 1450439 | 0.000
8315 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0153 | A city of Rochester project to resurface a portion of Thurston Road from Brooks Avenue to Chili Avenue in the city of Rochester, Monroe County. A thin layer of asphalt will be placed on top of the exi | Pavement Improvement | 2010-04-15 | 2010-04-15 | 2011-08-18 | 2010-08-23 | 1962500 | 0.000
8316 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0163 | A City of Rochester project to reconstruct a portion of East Henrietta Road from Mount Hope Avenue to the Erie Canal in the city of Rochester, Monroe County. The existing pavement will be complete | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2011-10-05 | 2010-10-30 | 2142000 | 0.000
8317 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE |  | 28 | 4LS0223 | A city of Rochester project to resurface Byron Street from South Avenue to S. Clinton Avenue in the city of Rochester, Monroe County. The top layer of worn, deteriorated pavement will be removed and r | Pavement Improvement | 2010-04-13 | 2010-04-13 | 2011-02-21 | 2010-09-02 | 2141000 | 0.000
8318 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0263 | A city of Rochester project to replace sections of hazardous sidewalks in multiple locations within the city limits, Monroe County. Replacing sidewalks that are in disrepair will improve the service l | Transportation Enhancements | 2010-04-05 | 2010-04-05 | 2010-08-05 | 2010-08-31 | 981000 | 0.000
8319 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0273 | Streetscape Enhancements on North Clinton Avenue | Other | 2009-11-01 | 2009-11-01 | 2010-09-17 | 2010-10-12 | 1824300 | 0.000
8320 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4LS0323 | A Monroe County project to resurface Chili Center Coldwater Road from Route 33A to Westside Drive in the town of Chili, Elmgrove Road from Route 33 to Route 531 in the town of Gates, North Greece Road | Pavement Improvement | 2009-08-25 | 2009-08-25 | 2010-09-20 | 2010-09-18 | 3400000 | 0.000
8321 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE |  | 26 | 4LS0343 | Resurface various roads owned by Monroe County including: Dewey Avenue, Long Pond Road, English Road, East Ridge Road, North Goodman Street, Thomas Avenue, Culver Road, Panorama Trail, and Old Ridge R | Pavement Improvement | 2009-07-29 | 2009-07-29 | 2009-12-30 | 2010-09-03 | 5950000 | 0.000
8322 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | Multiple | 4LS0363 | Preventative maintenance projects on Monroe County bridges. The Flynn Road bridge in the town of Greece and the Brick School House bridge in the town of Hamlin will be deck sealed; the Redman Road and | Bridge Improvement | 2009-09-23 | 2009-09-23 | 2009-12-31 | 2009-10-10 | 323308 | 0.000
8323 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 25 | 4LS0633 | A Monroe County project to replace signs in various municipalities around the County. | Other | 2010-02-10 | 2010-02-10 | 2011-07-18 | 2010-05-27 | 296102 | 0.000
8324 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4LS0653 | A city of Canandaigua project to resurface a portion of Lakeshore Drive from Muar Street to S. Main Street in the city of Canandaigua, Ontario County. The top layer of worn, deteriorated pavement will | Pavement Improvement | 2009-09-03 | 2009-09-03 | 2010-07-16 | 2009-11-05 | 159726 | 0.000
8325 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO | ROCHESTER | 24 | 4LS0663 | A city of Canandaigua project to replace the West Avenue Bridge over Sucker Brook in the city of Canandaigua, Ontario County. | Bridge Replacement | 2009-09-03 | 2009-09-03 | 2010-04-09 | 2010-05-20 | 552117 | 0.000
8326 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4LS0673 | An Ontario County project to resurface County Road 41 from State Route 332 to County Road 8 in the town of Farmington, Bankert Road from State Route 96 to County Road 13 in the town of Phelps and Coun | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2009-12-30 | 2010-07-23 | 2743262 | 0.000
8327 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORLEANS |  | Multiple | 4LS0703 | An Orleans County project to replace signs in various municipalities around the county. | Other | 2009-07-28 | 2009-07-28 | 2011-02-21 | 2009-09-25 | 194427 | 0.000
8328 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0713 | A town of Arcadia to locally administer a project to make element-specific repairs to the Van Buren Street Bridge over CSX Railroad in the town of Arcadia, Wayne County. The deck will be sealed and wo | Bridge Improvement | 2009-08-25 | 2009-08-25 | 2010-03-16 | 2010-03-31 | 409426 | 0.000
8329 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0723 | Resurface a portion of Lake Bluff Road from Route 104 to Ridge Road in the town of Sodus, Wayne County and a portion of Newark Marion Road from Lyon Road to the gravel pit in the town of Palmyra, Wayn | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2009-12-30 | 2009-09-04 | 177000 | 0.000
8330 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0743 | A Wayne County project to resurface a portion of Ridge Road from East Williamson hamlet to Van Slyke Road in the town of Sodus, Wayne County. The top layer of worn, deteriorated pavement will be remov | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2010-06-17 | 2010-06-14 | 340000 | 0.000
8331 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0753 | A Wayne County project to replace the bridge deck on the Christian Holler Road bridge over Salmon Creek in the town of Sodus, Wayne County. | Bridge Improvement | 2010-03-23 | 2010-03-23 | 2010-06-11 | 2010-06-11 | 225894 | 0.000
8332 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0763 | Resurface a portion of Atlantic Avenue from Downs Road to Route 350 in the town of Walworth, Wayne County. The top layer of worn, deteriorated pavement will be removed and replaced with new surface an | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2009-12-30 | 2009-10-30 | 87153 | 0.650
8333 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0773 | A town of Williamson project to replace the sidewalks on Ridge Road in the hamlet of Williamson, Wayne County. Replacing sidewalks that are in disrepair will improve the service life and provide a bet | Transportation Enhancements | 2010-05-17 | 2010-05-17 | 2010-06-30 | 2010-06-16 | 93933 | 0.000
8334 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0783 | A village of Palmyra project to reconstruct a portion of Route 21 (Canandaigua Street) from southern village line to Route 31 in the village of Palmyra, Wayne County. The existing pavement will be | Pavement Improvement | 2010-04-17 | 2010-04-17 | 2011-08-17 |  | 2191618 | 0.000
8335 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4LS0793 | Resurface a portion of Bixby Hill Road from Route 39 to the Cattaraugus county line in the town of Arcade, Wyoming County. The top layer of worn, deteriorated pavement will be removed and replaced wit | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2009-12-30 | 2009-09-21 | 697382 | 1.000
8336 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4LS0873 | Lehigh Valley Trail Extension, from Genesee Valley Greenway to River Road and from Rochester Junction to Clover Street, Enhancement Project in the Town of Mendon, Monroe County. | Transportation Enhancements | 2011-04-26 | 2011-04-26 | 2011-11-25 |  | 523000 | 0.000
8337 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0893 | A city of Rochester to locally administer a preventative maintenance project to paint and deck seal the Lake Avenue Bridge over CSX Railroad in the city of Rochester, Monroe County. Painting and s | Bridge Improvement | 2009-09-28 | 2009-09-28 | 2010-08-17 | 2009-11-26 | 61358 | 0.000
8338 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4LS0923 | Highway Preventative Maintenance, County Road 10, Geneseo Village Line to Maple Beach Road (County Road 44) in the Towns of Geneseo and Groveland, Livingston County. | Pavement Improvement | 2010-06-08 | 2010-06-08 | 2010-08-02 |  | 2232247 | 0.000
8339 | Completed | C220,C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE |  | Multiple | 4LS0943 | A project to construct 7.3 miles of paved shoulders to provide for safe bicycle and pedestrian use along Jackson Rd in Penfield and Webster and Stone Rd in Henrietta and Pittsford. | Transportation Enhancements | 2011-04-04 | 2011-04-04 | 2011-08-17 | 2011-08-17 | 1489400 | 0.000
8340 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4LSA303 | Resurface various roads owned by Monroe County including: Brighton-Henrietta Town Line Road, South Winton Road, Calkins Road, Creek Street, Whalen Road, Five Mile Line Road, Whitney Road, Philips Road | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-06-30 | 2010-09-10 | 5478638 | 0.000
8341 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4T47103 | Install detectable warning fields at more than 800 locations across the seven-county region. The installation of plastic tiles containing raised bumps will help alert pedestrians with visual impairmen | Other | 2009-08-11 | 2009-08-11 | 2009-10-15 | 2009-10-16 | 304466 | 0.000
8342 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5006743 | Rehabilitate approximately 6.5 miles of Interstate 86 eastbound in the towns of Randolph and Cold Springs and the village of Randolph, all in Cattaraugus County. The project is addressing deterioratin | Other | 2009-07-31 | 2009-07-31 | 2010-01-29 | 2009-10-30 | 1018824 | 6.310
8343 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5006753 | Rehabilitate approximately 12 miles of Interstate 86 in the Towns of Sherman, North Harmony, and Ellery, in Chautauqua County. Eleven miles eastbound and 1 mile westbound will be improved. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2011-08-12 | 2011-07-15 | 4949516 | 11.630
8344 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5017283 | Replace two culverts on NY Route 242 in the towns of Ellicottville and Little Valley, Cattaraugus County. This project will eliminate culvert deficiencies and ensure good structural condition. | Other | 2009-06-23 | 2009-06-23 | 2010-01-29 | 2009-10-30 | 1287584 | 0.000
8345 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5019233 | Repave two sections of NY Route 265 (Military Road) in Erie County. Section 1 is .4 miles in length and extends from Fletcher Street to Tonawanda Creek in the city of Tonawanda, Erie County. Section 2 | Pavement Improvement | 2009-08-21 | 2009-08-21 | 2010-01-29 | 2009-10-31 | 1244894 | 1.940
8346 | Underway | C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5050963 | A bridge replacement project in the city of Niagara Falls of I-190 over the LaSalle arterial ramps. The project also includes repaving and guiderail improvements on I-190. | Pavement Improvement | 2010-02-26 | 2010-02-26 | 2012-09-26 |  | 4072362 | 0.770
8347 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5058393 | Conduct a bridge replacement and highway resurfacing and reconstruction project in the city of Jamestown, Chautauqua County. The objective of the project is to replace the Washington Street Bridge ove | Bridge Replacement | 2009-10-06 | 2009-10-06 | 2011-06-17 | 2011-05-31 | 4011173 | 0.500
8348 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5086283 | A project to reconstruct into a modern roundabout the intersection of State Route 324 (Grand Island Boulevard) and Stahley Road in the Town of Grand Island, Erie County. The project will address safe | Pavement Improvement | 2010-03-03 | 2010-03-03 | 2011-05-19 | 2011-05-25 | 1909800 | 0.000
8349 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5101793 | Repair culverts on US Route 219 and NY Route 400 in the towns of Boston and Concord, Erie County. This preventative maintenance work will eliminate corrosion and restore drainage elements to a state o | Other | 2009-07-01 | 2009-07-01 | 2009-12-29 | 2009-10-08 | 842715 | 4.700
8350 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5111903 | Replace the bridge for NY Route 20 over Bell Creek in the Town of Westfield, Chautauqua County. The existing bridge will be replaced with 3-side precast concrete bridge. | Bridge Replacement | 2010-01-04 | 2010-01-04 | 2010-10-28 | 2010-09-30 | 1042868 | 0.000
8351 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5470243 | Rehabilitate the stone facade of a notable bridge carrying NY Route 198, the Scajaquada Expressway, over NY Route 384 in the City of Buffalo, Erie County. The bridge is located in the historic site of | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2011-02-04 | 2010-11-12 | 2483814 | 0.000
8352 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5512463 | Route 33 Retaining Wall Railing and Corridor Enhancements | Other | 2009-10-23 | 2009-10-23 | 2012-01-19 | 2011-11-03 | 4613632 | 2.750
8353 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5580393 | Replace two highway ramp bridges at the Interstate I-190/ I-290 interchange in the Town of Tonawanda, Erie County. New bridges will be installed on new alignments to the north of the existing bridges, | Bridge Replacement | 2009-11-06 | 2009-11-06 | 2012-09-04 | 2011-12-30 | 2075732 | 0.000
8354 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 26 | 5755473 | Reconstruct Maple Road for 1.6 miles from Route 62 to Flint Road -- the entrance to State University of New York at Buffalo -- in the Town of Amherst, Erie County. The project will also reconstruct a | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2011-07-25 |  | 7000000 | 0.430
8355 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5755993 | Construct four new local roads in support of the Inner Harbor Redevelopment Plan, City of Buffalo, Erie County. The four roads are Lloyd, Hanover, Perry, and Prime Slip. | New Construction | 2009-09-22 | 2009-09-22 | 2011-12-19 | 2010-12-08 | 1900000 | 0.000
8356 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5756293 | A pavement resurfacing project including sidewalk and snow storage improvement on Porter Avenue in the city of Buffalo. | Pavement Improvement | 2010-07-23 | 2010-07-23 | 2011-12-30 | 2011-11-22 | 850000 | 0.000
8357 | Underway | C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5757173 | A roadway reconstruction project on portions of 10th Street and Cedar Avenue in the city of Niagara Falls. | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2012-11-01 |  | 1330000 | 0.000
8358 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 5757213 | Replace the Cedar Street Bridge over Tonawanda Creek in the town of Newstead, Erie County, and the town of Royalton, Niagara County. The bridge is in poor condition and will be reconstructed so that i | Bridge Replacement | 2009-08-11 | 2009-08-11 | 2011-07-21 | 2011-07-21 | 2055000 | 0.000
8359 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5757223 | A bridge replacement project of Drum Seaman Road over Johnson Creek in the town of Hartland. | Bridge Replacement | 2010-02-16 | 2010-02-16 | 2010-11-15 | 2010-11-15 | 790000 | 0.000
8360 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5757823 | Repave portions of three local streets in the city of Buffalo, Erie County, to address deteriorating pavement conditions. The streets are: Grant Street, Amherst Street, and Hertel Avenue. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-10-21 | 2010-10-21 | 431077 | 0.000
8361 | Completed | C220,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5758893 | Repave a 2.2 mile section of South Park Avenue, from Bailey Avenue to the Buffalo city line, in the city of Buffalo, Erie County. Sidewalks and lighting will also be improved along this corridor. | Transportation Enhancements | 2010-04-12 | 2010-04-12 | 2011-12-30 | 2011-11-07 | 1125000 | 0.000
8362 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5759143 | A project to conduct sidewalk and curb replacement along nine local streets in the City of Buffalo, Erie County. The streets are: Abbott Street from Cazenovia Street to Red Jacket Street; Austin Stre | Transportation Enhancements | 2010-05-07 | 2010-05-07 | 2010-10-21 | 2010-10-21 | 399047 | 0.000
8363 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5759153 | A project to repave nine local streets in the city of Buffalo, Erie County, to address deteriorating pavement conditions. The streets are: Abbott Street from Cazenovia Street to Red Jacket Street; Aus | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-08-31 | 2010-08-31 | 1155530 | 0.000
8364 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759213 | Repave 1.6 miles of Main Street (NY Route 104) from Ontario Street to Pierce Street in the city of Niagara Falls, Niagara County ( Main Street, Walnut Avenue to Ontario Avenue; 11th Street, Lockport S | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2009-12-15 | 2009-12-31 | 848109 | 0.000
8365 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759223 | Repave 0.4 miles of Packard Road from Niagara Falls Bou levard to the CSX Bridge in the City of Niagara Falls, Niagara County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2011-04-01 | 2010-07-28 | 952000 | 0.000
8366 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759233 | Repave 1.6 miles of Pine Avenue US Route 62 to Main Street (NY Route 104) in the city of Niagara Falls, Niagara County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2010-08-17 | 2010-07-30 | 1317372 | 0.000
8367 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759243 | Repave a two-mile section of Townline Road from Beach Ridge Road to the Bridge Over Bull Creek in the towns of Pendleton and Wheatfield in Niagara County to address deteriorating pavement conditions. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-10-29 | 2010-10-31 | 2480000 | 1.700
8368 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759253 | Conduct guide rail end replacements at approximately 50 locations throughout Niagara County to meet current federal standards. | Other | 2010-03-08 | 2010-03-08 | 2010-06-10 | 2010-07-02 | 141148 | 0.000
8369 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 29 | 5759263 | Repave a 3.1 mile section of Hartland Road, from Townline Road to Lake Road (NY Route 18), in the town of Somerset, Niagara County. The roadway will be paved to address deteriorating pavement conditio | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-12-14 | 2009-09-29 | 401627 | 2.950
8370 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759273 | Repave a one-mile section of Nash Road from Cherry Hill Road to Steig Road in the town of Wheatfield, Niagara County. The paving address deteriorating pavement conditions. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-12-14 | 2010-07-02 | 564330 | 0.930
8371 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759283 | Improve storm water management along Tonawanda Creek Road in the Town of Pendleton, Niagara County. | Other | 2009-08-10 | 2009-08-10 | 2009-12-14 | 2009-11-18 | 81833 | 1.810
8372 | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5759293 | Repave 4.1 miles of NY Route 430 from County Route 128/44 to County Route 13 in the Town of Ellery, Chautauqua County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-10-20 | 2009-10-20 | 2010-06-30 | 2010-06-04 | 877000 | 0.000
8373 | Underway | C250 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5759303 | Repave 5.6 miles of Hunt Road (County Route 82/32) from County Route 43 to the Jamestown city line in the towns of Busti, Ellicott, and North Harmony, in Chautauqua County. The project will address de | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2010-01-06 |  | 1099696 | 0.000
8374 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5759313 | Repave 1.7 miles of State Route 417 (West State Street) from the Olean city line to State Route 16 in the City of Olean, Cattaraugus County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-10-20 | 2009-10-20 | 2010-09-27 |  | 931122 | 1.700
8375 | Underway | C200 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5759323 | Repave 0.2 miles of Doughty Street from the NY Route 60 to Lincoln Avenue in the City of Dunkirk, Chautauqua County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2010-07-15 |  | 433635 | 0.000
8376 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5759343 | Repave 1.2 miles of County Route 4 (Broadway Road) in the Town of Persia. Repave 2.84 miles of CR 83 (Old Buffalo Road)and 0.9 miles of CR19 (Five Mile Road) in Town of Allegany,Cattaraugus County. Th | Pavement Improvement | 2009-09-03 | 2009-09-03 | 2009-10-09 | 2009-10-08 | 1077556 | 0.000
8377 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5759363 | Repave 2.1 miles of NY Route 417 (Wildwood Avenue) from Linwood Avenue to the east City line in the City of Salamanca, Cattaraugus County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2010-11-15 | 2010-09-14 | 1256000 | 0.000
8378 | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5759413 | Enhancement project that will construct a two-classroom building for traffic and personal safety instruction at the Chautauqua Children's Safety Education Village in the town of North Harmony, Chautau | Transportation Enhancements | 2009-09-15 | 2009-09-15 | 2011-03-01 | 2011-03-31 | 1760000 | 0.000
8379 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5759423 | ENHANCEMENTS TO OUTER HARBOR; SOUTH PARK AVE, TIFF STREET, TIFF STREET PIER, TIMES BEACH, GALLAGER BEACH, CITY OF BUFFALO; SIDEWALK, BOARDWALK, FISHING PIER, PARKING AND SEATING AREAS, BICYCLE/PEDEST | Transportation Enhancements | 2010-06-29 | 2010-06-29 | 2012-02-29 |  | 1075281 | 0.000
8380 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5759433 | UNION SHIP CANAL PROMEMADE - IMPROVE WESTERN END OF UNION SHIP CANAL. CONSTRUCT BOARDWALK AND PROMENADE WITH BENCHES, ARCHITECTUAL LIGHTING, FISH CLEANING TABLES AND RAISED LETTERING INFORMATIONAL DIS | Transportation Enhancements | 2010-04-06 | 2010-04-06 | 2011-12-30 |  | 2000000 | 0.000
8381 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | Multiple | 5759523 | A project to upgrade and repair bridge joints on six bridges in the towns of Lockport, Newfane, Niagara, Pendleton, Wilson, and Wheatfield. | Bridge Improvement | 2010-05-01 | 2010-05-01 | 2010-05-21 | 2010-05-21 | 216917 | 0.000
8382 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5805903 | Replace nine traffic signals and 41 pedestrian signals at various locations in Erie County. | Other | 2009-08-21 | 2009-08-21 | 2012-02-29 | 2011-10-31 | 891570 | 0.000
8383 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5806113 | Replace selected signs on state highways throughout the City of Buffalo, towns of Amherst and Cheektowaga and Village of Williamsville, Erie County. | Other | 2009-07-03 | 2009-07-03 | 2010-12-31 | 2010-11-02 | 397000 | 0.000
8384 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5807623 | Repair and replace bridge joints along Interstate 290 in the towns of Tonawanda and Amherst, Erie County. Joints require periodic repair to prevent water from penetrating onto other bridge elements, | Bridge Improvement | 2009-10-23 | 2009-10-23 | 2011-01-06 | 2010-11-08 | 200000 | 0.000
8385 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5807653 | Paint eight bridges in various locations in the city of Buffalo and town of Tonawanda, Erie County. The bridge painting is preventive maintenance. | Bridge Improvement | 2009-02-16 | 2009-02-16 | 2010-08-30 | 2010-07-10 | 537000 | 0.000
8386 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | BUFFALO-NIAGARA FALLS, NY |  | 5807683 | A project to paint and seal eight bridges in Erie and Niagara counties. Painting bridges and sealing their supportive members and decks is preventive maintenance done to keep water from penetra | Bridge Improvement | 2010-01-18 | 2010-01-18 | 2010-08-27 | 2010-07-31 | 1000000 | 0.000
8387 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | BUFFALO-NIAGARA FALLS, NY |  | 5808233 | Install approximately 285 detectable warnings at various locations in the city of Buffalo and the town of Cheektowaga in Erie County, and the city of Niagara Falls and the town of Wheatfield in Niagar | Transportation Enhancements | 2009-08-21 | 2009-08-21 | 2010-01-11 | 2009-11-09 | 263066 | 0.000
8388 | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5810433 | Resurface approximately three miles of pavement on US Route 219 and NY Route 417 in the City of Salamanca, Cattaraugus County, and Allegany Reservation of the Seneca Nation of Indians. The top layer o | Pavement Improvement | 2009-07-02 | 2009-07-02 | 2009-09-30 | 2009-08-25 | 978714 | 6.240
8389 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5810463 | Mill and repave highway access ramps with a single course overlay. Ramp locations, all in Erie County, include: N.Y. Route 78 in the towns of Clarence and Amherst, N.Y. Route 263 in the town of Amhers | Other | 2009-07-23 | 2009-07-23 | 2009-10-19 | 2009-09-30 | 474226 | 1.460
8390 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5810473 | Resurface approximately 1.5 miles of pavement on NY Route 78 in the Village of Depew and towns of Lancaster and Cheektowaga, Erie County. The top layer of worn, deteriorated pavement will be removed a | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-10-22 | 2009-09-30 | 726874 | 1.440
8391 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5810513 | Repave Route 957A, Robert Moses Parkway, from Interstate 190 to JB Daly Boulevard in the City of Niagara Falls, Niagara County. The top layer of worn, deteriorated pavement will be removed and replace | Pavement Improvement | 2009-07-23 | 2009-07-23 | 2009-12-10 | 2009-10-23 | 1172173 | 3.230
8392 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5810563 | Clean and repair closed drainage systems along State Routes 198, 78, 277, 5 and 425 in the towns of Tonawanda, Amherst and Clarence and the city of Buffalo, Erie County. Collapsed drainage structures | Other | 2009-08-06 | 2009-08-06 | 2009-12-29 | 2009-11-04 | 261041 | 5.040
8393 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 5810613 | Replace two overhead sign structures on State Route 400 in the towns of West Seneca and Elma and also install a 511 system signage region-wide. 511 is the state's latest traveler-advisory system. With | Other | 2009-08-12 | 2009-08-12 | 2010-08-27 | 2010-07-29 | 528419 | 0.000
8394 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE |  | Multiple | 5810623 | Replace joints on various bridges along the NY Route 33 corridor in the city of Buffalo and town of Cheektowaga, Erie County. | Bridge Improvement | 2009-07-03 | 2009-07-03 | 2010-01-06 | 2009-11-30 | 501454 | 0.000
8395 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 5810723 | Install signs for bike route 517 in Erie, Niagara, and Chautauqua counties. The project also includes sidewalk construction at the intersection of State Route 263 and State Route 270 in the Town of Am | Transportation Enhancements | 2009-10-27 | 2009-10-27 | 2010-08-27 | 2010-05-12 | 318340 | 0.000
8396 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5V09133 | Repave portions of State Route 394 totaling 6.2 miles in the towns of Cold Spring, Conewango, Napoli and Randolph and the village of East Randolph, in Cattaraugus County. The new pavement will address | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2011-02-15 | 2009-10-20 | 574789 | 6.160
8397 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5V09153 | Repave a five-mile portion of U.S. Route 62, from the Chautauqua County line to Youngs Road in the towns of Conewango and Leon, Cattaraugus County. | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2011-02-15 | 2010-06-30 | 342468 | 3.100
8398 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5V09163 | Conduct pavement crack sealing on approximately 100 miles of roads throughout Cattaraugus County. Asphalt pavement will be cleaned and sealant will be applied. | Pavement Improvement | 2009-09-01 | 2009-09-01 | 2009-12-15 | 2009-10-21 | 220061 | 0.000
8399 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 5V09213 | Repave approximately 21 miles of Interstate 86 in the towns of Ellery, Ellicott and Poland, the village of Falconer and the city of Jamestown in Chautauqua County, and the town and village of Randolph | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2011-01-03 | 2010-08-19 | 1487524 | 21.340
8400 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5V09223 | Repave a 2.5 mile bypass from Interstate 86 to NY Route 430 in the town of Ellery and village of Bemus Point, Chautauqua County. A single course overlay will be applied to address deteriorating paveme | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2011-01-31 | 2010-06-02 | 338446 | 1.620
8401 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5V09253 | Conduct pavement crack sealing on approximately 100 miles of roads throughout Chautauqua County. Asphalt pavement will be cleaned and sealant will be applied. | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2009-12-15 | 2009-10-22 | 260285 | 0.000
8402 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09323 | Seal pavement cracks on federal aid-eligible routes in northern Erie County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pave | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2011-01-31 | 2010-06-15 | 128297 | 0.000
8403 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09413 | Repave a 0.8 mile portion of US Route 20, from Cazenovia Creek to Seneca Street (NY Route 16) in the towns of West Seneca and Elma, Erie County. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2011-01-31 | 2010-06-30 | 229321 | 1.540
8404 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE |  | 27 | 5V09423 | Repave a one-mile portion of U.S. Route 20A (Quaker Street) in the village of Orchard Park, Erie County. The project will address deteriorating pavement conditions. The top layer of worn, deteriorated | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2009-09-15 | 2009-09-21 | 109955 | 1.020
8405 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09433 | Repave a 5.8-mile-long section of N.Y. Route 39 in Erie County, from N.Y. Route 75 in the town of Collins to Trevett Road in the town of Concord. The project will address deteriorating pavement condit | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2011-01-31 | 2010-10-05 | 350922 | 5.770
8406 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09443 | Repave a 3.5-mile-long portion of N.Y. Route 249 in the Town of North Collins, Erie County. The project will address deteriorating pavement conditions. The top layer of worn, deteriorated pavement wil | Pavement Improvement | 2010-08-20 | 2010-08-20 | 2009-09-15 | 2009-09-25 | 733595 | 3.480
8407 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09463 | Seal pavement cracks on federal aid-eligible routes in southern Erie County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pave | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2011-01-31 | 2010-07-09 | 225621 | 0.000
8408 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09513 | Repave a 3.7-mile-long portion of N.Y. Route 425 in the town of Cambria, Niagara County. The paving will extend from Upper Mountain Road to N.Y. Route 104. It will address deteriorating pavement condi | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-15 | 2009-09-11 | 450559 | 3.740
8409 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09523 | Repave a 10.4-mile-long portion of N.Y. Route 77 in the towns of Lockport and Royalton, Niagara County. The project will extend from N.Y. Route 31 to the Genesee County line. It will address deteriora | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-15 | 2009-10-15 | 1109897 | 10.440
8410 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09533 | Repave a 5.8-mile-long portion of NY Route 429 in Niagara County. The project will extend from Lockport Road in the town of Wheatfield to N.Y. Route 104 in the towns of Cambria and Lockport, where the | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-15 | 2009-10-20 | 964862 | 5.810
8411 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09543 | Seal pavement cracks on federal aid-eligible routes in Niagara County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pavements | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-15 | 2009-10-06 | 135253 | 0.000
8412 | Underway | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6008513 | Build embankment and pavement on a five-mile section of relocated US Route 15 in the Town of Lindley, Steuben County. This project is the first phase of a staged project to build a four lane highway w | Other | 2009-09-14 | 2009-09-14 | 2012-08-31 |  | 6056978.47 | 0.000
8413 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | YATES |  | 29 | 6011163 | A highway resurfacing project on Rt 54A from Branchport to Penn Yan in the town of Jerusalem and the village of Penn Yan in Yates County. | Pavement Improvement | 2010-03-23 | 2010-03-23 | 2010-11-04 | 2010-11-04 | 5380608 | 5.940
8414 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHUYLER |  | 29 | 6017213 | Replace the bridge carrying State Route 224 over Catharine Creek in the village of Montour Falls, Schuyler County. | Bridge Improvement | 2010-01-13 | 2010-01-13 | 2010-11-17 | 2010-11-17 | 1645644 | 0.000
8415 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6021143 | Replace the bridge carrying State Route 244 over the north branch of Phillips Creek in the town of Amity, Allegany County. | Bridge Replacement | 2010-01-14 | 2010-01-14 | 2011-05-26 | 2011-05-26 | 1422790 | 0.000
8416 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6037173 | Replace the bridge on Route 415 over Wolf Run Creek in the town of Campbell, Steuben County. | Bridge Replacement | 2009-05-20 | 2009-05-20 | 2009-12-30 | 2009-11-18 | 1612046 | 0.000
8417 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6056233 | Replace the bridge carrying State Route 417 over Dyke Creek in the town of Andover, Allegany County. | Bridge Replacement | 2010-01-12 | 2010-01-12 | 2010-11-15 | 2010-11-15 | 1340584 | 0.000
8418 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6066843 | Replace the I-86 bridge over Route 415 in the town of Painted Post, Steuben County. | Bridge Replacement | 2009-05-15 | 2009-05-15 | 2011-05-02 | 2011-06-02 | 4874526 | 0.000
8419 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | CHEMUNG | ELMIRA | 29 | 6753763 | A project to replace the county Route 43 bridge over Sing Sing Creek in the town of Big Flats, Chemung County. | Bridge Replacement | 2010-04-01 | 2010-04-01 | 2011-04-15 | 2011-12-19 | 1074171 | 0.000
8420 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | CHEMUNG | ELMIRA | 29 | 6754133 | A project to reconstruct Washington Avenue, from Davis Street to Walnut Street, in the city of Elmira, Chemung County. | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2011-06-30 | 2011-06-30 | 644000 | 0.000
8421 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6754293 | Resurface seven miles of County Route 12 from the Village of Alfred to State Route 417 in the towns of Andover, Ward, and Alfred, Allegany County. Existing pavement will be overlaid to provide a smoot | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2009-11-30 | 2009-09-04 | 795179 | 0.000
8422 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHUYLER |  | 29 | 6754303 | Resurface 2.5 miles of County Route 16 from Meads Hill Road to Townsend Road in the Town of Dix, Schuyler County. The existing pavement will be resurfaced to provide a smooth surface and prolong the l | Pavement Improvement | 2009-10-01 | 2009-10-01 | 2009-11-30 | 2009-10-05 | 240430 | 0.000
8423 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | YATES |  | 29 | 6754313 | Resurface 1.8 miles of County Route 32 from County Route 29 to County Route 33 in the Town of Jerusalem, Yates County. Existing pavement will be overlaid to provide a smooth surface and prolong the li | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2009-11-30 | 2010-05-19 | 183208 | 0.000
8424 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6754323 | Resurface 1.9 miles of County Route 14 from County Route 15 south in the Town of Bath, Steuben County. The existing pavement will be recycled and resurfaced with new asphalt. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2009-11-30 | 2009-09-03 | 227514 | 0.000
8425 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6754333 | Resurface 3.3 miles of County Route 14 from County Route 69 north in the towns of Bath and Howard, Steuben County. The existing pavement will be recycled and resurfaced with new asphalt. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2009-11-30 | 2009-09-02 | 434224 | 0.000
8426 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6754343 | Resurface four-tenths of a mile of East Avenue from Main Street to Addison Street in the Village of Arkport, Steuben County. The existing deteriorated pavement surface will be removed and replaced wit | Pavement Improvement | 2009-09-18 | 2009-09-18 | 2009-11-30 | 2009-09-21 | 80104 | 0.000
8427 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6754353 | Resurface 1.2 miles of streets in the City of Hornell, Steuben County. The project will overlay the existing pavement on portions of Thatcher, North Church, Erie, Center, and Adsit Streets to provide | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-11-30 | 2009-09-09 | 150885 | 0.000
8428 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN | ELMIRA | 29 | 6754443 | Resurface two-tenths of a mile of West Third Street in the City of Corning, Steuben County. The existing deteriorated pavement surface, from Walnut Street to State Street, will be removed and replaced | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-11-30 | 2009-10-06 | 19835 | 0.000
8429 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN | ELMIRA | 29 | 6754453 | Resurface one-tenth of a mile of East Third Street from Cedar Street to Pine Street in the City of Corning, Steuben County. The existing deteriorated pavement surface will be removed and replaced with | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2009-11-30 | 2009-10-06 | 17540 | 0.000
8430 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN | ELMIRA | 29 | 6754463 | Resurface four-tenths of a mile of West William Street from Pulteney Street to Bissell Avenue in the City of Corning, Steuben County. The existing deteriorated pavement surface will be removed and rep | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-11-30 | 2009-10-06 | 79584 | 0.000
8431 | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6754483 | A TEP project to complete the Genesee Valley Greenway in the village of Cuba, Allegany County. The project will include improving existing trail, constructing two new footbridges, installing gates and | Transportation Enhancements | 2011-02-01 | 2011-02-01 | 2011-08-31 | 2011-08-25 | 589400 | 0.000
8432 | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6754493 | A TEP project to enhance landscaping and to replace or install new light fixtures and sidewalks, sidewalk ramps and pavement markings in the village of Andover, Allegany County. | Transportation Enhancements | 2011-01-10 | 2011-01-10 | 2011-06-17 | 2011-06-17 | 513500 | 0.000
8433 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6803963 | Rehabilitate culverts in various locations in the towns of Urbana and Pulteney, Steuben County. | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2010-05-30 | 2009-07-28 | 915925 | 0.000
8434 | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804183 | Wash bridges and seal bridge decks at various locations in Allegany and Steuben counties. | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2009-09-30 | 2009-10-30 | 584282 | 0.000
8435 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804223 | A project to remove hazardous trees along select state rights-of-way in Allegany, Schuyler, Steuben, and Yates counties. | Other | 2010-02-01 | 2010-02-01 | 2010-05-30 | 2010-03-10 | 229199 | 0.000
8436 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804233 | Sidewalk Reconstruction for ADA compliance, Montour Falls, Addison, Southport. | Transportation Enhancements | 2009-10-27 | 2009-10-27 | 2010-06-30 | 2010-04-15 | 186044 | 1.370
8437 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | YATES |  | 29 | 6804263 | A project resurface 30 miles of state Routes 14, 14A, 245, 409 in Schuyler and Yates counties. | Pavement Improvement | 2010-03-04 | 2010-03-04 | 2010-12-15 | 2010-07-28 | 1933641 | 5.710
8438 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804273 | Rock Slope Remediation of 10 sites in Allegany & Steuben Counties. | Other | 2010-03-17 | 2010-03-17 | 2010-05-28 | 2010-04-21 | 366505 | 0.100
8439 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804283 | Paint bridges on I-86 and I-390 at various locations in Allegany and Steuben counties. | Bridge Improvement | 2009-08-25 | 2009-08-25 | 2010-10-31 |  | 1085544 | 0.000
8440 | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804293 | Rehabilitate bridges in various locations in Allegany and Steuben counties. | Bridge Improvement | 2009-07-07 | 2009-07-07 | 2009-10-31 | 2009-11-19 | 444923 | 0.000
8441 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6804333 | Repair 21 culverts on Interstate 86 in the towns of Cuba and Friendship, Allegany County. The project includes drainage structure replacement and culvert relining. | Other | 2009-08-13 | 2009-08-13 | 2010-06-30 | 2010-05-17 | 937268 | 0.000
8442 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6935223 | A project to repair two Bath & Hammondsport Railroad bridges over Niles Creek and Moores Creek in the town of Avoca, Steuben County. | Bridge Improvement | 2010-10-20 | 2010-10-20 | 2010-12-15 | 2011-11-29 | 625000 | 0.000
8443 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 23 | 7752473 | Replace the County Route 39 Bridge over the Grasse River in the Town of Louisville, St. Lawrence County. This project involves replacing the historic stone arch bridge with a steel structure adjacent | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2010-10-13 | 2010-10-13 | 3467929 | 0.000
8444 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LEWIS |  | 23 | 7752543 | A project to replace the Sweeney Road bridge over the East Branch of Fish Creek in the Town of West Turin, Lewis County. The new bridge will be built next to the existing structure and will have wide | Bridge Replacement | 2009-12-23 | 2009-12-23 | 2010-09-14 | 2010-09-14 | 725857 | 0.000
8445 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | JEFFERSON |  | 23 | 7752583 | A project to replace the Lisk Bridge carrying County Route 69 over Sandy Creek in the Town of Adams, Jefferson County. The new structure will be built adjacent to the existing bridge. Improvements w | Bridge Replacement | 2009-11-26 | 2009-11-26 | 2010-11-24 | 2010-11-24 | 2359999.53 | 0.000
8446 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 23 | 7752913 | Replace the Willow Street Bridge over the Salmon River in the Village of Malone, Franklin County. This project involves replacing the existing steel structure with a concrete structure at the same loc | Bridge Replacement | 2009-08-04 | 2009-08-04 | 2010-12-08 | 2010-12-08 | 1299000 | 0.000
8447 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LEWIS |  | 23 | 7752973 | Pave County Route 29, West Road, in the Town of Martinsburg, Lewis County. This project involves the rehabilitation of nearly three miles of roadway from Cemetery Road to State Route 26. | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2009-10-15 | 2011-08-04 | 990038 | 0.000
8448 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7753023 | Replace the Narrows Road Bridge over the Chateaugay Narrows in the Town of Ellenburg, Clinton County. The new bridge will have increased vertical clearance, allowing for easier movement of recreationa | Bridge Replacement | 2010-04-01 | 2010-04-01 | 2012-06-19 |  | 1364000 | 0.000
8449 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7753033 | Replace the Silver Lake Road Bridge over the Saranac River in the Town of Black Brook, Clinton County. The existing steel bridge will be replaced with a concrete structure at the same location. | Bridge Replacement | 2009-09-23 | 2009-09-23 | 2011-08-24 | 2011-08-24 | 1539682 | 0.000
8450 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7753083 | A bridge replacement project of Slosson Road over Little Chazy River in Clinton County. | Bridge Replacement | 2010-05-03 | 2010-05-03 | 2011-08-03 | 2011-08-03 | 774000 | 0.000
8451 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7753103 | Resurface approximately one mile of Oak Street, a Plattsburgh city street, and one mile of North Catherine Street (State Route 22), also in Plattsburgh. The streets, which run parallel to each other, | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-11-02 | 2009-10-16 | 218812 | 3.330
8452 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | JEFFERSON |  | 23 | 7753113 | Resurface Arsenal Street and Washington Street in the City of Watertown | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2011-06-16 | 2011-06-16 | 260114 | 1.790
8453 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804393 | Replace five intersection signal systems in Clinton, Franklin and Jefferson counties. These signal improvements will maximize travel efficiency at the intersections as well as provide an added measure | Safety/Traffic Management | 2009-12-04 | 2009-12-04 | 2010-11-18 | 2010-10-11 | 624067 | 0.000
8454 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804453 | Restore the protective paint on eight bridges in Jefferson and St. Lawrence counties. Structures to be addressed in the contract include Interstate bridges on I-81 in Jefferson County, as well as a pa | Bridge Improvement | 2009-07-14 | 2009-07-14 | 2009-12-18 | 2009-11-25 | 2897462 | 0.000
8455 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804553 | Provide much-needed maintenance to approximately 500 miles of highway in Lewis, Jefferson, St. Lawrence, Franklin and Clinton counties. This work involves cleaning and sealing cracks in the pavement t | Pavement Improvement | 2009-07-03 | 2009-07-03 | 2010-09-28 | 2010-09-27 | 1060415 | 0.000
8456 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804573 | Rehabilitate four large culverts in Jefferson and St. Lawrence counties. The culverts are located on State Routes 72, 184 and 342 and will be receiving new linings as well as inlet and outlet cleaning | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2010-08-10 | 2009-11-30 | 2626327 | 0.000
8457 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804733 | Clean and repaint nine state highway bridges in order to extend their useful service life. The project includes bridges carrying State Routes 22, 37, 37 C, 420 and 458 and U.S. Route 11 in Franklin, C | Bridge Improvement | 2010-04-06 | 2010-04-06 | 2010-12-14 | 2010-11-30 | 3273155 | 0.000
8458 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804763 | Repair bridges in Lewis, Jefferson, St. Lawrence, Franklin and Clinton counties. This work will help curb deterioration and improve overall bridge conditions. | Bridge Improvement | 2010-05-03 | 2010-05-03 | 2011-09-13 | 2011-07-29 | 2054181 | 0.000
8459 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 24 | 7805033 | Provide needed maintenance work to two bridges in St. Lawrence County. One structure is on State Route 11B and crosses the East Branch of the St. Regis River while the second is on State Route 420 and | Bridge Improvement | 2009-06-03 | 2009-06-03 | 2010-01-20 | 2009-11-18 | 1306928 | 0.000
8460 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7805053 | Replacing deteriorated guide rail in the Adirondack Park in Clinton Franklin and St. Lawrence counties. | Safety/Traffic Management | 2009-07-03 | 2009-07-03 | 2009-11-20 | 2009-11-21 | 1139464 | 0.000
8461 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7805213 | Reconstruct 1.5 miles of sidewalks and approximately 100 sidewalk ramps to bring them into compliance with federal Americans with Disabilities Act guidelines. Construction will focus on sidewalks and | Other | 2009-07-31 | 2009-07-31 | 2010-09-13 | 2010-06-17 | 754862 | 0.000
8462 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7805243 | A TEP project in the village of Rouses Point, Clinton County, will restore the National Register-listed Delaware and Hudson Railroad Station. In addition to replacing the roof, the restoration is expe | Transportation Enhancements | 2009-12-28 |  | 2012-11-30 |  | 833000 | 0.000
8463 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | JEFFERSON |  | 23 | 7805253 | A TEP project in Sackets Harbor, Jefferson County, to build six miles of non-motorized, multi-use trail in and around the village of Sackets Harbor. The trail system will link existing local historica | Transportation Enhancements | 2009-11-02 |  | 2012-08-06 |  | 495000 | 0.500
8464 | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 23 | 7805273 | A TEP project to build a multi-use trail to link the Market Street retail corridor with both Clarkson University and SUNY Potsdam in Potsdam, St. Lawrence County. The trail will connect to Sandstoner | Transportation Enhancements | 2010-09-22 | 2010-09-22 | 2011-10-20 | 2011-10-20 | 1450000 | 0.570
8465 | Underway | C950 | Ferryboat | NEW YORK | CLINTON |  | 23 | 7805281 | LAKE CHAMPLAIN TRANSPORTATION COMPANY FERRY SLIP SLIP RECONCONSTRUCTION, TOWN OF PLATTSBURGH, CLINTON CO. (ARRA FERRY BOAT DISCRETIONARY FUNDS) | Other | 2009-09-17 |  | 2013-02-28 |  | 289200 | 0.000
8466 | Underway | C950 | Ferryboat | NEW YORK | CLINTON |  | 23 | 7805283 | LAKE CHAMPLAIN TRANSPORTATION COMPANY FERRY SLIP SLIP RECONCONSTRUCTION, TOWN OF PLATTSBURGH, CLINTON CO. (ARRA FERRY BOAT DISCRETIONARY FUNDS) | Other | 2009-09-17 |  | 2012-10-02 |  | 2210800 | 0.000
8467 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | JEFFERSON |  | 23 | 7BRD083 | Construct two new traffic lanes and enhance shoulders on Interstate 81 on Wellesley Island in the Town of Orleans, Jefferson County. The improvements will help expedite border crossing movements and e | Pavement Widening | 2009-08-20 | 2009-08-20 | 2010-09-02 | 2009-12-30 | 1484414 | 0.180
8468 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 24 | 7V09113 | Resurface 1.3 Miles of Route 374, Village of Dannemora | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-10-08 | 174356 | 1.300
8469 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 24 | 7V09123 | Resurface 1.4 Miles of Route 9, Village of Champlain | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-09-23 | 156028 | 1.400
8470 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 24 | 7V09133 | Resurface 0.4 Miles Of Route 2U, US Route 11 - Vermont State Line | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-08-28 | 68719 | 0.400
8471 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 24 | 7V09243 | Resurface 4.8 Miles Of Route 374, Chateaugay - Brainardsville | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2011-10-21 | 2011-10-21 | 1042000 | 4.800
8472 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 24 | 7V09293 | Resurface 2.0 Miles of Route 3, Saint Lawrence County -Tupper Lake | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-09-16 | 249135 | 2.000
8473 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 24 | 7V09294 | Resurface 9.2 Miles Of Route 11, Malone - Chateaugay | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-09-09 | 1127487 | 9.200
8474 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 24 | 7V09295 | Resurface 0.8 Miles Of Route 30, Malone, Elm Street & Constable Street | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 |  | 1366220 | 0.500
8475 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 24 | 7V09594 | Resurface 3.9 Miles Of Route 68, Pierrepont - Colton | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-10-19 | 331072 | 3.900
8476 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 24 | 7V09595 | Resurface 1.1 Miles Of Route 184, Heuvelton Village (Union St) | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-08-14 | 130181 | 1.070
8477 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | COLUMBIA |  | 20 | 8001443 | Rehabilitate the Route 9G bridge over the Roeliff Jansen Kill in the Town of Germantown, Columbia County. | Bridge Improvement | 2009-10-06 | 2009-10-06 | 2011-11-30 | 2011-11-30 | 7041732 | 0.100
8478 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8010683 | A project to install a stormwater treatment system along Route 9, adjacent the Wappingers Lake in the Village of Wappingers Falls, Dutchess County. The new system will help to reduce pollutants enter | Other | 2009-11-26 | 2009-11-26 | 2011-03-28 | 2010-07-02 | 386741 | 0.290
8479 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 19 | 8029053 | A pavement overlay project of Route 123 in the city of Rye in Westchester County. | Pavement Improvement | 2010-02-12 | 2010-02-12 | 2010-09-24 | 2010-06-07 | 331114 | 1.490
8480 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 22 | 8062123 | Provide much-needed general maintenance of four bridges carrying Interstate 84 in the Town of Newburgh, Orange County. The work will extend the service life of the structures. | Bridge Improvement | 2009-09-07 | 2009-09-07 | 2011-08-16 | 2010-11-30 | 742023 | 0.000
8481 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8093573 | Replace the Palisades Interstate Parkway bridge over Route 202 in the towns of Haverstraw and Ramapo, Rockland County. | Bridge Replacement | 2009-06-11 | 2009-06-11 | 2011-12-30 | 2011-12-30 | 15477026 | 1.520
8482 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8099413 | Install an automated traffic management system on the Cross County Parkway in Westchester County. The new system will include acoustic vehicle detectors that will communicate with the regional Transpo | Safety/Traffic Management | 2009-05-29 | 2009-05-29 | 2011-08-23 | 2010-08-31 | 5493251 | 122.460
8483 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8177323 | Construct new bluestone sidewalks along Route 209 in the Hamlet of Stone Ridge located in the Town of Marbletown, Ulster County. The project will restore the historic sidewalk, repave a nearly one mil | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2010-05-28 | 2010-05-31 | 2914138 | 0.960
8484 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | POUGHKEEPSIE-NEWBURGH | Multiple | 8239163 | A project to reconstruct almost two miles of Robinson Avenue (Route 9W) in the City of Newburgh, Orange County. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2011-01-31 |  | 8352000 | 1.870
8485 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8327363 | A project to improve sidewalks and crosswalks at the intersection of Main Street (Route 9D) and Spring Street in the Village of Wappingers Falls, Dutchess County. The project will improve pedestrian | Safety/Traffic Management | 2010-05-13 | 2010-05-13 | 2010-12-03 |  | 158035 | 0.090
8486 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS |  | 20 | 8505203 | Construct a new park-and-ride lot on Route 199 in the Town of Rhinebeck, Dutchess County. The new facility will accommodate 35 parking spaces. And will include lighting and landscaping. | Other | 2009-10-06 | 2009-10-06 | 2010-08-31 |  | 311875 | 0.100
8487 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 19 | 8561363 | A pavement resurfacing project of Route 35 from Mead Street to Boutonville Road in the town of Lewisboro in Westchester County. | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2011-03-22 | 2010-12-31 | 377098 | 2.270
8488 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 20 | 8753783 | Replace the Leedsville Road (County Road 2) bridge over the Webutuck Tributary in the Town of Amenia, Dutchess County. | Bridge Replacement | 2009-12-28 | 2009-12-28 | 2011-10-03 |  | 593000 | 0.000
8489 | Underway | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8755143 | New Paltz Road/Conrail Bridge Repleacement in the Town of Lloyd. | Bridge Replacement | 2010-03-21 | 2010-03-21 | 2011-01-31 |  | 2224115 | 0.000
8490 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 20 | 8755813 | Replace the Crum Elbow Road, County Road 41, bridge over the Fallkill Creek in the Town of Hyde Park, Dutchess County. | Bridge Replacement | 2010-04-15 | 2010-04-15 | 2010-08-31 |  | 1110520 | 0.000
8491 | Underway | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8756193 | Replace the Main Street bridge over the Rondout Creek in the Town of Wawarsing, Ulster County. | Bridge Replacement | 2009-09-08 | 2009-09-08 | 2010-08-31 |  | 4519656 | 0.000
8492 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8756673 | Replace the Popham Road Bridge over the Metro-North Railroad tracks in the Village of Scarsdale, Westchester County. | Bridge Replacement | 2009-08-25 | 2009-08-25 | 2010-06-30 |  | 13006683 | 0.010
8493 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | COLUMBIA |  | 20 | 8757184 | A project to replace the Hall Hill Road bridge over the Roeliff Jansen Kill in the Town of Ancram, Columbia County. | Bridge Replacement | 2010-03-24 | 2010-03-24 | 2011-01-31 |  | 1355000 | 0.000
8494 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS |  | 19 | 8757253 | Rehabilitate the Lime Kiln Road bridge over the Ten Mile River in the Town of Dover, Dutchess County. The project will include cleaning and painting bridge members, waterproofing the bridge deck, repa | Bridge Improvement | 2009-09-24 | 2009-09-24 | 2012-02-01 |  | 1610100 | 0.020
8495 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | COLUMBIA |  | 20 | 8757613 | A project to replace the Empire Road bridge over the Roeliff Jansen Kill in the Town of Copake, Columbia County. | Bridge Replacement | 2010-03-24 | 2010-03-24 | 2011-01-31 |  | 1057000 | 0.000
8496 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | POUGHKEEPSIE-NEWBURGH | 18 | 8757723 | Replace the Odell Avenue Bridge over abandoned railroad tracks in the City of Yonkers, Westchester County. | Bridge Replacement | 2009-04-01 | 2009-04-01 | 2010-03-30 | 2010-05-26 | 1619219 | 0.020
8497 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 17 | 8757733 | Replace the South First Avenue Bridge over the Metro-North Railroad tracks in the City of Mount Vernon, Westchester County. | Bridge Replacement | 2009-09-08 | 2009-09-08 | 2010-06-30 | 2011-04-13 | 7616157 | 0.000
8498 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 22 | 8757873 | A project to replace the Hoffman Street bridge over Metro-North Railroad in the City of Poughkeepsie, Dutchess County. | Bridge Replacement | 2010-06-30 | 2010-06-30 | 2013-01-31 |  | 9939683 | 0.000
8499 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE |  | 22 | 8757933 | Replace the Petticoate Lane bridge over the Shawagunkill in the Town of Crawford, Orange County. (BIN 3344340) | Bridge Replacement | 2010-04-15 | 2010-04-15 | 2010-12-31 |  | 1396000 | 0.000
8500 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8758023 | Rehabilitate the Beckley Drive bridge over the Fantine Kill in the Town of Wawarsing, Ulster County. | Bridge Replacement | 2010-04-19 | 2010-04-19 | 2010-10-29 | 2010-10-15 | 1135000 | 0.000
8501 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8759123 | Provide new pavement markings along select highways throughout Dutchess County. The new pavement markings will improve roadway safety by increasing their reflectivity and better delineating the travel | Other | 2009-09-25 | 2009-09-25 | 2010-08-31 |  | 770140 | 0.000
8502 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8759143 | A project for a new/improved bicycle facility on the Hudson Valley Rail Trail from Haviland Road to Commercial Avenue in the town of Lloyd. | Transportation Enhancements | 2010-03-30 | 2010-03-30 | 2011-01-14 |  | 2610000 | 0.000
8503 | Underway | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 19 | 8759163 | Construction of a Park and Ride lot in the Village of Kiryas Joel. | Transportation Enhancements | 2009-12-29 | 2009-12-29 | 2010-12-31 |  | 1452194 | 0.000
8504 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | POUGHKEEPSIE-NEWBURGH | 19 | 8759473 | A project to improve East Shore Road in the Town of Warwick, Orange County. Pavement, drainage and retaining wall improvements will be made as part of the project. | Pavement Widening | 2010-03-11 | 2010-03-11 | 2011-01-31 |  | 839000 | 0.000
8505 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 19 | 8759493 | Phase 6 of a project to provide new sidewalks and rehabilitate existing sidewalks in the Village of Kiryas Joel, Orange County . The project will improve pedestrian access and safety. | Other | 2010-04-12 | 2010-04-12 | 2011-01-31 |  | 501000 | 0.000
8506 | Underway | C200 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8759793 | A project to perform pavement rehabilitation along County Roads 27, 93, 114, 35 and 77 in the towns of East Fishkill, Fishkill, Wappingers Falls and Poughkeepsie, Dutchess County. | Pavement Improvement | 2010-02-02 | 2010-02-02 | 2010-11-30 |  | 3911186 | 0.000
8507 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8760193 | Construct a pedestrian walkway along the Rondout Creek waterfront from Ravine Street to Route 9W in the City of Kingston, Ulster County. The project will build approximately .25 miles of walkway and 4 | Transportation Enhancements | 2009-09-16 | 2009-09-16 | 2011-01-31 | 2010-04-27 | 200000 | 0.000
8508 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 19 | 8760533 | Improve intersection lighting along the Bronx River Parkway in Westchester County. The intersections include Virginia Road, Parkway Holmes Road, Fisher Lane, Old Tarrytown Road, and Strathmore Road. | Other | 2009-08-17 | 2009-08-17 | 2010-06-30 | 2010-07-31 | 320294 | 0.000
8509 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760543 | Upgrade 60 traffic signals at select locations in Westchester County. | Other | 2009-08-17 | 2009-08-17 | 2010-06-30 | 2010-07-31 | 301001 | 0.000
8510 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760553 | Install an automated traffic management system on the Bronx River Parkway in Westchester County. The new system will include in-pavement vehicle detectors capable of monitoring traffic volume and spee | Other | 2009-08-17 | 2009-08-17 | 2009-12-31 | 2010-07-31 | 579151 | 0.000
8511 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760563 | Replace guide rail at select locations in Westchester County. | Other | 2009-08-17 | 2009-08-17 | 2010-01-29 | 2010-07-22 | 862118 | 0.000
8512 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760573 | A project to paint 10 local bridges at select locations throughout Rockland County. | Bridge Improvement | 2010-03-18 | 2010-03-18 | 2010-09-29 | 2010-09-29 | 831565 | 0.000
8513 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760583 | Replace roadside guiderail at select locations on local roadways throughout Rockland County. | Other | 2009-09-23 | 2009-09-23 | 2010-10-08 | 2010-10-08 | 600395 | 0.000
8514 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760593 | Upgrade and modernize existing traffic and pedestrian signal equipment in the City of Yonkers, Westchester County. | Safety/Traffic Management | 2009-09-23 | 2009-09-23 | 2010-07-02 | 2010-08-31 | 865904 | 0.000
8515 | Underway | C230 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760623 | A project to rehabilitate Creek Road pavement from the Poughkeepsie city line to Cottage Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 2010-04-07 | 2010-04-07 | 2011-01-31 |  | 1494986 | 0.000
8516 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760653 | Rehabilitate the pavement along Buckingham Avenue from East Cedar Street to Fulton Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2009-12-31 | 2010-10-26 | 238421 | 0.000
8517 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760663 | Rehabilitate the pavement along Fairview Avenue from the Poughkeepsie city line to Fulton Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 2010-04-07 | 2010-04-07 | 2010-10-26 | 2010-10-26 | 617000 | 0.000
8518 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 19 | 8760683 | Orange County Paving | Pavement Improvement | 2010-02-23 | 2010-02-23 | 2011-10-03 |  | 2641829 | 0.000
8519 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 19 | 8760803 | A project to repave Peenpack Trail in the Town of Deerpark, Orange County. | Transportation Enhancements | 2009-12-21 | 2009-12-21 | 2011-10-03 | 2010-09-10 | 310140 | 0.000
8520 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 22 | 8760813 | Paint 20 bridges at select locations throughout Orange County. This preventative-maintenance project will enhance the bridges structural integrity. | Bridge Improvement | 2010-05-03 | 2010-05-03 | 2010-07-22 | 2010-07-22 | 655283 | 0.000
8521 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760833 | Resurface select local roadways throughout the Town of Clarkstown, Rockland County. | Pavement Improvement | 2009-10-07 | 2009-10-07 | 2010-09-30 | 2010-03-19 | 618689 | 0.000
8522 | Underway | C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760843 | A sidewalk/pedestrian improvement project throughout the city of Rye in Westchester County. Includes work on sidewalks, pedestrian signals, and curb cuts. | Safety/Traffic Management | 2010-03-22 | 2010-03-22 | 2011-01-31 |  | 678000 | 0.000
8523 | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760853 | A pavement rehabilitation project on Sheafe Road, from South Road to Channingville Road, in the town of Poughkeepsie. | Pavement Improvement | 2010-04-07 | 2010-04-07 | 2011-10-03 | 2010-07-20 | 761784 | 0.000
8524 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8780383 | Construction of Sidewalks along Route 44/55 in Gardiner | Transportation Enhancements | 2010-02-02 |  | 2012-03-30 |  | 893000 | 0.140
8525 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 22 | 8780423 | $2.4 million in ARRA funding for an enhancement project to construct a single-shaft elevator and a stairway from ground level to the Walkway Over the Hudson bridge near Water Street in the city of | Transportation Enhancements | 2009-07-16 |  | 2010-12-31 |  | 2400000 | 0.000
8526 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | POUGHKEEPSIE-NEWBURGH |  | 8809883 | Paint the steel superstructure of four bridges and provide localized, spot painting on 57 other bridges along Interstate 84 in Dutchess, Putnam, and Orange counties. This preventative-maintenance proj | Bridge Improvement | 2010-08-06 | 2010-08-06 | 2011-08-31 |  | 1870000 | 0.000
8527 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8810893 | Provide much-needed general maintenance of 18 bridges along Interstate 684 in Westchester County, helping to extend the service life of the structures. | Bridge Improvement | 2009-06-30 | 2009-06-30 | 2011-09-09 | 2011-09-09 | 14958837 | 0.000
8528 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | STATEWIDE |  | 8810903 | Repave approximately 18 miles of state roadway in Columbia, Dutchess and Putnam counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2011-04-12 | 2009-12-28 | 5493732 | 11.120
8529 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 8810993 | Repave approximately 22 miles of state roadway in Orange and Ulster counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings to | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-09-23 | 2010-01-15 | 4398529 | 10.060
8530 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 8811003 | Repave approximately 34 miles of state roadway in Westchester and Rockland counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement marki | Pavement Improvement | 2009-06-10 | 2009-06-10 | 2010-05-12 | 2009-12-18 | 5680674 | 14.370
8531 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 19 | 8811123 | Pavement Resurfacing on the Taconic State Parkway Southbound | Pavement Improvement | 2009-09-18 | 2009-09-18 | 2010-09-14 | 2010-05-17 | 4099359 | 3.300
8532 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | Multiple | 8811283 | A preventative maintenance project in Dutchess County on Rt 44/55 AND RT 9G. | Pavement Improvement | 2010-02-25 | 2010-02-25 | 2011-01-31 | 2010-12-31 | 5480000 | 7.170
8533 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8811293 | Repave approximately four miles of Route 28 between Route 212 and Route 214 in the Town of Shandaken, Ulster County. The top layer of worn, deteriorated pavement will be removed and replaced with new | Pavement Improvement | 2009-07-23 | 2009-07-23 | 2010-03-04 | 2009-10-15 | 1406523 | 3.430
8534 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 22 | 8811303 | Rebuild existing sidewalks and curb ramps along South Street from Dubois Street to Liberty Street in the City of Newburgh, Orange County. The project will improve pedestrian access and safety. | Safety/Traffic Management | 2009-11-11 | 2009-11-11 | 2010-09-30 | 2010-11-05 | 317000 | 0.240
8535 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8811363 | A pavement resurfacing project on Rt 28 from Route 375 to Route 28A and Route 214 to Delaware County line in towns of Hurley, Olive, and Shandaken. | Pavement Improvement | 2010-03-10 | 2010-03-10 | 2011-08-16 | 2010-11-03 | 8250000 | 22.900
8536 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9009253 | A TEP pedestrian safety project along State Route 7 in the town of Cobleskill, Schoharie County. The project will add new sidewalks, bicycle facilities, crosswalks, traffic signals, and a landscaped m | Transportation Enhancements | 2011-09-09 | 2011-09-09 | 2011-11-30 |  | 1403841 | 0.500
8537 | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9009273 | A TEP project to construct new pedestrian facilities and a scenic overlook to provide pedestrian access to the waterfront in the village of Hancock, Delaware County. | Transportation Enhancements | 2009-06-18 |  | 2012-10-15 |  | 564000 | 0.570
8538 | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | SULLIVAN |  | 22 | 9009283 | A TEP project to construct pedestrian facilities in the village of Monticello, Sullivan County. The project will include repairing existing sidewalk and building new sidewalk to connect residential ar | Transportation Enhancements | 2010-11-30 | 2010-11-30 | 2011-07-27 | 2011-07-27 | 333205 | 0.500
8539 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME |  | 22 | 9009293 | Construct a new multi-use trail between Main St. and Castle Gardens in the Town of Vestal, Broome county. | Transportation Enhancements | 2009-07-01 |  | 2013-06-17 |  | 1803000 | 0.000
8540 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9014463 | This project will use a Mill and Fill treatment to resurface this section of Route 206 in the Town of Walton. | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2010-11-30 | 2010-10-23 | 1075000 | 4.330
8541 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9028103 | This project will resurface sections of Rtes. 23 and 30 in the Village of Grand Gorge | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2010-11-30 | 2010-10-28 | 135000 | 0.710
8542 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | TIOGA | BINGHAMTON | 22 | 9038193 | Resurface State Route 434 from the Court Street Bridge to the eastern intersection with Marshland Road in the Village and Town of Owego, Tioga County. This project will improve 11 miles of pavement, r | Pavement Improvement | 2009-09-30 | 2009-09-30 | 2010-08-26 | 2010-08-26 | 5255867 | 11.080
8543 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TIOGA | BINGHAMTON | 24 | 9067323 | Resurface State Route 17 between Pumpelly Creek in the Village of Owego and the Broome County line in the Town of Owego, Tioga County.The top layer of 42 miles of worn, deteriorated pavement will be r | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2010-08-13 | 2010-08-13 | 8047442 | 10.590
8544 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TIOGA |  | 22 | 9067333 | Resurface State Route 17 between the Chemung County Line and Sackett's Creel in the Village of Waverly and towns of Barton and Nichols, Tioga County. This project will improve 40 miles of pavement, re | Pavement Improvement | 2009-09-04 | 2009-09-04 | 2010-07-21 | 2010-07-21 | 5579038 | 10.000
8545 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | BROOME |  | 22 | 9067343 | Resurface 18 miles of State Route 17 in the Town of Windsor in Broome County. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-05-28 | 2010-05-28 | 1815137 | 4.460
8546 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9125083 | This project will resurface this section of Rtes. 30A and 20 to restore the riding surface in the Town of Esperance. | Pavement Improvement | 2010-06-10 | 2010-06-10 | 2010-08-20 | 2010-06-16 | 207659 | 1.830
8547 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9358093 | Rehabilitate approaches to seven bridges carrying Interstate 88 in Schoharie County. Guide rail will also be improved at these locations. | Bridge Improvement | 2009-07-28 | 2009-07-28 | 2010-10-13 | 2010-10-13 | 2165328 | 0.000
8548 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | CHENANGO |  | 24 | 9752543 | Replace the bridge carrying County Route 34 over Johnson Creek in the Town of Norwich, Chenango County. | Bridge Replacement | 2009-09-14 | 2009-09-14 | 2010-06-15 | 2010-06-15 | 921802 | 0.000
8549 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753413 | Paint the bridge carrying County Route 48 over the Susquehanna River in the Town of Vestal and Village of Endicott, Broome County. | Bridge Improvement | 2010-04-13 | 2010-04-13 | 2010-06-29 | 2010-06-18 | 2535000 | 0.000
8550 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753423 | Rehabilitee the bridge carrying Arch Street over the Norfolk-Southern Railroad in the Village of Johnson City, Broome County. | Bridge Improvement | 2009-09-30 | 2009-09-30 | 2010-10-14 | 2010-02-17 | 72811 | 0.000
8551 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753433 | A project to culvert replacement project on Barlow Road over Acre Creek in the Town of Kirkwood, Broome County. | Other | 2010-05-01 | 2010-05-01 | 2010-08-11 | 2010-06-30 | 207000 | 0.000
8552 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | TIOGA | BINGHAMTON | 24 | 9753443 | Replace the bridge carrying South side Drive over Pumpelly Creek in the town and village of Owego, Tioga County. | Bridge Replacement | 2010-04-15 | 2010-04-15 | 2010-11-17 | 2010-11-17 | 1500000 | 0.000
8553 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME |  | 22 | 9753453 | A project to replace the bridge carrying Mason Road over Tracey Creek in the Town of Vestal, Broome County. | Bridge Replacement | 2010-02-11 | 2010-02-11 | 2010-08-12 | 2010-10-30 | 560000 | 0.000
8554 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME |  | 22 | 9753463 | Resurface County Route 44, Vestal Road, from Jensen Road to Orchid Street in the Town of Vestal, Broome County. | Pavement Improvement | 2010-03-05 | 2010-03-05 | 2010-09-01 | 2010-06-02 | 346000 | 0.000
8555 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753473 | Resurface Main Street from Front Street to the western city line in the City of Binghamton, Broome County. | Pavement Improvement | 2009-09-30 | 2009-09-30 | 2009-11-23 | 2009-12-03 | 734602 | 1.670
8556 | Underway | C200 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753483 | A project to resurface Vestal Avenue from the Vestal-Endicott Bridge to East Main Street in the Village of Endicott, Broome County. | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-08-06 |  | 51542 | 0.000
8557 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9753493 | Resurface approximately one mile of County Route 7 from the Sullivan County line to Beaver Kill Road in the Town of Colchester, Delaware County. | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2009-07-30 | 2009-09-24 | 330050 | 0.950
8558 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9753503 | Resurface County Route 21 from Leland Hull Road to Oak Hill Road in the Town of Franklin, Delaware County. | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2010-08-09 | 2010-08-09 | 476995 | 0.000
8559 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CHENANGO |  | 24 | 9753513 | Install new signage on County Routes 5, 10A, 25, 32, 32A, 32B, 33, 34, 35, 36 and 44 in Chenango County. | Safety/Traffic Management | 2009-07-27 | 2009-07-27 | 2010-06-01 | 2009-11-16 | 127758 | 0.000
8560 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 24 | 9753523 | Highway Resurfacing on County Route 31, Springfield Hill Road to Route 20, Town of Springfield. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-08-31 | 2010-09-23 | 331252 | 0.000
8561 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 20 | 9753533 | Highway Resurfacing on County Route 33, Village of Cooperstown to Route 166, Town of Middlefield. | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2009-10-26 | 2009-10-26 | 751843 | 0.000
8562 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SULLIVAN |  | 22 | 9753543 | Paint 22 local bridges in Sullivan County. | Bridge Improvement | 2009-09-17 | 2009-09-17 | 2010-09-01 | 2010-09-01 | 2251241 | 0.000
8563 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 24 | 9753553 | A project to rehabilitate the bridge carrying Spring Street in the Town of Butternuts, Otsego County. | Bridge Improvement | 2010-06-30 | 2010-06-30 | 2010-09-03 | 2010-09-06 | 420000 | 0.000
8564 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9753563 | Repave nearly 10 miles of County Route 1, Mineral Springs Road, in the Town of Richmondville and the Town and Village of Cobleskill, Schoharie County. | Pavement Improvement | 2009-09-23 | 2009-09-23 | 2010-01-29 | 2009-12-31 | 1112996 | 0.000
8565 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SULLIVAN |  | 22 | 9753573 | Replace approximately 132 signs on various county roads in Sullivan County. | Other | 2009-10-20 | 2009-10-20 | 2010-01-07 | 2009-12-18 | 91995 | 0.000
8566 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SULLIVAN |  | 22 | 9753583 | Upgrade five traffic signals in the towns of Fallsburg, Highland, Rockland and Tusten in Sullivan County. | Safety/Traffic Management | 2009-10-12 | 2009-10-12 | 2009-12-23 | 2009-12-23 | 119458 | 0.000
8567 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9753591 | Culvert replacement project on County Route 8 in the Town of Cobleskill, Schoharie County. | Other | 2009-09-23 | 2009-09-23 | 2010-03-18 | 2010-07-30 | 28355 | 0.000
8568 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9753593 | Culvert replacement project on County Route 8 in the Town of Cobleskill, Schoharie County. | Pavement Improvement | 2009-09-23 | 2009-09-23 | 2010-03-18 | 2010-07-30 | 238837 | 0.000
8569 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 24 | 9753643 | A project to resurface East Street from Irving Place to Graduate Avenue in the City of Oneonta, Otsego County. | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-08-12 | 2010-08-11 | 200000 | 0.000
8570 | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 24 | 9753653 | A project to resurface Grand Street from Division Street to Main Street and Division Street from James Georgeson Avenue to Grand Street in the City of Oneonta, Otsego County. | Pavement Improvement | 2010-07-27 | 2010-07-27 | 2010-08-12 | 2010-08-11 | 106000 | 0.000
8571 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9753663 | Rehabilitation of CR 21 in the Town of Franklin | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2010-08-13 | 2010-08-13 | 394524 | 0.000
8572 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CHENANGO |  | 24 | 9753673 | Rehabilitation of CR 44 within the Towns of N. Norwich and Plymouth | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2010-05-19 | 2010-05-19 | 266125 | 0.000
8573 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 23 | 9805603 | Rehabilitate twelve culverts along Interstate 88 in the Towns of Otego, Oneonta, Milford and Maryland, Otsego County. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2010-11-30 | 2010-11-30 | 3038177 | 81.930
8574 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | BINGHAMTON |  | 9805633 | Paint 25 bridges on State Route 17 in Broome and Tioga counties in the towns of Vestal, Candor, Nichols, Barton and the Village of Waverly. The work will be entirely funded by ARRA. Bridge painting he | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2010-11-15 | 2010-11-15 | 7342928 | 0.000
8575 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 9805643 | Replace signage on state highways in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. Signs that are no longer in compliance with federal and state standards will be updated | Safety/Traffic Management | 2009-08-12 | 2009-08-12 | 2010-08-31 | 2010-08-31 | 839624 | 0.000
8576 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9805653 | Bring sidewalks and curbs at select locations in the Town of Union and the villages of Johnson City and Endicott, Broome County, into compliance with Americans with Disabilities Act guidelines. | Safety/Traffic Management | 2009-07-21 | 2009-07-21 | 2009-11-30 | 2010-05-28 | 505195 | 0.000
8577 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 9805663 | Perform bridge maintenance at various locations in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. The projects will be entirely funded by ARRA. This work includes repairs | Bridge Improvement | 2009-08-26 | 2009-08-26 | 2010-10-20 | 2010-10-20 | 1000000 | 0.000
8578 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 9805673 | Perform bridge maintenance at various locations in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. The projects will be entirely funded by ARRA. This work includes repairs | Other | 2009-08-26 | 2009-08-26 | 2010-10-20 | 2010-10-20 | 1084624 | 0.000
8579 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9805713 | Remove hazardous trees in south Delaware County. Removal of these trees will increase safety for the traveling public. | Safety/Traffic Management | 2009-07-23 | 2009-07-23 | 2009-08-07 | 2009-08-07 | 574326 | 0.000
8580 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 9805813 | A project to remove and replace curb ramps and sidewalks that are not in compliance with the Americans With Disabilities Act. | Safety/Traffic Management | 2010-02-12 | 2010-02-12 | 2010-11-18 | 2010-11-18 | 421752 | 0.000
8581 | Underway | C490 | OJT/SS | NEW YORK | STATEWIDE |  |  | CRBU012 | NYSDOT: YOUTH CONSTRUCTION INITIATIVE PROGRAM FROM 09/01/2010 TO 08/31/2011. | Other | 2010-09-15 | 2010-09-15 |  |  | 1354794
8582 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X731303 | A project to improve access on the Staten Island Expressway (I-278) between the Verrazano Narrows Bridge toll plaza and Renwick Avenue in Richmond County. Improvements will include the construction o | Bridge Replacement | 2010-06-24 | 2010-06-24 | 2012-05-22 |  | 39793056 | 1.150
8583 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | X751064 | Rehabilitate the Brooklyn Bridge in Kings and New York counties. The project will repair and widen the ramps leading to the bridge in Brooklyn and Manhattan and the entire bridge will be repainted. Th | Bridge Improvement | 2010-01-29 | 2010-01-29 | 2014-04-22 |  | 30000000 | 0.000
8584 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | QUEENS | NEW YORK-NORTHEASTERN NJ (NJ) | 12 | X770613 | Rehabilitation of the Greenpoint Avenue Bridge over Newton Creek In Kings County. The project will replace deteriorated bridge deck material with a light weight grid deck. Replacement of cracked memb | Bridge Improvement | 2010-04-05 | 2010-04-05 | 2011-02-03 | 2011-02-03 | 2500000 | 0.000
8585 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BRONX | NEW YORK-NORTHEASTERN NJ (NJ) | 16 | X770623 | Painting and maintenance to extend the useful life of Bruckner Expressway Bridges in the Bronx County. | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2011-04-29 | 2011-04-29 | 3500000 | 0.000
8586 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | X770633 | Rehabilitation of 12 concrete and steel bridges in Bronx, Kings, New York , Queens and Richmond counties. The work will include deck overlay, sidewalk improvements, joint sealing, painting, washing, u | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2013-05-06 |  | 2500000 | 0.000
8587 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NEW YORK | NEW YORK-NORTHEASTERN NJ (NJ) | 15 | X770643 | A project to mechanically and electrically rehabilitate the Wards Island pedestrian bridge. | Bridge Improvement | 2010-06-14 | 2010-06-14 | 2012-09-18 |  | 1500000 | 0.000
8588 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | X805933 | Replace sign panels on highway s in Bronx, Kings, New York, Queens and Richmond counties. Approximately 150 overhead and 11 ground-mounted sign panels that are exhibiting deterioration, have lost refl | Safety/Traffic Management | 2009-10-20 | 2009-10-20 | 2011-07-31 | 2011-07-05 | 2206029 | 0.000
8589 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | X806253 | Repair and resurface approximately 45 miles of pavement on highways in Bronx, New York and Queens counties. In Bronx County, work will be done on the Major Deegan Expressway southbound lanes from the | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2012-01-31 |  | 23100670 | 10.850
8590 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X806383 | Park & Ride Lot Expansion at Huguenot Ave, Richmond County | Transportation Enhancements | 2009-10-01 | 2009-10-01 | 2010-10-15 | 2010-08-13 | 1965565 | 0.000
8591 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X806393 | Park & Ride Lot Expansion (Adding 159 Spaces) at Eltingville Transit Center- Richmond County | Other | 2009-09-07 | 2009-09-07 | 2010-09-09 | 2010-10-29 | 2475075 | 0.000
8592 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | X806463 | Repairs to Various State Highway Bridges- Richmond, Kings, Queens, New York and Bronx Counties | Bridge Improvement | 2009-10-20 | 2009-10-20 | 2012-03-13 |  | 8101708 | 0.000
8593 | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | X806533 | THIS PROJECT WILL REPLACE SIGN PANELS, OVERHEAD AND GROUND MOUNTED, IN POOR CONDITION ON STATE HIGHWAYS WITH PANELS CONFORMING TO THE MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES. | Safety/Traffic Management | 2009-12-23 | 2009-12-23 | 2011-04-29 | 2011-03-25 | 1714204 | 18.010
8594 | Underway | C950 | Ferryboat | NEW YORK | RICHMOND |  | 13 | X823343 | A project to rehabilitate and upgrade the Staten Island Ferry terminal and dock to improve safety, efficiency, and reliability. | Other | 2011-04-04 | 2011-04-04 | 2012-02-16 |  | 4000000 | 0.000
8595 | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | BRONX |  | Multiple | XM09063 | Painting of South Bound Bruckner Expressway viaduct and ramps between RFK bridges and Sheridan Expressway to arrest the deterioration of the structure and extend its service life. | Bridge Improvement | 2010-04-14 | 2010-04-14 | 2012-07-03 |  | 20000000 | 0.000
8596 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FRANKLIN |  | Multiple | 0001122 | This project will repave US 1 in Franklin County from Wake County line to NC 56 to improve road condition. Includes TIP project U-5125. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-10-30 | 2010-08-23 | 2072895 | 17.040
8597 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LEE |  | Multiple | 0001123 | This project will repave US 1 in Lee County from US 1 Business to Farrell Road to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-11-20 | 2010-03-29 | 2116024 | 10.220
8598 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MOORE |  | Multiple | 0001124 | This project will add paved shoulders on US 1 in Moore County from Morganton Road to Aiden Road to enhance safety. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-11-20 | 2011-04-20 | 1292031 | 16.370
8599 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | VANCE |  | 02 | 0001133 | This project will repave the following roadways in Vance County to improve road condition: US 1 in Kittrell, US 1/158 Business from Henderson to the Warren County line, NC 39 from Rock Springs Road to | Pavement Improvement | 2009-12-21 | 2010-06-02 | 2010-10-15 | 2011-02-10 | 2000000 | 24.050
8600 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 000S531 | Preliminary engineering to rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for m | Other | 2009-04-29 | 2009-04-29 |  | 2010-03-03 | 325250 | 0.000
8601 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 02 | 000S533 | Construct the Neuse River Greenway in Smithfield which includes a ten foot paved greenway from Wake County Line to Sam's Branch parallel to the Neuse River in Johnston County. This section of greenwa | Transportation Enhancements | 2010-01-19 | 2010-06-16 | 2011-09-21 |  | 1519294 | 3.000
8602 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHOWAN |  | 01 | 000S534 | This project will clean and paint the structural steel on Bridge #26 over US 17 Bypass on SR 1234, Bridge #28 over US17 Bypass on SR 1319, Bridge #27 over NC 32 on US17 Bypass and Bridge #30 over the | Bridge Improvement | 2009-06-15 | 2009-06-15 | 2011-11-04 | 2011-10-27 | 517165 | 0.000
8603 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHOWAN |  | 01 | 000S536 | This project will relocate the lighthouse to a new foundation system, complete required hazardous material abatement, perform structural repairs, historic restoration and stabilization of the lighthou | Transportation Enhancements | 2009-06-15 | 2009-08-17 | 2010-10-06 |  | 841215 | 0.000
8604 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DAVIDSON |  | Multiple | 000S538 | This project will repave the following roadways in Davidson County to improve road condition: NC 62 from NC 109 to the Randolph County line, NC 109 from Denton Road to north of Ben Lee Road, NC 150 f | Pavement Improvement | 2009-05-22 | 2009-05-22 | 2009-11-01 | 2009-12-02 | 1784410 | 13.560
8605 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DAVIE |  | Multiple | 000S540 | This project will repave the following roadways in Davidson and Davie Counties to improve road condition: US 64 from Lake Louise Golf Course to east of the Yadkin River, US 64-601 from US 158 to US 6 | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2009-11-30 | 2010-10-26 | 3211948 | 18.436
8606 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROWAN |  | Multiple | 000S541 | This project will repave various roadways in Rowan County, including the following, to improve road condition: Section of US 52, Section of NC 150, Section of NC 152, Section of NC 801, Sections of 8 | Pavement Improvement | 2009-05-22 | 2009-05-22 | 2009-11-30 | 2011-01-24 | 4454164 | 38.693
8607 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STOKES |  | 05 | 000S542 | This project will repave various roadways in Stokes County, including the following, to improve road condition: US 52 from King City limits to Surry County line, Section of NC 65, Section of NC 66, S | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2009-11-30 | 2011-04-15 | 3222130 | 31.790
8608 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 000S564 | This project will provide for upgrades for traffic signals including the replacement of incandescent bulbs with LED inserts in signal heads, upgrade of undersized signal heads with LED signal heads an | Safety/Traffic Management | 2009-10-19 | 2010-02-12 | 2010-09-30 |  | 532669 | 0.000
8609 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 000S568 | This project will repave Northwest Boulevard and construct sidewalk in Winston-Salem / Forsyth County to improve road condition and provide pedestrian accommodation. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-04-30 |  | 276738 | 0.000
8610 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HARNETT |  | 02 | 000S574 | The project (ER-5100F) will preliminary engineer Roadside Environmental Rehabilitation/Renovation projects in Highway Division 6 (Fayetteville). | Other | 2009-11-01 |  |  |  | 4270 | 0.000
8611 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE |  |  | 000S577 | These funds will provide the preliminary engineering for the project that will renovate the landscape enhancement for the I-85 Rest Area in Davidson County and the I-40/US-52 landscape initiative in F | Other | 2009-08-05 | 2009-08-05 |  |  | 4273 | 0.000
8612 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE |  |  | 000S582 | The project will install landscape enhancement planting in Columbus at the US 74 and I-26 Interchange in Polk County and at the intersection of US 64 and Jones Cove Road in Haywood County. | Transportation Enhancements | 2009-08-20 | 2010-01-12 | 2010-03-26 | 2010-05-25 | 94683 | 0.110
8613 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 000S588 | This project provides for the construction of a 10 foot multi-use asphalt trail including bridge over Jones Creek for the Twin Creeks Park Greenway in Orrange County. This is a locally administered p | Transportation Enhancements | 2009-09-22 | 2010-03-01 | 2010-08-26 |  | 429457 | 0.000
8614 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 000S593 | Rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for motorists. | Bridge Improvement | 2009-08-12 | 2010-04-20 | 2010-08-15 | 2011-07-22 | 4109972 | 0.000
8615 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 000S594 | Rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for motorists. | Bridge Improvement | 2009-11-16 | 2010-06-28 | 2011-09-30 |  | 7031435 | 0.000
8616 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 000S596 | This project will provide alternate fuel vehicles to serve homebound individuals or those with no personal means of transportation while promoting environmental health by reducing carbon emissions in | Other | 2009-11-17 | 2010-04-02 | 2011-10-31 |  | 736989 | 0.000
8617 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 000S597 | This project provides for the purchase of a transit bus fueled by compressed natural gas (CNG), and the construction of a CNG fueling station in Henderson County. | Other | 2009-08-31 | 2010-02-22 | 2010-09-20 |  | 641347 | 0.000
8618 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON |  | 11 | 000S605 | The project will install flowering tree seedlings for reforestation at the following locations: I-26 at US 25 in Henderson County, I-26 at US 74 in Polk County, US 64 from US 74 to NC 141 in Cherokee | Transportation Enhancements | 2009-09-09 | 2009-12-11 | 2010-02-26 | 2010-03-29 | 187531 | 11.370
8619 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 000S610 | The project (U-5195) will upgrade dynamic message signs at various locations in Forsyth county. | Safety/Traffic Management | 2009-12-17 | 2010-03-02 | 2010-10-01 | 2011-03-21 | 500000 | 0.000
8620 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE |  |  | 000S656 | ER-5100R - This Project Will Provide For (Statewide) Special Storm Water Management For Eroding Slopes Across North Carolina. | Transportation Enhancements | 2010-08-26 | 2010-10-28 | 2010-12-30 | 2011-01-04 | 20000 | 0.000
8621 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0011015 | This project will resurface NC 11 Business in Hertford County from NC 11 to the Aulander East City Limits to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2011-01-24 | 264966 | 2.100
8622 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0011017 | This project will resurface NC 11in Hertford County from SR 1130 (Modlin Hatchery Road) southward for 2.6 miles to the Bridge over Ahoskie Creek to improve road condition. | Pavement Improvement | 2010-01-04 | 2010-10-26 | 2011-06-30 | 2011-03-09 | 410604 | 2.600
8623 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0011018 | This project will clean and paint the structural steel on Bridge #39 over the Roanoke River on NC 11 in Martin County to extend the life of the structure. | Bridge Improvement | 2009-11-24 | 2010-03-17 | 2010-12-15 | 2010-10-05 | 400833 | 0.000
8624 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 0011020 | R-5220 - This Project Will Mill And Resurface NC 11/55 From The Neuse River Bridge To The Railroad Tracks in Lenoir County, North Carolina. | Pavement Improvement | 2010-08-05 | 2011-06-22 | 2011-08-19 | 2011-08-05 | 192500 | 0.400
8625 | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HYDE |  | Multiple | 0012036 | This project will resurface NC 12 from the Northern Ferry Dock to Ocracoke Village in Hyde County to improve road condition. Widen paved shoulders to accommodate bicycles will be added on a 3.26 mile | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-08-20 | 2010-08-28 | 2271442 | 12.980
8626 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HYDE |  | Multiple | 0012037 | This project will construct a multi-use asphalt trail adjacent to NC 12 from Ocracoke Village to the National Park Service Campground in Hyde County to enhance pedestrian and bicycle access and safety | Transportation Enhancements | 2009-06-15 | 2009-06-15 | 2010-08-20 | 2011-04-20 | 611594 | 3.100
8627 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | 03 | 0012039 | This project will resurface NC 12 from National Park Service Boundary South of Salvo to 8 miles south of the National Park Service Boundary in Dare County to improve road condition. | Pavement Improvement | 2010-01-12 | 2010-10-05 | 2011-06-11 | 2010-11-19 | 1000000 | 8.000
8628 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0013028 | This project will strengthen and resurface US 13 in Hertford County from SR 1130 (Modlin Hatchery Road) to NC 461 to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-10-30 | 2009-12-18 | 487951 | 4.200
8629 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0013029 | Replace deficient bridges #12 and #25 carrying US 13 over Ahoskie Creek and Ahoskie Creek Overflow in Hertford County. | Bridge Replacement | 2009-04-21 | 2009-04-21 | 2011-10-28 | 2011-10-27 | 3060409 | 0.230
8630 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0013031 | This project will resurface US 13-US 17 from the Roanoke River to Saint Francis Road in Bertie County to improve road condition. | Pavement Improvement | 2009-11-10 | 2010-04-05 | 2010-06-15 | 2010-08-31 | 1048436 | 4.920
8631 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0013032 | This project will level existing pavement and resurface US 13/US 17 in Bertie County from SR 1106( St. Francis Road) to SR 1102 (Pleasant Oak Road) to improve road condition. | Pavement Improvement | 2009-11-10 | 2010-04-05 | 2010-06-15 | 2010-08-31 | 786267 | 3.440
8632 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GREENE |  | 01 | 0013036 | R-5222 - This Project Will Mill and Resurface US 13-NC 903 In Snow Hill From NC 58 To NC 91 And Resurface SR1255 (N.W.Second Street) From US 13-NC 903 To US 258 In Greene County, North Carolina. | Pavement Improvement | 2010-08-16 | 2011-06-13 | 2011-08-19 | 2011-08-07 | 770000 | 1.690
8633 | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GRANVILLE, ORANGE |  | Multiple | 0015020 | This project will repave US 15 in Granville County from Tar River Road south of Oxford to Industry Drive in Oxford to improve road condition. | Pavement Improvement | 2009-11-16 | 2010-08-11 | 2010-10-15 | 2011-04-26 | 3075347 | 8.630
8634 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0015026 | Thie project provides for the construciton of the Morgan Creek Greenway, Phase I, to improve pedestrian access from US 15/501 (Culbeth Road) to Smith Level Road in Orange County. This project is loc | Transportation Enhancements | 2009-10-14 | 2010-03-01 | 2011-03-01 |  | 347488 | 0.000
8635 | Underway | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHATHAM | DURHAM | Multiple | 0015027 | Preliminary engineering for pedestrian enhancements to traffic signals and sidewalks on East and/or the west side of US 15-501 in the Cole Park area north to the Orange County line using the existing | Transportation Enhancements | 2009-06-23 | 2009-07-09 | 2010-06-15 |  | 145077 | 2.338
8636 | Underway | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHATHAM | DURHAM | Multiple | 0015028 | This project will renovate the existing landscape enhancement US 421 & US 64 in Chatham County. | Transportation Enhancements | 2009-06-23 | 2009-07-09 | 2010-06-15 |  | 31563 | 2.338
8637 | Underway | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0015029 | This projet provides for the construction of sidewalk ro increase pedestrain safety and mobility on US 15/501/NC 54 from SR 1902 (Manning Drive) to Old Mason Farm Road in Orange County. This is a loc | Transportation Enhancements | 2009-09-21 | 2010-01-13 | 2010-06-24 |  | 142613 | 0.280
8638 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0015030 | The project (R-5164C) will resurface US 15/501 Business south from NC 98 to US 15/501 Business; US 15/501 Business north from US 15/501 to NC 98, US 15/501 Business from US 15/501 to SR 1361 (Vickers | Pavement Improvement | 2009-12-17 | 2010-05-19 | 2010-09-15 | 2010-12-10 | 960790 | 2.900
8639 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0015031 | The project (ER-5100GE) will provide plantings on US 15/501 at Erwin Road/Europa Drive intersection in Orange county. | Transportation Enhancements | 2009-11-10 |  | 2012-04-30 |  | 43000 | 0.000
8640 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0016045 | This project inlcudes landscaping on NC 16 within construction project limits from South of SR 2948 (Marvin School Road) in Uniton County to South of I-185 in Mecklenburg County to enhance aesthetics | Transportation Enhancements | 2009-04-10 | 2011-02-03 | 2011-03-18 |  | 73664 | 3.350
8641 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION | CHARLOTTE | Multiple | 0016046 | This project includes turning lane radius improvements, traffic signal upgrades and a railroad crossing upgrade in Waxhaw on NC 16 at the NC 75 intersection to improve intersection operations and safe | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2010-09-17 |  | 720744 | 0.000
8642 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILKES |  | 05 | 0016047 | This project will rehabilitate pavement and improve guardrail on NC 16 N from SR 1559 (Old NC 16) to the Ashe County line in Wilkes County to improve road condition and safety. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-31 | 2010-08-23 | 1652051 | 9.350
8643 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ASHE |  | 05 | 0016048 | This project will rehabilitate pavement and improve guardrail on NC 16 from NC 88 to the Virginia line in Ashe County to improve road condition and safety. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-31 |  | 2311563 | 13.125
8644 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0017089 | This project will mill asphalt from existing pavement and resurface US 17 Business in Williamston from NC 125 to 0.7 miles east to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2009-12-02 | 190643 | 0.660
8645 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PERQUIMANS |  | 01 | 0017090 | This project will resurface US 17 in Perquimans County from SR 1101 (Bear Swamp Road) to SR 1302 (Union Hall Road) to improve road condition. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-07-10 |  | 2648375 | 15.400
8646 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER, BRUNSWICK |  | 07 | 0017097 | Construct US 17 Bypass (Future I-140) from NC 87 to US 74-76 in Brunswick County. Route will be a four lane divided freeway to alleviate congestion on surrounding roadways. | New Bridge Construction | 2009-10-13 | 2010-03-29 | 2013-10-15 |  | 14725487 | 6.100
8647 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PASQUOTANK |  | 01 | 0017098 | This project will resurface four sections of the US 17 Bypass of Elizabeth City to eliminate ponding of water on roadway and improve safety conditions.. | Pavement Improvement | 2009-11-24 | 2010-09-14 | 2010-10-01 | 2010-09-24 | 231511 | 2.300
8648 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PASQUOTANK |  | 01 | 0017100 | The project (ER-5100AC) will provide reforestation on US 17 (Elizabeth City Bypass) in Pasquotank county. | Transportation Enhancements | 2009-10-28 | 2010-12-13 | 2010-12-31 | 2010-12-22 | 42000 | 7.400
8649 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROBESON |  | 07 | 0017101 | The project will renovate and improve existing landscape enhancement in Maxton at the NC 71 and I-74 Interchange in Robeson County | Transportation Enhancements | 2009-09-24 | 2010-03-03 | 2010-04-30 | 2010-05-09 | 61654 | 0.000
8650 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PASQUOTANK |  | 01 | 0017104 | ER-5100AE - This project will provide Czip Planting at the US 17 Bypass/US 17 Interchange in Pasquotank County, North Carolina. | Transportation Enhancements | 2010-02-09 |  |  |  | 85500 | 0.000
8651 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PERQUIMANS |  | 01 | 0017105 | The project (ER-5100AF) will repair critical eroding slopes on US 17 in Perquimans county. | Transportation Enhancements | 2009-11-24 |  | 2011-07-30 |  | 138333 | 30.376
8652 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0017106 | B-4576 - Replace Bridge #6 On US 17 Southbound Over Ready Branch in Martin County, North Carolina. | Bridge Replacement | 2010-02-18 | 2010-07-30 | 2011-11-30 | 2011-10-18 | 1185000 | 0.000
8653 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ONSLOW |  | 03 | 0017111 | U-4007B - This project will add additional turn lanes by improving grading, drainage, paving, structures, signal, retaining wall, and culvert extension on Western Parkway from 1300 feet South of Count | Pavement Widening | 2010-09-14 | 2010-12-17 | 2013-09-15 |  | 11421295 | 2.014
8654 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALLEGHANY |  | 05 | 0018014 | This project will add a left turn lane on NC 18 from SR 1173 (Tayson Rd) to SR 1138 (Osborne Rd) and realign Osborne Rd to improve safety and mobility. | Pavement Improvement | 2010-03-15 | 2010-04-07 | 2010-08-15 | 2011-01-24 | 408783 | 0.540
8655 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MONTGOMERY |  | 08 | 0024036 | Widen NC 24-27 in Biscoe / Montgomery County, between US 220A and Future I-73/74, to enhance safety and mobility. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2011-08-01 | 2011-09-29 | 4541752 | 0.909
8656 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MOORE |  | Multiple | 0024037 | This project will widen NC 24-27 in Moore County and add turn lanes, from Montgomery County line to NC 705, to enhance safety and mobility. | Pavement Widening | 2009-03-26 | 2009-03-26 | 2010-06-25 | 2011-05-10 | 3313779 | 9.400
8657 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0024038 | This project will inlcude landscaping in Albemarle within the construction project limits from East of Big Bear Creek to SR 1963 (St. Martin Road) to enhance aesthics when ,otorists enter the Albemarl | Transportation Enhancements | 2009-06-08 | 2010-11-17 | 2010-12-31 | 2011-02-10 | 85580 | 5.800
8658 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0024042 | This project includes resurfacing NC 740 from SR 1730 (Vickers Store Rd) to Island in Stanly County. Milling and resurfacing NC 24/27 from NC 740 to Bird St in Stanly County. Pavement rehabilitation | Pavement Improvement | 2009-11-17 |  | 2010-07-30 | 2011-01-24 | 1919233 | 7.280
8659 | Underway | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DUPLIN, ONSLOW |  | 03 | 0024046 | R-5218 - This Project Will Mill And Resurface NC 24 From NC 24 Business-Kenansville Bypass In Duplin County To US 258 AT Jarman's Fork In Onslow County, North Carolina. | Pavement Improvement | 2010-08-23 | 2010-11-01 | 2012-11-12 |  | 2238256 | 40.710
8660 | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 0025025 | Preliminary engineering for the installation of trees, shrubs, and flowering plants as well as hardscape items and native grasses in Asheville on future I-26, Exit 23, interchange in Woodfin and I-2 | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2011-06-30 | 2011-05-07 | 214051 | 0.000
8661 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | 05 | 0029044 | This project will repair and rehabilitate concrete pavement and shoulders on US 29 in Rockingham County from Guilford County line to Troublesome Creek to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-10-16 | 2011-01-24 | 1712661 | 3.890
8662 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0029045 | Repair bridge expansion joints on 8 structures: Bridge 23 on US 29 Business, Bridge 116 on SR 2600, Bridge 134 on NC 700, Bridge 168 on NC 14/87, Bridge 169 on NC 770, Bridge 124 on SR 2177, Bridge 1 | Bridge Improvement | 2009-07-28 | 2009-12-29 | 2010-05-29 | 2010-03-04 | 109031 | 0.045
8663 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0029046 | The project will install landscape enhancement plantings in Greensboro on US 29 from SR 4240 (Lee Street) to 16th Street in Guilford County. Includes TIP project ER-5100GC. | Transportation Enhancements | 2009-10-22 | 2010-01-26 | 2012-04-30 |  | 181542 | 3.100
8664 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0029047 | Upgrade Electrical Wiring System And Replace Metal Breakaway Poles On US 29 From I-40/I-85 Business To Phillips Avenue In Guilford County, North Carolina | Safety/Traffic Management | 2010-01-22 |  | 2010-12-31 | 2011-07-15 | 488216 | 3.100
8665 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0029048 | The project (U-5202) will upgrade fiberglass poles with metal breakaway poles and install high mast lighting at interchanges on US 29 from Phillips Avenue to north of SR 2835 (McKnight Mill Road) in G | Pavement Improvement | 2009-12-21 |  | 2011-07-31 | 2011-07-18 | 612560 | 1.500
8666 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0035005 | This project will resurface NC 35 in Northampton County from US 158 to SR 1545 (Buck Boone Road) to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-11-13 | 2010-04-21 | 261007 | 2.200
8667 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PERQUIMANS |  | 01 | 0037002 | The project will replace Culvert #6 with a new aluminum culvert for Burnt Mill Creek on NC 37 at the Perquimans/Chowan County Line in Perquimans County. | Bridge Replacement | 2009-08-17 | 2009-08-17 | 2010-07-31 | 2010-09-21 | 337120 | 0.000
8668 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JONES |  | Multiple | 0041030 | R-5224 - This Project Will Widen And Resurface NC 41-58 From The Intersection Of NC 41-58 -SR 1300 (Middle Road) To The Pavement Change In Jones County, North Carolina. | Pavement Improvement | 2010-08-13 | 2011-08-01 | 2011-08-19 | 2011-12-02 | 700000 | 2.000
8669 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | Multiple | 0042020 | This project provides improvements to increase safety and mobility on NC 42 at the intersection with SR 1010 (Cleveland Road) in Johnston County. | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2010-12-14 |  | 760513 | 0.000
8670 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 0043012 | This project adds sidewalks along the southwest side of NC43 in Greenville from US 264A to Red Banks Road in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-08-18 | 2009-09-11 | 2010-04-29 |  | 60090 | 0.500
8671 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CRAVEN |  | 01 | 0043013 | This project will resurface and do minimal widening on NC 43 from US 17 South to Bosch Boulevard in Craven County to improve road condition. | Pavement Improvement | 2009-09-21 | 2010-06-07 | 2010-11-15 | 2011-03-21 | 2349765 | 8.600
8672 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WASHINGTON |  | 01 | 0045004 | This project will replace deficient Bridge #1 over a canal on NC 45/99 0.6 miles north of the Hyde County line in Washington County. | Bridge Improvement | 2009-08-05 | 2009-08-05 | 2010-06-28 | 2010-08-23 | 347334 | 0.000
8673 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0045006 | This project will perform concrete and steel repairs to the bridge supports, replace five leaking construction joints and finger joints at the ends of the bridge span and clean & paint structural ste | Bridge Replacement | 2009-12-21 |  | 2011-06-30 | 2011-02-17 | 1991990 | 0.000
8674 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0048006 | This project will resurface NC 48 in Northampton County from SR 1200 (James Jones Road) to the Gaston East City Limits to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-11-13 | 2010-04-21 | 221144 | 2.660
8675 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PERSON |  | 13 | 0049027 | This project will repave the following roadways in Person County to improve road condition: NC 49 from south of Salem Church Road to Hassell Horton Road, NC 49 from Roxboro southern city limits to US | Pavement Improvement | 2009-11-09 | 2010-08-09 | 2010-11-01 | 2011-01-24 | 1501401 | 8.630
8676 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE | RALEIGH |  | 0050011 | This project will perform a comprehensive Corridor Study on NC 50 From I-540 in Wake County to the City of Creedmoor in Granville County to identify alternatives for easing congestion and managing are | Other | 2009-09-24 | 2010-01-21 | 2010-12-31 |  | 200000 | 0.000
8677 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | 08 | 0051028 | This project will widen NC 51 from the South Carolina state line to SR 3645 (Downs Circle) in Mecklenburg County to improve safety and mobility. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2010-11-24 |  | 5521529 | 1.063
8678 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 0051030 | U-5199 - This project will lengthen the left turn lanes on NC 51 at NC 51 at Fullwood Lane and Monroe Road in Matthews, Mecklenbug county, North Carolina. | Pavement Improvement | 2010-01-21 | 2010-08-19 | 2010-08-27 |  | 205000 | 0.000
8679 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 0052033 | This project will rehabilitate pavement on US 52 from Stokes County line to SR 1815 (Cooke School Rd) in Surry County to improve road condition. | Pavement Improvement | 2009-08-05 | 2009-10-13 | 2010-06-15 |  | 3247234 | 31.960
8680 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STOKES |  | 05 | 0052036 | The project (R-5174A) will overlay existing pavement with an ultrathin bonded wearing course on US from the King city limits to the Surry county line in Stokes county. | Pavement Improvement | 2009-12-17 | 2010-04-01 | 2010-08-15 | 2011-04-19 | 100000 | 9.610
8681 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0052037 | The project (ER-5100JE) will landscape US 52 and NC 24/27/73 interchange in Albemarle, Stanley county. | Transportation Enhancements | 2009-12-15 | 2010-12-20 | 2010-12-31 | 2010-12-31 | 35000 | 0.000
8682 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0052038 | The project (ER-5100JG) will replace Bradford Pear trees on US 52 at various location in Stanley county. | Transportation Enhancements | 2009-12-30 | 2010-11-02 | 2010-12-31 | 2011-02-10 | 50000 | 0.000
8683 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HARNETT | RALEIGH | Multiple | 0055041 | This project will resurface NC 55 from NC 210 to SR 1415 (Rawls Church Raod) to imporve road condition in Harnett County. | Pavement Improvement | 2009-09-09 | 2010-01-27 | 2010-07-16 |  | 335204 | 0.480
8684 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0055042 | This project will add turn lanes on NC 55 in Durham at the Riddle Road intersection to enhance safety and improve mobility. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2009-10-30 | 2011-03-21 | 209254 | 0.000
8685 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0057004 | This project will repave NC 57 and add two foot paved shoulders in Orange County from NC 86 to SR 1544 (Pearson Road) to improve road condition. | Pavement Improvement | 2009-08-04 | 2010-04-05 | 2010-07-30 | 2010-09-10 | 1214026 | 6.340
8686 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CARTERET |  | 01 | 0058011 | Construct the Emerald Isle Bike Path in Emerald Isle which includes a 10 feet multiuse path along NC58 from Black Skimmer Drive (MP 19) to the Regional Beach Access (MP 15) and future site of the new | Transportation Enhancements | 2009-07-16 | 2010-01-04 | 2010-06-30 |  | 420406 | 2.000
8687 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0062008 | Repair bridge expansion joints four (4) structures: Bridge 12 on NC 62, Bridge 109 on SR 2309, Bridge 115 on SR 1154 and Bridge 75 on SR 1158 in Alamance County to extend the life of the structures. | Bridge Improvement | 2009-08-05 | 2009-08-05 | 2010-05-29 | 2010-03-19 | 41333 | 0.000
8688 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0064117 | This project will mill asphalt from existing pavement and resurface US 64 in Martin County from the Jamesville East City Limit to west of Sweetwater Creek to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-10-01 | 2009-12-02 | 3018256 | 19.420
8689 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0064118 | This project will resurface US 64 from Edgecombe County Line to US 64 Alternate in Williamston in Martin County to improve road condition. | Pavement Improvement | 2009-05-06 | 2009-05-06 | 2010-11-15 | 2011-05-03 | 6440404 | 36.800
8690 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TYRRELL |  | Multiple | 0064119 | This project will resurface US 64 in Tyrrell County from the Bridge over the Alligator River westward for 3 miles to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-08-24 | 2009-11-13 | 2010-01-22 | 313642 | 3.000
8691 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 0064120 | This project will repave US 64 and US 264 in Wake and Franklin Counties from US 64 / US 264 interchange to Nash County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-11-01 | 2010-07-27 | 7064073 | 30.920
8692 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALEXANDER |  | 05 | 0064121 | This project will resurface US 64 from NC 90 in Iredell County to NC 90 in Alexander County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-10-16 | 2010-08-23 | 2332896 | 18.120
8693 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH |  | Multiple | 0064122 | This project will resurface US 64 from the Franklin County Line to Winstead Avenue in Nash County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-15 | 2010-08-23 | 3822795 | 46.360
8694 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | EDGECOMBE, NASH |  | Multiple | 0064123 | This project will resurface US 64 from Winstead Avenue in Nash County to the Tar River Bridge in Edgecombe County to improve road condition. | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2009-11-15 | 2010-07-26 | 7800701 | 38.420
8695 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | Multiple | 0064125 | This project will clean and paint the structural steel of Bridge #9 (Old Manns Harbor Bridge) carrying US 64 over Croatan Sound in Dare County to extend the life of the structure. | Bridge Replacement | 2009-06-15 | 2009-06-15 | 2011-11-04 | 2010-12-01 | 3365787 | 0.000
8696 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | Multiple | 0064126 | This project will construct a stormwater wetland at the corner of US64/264 Business and Greenville Street in Manteo, NC in Dare County. This saltwater wetland will be used to treat stormwater runoff | Other | 2009-09-24 | 2009-09-24 | 2010-05-11 |  | 252719 | 0.000
8697 | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | EDGECOMBE |  | 02 | 0064130 | This is the preliminary engineering for the project that will focus efforts to improve enhancement of the landscape at the interchanges US 64 / US 258 and US 64 / McNair Road in Halifax County. | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2010-12-15 | 2010-12-15 | 88754 | 0.000
8698 | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH |  | Multiple | 0064131 | This is the preliminary engineering for the project that will improve the landscape at the interchanges US 64 / Buck Leonard Boulevard and I-95 / NC 481 in Nash and Halifax Counties. | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2010-12-15 | 2010-12-15 | 98712 | 0.000
8699 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0064132 | This project will mill asphalt pavement from US 64 Alt. in Williamston and resurface with new asphalt pavement from SR 1446 (Sycamore St.) to SR 1445 (Main Street) to improve road condition. | Pavement Improvement | 2009-09-24 | 2010-06-17 | 2010-11-30 | 2010-10-05 | 643996 | 2.600
8700 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TYRRELL |  | 03 | 0064135 | This project will provide concrete repairs to the bridge supports and clean & paint the structural steel on Bridge #7 over the Alligator River on US 64 at the Tyrrell/Dare County Line to extend the li | Bridge Improvement | 2009-12-16 | 2010-04-01 | 2011-06-30 | 2011-08-25 | 1268230 | 0.000
8701 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MACON |  | 11 | 0064137 | The project (R-5203) will construct left turn lanes on US 64 at the intersections of SR 1516 (Sanders Road), SF 1517 (Bethel Church Road) and SR 1533 (Walnet Creek Road) in Macon county. | Pavement Improvement | 2009-11-19 | 2009-12-02 | 2010-07-30 | 2010-10-26 | 552931 | 0.611
8702 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TYRRELL, WASHINGTON |  | Multiple | 0064138 | The project (ER-511AD) will provide reforestation using Atlantic White Cedar on US 64 in Washington and Tyrell counties. | Transportation Enhancements | 2009-09-24 | 2010-01-25 | 2010-02-28 | 2010-08-23 | 76486 | 0.000
8703 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0065007 | Replace deficient bridge Number 54 carrying NC 65 over Rock House Creek in Rockingham County. | Bridge Replacement | 2009-11-09 | 2010-02-08 | 2010-11-01 | 2011-04-11 | 1283747 | 0.000
8704 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0068012 | This project will repave, widen and add trun lanes on NC 68 in Guilford County from SR 2011 (Edgefield Road) south of Oak Ridge to NC 65 north of Stokesdale to improve road condition. | Pavement Widening | 2009-07-21 | 2010-04-12 | 2010-07-31 | 2011-01-24 | 1572439 | 4.380
8705 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0068013 | This project provides for improvements at the intersection of NC 68 (Westchester Avenue) and Burton Street of adding turn lanes, revising the signals and improving draininge to increase safety and mob | Pavement Improvement | 2009-09-23 | 2010-01-11 | 2010-11-06 |  | 318603 | 0.000
8706 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0068014 | This project provides for improvements at the intersection of NC 68 (Westchester Avenue) and Clinard Farms Road of adding turn lanes and improving draininge to increase safety and mobility in Guilford | Pavement Improvement | 2009-09-23 | 2010-01-11 | 2010-11-06 |  | 77433 | 0.000
8707 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CLAY |  | 11 | 0069006 | The project (R-5204) will construct a center turn lane and improve access management on NC 69 from north of US 64 to south of SR 1118 in Clay county. | Pavement Improvement | 2010-01-12 | 2010-03-22 | 2011-06-30 | 2011-09-23 | 1512370 | 1.004
8708 | Underway | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 03 | 0070121 | This project will provide improvements to increase safety and mobility on US 70 Business at the SR 1553 (Shotwell Road) intersection in Johnston County. | Pavement Improvement | 2009-07-07 | 2010-03-01 | 2010-04-15 |  | 70134 | 0.000
8709 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0070127 | Repair bridge expansion joints on one (1) structure: Bridge 6 on US 70 in Orange County to extend the life of the structure. | Bridge Improvement | 2009-07-28 | 2010-01-25 | 2010-05-29 | 2010-01-28 | 22410 | 0.000
8710 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0070129 | This project will repave US 70 (Church Street) in Burlington / Alamance County, from SR 1716 (Graham-Hopedale Road) to NC 62 to improve road condition. Includes TIP project R-5175B. | Pavement Improvement | 2009-08-17 | 2010-03-17 | 2010-09-17 | 2011-03-09 | 1897335 | 11.170
8711 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 02 | 0070134 | The project (ER-5100DE) will provide roadside landscape enhancement and establishment on US 70 (Clayton Bypass) in Johnston county. | Transportation Enhancements | 2009-12-28 | 2010-08-06 | 2011-12-15 | 2011-12-14 | 318423
8712 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0070140 | R-5164E - This project will resurface US 70 Business from Buchanan Street to 9th street; US 15-501 from Enterprise Street to NC 751; US 70 Business from Great Jones Street to Main Street; SR 2295 (Sou | Pavement Improvement | 2010-08-23 | 2011-04-01 | 2011-09-02 | 2011-12-01 | 400000 | 7.530
8713 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0073019 | Replace deficient bridge carrying NC 73 over Long Creek in Stanly County. | Bridge Replacement | 2009-03-02 | 2009-03-02 | 2010-12-31 | 2010-12-01 | 3020655 | 0.000
8714 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CABARRUS |  | Multiple | 0073020 | "This project includes construction to repair drainage and pavement issues in Mount Pleasant on NC 73 from east of the City Limits to SR 1411 (Cold Springs Road) as follows: Project 1: Removes the ex | Pavement Improvement | 2009-06-02 | 2009-06-02 | 2010-09-17 | 2011-02-10 | 531623 | 11.004
8715 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 0073021 | Widen NC 73 from US 21 to NC 115 in Mecklenburg County to improve safety and mobility. | Pavement Widening | 2009-09-21 | 2009-09-21 | 2012-11-15 |  | 21684048 | 1.190
8716 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RICHMOND |  | 08 | 0073022 | B-4614 - This project will replace bridge 41 on NC 73 over Naked Creek in Richmond county, North Carolina. | Bridge Replacement | 2010-02-09 | 2010-06-02 | 2010-09-17 | 2011-04-20 | 685046 | 0.000
8717 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CLEVELAND |  | 10 | 0074104 | This project will resurface US 74 from SR 1170 (Lucas Rd) to West Lee in Cleveland County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-02 | 2010-07-26 | 1436373 | 3.066
8718 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SWAIN |  | 11 | 0074105 | This project will rehabilitate pavement on US 74 from SR 1159 (Spring St) to the Jackson County line in Swain County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-12-15 | 2011-03-21 | 6108843 | 9.740
8719 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ANSON |  | 08 | 0074108 | This project will include pavement rehabilitation, paved shoulders, and guardrail on US 74 westbound from beginning of divided highway west of SR 1259 to Union County line in Anson County, improving r | Pavement Improvement | 2009-09-09 | 2010-05-07 | 2010-07-02 | 2010-11-18 | 3002394 | 10.800
8720 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ANSON |  | 08 | 0074109 | The project (U-5196) will mill and surface US 74 from NC 109 to west of North Park Road in Anson county. | Pavement Improvement | 2010-01-07 | 2010-10-28 | 2010-11-15 | 2011-03-23 | 310012 | 1.480
8721 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ANSON, UNION |  | Multiple | 0074110 | The project (ER-5100JF) will replace Bradford Pear trees on US 74 at various locations in Anson and Union counties. | Transportation Enhancements | 2009-12-29 | 2010-10-18 | 2010-12-31 | 2011-02-10 | 75000
8722 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LEE |  | 03 | 0078004 | This project will widen NC 78 in Sanford / Lee County, from Tramway to beyond St. Andrews Road, to enhance safety and mobility. | Pavement Widening | 2009-03-26 | 2009-03-26 | 2010-04-30 | 2011-03-21 | 1939063 | 2.450
8723 | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CASWELL |  | Multiple | 0086008 | This project will repave NC 86 in Caswell County from NC 119 to US 158, including shoulders, to improve road condition. | Pavement Improvement | 2009-08-04 | 2010-07-19 | 2010-08-06 | 2010-11-06 | 1379720 | 7.813
8724 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0086010 | R-5178B - This project will mill, resurface and replace curb and gutter on NC 86 from SR 1010 (Franklin Street) to Cameron Avenue in Chapel Hill, Orange county, North Carolina. | Pavement Improvement | 2009-08-04 |  | 2010-08-13 | 2011-03-21 | 181152 | 0.200
8725 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | 06 | 0087022 | This project provides for the replacement of existing signal poles & mast arms at the NC 87 (Webb Avenue) and Elmira Street intersection to improve road conditions in Alamance County. | Other | 2009-08-05 | 2009-08-05 | 2010-02-16 |  | 2484 | 0.620
8726 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BLADEN |  | 07 | 0087024 | The project (ER-5100FF) will provide Czip planting on NC 87 north from SR 1356 (Pearl Lloyd Road) to SR 1308 (Old NC 20) in Bladen county. | Transportation Enhancements | 2010-01-04 | 2010-05-17 | 2010-06-11 | 2010-06-16 | 45000 | 0.470
8727 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALLEGHANY |  | 05 | 0093003 | This project will rehabilitate pavement on NC 93 from US 221 to SR 1337 (Mt. Carmel Rd) in Alleghany County to improve road condition. This project includes TIP R-5157. | Pavement Improvement | 2009-06-22 | 2009-07-01 | 2010-07-01 | 2011-04-20 | 1208490 | 10.000
8728 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0098025 | This project will repave NC 98 in Durham County from Junction Road to Sherron Road to improve road condition. | Pavement Widening | 2009-05-13 | 2009-05-13 | 2010-05-14 | 2011-05-16 | 732133
8729 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FRANKLIN |  | 02 | 0098026 | This project will repave the following roadways in Franklin County to improve road condition: NC 98 from US 401 to Bunn and US 1A from US 1 to NC 56 in Franklinton. | Pavement Improvement | 2009-11-09 |  | 2010-11-01 |  | 2471341 | 9.830
8730 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CUMBERLAND | FAYETTEVILLE | Multiple | 0100017 | This project will perform grading and construct the bridges on the future I-295 Fayetteville Outer Loop in Cumberland County from Bragg Boulevard to Murchison Road for a four lane divided highway. Pa | Pavement Widening | 2009-04-21 | 2009-04-21 | 2012-07-01 |  | 54501720 | 1.390
8731 | Underway | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JACKSON |  | 11 | 0107011 | The project (R-5202) will widen pavement and shoulders, improve drainage and construct a left turn late on NC 107 at SR 1145 in Jackson county. | Pavement Improvement | 2010-01-06 | 2010-03-22 | 2010-11-01 |  | 2470302 | 0.784
8732 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILKES |  | 05 | 0115005 | R-5159 - This project will widenen and rehabilitate pavement on NC 115 from US 421 to the Iredell county line in Wilkes county, North Carolina. | Pavement Improvement | 2010-02-05 | 2010-05-04 | 2010-11-15 |  | 3749661 | 8.100
8733 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0119003 | This project will repave NC 119 with two foot shoulders in Alamance County from the Mebane north city limits to the Caswell County line to improve road condition. | Pavement Improvement | 2009-11-16 | 2010-03-18 | 2010-05-17 | 2011-03-21 | 1783990 | 9.998
8734 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GRAHAM |  | 11 | 0129002 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 10 over East Buffaloe Creek on US 129 in Graham County to extend the life of the structure. | Bridge Improvement | 2009-10-15 | 2009-10-15 | 2010-09-30 | 2011-03-21 | 992812 | 0.000
8735 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHEROKEE |  | 11 | 0141005 | This project will rehabilitate pavement on NC 141 from US 64 to US 74 in Cherokee County to improve road condition. | Pavement Improvement | 2009-07-08 | 2009-07-08 | 2010-11-15 | 2010-11-23 | 2468528 | 16.220
8736 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0147003 | R-5164D - This project will resurface NC 147 from the concrete/asphalt joint West of Exit 14 (Swift Avenue) to the concrete/asphalt North of Exit 7 (TW Alexander Drive) in Durham County, North Carolin | Pavement Improvement | 2010-08-23 | 2011-03-15 | 2011-11-01 |  | 1040000 | 13.600
8737 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CAMDEN |  | Multiple | 0158040 | This project will widen US 158-NC 34 from East of the Pasquotank River in Elizabeth City to North of Havenwood Road in Camden County from two lanes to multi-lanes to improve traffic operations and im | Pavement Widening | 2009-03-02 | 2009-03-02 | 2011-08-01 |  | 7057343 | 3.855
8738 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | Multiple | 0158042 | This project will perform renovations to the existing buildings at the Kitty Hawk Rest Area on US 158 including replacement of wall tile and plumbing fixtures, addition of an ADA compliant family rest | Pavement Improvement | 2009-05-26 | 2009-05-26 | 2010-03-20 | 2010-10-26 | 312280 | 0.000
8739 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0158043 | This project will resurface US 158 from Halifax County Line to multi-lane section west of Hertford County Line in Northampton County to improve road condition. | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2011-11-15 | 2011-12-14 | 7710316 | 28.190
8740 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0158048 | The project (ER-5100AA) will renovate existing plantings and add additional plant material on US 158 Business from SR 1300 (Wise Store Road) to 0.2 miles east of SR 1335 (Lance Road) and along US 258 | Transportation Enhancements | 2009-10-28 | 2010-04-26 | 2011-05-31 | 2011-05-31 | 78967 | 1.899
8741 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0158049 | ER-5100AB - This project will provide for the installation of enhancement plantings at three ""Welcome to Garysburg"" signs on US 158, US 301 and NC 46 in Northampton county, North Carolina." | Transportation Enhancements | 2010-02-09 | 2010-05-20 | 2011-05-31 | 2011-05-31 | 31969 | 0.000
8742 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ONSLOW |  | 03 | 0172012 | R-5219 - This Project Will Construct Right Turn Lanes On NC 172 and NC 210 Northbound At The Intersection Of The Two Roads In Sneads Ferry, Onslow County, North Carolina | Safety/Traffic Management | 2010-08-08 | 2010-10-04 | 2010-11-10 | 2010-11-10 | 140000 | 0.000
8743 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON |  | 11 | 0176006 | This project will rehabilitate pavement on US 176 from NC 225 to US 25 in Henderson County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-12-15 | 2010-07-26 | 2488322 | 4.980
8744 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RICHMOND |  | 08 | 0177003 | The project will install landscape enhancement plantings at the NC 177 and SR1900 Battlet Dairy Road interchange in Richmond County. | Transportation Enhancements | 2009-09-21 | 2009-11-30 | 2009-02-26 | 2010-02-09 | 20523 | 0.000
8745 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | AVERY |  | Multiple | 0194010 | This project will rehabilitate pavement and widen NC 194 from US 221 to US 19 E in Avery County to improve road condition and safety. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-06-01 | 2011-05-10 | 1030620 | 4.200
8746 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | AVERY |  | 10 | 0194013 | R-2710 - This project will resurface and improve safety by improving grading, drainage, paving, signal and retaining wall on NC 194 from Banner Elk in Avery County to Valle Crucis in Watauga County, N | Pavement Improvement | 2010-08-23 | 2010-11-09 | 2012-06-15 |  | 5740000 | 5.500
8747 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BEAUFORT |  | Multiple | 0207002 | The project (ER-5100BD) will provide picnic tables with shelters, bike rack with concrete pad and concrete trash cans at the Bayview Beach Ferry Terminal in Beaufort county. | Transportation Enhancements | 2009-10-23 |  | 2010-03-15 | 2010-04-13 | 27601 | 0.000
8748 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TRANSYLVANIA |  | 11 | 0215004 | This project will install and revise guardrail on NC 215 from US 64 to the Haywood County line in Transylvania County to improve safety. | Safety/Traffic Management | 2009-05-13 | 2009-05-13 | 2010-08-01 | 2010-07-28 | 2257227 | 16.820
8749 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION |  | Multiple | 0218008 | This project will rehabilitate pavement on NC 218 from east of I-485 to west of US 601 in Mecklenburg and Union Counties to improve road condition. | Pavement Improvement | 2009-06-16 | 2009-07-08 | 2009-09-30 | 2009-12-18 | 1736308 | 6.960
8750 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION |  | Multiple | 0218009 | This project will rehabilitate pavement on NC 218 from east of US 601 to west of NC 205 in Union County to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-10-30 | 2010-12-01 | 3080356 | 10.930
8751 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION |  | Multiple | 0218010 | This project will rehabilitate pavement on NC 218 from east of NC 205 to US 74 in Anson and Union Counties to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-11-20 | 2010-12-01 | 3386116 | 13.650
8752 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION | CHARLOTTE | Multiple | 0218011 | Widening for turn lanes on NC 218 @ NC 205, Also widening for turn lanes on US 601 @ NC 218. | Pavement Widening | 2009-05-07 | 2009-05-07 | 2009-09-30 |  | 567418 | 0.000
8753 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION |  | Multiple | 0218012 | This project will construct three filtration basins and a stormwater wetland for the purpose of treating stormwater runoff, from the intersection of US 601 and NC 218 in Union County, before dischargi | Other | 2009-09-15 | 2009-09-15 | 2010-02-15 | 2010-03-01 | 138349 | 0.000
8754 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0220041 | This project will repave US 220 in Rockingham County from NC 135 to the Virginia State line to improve road condition. Includes TIP project R-5180 | Pavement Improvement | 2009-09-08 | 2010-08-02 | 2010-09-24 | 2011-05-25 | 2870657 | 18.640
8755 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RANDOLPH |  | 06 | 0220044 | Landscape Planting Renovation on US 220 At US 64 And SR 1713 (Albemarle Road) Interchanges In Randolph County, North Carolina | Transportation Enhancements | 2009-10-29 | 2010-02-09 | 2010-03-31 | 2010-04-08 | 126142 | 0.000
8756 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 0224013 | Perform grading and construct the bridges on C. Felix Harvey Parkway in Lenoir County from US 70 to US 258 for a four lane divided highway. Paving contract will be done as a separate project in the f | New Construction | 2009-05-08 | 2009-05-08 | 2012-08-01 |  | 42926208 | 0.000
8757 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CRAVEN |  | Multiple | 0229010 | The project (ER-5100BA) will implement plantings at the intersections of US 70 and Pembroke Avenue, Glenburnie Avenue, NC 41 AND US 17; intersection of NC 43 Bypass and NC55, Broad Street median; and | Transportation Enhancements | 2009-09-21 | 2010-02-22 | 2010-12-31 | 2010-12-22 | 264130 | 0.000
8758 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 0240002 | Rehabilitate pavement on I-240 from US 70 to I-40 in Buncombe County to improve road condition. | Pavement Improvement | 2010-01-13 | 2010-03-29 | 2011-09-15 | 2011-10-25 | 1000000 | 5.930
8759 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 0240003 | This project will construct three filtration basin systems for treating stormwater runoff, from I-240, near mile marker 6, just west of Chuns Cove Road, in Asheville, NC before discharging to Ross Cre | Other | 2009-11-05 | 2010-04-16 | 2010-07-02 | 2010-07-02 | 291849 | 0.000
8760 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 0241004 | R-5221 - This Project Will Mill, Resurface and Widen NC 241 Two (2) Feet From NC 11 In Pink Hill To End of Curb And Gutter in Duplin County Line In Lenoir County, North Carolina. | Pavement Improvement | 2010-08-05 | 2011-03-11 | 2011-08-19 | 2011-04-20 | 455000 | 1.470
8761 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0258015 | This project will mill asphalt from existing pavement and resurface US 258 from Roanoke River to NC 305 in Northampton County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-11-01 | 2010-01-22 | 1034928 | 7.450
8762 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GREENE |  | 01 | 0258017 | This project will resurface and do minimal widening on US 258 from Contentnea Creek to NC 123 in Greene County to improve road condition. | Pavement Improvement | 2009-09-21 | 2010-08-24 | 2010-11-15 | 2011-04-07 | 1269268 | 4.000
8763 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PAMLICO |  | 03 | 0259002 | The project (ER-5100BC) will provide picnic tables with shelters, bike rack with concrete pad and concrete trash cans at the Minnessott Beach Ferry Terminal in Pamlico county. | Transportation Enhancements | 2009-10-23 | 2010-02-23 | 2010-03-15 | 2010-04-13 | 28176 | 0.000
8764 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 0261083 | Mill areas where potholes, cracking and/or delamination of the asphalt surface has occurred and resurface to promote the life of the roadway surface on I-26 from mile post 31 to mile post 37 in Buncom | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2010-09-30 | 2011-07-22 | 7208169 | 5.360
8765 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | POLK |  | 11 | 0261085 | This project provides for preconstruction activities to rehabilitate the pavement on I-26 from milepost 61 to milepost 71 in Polk County to improve road condition. | Pavement Improvement | 2009-07-08 | 2009-07-08 | 2010-09-30 | 2011-04-29 | 7011743 | 27.570
8766 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | Multiple | 0264039 | This project will resurface US 264 in Dare County from SR 1100 (Stumpy Point Road) to the Navy Range to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2010-01-22 | 350033 | 2.870
8767 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 0264042 | This project adds an additional turn lane on US 264 in Greenville at the intersection of Stantonsburg Road and Arlington Blvd in Pitt County to ease congestion and improve safety. This is a locally a | Pavement Widening | 2009-08-18 | 2009-09-08 | 2010-05-14 |  | 5097 | 0.000
8768 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILSON |  | Multiple | 0264043 | This project will resurface US 264 from NC 58 to the Greene County Line in Wilson County to improve road condition. | Pavement Improvement | 2009-09-09 | 2010-08-05 | 2010-11-01 | 2011-06-09 | 4016081 | 16.400
8769 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH, WILSON |  | Multiple | 0264045 | This project will resurface US 264 from the Wake County Line to US 264 Alternate in Nash and Wilson Counties to improve road condition. | Pavement Improvement | 2009-11-10 | 2010-04-17 | 2010-10-01 | 2010-10-29 | 3213406 | 25.800
8770 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 0264046 | The project (ER-5100BB) will provide tree planting on US 264 and US 258 in Farmville, Pitt county. | Transportation Enhancements | 2009-11-02 | 2010-03-15 | 2010-12-15 | 2010-11-23 | 110231 | 0.000
8771 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BEAUFORT |  | Multiple | 0264048 | R-5223 - This Project Will Widen And Resurface US 264 From SR 1718 (Yeatesville Road) To SR 1714 (Seed Tick Neck Road) In Beaufort County, North Carolina. | Pavement Widening | 2010-08-23 | 2011-04-18 | 2011-08-19 | 2011-09-16 | 770000 | 2.100
8772 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | 09 | 0274007 | This project will widen NC 274 from SR 1484 (Maine Ave) to NC 275 in Gaston County to improve safety and mobility. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2011-07-01 | 2011-11-21 | 5450259 | 1.261
8773 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TRANSYLVANIA |  | 11 | 0276008 | This project will rehabilitate pavement and install paved shoulders on US 276 from Pisgah Forest to Brevard in Transylvania County to improve road condition and safety. | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2010-05-15 | 2010-10-26 | 2040315 | 6.768
8774 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0305001 | This project will mill asphalt from existing pavement, overlay with an asphalt surface treatment (mat & seal) and resurface the pavement of NC 305 NC 305 from US 13 to NC 11 in Bertie County to improv | Pavement Improvement | 2009-05-06 | 2009-05-06 | 2010-07-01 | 2010-09-16 | 1977315 | 12.450
8775 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0308004 | This project will resurface NC 308 in Windsor from King Street to Sterlingworth Street to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2011-01-24 | 92507 | 0.270
8776 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0308005 | This project will resurface NC 308 in Bertie County from the Kelford East City Limits to the Kelford West City Limits to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2011-01-24 | 132297 | 1.000
8777 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0308006 | This project will resurface NC 308 in Bertie County from SR 1119 (Jack Branch Road) to SR 1247 (Mount Olive Road) to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2011-01-24 | 158601 | 1.720
8778 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0311026 | This project includes the preparation of an environmental document for the replacement of the interchange at US 311 & NC 68 in High Point in Guilford County. This is a locally administered project by | Other | 2009-08-18 | 2009-08-21 | 2012-04-01 |  | 475000 | 0.000
8779 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0311027 | This project will modify two existing hazardous spill basins and construct a linear filtration basin to collect the runoff from the bridge over the Oak Hollow Reservoir located on US-311/SR-1979 in Gu | Other | 2009-11-04 |  | 2010-10-30 | 2011-07-13 | 68568 | 0.000
8780 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CALDWELL |  | 10 | 0321020 | This project will rehabilitate pavement on US 321 from SR 1178 (Hibriten Dr SE) to city limits of Lenoir in Caldwell County to improve road condition. | Pavement Improvement | 2009-06-01 | 2009-08-31 | 2009-10-30 | 2011-01-24 | 478748 | 2.320
8781 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CATAWBA |  | 10 | 0321021 | The project (ER-5100LB) will provide reforestation of trees on US 321 northbound and southbound from the lincoln county line to the NC 127 interchange in Catawba county. | Transportation Enhancements | 2009-10-28 | 2010-02-10 | 2011-04-29 | 2010-03-25 | 55000 | 23.722
8782 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER |  | 07 | 0332034 | This project will construct a 0.6 mile long asphalt multi-use path in Wilmington along South 17th Street between the Cameron Art Museum and Halyburton Park and an 0.2 mile long asphalt multi-use path | Transportation Enhancements | 2009-08-03 | 2010-02-01 | 2010-07-01 |  | 300180 | 0.000
8783 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER |  | 07 | 0332035 | This project will construct a 2.6 mile long asphalt multi-use path in Wilmington between Randall Parkway and Converse Road, parallel to Rosemont Avenue, Caswell Street, Park Avenue and Independence Bo | Transportation Enhancements | 2009-05-28 | 2010-03-01 | 2010-09-01 |  | 1620000 | 0.000
8784 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER |  | 07 | 0332039 | EB-5118CA - This project Will Construct Phase III of the Wilmington Cross-City Trail, A Multi-Use Path Between South College Road And The Autumn Hall Mixed Use Development In Wilmington, New Hanover C | Transportation Enhancements | 2010-09-23 | 2011-02-17 | 2011-08-16 |  | 1362267 | 0.000
8785 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 0401200 | This project will improve drainage and?complete minor landscape improvements to the I-40 west bound rest area building in Haywood County at MM 10. | Transportation Enhancements | 2009-07-27 | 2010-01-26 | 2010-03-26 | 2010-05-25 | 25444 | 0.350
8786 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 0401204 | Rehabilitate pavement on I-40 from SR 2838 (Exit 55) to mile post 67 in Buncombe County to improve road condition. | Pavement Improvement | 2009-11-17 | 2010-02-01 | 2010-10-30 | 2011-07-22 | 8340778 | 11.720
8787 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0401206 | Widen US 401 in Wake County between Neuse River and Louisburg Road near Rolesville, to enhance safety and mobility. | Pavement Widening | 2009-11-09 | 2010-02-19 | 2011-12-31 | 2011-12-06 | 9917986 | 3.695
8788 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 0401210 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 124 over SR 1338 ON I-40 in Haywood County to extend the life of the structure. | Bridge Improvement | 2009-10-15 | 2009-10-15 | 2010-01-31 | 2010-10-05 | 720385 | 0.000
8789 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 0401211 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 205 over SR 1364 ON I-40 in Haywood County to extend the life of the structure. | Bridge Improvement | 2009-10-28 | 2009-11-20 | 2010-01-31 | 2010-10-05 | 407385 | 0.000
8790 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 0401212 | The project (I-5140) will replace six dynamic message signs on Interstate 40 at milepost 33.4 (east and westbound), milepost 28.7 (east and westbound), milepost 21 (westbound), and milepost 0.7 (eastb | Safety/Traffic Management | 2009-11-02 | 2010-02-22 | 2010-08-27 |  | 672744 | 0.000
8791 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BURKE |  | 10 | 0402142 | This project will resurface the roadway with an asphalt microsurface (a thinner yet extremely durable treatment) to extend the life of the road and provide improved rideability on I-40 from mile post | Pavement Improvement | 2009-04-16 | 2009-04-17 | 2010-10-29 | 2011-03-30 | 9583890 | 23.830
8792 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CATAWBA |  | 10 | 0402146 | This project will renovate the existing pair of?rest area?buildings located on I-40, west of Claremont into vending,?security offices?and storage, construct a new pair of restroom buildings with dual | Pavement Improvement | 2010-01-13 | 2010-03-30 | 2011-04-01 | 2011-06-10 | 1408843 | 0.000
8793 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BURKE |  | 10 | 0402149 | ER-5100MB - This project will provide sod seeding and tree plantings on I-40 from milepost 95 to milepost 119 in Burke county, North Carolina. | Transportation Enhancements | 2010-01-21 | 2010-05-24 | 2011-05-03 | 2011-05-03 | 176000 | 2.010
8794 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MCDOWELL |  | 11 | 0402150 | K-4909 - This project will renovate rest area pair, including grounds, parking facilities and buildings to include dual restrooms and ADA compliant family restrooms on I-40 in McDowell County, North C | Transportation Enhancements | 2010-07-15 | 2010-10-01 | 2011-09-30 |  | 1905285 | 0.000
8795 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | IREDELL |  | Multiple | 0402154 | ER-5100LD - This Project Will Provide For Interchange Enhancement Plantings On I-40 At Exits 148 and 150 In Iredell County, North Carolina. | Transportation Enhancements | 2010-08-23 | 2010-12-13 | 2011-01-31 | 2011-03-08 | 100000 | 0.000
8796 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0403122 | Resurface I-40 from Clemmonsville Road to US 311 in Winston-Salem / Forsyth County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-09-15 | 2010-05-25 | 1786443 | 3.500
8797 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 0403123 | Resurface I-40/85 from Rock Creek Dairy Road in Guilford County to University Drive in Alamance County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-10-30 | 2010-04-21 | 4416766 | 8.294
8798 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0403124 | Resurface I-40 from Harper Road to Jonestown Road in Forsyth County to improve road condition. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-06-15 | 2010-10-05 | 3107926 | 9.200
8799 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 0403125 | Replace damaged/missing reflectors in pavement lane markers on I-40/85 in Guilford County, between I-40 and I-85 junction east of Greensboro to beyond Mount Hope Church Road, to improve nighttime visi | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2010-05-01 | 2010-10-26 | 28638 | 2.000
8800 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0403126 | The project will install landscape enhancement in Burlington at the interchange of I-40/85 and SR 1226 (University Drive) in Alamance County. | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2011-12-15 |  | 120000 | 0.000
8801 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0403127 | The project will renovate multiple landscape beds in Winston Salem along I-40 and install flowering trees along US-52 in Forsyth County. | Transportation Enhancements | 2009-12-04 | 2009-12-10 | 2011-03-31 | 2011-02-14 | 507010 | 22.060
8802 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0403128 | The project (ER-5100GG) will provide landscape rehabilitation on Interstate 40/Interstate 85 at the NC 87 interchange in Alamance county. | Transportation Enhancements | 2009-12-21 | 2010-03-01 | 2012-05-28 |  | 67999 | 0.000
8803 | Completed | C250,C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SAMPSON, DUPLIN |  | Multiple | 0405052 | Resurface I-40 from east of Newton Grove in Sampson County to east of Warsaw in Duplin County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2010-11-15 | 2011-07-21 | 13541125 | 41.760
8804 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 02 | 0405053 | This projects provides for the resurfacing of I-40 from west of Morgan Road to the Sampson County Line in Johnston County to improve road condition. | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2010-11-15 | 2010-10-05 | 2647220 | 22.000
8805 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DUPLIN |  | 03 | 0405054 | The project (I-5001A) will repave Interstate 40 from milepost 369.4 in Duplin county to milepost 389.5 in Pender county to improve road condition. | Pavement Improvement | 2009-12-16 | 2010-02-08 | 2011-05-31 |  | 1000000 | 40.180
8806 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER, SAMPSON, DUPLIN, PENDER |  | Multiple | 0405055 | The project (ER-5100CA) will provide wildflower seeding and mulching on Interstate 40 in New Hanover, Pender, Duplin and Sampson counties. | Transportation Enhancements | 2009-10-09 | 2010-02-08 | 2010-04-02 | 2010-03-16 | 160788
8807 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAYNE |  | Multiple | 0414004 | This project will install a computerized central signal system in the City of Goldsboro to synchronize the traffic signals to improve traffic flow. | Safety/Traffic Management | 2009-08-05 | 2009-08-05 | 2012-02-01 |  | 3622986 | 0.000
8808 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WATAUGA |  | 05 | 0421047 | This project will widen US 421 (King Street) from NC 194 to US 321 in Watauga County to improve safety and mobility. | Other | 2009-05-06 | 2009-05-06 | 2011-12-31 |  | 15861069 | 1.098
8809 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LEE |  | 02 | 0421050 | Construct section of Sanford Bypass between NC 42 and NC 87 south of Sanford, to reduce congestion and improve mobility. | New Construction | 2009-11-09 | 2010-02-22 | 2012-11-15 |  | 27757178 | 0.000
8810 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0421053 | This project will repave US 421 in Guilford County from the Randolph County line to north of SR 3485 (Harmont Drive) to improve road condition. | Pavement Improvement | 2009-10-13 | 2010-03-08 | 2010-09-03 | 2011-03-21 | 2994071 | 19.920
8811 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHATHAM |  | Multiple | 0421055 | The project (ER-5100HC) will provide landscape renovation planting and plant bed restoration on US 421 at US 64 and US 421 at SR 1362 (Piney Grove Church Road) in Chatham county. | Transportation Enhancements | 2009-10-23 | 2010-01-30 | 2010-03-31 | 2010-03-31 | 96361 | 0.000
8812 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0421057 | The project (U-5144B) wil mill, rehabilitate pavement and resurface two lanes northbound and two lanes southbound of US 421 from pavement joint at the ramps at Lesisville to the Yadkin county line in | Pavement Improvement | 2009-12-17 | 2010-05-09 | 2010-09-30 | 2011-01-24 | 500000 | 8.186
8813 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILKES |  | 05 | 0421058 | The project (ER-5100KA) will provide reforestation and manual clearing on US 421 From SR 1765 (Unifi Industrial Road) in Yadkin County to the Boome Town limits in Wataugh County in Wilkes County. | Transportation Enhancements | 2009-10-22 | 2010-01-27 | 2010-04-23 | 2010-08-23 | 93043 | 33.760
8814 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILKES |  | 05 | 0421060 | ER-5100KB - This project will renovate and enhance landscape plantings on US 421 at the interchanges with NC 268, NC 16/18 South and SR 1001 (Brushy Mountain Road) in Wilkesboro in Wilkes county, Nort | Transportation Enhancements | 2010-01-21 | 2010-08-30 | 2011-12-17 | 2011-12-17 | 106799 | 0.000
8815 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER |  | 07 | 0421063 | ER-5100CB - This project will remove vegetation and supplement seeding & plantings within the medians and shoulders in the vacinity of the battleship on US 421/17/74/76 interchange in New Hanover coun | Transportation Enhancements | 2010-02-01 | 2010-12-02 | 2012-08-31 |  | 731500 | 0.000
8816 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | 04 | 0440006 | Remove sections of concrete pavement and replace with asphalt to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-04-15 | 2010-06-30 | 2011-05-01 | 4024604 | 5.000
8817 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 0440007 | Resurface I-440 Beltline in Raleigh from Wade Avenue to Wake Forest Road to improve road condition | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-12-31 | 2010-06-18 | 3709163 | 10.000
8818 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0440008 | This project consists of cleaning and painting bridges in Raleigh along I-440 including bridge numbers, 249 (Glen Eden), 252 (Ridge Road), 139 (US 401), 287 (US 1), and 288 (US 410 SBL) to extend lif | Bridge Improvement | 2009-08-24 | 2010-04-14 | 2010-10-31 | 2011-02-24 | 896775 | 0.000
8819 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 0440009 | This project provides for the installation of a Wireless Camera System on the Northern Section of I-440 in Raleigh to improve response to traffic congestion in Wake County. | Safety/Traffic Management | 2009-04-30 | 2009-04-30 | 2010-03-02 | 2010-03-17 | 382761 | 3.680
8820 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0485016 | This project will construct a filtration basin/wetland at NC 51/I-485 to treat stormwater runoff from NC 51 in Mecklenburg County helping to prevent pollutants from entering into a tributary of Clear | Other | 2009-10-15 | 2009-10-15 | 2010-04-30 | 2010-04-19 | 148065 | 0.000
8821 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0485025 | ER-5100JD - This project will reforestate at various locations on I-485 from US 74 East to I-85 North in Mecklenburg county, North Carolina. | Transportation Enhancements | 2010-01-21 |  | 2011-03-18 |  | 40000 | 26.540
8822 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0501014 | This project will repave Duke Street in Durham from Horton Road to Hudson Street to improve road condition. | Pavement Widening | 2009-05-13 | 2009-05-13 | 2010-05-14 | 2011-05-16 | 777500
8823 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0501015 | This project will install a traffic signal in Apex at the Intersection of SR 1010 (Center Street) and SR 1011 (North Salem Street) to improve safety. This is a locally administered project by the Tow | Safety/Traffic Management | 2009-09-17 | 2010-04-14 | 2010-05-14 |  | 30791 | 0.000
8824 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0503007 | This project will construct a portion of the Black Creek Greenway pedestrian and bicycle facilities from the Credit Union near the intersection of Chapel Hill Road and Northwest Maynard Road to the Sh | Transportation Enhancements | 2009-09-21 | 2010-03-01 | 2010-10-26 |  | 1299000 | 0.000
8825 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0505034 | This project will provide for traffic signal upgrades in Durham including pedestrian installed equipment at various locations for the city maintained signals to improve operating efficiency and safety | Safety/Traffic Management | 2009-09-22 | 2010-01-15 | 2010-09-12 |  | 122702 | 0.000
8826 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0505036 | The project provides for the installation of a new traffic signal in Durham at Northpoint Drive at Home Depot Entrance and Dehaven?s Entrance to improve safety in Durham County. TIP U-5150 is include | Safety/Traffic Management | 2009-09-22 | 2010-01-15 | 2010-09-12 |  | 346539 | 0.000
8827 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0505037 | This project provides for the installation of a new signal on Renaissance Parkway at the ATT Crossing and at the Mall Site Drive to improve access and safety in Durham County. This project includes T | Safety/Traffic Management | 2009-09-22 | 2010-01-15 | 2010-09-12 |  | 232071 | 0.000
8828 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505039 | This project will remove the free flow traffic turn lane in Durham at the intersection of SR 1670 (Greer Street) and Miami Boulevard to improve safety a the intersection in Durham County. This is a | Pavement Improvement | 2009-09-16 | 2010-05-11 | 2010-07-02 |  | 44789 | 0.000
8829 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505040 | The project will provide for replacement of trees in Durham along Duke and Gregson streets to improve neighborhood appearance in Durham County. This is a locally administered project by the City of D | Transportation Enhancements | 2009-09-21 | 2010-01-10 | 2010-04-10 |  | 89792 | 0.000
8830 | Underway | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505042 | This project will construct neighborhood accesses to the Third Fork Creek Greenway to improve community access in Durham County. This is a locally administered project by the City of Durham. | Transportation Enhancements | 2009-09-22 | 2010-01-18 | 2010-10-15 |  | 827000 | 0.000
8831 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505043 | This project will resurface asphalt on the North-South Greenway Trail in Durham from Lavender Street to Murray Avenue to improve pavement life and ride quality in Durham County. U-4726HI includes TIP | Transportation Enhancements | 2009-09-16 | 2010-05-07 | 2010-07-31 |  | 342183 | 0.000
8832 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505050 | U-3804 - This project will widen to multi-lanes by improving grading, paving, drainage and installing signals on SR 1321 (Hillandale Road) from I-85 to north of SR 1407 (Carver Avenue) in Durham Coun | Pavement Widening | 2010-06-16 | 2010-09-30 | 2012-06-15 |  | 2658263 | 0.836
8833 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | Multiple | 0520028 | This project will construct the Neuse River Greenway pedestrian and bicycle facilities from Falls Lake Dam to the South Soccer Complex on SR 2006 (Perry Creek Road) in Wake County. This project is lo | Transportation Enhancements | 2009-08-28 | 2010-01-19 | 2011-03-19 |  | 3250000 | 0.000
8834 | Completed | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0520038 | EB-4978 - This Project Will Construct The Edwards Mill Road Greenway, A Multi-use Path On Edwards Mill Road Extension From Reedy Creek Road to Trinity Road in Wake County, North Carolina. | Transportation Enhancements | 2010-09-20 | 2011-02-28 | 2011-10-15 | 2011-10-25 | 425000 | 0.000
8835 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0527006 | This project provides for the construction of the Dunn Creek Greenway to improve pedestrain access and safety from Smith Creek Soccer Center to the NC 98 Bypass in Wake County. This is a locally adm | Transportation Enhancements | 2009-09-16 | 2010-01-22 | 2010-07-23 |  | 450000 | 0.000
8836 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0529001 | This project provides for the construction of crosswalks at Athird and Main Streets to improve pedestrain safety and mobility in Wake County. This is a locally administered project by the Town of Wen | Transportation Enhancements | 2009-09-10 | 2010-02-01 | 2010-03-13 |  | 33810 | 0.000
8837 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0529002 | This project provides for the construction of 4500 feet of sidewalk in Wendell along Third Street and Buffaloe Road to improve pedestrian access to the park in Wake County. This is a locally adminis | Transportation Enhancements | 2009-08-14 | 2010-02-15 | 2010-06-30 |  | 375749 | 0.300
8838 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0532003 | This project constructs sidewalk in Zebulon on West Judd Street from North Wakfield Street to North Church Street in Wake County. This is a locally administered project by the Town of Zebulon. | Transportation Enhancements | 2009-09-08 | 2010-02-08 | 2010-04-08 |  | 71923 | 0.000
8839 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0540015 | Widen ramp from I-540 west to I-40 west in Durham and Wake Counties, and add merge lane on I-40 westbound between I-540 and Page Road in Durham County, to reduce congestion. | Pavement Improvement | 2009-12-17 | 2010-04-01 | 2010-12-31 |  | 3835029 | 7.767
8840 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 0540016 | Resurface I-540 in Wake County from north of I-40 to US 70 to improve road condition | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2010-05-27 | 2011-01-24 | 2569522 | 3.800
8841 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0540018 | The project will provide for landscape enhancement in Knightdale at the interchange of I-540 and US 64 in Wake County. This is a locally administered project by the Town of Knightdale. | Transportation Enhancements | 2009-09-16 | 2010-03-24 | 2010-06-13 |  | 117128 | 0.000
8842 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0561020 | This project will widen and resurface NC 561 from NC 11 to Northampton County in Hertford County to improve road condition. | Pavement Widening | 2009-07-20 | 2011-03-01 | 2011-06-30 | 2011-06-30 | 1919494 | 10.210
8843 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0700008 | This project will repave NC 700 in Rockingham County from the Dan River to SR 1902 (Dibrell Road) to improve road condition. | Pavement Improvement | 2010-03-01 | 2010-04-15 | 2010-05-29 | 2011-01-24 | 870044 | 8.671
8844 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | 06 | 0701018 | This project provides for the replacement of existing signal poles & mast arms at the SR 1300 (University Drive) and Rural Retreat Road intersection to improve road conditions in Alamance County. Inc | Safety/Traffic Management | 2009-08-05 | 2009-08-05 | 2011-06-30 | 2011-04-13 | 413272 | 0.000
8845 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701019 | This project provides for the replacement of existing signal poles & mast arms at the SR 1300 (University Drive) and Bonner Bridge Road intersection to improve road conditions in Alamance County. | Other | 2009-08-04 | 2009-08-04 | 2009-10-09 | 2009-10-09 | 455 | 0.000
8846 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BLADEN |  | Multiple | 0701020 | This project will construct bicycle lanes on US 701 between Elizabethtown and White Lake for approximately 6 miles by widening the existing paved shoulder to four feet on both sides in Bladen County. | Transportation Enhancements | 2009-08-07 | 2009-08-07 | 2010-06-01 | 2010-03-08 | 466764 | 5.300
8847 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701022 | This project provides for the construction of sidewalks, including curb and gutter to improve pedestrian mobility and safety on Piedmont Street from SR 1785 (Sellars Mill Road) to the Cummings High S | Transportation Enhancements | 2009-09-21 | 2010-03-27 | 2010-03-20 |  | 25611 | 0.000
8848 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701023 | This project provides for the construction of sidewalk and the installation of pedestrian signals to improve pedestrian safety and mobility on US 70 (Church Street)/SR 1158 (Huffman Mill Rd) from SR | Transportation Enhancements | 2009-12-21 | 2010-04-05 | 2010-06-30 | 2010-11-10 | 52463 | 0.000
8849 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701024 | This project provides for the construction of an ADA-compliant crosswalk and sidewalk to improve pedestrian mobility and safety on SR 1158 (Huffman Mill Road) and Forestdale Drive in Alamance County. | Transportation Enhancements | 2009-12-21 | 2010-04-05 | 2010-06-30 | 2010-11-10 | 53208 | 0.000
8850 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701025 | EB-5118GE - This project will construct sidewalks along Huffman Mill Road including a crosswalk at South Church Street in Burlington, Alamance county, North Carolina. | Other | 2010-02-09 |  |  |  | 16200 | 0.000
8851 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701026 | EB-5118GF - This project will construct sidewalks along Forestdale Drive including a crosswalk at Huffman Mill Road in Burlington, Alamance county, North Carolina. | Other | 2010-02-09 |  |  |  | 3762 | 0.000
8852 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0702015 | This project provides for the construction of Bus Stop Shelters to improve pedestrain mobility and safety at various locations in Carboro in Orange County. This is a locally administered project by t | Transportation Enhancements | 2009-07-29 | 2009-08-27 | 2010-06-23 |  | 76357 | 0.000
8853 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0702016 | This project proivdes for the construction of sidewalk on one side of Ashe Street from West Main Street to Shelton Street in Carrboro in Orange County. This is a locally administered project by the T | Other | 2009-09-09 | 2010-03-18 | 2010-06-28 |  | 139938 | 0.000
8854 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0702017 | This project provides for the construction of sidewalk on one side of Bim Street from SR 1005 (Jones Ferry Rd) to Fidelity Street in Carrboro in Orange County. This is a locally administered project | Transportation Enhancements | 2009-09-09 | 2010-03-18 | 2010-06-28 |  | 144238 | 0.000
8855 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0703014 | This project will upgrade the citywide traffic signal system at 124 intersections and install fiber optic communications cable in Chapel Hill / Orange County to reduce congestion and emissions and imp | Safety/Traffic Management | 2009-08-05 | 2009-08-05 | 2012-08-01 |  | 5686446 | 0.000
8856 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0703015 | This project provides for the construction of ADA Ramps to improve pedestrian mobility and safety at seven (7) selected locations in Chapel Hill in Orange County. This is a locally administered proj | Transportation Enhancements | 2009-09-21 | 2010-01-13 | 2010-06-24 |  | 50000 | 0.000
8857 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0703016 | This project proides for the construction of raised crosswalks and traffic calming devices at eight (8) selected locations in Chapel Hill in Orange County. This is a locally administered project by t | Safety/Traffic Management | 2009-09-21 | 2010-01-13 | 2010-06-24 |  | 65189 | 0.000
8858 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0703017 | This project provides for the construction of pedestrian safety improvements, pedestrain refuge islands, at one (1) location on NC 86 (Martin Luther King, Jr. Drive) and four (4) locations on east Fra | Transportation Enhancements | 2009-07-29 | 2009-08-05 | 2010-06-24 |  | 403550 | 0.000
8859 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0705004 | This project provides for the construction of sidewalk to improve pedestrian mobility on the West side of Oak Street from East Trollinger Street to Truitt Drive in Guildford County. This is a loca | Transportation Enhancements | 2009-12-08 | 2010-03-08 | 2010-06-07 |  | 53894 | 0.200
8860 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0708022 | This project provides for the construction of Phases IV and V of the Bicentenial Greenway, multi-use path and sidewalk, to improve pedestrin safety and mobility, from Ballinger Road to Market Street i | Transportation Enhancements | 2009-08-28 | 2010-03-31 | 2011-05-28 |  | 548112 | 0.000
8861 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0708023 | This project provides for the construction of intersection improvements and sidewalk and widening Lake Jeanette Road from Lawndale Drive to SR 2348 (Bass Chapel Road/Elm Street) to improve safety and | Pavement Widening | 2009-09-17 | 2010-02-08 | 2011-05-23 |  | 2960151 | 0.000
8862 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0708024 | This project provides for the construction of pedestrain improvements by replacing the median turn lane on South Elm-Sugene Street from JJ Drive to Vandalia Road to improve safety and mobility in Gree | Pavement Improvement | 2009-09-01 | 2010-01-25 | 2010-09-15 |  | 1678417 | 0.000
8863 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0708025 | This project will repave Holden Road from SR 4121 (High Point Road) to Pinecroft Road, Cone Boulevard form Elm Street to Summitt Avenue, Friendly Avenue from Radience Drive to Elam Avenue and Smith St | Pavement Improvement | 2009-08-04 | 2010-03-23 | 2010-09-03 |  | 1561890 | 0.000
8864 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0710021 | The project (EB-5118GH) will construct Sidewalks on the north side of SR 1486 (Lexington Avenue) from the High Point Greenway to SR 1471 (Montlieu Avenue) and on the south side from the High Point Gre | Transportation Enhancements | 2009-12-21 | 2010-03-15 | 2010-05-15 | 2011-02-10 | 107136 | 0.200
8865 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0711011 | This project provides for the construction of sidewalks to improve pedestrian safety and mobility on Nash Street, Faucette Mill Street, Revere Road, Hayes Street, Union Street, Eno Street and Allison | Transportation Enhancements | 2009-09-22 | 2010-03-01 | 2010-12-21 |  | 319459 | 0.000
8866 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0729002 | This project provides for the acquisition of right-of-way to construct trailhead parking area to access the Lake Brandt Greenway on US 220 North of Strawberry Road in Guildofrd County. This is a loc | Transportation Enhancements | 2009-08-18 | 2010-05-27 | 2010-12-31 |  | 274538 | 0.000
8867 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHATHAM | DURHAM | 02 | 0751023 | This project will construct left turn lanes and a traffic signal on NC-751 at the intersection of O'Kelly Church Road in Chatham County to ease congestion. | Safety/Traffic Management | 2009-08-18 | 2010-03-16 | 2009-04-30 | 2010-10-26 | 393000 | 0.000
8868 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0770003 | This project will construct curb & gutter and sidewalk to improve pedestrian mobility on the north side of NC 770 from Westridge Apartments to SR 1405 (South Glenn Street) in Rockingham County. Thi | Transportation Enhancements | 2009-11-09 | 2010-03-05 | 2010-05-15 | 2011-02-10 | 295703 | 1.500
8869 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 0771192 | Rehabilitate pavement on I-77 from US 21 (Exit 79) to milepost 84 in Surry and Yadkin Counties to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-12-31 | 2010-11-01 | 3497918 | 10.200
8870 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0771194 | The project (I-5128) will paint bridges at selected locations on Interstate 77 from Nations Ford Road to Catawba Avenue in Mecklenburg county. | Other | 2009-05-13 |  |  |  | 2708 | 0.000
8871 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | YADKIN |  | Multiple | 0771195 | Rehabilitate pavement on I-77 from Iredell County line to south of SR 1125 (Asbury Church Rd) in Yadkin County to improve road condition. | Pavement Improvement | 2009-09-08 | 2010-05-07 | 2010-07-01 | 2010-10-27 | 1057392 | 6.240
8872 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 0771196 | Rehabilitate pavement on I-77 from mile post 88.4 to mile post 90 in Surry County to improve road condition. | Pavement Improvement | 2009-08-06 | 2009-08-06 | 2009-11-20 | 2010-10-05 | 336992 | 3.200
8873 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 0771197 | Paint bridges carrying I-77 over NC 89 and I-74 eastbound lane in Surry County to extend the life of the structures. | Bridge Improvement | 2009-05-01 | 2010-08-11 | 2010-10-23 | 2011-02-10 | 586574 | 0.000
8874 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 0771198 | This project will construct a linear wetland at the I-77 Welcome Center in Mecklenburg County, NC. The purpose of this project is to treat stormwater runoff from the Welcome Center parking lot helpin | Other | 2009-12-07 |  | 2010-03-01 | 2010-03-11 | 87218 | 0.000
8875 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | IREDELL |  | Multiple | 0771199 | This project will construct a stormwater wetland, at the I-77SB Rest Area in Iredell County, to treat stormwater runoff from the Rest Area and a portion of the roadway before discharging into Lake Nor | Other | 2009-10-30 | 2010-02-08 | 2010-04-30 |  | 125071 | 0.000
8876 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | IREDELL |  | Multiple | 0771200 | The project will install landscape enhancement plantings at the I-77 and Langtree Road interchange in Iredell County. | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2009-12-15 | 2009-12-29 | 148121 | 0.000
8877 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0771201 | This project provides for the cleaning and painting of bridges 136, 120 and 85 on I-77 from Nations Ford Road to Catawba Avenue in Mecklenburg County to extend the life of the structures. | Bridge Improvement | 2009-09-09 | 2010-06-23 | 2011-08-05 |  | 1033000 | 0.000
8878 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LEE |  | Multiple | 0837005 | This project will construct the Endor Iron Furnace Greenway in Sanford which is a 10 feet wide paved asphalt multi-use greenway trail from Kiwanis Family Park on Carbonton Road to Boone Drive (approxi | Transportation Enhancements | 2009-08-14 | 2010-01-12 | 2010-10-12 |  | 554171 | 0.000
8879 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | Multiple | 0851114 | Interchange Planings On I-85 At Exit 26 In Belmont In Gaston County, North Carolina | Transportation Enhancements | 2010-01-21 | 2010-03-15 | 2011-04-29 | 2010-05-07 | 92000 | 0.000
8880 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CLEVELAND |  | 10 | 0851116 | I-5403 - This Project Will Mill And Fill I-85 From The South Carolina State Line To Milepost 7.2 In Cleveland County And Refurbish The Ramps At Exit 22 In Gastonia, Gaston County, North Carolina. | Pavement Improvement | 2010-08-13 | 2011-02-22 | 2011-06-24 | 2011-06-24 | 3500000 | 14.970
8881 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CABARRUS |  | Multiple | 0852067 | This project will rehabilitate existing pavement on I-85 from US 29/601 to NC 73 in Cabarrus County to improve road condition. | Pavement Improvement | 2009-03-27 | 2009-03-27 | 2009-10-30 | 2009-12-18 | 2647031 | 6.680
8882 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | Multiple | 0852068 | Mill and resurface I-85 from mile post 21.8 to mile post 23.5 in Gaston County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-02 | 2010-04-21 | 1007108 | 3.600
8883 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0852069 | This project will construct a wetland and provide credit for excess stabilization on the Northbound side of I-85 near the bridge crossing over Mallard Creek in Mecklenburg County. The purpose is to t | Other | 2009-10-19 | 2010-04-06 | 2009-04-30 | 2010-04-29 | 29113 | 0.000
8884 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CABARRUS |  | Multiple | 0852070 | This project will renovate the existing pair of?rest area buildings located on I-85, west of Concord at Mile Post 59 into vending,?security offices?and storage, construct a new pair of restroom buildi | Pavement Improvement | 2009-08-05 | 2009-12-01 | 2010-10-15 |  | 1719300 | 0.000
8885 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 0853195 | This project provides for resurfacing I-85 in Guilford County from US 29-70/Business 85 to Groometown Road to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2010-08-13 | 2010-12-01 | 2684768 | 2.800
8886 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DAVIDSON |  | 06 | 0853200 | This project will renovate the existing pair of?rest area located on I-85, south of Thomasville at Mile Post 100 into vending,?security offices?and storage, construct a new pair of restroom buildings | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2010-08-15 | 2010-12-17 | 1944158 | 0.000
8887 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | 06 | 0853201 | Install pavement marking reflectors and replace damaged/missing reflectors on I-85 in Guilford County, between Groomtown Road (milepost 131) and I-40 / I-85 junction east (milepost 120) of Greensboro, | Pavement Improvement | 2009-08-05 | 2009-09-24 | 2010-05-01 | 2010-10-26 | 441444 | 22.000
8888 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 0853202 | Install pavement marking reflectors and replace damaged/missing reflectors on I-85 in Guilford County, between NC 62 near Archdale and Business 85 in Greensboro, to improve nighttime visibility. | Pavement Improvement | 2009-08-05 | 2009-09-24 | 2010-05-01 | 2010-10-26 | 101102 | 6.000
8889 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0853204 | The project will provide reforestation along I-73 and I-85 at Various Locations in Guilford County, south of Greensboro | Transportation Enhancements | 2009-11-17 |  | 2012-04-30 |  | 66000 | 0.000
8890 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DAVIDSON |  | Multiple | 0853205 | The project will renovate landscaping south of Thomasville at the I-85 Rest Area Vietnam Memorial in Davidson County. | Transportation Enhancements | 2009-12-02 | 2009-12-07 | 2011-03-31 | 2011-03-10 | 60000 | 0.000
8891 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0853206 | The proejct (ER-5100GF) wil provide corridor plantings on Interstate 85 from Groometown Road (milepost 120) to I-85/I-85 Business (milepost 118) in Guilford county. | Transportation Enhancements | 2009-12-21 | 2010-03-09 | 2012-05-28 |  | 85000 | 2.000
8892 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0854113 | Resurface I-85 in Orange County from I-40 / I-85 interchange to SR 1006 (Orange Grove Road) to improve road condition. | Pavement Improvement | 2009-09-08 | 2010-04-11 | 2010-07-16 | 2011-04-20 | 1881209 | 1.466
8893 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0854114 | The project (R-5164A) will mill asphalt from existing pavement and resurface on Interstate 85 from the Orange county line to SR 1401 (Cole Mill Road); NC 147 from I-85 to the end of asphalt roadway ne | Pavement Improvement | 2009-12-17 | 2010-08-04 | 2010-12-16 | 2011-08-23 | 5575120 | 19.432
8894 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0909004 | This project constructs 481 square yards of sidewalk in Kernersville along the west side of Oakhurst Drive from Cherry St north past Lambeth Farm Lane to enhance pedestrian safety in Forsyth County. | Transportation Enhancements | 2009-07-14 | 2010-05-20 | 2010-06-30 |  | 54140 | 0.000
8895 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROWAN |  | Multiple | 0914027 | This project will construct the Grants Creek Greenway Bicycle Trail in Salisbury which is a 12 feet wide, paved greenway trail from Hogan's Valley Way to Forestdale Drive in Rowan County. This is a l | Transportation Enhancements | 2010-01-06 | 2010-11-08 | 2011-03-07 |  | 493764 | 0.000
8896 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0918068 | This projects constructs new sidewalk & installs one bus shelter and required retaining walls in Winston-Salem on east side of New Walkertown Road from Waterworks Road to Spaulding Drive to enhance pe | Transportation Enhancements | 2009-08-14 | 2010-03-01 | 2010-03-02 |  | 110643 | 0.000
8897 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0918069 | This project constructs new sidewalk and installs two bus shelters in Winston-Salem on east side of Peters Creek Parkway from Brewer Road to the existing sidewalk and from existing sidewalk to the bus | Transportation Enhancements | 2009-08-14 | 2009-09-24 | 2010-03-02 |  | 83569 | 0.000
8898 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0918070 | This project provides intersection improvements in Winston-Salem along Shattalon Drive intersections from Murray Road to Bright Oak Avenue to improve safety in Forsyth County. This is a locally admin | Safety/Traffic Management | 2009-06-23 | 2009-09-24 | 2010-08-25 |  | 292000 | 0.400
8899 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0923003 | This project will construct 725 feet of sidewalk in Walkertown on East Friendly Road from SR 2004 (Main Street) to Willoughby Drive with high visibility improvements to the Friendly Road/Walkertown El | Transportation Enhancements | 2009-06-05 | 2010-01-06 | 2010-03-05 |  | 28790 | 0.000
8900 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0923004 | This project will construct 617 feet of 5 feet wide concrete sidewalk in Walkertown on the east shoulder of Morris Street between Old Hollow Road (NC 66) and New Walkertown Road (US 311) to enhance pe | Transportation Enhancements | 2009-07-14 | 2010-02-08 | 2010-03-05 |  | 23050 | 0.000
8901 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0926003 | This project constructs 5,750 feet of sidewalk and required storm drainage in the Village of Clemmons on Middlebrook Drive between Idols Road and Greenbrook Drive to enhance pedestrian safety in Forsy | Transportation Enhancements | 2009-07-02 | 2010-01-25 | 2010-04-24 |  | 153819 | 1.100
8902 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0927003 | This project constructs a roundabout in Lewisville at the Lewisville-Concord Church Road/US 421/Williams Road intersection to improve safety in Forsyth County. This is a locally administered project | Pavement Improvement | 2010-01-21 | 2010-05-19 | 2010-11-30 | 2011-04-20 | 322765 | 0.020
8903 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CUMBERLAND |  | Multiple | 0951080 | This the preliminary engineering for the project that will renovate and improve existing landscape enhancements at the interchange of I-95 and NC 87 in Cumberland County. | Other | 2009-07-13 | 2009-07-13 |  |  | 186 | 0.350
8904 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROBESON |  | 07 | 0951081 | The project will renovate and improve existing landscape enhancement along I-95 between Mile Post 4 through 30 in Robeson County | Transportation Enhancements | 2009-09-24 | 2009-12-29 | 2010-02-27 | 2010-03-22 | 110633 | 0.000
8905 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CUMBERLAND |  | Multiple | 0951082 | The project (ER-5100FD) will renovate plantings on Interstate 95 and NC 87 at exit 46 in Cumberland county. | Transportation Enhancements | 2009-10-23 | 2010-03-22 | 2010-05-28 | 2010-05-21 | 210170 | 0.350
8906 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROBESON |  | 07 | 0951083 | The project (ER-5100FE) will provide reforestation on Interstate 95 from mile marker 3 to mile marker 5 in Robeson county. | Transportation Enhancements | 2009-10-28 | 2010-03-22 | 2010-04-02 | 2010-03-25 | 11875 | 2.000
8907 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | Multiple | 0952114 | Resurface I-95 from North of US 70 to North of Main Street in Johnston County to improve road condition. | Pavement Improvement | 2009-09-11 | 2010-03-31 | 2010-08-01 | 2011-12-01 | 2217715 | 14.600
8908 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CUMBERLAND |  | Multiple | 0952115 | This project will provide landscape enhancement at the I-95 Rest Area near Mile Post 48 in Cumberland County. | Transportation Enhancements | 2009-09-24 |  | 2012-06-24 |  | 122322 | 0.000
8909 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILSON |  | Multiple | 0953104 | This is the preliminary engineering for the project that will focus on landscape enhancement at the interchanges US 264/US 264 Alt & I-95 / US 264 in Wilson County. | Transportation Enhancements | 2009-07-09 | 2009-07-09 | 2010-12-15 |  | 152990 | 0.070
8910 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE |  |  | 0953105 | This project provides for pavement rehabilitation and resurfacing I-95 from south of the Nash County line (Milepost 123) in Wilson County to south of NC 58 (Milepost 128) in Nash County to improve ro | Pavement Improvement | 2009-09-09 | 2010-05-26 | 2010-08-15 | 2011-04-05 | 1507260 | 9.000
8911 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0999007 | This project constructs sidewalk in Rural Hall on NC 66 between Paso Street and Wall Street and constructs sidewalk and curb and gutter along Park Street between NC 66 and Church Street to improve ped | Transportation Enhancements | 2009-06-12 | 2010-03-01 | 2010-05-14 |  | 147316 | 0.200
8912 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 1001052 | The project (E-4129B) will construct the Snyder Greenway from Salisbury Avenue to Depot Street in Albemarle, Stanley county. | Transportation Enhancements | 2009-11-02 | 2010-03-08 | 2010-06-23 |  | 281777 | 0.000
8913 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1003085 | This project will design the upgrade and expansion of Charlotte's Intelligent Transportation System (ITS) Communications backbone which will provide for on-the-fly remote operation of Traffic Signaliz | Safety/Traffic Management | 2009-05-06 | 2009-05-21 | 2011-12-22 |  | 1227777 | 0.000
8914 | Underway | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1003086 | This project includes the construction of two miles of the Toby Creek Greenway in Charlotte from Mallard Creek Greenway near US 29 to University Blvd (NC 49) to improve pedestrian access in Mecklenbur | Transportation Enhancements | 2009-09-22 | 2009-09-22 | 2011-01-27 |  | 1239772 | 0.000
8915 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1003089 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the South Charlotte area including surveillance system along Providence Road, Ballentyne Commons Parkway and NC 51 | Safety/Traffic Management | 2009-09-09 | 2009-09-09 | 2010-10-15 |  | 629362 | 0.000
8916 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 1003090 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the Northwest Charlotte area including surveillance system along Beatties Ford Road, Sunset Road, Statesville Road | Safety/Traffic Management | 2009-05-19 | 2009-10-15 | 2010-12-15 |  | 1037565 | 0.000
8917 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 1003091 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the University area (Northwest Charlotte) including surveillance system along W. T. Harris, The Plaza, North Tryon | Safety/Traffic Management | 2009-10-15 | 2009-10-15 | 2010-12-15 |  | 1018904 | 0.000
8918 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1003093 | The project (EB-5118JC) will construct pedestrian signals and crosswalk markings at various locations in Charlotte, Mecklenburg County. | Transportation Enhancements | 2009-10-14 | 2009-10-20 | 2010-11-19 |  | 374624 | 0.000
8919 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 1003094 | The project (EB-5118JD) will install a sidewalk along Shasta Lane from Randolph Road to Sardis Road in Charlotte, Mecklenburg county. | Transportation Enhancements | 2009-10-20 | 2009-10-20 | 2010-08-15 |  | 350826 | 0.000
8920 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 1004039 | This project will repave Old Oxford Road in Durham County from Roxboro Street to Granville County line to improve road condition. | Pavement Widening | 2009-05-13 | 2009-05-13 | 2010-05-14 | 2010-12-01 | 1946021 | 16.620
8921 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1006034 | The project (EB-5118JB) will construct the West Branch Rocky River Greenway from River Ford Drive eastward along West Branch Rocky River for 1.1 miles in Davidson, Mecklenburg county. | Transportation Enhancements | 2009-10-20 | 2009-10-20 | 2011-04-07 |  | 517767 | 0.000
8922 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION | CHARLOTTE | Multiple | 1008020 | This project will construct left turn lanes in Indian trail on Unionville Indian Trail Road at the intersection with Faith Church Road in Union County to improve safety. | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-12-11 | 2010-04-14 | 299675 | 0.000
8923 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1013002 | This project includes milling existing asphalt, patching existing asphalt, repaving existing roadway, thermoplastic long life pavement markings in Matthews from North Trade Street/Matthews-Mint Hill R | Pavement Improvement | 2009-08-18 | 2009-08-19 | 2010-06-01 |  | 653571 | 1.110
8924 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 1031007 | The project (EB-5118JA) will construct sidewalks on Wilgrove-Mint Hill Road from NC 51 to Jim Harper Lane in Mint Hill, Mecklenburg county. | Transportation Enhancements | 2009-10-09 | 2010-03-05 | 2010-05-31 |  | 113656 | 0.800
8925 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CABARRUS |  | Multiple | 1034015 | "This enhancement project will Install a Pedestrian Tunnel in Kanapolis under SR 1691 (Loop Road) to connect the City Park and Research Campus and install an 84"" Stormwater pipe to improve area drain | Transportation Enhancements | 2010-01-21 | 2011-03-14 | 2011-12-09 |  | 600000 | 0.000
8926 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | IREDELL |  | 05 | 1100024 | Widen Brawley School Rd from Centre Church Rd to I-77 in Iredell County to improve safety and mobility. | Pavement Widening | 2009-09-15 | 2009-11-30 | 2013-07-01 |  | 22964090 | 1.203
8927 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GATES |  | 01 | 1100025 | This project will replace deficient Bridge #32 over Trotman Creek on SR 1100 (Carters Road) in Gates County. | Bridge Replacement | 2009-12-28 | 2010-06-21 | 2011-08-11 | 2011-09-20 | 881091 | 0.000
8928 | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 1107016 | This project will widen Old Fayetteville Road to accommodate pedestrain, bicycle and transit traffic in Carrboro / Orange County from NC 54 to Stroud Lane to provide bike lanes, sidewalks and bus turn | Transportation Enhancements | 2009-06-22 | 2009-06-22 | 2010-09-15 | 2010-11-17 | 800000 | 0.450
8929 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1133006 | This project adds sidewalks along the south side of SR 1133 (Main Street) in Winterville from Graham Street to Railroad Street in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-07-24 | 2009-09-11 | 2010-10-23 |  | 75000 | 0.400
8930 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1133007 | This project adds sidewalks along the south side of SR 1133 (Main Street) in Winterville from Mill Street to Winterville Parkway in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-07-24 | 2009-09-11 | 2010-10-23 |  | 55000 | 0.200
8931 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 1138016 | Paint bridges carrying SR 1138 (CC Camp Rd), SR 1131, SR 1122 (Dobbins Mill Rd), SR 1001, and SR 1345 over I-77 in Surry County to extend the life of the structures. | Bridge Improvement | 2009-05-01 | 2010-08-11 | 2010-10-23 | 2011-02-10 | 963149 | 0.000
8932 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1149007 | This project adds sidewalks along SR 1149 (Lee Street/Old NC 11) in Ayden from West Barwick Street to Allen Drive in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-07-14 | 2009-09-11 | 2010-08-18 |  | 75500 | 0.300
8933 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1149008 | This project adds sidewalks along the west side of SR 1149 (Lee Street/Old NC 11) in Ayden from the northernmost intersection of Countryaure Drive to First Street in Pitt County to improve pedestrian | Transportation Enhancements | 2009-09-11 | 2009-09-11 | 2010-08-18 |  | 142405 | 1.100
8934 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MADISON |  | 11 | 1151008 | B-3488 - This project will replace bridge #142 on SR 1151 over Big Pine Creek in Madison county, North Carolina. | Bridge Replacement | 2010-02-01 | 2010-09-27 | 2011-08-01 | 2011-12-06 | 590000 | 0.000
8935 | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | Multiple | 1213020 | EB-5119 - This project will construct the Carolina Thread Trail; Downtown Connector to Highland Rail Trail in Gastonia, Gaston county, North Carolina. | Transportation Enhancements | 2010-02-16 | 2010-09-07 | 2010-11-19 |  | 850000 | 0.000
8936 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 1221013 | This project will replace deficient Bridge #36 over Connaritsa Swamp on SR 1221 (Charles Taylor Road) in Bertie County. | Bridge Replacement | 2009-08-21 | 2009-08-31 | 2011-02-16 | 2011-04-05 | 644792 | 0.013
8937 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CURRITUCK |  | Multiple | 1222012 | Replace deficient bridge carrying Tullis Creek Road over Shingle Landing Creek in Currituck County. | Bridge Replacement | 2009-03-02 | 2009-03-02 | 2009-12-01 | 2010-07-26 | 649494 | 0.000
8938 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 1260002 | This project will replace deficient Bridge #16 over the Cashie River on SR 1260 (Republican Road) in Bertie County. | Bridge Replacement | 2009-08-21 | 2009-08-31 | 2010-10-22 | 2011-04-20 | 791672 | 0.000
8939 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302043 | This project will provide safe, efficient mobility for bicyclist while making much needed repairs to Coxe Avenue in the Asheville in Buncombe County. Includes TIP project U-5177. | Transportation Enhancements | 2009-08-24 | 2010-04-15 | 2010-09-17 |  | 246340 | 0.000
8940 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302044 | This is an enhancement project to provide trees, shrubs and other landscape items in the downtown central business district and a Gateway locations on Lexington and Clingman Avenues, College Street me | Transportation Enhancements | 2009-08-28 | 2010-03-01 | 2010-05-04 |  | 85217 | 0.000
8941 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302046 | This project will provide and promote safe pedestrian facilities including the upgrade of traffic signals to for pedestrian use along Fairview Road at heavily traveled intersections in Asheville in Bu | Transportation Enhancements | 2009-08-18 | 2010-04-01 | 2010-05-04 |  | 67481 | 0.000
8942 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302047 | This City of Asheville plans to build sidewalks to fill in gaps along city streets and NCDOT facilities to provide safe, effective pedestrian mobility to communities and businesses within Asheville in | Transportation Enhancements | 2009-09-09 | 2010-05-11 | 2010-09-17 |  | 502458 | 0.000
8943 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302048 | This project includes repaving Kimberly Avenue from Edwin Place to Gracelyn Road and is focused at providing safe, efficient mobility for bicyclist while making much needed repairs in Asheville in Bun | Pavement Improvement | 2009-12-03 | 2010-03-09 | 2010-10-15 |  | 598994 | 0.000
8944 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 1302050 | This project consist of installing a pedestrian crosswalk with signals to allow safe travel between two schools located on either side of Overlook Road (SR 3503) in Buncombe County. | Transportation Enhancements | 2009-10-19 | 2010-03-30 | 2010-03-19 | 2010-04-19 | 7430 | 0.000
8945 | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 1302051 | This project consist of installing sidewalk and wheelchair ramps at SR 3503 (Overlook Road) at Pinchot Drive in Buncombe County. This project is in conjunction with E-5105A. | Transportation Enhancements | 2009-10-19 | 2009-12-14 | 2010-02-19 | 2010-03-26 | 21769 | 0.000
8946 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MITCHELL |  | 10 | 1303007 | The project (EL-5107) will construct concrete sidewalks on SR 1260 (South Mitchell Avenue) from Bowman Middle School to NC 226 and along NC 226 from SR 1260 to SR 1211 (Cane Creek Road) in Bakersville | Transportation Enhancements | 2009-12-29 | 2010-05-11 | 2010-08-06 | 2010-08-05 | 100551 | 0.000
8947 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1305006 | This project will extend existing sidewalk along the US 70 in Black Mountain from Blue Ridge Road to Grovestone Road to promote walkability from surrounding neighborhoods to businesses along this rou | Transportation Enhancements | 2009-08-11 | 2010-03-22 | 2010-07-31 |  | 224971 | 1.270
8948 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1305007 | Preliminary engineering for the Flat Creek Greenway from Cotton Avenue for Charlotte Street as a part of a larger plan to promote multimodal forms of transportation in the Town of Black Mountain and s | Transportation Enhancements | 2009-08-11 | 2009-08-19 | 2011-06-30 |  | 196503 | 0.000
8949 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 1306020 | This project will widen SR 1306 (Mebane Street) in Burlington / Alamance County from Huffman Mill Road to Chapel Hill Road to four naes with a divided media to enhance safety and improve mobility. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2011-08-15 |  | 13386283 | 2.563
8950 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | YANCEY |  | 11 | 1307004 | This project includes construction of 850 feet of sidewalk in Burnsville to include curb and gutter and drainage items to connect with existing sidewalks and provide safe pedestrian travel along Mitch | Transportation Enhancements | 2009-10-28 | 2010-03-15 | 2010-05-21 | 2010-10-05 | 189956 | 0.000
8951 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH |  | Multiple | 1316012 | Replace deficient bridge Number 82 carrying SR 1316/SR 1612 over Cypress Creek in Nash County. | Bridge Replacement | 2009-08-05 | 2009-08-05 | 2010-09-26 | 2010-10-26 | 744331 | 0.000
8952 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MCDOWELL |  | 11 | 1316013 | The project (EL-5106) will construct concrete sidewalks on SR1001 (Sugar Hill Road) from SR 1168 (Reid Street) to Wilhemenia Street in Maron, McDowell county. | Transportation Enhancements | 2009-12-29 | 2010-05-11 | 2010-08-06 | 2010-08-05 | 27953 | 0.100
8953 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GATES |  | 01 | 1320009 | B-4521 - This project will replace bridge #26 on SR 1320 over Duke Swamp in Gates county, North Carolina. | Bridge Replacement | 2010-02-18 |  | 2012-04-09 |  | 675000 | 0.000
8954 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 1321005 | This project will repave Hillandale Road / Fulton Street in Durham from I-85 to Erwin Road to improve road condition. | Pavement Widening | 2009-05-18 | 2009-05-18 | 2010-05-14 | 2010-12-01 | 442239
8955 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1323004 | This project adds sidewalks along the east side of SR 1323 (Arlington Boulevard) in Greenville from SR 1467 (Stantonsburg Road) to US 13 in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-08-18 | 2009-09-11 | 2010-04-15 |  | 108897 | 0.000
8956 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BRUNSWICK |  | 07 | 1357005 | This project will realign the intersection of Smith Avenue and NC 130 in Brunswick County to eliminate the offset condition to improve safety and congestion. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2010-12-31 |  | 6702506 | 1.225
8957 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHEROKEE |  | 11 | 1393004 | Replace deficient bridge carrying SR 1393 (Rocky Creek-Wakefield Roads) over Junaluska Creek in Cherokee County. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-11-15 | 2011-02-10 | 416208 | 0.000
8958 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 1396002 | Paint bridges carrying SR 1396 (Pine Ridge Rd), SR 1602, and SR 1649 (Clyde Hayes Rd) over I-77 in Surry County to extend the life of the structures. | Bridge Improvement | 2009-05-01 | 2010-08-11 | 2010-10-23 | 2011-02-10 | 385910 | 0.000
8959 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1413010 | This project will construct a new road around the Oakdale Cemetery in Hendersonville and will provide access from US 64 to Hendersonville Elementary and Middle schools without disturbing the cemetery | Other | 2009-08-31 | 2009-11-05 | 2010-07-01 |  | 362999 | 0.200
8960 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1429003 | This project will construct the Cane Creek Greenway in Fletcher which includes a 10 feet multi-use greenway trail along the banks of Cane Creek to enhance pedestrian access in Henderson County. This | Transportation Enhancements | 2009-09-21 | 2010-01-13 | 2010-06-30 |  | 213738 | 0.000
8961 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1429004 | This project will construct a sidewalk in Fletcher along St. Johns Road from US 25 to Fanning Bridge Road to enhance pedestrian access within the Town of Fletcher in Henderson County. This is a local | Transportation Enhancements | 2009-09-21 | 2010-01-13 | 2010-06-30 |  | 390830 | 0.660
8962 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1429005 | U-5184 - This project will construct the Cane Creek Greenway in Fletcher, Henderson county, North Carolina | Other | 2010-02-11 |  |  |  | 40636 | 0.000
8963 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1430006 | This project will construct a brick paver sidewalk in the Village of Flat Rock along US 225 and Little River Road to enhance pedestrian access within the central historic area of the Village in Haywoo | Transportation Enhancements | 2009-09-23 |  |  |  | 56034 | 0.000
8964 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HALIFAX |  | Multiple | 1434004 | Replace deficient bridge Number 24 carrying SR 1434 over Quankey Creek in Halifax County. | Bridge Replacement | 2010-03-15 | 2010-03-01 | 2010-07-01 | 2010-08-23 | 504723 | 0.000
8965 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 1435008 | The project (R-5169B) will mill, strengthen, and resurface SR 1435 (Old Raleigh Road) from Mason Street to SR 1521 (Lake Pine Drive) and SR 1521 (Lake Pine Drive) from SR 1435 (Old Raleigh Road) to US | Pavement Improvement | 2009-12-15 | 2010-05-03 |  | 2011-04-20 | 451655 | 2.500
8966 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1467002 | U-5212 - This Project Will Mill And Resurface SR 1467 (Stantonsburg Road) From US 13-NC 11 To The End Of Curb And Gutter & Resurface From The End Of Curb And Gutter To SR 1204 (B'S Barbeque Road) In G | Pavement Improvement | 2010-08-05 | 2011-07-11 | 2011-08-19 | 2011-11-03 | 770000 | 1.700
8967 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 1486002 | This project will repave SR 1486/1768 (Lexington Avenue) from Montlieu Avenue to US 311 Business in High Point in Guilford County to improve ride quality and extend pavement life. | Pavement Improvement | 2009-09-14 |  | 2009-11-15 | 2011-01-24 | 512835 | 2.240
8968 | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD | ASHEVILLE | 11 | 1499003 | Preliminary engineering for the construction of sidewalks along Moody Farm Road terminating at Soco Road (US 19) enhancing pedestrian access within the Town of Maggie Valley in Haywood County. This i | Transportation Enhancements | 2009-08-19 | 2009-08-19 | 2010-11-29 |  | 940952 | 1.880
8969 | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD | ASHEVILLE | 11 | 1499004 | Maggie Valley: Two Pedestrian Bridges At Jonathan Creek Along Moody Farm Road (SR 1307) In Haywood County, North Carolina | Transportation Enhancements | 2009-09-23 | 2010-04-01 | 2010-11-09 |  | 687970 | 0.000
8970 | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BRUNSWICK |  | 07 | 1500007 | R-5216 - This Project Will Mill And Resurface SR 1500 (Midway Road) From NC 211 To US 17 Business And SR 1401 (Galloway Road) and US 17 Business to US 17 Bypass in Brunswick County, North Carolina. | Pavement Improvement | 2010-08-18 | 2011-02-01 | 2011-08-31 | 2011-10-07 | 2800000 | 7.750
8971 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 1515009 | B-4570 - This project will replace bridge #79 on SR 1544 over Gum Swamp Creek in Lenior county, North Carolina. | Bridge Replacement | 2010-02-11 | 2010-05-10 | 2010-09-24 | 2010-09-16 | 669494 | 0.000
8972 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 1538007 | This project will provide for the realignment, resurfacing, sidewalks and drainiage improvements on SR 1538 (Deep River Road) at Sunset Hollow Drive to NC 68 (Eastchester Drive) at Lake Forest Drive o | Pavement Improvement | 2009-09-23 | 2010-01-11 | 2010-11-06 |  | 1508572 | 0.500
8973 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 1542009 | This project will relocate a portion of SR 1542 (Ridge St) and extend SR 1542 on new location from existing Ridge Street west of SR 1545 (Mountain View Church Rd) to SR 1549 (Airport Rd) in Stanly Cou | New Construction | 2009-03-02 | 2009-03-02 | 2010-12-31 |  | 4209737 | 0.000
8974 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 1544005 | B-4604 - This project will replace bridge #13 on SR 1753 over Indian Wells Swamp in Pitt county, North Carolina. | Bridge Replacement | 2010-02-18 | 2010-06-17 | 2010-10-14 | 2010-11-05 | 547746 | 0.000
8975 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RANDOLPH |  | Multiple | 1547008 | This project will make improvements to increase mobility and safety at the intersection of SR 1547 (Finch Farm Road) at the intersection of SR 1533 (Mountain Road) and SR 3106 (Kennedy Road) in Trini | Other | 2009-09-17 | 2009-09-17 |  |  | 135000 | 0.000
8976 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH, STOKES | WINSTON-SALEM | 05 | 1611007 | Widen Doral Drive / Main Street in Forsyth and Stokes Counties, between Tobaccoville and King, to enhance safety and mobility. | Pavement Widening | 2009-04-27 | 2009-04-27 | 2011-08-15 | 2011-12-16 | 14684035 | 1.020
8977 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ANSON |  | 08 | 1627009 | Replace deficient bridge carrying SR 1627 (Pinkston-River Rd.) over Winston-Salem Southbound Railroad in Anson County. Includes TIP project B-4410 (replace bridge #307). | Bridge Replacement | 2009-06-22 | 2009-06-22 | 2011-09-01 | 2011-08-26 | 2874117 | 0.000
8978 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 1666002 | This project provides for the installation of sidewalk in Durham on SR 1666 (Dearborn Drive) from SR 1004 (Old Oxford Highway) to Ruth Street to improve pedestrian access and safety in Durham County. | Transportation Enhancements | 2009-09-16 | 2010-05-04 | 2011-05-02 |  | 579977 | 6.130
8979 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SCOTLAND |  | Multiple | 1674005 | This project will widen Lauchwood Drive in Laurinburg / Scotland County from US 15-401 Business to US 501 to improve traffic flow. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2010-07-15 | 2010-10-09 | 2724877 | 1.200
8980 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1708008 | This project provides for the construction of SR 1708 (Fire tower Road) from SR 1709 (Corey Road) to NC 43 to improve safety and mobility in Pitt County. This is a locally administered project by the | Pavement Improvement | 2009-10-19 | 2010-03-15 | 2010-08-31 | 2011-01-24 | 344032 | 1.040
8981 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 1728004 | This project will repave the following roadways in Wake County to improve road condition: Wade Avenue from Faircloth Street to Capital Boulevard (Raleigh), Old Raleigh Road from Gregson Drive to Maso | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2010-06-11 | 2011-05-10 | 1497307 | 2.500
8982 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 1733016 | U-3306 - This project will provide corridor upgrade (part on new location) by improving grading, paving, drainage and installing signals, curb & gutter, retaining wall and sidewalks on SR 1733 (Weaver | New Construction | 2010-06-16 | 2010-09-07 | 2013-06-15 |  | 6695450 | 2.838
8983 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1753003 | B-4568 - This project will replace bridge #67 on SR 1515 over Falling Creek in Lenior county, North Carolina. | Bridge Replacement | 2010-02-18 | 2010-07-13 | 2010-11-09 | 2011-03-15 | 666600 | 0.000
8984 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | Multiple | 1800006 | B-4519 - This project will replace Bridge #155 on SR 1800 over Little Long Creek in Gaston county, North Carolina. | Bridge Replacement | 2010-02-19 | 2010-04-19 | 2010-08-20 | 2010-08-18 | 546428 | 0.000
8985 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 1853001 | The project (R-4436GED) will implement environmental restoration and pollution abatement at the NCDOT west maintenance yard on Sandy Camp Road in Guilford county. | Other | 2009-11-04 |  | 2010-10-30 | 2010-10-08 | 146719 | 0.000
8986 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 1890003 | B-2988 - This project will replace bridge #13 on SR 1890 over East Fork of Pigeon River in Haywood county, North Carolina. | Bridge Replacement | 2010-02-19 | 2010-07-12 | 2011-10-14 |  | 905724 | 0.000
8987 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RUTHERFORD |  | Multiple | 1913003 | B-4633 - This project will replace bridge #32 on SR 1913 over Webbs Creek in Rutherford county, North Carolina. | Bridge Replacement | 2010-02-19 | 2010-12-10 | 2011-08-01 | 2011-12-06 | 732303 | 0.000
8988 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 03 | 1923009 | This project will extend Booker Dairy Road from US 70 Business to Buffalo Road in Johnston County. Route will be a two lane roadway with a new bridge over the Neuse River. | New Construction | 2009-04-09 | 2009-04-09 | 2011-12-31 |  | 11673744 | 0.000
8989 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH |  | 01 | 1945005 | Replace deficient bridge Number 69 carrying SR 1945 over Toisnot Swamp in Nash County. | Bridge Replacement | 2009-09-11 | 2009-09-11 | 2010-05-24 | 2010-07-15 | 898370 | 0.000
8990 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RANDOLPH |  | 06 | 1952001 | The project (U-5194) will improve the intersections of SR 1952 (High Point Street) at SR 1950 (Academy Street) and SR 1989 (Tiger's Den Road) and the Walmart entrance in Randolph county. | Other | 2009-11-09 | 2010-04-26 | 2011-05-01 | 2011-06-21 | 1180122 | 0.400
8991 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 1968003 | Replace deficient bridge carrying SR 1968 (St. Martin Rd.) over Long Creek in Stanly County. | Bridge Replacement | 2010-01-12 | 2010-04-05 | 2010-11-15 | 2011-02-10 | 1041814 | 0.000
8992 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 1970001 | Repair bridge expansion joints on 12 structures: Bridge 12 on SR 1970, Bridge 274 on US 220, Bridge 136 on SR 2254, Bridge 220 on SR 1547, Bridge 757 on US 311 Business, Bridge 287 on US 70 (Wendover | Bridge Improvement | 2009-08-05 | 2009-08-05 | 2010-05-29 | 2010-05-09 | 194826 | 0.000
8993 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 1978003 | This project will repave US 158 Bypass in Granville County from US 15 to US 158 Business to improve road condition. | Pavement Widening | 2009-05-13 | 2009-05-13 | 2010-05-14 | 2010-12-22 | 186954
8994 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RUTHERFORD |  | Multiple | 2169001 | The project will realign Brick Store Road (SR 2194) to intersect across from Pine Ridge Rd (SR 2159) and with Oakland Rd (SR 2193) at the existing signal in Forrest City in Rutherford County. The pur | Pavement Improvement | 2009-10-19 | 2010-02-23 | 2010-10-22 | 2010-07-22 | 633052 | 0.000
8995 | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 2693002 | This project includes the construction of a roundabout in Davidson at the intersection of SR-2420 (East Rocky River Road) and SR 2693 (Davidson-Concord Road) to improve safety In Mecklenburg County. | Safety/Traffic Management | 2009-05-13 | 2009-05-13 | 2009-10-23 | 2010-01-27 | 482893 | 0.000
8996 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 2825001 | The project (R-4436GD) will implement environmental restoration and pollution abatement at the NCDOT east maintenance yard on Camp Burton Road in Guilford county. | Other | 2009-09-24 |  | 2010-10-30 | 2010-10-08 | 135511 | 0.000
8997 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 4497001 | U-5198 - This project will mill and resurface SR 4497 (Independence Point Parkway) from NC 51 to Matthews-Mint Hill Road in Matthews, Mecklenburg county, North Carolina. | Pavement Improvement | 2010-01-21 | 2010-07-14 | 2010-08-27 | 2010-12-01 | 212000 | 0.450
8998 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 0002017 | This Barnes County project is a enhancement project to restore the Midland Continental Depot in Wimbledon. | Transportation Enhancements | 2010-07-12 | 2010-07-30 | 2011-02-01 |  | 240531 | 0.000
8999 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 0008027 | This Bismarck project is an enhancement project to contstruct a shared use path at United Tribes Technical College. | Transportation Enhancements | 2010-03-01 | 2010-05-17 | 2010-07-31 |  | 170925 | 0.000
9000 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS |  |  | 0009030 | This Cass County project is a Structure Replacement project on a Off-System Bridge at Maple River, 6 miles East & 6 miles south of Alice. | Bridge Replacement | 2009-06-01 | 2009-08-20 | 2009-10-03 | 2010-05-11 | 487890.38 | 0.047
9001 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON |  |  | 0030039 | This Morton Count project is an enhancement project to construct a bike/ped facility for the Lewis and Clark Trail Phase III. | Transportation Enhancements | 2010-07-13 | 2010-07-27 | 2010-11-06 |  | 202733.99 | 0.000
9002 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | TOWNER |  |  | 0048010 | This Towner County project is a Structure Replacement project on Off-System Bridge Off-System - 2 Miles South & 1 Mile West of Cando. | Bridge Replacement | 2009-08-10 | 2009-09-28 | 2009-10-31 | 2010-05-04 | 271667.36 | 0.047
9003 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 0221069 | This Barnes County project is a Microsurfacing on CMC 221 - From10 Miles South of Valley City, N to preserve the pavement structure. | Pavement Improvement | 2009-06-23 | 2009-09-03 | 2009-09-15 | 2011-01-19 | 452095.04 | 9.607
9004 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BOTTINEAU |  |  | 0520055 | This Bottineau County project is a Microsurfacing on CMC 0520 - From the Souris River, E to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-06-23 | 2009-09-01 | 2010-02-03 | 233058.04 | 4.560
9005 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BOTTINEAU |  |  | 0547058 | This Bottineau project is an enhancement project to complete surfacing of a shared use path at Lake Metigoshe from Sam Mill corner north. | Transportation Enhancements | 2010-03-09 | 2010-06-02 | 2010-10-15 |  | 353663.26 | 0.000
9006 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS |  |  | 0918055 | This Cass County project is a Thin Lift Overlay on CMC 0918 - From 8 Miles West of ND 18, E to preserve the pavement structure. | Pavement Improvement | 2009-06-01 | 2009-06-11 | 2009-08-28 | 2010-04-16 | 995719 | 8.039
9007 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CAVALIER |  |  | 1017061 | This Cavalier County project is a Chip Seal Coat on CMC 1017 - From ND 5, N to Wales to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-08-03 | 2009-09-01 | 2010-06-11 | 221875.23 | 8.966
9008 | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRANT |  |  | 1031012 | This NDDOT project is a thin overlay on ND 31 from the State Line north to Jct 21 to preserve the pavement structure. | Pavement Improvement | 2010-08-24 | 2010-09-09 | 2010-10-16 |  | 3745091.02
9009 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | LOGAN |  |  | 1034013 | This NDDOT project is a thin overlay on ND 34 from W Napoleon east to the south junction of ND 30, to preserve the pavement. | Pavement Improvement | 2011-01-03 | 2011-06-02 | 2011-10-15 |  | 1700000
9010 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | LOGAN |  |  | 1034015 | This NDDOT project is an intersection improvement project at the junction of ND 30 and ND 34, to improve safety. | Safety/Traffic Management | 2011-01-03 | 2011-06-02 | 2011-10-15 |  | 150000
9011 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | 1083071 | This NDDOT project is a structure replacement project on US 83, to replace the Sterling Railroad separation. | Bridge Replacement | 2010-02-09 | 2010-04-14 | 2011-11-05 |  | 1784825.87 | 0.100
9012 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | 1083078 | This NDDOT project is a surcharge project prior to a structure replacment project on US 83 for the Sterline Railroad separation. | Pavement Improvement | 2010-02-09 | 2010-04-14 | 2010-08-07 |  | 425389.69 | 0.100
9013 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1083086 | This Bismarck project is a Mill & Asphalt Overlay, Curb & Gutter, Marking and Video Detection on Bismarck - 7th Street from Bismarck Expressway to Boulevard Avenue to rehabilitate the pavement structu | Pavement Improvement | 2009-07-14 | 2009-08-10 | 2009-10-15 |  | 658920 | 1.470
9014 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1083087 | This Bismarck project is a Mill & Asphalt Overlay, Curb & Gutter, Marking and Video Detection on Bismarck - 9th Street from Bismarck Expressway to Boulevard Avenue to rehabilitate the pavement structu | Pavement Improvement | 2009-07-14 | 2009-08-24 | 2009-10-15 |  | 403664 | 1.470
9015 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | 1083088 | This NDDOT project is a thin overlay on US 83 from Bismarck north to south of Wilton to preserve the pavement structure. | Pavement Improvement | 2010-03-16 | 2010-08-16 | 2010-10-15 |  | 6627764.86 | 19.866
9016 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1083093 | This NDDOT project is a thin overlay on US 83 from Bismarck north to 57th Ave to preserve the pavement structure. | Pavement Improvement | 2010-03-16 | 2010-08-26 | 2010-10-15 |  | 482384.82 | 1.492
9017 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | KIDDER |  |  | 1094121 | This NDDOT project is a Mill & Hot Bituminous Pavement on I 94 - From County Line E TO Dawson to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-04-20 | 2010-09-19 |  | 3857048.25 | 15.574
9018 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | KIDDER |  |  | 1094122 | This NDDOT project is a Mill & Hot Bituminous Pavement on I 94 - From County Line TO E Dawson Interchange to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-04-20 | 2010-09-19 |  | 4559717.97 | 15.684
9019 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | DICKEY |  |  | 1112062 | This Dickey County project is a shoulder widening and aggregate project on CMC 1112 - 9 miles west of ND 1, east to widen the pavement structure. | Pavement Improvement | 2010-05-07 | 2010-08-16 | 2010-09-25 | 2011-10-11 | 731000 | 4.104
9020 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | DIVIDE |  |  | 1249059 | This Divide County project is a Chip Seal Coat on CMC 1249 - From 9 & 18 Miles South of Noonan, N to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-07-22 | 2009-09-01 | 2010-02-18 | 159553 | 6.127
9021 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | EMMONS |  |  | 1515051 | This Emmons County project is a Hot Bituminous Pavement on CMC 1515 - 0.5 miles south of ND 32, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-27 | 2009-09-09 | 2009-10-01 | 2010-04-13 | 153116.46 | 0.500
9022 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | FOSTER |  |  | 1613054 | This Foster County project is a microsurface on CMC 1613 from ND 9 north to preserve the pavement structure. | Pavement Improvement | 2010-02-22 | 2010-06-21 | 2010-09-15 | 2011-03-29 | 484716 | 16.969
9023 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRANT |  |  | 1919054 | This Grant County project is a grading project on CMC 1919 from 26 miles south of Heil, north, to reconstruct the pavement structure. | Pavement Improvement | 2010-03-04 | 2010-06-21 | 2010-10-15 | 2011-03-21 | 488291.63 | 2.000
9024 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | 1981086 | This Bismarck project is a Hot Bituminous Pavement and Curb & Gutter on Bismarck - North 19th Street from 75' N of E Century Ave to Oregon Dr to rehabilitate the pavement structure. | Pavement Improvement | 2009-08-17 | 2009-09-02 | 2010-08-01 |  | 755631.64 | 0.280
9025 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1981088 | This Bismarck project is a Concrete Pavement Repair and Mill & Overlay on Bismarck - West Main Avenue from Washington Street to Memorial Highway to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-23 | 2009-07-16 | 2010-08-01 |  | 1367500 | 0.880
9026 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1981089 | This Bismarck project is a Mill & Asphalt Overlay on Bismarck - South Washington Street from Bismarck Expressway to 175' south of Billings Drive to rehabilitate the pavement structure. | Pavement Improvement | 2009-08-17 | 2009-09-28 | 2010-08-01 |  | 594755 | 1.000
9027 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1981091 | This Bismarck Project is an enhancement project to construct a bike/ped facility along South Washington Street. | Transportation Enhancements | 2010-03-23 | 2010-07-26 | 2010-10-29 |  | 314257.56 | 0.000
9028 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988026 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - Division St NE from Collins Ave to 8th Ave NE to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-09-18 |  | 300000 | 0.511
9029 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988028 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 14th St NE from Collins Ave to 3rd Avenue NE to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-08-26 | 2009-09-18 |  | 150000 | 0.246
9030 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988029 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 3rd Ave NE from 5th St NE to 14th St NE to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-08-17 | 2009-09-18 |  | 250000 | 0.390
9031 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON |  |  | 1988030 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 27th St NW from 12th Ave NW to 8th Ave NW to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-10-08 | 2010-06-30 |  | 150000 | 0.231
9032 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988031 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - Old Red Trail from Sunset Drive to Collins Avenue to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-10-08 | 2010-06-30 |  | 400000 | 0.795
9033 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988032 | This Mandan Project is an enhancement project to construct a bike/ped facility from Main St/Mandan Ave south to 3rd St Trolley Station. | Transportation Enhancements | 2010-04-19 | 2010-06-23 | 2010-10-15 |  | 385438.36 | 0.000
9034 | Underway | C250,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2001053 | This NDDOT project is a Thin Lift Overlay on ND 1 - From W Jct I-94 N To Jct ND 26-DAZEY to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-03 | 2010-10-02 |  | 3911839.54 | 19.329
9035 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | LOGAN, MCINTOSH, LA MOURE |  |  | 2013028 | This NDDOT project is a Thin Lift Overlay on ND 13 - From JCT 30 East To E JCT 56 to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-09-17 | 2009-10-17 | 2010-04-29 | 2098744.99 | 19.763
9036 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | KIDDER |  |  | 2094081 | This NDDOT project is a Hot Bituminous Pavement on I 94 - From E Dawson Interchange To Crystal Springs to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-17 | 2010-10-02 | 2011-05-03 | 2533804.27 | 11.863
9037 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2094082 | This NDDOT project is a Hot Bituminous Pavement on I 94 - From W Eckelson E To E ND 1-OAKES to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-17 | 2010-10-02 |  | 2887483.15 | 13.168
9038 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | HETTINGER |  |  | 2117056 | This Hettinger County project is a Hot Bituminous Pavement on CMC 2117 - 0.8 Miles N of ND 21, N to rehabilitate the pavement structure. | Pavement Improvement | 2010-01-07 | 2010-05-20 | 2010-10-01 | 2011-03-25 | 484084 | 5.000
9039 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | KIDDER |  |  | 2215054 | This Kidder County project is a Hot Bituminous Pavement on CMC 2215 - From 5 Miles South of ND 36, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-24 | 2009-09-23 | 2009-10-02 | 2010-04-26 | 687270.6 | 5.170
9040 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | LA MOURE |  |  | 2281034 | This NDDOT project is a Microsurfacing and Chip Seal on US 281 - From Edgeley To 1.345 MI N JCT 46 to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-24 | 2009-09-19 | 2009-12-29 | 709552.95 | 20.274
9041 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STUTSMAN |  |  | 2281036 | This Jamestown project is a Concrete Pavement Repair, Dowel Bar Retrofit, and Grinding on Jamestown - US 281 from 17th St SW to 4th Ave SW to rehabilitate the pavement structure. | Pavement Improvement | 2010-01-06 | 2010-05-17 | 2010-10-15 | 2011-04-13 | 525664.88 | 0.460
9042 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCHENRY |  |  | 2511055 | This McHenry County project is a Microsurfacing on CMC 2511 - From 7 Miles North of Granville, N to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-06-16 | 2009-09-01 | 2010-02-03 | 249923.3 | 5.006
9043 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCKENZIE |  |  | 2755053 | This McKenzie County project is a Hot Bituminous Pavement on CMC 2755 - From 4.5 Miles North of Keene, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-29 | 2009-08-19 | 2009-09-01 | 2011-03-01 | 264525 | 6.275
9044 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCLEAN |  |  | 2800009 | This McLean County project is a Microsurfacing on CMC 2828, 2836, & 2879 - County Wide to preserve the pavement structure. | Pavement Improvement | 2009-06-29 | 2009-07-09 | 2009-09-19 | 2010-03-24 | 317756.65 | 12.176
9045 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STUTSMAN |  |  | 2987031 | This Jamestown project is a Mill and Overlay, Signing, Striping, and Mailbox Post Replacement on Jamestown - 3rd Street E from BNSF Railroad to 87th Avenue SE to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-18 | 2009-09-05 | 2010-03-16 | 679198.39 | 2.880
9046 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2990024 | This Valley City project is a Mill & Asphalt Overlay on Valley City - Wintershow Road from 4th Avenue SW to 5th Avenue SE to rehabilitate the pavement structure. | Pavement Improvement | 2010-03-17 | 2010-06-14 | 2010-08-28 | 2011-03-30 | 227253.36 | 0.538
9047 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2990025 | This Valley City project is a Chip Seal Coat on Valley City - 7th Street SE from 5th Avenue SE to 12th Avenue SE to preserve the pavement structure. | Pavement Improvement | 2010-03-17 | 2010-06-14 | 2010-08-28 | 2011-03-30 | 29283.79 | 0.473
9048 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2990026 | This Valley City project is a Mill & Asphalt Overlay on Valley City - 2nd Street NW from 9th Avenue NW to Central Avenue to rehabilitate the pavement structure. | Pavement Improvement | 2010-03-17 | 2010-06-14 | 2010-08-28 | 2011-03-30 | 189045.57 | 0.545
9049 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2990027 | This Valley City project is a Mill & Asphalt Overlay on Valley City - 2nd Street NE from 3rd Ave NE to 6th Ave NE to rehabilitate the pavement structure. | Pavement Improvement | 2010-03-17 | 2010-06-14 | 2010-08-28 | 2011-03-30 | 93562.75 | 0.191
9050 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON |  |  | 3000009 | This Morton County project is a Chip Seal Coat on CMC 3003 & 3006 - County Wide to preserve the pavement structure. | Pavement Improvement | 2009-08-03 | 2009-08-28 | 2009-09-01 | 2010-06-11 | 357242.46 | 14.485
9051 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RAMSEY |  |  | 3002099 | This NDDOT project is a Concrete Pavement Repair, Dowel Bar Retrofit and Grinding on US 2 - From Mauvais Coulee To Channel A to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-06-01 | 2010-09-15 | 2011-03-22 | 4151429.31 | 14.704
9052 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3002106 | This NDDOT project is a Thin Lift Overlay on US 2 - From Rugby E To Near Leeds to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-08-02 | 2010-10-02 | 2011-04-07 | 3430640.19 | 23.993
9053 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3003023 | This NDDOT project is a Hot Bituminous Pavement on ND 3 - From Rugby N TO JCT 66-Fonda to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-26 | 2009-06-24 | 2009-10-10 | 2010-04-13 | 4583614.25 | 22.957
9054 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BENSON |  |  | 3019042 | This NDDOT project is a thin overlay on ND 19 from Esmond east to junction ND 30 to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-07-13 | 2010-10-09 | 2011-04-11 | 1710162.57 | 12.564
9055 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BENSON |  |  | 3019046 | This NDDOT project is a thin overlay on ND 19 from Benson County line to Esmond to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-07-13 | 2010-10-09 | 2011-04-11 | 600617.01 | 4.082
9056 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RAMSEY |  |  | 3019047 | This Devils Lake project is a Mill & Asphalt Overlay on Devils Lake - ND 19 from US 2 to ND 20 (Asphalt Portion only) to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-26 | 2009-08-22 | 2009-10-01 | 2010-08-12 | 69016.01 | 0.182
9057 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3019050 | This NDDOT project is a thin overlay on ND 19 from junction ND 3 to the county line to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-07-13 | 2010-10-09 | 2011-04-11 | 764230.72 | 4.698
9058 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 3020081 | This Devils Lake project is a Mill & Asphalt Overlay on Devils Lake - ND 20 from US 2 to (RP 104.408) Urban Limits (exception 3rd St NW to 6th St NE) to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-26 | 2009-08-05 | 2009-10-01 | 2010-08-12 | 647824 | 1.504
9059 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RAMSEY |  |  | 3020086 | This Devils Lake project is an enhancement project to install entrance welcome signage at the city of Devils Lake at ND 20 north and south of town. | Transportation Enhancements | 2010-03-02 | 2010-05-10 | 2010-06-25 |  | 160297 | 0.000
9060 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MOUNTRAIL |  |  | 3100009 | This Mountrail County project is a Chip Seal Coat on CMC 3114, 3133, 3136, & 3143 - County Wide to preserve the pavement structure. | Pavement Improvement | 2009-07-21 | 2009-08-21 | 2009-09-04 |  | 264592 | 11.835
9061 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | NELSON |  |  | 3204064 | This Nelson County project is a Chip Seal Coat on CMC 3204 - From ND 1, E to preserve the pavement structure. | Pavement Improvement | 2009-05-22 | 2009-08-05 | 2009-08-15 | 2011-04-19 | 283946.62 | 9.993
9062 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PEMBINA |  |  | 3428053 | This Pembina County project is a Structure Replacement project on CMC 3428 - 6 Miles West of Pittsburg. | Bridge Replacement | 2009-07-13 | 2009-07-28 | 2009-10-31 | 2011-10-21 | 296822.75 | 0.100
9063 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3521058 | This Pierce County project is a Chip Seal Coat on CMC 3521 - City of Rugby to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-07-23 | 2009-09-01 | 2010-04-30 | 100003.62 | 2.807
9064 | Completed | C250 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3521059 | This Pierce County project is a Chip Seal Coat on CMC 3521 - City of Rugby CMC 3521 Spur to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-07-24 | 2009-09-01 | 2010-04-30 | 33650.85 | 1.116
9065 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RAMSEY |  |  | 3627061 | This Ramsey County project is a grading, widening, and HBP project on CMC 3627 - From the Benson County Line, N, to reconstruct the pavement structure. | Pavement Improvement | 2010-02-22 | 2010-05-31 | 2010-09-25 |  | 253804 | 3.244
9066 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RANSOM |  |  | 3705055 | This Ransom County project is a Chip Seal Coat on CMC 3705 - 8 miles south of ND 46, N to preserve the pavement structure. | Pavement Improvement | 2009-06-16 | 2009-08-25 | 2009-09-01 | 2010-02-18 | 185632 | 8.022
9067 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 3913054 | This Richland County project is a Hot Bituminous Pavement on CMC 3913 - 4 miles north of Barney, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-09-14 | 2009-10-02 | 2010-04-19 | 407833 | 4.000
9068 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4002084 | This NDDOT project is a Thin Lift Overlay on US 2 - From 3 Miles W Jct 52 E TO 1 Mile W Jct 83 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-03 | 2010-10-02 | 2011-06-07 | 2218137.19 | 14.192
9069 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4002092 | This NDDOT project is a Thin Lift Overlay on US 2 - From 3 Miles West of Jct 52 East TO 1 Mile West Jct 83 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-03 | 2010-10-02 | 2011-06-07 | 2175567.35 | 13.934
9070 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | ROLETTE |  |  | 4006060 | This Rolette County project is a Hot Bituminous Pavement on CMC 4006 - From 5.7 Miles West of St. John, E to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-26 | 2009-07-24 | 2009-10-09 | 2010-03-24 | 796362 | 5.667
9071 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | ROLETTE |  |  | 4006062 | This Rolette County project is an enhancement project to complete surfacing of a shared use path near St. John from the Horse Arena to town | Transportation Enhancements | 2010-03-02 | 2010-07-14 | 2010-10-15 |  | 94048.95 | 0.000
9072 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MOUNTRAIL |  |  | 4023009 | This NDDOT project is a Thin Lift Overlay on ND 23 - From JCT 8 East To Makoti to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-17 | 2009-10-10 | 2011-07-15 | 2103446.74 | 23.896
9073 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4023010 | This NDDOT project is a Thin Lift Overlay on ND 23 - From Makoti E To JCT US 83 to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-17 | 2009-10-10 | 2011-07-15 | 2420967.48 | 24.869
9074 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCLEAN, MOUNTRAIL |  |  | 4037012 | This NDDOT project is a Thin Lift Overlay on ND 37 - From JCT 23-Parshall-S TO 1 MI W ND 1804 to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-10 | 2009-10-10 | 2010-03-24 | 1880576.02 | 15.693
9075 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCLEAN |  |  | 4037013 | This NDDOT project is a Thin Lift Overlay on ND 37 - From 1 MI W JCT 1804 E & S TO Emmet Corner to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-10 | 2009-10-10 | 2010-03-24 | 2916300.13 | 28.112
9076 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCLEAN |  |  | 4083053 | This NDDOT project is a Grading, Base and Asphalt Pavement project on US 83 - From Near JCT 37 N TO 0.6 MI N Max Southbound to reconstruction the existing pavement. | Pavement Improvement | 2009-04-21 | 2009-05-20 | 2009-10-17 | 2011-07-01 | 8507134.56 | 13.358
9077 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | SARGENT |  |  | 4124052 | This Sargeant County project is a Hot Bituminous Pavement project on CMC 4124 - From 3.5 Miles East of ND 32, E, to rehabilitate the pavement. | Pavement Improvement | 2010-03-02 | 2010-06-30 | 2010-09-18 | 2011-03-22 | 211998 | 1.993
9078 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | SARGENT |  |  | 4125059 | This Sargeant County project is a Hot Bituminous Pavement project on CMC 4125 - From 1 Mile North of County Line, N, to rehabilitate the pavement. | Pavement Improvement | 2010-03-02 | 2010-06-30 | 2010-09-18 | 2011-03-22 | 317996 | 3.019
9079 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 4510060 | This Stark County project is a Thin Lift Overlay on CMC 4510 - From South Heart, East to preserve the pavement structure. | Pavement Improvement | 2009-07-07 | 2009-08-12 | 2009-10-16 | 2010-02-01 | 680000 | 4.871
9080 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRIGGS |  |  | 4612051 | This Steele County project is a Chip Seal Coat on CMC 4612 - Griggs co ln, east to ND 32 to preserve the pavement structure. | Pavement Improvement | 2009-07-07 | 2009-07-20 | 2009-09-01 | 2010-03-05 | 136481 | 8.000
9081 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STUTSMAN |  |  | 4718058 | This Stutsman County project is a Chip Seal Coat on CMC 4718 - From Buchanan, E to preserve the pavement structure. | Pavement Improvement | 2009-06-16 | 2009-07-14 | 2009-09-01 | 2010-02-18 | 143265.59 | 7.141
9082 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STUTSMAN |  |  | 4718059 | This Stutsman County project is a Chip Seal Coat on CMC 4718 - From ND 20, E to preserve the pavement structure. | Pavement Improvement | 2009-06-16 | 2009-07-14 | 2009-09-01 | 2010-02-18 | 160737.27 | 8.010
9083 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989070 | This Minot project is a Mill & Asphalt Overlay on Minot - 31st Ave SW from Broadway to 16th St SW to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-08-03 | 2010-07-01 | 2010-05-10 | 324719.19 | 1.009
9084 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989071 | This Minot project is a Mill & Asphalt Overlay on Minot - 4th Ave NW from Broadway to Bypass to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-08-03 | 2010-07-01 | 2010-05-10 | 701334 | 1.822
9085 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989072 | This Minot project is a Chip Seal Coat on Minot - 11th Ave S from Hiawatha to 16th St SW to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 84452.18 | 1.391
9086 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989073 | This Minot project is a Chip Seal Coat on Minot - 31st Ave SE from Broadway to 13th St SE to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 41050.83 | 0.987
9087 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989075 | This Minot project is a Mill & Asphalt Overlay on Minot - 3rd St NE from Hillcrest to Airport to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-08-04 | 2010-07-01 | 2010-05-10 | 123639.92 | 0.502
9088 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989076 | This Minot project is a Chip Seal Coat on Minot - 3rd St NE from Hillcrest to 5th Ave NE to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 37791.25 | 0.417
9089 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989077 | This Minot project is a Asphalt Overlay on Minot - 11th Ave SE from 31st St SE to 42nd St SE to rehabilitate the pavement structure. | Pavement Improvement | 2009-12-30 | 2010-06-04 | 2010-10-15 | 2011-03-07 | 143555.72 | 0.739
9090 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989078 | This Minot project is a Asphalt Overlay on Minot - 31st St SE from Burdick Expressway to 11th Ave SE to rehabilitate the pavement structure. | Pavement Improvement | 2009-12-30 | 2010-06-04 | 2010-10-15 | 2011-03-07 | 32959.54 | 0.254
9091 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989079 | This Minot project is a Mill & Asphalt Overlay on Minot - Railway Ave from 5th St NE to 13th St NE to rehabilitate the pavement structure. | Pavement Improvement | 2009-12-30 | 2010-06-07 | 2010-10-15 | 2011-03-07 | 235533.85 | 0.530
9092 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989080 | This Minot project is a Chip Seal Coat on Minot - 27th St from Burdick to Railway Ave to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 39592.51 | 0.657
9093 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989081 | This Minot project is a Chip Seal Coat on Minot - 21st Ave NW from US 83 Bypass to 20th St NW to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 41305.06 | 0.625
9094 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989082 | This Minot project is an interior reconstruction of the Amtrak Depot in Minot - 401 1st Avenue SW. | Transportation Enhancements | 2010-03-01 | 2010-04-26 | 2010-10-01 |  | 477000 | 0.000
9095 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989084 | This Minot project is a mill and bituminous pavement overlay project on 16th St SW from 20th Ave SW to 4th Ave SW, to rehabilitate the pavement. | Pavement Improvement | 2010-03-16 | 2010-06-07 | 2010-10-16 |  | 608011.23 | 1.360
9096 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WALSH |  |  | 5000009 | This Walsh County project is a Chip Seal Coat on CMC 5018 & 5047 - County Wide to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-07-28 | 2009-09-01 | 2010-04-29 | 296960.46 | 12.494
9097 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5008033 | This NDDOT project is a Thin Lift Overlay on ND 8 - From 1.4 Miles N County Line N Through Richardton to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-08-06 | 2010-10-09 | 2011-09-28 | 2297739.22 | 16.821
9098 | Underway | C250,C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BOWMAN |  |  | 5012038 | This NDDOT project is a thin overlay on US 12 from Rhame to Bowman, to preserve the pavement. | Pavement Improvement | 2011-01-03 | 2011-10-10 | 2011-10-15 |  | 1700000
9099 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5022085 | This Dickinson project is a Slurry Seal on Dickinson - ND 22 from 8th Street SW to Heart River Bridge to rehabilitate the pavement structure. | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-09-19 | 2010-01-13 | 119278.57 | 0.682
9100 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BILLINGS |  |  | 5085055 | This NDDOT project is a thin overlay on US 85 from Belfield north to near Gorham junction to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-07-19 | 2010-10-16 |  | 2941631.98 | 14.610
9101 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5094045 | This NDDOT project is a PCC Pavement Recycle project on I 94 - From Youngmans Butte to near Eagles Nest to reconstruction the existing pavement. | Pavement Improvement | 2009-03-24 | 2009-05-01 | 2009-10-17 | 2011-03-15 | 19179650.07 | 9.193
9102 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5094055 | This NDDOT project is a I-94 landscaping enhancement near Dickinson - I-94 from Exit 59 to Exit 64. | Transportation Enhancements | 2009-11-10 | 2010-04-22 | 2010-10-29 |  | 272395.64 | 5.011
9103 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BILLINGS |  |  | 5094067 | This NDDOT project is a Slurry Seal on I 94 - From Fryburg To Belfield to preserve the pavement structure. | Pavement Improvement | 2009-04-07 | 2009-08-17 | 2009-09-01 | 2010-01-21 | 580075.65 | 7.175
9104 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 5153056 | This Ward County project is a Chip Seal Coat on CMC 5153 - From 4 Miles East of Surrey, N & from 17 Miles South & 1 Mile west of Sawyer, N to preserve the pavement structure. | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2009-09-01 | 2009-11-10 | 626623 | 26.021
9105 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 5351053 | This Williams County project is a Hot Bituminous Pavement on CMC 5351 - FROM From 4 Miles South of US 2, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-06-25 | 2009-10-01 | 2010-04-16 | 439452.04 | 3.968
9106 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5983038 | This Dickinson project is a Slurry Seal on Dickinson - ND 22 Frontage Roads from 8th Street SW to Heart River Bridge to rehabilitate the pavement structure. | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-09-19 | 2010-01-13 | 76312.33 | 0.500
9107 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5983039 | This Dickinson project is a Slurry Seal on Dickinson - 4th Avenue E from Villard to Museum Drive to rehabilitate the pavement structure. | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-09-19 | 2010-01-13 | 119986.8 | 1.100
9108 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5983040 | This Dickinson project is a Mill & Asphalt Overlay on Dickinson - 21st Street W from 10th Avenue W to 10th Ave E to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-21 | 2009-10-16 | 2010-05-14 | 647614.68 | 1.447
9109 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STATEWIDE |  |  | 5999009 | This NDDOT project is the placement of rumble stripes on various highways within the Dickinson District, to improve safety. | Safety/Traffic Management | 2011-01-05 | 2011-04-15 | 2011-08-13 |  | 1606647.9
9110 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | NELSON |  |  | 6002078 | This NDDOT project is a Thin Lift Overlay on US 2 - From Michigan Bypass E To County Line? to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-04-29 | 2010-10-02 | 2011-05-23 | 1545715.19 | 10.189
9111 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PEMBINA |  |  | 6066016 | This NDDOT project is a Thin Lift Overlay on ND 66 - From S Jct 81-St. Thomas E TO I-29 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-27 | 2010-10-02 | 2011-05-23 | 1454818.11 | 11.975
9112 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CAVALIER |  |  | 6066017 | This NDDOT project is a Thin Lift Overlay on ND 66 - From District Boundary E TO N Jct 32 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-27 | 2010-10-02 | 2011-05-23 | 687281.16 | 8.033
9113 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PEMBINA |  |  | 6066018 | This NDDOT project is a Mill & Asphalt Overlay on ND 66 - From S JCT 32-Gardar E To Crystal to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-27 | 2010-10-02 | 2011-05-23 | 1127031.12 | 8.127
9114 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PEMBINA |  |  | 6066019 | This NDDOT project is a Thin Lift Overlay on ND 66 - From Crystal E To N Jct 81 St. Thomas to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-27 | 2010-10-02 | 2011-05-23 | 1279442.51 | 10.943
9115 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WALSH |  |  | 6985042 | This Grafton project is a Mill & Asphalt Overlay on Grafton - 5th Street from McHugh Avenue to Burgamott Avenue to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-12 | 2009-06-16 | 2009-10-02 | 2010-06-02 | 314166.29 | 0.600
9116 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WALSH |  |  | 6985043 | This Grafton project is a Chip Seal Coat on Grafton Urban Roads - 10 Sites to preserve the pavement structure. | Pavement Improvement | 2009-07-02 | 2009-07-08 | 2009-09-01 | 2010-07-30 | 209850 | 4.000
9117 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WALSH |  |  | 6985044 | This Grafton Project is an enhancement project to construct a bike/ped facility along ND 17 from School Road west and along Colette Ave from ND 17 south to School Road . | Transportation Enhancements | 2010-03-17 | 2010-07-14 | 2010-10-08 |  | 359491.6 | 0.000
9118 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986087 | This Grand Forks project is a Signals and Pavement Marking on Grand Forks - Intersection of 47th Ave S and Washington Street to preserve the pavement structure. | Pavement Improvement | 2009-06-17 | 2009-07-22 | 2009-11-01 | 2010-07-08 | 370460.42 | 0.060
9119 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986088 | This Grand Forks project is a Sign Replacement project on various Streets. | Other | 2009-11-03 | 2010-04-13 | 2010-07-01 | 2011-04-29 | 244972.59 | 9.118
9120 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986089 | This Grand Forks project is a concrete panel replacement and mill and bituminous pavement overlay project on Cherry Street from 25th Ave S to 47th Ave S, to rehabilitate the pavement. | Pavement Improvement | 2010-02-16 | 2010-07-06 | 2010-09-29 | 2011-04-11 | 870539.8 | 1.464
9121 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986090 | This Grand Forks project is a Chip Seal Coat on Grand Forks - University Avenue from 3rd Street N to State Street to preserve the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-03 | 2009-09-01 | 2010-01-15 | 257324.19 | 2.420
9122 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986091 | This Grand Forks project is a Chip Seal Coat on Grand Forks - Mill Road from Gateway Drive N to Urban limit to preserve the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-03 | 2009-09-01 | 2010-01-15 | 57000 | 1.560
9123 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS |  |  | 6986092 | This Grand Forks project is a Chip Seal Coat on Grand Forks - 20th Street N from Gateway Drive to University Avenue to preserve the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-03 | 2009-09-01 | 2010-01-15 | 37551.33 | 0.730
9124 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986093 | This Grand Forks project is a Chip Seal Coat on Grand Forks - 20th Street S from 24th Avenue S to 32nd Avenue to preserve the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-03 | 2009-09-01 | 2010-01-15 | 25319.27 | 0.480
9125 | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986096 | This Grand Forks project is a Concrete Pavement Repair and Mill & Overlay on Grand Forks - 8th Avenue N from 3rd Street N to Columbia Road to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-06 | 2009-10-01 | 2010-06-23 | 365000 | 1.060
9126 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986097 | This Grand Forks project is a concrete panel replacement and mill and bituminous pavement overlay project on 13th Avenue S from Cherry Street to Columbia Road, to rehabilitate the pavement. | Pavement Improvement | 2010-02-16 | 2010-08-05 | 2010-11-19 | 2011-04-14 | 442173.94 | 0.928
9127 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986099 | This Grand Forks project is a Concrete Pavement Repair on Grand Forks - 17th Avenue S from Washington Street to 42nd Ave S to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-07-27 | 2009-10-01 | 2010-06-23 | 636153.18 | 1.960
9128 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986100 | This Grand Forks Project is an enhancement project to construct a bike/ped facility along south 42nd street from 11th Ave S to 17th Ave S. | Transportation Enhancements | 2010-02-16 | 2010-05-20 | 2010-09-29 |  | 95709 | 0.000
9129 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCKENZIE |  |  | 7023027 | This NDDOT project is a Hot Bituminous Pavement on ND 23 - From Watford City East TO JCT 73 to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-05 | 2009-06-29 | 2009-10-10 | 2010-07-01 | 3591431.71 | 16.408
9130 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCKENZIE |  |  | 7023029 | This NDDOT project is a Thin Lift Overlay on ND 23 - From JCT 73 N&E TO Reservation Boundary to preserve the pavement structure. | Pavement Improvement | 2009-05-05 | 2009-06-29 | 2009-10-10 | 2010-07-01 | 1906034.96 | 19.291
9131 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7804034 | This NDDOT project is a Thin Lift Overlay on ND 1804 - From Beaver Creek W TO E BN Overpass to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-19 | 2009-10-10 | 2010-07-07 | 3287409.1 | 29.029
9132 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993030 | This Williston project is a Mill & Asphalt Overlay, Curb Ramps, and Driveways on Williston - 22nd St from 2nd Avenue West to University Ave to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-26 | 2009-07-07 | 2009-10-02 | 2010-04-27 | 240000 | 0.487
9133 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993031 | This Williston project is a Mill & Asphalt Overlay, Curb Ramps, Sidewalks, and Driveways on Williston - 22nd St E from University Ave to 12th Ave E (E Dakota Parkway) to rehabilitate the pavement stru | Pavement Improvement | 2009-06-26 | 2009-07-07 | 2009-10-02 | 2010-04-27 | 108686 | 0.330
9134 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993032 | This Williston project is a Mill & Asphalt Overlay, Sidewalk, Driveway, Valley Gutters, Curb Ramps on Williston - 26th St W from 6th Ave W to 16th Ave W to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-26 | 2009-07-07 | 2009-10-02 | 2010-05-25 | 260000 | 0.675
9135 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993033 | This Williston project is a Mill & Asphalt Overlay, Sidewalk, Driveway, Valley Gutters, Curb Ramps on Williston - West 2nd Avenue W Frontage Road from 6th Ave W to 42nd Street to rehabilitate the pav | Pavement Improvement | 2009-06-26 | 2009-07-08 | 2009-10-02 | 2010-05-25 | 157203.52 | 0.700
9136 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993035 | This Williston project is a Railroad Park enhancement and landscaping project at Railroad Park - 1 South Main Street. | Transportation Enhancements | 2009-12-23 | 2010-05-17 | 2010-11-12 |  | 210000 | 0.000
9137 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993038 | This Williston project is a Pavement Reconstruction project on Williston - Main St from Amtrak Depot to Front St to reconstruction the existing pavement. | Pavement Improvement | 2009-12-23 | 2010-05-17 | 2010-11-12 |  | 250000 | 0.039
9138 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8010034 | This Fargo project is a Mill & Asphalt Overlay on Fargo - Main Avenue from 2nd Street N to 25th Street to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-29 | 2009-08-19 | 2009-10-01 |  | 495000 | 1.540
9139 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | SARGENT |  |  | 8011022 | This NDDOT project is a Thin Lift Overlay on ND 11 - From N Jct 32 To S JCT 32-Forman to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-12 | 2010-09-19 | 2011-03-31 | 122241.07 | 1.314
9140 | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8011023 | This NDDOT project is a thin overlay on ND 11 from Lidgerwood east to Hankinson to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-05-18 | 2010-10-09 |  | 1676344.74 | 12.693
9141 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8029099 | This NDDOT project is a Concrete Pavement Repair on I 29 - From ND 13 N TO Christine Interchange to rehabilitate the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-10 | 2009-09-26 | 2011-02-17 | 1348123.13 | 21.572
9142 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8029104 | This NDDOT project is a Concrete Pavement Repair on I 29 - From ND 13 N TO Christine Interchange to rehabilitate the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-16 | 2009-09-26 | 2011-02-17 | 1638890.34 | 21.570
9143 | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | SARGENT |  |  | 8032028 | This NDDOT project is a Thin Lift Overlay on ND 32 - From SD Line to S. Jct. ND 11 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-12 | 2010-09-19 | 2011-03-31 | 1078471.64 | 10.196
9144 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8094073 | This NDDOT project is a lighting and structural repair project to improve a pedestrian underpass. | Transportation Enhancements | 2011-01-28 | 2011-05-11 | 2011-07-02 |  | 32927.11
9145 | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8984108 | This Fargo project is a concrete pavement reconstruction project on 45th St from 26th Ave S to 52nd Ave S to include grading, storm drains, sanitary sewer, lighting, and signals to reconstruct the exi | Pavement Improvement | 2010-03-22 | 2010-03-31 | 2010-10-15 |  | 4212312.06 | 2.470
9146 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8984113 | This Fargo project is a Structure Replacement project on Fargo - 38th St Bridge over Drain 27. | Bridge Replacement | 2009-12-14 | 2010-02-02 | 2010-09-03 | 2011-09-08 | 719895.06 | 0.091
9147 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8984114 | This Fargo project is a Structure Widening project on Fargo - 45th St at Drain 27. | Bridge Improvement | 2009-12-14 | 2010-02-15 | 2010-09-03 | 2011-05-19 | 317000 | 0.022
9148 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8984116 | This Fargo project is a Mill & Asphalt Overlay on Fargo - 25th Street from 32nd Avenue S to Rose Coulee to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-29 | 2009-07-29 | 2009-08-22 | 2011-05-12 | 362500 | 1.487
9149 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | BISMARCK-MANDAN |  | 8984118 | This Fargo project is a Asphalt Overlay and Concrete Pavement Repair on Fargo - Old HWY 81 from Dakota Dr to Co. Rd 20 to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-29 | 2009-09-21 | 2009-10-01 |  | 380000 | 1.940
9150 | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | BISMARCK-MANDAN |  | 8984119 | This Fargo project is a City wide pavement marking project to restore pavement markings. | Pavement Improvement | 2009-07-20 | 2009-07-27 | 2009-10-15 |  | 400000 | 10.075
9151 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991021 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 6th Street S from Dakota Ave. to 11th Ave. S. to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-12 | 2009-10-02 | 2010-05-11 | 102000 | 0.658
9152 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991022 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 4th Avenue S from 6th St. S to 11th St. S to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-12 | 2009-10-02 | 2010-05-11 | 41000 | 0.340
9153 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991023 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 2nd Avenue N from 2nd St. N to 11th St. N to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-12 | 2009-10-02 | 2010-05-11 | 56000 | 0.698
9154 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991024 | This Wahpeton project is a Pavement Patching and Seal Coat on Wahpeton - 7th Street N from 8th Ave N to 16th Ave N to preserve the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 47540.84 | 0.747
9155 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991025 | This Wahpeton project is a Chip Seal Coat on Wahpeton - 4th Street N from 2nd Ave N to ND 210 to preserve the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 119164.28 | 1.690
9156 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991026 | This Wahpeton project is a Mill & Asphalt Overlay on Wahpeton - 11th Street N from 16th Ave N to ND 210 to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 142504.43 | 0.487
9157 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991027 | This Wahpeton project is a Pavement Patching and Mill & Asphalt Overlay on Wahpeton - 7th Street N from 2nd Ave N to 8th Ave N to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 119400 | 0.435
9158 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991028 | This Wahpeton project is a Pavement Patching and Mill & Asphalt Overlay on Wahpeton - 11th Street N from Dakota to B Ave to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 106984 | 0.794
9159 | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS |  |  | 8992031 | This West Fargo project is a Mill & Asphalt Overlay on West Fargo, 6 locations to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-07-15 | 2009-08-15 | 2011-08-08 | 1226294 | 5.240
9160 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8992033 | This West Fargo Project is an enhancement project to construct a bike/ped facility from Sheyenne River to 9th St West. | Transportation Enhancements | 2010-03-29 | 2010-06-21 | 2010-08-15 |  | 247238.2 | 0.000
9161 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STATEWIDE |  |  | 9999248 | This NDDOT project is a project to update the history of the NDDOT. | Transportation Enhancements | 2010-04-06 | 2010-04-20 | 2011-05-30 |  | 267747 | 0.000
9162 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CAVALIER |  |  | A010032 | This Langdon project is an enhancement project to install entrance welcome signage at the city of Langdon. | Transportation Enhancements | 2010-03-01 | 2010-05-11 | 2010-08-01 |  | 140376.4 | 0.000
9163 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | TRAILL |  |  | T0UR035 | This NDDOT project is an enhancement project to rehabilitate the Viking Bridge northwest of Portland. | Transportation Enhancements | 2010-01-20 | 2010-03-09 | 2010-10-01 |  | 529912.15 | 0.000
9164 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS |  |  | T0UR036 | This North Dakota Parks and Recreation project is an enhancement project to contruct a new pedestrian briridge at Turtle River State Park. | Transportation Enhancements | 2010-03-03 | 2010-07-20 | 2010-10-29 |  | 325775.84 | 0.000
9165 | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | T0UR037 | This SHSND project is a enhancement project to Camp Hancock Locomotive at Camp Hancock in Bismarck - Main Avenue near 2nd Street. | Transportation Enhancements | 2010-03-30 | 2010-05-30 | 2010-07-15 |  | 206421.39 | 0.000
9166 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | 0H03001 | This project is for preliminary engineering for a multi use bike and hike trail along the north bank of the Ohio River | Transportation Enhancements | 2009-12-08 | 2010-03-15 | 2011-07-15 |  | 1582588.75 | 6.690
9167 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E031995 | This is a preservation project on I-75 from North Cove bridge to Cecilia. It will prevent future pavement decay on this priority route. The resurfacing project will prolong the life of I-75 between Be | Pavement Improvement | 2009-08-25 | 2009-09-08 | 2009-10-15 | 2009-11-08 | 1133582.59 | 2.700
9168 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CRAWFORD |  | 04 | E032086 | This project will resurface approximately 11.50 miles of SR 4 from the north corporation limit of the city of Bucyrus to the Seneca County line. It includes bridge work at seven locations. | Pavement Improvement | 2009-08-20 | 2009-09-16 | 2010-07-30 | 2010-08-30 | 3146444.09 | 11.330
9169 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E032369 | This project is to reconstruct the 15th street bridge over ABC railroad in Barberton | Bridge Replacement | 2009-09-11 | 2009-09-11 | 2011-06-30 | 2011-09-26 | 268000 | 0.000
9170 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | LAKE | CLEVELAND, OH | 14 | E033177 | In the City of Willowick this project is to upgrade and interconnet the traffic signal system at approximately 15 locations along Lakshore Blvd, Vine St and E 305th Street to improve safety. | Safety/Traffic Management | 2010-04-05 | 2010-05-20 | 2011-09-30 |  | 1205290 | 0.010
9171 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | JACKSON |  | 06 | E035110 | This is a four-lane minor rehabilitation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Jackson County. The project includes re | Pavement Improvement | 2009-08-18 | 2009-08-28 | 2010-10-31 | 2011-06-08 | 8982693.38 | 9.690
9172 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLERMONT |  | 02 | E035574 | Painting of Clinton U.S. 68 bridge over Cowan Creek; Clinton U.S. 68 over Anderson Ford; Wilmington Road bridge over I-71 in Warren; Stubbs Mills Road bridge over I-71 in Warren. | Bridge Improvement | 2009-08-12 | 2009-08-21 | 2010-06-01 | 2010-10-29 | 1291031.92 | 0.000
9173 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PREBLE |  | 08 | E035896 | Repave portions of SR 732; also resurface Eaton-Oxford Rd., CR 29, in from the Morning Sun Outpost | Pavement Improvement | 2009-10-02 | 2010-04-22 | 2010-06-30 | 2010-07-14 | 2252153.73 | 13.540
9174 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 12 | E036406 | This project includes the resurfacing of State Route 16 from mile marker 19.72 near the 21st Street bridge east to mile marker 23.66 near the Dayton Road Intersection. The project also includes the re | Pavement Improvement | 2009-09-03 | 2009-09-08 | 2010-10-30 | 2010-12-17 | 6230065.56 | 6.300
9175 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | JACKSON |  | 18 | E036464 | This is a preservation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Jackson County. The project will resurface 11.45 miles (2 | Pavement Improvement | 2009-08-19 | 2009-09-21 | 2009-10-31 | 2009-11-30 | 1501677.14 | 11.450
9176 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E036720 | This project is to rahabilitate the West 77th Street bridge over Norfolk Southern Railroad and GCRTA located between Franklin Ave and Madison Ave in Cleveland | Bridge Replacement | 2009-11-02 | 2010-01-06 | 2011-06-30 | 2012-01-26 | 1509000
9177 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E040008 | Improving travel and providing better connectivity is what this project will do. 5 miles of roadway will be resurfaced from the Montgomery/Miami county line to Tipp City in Miami County. | Pavement Improvement | 2009-06-25 | 2009-07-08 | 2009-09-30 | 2009-08-21 | 1800000 | 4.840
9178 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ATHENS |  | 06 | E040367 | The project is a five-mile, two-lane resurfacing project which includes two miles of SR 682 in Athens County and six miles of SR 356 in Vinton County. | Pavement Improvement | 2009-07-01 | 2009-08-21 | 2010-06-15 | 2010-09-13 | 728540.48 | 12.520
9179 | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | TUSCARAWAS |  | 18 | E040567 | Replace existing bridge constructed in 1906 over the Tuscarawas River between Front Street and Broadway in the city of Dover with a new multi-span, multi-beam bridge with sidewalks and pedestrian rail | Bridge Improvement | 2009-08-05 | 2009-09-18 | 2011-06-30 | 2011-02-18 | 810944 | 0.060
9180 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | HANCOCK |  | 04 | E040571 | Pave deteriorated sections along Interstate 75 in Hancock County, starting at State Route 613 north to the Wood County line. | Pavement Improvement | 2009-06-12 | 2009-07-06 | 2009-08-30 | 2009-08-22 | 1128068.62 | 2.810
9181 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | HARDIN |  | 04 | E040577 | Repave route SR37 from the Hancock County line to the Wyandot County line through the village of Forest and SR53 from the North Corporation limit of Kenton to SR37 in Hardin County due to pavement det | Pavement Improvement | 2009-07-08 | 2009-08-27 | 2009-10-01 | 2009-10-20 | 291000 | 12.870
9182 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 05 | E040597 | This project in southern Lorain County replaces 2 structures west of the Village of Wellington. The first is a 133' structure over the West Branch of the Black River, 0.57-mile west of Quarry Road and | Bridge Replacement | 2009-12-01 | 2010-02-22 | 2011-09-01 | 2010-10-25 | 1000000 | 0.080
9183 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 13 | E040717 | The project includes the complete reconstruction of 6.5 miles of Interstate 76 east of its interchange with Interstate 71 in Medina County. The project ends at the western side of the State Route 57 i | Pavement Improvement | 2010-04-14 | 2010-04-15 | 2011-09-30 | 2011-11-29 | 14883240.88 | 7.000
9184 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LORAIN | CLEVELAND, OH | 05 | E040910 | This project will widen the lanes of CR61 by 1' each side and add 4' paved shoulder. | Pavement Improvement | 2010-06-16 | 2010-08-05 | 2011-10-28 | 2011-10-31 | 1875065 | 2.650
9185 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E050142 | This project is to create a 4 lane divided roadway at Austin Pike to Washinton Church Road in Montgomery County. This project will also construct a recreation trail on the north side of the roadway. | Pavement Widening | 2010-04-06 | 2010-04-26 | 2011-06-30 | 2011-07-29 | 2000000 | 1.030
9186 | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | LOGAN |  | 07 | E050427 | This project will replace beams, deck, substructure and widen the structure over Great Miami River. | Bridge Improvement | 2010-04-14 | 2010-04-20 | 2010-11-30 | 2010-11-17 | 1341353.99 | 0.000
9187 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E050443 | To improve this major distribution link in East Central Ohio, this project will resurface approximately 3 miles of State Route 16 in Muskingum County and almost 10 miles of State Route 16 in Coshocton | Pavement Improvement | 2009-06-26 | 2009-07-06 | 2009-10-01 | 2009-12-03 | 2791601.89 | 13.000
9188 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | MERCER |  | 08 | E050631 | This project will correct deficiencies in the bridge as part of an Ohio Department of Transportation (ODOT) initiative to ?Fix it First.? Preserving this bridge on SR 118 in Mercer County by removing | Bridge Improvement | 2009-07-21 | 2009-08-27 | 2009-09-30 | 2009-10-04 | 205790 | 0.000
9189 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HOCKING |  | 06 | E050633 | This project is a nine mile, two-lane resurfacing project using an asphalt overlay on SR-180 in Hocking county | Pavement Improvement | 2009-09-03 | 2010-05-10 | 2010-07-15 | 2010-06-25 | 961651.6 | 9.160
9190 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PICKAWAY |  | 07 | E051164 | This project rehabilitates nine bridges on US 23 throughout Pickaway County. Original construction of these bridges was in the 1950s. Rehabilitation includes resurfacing or replacement of the bridge d | Bridge Improvement | 2009-07-24 | 2009-07-24 | 2010-09-30 | 2010-11-24 | 9566695.96 | 0.580
9191 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E051227 | Construct bicycle/pedestrian bridge at Deer Creek Dam spill way in Stark County | Transportation Enhancements | 2009-08-12 | 2009-09-14 | 2010-06-30 | 2010-09-10 | 611485
9192 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 07 | E051293 | Bridge maintenance projects on the Broad Street bridge over I-71 including backwall repair, new barrier wall, vandal fence and curb ramps. | Bridge Improvement | 2009-09-02 | 2009-10-26 | 2010-05-31 | 2010-09-02 | 714080 | 0.010
9193 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E051296 | Kettering Boulevard from the Moraine North Corp Line to the Moraine South Corp Line-Reconfigure right turn drop lanes, replace existing bridge, install sidewalk, resurface the existing roadway. | Pavement Improvement | 2010-05-13 | 2010-04-22 | 2010-10-30 | 2011-07-22 | 375000 | 1.870
9194 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E051298 | Reconstruction 5 lanes of MOT CR 99 from Stonequarry Road to Cresthill Drive in Vandalialanes. | Pavement Improvement | 2009-07-21 | 2009-09-16 | 2010-05-31 | 2010-09-02 | 126392 | 0.450
9195 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E060146 | In Gahanna at the IR270/SR317 (Hamilton Road) Interchange complete interchange ramp modifications by adding two lanes to the east bound exit ramd and one lane to the west bound exit ramp. Also will ex | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-10-31 | 2011-05-31 | 1985651.56 | 1.070
9196 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SENECA |  | 05 | E060167 | Bridge replacement on State Route 67, near State Route 100, in Seneca County. This project will provide a new bridge structure. | Bridge Replacement | 2009-06-26 | 2009-08-25 | 2010-09-30 | 2010-09-17 | 1575119.1 | 0.090
9197 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E060194 | Construct a bikepath from Sutton Avenue to Four Mile Road along north side of Kellogg Avenue including a spur into Kellogg Park on the south side of Kellogg Ave. near Four Mile Road; utilizing the cro | Transportation Enhancements | 2010-05-12 | 2010-06-21 | 2010-08-30 | 2011-05-16 | 463000 | 1.450
9198 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E060228 | Construction of new bridge over Mahoning River to replace current RR bridge | New Bridge Construction | 2010-03-26 | 2010-03-26 | 2010-10-01 | 2010-11-03 | 703610.06
9199 | Underway | C220 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 13 | E060255 | This project is to construct a pedestrian trail along Ohio and Erie Canal Towpath, in downtown Akron. | Transportation Enhancements | 2010-05-27 | 2010-06-07 | 2010-12-31 |  | 2500000 | 0.000
9200 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TUSCARAWAS |  | 18 | E060275 | This project is to construct a new interchange off I-77 at CR 80 in Dover to help relieve congestion at the existing I-77 interchanges in Dover and Strasburg. This interchange will provide improved ac | New Construction | 2009-08-27 | 2009-09-16 | 2011-06-30 | 2011-08-24 | 2162071.79 | 1.740
9201 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E060304 | Replacement of the North Street Bridge in the Village of Plymouth. The existing bridge is in very poor condition, has an ODOT bridge appraisal rating of 2P and a load limit of 20 tons. The project inc | Bridge Replacement | 2009-07-09 | 2009-09-08 | 2009-10-29 | 2009-10-29 | 210000 | 0.020
9202 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HANCOCK |  | 04 | E060317 | Add turn lanes on the north and west approaches of the intersection at SR 568 and Township Road 236 | Safety/Traffic Management | 2009-08-20 | 2009-08-31 | 2009-10-31 | 2011-10-01 | 475500 | 0.220
9203 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CRAWFORD |  | 04 | E060342 | This project involves the full reconstruction of State Route 4/State Route 98 (Sandusky Avenue) through Downtown Bucyrus. The 0.51 mile long project begins at Charles Avenue and concludes at the Sandu | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2010-10-27 | 2010-12-21 | 4415193.86 | 0.550
9204 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E060344 | This is the third in a series of projects to reconstruct, widen and improve safety along the U.S. Route 224 corridor through the City of Willard. The project will replace 1400 linear feet of two lane | Pavement Improvement | 2010-05-24 | 2010-06-05 | 2010-10-31 | 2011-07-11 | 1200000 | 0.450
9205 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E060378 | Resurface almost six miles of SR 147, from Belmont to SR 9 near Centerville, and over six miles of SR 149 from SR 9 at Warnock to Belmont. | Pavement Improvement | 2009-08-10 | 2009-08-31 | 2009-10-30 | 2010-07-17 | 895883.03 | 11.980
9206 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LAKE | CLEVELAND, OH | 14 | E060405 | This project is for reconstruction of Fairgrounds Road from SR-84 to Woodland Road in Concord and Painesville Twps. | Pavement Improvement | 2010-03-26 | 2010-03-29 | 2011-09-30 | 2011-10-24 | 2730074 | 1.140
9207 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E060436 | This project is for the reconstruction of Secor Road in Toledo from Monroe St to Laskey Rd. It will also modify the configuration of the intersection of Secor Rd and Sylvania Ave to improve traffic | Pavement Improvement | 2010-02-04 | 2010-03-17 | 2010-11-12 | 2011-10-07 | 2880000 | 1.090
9208 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | BROWN |  | 02 | E060440 | This project is to maintain and preserve the pavement by making the necessary repairs and overlaying the existing pavement with asphalt concrete on SR-32 from Clermont/Brown Co. Line to .017 miles eas | Pavement Improvement | 2010-02-09 | 2010-03-17 | 2010-09-30 | 2010-11-03 | 4093535.94 | 5.800
9209 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PERRY |  | 18 | E060540 | Modernizing a main connector for residents and businesses to the major cities of Zanesville in Muskingum County and Lancaster in Fairfield County, this project will resurface 14 miles of highly-travel | Pavement Improvement | 2009-06-25 | 2009-08-20 | 2009-10-15 | 2009-09-30 | 1535913.92 | 7.500
9210 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 18 | E060550 | As part of the Ohio Department of Transportation?s ?Fix it First? initiative, this project will help correct deficiencies in the bridges at two locations on U.S. 40 in Licking and Muskingum counties. | Bridge Improvement | 2009-09-03 | 2009-09-08 | 2010-09-15 | 2010-07-19 | 356130 | 0.040
9211 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | PUTNAM |  | 05 | E060605 | Repave routes SR189 and SR190 through the village of Ft. Jennings from the west corporation limits to US224 and SR694 from SR115 to the west corporation limit of the village of Glandorf in Putnam Coun | Pavement Improvement | 2009-06-25 | 2009-09-25 | 2009-10-31 | 2009-11-06 | 958437.3 | 9.620
9212 | Underway | C220 | Highway Infrastructure Investment Grant | OHIO | MIAMI |  | 08 | E060683 | This is a streetscape project for three intersections and will included landscaping, upgrading lighting, and adding other enhancement items. | Transportation Enhancements | 2011-03-23 | 2011-07-01 | 2011-11-15 |  | 456828 | 0.480
9213 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 13 | E060754 | This project is the resurfacing of I-77 from Ghent Road to the Richfield Village corporation line. Project also includes minor repairs (sealing and patching) to six bridges, including two over Ira Roa | Pavement Improvement | 2010-04-14 | 2010-04-23 | 2010-11-30 | 2010-10-19 | 2734471.35 | 4.170
9214 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | AUGLAIZE |  | 04 | E060946 | This project is to resurface the existing roadway with asphalt concrete on SR-362 in Auglaize county from the Shelby/Auglaize county line to the Village of Minster and in Shelby county from Lake Loram | Pavement Improvement | 2009-06-11 | 2009-07-21 | 2009-08-31 | 2009-08-19 | 476000 | 3.370
9215 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E060950 | This project is to rehabilitate the Aetna Road Bridge over the CSX tracks in the City of Cleveland | Bridge Improvement | 2010-03-29 | 2010-05-17 | 2010-10-30 |  | 1048230 | 1.120
9216 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SHELBY |  | 08 | E060967 | This project is to resurface the existing roadway with asphalt concrete on SR47 from 0.59 mile East of SR66 to Kuther Road in Shelby county | Pavement Improvement | 2009-09-02 | 2009-09-15 | 2009-10-31 | 2009-11-05 | 1239028.25 | 8.170
9217 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | SANDUSKY |  | 05 | E070033 | This project is for resurfacing SR125 in Scioto County. | Pavement Improvement | 2011-01-31 | 2011-04-25 | 2011-07-31 | 2011-07-19 | 683450.87
9218 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HIGHLAND |  | 03 | E070048 | This is a preservation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Highland County. The project will resurface U.S. Route 62 | Pavement Improvement | 2009-06-25 | 2009-09-09 | 2009-10-31 | 2009-12-08 | 488841.23 | 12.020
9219 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LAWRENCE |  | 06 | E070064 | This project will replace a deficient structure situated over Dick Creek, at the 5.78-mile marker on state Route 217, just west of the route?s junction with state Route 378. This project is necessary | Bridge Replacement | 2009-08-04 | 2009-08-17 | 2009-10-31 | 2009-11-24 | 349960
9220 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | SCIOTO |  | 06 | E070067 | This project will replace a deficient structure situated over Gas Hollow and located at the 1.28-mile marker on U.S. Route 52 (just east of Township Road 97 and the Adams-Scioto County line) and inclu | Bridge Replacement | 2009-07-01 | 2009-07-13 | 2009-10-31 | 2009-12-18 | 726871.92
9221 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GEAUGA |  | 14 | E070129 | Resurfacing of State Route 700 from U.S. 422 to State Route 168 in Troy and Burton Townships. | Pavement Improvement | 2009-09-02 | 2010-04-15 | 2010-07-15 | 2011-09-19 | 961865.64 | 5.040
9222 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E070130 | This project includes the resurfacing of approximately 7 miles of State Route 60 from the Morgan County line to the south corporation limit of Duncan Falls in Muskingum County. | Pavement Improvement | 2009-08-24 | 2009-09-08 | 2009-10-16 | 2009-10-19 | 1449185.43 | 8.150
9223 | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | MADISON |  | 15 | E070248 | EXTENSION OF SIDEWALKS, BRICK PAVERS, STREET LIGHTS, BENCHES, TREES AND TRASH RECEPTACLES ON US40 (MAIN STREET) FROM POND ROAD TO MILL STREET. Paving from SLM 14.17-14.60 will be done on this projec | Transportation Enhancements | 2011-01-19 | 2011-02-28 | 2011-09-30 | 2011-12-31 | 600000
9224 | Underway | C220,C240 | Highway Infrastructure Investment Grant | OHIO | PICKAWAY |  | 15 | E070267 | The Rickenbacker area, 10 miles southeast of Columbus, includes Rickenbacker International Airport, the Rickenbacker Intermodal Terminal and an industrial area. Building a new road that includes bette | New Construction | 2010-05-17 | 2010-05-24 | 2012-07-30 |  | 8512002.76 | 0.010
9225 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLERMONT |  | 02 | E070273 | Resurface portions of SR 232 in Clermont County to include just over 10 miles of roadway. | Pavement Improvement | 2009-08-18 | 2009-10-06 | 2010-07-30 | 2010-04-28 | 540548.55 | 10.190
9226 | Completed | C220,C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E070274 | This project involves the West Main Street (Business US 35) Streetscape including trees, shrubs, and masonry walls.and gateway sign. | Transportation Enhancements | 2010-09-13 | 2010-10-30 | 2010-12-03 | 2011-11-15 | 295139.68 | 0.190
9227 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E070284 | Resurface over 14 miles of SR 148 from SR 145 to SR 7 at Powhatan Point in Belmont County; resurface over four miles of SR 164 in Carroll County from SR 9 at Kilgore to SR 43 at Amsterdam; and resurfa | Pavement Improvement | 2009-08-31 | 2010-04-19 | 2010-07-31 | 2011-08-20 | 2741278.84 | 19.020
9228 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E070294 | Replace SR 148 bridge deck just west of the junction with SR 7 near Steinersville. | Bridge Improvement | 2009-08-27 | 2010-03-31 | 2010-07-15 | 2011-07-22 | 210583.55 | 0.010
9229 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E070304 | Resurface just over five miles of SR 149 from the village of Flushing in Belmont County to the village of New Athens in Harrison County, as well as resurfacing just under a mile of SR 9 in New Athens. | Pavement Improvement | 2009-07-01 | 2009-08-13 | 2009-09-30 | 2009-12-01 | 809655.81 | 6.150
9230 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E070362 | This project will upgrade of the existing traffic control at the intersection of Coy Rd and Starr Ave, in the City of Oregon, from all-way stop to a fully actuated traffic signal. | Other | 2010-02-17 | 2010-06-08 | 2010-06-16 | 2011-07-07 | 194201 | 0.040
9231 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | ASHLAND |  | 16 | E070379 | This project will rehabilitate a deficient 160-foot bridge over Claremont Avenue, 0.25-mile south of Baney Road. | Bridge Improvement | 2009-07-17 | 2009-07-28 | 2010-09-15 | 2010-09-29 | 1175274.8 | 0.020
9232 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLERMONT |  | 02 | E070407 | This project is to replace the bridge that carries SR 276 over Kain Run in Clermont county. | Pavement Improvement | 2009-07-01 | 2009-08-03 | 2009-10-30 | 2009-10-06 | 326082.73
9233 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E070412 | In Clinton county replace Culvert on SR 124 and SR 350 | Pavement Improvement | 2009-08-20 | 2010-08-14 | 2009-11-01 | 2010-12-08 | 220369.81 | 0.100
9234 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BUTLER |  | 08 | E070422 | This project will resurface portions of US 27 for approximately 15 miles. | Pavement Improvement | 2009-09-10 | 2009-09-11 | 2009-10-15 | 2010-06-02 | 2281937.33 | 14.940
9235 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E070513 | This project will alleviate safety concerns by widening State Route 2 in Lucas County at the Howard Road intersection, with exclusive left and right turn lanes. Work will also provide wider medians an | Safety/Traffic Management | 2010-05-20 | 2010-06-03 | 2010-10-22 | 2011-06-23 | 2227275.21 | 1.100
9236 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E070634 | Rehab existing single span steel beam bridge, originally built in 1952. Reconstruction of bridge/approach railing with decorative stone face wall. Installation of bridge lighting. Drainage improvement | Transportation Enhancements | 2009-09-17 | 2009-08-10 | 2009-12-31 | 2009-12-25 | 400000 | 0.460
9237 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GEAUGA | CLEVELAND, OH | 14 | E070642 | Resurface Washington Street from the County line to Chillicothe Rd. (SR-306) in the Village of South Russell and Bainbridge Twp | Pavement Improvement | 2009-08-19 | 2009-08-10 | 2009-12-01 | 2009-11-25 | 363187.4 | 2.180
9238 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GEAUGA | CLEVELAND, OH | 13 | E070646 | This project is to resurface Wilson Mills Road from County Line Rd. to Chillicothe Road (SR-306) in Chester Twp in Geauga county | Pavement Improvement | 2009-08-19 | 2009-08-17 | 2009-12-01 | 2010-02-12 | 499885.18 | 2.750
9239 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CHAMPAIGN |  | 07 | E070751 | This project is to resurface the existing roadway with asphalt concrete on SR-55 in Champaign county from the junction of SR-560 to the Urbana west county line. | Pavement Improvement | 2009-06-25 | 2009-08-31 | 2009-09-30 | 2009-09-30 | 424299.72 | 3.430
9240 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MEDINA | CLEVELAND, OH | 13 | E070779 | In Medina county on CR 97 (Greenwich Road) - from SR 3 to SR 57 resurface existing pavement and add paved shoulders to provide a new pavement surface and preserve the pavement structure | Pavement Improvement | 2010-05-25 | 2010-06-30 | 2010-10-29 | 2010-11-23 | 2147193.21 | 5.550
9241 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MEDINA | CLEVELAND, OH | 13 | E070780 | In Medina county on Marks Road (CR 22) - from Fenn Road (CR 70) to Hamilton Road (CR 76) resurface existing pavement and add paved shoulders to provide a new pavement surface and preserve the pavemen | Pavement Improvement | 2009-08-07 | 2009-09-21 | 2009-10-16 | 2009-10-23 | 529091.57 | 1.840
9242 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | DARKE |  | 08 | E070781 | The project will resurface 4.5 miles of SR 571 near the Darke/Miami County Line, specifically between the City Greenville and the Village of West Milton. This route is heavily traveled by truck traffi | Pavement Improvement | 2009-06-16 | 2009-08-17 | 2009-09-30 | 2009-09-08 | 510000 | 4.150
9243 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MEDINA | CLEVELAND, OH | 13 | E070785 | This project is to resurface CR 19 (Lake Road) - from CR 50 (Chippewa Road) to SR 162 (Wedgewood Road) which will include adding paved shoulders to provide a new pavement surface and preserve the pave | Pavement Improvement | 2009-08-07 | 2009-09-21 | 2009-10-16 | 2009-11-03 | 336748.47 | 1.540
9244 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | LOGAN |  | 04 | E070856 | The project will replace the bridge on SR 274 over the Great Miami River, which is two miles west of SR 235. The original structure was built in 1954 and is being replaced because of its age as well a | Bridge Replacement | 2009-06-26 | 2009-07-20 | 2009-10-30 | 2009-11-06 | 843508.79
9245 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | NOBLE |  | 06 | E070920 | This is a two-lane resurfacing project using an asphalt overlay treatment. | Pavement Improvement | 2010-12-22 | 2011-05-02 | 2011-07-15 | 2011-06-22 | 850453.62
9246 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | CHAMPAIGN |  | 04 | E070928 | This project will resurface the existing roadway on State Route 29 between State Route 560 and State Route 296 as well as the roadway on State Route 187 between the Madison / Champaign County Line and | Pavement Improvement | 2010-03-19 | 2010-05-03 | 2010-10-15 | 2010-07-12 | 586055.43 | 8.390
9247 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | DARKE |  | 08 | E070933 | This project is to resurface SR503 from the Preble/Darke county line to SR121 | Pavement Improvement | 2009-08-04 | 2009-09-15 | 2009-10-31 | 2009-11-09 | 1006737.21 | 9.290
9248 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GUERNSEY |  | 18 | E070951 | Interstate 77 is a major North-South economic corridor for eastern Ohio. This project will upgrade and rehabilitate approximately 2.5 miles of I-77 through Guernsey County. | Pavement Improvement | 2009-06-26 | 2009-07-01 | 2009-10-15 | 2009-08-28 | 1604000 | 2.510
9249 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | FAIRFIELD |  | 07 | E070952 | In Fairfield county resurface SR 204 from SR 256 to SR 158 and SR 204A from IR 70 to SR 204 | Pavement Improvement | 2010-03-17 | 2010-05-04 | 2010-10-15 | 2010-09-09 | 1719897.05 | 11.650
9250 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PERRY |  | 18 | E070959 | This project calls for the replacement of a deficient bridge deck located over Penn Central railroad on SR 93. This project is necessary for the safety of the traveling public, as well as to preserve | Bridge Improvement | 2009-06-25 | 2009-07-06 | 2009-10-31 | 2010-08-13 | 1187087.81 | 0.020
9251 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E071098 | Resurfacing SR 7 from Midlothian Blvd. to Indianola Ave; nearly one-half mile of U.S. 62 from Williamson Ave. to Hadnett Drive, and three-quarter miles of SR 625 from Midlothian Blvd. to U.S. 62. | Pavement Improvement | 2009-08-04 | 2009-08-14 | 2009-10-15 | 2009-10-27 | 753036.11 | 1.980
9252 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E071109 | This is a safety project to reconstruct and rehabilitate sections of SR153 in Louisville including new curbs, gutters, sidewaly pavement widening west of California and Signals at California | Other | 2009-06-16 | 2009-06-16 | 2012-12-31 |  | 330000 | 1.090
9253 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E071111 | The project is for the slope repair and reconstruction on I-271 at two locations between the Ohio Turnpike and Brandywine Road. | Pavement Improvement | 2009-06-24 | 2009-07-20 | 2009-12-01 | 2009-12-16 | 754120.55 | 0.020
9254 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E080046 | This project is to construct Superstreet intersection at Hamilton Mason Road and SR 4B with associated widening on SR 4B, including tapers. | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2011-10-28 | 2011-10-27 | 577562.84 | 0.620
9255 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E080099 | Bridge deck replacement and painting of the SR 11 twin bridges over Indian Run between U.S. 224 and Western Reserve Road. | Bridge Improvement | 2009-08-04 | 2009-08-14 | 2010-10-15 | 2010-11-24 | 1755873.09 | 0.000
9256 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 13 | E080129 | The project will replace a deficient 68-foot, three-span bridge on State Route 301, over Rudd Creek, north of the Village of Spencer. | Bridge Replacement | 2009-06-09 | 2010-03-31 | 2010-08-15 | 2010-08-18 | 391432.6 | 0.040
9257 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 13 | E080130 | This project involves the replacement of a deficient 38-foot bridge structure over the Carpenter Ditch, 0.17 mile north of Jason Road. | Bridge Replacement | 2009-06-11 | 2009-06-18 | 2010-10-29 | 2010-04-12 | 427996.38 | 0.010
9258 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E080160 | This project will resurface US Route 62 from SR 44 to State Street. Project also includes minor bridge work (patching and sealing) to six structures, two over Beech Creek, one over the Nimishillen Cre | Pavement Improvement | 2010-05-20 | 2010-05-26 | 2010-12-31 | 2010-11-17 | 3416393.19 | 5.370
9259 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CLERMONT | CINCINNATI (KY) | 02 | E080245 | This project is to resurface SR 125 from near I-275 to SR 132 in Clermont County. | Pavement Improvement | 2010-08-31 | 2010-09-03 | 2010-10-15 | 2010-11-19 | 202450.72 | 6.230
9260 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LORAIN | CLEVELAND, OH | 13 | E080278 | In Loraine county, resurface CR 57 (Russia Road) from SR 58 to CR 231 (Oberlin Elyria Road) | Pavement Improvement | 2009-11-12 | 2010-01-07 | 2010-10-29 | 2011-05-23 | 1584000 | 4.910
9261 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E080481 | This project is to rebuild Fifteen Signalized Intersections Throughout The City, Including Poles, Vehicle Signals, Pedestrian Signals And Cable. | Safety/Traffic Management | 2010-06-17 | 2010-06-07 | 2011-12-01 |  | 379921 | 0.120
9262 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E080491 | This project is to upgrade 7 signalized intersections to current standards and establish signal interconnection/coordination. | Safety/Traffic Management | 2010-11-23 | 2011-03-17 | 2011-08-31 |  | 260000
9263 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | NOBLE |  | 06 | E080504 | This is a two-Lane resurfacing project using an asphalt overlay treatment on SR145 in Washington and Noble counties. Work includes raised pavement markers, pavement marking and berm conditioning. | Pavement Improvement | 2010-03-03 | 2010-07-06 | 2010-10-15 | 2010-10-20 | 2890937.52 | 24.770
9264 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E080519 | Great Miami River Bikeway from Old Springfield Road north to Kyle Park in Tipp City-Construct a missing link on the River Corridor Bikeway. | Transportation Enhancements | 2010-06-15 | 2010-08-24 | 2009-10-30 |  | 263276
9265 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E080527 | Resurfacing of ten miles of U.S. Route 30 East Canton and Minerva. Extensive pavement repairs and guardrail replacement are included. There is also some minor work being done to the bridges in this se | Pavement Improvement | 2010-04-14 | 2010-04-21 | 2010-10-31 | 2010-11-16 | 2715184.43 | 10.410
9266 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E080541 | Realignment of four sets of railroad tracks to the south of the present location along US 50 in Cincinnati, Ohio. Track realignment is necessary to permit maintenance of traffic for the future roadwa | Pavement Improvement | 2009-12-01 | 2010-01-05 | 2011-06-30 | 2011-03-31 | 1075000 | 0.100
9267 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | SHELBY |  | 04 | E080582 | This project is to replace a heavily deteriorated 9'x5' concrete culvert. The project is located 0.87 miles east of the Darke/Shelby county line. This section of SR 47 runs between the Village of Vers | Pavement Improvement | 2009-06-05 | 2009-07-21 | 2009-08-31 | 2009-08-05 | 133217.78 | 0.010
9268 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | COLUMBIANA |  | 17 | E080586 | Resurface nearly five miles of SR 45, from McCracken Rd. south of Salem to U.S. 62 in Salem, and resurface just over 12 miles of SR 558 from SR 45 at Teegarden to SR 517 at East Fairfield, and from SR | Pavement Improvement | 2009-09-02 | 2010-04-07 | 2010-07-31 | 2010-12-01 | 1072915.69 | 17.110
9269 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CARROLL |  | 18 | E080587 | This project includes the resurfacing of approximately five miles of SR 39 in Carroll County and almost eight miles of SR 39 and SR 44 in Columbiana County. | Pavement Improvement | 2009-07-01 | 2009-07-20 | 2009-09-18 | 2009-12-02 | 1486660 | 13.070
9270 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CARROLL |  | 18 | E080588 | Almost three miles of SR 183 will be resurfaced, including just over a mile in Carroll County, from the Tuscarawas County line to the Stark County line at Magnolia, and about a mile and a half in Tusc | Pavement Improvement | 2009-08-04 | 2009-09-12 | 2009-10-15 | 2009-12-02 | 361029.35 | 2.850
9271 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 05 | E080613 | The project includes the reconstruction and resurfacing of 1.2 miles of East River Street in the City of Elyria. This includes the replacement of concrete curb & gutter, upgrading existing sidewalk, r | Pavement Improvement | 2010-03-15 | 2010-03-26 | 2010-10-29 | 2011-09-30 | 1457759 | 1.160
9272 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | COLUMBIANA |  | 17 | E080657 | Replace existing box beam bridge on SR 154, located approximately one mile east of SR 7 at Rogers, with a steel beam superstructure. | Bridge Improvement | 2009-08-25 | 2010-02-22 | 2010-07-15 | 2010-09-17 | 550225.5 | 0.500
9273 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LORAIN | CLEVELAND, OH | 13 | E080683 | This project is to upgrade State Route 611 to three lanes in Loraine County to provide adquate capacity. | Pavement Improvement | 2010-03-26 | 2010-03-16 | 2011-06-30 | 2011-12-02 | 4540176 | 2.810
9274 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WAYNE |  | 16 | E080696 | This project will rehabilitate a 282' bridge on State Route 539 over Interstate 71 in northwestern Wayne County. The project is between Ruff Road and Palmer Road. The SR-539/I-71 interchange is south | Bridge Replacement | 2009-09-09 | 2010-04-16 | 2010-10-15 | 2010-11-19 | 1266772.69 | 0.010
9275 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | ERIE |  | 05 | E080699 | This project will replace twin 10-foot arch bridges on SR-61 over Old Woman?s Creek, 0.15-mile east of the south juncture with State Route 113. | Pavement Improvement | 2009-06-12 | 2009-07-24 | 2009-10-15 | 2009-10-02 | 314234.94 | 0.020
9276 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HARRISON |  | 18 | E080712 | Fifteen miles of asphalt resurfacing and base repairs on SR 9 as well as six miles of asphalt resurfacing and chip sealing on SR 799 in Harrison County. | Pavement Improvement | 2009-07-17 | 2009-07-20 | 2009-10-15 | 2010-06-04 | 2706796 | 21.070
9277 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GREENE |  | 07 | E080736 | This project is to resurface U.S. 35 from the Montgomery/Greene county line to the US 35/I-675 interchange | Bridge Improvement | 2009-08-28 | 2009-09-29 | 2010-07-31 | 2011-06-01 | 5845640.96 | 1.090
9278 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | DARKE |  | 08 | E080747 | The project will reconstruct and lower USR 36 just west of Arcanum-Bears Mill Road to improve visibility and intersection safety. Due to the high accident rate at this intersection, the road grade wil | Safety/Traffic Management | 2009-06-12 | 2009-07-07 | 2009-09-30 | 2009-07-21 | 105981.5 | 0.090
9279 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 11 | E080755 | The project is a minor rehabilitation of Interstate 271, from Wilson Mills Road to Interstate 90 in Cuyahoga County and Lake County. The work includes replacement of overhead signs. | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2010-10-15 | 2010-09-30 | 8309390.72 | 4.310
9280 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E080757 | This safety related resurfacing project on SR 2 will provide motorists with safer access to Interstate 475 from the Spring Meadows shopping corridor. The safety project includes updated pavement marki | Safety/Traffic Management | 2009-08-12 | 2009-09-09 | 2009-12-15 | 2009-12-01 | 137437.18 | 0.430
9281 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E080763 | Resurfacing 7.88 miles of U.S. 20 from SR 11 to the Norfolk and Southern Railroad. | Pavement Improvement | 2009-06-26 | 2009-07-14 | 2009-10-15 | 2009-11-30 | 2593472.23 | 7.880
9282 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MEIGS |  | 06 | E080790 | The project focuses on pavement surfacing of a 7-mile portion of SR 7 through Meigs County. The two-lane micro-surfacing will improve pavement deficiencies and pavement conditions, thereby enhancing t | Pavement Improvement | 2009-06-25 | 2009-06-29 | 2010-06-30 | 2009-08-31 | 1289972.42 | 7.290
9283 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WASHINGTON |  | 06 | E080793 | Six miles of SR 60 in Washington County is being resurfaced. The work includes resurfacing on both lanes of the project. | Pavement Improvement | 2009-08-20 | 2009-09-03 | 2009-10-31 | 2009-10-26 | 1112788.13 | 6.090
9284 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | WYANDOT |  | 04 | E080796 | Grind and pave deteriorated pavement on US23 from County Road 62 to the CSX railroad in Wyandot county | Pavement Improvement | 2009-06-25 | 2009-07-06 | 2009-10-10 | 2009-11-02 | 500000 | 3.480
9285 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONROE |  | 06 | E080827 | An eight-mile stretch of SR 379 in Monroe County will be resurfaced. The project includes resurfacing work on both lanes of the roadway. | Pavement Improvement | 2009-08-12 | 2009-10-07 | 2010-06-30 | 2010-06-29 | 231815.37 | 8.070
9286 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E080895 | Resurfacing I-77 from the US 30 interchange to the SR 800/Cleveland Avenue interchange. Resurfacing of various ramps at both the US 30 and the SR 800/Cleveland Ave. interchanges. The project also incl | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-07-01 | 2010-06-25 | 2939729 | 1.050
9287 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | WOOD |  | 09 | E081010 | This project is a 2-Lane resurfacing project with pavement repairs on SR-582 from the Village of Luckey west corp line to US-23 | Pavement Improvement | 2010-03-09 | 2010-04-16 | 2010-08-06 | 2010-11-10 | 937766.71 | 4.340
9288 | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | SANDUSKY |  | 05 | E081011 | This project is on SR-600 from Wood County Line to US-20 and SR-300 in Gibsonburg. A 2-Lane resurfacing project with pavement repairs of SR-600 from Wood County Line to US-20 in Sandusky County and SR | Pavement Improvement | 2010-04-06 | 2010-06-01 | 2010-08-06 | 2010-11-12 | 3298923.4 | 10.820
9289 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E081028 | Minor rehabilitation/resurfacing with two deck overlays from Gypsy Ln in Niles to Girard city limits. | Pavement Improvement | 2010-06-08 | 2010-06-17 | 2010-10-31 | 2010-11-15 | 250000 | 2.950
9290 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CHAMPAIGN |  | 07 | E081032 | In Champaign county, replace 23 foot bridge over Jumping Run with minimal approach work. | Bridge Replacement | 2009-09-02 | 2009-09-28 | 2009-10-31 | 2009-12-09 | 309269.07
9291 | Underway | C240,C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E081064 | State Route 4 was built in the late 1960s as a 2 lane highway, but tremendous business growth in the area has led to congestion and has limited future economic potential. This latest phase of the bypa | Pavement Widening | 2010-05-07 | 2010-05-10 | 2012-04-13 |  | 6291933 | 1.600
9292 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E081068 | This project is for resurfacing North Fairfield Road in Greene County. | Pavement Improvement | 2011-03-25 | 2011-03-15 | 2011-08-31 | 2011-11-14 | 827728.82 | 1.140
9293 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HAMILTON |  | 01 | E081077 | Improve the pavement condition of Interstate 75 from south of SR 126 to south of the Lockland corporation. Project includes several minor bridge rehabilitations. | Pavement Improvement | 2009-08-04 | 2009-08-11 | 2010-08-01 | 2011-11-15 | 6246995.65 | 2.490
9294 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E081127 | Chip seal will be used as a preventive maintenance treatment to extend the pavement life on almost seven miles of SR 379 in Belmont County, between the Monroe and Noble county lines. Additionally, it | Pavement Improvement | 2009-08-18 | 2010-05-27 | 2010-08-30 | 2010-08-25 | 111015.62 | 9.400
9295 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CARROLL |  | 18 | E081129 | Chip seal will be used as a preventive maintenance treatment to extend the pavement life on about 18 miles of two-lane roadways in Carroll and Columbiana counties. Six miles of SR 9 in Carroll County | Pavement Improvement | 2009-07-08 | 2009-08-10 | 2009-10-31 | 2009-11-06 | 572426.23 | 17.600
9296 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 13 | E081175 | In Summit county on Waterloo Road, From US224 to Portage Line Road this project is to improve the road by making pavement repairs and resurfacing the full width of the roadway , applying pavement mark | Pavement Improvement | 2010-05-10 | 2010-07-26 | 2010-10-31 | 2010-12-20 | 663695 | 1.670
9297 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E081178 | This project is a Streetscape project within the Village of Glendale. The project will include paver brick sidewalks, decorative lighting, updated street furniture (park benches, trash receptacles), s | Transportation Enhancements | 2010-07-27 | 2010-08-02 | 2010-10-29 | 2010-12-16 | 287718 | 0.010
9298 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E090047 | Resurface State Route 380 from Greene County to Highland County | Pavement Improvement | 2009-09-17 | 2010-04-05 | 2010-07-01 | 2010-06-15 | 1827182.08 | 9.710
9299 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090071 | This project is to resurface Michigan St. (SR-25D) from Lafayette St. to Madison Ave in Toledo | Pavement Improvement | 2010-02-02 | 2010-03-22 | 2010-11-19 | 2010-11-15 | 1004570.45 | 0.440
9300 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090118 | Resurfacing of SR 800 from the Tuscarawas County line to south of Faircrest Street in Canton and Pike Townships and in the Village of East Sparta. | Pavement Improvement | 2009-07-01 | 2009-07-20 | 2009-12-01 | 2009-10-08 | 1256052.25 | 7.030
9301 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E090187 | Resurface State Route 72 from Highland County to Greene County to improve pavement condition. | Pavement Improvement | 2009-06-25 | 2009-07-08 | 2009-10-30 | 2009-10-28 | 2955680.41 | 14.000
9302 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONROE |  | 18 | E090192 | The project is a seven-mile, two-lane resurfacing project of SR 7 in Monroe County, including four miles of SR 7 in Washington County. | Pavement Improvement | 2009-09-02 | 2009-09-30 | 2009-10-31 | 2010-08-03 | 2332721.93 | 12.460
9303 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MORGAN |  | 18 | E090196 | Ten miles of SR 376 in Morgan County are being resurfaced. The project includes resurfacing work on both lanes of the highway. | Pavement Improvement | 2009-08-10 | 2009-08-12 | 2010-06-30 | 2009-10-02 | 1313282.43 | 9.730
9304 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090220 | This project involves landscape enhancement along outer edge of SR 4 roadway pavement by installing brick pavers, shrubs and retaining wall at gateway sign. | Transportation Enhancements | 2010-10-13 | 2010-10-28 | 2011-10-01 | 2011-10-01 | 14040 | 0.500
9305 | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | MEIGS |  | 06 | E090248 | This project begins 0.05 mi. N of 6th Street and SR 124 intersection. It includes upgrades to Starmill Park in Racine. Work includes parking lot resurfacing, walking track lighting, park entrance upg | Transportation Enhancements | 2010-05-17 | 2010-06-09 | 2010-10-29 | 2010-12-10 | 731804.06
9306 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MERCER |  | 05 | E090250 | This project includes pavement planing, shoulder stabilization, and resurfacing the existing roadway on SR29 and SR707 with Asphalt Concrete. | Pavement Improvement | 2010-02-24 | 2010-04-21 | 2010-10-15 | 2010-07-02 | 1610789.56 | 17.320
9307 | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E090289 | This project is to renovate the existing steel railroad bridge with a new deck and railing for bicycles and walkers. The old railroad corridor is owned by the Lorain County Metropolitan Park District | Transportation Enhancements | 2010-09-27 | 2010-12-11 | 2011-06-24 | 2011-05-09 | 283522.8
9308 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | ALLEN |  | 04 | E090292 | Repair and replace sections of deteriorated safety median wall barrier on both Interstate 75 in Allen County and U.S. Route 68 in Hancock County. Excessive deterioration of the existing concrete walls | Safety/Traffic Management | 2009-07-01 | 2009-07-27 | 2009-10-01 | 2009-10-15 | 875273.76 | 4.650
9309 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GEAUGA | CLEVELAND, OH | 13 | E090309 | This project is resurface Wilson Mills Road from Chillicothe Road (SR-306) to Heath Rd. in Chester Township | Pavement Improvement | 2009-08-19 | 2009-08-17 | 2009-12-01 | 2009-11-25 | 405387.99 | 2.200
9310 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E090320 | The project will repair two of Wilmington?s most traveled streets, Main and Locust street as well as install curbs and gutter. In addition to the semi-truck traffic that travels these two streets, the | Pavement Improvement | 2010-03-11 | 2010-03-25 | 2010-10-15 | 2011-04-30 | 2930266.19 | 3.420
9311 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090325 | This project is to resurface U.S. Route 62 from Sugar Creek to Navarre. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-12-01 | 2010-06-02 | 1771258.79 | 5.260
9312 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | AUGLAIZE |  | 04 | E090342 | This project involves pavement planing and resurfacing the existing roadway of SR 67 with Asphalt Concrete. | Pavement Improvement | 2010-02-18 | 2010-04-19 | 2010-09-30 | 2010-06-25 | 1404594.87 | 10.690
9313 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E090343 | This project will resurface the existing roadway with asphalt concrete on US-40 from the Preble / Montgomery county line to the west corporation limit of Clayton. | Pavement Improvement | 2010-03-16 | 2010-06-08 | 2012-08-15 | 2010-11-02 | 900000 | 6.220
9314 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 05 | E090357 | This project will provide various ?finishing touches? on the Veterans? Glass City Skyway. The project will provide funding for the installation of permanent inspection platforms. Work will also includ | Bridge Improvement | 2010-04-05 | 2010-04-26 | 2010-10-29 | 2010-09-16 | 1549690 | 2.000
9315 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E090373 | Resurfacing four miles of I-680 from SR 11 to Steel Street. Project also includes minor bridge work. | Pavement Improvement | 2009-07-27 | 2009-07-27 | 2010-06-30 | 2010-09-22 | 4051803.15 | 4.060
9316 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GREENE |  | 07 | E090375 | This project will resurface I-675 from SR 235 to the Clark County line and resurface SR 444 at I-675 interchange | Bridge Improvement | 2009-09-17 | 2009-09-21 | 2010-06-01 | 2011-07-20 | 4854049.01 | 3.240
9317 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | VAN WERT |  | 05 | E090387 | Repave route SR49 in Van Wert and Paulding County from US30 to the south corporation limit of Payne due to pavement deterioration | Pavement Improvement | 2009-06-12 | 2009-09-08 | 2009-11-04 | 2009-10-30 | 675236.63 | 8.260
9318 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | CLARK |  | 07 | E090400 | Improving the roadways and making sure the access points are ADA compliant is what this project will do for the city of Springfield. Five roadways in all will be resurfaced and new new ADA curb ramps | Pavement Improvement | 2010-04-13 | 2010-04-01 | 2010-07-20 | 2010-11-22 | 909053.76 | 3.180
9319 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLARK |  | 07 | E090401 | This is Clark County?s longest bridge and is in need of repair. The project will rehabilitate the structure and paint the Dayton Road bridge over the Norfolk Southern railroad near the Greene County L | Bridge Improvement | 2010-03-10 | 2010-03-01 | 2010-11-01 | 2010-11-16 | 384877 | 0.000
9320 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 13 | E090427 | This project will replace a deficient 12-foot structure over small creek in Medina County on SR 421, .25 miles west of SR 85. | Pavement Improvement | 2009-08-24 | 2010-07-28 | 2011-10-14 | 2011-11-01 | 668947.93 | 0.040
9321 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090439 | This project is to rehabilitate the State Street bridge in downtown Akron. | Other | 2009-09-17 | 2009-09-17 | 2011-10-31 |  | 500000 | 0.010
9322 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ADAMS |  | 02 | E090442 | This is a four-lane preventive maintenance (preservation) project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Adams County. The proj | Pavement Improvement | 2009-09-02 | 2010-04-20 | 2010-08-31 | 2010-09-13 | 3483829.51 | 13.700
9323 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090485 | Resurface South Maple Avenue from Doris Drive to Dayton Yellow Springs Road-Asphalt. | Pavement Improvement | 2009-09-10 | 2009-09-25 | 2010-03-08 | 2009-10-13 | 239165.46 | 1.200
9324 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL |  | 13 | E090491 | This is a safety project to install pedestrian lighting along Mahoning Ave between High Street and Summit Street. | Safety/Traffic Management | 2010-03-03 | 2010-06-29 | 2010-08-31 | 2010-11-30 | 203438.84 | 0.520
9325 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WARREN |  | 03 | E090503 | Resurface Clearcreek-Franklin Road from approximately 160 feet south of Whispering Pines to Pennyroyal Road. | Pavement Improvement | 2010-01-07 | 2010-04-23 | 2010-08-01 | 2010-05-13 | 164616.57 | 0.760
9326 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GREENE |  | 07 | E090504 | Resurface Dayton-Yellow Springs Road from Kauffman Avenue to Ironwood Drive to improve pavement condition | Pavement Improvement | 2009-10-23 | 2009-10-07 | 2010-05-28 | 2009-11-16 | 209858.39 | 0.640
9327 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E090505 | This paving project would improve U.S. 68 through the city of Wilmington, another of the city?s most heavily used streets by car and truck traffic. The project would replace the curb, gutter and pavem | Pavement Improvement | 2010-04-21 | 2010-05-11 | 2010-11-01 | 2010-10-14 | 880119 | 0.960
9328 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | HAMILTON |  | 01 | E090506 | This project constructs Phase 2 of the Banks Intermodal Facility and the surrounding street network. The Banks Intermodal Facility, in conjunciton with the Riverfront Transit Center, will serve as Ci | New Construction | 2010-06-10 | 2010-06-14 | 2011-09-30 |  | 8000000 | 0.330
9329 | Completed | C240,C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090507 | Project will design and construct Freedom Way between Rosa Parks and Race Street, Mehring Way between Main Street and Elm Street, and relocate and construct components of a new utility distribution li | New Construction | 2010-03-29 | 2010-03-15 | 2010-11-15 | 2012-02-23 | 6500000 | 0.320
9330 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | MORGAN |  | 18 | E090508 | The majority of bridges in Morgan County accommodate mostly truck, car and school bus traffic. All but one bridge in Morgan County spans a river or waterway. Some of the bridges are as old as 1914 and | Bridge Improvement | 2009-07-22 | 2009-07-27 | 2009-10-15 | 2009-09-21 | 94366.38 | 0.000
9331 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MORGAN |  | 18 | E090509 | Safety studies have indicated that guardrail is needed along 11,000 feet of roadway that parallels the Muskingum River. Slopes in these areas are very steep and guardrail would protect vehicles from g | Safety/Traffic Management | 2009-09-18 | 2009-10-19 | 2009-10-15 | 2009-11-03 | 120155 | 10.950
9332 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | WASHINGTON |  | 06 | E090511 | Resurfacing over seven miles of Marietta city streets, reconstructing 100 ADA curb ramps along city streets, and limited drainage improvements. Includes various sections on Acme, Colegate, Front, Gilm | Pavement Improvement | 2009-08-20 | 2009-09-03 | 2010-06-30 | 2010-08-06 | 1067710.19 | 9.000
9333 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | GALLIA |  | 06 | E090512 | The project will focus on the resurfacing of 5.25 miles of Gallia County roads, thereby reducing maintenance needs and providing structural strength for all local travelers. The roads are as follows: | Pavement Improvement | 2009-07-17 | 2009-09-03 | 2010-06-30 | 2009-09-24 | 352552.41 | 5.010
9334 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | VINTON |  | 18 | E090513 | This project will focus on resurfacing over ten miles of Vinton County roads, reducing maintenance needs and providing structural strength for all local travelers. | Pavement Improvement | 2009-06-24 | 2010-04-22 | 2010-06-30 | 2010-06-07 | 408383.12 | 4.440
9335 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090515 | Resurfacing from Walnut St to the Crab Creek Bridge. | Pavement Improvement | 2010-03-26 | 2010-04-14 | 2009-12-31 | 2010-06-10 | 441152.99 | 0.420
9336 | Underway | C220,C200,C240 | Highway Infrastructure Investment Grant | OHIO | ALLEN |  | 04 | E090516 | This railroad grade separation underpass project in the city of Lima?s south side is located on Vine St. between Main St. and Central Ave. The project is being constructed in conjunction with IGCC (Li | New Bridge Construction | 2009-05-18 | 2010-05-10 | 2011-11-01 |  | 12665306.94
9337 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E090517 | The KROC Center is a $66 million community center under construction in the Keowee/Webster Street area of Dayton. The $66 million is also being invested to renovate a very large historic home once cov | Pavement Improvement | 2009-10-06 | 2009-09-08 | 2009-11-02 | 2009-12-01 | 349497.57 | 0.830
9338 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E090518 | As the largest city in Montgomery County, Dayton has more than 150,000 residents. This project will improve the safety of five major thoroughfares that are deteriorating and will continue to unless im | Pavement Improvement | 2009-10-22 | 2009-10-09 | 2009-11-30 | 2010-05-07 | 1414900.9 | 5.610
9339 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E090519 | This project will restore and preserve a major thoroughfare for residents and businesses using the heavily traveled James H. McGee Boulevard. Construction work will resurface the boulevard and make re | Pavement Improvement | 2010-04-26 | 2010-03-29 | 2010-10-29 | 2011-07-01 | 1129110.32 | 0.310
9340 | Completed | C220,C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090520 | In the Central Business District in Dayton-Add gateway features, resurface, curb and sidewalk repair, add tree lawn on several main corridors. | Pavement Improvement | 2010-06-09 | 2010-05-17 | 2010-10-29 | 2011-06-28 | 3308898.95 | 2.190
9341 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E090523 | New Box Beam Superstructure replacement over the Tuscarawas River | Bridge Replacement | 2010-03-03 | 2010-03-01 | 2010-07-31 | 2010-08-31 | 747654.5 | 0.010
9342 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E090524 | This is to resurface Tod Ave. from south corp. limits to West Market St in Warren | Pavement Improvement | 2010-05-17 | 2010-06-04 | 2010-09-30 | 2010-07-30 | 342500.6 | 1.000
9343 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E090525 | This project is to resurface Hallock Young Road from SR 45 east to Austintown Warren Rd in Trumbull county. | Pavement Improvement | 2010-03-22 | 2010-03-22 | 2010-07-01 | 2010-07-20 | 522779.65 | 0.660
9344 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090526 | Resurfacing from Presidential Drive to Mathews Rd in Mahoning County | Pavement Improvement | 2009-11-12 | 2009-09-14 | 2009-12-31 | 2009-11-04 | 955985.52 | 1.450
9345 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090527 | Resurfacing from SR 616 west to city corp. limits. Also includes Handicap ramps installed with associated sidewalk and curbing, catch basin inlet adjustments. | Pavement Improvement | 2010-03-08 | 2010-03-08 | 2009-09-01 | 2010-06-11 | 291108.46 | 0.890
9346 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E090528 | The EastPointe Industrial Park on State Route 93 in Muskingum County is a 1200 acre business park home to several major distribution centers. This project will construct a left turn lane to accommodat | Pavement Widening | 2010-04-01 | 2010-07-06 | 2010-09-30 | 2010-09-03 | 938610 | 0.700
9347 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E090529 | Zanesville is the county seat for Muskingum County, and this project will improve four major thoroughfares in Zanesville. The streets are Dryden, Pershing, Dresden and Ridge. The project will also imp | Pavement Improvement | 2010-03-08 | 2010-05-24 | 2010-08-31 | 2010-09-25 | 726262.1 | 3.840
9348 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 12 | E090530 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. Bayer and the City of Newark requested Federal Stimulus funds for the replacement of a crossing surface on a | Safety/Traffic Management | 2009-09-01 | 2009-09-25 | 2010-07-31 | 2009-09-28 | 100000 | 0.100
9349 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MORROW |  | 04 | E090531 | The project will replace the traffic signal at US Route 42 and State Route 529 in Cardington in Morrow County. The traffic signal is old and outdated. | Safety/Traffic Management | 2010-01-04 | 2010-03-22 | 2010-07-31 | 2010-05-28 | 85000 | 0.020
9350 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | MARION |  | 04 | E090532 | Marion County is in a unique position in that its industrial base is on the west side of the county, yet the major route for moving commerce is located on the east side of Marion. The Northwest Indust | New Construction | 2010-01-04 | 2009-12-14 | 2010-12-31 | 2011-10-14 | 5100000
9351 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MADISON |  | 15 | E090533 | Xenia Road is also County Road 12 in the southern part of Madison County between the Clark County line and State Route 56 near London. This project will replace the bridge that is currently deficient. | Bridge Replacement | 2010-03-30 | 2010-05-24 | 2010-12-31 | 2010-08-18 | 393680 | 0.100
9352 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 12 | E090534 | This project is to rehabilitate Camp Chase Railroad's railroad bridge over West Broad Street (US40) in Franklin Co. This work will encompass concrete patching, replacement, painting, vegetation contr | Other | 2010-03-31 | 2010-05-01 | 2010-10-01 | 2010-12-08 | 300000
9353 | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 15 | E090535 | As part of the City of Columbus Capital Improvement plan, the project will convert several one-way downtown streets to accommodate both directions of traffic in an effort to be more user friendlier fo | Pavement Widening | 2010-04-19 | 2010-04-20 | 2011-12-31 | 2011-11-09 | 5500000 | 0.770
9354 | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 12 | E090536 | Parsons Avenue and Livingston Avenue surround the campus of Nationwide Children?s Hospital in Columbus. This project widens Livingston Avenue between Ohio Avenue and Ninth Street and Parsons Avenue be | Pavement Widening | 2010-06-01 | 2010-06-21 | 2012-07-31 | 2011-10-31 | 15804875.51 | 1.080
9355 | Completed | C200,C230 | Highway Infrastructure Investment Grant | OHIO | DELAWARE | COLUMBUS | 12 | E090537 | The project connects a recently constructed commercial shopping area with the US 36 corridor and provides the surrounding properties with improvements and necessary access for additional development o | New Construction | 2010-04-21 | 2010-05-07 | 2011-09-30 | 2010-12-30 | 3465177 | 0.350
9356 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E090540 | Install pavement markings on Mall Road and Banfield Road to increase safety. These are two of Belmont County highest volume of traffic roadways, and the pavement markings are very hard to maintain, be | Pavement Improvement | 2010-06-11 | 2010-08-22 | 2010-09-30 | 2010-08-30 | 27848.41 | 1.300
9357 | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 06 | E090541 | Install a traffic control device at the intersection of State Route 7 and State Route 148 in the village of Powhatan Point. There are currently stop signs at this intersection because the traffic sign | Safety/Traffic Management | 2009-06-11 | 2009-06-11 | 2010-10-01 | 2010-12-08 | 122000 | 0.020
9358 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | CARROLL |  | 18 | E090542 | The project will install new energy efficient traffic signals with integrated traffic demand devices in an effort to reduce traffic idling and fuel waste. With the installation of five new traffic sig | Safety/Traffic Management | 2009-06-05 | 2009-06-05 | 2010-10-01 | 2011-08-03 | 565794.25 | 0.100
9359 | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | HOLMES |  | 18 | E090543 | Repair and resurface over a mile of State Route 39 from Grant St. to Port Washington Rd. in the village of Millersburg as well as two miles of State Route 83 from Jackson St. to the western village co | Pavement Improvement | 2010-01-07 | 2010-04-01 | 2010-10-01 | 2010-10-19 | 222266.93 | 13.070
9360 | Underway | C200,C240 | Highway Infrastructure Investment Grant | OHIO | JEFFERSON |  | 18 | E090544 | SR 43 (Washington St) was built with concrete pavement in 1973 and is currently in very poor condition. The roadway is a four-lane, east-west arterial through the city, carrying approximately 15-18,00 | Pavement Improvement | 2009-08-07 | 2010-08-05 | 2011-09-30 |  | 6713765.5 | 1.090
9361 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TUSCARAWAS |  | 18 | E090545 | Renovation of three existing bridges on the county system, including steel beam repair and painting, deck repair, repair of waterproofing, and repair of wearing surface. The three bridges are located | Bridge Replacement | 2010-03-17 | 2010-05-07 | 2010-10-01 | 2010-09-28 | 1178514.5 | 0.100
9362 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | ADAMS |  | 02 | E090547 | This project calls for resurfacing County Road 70 (Lloyd Road) and County Road 18 (Blue Creek Road), for a total of 0.90 miles of a Rural Major Collector Route and 4.38 miles of a Rural Minor Collecto | Pavement Improvement | 2010-03-19 | 2010-06-02 | 2010-06-30 | 2010-06-28 | 101066.97 | 0.950
9363 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ROSS |  | 07 | E090548 | The project will rehabilitate and correct deficiencies of the U.S Rail in the city of Jackson. This rail service is crucial for business in rural, Appalachian Ohio serving two of the poorest counties, | Safety/Traffic Management | 2009-12-02 | 2009-12-02 | 2010-12-31 | 2010-12-11 | 1775347.21
9364 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | SCIOTO |  | 06 | E090549 | It is proposed to resurface approximately 10 miles of roadway along county roads 28, 53, 1, 163 and 15. The project also includes milling where necessary, signs and pavement marking installation. This | Pavement Improvement | 2010-04-21 | 2010-07-01 | 2010-06-30 | 2010-08-30 | 1200000 | 8.670
9365 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | HENRY |  | 05 | E090553 | The replacement and widening of the existing bridge along Oakwood Avenue in Napoleon will restore legal load limits to the structure, allowing for larger vehicles and trucks to use this potential haul | Bridge Replacement | 2009-08-19 | 2009-08-31 | 2009-11-27 | 2010-10-11 | 400000 | 0.010
9366 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | FULTON |  | 05 | E090554 | Resurfacing of State Route 66, S. Defiance Street, within the Village of Archbold from West Barre Road (CR C) north to the Norfolk-Southern Railway. This section of roadway was reconstructed by ODOT i | Pavement Improvement | 2010-03-17 | 2010-05-24 | 2010-07-30 | 2010-10-15 | 240000 | 0.420
9367 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E090556 | Otter Creek Road is an important trucking route. This $3 million project reconstructs the concrete pavement and adds a new asphalt overlay to Otter Creek Road between Corduroy Road and Bay Shore Road, | Pavement Improvement | 2010-02-17 | 2010-04-12 | 2010-10-15 | 2011-07-15 | 2998709.1 | 2.160
9368 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | OTTAWA |  | 09 | E090557 | This outdated bridge was built in 1954. By upgrading and rehabilitating this bridge, carrying Billman Road over Cedar Creek in Allen Township, this bridge will safely carry traffic in Allen Township f | Bridge Replacement | 2010-06-02 | 2010-08-01 | 2010-07-30 | 2011-06-24 | 292365 | 0.010
9369 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | WILLIAMS |  | 05 | E090558 | Construction of this overhead bridge crane and conveyor system will render the Port Authority's Intermodal Facility fully operational. This bridge crane will be able to transload cargo from a barge on | Other | 2010-04-14 | 2010-05-17 | 2010-10-15 | 2010-10-19 | 393610.42 | 0.000
9370 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E090559 | Norfolk Southern is committed to revise the layout of Airline Yard to increase the capacity from 30,000 lifts per year to 60,000 lifts per year, while minimizing any disruption of the adjacent rail li | Other | 2010-07-01 | 2010-07-01 | 2012-03-01 |  | 6814000
9371 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090560 | This is a project to upgarde signalization at 13 intersections in Lucas County and to perform necessary related work. | Safety/Traffic Management | 2009-09-14 | 2010-03-17 | 2009-12-18 | 2010-08-27 | 420000 | 0.010
9372 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | WOOD | TOLEDO (MI) | 09 | E090562 | This is a project to improve lighting from intersection of Bacon St & SR-65 to 2600 feet northeast, in the City of Rossford. | Safety/Traffic Management | 2010-05-10 | 2011-03-07 | 2010-08-13 |  | 219270 | 0.490
9373 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E090563 | This project will replace the Gibbs Road Bridge in Norwalk Township, east of the City of Norwalk. There is minimal road work involved; however the existing bridge is in poor condition. The ODOT bridge | Bridge Replacement | 2009-12-17 | 2010-03-12 | 2010-10-29 | 2010-05-25 | 208590.24 | 0.050
9374 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E090564 | The project will replace the deteriorated Ogan Rd Bridge, west of the Village of Wakeman. The existing 1-span steel beam bridge has a clear span of 28' and a width of 20'; has a bridge rating of 3P7 a | Bridge Replacement | 2009-07-09 | 2009-07-20 | 2010-10-29 | 2009-10-07 | 220000 | 0.130
9375 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 13 | E090565 | The project proposes to mill and resurface 0.422 miles of South Broadway Ave., between Cooper Foster Parkway (State Route 611) and the State Route 2 interchange, in the City of Lorain. Other work incl | Pavement Improvement | 2010-04-29 | 2010-05-07 | 2010-10-29 | 2010-07-06 | 530931.78 | 0.780
9376 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 13 | E090566 | Repair, Reconstruct and Resurface about 1.4 miles of Gateway Blvd., from Lake Ave. to Infirmary Rd. The roadway varies from 2 to 3 lanes (24 to 36 feet wide). This is a major arterial through the city | Pavement Improvement | 2010-03-15 | 2010-05-07 | 2010-10-29 | 2010-11-10 | 584998 | 1.220
9377 | Underway | C220,C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 13 | E090567 | The project involves the continued re-development of Lorain?s waterfront on a portion of a U.S. Army Corps of Engineers 58-acre dredge disposal site. The project is part of a plan to diversify Lorain? | Transportation Enhancements | 2009-09-14 | 2010-06-24 | 2010-10-29 |  | 3281892.16
9378 | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | RICHLAND |  | 04 | E090568 | This project will renovate approximately 4700 centerline feet of existing streetscape in downtown Mansfield, including widening a section of State Route 430 and improving traffic congestion near State | Transportation Enhancements | 2010-04-08 | 2010-03-26 | 2010-10-29 | 2011-04-06 | 960808.05 | 1.060
9379 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | RICHLAND |  | 04 | E090569 | Project consists of construction of approx. 3000' of new 29' curb & gutter street for an industrial park. Approx. 500' of existing street will be rebuilt on new vertical alignment to provide a safer i | New Construction | 2010-02-11 | 2010-04-12 | 2010-10-29 | 2010-12-02 | 1284248.88 | 1.080
9380 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E090570 | This project involves overhauling and rehabilitating the overpasses carrying Zane Grey Road (County Road 199) and Moose Eye Road (County Road 436) over Interstate 70. To ensure continued safety for tr | Bridge Improvement | 2009-08-19 | 2009-08-31 | 2010-07-31 | 2010-07-23 | 1643207.67 | 0.080
9381 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090574 | Union Boulevard from I-70 to National Road-Smooth sealing of the roadway. | Pavement Improvement | 2009-08-12 | 2009-09-17 | 2010-12-15 | 2009-11-04 | 200000 | 1.500
9382 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090575 | This project is to pave Evanston Road from CR 25A easterly to the CSX RR tracks in Tipp City. | Pavement Improvement | 2009-09-03 | 2009-08-29 | 2009-09-30 | 2009-12-14 | 205140.12 | 1.590
9383 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090576 | Plane and resurface West Stanfield Road from South Stanfield Road to 300' west of Industry Court. | Pavement Improvement | 2009-10-07 | 2009-10-16 | 2009-11-15 | 2010-03-24 | 76473.59 | 0.250
9384 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090577 | Plane and resurface South Stanfield Road from State Route 41 to West Stanfield Road. | Pavement Improvement | 2009-10-07 | 2009-10-16 | 2009-12-15 | 2010-03-24 | 102667.4 | 0.380
9385 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090578 | Wilmington Pike from Smithville Road to the Kettering North Corp Line -Mill the existing roadway, repair concrete pavement base, resurface and install new pavement markings, including raised pavement | Pavement Improvement | 2009-11-10 | 2009-11-03 | 2010-07-02 | 2010-08-13 | 504277.85 | 1.000
9386 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090579 | Various locations in Huber Heights-Rehab pavement at the following locations: Taylorsville Road from State Route 202 to Gentry Lane and from Wildcat Road to Timbercrest Drive; Powell Road from the wes | Pavement Improvement | 2009-11-23 | 2010-05-03 | 2010-06-15 | 2010-08-13 | 445399.26 | 0.530
9387 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090580 | Maue Road from Heincke Road to Byers Road-Pavement milling, adjustment of valve boxes and manholes, crack sealing and asphalt overlay, and new pavement markings. | Pavement Improvement | 2010-05-12 | 2010-05-17 | 2010-06-08 | 2010-11-02 | 389400 | 1.190
9388 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090581 | Olive Road from Salem Avenue to Main Street-Repair existing curbs as needed, pavement planing, full depth repairs, pavement overlay, new curbs and pavement markings. | Pavement Improvement | 2010-06-08 | 2010-07-19 | 2010-06-18 | 2011-06-08 | 792000 | 1.990
9389 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090582 | Stonequarry Road from the Vandaila West Corp Line to the East Line of the Ashbury Farms Subdivision-Mill and resurface the roadway, water valves and manholes will be adjusted to grade, construct ADA c | Pavement Improvement | 2010-04-14 | 2010-05-17 | 2010-05-31 | 2010-07-13 | 267455.37 | 1.150
9390 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090583 | Wolf Creek Street from McMaken Lane to Market Street-Mill and overlay roadway, including restriping and improving curb ramps. | Pavement Improvement | 2009-10-01 | 2010-04-28 | 2009-10-30 | 2010-06-18 | 200000 | 1.430
9391 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090584 | Spinning Road from Airway Road to Linden Avenue-Slurry seal of the existing pavement with some full depth base repairs, utility manhole and valve adjustments and thermoplastic striping. | Pavement Improvement | 2010-01-08 | 2010-03-24 | 2010-05-31 | 2010-10-08 | 331397.73 | 2.030
9392 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090585 | Paragon Road from Congress Park to Normandy Road and Paragon Road from Alex-Bell Road to Grants Trail-Street resurfacing. | Pavement Improvement | 2009-10-27 | 2010-05-07 | 2009-10-15 | 2010-06-02 | 205282 | 0.720
9393 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090587 | Various locations in the City of Clayton-Install up to 179 handicap accessible ramps in two areas in the city. | Transportation Enhancements | 2010-03-16 | 2010-04-05 | 2010-05-31 | 2010-06-18 | 244468.08
9394 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090588 | West Central Avenue from Miami Avenue to Walnut Street and Miami Avenue from Central Avenue to Hydraulic Road-Pavement planing and repaving to eliminate rutting and support heavy loads. Sections of cu | Pavement Improvement | 2010-03-05 | 2010-03-25 | 2010-06-15 | 2010-07-22 | 300960.44 | 0.150
9395 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090589 | Patterson Boulevard/Riverside Drive Bridge over the Great Miami River-Replace backwalls, rehab main superstructure steel immediately adjacent to the backwalls and replace minor bracing members adjacen | Bridge Improvement | 2010-03-17 | 2010-05-03 | 2010-11-29 | 2010-11-19 | 460800 | 0.030
9396 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090590 | Little York Road Bridge over the Great Miami River-Replace the prestressed box beams due to beam delaminations and strand failure. | Bridge Replacement | 2010-05-27 | 2010-08-23 | 2010-11-05 | 2011-01-27 | 1294397.88 | 0.500
9397 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090591 | Shoup Mill Road Bridge over the Stillwater River-Remove paint from the structural steel and reapply. Repair damaged guardrail. | Bridge Improvement | 2010-04-26 | 2010-07-06 | 2010-11-30 | 2011-01-27 | 575674.23
9398 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090592 | Bigger Road from State Route 725 to the Centerville North Corp Line-Mill and resurface the existing roadway, maintenance to the curb, sidewalk and shared use path. Upgrade ramps to meet ADA compliance | Pavement Improvement | 2009-10-22 | 2009-10-12 | 2010-07-12 | 2010-07-02 | 638526 | 1.040
9399 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090593 | Washington Road from a point 1,200' north of State Route 41, north to Drake Road-Shoulder stabilization and asphalt overlay. | Pavement Improvement | 2010-03-10 | 2010-05-19 | 2010-07-30 | 2010-07-26 | 771717.64 | 1.000
9400 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090594 | Plane and resurface North Elm Street from State Route 41 to the Troy City Limits. | Pavement Improvement | 2009-10-07 | 2009-10-05 | 2009-11-30 | 2009-10-28 | 148373.42 | 0.380
9401 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090595 | Various locations in Oakwood-Replace current curb ramps with ADA compliant ramps and associated work. | Safety/Traffic Management | 2010-01-07 | 2010-04-05 | 2010-05-31 | 2010-06-30 | 184209 | 2.840
9402 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090598 | This project is for the rehabilitation of Main Street between I-277 and Firestone Blvd. This I-277 Corridor project involves reconstruction of four lanes of pavement on South Main Street in South Akro | Pavement Improvement | 2010-05-26 | 2010-08-02 | 2011-06-30 | 2011-11-15 | 4775323.77 | 0.620
9403 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 11 | E090599 | This project is to repair the bridge surface and sidewalks on the Center Street Lift Bridge over the Cuyahoga River channel in the City of Cleveland. | Bridge Improvement | 2010-05-21 | 2010-05-27 | 2010-09-30 |  | 2845462.91 | 0.100
9404 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 11 | E090600 | This project consists of the reconstruction of E. 12th Street between from Superior Avenue to Chester Avenue in the City of Cleveland. Work includes removal of existing sidewalk, pavement planning and | Transportation Enhancements | 2010-06-08 | 2010-04-20 | 2010-09-30 |  | 413619.14 | 0.490
9405 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 11 | E090601 | In Cleveland, this project is to rehabilitate the Willow Street bridge over the Cuyahoga River channel | Bridge Improvement | 2010-04-23 | 2010-04-23 | 2010-09-30 |  | 3392348.88 | 0.030
9406 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LICKING | COLUMBUS | 12 | E090604 | This project is in downtown Pataskala, Sidewalks, install ADA ramps and replace sidewalks. | Safety/Traffic Management | 2010-04-14 | 2010-04-26 | 2010-07-31 | 2010-08-05 | 184218.24 | 0.890
9407 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E090605 | In Franklin County, resurfacing and pavement reconstruction of various roadways. Locations include Alkire Road from MAD County to Big Darby Creek; Brice Road from Chatterton Road to Refugee Road; Cas | Pavement Improvement | 2009-10-06 | 2009-09-11 | 2010-10-01 | 2010-02-15 | 1856743.46 | 12.870
9408 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090606 | This project is along Alum Creek near Sunbury Rd from Mock Rd to Innis Rd at Innis Park. MORPC stimulus project funded 100% up to $3.0 M2.2 mile Muliti-use path, including three bridges and two neigh | Transportation Enhancements | 2010-01-26 | 2010-02-08 | 2011-10-15 | 2011-05-31 | 3000000
9409 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090607 | This project is in Reynoldsburg. Trail from Civic Park trailhead to Blackoak Drive. Civic Park multi-purpose trail.Blacklick Creek Greenway mulit-use path from Civic Park trailhead to Blackoak Drive. | Transportation Enhancements | 2010-04-29 | 2010-07-06 | 2011-06-01 | 2010-09-24 | 317219.2
9410 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E090609 | Approximately 9000' of new sidewalks on school bus routes. Glenn Avenue: Tremont to Northwest; Waltham Road: Hampshire Road to Cambridge Blvd; Tremont Road: Pemberton Drive to Private Road; Mountview | Transportation Enhancements | 2010-01-04 | 2010-03-30 | 2010-11-01 | 2010-07-15 | 416000
9411 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090610 | This project is in New Albany. Intersection of SR-605 and Walton Parkway. Install a new traffic signalization systsem including posts and mast arms. Repair pavement deficiencies, overlay 1.5" asphalt | Safety/Traffic Management | 2010-01-26 | 2010-04-01 | 2010-11-01 | 2010-10-15 | 343813.26 | 0.050
9412 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E090611 | This project is in Hilliard. Intersection of CR-3/Avery Rd and Northwest Parkway. Intersection upgrade including sidewalks, multi-use path, and street lighting - Avery Rd and Norwest Pkwy. | Pavement Improvement | 2010-03-26 | 2010-04-05 | 2011-06-01 | 2010-12-13 | 1000000 | 0.020
9413 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090612 | This project is in Plain Twp. CR546/Dublin Granville Rd over Sugar Run. Just W of Harlem Road. Replace superstructure - concrete slab deck and rehab work to abutments and pier. | Bridge Improvement | 2010-04-13 | 2010-08-01 | 2011-06-01 | 2010-10-15 | 355179.7 | 0.010
9414 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | DELAWARE | COLUMBUS | 12 | E090613 | Replace deck and superstructure members.Modify or replace bridge abutments.Possible piers work, minor roadway approach work, guardrail replacement. Vilage of Galena. South Old 3C Highway over Hoover R | Bridge Improvement | 2010-01-21 | 2010-07-06 | 2010-10-01 | 2010-09-30 | 659753 | 0.040
9415 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090614 | This project is in Whitehall. From Broad St to Mayflower Blvd. Yearling Road Reconstruction Phase 3Signalization, street lighting, storm sewer, ADA sidewalk, and traffic signal improvements. | Pavement Improvement | 2010-04-21 | 2010-05-03 | 2011-09-01 | 2010-10-21 | 2258044.16 | 0.450
9416 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090615 | This project is in Blendon Twp. CR-18/Central College Rd over Big Walnut Creek. 0.27 mi E of Sunbury Rd. MORPC funded stimulus project for $960,000.Replace existing superstructure - prestressed box b | Bridge Improvement | 2010-03-17 | 2010-04-19 | 2011-06-01 | 2010-08-01 | 910000 | 0.080
9417 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090616 | This project is in Bexley. Urban core ADA Accessibility.Sidewalks, curb ramps, sidewalk improvements, and traffic signal improvements for better ADA accessibility. | Transportation Enhancements | 2010-03-15 | 2010-04-19 | 2011-09-01 | 2011-11-08 | 800779.9 | 2.430
9418 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090633 | This is a project to rehabilitate George Hardy Dr., From Tiffin Ave to Saint Lawrence Dr in the Port of Toledo; and to perform necessary related work | Pavement Widening | 2010-03-29 | 2010-05-07 | 2010-08-13 | 2010-10-20 | 901337.85
9419 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090634 | This is a project to mill and fill Illinois Ave (US-20A) in the City of Maumee from Ford St to west of Conant St (US-20) and to perform necessary related work. | Pavement Improvement | 2010-02-11 | 2010-05-31 | 2010-07-30 | 2010-06-15 | 448004 | 0.860
9420 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WOOD | TOLEDO (MI) | 05 | E090635 | This project is to resurface S. Main St (SR-25) in the City of Bowling Green from Clay St to Dill Ave; The project includes some curb and curb ramp replacements. The sidewalk on the east side | Pavement Improvement | 2010-03-17 | 2010-06-03 | 2010-08-31 | 2010-10-15 | 501851.88 | 0.450
9421 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090636 | This project is to to resurface Hill Ave, in the City of Toledo, from Westwood Ave to Detroit Ave. | Pavement Improvement | 2009-11-09 | 2010-03-29 | 2010-11-19 | 2010-09-21 | 1175000 | 0.830
9422 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090637 | This project is to resurface South Ave, in the City of Toledo, from Airport Hwy (SR-2) to Detroit Ave (US-24) | Pavement Improvement | 2009-11-17 | 2010-05-10 | 2010-05-21 | 2010-06-22 | 202522 | 0.210
9423 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WOOD | TOLEDO (MI) | 09 | E090638 | This project is to improve the intersection of Curtice Rd and Bradner Rd in the City of Northwood | Safety/Traffic Management | 2010-04-27 | 2010-06-11 | 2010-06-11 | 2010-11-08 | 61506 | 0.010
9424 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090639 | The project includes rehabilitating the existing Frank Boulevard including a reconstructed intersection with White Pond Drive | Pavement Improvement | 2010-06-03 | 2010-04-19 | 2010-12-31 | 2011-05-11 | 2156644.31 | 0.440
9425 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090650 | This project is on Galbraith from Deer Park West Corp line to Blue Ash Road to resurface and restore pavement, curbs, improve drainage, and replace traffic loops | Pavement Improvement | 2009-12-10 | 2010-03-29 | 2010-07-02 | 2010-10-28 | 523840 | 0.540
9426 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090653 | This project involves Troy Ave and Morse Road. Resurfacing, curb replacement, base repairs, inlet reconstruction and storm sewer to restore roadway intergrity and ride quality and improve drainage. | Pavement Improvement | 2010-01-07 | 2010-03-29 | 2010-09-15 | 2010-09-15 | 207799.43 | 0.350
9427 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E090656 | There are four interrelated and interdependent highway infrastructure projects within this important regional transportation center. The project along SR 45 begins at the intersection of I-90 and SR 4 | Safety/Traffic Management | 2010-06-15 | 2010-08-03 | 2010-12-31 | 2011-12-15 | 622073 | 0.130
9428 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E090658 | Reconstruction and paving of North Eagle Street in the city of Geneva. | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2010-09-30 | 2010-09-01 | 450000 | 0.500
9429 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E090659 | This project is for the resurfacing and improvements to Middle Road. The area is heavily traveled and located in a major manufacturing area. | Pavement Improvement | 2010-05-05 | 2010-06-09 | 2010-09-30 | 2010-09-20 | 769764 | 4.680
9430 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E090660 | The Norfolk Southern Line relocation entails the relocation of rail line in conjunction with the $900,000,000 steel mill expansion. The project will free up 100 acres for future growth and development | Safety/Traffic Management | 2009-11-02 | 2009-11-06 | 2011-12-15 | 2010-06-11 | 3464899.32
9431 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090661 | The Fulton Road/Park Dr. NW Intersection Improvement includes the widening and addition of turn lanes to Park Drive north and south of Fulton Rd. NW; full width road pavement reconstruction with concr | Safety/Traffic Management | 2010-04-01 | 2010-05-03 | 2010-09-30 | 2011-01-26 | 368994.98 | 0.010
9432 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090662 | The Sherrick Road stabilization project includes the injection of High Density Polyurethane (HDPE) Foam columns to stabilize the sanitary sewer trench; install ADA compliant curb ramps; and the profil | Pavement Improvement | 2010-02-17 | 2010-05-03 | 2010-12-01 | 2010-08-20 | 1072305.53 | 0.720
9433 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090663 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project will involve three (3) crossings in Hartville and the surrounding area. One of the crossings wa | Safety/Traffic Management | 2009-11-12 | 2009-11-12 | 2010-08-31 |  | 540000 | 0.010
9434 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090664 | This project is Wheeling Lake Erie Rail Line track rehabilitation in Stark, Portage, Jefferson, Wayne, Lorain, Tuscarawas, and Cuyahoga counties | Other | 2009-09-08 | 2009-09-08 | 2010-12-15 | 2010-10-22 | 1200000
9435 | Underway | C220,C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090665 | The city of Akron is proposing to hydro-demo and resurface approximately 24,500 squar yards of the Y-Bridge deck from Perkins to the northern limits of the bridges along with other minor associated br | Bridge Improvement | 2009-11-25 | 2010-03-29 | 2011-05-01 |  | 6326527.82 | 0.920
9436 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090666 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. The communities of Hudson, Macedonia and Northfield Center requested Federal Stimulus Funds to pursue a quie | Safety/Traffic Management | 2010-03-03 | 2010-06-02 | 2011-03-03 | 2010-11-04 | 168323 | 0.010
9437 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E090668 | Resurfacing Olive St from Ohio Ave to northern corp. limits in the Village of McDonald | Pavement Improvement | 2009-11-12 | 2010-01-04 | 2010-08-01 | 2010-05-13 | 182752.56 | 0.500
9438 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090669 | Resurfacing 12th street from Robinson Rd to Coitsville Rd in the city of Campbell. | Pavement Improvement | 2009-11-25 | 2009-12-23 | 2010-09-01 | 2010-06-11 | 335339.66 | 1.220
9439 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090677 | This project involves Dining Lane to Catalina Apartments west driveway. Resurface, curb replacement, base repairs and inlet reconstruction to restore roadway integrity and ride quality and improve dr | Pavement Improvement | 2010-01-08 | 2010-03-29 | 2010-09-15 | 2010-08-20 | 239881.89 | 1.100
9440 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090679 | This project consists of 2 parts. Part one will replace a 700 foot bridge over the Scioto River with minimal appraoch work. This new bridge will connect to Rich Street and to reconstruct Washington Bl | Pavement Improvement | 2010-02-19 | 2010-03-03 | 2011-08-31 |  | 2076961.6 | 0.210
9441 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | PORTAGE | AKRON | 14 | E090680 | This project is to replace or rehabilitate the bridge over the Cuyahoga River and CSX. It will also improve the Crain Ave intersection | Bridge Replacement | 2009-07-31 | 2009-09-18 | 2012-12-01 |  | 3000000 | 0.090
9442 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ROSS |  | 18 | E090681 | State Route 104 is currently a two-lane highway between U.S. Route 35 and the new state Route 207 extension to U.S. Route 23, and it serves as the northwest bypass of Chillicothe. The project consists | Pavement Improvement | 2009-07-01 | 2009-07-02 | 2010-09-30 | 2010-10-31 | 6530215.42 | 3.760
9443 | Underway | C200 | Highway Infrastructure Investment Grant | OHIO | HOCKING |  | 06 | E090683 | This is part 2 of 3 for the Nelsonville By-Pass Project. The portion of this project is for preliminary engineering and right of way activities. | New Construction | 2009-09-29 | 2009-10-07 | 2012-03-03 |  | 45547525.57 | 4.560
9444 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090684 | In Lucas county, widening of Wheeling Street from Navarre (SR2) to Pickle Road. This includes widening the bridge over I-280 in the City of Oregon | Pavement Widening | 2010-05-05 | 2010-06-21 | 2011-11-18 |  | 1533310.28 | 0.510
9445 | Completed | C220,C200 | Highway Infrastructure Investment Grant | OHIO | DEFIANCE |  | 05 | E090685 | This project is to widen and add concrete islands to SR-66 corridor through Defiance. This activity will reduce the high rate of accidents caused by unsafe turning along the city?s busiest business c | Pavement Widening | 2010-02-02 | 2010-02-24 | 2010-10-31 | 2010-11-12 | 3193503.37 | 1.440
9446 | Underway | C240,C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E090686 | Construct a grade separation at Columbia Road (SR-252) and the CSX Railroad Company tracks in the City of Olmsted Falls, from north of Sprague Road to the Ohio Turnpike (IR-80). | New Bridge Construction | 2009-03-27 | 2009-07-21 | 2011-06-30 |  | 7693000 | 0.350
9447 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 12 | E090687 | This project provides for the realignment and reconstruction of Waterworks Road and Deo Drive at State Route 13 and relocation and improvement the existing Railroad crossing. | Safety/Traffic Management | 2010-03-31 | 2010-04-08 | 2010-10-31 | 2010-11-05 | 1800000 | 0.500
9448 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | HOCKING |  | 06 | E090688 | The US 33 Corridor is a designated National Highway System route that extends from Michigan to Virginia and includes the Nelsonville Bypass. This construction project will focus on the west end of a n | New Construction | 2009-09-14 | 2009-09-21 | 2012-03-03 |  | 94317302.53 | 3.040
9449 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | UNION | COLUMBUS | 07 | E090691 | This project takes place at the Intersection of SR-161, CR1(Industrial Parkway) and CR24 (Post Rd). MORPC stimulus project for $1,000,000.Realignment of 2050' of Industrial Parkway on north side of S | New Construction | 2009-11-02 | 2009-11-15 | 2012-10-01 | 2011-07-29 | 1000000 | 0.820
9450 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090692 | Resurfacing from Main St to Beloit Village limit with ADA compliant intersections. | Pavement Improvement | 2009-08-04 | 2009-08-27 | 2009-10-30 | 2009-10-06 | 161158.41 | 0.750
9451 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 12 | E090703 | The project begins at SR79 at the intersection of South High Street and terminates at the North end in a cul-de-sac created when the new SR79 was created. A two lane roadway (formerly SR79) passes thr | Pavement Improvement | 2010-02-16 | 2010-05-17 | 2010-08-31 | 2010-08-02 | 335989.27 | 1.720
9452 | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | SHELBY |  | 08 | E090705 | This project is to install new curb ramps and driveway aprons using brick pavers & stamped concrete on State Street in Shelby County. | Transportation Enhancements | 2011-01-28 | 2011-03-21 | 2011-11-15 | 2011-11-03 | 374306 | 0.140
9453 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LAKE |  | 14 | E090708 | This section of four lane roadway, which is on the federal aid system, was rated in the ?poor? category during a 2006 pavement condition rating performed by our local Metropolitan Planning Organizatio | Pavement Improvement | 2010-06-02 | 2010-06-07 | 2010-09-30 | 2011-03-07 | 2528188.52 | 3.030
9454 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | PREBLE |  | 08 | E090709 | Replace small culvert; existing culvert is an 84? by 40? cast-in-place concrete culvert in Preble county | Pavement Improvement | 2009-06-19 | 2009-07-31 | 2009-08-15 | 2009-08-07 | 129940.63 | 0.010
9455 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090710 | In Butler county, resurface sections of Tylersville and River Roads and replace striping. | Pavement Improvement | 2009-08-05 | 2009-09-08 | 2010-04-02 | 2009-12-08 | 1857217.45 | 6.000
9456 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CLERMONT | CINCINNATI (KY) | 02 | E090711 | This project is to resuface county roads in Clermont county and add curb and ADA curb ramps on Buckwheat Road | Pavement Improvement | 2009-10-20 | 2009-08-26 | 2010-06-11 | 2009-12-18 | 2464300 | 32.480
9457 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090712 | Construct second phase of Access Road from Union Road to State Route 380, south and west of US 35 and Route 68 interchange. | New Construction | 2009-11-06 | 2009-12-14 | 2011-04-18 | 2011-07-15 | 1350905.49
9458 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090713 | Overlay of pavement, striping and berm repair of Valley Road from Upper Bellbrook Road to US 35 | Pavement Improvement | 2009-09-02 | 2009-09-11 | 2010-04-16 | 2009-09-18 | 182714.87 | 1.790
9459 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090714 | This project is to resurface a portion of Blue Rock Road in Hamilton county. This will include base repair and replacing guardrail. | Pavement Improvement | 2010-03-17 | 2010-04-19 | 2010-05-30 | 2010-10-15 | 500000 | 1.350
9460 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090715 | This project is to microsurface Cornell Road from the bridge over I-71 to the bridge over I-275. This will include new pavement marking and curb ramps. | Pavement Improvement | 2009-09-29 | 2009-09-18 | 2010-05-01 | 2009-10-16 | 95520.86 | 0.680
9461 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090716 | Resurface a portion of the Reed Hartman Hwy. Also, perform pavement repair, curb & gutter repair, replace signal loops with video detection, replacing pavement striping, place new RPMs, and where ap | Pavement Improvement | 2009-08-12 | 2009-08-10 | 2010-04-02 | 2009-11-13 | 675121.57 | 1.200
9462 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WARREN | CINCINNATI (KY) | 02 | E090717 | Resurfacing of Kings Island Drive from the theater entrance to Western Row Road. | Pavement Improvement | 2009-11-25 | 2009-11-16 | 2010-03-17 | 2010-05-06 | 307880 | 1.200
9463 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090718 | This project is for resurfacing, curb replacement, base repairs and inlet reconstruction on Harrison Ave from Section Road to Lovell Avenue to restore roadway integrity | Pavement Improvement | 2009-11-06 | 2009-10-09 | 2010-08-13 | 2010-06-01 | 526465.82 | 1.000
9464 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090719 | This project is in the city of Middleton on Sutphin between Grand Avenue to Central Avenue to resurface, spot curb and gutter repair, and ensurecurb ramps to be ADA compliant. | Pavement Improvement | 2010-04-07 | 2010-06-07 | 2010-08-10 | 2010-09-28 | 716542.94 | 0.920
9465 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090720 | This project is in Middleton on University Blvd from Reinartz Blvd. to Briel to resurface, spot curb and gutter repair, and ADA compliant curb ramps | Pavement Improvement | 2010-04-07 | 2010-04-19 | 2010-09-02 | 2010-09-28 | 1920838.04 | 0.380
9466 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WARREN | DAYTON | 03 | E090721 | Various locations on State Route 73 and State Route 741 in Springboro-Replace existing traffic signal lamps with LED lamps. Install three battery backups and interconnect three traffic signals between | Safety/Traffic Management | 2010-01-07 | 2010-08-10 | 2010-12-01 | 2010-12-30 | 173090.66 | 0.010
9467 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WARREN | DAYTON | 02 | E090722 | Franklin-Trenton Road from the Franklin West Corp Line to Park Ave.-Resurface roadway including restriping and making curb ramps ADA compliant. | Pavement Improvement | 2009-12-09 | 2010-04-13 | 2010-06-23 | 2010-05-03 | 201991.86 | 1.800
9468 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090723 | From the intersection of Miami Avenue and South Detroit Street to 150' east of the intersection of Hill Street and South Detroit Street-Realign and widen sidewalks, replacing and aligning curb ramps, | Transportation Enhancements | 2010-04-22 | 2010-03-26 | 2010-12-01 | 2010-04-09 | 17264.36
9469 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WARREN | CINCINNATI (KY) | 02 | E090724 | In Warren county, on Columbia road and various county roads resurface, stripe, and add berm and curb ramp. | Pavement Improvement | 2009-12-09 | 2010-04-02 | 2010-12-01 | 2010-06-17 | 1750678.44 | 1.000
9470 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090726 | In the village of Terrace Park on US 50 from Milford/Terrace Park Corp Line to Elm St. catch basin repair, curb replacement, install curb ramps as required, sidewalk replacement where necessary, impr | Safety/Traffic Management | 2010-03-16 | 2010-03-18 | 2010-09-30 | 2010-09-28 | 716127.65 | 1.400
9471 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090727 | East Main Street from Whiteman Street to Collier Street-Streetscape improvements that include curbs, replacing sidewalks, driveway apron improvements, aesthetic enhancements in the form of tree remova | Transportation Enhancements | 2010-04-23 | 2010-04-19 | 2010-12-01 | 2010-08-23 | 178360.36 | 0.100
9472 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090728 | Colonel Glenn Highway from the west corp. of Beavercreek to National Road-Mill and resurface the roadway. Includes base repairs, pavement markings, restoration of traffic signal loops, curb ramp upgra | Pavement Improvement | 2010-02-02 | 2010-04-06 | 2010-08-13 | 2010-05-28 | 306972.14 | 0.490
9473 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090729 | Creekside Trail from the Beavercreek WCL to the Beavercreek East Corp Line -Resurface the bikepath, install top soil berms, upgrade curb remps at crossing, replace/repair expansion joints on path brid | Transportation Enhancements | 2010-01-27 | 2010-04-19 | 2010-08-13 | 2010-07-28 | 190248
9474 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090730 | On Northland Blvd in Springdale, repair the concrete base, extend the west bound turn lane, widen the east boun turn land, curb replacement, catch basin repair, resurfacing, and a pedestrian walkway. | Pavement Improvement | 2010-04-29 | 2010-04-26 | 2010-12-01 | 2010-10-15 | 876221.37 | 0.820
9475 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090731 | This project is on Mosteller Rd from Sharon Road to 400 ft south of Kemper to resurface, replace curbs, base repairs, and inlet construction | Pavement Improvement | 2010-04-29 | 2010-04-19 | 2010-10-01 | 2011-04-29 | 761565.9 | 1.020
9476 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090732 | In Cincinnati replacement and expansion of the existing computerized traffic control system interconnect cabling. The current cable is telephone grade twisted pair wire and the project will replace th | Other | 2010-04-22 | 2010-07-27 | 2010-09-10 |  | 1148265.13
9477 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090734 | This project is to complete the construction of missing segments of the multi us path within the Oxford Community Park | Pavement Improvement | 2010-04-27 | 2010-05-14 | 2010-10-30 | 2010-08-27 | 184268.82
9478 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E090747 | This project is in Columbus and includes various routes in the City of Columbus. Regional resurfacing program in City of Columbus. | Pavement Improvement | 2009-09-09 | 2009-09-08 | 2010-06-15 | 2010-08-15 | 2308108 | 6.200
9479 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | DELAWARE | COLUMBUS | 12 | E090748 | In Delaware County, resurfacing and pavement reconstruction of various county roads and city streets. Locations include London Road in the City of Delaware from US42 north 0.10 miles; Liberty Street | Pavement Improvement | 2009-10-08 | 2009-10-02 | 2010-10-01 | 2010-05-30 | 1795005 | 14.070
9480 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 11 | E090751 | Widening of the ramp from I-490 eastbound to I-77 northbound and re-facing of the outside parapets on the I-77 bridge over U.S. 422 (Orange Avenue) and East 30th Street. The work includes replacement | Bridge Improvement | 2009-05-18 | 2009-06-02 | 2009-10-31 | 2010-05-14 | 2561008.82 | 0.840
9481 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WOOD |  | 09 | E090752 | This project consists of replacing the current bridge deck surface on the Disalle bridge crossing the Maumee River. Additional bridge work will be performed at Miami Street overpass and railroad bridg | Bridge Improvement | 2009-06-15 | 2009-06-15 | 2010-10-15 | 2011-06-10 | 5585106.13 | 0.820
9482 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HARRISON |  | 18 | E090753 | Three bridges on U.S. 22 (eastbound U.S. 22, westbound U.S. 22, and the westbound on-ramp to U.S. 22) over an abandoned railroad just west of SR 9 in Cadiz Township will be removed and replaced with e | Bridge Replacement | 2009-05-26 | 2009-06-30 | 2009-11-15 | 2010-06-11 | 910619.13 | 0.030
9483 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 12 | E090754 | Resurface two miles of US 40 between Hague Avenue and Central Avenue in Columbus including the ramp from I-70 eastbound to Broad Street and the ramp from Broad Street to I-70 westbound. | Pavement Improvement | 2010-06-01 | 2010-07-06 | 2010-08-31 | 2011-06-09 | 654980 | 1.960
9484 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TUSCARAWAS |  | 18 | E090755 | Resurfacing nearly four miles of U.S. 250 from SR 800 at Dennison to the Harrison County line, and just over a mile of SR 800 from Thornwood Park in Dennison to U.S. 250. | Pavement Improvement | 2009-07-17 | 2009-09-11 | 2009-10-15 | 2010-05-11 | 1039889.3 | 4.990
9485 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LOGAN |  | 04 | E090756 | This project is to resurface Main Street in Bellefontaine from Lake Street (SLM 7.32) to Water Street (SLM 7.94) with asphalt concrete. | Pavement Improvement | 2009-06-25 | 2009-09-16 | 2009-09-15 | 2009-10-13 | 227525 | 0.620
9486 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 10 | E090757 | The project calls for a complete ramp replacement at the Interstate 480/West 130th Street interchange in the city of Cleveland. The work will include a complete replacement of aging pavements. | Pavement Improvement | 2009-08-27 | 2009-09-25 | 2010-06-30 | 2010-05-28 | 782661.35
9487 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | ASHLAND |  | 16 | E090767 | This project will replace the bridge over Jerome Fork on SR89 in Ashland County. | Bridge Replacement | 2009-06-26 | 2009-08-17 | 2010-08-15 | 2010-02-01 | 388030.82 | 0.040
9488 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | PORTAGE | AKRON | 14 | E090769 | This project is to resurface Chestnut street from Ravenna South Corp to State Route 14. | Pavement Improvement | 2010-04-19 | 2010-04-26 | 2010-08-31 | 2010-10-04 | 616000 | 2.570
9489 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | PORTAGE | AKRON | 14 | E090770 | This project is for the consturction of curbs and gutters with some storm sewer on SR 305 from State Route 700 to East Corp limit. | Pavement Improvement | 2010-02-24 | 2010-05-13 | 2010-07-31 | 2010-07-30 | 143600 | 0.480
9490 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090771 | In the City of Norton, Summit County, rehabilitation of 2.59 miles of Greenwich Road beginning at the Medina County line and ending at Cleveland-Massillon Road. Included in the rehabilitation are mill | Pavement Improvement | 2010-03-29 | 2010-03-29 | 2010-09-30 | 2010-07-28 | 483340 | 3.300
9491 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090772 | This project invloves reconstruction, Including traffic signal upgrade on Summit CR 512 from Triplett Boulevard to East Market Street. | Pavement Improvement | 2010-04-19 | 2010-04-05 | 2010-12-31 | 2011-10-15 | 2224006 | 1.160
9492 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090773 | This project invloves Mogadore Road at Cleveland Avenue, with removal of retaining wall, and increasing turning radius. | Safety/Traffic Management | 2010-03-24 | 2010-04-30 | 2010-06-30 | 2010-07-06 | 54729.72 | 0.010
9493 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090779 | This project invloves resurfacing of Liberty Road from Cannon Road to Cuyahoga County line. | Pavement Improvement | 2009-11-06 | 2009-10-05 | 2010-08-31 | 2010-04-30 | 444263.97 | 2.540
9494 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090780 | This project involves Reconstruction and Adding turn lanes on Summit CR 145 from Wyoga Lake Road to Allen Road. | Pavement Widening | 2009-06-05 | 2010-03-01 | 2010-12-31 | 2011-04-11 | 2560000 | 1.170
9495 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090781 | This project involves Wheatley Road at Brecksville Road. Construct turn lanes. Install new traffic signal. Upgrade existing signal. | Safety/Traffic Management | 2010-06-23 | 2010-08-09 | 2010-09-30 | 2011-06-13 | 239800 | 0.030
9496 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | ASHLAND |  | 16 | E090785 | This project will replace a deficient 3-span steel beam bridge over the Muddy Fork on State Route 302, 0.19 mile west of Township Road 63, in Perry Township. This is east of the community known as Red | Bridge Replacement | 2009-06-25 | 2009-08-31 | 2010-07-15 | 2009-11-06 | 424648 | 0.030
9497 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WAYNE |  | 16 | E090786 | This project will rehabilitate a deficient bridge on SR 301 in Wayne county over Interstate 71. | Bridge Improvement | 2009-07-17 | 2010-04-26 | 2010-10-15 | 2011-05-11 | 1485544.8 | 0.010
9498 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090787 | This project is in the city of Monroe to install new signal at Britton and improve signal at intersection of Cincinnati Dayton Road and SR 63 by adding backplates, led heads, and dilemma zone detectio | Safety/Traffic Management | 2010-06-04 | 2010-08-03 | 2010-11-01 | 2011-07-01 | 543960 | 0.290
9499 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E090788 | To provide access to work for low income individuals not able otherwise to hold a job. Some of these services are provided directly by GCRTA and some are contracted to other area transportation provi | Other | 2009-09-23 | 2009-09-23 | 2011-09-23 | 2010-08-31 | 1863358
9500 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090789 | This project is to resurface Telegraph Rd (US-24) from Alexis Rd (SR-184) to just south of the Michigan State Line in the City of Toledo. | Pavement Improvement | 2009-11-09 | 2010-05-05 | 2010-05-28 | 2010-06-18 | 315000 | 0.530
9501 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090790 | This project is to resurface Detroit Ave (US-24) in the City of Toledo from I-75 near Monroe St to Central Ave (SR-120). | Pavement Improvement | 2009-11-09 | 2010-05-07 | 2010-06-04 | 2010-08-31 | 570000 | 0.860
9502 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 10 | E090792 | Track rehabilitation work to reduce derailment expenses and help railroad provide reliable service to two rail-dependent businesses that employ a total of 50 people. | Other | 2010-05-27 | 2010-06-01 | 2010-10-01 | 2010-08-31 | 66988
9503 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | KNOX |  | 18 | E090793 | Knox and Muskingum Counties are considered smaller to medium sized counties with populations that have grown in the last decade. The average driver in these counties spends between 16 and 26 minutes i | Bridge Improvement | 2009-08-28 | 2009-09-04 | 2009-10-31 | 2009-12-03 | 1100000 | 0.460
9504 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LAWRENCE |  | 06 | E090794 | The project will construct access roads to allow for better access handling between Ohio River barges, rail and highway freight and spur the development of the South Point Inter-modal Transfer Facilit | Other | 2010-04-01 | 2010-04-15 | 2010-10-04 | 2011-12-30 | 1211028.62
9505 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090795 | In Hamilton county on Galbraith Rd from Daly Road to Winton, remove and replace pavement with ajacent curbs and sidewalk. Also replace the signal Galbraith and Mockingbird. | Pavement Improvement | 2010-04-23 | 2010-04-29 | 2010-10-15 | 2011-03-30 | 2655491.58 | 0.590
9506 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090797 | The project consists of infrastructure repairs along Woodman Drive from north of US 35 and Linden Avenue to the community of Beavercreek. The improvement work in both areas include milling and asphalt | Pavement Improvement | 2010-03-31 | 2010-05-10 | 2010-05-31 | 2010-12-03 | 1373617.39 | 2.160
9507 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PIKE |  | 02 | E090798 | The project will improve the cloverleaf interchange at U.S. Route 23 and the exit for the Portsmouth Gaseous Diffusion Plant (A-Plant), south of Piketon, by creating access to the west side and into t | Pavement Improvement | 2010-05-03 | 2010-05-19 | 2010-10-31 | 2011-06-16 | 1420005.74 | 0.010
9508 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 05 | E090799 | This project consists of a safety upgrade for quiet zone in North Ridgeville. | Safety/Traffic Management | 2010-10-04 | 2010-10-04 | 2011-12-31 |  | 800000
9509 | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | WAYNE |  | 16 | E090800 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project involves five grade crossings on the W&LE rail line between Smithville and Orrville. All five c | Safety/Traffic Management | 2009-09-16 | 2009-10-20 | 2010-06-17 | 2010-06-13 | 793842.51
9510 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLARK |  | 07 | E090801 | This project expands the existing investment by the State of Ohio and the West Central Ohio Port Authority (WESTCO) by improving bridge and track conditions on the rail lines. | Other | 2009-11-04 | 2009-11-12 | 2011-12-31 | 2010-11-20 | 1000000
9511 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | COLUMBIANA |  | 17 | E090802 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project will install state-of-the-art warning devices and a new high-type grade crossing surface at the | Safety/Traffic Management | 2010-02-18 | 2010-06-04 | 2010-06-30 | 2010-07-02 | 250000
9512 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 13 | E090803 | The City of Medina obtained a long-term lease for this line in 1985, and has been working with numerous public and private partners to rehabilitate the line. Shippers along the line have consistently | Other | 2011-09-23 | 2011-09-23 | 2011-12-31 | 2011-12-21 | 949794.62
9513 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | PORTAGE | AKRON | 14 | E090807 | In the City of Aurora (Portage Co.), widening and resurfacing of 2.15 miles of SR 43 (North Aurora Road) including new storm sewer, curb and gutter, water mains, traffic signals, signing and pavement | Pavement Improvement | 2009-07-17 | 2009-08-31 | 2010-12-31 | 2011-12-15 | 1000000 | 2.010
9514 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA, SUMMIT |  | Multiple | E090808 | This is a two-part project to install a new intelligent transportation system. Part 1 (Cuyahoga, Lorain, Medina, Summit, Portage & Lake Counties) includes the putting in place of approximately 83 traf | Safety/Traffic Management | 2009-08-21 | 2009-10-21 | 2011-09-30 |  | 19895582.82
9515 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LAKE | CLEVELAND, OH | 14 | E090811 | Traffic signal and widening improvements along SR-91 in Willougby Hills. | Safety/Traffic Management | 2010-04-05 | 2010-05-18 | 2010-09-30 | 2011-06-01 | 862360 | 2.380
9516 | Underway | C220 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 10 | E090812 | This project is located in the City of Cleveland on Lorain Avenue between the City of Cleveland west corporation limit and Groveland Avenue. This project is a streetscape improvement that includes new | Transportation Enhancements | 2010-06-08 | 2010-06-14 | 2010-10-30 |  | 1450410.56 | 0.530
9517 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GEAUGA | CLEVELAND, OH | 14 | E090813 | In Geauga county this project will resurface Auburn Road from Kinsman Rd. to Fairmount Rd. in Newbury Twp | Pavement Improvement | 2009-12-01 | 2010-05-24 | 2010-06-30 | 2010-09-01 | 279635.46 | 1.770
9518 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | LAKE | CLEVELAND, OH | 14 | E090820 | This project is to resurface Lake Road in Madison Twp. | Pavement Improvement | 2011-03-10 | 2011-04-04 | 2011-12-02 |  | 557556.82 | 0.890
9519 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E090846 | In Stark County, CR-98, from SR-241(Wales Ave.) to Brunerdale Ave. Widen existing road to four lanes with curb and gutters. Increase to 5 lanes at all major intersections. Includes Storm Sewer and tra | Pavement Widening | 2009-06-15 | 2009-09-21 | 2010-12-31 | 2011-12-01 | 4800000 | 2.540
9520 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090848 | Resurfacing of Fairground Blvd from SR 46 east to city limits. Resurfacing of Herbert Rd from the east city limits to the west city limits. | Pavement Improvement | 2010-03-24 | 2010-05-03 | 2010-08-31 | 2010-06-24 | 300533.64 | 1.150
9521 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STATEWIDE |  |  | E090851 | This project provides long term rail improvements to the State of Ohio-owned Panhandle Rail line including the repair and rehabilitation of bridges, rail and a tunnel. | Other | 2010-04-13 | 2010-06-01 | 2010-10-31 | 2011-06-17 | 7349941
9522 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | STATEWIDE |  |  | E090852 | The project consists of five rail line impediments between Rickenbacker and Sharonville and on-site improvements at the Rickenbacker Terminal that when complete will allow for the movement of double-s | Other | 2010-06-11 | 2010-08-30 | 2012-03-01 |  | 4100000
9523 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | STATEWIDE |  |  | E090854 | Railroad tie replacement and other related track work to rehabilitate RJ Corman-owned lines in Western Ohio. Overall, the RJC Western Ohio lines generated 4,274 (2005), 4,541 (2006), and 3,648 (2007) | Other | 2009-11-18 | 2009-11-30 | 2010-10-31 |  | 1300000
9524 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LICKING | COLUMBUS | 12 | E090856 | The resurfacing of Taylor Rd (TR36) from SR16 north to Havens Corners Rd and the resurfacing of Palmer Road (TR169) from Mink Road west to the Reynoldsburg Corporation. | Pavement Improvement | 2010-03-02 | 2010-06-07 | 2010-11-30 | 2010-08-06 | 421785 | 4.810
9525 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FAIRFIELD | COLUMBUS | 07 | E090857 | The resurfacing of sections or various federal aid routes within Fairfield County - Twsp Rd 223 (Wagram Rd) from Taylor Rd north to the county line. County Rd 13 (Baisl-Western Rd) from CR18 east to C | Pavement Improvement | 2010-05-03 | 2010-07-06 | 2010-11-30 | 2010-07-29 | 514815 | 5.620
9526 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL |  | 13 | E090859 | The Mahoning Avenue Resurfacing and Lighting Project includes resurfacing the asphalt pavement. The alignment will follow existing and include curb ramp construction in accordance with ADA standards. | Pavement Improvement | 2010-05-17 | 2010-08-24 | 2009-12-31 | 2011-01-10 | 490993.73 | 1.720
9527 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E090869 | Planing and resurfacing of 1.78 miles of High Street from Mahoning Ave to Chestnut; incidental curb and walk replacement. | Pavement Improvement | 2010-05-17 | 2010-09-09 | 2010-08-31 | 2010-10-27 | 385300.72 | 0.590
9528 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E090870 | Roadway resurfacing and repair on Trumbull Ave from the City of Girard to SR 193. Roadway resurfacing and repair on West Liberty St from Four Mile Run Rd to Salt Springs Rd. Roadway resurfacing and | Pavement Improvement | 2010-05-05 | 2010-05-06 | 2010-09-30 | 2010-08-10 | 423396.36 | 2.430
9529 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E090871 | Resurfacing Austintown Warren Road from Burnett East Rd to the City of Warren south corp. limits in Trumbell county. | Pavement Improvement | 2010-05-10 | 2010-06-05 | 2010-07-31 | 2010-08-04 | 229888.96 | 1.170
9530 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E090872 | Roadway resurfacing and repair on Carson Salt Springs Rd from railroad to Austintown Warren Rd. Roadway resurfacing and repair on Austintown Warren Rd from Village of Lordstown to Carson Salt Springs | Pavement Improvement | 2010-04-14 | 2010-05-19 | 2010-08-31 | 2010-08-20 | 439857.56 | 2.730
9531 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090875 | This project is in Amberely Village to surface, replace damaged curb, repair pavement distressed areas, repair damaged inlets, install ADA compliant ramps where needed, upgrade existing traffic signal | Pavement Improvement | 2010-04-19 | 2010-06-21 | 2010-10-30 | 2010-11-04 | 870388.51 | 1.490
9532 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 08 | E090876 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project involves upgrading circuitry and warning devices on six (6) crossings in Montgomery and Warren | Safety/Traffic Management | 2010-02-01 | 2010-03-01 | 2010-12-31 |  | 1000000
9533 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090877 | This project will improve safety at railroad crossings and highway intersections in proximity to active rail grade crossing warning devices in the State of Ohio. This project was originally identified | Safety/Traffic Management | 2010-05-10 | 2010-08-01 | 2012-03-01 |  | 2500000
9534 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090879 | In Franklin County, resurfacing and pavement reconstruction of various roadways. Locations include Alum Creek Drive from Big Walnut Creek to Rathmell Road; Cambridge Blvd from Riverside Drive to Arli | Pavement Improvement | 2010-04-13 | 2010-04-21 | 2010-07-31 | 2010-11-15 | 1829848.59 | 11.670
9535 | Completed | C240,C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090906 | This project is for the rehabilitation of Northlawn Avenue Bridge in the City of Moraine. | Bridge Improvement | 2010-11-01 | 2010-12-15 | 2011-06-10 | 2011-06-07 | 324000
9536 | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | VAN WERT |  | 05 | E090911 | This project proposes to install lights and gates at 5 railroad crossings in Delphos. These crossings are: S. Pierce St., AAR DOT # 532743U; S. Franklin St., AAR DOT # 532744B; S. Main St., AAR DOT # | Safety/Traffic Management | 2009-09-02 | 2010-06-28 | 2011-01-08 | 2010-09-29 | 778600
9537 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PORTAGE |  | 17 | E090927 | This project replaces the Brady Lake Road bridge over the CSX Railroad and Breakneck Creek in Franklin Township, Portage County. | Bridge Replacement | 2009-09-16 | 2010-01-04 | 2009-12-31 | 2011-06-17 | 1124000 | 0.010
9538 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | LAWRENCE |  | 06 | E090992 | The project will construct access roads to allow for better access handling between Ohio River barges, rail and highway freight and spur the development of the South Point Inter-modal Transfer Facilit | Other | 2010-05-26 | 2010-05-26 | 2010-11-30 |  | 2388971.38
9539 | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | FAYETTE |  | 07 | E091007 | In Fayette County, pavement repairs and resurfacing of SR 734 beginning at Greene county line and ending at SR 38. Included in this distance is State Street (also known as SR 41 & SR 734) through the | Pavement Improvement | 2010-02-11 | 2010-07-19 | 2010-09-30 | 2010-09-30 | 980126.7 | 13.590
9540 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E091023 | This project will resurface County Route 66 from 12th Street to 50th Street. | Pavement Improvement | 2010-05-10 | 2010-05-17 | 2010-06-30 | 2011-01-26 | 102345.5 | 3.440
9541 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E091027 | This project involves construction of inter-modal facility and new railroad tracks at Brier Hill Industrial Park. | Other | 2011-07-15 | 2011-08-17 | 2012-06-30 |  | 16535100.68
9542 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | LORAIN | CLEVELAND, OH | 13 | E091030 | To fund a transportation brokerage in Lorain County to receive and redirect requests for work trips to eligible transportation providers | Other | 2010-01-04 | 2010-01-04 | 2012-01-04 |  | 140000
9543 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 13 | E091052 | This project is in Summit county South Main St. Intersection, Widen North and South approaches. Convert Southbound right turn lane into a through/right lane. Upgrade of signal control. | Other | 2010-06-09 | 2009-10-26 | 2011-09-30 |  | 200000 | 0.020
9544 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E091103 | This project takes place at Vine Street from Mitchell Avenue to Elmwood Place South Corp Line. It consists of resurfacing with asphaltic concrete and restriping. | Pavement Improvement | 2010-04-16 | 2010-04-16 | 2010-10-01 | 2010-10-29 | 739162.34 | 2.110
9545 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E091106 | From the southern terminus of Hempstead Station Drive, north along Hempstead Station Drive to Stroop Road then east along Stroop to the southwest corner of the Stroop/Wilmington Pike intersection-Cons | Transportation Enhancements | 2009-11-23 | 2009-11-09 | 2009-09-30 | 2010-04-12 | 179792
9546 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 13 | E091125 | In the city of Green, widen and resuface of Arlington road. Also adding turn lanes, signal coordinate and drainage improvments. This project also includes the realignment of Jarvis Road | Safety/Traffic Management | 2010-03-08 | 2010-04-05 | 2011-09-01 |  | 2000000 | 1.380
9547 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E091126 | This project is a bridge replacement taking place over Penn Central Rail Road. | Bridge Replacement | 2010-06-02 | 2010-06-14 | 2010-08-31 | 2011-06-16 | 350000 | 0.000
9548 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E091159 | This project is In the Port of Toledo from Sinclair Ave to John Carey Dr. It is for the reconstruction of a portion of St. Lawrence Drive, and the realignment of a portion of St. Lawrence Drive which | New Construction | 2010-03-29 | 2010-04-13 | 2010-11-26 | 2011-07-07 | 1985975.58
9549 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E091161 | The project involves the Toledo shipyard. It is to extend an existing Rail Road spur into the shipyard allowing steel and other material supporting shipyard operations to be shipped and delivered via | Other | 2010-04-14 | 2010-04-20 | 2011-12-31 | 2010-07-19 | 131730
9550 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E091162 | This project involves the port of Toledo, General Cargo Facility # 1. It is to repair, maintain and enhance the on dock rail capability at the Port's general cargo facility # 1 and to perform necessa | Other | 2010-07-20 | 2010-08-03 | 2011-12-31 | 2011-08-10 | 4385421
9551 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 16 | E091189 | This project will replace the bridge over CSXs railroad tracks at Mud Lake Rd. in Creston, in Medina County. This project is a part of CSX's National Gateway project to allow for double stack clearan | Pavement Improvement | 2010-12-13 | 2011-04-06 | 2012-03-01 |  | 1642355.49
9552 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E091190 | The bridge over CSX's railroad tracks at Park Street in Akron, in Summit County, will be removed for this project. This project is a part of CSX's National Gateway project to allow for double stack c | Other | 2010-08-13 | 2010-09-24 | 2012-03-01 |  | 492623
9553 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | PORTAGE |  | 17 | E091192 | This project will replace the bridge over CSX's railroad tracks at Rock Spring Road in Newton Falls, located in Portage County. This project is a part of CSX's National Gateway project to allow for d | Bridge Replacement | 2010-08-22 | 2010-09-24 | 2012-03-01 |  | 5027898 | 0.000
9554 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL |  | 14 | E091193 | The 5th Street bridge in Niles, over CSX's railroad tracks through Trumbull County, will be replaced for this project. This project is a part of CSX's National Gateway project to allow for double sta | Other | 2010-12-16 | 2011-03-01 | 2012-03-01 |  | 2255300
9555 | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E091204 | National Road in Vandalia from I-75 to just east of Brown School Road-Remove and replace trees, add decorative tree grates, decorative lights, replace sidewalk, pavers, drive aprons an upgrade bus sto | Transportation Enhancements | 2010-05-20 | 2010-05-25 | 2010-10-29 | 2010-11-19 | 921971.14 | 0.330
9556 | Underway | C220 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 11 | E091217 | This project is in Cleveland from Prospect Avenue to Euclic Avenue. It involves East 14th Street Streetscape: Sidewalks, paving, trees, plants and benches. | Transportation Enhancements | 2010-06-11 | 2010-04-20 | 2010-10-30 |  | 1923151.12 | 0.280
9557 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E091251 | In Montgomery county, widen Byers Road from 2 to 5 lanes and Relocate To The West To Form A Four-Leg Intersection With The Northern Most Section of Wood Rd. | Pavement Widening | 2010-06-16 | 2010-05-26 | 2011-06-30 | 2011-12-28 | 4000000 | 2.000
9558 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E091267 | The project consists of reconstructing approximately 2.44 miles of Bainbridge Road within the City of Solon. The work includes a new flexible pavement, integral bike lanes, and a new curb. | Pavement Improvement | 2010-01-21 | 2010-04-05 | 2011-09-30 |  | 12606660.97 | 2.460
9559 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E091291 | This project will resurface and rehab Girard-I80/SR11 to Girard south corp. limit. It will include planing the entire roadway, repairing and widening sub-standard lane widths, pavement marking applic | Pavement Improvement | 2010-01-14 | 2010-03-30 | 2010-12-31 | 2010-11-10 | 800000 | 1.320
9560 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E091335 | This project is to resurface Mahoning Ave from SR45 east to Lipkey Road. | Pavement Improvement | 2010-06-08 | 2010-05-10 | 2010-09-30 | 2010-08-02 | 519835.53 | 1.770
9561 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E091336 | This project is to resurface Tibbets Wick from US422 east to SR 11. | Pavement Improvement | 2010-06-11 | 2010-06-26 | 2010-09-30 | 2010-08-10 | 299892.19 | 1.350
9562 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E100023 | This project is to resurface Glenwood Avenue from Falls Avenue to Mahoning Avenue . | Pavement Improvement | 2010-10-22 | 2010-09-16 | 2010-11-15 | 2010-10-15 | 332500 | 0.740
9563 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | DELAWARE |  | 12 | E100027 | This project is the construction of a grade separation with the CSX Railroad. | New Construction | 2010-05-03 | 2010-05-03 | 2011-09-30 |  | 7677529.5 | 0.340
9564 | Completed | C240,C950 | Highway Infrastructure Investment Grant | OHIO | OTTAWA |  | 05 | E100048 | This project is a Ferry Boat Stimulus (ARRA) funded project to repair deteriorating commercial dock and to replace passenger and freight terminal building. | Other | 2010-08-19 | 2010-08-23 | 2010-10-31 | 2011-08-29 | 870000
9565 | Completed | C220,C200 | Highway Infrastructure Investment Grant | OHIO | CLARK |  | 07 | E100102 | This project includes streetscape and resurfacing Fountain Street from the bridge over Buck Creek to McCreight Ave. | Transportation Enhancements | 2010-05-25 | 2010-05-17 | 2010-09-11 | 2010-11-29 | 847106 | 0.620
9566 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | PORTAGE |  | 13 | E100106 | This project will involve railroad improvements and rehabilitation at milepost 120 and 103.95 on National Gateway in Kent Ohio. | Other | 2010-07-30 | 2011-04-04 | 2011-06-30 |  | 8790235
9567 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | FULTON |  | 09 | E100110 | This project is a Tier 1 Railroad Grade Separation project for Hallett Ave/Norfolk Southern in the Village of Swanton with offset alignment. | Safety/Traffic Management | 2010-05-18 | 2010-08-23 | 2011-11-01 |  | 7900000 | 0.000
9568 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | SENECA |  | 05 | E100111 | This project is a Tier 1 Railroad Grade Separation and the construction of Jones Rd / CSX RR in the city of Fostoria. | Other | 2010-05-05 | 2010-06-23 | 2011-11-30 | 2011-11-15 | 1084158.99 | 0.050
9569 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HAMILTON |  | 02 | E100123 | This project is Phase 2 of the Hamilton Interstate 75 corridor improvement project. The scope of this project includes replacing the Monmouth Street overpass, and converting the roadway to a through s | Bridge Replacement | 2010-02-25 | 2010-03-11 | 2011-10-18 | 2011-09-30 | 7192394.16 | 0.000
9570 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E100141 | This project is to construction a 6 leg roundabout including sight distance to the Northeast Avenue approach in Tallmage. This is the intersection of Howe Road/Northeast Avenue/Munroe Road | Pavement Improvement | 2010-03-16 | 2010-04-12 | 2010-05-03 | 2011-03-02 | 268800 | 0.100
9571 | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | UNION |  | 07 | E100220 | The project will replace the 1913 bridge with a modern covered bridge bringing tourism to the country which will be highlighted at the County?s Annual Covered Bridge Festival. | Bridge Replacement | 2010-04-08 | 2010-04-17 | 2010-12-31 | 2010-11-15 | 377000 | 0.010
9572 | Underway | C220,C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 11 | E100247 | The Cleveland Innerbelt Modernization Plan is focused on improving safety, reducing congestion and traffic delays, and modernizing interstate travel along I-71, I-77 and I-90 through Downtown Clevelan | Bridge Replacement | 2010-09-17 | 2011-02-01 | 2014-06-30 |  | 79542011.32 | 2.000
9573 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E100295 | This project is intended to preserve roadway in the City of Kettering. It will include replacing pavement and installation of tree lawns with trees and new sidewalks. It will also include updating | Pavement Improvement | 2010-04-13 | 2010-05-03 | 2010-11-30 |  | 1345519.34 | 0.100
9574 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WOOD | TOLEDO (MI) | 05 | E100300 | This is a TMACOG ARRA stimulus funded project to resurface East Poe Rd, in the City of Bowling Green, from Tarragon Dr to Dunbridge Rd, a distance of about 1.12 mile; perform full depth repairs where | Pavement Improvement | 2011-04-11 | 2011-05-17 | 2011-07-22 | 2011-07-22 | 750198.52 | 1.530
9575 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E100306 | This is Project 1 of Alum Creek/Groveport Rd upgrade to widen Alum Creek from N of Rathmel Rd to I-270. | Pavement Improvement | 2010-09-23 | 2010-08-30 | 2010-11-30 |  | 1207809 | 0.490
9576 | Completed | C220,C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E100356 | This project is for Streetscape including trees, shrubs, and breakaway poles for flags. | Transportation Enhancements | 2010-09-13 | 2010-10-08 | 2010-12-31 | 2011-11-09 | 282044 | 0.330
9577 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E100403 | This project is to resurface Sharon Road in Warren County From SR7 to Yankee Run Road (1.88 miles). | Pavement Improvement | 2010-10-12 | 2010-10-14 | 2010-11-15 | 2010-11-03 | 441662.14 | 1.560
9578 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E100432 | This project is to conduct environmental analysis for proposed widening of SR 4 bypass from two lanes to 4 lanes , with turn lanes as required, and proposed Bobmeyer Road extension from Airport to SR | Pavement Widening | 2010-07-07 | 2010-07-14 | 2011-09-30 | 2011-10-21 | 1702293 | 0.860
9579 | Obligated and Not Awarded | C490 | OJT/SS | OHIO | STATEWIDE |  |  | E100459 | This project is for the OJT/SS Program through FY 2010 and will be used to provide construction career/job fairs, tools, work boots, clothing, medical examinations/drug testing and seminars/training t | Other |  |  |  |  | 318416
9580 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E100467 | This project is the Summit County Hilbish Avenue Bridge replacement over Springfield Lake outlet. | Bridge Replacement | 2010-12-15 | 2011-06-15 | 2011-07-15 | 2011-08-26 | 132166.31 | 0.010
9581 | Underway | C220 | Highway Infrastructure Investment Grant | OHIO | AUGLAIZE |  | 08 | E100538 | This project is for resurfacing the intersection of SR66 and SR119 in Auglaize County. | Transportation Enhancements | 2011-05-12 | 2011-04-18 | 2012-09-30 |  | 1200000 | 0.070
9582 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E100539 | This project is to upgrade sign reflectivity through the replacement of overhead-mounted lane-control and street name signs in the City of Toledo. | Other | 2011-02-17 | 2011-05-12 | 2011-10-01 | 2011-07-05 | 186551 | 0.010
9583 | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | DEFIANCE |  | 05 | E100605 | This project includes decorative lighting, streetscape furniture, replacing trees in Treelawn, and replacing deteriorated bricks and sidewalks. | Transportation Enhancements | 2010-11-19 | 2010-11-29 | 2011-05-01 | 2011-07-29 | 986964
9584 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E100657 | This project is for resurfacing on Washington Avenue in Miami County. | Pavement Improvement | 2010-10-05 | 2010-10-08 | 2010-11-30 | 2010-12-13 | 194045.41 | 1.140
9585 | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E100796 | This is a streetscape project that will include gateway signage, medians being constructed, and landscaping. | Transportation Enhancements | 2011-05-05 | 2011-06-14 | 2011-10-14 | 2011-10-14 | 464818.22
9586 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E100809 | Analyzing existing bridge structures to determine their current load carrying capacity and entering the results of this load rating analysis into the statewide bridge inventory database. | Other | 2011-03-23 | 2011-03-23 | 2013-03-23 |  | 100000
9587 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E100810 | Analyzing existing bridge structures to determine their current load carrying capacity and entering the results of this load rating analysis into the statewide bridge inventory database. | Other | 2011-03-23 | 2011-03-23 | 2013-03-23 |  | 123746.8
9588 | Underway | C240,C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E101007 | This project is to replace the superstructure and widen as necessary. | Bridge Improvement | 2010-12-10 | 2010-12-15 | 2012-07-31 |  | 6407444.02
9589 | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E101027 | This project is for the reconstruction of the existing road including adding 2 to 3 lanes, street lighting, and a sidewalk. | Pavement Widening | 2011-02-28 | 2011-03-28 | 2012-09-30 |  | 1269286.33
9590 | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E101110 | This project is to replace the pavement on Interstate Route 90 in Ashtabula County. It also includes bridge work. | Pavement Improvement | 2011-01-31 | 2011-03-25 | 2013-08-29 |  | 28760000
9591 | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM001 | Resurface 6.50 miles of concrete pavement on east and westbound I-40 from MP 281.67 to MP 288.22 and replace the east and westbound Dirty Creek bridges. | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2011-01-21 |  | 27178471 | 6.550
9592 | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LE FLORE |  | 02 | STIM008 | Roadway construction of the remaining 2 lanes of a 4 lane facility from SH-9A extending east to SH-112 to add capacity for an existing two lane facility and replace structurally obsolete and/or defien | Bridge Replacement | 2009-09-14 | 2009-12-01 | 2010-09-13 |  | 5968238 | 1.800
9593 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ATOKA |  | 02 | STIM009 | Roadway and Bridge construction of a new 2 lane facility offset to an existing 2 lane facility from 0.33 miles West of the Atoka and Pushmataha County Line extending East into Atoka County 1.82 miles. | Pavement Widening | 2009-04-27 | 2009-04-27 | 2009-11-22 | 2010-08-13 | 3818000 | 1.820
9594 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | GARVIN |  | 04 | STIM010 | This project will extend the life of the pavement and significantly improves ride quality on 6.57 miles of I-35 by stabalizing the existing pavement. Project begins at SH-29 and extends to SH-19. | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2010-11-27 | 2010-09-30 | 24530000 | 6.570
9595 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | SEMINOLE |  | 05 | STIM011 | Full depth concrete pavement reconstruction for 2.47 miles on I-40 in Seminole County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-13 | 2009-07-07 | 2010-01-28 | 2010-01-27 | 3030000 | 2.470
9596 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCLAIN |  | 04 | STIM013 | Asphalt pavement resurfacing and bridge repair on I-44 in McClain County. This project was resurfaced within existing right of ways and no lanes were added. | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-09-23 | 2009-07-10 | 6760000 | 7.500
9597 | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM015 | "This project overlays the existing concrete pavement with a concrete overlay. Also, 2 additional lanes are being added injunction with reconstructing the existing bridges The project starts at Mile M | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2011-08-09 |  | 30000000 | 4.000
9598 | Underway | C200,C240 | Highway Infrastructure Investment Grant | OKLAHOMA | KAY |  | 03 | STIM019 | This project reconstructs the pavement surfacing upgrades the bridges and installs cable barrier in the median. The project starts at Mile Marker 224.4 and extends to Mile Marker 229.3 on I-35. | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2011-03-02 |  | 21586000 | 4.900
9599 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | BECKHAM |  | 03 | STIM024 | "This project replaces deteriorated bridge decks and improves deteriorated pavement for eight miles of I-40 near Sayre, OK. " | Pavement Improvement | 2009-04-27 | 2009-05-01 | 2010-01-21 | 2009-11-11 | 13379000 | 8.000
9600 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM028 | This project seals cracks and overlays the existing asphalt pavement. The project starts at Guymon and extends east 7.0 miles on US- 412 | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-09-23 | 2010-05-11 | 6249000 | 7.300
9601 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CIMARRON |  | 03 | STIM031 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at 7.5 miles east of Jct. with US-287 on US-64 and extends 14.5 miles east. | Pavement Improvement | 2009-06-09 | 2009-07-28 |  | 2009-11-13 | 6539700 | 8.000
9602 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM033 | This project crack seals and overlays the existing asphalt pavement. The project starts at the Texas/Cimarron County Line and extends east 4.5 miles on US-64 north of Guymon. | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-09-03 | 2009-09-16 | 3567000 | 4.500
9603 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ELLIS |  | 03 | STIM034 | This project installs a new bridge on US -283 over 25 mile creek 0.5 miles north of the Jct with State Highway 15 | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-11-22 | 2009-12-01 | 3464300 | 0.750
9604 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | COMANCHE |  | 04 | STIM037 | "This project replaces the deficient bridge over Beaver Creek for the west bound lanes of State Highway 7 west of Lawton, OK. " | Bridge Replacement | 2009-04-27 | 2009-05-06 | 2009-12-02 | 2009-10-02 | 2241000 | 0.381
9605 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CARTER |  | 04 | STIM038 | "This project replaces a deficient bridge over Red Oak Creek on US 70 west of Ardmore, OK. " | Bridge Replacement | 2009-04-27 | 2009-04-27 | 2009-12-22 | 2010-05-22 | 1272000 | 0.250
9606 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | STEPHENS |  | 04 | STIM039 | "This project constructs a new interchange at US 81 and Bois D'Arc Avenue in Duncan, OK to provide four lanes of Bois D'Arc Avenue at this location. " | Pavement Widening | 2009-06-01 | 2009-06-01 | 2010-02-25 | 2010-04-06 | 4954000 | 0.440
9607 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CARTER |  | 04 | STIM040 | "This project widens about 3 miles of US 70 from two lanes to four lanes east of the Jefferson County line west of Ardmore, OK. " | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-12-22 | 2010-05-22 | 5344000 | 3.080
9608 | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM047 | "This project is located on the north bound lanes of Interstate 244 beginning at the U.S. Highway 75 interchange extending north to the U.S. Highway 64 interchange (also referred to as the west leg of | Bridge Improvement | 2009-06-08 | 2009-06-08 | 2011-01-08 |  | 10750000 | 1.176
9609 | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM048 | "This project is located on the south bound lanes of Interstate 244 beginning at the U.S. Highway 75 interchange extending north to the U.S. Highway 64 interchange (also referred to as the west leg of | Bridge Improvement | 2009-06-08 | 2009-06-08 | 2011-01-08 |  | 20616000 | 1.124
9610 | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM049 | "This project is located on the east bound lanes of Interstate 244 beginning at the U.S. Highway 64 interchange extending east to the U.S. Highway 75 interchange (also referred to as the north leg of | Bridge Improvement | 2009-06-08 | 2009-06-08 | 2011-01-08 |  | 14900000 | 1.754
9611 | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM050 | "This project is located on the west bound lanes of Interstate 244 beginning at the U.S. Highway 64 interchange extending east to the U.S. Highway 75 interchange (also referred to as the north leg of | Bridge Improvement | 2009-06-08 | 2009-06-08 | 2011-01-08 |  | 17200000 | 1.751
9612 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA |  | 01 | STIM061 | "This project will replace the pavement approaching the State Highway 151 bridges over State Highway 51 and SL/SF railroad, replace the both deteriorated bridges and install new safety barriers. The | Bridge Replacement | 2009-06-01 | 2009-05-27 | 2010-03-27 | 2009-11-22 | 6059000 | 0.250
9613 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | NOWATA |  | 02 | STIM062 | "This project will resurface 6.0 mile of U.S. Highway 169 beginning at the Kansas State Line by replacing 2 to 4 inches of existing asphalt with 4 inches of new asphalt which results in a smoother rid | Pavement Widening | 2009-07-06 | 2009-07-23 | 2009-09-03 | 2009-09-17 | 3535000 | 6.000
9614 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | WOODS |  | 03 | STIM063 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 4.5 miles north of the Woods/Major County Line on US-281 and entends south 3.7 miles | Pavement Improvement | 2009-07-06 | 2009-04-29 | 2009-08-24 | 2009-05-18 | 706900 | 3.700
9615 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM064 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 5.3 miles southwest of the Junction with State Highway 94 on State Highway 54 and entends northeast 5. | Pavement Improvement | 2009-07-22 | 2009-10-01 |  | 2009-10-28 | 1090729 | 5.000
9616 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM065 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 9.8 miles northeast of the Texas State line on US 54 miles entends 1.6 miles to the Goodwell City limi | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-03 | 2009-10-29 | 792900 | 1.600
9617 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM066 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 11.4 miles northeast of the Texas State line on US 54 miles entends 7.0 miles. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-03 | 2009-10-29 | 1409500 | 7.000
9618 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | WOODS |  | 03 | STIM067 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 4.6 miles east of the Jct US-281 on State Highway 45 and entends east 3.5 miles. | Pavement Improvement | 2009-07-06 | 2009-04-29 | 2009-08-24 | 2009-05-18 | 598700 | 3.500
9619 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CUSTER |  | 03 | STIM069 | "This project resurfaces about 6 miles of US 183 north of Clinton, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-24 | 2009-08-28 |  | 2009-09-30 | 1197383 | 5.960
9620 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CUSTER |  | 03 | STIM070 | "This project resurfaces about 5 miles of US 183 north of Clinton, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-24 | 2009-08-28 |  | 2009-09-30 | 938475 | 4.660
9621 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | JACKSON |  | 04 | STIM071 | "This project resurfaces about 8 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2009-09-08 | 2009-08-19 | 997900 | 7.700
9622 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TILLMAN |  | 03 | STIM086 | "This project resurfaces about 4 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2009-09-08 | 2009-08-19 | 795600 | 3.920
9623 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TILLMAN |  | 03 | STIM087 | "This project resurfaces about 7 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2009-09-08 | 2009-08-19 | 1463000 | 7.130
9624 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ROGERS |  | 02 | STIM088 | This project extends the service life of the pavement by removing 2 inches of asphalt and placing 2 inches of new asphalt on U.S. Highway 412 beginning at the McClelan Kerr Navigation Channel extendin | Pavement Improvement | 2009-07-06 | 2009-07-30 | 2009-10-03 | 2009-09-29 | 1452092.1 | 5.020
9625 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OKFUSKEE |  | 02 | STIM093 | This project resurfaces about 8 miles of I-40 east of the Seminole County line to improve the smoothness of the road and to extend it's life. This project was reconstructed within existing right of wa | Pavement Improvement | 2009-06-09 | 2009-08-31 |  | 2009-12-04 | 3380000 | 8.000
9626 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | POTTAWATOMIE |  | 05 | STIM095 | Asphalt pavement resurfacing for 7.72 miles on I-40 in Seminole County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-06 | 2009-05-18 | 2009-08-19 | 2009-08-06 | 1296700 | 7.720
9627 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | SEMINOLE |  | 05 | STIM096 | Resurface I-40 from the Pottawatomie county line going east about 6.5 miles. | Pavement Improvement | 2009-07-06 | 2009-05-18 | 2009-08-19 | 2009-08-06 | 1086200 | 6.460
9628 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MURRAY |  | 04 | STIM120 | This project resurfaces about 7 miles of I-35 north of the Carter County line to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 2009-04-27 | 2009-05-26 | 2009-07-20 | 2009-10-01 | 4927000 | 6.560
9629 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CARTER |  | 04 | STIM121 | "This project resurfaces about 8 miles of US 70 east of Ardmore, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-09 | 2009-11-09 |  | 2010-06-17 | 2915633 | 8.000
9630 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ATOKA |  | 02 | STIM150 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 1.44 miles to 3.80 miles North of State Highway to repair deteriorating pavement section. | Pavement Improvement | 2009-04-20 | 2009-04-21 | 2009-10-16 | 2009-08-27 | 696712.16 | 3.800
9631 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | BRYAN |  | 02 | STIM152 | Asphalt pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.21 miles to 5.26 miles North of Oklahoma-Texas State Line for Southbound and Northbound Lanes to repair det | Pavement Improvement | 2009-07-06 | 2009-07-22 | 2009-09-18 | 2010-05-26 | 3935957.84 | 5.260
9632 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM153 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at Mile Marker 108 and entends to Mile Marker 115 on I-40 west of Oklahoma city | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-18 | 2009-09-24 | 1716300 | 7.000
9633 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM154 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at Mile Marker 115 and entends to Mile Marker 118 on I-40 west of Oklahoma city | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-18 | 2009-09-24 | 922650 | 4.200
9634 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | GARVIN |  | 04 | STIM156 | Asphalt pavement resurfacing for 8.01 miles on State Highway 76 in Garvin County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-06 | 2009-05-29 | 2009-08-09 | 2009-07-08 | 1128800 | 8.010
9635 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | HASKELL |  | 02 | STIM157 | "13.85 miles of 9.5"" thick of concrete patching and concrete surface smoothing at varies locations in Haskell county. These project were reconstructed within existing right of ways and no lanes were | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 201830.67 | 1.070
9636 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM158 | Concrete pavement reconstrcution of the driving lanes and shoulder along SH-2 beginning 14 miles north of Haskell County line and going north approximately 2 miles. | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 460649.1 | 1.750
9637 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OKMULGEE |  | 02 | STIM159 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-75 beginning at I-40 and going north approximately 2.5 miles. | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 857500 | 2.440
9638 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER |  | 01 | STIM163 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-69 beginning 0.5 miles north of SH-51 and going north approximately 8 miles. | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 1770370.23 | 7.840
9639 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER |  | 01 | STIM164 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-69 beginning 1/4 miles south of SH-51 and going north approximately 1 mile. | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 393800 | 0.750
9640 | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LE FLORE |  | 02 | STIM169 | "Roadway and Bridge Construction of driving lanes and shoulder on an offset alignment of along US Highway 59 from State Highway West to 5.26 miles North of Junction to increase the capacity and update | Pavement Widening | 2009-09-08 | 2009-07-06 | 2010-11-01 |  | 12000000 | 5.000
9641 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | HUGHES |  | 02 | STIM172 | Asphalt pavement resurfacing for 1.96 miles on U.S. Highway 270B in Hughes County. Part of this project include full depth concrete patching. This project was reconstructed within existing right of wa | Pavement Improvement | 2009-07-06 | 2009-06-16 | 2009-08-04 | 2009-09-02 | 387000 | 1.960
9642 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM173 | "This project resurfaces about 8 miles of SH-105 in Lincoln County, OK between US-177 and SH-18 to improve the smoothness of the road and to extend it's life. This project was reconstructed within ex | Pavement Improvement | 2009-07-06 | 2009-07-02 | 2009-08-04 | 2009-09-22 | 985000 | 7.970
9643 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM174 | Asphalt pavement resurfacing for 5.05 miles on State. Highway 18 in Lincoln County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-06 | 2009-07-13 | 2009-08-04 | 2009-09-04 | 487000 | 5.050
9644 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MAYES |  | 02 | STIM175 | "This project will provide a smother ride and extend the service life of the pavement by rehabilitating the existing concrete pavement. Improvements include patching deteriorated sections, adding sup | Pavement Improvement | 2009-06-01 | 2009-07-28 | 2009-09-28 | 2009-09-30 | 1871300 | 4.500
9645 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | NOBLE |  | 03 | STIM176 | Resurface both directions of I-35 starting about 1 mile north of the Payne county line and going north 6 miles. | Pavement Improvement | 2009-07-06 | 2009-07-17 | 2009-08-19 | 2009-09-03 | 1255000 | 6.000
9646 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM177 | This project will extend the life of the pavement and significantly improves ride quality on 3.5 miles of I-235 in Oklahoma City by stabalizing the existing pavement. | Pavement Improvement | 2009-04-27 | 2009-05-18 | 2009-07-25 | 2009-08-17 | 2538647.59 | 3.470
9647 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | PITTSBURG |  | 02 | STIM178 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.00 miles to 3.0 miles North of County Line for Southbound and Northbound Lanes to repair deteriorating pav | Pavement Improvement | 2009-04-20 | 2009-04-21 | 2009-10-16 | 2009-08-27 | 1571640 | 3.000
9648 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | PITTSBURG |  | 02 | STIM179 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.30 miles to 4.65 miles North of Atoka County Line for Southbound Lanes and from 3.08 miles to 6.0 miles No | Pavement Improvement | 2009-04-20 | 2009-04-21 | 2009-10-16 | 2009-08-27 | 2121700 | 4.650
9649 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ROGERS |  | 02 | STIM180 | This project extends the service life of the pavement by removing 2 inches of asphalt and placing 3 inches of new asphalt on State Highway 266 beginning at State Highway 167 extending east approximate | Pavement Improvement | 2009-07-06 | 2009-07-30 | 2009-10-03 | 2009-09-29 | 934507.9 | 6.000
9650 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | SEMINOLE |  | 05 | STIM181 | Asphalt pavement resurfacing for 4.76 miles on State Highway 56 in Seminole County. Part of this project include full depth concrete patching. This project was reconstructed within existing right of w | Pavement Improvement | 2009-07-06 | 2009-06-30 | 2009-09-03 | 2010-02-19 | 935000 | 4.760
9651 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TILLMAN |  | 04 | STIM182 | "This project resurfaces about 4 miles of US 183 south of Frederick, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-07-06 | 2009-07-09 | 2009-08-04 | 2009-07-28 | 713900 | 4.050
9652 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | MAYES |  | 02 | STIM183 | This project will replace a deteriorated county bridge on EW-58 over Chouteau Creek located approximately 0.3 mile south and 2.3 miles east of Chouteau. | Bridge Replacement | 2009-09-08 | 2009-09-29 | 2010-03-06 | 2010-04-16 | 968697 | 0.060
9653 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | MAYES |  | 02 | STIM184 | This project replaces a deteriorated bridge over Brushy Creek located approximately 2.2 miles south and 2.5 miles west of the U.S. Highway 412/69 junction. | Bridge Replacement | 2009-09-08 | 2009-10-05 | 2010-01-05 | 2010-05-05 | 289172 | 0.020
9654 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA |  | 01 | STIM185 | This project replaces a deteriorated county bridge over Delaware Creek overflow on Cincinnati Avenue located 0.5 mile south of 86th Street North in Tulsa. | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2010-01-29 | 2010-06-23 | 940731 | 0.400
9655 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | WASHINGTON |  | 01 | STIM186 | This project will replace a low water crossing on N-401 over Unnamed Creek located 0.6 miles south and 4.2 miles east of the U.S. Highway 75/ Kansas Border junction. | Bridge Replacement | 2009-08-03 | 2009-07-24 | 2010-03-30 | 2010-11-05 | 616000 | 0.020
9656 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | WASHINGTON |  | 01 | STIM187 | This project will replace a low water crossing with a new bridge on N-400 over Brush Creek located approximately 0.8 mile south and 2.0 miles east of the U.S. Highway / State Highway 10 junction. | New Bridge Construction | 2009-08-03 | 2009-07-24 | 2010-03-30 | 2010-11-05 | 471400 | 0.200
9657 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | ADAIR |  | 02 | STIM188 | Construct a new bridge on Peavine Road about 4 miles north of junction US-59/SH-51. Additional right of way was acquired to construct this project. | New Bridge Construction | 2009-09-08 | 2009-09-08 | 2010-01-25 | 2010-04-23 | 584000 | 0.250
9658 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | CHEROKEE |  | 02 | STIM189 | Replace the bridge over the Telmay Hollow creek in Cherokee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-08-03 | 2009-07-27 | 2009-10-31 | 2009-12-21 | 288000 | 0.230
9659 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | MCINTOSH |  | 02 | STIM190 | Replace the bridge over the Flat Rock creek creek in McIntosh county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-09-08 | 2009-08-10 | 2009-12-06 | 2009-12-16 | 335000 | 0.250
9660 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM191 | Replace the bridge over Cloud creek north and east of Boyton in Muskogee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-11-30 | 2009-11-30 | 2010-04-28 | 2010-08-21 | 418449 | 0.365
9661 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | OKMULGEE |  | 02 | STIM192 | Replace the bridge over the unnamed creek creek that is about 4 miles east and 2 miles north of US-75 in Okmulgee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-09-08 | 2009-07-13 | 2010-01-05 | 2009-12-18 | 320000 | 0.200
9662 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | SEQUOYAH |  | 02 | STIM193 | Construct a new bridge over the Prairie Creek just south and west of Akins in Sequoyah county. Additional right of way was acquired to construct this project. | New Bridge Construction | 2009-12-07 | 2009-09-08 | 2010-04-05 | 2010-04-28 | 300000 | 0.250
9663 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER |  | 01 | STIM194 | Replace the bridge 1 mile north and 4 miles west of the junction of US-69 and SH-51 in Wagoner county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-08-03 | 2009-07-22 | 2009-10-31 | 2009-10-28 | 220000 | 0.125
9664 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | BRYAN |  | 02 | STIM195 | County Bridge Constrcution of the driving lanes and shoulders over Island Bayou and Island Bayou Tributaries located 2.60 miles North of State Highway 78 on NS 380 Section Line Road to replace a struc | Bridge Replacement | 2009-08-03 | 2009-08-17 | 2009-11-30 | 2010-05-04 | 558000 | 0.400
9665 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | BRYAN |  | 02 | STIM196 | County Bridge Constrcution of the driving lanes and shoulders over Red Ranch Creek located 1.00 miles North and 1.50 miles East of the Town of Smith-Lee to replace a strucutrally defecient or obsolete | Bridge Replacement | 2009-08-03 | 2009-08-17 | 2009-11-30 | 2010-05-04 | 381000 | 0.300
9666 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | LATIMER |  | 02 | STIM197 | County Bridge Constrcution of the driving lanes and shoulders over Peachland Creek located 0.70 miles North and 2.00 miles West of the Town of Bengal to replace a strucutrally defecient or obsolete lo | Bridge Replacement | 2009-08-03 | 2009-08-14 | 2009-11-30 | 2010-01-20 | 535000 | 0.200
9667 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | LE FLORE |  | 02 | STIM198 | County Bridge Constrcution of the driving lanes and shoulders over Fourche Maline Creek located 1.50 miles North and 2.30 miles East of the Town of LeFLore to replace a strucutrally defecient or obso | Bridge Replacement | 2009-10-05 | 2009-06-10 | 2010-03-03 | 2010-01-27 | 1000376.12 | 0.500
9668 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | PITTSBURG |  | 02 | STIM199 | County Bridge Constrcution of the driving lanes and shoulders over Unnamed Creek located 2.00 miles North and 3.70 miles West of the Town of Quinton to replace a strucutrally defecient or obsolete loc | Bridge Replacement | 2009-10-05 | 2009-06-25 | 2010-02-01 | 2010-01-19 | 329623.88 | 0.300
9669 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | COAL |  | 02 | STIM200 | Replace the bridge over Coal Creek thats about 2 miles east and 2 miles south of Lehigh | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2010-01-29 | 2010-08-06 | 295400 | 0.200
9670 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | COAL |  | 02 | STIM201 | Replace the bridge over the tributary to Keel Creek that is about 8 miles north and 7 miles east of Coalgate. | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2010-01-29 | 2010-08-06 | 162000 | 0.200
9671 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | HUGHES |  | 02 | STIM202 | Replace the bridge over the Big creek that is about 4 miles east of Allen in Hughes county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-09-08 | 2009-08-17 | 2010-01-05 | 2010-05-05 | 429292 | 0.300
9672 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM203 | Replace the bridge over the Spring creek about a mile west of US-177 junction SH-66 in Lincoln county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2009-11-30 | 2009-12-18 | 259200 | 0.300
9673 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | OKFUSKEE |  | 02 | STIM204 | Replace the bridge over the Harrican creek that is about 3 miles south of Micawber in Okfuskee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-08-03 | 2009-06-05 | 2009-11-30 | 2009-09-14 | 421400 | 0.240
9674 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | PONTOTOC |  | 04 | STIM205 | Replace the bridge over the Grayson Creek that is about 2 miles south and 7 miles east of SH-59a junction SH-3w. | Bridge Replacement | 2009-09-08 | 2009-09-01 | 2010-04-05 | 2010-05-25 | 387159 | 0.020
9675 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | PONTOTOC |  | 04 | STIM206 | Replace the bridge over the Mill creek that is about 0.5 miles north and 2 miles east of Fittstown. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-09-08 | 2009-09-01 | 2010-04-05 | 2010-05-25 | 275105 | 0.020
9676 | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | POTTAWATOMIE |  | 05 | STIM207 | "Replace the bridge over the Popshego creek that is about 3 miles east of St. Louis, Oklahoma. Additional right of way was acquired to construct this project." | Bridge Replacement | 2009-09-08 | 2009-09-09 | 2010-01-05 | 2010-04-16 | 491743 | 0.020
9677 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GARVIN |  | 04 | STIM208 | Replace the bridge over the unnamed creek that is about 3.5 miles north of SH-7. | Bridge Replacement | 2009-08-03 | 2009-07-01 | 2009-11-30 | 2009-11-12 | 544000 | 0.300
9678 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN |  | 03 | STIM209 | Replace the bridge on EW-81 over Blue Creek about 4 miles west of Meridian. | Bridge Replacement | 2009-08-03 | 2009-07-01 | 2009-11-30 | 2009-11-25 | 400000 | 0.210
9679 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | MURRAY |  | 04 | STIM210 | Replace the bridge over Guy Sandy Creek that is about 8 miles north and a mile west of Sulphur in Murray County. | Bridge Replacement | 2009-10-05 | 2009-10-05 | 2010-02-01 | 2010-04-13 | 600000 | 0.250
9680 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | PAYNE |  | 03 | STIM211 | Replace the bridge over Clear Creek that is about 2 miles east and 7 miles south of the junction of I-35 and SH-51 | Bridge Replacement | 2009-08-03 | 2009-07-21 | 2009-10-31 | 2009-11-19 | 400000 | 0.250
9681 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM212 | This project installs a new bridge and approaches on a county bridge 3.9 miles west and 1 mile south of Piedmont | Bridge Replacement | 2009-08-03 | 2009-06-12 | 2009-12-30 | 2009-12-31 | 462972 | 0.200
9682 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM213 | This project installs a new box culvert and approaches on a county road 2 miles north and 3.6 mile east of Geary | Bridge Replacement | 2009-08-03 | 2009-06-12 | 2009-12-30 | 2009-12-31 | 166877 | 0.200
9683 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | COTTON |  | 04 | STIM214 | "This project replaces the deficient county bridge over East Cache Creek near Walters, OK. " | Bridge Replacement | 2009-08-03 | 2009-07-20 | 2009-11-30 | 2009-12-21 | 239425 | 0.250
9684 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | JEFFERSON |  | 04 | STIM215 | "This project replaces the deficient county bridge over Mud Creek near Ringling, OK. " | Bridge Replacement | 2009-08-03 | 2009-05-29 | 2009-12-30 | 2009-10-23 | 477024 | 0.250
9685 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOVE |  | 02 | STIM216 | This project replaces a low water crossing with a new bridge over Simon Creek northeast of the intersection of State Highways 76 and 32. | New Bridge Construction | 2009-08-03 | 2009-08-11 | 2009-12-30 | 2010-04-16 | 519881 | 0.120
9686 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | STEPHENS |  | 04 | STIM217 | "This project replaces the deficient county bridge over Deer Creek southeast of Comanche, OK. " | Bridge Replacement | 2009-10-05 | 2009-09-08 | 2010-05-02 | 2010-05-10 | 382956 | 0.010
9687 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | STEPHENS |  | 04 | STIM218 | "This project replaces the deficient county bridge over Stage Stand Creek southwest of Duncan, OK. " | Bridge Replacement | 2009-10-05 | 2009-09-08 | 2010-05-02 | 2010-05-10 | 452164 | 0.010
9688 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BECKHAM |  | 03 | STIM219 | "This project replaces a deficient county bridge over Buffalo Creek located about 7.5 miles north of Erick, OK. " | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2009-11-30 | 2009-12-16 | 709380.4 | 0.010
9689 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CUSTER |  | 03 | STIM220 | "This project replaces the deficient county bridge over Barnitz Creek northwest of Clinton, OK. " | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2009-10-31 | 2010-01-12 | 439978.03 | 0.200
9690 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | DEWEY |  | 03 | STIM221 | "This project replaces the deficient county bridge over the South Canadian River northwest of Oakwood, OK. " | Bridge Replacement | 2009-10-05 | 2009-09-16 | 2010-04-02 | 2010-03-19 | 1726572 | 0.379
9691 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GREER |  | 03 | STIM222 | "This project replaces the deficient county bridge over Unnamed Creek southwest of Willow, OK. " | Bridge Replacement | 2009-10-05 | 2009-08-12 | 2010-01-02 | 2009-11-17 | 348518.43 | 0.010
9692 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | TILLMAN |  | 04 | STIM223 | "This project replaces the deficient county bridge over Deep Red Creek southeast of Loveland, OK. " | Bridge Replacement | 2009-08-03 | 2009-07-28 | 2009-11-30 | 2009-12-01 | 442728.6 | 0.200
9693 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | ALFALFA |  | 03 | STIM224 | This project resurfaces the existing asphalt pavement with and asphalt overlay on county road ( NS-271) 1.0 miles west Goltry and extends north 2.1 miles | Pavement Improvement | 2009-08-03 | 2009-07-06 | 2009-10-01 | 2009-09-01 | 491864 | 2.200
9694 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BEAVER |  | 03 | STIM225 | This project installs a new bridge and approaches on a county road ( NS-146) 7.0 miles east and 3.5 miles south of Elmwood | Bridge Replacement | 2009-08-03 | 2009-07-28 | 2010-03-30 | 2010-03-17 | 480040 | 0.200
9695 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CIMARRON |  | 03 | STIM226 | This project rehabitates the existing bridge over the Beaver River on a county road ( NS-13) 1.2 miles north of Felt | Bridge Improvement | 2009-08-03 | 2009-08-03 | 2009-10-31 | 2009-09-04 | 267370 | 0.010
9696 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GARFIELD |  | 03 | STIM227 | This project installs a new bridge and approaches on a county road ( NS-188) 0.6 miles north and 6.6 miles east of Waukomis | Bridge Replacement | 2009-08-03 | 2009-07-06 | 2009-12-30 | 2009-11-12 | 539870 | 0.250
9697 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GRANT |  | 03 | STIM228 | This project installs a new bridge and approaches on a county bridge over Sand Creek 1.0 miles north and 1.5 miles east of the junction with State Highway 11 and State Highway 132. | Bridge Replacement | 2009-08-03 | 2009-09-01 | 2009-12-30 | 2010-01-26 | 510378 | 0.250
9698 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GRANT |  | 03 | STIM229 | This project resurfaces the existing asphalt pavement with and asphalt overlay on a county road 5.3 miles south of Pond Creek and extends north 5.3 miles | Pavement Improvement | 2009-08-03 | 2009-08-06 | 2009-11-30 | 2009-06-08 | 514500 | 5.300
9699 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | KINGFISHER |  | 03 | STIM230 | This project installs a new bridge and reconstruct the roadway approaches on a county bridge 4.5 miles west State Highway74F in Cashion | Bridge Replacement | 2009-08-03 | 2009-09-08 | 2009-12-30 | 2010-02-19 | 564045 | 0.200
9700 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | NOBLE |  | 03 | STIM231 | This project installs a new bridge and approaches on county road over Red Rock Creek 4.5 miles west of the Junction with US 77 and State Highway 15 | Bridge Replacement | 2009-08-03 | 2009-07-09 | 2009-12-30 | 2009-11-06 | 764687 | 0.200
9701 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BEAVER |  | 03 | STIM232 | This project installs a new bridge and approaches on county road over Bull Creek 3.0 miles west and 3.4 miles north of the junction with State Highway 3 and US 83 at Byran Corner | Bridge Replacement | 2009-08-03 | 2009-07-28 | 2010-03-30 | 2010-03-17 | 439600 | 0.100
9702 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 03 | STIM235 | This project installs a new bridge and approaches on county road over a unnamed creek 15.0 miles east and 7.0 miles south of Okarche | Bridge Replacement | 2009-12-07 | 2009-11-18 | 2010-03-06 | 2010-04-02 | 241370.37 | 0.250
9703 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM236 | Installation of traffic signals and signal interconnection on 24th West Avenue beginning at State Highway 9 extending North to Tecumseh Road in Norman. | Safety/Traffic Management | 2009-08-03 | 2009-08-03 | 2009-10-01 | 2011-01-05 | 476193.85 | 0.010
9704 | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | NOBLE |  | 03 | STIM237 | This project resurfaces and widens the existing asphalt pavement with an concrete overlay The project starts at Mile Marker 198 and entends to Mile Marker 203 on I-35 north of Perry | Pavement Widening | 2009-09-08 | 2009-08-10 | 2010-12-21 |  | 8474000 | 5.000
9705 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM238 | This project resurfaces the existing asphalt pavement with a Ultrathin MicroSurfacing preventive maintenance treatment The project starts at at the Kingfisher County Line on State Highway 3 east of Ok | Pavement Improvement | 2009-06-05 | 2009-08-31 |  | 2009-11-25 | 2493352.41 | 15.540
9706 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | GARFIELD |  | 03 | STIM239 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the Major County Line on US 60 and extends east 5.0 miles toward Enid | Pavement Improvement | 2009-06-05 | 2009-08-10 |  | 2009-10-16 | 2201741 | 5.000
9707 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | WASHITA |  | 03 | STIM240 | "This project widens 2.5 miles of US 183 from two lanes to four lanes just south of Cordell, OK. " | Pavement Widening | 2009-08-03 | 2009-08-03 | 2010-01-19 | 2010-05-08 | 3781000 | 2.500
9708 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | BLAINE |  | 03 | STIM241 | "This project resurfaces about 8 miles of US 270 west of Watonga, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-05-29 | 2009-08-19 |  | 2009-09-29 | 2778000 | 7.900
9709 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM263 | Reconstruct, widen, and replace traffic signals at the intersection of E 131ST STREET & MEMORIAL | Safety/Traffic Management | 2010-08-02 | 2010-08-02 | 2011-04-28 |  | 817379.1 | 0.300
9710 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM264 | Resurface Elm Place from New Orleans St. to Florence St. | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-06-30 | 2010-08-16 | 823348.4 | 1.000
9711 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM265 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt at the intersection of Elm Place and Houston Street in Broken Arrow. The | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-06-30 | 2010-08-16 | 222405 | 0.250
9712 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM266 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Kenosha Street from Main Street to Sixth Street in Broken Arrow. This | Pavement Improvement | 2010-02-01 | 2009-11-16 | 2010-05-31 | 2010-03-31 | 236578 | 0.500
9713 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM267 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Kenosha Street from Hickory Court to Aspen Avenue in Broken Arrow. The | Pavement Improvement | 2010-02-01 | 2009-11-16 | 2010-05-31 | 2010-03-31 | 295984 | 0.500
9714 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM268 | Resurface intersection of 9th Street and Houston Street | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-06-30 | 2010-08-16 | 198538 | 0.250
9715 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM269 | Installation of traffic signals at the intersection of Albany Street and Stone Ridge Drive in Broken Arrow. | Safety/Traffic Management | 2010-01-04 | 2010-03-15 | 2010-04-03 | 2010-10-31 | 104331 | 0.125
9716 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM270 | Installation of traffic signals at the intersection of New Orleans and 9th Street in Broken Arrow. | Safety/Traffic Management | 2010-01-04 | 2010-03-15 | 2010-04-03 | 2010-10-31 | 86505 | 0.125
9717 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM271 | Installation of traffic signals at the intersection of Elm Place and Stonewood Drive in Broken Arrow. | Safety/Traffic Management | 2010-01-04 | 2010-03-15 | 2010-04-03 | 2010-10-31 | 109921 | 0.010
9718 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | ROGERS | TULSA | 01 | STIM272 | Installation of traffic signals at the intersection of Cherokee and South School Access in Catoosa. | Safety/Traffic Management | 2010-02-01 | 2010-04-21 | 2010-05-31 | 2010-08-10 | 142975 | 0.125
9719 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER | TULSA | 01 | STIM273 | Installation of traffic signals at the intesection of 141st Street and State Highway 51 in Coweta. | Safety/Traffic Management | 2010-02-01 | 2010-06-11 | 2010-05-01 | 2010-06-17 | 9653 | 0.125
9720 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER | TULSA | 01 | STIM274 | Resurface 151st St. from Division to SH-72 | Pavement Improvement | 2010-02-01 | 2010-06-11 | 2010-05-01 | 2010-06-17 | 34507 | 0.250
9721 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CREEK | TULSA | 01 | STIM275 | "GRADE, DRAIN & SURFACE WEST 81ST STREET SOUTH FROM SH-66 WEST TO FRANKHOMA ROAD" | Pavement Widening | 2010-08-02 | 2010-09-07 | 2011-01-28 |  | 1496904.67 | 1.000
9722 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM276 | RESURFACE 5TH STREET OVERLAY | Pavement Improvement | 2010-04-19 | 2010-05-25 | 2010-06-02 |  | 115650 | 0.500
9723 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM278 | This project will resurface the pavement of Airport Access Road from Euchee Creek Boulevard to West Shellcreek Road in Sand Springs by placing 2 to 2-3/4 inches of new asphalt which results in a smoot | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-11-18 | 2010-04-20 | 472877 | 3.000
9724 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CREEK | TULSA | 03 | STIM279 | This project will remove and replace the 6 inch concrete pavement on East Line Street from Mission Street to Moccasin Place in Sapulpa. | Pavement Improvement | 2009-11-02 | 2009-11-03 | 2010-03-01 | 2010-03-12 | 450828 | 0.500
9725 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM281 | This project includes pavement and driveway repairs and will resurface the pavement to Mohawk Boulevard from Cincinnati Avenue to Hartford Avenue in Tulsa by placing 2 inches of new asphalt. The proj | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2010-02-01 | 2010-04-01 | 762026 | 0.500
9726 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM282 | Pavement reconstruction and drainage improvements on Yale Avenue from Admiral Place to Pine Street in Tulsa. | Pavement Improvement | 2010-01-04 | 2010-02-08 | 2010-08-01 |  | 1111505.31 | 1.000
9727 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM283 | "This project includes full depth concrete repairs and complete concrete pavement replacement on Southwest Boulevard from 23rd Street South to the Arkansas River Bridge in Tulsa. This project also re | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-09-25 | 2011-03-03 | 1940282 | 0.750
9728 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM284 | This project will extend the service life of the pavement by removing 2-3/4 inches of asphalt and placing 3 inches of new asphalt on Sheridan Road from 111th Street South to Admiral Boulevard in Tulsa | Pavement Improvement | 2010-01-04 | 2010-02-02 | 2011-03-29 |  | 1301812.65 | 1.000
9729 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM285 | "This project improves safety by adding paved shoulders and will extend the service life of the pavement by removing 3"" of existing asphalt and placing 3"" of new asphalt pavement. The project is lo | Pavement Improvement | 2010-03-15 | 2010-04-14 | 2010-12-24 | 2010-09-16 | 718372 | 0.350
9730 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM286 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Sheridan Road from 11th Street South to 21st Street South in Tulsa. Th | Pavement Improvement | 2010-01-04 | 2010-02-02 | 2011-03-29 |  | 1362389.45 | 1.000
9731 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM287 | This project will extend the service life of the pavement and makes driveway repairs to East 31st Street South from just west of South 132nd East Avenue to just east of South 140th East Avenue in Tuls | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2010-04-02 | 2010-06-04 | 387454 | 1.000
9732 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM288 | "This project will extend the service life of the pavement by removing 3-1/2"" of existing asphalt and placing 3"" of new asphalt pavement. The project also includes bridge deck repairs, upgrades an | Pavement Improvement | 2010-01-11 | 2010-01-11 | 2010-11-06 | 2011-01-30 | 1374172 | 1.000
9733 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM289 | "This project removes and replaces the existing pavement on East 41st Street from Interstate 44 to Sheridan Road and South Yale Avenue from 31st Street South to 36st Street South in Tulsa. The projec | Pavement Improvement | 2010-01-11 | 2010-01-11 | 2010-09-07 |  | 1841843 | 0.750
9734 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OSAGE |  | 03 | STIM290 | This project will extend the service life of the pavement by placing 3 inches of new asphalt pavement on U.S. Highway 60 beginning 0.75 mile east of the Osage/Kay County Line extending east 4.44 miles | Pavement Improvement | 2009-07-06 | 2009-07-01 | 2009-07-28 | 2009-08-06 | 1169214.61 | 4.440
9735 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OSAGE |  | 03 | STIM291 | This project will extend the service life of the pavement by removing 1 inch of asphalt pavement and placing 2 inches of new asphalt pavement on State Highway 99 beginning 0 .86 mile north of the Stat | Pavement Improvement | 2009-07-06 | 2009-06-24 | 2009-08-05 | 2009-08-25 | 616161.88 | 4.170
9736 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | PAWNEE |  | 03 | STIM293 | "This project will extend the service life of the pavement by patching the existing concrete pavement, installing supports at the joints, and grinding the surface to provide a smooth ride on U.S. High | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2009-12-14 | 2010-09-23 | 2162178.12 | 7.650
9737 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | PAWNEE |  | 03 | STIM294 | "This project will extend the service life of the pavement by patching the existing concrete pavement, installing supports at the joints, and grinding the surface to provide a smooth ride on U.S. High | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2009-12-14 | 2010-09-23 | 1212445.39 | 6.700
9738 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM295 | Asphalt pavement resurfacing for 2.77 miles on I-40 in Muskogee County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-06-05 | 2009-08-24 |  | 2009-10-09 | 2313529 | 4.390
9739 | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | COMANCHE | LAWTON | 04 | STIM296 | "This project repairs 5 bridges, reconstructs deteriorated pavement, and improves safety features for about 2.5 miles of I-44 in Lawton, OK. " | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-08-18 |  | 14217384 | 1.520
9740 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM297 | Resurface Rockwell Ave from NW 16th to NW 23rd and resurface NW 36th from Rockwell to Hammond | Pavement Improvement | 2010-02-18 | 2010-03-23 |  | 2010-06-17 | 414237 | 1.000
9741 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCLAIN | OKLAHOMA CITY | 04 | STIM298 | RESURFACE BLANCHARD ARRA: FROM SH-76 TO COUNTY LINE ROAD | Pavement Improvement | 2010-04-26 | 2010-04-27 | 2010-05-25 | 2010-05-25 | 135724.58 | 0.900
9742 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CIMARRON |  | 03 | STIM299 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the Junction with US 287 and extends east 7.5 miles on US 412 | Pavement Improvement | 2009-06-09 | 2009-07-28 |  | 2009-11-13 | 2150000 | 7.500
9743 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM300 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the on County Line road in the Cashion Area and extends from Seward Road to Forest Hill Road | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2009-12-11 | 2010-02-12 | 176426 | 1.000
9744 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM301 | RESURFACE NE 23RD FROM HENNEY RD TO CHOCTAW RD | Pavement Improvement | 2010-07-26 | 2010-07-26 | 2010-09-08 | 2010-09-30 | 323286 | 0.010
9745 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM302 | Resurface Etowah road from 108th Ave to 180th Ave SE. | Pavement Improvement | 2009-08-12 | 2009-08-31 |  | 2010-04-23 | 717297 | 6.000
9746 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 04 | STIM303 | "This project will resurface 1.75 miles of road in Del City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2010-02-01 | 2009-11-23 | 2010-03-02 | 2010-04-05 | 233637.29 | 1.750
9747 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM304 | "RESURFACE EDMOND ARRA: MULTIPLE LOCATIONS ON KELLY AVE, DANFORTH, EDMOND RD & 15TH STREET" | Pavement Improvement | 2010-05-04 | 2010-05-24 |  | 2010-10-13 | 1683176 | 4.700
9748 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM305 | This project will resurface 1 mile of road in the vicinity of Forrest Park in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 147302 | 1.000
9749 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM306 | Resurface Coltrane rodade from Seward road to Lakeshore Drive. | Pavement Improvement | 2010-04-01 | 2010-03-24 | 2010-04-30 | 2010-04-26 | 271669 | 1.500
9750 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM307 | Resurface Reno Avenue from Harrah Road to Pottawatomie Road | Pavement Improvement | 2010-04-05 | 2010-03-15 | 2010-05-19 | 2010-04-07 | 197078 | 1.500
9751 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM308 | This project will resurface 1.5 miles of Main Street in Jones to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 131157 | 1.500
9752 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM309 | Resurface Pensylvania avenue from Oklahoma Couty line north into logan county | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2009-12-11 | 2010-02-12 | 443708 | 1.700
9753 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 04 | STIM400 | Resurface multiple locations in Midwest City on SE 29th and NE 10th. | Pavement Improvement | 2010-07-12 | 2010-07-20 | 2010-11-28 |  | 239175 | 2.000
9754 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM401 | Resurface Janeway and Santa Fe from NW 12th to NW 27th | Pavement Improvement | 2009-08-12 | 2009-08-31 |  | 2010-04-23 | 600303 | 2.000
9755 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 04 | STIM403 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts is on N Sara Rd in Mustang and extends from State Highwy 152 to SW 59th Street and South Mustage Fronta | Pavement Improvement | 2009-08-19 | 2009-10-16 |  | 2009-10-30 | 279620 | 2.000
9756 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM404 | TRAFFIC SIGNALS NE 23RD AT NICHOLS (TRAFFIC SIGNALS) | Transportation Enhancements | 2010-07-26 | 2010-07-26 | 2010-08-25 | 2010-10-01 | 70367 | 0.010
9757 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM405 | This project will resurface 1 mile of road in the vicinity of Nicoma Park in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 60197 | 1.000
9758 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM406 | Resurface Etowah road from 48th Ave SE to US-77 | Pavement Improvement | 2010-04-05 | 2010-03-22 | 2010-05-04 | 2010-04-05 | 191001.74 | 2.500
9759 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM407 | "Asphalt pavement resurfacing of portions of Eufaula Street, Flood Avenue, Jenkins Avenue, Lindsey Street, Porter Avenue, and University Boulevard in Cleveland County. This project was reconstructed w | Pavement Improvement | 2009-08-12 | 2009-08-31 |  | 2010-04-23 | 1142437 | 3.740
9760 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM408 | "This project will resurface 5 miles of Memorial Road through north east Oklahoma City and Edmond to improve ride quality and extend the life of the pavement. In addition, new curb ramps will be insta | Pavement Improvement | 2009-08-13 | 2009-08-24 |  | 2009-11-16 | 1355644 | 5.000
9761 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM409 | "This project will resurface 8 miles of road in north west Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-12-18 |  | 3179188 | 8.000
9762 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM410 | "This project will resurface 1.7 miles of road in north west Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-08-19 | 2009-08-31 |  | 2010-06-09 | 652692 | 1.700
9763 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM411 | "This project will resurface 3 miles of May Avenue in south Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-08-19 | 2009-08-31 |  | 2010-06-09 | 966992 | 3.000
9764 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM412 | "This project will resurface 3.5 miles of Shields Boulevard in south Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-07-27 | 2009-07-20 | 2009-11-23 | 2010-01-13 | 1514850 | 3.500
9765 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM413 | Resurface multiple locations on Penn and May in the areas of SW 89th and SW 119th. | Pavement Improvement | 2009-07-27 | 2009-07-20 | 2009-11-23 | 2010-01-13 | 1416273 | 5.000
9766 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM414 | "This project will resurface 6 miles of road in Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-09-28 | 2009-09-15 | 2009-11-26 |  | 2202725 | 6.000
9767 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM415 | This project will resurface 6.3 miles of Midwest Boulevard in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 2274617 | 6.300
9768 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM416 | This project will resurface 3 miles of road north of Luther to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 522272 | 3.000
9769 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 03 | STIM417 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts is on Piedmont Rd in Mustang and extends from Arrowhead Road to Apache Street. | Pavement Improvement | 2009-07-27 | 2009-08-03 | 2009-08-26 | 2009-08-24 | 188523 | 1.000
9770 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 04 | STIM418 | This project will resurface 1 mile of road south of Spencer to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 117961 | 1.000
9771 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM419 | "This project will resurface 1 mile of Penn Avenue in the city of Village to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-08-19 | 2009-08-31 |  | 2010-06-09 | 278129 | 1.000
9772 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM420 | "This project will resurface 0.5 mile of road in the city of Warr Acres to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramp " | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-03-02 | 2010-04-14 | 116229.34 | 0.500
9773 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 03 | STIM421 | Resurface Cornwell from NW10th to Vandement. | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-08-30 | 2010-09-02 | 676877 | 1.000
9774 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM422 | This project will extend the service life of the pavement by removing 2 inches of asphalt and placing 2 inches of new asphalt on East 2nd Street from Main Street to Adams Street in Sand Springs. | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-11-18 | 2010-04-20 | 185046 | 0.500
9775 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCLAIN | OKLAHOMA CITY | 04 | STIM423 | Redeck and rehabilitation of US-62 bridge and approaches over H.E. Bailey Turnpike (I-44) in McClain County. This project was reconstructed within existing right of ways and no lanes were added. | Bridge Improvement | 2010-03-01 | 2010-03-01 | 2010-04-29 | 2010-09-28 | 392075.65 | 0.010
9776 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCLAIN | OKLAHOMA CITY | 04 | STIM424 | Installation of traffic signals on U.S. Highway 77 at the intesections of State Highway 74 and State Highway 39. | Safety/Traffic Management | 2010-02-08 | 2010-02-08 | 2010-05-08 | 2010-05-14 | 163803.18 | 0.010
9777 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | GRADY | OKLAHOMA CITY | 04 | STIM425 | INTERSECTION MOD. & TRAF. SIGNALS TUTTLE ARRA: INTERSECTION OF SH-37 & CIMARRON ROAD | Transportation Enhancements | 2010-05-03 | 2010-04-28 | 2010-07-16 |  | 225000 | 0.010
9778 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 04 | STIM427 | Resurface SE 15th from Douglas Blvd to Post Road. | Pavement Improvement | 2010-05-03 | 2010-05-04 | 2010-06-01 | 2010-06-08 | 351192 | 1.000
9779 | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CIMARRON |  | 03 | STIM428 | This project reconstructs the existing pavement with a new asphalt pavement. The project starts 7.0 miles south of the juncton with US 64 on US 287 and extends 0.8 miles | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2010-02-12 | 2010-04-27 | 2084606 | 0.830
9780 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN |  | 03 | STIM429 | This project installs a new bridge and approaches on a county bridge over Wof Creek 2.0 miles north and 2.2 miles east of the junction with State Highway 74 and State Highway 74C. | Bridge Replacement | 2009-10-28 | 2009-11-30 | 2010-04-03 | 2010-03-19 | 172636 | 0.250
9781 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | MURRAY |  | 04 | STIM430 | "This project replaces the deficient county bridge over Eight Mile Creek near Hennepin, OK. " | Bridge Replacement | 2009-12-07 | 2009-11-30 | 2010-04-05 | 2010-03-19 | 247000 | 0.250
9782 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | ALFALFA |  | 03 | STIM431 | This project installs a new bridge and approaches on a county bridge over West Clay Creek on county road( NS 262) 1.0 miles east and 2.7 miles north of SH-8 junction with US-64 | Bridge Replacement | 2010-01-05 | 2010-01-05 | 2010-05-04 | 2010-06-24 | 511965 | 0.200
9783 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | OSAGE |  | 03 | STIM432 | This project replaces a deteriorated bridge on EW-33 over Cander Creek located 0.2 mile south and 1.3 miles east of Wolco. | Bridge Replacement | 2010-03-22 | 2010-03-08 | 2010-10-17 | 2010-12-23 | 430812 | 0.400
9784 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LATIMER |  | 02 | STIM433 | County Bridge Constrcution of the driving lanes and shoulders over Bear Creek located 0.50 miles North and 0.50 miles East of the Town of Lodi to replace a strucutrally defecient or obsolete local gov | Bridge Replacement | 2010-04-05 | 2010-04-05 | 2010-08-02 | 2010-08-11 | 125149 | 0.500
9785 | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CHEROKEE |  | 02 | STIM434 | PEDESTRIAN IMPROVEMENTS HULBERT ARRA: SH-51 RIDER LN TO HALF BLOCK EAST OF THE POST OFFICE | Transportation Enhancements | 2010-08-02 | 2010-09-20 | 2010-10-30 |  | 366699 | 0.100
9786 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM435 | PEDESTRIAN IMPROVEMENTS COUNCIL HILL ARRA: SH-72 FROM 4TH ST TO 8TH ST (WEST SIDE ONLY) | Transportation Enhancements | 2010-04-05 | 2010-03-23 | 2010-07-02 | 2010-05-06 | 133395 | 0.100
9787 | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM436 | PEDESTRIAN IMPROVEMENTS PORUM ARRA SH-2 FROM HALF BLOCK NORTH OF OSAGE SOUTH TO CHEROKEE AVE | Transportation Enhancements | 2010-08-02 | 2010-11-05 | 2010-10-30 |  | 348474 | 0.100
9788 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | SEQUOYAH |  | 02 | STIM437 | PEDESTRIAN IMPROVEMENTS VIAN ARRA US-64 FROM BLACKSTONE TO KENNEDY; SH-82 FROM MAIN TO SEQUOYAH | Transportation Enhancements | 2010-04-05 | 2010-04-05 | 2010-06-03 | 2010-08-23 | 441911 | 0.100
9789 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM438 | PEDESTRIAN IMPROVEMENTS BOYNTON ARRA SH-72 FROM LUCILLE AVE NORTH TO NORTH OF KENEFICK AVE | Transportation Enhancements | 2010-04-05 | 2010-03-23 | 2010-07-02 | 2010-05-06 | 89298 | 0.100
9790 | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | HASKELL |  | 02 | STIM439 | PEDESTRIAN IMPROVEMENTS KINTA ARRA SH-31 FROM HOYT TO MAIN; SH-2 FROM 4TH ST TO NORTH OF 2ND ST | Transportation Enhancements | 2010-04-05 | 2010-04-05 | 2010-06-03 |  | 161325 | 0.100
9791 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | LE FLORE |  | 02 | STIM441 | PEDESTRIAN IMPROVEMENTS TALIHINA ARRA US-271 FROM 1ST ST TO DUKE ST 1/2 BLOCK NORTH ON SH-1 | Transportation Enhancements | 2010-04-05 | 2010-03-11 | 2010-06-03 | 2010-06-02 | 128467 | 0.100
9792 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCURTAIN |  | 02 | STIM442 | PEDESTRIAN IMPROVEMENTS BROKEN BOW ARRA US-70 FROM PARK DR TO CHATA RD; US-259 FROM US-70 NORTH 0.4 MI (WEST SIDE ONLY) | Transportation Enhancements | 2010-04-05 | 2010-03-25 | 2010-06-03 | 2010-07-20 | 239644 | 0.100
9793 | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MARSHALL |  | 04 | STIM445 | PEDESTRIAN IMPROVEMENTS KINGSTON ARRA US-70 FROM MAYTUBBY ST TO HANEY ST; US-70B FROM US-70 TO 1ST ST | Transportation Enhancements | 2010-04-05 | 2010-04-01 | 2010-08-02 |  | 457323 | 0.100
9794 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM446 | PEDESTRIAN IMPROVEMENTS AGRA ARRA SH-18 HAYES ST TO WASHINGTON ST | Transportation Enhancements | 2010-04-05 | 2010-04-09 | 2010-06-03 | 2010-07-12 | 144663 | 0.100
9795 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM447 | PEDESTRIAN IMPROVEMENTS TRYON ARRA SH-105 FROM OKLAHOMA ST TO 1ST ST | Transportation Enhancements | 2010-05-03 | 2010-05-11 | 2010-07-31 | 2010-10-12 | 237215 | 0.100
9796 | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | SEMINOLE |  | 05 | STIM448 | PEDESTRIAN IMPROVEMENTS SASAKWA ARRA SH-56 FROM PINE ST TO CHESTNUT ST | Transportation Enhancements | 2010-05-03 | 2010-05-05 | 2010-08-30 |  | 148764 | 0.100
9797 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | GARVIN |  | 04 | STIM449 | PEDESTRIAN IMPROVEMENTS MAYSVILLE ARRA SH-19/SH-74 EAST TO PINE ALLEY | Transportation Enhancements | 2010-07-12 | 2010-06-28 | 2010-09-10 | 2011-01-14 | 95958 | 0.100
9798 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | KAY |  | 03 | STIM452 | PEDESTRIAN IMPROVEMENTS TONKAWA ARRA US-77/US-60B FROM GRAND AVE TO PARK AVE & MAIN ST TO PUBLIC ST | Transportation Enhancements | 2010-05-03 | 2010-04-19 | 2010-07-01 | 2011-01-28 | 317386 | 0.100
9799 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | KINGFISHER |  | 03 | STIM453 | PEDESTRIAN IMPROVEMENTS OKARCHE ARRA US-81 FROM IOWA ST NORTH TO MISSOURI (EAST SIDE ONLY) & MEMORIAL (WEST SIDE) | Transportation Enhancements | 2010-04-05 | 2010-04-26 | 2010-06-03 | 2010-08-17 | 304492 | 0.100
9800 | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | KINGFISHER |  | 03 | STIM454 | PEDESTRIAN IMPROVEMENTS HENNESSEY ARRA US-81 FROM IOWA ST SOUTH TO 6TH ST | Transportation Enhancements | 2010-07-05 | 2010-08-11 | 2010-10-02 | 2011-01-08 | 778345 | 0.100
9801 | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN |  | 03 | STIM455 | PEDESTRIAN IMPROVEMENTS CRESCENT ARRA SH-74 FROM NORTH LOCUST ST SOUTH TO WEST ADAMS ST | Transportation Enhancements | 2010-07-19 | 2010-07-19 | 2010-10-16 | 2010-11-18 | 355410 | 0.100
9802 | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN |  | 03 | STIM456 | PEDESTRIAN IMPROVEMENTS LANGSTON ARRA SH-OB FROM WASHINGTON ST EAST TO MARTIN LUTHER KING ST | Transportation Enhancements | 2010-05-03 | 2010-05-03 | 2010-07-31 | 2010-11-27 | 1357120 | 0.010
9803 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | KINGFISHER |  | 03 | STIM457 | PEDESTRIAN IMPROVEMENTS KINGFISHER ARRA US-81 NORTH OF SH-33 RECONSTRUCTION OF THREE INTERSECTIONS | Transportation Enhancements | 2010-04-05 | 2010-04-13 | 2010-06-03 | 2010-10-19 | 494012 | 0.870
9804 | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | HARMON |  | 03 | STIM458 | PEDESTRIAN IMPROVEMENTS HOLLIS ARRA US-62 FROM MAIN ST EAST TO 1ST ST | Transportation Enhancements | 2010-07-19 | 2010-08-25 | 2010-10-16 |  | 452793 | 0.100
9805 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | BECKHAM |  | 03 | STIM459 | PEDESTRIAN IMPROVEMENTS SAYRE ARRA SH-152/US-283 EAST TO COURTHOUSE SQUARE; US-283 FROM MAIN ST NORTH TO US-66 | Transportation Enhancements | 2010-03-01 | 2010-04-26 | 2010-04-29 | 2010-08-10 | 441823 | 0.100
9806 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | DEWEY |  | 03 | STIM460 | PEDESTRIAN IMPROVEMENTS VICI ARRA SH-51 FROM SPECK ST EAST TO BROWN ST **CERT** | Transportation Enhancements | 2010-04-05 | 2010-03-09 | 2010-06-03 | 2010-05-10 | 299649 | 0.100
9807 | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BLAINE |  | 03 | STIM461 | PEDESTRIAN IMPROVEMENTS CANTON ARRA SH-51 FROM GRANT ST TO LINCOLN ST; SH-58 FROM MAIN ST TO PARK ST | Transportation Enhancements | 2010-07-05 | 2010-06-07 | 2010-10-02 |  | 595704 | 0.100
9808 | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | GREER |  | 03 | STIM462 | PEDESTRIAN IMPROVEMENTS MANGUM ARRA SH-34 FROM EAST JACKSON ST TO EAST SOUTH ST | Transportation Enhancements | 2010-08-02 | 2010-08-03 | 2010-10-30 |  | 478252 | 0.100
9809 | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | KIOWA |  | 03 | STIM463 | PEDESTRIAN IMPROVEMENTS HOBART ARRA US-183 | Transportation Enhancements | 2010-07-05 | 2010-07-06 | 2010-10-02 | 2010-11-02 | 491751 | 1.000
9810 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM464 | PEDESTRIAN IMPROVEMENTS HARDESTY ARRA US-412 FROM 2ND ST WEST TO 6TH ST | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-04-29 | 2010-05-18 | 197303 | 0.100
9811 | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | ELLIS |  | 03 | STIM465 | PEDESTRIAN IMPROVEMENTS SHATTUCK ARRA US-283 FROM GRAND AVE SOUTH TO 10TH ST | Transportation Enhancements | 2010-05-03 | 2010-05-03 | 2010-07-01 |  | 559449 | 0.100
9812 | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | ELLIS |  | 03 | STIM466 | PEDESTRIAN IMPROVEMENTS GAGE ARRA SH-46 FROM NORTH ST SOUTH TO SH-46/SH-15 JCT | Transportation Enhancements | 2010-07-12 | 2010-07-14 | 2010-09-10 |  | 109804 | 0.100
9813 | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | ALFALFA |  | 03 | STIM467 | PEDESTRIAN IMPROVEMENTS GOLTRY ARRA SH-45 FROM 7TH ST SOUTH TO 1/4 MI SOUTH OF MAIN ST | Transportation Enhancements | 2010-07-19 | 2010-08-16 | 2010-10-16 |  | 454528 | 0.100
9814 | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BEAVER |  | 03 | STIM468 | PEDESTRIAN IMPROVEMENTS FORGAN ARRA US-270 FROM TEXAS ST TO MISSISSIPPI AVE | Transportation Enhancements | 2010-04-19 | 2010-04-06 | 2010-06-17 | 2010-08-02 | 658984 | 0.100
9815 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | JEFFERSON |  | 04 | STIM469 | PEDESTRIAN IMPROVEMENTS WAURIKA ARRA SH-5 FROM ANDERSON AVE SOUTH TO US-70 | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-04-29 | 2010-06-10 | 236578 | 0.100
9816 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | GRADY |  | 04 | STIM470 | PEDESTRIAN IMPROVEMENTS POCASSET ARRA US-81 FROM 1ST ST SOUTH TO 5TH ST | Transportation Enhancements | 2010-04-05 | 2010-03-01 | 2010-06-03 | 2010-03-19 | 127638 | 0.100
9817 | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | COTTON |  | 04 | STIM471 | PEDESTRIAN IMPROVEMENTS TEMPLE ARRA SH-65 FROM OREGON ST SOUTH TO OKLAHOMA ST | Transportation Enhancements | 2010-07-12 | 2010-07-12 | 2010-10-09 |  | 440815 | 0.100
9818 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | GRADY |  | 04 | STIM472 | PEDESTRIAN IMPROVEMENTS RUSH SPRINGS ARRA SH-17/SH-81B JCT TO SH-81 | Transportation Enhancements | 2010-04-05 | 2010-03-01 | 2010-07-03 | 2010-05-05 | 152435 | 0.100
9819 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | JEFFERSON |  | 04 | STIM473 | PEDESTRIAN IMPROVEMENTS HASTINGS ARRA SH-5 FROM COMMERCIAL AVE TO 4TH ST | Transportation Enhancements | 2010-05-03 | 2010-05-03 | 2010-07-01 | 2010-11-09 | 163191 | 0.100
9820 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | CADDO |  | 03 | STIM474 | "PEDESTRIAN IMPROVEMENTS CEMENT ARRA US-277(SH-19) FROM ""F"" AVE WEST TO ONE BLK WEST OF MAIN ST " | Transportation Enhancements | 2010-05-03 | 2010-06-01 | 2010-07-01 | 2010-06-18 | 113608 | 0.100
9821 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | CARTER |  | 04 | STIM475 | PEDESTRIAN IMPROVEMENTS GENE AUTRY ARRA SH-53A FROM GRANT AVE TO MILL ST (WEST SIDE ONLY) | Transportation Enhancements | 2010-04-05 | 2010-03-29 |  | 2010-06-10 | 95369 | 0.100
9822 | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CREEK |  | 01 | STIM476 | PEDESTRIAN IMPROVEMENTS MOUNDS ARRA US-75A FROM 9TH ST TO 14TH ST | Transportation Enhancements | 2010-07-05 | 2010-07-05 | 2010-10-02 | 2010-12-02 | 238017 | 0.200
9823 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | NOWATA |  | 02 | STIM477 | PEDESTRIAN IMPROVEMENTS NOWATA ARRA US-60 FROM DELAWARE OAK ST | Transportation Enhancements | 2010-05-03 | 2010-04-26 | 2010-07-01 | 2010-06-21 | 189298 | 0.100
9824 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | OSAGE |  | 03 | STIM478 | PEDESTRIAN IMPROVEMENTS FAIRFAX ARRA SH-18 FROM WALNUT ST TO MULBERRY ST | Transportation Enhancements | 2010-07-05 | 2010-06-21 | 2010-09-03 | 2010-12-17 | 200199 | 0.100
9825 | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | OTTAWA |  | 02 | STIM479 | PEDESTRIAN IMPROVEMENTS QUAPAW ARRA US-69A FROM 1ST ST SOUTH TO 4TH ST | Transportation Enhancements | 2010-07-05 | 2010-07-06 | 2010-10-02 |  | 382625 | 0.100
9826 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | MAYES |  | 02 | STIM480 | PEDESTRIAN IMPROVEMENTS LOCUST GROVE ARRA US-412A FROM BROADWAY EAST TO CHEROKEE ST | Transportation Enhancements | 2010-07-05 | 2010-07-09 | 2010-10-02 | 2010-10-14 | 223695 | 0.100
9827 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | HASKELL |  | 02 | STIM481 | Replace the bridge over San Bois Creek about 1 mile south and 2 miles west of Kinta. | Bridge Replacement | 2010-03-01 | 2010-03-16 | 2010-06-28 | 2010-08-04 | 255379.54 | 0.220
9828 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM482 | Intersection modifications and installation of traffic signals at 21st Street and Sheridan Road in Tulsa. | Pavement Improvement | 2010-01-04 | 2010-02-02 | 2011-03-29 |  | 652209.95 | 0.010
9829 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM483 | RESURFACE BRYANT AVE BEG @ SH-37 & EXT NORTH TO N.E. 27TH ST & S.E. 34TH ST FR BRYANT AVE. TO SOONER RD. | Pavement Improvement | 2010-03-24 | 2010-06-23 |  |  | 851806 | 4.000
9830 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER |  | 01 | STIM484 | PEDESTRIAN IMPROVEMENTS PORTER ARRA SH-51B FROM HALE ST SOUTH 6 BLK TO BELAIRE ST | Transportation Enhancements | 2010-04-05 | 2010-03-18 | 2010-06-18 | 2010-07-08 | 377227 | 0.500
9831 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | PITTSBURG |  | 02 | STIM485 | PEDESTRIAN IMPROVEMENTS KIOWA ARRA US-69 START & END AT THE CURB & GUTTER BOTH SIDES OF ROAD 8/10 MI LONG | Transportation Enhancements | 2010-04-05 | 2010-04-13 | 2010-08-02 | 2010-08-13 | 511485 | 0.800
9832 | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | OTTAWA |  | 02 | STIM489 | PEDESTRIAN IMPROVEMENTS MIAMI ARRA US-69 FROM C ST SW TO A ST SW 4 BLK; SH-10 FROM A ST SW EAST 1.5 BLK | Transportation Enhancements | 2010-04-05 | 2010-05-05 | 2010-06-03 |  | 460384 | 0.100
9833 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM490 | RESURFACE S.E. 44TH STREET BEG @ BRYANT AVE. & EXTEND EAST TO SOONER ROAD IN DEL CITY & OKLAHOMA CITY | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-05-18 | 2010-06-25 | 600229 | 2.000
9834 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 04 | STIM491 | RESURFACE MORGAN ROAD BEG @ S.W. 89TH STREET & EXTEND NORTH TO S.W. 59TH STREET IN MUSTANG. | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2010-06-15 | 2010-06-08 | 210466 | 2.000
9835 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM492 | RESURFACE KELLY AVE BEG @ WATERLOO ROAD & EXTEND NORTH TO CO RD(EW-88) | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-05-25 | 2010-06-15 | 111305 | 1.000
9836 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM493 | RESURFACE MAIN STREET BEG @ STATE STREET & EXTEND EAST 0.5 MILE | Pavement Improvement | 2010-05-17 | 2010-05-10 | 2010-07-15 | 2010-07-21 | 87399 | 0.500
9837 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM494 | RESURFACE JONES ARRA: N.E. 36TH STREET BEG @ COLTRANE & EXT TO BARTREL RD | Pavement Improvement | 2010-05-17 | 2010-05-10 | 2010-07-15 | 2010-07-21 | 71068 | 1.000
9838 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM495 | RESURFACE LUTHER ARRA: LUTHER ROAD BEG @ EDMOND ROAD & EXT NORTH TO DANFORTH RD | Pavement Improvement | 2010-05-17 | 2010-05-10 | 2010-07-15 | 2010-07-21 | 188000 | 1.100
9839 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM497 | "RESURFACE SPENCER ARRA: SPNCR RD FR NE 36TH EXT N TO NE 50TH; SDWLKS & ADA RMPS FR NE 23RD TO NE 36TH ON SPNCR RD**CERT**(DEL FR 02-10, ADD TO 03-10;PLAN REV)" | Pavement Improvement | 2010-07-05 | 2010-07-16 | 2010-08-18 | 2010-09-16 | 89918 | 1.000
9840 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM499 | RESURFACE WARR ACRES ARRA: MACARTHUR AVE BEG @ NW 63RD ST & EXT NORTH TO N.W. EXPRESSWAY | Pavement Improvement | 2010-04-19 | 2010-05-21 | 2010-05-18 | 2010-05-27 | 217107 | 0.800
9841 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM500 | RESURFACE GUTHRIE ARRA: WALNUT AVE FROM NOBLE TO MANSUR | Pavement Improvement | 2010-08-02 | 2010-08-02 | 2010-08-22 | 2010-09-20 | 46150 | 0.200
9842 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM501 | RESURFACE OKC ARRA: ANDERSON RD BEG @ S.E. 149TH ST. & EXT NORTH TO S.E. 89TH ST. | Pavement Improvement | 2010-05-17 | 2010-08-17 | 2010-06-30 | 2010-12-16 | 1304447 | 4.000
9843 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM502 | RESURFACE OKC ARRA: MERIDIAN AVE BEG AT S.W. 54TH ST. & EXT NORTH TO S.W. 29TH ST. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2010-07-06 | 2010-07-29 | 489821 | 1.600
9844 | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GRANT |  | 03 | STIM503 | "GRADE,DRAINING,BRIDGE & SURFACE CO. BR. OVER POND CR., 3 MI. N. AND 4.9 MI. E. OF THE SH-11/SH-11A JCT (FORMERLY BRO-127D(100)CO) " | Bridge Replacement | 2010-05-03 | 2010-04-12 | 2010-08-30 | 2010-09-10 | 95480 | 0.100
9845 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM504 | "GRADE,DRAINING,BRIDGE & SURFACE ROBINSON STREET AT THE BURLINGTON NORTHERN SANTE FE RAILROAD CROSSING, IN NORMAN " | Pavement Improvement | 2010-08-02 | 2010-06-14 | 2011-11-09 |  | 1888512 | 0.200
9846 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM505 | RESURFACE BROKEN ARROW ARRA: HOUSTON ST(81ST STREET SOUTH) BEG @ ASPEN AVE(145TH E. AVE) & EXT TO ELM PLACE(161ST E. AVE) | Pavement Improvement | 2010-07-05 | 2010-07-06 | 2010-08-18 |  | 435076 | 1.000
9847 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM506 | PAVEMENT REHABILITATION JENKS ARRA: MAIN STREET - RAILROAD EAST TO 4TH STREET | Pavement Improvement | 2010-08-02 | 2010-08-02 | 2010-10-30 |  | 141815 | 0.300
9848 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM507 | INTERSECT MODIF OWASSO ARRA: EAST 86TH STREET NORTH TO GARNETT ROAD INTERSECTION | Safety/Traffic Management | 2010-07-16 | 2010-09-09 |  | 2010-11-05 | 239679 | 0.100
9849 | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CREEK | TULSA | 01 | STIM508 | PAVEMENT REHABILITATION SAPULPA ARRA: 71ST ST SOUTH FROM RIVA RIDGE ROAD EAST TO 41ST STREET | Pavement Improvement | 2010-08-02 | 2010-09-20 | 2010-10-01 | 2010-12-10 | 209634.6 | 0.500
9850 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM510 | PAVEMENT REHABILITATION TULSA ARRA: 61ST STREET - YALE TO SHERIDAN | Pavement Improvement | 2010-10-04 | 2010-10-25 | 2011-03-12 |  | 1154002.81 | 1.000
9851 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM511 | PAVEMENT REHABILITATION TULSA ARRA: RIVERSIDE DRIVE FROM 68TH STREET TO 71ST STREET SOUTH | Safety/Traffic Management | 2010-10-04 | 2010-10-04 | 2011-01-31 |  | 332646.88 | 0.300
9852 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM512 | RESURFACE BROKEN ARROW ARRA: FLORENCE ST(111TH ST S) BEG @ OLIVE AVE(129TH E. AVE) & EXT TO ASPEN AVE(145TH E. AVE) | Pavement Improvement | 2010-07-05 | 2010-07-05 | 2010-10-02 |  | 310801 | 1.000
9853 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM513 | RESURFACE BROKEN ARROW ARRA: 23RD ST(COUNTY LINE) BEG @ JASPER ST(131ST ST S) & EXT TO YAZOO ST(141ST ST S) | Pavement Improvement | 2010-07-05 | 2010-07-05 | 2010-10-02 |  | 282225 | 1.000
9854 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM514 | PEDESTRIAN IMPROVEMENTS TULSA ARRA: LEWIS AVE FROM 21ST STREET TO 31ST STREET | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2011-07-30 |  | 1019671.73 | 1.000
9855 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM515 | PEDESTRIAN IMPROVEMENTS TULSA ARRA: UNION AVE FROM 71ST STREET TO 81ST STREET | Pavement Improvement | 2010-08-30 | 2010-09-13 | 2010-11-27 |  | 668664.01 | 1.000
9856 | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MURRAY |  | 04 | STIM516 | PEDESTRIAN IMPROVEMENTS SULPHUR ARRA SH-7 FROM 9TH ST EAST 0.521 MI TO FIRST ST | Transportation Enhancements | 2010-07-12 | 2010-07-12 | 2010-09-10 | 2010-10-29 | 298566 | 0.521
9857 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM517 | "GRADE, DRAIN & SURFACE WIDEN POST ROAD, BEGIN AT SE 15TH AND EXTEND NORTH TO RENO AVE." | Pavement Widening | 2010-10-04 | 2010-10-04 | 2011-07-10 |  | 2743619 | 1.000
9858 | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM518 | INTERSECTION MOD. & TRAF. SIGNALS INTERSECTION MOD & TRAFFIC SIGNALS @ EAST ADMIRAL PLACE & SOUTH GARNETT ROAD. | Safety/Traffic Management | 2010-11-01 | 2010-11-08 | 2010-12-30 |  | 505184.44 | 0.250
9859 | Underway | C250,C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MAJOR |  | 03 | STIM519 | Bridge replacement and redo approaches of US-281 over Griever Creek approx. 5.0 miles north of junction of US-281 and US-60E | Bridge Replacement | 2010-08-02 | 2010-06-25 | 2011-05-03 |  | 2203565 | 1.000
9860 | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | POTTAWATOMIE |  | 05 | STIM525 | Railroad Rehabilation - Replacement of railroad ties, culverts, and bridge decking north out of Shawnee | Other | 2010-09-21 | 2010-10-01 |  |  | 4000000 | 0.010
9861 | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA |  | 05 | STIM526 | Railroad Rehabilation - Stabilize the river banks & THE railroad bed along the OKC to Shawnee spur (multiple locations) | Other | 2010-07-21 | 2010-08-02 |  |  | 4000000 | 0.010
9862 | Underway | C200,C240 | Highway Infrastructure Investment Grant | OKLAHOMA | BECKHAM |  | 03 | STIM527 | Resurface I-40 eastward from mile marker 22 to approximatly mile marker 25. | Pavement Improvement | 2010-06-07 | 2010-06-10 | 2010-10-04 |  | 3036915 | 2.360
9863 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | OKLAHOMA | GARFIELD |  | 03 | STIM528 | Reconstruct US-81 beginning at the Kingfisher C/L & extending north approximately 7.2 miles resurfacing both the north and south lanes | Pavement Widening | 2010-08-02 | 2010-07-29 | 2011-01-28 | 2010-11-30 | 2110225 | 7.200
9864 | Underway | C490 | OJT/SS | OKLAHOMA | OKLAHOMA |  | 05 | STIM529 | ARRA O.J.T. SUPPORTIVE SERVICES | Other | 2010-08-05 | 2010-08-05 |  |  | 96180
9865 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 0000183 | Enhance safety to pedestrians and bicyclists by repaving the EWEB Bike Path between Pioneer Parkway and 31st street in Eugene. | Other | 2009-05-11 | 2009-05-11 |  | 2009-06-18 | 1766.48
9866 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | 0100030 | Pave Salem Ave between Sherman St and the UP railroad crossing in Albany to improve safety and extend pavement life. | Pavement Improvement | 2009-07-14 | 2009-07-22 | 2009-08-31 | 2010-03-24 | 1040874.6
9867 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | 0100031 | Pave Salem Ave between Sherman St and the UP railroad crossing in Albany to improve safety and extend pavement life. | Other | 2009-04-28 | 2009-04-28 |  |  | 3129.4
9868 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | 0305019 | Improves safety on Hersey St between Oak St and Ann St in Ashland by reconstructing sidewalks. | Transportation Enhancements | 2009-07-14 | 2009-08-05 | 2009-10-31 | 2009-11-20 | 192069.3
9869 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 0305020 | Pave several city streets in Ashland to improve safety and extend pavement life. | Other | 2009-04-15 | 2009-04-15 |  | 2009-07-16 | 20095.52
9870 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | 0305021 | Improves safety on Hersey St between Oak St and Ann St in Ashland by reconstructing sidewalks. | Other | 2009-04-15 | 2009-04-15 |  |  | 3986.69
9871 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 0305022 | Pave several city streets in Ashland to improve safety and extend pavement life. | Pavement Improvement | 2009-08-11 | 2009-09-22 | 2009-10-31 | 2009-10-30 | 389776.33
9872 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | 0315006 | Pave several city streets in Astoria to improve safety and extend pavement life. | Pavement Improvement | 2010-03-03 | 2010-07-20 | 2010-08-31 | 2010-08-05 | 195779
9873 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | 0315007 | Pave several city streets in Astoria to improve safety and extend pavement life. | Other | 2009-07-23 | 2009-07-23 |  | 2010-02-04 | 20000
9874 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | 0330007 | Improve pedestrian and bicycle safety by adding sidewalks, curb cuts and drainage on OR 99E between Main St and 4th Street in Aurora. | Transportation Enhancements | 2009-07-24 | 2010-01-13 | 2009-10-15 | 2010-03-10 | 128175.52 | 0.090
9875 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | 0330008 | Improve pedestrian and bicycle safety by adding sidewalks, curb cuts and drainage on OR 99E between Main St and 4th Street in Aurora. | Other | 2009-06-25 | 2009-06-25 |  | 2009-06-26 | 344.11 | 0.090
9876 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | BAKER |  | 02 | 0365020 | Construct a pedestrian/bicycle shared use path on the Leo Adler Memorial Parkway between Madison St and Court St in Baker City. | Transportation Enhancements | 2009-11-23 | 2010-05-11 | 2010-09-30 | 2010-10-09 | 217064
9877 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535022 | Pave Hall Blvd between Hart Rd and Ridgecrest Dr in Beaverton to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2009-12-18 | 46671.81
9878 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535023 | Improve pedestrian safety and access by constructing sidewalks and ADA ramps on Laurelwood Ave and 87th Ave in Beaverton. | Other | 2009-07-08 | 2009-07-08 |  | 2010-01-21 | 212580.97
9879 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535024 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Other | 2009-08-05 | 2009-08-05 |  |  | 117929.99
9880 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535026 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Safety/Traffic Management | 2009-08-28 | 2009-08-28 | 2011-08-31 |  | 280000
9881 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535027 | Pave Hall Blvd between Hart Rd and Ridgecrest Dr in Beaverton to improve safety and extend pavement life. | Pavement Improvement | 2009-12-18 | 2010-02-23 | 2010-05-15 | 2010-05-06 | 517883.67
9882 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535028 | Improve pedestrian safety and access by constructing sidewalks and ADA ramps on Laurelwood Ave and 87th Ave in Beaverton. | Transportation Enhancements | 2010-02-19 | 2010-03-16 | 2010-07-15 | 2010-06-21 | 418307.38
9883 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535029 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Safety/Traffic Management | 2010-03-05 | 2010-07-07 | 2010-09-03 | 2010-08-06 | 300500.81
9884 | Completed | C240,C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535032 | PAVEMENT PRESERVATION. GRIND AND REPLACE WITH 4-7" OF LEVEL 3 HMAC | Pavement Improvement | 2010-07-06 | 2010-08-20 | 2010-11-30 | 2010-11-12 | 642947.87
9885 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | 0580035 | Pave several city streets in Bend to improve safety and extend pavement life. | Pavement Improvement | 2009-09-18 | 2010-04-30 | 2010-06-30 | 2010-06-08 | 1125940.16
9886 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES | BEND | 02 | 0580036 | Pave several city streets in Bend to improve safety and extend pavement life. | Other | 2009-05-04 | 2009-05-04 |  | 2009-07-13 | 50014.3
9887 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 05 | 1075005 | Improve vehicle and pedestrian safety and extend pavement life by paving and adding curbs and sidewalk on North Knights Bridge Rd between Knights Bridge and N Grant St in Canby. | Other | 2009-06-22 | 2009-06-22 |  | 2010-03-11 | 19124.86
9888 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 05 | 1075006 | Improve vehicle and pedestrian safety and extend pavement life by paving and adding curbs and sidewalk on North Knights Bridge Rd between Knights Bridge and N Grant St in Canby. | Pavement Improvement | 2010-04-21 | 2010-06-16 | 2010-08-17 | 2010-12-17 | 305507.14
9889 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HARNEY |  | 02 | 1240011 | Pave Pine St between 1st St and 6th St in Central Point to improve safety and extend pavement life. | Safety/Traffic Management | 2010-02-04 | 2010-08-02 | 2010-07-31 | 2010-08-26 | 337276.31
9890 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 1240012 | Pave Pine St between 1st St and 6th St in Central Point to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2010-01-14 | 24877.49
9891 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | WASCO |  | 02 | 1342003 | Improves safety and access on US 30 at the Brewery Grade intersection in The Dalles by reconstructing intersection to a round-about. | Pavement Improvement | 2009-07-09 | 2009-08-25 | 2010-05-01 | 2010-06-03 | 2524023.94 | 0.410
9892 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | 1525004 | Pave North 10th St between Central Ave and Cedar Ave in Coos County to improve safety and extend pavement life. | Pavement Improvement | 2009-10-09 | 2009-11-30 | 2009-11-30 | 2010-05-07 | 332720.29
9893 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | 1555007 | Improve pavement, add curbs, sidewalks and signals to enhance safety and reduce wear and tear on OR Hwy 8 in Cornelius. | Other | 2009-04-09 | 2009-04-09 |  | 2009-06-16 | 24265.33
9894 | Completed | C240,C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 1555008 | Improve pavement, add curbs, sidewalks and signals to enhance safety and reduce wear and tear on OR Hwy 8 in Cornelius. | Pavement Improvement | 2008-05-22 | 2008-06-09 | 2009-02-28 | 2009-09-10 | 495659
9895 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 1555011 | Improve safety and extend the life of the pavement by sealing craks and repaving several streets in Cornelius. | Other | 2009-08-21 | 2009-08-21 |  | 2010-02-11 | 21474.9
9896 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | BENTON | CORVALLIS | 04 | 1580031 | Pave several city streets in Corvallis to improve safety and extend pavement life. | Pavement Improvement | 2009-08-28 | 2009-09-08 |  |  | 736145.54
9897 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | 1580032 | Enhance safety to pedestrians and bicyclists by repaving the Corvallis-Phillomath multi-use bicycle and pedestrian path in Benton County. | Pavement Improvement | 2009-07-09 | 2009-07-29 |  |  | 251120.55
9898 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | BENTON | CORVALLIS | 04 | 1580034 | Pave Western Ave between 7th and 17th St and 5th St between Western and 9th Ave in Corvallis to improve safety and extend pavement life. | Pavement Improvement | 2010-01-14 | 2010-05-18 |  |  | 407711.55
9899 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | 1580041 | PAVE EXISTING STREET | Pavement Improvement | 2010-01-05 | 2010-02-05 |  |  | 112514.39
9900 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 1595004 | Improve safety on South 8th St and Woodson Bridge approaches in Cottage Grove by adding curb, gutter, sidewalks and paved shoulders. | Other | 2009-08-13 | 2009-08-13 |  | 2010-02-11 | 5188.99
9901 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 1595005 | Improve safety on South 8th St and Woodson Bridge approaches in Cottage Grove by adding curb, gutter, sidewalks and paved shoulders. | Pavement Improvement | 2010-03-08 | 2010-04-07 | 2010-09-30 | 2010-05-14 | 175361.27
9902 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 1595007 | REHAB BRIDGE FOR PEDESTRIAN AND BICYCLE TRAFFIC | Transportation Enhancements | 2010-11-19 | 2011-01-14 | 2011-11-30 | 2011-11-30 | 489329.64
9903 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 1770002 | Pave several city streets in Dallas to improve safety and extend pavement life. | Pavement Improvement | 2009-08-06 | 2009-08-24 | 2009-10-02 | 2009-09-16 | 351894.04
9904 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 1770003 | Pave several city streets in Dallas to improve safety and extend pavement life. | Other | 2009-06-04 | 2009-06-04 |  | 2009-07-16 | 697.26
9905 | Underway | C220 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 2385052 | Enhances bridge and trail elements to improve usage of the Delta Ponds multi-use path between Goodpasture Island and Robin Hood Ln in Eugene. | Other | 2007-05-17 | 2007-05-17 |  |  | 60027.44
9906 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 2385059 | Improves access to the Eugene train depot by adding sidewalk and lighting to the pedestrian access. | Transportation Enhancements | 2009-07-13 | 2009-08-03 | 2009-10-31 | 2010-06-30 | 139245.05
9907 | Underway | C220 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385060 | Enhances bridge and trail elements to improve usage of the Delta Ponds multi-use path between Goodpasture Island and Robin Hood Ln in Eugene. | Transportation Enhancements | 2009-08-10 | 2009-08-24 |  |  | 1229085.82
9908 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385061 | Complete pavement preservation project on Garfeield St between W 6th Ave and W 11th Ave in Eugene to improve safety and extend the life of the pavement. | Other | 2009-05-21 | 2009-05-21 |  |  | 31625.82
9909 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385063 | Complete pavement preservation project on Crescent Ave between Gamefarm Rd and Shadowview in Eugene to improve safety and extend the life of the pavement. | Other | 2009-06-19 | 2009-06-19 |  | 2009-11-19 | 6000
9910 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385064 | Complete pavement preservation project on High St between 3rd Ave and 17th Ave in Eugene to improve safety and extend the life of the pavement. | Other | 2009-06-19 | 2009-06-19 |  |  | 43268.18
9911 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385068 | Complete pavement preservation project on 11th Ave between Garfield and Tyinn and 13th Ave between Alder and Washington in Eugene to improve safety and extend the life of the pavement. | Pavement Improvement | 2010-07-07 | 2010-07-06 |  |  | 691951.33
9912 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 2605001 | Pave several city streets in Florence to improve safety and extend pavement life. | Other | 2009-04-29 | 2009-04-29 |  | 2009-12-10 | 15000
9913 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 2605002 | Pave several city streets in Florence to improve safety and extend pavement life. | Pavement Improvement | 2010-01-06 | 2010-05-07 | 2010-05-31 | 2010-08-05 | 186437
9914 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 2620003 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Other | 2006-04-04 | 2006-04-04 |  | 2009-06-17 | 86399.5
9915 | Completed | C220,C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 2620004 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Transportation Enhancements | 2008-04-04 | 2008-04-28 | 2008-12-31 | 2010-01-11 | 1325945.17
9916 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 2620005 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Other | 2007-08-29 | 2007-08-29 |  |  | 9222.45
9917 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 2900008 | Pave several city streets in Gladstone to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  |  | 66989.51
9918 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 2900009 | Pave several city streets in Gladstone to improve safety and extend pavement life. | Pavement Improvement | 2010-03-04 | 2010-05-06 | 2010-07-30 | 2010-07-14 | 721679.79
9919 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 02 | 3055403 | Pave several city streets in Grants Pass to improve safety and extend pavement life. | Other | 2009-06-05 | 2009-06-05 |  | 2010-01-14 | 60000
9920 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 04 | 3055404 | Pave several city streets in Grants Pass to improve safety and extend pavement life. | Pavement Improvement | 2010-02-01 | 2010-05-03 | 2010-05-31 | 2010-06-15 | 513254.73
9921 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 02 | 3055405 | CONSTRUCT 6 NEW TRANSIT SHELTERS | Other | 2009-09-11 | 2009-09-11 | 2012-10-20 |  | 65000
9922 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 3125034 | Improve safety and access to vehicles, bicycles and pedestrians on 242nd and Hogan Rd between Glisan St and Stark St by widening the seciton of road and adding four travel lanes, center turn lane, bic | Other | 2009-06-11 | 2009-06-11 |  | 2009-10-22 | 34032.76
9923 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 3125035 | Improve safety and access to vehicles, bicycles and pedestrians on 242nd and Hogan Rd between Glisan St and Stark St by widening the seciton of road and adding four travel lanes, center turn lane, bic | Pavement Improvement | 2009-11-24 | 2010-02-01 | 2009-09-30 | 2010-10-15 | 1711867.04
9924 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 3205001 | Extend the life of the pavement on city streets in Happy Valley by sealing and resurfacing several minor arterial streets. | Other | 2009-05-15 | 2009-05-15 |  | 2010-02-04 | 80051.09
9925 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 03 | 3205002 | Extend the life of the pavement on city streets in Happy Valley by sealing and resurfacing several minor arterial streets. | Pavement Improvement | 2010-03-05 | 2010-08-23 | 2010-10-31 | 2010-10-21 | 708367.81
9926 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | 3370003 | Pave Feedville Rd and Kelli blvd between OR 395 and Cook Industrial site in Umatilla County to improve safety and extend pavement life. | Pavement Improvement | 2009-12-22 | 2010-07-23 | 2010-07-31 | 2010-07-30 | 297706.65
9927 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | 3370004 | Pave Feedville Rd and Kelli blvd between OR 395 and Cook Industrial site in Umatilla County to improve safety and extend pavement life. | Other | 2009-07-29 | 2009-07-29 |  | 2009-07-31 | 14067.89
9928 | Underway | C220 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 3410013 | MULTI-USE PATH THAT CONNECTS TO QUATAMA LRT STATION | Other | 2010-07-26 | 2010-07-26 | 2012-03-22 |  | 138000
9929 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OREGON | MORROW |  | 02 | 3650003 | Enhance pedestrian and bicycle safety by constructing sidewalks, bike lanes, and a planter strip with street trees along 1st St and Main Ave in Irrigon. | Transportation Enhancements | 2009-07-09 | 2009-07-23 | 2009-10-31 | 2010-12-15 | 1527961.59
9930 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MORROW |  | 02 | 3650004 | Enhance pedestrian and bicycle safety by constructing sidewalks, bike lanes, and a planter strip with street trees along 1st St and Main Ave in Irrigon. | Other | 2009-05-13 | 2009-05-13 |  | 2009-06-18 | 94570.28
9931 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 3700009 | Improve bicycle and pedestrian safety and mobility by adding bike lanes and sidewalks to C St in Jacksonville. | Other | 2009-05-14 | 2009-05-14 |  | 2010-01-21 | 58000
9932 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | 3700010 | Improve bicycle and pedestrian safety and mobility by adding bike lanes and sidewalks to C St in Jacksonville. | Transportation Enhancements | 2010-02-19 | 2010-03-08 | 2010-08-31 | 2010-08-04 | 180500
9933 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | 3850008 | Pave Dearborn Ave and Chemawa Rd in Keizer to improve safety and extend pavement life. | Pavement Improvement | 2010-04-06 | 2010-08-27 | 2010-09-15 | 2010-09-15 | 96539.43
9934 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | 3850009 | Pave Dearborn Ave and Chemawa Rd in Keizer to improve safety and extend pavement life. | Other | 2010-03-22 | 2010-03-22 |  | 2010-03-04 | 199.89
9935 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | KLAMATH |  | 02 | 3970018 | Improve safety of pedestrian connections to the bus and train station in Klamath Falls by restoring fencing, adding lighting and crossing enhancements. Improves mobility by repaving Spring St. | Transportation Enhancements | 2009-06-10 | 2009-07-13 | 2009-09-30 | 2009-10-14 | 136097.56
9936 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UNION |  | 02 | 4035014 | Pave Spruce St between Monroe Ave and Z avenue in LaGrande to improve safety and extend pavement life. | Pavement Improvement | 2010-02-11 | 2010-06-19 | 2010-07-31 | 2010-06-25 | 230822.74
9937 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UNION |  | 02 | 4035015 | Pave Spruce St between Monroe Ave and Z avenue in LaGrande to improve safety and extend pavement life. | Other | 2009-07-20 | 2009-07-20 |  | 2010-01-14 | 11574.51
9938 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 4055009 | Pave Royce and McNary St in Lake Oswego to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2010-02-04 | 83490.87
9939 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 4055010 | Pave Royce and McNary St in Lake Oswego to improve safety and extend pavement life. | Pavement Improvement | 2010-03-08 | 2010-05-06 | 2010-07-30 | 2010-07-12 | 395394.88
9940 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | 4165007 | Pave 2nd St and Airport Rd in Lebanon to improve safety and extend pavement life. | Pavement Improvement | 2010-02-23 | 2010-04-23 | 2010-07-31 | 2010-07-30 | 253672.93
9941 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | 4165008 | Pave 2nd St and Airport Rd in Lebanon to improve safety and extend pavement life. | Other | 2009-07-01 | 2009-07-01 |  | 2010-01-28 | 43112.92
9942 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | 4500006 | Pave several city streets in McMinnville to improve safety and extend pavement life. | Pavement Improvement | 2009-07-16 | 2009-08-13 | 2010-05-28 | 2009-10-20 | 739314.74
9943 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | 4500007 | Pave several city streets in McMinnville to improve safety and extend pavement life. | Other | 2009-06-18 | 2009-06-18 |  | 2009-06-19 | 7924.48
9944 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 03 | 4865010 | Improve pedestrian safety and access by reconstructing sidewalks, streetscape, and curb extensions on Jackson St between Main St and 21st Ave in Clackamas. | Other | 2009-08-05 | 2009-08-05 |  | 2010-03-04 | 159573.74
9945 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLATSOP | PORTLAND (WA) | 01 | 4865013 | Improve pedestrian safety and access by reconstructing sidewalks, streetscape, and curb extensions on Jackson St between Main St and 21st Ave in Clackamas. | Transportation Enhancements | 2010-04-15 | 2010-05-28 | 2010-10-29 | 2010-11-24 | 817275.02
9946 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 4955001 | Pave Stadium Dr and Jackson St in Monmouth to improve safety and extend pavement life. | Pavement Improvement | 2010-01-11 | 2010-05-11 | 2010-06-30 | 2010-08-19 | 153925.36
9947 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 4955002 | Pave Stadium Dr and Jackson St in Monmouth to improve safety and extend pavement life. | Other | 2009-08-10 | 2009-08-10 |  | 2009-10-12 | 2170.49
9948 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | GRANT |  | 02 | 5025101 | Install additional lights on Main Street in Mt. Vernon to improve pedestrian safety. | Transportation Enhancements | 2009-02-24 | 2009-03-30 | 2009-10-23 | 2009-08-14 | 99964 | 0.500
9949 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | 5210002 | Pave several city streets in Newberg to improve safety and extend pavement life. | Other | 2009-10-30 | 2009-10-30 |  | 2010-02-11 | 34745.71
9950 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | 5210003 | Pave several city streets in Newberg to improve safety and extend pavement life. | Pavement Improvement | 2010-03-18 | 2010-06-21 | 2010-08-15 | 2010-11-11 | 449218.33
9951 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | 5245004 | Improve safety and access with repairs to sidewalks, curb and gutter, paving, and lighting on Bay Blvd in Newport. | Pavement Improvement | 2009-08-17 | 2009-09-08 | 2010-06-30 | 2010-06-30 | 583000
9952 | Underway | C200,C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | 5245005 | Improve safety and access with repairs to sidewalks, curb and gutter, paving, and lighting on Bay Blvd in Newport. | Other | 2009-04-15 | 2009-04-15 |  |  | 11671.95
9953 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 5245006 | Improve safety and extend pavement life on several city streets in Talent and Phoenix by paving, addind additional signage and signals. | Pavement Improvement | 2009-08-11 | 2009-10-12 | 2009-11-16 | 2010-02-23 | 381548.97
9954 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | 5245007 | Pave several city streets in Newport to improve safety and extend pavement life. | Other | 2009-05-21 | 2009-05-21 |  |  | 2315.29
9955 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | 5245008 | Pave several city streets in Newport to improve safety and extend pavement life. | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2009-10-16 | 2009-10-20 | 191502.45
9956 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | 5300006 | Pave Sherman Ave between Newmark St and City Limits in North Bend to improve safety and extend pavement life. | Pavement Improvement | 2010-03-01 | 2010-06-28 | 2010-07-30 | 2010-11-17 | 233212.82
9957 | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | OREGON | MALHEUR |  | 02 | 5490003 | Enhance safety by widening and repaving roadway, and installing sidewalks and curbs on N Oregon St between Idaho Ave and NW 1st St in Ontario. | Pavement Improvement | 2009-07-06 | 2009-07-24 | 2009-11-30 | 2010-10-22 | 1991199.17
9958 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 5520019 | Improve vehicle and pedestrian safety, mobility and traffic flow on Warner Milne Rd between Beaversreek and Mollala in Oregon City buy realigning the intersection, updating signal timing and adding si | Safety/Traffic Management | 2009-08-18 | 2009-09-21 | 2010-05-14 | 2010-08-20 | 1152241.94
9959 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 03 | 5520020 | Enhance safety on historic McLoughlin Promenade multi-use path between 7th St and S 1st St in Oregon City by restoring historing walls, including wall caps and joints, handrails, stairs and tunnel. | Transportation Enhancements | 2009-07-09 | 2009-08-20 | 2010-09-01 | 2010-06-29 | 1065721
9960 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 5520023 | Improve vehicle and pedestrian safety, mobility and traffic flow on Warner Milne Rd between Beaversreek and Mollala in Oregon City buy realigning the intersection, updating signal timing and adding si | Other | 2009-04-27 | 2009-04-27 |  | 2009-08-31 | 14151.71
9961 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | 5715013 | Pave Tutuilla Rd between US 395 (Southgate) and SW Athens Way in Umatilla County to improve safety and extend pavement life. | Pavement Improvement | 2010-01-07 | 2010-06-30 | 2010-07-31 | 2010-09-21 | 357100.17
9962 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | 5715014 | Pave Tutuilla Rd between US 395 (Southgate) and SW Athens Way in Umatilla County to improve safety and extend pavement life. | Other | 2009-07-29 | 2009-07-29 |  | 2009-07-31 | 19959.51
9963 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 01 | 5900175 | Improve safety and mobility for motorists, pedestrians and bicyclists and extend pavement life by reconstructing roadway, sidewalks and bikelanes on NW 23rd Ave between Lovejoy and Burnside. | Safety/Traffic Management | 2010-01-04 | 2010-01-04 |  |  | 432000
9964 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900197 | Complete pavement preservation project on several streets in SE Portland to improve safety and extend the life of the pavement. | Pavement Improvement | 2010-03-22 | 2010-03-25 |  |  | 2596002.47
9965 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900199 | Improve safety and accessibility in southwest and east Portland with curb cuts and sidewalks on variuos streets. | Pavement Improvement | 2010-04-12 | 2010-05-26 |  |  | 1224083.36
9966 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900201 | Improve bicycle safety and mobility by adding striping, signage and wayfinding to the Portland bicycle boulevard project. | Other | 2009-07-21 | 2009-07-21 |  | 2009-11-10 | 70332.39
9967 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 01 | 5900202 | Improve interesection safety and access by adding a right turn lane from 82nd Ave to westbound Columbia Blvd in Portland. | Other | 2009-07-20 | 2009-07-20 | 2011-06-30 | 2011-06-30 | 200000
9968 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900203 | Pave Springwater Trail between UPRR Bridge and the East City border in Portland to improve safety and extend the life of the pavement. | Other | 2009-07-21 | 2009-07-21 |  |  | 99358.25
9969 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900204 | Complete pavement preservation project on several streets in SE Portland to improve safety and extend the life of the pavement. | Other | 2009-08-05 | 2009-08-05 |  | 2009-12-07 | 15291.99
9970 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900205 | Pave Springwater Trail between UPRR Bridge and the East City border in Portland to improve safety and extend the life of the pavement. | Pavement Improvement | 2010-03-18 | 2010-05-06 |  |  | 1191463.06
9971 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900207 | Improve safety and accessibility in southwest and east Portland with curb cuts and sidewalks on variuos streets. | Other | 2009-08-05 | 2009-08-05 |  | 2009-12-07 | 175906.11
9972 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 01 | 5900212 | Improve bicycle, pedestrian and motorist safety by replacing street lighting on several city streets around Keller Auditorium in downtown Portland. | Safety/Traffic Management | 2011-01-17 | 2011-01-17 |  |  | 5334620.02
9973 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900215 | Improve bicycle safety and mobility by adding striping, signage and wayfinding to the Portland bicycle boulevard project. | Transportation Enhancements | 2010-03-09 | 2010-03-31 |  |  | 705487.85
9974 | Underway | C220 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900216 | Improve multi-modal access for patrons of Amtrak, light rail transit, streetcar, inter-city and city bus by making facility improvements at Union Station. | Transportation Enhancements | 2010-06-10 | 2010-06-10 |  |  | 873741.75
9975 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | 5985008 | Improve mobility and safety by adding 2nd Street egress to OR 126 (3rd St) in Prineville. | Other | 2009-03-24 | 2009-03-24 |  | 2009-06-16 | 4126.71
9976 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | 5985009 | Improve mobility and safety by adding 2nd Street egress to OR 126 (3rd St) in Prineville. | New Construction | 2009-07-13 | 2009-08-24 | 2009-10-31 | 2010-04-28 | 280974.72
9977 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | 5985010 | Pave several city streets in Prineville to improve safety and extend pavement life. | Pavement Improvement | 2009-08-05 | 2009-09-02 | 2009-09-15 | 2009-11-10 | 218674.6
9978 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | 5985011 | Pave several city streets in Prineville to improve safety and extend pavement life. | Other | 2009-03-24 | 2009-03-24 |  |  | 3312.4
9979 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | 6120009 | Improve safety by reconstructing 5th St between SW Glacier and Jackpine in Redmond. Project includes paving, stormwater system, curb repair and sidewalks. | Other | 2009-02-23 | 2009-02-23 |  |  | 3468 | 1.020
9980 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | 6120010 | Improve safety by reconstructing 5th St between SW Glacier and Jackpine in Redmond. Project includes paving, stormwater system, curb repair and sidewalks. | Pavement Improvement | 2009-07-07 | 2009-08-03 | 2010-06-30 | 2010-07-08 | 3657957.62 | 1.020
9981 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | 6365002 | Pave Garden Valley Blvd between Stewart Pkwy and West City Line in Roseburg to improve safety and extend pavement life. | Pavement Improvement | 2010-02-22 | 2010-07-02 | 2010-07-15 | 2010-07-30 | 658791
9982 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | 6460002 | Improve vehcile and pedestrian safety and extend pavement life on Columbia Blvd between US 30 and 1st St in St. Helens by paving and adding sidewalks, curb and gutter. | Pavement Improvement | 2010-02-17 | 2010-07-06 | 2010-06-30 | 2010-07-21 | 204384.94
9983 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | 6460003 | Improve vehcile and pedestrian safety and extend pavement life on Columbia Blvd between US 30 and 1st St in St. Helens by paving and adding sidewalks, curb and gutter. | Other | 2009-08-14 | 2009-08-14 |  | 2010-01-21 | 59452.06
9984 | Underway | C220 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 6490071 | Preserve investment in Union Street Rail Road bridge shared use path in Salem by removing lead based paint and re-painting upper portion of the bridge. | Other | 2009-05-11 | 2009-05-11 |  |  | 20213.81
9985 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | 6490072 | Pave sections of Hyacinth St, Chemawa Rd, Cordon Rd, Hawthorne Ave and Kuebler Blvd in Salem to improve safety and extend pavement life. | Other | 2009-08-13 | 2009-08-13 |  |  | 252944.92
9986 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | 6490073 | Pave sections of Hyacinth St, Chemawa Rd, Cordon Rd, Hawthorne Ave and Kuebler Blvd in Salem to improve safety and extend pavement life. | Pavement Improvement | 2010-03-08 | 2010-03-25 | 2010-09-30 | 2011-05-27 | 3677369.34
9987 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | 6490075 | Preserve investment in Union Street Rail Road bridge shared use path in Salem by removing lead based paint and re-painting upper portion of the bridge. | Transportation Enhancements | 2009-10-16 | 2009-11-09 | 2010-05-15 | 2011-09-30 | 2066707.9
9988 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | POLK | SALEM | 05 | 6490077 | Improve bicycle and pedestrian safety and mobility by improving the bike / ped path in Wallace Marine Park from the Union St Bridge to Glen Creek Rd. | Other | 2009-11-24 | 2009-11-24 | 2012-08-16 |  | 50000
9989 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | 6550002 | Improve safety along road by removing and replacing curb, gutter, sidewalk and street trees along US 30 between Old Portland Rd and Crown Zellerbach Rd in Scappoose. | Transportation Enhancements | 2009-07-15 | 2009-08-05 | 2009-09-30 | 2009-10-30 | 251291 | 1.030
9990 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | 6550003 | Improve safety along road by removing and replacing curb, gutter, sidewalk and street trees along US 30 between Old Portland Rd and Crown Zellerbach Rd in Scappoose. | Other | 2009-04-15 | 2009-04-15 |  | 2009-06-18 | 59079.34 | 1.030
9991 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 6710003 | Pave Sherwood Blvd between 3rd St and Langer Dr in Sherwood to improve safety and extend pavement life. | Other | 2009-08-26 | 2009-08-26 |  | 2010-02-11 | 23666.88
9992 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960020 | Complete pavement preservation project on Pioneer Parkway between Hayden Bridge and Q St in Springfield to improve safety and extend pavement life. | Other | 2009-07-01 | 2009-07-01 |  |  | 68314.84
9993 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960021 | Complete pavement preservation project on Pioneer Parkway between Hayden Bridge and Q St in Springfield to improve safety and extend pavement life. | Pavement Improvement | 2010-03-26 | 2010-04-20 | 2010-10-29 | 2010-10-26 | 1968740.17
9994 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960029 | Improve safety and traffic flow on several city streets in Springfield retiming traffic signals. | Safety/Traffic Management | 2010-01-12 | 2010-05-18 | 2010-06-25 | 2010-06-25 | 177132.21
9995 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960030 | Improve safety on several city streets in Springfield by replacing low pressure sodium lights with high pressure sodium and metal halide lights. | Other | 2009-08-10 | 2009-08-10 |  | 2009-11-19 | 15800.2
9996 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960031 | Improve safety and traffic flow on several city streets in Springfield retiming traffic signals. | Other | 2009-08-13 | 2009-08-13 |  |  | 12210.42
9997 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 7250009 | Improve safety and extend pavement life on several city streets in Talent and Phoenix by paving, addind additional signage and signals. | Other | 2009-04-16 | 2009-04-16 |  | 2009-07-16 | 43161.49
9998 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 7365007 | Pave Bonita, Durham and 72nd Ave in Tigard to improve safety and extend pavement life. | Other | 2009-08-21 | 2009-08-21 |  | 2010-02-11 | 46057.84
9999 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8015000 | Pave Salamo Rd between Barrington Dr and Rosemont in West Linn to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2010-03-04 | 84710.75
10000 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8015001 | Pave Salamo Rd between Barrington Dr and Rosemont in West Linn to improve safety and extend pavement life. | Pavement Improvement | 2010-04-01 | 2010-06-14 | 2010-08-30 | 2010-09-30 | 1049813.73
10001 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8015002 | Improve pedestrian and bicycle safety and mobility by construcing the West Linn Trainl bike / ped path. | Other | 2009-11-24 | 2009-11-24 | 2012-03-16 |  | 250000
10002 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8280005 | Improve vehicle, bicycle and pedestrian safety on Barber St between Boberg Rd and Boones Ferry Rd in Wilsonville by widening to allow for bike lanes and sidewalks on both sides and a center turn lane. | Other | 2009-08-26 | 2009-08-26 |  | 2010-03-11 | 24499.83
10003 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8280006 | Improve vehicle, bicycle and pedestrian safety on Barber St between Boberg Rd and Boones Ferry Rd in Wilsonville by widening to allow for bike lanes and sidewalks on both sides and a center turn lane. | Transportation Enhancements | 2010-04-19 | 2010-06-03 | 2010-11-17 | 2010-12-24 | 623424.35
10004 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HARNEY |  | 02 | C001011 | Pave Wingville Ln from mile point 0 to milp point 4.76 in Baker County to improve safety and extend pavement life. | Pavement Improvement | 2010-03-01 | 2010-07-07 | 2010-09-01 | 2010-09-10 | 421301.23
10005 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | BAKER |  | 02 | C001012 | Pave Wingville Ln from mile point 0 to milp point 4.76 in Baker County to improve safety and extend pavement life. | Other | 2009-07-21 | 2009-07-21 |  | 2009-07-31 | 13271.77
10006 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | C003035 | Pave Alpine Rd in Benton County to improve safety and extend pavement life. | Pavement Improvement | 2009-07-20 | 2009-07-20 |  |  | 317997.56
10007 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | C003036 | Improve safety to pedestrians and bicyclists by repaving the Campus Way multi-use bicycle and pedestrian path between 35th St and 53rd St in Corvallis. | Pavement Improvement | 2009-07-02 | 2009-07-06 |  |  | 76200.62
10008 | Underway | C200,C240 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | C003037 | Pave Springhill Dr between Buena Vista Rd and Independence Hwy to improve safety and extend pavement life. | Pavement Improvement | 2010-03-10 | 2010-07-06 |  |  | 135902.44
10009 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 05 | C005060 | REALIGN & WIDEN STAFFORD RD - WIDEN MOUNTAIN RD FOR SEPARATE LEFT & RIGHT TURN LANES | Safety/Traffic Management | 2011-01-31 | 2011-01-31 |  | 2011-09-29 | 553531.22
10010 | Underway | C200,C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 03 | C005066 | Pave King Rd between Witchita and 82nd Ave in Clackamas County to improve safety and extend pavement life. | Pavement Improvement | 2010-05-29 | 2010-05-29 |  |  | 591764.35
10011 | Underway | C200,C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 03 | C005067 | Pave Sunnyside Rd between 82nd Ave and 122nd Ave to improve safety and extend pavement life. Improve traffic flow andmobility by replacing traffic signals and controllers and adding video detection a | Pavement Improvement | 2010-05-29 | 2010-08-05 |  |  | 1174987.43
10012 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | C007023 | Pave Lewis & clark Rd between Tucker Creek Rd and Lyngstad Heights Rd in Clatsop County to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2009-09-10 | 17125.84
10013 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | C007024 | Pave Lewis & clark Rd between Tucker Creek Rd and Lyngstad Heights Rd in Clatsop County to improve safety and extend pavement life. | Pavement Improvement | 2009-12-09 | 2010-04-19 | 2010-06-15 | 2010-06-07 | 542394
10014 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | C007025 | Improve pedestrian and bicycle safety and access by constructing shared-use paths, rest/view sites, and gazebo shelters on the Port of Astoria Pedestrian Access Paths. | Transportation Enhancements | 2010-02-16 | 2010-04-05 | 2010-07-30 | 2010-08-06 | 432686.09
10015 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | C009055 | Pave Apiary Rd between mile point 14 and mile point 19 in Columbia County to improve safety and extend pavement life. | Other | 2009-06-09 | 2009-06-09 |  | 2009-09-10 | 50947.86
10016 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | C009056 | Pave Apiary Rd between mile point 14 and mile point 19 in Columbia County to improve safety and extend pavement life. | Safety/Traffic Management | 2009-10-09 | 2010-05-10 | 2010-07-15 | 2010-07-12 | 728584.14
10017 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011057 | Pave and add additional signage to Central Blvd between OR 42 and 10th St in Coos County to improve safety and extend pavement life. | Pavement Improvement | 2010-02-26 | 2010-06-29 | 2010-09-05 | 2010-09-24 | 424459.2
10018 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011058 | Pave and add additional signage to Central Blvd between OR 42 and 10th St in Coos County to improve safety and extend pavement life. | Other | 2009-06-12 | 2009-06-12 |  | 2010-02-04 | 60000
10019 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011059 | Repair the Anson Rogers Bridge on South Coos River Rd in Coos County to improve safety and extend the life of the bridge. | Other | 2009-06-10 | 2009-06-10 |  | 2010-01-14 | 50000
10020 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011060 | Pave Sherman Ave between Newmark St and City Limits in North Bend to improve safety and extend pavement life. | Other | 2009-08-14 | 2009-08-14 |  | 2010-02-04 | 1748.6
10021 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011061 | Repair the Anson Rogers Bridge on South Coos River Rd in Coos County to improve safety and extend the life of the bridge. | Bridge Improvement | 2010-02-03 | 2010-03-23 | 2010-08-31 | 2010-08-16 | 358969.86
10022 | Completed | C250,C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | C013015 | Pave Lone Pine Rd and Smith Rock Way in Crook County to improve safety and extend pavement life. | Pavement Improvement | 2010-01-12 | 2010-04-09 | 2010-06-11 | 2010-06-11 | 531411.53
10023 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | C013016 | Pave Lone Pine Rd and Smith Rock Way in Crook County to improve safety and extend pavement life. | Other | 2009-05-05 | 2009-05-05 |  | 2009-10-26 | 23351.47
10024 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | C017013 | Pave Huntington Rd and Riverview Rd between South Century Drive and Burgess Rd in Deschutes County to improve safety and extend pavement life. | Pavement Improvement | 2009-08-27 | 2009-09-30 | 2009-10-15 | 2009-10-19 | 1074637.3
10025 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | C017014 | Pave Huntington Rd and Riverview Rd between South Century Drive and Burgess Rd in Deschutes County to improve safety and extend pavement life. | Other | 2009-05-03 | 2009-05-03 |  | 2009-06-15 | 19841.7
10026 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | C019036 | Pave Dillard Hwy between mile point .71 and mile point 5.85 in Douglas County to improve safety and extend pavement life. | Other | 2009-06-14 | 2009-06-14 |  | 2009-09-24 | 28087.55
10027 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | C019037 | Pave Dillard Hwy between mile point .71 and mile point 5.85 in Douglas County to improve safety and extend pavement life. | Pavement Improvement | 2009-10-09 | 2010-03-12 | 2010-05-01 | 2010-09-02 | 1511627.46
10028 | Completed | C250 | Highway Infrastructure Investment Grant | OREGON | GRANT |  | 02 | C023007 | Pave County Rd 51 (Adams Rd) between MP 0 and MP 3.24 to improve safety and extend pavement life. | Pavement Improvement | 2010-03-18 | 2010-05-14 | 2010-07-31 | 2010-06-30 | 336793.25
10029 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HARNEY |  | 02 | C025019 | Place chip seal on Silver Creek Rd and Green House Ln in Harney County to improve safety and extend pavement life. | Pavement Improvement | 2009-09-16 | 2010-06-21 | 2009-10-31 | 2010-11-15 | 405634.17
10030 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HARNEY |  | 02 | C025021 | Place chip seal on Silver Creek Rd and Green House Ln in Harney County to improve safety and extend pavement life. | Other | 2009-07-21 | 2009-07-21 |  | 2009-10-31 | 5750.58
10031 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HOOD RIVER |  | 02 | C027013 | Pave Belmont Dr and Cooper Spur Rd in Hood River County to improve safety and extend pavement life. | Other | 2009-05-15 | 2009-05-15 |  | 2010-02-04 | 45392.74
10032 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HOOD RIVER |  | 02 | C027014 | Pave Belmont Dr and Cooper Spur Rd in Hood River County to improve safety and extend pavement life. | Pavement Improvement | 2010-03-09 | 2010-06-28 | 2010-07-31 | 2010-07-30 | 381026.26
10033 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | C029058 | Pave several county roads in Jackson County to improve safety and extend pavement life. | Other | 2009-04-29 | 2009-04-29 |  | 2009-08-20 | 84998.86
10034 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | C029059 | Improve pedestrian and bicycle safety and access by constructing a shared use path on Barnett Rd in Jackson County. | Transportation Enhancements | 2009-10-07 | 2009-11-16 | 2010-07-31 | 2011-07-11 | 1058176.46
10035 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | C029061 | Pave several county roads in Jackson County to improve safety and extend pavement life. | Pavement Improvement | 2009-09-10 | 2009-10-06 | 2010-07-31 | 2009-11-19 | 1390796.14
10036 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JEFFERSON |  | 02 | C031004 | Pave Lone Pine Rd from mile point 0 to mile point 3.7 in Jefferson County to improve safety and extend pavement life. | Pavement Improvement | 2009-09-03 | 2009-10-01 | 2009-10-23 | 2009-11-20 | 432188.52
10037 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JEFFERSON |  | 02 | C031005 | Pave Lone Pine Rd from mile point 0 to mile point 3.7 in Jefferson County to improve safety and extend pavement life. | Other | 2009-05-05 | 2009-05-05 |  | 2009-06-22 | 15527.2
10038 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 02 | C033031 | Pave Old Hwy 99 from mile point 0 to mile point .67 in Josephine County to improve safety and extend pavement life. | Other | 2009-06-04 | 2009-06-04 |  |  | 1386.94
10039 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 04 | C033032 | Pave Old Hwy 99 from mile point 0 to mile point .67 in Josephine County to improve safety and extend pavement life. | Pavement Improvement | 2009-08-17 | 2009-09-28 | 2009-10-31 | 2009-10-30 | 203616.56
10040 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | KLAMATH |  | 02 | C035024 | Improve safety on Washburn Way between Crosby and Joe Wright Rd in Klamath Falls by paving and adding additional signage. | Other | 2009-05-01 | 2009-05-01 |  | 2009-06-08 | 55810.71
10041 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | KLAMATH |  | 02 | C035025 | Improve safety on Washburn Way between Crosby and Joe Wright Rd in Klamath Falls by paving and adding additional signage. | Pavement Improvement | 2009-08-10 | 2009-09-09 | 2009-10-23 | 2009-10-23 | 963054.55
10042 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | C039027 | Enhance safety to pedestrians and bicyclists by repaving the EWEB Bike Path between Pioneer Parkway and 31st street in Eugene. | Pavement Improvement | 2009-07-15 | 2009-07-20 | 2009-09-30 | 2009-09-30 | 308191.66
10043 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | C039028 | Pave Clear Lake Rd and Marcola Rd in Lane County to improve safety and extend pavement life. | Other | 2009-05-07 | 2009-05-07 |  | 2009-11-19 | 75420.85
10044 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | C039029 | Pave Clear Lake Rd and Marcola Rd in Lane County to improve safety and extend pavement life. | Pavement Improvement | 2009-12-17 | 2010-08-12 | 2010-10-01 | 2011-09-23 | 1596640.02
10045 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | C039030 | Complete pavement preservation project on River Rd, 23rd St and Coburg Rd in Eugene to improve safety and extend the life of the pavement. | Other | 2009-06-04 | 2009-06-04 |  | 2009-11-19 | 69037.57
10046 | Completed | C200,C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | C039031 | Complete pavement preservation project on River Rd, 23rd St and Coburg Rd in Eugene to improve safety and extend the life of the pavement. | Pavement Improvement | 2009-12-17 | 2010-07-06 | 2010-10-01 | 2010-09-14 | 1055896.58
10047 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | C039032 | Complete pavement preservation project on W 1st Ave between Seneca Rd and Bertelsen Rd in Eugene to improve safety and extend the life of the pavement. | Other | 2009-06-11 | 2009-06-11 |  |  | 23055.89
10048 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | C041009 | Pave Northbank Rd and Schooner Creek Rd in Lincoln County to improve safety and extend pavement life. | Other | 2009-05-05 | 2009-05-05 |  | 2009-07-16 | 44063.54
10049 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | C041010 | Pave Northbank Rd and Schooner Creek Rd in Lincoln County to improve safety and extend pavement life. | Pavement Improvement | 2009-08-24 | 2009-09-11 | 2009-10-15 | 2009-10-21 | 933391.46
10050 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | C043021 | Pave Stayton-Scio Rd and Oakville Rd in Linn County to improve safety and extend pavement life. | Other | 2009-05-07 | 2009-05-07 |  | 2009-08-27 | 42692.83
10051 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | C043022 | Pave Stayton-Scio Rd and Oakville Rd in Linn County to improve safety and extend pavement life. | Pavement Improvement | 2009-09-17 | 2009-09-21 | 2009-11-07 | 2009-11-24 | 1354437.17
10052 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | MALHEUR |  | 02 | C045025 | Pave Foothill Dr, Halliday St and Railroad Ave in Malheur County to improve safety and extend pavement life. | Pavement Improvement | 2010-02-05 | 2010-05-04 | 2010-09-30 | 2010-06-03 | 676056.07
10053 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | MALHEUR |  | 02 | C045026 | Pave Foothill Dr, Halliday St and Railroad Ave in Malheur County to improve safety and extend pavement life. | Other | 2009-01-14 | 2009-01-14 |  | 2009-07-31 | 12689.19
10054 | Underway | C200,C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047041 | Pave several county roads in Marion County and Young St in Woodburn to improve safety and extend pavement life. | Pavement Improvement | 2009-08-28 | 2010-06-15 | 2010-06-30 |  | 1636132.72
10055 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047042 | Pave sections of Auburn Rd, Hazelgreen Rd, State St, Turner Rd, Center St, Ward Dr and Brown Rd in Marion County (Salem and Keizer) to improve safety and extend pavement life. | Other | 2009-06-05 | 2009-06-05 |  | 2009-07-23 | 2253.58
10056 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047043 | Pave sections of Auburn Rd, Hazelgreen Rd, State St, Turner Rd, Center St, Ward Dr and Brown Rd in Marion County (Salem and Keizer) to improve safety and extend pavement life. | Pavement Improvement | 2009-08-28 | 2009-10-26 | 2010-06-30 | 2010-08-17 | 1513140.52
10057 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | C047044 | Pave several county roads in Marion County and Young St in Woodburn to improve safety and extend pavement life. | Other | 2009-06-19 | 2009-06-19 |  |  | 9999.57
10058 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047047 | Upgrade signals at Lancaster Dr and Durbin to improve safety and traffic flow. | Other | 2009-07-27 | 2009-07-27 |  | 2010-02-11 | 47458.89
10059 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047048 | Upgrade signals at Lancaster Dr and Durbin to improve safety and traffic flow. | Safety/Traffic Management | 2010-03-23 | 2010-09-10 | 2010-09-30 | 2011-05-27 | 367813.43
10060 | Completed | C950 | Ferryboat | OREGON | MARION |  | 05 | C047049 | Improve access by replacing Buena Vista Ferry Boat and make improvements to ferry terminal. | Other | 2010-06-30 | 2010-06-30 |  | 2010-07-22 | 532840.41
10061 | Completed | C950 | Ferryboat | OREGON | MARION |  | 05 | C047050 | REPLACE FERRY BOAT AND IMPROVEMENTS TO FERRY TERMINI | Other | 2010-08-17 | 2010-09-17 | 2011-02-18 | 2011-06-22 | 1544528.01
10062 | Completed | C240,C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047051 | Pave Cordon Rd, Garfield St, Harrison St and Cleaveland in Salem to improve safety and extend pavement life. | Pavement Improvement | 2010-03-31 | 2010-06-07 | 2010-09-15 | 2010-08-09 | 353315.25
10063 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | C047052 | Pave Cordon Rd, Garfield St, Harrison St and Cleaveland in Salem to improve safety and extend pavement life. | Other | 2010-01-13 | 2010-01-13 |  | 2010-03-04 | 2203.46
10064 | Completed | C950 | Ferryboat | OREGON | MARION |  | 05 | C047055 | REPLACE FERRY BOAT AND IMPROVEMENTS TO FERRY TERMINI | Other | 2010-10-11 | 2010-10-11 |  | 2010-07-22 | 1146079.99
10065 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | MORROW |  | 02 | C049013 | Pave Upper Rhea Creek Rd from mile point 2.2 to mile point 4.5 in Morrow County to improve safety and extend pavement life. | Pavement Improvement | 2009-10-07 | 2009-10-22 | 2010-06-30 | 2009-10-30 | 461078.28
10066 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH |  | 03 | C051070 | Improve safety and mobility at the intersection of 282nd Ave and Stone Rd in Multnomah County by widening 282nd Ave to provide left turn lanes and widening and aligning Stone Rd. | Pavement Improvement | 2008-05-05 | 2008-05-22 | 2008-10-31 | 2010-07-20 | 184655
10067 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 01 | C051079 | Improve pedestrian safety and access by constructing sidwalks on Halsey St and Stark St in Multnomah County. | Transportation Enhancements | 2009-10-06 | 2009-11-02 | 2010-03-31 | 2010-05-13 | 366688.23
10068 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | C051080 | Improve safety on NW Cornelius Pass Rd in Portland by installing signs and signals and repairing guardrail. | Safety/Traffic Management | 2009-10-07 | 2009-12-22 | 2010-03-31 | 2010-03-31 | 208065.62
10069 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | C051081 | Improve pedestrian safety and access by constructing sidwalks on Halsey St and Stark St in Multnomah County. | Other | 2009-06-05 | 2009-06-05 |  |  | 40000.07
10070 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH |  | 03 | C051082 | Improve safety on NW Cornelius Pass Rd in Portland by installing signs and signals and repairing guardrail. | Other | 2009-06-11 | 2009-06-11 |  |  | 11934.38
10071 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 01 | C051083 | Pave city streets and perform sealing and crack repair to concrete pavement in Tigard, Sherwood and Cornelius to improve safety and extend pavement life. | Pavement Improvement | 2010-03-12 | 2010-04-05 | 2010-07-21 | 2010-10-14 | 1605633.5
10072 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | C051085 | Pave various streets in Multnomah County tp improve safety and extend pavement life. | Pavement Improvement | 2010-04-13 | 2010-07-14 | 2010-08-31 | 2010-08-04 | 1210980.78
10073 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | C053033 | Pave Falls City Rd from mile point 0 to mile point 3.8 in Polk County to improve safety and extend pavement life. | Pavement Improvement | 2009-09-17 | 2009-10-07 | 2009-11-15 | 2009-10-29 | 448097.09
10074 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | C053034 | Pave Falls City Rd from mile point 0 to mile point 3.8 in Polk County to improve safety and extend pavement life. | Other | 2009-06-09 | 2009-06-09 |  | 2009-08-27 | 29670.72
10075 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | TILLAMOOK |  | 05 | C057034 | Repave Long Prairie Rd and the Johnson Bridge Rd approaches in Tillamook county to improve safety and extend pavement life. | Pavement Improvement | 2009-08-07 | 2009-09-16 | 2010-05-31 | 2010-05-31 | 626548
10076 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | TILLAMOOK |  | 05 | C057037 | Construct local bridge on Beaver-Blaine Road over Boulder Creek in Tillamook county to improve mobility. | Other | 2010-06-21 | 2010-07-29 | 2011-06-30 | 2011-06-06 | 784474.39
10077 | Completed | C250,C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | C059038 | Pave Despain Gulch Rd between Pendleton-Cold Springs Hwy and mile point 6 in Umatilla County to improve safety and extend pavement life. | Pavement Improvement | 2009-11-24 | 2010-05-03 | 2010-07-31 | 2010-06-08 | 870911.5
10078 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | C059039 | Pave Despain Gulch Rd between Pendleton-Cold Springs Hwy and mile point 6 in Umatilla County to improve safety and extend pavement life. | Other | 2009-07-29 | 2009-07-29 |  | 2009-07-31 | 12820.55
10079 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | WALLOWA |  | 02 | C063018 | Pave Upper Diamond Ln between OR 82 and Lower Diamond Ln in Wallowa County to improve safety and extend pavement life. | Pavement Improvement | 2010-02-26 | 2010-06-14 | 2010-07-30 | 2010-06-18 | 375242.27
10080 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | WALLOWA |  | 02 | C063019 | Pave Upper Diamond Ln between OR 82 and Lower Diamond Ln in Wallowa County to improve safety and extend pavement life. | Other | 2009-09-09 | 2009-09-09 |  | 2010-01-28 | 8388.26
10081 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | WASCO |  | 02 | C065018 | Pave severla county roads in Wasco County to improve safety and extend pavement life. | Pavement Improvement | 2009-11-02 | 2010-08-20 | 2010-06-30 | 2010-08-27 | 377526.52
10082 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | WASCO |  | 02 | C065019 | Pave severla county roads in Wasco County to improve safety and extend pavement life. | Other | 2009-04-23 | 2009-04-23 |  | 2009-08-24 | 11349.99
10083 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | C067063 | Pave several county roads in Washington County to improve safety and extend pavement life. | Other | 2009-05-06 | 2009-05-06 |  |  | 109215.52
10084 | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | C067064 | Improve safety by installing upgraded bridge guardrail on several bridges in Washington County. | Other | 2009-05-06 | 2009-05-06 |  |  | 58756.74
10085 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067065 | Improve school zone safety by installing new solar powered school zone flasher units at several school zones in Washington County. | Other | 2009-05-06 | 2009-05-06 |  | 2009-09-10 | 37013.19
10086 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067066 | Improve safety and traffic flow on several streets in Washington County by installing new signal hardware to include flasshing yellow arrows and replacing illuminated signs. | Other | 2009-06-11 | 2009-06-11 |  | 2009-11-02 | 43733.73
10087 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067067 | Pave several city streets in Washington County to improve safety and extend pavement life. | Other | 2009-05-07 | 2009-05-07 |  |  | 160005.05
10088 | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067068 | Improve mobility and traffic flow at several intersections in Washington County by evaluating signal timing and making changes to the signal timing as necessary. | Safety/Traffic Management | 2009-05-28 | 2009-05-28 | 2011-08-31 |  | 600000
10089 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | C067069 | Pave several county roads in Washington County to improve safety and extend pavement life. | Pavement Improvement | 2010-02-18 | 2010-03-18 | 2010-05-31 | 2010-09-14 | 693354.82
10090 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067070 | Pave several city streets in Washington County to improve safety and extend pavement life. | Pavement Improvement | 2010-02-18 | 2010-03-18 | 2010-06-11 | 2010-10-14 | 1632708.41
10091 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | C067071 | Improve pedestrian and bicycle safety and mobility by constructing Banks-Vernonia Train between South Trailhead and Banks Rd. Improve trailhead parking and provide landscaping. | Transportation Enhancements | 2010-03-23 | 2010-05-17 | 2010-10-15 | 2010-10-22 | 268360.56
10092 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067072 | Improve school zone safety by installing new solar powered school zone flasher units at several school zones in Washington County. | Safety/Traffic Management | 2009-10-07 | 2009-12-15 | 2009-12-31 | 2010-01-05 | 225000
10093 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE | PORTLAND (WA) |  | C067073 | Improve safety and traffic flow on several streets in Washington County by installing new signal hardware to include flasshing yellow arrows and replacing illuminated signs. | Safety/Traffic Management | 2009-12-09 | 2010-02-15 | 2010-06-30 | 2010-08-11 | 593536.65
10094 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067076 | Improve safety by installing emergency vehicle signal pre-emption devices at approximately 86 intersections in Washington County. | Other | 2009-08-28 | 2009-08-28 |  | 2010-01-14 | 19576.36
10095 | Completed | C240,C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067078 | Improve safety and traffic flow by installing traffic video detection equipment at 20 intersections in Washington County and Tigard. | Safety/Traffic Management | 2010-04-13 | 2010-08-16 | 2010-12-31 | 2010-12-14 | 578371.49
10096 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067080 | Improve safety and traffic flow by installing traffic video detection equipment at 20 intersections in Washington County and Tigard. | Other | 2009-09-01 | 2009-09-01 |  | 2010-03-18 | 38765.8
10097 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067081 | Improve pedestrian safety by installing pedestrian countdown timers at approximately 150 intersections in Washington County. | Other | 2009-08-28 | 2009-08-28 |  | 2010-01-14 | 29425.43
10098 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067082 | Improve pedestrian safety by adding pedestrian countdown timers and improve emergency response by adding emergency signal pre-emption to several intersections in Washington County. | Safety/Traffic Management | 2010-02-09 | 2010-08-16 | 2010-12-31 | 2010-12-14 | 568262.76
10099 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | C067083 | Improve safety by installing upgraded bridge guardrail on several bridges in Washington County. | Safety/Traffic Management | 2010-03-25 | 2010-05-28 | 2010-06-30 | 2010-06-25 | 211033.89
10100 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | C067084 | Improve pedestrian and bicycle safety and mobility by constructing Banks-Vernonia Train between South Trailhead and Banks Rd. Improve trailhead parking and provide landscaping. | Transportation Enhancements | 2009-12-01 | 2009-12-01 |  | 2010-02-25 | 120965.76
10101 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067087 | PURCHASE/INSTALL VIDEO DETECTION EQUIPMENT AT 40 EXISTING TRAFFIC SIGNALS | Other | 2010-06-24 | 2010-06-24 |  | 2010-09-09 | 5000
10102 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | C067088 | PURCHASE/INSTALL VIDEO DETECTION EQUIPMENT AT 40 EXISTING TRAFFIC SIGNALS | Safety/Traffic Management | 2010-10-12 | 2011-02-07 | 2011-06-30 | 2011-06-29 | 741565.59
10103 | Completed | C250,C200 | Highway Infrastructure Investment Grant | OREGON | WHEELER |  | 02 | C069001 | Pave Upper Rowe Creek Rd in Wheeler County to improve safety and extend pavement life. | Pavement Improvement | 2010-03-18 | 2010-05-26 | 2010-08-31 | 2010-06-09 | 226554.54
10104 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | WHEELER |  | 02 | C069002 | Pave Upper Rowe Creek Rd in Wheeler County to improve safety and extend pavement life. | Other | 2009-10-14 | 2009-10-14 |  | 2010-02-25 | 16729.23
10105 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | C071014 | Pave Baker Creek Rd between Michelbrook Ln and Power House Hill Rd in Yamhill County to improve safety and extend pavement life. | Pavement Improvement | 2009-07-14 | 2009-08-10 | 2009-10-15 | 2009-09-03 | 698518.45
10106 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | C071015 | Pave various roads in Yamhill County to improve safety and extend pavement life. | Pavement Improvement | 2010-03-02 | 2010-05-17 | 2010-06-30 | 2010-06-18 | 238055.68
10107 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | C071016 | Pave various roads in Yamhill County to improve safety and extend pavement life. | Other | 2010-01-06 | 2010-01-06 |  | 2010-02-04 | 291.87
10108 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 04 | S000312 | Preserves road by extending current project replacing poor pavement on OR 99 and OR 238 in Josephine County. | Other | 2006-10-31 | 2006-10-31 |  | 2010-01-01 | 18193.32 | 4.470
10109 | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 04 | S000393 | Preserves road by extending current project replacing poor pavement on OR 99 and OR 238 in Josephine County. | Pavement Improvement | 2009-02-25 | 2009-03-03 | 2009-10-30 | 2010-11-09 | 2555555.32 | 4.470
10110 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | S000431 | Improves safety of a dangerous rail crossing on US 30 between Pendleton and Athena through reconstruction and paving. | Pavement Improvement | 2009-05-19 | 2009-06-24 | 2010-08-15 | 2010-09-09 | 899516.23 | 16.340
10111 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | S000457 | Improve safety on US 20 between Pioneer Mountain Loop Rd and Yaquina River in Lincoln County by removing narrow, winding roads. | Other | 2009-07-09 | 2009-07-09 |  | 2009-12-17 | 317976.23 | 6.510
10112 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE |  |  | S000481 | Enhance safety by replacing damaged or substandard guardrail on OR 219, OR 34, OR 58, OR 126, and US 101. | Safety/Traffic Management | 2009-07-02 | 2010-02-08 | 2010-04-30 | 2010-05-21 | 989905.62
10113 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | BAKER |  | 02 | S000485 | Improve safety for motorists and pedestrians by paving and adding curb and gutter to Birch Street in Baker City. | Pavement Improvement | 2009-05-22 | 2009-06-08 | 2009-10-31 | 2009-10-28 | 537687.17
10114 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | BAKER |  | 02 | S000489 | Improve safety by replacing the aging Dewey Ave Union Pacific rail-road crossing on OR 7in Baker City. | Pavement Improvement | 2009-05-22 | 2009-06-08 | 2009-11-30 | 2010-11-17 | 1228589.97 | 0.010
10115 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE |  |  | S000493 | Improve mobility and safety at 277 intersections in the Portland Metropolitan reagion by installing 2070 signal controllers and updating signal control software at the intersections. | Other | 2009-04-09 | 2009-04-09 |  |  | 381945.46
10116 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE |  |  | S000497 | Improve mobility and safety at 277 intersections in the Portland Metropolitan reagion by installing 2070 signal controllers and updating signal control software at the intersections. | Other | 2009-07-07 | 2010-01-11 | 2010-07-02 | 2010-08-05 | 2771491.58
10117 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE |  |  | S000499 | Improves safety by replacing or retrofitting restrooms at rest areas in Western Oregon. | Other | 2009-05-05 | 2009-05-05 |  | 2009-08-11 | 4398.52
10118 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE |  |  | S000500 | Improves safety by replacing or retrofitting restrooms at 6 rest areas in Eastern Oregon. Repave one rest area. | Pavement Improvement | 2009-08-04 | 2009-09-10 |  |  | 874870.99
10119 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE |  |  | S000501 | Improves safety by replacing or retrofitting restrooms at rest areas in Western Oregon. | Pavement Improvement | 2009-08-01 | 2009-08-01 |  | 2011-04-15 | 851630.66
10120 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | S000502 | Enhance freight operations by repairing 7 miles of track in along the Albany & Eastern Rail Road rail line. | Other | 2009-05-05 | 2009-05-05 |  | 2009-06-12 | 30000
10121 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | S000503 | Enhance freight operations by repairing unsafe track in Prineville. | Other | 2009-05-06 | 2009-05-06 |  | 2010-07-13 | 19487.55
10122 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | S000504 | Improve safety at 7 rail road crossings and replace track on the Portland & Western Rail Road in Portland. | Other | 2009-05-06 | 2009-05-06 |  | 2009-06-12 | 50000
10123 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | S000505 | Enhance freight operations by repairing unsafe track on the Coos Bay Rail Line in Coos Bay. | Other | 2009-05-03 | 2009-05-03 |  | 2009-06-17 | 20000
10124 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | MORROW |  | 02 | S000506 | Enhance shipping by adding additional rail capacity at the Port of Morrow in Morrow County. | Other | 2009-05-07 | 2009-05-07 |  |  | 30000
10125 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | S000507 | Enhance mobility with improved switching on the North Portland Junction crossovers in Portland. | Other | 2009-05-18 | 2009-05-18 |  | 2009-06-16 | 49907.58
10126 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | BAKER |  | 02 | S000513 | Improve safety for motorists and pedestrians by paving and adding curb and gutter to Birch Street in Baker City. | Other | 2009-04-30 | 2009-04-30 |  | 2009-04-30 | 24337.15
10127 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | S000514 | Enhance freight operations by repairing unsafe track in Prineville. | Safety/Traffic Management | 2009-07-01 | 2009-07-01 |  | 2010-07-13 | 1014775
10128 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | S000515 | Enhance freight operations by repairing 7 miles of track in along the Albany & Eastern Rail Road rail line. | Safety/Traffic Management | 2009-07-01 | 2009-07-01 |  |  | 2951649
10129 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | S000516 | Improve safety at 7 rail road crossings and replace track on the Portland & Western Rail Road in Portland. | Safety/Traffic Management | 2009-06-18 | 2009-06-18 |  | 2010-09-29 | 1427700
10130 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | S000518 | Enhance freight operations by repairing unsafe track on the Coos Bay Rail Line in Coos Bay. | Safety/Traffic Management | 2009-06-18 | 2009-06-18 |  |  | 2480000
10131 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH |  | 03 | S000519 | Enhance mobility with improved switching on the North Portland Junction crossovers in Portland. | Safety/Traffic Management | 2009-06-18 | 2009-06-18 |  | 2010-08-17 | 4264037.72
10132 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | MORROW |  | 02 | S000520 | Enhance shipping by adding additional rail capacity at the Port of Morrow in Morrow County. | Safety/Traffic Management | 2009-06-18 | 2009-06-18 |  |  | 1454400
10133 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE |  |  | S000522 | Improves safety by replacing or retrofitting restrooms at 6 rest areas in Eastern Oregon. Repave one rest area. | Other | 2009-06-19 | 2009-06-19 |  |  | 9726.72
10134 | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CURRY |  | 04 | S000542 | Pave various roads in Curry County and the City of Brookings to improve safety and extend pavement life. | Pavement Improvement | 2010-02-24 | 2010-05-03 | 2010-07-31 | 2010-07-08 | 641936.28
10135 | Underway | C490 | OJT/SS | OREGON | STATEWIDE |  |  | S000544 | Improve Oregon Workforce Development Program by providing on-the-job training and supportive services program to transportation related careers. | Other | 2010-01-15 | 2010-01-15 | 2013-06-30 |  | 880000
10136 | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE | EUGENE |  | S000590 | ILLUM I-5 @ N ALBANY,GLENWOOD,OR569@RIVERRD,I-105 RPR/REPLACE 21 TOWERS,US20REPL 14 LIGHTS | Safety/Traffic Management | 2010-06-11 | 2010-08-16 | 2011-02-28 | 2011-06-07 | 2181890.82
10137 | Underway | C490 | OJT/SS | OREGON | STATEWIDE |  |  | S000603 | RECRUIT,ASSESS & TRAIN TRIBAL MEMBERS FOR HIGHWAY CONSTRUCTION JOBS THRU APPRENTICESHIPS | Other | 2010-07-08 | 2010-07-08 | 2013-06-30 |  | 60010
10138 | Underway | C490 | OJT/SS | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | S000604 | PROVIDES TRAINING PROGRAM FORTARGET GROUP ME MBERS IN PORTLAND METRO AREA | Other | 2010-08-23 | 2010-08-23 | 2013-06-30 |  | 120000
10139 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | S001233 | Improves pedestrian access and safety by extending fairground multi-use path in Roseburg. | Transportation Enhancements | 2008-05-05 | 2008-06-03 | 2008-07-31 | 2009-10-05 | 433118.2
10140 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | S001329 | Improves safety on I5 between Booth Rand and Glendale in Douglas county by replacing poor pavement. | Pavement Improvement | 2009-05-13 | 2009-06-04 | 2009-10-30 | 2010-09-29 | 6624682 | 29.490
10141 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | S001332 | Improve safety by replacing pavement worn down by chains, severe weather on 11 miles of I-5 in Ashland. | Pavement Improvement | 2009-05-01 | 2009-05-11 | 2009-08-31 | 2009-10-29 | 1937085.06 | 11.000
10142 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE |  |  | S001333 | Improve safety by replacing worn striping on I-5 between mile point 18 and 168. | Safety/Traffic Management | 2009-04-23 | 2009-06-03 | 2009-09-15 | 2009-09-24 | 1921586.41 | 150.000
10143 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | S001338 | Reduce truck crash probability on I-5 in Marion County by replacing substandard barriers. | Safety/Traffic Management | 2009-06-23 | 2009-10-15 | 2010-05-27 | 2010-07-09 | 3973445.43 | 12.630
10144 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | S001339 | Pavement overlay of I-5 between Tualitin River Bridge and Willsonville Rd to improve traffic flow for vehicles merging on and off the freeway; added cable barrier to reduce risk of fatal crashes. | Pavement Improvement | 2009-05-21 | 2009-06-08 | 2010-10-31 | 2011-04-15 | 3425781.89 | 6.370
10145 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 05 | S001357 | Improve awareness on the Oregon Solar Highway System by installing an interpretative display at the I-5 Baldock rest area. | Other | 2009-10-27 | 2009-10-27 | 2011-12-31 | 2011-07-22 | 50000
10146 | Completed | C250 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | S001358 | Improve awareness on the Oregon Solar Highway System by installing an interpretative display at the I-5 Baldock rest area. | Pavement Improvement | 2010-04-29 | 2010-07-07 | 2010-09-30 | 2010-10-08 | 6488566.27 | 13.140
10147 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | S001361 | Install welcome sign on I-5 northbound in Jackson County. | Other | 2010-03-22 | 2010-03-22 | 2010-07-30 | 2010-09-30 | 27449.98
10148 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | S001363 | Install welcome sign on I-5 northbound in Jackson County. | Other | 2010-03-22 | 2010-04-20 | 2010-09-30 | 2010-10-29 | 339446.31
10149 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | STATEWIDE |  |  | S002079 | Repair and reconstruct access control fencing along I-84 between Sandy River and The Dalles to reduce weather/animal-related crashes. | Pavement Improvement | 2009-06-02 | 2009-07-19 | 2010-05-12 | 2010-10-13 | 299999.61 | 44.200
10150 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | S002109 | Builds rockfall screen along busy section of I-84 over Cabbage Hill to improve safety. | Safety/Traffic Management | 2009-05-26 | 2009-08-24 | 2009-10-15 | 2009-09-16 | 195421.89 | 8.110
10151 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | S002110 | Enhances mobility by adding a right turn lane to I-84 exit at 257th in Troutdale. | Pavement Widening | 2009-06-26 | 2009-08-10 | 2009-11-24 | 2009-12-03 | 602567.5 | 0.890
10152 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | GILLIAM |  | 02 | S002112 | Improve safety and extend pavement life on I-84 between Rufus and Swanson Canyon by repairing and chip sealing existing pavement. | Pavement Improvement | 2010-04-21 | 2010-06-29 | 2010-10-29 | 2011-09-09 | 191959.3
10153 | Underway | C220,C240 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | S004120 | Enhance safety on US 97 between Lava Butte and S Century Driver by adding lanes and access routes in Deschutes County. Improves safety by restoring fencing and crossing enhancements at the US 97 Lava | Pavement Improvement | 2009-06-11 | 2009-06-22 | 2011-11-30 |  | 11736733.38 | 10.730
10154 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | WASCO |  | 02 | S004125 | Enhances bicycle and pedestrian safety by building sidewalks, curbs, and multi-use paths on US 197 between Burnham Ave and 3rd St in Maupin. | Transportation Enhancements | 2009-01-27 | 2009-02-11 | 2009-06-05 | 2009-09-18 | 754678.96 | 0.320
10155 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | WASCO |  | 02 | S004132 | Improve safety in extreme weather area by extending current pavement project on US 197 between The Dalles and Eight Mile Creek. | Pavement Improvement | 2009-06-16 | 2009-07-31 | 2009-11-25 | 2010-01-05 | 3055790.45 | 5.680
10156 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | KLAMATH |  | 02 | S004133 | Improve safety and mobility by adding a 2 mile passing lane to US 97 at mile point 230 in Klamath County. | Pavement Improvement | 2009-06-04 | 2009-06-22 | 2010-08-31 | 2010-09-03 | 4450893.73 | 5.000
10157 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | S004136 | Improves mobility and safety by installing an adaptive traffic signal control system at 19 intersections in Redmond. | Other | 2009-03-13 | 2009-03-13 |  |  | 80412.1
10158 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | S004137 | Improves mobility and safety by installing an adaptive traffic signal control system at 19 intersections in Redmond. | Safety/Traffic Management | 2009-07-13 | 2009-08-17 | 2010-02-26 | 2010-05-31 | 1407816.22
10159 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | UNION |  | 02 | S006106 | PLACE INFORMATIONAL AND INTERPRETIVE INFORMATION FACILITIES AT UPPER PERRY ARCH BRIDGE | Other | 2010-02-16 | 2010-02-16 |  | 2010-12-02 | 20000
10160 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | UNION |  | 02 | S006107 | PLACE INFORMATIONAL AND INTERPRETIVE INFORMATION FACILITIES AT UPPER PERRY ARCH BRIDGE | Transportation Enhancements | 2011-01-13 | 2011-09-28 | 2011-11-30 | 2011-12-01 | 173319.92
10161 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | S006111 | PAVEMENT PRESERVATION INTERSTATE MAINTENANCE | Safety/Traffic Management | 2011-03-09 | 2011-03-22 | 2011-11-15 | 2011-11-09 | 5125182.24
10162 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | HARNEY |  | 02 | S007051 | Complete pavement preservation project on US 20 between Bulger Creek and Riley Junction in Hines. | Pavement Improvement | 2009-05-20 | 2009-06-11 | 2010-07-31 | 2010-09-15 | 6225776.66 | 23.200
10163 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OREGON | TILLAMOOK |  | 05 | S009317 | Repave US 101 between 12th St and Farmer Creek Rd in Tillamook to improve safety and reduce maintainance costs by preventing water permeation. | Pavement Improvement | 2009-04-29 | 2010-03-30 | 2010-08-31 | 2011-09-15 | 6175378.86 | 16.720
10164 | Completed | C250 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | S009323 | Improves safety along US 101 and OR 38 between Reedsport and Winchester Bay by repaving poor highway and upgrading sidewalks. | Pavement Improvement | 2009-03-23 | 2009-04-20 | 2009-10-09 | 2010-02-25 | 781361.49 | 4.160
10165 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CURRY |  | 04 | S009337 | Paves poor section of US 101 between Bethel Cr and Crystal Cr in Coos County to improve safety. | Pavement Improvement | 2009-05-13 | 2009-08-10 | 2009-09-30 | 2009-11-12 | 1967967.45 | 10.800
10166 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | S009338 | Improve safety on OR 38 and US 101 between Lane County and Gardner in douglas County by replacing poor pavement. | Pavement Improvement | 2009-05-20 | 2009-05-23 | 2009-09-30 | 2010-08-20 | 5387911.7 | 11.100
10167 | Underway | C250,C240 | Highway Infrastructure Investment Grant | OREGON | UNION |  | 02 | S010037 | Improve pedestrian safety and stormwater drainage by sidewalks, curb, gutter and stormwater drainage system on OR82 in Imbler. | Pavement Improvement | 2010-04-14 | 2010-05-17 | 2011-03-15 |  | 485000
10168 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | S021014 | PAVEMENT PRESERVATION | Pavement Improvement | 2011-01-11 | 2011-04-12 | 2011-08-31 | 2011-09-17 | 3846213.53
10169 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | S022031 | Improves safety and extends pavement life on OR 62 and OR 140 between Medford and White city by replacing worn out pavement. | Pavement Improvement | 2009-06-08 | 2009-07-07 | 2010-05-19 | 2011-10-20 | 9011292.59 | 6.470
10170 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 03 | S026066 | Improve safety and extend pavement life with paving on US 26 between the Salmon River Bridge and E Lolo Pass Road. | Safety/Traffic Management | 2008-06-23 | 2008-07-21 | 2009-08-28 | 2009-08-23 | 93059.32 | 5.230
10171 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | S030017 | Enhances safety by paving roadway and repairing guardrail on OR 22 between OR 18 and OR 99W in Polk County. | Pavement Improvement | 2009-06-03 | 2009-06-04 | 2009-10-31 | 2010-03-18 | 4192136.74 | 16.400
10172 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | S030018 | Repaves bridge deck on OR 22 over Willamette River and paves older sections of OR 22 to increase safety in Polk County. | Pavement Improvement | 2009-05-29 | 2009-08-20 | 2009-10-31 | 2010-07-14 | 6168639.48 | 5.380
10173 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | S033021 | Improve safety on US 20 between Pioneer Mountain and Eddyville in Lincoln County by improving alignment, widening shoulders and adding channelization at appropriate locaitons. | Pavement Widening | 2005-07-05 | 2005-07-05 | 2009-10-31 |  | 6544764.61 | 11.540
10174 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | S033031 | Install median landscaping on new section of US 20 / OR 34 between Newton Creek and Jade Place in Philomath. | Other | 2009-06-05 | 2009-06-05 |  | 2009-11-12 | 41939.64 | 1.440
10175 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | S033032 | Improve safety on US 20 between Pioneer Mountain Loop Rd and Yaquina River in Lincoln County by removing narrow, winding roads. | Other | 2010-02-08 | 2010-02-23 | 2011-07-31 | 2011-09-13 | 2075000 | 6.510
10176 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | S033033 | Improve safety on US 20 between Pioneer Mountain Loop Rd and Yaquina River in Lincoln County by removing narrow, winding roads. | Other | 2009-06-16 | 2009-06-16 |  |  | 287000 | 6.510
10177 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | BENTON | CORVALLIS | 04 | S033034 | Install median landscaping on new section of US 20 / OR 34 between Newton Creek and Jade Place in Philomath. | Transportation Enhancements | 2009-12-11 | 2010-02-09 | 2010-03-31 | 2010-03-31 | 220850.46 | 1.440
10178 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | S045037 | Improve safety by paving OR 38 between Rock Cr and I-5 and OR 138 between Elkton and mile point 8 in Douglas County. | Pavement Improvement | 2009-06-01 | 2009-06-12 | 2009-09-30 | 2009-08-25 | 4018187.67 | 17.470
10179 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | S047074 | Replaces pavement on the Sunset Highway (US 26) between North Plains and Cornell Road to fix severe rutting and reduce hydroplaning and installs cable barrier to improve safety. | Pavement Improvement | 2009-03-16 | 2009-04-17 | 2009-10-31 | 2010-06-30 | 1171732.52 | 8.610
10180 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MORROW |  | 02 | S052018 | Improves roadway and pedestrian safety on OR 74 between Willow Creek Bridge and Morrow County fairgrounds in Heppner by repairing the bridge, adding bicycle and pedestrian facilities and repaving the | Safety/Traffic Management | 2009-02-27 | 2009-03-11 | 2009-10-31 | 2009-11-17 | 750000 | 1.020
10181 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH |  | 01 | S061009 | Replace existing concrete roadway on I-405 between the Freewont and Marquam bridges to reduces wear and tear on the roadway. Adds new lights and signs to improve safety on the same section of road. | Pavement Improvement | 2009-05-18 | 2009-06-02 | 2009-12-30 |  | 3696873.14 | 3.080
10182 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | S063030 | Repair the 70-year-old culvert at the Bear Gulch Slide Drainage Tunnel in Jackson County to preserve road. | Other | 2009-07-21 | 2009-08-13 | 2009-10-15 | 2009-11-24 | 546191.44
10183 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH |  | 03 | S081014 | Pave detour streets to improve safety and reduce wear and tear while work is performed to replace the Martin Luther King Viaduct in Portland. | Pavement Improvement | 2007-01-12 | 2007-02-27 | 2010-10-31 | 2011-09-20 | 1110000
10184 | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | S091037 | Improve bicycle safety and mobility by preserving bike paths on OR 99W between Rickreall and Monmouth. | Other | 2009-11-23 | 2009-11-23 |  | 2010-01-11 | 62236.16
10185 | Completed | C220,C240 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | S091039 | Improve bicycle safety and mobility by preserving bike paths on OR 99W between Rickreall and Monmouth. | Transportation Enhancements | 2010-05-12 | 2010-08-03 | 2010-09-30 | 2010-09-29 | 465083.58
10186 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 05 | S092017 | Updates signage along US 30 in Portland to improve visibility and safety as part of the Yeon Street preservation project. | Other | 2008-12-09 | 2008-12-09 |  | 2009-06-01 | 2295.08 | 1.950
10187 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH |  | 01 | S092028 | Updates signage along US 30 in Portland to improve visibility and safety as part of the Yeon Street preservation project. | Pavement Improvement | 2008-12-09 | 2009-02-03 | 2009-09-30 | 2009-09-30 | 160000 | 1.950
10188 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | S092029 | Enhance mobility and safety on US 30 in Scappoose with a new RR crossing, improved signalization and street widening. | Pavement Improvement | 2009-07-23 | 2009-12-07 | 2010-06-15 | 2011-05-10 | 1215789.35 | 0.010
10189 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | S092030 | Enhance mobility and safety on US 30 in Scappoose with a new RR crossing, improved signalization and street widening. | Safety/Traffic Management | 2009-06-23 | 2009-06-23 | 2009-06-23 | 2009-06-23 | 1938141 | 0.010
10190 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | S092031 | Enhance mobility and safety on US 30 in Scappoose with a new RR crossing, improved signalization and street widening. | Other | 2009-06-23 | 2009-06-23 |  | 2009-06-23 | 129752.92 | 0.010
10191 | Completed | C250,C240 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | S138002 | Pavement preservation project to extend the life of existing pavement on OR 138 between mile point 4 and 18 and US 199 between mile point 20 and 41 in Douglas and Josephine Counties. | Pavement Improvement | 2009-04-17 | 2009-06-29 | 2009-09-30 | 2010-09-29 | 3961225.59 | 25.000
10192 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 05 | S160040 | Preserves roadway with new pavement and adds signing, signal loops and lighting on OR 213 between I-205 and Redland Rd in Clackamas County. | Pavement Improvement | 2008-07-21 | 2008-08-20 | 2009-09-30 | 2009-11-05 | 1669912.18 | 3.930
10193 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | S162040 | Enhance safety by installing cable and concrete barriers on OR 22 between Lancaster Dr and Golf Club Rd in Marion County. | Safety/Traffic Management | 2009-07-08 | 2009-07-22 | 2009-12-31 | 2009-12-30 | 1753105.09 | 9.620
10194 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | S210014 | PAVEMENT PRESERVATION | Other | 2010-12-02 | 2010-12-02 |  | 2010-12-02 | 25000
10195 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | S210015 | PAVEMENT PRESERVATION | Other | 2010-09-14 | 2010-09-14 |  | 2010-12-02 | 15000
10196 | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | S229010 | Complete pavement preservation project on OR 36 between OR 200 and OR 99W. | Pavement Improvement | 2009-06-16 | 2009-07-30 | 2009-10-15 | 2009-10-15 | 935545.91 | 4.180
10197 | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | MALHEUR |  | 02 | S455016 | Complete pavement preservation projecton OR 201 between Weiser interchange and the Snake River (Payette Bridge). | Pavement Improvement | 2009-06-04 |  |  |  | 6277836.39 | 8.050
10198 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CRAWFORD |  | 03 | Z011211 | This is a Safety and drainage improvement project involving pavement resurfacing, markings, guiderail upgrade on State Route 77 covering seven municipalities in Crawford County. | Pavement Improvement | 2009-05-18 | 2009-06-22 | 2009-12-11 | 2009-09-12 | 2641417.22 | 11.378
10199 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CRAWFORD |  | 03 | Z011212 | This project located in the City of Meadville, Crawford County, updates and retrofits Curb Ramps and pedestrian signals for Pedestrian Safety and in compliance with ADA requirements. | Transportation Enhancements | 2009-04-27 | 2009-05-18 | 2010-01-27 | 2009-10-29 | 830943.03 | 4.090
10200 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CRAWFORD |  | Multiple | Z011213 | This project replaces the bridges and reconstructs the roadway approaches on State Routes 1020 and 3025 in Venango and Crawford Counties of District 1. | Bridge Improvement | 2009-06-25 | 2009-07-30 | 2010-08-18 | 2010-05-20 | 829203.03 | 0.017
10201 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CRAWFORD |  | 03 | Z011214 | This is a Safety and roadway preservation project of about 5 miles of Interstate 79 in Crawford and Mercer Counties. The project involves concrete patching, milling and resurfacing of the roadway as w | Pavement Improvement | 2009-08-03 | 2009-08-27 | 2010-09-22 | 2010-06-24 | 4252282 | 10.380
10202 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CRAWFORD |  | Multiple | Z011216 | This project in Crawford County is East Branch Trail Ph 1. It is multi-use trail North of the Borough of Spartansburg to the Borough of Centerville in Spartansburg & Centerville Boroughs, Sparta & R | Transportation Enhancements | 2010-01-27 | 2010-03-29 | 2010-11-04 | 2010-08-06 | 1087307
10203 | Completed | C250,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CRAWFORD |  | 03 | Z011217 | In Blooming Valley borough of Crawford County, this project will improve safety and drainage as well as extend the life of about 2 miles of Blooming Valley road by milling and resurfacing of the deter | Pavement Improvement | 2009-10-07 | 2010-04-02 | 2010-09-16 | 2010-06-18 | 995812.59 | 1.636
10204 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CRAWFORD |  | 03 | Z011226 | This project is to resurface the deteriorating pavement with new asphalt pavement to improve the ride smoothness for 3.48 miles and add ADA ramps on State Route 77 from Spartansburg to the Erie Count | Pavement Improvement | 2010-09-07 | 2010-09-13 | 2011-10-13 | 2011-07-15 | 1980000 | 3.482
10205 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE |  | 03 | Z012356 | This is a Safety project to install durable Railroad Crossing markings on various state routes in District 1, and this covers the Counties of Crawford, Erie, Forest, Mercer, Venango and Warren. | Safety/Traffic Management | 2009-04-27 | 2009-05-04 | 2009-12-25 | 2009-09-26 | 377037.44 | 0.000
10206 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE |  | 03 | Z012357 | This project will extend the life of the bridges over Elk Creek and improve roadway approaches on State Route 98 in Fairview Township of Erie County. | Bridge Improvement | 2009-05-04 | 2009-05-04 | 2009-10-15 | 2009-07-17 | 620221.97 | 0.043
10207 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE |  | 03 | Z012358 | This milling and resurfacing project will extend the life of the existing roadway, State Route 20 in Springfield, Millcreek and Girard Townships of Erie County; and upgrade Curb ramps to comply with A | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2010-01-17 | 2009-10-19 | 3892213.33 | 20.049
10208 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE |  | 03 | Z012359 | The project extends the life of the pavement on State Route 8 in Venango and Millcreek Townships of the City of Erie, Erie County. It involves pavement resurfacing and markings, guiderail improvements | Pavement Improvement | 2009-06-16 | 2009-06-23 | 2009-11-05 | 2009-08-07 | 1240090.49 | 4.623
10209 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE | ERIE | 03 | Z012360 | This project replaces the bridges over Six Mile Creek and Seven Mile Creek on State Route 955 in Harborcreek Township of Erie County. The project will also include drainage and guiderail upgrades as w | Bridge Replacement | 2009-07-06 | 2009-07-06 | 2011-07-26 | 2011-04-27 | 1976099 | 0.520
10210 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE |  | 03 | Z012361 | This project in the City of Erie, Erie County, improves Pedestrian Safety through the construction of sidewalks, installation of curb ramps, lightings, and signals improvements on City Street and Para | Transportation Enhancements | 2009-08-25 | 2009-08-25 | 2011-09-28 | 2011-06-30 | 727031 | 0.000
10211 | Completed | C220,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE | ERIE | 03 | Z012363 | This project, located in the City of Erie, Erie County, will update and retrofit Curb Ramps and pedestrian signals for Pedestrian Safety and in compliance with ADA requirements. | Transportation Enhancements | 2009-06-01 | 2009-06-01 | 2011-08-24 | 2011-05-26 | 1569999.99 | 33.017
10212 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE |  | 03 | Z012364 | This project will preserve the pavement and prevent skidding on 10 miles of Interstate 79 covering Franklin, McKean and Summit Townships in Erie County. It will involve the use of friction-resistant p | Pavement Improvement | 2009-07-22 | 2009-08-17 | 2011-07-27 | 2011-04-28 | 5549437 | 21.111
10213 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE | ERIE | 03 | Z012371 | This Erie County project extends the life of the pavement and improves Safety and drainage on 1.5 miles of State Route 290 (the Bayfront Connector); and this involves pavement resurfacing, guiderail a | Pavement Improvement | 2009-10-14 | 2010-05-17 | 2010-09-15 | 2010-06-17 | 471008.61 | 0.768
10214 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE | ERIE | 03 | Z012372 | This project will preserve the pavement and improve drainage on PA 5 (Lake road) in Harborcreek and Lawrence Townships of Erie County. It involves pavement resurfacing and other miscellaneous work. | Pavement Improvement | 2009-10-08 | 2010-04-12 | 2010-08-15 | 2010-05-17 | 840934.07 | 3.051
10215 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE | ERIE | 03 | Z012373 | This project in the City of Erie, Erie County, improves Pedestrian Safety through the construction of sidewalks, installation of curb ramps, lightings, and landscaping on State Street between Bayfront | Transportation Enhancements | 2009-10-23 | 2009-10-23 | 2012-03-21 | 2011-12-22 | 900000 | 0.000
10216 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE |  | 03 | Z012386 | This project on SR 2010 over Pine Run is in Erie County. It will improve safety by replacing the existing deteriorating bridge carrying Concord Road (SR 2010) over Pine Run in Union Township. | Bridge Replacement | 2010-01-27 | 2010-07-12 | 2011-08-03 | 2011-05-05 | 806632 | 0.365
10217 | Completed | C220,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ERIE | ERIE | 03 | Z012397 | This project is to repave the deteriorating pavement and to construct ADA ramps on State Route 20 (26th Street) for 3.57 miles from Peach Street to Buffalo Road in the City of Erie in Erie Countly. | Transportation Enhancements | 2010-09-07 | 2010-09-27 | 2011-11-23 | 2011-08-25 | 500000 | 3.571
10218 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FOREST |  | 05 | Z013119 | This project will restore State route 66 in Jenks Township of Forest County; and it involves pavement resurfacing and guiderail safety upgrades. | Pavement Improvement | 2009-06-08 | 2009-07-13 | 2009-11-12 | 2009-08-14 | 917920.42 | 4.292
10219 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER | YOUNGSTOWN | 03 | Z014231 | This project will extend the life of the pavement and improve pedestrian Safety on State Routes 18, 2005 and 4019 in Greenville Borough, Pine Hempfield, Sugar Grove and Salem Townships of Mercer Coun | Pavement Improvement | 2009-06-24 | 2009-06-29 | 2010-09-06 | 2010-06-08 | 1556537.65 | 4.116
10220 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER |  | 03 | Z014232 | This project will restore and preserve various State Routes including 62, 19, 58, 1028 located in various Townships and Boroughs in Mercer County; it involves milling and overlays as well as guiderail | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2009-12-03 | 2009-09-04 | 2144664.79 | 13.347
10221 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER | YOUNGSTOWN | Multiple | Z014233 | This project on State Route 3011 (Keel Ridge Road) in Shenango Township and City of Hermitage of Mercer County, will preserve the pavement and improve Safety; it involves pavement repairs and overlays | Pavement Improvement | 2009-06-24 | 2009-07-06 | 2010-04-15 | 2010-01-15 | 821484.28 | 6.547
10222 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER | YOUNGSTOWN | Multiple | Z014235 | This project will extend the life of pavement on 17 miles of Interstate 80 in Shenango, Lackawannock and East Lackawannock Townships of Mercer County; it involves pavement patching and overlay, guide | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-08-24 | 2010-05-26 | 1785378.76 | 31.068
10223 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER |  | 03 | Z014240 | This project will restore the deteriorating portion of US Route 62 in CoolSpring and Jackson Townships and Jackson Center Borough of Mercer County; it involves pavement and bridge repairs, overlay, | Pavement Improvement | 2009-07-20 | 2009-08-17 | 2010-08-10 | 2010-05-12 | 1830329 | 5.141
10224 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER |  | 03 | Z014243 | This project in Mercer County will improve safety for the public by replacing the deteriorating bridge carrying Baker Hill Road (SR 4024) over Lenango Creek in Delaware Township. | Bridge Replacement | 2010-01-19 | 2010-03-01 | 2010-10-12 | 2010-07-14 | 779049.38 | 0.000
10225 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER | YOUNGSTOWN | 03 | Z014247 | This project on State Route 3020 (Lamar Road) in the City of Hermitage of Mercer County, will improve safety and mobility through roadway widening, guiderail and drainage upgrades. | Pavement Widening | 2009-12-04 | 2010-04-19 | 2010-09-29 | 2010-07-01 | 713527.52 | 0.549
10226 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER |  | 03 | Z014248 | This project will extend the life of the pavement and improve drainage on approximately 1.15 miles of State Route 322 (28th Division Highway) in French Creek Township of Mercer County; it involves pav | Pavement Improvement | 2009-09-21 | 2010-04-19 | 2010-08-04 | 2010-05-06 | 346785.04 | 1.147
10227 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER |  | 03 | Z014261 | This project is to improve the pavement smoothness by milling and replacing the deteriorating pavement with 2" of new asphalt for 11.8 miles on State Route 58 from Main Street to Main Street Extensio | Pavement Improvement | 2010-09-08 | 2010-09-08 | 2012-02-19 | 2011-11-21 | 2445000 | 11.717
10228 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MERCER | YOUNGSTOWN | Multiple | Z014263 | This project is to improve the smoothness by milling the deteriorating asphalt roadway and resurfacing with asphalt paving for 0.7 miles on Stambaugh Avenue from East Connelly Boulevard to Division S | Pavement Improvement | 2010-09-08 | 2010-09-08 | 2011-08-24 | 2011-05-26 | 355000
10229 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | VENANGO |  | 05 | Z015189 | This project will extend the life of the pavement on US Route 62 in the City of Franklin, French Creek and Sandy Creek Townships of Venango County; it also involves improvements to drainage and guide | Pavement Improvement | 2009-05-11 | 2009-07-25 | 2009-11-10 | 2009-08-12 | 1330276.28 | 6.740
10230 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | VENANGO |  | 05 | Z015190 | This project will replace two bridges over Prathers Run and Little Sugar Creek on State Route 428 in Oakland Township of Venango County; it also includes improvements to the approach roadways and drai | Bridge Replacement | 2009-06-24 | 2009-07-06 | 2011-04-21 | 2011-01-21 | 1634719.98 | 0.021
10231 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | VENANGO |  | 05 | Z015193 | This project will stabilize and preserve pavement on State Route 8 Bypass in the City of Oil City of Venango County; it involves construction of a retaining wall; it also involves guiderail and draina | Other | 2009-08-11 | 2009-10-12 | 2011-08-16 | 2011-05-18 | 2705312 | 0.782
10232 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WARREN |  | 05 | Z016177 | This project will preserve about 2.5 miles of pavement on State Route 3005 covering various Townships in Warren County; it involves pavement repairs and overlay as well as improvements to guiderail an | Pavement Improvement | 2009-05-04 | 2009-06-11 | 2009-10-13 | 2009-07-15 | 599631.19 | 2.451
10233 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WARREN |  | 05 | Z016178 | This project will replace the bridge over Six Mile Creek on State Route 6 (Grand Army Highway) in Mead Township of Warren County. | Pavement Improvement | 2009-08-25 | 2009-08-25 | 2011-12-27 | 2011-09-28 | 1592996 | 0.008
10234 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WARREN |  | 05 | Z016185 | This project is on US-6 in Warren County will repair the mechanically stabilized earth retaing wall on the Warren Bypass (US 6) left side in Mead Township. | Pavement Improvement | 2010-01-27 | 2010-04-06 | 2010-09-12 | 2010-06-14 | 526823.14 | 0.306
10235 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CENTRE |  | 05 | Z021241 | This project will improve safety and mobility on State Route 26, in Pleasant Gap of Center County. This is an alternate emergency Route to terstate 80. The work involves widening, resurfacing, guider | Pavement Improvement | 2009-04-08 | 2009-06-17 | 2009-11-19 | 2009-08-21 | 3365202.47 | 6.372
10236 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CENTRE |  | 05 | Z021253 | This project will replace the existing bridge over Marsh Creek on State Route 1001 in Curtin Township of Center County; it also involves drainage and guiderail upgrades. | Bridge Replacement | 2009-04-27 | 2009-05-18 | 2010-02-04 | 2009-11-06 | 1051267.99 | 0.778
10237 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CENTRE | STATE COLLEGE | 05 | Z021254 | This project will extend the life of bridges on State Route 322 including bridges in College and Harris Townships of Center County. The bridges will be painted for protection from rusts and other dete | Bridge Improvement | 2009-06-01 | 2009-07-06 | 2010-01-18 | 2009-10-20 | 869587.08 | 0.585
10238 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CENTRE |  | 05 | Z021255 | This project will replace the bridge over the Tributary to Penns Creek on State Route 2014 in Gregg Township of Center County; it also involves guiderail and drainage upgrades. | Bridge Replacement | 2009-05-18 | 2009-06-15 | 2009-11-24 | 2009-08-26 | 466403.41 | 0.496
10239 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CENTRE |  | 05 | Z021259 | This project extends the life of 5.59 miles of pavement on State Route 3040 (Old SR 220) covering Taylor and Worth Townships in Center County; it also involves roadway resurfacing, guiderail and drain | Pavement Improvement | 2009-09-08 | 2010-04-05 | 2011-01-05 | 2010-10-07 | 1992296.63 | 5.611
10240 | Completed | C220,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CENTRE | STATE COLLEGE | 05 | Z021270 | This project consists of Streetscape Enhancements for 1.8 miles on Boals Avenue (State Highway 45) in the Village of Boalsburg in Centre County. | Transportation Enhancements | 2010-08-23 | 2010-09-08 | 2011-10-13 | 2011-07-15 | 183000 | 1.789
10241 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLEARFIELD |  | 05 | Z022246 | This project will improve the existing roadway, on State Route 219 in Brady, Union and Bloom Townships of Clearfield County, for longevity and Safety; it involves resurfacing, bridge deck repairs, min | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2010-03-08 | 2009-12-08 | 2797706.16 | 3.077
10242 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLEARFIELD |  | 05 | Z022249 | This project is for roadway preservation and Safety on State Route 970 in Bradford and Goshen Townships of Clearfield County; it involves pavement widening and resurfacing, guiderail and drainage upgr | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-09-09 | 2010-06-11 | 3615370 | 5.122
10243 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLEARFIELD |  | 05 | Z022252 | This project will preserve six bridges at various locations in various municipalities grouped together as GROUP-2-09-R04 in Cameron, Clearfield, McKean and Potter Counties; it involves bridge deck rep | Bridge Improvement | 2009-07-27 | 2009-08-03 | 2011-10-04 | 2011-07-06 | 4087029 | 2.649
10244 | Completed | C250,C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLEARFIELD |  | Multiple | Z022253 | This project will preserve seven bridges at various locations in various municipalities grouped together as GROUP-2-09-R05 in Clearfield and Potter Counties; it involves bridge deck repairs, steel pai | Bridge Improvement | 2009-07-31 | 2009-09-01 | 2011-02-03 | 2010-11-05 | 2414522 | 1.423
10245 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLINTON |  | 05 | Z023177 | The project will construct a new asphalt riding surface on Lock Haven Bypass from Salona to Avis in Pine Creek, Wayne, Castenea, Bald Eagle and Lamar Townships | Pavement Improvement | 2009-06-15 | 2009-06-22 | 2011-11-08 | 2011-08-10 | 7386999.98 | 28.174
10246 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLINTON |  | 05 | Z023178 | This project is for the preservation of 24 miles of roadway and associated bridges on Interstate 80 in Greene, Lamar and Porter Townships of Clinton and Union Counties; it involves concrete and bridge | Pavement Improvement | 2009-09-10 | 2009-09-28 | 2011-08-31 | 2011-06-02 | 14604501 | 95.906
10247 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CAMERON |  | 05 | Z024116 | This project will improve safety to the traveling public by replacing the deteriorating bridge on SR 0555 (Low Grade Road), over Hicks Run, north of Run road in Gibson Township in Cameron County. | Bridge Replacement | 2010-01-27 | 2010-02-03 | 2011-02-03 | 2010-11-05 | 1245626.77 | 0.170
10248 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MCKEAN |  | 05 | Z025185 | This project will extend pavement life and improve Safety on US Route 219 in Bradford Township of Mckean County; it involves roadway repairs and resurfacing, drainage and guiderail upgrades. | Pavement Improvement | 2009-07-23 | 2009-09-11 | 2011-02-22 | 2010-11-24 | 3114663 | 3.503
10249 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MCKEAN |  | 05 | Z025187 | This project will replace the bridge over Janders Run on State 44 in Ceres Township of McKean County; it also involves guiderail and drainage upgrades. | Bridge Replacement | 2009-11-06 | 2010-03-22 | 2010-10-17 | 2010-07-19 | 809085.34 | 0.005
10250 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | POTTER |  | 05 | Z026154 | This project will restore the deteriorating portion of US Route 6 in Coudersport Borough and Eulalia Township in Potter County; it involves pavement, sidewalk and bridge repairs, overlay, guiderail | Pavement Improvement | 2009-04-13 | 2009-04-14 | 2010-01-25 | 2009-10-27 | 2361611.4 | 1.688
10251 | Completed | C250,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | POTTER |  | 05 | Z026161 | This project will increase the life of the pavement and make the road smoother by restoring the deteriorating asphalt pavement on SR 0006 (Second Street), east of SR 0144 (Main Street) in Coudersport | Pavement Improvement | 2010-01-25 | 2010-03-29 | 2011-02-10 | 2010-11-12 | 2154460 | 2.049
10252 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MIFFLIN |  | 05 | Z027151 | This project will preserve 1.5 miles of pavement on State Route 1005 (Electric Avenue) in Derry Township and Burnham Borough of Mifflin County; it involves milling and resurfacing of roadway, guiderai | Pavement Improvement | 2009-11-30 | 2010-03-29 | 2011-01-11 | 2010-10-13 | 1275512 | 1.274
10253 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ELK |  | 05 | Z028158 | This project will extend the life of 5 miles of pavement on State Route 219 in Johnsonburg Borough, Ridgeway and Jones Townships in Elk County; it involves pavement repairs and resurfacing as well as | Bridge Replacement | 2009-09-14 | 2009-10-08 | 2011-03-06 | 2010-12-06 | 975000 | 5.166
10254 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ELK |  | 05 | Z028160 | This project will improve the pavement smoothness and safety by concrete patching, micro-surfacing, curbing, drainage and guiderail improvements on 4.2 miles of State Route 120 in the City of Saint M | Pavement Improvement | 2010-09-07 | 2010-09-27 | 2012-02-19 | 2011-11-21 | 2926656 | 0.980
10255 | Completed | C250,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | JUNIATA |  | 09 | Z029135 | This project will extend the life of bridge over Juniata River on State Route 75 in the Borough of Port Royal and Walker Township in Juniata County; it involves deck and steel repairs, bridge paintin | Bridge Improvement | 2009-06-22 | 2009-06-22 | 2010-11-25 | 2010-08-27 | 5010000 | 0.246
10256 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | COLUMBIA |  | 11 | Z031209 | The project will replace deteriorated, outdated, and substandard major guide signs and install additional major guide signs on various highways in Lycoming County to improve visibility and legibility | Safety/Traffic Management | 2009-06-10 | 2009-07-23 | 2010-06-02 | 2010-03-04 | 186937.68 | 538.206
10257 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | COLUMBIA |  | 11 | Z031211 | This project in Columbia County will increase the life of the bridge and make it safet for the public by rehabilitating the deteriorating State Route 42 bridge over Roaring Creek in Catawissa and Locu | Bridge Improvement | 2009-07-10 | 2009-07-10 | 2011-02-21 | 2010-11-23 | 738343 | 0.189
10258 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | COLUMBIA |  | 11 | Z031212 | This project in Columbia County will increase the life of the bridge and increase safety for the pulic by rehabilitating the deteriorating State Route 2001 bridge over a tributary of Roaring Creek in | Bridge Improvement | 2009-07-10 | 2009-07-10 | 2011-02-21 | 2010-11-23 | 355250 | 0.076
10259 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | COLUMBIA |  | 11 | Z031213 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck of the State Route 42 bridge over State Route 11 at Bloomsburg in Montour Township in Col | Bridge Improvement | 2009-09-04 | 2010-04-12 | 2010-12-02 | 2010-09-03 | 1414490 | 0.074
10260 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING |  | Multiple | Z032285 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 2009-05-18 | 2009-08-03 | 2010-09-16 | 2010-06-18 | 912605.84 | 0.791
10261 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING | WILLIAMSPORT | Multiple | Z032286 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 15 from Beauty's Run to Trout Run in Lewis, Old Lycoming, and Lycoming | Pavement Improvement | 2009-05-18 | 2009-07-27 | 2010-08-12 | 2010-05-14 | 2156734.07 | 7.488
10262 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING |  | 10 | Z032287 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 220 from Lycoming County Line to Muncy Valley in Davidson Township, Sul | Pavement Improvement | 2009-06-01 | 2009-06-29 | 2009-12-13 | 2009-09-14 | 662706.97 | 1.696
10263 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING | WILLIAMSPORT | 05 | Z032288 | This project will overlay the existing deteriorating pavement with new asphalt pavement on State Route 2014 from Montour Street to Fairfield Road in Montoursville Borough in Lycoming County. | Pavement Improvement | 2009-06-01 | 2009-06-29 | 2009-12-09 | 2009-09-10 | 527915.57 | 1.890
10264 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING | WILLIAMSPORT | 05 | Z032290 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the US Route 220 bridge over Pine Run in Woodward Township | Pavement Improvement | 2009-07-06 | 2010-03-29 | 2010-11-17 | 2010-08-19 | 634024 | 0.076
10265 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING |  | 10 | Z032291 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the State Route 2085 bridge over Muncy Creek in Penn Towns | Bridge Improvement | 2009-09-02 | 2010-04-05 | 2010-11-18 | 2010-08-20 | 665000 | 0.095
10266 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING |  | 10 | Z032292 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the State Route 2048 bridge over Little Muncy Creek in Mun | Bridge Improvement | 2009-08-21 | 2010-04-05 | 2011-01-05 | 2010-10-07 | 800000 | 0.024
10267 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING | WILLIAMSPORT | 05 | Z032298 | This project will make the pavement smoother and last longer by removing the upper layers of the deteriorating asphalt pavement and replace it with new asphalt pavement on SR 3028 from Thomas to Main | Pavement Improvement | 2009-10-05 | 2010-04-08 | 2010-12-13 | 2010-09-14 | 489136 | 2.177
10268 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING | WILLIAMSPORT | 05 | Z032300 | This project will make the road smoother by removing several inches of deteriorating pavement and replacing it with asphalt on SR 3028 from Thomas to Main Street in Jersey Shore Borough and Porter Tow | Pavement Improvement | 2009-10-05 | 2010-04-08 | 2010-12-13 | 2010-09-14 | 267733 | 1.099
10269 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LYCOMING |  | Multiple | Z032308 | This project in Lycoming County is to improve safety and riding smoothness by adding a traction enhancing layer (microsurface) to the asphalt roadway on PA 14 from Red Burn Road in McIntyre Township | Pavement Improvement | 2010-02-01 | 2010-04-14 | 2010-10-19 | 2010-07-21 | 860738.86 | 14.081
10270 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONTOUR |  | 10 | Z033128 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on Interstate 80 Eastbound from West of Grey Hill Road to Old US Route 15 in White | Pavement Improvement | 2009-05-28 | 2009-06-25 | 2009-10-21 | 2009-07-23 | 158143.87 | 4.609
10271 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONTOUR |  | 10 | Z033129 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 54 from State Route 44 to State Route 254 in Anthony, Derry, Limesto | Pavement Improvement | 2009-06-22 | 2009-08-17 | 2010-02-23 | 2009-11-25 | 1574940.35 | 4.665
10272 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHUMBERLAND |  | 10 | Z034190 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 54 from State Route 2024 to Natalie in Coal, Mt. Carmel and Ralpho T | Pavement Improvement | 2009-06-19 | 2009-06-25 | 2010-02-16 | 2009-11-18 | 1708193.09 | 4.399
10273 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHUMBERLAND |  | 10 | Z034191 | This project in Northumberland County will make the pavement last longer and ride smoother by resurfacing the deteriorating asphalt roadway on State Route 54 from State Route 2024 to Natalie in Coal, | Pavement Improvement | 2009-06-19 | 2009-06-25 | 2010-02-16 | 2009-11-18 | 888912.92 | 2.102
10274 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHUMBERLAND |  | 10 | Z034192 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 2009-05-13 | 2009-06-01 | 2009-10-20 | 2009-07-22 | 513648.14 | 1.067
10275 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHUMBERLAND |  | 10 | Z034193 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck on the State Route 4009 bridge over Shamokin Creek in Upper Augusta Township in Northumbe | Bridge Improvement | 2009-06-02 | 2009-06-15 | 2010-01-25 | 2009-10-27 | 1025868.01 | 0.158
10276 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHUMBERLAND |  | 10 | Z034194 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the Interstate 180 bridge over State Route 44 in Delaware | Bridge Improvement | 2009-08-07 | 2010-04-05 | 2011-08-24 | 2011-05-26 | 3191614 | 0.124
10277 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHUMBERLAND |  | 10 | Z034197 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on Snydertown Road from Zimmermans Hollow Road to PA 487 in Northumberland County. | Pavement Improvement | 2009-10-26 | 2009-10-26 | 2011-01-27 | 2010-10-29 | 2070789 | 8.287
10278 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SNYDER |  | 10 | Z035131 | This project in Snyder County will make the ride smoother and make the pavement last longer by resurfacing the deteriorating asphalt pavement on State Route 235 from Snyder/Union County Line to Breinn | Pavement Improvement | 2009-06-05 | 2009-06-08 | 2010-02-11 | 2009-11-13 | 957900 | 4.158
10279 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SNYDER |  | 10 | Z035132 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the State Route 35 bridge over Tributary to Middle Creek i | Bridge Improvement | 2009-07-10 | 2009-07-10 | 2011-02-21 | 2010-11-23 | 1280807 | 0.076
10280 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SNYDER |  | 10 | Z035133 | This project will remove the existing deteriorating bridge and replace it with a new bridge on State Route 3009 over Middle Creek in Franklin Township in Snyder County. | Bridge Replacement | 2009-08-19 | 2009-09-14 | 2011-08-24 | 2011-05-26 | 1863357 | 0.104
10281 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SULLIVAN |  | 10 | Z036129 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 220 from Ringdale to Dushore in Cherry and Laporte Townships in Sulliva | Pavement Improvement | 2009-06-01 | 2009-09-01 | 2010-01-28 | 2009-10-30 | 1170207.35 | 4.689
10282 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SULLIVAN |  | 10 | Z036130 | This project in Sullivan County will make the road last longer and the ride smoother by resurfacing the deteriorating asphalt roadway on US Route 220 from Lycoming County Line to Muncy Valley in David | Pavement Improvement | 2009-06-01 | 2009-06-29 | 2009-12-13 | 2009-09-14 | 708624.3 | 2.579
10283 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SULLIVAN |  | 10 | Z036131 | This project will upgrade the old metal guardrail to meet new design standards at various locations in Lycoming County | Safety/Traffic Management | 2009-06-22 | 2009-06-22 | 2011-03-14 | 2010-12-14 | 536465.49 | 36.631
10284 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | TIOGA |  | 05 | Z037222 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 2009-04-02 | 2009-05-27 | 2009-09-10 | 2009-06-12 | 344345.56 | 0.288
10285 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | TIOGA |  | 05 | Z037223 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 287 from Wilson Creek to Shumway Hill Road in Delmar Township, Tioga | Pavement Improvement | 2009-05-15 | 2009-05-25 | 2010-12-22 | 2010-09-23 | 1629006.53 | 4.650
10286 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | TIOGA |  | 05 | Z037224 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on US Route 15 from State Route 287 to Tioga River in Lawrence, Tioga Townships and | Pavement Improvement | 2009-05-15 | 2009-05-18 | 2010-01-05 | 2009-10-07 | 1948999.89 | 4.839
10287 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | TIOGA |  | 05 | Z037225 | This project will remove the existing deteriorating bridge and replace it with a new bridge on State Route 414 bridge over Zimmerman's Creek in Liberty Township, Tioga County. | Bridge Replacement | 2009-06-29 | 2009-06-29 | 2010-08-13 | 2010-05-15 | 1079434.54 | 0.082
10288 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | TIOGA |  | Multiple | Z037226 | This project in Tioga County will make the bridge last longer by repairing deteriorating portions of State Route 2005 bridge over Blockhouse Creek in Liberty Township. This bridge is part of State Pr | Bridge Improvement | 2009-06-29 | 2009-06-29 | 2010-08-13 | 2010-05-15 | 23933.8 | 0.009
10289 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | TIOGA |  | 05 | Z037233 | This project in Tioga County will make the pavement last longer and ride smoother by removing the upper layers of the deteriorating asphalt pavenemt and replace with new asphalt on US 15 southbound fr | Pavement Improvement | 2010-01-29 | 2010-05-03 | 2010-10-25 | 2010-07-27 | 1963194.48 | 7.797
10290 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | UNION |  | 10 | Z038150 | This project in Union County will make the roadway last longer and ride smoother by resurfacing the deteriorating pavement on the eastbound Interstate 80 lanes from West of Grey Hill Road to Old US Ro | Pavement Improvement | 2009-05-28 | 2009-06-25 | 2009-10-21 | 2009-07-23 | 114468.93 | 2.601
10291 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | UNION |  | 10 | Z038151 | This project will make the roadway last longer and ride smoother by resurfacing the deteriorating pavement on Interstate 80 Westbound from old US Route 15 to White Deer Pike in White Deer in Union Co | Pavement Improvement | 2009-05-28 | 2009-06-25 | 2009-10-21 | 2009-07-23 | 114619.5 | 3.431
10292 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | UNION |  | 10 | Z038152 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 235 from Snyder/Union County Line to Breinnger Run in Adams Township | Pavement Improvement | 2009-06-05 | 2009-06-08 | 2010-02-11 | 2009-11-13 | 985980.26 | 5.299
10293 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | UNION |  | 10 | Z038153 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 2009-08-27 | 2010-03-29 | 2010-12-15 | 2010-09-16 | 1452792.44 | 0.050
10294 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BRADFORD |  | 10 | Z039194 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated bridge deck by removing the top layer of concrete and replacing or patching it with latex-modi | Bridge Improvement | 2009-06-25 | 2010-03-29 | 2011-09-02 | 2011-06-04 | 1714714 | 0.258
10295 | Completed | C250,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BRADFORD |  | 10 | Z039195 | This project will preserve the concrete deck by removing the top layer of concrete and replacing or patching it with a latex-modified concrete and add an epoxy overlay on the State Route 187 bridge ov | Bridge Improvement | 2009-07-21 | 2009-08-03 | 2011-01-26 | 2010-10-28 | 1097004.8 | 0.189
10296 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BRADFORD |  | 10 | Z039196 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on the US Route 6 bridge over Sugar Creek in Sylvania Borough | Bridge Improvement | 2009-07-29 | 2010-04-05 | 2011-08-22 | 2011-05-24 | 935000 | 0.196
10297 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BRADFORD |  | 10 | Z039197 | This project in Bradford County will make the bridge safer and last longer by rehabilitating the deteriorating portions of State Route 187 bridge over Bullard Creek in Rome Borough and Township. This | Bridge Improvement | 2009-07-29 | 2010-04-05 | 2011-08-22 | 2011-05-24 | 663000 | 0.076
10298 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BRADFORD |  | 10 | Z039198 | This project in Bradford County will make the bridge safer and last longer by rehabilitating the deteriorating portions of the bridge on State Route 1055 over Parks Creek in Rome Township. This is pro | Bridge Improvement | 2009-07-29 | 2010-04-05 | 2011-08-22 | 2011-05-24 | 430450 | 0.076
10299 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BRADFORD |  | 10 | Z039202 | This project will preserve the deteriorating steel beams by painting the bridges on PA 187 over Susquehanna River in Asylum and Wysox Townships, in Bradford County. | Bridge Improvement | 2009-10-02 | 2010-07-26 | 2010-12-28 | 2010-09-29 | 904000 | 0.189
10300 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LACKAWANNA | SCRANTON--WILKES-BARRE | 11 | Z042405 | This project in Lackawanna County will resurface a heavily travelled local road to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-09-23 | 2009-09-24 | 2011-10-06 | 2011-07-08 | 1083949 | 1.795
10301 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LACKAWANNA | SCRANTON--WILKES-BARRE | Multiple | Z042417 | This project will improve the pavement smoothness by resurfacing 12.5 miles of Business Route 6 from Timber Falls to Wayne County Line in Archbald and Mayfield Boroughs, Carbondale Township, and Carbo | Pavement Improvement | 2010-09-07 | 2010-09-08 | 2011-07-31 |  | 3617322 | 12.500
10302 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LUZERNE | SCRANTON--WILKES-BARRE | 11 | Z043387 | This project in Luzerne County is construction of a new Cleveland Street Bridge over Mill Creek in Plains Township to replace one that had been closed to traffic. | Bridge Replacement | 2009-06-04 | 2009-06-04 | 2010-09-30 | 2010-07-02 | 1528071.83 | 0.000
10303 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LUZERNE | SCRANTON--WILKES-BARRE | 11 | Z043407 | This project in Luzerne County will extend the life of the State Route 29 Bridges over the Susquehanna River and over State Route 2002 by repairing deteriorated steel, replacing the deteriorated decks | Bridge Improvement | 2009-08-03 | 2009-08-10 | 2011-11-10 |  | 19236548 | 0.563
10304 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LUZERNE |  | Multiple | Z043408 | This project in Luzerne County will extend the life of the State Route 4001 bridge over Branch of Hunlock Creek and State Route 4016 bridge over Marsh Creek by repairing deteriorated steel, replacing | Bridge Improvement | 2009-06-03 | 2009-07-13 | 2010-12-22 | 2010-09-23 | 979000 | 1.001
10305 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LUZERNE |  | 11 | Z043411 | This 11.5 mile-long project in Luzerne County will mill and resurface a heavily travelled Interstate Highway to improve ride quality and extend the life of the pavement on both the northbound and sou | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2009-12-24 | 2009-09-25 | 2797620.44 | 10.694
10306 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LUZERNE |  | 11 | Z043412 | This 28 mile-long project will mill and resurface a heavily travelled Interstate Highway to improve ride quality and extend the life of the pavement on both the northbound and southbound lanes includi | Pavement Improvement | 2009-06-30 | 2009-07-22 | 2010-02-05 | 2009-11-07 | 6843231.53 | 43.866
10307 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LUZERNE |  | 11 | Z043415 | This project in Luzerne and Lackawanna Counties will resurface a number heavily travelled highways (SR 924, 11, 3033, 3027, 347, 315) to improve ride quality and extend the life of the pavement. Inclu | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2010-07-04 |  | 6000000 | 16.095
10308 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PIKE |  | 10 | Z044172 | This 5 mile long project in Pike and Wayne Counties will improve safety for bicyclists utilizing US Route 6 by widening the shoulders, placing new bituminous pavement, painting new pavement markings a | Transportation Enhancements | 2009-06-01 | 2009-06-01 | 2010-05-21 |  | 1532505.27 | 13.502
10309 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PIKE |  | 10 | Z044180 | This 2.8 mile-long project in Blooming Grove Township, Pike County, will resurface a heavily travelled highway to improve ride quality and extend the life of the pavement. Included in this project ar | Pavement Improvement | 2009-07-08 | 2009-07-08 | 2009-12-08 | 2009-09-09 | 571506.74 | 3.338
10310 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PIKE |  | 10 | Z044181 | This 28 mile-long project will mill and resurface a heavily travelled Interstate 84 highway in Pike County to improve ride quality and extend the life of the pavement on the eastbound lanes includin | Pavement Improvement | 2009-08-17 | 2009-07-22 | 2010-10-25 | 2010-07-27 | 7535000 | 57.180
10311 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PIKE |  | 10 | Z044184 | This project in Pike County will extend the life of the US Route 6 bridge over the Delaware River by repairing deteriorated steel, replacing the deteriorated deck with a new concrete deck, and repairi | Bridge Improvement | 2009-10-21 | 2009-10-21 | 2012-01-09 | 2011-10-11 | 3302280 | 0.125
10312 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PIKE |  | 10 | Z044185 | This 5 mile-long project in Pike County will resurface a heavily travelled highway to improve ride quality and extend the life of the pavement. Included in this project are edge repairs, resurfacing | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2010-03-03 | 2009-12-03 | 998349.03 | 4.959
10313 | Underway | C250,C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PIKE |  | 10 | Z044191 | This project is to make it safet for the public by replacing the deteriorating bridge carrying Twin Lakes Road (SR 1005) over Shohola Creek in Shohola Township in Pike County. | Bridge Replacement | 2010-01-04 | 2010-01-04 | 2010-10-14 |  | 897035 | 0.028
10314 | Underway | C250,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PIKE |  | 10 | Z044192 | This project is to replace the deteriorating bridge carrying Twin Lakes Road (SR 1005) over Shohola Creek in Shohola Township in Pike County. | Bridge Replacement | 2010-01-04 | 2010-01-04 | 2010-10-14 |  | 913403 | 0.028
10315 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PIKE |  | 10 | Z044193 | This project is to make the existing pavement smoother by resurfacing 15.4 miles of State Route 390 from the Monroe County line north to State Route 507 in Greene, Palmyra, and Blooming Grove Township | Pavement Improvement | 2010-09-07 | 2010-09-08 | 2011-07-31 |  | 1990000 | 15.439
10316 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SUSQUEHANNA |  | 10 | Z045231 | This 0.5 mile long project in Susquehanna County will repair a section of roadway embankment on State Route 267 in Coconut Township damaged by numerous storms between 2006 and 2009. Repairs will inclu | Pavement Improvement | 2009-05-27 | 2009-06-11 | 2009-12-30 | 2009-10-01 | 509463.37 | 0.294
10317 | Completed | C250,C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SUSQUEHANNA |  | 10 | Z045244 | This project in Susquehanna County will extend the life of the bridge on State Route 2040 over the Lackawanna River by installing new prestressed concrete beams, a new concrete deck, and replacing the | Bridge Improvement | 2009-08-06 | 2009-08-24 | 2011-08-15 | 2011-05-17 | 1243000 | 0.038
10318 | Completed | C250,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SUSQUEHANNA |  | 10 | Z045245 | This 16 mile long project will resurface two heavily travelled highways, SR 11 and SR 2023 in Susquehanna County, to improve ride quality and extend the life of the pavement. Included in this project | Pavement Improvement | 2009-06-22 | 2009-07-13 | 2009-12-30 | 2009-10-01 | 660057.02 | 6.398
10319 | Completed | C250,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SUSQUEHANNA |  | 10 | Z045246 | This project is to make the roadway last longer and ride smoother by resurfacing the deteriorating asphalt roadways on various State Routes in Susquehanna County. This project is part of State Project | Pavement Improvement | 2009-06-22 | 2009-07-13 | 2009-12-30 | 2009-10-01 | 1689748.8 | 9.485
10320 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SUSQUEHANNA |  | 10 | Z045249 | This 4 mile long project in Susquehanna County will resurface a local highway, SR 4002 (Laurel Lake Road) to improve ride quality and extend the life of the pavement. Included in this project are edg | Pavement Improvement | 2009-09-14 | 2009-10-08 | 2010-02-07 | 2009-11-09 | 649211.27 | 4.231
10321 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SUSQUEHANNA |  | 10 | Z045251 | This project is to make the traveling public safer by replacing the deteriorating bridge carrying Graham Road (SR 3033) over Wyalusing Creek in Rush Township in Susquehanna County. | Bridge Replacement | 2010-01-08 | 2010-03-29 | 2010-12-23 | 2010-09-24 | 900000 | 0.016
10322 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SUSQUEHANNA |  | 10 | Z045252 | This project is make the traveling public safer by replacing the deteriorating bridge carrying Graham Road (SR 3033) over Wyalusing Creek in Rush Township in Susquehanna County. | Bridge Replacement | 2010-01-08 | 2010-03-29 | 2010-12-23 | 2010-09-24 | 150000 | 0.016
10323 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WAYNE |  | 10 | Z046215 | This project will extend the lives of the SR 3037 Bridge over Middle Creek in Cherry Ridge Township, Wayne County, and the SR 2005 Bridge over Roaring Brook in Moscow, Lackawanna County. On 3037, the | Bridge Improvement | 2009-04-20 | 2009-04-20 | 2010-07-29 | 2010-04-30 | 798819.14 | 0.495
10324 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WAYNE |  | 10 | Z046217 | This project in Wayne County will extend the life of the State Route 3006 Ledgedale Road bridge over Ariel Creek by replacing the deteriorated superstructure with a new concrete superstructure. | Bridge Improvement | 2009-06-22 | 2009-06-22 | 2010-11-16 | 2010-08-18 | 578000 | 0.409
10325 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WAYNE |  | 10 | Z046218 | This State Route 4031 bridge over Johnson Creek, painting project in Wayne County will include containment and disposal of hazardous material and painting the steel beams to extend the life of the bri | Bridge Improvement | 2009-06-08 | 2009-07-13 | 2009-12-17 | 2009-09-18 | 94086.54 | 0.428
10326 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WYOMING |  | 10 | Z047189 | This project will extend the lives of the SR 29 Bridge in Laceyville Borough and the SR 3001 Bridge in Eaton Township, Wyoming County. On SR 29, the project will repair the deteriorated deck, constru | Bridge Improvement | 2009-07-07 | 2009-07-07 | 2011-02-02 | 2010-11-04 | 3450000 | 1.569
10327 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS | READING | 06 | Z051239 | This project will make the road smoother by removing several inches of deteriorating pavement, patching the concrete, and replacing it with new pavement surface on SR 3222 from PA 724 (Philadelphia Av | Pavement Improvement | 2009-10-22 | 2009-10-22 | 2012-01-08 | 2011-10-10 | 2180274.25 | 3.776
10328 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS | READING | Multiple | Z051240 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 2005 - 5th Street in the City of Reading, Berks County. | Pavement Improvement | 2009-06-03 | 2009-10-13 | 2011-11-23 | 2011-08-25 | 3442714.22 | 3.789
10329 | Completed | C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS | READING | Multiple | Z051241 | The project will paint the steel beams on 11 bridges in various locations in Berks County | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2011-01-27 | 2010-10-29 | 4958346.78 | 2.991
10330 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS | READING | 06 | Z051242 | The project will install metal guardrail in median of State Route 100 to improve safety and reduce median crossover crashes in Berks County. | Safety/Traffic Management | 2009-09-22 | 2009-10-13 | 2010-03-22 | 2009-12-22 | 308242.92 | 1.645
10331 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS | READING | Multiple | Z051243 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and adding linestriping on US Route 222 in Spring, Muhlenberg, Ontelaunee and Mai | Pavement Improvement | 2009-07-07 | 2009-07-08 | 2011-08-10 | 2011-05-12 | 11244850 | 28.311
10332 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS |  | 17 | Z051246 | The project will install cameras and changeable message signs to improve traveler information availability on Interstate 78 from the Lebanon County Line to State Route 61 in Berks County. | Safety/Traffic Management | 2009-06-29 | 2009-06-29 | 2011-04-25 | 2011-01-25 | 1943027 | 0.800
10333 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS | READING | 17 | Z051247 | This project is to replace the substandard precast parapets (concrete railing) on bridges on Interstate 78 in Lenhartsville, Greenwich Township in Berks County. This project is part of State Project N | Safety/Traffic Management | 2009-10-13 | 2010-05-03 | 2011-12-01 |  | 1020000 | 0.362
10334 | Underway | C220,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS | READING | Multiple | Z051265 | This project will make pedestrian safer by installing curb ramps that meet Americans with Disablities Act requirements in various locations in Berks County. | Transportation Enhancements | 2010-02-18 | 2010-02-18 | 2011-07-30 |  | 1848395.46 | 96.503
10335 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS |  | 17 | Z051278 | This project is to enhance safety by making improvements to the intersection of Bernville Road (State Route 183) and Plum Creek Road (State Route 4030) by installating a new traffic signal, establishi | Safety/Traffic Management | 2010-09-07 | 2010-09-07 | 2012-09-30 |  | 355000 | 0.042
10336 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BERKS | READING | Multiple | Z051280 | This project is to make the roadway smoother by overlaying 3.8 miles of the asphalt pavement on State Route 222 from Lehigh County line to Kutztown Bypass in Maxatawny Township in Berks County. | Pavement Improvement | 2010-09-07 | 2010-09-07 | 2012-01-12 | 2011-10-14 | 1551419 | 2.358
10337 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CARBON |  | 11 | Z052135 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 209 from McCall Bridge through Lehighton in Carbon County | Pavement Improvement | 2009-06-30 | 2009-09-23 | 2010-10-22 | 2010-07-24 | 1880575.62 | 4.249
10338 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053191 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 329 in North Whitehall and Whitehall Townships in Lehigh County | Pavement Improvement | 2009-06-04 | 2009-10-26 | 2010-10-28 | 2010-07-30 | 1754025.14 | 1.510
10339 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053193 | This project will increase the life of several bridges by painting the steel beams on 11 bridges in various locations in Lehigh County | Bridge Improvement | 2009-05-21 | 2009-05-21 | 2011-01-10 | 2010-10-12 | 1548670.24 | 0.180
10340 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053194 | The project will repair bridge parapets on various state routes in Weisenberg, South Whitehall, Whitehall, Washington Townships and City of Bethlehem, in Lehigh and Northampton Counties | Safety/Traffic Management | 2009-10-13 | 2010-05-03 | 2011-12-01 |  | 4010648 | 1.997
10341 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053202 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and add curb ramps on Fairmont Avenue from MacArthur Road to Fullerton Avenue in Wh | Pavement Improvement | 2010-01-19 | 2010-01-19 | 2011-02-17 | 2010-11-19 | 855513.88 | 0.000
10342 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053203 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and add curb ramps on Hanover Avenue from the Lehigh River Bridge to Irving Street | Pavement Improvement | 2010-01-19 | 2010-01-19 | 2010-11-30 |  | 2291766.44 | 0.000
10343 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053205 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and add curb ramps on Broad Street from Terrace Avenue to Eaton Avenue and on Penns | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2011-10-27 | 2011-07-29 | 1952000 | 0.000
10344 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LEHIGH | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z053213 | This project is to make 3.0 miles of State Route 378 safer and smoother by widening, resurfacing, pipe replacement, guide rail update, drainage improvements, sign replacement and bridge safety improve | Pavement Improvement | 2010-09-07 | 2010-10-04 | 2011-12-25 | 2011-09-26 | 1108031 | 2.981
10345 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONROE |  | 11 | Z054183 | The project will replace the deteriorated decks of 10 bridges in various locations in Monroe and Schuylkill Counties | Bridge Improvement | 2009-06-04 | 2009-06-15 | 2011-03-03 | 2010-12-03 | 2177420.16 | 0.254
10346 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONROE |  | 11 | Z054184 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 33 and State Route 8017 in Hamilton Township, Monroe County. | Pavement Improvement | 2009-07-16 | 2009-08-17 | 2012-02-09 | 2011-11-11 | 7997775 | 6.324
10347 | Underway | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONROE |  | 11 | Z054185 | This project will upgrade existing traffic barrier on bridges to improve safety on Interstate 80 in Pocono Township, Monroe County. This project will also upgrade existing traffic barrier on bridge | Safety/Traffic Management | 2009-09-25 | 2010-04-11 | 2011-11-11 |  | 1969052 | 1.804
10348 | Underway | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONROE |  | 11 | Z054186 | This project is to replace non-standard precast parapets (concrete railings) on bridges on Interstate 80 in Pocono Township in Monroe County. This project is part of State Project Number 66660, 66662, | Safety/Traffic Management | 2009-09-25 | 2010-04-11 | 2011-11-11 |  | 4650801 | 1.130
10349 | Underway | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONROE |  | 11 | Z054187 | This project is to replace non-standard precast parapets (concrete railings) on various bridges in Stroud, Smithfield Townships, Stroudsburg and East Stroudsburg Boroughs in Monroe County. This proje | Safety/Traffic Management | 2009-09-25 | 2010-04-11 | 2011-11-11 |  | 3482484 | 0.930
10350 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONROE |  | 11 | Z054189 | The project will construct curb ramps for improving pedestrian access and safety at various locations in Coolbaugh, Middle Smithfield, Pocono, Polk, Smithfield and Stroud Townships, the Boroughs of Ea | Transportation Enhancements | 2010-01-21 | 2010-01-21 | 2012-04-19 | 2012-01-20 | 529845 | 23.907
10351 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONROE |  | 11 | Z054192 | This project will repair the concrete pavement, repair and seal the joints, and resurface the pavement from the Luzerne County line to PA 54 Interchange including new pavement on the four ramps at the | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2012-01-29 |  | 14785154 | 10.178
10352 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONROE |  | 11 | Z054195 | This project in Monroe County will make the roadway last longer and ride smoother by improving the asphalt roadway on PA 33, including the Sciota and Snydersville ramps, from Bossardsville Road includ | Pavement Improvement | 2010-02-25 | 2010-02-25 | 2012-02-12 | 2011-11-14 | 6123419.51 | 11.058
10353 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055193 | The project will replace the deteriorated decks of 7 bridges in various locations in Northampton County | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2010-01-11 | 2009-10-13 | 1779798.76 | 0.198
10354 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055194 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement and linestriping on State Route 33 from Belfast to Wind Gap in Northampton County | Pavement Improvement | 2009-06-30 | 2009-09-08 | 2012-02-15 | 2011-11-17 | 10268188.11 | 13.530
10355 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055195 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 412 from Interstate 78 through Hellertown in Northampton County | Pavement Improvement | 2009-05-27 | 2009-07-20 | 2010-02-21 | 2009-11-23 | 1408327.7 | 1.991
10356 | Underway | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055197 | This project will construct curb ramps to improve pedestrian access and safety at various locations in Northampton County. | Transportation Enhancements | 2010-01-22 | 2010-01-21 | 2011-01-30 |  | 1041110.74 | 40.962
10357 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055198 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on Interstate 78 from State Route 412 to Easton in Northampton County | Bridge Replacement | 2009-09-15 | 2010-05-09 | 2012-02-20 | 2011-11-22 | 9552180 | 31.883
10358 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHAMPTON | ALLENTOWN-BETHLEHEM-EASTON (NJ) | 15 | Z055203 | This project will make the street system safer by relocating and realigning the existing 2nd Street ramp from 3rd Street to PA 378 in the City of Bethlehem in Northampton County. | Pavement Improvement | 2010-02-17 | 2010-04-12 | 2012-01-08 |  | 6106044 | 0.194
10359 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | NORTHAMPTON |  | 15 | Z055204 | This project in Northampton County will make the bridge last longer by replacing deterioriating portions of the Eighth Street Bridge over PA 33 in Plainfield Township. | Bridge Improvement | 2010-03-03 | 2010-04-12 | 2011-08-31 | 2011-06-02 | 382931.78 | 0.000
10360 | Underway | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SCHUYLKILL |  | 17 | Z056178 | This project in Schukill County is to replace the non-standard precast bridge parapets (concrete railings) on several bridges. This project is part of State Project Numbers 66660, 66661, and 66662. | Safety/Traffic Management | 2009-09-25 | 2010-04-11 | 2011-11-11 |  | 631520 | 0.224
10361 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SCHUYLKILL |  | 17 | Z056179 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on State Route 924 from State Route 61 to 4 lane section north of Frackville in Sch | Pavement Improvement | 2009-07-09 | 2009-07-13 | 2011-02-21 | 2010-11-23 | 832809 | 0.963
10362 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SCHUYLKILL |  | 17 | Z056180 | The project will construct curb ramps at various locations in Schuylkill County to improve pedestrian access and safety. | Transportation Enhancements | 2010-01-04 | 2010-01-04 | 2012-03-22 | 2011-12-23 | 432047 | 49.616
10363 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SCHUYLKILL |  | 17 | Z056182 | This project will make the road smoother by overlaying the existing deteriorating pavement with new asphalt pavement on PA 54 from the Bridge over the Reading and Blue Mountain Railroad, near Coles S | Pavement Improvement | 2010-01-20 | 2010-01-19 | 2012-03-19 | 2011-12-20 | 3665205.9 | 5.131
10364 | Underway | C250,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SCHUYLKILL |  | 17 | Z056187 | This project will improve the smoothness of the roadway surface by repairing and sealing the concrete, milling, overlay and shoulder rehabilitation and upgrading I-81 from Luzerne County Line to the P | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2011-12-30 |  | 24425748 | 17.138
10365 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 08 | Z061100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Bucks County | Transportation Enhancements | 2009-06-19 | 2009-07-20 | 2010-04-01 | 2010-01-01 | 1067150.4 | 3.835
10366 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 08 | Z061101 | This project will add cameras, message boards and instrumentation to detect incidents and provide Travel Times to help the traveling public on Interstate 95 in various locations of Bucks and Philadelp | Safety/Traffic Management | 2009-06-30 | 2009-08-31 | 2013-10-09 |  | 22853719 | 46.963
10367 | Underway | C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 08 | Z061102 | This project will add cameras, message boards and instrumentation to detect incidents and provide Travel Times to help the traveling public in various locations of Philadelphia and Bucks Counties. | Safety/Traffic Management | 2009-09-14 | 2009-09-14 | 2013-11-27 |  | 19879059 | 41.837
10368 | Completed | C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 08 | Z061103 | This project will mill and overlay the existing pavement, install a landscaped median, provide new traffic signals, pavement markings and signing on Stoopville Road in Newton Township, Bucks County. | Pavement Improvement | 2009-09-23 | 2009-11-09 | 2010-09-01 | 2010-06-03 | 1322270.54 | 4.112
10369 | Completed | C220,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUCKS | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 08 | Z061104 | This project will provide a paved pedestrian and bike trail from the New Hope borough municipal parking lot to the New Hope-Ivyland historic train station in Bucks County. | Transportation Enhancements | 2009-12-10 | 2010-01-27 | 2011-01-25 | 2010-10-27 | 291448 | 0.000
10370 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z062100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Chester County | Transportation Enhancements | 2009-04-30 | 2009-06-29 | 2011-03-10 | 2010-12-10 | 4978590 | 101.163
10371 | Completed | C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 06 | Z062101 | This project will mill and overlay 5 miles of existing pavement, install an updated median barrier, shoulder rumble strips, pavement markings, and updated signing and guiderail on the US Route 30 Exto | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-09-13 | 2010-06-15 | 5038807 | 10.249
10372 | Completed | C220,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z062102 | This project will convert 2 miles of abandoned railway into a paved pedestrian and bike trail from State Route 29 to Church Farm School Road in Tredyffrin, East Whiteland and West Whiteland Townships, | Transportation Enhancements | 2009-09-20 | 2009-09-23 | 2010-12-09 | 2010-09-10 | 4558414 | 0.000
10373 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 16 | Z062103 | This project in Chester County is to remove the abandonded abutments from the old State Street bridge over AMTRAK in Parkesburg Borough. | Pavement Improvement | 2010-01-27 | 2010-02-01 | 2010-08-01 |  | 707000 | 0.000
10374 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 07 | Z062104 | This project in Chester County will make the roadway last longer and ride smoother by removing the deteriorating upper layers of asphalt and replace it with new asphalt on US 202 from Stanton Avenue t | Pavement Improvement | 2010-05-21 | 2010-05-25 | 2011-09-30 |  | 15408924 | 7.614
10375 | Completed | C220,C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CHESTER | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z062105 | This project will provide new sidewalks along sections of Old Lancaster Rd., Conestoga Rd., Howelville Rd., and Irish Rd. It will also install traffic calming measures and provide storm water manageme | Transportation Enhancements | 2010-01-06 | 2010-03-01 | 2011-03-13 | 2010-12-13 | 2181451.23 | 0.000
10376 | Underway | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z063100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Delaware County. | Transportation Enhancements | 2009-05-08 | 2009-06-15 | 2010-06-27 |  | 4233367.58 | 27.008
10377 | Underway | C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z063101 | This project on I-95 and I-476, in Philadelphia, Delaware, and Montgomery Counties, will install cameras, message boards, and instrumentation to detect incidents and provide Travel Times to minimize d | Safety/Traffic Management | 2009-07-13 | 2009-07-20 | 2013-10-09 |  | 15009061 | 72.188
10378 | Completed | C220,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z063102 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings on Bridgewater and Brookhaven Roads in Brookhaven Borough, Delaware County. | Transportation Enhancements | 2009-07-06 | 2009-10-21 | 2010-07-18 | 2010-04-19 | 198434.35 | 0.769
10379 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 07 | Z063103 | This project will provide new traffic signal equipment at the intersection of Darby-Paoli and Whitehorse Roads in Newtown Township, Delaware County. | Safety/Traffic Management | 2009-08-31 | 2009-08-31 | 2010-02-15 | 2009-11-17 | 130067.16 | 0.361
10380 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z063104 | This project will replace incandescent traffic signal heads with more efficient Light Emitting Diode traffic signal heads at 7 intersections and pedestrian signals at 4 locations in Darby, Brookhaven | Safety/Traffic Management | 2009-08-31 | 2009-08-31 | 2011-03-21 | 2010-12-21 | 206907 | 2.551
10381 | Completed | C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DELAWARE | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 07 | Z063105 | This project will provide a smoother road by milling and repaving Valley Rd. from Middletown Road to Brick House Farm Road in Edgemont Township, Delaware County. | Pavement Improvement | 2009-09-25 | 2009-10-01 | 2010-01-25 | 2009-10-27 | 188733.24 | 0.000
10382 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z064100 | This project will repair existing pavement and resurface and provide pavement markings and drainage and guiderail improvements on US Route 422 from State Route 29 to Township Line in Limerick and Upp | Pavement Improvement | 2009-05-22 | 2009-05-22 | 2011-04-06 | 2011-01-06 | 14468477.71 | 10.050
10383 | Completed | C220,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z064101 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings at various locations in Montgomery County to improve pedestrian access and safety. | Transportation Enhancements | 2009-05-19 | 2009-07-20 | 2010-04-11 | 2010-01-11 | 1587279.9 | 7.197
10384 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 13 | Z064102 | This project will provide landscaping enhancements along Bethlehem Pike in Springfield and Whitemarsh Townships, Montgomery County, to improve the aesthetics for drivers and pedestrians. | Transportation Enhancements | 2009-07-17 | 2009-07-17 | 2010-08-26 | 2010-05-28 | 273000 | 0.095
10385 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z064103 | This project will reconstruct the pavement and shoulders along I-476 from I-76 to the PA Turnpike, in Plymouth Township and West Conshohocken Borough, Montgomery County. This project also include bri | Pavement Improvement | 2009-08-31 | 2009-09-14 | 2012-11-22 |  | 3771084 | 9.831
10386 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 07 | Z064104 | This project will construct new ramps to and from I-76 at Henderson Rd. in Upper Merion Township, Montgomery County. | Pavement Improvement | 2009-10-15 | 2009-11-06 | 2012-07-19 |  | 11938178 | 3.718
10387 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | MONTGOMERY | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z064105 | This project will include traffic signal improvements and pedestrian signals, and construct concrete curb ramp for pedestrian access and safety in 11 municipalities in Montgomery County.. | Safety/Traffic Management | 2009-12-31 | 2009-12-31 | 2011-07-28 |  | 4673888 | 0.510
10388 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z065100 | This project will provide concrete curb ramps, pavement restoration, and new pavement markings on various state highways in the City of Philadelphia, Philadelphia County. | Transportation Enhancements | 2009-06-25 | 2009-08-17 | 2011-12-08 | 2011-09-09 | 1771793.07 | 18.345
10389 | Underway | C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z065101 | This project provides for milling and paving of over 20 miles of Philadelphia City streets and installing concrete curb ramps. | Transportation Enhancements | 2009-10-14 | 2009-10-14 | 2010-12-12 |  | 6198539 | 0.000
10390 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 01 | Z065102 | This project will make the bidge last longer by repairing and painting structural steel, and redecking the bridge surface on the Girard Point Bridge on I-95 in Philadelphia. | Bridge Improvement | 2009-10-02 | 2009-10-02 | 2012-10-24 |  | 77579068.75 | 1.958
10391 | Underway | C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z065103 | This project provides for milling and paving various Philadelphia City streets and providing concrete curb ramps. | Transportation Enhancements | 2010-01-29 | 2010-02-04 | 2010-10-19 |  | 4317115 | 0.000
10392 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 02 | Z065104 | This project is to replace four deteriorating Gustine Lake Bridges in the City of Philadelphia, Philadelphia County. | New Construction | 2010-02-18 | 2010-03-01 | 2011-10-30 |  | 13672965 | 0.205
10393 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | Multiple | Z065105 | This project will improve safety by constructing concrete and brick curb ramps, replacing traffic signal poles, and resurfacing various city of Philadelphia streets in the southeast quadrant of the ce | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-11-10 |  | 3674000 | 0.000
10394 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PHILADELPHIA | PHILADELPH-WILMINGTON (PA-DE-NJ-MD) | 02 | Z065106 | This project is to install safety improvements and rehabilitate both bridge structures that carry US 1 (Roosevelt Expressway) over the Schuylkill River in the City of Philadelphia, Philadelphia County | Bridge Improvement | 2010-02-19 | 2010-02-19 | 2011-03-04 |  | 6375859 | 0.748
10395 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ADAMS |  | 19 | Z081001 | This project will improve rideability and safety by resurfacing and updating guiderail on 6 miles of US 15 north of Gettysburg in Adams County. | Pavement Improvement | 2009-06-22 | 2009-06-25 | 2012-03-19 | 2011-12-20 | 6785000 | 9.378
10396 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CUMBERLAND |  | 09 | Z082001 | This project will improve safety by replacing an existing deteriorated bridge on SR 34 north of Carlisle in Cumberland County. | Bridge Replacement | 2009-04-29 | 2009-06-11 | 2010-02-18 | 2009-11-20 | 1888751.7 | 0.032
10397 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CUMBERLAND |  | 19 | Z082002 | This Cumberland County project will improve rideability and safety by resurfacing about 8 miles of I-81 SB from Exit 57 to Exit 65, Restoring concrete pavement at Milepost 50.5 Northbound near Carlisl | Pavement Improvement | 2009-07-27 | 2009-07-30 | 2010-03-03 | 2009-12-03 | 5000077 | 18.534
10398 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CUMBERLAND | HARRISBURG | 19 | Z082003 | This project will extend the life of the bridge and improve safety of the SR 15 bridge over SR 114 south of the Pennsylvania Turnpike and of the Wesley Road/Rossmoyne Road bridge over US 15 north of t | Bridge Improvement | 2009-07-08 | 2009-07-13 | 2010-07-16 | 2010-04-17 | 3185798.52 | 0.076
10399 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CUMBERLAND | HARRISBURG | Multiple | Z082004 | This project will improve rideability and safety by resurfacing about 2 miles of SR 641 from US 11 to PA 465 in North Middletown Township on the west side of Carlisle, in Cumberland County. This pr | Pavement Improvement | 2009-09-23 | 2009-09-28 | 2010-10-21 | 2010-07-23 | 1990363.73 | 4.658
10400 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FRANKLIN |  | 09 | Z083001 | This project will improve rideability and safety by resurfacing 6 miles of US 30 from Norlo Road to the Adams County Line in Guilford and Greene Townships east of Chambersburg in Franklin County. | Pavement Improvement | 2009-05-18 | 2009-05-20 | 2010-01-21 | 2009-10-23 | 2970387.06 | 6.843
10401 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | YORK | YORK | 19 | Z083002 | This project will improve rideability and safety by resurfacing, updating guiderail and restoring 3 structures (surfacing and substructure repairs) on about 5 miles of US 30 from the Hellam Interchang | Pavement Improvement | 2009-06-08 | 2009-06-11 | 2010-01-12 | 2009-10-14 | 3422473.45 | 9.954
10402 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FRANKLIN |  | 09 | Z083003 | This Franklin County project will improve rideability and safety by resurfacing and updating guiderail on US 30 from State Route 3012 (Jack Road) to Hilltop Drive in St Thomas and Hamilton Townships w | Pavement Improvement | 2009-07-02 | 2009-07-06 | 2010-03-11 | 2009-12-11 | 3051581.76 | 5.717
10403 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FRANKLIN |  | 09 | Z083004 | This Franklin County project will extend the life of the PA 433 bridge over Rowe Run in Southampton Township and improve safety by replacing the superstructure (beams and deck) and improving approache | Bridge Improvement | 2009-09-14 | 2009-09-17 | 2010-07-06 | 2010-04-07 | 448899.42 | 0.108
10404 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FRANKLIN |  | 09 | Z083005 | This bridge painting project will preserve the steel beams on the US 11 bridge (Molly Pitcher Highway) over I-81 Exit 3 in Antrim Township in Franklin County. | Bridge Improvement | 2009-09-14 | 2010-04-12 | 2010-09-06 | 2010-06-08 | 436010.9 | 0.052
10405 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FRANKLIN |  | 09 | Z083006 | This Franklin County project will make the bridge last longer by rehabilitating the deteriorating portions of the bridge carrying Mont Alto Road (SR 2031) over the Conococheague Creek tributary in Gui | Bridge Improvement | 2010-02-08 | 2010-02-08 | 2010-11-28 | 2010-08-30 | 437150 | 0.006
10406 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | YORK | YORK | 19 | Z084001 | This work will provide 3 closed circuit TV cameras in the York County Area on I-83 (Exits 21, 24, Milepost 30) and 1 Highway Advisory Radio (HAR) & 4 Signs at I-83 (Exit 22) to allow the District to m | Safety/Traffic Management | 2009-05-29 | 2009-05-29 | 2009-08-27 | 2009-05-29 | 662988 | 0.000
10407 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | YORK | YORK | 19 | Z084002 | This project will improve rideability and safety by resurfacing and updating guiderail on about 2.5 miles of US 30 from Interstate 83 to State Route 24 in Manchester and Springettsbury Townships on th | Pavement Improvement | 2009-08-17 | 2009-08-20 | 2012-02-02 | 2011-11-04 | 7700000 | 7.499
10408 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | YORK | YORK | 19 | Z084003 | This York County project will improve rideability and safety by resurfacing the roadway and upgrading guiderail on about 7.5 miles of US 15 from Golf Course Road to Cumberland County Line in Carroll T | Pavement Improvement | 2009-09-23 | 2010-03-01 | 2011-02-22 | 2010-11-24 | 2881500 | 5.035
10409 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | YORK |  | 19 | Z084004 | This York County project will make the bridge last longer by restoring the deteriorating portions of the Indian Rock Dam Road (SR 3044) bridge over West Branch of Codorus Creek in North Codorus and We | Bridge Improvement | 2010-02-15 | 2010-02-15 | 2010-08-30 | 2010-06-01 | 693894.01 | 0.128
10410 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | YORK |  | 19 | Z084005 | This project will make the roadway last longer and ride smoother by resurfacing PA 116 with a new asphalt riding surface from Jacobs Mill Road (SR 3045) to PA 516 in Heidelberg and North Codorus Town | Pavement Improvement | 2010-02-25 | 2010-02-25 | 2011-10-19 | 2011-07-21 | 1787166 | 4.319
10411 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | YORK |  | 19 | Z084006 | This project is to make the 2.3 miles of State Highway 24 (Main Street and Barrens Road) smoother from Trouts Lane to to 2300 ft north of Lowe Road in Stewartstown Borough and Hopewell Township in Yor | Pavement Improvement | 2010-09-08 | 2010-09-08 | 2011-08-25 | 2011-05-27 | 735730 | 2.327
10412 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | YORK | YORK | 19 | Z084007 | This project is to make 2.9 miles of State Highway 74 (Carlisle Avenue) smoother from north of US 30 to State Highway 462 (Market Street in West Manchester Twp. and the City of York in York County. | Pavement Improvement | 2010-10-04 | 2010-10-06 | 2011-11-21 | 2011-08-23 | 1161520 | 2.848
10413 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DAUPHIN |  | 17 | Z085001 | This project will improve rideability and safety by resurfacing and updating guiderail on 1.5 miles of PA 147 from Fisher Street to Dawn Road north of Halifax, in Dauphin County. This Dauphin Count | Pavement Improvement | 2009-04-30 | 2009-05-18 | 2009-12-30 | 2009-10-01 | 2029171.63 | 5.344
10414 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DAUPHIN |  | 17 | Z085002 | This project will upgrade the crashworthiness of precast concrete parapets on bridges in Dauphin County at US 22 Eastbound, Westbound, Ramps and Retaining Walls over the Susquehanna River at Clarks Fe | Safety/Traffic Management | 2009-06-23 | 2009-06-23 | 2011-05-22 | 2011-02-21 | 5107600 | 1.372
10415 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DAUPHIN | HARRISBURG | 17 | Z085003 | This Dauphin County project will provide 5 closed circuit TV cameras in the Harrisburg Metropolitan Area on I-81 (Exits 45, 47, Milepost 74, Milepost 79) and US 22/322 (PA39 Exit) to allow the Distric | Safety/Traffic Management | 2009-05-29 | 2009-05-29 | 2009-06-28 |  | 736557.88 | 0.000
10416 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DAUPHIN | HARRISBURG | 17 | Z085004 | This Dauphin County project will improve rideability and safety by resurfacing 2 miles of I-83 south of Union Deposit Road interchange to Bridge over Valley Road in Lower Paxton Township from Exit 48 | Pavement Improvement | 2009-07-27 | 2009-08-31 | 2010-12-22 | 2010-09-23 | 2995000 | 8.802
10417 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DAUPHIN | HARRISBURG | 17 | Z085006 | This project will relieve congestion and improve safety of about 1.5 miles of PA 39 with pavement widening and reconstruction, installing traffic signals and other misc. work at the PA 39/I-81 Interch | Pavement Widening | 2009-07-17 | 2009-07-20 | 2012-04-19 | 2012-01-20 | 10700000 | 2.045
10418 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DAUPHIN | HARRISBURG | 17 | Z085007 | This Dauphin County project will improve rideability and safety by resurfacing, drainage improvements, ADA ramps and other misc. improvements on about 2 miles of SR 230 (Cameron Street) and about 6 mi | Pavement Improvement | 2009-09-28 | 2010-04-20 | 2011-01-13 | 2010-10-15 | 2258960 | 3.651
10419 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | DAUPHIN |  | 17 | Z085008 | This project is to improve safety by replacing the bridge on State Route 209 over Wiconisco Creek at Williams Valley High School in Williams Township in Dauphin County. | Bridge Replacement | 2010-09-13 | 2010-09-13 | 2012-05-26 |  | 1861923 | 0.241
10420 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LANCASTER | LANCASTER | 16 | Z087001 | This Lancaster County project will improve safety and remove weight restrictions on the PA 324 bridge over Pequea Creek in Pequea and Martic Townships by replacing the superstructure (beams and deck) | Bridge Improvement | 2009-04-20 | 2009-04-20 | 2010-09-01 | 2010-06-03 | 1622293.03 | 0.037
10421 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LANCASTER |  | 16 | Z087002 | This project will upgrade the crashworthiness of precast concrete parapets on bridges in Adams County on SR 1005 over Mud Creek, 3 miles southeast of York Springs; in Cumberland County on I-83 over SR | Safety/Traffic Management | 2009-06-23 | 2009-06-23 | 2010-10-07 | 2010-07-09 | 2063628 | 2.947
10422 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LANCASTER | LANCASTER | 16 | Z087003 | This Lancaster County project will provide 2 closed circuit TV Cameras in the Lancaster County Area on US 30 (PA 501 and PA 283 Exits under Part IV of Contract 354R23, Phase 4 (Expansion of the Harris | Safety/Traffic Management | 2009-05-29 | 2009-05-29 | 2009-08-27 | 2009-05-29 | 318350 | 0.000
10423 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LANCASTER | LANCASTER | 16 | Z087004 | This Lancaster County project will improve rideability and safety by resurfacing and updating guiderail on about 7.5 miles of State Route 222 from north of Bushong Road to US Route 322 in Ephrata, Man | Pavement Improvement | 2009-06-22 | 2009-06-24 | 2011-08-04 | 2011-05-06 | 12401485 | 12.297
10424 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LANCASTER |  | 16 | Z087005 | This Lancaster County project will improve rideability and safety by resurfacing and updating guiderail on about 5 miles of State Route 222 from Quarryville to Brennenman Road in Providence and Stras | Pavement Improvement | 2009-08-14 | 2009-08-17 | 2010-11-18 | 2010-08-20 | 3390677 | 5.218
10425 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LANCASTER | LANCASTER | 16 | Z087006 | This Lancaster County project will improve rideability and safety by resurfacing and updating guiderail on US 30 from PA 896 to PA 897 in East Lampeter, Leacock, Paradise, and Salisbury Townships east | Pavement Improvement | 2009-09-28 | 2009-09-30 | 2011-07-17 | 2011-04-18 | 4186500 | 9.800
10426 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LANCASTER |  | 16 | Z087007 | This Lancaster County project will make the roadway last longer and ride smoother by resurfacing the deteriorating asphalt pavement with a new riding surface on PA 272 from US 222 to north of Dennis D | Pavement Improvement | 2010-02-20 | 2010-03-01 | 2011-01-27 | 2010-10-29 | 4082123 | 9.551
10427 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LANCASTER |  | 16 | Z087008 | Rehabilitation of the Wrights Ferry Bridge on US-30 over Susquehanna River in Columbia Borough and West Hempfield Township | Bridge Improvement | 2010-10-25 | 2011-03-18 | 2012-12-21 |  | 2150741.48 | 1.084
10428 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LEBANON |  | 17 | Z088001 | This Lebanon County project will improve rideability and safety by resurfacing, upgrading guiderail, placing concrete median barrier and constructing left turn lanes on about 3 miles of US 22 from Lin | Pavement Improvement | 2009-08-14 | 2009-08-17 | 2011-01-27 | 2010-10-29 | 6179250 | 5.890
10429 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PERRY |  | Multiple | Z089001 | This Perry County project will improve rideability and safety by resurfacing and updating guiderail on about 3 miles of State Route 74 east of Loysville. | Pavement Improvement | 2009-04-30 | 2009-06-15 | 2009-12-24 | 2009-09-25 | 1104225.01 | 3.134
10430 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | PERRY |  | 09 | Z089002 | This project will make the bridge last longer by restoring the deteriorating portions of the bridge carrying Waggoners Gap Road (PA 74) over Sherman's Creek in Spring Township in Perry County. | Bridge Improvement | 2010-02-17 | 2010-03-17 | 2012-01-29 | 2011-10-31 | 3093159 | 0.341
10431 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BEDFORD |  | 09 | Z091001 | This project will overlay the existing deteriorating pavement with new asphalt pavement of State Route 30 from Stony Lane (T-720) to the Snake Spring Twp Line in Bedford Township and Bedford Borough i | Pavement Improvement | 2009-04-29 | 2009-04-29 | 2011-07-27 | 2011-04-28 | 6340143 | 9.321
10432 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BEDFORD |  | 09 | Z091002 | The project will paint the steel beams of 20 bridges in Bedford, Blair, Cambria, Fulton, Huntingdon and Somerset Counties | Bridge Improvement | 2009-05-04 | 2009-05-18 | 2010-02-10 | 2009-11-12 | 4616127.54 | 2.495
10433 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BEDFORD |  | 09 | Z091003 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated decks on various structures in Bedford County | Bridge Improvement | 2009-05-01 | 2009-07-14 | 2010-02-01 | 2009-11-03 | 251406.63 | 0.103
10434 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BEDFORD |  | 09 | Z091004 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams of 2 bridges on State Route 915 over Sandy Run in Broadtop To | Bridge Improvement | 2009-07-22 | 2009-08-17 | 2011-09-25 | 2011-06-27 | 1509774 | 0.134
10435 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BEDFORD |  | 09 | Z091005 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and patching concrete beams on SR 1010 (Woy Bridge Road) over Raystown Branch of the Jun | Bridge Improvement | 2009-09-11 | 2010-04-16 | 2011-02-09 | 2010-11-11 | 1890957 | 0.134
10436 | Completed | C250,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BEDFORD |  | 09 | Z091006 | This project is to extend the life of six bridges in Bedford County. These include: Chaneysville Road (SR 2002) over Elk Lick Creek approximately 1/2 mile south - Over Elk Lick Creek, Brush Creek, Swe | Bridge Improvement | 2010-08-17 | 2010-08-23 | 2012-01-19 | 2011-10-21 | 1088361 | 0.069
10437 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BLAIR | ALTOONA | 09 | Z092001 | The Blair County project will construct new pavement surface, guardrail, and curb ramps on State Route 1001 from Convention Center Blvd north to 3rd Street and on State Route 36 from Pine St (T-612) t | Pavement Improvement | 2009-05-20 | 2009-05-26 | 2010-02-01 | 2009-11-03 | 4043473.6 | 11.386
10438 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BLAIR | ALTOONA | 09 | Z092002 | The project will construct a new pavement surface and curb ramps on Penn Street (State Route 36) from Chimney Rocks Road to Pine Street in Hollidaysburg Borough, Blair County. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2011-08-04 | 2011-05-06 | 3132375 | 1.842
10439 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BLAIR | ALTOONA | 09 | Z092003 | The project will replace deteriorated bridge deck surfaces on various bridges in Snyder, Antis Townships and Tyrone Borough, Blair County. | Bridge Improvement | 2009-07-21 | 2009-08-03 | 2011-08-10 | 2011-05-12 | 1511446 | 0.293
10440 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CAMBRIA | JOHNSTOWN | 09 | Z093001 | Replacement of deteriorated bridge decks on 3 bridges on State Route 1021 over Wyerough Run, State Route 1026 over Slate Lake Run, State Route 4024 over Chest Creek in White and Chest Township, Cambri | Bridge Improvement | 2009-06-16 | 2009-08-03 | 2011-02-17 | 2010-11-19 | 1562093 | 0.062
10441 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CAMBRIA | JOHNSTOWN | 12 | Z093002 | The project will construct a new pavement surface on US Route 219 from Galleria Drive to Palestine Road and resurface the bridge deck on the Palestine Road Bridge in Adams and Richland Townships in | Pavement Improvement | 2009-07-16 | 2009-08-03 | 2011-08-16 | 2011-05-18 | 5481851 | 9.457
10442 | Completed | C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CAMBRIA |  | Multiple | Z093003 | The project will replace deteriorated bridge decks for 2 bridges on Manor Drive (State Route 1001) over R. J. Corman Railroad near the intersection of Munster Rd (State Route 1003) and over R. J. Corm | Bridge Improvement | 2009-07-20 | 2009-08-03 | 2010-11-10 | 2010-08-12 | 909753 | 0.038
10443 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CAMBRIA |  | Multiple | Z093004 | This project in Cambria County will make the bridges last longer by repairing deteriorating portions of 10 bridges on US 219, PA 36, PA 56, PA 271 and SR 3031. | Bridge Improvement | 2010-03-01 | 2010-03-08 | 2012-02-02 | 2011-11-04 | 1772380 | 0.574
10444 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CAMBRIA | JOHNSTOWN | 12 | Z093005 | This Cambria County project will make the bridge last longer by rehabilitaing deteriorating portions of Eisenhower Boulevard (SR 3006) bridge over Stonycreek River near the intersection of Ferndale A | Bridge Improvement | 2010-02-02 | 2010-05-03 | 2011-09-27 | 2011-06-29 | 1635298 | 0.044
10445 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CAMBRIA |  | 12 | Z093006 | This project is to improve the deteriorating pavement and make it smoother by patching the concrete and overlaying about 9 miles of US 219 from the New Germany Interchange north to the US 22 Interchan | Bridge Improvement | 2010-10-09 | 2010-10-12 | 2012-01-23 | 2011-10-25 | 2238109 | 8.839
10446 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FULTON |  | 09 | Z094001 | This Fulton County project will replace bridge decks of 3 bridges on State Route 1003 over Cove Creek, State Route 3006 over Little Tonoloway, and State Route 4004 over Wooden Bridge Creek in Ayr an | Bridge Improvement | 2009-04-13 | 2009-04-20 | 2009-11-30 | 2009-09-01 | 506138.69 | 0.030
10447 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FULTON |  | 09 | Z094002 | The Fulton County project will construct a new pavement surface on US Route 30 from Bedford County line to the Truck Pull-off in Brush Creek Township. | Pavement Improvement | 2009-04-17 | 2009-05-05 | 2009-12-27 | 2009-09-28 | 591442.83 | 2.624
10448 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | HUNTINGDON |  | 09 | Z095001 | The project will replace the bridge on State Route 1010 in Huntingdon Borough over Standing Stone Creek in Huntingdon County. | Bridge Replacement | 2009-05-06 | 2009-06-12 | 2010-02-04 | 2009-11-06 | 1354913.34 | 0.024
10449 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | HUNTINGDON |  | 09 | Z095002 | The project will construct a new pavement surface on US Route 22 from Old Twenty-two Road (T-613) to Walnut Terrace Road (T-561) in Smithfield and Porter Townships, Huntingdon County. | Pavement Improvement | 2009-05-20 | 2009-05-26 | 2010-01-22 | 2009-10-24 | 1374826 | 1.904
10450 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | HUNTINGDON |  | 09 | Z095003 | The project will replace the deteriorated bridge deck surface on US 522 over Pump Station Road (T-396), Aughwick Creek and East Broad Top Railroad in Shirley Township | Bridge Improvement | 2009-09-24 | 2009-09-24 | 2011-03-21 | 2010-12-21 | 1724415 | 0.216
10451 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SOMERSET |  | 12 | Z097001 | The project will construct a new pavement surface on US Route 30 from Westmoreland County Line to State Route 985 in Jenner Township and Jennerstown Borough | Pavement Improvement | 2009-04-15 | 2009-05-13 | 2009-10-15 | 2009-07-17 | 1222568.55 | 3.816
10452 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SOMERSET |  | 09 | Z097002 | The project will replace 3 bridges and 2 deteriorated bridge decks on State Route 2019 and State Route 2021 over Shaffers Run in Fairhope Township | Bridge Replacement | 2009-06-01 | 2009-06-22 | 2011-12-17 |  | 2422643 | 0.105
10453 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | SOMERSET |  | 12 | Z097003 | The project will remove a bridge and place it with earth fill and asphalt pavement at Wilber Coal Company Coal Mine Railroad bridge in Quemahoning Township | Bridge Replacement | 2009-07-20 | 2009-08-11 | 2010-11-01 | 2010-08-03 | 477381.05 | 0.076
10454 | Underway | C490 | OJT/SS | PENNSYLVANIA | STATEWIDE |  |  | Z099001 | PENNDOT'S BUREAU OF EQUAL OPPORTUNITY: STATEWIDE ¦ ARRA GRANT TO PROVIDE HIGHWAY CONSTRUCTION INDUSTRY TRAINING THAT | Other | 2010-09-09 | 2010-09-19 |  |  | 300000
10455 | Underway | C490 | OJT/SS | PENNSYLVANIA | DAUPHIN | HARRISBURG | 17 | Z099002 | PENNDOT'S DISTRICT 8- DISTRICT-WIDE ¦ CONSTRUCTION INSPECTION TECHNICAL ASSISTANT TRAINING PROGRAM: | Other | 2010-09-09 | 2010-09-19 |  |  | 169023
10456 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ARMSTRONG |  | 03 | Z101207 | This project will extend the life of one bridge by placing an epoxy overlay on the deck. The bridge is on Iron Bridge Road, in Armstrong County, South Buffalo Township just west of the South Scenic Dr | Bridge Improvement | 2009-04-27 | 2009-06-08 | 2009-11-18 | 2009-08-20 | 313290.78 | 0.066
10457 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ARMSTRONG |  | 03 | Z101208 | This project will patch the existing concrete roadway on State Route 422 in Armstrong County West Franklin township and Worthington Borough. The project is from approximately 0.26 miles west of the SR | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2010-01-20 | 2009-10-22 | 5331218.42 | 13.338
10458 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ARMSTRONG | PITTSBURGH , PA | Multiple | Z101209 | This project will patch the existing concrete on State Route 28 and overlay it with asphalt from the overpass at Iron Bridge Road to the overpass at State Route 128, in Armstrong County South Buffalo | Pavement Improvement | 2009-05-27 | 2009-05-27 | 2010-01-26 | 2009-10-28 | 5581694.05 | 9.376
10459 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ARMSTRONG |  | 03 | Z101219 | This project will extend the life of two bridges and improve safety by replacing the existing deteriorated decks on two State Route 422 bridges that pass over State Route 28 in Armstrong County's East | Bridge Improvement | 2009-07-17 | 2009-08-17 | 2010-12-09 | 2010-09-10 | 4771814.7 | 2.417
10460 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ARMSTRONG |  | 12 | Z101220 | This is a Transportation Enhancement project that consists of a tar and chip widening of approximately 1/2 mile of the existing trail, construction of about two miles of new trail, and construction of | Transportation Enhancements | 2009-08-11 | 2009-08-11 | 2010-01-25 | 2009-10-27 | 667947.7 | 0.000
10461 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUTLER |  | 03 | Z102224 | This project will extend the service life of one bridge by patching the deck/joints and overlaying the deck with a latex modified concrete surface. The bridge is on State Route 528 in Butler County ap | Bridge Improvement | 2009-04-27 | 2009-04-27 | 2009-10-04 | 2009-07-06 | 415810.45 | 0.058
10462 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUTLER |  | Multiple | Z102225 | This project will extend the life of four bridges in Butler County with preservation activities, including, shear key replacement, concrete beam repair and placement of concrete composite deck on Stat | Bridge Improvement | 2009-04-27 | 2009-05-04 | 2009-12-16 | 2009-09-17 | 729884.37 | 0.348
10463 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUTLER |  | 04 | Z102226 | This project will replace the existing bridge with a new two-lane six span multi-girder steel bridge on State Route 3027 in Butler County, Jackson Township. | Bridge Replacement | 2009-06-08 | 2009-06-08 | 2010-09-08 | 2010-06-10 | 5473500 | 0.287
10464 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUTLER |  | 03 | Z102229 | This project will extend the life of the roadway by replacing the surface course on State Route 422 in Butler County from the SR 422/T439 Whipporwill Road intersection to approximately 500 feet east o | Pavement Improvement | 2009-07-13 | 2009-07-27 | 2010-01-17 | 2009-10-19 | 1410518.13 | 3.915
10465 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BUTLER |  | 03 | Z102233 | This project will replace the bridge deck on I-79 in Worth Township in Butler County and replace the bridge decks on two structures over Interstate 79, with one being State Route 4007 and the other Pa | Bridge Improvement | 2009-08-03 | 2009-08-31 | 2011-03-08 | 2010-12-08 | 3204989 | 0.085
10466 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLARION |  | 05 | Z103194 | This project will extend the service life of two bridges by replacing the decks. These are the bridges that carry State Route 68 over interstate 80 in Clarion County. The project will replace the d | Bridge Improvement | 2009-05-18 | 2009-07-20 | 2011-02-22 | 2010-11-24 | 5929371 | 0.870
10467 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLARION |  | 05 | Z103196 | Bridge preservation activities, including, shear key replacement, concrete beam repair, placement of concrete composite deck and other miscellaneous construction for State routes 66(#1), 66(#2), 2007( | Bridge Improvement | 2009-05-04 | 2009-05-04 | 2009-10-20 | 2009-07-22 | 750174.62 | 0.176
10468 | Completed | C250 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLARION |  | 05 | Z103200 | This project will replace an existing two lane single span structure with a two lane single span prestressed spread box beam bridge with minimal approach work on state route 28 in Clarion County Redba | Bridge Replacement | 2009-07-21 | 2009-10-19 | 2011-08-25 | 2011-05-27 | 1943009 | 0.270
10469 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | CLARION |  | 05 | Z103201 | This project will increase Americans with Disabilities Act facilities by building ADA compliant curb ramps on State Route 322 in Clarion Borough, Clarion County from approximately the First Avenue int | Transportation Enhancements | 2009-12-01 | 2010-03-26 | 2011-02-14 | 2010-11-16 | 717819 | 0.842
10470 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | INDIANA |  | 09 | Z104234 | This project will extend the service life of the roadway by patching the existing concrete pavement and overlaying it with asphalt. The project is on State Route 119 in Indiana County from the SR 56/S | Pavement Improvement | 2009-06-08 | 2009-07-01 | 2010-06-21 | 2010-03-23 | 1149940.41 | 2.272
10471 | Completed | C250,C200 | Highway Infrastructure Investment Grant | PENNSYLVANIA | INDIANA |  | 12 | Z104235 | This project will extend the service life of two bridges by replacing their decks and repairing the piers. The bridges are on eastbound and westbound State Route 422 at the Chestnut Ridge Road overpas | Bridge Improvement | 2009-07-20 | 2009-08-04 | 2011-08-09 | 2011-05-11 | 3343338 | 0.378
10472 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | INDIANA |  | 09 | Z104236 | This project will extend the service life of the existing concrete pavement by performing slab stabilization, full depth slab patching, dowel bar retrofits, crack and joint sealing and microsurfacing. | Pavement Improvement | 2009-09-18 | 2009-09-24 | 2011-01-21 | 2010-10-23 | 4445241 | 7.014
10473 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | INDIANA |  | 12 | Z104241 | This project is to replace the deteriorating bridge carrying PA 403 (Clymer Bridge) over Dixon Run and Two Lick Creek in Clymer Borough in Indiana County. | Bridge Replacement | 2010-01-04 | 2010-01-27 | 2012-02-21 | 2011-11-23 | 5435892 | 0.379
10474 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | INDIANA |  | 09 | Z104242 | This project will make the bridge last longer by rehabilitating the deteriorating portions of the Heshbon Bridgebridge carrying Yellow Creek Park Road (PA 259) over Blacklick Creek in West Wheatfield | Bridge Improvement | 2010-01-28 | 2010-04-01 | 2011-09-01 | 2011-06-03 | 1526197 | 0.030
10475 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | JEFFERSON |  | 05 | Z105182 | This project will extend the service life of one bridge by performing preventative maintenance activities such as shear key replacement, concrete beam repair and the placement of concrete composite de | Bridge Improvement | 2009-05-18 | 2009-06-24 | 2010-01-04 | 2009-10-06 | 627262.1 | 0.045
10476 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | JEFFERSON |  | 05 | Z105183 | This project will replace the superstructure (bridge beams and deck) on a one Span Steel Multi-Girder Structure. The structure is on State Route 2023 (Knoxdale Road) in Jefferson County approximately | Bridge Improvement | 2009-05-18 | 2009-06-01 | 2010-02-02 | 2009-11-04 | 1048484.85 | 0.095
10477 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | JEFFERSON |  | 05 | Z105185 | This project will extend the service life of State Route 36 in Punxsutawney Borough by performing activities such as leveling, Superpave overlay, transverse joint repair, guiderail and ADA ramp upgrad | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-02-03 | 2009-11-05 | 1752109.89 | 5.633
10478 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | JEFFERSON |  | 05 | Z105187 | This project will construct ADA compliant curb ramps along State Route 28 in Brockway Borough from approximately the SR 28/Second Avenue intersection to approximately the SR 28/SR 219 intersection. | Transportation Enhancements | 2009-10-13 | 2010-04-13 | 2011-11-09 | 2011-08-11 | 469000 | 1.159
10479 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | JEFFERSON |  | 05 | Z105188 | This project will extend the service life of the existing roadway by milling the surface course and replacing it with a bituminous overlay. This project is on State Route 436 in Punxsutawney Borough | Pavement Improvement | 2009-09-22 | 2010-04-05 | 2010-10-20 | 2010-07-22 | 726770.99 | 1.792
10480 | Completed | C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ALLEGHENY | PITTSBURGH , PA | 18 | Z111300 | The project involves reconstructing the ramp pavement, eliminating 2 ramps, and installing new signals and signs in Robinson and North Fayette Townships. It will also construct new asphalt pavement al | Pavement Improvement | 2009-06-01 | 2009-06-08 | 2011-08-23 | 2011-05-25 | 9620000 | 1.650
10481 | Underway | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ALLEGHENY | PITTSBURGH , PA | 14 | Z111606 | This project involves relocating a railroad, moving a pier, building a few retaining walls to prepare for the next project phase which will widen Route 28 from Troy Hill to Milvale in the City of Pitt | Other | 2009-11-02 | 2009-11-02 | 2012-06-09 |  | 23150000 | 4.112
10482 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ALLEGHENY | PITTSBURGH , PA | 14 | Z111624 | The project will fix or repair various tunnel components that are worn out or deteriorated of the tunnel carrying State Route 3069 from the Liberty Bridge over the Monongahela River to State Route 51 | Pavement Improvement | 2009-09-21 | 2009-10-01 | 2011-04-17 | 2011-01-17 | 12526662 | 2.252
10483 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ALLEGHENY | PITTSBURGH , PA | 14 | Z111625 | The project will replace the bridge deck surfaces on the Ft. Duquesne Bridge in City of Pittsburgh | Bridge Improvement | 2009-07-07 | 2009-07-07 | 2012-02-21 | 2011-11-23 | 26190521 | 2.265
10484 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ALLEGHENY | PITTSBURGH , PA | 04 | Z111640 | The project will construct a new pavement surface along the entire route. | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2011-12-08 | 2011-09-09 | 845658 | 5.728
10485 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ALLEGHENY | PITTSBURGH , PA | Multiple | Z111659 | This project will make the bridge last longer by rehabilitating the deteriorating portions of the bridge carrying California Avenue (SR 7301) over Jacks Run in the City of Pittsburgh in Allegheny Coun | Bridge Improvement | 2010-02-12 | 2010-02-12 | 2012-03-13 | 2011-12-14 | 9127210.05
10486 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ALLEGHENY | PITTSBURGH , PA | 14 | Z111660 | This project in Allegheny County will make pedestrians safer by replacing deteriorating sidewalks and curbing, installing four handicap ramps to access the sidewalks, installing four street lights wit | Transportation Enhancements | 2010-05-18 | 2010-06-03 | 2011-01-10 | 2010-10-12 | 328450
10487 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | ALLEGHENY | PITTSBURGH , PA | 14 | Z111681 | This project in the Liberty Tunnel is to repair structural concrete and the ventilation shafts of the tunnels , replace fluorescent lighting system and switchgear, upgrade various safety systems, rel | Safety/Traffic Management | 2010-08-23 | 2010-09-07 | 2012-01-05 | 2011-10-07 | 8865836 | 3.712
10488 | Completed | C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | BEAVER | PITTSBURGH , PA | 04 | Z112213 | The project will repair steel members, paint the bridge, and replace expansion joints on the Rochester Bridge over Beaver River in Rochester and Bridgewater Boroughs | Bridge Improvement | 2009-05-18 | 2009-05-18 | 2011-09-05 | 2011-06-07 | 12451747 | 0.329
10489 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LAWRENCE |  | 04 | Z114210 | The project will upgrade the interchange by adding a lane on SR60 southbound, installing new signs and sign structures, and modifying ramps at various interchanges to meet standards in preparing for t | Pavement Improvement | 2009-11-16 | 2010-01-20 | 2011-03-10 | 2010-12-10 | 10450000 | 15.802
10490 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LAWRENCE |  | 04 | Z114220 | The project will construct a new asphalt riding surface on US Route 422 (Ben Franklin Highway) from Pine Glen Road to Zoccoli Road in Mahoning and Pulaski Townships | Pavement Improvement | 2009-06-22 | 2009-06-23 | 2010-01-28 | 2009-10-30 | 2574486.13 | 4.392
10491 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LAWRENCE |  | 04 | Z114221 | The project will replace the deck and provide other miscellaneous repairs of the State Route 2004 (Grove Street) bridge over Neshannock Creek in City of New Castle. | Bridge Improvement | 2009-06-30 | 2009-08-10 | 2010-10-07 | 2010-07-09 | 3342447 | 0.149
10492 | Completed | C220,C240,C230 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LAWRENCE | PITTSBURGH , PA | 04 | Z114225 | This Lawrence County project will make the area more esthetic and pedestrians safer by constructing concrete curbs, sidewalks, pedestrian lighting, landscaping, and adding street furniture. It is loca | Transportation Enhancements | 2010-02-12 | 2010-04-08 | 2011-03-28 | 2010-12-28 | 542940
10493 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | LAWRENCE |  | 04 | Z114227 | This project will make the roadway last longer and the ride smoother by patching and overlaying the deteriorating pavement on US 422 from Cascade Street (SR 2004) to Ben Franklin Highway (Butler Count | Pavement Improvement | 2010-01-28 | 2010-04-05 | 2011-01-14 | 2010-10-16 | 8700988 | 10.266
10494 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FAYETTE | UNIONTOWN-CONNELLSVILLE | Multiple | Z121001 | This project includes the replacement of bridge strip seals, bridge beam repair and minor concrete bridge deck repair for 31 bridges throughout Fayette, Greene, Washington and Westmoreland Counties. T | Bridge Improvement | 2009-05-07 | 2009-07-08 | 2010-09-15 | 2010-06-17 | 1487824 | 1.462
10495 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FAYETTE |  | Multiple | Z121002 | This project is the full replacement of a structurally deficient two span bridge carrying State Route 3006 over York Run. The roadway rehabilitation will consist of bridge approach slabs, drainage enh | Bridge Replacement | 2009-07-20 | 2011-03-28 | 2012-01-19 | 2011-10-21 | 1531676 | 0.170
10496 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FAYETTE |  | 12 | Z121003 | This project is the full replacement of two structurally deficient bridges carrying State Route 1054 over Trout Run. The roadway rehabilitation will consist of bridge approach slabs, drainage enhancem | Bridge Replacement | 2009-07-20 | 2009-07-21 | 2011-10-30 |  | 1364102 | 0.010
10497 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FAYETTE | UNIONTOWN-CONNELLSVILLE | 12 | Z121004 | This project includes the full bridge replacement of SR 1039 over Dickerson Run in Dunbar Township, Fayette County. | Bridge Replacement | 2009-07-09 | 2009-08-17 | 2012-02-23 | 2011-11-25 | 844081 | 0.004
10498 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FAYETTE | UNIONTOWN-CONNELLSVILLE | Multiple | Z121005 | This project consists of concrete pavement overlay to 2.19 miles of SR 0119 from Penn State Fayette to Pechin Road in North Union and Dunbar Townships. This project includes existing pavement milling, | Pavement Improvement | 2009-08-06 | 2010-01-01 | 2011-10-20 | 2011-07-22 | 4285933 | 6.214
10499 | Completed | C200,C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FAYETTE | UNIONTOWN-CONNELLSVILLE | 12 | Z121006 | This Fayette County project will make the roadway last longer and ride smoother by overlaying the deteriorating pavement on US 119 from Penn State Fayette to the Connellsville Street exit in North Uni | Pavement Improvement | 2010-02-25 | 2010-03-08 | 2010-11-29 | 2010-08-31 | 2599522.21 | 8.011
10500 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | FAYETTE |  | 12 | Z121008 | This Fayette County project will make the roadway last longer and the ride smoother by overlaying the deteiorating pavement on PA 51 from Waltersburg Bridge to Smock Road (SR 4016) in Franklin and Men | Pavement Improvement | 2010-02-26 | 2010-03-22 | 2010-09-02 | 2010-06-04 | 1139993.17 | 8.902
10501 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | GREENE |  | 12 | Z122001 | This project is the full replacement of a structurally deficient bridge carrying State Route 0018 over Browns Creek in Franklin Township, Greene County. The roadway rehabilitation will consist of brid | Bridge Replacement | 2009-10-02 | 2009-10-02 | 2011-12-14 |  | 2110953 | 0.018
10502 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | GREENE |  | 12 | Z122002 | This project is the full replacement of a structurally deficient bridge carrying State Route 0018 over a Branch of Browns Run in Morris Township, Greene County. The roadway rehabilitation will consist | Bridge Replacement | 2009-08-07 | 2009-08-17 | 2011-12-10 |  | 1114156 | 0.006
10503 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | GREENE |  | 12 | Z122003 | This project is the full replacement of a structurally deficient bridge carrying State Route 0018 over Garner's Run in Washington Township, Greene County. The roadway rehabilitation will consist of br | Bridge Replacement | 2009-08-07 | 2009-08-17 | 2011-04-20 | 2011-01-20 | 851172 | 0.004
10504 | Completed | C220 | Highway Infrastructure Investment Grant | PENNSYLVANIA | GREENE |  | 12 | Z122004 | This is a safety improvement project that will upgrade curb ramps to current standards in the Borough of Waynesburg and Franklin Township, Greene County. | Transportation Enhancements | 2009-07-31 | 2009-09-15 | 2011-07-31 | 2011-05-02 | 1607593 | 3.900
10505 | Underway | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WASHINGTON |  | 18 | Z124001 | This project is the full replacement of the Pattersons Mill Bridge over the North Fork of Cross Creek on SR 4029 in Cross Creek Township, Washington County. | Bridge Replacement | 2009-07-24 | 2009-08-05 | 2011-11-25 |  | 1021520 | 0.150
10506 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WASHINGTON |  | 18 | Z124002 | This project consists of pavement preservation and other miscellaneous construction for State Route 0019, in Washington County, North Strabane Township from approximately Conklin Rd. (T-639) to approx | Pavement Improvement | 2009-07-28 | 2009-08-17 | 2010-01-20 | 2009-10-22 | 765630.22 | 3.126
10507 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WASHINGTON | PITTSBURGH , PA | Multiple | Z124003 | This project includes repairing the deteriorating concrete roadway by concrete patches on Interstate 79 from Canonsburg to the Allegheny County Line in Washington County | Pavement Improvement | 2009-10-21 | 2009-10-21 | 2011-11-28 | 2011-08-30 | 15594320 | 14.218
10508 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WASHINGTON | UNIONTOWN-CONNELLSVILLE | 12 | Z124006 | This project is to repair the deteriorating portions of the bridge carrying Bridge Boulevard on SR 2067 over the Monogalhlela River in West Brownsville Bourough in Fayette and Washington counties . Br | Bridge Improvement | 2010-04-07 | 2010-04-26 | 2011-08-18 | 2011-05-20 | 1530560 | 0.199
10509 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND | PITTSBURGH , PA | Multiple | Z125001 | This project will consist of existing pavement milling, pavement resurfacing, installing concrete barrier in the median, adding left turn lanes at the following intersections: SR 30/ Monastery Dr (T-7 | Pavement Improvement | 2009-05-07 | 2009-05-20 | 2010-03-15 | 2009-12-15 | 2210657.16 | 4.005
10510 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND | PITTSBURGH , PA | 18 | Z125002 | This project consists of existing pavement milling, bituminous pavement overlay, minor drainage improvements, new guide rail, bridge approach slabs, traffic signal improvements for State Route 0030, i | Pavement Improvement | 2009-07-30 | 2009-08-23 | 2010-09-20 | 2010-06-22 | 2743610 | 5.434
10511 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND | MONESSEN | 12 | Z125003 | This project consists of steel repairs, bridge beam painting, and concrete pier repairs for State Route over Interstate 70, in Westmoreland County, Rostraver Township. These upgrades will extend the l | Bridge Improvement | 2009-07-01 | 2009-08-22 | 2010-01-19 | 2009-10-21 | 799043.66 | 0.029
10512 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND |  | 12 | Z125004 | This project is the full bridge replacement of SR 1006 (Moon's Bridge) over a Tubmill Run in Fairfield Township, Westmoreland County. | Bridge Replacement | 2009-07-02 | 2009-07-20 | 2012-03-08 | 2011-12-09 | 719905 | 0.008
10513 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND | PITTSBURGH , PA | 18 | Z125005 | This project will consist of a truss bridge rehabilitation and concrete bridge deck rehabilitation for State Route 993 (Larimer Bridge) over Brush Creek, in Westmoreland County, North Huntingdon Towns | Bridge Improvement | 2009-08-04 | 2010-03-22 | 2011-03-06 | 2010-12-06 | 2372698 | 0.028
10514 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND |  | 12 | Z125006 | This project consists of the full replacement of the existing one span concrete bridge of State Route 201 over Pollock Run in Rostraver Township, Westmoreland County. The structurally deficient bridge | Bridge Replacement | 2009-07-17 | 2009-07-27 | 2010-09-15 | 2010-06-17 | 751002.13 | 0.005
10515 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND | PITTSBURGH , PA | 18 | Z125007 | This project consists of painting the ends of the bridge beams at expansion joints, repairing bridge pier columns and caps at various locations, jacking and resetting of expansion bearings at piers 3 | Bridge Improvement | 2009-07-13 | 2009-07-20 | 2010-08-16 | 2010-05-18 | 1196766.74 | 0.175
10516 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND | MONESSEN | 12 | Z125008 | This project includes bridge abutment upgrades, spot painting, pier protection, and new bridge lighting for State Route 981 (Smithton Lo-Level Bridge), in Westmoreland County, Smithton Borough, Rostra | Bridge Improvement | 2009-07-13 | 2009-07-20 | 2010-07-28 | 2010-04-29 | 665349 | 0.136
10517 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND | MONESSEN | 12 | Z125009 | This project includes the enhancing several traffic signalized intersections. The work includes upgrading vehicular and pedestrian signal heads, replacing existing detection sensors, amplifiers, contr | Safety/Traffic Management | 2009-07-29 | 2009-08-24 | 2010-07-06 | 2010-04-07 | 193460.02 | 1.133
10518 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND | PITTSBURGH , PA | 12 | Z125010 | This project will make the bridge last longer by replacing the deteriorating portons of the bridge carrying PA 136 over the Youghiogheny River in West Newton Borough in Westmoreland County. | Bridge Improvement | 2010-02-18 | 2010-04-27 | 2010-12-16 | 2010-09-17 | 1385535 | 0.133
10519 | Completed | C240 | Highway Infrastructure Investment Grant | PENNSYLVANIA | WESTMORELAND | PITTSBURGH , PA | Multiple | Z125011 | This Westmoreland County project will make the roadway last longer and the ride smoother by overlaying the deteriorating pavement on US 30 from US 119 to Georges Station Road in Hempfield and Unity T | Pavement Improvement | 2010-02-22 | 2011-03-07 | 2012-04-05 | 2012-01-06 | 5430982 | 9.987
10520 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | 0001104 | This project includes excavating planting beds, placing loam and installing new planting material in select locations in the U.S. Route 1 median between Mooresfield Road and the Oliver Stedman Governm | Pavement Improvement | 2009-03-03 | 2009-06-15 | 2010-11-30 | 2010-11-23 | 176981.9 | 6.837
10521 | Completed | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | Multiple | 0010011 | This project involves replacement of all signage on Route 10 from Park Avenue/Route 12 in Cranston to I-95 in Providence (5 miles). | Safety/Traffic Management | 2009-05-20 | 2009-10-19 | 2010-09-22 | 2011-04-15 | 3427205.41 | 9.953
10522 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | 0043002 | This project will rehabilitate both Wyoming Bridges in Hopkinton, which carry Bridge Street over the Wood River, which are presently closed to traffic due to structural deterioration. | Bridge Replacement | 2009-09-17 | 2010-05-04 | 2011-09-23 | 2011-06-28 | 2908062.11 | 0.033
10523 | Completed | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 01 | 0146020 | This project will resurface Route 146 in Lincoln, from the Route 116 interchange to area of Sherman Avenue and Old Louisquisset Pike/Route 246 interchange, and will include guardrail replacement, join | Pavement Improvement | 2009-09-22 | 2009-04-27 | 2011-07-01 | 2011-07-31 | 9893503.23 | 1.150
10524 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | 0481001 | This project will rehabilitate two bridges at the Dillons Corner Rotary in Narragansett. Work to consist of superstructure replacement of Dillions Corner Bridge (two structures), which carries Route 1 | Bridge Improvement | 2009-06-30 | 2009-09-28 | 2011-05-21 | 2011-05-23 | 8152543.05 | 0.099
10525 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | 0800003 | This project will fund continued long-term maintenance on the Jamestown-Verrazzano Bridge, which carries Route 138 over the West Passage of Narragansett Bay. | Bridge Improvement | 2009-05-26 | 2009-09-14 | 2010-09-24 | 2010-11-19 | 1050959.5 | 1.400
10526 | Completed | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 01 | 0882002 | This project will rehabilitate Industrial Drive Bridge, which carries Industrial Drive over the Moshassuck River in Providence, including sidewalk repairs and resurfacing with new pavement. | Bridge Improvement | 2009-06-09 | 2010-03-08 | 2011-05-15 | 2011-05-23 | 2459263.23 | 0.031
10527 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | 0953108 | This project is the first phase of a 25-mile resurfacing project of I-95 from Connecticut line to Exit 8 in Warwick. Stimulus funds will pay for first 7.6 miles from the State line to Exit 3 (Route 13 | Pavement Improvement | 2009-04-15 | 2009-07-13 | 2009-12-09 | 2009-12-07 | 7901550 | 15.059
10528 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | KENT |  | 02 | 2955108 | This project will removal and replace light poles and electrical systems for overhead lighting on I-295 at Exits 1, 2, 4 and 5 in Warwick, Cranston and Johnston. Contract also includes additional traf | Safety/Traffic Management | 2009-03-16 | 2009-07-12 | 2010-11-04 | 2010-11-02 | 3865243.39 | 11.900
10529 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | 4444072 | This project involves the application of striping on State roadways in Burrillville, Central Falls, Cumberland, Glocester, Lincoln, North Providence, North Smithfield, Pawtucket, Smithfield and Woonso | Safety/Traffic Management | 2009-03-03 | 2009-05-10 | 2010-11-30 | 2010-11-30 | 1811221.25
10530 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | 4444073 | This project involves the application of striping on State roadways in Barrington, Bristol, East Providence, Little Compton, Middletown, Newport, Portsmouth, Providence, Tiverton and Warren. | Safety/Traffic Management | 2009-03-03 | 2009-05-17 | 2010-11-30 | 2010-11-30 | 1695755.5
10531 | Underway | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | 4444078 | Application of striping on State roadways in Barrington, Bristol, east Providence, Little Compton, Middletown, Newport, Portsmouth, Providence, Tiverton and Warren. | Safety/Traffic Management | 2010-09-22 | 2011-06-07 | 2012-11-15 |  | 1683084.82
10532 | Underway | C240,C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) |  | 4444079 | This project involves the application of striping on State roadways in Burrillville, Central Falls, Cumberland, Glocester, Lincoln, North Providence, North Smithfield, Pawtucket, Smithfield and Woonso | Safety/Traffic Management | 2010-09-22 | 2011-06-28 | 2012-11-15 |  | 1741677.58
10533 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | 8888180 | This enhancement project will improve the Manton Avenue streetscape in Providence, from Delaine Street to Sisson Street, and will include new sidewalks, crosswalks, street trees and street lighting (0 | Safety/Traffic Management | 2009-03-17 | 2009-08-01 | 2010-07-15 | 2010-08-30 | 175547.74 | 0.800
10534 | Completed | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) |  | 8888181 | This statewide maintenance contract which involves signal repair and minor resurfacing as needed at roughly 60 different intersections throughout the state | Safety/Traffic Management | 2009-06-02 | 2009-09-21 | 2010-05-18 | 2010-05-13 | 1395448.96 | 0.000
10535 | Completed | C240,C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) |  | 8888182 | This project will make various traffic signal improvements including the installation of new signals, signal modifications, and island modifications in Barrington, Burrillville, Foster, Johnston, Nort | Safety/Traffic Management | 2009-06-03 | 2009-10-19 | 2010-08-18 | 2010-07-16 | 1038050.79 | 0.000
10536 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | 8888183 | This project will make various traffic signal improvements including the installation of new signals, signal modifications, and island modifications in Coventry, East Greenwich, Exeter, North Kingstow | Safety/Traffic Management | 2009-09-09 | 2010-03-22 | 2010-10-31 | 2011-02-21 | 696968.88 | 0.000
10537 | Underway | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | 8888185 | Statewide maintenance contract which involves signal repair and minor resurfacing as needed at different intersections around the State. | Safety/Traffic Management | 2010-09-22 |  | 2012-11-16 |  | 1015438.31 | 0.000
10538 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | 9999071 | The project involves the replacement and repair of rusted, damaged and/or substandard guardrail throughout the state to improve traffic safety. | Safety/Traffic Management | 2009-03-09 | 2009-05-10 | 2011-03-31 | 2011-07-15 | 848648.82 | 1.000
10539 | Completed | C250,C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | A951001 | This project will replace the Chestnut Hill Road Bridge which carries Chestnut Hill Road over the spillway that flows from the Sayles and Smith Reservoir to the Chepachet River in Glocester. The proje | Bridge Improvement | 2010-02-08 | 2010-06-29 | 2011-09-09 | 2011-11-05 | 1467015.08 | 1.000
10540 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | NEWPORT |  | 01 | AWDA016 | This project will install new sidewalks and curbing on Bristol Ferry Road in Portsmouth, from West Main Road/Route 114 to Boyd's Lane, and will Include intersection improvements and new traffic signal | Pavement Improvement | 2009-03-04 | 2009-05-18 | 2009-11-12 | 2011-11-02 | 1842374.39 | 1.225
10541 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | KENT |  | 02 | AWDA019 | This project includes installation of new sidewalks and curbing in West Warwick on Legion Way, from Main Street to Providence Street, and on Providence Street, from Legion Way to East Main Street/Rout | Pavement Improvement | 2009-03-16 | 2009-07-06 | 2009-09-16 | 2011-10-21 | 881335.99 | 0.720
10542 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | BRISTOL |  | 01 | AWDA020 | This project includes installation of new sidewalks in Warren, including new curbs and curb ramps, on Child Street from Cutler Street to the Massachusetts State line. (2.2 miles). | Pavement Improvement | 2009-04-07 | 2009-10-26 | 2010-08-20 | 2010-10-28 | 2397793.22 | 1.803
10543 | Completed | C240,C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | Multiple | AWDA021 | This project will repair a number of sidewalks in downtown Providence along Washington Street, from Empire Street to Eddy Street, and on Westminster Street, from Empire Street to 100 feet east of Math | Transportation Enhancements | 2009-07-13 | 2010-08-01 | 2011-05-21 | 2011-11-30 | 1608516.44 | 0.430
10544 | Completed | C200 | Highway Infrastructure Investment Grant | RHODE ISLAND | BRISTOL |  | 01 | AWDA023 | This project will install new sidewalks and curbing in Warren along North Main Street from Park Street to Wood Street and on Child Street from Cutler Street to the East Bay Bike Path (0.2 miles). | Pavement Improvement | 2009-12-14 | 2010-04-09 | 2010-08-20 | 2010-09-14 | 761032.72 | 0.215
10545 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | DRNG015 | This project involves drainage improvements in the following communities: Hopkinton (Mechanic Street), Johnston (Winsor Avenue at Hawkins Pond), North Smithfield (Greenville Road), and West Greenwich | Pavement Improvement | 2009-03-03 | 2009-06-09 | 2009-09-15 | 2009-09-14 | 629575.69 | 0.000
10546 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | DRNG016 | This project will improve the drainage at the intersection of Ten Rod Road/Route 165 and Black Plain Rd in Exeter. | Pavement Improvement | 2009-03-04 | 2009-06-22 | 2009-09-15 | 2009-07-29 | 357661.62 | 0.000
10547 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | DRNG018 | This project involves various drainage improvements in the following communities: Cranston (Pippin Orchard Road), Lincoln (River Road/Route 126), and Narragansett (Bridgetown Road). | Pavement Improvement | 2009-05-20 | 2009-09-02 | 2009-10-30 | 2009-10-27 | 365324.14 | 0.000
10548 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | DRNG020 | This project involves various drainage improvements in the following communities: Providence (North Main St.); Tiverton (East Rd. & Crandall Rd.); West Greenwich (Escoheag Hill Road). These improveme | Pavement Improvement | 2010-02-17 | 2010-06-15 | 2010-10-30 | 2010-10-30 | 253958.12 | 0.590
10549 | Completed | C220 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | KSRR001 | This project will repair and replace certain portions if the lead coated copper roof of the Kingston Train Station located in the village of West Kingston. The public train sstation is of historical s | Transportation Enhancements | 2010-02-22 |  | 2010-10-01 | 2011-05-06 | 231380
10550 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | MAIN022 | This project involves the power washing of 65 of Rhode Island's 772 bridges to remove road salts, dirt and bird droppings. Includes bridges located in the following towns: Cumberland, East Providence, | Bridge Improvement | 2009-03-03 | 2010-08-23 | 2010-09-30 | 2011-11-02 | 554298.71 | 1.000
10551 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | MAIN023 | This project will power wash bridges to remove road salts, dirt and bird droppings. Includes bridges located in the following towns: Burrillville, Charlestown, Cranston, East Greenwich, Exeter, Hopkin | Bridge Improvement | 2009-03-03 | 2009-06-29 | 2009-11-30 | 2009-07-28 | 370518 | 1.000
10552 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 01 | R012009 | This project will result in the construction of a 400-foot rocky seawall along the shoreline of the Seekonk River in East Providence and will include salt marsh mitigation, installation of a stone dus | Other | 2009-03-04 | 2009-06-15 | 2009-11-10 | 2009-10-09 | 435169.72 | 1.000
10553 | Completed | C250,C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | RESF136 | This project will resurface Putnam Pike/Route 44 in Glocester, from Tourtellot Hill Road to the RIDOT Maintenance Facility, and will include drainage improvements and guardrail replacement (2 miles). | Pavement Improvement | 2009-03-06 | 2009-06-29 | 2009-11-04 | 2009-09-19 | 1492592.89 | 1.202
10554 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | RESF137 | This project will resurface Putnam Pike/Route 44 in Smithfield, from Austin Avenue to West Greenville Road, and will include replacement of sidewalks and curbing, drainage improvements, and a new sign | Pavement Improvement | 2009-04-07 | 2009-08-03 | 2010-05-07 | 2010-06-11 | 2232739.3 | 0.998
10555 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | NEWPORT |  | 01 | RESF138 | This project will resurface Main Road/Route 138 in Tiverton, from John Street to the Massachusetts State Line, and will include curbing, sidewalks, and drainage and guardrail improvements (2.3 miles). | Pavement Improvement | 2009-03-03 | 2009-03-23 | 2009-09-21 | 2009-09-21 | 3188236.02 | 2.375
10556 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 01 | RESF139 | This project will resurface Old Louisquisset Pike/Route 246 in Lincoln, from Breakneck Hill Road/Route 123 to Route 116/Route 146 interchange (2.3 miles). | Pavement Improvement | 2009-03-03 | 2009-05-18 | 2009-09-18 | 2009-12-04 | 1343539.58 | 2.318
10557 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | NEWPORT |  | 01 | RESF144 | This project will resurface West Main Road in Middletown, from Coddington Highway to John Kesson Lane, and will include curbing and sidewalk replacement, new signage and pavement markings, replacement | Pavement Improvement | 2009-03-06 | 2009-05-26 | 2010-10-06 | 2010-10-06 | 5611718.35 | 2.220
10558 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | RESF147 | This project involves the application of a rubberized asphalt chip seal on top of existing pavement to extend pavement service life. Roads will be sealed in Burrillville, Charlestown, Coventry, East G | Pavement Improvement | 2009-03-03 | 2009-06-03 | 2009-09-03 | 2009-08-07 | 2273697.78 | 21.800
10559 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | RESF148 | This project involves the cleaning and sealing of cracks and open joints in existing pavement with a hot applied rubberized asphalt sealant to extend the pavement service life of roads in the southern | Pavement Improvement | 2009-03-31 | 2009-07-13 | 2009-09-30 | 2011-03-28 | 257132.57 | 1.000
10560 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | RESF149 | This project involves cleaning and sealing cracks and open joints in existing pavement with a hot applied rubberized asphalt sealant to extend the pavement service life of the roads in the northern an | Pavement Improvement | 2009-03-31 | 2009-08-03 | 2009-09-30 | 2011-03-09 | 233897.27 | 1.000
10561 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | RESF151 | This project will resurface Kingstown Road/Route 138 in Richmond, from Beaver River Road to 660 feet west of Route 112 (2 miles). | Pavement Improvement | 2009-05-04 | 2009-07-22 | 2009-11-06 | 2009-11-06 | 2666073.89 | 2.221
10562 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | RESF153 | This project will resurface Ocean Road in Narragansett, from Narragansett Town Beach to Point Judith (3.7 miles), and Shore Road in Westerly, from Post Road to Ocean View Highway (4.5 miles). | Pavement Improvement | 2009-03-09 | 2009-05-18 | 2009-10-15 | 2011-10-27 | 2841428.08 | 8.730
10563 | Completed | C250,C200,C240,C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE | STATEWIDE | 02 | RESF157 | Resurfacing of Route 102 from Route 101 in Scituate to Old Plainfield in Foster (7.4), including drainage, guardrail improvements and safety improvements involving highway signs and pavement markings. | Pavement Improvement | 2010-02-22 | 2010-06-22 | 2010-10-15 | 2010-10-15 | 2366146.98 | 7.540
10564 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | RESF159 | This project will add chip seal overlay along Hartford Pike/Route 101, from the Connecticut State line to Route 94 in Foster, and from Anan Wade Road to Route 102 in Scituate (4 miles). | Pavement Improvement | 2009-05-14 | 2009-09-28 | 2009-10-30 | 2009-10-30 | 1690832.43 | 4.200
10565 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 01 | RESF160 | This project will resurface Nate Whipple Highway/Route 120 in Cumberland, from Diamond Hill Road/Route 114 to Mendon Road/Route 122, and will include new curbing, sidewalk, guardrail, minor drainage w | Pavement Improvement | 2009-03-06 | 2009-06-01 | 2009-11-30 | 2009-10-19 | 2841050 | 2.628
10566 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 01 | RESF166 | This project will resurface Nate Whipple Highway/Route 120, in Cumberland, from Diamond Hill Road/Route 114 to the Massachusetts State line, and will include new curbing, sidewalk, guardrail, minor dr | Pavement Improvement | 2009-06-09 | 2009-09-07 | 2010-08-20 | 2010-05-05 | 1970898.88 | 1.700
10567 | Completed | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 01 | RESF170 | This project will resurface Diamond Hill Road/Route 114 in Woonsocket, from Social Street to Bound Road, and will include curbing, sidewalks, guardrail, minor drainage improvements, and signal work (2 | Pavement Improvement | 2009-08-03 | 2009-10-26 | 2010-10-22 | 2010-10-17 | 4455588.1 | 2.160
10568 | Underway | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 01 | RESF174 | This project involves reconstruction of Hartford Avenue/Route 6A in Johnston, from the I-295 interchange to Atwood Avenue/Route 5, and will include curbing, sidewalks, widening a portion to provide a | Pavement Improvement | 2009-05-20 | 2009-09-28 | 2010-10-29 |  | 3838253.67 | 2.542
10569 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 01 | RESF175 | This project will resurface High Street/Diamond Hill Road/Route 114 in Woonsocket, from the Cumberland Public Library to Blackstone Street, and will include curbing, sidewalk, guardrail, minor drainag | Pavement Improvement | 2009-09-09 | 2010-04-17 | 2010-09-03 | 2010-09-03 | 1461894.6 | 1.021
10570 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | BRISTOL |  | 01 | RESF176 | Main St. (Rte. 114), installation of new curbing, sidewalks, minor drainage improvements and street tree preservation and replacement from Cherry St. to 160 feet south of Beach St. (0.3 miles). | Pavement Improvement | 2010-02-12 | 2010-07-23 | 2010-11-22 | 2010-11-12 | 684294 | 0.400
10571 | Completed | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 01 | RESF178 | This project involves the resurfacing of three streets in Providence, from West Exchange Street to Point Street, encompassing Dean Street, Cahir Street and Stewart Street. It will include upgraded sig | Pavement Improvement | 2009-05-20 | 2009-09-28 | 2010-12-14 | 2010-12-22 | 4189641.58 | 0.739
10572 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | RESF179 | This project will resurface Oak Street/Westerly Bradford Road/Route 91 in Westerly, from Route 3 to Westerly Maintenance Facility, and will include new sidewalks, minor drainage improvements, water li | Pavement Improvement | 2009-06-17 | 2009-09-28 | 2009-10-21 | 2011-08-19 | 3779852.1 | 1.304
10573 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | RESF181 | This project involves the reclamation and resurfacing of Route 14/Route 102/Plainfield Pike/Victory Highway from Briggs Rd. to Old Plainfield Pike in the Town of Foster. (1.2 miles). | Pavement Improvement | 2010-02-03 | 2010-07-05 | 2010-09-24 | 2012-01-13 | 626227.21 | 1.300
10574 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | RESF182 | This project involves the reclamation and resurfacing of Moosup Valley Road from 0.9 miles west of Route 14/Plainfield Pike to Cucumber Hill Road in the Town of Foster.(1.4 miles). | Pavement Improvement | 2010-02-03 | 2010-05-24 | 2010-09-24 | 2010-09-13 | 818457.6 | 1.400
10575 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | WASHINGTON |  | 02 | RESF183 | This project will resurface Route 91/Westerly Bradford Road/Bradford Road, including curbing, sidewalks, guardrail, minor drainage improvements, signage and pavement markings, from Westerly Maintenanc | Pavement Improvement | 2010-01-28 | 2010-05-24 | 2010-11-23 | 2010-12-20 | 2854508.85 | 4.450
10576 | Completed | C240,C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE | PROVIDENCE-PAWTUCKET-WARWICK (MA) | 01 | RESF185 | Resurfacing of Route 99/Woonsocket Industrial Highway, including curbing, minor drainage work, signage structures and minor bridge work from Route 146 to Route 122/Mendon Rd. (2.7 miles). | Pavement Improvement | 2010-02-12 | 2010-06-10 | 2011-04-21 | 2011-04-21 | 3419686.39 | 3.840
10577 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | NEWPORT |  | 01 | RESF188 | Resurfacing of Colebrook Road in the town of Little Compton including the replacement of drainage systems, from Long Highway to Route 179 (1.7 miles) | Pavement Improvement | 2010-02-08 | 2010-10-27 | 2011-08-16 | 2012-01-06 | 1777033.62 | 1.982
10578 | Completed | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) |  | RESF189 | This project involves the cleaning and sealing of cracks and open joints in existing pavement with a hot applied rubberized asphalt sealant to extend the pavement service life of roads in the southern | Pavement Improvement | 2010-09-22 | 2011-05-16 | 2011-08-31 | 2011-06-29 | 204319.04 | 1.000
10579 | Completed | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) |  | RESF190 | This project involves cleaning and sealing cracks and open joints in existing pavement with a hot applied rubberized asphalt sealant to extend the pavement service life of the roads in the northern an | Pavement Improvement | 2010-09-22 | 2011-05-16 | 2011-08-31 | 2011-06-20 | 204319.04 | 1.000
10580 | Underway | C230 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE | PROVIDENCE-PAWTUCKET-WARWICK (MA) |  | RESF191 | This project involves the application of a rubberized asphalt chip seal on top of existing pavement to extend pavement service life. | Pavement Improvement | 2010-09-22 | 2011-05-16 | 2012-05-15 |  | 1159840.78
10581 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | SDRP007 | This project involves the construction of a storm water treatment pond at the interchange of Route 6 on the Providence/Johnston line at the Killingly Street/Route 128 exit. | Other | 2009-03-03 | 2009-04-13 | 2009-10-16 | 2009-10-16 | 892119.46 | 1.000
10582 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | SDRP008 | This project will review approximately 60 out of 130 storm water drainage systems, ponds, catch basins, etc. that were previously upgraded to meet Federal Best Management Practices, in accordance with | Other | 2009-06-04 | 2010-06-22 | 2010-11-19 | 2010-09-29 | 421836.36 | 1.000
10583 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | SIGN015 | This project will replace signage along I-95 at Exits 6, 7 and 8 (West Greenwich, East Greenwich, West Warwick, and Warwick), Exit 12B (Warwick), Exists 16-18 (Cranston and Providence), and Exit 29 (P | Safety/Traffic Management | 2009-03-09 | 2009-07-16 | 2010-07-07 | 2011-05-27 | 3001224.46 | 15.003
10584 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | SIGN016 | This project will replace all road signage on Route 37 from Post Road/Route 1 in Warwick to Natick Avenue in Cranston (3.2 miles). | Safety/Traffic Management | 2009-03-09 | 2009-07-20 | 2010-08-26 | 2010-09-15 | 2691000 | 6.424
10585 | Underway | C490 | OJT/SS | RHODE ISLAND | STATEWIDE |  |  | SSRV002 | OJT Training Supportive Services- ARRA OJT/SS PRogram 2009. The purpose of this award is to establish partnerships to facilitate the referral of qualified individuals to increase the participation o | Other | 2009-07-16 | 2010-10-11 | 2012-10-10 |  | 350000
10586 | Completed | C220 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | 02 | TEA2060 | This enhancement project will improve the Manton Avenue streetscape in Providence, from Delaine Street to Sisson Street, and will include new sidewalks, crosswalks, street trees and street lighting (0 | Transportation Enhancements | 2009-03-17 | 2009-08-01 | 2010-12-01 | 2010-08-30 | 500000 | 0.770
10587 | Underway | C220 | Highway Infrastructure Investment Grant | RHODE ISLAND | PROVIDENCE |  | Multiple | TEAC090 | This project will improve the Westminster Street streetscape in Providence, from Service Road No. 7 to Olneyville Square/Manton Avenue/Plainfield Street, and will include sidewalks, crosswalks, bicycl | Transportation Enhancements | 2009-06-11 |  |  |  | 3381492 | 1.223
10588 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | TRMS009 | This project involves the installation of radar-based vehicle detectors, at the same location as existing traffic cameras, to collect data on traffic volume and speeds. The new detectors provide alert | Safety/Traffic Management | 2009-03-09 | 2009-06-07 | 2010-06-11 | 2010-01-05 | 463059.2
10589 | Completed | C240 | Highway Infrastructure Investment Grant | RHODE ISLAND | STATEWIDE |  |  | TRMS010 | This project involves the installation of radar-based vehicle detectors in several locations to collect data on traffic volume, speed, and vehicle classification used for annual reporting requirements | Safety/Traffic Management | 2009-03-03 | 2009-05-31 | 2010-06-16 | 2010-06-16 | 1013832.26
10590 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN |  | 03 | SP09001 | Resurfacing various road in Aiken County. | Pavement Improvement | 2010-01-25 | 2010-03-29 | 2010-10-31 | 2010-10-29 | 2634977.47
10591 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | KERSHAW |  | 05 | SP09002 | Resurfacing various roads in Kershaw County. | Pavement Improvement | 2010-02-04 | 2010-03-13 | 2010-07-31 | 2010-08-31 | 2360329.86
10592 | Completed | C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN | AUGUSTA (GA) | 03 | SP09003 | Resurfacing various roads in and around North August, in Aiken County SC. | Pavement Improvement | 2010-04-23 | 2010-07-06 | 2010-08-31 | 2010-08-31 | 1472994.63
10593 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | RICHLAND |  | 06 | SP09005 | Resurfacing various roads in Richland County. | Pavement Improvement | 2009-07-31 | 2009-07-29 | 2009-11-30 | 2010-01-28 | 2059601.66 | 2.420
10594 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ANDERSON |  | 03 | SP09014 | Resurfacing various roads in Anderson County. | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-04-30 | 2010-04-30 | 2890098.05
10595 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | MARION, FLORENCE |  | 06 | SP09028 | Resurfacing various roads in Florence and Marion Counties. | Pavement Improvement | 2009-06-26 | 2009-08-03 | 2010-06-30 | 2010-06-30 | 4315838.8
10596 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN, WILLIAMSBURG, HORRY |  | Multiple | SP09029 | Resurfacing various roads in Georgetown and Horry Counties. | Pavement Improvement | 2009-08-17 | 2009-08-31 | 2010-05-31 | 2010-06-02 | 6683570.43 | 3.360
10597 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | JASPER, BEAUFORT |  | 02 | SP09034 | Resurfacing various roads in Beaufort and Jasper Counties. | Pavement Improvement | 2010-03-29 | 2010-04-21 | 2010-08-31 | 2010-12-15 | 2111520.51 | 3.010
10598 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BERKELEY |  | 01 | SP09035 | Resurfacing various roads in Berkeley County. | Pavement Improvement | 2009-07-15 | 2009-08-10 | 2009-11-30 | 2009-11-16 | 1667853.44 | 2.500
10599 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BERKELEY, CHARLESTON |  | 01 | SP09036 | Resurfacing various roads in Charleston County. | Pavement Improvement | 2009-11-13 | 2010-01-13 | 2010-11-30 | 2010-12-15 | 2867171.49
10600 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SP09044 | Resurfacing various roads in Orangeburg County. | Pavement Improvement | 2010-02-02 | 2010-04-19 | 2010-08-31 | 2011-04-07 | 4483991.06
10601 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | KERSHAW |  | 05 | SP09048 | Resurfacing various roads in Kershaw County. | Pavement Improvement | 2009-07-17 | 2009-07-14 | 2009-11-30 | 2009-09-24 | 1071890.08 | 0.560
10602 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SUMTER, LEE |  | Multiple | SP09049 | Resurfacing various roads in Lee County. | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2010-05-31 | 2010-10-29 | 2469147.4
10603 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LEXINGTON |  | 02 | SP09050 | Resurfacing various roads in Lexington County. | Pavement Improvement | 2009-08-24 | 2009-08-26 | 2010-04-30 | 2010-04-30 | 3007381.17
10604 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENWOOD, LAURENS, ABBEVILLE |  | 03 | SP09053 | Resurfacing various roads in Abbeville, Greenwood, and Laurens Counties. | Pavement Improvement | 2009-06-09 | 2009-09-10 | 2010-05-31 | 2010-06-12 | 5698590.52
10605 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | EDGEFIELD, NEWBERRY, SALUDA, MCCORMICK |  | Multiple | SP09054 | Resurfacing various roads in Edgefield, McCormick, Newberry, and Saluda Counties. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-05-31 | 2010-05-31 | 4846344.09 | 9.920
10606 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENVILLE |  | 04 | SP09061 | Resurfacing various roads in Greenville County. | Pavement Improvement | 2009-07-24 | 2009-07-27 | 2010-04-30 | 2010-03-30 | 4314007.21
10607 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | OCONEE |  | 03 | SP09062 | Resurfacing various roads in Oconee County. | Pavement Improvement | 2009-06-19 | 2009-06-12 | 2009-11-30 | 2009-09-30 | 2102074.79
10608 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | PICKENS |  | 03 | SP09063 | Resurfacing various roads in Pickens County. | Pavement Improvement | 2009-07-10 | 2009-07-16 | 2010-04-30 | 2009-11-17 | 1980509
10609 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SPARTANBURG |  | 04 | SP09064 | Resurfacing various roads in Spartanburg County. | Pavement Improvement | 2009-11-19 | 2010-02-07 | 2010-11-30 | 2010-12-31 | 3771592.61
10610 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHEROKEE, UNION |  | Multiple | SP09065 | Resurfacing various roads in Cherokee and Union Counties. | Pavement Improvement | 2009-06-19 | 2009-07-20 | 2010-05-31 | 2010-05-31 | 1938522.1 | 5.470
10611 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHESTER |  | 05 | SP09066 | Resurfacing various roads in Chester County. | Pavement Improvement | 2009-06-19 | 2009-07-06 | 2010-04-30 | 2009-12-01 | 1099040.8
10612 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHESTERFIELD |  | 05 | SP09067 | Resurfacing various roads in Chesterfield County. | Pavement Improvement | 2009-07-10 | 2009-07-06 | 2009-11-30 | 2009-08-18 | 1375591.1
10613 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | FAIRFIELD |  | 05 | SP09068 | Resurfacing various roads in Fairfield County. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2009-11-30 | 2010-03-19 | 1479293.68
10614 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LANCASTER |  | 05 | SP09069 | Resurfacing various roads in Lancaster County. | Pavement Improvement | 2009-07-24 | 2009-07-27 | 2009-11-30 | 2009-12-01 | 1802638.38
10615 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | YORK |  | 05 | SP09071 | Resurfacing various roads in York County. | Pavement Improvement | 2009-07-24 | 2009-06-24 | 2009-11-30 | 2009-11-30 | 1482623.04
10616 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | DILLON, DARLINGTON, MARLBORO |  | Multiple | SP09072 | Resurfacing various roads in Darlington, Dillion, and Marlboro Counties. | Pavement Improvement | 2009-07-17 | 2009-09-03 | 2010-05-31 | 2010-04-30 | 2990108.81
10617 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BEAUFORT |  | 02 | SP09080 | Resurfacing various roads in Beaufort County. | Pavement Improvement | 2009-07-31 | 2009-08-14 | 2009-10-31 | 2009-10-31 | 1918198.06
10618 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHARLESTON |  | 06 | SP09082 | Resurfacing various roads in Charleston County. | Pavement Improvement | 2009-07-10 | 2009-08-12 | 2009-11-30 | 2009-11-30 | 2399142.42
10619 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | COLLETON |  | 06 | SP09083 | Resurface various roads in Colleton County. | Pavement Improvement | 2009-07-24 | 2009-10-15 | 2009-11-30 | 2009-11-30 | 1860677.35
10620 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | DORCHESTER |  | 01 | SP09084 | Resurfacing various roads in Dorchester County. | Pavement Improvement | 2009-07-24 | 2009-09-03 | 2009-11-30 | 2009-11-25 | 1571321.12
10621 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | JASPER |  | 02 | SP09085 | Resurfacing various roads in Jasper County. | Pavement Improvement | 2009-07-31 | 2009-08-18 | 2009-11-30 | 2009-11-16 | 1614083.61 | 2.420
10622 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BAMBERG, HAMPTON, ALLENDALE, BARNWELL |  | Multiple | SP09086 | Resurfacing various roads in Allendale, Bamberg, Barnwell, and Hampton Counties. | Pavement Improvement | 2009-06-09 | 2009-07-15 | 2009-11-30 | 2010-03-30 | 4128933.17
10623 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CLARENDON, ORANGEBURG, CALHOUN |  | Multiple | SP09089 | Resurfacing various roads in Calhoun, Clarendon, and Orangeburg Counties. | Pavement Improvement | 2009-06-19 | 2009-06-29 | 2010-05-31 | 2010-05-31 | 4265833.68
10624 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN |  | 02 | SP09093 | Resurfacing various roads in Aiken County. | Pavement Improvement | 2010-01-21 | 2010-04-13 | 2010-09-30 | 2008-09-08 | 2336735.13
10625 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | RICHLAND |  | 02 | SP09095 | Resurfacing various roads in Richland County. | Pavement Improvement | 2009-09-26 | 2010-01-20 | 2010-08-31 | 2010-08-31 | 1924617.01
10626 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LEXINGTON |  | 02 | SP09096 | Resurface various roads in Lexington County. | Pavement Improvement | 2010-01-25 | 2010-04-26 | 2010-09-30 | 2010-11-14 | 2762858.16
10627 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SUMTER, LEE |  | 05 | SP09098 | Resurfacing various roads in Lee County. | Pavement Improvement | 2010-04-01 | 2010-04-27 | 2010-08-31 | 2010-09-13 | 3773799.54
10628 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SPARTANBURG |  | 04 | SP09110 | Resurfacing various roads in Spartanburg County. | Pavement Improvement | 2010-01-20 | 2010-02-04 | 2011-04-30 |  | 6350459.55
10629 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHEROKEE |  | 05 | SP09111 | Resurfacing various roads in Cherokee County. | Pavement Improvement | 2009-11-23 | 2010-03-18 | 2010-06-30 | 2010-08-05 | 1971549.67
10630 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHESTER |  | 05 | SP09112 | Resurfacing various roads in Cherster County. | Pavement Improvement | 2009-11-12 | 2010-05-04 | 2010-08-17 | 2010-10-08 | 1421891.71 | 5.590
10631 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHESTERFIELD |  | 05 | SP09113 | Resurfacing various roads in Chesterfield County. | Pavement Improvement | 2009-12-01 | 2010-05-11 | 2010-08-31 | 2010-11-15 | 2714312.62 | 10.880
10632 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | FAIRFIELD |  | 05 | SP09114 | Resurfacing various roads in Greenville County. | Pavement Improvement | 2009-11-12 | 2010-06-15 | 2010-09-30 | 2010-11-15 | 1622393.52
10633 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LANCASTER |  | 05 | SP09115 | Resurfacing various roads in Lancaster County. | Pavement Improvement | 2010-02-02 | 2010-05-06 | 2010-07-31 | 2010-08-06 | 2210184.77
10634 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | DILLON, DARLINGTON, MARLBORO |  | 05 | SP09118 | Resurfacing various roads in Dillon, Darlington, and Marlboro Counties. | Pavement Improvement | 2010-01-06 | 2010-01-28 | 2011-05-31 |  | 5253043.62 | 8.820
10635 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN, MARION, HORRY |  | Multiple | SP09121 | Resurfacing various roads in Georgetown, Horry, Marion, and Williamsburg Counties | Pavement Improvement | 2010-04-28 | 2010-04-28 | 2010-11-30 | 2011-04-15 | 6996694.85 | 1.120
10636 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | WILLIAMSBURG, FLORENCE |  | 06 | SP09125 | Resurfacing various roads in Florence County. | Pavement Improvement | 2009-11-05 | 2009-12-28 | 2011-06-30 |  | 7428448.91 | 8.680
10637 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SP09132 | Resurfacing various roads in Allendale and Hampton Counties. | Pavement Improvement | 2010-02-03 | 2010-05-05 | 2010-08-31 | 2010-08-06 | 3280731.73 | 11.850
10638 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BARNWELL |  | 02 | SP09134 | Resurfacing various roads in Barnwell County. | Pavement Improvement | 2010-02-03 | 2010-03-24 | 2010-06-30 | 2010-06-30 | 1151703.26 | 3.760
10639 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CALHOUN |  | 02 | SP09135 | Resurfacing various roads in Calhoun County. | Pavement Improvement | 2010-02-02 | 2010-03-08 | 2010-07-31 | 2010-05-18 | 1138392.04 | 2.660
10640 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | RICHLAND |  | 06 | SP09143 | Resurfacing various roads in Richland County. | Pavement Improvement | 2009-06-19 | 2009-07-17 | 2009-11-30 | 2009-12-04 | 1879174.79
10641 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENWOOD, LAURENS, ABBEVILLE |  | 03 | SP09145 | Resurfacing various roads in Abbeville County. | Pavement Improvement | 2010-04-23 | 2010-06-14 | 2010-11-30 | 2011-01-30 | 3415707.88 | 4.710
10642 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | EDGEFIELD, NEWBERRY, SALUDA, MCCORMICK |  | Multiple | SP09146 | Resurfacing various roads in Edgefield, McCormick, Newberry, and Saluda Counties. | Pavement Improvement | 2010-04-23 | 2010-06-09 | 2010-09-30 | 2010-10-31 | 4406222.02 | 12.560
10643 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ANDERSON |  | 03 | SP09152 | Resurfacing various roads in Anderson County. | Pavement Improvement | 2010-02-18 | 2010-06-02 | 2010-08-31 | 2010-08-30 | 1962809.24
10644 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENVILLE |  | 04 | SP09153 | Resurfacing various roads in Greenville County. | Pavement Improvement | 2010-02-16 | 2010-02-26 | 2010-08-30 | 2010-09-16 | 2200000
10645 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | OCONEE, PICKENS |  | 03 | SP09154 | Resurfacing various roads in Oconee and Pickens Counties. | Pavement Improvement | 2009-10-26 | 2009-10-28 | 2010-09-30 | 2010-06-04 | 2150242.29
10646 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | UNION |  | 04 | SP09162 | Resurfacing various roads in Union County. | Pavement Improvement | 2009-11-12 | 2010-01-27 | 2010-07-31 | 2010-07-27 | 967546.8 | 3.610
10647 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | YORK |  | 05 | SP09163 | Resurfacing various roads in York County. | Pavement Improvement | 2009-11-27 | 2010-04-22 | 2010-11-30 | 2010-12-17 | 1552975.78 | 3.960
10648 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | COLLETON, DORCHESTER |  | 06 | SP09175 | Resurfacing various roads in Colleton County. | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2010-08-31 | 2011-01-20 | 2423396.86
10649 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPBR001 | Replacement of eight bridges on US 378 over the Little Pee Dee River and Maple Swamp areas of Marion and Horry Counties. | Bridge Replacement | 2009-07-10 | 2009-07-08 | 2011-10-31 |  | 21000000 | 7.200
10650 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LAURENS |  | 03 | SPBR002 | Replacement of bridge over Durbin Creek on Allen Bridge Road in Laurens County 14.8 miles west of Laurens. | Bridge Replacement | 2009-11-11 | 2009-11-18 | 2010-11-30 | 2010-11-26 | 1331973.78 | 0.100
10651 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | EDGEFIELD |  | 03 | SPBR003 | Replacement of bridge over Turkey Creek on Weaver Road in Edgefield County 3.1 miles west of Johnston SC, and replacement of bridge over Bartly Branch on Bland Baptist Road 2.5 miles north west of Joh | Bridge Replacement | 2009-09-23 | 2009-10-26 | 2010-07-31 | 2010-10-13 | 1691689.08 | 0.200
10652 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHARLESTON | CHARLESTON | 01 | SPBR005 | Replacement of bridge over Tidal Creek on Brickyard Road in Charleston County. | Bridge Replacement | 2009-07-24 | 2009-07-27 | 2010-04-30 | 2010-04-01 | 645119.21
10653 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | COLLETON |  | 06 | SPBR006 | Replacement of bridge over Caphen Swamp on Combahee Road near Walterboro, SC in Colleton County. | Bridge Replacement | 2009-11-30 | 2009-10-09 | 2010-03-10 | 2010-03-01 | 911654.86 | 0.499
10654 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | JASPER |  | 02 | SPBR007 | Replace bridge to Knowles Island in Jasper County. | Bridge Replacement | 2009-10-12 | 2009-10-12 | 2010-06-30 | 2010-06-28 | 1619971.75 | 0.040
10655 | Underway | C240,C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | YORK | STATEWIDE | 05 | SPBR008 | Replacement of bridge over Catawba River on Cherry Road 4.1 miles north of Rock Hill, SC in York County. | Bridge Replacement | 2010-03-11 | 2010-04-05 | 2012-11-30 |  | 11836210 | 1.230
10656 | Underway | C250,C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BAMBERG, ORANGEBURG |  | 06 | SPBR009 | Replacement of bridge and bridge approaches over the South Edisto River on Us 78 (Edwards Street) 4.0 miles west of Branchville near the Bamberg and Orangeburg County lines. | Bridge Replacement | 2010-04-28 | 2010-05-18 | 2012-08-31 |  | 10988741.56 | 1.310
10657 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | KERSHAW, LEE |  | Multiple | SPEH001 | Sidewalk repairs, replacement, and construction in various locations in Kershaw and Lee Counties. | Transportation Enhancements | 2009-10-12 | 2009-11-04 | 2010-06-30 | 2010-03-30 | 316356.3
10658 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LAURENS |  | 03 | SPEH002 | Repair, replace, construct sidewalks in various locations in Laurens County SC | Transportation Enhancements | 2010-04-23 | 2010-05-06 | 2010-08-31 | 2010-08-27 | 176569.16
10659 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LEXINGTON |  | 02 | SPEH003 | Sidewalk repairs, replacement, and construction in various locations in Lexington County. | Transportation Enhancements | 2009-11-16 | 2009-11-16 | 2010-07-31 | 2010-12-15 | 298476.49
10660 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | YORK |  | 05 | SPEH004 | Sidewalk repairs, replacement, and construction in various locations in York County | Transportation Enhancements | 2010-01-23 | 2010-03-19 | 2010-07-31 | 2010-08-24 | 478125.43
10661 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BERKELEY, DORCHESTER |  | 06 | SPEH005 | Construct, repair, replace ADA ramps in Berkeley and Dorchester Counties | Transportation Enhancements | 2010-06-25 | 2010-09-20 | 2010-11-30 | 2010-11-16 | 132401.74
10662 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | COLLETON, JASPER, BEAUFORT |  | 02 | SPEH006 | Construct, repair, replace ADA ramps in various locations in Baufort, Colleton, and Jasper Counties SC | Transportation Enhancements | 2010-06-25 | 2010-08-11 | 2010-12-15 | 2010-12-10 | 156369
10663 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | RICHLAND, LEXINGTON |  | 02 | SPEH007 | Sidewalk repairs, replacement, and construction in various locations in Richland County | Transportation Enhancements | 2010-01-18 | 2010-01-20 | 2010-12-31 | 2011-03-23 | 628243.5
10664 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHARLESTON |  | 01 | SPEH008 | Construct, repair, replace ADA ramps in various locations in Charleston County, SC | Transportation Enhancements | 2010-06-25 | 2010-07-19 | 2010-11-30 | 2010-11-18 | 258288.54
10665 | Underway | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LEXINGTON |  | 02 | SPEH009 | Repari, replace, construct various sidewalks in Richland County | Transportation Enhancements | 2011-02-07 | 2011-04-26 | 2011-05-31 |  | 169654.13
10666 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LEXINGTON |  | 02 | SPEH010 | Construct, repair, and replace side walks at various locations in Lexington County | Transportation Enhancements | 2010-08-02 | 2010-08-17 | 2010-09-30 | 2010-09-23 | 249901.94
10667 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SUMTER |  | 06 | SPEH011 | Sidewalk repairs, replacement, and construction in various locations in Sumter County | Transportation Enhancements | 2010-05-07 | 2010-05-12 | 2010-07-31 | 2011-02-28 | 224904.96
10668 | Underway | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LEXINGTON |  | 02 | SPEH012 | ARRA Sidewalk Projects in Lexington County | Transportation Enhancements | 2011-02-07 | 2011-05-02 | 2010-05-31 |  | 82503.36
10669 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ABBEVILLE |  | 03 | SPEH013 | Sidewalk repairs, replacement, and construction in various locations in Abbeville, Laurens, and Newberry Counties | Transportation Enhancements | 2010-05-05 | 2010-05-05 | 2010-06-30 | 2010-07-08 | 79595.53
10670 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENWOOD, EDGEFIELD |  | 03 | SPEH014 | Sidewalk repairs, replacement, and construction in various locations in Edgefield, Greenwood, and McCormick Counties | Transportation Enhancements | 2009-12-23 | 2010-01-18 | 2010-06-30 | 2010-06-25 | 450139.55
10671 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN |  | 02 | SPEH015 | Replace, repair, construct sidewalks in Aiken County | Transportation Enhancements | 2010-05-18 | 2010-06-29 | 2010-07-31 | 2010-07-28 | 110656.87
10672 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LAURENS |  | 03 | SPEH016 | Repair, replace, construct sidewalks at various locations in Laurens County, SC | Transportation Enhancements | 2010-03-29 | 2010-06-09 | 2010-09-30 | 2010-08-09 | 163899.99
10673 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | RICHLAND |  | 06 | SPEH017 | Repair, replace, construc various sidewalks in Richland County | Transportation Enhancements | 2010-10-13 | 2011-04-05 | 2011-05-31 | 2011-05-31 | 196560.33
10674 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENWOOD |  | 03 | SPEH018 | Construct, repair, and replace sidewalks at various locations in Greenwood County | Transportation Enhancements | 2010-05-14 | 2010-08-16 | 2010-09-30 | 2010-09-09 | 159103.45
10675 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENWOOD |  | 03 | SPEH019 | Repari, replace, construct various sidewalks in Greenwood County | Transportation Enhancements | 2011-01-24 | 2011-02-02 | 2011-04-30 | 2011-05-06 | 165209.82
10676 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENVILLE |  | 04 | SPEH020 | Sidewalk repairs, replacement, and construction in various locations in Greenville County | Transportation Enhancements | 2009-12-01 | 2010-01-04 | 2010-07-31 | 2010-07-31 | 493205.15
10677 | Underway | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENWOOD |  | 03 | SPEH021 | ARRA Sidewalk Projects in Greenwood County | Transportation Enhancements | 2011-02-07 | 2011-05-09 | 2011-07-31 |  | 15543.42
10678 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENVILLE |  | 04 | SPEH022 | Sidewalk repairs, replacement, and construction in various locations in Greenville County | Transportation Enhancements | 2010-06-03 | 2010-08-05 | 2010-09-30 | 2010-09-22 | 213408.4
10679 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | OCONEE, PICKENS |  | 03 | SPEH024 | Sidewalk repairs, replacement, and construction in various locations in Oconee and Pickens Counties | Transportation Enhancements | 2010-02-02 | 2010-02-10 | 2010-06-30 | 2010-03-31 | 401532.61
10680 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LAURENS |  | 03 | SPEH025 | ARRA Sidewalk Projects in Laurens County | Transportation Enhancements | 2011-03-01 | 2011-02-21 | 2011-05-31 | 2011-05-13 | 118621.2
10681 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SPARTANBURG |  | 04 | SPEH026 | Sidewalk repairs, replacement, and construction in various locations in Spartenburg County | Transportation Enhancements | 2010-03-23 | 2010-03-24 | 2010-06-30 | 2010-07-16 | 405793.54
10682 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | FAIRFIELD |  | 05 | SPEH027 | ARRA Sidewalk Projects in Fairfield County | Transportation Enhancements | 2010-11-10 | 2011-02-02 | 2011-05-31 | 2011-05-10 | 132743.62
10683 | Underway | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHEROKEE, UNION |  | Multiple | SPEH028 | Sidewalk repairs, replacement, and construction in various locations in Cherokee and Union Counties | Transportation Enhancements | 2010-03-31 | 2010-05-12 | 2011-10-31 |  | 277751.93
10684 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHESTER, FAIRFIELD |  | 05 | SPEH029 | Sidewalk repairs, replacement, and construction in various locations in Chester County | Transportation Enhancements | 2009-12-10 | 2010-01-04 | 2010-08-31 | 2010-08-31 | 402882.94
10685 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHESTERFIELD, LANCASTER |  | 05 | SPEH030 | Sidewalk repairs, replacement, and construction in various locations in Chesterfield County | Transportation Enhancements | 2009-11-19 | 2010-02-17 | 2010-07-31 | 2010-08-10 | 518595.74
10686 | Underway | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | YORK |  | 05 | SPEH031 | Repair, replace, construct various sidewalks in York County | Transportation Enhancements | 2010-10-25 | 2010-12-14 | 2011-06-30 |  | 360733.94
10687 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | DILLON, FLORENCE |  | Multiple | SPEH032 | Repair, replace, construct various sidewalks in Dillion County | Transportation Enhancements | 2010-12-01 | 2010-12-06 | 2011-04-30 | 2011-04-07 | 120457.72
10688 | Underway | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | HORRY |  | 01 | SPEH034 | ARRA Sidewalk Projects in Horry County | Transportation Enhancements | 2011-01-17 | 2011-01-26 | 2011-06-30 |  | 175908.1
10689 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ORANGEBURG, BARNWELL |  | Multiple | SPEH035 | Repari, replace, construct various sidewalks in Barnwell County | Transportation Enhancements | 2010-11-18 | 2011-01-13 | 2011-04-30 | 2010-02-18 | 191913.62
10690 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHARLESTON |  | 01 | SPEH036 | ARRA Sidewalk Projects in Charleston County | Transportation Enhancements | 2010-11-08 | 2010-12-01 | 2011-06-30 | 2009-06-30 | 337370.83
10691 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | DILLON, DARLINGTON, MARLBORO |  | 05 | SPEH037 | Sidewalk repairs, replacement, and construction in various locations in Darlingtion, Dillon, and Marlboro Counties | Transportation Enhancements | 2009-09-28 | 2009-09-28 | 2010-04-30 | 2010-04-30 | 360744.3
10692 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | WILLIAMSBURG, MARION, FLORENCE |  | 06 | SPEH039 | Sidewalk repairs, replacement, and construction in various locations in Florence, Marion, and Williamsburg Counties | Transportation Enhancements | 2010-03-25 | 2010-03-28 | 2010-10-31 | 2010-09-22 | 284230.15
10693 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN, HORRY |  | 01 | SPEH040 | Sidewalk repairs, replacement, and construction in various locations in Georgetown and Horry Counties | Transportation Enhancements | 2010-03-01 | 2010-03-08 | 2010-07-31 | 2010-08-04 | 333968.45
10694 | Underway | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN |  | 03 | SPEH041 | Repair, replace, construct various sidewalks in Aiken County | Transportation Enhancements | 2010-09-07 | 2011-01-26 | 2011-04-30 |  | 201230.4
10695 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | DILLON, DARLINGTON, MARLBORO, FLORENCE |  | Multiple | SPEH045 | Sidewalk repairs, replacement, and construction in various locations in Darlington, Dillon, Florence, and Marlboro Counties. | Transportation Enhancements | 2009-12-27 | 2009-12-29 | 2010-06-30 | 2010-06-28 | 257751.4
10696 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN, MARION, WILLIAMSBURG, HORRY |  | Multiple | SPEH050 | Sidewalk repairs, replacement, and construction in various locations in Georgetown, Horry, Marion, and Williamsburg Counties. | Transportation Enhancements | 2009-12-27 | 2010-02-12 | 2010-06-30 | 2010-05-10 | 139104
10697 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | COLLETON, JASPER, BEAUFORT |  | 02 | SPEH053 | Sidewalk repairs, replacement, and construction in various locations in Beaufort, Colleton, Jasper Counties. | Transportation Enhancements | 2010-08-20 | 2010-09-08 | 2010-12-31 | 2010-12-09 | 461067.14
10698 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BERKELEY |  | 01 | SPEH054 | Sidewalk repairs, replacement, and construction in various locations in Berkeley and Dorchester Counties. | Transportation Enhancements | 2010-04-26 | 2010-05-05 | 2010-08-31 | 2010-09-15 | 358843.94
10699 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHARLESTON |  | 01 | SPEH056 | Sidewalk repairs, replacement, and construction in various locations in Charleston County | Transportation Enhancements | 2010-08-09 | 2010-09-20 | 2010-12-31 | 2010-12-15 | 635780
10700 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | DORCHESTER |  | 06 | SPEH059 | Repair, replace, construct sidewalks in various locations in Dorchester County SC | Transportation Enhancements | 2010-03-22 | 2010-08-03 | 2010-10-31 | 2010-10-31 | 159871.04
10701 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN |  | 03 | SPEH061 | Sidewalk repairs, replacement, and construction in various locations in Aiken County | Transportation Enhancements | 2010-03-04 | 2010-05-12 | 2010-06-30 | 2010-06-28 | 525849.08
10702 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BAMBERG, HAMPTON, ALLENDALE, BARNWELL |  | 02 | SPEH065 | Sidewalk repairs, replacement, and construction in various locations in Allendale, Bamberg, Barnwell, Hampton Counties | Transportation Enhancements | 2009-12-07 | 2010-01-18 | 2010-07-31 | 2010-05-03 | 320974.71
10703 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CLARENDON, ORANGEBURG, CALHOUN |  | 06 | SPEH068 | Sidewalk repairs, replacement, and construction in various locations in Calhoun, Clarendon, and Orangeburg Counties | Transportation Enhancements | 2010-02-02 | 2010-02-23 | 2010-06-30 | 2010-05-11 | 471919.61
10704 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENVILLE |  | 04 | SPEH074 | ARRA Sidewalk repari, replacement, construction in various locations in Greenville County SC. | Transportation Enhancements | 2010-06-01 | 2010-07-15 | 2010-10-31 | 2010-10-04 | 186521.34
10705 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ANDERSON |  | 03 | SPEH075 | Repair, replace, construct sidewalks at various locations in Anderson County SC | Transportation Enhancements | 2010-04-16 | 2010-04-21 | 2010-08-31 | 2010-09-01 | 219212.32
10706 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ANDERSON |  | 03 | SPEH077 | Repair, replace, construct sidewalks at various locations in Anderson County SC | Transportation Enhancements | 2010-04-16 | 2010-04-21 | 2010-06-30 | 2010-06-17 | 166206.6
10707 | Completed | C220 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | NEWBERRY |  | 05 | SPEH078 | Repiar, replace, construct sidewalks at various locations in Newberry County SC | Transportation Enhancements | 2010-05-24 | 2010-05-24 | 2010-09-30 | 2010-07-30 | 145746.67
10708 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPIM001 | Resurface and rehabilitate the east bound lane of I-20 in Lexington and Richland Counties from approximately US-378 to approximately US-321. | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2010-10-31 |  | 10540556.3 | 10.000
10709 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN |  | 03 | SPIM002 | Resurface and rehabilitate the east bound lane of I-20 in Aiken County from approximately US-1 to approximately US-178. | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-09-30 | 2011-05-24 | 11368849.35 | 16.000
10710 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | RICHLAND | COLUMBIA | 02 | SPIM003 | Resurface and rehabilitate the south bound lane of I-77 in Richland County from approximately S-151 to approximately US-1 | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2010-06-30 |  | 2745808.23 | 5.000
10711 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CLARENDON |  | 06 | SPIM004 | Resurface and rehabilitate the south bound lane of I-95 in Clarendon County from approximately mile marker 99 to approximately mile marker 100. | Pavement Improvement | 2009-08-10 | 2009-08-23 | 2010-07-31 | 2010-09-17 | 4542026.62 | 6.000
10712 | Underway | C240,C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHARLESTON | CHARLESTON | 01 | SPIM005 | Resurface and rehabilitate the east bound and west bound lane of I-26 in Charleston County from approximately mile marker 212 near I-526 to approximately mile marker 218 at Heriot Steet. | Pavement Improvement | 2009-08-26 | 2009-09-30 | 2011-04-30 |  | 14668347.24 | 18.000
10713 | Underway | C200,C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LAURENS, SPARTANBURG, STATEWIDE |  | Multiple | SPIM006 | Rehabilitation of I-26 Bridges in Laurens and Spartanburg Counties. Bridge jacking at SC Route 66, SC route 56,L 681, state road 314 in Laurens County, and SC Route 49 in Spartanburg County. This al | Pavement Improvement | 2010-08-24 | 2010-08-24 | 2012-11-30 |  | 26613698.01 | 9.000
10714 | Underway | C240,C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENVILLE | GREENVILLE | 04 | SPIM007 | Resurface and rehabilitate I-85 in Greenville County from south of US-276 exit 48 to US-25 exit 44 | Pavement Improvement | 2010-03-08 | 2010-03-22 | 2011-07-31 |  | 5800000 | 5.000
10715 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | JASPER |  | 02 | SPIM008 | Resurface and rehabilitate a portion of I-95 in Jasper County from approximately mile marker 18.3 to approximately mile marker 23.9 | Pavement Improvement | 2009-09-18 | 2009-09-18 | 2010-06-30 | 2010-09-13 | 4882506.75 | 4.890
10716 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | FLORENCE |  | 06 | SPIM010 | Resurface and rehabilitate the north bound lane of I-95 in Florence County from approximately mile marker 156 to approximately mile marker 161. | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2010-08-31 | 2010-08-17 | 1951212.7 | 5.000
10717 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SPARTANBURG |  | 04 | SPIM011 | Resurface and rehabilitate the east bound lane of I-26 in Spartanburg County from approximately mile marker 5 to approximately mile marker 11.1. | Pavement Improvement | 2010-02-26 | 2010-03-29 | 2010-11-30 | 2011-03-24 | 5923499.26 | 5.000
10718 | Underway | C240,C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENVILLE | GREENVILLE | 04 | SPIM012 | Resurface and rehabilitate Northbound I-185, from I-85 to Road S-260 near Greenville | Pavement Improvement | 2010-02-08 | 2010-02-11 | 2010-10-31 |  | 1694585.57
10719 | Underway | C240,C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENVILLE | GREENVILLE | 04 | SPIM013 | Reconstruction and rehabilitation including resurfacing approximately 6.5 miles of I 385 from Southern Connector to Woodruff Road. | Pavement Widening | 2010-10-11 | 2010-11-30 | 2012-10-24 |  | 36938304.88
10720 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ANDERSON | ANDERSON | 03 | SPMC001 | Construction of a five lane roadway on new location in Anderson County known as the East - West Connector from US76-US178 (Clemson Boulevard) to SC Route 81 (Greenville Street). | New Construction | 2009-10-20 | 2009-10-20 | 2011-10-31 |  | 7363520.32
10721 | Completed | C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | PICKENS | GREENVILLE | 03 | SPMC002 | Intersection improvement project at Calhoun Memorial Highway and Prince Perry in Easley, SC and includes replacing the bridge over the CSX railroad . | Pavement Improvement | 2009-12-14 | 2009-12-21 | 2010-09-30 | 2010-09-30 | 5027417.52 | 0.850
10722 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | UNION |  | 04 | SPMC003 | Intersection improvement of Wildcat Road in Union County. | Pavement Improvement | 2010-05-11 | 2010-06-16 | 2010-10-31 | 2010-10-31 | 1020000 | 0.060
10723 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | NEWBERRY |  | 05 | SPMC004 | Intersection improvement in Newberry County at SC Route 391 and Stoney Hill Road and Mt. Pillgram Road. | Pavement Improvement | 2010-02-09 | 2010-03-10 | 2010-05-31 | 2010-06-23 | 160000 | 0.100
10724 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | PICKENS |  | 03 | SPMC005 | Intersection improvement of SC 133 and Clemson Blvd. in the City of Clemson. Also includes the replacement of the railroad bridge at the interseciton. | Pavement Improvement | 2010-07-12 | 2010-07-29 | 2012-04-30 |  | 5526000 | 0.400
10725 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BEAUFORT |  | 02 | SPMC006 | Widening from two lanes to five lanes Simmonsville Road in Bluffton, SC from US78 to Bluffton Parkway. Adding a lane eastbount and westbound to the existing 2 lanes along with a center turing lane | Pavement Widening | 2009-06-28 | 2009-08-31 | 2010-12-15 |  | 7000000 | 0.750
10726 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LAURENS |  | 03 | SPMC007 | Construction of road way "New Frontage Road" in Clinton SC from SC Highway 72 near exit 54 to SC Route 56 near exit 52. | New Construction | 2010-02-26 | 2010-03-01 | 2011-05-31 |  | 2159481.01 | 1.260
10727 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | DORCHESTER |  | 06 | SPMC008 | Project to widen a section of US 178 to three lanes in the Town of Dorchester in Dorchester County, SC and to resurface a portion of US 178 in the Town of Dorchester. This project is a part of the Lo | Pavement Improvement | 2009-10-29 | 2010-04-12 | 2011-06-30 |  | 1000000 | 11.470
10728 | Completed | C200,C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | HORRY |  | 01 | SPMC009 | Intersection improvement project at US 17 Mineola Avenue in Horry County. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2010-06-30 | 2010-08-31 | 416520.33 | 0.280
10729 | Completed | C200,C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN |  | 01 | SPMC010 | Improvement of intersection of Fraiser Street and Front Street in Georgetown, SC. The project improvement includes signal upgrades, additonal pedestrian signals, and crosswalk and sidewalk improvement | Pavement Improvement | 2010-01-04 | 2010-01-27 | 2010-06-30 | 2010-06-30 | 183618.05 | 0.000
10730 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SALUDA |  | 03 | SPMC011 | Intersection improvement at SC 39 (Chappells Highway) and SC 702 in Saluda County. Improvement includes realigning SC 702 to tie into SC 39 at a 90 degree angle. | Pavement Improvement | 2009-09-23 | 2010-02-11 | 2010-07-31 | 2010-06-17 | 700989.68 | 0.280
10731 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN | MYRTLE BEACH | 01 | SPMC012 | Intersection improvement of Sandy Island Road and US 17 in Georgetown County to improve safety. | Pavement Improvement | 2010-03-15 | 2010-04-13 | 2010-08-31 | 2010-08-31 | 455229.9 | 0.150
10732 | Underway | C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GREENVILLE | GREENVILLE | 04 | SPMC013 | Widening of Fairforest Way from Mauldin Road to Laurens Road in Greenville County. This project includes reconstruction of the four lane facility to create a landscaped median, turn lanes at major in | Pavement Widening | 2010-07-23 | 2010-08-21 | 2011-08-31 |  | 3118000 | 2.150
10733 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SUMTER | SUMTER | 06 | SPMC014 | Street sidewalk lighting and moving of overhead utilities underground on Alice Drive from Westmark Blvd to Camden Highway. | Other | 2009-09-01 | 2009-09-01 | 2011-04-30 |  | 1413600 | 1.200
10734 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SPARTANBURG | SPARTANBURG | 04 | SPMC015 | Widening of SC 9 in Boiling Springs SC from Fagans Creek Road to north of River Oak Phase I in Spartanburg County. The project consist of adding lanes in both directions as an undivided highway. | Pavement Widening | 2010-07-15 | 2010-07-24 | 2012-08-31 |  | 4712000 | 1.770
10735 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ANDERSON | GREENVILLE | 03 | SPMC016 | Resurfacing and 2 foot shoulder paving of Sc Route 153 from the Southern Connector end and widening SC Route 153 from 2 lanes to 3 lanes near I-85 | Pavement Widening | 2010-04-14 | 2010-04-14 | 2010-08-31 | 2010-08-31 | 443189.69 | 0.435
10736 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | YORK | ROCK HILL | 05 | SPMC018 | Widening of SC 5 Bypass from the interection of SC 5 Business and SC 161 on the east side of York , SC westward to SC 5 (Black Highway). This project is a part of the 1997 Pennies for Progress Progra | Pavement Widening | 2009-12-27 | 2010-01-19 | 2012-08-31 |  | 5750000 | 4.240
10737 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | HORRY | MYRTLE BEACH | 01 | SPMC019 | New Construction from SC 544 to SC 707 to include clearing of new location and relocation of utilities. | Other | 2010-01-04 | 2010-01-04 | 2011-06-27 |  | 8038395.05
10738 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SPARTANBURG | SPARTANBURG | 04 | SPMC020 | Signalization projects at the intersection of US 29 and W.O. Ezell Blvd, US 221 and Church Street, and US 176 and Pine Street in Spartanburg County. | Safety/Traffic Management | 2010-06-25 | 2010-10-04 | 2012-03-31 |  | 2463400.74
10739 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN | MYRTLE BEACH | 01 | SPMC023 | Intersection improvement of US701 and Old Pee Dee Road in Georgetown for safety reasons. | Pavement Improvement | 2010-03-15 | 2010-05-03 | 2010-07-31 | 2010-07-31 | 146077.33 | 0.140
10740 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | HORRY | MYRTLE BEACH | 01 | SPMC024 | Widening of US 17 southbound from four lanes to six lanes from 2nd Avenue to Sea Mountain Highway | Pavement Widening | 2010-04-20 | 2010-04-30 | 2011-11-30 |  | 3798782.62 | 1.840
10741 | Underway | C240,C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN | AUGUSTA (GA) | 03 | SPMC025 | Install smart signal system and imprve drainage along Whiskey Road in Aiken County from Corporate Parkway to Brookhaven Drive | Pavement Improvement | 2010-06-30 | 2010-08-10 | 2010-10-05 |  | 971429.37
10742 | Underway | C240,C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | RICHLAND | COLUMBIA | 06 | SPMC026 | North Main Streetscape in the City of Columbia from Fuller Avenue to Fairfield Road. | Pavement Improvement | 2010-04-28 | 2010-05-01 | 2012-04-30 |  | 6000000 | 0.490
10743 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BERKELEY |  | 01 | SPMC027 | Widening of US 17 Alternate in Moncks Corner, SC by adding additional 2 lanes with center turning lane infrom Cypress Garden Road to near Moncks Corner. | Pavement Widening | 2009-11-16 | 2009-11-16 | 2012-06-30 |  | 1000000 | 7.300
10744 | Underway | C240,C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LEXINGTON | COLUMBIA | 02 | SPMC028 | Widen from SC 6 to S-103 Platt Springs Road from 2 lanes to 5 lane curb and gutter. | Pavement Widening | 2010-05-10 | 2010-05-13 | 2013-05-31 |  | 13997320 | 4.920
10745 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN |  | 01 | SPMC029 | Intersection improvement at US17 and Waverly Road. Adding a left turn lane on Waverly, Georgetown County SC | Pavement Improvement | 2010-03-11 | 2010-03-03 | 2010-07-31 | 2010-09-30 | 200375.49 | 0.110
10746 | Completed | C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN | AUGUSTA (GA) | 03 | SPMC030 | Resurface US 1 from Richland Avenue to Valley Road in Aiken County | Pavement Improvement | 2010-07-09 | 2010-08-03 | 2010-08-31 | 2010-08-31 | 519000
10747 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN | MYRTLE BEACH | Multiple | SPMC031 | Improve drainage on street around High Market Street, Front Street, and US 17 in Georgetown SC. | Other | 2010-06-15 | 2010-08-31 | 2012-05-31 |  | 3084133
10748 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | BEAUFORT |  | 02 | SPMC032 | Resurfacing and rehabilitating three sections of the William Hilton Parkway from Shelter Cove to Sea Pines Circle on Hilton Head Island, Beaufort county. | Pavement Improvement | 2010-04-23 | 2010-04-29 | 2011-03-31 | 2011-03-23 | 2211000
10749 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPSA004 | Pavement marking project on Interstate 20 in Kershaw and Lee Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime | Safety/Traffic Management | 2009-07-24 | 2009-07-14 | 2009-10-31 | 2009-11-05 | 585604.41 | 32.900
10750 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPSA005 | Pavement marking project on Interstate 26 in Laurens and Spartanburg Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve | Safety/Traffic Management | 2009-08-03 | 2009-08-20 | 2009-10-31 | 2009-10-29 | 274610.78 | 17.400
10751 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPSA006 | Pavement marking project on Interstate 77 in Chester and Fairfield Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve da | Safety/Traffic Management | 2009-07-17 | 2009-08-19 | 2009-10-31 | 2009-08-26 | 236844.93 | 14.100
10752 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | FLORENCE |  | 06 | SPSA007 | Pavement marking project on Interstate 95 in Florence County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night | Safety/Traffic Management | 2009-06-26 | 2009-06-19 | 2009-10-31 | 2009-06-30 | 224003.65 | 12.000
10753 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | AIKEN |  | 03 | SPSA008 | Pavement marking project on Interstate 20 in Aiken County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night ti | Safety/Traffic Management | 2009-08-03 | 2009-08-22 | 2009-11-20 | 2009-08-27 | 238466.49
10754 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | RICHLAND |  | 02 | SPSA009 | Pavement marking project on Interstate 20 in Richland County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night | Safety/Traffic Management | 2009-09-01 | 2009-11-02 | 2009-11-20 | 2009-12-17 | 138754.48 | 7.000
10755 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPSA010 | Pavement marking project on Interstate 77 in Fairfield and Richland Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve d | Safety/Traffic Management | 2009-07-16 | 2010-04-15 | 2009-11-20 | 2010-06-06 | 419958.22 | 23.400
10756 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | COLLETON |  | 02 | SPSA011 | Pavement marking project on Interstate 95 in Colleton County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and night | Safety/Traffic Management | 2009-07-31 | 2009-10-23 | 2009-11-20 | 2009-11-02 | 155693.98 | 6.800
10757 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SPARTANBURG |  | 04 | SPSA012 | Pavement marking project on Interstate 26 in Spartanburg County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and ni | Safety/Traffic Management | 2009-07-24 | 2009-10-06 | 2010-06-30 | 2010-06-04 | 266198.82 | 21.200
10758 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPSA013 | Pavement marking project on Interstate 20 in Darlington and Lee Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve dayti | Safety/Traffic Management | 2009-08-10 | 2009-08-04 | 2010-06-30 | 2009-08-21 | 313748.66 | 18.300
10759 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHARLESTON |  | 01 | SPSA014 | Pavement marking project on Interstate 526 in Charleston County. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve daytime and ni | Safety/Traffic Management | 2009-07-30 | 2009-10-28 | 2010-06-30 | 2010-06-21 | 161781.29 | 7.000
10760 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPSA015 | Pavement marking project on Interstate 95 in Darlingtonand Florence Counties. The project consist of the removal of the existing markings and replacement with new thermo-plastic markings to improve d | Safety/Traffic Management | 2010-02-17 | 2010-06-13 | 2010-06-30 | 2010-06-22 | 137121.36 | 10.000
10761 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LEXINGTON |  | 02 | SPSA016 | Install fiber optic lines along various interstates and Fish Hatchery Road to connect to the Emergency Management Division office for the purpose of monitoring traffic camers in emergency situations. | Safety/Traffic Management | 2009-07-01 | 2009-10-26 | 2010-02-26 | 2010-04-01 | 601859.66
10762 | Completed | C240,C230 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | LEXINGTON | COLUMBIA | 02 | SPSA017 | Realign and add turn lanes on Fish Hatchery Road in Lexington County. This project is to improve safety along Fish Hactchery Road | Safety/Traffic Management | 2009-10-19 | 2010-01-27 | 2010-09-30 | 2010-10-08 | 666835.19 | 0.300
10763 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | DARLINGTON |  | 05 | SPSA018 | Addition of turn lanes at the intersection of US 15 and S-10 in Darlington County. | Safety/Traffic Management | 2009-07-24 | 2009-08-03 | 2009-11-30 | 2009-11-30 | 1013180.16 | 1.500
10764 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ANDERSON |  | 03 | SPSA019 | Improvement of interestion of Lane Avenue and S-283 (road) in Anderson County to realign, add turn lanes, and signals. | Pavement Improvement | 2009-08-13 | 2009-08-13 | 2010-04-05 | 2010-05-28 | 509163.16 | 0.100
10765 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHEROKEE |  | 05 | SPSA020 | Safety Improvement to flatten curve on SC105 in Cherokee County | Safety/Traffic Management | 2009-09-21 | 2009-09-21 | 2010-08-31 | 2010-07-22 | 921595.75 | 0.650
10766 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | RICHLAND |  | 02 | SPSA021 | Install gardrail at various locations along Wilson Road in Richland County. | Safety/Traffic Management | 2009-08-10 | 2009-08-27 | 2010-01-07 | 2010-01-20 | 188488.75 | 0.199
10767 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPSA022 | Upgrade signal by installing LED signal heads at various interestions through out District 2 - Abbeville, Anderson, Edgefield, Greenwood, Laurens, McCormick, Newberry, and Saluda Counties. | Safety/Traffic Management | 2009-08-19 | 2009-08-24 | 2010-08-31 | 2010-10-08 | 913356.39
10768 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPSA023 | Upgrade signal by installing LED signal heads at various interestions through out District 3 - Greenivlle, Oconee, Pickens, Spartanburg Counties. | Safety/Traffic Management | 2009-08-04 | 2009-10-06 | 2010-06-30 | 2010-09-17 | 824357
10769 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | STATEWIDE |  |  | SPSA024 | Upgrade signal by installing LED signal heads at various interestions through out District 5 - Darlington, Dillon, Florence, Georgetown, Horry, Marion, Marlboro, and Williamsburg Counties. | Safety/Traffic Management | 2009-09-30 | 2009-10-26 | 2010-09-30 | 2010-09-30 | 400101.91
10770 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | CHARLESTON, STATEWIDE |  | 01 | SPSA025 | Installation of fiber optic cable along I-526 from Clements Ferry Road to Johnny Dodds Boulevard. | Safety/Traffic Management | 2009-08-05 | 2009-10-06 | 2010-04-30 | 2010-04-29 | 618961.12 | 9.000
10771 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | UNION |  | 04 | SPSA026 | Intersection improvement at Jonesville Lockhart Highway and Bob Little Road in Union County. | Pavement Improvement | 2010-05-11 | 2010-06-14 | 2010-08-31 | 2010-10-08 | 630351.45 | 0.400
10772 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | ANDERSON |  | 03 | SPSA027 | Intersection improvement at Airline Road and Corning Avenue on the Abbeville Highway in Anderson County. The project involves reconstruction of the intersection for safety reasons. | Pavement Improvement | 2010-05-27 | 2010-05-27 | 2010-11-30 | 2011-01-28 | 990734.12 | 0.400
10773 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | SPARTANBURG |  | 04 | SPSA029 | Intersection improvement at Lyman Road and New Cut Road in Spartanburg County. Improvement includes flattening out the curve and adding turn lanes. | Pavement Improvement | 2010-05-10 | 2010-05-14 | 2010-11-30 | 2011-03-18 | 1096288.06 | 0.400
10774 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | MARION |  | 06 | SPSA030 | Intersection improvement at US76 Wahee Road and SC 576. Improvement includes adding turn lanes and signals. | Pavement Improvement | 2009-12-27 | 2010-01-18 | 2010-08-31 | 2010-11-01 | 771027.28 | 0.390
10775 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH CAROLINA | GEORGETOWN |  | 01 | SPSA031 | Two foot shoulder widening and improvement of various intersections on Penny Royal Road from US17 to US17A in Georgetown County. | Safety/Traffic Management | 2010-03-18 | 2010-03-24 | 2010-12-15 | 2010-12-15 | 3284333.34
10776 | Underway | C490 | OJT/SS | SOUTH CAROLINA | STATEWIDE |  |  | SPTC001 | To provide on-the-job training for women, minorities, and other disadvantages individuals for employment in the transportation industry. The training will be comprised of pre-emploment training, comm | Other | 2009-12-29 | 2009-12-29 | 2010-12-31 |  | 437776
10777 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | MARSHALL, BROWN |  |  | 0010078 | This resurfacing project will extend the roadway life of SD Highway 10 from the east junction with SD Highway 37 to west of Britton. The project will also improve safety as the result of a smoother d | Pavement Improvement | 2010-02-11 | 2010-07-06 | 2010-10-15 | 2010-11-12 | 3409086.2 | 15.960
10778 | Completed | C200,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | UNION |  |  | 0011047 | This resurfacing project will extend the roadway life for SD Highway 11 from 0.5 miles south of Alcester, north to the junction with SD Highway 46. Safety will also be improved as a result of a smoot | Pavement Improvement | 2009-12-02 | 2010-06-01 | 2010-10-15 | 2010-10-01 | 1200671.92 | 5.000
10779 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | DEUEL, HAMLIN |  |  | 0012154 | Ths project will mill and asphalt repave SD Highway 29 from the Hamlin/Deuel County Line to SD Highway 15. SD Highway 15 from SD 28 north the south city limits of Clear Lake, South Dakota. Safety wi | Pavement Improvement | 2009-12-18 | 2010-05-21 | 2010-10-15 | 2010-11-03 | 3108392.17 | 20.030
10780 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | BEADLE |  |  | 0014165 | This pavement grinding project will extend the life of US Highway 14 from Miller to east of Wessington. The project will also improve safety as the result of a smoother driving surface. | Pavement Improvement | 2009-03-27 | 2009-06-01 | 2009-10-02 | 2009-10-07 | 1679652.75 | 18.700
10781 | Completed | C200,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | PENNINGTON | RAPID CITY |  | 0016068 | This resurfacing project will extend the roadway life of US Highway 16 from Spring Creek Road to Cathedral Drive in Rapid City. | Pavement Improvement | 2009-06-17 | 2009-09-14 | 2010-07-28 | 2010-11-05 | 4325570.46 | 5.700
10782 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | SPINK |  |  | 0020092 | This resurfacing project will extend the roadway life for SD Highway 20 from SD Highway 45 to Brentford. | Pavement Improvement | 2009-04-03 | 2009-05-11 | 2010-07-31 | 2009-08-12 | 6213585.95 | 34.800
10783 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | PERKINS |  |  | 0020093 | This resurfacing project will extend the roadway life of SD Highway 20 from Prairie City to 2.6 miles west of Bison. | Pavement Improvement | 2009-03-30 | 2009-10-03 | 2009-10-31 | 2010-07-13 | 4043577.1 | 14.000
10784 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | CHARLES MIX |  |  | 0021094 | This project will mill and asphalt repave SD Highway 50 from the east junction with SD Highway 44 to US Highway 18 and SD Highway 1804 from south of the junction with SD Highway 50 to the junction wit | Pavement Improvement | 2009-12-28 | 2010-06-03 | 2010-10-29 |  | 4455744.12 | 23.700
10785 | Underway | C200,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | DOUGLAS, CHARLES MIX, HUTCHINSON |  |  | 0021147 | This project will mill and asphalt repave US Highway 18 from the east junction with SD Highway 50 to the east junction with US Highway 281. It will also mill and asphalt repave US Highway 281 fromt t | Pavement Improvement | 2009-12-16 | 2010-05-03 | 2010-10-29 |  | 5905127.75 | 30.174
10786 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | HAAKON |  |  | 0034132 | This resurfacing project will extend the roadway life of SD Highway 34 from east of the Cheyenne River to near the east junction with SD Highway 73. The project will also improve safety as a result o | Pavement Improvement | 2009-03-30 | 2009-08-19 | 2009-10-16 | 2009-10-16 | 2612293.95 | 14.900
10787 | Underway | C200 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | MOODY |  |  | 0034135 | This project will reconstruct SD Highway 34 from 1 mile west of SD Highway 13 to the Mineesota State Line. | Pavement Improvement | 2009-12-17 | 2010-04-05 | 2011-05-27 |  | 4753746 | 7.700
10788 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | CUSTER |  |  | 0036010 | This resurfacing project will extend the roadway life for SD Highway 36 from the junction of US Highway 16A, easat 0.9 miles. | Pavement Improvement | 2009-05-19 | 2010-04-26 | 2010-12-03 | 2010-08-31 | 188815.52 | 0.900
10789 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | PENNINGTON, JACKSON |  |  | 0041144 | This resurfacing project will extend the roadway life of SD 44 from the Jct. With the Conata Road to the Jct. With SD377. Safety will also be improved with the smoother driving surface. | Pavement Improvement | 2009-11-18 | 2010-06-24 | 2010-10-15 | 2010-09-08 | 2080109.12 | 12.525
10790 | Completed | C200,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | FALL RIVER |  |  | 0043009 | This resurfacing project with ADA upgrades will extend the roadway life on US Highway 18B from the west junction with US 18 to the east junction of US Highway 18 in Hot Springs, US 18P from US 18 to S | Pavement Improvement | 2010-01-20 | 2010-03-18 | 2010-12-03 | 2010-09-22 | 2083390.1 | 7.249
10791 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | TURNER |  |  | 0044140 | This resurfacing project will extend the roadway life for SD Highway 44 from US Highway 81 to Marion Road. The safety of the route will also be improved by have a smoother driving surface. | Pavement Improvement | 2009-12-17 | 2010-05-13 | 2010-10-15 | 2011-07-07 | 1706113.71 | 8.000
10792 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | MELLETTE, TRIPP |  |  | 0044142 | This resurfacing project will extend the roadway life of SD Highway 44 from Wood to the US 183 Junction. | Pavement Improvement | 2009-12-15 | 2010-05-04 | 2010-10-15 | 2010-11-13 | 3929016.36 | 24.994
10793 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | YANKTON |  |  | 0046044 | This resurfacing project will extend the roadway life of SD Highway 46 from US Highway 281 to Irene. The project will also improve safety by providing a smoother driving surface. | Pavement Improvement | 2009-12-18 | 2010-04-19 | 2010-10-15 | 2010-11-12 | 2620057.6 | 12.004
10794 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | LYMAN |  |  | 0053004 | This resurfacing project will extend the roadway life of SD Highway 53 from the end of the pavement north of the White River to south of I-90 near Vivian. The project will also improve safety as the | Pavement Improvement | 2009-03-27 | 2009-05-25 | 2009-10-30 | 2009-07-21 | 1278344.84 | 8.000
10795 | Completed | C200 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | DEWEY |  |  | 0063037 | This resurfacing project will extend the roadway life of SD Highway 63 from north of the Moreau River to the west junciton with SD Highway 20. The project will also improve safety as a result of a sm | Pavement Improvement | 2010-01-06 | 2010-05-18 | 2010-10-29 | 2011-06-07 | 2277879.23 | 13.198
10796 | Completed | C200,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | ZIEBACH, DEWEY |  |  | 0063040 | This resurfacing project will extend the roadway life for SD Highway 63 from north of the Cheyenne River to the west Junction with US Highway 212. The project will also improve safety as reflected by | Pavement Improvement | 2010-02-25 | 2010-05-03 | 2010-10-29 | 2011-06-07 | 5391709.41 | 22.380
10797 | Completed | C250,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | HARDING |  |  | 0079066 | This resurfacing project will extend the roadway life of SD Highway 79 from the Slim Buttes area to west of the junction with SD Highway 20. The road will also improve safety as the result of a smoot | Pavement Improvement | 2009-03-31 | 2010-04-15 | 2010-07-31 | 2010-11-04 | 3517728.17 | 14.000
10798 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | LAKE, KINGSBURY |  |  | 0081035 | This project will resurface US Highway 81 from Madison north to the Kingsbury County Line, extending the life of the highway. Safety will also be improved by a smoother driving surface. | Pavement Improvement | 2009-12-24 | 2010-08-04 | 2010-10-15 | 2011-09-23 | 3348383.49 | 15.200
10799 | Underway | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | YANKTON |  |  | 0081063 | This project will convert the Meridian Bridge at Yankton from a highway bridge to a pedestrian bridge. | Transportation Enhancements | 2009-12-23 | 2010-04-04 | 2011-04-30 |  | 5301305.77 | 0.000
10800 | Underway | C200,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | BUTTE |  |  | 0085051 | This project will reconstruct US Highway 85 in Belle Fourche from Hay Creek to the Belle Fourche River. | Pavement Widening | 2009-10-22 | 2010-02-11 | 2010-12-03 |  | 6254002.01 | 1.111
10801 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | HARDING |  |  | 0085066 | This resurfacing project will extend the roadway life of US Highway 85 from north of Buffalo to the North Dakota State Line. Safety will also be inmporved with a smoother driving surface. | Pavement Improvement | 2010-02-25 | 2010-04-20 | 2010-10-01 |  | 3988657.91 | 20.300
10802 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | ROBERTS |  |  | 0127006 | This resurfacing project will extend the roadway life of SD Highway 127 from I-29 west of the town of Victor, east and north to the North Dakota State Line. Safety will also be improved with the smoo | Pavement Improvement | 2009-12-28 | 2010-06-30 | 2010-10-15 | 2010-10-22 | 2875326.12 | 16.546
10803 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | CUSTER |  |  | 016A002 | This resurfacing project will extend the roadway life of US Highway 16A from the west entrance of Custer State Park, easat to the junction with SD Highway 36. The project will also improve safety as | Pavement Improvement | 2009-05-19 | 2010-04-26 | 2010-12-03 | 2010-08-31 | 2571612.49 | 13.700
10804 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | CLARK, CODINGTON |  |  | 0212113 | This pavement restoration project will extend the life of the section of US Highway 212 from the Spink/Clark County Line to East of Clark, and the section of US Highway 212 that goes through the town | Pavement Improvement | 2009-03-27 | 2010-04-05 | 2010-09-03 | 2010-08-26 | 1618856.47 | 9.000
10805 | Completed | C250 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | MCPHERSON |  |  | 0247005 | This resurfacing project will extend the roadway life of SD Highway 247 from Roscoe to north of SD Highway 10. The project will also improve safety as a result of a smoother driving surface. | Pavement Improvement | 2009-10-08 | 2010-08-02 | 2010-10-15 | 2011-05-25 | 2839699.59 | 22.535
10806 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | UNION |  |  | 0291075 | This project will remove and replace the existing surface of the northbound lanes of I-29 from Elk Point to the SD Highway 50 exit. | Pavement Improvement | 2009-10-26 | 2010-03-30 | 2010-11-24 |  | 10604818.62 | 9.586
10807 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | UNION |  |  | 0291101 | This project will remove and replace the concrete surface on the northbound lanes of I-29 from south of the Volin Exit to south of the Beresford exit. | Pavement Improvement | 2009-04-02 | 2009-04-17 | 2010-08-20 | 2011-02-25 | 8496814.5 | 9.400
10808 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | CODINGTON |  |  | 0297030 | This project will remove and replace the current concrete pavement on the southbound lanes of I-90 from SD Highway 20 north, 14.7 miles, to US Highway 212. The improvements will improve safety with a | Pavement Improvement | 2009-03-27 | 2009-04-15 | 2009-10-30 | 2010-09-15 | 14595074.99 | 14.700
10809 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | JACKSON |  |  | 0903078 | This resurfacing project will extend the pavement life of a section of both the east and west bound sections of I-90 from Murdo to the Jackson/Jones County Line. Safety will also be improved by shoul | Pavement Improvement | 2009-04-01 | 2009-05-11 | 2010-07-16 | 2009-11-10 | 12963056.58 | 32.200
10810 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | AURORA, DAVISON |  |  | 0907052 | This project will remove and replace the concrete surface on the westbound lanes of I-90 from White Lake to Mount Vernon. | Pavement Improvement | 2009-03-30 | 2009-05-05 | 2010-10-29 |  | 22752460.65 | 21.800
10811 | Underway | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | AURORA, DAVISON |  |  | 0907074 | This project will remove and replace the concrete surface on the eastbound lane of I-90 from 1 mile east of Plankinton to Mount Vernon. Safety will also be improved as a result of a smoother driving | Pavement Improvement | 2009-12-16 | 2010-04-22 | 2010-10-29 |  | 9653568.76 | 10.757
10812 | Completed | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | UNION |  |  | 0ENH185 | This project will design and construct a bike path throughout the City of Beresford. | Transportation Enhancements | 2010-01-04 | 2010-08-16 | 2010-10-29 | 2011-08-16 | 139336.46 | 0.000
10813 | Underway | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | LINCOLN |  |  | 0ENH187 | This project will restore a historic train depot into a museum. | Transportation Enhancements | 2010-01-14 | 2010-03-24 | 2010-07-01 |  | 120812.34 | 0.000
10814 | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | DEWEY |  |  | 0ENH189 | This project will design and construct a multi-use path along Main Street, Prairie Road, and Willow Street in Eagle Butte. | Transportation Enhancements | 2010-01-11 | 2010-05-05 | 2010-10-29 | 2011-08-11 | 446012.14 | 0.000
10815 | Completed | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | GREGORY |  |  | 0ENH190 | This project will design and construct a bike path along 5th Street in Gregory. | Transportation Enhancements | 2010-01-11 | 2010-02-08 | 2010-10-29 | 2010-11-02 | 489622.08 | 0.000
10816 | Completed | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | HUGHES |  |  | 0ENH191 | This project will design and contruct the Hilger's Gulch Bicycle and Pedestrian Trail along 4th Street in Pierre. | Transportation Enhancements | 2010-01-06 | 2010-04-21 | 2010-09-24 | 2010-10-14 | 436870.11 | 0.000
10817 | Completed | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | SPINK |  |  | 0ENH193 | This project will design and contruct a bike path along 10th Avenue in Redfield. | Transportation Enhancements | 2010-01-14 | 2010-07-19 | 2010-10-29 | 2010-10-12 | 363865.63 | 0.000
10818 | Completed | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | MINNEHAHA | SIOUX FALLS |  | 0ENH194 | This project will rehabilitate a historic bridge along the Souix Falls Trail System. | Transportation Enhancements | 2010-03-01 | 2010-03-08 | 2010-08-13 | 2010-09-01 | 646752.93 | 0.000
10819 | Completed | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | ROBERTS |  |  | 0ENH195 | This project will design and construct a bike path within the City of Sisseton | Transportation Enhancements | 2010-01-05 | 2010-04-12 | 2010-10-29 | 2010-08-10 | 361068.15 | 0.000
10820 | Completed | C250,C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | CODINGTON |  |  | 0ENH196 | This project will design and construct a bike path along SD Highway 20 between Watertown and Lake Kampeska. | Transportation Enhancements | 2009-12-18 | 2010-06-14 | 2010-08-01 | 2010-09-01 | 390258.61 | 0.000
10821 | Underway | C220 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | BROWN |  |  | 0ENH198 | This project will restore the Railroad Depot in Aberdeen, SD. | Transportation Enhancements | 2010-04-16 | 2010-06-28 | 2010-10-31 |  | 383025.39 | 0.000
10822 | Completed | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | BEADLE |  |  | 0ENH199 | This project will provide for the preliminary engineering and construction of a pedestrian/bicycle trail in Wolsey, South Dakota | Transportation Enhancements | 2010-01-05 | 2010-07-12 | 2010-10-29 | 2010-10-01 | 229397.11 | 0.000
10823 | Completed | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | LAWRENCE |  |  | 0ENH201 | This project will design and construct a bike path at Black Hills State University in Spearfish | Transportation Enhancements | 2010-01-05 | 2010-05-17 | 2010-08-31 | 2010-11-01 | 207748.69 | 0.000
10824 | Underway | C220,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | LAKE |  |  | 0ENH202 | This project will rehabilitate a historic train depot in Madison. | Transportation Enhancements | 2010-01-11 | 2010-04-05 | 2010-09-01 |  | 143191.98 | 0.000
10825 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | CHARLES MIX |  |  | 1804008 | This resurfacing project will extend the roadway life of SD Highway 1804 from SD Highway 44 south 8 miles. The project will also improve safety as the result of a smoother driving surface. | Pavement Improvement | 2009-03-30 | 2009-04-25 | 2010-05-01 | 2009-11-20 | 1636423.33 | 8.000
10826 | Completed | C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | BUTTE |  |  | 3034001 | This resurfacing project will extend the roadway life of SD Highway 34 from the Wyoming State Line to Belle Fourche. Safety will also be improved as the result of a smoother driving surface. | Pavement Improvement | 2009-03-30 | 2009-06-22 | 2010-07-31 | 2009-11-12 | 1704882.03 | 9.800
10827 | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | CUSTER |  |  | 3040008 | This project will reconstruct SD Highway 40 in Hermosa, from SD Highway 79 to the trailer park east of the railroad tracks. Along with a new road surface, the project will include storm sewers, curb | Pavement Improvement | 2009-07-21 | 2009-11-30 | 2010-12-03 | 2011-06-30 | 1748271.26 | 0.900
10828 | Completed | C250,C240 | Highway Infrastructure Investment Grant | SOUTH DAKOTA | STANLEY |  |  | 3806027 | This project will resurface 5.117 miles of SD Highway 1806 from US Highway 14 in Ft. Pierre to SD Highway 204 on the west end of the Oahe Dam. The project will extend the surface life of the pavement | Pavement Improvement | 2010-02-09 | 2010-06-08 | 2010-10-15 | 2011-09-01 | 2332805.64 | 5.117
10829 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | SHELBY | MEMPHIS (AR-MS) | 09 | 0001236 | This project located on SR-1 FROM ISABELLE STREET TO WHITE STATION ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ext | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 1132123 | 2.700
10830 | Underway | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WARREN |  | 04 | 0001237 | This project includes the necessary grading, drainage work, and bridge construction in preparation for a future paving project. | New Construction | 2009-04-07 | 2009-04-07 | 2011-12-31 |  | 8951029 | 5.200
10831 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | VAN BUREN |  | 04 | 0001240 | This project located on SR-1 FROM WARREN COUNTY LINE TO WHITE COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help e | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-10-31 | 2009-10-31 | 272593.01 | 2.850
10832 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WARREN |  | 04 | 0001242 | This project located on SR-1 FROM VICTOR J. YOUNG ROAD TO VAN BUREN COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-10-31 | 2009-10-31 | 131908 | 1.150
10833 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | WHITE |  | 04 | 0001243 | This project located on SR-1 FROM VAN BUREN COUNTY LINE TO COLE ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-10-31 | 2009-09-30 | 186971.96 | 1.890
10834 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HAYWOOD |  | 08 | 0001244 | This project located on SR-1 FROM TIPTON COUNTY LINE TO OVERFLOW BRIDGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help ext | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-12-15 | 2009-11-30 | 917711 | 5.580
10835 | Completed | C230 | Highway Infrastructure Investment Grant | TENNESSEE | DAVIDSON | NASHVILLE-DAVIDSON | 05 | 0001245 | This project is for the rehabilitation/upgrading of sidewalks on Harding Pike/West End Avenue from White Bridge Road to I-440 in Nashville | Transportation Enhancements | 2009-11-06 | 2009-11-06 | 2011-01-31 | 2010-11-02 | 381766 | 1.680
10836 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | LOUDON | KNOXVILLE | 02 | 0002092 | This project located on SR-2 FROM WEST OF SR-73 TO WEST OF SR-1 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 909796 | 5.000
10837 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | RUTHERFORD | MURFREESBORO | 06 | 0002093 | This project located on SR-2 FROM NORTH OF RUTHERFORD BOULEVARD TO EPPS MILL ROAD will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will als | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-09-30 | 904837.41 | 6.800
10838 | Completed | C200 | Highway Infrastructure Investment Grant | TENNESSEE | BRADLEY | CLEVELAND | 03 | 0002094 | This project located on SR-2 FROM CLEVELAND CITY LIMITS TO SR-40 will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend the | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-08-31 | 630246.93 | 2.600
10839 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | HAMILTON | CHATTANOOGA (GA) | 03 | 0002095 | This project located on SR-2 FROM LILAC AVENUE TO NORFOLK SOUTHERN R/R OVERPASS will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-31 | 746618.93 | 3.000
10840 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | COFFEE |  | 04 | 0002096 | This project located on SR-2 FROM RUTHERFORD COL TO OLD HWY 41 (LT) will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help extend | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-30 | 782759.8 | 6.100
10841 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | MCMINN |  | 02 | 0002097 | This project located on SR-2 FROM NORTH OF NIOTA TO MONROE COUNTY LINE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also help exte | Pavement Improvement | 2009-04-07 | 2009-04-07 | 2009-12-15 | 2009-09-30 | 365223.18 | 2.500
10842 | Underway | C200,C240 | Highway Infrastructure Investment Grant | TENNESSEE | COFFEE |  | 04 | 0002098 | This project will improve safety and reliability of the transportation system by replacing an older bridge on SR-2 with a new BRIDGE OVER DUCK RIVER IN MANCHESTER to serve the community for the next s | Bridge Replacement | 2009-04-06 | 2009-04-06 | 2010-12-31 |  | 6598015.67 | 0.300
10843 | Completed | C240 | Highway Infrastructure Investment Grant | TENNESSEE | LAUDERDALE |  | 08 | 0003110 | This project located on SR-3 FROM TIPTON COUNTY LINE TO STATE HIGHWAY GARAGE will provide a smoother riding surface for motorists, thus decreasing wear and tear on their automobiles, and will also hel | Pavement Improvement | 2009-04-06 | 2009-04-06 | 2009-10-31 | 2009-10-15 | 1470293.93 | 5.000