## Introduction & TOC
Weekly List of FHWA Recovery Act Projects
As of February 8,2013
Introduction:
This report summarizes all projects that are using or will receive American Recovery and Reinvestment Act of 2009 (Recovery Act) funds. The recipients include Federal Grants to States, including Ferry Boat Discretionary grants and On-the-Job Training/Supportive Services (OJT/SS) grants ; Federal Lands Divisions; Federal land management agencies including the Bureau of Land Management, the USDA Forest Service, and the National Park Service; Indian Reservation Roads (IRR) Program projects; and TIGER grants. The report is produced weekly on Fridays and is organized by the recipients listed above as well as summary tabs by State/Division/Recipient, improvement type, and program. The project lists are split by Obligated and Awarded or Not Awarded, Projects Underway, and Completed Projects (see below for definitions). If you have any questions, please contact Paolo Angulo at paolo.angulo.ctr@dot.gov or 202-366-8030.
Project Summaries: | Definition
Summary by State: | Summary by State of the Highway Infrastructure Investment Grants plus Federal Lands and TIGER projects.
Summary by Program: | Summary by Program of all Highway Infrastructure Investment Grants plus Federal Lands and TIGER projects.
Summary by Type: | Summary by Improvement Type of the Highway Infrastructure Investment Grants (HIIG)plus Federal Lands and TIGER projects.
Project Lists:
Hwy Infra Invest Grant: | List of all State and Territory administered Highway Infrastructure Investment Grant (HIIG) projects. This list includes all projects including Projects Obligated and Awarded/Not Awarded, Projects Underway, and Completed Projects.
Federal Lands: | List of all Federal Land administered projects including ones managed by Federal Land Divisions, National Park Services, Indian Reservation Roads, etc.
TIGER 1: | List of all TIGER Grant projects.

## Summary by State
| Obligated and Awarded |  | Underway Projects |  | Completed Projects |  | All Projects
State | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations
ALABAMA |  |  | 22 | 204402549.67 | 306 | 307894054.17 | 328 | 512296603.84
ALASKA |  |  | 4 | 21608665 | 24 | 150016085.29 | 28 | 171624750.29
AMERICAN SAMOA |  |  |  |  | 1 | 4500000 | 1 | 4500000
ARIZONA |  |  | 25 | 116947616 | 184 | 396347678.22 | 209 | 513295294.22
ARKANSAS |  |  | 6 | 46870422 | 126 | 305024046 | 132 | 351894468
CALIFORNIA |  |  | 67 | 1321928236.66 | 917 | 1194373450.61 | 984 | 2516301687.27
COLORADO |  |  | 34 | 156025152 | 80 | 229874110.65 | 114 | 385899262.65
CONNECTICUT |  |  | 14 | 159887305.62 | 137 | 134164975.26 | 151 | 294052280.88
DELAWARE |  |  | 10 | 66189342.3 | 34 | 55639307.7 | 44 | 121828650
DISTRICT OF COLUMBIA |  |  | 11 | 87574326.11 | 7 | 34272137.49 | 18 | 121846463.6
FLORIDA |  |  | 122 | 965144947 | 558 | 364446959 | 680 | 1329591906
GEORGIA |  |  | 83 | 444708369.56 | 315 | 454762222.89 | 398 | 899470592.45
GUAM |  |  | 7 | 19560000 |  |  | 7 | 19560000
HAWAII |  |  | 7 | 48199806.85 | 19 | 76669929.37 | 26 | 124869736.22
IDAHO |  |  | 19 | 60654088.16 | 66 | 116977687.14 | 85 | 177631775.3
ILLINOIS |  |  | 40 | 136037640.38 | 780 | 796304945.54 | 820 | 932342585.92
INDIANA |  |  | 7 | 5355804.41 | 1090 | 642378901.49 | 1097 | 647734705.9
IOWA |  |  | 6 | 8801248 | 229 | 348345016.41 | 235 | 357146264.41
KANSAS |  |  | 32 | 264183028.43 | 120 | 83789208.92 | 152 | 347972237.35
KENTUCKY |  |  | 26 | 264264768.62 | 84 | 154422700.61 | 110 | 418687469.23
LOUISIANA |  |  | 41 | 313477908.43 | 80 | 119258611.88 | 121 | 432736520.31
MAINE |  |  | 2 | 5122821.06 | 74 | 132177524.7 | 76 | 137300345.76
MARYLAND |  |  | 144 | 371212897 | 28 | 44551878 | 172 | 415764775
MASSACHUSETTS |  |  | 58 | 281284710.76 | 36 | 74285631.07 | 94 | 355570341.83
MICHIGAN |  |  | 134 | 411878832.34 | 619 | 441902327.02 | 753 | 853781159.36
MINNESOTA |  |  | 14 | 79923557.05 | 197 | 424984814.98 | 211 | 504908372.03
MISSISSIPPI |  |  | 4 | 3188295 | 169 | 346037966 | 173 | 349226261
MISSOURI |  |  | 23 | 240161190.77 | 314 | 397917701.62 | 337 | 638078892.39
MONTANA |  |  | 2 | 11022556.02 | 84 | 201813001.98 | 86 | 212835558
NEBRASKA |  |  | 5 | 8404233 | 124 | 217625050.52 | 129 | 226029283.52
NEVADA |  |  | 2 | 21862430 | 70 | 171615137.83 | 72 | 193477567.83
NEW HAMPSHIRE |  |  |  |  | 34 | 129432260.46 | 34 | 129432260.46
NEW JERSEY |  |  | 37 | 170336637 | 132 | 468299575.43 | 169 | 638636212.43
NEW MEXICO |  |  | 25 | 69538993.07 | 78 | 178284346.67 | 103 | 247823339.74
NEW YORK |  |  | 51 | 177958724 | 392 | 764437341.31 | 443 | 942396065.31
NORTH CAROLINA |  |  | 128 | 319148597 | 274 | 406326225 | 402 | 725474822
NORTH DAKOTA |  |  | 53 | 54164671.75 | 115 | 109358570.61 | 168 | 163523242.36
NORTHERN MARIANA | 1 | 1042300 |  |  | 1 | 3457700 | 2 | 4500000
OHIO |  |  | 25 | 377828316.26 | 400 | 537147210.86 | 425 | 914975527.12
OKLAHOMA |  |  | 54 | 226523498 | 220 | 238227907 | 274 | 464751405
OREGON |  |  | 64 | 47966106.37 | 269 | 221053345.93 | 333 | 269019452.3
PENNSYLVANIA |  |  | 19 | 206149585.86 | 303 | 822498449.14 | 322 | 1028648035
PUERTO RICO |  |  | 18 | 93233605.89 | 5 | 11755227.83 | 23 | 104988833.72
RHODE ISLAND |  |  | 1 | 1741677.58 | 69 | 135189858.55 | 70 | 136931536.13
SOUTH CAROLINA |  |  | 38 | 240908809.02 | 149 | 222610449.98 | 187 | 463519259
SOUTH DAKOTA |  |  | 13 | 77578985.16 | 39 | 108141809.92 | 52 | 185720795.08
TENNESSEE |  |  | 55 | 292568884.98 | 268 | 277943351.15 | 323 | 570512236.13
TEXAS |  |  | 99 | 1264517016.38 | 428 | 975829725.65 | 527 | 2240346742.03
UTAH |  |  | 18 | 57677309.28 | 110 | 155208790.62 | 128 | 212886099.9
VERMONT |  |  | 2 | 6135723.42 | 71 | 119208740.1 | 73 | 125344463.52
VIRGIN ISLANDS |  |  | 3 | 8678800.15 | 3 | 6784044.85 | 6 | 15462845
VIRGINIA |  |  | 39 | 339392719 | 102 | 294717645 | 141 | 634110364
WASHINGTON |  |  | 2 | 18825234 | 223 | 471211399.57 | 225 | 490036633.57
WEST VIRGINIA |  |  | 4 | 21397446 | 151 | 187037180 | 155 | 208434626
WISCONSIN |  |  |  |  | 422 | 526905546.32 | 422 | 526905546.32
WYOMING |  |  | 4 | 4478407.46 | 65 | 153137650.54 | 69 | 157616058
Sub Total (HIIG) | 1 | 1042300 | 1723 | 10222632495.83 | 11195 | 15946577414.85 | 12919 | 26170252210.68
TIGER 1 |  |  | 42 | 709446357.61 |  |  | 42 | 709446357.61
(HQFL) IRR | 4 | 2644715 | 18 | 10648034.81 | 65 | 60434999.75 | 87 | 73727749.56
Federal Lands Central Division |  |  | 2 | 5738898.98 | 27 | 94561783.35 | 29 | 100300682.33
Federal Lands Eastern Division |  |  | 6 | 59701025.37 | 19 | 44209658.75 | 25 | 103910684.12
Federal Lands Western Division |  |  | 6 | 44114124.79 | 7 | 24919131.73 | 13 | 69033256.52
Title 16 |  |  | 9 | 15007994 | 42 | 92218047.02 | 51 | 107226041.02
Grand Total | 5 | 3687015 | 1806 | 11067288931.39 | 11355 | 16262921035.4499 | 13166 | 27333896981.84

## Summary By Type
| Obligated and Awarded |  | Underway Projects |  | Completed Projects |  | All Projects
Improvement Type | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations
Bridge Improvement |  |  | 52 | 306321381.63 | 527 | 888362849.26 | 579 | 1194684230.89
Bridge Replacement |  |  | 74 | 700449675.7 | 601 | 748063842.16 | 675 | 1448513517.86
New Bridge Construction |  |  | 15 | 400620976.94 | 49 | 195541870.6 | 64 | 596162847.54
New Construction |  |  | 58 | 1216175363.69 | 127 | 687031909.86 | 185 | 1903207273.55
Pavement Improvement | 3 | 2544715 | 682 | 3155383012.01 | 7058 | 10449099905.35 | 7743 | 13607027632.36
Pavement Widening |  |  | 163 | 3223472890.87 | 263 | 1501035616.77 | 426 | 4724508507.64
Safety/Traffic Management |  |  | 186 | 754434126.38 | 792 | 606071208.56 | 978 | 1360505334.94
Transportation Enhancements |  |  | 332 | 330346754.64 | 1312 | 771835550.31 | 1644 | 1102182304.95
Other | 2 | 1142300 | 244 | 980084749.53 | 626 | 415878282.58 | 872 | 1397105332.11
Grand Total | 5 | 3687015 | 1806 | 11067288931.39 | 11355 | 16262921035.4499 | 13166 | 27333896981.84

## Summary By Program
| Obligated and Awarded |  | Underway Projects |  | Completed Projects |  | All Projects
Program | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations | Number of Projects | Obligations
Highway Infrastructure Investment Grant | 1 | 1042300 | 1684 | 10189140462.23 | 11149 | 15906939229.6099 | 12834 | 26097121991.84
Ferryboat |  |  | 14 | 24263309.25 | 24 | 31094652.4 | 38 | 55357961.65
OJT/SS |  |  | 25 | 9228724.35 | 22 | 8543532.84 | 47 | 17772257.19
TIGER 1 |  |  | 42 | 709446357.61 |  |  | 42 | 709446357.61
(CFL) BLM |  |  |  |  | 15 | 16110095.88 | 15 | 16110095.88
(CFL) BOR |  |  |  |  | 1 | 4234364.9 | 1 | 4234364.9
(CFL) FS |  |  |  |  | 2 | 3152392.34 | 2 | 3152392.34
(CFL) IRR |  |  |  |  | 1 | 49290.16 | 1 | 49290.16
(CFL) NPS |  |  |  |  | 12 | 52277007.49 | 12 | 52277007.49
(EFL) FWS |  |  |  |  | 1 | 1000000.01 | 1 | 1000000.01
(EFL) NPS |  |  | 1 | 3024016 | 2 | 4745396.51 | 3 | 7769412.51
(HQFL) FS |  |  | 1 | 25001.75 | 3 | 715411 | 4 | 740412.75
(HQFL) IRR | 4 | 2644715 | 18 | 10648034.81 | 65 | 60434999.75 | 87 | 73727749.56
(HQFL) NPS |  |  | 6 | 7712836 |  |  | 6 | 7712836
(WFL) BLM |  |  |  |  | 1 | 91.34 | 1 | 91.34
(WFL) FS |  |  | 1 | 4246140.25 | 4 | 9933997.39 | 5 | 14180137.64
Federal Lands Central Division |  |  | 2 | 5738898.98 | 27 | 94561783.35 | 29 | 100300682.33
Federal Lands Eastern Division |  |  | 6 | 59701025.37 | 19 | 44209658.75 | 25 | 103910684.12
Federal Lands Western Division |  |  | 6 | 44114124.79 | 7 | 24919131.73 | 13 | 69033256.52
Grand Total | 5 | 3687015 | 1806 | 11067288931.39 | 11355 | 16262921035.4499 | 13166 | 27333896981.84

## Hwy Infra Invest Grant
Row | Managing Group | Status | Program Code | Program | State | County | Urban Area | Cong. District | Project # | Project Description | Improvement Type | Proceed Date | Work Start Date | Estimated Completion Date | Work Complete Date | Recovery Act Obligations | Length | 1512 Award Number
1 | ALABAMA | Underway | C240,C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | 0001537 | This project constructs the mainline of US-231/431 with overpasses at Max Luther and Sparkman Drive. The mainline will be four and six lanes with a concrete median divider for approximately 1 mile. | New Construction | 2009-08-10 | 2009-08-25 | 2012-09-30 |  | 23267295.47 | 1.030 | 0001537
2 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 0001538 | This project will upgrade the bridge rails to current safety standards for bridges with inventory number 006900 and 006901 over Big Creek on US Highway 231 in Houston County | Pavement Improvement | 2009-05-13 | 2009-05-26 | 2010-04-01 | 2009-12-07 | 195937.75 | 0.010 | 0001538
3 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 0001539 | This project involve the repaving of approximately 6 miles of US Highway 231 from the Florida State line to just north of County Road 93 (Smithville Road) south of Dothan | Pavement Improvement | 2009-05-13 | 2009-05-29 | 2010-04-01 | 2009-12-07 | 2780419.27 | 6.082 | 0001539
4 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HENRY |  | 02 | 0001543 | This project involves the repaving of about 3 miles of US Highway 431 from the the south city limit of Headland to just north of State Highway 173 | Pavement Improvement | 2009-10-14 | 2009-11-03 | 2010-07-01 | 2010-07-06 | 1786185.94 | 3.060 | 0001543
5 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 0001546 | This project involves the repaving of 10 miles of US Highway 431 from Old Seale Highway to just south of US Highway 280 in Russell County | Pavement Improvement | 2009-09-25 | 2009-11-06 | 2010-04-01 | 2010-10-15 | 4496092.12 | 10.330 | 0001546
6 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH | GADSDEN | 04 | 0001547 | This project involves the repaving US Highway 31 from the north end of the Meighan Boulevard bridge to Terminal Street in the city of Gadsden | Pavement Improvement | 2010-09-21 |  | 2011-03-03 | 2012-09-04 | 1184129 | 0.920 | 0001547
7 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MARSHALL |  | 04 | 0001548 | This project involves the repaving and widening of approximately 7 miles of US Highway 431 from the north end of the Tennessee River Bridge to County Road 5 (Cathedral Caverns Highway) just north of Guntersville | Pavement Improvement | 2009-09-10 | 2009-11-24 | 2010-02-14 | 2010-08-30 | 3772979.82 | 6.660 | 0001548
8 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHAMBERS |  | 03 | 0001553 | This project will improve the curves along SR-1(US-431) from one mile south of SR-147 to south of Sturkie and provide new traffic stripe. | Safety/Traffic Management | 2009-10-22 | 2009-12-11 | 2010-02-28 | 2010-06-10 | 228025.03 | 2.000 | 0001553
9 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLEBURNE |  | 03 | 0001554 | This project involves safety improvements at various curves along US-431 | Safety/Traffic Management | 2010-01-28 | 2010-05-07 | 2010-06-30 | 2011-04-11 | 673974.66 | 1.960 | 0001554
10 | ALABAMA | Completed | C240,C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 0001555 | This project involves the repaving of US Highway 43 (State Highway 1) from US Highway 80 (State Highway 80) to the north city lilmits of Phenix City in Russell County | Pavement Improvement | 2010-05-27 | 2010-06-28 | 2010-09-30 | 2011-07-07 | 2281860.54 | 1.790 | 0001555
11 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 0002534 | This project involves the repaving and 2 foot safety widening for about 4 miles of US Highway 72 from west of Cane Creek to east of Dry in Colbert County | Pavement Improvement | 2009-05-15 | 2009-07-02 | 2010-04-10 | 2009-08-14 | 1664166.5 | 3.673 | 0002534
12 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LIMESTONE |  | 05 | 0003544 | This project involves the repaving and widening of about 3 miles of US Highway 31 from just south of Cactus Street to Interstate 65 near Athens | Pavement Improvement | 2009-05-04 | 2009-05-19 | 2009-07-31 | 2009-08-19 | 1392476.71 | 2.655 | 0003544
13 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | 0003546 | This project involves the repaving of aproximately 7 miles of the Gulf Shores Parkway from Stapleton to the Bay Minette south city limits | Pavement Improvement | 2009-05-13 | 2009-06-01 | 2009-10-31 | 2009-11-16 | 3005543.44 | 7.380 | 0003546
14 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BUTLER |  | 02 | 0003550 | This project involves the repaving and 2 foot widening of approximately 5 miles of US Highway 31 from the Conecuh County line to a bout a mile north of Persimmon Creek of Butler County | Pavement Improvement | 2009-07-23 | 2009-08-24 | 2009-12-01 | 2010-03-03 | 2005989.47 | 5.215 | 0003550
15 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | 0003551 | This project involves the repaving and 2 foot widening of approximately 10 miles of US Highway 31 near Fort Deposit from the Junction of State Highway 185 to the Montgomery County line | Pavement Improvement | 2009-08-13 | 2009-10-08 | 2010-03-31 | 2011-03-11 | 3938023.53 | 9.637 | 0003551
16 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CONECUH |  | 02 | 0003552 | This project involves the repaving of about 12 miles of US Highway 31 from US Highway 84 to the Butler County Line in Conecuh County | Pavement Improvement | 2009-08-13 | 2009-09-15 | 2009-12-31 | 2010-08-19 | 2943540.58 | 12.127 | 0003552
17 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | 01 | 0005526 | This project involves the repaving of approximately 5 miles of State Highway 5 in Clarke County from US Highway 43 to the Wilcox County Line north of Thomasville | Pavement Improvement | 2009-05-01 | 2009-05-05 | 2009-06-26 | 2009-07-09 | 1385805.21 | 4.795 | 0005526
18 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | AUTAUGA | MONTGOMERY | 02 | 0006538 | This project involves the repaving and 2 foot widening of 12 miles of US Highway 82 from just west of County Road 40 to State Highway 206 in Pratville | Pavement Improvement | 2009-08-14 | 2009-08-31 | 2010-01-30 | 2010-10-27 | 3905909.2 | 12.000 | 0006538
19 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 0007519 | This project involves the repaving of US Highway 11 from the Greene County Line to just south of the Warrior River Bridge in the Fosters. The project also include the repaving of Holly Springs Road from US Highway 11 to the Interstate 20/59 interchange | Pavement Improvement | 2009-09-16 | 2009-10-13 | 2010-03-19 | 2010-10-18 | 3836899.73 | 9.826 | 0007519
20 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | GREENE |  | 07 | 0007520 | This project invovles the repaving and widening of 10 miles US Highway 11 from north of Greentrack Road to Tuscaloosa County Line near Knoxville | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2010-02-10 | 2010-10-27 | 3370826.99 | 9.634 | 0007520
21 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MACON |  | 03 | 0008554 | This project involves the repaving and widening of 9 miles of US Highway 80 in Macon County from near the junction of State Highway 186 to the Lee County line | Pavement Improvement | 2009-08-14 | 2009-09-18 | 2009-12-01 | 2010-06-30 | 2438634.49 | 9.030 | 0008554
22 | ALABAMA | Completed | C200,C240 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY |  | 03 | 0009509 | This project will add two additional lanes to the existing two lanes to provide a four-lane facility on US Highway 331 from approximately one-half mile south of State Highway 94 to the end of the present four-lane highway at Legrand. | Pavement Widening | 2009-11-18 | 2009-12-07 | 2012-01-01 | 2012-10-17 | 20160044.36 | 4.210 | 0009509
23 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WILCOX |  | 07 | 0010520 | This project involves the repaving of 2 miles of State Highway 10 (Camden Bypass) from State Highway 28 to State Highway 28 in Camden. Wilcox County | Pavement Improvement | 2009-08-04 | 2009-08-08 | 2009-09-30 | 2009-12-15 | 520425.7 | 1.964 | 0010520
24 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CRENSHAW |  | 02 | 0010521 | This project involves the repaving and widening for 10 miles of State Highway 10 from the Butler County line to US Highway 331 in Crenshaw County | Pavement Improvement | 2009-08-12 | 2009-09-04 | 2010-06-01 | 2010-07-30 | 3058930.46 | 9.872 | 0010521
25 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | 0012536 | This project involves repaving approximately 7 miles of US Highway 84 from about 2 miles north of County Road 6 (Bladon Road) to east end of Tombigbee River Bridge in Choctaw County | Pavement Improvement | 2010-03-02 | 2010-04-22 | 2010-06-30 | 2010-08-27 | 1385021.44 | 6.626 | 0012536
26 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | 07 | 0012537 | This project involves the repaving and widening of 5 miles of US Highway 84 from the east end of the Tombigbee River Bridge to west of County Road 3 in Clarke County | Pavement Improvement | 2010-02-09 | 2010-04-22 | 2010-06-30 | 2010-09-04 | 2128816 | 5.344 | 0012537
27 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE |  | 05 | 0013503 | This project will add two additional lanes to the existing two lanes to ultimately provide a four-lane facility from the end of the present four-lane at Killen to State Highway 64. This project will | Pavement Improvement | 2009-12-02 | 2009-12-15 | 2011-08-31 | 2012-06-21 | 10822681.4 | 5.066 | 0013503
28 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BULLOCK |  | 02 | 0015515 | This project involves the repaving of a mile of US Highway 29 from State Highway 197 to US Highway 82 in Union Springs | Pavement Improvement | 2009-09-10 | 2009-09-28 | 2010-01-01 | 2010-03-10 | 380050.43 | 1.010 | 0015515
29 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | 0015516 | This project involves the repaving of over 11 miles of US Highway 29 from 1 mile south of Maye Creek to just south of Smith Creek in Escambia County | Pavement Improvement | 2010-01-26 | 2010-03-25 | 2010-04-30 | 2010-08-13 | 1914967.31 | 11.420 | 0015516
30 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | 0015517 | This project involves the repaving of about 2 miles of US Highway 29 from the Macon County Line to Sand Hill Road in Lee County | Pavement Improvement | 2009-07-29 | 2009-08-21 | 2009-10-31 | 2010-02-24 | 938557.57 | 1.860 | 0015517
31 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | 0017525 | This project involves the repaving and widening of approximately 4 miles of State Highway 17 in Chocktaw County from about 1 mile south of County Road 18 to just north of County Road 28 east of Needham | Pavement Improvement | 2009-07-29 | 2009-08-13 | 2009-10-30 | 2010-03-31 | 1098139.91 | 3.571 | 0017525
32 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | 0017526 | This project involves the repaving of 5 miles of State Highway 17 (Mulberry Avenue) from just north of County Road 28 to north of the Butler city limits in Choctaw County | Pavement Improvement | 2009-07-29 | 2009-08-13 | 2009-10-30 | 2010-03-31 | 1105494.64 | 5.541 | 0017526
33 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LAMAR |  | 04 | 0017528 | This project involves the repaving of approximately 8 miles of State Highway 17 from about a mile north of County Road 29 to County Road 30 in Sulligent | Pavement Improvement | 2009-09-11 | 2009-11-13 | 2010-08-08 | 2010-07-20 | 5956216.29 | 8.300 | 0017528
34 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MARION |  | 04 | 0017529 | This project involves the repaving of approximately 7 miles of State Highway 17 from the Lamar County line to State Highway 4 south of Hamilton in Marion County | Pavement Improvement | 2009-05-04 | 2009-07-06 | 2010-04-01 | 2009-08-07 | 1735447.28 | 7.191 | 0017529
35 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | SUMTER |  | 07 | 0017530 | This project involves the repaving of 6 miles of State Highway 17 from State Highway 28 to County Road 24 in Sumter County | Pavement Improvement | 2009-09-14 | 2010-03-30 | 2010-07-01 | 2011-04-07 | 2469090.61 | 5.970 | 0017530
36 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | WASHINGTON |  | 01 | 0017531 | This project involves the repaving of 9 miles of State Highway 17 from about 2 miles south of County Road 20 To State Highway 56 in Chatom | Pavement Improvement | 2009-09-28 | 2010-03-22 | 2009-12-18 | 2010-06-30 | 3191452.24 | 9.042 | 0017531
37 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | PICKENS |  | Multiple | 0017532 | This project involves the repaving of 2.5 miles of State Highway 17 from the Carrollton south city limits to just north of the north city limits in Pickens County | Pavement Improvement | 2009-09-21 | 2009-10-13 | 2010-04-06 | 2011-02-18 | 2045405.03 | 2.400 | 0017532
38 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE |  | 05 | 0020510 | This project involves the repaving of approximately 8 miles of State Highway 20 from the Tennessee State line to south of County Road 22 at the Natchez Trace Parkway in Lauderdale County | Pavement Improvement | 2009-09-23 | 2009-10-09 | 2010-07-01 | 2010-05-26 | 3180129.04 | 7.840 | 0020510
39 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | 0021522 | This project involves the repaving of approximately 6 miles of State Highway 21 in Monroe County from the north end of the Litte River Bridge at the Escambia County line to County Road 8 north of Uriah | Pavement Improvement | 2009-08-17 | 2009-09-14 | 2009-10-31 | 2010-06-02 | 2092374.22 | 6.245 | 0021522
40 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | 0021523 | This project involves the repaving of approximately 6 miles of State Highway 21 from north of County Road 8 to south of County Road 10 in Monroe County | Pavement Improvement | 2009-08-17 | 2009-09-14 | 2009-10-31 | 2010-06-02 | 2109032.19 | 6.425 | 0021523
41 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | 0021527 | This project involves the repaving of South Main Street in the town of Atmore from the Florida State line to about 1 mile north | Pavement Improvement | 2009-08-18 | 2009-09-08 | 2009-11-30 | 2009-11-18 | 300690.54 | 0.968 | 0021527
42 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN |  | 03 | 0021528 | This project involves the repaving of 5 miles of Jacksonville State University Highway from Maxwellborn Road to near Foothills Drive in the town of Piedmont | Pavement Improvement | 2009-09-15 | 2010-01-04 | 2010-07-01 | 2010-10-12 | 1586569.53 | 4.760 | 0021528
43 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALLAS |  | 07 | 0022509 | This project involves the repaving and 2 foot widening of approximately 19 miles of State Highway 22 from State Highway 5 to State Highway 219 in Dallas County southwest of Selma | Pavement Improvement | 2009-08-04 | 2009-09-14 | 2010-01-15 | 2010-09-19 | 3931305.24 | 19.181 | 0022509
44 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | RANDOLPH |  | 03 | 0022510 | This project will improve the curves along State Highway 22 from 1 mile north of Randolph County Road 17 to the State Line | Pavement Improvement | 2009-10-15 | 2009-11-06 | 2009-12-31 | 2010-05-06 | 492885.04 | 1.000 | 0022510
45 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LAWRENCE |  | 05 | 0024501 | This project involves the repaving of 5 miles of State Highway 24 from County Road 460 to near County Road 320 in Lawrence County | Pavement Improvement | 2009-10-14 | 2009-11-05 | 2010-07-01 | 2010-05-17 | 3083491.02 | 5.030 | 0024501
46 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HALE |  | 07 | 0025520 | This project involves repaving and widening fro about 5 miles of State Highway 25 in Hale County from County Road 29 to the Bibb County line | Pavement Improvement | 2009-08-19 | 2009-09-15 | 2010-03-03 | 2010-08-19 | 1747864.63 | 4.534 | 0025520
47 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 0027504 | This project involves the repaving and widening of approximately 10 miles of State Highway 27 in Dale County from east of County Road 59 to the Henry County line | Pavement Improvement | 2010-01-20 | 2010-02-11 | 2010-07-19 | 2010-07-19 | 2630054.44 | 9.591 | 0027504
48 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | COFFEE |  | 02 | 0027505 | This project involves the repaving and widening of approximately 5 miles of State Highway 27 northeast of Enterprise from Indego Place to the Dale County line | Pavement Improvement | 2009-08-04 | 2009-09-30 | 2010-06-01 | 2010-08-16 | 1811003.9 | 5.217 | 0027505
49 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WINSTON |  | 04 | 0033502 | This project involves the repaving of 5 miles of State Highway 24 from County Road 460 to near County Road 320 in Lawrence County | Pavement Improvement | 2009-08-18 | 2009-08-31 | 2010-06-01 | 2010-02-03 | 1552575.76 | 4.945 | 0033502
50 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | JACKSON |  | 05 | 0035509 | This project involves the repaving and 2 foot safety widening for approximately 13 miles of State Highway 35 from State Highway 79 westerly through Woodville to US Highway 72 in Jackson County | Pavement Improvement | 2009-05-04 | 2009-06-01 | 2009-08-01 | 2010-01-13 | 1477602.35 | 13.290 | 0035509
51 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | Multiple | 0036504 | This project involves the repaving and widening of over 2 miles of State Highway 36 (Main Street) from the intersection with US Highway 31 in Hartselle to Interstate 65 | Pavement Improvement | 2009-09-24 | 2009-10-19 | 2009-11-30 | 2010-04-07 | 1100964.86 | 2.414 | 0036504
52 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | 0038522 | This project involves the repaving of over 6 miles of US-280 from Hugh Daniel Drive to Old US 280 Highway | Pavement Improvement | 2009-05-14 | 2009-06-05 | 2009-11-15 | 2011-08-26 | 5795544.45 | 6.250 | 0038522
53 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CONECUH |  | 02 | 0041504 | This project involves the repaving of 10 miles of State Highway 41 from Interstate 65 to US Highway 84 in Conecuh County | Pavement Improvement | 2010-07-22 | 2010-08-18 | 2010-11-01 | 2010-12-16 | 3034720.67 | 10.596 | 0041504
54 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | 0041505 | This project involves the repaving of approximately 10 miles of State Highway 41 from south of County 39 to just south of Interstate 65 in Escambia County | Pavement Improvement | 2010-03-02 | 2010-03-23 | 2010-05-31 | 2010-09-29 | 3392321.49 | 10.790 | 0041505
55 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN | PENSACOLA | 01 | 0042518 | This project involves the replacement of traffic signals at the intersection of US Highway 98 and 6th Street in the town of Lillian in Baldwin County | Safety/Traffic Management | 2010-06-24 |  | 2010-12-11 | 2011-04-29 | 66119 | 0.010 | 0042518
56 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLAY |  | 03 | 0049502 | This project involves the repaving of about 8 miles of State Highway 49 fromt the Tallapoosa County line to State Highway 77 near the town of Ashland | Pavement Improvement | 2009-07-21 | 2009-08-09 | 2009-10-13 | 2010-08-03 | 2530360.67 | 7.334 | 0049502
57 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | TALLAPOOSA |  | 03 | 0049503 | This project involves the resurfacing and traffic stripe at various sites on SR-49. | Safety/Traffic Management | 2010-01-07 | 2010-02-04 | 2010-03-24 | 2010-07-27 | 732845.67 | 20.000 | 0049503
58 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | 0051503 | This project involves the repaving and and widening of approximately 10 miles of State Highway 51 in Barbour County from just South of State Highway 239 to the Bullock County line | Pavement Improvement | 2009-08-07 | 2009-09-23 | 2010-06-01 | 2010-07-23 | 2784528.24 | 10.325 | 0051503
59 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 0051504 | This project involves the repaving and widening of 3 miles of State Highway 51 in Dale County from the Coffee County line to US Highway 231 | Pavement Improvement | 2010-01-20 | 2010-02-11 | 2010-07-19 | 2010-07-19 | 800548.47 | 3.107 | 0051504
60 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BULLOCK |  | 02 | 0051505 | This project involves the repaving and 2 foot widening of 13 miles of State Highway 51 in Bullock County from US Highway 82 to the Russell County line | Pavement Improvement | 2010-01-27 | 2010-03-18 | 2010-08-01 | 2010-11-19 | 4911093.75 | 13.000 | 0051505
61 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 0053537 | This project will upgrade the bridge rails to current safety standards for bridges with inventory numbers 005532 and 005533 over Little Claybank Creek and bridges with inventory numbers 005571 and 009 | Bridge Improvement | 2009-05-04 | 2009-06-05 | 2010-04-01 | 2009-10-02 | 149626.25 | 6.390 | 0053537
62 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 0053538 | This project involves the repaving of about 6.5 miles of US Higway 231 from just south of State Highway 27 north to County Road 2 in Ozark | Pavement Improvement | 2009-05-04 | 2009-06-30 | 2010-04-01 | 2009-10-02 | 2723856.06 | 6.390 | 0053538
63 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | BLOUNT |  | 04 | 0053541 | This project involves the repaving of approximately 6 miles of US Highway 231 from US Highway 278 to Cullman County | Pavement Improvement | 2010-04-20 | 2010-04-27 | 2010-06-30 | 2010-10-27 | 1223129.83 | 6.214 | 0053541
64 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BLOUNT |  | 04 | 0053542 | This project involves the repaving of about 4 miles of US Highway 231 from State Highway 79 to County Road 26 in Blount County | Pavement Improvement | 2010-04-20 | 2010-04-27 | 2010-06-30 | 2010-10-27 | 1018632.19 | 3.706 | 0053542
65 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | ST CLAIR |  | 06 | 0053543 | This project involves the repaving of 7.5 miles of US Highway 231 from just north of Interstate 20 to a couple miles north of Wattsville in Ashville. | Pavement Improvement | 2009-07-16 | 2009-07-20 | 2009-09-17 | 2010-05-18 | 1506315.92 | 7.510 | 0053543
66 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | COVINGTON |  | 02 | 0055504 | This project involves the repaving of 7 miles of State Highway 55 from US Highway 84 to the North city limits of Red Level | Pavement Improvement | 2009-10-08 | 2009-10-26 | 2010-08-04 | 2010-08-04 | 3815392.73 | 6.548 | 0055504
67 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BUTLER |  | 02 | 0055505 | This project involves the repaving of a little over 1 mile of State Highway 55 from the Conecuh County Line to US Highway 31 in McKenzie | Pavement Improvement | 2009-07-23 | 2009-08-24 | 2009-12-01 | 2010-03-03 | 518140.62 | 1.169 | 0055505
68 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HALE |  | 07 | 0060500 | This project involves the repaving and widening of approximately 11 miles of State Highway 60 from State Highway 14 to State Highway 69 near Havana | Pavement Improvement | 2010-04-21 | 2010-06-08 | 2010-12-31 | 2011-10-05 | 4719006.63 | 11.310 | 0060500
69 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DALLAS |  | 07 | 0066502 | This project involves the repaving and 2 foot widening for approximately 5 miles of State Highway 66 from Marengo County line to State Highway 5 in Dallas County | Pavement Improvement | 2010-02-12 | 2010-03-15 | 2010-05-26 | 2011-03-26 | 1302509.19 | 4.959 | 0066502
70 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MARENGO |  | 07 | 0069521 | This project involves the widening of approximately 12 miles of State Highway 69 in Marengo County from US Highway 43 to the Hale County line | Pavement Improvement | 2009-07-23 | 2009-07-30 | 2009-10-16 | 2010-01-16 | 947089.69 | 11.643 | 0069521
71 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | FRANKLIN |  | 04 | 0069523 | This project involves the repaving of about 4 miles of State Highway 69 from Interstate 65 in Good Hope to the US Highway 31 intersection in Cullman | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-10-31 | 2009-12-07 | 1276909.8 | 3.700 | 0069523
72 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | HALE |  | 07 | 0069525 | This project involves the repaving and extension of culvert pipes to improve roadside safety along 2 milesof State Highway 69 from the Marengo County line to US Highway 80 in Hale County | Pavement Improvement | 2009-07-23 | 2009-07-30 | 2009-10-16 | 2010-01-16 | 491005.69 | 1.994 | 0069525
73 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | 01 | 0069526 | This project involves repaving approximately 9 miles of State Highway 69 from north of County Road 23 (Salt Works Road) to about a mile north of County Road 368 (Dalmation Lane) in Clarke County | Pavement Improvement | 2010-03-02 | 2010-04-22 | 2010-06-30 | 2010-09-14 | 2229820.48 | 8.781 | 0069526
74 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MARENGO |  | 07 | 0069529 | This project involves the repaving of about 12 miles of State Highway 69 in Marengo County from US Highway 43 to the Hale County line | Pavement Improvement | 2009-07-23 | 2009-07-30 | 2009-10-16 | 2010-01-16 | 2497955.21 | 11.643 | 0069529
75 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BLOUNT |  | 04 | 0075515 | This project involves the repaving of aprroximately 4 miles of State Highway 75 from from Brooks Lane (County Road 363) in Allgood to 2nd Street (County Road 58) in Oneonta | Pavement Improvement | 2009-09-15 | 2009-10-02 | 2009-12-15 | 2010-08-19 | 1590122.66 | 3.570 | 0075515
76 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | DE KALB |  | 04 | 0075516 | The project involves the repaving and widening of 4 miles of State Highway 75 (McCurdy Avenue) from about a half mile north of County Road 50 (Traylor Street) in Fyffe to just south of State Highway 35 (Lowell Barron Highway) in Rainsville. Dekalb County | Pavement Improvement | 2009-10-06 | 2009-10-20 | 2010-05-15 | 2010-06-23 | 2723786.54 | 4.030 | 0075516
77 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | Multiple | 0079510 | This project involvesthe repaving of approximately 5 miles of State Highway 79 (Pinson Valley Parkway) from Winewood Road to State Highway 151 just west of Pinson in Jefferson County | Pavement Improvement | 2009-07-21 | 2009-08-10 | 2009-10-31 | 2010-06-02 | 2450035.84 | 5.200 | 0079510
78 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | PIKE |  | 02 | 0093501 | This project involves the repaving of about 2 miles of State Highway 93 from Us Highway 231 to the North city limits of Brundidge | Pavement Improvement | 2009-08-10 | 2009-09-02 | 2010-06-01 | 2009-10-22 | 721163.47 | 2.250 | 0093501
79 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | 03 | 0097503 | This project involves the repaving and 2 foot widening of approximately 1 mile State Highway 97 from Crenshaw County line to north of US Highway 31 near Letohatchee | Pavement Improvement | 2009-08-13 | 2009-10-08 | 2010-03-31 | 2011-03-11 | 572236.14 | 1.187 | 0097503
80 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | 0102530 | This project involves the repaving of about 7 miles of State Highway 102 from the Fayette County Line to the intersection with Old Birmingham Highway in Walker County | Pavement Improvement | 2010-02-02 | 2010-04-15 | 2010-08-01 | 2010-10-18 | 924020.85 | 6.896 | 0102530
81 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | 0103508 | This project involves the repaving and widening of 9 miles of State Highway 103 from the Florida State line to State Highway 52 in Slocomb | Pavement Improvement | 2009-11-16 | 2009-12-04 | 2010-07-20 | 2010-07-20 | 2413628.45 | 8.933 | 0103508
82 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | COOSA |  | 03 | 0115503 | This project involves the repaving of about 3 miles of State Highway 115 from State Highway 9 to US Highway 280 | Pavement Improvement | 2009-07-08 | 2009-07-23 | 2009-09-02 | 2010-10-14 | 1157297.85 | 3.190 | 0115503
83 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | JACKSON |  | 05 | 0117505 | This project involves the repaving of State Highway 117 in Jackson County from the intersection with State Highway 71 north for about 6 miles. | Pavement Improvement | 2010-01-19 | 2010-04-13 | 2010-07-01 | 2010-07-19 | 1717468.17 | 5.730 | 0117505
84 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | 0118508 | This project involves the repaving of about 4 miles of US Highway 78 in Carbon Hill from 4th Street to Ripley Loop Road. | Pavement Improvement | 2009-09-25 | 2009-10-09 | 2009-12-11 | 2010-06-01 | 1378812.75 | 3.676 | 0118508
85 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | AUTAUGA |  | 02 | 0123200 | This project involves the repaving of approximatley 3 miles of Autauga County Road 37 from Autauga County Road 24 to the Chilton County Line and is located North of Billingsley, Alabama. | Pavement Improvement | 2010-01-19 | 2010-03-02 | 2010-03-15 | 2010-06-24 | 265000 | 2.840 | 0123200
86 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | 0124500 | This project involves the repaving of approximately 10 miles of Old Birmingham Highway from US Highway 78 south to the intersection with State Highway 69 in Walker County. | Pavement Improvement | 2010-02-02 | 2010-04-15 | 2010-08-01 | 2010-10-18 | 1566988.39 | 10.896 | 0124500
87 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | FAYETTE |  | 04 | 0129502 | This project involves the repaving of approximately 7 miles of State Highway 129 from US Highway 43 to County Road 49 in Hubbertville | Pavement Improvement | 2009-08-10 | 2009-08-27 | 2009-10-27 | 2010-03-12 | 1620647.41 | 7.260 | 0129502
88 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE |  | 05 | 0133501 | This project involves the repaving of State Highway 133 from State Highway 20 to Magnum Street in the city of Florence | Pavement Improvement | 2010-04-21 | 2010-05-06 | 2010-10-15 | 2010-11-19 | 5086063.39 | 8.386 | 0133501
89 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 0133503 | This project involves the repaving of State Highway 133 from near Old Highway 20 (Colbert County Road 22) to Lincoln Avenue just south of Avalon Avenue | Pavement Improvement | 2010-06-23 | 2010-07-21 | 2010-10-15 | 2010-09-21 | 492906.7 | 2.545 | 0133503
90 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BIBB |  | 06 | 0139502 | This project involves the repaving of 7 miles of State Highway 139 from Six Mile Creek to just north of the Shelby County line | Pavement Improvement | 2009-09-10 | 2009-10-08 | 2010-02-27 | 2010-05-21 | 2244145.93 | 7.104 | 0139502
91 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | TALLADEGA |  | 03 | 0148500 | This project involves the repaving and 2 foot widening of about 2 miles of State Highway 148 from State Highway 21 to the east city limits of Sylacauga | Pavement Improvement | 2009-07-23 | 2009-08-07 | 2009-10-10 | 2009-11-23 | 596730.26 | 1.780 | 0148500
92 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | Multiple | 0154501 | This project involves repaving and widening for about 8 miles on State Highway 154 from 1 mile west of County Road 24 to US Highway 43 in Clarke County | Pavement Improvement | 2010-04-14 | 2010-04-20 | 2010-07-31 | 2011-04-19 | 3392134.11 | 7.600 | 0154501
93 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHILTON |  | 06 | 0155500 | This project involves the repaving and widening of 4 miles of State Highway 155 in Chilton County from near County Road 33 to the Shelby County line | Pavement Improvement | 2009-08-18 | 2009-09-03 | 2009-12-31 | 2010-05-28 | 1739561.92 | 4.076 | 0155500
94 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 0157514 | This project involves the repaving and the upgrade of bridge rails to current safety standards along State Highway 157 from the lawrence County Line to State Highway 20 in Colbert County | Pavement Improvement | 2009-09-15 | 2009-09-30 | 2010-07-01 | 2010-05-30 | 3557416.49 | 7.495 | 0157514
95 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | WILCOX |  | 07 | 0162501 | This project involves the repaving of 3 miles State Highway 162 from west of Dixon Creek to west of County Road 28 in Wilcox County | Pavement Improvement | 2010-02-09 | 2010-05-24 | 2010-07-31 | 2011-03-11 | 634261.27 | 3.141 | 0162501
96 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | PERRY |  | 07 | 0175500 | This project involves the repaving and widening of State Highway 175 from State Highway 14 near Heiberger to State Highway 5 in Perry County | Pavement Improvement | 2009-09-11 | 2010-04-27 | 2010-07-01 | 2011-04-01 | 1730838.95 | 5.382 | 0175500
97 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 0188501 | This project involves the repaving of about 9 miles of State Highway 188 from Franklin Creek to Oddfellows Cemetery in Baldwin County | Pavement Improvement | 2010-01-19 | 2010-02-10 | 2010-04-30 | 2010-06-10 | 1268047.1 | 8.670 | 0188501
98 | ALABAMA | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 0192901 | This project provides for grading the road so it can be paved to a four lane roadway from 1500' South of Lake Yahoo to SR-1 (US-431) in Anniston. The project will be partial base and pave wih a bridge culvert and a new bridge. | New Construction | 2009-09-21 | 2009-10-09 | 2011-05-13 |  | 36100378.68 | 2.560 | 0192901
99 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | 0196500 | This project involves the repaving of Magnolia Avenue from State Highway 52 to State Highway 27 in Geneva | Pavement Improvement | 2010-01-19 | 2010-02-24 | 2010-04-15 | 2010-04-15 | 463771.24 | 1.690 | 0196500
100 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | 0198500 | This project involves the repaving and widening of approximately 2 miles of State Highway 198 in Barbour County from just east of State Highway 239 to State Highway 30 | Pavement Improvement | 2010-02-03 | 2010-02-22 | 2010-07-23 | 2010-07-23 | 462493.22 | 1.610 | 0198500
101 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | 0210200 | This project involves the repaving of County Road 32 from Sate Highway 59 to County Road 87 in Baldwin County | Pavement Improvement | 2010-05-13 | 2010-06-07 | 2010-08-01 | 2011-01-27 | 265000 | 7.000 | 0210200
102 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 0213502 | This project involves the repaving and widening of about 3 miles of State Highway 213 (Shelton Beach Road) from State Highway 158 (Industrial Parkway) to US Highway 43 (Saraland Boulevard) in Saraland | Pavement Improvement | 2009-07-22 | 2009-09-29 | 2009-11-30 | 2010-04-30 | 666232.44 | 2.880 | 0213502
103 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BULLOCK |  | 02 | 0223501 | This project involves the repaving and 2 foot widening of a bout a mile of State Highway 223 (Baskin Street) from the Bullock County High School to the junction of US Highway 82 in Union Springs | Pavement Improvement | 2009-09-10 | 2009-09-28 | 2010-01-01 | 2010-03-10 | 266301.56 | 0.750 | 0223501
104 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | 0239501 | This project involves the repaving and widening of 2 miles of State Highway 239 from State Highway 51 to State Highway 51 North in Barbour County | Pavement Improvement | 2010-02-03 | 2010-02-22 | 2010-07-23 | 2010-07-23 | 482317.97 | 1.916 | 0239501
105 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | FRANKLIN |  | 04 | 0241501 | This project involves the repaving of about a mile of State Highway 241 from just south of the Marion County line to State Highway 237 in Franklin County | Pavement Improvement | 2009-07-30 | 2009-08-28 | 2010-05-01 | 2009-10-21 | 840274.79 | 1.024 | 0241501
106 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | 0263501 | This project involves the repaving and 2 foot widening of approximately 9 miles of State Highway 263 from the Butler County line to State Highway 21 | Pavement Improvement | 2010-01-26 | 2010-03-03 | 2010-06-30 | 2011-01-11 | 2558166.21 | 8.480 | 0263501
107 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | WILCOX |  | 07 | 0265500 | This project involves the repaving and safety widening for about 7 miles of State Highway 265 from just north of County Road 51 to State Highway 41 in Wilcox County | Pavement Improvement | 2010-02-09 | 2010-05-24 | 2010-07-31 | 2011-03-11 | 1531762.17 | 6.830 | 0265500
108 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | CHEROKEE |  | 03 | 0273500 | The project involves the repaving and widening of approximately 16 miles of State Highway 273 from State Highway 68 in Leesburg to State Highway 35 near Blanche | Pavement Improvement | 2009-08-12 | 2010-05-21 | 2010-09-30 | 2010-12-06 | 3816700.1 | 15.836 | 0273500
109 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | 0325201 | This project involves the repaving of Barbour County Road 49 from US Highway 82 to Barbour County Road 89 at Springhill | Pavement Improvement | 2010-05-20 | 2010-06-14 | 2010-09-30 | 2010-11-30 | 265000 | 4.203 | 0325201
110 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | BULLOCK |  | 02 | 0621200 | This project will completely rebuild the pavement structure (full depth reclamation) down to the subgrade, then the pavement will be widened and repaved approximately 8 miles of Bullock County Road 2 | Pavement Improvement | 2009-10-22 | 2009-11-18 | 2010-02-03 | 2011-01-28 | 265000 | 7.610 | 0621200
111 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | BUTLER |  | 02 | 0707200 | This project involves the repaving and widening of County Road 15 from State Highway 106 to County Road 38 in Butler County | Pavement Improvement | 2010-05-20 | 2010-06-08 | 2010-08-31 | 2010-09-23 | 265000 | 7.902 | 0707200
112 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 0800214 | This project involves the repaving of Hillyer Robinson Industrial Parkway from Greenbrier Road to city limits of Anniston | Pavement Improvement | 2010-07-29 | 2010-09-15 | 2011-04-30 | 2012-10-29 | 775679.93 | 0.790 | 0800214
113 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 0800215 | This project involves the repaving of Frank Akers Road from Hillyer Robinson Road to Coleman Road in the city of Anniston in Calhoun County | Other | 2010-07-29 | 2010-09-15 | 2011-04-30 | 2012-10-29 | 217672 | 0.370 | 0800215
114 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN |  | 03 | 0800216 | This project involves the replacement of a bridge with an inventory number 1001 and its approaches on Prickett Trail (County Road 553) over Tallassechatchee Creek | Pavement Improvement | 2010-05-25 | 2010-06-09 | 2010-12-01 | 2011-05-05 | 265000 | 0.255 | 0800216
115 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CHAMBERS |  | 03 | 0928200 | This project will completely rebuild the pavement structure (full depth reclamation) down to the subgrade, then the pavement will be repaved approximately 5 miles of County Road 267 in Chambers County | Pavement Improvement | 2009-07-27 | 2009-10-02 | 2009-11-15 | 2010-03-31 | 265000 | 5.571 | 0928200
116 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CHEROKEE |  | 03 | 1006201 | "This project involves the repaving of approximately 4 miles of Cherokee County Road 71 (Centre Rd.) from 0.6 miles north of Cherokee County Road 59 ( to the Terrapin Creek Bridge south of Centre | Pavement Improvement | 2009-12-29 | 2010-05-21 | 2010-06-11 | 2010-06-30 | 265000 | 4.200 | 1006201
117 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | 1205201 | This project involves the repaving and widening of County Road 32 from County Road 9 to State Highway 17 in Choctaw County | Pavement Improvement | 2010-05-18 | 2010-07-02 | 2010-07-12 | 2010-10-07 | 265000 | 6.130 | 1205201
118 | ALABAMA | Underway | C250 | Highway Infrastructure Investment Grant | ALABAMA | CLARKE |  | 07 | 1301200 | This project involves the replacement of a bridge on Clarke County Road 15 over Bassetts Creek | Other | 2010-02-11 | 2010-02-11 | 2011-01-01 |  | 265000 | 0.110 | 1301200
119 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CLAY |  | 03 | 1405201 | "This project involves the repaving of approximately 7 miles of Clay County Road 35 (Bluff Springs Road) from the Tallapoosa County Line to the intersection of Clay County Road 132 (Sardis Road) south of Ashland | Pavement Improvement | 2010-03-02 | 2010-04-20 | 2010-06-18 | 2010-08-06 | 265000 | 6.900 | 1405201
120 | ALABAMA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 1709200 | This project involves the repaving of County Road 57 from County Road 61 to the Joe Wheeler Highway (State Highway 20) in Tuscumbia | Pavement Improvement | 2009-08-19 | 2009-09-30 | 2010-06-26 | 2009-12-22 | 330972.08 | 2.727 | 1709200
121 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT |  | 05 | 1710201 | This project involves the replacement of a bridge with inventory number 001173 over Rock Creek on Colbert County Road 1 (Maud Rd.) | Other | 2009-08-27 | 2009-08-27 | 2011-02-15 | 2011-10-12 | 107767.49 | 0.246 | 1710201
122 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | 1717200 | This project involves the repaving of 1 mile of River Road from County Road 48 to Brick School Road in Muscle Shoals | Pavement Improvement | 2009-10-13 | 2010-04-22 | 2010-05-19 | 2010-05-19 | 135105.43 | 0.893 | 1717200
123 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CONECUH |  | 02 | 1818202 | "This project involves the repaving of approximately 4 miles of Conecuh County Road 23 from U.S. Highway 31(N. Jackson Street) northwesterly to Interstate 65 (I-65) north of Castleberry | Pavement Improvement | 2009-11-09 | 2009-12-08 | 2010-01-31 | 2010-04-29 | 265000 | 4.160 | 1818202
124 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | COOSA |  | 03 | 1907200 | This project involves the repaving of County Road 85 from County Road 50 at Kellyton to County Road 86 in Coosa County | Pavement Improvement | 2010-05-18 | 2010-06-05 | 2010-08-30 | 2010-10-04 | 265000 | 6.200 | 1907200
125 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COFFEE |  | 02 | 1E34600 | This project involves the repaving of County Road 709 in Enterprise from State Highway 167 to State Highway 134 | Pavement Improvement | 2009-09-11 | 2009-10-12 | 2010-07-01 | 2010-08-27 | 265000 | 2.589 | 1E34600
126 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CRENSHAW |  | 02 | 2032200 | "This project involves the widening and repaving of Covington County Road 98 from U.S. Highway 84 to Covington County Road 49 in Covington County. | Pavement Improvement | 2009-10-07 | 2009-11-02 | 2010-07-29 | 2010-07-29 | 265000 | 1.241 | 2032200
127 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CRENSHAW |  | 02 | 2111202 | "This project involves the repaving of approximately 5 miles of Crenshaw County Road 6 (Glenwood Rd./Luverne St.) from the Luverne | Pavement Improvement | 2010-05-18 | 2010-06-22 | 2010-09-30 | 2010-11-09 | 265000 | 3.963 | 2111202
128 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | CULLMAN |  | 04 | 2215200 | This project involves the repaving of County Road 1069 from County Road 1043 to County Road 1101 in Cullman County | Pavement Improvement | 2010-05-13 | 2010-07-14 | 2010-09-30 | 2011-02-18 | 265000 | 6.329 | 2215200
129 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2304200 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 31 from U.S. Routhe 84/Alabama Route 12 to Dale County Road 43.in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 62917 | 3.969 | 2304200
130 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2311201 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 73 from Dale County Road 14 to the Henry County Line in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 70257 | 4.432 | 2311201
131 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2311202 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 14 from Dale County Road 67 to Dale County Road 73 in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 20449 | 1.290 | 2311202
132 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2315201 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 83 from Dale County Road 62 to Dale County Road 36 in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 51599 | 3.255 | 2315201
133 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 2331200 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 63 from U.S. Routhe 231/Alabama Route 53 to Dale County Road 14.in Dale County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 33131 | 2.090 | 2331200
134 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | DALLAS |  | 07 | 2446200 | This projects involves the repaving and widening of county road 81 from State Highway 22 to State Highway 22 at Valley Grande | Pavement Improvement | 2010-06-01 | 2010-07-13 | 2010-08-31 | 2011-03-31 | 265000 | 3.627 | 2446200
135 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE |  | 02 | 2601201 | This projects involed paving the shoulder and traffic striping along Rifle Range Road from Redland Road to Mitchell Creek Road | Pavement Improvement | 2010-01-26 | 2010-02-03 | 2010-03-05 | 2010-04-12 | 297940.2 | 6.610 | 2601201
136 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE |  | 02 | 2606202 | This project involves the repaving andstriping of Main Street from 1st Avenue east to the Eclectic city limits | Pavement Improvement | 2010-02-24 | 2010-03-29 | 2010-05-11 | 2010-05-11 | 265000 | 1.634 | 2606202
137 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | 2710200 | "This project involves the widening and repaving of approximately 5 miles of Escambia County Road 17 (Stanley Rd.) from Escambia County Road 27 (Robinsonville Rd.) to Alabama Highway Route 113 | Pavement Improvement | 2010-01-05 | 2010-02-02 | 2010-04-28 | 2010-06-15 | 265000 | 4.720 | 2710200
138 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH |  | 04 | 2810200 | This proeject involves the milling and repaving of Gilley Road from Centre Road to the Cherokee County line | Pavement Improvement | 2010-01-27 | 2010-09-22 | 2010-10-21 | 2010-10-20 | 265000 | 1.410 | 2810200
139 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DE KALB |  | 04 | 2F07600 | This project involves the widening and repaving of County Road 89 from the Fort Payne city limits to County Road 78. | Pavement Improvement | 2010-05-12 | 2010-06-04 | 2010-08-15 | 2010-08-10 | 265000 | 2.900 | 2F07600
140 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | FRANKLIN |  | 04 | 3000209 | The replacement of the bridge with identification number 001134 and the roadway approaches over Bear Creek located on Franklin County Road 93 in Franklin County, Alabama. | Bridge Replacement | 2010-05-25 | 2010-06-24 | 2010-12-01 | 2011-01-19 | 265000 | 0.072 | 3000209
141 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | 3131200 | "This project involves the repaving and widening of approximately 3 miles of Geneva County Road 4 (Goathill Road) from Alabama State Highway 87 to Geneva County Road 120 (Ausley Road) West of Geneva | Other | 2009-11-09 | 2009-12-28 | 2010-02-26 | 2010-07-06 | 265000 | 6.180 | 3131200
142 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | GREENE |  | 07 | 3200205 | This project involves the replacement of bridge over South Needham Creek on County Road 25 | Pavement Improvement | 2010-05-11 | 2010-06-11 | 2010-09-26 | 2010-11-29 | 265000 | 0.060 | 3200205
143 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | HALE |  | 07 | 3314200 | This project involves the widening and resurfacing of County Road 32 from State Highway 69 to State Highway 25 | Pavement Improvement | 2010-04-15 | 2010-05-05 | 2010-11-11 | 2011-12-12 | 530000 | 6.456 | 3314200
144 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | HENRY |  | 02 | 3408200 | "This project involves the widening and repaving of Henry County Road 99 from Henry County Road 41 to Henry County Road 107 in Abbeville | Pavement Improvement | 2009-08-21 | 2009-09-09 | 2010-06-01 | 2010-02-04 | 265000 | 1.706 | 3408200
145 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON |  | 02 | 3500214 | This project will replace the bridge with inventory number 003313 over Cedar Creek on East Cook Road (County Road 438) about a half north of Ed Tolar Road in Houston County | Bridge Replacement | 2009-07-14 | 2009-08-03 | 2010-05-01 | 2010-07-21 | 265000 | 0.038 | 3500214
146 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | JACKSON |  | 05 | 3621201 | The widening and repaving of Jackson County Road 88 from Alabama Route 71 to the Dekalb County Line in Jackson County, Alabama. | Pavement Improvement | 2010-05-12 | 2010-07-09 | 2010-08-15 | 2010-12-21 | 354005 | 4.150 | 3621201
147 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 3713200 | Rex Lake Road is currently a 2 lane county road that serves the Barber Motorsports facility and the recently constructed Bass Pro Shop. The project will convert the existing 2 lane to a 4 lane divide | Pavement Improvement | 2009-10-30 | 2009-11-16 | 2011-05-09 |  | 5497447.75 | 0.956 | 3713200
148 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LAMAR |  | 04 | 3804200 | "This project involves the repaving of approximately 10 miles of Lamar County Road 49 & 20 (Pickens St.) from the Northern Right of Way of the Luxapallila Railroad in Kennedy | Pavement Improvement | 2009-11-04 | 2009-12-03 | 2010-02-20 | 2010-03-08 | 265000 | 9.850 | 3804200
149 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LAWRENCE |  | 05 | 4000219 | The project involves the replacement of a bridge with the inventory number 003222 on County Road 129 over Pool Creek in Lawrence County | Bridge Replacement | 2009-09-14 | 2009-10-28 | 2010-07-31 | 2009-12-22 | 121765.18 | 0.005 | 4000219
150 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LAWRENCE |  | 05 | 4000220 | "This project will replace the bridge for Sandy Creek on Lawrence County Road 150. The bridge has an inventory number of 002345 and wil be replace by a bridge culvert that has 3 barrels that are 10 f | Pavement Improvement | 2009-11-06 | 2009-11-20 | 2010-03-24 | 2010-03-24 | 128994.63 | 0.006 | 4000220
151 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LEE |  | 03 | 4107200 | This project involves the widening and repaving of County Road 401 from County Road 166 to County Road 165 | Pavement Improvement | 2010-05-26 | 2010-08-01 | 2010-09-30 | 2010-12-21 | 234877.27 | 1.288 | 4107200
152 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | 4311200 | This project involves the repaving of County Road 26 from State Highway 21 to west of County Highway 6 | Pavement Improvement | 2010-01-28 | 2010-02-13 | 2010-03-30 | 2010-05-06 | 265000 | 8.989 | 4311200
153 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MACON |  | 03 | 4424203 | This project involves the repaving of County Road 54 from East of the Notasulga city limits to County Road 53 | Pavement Improvement | 2010-01-19 | 2010-02-01 | 2010-04-15 | 2010-04-30 | 265000 | 2.810 | 4424203
154 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | 4500215 | This project will replace a bridge with inventory number 009682 and upgrade the width and safety of the approaching roadway on County Road 50 (Douglass Road) over Douglass Branch approximately a half mile west of County Road 19 (Jeff Road) in Monrovia | Pavement Improvement | 2010-05-18 | 2010-06-22 | 2010-10-15 | 2011-06-08 | 390770 | 0.129 | 4500215
155 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | 4500216 | This project involves he replacement of a bridge on Low Gap Road (County Road 286) over Glover Branch in Madison County | Bridge Replacement | 2010-07-14 | 2010-09-29 | 2010-09-30 | 2011-05-20 | 201278.01 | 0.008 | 4500216
156 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MARENGO |  | 07 | 4606201 | The repaving of Marengo County Road 33 from U.S. 43/Alabama Route 13 to Marengo County Road 47 in Marengo County, Alabama. | Pavement Improvement | 2010-05-19 | 2010-06-21 | 2010-08-31 | 2010-08-18 | 265000 | 4.100 | 4606201
157 | ALABAMA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | MARENGO |  | 07 | 4738200 | This project involves the repaving of County Road 51 from County Road 42 to US Highway 278 (State Highway 74) in Marengo County | Pavement Improvement | 2010-05-19 | 2010-06-17 | 2010-08-31 | 2010-09-21 | 265000 | 1.590 | 4738200
158 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MARSHALL |  | 04 | 4803201 | This project involves repaving County Road 73 (High Point Road) from Old Oneonta Road to Oneonta Cut-off Road | Pavement Improvement | 2010-05-04 | 2010-06-18 | 2010-08-31 | 2010-08-20 | 196513.15 | 0.767 | 4803201
159 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | 5027200 | This project involves the widening and repaving of County Road 45 from State Highway 21 to County Road 7 | Pavement Improvement | 2010-04-28 | 2010-05-17 | 2010-08-12 | 2010-11-10 | 265000 | 1.961 | 5027200
160 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | 5218200 | This project involves the repaving of South Seneca Drive From the Trinity town limits to Deanna Bridge Highway | Pavement Improvement | 2009-06-29 | 2009-07-02 | 2010-07-01 | 2010-08-18 | 55906.97 | 1.000 | 5218200
161 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | 5222200 | This project involves the repaving of less than a mile of Indian Hills Road from Lincoya Circle to Ben Poole Road in the city of Decatur | Pavement Improvement | 2009-07-17 | 2009-08-01 | 2010-07-15 | 2010-12-06 | 84137.1 | 1.520 | 5222200
162 | ALABAMA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 05 | 5226200 | This project involves repaving and striping of Finley Road from State Highway 20 to Gate | Pavement Improvement | 2010-04-22 | 2010-06-28 | 2010-10-01 | 2010-08-10 | 566265 | 1.690 | 5226200
163 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | PERRY |  | 07 | 5303200 | This project involves the repaving of about 7 miles of County Road 12 from 2 miles east of State Highway 183 to State Highway 5 in Perry County | Pavement Improvement | 2009-10-13 | 2010-02-02 | 2010-04-08 | 2011-09-13 | 265000 | 6.910 | 5303200
164 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | PICKENS |  | 07 | 5422200 | The project involves the milling, repavaing, and striping of County Road 85 from the Sumter County line to State Highway 17 | Pavement Improvement | 2010-01-27 | 2010-04-02 | 2010-11-11 | 2010-10-28 | 265000 | 4.493 | 5422200
165 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | PIKE |  | 02 | 5505202 | This project involves the repaving of County Road 2276 from the Crenshaw County line to County Road 2290 and also the repaving of County Road 2290 from County Road 2276 to County Road 2262 near Henderson in Pike County | Pavement Improvement | 2009-07-16 | 2009-07-23 | 2010-05-01 | 2010-06-28 | 265000 | 5.565 | 5505202
166 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | RANDOLPH |  | 03 | 5605200 | This project involves the widening and repaving of Randolph County Road 82 from the Meadows Bridge (Little Tallapoosa River) to Randolph County Road 87. | Pavement Improvement | 2009-09-28 | 2009-10-22 | 2010-05-25 | 2010-06-04 | 265000 | 5.642 | 5605200
167 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL |  | 03 | 5704200 | This project will relocate and replace a bridge on Russell County Road 4 over Weolustee Creek north of Pitttsview | Pavement Improvement | 2009-09-30 | 2009-10-09 | 2010-08-10 | 2012-07-26 | 265000 | 0.056 | 5704200
168 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | ST CLAIR |  | 06 | 5824200 | The project involves the repaving of County Road 12 from County Road 6 to State Highway 174 | Pavement Improvement | 2010-05-04 | 2010-06-14 | 2010-09-14 | 2010-09-24 | 530000 | 7.222 | 5824200
169 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LIMESTONE | DECATUR | 05 | 5A20600 | This project involves the widening and repaving of Lucas Ferry Road (County Road 45) from Harris Station Road (County Road 45) to Nuclear Plant Road (County Road 677). | Pavement Improvement | 2010-06-01 | 2010-07-01 | 2010-08-30 | 2010-08-13 | 265000 | 2.050 | 5A20600
170 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | SUMTER |  | 07 | 6020200 | "This project involves the repaving and extending the culvert pipes to improve the roadside safety of approximately 2 miles of Sumter County Road 27 from the Mississippi State line south to Sumter Co | Pavement Improvement | 2009-10-16 | 2009-11-04 | 2010-08-31 | 2011-04-06 | 265000 | 7.010 | 6020200
171 | ALABAMA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | TALLADEGA |  | 03 | 6111200 | This project involves the repaving of Horn's Lake Road (County Road 209) from State Highway 77 to the Clay County line | Pavement Improvement | 2010-06-01 | 2010-07-15 | 2010-08-10 | 2010-09-22 | 358844.72 | 2.700 | 6111200
172 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | TALLAPOOSA |  | 03 | 6233200 | "This project includes widening and repaving of approximately 7 milles of Tallapoosa County Road 44 (Dudleyville Road) from Tallapoosa County Road 32 (Denver Road) to the Chambers County Line | Pavement Improvement | 2010-01-07 | 2010-03-01 | 2010-05-31 | 2010-07-08 | 265000 | 7.250 | 6233200
173 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 6303200 | This project involves the milling and paving of Hagler Coaling Road (County Road 239) from Serty Boyd Road (County Road 240) to Clements Road (State Highway 566) in Tuscaloosa County | Pavement Improvement | 2010-05-25 | 2010-06-21 | 2010-08-07 | 2011-03-11 | 1221280 | 5.900 | 6303200
174 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 6312200 | The replacement of the bridge and roadway approaches with a triple barrel box bridge culvert with identification number 000864 over Cooley Creek on Tuscaloosa County Road 97 (Eastern Valley Road) near Tuscaloosa, Alabama. | Pavement Improvement | 2010-06-24 | 2010-08-09 | 2011-03-31 | 2011-04-07 | 769000 | 0.013 | 6312200
175 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | WASHINGTON |  | 01 | 6500206 | The replacement of the bridge over the Escatawpa River with a new Precast Bridge in Washington County, Alabama. | Bridge Replacement | 2010-05-27 | 2010-06-08 | 2011-01-31 | 2011-04-14 | 265000 | 0.098 | 6500206
176 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | WILCOX |  | 07 | 6617200 | The repaving of Wilcox County Road 29 from Gees Bend Landing to 0.47 mile north of Chilatchee Park Road in Wilcox County, Alabama. | Pavement Improvement | 2010-06-02 | 2010-06-22 | 2010-08-09 | 2011-02-18 | 265000 | 7.149 | 6617200
177 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | WINSTON |  | 04 | 6721200 | This project involves the repaving of County Road 14 from County Road 41 to County Road 39 in Winston County | Pavement Improvement | 2010-05-18 | 2010-07-12 | 2010-08-15 | 2010-08-17 | 266297.11 | 3.040 | 6721200
178 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7005600 | This project will realign 3 intersections in the City of Hoover and replace the existing signals. The realignments will improve driver's sight distance and visibility. | Pavement Improvement | 2009-12-15 | 2010-01-12 | 2011-06-30 | 2013-01-15 | 1878317.89 | 0.166 | 7005600
179 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7020600 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Widening | 2010-05-05 | 2010-06-21 | 2011-03-20 |  | 1375027 | 0.600 | 7020600
180 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7045600 | This project will add a center two way left turn lane to Jefferson Avenue (County Road 18) from the Birmingham City limits to 50th Street. | Other | 2010-02-26 |  | 2011-08-01 |  | 1659402.64 | 1.500 | 7045600
181 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 07 | 7045601 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Improvement | 2009-11-12 |  | 2011-03-27 |  | 2624716.25 | 0.750 | 7045601
182 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | 7112604 | This project involves the widening and repaving of County 17 from north of County Road 270 to apprroximately south of Lacey Avenue. This project includes the replacement of the bridge over Beaverdam Creek | Other | 2010-01-29 | 2010-08-23 | 2010-10-10 | 2011-06-14 | 265000 | 0.480 | 7112604
183 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 07 | 7173600 | This project will add dual left turn lanes on East Lake Blvd to SR-79 SB. The improvements will help relieve congestion by allowing more vehicles to make a left turn in a shorter amount of time. | Pavement Widening | 2010-05-26 | 2010-08-11 | 2011-12-10 |  | 339737 | 0.170 | 7173600
184 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 07 | 7229601 | This project will add a center two-way left turn lane for the length of the project. This additional turn lane will allow traffic making a left turn to move out of the through lane and improve conges | Pavement Widening | 2009-11-09 | 2010-02-01 | 2010-11-24 |  | 2900626.44 | 1.400 | 7229601
185 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7273600 | The repaving of Jefferson County Road 2133 known as Deefoot Parkway from U.S. Route 11/Alabama Route 7 to Interstate 59. | Pavement Improvement | 2010-05-26 | 2010-06-15 | 2010-08-10 | 2010-09-04 | 265000 | 1.584 | 7273600
186 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 7321600 | This project is for the relocation of utilities that conflict with the construction of Chapel Lane Extension from Al Seier Road to Galleria Boulevard in Birmingham. | Other | 2010-02-25 | 2010-06-29 |  |  | 1659402.64 | 0.750 | 7321600
187 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7400600 | This project involves the repaving of approximately 3 miles of Friendship Road in the city of Oxford from SR-21 to Boiling Spring Road | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2010-07-28 | 2011-05-19 | 665600 | 7.200 | 7400600
188 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7401601 | This project involves the installation of a new traffic signal at the intersection of Noble Street (County Road 105) and Greenbrier Dear Road (County Road 198) | Safety/Traffic Management | 2010-04-13 |  | 2011-03-07 | 2010-05-06 | 105726 | 0.000 | 7401601
189 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7425600 | The project will consist of pole replacement, new traffic lights to upgrade the traffic signal at Bill Robinson Parkway. | Safety/Traffic Management | 2010-04-13 |  | 2011-03-07 | 2011-05-06 | 105000 | 0.000 | 7425600
190 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7431600 | This project involves the repaving of Alexandria/Jacksonville Road from Francis Street to South Jacksonville city limits | Pavement Improvement | 2010-04-28 | 2010-06-02 | 2010-09-01 | 2010-11-30 | 400000 | 1.570 | 7431600
191 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | 7460600 | This project involves the replacement of a bridge on Eulaton Road (County Road 81), north of State Highway 202 near County Road 109 | Pavement Improvement | 2010-05-11 | 2010-06-21 | 2010-08-30 | 2011-02-25 | 409530 | 0.208 | 7460600
192 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7507600 | This project will replace a bridge and upgrade the width and safety of the approaching roadway on Michigan Avenue over the CSX railroad in Mobile | Pavement Improvement | 2010-05-06 | 2010-09-01 | 2011-05-15 |  | 3583781.38 | 0.191 | 7507600
193 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7548600 | This project involves the repaving about a mile of Springhill Avenue from McGregor Avenue to Intersate 65 in the city of Mobile | Pavement Improvement | 2009-08-27 | 2009-09-03 | 2009-11-30 | 2009-12-10 | 309146.29 | 1.300 | 7548600
194 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7548601 | This project involves the repaving of less than a mile of Springhill Avenue from Interstate 65 to Moffet Road in the city of Mobile | Pavement Improvement | 2009-08-27 | 2009-09-03 | 2009-11-30 | 2009-12-10 | 136802.85 | 0.600 | 7548601
195 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7552600 | This project involves the repaving of Howells Ferry Road (County Road 605) from Snow Road (County Road 25) to Cody Road (County Road 429) | Pavement Improvement | 2010-01-28 | 2010-03-10 | 2010-05-31 | 2010-08-30 | 1322100 | 5.000 | 7552600
196 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7560600 | This project involves the repaving of about 3 miles of West Main Street from Prichard Avenue to Branch Avenue in the city of Mobile | Pavement Improvement | 2009-06-22 | 2009-07-24 | 2010-08-31 | 2010-12-27 | 903586.96 | 6.448 | 7560600
197 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7573600 | This project involves traffic stripe, markings, legends and pavement markers on CR-41 (Celeste Road) from SR-13 (US-43) in Saraland to Lafitte Road. | Safety/Traffic Management | 2009-12-30 | 2010-01-18 | 2010-02-28 | 2010-02-11 | 114172.55 | 2.500 | 7573600
198 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MACON | MOBILE | 03 | 7597600 | This project involves the repaving and widening of Viaduct Road from east of Mike Box Bridge to Warrior Gulf and from Mike Box Bridge to Southern Ionix. This project also includes the repaving of viaduct Road from Howell Street to Mike Box Bridge. | Pavement Improvement | 2009-07-07 | 2009-08-10 | 2010-07-15 | 2010-09-10 | 439451.75 | 2.000 | 7597600
199 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7599600 | This project involves the repaving of about 1 mile of Baker from Interstate 64 to US Highway 43 north of Mobile | Pavement Improvement | 2009-06-17 | 2009-07-24 | 2010-07-15 | 2010-10-18 | 274305.19 | 2.000 | 7599600
200 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7614600 | This project involves the repaving of McCrary Road (County Road 604) from US Highway 98 (SR-42) to Lott Road (SR-217) | Pavement Improvement | 2010-02-03 | 2010-02-26 | 2010-04-30 | 2010-12-06 | 813600 | 2.900 | 7614600
201 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7615600 | Mobile County will widen the existing 20 eet width pavement of Half Mile Road 2 feet on each side and then resurface with asphalt the entire 24 feet width from Beverly Road eastwardly approximately 2 | Pavement Improvement | 2009-07-24 | 2009-09-28 | 2009-12-31 | 2010-07-30 | 265000 | 1.837 | 7615600
202 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | 7616600 | This project involves the repaving of about 6 miles of the Irvington-Bayou La Batre Highway from State Highway 188 to US Highway 90 in the town of Irvington | Pavement Improvement | 2010-04-29 | 2010-05-14 | 2010-08-09 | 2011-06-29 | 1724068.84 | 5.740 | 7616600
203 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | 02 | 7724601 | The existing two-lanes of Perry Hill Road in Montgomery from Interstate 85 to Harrison Road will be widened to provide an undivided four-lane highway. | Pavement Widening | 2010-04-15 | 2010-09-21 | 2011-04-28 | 2012-03-20 | 1949739.91 | 0.511 | 7724601
204 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE | MONTGOMERY | 02 | 7804601 | This project involves the repaving of Alabama River Parkway (County Road 2) from State Highway 143 to Jackson Lake Road (County Road 60) | Pavement Improvement | 2010-05-05 | 2010-06-22 | 2010-07-30 | 2010-09-09 | 500837.88 | 1.690 | 7804601
205 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | AUTAUGA | MONTGOMERY | 02 | 7812601 | This project involves the repaving of McQueen Smith Road (County Road 75) from East Main Street (County Road 2) to State Highway 14 | Pavement Improvement | 2010-04-21 | 2010-05-20 | 2010-07-16 | 2010-08-24 | 740000 | 1.467 | 7812601
206 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | AUTAUGA | MONTGOMERY | 02 | 7899600 | This project involves the repaving of Gin Shop Hill Road (County Road 29) from West 4th Street (State Highway 206) to US Highway 82 (State Highway 6) | Pavement Improvement | 2010-04-15 | 2010-05-17 | 2010-07-06 | 2010-08-24 | 217453.97 | 1.083 | 7899600
207 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 8007601 | "This project involves the repaving of Russell County Road 28 (Sandfort Road) from the West City Limit of Phenix City | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-07-30 | 2011-05-19 | 594180 | 5.120 | 8007601
208 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 8018600 | "This project involves the repaving Russell County Road 427 (Opelika Rd.) from Russell County Road 418 (Crawford Rd.) to 22nd Street and Russell County Road 427 (Opelika Road) from Russell County Road | Pavement Improvement | 2009-07-28 | 2009-07-28 | 2010-07-30 | 2010-10-19 | 321358.24 | 1.820 | 8018600
209 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 8018601 | This project involves the repaving and striping of Opelika Road (County Road 427) from Cut Rate Road (County Road 296) to south of Stafford Raod (County Road 296) | Pavement Improvement | 2009-12-01 | 2009-12-01 | 2010-08-15 | 2010-12-02 | 269827.44 | 1.940 | 8018601
210 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL | COLUMBUS (GA) | 03 | 8041601 | This project involves the repaving and striping of Pierce Road (County Road 427) from US Highway 431/280 in Russell County to Summerville Road in Lee County | Pavement Improvement | 2010-05-11 | 2010-06-25 | 2010-08-02 | 2011-02-09 | 486277.31 | 1.778 | 8041601
211 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH | GADSDEN | 04 | 8104600 | This project constructs a new 4 lane roadway approximately 1 mile long between the intersections of Steel Station / Sutton Bridge Roads to I-759. | Pavement Improvement | 2009-12-15 | 2010-02-10 | 2010-07-02 | 2011-12-11 | 2138433 | 3.360 | 8104600
212 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON, MACON | HUNTSVILLE | Multiple | 8509601 | This project constructs additional turn lanes on both Wall Triana Highway and US-72 (SR-2) with a signal Modification. | Pavement Improvement | 2009-08-27 | 2010-05-26 | 2010-08-14 | 2011-10-31 | 738997 | 1.622 | 8509601
213 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 05 | 9229600 | This project involves the repaving of Austinville Road SW from Carridale Street to 14 th Street SW and 14th Street SW to Central Parkway in the city of Decatur | Pavement Improvement | 2009-07-07 | 2009-07-09 | 2010-07-01 | 2010-12-06 | 133917 | 0.660 | 9229600
214 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 9412601 | This project involves the repaving of Westgate Parkway from US Highway 84 to US Highway 231 in the city of Dothan | Pavement Improvement | 2009-06-22 | 2009-07-01 | 2010-09-15 | 2011-02-17 | 644000 | 4.000 | 9412601
215 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 9412602 | This project involves the repaving of Honeysuckle Road from US Highway 84 to Park Avenue in the city of Dothan | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-09-15 | 2011-02-17 | 763590 | 5.100 | 9412602
216 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 9414601 | This project involves the widening and repaving of Fortner Street (County Road 40) from Brannon Stand Road to Honeysuckle Road | Pavement Improvement | 2010-05-05 | 2010-06-15 | 2010-10-31 | 2011-01-31 | 105968.88 | 3.050 | 9414601
217 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | 9440600 | The rehabilitation of the paved surface by means of a surface treatment on Dale County Road 75 (Alpha Street) from U.S. Routhe 231/Alabama Route 53 to Dale County Road 112. | Pavement Improvement | 2010-05-19 | 2010-06-29 | 2010-09-30 | 2010-11-02 | 26647 | 1.685 | 9440600
218 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | 9441604 | This project involves the resurfacing of South Brannon Stand Road (CR-59) from 0.06 mile north of SR-52 to 0.30 mile north of CR-40 (Fortner Street). | Pavement Improvement | 2010-01-13 | 2010-06-01 | 2010-09-15 | 2010-09-16 | 317740 | 2.150 | 9441604
219 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 9628600 | This project involves the repaving of Charlie Shirley Road (County Road 84) from State Highway 69 to US Highway 43( State Highway 13) in the city of Northport in Tuscaloosa County | Pavement Improvement | 2010-09-16 |  | 2010-11-30 | 2011-02-14 | 370851.4 | 2.410 | 9628600
220 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | 9642600 | This project involves the repaving of 5th Street (County Road 30) from Main Avenue to Robert Cardinal Airport Road in Tuscaloosa County | Pavement Improvement | 2010-09-16 |  | 2010-11-30 | 2011-02-14 | 175213.53 | 1.425 | 9642600
221 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | 9802918 | This project will improve lane widths and turn lane lengths at selected intersections along Lorna Road. The project will also replace the traffic signals with new equipment. These improvements will | Safety/Traffic Management | 2010-05-19 | 2010-09-13 | 2011-05-06 |  | 1246204.81 | 2.900 | 9802918
222 | ALABAMA | Underway | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 07 | 9802920 | This project involves the first phase of modification and upgrade to the traffic management center in the city of Birmingham | Safety/Traffic Management | 2010-05-25 | 2010-06-09 | 2011-02-09 |  | 660387.5 | 0.000 | 9802920
223 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | CN07908 | This project is the first phase of the Hoover Park Avenue Sidewalks project and involves the addition of sidewalks along Rockview lane from the Rockview Lane/ Park Avenue intersection to the Bluff Park Community Center on Cloudland Drive | Transportation Enhancements | 2010-05-27 | 2010-07-13 | 2011-02-11 | 2013-01-15 | 161055 | 0.000 | CN07908
224 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | CN07909 | This project involves the addition of sidewalks along Park Avenue in Hoover between Chapel Raod and Farlay Road | Transportation Enhancements | 2010-05-27 | 2010-07-13 | 2011-02-11 | 2013-01-15 | 442464.08 | 0.000 | CN07909
225 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE, BALDWIN |  | 01 | CN09208 | "This project will repair badly deteriorated pavements at 16 sites located throughout Mobile and Baldwin Counties. The sites are located on various state | Pavement Improvement | 2009-07-27 | 2009-09-09 | 2009-12-31 | 2010-03-31 | 784937.81 | 0.000 | CN09208
226 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | Multiple | CN09906 | This project involves the repaving of various streets in the central business district of Montgomery | Pavement Improvement | 2010-04-29 | 2010-06-01 | 2011-02-09 | 2012-07-20 | 2850260 | 0.000 | CN09906
227 | ALABAMA | Completed | C240 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE | MONTGOMERY | 02 | CN09908 | This project involves the repaving of the Coosa River Parkway from West Bridge Street to US Highway 231 and the repaving of West Bridge Street from the Coosa River Parkway to North Bridge Street in Wetumpka | Pavement Improvement | 2009-07-30 | 2009-08-27 | 2009-11-30 | 2010-05-20 | 1147835.61 | 3.459 | CN09908
228 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE |  | 05 | CN10201 | "This project involves the repaving of two different roads. Site 1 is South of Lovelace Crossroads and includes approximately 2 miles of Lauderdale County Road 6 from Lauderdale County Road 219 to Ala | Pavement Improvement | 2009-12-28 | 2010-03-28 | 2010-04-21 | 2010-04-21 | 265000 | 3.561 | CN10201
229 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON | DOTHAN | 02 | CN10204 | This project involves the resurfacing of CR-26 (Jordon Avenue) from North ROW SR-12 (US-84) to 0.22 mile east of Glen Lawrence Int. | Pavement Improvement | 2010-01-13 | 2010-06-01 | 2010-09-15 | 2010-09-16 | 328590 | 2.110 | CN10204
230 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | FAYETTE |  | 04 | CN10208 | This project involves striping various county roads in Fayette County | Safety/Traffic Management | 2010-04-20 |  |  | 2011-05-12 | 265000 | 50.375 | CN10208
231 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE | FLORENCE | 05 | CN10211 | This project involves the repaving of County Road 47 from State Highway 133 to County Road 320 and from County Road 37 to County Road 63 and also the repaving of JC Mauldin Highway from County Road 25 to US Highway 72 | Pavement Improvement | 2010-05-25 | 2010-06-09 | 2010-08-15 | 2010-08-02 | 617690 | 5.629 | CN10211
232 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | BIBB |  | 06 | CN10213 | This project invovles the traffic striping and sign replacement along various county roads in Bibb County | Safety/Traffic Management | 2010-05-25 | 2010-06-07 | 2010-07-30 | 2010-09-20 | 265000 | 71.000 | CN10213
233 | ALABAMA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ALABAMA | MARSHALL |  | 04 | CN10214 | This project involves the repaving of Huntsville Road (County Road 414) from Short Creek Bridge ot State Highway 75 | Pavement Improvement | 2010-05-20 | 2010-06-17 | 2010-08-31 | 2010-08-20 | 68486.85 | 4.000 | CN10214
234 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | CN10215 | The replacement of the bridge with the identification number #2494 over Leslie Branch on Madison County Road 86 (Love Branch Road) near the City of Huntsville, Alabama. | Pavement Improvement | 2010-05-27 | 2010-07-01 | 2010-10-01 | 2011-11-15 | 425509.94 | 0.216 | CN10215
235 | ALABAMA | Completed | C250 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | 03 | CN10216 | This project contains two sites listed as follows: Site #1: The repaving of Montgomery County Road 24 known as Cloverdale/Federal Rd. from the Lowndes County Line to US Route 31/Alabama Route 3. Site | Pavement Improvement | 2010-05-13 | 2010-05-28 | 2010-08-27 | 2010-09-15 | 530000 | 8.020 | CN10216
236 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | CLEBURNE |  | 03 | CN10217 | This project contains two sites listed as follows: Site #1 :The widening and repaving of Cleburne County Road 34 from US Route 431/ Alabama Route 1 to County Road 13. Site #2: The widening and repa | Pavement Improvement | 2010-05-27 | 2010-06-10 | 2010-09-09 | 2012-01-04 | 265000 | 3.209 | CN10217
237 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | CN10900 | This project involves the repaving at three different sites in Sheffield. Site #1 is the repaving of Old Jackson Highway from the Tuscumbia city limits to South Montgomery Avenue. Site #2 is South M | Pavement Improvement | 2010-04-28 | 2010-06-04 | 2010-08-15 | 2010-08-19 | 306788.32 | 1.770 | CN10900
238 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | CN10901 | The project involves the restriping of Dead Lake Road from US Highway 43 to Interstate 65 and Radcliff Road from US Highwya 43 to one mile west of Creola city limit | Pavement Improvement | 2010-05-06 | 2010-05-24 | 2010-06-30 | 2010-07-06 | 51304 | 3.550 | CN10901
239 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | CN10902 | This project involves the installation of LED traiffc and pedestrian signals at various intersections in the city of Mobile | Safety/Traffic Management | 2010-04-22 | 2010-08-30 | 2010-12-11 | 2011-06-30 | 911640 | 0.000 | CN10902
240 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | CN10903 | This project involves the repaving of Gusmus Aveneue from 2nd Street (State Highway 184) to Avalon Avenue, South Broadway Avenue from West 6th Street (County Road 24) to Avalon Avenue and West 6th Str | Pavement Improvement | 2010-04-27 | 2010-05-12 | 2010-08-15 | 2010-08-03 | 307214.76 | 2.500 | CN10903
241 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | CN10905 | This project involves the repaving and striping of portions of Danville Road from Chapel Hill Road to 2nd Street Southwest in the city of Decatur | Pavement Improvement | 2010-04-13 | 2010-05-03 | 2010-07-01 | 2010-12-06 | 382187.6 | 1.906 | CN10905
242 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | CN10906 | This project involves the repaving of 8th Street Southeast from 16th Avenue to Point Mallard Drive and Pont Mallard Drive to Point Mallard Circle in the city of Decatur | Pavement Improvement | 2010-04-29 | 2010-05-14 | 2010-07-01 | 2010-12-06 | 429002.6 | 2.043 | CN10906
243 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | CN10907 | This project involves the repaving and striping of Country Club Road from State Highway 67 to Somerville Road in the city of Decatur | Pavement Improvement | 2010-04-14 | 2010-06-07 | 2010-08-15 | 2010-12-06 | 154393.25 | 1.080 | CN10907
244 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | CN10909 | This project involves the repaving of various eligible roads in the city of Auburn | Pavement Improvement | 2010-05-26 | 2010-06-16 | 2010-09-30 | 2011-02-09 | 1247027.47 | 0.000 | CN10909
245 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | CN10915 | This project involves the purchase of 2 vans for the Association of Retarded Citizens | Other | 2009-10-21 | 2009-10-21 | 2010-10-01 | 2012-03-16 | 67860 | 0.000 | CN10915
246 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | CN10916 | This project involves sidewalk improvements along State Highway 188 from Alba School to Arnett Street | Transportation Enhancements | 2010-05-06 | 2010-06-02 | 2010-07-15 | 2011-03-21 | 125000 | 1.000 | CN10916
247 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | CN10917 | This project involves the repaving of various eligible roads in the city of Opelika | Pavement Improvement | 2010-07-27 | 2010-08-11 | 2010-10-12 | 2011-10-27 | 832465.57 | 0.000 | CN10917
248 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | CN10918 | This project involves the repaving of North Main Street from 3rd Street to Sheffield city limit and repaving North Cave Street from East Hobson Street to West North Commons Street | Pavement Improvement | 2010-04-28 | 2010-05-13 | 2010-07-20 | 2010-07-20 | 304347.29 | 1.200 | CN10918
249 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE | FLORENCE | 05 | CN10919 | This project involves the repaving of Hermitage Drive from Royla Avenue to Helton Drive and North Pine Street from North Wood Avenue to Kenneth Court and South Pine Street from West Alabama Street to West Mobile Street | Pavement Improvement | 2010-04-27 | 2010-05-13 | 2010-08-15 | 2010-08-06 | 448064.17 | 0.820 | CN10919
250 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | CN10920 | This project involves the repaving of various eligilbe streets in the city of Huntsville | Pavement Improvement | 2010-04-13 | 2010-05-07 | 2010-09-21 | 2010-10-20 | 2762382.33 | 0.000 | CN10920
251 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | CN10921 | This project involves the repaving of various eligilbe streets in the city of Huntsville | Pavement Improvement | 2010-05-13 | 2010-06-01 | 2010-10-31 | 2010-10-20 | 1665827.53 | 0.000 | CN10921
252 | ALABAMA | Underway | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | CN10922 | REVITALIZATION ALONG SR-215 (GREENSBORO AVENUE) FROM 15TH STREET TO HARGROVE ROAD | Pavement Improvement | 2010-12-07 |  |  |  | 1725290 |  | CN10922
253 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 05 | CN10923 | Repaving of Morgan County Route 103 also known as Hayes Street from US Route 31/Alabama Route 3 to Karl Prince Rd. and the repaving of Sparkman Street from Karl Prince Rd. to US Route 31/Alabama Route 3 in the City of Hartselle, Alabama. | Pavement Improvement | 2010-06-02 | 2010-06-28 | 2010-08-25 | 2010-09-21 | 253153.61 | 2.321 | CN10923
254 | ALABAMA | Completed | C950 | Ferryboat | ALABAMA | WILCOX |  | 07 | CN10928 | ARRA FERRY BOAT DISCRETIONARY - GEES BEND FERRY TERMINAL FACILITIES, ARRA FUNDED | Other | 2011-01-19 |  |  | 2011-12-16 | 1265800 |  | CN10928
255 | ALABAMA | Underway | C200,C240 | Highway Infrastructure Investment Grant | ALABAMA | ST CLAIR |  | 06 | I020324 | "This project will convert an existing 4 lane section of interstate to a 6 lane. The completion of this project will tie an existing 6 lane interstate immediately east and immediately west of the project limits | Pavement Widening | 2009-09-25 | 2009-10-13 | 2012-10-01 |  | 72524929.49 | 7.870 | I020324
256 | ALABAMA | Underway | C240 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH | GADSDEN | 04 | I059342 | Reconstructs a portion of existing concrete Interstate 59 near Gadsden by placing a layer of asphalt on the existing roadway and then placing an 11 inch layer of concrete pavement on the asphalt layer | Pavement Improvement | 2009-05-14 | 2009-07-09 | 2010-06-15 |  | 47525423.51 | 10.913 | I059342
257 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | PE09906 | "This project includes improvements to four different repaving sites in Sheffield | Other | 2009-07-01 | 2009-08-17 | 2010-02-01 | 2010-01-14 | 2056.88 | 2.170 | PE09906
258 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | PE09907 | This project involves the adjustment of signal time of various traffic signals in the city of Mobile in order to improve traffic flow | Other | 2009-07-07 | 2009-10-01 | 2010-10-01 | 2010-02-26 | 154451.16 | 0.000 | PE09907
259 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | PE09908 | This project involves the repaving at three different sites in Muscle Shoals. Site #1 is a mile of repaving of Gusmus Avenue between 2nd Street and Avalon Avenue. Site #2 is 1 mile of South Broadway A | Other | 2009-07-07 | 2009-07-07 | 2010-02-01 | 2010-01-15 | 1630.44 | 2.500 | PE09908
260 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | PE09909 | This project involves the repaving various streets in the city of Huntsville | Other | 2009-07-07 | 2009-07-09 | 2010-02-01 | 2010-06-10 | 3412.08 | 0.000 | PE09909
261 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MADISON | HUNTSVILLE | 05 | PE09910 | This project involves the repaving various streets in the city of Huntsville | Other | 2009-07-07 | 2009-07-09 | 2011-12-01 | 2010-06-10 | 673.23 | 0.000 | PE09910
262 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | PE09911 | "This project involves the restriping Mobile County Road 917 (Dead Lake Road) from U.S. Highway 43 to Interstate 65 and Mobile County Road 933 (Radcliff Road from U.S. Highway 43 to the Creola | Other | 2009-07-22 | 2009-07-31 | 2010-02-01 | 2010-01-31 | 15000 | 3.550 | PE09911
263 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LAUDERDALE | FLORENCE | 05 | PE09912 | This project involves the repaving at three differenct sites in Florence. Site #1 is the repaving of about a 1 mile section of Hermitage Drive from Royal Avenue to Helton Drive. Site # 2 is the repa | Other | 2009-07-20 | 2009-08-02 | 2010-02-01 | 2010-01-15 | 26745.69 | 0.820 | PE09912
264 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | PE09913 | This project involves the repaving of 8th Street SE from 16th Avenue to Point Mallard Drive and Point Mallard Drive to Point Mallard Circle in the city of Decatur | Other | 2009-07-17 | 2009-07-18 | 2010-02-01 | 2010-06-10 | 1191.4 | 2.180 | PE09913
265 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | PE09914 | "This project involves the repaving of Country Club Road from Alabama State Highway 67 to Somerville Road in Decatur | Other | 2009-07-17 | 2010-06-07 | 2010-02-01 | 2010-06-10 | 831.46 | 1.080 | PE09914
266 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 04 | PE09915 | "This project involves the repaving of approximately 4 miles of Morgan County Road 41 (Danville Road) from Morgan County Road 191 (Chapel Hill Rd.) to 2nd Street SW in Decatur | Other | 2009-07-17 | 2009-07-18 | 2010-02-01 | 2010-06-10 | 1570.4 | 1.970 | PE09915
267 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN | DECATUR | 05 | PE09916 | This project involves the repaving of Hayes Street from US Highway 31 to Karl Prince Road and the repaving of Sparkman Street from Karl Prince Road to US Highway 31 in the town of Hartselle | Other | 2009-07-31 | 2009-07-31 | 2010-02-01 | 2010-06-10 | 10398.36 | 2.400 | PE09916
268 | ALABAMA | Completed | C950 | Ferryboat | ALABAMA | WILCOX |  | 07 | PE10906 | This project involves improvements to the Gees Bend Ferry Terminal Facility | Other | 2009-12-08 | 2010-04-12 | 2010-10-01 | 2010-11-05 | 153200 | 0.000 | PE10906
269 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | PE10907 | This project involves the repaving of various eligible roads in the city of Opelika | Other | 2009-12-16 | 2009-12-16 | 2010-02-01 | 2010-02-26 | 1117.43 | 0.000 | PE10907
270 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | PE10908 | This project involves the repaving of various eligible roads in the city of Auburn | Other | 2009-12-16 | 2009-12-16 | 2010-02-01 | 2010-02-26 | 3347.53 | 0.000 | PE10908
271 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT | FLORENCE | 05 | PE10909 | This project involves the repaving of North Main Street from 3rd Street to Sheffield city limit and repaving North Cave Street from East Hobson Street to West North Commons Street | Other | 2009-12-07 | 2009-12-07 | 2010-02-01 | 2010-02-26 | 701.93 | 1.200 | PE10909
272 | ALABAMA | Underway | C490 | OJT/SS | ALABAMA | STATEWIDE |  |  | SP10904 | This project is to provide funding for an internship for juniors and seniors for careers in the surface transportation industry as provided for by Alabama State University OJT/SS Program. | Other | 2010-05-14 |  | 2011-12-30 |  | 269658 |  | SP10904
273 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | CRENSHAW |  | 02 | TE09900 | This project will add sidewalks to Emment Avenue, Fulton Avenue, U.S. Highway 331 and Sasser Street in Brantley, Alabama in Crenshaw County. | Transportation Enhancements | 2010-01-13 | 2010-02-01 |  | 2010-06-25 | 225933.82 | 0.900 | TE09900
274 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | FRANKLIN |  | 04 | TE09901 | This project will add sidewalks to Jackson Avenue in downtown Russelleville, Alabama in Franklin County. | Transportation Enhancements | 2010-02-09 | 2010-02-23 | 2010-08-15 | 2010-07-27 | 358072.38 | 0.570 | TE09901
275 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | TE09902 | This project will add sidewalks along Alabama Avenue, 18th Street and 19th Street in downtown Jasper, Alabama in Walker County. | Transportation Enhancements | 2010-06-14 | 2010-06-14 | 2010-11-24 | 2011-05-31 | 343500.67 | 0.460 | TE09902
276 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | COFFEE |  | 02 | TE09903 | This project will add streetscaping to U.S. Highway 84 (Main Street) in downtown Enterprise, Alabama in Coffee County. This is Phase III of the project. | Transportation Enhancements | 2010-06-12 | 2010-06-28 | 2010-11-30 | 2011-02-11 | 860505 | 0.250 | TE09903
277 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | TE09904 | This project will add sidewalks along Alco Drive, U.S. Highway 31 and Persimmon Street in downtown Brewton, Alabama in Escambia County. | Transportation Enhancements | 2010-06-01 | 2010-06-14 | 2010-09-30 | 2010-11-22 | 290962.25 | 1.750 | TE09904
278 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | ESCAMBIA |  | 01 | TE09905 | This project involves the additon of sidewalks to Presley Street, Pine Street, Ashley Street, Carver Stree and Alabama State Highway Route 21 in Atmore, Alabama in Covington County. | Transportation Enhancements | 2010-07-20 | 2010-07-22 | 2010-11-19 | 2011-11-01 | 375520.37 | 1.960 | TE09905
279 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | COVINGTON |  | 02 | TE09906 | "This project involves streetscaping along Alabama State Highway Route 55 (Main Street) in Florala | Transportation Enhancements | 2010-03-24 | 2010-04-08 | 2010-08-01 | 2011-10-19 | 317164 | 0.100 | TE09906
280 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | TE09907 | "This project involves the addtion of a sidewalk on University Blvd. from the University Church of Christ to Zeigler Interchange in Mobile | Transportation Enhancements | 2010-02-08 | 2010-03-01 | 2010-05-08 | 2010-03-31 | 62042 | 0.320 | TE09907
281 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | TE09908 | "This project involves the addition of sidewalks along approximately 1 mile of South Mount Pleasant Avenue from Murdock Street to Eagle Point Apartments in Monroeville | Transportation Enhancements | 2010-03-08 | 2010-03-08 |  | 2010-03-31 | 132436.13 | 0.780 | TE09908
282 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | TE09909 | "This project involves the paving of 2 gravel section of the Hugh Branyon Backcountry Trail | Transportation Enhancements | 2010-04-19 | 2010-04-26 | 2010-08-24 | 2011-11-30 | 296369 | 2.250 | TE09909
283 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | TE09910 | "This project will provide a pedestrian connection called the Amber Isle Connection to the Hugh S. Branyon Backcountry Trail in Orange Beach | Transportation Enhancements | 2010-05-06 | 2010-09-24 | 2010-09-24 | 2011-06-06 | 277138 | 0.290 | TE09910
284 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BALDWIN |  | 01 | TE09911 | This project, located in Baldwin County, Alabama, involves the addition of a sidewalk along Alabama State Highway Route 104 with the purpose to connect the Downtown Area of Silverhill, Alabama with the Oscar Johnson Memorial Park. | Transportation Enhancements | 2010-06-15 | 2010-06-15 | 2010-10-29 | 2011-02-14 | 290685.58 | 0.680 | TE09911
285 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | TE09912 | Place Landscaping along Alabama State Route 119 in front of the American Village, in Montevallo, Shelby County, Alabama | Transportation Enhancements | 2010-03-29 | 2010-04-01 | 2010-07-29 | 2010-08-17 | 326202.96 | 0.640 | TE09912
286 | ALABAMA | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | TE09913 | Create enhancements to the online Geographical Information System (GIS) computer Tools for research and planning located at 13075 Moundville Archaeological Park in Moundville, | Other | 2009-11-03 | 2009-11-11 | 2012-11-02 |  | 138650 | 0.000 | TE09913
287 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON |  | 02 | TE09914 | "This project involves streetscaping along Alabama Highway 53 in the Downtown Commercial District of Cottonwood | Transportation Enhancements | 2010-10-08 | 2010-11-01 | 2011-02-25 | 2011-10-03 | 244976.63 | 0.640 | TE09914
288 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | TE09915 | "This project involves adding sidewalks to the east side Lowndes County Road 29 in Lowndesboro | Transportation Enhancements | 2010-02-19 | 2010-02-22 | 2010-06-16 | 2010-06-22 | 214917.21 | 0.690 | TE09915
289 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | COVINGTON |  | 02 | TE09916 | "This project involves streetscaping (Phase III) of Main Street in Opp | Transportation Enhancements | 2010-06-15 | 2010-06-28 | 2010-11-15 | 2011-01-25 | 309332 | 0.190 | TE09916
290 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | TE09917 | "This project involves streetscaping for 3rd Avenue in Downtown Hartford | Transportation Enhancements | 2010-08-31 | 2010-09-14 | 2010-12-30 | 2011-03-14 | 276851.58 | 0.360 | TE09917
291 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | TE09918 | "This project involves streetscaping (Phase II) along Alabama Highway 27 (Commerce Street) in Geneva | Transportation Enhancements | 2010-07-19 | 2010-08-03 | 2010-11-30 | 2011-02-24 | 539053 | 0.240 | TE09918
292 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | DALE |  | 02 | TE09919 | "This project involves downtown streetscape improvements for Broad Street and Merrick Street in Ozark | Transportation Enhancements | 2010-07-08 | 2010-09-09 | 2011-01-19 | 2011-02-28 | 356387 | 0.090 | TE09919
293 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | RUSSELL |  | 03 | TE09920 | "This project involves streetscaping along Main Street in Downtown Hurtsboro | Transportation Enhancements | 2010-06-07 | 2010-06-07 | 2010-11-09 | 2011-04-15 | 98604 | 0.150 | TE09920
294 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | CONECUH |  | 02 | TE09921 | "This project will provide pedestrian improvements along Magnolia Avenue | Transportation Enhancements | 2010-03-22 | 2010-03-23 | 2010-09-30 | 2011-03-15 | 461395.44 | 2.080 | TE09921
295 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | TE09922 | Widen Watkins Creek Bridge for Pedestrians in the City of Mountain Brook, Alabama on Watkins Bridge Road in Jefferson County, Alabama. | Transportation Enhancements | 2010-08-23 | 2010-08-30 | 2010-12-20 | 2011-07-01 | 263106.15 | 0.020 | TE09922
296 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | TE09923 | "This project will add sidewalks along Parrish Jasper Road from First Street to Parrish Elementary School in the old downtown area of Parrish | Transportation Enhancements | 2010-06-04 | 2010-06-21 | 2010-11-17 | 2011-03-30 | 299596.51 | 0.490 | TE09923
297 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | ETOWAH | GADSDEN | 04 | TE09924 | "This project will landscape approximately 1.7 miles of U.S. Highway 431 from Keysburg Road to Bank Street in Glencoe | Transportation Enhancements | 2010-06-02 | 2010-06-02 | 2010-10-31 | 2010-10-01 | 149768.76 | 1.490 | TE09924
298 | ALABAMA | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | STATEWIDE |  |  | TE09925 | This projects will conduct an Archaeological Survey of the Old Federal Road Statewide to be done byt the University of South Alabama. This project is a research project and is located at the University of South Alabama. | Other | 2010-01-20 | 2010-02-15 | 2010-10-22 |  | 48526 | 0.000 | TE09925
299 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | TE09926 | Repave Chief Ladiga Trail in the City of Jacksonville, Alabama parallel and adjacent to Alabama Route 21 for 7.1 miles in Calhoun County, Alabama. | Transportation Enhancements | 2010-06-28 | 2010-09-08 | 2010-09-27 | 2011-08-31 | 254030 | 8.100 | TE09926
300 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MORGAN |  | 05 | TE09927 | "This project involves a Historic Downtown Sidewalk and Canopy Restoration for Hartselle | Transportation Enhancements | 2010-02-17 | 2010-02-22 | 2010-11-22 | 2010-10-29 | 457940 | 0.240 | TE09927
301 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BUTLER |  | 02 | TE09928 | "This project involves the addition of sidewalks on U.S. Highway 31 in Georgiana | Transportation Enhancements | 2010-03-15 | 2010-03-15 | 2010-05-04 | 2010-07-20 | 161607.05 | 0.850 | TE09928
302 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | DE KALB |  | 04 | TE09929 | "This project involves the addition of sidewalks on Alabama Higway 68 in Crossville | Transportation Enhancements | 2010-03-12 | 2010-04-16 | 2010-10-31 | 2010-11-09 | 300074.7 | 1.820 | TE09929
303 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | LOWNDES |  | 02 | TE09930 | "This project involves the addition of sidewalks on Alabama Higway 97 in Hayneville | Transportation Enhancements | 2010-05-07 | 2010-06-04 | 2010-07-29 | 2012-01-07 | 154320 | 1.000 | TE09930
304 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | GENEVA |  | 02 | TE09931 | "This project involves streetscaping approximately x miles of West Slocomb Street- Phase II in Slocumb | Transportation Enhancements | 2010-07-21 | 2010-09-07 | 2010-10-30 | 2011-01-26 | 190000 | 0.060 | TE09931
305 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BIBB |  | 06 | TE09932 | "This project will add sidewalks along Alabama Highway 25 from Creekview Lane to Cooper Avenue in Brent | Transportation Enhancements | 2010-07-14 | 2010-07-26 | 2010-11-10 | 2011-04-18 | 393924.45 | 1.330 | TE09932
306 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | CALHOUN | ANNISTON | 03 | TE09933 | Construct Project AL 204 Sidewalk- Phase II at Jacksonville State University in Jacksonville, AL. along Alabama Route 204 in Calhoun County, Alabama. | Transportation Enhancements | 2010-03-12 | 2010-04-01 | 2010-05-14 | 2010-05-19 | 74377.15 | 0.250 | TE09933
307 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | ELMORE | MONTGOMERY | 02 | TE09934 | Construct sidewalks along the southern side of Chapman Rd. from the intesection of Chapman Road & Main Street East to the Millbrook City School, in Elmore County, Alabama. | Transportation Enhancements | 2010-06-18 | 2010-08-19 | 2010-09-08 | 2011-03-18 | 75358.73 | 0.380 | TE09934
308 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MOBILE | MOBILE | 01 | TE09935 | This project will add sidewalks to approximately 2 miles of U.S. Highway 43 (Saraland Blvd. N.) from Cleveland Road North to 225 Saraland Blvd. N. ) | Transportation Enhancements | 2010-05-11 | 2010-06-07 | 2010-10-30 | 2010-12-15 | 242967.46 | 1.200 | TE09935
309 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | TALLADEGA |  | 03 | TE09936 | This project will add sidewalks to several streets in Linoln, Alabama. Talladega County. The sidewalks will be located along Lock 4 Road to McLain Street and Magnolia Street. | Transportation Enhancements | 2010-09-22 | 2010-10-06 | 2010-12-31 | 2011-04-30 | 143128.81 |  | TE09936
310 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | PICKENS |  | 04 | TE09937 | "This project will add sidewalks along 5th Street NW and 2nd Avenue NW from 5th Street Northwest to 7th Street Northwest in Reform | Transportation Enhancements | 2010-04-22 | 2010-04-26 | 2010-06-25 | 2010-08-05 | 134066 | 0.450 | TE09937
311 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | GREENE |  | 07 | TE09938 | "This project will add sidewalks along the north side of West End Avenue beginning ath te Elmwood Manor Apartments and proceeding East to US Highwyay 11 in Eutaw | Transportation Enhancements | 2010-08-18 | 2010-08-31 | 2010-11-28 | 2011-06-01 | 458750 | 0.770 | TE09938
312 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | TE09939 | Construct Sidewqlks along Hillcrest High School Patriot Parkway from Remington Parkway to Old Marion Road in South Tucaloosa County, Alabama. | Transportation Enhancements | 2010-06-15 | 2010-06-28 | 2010-10-01 | 2010-09-30 | 354177.18 | 0.950 | TE09939
313 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MONROE |  | 01 | TE09940 | "This project will add a pedestrian connector between Alabama Southern Community College and Monroe County High School. This Project is located South of Agricultural Road and East of Veterans Drive in Monroeville | Transportation Enhancements | 2010-04-27 | 2010-05-11 |  | 2010-10-20 | 387205 | 1.320 | TE09940
314 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | TALLAPOOSA |  | 03 | TE09941 | "This project will add sidewalks along the west side of K Street in Northeast Alexander City | Transportation Enhancements | 2010-06-24 | 2010-06-28 | 2010-10-31 | 2010-11-19 | 503515.98 | 0.550 | TE09941
315 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | TALLADEGA |  | 03 | TE09942 | "This Project involves streetscaping on Broadway Avenue from 3rd Street to 8th Street in Sylacauga | Transportation Enhancements | 2010-08-05 | 2010-08-10 | 2010-12-10 | 2012-01-13 | 410853.5 | 1.330 | TE09942
316 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | LEE | AUBURN-OPELIKA | 03 | TE09943 | This project involves the construction of a sidewalk along South College Street from East University Drive to South Donahue Drive in the city of Auburn. | Transportation Enhancements | 2011-03-07 | 2011-03-21 | 2011-06-20 | 2011-08-15 | 91900 |  | TE09943
317 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | 06 | TE09944 | Place Landscaping Enhancements on the Interchange of Interstate 65 and intesection U.S. Highway 31 in the City of Hoover, County of Jefferson, State of Alabama. | Transportation Enhancements | 2011-02-16 | 2011-02-16 | 2011-05-26 | 2011-05-26 | 313603.47 | 0.380 | TE09944
318 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MONTGOMERY | MONTGOMERY | 03 | TE09945 | Place Landscaping along Alabama Route 271 known as Taylor Road at the Auburn University at Montgomery Campus Property Border with AL -271. | Transportation Enhancements | 2010-04-22 | 2010-05-01 | 2010-06-16 | 2010-05-10 | 11120 | 0.080 | TE09945
319 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | BARBOUR |  | 02 | TE09946 | This Project involves streetscaping on Main Street in Louisville, Alabama. Barbour County | Transportation Enhancements | 2010-01-20 | 2010-02-15 | 2010-01-05 | 2010-05-19 | 156711.1 | 0.000 | TE09946
320 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | COLBERT |  | 05 | TE09947 | GUSMUS AVENUE SIDEWALKS IN THE CITY OF MUSCLE SHOALS. THIS PROJECT IS LOCATED ON GUSMUS AVE. FROM THE INTERSECTION OF GUSMUS AVE. AND AVALON AVE. NORTH TO FLORENCE AVE. IN THE CITY OF MUSCLE SHOALS. | Transportation Enhancements | 2010-11-18 | 2010-12-03 | 2011-05-26 | 2011-08-02 | 525775 |  | TE09947
321 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | HOUSTON |  | 02 | TE09954 | This project involves the streetscape along South Maint Street from Church Street to North Street and small portions of Church Street and North Street in the town of Columbia. | Transportation Enhancements | 2011-02-03 | 2011-02-21 | 2011-05-17 | 2011-06-20 | 73355 |  | TE09954
322 | ALABAMA | Completed | C200 | Highway Infrastructure Investment Grant | ALABAMA | TUSCALOOSA | TUSCALOOSA | 07 | TE09955 | Construct sidewallks along both sides of Coaling Ridge Road and Stephens Loop Road in the Town of Coaling, Alabama. | Transportation Enhancements | 2010-06-08 | 2010-06-14 | 2010-12-04 | 2011-02-28 | 848963 | 0.000 | TE09955
323 | ALABAMA | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | TE09960 | SIDWALKS ALONG OLD BIRMINGHAM HIGHWAY IN THE CITY OF SUMITON. THIS PROJECT IS LOCATED ALONG OLD BIRMINGHAM HIGHWAY IN THE CITY OF SUMITON. | Transportation Enhancements | 2011-12-12 | 2011-12-12 |  |  | 436000 |  | TE09960
324 | ALABAMA | Underway | C220 | Highway Infrastructure Investment Grant | ALABAMA | WALKER |  | 04 | TE09961 | This project involves the construction of sidewalks along North Street and Cordova Street connecting the middle school to the high school in the city of Cordova. | Transportation Enhancements | 2011-12-05 | 2011-12-05 |  |  | 332400 |  | TE09961
325 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | CHOCTAW |  | 07 | TE09973 | SIDWALKS ALONG AL 17 IN THE TOWN OF SILAS. THIS PROJECT IS LOCATED ALONG AL 17 IN THE TOWN OF SILAS CONNECTING THE DOWNTOWN AREA BY RUNNING ALONG SECOND AVENUE FROM FIRST STREET TO STATE ROUTE 17. | Transportation Enhancements | 2011-05-24 | 2011-05-25 | 2011-09-30 | 2012-03-22 | 20419.8 |  | TE09973
326 | ALABAMA | Underway | C220,C240 | Highway Infrastructure Investment Grant | ALABAMA | SHELBY | BIRMINGHAM | 06 | TE09974 | Construct sidewalks along Ballpark Rd. from Bearden Rd. through Pelham Park to U.S.31 in the City of Pelham in Shelby County, Alabama | Transportation Enhancements | 2010-07-07 | 2010-09-07 | 2010-11-02 |  | 222265.11 | 0.000 | TE09974
327 | ALABAMA | Completed | C220 | Highway Infrastructure Investment Grant | ALABAMA | MARSHALL |  | 04 | TE09985 | SIDEWALKS & PEDESTRIAN LIGHTING ALONG 2ND ST., 8TH AVENUE & 4TH STREET IN THE CITY OF ARAB. THIS PROJECT IS LOCATED ON 2ND. ST., 8TH AVE. & 4TH ST. IN THE CITY OF ARAB. | Transportation Enhancements | 2011-03-14 | 2011-03-14 | 2011-05-14 | 2011-06-28 | 130368.97 |  | TE09985
328 | ALABAMA | Completed | C230 | Highway Infrastructure Investment Grant | ALABAMA | JEFFERSON | BIRMINGHAM | Multiple | TR09900 | This project will provide new buses for the Clastran service area. Clastran is a bus system that covers areas in Jefferson and Shelby Counties not covered by the Birmingham transit system. | Other | 2009-09-22 | 2010-01-06 | 2010-09-01 | 2012-03-15 | 784030 | 0.000 | TR09900
329 | ALASKA | Completed | C220,C240 | Highway Infrastructure Investment Grant | ALASKA | DILLINGHAM |  |  | 0001260 | Reconstruct 2.8 miles of road from the intersection of Kanakanak Road and Wood River Road to the end of the road at Wood River Landing. Realign the road horizontally and vertically to create improved | Pavement Improvement | 2010-04-16 | 2010-04-17 | 2010-08-31 | 2011-09-11 | 12754842.22 | 2.800 | 0001260
330 | ALASKA | Completed | C230 | Highway Infrastructure Investment Grant | ALASKA | ANCHORAGE | ANCHORAGE |  | 0001359 | Increase capacity and improve safety by reconstructing a high-volume intersection at Tudor Road and Lake Otis Boulvard in Anchorage. In addition to dual left-turn lanes at all four corners of the int | Pavement Widening | 2010-04-07 | 2010-04-12 | 2010-10-30 | 2010-10-27 | 5000000 | 0.710 | 0001359
331 | ALASKA | Underway | C250 | Highway Infrastructure Investment Grant | ALASKA | NORTHWEST ARCTIC |  |  | 0002109 | This project will reconstruct and pave approximately 4,400 lineal feet of Shore Avenue between Lake Street and Crowley Dock Road and armor the tidewater side of the road with a combination of sheet pi | Pavement Improvement | 2009-06-17 | 2009-06-17 | 2011-10-01 |  | 6500000 | 1.077 | 0002109
332 | ALASKA | Completed | C250,C240 | Highway Infrastructure Investment Grant | ALASKA | YUKON-KOYUKUK |  |  | 0002178 | This project will upgrade and improve a 1.2-mile road between the City of Huslia and the recently-opened landfill. The project does not include realignments or widening, but will provide an improved driving surface between town and the landfill. | Pavement Improvement | 2010-09-07 | 2010-09-01 | 2011-08-31 | 2011-12-08 | 1780950.82 | 1.000 | 0002178
333 | ALASKA | Completed | C250,C240 | Highway Infrastructure Investment Grant | ALASKA | NOME |  |  | 0002185 | Construct drainage improvements and provide dust control on approximately 7,532 linear feet of roads within the City of Nome. The subgrade of the roads will be constructed to prepare for paving and | Pavement Improvement | 2010-06-21 | 2010-08-16 | 2011-07-31 | 2011-07-31 | 3588248 | 17.000 | 0002185
334 | ALASKA | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | SKAGWAY-HOONAH-ANGN |  |  | 0003053 | The project will construct a 1,300 foot, two-lane causeway connected to a 6,000 square-foot dock. A pontoon-supported, tidally-operated transfer bridge and ramp will provide roll-on/roll-off access fo | Bridge Improvement | 2009-04-16 | 2009-04-27 | 2011-05-15 | 2011-05-15 | 7700000 | 0.185 | 0003053
335 | ALASKA | Completed | C220 | Highway Infrastructure Investment Grant | ALASKA | VALDEZ - CORDOVA |  |  | 000S684 | The project will re-pave 7.1 miles of bike and pedestrian path alongside the Richardson Highway between Meals Avenue in downtown Valdez and River Road at the Robe River Subdivision, and improve its sa | Transportation Enhancements | 2009-07-24 | 2009-06-03 | 2010-07-15 | 2010-07-01 | 944038.12 | 7.600 | 000S684
336 | ALASKA | Completed | C250,C220 | Highway Infrastructure Investment Grant | ALASKA | VALDEZ - CORDOVA |  |  | 000S685 | Repave 0.95 miles of Blueberry Lake Road in Valdez at the access to the Blueberry Lake Campground. Pave 1,900 feet of roadway within the Blueberry Lake Campground. The project provides improved access to a popular recreation site. | Pavement Improvement | 2009-07-27 | 2009-06-03 | 2010-06-30 | 2010-06-18 | 912058.05 | 0.950 | 000S685
337 | ALASKA | Completed | C250,C240 | Highway Infrastructure Investment Grant | ALASKA | SOUTHEAST FAIRBANKS |  |  | 000S686 | This project will rehabilitate and resurface the Richardson Highway between MP 265-267 (Delta Junction area), to include its junction of the Alaska Highway and frontage roads. Work includes pulverizi | Pavement Improvement | 2010-05-15 | 2010-05-26 | 2010-09-30 | 2010-09-29 | 3262637.23 | 1.530 | 000S686
338 | ALASKA | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | KENAI PENINSULA |  |  | 0221054 | The project will resurface the driving lanes and shoulder of 16.75 miles of the Sterling Highway between Kalifornsky Beach Road and South Coho Loop Road in the Kenai Peninsula Borough. The project wi | Pavement Improvement | 2009-07-29 | 2009-05-26 | 2010-07-06 | 2010-07-15 | 6554670.9 | 17.000 | 0221054
339 | ALASKA | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | KODIAK ISLAND |  |  | 0391014 | Resurface 6.4 miles of urban roadway in the City of Kodiak. The project will include replacement of the waterproof membrane on the Buskin River bridge, paint striping, installation of pedestrian cros | Pavement Improvement | 2009-08-06 | 2009-06-02 | 2009-10-01 | 2009-10-08 | 6532387.48 | 6.950 | 0391014
340 | ALASKA | Completed | C230 | Highway Infrastructure Investment Grant | ALASKA | ANCHORAGE | ANCHORAGE |  | 0515004 | Resurface 1.837 miles of Jewel Lake Road from its intersection with Dimond Boulevard to its intersection with 63rd Avenue. Upgrade the collapsable, energy-absorbing ends of the guardrails to current | Pavement Improvement | 2010-05-14 | 2010-05-18 | 2010-07-31 | 2010-07-31 | 2280000 | 1.837 | 0515004
341 | ALASKA | Completed | C240,C230 | Highway Infrastructure Investment Grant | ALASKA | ANCHORAGE | ANCHORAGE |  | 0558007 | This 4.1-mile project will add 4-foot shoulders and new pavement, construct a paved pathway to connect existing pathways at South and North Birchwood Loop, construct a short truck-climbing lane just n | Pavement Improvement | 2010-04-19 | 2010-05-06 | 2011-09-01 | 2011-09-01 | 13059238 | 4.100 | 0558007
342 | ALASKA | Completed | C220 | Highway Infrastructure Investment Grant | ALASKA | VALDEZ - CORDOVA |  |  | 0750011 | This project will construct a new wayside in the vicinity of Milepost 7 of the Denali Highway. The project includes paved parking, a vault toilet,, litter barrel, table and bench. The project will r | Transportation Enhancements | 2009-09-03 | 2010-05-17 | 2010-07-15 | 2010-07-12 | 441283 | 0.000 | 0750011
343 | ALASKA | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | KETCHIKAN GATEWAY |  |  | 0902034 | This project is the second and final phase of structural rehabilitation and cathodic protection of the elevated Tongass Avenue viaduct in Ketchikan, Alaska. The scope of this project is to repair and | Bridge Improvement | 2010-01-21 | 2010-03-08 | 2011-03-23 | 2011-03-23 | 8591534 | 0.750 | 0902034
344 | ALASKA | Completed | C220 | Highway Infrastructure Investment Grant | ALASKA | KETCHIKAN GATEWAY |  |  | 0902035 | The project will widen and modify existing sidewalks for approximately 2,040 feet, from Chapmen Street to the existing Viaduct Tunnel to improve pedestrian capacity and safety and achieve Americans wi | Transportation Enhancements | 2010-05-12 | 2010-06-05 | 2011-05-01 | 2011-01-13 | 2151911 | 0.360 | 0902035
345 | ALASKA | Completed | C250 | Highway Infrastructure Investment Grant | ALASKA | SKAGWAY-HOONAH-ANGN |  |  | 0918007 | This project will rehabilitate 2.2 miles of road in the City of Hoonah linking the city airport and the state ferry terminal. The rehabilitated road will reduce maintenance efforts, improve ride quality and increase safety on this inter-modal link. | Pavement Improvement | 2010-01-07 | 2010-04-05 | 2010-09-23 | 2010-09-23 | 1989122.56 | 2.200 | 0918007
346 | ALASKA | Underway | C950 | Ferryboat | ALASKA | SKAGWAY-HOONAH-ANGN |  |  | 0918009 | The project will include removal and replacement of four or five mooring dolphins, installation of access gangways to two of the mooring dolphins nearest to the bridge float and replacement of the ste | Other | 2010-09-22 | 2011-06-15 | 2011-12-31 |  | 3059507 | 0.000 | 0918009
347 | ALASKA | Underway | C240 | Highway Infrastructure Investment Grant | ALASKA | KETCHIKAN GATEWAY |  |  | 0920025 | The project will reconstruct the highway for approximately two miles to provide a paved width of 36' including 12-foot driving lanes and 6-foot shoulders, from the first junction with D-1 Loop Road to | Pavement Improvement | 2010-04-06 | 2010-05-03 | 2011-06-30 |  | 10014923 | 2.100 | 0920025
348 | ALASKA | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | JUNEAU |  |  | 0933027 | This project will widen and straighten Glacier Highway to a paved width of 30 feet for 4.6 miles between the Amalga Harbor Road and the kayak launch at Eagle Beach. The project will include culvert r | Pavement Improvement | 2009-07-23 | 2009-05-27 | 2010-12-01 | 2010-11-04 | 11273789 | 4.597 | 0933027
349 | ALASKA | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | JUNEAU |  |  | 0933036 | The project will rehabilitate and resurface 4.52 miles of driving lanes on Glacier Highway in Juneau, between the Mendenhall Loop road and the Auke Bay Ferry Terminal, not including a segment between | Pavement Improvement | 2009-08-03 | 2009-05-27 | 2010-06-30 | 2010-09-20 | 3416667 | 4.474 | 0933036
350 | ALASKA | Completed | C250 | Highway Infrastructure Investment Grant | ALASKA | HAINES |  |  | 0956032 | This project will rebuild 0.59 miles of highway between the intersections of Front Street and Union Street including removal and replacement of asphalt, grading and adding material to the subgrade as | Pavement Improvement | 2009-08-12 | 2009-10-19 | 2011-05-26 | 2011-05-26 | 2175989 | 0.590 | 0956032
351 | ALASKA | Completed | C250 | Highway Infrastructure Investment Grant | ALASKA | SOUTHEAST FAIRBANKS |  |  | 0A11011 | This project will remove the existing truck weigh scale, scale house and associated utilities, and replace them with a new multi-platform scale and a scale house. Site work will include construction | New Construction | 2010-02-09 | 2010-02-23 | 2011-06-15 | 2011-12-05 | 3750000 | 0.000 | 0A11011
352 | ALASKA | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | MATANUSKA-SUSITNA |  |  | 0A15026 | This project will resurface 5.8 miles of the Glenn Highway between mileposts 34-42 and replace or repair guardrails including the energy-absorbing, collapsable ends of the guardrails. The project wil | Pavement Improvement | 2009-07-16 | 2009-06-04 | 2009-10-01 | 2009-09-12 | 1812582.91 | 5.800 | 0A15026
353 | ALASKA | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | MATANUSKA-SUSITNA | ANCHORAGE |  | 0A16039 | This project will resurface 15.188 miles of driving lanes, and all ramps and bridges, on the Glenn Highway between Hiland Road and Artillery Road interchanges. Replace or repair guardrails including | Pavement Improvement | 2009-06-12 | 2002-05-26 | 2009-10-01 | 2010-06-07 | 13318636 | 15.200 | 0A16039
354 | ALASKA | Completed | C240 | Highway Infrastructure Investment Grant | ALASKA | MATANUSKA-SUSITNA |  |  | 0A16040 | This project will resurface 10.03 miles of the Glenn Highway including driving lanes, ramps, interchages and bridges between Mt. View Drive and the Hiland Interchange. Upgrade or replace guardrails i | Pavement Improvement | 2010-05-03 | 2010-05-06 | 2010-08-01 | 2011-06-29 | 11550500 | 10.030 | 0A16040
355 | ALASKA | Underway | C240 | Highway Infrastructure Investment Grant | ALASKA | ANCHORAGE | ANCHORAGE |  | 0A16042 | This project will provide continuous highway lighting on the Glenn Highway for approximately 9.6 miles between the South Birchwood and Eklutna Interchanges. Lighting will consist of approximately 300 | Safety/Traffic Management | 2010-11-19 | 2010-11-19 | 2012-06-15 |  | 2034235 | 8.435 | 0A16042
356 | ALASKA | Completed | C250,C220,C240 | Highway Infrastructure Investment Grant | ALASKA | MATANUSKA-SUSITNA |  |  | 0A41022 | Rehabilitate the driving surface and widen the shoulders of 11.1 miles of roadway on the Parks Highway between Willow Creek and the Kashwitna River including 3 passing zones for northbound traffic an | Pavement Improvement | 2009-10-20 | 2009-10-21 | 2011-09-30 | 2011-08-31 | 25175000 | 11.000 | 0A41022
357 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | 008A204 | The Arizona Department of Transportation proposes to construct a Chain Link Fence project in Yuma County along I-8; US-95 (16th St) to Araby Rd in YUMA. | Other | 2009-10-08 | 2009-10-19 | 2010-02-08 | 2010-02-18 | 293156.27 | 5.396 | 008A204
358 | ARIZONA | Completed | C250,C240 | Highway Infrastructure Investment Grant | ARIZONA | YUMA |  | 07 | 008A206 | The Arizona Department of Transportation proposes pavement preservation from the state line to Fortuna. | Pavement Improvement | 2011-01-25 | 2011-02-14 | 2011-08-01 | 2012-07-03 | 14050623.07 |  | 008A206
359 | ARIZONA | Completed | C200,C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 07 | 008B200 | The Arizona Department of Transportation proposes a pavement preservation project in Maricopa County, on I-8, from Milepost 121 to Big Horn, east of Gila Bend. | Pavement Improvement | 2010-07-08 | 2010-08-02 | 2011-02-28 | 2011-05-23 | 1358212 | 13.541 | 008B200
360 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | 010B205 | The Arizona Department of Transportation proposes to reconstruct a traffic interchange in Pima County along I-10, from Cienega Creek (milepost 288.4) to Marsh Station (milepost 290.5). Work will incl | Pavement Widening | 2009-07-27 | 2010-09-11 | 2011-02-15 | 2011-08-16 | 25135071 | 6.054 | 010B205
361 | ARIZONA | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | PINAL |  | 01 | 010C203 | The Arizona Department of Transportation proposes a widen freeway project in Pinal County, on I-10, from I-8 to SR 87. | Pavement Improvement | 2010-06-29 | 2010-08-04 | 2012-01-04 |  | 40735939 | 10.426 | 010C203
362 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PINAL |  | 01 | 010D204 | The Arizona Department of Transportation proposes to complete a freeway widening project in Pinal County along I-10 from the Town of Picacho to the Picacho Peak traffic interchange. Work will include | Pavement Improvement | 2009-07-29 | 2009-08-14 | 2010-09-10 | 2010-11-22 | 17294637.35 | 5.706 | 010D204
363 | ARIZONA | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 07 | 010D206 | The Arizona Department of Transportation will construct an ITS Freeway Management System project in Pima County along Interstate 10 from milepost 250.2 to milepost 267.2 and along Interstate 19 towards Valencia Road in Tucson. | New Bridge Construction | 2010-01-28 | 2010-02-18 | 2011-03-24 | 2011-06-27 | 4317528.73 | 5.378 | 010D206
364 | ARIZONA | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | 010E201 | The Arizona Department of Transportation proposes to reconstruct a traffic interchange in Pima County along I-10, from Cienega Creek (milepost 288.4) to Marsh Station (milepost 290.5). Work will incl | Pavement Widening | 2009-07-27 | 2009-07-27 | 2010-12-30 |  | 10122297 | 0.519 | 010E201
365 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | 010E203 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Pima County along I-10, from Rita Rd to Houghton Rd east of TUCSON a total of 4 miles. | Pavement Improvement | 2009-07-08 | 2009-09-10 | 2009-12-24 | 2009-12-21 | 2840742.84 | 3.991 | 010E203
366 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | 010E204 | The Arizona Department of Transportation proposes to replace barbed wire fence in Pima County along I-10; from Vail Rd to Pima/Cochise County Line. | Other | 2009-10-05 | 2009-10-22 | 2010-01-28 | 2010-04-01 | 180294.57 | 16.785 | 010E204
367 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | 010E205 | The Arizona Department of Transportation proposes a pavement preservation project in Pima County, on I-10, from Houghton Rd to Mountain View TI, approximately 20 miles southeast of Tucson. | Pavement Improvement | 2010-06-03 | 2010-06-23 | 2010-10-13 | 2011-03-28 | 4239664.02 | 5.302 | 010E205
368 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 07 | 010E206 | The Arizona Department of Transportation proposes a pavement preservation project in Pima County, on I-10, from Kino Parkway to Valencia Rd, in Tucson. | Pavement Improvement | 2010-12-06 | 2011-01-18 | 2011-08-06 | 2009-09-30 | 6527200 |  | 010E206
369 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 010F201 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Cochise County along I-10 (EB), from East Benson to Johnson Rd (milepost 307.68 to milepost 321.60) total of 14.1 miles. | Pavement Improvement | 2009-06-08 | 2009-07-06 | 2009-12-28 | 2010-01-26 | 6718114 | 13.705 | 010F201
370 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 010F203 | The Arizona Department of Transportation proposes to implement a pavement preservation project in Cochise County along I-10 (east bound); from Luzena to Bowie. | Pavement Improvement | 2009-07-29 | 2009-08-24 | 2009-10-19 | 2010-01-12 | 1341645.19 | 4.909 | 010F203
371 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 03 | 017A207 | The Arizona Department of Transportation proposes to construct a Freeway Widening project in Maricopa County along I-17; SR-74 to Anthem Way in PHOENIX to include Major widening along 5 miles to provi | Pavement Widening | 2009-06-30 | 2009-08-05 | 2010-07-08 | 2010-09-27 | 14237477 | 4.831 | 017A207
372 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 02 | 017A210 | The Arizona Department of Transportation proposes to construct a Right-of-way fence replacement project in Maricopa County along Interstate 17 (South Bound); from Table Mesa Interchange to Rock Springs Interchange. | Other | 2009-06-30 | 2009-07-29 | 2009-09-17 | 2009-12-16 | 95040.01 | 6.105 | 017A210
373 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | 017A211 | The Arizona Department of Transportation proposes a widen roadway project in Maricopa County within the City of Phoenix on SB I-17 beginning at the I-10 stack and extending to Indian School Road. | Pavement Widening | 2010-06-29 | 2010-07-21 | 2010-12-04 | 2010-12-14 | 1237799 | 0.015 | 017A211
374 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | SANTA CRUZ |  | 07 | 019A202 | The Arizona Department of Transportation proposes to replace barbed wire fence in Santa Cruz County along I-19; from Rio Rico Rd to Chaves Siding Road north of NOGALES. | Other | 2009-11-04 | 2010-11-16 | 2010-04-15 | 2010-11-24 | 491785 | 13.297 | 019A202
375 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | 040A208 | The Arizona Department of Transportation proposes to replace barb wire fence in Mohave County along Interstate 40; California State Line to Oatman Hwy Interchange to include Safety. | Other | 2009-08-28 | 2009-09-16 | 2009-12-16 | 2010-01-27 | 205684.07 | 44.328 | 040A208
376 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | 040B205 | The Arizona Department of Transportation proposes to construct a fence replacement project in Mohave County along Interstate 40; Railroad Ave to Rattlesnake Wash in Kingman, AZ, to include chain link fence. | Other | 2009-06-23 | 2009-07-16 | 2009-11-23 | 2010-02-25 | 434779.89 | 4.148 | 040B205
377 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | 040C202 | The Arizona Department of Transportation proposes to replace barb wire fence in Coconino County along Interstate 40 from State Route 64 (milepost (MP) 166) to Volunteer Wash (MP 188). | Other | 2009-08-10 | 2009-08-24 | 2010-01-22 | 2010-10-29 | 418995.3 | 22.157 | 040C202
378 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | 040C203 | The Arizona Department of Transportation proposes to construct a pavement preservation project in Coconino County along Interstate 40 from milepost (MP) 150 to MP 190.8. | Pavement Improvement | 2009-08-04 | 2009-08-17 | 2009-09-21 | 2009-08-26 | 443353.34 | 41.121 | 040C203
379 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | 040D018 | The Arizona Department of Transportation proposes to reconstruct the roadway and alleviate steep grades in Coconino County along Interstate 40 westbound near Walnut Canyon (milepost 205) east of Flagstaff, AZ. | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2010-08-13 | 2010-08-19 | 6884386.6 | 0.073 | 040D018
380 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | APACHE |  | 01 | 040E201 | The Arizona Department of Transportation proposes to construct features that will protect the Dead River Bridge (Bridge #565) in Apache County along Interstate 40 (Eastbound) from the effects of high water. | Bridge Improvement | 2009-06-25 | 2009-07-07 | 2009-09-29 | 2009-10-05 | 133371.67 | 0.027 | 040E201
381 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | APACHE |  | 01 | 040E202 | The Arizona Department of Transportation proposes a bridge rehabilitation project in Apache County along Interstate 40 at the Black Creek west of Houck, AZ; project also includes high water protective features. | Bridge Improvement | 2009-06-08 | 2009-07-06 | 2009-10-19 | 2009-10-05 | 401053.08 | 0.036 | 040E202
382 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 02 | 060A204 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Maricopa County along US 60, from MP 107.6 to MP 110.2 in WICKENBURG to include Micro Seal. | Pavement Improvement | 2009-08-24 | 2009-10-12 | 2009-11-11 | 2010-07-08 | 333011.92 | 2.535 | 060A204
383 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | 060B200 | The proposed widen roadway project is located in Maricopa County within the City of Peoria on US 60. The project begins at MP 148.5 and extends to MP 150.3 for a total length of approximately 1.8 miles. The work consists of widening Grand Avenue | Pavement Widening | 2009-06-03 | 2009-06-03 | 2010-12-13 | 2011-09-20 | 8046826.32 | 1.885 | 060B200
384 | ARIZONA | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 060B201 | The Arizona Department of Transportation proposes to construct a Roadway Widening project in Maricopa County along US-60 (Grand Av); SR-303L to 99th Av to include Road Widening. | Pavement Widening | 2010-01-29 | 2010-01-22 | 2011-11-03 | 2012-06-26 | 22612061 | 10.140 | 060B201
385 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PINAL | PHOENIX, AZ | Multiple | 060C201 | The Arizona Department of Transportation proposes to construct a Gateway graphics project in Pinal County along US 60 at Tomahawk Rd in APACHE JUNCTION (Graphics) to include Gateway graphics. | Transportation Enhancements | 2009-10-05 | 2009-11-19 | 2011-05-17 | 2010-09-22 | 345067.89 | 0.210 | 060C201
386 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PINAL | PHOENIX, AZ | Multiple | 060C202 | The Arizona Department of Transportation proposes to construct a Transportation Enhancement project in Pinal County along US-60 at Goldfield Rd in APACHE JUNCTION to include Gateway graphics. | Transportation Enhancements | 2009-10-05 | 2009-11-19 | 2011-05-17 | 2010-09-22 | 356311.81 | 0.235 | 060C202
387 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 060D201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along US-60, Miami City Limits to McMillan Wash. | Pavement Improvement | 2009-06-25 | 2009-08-05 | 2010-01-21 | 2010-10-18 | 10459822.74 | 8.250 | 060D201
388 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 060E202 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along US-60, from Timber Mountain (MP 278.8) to Seneca (MP 286.4). | Pavement Improvement | 2009-05-28 | 2009-07-13 | 2009-09-30 | 2009-10-14 | 3020674.22 | 6.822 | 060E202
389 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | YAVAPAI |  | 01 | 069A206 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Yavapai County along SR-69, I-17 to Big Bug Creek. | Pavement Improvement | 2009-06-10 | 2009-06-26 | 2009-09-03 | 2009-09-25 | 2295022.4 | 7.744 | 069A206
390 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GRAHAM |  | 01 | 070A202 | The Arizona Department of Transportation proposes to construct a traffic intersection improvement project in Graham County on US-70 @ 8th Avenue in SAFFORD to include pavement and signal improvements. | Pavement Improvement | 2009-08-03 | 2009-08-31 | 2009-10-26 | 2009-11-03 | 220664 | 0.159 | 070A202
391 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 073A200 | The Arizona Department of Transportation proposes to construct a Replace Barb Wire Fence project in Gila County along SR 73; Cedar Creek to Canyon Day to include Safety. | Other | 2009-09-08 | 2009-09-21 | 2010-02-24 | 2010-04-26 | 350214.61 | 11.420 | 073A200
392 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 02 | 074A200 | The Arizona Department of Transportation proposes to construct a Widen Roadway project in Maricopa County along SR-74; MP 19 - New River Rd to include new construction of passing lanes on both eastbound and westbound SR 74. | Pavement Widening | 2009-11-02 | 2009-11-19 | 2010-06-27 | 2010-11-03 | 2730501 | 1.427 | 074A200
393 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 02 | 074A201 | The Arizona Department of Transportation proposes a widen roadway project in Maricopa County on SR 74 from Milepost 14 to Milepost 16. | Pavement Widening | 2010-07-21 | 2010-08-18 | 2011-04-06 | 2012-12-03 | 3603864 | 2.001 | 074A201
394 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | GREENLEE |  | 01 | 075A001 | The Arizona Department of Transportation proposes to construct a transportation enhancement project in Greenlee County along SR 75 in York Valley to include pathways, railings, and retaining walls. | Transportation Enhancements | 2009-10-27 | 2009-11-19 | 2010-03-18 | 2010-05-07 | 270508 | 0.510 | 075A001
395 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 080A201 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Cochise County along SR-80 through TOMBSTONE. | Pavement Improvement | 2009-06-30 | 2009-08-12 | 2009-10-21 | 2009-09-30 | 761584.47 | 0.962 | 080A201
396 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 080A202 | The Arizona Department of Transportation proposes to replace fence in Cochise County along SR-80; from Double Adobe Road to the Town of Douglas. | Other | 2009-06-16 | 2009-07-13 | 2009-12-21 | 2010-01-14 | 379482.65 | 14.000 | 080A202
397 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | SANTA CRUZ |  | 08 | 083A201 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Santa Cruz County along SR-83, near Sonoita from milepost 31.6 to milepost 43.5, a total of 11.9 miles. | Pavement Improvement | 2009-06-16 | 2009-07-06 | 2009-10-12 | 2011-11-19 | 2277274.63 | 10.293 | 083A201
398 | ARIZONA | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 085B200 | The Arizona Department of Transportation proposes to construct a Widen Roadway project in Maricopa County along SR-85; Southern Ave to I-10. | Pavement Widening | 2009-10-06 | 2009-10-22 | 2010-11-26 | 2011-08-03 | 10147270.09 | 0.921 | 085B200
399 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 07 | 086A008 | The Arizona Department of Transportation proposes to construct a shoulder widening project in Pima County along SR-86 west Sells from milepost 73.9 to milepost 77.4. | Pavement Improvement | 2009-07-28 | 2009-09-10 | 2010-01-08 | 2012-12-03 | 2127459.61 | 3.680 | 086A008
400 | ARIZONA | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 07 | 086A200 | The Arizona Department of Transportation proposes a widen roadway project in Pima County on SR 86 between milepost 141.1 and the Reservation Boundary, approximately 5 miles west of Robles Junction.? | Pavement Improvement | 2010-06-28 | 2010-07-23 | 2011-09-14 |  | 8512555 | 0.680 | 086A200
401 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 07 | 086A203 | The Arizona Department of Transportation proposes to conduct a pavement preservation project in Pima County along SR-86, from Kinney Road to La Cholla Blvd in TUCSON, a total of 3.1 miles. | Pavement Improvement | 2009-08-05 | 2009-08-27 | 2010-02-22 | 2010-10-07 | 2342524.74 | 3.164 | 086A203
402 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 07 | 086A204 | The Arizona Department of Transportation proposes to perform a bridge deck rehabilitation project in Pima County on SR-86 at the Santa Cruz River in TUCSON. Work will include repair of deteriorating deck surface of Santa Cruz River Bridge #528. | Bridge Improvement | 2009-07-08 | 2009-07-18 | 2009-08-28 | 2009-08-31 | 315844.72 | 0.049 | 086A204
403 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 07 | 086A205 | The Arizona Department of Transportation proposes to complete the widening of SR-86 in Pima County across Brawley Wash west of TUCSON from milepost 145.69 to milepost 148.3. | Pavement Improvement | 2009-08-03 | 2009-09-01 | 2010-02-16 | 2010-11-02 | 1622928.59 | 2.562 | 086A205
404 | ARIZONA | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | 087B205 | The Arizona Department of Transportation proposes a reconstruct roadway project in Maricopa County within the Tonto National Forest on SR 87 between New Four Peaks Road and Dos S Ranch Road. | Pavement Widening | 2010-06-01 | 2010-06-24 | 2011-06-09 |  | 13389170 | 5.565 | 087B205
405 | ARIZONA | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | 087B206 | The Arizona Department of Transportation proposes a reconstruct and repair roadway cut slopes project in Maricopa County within the Tonto National Forest on SR 87 between MP 211.8 and MP 213. | Pavement Improvement | 2010-06-01 | 2010-06-24 | 2011-06-09 |  | 1220985 | 1.235 | 087B206
406 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 087C002 | The Arizona Department of Transportation proposes to construct a Shoulder Widening project in Gila County along SR-87, PAYSON to PINE. | Pavement Improvement | 2009-05-22 | 2009-06-02 | 2009-12-29 | 2010-11-09 | 5275943.59 | 1.215 | 087C002
407 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 087C201 | The Arizona Department of Transportation proposes to construct a Replace Barb Wire Fence project in Gila County along SR 87; PAYSON to PINE. | Other | 2009-08-18 | 2009-09-01 | 2010-02-16 | 2010-04-29 | 435354.84 | 12.049 | 087C201
408 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO | FLAGSTAFF | 01 | 089C200 | The Arizona Department of Transportation proposes to construct a pavement preservation project in Coconino County along US 89; Townsend (milepost (MP) 420) to Fernwood (MP 426) north of Flagstaff, AZ. | Pavement Improvement | 2009-05-22 | 2009-06-22 | 2009-10-07 | 2009-10-20 | 4463750.62 | 5.119 | 089C200
409 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | 093B201 | The Arizona Department of Transportation proposes to construct new southbound travel lanes, creating a divided highway, in Mohave County along US 93, from milepost (MP) 104.1 to MP 106 (Ranch Rd Section). | New Construction | 2009-07-28 | 2009-08-05 | 2010-07-31 | 2011-05-23 | 7514739.07 | 2.055 | 093B201
410 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | 095A200 | The Arizona Department of Transportation proposes sidewalk, landscaping, irrigation, and pedestrian lighting work on Us 95 Somerton West Gateway Mp 12.36 - Mp 12.51. | Transportation Enhancements | 2011-01-03 | 2011-01-19 | 2011-04-27 | 2012-07-20 | 185744.09 |  | 095A200
411 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | 095A201 | The Arizona Department of Transportation proposes to construct a widening project in Yuma County along US 95 (16th Street), I-8 to Palms Ave. | Pavement Widening | 2009-08-18 | 2009-09-08 | 2010-08-10 | 2011-04-07 | 10906523.66 | 0.709 | 095A201
412 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | LA PAZ |  | 07 | 095B200 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in La Paz County along US-95, from Peligro (MP 63) to Clarks (MP 80). | Pavement Improvement | 2009-09-28 | 2009-10-13 | 2010-04-27 | 2010-06-21 | 7941554.6 | 28.461 | 095B200
413 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | YUMA |  | 07 | 095B202 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Yuma County along US 95, from MP 44.3 to MP 312.7. | Pavement Improvement | 2009-08-24 | 2009-09-14 | 2009-11-09 | 2009-10-07 | 356808.84 | 9.652 | 095B202
414 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | LA PAZ |  | 07 | 095C203 | The Arizona Department of Transportation proposes to construct a Passing Lanes project in La Paz County along SR 95 South of Bouse Wash. | Pavement Improvement | 2009-06-30 | 2009-07-27 | 2009-10-29 | 2009-11-06 | 1655770 | 2.248 | 095C203
415 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | 0RV0201 | The Town of Oro Valley will perform a pavement preservation project on the following roadways: LaCholla, First, Lamber, Moor,Tan in the Town of Oro Valley. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-07-28 | 2010-07-13 | 1265533.62 | 0.894 | 0RV0201
416 | ARIZONA | Underway | C250 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | 0RV0202 | The Town of Oro Valley will perform a pavement preservation project on Lacanada Dr. (Lambert Lane To Naranja Dr.) in the Town of Oro Valley. | Pavement Improvement | 2011-01-31 | 2011-02-23 | 2011-04-27 |  | 823000 |  | 0RV0202
417 | ARIZONA | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 07 | 101A203 | The Arizona Department of Transportation proposes a widen roadway project in Maricopa County, on 99th Avenue between I-10 and Van Buren Street, within the Cities of Avondale and Tolleson. | Pavement Widening | 2010-06-28 | 2010-07-21 | 2011-01-12 | 2011-04-29 | 2141425 |  | 101A203
418 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 101A204 | The Arizona Department of Transportation proposes to widen Union Hills Road Traffic Interchange in Maricopa County along SR-101L (Aqua Fria Frwy) @ Beardsley Rd/Union Hills Dr in GLENDALE. | New Bridge Construction | 2009-10-26 | 2009-10-26 | 2012-01-01 | 2011-12-12 | 5167374 | 1.213 | 101A204
419 | ARIZONA | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | 101A205 | The Arizona Department of Transportation proposes to construct an auxiliary lane project in Maricopa County, on SR 101L, eastbound between 51st Avenue and 35th Avenue within the City of Phoenix. | Pavement Improvement | 2010-05-13 | 2010-06-07 | 2011-03-04 | 2011-03-25 | 1546079.89 | 2.003 | 101A205
420 | ARIZONA | Completed | C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 101A206 | The Arizona Department of Transportation proposes to construct an auxiliary lane project in Maricopa County, on SR 101L, southbound between Northern Avenue and Grand Avenue within the City of Peoria. | Pavement Improvement | 2010-05-13 | 2010-06-07 | 2011-03-04 | 2011-03-25 | 1829433.12 | 2.807 | 101A206
421 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | 101A207 | The Arizona Department of Transportation proposes an intersection improvement project in Maricopa County, within the City of Peoria on Olive Avenue at the intersection with Agua Fria Freeway (101L). | Pavement Widening | 2010-03-25 | 2010-04-21 | 2010-11-10 | 2011-12-12 | 2172403 | 0.358 | 101A207
422 | ARIZONA | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | 143A200 | The Arizona Department of Transportation proposes a reconstruct traffic interchange project in Maricopa County, at the intersection of SR 143 and Sky Harbor Boulevard, within the City of Phoenix. | Pavement Widening | 2010-10-27 | 2010-12-02 | 2012-08-27 |  | 12570454.85 |  | 143A200
423 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | 160A001 | The Arizona Department of Transportation proposes a pavement preservation project in Coconino County along US 160, from the junction of US 89 and US 160 to Van's Trading Post; west of Tuba City, AZ - 9.0 miles. | Pavement Improvement | 2009-06-01 | 2009-06-11 | 2009-10-01 | 2009-09-18 | 3062945 | 8.124 | 160A001
424 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 160A200 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County along US 160, in Kayenta, AZ to Navajo Route 59 - 12.5 miles | Pavement Widening | 2009-05-26 | 2009-06-04 | 2009-12-31 | 2009-12-17 | 6338995.79 | 12.502 | 160A200
425 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 160B200 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County along US 160; from Navajo Route 59 to Dennehotso - 14 miles. | Pavement Improvement | 2009-05-26 | 2009-06-04 | 2009-12-31 | 2009-12-17 | 3187272.15 | 14.003 | 160B200
426 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 180B202 | The Arizona Department of Transportation proposes to replace barb wire fence in Navajo County along US 180, east of Holbrook, AZ; from milepost (MP) 307.3 to 324.9, near the Petrified Forest Road. | Other | 2009-08-05 | 2009-09-08 | 2010-03-22 | 2010-06-10 | 576439.86 | 17.393 | 180B202
427 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE | PHOENIX, AZ | 08 | 191A200 | The Arizona Department of Transportation proposes to construct an intersection improvement project in Cochise County along US-191 @ High Street in Sunsites (MP 48.36 to MP 48.94 to include Widen Roadway for Turn Lanes (left and right). | Pavement Improvement | 2009-06-16 | 2009-07-20 | 2009-10-26 | 2009-11-25 | 478303.33 | 0.581 | 191A200
428 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | GRAHAM |  | 01 | 191B001 | The Arizona Department of Transportation proposes to construct a transportation enhancement project in Graham County along US 191 from Discovery Blvd. to Relations St. in the Town of Safford. Work wi | Transportation Enhancements | 2010-01-04 | 2010-01-25 | 2010-07-07 | 2010-06-04 | 357650.32 | 1.468 | 191B001
429 | ARIZONA | Underway | C240 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | 191B200 | The Arizona Department of Transportation proposes to construct a parallel road project in Cochise County on US 191 from Dial Wash to Ten Ranch south of SAFFORD. | New Construction | 2010-06-30 | 2010-07-21 | 2011-08-01 |  | 7800624 | 5.636 | 191B200
430 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GREENLEE |  | 01 | 191C202 | The Arizona Department of Transportation proposes an intersection improvement project in Greenlee County along US 191 at Black Hills Rd (Back County Byway) at milepost 159.5. | Pavement Improvement | 2009-07-24 | 2010-09-15 | 2010-01-08 | 2010-04-08 | 790888.89 | 0.142 | 191C202
431 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GREENLEE |  | 01 | 191C203 | The Arizona Department of Transportation proposes to construct a drainage improvement project in Greenlee County along US-191 (Coronado Trail) at milepost 175 to include Lower Coronado Drainage Improvements. | Other | 2009-09-28 | 2009-10-19 | 2010-02-08 | 2010-07-12 | 373630.3 | 4.747 | 191C203
432 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | APACHE |  | 01 | 191E202 | The Arizona Department of Transportation proposes a pavement preservation project in Apache County along US 191, from milepost (MP) 427 to MP 436 south of Chinle, AZ. | Pavement Improvement | 2009-06-16 | 2009-07-23 | 2009-10-26 | 2009-10-29 | 2710391.11 | 8.381 | 191E202
433 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 260C003 | The Arizona Department of Transportation proposes to construct a Transportation Enhancement project in Navajo County along SR-260; Porter Mtn. Rd to Woodland Rd in PINETOP/LAKESIDE to include Pedestrian lighting and plantings. | Other | 2009-10-28 | 2010-05-03 | 2010-05-06 | 2011-08-29 | 627151 | 0.389 | 260C003
434 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | 277A201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Navajo County along SR 277, from MP 305.7 to 312.7. | Pavement Improvement | 2009-08-05 | 2009-08-10 | 2009-09-28 | 2009-09-28 | 315343.25 | 6.831 | 277A201
435 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | STATEWIDE |  |  | 999A238 | The Arizona Department of Transportation proposes to implement a Pavement Micro Seal project Statewide in various Counties in Southeast Arizona. | Pavement Improvement | 2009-08-24 | 2009-09-16 | 2009-12-09 | 2010-12-14 | 1037435.5 | 5.020 | 999A238
436 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | STATEWIDE |  |  | 999A239 | The Arizona Department of Transportation proposes a pavement preservation project in Navajo County at various locations. | Pavement Improvement | 2009-08-03 | 2009-08-19 | 2009-10-12 | 2010-10-19 | 608576.08 | 5.508 | 999A239
437 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | 999A242 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project in Gila County along Globe District Chip Seals to include Chip Seal. | Pavement Improvement | 2009-07-29 | 2009-08-17 | 2009-10-05 | 2009-09-30 | 397464.4 | 7.284 | 999A242
438 | ARIZONA | Completed | C240 | Highway Infrastructure Investment Grant | ARIZONA | STATEWIDE |  |  | 999A244 | The Arizona Department of Transportation proposes to construct Pipe Liner Inserts (Relining) in VARIOUS Locations Statewide. | Other | 2010-01-05 | 2010-01-20 | 2010-09-01 | 2010-09-22 | 2092408.97 | 9.087 | 999A244
439 | ARIZONA | Underway | C490 | OJT/SS | ARIZONA | STATEWIDE |  |  | 999M018 | The Arizona Department of Transportation will be supporting the On-The-Job Training, Support Services Program 2009--Pre-Apprenticeship In Highway Construction Program. | Other | 2010-10-01 | 2010-10-01 |  |  | 509883 |  | 999M018
440 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PINAL |  | 06 | APJ0200 | The City of Apache Junction, AZ will perform Pavement Preservation along Ironwood Drive from US 60 (Superstition Frwy) to Southern Ave. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-08-11 | 2011-03-30 | 1559598.47 | 0.773 | APJ0200
441 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PINAL | PHOENIX, AZ | 06 | APJ0203 | The City of Apache Junction will perform pavement preservation at Ironwood Drive from 16Th Ave To Broadway Ave. | Pavement Improvement | 2010-11-29 | 2011-02-22 | 2011-08-09 | 2011-09-01 | 688800 |  | APJ0203
442 | ARIZONA | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 07 | AVN0203 | The City of Avondale will construct an interim Traffic Operations Center. | Safety/Traffic Management | 2012-01-05 | 2012-01-18 | 2012-04-04 |  | 259292 |  | AVN0203
443 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | AVN0206 | The City of Avondale will perform a Preliminary engineering, design and construction along Dysart Rd; I-10 to Indian School Rd in AVONDALE. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-07-05 | 2010-12-09 | 1773084.17 | 0.474 | AVN0206
444 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | AVN0207 | The City of Avondale will perform a Preliminary engineering, design and construction for along Dysart Rd; Van Buren St to I-10 in AVONDALE. | Other | 2009-06-23 | 2009-06-23 | 2010-01-29 | 2010-02-23 | 48515 | 0.540 | AVN0207
445 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | BKY0201 | The Town of Buckeye will pave shoulders at various locations: Mc-85/Monroe, Southern Ave, Apache Rd. | Pavement Improvement | 2011-03-10 | 2011-03-24 | 2011-05-03 | 2011-07-25 | 249835 |  | BKY0201
446 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | BKY0202 | The Town of Buckeye will perform a Pre-engineering/Design and Pavement Rehabilitation and Preservation along Various Locations on Functionally Classified Roads in BUCKEYE. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-06-23 | 2011-01-27 | 1274037 | 0.992 | BKY0202
447 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | BUL0200 | Bullhead City will perform a pavement preservation project of existing deteriorating asphalt pavement along Miracle Mile in Bullhead City, AZ. | Pavement Improvement | 2009-07-02 | 2009-07-02 | 2010-08-30 | 2010-10-08 | 452864.79 | 1.325 | BUL0200
448 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO |  | 01 | CCN0204 | The Coconino County will perform a pavement preservation along Lake Mary Road south of Flagstaff, AZ. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-10-27 | 2010-10-27 | 703023.96 | 0.000 | CCN0204
449 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO | FLAGSTAFF | 01 | CCN0205 | The Coconino County will perform a pavement preservation project along State Route B40 (Old US 66), from I-40 to City Limits, west of Flagstaff, AZ. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-08-26 | 2010-08-18 | 820717.8 | 0.000 | CCN0205
450 | ARIZONA | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | CFE0201 | The Town of Carefree, AZ will perform Design and construction of repair and restoration of Cave Creek Road from Scopa Trail to Carefree Eastern Border. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2011-05-18 | 2010-12-01 | 582529.72 | 4.000 | CFE0201
451 | ARIZONA | Underway | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | CHN0014 | The City of Chandler, AZ will construct a Multi-Use Pathway along Paseo Road. | Transportation Enhancements | 2010-07-20 |  | 2011-03-23 |  | 867383.31 | 1.500 | CHN0014
452 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | CHN0025 | The City of Chandler, AZ will perform Intersection and Capacity Improvement along Chandler Blvd at Dobson Rd, and on Dobson Rd from Chandler Blvd to Frye Rd. | Pavement Widening | 2009-08-24 | 2009-08-24 | 2011-02-04 | 2011-03-04 | 3949421 | 0.500 | CHN0025
453 | ARIZONA | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | CHN0211 | The City of Chandler will perform Design and reconstruction of pavement along Price Road; Germann Road to Queen Creek Road in CHANDLER. | Pavement Improvement | 2009-06-30 | 2009-06-30 | 2011-04-25 |  | 2018178 | 1.000 | CHN0211
454 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PINAL |  | 08 | CSG0200 | The City of Casa Grande will install intersection traffic signals at the following intersection Peart Road / McCartney Road and Peart Road / Korsten Road in Casa Grande. | Other | 2009-06-18 | 2009-06-18 | 2009-10-16 | 2010-01-11 | 17562 | 0.000 | CSG0200
455 | ARIZONA | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | CVK0201 | The Arizona Department of Transportation proposes to construct a Pavement Preservation project along Cave Creek Road from Spur Crossing to the Cave Creek Town Limits in CAVE CREEK, AZ. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2011-05-18 | 2010-11-09 | 521389.16 | 1.500 | CVK0201
456 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE |  | 08 | DGS0005 | The City of Douglas will perform a transportation enhancement project which will include a shared use pathway with ADA ramps over a railroad bridge along Paseo de la Amistad. | Transportation Enhancements | 2009-12-29 | 2010-02-01 | 2010-08-27 | 2011-04-10 | 545968.41 | 0.200 | DGS0005
457 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | APACHE |  | 01 | EGR0200 | The City of Eager will perform a Pavement Preservation along Main Street; from US-60 to SR-260 in EAGER. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-07-24 | 2011-05-13 | 867092 | 1.600 | EGR0200
458 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | ELM0202 | The City of El Mirage will perform a Pre-Engineer/Design and Mill and Replace Existing Pavement along Various Locations on Functionally Classified Roadways. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-09-01 | 2011-01-27 | 628367.77 | 1.500 | ELM0202
459 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | ELM0203 | The City of El Mirage will micro-seal pavement surface - Cactus To Olive | Pavement Improvement | 2011-03-07 | 2011-03-24 | 2011-05-08 | 2011-07-07 | 167750 |  | ELM0203
460 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | COCONINO | FLAGSTAFF | 01 | FLA0006 | The City of Flagstaff will perform a improvements along State Route B40 in downtown Flagstaff, AZ; the project includes pathway and landscaping improvements. | Transportation Enhancements | 2009-09-14 | 2009-09-14 | 2010-06-11 | 2010-06-11 | 470119 | 0.000 | FLA0006
461 | ARIZONA | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | FTH0006 | The City of Fountain Hills will construct a median, bike Lanes and perform pavement preservation from Shea Blvd, Fountain Hills Blvd To Saguaro Blvd. | Transportation Enhancements | 2011-04-06 | 2011-04-20 | 2011-08-03 |  | 1133610.5 |  | FTH0006
462 | ARIZONA | Completed | C250,C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GBD0200 | The City of Gila Bend will construct Pedestrian and Landscape Improvements along Various Locations along SR-85 (Pima St) in GILA BEND. | Transportation Enhancements | 2009-09-10 | 2009-09-10 | 2011-10-19 | 2011-10-04 | 244147 | 0.000 | GBD0200
463 | ARIZONA | Underway | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GBD0203 | The City of Gila Bend will design and construct a carpool lane and transit park & ride lot at the Gila Bend Airport on SR85. | Other | 2009-09-10 | 2009-09-10 | 2010-10-25 |  | 298862 | 0.000 | GBD0203
464 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GDY0202 | The City of Goodyear will perform a Pre-Engineer/Design to mill, patch and replace pavement along Various Locations on Functionally Classified Roads in GOODYEAR. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-11-15 | 2010-11-15 | 655149.28 | 2.500 | GDY0202
465 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | GGI0005 | The Gila County, will perform a Bridge Rehabilitation along Ice House, Bridge and Ice House Wash Bridge and Approaches in GLOBE. | Bridge Replacement | 2009-06-18 | 2009-06-18 | 2010-12-08 | 2011-05-06 | 1732990 | 0.000 | GGI0005
466 | ARIZONA | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | GIL0012 | The City of Gilbert will construct a multi use path along the Eastern Canal: Guadalupe Rd To Elliot Rd (Santan Vista Trail Phase II). | Transportation Enhancements | 2011-03-02 | 2011-05-23 | 2011-08-31 |  | 939703 |  | GIL0012
467 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | GIL0015 | The City of Gilbert will construct Pedestrian bridges across a major Canal within the City. | Transportation Enhancements | 2010-02-22 | 2009-12-14 | 2010-05-06 | 2010-06-30 | 270000 | 0.000 | GIL0015
468 | ARIZONA | Underway | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | GIL0202 | The City of Gilbert will construct Sidewalks, ADA Handicap Ramps, Landscaping & Irrigation in the Heritage District in Downtown GILBERT. | Transportation Enhancements | 2009-09-24 | 2009-08-25 | 2010-06-03 |  | 421847.85 | 1.300 | GIL0202
469 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | GIL0203 | The City of Gilbert, AZ will perform Design and Construction of Chip Seal Overlays on various arterial roadways in GILBERT. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2011-05-18 | 2011-01-27 | 3923827.93 | 15.000 | GIL0203
470 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | GLN0201 | The City of Glendale will perform a Pedestrian corridor enhancements along Old Roma Alley in GLENDALE. | Transportation Enhancements | 2010-03-01 | 2010-02-03 | 2010-06-13 | 2010-10-13 | 467549 | 0.100 | GLN0201
471 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GLN0211 | The City of Glendale, will perform a Pre-Engineer/Design for pavement overlay along Glendale Ave; 51st Ave to 66th Ave in GLENDALE. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-09-26 | 2011-01-27 | 1651301.25 | 2.000 | GLN0211
472 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0212 | The City of Glendale will perform a Pre-Engineer/Design and construct pavement surface treatment along Litchfield Rd; Missouri to Northern Ave in GLENDALE. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-11-04 | 2011-06-13 | 653966 | 2.000 | GLN0212
473 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0214 | The City of Glendale will Install thermoplastic pavement markings along 25 Miles on Arterial Streets in GLENDALE. | Pavement Widening | 2009-06-12 | 2009-06-12 | 2011-11-22 | 2010-08-24 | 228002.37 | 25.000 | GLN0214
474 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GLN0215 | The City of Glendale will install wireless communication devices along Camelback Rd from 47th Ave to 83rd Ave to improve communication with traffic signals. | Safety/Traffic Management | 2009-06-12 | 2009-06-12 | 2010-11-17 | 2010-10-29 | 180035.13 | 4.500 | GLN0215
475 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0216 | The City of Glendale will install wireless communication devices along Bethany Home Rd from 63rd Ave to 83rd Ave to improve communication with traffic signals. | Other | 2009-06-23 | 2009-06-23 | 2010-05-21 | 2010-05-21 | 13332 | 2.500 | GLN0216
476 | ARIZONA | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0217 | The City of Glendale will install CCTV cameras at various locations on their functionally classified roadways to improve traffic operations and management. | Other | 2009-06-23 | 2009-06-23 |  |  | 13282 | 0.000 | GLN0217
477 | ARIZONA | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | GLN0218 | The City of Glendale will modernize traffic signals at various locations on functionally classified roadways to improve traffic operations and management. | Other | 2009-06-23 | 2009-06-23 |  |  | 13512 | 0.000 | GLN0218
478 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GLN0219 | The City of Glendale will install new traffic signal cabinets and controllers at various locations on functionally classified roadways to improve traffic operations and management. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2011-06-22 | 2011-03-03 | 1189815.2 | 0.000 | GLN0219
479 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | GLN0233 | The City of Glendale will perform pavement preservation on Bell Road - 59Th Ave To 70Th Ave. | Pavement Improvement | 2011-03-29 | 2011-04-20 | 2011-07-04 | 2011-07-15 | 1016837 |  | GLN0233
480 | ARIZONA | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | GRI0200 | ADOT will perform Design and Construction of Pavement Rehab projects along Various Locations on Functionally Classified Roads within Gila River Indian Community. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-11-15 | 2010-11-15 | 529769.54 | 1.500 | GRI0200
481 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | GUA0200 | The Town of Guadalupe AZ will perform Replacement of existing street lights to improve safety along Various Roadways in GUADALUPE, AZ | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-08-16 | 2010-11-03 | 598668.35 | 0.000 | GUA0200
482 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | IT00200 | The Tohono O'odham Indian Reservation will perform a pavement preservation project along San Xavier Road from Mission to Los Reales on the Tohono O'odham Nation. | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-09-30 | 2010-11-30 | 1324519.45 | 0.000 | IT00200
483 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | IT00203 | The Tohono O'odham Indian Reservation will perform a pavement preservation project along Mission Road Bmp 11.3-13.8 on the Tohono O'odham Nation. | Pavement Improvement | 2011-03-28 | 2011-07-05 | 2011-04-11 | 2011-04-01 | 525000 |  | IT00203
484 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | KNG0202 | The City of Kingman will perform a pavement preservation project along Bank Street Kingman, AZ. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-09-29 | 2010-12-31 | 566339 | 0.500 | KNG0202
485 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | LHV0003 | The Lake Havasu City will construct a shared use pathway along Magnolia Drive to Acoma Boulevard (Multi-Use Path) in Lake Havasu City, AZ. | Transportation Enhancements | 2009-08-11 | 2010-01-04 | 2010-05-04 | 2010-04-30 | 410114.89 | 0.500 | LHV0003
486 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | LHV0200 | The Lake Havasu City will install traffic signals at the intersection of South Palo Verde and Acoma in Lake Havasu City, AZ. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-10-27 | 2010-11-24 | 195406.38 | 0.000 | LHV0200
487 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | LA PAZ |  | 07 | LLA0201 | The LaPaz County will perform a Pavement Preservation project along Salome Road, from US 60 to MP 5.5. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-08-12 | 2010-09-17 | 559644.44 | 5.500 | LLA0201
488 | ARIZONA | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | LPK0201 | The City of Litchfield Park will perform a Pre-Engineer/Design to mill and replace pavement resurfacing/ reconstruction along Various Locations on Functionally Classified Roads in LITCHFIELD PARK. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2011-07-01 | 2011-12-12 | 484233.52 | 0.700 | LPK0201
489 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | MES0021 | The City of Mesa, AZ will construct a Transportation Enhancement along Consolidated Canal Pathway in MESA to include Shared use pathway. | Transportation Enhancements | 2010-07-01 | 2011-02-02 | 2011-06-02 | 2011-06-02 | 646784.81 | 0.000 | MES0021
490 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | MES0206 | The City of Mesa will install fiber, cameras, detection, cabinets, and Controllers for ITS Signal Conversions - Phase 4A . | Safety/Traffic Management | 2011-03-28 |  |  | 2011-08-25 | 549334 |  | MES0206
491 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | MES0209 | The City of Mesa, AZ will perform Design and Construction of Pavement Preservation and Americans with Disabilities Act (ADA) upgrades along Various Roadways. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-07-28 | 2010-07-28 | 1006459 | 7.500 | MES0209
492 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | MES0210 | The City of Mesa, AZ will perform Design and construction of mill and replace pavement along Various Roadways. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-08-27 | 2010-08-27 | 1141765.69 | 3.500 | MES0210
493 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | MES0211 | The City of Mesa proposes a pavement preservation project and American with Disabilities Act upgrades in various locations in Mesa, AZ. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2011-02-03 | 2011-02-03 | 2110670.98 | 2.000 | MES0211
494 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | MES0212 | City of Mesa, AZ proposes a pavement preservation project and upgrades to the American with Disabilities Act features in various locations in Mesa, Arizona. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-07-01 | 2010-07-01 | 1750144.18 | 2.000 | MES0212
495 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | MES0213 | City of Mesa, AZ proposes a pavement preservation project with Americans with Disabilities Act improvements in various locations in Mesa, Arizona. | Pavement Improvement | 2009-08-06 | 2009-08-06 | 2010-09-15 | 2010-11-23 | 3516407 | 3.000 | MES0213
496 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | MM00001 | The Mohave County will construct a shared use pathway along the Mohave Wash Pathway (County) from Gordon Drive to Bank Street in Kingman, AZ. | Transportation Enhancements | 2009-11-20 | 2009-07-01 | 2010-08-17 | 2010-10-19 | 386219.78 | 0.000 | MM00001
497 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | MM00200 | The Mohave County will construct a shared use pathway along Mohave Wash Pathway (County) from Bank Street to Northern Avenue in Kingman, AZ. | Transportation Enhancements | 2009-11-20 | 2009-10-19 | 2010-04-20 | 2010-04-20 | 190744.33 | 0.600 | MM00200
498 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | MOHAVE |  | 02 | MM00203 | The Mohave County will perform a pavement preservation project along Northern Avenue in Kingman, AZ. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-08-22 | 2011-02-16 | 534998 | 1.500 | MM00203
499 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA |  | 05 | MMA0201 | Maricopa County, AZ will construct Paved shoulders and add bike lanes along Bush Highway from Usery Pass Rd to Steward Mountain Rd northwest of MESA AZ. | Other | 2009-10-05 | 2009-10-05 | 2010-01-15 | 2010-01-15 | 552383.84 | 4.600 | MMA0201
500 | ARIZONA | Completed | C250,C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | MMA0210 | Maricopa County, will perform Pre-Engineer/Design and construct Asphalt Rubber Overlay along Various Locations on Functionally Classified Roadways in MARICOPA COUNTY. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2009-12-11 | 2010-12-02 | 6514280 | 31.100 | MMA0210
501 | ARIZONA | Underway | C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | MRN0202 | The City of Marana will perform various pavement preservation projects: Rattlesnake Pass (2.5 miles); Tangerine Road, I-10 to Thornydale Road; Moore Road, I-10 to Sandario Road; Sandario Road, Trico Road to County Line; all in the City of Marana. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-08-09 |  | 2769958 | 7.900 | MRN0202
502 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | MRN0203 | The City of Marana will perform pavement preservation from I-10 (Sandario) to 1580 Linda Lane. | Pavement Improvement | 2011-03-02 | 2011-03-24 | 2011-05-26 | 2011-08-08 | 853100 |  | MRN0203
503 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | NNA0200 | The Navajo County will perform a pavement preservation project along Bourdon Ranch Road from milepost (MP) 6.5 to MP 10.1 in Navajo County. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-09-02 | 2010-08-06 | 492887.01 | 3.500 | NNA0200
504 | ARIZONA | Completed | C250,C240 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PAS0201 | The Pascua Yaqui Tribe will perform a pavement preservation project along Calle Torim and Ignacio. | Pavement Improvement | 2009-07-14 | 2009-07-14 | 2010-07-29 | 2010-09-23 | 397966.59 | 2.600 | PAS0201
505 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | PE00205 | Major Arterial mill, overlay and re-striping to 5 general purpose lanes and bike lanes along Beardsley Rd; Lake Pleasant Rd to 83rd Av in PEORIA. | Pavement Widening | 2009-06-08 | 2009-06-08 | 2010-11-18 | 2010-11-18 | 1822530.75 | 2.400 | PE00205
506 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | PE00206 | The City of Peoria will Widen the Beardsley Rd Connection: SR-101L (Agua Fria Fwy) to Beardsley Rd at 83rd Av/Lake Pleasant Pkwy in PEORIA, which will include Advance constructing the Beardsley Road extension and bridge over New River. | New Construction | 2009-06-08 | 2009-06-08 | 2011-04-15 | 2011-08-19 | 1471776 | 2.000 | PE00206
507 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0209 | The City of Phoenix, AZ will perform Design & Construction of Intersection Improvements along 7th St at McDowell Rd in PHOENIX. | Pavement Widening | 2009-07-01 | 2009-07-01 |  | 2010-06-18 | 99999 | 0.000 | PHX0209
508 | ARIZONA | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0218 | The City of Phoenix will construct a multi use underpass 7Th Ave at the Cads Canal | Transportation Enhancements | 2011-04-04 | 2011-04-04 | 2011-10-31 |  | 900000 |  | PHX0218
509 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0230 | The City of Phoenix, AZ will perform Design & Construction of Removal/Replacement of Existing Americans with Disabilities (ADA) Ramps or Construction of New ADA Ramps along Various Locations in PHOENIX (South Area). | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2010-11-13 | 2010-10-29 | 1163647.94 | 0.000 | PHX0230
510 | ARIZONA | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0231 | The City of Phoenix, AZ will perform Design & Construction of Bridge Deck Rehabilitations along 11 Locations in PHOENIX. | Bridge Improvement | 2009-07-08 | 2009-07-08 | 2010-12-30 |  | 1454566.59 | 0.000 | PHX0231
511 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0232 | The City of Phoenix, AZ will perform Design & Construction of Bridge Joint Rehabilitations along 6 Locations in PHOENIX. | Bridge Improvement | 2009-07-08 | 2009-07-08 | 2010-12-27 | 2010-12-22 | 671822.36 | 0.000 | PHX0232
512 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0233 | The City of Phoenix will design, procure, and install CCTV along various corridors to improve traffic operations and management. | Safety/Traffic Management | 2009-07-08 | 2009-07-08 | 2010-07-14 | 2012-01-12 | 739943.9 | 0.000 | PHX0233
513 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0234 | The City of Phoenix will design, procure and install a fiber optic backbone system along various corridors to improve traffic operations and management. | Safety/Traffic Management | 2009-07-08 | 2009-07-08 | 2010-04-21 | 2011-08-31 | 519714.42 | 0.000 | PHX0234
514 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0235 | The City of Phoenix will design, procure, and install wireless communications devices along various corridors to improve communications facilitating better traffic operations and management. | Safety/Traffic Management | 2009-07-09 | 2009-07-09 | 2010-07-07 | 2012-01-12 | 398208.62 | 0.000 | PHX0235
515 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0236 | The City of Phoenix will perform an inventory, procure, and install traffic control signs along various corridors to aid in the control and management of traffic. | Safety/Traffic Management | 2009-07-09 | 2009-07-09 | 2011-08-26 | 2012-01-26 | 2007167.62 | 0.000 | PHX0236
516 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | PHX0237 | The City of Phoenix will perform a Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (North Area). | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-02-21 | 2011-01-27 | 6798216 | 16.000 | PHX0237
517 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0238 | The City of Phoenix, will perform Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (Central Area). | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-02-21 | 2011-12-27 | 6716919 | 16.000 | PHX0238
518 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0239 | The City of Phoenix, will perform Design & Construction of Pavement Preservation along Various Locations on Functionally Classified Roadways in PHOENIX (South Area). | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2010-12-06 | 2010-09-20 | 6797577 | 16.000 | PHX0239
519 | ARIZONA | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | PHX0261 | Pavement Preservation | Pavement Improvement | 2011-03-07 | 2011-03-07 | 2011-10-03 |  | 6683267 |  | PHX0261
520 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0161 | The Pima County will perform a transportation enhancement project which consists of new paved shoulders, shared use driveway improvements, and access ramps near the Hohokam Middle School in Pima County. | Other | 2010-01-11 | 2010-01-11 | 2011-09-30 | 2010-12-31 | 419146.96 | 1.000 | PPM0161
521 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0214 | The Pima County will perform pavement preservation projects in various locations throughout Pima County. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2011-09-30 | 2010-05-21 | 1224842.51 | 0.000 | PPM0214
522 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0215 | Pima County will complete bridge deck repairs from along Sabino Canyon Rd and Tanque Verde Creek in PIMA COUNTY. | Bridge Improvement | 2009-06-22 | 2009-06-22 | 2011-09-30 | 2010-09-13 | 600000 | 43.000 | PPM0215
523 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0218 | The Pima County will perform pavement preservation projects in the La Canadad Area | Pavement Improvement | 2010-04-08 | 2010-04-08 | 2011-09-30 | 2010-06-18 | 736232 |  | PPM0218
524 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0219 | The Pima County will perform pavement preservation projects in the Flowing Wells Area | Pavement Improvement | 2010-04-23 | 2010-04-23 | 2011-09-30 | 2010-05-19 | 289126.87 |  | PPM0219
525 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0220 | The Pima County will perform Countywide Overlay projects in various locations throughout Pima County. | Pavement Improvement | 2010-11-04 | 2010-11-04 | 2011-09-30 | 2010-11-30 | 1125033.99 | 0.000 | PPM0220
526 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0221 | The Pima County will perform Countywide Microseal projects in various locations throughout Pima County. | Pavement Improvement | 2010-06-28 | 2010-08-01 | 2011-09-30 | 2011-02-14 | 1259744.12 | 0.000 | PPM0221
527 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0222 | The Pima County will perform Countywide Chipseal projects in various locations throughout Pima County. | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2011-09-30 | 2010-06-29 | 521166.35 | 0.000 | PPM0222
528 | ARIZONA | Underway | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | PPM0225 | The City of Tucson will perform a bicycle & pedestrian education progam. & safety enhancements at Pima County Middle Schools. | Other | 2010-11-04 | 2010-11-04 | 2013-01-01 |  | 850000 |  | PPM0225
529 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | PPM0226 | Pima County will Replace/Install video detection, striping, and signal lamps for traffic operations. | Pavement Improvement | 2011-03-31 |  | 2012-01-09 | 2011-09-30 | 1215740.86 |  | PPM0226
530 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | YAVAPAI |  | 01 | PRV0004 | The City of Prescott Valley will perform a Transportation Enhancement project along Bison Lane in PRESCOTT VALLEY to include a shared use pathway. | Other | 2009-08-24 | 2009-08-24 |  | 2009-10-22 | 486218.68 | 0.600 | PRV0004
531 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | YAVAPAI | FLAGSTAFF | 01 | PRV0203 | The City of Prescott Valley will perform a Pavement Preservation along Glassford Hill Road in PRESCOTT VALLEY to include Overlay/ 3" AC. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2009-12-18 | 2010-11-16 | 1574155 | 0.000 | PRV0203
532 | ARIZONA | Completed | C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | PVY0202 | The Town of Paradise Valley, AZ will perform Design and construction of pavement resurfacing along Various Roadways in PARADISE VALLEY. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-11-24 | 2011-03-11 | 823174 | 3.700 | PVY0202
533 | ARIZONA | Completed | C250,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | QCR0205 | The City of Queen Creek, AZ will perform Design and construction of roadway resurfacing and shoulder paving along Various Locations on Rittenhouse Rd in QUEEN CREEK. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2010-09-22 | 2010-09-07 | 896371.06 | 1.700 | QCR0205
534 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | SAH0201 | The Town of Sahuarita will perform a pavement preservation project in Rancho Sahuarita: La Villita to 2 miles north and Traffic signals & signage reflectivity upgrades and Duval Mine Rd: La Canada to west Town limits, w/ pedestrian path improvements. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-08-12 | 2010-10-18 | 1623900.26 | 2.600 | SAH0201
535 | ARIZONA | Underway | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | SAH0202 | The Town of Sahuarita will perform pavement preservation and striping on La Canada Dr. - El Toro Rd And Duval Mine Rd (3 Miles) | Pavement Improvement | 2011-01-03 | 2011-01-19 | 2011-04-20 |  | 1996626.9 |  | SAH0202
536 | ARIZONA | Completed | C220,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | SCT0200 | The City of Scottsdale, AZ will construct a Shared use pathway along Crosscut Canal, from Thomas Rd to Indian School Rd in SCOTTSDALE to include Shared use pathway and pedestrian bridge. | Other | 2009-11-18 | 2010-02-16 | 2010-08-01 | 2011-05-11 | 749942.59 | 0.800 | SCT0200
537 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | SCT0203 | The City of Scottsdale, AZ will construct a Shared use pathway along Arizona Canal (Sun Circle Trail) at Goldwater Blvd in SCOTTSDALE. | Transportation Enhancements | 2009-09-09 | 2009-12-07 | 2010-08-15 | 2011-06-20 | 337622.87 | 0.100 | SCT0203
538 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 04 | SCT0206 | The City of Scottsdale will upgraded traffic controllers and cabinets at various locations in the southern area of Scottsdale to improve traffic operations and management. | Safety/Traffic Management | 2009-08-05 | 2009-08-05 | 2010-12-12 | 2011-02-27 | 476615 | 0.000 | SCT0206
539 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | SCT0209 | The City of Scottsdale, will perform Pavement Preservation along Various Roadways in the City of Scottsdale. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-09-14 | 2011-02-17 | 4600000 | 10.500 | SCT0209
540 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | SCT0212 | The City of Scottsdale will perform pavement preservation at various locations. | Pavement Improvement | 2011-05-16 | 2011-05-17 |  | 2011-09-14 | 831860 |  | SCT0212
541 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | NAVAJO |  | 01 | SLW0201 | The Navajo County will perform a Pavement Preservation along Penrod Road in SHOW LOW. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2010-08-23 | 2010-10-11 | 687362 | 4.100 | SLW0201
542 | ARIZONA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 06 | SRI0200 | The Salt River Pima-Maricopa Indian Community, will Design & Construct Pavement Preservation/Chip-Seal along Various Locations on Functionally Classified Roads within Salt River Pima - Maricopa Indian Community. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2010-07-01 | 2010-12-01 | 653707.08 | 2.000 | SRI0200
543 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | STC0200 | The City of South Tucson will perform a pavement preservation project along 29th Street; from 12th Avenue to the Union Pacific Railroad in SOUTH TUCSON. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-07-12 | 2010-06-28 | 465310.76 | 0.500 | STC0200
544 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | GILA |  | 01 | SUP0200 | The Town of Superior will perform a Pavement Preservation along Main Street. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-05-28 | 2010-08-05 | 457152.04 | 1.000 | SUP0200
545 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | SUR0208 | The City of Surprise will perform a Pre-Engineer/Design and construct pavement Reconstruction and ITS Conduit Installation along Bell Rd; Parkview to West City Limit in SURPRISE. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-10-26 | 2010-10-26 | 2541193.46 | 4.300 | SUR0208
546 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA |  | 08 | SVS0200 | The City of Sierra Vista will complete transportation enhancement along Snyder Boulevard multi-use path, Avenida del Sol to SR-92 in SIERRA VISTA to include pathways, landscaping, and irrigation. | Other | 2009-08-31 | 2009-09-21 | 2010-01-21 | 2010-02-17 | 373990.77 | 0.500 | SVS0200
547 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | COCHISE | PHOENIX, AZ | 08 | SVS0204 | The City of Sierra Vista will perform widening, signal upgrades, drainage, improvements, curb, sidewalk, multi-use pathways on South side along Charleston Road. | Other | 2009-06-11 | 2009-06-11 | 2010-12-26 | 2011-09-15 | 2208506 | 1.200 | SVS0204
548 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | GRAHAM |  | 01 | THR0200 | The Town of Thatcher will perform a 2 inch asphalt overlay along Reay Lane in the Town of Thatcher. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-07-14 | 2010-09-30 | 563647.89 | 2.000 | THR0200
549 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | TMP0202 | The City of Tempe, AZ will construct a Shared Use Pathway along Crosscut Canal from Papago Park to Mouer Park in TEMPE. | Transportation Enhancements | 2010-09-07 | 2010-09-07 | 2011-07-04 | 2011-12-31 | 1698533 | 1.000 | TMP0202
550 | ARIZONA | Completed | C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 02 | TMP0211 | The City of Tempe, AZ will Construct a replacement bridge over the Western Canal along Baseline Rd (Kyrene Rd to Union Pacific Railroad) in TEMPE. | Bridge Replacement | 2009-08-11 | 2009-08-11 | 2010-11-15 | 2011-04-15 | 2136143 | 0.200 | TMP0211
551 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 05 | TMP0216 | The City of Tempe will do milling and fill, ADA ramps, striping, utility adjustments and replacement of signal loops on Broadway Rd. - Mill Ave To Evergreen Rd. | Pavement Improvement | 2011-02-03 | 2011-02-07 | 2011-05-03 | 2011-08-01 | 2087487 |  | TMP0216
552 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0051 | The City of Tucson will install, repair or replace deteriorated sidewalks/driveways along South Fourth Avenue in TUCSON. | Other | 2009-09-14 | 2009-09-14 | 2010-06-08 | 2010-08-15 | 358625 | 0.500 | TUC0051
553 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0067 | The City of Tucson will construct a bicycle & pedestrian enhancement at Tyndall Ave., University Blvd. To 6th St. | Transportation Enhancements | 2011-04-16 | 2011-04-16 |  | 2011-08-10 | 800000 |  | TUC0067
554 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0073 | The City of Tucson will perform a transportation enhancement project along Fourth Avenue between 17th and 22nd Streets in Tucson to include construction of sidewalks and driveways to meet ADA standards. | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-08-27 | 2010-08-13 | 298800 | 0.000 | TUC0073
555 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0215 | The City of Tucson will construct a pedestrian bridge and walkway at Treat Ave., Between Speedway And 22Nd St.. | Transportation Enhancements | 2011-02-07 |  | 2011-05-07 | 2011-05-05 | 295000 |  | TUC0215
556 | ARIZONA | Completed | C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0231 | The City of Tucson will perform pavement preservation projects at various locations within the City of Tucson. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-11-24 | 2011-07-22 | 7376691 | 0.000 | TUC0231
557 | ARIZONA | Completed | C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0232 | The City of Tucson will complete various pavement preservation projects within the City of Tucson. | New Construction | 2009-09-03 | 2009-09-03 | 2010-07-17 | 2010-12-31 | 3482051 | 0.000 | TUC0232
558 | ARIZONA | Completed | C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | PIMA | TUCSON | 08 | TUC0239 | The City of Tucson will replace sign panels, install video detection, and do striping for Traffic Operations. | Pavement Improvement | 2011-10-10 | 2011-12-05 | 2012-01-07 | 2012-01-24 | 2720000 |  | TUC0239
559 | ARIZONA | Underway | C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | 03 | WBG0200 | The Town of Wickenburg, will perform a Pavement Preservation project along North Vulture Mine Rd; from US 60 to Northern Town Limits in WICKENBURG to include Mill and Replace. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2012-05-18 |  | 642619 | 1.600 | WBG0200
560 | ARIZONA | Completed | C250,C200,C230 | Highway Infrastructure Investment Grant | ARIZONA | MARICOPA | PHOENIX, AZ | Multiple | YTN0200 | The Town of Youngtown will perform a Pre-Engineer/Design to construct, mill and replace pavement resurfacing along Peoria Ave; 111th Ave to 115th Av in YOUNGTOWN. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2010-11-09 | 2010-11-09 | 395711 | 0.000 | YTN0200
561 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | YUM0200 | The City of Yuma will perform a Transportation Enhancement project in YUMA to include Construction of an interpretative plaza, complete with retaining walls. | Other | 2009-08-01 | 2010-08-01 | 2011-01-01 | 2010-12-07 | 750000 | 0.200 | YUM0200
562 | ARIZONA | Completed | C220 | Highway Infrastructure Investment Grant | ARIZONA | YUMA |  | 07 | YUM0201 | The City of Yuma will construct a shared-use pathway/linear park at Yuma Main Canal, E. Of 4Th Ave. At Yuma Siphon | Other | 2010-10-25 | 2011-02-22 |  | 2011-12-14 | 750000 |  | YUM0201
563 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | YUMA |  | 07 | YYU0031 | The Yuma County will perform a Bridge Replacement project for Red Top Wash Bridge in Yuma. | Bridge Replacement | 2009-03-03 | 2009-11-19 | 2010-08-16 | 2011-01-25 | 1325000 | 0.000 | YYU0031
564 | ARIZONA | Completed | C200 | Highway Infrastructure Investment Grant | ARIZONA | YUMA | YUMA (CA) | 07 | YYU0200 | The Yuma County will perform a round-about construction project along Avenue E @ Juan Sanchez Blvd within the New San Luis II POE in YUMA COUNTY. | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2010-08-04 | 2010-08-11 | 932000 | 2.000 | YYU0200
565 | ARIZONA | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARIZONA | YAVAPAI |  | 01 | YYV0202 | The Yavapai County will perform a Cold in place recycle; reconstruction along Cornville Rd; from Aspaas Rd to Beaverhead Flat Rd in YAVAPAI COUNTY. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2010-09-14 | 2010-09-13 | 894016 | 3.800 | YYV0202
566 | ARKANSAS | Underway | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LAWRENCE |  | 01 | ARR1001 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT THE EMBANKMENT AND BRIDGES FOR 9.89 MILES OF THE NEW LOCATION OF HIGHWAY 67 BETWEEN HIGHWAY 230 AND HIGHWAY 63, SOUTH OF HOXIE IN LAWRENCE COUNTY. WORK INC | New Construction | 2009-06-22 | 2009-07-15 | 2012-12-31 |  | 21094279 | 19.780 | ARR1001
567 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI |  | 02 | ARR1003 | THE PURPOSE OF THIS PROJECT IS TO REPLACE FOUR EXISTING BRIDGE STRUCTURES, RECONSTRUCT APPROACHES ON I-430 AND CONSTRUCT WIDENING TO THE I-630 LOOP RAMP CONNECTIONS AT THE I-430/I-630 INTERCHANGE IN | Bridge Improvement | 2009-07-17 | 2009-07-20 | 2010-11-15 | 2011-01-19 | 15991380 | 0.000 | ARR1003
568 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | ST FRANCIS |  | 01 | ARR1004 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.30 MILES OF HIGHWAY 1 BETWEEN THE CITIES OF CALDWELL AND COLT IN ST. FRANCIS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-06-15 | 2009-07-07 | 2009-08-21 | 2009-09-10 | 1673191 | 4.300 | ARR1004
569 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PHILLIPS |  | 01 | ARR1005 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.36 MILES OF HIGHWAY 49B BETWEEN HIGHWAY 49 AND HIGHWAY 242 IN THE CITY OF HELENA-WEST HELENA, PHILLIPS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, | Pavement Improvement | 2009-06-03 | 2009-07-02 | 2009-07-15 | 2009-07-15 | 391184 | 1.360 | ARR1005
570 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MONROE |  | 01 | ARR1006 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.45 MILES OF HIGHWAY 49 FROM HIGHWAY 241 NORTH IN THE VICINITY OF THE CITY OF RICH IN MONROE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-22 | 2009-06-19 | 2009-07-09 | 2009-07-09 | 580419 | 2.450 | ARR1006
571 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN |  | 01 | ARR1007 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 9.63 MILES OF HIGHWAY 79 IN CRITTENDEN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-20 | 2009-04-22 | 2009-07-15 | 2009-07-15 | 2139531 | 9.630 | ARR1007
572 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LINCOLN |  | 04 | ARR1008 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.39 MILES OF HIGHWAY 425 NORTH AND SOUTH OF STAR CITY IN LINCOLN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-17 | 2009-05-04 | 2009-07-06 | 2009-07-06 | 1256575 | 5.390 | ARR1008
573 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CHICOT |  | 04 | ARR1010 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.75 MILES OF HIGHWAY 65 BETWEEN THE CITY OF LAKE VILLAGE AND THE CITY OF MCMILLAN CORNER IN CHICOT COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD | Pavement Improvement | 2009-06-03 | 2009-06-30 | 2009-09-14 | 2009-09-24 | 1175182 | 3.730 | ARR1010
574 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | ASHLEY |  | 04 | ARR1011 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 6.09 MILES OF HIGHWAY 82 EAST OF THE CITY OF CROSSETT IN ASHLEY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUTTERS, MAINTENAN | Pavement Improvement | 2009-06-15 | 2009-06-26 | 2009-09-14 | 2009-10-23 | 1863272 | 6.090 | ARR1011
575 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | ARKANSAS |  | 01 | ARR1012 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.11 MILES OF SELECTED SECTIONS OF HIGHWAY 79 BETWEEN HIGHWAY 79C AND HIGHWAY 165 NEAR THE CITY OF STUTTGART IN ARKANSAS COUNTY. WORK INCLUDES PAVEMENT | Pavement Improvement | 2009-04-17 | 2009-05-22 | 2009-07-01 | 2009-07-01 | 682688 | 3.110 | ARR1012
576 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PIKE |  | 04 | ARR1013 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.06 MILES OF HIGHWAY 70 FROM THE CITY OF KIRBY EAST IN PIKE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-22 | 2009-04-30 | 2009-08-10 | 2009-08-07 | 1020068 | 3.060 | ARR1013
577 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | NEVADA |  | 04 | ARR1014 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.02 MILES OF HIGHWAY 67 FROM THE CITY OF PRESCOTT SOUTH IN NEVADA COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUTTERS, MAINTE | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2009-09-14 | 2009-09-21 | 953699 | 3.020 | ARR1014
578 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD |  | 04 | ARR1015 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.67 MILES OF HIGHWAY 278 BETWEEN HAZEL STREET AND GREENWOOD STREET IN THE CITY OF HOPE, HEMPSTEAD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD M | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-09-14 | 2009-09-09 | 335086 | 1.670 | ARR1015
579 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LITTLE RIVER |  | 04 | ARR1016 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.41 MILES OF HIGHWAY 71 BETWEEN THE CITIES OF ASHDOWN AND WILTON IN LITTLE RIVER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENAN | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-07-24 | 2009-07-24 | 833726 | 3.410 | ARR1016
580 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SEVIER |  | 04 | ARR1017 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.01 MILES OF HIGHWAY 70 FROM THE CITY OF DEQUEEN WEST IN SEVIER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-08-20 | 2009-08-06 | 368943 | 1.010 | ARR1017
581 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LAFAYETTE |  | 04 | ARR1018 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.08 MILES OF HIGHWAY 82 EAST AND WEST OF THE RED RIVER IN MILLER AND LAFAYETTE COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH | Pavement Improvement | 2009-04-27 | 2009-05-21 | 2009-08-10 | 2009-08-07 | 607701 | 4.160 | ARR1018
582 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD |  | 04 | ARR1019 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.45 MILES OF HIGHWAY 278 FROM THE CITY OF OZAN WEST IN HEMPSTEAD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-06-08 | 2009-08-18 | 2009-09-14 | 2009-09-04 | 885084 | 5.450 | ARR1019
583 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WASHINGTON |  | 03 | ARR1020 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.78 MILES OF HIGHWAY 412 BETWEEN HIGHWAY 112 AND INTERSTATE 540 IN THE CITY OF SPRINGDALE, WASHINGTON COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, CO | Pavement Improvement | 2009-04-23 | 2009-05-26 | 2009-07-08 | 2009-07-08 | 570814 | 1.780 | ARR1020
584 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FRANKLIN |  | 03 | ARR1021 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.09 MILES OF HIGHWAY 22 FROM CHARLESTON EAST IN FRANKLIN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROSION CONTROL ITEMS, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-06-15 | 2009-07-27 | 2009-09-14 | 2009-09-11 | 684500 | 3.090 | ARR1021
585 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LOGAN |  | 04 | ARR1022 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.77 MILES OF HIGHWAY 22 BETWEEN THE CITIES OF SUBIACO AND MIDWAY IN LOGAN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF T | Pavement Improvement | 2009-04-17 | 2009-04-23 | 2009-05-28 | 2009-05-28 | 691491 | 2.770 | ARR1022
586 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SHARP |  | 01 | ARR1023 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.47 MILES OF HIGHWAY 71 SOUTH OF THE CITY OF WALDRON IN SCOTT COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROS | Pavement Improvement | 2009-06-15 | 2009-07-07 | 2009-08-07 | 2009-08-19 | 805350 | 3.470 | ARR1023
587 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN |  | 03 | ARR1024 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.74 MILES OF HIGHWAY 22 FROM INTERSTATE 540 EAST IN THE CITY OF FORT SMITH, SEBASTIAN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAIN | Pavement Improvement | 2009-06-08 | 2009-07-31 | 2009-09-07 | 2009-09-20 | 1021316 | 2.740 | ARR1024
588 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | POLK |  | 04 | ARR1025 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.65 MILES OF HIGHWAY 71 SOUTH AND NORTH OF HIGHWAY 8 IN THE CITY OF MENA, POLK COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE | Pavement Improvement | 2009-04-27 | 2009-05-29 | 2009-06-24 | 2009-06-24 | 581777 | 1.650 | ARR1025
589 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRAWFORD |  | 03 | ARR1026 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.00 MILES OF HIGHWAY 64 FROM ALMA EAST IN CRAWFORD COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, EROSION CONTROL ITEMS, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2009-07-24 | 2009-07-24 | 524121 | 2.000 | ARR1026
590 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR1027 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.67 MILES OF HIGHWAY 167 NORTH OF THE CITY OF BALD KNOB IN WHITE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-06-08 | 2009-07-27 | 2009-09-01 | 2009-09-02 | 1132854 | 3.670 | ARR1027
591 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | STONE |  | 01 | ARR1028 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.57 MILES OF HIGHWAY 14 EAST OF THE CITY OF MOUNTAIN HOME IN STONE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-17 | 2009-05-04 | 2009-05-19 | 2009-05-19 | 438853 | 1.570 | ARR1028
592 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR1029 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.88 MILES OF HIGHWAY 167 FROM THE JACKSON COUNTY LINE NORTH IN WHITE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-06-08 | 2009-07-09 | 2009-09-14 | 2009-08-29 | 862415 | 2.830 | ARR1029
593 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE, INDEPENDENCE |  | Multiple | ARR1030 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.64 MILES OF HIGHWAY 167 FROM THE CITY OF PLEASANT PLAINS SOUTH IN INDEPENDENCE AND WHITE COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING | Pavement Improvement | 2009-04-17 | 2009-05-28 | 2009-06-01 | 2009-06-26 | 862046 | 4.780 | ARR1030
594 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CLEBURNE |  | 01 | ARR1031 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.66 MILES OF HIGHWAY 25 FROM GREERS FERRY DAM SOUTH IN THE VICINITY OF THE CITY OF HEBER SPRINGS IN CLEBURNE COUNTY. WORK INCLUDES PAVEMENT REHABILITAT | Pavement Improvement | 2009-04-22 | 2009-07-15 | 2009-08-10 | 2009-08-21 | 648533 | 2.660 | ARR1031
595 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | INDEPENDENCE |  | 01 | ARR1032 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.14 MILES OF HIGHWAY 69 FROM THE BLACK RIVER WEST IN INDEPENDENCE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-06-03 | 2009-07-06 | 2009-09-14 | 2009-09-28 | 245794 | 1.140 | ARR1032
596 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI |  | 02 | ARR1033 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.10 MILES OF INTERSTATE 40 BETWEEN INTERSTATE 30 AND HIGHWAY 67 IN THE CITY OF NORTH LITTLE ROCK, PULASKI COUNTY. WORK INCLUDES CONCRETE PAVEMENT PATCH | Pavement Improvement | 2009-08-04 | 2009-08-17 | 2009-11-13 | 2010-06-08 | 1892346 | 1.100 | ARR1033
597 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LONOKE |  | 01 | ARR1034 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.80 MILES OF HIGHWAY 70 FROM THE PULASKI COUNTY LINE EAST IN LONOKE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, TRENCHING AND SHOULDER PREPARATION, | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2009-06-30 | 2009-06-30 | 467972 | 2.800 | ARR1034
598 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | HOT SPRING |  | 04 | ARR1035 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.20 MILES OF HIGHWAY 67 FROM THE CITY OF GLEN ROSE SOUTH IN HOT SPRING COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, TRENCHING AND SHOULDER PREPARATIO | Pavement Improvement | 2009-04-17 | 2009-05-05 | 2009-06-17 | 2009-06-17 | 264789 | 1.200 | ARR1035
599 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PRAIRIE |  | 01 | ARR1036 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.40 MILES OF HIGHWAY 70 BETWEEN HAZEN AND DEVALLS BLUFF IN PRAIRIE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-22 | 2009-04-22 | 2009-06-17 | 2009-06-17 | 993892 | 5.400 | ARR1036
600 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LONOKE, PULASKI |  | Multiple | ARR1037 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.25 MILES OF HIGHWAY 165 BETWEEN THE CITIES OF NORTH LITTLE ROCK AND SCOTT IN LONOKE AND PULASKI COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD | Pavement Improvement | 2009-06-01 | 2009-06-08 | 2009-09-14 | 2009-09-11 | 1181822 | 11.250 | ARR1037
601 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | OUACHITA |  | 04 | ARR1038 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.60 MILES OF HIGHWAY 79 BETWEEN THE CITIES OF CAMDEN AND EAST CAMDEN IN OUACHITA COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH | Pavement Improvement | 2009-06-03 | 2009-06-22 | 2009-09-14 | 2009-08-26 | 1294334 | 2.600 | ARR1038
602 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | DALLAS |  | 04 | ARR1039 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.61 MILES OF HIGHWAY 79 IN DALLAS COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-17 | 2009-05-07 | 2009-06-24 | 2009-06-24 | 1124559 | 3.610 | ARR1039
603 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CLEVELAND |  | 04 | ARR1040 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 9.50 MILES OF HIGHWAY 79 BETWEEN THE CITIES OF KINGLAND AND RISON IN CLEVELAND COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GUT | Pavement Improvement | 2009-06-03 | 2009-06-11 | 2009-08-21 | 2009-08-20 | 1354932 | 9.500 | ARR1040
604 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CALHOUN |  | 04 | ARR1041 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.12 MILES OF HIGHWAY 167 FROM THE CITY OF HAMPTON SOUTH IN CALHOUN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-17 | 2009-05-05 | 2009-06-09 | 2009-06-09 | 1026517 | 4.120 | ARR1041
605 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | VAN BUREN |  | 02 | ARR1042 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.87 MILES OF HIGHWAY 65 NORTH OF THE CITY OF CLINTON IN VAN BUREN COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-06-08 | 2009-08-10 | 2009-09-14 | 2009-10-16 | 1725247 | 5.870 | ARR1042
606 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR1043 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.68 MILES OF HIGHWAY 65 NORTH AND SOUTH OF HIGHWAY 25 IN THE CITY OF GREENBRIER, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 2009-04-22 | 2009-07-02 | 2009-08-03 | 2009-08-03 | 778244 | 2.680 | ARR1043
607 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | YELL |  | 02 | ARR1044 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.90 MILES OF HIGHWAY 10 EAST AND WEST OF THE CITY OF MICKLES IN YELL COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-17 | 2009-04-27 | 2009-07-07 | 2009-07-07 | 1092148 | 5.900 | ARR1044
608 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | POPE |  | 03 | ARR1045 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.64 MILES OF HIGHWAY 7 BETWEEN J STREET AND HIGHWAY 326 IN THE CITY OF RUSSELLVILLE, POPE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 2009-06-04 | 2009-09-04 | 2009-09-14 | 2009-10-01 | 467277 | 1.640 | ARR1045
609 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR1046 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 0.37 MILE OF HIGHWAY 65 BETWEEN THE INTERSTATE 40 OFF AND ON RAMPS IN THE CITY OF CONWAY, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD M | Pavement Improvement | 2009-04-22 | 2009-07-02 | 2009-08-05 | 2009-08-04 | 182026 | 0.740 | ARR1046
610 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR1047 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE HIGHWAY 412 FROM HIGHWAY 59 IN THE CITY OF SILOAM SPRINGS TO THE EAST 5.45 MILES IN BENTON COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 2009-06-01 | 2009-06-22 | 2009-08-27 | 2009-08-24 | 2030641 | 5.450 | ARR1047
611 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | BOONE |  | 03 | ARR1048 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.40 MILES OF HIGHWAY 65 FROM THE MISSOURI STATE LINE SOUTH IN BOONE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-04-22 | 2009-05-04 | 2009-07-28 | 2009-07-28 | 2871797 | 7.400 | ARR1048
612 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | GREENE |  | 01 | ARR1052 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.79 MILES OF HIGHWAY 412 BETWEEN REYNOLDS ROAD AND HIGHWAY 49B IN THE CITY OF PARAGOULD, GREENE COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MIL | Pavement Improvement | 2009-06-08 | 2009-08-19 | 2009-09-14 | 2009-09-12 | 770949 | 1.790 | ARR1052
613 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MISSISSIPPI |  | 01 | ARR1053 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 0.84 MILE OF HIGHWAY 18 FROM INTERSTATE 55 WEST IN THE CITY OF BLYTHEVILLE, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAI | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-05-28 | 2009-05-28 | 348065 | 0.840 | ARR1053
614 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CLAY |  | 01 | ARR1054 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4.10 MILES OF HIGHWAY 67 BETWEEN HIGHWAY 328 NORTH OF CORNING AND THE MISSOURI STATE LINE IN CLAY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MI | Pavement Improvement | 2009-06-08 | 2009-07-15 | 2009-09-14 | 2009-09-12 | 1098919 | 4.100 | ARR1054
615 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MISSISSIPPI |  | 01 | ARR1055 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.10 MILES OF HIGHWAY 140 WEST AND EAST OF HIGHWAY 119Y IN THE CITY OF OSCEOLA, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, | Pavement Improvement | 2009-04-27 | 2009-05-15 | 2009-06-09 | 2009-06-09 | 452888 | 1.100 | ARR1055
616 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LAWRENCE |  | 01 | ARR1056 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE A 0.26 MILE SECTION OF HIGHWAY 412 BETWEEN HIGHWAY 67B NORTH AND HIGHWAY 67B SOUTH IN THE CITY OF WALNUT RIDGE, LAWRENCE COUNTY. WORK INCLUDES PAVEMENT | Pavement Improvement | 2009-06-01 | 2009-08-11 | 2009-09-14 | 2009-09-21 | 125418 | 0.250 | ARR1056
617 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | RANDOLPH |  | 01 | ARR1057 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.05 MILES OF HIGHWAY 67 FROM HIGHWAY 90 NORTH IN THE THE CITY OF POCAHONTAS, RANDOLPH COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAIN | Pavement Improvement | 2009-04-17 | 2009-05-14 | 2009-08-03 | 2009-08-03 | 174441 | 1.050 | ARR1057
618 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | POINSETT |  | 01 | ARR1058 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.14 MILES OF HIGHWAY 63 FROM THE CRAIGHEAD COUNTY LINE TO HIGHWAY 69 WEST OF THE CITY OF TRUMANN IN POINSETT COUNTY. WORK INCLUDES PAVEMENT REHABILITAT | Pavement Improvement | 2009-06-01 | 2009-06-04 | 2009-09-14 | 2009-08-14 | 673482 | 2.140 | ARR1058
619 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRAIGHEAD |  | 01 | ARR1059 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.59 MILES OF HIGHWAY 63 BETWEEN HIGHWAY 91 AND HIGHWAY 226 IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK INCLUDES CONCRETE PAVEMENT GRINDING AND P | Pavement Improvement | 2009-05-08 | 2009-07-06 | 2009-10-30 | 2009-12-15 | 1182066 | 3.590 | ARR1059
620 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | GARLAND |  | 04 | ARR1060 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 0.37 MILE OF HIGHWAY 128 FROM SHADY GROVE ROAD TO NORTH OF HIGHWAY 270 IN THE CITY OF HOT SPRINGS, GARLAND COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADW | Pavement Widening | 2009-09-23 | 2009-10-21 | 2010-06-25 | 2010-06-24 | 1583907 | 0.370 | ARR1060
621 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | GRANT |  | 04 | ARR1061 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.1 MILES OF HIGHWAY 167 BETWEEN NORTH MILLERVILLE AND THE SHERIDAN BYPASS IN GRANT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN | Pavement Widening | 2009-09-18 | 2009-09-24 | 2011-07-22 | 2010-12-16 | 8819100 | 4.080 | ARR1061
622 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN |  | 03 | ARR1063 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT FOUR MAIN LANE BRIDGES AS PART OF THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49) BETWEEN TAYLOR AVENUE AND HIGHWAY 22 NEAR FT. CHAFFEE IN SEBASTIAN C | New Bridge Construction | 2009-07-06 | 2009-07-09 | 2010-12-30 | 2011-04-19 | 11693084 | 0.660 | ARR1063
623 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN |  | 03 | ARR1064 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 2.69 MILES OF GRADING AND STRUCTURES OF THE NEW LOCATION HIGHWAY 71 BETWEEN CO ROAD 8 AND CUSTER BLVD. NEAR FORT CHAFFEE IN SEBASTIAN COUNTY. WORK WILL INC | New Construction | 2009-10-16 | 2009-10-15 | 2011-09-30 | 2012-03-15 | 10730011 | 5.380 | ARR1064
624 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MILLER |  | 04 | ARR1065 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 1.77 MILES OF EMBANKMENT AND MINOR DRAINAGE STRUCTURES FOR THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49) BETWEEN COUNTY ROAD 2 AND DODDRIDGE, SOUTH | New Construction | 2009-08-21 | 2009-09-03 | 2011-06-25 | 2012-04-17 | 6685747 | 1.770 | ARR1065
625 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRAIGHEAD |  | 01 | ARR1066 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 141 AND PARKER ROAD IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT AND PAVEMENT MARKINGS. | Safety/Traffic Management | 2009-06-08 | 2009-10-20 | 2009-12-18 | 2009-12-17 | 83737 | 0.000 | ARR1066
626 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | ARKANSAS |  | 01 | ARR1067 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT APPROXIMATELY 1.30 MILES OF COUNTY ROADS 33 AND 43 NEAR THE CITY OF ALMYRA IN ARKANSAS COUNTY. WORK WILL INCLUDE RECONSTRUCTING THE EXISTING ROADWAY, PAVEMENT MARKINGS AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2009-06-15 | 2009-06-26 | 2009-08-14 | 2009-09-01 | 156690 | 1.260 | ARR1067
627 | ARKANSAS | Underway | C220 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN |  | 01 | ARR1068 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A WELCOME CENTER AT THE COMMON SECTION OF INTERSTATE 55 AND INTERSTATE 40 IN WEST MEMPHIS, CRITTENDEN COUNTY. WORK ITEMS INCLUDE EARTHWORK, A WELCOME CENTER FACILITY, LANDSCAPING, AND MISCELLANEOUS ITEMS. | Transportation Enhancements | 2010-04-07 | 2010-05-11 | 2012-07-01 |  | 3830174 | 0.000 | ARR1068
628 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2001 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 67B, HIGHWAY 31 AND HIGHWAY 367 INTERSECTION IN THE CITY OF BEEBE IN WHITE COUNTY. WORK ITEMS INCLUDE TRAFFIC S | Safety/Traffic Management | 2010-02-11 | 2010-04-21 | 2010-05-20 | 2010-08-18 | 76337 | 0.000 | ARR2001
629 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | VAN BUREN |  | 02 | ARR2002 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 65 AND HIGHWAY 16 EAST IN THE CITY OF CLINTON IN VAN BUREN COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT, CONCRETE WORK AND PAVEMENT MARKINGS. | Safety/Traffic Management | 2010-03-25 | 2010-05-06 | 2010-10-08 | 2010-09-29 | 62720 | 0.000 | ARR2002
630 | ARKANSAS | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2003 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A 2-LANE ROUNDABOUT ON PIKE AVENUE IN NORTH LITTLE ROCK, PULASKI COUNTY. THE WORK WILL ALSO INCLUDE CURBS, GUTTERS, SIDEWALKS, DRAINAGE, LANDSCAPING AND ELECTRICAL ITEMS. | Pavement Widening | 2010-01-11 | 2010-01-11 | 2010-10-08 | 2011-01-24 | 1489935 | 0.170 | ARR2003
631 | ARKANSAS | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN | MEMPHIS (TN-MS) | 01 | ARR2004 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND UPGRADE THE PAVEMENT TO CONCRETE WITH NEW CURBS ON GLEN BAILEY DRIVE BETWEEN HIGHWAY 77 AND HIGHWAY 191 IN THE CITY OF WEST MEMPHIS, CRITTENDEN COUNTY | Pavement Improvement | 2010-05-20 | 2010-06-14 | 2010-11-30 | 2010-11-15 | 1300000 | 0.620 | ARR2004
632 | ARKANSAS | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN | MEMPHIS (TN-MS) | 01 | ARR2005 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AN ADDITIONAL LANE TO L.H. POLK DRIVE IN THE CITY OF MARION, CRITTENDEN COUNTY. THIS LANE WILL BE APPROXIMATELY 1,000 FEET LONG AND 12 FEET WIDE TO REMOVE | Pavement Improvement | 2010-07-02 | 2010-07-14 | 2010-09-05 | 2010-09-30 | 197529 | 0.190 | ARR2005
633 | ARKANSAS | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI |  | 02 | ARR2006 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT TWO CONCRETE. BOX CULVERTS AND APPROACHES ON 0.360 MILE OF COUNTY ROAD 67 IN THE VICINITY OF SHERWOOD IN PULASKI COUNTY. WORK INCLUDES CLEARING AND GRUBBI | Bridge Replacement | 2009-09-17 | 2009-09-17 | 2010-09-01 | 2011-03-03 | 770372 | 0.360 | ARR2006
634 | ARKANSAS | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2008 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A BRIDGE AND APPROACHES ON APPROXIMATELY 0.47 MILE OF COUNTY ROAD 9 NEAR SILOAM SPRINGS IN BENTON COUNTY. WORK WILL INCLUDE CLEARING, GRADING, DRAINAGE IMP | Bridge Replacement | 2009-11-20 | 2010-02-03 | 2011-05-14 | 2011-03-28 | 1319151 | 0.460 | ARR2008
635 | ARKANSAS | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | BRADLEY |  | 04 | ARR2009 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT ONE CONCRETE BOX CULVERT AND APPROACHES ON 0.80 MILE OF COUNTY ROAD 2 IN THE VICINITY OF HERMITAGE IN BRADLEY COUNTY. WORK INCLUDES CLEARING AND GRUBBING, | Pavement Improvement | 2009-08-12 | 2009-08-20 | 2009-12-18 | 2010-07-23 | 319946 | 1.600 | ARR2009
636 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | RANDOLPH |  | 01 | ARR2010 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT ONE BRIDGE LENGTH STRUCTURE AND APPROACHES ON 0.492 MILE OF COUNTY ROAD 48 NEAR POCAHONTAS IN RANDOLPH COUNTY. WORK INCLUDES GRADING, DRAINAGE IMPROVEMENTS, | Bridge Replacement | 2009-06-22 | 2009-07-09 | 2010-12-22 | 2010-12-21 | 1693838 | 0.490 | ARR2010
637 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CLARK |  | 04 | ARR2011 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT TWO BRIDGE LENGTH STRUCTURES AND APPROACHES ON 0.72 MILE OF COUNTY ROAD 38 NEAR ASH FLAT IN SHARP COUNTY. WORK WILL INCLUDE EARTHWORK, DRAINAGE IMPROVEMENT | Pavement Improvement | 2009-07-14 | 2009-07-16 | 2010-12-22 | 2010-12-22 | 985359 | 0.720 | ARR2011
638 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | ST FRANCIS |  | 01 | ARR2012 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 1 AND HIGHWAY 306 IN THE CITY OF COLT IN ST. FRANCIS COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT, CONCRETE WORK AND PAVEMENT MARKINGS. | Safety/Traffic Management | 2009-11-06 | 2009-11-30 | 2010-07-23 | 2010-07-30 | 127341 | 0.000 | ARR2012
639 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | WASHINGTON |  | 03 | ARR2013 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 16 AND HIGHWAY 74 IN THE CITY OF ELKINS IN WASHINGTON COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT AND PAVEMENT MARKINGS. | Safety/Traffic Management | 2009-11-06 | 2010-02-17 | 2010-05-17 | 2010-05-17 | 65247 | 0.000 | ARR2013
640 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLARK |  | 04 | ARR2014 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL THREE TRAFFIC SIGNALS ON HIGHWAY 67 AT THE INTERSECTIONS OF HENDERSON STREET, HIGHWAY 51 WEST/PINE STREET AND HIGHWAY 51 EAST/CADDO STREET IN TH | Safety/Traffic Management | 2009-11-13 | 2010-01-15 | 2010-07-30 | 2010-07-29 | 203370 | 0.000 | ARR2014
641 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2016 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 64, ROOSTER ROAD AND LOWER RIDGE ROAD NEAR THE CITY OF CONWAY IN FAULKNER COUNTY. WORK ITEMS IN | Pavement Improvement | 2009-08-19 | 2009-09-14 | 2010-02-05 | 2010-02-03 | 76248 | 0.000 | ARR2016
642 | ARKANSAS | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | SALINE | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2017 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND WIDEN 1.4 MILES OF MILITARY ROAD FROM INTERSTATE 30 TO CONGO ROAD IN THE CITY OF BENTON, SALINE COUNTY. WORK WILL INCLUDE WIDENING TO A FOUR-LANE DIV | Other | 2009-08-12 | 2009-08-12 | 2011-01-14 | 2011-03-03 | 5519716 | 1.410 | ARR2017
643 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD |  | 04 | ARR2018 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 278, HIGHWAY 29 AND SHOVER ROAD IN THE CITY OF HOPE IN HEMPSTEAD COUNTY. WORK ITEMS INCLUDE TRA | Transportation Enhancements | 2009-12-31 | 2010-06-02 | 2010-07-09 | 2010-07-16 | 113093 | 0.000 | ARR2018
644 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | HOWARD |  | 04 | ARR2019 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND INSTALL TRAFFIC SIGNALS ON HIGHWAY 371 AT THE INTERSECTIONS OF HIGHWAY 27/HIGHWAY 278 AND HIGHWAY 980/MAIN STREET IN THE CITY OF NASHVILLE, HOWARD COU | Safety/Traffic Management | 2010-01-14 | 2010-03-29 | 2010-07-09 | 2010-07-02 | 207191 | 0.000 | ARR2019
645 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | INDEPENDENCE |  | 01 | ARR2021 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE THE TRAFFIC SIGNALS ON HIGHWAY 167 AT THE INTERSECTIONS OF SOUTHERLAND DRIVE, MYERS AVENUE, LAWRENCE STREET, VIRGINIA DRIVE AND COLLEGE AVENUE IN THE CIT | Safety/Traffic Management | 2010-05-26 | 2010-08-05 | 2010-11-12 | 2010-11-01 | 220822 | 0.000 | ARR2021
646 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2022 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 16 AND HOLMES ROAD INTERSECTION IN THE CITY OF SEARCY IN WHITE COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPM | Safety/Traffic Management | 2010-02-18 | 2010-04-09 | 2010-05-20 | 2010-12-03 | 94063 | 0.000 | ARR2022
647 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLEBURNE |  | 01 | ARR2023 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 25/124 INTERSECTION IN THE CITY OF QUITMAN IN CLEBURNE COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT, REM | Safety/Traffic Management | 2010-04-14 | 2010-08-03 | 2010-11-12 | 2010-11-17 | 165163 | 0.000 | ARR2023
648 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLARK |  | 04 | ARR2025 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF INTERSTATE 30 AND HIGHWAY 7 IN THE CITY OF CADDO VALLEY IN CLARK COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT, CONCRETE WORK AND PAVEMENT MARKINGS. | Safety/Traffic Management | 2010-02-11 | 2010-06-29 | 2010-08-20 | 2010-08-20 | 117523 | 0.000 | ARR2025
649 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | HOT SPRING |  | 04 | ARR2027 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE TRAFFIC SIGNALS AT THE INTERSECTIONS OF HIGHWAY 270B/3RD STREET, HIGHWAY 270B/HIGHWAY 67, HIGHWAY 67/ASH STREET AND HIGHWAY 9/5TH STREET IN THE CITY OF M | Safety/Traffic Management | 2010-04-27 | 2010-07-14 | 2010-11-12 | 2010-11-10 | 288770 | 0.000 | ARR2027
650 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2029 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 100 AND VESTAL BLVD. INTERSECTION IN THE CITY OF NORTH LITTLE ROCK IN PULASKI COUNTY. WORK ITEMS INCLUDE TRAFFI | Safety/Traffic Management | 2010-02-19 | 2010-07-12 | 2010-08-20 | 2010-08-31 | 101867 | 0.000 | ARR2029
651 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2030 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 279, HIGHWAY 340 AND HIGHLANDS BLVD. IN THE CITY OF BELLA VISTA IN BENTON COUNTY. WORK ITEMS I | Safety/Traffic Management | 2010-03-05 | 2010-05-17 | 2010-08-20 | 2010-08-18 | 89105 | 0.000 | ARR2030
652 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | LINCOLN, DESHA |  | 04 | ARR2031 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 5.39 MILES OF HIGHWAY 65 NORTH AND SOUTH OF THE CITY OF GOULD IN LINCOLN AND DESHA COUNTIES. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, DRAINAGE IMPROVEM | Pavement Widening | 2009-09-18 | 2009-12-03 | 2012-10-05 | 2012-06-19 | 15776865 | 5.390 | ARR2031
653 | ARKANSAS | Completed | C220 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN | MEMPHIS (TN-MS) | 01 | ARR2032 | THE PURPOSE OF THIS PROJECT IS TO RELOCATE RAMPS AND CONNECTOR ROUTES TO PROVIDE ACCESS TO THE NEW WELCOME CENTER LOCATED IN THE COMMON AREA OF INTERSTATE 55 AND INTERSTATE 40 IN THE CITY OF WEST MEMPHIS, CRITTENDEN COUNTY. | Transportation Enhancements | 2010-05-26 | 2010-06-16 | 2011-06-03 | 2011-08-12 | 6716160 | 0.100 | ARR2032
654 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | JEFFERSON |  | 04 | ARR2033 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL THREE TRAFFIC SIGNALS ON HIGHWAY 65B AT THE INTERSECTIONS OF CHERRY STREET, HIGHWAYS 79B/365, AND HIGHWAY 79B/UNIVERSITY DRIVE IN THE CITY OF PI | Safety/Traffic Management | 2010-02-18 | 2010-03-25 | 2010-08-20 | 2010-10-12 | 333713 | 0.000 | ARR2033
655 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN |  | 03 | ARR2036 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 3.02 MILES OF HIGHWAY 22 BETWEEN HIGHWAY 255 AND HIGHWAY 96 IN THE VICINITY OF CENTRAL CITY, SEBASTIAN COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, | Pavement Widening | 2010-06-03 | 2010-06-03 | 2011-11-23 | 2012-01-13 | 12021297 | 3.020 | ARR2036
656 | ARKANSAS | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | POLK |  | 04 | ARR2037 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 1.40 MILES OF A NORTHBOUND PASSING LANE ON HIGHWAY 71 BETWEEN COUNTY ROAD 16 AND HIGHWAY 246 NEAR VANDERVOORT IN POLK COUNTY. WORK WILL INCLUDE PASSING LAN | Pavement Widening | 2010-02-23 | 2010-03-01 | 2011-04-30 | 2011-09-27 | 2015265 | 1.400 | ARR2037
657 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | SEBASTIAN | FORT SMITH (OK) | 03 | ARR2039 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AND PROVIDE OPERATIONAL IMPROVEMENTS AT THE INTERSECTION OF HIGHWAY 271 AND HARVARD AVENUE IN THE CITY OF FT. SMITH IN SEBASTIA | Pavement Improvement | 2010-03-05 | 2010-03-31 | 2010-08-18 | 2010-07-21 | 191963 | 0.160 | ARR2039
658 | ARKANSAS | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2041 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A NORTHBOUND AND A SOUTHBOUND PASSING LANE FOR A DISTANCE OF 2.40 MILES ON HWY . 16, BETWEEN THE CITIES OF PANGBURN AND SEARCY IN WHITE COUNTY. WORK WILL A | Pavement Widening | 2010-04-07 | 2010-04-28 | 2011-05-30 | 2011-08-04 | 3294666 | 2.400 | ARR2041
659 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | UNION |  | 04 | ARR2043 | THE PURPOSE OF THIS PROJECT IS TO PROVIDE 3.22 MILES OF BASE AND SURFACING TO COMPLETE WIDENING HIGHWAY 167 BETWEEN CHAMPAGNOLLE ROAD AND HIGHWAY 7 SOUTH IN THE CITY OF EL DORADO, UNION COUNTY. WORK | New Construction | 2009-11-09 | 2009-12-04 | 2011-07-22 | 2011-08-04 | 552587 | 3.220 | ARR2043
660 | ARKANSAS | Completed | C250,C200 | Highway Infrastructure Investment Grant | ARKANSAS | POPE |  | 03 | ARR2044 | THE PURPOSE OF THIS PROJECT IS TO WIDEN HIGHWAY 247 FROM HIGHWAY 7 EAST 5.26 MILES IN THE VICINITY OF POTTSVILLE, POPE COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN 11' CE | Pavement Widening | 2010-07-07 | 2010-07-07 | 2012-05-04 | 2012-05-05 | 15252775 | 5.260 | ARR2044
661 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2045 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A 10.10 MILE HIGHWAY 64 BYPASS OF THE CITY OF VILONIA IN FAULKNER COUNTY. WORK INCLUDES BASE, PAVING , EROSION CONTROL, PAVEMENT MARKINGS AND MISCELLANEOUS ITEMS FOR A 4-LANE DIVIDED FACILITY ON NEW LOCATION. | New Construction | 2010-04-28 | 2010-06-02 | 2011-12-15 | 2012-05-14 | 23931157 | 10.100 | ARR2045
662 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2046 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AND PROVIDE INTERSECTION IMPROVEMENTS AT THE INTERSECTION OF HIGHWAY 112 AND HIGHWAY 264 EAST IN THE CITY OF CAVE SPRINGS IN BE | Pavement Widening | 2010-03-09 | 2010-08-30 | 2011-06-17 | 2011-10-07 | 684470 | 0.000 | ARR2046
663 | ARKANSAS | Underway | C200 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2047 | THE PURPOSE OF THIS PROJECT IS TO RELOCATE THE UTILITIES TO PREPARE FOR THE FUTURE CONSTRUCTION ON NEW LOCATION OF THE 4-LANE DIVIDED BELLA VISTA BYPASS, BENTON COUNTY. | Other | 2010-09-08 | 2010-09-08 | 2011-09-03 |  | 3000000 | 0.000 | ARR2047
664 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | BENTON |  | 03 | ARR2048 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 1.61 MILES OF HIGHWAY 412 BETWEEN THE OKLAHOMA STATE LINE AND WASHINGTON STREET IN SILOAM SPRINGS, BENTON COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADW | Pavement Widening | 2010-01-14 | 2010-02-10 | 2012-11-20 | 2012-10-17 | 7070251 | 1.600 | ARR2048
665 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CRAIGHEAD |  | 01 | ARR2049 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 3.55 MILES OF HIGHWAY 226 FROM THE NEW LOCATION OF HIGHWAY 67 TO WEST OF CASH IN CRAIGHEAD COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, FOUR BRIDG | Pavement Widening | 2010-04-16 | 2010-05-04 | 2012-08-31 | 2012-10-03 | 13764995 | 7.560 | ARR2049
666 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WASHINGTON, BENTON |  | 03 | ARR2050 | THE PURPOSE OF THIS PROJECT IS TO WIDEN RAMPS AND ADD AUXILIARY LANES AT FOUR INTERCHANGES IN BENTON AND WASHINGTON COUNTIES. IMPROVEMENTS AT A FIFTH INTERCHANGE (PORTER RD.) IN WASHINGTON COUNTY INV | Pavement Widening | 2009-09-29 | 2009-10-12 | 2010-10-01 | 2010-10-01 | 2013305 | 0.000 | ARR2050
667 | ARKANSAS | Completed | C230 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2052 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT A RAILROAD OVERPASS BRIDGE WITH APPROACH EMBANKMENTS ON SALEM ROAD IN THE CITY OF CONWAY, FAULKNER COUNTY. WORK INCLUDES CONSTRUCTING THE RAILROAD OVERPASS | New Bridge Construction | 2009-09-30 | 2009-09-30 | 2010-10-25 | 2011-06-10 | 2360595 | 0.310 | ARR2052
668 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CHICOT |  | 04 | ARR2053 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 2.2 MILES OF HIGHWAY 65 BETWEEN FAIRVIEW AND THE LAKE VILLAGE TOURIST INFORMATION CENTER IN CHICOT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4 | Pavement Widening | 2010-02-12 | 2010-02-17 | 2010-11-30 | 2011-09-27 | 6697617 | 2.280 | ARR2053
669 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | DALLAS |  | 04 | ARR2054 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.44 MILES OF HIGHWAY 167 BETWEEN FORDYCE AND HIGHWAY 273 IN DALLAS COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY, FIVE STRUCTURES, DRAINAGE IMPROVEM | Pavement Widening | 2010-01-12 | 2010-01-20 | 2012-10-12 | 2012-10-12 | 19721383 | 4.440 | ARR2054
670 | ARKANSAS | Underway | C230 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2055 | THE PURPOSE OF THIS PROJECT IS TO WIDEN BROCKINGTON ROAD BETWEEN HIGHWAY 176 AND MARYLAND AVENUE IN THE CITY OF SHERWOOD, PULASKI COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4 LANES WI | Pavement Widening | 2010-05-04 | 2009-07-02 | 2011-11-01 |  | 4844503 | 0.730 | ARR2055
671 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI | LITTLE ROCK-NORTH LITTLE ROCK | 02 | ARR2056 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 0.851 MILE OF HIGHWAY 107 IN PULASKI COUNTY. WORK INCLUDES GRADING, MINOR DRAINAGE STRUCTURES, PAVING, STORM DRAINS, EROSION CONTROL ITEMS, MAINTENANCE OF TRAFFIC AND MISCELLANEOUS ITEMS. | Pavement Widening | 2009-11-12 | 2009-11-12 | 2011-04-15 | 2011-08-22 | 2669342 | 0.850 | ARR2056
672 | ARKANSAS | Underway | C240 | Highway Infrastructure Investment Grant | ARKANSAS | GRANT |  | 04 | ARR2057 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 4.91 MILES OF HIGHWAY 167 BETWEEN THE SALINE RIVER AND NORTH MILLERVILLE IN GRANT COUNTY. WORK WILL INCLUDE WIDENING THE EXISTING ROADWAY TO 4-LANES WITH AN 11 | Bridge Replacement | 2009-11-13 | 2009-12-01 | 2013-05-10 |  | 7244745 | 4.910 | ARR2057
673 | ARKANSAS | Underway | C200 | Highway Infrastructure Investment Grant | ARKANSAS | MILLER |  | 04 | ARR2058 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AN OVERPASS BRIDGE STRUCTURE AND 2.44 MILES OF EMBANKMENT AS PART OF THE NEW LOCATION OF HIGHWAY 71 (FUTURE INTERSTATE 49), BETWEEN THE LOUISIANA STATE LINE | New Construction | 2010-01-26 | 2010-04-19 | 2011-12-31 |  | 6856721 | 2.440 | ARR2058
674 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | PULASKI |  | 02 | ARR2059 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT AND WIDEN 1.57 MILES OF HIGHWAY 67 BETWEEN KIEHL AVENUE AND HIGHWAY 440 IN THE CITY OF SHERWOOD, PULASKI COUNTY. WORK INCLUDES WIDENING THE EXISTING ROAD | Pavement Widening | 2010-03-19 | 2010-03-04 | 2010-12-20 | 2011-04-16 | 8516865 | 1.570 | ARR2059
675 | ARKANSAS | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | CLEBURNE |  | 01 | ARR2060 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.96 MILES OF COUNTY ROAD 79 FROM WILBURN NORTH IN CLEBURNE COUNTY. | Pavement Improvement | 2010-02-19 | 2010-04-06 | 2010-04-21 | 2010-04-21 | 287990 | 2.960 | ARR2060
676 | ARKANSAS | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD |  | 04 | ARR2061 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.83 MILES OF COUNTY ROAD 88 BETWEEN HIGHWAY 78 AND HIGHWAY 174 IN HEMPSTEAD COUNTY. | Pavement Improvement | 2010-03-01 | 2010-03-02 | 2010-03-17 | 2010-03-17 | 225622 | 1.830 | ARR2061
677 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | CRITTENDEN |  | 01 | ARR2062 | THE PURPOSE OF THIS PROJECT IS TO WIDEN 1.0 MILE OF HIGHWAY 118 BETWEEN HIGHWAY 70 AND INTERSTATE 40 IN THE CITY OF WEST MEMPHIS IN CRITTENDEN COUNTY. | Pavement Widening | 2010-02-22 | 2010-04-19 | 2010-11-29 | 2011-06-29 | 2877096 | 0.840 | ARR2062
678 | ARKANSAS | Completed | C250,C240 | Highway Infrastructure Investment Grant | ARKANSAS | HEMPSTEAD, LAFAYETTE |  | 04 | ARR2063 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT 3 NORTHBOUND AND 3 SOUTHBOUND PASSING LANES FOR A DISTANCE OF 7.2 MILES BETWEEN THE CITIES OF HOPE AND LEWISVILLE IN HEMPSTEAD AND LAYFAYETTE COUNTIES. | Pavement Widening | 2010-04-21 | 2010-05-04 | 2011-10-31 | 2011-12-02 | 9452572 | 7.410 | ARR2063
679 | ARKANSAS | Completed | C950 | Ferryboat | ARKANSAS | MARION |  | 03 | ARR2064 | THE PURPOSE OF THIS PROJECT IS TO REPLACE TWO OF THE PEEL FERRY TUGBOATS | Other | 2010-10-08 | 2010-10-01 | 2011-01-15 | 2011-03-09 | 350000 | 0.000 | ARR2064
680 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | INDEPENDENCE |  | 01 | ARR2065 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.54 MILES OF HIGHWAY 167 FROM NORTH OF THE CITY OF PLEASANT PLAINS SOUTH IN INDEPENDENCE COUNTY. | Pavement Improvement | 2010-02-16 | 2010-04-05 | 2010-06-25 | 2010-05-13 | 664680 | 1.540 | ARR2065
681 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2066 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 2.64 MILES OF HIGHWAY 64 BETWEEN INTERSTATE 40 AND SQUIRREL HILL IN FAULKNER COUNTY. | Pavement Improvement | 2010-02-03 | 2010-03-01 | 2010-06-25 | 2010-04-20 | 916518 | 2.640 | ARR2066
682 | ARKANSAS | Completed | C250 | Highway Infrastructure Investment Grant | ARKANSAS | YELL |  | 02 | ARR2067 | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT 1.25 MILES OF COUNTY ROAD 88 BETWEEN KINGSTON AND HIGHWAY 28 IN YELL COUNTY. | Pavement Improvement | 2010-04-07 | 2010-04-19 | 2011-09-26 | 2011-09-23 | 208241 | 2.500 | ARR2067
683 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2068 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 60 AND COUNTRY CLUB ROAD IN THE CITY OF CONWAY IN FAULKNER COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT, PAVING ITEMS AND PAVEMENT MARKINGS. | Safety/Traffic Management | 2010-06-04 | 2010-07-22 | 2010-11-12 | 2010-11-09 | 129929 | 0.000 | ARR2068
684 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | JEFFERSON | PINE BLUFF | 04 | ARR2069 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL TWO TRAFFIC SIGNALS ON HIGHWAY 65B AT THE INTERSECTIONS OF WALNUT STREET AND CONVENTION CENTER DRIVE IN THE CITY OF PINE BLUFF IN JEFFERSON COUN | Safety/Traffic Management | 2010-08-18 | 2010-12-09 | 2011-02-18 | 2011-04-18 | 219714 | 0.000 | ARR2069
685 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | JEFFERSON |  | 04 | ARR2070 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL ON HIGHWAY 190 AT THE INTERSECTION OF OHIO STREET/EAST HARDING AVENUE IN THE CITY OF PINE BLUFF IN JEFFERSON COUNTY. WORK ITEM | Safety/Traffic Management | 2011-02-23 | 2011-03-04 | 2011-09-18 | 2011-08-02 | 84002 | 0.000 | ARR2070
686 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLEBURNE |  | 01 | ARR2072 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 25/110 INTERSECTION IN THE CITY OF HEBER SPRINGS IN CLEBURNE COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMEN | Safety/Traffic Management | 2010-08-04 | 2010-10-14 | 2011-02-18 | 2011-02-15 | 96634 | 0.000 | ARR2072
687 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | OUACHITA |  | 04 | ARR2073 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE HIGHWAY 278 AND COUNTRY CLUB ROAD INTERSECTION IN THE CITY OF CAMDEN IN OUACHITA COUNTY. WORK ITEMS INCLUDE TRAFFIC SIG | Safety/Traffic Management | 2010-07-06 | 2010-11-30 | 2011-08-11 | 2011-03-16 | 84304 | 0.000 | ARR2073
688 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CLARK |  | 04 | ARR2074 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL ON HIGHWAY 51 AT THE INTERSECTION OF 12TH STREET IN THE CITY OF ARKADELPHIA IN CLARK COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL | Safety/Traffic Management | 2011-04-04 | 2011-06-13 | 2011-08-11 | 2011-08-11 | 84002 | 0.000 | ARR2074
689 | ARKANSAS | Completed | C200 | Highway Infrastructure Investment Grant | ARKANSAS | CRAIGHEAD | JONESBORO | 01 | ARR2075 | THE PURPOSE OF THIS PROJECT IS TO CONSTRUCT AND INSTALL A TRAFFIC SIGNAL AT THE INTERSECTION OF HIGHWAY 91 AND GEE ST. IN THE CITY OF JONESBORO IN CRAIGHEAD COUNTY. WORK ITEMS INCLUDE TRAFFIC SIGNAL EQUIPMENT AND PAVEMENT MARKINGS. | Safety/Traffic Management | 2010-07-02 | 2010-09-21 | 2011-01-08 | 2011-01-07 | 82409 | 0.000 | ARR2075
690 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WASHINGTON | FAYETTEVILLE-SPRINGDALE | 03 | ARR2076 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.74 MILES OF HIGHWAYS 71 AND 71B BETWEEN HIGHWAY 156 AND INTERSTATE 540 IN THE CITY OF FAYETTEVILLE, WASHINGTON COUNTY. WORK INCLUDES PAVEMENT REHABIL | Pavement Improvement | 2010-06-25 | 2010-07-02 | 2010-11-12 | 2010-09-03 | 1042398 | 1.740 | ARR2076
691 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | BAXTER, MARION |  | Multiple | ARR2077 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.26 MILES OF HIGHWAY 62 FROM THE TOWN OF GASSVILLE WEST IN BAXTER AND MARION COUNTIES. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, APPROACH GU | Pavement Improvement | 2010-06-25 | 2010-07-19 | 2010-10-03 | 2010-12-09 | 843706 | 3.260 | ARR2077
692 | ARKANSAS | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | ARKANSAS | MISSISSIPPI |  | 01 | ARR2078 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 5.0 MILES OF INTERSTATE 55 FROM SOUTH OF HIGHWAY 61 TO NORTH OF HIGHWAY 18 IN THE CITY OF BLYTHEVILLE, MISSISSIPPI COUNTY. WORK INCLUDES PAVEMENT RUBBL | Pavement Improvement | 2010-12-16 | 2011-01-24 | 2012-06-20 | 2012-07-06 | 19532858 | 10.000 | ARR2078
693 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2079 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 3.7 MILES OF HIGHWAY 65 FROM HWY. 25 NORTH AND SOUTH IN THE CITY OF GREENBRIER, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MA | Pavement Improvement | 2010-09-09 | 2011-02-28 | 2011-04-15 | 2011-04-29 | 1125491 | 9.840 | ARR2079
694 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | MONTGOMERY |  | 04 | ARR2080 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 7.51 MILE OF HIGHWAY 27 FROM HWY. 270 SOUTH IN THE CITY OF MOUNT IDA, MONTGOMERY COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2010-09-03 | 2010-10-26 | 2010-12-31 | 2010-12-22 | 1608047 | 7.510 | ARR2080
695 | ARKANSAS | Completed | C200,C240 | Highway Infrastructure Investment Grant | ARKANSAS | FAULKNER |  | 02 | ARR2081 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 1.66 MILES OF HIGHWAY 65 FROM HWY. 124 NORTH AND SOUTH IN THE CITY OF DAMASCUS, FAULKNER COUNTY. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MA | Pavement Improvement | 2010-09-09 | 2011-04-05 | 2011-06-01 | 2011-04-19 | 488679 | 3.320 | ARR2081
696 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2082 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 4 RAMPS OFF HIGHWAY 67 IN WHITE COUNTY. WORK WILL INCLUDE PAVEMENT REHABILITATION, COLD MILLING, MAINTENANCE OF TRAFFIC, PAVEMENT MARKING AND MISCELLANEOUS ITEMS. | Pavement Improvement | 2010-09-13 | 2010-11-23 | 2011-04-15 | 2011-03-31 | 818332 | 0.040 | ARR2082
697 | ARKANSAS | Completed | C240 | Highway Infrastructure Investment Grant | ARKANSAS | WHITE |  | 02 | ARR2083 | THE PURPOSE OF THIS PROJECT IS TO REHABILITATE 6.56 MILES OF HIGHWAY 67 FROM THE LONOKE COUNTY LINE NORTH IN WHITE COUNTY IN THE CITY OF BEEBE. WORK INCLUDES PAVEMENT REHABILITATION, COLD MILLING, MA | Pavement Improvement | 2010-09-03 | 2010-11-10 | 2011-08-01 | 2011-09-16 | 1456205 | 6.560 | ARR2083
698 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA, SACRAMENTO, PLACER | SACRAMENTO | Multiple | 000C303 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In Colusa, Placer and Sacramento Counties, at various locations. | Pavement Improvement | 2009-07-02 | 2009-09-18 | 2011-03-18 | 2011-03-18 | 6246659 | 1.000 | 000C303
699 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO, SACRAMENTO, PLACER | SACRAMENTO | Multiple | 000C304 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In Sacramento, El Dorado, Yolo and Placer counties, at various locations. | Safety/Traffic Management | 2009-05-18 | 2009-07-27 | 2009-12-24 | 2009-12-24 | 1810921 | 1.000 | 000C304
700 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA, PLUMAS |  | Multiple | 000C305 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Tehama and Plumas Counties, as Various Locations. | Pavement Improvement | 2009-06-26 | 2009-07-06 | 2009-09-18 | 2009-09-18 | 2239548.17 | 1.000 | 000C305
701 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 000C306 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Kern and King Counties near Avenal and Devils Den (Sunflower Valley) on State Ro | Pavement Improvement | 2009-07-02 | 2009-07-09 | 2009-10-19 | 2009-10-19 | 3671087.12 | 1.000 | 000C306
702 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO, SAN BERNARDINO |  | 25 | 000C307 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: Shoshone from SR 127 to 0.2 miles E of Chicago Valley in San Bernardino near Baker | Pavement Improvement | 2010-01-28 | 2010-03-17 | 2010-09-07 | 2010-09-07 | 1438774.9 | 5.000 | 000C307
703 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE, SAN BERNARDINO |  | Multiple | 000C313 | This is a Archaeological Planning and Research project by the California Department of Transportation. The project is described as: Various Conventional Routes in Riverside and San Bernardino County. | Other | 2010-09-24 | 2010-09-24 | 2012-04-01 |  | 1405000 | 1.000 | 000C313
704 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | 0052943 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: In Orange County, on Route 5 from Calle Juanita to 4th Street. Provide enhanced paving and landscaping. | Transportation Enhancements | 2010-05-11 | 2010-09-04 | 2014-07-10 |  | 1152094 | 25.100 | 0052943
705 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 0053014 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Sun Valley and Sylmar, from Hollywood Way to north of San Fernando Road. | Pavement Improvement | 2009-10-12 | 2009-10-22 | 2011-04-13 | 2011-09-28 | 11034118 | 4.900 | 0053014
706 | CALIFORNIA | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | STATEWIDE | Multiple | 0053029 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Slab Replacement combined with HOV From Buena Vista to Rte 170. | Safety/Traffic Management | 2010-12-20 | 2011-03-01 | 2014-06-02 |  | 39280884 | 4.400 | 0053029
707 | CALIFORNIA | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | STATEWIDE | 28 | 0053033 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Sun Valley and Sylmar, from Hollywood Way to north of San Fernando Road. | Pavement Improvement | 2010-06-25 | 2010-07-19 | 2015-08-12 |  | 31237808 | 3.400 | 0053033
708 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 25 | 0053043 | IN LOS ANGELES COUNTY, IN VALENCIA AND CASTAIC, ROADWAY REHABILITATION (TC) | Pavement Improvement | 2011-02-14 | 2011-02-24 | 2012-03-30 |  | 14385735 |  | 0053043
709 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 0054182 | This is a Safety project by the California Department of Transportation. The project is described as: Near Grapevine, at various locations. | Pavement Improvement | 2009-07-15 | 2009-09-08 | 2010-06-30 | 2010-06-30 | 1527511.33 | 3.800 | 0054182
710 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 0054185 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Near Buttonwillow from Route 223 to 7th Standard Road. Rehabilitate Roadway. | Pavement Improvement | 2011-01-30 | 2011-02-23 | 2011-11-04 |  | 17377362 |  | 0054185
711 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA |  | 02 | 0058336 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In and near Red Bluff, from 5.3 miles south of Adobe Road Overcrossing to Adobe Road Overcrossing. | Pavement Improvement | 2009-07-08 | 2009-08-24 | 2011-11-21 | 2011-10-11 | 36407184.43 | 3.400 | 0058336
712 | CALIFORNIA | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | STATEWIDE | 45 | 0103101 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Construct new Bob Hope Drive Interchange and modify Ramon Interchange. | Pavement Widening | 2009-12-10 | 2010-02-03 | 2012-01-31 | 2012-02-09 | 23553000 | 3.000 | 0103101
713 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | Multiple | 0153044 | ON INTERSTATE ROUTE 15 IN SAN BERNARDINO COUNTY ABOUT 25 MILES SOUTH OF THE ***, TRANSPORTATION ENHANCEMENT (LANDSCAPING) (TC) | Transportation Enhancements | 2011-05-11 | 2011-05-16 | 2012-03-06 | 2012-04-13 | 710010 |  | 0153044
714 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE |  | 44 | 0155152 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Riverside County in and near Corona, from Temescal Canyon Road to 0.4 mile south of Ontario Avenue. | Pavement Improvement | 2009-06-15 | 2009-06-29 | 2009-08-05 | 2009-08-05 | 851045 | 5.000 | 0155152
715 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | SAN FRANCISCO-OAKLAND, CA | 03 | 0802356 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Fairfield, from 0.4 mile west of Route 12 to 0.8 mile east of | Pavement Improvement | 2009-04-28 | 2009-05-18 | 2010-11-30 | 2010-11-30 | 17309708.55 | 4.700 | 0802356
716 | CALIFORNIA | Underway | C490 | OJT/SS | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 1002000 | This is a training project by the California Department of Transportation. The project is described as: OJT. | Other | 2010-10-28 | 2011-06-30 | 2012-06-29 |  | 130000 |  | 1002000
717 | CALIFORNIA | Underway | C490 | OJT/SS | CALIFORNIA | STATEWIDE |  |  | 1010000 | This is a training project by the California Department of Transportation. The project is described as: OJT training. | Other | 2011-04-04 | 2011-04-04 | 2012-04-03 |  | 208543 |  | 1010000
718 | CALIFORNIA | Underway | C490 | OJT/SS | CALIFORNIA | SACRAMENTO | SACRAMENTO | 05 | 1011000 | This is a training project by the California Department of Transportation. The project is described as: OJT training. | Other | 2011-06-01 | 2011-06-01 | 2012-06-01 |  | 338590 |  | 1011000
719 | CALIFORNIA | Completed | C490 | OJT/SS | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 1014000 | This is a training project by the California Department of Transportation. The project is described as: Commercial truck driver license training course. | Other | 2011-06-30 | 2011-06-30 | 2012-06-29 | 2012-06-29 | 230789 |  | 1014000
720 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 2056328 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: Near Tracy, on Route 205 from Alameda County line to Route 5. Tree Planting. | Transportation Enhancements | 2010-06-10 | 2010-06-14 | 2011-04-01 | 2011-04-01 | 1207301 | 12.600 | 2056328
721 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 2101795 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Los Angeles County in and near Pasadena, from State Route 2-A | Pavement Improvement | 2009-09-16 | 2009-11-09 | 2010-07-02 | 2010-07-02 | 341883 | 5.400 | 2101795
722 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN FRANCISCO-OAKLAND, CA | Multiple | 2801119 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In San Jose, from Cypress Avenue Pedestrian Overcrossing to Tantau Avenue. | Pavement Improvement | 2009-07-29 | 2009-09-09 | 2010-07-14 | 2010-07-14 | 11304295 | 2.700 | 2801119
723 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 2801122 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: In San Mateo County from Santa Clara County line to San Francisco County Line. Install TMS Elements. | Safety/Traffic Management | 2009-10-08 | 2009-12-16 |  | 2011-03-28 | 1705293 | 27.400 | 2801122
724 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 2801126 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Ramp Meters at 9 Locations. | Safety/Traffic Management | 2010-04-07 | 2010-05-03 |  | 2011-10-26 | 2985656 | 3.000 | 2801126
725 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | Multiple | 2801127 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Ramp Meters at 8 Locations. | Safety/Traffic Management | 2010-04-28 | 2010-05-10 | 2011-04-25 | 2011-07-13 | 3248320 | 3.500 | 2801127
726 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 2801129 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Ramp Meters at 7 Locations. | Safety/Traffic Management | 2010-03-08 | 2010-06-02 | 2011-05-25 | 2012-01-19 | 4182612 | 7.000 | 2801129
727 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 4053015 | This is a Design-Build Contract project by the California Department of Transportation. The project is described as: Widen NB I-405 for HOV Lane. | Safety/Traffic Management | 2009-06-02 | 2009-06-02 | 2013-04-01 |  | 189900000 | 10.200 | 4053015
728 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 05 | 5002138 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sacramento. The project is described as: Various locations W/in the city of Sacramento. | Pavement Improvement | 2009-08-26 | 2009-08-27 | 2009-12-01 | 2010-01-11 | 5246052 | 1.000 | 5002138
729 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5002140 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sacramento. The project is described as: Overlays - various locations w/in Sacramento City (Phase II). | Pavement Improvement | 2009-08-26 | 2009-09-08 | 2009-12-01 | 2009-11-30 | 2810571 | 1.000 | 5002140
730 | CALIFORNIA | Underway | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 05 | 5002142 | This is a Transit project by a local agency in the City of Sacramento. The project is described as: Sacramento Railyards - vicinity of I-5/7th St/H Street. | Other | 2011-04-06 | 2011-04-15 | 2013-01-31 |  | 21047897 | 0.000 | 5002142
731 | CALIFORNIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | STATEWIDE | 07 | 5003023 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Benicia. The project is described as: State Park Road Bridge Widening Class 1 Bike Path between Columbus and the Benicia State Park. | Transportation Enhancements | 2009-12-17 | 2009-12-17 | 2010-08-01 | 2010-12-17 | 491800 | 0.200 | 5003023
732 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VALLEJO | 07 | 5003024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Benicia. The project is described as: East 2nd Street between Lake Herman Rd. and Wagner St. | Pavement Improvement | 2009-10-26 | 2009-10-26 | 2009-12-04 | 2009-12-04 | 219195.58 | 0.590 | 5003024
733 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5005096 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Jose. The project is described as: Rehabilitate local streets. | Pavement Improvement | 2009-10-06 | 2009-10-19 | 2010-12-30 | 2010-12-31 | 8128535.23 | 8.650 | 5005096
734 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | STATEWIDE | 16 | 5005099 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Jose. The project is described as: Various Street Rehabilitation | Pavement Improvement | 2010-05-17 | 2010-05-28 | 2010-12-30 | 2011-03-01 | 6116534 | 4.380 | 5005099
735 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5006569 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Angeles. The project is described as: LAX Hospitality Zone Street and Sidewalk Rehabilitation Phase 1. | Pavement Improvement | 2009-07-06 | 2009-07-07 | 2012-12-01 |  | 7000000 | 3.850 | 5006569
736 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5006571 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: Commerce Ave restoration project. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2010-02-01 | 2010-06-30 | 900000 | 0.500 | 5006571
737 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5006574 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: LAUSD Valley Region High School #4 sidewalk improvements. | Pavement Improvement | 2011-08-29 | 2011-09-19 | 2012-12-30 |  | 300000 | 0.500 | 5006574
738 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006577 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: City of Los Angeles North Central Region Resurfacing Project | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2013-06-30 |  | 7275000 | 14.000 | 5006577
739 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006578 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: West Valley Region Resurfacing project | Pavement Improvement | 2009-07-01 | 2009-07-02 | 2012-09-01 |  | 7275000 | 18.000 | 5006578
740 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5006579 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: East Valley Region Resurfacing Project | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2012-09-01 |  | 7275000 | 16.000 | 5006579
741 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006580 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: Bay Harbor Region Resurfacing Projects | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2012-09-01 |  | 7275000 | 16.500 | 5006580
742 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006581 | This is a Safety project by a local agency in the City of Los Angeles. The project is described as: Installation of left turn arrows Citywide | Safety/Traffic Management | 2011-01-03 | 2011-01-24 | 2011-10-03 | 2011-09-30 | 4000000 | 1.000 | 5006581
743 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006582 | This is a Transit project by a local agency in the City of Los Angeles. The project is described as: Transit Priority System and ATSAC Communication System Rehab | Safety/Traffic Management | 2010-06-01 | 2010-06-08 | 2013-06-30 |  | 5598697 | 0.000 | 5006582
744 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006586 | This is a Traffic Management Engineering project by a local agency in the City of Los Angeles. The project is described as: Signal LED Retrofit Program Phase 1 | Safety/Traffic Management | 2009-07-01 | 2009-07-01 | 2012-09-01 |  | 9000000 | 1.000 | 5006586
745 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006589 | This is a Safety project by a local agency in the City of Los Angeles. The project is described as: New Traffic Signals | Safety/Traffic Management | 2011-01-03 | 2011-01-24 | 2011-10-03 | 2011-09-30 | 3500000 | 1.000 | 5006589
746 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006591 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: Upgrading approx 1000 catch basins to bicycle safety grates | Transportation Enhancements | 2010-04-21 | 2010-06-01 | 2012-08-01 | 2011-02-28 | 524780 | 1.000 | 5006591
747 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006592 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: Upgrade 500 catch basins to bicycle safety grates | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2012-02-28 | 2012-02-28 | 1555275 | 1.000 | 5006592
748 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006593 | This is a Rail/Highway Crossing project by a local agency in the City of Los Angeles. The project is described as: Highway Rail Grade Crossing Improvement Program. | Pavement Improvement | 2010-11-29 | 2010-12-13 | 2013-06-30 |  | 2769303 | 1.000 | 5006593
749 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006595 | This is a Pavement Resurfacing project by a local agency in the City of Los Angeles. The project is described as: City of Los Angeles Resurfacing Phase 2. | Pavement Improvement | 2009-07-01 | 2009-07-01 | 2012-09-01 |  | 15588000 | 10.250 | 5006595
750 | CALIFORNIA | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5006597 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: Tampa Ave over Los Angeles River. | Pavement Improvement | 2010-10-26 | 2011-03-07 | 2012-07-15 |  | 3700372.56 | 1.000 | 5006597
751 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006598 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: AC resurfacing at 4 locations: Colfax Ave btwn Moorpark St/Ventura | Pavement Improvement | 2010-10-18 | 2010-11-02 | 2013-04-18 |  | 2700000 | 1.000 | 5006598
752 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5006601 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Angeles. The project is described as: Winnetka Ave over Los Angeles River | Pavement Improvement | 2011-02-11 | 2011-05-06 | 2012-09-28 |  | 2000000 | 1.000 | 5006601
753 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5006602 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Los Angeles. The project is described as: Harry Bridges Relocation | Pavement Improvement | 2010-03-22 | 2010-03-22 | 2012-05-29 |  | 15545200 | 1.110 | 5006602
754 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5006674 | This is a Rail/Highway Crossing project by a local agency in the City of Los Angeles. The project is described as: CITYWIDE AT RR CROSSINGS / CITY OF LOS ANGELES, HIGHWAY-RAIL GRADE CROSSING SURFACE RECONSTRUCTION | Pavement Improvement | 2010-07-02 | 2010-07-02 | 2013-09-30 |  | 7932000 |  | 5006674
755 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5007046 | This is a Pavement Resurfacing project by a local agency in the City of Santa Barbara. The project is described as: Various Roads in the city of SB | Pavement Improvement | 2010-04-15 | 2010-05-24 | 2010-08-30 | 2011-07-11 | 2674796 | 1.000 | 5007046
756 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5007047 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Barbara. The project is described as: Various locations at intersections in the City of Santa Barbara | Transportation Enhancements | 2010-06-03 | 2010-06-03 | 2010-12-30 | 2010-12-30 | 300000 | 1.000 | 5007047
757 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5007048 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Barbara. The project is described as: Various locations throughout City of Santa Barbara | Transportation Enhancements | 2010-06-30 | 2010-07-12 | 2010-12-17 | 2011-07-11 | 791217.44 | 1.000 | 5007048
758 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5008087 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Stockton. The project is described as: Rehabilitation of 24 streets in the City of Stockton | Pavement Improvement | 2009-10-01 | 2009-10-20 | 2012-12-30 | 2012-10-17 | 6141391 | 14.000 | 5008087
759 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5008091 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Stockton. The project is described as: 72 Streets in the City of Stockton | Pavement Improvement | 2011-08-01 | 2011-08-10 | 2013-01-30 |  | 2603160 | 31.000 | 5008091
760 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5008092 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Stockton. The project is described as: Construct and enhance new median from 10th Street to Duck Creek | Transportation Enhancements | 2010-06-01 | 2010-06-07 | 2010-11-30 | 2010-11-19 | 894955 | 0.400 | 5008092
761 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA | SACRAMENTO | 02 | 5009027 | This is a Traffic Management Engineering project by a local agency in the City of Marysville. The project is described as: 10th and Ramirez Street intersection, and 10th Street between Yuba Street and Ramirez Street | Pavement Improvement | 2010-05-18 | 2010-05-24 | 2010-11-15 | 2010-11-30 | 43000 | 1.000 | 5009027
762 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | 5009028 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Marysville. The project is described as: Third Street from E ST to J ST | Pavement Improvement | 2011-10-05 | 2012-04-02 | 2012-12-31 | 2013-01-10 | 1386215 | 1.000 | 5009028
763 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5012098 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Oakland. The project is described as: Citywide Curb Ramp and Sidewalk Repair | Transportation Enhancements | 2010-02-15 | 2010-04-12 | 2013-01-31 |  | 1118832 | 1.000 | 5012098
764 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5012099 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakland. The project is described as: Various Streets and Roads Rehabilitation - Citywide | Pavement Improvement | 2010-03-01 | 2010-04-12 | 2012-02-15 | 2012-01-20 | 3857444 | 5.580 | 5012099
765 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5012100 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Oakland. The project is described as: 7th Steet, West Oakland Transit Village Improvements. | Transportation Enhancements | 2010-04-26 | 2010-05-19 | 2013-01-31 |  | 1300000 | 0.500 | 5012100
766 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN JOSE, CA | 09 | 5012101 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakland. The project is described as: City of Oakland Various Streets and Road Rehabilitation | Pavement Improvement | 2010-12-20 | 2010-12-20 | 2013-01-31 |  | 1255000 | 9.170 | 5012101
767 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | STATEWIDE | 09 | 5012104 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakland. The project is described as: Various Locations | Pavement Improvement | 2010-12-22 | 2010-12-22 | 2012-05-15 | 2012-05-01 | 991725 | 3.010 | 5012104
768 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5013012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Crescent City. The project is described as: On Fifth Street (A to Wendell) | Pavement Improvement | 2010-06-02 | 2010-06-07 | 2010-09-30 | 2010-07-08 | 79750 | 0.060 | 5013012
769 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5013013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Crescent City. The project is described as: On H Street from Front Street to 11th Street. | Transportation Enhancements | 2010-06-02 | 2010-06-17 | 2010-09-30 | 2010-08-27 | 146044 | 0.570 | 5013013
770 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5014032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alameda. The project is described as: Central Ave- Pacific Ave. to Webster St, | Pavement Improvement | 2009-08-07 | 2009-08-07 | 2012-07-01 | 2012-06-29 | 1304000 | 1.040 | 5014032
771 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | CONCORD | 13 | 5014033 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Alameda. The project is described as: Buena Vista Ave. | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2011-04-01 | 2011-03-01 | 350000 | 0.440 | 5014033
772 | CALIFORNIA | Completed | C250,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO | SACRAMENTO | 04 | 5015013 | This is a Pavement Resurfacing project by a local agency in the City of Placerville. The project is described as: Cold Springs Road and Carson Road | Pavement Improvement | 2009-11-16 | 2009-11-16 | 2010-02-01 | 2010-03-09 | 415584 | 0.800 | 5015013
773 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO | SACRAMENTO | 04 | 5015018 | MORRENE DR: HOCKING ST TO GIOVANNI DR AND HOCKING ST: MOSQUITO RD TO MORRENE DR, ROADWAY REHABILITATION / ADA CURB RAMPS (VAR) | Pavement Improvement | 2011-08-15 | 2011-08-16 | 2011-10-15 | 2011-12-09 | 244743.69 |  | 5015018
774 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 23 | 5016049 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of San Luis Obispo. The project is described as: Monterey Street | Pavement Improvement | 2011-01-04 | 2011-01-31 | 2011-05-13 | 2011-05-17 | 1168343.42 | 0.500 | 5016049
775 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5017023 | This is a Pavement Resurfacing project by a local agency in the City of Eureka. The project is described as: Hodgson, Harris, and Summer Streets. Hodgson St from F St to W St, Harris St from Broadway to S St, and Summer St from 5th St to 14th St. | Pavement Improvement | 2009-10-29 | 2010-05-10 | 2010-07-20 | 2010-10-05 | 656094.99 | 3.530 | 5017023
776 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5017024 | This is a Pavement Resurfacing project by a local agency in the City of Eureka. The project is described as: Third Street from Broadway to B St, and Harris St from K St to Harrison | Pavement Improvement | 2010-08-27 | 2010-09-07 | 2011-01-31 | 2011-01-31 | 329925 | 0.230 | 5017024
777 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5018017 | This is a Pavement Resurfacing project by a local agency in the City of Nevada City. The project is described as: Broad St from Union St to Commercial St, and from Commercial St to SR 49 | Pavement Improvement | 2010-09-01 | 2010-09-27 | 2010-10-01 | 2010-10-01 | 120438 | 0.700 | 5018017
778 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | STATEWIDE | 15 | 5019022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clara. The project is described as: Rehabilitate local streets. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2010-07-01 | 2010-11-16 | 1050907.93 | 4.800 | 5019022
779 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5019023 | This is a Traffic Management Engineering project by a local agency in the City of Santa Clara. The project is described as: Monroe Street Traffic Signal Interconnect | Safety/Traffic Management | 2009-09-28 | 2009-09-28 | 2010-10-01 | 2010-09-28 | 404585 | 1.290 | 5019023
780 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5020015 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Yreka. The project is described as: Crosswalk & bike lane striping, bike ped signs on existing posts. Greenh | Transportation Enhancements | 2011-03-28 | 2011-06-06 | 2011-07-07 | 2011-06-16 | 48864.59 | 0.250 | 5020015
781 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5021015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arcata. The project is described as: AC overlay from Union Ave to Buttermilk Lane | Pavement Improvement | 2011-06-27 | 2011-07-28 | 2011-09-29 | 2011-10-31 | 136835 |  | 5021015
782 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5021016 | This is a Pavement Resurfacing project by a local agency in the City of Arcata. The project is described as: Alliance Rd, Arcata | Pavement Improvement | 2010-07-23 | 2010-08-10 | 2010-08-31 | 2011-01-31 | 390317.89 | 0.700 | 5021016
783 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5021017 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Arcata. The project is described as: Bike and Ped Improvements along Samoa Blvd. | Transportation Enhancements | 2011-07-19 | 2011-07-19 | 2012-09-30 | 2012-08-28 | 1445181 | 1.150 | 5021017
784 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5022044 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Petaluma. The project is described as: Ely Road, Sunnyslope Avenue | Pavement Improvement | 2009-09-10 | 2009-09-28 | 2010-03-15 | 2010-03-01 | 561046.76 | 1.010 | 5022044
785 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5022045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Petaluma. The project is described as: McDowell Blvd North from Lynch Creek Way to Dynamic Street | Pavement Improvement | 2010-03-08 | 2010-04-06 | 2010-09-01 | 2010-06-21 | 728000 | 0.650 | 5022045
786 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5023009 | This is a Pavement Resurfacing project by a local agency in the City of Grass Valley. The project is described as: South Auburn Street from Hwy 20/49 to McNight Way | Pavement Improvement | 2008-10-10 | 2010-05-28 | 2010-06-15 | 2010-08-19 | 506565 | 0.220 | 5023009
787 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 07 | 5024023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Martinez. The project is described as: Alhambra Ave. | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2009-12-01 | 2009-12-31 | 850000 | 4.200 | 5024023
788 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 07 | 5024024 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Martinez. The project is described as: Pedestrian Enhancements | Transportation Enhancements | 2010-03-15 | 2010-03-29 | 2012-09-30 | 2012-12-19 | 756299 | 0.600 | 5024024
789 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: Morrissey Blvd from Soquel Ave to Fairmount | Pavement Improvement | 2009-08-18 | 2009-08-31 | 2009-10-01 | 2009-11-16 | 388682 | 0.200 | 5025045
790 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: Market Street between Water Street to SR1/Mission | Pavement Improvement | 2009-08-18 | 2009-09-04 | 2009-10-01 | 2009-11-16 | 272210.98 | 0.500 | 5025046
791 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025047 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: West Cliff Drive between Almar Bld and Bay Steet | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2010-04-15 | 2009-11-20 | 689107 | 1.600 | 5025047
792 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025049 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Cruz. The project is described as: In the City of Santa Cruz on Pacfic Ave, Second, & Third St CTIPS-201-0000-0471 | Pavement Improvement | 2010-04-05 | 2010-04-13 | 2010-03-01 | 2010-06-11 | 1000000 | 1.930 | 5025049
793 | CALIFORNIA | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025050 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Cruz. The project is described as: Pacific Ave/Center St (Depot Pk Intersections) | New Construction | 2010-10-06 | 2010-10-11 | 2011-07-29 | 2011-11-15 | 750000 | 0.300 | 5025050
794 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5025052 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Cruz. The project is described as: Road repairs: Almar to Swanton | Pavement Improvement | 2011-06-09 | 2011-06-13 | 2011-07-01 | 2011-10-31 | 299999.99 |  | 5025052
795 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5026043 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Buena Ventura. The project is described as: VARIOUS STREETS | Pavement Improvement | 2010-01-05 | 2010-01-06 | 2010-06-01 | 2010-10-01 | 530943 | 1.000 | 5026043
796 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5026044 | This is a Safety project by a local agency in the City of San Buena Ventura. The project is described as: INTERSECTION OF FOOTHILL ROAD AND KIMBALL ROAD | Other | 2010-04-29 | 2010-05-03 | 2010-06-15 | 2010-10-29 | 207911.97 | 1.000 | 5026044
797 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5026046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Buena Ventura. The project is described as: OLIVE STREET: CENTER STREET TO MAIN STREET AND POLI STREET/FOOTHILL ROAD | Pavement Improvement | 2010-05-10 | 2010-05-11 | 2010-09-01 | 2011-02-15 | 587006.84 | 1.000 | 5026046
798 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5026047 | This is a Pavement Resurfacing project by a local agency in the City of San Buena Ventura. The project is described as: Well Road Repaving; Street Overlay | Pavement Improvement | 2011-04-21 | 2011-04-25 | 2011-10-01 | 2011-11-03 | 263782.38 |  | 5026047
799 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5027014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Healdsburg. The project is described as: Center Street, Reed Ct, March Ave., Monte Vista Dr., Powell Ave., Grant St. | Pavement Improvement | 2009-09-08 | 2009-09-18 | 2010-05-13 | 2010-08-20 | 500000 | 2.470 | 5027014
800 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5028053 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Rosa. The project is described as: College Avenue and Summerfield Road | Pavement Improvement | 2009-09-30 | 2009-11-02 | 2010-09-30 | 2011-01-01 | 2803347.73 | 2.100 | 5028053
801 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5028054 | This is a Traffic Management Engineering project by a local agency in the City of Santa Rosa. The project is described as: Mendocino Avenue from Ridgway Avenue to Bicentennial Way | Safety/Traffic Management | 2010-10-28 | 2010-11-01 | 2010-12-30 | 2010-12-07 | 824099.94 | 1.600 | 5028054
802 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5028057 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Rosa. The project is described as: Montecito Blvd and Range Avenue from Russell Avenue to 200 Feet s/o Guerneville Road | Pavement Improvement | 2010-10-18 | 2011-03-11 | 2011-06-30 | 2011-09-12 | 840919.99 | 1.000 | 5028057
803 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | Multiple | 5029020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Redwood City. The project is described as: Veterans, Jefferson, Roosevelt | Pavement Improvement | 2009-09-08 | 2009-09-10 | 2009-10-01 | 2010-06-28 | 688774.6 | 1.500 | 5029020
804 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5029021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Redwood City. The project is described as: On El Camino Real (SR82) from Broadway to Brewster | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2011-02-28 | 2011-03-07 | 523000 | 0.250 | 5029021
805 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VALLEJO | 07 | 5030048 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Vallejo. The project is described as: Sacrmento street, Virginia Street, Marin street | Transportation Enhancements | 2009-12-14 | 2009-12-14 | 2010-12-01 | 2011-08-01 | 2207700 | 0.850 | 5030048
806 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VALLEJO | 07 | 5030049 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Vallejo. The project is described as: Sereno Drive from Transit Center to Fairgrounds Drive | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2010-04-30 | 2010-06-07 | 1020000 | 1.330 | 5030049
807 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5031018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Watsonville. The project is described as: Various Federal Aid Routes | Pavement Improvement | 2009-08-13 | 2009-08-18 | 2009-10-01 | 2010-01-26 | 1182751.76 | 10.000 | 5031018
808 | CALIFORNIA | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5031019 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Watsonville. The project is described as: Green Valley Road from Main Street (SR 152) to Penny Lane | Pavement Improvement | 2010-07-01 | 2010-08-02 | 2010-11-18 | 2011-10-11 | 2066357 | 0.800 | 5031019
809 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | FAIRFIELD | 10 | 5032022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Suisun City. The project is described as: Sunset Ave. from Rt. 12 to Railroad Avenue | Pavement Improvement | 2009-10-07 | 2009-10-13 | 2010-07-01 | 2010-06-15 | 700000 | 0.700 | 5032022
810 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | STATEWIDE | 10 | 5032024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Suisun City. The project is described as: Main Street from Solano Street to Lotz Way | Pavement Improvement | 2010-08-23 | 2010-09-07 | 2010-12-24 | 2011-09-30 | 670000 | 1.000 | 5032024
811 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5034020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Gilroy. The project is described as: Sidewalk Rehab | Transportation Enhancements | 2010-01-18 | 2010-02-16 | 2010-07-10 | 2010-07-10 | 659603.68 | 9.400 | 5034020
812 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5035010 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Colusa. The project is described as: Freemont Street ARRA | Transportation Enhancements | 2010-08-09 | 2010-08-09 | 2010-10-19 | 2010-11-17 | 130000 | 0.530 | 5035010
813 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5035011 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Colusa. The project is described as: 5th Street, between Webster St. and Oak St. in City of Colusa | Transportation Enhancements | 2010-08-09 | 2010-08-09 | 2010-10-19 | 2010-11-17 | 236464 | 0.210 | 5035011
814 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5036010 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Trinidad. The project is described as: Museum Access | Transportation Enhancements | 2010-04-01 | 2010-04-16 | 2010-06-30 | 2010-07-15 | 20000 | 0.760 | 5036010
815 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE | CHICO | 02 | 5037016 | This is a Traffic Management Engineering project by a local agency in the City of Chico. The project is described as: Skyway and SR 99 Interchange | Pavement Widening | 2010-02-01 | 2010-02-18 | 2012-08-31 | 2012-07-25 | 5500000 | 0.600 | 5037016
816 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE | CHICO | 02 | 5037018 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Chico. The project is described as: Phase 1 - In the City of Chico thru the urbanized area construct class | Transportation Enhancements | 2010-10-04 | 2010-10-04 | 2011-08-01 | 2011-12-27 | 2425000 | 6.700 | 5037018
817 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10 | 5038021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Antioch. The project is described as: Hillcrest Ave. | Pavement Improvement | 2009-09-14 | 2009-10-01 | 2010-08-31 | 2010-08-10 | 1604963.12 | 3.200 | 5038021
818 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA |  | 01 | 5039021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cloverdale. The project is described as: S. Franklin Street, Cloverdale Blvd | Pavement Improvement | 2009-08-25 | 2009-08-31 | 2009-10-01 | 2009-10-28 | 299209.24 | 1.600 | 5039021
819 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5041033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Leandro. The project is described as: Aladdin Ave. I-880 to Alvarado St. and two segments of Washing Ave. between Anza wy. and Caliennte Dr. | Pavement Improvement | 2009-09-17 | 2009-09-28 | 2010-03-01 | 2010-09-10 | 1029885 | 0.650 | 5041033
820 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5041034 | This is a Pavement Resurfacing project by a local agency in the City of San Leandro. The project is described as: San Leandro- Springlake Drive from Washington Ave to ACFCD Canel | Pavement Improvement | 2010-04-30 | 2010-05-07 | 2010-06-01 | 2010-09-30 | 344274.04 | 0.270 | 5041034
821 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5041035 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Leandro. The project is described as: Bancroft Ave. from 138th Ave. to 148th Ave. | Pavement Improvement | 2010-10-01 | 2010-10-18 | 2010-10-25 | 2011-01-03 | 308019.63 | 0.600 | 5041035
822 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA | SAN FRANCISCO-OAKLAND, CA | 01 | 5042048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Napa. The project is described as: Widen sidewalk to better accommodate pedestrian and bicycle traffic on N. | Transportation Enhancements | 2010-06-14 | 2010-06-28 | 2010-08-31 | 2010-10-26 | 147806 | 1.000 | 5042048
823 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA | STATEWIDE | 01 | 5042049 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Napa. The project is described as: City of Napa Various Streets and Roads Rehabilitation | Pavement Improvement | 2009-09-04 | 2009-09-14 | 2010-04-30 | 2010-11-23 | 1619131.15 | 1.400 | 5042049
824 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5043030 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Rafael. The project is described as: In San Rafael at Nova Albion Way, Kerner Blvd., Knight Drive, Smith Ranch Rd., and Las Gallinas Avenue. | Pavement Improvement | 2009-09-23 | 2009-10-07 | 2010-02-01 | 2010-01-27 | 1187000 | 3.330 | 5043030
825 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE | VISALIA | 21 | 5044051 | This is a Traffic Management Engineering project by a local agency in the City of Visalia. The project is described as: Widening of Ben Maddox Bridge over SR-198 , and Improvements on E Noble Ave. | Bridge Improvement | 2010-03-22 | 2010-04-23 | 2012-09-07 | 2012-09-20 | 5400000 | 0.790 | 5044051
826 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE | VISALIA | 21 | 5044054 | This is a Pavement Resurfacing project by a local agency in the City of Visalia. The project is described as: At six locations, rehabilitiate local street. | Pavement Improvement | 2010-07-07 | 2010-07-26 | 2010-09-01 | 2010-11-02 | 546207 | 1.920 | 5044054
827 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE | VISALIA | 21 | 5044060 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Visalia. The project is described as: Intersection improvements and widening at Walnut Ave and Mooney Blvd (SR-63) | Pavement Widening | 2011-06-16 | 2011-06-27 | 2012-09-04 | 2012-09-04 | 1250000 |  | 5044060
828 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5045023 | This is a Pavement Resurfacing project by a local agency in the City of Salinas. The project is described as: East Laurel Drive Improvements | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2010-04-05 | 2010-04-05 | 2795486.64 | 1.000 | 5045023
829 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5045024 | This is a Historic Preservation project by a local agency in the City of Salinas. The project is described as: Harvey Baker House Improvements | Transportation Enhancements | 2010-07-01 | 2010-07-01 | 2011-02-10 | 2011-04-12 | 176999.72 | 0.000 | 5045024
830 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5045025 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Salinas. The project is described as: Roadway preservation and landscape improvements. | Pavement Improvement | 2010-11-23 | 2010-11-23 | 2011-03-25 | 2011-04-14 | 157321.24 |  | 5045025
831 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 01 | 5046029 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Woodland. The project is described as: County Road 102 from Beamer Street to Hanson Way | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2009-12-01 | 2009-11-18 | 655725 | 1.000 | 5046029
832 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 01 | 5046030 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Woodland. The project is described as: Main Street lighting Project from West Street to Elm Street | Pavement Improvement | 2010-07-02 | 2010-07-19 | 2011-03-31 | 2011-03-31 | 541446.92 | 1.000 | 5046030
833 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 01 | 5046033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Woodland. The project is described as: Rehabilitate pavement at various roadways. | Pavement Improvement | 2010-06-22 | 2010-07-06 | 2010-08-09 | 2010-08-15 | 327863 | 5.570 | 5046033
834 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BENITO |  | 17 | 5047015 | This is a Pavement Resurfacing project by a local agency in the City of Hollister. The project is described as: In the City of Hollister on Various Road | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2010-10-15 | 2010-10-13 | 1226091 | 1.540 | 5047015
835 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | 5048004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Wheatland. The project is described as: Main Street from SR 65 (D Street) to Olive Avenue | Pavement Improvement | 2009-10-23 | 2009-11-05 | 2010-02-01 | 2010-04-15 | 486258.91 | 1.000 | 5048004
836 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5049022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Ukiah. The project is described as: South Dora Street Rehabilitation from Luce to Washington | Pavement Improvement | 2010-09-30 | 2010-10-18 | 2011-06-30 | 2011-06-30 | 438000 | 0.320 | 5049022
837 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5050036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hayward. The project is described as: Citywide | Pavement Improvement | 2009-07-24 | 2009-07-27 | 2009-11-01 | 2009-11-19 | 2037000 | 3.880 | 5050036
838 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5050037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hayward. The project is described as: Industrial Blvd. Cryer St. to West Tennyson Rd, Arf Ave and 2 other locations | Pavement Improvement | 2009-11-20 | 2009-11-30 | 2010-05-01 | 2010-06-07 | 475000 | 2.150 | 5050037
839 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 10 | 5053018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Livermore. The project is described as: Portola Ave,East Ave, E. Stanley Blvd., and Murrieta Blvd. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-01 | 2009-12-10 | 1322261.59 | 1.130 | 5053018
840 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | CONCORD | 10 | 5053020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Livermore. The project is described as: Holmes Street- Murrieta Boulevard to Q Street; Vasco Road- Dalton Avenue to Overlake Drive. | Pavement Improvement | 2010-06-21 | 2010-06-21 | 2010-08-10 | 2010-09-14 | 350000 | 0.580 | 5053020
841 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5055155 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Magnolia Avenue from the south city limits to approximately 915 feet north of Ball Road | Pavement Improvement | 2010-04-05 | 2010-04-05 | 2010-03-01 | 2010-06-21 | 725390.09 | 0.670 | 5055155
842 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5055156 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: East Street from Santa Ana Street to Cypress Street | Pavement Improvement | 2010-03-22 | 2010-03-22 | 2010-04-22 | 2010-06-11 | 675796.83 | 0.460 | 5055156
843 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5055157 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Miraloma Avenue from 800 feet west of Tustin Avenue to the east city limits west of Van Buren Street | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-09-17 | 2010-08-06 | 493532.28 | 0.800 | 5055157
844 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5055158 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Broadway from East Street to Bond Street | Pavement Improvement | 2010-03-22 | 2010-03-22 | 2010-04-01 | 2010-05-24 | 276030 | 0.380 | 5055158
845 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | STATEWIDE | 47 | 5055159 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: Street pavement rehabilitation / reconstruction, including curb ramps, utility adjustmen | Pavement Improvement | 2011-02-09 | 2011-02-09 | 2011-03-22 | 2011-04-28 | 659712.58 | 0.600 | 5055159
846 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5055160 | This is a Pavement Resurfacing project by a local agency in the City of Anaheim. The project is described as: La Palma Avenue from Clementine Street to Anaheim Boulevard | Pavement Improvement | 2011-01-18 | 2011-01-18 | 2011-04-02 | 2011-02-23 | 506168 | 0.190 | 5055160
847 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO |  | 10 | 5056016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Dixon. The project is described as: North Almond Street from A street to H Street | Pavement Improvement | 2009-10-19 | 2009-10-20 | 2009-12-01 | 2010-02-23 | 299247.9 | 0.520 | 5056016
848 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | SANTA ROSA | 10 | 5056017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Dixon. The project is described as: Stratford Avenue between Pitt School Rd. and Weyand Way | Pavement Improvement | 2010-07-09 | 2010-07-12 | 2010-07-30 | 2010-08-24 | 148860.85 | 0.200 | 5056017
849 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5057032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Berkeley. The project is described as: University Ave. From San Pablo Ave. (SR-123) to Sacramento Streetan | Pavement Improvement | 2009-09-18 | 2009-09-24 | 2010-06-01 | 2010-05-21 | 1522313.39 | 0.560 | 5057032
850 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5057033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Berkeley. The project is described as: University Ave. Sacramento st. McGee Ave. | Pavement Improvement | 2010-02-05 | 2010-03-01 | 2010-06-30 | 2010-06-10 | 400000 | 0.260 | 5057033
851 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | SAN BERNARDINO-RIVERSIDE | 44 | 5058079 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Riverside. The project is described as: Alessandro Boulevard from Mission Grove Parkway to Sycamore Canyon Boulevard | Transportation Enhancements | 2009-12-21 | 2009-12-21 | 2010-04-09 | 2010-05-20 | 348176 | 1.000 | 5058079
852 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | Multiple | 5059160 | This is a Pavement Resurfacing project by a local agency in the City of Modesto. The project is described as: Various Streets segments throughout the City of Modesto | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2012-10-01 | 2012-08-14 | 2809187 | 30.000 | 5059160
853 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 19 | 5059166 | This is a Pavement Resurfacing project by a local agency in the City of Modesto. The project is described as: Various Streets within City of Modesto | Pavement Improvement | 2010-09-13 | 2010-11-03 | 2012-10-01 | 2012-08-08 | 3671452 | 10.000 | 5059166
854 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060165 | This is a Safety project by a local agency in the City of Fresno. The project is described as: Maple and Behymer Avenues Intersection | Pavement Improvement | 2010-05-07 | 2010-05-07 | 2010-08-03 | 2011-03-01 | 270683.15 | 1.000 | 5060165
855 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5060166 | This is a Traffic Management Engineering project by a local agency in the City of Fresno. The project is described as: Traffic Signal Installation @ intersection of Maple and Teague Avenues. | Pavement Improvement | 2010-05-25 | 2010-05-25 | 2010-10-29 | 2010-11-02 | 284377.58 | 1.000 | 5060166
856 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5060167 | This is a Traffic Management Engineering project by a local agency in the City of Fresno. The project is described as: Maple and Perrin Avenues Intersection | Pavement Improvement | 2010-04-02 | 2010-04-02 | 2010-08-03 | 2010-12-10 | 300000 | 1.000 | 5060167
857 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5060168 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Various AC Overlays/Reconstruction on Eligible Routes. Consistent with 40 CFR part 93.126 | Pavement Improvement | 2010-04-07 | 2010-05-24 | 2010-07-27 | 2010-08-20 | 663969.6 | 2.000 | 5060168
858 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5060169 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Divasdero Street between H Street to Clark Street | Pavement Improvement | 2010-07-22 | 2010-07-22 | 2010-10-29 | 2010-09-15 | 495025 | 1.000 | 5060169
859 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060170 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Shaw Avenue between Marks and Brawley Avenues | Pavement Improvement | 2010-07-08 | 2010-07-08 | 2010-10-25 | 2010-08-25 | 908021.33 | 1.500 | 5060170
860 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060171 | This is a Safety project by a local agency in the City of Fresno. The project is described as: Millbrook and Shepherd Avenues Intersection | Pavement Improvement | 2010-05-07 | 2010-05-07 | 2010-08-03 | 2011-03-03 | 222302.93 | 1.000 | 5060171
861 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060172 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Blackstone Avenue between Shaw and Minarets Avenues | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-07-29 | 2010-08-22 | 1522297.35 | 3.000 | 5060172
862 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060178 | This is a Safety project by a local agency in the City of Fresno. The project is described as: Marks and Emerson Avenues Intersection | Pavement Improvement | 2010-09-20 | 2010-09-20 | 2010-11-30 | 2011-06-02 | 375000 | 1.000 | 5060178
863 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060181 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Fresno. The project is described as: Friant Road between SR41and Shpherd Avenue | Pavement Improvement | 2010-05-28 | 2010-05-28 | 2010-10-29 | 2010-09-30 | 1158739.49 | 0.850 | 5060181
864 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5060183 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Fresno. The project is described as: Clovis Avenue from SR180 to McKinley Avenue | Transportation Enhancements | 2010-05-24 | 2010-05-24 | 2010-08-30 | 2010-08-20 | 114750.16 | 1.000 | 5060183
865 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5060185 | This is a Pavement Resurfacing project by a local agency in the City of Fresno. The project is described as: Blackstone Avenue from Olive to Belmont Avenues | Pavement Improvement | 2010-08-11 | 2010-08-11 | 2010-11-22 | 2010-09-30 | 298772.38 | 0.500 | 5060185
866 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5060189 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fresno. The project is described as: Lump-Sum Various AC Overlays/Reconstruction on Eligible Routes. Herndon from Cedar to Willow | Pavement Improvement | 2010-10-24 | 2010-10-24 | 2011-01-14 | 2011-01-07 | 1047000 |  | 5060189
867 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5060190 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fresno. The project is described as: Lump-Sum Various AC Overlays/Reconstruction on Eligible Routes. Cedar Ave from Clinton to Gettysburg | Pavement Improvement | 2011-08-30 | 2011-08-30 | 2011-10-28 | 2011-12-11 | 711635.41 |  | 5060190
868 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 19 | 5060191 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fresno. The project is described as: Lump-Sum Various AC Overlays/Reconstruction on Eligible Routes. Northbound Friant from Fresno to Champlain | Pavement Improvement | 2011-07-11 | 2011-07-11 | 2011-09-23 | 2011-10-28 | 563107.83 |  | 5060191
869 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5062013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Willows. The project is described as: Tehama Street from CR 53 to CR 57 | Pavement Improvement | 2010-06-14 | 2010-06-18 | 2010-05-31 | 2010-10-10 | 384095.42 | 0.500 | 5062013
870 | CALIFORNIA | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5062014 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Willows. The project is described as: Tehama Street between County Roads 57-59 | Transportation Enhancements | 2010-10-21 | 2010-11-01 | 2010-12-15 | 2010-11-19 | 83739.15 | 0.930 | 5062014
871 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5062015 | This is a Pavement Resurfacing project by a local agency in the City of Willows. The project is described as: Tehama Street overlay;Road maintenance | Pavement Improvement | 2010-10-18 | 2010-10-29 | 2010-10-29 | 2010-11-18 | 156993.86 |  | 5062015
872 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5062016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Willows. The project is described as: Tehama Street overlay (57 to south city limit); Road maintenance. | Pavement Improvement | 2010-10-18 | 2010-10-29 | 2010-10-29 | 2010-11-18 | 117460.58 |  | 5062016
873 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5063131 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Ana. The project is described as: McFadden Avenue from Maple Street to Standard Avenue | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2011-06-01 | 2010-07-02 | 634368 | 0.400 | 5063131
874 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5063132 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Ana. The project is described as: McFadden Avenue from Bristol Street to Flower Street. | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2011-06-01 | 2010-07-02 | 599048 | 0.500 | 5063132
875 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5063133 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Ana. The project is described as: Civic Center Drive from French Street to Santiago Street | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2011-06-01 | 2010-07-02 | 632035 | 0.400 | 5063133
876 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5063138 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Ana. The project is described as: Lyon Street: Edinger Ave. to Chestnut Ave;Roadway Rehabilitation Non-capacity Adding | Pavement Improvement | 2010-10-18 | 2010-10-18 | 2011-02-01 | 2011-03-11 | 677253 | 1.100 | 5063138
877 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5064061 | This is a Pavement Resurfacing project by a local agency in the City of Pasadena. The project is described as: VARIOUS LOCATIONS | Pavement Improvement | 2010-04-12 | 2010-04-16 | 2010-08-16 | 2011-04-30 | 4331000 | 9.800 | 5064061
878 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5067014 | This is a Traffic Management Engineering project by a local agency in the City of Los Gatos. The project is described as: University Avenue & Blossom Hill Road Intersection | Safety/Traffic Management | 2009-07-20 | 2010-01-04 | 2010-05-14 | 2010-06-21 | 452553.9 | 0.250 | 5067014
879 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5067015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Gatos. The project is described as: Prospect Avenue, Prospect Ct, Ambassador Ct Street Resurfacing | Pavement Improvement | 2010-04-06 | 2010-04-19 | 2010-07-01 | 2010-06-21 | 173874.42 | 0.500 | 5067015
880 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA | REDDING | 02 | 5068028 | This is a New Construction Roadway project by a local agency in the City of Redding. The project is described as: Oasis Rd/ I5 Interchange in City of Redding | Pavement Widening | 2010-07-12 | 2010-07-15 | 2011-07-31 | 2011-11-09 | 2746952 | 0.100 | 5068028
881 | CALIFORNIA | Completed | C250,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5068029 | This is a Pavement Resurfacing project by a local agency in the City of Redding. The project is described as: Cypress Ave, Hartnell Ave, Victor Ave and Hilltop Dr | Pavement Improvement | 2010-09-09 | 2010-09-20 | 2010-10-29 | 2010-11-12 | 849765 | 6.050 | 5068029
882 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 28 | 5069009 | This is a Pavement Resurfacing project by a local agency in the City of Monrovia. The project is described as: Various City Streets | Pavement Improvement | 2011-03-14 | 2011-03-28 | 2011-06-30 | 2011-06-30 | 995000 | 4.400 | 5069009
883 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 28 | 5069011 | This is a Traffic Management Engineering project by a local agency in the City of Monrovia. The project is described as: Intersections of Myrtle Ave & Chesnut Ave and Myrtle Ave & Huntington Dr | Pavement Improvement | 2010-11-17 | 2011-01-10 | 2011-05-24 | 2011-05-05 | 160999.99 | 1.000 | 5069011
884 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5070017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pomona. The project is described as: White Ave: Orange Grove to North City Limits | Pavement Improvement | 2011-12-22 | 2010-04-05 | 2010-07-20 | 2010-07-20 | 2699039.09 | 1.500 | 5070017
885 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5070018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pomona. The project is described as: Towne Ave Road: Lexington Avenue to Riverside Drive | Pavement Improvement | 2010-02-08 | 2010-04-05 |  | 2010-06-25 | 1016990.63 | 1.250 | 5070018
886 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5071018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South Pasadena. The project is described as: Fair Oaks Ave. Corridor and Columbia St. | Safety/Traffic Management | 2010-10-12 | 2010-10-25 | 2012-03-15 | 2012-03-15 | 761000 | 1.300 | 5071018
887 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | 5072047 | This is a Traffic Management Engineering project by a local agency in the City of Tulare. The project is described as: Prosperity Avenue from Cherry St. to Oaks St. | Pavement Improvement | 2010-07-20 | 2010-08-16 | 2010-09-28 | 2011-02-15 | 333000 | 0.600 | 5072047
888 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5072048 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Tulare. The project is described as: Santa Fe Bike/Pedestrian trail between W. Street and E. Street. | Transportation Enhancements | 2010-07-26 | 2010-08-02 | 2010-10-19 | 2011-05-17 | 186616.87 | 1.000 | 5072048
889 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5073062 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Orange. The project is described as: Chapman Avenue from Main Street to 300 feet east of Pixley Street and from Hewes Street to 100 feet east of Cannon Street | Pavement Improvement | 2010-05-17 | 2010-07-12 | 2010-10-10 | 2010-12-14 | 1465302.32 | 1.170 | 5073062
890 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5073065 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Orange. The project is described as: Santiago Creek Bike Trail from Tustin Street to Collins Avenue | Transportation Enhancements | 2010-09-08 | 2010-10-04 | 2011-09-02 | 2011-12-13 | 1889000 | 2.000 | 5073065
891 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LAKE |  | 01 | 5076007 | This is a Pavement Resurfacing project by a local agency in the City of Lakeport. The project is described as: Forbes Street between Martin St and Clearlake Ave | Pavement Improvement | 2010-04-15 | 2010-04-15 | 2010-07-20 | 2010-07-23 | 643449 | 0.660 | 5076007
892 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5078030 | This is a Pavement Resurfacing project by a local agency in the City of Compton. The project is described as: Various City Streets | Pavement Improvement | 2010-03-30 | 2010-04-12 | 2010-06-30 | 2010-06-02 | 552218.83 | 14.000 | 5078030
893 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5078031 | This is a Pavement Resurfacing project by a local agency in the City of Compton. The project is described as: Greenleaf Blvd: Long Beach Blvd and Central Ave, Santa Fe Ave: Alondra Blvd and Stockton St. | Pavement Improvement | 2010-03-30 | 2010-04-12 | 2010-07-20 | 2010-10-01 | 2004000 | 4.300 | 5078031
894 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | LOMPOC | 24 | 5080019 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Lompoc. The project is described as: In the city of Lompoc from north of the Santa Ynez River Bridge to Allan Hancock College. Construct class I bicycle path. | Transportation Enhancements | 2010-09-27 | 2010-09-27 | 2010-12-27 | 2011-04-29 | 568036 | 1.000 | 5080019
895 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | LOMPOC | 24 | 5080021 | This is a Pavement Resurfacing project by a local agency in the City of Lompoc. The project is described as: City of Lompoc V St, College Ave, 7th St, O St and North Ave | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2009-12-17 | 2009-11-25 | 682161 | 2.700 | 5080021
896 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | LOMPOC | 24 | 5080022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lompoc. The project is described as: In the City of Lompoc on Various Streets | Pavement Improvement | 2010-08-30 | 2010-08-30 | 2010-12-03 | 2010-11-23 | 1113464 | 1.900 | 5080022
897 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5082057 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Willits. The project is described as: West Commercial Street | Pavement Improvement | 2010-07-09 | 2010-07-19 | 2010-11-29 | 2010-11-29 | 432285 | 0.200 | 5082057
898 | CALIFORNIA | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | 5084015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Paso De Robles. The project is described as: Theatre Drive - 46W/101 | New Construction | 2010-10-12 | 2010-10-22 | 2012-12-31 |  | 2860000 | 0.750 | 5084015
899 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED | MERCED | 18 | 5085019 | This is a Pavement Resurfacing project by a local agency in the City of Merced. The project is described as: 16th street Overlay from G Street to V street | Pavement Improvement | 2010-03-03 | 2010-03-15 | 2010-05-01 | 2010-07-22 | 1402602.09 | 2.500 | 5085019
900 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED | MERCED | 18 | 5085020 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Merced. The project is described as: G Street,M Street,18th Steet ,Small portion of N Street, Canal Street,and Canal Street. | Pavement Improvement | 2010-12-15 | 2011-01-03 | 2012-04-30 | 2011-11-23 | 2395714.37 | 2.150 | 5085020
901 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5086029 | This is a Pavement Resurfacing project by a local agency in the City of Monterey. The project is described as: Munras, Soledad and El Dorado Street Rehab | Pavement Improvement | 2009-08-31 | 2009-09-14 | 2010-05-31 | 2010-04-30 | 602716 | 1.000 | 5086029
902 | CALIFORNIA | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | 5086030 | This is a Safety project by a local agency in the City of Monterey. The project is described as: Del Monte and Figueroa Signal Improvements | Safety/Traffic Management | 2010-01-04 | 2010-01-11 | 2010-07-31 | 2010-08-01 | 375000 | 1.000 | 5086030
903 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5087027 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Pacific Grove. The project is described as: Sidewalk and storm drain improvements | Transportation Enhancements | 2009-11-10 | 2009-11-18 | 2010-03-01 | 2010-04-16 | 303000 | 1.000 | 5087027
904 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5088020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fort Bragg. The project is described as: Pudding Creek Rd. Reconstruction | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2010-07-09 | 2010-07-12 | 206820.64 | 0.250 | 5088020
905 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5088021 | This is a Pavement Resurfacing project by a local agency in the City of Fort Bragg. The project is described as: Harold St: Laurel St to Fir St and Dana St: Oak St to Chestnut | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-07-29 | 2010-08-06 | 413674.58 | 0.600 | 5088021
906 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5088024 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Fort Bragg. The project is described as: Laurel St. between Harold St. & Morrow St., Pine St. beween Corry St. & Whipple St. | Transportation Enhancements | 2010-07-28 | 2010-07-28 | 2010-09-09 | 2010-09-30 | 87704 | 0.180 | 5088024
907 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS | HANFORD | 20 | 5091037 | This is a Pavement Resurfacing project by a local agency in the City of Hanford. The project is described as: On Hanford-Armona Road, from 11th to Greenbriar Dr. | Pavement Improvement | 2009-10-12 | 2009-10-12 | 2010-04-01 | 2010-06-30 | 630433 | 1.000 | 5091037
908 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS | HANFORD | 20 | 5091040 | This is a Pavement Resurfacing project by a local agency in the City of Hanford. The project is described as: On 11th Ave, from 3rd Ave to Ivy St. | Pavement Improvement | 2010-05-31 | 2010-05-31 | 2010-08-01 | 2010-09-21 | 692231 | 1.000 | 5091040
909 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS | HANFORD | 20 | 5091044 | This is a Traffic Management Engineering project by a local agency in the City of Hanford. The project is described as: On Douty St, from Cortner St to Windsor Dr. | Pavement Improvement | 2010-05-31 | 2010-05-31 | 2010-08-15 | 2010-09-21 | 458016 | 1.000 | 5091044
910 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5093013 | This is a Pavement Resurfacing project by a local agency in the City of Redondo Beach. The project is described as: Inglewood Av: Artesia Bl to Manhattan Beach Bl | Pavement Improvement | 2009-10-12 | 2009-10-19 | 2010-01-01 | 2010-04-20 | 1000904.65 | 1.000 | 5093013
911 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5093014 | This is a Pavement Resurfacing project by a local agency in the City of Redondo Beach. The project is described as: Prospect Ave: Palos Verdes Blvd. to 190th St | Pavement Improvement | 2010-08-17 | 2010-08-20 | 2010-11-30 | 2010-11-24 | 920000 | 2.500 | 5093014
912 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VACAVILLE | 07 | 5094049 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Vacaville. The project is described as: Peabody Rd. and Marshall Rd. Intersection | Safety/Traffic Management | 2009-06-12 | 2009-06-15 | 2009-11-01 | 2009-11-10 | 260000 | 0.270 | 5094049
913 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VACAVILLE | 07 | 5094052 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Vacaville. The project is described as: Various Street | Pavement Improvement | 2009-09-23 | 2009-10-01 | 2010-05-01 | 2010-09-29 | 1376000 | 4.700 | 5094052
914 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | VACAVILLE | 07 | 5094053 | This is a Traffic Management Engineering project by a local agency in the City of Vacaville. The project is described as: Various Locations in City of Vacaville | Safety/Traffic Management | 2009-10-30 | 2010-02-22 | 2010-05-14 | 2010-06-01 | 320000 | 0.000 | 5094053
915 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5095013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rocklin. The project is described as: Sunset Blvd from Blue Oaks Blvd to Atherton Road | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2009-12-01 | 2009-12-10 | 1289206 | 1.000 | 5095013
916 | CALIFORNIA | Completed | C220,C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5097007 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Ferndale. The project is described as: Rose Ave: Berding to McKinley, and Herbert St: Rose to Dewey | Transportation Enhancements | 2011-12-22 | 2012-01-03 | 2012-04-06 | 2012-04-06 | 400000 | 0.690 | 5097007
917 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5100011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palo Alto. The project is described as: Lytton Avenue Road Rehabilitation | Pavement Improvement | 2009-11-10 | 2009-11-16 | 2010-03-31 | 2010-03-31 | 580000 | 0.600 | 5100011
918 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5100012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palo Alto. The project is described as: San Antonio Avenue Road Rehab | Pavement Improvement | 2009-12-04 | 2009-12-07 | 2010-01-27 | 2010-01-27 | 505000 | 1.700 | 5100012
919 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5100013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palo Alto. The project is described as: Alma Street (Colorado Ave south to East Meadow Dr) | Pavement Improvement | 2010-06-29 | 2010-08-09 | 2010-09-30 | 2010-09-23 | 209000 | 1.100 | 5100013
920 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 10 | 5101022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasanton. The project is described as: Resurface portions of Stoneridge Drive and Santa Rita Rd. | Pavement Improvement | 2009-09-15 | 2009-10-22 | 2010-06-01 | 2010-08-17 | 1047410.32 | 1.200 | 5101022
921 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | Multiple | 5101023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasanton. The project is described as: On Bernal Ave from Valley Ave to Pleasanton Ave | Pavement Improvement | 2010-05-03 | 2010-05-10 | 2010-06-23 | 2010-07-07 | 370000 | 1.000 | 5101023
922 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 11 | 5101024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasanton. The project is described as: Santa Rite Road- from Valley Ave. to Jensen Street, | Pavement Improvement | 2010-06-25 | 2010-07-08 | 2010-08-30 | 2010-08-26 | 371289 | 0.700 | 5101024
923 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5102034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Mateo. The project is described as: Various Street | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2010-01-01 | 2010-04-01 | 1095000 | 4.000 | 5102034
924 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5102035 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Mateo. The project is described as: Crystal Springs, Santa Inez, Delaware, Campus | Pavement Improvement | 2010-07-27 | 2010-07-27 | 2010-10-01 | 2011-03-14 | 452000 | 2.000 | 5102035
925 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5102036 | EL CAMINO REAL, CONCAR, HILLSDALE, DELAWARE, SARATOGA, INSTALL ITS ELEMENTS | Safety/Traffic Management | 2010-10-04 | 2010-10-04 | 2012-11-30 |  | 1000000 |  | 5102036
926 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5107021 | This is a Pavement Resurfacing project by a local agency in the City of Santa Monica. The project is described as: Santa Monica Blvd: Cloverfield Blvd to Centinela Av | Pavement Improvement | 2010-01-05 | 2010-01-05 | 2010-02-01 | 2011-03-04 | 549129.13 | 0.700 | 5107021
927 | CALIFORNIA | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5107022 | This is a Pavement Resurfacing project by a local agency in the City of Santa Monica. The project is described as: CITYWIDE STREETS IN SANTA MONICA | Pavement Improvement | 2010-01-04 | 2010-01-05 | 2010-04-01 | 2011-03-04 | 1870221.47 | 5.500 | 5107022
928 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108094 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: Spring St: Clark Ave to ECL | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2010-10-15 | 2010-06-04 | 3028790 | 4.500 | 5108094
929 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108095 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: Harding St: DeForest Ave to Atlantic Ave | Pavement Improvement | 2010-01-19 | 2010-01-19 | 2010-06-01 | 2010-05-18 | 229342 | 4.500 | 5108095
930 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108096 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: California Av: Harding St to Artesia Bl | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2010-06-01 | 2010-06-07 | 487632.99 | 4.500 | 5108096
931 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108097 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: Carson St: Long Beach Blvd to Atlantic Ave | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2010-06-01 | 2010-05-28 | 634018 | 4.500 | 5108097
932 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108103 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: Rehabilitation of various streets which includes asphalt pavement, damaged curb and gutter, etc. | Pavement Improvement | 2010-07-26 | 2010-07-26 | 2010-12-31 | 2010-09-09 | 309000.03 | 4.500 | 5108103
933 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108107 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: Rehabilitation of various streets which includes asphalt pavement, damaged curb and gutter, etc. | Pavement Improvement | 2010-07-26 | 2010-09-13 | 2010-12-31 | 2010-10-18 | 911464.66 | 4.500 | 5108107
934 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108109 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: Rehabilitation of various streets which includes asphalt pavement, damaged curb and gutter, etc. | Pavement Improvement | 2010-07-13 | 2010-07-13 | 2010-12-31 | 2010-09-09 | 272694.81 | 4.500 | 5108109
935 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108112 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: Rehabilitation of various streets which includes asphalt pavement, damaged curb and gutter, etc. | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-12-31 | 2011-03-25 | 1418027.55 | 4.500 | 5108112
936 | CALIFORNIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5108115 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Long Beach. The project is described as: Custom bicycle racks and protected bicycle parking for installation throughout the city. | Transportation Enhancements | 2010-03-15 | 2010-03-15 | 2011-01-01 | 2011-04-30 | 837764 | 1.000 | 5108115
937 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108124 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Long Beach. The project is described as: Rehabilitation of various streets which includes asphalt pavement, damaged curb and gutter, etc. | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2010-12-31 | 2011-04-15 | 3644332.31 | 4.500 | 5108124
938 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5108127 | WARDLOW ROAD: BETWEEN CLARK AVENUE AND PALO VERDE AVENUE, ROAD REHABILITATON | Pavement Improvement | 2010-10-25 | 2010-10-25 | 2011-01-31 | 2011-05-09 | 1502201.3 |  | 5108127
939 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5108129 | PARAMOUNT BLVD: ARTESIA BLVD TO CANDLEWOOD ST, ROAD REHABILITATION | Pavement Improvement | 2011-06-06 | 2011-06-06 | 2011-08-29 | 2011-10-31 | 852942 |  | 5108129
940 | CALIFORNIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5108132 | CITYWIDE PARKING EQUIPMENT, BICYCLE RELATED | Transportation Enhancements | 2012-01-09 | 2012-01-15 | 2012-06-30 | 2012-04-27 | 92584 |  | 5108132
941 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109153 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Wilson Rd (White lane to Planz Rd), Hughes Lane (White Lane to Planz Rd), Wible Rd (White lane to Pacheco Rd) | Other | 2009-09-02 | 2009-09-17 | 2010-04-30 | 2010-05-10 | 1717761.87 | 1.560 | 5109153
942 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109154 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Mount Vernon Avenue from SR 178 to University Avenue | Other | 2009-09-03 | 2009-09-08 | 2009-11-01 | 2010-02-26 | 1733374.47 | 0.700 | 5109154
943 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109155 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Ashe Road from White Lane to Ming Ave | Other | 2009-09-02 | 2009-09-17 | 2009-11-01 | 2010-02-17 | 1473715.42 | 1.120 | 5109155
944 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109157 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Coffee Road from Friant Kern Canal to Riverlakes Drive-Meany Drive & Coffee Road from Olive Drive to Norris Road | Pavement Improvement | 2010-04-21 | 2010-05-03 | 2010-06-25 | 2010-06-29 | 1538102.43 | 0.900 | 5109157
945 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5109158 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bakersfield. The project is described as: Ming Avenue from Gosford Road to Ashe Road and from Ashe Road to New Stine Road | Pavement Improvement | 2010-04-22 | 2010-05-03 | 2010-08-04 | 2010-08-06 | 4283184.22 | 1.860 | 5109158
946 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 02 | 5110027 | This is a Safety project by a local agency in the City of Winters. The project is described as: Grant Avenue Safety Improvements | Pavement Improvement | 2009-09-01 | 2009-09-01 | 2009-12-01 | 2009-11-10 | 334955.14 | 1.000 | 5110027
947 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111046 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Whittier. The project is described as: GREENLEAF AVE FROM WHITTIER BL TO SOUTH CITY LIMITS | Pavement Improvement | 2010-06-04 | 2010-06-21 | 2010-10-12 | 2010-10-12 | 581521.5 | 1.000 | 5111046
948 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111049 | This is a Safety project by a local agency in the City of Whittier. The project is described as: Santa Gertrudes Ave at Starbuck Street | Safety/Traffic Management | 2010-04-20 | 2010-08-02 | 2010-10-11 | 2010-11-09 | 161230.83 | 1.000 | 5111049
949 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111052 | This is a Safety project by a local agency in the City of Whittier. The project is described as: PAINTER AVE FROM HADLEY STREET TO BEVERLY BLVD AND RAMONA DRIVE EAST OF PAINTER AVE | Other | 2010-03-10 | 2010-06-01 | 2011-03-08 | 2011-03-08 | 229794.64 | 1.000 | 5111052
950 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111053 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Whittier. The project is described as: LAUREL AVE. FROM WHITTIER BLVD. TO LAMBERT ROAD. | Pavement Improvement | 2010-06-04 | 2010-06-21 | 2010-10-12 | 2010-10-12 | 360673 | 1.000 | 5111053
951 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111054 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Whittier. The project is described as: LA CUARTA STREET FROM WHITTIER BLVD TO COLLEGE AVE | Pavement Improvement | 2011-04-25 | 2011-05-02 | 2011-09-09 | 2011-08-24 | 760000 | 1.000 | 5111054
952 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111055 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Whittier. The project is described as: SLAUSON AVE./ MULBERRY DRIVE FROM WEST CITY LIMITS AT CHETLE AVE. TO EAST CITY LIMITS EAST OF GREENLEAF AVE. | Pavement Improvement | 2010-06-04 | 2010-06-21 | 2010-10-12 | 2010-10-12 | 218805.75 | 1.000 | 5111055
953 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5111056 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Whittier. The project is described as: INTERSECTION OF MAR VISTA ST AND CALIFORNIA AVE | Pavement Improvement | 2010-04-19 | 2010-05-03 | 2010-06-01 | 2010-05-20 | 70058 | 1.000 | 5111056
954 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5112010 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Azusa. The project is described as: Foothill Blvd from Todd Ave to Orange Ave | Pavement Improvement | 2009-09-23 | 2009-09-28 | 2010-01-08 | 2010-01-22 | 879841 | 0.700 | 5112010
955 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5112012 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Azusa. The project is described as: Citrus Ave: Alosta St to the Northerly City Limits | Pavement Improvement | 2010-06-30 | 2010-07-12 | 2010-08-27 | 2011-01-18 | 540000 | 1.000 | 5112012
956 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5113010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Mill Valley. The project is described as: In Mill Valley at Edgewood Avenue between Marion Avenue and Sequoia Valley Road. | Pavement Improvement | 2009-10-22 | 2009-10-26 | 2009-11-25 | 2009-11-25 | 265521.6 | 0.360 | 5113010
957 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | Multiple | 5114014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sonoma. The project is described as: 5TH STREET WEST FROM W. NAPA ST. TO WEST MACARTHUR STREET | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2010-01-12 | 2010-01-12 | 500000 | 0.530 | 5114014
958 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5115019 | This is a Pavement Resurfacing project by a local agency in the City of Lemoore. The project is described as: Hanford-Armona Rd. btwn. SR41 and 19th Ave. and Liberty Dr. to 18th Ave (N Lemoore Ave). | Pavement Improvement | 2009-10-19 | 2009-10-21 | 2009-12-01 | 2009-12-01 | 396422.92 | 1.000 | 5115019
959 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5115021 | This is a Pavement Resurfacing project by a local agency in the City of Lemoore. The project is described as: Lemoore Avenue from Cinnamon Drive to Glendale Avenue | Pavement Improvement | 2010-07-27 | 2010-07-28 | 2010-08-16 | 2010-08-27 | 355601.19 | 1.000 | 5115021
960 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LASSEN |  | 04 | 5116013 | This is a Pavement Resurfacing project by a local agency in the City of Susanville. The project is described as: Cherry Terrace, Glenn Drive, Numa Road | Pavement Improvement | 2010-11-09 | 2010-11-24 | 2012-07-30 | 2012-07-18 | 740720 | 1.200 | 5116013
961 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5117008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hercules. The project is described as: San Pablo Ave. | Pavement Improvement | 2009-10-29 | 2009-10-29 | 2010-04-30 | 2010-04-27 | 576927.55 | 0.830 | 5117008
962 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5118014 | This is a Pavement Resurfacing project by a local agency in the City of Covina. The project is described as: Citywide Various Locations | Pavement Improvement | 2009-12-02 | 2009-12-02 | 2010-02-01 | 2010-02-01 | 839828.94 | 2.650 | 5118014
963 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5121017 | This is a Pavement Resurfacing project by a local agency in the City of Santa Paula. The project is described as: 8 TH ST: HARVARD BL TO SANTA PAULA ST | Pavement Improvement | 2009-10-14 | 2009-10-14 | 2010-01-01 | 2010-02-22 | 254000 | 1.000 | 5121017
964 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | THOUSAND OAKS | 24 | 5121019 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Paula. The project is described as: Peck Road from Faulkner Road to Harvard Blvd | Pavement Improvement | 2010-11-10 | 2011-01-03 | 2011-05-26 | 2011-05-26 | 242008 | 0.500 | 5121019
965 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE | PORTERVILLE | 21 | 5122062 | This is a Pavement Resurfacing project by a local agency in the City of Porterville. The project is described as: On Olive Ave, from Main St. to H St. | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2010-07-20 | 2010-07-22 | 318981 | 0.850 | 5122062
966 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5123014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sebastopol. The project is described as: Bodega Ave., Ragel Rd., Pleasant Hill Ave. N., valentine Ave., Covert Ln., Jewell Ave. | Pavement Improvement | 2009-11-10 | 2009-11-23 | 2009-12-01 | 2010-08-10 | 601341.42 | 0.830 | 5123014
967 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5124027 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Mountain View. The project is described as: Moffett, Castro, Franklin | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2010-02-01 | 2010-03-23 | 720325.74 | 0.860 | 5124027
968 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | 5125022 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bishop. The project is described as: Hanby Avenue from East Line Street to East Pine Street | Pavement Improvement | 2009-08-28 | 2009-09-01 | 2010-07-01 | 2010-08-31 | 379417.95 | 0.200 | 5125022
969 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5126010 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Pinole. The project is described as: San Pablo Ave. | Pavement Improvement | 2009-10-22 | 2010-03-15 | 2010-05-15 | 2010-04-26 | 180375.48 | 1.000 | 5126010
970 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5126012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pinole. The project is described as: Appian Way from San Bablo to Tara Hill | Pavement Improvement | 2009-09-23 | 2009-09-23 | 2009-11-01 | 2010-10-20 | 420000 | 0.600 | 5126012
971 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | ANTIOCH-PITTSBURGH | 07 | 5127023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pittsburg. The project is described as: Pittsburg Pavement Rehab. | Pavement Improvement | 2009-09-25 | 2009-10-19 | 2010-01-01 | 2010-01-02 | 1103000 | 1.020 | 5127023
972 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5129053 | This is a Pavement Resurfacing project by a local agency in the City of Oxnard. The project is described as: Hemlock Street: J Street to Ventura Road & J Street: Wooley Road to Hemlock Street. | Pavement Improvement | 2010-05-13 | 2010-05-24 | 2010-07-15 | 2010-10-25 | 765229.8 | 1.000 | 5129053
973 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | Multiple | 5129054 | This is a Traffic Management Engineering project by a local agency in the City of Oxnard. The project is described as: VARIOUS LOCATIONS IN THE CITY OF OXNARD | Safety/Traffic Management | 2009-11-02 | 2009-11-02 | 2010-03-01 | 2010-06-17 | 681146.74 | 1.000 | 5129054
974 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5129055 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oxnard. The project is described as: J street: Wooley Road to Hemlock and Hill Street: I Street to N Street. | Pavement Improvement | 2009-10-13 | 2009-10-24 | 2010-03-31 | 2010-03-31 | 917300.49 | 0.900 | 5129055
975 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | STATEWIDE | 23 | 5129058 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Oxnard. The project is described as: Route 101 at Rice Ave/Santa Clara Ave Intersection Improvement. | Pavement Widening | 2009-11-18 | 2009-11-18 | 2012-12-30 | 2010-12-31 | 5000000 | 1.000 | 5129058
976 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5130014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alhambra. The project is described as: Alhambra Rd from 200' e/o Alahmar St to Huntington Dr | Pavement Improvement | 2010-08-04 | 2010-08-04 | 2010-11-04 | 2011-03-17 | 1146474.9 | 2.500 | 5130014
977 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5130015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alhambra. The project is described as: Poplar Blvd. from Fremont Ave to Winchester Ave (City Boundary West) | Pavement Improvement | 2010-04-29 | 2010-05-13 | 2010-06-30 | 2010-06-28 | 202318.98 | 0.600 | 5130015
978 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5130016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Alhambra. The project is described as: New Ave from Adams Street to I-10 Fwy (City Boundary South) | Pavement Improvement | 2011-03-28 | 2011-03-28 | 2011-06-30 | 2011-07-01 | 1242510.46 | 0.750 | 5130016
979 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5131014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arcadia. The project is described as: Duarte Road between El Monte Ave & Santa Anita Ave. | Pavement Improvement | 2010-10-08 | 2010-10-11 | 2010-07-01 | 2011-01-04 | 299957.99 | 0.500 | 5131014
980 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5131015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arcadia. The project is described as: Santa Anita Ave. from Grand View Ave. to Foothill Blvd. | Pavement Improvement | 2009-12-14 | 2009-12-29 | 2010-03-17 | 2010-03-26 | 757000 | 1.100 | 5131015
981 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5131016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arcadia. The project is described as: Santa Anita Ave/ Longden Ave & Live Oak Ave | Pavement Improvement | 2009-09-29 | 2009-10-01 | 2009-12-01 | 2010-01-05 | 574528.78 | 0.500 | 5131016
982 | CALIFORNIA | Underway | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | SAN FRANCISCO-OAKLAND, CA | 10 | 5132032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: McGary Road from Lynch Canyon Rd. to Red Top Rd. | Transportation Enhancements | 2010-05-10 | 2010-05-10 | 2013-10-25 |  | 1603000 | 2.000 | 5132032
983 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | FAIRFIELD | 10 | 5132033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: Gateway Blvd. from travis Blvd. to Pennsylvania Ave. | Pavement Improvement | 2009-10-11 | 2009-11-12 | 2010-04-23 | 2010-07-20 | 647711.94 | 0.700 | 5132033
984 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | FAIRFIELD | 10 | 5132034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: E. Tabor Ave. from Villa Ct. to Walters Rd. | Pavement Improvement | 2009-10-26 | 2009-11-09 | 2010-04-16 | 2010-08-13 | 441890.67 | 0.800 | 5132034
985 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO | CONCORD | 10 | 5132036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfield. The project is described as: Suisun Valley Rd. from Mangels Blvd. to Fairfield City limits | Pavement Improvement | 2010-06-07 | 2010-06-22 | 2010-10-01 | 2010-11-04 | 502905.07 | 0.700 | 5132036
986 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5133038 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Fullerton. The project is described as: Harbor Boulevard from Chapman Avenue to Berkeley Avenue | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-06-18 | 2010-06-25 | 995873.52 | 0.350 | 5133038
987 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5134006 | This is a Pavement Resurfacing project by a local agency in the City of Imperial. The project is described as: Barioni Rd. between B St. and P St. | Pavement Improvement | 2010-07-28 | 2010-07-30 | 2010-12-10 | 2011-01-18 | 895000 | 1.000 | 5134006
988 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5135036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Concord. The project is described as: Clayton Rd. Rehab. | Pavement Improvement | 2009-10-03 | 2009-10-05 | 2009-12-09 | 2010-12-07 | 1110922.64 | 1.200 | 5135036
989 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 07 | 5135037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Concord. The project is described as: Clayton Rd. Intersection Improvements | Pavement Improvement | 2009-09-10 | 2009-09-14 | 2009-10-30 | 2010-12-07 | 584000 | 0.500 | 5135037
990 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 07 | 5135038 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Concord. The project is described as: On Monument Blvd between Victory land and Oak Grove Road, and Meadow Lane between Sunshine Drive and Monument Blvd | Transportation Enhancements | 2010-04-16 | 2010-04-19 | 2012-07-16 | 2012-04-03 | 370701 | 1.200 | 5135038
991 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5137037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Richmond. The project is described as: Carlson Blvd. | Pavement Improvement | 2010-02-10 | 2010-05-03 | 2010-11-30 | 2012-03-30 | 1578000 | 0.800 | 5137037
992 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138033 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Maria. The project is described as: In the City of Santa Maria on Various Streets - Phase I | Pavement Improvement | 2010-04-26 | 2010-04-26 |  | 2010-08-10 | 1657050 | 4.100 | 5138033
993 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138035 | This is a Pavement Resurfacing project by a local agency in the City of Santa Maria. The project is described as: In the City of Santa Maria on Various Streets - Phase II | Pavement Improvement | 2010-02-22 | 2010-02-22 |  | 2010-06-14 | 1135112.88 | 2.600 | 5138035
994 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138036 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Maria. The project is described as: In the City of Santa Maria - Concrete Repair Work Phase I | Transportation Enhancements | 2010-10-08 | 2010-10-08 |  | 2011-02-07 | 196001 | 1.780 | 5138036
995 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138037 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Maria. The project is described as: In the City of Santa Maria - Concrete Repair Work Phase II | Transportation Enhancements | 2010-04-07 | 2010-04-07 |  | 2010-07-28 | 301554 | 1.000 | 5138037
996 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138038 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Santa Maria. The project is described as: In the City of Santa Maria - Concrete Repair Work Phase III | Transportation Enhancements | 2010-03-03 | 2010-03-03 |  | 2010-07-16 | 232089 | 1.070 | 5138038
997 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA MARIA | 23 | 5138041 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Santa Maria. The project is described as: City of Santa Maria- Lump- sum chip seal and street lighting project | Pavement Improvement | 2011-06-14 | 2011-07-13 | 2011-12-23 | 2011-12-23 | 557519 |  | 5138041
998 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 34 | 5139011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Vernon. The project is described as: 26 th St: Alameda St to Downey Rd | Pavement Improvement | 2011-02-02 | 2011-02-07 | 2011-05-25 | 2011-09-03 | 500000 | 2.000 | 5139011
999 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 04 | 5142030 | This is a Pavement Resurfacing project by a local agency in the City of Oroville. The project is described as: Table Mountain Blvd & Grand Ave | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2010-02-10 | 2010-02-10 | 1052369.75 | 2.000 | 5142030
1000 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 04 | 5142031 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Oroville. The project is described as: Hwy 70/Montgomery St Beautification ARRA TE project. | Transportation Enhancements | 2010-09-07 | 2010-09-13 | 2011-10-14 | 2011-10-03 | 211529.23 | 0.200 | 5142031
1001 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144047 | This is a Safety project by a local agency in the City of Glendale. The project is described as: Monterey Rd. at intersections of GenevaSt., Jackson St., Louise St. | Pavement Improvement | 2009-12-07 | 2010-01-25 | 2010-05-06 | 2010-11-01 | 616600 | 0.340 | 5144047
1002 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144048 | This is a Pavement Resurfacing project by a local agency in the City of Glendale. The project is described as: Pacific Ave: Colorado St to San Fernando Rd & Allen Ave: Glenwood Rd to San Fernando Rd | Pavement Improvement | 2010-03-15 | 2010-03-29 | 2010-06-28 | 2010-07-16 | 1233076.11 | 0.820 | 5144048
1003 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144049 | This is a Traffic Management Engineering project by a local agency in the City of Glendale. The project is described as: Southern Portion of Glendale, 52 Locations | Pavement Improvement | 2009-12-07 | 2010-01-25 | 2010-05-06 | 2010-06-30 | 149353.3 | 1.000 | 5144049
1004 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144050 | This is a Safety project by a local agency in the City of Glendale. The project is described as: Central Ave @ Maple St, Chevy Chase Dr @ Harvard St, Wilson Ave @ Sinclair Ave | Pavement Improvement | 2010-01-26 | 2010-02-01 | 2010-07-01 | 2010-11-03 | 609463.63 | 1.000 | 5144050
1005 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144051 | This is a Pavement Resurfacing project by a local agency in the City of Glendale. The project is described as: Chevy Chase Drive.: Wilson Ave to Adams St | Pavement Improvement | 2010-04-05 | 2010-04-05 | 2010-06-28 | 2010-12-07 | 895000 | 1.100 | 5144051
1006 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144052 | This is a Traffic Management Engineering project by a local agency in the City of Glendale. The project is described as: North City of Glendale, Various Locations | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2010-03-01 | 2010-06-30 | 318042.05 | 1.000 | 5144052
1007 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5144055 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Glendale. The project is described as: 13 Locations: GlenoaksBlvd : Allen Ave to Harvey Dr. | Safety/Traffic Management | 2011-01-03 | 2011-01-10 | 2011-08-08 | 2012-01-27 | 2198146 | 1.000 | 5144055
1008 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5145011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fortuna. The project is described as: Fortuna Blvd (Main St to Newburg) | Pavement Improvement | 2010-08-09 | 2010-08-16 | 2011-02-28 | 2011-05-18 | 971730.12 | 0.500 | 5145011
1009 | CALIFORNIA | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5146009 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Coalinga. The project is described as: Cherry Lane and Elm Avenue (SH33/198) | New Construction | 2010-06-22 | 2010-07-26 | 2010-09-23 | 2011-04-07 | 355427 | 0.040 | 5146009
1010 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5149005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Verne. The project is described as: Golden Hills Road - San Dimas Canyon Rd to Esperanza Dr | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2009-10-09 | 2009-10-09 | 598976 | 1.300 | 5149005
1011 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5149006 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of La Verne. The project is described as: Towne Center Drive from Foothill Blvd to White Ave | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2009-10-23 | 2009-10-23 | 136928.06 | 0.250 | 5149006
1012 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5149011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Verne. The project is described as: Emerald Avenue Rehabilitaion | Pavement Improvement | 2011-02-01 | 2011-02-07 | 2011-03-21 | 2011-03-31 | 241000 |  | 5149011
1013 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5150008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Huntington Park. The project is described as: STREET IMPROVEMENTS AT BISSELL FROM FLORENCE AVE. TO RANDOLPH | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-06-01 | 2010-06-30 | 1898000 | 2.780 | 5150008
1014 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5151024 | This is a Pavement Resurfacing project by a local agency in the City of Newport Beach. The project is described as: Balboa Boulevard from 44th Street to 22nd Street | Pavement Improvement | 2009-11-09 | 2009-11-09 | 2010-04-27 | 2010-04-27 | 1027455.87 | 0.950 | 5151024
1015 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 11 | 5152019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Morgan Hill. The project is described as: E. Dunne Ave (US 101 to Butterfield Blvd) | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2009-11-01 | 2010-01-20 | 436393.46 | 0.600 | 5152019
1016 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 19 | 5153028 | This is a Pavement Resurfacing project by a local agency in the City of Oakdale. The project is described as: North Oak Avenue Reconstruction - from Poplar Ave. to Walnut Ave. | Pavement Improvement | 2010-06-07 | 2010-08-24 | 2010-10-22 | 2011-08-15 | 180521.83 | 0.500 | 5153028
1017 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 18 | 5153030 | This is a Pavement Resurfacing project by a local agency in the City of Oakdale. The project is described as: 1) D Street - from Johnson to Maag, 2) Maag - from F St. to G St. | Pavement Improvement | 2010-05-05 | 2010-06-01 | 2010-06-01 | 2010-08-31 | 306799 | 1.000 | 5153030
1018 | CALIFORNIA | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | LODI | 11 | 5154036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lodi. The project is described as: Lodi Avenue from UPRR to 200' East of Cherokee Lane | Pavement Improvement | 2009-11-11 | 2010-04-19 | 2010-12-01 | 2011-03-24 | 2204608.11 | 0.620 | 5154036
1019 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5155006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hermosa Beach. The project is described as: 8th St: PCH to Valley Dr | Pavement Improvement | 2010-03-29 | 2010-04-05 | 2010-08-01 | 2010-07-08 | 294433 | 0.120 | 5155006
1020 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5155007 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Hermosa Beach. The project is described as: Pier Av: PCH to Ardmore Av | Pavement Improvement | 2010-03-29 | 2010-04-05 | 2010-08-01 | 2010-06-22 | 279077 | 0.110 | 5155007
1021 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157068 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Madera. The project is described as: lake:Kennedy to Ellis, Adell:Lake to Merced, Kenedy & Clark Streets: Lake to Tulare Streets. | Pavement Widening | 2010-06-14 | 2010-06-14 | 2011-01-20 | 2011-03-16 | 580000 | 0.500 | 5157068
1022 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157069 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Madera. The project is described as: Construct Bicycle / Pedestrian Facility - Fresno River Trail, Westberry to Road 24 | Transportation Enhancements | 2010-08-16 | 2010-08-16 | 2010-11-16 | 2011-03-16 | 66000 | 0.300 | 5157069
1023 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157070 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Madera. The project is described as: Street Rehabilitation/Resurfacing: I St. - North of 2nd to South of Cen | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-08-18 | 2010-07-30 | 203766.23 | 0.400 | 5157070
1024 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157073 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Madera. The project is described as: Lake Street Phase 1- Cleveland Ave. to Kennedy St. CTIP# 221-0000-0272 | Pavement Widening | 2009-10-19 | 2009-10-19 | 2010-07-21 | 2010-05-14 | 1017000 | 0.500 | 5157073
1025 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA | MADERA | 19 | 5157076 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Madera. The project is described as: Sherwood Way- Austin to Lake, D street- Riverside to Cleveland, Lake Street-Moore to Yosemite. | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2011-01-02 | 2011-05-04 | 178000 | 1.200 | 5157076
1026 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5159014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Anselmo. The project is described as: In San Anselmo at Saunders Avenue. | Pavement Improvement | 2009-10-20 | 2009-10-20 | 2009-11-01 | 2010-01-04 | 228035.19 | 0.300 | 5159014
1027 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5160016 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Los Banos. The project is described as: The overlay of selected streets | Pavement Improvement | 2010-08-24 | 2010-09-08 | 2010-11-30 | 2010-12-08 | 579498.74 | 1.000 | 5160016
1028 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5160017 | This is a Pavement Resurfacing project by a local agency in the City of Los Banos. The project is described as: Overlay and Cape Seal of selected streets | Pavement Improvement | 2010-08-24 | 2010-09-08 | 2010-11-30 | 2010-12-08 | 663805 | 3.000 | 5160017
1029 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5162017 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Claremont. The project is described as: Arrow Highway from Cambridge Ave to Wayland Court | Pavement Improvement | 2010-04-05 | 2010-04-19 | 2010-06-28 | 2010-10-27 | 895000 | 1.600 | 5162017
1030 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5162018 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Claremont. The project is described as: Indian Hill Blvd, Harvard Ave and Foothill Blvd | Transportation Enhancements | 2010-02-18 | 2010-02-22 | 2010-07-08 | 2010-10-27 | 1249606 | 1.510 | 5162018
1031 | CALIFORNIA | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER | YUBA CITY | 02 | 5163019 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Yuba City. The project is described as: in Yuba City, on Bridge St. from 200' west of Shasta St. to 400' east of Shasta St. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-04-30 | 2010-09-08 | 1900000 | 1.000 | 5163019
1032 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | 5163023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Yuba City. The project is described as: Live Oak Blvd from Miller Street to Pease Road | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-07-02 | 2010-05-21 | 753627 | 1.000 | 5163023
1033 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5164016 | This is a Pavement Resurfacing project by a local agency in the City of Inglewood. The project is described as: Manchester Blvd: Ash Av to Crenshaw Blvd | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2010-04-12 | 2010-09-30 | 2524765 | 2.450 | 5164016
1034 | CALIFORNIA | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5164017 | This is a Pavement Resurfacing project by a local agency in the City of Inglewood. The project is described as: La Cienega Blvd at intersections of La Tijera Blvd and Centinela Ave. | Pavement Improvement | 2011-08-11 | 2011-08-15 | 2013-11-29 |  | 952235 | 0.330 | 5164017
1035 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | TURLOCK | 19 | 5165055 | This is a Pavement Resurfacing project by a local agency in the City of Turlock. The project is described as: Streets Preventive Maintenenace. | Pavement Improvement | 2010-06-21 | 2010-06-28 | 2010-12-01 | 2011-05-24 | 2389944 | 1.000 | 5165055
1036 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5166022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Larkspur. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2009-11-30 | 2009-11-30 | 236000 | 0.490 | 5166022
1037 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5167024 | This is a Pavement Resurfacing project by a local agency in the City of Brawley. The project is described as: Western Ave. from SR-86 to N of Park View Dr. | Pavement Improvement | 2010-03-24 | 2010-03-24 | 2010-06-10 | 2010-06-10 | 884922.81 | 0.800 | 5167024
1038 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5167025 | This is a Pavement Resurfacing project by a local agency in the City of Brawley. The project is described as: Brawley Cattle Call Park | Transportation Enhancements | 2010-04-05 | 2010-04-06 | 2011-01-05 | 2011-01-10 | 130595 | 1.000 | 5167025
1039 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5168013 | This is a Pavement Resurfacing project by a local agency in the City of Calexico. The project is described as: Emmerson Avenue from Highway 98 to Third Street | Pavement Improvement | 2010-03-25 | 2010-04-15 | 2010-11-05 | 2010-10-20 | 974000 | 0.780 | 5168013
1040 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL | EL CENTRO | 51 | 5169027 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Centro. The project is described as: Dogwood Rd. from I-8 to State St. (Ph. 1) | Pavement Improvement | 2010-07-06 | 2010-07-26 | 2010-11-01 | 2011-01-24 | 800000 | 1.200 | 5169027
1041 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL | EL CENTRO | 51 | 5169028 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of El Centro. The project is described as: Adams Avenue from Imperial Avenue to LaBrucherie | Pavement Improvement | 2010-08-30 | 2010-09-01 | 2011-03-01 | 2011-01-06 | 302000 | 0.520 | 5169028
1042 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | 5170035 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Kingsburg. The project is described as: In the City of Kingsburg, on 18th Avenue, from Kamm Ave to Solig | Transportation Enhancements | 2010-07-26 | 2010-08-02 | 2010-10-08 | 2010-09-10 | 127393.45 | 0.200 | 5170035
1043 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | 5170036 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Kingsburg. The project is described as: Construct pedestrian facilities along Sierra Street at the UPRR trac | Transportation Enhancements | 2010-10-06 | 2010-10-06 | 2012-04-01 | 2012-03-14 | 209884 | 0.100 | 5170036
1044 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5171016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Burlingame. The project is described as: Airport Blvd fr Anza Blvd to 411 Airport Blvd. Trousdale fr Toledo to Marco Polo | Pavement Improvement | 2009-08-13 | 2009-08-17 | 2009-09-01 | 2009-09-28 | 551000 | 1.200 | 5171016
1045 | CALIFORNIA | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 19 | 5172018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Newman. The project is described as: Construct Downtown Plaza. | Transportation Enhancements | 2010-07-12 | 2010-07-12 | 2010-12-01 | 2011-04-15 | 1821768 | 0.080 | 5172018
1046 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5173020 | This is a Pavement Resurfacing project by a local agency in the City of Fowler. The project is described as: Adams Ave between Vista St. and Dee Ann St. | Pavement Improvement | 2010-06-14 | 2010-06-14 | 2010-07-23 | 2010-07-23 | 160000 | 0.300 | 5173020
1047 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5174007 | This is a Pavement Resurfacing project by a local agency in the City of Holtville. The project is described as: Holt Ave. (W side) between Ninth St. and Tenth St. | Pavement Improvement | 2010-01-04 | 2010-02-08 | 2010-04-23 | 2010-04-02 | 346000 | 0.110 | 5174007
1048 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5174008 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Holtville. The project is described as: SR 115 and Fourth Street Gateway | Transportation Enhancements | 2010-03-24 | 2010-04-05 | 2010-05-21 | 2010-06-02 | 50000 | 0.060 | 5174008
1049 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5174009 | This is a Pavement Resurfacing project by a local agency in the City of Holtville. The project is described as: Walnut Avenue from 5th Street/SR 115 to 4th Street | Pavement Improvement | 2009-12-10 | 2009-12-14 | 2010-03-18 | 2010-03-19 | 317868 | 0.110 | 5174009
1050 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5174010 | This is a Pavement Resurfacing project by a local agency in the City of Holtville. The project is described as: Ninth Street (N side) between Cedar Avenue and Holt Avenue | Pavement Improvement | 2010-06-18 | 2010-07-07 | 2010-08-13 | 2010-08-19 | 247000 | 0.120 | 5174010
1051 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5176005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Ross. The project is described as: Along SFD Blvd. in the Town of Ross Limits. | Pavement Improvement | 2010-09-20 | 2010-10-04 | 2010-10-22 | 2010-11-03 | 226436 | 1.000 | 5176005
1052 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5177022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South San Francisco. The project is described as: Various Streets in South SF | Pavement Improvement | 2009-08-10 | 2009-09-14 | 2009-10-01 | 2009-10-07 | 675702.34 | 0.850 | 5177022
1053 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5177023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South San Francisco. The project is described as: Utah from Utah Bridge Channel to Litttlefield Avenue Grand Ave fr Chestnut to Old Mission | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2010-09-27 | 2010-09-27 | 328300 | 0.800 | 5177023
1054 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5180008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Montague. The project is described as: North & South 11th Street | Pavement Improvement | 2010-06-18 | 2010-06-28 | 2010-07-30 | 2010-07-16 | 405500 | 0.900 | 5180008
1055 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5181164 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Huntington Beach. The project is described as: Edinger Avenue from Countess Drive to Saybrook Lane | Transportation Enhancements | 2010-01-12 | 2010-01-12 | 2010-07-15 | 2010-08-04 | 156000 | 0.840 | 5181164
1056 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5181166 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Huntington Beach. The project is described as: Slater Avenue from Graham Street to Goldenwest Street | Pavement Improvement | 2010-03-29 | 2010-03-29 | 2010-07-20 | 2010-06-28 | 1120616 | 1.500 | 5181166
1057 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5181168 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Huntington Beach. The project is described as: Garfield Avenue Newland to Magnolia Rehabilitation Improvements | Pavement Improvement | 2011-02-22 | 2011-02-22 | 2011-05-25 | 2011-05-19 | 653141 |  | 5181168
1058 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182041 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: Construct bicycle & pedestrian improvements along Washington Boulevard & place bonded wearing course to roadway. | Transportation Enhancements | 2010-04-26 | 2010-04-26 | 2010-07-30 | 2010-07-30 | 800000 | 0.300 | 5182041
1059 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182046 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: Place hot mix asphalt on Junction Boulevard, Woodcreek Oaks Boulevard & Eureka Road. | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-11-01 | 2010-11-01 | 1006173 | 5.000 | 5182046
1060 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182048 | This is a Traffic Management Engineering HOV project by a local agency in the City of Roseville. The project is described as: Intersection of Sierra College Blvd and Douglas Blvd | Other | 2009-08-06 | 2009-08-06 | 2009-11-01 | 2010-01-06 | 295436.01 | 0.100 | 5182048
1061 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182049 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: N. Sunrise Ave btw Lead Hill Rd and E Roseville Parkway | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2010-01-07 | 2010-01-07 | 844208.46 | 1.000 | 5182049
1062 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182050 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: Cirby Way east of I80 to Old Auburn Road | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2010-10-30 | 2011-01-19 | 1131767 | 1.500 | 5182050
1063 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182051 | This is a Traffic Management Engineering project by a local agency in the City of Roseville. The project is described as: Sunrise Ave south of Cirby Way | Safety/Traffic Management | 2009-09-30 | 2009-09-30 | 2010-02-11 | 2010-02-11 | 105207.27 | 1.000 | 5182051
1064 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182052 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Roseville. The project is described as: Sierra College Blvd/East Roseville Parkway Intersection improvements | Safety/Traffic Management | 2009-09-08 | 2009-09-08 | 2009-11-01 | 2009-11-01 | 121208.35 | 0.100 | 5182052
1065 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182054 | This is a Pavement Resurfacing project by a local agency in the City of Roseville. The project is described as: I-inch bonded wearing course placed on Douglas Blvd. | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2010-08-30 | 2010-08-30 | 352863 | 1.600 | 5182054
1066 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5182055 | CHURCH ST, BASELINE RD, JUNCTION BL, FOOTHILLS BL, ATLANTIC ST & PLEASANT GROVE, MICROPAVE RESURFACING | Pavement Improvement | 2011-09-06 | 2011-09-06 | 2012-08-15 | 2012-08-15 | 646182 |  | 5182055
1067 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5184011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Tehachapi. The project is described as: North Mill Street from H Street to State Route 58 and westbound H Street from North Mill Street to North Green Street | Pavement Improvement | 2010-09-01 | 2010-09-06 | 2010-12-15 | 2010-12-22 | 479906.43 | 0.950 | 5184011
1068 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5184014 | "This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Tehachapi. The project is described as: South of Tehachapi Blvd., North of ""F"" St between Green St and | Transportation Enhancements | 2010-04-22 | 2010-05-03 | 2010-09-03 | 2011-03-21 | 419551.67 | 0.040 | 5184014
1069 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | GLENN |  | 02 | 5185005 | This is a Pavement Resurfacing project by a local agency in the City of Orland. The project is described as: Sixth Street from North to South city Limits | Pavement Improvement | 2009-10-05 | 2009-10-30 | 2009-11-01 | 2009-11-20 | 423181 | 1.070 | 5185005
1070 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5190006 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Blue Lake. The project is described as: Greenwood Ave from Blue Lake Blvd to Railroad Ave | Transportation Enhancements | 2010-06-16 | 2010-06-21 | 2010-08-31 | 2010-08-26 | 89000 | 0.100 | 5190006
1071 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5191004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hillsborough. The project is described as: Ralston, Parrott, Black Mountain Road, Tartan, Hayne | Pavement Improvement | 2009-09-29 | 2009-10-01 | 2009-12-01 | 2009-12-30 | 392000 | 2.300 | 5191004
1072 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | TRACY | 11 | 5192028 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Tracy. The project is described as: Bessie Avenue from 11th St to Carlton Way | Pavement Improvement | 2009-10-08 | 2009-10-26 | 2011-04-05 | 2011-04-05 | 1614305.99 | 0.500 | 5192028
1073 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5193030 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Taft. The project is described as: 6th Street from Kern Street to Warren Street | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2010-06-30 | 2010-06-18 | 297881.67 | 0.260 | 5193030
1074 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5194005 | This is a Pavement Resurfacing project by a local agency in the City of King City. The project is described as: Bassett Street Overlay | Pavement Improvement | 2009-11-24 | 2009-12-11 | 2010-01-15 | 2010-04-07 | 232000 | 1.000 | 5194005
1075 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5194006 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of King City. The project is described as: Downtown Sidewalk Gap Closure | Transportation Enhancements | 2010-05-20 | 2010-05-24 | 2010-07-01 | 2010-07-08 | 197500 | 1.000 | 5194006
1076 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5196032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Daly City. The project is described as: Various Street: Callan, Mission St, Glenwood, Hillside, Carter, John Daly Blvd | Pavement Improvement | 2009-09-21 | 2009-09-28 | 2010-02-01 | 2010-01-25 | 1045000 | 0.800 | 5196032
1077 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5196033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Daly City. The project is described as: Carter St. from Martin to City Limits, Crocker Ave. fr Mission to Brunswick | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-08-01 | 2010-10-11 | 318000 | 0.300 | 5196033
1078 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5197018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sanger. The project is described as: On Academy Ave, from California Ave to Church Ave. | Pavement Improvement | 2010-04-07 | 2010-04-07 | 2010-07-05 | 2010-10-21 | 398112.93 | 0.500 | 5197018
1079 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO | SAN LUIS OBISPO | 22 | 5199021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Arroyo Grande. The project is described as: West Branch st. Rehab | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2010-12-31 | 2010-11-12 | 525000 | 1.500 | 5199021
1080 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5200028 | This is a Rail/Highway Crossing project by a local agency in the City of Burbank. The project is described as: BUENA VISTA ST BETWEEN SAN FERNANDO BL AND I-5 NORTH BOUND ON RAMP | Safety/Traffic Management | 2010-10-28 | 2010-11-04 | 2011-03-22 | 2011-06-22 | 1041842 | 0.090 | 5200028
1081 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5200029 | This is a Traffic Management Engineering project by a local agency in the City of Burbank. The project is described as: VARIUOS LOCATIONS WITHIN BURBANK | Safety/Traffic Management | 2010-01-25 | 2010-04-20 | 2010-09-23 | 2010-09-23 | 377754.22 | 1.000 | 5200029
1082 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5200033 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Burbank. The project is described as: VARIOUS LOCATIONS CITYWIDE | Transportation Enhancements | 2010-04-28 | 2010-05-03 | 2010-11-24 | 2011-01-07 | 661318.87 | 3.000 | 5200033
1083 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5202014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Fernando. The project is described as: BRAND BL FROM TRUMAN ST TO SOUTH CITY LIMITS | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2011-05-31 | 2011-05-31 | 660176 | 0.580 | 5202014
1084 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5204011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Glendora. The project is described as: Grand Ave from Arrow Highway to Foothill Blvd | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-02-01 | 2010-03-05 | 1181304.4 | 2.000 | 5204011
1085 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5206011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Angels. The project is described as: Stockton Rd. in City of Angels from SR49 to Angels Oak Drive | Pavement Improvement | 2010-06-21 | 2010-06-23 | 2010-07-20 | 2010-10-14 | 109801.15 | 0.540 | 5206011
1086 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208066 | ASHLAN AVE FROM WHITTIER TO TEMPERANCE & ARMSTRONG SO. OF ASHLAN TO GOULD CANAL, LANDSCAPING IMPROVEMENTS | Transportation Enhancements | 2010-11-01 | 2010-11-12 | 2011-11-21 | 2011-11-21 | 116325 |  | 5208066
1087 | CALIFORNIA | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208090 | This is a New Construction Roadway project by a local agency in the City of Clovis. The project is described as: Temperance Ave, Gettysburg - Gould Canal | Pavement Widening | 2009-10-23 | 2009-10-23 | 2010-03-01 | 2010-03-15 | 400000 | 0.750 | 5208090
1088 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208091 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Shaw Ave, Minnewawa-Clovis | Pavement Improvement | 2009-09-20 | 2009-09-20 | 2010-04-01 | 2010-03-15 | 607855 | 0.500 | 5208091
1089 | CALIFORNIA | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208092 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Bullard Ave, Fowler-Armstrong | Pavement Improvement | 2009-09-30 | 2009-09-30 | 2010-03-01 | 2010-03-15 | 350000 | 0.500 | 5208092
1090 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208093 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Ness Ave: Peach-Minnewawa | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-04-01 | 2010-03-15 | 400000 | 0.500 | 5208093
1091 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | 5208095 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Clovis. The project is described as: Shaw Ave. from Willow to Peach | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2011-02-22 | 2011-02-22 | 592555.56 | 0.500 | 5208095
1092 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5210016 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of El Monte. The project is described as: Various Streets Citywide | Transportation Enhancements | 2010-07-14 | 2010-07-19 | 2011-03-15 | 2010-12-15 | 1192670 | 5.100 | 5210016
1093 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5210018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Monte. The project is described as: Various locations Citywide | Pavement Improvement | 2010-07-14 | 2010-07-19 | 2010-11-22 | 2010-11-05 | 3217000 | 7.000 | 5210018
1094 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5212003 | This is a Pavement Resurfacing project by a local agency in the City of Manhattan Beach. The project is described as: AVIATION BLVD FROM MARINE AVE TO MANHATTAN BEACH BLVD | Pavement Improvement | 2009-12-03 | 2009-12-07 | 2010-01-08 | 2010-01-08 | 151413.63 | 0.500 | 5212003
1095 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5212004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Manhattan Beach. The project is described as: VALLEY DRIVE FROM 15TH STREET to SEPULVEDA BLVD | Pavement Improvement | 2009-12-03 | 2009-12-07 | 2010-02-01 | 2010-02-05 | 378837 | 1.300 | 5212004
1096 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5212007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Manhattan Beach. The project is described as: Pacific Ave. Resurfacing Project | Pavement Improvement | 2011-06-14 | 2011-07-05 | 2011-10-07 | 2011-08-22 | 543749 |  | 5212007
1097 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5213032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sunnyvale. The project is described as: Wolfe Road Caltrain Overcrossing, Bridge 37C0776 | Bridge Improvement | 2009-08-19 | 2009-09-28 | 2009-11-01 | 2009-11-20 | 1225635 | 0.300 | 5213032
1098 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5213033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sunnyvale. The project is described as: Sunnyvale Avenue Pavement Rehabilitation/Resurfacing | Pavement Improvement | 2010-10-18 | 2010-10-25 | 2011-01-25 | 2011-06-01 | 417509 | 0.300 | 5213033
1099 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN FRANCISCO-OAKLAND, CA | 14 | 5213034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Sunnyvale. The project is described as: Homestead Road Resurfacing | Pavement Improvement | 2010-09-07 | 2010-09-20 | 2010-12-18 | 2011-06-01 | 869365 | 1.000 | 5213034
1100 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 19 | 5216039 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Reedley. The project is described as: Intersection of Buttonwillow & Dinuba Avenues Construction of multi-lane roundabout, lighting, landscape and irrigation | Other | 2010-08-18 | 2010-09-07 | 2010-12-10 | 2011-02-22 | 477025 | 1.000 | 5216039
1101 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5217011 | This is a Safety project by a local agency in the City of San Gabriel. The project is described as: LAS TUNAS DRIVE - WEST CITY LIMIT TO MUSCATEL AVEUNE | Pavement Improvement | 2010-06-17 | 2010-06-30 | 2012-04-30 | 2012-04-30 | 1247059.56 | 2.750 | 5217011
1102 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5218007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Marino. The project is described as: Huntington Drive from San Marino Ave to San Gabriel Blvd | Pavement Improvement | 2010-09-02 | 2010-09-07 | 2010-11-08 | 2010-11-17 | 500000 | 0.750 | 5218007
1103 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5221009 | This is a Pavement Resurfacing project by a local agency in the City of Beverly Hills. The project is described as: Robertson Blvd: Burton Way to Withworth Dr | Pavement Improvement | 2009-10-26 | 2009-11-02 | 2010-12-01 | 2009-11-23 | 437174 | 1.100 | 5221009
1104 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5221011 | This is a Pavement Resurfacing project by a local agency in the City of Beverly Hills. The project is described as: RESURFACING OF APPROXIMATELY 8.1 MILES OF PRINCIPAL ARTERIAL AND MAJOR COLLECTOR STREETS WITHIN THE CITY OF BEVERLY HILLS. | Pavement Improvement | 2011-06-06 | 2011-06-06 | 2011-07-11 | 2011-08-25 | 621826 |  | 5221011
1105 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5222018 | This is a Pavement Resurfacing project by a local agency in the City of Fillmore. The project is described as: MOUNTAIN VIEW STREET FROM VENTURA STREET TO SECOND STREET AND A STREET FROM SANTA CLARA STREET TO SESPE AVENUE | Pavement Improvement | 2010-05-26 | 2010-05-26 | 2010-07-14 | 2012-01-27 | 400000 | 0.820 | 5222018
1106 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5223014 | This is a Pavement Resurfacing project by a local agency in the City of Corcoran. The project is described as: City of Corcoran, Orange Ave. From Otis Ave. to Dairy Ave.; Overlay Roadway | Pavement Improvement | 2010-05-17 | 2010-05-26 | 2011-02-01 | 2011-01-03 | 961556.85 | 1.000 | 5223014
1107 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5224014 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Firebaugh. The project is described as: On O Street from 9th to 11th Street in the City of Firebaugh | Transportation Enhancements | 2010-09-09 | 2010-09-20 | 2010-11-15 | 2010-12-30 | 160000 | 0.170 | 5224014
1108 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5225020 | This is a Safety project by a local agency in the City of Walnut Creek. The project is described as: North side of Ygnacio Valley Road between Marchbank Drive (West) and Ygnacio Court | Transportation Enhancements | 2010-08-09 | 2010-08-09 | 2010-10-11 | 2011-01-25 | 436864 | 0.600 | 5225020
1109 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5225022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Walnut Creek. The project is described as: Civic Dr. | Pavement Improvement | 2009-09-09 | 2009-09-10 | 2009-11-10 | 2009-11-10 | 882211.2 | 0.830 | 5225022
1110 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5226016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Bruno. The project is described as: Various Streets in San Bruno | Pavement Improvement | 2010-05-19 | 2010-05-26 | 2010-11-20 | 2011-05-26 | 593842.9 | 1.400 | 5226016
1111 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 20 | 5227036 | This is a Pavement Resurfacing project by a local agency in the City of Delano. The project is described as: 11th Ave from Albany St to High St, 9th Ave from High St to Randolph St, Norwalk St from C | Pavement Improvement | 2010-01-07 | 2010-01-19 | 2010-06-01 | 2010-08-02 | 934745 | 3.420 | 5227036
1112 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 5227039 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Delano. The project is described as: 11th Ave from High St. to Randolph St; High St .from Garces Hwy to Ceci | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-09-15 | 2010-12-06 | 1002581 | 3.000 | 5227039
1113 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5229011 | This is a Pavement Resurfacing project by a local agency in the City of Seal Beach. The project is described as: Seal Beach Boulevard from Pacific Coast Highway (SR 1) to Bolsa Avenue | Pavement Improvement | 2011-08-08 | 2011-08-08 | 2012-02-13 | 2012-02-13 | 362876.76 | 0.310 | 5229011
1114 | CALIFORNIA | Completed | C250,C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5230002 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Gustine. The project is described as: On West, Second, Sixth and Third Streets near City Park. | Transportation Enhancements | 2010-04-21 | 2010-04-22 | 2010-05-31 | 2010-06-07 | 182762 | 0.700 | 5230002
1115 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5231012 | This is a Pavement Resurfacing project by a local agency in the City of Monterey Park. The project is described as: Various City Streets | Pavement Improvement | 2010-03-15 | 2010-03-22 | 2010-07-01 | 2010-09-14 | 1589805.8 | 3.100 | 5231012
1116 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5232009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Corte Madera. The project is described as: In Corte Madera at Tamal Vista Blvd. and Casa Buena Drive from Sanford to # 1595. | Pavement Improvement | 2009-10-21 | 2009-11-05 | 2009-12-01 | 2009-11-25 | 130772.06 | 0.770 | 5232009
1117 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5235010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Segundo. The project is described as: Mariposa Ave:Sepulveda Bl to Nash St | Pavement Improvement | 2010-04-15 | 2010-04-19 | 2010-03-20 | 2010-06-07 | 210341.65 | 0.510 | 5235010
1118 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5235011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Segundo. The project is described as: Main Street from Mariposa Ave to Imperial Hwy | Pavement Improvement | 2009-12-08 | 2009-12-10 | 2010-01-02 | 2010-01-12 | 199013.38 | 0.500 | 5235011
1119 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | 5237026 | This is a Pavement Resurfacing project by a local agency in the City of Brea. The project is described as: Associated Road from 500 feet north of Imperial Highway to Birch Street | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2010-09-30 | 2010-09-10 | 479243.25 | 0.470 | 5237026
1120 | CALIFORNIA | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 01 | 5238048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Davis. The project is described as: Various Locations in the City of Davis for Roadway Rehabilitation | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2009-12-01 | 2009-11-09 | 730551.16 | 1.000 | 5238048
1121 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 02 | 5238051 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Davis. The project is described as: See NEPA for locations | Transportation Enhancements | 2010-08-16 | 2010-08-16 | 2010-12-01 | 2011-03-08 | 636998.86 | 1.000 | 5238051
1122 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 01 | 5238052 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Davis. The project is described as: Second Street from C to F Streets, construct bulb-outs and Ped/Transit Improvements, ADA Upgrade | Transportation Enhancements | 2010-07-06 | 2010-07-06 | 2010-12-01 | 2011-06-16 | 650000 | 1.000 | 5238052
1123 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5239014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of El Cerrito. The project is described as: El Cerrito Pavement Rehab. | Pavement Improvement | 2010-09-28 | 2010-10-11 | 2009-12-01 | 2011-02-25 | 678000 | 1.500 | 5239014
1124 | CALIFORNIA | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5240021 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Culver City. The project is described as: Ballona Creek Bike Path: Overland Ave to Ocean Dr. (Ped. Bridge) | Transportation Enhancements | 2010-09-08 | 2010-09-20 | 2011-02-01 | 2011-02-21 | 476174 | 0.200 | 5240021
1125 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5240023 | This is a Pavement Resurfacing project by a local agency in the City of Culver City. The project is described as: Washington Blvd: Helms Ave to Lacienega Blvd | Pavement Improvement | 2009-10-14 | 2009-10-23 | 2009-12-01 | 2009-12-22 | 619279.35 | 0.500 | 5240023
1126 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5240024 | This is a Pavement Resurfacing project by a local agency in the City of Culver City. The project is described as: Culver Blvd: Sepulveda Bl to Elenda St | Pavement Improvement | 2009-10-22 | 2009-10-28 | 2009-11-19 | 2010-04-05 | 172982.63 | 0.350 | 5240024
1127 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 18 | 5241031 | This is a Pavement Resurfacing project by a local agency in the City of Ceres. The project is described as: Arterial Street Overlay. | Pavement Improvement | 2010-06-10 | 2010-06-15 | 2010-08-06 | 2010-08-06 | 1271586.78 | 1.500 | 5241031
1128 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5242021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Manteca. The project is described as: Union Rd, Northgate Dr, North St, Hoyt Ln, Winters Dr, Button Ave, Wawona St, Alameda Ave, and Mission Ridge Dr | Pavement Improvement | 2009-10-16 | 2009-10-26 | 2010-04-01 | 2010-05-11 | 1098498.89 | 4.000 | 5242021
1129 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5242025 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: Landscaping at Route 99/120 interchanges. Plant approximate | Transportation Enhancements | 2010-07-23 | 2010-07-31 | 2013-04-22 |  | 909570 | 1.900 | 5242025
1130 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | MANTECA | 11 | 5242027 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Manteca. The project is described as: Landscaping enhancement of existing state highway | Transportation Enhancements | 2011-01-24 | 2011-02-23 | 2013-11-17 |  | 2375000 |  | 5242027
1131 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5243006 | This is a Pavement Resurfacing project by a local agency in the City of Calipatria. The project is described as: Main St. between SR-111/115 and Lyerly | Pavement Improvement | 2010-02-26 | 2010-03-08 | 2010-06-07 | 2010-09-07 | 895000 | 0.640 | 5243006
1132 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 18 | 5244022 | This is a Pavement Resurfacing project by a local agency in the City of Patterson. The project is described as: City of Patterson project location SR 33 & M St. | Pavement Improvement | 2010-06-03 | 2010-08-16 | 2010-12-29 | 2011-11-15 | 637319 | 1.000 | 5244022
1133 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5245009 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of San Joaquin. The project is described as: Main Street from Arizona to Placer Avenues | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2010-09-01 | 2010-08-11 | 160000 | 0.320 | 5245009
1134 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5246004 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Williams. The project is described as: E Street at several cross streets between I-5 and SR20. | Safety/Traffic Management | 2010-10-08 | 2010-10-12 | 2012-06-01 | 2012-01-06 | 220000 | 1.000 | 5246004
1135 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5247015 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Montebello. The project is described as: Various Locations Citywide | Transportation Enhancements | 2009-12-01 | 2009-12-08 | 2010-05-14 | 2010-05-14 | 1573305.9 | 0.700 | 5247015
1136 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5247016 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Montebello. The project is described as: Whittier Blvd: 4th St. to Van Norman St. | Transportation Enhancements | 2010-06-16 | 2010-06-16 | 2011-01-10 | 2010-12-28 | 671821.53 | 0.500 | 5247016
1137 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5248006 | This is a Safety project by a local agency in the City of Soledad. The project is described as: Oak and Front Street | Safety/Traffic Management | 2009-06-22 | 2009-06-22 | 2010-02-03 | 2010-03-03 | 544891 | 0.120 | 5248006
1138 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5249019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Torrance. The project is described as: Crenshaw Bl: Maricopa St to Sepulveda Bl | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2012-01-28 | 2010-07-31 | 1206368.59 | 2.000 | 5249019
1139 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 36 | 5249021 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Torrance. The project is described as: Del Amo Blvd: Madrona Ave/ Crenshaw Blvd | Pavement Improvement | 2010-11-24 | 2010-11-24 | 2012-12-31 | 2012-11-30 | 3125678 | 1.000 | 5249021
1140 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5250013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: Atlantic Ave from Fernwood Ave to South City limit (McMillan Ave). | Pavement Improvement | 2010-03-11 | 2010-03-29 | 2010-05-06 | 2010-08-03 | 435189.74 | 0.300 | 5250013
1141 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5250014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: MLK BLVD. FROM ATLANTIC AVE TO EAST CITY LIMIT | Pavement Improvement | 2010-01-04 | 2010-01-25 | 2010-04-01 | 2010-10-05 | 643052.72 | 0.470 | 5250014
1142 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5250015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: OTIS AVE FROM IMPERIAL HIGHWAY TO ABBOTT ROAD | Pavement Improvement | 2010-01-04 | 2010-01-25 | 2010-04-29 | 2010-08-03 | 309403 | 0.230 | 5250015
1143 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5250016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lynwood. The project is described as: IMPERIAL HIGHWAY FROM ATLANTIC AVE. TO EAST CITY LIMIT. | Pavement Improvement | 2010-03-11 | 2010-05-03 | 2010-06-03 | 2011-03-01 | 604076.53 | 0.500 | 5250016
1144 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5251020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Ojai. The project is described as: VALLE RIOS, BRISTOL RD, FOOTHILL RD, MONTGOMERY AVE. AND DEL NORTE ROAD. | Pavement Improvement | 2010-03-10 | 2010-03-24 | 2010-03-01 | 2010-04-29 | 400000 | 1.500 | 5251020
1145 | CALIFORNIA | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5252013 | This is a Pavement Resurfacing project by a local agency in the City of Parlier. The project is described as: Manning Ave, from 650 ft w/o Academy to Whitener Ave | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-08-16 | 2010-08-15 | 248443 | 0.500 | 5252013
1146 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5253014 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Hawthorne. The project is described as: Birch Ave @ UPRR Grade Crossing | Pavement Improvement | 2009-09-30 | 2010-03-12 | 2010-03-13 | 2010-03-13 | 35000 | 0.100 | 5253014
1147 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5253015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Hawthorne. The project is described as: CITYWIDE: Various City Streets | Pavement Improvement | 2009-09-20 | 2009-10-15 | 2010-02-01 | 2010-02-15 | 2600000 | 1.000 | 5253015
1148 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5254012 | This is a Pavement Resurfacing project by a local agency in the City of Atwater. The project is described as: SHAFFER RD (OVERLAY AND PARTIAL RECONSTRUCTION) between Bellevue Rd. and Juniper Ave. | Pavement Improvement | 2009-12-14 | 2010-01-27 | 2010-05-01 | 2010-09-13 | 568275.82 | 0.700 | 5254012
1149 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5254013 | This is a Pavement Resurfacing project by a local agency in the City of Atwater. The project is described as: On Juniper Ave from Shaffer Rd to Bridgewater St | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-11-03 | 2009-11-03 | 323067.76 | 0.400 | 5254013
1150 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5254014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Atwater. The project is described as: Winton Way from Bellevue Rd. to Livingston Canal. | Pavement Improvement | 2011-03-15 | 2011-03-15 | 2011-05-13 | 2011-05-06 | 551769 | 0.250 | 5254014
1151 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | 5255042 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Riverbank. The project is described as: Third Street(Sierra to Patterson),Santa Fe (Second to Fiirst),Third Street (North of Topeka to just before Atchion) | Pavement Improvement | 2010-06-01 | 2010-07-06 | 2010-10-25 | 2011-01-10 | 331425 | 0.500 | 5255042
1152 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 19 | 5255043 | This is a Pavement Resurfacing project by a local agency in the City of Riverbank. The project is described as: Roselle Ave from 150 ft. South of Turpin to Claribel Rd | Pavement Improvement | 2010-06-01 | 2010-06-28 | 2010-07-28 | 2010-08-23 | 317559 | 1.000 | 5255043
1153 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5256009 | This is a Pavement Resurfacing project by a local agency in the City of Livingston. The project is described as: Project involves road grinding, replacement of asphalt concrete, crack sealing of road | Pavement Improvement | 2009-10-02 | 2009-10-05 | 2010-02-01 | 2010-04-17 | 550803 | 2.620 | 5256009
1154 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5257022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South Gate. The project is described as: State Street from North City Limit (Santa Ana St) to Tweedy Blvd. | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2010-11-01 | 2011-09-13 | 1408326 | 1.300 | 5257022
1155 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5257023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of South Gate. The project is described as: Atlantic Ave from Firestone Blvd to Abbott Rd | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2010-06-01 | 2011-01-25 | 1186674 | 1.250 | 5257023
1156 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5258026 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Chowchilla. The project is described as: Washington Rd. - Road rehabilitation; curb/gutter/sidewalk, utility and street light installation | Pavement Improvement | 2011-11-14 | 2011-11-28 | 2012-04-28 | 2012-02-02 | 355569.66 | 0.150 | 5258026
1157 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5259017 | This is a Traffic Management Engineering HOV project by a local agency in the City of West Covina. The project is described as: Intersections Puente Ave at Sunset Ave, Puente Ave at Lark Ellen Ave, Nogales St at Amanda St | Safety/Traffic Management | 2009-11-17 | 2010-02-16 | 2010-03-22 | 2010-03-22 | 213198 | 0.250 | 5259017
1158 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5259018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of West Covina. The project is described as: Various Locations Citywide, Sunset Ave et.al | Pavement Improvement | 2009-11-17 | 2009-11-30 | 2010-08-25 | 2010-08-25 | 2954577 | 8.600 | 5259018
1159 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5261006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Atherton. The project is described as: Atherton Ave from Stern Lane to Elena | Pavement Improvement | 2009-07-27 | 2009-07-29 | 2009-08-01 | 2009-08-31 | 463060.84 | 0.500 | 5261006
1160 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 38 | 5262004 | This is a Pavement Resurfacing project by a local agency in the City of Signal Hill. The project is described as: Cherry Ave: Spring St to 19th St | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2009-11-01 | 2010-03-15 | 500000 | 1.500 | 5262004
1161 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5264003 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Colma. The project is described as: Serramonte Blvd between ECR (SR82) to Junipero Serra Blvd | Pavement Improvement | 2009-09-11 | 2009-09-22 | 2009-10-24 | 2009-10-20 | 131000 | 0.500 | 5264003
1162 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5265010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Maywood. The project is described as: Slauson Ave: Downey Road to Pine Avenue | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2010-06-01 | 2010-07-05 | 294847.47 | 1.000 | 5265010
1163 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 34 | 5265011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Maywood. The project is described as: Atlantic Blvd:Randolph St. to 59th Place | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2010-03-31 | 2010-03-31 | 588152.53 | 0.300 | 5265011
1164 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | 5266018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Habra. The project is described as: Idaho Street from the south city limits to Imperial Highway (SR 90) | Pavement Improvement | 2010-02-01 | 2010-02-04 | 2010-03-22 | 2010-04-05 | 336897 | 0.750 | 5266018
1165 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5267013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Carlos. The project is described as: Various Locations in San Carlos | Transportation Enhancements | 2009-09-28 | 2009-09-28 | 2010-02-22 | 2010-02-22 | 285510.82 | 0.750 | 5267013
1166 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5267014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Carlos. The project is described as: Crestview Drive from Edgewood to Melandy | Pavement Improvement | 2010-06-21 | 2010-06-21 | 2010-09-13 | 2010-09-13 | 264000 | 1.000 | 5267014
1167 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5268004 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Belmont. The project is described as: Ralston/101 Bike Overpass. | Transportation Enhancements | 2010-01-21 | 2010-02-01 | 2013-06-30 |  | 1952194 | 0.200 | 5268004
1168 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5268015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Belmont. The project is described as: 6th Ave, Carlmont, Cipriani, Hallmark | Pavement Improvement | 2009-08-31 | 2009-09-09 | 2010-04-30 | 2010-06-08 | 464000 | 0.800 | 5268015
1169 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5268016 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Belmont. The project is described as: over crossing on SR 101 north of Ralston Avenue Interchang | Transportation Enhancements | 2010-01-01 | 2010-01-01 | 2013-06-30 |  | 2493000 | 0.200 | 5268016
1170 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5269021 | This is a Pavement Resurfacing project by a local agency in the City of Placentia. The project is described as: Placentia Avenue from south city limits at Palm Drive to Mystic Avenue | Pavement Improvement | 2010-03-23 | 2010-04-05 | 2010-07-15 | 2010-08-17 | 500000 | 0.530 | 5269021
1171 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | 5271020 | This is a Pavement Resurfacing project by a local agency in the City of Tustin. The project is described as: Jamboree Road from 2,750 feet north of Tustin Ranch Road to the north city limits. | Pavement Improvement | 2010-03-29 | 2010-04-05 | 2010-06-28 | 2010-09-05 | 813324 | 1.400 | 5271020
1172 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5272009 | This is a Pavement Resurfacing project by a local agency in the City of Bell. The project is described as: Bandini Blvd : Eastern Ave. to 26th St. | Pavement Improvement | 2010-05-12 | 2010-05-17 | 2010-09-01 | 2010-08-03 | 517574.59 | 0.800 | 5272009
1173 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5272010 | This is a Pavement Resurfacing project by a local agency in the City of Bell. The project is described as: Wilcox Ave: Gage Ave to Randolph St | Pavement Improvement | 2010-05-12 | 2010-05-17 | 2010-08-05 | 2010-08-10 | 507554 | 0.250 | 5272010
1174 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5273020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Menlo Park. The project is described as: Haven, Live Oak, Monte Rosa | Pavement Improvement | 2009-09-03 | 2009-09-14 | 2009-12-01 | 2010-03-22 | 635000 | 1.300 | 5273020
1175 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | STATEWIDE | 44 | 5274029 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Clemente. The project is described as: South Ola Vista from Avenida Princesa to Avenida Calafia | Pavement Improvement | 2010-06-14 | 2010-06-14 | 2010-08-09 | 2011-03-10 | 500000 | 0.750 | 5274029
1176 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5276022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Gardena. The project is described as: Western Ave from Redondo Beach to El Segundo Blvd | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2010-03-15 | 2010-03-24 | 838793.21 | 2.000 | 5276022
1177 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5276023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Gardena. The project is described as: 135th Street from Crenshaw Blvd. to Vermont Ave. | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2010-03-15 | 2010-03-24 | 795294.08 | 2.000 | 5276023
1178 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5277024 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fairfax. The project is described as: In Fairfax at Sir Francis Drake Blvd. from June Court to Town limits. | Pavement Improvement | 2010-03-29 | 2010-03-29 | 2010-05-10 | 2010-04-23 | 167000 | 0.960 | 5277024
1179 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5278009 | This is a Pavement Resurfacing project by a local agency in the City of Westmorland. The project is described as: 7th Street from H Street to Center Street | Safety/Traffic Management | 2009-11-20 | 2009-11-23 | 2010-03-01 | 2010-04-06 | 234610.5 | 0.250 | 5278009
1180 | CALIFORNIA | Completed | C250,C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5279003 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Dos Palos. The project is described as: Westside of Center Ave from Blossom St. to Almond St.(Dos Palos) | Transportation Enhancements | 2010-06-25 | 2010-08-02 | 2011-03-04 | 2011-03-07 | 176610.5 | 0.090 | 5279003
1181 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 5281012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Shafter. The project is described as: Lerdo Highway between Carver Street and Driver Road | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-06-30 | 2010-06-16 | 589437 | 1.500 | 5281012
1182 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | INDIA-COACHELLA | 45 | 5282027 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Palm Springs. The project is described as: Gene Autry Trail from Vista Chino to Via Escuela | Transportation Enhancements | 2009-11-09 | 2009-11-09 | 2010-06-01 | 2010-12-09 | 1800000 | 0.250 | 5282027
1183 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | INDIA-COACHELLA | 45 | 5282034 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Palm Springs. The project is described as: Widen OC, add/widen ramps, improve circulation | Pavement Widening | 2010-08-10 | 2010-08-23 | 2012-06-30 | 2012-05-18 | 5517500 | 1.100 | 5282034
1184 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 5283006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palos Verdes Est. The project is described as: Palos Verdes Dr W @ Bluff Cove | Pavement Improvement | 2009-11-09 | 2009-11-16 | 2010-03-19 | 2010-03-19 | 500000 | 0.050 | 5283006
1185 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5284006 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Woodlake. The project is described as: Existing Bravo Lake Botanical Garden just South of SR 216 and just East SR 245 in the City of Woodlake. | Transportation Enhancements | 2010-09-01 | 2010-11-01 | 2011-03-31 | 2011-02-28 | 206563 | 1.140 | 5284006
1186 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5286012 | This is a Traffic Management Engineering project by a local agency in the City of Ripon. The project is described as: City of Ripon Wilma and 2nd St. Roundabout | Pavement Improvement | 2009-11-24 | 2009-12-09 | 2010-03-01 | 2010-12-21 | 202131 | 1.000 | 5286012
1187 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5286013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Ripon. The project is described as: E. Main Street between Second Street and Manley Road | Pavement Improvement | 2010-07-26 | 2010-08-17 | 2010-11-01 | 2011-08-02 | 100000 | 1.000 | 5286013
1188 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5286016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Ripon. The project is described as: Rehabilitation of 3 streets in the City of Ripon. | Pavement Improvement | 2010-07-26 | 2010-08-01 | 2010-11-30 | 2011-08-02 | 393496 |  | 5286016
1189 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 5287026 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Wasco. The project is described as: On Poso Dr. from SR 43(F St.) to Palm Ave. | Pavement Improvement | 2009-10-14 | 2009-10-21 | 2010-04-06 | 2010-04-06 | 917067.19 | 0.400 | 5287026
1190 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 03 | 5288026 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Folsom. The project is described as: Citywide Pavement Repair & ADA Improvements | Pavement Improvement | 2011-05-23 | 2011-06-06 | 2011-11-11 | 2011-12-30 | 1382085.99 |  | 5288026
1191 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 03 | 5288030 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Folsom. The project is described as: East Bidwell Street at Humbug-Willow Creek Parkway | Transportation Enhancements | 2010-04-26 | 2010-04-26 | 2011-01-13 | 2011-03-15 | 467422 | 1.000 | 5288030
1192 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 23 | 5289009 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Pismo Beach. The project is described as: In Pismo Beach along the ocean frontage. Improve walkway. Part 2. | Transportation Enhancements | 2010-04-26 | 2010-04-26 | 2011-04-01 | 2011-03-31 | 1100000 | 0.070 | 5289009
1193 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5291012 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Kerman. The project is described as: On Kearny Blvd, from Madera Ave to Del Norte Ave. | Pavement Improvement | 2010-07-27 | 2010-08-02 | 2010-11-24 | 2011-05-03 | 258753 | 0.500 | 5291012
1194 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO |  | 03 | 5293012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Galt. The project is described as: Various locations w/in the City of Galt | Pavement Improvement | 2009-08-11 | 2009-09-14 | 2009-12-11 | 2010-03-09 | 416140 | 1.000 | 5293012
1195 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO |  | 03 | 5293013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Galt. The project is described as: Eight locations in the City of Galt | Pavement Improvement | 2009-09-21 | 2009-09-23 | 2009-11-01 | 2010-03-24 | 298833 | 1.000 | 5293013
1196 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | 5295004 | This is a Pavement Resurfacing project by a local agency in the City of Greenfield. The project is described as: El Camino Real Storm Drain Improvements | Other | 2010-02-03 | 2010-02-16 | 2010-11-15 | 2010-12-01 | 340000 | 1.000 | 5295004
1197 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | 5296003 | This is a Pavement Resurfacing project by a local agency in the City of Gonzales. The project is described as: South Alta Street Reconstruction | Pavement Improvement | 2009-08-12 | 2009-08-12 | 2009-12-14 | 2009-12-14 | 171890.35 | 1.000 | 5296003
1198 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | 5297006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Live Oak. The project is described as: Apricot Street from N Street to Braodway. | Pavement Improvement | 2009-10-12 | 2009-10-13 | 2009-12-01 | 2009-12-18 | 205178 | 1.000 | 5297006
1199 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5299011 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Millbrae. The project is described as: Broadway, Magnolia | Pavement Improvement | 2009-08-31 | 2009-09-08 | 2009-10-01 | 2009-10-23 | 382000 | 0.500 | 5299011
1200 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5300008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Brentwood. The project is described as: Balfour Rd. | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2009-12-01 | 2009-10-30 | 1040777.16 | 1.000 | 5300008
1201 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | 5301007 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Orange Cove. The project is described as: Center Street from Park Boulevard to Adams Avenue | Pavement Improvement | 2009-09-21 | 2009-09-23 | 2010-04-01 | 2010-08-10 | 200866 | 0.500 | 5301007
1202 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5302006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the Port Hueneme. The project is described as: Street Rehabilitation in Port Hueneme | Pavement Improvement | 2010-07-14 | 2010-08-02 | 2010-10-18 | 2010-09-03 | 400000 | 1.400 | 5302006
1203 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 07 | 5303013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Pablo. The project is described as: San Pablo Ave. | Pavement Improvement | 2009-09-28 | 2009-10-05 | 2010-09-20 | 2010-09-20 | 694000 | 0.850 | 5303013
1204 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5304007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Capitola. The project is described as: 41st Ave between Capitola Road and Clares St | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2009-11-25 | 2009-11-25 | 230000 | 0.300 | 5304007
1205 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | 5305009 | This is a Pavement Resurfacing project by a local agency in the City of Huron. The project is described as: Railroad Avenue from Los Angeles to Lassen Avenue (SR 269) | Pavement Improvement | 2010-06-01 | 2010-06-04 | 2010-09-14 | 2010-09-29 | 159143.83 | 0.100 | 5305009
1206 | CALIFORNIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5306013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Campbell. The project is described as: East Campbell Avenue Improvement (Railway Ave to Union Ave) | Transportation Enhancements | 2010-03-22 | 2010-03-22 | 2011-05-31 | 2011-12-12 | 2260000 | 0.400 | 5306013
1207 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5306018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Campbell. The project is described as: S. Bascom Ave (Campisi Wy to El Solyo Av) | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2009-12-01 | 2009-12-04 | 548088.95 | 0.420 | 5306018
1208 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | SAN BERNARDINO-RIVERSIDE | 43 | 5307018 | This is a Preservation of Abandoned Railway Corridors project by a local agency in the City of Fontana. The project is described as: The project will construct a recreational trail in City of Fontana | Transportation Enhancements | 2011-01-18 | 2011-01-18 | 2011-06-02 | 2012-01-09 | 300001 | 1.000 | 5307018
1209 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5309013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Altos. The project is described as: San Antonio Road Resurfacing | Pavement Improvement | 2009-10-12 | 2009-10-12 | 2010-01-12 | 2010-01-12 | 220105.32 | 2.000 | 5309013
1210 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5310031 | This is a Pavement Resurfacing project by a local agency in the City of Buena Park. The project is described as: Knott Avenue from Crescent Avenue to La Palma Avenue | Pavement Improvement | 2010-04-06 | 2010-04-13 | 2010-06-15 | 2010-08-03 | 583276.41 | 0.530 | 5310031
1211 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5310034 | This is a Pavement Resurfacing project by a local agency in the City of Buena Park. The project is described as: Rehabilitation of approximately 0.5 miles of Knott Avenue from Lincoln Avenue to Crescent Avenue | Pavement Widening | 2011-06-30 | 2011-07-05 | 2011-10-28 | 2012-01-11 | 292313 |  | 5310034
1212 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5312071 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Costa Mesa. The project is described as: Southbound onramp area of the I-405 / Fairview Road interchange | Transportation Enhancements | 2009-11-02 | 2009-11-02 | 2010-03-01 | 2010-03-17 | 450357.69 | 2.300 | 5312071
1213 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5312074 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Costa Mesa. The project is described as: Santa Ana Avenue from 17th Street to 22nd Street | Pavement Improvement | 2010-01-20 | 2010-02-03 | 2010-05-27 | 2010-05-28 | 1100000 | 1.250 | 5312074
1214 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5312079 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Costa Mesa. The project is described as: WILSON STREET FROM NEWPORT BLVD. TO FAIRVIEW ROAD | Pavement Improvement | 2010-10-20 | 2010-11-01 | 2011-02-21 | 2011-01-12 | 291264.85 | 0.120 | 5312079
1215 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5312081 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Costa Mesa. The project is described as: Wilson Street Rehabilitation from harbor Boulevard to Anaheim | Pavement Improvement | 2011-01-19 | 2011-02-14 | 2011-05-13 | 2011-05-11 | 300000 |  | 5312081
1216 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5314007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Milpitas. The project is described as: S. Park Victoria Dr | Pavement Improvement | 2009-09-01 | 2009-09-02 | 2009-12-01 | 2010-01-05 | 735350.7 | 0.600 | 5314007
1217 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 5314008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Milpitas. The project is described as: Abbott Ave (Health St - Marylinn Dr) and Marylinn Dr (Abbott Ave - Main St) | Pavement Improvement | 2010-07-30 | 2010-08-03 | 2010-09-27 | 2010-10-25 | 702719 | 1.000 | 5314008
1218 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5315006 | This is a Pavement Resurfacing project by a local agency in the City of Lakewood. The project is described as: Bloomfield Ave: Del Amo Blvd to South City Limit ( 100' South of 215th St) | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2010-02-09 | 2010-02-09 | 565245.53 | 0.890 | 5315006
1219 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5315007 | This is a Pavement Resurfacing project by a local agency in the City of Lakewood. The project is described as: South Street: East City Limit to Lakewood Blvd | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2010-02-09 | 2010-02-09 | 1386695.61 | 0.830 | 5315007
1220 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5315008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lakewood. The project is described as: Centralia St Improvement Project (Bloomfield to Studebaker) | Pavement Improvement | 2010-11-29 | 2010-11-29 | 2011-03-31 | 2011-06-14 | 493058.86 |  | 5315008
1221 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5316006 | This is a Pavement Resurfacing project by a local agency in the City of Seaside. The project is described as: Del Monte Reconstruction | Pavement Improvement | 2009-09-10 | 2009-09-14 | 2010-03-01 | 2010-06-04 | 669839 | 1.000 | 5316006
1222 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5318025 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cupertino. The project is described as: Homestead Rd Rehab (Mary Ave to De Anza Blvd) | Pavement Improvement | 2009-10-05 | 2009-10-09 | 2010-05-03 | 2010-05-03 | 707000 | 0.810 | 5318025
1223 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5319012 | This is a Pavement Resurfacing project by a local agency in the City of La Palma. The project is described as: Orangethorpe Avenue from the west city limits at Moody Street to the east city limits at Valley View Street | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2010-12-01 | 2010-06-04 | 317875.08 | 1.000 | 5319012
1224 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5319013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Palma. The project is described as: Street Rehabilitation, Orangethorpe Av from Moody St to SR-91 and Valley View St from Ornagethorpe Av to Fresco Dr | Other | 2011-01-14 | 2011-01-27 | 2011-06-30 | 2011-02-28 | 214676.98 |  | 5319013
1225 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5321015 | This is a Pavement Resurfacing project by a local agency in the City of Anderson. The project is described as: 8 locations on various roads within the City | Pavement Improvement | 2009-09-03 | 2009-09-21 | 2009-11-01 | 2009-10-30 | 413491.59 | 2.940 | 5321015
1226 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5322035 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fremont. The project is described as: City Wide | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2009-12-01 | 2010-01-20 | 5907000 | 4.280 | 5322035
1227 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 10 | 5322040 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Fremont. The project is described as: Rehabilitate Osgood Road between Washington Boulevard and South Grimmer Boulevard. | Pavement Improvement | 2010-08-16 | 2010-08-16 | 2012-09-30 | 2012-09-20 | 1022422 |  | 5322040
1228 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5323018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Baldwin Park. The project is described as: Ramona Blvd: I-605 to Francisquito Ave | Pavement Improvement | 2010-08-11 | 2010-08-24 | 2012-05-30 | 2012-05-31 | 891148.36 | 0.500 | 5323018
1229 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5323019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Baldwin Park. The project is described as: Ramona Blvd: Francisquito Ave to Merced Ave | Pavement Improvement | 2010-08-04 | 2010-08-16 | 2011-04-07 | 2011-04-07 | 1320402.79 | 1.000 | 5323019
1230 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5324005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Los Altos Hills. The project is described as: Moody & Pagemill | Pavement Improvement | 2009-07-16 | 2009-07-20 | 2009-08-04 | 2009-08-04 | 316000 | 1.800 | 5324005
1231 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5325012 | This is a Pavement Resurfacing project by a local agency in the City of Cerritos. The project is described as: BLOOMFIELD AVENUE AND VARIOUS CITY STREETS | Pavement Improvement | 2010-02-02 | 2010-02-02 | 2010-06-01 | 2010-08-12 | 1072424.79 | 1.000 | 5325012
1232 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | SAN BERNARDINO-RIVERSIDE | 26 | 5326013 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Montclair. The project is described as: Mission Boulevard Corridor Improvement Project (Segment 8 in the City of Montclair) from Ada Avenue to Benson Avenue | Transportation Enhancements | 2010-06-15 | 2010-06-21 | 2010-12-31 | 2011-04-08 | 300000 | 0.500 | 5326013
1233 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5327012 | This is a Pavement Resurfacing project by a local agency in the City of Stanton. The project is described as: Dale Street from Katella Avenue to Cerritos Avenue | Pavement Improvement | 2010-02-25 | 2010-03-08 | 2010-12-01 | 2010-04-30 | 363924.03 | 0.500 | 5327012
1234 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5327013 | This is a Pavement Resurfacing project by a local agency in the City of Stanton. The project is described as: Dale St. Rehabilitation - Chapman Ave to SCL | Pavement Improvement | 2010-10-18 | 2010-10-27 | 2010-11-30 | 2010-11-05 | 105233.85 |  | 5327013
1235 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5328063 | This is a Pavement Resurfacing project by a local agency in the City of Garden Grove. The project is described as: To resurface 0.7 miles of Harbor Boulevard (an arterial highway) from Garden Grove to Chapman. | Pavement Improvement | 2010-03-18 | 2010-03-22 | 2010-12-31 | 2010-08-24 | 884512.1 | 0.700 | 5328063
1236 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 47 | 5330013 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Cypress. The project is described as: Moody Street from Cerritos Avenue to Lincoln Avenue | Transportation Enhancements | 2011-04-07 | 2011-04-11 | 2012-07-20 | 2012-04-26 | 500000 | 1.500 | 5330013
1237 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5330014 | This is a Pavement Resurfacing project by a local agency in the City of Cypress. The project is described as: Valley View Street from Cerritos to Katella Avenue | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-07-12 | 2010-08-23 | 442870.34 | 0.500 | 5330014
1238 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 38 | 5331011 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of La Puente. The project is described as: Hacienda Blvd from Nelson Ave to Amar Rd | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2010-03-30 | 2010-03-30 | 648601.44 | 0.900 | 5331011
1239 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5331012 | This is a Pavement Resurfacing project by a local agency in the City of La Puente. The project is described as: Glendora Ave. from Temple Ave. to Hacienda Blvd. | Pavement Improvement | 2009-11-19 | 2009-11-19 | 2010-03-31 | 2010-03-31 | 243828.18 | 0.400 | 5331012
1240 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5331015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Puente. The project is described as: Street Rehabilitation on Unruh Avenue and Loukelton Street | Pavement Improvement | 2011-01-17 | 2011-01-17 | 2011-04-30 | 2011-06-13 | 378568.38 |  | 5331015
1241 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5332014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Saratoga. The project is described as: Saratoga Avenue Overlay & Rehab | Pavement Improvement | 2009-11-09 | 2009-11-09 | 2010-05-20 | 2011-12-21 | 714000 | 1.300 | 5332014
1242 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5332015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Saratoga. The project is described as: Various Streets Rehabilitation | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-08-16 | 2010-08-20 | 137160 | 0.800 | 5332015
1243 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5334034 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Downey. The project is described as: LAKEWOOD BLVD. BETWEEN 5TH STREET/CECILIA STREET AND TELEGRAPH ROAD | Pavement Improvement | 2010-10-06 | 2010-10-18 | 2012-03-27 | 2012-03-27 | 3317000 | 5.800 | 5334034
1244 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5336012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Paramount. The project is described as: Downey Ave from Rosecrans Ave to Gardendale Street. Traffic Signal Improvement at Garfield Ave and Howery Street | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2010-06-01 | 2010-09-01 | 678100.17 | 0.760 | 5336012
1245 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5336013 | This is a Pavement Resurfacing project by a local agency in the City of Paramount. The project is described as: Rosecrans Ave from Garfield Ave. to 1135 feet west of Orange Ave. | Pavement Improvement | 2009-10-12 | 2009-10-12 | 2010-06-01 | 2010-06-25 | 586087.8 | 0.720 | 5336013
1246 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5336014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Paramount. The project is described as: Somerset Blvd : Orange Ave to 1160' west of San Jose Ave, Orange Ave: Alondra Blvd to Jackson St | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-07-31 | 2010-09-07 | 435812.03 | 0.470 | 5336014
1247 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5337009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Escalon. The project is described as: West Yosemite Ave Rehabilitation Project- from Escalon Ave to stanislaus street. | Pavement Improvement | 2010-03-15 | 2010-03-29 | 2010-05-14 | 2010-06-10 | 149714 | 0.250 | 5337009
1248 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5338041 | This is a Pavement Resurfacing project by a local agency in the City of Westminster. The project is described as: Brookhurst Street from Bolsa Avenue to Hazard Avenue | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2010-02-01 | 2010-04-28 | 813214 | 0.500 | 5338041
1249 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5339001 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Monte Sereno. The project is described as: Daves Avenue (Winchester Blvd - Carril Ct),(Kevin Ln - city limits),(550ft north of Constitution Ave) | Pavement Improvement | 2009-08-10 | 2009-08-17 | 2009-11-01 | 2009-11-17 | 94000 | 0.500 | 5339001
1250 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5340012 | This is a Pavement Resurfacing project by a local agency in the City of Santa Fe Springs. The project is described as: VARIOUS LOCATIONS | Pavement Improvement | 2010-01-11 | 2010-01-11 | 2010-04-01 | 2010-04-19 | 528000 | 0.530 | 5340012
1251 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 46 | 5341028 | This is a Pavement Resurfacing project by a local agency in the City of Fountain Valley. The project is described as: Warner Avenue from Magnolia Street to Bushard Street and Bushard Street from Ellis Avenue to Talbert Avenue | Pavement Improvement | 2010-04-05 | 2010-04-15 | 2010-06-04 | 2010-06-11 | 619157 | 1.000 | 5341028
1252 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 20 | 5343002 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Mcfarland. The project is described as: Intersection of West Perkins Ave at overpass | Pavement Improvement | 2009-11-13 | 2009-11-16 | 2010-01-01 | 2010-04-16 | 209870.03 | 0.050 | 5343002
1253 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5345005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Irwindale. The project is described as: Gladstone Street from Irwindale Avenue to East City Limit | Pavement Improvement | 2010-03-15 | 2010-03-17 | 2010-06-30 | 2010-06-29 | 500000 | 0.300 | 5345005
1254 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5346009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Duarte. The project is described as: Huntington Drive from West City limits to East City limits | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2010-08-27 | 2010-09-15 | 679000 | 2.460 | 5346009
1255 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5347032 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Norwalk. The project is described as: FRONT STREET FROM SAN ANTONIO DRIVE TO ROSECRANS AVE. | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2010-05-18 | 2010-05-18 | 370772.31 | 0.770 | 5347032
1256 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5347033 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Norwalk. The project is described as: FIRESTONE BLVD. FROM HOXIE AVE. TO IMPERIAL HIGHWAY | Pavement Improvement | 2010-04-01 | 2010-05-03 | 2010-08-01 | 2010-12-15 | 623000 | 0.910 | 5347033
1257 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5347034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Norwalk. The project is described as: STUDEBAKER ROAD FROM IMPERIAL HIGHWAY TO ALONDRA. | Pavement Improvement | 2010-02-01 | 2010-04-12 | 2011-02-09 | 2011-01-31 | 1492417.88 | 2.000 | 5347034
1258 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5348016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Bellflower. The project is described as: Downey Ave : North City Limit to South City Limit | Pavement Improvement | 2010-05-26 | 2010-06-14 | 2011-02-14 | 2011-02-14 | 434918.32 | 0.500 | 5348016
1259 | CALIFORNIA | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5348018 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Bellflower. The project is described as: West Branch Greenway: Lakewood Blvd to San Gabriel River | Transportation Enhancements | 2011-07-21 | 2011-07-21 | 2012-10-01 | 2012-01-22 | 823313 | 2.500 | 5348018
1260 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 5349005 | This is a Traffic Management Engineering project by a local agency in the City of Rolling Hills Estates. The project is described as: Palos Verdes Dr N & Crenshaw Blvd | Safety/Traffic Management | 2010-02-22 | 2010-02-22 | 2010-07-15 | 2010-09-13 | 53758.59 | 0.100 | 5349005
1261 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 5349006 | This is a Safety project by a local agency in the City of Rolling Hills Estates. The project is described as: Citywide Various Locations | Safety/Traffic Management | 2010-07-13 | 2010-10-11 | 2010-12-31 | 2010-12-22 | 65472 | 0.100 | 5349006
1262 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 46 | 5349007 | This is a Pavement Resurfacing project by a local agency in the City of Rolling Hills Estates. The project is described as: Palos Verdes Dr. North : Crenshaw Blvd and Rolling Hills Rd | Pavement Improvement | 2010-07-13 | 2010-07-26 | 2010-09-30 | 2010-12-22 | 380089 | 0.600 | 5349007
1263 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5350016 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pacifica. The project is described as: Manor, Oddstad, Monterey | Pavement Improvement | 2009-09-21 | 2009-09-28 | 2009-12-04 | 2010-12-13 | 677000 | 2.000 | 5350016
1264 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 38 | 5351017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pico Rivera. The project is described as: Beverly Blvd : Paramount Blvd. to 510' East of Abbeywood Ave. | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2011-11-01 | 2011-11-30 | 1960000 | 1.260 | 5351017
1265 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5352011 | This is a Pavement Resurfacing project by a local agency in the City of South El Monte. The project is described as: Potrero Ave. from Rush St. to south end (City Limits) | Pavement Improvement | 2010-09-07 | 2010-09-07 | 2010-11-10 | 2010-11-09 | 580641.41 | 0.600 | 5352011
1266 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 32 | 5353005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Walnut. The project is described as: Nogales Street from South City Limits to Amar Road | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2010-06-01 | 2010-03-12 | 755431 | 0.500 | 5353005
1267 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5355021 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Artesia. The project is described as: SOUTH STREET BETWEEN JERSEY AVE. AND PONEER BLVD. | Transportation Enhancements | 2009-11-09 | 2009-11-09 | 2010-03-01 | 2010-05-03 | 402866 | 0.500 | 5355021
1268 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5357005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Half Moon Bay. The project is described as: Main St, Purissma | Pavement Improvement | 2009-08-07 | 2009-08-15 | 2010-02-01 | 2010-04-20 | 210000 | 0.500 | 5357005
1269 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5358010 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Rosemead. The project is described as: Various Locations Citywide | Pavement Improvement | 2010-04-19 | 2010-05-10 | 2010-07-30 | 2010-10-15 | 1684000 | 5.150 | 5358010
1270 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO | SAN LUIS OBISPO | 23 | 5359015 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Grover Beach. The project is described as: West Grand Avenue | Transportation Enhancements | 2009-12-22 | 2010-03-23 | 2010-06-15 | 2011-01-21 | 856000 | 0.170 | 5359015
1271 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5360008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lawndale. The project is described as: Rosecrans Av: 430 ft E of Inglewood Ave to 100 ft W of Hawthorne Bl & 280 ft E of Hawthorne Bl to 110 ft W of Prairie Av | Pavement Improvement | 2009-12-01 | 2009-12-14 | 2010-03-01 | 2010-04-19 | 986997 | 1.000 | 5360008
1272 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5361022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Novato. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2010-05-01 | 2010-09-28 | 1062000 | 6.000 | 5361022
1273 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 38 | 5362014 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Commerce. The project is described as: Intersection of Garfield Ave and Slauson Ave. | Pavement Improvement | 2009-11-28 | 2009-11-28 | 2010-06-01 | 2011-02-03 | 500000 | 0.100 | 5362014
1274 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5363010 | This is a Pavement Resurfacing project by a local agency in the City of Los Alamitos. The project is described as: Katella Avenue from Siboney Street to Walker Street | Pavement Improvement | 2010-03-15 | 2010-03-30 | 2010-05-24 | 2010-07-21 | 342480.98 | 0.400 | 5363010
1275 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5364005 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Mirada. The project is described as: LA MIRADA BLVD FROM LEFFINGWELL ROAD TO OAKWOOD LANE. | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-05-05 | 2010-05-05 | 731018.52 | 0.800 | 5364005
1276 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5364006 | This is a Pavement Resurfacing project by a local agency in the City of La Mirada. The project is described as: STAGE RD. FROM ALONDRA BLVD. TO EAST CITY LIMIT. | Pavement Improvement | 2010-05-10 | 2010-06-21 | 2010-08-09 | 2010-11-23 | 378109.71 | 1.100 | 5364006
1277 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5365003 | This is a Safety project by a local agency in the City of Temple City. The project is described as: TEMPLE CITY BLVD @ ELLIS LANE | Safety/Traffic Management | 2010-01-22 | 2010-04-26 | 2010-06-14 | 2010-06-14 | 118108.65 | 1.000 | 5365003
1278 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5365004 | This is a Pavement Resurfacing project by a local agency in the City of Temple City. The project is described as: Freer Street from Santa Anita Avenue to Arden Drive | Pavement Improvement | 2010-01-26 | 2010-02-15 | 2010-04-14 | 2010-04-14 | 599000 | 0.800 | 5365004
1279 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5365005 | This is a Traffic Management Engineering project by a local agency in the City of Temple City. The project is described as: Rosemead Bl @ intersection Longden Ave & Broadway | Pavement Improvement | 2010-05-10 | 2010-07-12 | 2010-12-16 | 2010-12-16 | 124174 | 1.000 | 5365005
1280 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 26 | 5367006 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Dimas. The project is described as: San Dimas Ave: Gladstone St to Foothill Blvd | Pavement Improvement | 2009-10-26 | 2009-10-29 | 2010-07-30 | 2011-12-15 | 1085000 | 0.700 | 5367006
1281 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5369008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cudahy. The project is described as: Live Oak Street from Wilcox Ave to Salt Lake Ave | Pavement Improvement | 2010-07-27 | 2010-08-02 | 2010-12-30 | 2011-01-14 | 663000 | 1.300 | 5369008
1282 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5370021 | This is a Pavement Resurfacing project by a local agency in the City of Arvin. The project is described as: Campus Drive, SR 223 to Grapevine Ave | Pavement Improvement | 2010-07-15 | 2010-08-10 | 2010-10-01 | 2010-10-28 | 421087.33 | 0.250 | 5370021
1283 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5371005 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Weed. The project is described as: City of Weed -California, Morris, Park Streets. North Davis and Shasta Aves | Pavement Improvement | 2010-04-20 | 2010-06-24 | 2010-06-15 | 2010-06-28 | 498591.12 | 1.630 | 5371005
1284 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5372012 | This is a Pavement Resurfacing project by a local agency in the City of San Juan Capistrano. The project is described as: Camino Capistrano from San Juan Creek Road to La Zanja Street | Pavement Improvement | 2010-05-17 | 2010-05-18 | 2013-12-31 |  | 500000 | 1.300 | 5372012
1285 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5373012 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Bell Gardens. The project is described as: Garfield Ave: Florance Ave to Loveland St and Loveland St: Garfield Ave to Suva St | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-01-13 | 2010-01-13 | 414700 | 1.000 | 5373012
1286 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5373013 | This is a Pavement Resurfacing project by a local agency in the City of Bell Gardens. The project is described as: Florence Ave: El Selinda Ave to Emil Ave & Florence Place: Florence Ave to Garfield Ave | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2010-02-02 | 2010-02-02 | 731929.65 | 0.700 | 5373013
1287 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 10 | 5375021 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Pleasant Hill. The project is described as: Contra Costa Blvd. | Pavement Improvement | 2009-08-19 | 2009-08-19 | 2010-10-29 | 2010-11-01 | 842000 | 0.710 | 5375021
1288 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5376008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Brisbane. The project is described as: Bayshore Blvd Overlay fr Geneva to NB 101 off Ramp | Pavement Improvement | 2009-07-10 | 2009-07-13 | 2009-09-29 | 2009-09-29 | 131000 | 0.100 | 5376008
1289 | CALIFORNIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5377006 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Villa Park. The project is described as: Taft Avenue from Lemon Street to Cannon Street | Transportation Enhancements | 2010-09-20 | 2010-09-20 | 2010-11-24 | 2011-05-24 | 223983 | 1.000 | 5377006
1290 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 40 | 5377012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Villa Park. The project is described as: Santiago Boulevard from Prado Woods Drive to Sycamore Avenue and Lemon Street from Villa Park Road to Robin Way | Pavement Improvement | 2010-01-20 | 2010-02-03 | 2010-02-28 | 2010-03-10 | 435500.96 | 2.200 | 5377012
1291 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5378019 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Palmdale. The project is described as: Citywide Various Arterial streets | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2010-05-01 | 2010-09-01 | 4072751.09 | 24.580 | 5378019
1292 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5379017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rohnert Park. The project is described as: Redwood Dr., Commerce Blvd., Snyder Ln., Southwest Blvd., Seed Farm Dr., Enterprise Dr., State Farm Dr. | Pavement Improvement | 2009-08-13 | 2009-08-27 | 2012-04-30 | 2012-02-14 | 869000 | 3.210 | 5379017
1293 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 06 | 5383007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Cotati. The project is described as: Old Redwood Hwy, Eucalyptus to Lasker | Pavement Improvement | 2009-11-09 | 2009-11-09 | 2010-01-01 | 2010-03-10 | 492445.74 | 0.340 | 5383007
1294 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5385038 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Ridgecrest. The project is described as: College Heights Boulevard from Franklin Avenue to Dolphin Avenue | Pavement Improvement | 2010-11-01 | 2010-11-02 | 2010-12-17 | 2011-06-17 | 405049.15 | 0.250 | 5385038
1295 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5385040 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Ridgecrest. The project is described as: South College Heights Boulevard from South China Lake Boulevard to West Dolphin Avenue | Pavement Improvement | 2010-11-01 | 2010-11-02 | 2010-12-17 | 2011-06-17 | 520359.96 | 0.330 | 5385040
1296 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 10 | 5386009 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Clayton. The project is described as: Clayton Rd. | Pavement Improvement | 2009-08-18 | 2009-08-24 | 2009-10-01 | 2009-10-06 | 355854 | 1.100 | 5386009
1297 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 39 | 5387009 | This is a Pavement Resurfacing project by a local agency in the City of Hawaiian Gardens. The project is described as: NORWALK BL: CARSON STREET TO SOUTH CITY LIMIT | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-12-29 | 2009-12-29 | 428059.66 | 0.560 | 5387009
1298 | CALIFORNIA | Completed | C200,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5388008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Tiburon. The project is described as: In Tiburon at Reed Ranch Road and Ridge Road Overlay. | Pavement Improvement | 2009-10-21 | 2009-11-02 | 2009-09-01 | 2009-12-24 | 203000 | 1.000 | 5388008
1299 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5390004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Portola Valley. The project is described as: Portola Rd., Cervantes Rd., Westridge Dr. | Pavement Improvement | 2009-09-18 | 2009-09-24 | 2009-12-01 | 2009-12-18 | 196000 | 0.600 | 5390004
1300 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO | SAN LUIS OBISPO | 22 | 5391012 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Morro Bay. The project is described as: North Main Street | Transportation Enhancements | 2010-09-07 | 2010-10-04 | 2010-11-30 | 2011-06-14 | 480000 | 1.800 | 5391012
1301 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | THOUSAND OAKS | 23 | 5392039 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Thousand Oaks. The project is described as: CONEJO CREEK PARK FROM INTERSECTION OF JANSS ROAD /PAIGE LANE TO SOUTH SIDE OF PARK. | Transportation Enhancements | 2010-06-25 | 2010-06-28 | 2011-03-31 | 2011-05-19 | 1071356 | 1.320 | 5392039
1302 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | THOUSAND OAKS | 24 | 5392040 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Thousand Oaks. The project is described as: ROUTE 101 AND ROUTE 23 INTERCHANGE | Other | 2010-01-04 | 2010-01-04 | 2013-06-30 |  | 5196325 | 0.750 | 5392040
1303 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | THOUSAND OAKS | 23 | 5392041 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Thousand Oaks. The project is described as: Rehabilitation of Moorpark Road between Wilbur Road and Columbia | Pavement Improvement | 2010-10-04 | 2010-10-19 | 2013-02-19 |  | 1091194 | 2.310 | 5392041
1304 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5393020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Camarillo. The project is described as: VARIOUS LOCATIONS | Pavement Improvement | 2009-11-23 | 2009-12-07 | 2010-03-01 | 2010-02-24 | 1099966 | 2.450 | 5393020
1305 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5393023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Camarillo. The project is described as: Annual Pavement Rehabilitation at Various Arterial Streets | Pavement Improvement | 2010-08-04 | 2010-09-13 | 2011-02-28 | 2011-03-09 | 519192 | 2.700 | 5393023
1306 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA | SAN FRANCISCO-OAKLAND, CA | 01 | 5395001 | This is a Safety project by a local agency in the City of Yountville. The project is described as: Construct Class I Bike Path parallel and inside the east Caltrans right-of-way of northbound SR 29 from California Drive to Madison St. | Transportation Enhancements | 2010-03-17 | 2010-03-29 | 2010-10-01 | 2010-11-02 | 1000000 | 0.800 | 5395001
1307 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5396006 | This is a Pavement Resurfacing project by a local agency in the City of Rio Dell. The project is described as: Wildwood Ave from Elm St to Eagle Prairie Bridge. | Pavement Improvement | 2010-06-21 | 2010-07-06 | 2010-11-30 | 2010-11-27 | 576000 | 0.300 | 5396006
1308 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5397009 | This is a Pavement Resurfacing project by a local agency in the City of Carpinteria. The project is described as: In the City of Carpinteria on various streets | Pavement Improvement | 2010-07-20 | 2010-08-09 | 2010-09-15 | 2010-12-03 | 596535 | 1.800 | 5397009
1309 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5399014 | This is a Traffic Management Engineering project by a local agency in the City of California City. The project is described as: Intersection of California City Boulevard, Randsburg-Mojave Road, and Proctor Boulevard | Safety/Traffic Management | 2010-04-22 | 2010-05-05 | 2010-07-13 | 2010-08-10 | 542341.69 | 1.000 | 5399014
1310 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ |  | 17 | 5400014 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Scotts Valley. The project is described as: Road preservation | Pavement Improvement | 2010-04-01 | 2010-04-05 | 2010-07-30 | 2010-07-30 | 115000 | 3.100 | 5400014
1311 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5400015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Scotts Valley. The project is described as: Bean Creek Road from Scotts Valley Drive to Bluebonnet Lane | Pavement Improvement | 2010-04-05 | 2010-06-01 | 2010-08-30 | 2010-08-30 | 160000 | 0.400 | 5400015
1312 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | 5402026 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Yorba Linda. The project is described as: Village Center Drive from Manzanita Avenue to Fairmont Boulevard | Pavement Improvement | 2010-03-22 | 2010-03-29 | 2010-06-01 | 2010-04-30 | 272427.14 | 1.000 | 5402026
1313 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | 5402028 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Yorba Linda. The project is described as: Pavement Rehabilitation from Casa Loma to Van Buren | Pavement Improvement | 2011-02-04 | 2011-02-04 | 2011-04-08 | 2011-03-16 | 199640 |  | 5402028
1314 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5403014 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Carson. The project is described as: Broadway: Griffith St to Alondra Bl | Pavement Improvement | 2009-11-02 | 2009-11-16 | 2010-04-23 | 2010-06-25 | 2000000 | 0.400 | 5403014
1315 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 10 | 5404020 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lafayette. The project is described as: Lafayette Pavement Rehab. | Pavement Improvement | 2009-08-04 | 2009-08-31 | 2009-10-16 | 2009-10-16 | 706277.78 | 2.250 | 5404020
1316 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5405050 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Simi Valley. The project is described as: VARIOUS LOCATIONS | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2010-10-29 | 2010-08-05 | 1080532 | 2.350 | 5405050
1317 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5405056 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Simi Valley. The project is described as: Major Street Rehabilitation, various locations | Pavement Improvement | 2010-03-22 | 2010-03-23 | 2010-05-21 | 2010-06-09 | 979779.01 | 1.000 | 5405056
1318 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 19 | 5406019 | This is a Pavement Resurfacing project by a local agency in the City of Waterford. The project is described as: Bentley Street (I Street to Skyline Blvd), Bonnie Brae Ave. (F Street to Tim Bell Rd), Tim Bell Road (Yosemite to N. City Limits), F Street. | Pavement Improvement | 2010-04-08 | 2010-04-13 | 2010-06-11 | 2010-06-25 | 610770 | 2.650 | 5406019
1319 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | 5409015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Foster City. The project is described as: Foster City Blvd from Foster City Blvd Bridge to Beach Park Blvd | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2009-11-01 | 2009-09-30 | 378455.79 | 0.500 | 5409015
1320 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | 5410065 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Irvine. The project is described as: Jeffrey Road / I-405 bicycle and pedestrian bridge | Transportation Enhancements | 2010-02-04 | 2010-03-15 | 2010-10-14 | 2011-05-11 | 344073.08 | 1.000 | 5410065
1321 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5410069 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Irvine. The project is described as: Red Hill Avenue from Reynolds Avenue to Deere Avenue | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-04-01 | 2010-05-06 | 1954172.84 | 0.670 | 5410069
1322 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 36 | 5413010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rancho Palos Verdes. The project is described as: Arterial St : Hawthorne Blvd,PV DR West , PV Dr. South | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2010-06-01 | 2010-08-27 | 1262000 | 4.470 | 5413010
1323 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 10 | 5415010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Moraga. The project is described as: Moraga Rd. | Pavement Improvement | 2009-09-15 | 2009-09-15 | 2010-04-30 | 2011-05-07 | 609000 | 1.100 | 5415010
1324 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5416006 | This is a Pavement Resurfacing project by a local agency in the City of Marina. The project is described as: Improvements include bike lanes, sidewalk, landscaping and resurfacing | Pavement Improvement | 2009-07-10 | 2009-07-13 | 2009-08-14 | 2009-12-11 | 375548 | 1.000 | 5416006
1325 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5416007 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Marina. The project is described as: Infill sidewalks at various locations near schools. | Transportation Enhancements | 2010-06-04 | 2010-06-14 | 2010-06-08 | 2010-08-11 | 259500 | 1.000 | 5416007
1326 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 27 | 5417015 | This is a Pavement Resurfacing project by a local agency in the City of La Canada Flintridge. The project is described as: Various City Street | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2010-07-15 | 2010-07-16 | 964700 | 2.160 | 5417015
1327 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 26 | 5417017 | This is a Pavement Resurfacing project by a local agency in the City of La Canada Flintridge. The project is described as: RESURFACING OF VARIOUS CITY STREETS IN CITY OF LA CANADA FLINTRIDGE | Pavement Improvement | 2010-11-13 | 2010-11-13 | 2011-04-30 | 2011-05-18 | 165300 |  | 5417017
1328 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5419020 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Lancaster. The project is described as: North half of Ave. K: 50th St. W to 52nd St. W. 50th St. W. : Ave. K to Ave. K-4 | Pavement Improvement | 2009-10-19 | 2009-10-26 | 2010-05-01 | 2010-03-08 | 303338.48 | 0.500 | 5419020
1329 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5419021 | This is a Pavement Resurfacing project by a local agency in the City of Lancaster. The project is described as: 40th St W:Ave J - Ave I, Ave K:22nd St E - 50th St E, 30th St E:Ave J-4 to J-8 & 60th St W: J-4 to J-8 | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2010-06-01 | 2010-09-17 | 2226367.62 | 3.800 | 5419021
1330 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5419023 | This is a Traffic Management Engineering project by a local agency in the City of Lancaster. The project is described as: Ave. L-8 & 30th St. W. and Ave L & 35th St. W. | Pavement Improvement | 2009-12-30 | 2010-01-04 | 2010-05-01 | 2010-04-13 | 1241603.58 | 0.200 | 5419023
1331 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | SAN BERNARDINO-RIVERSIDE | 43 | 5420018 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Rancho Cucamonga. The project is described as: Church Street from Rochester Avenue to Hyssop Drive | Transportation Enhancements | 2010-06-07 | 2010-06-14 | 2010-08-23 | 2010-09-03 | 100000 | 0.200 | 5420018
1332 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5422002 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of La Habra Heights. The project is described as: HACIENDA ROAD FROM NORTH CITY LIMIT TO AVACADO CREST AND HACIENDA ROAD TO FULLERTON ROAD. | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2010-04-16 | 2010-07-08 | 500000 | 4.160 | 5422002
1333 | CALIFORNIA | Completed | C220,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | 5423026 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Atascadero. The project is described as: Downtown Streetscape | Transportation Enhancements | 2011-05-02 | 2011-05-02 | 2011-10-03 | 2011-11-05 | 684999 | 0.250 | 5423026
1334 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | 5423027 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Atascadero. The project is described as: Santa Rosa Road | Pavement Improvement | 2010-06-10 | 2010-07-05 | 2010-08-23 | 2011-09-01 | 513000 | 1.250 | 5423027
1335 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5424007 | This is a Pavement Resurfacing project by a local agency in the City of Avenal. The project is described as: On San Joaquin St, from Seventh Ave to Skyline Blvd (SR 269). | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-12-10 | 2010-12-10 | 231946.4 | 1.000 | 5424007
1336 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5424008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Avenal. The project is described as: On San Joaquin Street, from 3rd Avenue to 7th Avenue. | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-12-10 | 2010-12-10 | 246529 | 1.000 | 5424008
1337 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 02 | 5425020 | This is a Pavement Resurfacing project by a local agency in the City of Paradise. The project is described as: Pentz Rd, Skyway, Clark Rd, Pearson Rd | Pavement Improvement | 2009-09-25 | 2009-10-20 | 2010-12-01 | 2011-07-05 | 1497943.04 | 5.100 | 5425020
1338 | CALIFORNIA | Completed | C250,C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LAKE |  | 01 | 5427019 | This is a Pavement Resurfacing project by a local agency in the City of Clearlake. The project is described as: Various Roads | Pavement Improvement | 2009-09-10 | 2009-09-21 | 2009-10-23 | 2009-10-23 | 813600 | 1.370 | 5427019
1339 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 34 | 5431006 | This is a Pavement Resurfacing project by a local agency in the City of Westlake Village. The project is described as: LINDERO CYN RD, AGOURA RD & LAKEVIEW CYN RD | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2010-06-18 | 2010-07-14 | 494220.32 | 1.000 | 5431006
1340 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 11 | 5434018 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Danville. The project is described as: Diablo Rd/Green Valley Rd | Pavement Improvement | 2009-10-08 | 2009-10-19 | 2009-12-23 | 2010-10-12 | 871614 | 2.100 | 5434018
1341 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5435016 | This is a Bridge Rehabilitation, Added Capacity project by a local agency in the City of Agoura Hills. The project is described as: REYES ADOBE ROAD INTERCHANGE @ US 101 FROM PM 36.1 TO 36.3. | Pavement Widening | 2009-10-01 | 2009-10-14 | 2012-10-01 | 2012-10-10 | 690000 | 0.200 | 5435016
1342 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5436015 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Moorpark. The project is described as: MOUNTAIN TRAIL STREET FROM TIERRA REJADA ROAD TO SUNSETRIDGE ROAD. | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-09-24 | 2011-05-04 | 618357.75 | 0.450 | 5436015
1343 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | CONCORD | 11 | 5437022 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of San Ramon. The project is described as: San Ramon Valley Blvd. | Pavement Improvement | 2009-10-01 | 2009-10-01 | 2010-03-01 | 2010-03-31 | 1122000 | 0.880 | 5437022
1344 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5438008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of East Palo Alto. The project is described as: Bay Rd, Newbridge, Pulgas, Donnohoe, University, Woodland | Pavement Improvement | 2009-11-04 | 2009-12-21 | 2010-05-28 | 2010-05-15 | 421000 | 1.900 | 5438008
1345 | CALIFORNIA | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONO |  | 25 | 5439023 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Mammoth Lakes. The project is described as: Lake Mary Road from Horseshoe Lake to Minaret Road | Transportation Enhancements | 2010-09-13 | 2010-09-20 | 2011-05-28 | 2011-07-06 | 182488.44 | 1.000 | 5439023
1346 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 29 | 5440008 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of West Hollywood. The project is described as: Sunset Blvd.: East City limits to West City limits | Pavement Improvement | 2010-01-12 | 2010-01-12 | 2010-12-01 | 2011-01-07 | 1105000 | 1.700 | 5440008
1347 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | 5443006 | This is a Pavement Resurfacing project by a local agency in the City of Solvang. The project is described as: 0.75 miles of pavement overlay on Alisal Road | Pavement Improvement | 2009-10-28 | 2009-11-12 | 2009-12-24 | 2009-12-15 | 143988 | 0.750 | 5443006
1348 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5444013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Orinda. The project is described as: Charles Hill Rd/Honey Hill Rd/Miner Rd | Pavement Improvement | 2009-10-12 | 2009-10-15 | 2009-12-11 | 2009-12-11 | 318538.99 | 0.900 | 5444013
1349 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 01 | 5447025 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of West Sacramento. The project is described as: Sacramento Avenue, Jefferson Boulevard, F Street | Pavement Improvement | 2010-06-10 | 2010-06-10 | 2011-07-15 | 2011-12-02 | 635802 | 1.000 | 5447025
1350 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450047 | This is a Safety project by a local agency in the City of Santa Clarita. The project is described as: Newhall Ave at Sierra Highway | Pavement Improvement | 2009-10-12 | 2009-10-12 | 2009-12-01 | 2010-01-25 | 282101 | 0.200 | 5450047
1351 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clarita. The project is described as: Soledad Cyn Rd: Sand Cyn Rd to E. side of River Circle Dr. | Pavement Improvement | 2009-09-30 | 2009-09-30 | 2009-12-01 | 2010-07-13 | 1297493 | 1.500 | 5450048
1352 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450049 | This is a Safety project by a local agency in the City of Santa Clarita. The project is described as: White Cnyn Rd. @ Soledad Cnyn Rd. | Pavement Improvement | 2010-03-10 | 2010-03-19 | 2010-05-14 | 2010-05-14 | 429027 | 0.100 | 5450049
1353 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450050 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clarita. The project is described as: McBean Pkwy: Newhall Ranch Rd to Decoro Dr and Soledad Cyn Rd: E. side of River Circle Dr to Sierra Hwy | Pavement Improvement | 2009-09-30 | 2009-09-30 | 2009-12-01 | 2010-07-13 | 1361858 | 1.500 | 5450050
1354 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 25 | 5450051 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Santa Clarita. The project is described as: Various Bridge No's. 53C-0469 , 0478 , 1024 , 1028 , 1999 | Pavement Improvement | 2009-11-30 | 2009-12-09 | 2010-01-29 | 2010-03-11 | 365878 | 0.280 | 5450051
1355 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 42 | 5451026 | This is a Pavement Resurfacing project by a local agency in the City of Mission Viejo. The project is described as: Overlay of Portions of Alicia, Trabuco and Olympiad | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2010-03-23 | 2010-06-04 | 898537 | 2.200 | 5451026
1356 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5454022 | This is a Pavement Resurfacing project by a local agency in the City of Dana Point. The project is described as: Del Prado from Golden Lantern Street to Copper Lantern Street and Stonehill Drive from Seaside Drive to the east city limits | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2010-05-17 | 2010-05-27 | 396228 | 0.830 | 5454022
1357 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 42 | 5455013 | This is a Pavement Resurfacing project by a local agency in the City of Diamond Bar. The project is described as: Various Locations | Pavement Improvement | 2009-09-23 | 2009-09-23 | 2009-12-01 | 2010-06-07 | 1748978.99 | 10.000 | 5455013
1358 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5456010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Lathrop. The project is described as: In the City of Lathrop Rehabilitate Harlan Road, Phase 1A and Phase 1B | Pavement Improvement | 2009-11-24 | 2010-04-26 | 2010-08-01 | 2010-07-23 | 289337.35 | 0.420 | 5456010
1359 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5456011 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Lathrop. The project is described as: Golden Valley Parkway from Lathrop rd south to River Islands Parkway | Transportation Enhancements | 2010-06-08 | 2010-06-08 | 2010-11-30 | 2011-03-11 | 969100.53 | 1.000 | 5456011
1360 | CALIFORNIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5458010 | This is a Landscaping and Other Scenic Beautification project by a local agency in the City of Laguna Niguel. The project is described as: Camino Capistrano from Paseo de Colinas to the north city limits | Transportation Enhancements | 2010-07-19 | 2010-07-19 | 2010-10-15 | 2010-11-09 | 849339.58 | 1.500 | 5458010
1361 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5458014 | This is a Pavement Resurfacing project by a local agency in the City of Laguna Niguel. The project is described as: Aliso Creek Road from Alicia Parkway to La Paz Road | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-04-23 | 2010-04-29 | 549010 | 0.500 | 5458014
1362 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5462012 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Malibu. The project is described as: MALIBU CANYON RD: PACIFIC COAST HWY TO MALIBU CITY LIMITS | Pavement Improvement | 2010-02-01 | 2010-03-01 | 2010-05-10 | 2010-06-14 | 425058.26 | 1.250 | 5462012
1363 | CALIFORNIA | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5463014 | This is a Traffic Management Engineering project by a local agency in the City of Calabasas. The project is described as: LAS VIRGENES RD, MUREA RD AND CALABASAS RD | Other | 2010-04-28 | 2010-05-03 | 2010-09-15 | 2011-05-31 | 940744.98 | 3.950 | 5463014
1364 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5463015 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Calabasas. The project is described as: BETWEEN A.E. WRIGHT MIDDLE SCHOOL AND LOST HILLS RD ACROSS LAS VIRGENES CREEK AT COLD SPRINGS ST. | Transportation Enhancements | 2010-07-30 | 2010-08-02 | 2011-02-23 | 2011-02-23 | 649999.99 | 0.100 | 5463015
1365 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | STATEWIDE | 45 | 5464029 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the City of Murrieta. The project is described as: I-215 / Clinton Keith Road interchange, Br. No. 56-0651 | Bridge Improvement | 2009-12-18 | 2009-12-18 | 2011-04-01 | 2011-09-01 | 9999981 | 1.100 | 5464029
1366 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5468013 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Laguna Hills. The project is described as: Laguna Hills Drive from Moulton Parkway to Paseo de Valencia | Pavement Improvement | 2009-12-07 | 2009-12-14 | 2010-06-01 | 2010-06-09 | 500000 | 0.720 | 5468013
1367 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5469013 | This is a Pavement Resurfacing project by a local agency in the City of Lake Forest. The project is described as: Trabuco Road from the south city limits with Mission Viejo to Lake Forest Drive | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2009-12-01 | 2010-01-06 | 603342.54 | 1.100 | 5469013
1368 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA | STATEWIDE | 01 | 5470007 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of American Canyon. The project is described as: American Canyon Road West - SR 29 to Wetlands Edge Road | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2010-03-01 | 2010-03-19 | 320000 | 0.500 | 5470007
1369 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | 01 | 5472012 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Windsor. The project is described as: Los Amigos Road | Pavement Improvement | 2009-08-25 | 2009-08-26 | 2009-10-01 | 2009-09-30 | 388799.24 | 0.750 | 5472012
1370 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA | SANTA ROSA | Multiple | 5472014 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Windsor. The project is described as: Old Redwood Highway from Joe Rodota Way to Bell Road. | Transportation Enhancements | 2010-04-01 | 2010-04-26 | 2010-07-23 | 2010-08-11 | 245079 | 0.250 | 5472014
1371 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5473009 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of Truckee. The project is described as: Legacy Bike Trail from Riverview Sports Park to Historical Overlook Site | Transportation Enhancements | 2010-06-03 | 2010-06-04 | 2010-11-15 | 2010-11-09 | 633332 | 0.740 | 5473009
1372 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5474013 | This is a Pavement Resurfacing project by a local agency in the City of Shasta Lake. The project is described as: 1.51miles of Preventative Maintenance on major local streets | Pavement Improvement | 2009-10-07 | 2009-10-15 | 2009-12-01 | 2009-12-23 | 409000 | 1.510 | 5474013
1373 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5475022 | This is a Pavement Resurfacing project by a local agency in the City of Citrus Heights. The project is described as: Sunrise Blvd. between Madison Ave. and Sayanara SAC24146/24430 Fair Oaks - Old Auburn to Oak Ave. SAC24429 | Pavement Improvement | 2009-09-08 | 2009-09-21 | 2010-08-20 | 2010-09-02 | 1404058 | 1.000 | 5475022
1374 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5475023 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Citrus Heights. The project is described as: Reconstruction and Rehabilitation of Twin Oaks Avenue between Auburn Blvd and Sunrise Ave. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-08-18 | 2010-07-30 | 525631.78 | 1.000 | 5475023
1375 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5475024 | This is a Safety project by a local agency in the City of Citrus Heights. The project is described as: Greenback lane from Mariposa Avenue to west of Birdcage Street Reconstruct medians and landscaping SAC 24456 | Other | 2010-05-10 | 2010-05-10 | 2011-04-28 | 2011-04-28 | 1049898.43 | 1.000 | 5475024
1376 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5476007 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Laguna Woods. The project is described as: El Toro Road from the westerly city limits with Laguna Beach to approximately 480 feet west of Calle Sonora | Pavement Improvement | 2009-10-12 | 2009-10-26 | 2010-06-01 | 2010-01-04 | 500000 | 1.300 | 5476007
1377 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10 | 5477003 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakley. The project is described as: Oakley Rd. | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2009-11-01 | 2009-12-10 | 347491 | 1.300 | 5477003
1378 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | ANTIOCH-PITTSBURGH | 10 | 5477004 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Oakley. The project is described as: Delta Rd. | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2009-11-01 | 2009-12-10 | 294540 | 0.980 | 5477004
1379 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 42 | 5478010 | This is a Pavement Resurfacing project by a local agency in the City of Rancho Santa Margarita. The project is described as: Alicia Parkway from the south city limits to Santa Margarita Parkway | Pavement Improvement | 2010-04-01 | 2010-04-19 | 2010-05-21 | 2010-06-23 | 297082.23 | 1.000 | 5478010
1380 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 42 | 5478011 | This is a Pavement Resurfacing project by a local agency in the City of Rancho Santa Margarita. The project is described as: Robinson Ranch Road from Raintree Lane to North Peak Drive | Pavement Improvement | 2010-08-16 | 2010-08-23 | 2010-08-09 | 2010-09-22 | 185000 | 1.000 | 5478011
1381 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5479019 | This is a Traffic Management Engineering project by a local agency in the City of Elk Grove. The project is described as: Install ITS components throughout Elk Grove | Safety/Traffic Management | 2009-10-26 | 2009-10-26 | 2010-11-01 | 2010-10-13 | 1000000 | 1.000 | 5479019
1382 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5479024 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the City of Elk Grove. The project is described as: I-5 N/B on Ramp @ Elk Grove Blvd. | Safety/Traffic Management | 2009-09-14 | 2009-09-14 | 2010-07-01 | 2010-02-10 | 181294.95 | 1.000 | 5479024
1383 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5479025 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Elk Grove. The project is described as: Rehabilitate roads in various location in Sacramento County. | Pavement Improvement | 2009-08-28 | 2009-08-28 | 2009-11-01 | 2010-11-10 | 1823001 | 1.000 | 5479025
1384 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 05 | 5479028 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Elk Grove. The project is described as: Elk Grove-Florin Road from Elk Grove Blvd to Bond Road: Rehabilitate roadway. | Pavement Improvement | 2010-05-24 | 2010-06-07 | 2010-09-15 | 2010-11-17 | 660400 | 1.000 | 5479028
1385 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | MISSION VIEJO | 48 | 5480003 | This is a Pavement Resurfacing project by a local agency in the City of Aliso Viejo. The project is described as: Pacific Park Drive from Cheyenne to Aliso Viejo Parkway | Pavement Improvement | 2010-03-17 | 2010-03-17 | 2010-03-01 | 2010-04-29 | 437219.7 | 0.480 | 5480003
1386 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | 5481007 | This is a Traffic Management Engineering project by a local agency in the City of Goleta. The project is described as: Various roads in the City of Goleta | Pavement Improvement | 2009-11-19 | 2009-11-23 | 2009-12-01 | 2010-06-02 | 1270736 | 1.700 | 5481007
1387 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 03 | 5482007 | This is a New Construction Roadway project by a local agency in the City of Rancho Cordova. The project is described as: City of Rancho Cordova from Kilgore to Sunrise Blvd. International Drive Extension | New Construction | 2009-10-20 | 2009-11-03 | 2012-06-01 | 2011-12-21 | 1050000 | 1.000 | 5482007
1388 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5482010 | This is a Pavement Restoration and Rehabilitation project by a local agency in the City of Rancho Cordova. The project is described as: Coloma Road from McGreger Dr. to Sunrise Blvd. | Pavement Improvement | 2009-07-20 | 2009-08-04 | 2010-04-30 | 2010-04-14 | 1121360 | 1.000 | 5482010
1389 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901034 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: Oceanview Drive from Mouth of Smith River Road to 1,100 feet south of Spy Glass Rd for a total distance of 7,100 feet. | Pavement Improvement | 2009-08-19 | 2009-08-25 | 2009-09-08 | 2009-09-08 | 239500.73 | 1.400 | 5901034
1390 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901035 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Del Norte. The project is described as: El Dorado Streeet from Hamilton Avenue to end (Del Norte High Schol property). | Transportation Enhancements | 2009-08-14 | 2009-08-17 | 2009-10-01 | 2009-08-31 | 28216.62 | 0.190 | 5901035
1391 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901036 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: On Pebble Beach Drive Between Hemlock Lane and Washington Blvd | Pavement Improvement | 2009-08-19 | 2009-08-24 | 2009-10-01 | 2009-09-04 | 150764.19 | 0.860 | 5901036
1392 | CALIFORNIA | Completed | C250,C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901037 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: On Lake Earl Drive from 800 feet north of Elk Valley Cross Road to Buzzini Road | Pavement Improvement | 2010-08-27 | 2010-09-07 | 2011-03-01 | 2010-11-15 | 292322.35 | 0.950 | 5901037
1393 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | DEL NORTE |  | 01 | 5901039 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Del Norte. The project is described as: On El Dorado Street from Hamilton to north end at High School | Pavement Improvement | 2009-08-24 | 2009-08-25 | 2009-10-01 | 2009-09-04 | 74355.83 | 0.190 | 5901039
1394 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5902060 | This is a Pavement Resurfacing project by a local agency in the County of Siskiyou. The project is described as: On Copco Rd from I-5 to Ager Rd. | Pavement Improvement | 2009-08-18 | 2009-08-21 | 2009-11-01 | 2009-10-12 | 1002333.39 | 3.200 | 5902060
1395 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SISKIYOU |  | 02 | 5902061 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Siskiyou. The project is described as: At Lake Siskiyou near City of Mt Shasta, Wagon Creek Bridge. | Transportation Enhancements | 2010-03-12 | 2010-03-15 | 2010-11-01 | 2010-10-14 | 1200000 | 0.100 | 5902061
1396 | CALIFORNIA | Completed | C250,C220,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MODOC |  | 04 | 5903048 | This is a Pavement Resurfacing project by a local agency in the County of Modoc. The project is described as: Asphalt Concrete Overlay on Modoc County Road 54 and various City streets. Overlay Pedes | Pavement Improvement | 2010-09-20 | 2010-10-04 | 2011-06-30 | 2011-06-07 | 789758 | 5.800 | 5903048
1397 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904097 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Airport Road from PM 0.00 at Central Avenue to PM 1.02 at Highway 101 | Pavement Improvement | 2009-10-23 | 2009-10-23 | 2010-02-16 | 2010-02-16 | 425794.56 | 1.020 | 5904097
1398 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904098 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Harris Street between Harrison Avenue and Hall Street | Pavement Improvement | 2009-11-06 | 2009-12-14 | 2010-08-27 | 2010-11-09 | 486990.97 | 0.760 | 5904098
1399 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904101 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Lucas Street outside the city limits of Eureka. | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2009-10-07 | 2010-02-01 | 191656.72 | 0.290 | 5904101
1400 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904104 | This is a Pavement Resurfacing project by a local agency in the County of Humboldt. The project is described as: Redwood Drive (Redway)-Rehabilitation and Paving | Pavement Improvement | 2011-06-06 | 2011-06-13 | 2011-11-15 | 2011-11-08 | 717595.52 |  | 5904104
1401 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | HUMBOLDT |  | 01 | 5904105 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Humboldt. The project is described as: On Bald Hills Road between Martins Ferry and SR101 | Pavement Improvement | 2010-06-14 | 2010-07-12 | 2011-01-04 | 2011-01-04 | 273770.69 | 1.000 | 5904105
1402 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TRINITY |  | 02 | 5905079 | This is a Bridge Rehabilitation, Added Capacity project by a local agency in the County of Trinity. The project is described as: 9-mile bridge rehab on Hyampom Road. | Bridge Improvement | 2010-01-05 | 2010-04-01 | 2011-10-31 | 2010-10-19 | 556248 | 0.300 | 5905079
1403 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5906096 | This is a Pavement Resurfacing project by a local agency in the County of Shasta. The project is described as: 33 locations proposed on various federal-aid roads within the County. | Pavement Improvement | 2009-07-31 | 2009-09-10 | 2009-12-01 | 2009-12-07 | 2595435 | 42.150 | 5906096
1404 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA | REDDING | 02 | 5906097 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Shasta. The project is described as: Construct East Redding Bike Lanes Phase 1 | Transportation Enhancements | 2010-01-14 | 2010-04-19 | 2010-07-12 | 2010-07-12 | 680217 | 2.190 | 5906097
1405 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | 5906102 | This is a Pavement Resurfacing project by a local agency in the County of Shasta. The project is described as: 37.7 miles of Preventative Maintenance on major local streets | Pavement Improvement | 2010-10-18 | 2010-11-01 | 2010-12-19 | 2010-11-30 | 223565 |  | 5906102
1406 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LASSEN |  | 04 | 5907055 | This is a Pavement Resurfacing project by a local agency in the County of Lassen. The project is described as: On Termo-Grasshopper Rd CR 513 between Mitchell Rd CR 538 & S Grasshopper Rd CR 507. Project begins at Mitchell Rd & proceeds east. | Pavement Improvement | 2009-09-15 | 2009-09-23 | 2009-09-01 | 2009-10-15 | 777240 | 3.500 | 5907055
1407 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | LASSEN |  | 04 | 5907056 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Lassen. The project is described as: Right of Way for bicycle path | Transportation Enhancements | 2011-06-14 | 2011-06-24 | 2011-02-01 | 2011-08-22 | 48117 | 0.500 | 5907056
1408 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA |  | 02 | 5908083 | This is a Pavement Resurfacing project by a local agency in the County of Tehama. The project is described as: On San Benito Rd between County Road 99W and Tehama City Limits up to intersection with C St. Excludes RR R/W. | Pavement Improvement | 2009-10-12 | 2009-11-09 |  | 2010-07-30 | 1242257.81 | 4.100 | 5908083
1409 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA |  | 02 | 5908084 | This is a Pavement Resurfacing project by a local agency in the County of Tehama. The project is described as: 2 sections of County Rd 99-1.5 m N of Corning, 1.8 mi S of Red Bluff | Pavement Improvement | 2010-12-22 | 2011-04-11 |  | 2011-06-28 | 1155093 | 3.000 | 5908084
1410 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLUMAS |  | 04 | 5909088 | This is a Pavement Resurfacing project by a local agency in the County of Plumas. The project is described as: Bucks Lake Rd Overlay - intx of Bellamy Lane, west 1.1 miles. PM 0.54 to PM 1.64 | Pavement Improvement | 2010-09-14 | 2010-09-15 | 2010-09-24 | 2010-09-22 | 353632.62 | 1.100 | 5909088
1411 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLUMAS |  | 04 | 5909089 | This is a Pavement Resurfacing project by a local agency in the County of Plumas. The project is described as: On Grizzly Rd btn SR 70 and Lake Davis near Portola | Pavement Improvement | 2010-09-17 | 2010-09-20 | 2010-10-22 | 2010-10-14 | 415175.82 | 2.000 | 5909089
1412 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5910071 | This is a Pavement Resurfacing project by a local agency in the County of Mendocino. The project is described as: West Road, Pudding Creek, and Comptche Ukiah Rd Overlay | Pavement Improvement | 2010-05-20 | 2010-05-20 | 2010-07-30 | 2010-07-12 | 1593153 | 10.490 | 5910071
1413 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | 5910079 | This is a Pavement Resurfacing project by a local agency in the County of Mendocino. The project is described as: Asphalt Concrete Overlay for designated segment | Pavement Improvement | 2011-07-05 | 2011-07-07 | 2011-07-08 | 2011-07-13 | 553653.93 |  | 5910079
1414 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 02 | 5912082 | This is a Pavement Resurfacing project by a local agency in the County of Butte. The project is described as: Midway from Town of Richvale to Western Canal Bridge | Pavement Improvement | 2009-10-19 | 2009-10-21 | 2009-12-01 | 2009-11-12 | 660000 | 3.300 | 5912082
1415 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | Multiple | 5912083 | This is a Pavement Resurfacing project by a local agency in the County of Butte. The project is described as: Lower Honcut from SR 70 to Palermo Honcut Hwy | Pavement Improvement | 2009-09-11 | 2009-09-24 | 2009-12-01 | 2009-10-26 | 620000 | 3.300 | 5912083
1416 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 04 | 5912084 | This is a Landscaping and Other Scenic Beautification project by a local agency in the County of Butte. The project is described as: Lincoln Blvd | Transportation Enhancements | 2011-10-17 | 2011-10-17 | 2011-11-18 | 2011-11-04 | 50758.31 | 1.000 | 5912084
1417 | CALIFORNIA | Completed | C250,C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SIERRA |  | 04 | 5913045 | This is a Scenic or Historic Highway Programs project by a local agency in the County of Sierra. The project is described as: Sierra City adjacent to SR49 | Transportation Enhancements | 2009-09-28 | 2009-11-04 | 2010-01-01 | 2010-08-06 | 105593.05 | 0.000 | 5913045
1418 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SIERRA |  | 04 | 5913047 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Sierra. The project is described as: Loyalton 4th Street Sidewalk Improvements: from SR49 (State right of way) to Loyalton High School (School right of way) | Transportation Enhancements | 2010-06-29 | 2010-07-06 | 2010-08-20 | 2010-09-03 | 89885.7 | 1.000 | 5913047
1419 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LAKE |  | 01 | 5914060 | This is a Pavement Resurfacing project by a local agency in the County of Lake. The project is described as: On Soda Bay Road | Pavement Improvement | 2010-05-28 | 2010-06-14 | 2010-08-13 | 2010-07-16 | 882159.83 | 2.400 | 5914060
1420 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LAKE |  | 01 | 5914062 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Lake. The project is described as: Lakeshore Boulevard Bikeway near the City of Lakeport | Transportation Enhancements | 2010-08-16 | 2010-08-23 | 2010-10-13 | 2010-10-18 | 132254 | 0.660 | 5914062
1421 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5915062 | This is a Pavement Resurfacing project by a local agency in the County of Colusa. The project is described as: Grimes-Arbuckle Rd. between Sycamore Slough Rd and SR45 | Pavement Improvement | 2010-06-21 | 2010-06-28 | 2010-07-30 | 2010-08-09 | 176830.96 | 5.720 | 5915062
1422 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5915065 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Colusa. The project is described as: On Hall St From Ninth St to Putnam Wy, Install new Sidewalk and place accessibility ramps as necessary | Transportation Enhancements | 2010-06-01 | 2010-06-14 | 2010-07-30 | 2010-07-24 | 26747 | 0.150 | 5915065
1423 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | 5915067 | This is a Safety project by a local agency in the County of Colusa. The project is described as: On Norman Rd at Argo St , Install Driver Radar Feedback Sign,shoulder improvements and HMA as necessary. | Other | 2010-09-07 | 2010-09-16 | 2010-10-19 | 2010-10-26 | 79000 |  | 5915067
1424 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | 5916079 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yuba. The project is described as: La Porte Road from Challenge Cutoff Road to Butte County Line, and from Butte County LIne to near Road 100. | Pavement Improvement | 2009-07-01 | 2009-07-16 | 2009-08-01 | 2009-08-12 | 995038 | 1.000 | 5916079
1425 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | 5916083 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yuba. The project is described as: Rehabilitate various roadways in Yuba County | Pavement Improvement | 2009-10-14 | 2009-11-06 | 2011-01-11 | 2011-01-11 | 1102834.95 | 1.000 | 5916083
1426 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917059 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Nevada. The project is described as: Hirschdale Road and Glenshire Drive | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2010-07-01 | 2009-11-05 | 250000 | 1.500 | 5917059
1427 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917061 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Nevada. The project is described as: Penn Valley Drive, North of Hwy 20 to Western Gateway Park | Transportation Enhancements | 2010-05-07 | 2010-05-28 | 2010-08-23 | 2010-08-19 | 258488.73 | 0.800 | 5917061
1428 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917062 | This is a Pavement Resurfacing project by a local agency in the County of Nevada. The project is described as: Magnolia Road from Lake of the Pines Road to 4,000 feet eastward. | Pavement Improvement | 2010-06-15 | 2010-06-21 | 2010-11-22 | 2010-08-13 | 581825.22 | 1.000 | 5917062
1429 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917063 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the County of Nevada. The project is described as: La Barr Meadow Road and Dog Bar Road | Pavement Improvement | 2010-09-16 | 2010-09-17 | 2010-11-19 | 2010-11-10 | 613768.54 | 3.500 | 5917063
1430 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917064 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the County of Nevada. The project is described as: Pleasant Valley Road, Ridge Road, Tyler Foote Road | Pavement Improvement | 2010-05-14 | 2010-05-24 | 2010-09-27 | 2010-07-09 | 681414.43 | 4.600 | 5917064
1431 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | 5917065 | This is a Pavement Resurfacing project by a local agency in the County of Nevada. The project is described as: Wolf Road from Hwy. 49 to Duggans Road;Pavement Rehab and Shoulder Widening | Pavement Improvement | 2010-10-05 | 2010-10-12 | 2010-11-29 | 2010-11-17 | 162800 |  | 5917065
1432 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | 5918072 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sutter. The project is described as: Various locations within Sutter County. All work within County R/W. | Pavement Improvement | 2009-10-19 | 2009-11-16 | 2009-12-18 | 2010-01-15 | 651463 | 1.000 | 5918072
1433 | CALIFORNIA | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER | SACRAMENTO | 02 | 5918073 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sutter. The project is described as: Road Rehabilitation - Acacia Ave (South Butte Rd - Butte House Rd), N | Pavement Improvement | 2010-07-19 | 2010-07-26 | 2010-09-30 | 2010-08-27 | 425115.3 | 4.020 | 5918073
1434 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER |  | 04 | 5919084 | This is a Pavement Resurfacing project by a local agency in the County of Placer. The project is described as: Douglas Blvd, Placer Hills Rd, Mt. Vernon Rd, Nelson Lane, Wise Lane | Pavement Improvement | 2010-05-14 | 2010-05-14 | 2010-07-02 | 2010-07-16 | 1848314.92 | 8.000 | 5919084
1435 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER |  | 04 | 5919089 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Placer. The project is described as: Auburn Folsom Road from near Woodchase Dr to Ann Place | Pavement Improvement | 2009-12-11 | 2010-01-04 | 2011-10-01 | 2011-10-07 | 2068237 | 6.000 | 5919089
1436 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | PLACER | SACRAMENTO | 04 | 5919091 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Placer. The project is described as: Foresthill Passing Lane Modification Project? | Pavement Improvement | 2011-07-07 | 2011-07-25 | 2011-10-05 | 2011-09-15 | 60008.24 | 0.250 | 5919091
1437 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA |  | Multiple | 5920116 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sonoma. The project is described as: Various Locations in Sonoma County | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-11-15 | 2010-10-15 | 6376000 | 60.000 | 5920116
1438 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA |  | Multiple | 5920121 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sonoma. The project is described as: Polymer Modified Asphalt Rubber Chip Seal at various locations in Sonoma County | Pavement Improvement | 2010-10-25 | 2011-07-18 | 2012-02-15 | 2011-12-21 | 2695944 |  | 5920121
1439 | CALIFORNIA | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | 5921045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Napa. The project is described as: County of Napa at Various Streets and Road Rehabilitation | Pavement Improvement | 2009-10-19 | 2009-11-09 | 2009-11-17 | 2010-02-23 | 471069.89 | 3.800 | 5921045
1440 | CALIFORNIA | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | 5921046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Napa. The project is described as: Rehabilitate local street. Silverado Trail: Larkmead Lane to Glass Mount, AC Overlay. | Pavement Improvement | 2009-10-12 | 2009-11-02 | 2009-11-09 | 2010-02-23 | 585915.86 | 1.100 | 5921046
1441 | CALIFORNIA | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | 5921048 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Napa. The project is described as: Silverado Trail Phase C - 3000' N of Howell Mountain Road to Deer Park Road | Pavement Improvement | 2010-06-14 | 2010-06-14 | 2010-07-09 | 2010-11-09 | 286083.16 | 1.200 | 5921048
1442 | CALIFORNIA | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | 5921049 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Napa. The project is described as: Silverado Trail Phase D - Larkmead Lane to Bale Lane | Pavement Improvement | 2010-08-26 | 2010-09-13 | 2010-09-17 | 2010-10-12 | 323673.68 |  | 5921049
1443 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 01 | 5922084 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Yolo. The project is described as: County Road 29 from CR99 to SR113, and County Road 99D from CR29 to Davis City LImits. | Transportation Enhancements | 2009-08-04 | 2009-08-17 | 2009-09-15 | 2009-09-15 | 368568 | 1.000 | 5922084
1444 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO |  | 02 | 5922085 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yolo. The project is described as: County Road 22, from CR 118 to CR 124 | Pavement Improvement | 2009-08-19 | 2009-09-17 | 2009-11-01 | 2010-03-16 | 907937 | 1.000 | 5922085
1445 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YOLO | SACRAMENTO | 02 | 5922087 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Yolo. The project is described as: County Road 31 from Davis City Limits to County Road 93A, and County Road 93A from County Road 31 to County Road 32. | Pavement Improvement | 2010-07-02 | 2010-07-26 | 2010-08-31 | 2010-09-22 | 276234 | 6.000 | 5922087
1446 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO |  | Multiple | 5923088 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Solano. The project is described as: Allendale Rd., Cantelow Rd., Halley Rd., Lake Herman Rd.,Pedrick Rd., Putah Creek Rd. and Stevenson Bridge Rd. | Pavement Improvement | 2009-06-25 | 2009-06-29 | 2009-09-01 | 2009-08-07 | 2000000 | 10.400 | 5923088
1447 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO |  | Multiple | 5923092 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Solano. The project is described as: Cordelia Rd. from Lopes Rd. to Central Way, and from Bridgeport Ave. to Pittman Rd. | Transportation Enhancements | 2010-01-12 | 2010-02-01 | 2011-12-01 | 2012-02-07 | 800000 | 0.600 | 5923092
1448 | CALIFORNIA | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | SOLANO |  | Multiple | 5923093 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Solano. The project is described as: Lewis Rd.from Hawkins Rd. to Werner Rd., and Pleasants Valley Rd. from Putah Crk Rd to Yolo County Line | Pavement Improvement | 2010-06-10 | 2010-06-15 | 2010-05-28 | 2010-06-25 | 388195 | 3.900 | 5923093
1449 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5924159 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Sacramento. The project is described as: Various locations w/in the county of Sacramento | Pavement Improvement | 2009-08-21 | 2009-09-08 | 2011-04-30 | 2011-07-19 | 10865138.01 | 1.000 | 5924159
1450 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5924161 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Sacramento. The project is described as: Various locations w/in the County of Sacrametno SAC24269 | Transportation Enhancements | 2009-10-21 | 2009-11-02 | 2010-12-01 | 2011-01-17 | 2973695 | 1.000 | 5924161
1451 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SACRAMENTO | SACRAMENTO | 04 | 5924162 | This is a Traffic Management Engineering project by a local agency in the County of Sacramento. The project is described as: Various locations w/in the County | Safety/Traffic Management | 2011-06-30 | 2011-07-11 | 2011-12-22 | 2011-11-28 | 3150000 | 1.000 | 5924162
1452 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925069 | This is a Pavement Resurfacing project by a local agency in the County of El Dorado. The project is described as: Forni Road and Pony Express Lane | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2009-09-10 | 2009-08-27 | 633349.32 | 0.700 | 5925069
1453 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925071 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of El Dorado. The project is described as: US50/Missour Flat Rd Interchange Phase 1B. | Transportation Enhancements | 2010-01-19 | 2010-01-19 | 2013-02-28 |  | 5173967 | 1.500 | 5925071
1454 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925072 | This is a Pavement Resurfacing project by a local agency in the County of El Dorado. The project is described as: Lotus Road from Wunschel Lane to SR 49 | Pavement Improvement | 2009-09-25 | 2009-09-25 | 2009-11-01 | 2009-10-22 | 1717941.85 | 6.570 | 5925072
1455 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925073 | This is a Pavement Resurfacing project by a local agency in the County of El Dorado. The project is described as: Malcom Dixon Road from Salmon Falls Road to Green Valley Road | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2009-11-01 | 2009-11-02 | 439255 | 2.040 | 5925073
1456 | CALIFORNIA | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO | SACRAMENTO | 04 | 5925078 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of El Dorado. The project is described as: Latrobe Road from Cothrin Ranch Road to South Shingle Road: rehabilitate roadways. | Pavement Improvement | 2010-10-08 | 2010-10-08 | 2010-11-10 | 2010-12-08 | 917206.97 | 3.700 | 5925078
1457 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | 5925080 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of El Dorado. The project is described as: Complete 2 in. overlay and repair of structural deficient pavement and curb and gutter/drainage areas. | Pavement Improvement | 2010-08-30 | 2010-08-30 | 2010-09-27 | 2010-09-27 | 558320 | 2.020 | 5925080
1458 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | 5926043 | This is a Safety project by a local agency in the County of Amador. The project is described as: Latrobe Rd. at the intersection with Old Sacramento Rd. in Amador Co. | Pavement Improvement | 2010-07-22 | 2010-08-02 | 2010-08-27 | 2010-09-07 | 250751.61 | 0.300 | 5926043
1459 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | 5926044 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the County of Amador. The project is described as: A Michigan Bar Rd. from 2 miles east of the boundary line with Sacramento County to the intersection with SR104 | Pavement Improvement | 2010-08-10 | 2010-08-19 | 2010-09-15 | 2010-09-29 | 355367.33 | 1.000 | 5926044
1460 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | 5926045 | This is a Safety project by a local agency in the County of Amador. The project is described as: Along Roadways throughout Amador County | Safety/Traffic Management | 2010-02-22 | 2010-04-07 | 2010-12-16 | 2010-12-20 | 403868.4 | 1.000 | 5926045
1461 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5927068 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Marin. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-10-05 | 2009-10-08 | 2009-12-01 | 2011-02-15 | 1993434.25 | 3.990 | 5927068
1462 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | SAN FRANCISCO-OAKLAND, CA | 06 | 5927070 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Marin. The project is described as: Atherton Ave - Highway 37 MP 0.12 to 730 ft east of Olive Ave MP 1.27, | Pavement Improvement | 2010-08-25 | 2010-09-08 | 2011-03-15 | 2011-05-10 | 1272590 | 1.000 | 5927070
1463 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | 10 | 5928091 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Contra Costa. The project is described as: Vasco Road Overlay | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2009-10-01 | 2009-10-28 | 1945770 | 5.100 | 5928091
1464 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | STATEWIDE | 10 | 5928093 | This is a Safety project by a local agency in the County of Contra Costa. The project is described as: Vasco Road Safety Improvements- Contra Costa | Safety/Traffic Management | 2010-04-26 | 2010-04-26 | 2012-02-14 | 2012-02-14 | 11279083 | 1.000 | 5928093
1465 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | CONTRA COSTA | STATEWIDE | 10 | 5928103 | This is a New Roadway Construction project by a local agency in the County of Contra Costa. The project is described as: SR4 Bypass: Segment 3 RAC Overlay Project.2 inch RAC Overlay Project. | Pavement Improvement | 2010-09-29 | 2010-09-29 | 2010-12-07 | 2011-03-22 | 1764728.41 |  | 5928103
1466 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5929197 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: French Camp Rd from Jack Tone Rd to SR 120 | Pavement Improvement | 2009-10-02 | 2009-10-13 | 2009-11-01 | 2009-11-12 | 784874.26 | 3.400 | 5929197
1467 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5929198 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Jack Tone Rd from French Camp Rd. to SR 120 | Pavement Improvement | 2009-10-12 | 2009-10-30 | 2009-11-01 | 2009-11-13 | 472124.56 | 2.000 | 5929198
1468 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | 5929199 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Swain Rd from Plymouth Rd to Alexandria Pl | Pavement Improvement | 2009-10-02 | 2009-10-13 | 2009-10-26 | 2009-10-26 | 213437.62 | 0.600 | 5929199
1469 | CALIFORNIA | Completed | C250,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STATEWIDE | 11 | 5929200 | This is a Pavement Resurfacing project by a local agency in the County of San Joaquin. The project is described as: Rubberized chip seal of 10 roadways in San Joaquin County | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2011-08-11 | 2011-08-11 | 4168169 | 30.000 | 5929200
1470 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 5929204 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Joaquin. The project is described as: In SJ Co. West Ripon Rd. Resurfacing from Austin Rd to Airport Way. | Pavement Improvement | 2010-05-06 | 2010-06-01 | 2010-06-21 | 2010-06-21 | 894126.77 | 4.000 | 5929204
1471 | CALIFORNIA | Underway | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 18 | 5929221 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Joaquin. The project is described as: Resurface roadway between Wallance Avenue and Ryde Avenue | Pavement Improvement | 2011-06-06 | 2011-06-13 | 2013-03-01 |  | 508926 |  | 5929221
1472 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930043 | This is a Pavement Resurfacing project by a local agency in the County of Calaveras. The project is described as: Rehab of Olive Orchard Rd. | Pavement Improvement | 2010-07-20 | 2010-08-02 | 2010-09-01 | 2010-10-01 | 204733.98 | 1.700 | 5930043
1473 | CALIFORNIA | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930044 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Calaveras. The project is described as: Rehab of Meko Dr. | Pavement Improvement | 2010-07-20 | 2010-08-02 | 2010-09-01 | 2010-10-01 | 139057.99 | 1.100 | 5930044
1474 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930045 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Calaveras. The project is described as: Rehab of Pennsylvania Gulch Rd. | Pavement Improvement | 2010-07-20 | 2010-08-02 | 2010-09-01 | 2010-10-01 | 150092 | 1.200 | 5930045
1475 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930046 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Calaveras. The project is described as: Rehab of Watertown Rd. | Pavement Improvement | 2010-07-20 | 2010-08-02 | 2010-09-01 | 2010-10-01 | 204219.58 | 1.800 | 5930046
1476 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930047 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Calaveras. The project is described as: Rehab of Independence Rd. | Pavement Improvement | 2010-07-20 | 2010-08-02 | 2010-09-01 | 2010-10-01 | 271045.49 | 2.300 | 5930047
1477 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930050 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Calaveras. The project is described as: West Point, CA. On Bald Mountain Road from Sate Route 26 to the end of West Point Elementary School. | Transportation Enhancements | 2010-09-13 | 2010-09-27 | 2010-10-01 | 2011-02-08 | 34762.97 | 0.050 | 5930050
1478 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930052 | PARROT'S FERRY RD, MAIN ST & TWO SECTIONS OF RAILROAD FLAT RD, ROADWAY PREVENTATIVE MAINTENANCE | Pavement Improvement | 2011-07-01 | 2011-07-11 | 2011-10-31 | 2011-08-23 | 423652.51 |  | 5930052
1479 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | CALAVERAS |  | 03 | 5930057 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Calaveras. The project is described as: Class II Bikeway in West-Point | Transportation Enhancements | 2011-02-16 | 2011-02-16 | 2011-05-31 | 2011-11-08 | 46378.96 |  | 5930057
1480 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALPINE |  | 03 | 5931017 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alpine. The project is described as: Rehabilitation of County roads Emigrant Trail and roads in Alpine Village | Pavement Improvement | 2010-06-21 | 2010-07-09 | 2010-09-01 | 2010-08-20 | 158536.56 | 3.600 | 5931017
1481 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TUOLUMNE |  | 19 | 5932055 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Tuolumne. The project is described as: Upgrade County Hignway J-59 from PM 12.61 to the South Country Boundary | Pavement Improvement | 2010-04-30 | 2010-05-03 | 2010-06-07 | 2011-04-05 | 2146000 | 12.500 | 5932055
1482 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TUOLUMNE |  | 19 | 5932058 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Tuolumne. The project is described as: Old Sugarpine Railroad Grade, East Ave to End of Gurney Station Rd. | Pavement Improvement | 2011-05-02 | 2011-05-09 | 2011-09-30 | 2011-09-20 | 249514 | 1.100 | 5932058
1483 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5933098 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alemeda. The project is described as: Redwood Rd.- between Castrovalelly Blvd. to Camino Alta Mira | Pavement Improvement | 2009-12-11 | 2009-12-11 | 2010-06-01 | 2011-02-10 | 1383127 | 1.650 | 5933098
1484 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | LIVERMORE | 10 | 5933099 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alemeda. The project is described as: Altamont Pass Rd. - Between Altamont Landfill and Grant Line Rd. | Pavement Improvement | 2009-10-30 | 2009-10-30 | 2010-06-01 | 2010-11-16 | 1200000 | 1.650 | 5933099
1485 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 13 | 5933101 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Alemeda. The project is described as: Hesperian Blvd to Grant Avenue | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-07-19 | 2010-11-16 | 420000 | 1.700 | 5933101
1486 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 5933103 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Alemeda. The project is described as: On San Miguel Ave. From Sumerset Ave. to Castro Valley Blvd. | Transportation Enhancements | 2010-08-24 | 2010-09-07 | 2010-09-16 | 2011-07-22 | 711097 | 0.400 | 5933103
1487 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934147 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Francisco. The project is described as: Jones Street from California St. to Market St. | Pavement Improvement | 2009-08-19 | 2009-08-19 | 2010-10-01 | 2010-07-29 | 1040947.35 | 0.700 | 5934147
1488 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934148 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Francisco. The project is described as: Turk Street from Market Street to Van Ness Ave. | Pavement Improvement | 2009-09-02 | 2009-09-02 | 2010-03-01 | 2010-09-02 | 910742.99 | 0.630 | 5934148
1489 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934149 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Francisco. The project is described as: Divisadero Street from Waller Street to Geary Blvd. | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2010-09-01 | 2010-08-11 | 2144894.99 | 0.700 | 5934149
1490 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 12 | 5934150 | This is a Pavement Restoration and Rehabilitation project by a local agency in the San Francisco County. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2010-01-01 | 2010-05-27 | 2196632.98 | 1.200 | 5934150
1491 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934151 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Francisco. The project is described as: Intersections of Geary Blvd at 19th Ave, 20th Ave, 21st Ave, 22nd Ave, and 23rd Ave | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-11-01 | 2010-04-28 | 415810.57 | 0.080 | 5934151
1492 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934152 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Francisco. The project is described as: Bush St from Van Ness Ave to Presidio Ave; Euclid Ave from Presidio Ave to Masonic Ave | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-10-01 | 2010-10-17 | 2000000 | 0.700 | 5934152
1493 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934153 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of San Francisco. The project is described as: San Francisco - Various locations | Transportation Enhancements | 2010-02-15 | 2010-02-15 | 2011-11-01 | 2011-06-17 | 721223.96 | 1.000 | 5934153
1494 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934156 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Francisco. The project is described as: San Francisco - Williams Avenue, from Phelps Street to 3rd Street | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2010-12-31 | 2011-03-11 | 872153.34 | 1.000 | 5934156
1495 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | STATEWIDE | 08 | 5934157 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Francisco. The project is described as: San Francisco Various Locations;Construct ADA compliant curb ramps at various locations | Pavement Improvement | 2010-09-20 | 2010-09-20 | 2010-12-15 | 2011-06-24 | 605094.94 | 1.000 | 5934157
1496 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934158 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Francisco. The project is described as: Construct ADA compliant curb ramps along Holloway Ave. | Transportation Enhancements | 2010-11-29 | 2010-11-29 | 2010-12-15 | 2011-04-08 | 263606.52 |  | 5934158
1497 | CALIFORNIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 5934160 | This is a Safety and Education for Pedestrians/Bicycles project by a local agency in the County of San Francisco. The project is described as: Corbin Place Stair Replacement Project;Pedestrian Enhancements | Transportation Enhancements | 2011-02-28 | 2011-02-28 | 2011-05-30 | 2011-06-23 | 239851.11 |  | 5934160
1498 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 14 | 5935054 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Mateo. The project is described as: Various Location San Mateo County | Pavement Improvement | 2009-09-25 | 2009-09-29 | 2009-12-28 | 2010-04-21 | 1725666.7 | 4.000 | 5935054
1499 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | 17 | 5936076 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Cruz. The project is described as: Carlton Rd,San Andreas, Green Valley and Boony Dunes/Pine Flat (non participating) | Pavement Improvement | 2009-07-21 | 2009-07-22 | 2009-11-01 | 2009-10-30 | 2132931.73 | 4.800 | 5936076
1500 | CALIFORNIA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | Multiple | 5936081 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Cruz. The project is described as: Road repairs: various roadways; cape seals | Pavement Improvement | 2010-07-08 | 2010-07-13 | 2010-09-10 | 2011-06-28 | 2545068 | 1.000 | 5936081
1501 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 14 | 5937132 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Clara. The project is described as: Montague Expressway Road Rehab (between highway US101 and Interstate 680 | Pavement Improvement | 2009-07-14 | 2009-07-20 | 2010-04-14 | 2009-12-16 | 2676319.99 | 2.700 | 5937132
1502 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5937133 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Clara. The project is described as: Rehabilitate local street | Pavement Improvement | 2009-08-25 | 2009-09-08 | 2009-10-21 | 2010-01-26 | 958999.99 | 2.330 | 5937133
1503 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | 5937162 | CENTRAL EXPRESSWAY (BETWEEN LAWRENCE EXPRESSWAY AND MARY AVENUE, AUXILLIARY LANES | Pavement Improvement | 2010-07-20 | 2010-08-16 | 2010-10-29 | 2011-02-08 | 300000 |  | 5937162
1504 | CALIFORNIA | Completed | C250,C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | 5938164 | This is a Pavement Resurfacing project by a local agency in the County of Stanislaus. The project is described as: within Stansiaus county | Pavement Improvement | 2010-08-11 | 2010-08-11 | 2010-10-26 | 2010-12-31 | 4798051.7 | 55.000 | 5938164
1505 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | 5938166 | This is a Traffic Management Engineering project by a local agency in the County of Stanislaus. The project is described as: Intersection of Carpenter Rd @ Robertson Rd and Carpenter Rd @ Beverly Dr. | Safety/Traffic Management | 2010-06-08 | 2010-07-26 | 2010-10-26 | 2011-03-14 | 1366675 | 0.530 | 5938166
1506 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | 5938170 | This is a Pavement Resurfacing project by a local agency in the County of Stanislaus. The project is described as: Cape/Seal Streets Preventive Maintenenace | Pavement Improvement | 2010-09-07 | 2010-09-07 | 2010-12-06 | 2010-11-11 | 491490.3 | 1.000 | 5938170
1507 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED | MERCED | 18 | 5939066 | This is a Pavement Resurfacing project by a local agency in the County of Merced. The project is described as: Various location (Santa Fe Drive, Belcher Ave, Westside Blvd.) | Pavement Improvement | 2010-05-18 | 2010-06-28 | 2010-08-20 | 2010-09-13 | 771264.27 | 20.400 | 5939066
1508 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5939069 | This is a Bridge Rehabilitation, No Added Capacity project by a local agency in the County of Merced. The project is described as: Avenue Two at Canal Creek (BR #39C0278) | Bridge Replacement | 2010-06-30 | 2010-07-26 | 2011-06-30 | 2011-05-20 | 1308605.21 | 0.330 | 5939069
1509 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | 5939073 | This is a Pavement Resurfacing project by a local agency in the County of Merced. The project is described as: Scrub Seal of Existing AC surface on Henry Miller Road | Pavement Improvement | 2010-10-06 | 2010-10-19 | 2010-11-30 | 2010-12-13 | 348109.24 |  | 5939073
1510 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIPOSA |  | 19 | 5940075 | This is a Pavement Resurfacing project by a local agency in the County of Mariposa. The project is described as: Hornitos Road - from Old Toll Road (P.M.20.115) to junction with State Hwy 140 (P.M.26.129). (31,750 LF) | Pavement Improvement | 2010-10-04 | 2011-06-22 | 2011-07-31 | 2011-11-30 | 197167 | 6.010 | 5940075
1511 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIPOSA |  | 19 | 5940076 | This is a Pavement Resurfacing project by a local agency in the County of Mariposa. The project is described as: Triangle Road - from the Hwy 140 intersection (P.M.10.00) to Carleton Road (P.M.11.75). (9,250 LF) | Pavement Improvement | 2010-10-04 | 2011-06-23 | 2011-07-31 | 2011-11-30 | 52289.75 | 1.750 | 5940076
1512 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIPOSA |  | 19 | 5940080 | This is a Pavement Resurfacing project by a local agency in the County of Mariposa. The project is described as: 8.0 miles of Greeley Hill Road (From Junction with Dogtown Road to junction with Smith Station Road, PM10.404 - 18.457) CTIPS: 230-0000-0287 | Pavement Improvement | 2010-10-04 | 2011-06-20 | 2011-07-31 | 2011-11-30 | 291756 | 8.050 | 5940080
1513 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5941068 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Madera. The project is described as: Pedestrian sidewalk | Transportation Enhancements | 2010-05-19 | 2010-06-14 | 2010-07-19 | 2010-07-03 | 109112 | 1.000 | 5941068
1514 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5941072 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Madera. The project is described as: Avenue 15, Road 29 to Road 35 | Pavement Improvement | 2009-10-21 | 2009-10-28 | 2010-10-30 | 2010-10-22 | 1868824 | 6.000 | 5941072
1515 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5941075 | This is a Pavement Resurfacing project by a local agency in the County of Madera. The project is described as: Pavement resurfacing | Pavement Improvement | 2010-09-15 | 2010-09-27 | 2010-11-09 | 2010-11-19 | 525000 | 2.000 | 5941075
1516 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | 5941077 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Madera. The project is described as: Road 26 rehabilitiation from Club Drive to Avenue 21 | Pavement Improvement | 2010-09-15 | 2010-09-27 | 2010-11-09 | 2010-11-19 | 545679 | 2.000 | 5941077
1517 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5942178 | This is a Pavement Resurfacing project by a local agency in the County of Fresno. The project is described as: Various | Pavement Improvement | 2010-04-30 | 2010-06-01 | 2010-08-05 | 2010-08-02 | 2882548.75 | 10.000 | 5942178
1518 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | 5942182 | This is a Landscaping and Other Scenic Beautification project by a local agency in the County of Fresno. The project is described as: Plant Palm Trees on Kearney Boulevard from Marks Ave. to Westlawn Ave. | Transportation Enhancements | 2010-09-23 | 2010-09-23 | 2013-03-22 |  | 473150 | 5.900 | 5942182
1519 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | Multiple | 5942189 | This is a Pavement Resurfacing project by a local agency in the County of Fresno. The project is described as: Lump-Sum AC Overlay on eligible route. Dinuba Avenue from 0.30 mi. east of Zumwalt to Alta. | Pavement Improvement | 2011-04-19 | 2011-04-19 | 2011-07-01 | 2011-05-20 | 192671 |  | 5942189
1520 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BENITO |  | 17 | 5943048 | This is a Pavement Resurfacing project by a local agency in the County of San Benito. The project is described as: Southside Road from Union Road to Southside Road Bridge | Pavement Improvement | 2009-09-08 | 2009-09-28 | 2010-02-01 | 2010-04-07 | 851092 | 3.000 | 5943048
1521 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BENITO |  | 17 | 5943049 | This is a Pavement Resurfacing project by a local agency in the County of San Benito. The project is described as: In the County of San Benito on Fairview Road | Pavement Improvement | 2010-04-23 | 2010-04-26 | 2010-06-01 | 2010-05-13 | 218891.89 | 1.000 | 5943049
1522 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BENITO |  | 17 | 5943050 | This is a Pavement Resurfacing project by a local agency in the County of San Benito. The project is described as: In the County of San Benito on Union Road | Pavement Improvement | 2010-04-23 | 2010-04-26 | 2010-06-01 | 2010-05-13 | 121419.72 | 1.000 | 5943050
1523 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY | SEASIDE-MONTEREY | 17 | 5944095 | This is a Pavement Resurfacing project by a local agency in the County of Monterey. The project is described as: Espinosa Road Rehabilitation | Safety/Traffic Management | 2009-08-10 | 2009-08-14 | 2009-12-02 | 2009-12-02 | 2108637.99 | 4.680 | 5944095
1524 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5945075 | This is a Pavement Resurfacing project by a local agency in the County of Kings. The project is described as: Kansas Av, from 4th Ave - SR 43 Houston Ave, from SR 43 - Shaw Pl Granville Blvd, from 6th Ave - SR43 | Pavement Improvement | 2010-10-07 | 2010-10-12 | 2010-11-12 | 2010-11-12 | 1130000 | 1.000 | 5945075
1525 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | KINGS |  | 20 | 5945077 | This is a Pavement Resurfacing project by a local agency in the County of Kings. The project is described as: Houston Avenue from 2nd to 7th Ave | Pavement Improvement | 2010-10-07 | 2010-10-12 | 2010-11-12 | 2010-11-12 | 906780.73 | 1.000 | 5945077
1526 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5946094 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Tulare. The project is described as: On Ave. 384 from SR99 to Road 80 | Pavement Improvement | 2010-08-02 | 2010-08-16 | 2010-12-01 | 2011-01-11 | 2297706 | 7.000 | 5946094
1527 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5946096 | This is a Pavement Resurfacing project by a local agency in the County of Tulare. The project is described as: Road 232, Ave. 56, Diagonal 134 (Ave. 192) | Pavement Improvement | 2010-07-12 | 2010-07-13 | 2010-12-01 | 2011-01-11 | 2758494.61 | 4.330 | 5946096
1528 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | 5946097 | This is a Pavement Resurfacing project by a local agency in the County of Tulare. The project is described as: Ave. 232 and Road 56 | Pavement Improvement | 2010-07-12 | 2010-07-19 | 2010-12-01 | 2011-01-11 | 4124000 | 8.000 | 5946097
1529 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONO |  | 25 | 5947037 | This is a Pavement Resurfacing project by a local agency in the County of Mono. The project is described as: Swall Meadows Road from Foothill Road to Lower Rock Creek Road | Pavement Improvement | 2010-04-13 | 2010-05-17 | 2010-06-17 | 2010-06-11 | 340000 | 1.500 | 5947037
1530 | CALIFORNIA | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | MONO |  | 25 | 5947038 | This is a Landscaping and Other Scenic Beautification project by a local agency in the County of Mono. The project is described as: Various locations along US 395 in the community of Lee Vining | Transportation Enhancements | 2010-11-16 | 2010-11-16 | 2011-07-23 | 2011-07-29 | 174000 | 0.800 | 5947038
1531 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | 5948069 | This is a Pavement Reconstruction, No Added Capacity project by a local agency in the County of Inyo. The project is described as: Reconstruct approx 0.5 mi of Barlow and 0.1 miles of Saniger install | Pavement Improvement | 2009-10-01 | 2009-10-06 | 2010-04-30 | 2010-08-09 | 988558 | 2.900 | 5948069
1532 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | 5948070 | This is a Establishment of Transporation Museums project by a local agency in the County of Inyo. The project is described as: Eastern California Museum website maintained at 155 North Grant Street in Independence | Transportation Enhancements | 2010-09-21 | 2010-10-27 | 2011-06-30 | 2011-08-31 | 24980.5 | 0.000 | 5948070
1533 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 23 | 5949117 | This is a Pavement Resurfacing project by a local agency in the County of San Luis Obispo. The project is described as: Willow Road | New Construction | 2010-06-18 | 2010-07-21 | 2011-03-31 | 2011-06-30 | 1709000 | 0.680 | 5949117
1534 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | 5949118 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of San Luis Obispo. The project is described as: Road repairs : (1) Lopez Dr:Orcutt Rd. to Lopez Lake Dam ( | Pavement Improvement | 2009-10-30 | 2009-11-01 | 2010-09-21 | 2010-09-21 | 1757741 | 5.500 | 5949118
1535 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5950307 | This is a Pavement Resurfacing project by a local agency in the County of Kern. The project is described as: On Lerdo Highway: SR33 to I-5 | Pavement Improvement | 2010-05-06 | 2010-05-20 | 2010-06-30 | 2010-09-07 | 1425989 | 6.200 | 5950307
1536 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 20 | 5950308 | This is a Pavement Resurfacing project by a local agency in the County of Kern. The project is described as: Lerdo Highway: Wildwood Rd. to Shafter City limit. | Pavement Improvement | 2010-01-05 | 2010-02-02 | 2010-03-24 | 2010-04-19 | 1054439 | 8.100 | 5950308
1537 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5950310 | This is a Pavement Resurfacing project by a local agency in the County of Kern. The project is described as: Garlock Road from SR395 to 5 miles west in the unincorporated area of Kern County | Pavement Improvement | 2009-11-05 | 2010-02-15 | 2010-04-22 | 2010-04-05 | 1394715 | 5.000 | 5950310
1538 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 20 | 5950312 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Kern. The project is described as: King road: Twisselman Road to County line. | Pavement Improvement | 2009-11-05 | 2009-12-04 | 2009-12-01 | 2010-01-12 | 928883.12 | 4.500 | 5950312
1539 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5950313 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Kern. The project is described as: Twisselman Road from King Road to Interstate 5 | Pavement Improvement | 2010-07-01 | 2010-07-10 | 2010-10-15 | 2010-11-24 | 4199241 | 7.400 | 5950313
1540 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | 22 | 5950317 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Kern. The project is described as: various locations in the city of Bakersfield | Transportation Enhancements | 2010-04-29 | 2010-05-11 | 2010-07-15 | 2010-08-25 | 417766.82 | 2.900 | 5950317
1541 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | 5950328 | This is a Pavement Resurfacing project by a local agency in the County of Kern. The project is described as: Lerdo Highway: State Route 33 to I-5 (portions); Asphalt Concrete Overlay: construct 6 foot AC shoulder with 2 foot dirt shoulder backing. | Pavement Improvement | 2011-01-06 | 2011-01-31 | 2011-03-07 | 2011-06-30 | 2137162 |  | 5950328
1542 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | Multiple | 5951124 | This is a Pavement Resurfacing project by a local agency in the County of Santa Barbara. The project is described as: Barker Pass Rd, Calle Real, Harris Grade, Paradise Rd, Simas St, Grand Ave. and Betteravia rd. | Pavement Improvement | 2009-06-24 | 2009-07-06 | 2009-12-01 | 2009-10-23 | 1522082.74 | 5.000 | 5951124
1543 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | Multiple | 5951125 | This is a Bridge Rehabilitation, No Added Capacity project by a local agency in the County of Santa Barbara. The project is described as: Various Locations in SB County | Bridge Improvement | 2009-06-24 | 2009-07-13 | 2009-11-01 | 2009-10-23 | 341154.18 | 1.000 | 5951125
1544 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | Multiple | 5951126 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Barbara. The project is described as: Various location in SB County | Transportation Enhancements | 2009-06-24 | 2009-08-03 | 2009-12-01 | 2009-10-23 | 605999.99 | 1.000 | 5951126
1545 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 23 | 5951128 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Santa Barbara. The project is described as: In Summerland on Ortega Hill Road and Lillie Avenue between Ortega Ridge Road and Greenwell Ave | Transportation Enhancements | 2010-01-08 | 2010-02-15 | 2010-06-28 | 2010-04-28 | 454837 | 1.000 | 5951128
1546 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | 5951129 | This is a Traffic Management Engineering project by a local agency in the County of Santa Barbara. The project is described as: Union Valley Parkway at Bradley Road in Santa Barbara County | Pavement Improvement | 2010-06-04 | 2010-06-28 | 2010-12-01 | 2010-12-06 | 1103642 | 1.000 | 5951129
1547 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | 5951130 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Santa Barbara. The project is described as: In Santa Barbara County In Old Town Orcutt at the intersection of Clark Avenue and Gray Street | Transportation Enhancements | 2010-04-16 | 2010-06-07 | 2010-08-04 | 2010-08-27 | 300000 | 1.000 | 5951130
1548 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | 5951131 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Santa Barbara. The project is described as: Santa Barbara County in Santa Ynez Refugio Road Class 2 Bike Lanes | Transportation Enhancements | 2010-02-19 | 2010-03-15 | 2010-09-01 | 2010-07-19 | 1329999.99 | 6.000 | 5951131
1549 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | Multiple | 5951132 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Santa Barbara. The project is described as: Santa Barbara County on Modoc Road and Betteravia Road | Pavement Improvement | 2009-12-08 | 2010-01-04 | 2010-06-01 | 2010-03-30 | 615938 | 1.200 | 5951132
1550 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | Multiple | 5952134 | This is a Safety project by a local agency in the County of Ventura. The project is described as: ROSE AVENUE / CENTRAL AVENUE INTERSECTION. | Pavement Widening | 2009-07-20 | 2009-07-21 | 2010-02-04 | 2010-02-04 | 210000 | 0.130 | 5952134
1551 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5952135 | This is a Bridge Rehabilitation, No Added Capacity project by a local agency in the County of Ventura. The project is described as: Bridge Deck Rehab. Various Locations | Pavement Improvement | 2009-07-29 | 2009-08-03 | 2009-09-08 | 2009-09-17 | 487273.54 | 0.240 | 5952135
1552 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5952138 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Ventura. The project is described as: VARIOUS LOCATIONS WITHIN VENTURA COUNTY | Pavement Improvement | 2009-07-10 | 2009-07-10 | 2009-10-01 | 2009-10-08 | 1658662 | 4.980 | 5952138
1553 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5952139 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Ventura. The project is described as: VARIOUS LOCATIONS WITHIN VENTURA COUNTY-PHASE A | Pavement Improvement | 2009-08-13 | 2009-08-17 | 2010-04-15 | 2010-06-14 | 2335171 | 10.340 | 5952139
1554 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | 5952143 | This is a Landscaping and Other Scenic Beautification project by a local agency in the County of Ventura. The project is described as: Katherine Road from railroad Right of Way to Santa Suzana Road | Pavement Improvement | 2010-02-23 | 2010-03-09 | 2010-04-13 | 2010-04-12 | 271714.52 | 1.060 | 5952143
1555 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 24 | 5952144 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Ventura. The project is described as: Pavement Rehabilitation- On System Roads, Tierra Rejada Road and Del Norte Road;Street Overlay. | Pavement Improvement | 2010-10-07 | 2010-10-21 | 2011-04-20 | 2011-03-18 | 568476 |  | 5952144
1556 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953595 | This is a Traffic Management Engineering project by a local agency in the County of Los Angeles. The project is described as: Intersection of Whittier Boulevard and Atlantic Boulevard and the east intersection of Admiralty Way and Marina City Club Drive | Safety/Traffic Management | 2009-10-06 | 2009-10-13 | 2009-12-29 | 2009-12-31 | 206821 | 1.000 | 5953595
1557 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953596 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: COLIMA RD, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 2010-04-12 | 2010-04-19 | 2010-12-14 | 2010-11-29 | 2945874 | 7.360 | 5953596
1558 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 25 | 5953597 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: ANGELES FOREST HIGHWAY, ET AL. FOR LOS ANGELES COUNTY FAS FUNDS | Pavement Improvement | 2010-04-15 | 2010-06-14 | 2010-10-21 | 2010-10-15 | 2531015.03 | 8.010 | 5953597
1559 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | 5953600 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: MULHOLLAND HIGHWAY, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 2009-11-09 | 2010-04-01 | 2011-04-29 | 2011-04-20 | 3291800 | 22.500 | 5953600
1560 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5953603 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: WASHINGTON BL, ET AL. - ROADWAY RESURFACING | Pavement Improvement | 2009-09-18 | 2009-10-30 | 2009-12-04 | 2009-12-04 | 343157 | 0.740 | 5953603
1561 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953604 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: GRAVES AV, ET AL. - ROADWAY RESURFACING PROJECT | Pavement Improvement | 2009-10-29 | 2010-01-25 | 2010-03-19 | 2010-03-19 | 545166.59 | 0.850 | 5953604
1562 | CALIFORNIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LANCASTER | 25 | 5953605 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: AVENUE G, ET AL; FOR LOS ANGELES COUNTY FAS FUNDS (PRIORITY #2 F | Pavement Improvement | 2010-04-15 | 2010-06-15 | 2010-10-22 | 2010-10-20 | 4537878.76 | 18.200 | 5953605
1563 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953610 | This is a Safety project by a local agency in the County of Los Angeles. The project is described as: REIS ET AL- BRIDGE BARRIER RAIL REPLACEMENT PROJECT | Bridge Improvement | 2009-11-09 | 2010-01-04 | 2010-03-26 | 2010-04-13 | 229477 | 1.000 | 5953610
1564 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 25 | 5953612 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: West Avenue N, 82nd St East, 106th St. East, 165th St. East, 170th St. East, Ave. S, and Ave. T | Pavement Improvement | 2010-04-15 | 2010-05-28 | 2010-10-29 | 2010-10-07 | 3821990.99 | 11.970 | 5953612
1565 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES |  | 22 | 5953614 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: GORMAN POST RD, ET AL ROADWAY RESURFACING PROJECT | Pavement Improvement | 2010-04-15 | 2010-06-07 | 2010-10-13 | 2010-10-27 | 2544138.33 | 7.330 | 5953614
1566 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 39 | 5953617 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: FIRESTONE BL, ET AL ROADWAY RESURFACING | Pavement Improvement | 2009-11-18 | 2010-02-01 | 2010-04-06 | 2010-04-07 | 1661053.8 | 2.630 | 5953617
1567 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5953618 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: 120th Street from Isis Avenue to La Cienega Boulevard | Pavement Improvement | 2009-11-05 | 2009-11-30 | 2010-03-01 | 2009-12-24 | 179041 | 0.270 | 5953618
1568 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 37 | 5953619 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: EL SEGUNDO BLVD ET AL. - ROADWAY RESURFACING | Pavement Improvement | 2009-11-05 | 2010-02-01 | 2010-03-30 | 2010-03-30 | 727575.53 | 1.420 | 5953619
1569 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 35 | 5953620 | This is a Pavement Resurfacing project by a local agency in the County of Los Angeles. The project is described as: Crenshaw Blvd, et al | Pavement Improvement | 2009-11-05 | 2010-02-24 | 2010-03-26 | 2010-03-26 | 726800 | 1.370 | 5953620
1570 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953624 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Los Angeles. The project is described as: Los Angeles River Bike Trail Et Al. (TEA Priority No. 1) | Transportation Enhancements | 2010-02-18 | 2010-05-04 | 2010-09-30 | 2010-08-25 | 846465 | 1.000 | 5953624
1571 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953625 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: EMERALD NECKLACE REHABILITATION | Transportation Enhancements | 2010-01-04 | 2010-03-29 | 2010-05-26 | 2010-06-18 | 1876629.25 | 34.620 | 5953625
1572 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953626 | This is a Traffic Management Engineering project by a local agency in the County of Los Angeles. The project is described as: Various intersections on the southwestern side of I-5 in Los Angeles County | Other | 2009-10-29 | 2010-07-20 | 2011-02-28 | 2011-03-02 | 2815738 | 1.000 | 5953626
1573 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953627 | This is a Traffic Management Engineering project by a local agency in the County of Los Angeles. The project is described as: Various intersections on the northeastern side of I-5 in Los Angeles County | Other | 2009-10-29 | 2010-02-16 | 2010-12-16 | 2010-12-08 | 2812709.5 | 1.000 | 5953627
1574 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | 5953631 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Los Angeles. The project is described as: Rosemead Bl-Foothill Bl/566 S/o Ardendale Av (Temple City Bounda | Pavement Improvement | 2009-10-13 | 2010-01-11 | 2012-04-30 | 2012-02-16 | 8528700 | 2.100 | 5953631
1575 | CALIFORNIA | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | 5954115 | This is a Pavement Resurfacing project by a local agency in the County of San Bernardino. The project is described as: Amboy Road from 9.35 miles south of National Trails Highway to National Trails Highway | Pavement Improvement | 2010-07-08 | 2010-07-19 | 2010-08-02 | 2010-07-30 | 1235552 | 9.400 | 5954115
1576 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | 5955068 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Orange. The project is described as: Newport Avenue from Wass Street to Hyde Park Drive | Pavement Improvement | 2010-05-20 | 2010-06-21 | 2010-09-30 | 2010-09-29 | 1837401 | 1.860 | 5955068
1577 | CALIFORNIA | Underway | C250,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | INDIA-COACHELLA | 45 | 5956179 | This is a Bridge Rehabilitation, Added Capacity project by a local agency in the County of Riverside. The project is described as: I-10 Interchange at Gene Autry Trail / Palm Drive, Bridge No. 56-0563. | Pavement Widening | 2010-02-26 | 2010-03-01 | 2013-02-20 |  | 10415000 | 0.800 | 5956179
1578 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | SAN BERNARDINO-RIVERSIDE | 44 | 5956187 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Riverside. The project is described as: State Route 60 and Valley Way interchange in Sunnyslope | New Construction | 2010-02-19 | 2010-02-22 | 2012-12-17 | 2012-11-27 | 3915396 | 0.800 | 5956187
1579 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5958064 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Imperial. The project is described as: Baughman Rd. from Forrester Rd. to SR-78/86 | Pavement Improvement | 2010-08-04 | 2010-09-07 | 2010-11-11 | 2011-05-03 | 552000 | 0.640 | 5958064
1580 | CALIFORNIA | Completed | C250 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5958065 | This is a Pavement Resurfacing project by a local agency in the County of Imperial. The project is described as: Worthington Rd. Intersection at McConnel Rd. | Other | 2010-08-10 | 2010-09-02 | 2010-11-10 | 2011-08-16 | 157000 | 0.460 | 5958065
1581 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | IMPERIAL |  | 51 | 5958066 | This is a Pavement Restoration and Rehabilitation project by a local agency in the County of Imperial. The project is described as: Drew Road from Ross Road to Evan Hewes Highway | Pavement Improvement | 2010-06-22 | 2010-07-06 | 2010-11-15 | 2011-03-01 | 276822 | 0.400 | 5958066
1582 | CALIFORNIA | Underway | C220,C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | STATEWIDE | 43 | 6053080 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of San Bernardino. The project is described as: I-215 from Rialto Avenue to approximately 500 feet north of 16th Street in San Bernardino | Safety/Traffic Management | 2009-10-01 | 2009-10-01 | 2014-01-31 |  | 128585744 | 2.500 | 6053080
1583 | CALIFORNIA | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE | SAN BERNARDINO-RIVERSIDE | 44 | 6054063 | This is a Pavement Reconstruction, Added Capacity project by a local agency in the County of Riverside. The project is described as: Replace/widen OC, realign/widen ramps, improve circulation | Pavement Widening | 2009-11-12 | 2010-07-19 | 2012-12-31 |  | 16667604 | 1.500 | 6054063
1584 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | 53 | 6066067 | This is a Transit project by a local agency in the County of San Diego. The project is described as: TE Reserve Grossmont Station Pedestrian Improvements | Transportation Enhancements | 2010-01-25 | 2010-03-05 |  | 2011-11-19 | 4002427 | 0.000 | 6066067
1585 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | 6127041 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the County of Amador. The project is described as: In City of Sutter Creek, at intersection of Valley View Way and Bowers Drive. | Transportation Enhancements | 2010-11-01 | 2010-11-01 | 2010-12-31 | 2010-12-31 | 49927 | 0.200 | 6127041
1586 | CALIFORNIA | Completed | C200 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CRUZ | SANTA CRUZ | Multiple | 6149062 | This is a Traffic Management Engineering project by a local agency in the County of Santa Cruz. The project is described as: Freeway Service Patrol on SR 1 & 17 in Santa Cruz County NEW EA 05-930166 | Safety/Traffic Management | 2009-07-13 | 2009-07-13 | 2011-02-01 | 2011-06-30 | 179999.9 | 7.030 | 6149062
1587 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 15 | 6264042 | This is a Traffic Management Engineering project by a local agency in the County of Santa Clara. The project is described as: SR 237/I-880 Express HOT Connectors I-880 PM 8.422 to 10.407 SR 237 PM 5.834 to 10.000 | Other | 2009-09-21 | 2009-09-21 | 2013-03-31 |  | 3500000 | 4.170 | 6264042
1588 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | Multiple | 6264044 | This is a Traffic Management Engineering project by a local agency in the County of Santa Clara. The project is described as: SR 85 Express Lanes | Other | 2009-12-04 | 2010-03-11 | 2013-12-23 |  | 3300000 | 24.060 | 6264044
1589 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 6273056 | This is a Traffic Management Engineering project by a local agency in the County of Alameda. The project is described as: Alameda I-580 EB HOT Lane | Other | 2010-05-03 | 2010-05-03 | 2015-06-01 |  | 7500000 | 11.300 | 6273056
1590 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | Multiple | 6328029 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of San Francisco. The project is described as: Various location in San francisco | Transportation Enhancements | 2010-03-18 | 2010-03-22 | 2011-06-01 | 2011-09-01 | 243400.35 | 1.000 | 6328029
1591 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | 6328030 | This is a Facilities for Pedestrians and Bicycles project by a local agency in the City of San Francisco. The project is described as: Various locations on Irving Street in San Francisco. Area bounded by 4th Ave, Moraga St, 9th Ave and Lincoln Way | Transportation Enhancements | 2010-02-22 | 2010-03-12 | 2011-06-01 | 2010-09-08 | 296197 | 1.000 | 6328030
1592 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN | STOCKTON | 11 | 6349005 | This is a Rail/Highway Crossing project by a local agency in the City of Stockton. The project is described as: Port of Stockton storage yard | Other | 2010-06-09 | 2010-06-21 | 2010-10-15 | 2010-12-10 | 1000000 | 0.000 | 6349005
1593 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | 50 | 8051608 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Chula Vista, from north of H Street to north of Route 54; also on Route 54 (PM 1.6/2,5). | Pavement Improvement | 2009-07-24 | 2009-10-05 |  | 2011-05-18 | 9925838 | 0.900 | 8051608
1594 | CALIFORNIA | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | Multiple | 8051610 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: From Carroll Canyon Road to Interstate 5 - On I-805, constructio | Pavement Widening | 2011-01-29 | 2011-03-15 | 2012-11-07 |  | 51816680 | 2.400 | 8051610
1595 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | 8801058 | This is a Bridge Rehabilitation, No Added Capacity project by the California Department of Transportation. The project is described as: In Oakland, at Fruitvale Avenue Bridge #33-0041. | Pavement Improvement | 2009-06-25 | 2009-07-20 | 2009-12-08 | 2009-12-08 | 8327479.13 | 0.300 | 8801058
1596 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | 51 | A905019 | This is a New Costruction Roadway project by the California Department of Transportation. The project is described as: From I-805 to Otay Mesa Port of Entry. | Pavement Widening | 2009-05-08 | 2009-07-01 | 2012-04-26 |  | 73930886 | 3.400 | A905019
1597 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SONOMA |  | 06 | P001540 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Sonoma County near Fort Ross, from 2.5 miles south of Fort Ross Road to Timber C | Pavement Improvement | 2009-09-10 | 2009-09-11 | 2009-10-23 | 2009-11-12 | 430451.08 | 7.900 | P001540
1598 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | P001541 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in and near Laguna Beach, from Dana Point/Laguna Beach City limits | Pavement Improvement | 2009-06-12 | 2009-09-09 | 2010-05-04 | 2010-05-04 | 1804560.43 | 9.500 | P001541
1599 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA | SANTA BARBARA | 23 | P001545 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Santa Barbara County near Lompoc on Route 1 from the intersection of Harris Gra | Pavement Improvement | 2010-06-01 | 2010-06-16 | 2010-12-15 | 2010-12-15 | 1834322 | 25.140 | P001545
1600 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN JOAQUIN |  | 11 | P004133 | This is a Safety project by the California Department of Transportation. The project is described as: West of Stockton, from east of Middle River to Trapper Road. Realign curve. | Safety/Traffic Management | 2009-09-21 | 2010-04-15 | 2012-10-12 |  | 9512058 | 2.800 | P004133
1601 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALPINE |  | 03 | P004135 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: Near Markleeville, from west of Raymond Meadow Creek Bridge to Junction Route 89. | Pavement Improvement | 2010-08-16 | 2010-08-23 | 2010-11-10 | 2010-11-10 | 929310.91 | 14.600 | P004135
1602 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN |  | 22 | P014065 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Kern County near Mojave, from South Junction State Route 58 to 5 miles north of | Pavement Improvement | 2009-06-28 | 2009-07-02 | 2009-11-03 | 2009-11-03 | 5129627 | 24.500 | P014065
1603 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P018037 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County, from 0.1 mile west of Route 18/330 Separation to Lakeview Point. | Pavement Improvement | 2009-06-25 | 2009-07-24 | 2010-04-19 | 2010-04-19 | 1360611 | 7.500 | P018037
1604 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P018038 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County near Big Bear City, from Snubbing Post Grade Road to 0.6 m | Pavement Improvement | 2009-06-04 | 2009-06-19 | 2009-08-24 | 2009-08-24 | 645773.59 | 10.000 | P018038
1605 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P018039 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Lucerne Valley, at Cushenbury Creek Bridge #54-394. | Pavement Improvement | 2009-10-12 | 2009-12-01 | 2010-11-04 | 2010-11-04 | 3998627 | 0.700 | P018039
1606 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | COLUSA |  | 02 | P020150 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In Williams, from 0.3 mile east to 0.6 mile west of Route 5. | Pavement Improvement | 2009-09-02 | 2009-10-06 |  | 2011-10-07 | 7088950 | 0.900 | P020150
1607 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | YUBA |  | 02 | P020151 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Yuba County near Marysville, from 0.2 miles west of Spring Valley Road to 0.1 mile east of Marysville Road. | Pavement Improvement | 2009-07-22 | 2009-08-13 | 2009-10-21 | 2009-10-21 | 902008.18 | 3.200 | P020151
1608 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA, CONTRA COSTA | SAN FRANCISCO-OAKLAND, CA | Multiple | P024030 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: Construction a 2-lane tunnel. | Pavement Improvement | 2009-11-20 | 2010-01-13 | 2014-05-01 |  | 175796000 | 2.200 | P024030
1609 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | P024031 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Realignment of WB Rte 24 to NB Rte 13. | Pavement Improvement | 2010-01-20 | 2010-01-29 | 2011-04-20 | 2011-04-20 | 3161086 | 0.100 | P024031
1610 | CALIFORNIA | Completed | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ALAMEDA | SAN FRANCISCO-OAKLAND, CA | 09 | P024032 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Widening and signalization at Kay Street. | Pavement Improvement | 2010-01-27 | 2010-02-09 | 2010-07-19 | 2010-07-19 | 483921 | 0.100 | P024032
1611 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NAPA |  | 01 | P029105 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Napa County near Calistoga, from 0.2 miles north of Silverado Trail to Lake County line. | Pavement Improvement | 2009-07-21 | 2009-08-19 | 2009-10-23 | 2009-10-23 | 639556.44 | 10.500 | P029105
1612 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | P033068 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Merced County in and near Dos Palos, from Fresno County Line to State Route 152; | Pavement Improvement | 2009-06-25 | 2009-07-10 | 2009-09-02 | 2009-09-02 | 1182595 | 19.900 | P033068
1613 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | OXNARD-VENTURA | 23 | P034004 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Ventura County in and near Camarillo, from Daily Drive to State Route 118. | Pavement Improvement | 2009-06-26 | 2009-07-12 | 2009-11-24 | 2009-11-24 | 1153182.15 | 4.000 | P034004
1614 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLUMAS |  | 04 | P036086 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Plumas County about 6 miles east of Chester, from 0.8 mile west to 1.2 miles east of Lake Almanor Safety Roadside Rest Area. | Pavement Improvement | 2009-06-12 | 2009-08-15 | 2009-10-05 | 2009-10-06 | 1390850.72 | 1.700 | P036086
1615 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | P039021 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In La Habra, from Route 90 to Los Angeles County Line; also on Route 72 from Route 39 to Los Angeles County line. | Pavement Improvement | 2009-07-17 | 2009-09-21 | 2010-11-05 | 2010-11-05 | 5019582.54 | 4.000 | P039021
1616 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 20 | P041110 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In Fresno - At McKinley Avenue and Shields Avenue. | Pavement Improvement | 2009-08-11 | 2009-08-24 | 2011-06-23 | 2011-06-23 | 2954313 | 1.400 | P041110
1617 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO | FRESNO | 21 | P041115 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: In the city of Fresno, on Route 41 at and near Friant Road. Tree planting. | Transportation Enhancements | 2010-08-19 | 2010-09-02 |  | 2011-08-01 | 1034370 | 1.000 | P041115
1618 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SHASTA |  | 02 | P044045 | This is a Safety project by the California Department of Transportation. The project is described as: Near Viola from 2.5 to 1.1 miles west of the Lassen Park entrance. Realign curve, widen shoulder and extend truck climbing lane. | Safety/Traffic Management | 2010-02-03 | 2010-05-03 | 2010-10-22 | 2010-10-22 | 5726722 | 1.400 | P044045
1619 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | P046042 | This is a Safety project by the California Department of Transportation. The project is described as: Near Shandon - at the Shandon Rest Area - rehabilitate Safety Roadside Rest Area. | Safety/Traffic Management | 2009-08-12 | 2009-10-06 | 2011-11-22 | 2011-01-31 | 4629688 | 0.000 | P046042
1620 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | P049143 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near El Dorado, from Ore Court Road to China Hill Road. | Pavement Improvement | 2009-06-26 | 2009-07-07 | 2010-10-25 | 2010-10-25 | 6868710 | 1.000 | P049143
1621 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SIERRA |  | 04 | P049144 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Sierra County on State Route 49 near Sierraville and Loyalton, from South Junction State Routes 49/89 to the Plumas County line. | Pavement Improvement | 2009-07-09 | 2009-07-27 | 2009-09-23 | 2009-09-23 | 789006.88 | 17.000 | P049144
1622 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TUOLUMNE |  | 19 | P049145 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Tuolumne County in and near Sonora, from 0.2 mile south of Pesce Way to Calaveras County line. | Pavement Improvement | 2009-07-02 | 2009-07-20 | 2010-01-14 | 2010-01-14 | 1269885.86 | 9.100 | P049145
1623 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | NEVADA |  | 04 | P049148 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: Nevada County near Grass Valley from 0.6 KM north of Alta Sierra Drive to 0.9 KM south of Wellswood Way. | Pavement Widening | 2011-05-12 | 2011-05-23 | 2012-06-28 |  | 2000000 |  | P049148
1624 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | P050125 | This is a Safety project by the California Department of Transportation. The project is described as: Near Meyers, from Echo Summit to 1.3 miles east. Upgrade rock guardrail to current standards and water quality improvements. | Safety/Traffic Management | 2011-03-29 | 2011-04-26 |  | 2011-11-03 | 2079775 |  | P050125
1625 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | Multiple | P057053 | This is a Safety project by the California Department of Transportation. The project is described as: In Orange, Anaheim and Fullerton, from West Orangewood Avenue to the Los Angeles County line at various locations. | Pavement Improvement | 2009-08-09 | 2010-02-01 | 2011-01-26 | 2011-01-26 | 2953660.5 | 11.000 | P057053
1626 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P062026 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County, from 4.9 miles west to 0.9 miles west of Rio Mesa Drive. | Pavement Improvement | 2009-06-19 | 2009-08-14 | 2009-08-26 | 2009-10-21 | 589715.66 | 4.000 | P062026
1627 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | PLUMAS |  | 04 | P070099 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Quincy (9 miles west), from 0.2 mile west to 0.2 mile east of Spanish Creek Bridge #09-0015. Rehabilitate bridge. | Bridge Replacement | 2010-06-24 | 2010-08-23 | 2013-03-18 |  | 18613911 | 0.400 | P070099
1628 | CALIFORNIA | Underway | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO | SAN BERNARDINO-RIVERSIDE | 42 | P071058 | ON ROUTE 71 IN SAN BERNARDINO AND RIVERSIDE COUNTIES NEAR CHINO HILLS ***, LANDSCAPING (TREE PLANTING) (TC) | Transportation Enhancements | 2011-02-28 | 2011-04-11 | 2014-09-25 |  | 661664 |  | P071058
1629 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 48 | P073086 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in Laguna Niguel, Laguna Hills, Aliso Viejo, Laguna Beach and Irvine, from Interstate 5 to Ford Road undercrossing. | Pavement Improvement | 2009-08-05 | 2009-08-19 | 2011-01-13 | 2011-01-13 | 7813394.89 | 12.500 | P073086
1630 | CALIFORNIA | Underway | C200,C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN DIEGO | SAN DIEGO, CA | 49 | P076024 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: CONSTRUCT 4-LANE HIGHWAY. | Pavement Widening | 2010-01-21 | 2010-02-03 | 2012-09-10 |  | 75612901 | 5.800 | P076024
1631 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE |  | 44 | P078108 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Palo Verde, on 32nd Avenue west of South Randalls Avenue Bridge #56-0216. | Pavement Improvement | 2009-08-04 | 2009-09-17 | 2010-10-01 | 2010-10-01 | 1545437 | 0.200 | P078108
1632 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR | STOCKTON | 03 | P088052 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Amador County in and near Barton, from 0.1 mile west of Wagon Wheel Drive to 0.1 mile west of Silver Lake Road. | Pavement Improvement | 2009-06-25 | 2009-07-06 | 2009-11-03 | 2009-11-03 | 910505.24 | 5.700 | P088052
1633 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | AMADOR |  | 03 | P088053 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Amador County near Plasse, from 2 miles west of Tragedy Springs Road to 0.3 mile east of Kit Carson Lodge Road. | Pavement Improvement | 2009-07-10 | 2009-07-10 | 2009-11-03 | 2009-11-03 | 307308.39 | 6.100 | P088053
1634 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | EL DORADO |  | 04 | P089094 | This is a Mitigation of Water Pollution due to Highway Runoff project by the California Department of Transportation. The project is described as: Near Meyers, from Alpine County Line to Route 50. | Pavement Improvement | 2009-07-01 | 2009-09-01 | 2011-11-15 | 2012-01-12 | 16425073 | 8.600 | P089094
1635 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | LOS ANGELES, CA | 42 | P090011 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Orange County in Brea and Placentia, from Randolph Avenue to 0.1 mile east of Rose Drive. | Pavement Improvement | 2009-06-19 | 2009-07-08 | 2009-10-14 | 2009-10-14 | 1768825 | 3.000 | P090011
1636 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE, ORANGE | LOS ANGELES, CA | Multiple | P091127 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Orange County add one lane on eastbound SR-91 from SR-241 to | Pavement Improvement | 2009-09-16 | 2009-11-10 | 2012-10-16 | 2011-05-13 | 44926884.83 | 5.900 | P091127
1637 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE |  | 45 | P095020 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: Near Blythe, from 0.4 mile north of Wiley Hill Log Cabin to 0.9 mile south of Wilson Road at various locations. | Pavement Improvement | 2009-06-26 | 2009-07-12 | 2010-02-01 | 2010-02-01 | 2639700 | 8.300 | P095020
1638 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | BUTTE |  | 02 | P099519 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: SR 99 Near Biggs - Rio Bonito to SR 162. | Pavement Improvement | 2009-07-07 | 2009-08-01 |  | 2012-02-29 | 11331484 | 4.600 | P099519
1639 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | P099520 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Sutter County, SR 99 near East Nicholas, from Sacramento County line to Route 70. | Pavement Improvement | 2009-06-12 | 2009-07-06 | 2009-12-31 | 2009-12-31 | 12195645 | 8.700 | P099520
1640 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED | MERCED | 18 | P099521 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: In Merced County, from north of V Street to Black Rascal Bridge #39-0131R/L. | Pavement Improvement | 2009-10-08 | 2010-01-04 | 2012-03-23 |  | 29695432 | 1.500 | P099521
1641 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS | MODESTO | 18 | P099522 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: Highway planting in Stanislaus County, in and near the City | Transportation Enhancements | 2010-02-15 | 2010-03-10 | 2010-07-19 | 2010-07-19 | 755065 | 7.900 | P099522
1642 | CALIFORNIA | Completed | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TEHAMA |  | 02 | P099525 | This is a Landscaping and Other Scenic Beautification project by the California Department of Transportation. The project is described as: Irrigation system for landscaping. | Transportation Enhancements | 2010-07-12 | 2010-07-12 | 2011-01-12 | 2011-01-12 | 79710 | 1.000 | P099525
1643 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SUTTER |  | 02 | P099529 | This is a New Construction Roadway project by the California Department of Transportation. The project is described as: Sutter County near Nicolaus from Power Line Road to 0.1 mile south of Laurel Avenue. | Pavement Widening | 2010-08-02 | 2010-09-21 | 2014-01-06 |  | 19060691 |  | P099529
1644 | CALIFORNIA | Underway | C220,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | TULARE |  | 21 | P099539 | This is a rehabilitate safety roadside rest area project by the California Department of Transportation. The project is described as: Near Tipton, at Phillip S. Raine Safety Roadside Rest Area. | Pavement Improvement | 2011-04-25 | 2011-05-11 | 2012-08-27 |  | 5536672 |  | P099539
1645 | CALIFORNIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA | STATEWIDE | 24 | P118058 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: In Simi Valley, from Tapo Canyon Road to the Los Angeles county | Pavement Widening | 2009-12-15 | 2010-01-06 | 2011-07-22 | 2011-07-22 | 6507000 | 5.500 | P118058
1646 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | P134035 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Los Angeles County in Burbank, Glendale and Los Angeles, from Bob Hope Drive Undercrossing to State Routes 134/2 Separation. | Pavement Improvement | 2009-08-06 | 2009-09-03 | 2010-08-18 | 2010-08-18 | 1110030.43 | 6.400 | P134035
1647 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LASSEN |  | 04 | P139019 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Lassen County about 40 miles north of Susanville, from 7.0 miles north of CDF Fire Station to Foster Draw Road. | Pavement Improvement | 2009-07-14 | 2009-07-27 | 2009-10-15 | 2009-10-16 | 1176593.88 | 13.000 | P139019
1648 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MADERA |  | 19 | P145029 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: Near Madera, from Avenue 5 1/2 to Avenue 11 1/2. | Pavement Improvement | 2009-06-20 | 2009-06-20 | 2010-06-25 | 2010-06-25 | 10525615 | 6.100 | P145029
1649 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 24 | P154018 | This is a Bridge Rehabilitation, No Added Capacity project by the California Department of Transportation. The project is described as: Construct physical barricade on Highway 154/Cold Sping Canyon Bridge near San Marcos Pass. | Safety/Traffic Management | 2010-06-01 | 2012-01-23 | 2012-05-18 | 2012-03-01 | 1499999.43 | 0.240 | P154018
1650 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA BARBARA |  | 23 | P154019 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Santa Barbara County near Santa Barbara on Route 154 from the intersection of S | Pavement Improvement | 2010-06-03 | 2010-06-03 | 2011-01-10 | 2011-01-10 | 1805421.02 | 18.000 | P154019
1651 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MERCED |  | 18 | P165011 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Near Los Banos, from Henery Miller Road to Route 140. Rehabilitate Roadway. | Pavement Improvement | 2011-07-05 | 2011-08-08 | 2012-05-25 | 2012-03-07 | 8139263 |  | P165011
1652 | CALIFORNIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 21 | P180053 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near Centerville, from Temperance Avenue to Academy Avenue (Qual | Pavement Improvement | 2009-09-21 | 2009-11-30 | 2011-11-21 | 2011-11-23 | 18369261 | 6.200 | P180053
1653 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | P190013 | This is a Scenic or Historic Highway Programs project by the California Department of Transportation. The project is described as: In Death Valley National Park, on Route 190 at Father Crowley Point. Construct scenic overlook. | Transportation Enhancements | 2010-05-13 | 2010-06-02 | 2010-08-17 | 2010-08-17 | 447881.08 | 1.000 | P190013
1654 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | P222001 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: Near Ukiah, at Russian River Bridge #10-80. | Bridge Replacement | 2009-06-29 | 2009-10-15 | 2011-12-13 | 2012-01-06 | 7903106 | 0.010 | P222001
1655 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | RIVERSIDE |  | 45 | P243002 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Riverside County near Idyllwild, from 1.1 miles north of State Routes 74/243 Sep | Pavement Improvement | 2009-07-15 | 2009-07-29 | 2009-10-08 | 2009-10-08 | 1933265 | 12.200 | P243002
1656 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | TRINITY |  | 02 | P299157 | This is a Facilities for Pedestrians and Bicycles project by the California Department of Transportation. The project is described as: In Trinity County at Weaverville 0.4 mile west of Miner Street to Court Street. | Transportation Enhancements | 2010-04-29 | 2010-06-14 | 2010-09-28 | 2010-09-28 | 227597.8 | 0.800 | P299157
1657 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MODOC |  | 04 | P395224 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Modoc County near Alturas, from the Lassen/Modoc County Line to Alturas Overhead. | Pavement Improvement | 2009-07-17 | 2009-08-13 | 2010-12-31 | 2010-12-31 | 1920749.94 | 20.800 | P395224
1658 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN BERNARDINO |  | 41 | P395225 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Bernardino County on US Highway 395 near Kramer Junction, from Federal Priso | Pavement Improvement | 2009-06-26 | 2009-07-10 | 2009-10-22 | 2009-10-22 | 1530677 | 6.000 | P395225
1659 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONO |  | 25 | P395226 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Mono County near Hilton Creek, from 0.1 mile north of Crooked Creek Bridge to 0.4 mile south of Obsidian Dome Road. | Pavement Improvement | 2009-07-03 | 2009-07-23 | 2009-10-23 | 2009-10-23 | 3273458 | 23.500 | P395226
1660 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | P710014 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Los Angeles from 0.3 mile south of Firestone Blvd to 0.2 mile south of Slauson Avenue. | Pavement Improvement | 2009-09-22 | 2009-11-16 | 2012-11-19 |  | 52219257 | 2.700 | P710014
1661 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | Q101151 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Near Salinas, from Central Avenue to Gould Avenue at various locations. | Pavement Improvement | 2009-08-14 | 2009-08-31 | 2011-04-06 | 2011-04-06 | 5942549 | 36.900 | Q101151
1662 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN MATEO | SAN FRANCISCO-OAKLAND, CA | 12 | Q101152 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In San Mateo County in South San Francisco and Brisbane, from Oyster Point Boulevard Overcrossing to the San Francisco County line. | Pavement Improvement | 2009-08-14 | 2009-08-19 | 2010-12-17 | 2010-12-17 | 2853351.53 | 3.100 | Q101152
1663 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN FRANCISCO | SAN FRANCISCO-OAKLAND, CA | 08 | Q101153 | This is a Pavement Reconstruction, No Added Capacity project by the California Department of Transportation. The project is described as: In the City and County of San Francisco on Route 101, Doyle | Pavement Improvement | 2010-04-13 | 2010-04-18 | 2013-03-15 |  | 85816153.1 | 1.800 | Q101153
1664 | CALIFORNIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | MARIN | STATEWIDE | 06 | Q101155 | This is a Traffic Management Engineering and Facilities for Pedestrians and Bicycles project by the California Department of Transportation. The project is described as: Construction HOV lanes and bike path. | Transportation Enhancements | 2007-08-15 | 2007-08-15 | 2011-02-03 | 2011-02-03 | 2701200 | 1.860 | Q101155
1665 | CALIFORNIA | Underway | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SAN LUIS OBISPO |  | 22 | Q101159 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In and near Atascadero, from Cuesta Grade overhead to north of Traffic Way. | Pavement Improvement | 2010-01-26 | 2010-03-22 | 2013-12-24 |  | 36476122 | 10.600 | Q101159
1666 | CALIFORNIA | Underway | C230 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA | SAN JOSE, CA | 16 | Q101164 | This is a Pavement Reconstruction, Added Capacity project by the California Department of Transportation. The project is described as: Construct operational & safety improvements as follows: Constru | Pavement Improvement | 2010-11-18 | 2010-11-23 | 2012-04-02 |  | 4063550 | 3.900 | Q101164
1667 | CALIFORNIA | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | Q101165 | This is a Safety project by the California Department of Transportation. The project is described as: On Route 101 near Prundale construct new interchange at San Juan Road. | Other | 2010-03-07 | 2010-03-07 | 2015-02-01 |  | 10450000 | 1.300 | Q101165
1668 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | Q101169 | This is a Safety project by the California Department of Transportation. The project is described as: In Mendocino County, at various locations from 0.3 mile south of Russian River Bridge to 0.5 mile | Safety/Traffic Management | 2010-07-05 | 2010-08-02 | 2011-09-27 | 2011-09-27 | 2737931 | 101.500 | Q101169
1669 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MENDOCINO |  | 01 | Q101170 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: Near Ukiah, from 0.2 mile north of Robinson Creek Bridge #10-000 | Pavement Improvement | 2010-08-10 | 2010-08-25 | 2011-05-16 | 2012-03-05 | 14925447 | 12.600 | Q101170
1670 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | 30 | Q101182 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Calabasas and Agoura Hills, from Las Virgenes Road to the Los Angeles/Ventura County line. | Pavement Improvement | 2011-02-16 | 2011-03-18 | 2011-09-17 | 2011-09-17 | 8123600 |  | Q101182
1671 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | STANISLAUS |  | 18 | S033069 | This is a Pavement Restoration and Rehabilitation project by the California Department of Transportation. The project is described as: In Newman, from Inyo Street to south of Jensen Road; also in Pat | Pavement Improvement | 2009-08-26 | 2010-06-01 | 2010-08-13 | 2010-08-13 | 1713285.32 | 14.000 | S033069
1672 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | SANTA CLARA |  | 15 | S035007 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Santa Clara County near Los Gatos, from Black Road to the State Route 35 separation. | Pavement Improvement | 2009-07-21 | 2009-08-19 | 2009-10-26 | 2009-10-26 | 1120693.48 | 6.420 | S035007
1673 | CALIFORNIA | Completed | C220 | Highway Infrastructure Investment Grant | CALIFORNIA | INYO |  | 25 | S168053 | This is a Facilities for Pedestrians and Bicycles project by the California Department of Transportation. The project is described as: Near Bishop, from Red Hill Road to Ed Powers Road. | Transportation Enhancements | 2010-05-27 | 2010-06-01 | 2010-09-16 | 2010-09-16 | 828741.65 | 1.600 | S168053
1674 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | KERN | BAKERSFIELD | Multiple | S204004 | This is a Bridge Replacement, No Added Capacity project by the California Department of Transportation. The project is described as: In Bakersfield, at Chester Avenue Bridge #50-183. | Bridge Replacement | 2009-07-03 | 2009-08-24 | 2011-12-06 | 2011-12-09 | 15032275 | 1.000 | S204004
1675 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | FRESNO |  | 20 | X019021 | This is a Pavement Resurfacing project by the California Department of Transportation. The project is described as: In Fresno County on Route 33 near Harris Ranch, from I-5 to 1.7 miles north of Harl | Pavement Improvement | 2009-06-18 | 2009-07-06 | 2009-09-02 | 2009-09-02 | 1427418.74 | 1.000 | X019021
1676 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | VENTURA, LOS ANGELES |  | Multiple | X037145 | This is a Safety project by the California Department of Transportation. The project is described as: In Ventura County in and near Oxnard from Wood Road to Mobil Pier Road and in routes 23,33,101,11 | Safety/Traffic Management | 2009-10-15 | 2010-01-01 | 2011-06-23 | 2011-06-23 | 852702.96 | 1.000 | X037145
1677 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | X037146 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles County in Santa Monica from Lincoln Blvd to Palasades pedestrian overcrossing and | Safety/Traffic Management | 2009-10-15 | 2009-11-09 | 2010-12-03 | 2010-12-03 | 959780.07 | 1.000 | X037146
1678 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | X037147 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles County from Santa Fe Springs to Los Angeles from Valley-View Avenue to Soto Street | Other | 2009-10-20 | 2009-12-14 | 2011-06-03 | 2011-06-03 | 943700.13 | 1.000 | X037147
1679 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | LOS ANGELES | LOS ANGELES, CA | Multiple | X037148 | This is a Safety project by the California Department of Transportation. The project is described as: In Los Angeles and Long Beach, on various routes. | Safety/Traffic Management | 2009-09-01 | 2009-10-17 | 2010-07-28 | 2010-07-28 | 614100.7 | 1.000 | X037148
1680 | CALIFORNIA | Completed | C240 | Highway Infrastructure Investment Grant | CALIFORNIA | MONTEREY |  | 17 | X053022 | This is a Safety project by the California Department of Transportation. The project is described as: Pacific Grove to Castroville, south of Route 1 to Tembladero Slough; also on Route 68 east of Fairground road. | Safety/Traffic Management | 2009-06-29 | 2009-09-01 | 2010-07-08 | 2010-07-08 | 1599643.6 | 17.100 | X053022
1681 | CALIFORNIA | Underway | C240,C230 | Highway Infrastructure Investment Grant | CALIFORNIA | ORANGE | STATEWIDE | Multiple | X059051 | This is a Traffic Management Engineering project by the California Department of Transportation. The project is described as: Provide direct HOV Connection between SR-22 and I-405. | Pavement Widening | 2010-06-25 | 2010-09-01 | 2014-03-28 |  | 49634873 | 2.100 | X059051
1682 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 002A003 | Asphalt resurfacing of 2.4 miles of State Highway 2 from Vasquez to Quebec, and adds curb ramps and safety improvements. | Pavement Improvement | 2010-04-23 | 2010-06-14 | 2010-09-22 | 2010-12-30 | 1619093 | 2.485 | 002A003
1683 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WASHINGTON |  | 04 | 0061080 | Asphalt resurfacing over 9 miles of State Highway 6 in Washington and Logan Counties. | Pavement Improvement | 2010-03-16 | 2010-07-06 | 2010-10-11 | 2011-04-25 | 3467546 | 9.480 | 0061080
1684 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | MESA |  | 03 | 0063031 | Enhancement Project: constructs bicycle and pedestrian trail in Fruita along United States Highway 6. | Transportation Enhancements | 2009-09-21 | 2009-09-21 | 2010-05-17 | 2010-06-08 | 433399 | 0.630 | 0063031
1685 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | EAGLE |  | 02 | 006A043 | Enhancement Project: constructs bicycle and pedestrian trail to connect Town of Minturn to Dowd Junction Eagle County (ECO) trail. | Transportation Enhancements | 2009-09-21 | 2009-09-22 | 2009-11-04 | 2009-11-12 | 282396 | 0.420 | 006A043
1686 | COLORADO | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | 006A047 | Project to acquire right-of-way and conduct relocations at United States Highway 6 and Wadsworth Boulevard interchange from 4th Avenue to 14TH Avenue in preparation for reconstruction project to add lanes and improve safety. | Other | 2010-08-09 | 2010-08-09 | 2012-03-10 |  | 4946658 | 2.670 | 006A047
1687 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | SUMMIT |  | 02 | 0091032 | Widens State Highway 9 to two lanes in each direction and constructs a new pedestrian bridge and retaining wall. The project will also relocate a bicycle path and improve drainage north of Breckenridge in Summit County. | Pavement Widening | 2009-06-04 | 2009-06-04 | 2010-01-13 | 2010-12-23 | 8193464 | 1.550 | 0091032
1688 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | RIO BLANCO |  | 03 | 0131055 | Reconstructs five miles of SH 13 in asphalt, adds eight-foot shoulders and climbing and passing lanes at Rio Blanco Hill in Rio Blanco County. The improvements will enhance recreational bicycling in t | Pavement Widening | 2009-07-17 | 2009-07-17 | 2010-10-01 | 2010-11-12 | 10359717 | 5.290 | 0131055
1689 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | JACKSON |  | 03 | 0141020 | Asphalt resurfacing of State Highway 14 east of Cameron Pass in Larimer and Jackson counties. | Pavement Improvement | 2009-06-04 | 2009-06-09 | 2009-11-18 | 2010-06-25 | 5177001 | 13.390 | 0141020
1690 | COLORADO | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | JACKSON |  | 03 | 0141021 | Resurfaces and repairs shoulder on 23 miles of State Highway 14 east of Muddy Pass. | Pavement Improvement | 2010-04-06 | 2010-07-12 | 2010-10-31 | 2010-10-19 | 6337976 | 23.000 | 0141021
1691 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | CHAFFEE |  | 05 | 0242045 | Asphalt resurfacing of 12.5 miles of United States Highway 24/United States Highway 285 north of Johnson Village in Chaffee County. | Pavement Improvement | 2009-05-19 | 2009-08-07 | 2009-11-27 | 2009-11-05 | 3714986 | 12.680 | 0242045
1692 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | EL PASO |  | 05 | 0243076 | Replaces a structurally deficient bridge in Falcon over Falcon Creek and improves drainage in El Paso County. | Bridge Replacement | 2009-09-16 | 2009-09-16 | 2010-08-31 | 2010-09-29 | 3378144 | 0.800 | 0243076
1693 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ELBERT |  | 06 | 0243079 | Resurfaces 11 miles of SH 24 west of Limon. | Safety/Traffic Management | 2010-02-26 | 2010-05-03 | 2010-08-13 | 2010-08-27 | 5496017 | 11.030 | 0243079
1694 | COLORADO | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | LAS ANIMAS | PUEBLO | 03 | 0251335 | Constructs the Purgatoire River Pedestrian Trail, adds street lights, parking lot paving, curb and gutter, drainage inlets, landscaping, and sidewalk along Interstate 25 in Trinidad. | Pavement Improvement | 2009-06-16 | 2009-05-29 | 2011-07-03 |  | 6572326 | 3.000 | 0251335
1695 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DENVER | DENVER, CO | 01 | 0252402 | Resurfaces approximately 3 miles of Interstate 25 in asphalt in Denver from 6th Avenue to 23rd Avenue. | Pavement Improvement | 2009-04-28 | 2009-06-14 | 2009-11-04 | 2010-06-15 | 3421919 | 2.000 | 0252402
1696 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | 0253206 | Improves 5 miles of roadway surface on Interstate 25 from the Crossroads Interchange at Loveland to State Highway 392 at the Windsor Interchange. | Pavement Improvement | 2009-07-01 | 2009-07-05 | 2009-10-19 | 2010-05-26 | 4594338 | 4.012 | 0253206
1697 | COLORADO | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | 0253207 | Constructs roundabouts at Interstate 25 and Crossroads at Loveland Interchange to improve mobility and safety. | Safety/Traffic Management | 2009-08-31 | 2009-08-31 | 2010-08-31 |  | 3000000 | 0.950 | 0253207
1698 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WELD |  | 04 | 0342050 | Installs a traffic signal at the intersection of United States Highway 34 and Weld County Road 49, west of Kersey. | Safety/Traffic Management | 2009-08-03 | 2009-08-08 | 2009-10-03 | 2010-03-23 | 381589 | 0.200 | 0342050
1699 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WASHINGTON |  | 04 | 0343030 | Resurfaces 15 miles of State Highway 34 from Brush to Akron with chip seal. | Pavement Improvement | 2010-02-03 | 2010-06-30 | 2010-07-20 | 2010-07-16 | 1625089 | 15.200 | 0343030
1700 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | LARIMER |  | 04 | 0361089 | Resurfaces 22 miles of United States Highway 36 between Lyons and Estes Park with chip seal to improve the roadway surface condition. | Pavement Improvement | 2009-06-22 | 2009-07-20 | 2009-08-24 | 2009-09-30 | 1396055 | 21.770 | 0361089
1701 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | 0361090 | Installs a new traffic signal at the intersection of United States Highway 36 and Broadway in Boulder. | Safety/Traffic Management | 2009-07-02 | 2009-08-03 | 2009-10-13 | 2010-04-01 | 326771 | 0.270 | 0361090
1702 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LINCOLN | DENVER, CO | 04 | 0405033 | Enhancement Project: rehabilitate railroad roundhouse in Lincoln County, to become a railroad museum in Hugo. | Transportation Enhancements | 2009-11-18 | 2010-01-26 | 2010-09-10 | 2010-09-03 | 511287 | 0.240 | 0405033
1703 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | PUEBLO | PUEBLO | 03 | 0504060 | Resurfaces and makes safety improvements on United States Highway 50 east of Pueblo. | Pavement Improvement | 2010-03-19 | 2010-04-05 | 2010-09-27 | 2011-02-15 | 5070313 | 11.400 | 0504060
1704 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | CHAFFEE |  | 05 | 050A009 | Enhancement Project: constructs curb, gutter, sidewalk, and Americans With Disabilities Acts (ADA) ramps in Salida on United States Highway 50. | Transportation Enhancements | 2009-09-03 | 2009-09-18 | 2009-12-27 | 2009-12-15 | 491470 | 0.766 | 050A009
1705 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | 052A031 | Replaces the bridge over Boulder Creek on State Highway 52 at the Boulder/Weld County Line. | Bridge Replacement | 2009-07-16 | 2009-08-31 | 2011-06-30 | 2008-03-07 | 4192992 | 0.511 | 052A031
1706 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WELD |  | 04 | 060A013 | Installs a new traffic signal at the intersection of the Interstate 25 exit ramps and frontage roads with State Highway 60 (Johnstown Exit). | Safety/Traffic Management | 2009-07-09 | 2009-08-03 | 2009-09-28 | 2009-10-16 | 409853 | 0.170 | 060A013
1707 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | SAN MIGUEL |  | 03 | 062A013 | Resurface a total of 21.5 miles of State Highway 62 (Dallas Divide in Ouray and San Miguel Counties between Placerville and Ridgway) in asphalt and repair embankments. Project includes some work on United States Highway 550 at Ridgway. | Pavement Improvement | 2009-05-12 | 2009-05-12 | 2009-10-02 | 2009-10-12 | 4000000 | 24.900 | 062A013
1708 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | MESA | GRAND JUNCTION | 03 | 0701197 | Improves safety by widening the acceleration and deceleration lanes at the interchange on Interstate 70 at the Palisade exit in Mesa County. The improvements will upgrade the interchange to current design standards. | Pavement Improvement | 2009-06-22 | 2009-09-21 | 2009-12-02 | 2009-12-02 | 1400712 | 1.000 | 0701197
1709 | COLORADO | Completed | C200 | Highway Infrastructure Investment Grant | COLORADO | SUMMIT |  | 02 | 0702283 | Resurfaces 14 miles of I-70 from milepost 190 to 204 as well as the right lane of eastbound I-70 between milepost 180 and 190. Numerous bridges along the I-70 corridor will also be rehabilitated by r | Pavement Improvement | 2009-05-05 | 2009-05-05 | 2009-11-08 | 2010-07-29 | 8000000 | 24.000 | 0702283
1710 | COLORADO | Completed | C200 | Highway Infrastructure Investment Grant | COLORADO | EAGLE |  | 02 | 0702297 | This safety improvement project will construct 4 roundabouts in Edwards at the interchange of Interstate 70 in Eagle County. | Safety/Traffic Management | 2010-02-26 | 2010-03-22 | 2010-11-19 | 2011-06-06 | 9347903.65 | 0.770 | 0702297
1711 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | 0703350 | Repairs and replaces concrete slabs on Interstate 70 between Kipling Street and Wadsworth Boulevard in Wheat ridge. | Pavement Improvement | 2009-04-21 | 2009-05-19 | 2009-08-22 | 2009-10-08 | 1732584 | 2.070 | 0703350
1712 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | EAGLE | DENVER, CO | 02 | 0703353 | Installs various truck parking management components (electronic signs, closed-circuit cameras, and power and communications systems) to provide notification during inclement weather along Interstate 70 between Dotsero and Georgetown. | Safety/Traffic Management | 2009-06-22 | 2009-06-22 | 2009-10-29 | 2010-10-08 | 2199037 | 54.440 | 0703353
1713 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 0704217 | Installs cable guardrail in the median at Interstate 70 between Pena Boulevard and Tower Road in Aurora to prevent crossover accidents. | Safety/Traffic Management | 2009-06-22 | 2009-07-13 | 2009-09-07 | 2009-09-30 | 294430 | 2.180 | 0704217
1714 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | KIT CARSON |  | 04 | 0705078 | Concrete slab replacement of various sections of Interstate 70 from Agate, Colorado to Kansas State Line. | Pavement Improvement | 2010-11-02 | 2010-11-08 | 2011-07-31 | 2011-06-10 | 1815122 | 110.088 | 0705078
1715 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 0761200 | Construct 2 roundabouts at the ramps to Interstate 76 on 96th Avenue in Commerce City. | Safety/Traffic Management | 2009-05-21 | 2009-06-22 | 2009-12-18 | 2010-06-10 | 2222733 | 0.040 | 0761200
1716 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 0761201 | Replaces 2 bridges on Interstate 76 over the Union Pacific Railroad and State Highway 224 in Commerce City. | Bridge Replacement | 2009-06-02 | 2009-07-06 | 2011-02-03 | 2010-12-20 | 9843607 | 1.043 | 0761201
1717 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | SEDGWICK |  | 04 | 0762045 | Reconstructs 11 miles of eastbound Interstate 76 in concrete between Sedgwick and the Nebraska state line. | Pavement Improvement | 2009-07-10 | 2009-07-13 | 2010-09-22 | 2010-09-22 | 15570336 | 19.490 | 0762045
1718 | COLORADO | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | GARFIELD |  | 03 | 0821087 | This safety improvement project at the Interstate 70 interchange with United State Highway 6 and State Highway 82 in Glenwood Springs will upgrade traffic signals and improve ramp width and length to benefit both pedestrians and vehicles. | Other | 2009-08-03 | 2009-08-17 | 2009-11-24 | 2009-11-20 | 2500000 | 3.020 | 0821087
1719 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DOUGLAS | DENVER, CO | 06 | 0852095 | Widens 1 mile of United State Highway 85 to 2 lanes in each direction, adding shoulders and a raised median with controlled access on United State Highway 85 between Titan Road and Cook Ranch Road in Douglas County. | Pavement Widening | 2009-08-17 | 2009-09-28 | 2010-09-23 | 2010-10-15 | 5400000 | 7.480 | 0852095
1720 | COLORADO | Underway | C240,C230 | Highway Infrastructure Investment Grant | COLORADO | DOUGLAS | DENVER, CO | 06 | 0852103 | This project is reconstructing the interchange of United States Highway 85 (Santa Fe) and C-470 to include a new southbound United States Highway 85 to eastbound C-470 flyover ramp. | New Bridge Construction | 2010-05-20 | 2010-06-07 | 2011-12-09 |  | 5864928 | 1.900 | 0852103
1721 | COLORADO | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | WELD |  | 04 | 0853072 | Conducts resurfacing on 8.5 miles of United State Highway 85 from mile 301 to mile 309.5, and replaces two bridges. | Bridge Replacement | 2010-07-30 | 2010-08-09 | 2011-08-31 |  | 4986402 | 8.542 | 0853072
1722 | COLORADO | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | 0853079 | Installation of conduit, fiber, and CCTV along State Highway 85 from Interstate 76 to State Highway 7. | Safety/Traffic Management | 2010-10-22 | 2010-11-01 | 2011-09-30 |  | 1150000 | 11.112 | 0853079
1723 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ARAPAHOE | DENVER, CO | 06 | 088A026 | Asphalt resurfacing of State Highway 88 (Belleview Avenue) between Santa Fe Drive and Federal Boulevard in Littleton. | Pavement Improvement | 2009-04-28 | 2009-05-18 | 2009-06-29 | 2009-07-17 | 431702 | 0.900 | 088A026
1724 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DELTA |  | 03 | 092A022 | Asphalt resurfacing of 5 miles of State Highway 92 and adds passing lanes and shoulders to improve recreational bicycling between Austin and Hotchkiss in Delta County. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2010-10-30 | 2010-10-29 | 8604148 | 4.100 | 092A022
1725 | COLORADO | Underway | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | FREMONT |  | 05 | 1151025 | Asphalt resurfacing of 20 miles of State Highway 115 in El Paso and Fremont Counties. | Pavement Improvement | 2010-10-05 | 2010-10-12 |  |  | 2015519 | 20.234 | 1151025
1726 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | GUNNISON |  | 03 | 135A025 | Enhancement Project: constructs bicycle and pedestrian trail, and bridge along State Highway 135 north of Gunnison. | Transportation Enhancements | 2010-03-16 | 2010-04-07 | 2010-09-05 | 2011-02-28 | 374515 | 0.170 | 135A025
1727 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | RIO GRANDE |  | 03 | 1602122 | Asphalt resurfacing of 3 miles of United State Highway 160 west of Del Norte in Rio Grande County. | Pavement Improvement | 2009-06-16 | 2009-10-05 | 2009-11-09 | 2009-11-03 | 1468886 | 3.320 | 1602122
1728 | COLORADO | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | LA PLATA |  | 03 | 1602123 | Relocates the intersection of La Plata County Roads 222 and 223 with United States Highway 160 east of Durango, and adds auxiliary lanes to improve sight distance. | New Construction | 2010-02-26 | 2010-02-26 | 2011-05-26 | 2011-09-09 | 4300000 | 1.774 | 1602123
1729 | COLORADO | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | RIO GRANDE |  | 03 | 1602125 | Asphalt resurfacing of a second phase of United States Highway 160 west to Del Norte in Rio Grande County, and constructs Americans With Disabilities Act (ADA) with ramps. | Pavement Improvement | 2010-03-25 | 2010-04-06 | 2010-07-16 | 2010-06-28 | 7441823 | 14.000 | 1602125
1730 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ALAMOSA |  | 03 | 1603027 | Asphalt resurfacing of 6 miles of United States Highway 160 east of Alamosa. | Pavement Improvement | 2009-06-12 | 2009-07-14 | 2009-09-08 | 2009-09-03 | 2736807 | 6.755 | 1603027
1731 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | LA PLATA |  | 03 | 160A010 | Constructs a new eastbound on-ramp as part of an already scheduled project that will widen United States Highway 160 to 4 lanes, and relocate a traffic signal due to the widening east of Durango. | New Construction | 2009-09-03 | 2009-09-03 | 2010-04-21 | 2010-08-27 | 3619600 | 1.490 | 160A010
1732 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DOUGLAS | DENVER, CO | 06 | 177A006 | Asphalt resurfacing of State Highway 177 (University Avenue) in Centennial, from C-470 to Arapahoe. | Pavement Improvement | 2009-05-12 | 2009-05-26 | 2009-09-08 | 2009-08-14 | 1559083 | 2.000 | 177A006
1733 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ARAPAHOE | DENVER, CO | 07 | 2254078 | Phase 1 of project to reconstruct the Interstate 225 / Colfax interchange in Aurora to rebuild the southbound ramp from Colfax to Interstate 225. | Pavement Widening | 2009-11-23 | 2009-11-30 | 2010-05-12 | 2010-09-24 | 1077890 | 0.096 | 2254078
1734 | COLORADO | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | ARAPAHOE | DENVER, CO | 07 | 2254079 | Phase 2 of the reconstruction of the Interstate 55/Colfax interchange in Aurora to provide access from Interstate 225 to 17th Avenue. | Pavement Widening | 2010-03-26 | 2010-03-26 | 2012-02-09 |  | 11300000 | 0.700 | 2254079
1735 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | 257A007 | Installs a new traffic signal at the intersection of State Highway 257 and Garden Drive in Windsor. | Safety/Traffic Management | 2009-07-16 | 2009-08-10 | 2009-10-05 | 2009-12-01 | 244422 | 0.160 | 257A007
1736 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | SAGUACHE |  | 03 | 2852016 | Asphalt resurfacing of 8 miles of United States Highway 285 south of Saguache. | Pavement Improvement | 2009-06-12 | 2009-08-27 | 2009-11-12 | 2009-11-06 | 3660211 | 9.480 | 2852016
1737 | COLORADO | Underway | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 06 | 2854117 | Constructs a grade-separated interchange at Elk Creek Road, new frontage roads and a wildlife crossing underpass. When complete, Elk Creek Rd. will run under US 285. THe project is located in Jefferso | Pavement Widening | 2009-08-26 | 2009-08-26 | 2010-12-08 |  | 9000000 | 0.664 | 2854117
1738 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | PARK |  | 05 | 2854120 | Enhancement Project: constructs pedestrian bridge and trail in Fairplay. | Transportation Enhancements | 2010-03-11 | 2010-04-26 | 2010-06-30 | 2010-09-16 | 253010 | 2.000 | 2854120
1739 | COLORADO | Underway | C250,C200 | Highway Infrastructure Investment Grant | COLORADO | BACA |  | 04 | 2871032 | Concrete resurfacing on United States Highway 287 and improve drainage and shoulder embankments south of Springfield in Baca County. | Pavement Improvement | 2009-10-07 | 2009-10-12 | 2010-10-04 |  | 12200277 | 8.300 | 2871032
1740 | COLORADO | Completed | C200,C240 | Highway Infrastructure Investment Grant | COLORADO | MESA |  | 03 | 340A015 | Installs two new traffic signals in Fruita west of the Interstate 70 interchange on State Highway 240 in Mesa County, and makes intersection safety improvements for pedestrians and vehicles. | Pavement Widening | 2009-09-21 | 2010-03-08 | 2010-05-24 | 2010-05-26 | 1383153 | 0.890 | 340A015
1741 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | DOUGLAS | DENVER, CO | 06 | 4701118 | Repairs or replaces concrete slabs on C-470 and resurfaces C-470 in asphalt between Santa Fe Drive and I-25 in Douglas County. Rehabilitates the C-470 bike path between I-70 and I-25 in Jefferson, Ara | Pavement Improvement | 2009-06-16 | 2009-07-09 | 2010-09-04 | 2011-02-07 | 31215789 | 9.243 | 4701118
1742 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | OURAY |  | 03 | 5502064 | Enhancement Project: constructs wildlife fence and ramps to reduce wildlife collisions along United States Highway 550. | Transportation Enhancements | 2010-01-25 | 2010-01-25 | 2010-04-30 | 2010-05-18 | 166666 | 8.910 | 5502064
1743 | COLORADO | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | OURAY |  | 03 | 5502069 | Project resurfaces State Highway 550 from Colona to Chipeta. | Pavement Improvement | 2010-11-05 | 2011-05-02 | 2011-07-27 |  | 915691 | 9.070 | 5502069
1744 | COLORADO | Underway | C240 | Highway Infrastructure Investment Grant | COLORADO | DENVER | DENVER, CO | 01 | C010101 | Replaces the Alameda bridge over Interstate 25 in Denver with one that is wider to accommodate an additional lane on Interstate 25 in each direction. | Bridge Replacement | 2010-02-11 | 2010-04-01 | 2012-03-23 |  | 33447164 | 0.550 | C010101
1745 | COLORADO | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | DENVER | DENVER, CO | 01 | C010103 | Construct a new interchange at Interstate 70 and Central Park Boulevard in Denver. | New Construction | 2010-01-29 | 2010-01-29 | 2011-10-01 |  | 12000000 | 1.500 | C010103
1746 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | PUEBLO | PUEBLO | 03 | C020033 | Enhancement Project: landscaping and irrigation installation for the Eastern Gateway Landscape Project located at the intersection of State Highway 50B and State Highway 47 in Pueblo. | Transportation Enhancements | 2010-02-08 | 2010-04-01 | 2010-06-25 | 2010-10-01 | 381424 | 0.000 | C020033
1747 | COLORADO | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | C030035 | Asphalt resurfacing of Weld County Road 74 from Weld County Road 13 to State Highway 357. | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2009-09-18 | 2009-10-09 | 459627 | 0.000 | C030035
1748 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | C060049 | Enhancement Project: constructs a bicycle/pedestrian underpass under State Highway 392 in Windsor. | Transportation Enhancements | 2009-07-28 | 2009-08-12 | 2009-10-09 | 2010-10-20 | 487037 | 0.369 | C060049
1749 | COLORADO | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | C060050 | Asphalt resurfacing of Larimer County Road 17 between Berthoud and Fort Collins. | Pavement Improvement | 2009-07-28 | 2009-08-03 | 2009-10-19 | 2010-11-30 | 3582424 | 0.000 | C060050
1750 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | ARAPAHOE | DENVER, CO | 06 | C100028 | Enhancement Project: construct an extension to the bicycle and pedestrian bridge over Interstate 25 south of Dry Creek Road to extend over Inverness Drive in Arapahoe County. | Transportation Enhancements | 2009-11-18 | 2009-11-18 | 2010-07-21 | 2011-01-27 | 708947 | 0.000 | C100028
1751 | COLORADO | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 07 | C120018 | Construct an underpass of Pecos Street under the railroad tracks, south of Interstate 76 in Adams County. | Pavement Improvement | 2009-12-16 | 2010-01-19 | 2012-01-10 |  | 4450000 | 0.000 | C120018
1752 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | PROWERS |  | 04 | C170006 | Enhancement Project: designs and constructs a transportation museum in Lamar in Prowers County. | Transportation Enhancements | 2010-06-05 | 2010-07-05 | 2010-11-12 | 2011-06-06 | 330750 | 0.000 | C170006
1753 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LA PLATA |  | 03 | C200006 | Enhancement Project: constructs shared use path along County Road 501 in Bayfield. | Transportation Enhancements | 2009-08-24 | 2009-08-24 | 2009-12-07 | 2010-06-11 | 223724 | 0.000 | C200006
1754 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | BENT |  | 04 | C290007 | Enhancement Project: historic restoration through Town Square in Las Animas in Bent County, and install streetscaping, sidewalks, and landscaping. | Transportation Enhancements | 2010-03-17 | 2010-03-17 | 2010-05-01 |  | 121000 | 0.000 | C290007
1755 | COLORADO | Completed | C220,C240 | Highway Infrastructure Investment Grant | COLORADO | CLEAR CREEK |  | 02 | C510023 | Enhancement Project: constructs asphalt recreation trail from Bakerville to Loveland Basin in Clear Creek County along Interstate 70. | Transportation Enhancements | 2010-05-07 | 2010-06-09 | 2010-08-31 | 2010-08-14 | 903625 | 0.000 | C510023
1756 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | PITKIN |  | 03 | C570017 | Enhancement Project: restoration of highway, intersection, and Pitkin County Coke Ovens in Redstone. | Transportation Enhancements | 2010-09-16 | 2011-05-01 | 2011-10-25 |  | 143089 |  | C570017
1757 | COLORADO | Underway | C490 | OJT/SS | COLORADO | STATEWIDE |  |  | HQ00023 | Provides on-the-job training to construction workers to develop construction skills. | Other | 2010-01-01 | 2010-01-01 | 2011-01-30 |  | 250000 | 0.000 | HQ00023
1758 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | Multiple | M040017 | Enhancement Project: construct a bicycle and pedestrian trail on the south side of West 86th Parkway in Arvada to connect the existing trails. | Transportation Enhancements | 2009-10-13 | 2009-10-22 | 2009-12-21 |  | 300000 | 0.000 | M040017
1759 | COLORADO | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | M040019 | This project widens 74th Avenue from Kipling to Carr to accommodate bicycle lanes and add sidewalks. | Transportation Enhancements | 2010-05-03 | 2010-05-03 | 2010-12-15 |  | 281773 | 0.000 | M040019
1760 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LA PLATA |  | 03 | M065003 | Enhancement Project: constructs sidewalks along United States Highway 160 business route in Bayfield. | Transportation Enhancements | 2009-08-20 | 2009-08-24 | 2009-11-30 | 2010-06-14 | 200000 | 0.110 | M065003
1761 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | M070002 | Enhancement Project: constructs bicycle and pedestrian improvements on Main Street in Berthoud. | Transportation Enhancements | 2010-07-06 | 2010-07-12 | 2010-08-25 | 2011-05-20 | 134000 | 0.010 | M070002
1762 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | PUEBLO | PUEBLO | 03 | M086056 | Enhancement Project: pedestrian trail replacement and streetscape on Northern Avenue from Vinewood Lane to Prairie Avenue in Pueblo. | Transportation Enhancements | 2010-04-01 | 2010-04-01 | 2010-06-25 | 2010-10-26 | 165000 | 0.000 | M086056
1763 | COLORADO | Completed | C220,C240 | Highway Infrastructure Investment Grant | COLORADO | PUEBLO | PUEBLO | 03 | M086058 | Constructs Veteran's memorial pedestrian bridge in Gateway Park at corner of Grand Avenue and South Main Street in Pueblo. | Transportation Enhancements | 2010-03-23 | 2010-03-23 | 2010-12-24 | 2010-12-01 | 600000 | 0.000 | M086058
1764 | COLORADO | Underway | C220,C230 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | STATEWIDE | 02 | M110065 | Enhancement Project: constructs pedestrian access ramps at various intersections in Boulder to meet Americans with Disabilities Acts (ADA) requirements. | Transportation Enhancements | 2009-09-08 | 2009-09-14 | 2009-11-09 |  | 732624 | 0.000 | M110065
1765 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | M110066 | Enhancement Project: constructs bicycle/pedestrian crossing treatments including medians, striping, flashing beacons, and signage at the Folsom Street and Spruce Street intersection in Boulder. | Transportation Enhancements | 2009-09-08 | 2009-09-08 | 2009-12-08 | 2009-11-21 | 273270 | 0.000 | M110066
1766 | COLORADO | Underway | C220,C230 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | STATEWIDE | 02 | M110073 | Enhancement Project: construction of a bicycle and pedestrian trail along State Highway 157 from Goose Creek to Valmont in Boulder. | Transportation Enhancements | 2011-01-03 | 2010-08-09 |  |  | 375843 | 0.000 | M110073
1767 | COLORADO | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | M190003 | Asphalt resurfacing of 4th Avenue(Weld County Road 74) in Severance, 2.5 miles west of Weld County Road 25. | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2009-11-30 | 2009-10-28 | 838000 | 0.000 | M190003
1768 | COLORADO | Underway | C220,C240,C230 | Highway Infrastructure Investment Grant | COLORADO | EL PASO | COLORADO SPRINGS | 05 | M240121 | Widens Woodmen Road and constructs a new interchange at Academy Boulevard in Colorado Springs, including construction of sidewalks and a bicycle path. | Pavement Widening | 2009-09-18 | 2009-09-24 | 2011-11-15 |  | 35031818 | 0.000 | M240121
1769 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | LOGAN |  | 04 | M256012 | Enhancement Project: improves sidewalks and Americans With Disabilities Act (ADA) ramps along 7th Street in Sterling. | Transportation Enhancements | 2010-06-01 | 2010-06-01 | 2010-08-03 |  | 211000 | 0.000 | M256012
1770 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | DENVER | DENVER, CO | 01 | M320064 | Enhancement Project: striping and signage on various designated bicycle paths on the streets of Denver. | Transportation Enhancements | 2009-10-22 | 2009-10-26 | 2010-07-09 |  | 188726 | 0.000 | M320064
1771 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 02 | M356024 | Enhancement Project: replace existing 4' sidewalks with 8' sidewalks to serve as a bicycle and pedestrian trail on Bradburn Boulevard from 73rd Avenue to Turnpike Drive in Westminster. | Transportation Enhancements | 2009-07-23 | 2009-07-27 | 2009-09-25 | 2009-09-30 | 260000 | 0.000 | M356024
1772 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | WELD | BOULDER | 02 | M400004 | Enhancement Project: construct bicycle paths on the north and south sides of Leon Wurl Parkway in Erie from Bonanza Drive east to Interstate 25. | Transportation Enhancements | 2009-10-12 | 2009-10-19 | 2010-02-16 |  | 587066 | 0.000 | M400004
1773 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | M400005 | Enhancement Project: constructs bicycle lanes on East County Line Road from State Highway 7 to Erie Parkway in Erie. | Transportation Enhancements | 2010-03-15 | 2010-03-15 | 2010-06-13 | 2011-05-13 | 388000 | 0.000 | M400005
1774 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | LARIMER |  | 04 | M405013 | Enhancement Project: constructs Fall River Trail/Path in Estes Park. | Transportation Enhancements | 2009-10-05 | 2009-10-08 | 2009-12-17 | 2010-03-28 | 140012 | 0.730 | M405013
1775 | COLORADO | Underway | C220,C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | STATEWIDE | 04 | M415011 | Enhancement Project: construct bicycle and pedestrian improvements on United States Highway 85 service road in Evans. | Transportation Enhancements | 2010-03-15 | 2010-03-22 | 2010-06-26 |  | 160000 | 0.000 | M415011
1776 | COLORADO | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | M415012 | Asphalt resurfacing of 37th Street in Evans. | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-10-20 | 2009-10-22 | 324629 | 0.000 | M415012
1777 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | WELD |  | 04 | M465007 | Enhancement Project: constructs bicycle trail at South Platte River Bridge in Fort Lupton. | Transportation Enhancements | 2010-05-26 | 2010-05-26 |  |  | 90000 | 0.000 | M465007
1778 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | MORGAN |  | 04 | M470009 | Enhancement Project: constructs Rainbow Bridge kiosk and makes pedestrian improvements in Fort Morgan. | Transportation Enhancements | 2010-02-05 | 2010-03-22 | 2010-06-02 | 2010-09-01 | 140000 | 0.100 | M470009
1779 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | GARFIELD |  | 03 | M535004 | Enhancement Project: constructs a pedestrian bridge over Interstate 70 along Devereux Road in Glenwood Springs. | Transportation Enhancements | 2009-09-11 | 2009-09-15 | 2010-07-31 | 2010-07-26 | 50200 | 0.000 | M535004
1780 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | GRAND |  | 02 | M560002 | Enhancement Project:: beautification and drainage improvements in Grand Lake at the Grand Lake Welcome Center in Grand County. | Transportation Enhancements | 2010-03-23 | 2010-05-10 | 2010-06-18 | 2010-06-18 | 169000 | 0.000 | M560002
1781 | COLORADO | Underway | C220,C230 | Highway Infrastructure Investment Grant | COLORADO | WELD | FORT COLLINS | 04 | M570040 | Enhancement Project: constructs bicycle and pedestrian trail along the Greeley #3 ditch. | Transportation Enhancements | 2010-06-03 |  |  |  | 212000 | 0.000 | M570040
1782 | COLORADO | Completed | C220 | Highway Infrastructure Investment Grant | COLORADO | ROUTT |  | 03 | M615002 | Enhancement Project: improves and extends sidewalks in Hayden. | Transportation Enhancements | 2010-04-15 | 2010-07-12 | 2010-10-10 | 2010-10-14 | 256000 | 0.250 | M615002
1783 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | M760030 | Constructs new bicycle path from Rooney Road to Indiana Street along United States Highway 6 and C-470. | Transportation Enhancements | 2010-03-04 | 2010-03-17 | 2010-06-03 |  | 153274 | 0.000 | M760030
1784 | COLORADO | Completed | C220,C240 | Highway Infrastructure Investment Grant | COLORADO | BENT |  | 04 | M780003 | Enhancement Project: historic restoration construction of sidewalks, landscaping, signage, and parking lot rehabilitation of Heritage Center in Bent County. | Transportation Enhancements | 2010-06-09 | 2010-08-16 | 2010-11-24 | 2011-08-03 | 98453 | 0.000 | M780003
1785 | COLORADO | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | M830046 | Upgrade equipment at the traffic operations center in Loveland. | Other | 2010-01-29 | 2010-01-29 | 2010-05-14 | 2010-06-03 | 129143 | 0.000 | M830046
1786 | COLORADO | Completed | C230 | Highway Infrastructure Investment Grant | COLORADO | LARIMER | FORT COLLINS | 04 | M830047 | Intersection improvements at State Highway 34 and Wilson in Loveland. | Safety/Traffic Management | 2009-09-14 | 2009-09-14 | 2009-12-01 | 2009-11-24 | 250000 | 0.000 | M830047
1787 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | M835002 | Enhancement Project: streetscape enhancements and reconstruction of Main Street (US 36) in Lyons between 3rd and 5th Avenues to include paving, curb and gutter, landscaping, and pedestrian amenities. | Transportation Enhancements | 2009-09-28 | 2009-10-12 | 2009-10-13 |  | 689000 | 0.294 | M835002
1788 | COLORADO | Underway | C220 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | BOULDER | 02 | M935001 | Enhancement Project: construct sidewalks on State Highway 119 between Eldora and Second Avenue in Nederland to connect the RTD parking. | Transportation Enhancements | 2009-09-08 | 2009-09-14 | 2009-12-12 |  | 385000 | 2.000 | M935001
1789 | COLORADO | Underway | C230 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 02 | M945001 | This project is reconstructing concrete on Huron Street from 104TH TO 112TH. | Pavement Improvement | 2010-04-16 | 2010-04-19 | 2011-03-21 |  | 3903974 | 0.000 | M945001
1790 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | LINCOLN |  | 04 | R100157 | Concrete reconstruction of pavement 8.7 miles of United States 40/United States 287 (at approximately mileposts 413-422) south of Hugo in Lincoln County. | Pavement Improvement | 2009-06-02 | 2009-07-16 | 2010-11-30 | 2010-10-26 | 11281493 | 8.700 | R100157
1791 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | ADAMS | DENVER, CO | 02 | R600340 | Installs ramp metering systems on Interstate 25, United States Highway 36, and C-470 in various locations. | Safety/Traffic Management | 2009-05-19 | 2009-06-01 | 2009-08-24 | 2009-10-06 | 259460 | 0.180 | R600340
1792 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | BOULDER | DENVER, CO | 02 | R600343 | Replaces traffic signals at the intersection of United States Highway 6, State Highway 58, and State Highway 93 in Golden, and at State Highway 128 and Simms intersection in Broomfield. | Safety/Traffic Management | 2009-06-04 | 2009-07-20 | 2009-11-02 | 2010-06-07 | 862403 | 4.380 | R600343
1793 | COLORADO | Completed | C240 | Highway Infrastructure Investment Grant | COLORADO | JEFFERSON | DENVER, CO | 07 | R600346 | Asphalt resurfacing of approximately 3 miles of United States 40 and Colfax Avenue, between Kipling Street and Sheridan Boulevard in Lakewood. | Pavement Improvement | 2009-05-01 | 2009-06-01 | 2009-09-09 | 2009-11-09 | 2231905 | 2.829 | R600346
1794 | COLORADO | Underway | C490 | OJT/SS | COLORADO | STATEWIDE |  |  | SW00836 | This grant will employ wounded veterans in transportation jobs to provide labor on highway projects and develop construction skills. | Other | 2010-03-29 | 2010-03-29 | 2012-12-31 |  | 150000 | 0.000 | SW00836
1795 | COLORADO | Underway | C490 | OJT/SS | COLORADO | STATEWIDE |  |  | SW00837 | This grant provides on-the-job training to construction workers to develop construction skills. | Other | 2010-03-29 | 2010-03-29 | 2012-12-31 |  | 210000 | 0.000 | SW00837
1796 | CONNECTICUT | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 0001315 | The project involves the reconstruction and lengthening of the existing AMTRAK bridge over Route 1, as well as the rehabilitation of a portion of Route 1 in the Town of Branford | Bridge Replacement | 2009-08-13 | 2009-08-13 | 2014-09-15 |  | 71219921.72 | 0.000 | 0001315
1797 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | MERIDEN-NEW HAVEN | 02 | 0001320 | This project involves the installation of sidewalks in Old Saybrook along Rte 1 | Transportation Enhancements | 2010-10-18 | 2010-10-18 | 2011-06-15 | 2011-07-17 | 458762 | 0.430 | 0001320
1798 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | SPRINGFIELD-CHICOPEE-HOLYOKE (MA) | 01 | 0005105 | This project will extend the life of the bridge along Route 5 over Interstate 91 in the Town of Enfield by replacing the existing deteriorated deck, bridge supports, and piers. | Bridge Improvement | 2009-06-22 | 2009-06-22 | 2010-12-13 | 2011-06-01 | 6730000 | 0.000 | 0005105
1799 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R418 | The State of Connecticut will replace overhead sign supports on multiple state highways | Safety/Traffic Management | 2009-08-03 | 2009-08-03 | 2011-07-15 | 2011-11-30 | 4651011.24 | 0.000 | 000R418
1800 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD |  | 01 | 000R430 | The State of Connecticut will install and revise traffic control signals at various intersections throughout District 1 | Safety/Traffic Management | 2009-07-27 | 2009-07-27 | 2010-08-10 | 2010-08-11 | 1350847 | 0.000 | 000R430
1801 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R442 | The State of Connecticut will install and revise traffic control signals at various intersections in District 2 to improve safety | Safety/Traffic Management | 2009-08-03 | 2009-10-31 | 2011-07-01 | 2011-04-04 | 328970 | 0.000 | 000R442
1802 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R444 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 2 to improve safety | Safety/Traffic Management | 2009-08-03 | 2009-10-31 | 2011-07-01 | 2011-04-04 | 1640252.42 | 0.000 | 000R444
1803 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 000R447 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 to improve safety | Safety/Traffic Management | 2009-08-03 | 2009-08-10 | 2011-01-24 | 2011-01-24 | 239954.44 | 0.010 | 000R447
1804 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 000R449 | The State of Connecticut will install and revise traffic control signals at various intersections in District 3 | Safety/Traffic Management | 2009-08-03 | 2009-08-10 | 2011-01-24 | 2011-01-24 | 342226.97 | 0.000 | 000R449
1805 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R453 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 4 | Safety/Traffic Management | 2009-12-11 | 2010-05-28 | 2010-07-14 | 2010-11-24 | 764070.03 | 0.000 | 000R453
1806 | CONNECTICUT | Underway | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R458 | This project will install STC traffic signals; District 2 STC signals, maintenance upgrades | Safety/Traffic Management | 2011-02-03 | 2011-07-21 | 2012-11-11 |  | 202379 | 0.000 | 000R458
1807 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R514 | The State of Connecticut will install and revise traffic control signals at multiple intersections in District 3 | Safety/Traffic Management | 2009-08-03 | 2009-08-10 | 2011-01-24 | 2011-01-24 | 1123160.9 | 0.000 | 000R514
1808 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R538 | This project consists of the replacement of bridge deck joints within District 4 | Bridge Improvement | 2009-07-24 | 2009-08-03 | 2010-01-26 | 2010-05-26 | 5599534.9 | 32.260 | 000R538
1809 | CONNECTICUT | Underway | C240,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) |  | 000R544 | Install STC traffic signals in District 3 and STC traffic signal maintenance upgrades | Safety/Traffic Management | 2011-02-03 | 2011-02-03 | 2011-11-29 |  | 794763 | 0.000 | 000R544
1810 | CONNECTICUT | Underway | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE | MERIDEN-NEW HAVEN |  | 000R581 | Install STC traffic signals, District 2 STC traffic signal maintenance upgrades | Safety/Traffic Management | 2011-02-03 | 2011-07-21 | 2012-11-11 |  | 269257 | 0.000 | 000R581
1811 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 000R594 | THE STATE OF CONNECTICUT WILL INSTALL TRAFFIC CONTROL SIGNAL CONTROLLERS, CITY OF NEW HAVEN | Other | 2010-09-11 | 2010-09-11 | 2011-10-16 | 2011-10-15 | 3817460 | 0.000 | 000R594
1812 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 03 | 000R596 | This project consists of pavement milling and resurfacing of the travel lanes, new line striping, rumble strips, and NOVACHIPTM Surface treatment that provides improved skid, wear, and rutting resiste | Pavement Improvement | 2009-10-16 | 2009-10-16 | 2010-05-17 | 2010-06-01 | 3390141.16 | 5.880 | 000R596
1813 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R597 | The State of Connecticut will conduct crack sealing and crack filling along major highways including Route 8, I-84, I-91, I-95, and I-384. This effort will help extend the lifetime of the pavements on these roadways. | Pavement Improvement | 2009-10-01 | 2009-10-01 | 2009-11-14 | 2009-12-04 | 1865912.89 | 22.270 | 000R597
1814 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R598 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists through District 1. | Safety/Traffic Management | 2009-08-31 | 2009-09-08 | 2009-09-30 | 2009-09-30 | 139004.1 | 0.000 | 000R598
1815 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R599 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 2. | Safety/Traffic Management | 2009-09-01 | 2009-10-05 | 2009-10-19 | 2009-10-19 | 124430.28 | 0.000 | 000R599
1816 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R600 | The State of Connecticut will install epoxy pavement markings and Interstae lines for safey of motorists through District 3. | Safety/Traffic Management | 2009-09-01 | 2009-09-20 | 2009-10-14 | 2009-10-14 | 219640.58 | 0.000 | 000R600
1817 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R601 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 4 | Safety/Traffic Management | 2009-09-02 | 2009-09-08 | 2010-05-17 | 2009-09-11 | 47305.11 | 0.000 | 000R601
1818 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R602 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 4 | Safety/Traffic Management | 2010-05-01 | 2010-05-01 | 2010-07-01 | 2010-07-08 | 258545.8 | 0.000 | 000R602
1819 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R603 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 3 | Safety/Traffic Management | 2010-09-01 | 2010-09-12 | 2010-10-08 | 2010-10-08 | 484675.96 | 0.000 | 000R603
1820 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R604 | The State of Connecticut will install epoxy pavement markings and Interste lines for safety of motorists throughout District 1. | Safety/Traffic Management | 2009-10-16 | 2009-10-25 | 2009-11-10 | 2009-12-01 | 300352.62 | 0.000 | 000R604
1821 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R605 | The State of Connecticut will install epoxy pavement markings and Interstate lines for safety of motorists throughout District 2. | Safety/Traffic Management | 2009-10-06 | 2009-10-19 | 2010-04-23 | 2010-05-09 | 390361.61 | 0.000 | 000R605
1822 | CONNECTICUT | Completed | C220,C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 000R606 | TOWN CENTER PEDESTRIAN AND STREETSCAPE ENHANCEMENTS, TOWN OF NEW FAIRFIELD | Transportation Enhancements | 2010-05-24 | 2010-05-20 | 2010-09-16 | 2011-05-11 | 259754 | 0.130 | 000R606
1823 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R630 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES, AND INTERSECTIONS WITHIN DISTRICT 1 | Safety/Traffic Management | 2010-07-07 | 2010-07-25 | 2010-09-28 | 2010-09-28 | 216831.89 | 0.000 | 000R630
1824 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R631 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES AND INTERSECTIONS WITHIN DISTRICT 2 | Safety/Traffic Management | 2010-06-07 | 2010-06-07 | 2010-09-15 | 2010-07-16 | 210855 | 0.000 | 000R631
1825 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) |  | 000R632 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES, AND INTERSECTIONS IN DISTRICT 3 | Safety/Traffic Management | 2010-06-18 | 2010-07-06 | 2010-09-09 | 2010-09-15 | 384719.33 | 0.000 | 000R632
1826 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R633 | THIS PROJECT INVOLVES THE INSTALLATION OF EPOXY PAVEMENT MARKINGS, LINES, AND INTERSECTIONS IN DISTRICT 4 | Safety/Traffic Management | 2010-07-15 | 2010-08-08 | 2010-10-16 | 2010-10-20 | 156643.85 | 0.000 | 000R633
1827 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R640 | This project is for the installation of epoxy pavment markings on Interstate routes. The markings will maintain delineation of existing travel lanes abnd shoulder markings, and to maintain the retro- | Safety/Traffic Management | 2011-04-01 | 2011-04-01 | 2011-06-09 | 2011-06-07 | 247203.72 | 18.400 | 000R640
1828 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R644 | This project is for the installation of durable epoxy pavement markings on Interstate routes. The installation will be to maintain the delineation of existing traffic lanes and shoulder markings and t | Safety/Traffic Management | 2011-02-16 | 2011-04-06 | 2011-06-15 | 2011-06-10 | 81885.17 | 18.420 | 000R644
1829 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | STATEWIDE |  |  | 000R657 | The timely sealing of the cracks in these roadways enhances pavement performance, while extending the pavement life in a cost effective manner. | Pavement Improvement | 2011-04-01 | 2011-04-25 | 2011-07-21 | 2011-06-08 | 513967.21 | 26.100 | 000R657
1830 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 0012138 | This project will involve the installation of sidewalks on Rte 12 from SR647 to School St and from RR avenue to Academy Hill Rd in Plainfield | Transportation Enhancements | 2010-05-05 | 2010-05-07 | 2010-09-01 | 2010-09-01 | 629759.8 | 1.200 | 0012138
1831 | CONNECTICUT | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0015103 | This project will provide for median deck repairs on the bridge carrying Route 15 (Merritt Parkway) over Reservoir Avenue in the Town of Trumbull | Bridge Improvement | 2009-06-15 | 2009-06-18 | 2012-07-27 |  | 1195115 | 0.000 | 0015103
1832 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND |  | 02 | 0031118 | This project involves the installation of sidewalks on Main St from Paden Rd to 1000 feet north of Rte 275 in Coventry | Transportation Enhancements | 2010-06-28 | 2010-06-28 | 2010-10-25 | 2010-10-22 | 499105.39 | 0.000 | 0031118
1833 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | 0032183 | INTERSECTION IMPROVEMENTS AT ROUTE 32, LATHROP RD., AND MAPLE RD., TOWN OF WATERFORD | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-09-28 | 2010-11-24 | 625632 | 0.200 | 0032183
1834 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN |  | 02 | 0032184 | The State of Connecticut will resurface Route 2 in Eastbound and Westbound directions from Colchester to Lebanon | Pavement Improvement | 2009-10-28 | 2009-10-28 | 2009-11-11 | 2010-05-07 | 3380088 | 0.020 | 0032184
1835 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND |  | 02 | 0044133 | This project will provide additional pavement shoulder width to provide a safe turning vehicle with bypassing vehicle movement | Pavement Improvement | 2011-04-28 | 2011-04-28 | 2011-07-28 | 2011-07-28 | 141998 | 0.150 | 0044133
1836 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 0044148 | route 44 and 41 sidewalks and curbing, Salisbury | Transportation Enhancements | 2010-08-09 | 2010-08-16 | 2010-12-06 | 2011-06-02 | 365877.92 | 0.244 | 0044148
1837 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 0045132 | Project is to replace the concrete crib retaining wall W/ new new structure. Original wall was built in 1929. Wall supports CT Route 45 in Washington CT | Pavement Improvement | 2010-12-16 | 2010-12-16 | 2011-09-05 | 2011-09-22 | 346064 | 0.000 | 0045132
1838 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 0089118 | This project involves the reconstruction of the existing bridge superstructure, including new steel girders and a concrete deck. Additional improvements to the approach pavement and drainage will also be completed | Bridge Improvement | 2009-07-03 | 2009-07-13 | 2010-08-03 | 2010-08-03 | 1120395.02 | 0.000 | 0089118
1839 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 0091103 | Pavement preservation will be conducted by the State of Connecticut along Interstate 91 from West Street in the Town of Rocky Hill to Route 3 in the Town of Wethersfield. Scope of work includes resurfacing 4 northbound and 4 southbound lanes. | Pavement Improvement | 2009-10-01 | 2009-10-14 | 2009-11-18 | 2009-11-17 | 4099684.52 | 4.080 | 0091103
1840 | CONNECTICUT | Underway | C250,C240 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 0097006 | This project involves the replacement of bridge#02594 on Route 97 over the Mashamoquet Brook in the town of Pomfret | Bridge Replacement | 2010-07-17 | 2010-07-17 | 2010-11-02 |  | 1094854 | 0.000 | 0097006
1841 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0111001 | THE STATE OF CONNECTICUT WILL COMPLETE A PAVING PROJECT THAT INCLUDES THE RESURFACING OF WHITNEY AVE. TOWN OF TRUMBULL | Pavement Improvement | 2010-08-12 | 2010-08-26 | 2010-10-24 | 2010-12-13 | 1032849 | 1.480 | 0111001
1842 | CONNECTICUT | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150192 | This project involves the resurfacing of the pavement, along with other bridge and safety improvements, along a section of Route 15 (Merritt Parkway) from Congress Street to Morehouse Highway | Pavement Improvement | 2009-06-15 | 2009-06-18 | 2012-07-27 |  | 23056722 | 44.060 | 0150192
1843 | CONNECTICUT | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150193 | This project will provide for the replacement of the existing Route 15 (Merritt Parkway) bridge over the Mill River in the Town of Fairfield. | Bridge Replacement | 2009-06-15 | 2009-06-18 | 2012-07-27 |  | 10103973 | 0.020 | 0150193
1844 | CONNECTICUT | Underway | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 0150194 | This project involves the resurfacing of the pavement, along with other bridge and safety improvements, along a section of Route 15 (Merritt Parkway) from Morehouse Highway to Route 8 | Pavement Improvement | 2009-06-15 | 2009-06-18 | 2012-07-27 |  | 39278907.9 | 10.730 | 0150194
1845 | CONNECTICUT | Underway | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 0529003 | This project will provide work involving the addition of left turn lanes and median islands for increased safety and streetscape improvements | Pavement Improvement | 2011-04-01 | 2011-04-01 | 2012-10-03 |  | 1414085 | 0.760 | 0529003
1846 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 01 | 0912132 | I-91 PAVEMENT PRESERVATION TOWNS OF CROMWELL AND ROCKY HILL | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-07-31 | 2010-08-18 | 2657549 | 3.620 | 0912132
1847 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | MERIDEN-NEW HAVEN | 02 | 0952111 | This project consists of replacing the bridge deck joints on the Baldwin Bridge on I95 over the Connecticut River | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2009-11-17 | 2009-11-17 | 2631100 | 0.000 | 0952111
1848 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1002105 | RESURFACING OF FORD AND BEAVER ST. ANSONIA | Pavement Improvement | 2010-09-01 | 2010-09-01 | 2010-10-15 | 2010-12-10 | 550935 | 0.000 | 1002105
1849 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1005102 | HILLCREST DR. CRACK SEALING AND 1' OVERLAY TOWN OF BARKHAMSTED | Pavement Improvement | 2010-07-08 | 2010-07-12 | 2010-09-05 | 2010-09-03 | 94442.31 | 0.000 | 1005102
1850 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 01 | 1005104 | The existing pavement has exceeded its serviceability and is in need of anew surface. The proposed improvement includes a 2" overlay of hot-mix asphalt | Pavement Improvement | 2011-06-06 | 2011-06-06 | 2011-08-04 | 2011-09-08 | 208241.48 | 0.750 | 1005104
1851 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1007105 | In the Town of Berlin, Episcopal Road will be reconstructed and paved from Deming Road to Rowley Street to improve road and dainage. | Pavement Improvement | 2010-04-05 | 2010-04-12 | 2010-06-03 | 2010-06-01 | 491625.21 | 0.510 | 1007105
1852 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 1009111 | THIS PROJECT INCLUDES THE MILLING AND PAVING OF HAWLEYVILLE ROAD, TOWN OF BETHEL | Pavement Improvement | 2010-07-16 | 2010-07-19 | 2010-09-16 | 2011-12-09 | 509563 | 1.500 | 1009111
1853 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1015118 | Congress Street Bridge (Phase1 - Partial Demolition), City of Bridgeport | Bridge Replacement | 2010-01-21 | 2010-03-02 | 2010-06-29 | 2010-06-16 | 504348.12 | 0.000 | 1015118
1854 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1015119 | The project involves the pavement rehabilitation of Iranistan Avenue and Capital in the city of Bridgeport | Pavement Improvement | 2010-08-26 | 2010-09-20 | 2011-04-17 | 2011-04-14 | 1558927.86 | 0.000 | 1015119
1855 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1017106 | THIS PROJECT INVOLVES MIX STREET RECONSTRUCTION AND NORMALIZATION OF INTERSECTION WITH MALBY STREET, BRISTOL | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2010-11-15 | 2010-11-20 | 1065600 | 0.510 | 1017106
1856 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 1018108 | THE STATE OF CONNECTICUT WILL COMPLETE A PAVING PROJECT THAT INCLUDES THE MILLING AND PAVING GRAY'S BRIDGE RD, BROOKFIELD | Pavement Improvement | 2010-06-21 | 2010-06-28 | 2010-10-03 | 2010-09-23 | 413600 | 0.000 | 1018108
1857 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1025003 | THE STATE OF CONNECTICUT WILL COMPLETE THE PAVING OF WEST JOHNSON RD, CHESHIRE | Pavement Improvement | 2010-07-14 | 2010-07-14 | 2010-08-27 | 2010-08-24 | 618408 | 0.000 | 1025003
1858 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 01 | 1029001 | RIVERTON RD. CRACK SEALING AND RUBBERIZED CHIP SEAL, TOWN OF COLEBROOK | Pavement Improvement | 2010-07-09 | 2010-07-28 | 2010-09-06 | 2010-09-22 | 95032.71 | 0.000 | 1029001
1859 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 01 | 1033107 | GEER STREET PAVEMENT PRESERVATION - CROMWELL | Pavement Improvement | 2010-08-02 | 2010-08-02 | 2010-08-31 | 2010-08-31 | 226355 | 0.960 | 1033107
1860 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | Multiple | 1034114 | MILLING AND PAVING OF WHITE STREET, FRANKLIN STREET, AND FRANKLIN STREET EXT. CITY OF DANBURY | Pavement Improvement | 2010-05-27 | 2010-05-27 | 2010-08-24 | 2010-08-31 | 1593000 | 0.000 | 1034114
1861 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1035103 | Replacement of Staircases & Railings at Noroton Heights RR Station, Town of Darien | Transportation Enhancements | 2010-05-20 | 2010-05-20 | 2010-11-16 | 2010-12-20 | 479170 | 0.000 | 1035103
1862 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | STATEWIDE | 04 | 1035104 | THE STATE OF CONNECTICUT WILL COMPLETE THE PAVEMENT RESURFACING OF HOLLOW TREE RIDGE ROAD, WEST AVE. AND LEROY AVE.,TOWN OF DARIEN | Pavement Improvement | 2010-07-21 | 2010-07-21 | 2010-08-19 | 2010-08-13 | 633799 | 0.000 | 1035104
1863 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1036001 | THIS PROJECT INCLUDES THE MILLING AND OVERLAY OF ELIZABETH STREET, TOWN OF DERBY | Pavement Improvement | 2010-07-28 | 2010-07-28 | 2010-09-10 | 2010-09-10 | 480798.31 | 0.000 | 1036001
1864 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 02 | 1037102 | THE STATE OF CONNECTICUT WILL COMPLETE A CONSTRUCTION PROJECT INVOLVING THE PAVING OF MAIDEN LANE, DURHAM | Pavement Improvement | 2010-10-11 | 2010-10-11 | 2010-11-28 | 2010-11-02 | 260993 | 0.610 | 1037102
1865 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 02 | 1040103 | THE STATE OF CONNECTICUT WILLCOMPLETE THE CONSTRUCTION PROJECT THAT INCLUDES THE PAVING OF LAKE SHORE DRIVE, EAST HADDAM | Pavement Improvement | 2010-10-01 | 2010-10-01 | 2010-10-31 | 2010-11-01 | 101219.36 | 1.510 | 1040103
1866 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 02 | 1041104 | THIS PROJECT INCLUDES THE RESURFACING OF HADDAM NECK RD, EAST HAMPTON | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2010-07-22 | 2010-06-10 | 174351.01 | 0.682 | 1041104
1867 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1042118 | PAVEMENT REHABILIATION OF PORTIONS OF MAIN STREET AND SCHOOL ST., TOWN OF EAST HARTFORD | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2010-10-27 | 2010-12-17 | 2047715 | 0.000 | 1042118
1868 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1050106 | Various intersection improvements will be completed at the Black Rock Turnpike and Commerce Drive in Fairfield | Other | 2010-04-19 | 2010-04-19 | 2011-04-19 | 2011-04-16 | 1145418 | 0.000 | 1050106
1869 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1054001 | EAST STREET - CRACK SEALING AND MICROSURFACING - GOSHEN/NORFOLK | Pavement Improvement | 2010-07-16 | 2010-07-19 | 2010-08-29 | 2010-08-29 | 232139.63 | 3.600 | 1054001
1870 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1056112 | PAVEMENT RECONSTRUCTION AND OVERLAY OF FIELD POINT ROAD, DEARFIELD DR, BROOKSIDE DR, WEST ELM ST., RAILROAD AVE, PROSPECT ST AND HORSENECK LN., GREENWICH | Pavement Improvement | 2010-05-06 | 2010-05-09 | 2010-06-23 | 2010-06-17 | 918712 | 2.350 | 1056112
1871 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1059107 | PAVEMENT PRESERVATION OF STEPSTONE HILL ROAD, GUILFORD | Pavement Improvement | 2010-09-01 | 2010-09-01 | 2010-12-01 | 2010-12-13 | 632405 | 0.800 | 1059107
1872 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 1068107 | RECONSTRUCTION OF A PORTION OF LAKE RD., KILLINGLY | Pavement Improvement | 2010-08-10 | 2010-08-23 | 2010-10-15 | 2010-12-22 | 484680 | 0.600 | 1068107
1873 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1073104 | WHITE WOOD ROAD OVERLAY , TOWN OF LITCHFIELD | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2010-10-07 | 2010-09-10 | 140228.52 | 0.000 | 1073104
1874 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1076120 | In the Town of Manchester, a new traffic control signal will be installed at the interesection of Slater Street and the Best Buy driveways to improve safety and traffic flow to and from exisiting stores. | Safety/Traffic Management | 2009-09-08 | 2010-04-01 | 2010-05-15 | 2010-05-15 | 216360.33 | 0.000 | 1076120
1875 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1076124 | In the Town of Manchester, pavement preservation will be conducted along Buckland Hills Road by repaving from Buckland Street eastward to Deming Street. | Pavement Improvement | 2009-11-05 | 2010-04-01 | 2010-06-29 | 2010-07-16 | 2509498 | 0.000 | 1076124
1876 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND |  | 02 | 1077107 | IN THE TOWN OF MANSFIELD, PAVING OF MANSFIELD CITY ROAD WILL BE COMPLETED | Pavement Improvement | 2010-07-07 | 2010-07-07 | 2010-10-13 | 2010-08-31 | 251844.1 | 0.000 | 1077107
1877 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 03 | 1081001 | THIS PAVEMENT PRESERVATION PROJECT WILL INCLUDE THE PAVING OF CEDAR STREET, DERBY AND JACKSON HILL ROAD, MIDDLEFIELD | Pavement Improvement | 2010-08-16 | 2010-08-16 | 2010-08-31 | 2010-08-31 | 54532.53 | 2.000 | 1081001
1878 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 03 | 1082111 | The contractor will complete the paving/resurfacing of Industrial Park Road in the town of Middletown | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2010-12-06 | 2011-05-19 | 1061915 | 0.740 | 1082111
1879 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1084104 | THIS PROJECT INVOLVES STRATEGIC PAVING ALONG CROSS HILL RD AND WILL BE COMPLETED WITHIN THE TOWN OF MONROE | Pavement Improvement | 2010-08-30 | 2010-08-30 | 2010-10-28 | 2010-10-28 | 866554 | 0.000 | 1084104
1880 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1086102 | THIS PROJECT WILL INCLUDE CRACK SEALING AND MRCROSURFACING OF ALAN WHITE ROAD IN THE TOWN OF MORRIS | Pavement Improvement | 2010-07-19 | 2010-07-21 | 2010-09-01 | 2010-09-01 | 89356.65 | 1.760 | 1086102
1881 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1088109 | This project work inlcudes the milling and overlaying of Corbin Avenue, East Street, and Stanley Street in the city of New Britain | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2010-12-15 | 2011-07-22 | 1734651 | 3.350 | 1088109
1882 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1089102 | THIS PROJECT INCLUDES PAVEMENT RESURFACING OF OLD NORWALK ROAD, FARM ROAD, WEST ROAD AND WEED ROAD, IN THE TOWN OF NEW CANAAN | Pavement Improvement | 2010-06-23 | 2010-06-23 | 2010-08-06 | 2010-08-05 | 883900 | 2.810 | 1089102
1883 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 1090103 | In the Town of New Fairfield, the park and ride lot will be repaved for an improved surface. | Pavement Improvement | 2009-10-13 | 2009-10-13 | 2009-10-27 | 2009-10-27 | 217133.91 | 4.250 | 1090103
1884 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1091107 | THIS PROJECT INCLUDES CRACK SEALING AND MICROSURFACING OF WEST HILL ROADIN THE TOWN OF NEW HARTFORD | Pavement Improvement | 2010-08-02 | 2010-08-16 | 2010-10-11 | 2010-09-28 | 99894.66 | 1.120 | 1091107
1885 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1092133 | This project will provide for the reconstruction of Quinnipiac Avenue, including pavement, drainage and sidewalks, from south of Ferry Street to Clifton Street in the City of New Haven. | Pavement Improvement | 2010-04-01 | 2010-04-01 | 2011-11-27 | 2011-10-15 | 6503800 | 0.789 | 1092133
1886 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1092135 | This project consists of the pavement rehabilitation of Congress Street in the City of New Haven | Pavement Improvement | 2010-12-27 | 2010-10-27 | 2011-04-25 | 2011-04-26 | 843700 | 0.000 | 1092135
1887 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1092136 | THIS PROJECT INVOLVES THE RECONSTRUCTION AND REHABILITATION OF QUINNIPIAC AVE., PHASE 2 CITY OF NEW HAVEN | Pavement Improvement | 2010-10-10 | 2010-10-10 | 2011-09-30 | 2011-09-30 | 1874700 | 0.197 | 1092136
1888 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | 1094106 | The project will complete roadway improvements to Montauk Avenue in New London | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2010-09-12 | 2011-01-05 | 807572 | 0.830 | 1094106
1889 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | DANBURY (NY) | 05 | 1095114 | This project includes the completion of milling and paving Boardman Road and Grove Street in the town of New Milford | Pavement Improvement | 2010-06-16 | 2010-06-17 | 2010-09-13 | 2010-09-17 | 1043944 | 1.900 | 1095114
1890 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | STATEWIDE | 05 | 1096103 | This project includes the milling and paving of Castle Hill Road with full depth reclamation and paving of Castle Meadow Road in the town of Newtown | Pavement Improvement | 2010-09-20 | 2010-09-20 | 2010-10-29 | 2010-10-19 | 641962.28 | 0.000 | 1096103
1891 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | MERIDEN-NEW HAVEN | 03 | 1100107 | The existing pavement has exceeded its serviceability and appears to be a very good candidate for pavement preservation improvements. The resurfacing of this roadway will help ensure its serviceability for a minimum of 15 years | Pavement Improvement | 2011-04-01 | 2011-04-01 | 2011-04-30 | 2011-05-31 | 376040 | 0.635 | 1100107
1892 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1102109 | THIS PROJECT INCLUDES THE RESURFACING AND PAVING OF DR. MARTIN LUTHER KING JR. DR. BELDEN HILL RD., BUTLER ST. HARBOR AVE., IN THE CITY OF NORWALK | Pavement Improvement | 2010-06-16 | 2010-06-21 | 2010-09-30 | 2010-08-04 | 1399934 | 0.000 | 1102109
1893 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1102110 | The timely resurfacing of these roadways enhance pavement performance while extending the pavement life in a cost effective manner | Pavement Improvement | 2011-05-18 | 2011-05-31 | 2011-08-28 | 2011-08-05 | 364176 | 1.700 | 1102110
1894 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1107004 | THIS PROJECT INVOLVES THE RESURFACING OF CHRISTIAN ST. IN OXFORD | Pavement Improvement | 2010-09-14 | 2010-09-14 | 2010-10-28 | 2010-10-28 | 182734 | 0.150 | 1107004
1895 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1109103 | THE STATE OF CONNECTICUT WILL PROVIDE FOR THE RECONSTRUCTION AND PAVING OF CAMP ST. IN THE TOWN OF PLAINVILLE | Pavement Widening | 2010-09-07 | 2010-09-07 | 2010-11-07 | 2010-11-05 | 707900 | 0.200 | 1109103
1896 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | HARTFORD | 05 | 1110106 | THE VENDOR WILL MILL AND OVERLAY HARWINTON AVE., ROUTE 6 TO ARMBURSTER RD. IN THE TOWN OF PLYMOUTH | Pavement Improvement | 2010-08-13 | 2010-08-25 | 2010-11-20 | 2010-11-09 | 422011.54 | 0.000 | 1110106
1897 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | HARTFORD | 01 | 1112001 | THE VENDOR WILL COMPLETE THE PAVEMENT PRESERVATION OF BARTLETT ST, COLLINS HILL RD, HIGH ST, ISINGLASS AND JOBS POND ROAD IN PORTLAND | Pavement Improvement | 2010-05-10 | 2010-06-14 | 2010-07-14 | 2010-06-24 | 234163.09 | 8.270 | 1112001
1898 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 03 | 1114107 | THIS ROAD IMPROVEMENT PROJECT WILL INCLUDE THE RESURFACING OF STRAITSVILLE ROAD IN THE TOWN OF PROSPECT | Pavement Improvement | 2010-08-11 | 2010-08-11 | 2010-09-24 | 2010-09-22 | 239774.75 | 0.000 | 1114107
1899 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM | WORCESTER (MA) | 02 | 1115105 | THIS ROAD IMPROVEMENT PROJECT WILL INCLUDE THE PAVEMENT PRESERVATION OF CHURCH STREET IN THE TOWN OF PUTNAM | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-11-17 | 2010-12-13 | 497246 | 0.000 | 1115105
1900 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD |  | 04 | 1116102 | This project will provide improvements along Main Street within the Georgetown Village area. Proposed improvements include sidewalks, crosswalks, ornamental lighting and landscaping. | Transportation Enhancements | 2010-10-12 | 2010-10-18 | 2011-08-08 | 2011-06-16 | 903712 | 0.250 | 1116102
1901 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1117108 | THE VENDOR WILL PERFORM MILLING AND PAVING OF FARMINGVILLE RD AND OLD STAGECOACH RD. IN THE TOWN OF RIDGEFIELD | Pavement Improvement | 2010-09-20 | 2010-09-21 | 2010-12-03 | 2010-12-03 | 716563 | 0.000 | 1117108
1902 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1118003 | In the Town of Rocky Hill, pavement preservation will be conducted along Old Main Street by repaving from Glastonbury Avenue extending 50 feet south of the bridge over Goff Brook | Pavement Improvement | 2009-07-29 | 2009-08-10 | 2009-10-18 | 2009-12-16 | 1229806.93 | 0.000 | 1118003
1903 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1124001 | THIS PAVEMENT PROJECT WILL INCLUDE THE PAVING AND REHABILITATION OF DERBY AVE.IN THE TOWN OF SEYMOUR | Pavement Improvement | 2011-04-01 | 2011-05-01 | 2011-10-27 | 2012-05-18 | 933259 | 0.000 | 1124001
1904 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1126108 | THIS PAVEMENT REHABILITATION PROJECT WILL INCLUDE THE PAVING AND REHABILITATION OF CONSTITUTION BLVD. SOUTH IN THE CITY OF SHELTON | Pavement Improvement | 2010-04-28 | 2010-05-05 | 2010-09-01 | 2010-06-29 | 453730 | 0.000 | 1126108
1905 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1130001 | This project involves the pavement preservation of Main Street in the town of Southbury | Pavement Improvement | 2010-10-12 | 2010-10-12 | 2010-11-25 | 2010-11-25 | 567557 | 2.000 | 1130001
1906 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1131106 | THIS PROJECT INVOLVES THE MILLING AND OVERLAYING OF SOUTH END RD AND MOUNT VERNON RD. IN THE TOWN OF SOUTHINGTON | Pavement Improvement | 2010-08-17 | 2010-08-17 | 2010-11-01 | 2010-12-20 | 819800 | 1.338 | 1131106
1907 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1132104 | In the Town of South Windsor, beginning at the Manchester Town Line and extending north, approximately 4400 feet of Buckland Road will be resurfaced. | Pavement Improvement | 2009-10-02 | 2009-10-02 | 2009-12-30 | 2009-12-03 | 988146.11 | 0.000 | 1132104
1908 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | 1138104 | IN THE TOWN OF STRATFORD THE VENDOR WILL COMPLETE THE REPAVING OF BRUCE AVE. | Pavement Improvement | 2010-09-07 | 2010-09-20 | 2010-11-18 | 2010-11-18 | 331184 | 0.600 | 1138104
1909 | CONNECTICUT | Completed | C200,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | HARTFORD | 05 | 1140001 | Pavement rehabilitaition will be completed on Old Northfield Road in Thomaston | Pavement Improvement | 2010-06-21 | 2010-07-07 | 2010-09-18 | 2010-07-27 | 172797.22 | 0.322 | 1140001
1910 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1143109 | THIS PAVEMENT PROJECT INCLUES THE MILLING AND OVERLAYING OF LITCHFIELD ST., WINTHROP ST. AND WATER ST., IN THE CITY OF TORRINGTON | Pavement Improvement | 2010-06-17 | 2010-08-02 | 2010-09-14 | 2010-10-21 | 976629.06 | 0.000 | 1143109
1911 | CONNECTICUT | Underway | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 05 | 1151117 | THIS PROJECT INCLUDES SIDEWALK IMPROVEMENTS ON COOKE ST IN WATERBURY | Transportation Enhancements | 2010-09-16 | 2010-09-16 | 2012-04-25 |  | 2527074 | 1.800 | 1151117
1912 | CONNECTICUT | Underway | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | WATERBURY | 05 | 1153102 | This project will provide full depth reconstruction for deteriorated pavement structure, much needed drainage upgrades and replacement of Turkey Brook's inadequate culvert crossing | Pavement Improvement | 2011-04-01 | 2011-04-01 | 2012-11-01 |  | 1422917 | 0.500 | 1153102
1913 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD | WATERBURY | 05 | 1153111 | THIS PROJECT INCLUDES THE RESURFACING OF FRENCH STREET, IN THE TOWN OF WATERTOWN | Pavement Improvement | 2010-09-27 | 2010-09-27 | 2010-11-10 | 2010-11-29 | 541375.59 | 0.000 | 1153111
1914 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | MIDDLESEX | MERIDEN-NEW HAVEN | 02 | 1154102 | THE VENDOR WILL COMPLETE THE MILLING AND PAVING OF MCVEIGH ROAD FROM ROUTE 153 TO POND MEADOW ROAD, IN THE TOWN OF WESTBROOK | Pavement Improvement | 2010-07-21 | 2010-07-26 | 2010-09-03 | 2010-08-31 | 518112.5 | 1.040 | 1154102
1915 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1157001 | THE VENDOR WILL COMPLETE THE PAVEMENT PRESERVATION OF OLD HYDE ROAD IN THE TOWN OF WESTON | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-08-03 | 2010-08-03 | 259172.44 | 0.000 | 1157001
1916 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1158001 | THIS PAVEMENT PRESERVATION PROJECT INCLUDES THE PAVING OF CROSS HIGHWAY, LONG LOTS RD., AND NEWTOWN TPKE, IN THE TOWN OF WESTPORT | Pavement Improvement | 2010-03-29 | 2010-03-29 | 2010-05-03 | 2010-05-03 | 736441.67 | 0.000 | 1158001
1917 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 1158002 | Pavement preservation | Pavement Improvement | 2010-10-18 | 2010-10-18 | 2010-12-27 | 2011-04-25 | 1190373 | 5.080 | 1158002
1918 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 1162112 | THIS PROJECT WILL CONSIST OF COMPLETING PAVEMENT OVERLAY ON WETMORE AVE. IN THE TOWN OF WINCHESTER | Pavement Improvement | 2010-08-16 | 2010-09-01 | 2010-10-14 | 2010-10-13 | 370400 | 0.455 | 1162112
1919 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 1163102 | THIS PROJECT WILL INCLUDE THE PAVING OF HIGH ST., VALLEY ST., AND JACKSON ST. IN THE TOWN OF WINDHAM | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2010-08-19 | 2010-08-10 | 445388.88 | 0.850 | 1163102
1920 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | 1164106 | In the Town of Windsor, pavement preservation will be conducted by along Day Hill Road by milling and paving from Blue Hills Avenue to Great Pond Drive. This will include new drainage and curbing. | Pavement Improvement | 2009-09-28 | 2009-10-01 | 2009-11-29 | 2009-11-19 | 780050.74 | 0.000 | 1164106
1921 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 05 | 1166001 | This project will include the paving of Long Swamp Road in the town of Wolcott | Pavement Improvement | 2010-08-17 | 2010-08-23 | 2010-12-15 | 2010-12-07 | 585300 | 0.250 | 1166001
1922 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | 3953001 | IN THE TOWNS OF EAST LYME,MONTVILLE AND WATERFORD THIS PROJECT WILL INCLUDE THE PAVEMENT PRESERVATION OF I-395. | Pavement Improvement | 2010-05-14 | 2010-05-14 | 2010-07-28 | 2010-06-25 | 3441330.92 | 5.600 | 3953001
1923 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | DANBURY (NY) | 05 | 6034007 | This project consists of the replacement of the Backus Avenue Bridge in the city of Danbury | Bridge Improvement | 2010-03-29 | 2010-03-29 | 2010-10-27 | 2010-10-27 | 1055328 | 0.049 | 6034007
1924 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | WATERBURY | 05 | 6080004 | The purpose of this project is to replace the Longmeadow Road Bridge in the Town of Middlebury | Bridge Replacement | 2010-04-01 | 2010-04-01 | 2011-05-26 | 2011-05-26 | 289700 | 0.000 | 6080004
1925 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON |  | 02 | 6085002 | THE PURPOSE OF THIS PROJECT IS TO REPAIR THE BRIDGE ON OLD COLCHESTER RD.IN THE TOWN OF MONTVILLE | Bridge Improvement | 2010-04-05 | 2010-04-05 | 2011-05-19 | 2010-12-06 | 1067200 | 0.094 | 6085002
1926 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW HAVEN | WATERBURY | 03 | 6087005 | This project consists of the rehabilitation of the Rubber Avenue Bridge, number 03713, town of Naugatuck | Bridge Improvement | 2010-04-12 | 2010-06-16 | 2010-11-07 | 2010-11-04 | 1168891 | 0.000 | 6087005
1927 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 6099012 | THE PURPOSE OF THIS PROJECT IS INSTALL A MEMBRANE AND OVERLAY BRIDGE #5207 ON LOWER RD IN NORTH CANAAN | Bridge Improvement | 2010-07-06 | 2010-07-06 | 2010-09-03 | 2010-12-03 | 406367.71 | 0.040 | 6099012
1928 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 05 | 6119002 | THIS PROJECT CONSISTS OF PAINTING JUDDS BRIDGE IN THE TOWN OF ROXBURY | Other | 2010-07-21 | 2010-07-21 | 2010-11-27 | 2010-12-24 | 233104 | 0.030 | 6119002
1929 | CONNECTICUT | Completed | C250 | Highway Infrastructure Investment Grant | CONNECTICUT | WINDHAM |  | 02 | 6123001 | THE VENDOR WILL REPAIR THE STATION ROAD BRIDGE (BR #4768) IN THE TOWN OF SCOTLAND | Bridge Improvement | 2010-07-19 | 2010-07-19 | 2010-10-23 | 2011-05-11 | 349571 | 0.030 | 6123001
1930 | CONNECTICUT | Completed | C240 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 04 | 6158006 | This project will provide rehabilitation of th existing Hales Road bridge over Metro North RR in the Town of Westport. Construction will include complete replacement of the bridge superstructure and new bridge abutments. | Bridge Improvement | 2009-09-28 | 2009-09-28 | 2011-04-28 | 2011-09-07 | 4192758 | 0.000 | 6158006
1931 | CONNECTICUT | Underway | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 02 | H011002 | This project will include the completing the reconstruction of Town Farms Road and Post Office Road in Enfield | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2011-10-27 |  | 3746137 | 1.200 | H011002
1932 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | H018011 | This project will include streetscape improvements for Mystic within the town of Stonington | Transportation Enhancements | 2010-05-17 | 2010-05-17 | 2010-11-12 | 2010-11-12 | 544172 | 0.340 | H018011
1933 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | H018012 | This project will provide for streetscape type improvements along Route 1 in the Town of Stonington from the Mystic Bridge easterly to Willow Street. The work includes new curbing, sidewalks, decortive lighting, and other streetscape amenities | Transportation Enhancements | 2009-09-14 | 2009-09-14 | 2010-05-01 | 2010-05-01 | 788777 | 0.110 | H018012
1934 | CONNECTICUT | Underway | C220,C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | H018013 | Mystic Streetscape, Town of Groton | Transportation Enhancements | 2010-09-17 | 2010-09-20 | 2012-06-30 |  | 3561200 | 0.300 | H018013
1935 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | H135002 | In the Town of Southington, the Linear Park multi-use trail will be constructed along an abandoned rail line from West Main Street to the Cheshire Town line. | Transportation Enhancements | 2010-01-14 | 2010-01-20 | 2011-04-01 | 2011-05-06 | 1902990 | 1.900 | H135002
1936 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | PEDS102 | THE PROJECT WILL INCLUDE EXTENDING THE CHARTER OAK GREENWAY 4,600 FEET THROUGH THE HIGHLAND PARK SECTION OF MANCHESTER | Transportation Enhancements | 2010-08-02 | 2010-08-02 | 2011-05-29 | 2011-11-30 | 643000 | 0.870 | PEDS102
1937 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | LITCHFIELD |  | 01 | PEDS124 | In the City of Torrington, the Still River Greenway multi-use path will be extended 1.8 miles from Princewoods Road north to Harris Drive. | Transportation Enhancements | 2009-07-15 | 2009-07-15 | 2009-11-11 | 2009-12-08 | 905096.42 | 0.000 | PEDS124
1938 | CONNECTICUT | Completed | C220,C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | PEDS125 | THE PROJECT WILL INCLUDE CONNECTING THE BURLINGTON TRAIL TO THE FARMINGTON TRAIL IN THE TOWNS OF BURLINGTON AND FARMINGTON | Transportation Enhancements | 2010-07-06 | 2010-08-04 | 2010-10-03 | 2010-11-15 | 354605 | 0.000 | PEDS125
1939 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | STATEWIDE | 01 | PEDS126 | WITHIN THE CITY OF HARTFFORD IMPROVEMENTS WILL BE COMPLETED ON PARK ST. FROM LAUREL ST. TO I-84/ POPE PARK HIGHWAY #4 | Transportation Enhancements | 2010-09-27 | 2010-09-27 | 2012-01-05 | 2011-10-14 | 3597000 | 0.230 | PEDS126
1940 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND |  | 02 | PEDS127 | THIS PROJECT WILL CONSIST OF COMPLETING THE BIRCH ROAD BIKEWAY IN THE TOWN OF MANSFIELD | Transportation Enhancements | 2010-09-13 | 2010-09-13 | 2011-07-13 | 2011-07-06 | 251601 | 0.000 | PEDS127
1941 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | PEDS128 | THIS PROJECT INCLUDES THE COMPLETION OF PHASE 3 OF THE FARMINGTON RIVER TRAIL IN THE TOWN OF CANTON | Transportation Enhancements | 2010-07-15 | 2010-07-15 | 2011-07-15 | 2011-07-15 | 1171200 | 1.850 | PEDS128
1942 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | PEDS129 | THE PROJECT TO BE COMPLETED WILL BE THE HOUSATONIC RIVER GREENWAY BIKE/PEDESTRIAN TRAIL IN THE TOWN OF STRATFORD | Transportation Enhancements | 2010-06-29 | 2010-06-29 | 2010-09-27 | 2010-09-27 | 501236 | 0.189 | PEDS129
1943 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | HARTFORD | HARTFORD | 01 | PEDS130 | THE PROJECT WILL INCLUDE THE REPAIR AND IMPROVEMENT OF SECTIONS OF THE I-84 /I-384 MULTI USE TRAIL IN EAST HARFORD AND MANCHESTER | Transportation Enhancements | 2010-05-21 | 2010-05-21 | 2010-08-26 | 2010-09-09 | 683991.88 | 2.600 | PEDS130
1944 | CONNECTICUT | Completed | C230 | Highway Infrastructure Investment Grant | CONNECTICUT | FAIRFIELD | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 03 | PEDS133 | THIS PROJECT WILL INCLUDE THE COMPLETION OF PHASE 2 OF THE STREETSCAPE IMPROVEMENTS ALONG BARNUM AVENUE IN STRATFORD | Transportation Enhancements | 2010-09-08 | 2010-10-21 | 2011-08-17 | 2011-08-16 | 1575550 | 3.860 | PEDS133
1945 | CONNECTICUT | Completed | C200 | Highway Infrastructure Investment Grant | CONNECTICUT | NEW LONDON | NEW LONDON-NORWICH | 02 | PEDS134 | THIS PROJECT WILL CONSIST OF COMPLETING THE BRIDGE STREET STREETSCAPE IN GROTON | Other | 2010-08-09 | 2010-08-09 | 2011-02-15 | 2011-03-09 | 1730000 | 0.310 | PEDS134
1946 | CONNECTICUT | Completed | C220 | Highway Infrastructure Investment Grant | CONNECTICUT | TOLLAND | HARTFORD | 02 | TCSP014 | THIS PROJECT WILL INCLUDE THE CONSTRUCTION OF THE HISTORIC TALCOTTVILLE STREETSCAPE IN THE TOWN OF VERNON | Transportation Enhancements | 2010-06-28 | 2010-06-28 | 2010-09-26 | 2011-06-08 | 136118 | 0.000 | TCSP014
1947 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009009 | This project will remove and replace hot-mix surface, hot mix patching, and profile improvements at one location in New Castle County. | Pavement Improvement | 2009-05-20 | 2009-05-20 | 2010-04-30 | 2010-03-24 | 4135646.6 | 4.940 | 2009009
1948 | DELAWARE | Completed | C250 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2009010 | This project will remove and replace hot-mix surface, hot-mix patching, and curb ramp upgrades at two locations in Sussex County. | Pavement Improvement | 2009-06-03 | 2009-06-08 | 2009-10-01 | 2009-08-07 | 866353.32 | 3.519 | 2009010
1949 | DELAWARE | Completed | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009011 | This project replaces the concrete median barrier on I-95 between SR 7 interchange and SR 72 overpass. | Pavement Improvement | 2009-08-13 | 2009-08-13 | 2010-01-01 | 2009-11-30 | 1643904.12 | 4.890 | 2009011
1950 | DELAWARE | Completed | C200,C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX, KENT |  |  | 2009012 | This project will improve the long-term condition of the roadway by paving and rehabilitating at various locations | Pavement Improvement | 2009-04-24 | 2009-04-24 | 2010-06-01 | 2010-11-18 | 6106411.3 | 1.000 | 2009012
1951 | DELAWARE | Completed | C250,C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2009013 | This project will involve full depth reclamation and hot-mix overlay | Pavement Improvement | 2010-05-10 | 2010-05-17 | 2009-12-01 | 2010-09-08 | 2106382.1 | 7.590 | 2009013
1952 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE |  |  | 2009014 | This project will improve the long-term condition of the roadway by milling, hot-mix patching, and overlaying at 2 locations in New Castle County. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-11-01 | 2009-10-07 | 1076873.59 | 2.630 | 2009014
1953 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009015 | This project will improve the long-term condition of the roadway by milling, hot-mix patching and overlaying at 4 locations in Wilmington. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2010-08-01 | 2010-09-30 | 1992237.69 | 1.000 | 2009015
1954 | DELAWARE | Completed | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009016 | This project will improve the long-term condition of the roadway by milling, patching and overlayin at 3 locations in New Castle County. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-10-01 | 2009-08-26 | 1201490.69 | 1.000 | 2009016
1955 | DELAWARE | Completed | C220 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2009017 | This project will construct a permanent berth for the historic Lightship Overfalls, listed in the National Register of Historic Places. | Transportation Enhancements | 2010-03-09 | 2010-03-15 | 2010-06-15 | 2010-05-31 | 400000 | 0.060 | 2009017
1956 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009018 | This project involves the rehabilitation of interstate bridges 1-800, 1-831, 1-802, 1-809, 1-811, 1-815, 1-819N, 1-826N and 1-826S. This work includes: replacing expansion joints, joint seals, compress | Bridge Improvement | 2009-05-04 | 2009-05-04 | 2010-04-10 | 2011-02-24 | 2750725 | 1.000 | 2009018
1957 | DELAWARE | Completed | C220,C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2009019 | This project involves the Boardwalk restoration - approximately 52,795 square foot section from the Henlopen Hotel to Rehoboth Avenue and the 24,300 square foot section from Laurel Street to Prospect Street. | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2010-06-01 | 2010-06-17 | 5247665.86 | 0.050 | 2009019
1958 | DELAWARE | Completed | C250,C200,C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | STATEWIDE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009020 | This project involves various intersections with different scope of works, variously involving new signal installations, reconstruction of aging infrastructure, pedestrian signal enhancements, upgrade of curb ramps to current standards. | Other | 2009-04-21 | 2009-04-21 | 2009-08-01 | 2010-09-13 | 1469928.47 | 1.000 | 2009020
1959 | DELAWARE | Completed | C220,C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009021 | This project will complete an over 4 mile loop recreational trail and will be a segment in an overall cross-county greenway trail system. | Transportation Enhancements | 2009-05-18 | 2009-05-18 | 2010-12-08 | 2010-11-01 | 632285.9 | 0.050 | 2009021
1960 | DELAWARE | Completed | C220,C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009022 | This project in the New Castle Industrial Track Rail Trail covers 4.75 miles of corridor running north from Delaware Street in New Castle, across Boulden Boulevard, then crossing the the Christina River where it terminates. | Transportation Enhancements | 2009-08-31 | 2009-08-31 | 2009-12-01 | 2010-09-15 | 835845.39 | 0.510 | 2009022
1961 | DELAWARE | Completed | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009023 | This project includes miscellaneous work at Bridge 1-701, 703, 703A, 704 and 705. Work includes the replacement of bearings, expansion joints, painting of structural steel, repair of spalled concrete. | Other | 2009-05-04 | 2009-05-04 | 2010-12-01 | 2010-01-31 | 157794.14 | 1.000 | 2009023
1962 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009024 | This project involves the rehabilwork at Bridge 1-792 and 829. Work includes the replacement of bearings, expansion joints, painting of structural steel, repair of spalled concrete and replacement of deck and substructure. | Other | 2009-04-28 | 2009-04-28 | 2010-12-01 | 2010-01-31 | 176065.92 | 1.000 | 2009024
1963 | DELAWARE | Underway | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009025 | This project involves the rehabilitation of interstate bridges 1-804, 1-805, 1-810, 1-811 and 1-812. This work includes cleaning and painting the steel beams,diaphragms and bearings. | Bridge Improvement | 2009-05-08 | 2009-05-08 | 2010-04-01 |  | 2228010.7 | 1.000 | 2009025
1964 | DELAWARE | Completed | C220,C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009026 | This streetscape improvement project is along Old Lancaster Pike from Valley Road to Errickson Drive. Improvements include; new sidewalks, upgrades to curb ramps, drainage modifications, decrotive crosswalks, and landscape. | Transportation Enhancements | 2009-05-07 | 2009-05-07 | 2010-12-01 | 2010-09-24 | 2830690.94 | 0.380 | 2009026
1965 | DELAWARE | Completed | C220,C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009027 | This project on Route 52 / Old Kennett Pike would replace current temporary traffic calming features with permanent ones. This work would improve safety for motorists and pedestrians. | Transportation Enhancements | 2009-09-29 | 2009-09-29 | 2010-09-04 | 2011-05-03 | 1843264.22 | 0.650 | 2009027
1966 | DELAWARE | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009028 | This project will replace non-standard guardrail, guardrail components and end treatments as required for all state-maintained roads in New Castle County. | Safety/Traffic Management | 2009-10-21 | 2009-10-21 | 2012-08-30 |  | 505798.38 | 1.000 | 2009028
1967 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | STATEWIDE |  |  | 2009029 | This project will repaint existing pavement markings statewide. | Safety/Traffic Management | 2009-08-31 | 2009-08-31 | 2010-06-01 | 2009-11-17 | 1251043.23 | 107.410 | 2009029
1968 | DELAWARE | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2009030 | This project involves the rehabilitation of interstate bridges 1-676, 1- 717, 1-719, 1-720, 1-738, 1-739 and 1-740. Work includes the replacement of bearings, expansion seal and/or joints, painting of | Bridge Improvement | 2009-05-04 | 2009-05-04 | 2010-12-26 |  | 6132527.53 | 1.000 | 2009030
1969 | DELAWARE | Completed | C200,C240 | Highway Infrastructure Investment Grant | DELAWARE | KENT | DOVER |  | 2009031 | This project will build the first phase of a DART Dover Transit Center on five acres on Water Street between Queen and West Streets. | Other | 2009-12-08 | 2009-12-08 | 2011-03-08 | 2010-12-15 | 3421196.39 | 0.110 | 2009031
1970 | DELAWARE | Completed | C200,C240 | Highway Infrastructure Investment Grant | DELAWARE | KENT | DOVER |  | 2009033 | This project will rotomill, patch, and 2" hot-mox overlay at 3 locations, including miscellaneous concrete work (curb ramps) in Kent County. | Pavement Improvement | 2009-09-29 | 2009-11-09 | 2010-06-01 | 2010-10-01 | 958513.45 | 1.000 | 2009033
1971 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE |  |  | 2010012 | "Project includes improvements to 3 intersections in the Newark area. The improvements include extension of left turn lanes to assist traffic during the I-95 Newark toll plaza project, and other incidental construction." | Safety/Traffic Management | 2010-03-23 | 2010-04-26 | 2010-09-30 | 2010-07-16 | 1012480.14 | 0.010 | 2010012
1972 | DELAWARE | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2010014 | This project entails patching and an overlay of the roadway surface for; the on and off ramps for the SR273/SR 1 interchange, the US 40/SR 1 interchange, and SR 273 from Harmony Road to Chapman Road. | Pavement Improvement | 2011-01-14 | 2011-05-27 | 2011-11-02 |  | 1368452.7 | 4.090 | 2010014
1973 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010024 | This project involves applying a 2" hot mix overlay on SR 24 from Drane Road to Bayfarm/Autumn Road. | Pavement Improvement | 2010-09-15 | 2010-09-27 | 2010-11-01 | 2010-11-22 | 996807.44 | 3.200 | 2010024
1974 | DELAWARE | Underway | C250,C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010025 | This project entails milling, a 2 inch full-width hot-mix overlay, drainage repairs, and curb ramp retrofits on SR 1 from the Maryland line to the northern town limits of Fenwick. | Pavement Improvement | 2011-08-14 | 2011-09-19 | 2011-11-18 |  | 1392277.11 | 2.380 | 2010025
1975 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010026 | This project entails P.C.C. patching and a 2 inch full-width hot-mix overlay on US 113 northbound and southbound from Oak Drive to just south of Wood Branch Road. | Pavement Improvement | 2011-03-01 | 2011-03-01 | 2011-06-30 | 2011-06-29 | 2287200.83 | 9.330 | 2010026
1976 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010027 | This project entails P.C.C. patching and a 2 inch full-width hot-mix overlay on SR 9/US 404 (Lewes-Georgetown Highway) from Gravel Hill Road to Sweetbriar Road. | Pavement Improvement | 2011-03-03 | 2011-03-21 | 2011-05-10 | 2011-05-31 | 1803557.6 | 5.320 | 2010027
1977 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | 2010038 | This project entails Patching, mill and overlay the roadway surface, retrofit curb ramps, extend two left turn lanes at the Foulk Road/Shipley Road intersection, and construct a sidewalk along the wes | Other | 2010-11-01 | 2010-11-01 | 2011-07-31 | 2011-09-19 | 523875.28 | 3.590 | 2010038
1978 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | 2010043 | This project entails removing areas of corrosion, the existing coating system, and then applying a new coating system to all of the structural steel on the following bridges; Rehoboth Blvd over Mispil | Bridge Improvement | 2011-04-15 | 2011-04-25 | 2011-10-29 | 2011-12-16 | 897048 | 0.086 | 2010043
1979 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | KENT | DOVER |  | K007007 | This project involves installation of a second northbound US 13 left turn lane onto westbound SR 8. The southbound US 13 turn lane will be extended 150 feet to the north to allow additional storage f | Pavement Improvement | 2010-10-14 | 2010-10-22 | 2010-11-10 | 2010-11-14 | 474159.81 | 0.213 | K007007
1980 | DELAWARE | Underway | C200,C240 | Highway Infrastructure Investment Grant | DELAWARE | KENT |  |  | K195003 | This project entails realigning approximately 1500' of Wyoming Mill Road (located in Dover | New Construction | 2010-11-09 | 2011-01-05 | 2011-12-04 |  | 2255891.28 | 0.860 | K195003
1981 | DELAWARE | Completed | C200 | Highway Infrastructure Investment Grant | DELAWARE | KENT | DOVER |  | K356011 | This project improves saftey by channelizing the median at the intersection of SR 10 and Sorghum Mill Road to accommodate eastbound and westbound SR 10 left-turns. | Safety/Traffic Management | 2009-06-17 | 2009-07-20 | 2009-11-01 | 2009-08-24 | 218880.81 | 0.150 | K356011
1982 | DELAWARE | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | N003010 | This project involves a 4" Cold In-Place Recycling with 2" overlay on SR 273 from Chapman Road to SR 7. | Pavement Improvement | 2010-08-19 | 2010-08-19 | 2010-12-28 |  | 2019318.05 | 1.490 | N003010
1983 | DELAWARE | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | N011027 | This project entails a 2 inch profile milling, hot-mix patching, 2 inch warm-mix asphalt Type C overlay on Kirkwood Highway from SR 7 to Prices Corner just west of SR 141 interchange. | Pavement Improvement | 2011-02-03 | 2011-02-03 | 2011-10-06 |  | 2114110.86 | 1.720 | N011027
1984 | DELAWARE | Underway | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | WILMINGTON (NJ-MD-PA) |  | N024001 | This project will elevate the roadway, improve shoulders, underground utilities, pave and restripe the hot mix pavement on Market Street from "A" Street to just north of the Market/Walnut St split. | Pavement Improvement | 2009-04-22 | 2009-04-22 | 2012-07-17 |  | 8701733.85 | 1.000 | N024001
1985 | DELAWARE | Underway | C240,C230 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | N056038 | This project entails constructing two highway speed EZ Pass Lanes in both the Northbound and Southbound directions of the Newark Toll Plaza located on I-95 near the DE/MD State Line. | New Construction | 2009-04-17 | 2009-04-17 | 2011-12-01 |  | 39471221.84 | 2.600 | N056038
1986 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD |  | N059036 | This project will mill and resurface southbound I-95 from the Wilmington Viaduct to just south of the SR 141 interchange. | Pavement Improvement | 2009-04-24 | 2009-04-24 | 2009-12-01 | 2009-11-09 | 2633869.21 | 2.830 | N059036
1987 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE | WILMINGTON (NJ-MD-PA) |  | N397001 | "This project will replace the existing corrugated metal pipes with a double cell precast concrete box culvert. It also will reconstruct the roadway approaches, place guardrail as required, and place riprap in the stream as required for scour protection" | Bridge Replacement | 2010-04-06 | 2010-04-07 | 2010-11-01 | 2010-11-22 | 868157.55 | 0.023 | N397001
1988 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | NEW CASTLE |  |  | N438002 | This project will expand the park & ride on along SR 299, west of SR 1. | Other | 2009-06-05 | 2009-06-05 | 2010-05-30 | 2010-04-30 | 932672.49 | 0.290 | N438002
1989 | DELAWARE | Completed | C250 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | S020003 | This project will involve hot-mix patching and 3 1/2" overlay at one location in Sussex County. | Pavement Improvement | 2009-07-08 | 2009-07-20 | 2009-10-01 | 2009-09-16 | 1523946.62 | 5.090 | S020003
1990 | DELAWARE | Completed | C240 | Highway Infrastructure Investment Grant | DELAWARE | SUSSEX |  |  | S584003 | This project improves the railroad crossing at SR 404 and Newton Road by installing automatic gates, updating the cantilever lights and controller, and replace pre-cast concrete surface. | Other | 2009-06-08 | 2009-10-19 | 2010-04-01 | 2009-10-30 | 362333.6 | 1.000 | S584003
1991 | DISTRICT OF COLUMBIA | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 1108027 | REPLACEMENT OF THE NEW YORK AVENUE BRIDGE WHICH CROSSES OVER METRO, AMTRACK AND CSX RAILROAD TRACKS | Bridge Improvement | 2009-09-22 |  |  |  | 25823004.7 | 0.100 | 1108027
1992 | DISTRICT OF COLUMBIA | Completed | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 1121013 | Rehabilitation of Sherman Avenue NW from Florida Avenue to Park Road. Reconfiguration of roadway, widening sidewalk, relocation and upgrading traffic signals, upgrading street lights, construction of | Pavement Improvement | 2010-08-04 |  |  | 2012-09-18 | 1787911.49 | 0.900 | 1121013
1993 | DISTRICT OF COLUMBIA | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 1300015 | CONSTRUCTION WILL INCLUDE SIDEWALK, CURB AND GUTTER, PAVING T, NEW STREETLIGHTS, TRAFFIC SIGNALS, SAFETY IMPROVEMENTS AND LANDSCAPING ALONG PENNSYLVANIA AVENUE FROM THE SOUSA BRIDGE TO SOUTHERN AVENUE | Pavement Improvement | 2009-11-30 |  |  |  | 19553626.19 | 1.400 | 1300015
1994 | DISTRICT OF COLUMBIA | Completed | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3000049 | THIS PROJECT IS FOR UPGRADES TO TRAFFIC SIGNALS, STREETLIGHTS, CURB, GUTTER, SIDEWALK WIDENING, AND LANDSCAPING, ALONG WITH AN IMPROVEMENT TO THE STORM SEWERS. THESE IMPORVEMENTS WILL BE COMPLETED ON ROADWAYS WITHIN THE MOUNT VERNON BUSINESS DISCTRICT | Pavement Widening | 2009-10-26 |  |  | 2010-09-20 | 3372714.95 | 0.250 | 3000049
1995 | DISTRICT OF COLUMBIA | Underway | C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3000050 | THIS PROJECT IS MAINLY TO REPAVE THE ROADWAY; ALSO MINOR IMPROVEMENTS WILL BE DONE ALONG VARIOUS ROADWAYS WITHIN THE HISTORIC DUPONT CIRCLE BUSINESS DISTRICT | Pavement Improvement | 2009-10-26 |  |  |  | 5378847.72 | 0.480 | 3000050
1996 | DISTRICT OF COLUMBIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3105006 | RECONSTRUCT/RESURFACE ROADWAY, SIDEWALK, CURB, GUTTER AND WHEELCHAIR RAMPS. UPGRADE STREETLIGHT AND TRAFFIC SIGNALS. REPLACE WATER MAIN AND LANDSCAPING .ALONG 18TH STREET, FROM FLORIDA AVENUE TO MASSACHUSETTS AVENUE | Pavement Improvement | 2009-11-15 |  |  | 2010-12-07 | 5826764.7 | 0.530 | 3105006
1997 | DISTRICT OF COLUMBIA | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3207003 | REPLACEMENT OF THE EASTERN AVENUE BRIDGE THAT CROSSES OVER KENNILWORTH AVENUE | Bridge Improvement | 2009-11-29 |  |  |  | 4744844.75 | 0.100 | 3207003
1998 | DISTRICT OF COLUMBIA | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3207004 | REPLACEMENT OF THE EASTERN AVENUE BRIDGE THAT CROSSES OVER KENNILWORTH AVENUE | Pavement Improvement | 2009-11-13 |  |  |  | 6237520.22 | 0.100 | 3207004
1999 | DISTRICT OF COLUMBIA | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 3208006 | Construct improvements to sidewalks, curbs, gutters, streets, tree boxes, replace street trees and install other streetscape elements. Construct facilities to improve reliability and safety of transi | Pavement Improvement | 2010-11-15 |  |  |  | 9201213 |  | 3208006
2000 | DISTRICT OF COLUMBIA | Underway | C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 4116001 | RECONSTRUCT THE ROADWAY AND ADD NEW SIDEWALKS ALONG WESTERN AVENUE FROM CHESTNUT STREET TO OREGON AVENUE IN NORTHWEST DC | Pavement Improvement | 2010-01-26 |  |  |  | 2701773.96 | 0.520 | 4116001
2001 | DISTRICT OF COLUMBIA | Underway | C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888323 | THE WORK WILL INCLUDE UPGRADING OF STREETLIGHTS, WHEELCHAIR RAMPS, PLANTING TREES AS WELL AS REPAIRING SIDEWALKS AND GUTTERS AND AND REPAVING THE ROADWAY. THIS WORK WILL OCCUR ALONG 25 BLOCKS OF THE DOWNTOWN BUSINESS DISTRICT | Safety/Traffic Management | 2009-08-10 | 2009-09-17 |  |  | 6611873.89 | 1.360 | 8888323
2002 | DISTRICT OF COLUMBIA | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888327 | INSTALL BATTERY BACKUP POWER SUPPLY FOR CRITICAL TRAFFIC LIGHTS THROUGHOUT THE CITY TO PROVIDE UP TO 8 HOURS OF POWER. | Safety/Traffic Management | 2010-01-01 |  |  |  | 1476449.09 |  | 8888327
2003 | DISTRICT OF COLUMBIA | Underway | C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888328 | REPAVING OF SECTIONS OF THE INTERSTATE HIGHWAY IN DC | Pavement Improvement | 2009-04-24 | 2009-04-24 |  |  | 999999.84 | 14.140 | 8888328
2004 | DISTRICT OF COLUMBIA | Underway | C240 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888329 | IMPROVE STREETLIGHTS ALONG THE DALECARLIA PARKWAY AND BLADENSBURG ROAD | Safety/Traffic Management | 2009-04-24 | 2009-04-24 |  |  | 4845172.75 | 12.640 | 8888329
2005 | DISTRICT OF COLUMBIA | Completed | C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888332 | IMPROVE PEDESTRIAN FACILITIES THAT SERVICE NEIGHBORHOOD SCHOOLS | Transportation Enhancements | 2010-01-07 | 2010-01-07 |  | 2012-01-07 | 2464384.23 |  | 8888332
2006 | DISTRICT OF COLUMBIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888339 | The work consists of resurfacing roadways along various locations, citywide. In areas of existing asphalt concrete surface, the work will consists of pavement milling to a depth of one (1) to two (2) | Pavement Improvement | 2010-06-02 |  |  | 2011-06-02 | 13294564.91 |  | 8888339
2007 | DISTRICT OF COLUMBIA | Completed | C220,C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888341 | The work consists of installation of new sidewalk or replacement of defective sidewalk along various locations citywide. The sidewalk may be concrete or brick and will be installed per DC Standards. | Transportation Enhancements | 2010-06-02 |  |  | 2011-06-02 | 4713546.87 |  | 8888341
2008 | DISTRICT OF COLUMBIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | DISTRICT OF COLUMBIA | DISTRICT OF COLUMBIA | WASHINGTON (MD-VA) |  | 8888362 | Project implements citywide vehicle detection stations. Determine number of vehicles passing through various permanent count stations, occupancy, speed and classification of vehicles. | Safety/Traffic Management | 2010-11-15 |  |  | 2010-05-15 | 2812250.34 |  | 8888362
2009 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | Multiple | 1301034 | RESURFACING SR-710/SW WARFIELD F ROM W OF ML KING BLVD. TO W OF VAN BUREN AVE (0001.072 MILES) IN MARTIN COUNTY, FLORIDA. | Pavement Improvement | 2011-02-17 | 2011-03-04 | 2011-09-12 | 2011-11-11 | 174619 | 1.072 | 1301034
2010 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA001 | "This Okaloosa County project will improve safety at the existing intersection of State Road 85 South and State Road 123, near the Northwest Florida Regional airport, by providing a flyover ramp for m | Pavement Widening | 2000-12-05 | 2009-07-01 | 2019-06-03 |  | 29689016 | 1.241 | ARRA001
2011 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | SANTA ROSA | PENSACOLA | 01 | ARRA002 | This Santa Rosa County project will widen the existing two-lane roadway to four with bike lanes and sidewalks to improve safety and relieve congestion. | Pavement Widening | 2001-04-02 | 2009-07-20 | 2019-05-25 |  | 6916839 | 0.984 | ARRA002
2012 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA003 | "This Leon County project will add lanes to Capital Circle SE, relieve congestion and improve safety along the roadway." | Pavement Widening | 2010-10-22 | 2010-10-22 | 2012-12-31 |  | 8300000 | 1.130 | ARRA003
2013 | FLORIDA | Underway | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | BAY | PANAMA CITY | 02 | ARRA004 | Bay County is building a new bridge over Grand Lagoon for vehicles and pedestrians to improve safety and relieve congestion on Thomas Drive in Panama City Beach. | Bridge Improvement | 2009-09-28 | 2009-09-28 | 2011-03-22 |  | 12802328 | 0.822 | ARRA004
2014 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA005 | Barrier walls and culverts will be installed on this Leon County safety improvement project to allow wildlife to pass under the road and improve driver safety along this roadway. | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-31 | 2010-10-05 | 3085365 | 1.074 | ARRA005
2015 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA006 | "Franklin County will construct approximately 2,500 feet of five-foot wide sidewalk along Bluff Road in Apalachicola to improve pedestrian safety." | Transportation Enhancements | 2009-11-16 | 2009-11-16 | 2010-02-13 | 2010-01-29 | 116145 | 0.737 | ARRA006
2016 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 17 | ARRA007 | The City of Hallandale Beach will improve pedestrian safety by installing brick pavers and stamped concrete crosswalks at various locations on West Hallandale Beach Boulevard. | Transportation Enhancements | 2010-02-03 | 2010-04-01 | 2010-06-30 | 2010-09-17 | 234530 | 1.937 | ARRA007
2017 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA010 | FDOT will build a new high level bridge over the south fork of the St. Lucie River and the Okeechobee Waterway between Palm City and Stuart to ease congestion and provide faster evacuation from the coastal area in Martin County. | New Bridge Construction | 2009-08-19 | 2009-08-19 | 2019-08-18 |  | 72255919 | 1.420 | ARRA010
2018 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 22 | ARRA011 | "The City of Wilton Manors will replace deteriorating pavement, build new sidewalks and bike lanes and plant landscaping to enhance N.E. 15th Avenue." | Transportation Enhancements | 2010-03-16 | 2010-03-16 | 2010-06-16 | 2010-06-16 | 185852 | 0.010 | ARRA011
2019 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 23 | ARRA012 | "The City of Fort Lauderdale will improve pedestrian safety by building paved parking, adding sidewalks, installing pedestrian lighting and enhancing landscaping at various locations on NW 7 Street, N | Transportation Enhancements | 2010-06-15 | 2010-06-30 | 2010-10-31 | 2011-05-24 | 500000 | 1.154 | ARRA012
2020 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 19 | ARRA013 | The City of Deerfield Beach will improve access to the west entrance of the Deerfield Beach train station that serves Tri-Rail (commuter) and Amtrak customers by building a sidewalk and a pedestrian pathway along Goolsby Boulevard and the access road. | Transportation Enhancements | 2009-12-07 | 2010-01-04 | 2010-08-31 | 2010-08-19 | 359764 |  | ARRA013
2021 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 21 | ARRA014 | "The City of Pembroke Pines will build new sidewalks at several locations along Pembroke Road and 196th Avenue to provide pedestrian access between major roads, subdivisions , schools, shops and to provide areas to encourage walking." | Transportation Enhancements | 2009-12-07 | 2009-12-14 | 2010-04-30 | 2010-05-18 | 519214 | 0.986 | ARRA014
2022 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | Multiple | ARRA015 | The City of Ft. Pierce will enhance bicyclist and pedestrian safety by improving three miles of bike lanes and sidewalk on Oleander Boulevard/Sunrise Boulevard from Virginia Avenue to Ohio Avenue. | Transportation Enhancements | 2009-12-31 | 2009-12-31 | 2012-12-31 | 2012-07-26 | 643831 | 0.485 | ARRA015
2023 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | WEST PALM BEACH | 22 | ARRA016 | Palm Beach County will provide access to bicyclists and pedestrians through the Cypress Creek Natural Area beginning at Indiantown Road West at Jupiter Farms Road by building 2.1 miles of shared-use path. | Transportation Enhancements | 2010-11-29 | 2010-11-29 | 2011-04-15 | 2011-07-28 | 452190 | 2.017 | ARRA016
2024 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 22 | ARRA017 | The City of Lighthouse Point will build sidewalks and install pedestrian lighting to improve safety on N.E. 44 Street. | Transportation Enhancements | 2010-01-18 | 2010-01-26 | 2010-07-14 | 2010-07-14 | 160000 | 0.212 | ARRA017
2025 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA018 | Indian River County will plant additional landscaping to enhance the median of 58th Avenue for 3.05 miles from Oslo Road to 16th Avenue in southern Indian River County. | Transportation Enhancements | 2010-01-04 | 2010-01-06 | 2010-04-16 | 2010-04-22 | 237265 | 3.050 | ARRA018
2026 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA019 | Martin County will provide access for bicyclists and pedestrians by building a one mile-long shared-use path from S.E. Grafton Avenue to Seabranch Preserve State Park south of Stuart. | Transportation Enhancements | 2010-04-26 | 2010-04-26 | 2010-07-27 | 2010-07-27 | 172369 | 0.931 | ARRA019
2027 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 16 | ARRA020 | The City of Port St. Lucie will add 0.6 miles of sidewalk to improve pedestrian safety on the east side of California Boulevard from Heatherwood Boulevard to Fairway Isles. | Transportation Enhancements | 2010-01-21 | 2010-02-01 | 2010-03-31 | 2010-04-01 | 48189 | 0.611 | ARRA020
2028 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | WEST PALM BEACH | Multiple | ARRA021 | Palm Beach County will provide safe access for bicyclists and pedestrians on the eastern levee of the South Florida Water Management drainage canal in the City of Palm Beach Gardens and unincorporated | Transportation Enhancements | 2010-03-01 | 2010-03-08 | 2010-11-03 | 2011-03-19 | 750000 |  | ARRA021
2029 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | Multiple | ARRA022 | "FDOT will improve safety for motorists by replacing the 56-year old structurally deficient Juanita Street Bridge over Taylor Creek in Fort Pierce, as well as improve bicyclist and pedestrian safety by adding wide sidewalks." | Bridge Improvement | 2010-04-05 | 2010-04-13 | 2011-02-15 | 2011-03-22 | 1150834 | 0.102 | ARRA022
2030 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 16 | ARRA023 | The City of Port St. Lucie will improve a 2.3-mile segment of Westmoreland by rebuilding the road using a new type of pavement that will wear longer and reduce the need for repairs. | Pavement Improvement | 2009-12-31 | 2010-01-01 | 2019-12-30 | 2010-06-28 | 832874 | 2.396 | ARRA023
2031 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 23 | ARRA024 | "The City of Fort Pierce will rebuild 13th Street from Orange Avenue to Avenue D using a new type of pavement that will last longer and reduce the need for repairs, reduce flooding by installing a new | Pavement Improvement | 2010-07-12 | 2010-08-02 | 2011-03-08 | 2010-11-23 | 879370 | 0.300 | ARRA024
2032 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA025 | The Village of Wellington will repave and add street lights to improve 5.4 miles of Forest Hill Boulevard. | Pavement Improvement | 2010-01-12 | 2010-03-19 | 2020-01-11 | 2011-06-30 | 5192268 | 7.254 | ARRA025
2033 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16 | ARRA026 | The Village of Royal Palm Beach will improve two miles of Royal Palm Beach Boulevard by adding sidewalks for pedestrians and resurfacing the road using a new type of pavement that will last longer and reduce the need for repairs. | Pavement Improvement | 2010-04-05 | 2010-04-12 | 2011-12-31 |  | 2578922 | 4.051 | ARRA026
2034 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 22 | ARRA027 | The City of Riviera Beach will replace deteriorating pavement on 3.3 miles of A1A from U.S. 1 at Blue Heron Boulevard north to Burnt Bridge on Singer Island. | Pavement Improvement | 2010-01-12 | 2010-07-19 | 2020-01-11 |  | 4067290 | 6.688 | ARRA027
2035 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 16 | ARRA028 | FDOT will restore vehicle traffic by replacing the Tequesta Drive Bridge over the North Fork of the Loxahatchee River. The bridge was recently closed due to its unsafe condition. | Pavement Improvement | 2009-10-28 | 2010-01-05 | 2012-03-26 | 2010-12-28 | 2638577 | 0.230 | ARRA028
2036 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 23 | ARRA029 | The City of Boynton Beach will improve 0.6 miles of Seacrest Boulevard by adding street lights and resurfacing the road using a new type of pavement that will last longer and reduce the need for repairs. | Pavement Improvement | 2010-01-12 | 2010-06-08 | 2020-01-11 | 2011-10-31 | 1057476 | 0.671 | ARRA029
2037 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 19 | ARRA030 | Palm Beach County will improve 14.7 miles of Military Trail between Clint Moore Road in Boca Raton and Lake Worth Road in Lake Worth by resurfacing the existing pavement and improve pedestrian safety by installing sidewalks and guardrails. | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2011-06-13 | 2011-11-10 | 6500785 | 14.664 | ARRA030
2038 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 22 | ARRA031 | "FDOT will build a new four-lane bridge between Hillsboro Boulevard/ State Road 810 in Deerfield Beach (Broward County) and S.W. 18th Street in Boca Raton (Palm Beach County), crossing over local stre | Pavement Widening | 2009-10-29 | 2010-03-11 | 2019-10-28 |  | 2487314 | 0.468 | ARRA031
2039 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 23 | ARRA032 | "FDOT will replace aging underground sewer and water lines, add sidewalks, curbs, drainage and resurface .316 miles of Southeast 3rd Street in Belle Glade." | Pavement Improvement | 2010-01-12 | 2010-08-02 | 2011-02-19 | 2011-05-23 | 960943 | 0.316 | ARRA032
2040 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA033 | Martin County will add a southbound right-turn lane at the intersection of State Road 707 and N.W. Wright Boulevard to ease congestion just north of the Roosevelt Bridge over the St. Lucie River in Stuart. | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2010-07-22 | 2010-07-30 | 132834 | 0.122 | ARRA033
2041 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA034 | Martin County is replacing the deteriorating pavement on one mile of Baker Road from U.S. 1 to Savannah Road in northeastern Martin County. | Pavement Improvement | 2009-10-05 | 2009-10-12 | 2009-12-01 | 2009-12-01 | 250000 | 1.298 | ARRA034
2042 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 23 | ARRA035 | Martin County will improve nine miles of County Road 609 from State Road 710 north of Indiantown north to County Road 714 by replacing aging pavement. | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-03-01 | 2010-03-01 | 2100000 | 9.000 | ARRA035
2043 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA036 | FDOT will resurface County Road 507 from the Fellsmere city limits north 3.09 miles to the Indian River/Brevard County line to extend the life of the road. | Pavement Improvement | 2009-11-16 | 2009-11-16 | 2012-04-11 | 2010-05-02 | 651190 | 6.362 | ARRA036
2044 | FLORIDA | Underway | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | PASCO |  | 05 | ARRA037 | "In Pasco County, this project widens 2.8 miles of U.S. 41 from the existing two lanes to a four-lane divided road with medians and turn lanes to reduce congestion." | Pavement Widening | 2009-07-01 | 2009-07-11 | 2012-07-01 |  | 14745320 | 2.841 | ARRA037
2045 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA038 | "In the City of Alachua, in northern Alachua County, a sidewalk and bike lane will be built along Northwest County Road 235A from U.S. 441 to Santa Fe High School which will improve the safety of students walking and biking to the school." | Transportation Enhancements | 2009-06-15 | 2009-06-15 | 2019-06-15 | 2010-08-12 | 67962 | 1.000 | ARRA038
2046 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA039 | "In Alachua County, a concrete sidewalk will be built along the north side of Southwest Eighth Avenue between Southwest 75th Street (Tower Road) and end of the road which will provide a safer place for pedestrians to walk." | Transportation Enhancements | 2009-06-15 | 2010-01-25 | 2012-02-10 |  | 90926 | 1.000 | ARRA039
2047 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | LEVY |  | 05 | ARRA040 | "In Levy County, bike lanes will be built along both sides of State Road 320 from Manatee Springs State Park to U.S. 19 to improve recreational options for campers at the state park as well as provide | Transportation Enhancements | 2009-06-15 | 2009-11-15 | 2012-03-08 |  | 1645308 | 5.784 | ARRA040
2048 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | 03 | ARRA041 | "In Bradford County, a 12-foot wide, 4-mile long multi-use trail will be built along the old abandoned railroad line along State Road 100 from the Clay County line to County Road 315 to provide recreation opportunities." | Transportation Enhancements | 2009-06-15 | 2009-06-15 | 2019-06-15 | 2011-05-03 | 1128587 | 4.366 | ARRA041
2049 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA | GAINESVILLE | 06 | ARRA042 | "In Gainesville, an off-road bicycle path will be built on the abandoned railroad property alongside West Sixth Street from Southeast Second Avenue to Northwest 16th Avenue for recreation and those who ride their bicycles to work and school." | Transportation Enhancements | 2009-08-04 | 2010-03-15 | 2010-09-15 |  | 427718 | 1.540 | ARRA042
2050 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA | GAINESVILLE | 03 | ARRA043 | "In Gainesville, Northeast Eighth Avenue will be repaved between North Main Street (State Road 329) and Northeast Boulevard to improve the road surface." | Pavement Improvement | 2009-08-04 | 2009-12-14 | 2010-02-02 |  | 110761 | 0.311 | ARRA043
2051 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA045 | "To promote economic development in the western area of Alachua County, a southbound turn lane will be added to U.S. 41 just south of Newberry onto Southwest 30th Avenue." | Safety/Traffic Management | 2009-06-15 | 2010-01-26 | 2012-02-10 |  | 437093 | 0.001 | ARRA045
2052 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA | GAINESVILLE | 03 | ARRA046 | "In Gainesville, North Main Street (County Road 329) will be reconstructed from four to two lanes with a center turn between Northwest Eighth and 16th avenues which will increase safety. It will also | Pavement Improvement | 2009-06-15 | 2009-10-23 | 2012-02-10 |  | 943082 | 1.681 | ARRA046
2053 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE |  | Multiple | ARRA047 | "Cash toll collections will be replaced with all-electronic tolling on a 21-mile segment of Florida?s Turnpike located between State Road 836 in Miami and County Line Road in Miramar.? The project wil | Pavement Improvement | 2009-09-30 | 2009-09-30 | 2011-10-03 | 2012-01-26 | 21980000 | 12.000 | ARRA047
2054 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA048 | Southwest 122nd Street in Alachua County will be resurfaced and a five-foot paved shoulder added south of Archer Road (State Road 24) to Southwest 89th Avenue which will improve safety. | Pavement Improvement | 2009-06-15 | 2010-01-18 | 2012-02-10 |  | 402911 | 0.343 | ARRA048
2055 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | BAKER |  | 04 | ARRA049 | "In Glen St. Mary, County Road 125 will be resurfaced from U.S. 90 to Glen Haven Lane and the culverts will be upgraded to make the roadway a safer route to drive." | Pavement Improvement | 2009-06-15 | 2009-10-15 | 2012-02-10 |  | 589224 | 1.556 | ARRA049
2056 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | BRADFORD |  | 06 | ARRA050 | "In Bradford County, Northwest County Road 229 between State Road 16 and Northwest 55th Avenue will be repaved to improve the road surface." | Pavement Improvement | 2009-06-15 | 2009-12-14 | 2012-02-10 |  | 726641 | 2.000 | ARRA050
2057 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | CLAY |  | 06 | ARRA051 | "In St. Johns County, County Road 214 will be resurfaced between State Road 100 and County Road 315C to improve the ride." | Pavement Improvement | 2009-06-15 | 2009-12-03 | 2012-03-17 |  | 1496913 | 6.584 | ARRA051
2058 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | COLUMBIA |  | 04 | ARRA052 | "In western Columbia County, County Road 250 (Lake Jeffery Road) will be widened from 10 to 12-foot lanes and resurfaced from Interstate 75 to the Suwannee County line to improve the road surface." | Pavement Improvement | 2009-06-15 | 2009-10-12 | 2012-02-10 |  | 1125609 | 2.900 | ARRA052
2059 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | COLUMBIA |  | 04 | ARRA053 | "In Lake City, County Road 129 (Northwest Lake Jeffery Road) will be resurfaced between U.S. 90 and the CSX Railroad and a crosswalk added at Parkview Baptist Church to provide additional safety on a busy and much traveled local roadway." | Pavement Improvement | 2009-06-15 | 2009-11-06 | 2012-02-10 |  | 391522 | 0.664 | ARRA053
2060 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | DIXIE |  | 02 | ARRA054 | "In Cross City, the intersection of U.S. 19 (State Road 55) and County Road 351A will be improved by widening the intersection to allow log trucks and larger vehicles to safely turn. The road also wil | Safety/Traffic Management | 2009-06-15 | 2009-12-05 | 2012-02-10 |  | 411954 | 0.100 | ARRA054
2061 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | MADISON |  | 04 | ARRA055 | "In Madison County, County Road 53 between Interstate 10 and Southeast Roger Sink Road will be resurfaced to improve the ride." | Pavement Improvement | 2009-06-15 | 2009-08-19 | 2012-02-10 |  | 855844 | 1.899 | ARRA055
2062 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | 03 | ARRA056 | St. Johns Avenue will be resurfaced between State Road 19 and Palm Avenue which will improve the roadway for traffic headed toward downtown Palatka. | Pavement Improvement | 2009-08-04 | 2009-10-23 | 2010-01-26 |  | 256881 | 1.176 | ARRA056
2063 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | Multiple | ARRA057 | Moseley Avenue in Palatka will be resurfaced from U.S. 17 to State Road 100 and the sidewalks will be repaired and made handicap-accessible to provide a safer ride for motorists and a safer way for pedestrians to walk along the roadway. | Pavement Improvement | 2009-12-15 | 2010-04-05 | 2010-07-05 |  | 309219 | 1.610 | ARRA057
2064 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | Multiple | ARRA058 | "In Pomona Park in southern Putnam County, a new concrete sidewalk will be built between U.S. 17 and Cisco Road to provide a safer path for pedestrians." | Transportation Enhancements | 2009-08-04 | 2009-10-05 | 2009-10-20 |  | 133948 | 3.835 | ARRA058
2065 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | 07 | ARRA059 | "In Putnam County, two culverts will be replaced on Silver Lake Drive over Devall Branch and Two Mile Creek with new concrete culverts to improve the drainage in the area." | Pavement Improvement | 2009-08-04 | 2009-10-05 | 2010-07-02 |  | 454020 | 3.440 | ARRA059
2066 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | Multiple | ARRA060 | "In western Putnam County, a concrete sidewalk and asphalt bike path will be built along a section of County Road 315 to improve safety for pedestrians and bicyclists." | Transportation Enhancements | 2009-08-04 | 2009-10-05 | 2010-02-02 |  | 328154 | 2.082 | ARRA060
2067 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | SUWANNEE |  | 02 | ARRA061 | "A two mile section of County Road 252 in eastern Suwannee County, between the Columbia County line and County Road 137, will be widened from 10 to 12-foot lanes and repaved to improve the road surface." | Pavement Improvement | 2009-06-15 | 2009-12-11 | 2012-02-10 |  | 878565 | 1.915 | ARRA061
2068 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS |  | 07 | ARRA062 | "In St. Johns County, West King Street (County Road 214) between County Road 13 and 13A will have several culverts or pipes replaced and extended to help with drainage issues." | Pavement Improvement | 2009-11-23 | 2009-06-15 | 2019-06-15 | 2011-09-02 | 299684 | 3.946 | ARRA062
2069 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS |  | 07 | ARRA063 | "In St. Johns County, West King Street (County 214) will be widened to improve safety and the road resurfaced between County 13 and 13A to improve the ride." | Pavement Improvement | 2009-11-23 | 2009-06-15 | 2019-06-15 | 2011-11-10 | 659246 | 7.891 | ARRA063
2070 | FLORIDA | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | GILCHRIST |  | 06 | ARRA064 | "In Gilchrist County, County Road 341 will be repaved between State Road 26 and the Levy County line to improve the road surface." | Pavement Improvement | 2009-06-15 | 2009-09-03 | 2012-02-10 |  | 262290 | 1.482 | ARRA064
2071 | FLORIDA | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | HAMILTON |  | 04 | ARRA065 | "In Hamilton County, County Road 135 between White Springs and Southeast 177th Court will be repaved to improve the road surface.." | Pavement Improvement | 2009-06-15 | 2009-09-17 | 2012-02-10 |  | 791978 | 2.900 | ARRA065
2072 | FLORIDA | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | LAFAYETTE |  | 02 | ARRA066 | "In Lafayette County, County Road 354 from U.S. 27 to County Road 361 will be repaved to improve the road surface." | Pavement Improvement | 2009-06-15 | 2009-09-18 | 2012-02-10 |  | 499567 | 2.707 | ARRA066
2073 | FLORIDA | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | LEVY |  | 05 | ARRA067 | "In Levy County, County Road 40 will be repaved between Park Street in Inglis and the Marion County line to improve the road surface and make it safer." | Pavement Improvement | 2009-06-15 | 2009-11-23 | 2012-03-08 |  | 806971 | 7.413 | ARRA067
2074 | FLORIDA | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU |  | 04 | ARRA068 | "In Nassau County, County Road 2 will be resurfaced between County Road 121 and the Georgia line and the Agricultural Inspection Station ramps will be repaved to improve safety for motorists." | Pavement Improvement | 2009-06-15 | 2009-10-09 | 2012-02-10 |  | 337858 | 1.381 | ARRA068
2075 | FLORIDA | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | PUTNAM |  | Multiple | ARRA069 | "In Crescent City in southern Putnam County, a new concrete sidewalk will be built along East Grand Rondo from Central Street to County Road 308 to provide a safer route for pedestrians." | Transportation Enhancements | 2009-08-04 | 2009-10-13 | 2009-11-30 |  | 89817 | 0.100 | ARRA069
2076 | FLORIDA | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | TAYLOR |  | 02 | ARRA070 | "In Taylor County, County Road 14 will be resurfaced between U.S. 221 in Shady Grove and the Madison County line to provide a safer road." | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-02-10 |  | 964360 | 3.063 | ARRA070
2077 | FLORIDA | Underway | C250 | Highway Infrastructure Investment Grant | FLORIDA | UNION |  | 04 | ARRA071 | County Road 231 in Union County will be resurfaced between the Department of Corrections Reception and Medical Center and the Bradford County line to improve the ride. | Pavement Improvement | 2009-06-15 | 2009-08-07 | 2012-02-10 |  | 458012 | 1.009 | ARRA071
2078 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 06 | ARRA072 | "In Clay County, Peoria Road (County Road 224A) will be widened to provide a center turn lane from College Drive (County Road 224) to Moody Road to improve traffic flow. An intersection improvement wi | Safety/Traffic Management | 2009-06-15 | 2009-09-09 | 2012-03-17 |  | 796791 | 0.241 | ARRA072
2079 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 03 | ARRA073 | "In Orange Park, an additional right turn lane will be added to Kingsley Avenue at U.S. 17 to increase the amount of traffic that can turn onto U.S. 17." | Safety/Traffic Management | 2009-06-15 | 2009-11-25 | 2012-03-17 |  | 388058 | 0.001 | ARRA073
2080 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 06 | ARRA074 | Four lanes on Knight Boxx Road (County Road 220B) in Orange Park in Clay County will be resurfaced from Blanding Boulevard (State Road 21) to County Road 220 to provide a safer ride. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-03-17 |  | 476968 | 1.206 | ARRA074
2081 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA075 | "In Jacksonville, for Alta Drive and New Berlin Road, the existing pavement will be resurfaced and paved shoulders added to improve the road surface between Zoo Parkway (State Road 105) and State Road 9A." | Pavement Improvement | 2009-08-20 | 2009-06-15 | 2015-05-13 | 2011-10-10 | 3663856 | 2.012 | ARRA075
2082 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA076 | Ninth Street in Jacksonville Beach will be improved by repairing the existing drainage system and resurfacing between Osceola Avenue and First Street. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2019-06-15 |  | 4196113 | 1.500 | ARRA076
2083 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA077 | "In Fernandina Beach, North 14th Street will be resurfaced between Atlantic Avenue and Pogy Place. The bridge railing will be replaced at Egans Creek Bridge to make the crossing safer for motorists, pedestrians and bicyclists." | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-04-10 |  | 488363 | 1.760 | ARRA077
2084 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA078 | North Eighth Street in Fernandina Beach between Dade Street and the Port of Fernandina will be repaved to improve the road surface. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-04-10 |  | 64136 | 0.464 | ARRA078
2085 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA079 | "In St. Augustine, West King Street or County Road 214 will be resurfaced between County Road 13 and Palmer Avenue to provide a safer road." | Pavement Improvement | 2009-11-23 | 2009-06-15 | 2019-06-15 | 2011-10-03 | 1401829 | 14.979 | ARRA079
2086 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA080 | "To improve capacity and safety at the Interstate 95/State Road 207 interchange in St. Johns County, the northbound and southbound ramps will be widened and a turn lane will be added for westbound traffic on State Road 207 getting onto northbound I-95." | Safety/Traffic Management | 2009-06-15 | 2009-09-21 | 2012-02-10 |  | 589377 | 0.001 | ARRA080
2087 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA081 | "In St. Augustine, concrete sidewalks will be provided along Del Monte, Varella and Durbin Creek Boulevard to increase safety for pedestrians." | Transportation Enhancements | 2009-08-20 | 2009-06-15 | 2010-06-19 |  | 386268 | 5.968 | ARRA081
2088 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA082 | "North of St. Augustine, a new traffic signal system along County Road 210 and Racetrack Road between U.S. 1 and County Road 16A will improve traffic flow along county roads." | Safety/Traffic Management | 2009-08-20 | 2009-11-16 | 2010-04-15 |  | 271115 | 16.160 | ARRA082
2089 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA083 | "In Citrus County, a new multi-use path is being built along U.S. 19 in Crystal River between NW 19th Street and W. State Park Street to provide an area for both bicyclists and pedestrians to travel safely along U.S. 19." | Transportation Enhancements | 2009-09-04 | 2009-09-14 | 2009-11-30 | 2009-11-30 | 170000 | 0.477 | ARRA083
2090 | FLORIDA | Completed | C250,C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA084 | "In Citrus County, this project repaves 2.4 miles of Fort Island Trail from North Palm Springs Terrace to U.S. 19/Suncoast Boulevard to improve the road surface." | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2010-03-13 | 2010-03-10 | 313348 | 1.461 | ARRA084
2091 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA085 | "In Citrus County, this project repaves 1.5 miles of Ozello Trail from U.S. 19 to Winterset Avenue to improve the road surface." | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-02-27 | 2010-02-06 | 172060 | 1.455 | ARRA085
2092 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA086 | "In Citrus County, to enhance the ride ability of the roadway, this project resurfaces 2.7 miles of Croft Ave. from State Road 44 to north of Harley Street." | Pavement Improvement | 2009-11-09 | 2009-11-11 | 2010-02-08 | 2010-02-06 | 367829 | 2.726 | ARRA086
2093 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA087 | "In Citrus County, this project repaves one mile of Turner Camp Road from Ella Avenue to Twin Lakes Drive to improve the road surface." | Pavement Improvement | 2009-11-12 | 2009-11-18 | 2010-02-09 | 2010-02-11 | 140757 | 1.530 | ARRA087
2094 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA088 | "In Citrus County, this project repaves six miles of Cardinal Street from U.S. 19 to County Road 491 (Lecanto Highway) to improve the road surface." | Pavement Improvement | 2009-12-14 | 2010-01-18 | 2010-07-09 | 2010-06-25 | 709410 | 6.151 | ARRA088
2095 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA089 | "In Citrus County, this project resurfaces 2.5 miles of County Road 491 from State Road 44 to County Road 486 due to the poor condition of the road." | Pavement Improvement | 2009-11-22 | 2009-11-22 | 2010-02-19 | 2010-02-16 | 478855 | 2.515 | ARRA089
2096 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA090 | FDOT will improve 2.69 miles of Barber Street in Sebastian by repaving the road and installing a new drainage system. | Pavement Improvement | 2009-11-16 | 2009-11-16 | 2012-04-11 | 2011-02-04 | 1806890 | 2.686 | ARRA090
2097 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA091 | "In Citrus County, due to the poor condition of the road, this project resurfaces 6.8 miles of County Road 491 from Pine Ridge Boulevard to State Road 200." | Pavement Improvement | 2010-01-04 | 2010-01-13 | 2010-04-03 | 2010-03-19 | 777534 | 7.018 | ARRA091
2098 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA093 | "In Citrus County, this project repairs approximately 200 feet of the Withlapopka Causeway shoulders to prevent further erosion along the canal." | Pavement Improvement | 2010-03-29 | 2010-04-05 | 2010-10-24 | 2010-10-18 | 594025 | 0.216 | ARRA093
2099 | FLORIDA | Completed | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA094 | "In Citrus County, this project repaves 5.6 miles of County Road 480 (Stagecoach Road) from County Road 491 (Lecanto Highway) to County Road 581 (Pleasant Grove Road) to improve the road surface." | Pavement Improvement | 2009-11-09 | 2009-11-10 | 2010-03-06 | 2010-02-20 | 992735 | 5.722 | ARRA094
2100 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA095 | "In Citrus County, this project adds a new traffic signal and a right turn lane on State Road 44 at the Citrus County Landfill to ease access and minimize backups at the entrance to the landfill." | Pavement Improvement | 2009-09-15 | 2010-01-11 | 2010-07-25 | 2010-06-08 | 548534 | 0.577 | ARRA095
2101 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA096 | "In Citrus County, this project repaves 2.4 miles of Grover Cleveland Boulevard from Tedna Terrace to County Road 491 to improve the road surface." | Pavement Improvement | 2009-12-07 | 2009-12-17 | 2010-03-06 | 2010-03-03 | 246292 | 2.403 | ARRA096
2102 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA097 | "In Citrus County, this project repaves 1.6 miles of Halls River Road from the Halls River Bridge to Fishbowl Drive to improve the road surface." | Pavement Improvement | 2009-11-30 | 2009-12-14 | 2010-02-28 | 2010-02-28 | 115327 | 1.067 | ARRA097
2103 | FLORIDA | Completed | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA099 | "In eastern Hernando County, this project resurfaces 1.8 miles of Cortez Blvd (State Road 50) between U.S. 98 and the railroad tracks to the east to provide a safer ride." | Pavement Improvement | 2009-08-15 | 2009-08-31 | 2009-11-18 | 2009-11-09 | 737444 | 1.844 | ARRA099
2104 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA100 | FDOT will resurface 3.5 miles of 20th Avenue from Oslo Road to State Road 60 in Vero Beach to extend the life of the road. | Pavement Improvement | 2009-12-11 | 2009-12-11 | 2012-04-12 |  | 2276800 | 5.543 | ARRA100
2105 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA101 | "In Hernando County, this project repaves 2.2 miles of Mariner Boulevard from Maderia Street to Augustine Road to improve the road surface." | Pavement Improvement | 2010-01-04 | 2010-01-17 | 2010-04-23 | 2010-04-23 | 780374 | 2.204 | ARRA101
2106 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA102 | "In Hernando County, this project repaves 0.6 miles of Spring Hill Drive from Pinehurst Drive to Deltona Boulevard to improve the road surface." | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2009-12-07 | 2009-11-23 | 277591 | 0.657 | ARRA102
2107 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA103 | "In Hernando County, this project repaves 1.5 miles of Deltona Boulevard from State Road 50 to Northcliffe Boulevard to improve the road surface." | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2009-12-04 | 2009-11-25 | 248011 | 1.489 | ARRA103
2108 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA104 | "In Hernando County, this project repaves 2.5 miles of Deltona Boulevard from Spring Hill Drive to Philatelic Drive to improve the road surface." | Pavement Improvement | 2010-02-14 | 2010-02-14 | 2010-06-04 | 2010-06-04 | 456863 | 2.508 | ARRA104
2109 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA105 | "In Hernando County, this project repaves 2.8 miles of Spring Hill Drive from Mariner Boulevard to Deltona Boulevard to improve the road surface." | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-03-15 | 2010-03-10 | 856722 | 3.038 | ARRA105
2110 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA106 | "In Hernando County, due to the poor condition of the road, this project replaces 2.1 miles of the asphalt surface on Burwell Rd. (County Road 575) and widens the 10-foot lanes to 12-foot lanes from State Road 50 to the Pasco County Line." | Pavement Improvement | 2009-10-22 | 2009-10-22 | 2009-12-11 | 2009-11-20 | 270714 | 2.049 | ARRA106
2111 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA107 | "In Hernando County, due to the poor condition of the road, this project resurfaces 3.8 miles of Citrus Way and widens the 11-foot lanes to 12-foot lanes from Ft. Dade Avenue to south of Centralia Road." | Pavement Improvement | 2010-01-05 | 2010-01-06 | 2010-08-15 | 2010-03-31 | 758923 | 3.826 | ARRA107
2112 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA108 | "In Hernando County, this project repaves 1.4 miles of Yontz Road from U.S. 98 to Howell Avenue to improve the road surface." | Pavement Improvement | 2009-12-15 | 2009-12-15 | 2010-01-14 | 2010-01-21 | 265142 | 1.433 | ARRA108
2113 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA109 | "In Hernando County, this project repaves one mile of North Avenue from Howell Avenue to Ponce de Leon Boulevard to improve the road surface." | Pavement Improvement | 2010-02-28 | 2010-03-01 | 2010-05-28 | 2010-05-28 | 241465 | 0.743 | ARRA109
2114 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA110 | "In Hernando County, 20 miles of the asphalt surface of the Suncoast Trail is being replaced due to the poor condition of the trail." | Transportation Enhancements | 2009-08-31 | 2009-09-21 | 2010-05-21 | 2010-04-12 | 755009 |  | ARRA110
2115 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HILLSBOROUGH | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 11 | ARRA113 | "In Hillsborough County, this project will add new lighting, landscaping and brick sidewalks for safety purposes on 56th Street from Temple Heights Road to east of 98th Avenue." | Transportation Enhancements | 2009-10-19 | 2009-11-23 | 2010-06-11 | 2010-06-08 | 348298 | 0.146 | ARRA113
2116 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PASCO |  | Multiple | ARRA124 | "In Pasco County, this project builds a new three mile, eight-foot wide trail from Congress Street to Starkey Boulevard to accommodate bicyclists and pedestrians." | Transportation Enhancements | 2010-01-27 | 2010-02-08 | 2010-07-22 | 2010-06-07 | 616243 |  | ARRA124
2117 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 09 | ARRA129 | "In Pinellas County, this project converts the existing southbound lane of East Avenue to a trail for pedestrians and bicyclists to travel safely between Drew Street and Turner Street." | Transportation Enhancements | 2009-10-19 | 2009-10-19 | 2010-10-31 | 2010-12-22 | 304407 | 0.001 | ARRA129
2118 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH, FL | Multiple | ARRA134 | This project is the final and largest section of the 12-part Palmetto Expressway (State Road 826) Improvement Program which consists of major construction along a 16-mile corridor. | Pavement Widening | 2009-11-13 | 2009-11-25 | 2019-11-24 |  | 89175975 | 2.979 | ARRA134
2119 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 23 | ARRA135 | "FDOT is widening 4.35 miles of State Road 70 in western St. Lucie County to a four-lane, divided highway and adding shoulders for safety on this major cross-state business and evacuation route." | Pavement Widening | 2009-07-27 | 2009-08-03 | 2019-08-02 |  | 15816857 | 4.356 | ARRA135
2120 | FLORIDA | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 22 | ARRA136 | "FDOT will build a new four-lane bridge between Hillsboro Boulevard/ State Road 810 in Deerfield Beach (Broward County) and S.W. 18th Street in Boca Raton (Palm Beach County), crossing over local stre | Pavement Widening | 2009-10-29 | 2009-10-29 | 2019-10-28 |  | 38349339 | 0.567 | ARRA136
2121 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | GULF |  | 02 | ARRA137 | This pedestrian safety project includes sidewalk and landscape improvements in the City of Port St. Joe in Gulf County. | Transportation Enhancements | 2009-10-23 | 2009-11-02 | 2010-05-01 | 2010-06-28 | 343118 | 0.297 | ARRA137
2122 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA138 | This project will repair the existing sidewalk and construct additional sidewalk near Bonifay Middle School to improve pedestrian safety in Holmes County. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 89020 | 0.239 | ARRA138
2123 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA139 | The City of Chipley will construct approximately 900 feet of five-foot wide sidewalk along State Road 77 to improve pedestrian safety in Washington County. | Transportation Enhancements | 2009-10-06 | 2009-10-06 | 2010-02-03 | 2010-01-21 | 49922 | 0.172 | ARRA139
2124 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA140 | Five-foot wide sidewalks along various streets within the city limits of Midway will be constructed to improve pedestrian safety in Gadsden County. | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2010-03-19 | 448766 | 1.350 | ARRA140
2125 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN | TALLAHASSEE | 02 | ARRA141 | A five-foot wide sidewalk along State Road 267 in the City of Quincy has been constructed to improve pedestrian safety in Gadsden County. | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2009-11-02 | 62002 | 0.272 | ARRA141
2126 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA142 | "Franklin County will construct approximately 1,600 feet of five-foot wide sidewalk along Franklin Boulevard to improve pedestrian safety." | Transportation Enhancements | 2009-11-09 | 2009-11-09 | 2010-02-07 | 2010-03-31 | 53320 | 0.139 | ARRA142
2127 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA143 | Jackson County will construct a five-foot wide sidewalk along Riverforest Road to improve pedestrian safety. | Transportation Enhancements | 2009-10-15 | 2009-10-15 | 2010-02-05 | 2010-03-23 | 42023 | 0.538 | ARRA143
2128 | FLORIDA | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | COLLIER | NAPLES | 14 | ARRA144 | Build a second two-lane bridge next to the existing Jolley Bridge to give drivers a four-lane bridge that connects Marco Island to U.S. 41 and reduces congestion during heavy travel times. | New Bridge Construction | 2002-11-19 | 2009-09-21 | 2019-09-08 |  | 27661293 | 0.783 | ARRA144
2129 | FLORIDA | Underway | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | POLK | LAKELAND | Multiple | ARRA145 | Construct a new two-lane road to provide a direct connection between State Road 33 and the Pace Road Interchange at the Polk Parkway for easy access to the new University of South Florida Polytechnic campus. | New Construction | 2009-12-29 | 2010-01-02 | 2019-12-28 |  | 36848227 | 5.200 | ARRA145
2130 | FLORIDA | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA147 | "Construct Metro Extension (State Road 739), a new six-lane road that connects U.S. 41 and Six Mile Cypress Parkway in Lee County and relieves heavy traffic on U.S. 41. It will also serve as an alternative to Interstate 75." | New Construction | 2009-04-29 | 2009-07-25 | 2050-04-08 |  | 34688828 | 2.772 | ARRA147
2131 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA148 | Widen U.S. 301 in Sarasota from four to six lanes to relieve roadway congestion. Improvements to drainage and sidewalks will also enhance safety in the area. | Pavement Widening | 2009-08-28 | 2009-09-16 | 2019-08-27 |  | 9702114 | 2.007 | ARRA148
2132 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA149 | Install communications devices at 88 intersections throughout Manatee County and connect them to the Manatee Traffic Management Center to improve traffic congestion and emergency response times. | Safety/Traffic Management | 2009-09-30 | 2009-10-13 | 2019-09-29 |  | 6106640 |  | ARRA149
2133 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA151 | "Replace the old Cape Haze Drive bridge over Amberjack Cove Waterway in Charlotte County with a new bridge with wider lanes, shoulders and sidewalks." | Pavement Improvement | 2009-09-09 | 2009-11-02 | 2012-03-11 | 2010-06-08 | 1061656 | 0.241 | ARRA151
2134 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE | PUNTA GORDA | Multiple | ARRA152 | "Construct intersection improvements at State Road 776/Coliseum Boulevard in Charlotte County, including new turn lanes and traffic signals to move traffic more efficiently through this area." | Pavement Improvement | 2009-09-29 | 2009-09-29 | 2012-03-29 | 2010-11-05 | 520761 | 0.207 | ARRA152
2135 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA153 | Add two new right turn lanes on Veterans Boulevard to improve traffic flow at the Murdock Circle intersection in Charlotte County. | Pavement Improvement | 2009-09-29 | 2009-09-29 | 2012-03-29 | 2010-11-05 | 221460 | 0.010 | ARRA153
2136 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA154 | Lengthen the left turn lane on State Road 776 at the Oriole Boulevard intersection to improve traffic movement through the intersection in Charlotte County. | Pavement Improvement | 2009-09-29 | 2009-09-29 | 2012-03-29 | 2010-11-05 | 95460 | 0.172 | ARRA154
2137 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | DE SOTO |  | 13 | ARRA155 | Pave five miles of County Road 760 from County Road 769 to U.S. 17 in Desoto County to improve the road surface. | Pavement Improvement | 2009-09-16 | 2009-10-24 | 2012-03-14 | 2010-06-11 | 1401250 | 3.170 | ARRA155
2138 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | GLADES |  | 16 | ARRA156 | Pave County Road 720 in Glades County from the Hendry County line to five miles west to improve the road surface. | Pavement Improvement | 2009-09-21 | 2009-11-25 | 2012-03-22 | 2010-09-01 | 1899401 | 5.000 | ARRA156
2139 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA157 | Resurface Main Street (County Road 664) in the city of Bowling Green from Doc Coil Road to east of U.S.17 to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2009-09-21 | 2009-10-24 | 2012-03-21 | 2010-05-02 | 693638 | 3.500 | ARRA157
2140 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | HENDRY |  | Multiple | ARRA158 | Pave County Road 832 in Hendry County from State Road 29 to nine miles east to improve the road surface. | Pavement Improvement | 2009-07-22 | 2009-09-15 | 2012-02-24 | 2010-10-29 | 1465027 | 9.000 | ARRA158
2141 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA159 | Resurface Memorial Drive (County Road 17A) in Highlands County from Sebring Parkway to Manatee Drive to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2012-03-23 | 2010-03-26 | 365735 | 2.268 | ARRA159
2142 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA160 | Resurface County Road 621 in Highlands County from U.S. 27 to Crocket Road to improve the surface of this heavily traveled road. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2012-03-23 | 2010-02-19 | 193020 | 0.600 | ARRA160
2143 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA161 | Add sidewalks along West Main Street from Booker T. Washington Avenue to Chester Avenue in the City of Bowling Green to improve safety. | Transportation Enhancements | 2009-09-21 | 2010-01-19 | 2012-03-21 | 2010-02-22 | 73701 |  | ARRA161
2144 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | DE SOTO |  | 13 | ARRA162 | "Construct a sidewalk along Dr. Martin Luther King, Jr. Street from Booker T. Washington Avenue to U.S. 17 to enhance safety for bicyclists and pedestrians." | Transportation Enhancements | 2009-09-16 | 2009-11-22 | 2012-03-14 | 2009-12-23 | 85504 |  | ARRA162
2145 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HENDRY |  | 16 | ARRA163 | Construct a new sidewalk along State Road 29 from the RV park to the post office in the Felda community in Hendry County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 2009-09-09 | 2009-09-09 | 2010-03-28 | 2010-08-04 | 398576 | 2.077 | ARRA163
2146 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | OKEECHOBEE |  | 16 | ARRA164 | "Add sidewalks along Southwest 7th Avenue, Southwest 9th Street and Southwest 11th Avenue in the City of Okeechobee to improve pedestrian safety." | Transportation Enhancements | 2009-09-21 | 2010-02-15 | 2012-03-16 | 2010-04-27 | 164378 |  | ARRA164
2147 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | POLK |  | 12 | ARRA165 | "Design and build a 12-foot wide paved trail between State Road 17 and 4th Street as an extension of the existing Lake Wales Trail, improving the connectivity of walking trails in Polk County." | Transportation Enhancements | 2009-09-10 | 2009-12-07 | 2012-03-16 | 2010-03-05 | 136677 |  | ARRA165
2148 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | POLK |  | 12 | ARRA166 | Build a 12-foot wide paved trail connecting the existing Fort Fraser Trail just south of the University of South Florida/Polk State College to the Circle B Bar Reserve located on S.R. 540 to improve the connectivity of walking trails in Polk County. | Transportation Enhancements | 2009-09-10 | 2009-09-29 | 2012-03-16 | 2010-03-10 | 457967 |  | ARRA166
2149 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE | PUNTA GORDA | 16 | ARRA167 | "Construct a paved pathway from Retta Esplande to Olympia Avenue in Punta Gorda to connect parks, schools, and the riverfront and give walkers and bicyclists a recreational route for exercise." | Transportation Enhancements | 2010-02-01 | 2010-02-08 | 2010-06-01 | 2010-10-07 | 417951 |  | ARRA167
2150 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | COLLIER | NAPLES | 25 | ARRA168 | "Construct a paved pathway along Bald Eagle Drive on Marco Island to connect the town center, residential areas, and schools and give walkers and bicyclists a recreational route for exercise." | Transportation Enhancements | 2009-08-19 | 2009-08-24 | 2009-11-22 | 2010-01-04 | 380719 | 1.185 | ARRA168
2151 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA169 | Resurface Kenilworth Boulevard from Lakeview Drive to Persimmon Avenue to improve the surface of this heavily traveled road in Highlands County. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2012-03-23 | 2010-03-26 | 153197 | 0.400 | ARRA169
2152 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA170 | Add landscaping along State Road 789 through the coastal city of Long Boat Key to enhance the roadway features of this beach community. | Transportation Enhancements | 2009-09-30 | 2009-10-22 | 2012-03-26 | 2010-06-30 | 232666 | 4.557 | ARRA170
2153 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA171 | Add landscaping along State Road 789 through the coastal city of Bradenton Beach to enhance the roadway features of this beach community. | Transportation Enhancements | 2009-09-30 | 2009-10-22 | 2012-03-26 | 2010-06-30 | 127040 | 0.902 | ARRA171
2154 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA172 | Resurface County Road 17 (S. Main Street) in the town of Lake Placid from Poinsettia Street to West Interlake Boulevard to improve the surface of this heavily traveled road. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2012-03-23 | 2010-02-19 | 204872 | 0.499 | ARRA172
2155 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA173 | Add sidewalks along Gulf Front Park from Palm Avenue to Willow Avenue in the City of Anna Maria to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-11-09 | 2012-03-26 | 2009-11-30 | 16250 |  | ARRA173
2156 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA174 | Resurface Home Avenue from Sebring Parkway to State Road 17 (North Gate Drive) to improve the surface of this heavily traveled road in Highlands County. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2012-03-23 | 2010-03-26 | 46730 | 0.168 | ARRA174
2157 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA176 | Add sidewalks along North Bay Boulevard from Hibiscus Street to North Shore Drive in the City of Anna Maria to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-11-09 | 2012-03-26 | 2009-12-12 | 42677 |  | ARRA176
2158 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA177 | Add sidewalks along Gulf Drive from Spring Avenue to Pine Avenue in the City of Anna Maria to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-11-09 | 2012-03-26 | 2009-11-30 | 6679 |  | ARRA177
2159 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA178 | Replace a short bridge in Lee County on Cortez Boulevard near Fort Myers High School with a new bridge that has sidewalks. | Pavement Improvement | 2009-10-28 | 2009-12-06 | 2010-01-28 | 2010-03-17 | 242169 | 0.001 | ARRA178
2160 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | 13 | ARRA179 | Add sidewalks along North and South Gulf Drive from 57th Street to 84th Street in the City of Holmes Beach to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-09-29 | 2012-03-26 | 2009-11-11 | 9994 | 1.203 | ARRA179
2161 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA180 | "Construct a new culvert on Carrel Road to replace an older, rough-riding surface." | Pavement Improvement | 2009-11-23 | 2010-01-18 | 2010-03-23 | 2010-03-05 | 94959 | 0.001 | ARRA180
2162 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA181 | Add sidewalks along Holmes Boulevard from 54th Street to 66th Street in the City of Holmes Beach to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-09-28 | 2012-03-26 | 2009-11-05 | 22605 |  | ARRA181
2163 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | 13 | ARRA182 | Add sidewalks along Palm Drive from 66th Street to 85th Street in the City of Holmes Beach to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-09-29 | 2012-03-26 | 2009-11-11 | 10441 |  | ARRA182
2164 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | 13 | ARRA183 | Add sidewalks along 85th Street from Gulf Drive to Marina Drive in the City of Holmes Beach to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-09-29 | 2012-03-26 | 2009-11-11 | 11333 |  | ARRA183
2165 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA184 | Add sidewalks along 21st Avenue from 26th Street West to 27th Street West in Bradenton to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-09-30 | 2012-03-26 | 2009-11-10 | 8532 |  | ARRA184
2166 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA185 | Add sidewalks along 27th Street from 22nd Avenue West to 23rd Avenue West in Bradenton to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-09-30 | 2012-03-26 | 2009-11-10 | 21178 |  | ARRA185
2167 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA186 | Add sidewalks along 23nd Avenue from 26th Street West to 27th Street West in Bradenton to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-09-30 | 2012-03-26 | 2009-11-10 | 7133 |  | ARRA186
2168 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA187 | Add sidewalks along 21st Avenue from 30th Street West to 34th Street West in Bradenton to improve pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-09-30 | 2012-03-26 | 2009-11-10 | 53232 |  | ARRA187
2169 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA189 | Add sidewalks along Thunderbird Road from Lotus Avenue to Red Pine Drive in the City of Sebring to improve pedestrian safety. | Transportation Enhancements | 2009-09-15 | 2010-01-04 | 2012-03-23 | 2010-04-16 | 111538 |  | ARRA189
2170 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA190 | Add paved shoulders that will be designated bike lanes on Buckingham Road from State Road 82 to Neal Road in Lee County to enhance safe riding for cyclists. | Pavement Improvement | 2010-01-14 | 2010-02-16 | 2010-06-14 | 2010-11-04 | 236228 | 1.800 | ARRA190
2171 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA191 | Add a second left turn lane on Daniels Parkway westbound at Bell Tower Boulevard in Lee County to improve traffic flow at the intersection. | Pavement Improvement | 2010-03-01 | 2010-03-10 | 2010-09-27 | 2011-02-09 | 419838 | 0.443 | ARRA191
2172 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA192 | "Add a bicycle lane on Summerlin Road in Lee County at the toll plaza to give walkers, runners, and bicyclists a connection to the Sanibel causeway bridge." | Transportation Enhancements | 2010-02-08 | 2010-02-08 | 2010-12-31 | 2010-11-04 | 319262 |  | ARRA192
2173 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA193 | Add two new right turn lanes on Sunshine Boulevard at Lee Boulevard in Lee County to move traffic more efficiently at the intersection. | Pavement Improvement | 2010-01-14 | 2010-01-20 | 2010-06-13 | 2010-11-04 | 553432 | 0.014 | ARRA193
2174 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA194 | Construct a left turn on Homestead Road South in Lee County at the Milwaukee Boulevard to move traffic more efficiently though the intersection. | Safety/Traffic Management | 2009-09-16 | 2009-09-17 | 2010-01-15 | 2010-01-13 | 70579 | 0.200 | ARRA194
2175 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA195 | Rehabilitate the Crescent Avenue bridge and the North Bay Boulevard bridge in the coastal city of Anna Maria Island to extend the use of the bridges by many years. | Pavement Improvement | 2009-09-22 | 2009-10-13 | 2012-03-12 | 2010-09-10 | 665298 | 0.001 | ARRA195
2176 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA196 | Resurface Pine Avenue in the city of Anna Maria from Gulf Drive to Bay Boulevard to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2009-09-16 | 2009-11-16 | 2012-03-26 | 2010-01-19 | 80948 | 0.504 | ARRA196
2177 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA197 | Resurface Gulf Drive in the city of Anna Maria from Willow Avenue to Pine Avenue to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2009-09-16 | 2009-11-16 | 2012-03-26 | 2010-01-19 | 126368 | 0.276 | ARRA197
2178 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA199 | Add landscaping and sidewalks along State Road 789/Gulf Drive from south of 2nd Street to north of 5th Street to improve the safety and enhance the roadway features of this beach community. | Transportation Enhancements | 2009-09-30 | 2009-10-22 | 2012-03-26 | 2010-04-26 | 315085 | 0.371 | ARRA199
2179 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA200 | Add pedestrian crosswalks to the intersections of East Bay Drive and Gulf Drive in the city of Holmes Beach to improve safety. | Transportation Enhancements | 2009-09-16 | 2009-11-16 | 2012-03-26 | 2009-12-12 | 20220 | 0.002 | ARRA200
2180 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA201 | "Beach Boulevard, (U.S. 90/State Road 212) in Duval County will be widened from four to six lanes for 1? miles between Hodges Boulevard and San Pablo Road in order to complete the six-lane section between Jacksonville and Jacksonville Beach." | Pavement Widening | 2009-06-10 | 2009-06-10 | 2019-06-15 | 2012-05-04 | 15064030 | 2.760 | ARRA201
2181 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | CLAY |  | Multiple | ARRA202 | "In Clay County, a new overpass for Plantation Oaks Boulevard traffic will separate the higher speed and volume of traffic on State Road 23, making it safer and more efficient." | Pavement Widening | 2005-08-03 | 2005-08-03 | 2016-06-16 | 2011-12-14 | 8165927 | 0.100 | ARRA202
2182 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU |  | 04 | ARRA203 | "In Nassau County, State Road A1A (State Road 200) will be widened from two to four lanes for six miles between Griffin and Stratton roads to improve traffic flow within the corridor." | Pavement Widening | 2009-06-16 | 2009-05-22 | 2016-06-16 |  | 29842828 | 7.890 | ARRA203
2183 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA204 | Lengthen two left turn lanes on southbound U.S. 41 in Charlotte County to improve traffic flow at the Midway Boulevard intersection. | Pavement Improvement | 2009-09-30 | 2010-03-24 | 2012-03-29 | 2010-06-17 | 127469 | 0.100 | ARRA204
2184 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CHARLOTTE |  | Multiple | ARRA205 | Add a left turn lane at Murdock Circle westbound at U.S. 41 to improve traffic movement in this area. | Pavement Improvement | 2009-09-30 | 2010-03-24 | 2012-03-29 | 2010-06-17 | 180690 | 0.100 | ARRA205
2185 | FLORIDA | Completed | C220,C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA206 | This project in Flagler County will extend the Lehigh Trail and Bike Path by adding 12-foot wide paths and two bridges which benefits trail users and increases safety. | Transportation Enhancements | 2010-02-05 | 2010-02-15 | 2010-09-22 | 2010-09-01 | 838242 | 2.718 | ARRA206
2186 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA207 | This project in the City of Palm Coast fixes the bridge over Club House Waterway and includes better guardrails. | Bridge Improvement | 2010-02-28 | 2010-02-28 | 2010-08-25 | 2011-01-06 | 741881 | 0.034 | ARRA207
2187 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 08 | ARRA208 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-06 | 2009-11-30 | 2010-03-26 | 2010-04-30 | 294153 | 1.517 | ARRA208
2188 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 06 | ARRA209 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-11 | 2010-01-21 | 2010-04-21 | 2010-04-21 | 182075 | 2.291 | ARRA209
2189 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA210 | RESURFACING NORTH RIVERSIDE DR FROM SAND PINE RD TO US 192 (0002.950 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-02-23 | 2010-03-05 | 2010-06-13 | 2010-08-26 | 225374 | 2.950 | ARRA210
2190 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | Multiple | ARRA211 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-25 | 2010-02-03 | 2010-05-05 | 2010-05-05 | 318511 | 2.773 | ARRA211
2191 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LADY LAKE | 05 | ARRA212 | This repaving project in Lake County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-22 | 2010-02-01 | 2010-06-15 | 2010-06-14 | 1704806 | 8.551 | ARRA212
2192 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA213 | This project replaces a bridge on County Road 305 in Flagler County and includes guardrail improvements. | Pavement Improvement | 2010-02-05 | 2010-04-19 | 2010-10-22 | 2010-10-12 | 804600 | 0.010 | ARRA213
2193 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 08 | ARRA214 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-06 | 2009-11-10 | 2010-03-06 | 2010-01-26 | 46931 | 0.839 | ARRA214
2194 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA215 | This project fixes a drainage pipe at Hall Road in the Town of Malabar in Brevard County. | Safety/Traffic Management | 2010-03-25 | 2010-03-25 | 2010-06-12 | 2010-08-31 | 17045 | 0.225 | ARRA215
2195 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA216 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-10 | 2009-11-16 | 2010-03-13 | 2010-01-26 | 129783 | 0.922 | ARRA216
2196 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA217 | "This project in the City of Melbourne will resurface the road, improve storm water drainage, make turn lanes safer, fix sidewalks and upgrade pedestrian crossings." | Pavement Improvement | 2010-02-16 | 2010-02-22 | 2010-06-22 | 2010-06-11 | 609034 | 1.277 | ARRA217
2197 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA218 | This turn lane project in the City of Ocala will improve safety and traffic flow and reduce traffic congestion at intersections. | Safety/Traffic Management | 2009-12-03 | 2009-12-07 | 2010-10-03 | 2010-09-08 | 1068623 | 1.058 | ARRA218
2198 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA219 | This repaving project in Marion County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-05 | 2009-11-09 | 2010-03-24 | 2010-04-06 | 963223 | 3.363 | ARRA219
2199 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA220 | This project in Brevard County will provide a safer environment for pedestrians with a new asphalt sidewalk on which to walk. | Transportation Enhancements | 2010-03-24 | 2010-03-24 | 2010-04-23 | 2010-04-27 | 41550 | 0.713 | ARRA220
2200 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA221 | This repaving project in the City of Palm Bay will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-13 | 2010-01-15 | 2010-06-13 | 2010-07-07 | 871050 | 1.980 | ARRA221
2201 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA222 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-06 | 2009-11-10 | 2010-03-06 | 2010-01-23 | 97297 | 0.707 | ARRA222
2202 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA223 | This repaving project in Brevard County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-04-28 | 2010-04-27 | 288679 | 0.793 | ARRA223
2203 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA224 | This repaving project in Marion County will improve the road surface and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-11-23 | 2009-12-14 | 2010-07-12 | 2010-10-15 | 4837445 | 10.849 | ARRA224
2204 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA225 | This resurfacing project in the City of Satellite Beach will improve the condition of the existing pavement and upgrade sidewalks and pedestrian crossings. | Pavement Improvement | 2009-12-16 | 2009-12-21 | 2010-03-22 | 2010-03-16 | 115775 | 0.275 | ARRA225
2205 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA226 | This resurfacing project in the City of Titusville will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2009-11-16 | 2009-12-07 | 2010-02-26 | 2010-03-10 | 51251 | 0.285 | ARRA226
2206 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA227 | This resurfacing project in Brevard County will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-05-24 | 2010-08-26 | 301684 | 1.681 | ARRA227
2207 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA228 | This resurfacing project in Brevard County will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2010-02-17 | 2010-02-17 | 2010-05-08 | 2010-08-19 | 333359 | 1.018 | ARRA228
2208 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA229 | This project fixes a drainage pipe at Atz Road in the Town of Malabar in Brevard County. | Safety/Traffic Management | 2010-03-25 | 2010-03-25 | 2010-06-12 | 2010-08-31 | 3445 | 0.230 | ARRA229
2209 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA230 | This project fixes storm water drainage problems on Riverside Drive in Brevard County. | Safety/Traffic Management | 2010-03-31 | 2010-03-31 | 2010-04-30 | 2010-04-27 | 24830 | 0.067 | ARRA230
2210 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA231 | This repaving project in the City of Palm Bay will improve the road surface. | Pavement Improvement | 2009-11-17 | 2009-11-17 | 2010-04-23 | 2010-03-16 | 682420 | 1.251 | ARRA231
2211 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA232 | This resurfacing project in the City of Titusville will improve the condition of the existing pavement as well as provide better guardrails. | Pavement Improvement | 2009-11-16 | 2009-12-07 | 2010-02-26 | 2010-03-10 | 125915 | 0.680 | ARRA232
2212 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA233 | This resurfacing project in Brevard County will improve the condition of the road and upgrade pedestrian crossings. | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-05-28 | 2010-09-14 | 501755 | 1.699 | ARRA233
2213 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA234 | "This resurfacing project in Brevard County will improve the condition of the existing pavement, provide better traffic signals and sensors, and enhance safety by upgrading pedestrian crossings." | Pavement Improvement | 2010-02-23 | 2010-02-23 | 2010-05-14 | 2010-05-23 | 742561 | 1.949 | ARRA234
2214 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA235 | This resurfacing project in Lake County will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2010-02-01 | 2010-02-11 | 2010-03-28 | 2010-03-23 | 19030 | 0.256 | ARRA235
2215 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA236 | This resurfacing project in Brevard County will improve the condition of the existing pavement and enhance safety by upgrading pedestrian crossings. | Pavement Improvement | 2010-02-17 | 2010-02-17 | 2010-05-08 | 2010-05-08 | 524419 | 0.995 | ARRA236
2216 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 06 | ARRA237 | This resurfacing project in Lake County will improve the condition of the pavement and enhance safety by upgrading pedestrian crossings. | Pavement Improvement | 2010-01-18 | 2010-01-28 | 2010-04-28 | 2010-04-28 | 156704 | 1.269 | ARRA237
2217 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA238 | This resurfacing project in the City of Cape Canaveral will improve the condition of the existing pavement and upgrade pedestrian crossings. | Pavement Improvement | 2010-02-08 | 2010-11-15 | 2010-10-15 | 2011-02-08 | 328998 | 0.998 | ARRA238
2218 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA239 | This resurfacing project in the Town of Malabar in Brevard County will improve the condition of the area where a paved driveway meets a road. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-06-12 | 2010-08-31 | 8175 | 0.103 | ARRA239
2219 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA240 | "This resurfacing project in Brevard County will improve the condition of the existing pavement, provide better traffic signals and controls, and enhance safety by providing upgraded pedestrian crossings." | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-03-14 | 2010-04-21 | 49243 | 0.161 | ARRA240
2220 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA241 | This resurfacing project in the Town of Malabar in Brevard County will improve the condition of the area where a paved driveway meets a road. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-06-12 | 2010-08-31 | 9195 | 0.071 | ARRA241
2221 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | Multiple | ARRA242 | "This project in the City of Cocoa will improve drainage along School Street, fix sidewalks and upgrade pedestrian crossings." | Safety/Traffic Management | 2010-03-02 | 2010-03-02 | 2010-06-30 | 2010-04-16 | 142678 | 0.247 | ARRA242
2222 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA243 | "This project in the City of Cocoa Beach will resurface the road, improve storm water drainage, fix sidewalks and upgrade pedestrian crossings." | Pavement Improvement | 2009-10-22 | 2009-11-02 | 2010-08-29 | 2011-01-18 | 262282 | 0.409 | ARRA243
2223 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA244 | "This resurfacing project in Brevard County will improve the condition of the existing pavement, provide better traffic signals and controls, and enhance safety by providing upgraded pedestrian crossings." | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-05-28 | 2011-03-11 | 374332 | 1.000 | ARRA244
2224 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA245 | This resurfacing project in the Town of Malabar in Brevard County will improve the condition of the area where a paved driveway meets a road. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-06-12 | 2010-08-31 | 6492 | 0.001 | ARRA245
2225 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA246 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-25 | 2010-02-03 | 2010-03-21 | 2010-03-15 | 18837 | 0.116 | ARRA246
2226 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 06 | ARRA247 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-22 | 2010-02-01 | 2010-05-18 | 2010-05-18 | 209728 | 2.276 | ARRA247
2227 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA248 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-11 | 2010-01-21 | 2010-05-21 | 2010-05-18 | 617616 | 4.896 | ARRA248
2228 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LADY LAKE | 06 | ARRA249 | This resurfacing project in Lake County will fix the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-11 | 2010-01-21 | 2010-04-21 | 2010-03-23 | 127208 | 0.300 | ARRA249
2229 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA250 | This resurfacing project in Lake County will improve the condition of the existing pavement and enhance safety by providing upgraded pedestrian crossings. | Pavement Improvement | 2010-01-18 | 2010-01-18 | 2010-04-28 | 2010-04-06 | 152316 | 1.854 | ARRA250
2230 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA251 | This resurfacing project in Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-11-24 | 2009-12-07 | 2010-03-08 | 2010-02-06 | 876255 | 2.160 | ARRA251
2231 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 24 | ARRA252 | This resurfacing project in the City of Oviedo will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-12-11 | 2009-12-11 | 2010-06-10 | 2010-05-13 | 996396 | 1.791 | ARRA252
2232 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA253 | This State Road 434 project in the City of Winter Springs will provide turn lanes to help reduce traffic congestion. | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-07-26 | 2010-08-27 | 160197 | 0.050 | ARRA253
2233 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA254 | The Rinehart Road project in the City of Lake Mary includes resurfacing which will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-11-19 | 2009-11-20 | 2010-03-12 | 2010-02-26 | 709242 | 2.090 | ARRA254
2234 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | Multiple | ARRA255 | The Howell Branch Road resurfacing project in Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2010-02-24 | 2010-01-25 | 497385 | 0.745 | ARRA255
2235 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA256 | The International Parkway resurfacing project within the City of Lake Mary will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2010-02-23 | 2010-03-01 | 2010-06-21 | 2010-06-07 | 355291 | 1.139 | ARRA256
2236 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA257 | The State Road 419 project in the City of Winter Springs will provide turn lanes to reduce traffic congestion. | Pavement Improvement | 2009-12-01 | 2009-12-01 | 2010-05-24 | 2010-08-18 | 387314 | 0.001 | ARRA257
2237 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | Multiple | ARRA258 | The West 25th Street resurfacing project is Seminole County will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2009-12-07 | 2009-12-17 | 2010-06-01 | 2010-04-30 | 1440164 | 1.164 | ARRA258
2238 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA259 | The 8th Street resurfacing project on a local road in the City of Holly Hill will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2010-01-27 | 2010-02-01 | 2010-03-13 | 2010-03-13 | 29962 | 0.110 | ARRA259
2239 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 24 | ARRA260 | The Taylor Creek Bridge project in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 2010-06-01 | 2010-06-01 | 2011-02-25 | 2011-04-18 | 2749828 | 0.049 | ARRA260
2240 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | Multiple | ARRA261 | The Campo Way Bridge project located in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 2010-04-09 | 2010-04-12 | 2010-10-08 | 2010-08-20 | 378019 | 0.333 | ARRA261
2241 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA262 | The Harrell Road Bridge project located in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 2010-04-02 | 2010-04-05 | 2010-10-31 | 2010-10-27 | 642519 | 0.457 | ARRA262
2242 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA263 | The Thorpe Road Bridge project located in Orange County will extend the life of the bridge and enhance safety. | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2010-11-05 | 2011-02-02 | 350559 | 1.005 | ARRA263
2243 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA264 | The Lake Underhill Road resurfacing project in Orange County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-04-01 | 2010-04-12 | 2010-11-28 | 2010-10-13 | 2109909 | 1.508 | ARRA264
2244 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | Multiple | ARRA265 | The Downtown Orlando Intelligent Transportation System (ITS) project will use underground fiber optic cable and video detection equipment to upgrade the regional computerized signal system which will ease traffic congestion. | Safety/Traffic Management | 2010-02-03 | 2010-02-03 | 2010-08-31 | 2010-09-09 | 3154100 |  | ARRA265
2245 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA266 | RESURFACING CLARKE ROAD FROM SILVER STAR ROAD TO CLARCONA-OCOEE ROAD (0002.516 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2010-02-04 | 2010-03-01 | 2010-05-30 | 2010-05-12 | 1109602 | 2.516 | ARRA266
2246 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA267 | The Morse Boulevard resurfacing project in Orange County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-01-07 | 2010-02-08 | 2010-05-31 | 2010-05-20 | 225502 | 0.870 | ARRA267
2247 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA268 | The General Rees Avenue resurfacing project in Orange County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-04-01 | 2010-04-12 | 2010-12-08 | 2010-11-08 | 967099 | 0.074 | ARRA268
2248 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA269 | The Dean Road resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-04-01 | 2010-04-05 | 2010-09-18 | 2010-08-11 | 1147105 | 1.864 | ARRA269
2249 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA270 | The Kaley Street resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-04-01 | 2010-04-05 | 2010-10-11 | 2010-09-08 | 394944 | 1.310 | ARRA270
2250 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 08 | ARRA271 | The Buenaventura Boulevard resurfacing project in Osceola County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2009-12-22 | 2009-12-22 | 2010-04-07 | 2010-05-25 | 1988254 | 2.573 | ARRA271
2251 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 08 | ARRA272 | The John Young Parkway resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2009-12-22 | 2009-12-22 | 2010-05-25 | 2010-04-16 | 1723783 | 1.494 | ARRA272
2252 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA273 | The Neptune Road resurfacing project will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2009-12-22 | 2009-12-22 | 2010-05-25 | 2010-04-16 | 163064 | 0.491 | ARRA273
2253 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA274 | The County Road 4139 resurfacing project in the City of Lake Helen will be constructed by Volusia County and will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-02-12 | 2010-02-22 | 2010-06-22 | 2010-06-04 | 300000 | 3.794 | ARRA274
2254 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA275 | The Riverside Drive resurfacing project in the City of New Smyrna Beach will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2009-11-19 | 2009-11-23 | 2010-04-17 | 2010-04-17 | 284059 | 0.839 | ARRA275
2255 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 24 | ARRA276 | The Canal View Boulevard resurfacing project in Port Orange will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2010-01-06 | 2010-01-11 | 2010-04-12 | 2010-03-15 | 103878 | 0.939 | ARRA276
2256 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA277 | The Lake Washington Road resurfacing project in the City of Melbourne will extend the usable life of the highway and enhance safety. | Pavement Improvement | 2010-02-16 | 2010-02-22 | 2010-06-22 | 2010-08-18 | 418399 | 1.046 | ARRA277
2257 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA278 | The Sykes Creek Parkway resurfacing project in Brevard County will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-06-08 | 2010-08-26 | 364283 | 1.437 | ARRA278
2258 | FLORIDA | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | HILLSBOROUGH | TAMPA-ST.PETERSBURG-CLEARWATER,FL | Multiple | ARRA279 | The I-4/Selmon Expressway Connector is a new toll road that will connect Interstate 4 to the Selmon Expressway and provide commercial trucks direct access to the Port of Tampa improving the efficient movement of goods. | Other | 1994-02-16 | 1994-02-16 | 2015-08-22 |  | 105033849 | 0.913 | ARRA279
2259 | FLORIDA | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | Multiple | ARRA280 | "In Pinellas County, to reduce congestion, this project removes the traffic signals on U.S. 19 between Whitney Road and State Road 60 and replaces them with two new interchanges at Belleair Road and Seville Boulevard." | Pavement Widening | 2004-05-24 | 2004-05-24 | 2014-09-29 |  | 45071034 | 2.643 | ARRA280
2260 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA281 | "This project widens Interstate 95 from Malabar Road to Palm Bay Road in Brevard County, making this section of I-95 three lanes in both directions." | Pavement Widening | 2009-10-01 | 2009-10-19 | 2012-06-30 |  | 21005001 | 4.173 | ARRA281
2261 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 05 | ARRA282 | "The U.S. 27 project will add two new lanes, making this a six-lane, divided highway from just north of Lake Louisa Road to Cluster Oaks Drive in the City of Clermont." | Pavement Widening | 2009-10-14 | 2009-10-14 | 2012-03-25 | 2012-01-17 | 19990334 | 3.837 | ARRA282
2262 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA283 | "This project will transform Baseline Road, which is primarily a two-lane highway, into a four-lane, divided highway near Ocala in Marion County." | Pavement Widening | 2009-09-11 | 2009-09-17 | 2019-10-16 |  | 27003841 | 5.704 | ARRA283
2263 | FLORIDA | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA284 | The State Road 50 project in the City of Winter Garden will widen this roadway more than three miles to a six-lane divided roadway. | Pavement Widening | 2007-07-26 | 2009-01-26 | 2012-09-30 |  | 18085738 | 3.056 | ARRA284
2264 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 03 | ARRA285 | "The State Road 434 project in the City of Altamonte Springs will make this section of the road a six-lane, divided highway, which is consistent to the rest of State Road 434 in this area." | Pavement Widening | 2009-09-30 | 2009-12-01 | 2012-03-25 | 2010-10-27 | 4628719 | 0.713 | ARRA285
2265 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 11 | ARRA288 | Resurface Tenth Street in the city of Palmetto from 8th Avenue to 14th Avenue to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2010-02-01 | 2010-04-29 | 2010-09-30 | 2010-11-01 | 76106 | 0.512 | ARRA288
2266 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA289 | Resurface Cattlemen Road in Sarasota County from Bahia Vista to south of Fruitville Road to improve the surface of this heavily traveled road. | Pavement Improvement | 2010-02-18 | 2010-02-18 | 2010-06-30 | 2011-04-19 | 395068 | 1.900 | ARRA289
2267 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | OKEECHOBEE |  | 16 | ARRA290 | Replace the bridge at 43rd Avenue in the city of Okeechobee to improve the safety of motorists. | Pavement Improvement | 2009-09-21 | 2009-10-24 | 2012-03-16 | 2010-11-26 | 1201547 | 0.001 | ARRA290
2268 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA291 | Resurface Sumter Boulevard in North Port from City Center Boulevard to Hansard Avenue. The project also includes the widening of a bridge and new turn lanes to move traffic more efficiently. | Pavement Improvement | 2010-03-22 | 2010-04-14 | 2012-12-31 | 2012-02-01 | 1448068 | 0.267 | ARRA291
2269 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA292 | "Install new traffic signals, ramps and asphalt crosswalks at the intersections at Venice Avenue and Harbor Drive in Sarasota County to improve the safety of the area." | Pavement Improvement | 2010-01-11 | 2010-03-31 | 2010-10-01 | 2010-11-10 | 332747 | 0.571 | ARRA292
2270 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA293 | Construct improvements to State Road 758 (Siesta Drive) between Siesta Bridge and Henson Bayou Bridge to correct a drainage problem along this entrance onto Siesta Key. | Pavement Improvement | 2010-03-24 | 2010-05-03 | 2010-09-30 |  | 1053068 | 0.502 | ARRA293
2271 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA294 | Resurface Venice Avenue in Sarasota County from Ramsey Road to Jacaranda Boulevard to improve the deteriorated surface of this busy road. | Pavement Improvement | 2010-04-21 | 2010-04-26 | 2010-08-31 | 2010-10-05 | 816068 | 1.016 | ARRA294
2272 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA295 | Resurface University Parkway in Manatee County from U.S. 41 to U.S. 301 to improve the deteriorated surface of this heavily traveled road. | Pavement Improvement | 2010-04-09 | 2010-04-14 | 2010-08-31 | 2011-04-19 | 753068 | 0.051 | ARRA295
2273 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | 13 | ARRA296 | Resurface University Parkway from U.S. 301 to I-75 to improve the deteriorated surface of this heavily traveled road. This is a joint project by Manatee and Sarasota counties. | Pavement Improvement | 2010-05-04 | 2010-05-11 | 2010-09-30 | 2010-10-08 | 1112836 |  | ARRA296
2274 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA297 | Resurface University Parkway from U.S. 301 to I-75 to improve the deteriorated surface of this heavily traveled road. This is a joint project by Manatee and Sarasota counties. | Pavement Improvement | 2010-05-04 | 2010-05-11 | 2010-09-30 |  | 1143956 | 5.235 | ARRA297
2275 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA303 | This trail project in Brevard County will create a safe environment for pedestrian and bicyclists. | Transportation Enhancements | 2010-01-06 | 2010-01-16 | 2010-06-08 | 2010-06-14 | 317660 |  | ARRA303
2276 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA304 | This project fixes a drainage pipe at Atz Road in the Town of Malabar in Brevard County. | Safety/Traffic Management | 2010-03-25 | 2010-03-25 | 2010-06-12 |  | 17493 | 0.293 | ARRA304
2277 | FLORIDA | Completed | C220,C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA305 | "The Downtown Streetscape project within the City of Flagler Beach will include sidewalks, better lighting and accessibility for all pedestrians." | Transportation Enhancements | 2010-02-26 | 2010-03-01 | 2012-02-28 | 2011-05-26 | 978028 | 0.519 | ARRA305
2278 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 08 | ARRA306 | "The Lois Drive Bridge project in Lake County replaces an outdated bridge that causes some vehicles to ""bottom out"" when they cross." | Pavement Improvement | 2009-12-17 | 2010-01-26 | 2012-04-26 | 2011-05-27 | 1867968 | 0.044 | ARRA306
2279 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA307 | This sidewalk project in Marion County will provide a safer environment for pedestrians and will upgrade pedestrian crossings. | Transportation Enhancements | 2009-10-16 | 2009-10-26 | 2010-03-31 | 2010-03-08 | 416083 |  | ARRA307
2280 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA308 | This repaving project in the City of Ocala will improve the road surface and upgrade sidewalks and pedestrians. | Pavement Improvement | 2009-11-06 | 2009-11-30 | 2010-08-25 | 2010-09-03 | 893095 | 1.020 | ARRA308
2281 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA309 | The Pine Hills Road/Silver Streetscape project in Orange County will provide a safer environment for pedestrians and bicyclists and enhance the renovation of Evans High School. | Transportation Enhancements | 2010-04-09 | 2010-04-12 | 2010-09-08 | 2010-10-15 | 320780 | 0.576 | ARRA309
2282 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | Multiple | ARRA310 | The Cross Seminole County Trail project will repair the Howell Creek Trestle Bridge which is a vital part of the Seminole County trail system. | Transportation Enhancements | 2009-12-07 | 2009-12-07 | 2010-03-26 | 2010-03-01 | 450866 |  | ARRA310
2283 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA311 | The International Parkway resurfacing project in the City of Lake Mary will extend the usable life of the roadway and enhance safety for all users. | Pavement Improvement | 2010-02-23 | 2010-03-01 | 2010-06-21 | 2010-06-07 | 391095 | 1.170 | ARRA311
2284 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 24 | ARRA312 | This State Road 434 project in the City of Winter Springs will provide safer conditions for making right turns at this intersection. | Pavement Improvement | 2009-12-01 | 2009-12-01 | 2010-05-20 | 2010-07-06 | 167396 | 0.064 | ARRA312
2285 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA313 | This repaving project in Osceola County will improve the road surface and upgrade pedestrian crossings. | Pavement Improvement | 2009-11-24 | 2010-01-11 | 2010-05-11 | 2010-07-13 | 661988 | 3.785 | ARRA313
2286 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA314 | This sidewalk project in Marion County will provide a safer environment for pedestrians and bicyclists as well as upgraded pedestrian crossings. | Pavement Improvement | 2009-11-24 | 2010-01-11 | 2010-06-10 | 2010-07-13 | 994947 | 7.425 | ARRA314
2287 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA315 | "The Lake Panasoffkee Pedestrian Trail, located in Sumter County, will provide a safe environment with a new, five-foot wide, concrete sidewalk for pedestrians and bicyclists." | Transportation Enhancements | 2009-12-10 | 2010-01-11 | 2010-04-10 | 2010-03-25 | 249507 |  | ARRA315
2288 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | Multiple | ARRA316 | The Dunn Avenue project in Daytona Beach will extend this road and includes a bridge over I-95. | New Construction | 2010-02-12 | 2010-03-01 | 2011-08-03 | 2011-06-30 | 5581933 | 0.612 | ARRA316
2289 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA318 | The 8th Street resurfacing project in the City of Holly Hill will extend the usable life of the roadway and enhance safety. | Pavement Improvement | 2010-02-03 | 2010-02-08 | 2010-06-18 | 2010-03-12 | 18402 | 0.129 | ARRA318
2290 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH, FL | 18 | ARRA319 | This project reconstructs almost three miles of the US 1 corridor known as the 18-mile stretch between Florida City and Key Largo. | Pavement Improvement | 2004-11-16 | 2004-11-16 | 2014-11-15 |  | 18198557 | 2.860 | ARRA319
2291 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA320 | "This bridge project will include the repair and safety upgrades of the bridge deck, repaving of the deck and the installation of handrails." | Transportation Enhancements | 2010-01-04 | 2010-01-05 | 2011-01-30 |  | 843134 | 0.243 | ARRA320
2292 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH, FL | 21 | ARRA322 | This project will provide improvements for bike paths and trails from Dadeland Station to S.W. 67th Avenue. | Transportation Enhancements | 2010-10-28 | 2011-01-07 | 2012-10-22 | 2012-01-23 | 3000000 |  | ARRA322
2293 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA323 | This project will provide maintenance and repairs to the Palm Drive Bridge in Monroe County. The project will replace the bridge deck and railings. | Bridge Improvement | 2009-11-19 | 2009-11-30 | 2010-03-05 | 2010-03-05 | 136053 | 0.013 | ARRA323
2294 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA324 | "This project will resurface the existing roadway, upgrade sidewalks, signing and pavement markings, replace signals and landscape. This project will enhance mobility for the community." | Pavement Improvement | 2010-06-02 | 2010-06-07 | 2011-10-31 | 2012-07-12 | 3913979 | 0.743 | ARRA324
2295 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA325 | This project will provide maintenance and repairs to the Geiger Creek bridge. These repairs will maintain a higher level of service. | Bridge Improvement | 2010-02-11 | 2010-02-17 | 2010-10-01 | 2011-10-13 | 914056 | 0.125 | ARRA325
2296 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA327 | The City of Medley will resurface and install new pavement markings. This project will enhance the efficient and safe flow of vehicular traffic. | Bridge Improvement | 2011-03-28 | 2011-04-08 | 2013-03-31 | 2011-10-24 | 42035 | 0.040 | ARRA327
2297 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA328 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2011-05-12 | 2011-09-21 | 154851 | 0.833 | ARRA328
2298 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA329 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2011-05-12 | 2011-09-21 | 212650 | 0.800 | ARRA329
2299 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA330 | This project will repave roadways throughout the Town of Cutler Bay. This project will enhance the ride for users of the town's roadway network. | Pavement Improvement | 2010-01-04 | 2010-03-22 | 2010-10-08 | 2012-02-08 | 194301 | 1.563 | ARRA330
2300 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA331 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Transportation Enhancements | 2009-12-01 | 2009-12-01 | 2010-09-30 | 2011-04-14 | 116640 |  | ARRA331
2301 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA332 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Transportation Enhancements | 2009-12-01 | 2009-12-01 | 2010-09-30 | 2011-02-28 | 146586 |  | ARRA332
2302 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA333 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2011-03-01 | 2011-11-03 | 449588 |  | ARRA333
2303 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA334 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2012-05-31 |  | 274051 |  | ARRA334
2304 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA335 | This project will provide bus stops at various locations in Miami-Dade County by repairing existing sidewalks and constructing sidewalk ramps. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2011-01-16 | 2011-07-28 | 176849 |  | ARRA335
2305 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA336 | The City of Surfside will install solar lighting on this corridor. This project will enhance safety. | Safety/Traffic Management | 2010-07-27 | 2010-08-16 | 2010-09-30 | 2011-11-02 | 46800 |  | ARRA336
2306 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA337 | "This project includes repaving, pavement markings, guardrails and sidewalk improvements." | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-11-01 | 2011-04-18 | 110000 | 1.000 | ARRA337
2307 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA338 | "This project will resurface 1.50 miles of road and add new markings, guardrails and sidewalk improvements." | Pavement Improvement | 2010-04-06 | 2010-04-06 | 2010-08-02 | 2010-10-26 | 88014 | 4.561 | ARRA338
2308 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA339 | This project will improve safety for motorists by repairing the underside of the bridge deck and bridge railings. | Bridge Improvement | 2010-03-11 | 2010-03-15 | 2010-09-30 | 2011-01-19 | 200753 | 0.080 | ARRA339
2309 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA340 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-22 | 2010-03-03 | 2012-03-31 | 2011-10-24 | 136680 | 0.400 | ARRA340
2310 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA341 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-22 | 2010-03-03 | 2010-10-22 | 2011-10-24 | 126202 | 0.228 | ARRA341
2311 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA342 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-03 | 2010-02-03 | 2011-01-26 | 2012-01-26 | 50582 | 0.070 | ARRA342
2312 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA343 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-03 | 2010-02-03 | 2011-01-26 | 2012-01-26 | 30892 | 0.250 | ARRA343
2313 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA344 | The City of Bal Harbour will provide crosswalk improvements. This project will provide enhancements to the pedestrian. | Safety/Traffic Management | 2010-03-09 | 2010-07-12 | 2010-10-29 |  | 24918 |  | ARRA344
2314 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA345 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2011-02-05 | 2012-08-03 | 167590 | 0.556 | ARRA345
2315 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA346 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2011-02-05 | 2012-08-03 | 32250 | 0.080 | ARRA346
2316 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA347 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-05-18 | 2010-05-18 | 2010-11-14 |  | 67881 | 0.080 | ARRA347
2317 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA348 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-10 | 2010-02-10 | 2011-02-10 | 2012-06-26 | 467820 | 0.630 | ARRA348
2318 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA349 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-05-18 | 2010-05-18 | 2010-11-14 |  | 48662 | 0.255 | ARRA349
2319 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA350 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-05-18 | 2010-05-18 | 2010-11-14 |  | 187035 | 0.270 | ARRA350
2320 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA351 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-03-02 | 2010-03-02 | 2011-02-25 | 2012-07-23 | 232873 | 0.310 | ARRA351
2321 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA352 | This project will provide bridge deck improvements to the Yacht Club bridge. | Bridge Improvement | 2010-01-25 | 2010-03-09 | 2010-09-30 | 2011-02-18 | 112553 | 0.200 | ARRA352
2322 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA353 | "The United Street corridor project in the City of Key West will repave the existing roadway, restripe the surface, and construct new sidewalks and curbs. This project will enhance safety for the motorist." | Pavement Improvement | 2010-06-01 | 2010-07-19 | 2011-05-31 | 2012-01-26 | 416433 | 0.266 | ARRA353
2323 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA354 | The Village of Biscayne Park will construct median curbs and an irrigation system. The project will enhance pedestrian safety. | Transportation Enhancements | 2009-09-16 | 2009-10-15 | 2009-12-21 | 2009-12-19 | 74073 | 0.527 | ARRA354
2324 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA355 | The Village of El Portal will resurface and enhance drainage at intersections. The project will enhance roadway safety for the traveling public. | Pavement Improvement | 2009-09-16 | 2009-11-09 | 2010-02-03 | 2010-01-20 | 56641 | 0.261 | ARRA355
2325 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA356 | "The City of Virginia Gardens will construct new drainage inlets at intersections, and perform pavement resurfacing and restriping. This project will enhance safety for the traveling public." | Pavement Improvement | 2009-09-16 | 2009-11-23 | 2010-02-03 | 2010-01-20 | 37260 | 0.300 | ARRA356
2326 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA357 | Larger drainage pipes will be installed under US 29 in the Town of Century as part of an overall community drainage improvement project in Escambia County. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2012-04-15 | 2010-06-02 | 460605 | 0.134 | ARRA357
2327 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA358 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2010-09-15 | 2010-09-15 | 2010-11-29 | 2012-03-23 | 174351 | 5.558 | ARRA358
2328 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA359 | This project will provide sidewalk enhancements along selected corridor. This project will increase pedestrian safety. | Transportation Enhancements | 2009-12-08 | 2010-01-05 | 2010-09-30 | 2010-11-06 | 112290 |  | ARRA359
2329 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA360 | This project will provide illuminated signs throughout various locations in Miami-Dade County to enhance driving conditions. | Safety/Traffic Management | 2010-01-20 | 2010-01-25 | 2010-09-23 | 2011-04-15 | 264345 |  | ARRA360
2330 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA361 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists. | Safety/Traffic Management | 2009-11-10 | 2009-11-12 | 2010-08-16 | 2010-06-04 | 126921 |  | ARRA361
2331 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA362 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists and pedestrians. | Safety/Traffic Management | 2009-11-30 | 2009-12-07 | 2010-09-13 | 2010-08-13 | 95443 |  | ARRA362
2332 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA363 | This project will provide new pavement markings and signage at designated sites throughout Miami-Dade County. The project will provide better direction for motorists. | Safety/Traffic Management | 2010-03-03 | 2010-03-08 | 2011-03-03 | 2011-04-21 | 216474 |  | ARRA363
2333 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA364 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along specific corridors. | Safety/Traffic Management | 2009-10-19 | 2009-10-19 | 2010-07-16 | 2010-06-04 | 54724 | 0.260 | ARRA364
2334 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA365 | "This project will renovate sidewalks, curbs, pavement, pavement markings and upgrade signage. These enhancements will help maintain a higher level of service." | Pavement Improvement | 2010-02-08 | 2010-03-02 | 2010-10-29 | 2011-03-21 | 199864 | 0.097 | ARRA365
2335 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA366 | "This project will add new drainage, lighting, sidewalk, curbs, pavement, pavement markings, signage and signalization. These enhancements will help maintain a higher level of service." | Pavement Improvement | 2010-02-15 | 2010-02-15 | 2010-10-29 | 2011-01-12 | 923920 | 0.524 | ARRA366
2336 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA367 | "This project will add new drainage, lighting, sidewalk, curbs, pavement, pavement markings, signage and signalization. These enhancements will help maintain a higher level of service." | Pavement Improvement | 2010-02-08 | 2010-03-01 | 2010-10-29 | 2011-05-06 | 884969 | 0.501 | ARRA367
2337 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA368 | "This project will add new drainage, lighting, sidewalk, curb, pavement, pavement markings, signage and signalization. These enhancements will help maintain a high level of service." | Pavement Improvement | 2010-02-08 | 2010-03-15 | 2010-10-29 | 2011-07-08 | 993339 | 0.465 | ARRA368
2338 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA369 | "This project will renovate sidewalks, curbs, pavement, pavement markings and upgrade signage. These enhancements will help maintain a higher level of service." | Pavement Improvement | 2010-02-08 | 2010-03-02 | 2010-10-29 | 2011-04-26 | 278218 | 1.488 | ARRA369
2339 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA370 | The City of Marianna will repave Milton Avenue to improve the road surface and driving quality in Jackson County. | Pavement Improvement | 2009-12-03 | 2009-12-18 | 2010-05-17 | 2010-08-30 | 219016 | 0.086 | ARRA370
2340 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA371 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2011-01-04 | 2011-07-28 | 147561 | 1.002 | ARRA371
2341 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA372 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2011-01-04 | 2011-07-28 | 194107 | 0.511 | ARRA372
2342 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA373 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-09-26 | 2012-05-24 | 262811 | 0.513 | ARRA373
2343 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA374 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-09-26 | 2012-05-24 | 190043 | 0.786 | ARRA374
2344 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA375 | This project will resurface the roadway. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-01-04 | 2010-01-04 | 2011-01-04 | 2011-07-28 | 162079 | 0.553 | ARRA375
2345 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA376 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 261098 | 1.512 | ARRA376
2346 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA377 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 26440 | 0.183 | ARRA377
2347 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA378 | This project will resurface the roadway. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 168559 | 0.516 | ARRA378
2348 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA379 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 198994 | 0.498 | ARRA379
2349 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA380 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-16 | 2010-02-16 | 2011-05-12 | 2011-09-21 | 357539 | 1.500 | ARRA380
2350 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA381 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-05-04 | 2011-10-25 | 139682 | 1.028 | ARRA381
2351 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA382 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-03-22 | 2010-03-22 | 2011-01-16 | 2011-10-24 | 342343 | 0.922 | ARRA382
2352 | FLORIDA | Completed | C250,C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA383 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2011-02-20 | 2012-06-11 | 550300 | 2.031 | ARRA383
2353 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA384 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-03-22 | 2010-03-22 | 2011-01-16 | 2011-10-24 | 166936 | 1.480 | ARRA384
2354 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA385 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-12-19 | 2011-10-25 | 249415 | 1.027 | ARRA385
2355 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA386 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-12-19 | 2011-10-25 | 351470 | 1.000 | ARRA386
2356 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA387 | This project will resurface the roadway. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2010-12-19 | 2011-10-25 | 237328 | 1.524 | ARRA387
2357 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA388 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2012-05-31 | 2012-08-03 | 65988 | 0.504 | ARRA388
2358 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA389 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2012-05-31 | 2012-08-03 | 183135 | 1.524 | ARRA389
2359 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA390 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-02-22 | 2010-02-22 | 2012-05-31 | 2012-08-03 | 237317 | 0.830 | ARRA390
2360 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA391 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-21 | 2010-04-30 | 2011-02-24 | 2012-01-18 | 132003 | 0.500 | ARRA391
2361 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA392 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-21 | 2010-04-30 | 2011-02-24 | 2012-01-18 | 107081 | 0.503 | ARRA392
2362 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA393 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-21 | 2010-04-30 | 2011-02-24 | 2012-01-18 | 383440 | 0.990 | ARRA393
2363 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA394 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-03-01 | 2012-01-26 | 216109 | 0.498 | ARRA394
2364 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA395 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-03-01 | 2012-01-26 | 102090 | 0.040 | ARRA395
2365 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA396 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2011-02-21 | 2011-07-14 | 573618 | 1.380 | ARRA396
2366 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA397 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses and residents. | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-07-30 | 2010-07-22 | 111494 | 0.311 | ARRA397
2367 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA398 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses and residents. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-10-29 | 2011-03-11 | 124240 | 0.160 | ARRA398
2368 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA399 | This project will enhance drainage at various locations to address flooding due to the existing drainage limitations. The project will provide a better quality of life for the surrounding businesses and residents. | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-10-29 | 2011-07-27 | 178641 | 0.826 | ARRA399
2369 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA400 | This Leon County project will add a left turn lane and a traffic signal on Meridian Road at Bannerman Road to improve traffic operations and safety. | Safety/Traffic Management | 2009-08-03 | 2009-08-03 | 2010-07-31 | 2010-05-04 | 662236 | 0.325 | ARRA400
2370 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA401 | The City of Homestead will install streetlight poles. Streetlights along the corridor will enhance the safety of all roadway users. | Safety/Traffic Management | 2009-12-01 | 2009-12-07 | 2010-10-29 | 2012-02-14 | 1155765 | 6.127 | ARRA401
2371 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA402 | This new project involves the installation of decorative lighting along the Ludlam Drive Bike Path in the City of Miami Springs. The project will provide better visibility for pedestrians. | Safety/Traffic Management | 2010-02-11 | 2010-02-12 | 2010-09-30 | 2011-02-22 | 554812 | 2.000 | ARRA402
2372 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA403 | This project will repair the deck of the Brickell Key Bridge over Biscayne Bay. The project will provide necessary repairs to the bridge to enhance mobility. | Bridge Improvement | 2010-09-30 | 2010-10-12 | 2011-06-29 | 2012-04-23 | 1680771 | 0.159 | ARRA403
2373 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA404 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 2010-02-25 | 2010-04-07 | 2010-11-19 | 2012-03-02 | 31122 | 0.191 | ARRA404
2374 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA405 | This project will provide lighting enhancements for the City of Homestead. Streetlights along this corridor will enhance safety for all roadway users. | Safety/Traffic Management | 2010-04-01 | 2010-04-01 | 2012-08-31 |  | 230754 | 0.903 | ARRA405
2375 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA406 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 2010-02-25 | 2010-04-07 | 2010-11-19 | 2012-03-02 | 96127 | 0.255 | ARRA406
2376 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA407 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 2010-02-25 | 2010-04-07 | 2010-11-19 | 2012-03-02 | 44135 | 0.137 | ARRA407
2377 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA408 | This project will resurface and repair existing pavement within the Village of Miami Shores. The project will provide a safer route along these important corridors. | Pavement Improvement | 2010-02-25 | 2010-04-07 | 2010-11-19 | 2012-03-02 | 69124 | 0.506 | ARRA408
2378 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA409 | "The City of South Miami will enhance sections of Sunset Drive by resurfacing, reconstructing sidewalks, upgrading drainage, and installing median landscaping and irrigation. This project will create a pedestrian-friendly corridor." | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-06-04 | 2012-03-01 | 253166 | 0.219 | ARRA409
2379 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA410 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along specific corridors. | Safety/Traffic Management | 2010-01-06 | 2010-01-06 | 2010-09-30 | 2010-08-17 | 13204 | 0.119 | ARRA410
2380 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA411 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along specific corridors. | Safety/Traffic Management | 2010-01-06 | 2010-01-06 | 2010-09-30 | 2010-08-17 | 12805 | 0.160 | ARRA411
2381 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA412 | This project will provide sidewalk enhancements along the selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-06-28 | 2010-07-23 | 2010-11-30 | 2011-05-17 | 123750 | 0.630 | ARRA412
2382 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA413 | This project will provide sidewalk enhancements along the selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-06-30 | 2010-08-02 | 2012-03-31 | 2012-03-07 | 856742 | 0.505 | ARRA413
2383 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA414 | The City of North Miami Beach will improve safety for motorists by repairing the underside of the bridge deck. | Bridge Improvement | 2010-06-02 | 2010-06-19 | 2010-09-30 | 2011-06-13 | 250000 | 0.016 | ARRA414
2384 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA415 | This project will repave the existing roadway. This project will enhance safety and mobility. | Pavement Improvement | 2010-03-09 | 2010-03-10 | 2011-03-31 | 2011-11-02 | 597596 | 0.424 | ARRA415
2385 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA417 | This project will provide sidewalk enhancements along selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-02-15 | 2010-02-18 | 2010-09-27 |  | 31880 | 0.140 | ARRA417
2386 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA418 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-03 | 2010-02-03 | 2011-01-26 | 2012-01-26 | 145528 | 0.394 | ARRA418
2387 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA419 | "The City of Key West will add sidewalks, curb ramps, crosswalks, signage, pavement replacement and pavement markings. This project will provide enhancements for pedestrians." | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-10-08 | 2012-01-26 | 170283 | 0.447 | ARRA419
2388 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA420 | This project will provide sidewalk enhancements along the selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-07-27 | 2010-10-18 | 2010-09-30 | 2011-11-02 | 84054 | 1.049 | ARRA420
2389 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA421 | This project will provide improvements for bike paths and trails. | Transportation Enhancements | 2010-02-22 | 2010-03-15 | 2010-10-01 | 2011-05-24 | 299825 | 2.387 | ARRA421
2390 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA422 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2011-01-25 | 2011-01-31 | 2010-11-29 | 2011-07-26 | 180479 | 1.666 | ARRA422
2391 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA423 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2011-05-23 | 2011-02-14 | 2010-06-25 | 2012-07-24 | 129777 | 0.474 | ARRA423
2392 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA424 | This project will repave roadways throughout the Town of Cutler Bay. This project will enhance the ride for users of the town's roadway network. | Pavement Improvement | 2010-01-04 | 2010-03-22 | 2010-10-08 | 2012-02-08 | 229073 | 1.682 | ARRA424
2393 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA425 | This project will repave roadways throughout the Town of Cutler Bay. This project will enhance the ride for users of the town's roadway network. | Pavement Improvement | 2010-01-04 | 2010-03-22 | 2010-10-08 | 2012-02-08 | 177532 | 1.112 | ARRA425
2394 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA426 | "This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network." | Pavement Improvement | 2010-01-04 | 2010-03-22 | 2010-10-08 | 2012-02-08 | 92368 | 1.232 | ARRA426
2395 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA427 | "This project will make improvements to sidewalks, concrete curbing, driveways, pavement markings, and partial drainage and roadway repairs. These improvements will enhance safety and mobility." | Pavement Improvement | 2010-09-08 | 2010-10-01 | 2011-03-11 | 2012-02-08 | 342882 | 1.626 | ARRA427
2396 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA428 | "This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network." | Pavement Improvement | 2010-01-04 | 2010-03-22 | 2010-10-08 | 2012-02-08 | 50059 | 0.450 | ARRA428
2397 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA429 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2011-02-07 | 2011-02-07 | 2010-12-01 | 2011-08-25 | 284147 | 1.188 | ARRA429
2398 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA430 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2011-02-07 | 2011-02-07 | 2010-12-01 | 2011-08-25 | 221918 | 2.176 | ARRA430
2399 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA431 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-11-01 | 2011-04-18 | 341088 | 1.410 | ARRA431
2400 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA432 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Pavement Improvement | 2010-04-06 | 2010-04-06 | 2010-08-02 | 2010-10-26 | 337988 | 1.000 | ARRA432
2401 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA434 | "This project includes repaving, pavement markings, guardrails and sidewalk improvements." | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2010-11-01 | 2011-04-18 | 160109 | 2.500 | ARRA434
2402 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA435 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along specific corridors. | Safety/Traffic Management | 2010-01-06 | 2010-01-06 | 2010-09-30 | 2010-08-17 | 14508 | 0.120 | ARRA435
2403 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA436 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along specific corridors. | Safety/Traffic Management | 2010-01-06 | 2010-01-06 | 2010-09-30 | 2010-08-17 | 30971 | 0.500 | ARRA436
2404 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA437 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2011-06-09 | 2011-06-09 | 2012-07-31 |  | 742984 |  | ARRA437
2405 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA438 | This project will resurface roadways within Miami-Dade County. This will enhance driving quality by improving the road surface. | Pavement Improvement | 2011-06-09 | 2011-06-09 | 2012-07-31 |  | 294399 |  | ARRA438
2406 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA439 | This project will repave the existing roadway and reconstruct existing sidewalks. This project will enhance safety and mobility. | Bridge Improvement | 2010-09-08 | 2010-09-28 | 2011-02-15 | 2011-09-13 | 444427 | 0.044 | ARRA439
2407 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA440 | This project will repave the existing roadway and repair existing pavement markings. This project will enhance safety and mobility. | Pavement Improvement | 2009-10-30 | 2010-02-11 | 2010-10-22 | 2011-03-01 | 317175 | 0.501 | ARRA440
2408 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA441 | The City of West Miami will construct four traffic-calming devices at various locations. This project will reduce the speed of traffic and improve pedestrian safety. | Safety/Traffic Management | 2009-09-14 | 2009-10-20 | 2010-07-12 | 2010-07-12 | 21063 | 0.013 | ARRA441
2409 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA442 | The City of West Miami will construct four traffic-calming devices at various locations. This project will reduce the speed of traffic and improve pedestrian safety. | Safety/Traffic Management | 2009-09-14 | 2009-10-20 | 2010-07-12 | 2010-07-12 | 30995 | 0.130 | ARRA442
2410 | FLORIDA | Completed | C220,C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA444 | This project will repave the existing roadway and repair existing pavement markings. This project will enhance safety and mobility. | Transportation Enhancements | 2009-10-30 | 2009-11-18 | 2010-10-08 | 2011-03-16 | 179282 | 0.470 | ARRA444
2411 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA445 | "This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network." | Pavement Improvement | 2010-01-04 | 2010-03-22 | 2010-10-08 | 2012-02-08 | 156805 | 1.708 | ARRA445
2412 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA446 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 2009-11-23 | 2009-11-23 | 2010-09-23 | 2010-09-13 | 20860 | 1.000 | ARRA446
2413 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA447 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 2009-11-23 | 2009-11-23 | 2010-09-23 | 2010-09-13 | 14781 | 1.174 | ARRA447
2414 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA448 | This project will provide sidewalk enhancements along selected corridors in Miami-Dade County. This project will increase pedestrian safety. | Safety/Traffic Management | 2009-11-23 | 2009-11-23 | 2010-09-23 | 2010-09-13 | 19806 | 0.504 | ARRA448
2415 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA449 | This project involves widening 0.8 miles of a three-lane roadway to five lanes. This project will ease congestion and provide interconnectivity. | Pavement Widening | 2010-01-08 | 2010-01-08 | 2012-06-30 | 2012-06-20 | 776997 | 1.017 | ARRA449
2416 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA450 | This project will provide sidewalk enhancements and increase pedestrian safety. | Transportation Enhancements | 2010-01-04 | 2010-01-05 | 2010-09-30 | 2011-03-10 | 456640 | 0.707 | ARRA450
2417 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA451 | "This project will provide new construction of a new raised landscaped median, new turning bays for left turn movements and new curb bump outs at intersections to provide for improved bus access. This | Pavement Improvement | 2010-03-18 | 2010-04-05 | 2010-12-22 | 2012-04-16 | 1036796 | 0.408 | ARRA451
2418 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA452 | This project will improve safety for motorists by repaving and adding new striping and pavement markings. | Pavement Improvement | 2011-06-09 | 2010-11-23 | 2012-03-31 | 2012-07-23 | 287676 | 0.327 | ARRA452
2419 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA453 | "This project will improve safety for motorists by repairing the bridge beams, bridge seawall and repairing the sidewalk approach." | Bridge Improvement | 2010-03-05 | 2010-03-05 | 2010-09-27 | 2011-04-12 | 270310 | 0.026 | ARRA453
2420 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA454 | This project will improve safety for motorists by sealing cracks at the bridge deck top and underside. | Bridge Improvement | 2010-03-05 | 2010-03-15 | 2010-09-30 | 2011-04-12 | 255443 | 0.028 | ARRA454
2421 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA455 | This project will repave the existing roadway. This project will enhance safety and mobility. | Pavement Improvement | 2009-12-08 | 2010-01-15 | 2012-03-31 | 2012-05-22 | 705217 | 0.752 | ARRA455
2422 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA456 | "This project will resurface the existing roadway, upgrade sidewalks, signing and pavement markings, replace signals and landscape. This project will enhance mobility for the community." | Pavement Improvement | 2010-05-27 | 2010-06-01 | 2010-11-29 | 2011-05-26 | 510979 | 0.297 | ARRA456
2423 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA457 | This project will install guardrails in areas adjacent to bodies of water along selected sites in Miami-Dade County. These enhancements will reduce potential canal hazards and increase safety along specific corridors. | Safety/Traffic Management | 2009-10-19 | 2009-10-19 | 2010-07-16 | 2010-06-04 | 69551 | 1.014 | ARRA457
2424 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA458 | The City of Fort Walton Beach will repave Memorial Parkway to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-07-31 | 2010-07-31 | 437600 | 1.304 | ARRA458
2425 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA459 | The City of Fort Walton Beach will repave Bay Drive Southeast to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-07-31 | 2010-07-31 | 152726 | 1.572 | ARRA459
2426 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | CALHOUN |  | 02 | ARRA460 | This safety project will provide roadway striping on city streets in the City of Blountstown to provide safer travel on roads that have little or no existing striping in Calhoun County. | Safety/Traffic Management | 2009-12-14 | 2009-12-24 | 2010-04-13 | 2010-04-02 | 80383 | 3.125 | ARRA460
2427 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA461 | This safety project will provide roadway striping on rural roads in Gadsden County to provide safer travel on roads that have little or no existing striping. | Safety/Traffic Management | 2010-05-03 | 2010-05-11 | 2010-08-31 | 2010-06-15 | 519777 |  | ARRA461
2428 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN | TALLAHASSEE | 02 | ARRA462 | This safety project will provide roadway striping on roads in Gadsden County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 2010-03-22 | 2010-04-01 | 2010-08-31 | 2010-04-29 | 268359 |  | ARRA462
2429 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | GULF |  | 02 | ARRA463 | Gulf County will repave County Road 30A to improve the road surface and driving quality. | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2010-04-30 | 2010-06-15 | 273077 | 0.300 | ARRA463
2430 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA464 | This safety project will provide roadway striping on rural roads in Holmes County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 2009-11-06 | 2009-11-12 | 2010-02-16 | 2010-02-05 | 547214 | 16.647 | ARRA464
2431 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | LIBERTY |  | 02 | ARRA465 | Liberty County will install guardrail at several locations on county roads to improve the safety of the traveling public. | Safety/Traffic Management | 2009-11-17 | 2009-11-30 | 2010-03-04 | 2010-02-18 | 266006 |  | ARRA465
2432 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA467 | Okaloosa County will replace drainage pipes and existing failing pavement on Hollywood Boulevard in Fort Walton Beach to improve the road surface and driving quality. | Pavement Improvement | 2009-11-19 | 2009-12-01 | 2010-05-15 | 2010-07-19 | 1391467 | 0.187 | ARRA467
2433 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA468 | "The City of Destin will add bus stops, public parking and landscaping, improve sidewalks, and replace existing failing pavement on Scenic Highway to improve pedestrian safety and travel in Okaloosa County." | Pavement Improvement | 2009-10-06 | 2009-10-19 | 2010-06-25 | 2010-07-10 | 760955 | 0.771 | ARRA468
2434 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WAKULLA |  | 02 | ARRA469 | This safety project will provide roadway striping on rural roads in Wakulla County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 2009-10-13 | 2009-11-02 | 2009-12-28 | 2009-11-18 | 64707 | 19.785 | ARRA469
2435 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA470 | Walton County will construct a pedestrian bridge over Big Redfish Lake along County Road 30A to improve pedestrian safety. | Transportation Enhancements | 2010-01-07 | 2010-01-17 | 2010-05-18 | 2010-07-19 | 458483 | 0.001 | ARRA470
2436 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA471 | This safety project will provide roadway striping on rural roads in Washington County to improve travel on roads that have little or no existing striping. | Safety/Traffic Management | 2009-11-04 | 2009-11-14 | 2010-03-15 | 2010-04-23 | 449538 | 11.460 | ARRA471
2437 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA472 | Washington County will repave State Park Road to improve the road surface and driving quality. | Pavement Improvement | 2009-12-07 | 2009-12-17 | 2010-05-25 | 2010-05-26 | 241313 | 1.035 | ARRA472
2438 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA473 | This project involves the design of a traffic circle that will be used as a traffic calming device and improvements at crosswalks. This project will enhance safety and mobility. | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2012-03-31 | 2012-06-26 | 409310 | 0.178 | ARRA473
2439 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA474 | "This project will resurface 9.3 miles of the town's roadway and repair damaged sidewalks. This project will improve the ride, safety and mobility for users of the town's roadway and sidewalk network." | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2010-09-30 | 2011-03-15 | 160500 | 0.010 | ARRA474
2440 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA475 | BIKE PATH/TRAIL SR 5/OVRSEAS HRT.TRL FROM MM 47 TO MM 54 SAFETY IMPROVEMENTS (0005.909 MILES) IN MONROE COUNTY, FLORIDA. | Transportation Enhancements | 2010-04-26 | 2010-05-03 | 2012-06-30 | 2012-06-11 | 500000 | 5.909 | ARRA475
2441 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA476 | "This project will provide intersection realignment, resurfacing of roadway, new striping, signage and emergency signalization." | Pavement Improvement | 2010-02-05 | 2010-02-15 | 2010-09-03 | 2011-07-05 | 87000 | 0.133 | ARRA476
2442 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA478 | "This project will enhance the Sombrero Beach Road extension by installing storm water facilities, renovating the bike path, installing streetlights, and widening, resurfacing and restriping the road." | Pavement Improvement | 2010-01-11 | 2010-01-27 | 2010-10-14 | 2011-03-18 | 1010000 | 0.260 | ARRA478
2443 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA479 | This project will repave approximately 0.9 miles of Harbor Drive to improve the ride for the users of this roadway. | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2010-08-30 | 2010-07-12 | 106109 | 0.912 | ARRA479
2444 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA480 | This project will install lighting along approximately 0.4 mile of the project corridor providing better visibility to the users of this roadway. | Safety/Traffic Management | 2009-10-19 | 2009-10-19 | 2010-08-30 | 2010-07-12 | 154195 | 0.497 | ARRA480
2445 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA481 | This project will provide sidewalk enhancements along the selected corridor. This project will increase pedestrian safety. | Safety/Traffic Management | 2010-03-09 | 2010-04-05 | 2010-11-12 | 2012-04-16 | 116249 | 0.250 | ARRA481
2446 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA482 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2010-07-09 | 2010-07-12 | 2010-10-25 | 2011-05-24 | 131889 | 0.210 | ARRA482
2447 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA483 | The City of Miami will repair and replace sidewalks and ramps to enhance the corridor for pedestrians. | Safety/Traffic Management | 2010-06-07 | 2010-06-28 | 2010-10-25 |  | 126562 | 0.983 | ARRA483
2448 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA484 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-11-18 | 2011-06-09 | 582508 | 2.000 | ARRA484
2449 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA485 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-04-07 | 2010-04-19 | 2012-05-31 | 2012-05-22 | 1246954 | 2.510 | ARRA485
2450 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA486 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-04-07 | 2010-04-19 | 2012-07-31 |  | 259496 | 1.540 | ARRA486
2451 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA487 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-11-18 | 2011-07-28 | 546331 | 1.320 | ARRA487
2452 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA488 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-11-18 | 2011-07-13 | 181784 | 0.509 | ARRA488
2453 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA489 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-16 | 2010-02-16 | 2010-11-18 | 2011-07-13 | 225723 | 2.039 | ARRA489
2454 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA490 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists. | Safety/Traffic Management | 2010-03-29 | 2010-03-29 | 2010-11-29 | 2012-01-06 | 242152 | 1.003 | ARRA490
2455 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA491 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2010-12-01 | 2011-07-27 | 459564 | 2.976 | ARRA491
2456 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA492 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2012-05-31 | 2012-05-22 | 470835 | 1.762 | ARRA492
2457 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA493 | The Village of Pinecrest will repave two miles of road. This project will enhance mobility for users of this roadway. | Pavement Improvement | 2009-12-25 | 2010-01-04 | 2010-09-30 | 2011-08-02 | 252822 | 2.042 | ARRA493
2458 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA494 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-03-29 | 2010-03-29 | 2010-11-29 | 2012-01-31 | 415374 | 2.770 | ARRA494
2459 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA495 | The project will repave the existing roadway. This project will enhance mobility for users of this roadway. | Pavement Improvement | 2009-12-25 | 2010-01-19 | 2010-09-30 | 2011-08-02 | 187586 | 1.331 | ARRA495
2460 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA496 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2010-12-01 | 2012-01-06 | 310190 | 1.989 | ARRA496
2461 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA497 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2012-05-31 | 2012-04-30 | 533492 | 2.001 | ARRA497
2462 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA498 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2010-12-01 | 2012-01-06 | 153379 | 1.212 | ARRA498
2463 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA499 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-23 | 2010-03-01 | 2010-10-02 | 2011-10-26 | 605793 | 2.004 | ARRA499
2464 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA500 | This project will provide street lighting installations throughout Miami-Dade County. The project will provide better visibility for motorists and pedestrians. | Safety/Traffic Management | 2010-02-26 | 2010-03-01 | 2010-10-01 | 2011-06-22 | 303825 | 1.009 | ARRA500
2465 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | CALHOUN |  | 02 | ARRA501 | Guardrail will be installed on several county roads in Calhoun County to improve the safety of the traveling public. | Safety/Traffic Management | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 146937 | 6.302 | ARRA501
2466 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | CALHOUN |  | 02 | ARRA502 | This safety project will provide roadway striping on rural roads in Calhoun County to provide safer travel on roads that had little or no existing striping. | Safety/Traffic Management | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2009-11-10 | 214699 | 9.656 | ARRA502
2467 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WAKULLA |  | 02 | ARRA503 | Crosswalks and sidewalks were constructed along State Road 363 to improve pedestrian safety in the City of St. Marks. | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2009-11-14 | 31746 | 0.097 | ARRA503
2468 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA504 | Five-foot wide sidewalks along various streets within the city limits of Gretna will be constructed to improve pedestrian safety in Gadsden County . | Transportation Enhancements | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2010-01-20 | 326817 | 0.777 | ARRA504
2469 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA505 | This pedestrian safety project in Holmes County will include the construction of a 600-foot sidewalk in the Town of Noma. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 37573 | 0.117 | ARRA505
2470 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA506 | This pedestrian safety project in Holmes County will include the construction of a 900-foot sidewalk in the Town of Esto. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 74565 | 0.336 | ARRA506
2471 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | JEFFERSON |  | Multiple | ARRA507 | Existing deficient pavement on North Salt Road in Jefferson County will be replaced to improve the road surface and driving quality. | Safety/Traffic Management | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2010-04-12 | 697642 | 4.889 | ARRA507
2472 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA508 | A five-foot wide sidewalk along State Road 69 will be constructed in the City of Grand Ridge to improve pedestrian safety in Jackson County. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 133912 | 0.255 | ARRA508
2473 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA509 | A five-foot wide sidewalk along State Road 285 has been constructed in the City of Niceville to improve pedestrian safety in Okaloosa County. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2009-11-06 | 155764 | 0.858 | ARRA509
2474 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA510 | A five-foot wide sidewalk along 19th Street will be constructed in the City of DeFuniak Springs to improve pedestrian safety in Walton County. | Transportation Enhancements | 2009-07-29 | 2009-07-29 | 2012-03-07 | 2010-06-11 | 164293 | 2.196 | ARRA510
2475 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA511 | Walton County will repave County Road 30A to improve the road surface and driving quality. | Pavement Improvement | 2010-01-07 | 2010-01-17 | 2010-05-12 | 2010-08-27 | 1028522 | 1.170 | ARRA511
2476 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA512 | The City of Marianna in Jackson County will repave College Street to improve the road surface and driving quality. | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2010-04-17 | 2010-04-15 | 187993 | 0.589 | ARRA512
2477 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA513 | The City of Freeport will construct a five-foot wide sidewalk along State Road 20 to improve pedestrian safety in Walton County. | Transportation Enhancements | 2009-11-09 | 2009-11-09 | 2009-12-08 | 2009-12-30 | 49132 | 0.114 | ARRA513
2478 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | WAKULLA | TALLAHASSEE | 02 | ARRA514 | This project will improve safety for motorists by providing a left turn lane onto Russell Drive north of the City of Crawfordville. | Pavement Widening | 2009-08-18 | 2009-08-18 | 2012-03-06 | 2009-12-17 | 199036 | 0.214 | ARRA514
2479 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA515 | This Jackson County project consists of installing sidewalk along Caverns Road to increase pedestrian safety to Marianna High School. | Transportation Enhancements | 2009-10-15 | 2009-10-15 | 2010-08-15 | 2010-09-15 | 507378 | 1.631 | ARRA515
2480 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA516 | This Jackson County project consists of restriping cross-walks and replacing failing sidewalks to improve pedestrian safety in the City of Marianna. | Safety/Traffic Management | 2009-10-15 | 2009-10-15 | 2010-04-27 | 2010-04-30 | 213675 | 0.068 | ARRA516
2481 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA517 | "The City of Tallahassee will construct approximately 2,300 feet of sidewalk along Idlewild Drive to improve pedestrian safety in Leon County." | Transportation Enhancements | 2010-03-04 | 2010-03-04 | 2010-10-24 | 2010-10-24 | 272599 | 0.413 | ARRA517
2482 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA518 | "The City of Tallahassee will construct approximately 1,800 feet of sidewalk along Lucy Street to improve pedestrian safety in Leon County." | Transportation Enhancements | 2010-03-03 | 2010-03-03 | 2010-08-30 | 2010-10-20 | 91587 | 0.353 | ARRA518
2483 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA519 | This City of Tallahassee project will reconstruct curb ramps and pedestrian signal features to improve pedestrian safety in the community. | Transportation Enhancements | 2010-03-29 | 2010-03-29 | 2010-09-21 | 2010-08-10 | 138480 | 1.081 | ARRA519
2484 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA520 | "The City of Tallahassee will construct approximately 1,000 feet of sidewalk along Ingleside Avenue to improve pedestrian safety in Leon County." | Transportation Enhancements | 2010-03-03 | 2010-03-03 | 2010-08-30 | 2010-10-22 | 357205 | 0.427 | ARRA520
2485 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA | FORT WALTON BEACH | Multiple | ARRA521 | The City of Fort Walton Beach will repave Country Club Avenue to improve the road surface and driving quality in Okaloosa County. | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-07-31 | 2010-07-31 | 142948 | 0.850 | ARRA521
2486 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN | TALLAHASSEE | 02 | ARRA522 | Gadsden County will repave Glades Road to improve the road surface and driving quality. | Pavement Improvement | 2009-12-14 | 2009-12-24 | 2010-05-31 | 2010-05-27 | 384409 | 1.840 | ARRA522
2487 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA523 | Gadsden County will repave South Main Street to improve the road surface and driving quality. | Pavement Improvement | 2010-03-16 | 2010-03-26 | 2010-08-31 | 2010-06-22 | 123790 | 0.250 | ARRA523
2488 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA524 | "Leon County will construct approximately 4,700 feet of sidewalk along Dempsey Mayo Road to improve pedestrian safety." | Transportation Enhancements | 2010-01-19 | 2010-01-19 | 2010-03-20 | 2010-04-27 | 125361 | 0.906 | ARRA524
2489 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA525 | Leon County will repair the existing sidewalk and construct additional sidewalk along Perkins Road to improve pedestrian safety in the City of Tallahassee. | Transportation Enhancements | 2009-11-23 | 2009-11-23 | 2010-03-22 | 2010-04-21 | 18727 | 0.076 | ARRA525
2490 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA526 | Leon County will construct approximately one mile of sidewalk along Velda Dairy Road to improve pedestrian safety. | Transportation Enhancements | 2010-04-13 | 2010-04-13 | 2010-06-25 | 2010-10-21 | 226484 | 1.729 | ARRA526
2491 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | OKALOOSA |  | Multiple | ARRA527 | Okaloosa County will construct a five-foot sidewalk along Brookmeade Drive to improve pedestrian safety in the City of Crestview. | Transportation Enhancements | 2009-12-16 | 2009-12-21 | 2010-03-30 | 2010-01-29 | 81454 | 0.373 | ARRA527
2492 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA528 | "Franklin County will construct approximately 2,700 feet of five-foot wide sidewalk along Pine Avenue to improve pedestrian safety." | Transportation Enhancements | 2009-11-09 | 2009-11-09 | 2010-02-07 | 2010-03-31 | 98745 | 0.227 | ARRA528
2493 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA529 | Escambia County will repave Dog Track Road to improve the road surface and driving quality. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-08-25 | 2010-05-28 | 256335 | 1.125 | ARRA529
2494 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA530 | Escambia County will repave Old Palafox Road from East Roberts Boulevard to Nine Mile Road to improve the road surface and driving quality in the City of Pensacola. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-08-25 | 2011-01-19 | 428776 | 2.182 | ARRA530
2495 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA531 | Escambia County will repave Old Palafox Road from Memory Lane to Nine Mile Road to improve the road surface and driving quality in the City of Pensacola. | Pavement Improvement | 2009-10-29 | 2009-11-02 | 2010-09-04 | 2011-01-18 | 1210429 | 4.342 | ARRA531
2496 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA532 | Escambia County will repave Copter Road to improve the road surface and driving quality. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-06-26 | 2010-08-19 | 283170 | 0.428 | ARRA532
2497 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA533 | "Along with pedestrian safety improvements, Escambia County will repave ""W"" Street to improve the road surface and driving quality." | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-09-24 | 2011-03-31 | 1645398 | 3.081 | ARRA533
2498 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA534 | Escambia County will repave Dog Track Road from Blue Angel Parkway to US 98 to improve the road surface and driving quality. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-07-06 | 2010-06-07 | 473189 | 2.084 | ARRA534
2499 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA535 | Escambia County will repave East Johnson Avenue to improve the road surface and driving quality. | Pavement Improvement | 2009-10-13 | 2009-10-19 | 2010-07-06 | 2010-07-06 | 243267 | 0.845 | ARRA535
2500 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA536 | Escambia County will repave Beulah Road to improve the road surface and driving quality. | Pavement Improvement | 2010-04-20 | 2010-04-26 | 2011-06-30 | 2010-11-09 | 650715 | 1.350 | ARRA536
2501 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA537 | Escambia County will construct a five-foot wide sidewalk along Broad Street to improve pedestrian safety. | Transportation Enhancements | 2009-10-13 | 2009-10-19 | 2010-04-17 | 2010-04-16 | 96201 | 0.468 | ARRA537
2502 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE |  | Multiple | ARRA538 | Add Sidewalks along Gulf Front Park from Maple Street to Oak Street in the City of Anna Maria to improve safety for pedestrians in the area. | Transportation Enhancements | 2009-09-16 | 2009-11-09 | 2012-03-26 | 2009-11-30 | 6452 |  | ARRA538
2503 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA539 | BIKE PATH/TRAIL WITHLACOOCHEE TRAIL CONNECTION FROM N TRAIL E ND TO NE OF US 41 & RIVER IN CITRUS COUNTY, FLORIDA. | Transportation Enhancements | 2006-05-05 |  | 2012-06-30 |  | 320000 |  | ARRA539
2504 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARION |  | Multiple | ARRA540 | This project was awarded from the Florida Department of Environmental Protection to Marion County and includes improvements to a bicycle/pedestrian trail. | Transportation Enhancements | 2010-03-08 | 2010-03-08 | 2010-12-31 | 2010-12-02 | 2000000 |  | ARRA540
2505 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | LIBERTY |  | 02 | ARRA541 | Liberty County will construct approximately one mile of sidewalk along County Road 12 leading to Tolar Elementary School to improve pedestrian safety in the City of Bristol. | Transportation Enhancements | 2009-12-02 | 2009-12-07 | 2010-06-04 | 2010-06-04 | 219582 | 0.809 | ARRA541
2506 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | WAKULLA | TALLAHASSEE | 02 | ARRA542 | This project will improve safety for motorists by providing a left turn lane onto Aaron Strickland Road north of the City of Crawfordville. | Pavement Widening | 2010-02-01 | 2010-02-15 | 2010-05-27 | 2010-05-14 | 174680 | 0.287 | ARRA542
2507 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA543 | Add a new sidewalk along Cape Coral Parkway from Agualinda Boulevard to 16th Place in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 2009-11-17 | 2009-11-23 | 2010-05-31 | 2010-06-01 | 102494 | 0.846 | ARRA543
2508 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA544 | Widen Six Mile Cypress Parkway from two to four lanes from Daniels Parkway to Winkler Extension to reduce congestion and enhance safety. | Pavement Widening | 2010-10-04 | 2010-10-04 | 2011-12-28 |  | 4030000 | 3.080 | ARRA544
2509 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA545 | Add a new sidewalk along Nicholas Parkway from State Road 78 to Santa Barbara Boulevard in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 2009-11-17 | 2010-03-29 | 2010-10-31 | 2011-06-29 | 257739 | 1.344 | ARRA545
2510 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA546 | Add a new sidewalk along Beach Parkway from Surfside Boulevard to Chiquita Boulevard in Lee County to enhance safety for bicyclists and pedestrians. | Transportation Enhancements | 2009-11-17 | 2010-06-30 | 2011-04-01 | 2011-04-28 | 379472 | 1.935 | ARRA546
2511 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA547 | This State Road 40 project in the City of Ormond Beach will provide an eight-foot wide bike/pedestrian trail in a residential community. | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-07-29 | 2010-06-24 | 171063 | 0.969 | ARRA547
2512 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA549 | "On the southeast side of Jacksonville, State Road 9B, a new four-lane highway, will relieve congestion on the heavily traveled U.S. 1 and Old St. Augustine Road corridors." | New Construction | 2008-11-20 | 2009-01-01 | 2015-11-20 |  | 64363517 | 3.593 | ARRA549
2513 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA550 | "On the southeast side of Jacksonville, State Road 9B, a new four-lane highway, will relieve congestion on the heavily traveled U.S. 1 and Old St. Augustine Road corridors." | New Construction | 2010-02-05 | 2010-01-20 | 2015-11-20 |  | 11435951 | 0.501 | ARRA550
2514 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA551 | "In Citrus County, this project repaves 2.4 miles of Independence Highway from State Road 44 to U.S. 41 to improve the road surface." | Pavement Improvement | 2010-04-04 | 2010-04-06 | 2010-06-19 | 2010-05-07 | 424144 | 2.412 | ARRA551
2515 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA552 | "In Hernando County, due to the poor condition of the road, this project resurfaces 1.6 miles of County Road 574 from California Street to Broad Street (U.S. 41)." | Pavement Improvement | 2010-05-21 | 2010-10-10 | 2010-11-08 | 2010-11-23 | 434286 | 1.595 | ARRA552
2516 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA553 | "In Hernando County, this project repaves 2.5 miles of the asphalt surface of County Road 541 from Mountain View Blvd. to State Road 50 to improve the road surface." | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-11-28 | 2011-04-12 | 1117356 | 2.450 | ARRA553
2517 | FLORIDA | Completed | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | PASCO | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 05 | ARRA554 | "In Pasco County, this project replaces the asphalt surface and constructs improvements for easier access at the interchange of State Road 54 and the Suncoast Parkway." | Pavement Improvement | 2010-07-26 | 2010-07-26 | 2011-06-24 | 2011-08-04 | 3421747 | 1.243 | ARRA554
2518 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | LEE |  | 14 | ARRA555 | Widen Interstate 75 from Colonial Boulevard to State Road 82 in Southwest Florida from four to six lanes to move daily traffic and commerce more efficiently. | Pavement Widening | 2009-12-15 | 2009-12-21 | 2050-07-29 |  | 9142131 | 1.536 | ARRA555
2519 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | Multiple | ARRA556 | ADD SPECIAL USE LANE I-95/EXPRESS/HOT LNS FROM DADE/BROWARD CO LINE TO I-595/BROWARD P& R LOT (0007.700 MILES) IN BROWARD COUNTY, FLORIDA. | Pavement Widening | 2010-04-23 | 2010-04-23 | 2020-04-22 |  | 87007359 | 7.700 | ARRA556
2520 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | GADSDEN |  | 02 | ARRA557 | SIDEWALK CITY OF GRETNA FOURTH STREET SIDEWALK 2009 ECONOMIC STIMULUS (0000.285 MILES) IN GADSDEN COUNTY, FLORIDA. | Transportation Enhancements | 2010-03-08 | 2010-03-08 | 2010-05-21 | 2010-05-14 | 39762 | 0.285 | ARRA557
2521 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | HENDRY |  | Multiple | ARRA558 | WIDEN/RESURFACE EXIST LANES CR 832 (KERI ROAD) FROM SR 29 TO 13.1 MILES E OF SR 29 (0013.100 MILES) IN HENDRY COUNTY, FLORIDA. | Pavement Improvement | 2009-07-22 | 2010-05-10 | 2012-07-21 | 2012-01-03 | 2428505 | 13.100 | ARRA558
2522 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA559 | RESURFACING HABEN BLVD FROM US 301 TO US 41 (0001.044 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 2009-09-22 | 2010-01-18 | 2012-03-12 |  | 807963 | 1.044 | ARRA559
2523 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA560 | SIDEWALK SR 79 SIDEWALKS PHASE II 2009 ECONOMIC STIMULUS (0000.433 MILES) IN HOLMES COUNTY, FLORIDA. | Transportation Enhancements | 2010-02-17 | 2010-02-17 | 2012-05-24 | 2010-06-17 | 85226 | 0.433 | ARRA560
2524 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | 07 | ARRA561 | RESURFACING BRENTWOOD DRIVE FROM FEC RAILROAD TO DERBYSHIRE ROAD (0001.478 MILES) IN VOLUSIA COUNTY, FLORIDA. | Pavement Improvement | 2010-06-04 | 2010-06-14 | 2010-10-13 | 2010-08-30 | 131931 | 1.478 | ARRA561
2525 | FLORIDA | Completed | C200,C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE |  | 06 | ARRA562 | BRIDGE REPLACEMENT PICCIOLA ROAD BRIDGE FROM SABLE PALM DRIVE TO EAST OF LAKE UNITY RD (0000.352 MILES) IN LAKE COUNTY, FLORIDA. | Bridge Replacement | 2010-07-19 | 2010-08-18 | 2011-08-18 | 2011-09-01 | 4296063 | 0.352 | ARRA562
2526 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA563 | RESURFACING SE LAKE WEIR AVENUE FROM SE 31ST STREET TO S OF SE 38TH STREET (0000.564 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2010-06-16 | 2010-07-12 | 2010-11-09 | 2010-08-31 | 152901 | 0.564 | ARRA563
2527 | FLORIDA | Completed | C220,C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA564 | PAVE SHOULDERS SR 300 FRANKLIN BLVD FROM W BAYSHORE DRIVE TO ST GEORGE ISLAND BR (0000.163 MILES) IN FRANKLIN COUNTY, FLORIDA. | Transportation Enhancements | 2010-04-28 | 2010-04-28 | 2012-06-24 | 2011-07-29 | 247925 | 0.163 | ARRA564
2528 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA565 | Resurface State Road 64 (Manatee Avenue) from 12th East to 15th Street West to improve the surface of this heavily traveled road. | Pavement Improvement | 2010-02-09 | 2010-02-09 | 2012-08-31 | 2012-05-14 | 1083242 | 1.321 | ARRA565
2529 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | LIBERTY |  | 02 | ARRA566 | SIDEWALK CR 12 SIDEWALK PHASE II 2009 ECONOMIC STIMULUS (0000.358 MILES) IN LIBERTY COUNTY, FLORIDA. | Transportation Enhancements | 2010-03-23 | 2010-03-23 | 2012-06-22 | 2011-02-17 | 67808 | 0.358 | ARRA566
2530 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 10 | ARRA567 | BIKE PATH/TRAIL NORTH BAY TRAIL (1ST ST) FROM 30TH AVE N TO 54TH AVE N IN PINELLAS COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-12 | 2010-05-12 | 2012-12-31 |  | 1026823 |  | ARRA567
2531 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA568 | RESURFACING CR490(HOMOSASSA TRL) FROM US 19 TO SR 44 (0006.184 MILES) IN CITRUS COUNTY, FLORIDA. | Pavement Improvement | 2010-05-09 | 2010-05-09 | 2010-08-09 | 2010-06-25 | 857648 | 6.184 | ARRA568
2532 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA569 | RESURFACING WISCON RD FROM SR 50 TO US 41 (0004.224 MILES) IN HERNANDO COUNTY, FLORIDA. | Pavement Improvement | 2010-05-23 | 2010-05-23 | 2010-08-15 | 2010-07-08 | 780871 | 4.224 | ARRA569
2533 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HIGHLANDS |  | 16 | ARRA570 | RESURFACING SPARTA ROAD FROM SR 66 TO ORDAY ROAD (0001.400 MILES) IN HIGHLANDS COUNTY, FLORIDA. | Pavement Improvement | 2009-09-15 | 2010-03-29 | 2012-03-23 | 2010-10-01 | 377298 | 1.400 | ARRA570
2534 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | COLLIER | NAPLES | Multiple | ARRA571 | BRIDGE REHABILITATION MOORINGLINE DRIVE AT BRIDGE #030125 (0000.001 MILES) IN COLLIER COUNTY, FLORIDA. | Pavement Improvement | 2009-07-22 | 2010-07-13 | 2012-02-24 | 2011-04-06 | 521300 | 0.001 | ARRA571
2535 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA572 | SIDEWALK DOWNTOWN OCALA BIKE/PED IMPROVEMENTS BROADWAY & SW 1ST AVE IN MARION COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-18 | 2010-06-15 | 2010-12-15 | 2010-11-15 | 225465 |  | ARRA572
2536 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA573 | RESURFACING NW/SW 27TH AVENUE FROM SW 20TH STREET TO NW OLD BLITCHTON ROAD (0001.994 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2010-06-16 | 2010-07-01 | 2010-12-28 | 2010-09-10 | 756147 | 1.994 | ARRA573
2537 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA574 | RESURFACING CR 470 FROM LAKE PANASOFKEE OUTF ALL CANAL TO SR 44 (0004.642 MILES) IN SUMTER COUNTY, FLORIDA. | Pavement Improvement | 2010-06-01 | 2010-06-15 | 2010-10-13 | 2010-11-08 | 1010963 | 4.642 | ARRA574
2538 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA575 | RESURFACING CR 476 E FROM US 301 TO SR 471 (0003.163 MILES) IN SUMTER COUNTY, FLORIDA. | Pavement Improvement | 2010-06-01 | 2010-06-15 | 2010-11-12 | 2010-09-30 | 733015 | 3.163 | ARRA575
2539 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA576 | RESURFACING SE 25TH AVENUE FROM SR 464 TO SR 40 (0001.099 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2010-08-10 | 2010-08-23 | 2011-01-19 | 2010-12-23 | 388071 | 1.099 | ARRA576
2540 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA577 | RESURFACING OLD DIXIE HWY FROM HAWTHORNE AVENUE TO RICHARD MARK DR (0001.582 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2010-08-03 | 2010-08-16 | 2010-09-25 | 2010-10-07 | 218889 | 1.582 | ARRA577
2541 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 08 | ARRA578 | RESURFACING BOGGY CREEK RD FROM CR 530 (BOGGY CREEK) TO W OF CR15 (NARCOOSEE) (0006.036 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Improvement | 2011-03-18 | 2011-03-21 | 2011-08-31 | 2011-08-22 | 890717 | 6.036 | ARRA578
2542 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA579 | RESURFACING CANOE CREEK RD FROM S OF JOE OVERSTREET RD TO S KENANSVILLE RD (0015.122 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Improvement | 2011-03-22 | 2011-04-04 | 2011-08-31 | 2011-10-26 | 1880452 | 15.122 | ARRA579
2543 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA580 | RESURFACING CR 318 FROM CR 315 INTERSECTION TO 1.75 W OF CR 315 (0001.735 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2010-07-13 | 2010-08-02 | 2010-10-31 | 2010-11-11 | 648735 | 1.735 | ARRA580
2544 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | VOLUSIA | DAYTONA BEACH | Multiple | ARRA581 | SIDEWALK SR40 MULTI-USE TRAIL (PHASE II) OLD TOMOKA RD TO BREAKAWAY TRAILS (0001.120 MILES) IN VOLUSIA COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-21 | 2010-06-14 | 2010-11-11 | 2010-09-22 | 172214 | 1.120 | ARRA581
2545 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 24 | ARRA582 | INTERSECTION IMPROVEMENT WATERFORD CHASE PARK WAY AT AVALON PARK BLVD INTERSECTION (0000.105 MILES) IN ORANGE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-11-04 | 2010-11-08 | 2011-05-06 | 2011-03-30 | 297687 | 0.105 | ARRA582
2546 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SUWANNEE |  | 02 | ARRA583 | BIKE PATH/TRAIL SR 49 (US 129) FR:WM.GUY LEMMON MEM.PARK TO SR 20 (US 27) (0002.706 MILES) IN SUWANNEE COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-25 | 2010-06-25 | 2011-02-19 | 2011-03-04 | 646143 | 2.706 | ARRA583
2547 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUWANNEE |  | 02 | ARRA584 | WIDEN/RESURFACE EXIST LANES CR 252 FROM US 129 TO CR 137 (0008.493 MILES) IN SUWANNEE COUNTY, FLORIDA. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2015-05-13 | 2011-12-15 | 3458714 | 8.493 | ARRA584
2548 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA585 | SIDEWALK OLD SPANISH TRAIL FROM LOCKEY AVE TO 3RD AVE (0001.760 MILES) IN JACKSON COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-15 | 2010-07-12 | 2011-01-08 | 2011-01-28 | 320028 | 1.760 | ARRA585
2549 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | SANTA ROSA | PENSACOLA | 01 | ARRA586 | ADD LANES & RECONSTRUCT SR 87 FROM N OF FIVE FORKS ROAD TO EGLIN AFB BOUNDARY (0003.025 MILES) IN SANTA ROSA COUNTY, FLORIDA. | Pavement Widening | 2010-07-20 | 2010-08-16 | 2020-06-23 |  | 17182109 | 3.025 | ARRA586
2550 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | BAY | PANAMA CITY | 02 | ARRA587 | RESURFACING 11TH STREET RESURFACING (0001.925 MILES) IN BAY COUNTY, FLORIDA. | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2010-12-16 | 2011-02-09 | 1000000 | 1.925 | ARRA587
2551 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA588 | RESURFACING SMITH STREET RESURFACING (0000.200 MILES) IN JACKSON COUNTY, FLORIDA. | Pavement Improvement | 2010-07-16 | 2010-07-16 | 2012-08-03 | 2011-09-08 | 78281 | 0.200 | ARRA588
2552 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | JEFFERSON |  | Multiple | ARRA589 | RESURFACING NORTH SALT ROAD PHASE II RESURFACING (0000.939 MILES) IN JEFFERSON COUNTY, FLORIDA. | Pavement Improvement | 2010-04-20 | 2010-04-20 | 2012-07-14 | 2011-02-25 | 175992 | 0.939 | ARRA589
2553 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH, FL | Multiple | ARRA590 | ADD SPECIAL USE LANE I-95/EXPRESS/HOT LNS FROM N. OF GOLDEN GLADES TO DADE/BROWARD CO LINE (0003.892 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Widening | 2010-04-23 | 2010-04-23 | 2020-04-22 |  | 17642344 | 7.260 | ARRA590
2554 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA592 | PUBLIC TRANSPORTATION SHELTER ARRA BROWARD COUNTY CNTYWDE PASNGER SHELTERS VARIOUS LOCATIONS IN BROWARD COUNTY, FLORIDA. | Other | 2010-05-19 | 2010-05-19 | 2020-05-18 |  | 2582363 |  | ARRA592
2555 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA593 | SIDEWALK WEST CASTILLO DRIVE FROM: SR 5 (US 1) TO: SR 5A/SAN MARCO AVE. (0000.277 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Transportation Enhancements | 2009-06-16 | 2009-06-16 | 2012-07-03 |  | 177230 | 0.277 | ARRA593
2556 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA594 | TRAFFIC OPS IMPROVEMENT SR 207 @ SR 312 (0000.013 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Safety/Traffic Management | 2009-06-16 | 2009-06-16 | 2016-06-16 | 2012-03-20 | 1101522 | 0.013 | ARRA594
2557 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA595 | TRAFFIC OPS IMPROVEMENT SR A1A/SR 200 @ BLACKROCK ROAD (0000.001 MILES) IN NASSAU COUNTY, FLORIDA. | Safety/Traffic Management | 2009-06-16 | 2009-06-16 | 2016-06-16 | 2012-02-22 | 773058 | 0.001 | ARRA595
2558 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 06 | ARRA596 | WIDEN/RESURFACE EXIST LANES CR 220 FROM: CR 209 TO: BLANDING BLVD. (0003.078 MILES) IN CLAY COUNTY, FLORIDA. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2016-06-16 | 2011-11-02 | 1571152 | 3.078 | ARRA596
2559 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRA597 | RESURFACING 9TH STREET FROM: OSCEOLA AVENUE TO: ST. JOHNS C/L (0000.182 MILES) IN DUVAL COUNTY, FLORIDA. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2016-06-16 | 2011-11-29 | 1094456 | 0.182 | ARRA597
2560 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA598 | RESURFACING OLD DIXIE HIGHWAY FROM: SR 312 TO: SR 207 (0000.227 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Pavement Improvement | 2010-07-23 | 2010-07-23 | 2012-08-20 |  | 352276 | 0.227 | ARRA598
2561 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA599 | SIDEWALK CR 107 BLACKROCK RD FROM: WINDSOR DRIVE TO: HERRON ISLES PKWAY (0001.611 MILES) IN NASSAU COUNTY, FLORIDA. | Transportation Enhancements | 2009-06-16 | 2009-06-16 | 2016-06-16 | 2012-03-01 | 362537 | 1.611 | ARRA599
2562 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 06 | ARRA600 | RESURFACING MOODY AVENUE FROM: DRS. LAKE ROAD TO: PE0RIA (0001.880 MILES) IN CLAY COUNTY, FLORIDA. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2012-06-05 |  | 920147 | 1.880 | ARRA600
2563 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | DUVAL | JACKSONVILLE | 06 | ARRA601 | RESURFACING CAHOON AVENUE FROM: DEVOE STREET TO: CANNON STREET (0000.297 MILES) IN DUVAL COUNTY, FLORIDA. | Pavement Improvement | 2010-05-01 | 2010-03-31 | 2012-07-09 |  | 196936 | 0.297 | ARRA601
2564 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA602 | BRIDGE-REPAIR/REHABILITATION CR 214 BRIDGE OVER I-95 (0000.044 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Bridge Improvement | 2009-06-16 | 2009-06-16 | 2012-08-20 |  | 168364 | 0.044 | ARRA602
2565 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | 03 | ARRA603 | TRAFFIC OPS IMPROVEMENT SR 224/KINGSLEY AVE. FROM: PLAINFIELD AVENUE TO: SMITH STREET (0000.438 MILES) IN CLAY COUNTY, FLORIDA. | Safety/Traffic Management | 2010-03-30 | 2010-03-30 | 2015-03-30 | 2011-11-02 | 85016 | 0.438 | ARRA603
2566 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST JOHNS | JACKSONVILLE | 07 | ARRA604 | RESURFACING CR 13B/FRUIT COVE RD FROM: SR 13 TO: SR 13 (0002.381 MILES) IN ST. JOHNS COUNTY, FLORIDA. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2016-06-16 | 2012-10-31 | 1024075 | 2.381 | ARRA604
2567 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA605 | RESURFACING LONGWOOD-LK MARY RD FROM CR 427 TO LAKE MARY BLVD (0002.597 MILES) IN SEMINOLE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-07 | 2011-02-07 | 2011-03-31 | 2011-05-27 | 992512 | 2.597 | ARRA605
2568 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BROWARD | FORT LAUDERDALE-HOLLYWOOD-POMP | 22 | ARRA606 | LANDSCAPING SE 10TH STREET FROM STATE ROAD A-1-A TO OCEAN WAY (0000.137 MILES) IN BROWARD COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-22 | 2010-06-21 | 2010-12-11 | 2011-05-27 | 358575 | 0.137 | ARRA606
2569 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA | GAINESVILLE | 06 | ARRA607 | SIDEWALK SR 121/NW 34TH ST. SR 222/NW 39TH AVE/MP5.86 TO NW 55TH BLVD /MP7.730 (0001.870 MILES) IN ALACHUA COUNTY, FLORIDA. | Transportation Enhancements | 2009-08-04 | 2009-06-15 | 2010-10-19 |  | 288450 | 1.870 | ARRA607
2570 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | OKEECHOBEE |  | 16 | ARRA608 | SIDEWALK OKEECHOBEE SIDEWALKS AT VARIOUS LOCATIONS IN OKEECHOBEE COUNTY, FLORIDA. | Transportation Enhancements | 2009-09-21 | 2010-04-14 | 2012-03-16 | 2010-11-06 | 285221 |  | ARRA608
2571 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | DE SOTO |  | 13 | ARRA609 | BRIDGE-ROUTINE MAINTENANCE CR 761 (CR 769) AT BRIDGE #040004 (0000.090 MILES) IN DESOTO COUNTY, FLORIDA. | Pavement Improvement | 2009-09-16 | 2010-05-04 | 2012-03-14 | 2011-05-20 | 389203 | 0.090 | ARRA609
2572 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA610 | SIDEWALK 4TH STREET FROM US 17 TO SCHOOL HOUSE RD IN HARDEE COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-04 | 2010-05-04 | 2010-10-26 | 2010-10-28 | 136253 |  | ARRA610
2573 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | DE SOTO |  | 13 | ARRA611 | SIDEWALK POLK STREET FROM MAGNOLIA STREET TO HICKORY STREET IN DESOTO COUNTY, FLORIDA. | Transportation Enhancements | 2010-05-04 | 2010-05-04 | 2010-10-26 | 2010-10-28 | 54483 |  | ARRA611
2574 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | GLADES |  | 16 | ARRA612 | BIKE PATH/TRAIL VANCE WHIDDEN PARK IN GLADES COUNTY, FLORIDA. | Transportation Enhancements | 2010-04-13 | 2010-04-13 | 2010-11-06 | 2010-09-30 | 257475 |  | ARRA612
2575 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA613 | ADD LANES & REHABILITATE PVMNT I-75 FROM S OF SR 82 TO S OF LUCKETT ROAD (0001.529 MILES) IN LEE COUNTY, FLORIDA. | Pavement Widening | 2005-03-16 | 2010-03-09 | 2050-03-31 |  | 8055440 | 1.529 | ARRA613
2576 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | PASCO |  | 05 | ARRA614 | SIDEWALK US 301/98 (SR35/700) FROM DADE CITY AVE TO US 98 BYPASS (0001.098 MILES) IN PASCO COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-08 | 2010-06-14 | 2011-01-04 | 2011-01-18 | 560740 | 1.098 | ARRA614
2577 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA615 | LIGHTING US 17 (SOUTHBOUND) FROM MAIN STREET TO HARDEE STREET (0000.491 MILES) IN HARDEE COUNTY, FLORIDA. | Transportation Enhancements | 2009-09-21 | 2010-04-13 | 2012-03-21 | 2011-03-15 | 285394 | 0.491 | ARRA615
2578 | FLORIDA | Completed | C220,C230 | Highway Infrastructure Investment Grant | FLORIDA | SARASOTA | SARASOTA-BRADENTON | 13 | ARRA616 | PEDESTRIAN/WILDLIFE OVERPASS LEGACY TRAIL AT US 41 (0000.100 MILES) IN SARASOTA COUNTY, FLORIDA. | Transportation Enhancements | 2010-03-30 | 2010-09-16 | 2020-03-29 | 2012-03-15 | 3015846 | 0.100 | ARRA616
2579 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | INDIAN RIVER | VERO BEACH | 15 | ARRA617 | RESURFACING OLD DIXIE HWY FROM 12TH ST. TO SR-60 (0000.988 MILES) IN INDIAN RIVER COUNTY, FLORIDA. | Pavement Improvement | 2010-09-13 | 2010-11-17 | 2011-01-25 | 2011-05-03 | 411016 | 0.988 | ARRA617
2580 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA618 | PAVE SHOULDERS BUCKINGHAM ROAD FROM NEAL ROAD TO GUNNERY ROAD (0002.401 MILES) IN LEE COUNTY, FLORIDA. | Pavement Improvement | 2010-11-08 | 2010-11-09 | 2011-03-09 | 2011-09-16 | 355477 | 2.401 | ARRA618
2581 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HENDRY |  | Multiple | ARRA619 | SIDEWALK NW/NE EUCALYPTUS BLVD FROM COWBOY WAY TO COLLINSWOOD PKWY IN HENDRY COUNTY, FLORIDA. | Transportation Enhancements | 2010-07-13 | 2010-07-13 | 2010-11-19 | 2011-01-21 | 190165 |  | ARRA619
2582 | FLORIDA | Completed | C220,C200 | Highway Infrastructure Investment Grant | FLORIDA | FRANKLIN |  | 02 | ARRA620 | SIDEWALK OAK STREET SIDEWALKS (0000.506 MILES) IN FRANKLIN COUNTY, FLORIDA. | Transportation Enhancements | 2010-04-14 | 2010-04-14 | 2012-06-24 | 2011-07-29 | 168606 | 0.506 | ARRA620
2583 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA621 | INTERSECTION IMPROVEMENT CITY OF WEST MIAMI FROM S.W. 64 AVENUE @ S.W. 15 STREET (0000.017 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-05-24 | 2010-06-02 | 2010-10-22 | 2011-03-18 | 46171 | 0.017 | ARRA621
2584 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA622 | BRIDGE REPLACEMENT CR 305 5.48 MILES SOUTH OF SR 100 (0000.258 MILES) IN FLAGLER COUNTY, FLORIDA. | Bridge Replacement | 2010-10-20 | 2010-11-08 | 2011-05-07 | 2011-03-15 | 908625 | 0.258 | ARRA622
2585 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | Multiple | ARRA623 | SIDEWALK MARION OAKS TRAIL FROM SW 63RD TERRACE TO SW 31ST AVENUE IN MARION COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-04 | 2010-06-08 | 2010-11-05 | 2010-09-09 | 241681 |  | ARRA623
2586 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | Multiple | ARRA624 | SIDEWALK COGAN DRIVE SIDEWALK FROM TORRENCE AVENUE TO BABCOCK STREET (0000.950 MILES) IN BREVARD COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-07 | 2010-06-14 | 2010-10-12 | 2010-09-12 | 71904 | 0.950 | ARRA624
2587 | FLORIDA | Completed | C250 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA625 | RESURFACING PALM COAST PARKWAY FROM OLD KINGS ROAD TO PALM HARBOR PARKWAY (0001.818 MILES) IN FLAGLER COUNTY, FLORIDA. | Pavement Improvement | 2010-05-16 | 2010-05-16 | 2010-07-15 | 2010-06-15 | 258117 | 1.818 | ARRA625
2588 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA626 | SIDEWALK BELLE TERRE PKWAY MULTI USE PATH FROM PINE GROVE TO PINE LAKES PKWY (0001.936 MILES) IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-10 | 2010-06-11 | 2010-09-21 | 2010-10-22 | 319809 | 1.936 | ARRA626
2589 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA627 | SIDEWALK NORTH LOCKWOOD BLVD FROM ASHLAND TRAIL TO CR 426 IN SEMINOLE COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-09 | 2010-06-28 | 2010-11-05 | 2010-08-26 | 180758 |  | ARRA627
2590 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA628 | RESURFACING RINEHART ROAD FROM CR 46-A TO TOWNE CENTER BLVD. (0000.796 MILES) IN SEMINOLE COUNTY, FLORIDA. | Pavement Improvement | 2010-06-18 | 2010-06-21 | 2010-09-18 | 2010-08-19 | 261601 | 0.796 | ARRA628
2591 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | CITRUS |  | 05 | ARRA629 | RESURFACING US 19 (SR 55) FROM NW SNUG HARBOR RD TO W CORNFLOWER DR (0007.476 MILES) IN CITRUS COUNTY, FLORIDA. | Pavement Improvement | 2010-06-06 | 2010-06-06 | 2011-02-20 | 2011-04-20 | 3030747 | 7.476 | ARRA629
2592 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA630 | FLEXIBLE PAVEMENT RECONSTRUCT. WEST 53RD STREET FROM WEST 16TH AVENUE TO WEST 12TH AVENUE (0000.499 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-01-10 | 2010-11-02 | 2012-06-30 | 2012-06-26 | 798964 | 0.499 | ARRA630
2593 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA631 | FLEXIBLE PAVEMENT RECONSTRUCT. WEST 36 AVENUE FROM WEST 76 STREET TO WEST 84 STREET (0000.498 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2010-12-31 | 2011-07-08 | 661394 | 0.498 | ARRA631
2594 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ESCAMBIA | PENSACOLA | 01 | ARRA632 | RESURFACING CR 292A GULF BEACH HIGHWAY RESURFACING (0006.842 MILES) IN ESCAMBIA COUNTY, FLORIDA. | Pavement Improvement | 2010-06-21 | 2010-06-21 | 2012-08-14 | 2011-09-14 | 2159731 | 6.842 | ARRA632
2595 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | WALTON | FORT WALTON BEACH | Multiple | ARRA633 | RESURFACING CR 1087 RESURFACING (0008.656 MILES) IN WALTON COUNTY, FLORIDA. | Pavement Improvement | 2011-03-01 | 2011-03-01 | 2020-06-21 |  | 1745986 | 8.656 | ARRA633
2596 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA634 | RESURFACING CR 10A HERITAGE ROAD /OLD COTTONDALE ROAD RESURFACING (0001.696 MILES) IN JACKSON COUNTY, FLORIDA. | Pavement Improvement | 2010-07-16 | 2010-07-16 | 2020-06-24 | 2011-09-07 | 326729 | 1.696 | ARRA634
2597 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA635 | PEDESTRIAN SAFETY IMPROVEMENT LAFAYETTE STREET PEDESTRIAN SAFETY PROJECT @ CSX R/R OVERPASS (0000.038 MILES) IN LEON COUNTY, FLORIDA. | Transportation Enhancements | 2010-06-24 | 2010-06-24 | 2012-07-31 |  | 1259986 | 0.038 | ARRA635
2598 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | PINELLAS | TAMPA-ST.PETERSBURG-CLEARWATER,FL | 10 | ARRA636 | INTERSECTION IMPROVEMENT US 19 (SR 55) FROM S OF MCCORMICK DR TO N OF ENTERPRISE RD (0000.957 MILES) IN PINELLAS COUNTY, FLORIDA. | Safety/Traffic Management | 2010-05-26 | 2010-06-21 | 2012-05-21 |  | 3359263 | 0.957 | ARRA636
2599 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | ALACHUA |  | 06 | ARRA637 | RESURFACING SR 200 (US 301) FROM NE 76TH PLACE TO SR 24 (0011.838 MILES) IN ALACHUA COUNTY, FLORIDA. | Pavement Improvement | 2010-06-07 | 2010-09-07 | 2011-03-27 | 2011-04-25 | 3741760 | 11.838 | ARRA637
2600 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | WEST PALM BEACH | 22 | ARRA638 | RESURFACING I-95 PAVEMENT REPAIR FROM S. OF LINTON BLVD TO THE L-30 CANAL BRIDGE (0003.876 MILES) IN PALM BEACH COUNTY, FLORIDA. | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2012-07-06 | 2011-06-05 | 2830580 | 3.876 | ARRA638
2601 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | MONROE |  | 18 | ARRA639 | RESURFACING SR 5/OVERSEAS HWY. FM N OF 37 ST./MM49.1 TO N OF COCOPLUM DR./MM 54.6 (0005.452 MILES) IN MONROE COUNTY, FLORIDA. | Pavement Improvement | 2010-06-24 | 2011-01-10 | 2011-06-08 | 2012-03-28 | 676933 | 5.452 | ARRA639
2602 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA640 | RESURFACING BUMBY AVENUE FROM SR15 (SOUTH ST) TO SR 50 (COLONIAL DR) (0000.508 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2010-09-28 | 2010-10-04 | 2011-05-02 | 2011-04-04 | 949354 | 0.508 | ARRA640
2603 | FLORIDA | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA641 | TRAFFIC CONTROL DEVICES/SYSTEM SR 500 US 192 FROM I-95 SB RAMPS TO E OF WICKHAM/MINTON RD IN BREVARD COUNTY, FLORIDA. | Safety/Traffic Management | 2011-07-11 | 2011-07-11 | 2012-07-31 |  | 762730 |  | ARRA641
2604 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 24 | ARRA642 | TRAFFIC OPS IMPROVEMENT MITCHELL HAMMOCK RD AT MANIGAN, EASTBRIDGE AND SHARON (0000.292 MILES) IN SEMINOLE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-09-10 | 2010-10-04 | 2011-02-01 | 2011-01-20 | 177023 | 0.292 | ARRA642
2605 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA643 | RESURFACING MURRELL ROAD FROM S OF LUTHER DRIVE TO BARTON BLVD (0000.384 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-02 | 2010-09-02 | 2010-11-02 | 2011-02-08 | 51495 | 0.384 | ARRA643
2606 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA644 | RESURFACING DESOTO PARKWAY FROM .17 MI E OF SR 513 TO 100' E OF TEMPLE ST (0000.504 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-01 | 2010-09-07 | 2010-12-06 | 2010-11-06 | 72330 | 0.504 | ARRA644
2607 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA645 | RESURFACING HOPKINS AVENUE FROM COUNTY CLUB DRIVE TO HARRISON STREET (0000.535 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-01 | 2010-09-01 | 2010-11-29 | 2011-02-17 | 100865 | 0.535 | ARRA645
2608 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 24 | ARRA646 | RESURFACING HARRISON STREET FROM FEC RAILROAD TO US 1 (0000.312 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-01 | 2010-09-01 | 2010-11-29 | 2011-02-17 | 59267 | 0.312 | ARRA646
2609 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 24 | ARRA647 | TRAFFIC SIGNAL UPDATE KELLER ROAD AT WESTHALL LANE (0000.001 MILES) IN ORANGE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-08-05 | 2010-08-06 | 2011-02-11 | 2011-01-19 | 176029 | 0.001 | ARRA647
2610 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA648 | BRIDGE REHABILITATION BOGGY CREEK RD BRIDGE IMPROVEMENT PHASE1 BRIDGE # 754120 (0000.034 MILES) IN ORANGE COUNTY, FLORIDA. | Bridge Improvement | 2011-05-03 | 2011-05-03 | 2011-06-30 | 2012-01-26 | 1232694 | 0.034 | ARRA648
2611 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | Multiple | ARRA649 | TRAFFIC CONTROL DEVICES/SYSTEM SR 551 (GOLDENROD) & EDGEWATER DR TRAFFIC CON TROL SYSTEM (2 LOCATIONS) (0002.998 MILES) IN ORANGE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-01-21 | 2011-01-24 | 2011-12-31 | 2011-05-20 | 213226 | 2.998 | ARRA649
2612 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA650 | RESURFACING ELLIS ROAD FROM JOHN RODES BLVD TO WEST OF WICKHAM RD (0000.660 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-02 | 2010-09-02 | 2010-11-02 | 2010-11-02 | 307252 | 0.660 | ARRA650
2613 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA651 | TRAFFIC SIGNALS BOGGY CREEK ROAD AT TURNBERRY BOULEVARD INTERSECTION (0000.001 MILES) IN OSCEOLA COUNTY, FLORIDA. | Safety/Traffic Management | 2010-08-25 | 2010-08-26 | 2010-03-13 | 2011-03-13 | 196528 | 0.001 | ARRA651
2614 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA652 | ADD TURN LANE(S) OSCEOLA PARKWAY ORANGE AVENUE / CR 527 (0000.001 MILES) IN OSCEOLA COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-22 | 2011-03-28 | 2010-12-31 | 2011-07-25 | 317316 | 0.001 | ARRA652
2615 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA653 | RESURFACING SYKES CREEK PKWY FROM SR 520 TO MERRITT AVE (0000.291 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-09-02 | 2010-09-02 | 2011-01-10 | 2010-12-27 | 227862 | 0.291 | ARRA653
2616 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA654 | RESURFACING APOLLO BLVD FROM AIRPORT BLVD TO SARNO RD (0001.818 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-08-19 | 2010-08-29 | 2011-01-10 | 2010-12-31 | 440725 | 1.818 | ARRA654
2617 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA655 | RESURFACING LAKE WASHINGTON ROAD FROM WICKHAM ROAD TO CROTON ROAD (0001.019 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2010-08-26 | 2010-08-30 | 2010-12-28 | 2010-12-08 | 463362 | 1.019 | ARRA655
2618 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA656 | RESURFACING CONROY-WINDERMERE RD FROM MAIN STREET TO HORIZON CIRCLE (0001.377 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2010-08-02 | 2010-08-02 | 2010-10-30 | 2010-10-01 | 280858 | 1.377 | ARRA656
2619 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA657 | RESURFACING AYERS RD FROM US 41 TO CR 581 (CULBREATH RD) (0004.961 MILES) IN HERNANDO COUNTY, FLORIDA. | Pavement Improvement | 2010-11-29 | 2010-11-29 | 2010-12-10 | 2011-02-27 | 862027 | 4.961 | ARRA657
2620 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MARTIN | FORT PIERCE-STUART | 16 | ARRA658 | SIDEWALK SE COMMERCE AVENUE FROM INDIAN STREET TO MONROE STREET (0001.130 MILES) IN MARTIN COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-07 | 2011-02-07 | 2011-12-31 | 2011-05-20 | 79677 | 1.130 | ARRA658
2621 | FLORIDA | Completed | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | SUMTER |  | 05 | ARRA659 | RESURFACING CR 476B FROM I-75 RAMPS TO CR 476 (0000.321 MILES) IN SUMTER COUNTY, FLORIDA. | Pavement Improvement | 2010-08-31 | 2010-09-14 | 2011-01-31 | 2011-02-01 | 718577 | 0.321 | ARRA659
2622 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA661 | SIDEWALK BELLE TERRE TRAIL SIDEWALKS 2 LOCATIONS IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2010-10-26 | 2010-11-01 | 2011-04-30 | 2011-09-01 | 959797 |  | ARRA661
2623 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA662 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMSN. DIST 1 & 2 - ADA BUS STOP ACCESS (VARIOUS LOCATION) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-11 | 2011-04-25 | 2012-07-31 |  | 522000 |  | ARRA662
2624 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 20 | ARRA663 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMMSN DISTRICT 8 & 12 - ADA BUS STOP ACCESS(VARIOUS LOCS) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-04 | 2011-04-12 | 2012-05-31 |  | 354143 |  | ARRA663
2625 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA664 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 1, 2 & 6 PED SIGNAL LED UPGRADE - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-04 | 2011-04-04 | 2012-02-28 | 2011-11-15 | 218828 |  | ARRA664
2626 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA665 | RESURFACING MIAMI-DADE CO COMMSN DISTRICT 11 - RESURFACING AT VARIOUS LOCATIONS IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-03-21 | 2011-03-21 | 2012-05-31 | 2012-07-23 | 728645 |  | ARRA665
2627 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA666 | RESURFACING N.W. 67 AVENUE FROM NW 188 TERR. TO NW 202 ST (MIAMI-DADE CMSN DIST 13) (0000.883 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-03-21 | 2010-08-31 | 2012-05-31 |  | 293593 | 0.883 | ARRA666
2628 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA667 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMMSN DISTRICT 9 - ADA BUS STOP ACCESS(VARIOUS LOCATIONS) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-14 | 2011-03-28 | 2012-05-31 | 2012-07-12 | 481582 |  | ARRA667
2629 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA668 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMMSN DISTRICT 10-ADA BUS STOP ACCESS(VARIOUS LOCATIONS) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-16 | 2011-03-28 | 2012-07-31 |  | 588663 |  | ARRA668
2630 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA669 | PEDESTRIAN SAFETY IMPROVEMENT MIAMI-DADE CO COMMSN DISTRICT 11-ADA BUS STOP ACCESS(VARIOUS LOCATIONS) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-28 | 2011-04-04 | 2012-05-31 | 2012-05-29 | 307117 |  | ARRA669
2631 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA670 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMS DIST 7, 9 & 11 PED SIGNAL LED UPGRADE - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-14 | 2011-03-17 | 2012-02-28 | 2011-08-22 | 115341 |  | ARRA670
2632 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA671 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMS DIST 8, & 10 PED SIGNAL LED UPGRADE - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2010-08-31 | 2010-08-31 | 2012-02-28 | 2012-02-10 | 149671 |  | ARRA671
2633 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA672 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DISTRICT 11 - PAVEMENT MARKINGS @ VAR LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-21 | 2011-03-21 | 2012-05-31 | 2012-07-23 | 23507 |  | ARRA672
2634 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 25 | ARRA673 | DRAINAGE IMPROVEMENTS S.W. 137 AVENUE FROM SW 72 ST. TO SW 56 ST. (MIAMI-DADE CMSN DIST 10) (0001.003 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-28 | 2011-02-28 | 2012-05-31 | 2012-08-03 | 491876 | 1.003 | ARRA673
2635 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA674 | BRIDGE REPLACEMENT N.W. 42 AVENUE AT NW 179 STREET (BRIDGE # 874023) (0000.017 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Bridge Replacement | 2010-10-19 | 2010-10-19 | 2012-07-09 |  | 667291 | 0.017 | ARRA674
2636 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA675 | FLEXIBLE PAVEMENT RECONSTRUCT. N.E. 2 AVENUE FROM N.E. 51 STREET TO N.E. 57 STREET (0000.171 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2011-04-29 | 2011-05-23 | 2012-07-31 |  | 2220578 | 0.171 | ARRA675
2637 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | Multiple | ARRA676 | RESURFACING SUNRISE & OLEANDER FROM OHIO STREET TO VIRGINIA AVENUE (0000.523 MILES) IN ST. LUCIE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2019-08-02 |  | 325601 | 0.523 | ARRA676
2638 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | Multiple | ARRA677 | RESURFACING 29TH STREET FROM ORANGE AVENUE TO AVENUE Q (0001.250 MILES) IN ST. LUCIE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2019-08-02 |  | 323488 | 1.250 | ARRA677
2639 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | PALM BEACH | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 22 | ARRA678 | RESURFACING SR5/US1/FEDERAL HWY FROM BROWARD/PALM BCH C/L TO SE 5TH STREET (0002.868 MILES) IN PALM BEACH COUNTY, FLORIDA. | Pavement Improvement | 2011-01-03 | 2011-04-25 | 2011-03-28 | 2011-10-10 | 1004406 | 2.868 | ARRA678
2640 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO | SPRING HILL | 05 | ARRA679 | BIKE PATH/TRAIL TOM VARN PARK FROM JB COMMUNITY CENTER TO MCKETHAN PARK IN HERNANDO COUNTY, FLORIDA. | Transportation Enhancements | 2011-05-02 | 2011-05-02 | 2012-12-31 | 2011-12-08 | 110966 |  | ARRA679
2641 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA680 | SIDEWALK SR A1A NAT'L SCENIC BYWAY, BING'S LANDING CORRIDOR ENHANCEMENTS IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2011-03-30 | 2011-04-04 | 2012-03-31 | 2011-09-30 | 149735 |  | ARRA680
2642 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA681 | SIDEWALK WHITEVIEW TRAIL PINE LAKES TO RAVENWOOD & BELLE TERRE TO PINE GRV IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-24 | 2011-03-07 | 2011-07-31 | 2011-09-07 | 609925 |  | ARRA681
2643 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA682 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 1,2,3,& 4 ILLUMINATE ST. NAME SIGNS-VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-21 | 2011-03-21 | 2012-02-28 | 2012-01-26 | 349557 |  | ARRA682
2644 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA683 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 6 & 7 ILLUMINATED ST NAME SIGNS - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-03-28 | 2011-03-28 | 2012-02-28 | 2011-11-14 | 180128 |  | ARRA683
2645 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA684 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 8 & 9 ILLUMINATED ST NAME SIGNS - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-11 | 2011-04-12 | 2012-02-28 | 2011-11-14 | 321460 |  | ARRA684
2646 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | Multiple | ARRA685 | SIGNING/PAVEMENT MARKINGS MIAMI-DADE CO COMMSN DIST 10,11 & 12 ILLUM ST. NAME SIGNS - VAR. LOC'S IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-04-25 | 2011-04-25 | 2012-02-28 | 2011-11-14 | 119616 |  | ARRA685
2647 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | Multiple | ARRA686 | RESURFACING SLEEPY HOLLOW ROAD FROM SUNNYSIDE DRIVE TO S OF US 441 (0000.660 MILES) IN LAKE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-25 | 2011-03-10 | 2011-07-31 | 2011-05-24 | 114549 | 0.660 | ARRA686
2648 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA687 | RESURFACING PHELPS AVENUE FROM LOCHBERRY ROAD TO ALOMA AVENUE (0000.511 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2011-05-16 | 2011-05-16 | 2011-12-31 | 2011-07-09 | 69961 | 0.511 | ARRA687
2649 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 08 | ARRA688 | RESURFACING DYER BOULEVARD FROM US 192 TO COLUMBIA AVENUE (0000.249 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Improvement | 2010-12-29 | 2011-01-04 | 2011-09-30 | 2011-03-04 | 84131 | 0.249 | ARRA688
2650 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 17 | ARRA689 | LIGHTING SR 5/BISCAYNE BLVD. FROM OLETA RIVER TO NE 214 STREET (0000.600 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-10-13 | 2012-01-02 | 2012-06-30 | 2012-04-30 | 247256 | 0.600 | ARRA689
2651 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA690 | BRIDGE REPLACEMENT ORANGE BLVD BRIDGE #774059 (0000.010 MILES) IN SEMINOLE COUNTY, FLORIDA. | Bridge Replacement | 2011-03-09 | 2011-03-14 | 2011-03-31 | 2011-06-06 | 696603 | 0.010 | ARRA690
2652 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 18 | ARRA691 | INTERSECTION IMPROVEMENT SW 64TH AVE/W. MIAMI FROM SW 20TH STREET TO SW 8TH ST/WEST MIAMI (0000.773 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Safety/Traffic Management | 2011-02-18 | 2011-02-21 | 2011-10-30 | 2011-05-17 | 30582 | 0.773 | ARRA691
2653 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA692 | RESURFACING CR 318 FROM NE 52ND CT TO 1.75 MI W OF CR 315 (0007.670 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2011-01-26 | 2011-01-31 | 2011-07-31 | 2011-08-04 | 2859714 | 7.670 | ARRA692
2654 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA693 | RESURFACING CR 200A FROM NE 100TH STREET TO US 301 (0007.223 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2011-01-26 | 2011-02-21 | 2011-07-31 | 2011-06-21 | 2534658 | 7.223 | ARRA693
2655 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | MARION | OCALA | 06 | ARRA694 | RESURFACING NE 25TH AVENUE FROM SR 40 TO NE 14TH STREET (0000.933 MILES) IN MARION COUNTY, FLORIDA. | Pavement Improvement | 2011-01-13 | 2011-01-24 | 2011-03-31 | 2011-04-23 | 323096 | 0.933 | ARRA694
2656 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | BREVARD | MELBOURNE-COCOA | 15 | ARRA695 | RESURFACING EMERSON DRIVE NW FROM JUPITER BLVD. TO MINTON ROAD (0004.415 MILES) IN BREVARD COUNTY, FLORIDA. | Pavement Improvement | 2011-01-04 | 2011-01-05 | 2011-07-31 | 2011-03-06 | 594577 | 4.415 | ARRA695
2657 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 05 | ARRA696 | RESURFACING CR 48 FROM SUMTER COUNTY LINE TO CR 33 (0005.555 MILES) IN LAKE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-25 | 2011-03-10 | 2011-05-31 | 2011-05-24 | 1523870 | 5.555 | ARRA696
2658 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 05 | ARRA697 | RESURFACING CR 452 FROM 0.1 MI N OF CR 44 TO 1.53 MI N OF CR 44 (0001.053 MILES) IN LAKE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-25 | 2011-03-17 | 2011-05-31 | 2011-06-15 | 400886 | 1.053 | ARRA697
2659 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | Multiple | ARRA698 | RESURFACING CR 44 FROM W OF N SILVERLAKE RD TO POE STREET (0002.207 MILES) IN LAKE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-25 | 2011-03-31 | 2011-05-31 | 2011-06-14 | 316908 | 2.207 | ARRA698
2660 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | LAKE | LEESBURG-EUSTIS | 05 | ARRA699 | BRIDGE REPLACEMENT LAKESHORE DRIVE FROM OSPREY POINTE BLVD TO SOUTH CLERMONT CONNECT (0003.585 MILES) IN LAKE COUNTY, FLORIDA. | Bridge Replacement | 2011-03-09 | 2011-03-24 | 2012-08-31 |  | 2412171 | 3.585 | ARRA699
2661 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | ORLANDO | 15 | ARRA700 | RESURFACING PLEASANT HILL ROAD FROM 17/92 TO REEDY CREEK BRIDGE N OF CYPRESS PKWY (0007.756 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Improvement | 2011-03-22 | 2011-04-04 | 2011-08-31 | 2011-11-09 | 2153198 | 7.756 | ARRA700
2662 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | ORANGE | ORLANDO | 08 | ARRA701 | RESURFACING LAKEMONT AVENUE FROM ALOMA AVENUE TO PINE AVENUE (0000.748 MILES) IN ORANGE COUNTY, FLORIDA. | Pavement Improvement | 2011-03-11 | 2011-03-11 | 2011-03-31 | 2011-06-01 | 202373 | 0.748 | ARRA701
2663 | FLORIDA | Completed | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 24 | ARRA702 | SIDEWALK CROSS SEMINOLE TRAIL PEDESTRIAN OVERPASS AT RED BUG AND SR 426 IN SEMINOLE COUNTY, FLORIDA. | Transportation Enhancements | 2011-05-24 | 2011-05-24 | 2012-08-31 | 2011-11-07 | 3373771 |  | ARRA702
2664 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | Multiple | ARRA703 | RESURFACING NORTH WINTER PARK DR FROM RED BUG LAKE RD TO 7TH ST SOUTH (0002.863 MILES) IN SEMINOLE COUNTY, FLORIDA. | Pavement Improvement | 2011-04-04 | 2011-04-04 | 2012-08-31 |  | 1755370 | 2.863 | ARRA703
2665 | FLORIDA | Underway | C240 | Highway Infrastructure Investment Grant | FLORIDA | OSCEOLA | KISSIMMEE | 15 | ARRA704 | ADD LANES & RECONSTRUCT HOAGLAND BLVD FROM 5TH STREET TO US 192 (0001.100 MILES) IN OSCEOLA COUNTY, FLORIDA. | Pavement Widening | 2011-04-28 | 2011-04-28 | 2012-06-30 |  | 4500000 | 1.100 | ARRA704
2666 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | ST LUCIE | FORT PIERCE-STUART | 16 | ARRA705 | RESURFACING PORT ST. LUCIE BLVD. FROM SW GRECO LANE TO SW SANSOM LANE (0000.138 MILES) IN ST. LUCIE COUNTY, FLORIDA. | Pavement Improvement | 2009-12-31 | 2010-01-02 | 2019-12-30 | 2012-03-01 | 520062 | 0.138 | ARRA705
2667 | FLORIDA | Underway | C200 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA706 | BRIDGE REPLACEMENT STYLES CREEK BRIDGE ON PRINCESS PLACE RD REPLACE #734090 (0000.016 MILES) IN FLAGLER COUNTY, FLORIDA. | Bridge Replacement | 2011-09-19 | 2011-09-19 | 2012-10-31 |  | 560895 | 0.016 | ARRA706
2668 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEE | FORT MYERS-CAPE | 14 | ARRA707 | BRIDGE REHABILITATION SR 865 (SAN CARLOS BLVD) FROM ESTERO BLVD TO MAIN STREET (0000.643 MILES) IN LEE COUNTY, FLORIDA. | Pavement Improvement | 2011-02-23 | 2011-02-23 | 2015-05-17 |  | 569718 | 0.643 | ARRA707
2669 | FLORIDA | Underway | C220,C200 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA708 | SIDEWALK SR 166 CAVERNS RD FROM MARIANNA HIGH SCHOOL TO RUSSELL ROAD (0000.896 MILES) IN JACKSON COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-22 | 2011-02-22 | 2021-01-17 |  | 128738 | 0.896 | ARRA708
2670 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | HOLMES |  | 01 | ARRA709 | SIDEWALK CR 179A & CR 181 FROM NORTH RAILROAD ST TO FERN ARNOLD PARK (0000.429 MILES) IN HOLMES COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-22 | 2011-02-22 | 2021-01-17 |  | 94393 | 0.429 | ARRA709
2671 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | JACKSON |  | 02 | ARRA710 | PAVE SHOULDERS LEGION ROAD FROM SR 10 (US 90) TO WEST OF PARK ENTRANCE (0001.214 MILES) IN JACKSON COUNTY, FLORIDA. | Transportation Enhancements | 2011-02-22 | 2011-02-22 | 2021-01-17 |  | 184792 | 1.214 | ARRA710
2672 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA711 | SIDEWALK CR 278 PIONEER ROAD FROM SR 77 WASHINGTON ST TO ROGERS REC COMPLEX (0000.634 MILES) IN WASHINGTON COUNTY, FLORIDA. | Transportation Enhancements | 2010-12-07 | 2010-12-07 | 2020-11-18 |  | 111741 | 0.634 | ARRA711
2673 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA712 | SIDEWALK CR 279 MOSS HILL RD FROM VERNON HIGH SCHOOL TO SR 79 MAIN STREET (0001.601 MILES) IN WASHINGTON COUNTY, FLORIDA. | Transportation Enhancements | 2010-12-07 | 2010-12-07 | 2020-11-18 |  | 200696 | 1.601 | ARRA712
2674 | FLORIDA | Underway | C250,C200 | Highway Infrastructure Investment Grant | FLORIDA | WASHINGTON |  | 01 | ARRA713 | DRAINAGE IMPROVEMENTS CR 273 ORANGE HILL FROM S OF GILBERT MILL RD TO SR 277 VERNON HWY (0012.743 MILES) IN WASHINGTON COUNTY, FLORIDA. | Pavement Improvement | 2010-12-07 | 2010-12-07 | 2020-11-18 |  | 1376388 | 12.743 | ARRA713
2675 | FLORIDA | Underway | C240,C230 | Highway Infrastructure Investment Grant | FLORIDA | SANTA ROSA | PENSACOLA | 01 | ARRA714 | ADD LANES & RECONSTRUCT SR 281 AVALON BLVD FROM SR 8 (I-10) TO S OF MOOR'S LODGE (0000.905 MILES) IN SANTA ROSA COUNTY, FLORIDA. | Pavement Widening | 2011-02-07 | 2011-02-07 | 2021-02-06 |  | 4045090 | 0.905 | ARRA714
2676 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MIAMI-DADE | MIAMI-HIALEAH-FT.LAUD-HOL-WPALM | 21 | ARRA715 | RESURFACING WEST 29TH STREET FROM SR 25/OKEECHOBEE RD. TO WEST 4TH AVENUE (0001.488 MILES) IN MIAMI-DADE COUNTY, FLORIDA. | Pavement Improvement | 2010-02-08 | 2010-03-02 | 2010-12-01 |  | 322084 | 1.488 | ARRA715
2677 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | SEMINOLE | ORLANDO | 07 | ARRA716 | RESURFACING LAKE MARY BOULEVARD FROM RINEHART ROAD TO COUNTRY CLUB ROAD (0001.524 MILES) IN SEMINOLE COUNTY, FLORIDA. | Pavement Improvement | 2011-01-28 | 2011-01-30 | 2011-02-28 | 2011-03-16 | 957405 | 1.524 | ARRA716
2678 | FLORIDA | Underway | C220 | Highway Infrastructure Investment Grant | FLORIDA | FLAGLER |  | 07 | ARRA717 | SIDEWALK PALM HARBOR TRAIL FROM HAMMOCK DUNES BRIDGE TO FERNMILL LANE IN FLAGLER COUNTY, FLORIDA. | Transportation Enhancements | 2011-09-26 | 2011-10-11 | 2011-09-30 |  | 1122013 |  | ARRA717
2679 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | LEON | TALLAHASSEE | Multiple | ARRA718 | RESURFACING SR 61 (US 27) MONROE FROM PERKINS STREET TO SR 61 THOMASVILLE ROAD (0001.387 MILES) IN LEON COUNTY, FLORIDA. | Pavement Improvement | 2011-01-22 | 2011-02-08 | 2011-08-03 | 2011-12-02 | 849971 | 1.387 | ARRA718
2680 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | CLAY | JACKSONVILLE | Multiple | ARRA719 | SIDEWALK CR 224A/DRS. LAKE DR FROM: BIRDWOOD DRIVE TO: SR 224/KINGSLEY AVE (0000.368 MILES) IN CLAY COUNTY, FLORIDA. | Transportation Enhancements | 2010-03-30 | 2010-03-30 | 2015-05-13 | 2012-02-22 | 164204 | 0.368 | ARRA719
2681 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | NASSAU | JACKSONVILLE | 04 | ARRA720 | RESURFACING CR 200A/PAGES DAIRY FR: SR 15(US 17) TO: FELMORE ROAD (0001.235 MILES) IN NASSAU COUNTY, FLORIDA. | Pavement Improvement | 2010-05-01 | 2010-03-31 | 2015-05-13 | 2012-01-18 | 781176 | 1.235 | ARRA720
2682 | FLORIDA | Completed | C220 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA721 | BIKE PATH/TRAIL GOOD NEIGHBOR TRAIL PHASE IIA FROM JASMINE DR TO MONDON HILL RD IN HERNANDO COUNTY, FLORIDA. | Transportation Enhancements | 2011-04-01 | 2011-04-04 | 2012-12-31 | 2011-07-07 | 206626 |  | ARRA721
2683 | FLORIDA | Underway | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA722 | RESURFACING CR 675 (RUTLAND RD) FROM US 301 TO SR 64 (0011.136 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-28 | 2011-02-24 | 2019-08-27 |  | 1697656 | 11.136 | ARRA722
2684 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA723 | RESURFACING 34TH STREET WEST FROM 53RD AVENUE WEST TO SR 684 (CORTEZ ROAD) (0000.482 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-28 | 2011-04-13 | 2019-08-27 | 2011-11-18 | 585203 | 0.482 | ARRA723
2685 | FLORIDA | Completed | C230 | Highway Infrastructure Investment Grant | FLORIDA | MANATEE | SARASOTA-BRADENTON | Multiple | ARRA724 | RESURFACING 43RD STREET WEST FROM SR 684 (CORTEZ RD) TO SR 64 (MANATEE AVE) (0001.707 MILES) IN MANATEE COUNTY, FLORIDA. | Pavement Improvement | 2009-08-28 | 2011-04-13 | 2019-08-27 | 2011-12-23 | 413760 | 1.707 | ARRA724
2686 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HARDEE |  | 13 | ARRA725 | FLEXIBLE PAVEMENT RECONSTRUCT. CR 663 FROM SR 62 TO POLK COUNTY LINE (0003.579 MILES) IN HARDEE COUNTY, FLORIDA. | Pavement Improvement | 2011-03-03 | 2011-03-03 | 2012-09-13 | 2011-10-01 | 1737473 | 3.579 | ARRA725
2687 | FLORIDA | Completed | C200 | Highway Infrastructure Investment Grant | FLORIDA | HERNANDO |  | 05 | ARRA726 | ADD LANES & REHABILITATE PVMNT SR 50 (CORTEZ BLVD) FROM US 19 (SR 55) TO CR587/W OF MARINER BVD (0003.855 MILES) IN HERNANDO COUNTY, FLORIDA. | Other | 2011-01-24 | 2011-02-02 | 2011-06-28 | 2011-06-28 | 274702 | 3.855 | ARRA726
2688 | FLORIDA | Completed | C950 | Ferryboat | FLORIDA | DUVAL | JACKSONVILLE | 04 | ARRF001 | SEAPORT PRESERVATION PROJECT JACKSONVILLE MAYPORT FERRY TERMINAL IMPROVE. ARRA FUNDING IN DUVAL COUNTY, FLORIDA. | Other | 2009-11-20 | 2009-11-20 | 2012-01-11 | 2011-04-05 | 658041 |  | ARRF001
2689 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 03 | 0000099 | This is an enhancement project in Muscogee County. The project construction consists of the construction of a 10 to 12 foot multi use trail beginning at Columbus State University and extending northe | Transportation Enhancements | 2009-09-23 | 2009-09-28 | 2011-05-15 |  | 663681 | 12.000 | 0000099
2690 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LANIER |  | 01 | 0000310 | This is a safety improvment project in Lanier County on SR 11/US 129. The project will realign on new location SR 11/US 129 and SR 31, 122/ US 221 to create two 90 degree intersections with SR 37 to | Pavement Widening | 2009-07-27 | 2009-08-03 | 2010-06-30 | 2010-07-27 | 1983740.28 | 1.050 | 0000310
2691 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | 0000424 | This project consists of reconstructing the existing intersection of SR 5 and Rose Avenue, located just north of I-20 in Douglas County. The existing intersection has an undesirable scissor-type confi | Safety/Traffic Management | 2009-07-27 | 2009-08-18 | 2011-02-28 | 2011-04-07 | 2604885.64 | 0.200 | 0000424
2692 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 05 | 0000608 | This project is a safety project in Atlanta in DeKalb County. The project will provide continuous ADA accessible sidewalks along both sides of Memorial Drive (S.R. 154) between Moreland Avenue and Ca | Transportation Enhancements | 2011-07-11 | 2012-01-06 | 2012-06-01 | 2012-06-20 | 713600 | 1.010 | 0000608
2693 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | GORDON |  | 09 | 0000683 | This project is a bridge replacement project is Gordon and Murray counties. The bridge is located on County Road 134/County Line Road over Polecat Creek on the Gordon and Murray county line. Also, t | Bridge Replacement | 2009-07-27 | 2009-09-17 | 2013-05-31 | 2010-10-22 | 1482416 | 0.610 | 0000683
2694 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 08 | 0000842 | This project is an intersection improvement project in Newton County. This project will widen SR 162/Salem Road 6 ft. symmetrically to provide a north bound left turn lane. In addition, County Road | Safety/Traffic Management | 2009-11-03 | 2009-11-17 | 2010-12-31 | 2010-08-20 | 820632.7 | 0.320 | 0000842
2695 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MILLER |  | 02 | 0001361 | This project is a bridge replacement project in Miller County. The construction proposes to construct a new 160' x 44' concrete bridge on SR 91 over Dry Creek at the existing bridge site. The roadway | Bridge Replacement | 2009-10-23 | 2009-11-05 | 2010-11-30 | 2010-12-10 | 1956969.84 | 0.320 | 0001361
2696 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TATTNALL |  | 12 | 0001364 | This project is a bridge replacement on S.R. 56/Nail Bridge @ the Ohoopee River, 2 miles west of Reidsville in Tattnall County. The project length is 0.41 miles. | Bridge Replacement | 2009-07-28 | 2009-08-31 | 2010-09-30 | 2010-09-30 | 2831014.42 | 0.410 | 0001364
2697 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CLAY |  | 02 | 0001369 | This project will replace the structurally deficient bridge in Clay County on County Road 76 over Drag Nasty Creek with a new 180' x 28' reinforced concrete bridge. The existing approaches consist of | Bridge Replacement | 2009-07-06 | 2009-07-31 | 2010-09-30 | 2010-08-15 | 1206753.14 | 0.320 | 0001369
2698 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | GLYNN | BRUNSWICK | 01 | 0001558 | This project is the construction of safety turn lanes on SR 520 in Brantley and Glynn Counties. The project begins just west of the Brantley/Glynn County Line at its intersection with County Road 580 | Safety/Traffic Management | 2009-11-23 | 2010-04-23 | 2010-12-31 | 2011-02-11 | 4775607.92 | 11.410 | 0001558
2699 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | DOUGHERTY | ALBANY | 02 | 0001562 | This project is a safety improvement project in Dougherty County. This project consists of median opening improvements on SR 300/US 19 from the Mitchell County line to the Worth County line. At 25 l | Safety/Traffic Management | 2010-02-03 | 2010-05-13 | 2011-09-30 | 2011-08-23 | 7998375.83 | 18.230 | 0001562
2700 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BARTOW | ATLANTA | 11 | 0001574 | "This project is a safety improvement located on SR 3/US 41 in Bartow County. The project begins approximately at the Cobb/Bartow County line and extends north to the SR 293 Connector in Bartow Count | Safety/Traffic Management | 2009-08-18 | 2009-09-16 | 2011-05-31 | 2011-05-31 | 11263039.7 | 15.150 | 0001574
2701 | GEORGIA | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | FLOYD | ROME | 11 | 0001575 | This project is a safety improvement that will construct turn lanes on SR 53 in Floyd County. The project will construct left and right turn lanes at fifteen intersections and four median crossovers | Safety/Traffic Management | 2009-11-30 | 2009-12-01 | 2011-09-30 |  | 7015514.31 | 9.930 | 0001575
2702 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0001794 | This project is a road widening in Richmond County. The project consists of the widening and reconstruction of Alexander Drive from Washington Road (SR 28) to Riverwatch Parkway (SR 104) in the City | Pavement Widening | 2010-01-12 | 2010-03-12 | 2012-12-31 |  | 8115912.6 | 0.870 | 0001794
2703 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | UNION |  | 09 | 0001918 | This project is a safety intersection improvement in Union County. SR 11/US 129 in Union County is a rural arterial route that currently consists of one southbound lane and one northbound lane. This | Safety/Traffic Management | 2010-03-23 | 2010-06-03 | 2011-09-30 | 2011-09-15 | 1937353.38 | 0.600 | 0001918
2704 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0002406 | This is a sidewalk construction project in Dekalb County. This project includes construction of sidewalks on both sides of SR 12/US 278/Covington Highway from SR 154/Memorial Drive to County Road 518 | Transportation Enhancements | 2009-07-27 | 2009-08-25 | 2010-08-31 | 2010-08-17 | 886822.43 | 1.580 | 0002406
2705 | GEORGIA | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0002487 | This is a lighting project in the City of Macon in Bibb County, Georgia. This project installs 13 High Mast Lighting Towers & 6 wall-mounted luminaries for underpass lighting at the existing I-75 at | New Construction | 2011-04-13 |  | 2014-03-31 |  | 394450 |  | 0002487
2706 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 13 | 0002638 | This project is a roadway widening project in Henry County. The project is located on Eagle's Landing Parkway, 0.4 miles east of the I-75 interchange in Henry County. This project will continue the | Pavement Widening | 2009-08-31 | 2009-09-29 | 2012-02-27 | 2012-02-27 | 23370448.45 | 2.600 | 0002638
2707 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CANDLER |  | 12 | 0002734 | This is a bridge replacement project in Candler County. The project is a bridge replacement on County Road 203/Glisson Road at Wolfe Creek. The existing bridge was constructed in 1955 and is structu | Bridge Replacement | 2009-08-26 | 2009-11-18 | 2011-09-30 | 2010-12-21 | 1208746.26 | 0.490 | 0002734
2708 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CANDLER |  | 12 | 0002841 | This project is a bridge replacement in Candler County. The project will replace the bridge on County Road 223/Portal Highway at Little Stocking Head Creek, 5 miles north of Metter. The existing bri | Bridge Replacement | 2009-07-28 | 2009-09-21 | 2010-12-31 | 2010-12-31 | 968761.6 | 0.350 | 0002841
2709 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CANDLER |  | 12 | 0002842 | This project will replace two bridges in Bulloch and Candler counties. The project will replace the bridge on County Road 223/Portal Highway at Big Branch and the bridge on County Road 223/Portal Hig | Bridge Replacement | 2009-07-28 | 2009-09-21 | 2010-12-31 | 2010-12-31 | 2288929.57 | 0.780 | 0002842
2710 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | 0002923 | This project is a roadway safety improvement in Savannah, Chatham County. ARRA funds will only be used to acquire right of way for this project. The project will improve SR 25 Connector/West Bay Stre | Other | 2010-07-21 | 2010-07-21 | 2015-09-30 |  | 2142593 | 1.100 | 0002923
2711 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | CARROLL |  | 03 | 0003083 | This project is a bridge replacement project on County Road 837 in Carroll County. This project replaces the existing structurally deficient bridge over Big Indian Creek with a 320 ft. x 30 ft. conc | Bridge Replacement | 2010-03-02 | 2010-03-29 | 2011-04-30 |  | 1847683.25 | 0.390 | 0003083
2712 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0003769 | This project is an intersection improvement in Fulton County. The project will reconstruct the intersection on County Road 85/Kimball Bridge Road at County Road 103/Waters Road. The construction wil | Pavement Improvement | 2009-12-01 | 2011-02-01 | 2010-10-31 | 2012-05-31 | 849092.42 | 0.200 | 0003769
2713 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0004393 | This is a transportation enhancement project in Atlanta, Fulton County. This project proposes to improve accessibility, mobility and safety by connecting to a bike and pedestrian system that is plann | Transportation Enhancements | 2010-06-18 | 2010-07-26 | 2011-07-01 |  | 1926137.3 | 0.690 | 0004393
2714 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0004456 | This is a new roadway construction project in Gwinnett County. This proposed project will connect to the existing intersection of McGinnis Ferry Road and Satellite Boulevard, with only minor improvem | New Construction | 2009-09-03 | 2009-09-11 | 2011-09-30 | 2011-09-30 | 20412160.25 | 2.670 | 0004456
2715 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0004467 | This project is a safety improvement in the city of Atlanta in Fulton County. The project will construct intersection safety improvements at Barge Road at Campbellton Road. | Safety/Traffic Management | 2012-02-03 | 2012-02-27 | 2012-12-31 |  | 288800 | 0.200 | 0004467
2716 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0004473 | This project is a transportation enhancement in Cobb County. This project is located 1,500 feet east of Cobb Parkway/US 41. The proposed project would construct a 10-foot multiuse path along the eas | Transportation Enhancements | 2010-08-31 | 2010-08-31 | 2011-12-31 |  | 2066335.35 | 0.570 | 0004473
2717 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0004633 | This is a transportation enhancement project in Jonesboro in Clayton County. This project includes enhancements to pedestrian safety and improved near term traffic flow. The project will also addres | Transportation Enhancements | 2010-04-09 | 2010-03-23 | 2011-06-30 | 2011-06-30 | 2862502.49 | 0.870 | 0004633
2718 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0005910 | This project is a transportation enhancement in Fulton County and the City of Sandy Springs. The project consists of the construction of a comprehensive sidewalk system, including new and improved s | Transportation Enhancements | 2010-12-09 |  | 2011-12-31 |  | 402404.1 | 0.310 | 0005910
2719 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0006259 | This project is an enhancement project in Fulton County. This project will construct and improve sidewalks along Piedmont Avenue from the Georgia State University MARTA Station to John Wesley Dobbs Aveneue. | Transportation Enhancements | 2010-09-01 | 2010-09-01 | 2011-12-31 |  | 820000 | 0.560 | 0006259
2720 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 13 | 0006262 | This is a transportation enhancement project in Cobb County, in the city of Acworth. The project will construct improvements along Senator Russell Avenue, including onstreet parking, curb and gutter, | Pavement Improvement | 2010-03-08 | 2010-03-08 | 2010-12-31 |  | 580000 | 0.850 | 0006262
2721 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | CLINCH |  | 01 | 0006534 | This project is a transportation enhancement in Clinch County. The historic Homerville Railroad Depot, also known as Station 11, will be restored to its original architectural style to the extent pos | Transportation Enhancements | 2009-10-08 | 2009-11-09 | 2011-07-01 | 2010-06-24 | 490753 | 0.000 | 0006534
2722 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | WASHINGTON |  | 12 | 0006562 | This project is a transportation enhancement in Washington County and the City of Sandersville. The project will provide new 5-ft sidewalks along Sun Hill Road, providing pedestrian access to Kaolin | Transportation Enhancements | 2010-06-15 | 2010-08-16 | 2011-12-31 | 2011-09-21 | 433724 | 1.570 | 0006562
2723 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 13 | 0006570 | This project is a transportation enhancement in Fulton County. This project will improve conditions at the intersection of Cascade Road and Benjamin Mays Drive from Beecher Road/Bouldevard Granada to | Transportation Enhancements | 2011-01-26 | 2011-11-01 | 2011-12-31 |  | 625000 | 0.210 | 0006570
2724 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 0006597 | This project is a transportation enhancement in Columbus, Muscogee County. This project consists of streetscape improvements on Veterans Pkwy SR 1/US 27 beginning at 8th Street and extending northerl | Transportation Enhancements | 2009-11-12 | 2010-01-25 | 2011-05-15 |  | 1258958.54 | 0.650 | 0006597
2725 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | PIKE |  | 03 | 0006600 | "This project constructs a walking trail in Molena, in Pike County. Construction includes the aesthetic revitalization of a portion of Georgia Highway 109 east of the Georgia Highway 18 intersection. | Transportation Enhancements | 2009-09-29 | 2009-10-21 | 2011-05-15 | 2010-07-31 | 97307 | 0.100 | 0006600
2726 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | POLK |  | 11 | 0006627 | This project is a transportation enhancement in Polk County. Construction includes streetscape improvements in downtown Rockmart along: State Route 6 (Elm Street) from CSX Railroad right-of-way to S | Transportation Enhancements | 2010-11-16 | 2011-02-07 | 2011-06-01 | 2011-04-04 | 210620 | 0.160 | 0006627
2727 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 13 | 0006647 | This project is an enhancement project in Henry County. This project will construct the Reeves Creek Trail and Greenway, a bicycle and pedestrian trail along the Reeves Creek in the City of Stockbridge. | Transportation Enhancements | 2010-04-30 | 2010-09-09 | 2011-12-31 | 2011-09-02 | 625386 | 0.000 | 0006647
2728 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0006657 | This project is a safety and operational improvement project in Fulton County. The proposed project will upgrade six intersections and is located along and adjacent to Mt. Vernon Rd. Intersection up | Safety/Traffic Management | 2011-04-07 | 2011-04-07 | 2012-01-12 |  | 2661626.5 | 1.200 | 0006657
2729 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0006683 | This project is a safety and operational improvement project in Fulton County and the City of Atlanta. This project consists of corridor and intersection improvements on SR 141/Peachtree Road from th | Pavement Improvement | 2010-02-04 | 2010-03-15 | 2012-06-30 |  | 10052474.59 | 1.330 | 0006683
2730 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0006726 | This project is a transportation enhancement in Fayette County in the city of Fayetteville. This project will construct sidewalks in downtown Fayetteville. | Transportation Enhancements | 2010-07-22 | 2010-11-01 | 2011-11-16 | 2011-03-31 | 408552.6 | 0.000 | 0006726
2731 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | 0006791 | This project is a safety improvement in Cherokee County. This project consists of signal, roadway, pedestrian, transit and landscaping improvements along SR Bus 5 (Riverstone Pkwy) between North Etow | Safety/Traffic Management | 2010-07-15 | 2010-08-09 | 2011-06-30 | 2011-09-27 | 445710.52 | 1.500 | 0006791
2732 | GEORGIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0006793 | This project is a transportation enhancement project in Clayton County. This project consists of constructing a pedestrian/bicycle underpass beneath SR 54/Jonesboro Rd. in Morrow, Georgia. Plans are | Transportation Enhancements | 2010-11-18 | 2011-01-24 | 2012-04-30 | 2012-03-08 | 1047895.67 | 0.000 | 0006793
2733 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0006810 | This project provides intersection improvements at 7 locations in Dekalb County. The project consists of the South and North Hairston Road corridors from Kenilworth Drive to Mainstreet Park Drive. T | Safety/Traffic Management | 2010-11-16 | 2010-05-17 | 2011-11-22 |  | 782993.05 | 2.800 | 0006810
2734 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 04 | 0006825 | The proposed project along Buford Highway in Gwinnett County will upgrade signal equipment and install fiber optic interconnect to allow for Intelligent Transporation Systems (ITS). Installation of IT | Safety/Traffic Management | 2009-09-18 | 2010-01-11 | 2011-10-28 | 2011-04-16 | 1195798.89 | 11.010 | 0006825
2735 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0006829 | This project, in Gwinnett County, includes the design of fiber optic communications cable and closed-circuit television (CCTV) cameras along Sugarloaf Parkway from Peachtree Industrial Boulevard in Du | Safety/Traffic Management | 2009-09-18 | 2010-01-25 | 2011-10-28 | 2011-05-05 | 1384553.27 | 12.300 | 0006829
2736 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | 0006840 | This project is a transportation enhancement in Henry County. The proposed project will construct sidewalks and sidewalk improvements in the Tanger Boulevard area of the city of Locust Grove. | Transportation Enhancements | 2010-05-07 | 2010-07-12 | 2012-03-15 |  | 367650 | 0.000 | 0006840
2737 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0006868 | This project is a safety improvement in Cobb County. This project proposes to increase the safety and operation improvements of the intersection of Sandy Plains Road at East Piedmont Road located in | Safety/Traffic Management | 2010-08-06 |  | 2011-11-30 |  | 1751145.79 | 0.600 | 0006868
2738 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0006869 | This project is new roadway construction in Cobb County. The project consists of the construction of Big Shanty Road Connector (SR 401) from Barrett Lakes Boulevard to George Busbee Parkway for a tot | New Construction | 2010-01-05 | 2010-02-19 | 2012-04-30 | 2012-07-27 | 8093954.79 | 1.880 | 0006869
2739 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0006956 | This project is the replacement of a structurally deficient bridge in Coweta County. This project will replace the bridge on County Road 41 over the CSX Railroad, 2.0 miles northeast of Newnan, Georg | Bridge Replacement | 2010-01-05 | 2010-01-15 | 2010-10-31 |  | 1345078.64 | 0.400 | 0006956
2740 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0006957 | This project is the replacement of a structurally deficient bridge in Coweta County. This project will replace the bridge on County Road 130 over White Oak Creek, 3.5 miles northeast of Moreland, Geo | Bridge Replacement | 2010-01-05 | 2010-02-15 | 2010-11-30 | 2010-11-30 | 1055465.1 | 0.250 | 0006957
2741 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0006978 | This project is a transportation enhancement in Fulton County, in downtown Atlanta. The project will construct new and wider sidewalks between the Civic Center MARTA Station and Centennial Olympic Pa | Transportation Enhancements | 2010-09-08 | 2010-11-29 | 2011-12-31 |  | 1200109.58 | 0.360 | 0006978
2742 | GEORGIA | Underway | C220,C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0006984 | This project is a transportation enhancement in Fulton County and the City of Sandy Springs. This project is the construction of a comprehensive streetscape/sidewalk system, including new and improve | Transportation Enhancements | 2010-08-16 |  | 2011-03-31 |  | 2687748.67 | 1.330 | 0006984
2743 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0007128 | This project is preliminary engineering and design for a bridge replacement in Chatham County. This project will replace the Bascule Bridges over the Wilmington River with an Intra-Coastal Waterway | Other | 2010-03-08 | 2010-03-08 | 2015-09-30 |  | 1000000.08 | 0.400 | 0007128
2744 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0007130 | This project is a transportation enhancement in Dekalb County. The project will construct streetscape designs and intersection improvements along SR 154/Memorial Drive from SR 155/Candler Road to Mou | Transportation Enhancements | 2009-07-23 | 2009-09-28 | 2012-05-31 |  | 4539202.25 | 3.400 | 0007130
2745 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0007131 | This project is the construction of intersection and pedestrian safety improvements in DeKalb County. This project is on SR 10/Memorial Drive and begins at Woodcroft Road and ends at Goldsmith Road. | Transportation Enhancements | 2009-11-19 | 2010-03-08 | 2011-12-31 |  | 2716982.02 | 3.470 | 0007131
2746 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | 0008065 | This project is a transportation enhancement in Baldwin County. Phase II of the Milledgeville downtown streetscape proposes to construct new sidewalks, ADA compliant access, new and reconstructed str | Transportation Enhancements | 2010-05-17 | 2010-06-07 | 2011-11-01 | 2011-02-04 | 801060.72 | 0.300 | 0008065
2747 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | JACKSON |  | 10 | 0008066 | This project is a transportation enhancement in Banks and Jackson Counties and in the City of Maysville. This project is the second phase of the Maysville Downtown Streetscape. Project construction | Transportation Enhancements | 2010-04-15 | 2010-07-26 | 2011-12-31 | 2011-07-12 | 355914 | 0.700 | 0008066
2748 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | BURKE |  | 12 | 0008080 | This project is a transportation enhancement in Burke County. The project will provide sidewalks and landscaping along State Route 56 from the intersection of Myrick Street along State Route 56 to Ba | Transportation Enhancements | 2010-04-30 | 2010-06-14 | 2011-12-31 |  | 1128500 | 0.200 | 0008080
2749 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0008098 | This is a transportation enhancement project in Clayton County and the City of Morrow. The project will construct phase II of the Jesters Creek Pedestrian Pathway in Morrow. Project construction beg | Transportation Enhancements | 2011-01-04 | 2011-01-25 | 2011-12-31 | 2011-06-23 | 996461.56 | 0.610 | 0008098
2750 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | DECATUR |  | 02 | 0008113 | This project provides streetscape improvements in downtown Bainbridge in Decatur County. The Bainbridge Central Business District is well defined on the north by Calhoun Street and on the south by Sh | Transportation Enhancements | 2009-09-29 | 2009-11-09 | 2011-07-01 | 2010-09-30 | 591411.23 | 0.360 | 0008113
2751 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 05 | 0008115 | This project is a transportation enhancement in Dekalb County. Deepdene Park will be rehabilitated. The Mead at the east end and the West Lawn at the west end of Deepdene Park will have the open, pas | Transportation Enhancements | 2010-01-05 | 2010-06-07 | 2011-05-07 |  | 1137182.6 | 0.400 | 0008115
2752 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0008119 | This project is a transportation enhancement in DeKalb and Rockdale Counties. This project involves clearing, grading, and installing a 10' to 12' wide concrete trail from MLK High School on Snapfinge | Transportation Enhancements | 2010-01-25 | 2010-05-03 | 2011-05-07 | 2010-10-01 | 653274.68 | 1.600 | 0008119
2753 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | 0008124 | This project is a transportation enhancement project in the City of Douglasville in Douglas County. The project will place historicly designed lighting with banners on Campbellton Street from Douglas | Transportation Enhancements | 2011-06-13 |  | 2012-06-30 |  | 500000 |  | 0008124
2754 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0008126 | The project will provide pedestrian improvements within the City of Fayetteville in Fayette County along Lee Street. This will include construction of a 5 foot sidewalk with a 2 foot grass buffer and | Transportation Enhancements | 2009-09-23 | 2009-11-02 | 2011-05-15 |  | 337500 | 0.590 | 0008126
2755 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0008131 | This is an enhancement project in Fulton County, city of Atlanta. Streetscape improvements within the Farlie Poplar historic district along: 1) Walton Street: between Centennial Olympic Park Drive a | Transportation Enhancements | 2010-05-27 | 2010-09-22 | 2011-12-01 | 2011-08-10 | 659609.34 | 0.210 | 0008131
2756 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0008135 | This project is a transportation enhancement project in Fulton County. The project will be a streetscape improvement extending 4,100 linear feet along Old National Parkway and a portion of Godby Road. | Transportation Enhancements | 2011-12-01 | 2012-04-12 | 2013-12-31 |  | 440800 |  | 0008135
2757 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 13 | 0008140 | This project is a transportation enhancement project in the City of Palmetto in Fulton County. This project will restore the historic Palmetto Train Depot to resmble its original appearance. Work wi | Transportation Enhancements | 2011-07-26 | 2011-09-26 | 2013-12-31 | 2012-07-27 | 750400 |  | 0008140
2758 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | HARALSON |  | 11 | 0008157 | This project is a transportation enhancement in the City of Buchanan in Haralson County. The project will construct sidewalks, curb and gutter, seatwalls, lighting, street furniture and landscaping a | Transportation Enhancements | 2009-10-09 | 2010-02-16 | 2011-06-01 | 2010-12-20 | 438000 | 0.200 | 0008157
2759 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | 0008159 | This project is a transportation enhancement in Henry County. The proposed project will provide a trailhead facility. The project will be constructed on two city owned parcels adjacent to Cleveland | Transportation Enhancements | 2009-10-01 | 2010-03-15 | 2011-05-15 | 2010-09-10 | 241204.1 | 0.910 | 0008159
2760 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | LEE |  | 02 | 0008167 | This project is a transportation enhancement project in Lee County, in the City of Smithville. New sidewalks will be constructed along Main Street to replace the existing broken, non-compliant, and n | Transportation Enhancements | 2010-08-27 | 2010-09-22 | 2011-12-31 |  | 128000 | 0.070 | 0008167
2761 | GEORGIA | Underway | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 0008185 | This is a transportation enhancement project in Muscogee County. This project will provide streetscape and beautification along SR 1/Veteran's Parkway in Columbus from 10th Street to SR 22 Spur. The | Transportation Enhancements | 2009-11-12 | 2010-01-25 | 2011-05-15 |  | 1169885.82 | 0.400 | 0008185
2762 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | OGLETHORPE |  | 10 | 0008187 | This is a transportation enhancement project in Oglethorpe County. The Crawford Depot project will include renovation and rehabilitation of the depot and surrounding grounds. Improvements include ne | Transportation Enhancements | 2010-07-28 | 2010-08-30 | 2011-12-01 | 2011-01-06 | 275000 | 0.000 | 0008187
2763 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0008188 | The project will provide a trailhead facility adjacent to downtown Dallas in Paulding County, on an approximate 1 acre site at the intersection of South Main Street and Hardee Street. The trailhead w | Transportation Enhancements | 2009-09-17 | 2009-12-01 | 2011-06-01 |  | 625000 | 0.060 | 0008188
2764 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | SCHLEY |  | 02 | 0008198 | This project is a transportation enhancement in Schley County. The project will construct sidewalks on three locations in Ellaville: 1) east side of Hill Street between West Buena Vista Street and | Transportation Enhancements | 2009-10-08 | 2010-01-18 | 2011-05-14 | 2010-04-04 | 62344.54 | 0.640 | 0008198
2765 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | TELFAIR |  | 01 | 0008202 | This project is a transportation enhancement project in the in the City of Milan in Telfair County. This project is the renovation of the historic Milan Train Depot. Improvements will include front | Transportation Enhancements | 2011-05-23 | 2011-05-31 | 2013-06-30 | 2011-07-26 | 100000 |  | 0008202
2766 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | WARREN |  | 12 | 0008213 | This is a transportation enhancement project in Warren County. Phase II of the Warren County Historic Depot project will provide streetscape and landscape improvements on the west side of Norwood Str | Transportation Enhancements | 2010-04-13 | 2010-08-02 | 2011-12-31 | 2011-01-14 | 104547 | 0.000 | 0008213
2767 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0008235 | This project will provide traffic signal upgrades in Spalding County. This project will upgrade traffic signal in the City of Griffin at the 12 locations. The signals on Poplar St. between 6th and | Safety/Traffic Management | 2010-02-22 | 2010-04-08 | 2012-03-28 | 2011-02-22 | 1236651.85 | 1.300 | 0008235
2768 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0008236 | This project will provide traffic signal upgrades in Spalding County. This project will upgrade traffic signals at the following intersections: 1) College St. @ 6th St. 2) Hill St. @ Chappell S | Safety/Traffic Management | 2010-02-22 | 2010-04-27 | 2012-03-28 | 2011-02-21 | 326933.55 | 0.000 | 0008236
2769 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0008544 | This is an interchange lighting project in Coweta County. This project shall install 38 High Mast Lighting Towers at two existing interchanges along Interstate 85 in Coweta County. Currently, no road | New Construction | 2010-05-10 | 2010-10-04 | 2010-12-31 | 2011-10-21 | 1109521.11 | 0.800 | 0008544
2770 | GEORGIA | Underway | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0008622 | This project is a transportation enhancement project in Cobb County in the City of Marietta. This project will construct pedestrian improvements, including sidewalks, lighting, benches, landscaping, | Transportation Enhancements | 2011-07-30 | 2011-07-30 | 2012-03-31 |  | 639175.32 | 0.490 | 0008622
2771 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0008902 | This project is a safety and enhancement project in DeKalb County. This project is the construction of sidewalks along South Hairston Road from Rockbridge Road to Wesley Chapel Road. The gross lengt | Transportation Enhancements | 2010-08-26 | 2010-09-06 | 2013-09-01 | 2011-09-12 | 1277442.7 | 5.590 | 0008902
2772 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | BARTOW | ATLANTA | 11 | 0008960 | The proposed project will reconstruct a portion of Glade Road from Catfish Court to Sugar Hill Road to improve the horizontal and vertical curves at this location. ARRA funds will only be used to acq | Other | 2010-04-26 | 2010-08-24 | 2011-06-30 | 2011-09-23 | 420200 | 0.200 | 0008960
2773 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | BACON |  | 01 | 0008977 | This project is a transportation enhancement project in Bacon County. This project is the renovation of a portion of a former elementary school built in 1934 to convert the building to a Welcome Cen | Transportation Enhancements | 2011-04-12 | 2011-06-01 | 2011-12-31 | 2011-10-10 | 218750 |  | 0008977
2774 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | MITCHELL |  | 02 | 0009112 | This is a transportation enhancement project in Mitchell County. This project will improve the streetscape along East Broad Street/ GA S. R. 97/112 in downtown Camilla. Construction includes the dem | Transportation Enhancements | 2010-01-28 | 2010-04-12 | 2011-10-07 | 2011-01-28 | 500000 | 0.100 | 0009112
2775 | GEORGIA | Completed | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009127 | This project is a transportation enhancement project in Richmond County. This project will construct a 10 foot wide multi-use trail on the Campus of Augusta State University and will connect to exist | Transportation Enhancements | 2011-02-01 | 2011-03-08 | 2012-12-31 | 2011-10-31 | 600000 |  | 0009127
2776 | GEORGIA | Underway | C220,C230 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 0009288 | This project is a transportation enhancement project in Columbus/Muscogee County. This project will provide landscaping and a gateway entrance at the interchange of I-185 and SR 520/Victory Drive, just north of the entrance to Fort Benning. | Transportation Enhancements | 2010-09-23 | 2010-11-18 | 2011-12-31 |  | 3059436 | 0.200 | 0009288
2777 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | STATEWIDE | ATLANTA |  | 0009312 | "This project is a planning study in the Atlanta Metropolitan Area. This study will develop a ""Strategic Regional Thoroughfare Plan"" for counties within the Atlanta MPO area. The planning study wi | Other | 2009-12-21 | 2009-12-21 | 2011-03-31 | 2011-12-31 | 1000077.21 | 0.000 | 0009312
2778 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | 0009313 | This project is an engineering study in Chatham County. The SR 21 Corridor Study will develop a congestion relief plan that encompasses several alternatives incorporating but not limited to toll lan | Other | 2010-02-19 | 2010-02-19 | 2012-12-31 |  | 780000 | 0.000 | 0009313
2779 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009314 | This project is an engineering study in Chatham County. The SR 204 Corridor Study will develop a congestion relief plan that encompasses several alternatives incorporating but not limited to toll lan | Other | 2010-02-19 | 2010-02-19 | 2012-12-31 |  | 745000 | 0.000 | 0009314
2780 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | WALKER | CHATTANOOGA (TN) | 09 | 0009317 | This project is a roadway maintenance repaving project in Walker County. This project is the milling and resurfacing of County Road 704/McFarland Avenue from Rossville City limits to SR 1/US 27 for a total project length of 1.64 miles. | Pavement Improvement | 2010-03-02 | 2010-03-03 | 2010-06-30 | 2010-06-30 | 84222.74 | 1.640 | 0009317
2781 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | WALKER | CHATTANOOGA (TN) | 09 | 0009328 | This project is a transportation enhancement project in Walker County in the City of Chickamauga. This project will construct sidewalks at several locations in the City of Chickamauga. Sidewalks will | Transportation Enhancements | 2010-06-23 | 2010-08-26 | 2011-05-15 | 2011-05-05 | 1102000 | 3.310 | 0009328
2782 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0009344 | This project is an intersection improvement in Gwinnett County. The purpose of this project is to improve the operating characteristics of the intersection of SR 8 (Lawrenceville Highway) and Pleasan | Safety/Traffic Management | 2009-08-28 | 2009-09-16 | 2011-06-30 |  | 9328483.55 | 0.210 | 0009344
2783 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 04 | 0009345 | The project is an intersection improvement in Gwinnett County. This project will improve the operation characteristics of the intersection of SR 8 (Lawrenceville Highway) and Beaver Ruin Road/Arcado | Safety/Traffic Management | 2009-08-05 | 2009-11-02 | 2011-06-30 |  | 6285053.8 | 1.100 | 0009345
2784 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | CATOOSA | CHATTANOOGA (TN) | 09 | 0009346 | This project is a safety intersection improvement project in Catoosa County. This project consists of reconstructing the existing left turns lanes on SR 2 from a Type A median crossover to a Type B. | Safety/Traffic Management | 2009-07-27 | 2009-08-26 | 2010-09-30 |  | 1531013.32 | 0.220 | 0009346
2785 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0009347 | This is a transportation enhancement project in Atlanta, Fulton County. This project will construct sidewalk improvements, including the replacement and upgrading of existing sidewalks along portions | Transportation Enhancements | 2010-07-09 | 2010-10-21 | 2011-12-31 |  | 4001548.18 | 0.800 | 0009347
2786 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0009348 | This project is a safety improvement in Fulton County. The proposed project will provide traffic signals at five key intersections in Midtown Atlanta. This project will provide a safer pedestrian an | Pavement Improvement | 2010-01-12 | 2010-05-11 | 2010-12-31 | 2010-12-15 | 427274.66 | 0.000 | 0009348
2787 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0009349 | This project will modify the interchange of SR 120/Roswell Road and SR 120 Alternate (formerly SR 120 Loop) in Cobb County. This project is located in the City of Marietta. The proposed project will | Pavement Improvement | 2009-08-18 | 2009-09-01 | 2011-06-30 | 2011-08-11 | 7573857.03 | 0.750 | 0009349
2788 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0009350 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 809/Corner Road. The construction will con | Pavement Improvement | 2009-08-19 | 2009-09-24 | 2011-04-30 | 2011-04-30 | 1242339.86 | 1.600 | 0009350
2789 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0009351 | This project is a road widening construction project in Gwinnett County. The project will widen and reconstruct the existing two lanes of SR 20 to accommodate 4 lanes beginning approximately 800 feet | Pavement Improvement | 2009-09-08 | 2009-10-22 | 2011-12-31 |  | 12285042.19 | 2.650 | 0009351
2790 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0009352 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 784/Hadaway Road. The construction will co | Pavement Improvement | 2009-08-19 | 2009-09-24 | 2011-04-30 | 2011-04-30 | 956562.38 | 0.400 | 0009352
2791 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0009353 | The project is an intersection safety improvement in Cobb County. This project will improve the intersection of SR 176/Lost Mountain Highway at County Road 55/Mars Hill Church Road. The construction | Pavement Improvement | 2009-08-19 | 2009-09-24 | 2011-04-30 | 2011-04-30 | 884562.14 | 0.400 | 0009353
2792 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 13 | 0009354 | This project will upgrade existing traffic signal equipment and pedestrian facilities for S.R. 138 at various intersections in Clayton and Henry Counties. The intersections are as follows: 1) SR 138 | Safety/Traffic Management | 2010-04-09 | 2010-08-23 | 2011-12-29 |  | 1170283.8 | 2.000 | 0009354
2793 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0009355 | This project will upgrade existing traffic signal equipment and pedestrian facilities for S.R. 314 and S.R. 54 at various intersections in Fayette County. The intersections are as follows: 1) SR 3 | Safety/Traffic Management | 2009-07-20 | 2009-10-26 | 2010-02-28 | 2010-02-28 | 159969.21 | 1.200 | 0009355
2794 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0009356 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at five locations for S.R. 42 in Clayton County. The intersections are as follows: 1) SR 42 @ I-675 NB Ram | Safety/Traffic Management | 2010-04-09 | 2010-08-23 | 2012-01-27 | 2011-05-11 | 560486.24 | 1.600 | 0009356
2795 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009357 | This project is a safety project in Fulton County in the City of Roswell. This project will upgrade existing traffic signal equipment and pedestrian facilities at various locations on Pine Grove Road | Safety/Traffic Management | 2010-02-05 | 2010-06-01 | 2010-10-31 | 2011-06-11 | 250129.91 | 1.600 | 0009357
2796 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009358 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations on SR 961/Old Alabama Road in the City of Roswell, Fulton County. The intersections are | Safety/Traffic Management | 2009-07-17 | 2009-10-12 | 2010-07-31 | 2010-07-16 | 739946.39 | 3.000 | 0009358
2797 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 06 | 0009359 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations in DeKalb County on Chamblee Tucker Road, Clairmont Road, & New Peachtree Road. The int | Safety/Traffic Management | 2009-07-20 | 2009-09-22 | 2010-05-31 | 2010-05-24 | 1134216 | 0.000 | 0009359
2798 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0009360 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at various locations on Briarcliff Road & Shallowford Road in Dekalb County. The intersections are as follow | Safety/Traffic Management | 2009-07-20 | 2009-11-04 | 2010-07-31 | 2010-07-21 | 892693.87 | 1.800 | 0009360
2799 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0009361 | This project will upgrade the existing traffic signal equipment and pedestrian facilities at various locations on Chamblee Dunwoody Road and NorthShallowford Road in DeKalb County. The intersections | Safety/Traffic Management | 2009-07-20 | 2010-02-01 | 2010-12-31 |  | 1855080.7 | 0.000 | 0009361
2800 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0009362 | This project is the upgrade of existing traffic signal equipment and pedestrian facilities at 21 locations on LaVista Rd, Northlake Pkwy, & Henderson Mill Rd in Dekalb County at the following intersec | Safety/Traffic Management | 2009-07-20 | 2010-05-11 | 2010-12-31 |  | 1984055.69 | 0.000 | 0009362
2801 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 13 | 0009363 | This project consists of the upgrade of the traffic signals at 4 locations on SR 139/Mableton Parkway and 1 location on County Road 2570/Old Alabama Road in Cobb County. Pedestrian improvements will | Safety/Traffic Management | 2009-07-20 | 2009-11-02 | 2010-07-31 |  | 439774.72 | 1.900 | 0009363
2802 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009365 | This project is the replacement of the existing bridge over Euchee Creek on SR 223, 2.2 miles northwest of Grovetown, in Columbia County. The project will widen and correct the structural deficiencie | Bridge Replacement | 2009-11-02 | 2010-02-24 | 2010-12-31 |  | 2397388.95 | 0.220 | 0009365
2803 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | ATKINSON |  | 01 | 0009366 | This project is located approximately four miles northwest of Pearson, Georgia in Atkinson County. This project will construct a bridge replacement over Pudding Creek along County Road 42/Antioch Chur | Bridge Replacement | 2009-07-28 | 2009-08-10 | 2010-06-30 | 2010-04-27 | 1444243.97 | 0.430 | 0009366
2804 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009367 | This project is a bridge replacement on CR 85/Kimball Bridge Road two miles southeast of Alpharetta in Fulton County. The project is 0.554 miles long, consisting of removal of the existing Big Creek B | Bridge Replacement | 2009-12-04 | 2010-01-21 | 2011-09-30 | 2011-10-28 | 4285509.95 | 0.200 | 0009367
2805 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009379 | This project is an engineering and planning study in Chatham County. The study will evaluate the US 80 Bridges and will develop a plan for replacement bridges over the Bull River and Lazaretto Creek. | Other | 2010-02-19 | 2010-02-19 | 2012-12-31 |  | 264961 | 0.000 | 0009379
2806 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009380 | This project is a safety improvement in Chatham County in downtown Savannah. This project consists of upgrading pedestrian countdown signal heads at multiple intersections. | Safety/Traffic Management | 2010-03-19 | 2010-06-28 | 2011-05-31 | 2011-03-18 | 450217.07 | 0.000 | 0009380
2807 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009381 | This project is a safety improvement in Chatham County in downtown Savannah. The project will install audible push buttons at 50 signalized intersections. The push buttons emit an audible signal to | Safety/Traffic Management | 2010-03-19 | 2010-06-28 | 2011-05-31 | 2011-03-18 | 274621.76 | 0.000 | 0009381
2808 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009382 | This project is a safety improvement in Chatham County in downtown Savannah. This project consists of replacing existing signal heads at eleven signalized intersections along 27th Street, from Montgo | Safety/Traffic Management | 2010-03-19 | 2010-06-28 | 2011-05-31 | 2011-03-18 | 70548.86 | 1.200 | 0009382
2809 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | 0009385 | This project is a safety improvement in Chatham County in the City of Savannah. This project consists of installing an emergency vehicle GPS pre-emption system assembly at existing signalized interse | Safety/Traffic Management | 2010-03-19 | 2010-06-28 | 2011-05-31 | 2011-03-18 | 1403176.23 | 0.000 | 0009385
2810 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 0009401 | This project is a transportation enhancement in Muscogee County. The 14th Street Bridge pedestrian project will connect the riverwalk projects in Georgia and Alabama. The project consist of rehabili | Transportation Enhancements | 2010-12-02 | 2011-03-28 | 2012-03-15 |  | 3351386 | 0.140 | 0009401
2811 | GEORGIA | Completed | C490 | OJT/SS | GEORGIA | STATEWIDE |  |  | 0009416 | This On-the-job Training/Supportive Services (OJT/SS) grant provides academic and occupational skills training to low-income women and minorities and places them in the highway construction industry a | Other | 2009-10-05 | 2009-12-15 | 2010-12-31 | 2010-12-31 | 171094.22 | 0.000 | 0009416
2812 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0009419 | This project is an intersection improvement in Coweta County. The project will realign the intersection of SR 16/Wells Street at County Road 157/Broad Street & Luther Bailey Road. The project will c | Safety/Traffic Management | 2009-10-06 | 2009-10-15 | 2010-09-30 | 2010-09-30 | 1017617.62 | 0.380 | 0009419
2813 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COFFEE |  | 01 | 0009421 | This project will replace the structurally deficient bridge on SR 135/US 221 over Tiger Creek in Coffee County. The existing 108 X 24' bridge was constructed in 1947 and will be replaced with a new 1 | Bridge Replacement | 2009-09-24 | 2009-10-29 | 2010-08-31 | 2010-09-10 | 1345914.2 | 0.300 | 0009421
2814 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | PIERCE |  | 01 | 0009422 | This is an intersection improvement project in Pierce County. This project will realign the intersection of SR 203/Strickland Street and County Road 309/Old Alma Road and with County Road 236 to impr | Pavement Improvement | 2009-09-28 | 2010-01-11 | 2010-06-30 |  | 1084675.85 | 0.360 | 0009422
2815 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | BARROW | ATLANTA | 07 | 0009423 | This project is a maintenance resurfacing project in Barrow County to repave local roadways. The Barrow resurfacing program includes four roadways: 1) Carl Bethlehem Road from SR 81 to SR 11; 2) Smi | Pavement Improvement | 2010-01-21 | 2010-02-01 | 2010-07-31 | 2010-05-07 | 1026314.51 | 8.590 | 0009423
2816 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | BARTOW | ATLANTA | 11 | 0009424 | This project is a maintenance resurfacing project in Bartow County to repave local roadways. The Bartow resurfacing program includes two roadways: 1) Red Top Mountain Road from 0.24 miles east of I- | Pavement Improvement | 2010-01-19 | 2010-03-16 | 2010-06-30 | 2010-06-03 | 194631.77 | 1.860 | 0009424
2817 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | 0009425 | This project is a maintenance resurfacing project in Cherokee County to repave local roadways. The Cherokee resurfacing program includes a single roadway 1) East Cherokee Drive from 0.16 miles north | Pavement Improvement | 2010-02-02 | 2010-04-27 | 2010-06-30 | 2010-06-30 | 220054.36 | 1.540 | 0009425
2818 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0009426 | This project is a maintenance resurfacing project in Clayton County to repave local roadways. The Clayton resurfacing program includes three roadways: 1) Flint River Road from Glenwoods Drive to Kend | Pavement Improvement | 2010-02-24 | 2010-03-29 | 2010-06-30 | 2010-05-24 | 874930.09 | 3.880 | 0009426
2819 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | 0009427 | This project is a maintenance resurfacing project in Coweta County to repave local roadways. The Coweta resurfacing program includes three roadways: 1) Poplar Road from I-85 to Yeager Road and from | Pavement Improvement | 2010-02-04 | 2010-05-25 | 2010-07-31 | 2010-07-30 | 749364.77 | 8.620 | 0009427
2820 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 03 | 0009428 | This project is a maintenance resurfacing project in Douglas County to repave local roadways. The Douglas resurfacing program includes three roadways: 1) Liberty Road from North Helton Road to Libert | Pavement Improvement | 2010-02-24 | 2010-04-12 | 2010-06-30 | 2010-06-09 | 822980.05 | 4.460 | 0009428
2821 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0009429 | This project is a maintenance resurfacing project in Fayette County to repave local roadways. The Fayette resurfacing program includes five roadways: 1) SR 85 Connector from SR 85 to Woods Road; 2) H | Pavement Improvement | 2010-02-05 | 2010-05-17 | 2010-07-31 | 2010-06-15 | 779214.75 | 7.460 | 0009429
2822 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | FORSYTH | ATLANTA | 09 | 0009430 | This project is a maintenance resurfacing project in Forsyth County to repave local roadways. The Forsyth resurfacing program includes seven roadways: 1) Old Atlanta Road from James Burgess Road to | Pavement Improvement | 2010-01-19 | 2010-03-31 | 2010-07-31 | 2010-05-17 | 1609403.57 | 9.370 | 0009430
2823 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | 0009431 | This project is a maintenance resurfacing project in Henry County to repave local roadways. The Henry resurfacing program includes two roadways: 1) Thurman Road from East Atlanta Road to Rex Road; | Pavement Improvement | 2010-02-03 | 2010-04-21 | 2010-07-31 | 2010-06-05 | 715104.65 | 3.200 | 0009431
2824 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | ROCKDALE | ATLANTA | 04 | 0009432 | This project is a maintenance resurfacing project in Rockdale County to repave local roadways. The Rockdale resurfacing program includes four roadways: 1) Sigman Road from Gees Mill Road to Old Covi | Pavement Improvement | 2010-02-11 | 2010-02-25 | 2010-06-30 | 2010-06-07 | 1132452.96 | 12.270 | 0009432
2825 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | WALTON | ATLANTA | 07 | 0009433 | This project is a maintenance resurfacing project in Walton County to repave local roadways. The Walton program includes four roadways: 1) Old Monroe Highway from Pannell Road to Nunnally Shoals Roa | Pavement Improvement | 2010-02-05 | 2010-04-07 | 2010-07-31 | 2010-06-11 | 1681770.15 | 15.380 | 0009433
2826 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | 0009452 | This project is the construction of the widening and improvement of SR 74 in Fayette County, from SR 85 to Cooper Circle Road (approximately 1.85 miles south of Crosstown Drive) for a total length of | Pavement Widening | 2009-10-26 | 2009-11-17 | 2011-12-31 |  | 15925376.13 | 3.000 | 0009452
2827 | GEORGIA | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | TROUP |  | 03 | 0009453 | This project will construct phase two of the South LaGrange Loop, a new roadway in Troup County. The roadway will be a bypass around the southern portion of the City of LaGrange. The limits extend f | New Construction | 2009-11-06 | 2009-11-23 | 2011-12-31 |  | 20310819.69 | 4.150 | 0009453
2828 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | CLARKE | ATHENS | 10 | 0009454 | This project is a roadway maintenance repaving project in Clarke County. This project is the milling and resurfacing of County Road 470/MAIN ST from County Road 134/ATHENS ROAD to OGLETHORPE COUNTY LINE for a total project length of 1.5 miles. | Pavement Improvement | 2010-02-05 | 2010-04-29 | 2010-07-31 | 2010-06-25 | 216583.46 | 1.500 | 0009454
2829 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | CLARKE | ATHENS | 10 | 0009455 | This project is a roadway maintenance repaving project in Clarke County. This project is the milling and resurfacing of County Road 140/OLD ELBERTON from County Road 477/VOYLES ROAD to MADISON COUNTY LINE for a total project length of 1.87 miles. | Pavement Improvement | 2010-02-05 | 2010-04-29 | 2010-07-31 | 2010-06-25 | 212885.59 | 1.870 | 0009455
2830 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | CLARKE | ATHENS | 10 | 0009456 | This project is a roadway maintenance repaving project in Clarke County. This project is the milling and resurfacing of County Road 120/SMOKEY ROAD from NOWHERE ROAD to HELICAN SPRINGS ROAD for a total project length of 2.45 miles. | Pavement Improvement | 2010-02-05 | 2010-04-29 | 2010-07-31 | 2010-06-25 | 273044.91 | 2.450 | 0009456
2831 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | ELBERT |  | 10 | 0009457 | This project is a roadway maintenance repaving project in Elbert County. This project is the milling and resurfacing of County Road 307/THIRTEEN FORKS ROAD from SR 77 to HART COUNTY LINE for a total project length of 4.13 miles. | Pavement Improvement | 2010-01-19 | 2010-04-06 | 2010-07-31 | 2010-06-02 | 417391.42 | 4.130 | 0009457
2832 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | FRANKLIN |  | 10 | 0009458 | This project is a roadway maintenance repaving project in Franklin County. This project is the milling and resurfacing of County Road 418/County Road 419/BOLD SPRINGS ROAD from SR 106 to SR 59; EXC SR 26 for a total project length of 3.62 miles. | Pavement Improvement | 2010-02-03 | 2010-04-22 | 2010-07-31 | 2010-06-09 | 566828.91 | 6.840 | 0009458
2833 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HABERSHAM |  | 10 | 0009459 | This project is a roadway maintenance repaving project in Habersham County. This project is the milling and resurfacing of County Road 387/DEMOREST/MT AIRY ROAD from SR 385/US 442 to SR 365 for a total project length of 1.25 miles. | Pavement Improvement | 2010-01-19 | 2010-04-19 | 2010-06-30 | 2010-05-29 | 331949.62 | 1.250 | 0009459
2834 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | 0009460 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 367/West Ridge Road from County Road 751/Athens Street to SR 11 for a total project length of 0.42 miles. | Pavement Improvement | 2010-03-02 | 2010-04-16 | 2010-06-30 | 2010-06-30 | 91513.81 | 0.420 | 0009460
2835 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | 0009461 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 367/County Road 1098/West Ridge Road from SR 11 to SR 53 Connector for a total project length of 0.69 miles. | Pavement Improvement | 2010-03-02 | 2010-04-16 | 2010-06-30 | 2010-06-30 | 160727.23 | 1.040 | 0009461
2836 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | 0009462 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 621/Wade Orr Road from SR 13 to County Road 685/Hog Mountain Road for a total project length of 1.1 miles. | Pavement Improvement | 2010-03-02 | 2010-04-16 | 2010-06-30 | 2010-06-30 | 187963.85 | 1.100 | 0009462
2837 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | 0009463 | This project is a roadway maintenance repaving project in Hall County. This project is the milling and resurfacing of County Road 451/Memorial Park Drive from SR 369 to SR 13 for a total project length of 1.6 miles. | Pavement Improvement | 2010-03-02 | 2010-04-16 | 2010-06-30 | 2010-06-30 | 255737.14 | 1.600 | 0009463
2838 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | HART |  | 10 | 0009464 | This project is a roadway maintenance repaving project in Hart County. This project is the milling and resurfacing of County Road 505/LIBERTY CHURCH ROAD from SR 172 to ELBERT COUNTY LINE for a total project length of 2.38 miles. | Pavement Improvement | 2010-01-19 | 2010-04-06 | 2010-07-31 | 2010-06-02 | 226141.92 | 2.380 | 0009464
2839 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JACKSON |  | 10 | 0009465 | This project is a roadway maintenance repaving project in Jackson County. This project is the milling and resurfacing of County Road 426/WAYNE POULTRY from OLD GAINESVILLE HWY to VALENTINE PKY for a total project length of 2.8 miles. | Pavement Improvement | 2010-02-05 | 2010-03-30 | 2010-06-30 | 2010-05-24 | 590755.4 | 2.800 | 0009465
2840 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LUMPKIN |  | 09 | 0009466 | This project is a roadway maintenance repaving project in Lumpkin County. This project is the milling and resurfacing of County Road 134/DAMASCUS CHURCH ROAD from SR 9/US 19 to WHITE COUNTY LINE for a total project length of 3.24 miles. | Pavement Improvement | 2010-01-21 | 2010-04-14 | 2010-07-31 | 2010-05-27 | 303783.7 | 3.240 | 0009466
2841 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MADISON |  | 10 | 0009467 | This project is a roadway maintenance repaving project in Madison County. This project is the milling and resurfacing of County Road 394/LEXINGTON ROAD from SR 72 to OGLETHORPE COUNTY LINE for a total project length of 1.63 miles. | Pavement Improvement | 2010-01-19 | 2010-04-01 | 2010-06-30 | 2010-05-05 | 171858.1 | 1.630 | 0009467
2842 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RABUN |  | 09 | 0009468 | This project is a roadway maintenance repaving project in Rabun County. This project is the milling and resurfacing of OLD 441 from south of County Road 218 to City Street 514 and from City Street 50 | Pavement Improvement | 2010-02-01 | 2010-03-29 | 2010-07-31 | 2010-06-05 | 1164968.56 | 10.000 | 0009468
2843 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | STEPHENS |  | 10 | 0009469 | This project is a roadway maintenance repaving project in Stephens County. This project is the milling and resurfacing of County Road 538/BROOKHAVEN CIR from County Road 43/E SILVER SHOALS ROAD to SR 328 for a total project length of 6.34 miles. | Pavement Improvement | 2010-02-01 | 2010-05-19 | 2010-07-31 | 2010-07-27 | 758953.49 | 6.340 | 0009469
2844 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TOWNS |  | 10 | 0009470 | This project is a roadway maintenance repaving project in Towns County. This project is the milling and resurfacing of County Road 172/GUM LOG ROAD from west of WINCHESTER CREEK ROAD to BARNARD ROAD for a total project length of 1.4 miles. | Pavement Improvement | 2010-01-19 | 2010-04-02 | 2010-07-31 | 2010-05-25 | 129695.44 | 1.400 | 0009470
2845 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | UNION |  | 09 | 0009471 | This project is a roadway maintenance repaving project in Union County. This project is the milling and resurfacing of County Road 341/OLD BLUE RIDGE HWY from County Road 117 to LITTLE YOUNGCANE CREEK for a total project length of 2.57 miles. | Pavement Improvement | 2010-01-19 | 2010-04-02 | 2010-07-31 | 2010-05-25 | 280070.76 | 2.570 | 0009471
2846 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WHITE |  | 09 | 0009472 | This project is a roadway maintenance repaving project in White County. This project is the milling and resurfacing of County Road 68/HULSEY ROAD from SR 75 to SR 11/US 129 for a total project length of 1.3 miles. | Pavement Improvement | 2010-01-21 | 2010-04-14 | 2010-07-31 | 2010-05-27 | 133980.42 | 1.300 | 0009472
2847 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | 0009473 | This project is a roadway maintenance repaving project in Baldwin County. This project is the milling and resurfacing of City Street 701/BLANDY ROAD from SR 49 to SR 22 for a total project length of 1.96 miles. | Pavement Improvement | 2010-01-29 | 2010-03-13 | 2010-06-30 | 2010-06-30 | 245366.36 | 1.960 | 0009473
2848 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | 0009474 | This project is a roadway maintenance repaving project in Baldwin County. This project is the milling and resurfacing of County Road 69/BROWNS CROSSING ROAD from SR 49 to SR 22 for a total project length of 3.64 miles. | Pavement Improvement | 2010-01-21 | 2010-03-01 | 2010-06-30 | 2010-06-30 | 334141.09 | 3.640 | 0009474
2849 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HANCOCK |  | 12 | 0009475 | This project is a roadway maintenance repaving project in Hancock County. This project is the milling and resurfacing of County Road 180/POWELLTON AVE from HAMILTON ST to SPARTA CITY LIMITS for a total project length of 0.57 miles. | Pavement Improvement | 2010-02-03 | 2010-05-26 | 2010-06-30 | 2010-07-05 | 58144.51 | 0.570 | 0009475
2850 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JEFFERSON |  | 12 | 0009476 | This project is a roadway maintenance repaving project in Jefferson County. This project is the milling and resurfacing of City Street 561/MIDVILLE ROAD from SR 4 to SR 24 for a total project length of 0.8 miles. | Pavement Improvement | 2010-02-03 | 2010-03-12 | 2010-06-30 | 2010-05-06 | 121321.74 | 0.800 | 0009476
2851 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JEFFERSON |  | 12 | 0009477 | This project is a roadway maintenance repaving project in Jefferson County. This project is the milling and resurfacing of County Road 59/QUAKER ROAD from SR 17 to SR 80 for a total project length of 1.5 miles. | Pavement Improvement | 2010-02-03 | 2010-03-12 | 2010-06-30 | 2010-05-06 | 176411.74 | 1.500 | 0009477
2852 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JOHNSON |  | 12 | 0009478 | This project is a roadway maintenance repaving project in Johnson County. This project is the milling and resurfacing of County Road 203/BAY SPRINGS CHURCH ROAD from SR 26 to MT OLIVE CHURCH ROAD for a total project length of 2.88 miles. | Pavement Improvement | 2010-01-29 | 2010-04-19 | 2010-06-30 | 2010-05-21 | 292633.57 | 2.880 | 0009478
2853 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LAURENS |  | 08 | 0009479 | This project is a roadway maintenance repaving project in Laurens County. This project is the milling and resurfacing of City Street 768/ROBERSON ST from SR 19/US 80 to City Street 770/KNOX ST for a total project length of 0.23 miles. | Pavement Improvement | 2010-02-01 | 2010-06-08 | 2010-06-30 | 2010-07-16 | 41310.98 | 0.230 | 0009479
2854 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LAURENS |  | 08 | 0009480 | This project is a roadway maintenance repaving project in Laurens County. This project is the milling and resurfacing of County Road 526/OLD MACON ROAD from EVERGREEN ROAD to WILKINSON COUNTY LINE for a total project length of 4.21 miles. | Pavement Improvement | 2010-02-01 | 2010-06-08 | 2010-06-30 | 2010-07-16 | 361536.74 | 4.210 | 0009480
2855 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | MCDUFFIE |  | 10 | 0009481 | This project is a roadway maintenance repaving project in McDuffie County. This project is the milling and resurfacing of City Street 663/RAILROAD STREET from SR 17 to SR 223 for a total project length of 0.67 miles. | Pavement Improvement | 2010-02-01 | 2010-04-21 | 2010-06-30 | 2010-06-24 | 96225.26 | 0.670 | 0009481
2856 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MCDUFFIE |  | 10 | 0009482 | This project is a roadway maintenance repaving project in McDuffie County. This project is the milling and resurfacing of County Road 309/HAPPY VALLEY ROAD from SR 17 to County Road 297/SAND HILL ROAD for a total project length of 1.16 miles. | Pavement Improvement | 2010-02-01 | 2010-04-21 | 2010-06-30 | 2010-06-24 | 163573.5 | 1.160 | 0009482
2857 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | OGLETHORPE |  | 10 | 0009483 | This project is a roadway maintenance repaving project in Oglethorpe County. This project is the milling and resurfacing of County Road 77/WOLFSKIN ROAD from County Road 240 to CLARKE COUNTY LINE for a total project length of 0.69 miles. | Pavement Improvement | 2010-01-21 | 2010-03-30 | 2010-06-30 | 2010-05-06 | 94033.58 | 0.690 | 0009483
2858 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | 0009484 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 1509/KEYSVILLE ROAD from SR 88 to BURKE COUNTY LINE for a total project length of 3.1 miles. | Pavement Improvement | 2010-01-29 | 2010-02-26 | 2010-06-30 | 2010-04-20 | 315540.22 | 3.100 | 0009484
2859 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | SCREVEN |  | 12 | 0009485 | This project is a roadway maintenance repaving project in Screven County. This project is the milling and resurfacing of County Road 243/E OGEECHEE ST from SR 73 to SYLVANIA CITY LIMITS for a total project length of 1 mile. | Pavement Improvement | 2010-01-29 | 2010-03-17 | 2010-06-30 | 2010-04-30 | 180411.65 | 1.000 | 0009485
2860 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WARREN |  | 12 | 0009486 | This project is a roadway maintenance repaving project in Warren County. This project is the milling and resurfacing of County Road 174/FIVE POINTS JEWELL ROAD from SR 16 to SR 123 for a total project length of 0.54 miles. | Pavement Improvement | 2010-02-01 | 2010-04-21 | 2010-06-30 | 2010-06-24 | 66207.8 | 0.540 | 0009486
2861 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | WASHINGTON |  | 12 | 0009487 | This project is a roadway maintenance repaving project in Washington County. This project is the milling and resurfacing of County Road 446/RIDGE ROAD from SR 88 to SR 15 for a total project length of 1.99 miles. | Pavement Improvement | 2010-02-03 | 2010-05-26 | 2010-06-30 | 2010-07-05 | 180890.21 | 1.990 | 0009487
2862 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WILKES |  | 10 | 0009488 | This project is a roadway maintenance repaving project in Wilkes County. This project is the milling and resurfacing of City Street 612/ANDREWS DRIVE from SR 17/US 78BU to SR 47 for a total project length of 2.13 miles. | Pavement Improvement | 2010-02-05 | 2010-05-05 | 2010-06-30 | 2010-06-11 | 272715.37 | 2.130 | 0009488
2863 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | BUTTS |  | 08 | 0009489 | This project is a roadway maintenance repaving project in Butts County. This project is the milling and resurfacing of County Road 296/BROWNLEE ROAD from SR 36 to County Road 136 at the Monroe County line for a total project length of 6.63 miles. | Pavement Improvement | 2010-02-05 | 2010-04-07 | 2010-07-31 | 2010-04-28 | 615758.83 | 6.630 | 0009489
2864 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | DOOLY |  | 02 | 0009490 | This project is a roadway maintenance repaving project in Dooly County. This project is the milling and resurfacing of County Road 320/ELKO ROAD from HOUSTON COUNTY LINE to SR 7 for a total project length of 1.2 miles. | Pavement Improvement | 2010-01-21 | 2010-05-11 | 2010-06-30 | 2010-06-30 | 116990.98 | 1.200 | 0009490
2865 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JONES |  | 08 | 0009491 | This project is a roadway maintenance repaving project in Jones County. This project is the milling and resurfacing of County Road 292/BOWEN HILL ROAD from County Road 107/SMITH ROAD to SR 49 for a total project length of 3.9 miles. | Pavement Improvement | 2010-01-29 | 2010-02-27 | 2010-07-31 | 2010-06-30 | 432947.57 | 3.900 | 0009491
2866 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LAMAR |  | 03 | 0009492 | This project is a roadway maintenance repaving project in Lamar County. This project is the milling and resurfacing of County Road 214/HIGH FALLS PARK from SR 36 to MONROE COUNTY LINE for a total project length of 4.42 miles. | Pavement Improvement | 2010-02-01 | 2010-03-09 | 2010-07-31 | 2010-06-30 | 466332.74 | 4.420 | 0009492
2867 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MACON |  | 02 | 0009493 | This project is a roadway maintenance repaving project in Macon County. This project is the milling and resurfacing of County Road 282/DRAYTON ROAD from County Road 22/TWIN CHURCHS ROAD to Dooly County line for a total project length of 5.05 miles. | Pavement Improvement | 2010-02-01 | 2010-04-30 | 2010-07-31 | 2010-06-24 | 312475.75 | 5.050 | 0009493
2868 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PIKE |  | 03 | 0009494 | This project is a roadway maintenance repaving project in Pike County. This project is the milling and resurfacing of County Road 161/KINGS ROAD from SR 109 to UPSON COUNTY LINE for a total project length of 3.93 miles. | Pavement Improvement | 2010-02-05 | 2010-06-08 | 2010-07-31 | 2010-07-31 | 471915.7 | 3.930 | 0009494
2869 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PULASKI |  | 08 | 0009495 | This project is a roadway maintenance repaving project in Pulaski County. This project is the milling and resurfacing of County Road 198/BURNT BRIDGE from SR 26 to SR 230 for a total project length of 4.1 miles. | Pavement Improvement | 2010-01-21 | 2010-05-12 | 2010-06-30 | 2010-06-30 | 369659.52 | 4.100 | 0009495
2870 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TROUP |  | 03 | 0009496 | This project is a roadway maintenance repaving project in Troup County. This project is the milling and resurfacing of County Road 407/BARTLEY ROAD from SHOEMAKER ROAD to SR 1 for a total project length of 8.35 miles. | Pavement Improvement | 2010-02-03 | 2010-03-12 | 2010-07-31 | 2010-05-20 | 834791.97 | 8.350 | 0009496
2871 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TWIGGS |  | 08 | 0009497 | This project is a roadway maintenance repaving project in Twiggs County. This project is the milling and resurfacing of County Road 193/SGODA-HUBER ROAD from SR 87 to County Road 185/RIGGINS MILL ROAD for a total project length of 4.78 miles. | Pavement Improvement | 2010-02-05 | 2010-02-19 | 2010-07-31 | 2010-07-31 | 787351.56 | 4.780 | 0009497
2872 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | UPSON |  | 03 | 0009498 | This project is a roadway maintenance repaving project in Upson County. This project is the milling and resurfacing of County Road 421/BARNESVILLE ROAD from SR 74 to LAMAR COUNTY LINE for a total project length of 5.27 miles. | Pavement Improvement | 2010-01-21 | 2010-02-17 | 2010-07-31 | 2010-06-03 | 627180.86 | 5.270 | 0009498
2873 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BAKER |  | 02 | 0009499 | This project is a roadway maintenance repaving project in Baker County. This project is the milling and resurfacing of County Road 122/PRETORIA ROAD from SR 91 to DOUGHERTY COUNTY LINE for a total project length of 7.49 miles. | Pavement Improvement | 2010-02-03 | 2010-05-12 | 2010-07-31 | 2010-07-28 | 641271.21 | 7.490 | 0009499
2874 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BEN HILL |  | 08 | 0009500 | This project is a roadway maintenance repaving project in Ben Hill County. This project is the milling and resurfacing of County Road 254/OSIERFIELD from SR 206 to IRWIN COUNTY LINE for a total project length of 1.09 miles. | Pavement Improvement | 2010-01-19 | 2010-04-07 | 2010-06-30 | 2010-06-02 | 90941.2 | 1.090 | 0009500
2875 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BERRIEN |  | 01 | 0009501 | This project is a roadway maintenance repaving project in Berrien County. This project is the milling and resurfacing of County Road 359/WYCLIFF ROBERTS ROAD from SR 158 to County Road 238/GLADYS ROAD for a total project length of 6.87 miles. | Pavement Improvement | 2010-01-19 | 2010-03-25 | 2010-07-31 | 2010-05-19 | 451816.03 | 6.870 | 0009501
2876 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | COLQUITT |  | 02 | 0009502 | This project is a roadway maintenance repaving project in Colquitt County. This project is the milling and resurfacing of City Street 759/City Street 1025/WEST BLVD from SR 33/US 319 to City Street 753/FIFTH AVE for a total project length of 1.87 miles. | Pavement Improvement | 2010-02-01 | 2010-06-07 | 2010-06-30 | 2010-07-22 | 315921.17 | 1.930 | 0009502
2877 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | COOK |  | 01 | 0009503 | This project is a roadway maintenance repaving project in Cook County. This project is the milling and resurfacing of County Road 247/MASSEE POST ROAD from BOONE ROAD to LONNIE GRIMSLEY ROAD for a total project length of 1.53 miles. | Pavement Improvement | 2010-01-21 | 2010-06-14 | 2010-06-30 | 2010-07-22 | 163130.23 | 1.530 | 0009503
2878 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | DOUGHERTY | ALBANY | 02 | 0009504 | This project is a roadway maintenance repaving project in Dougherty County. This project is the milling and resurfacing of WEST OAKRIDGE DRIVE from OLD PRETORIA ROAD to LOCKETT STATION for a total project length of 1.66 miles. | Pavement Improvement | 2010-01-21 | 2010-04-26 | 2010-06-30 | 2010-06-15 | 590782.8 | 3.200 | 0009504
2879 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | GRADY |  | 02 | 0009506 | This project is a roadway maintenance repaving project in Grady County. This project is the milling and resurfacing of County Road 315/17TH AVE from SR 93/SR 111 to 0.30 MI east of SR 38/US 84 for a total project length of 0.46 miles. | Pavement Improvement | 2010-02-05 | 2010-06-03 | 2010-07-31 | 2010-07-26 | 59611.55 | 0.460 | 0009506
2880 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LEE | ALBANY | 02 | 0009507 | This project is a roadway maintenance repaving project in Lee County. This project is the milling and resurfacing of County Road 227/PINEWOOD ROAD from KINCHAFOONEE CREEK to County Road 229/BRONWOOD ROAD for a total project length of 1.16 miles. | Pavement Improvement | 2010-02-04 | 2010-05-28 | 2010-07-31 | 2010-07-09 | 114349.49 | 1.160 | 0009507
2881 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LEE |  | 02 | 0009508 | This project is a roadway maintenance repaving project in Lee County. This project is the milling and resurfacing of County Road 231/NORTH PHILEMA ROAD from SR 32 to County Road 232/NEW YORK ROAD for a total project length of 4.68 miles. | Pavement Improvement | 2010-02-04 | 2010-05-28 | 2010-07-31 | 2010-07-09 | 392739.31 | 4.680 | 0009508
2882 | GEORGIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | GEORGIA | LOWNDES | VALDOSTA | 01 | 0009509 | This project is a roadway maintenance repaving project in Lowndes County. This project is the milling and resurfacing of County Road 779/HOWELL ROAD from County Road 1274/STATENVILLE to SR 7/PERIMETER ROAD for a total project length of 1.95 miles. | Pavement Improvement | 2010-01-21 | 2010-03-25 | 2010-06-30 | 2010-06-10 | 214123.38 | 1.950 | 0009509
2883 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LOWNDES | VALDOSTA | 02 | 0009510 | This project is a roadway maintenance repaving project in Lowndes County. This project is the milling and resurfacing of County Road 782/MORVEN ROAD from SR 122 to BROOKS COUNTY LINE for a total project length of 4.06 miles. | Pavement Improvement | 2010-02-04 | 2010-03-30 | 2010-07-31 | 2010-06-11 | 382144.56 | 4.060 | 0009510
2884 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MILLER |  | 02 | 0009511 | This project is a roadway maintenance repaving project in Miller County. This project is the milling and resurfacing of County Road 189/GRADY COBB ROAD from SHINGLER ROAD to THREE NOTCH ROAD for a total project length of 3.97 miles. | Pavement Improvement | 2010-02-03 | 2010-05-24 | 2010-07-31 | 2010-06-30 | 343454.18 | 3.970 | 0009511
2885 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MITCHELL |  | 02 | 0009512 | This project is a roadway maintenance repaving project in Mitchell County. This project is the milling and resurfacing of County Road 275/RIVER ROAD from SR 65 to County Road 11/SLASH ROAD for a total project length of 7.35 miles. | Pavement Improvement | 2010-02-05 | 2010-06-03 | 2010-07-31 | 2010-07-26 | 689910.75 | 7.350 | 0009512
2886 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RANDOLPH |  | 02 | 0009513 | This project is a roadway maintenance repaving project in Randolph County. This project is the milling and resurfacing of County Road 161/LOWER SHELLMAN from SR 41 to TERRELL COUNTY LINE for a total project length of 4.16 miles. | Pavement Improvement | 2010-02-05 | 2010-05-19 | 2010-07-31 | 2010-07-26 | 317738.59 | 4.160 | 0009513
2887 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | TIFT |  | 08 | 0009514 | This project is a roadway maintenance repaving project in Tift County. This project is the milling and resurfacing of County Road 418/OLD UNION ROAD from SOUTHWELL BLVD to OMEGA-ELDORADO ROAD for a total project length of 4.35 miles. | Pavement Improvement | 2010-01-21 | 2010-03-15 | 2010-07-31 | 2010-05-07 | 377064.94 | 4.350 | 0009514
2888 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WORTH |  | 08 | 0009515 | This project is a roadway maintenance repaving project in Worth County. This project is the milling and resurfacing of County Road 415/PHILLIP CAUSEY ROAD from SR 33 to County Road 412/SUMNER ROAD for a total project length of 5.48 miles. | Pavement Improvement | 2010-02-11 | 2010-05-13 | 2010-07-31 | 2010-07-31 | 371356.1 | 5.480 | 0009515
2889 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | BULLOCH |  | 12 | 0009516 | This project is a roadway maintenance repaving project in Bulloch County. This project is the milling and resurfacing of County Road 577/DENMARK-NEVILS ROAD from County Road 584/GROVELAND ROAD to SR 67 for a total project length of 2.52 miles. | Pavement Improvement | 2010-01-21 | 2010-04-08 | 2010-06-30 | 2010-05-26 | 322159.17 | 2.520 | 0009516
2890 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | CAMDEN |  | 01 | 0009517 | This project is a roadway maintenance repaving project in Camden County. This project is the milling and resurfacing of County Road 141/HARRIETTS BLUFF ROAD from DEEP CREEK to CHEMICAL PLANT for a total project length of 3.73 miles. | Pavement Improvement | 2010-02-01 | 2010-03-22 | 2010-07-31 | 2010-06-09 | 408522.94 | 3.730 | 0009517
2891 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | EFFINGHAM |  | 12 | 0009518 | This project is a roadway maintenance repaving project in Effingham County. This project is the milling and resurfacing of County Road 307/CLYO-KILDARE ROAD from SR 21 to north of PR 443 for a total project length of 10.257 miles. | Pavement Improvement | 2010-02-04 | 2010-05-05 | 2010-07-31 | 2010-06-24 | 1105065.17 | 10.257 | 0009518
2892 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | EVANS |  | 12 | 0009519 | This project is a roadway maintenance repaving project in Evans County. This project is the milling and resurfacing of County Road 233/OLD HWY 250 from TATTNALL CO LINE to County Road 204/SUNBURY ROAD for a total project length of 5.81 miles. | Pavement Improvement | 2010-01-19 | 2010-07-01 | 2010-07-31 | 2010-08-21 | 810587.86 | 5.810 | 0009519
2893 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TATTNALL |  | 12 | 0009520 | This project is a roadway maintenance repaving project in Tattnall County. This project is the milling and resurfacing of County Road 509/OLD HWY 250 from SR 73/US 301 to EVANS COUNTY LINE for a total project length of 3.89 miles. | Pavement Improvement | 2010-01-19 | 2010-07-01 | 2010-07-31 | 2010-08-21 | 563837.92 | 3.890 | 0009520
2894 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | TOOMBS |  | 12 | 0009521 | This project is a roadway maintenance repaving project in Toombs County. This project is the milling and resurfacing of County Road 335/THOMPSON POND ROAD from SR 292 to VIDALIA CITY LIMITS for a total project length of 1.4 miles. | Pavement Improvement | 2010-02-11 | 2010-03-31 | 2010-06-30 | 2010-06-07 | 268408.74 | 1.400 | 0009521
2895 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | WAYNE |  | 01 | 0009522 | This project is a roadway maintenance repaving project in Wayne County. This project is the milling and resurfacing of County Road 392/SUNSET BLVD from SR 169 to north of SR 38/US 84 for a total project length of 1.5 miles. | Pavement Improvement | 2010-01-21 | 2010-05-24 | 2010-06-30 | 2010-07-15 | 270808.79 | 1.500 | 0009522
2896 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATTOOGA |  | 11 | 0009523 | This project is a roadway maintenance repaving project in Chattooga County. This project is the milling and resurfacing of County Road 329/GORE-SUBLIGNA ROAD from SR 1/US 27 to County Road 29/JOHNSTON ROAD for a total project length of 4.29 miles. | Pavement Improvement | 2010-02-04 | 2010-05-13 | 2010-07-31 | 2010-07-09 | 484286.75 | 4.290 | 0009523
2897 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | FLOYD | ROME | 11 | 0009524 | This project is a roadway maintenance repaving project in Floyd County. This project is the milling and resurfacing of City Street 1124/BROAD STREET from SR 1/US 27 to COOSA RIVER for a total project length of 0.75 miles. | Pavement Improvement | 2010-02-05 | 2010-06-06 | 2010-06-30 | 2010-06-30 | 244519.69 | 0.750 | 0009524
2898 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | FLOYD | ROME | 11 | 0009525 | This project is a roadway maintenance repaving project in Floyd County. This project is the milling and resurfacing of City Street 642/Charlton Street from SR 1/US 27 to County Road 1050/Division Street for a total project length of 1.01 miles. | Pavement Improvement | 2010-03-11 | 2010-07-13 | 2010-06-30 | 2010-08-25 | 145684.43 | 1.010 | 0009525
2899 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | GORDON |  | 10 | 0009526 | This project is a roadway maintenance repaving project in Gordon County. This project is the milling and resurfacing of County Road 483/CRAIGTOWN ROAD from SR 225 to SR 3/US 41 for a total project length of 2.45 miles. | Pavement Improvement | 2010-01-19 | 2010-02-03 | 2010-06-30 | 2010-06-17 | 187972.56 | 2.450 | 0009526
2900 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | GORDON |  | 10 | 0009527 | This project is a roadway maintenance repaving project in Gordon County. This project is the milling and resurfacing of County Road 483/NEWTOWN CHURCH ROAD from SR 225 to County Road 21/NEWTOWN ROAD for a total project length of 1.13 miles. | Pavement Improvement | 2010-02-05 | 2010-04-06 | 2010-06-30 | 2010-06-17 | 122420.55 | 1.130 | 0009527
2901 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0009528 | This project is a roadway maintenance repaving project in Paulding County. This project is the milling and resurfacing of County Road 467/DALLAS NEBO ROAD from SR 61 to County Road 472/FROG ROAD for a total project length of 3.01 miles. | Pavement Improvement | 2010-03-03 | 2010-03-04 | 2010-07-31 | 2010-07-20 | 386427.16 | 3.010 | 0009528
2902 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 0009530 | This project is a roadway maintenance repaving project in Clayton County. This project is the milling and resurfacing of County Road 1351/REX ROAD from SR 42 to I-675 for a total project length of 0.66 miles. | Pavement Improvement | 2010-02-05 | 2010-04-19 | 2010-06-30 | 2010-05-26 | 149377.29 | 0.660 | 0009530
2903 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TURNER |  | 08 | 0009531 | This project is a roadway maintenance repaving project in Turner County. This project is the milling and resurfacing of County Road 249/WARWICK HWY from east of County Road 96/OAK GROVE to County Road 94/LEE ROAD for a total project length of 1.58 miles. | Pavement Improvement | 2010-01-19 | 2010-04-07 | 2010-06-30 | 2010-06-02 | 121085.44 | 1.580 | 0009531
2904 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0009532 | This project is a roadway maintenance repaving project in Cobb County. This project is the milling and resurfacing of County Road 1720/Windy Hill from County Road 1154/Powers Ferry Road to SR 3/US 41 for a total project length of 1.57 miles. | Pavement Improvement | 2010-02-24 | 2010-04-27 | 2010-06-30 | 2010-06-30 | 727189.84 | 1.570 | 0009532
2905 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 08 | 0009536 | "The proposed safety project is located in Newton County. This project will replace the intersection of Turner Lake Road and Clark Street currently controlled by a traffic signal with a roundabout. T | New Construction | 2010-04-29 | 2010-05-13 | 2010-11-30 | 2010-11-30 | 775622.42 | 0.800 | 0009536
2906 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CATOOSA | CHATTANOOGA (TN) | 09 | 0009540 | This project is a roadway maintenance repaving project in Catoosa County. This project is the milling and resurfacing of County Road 382/LAFAYETTE STREET from SR 151 to SR 3/US 41 for a total project length of 0.91 miles. | Pavement Improvement | 2010-02-01 | 2010-03-23 | 2010-06-30 | 2010-05-05 | 125035.57 | 1.780 | 0009540
2907 | GEORGIA | Completed | C950 | Ferryboat | GEORGIA | CHATHAM | SAVANNAH | 12 | 0009541 | This project is a Ferry Boat project with the Chatham Area Transit System (CATS) in Savannah. The funds will be used to purchase a new ferry boat for the Sanannah Belles Ferry system operated by CATS | Other | 2010-04-23 | 2010-04-23 | 2012-12-31 | 2012-03-26 | 1000000 | 0.000 | 0009541
2908 | GEORGIA | Underway | C220 | Highway Infrastructure Investment Grant | GEORGIA | POLK |  | 11 | 0009562 | This is a transportation enhancement project in Polk County in the City of Cedartown. Phase II of the Main Street project accomplishes a complete streetscape within the Cedartown Historic District. | Transportation Enhancements | 2011-03-24 | 2011-07-25 | 2012-12-31 |  | 625000 | 0.370 | 0009562
2909 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009563 | This project is an enhancement project in Fulton County. This project will install multi-use trail along the west side of Medlock Bridge Road for a distance of .1 miles just north of Grove Point Road | Transportation Enhancements | 2011-01-18 |  | 2011-08-15 |  | 84359.94 | 0.100 | 0009563
2910 | GEORGIA | Underway | C250 | Highway Infrastructure Investment Grant | GEORGIA | WASHINGTON |  | 12 | 0009598 | This project is an intersection improvement in Washington County. This project consists of intersection improvements on State Route 15 at Matthews Road in the City of Tennille. The project begins at | Safety/Traffic Management | 2010-01-19 | 2010-04-06 | 2011-09-30 |  | 2883272.29 | 0.590 | 0009598
2911 | GEORGIA | Completed | C220 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 03 | 0009601 | This is an enhancement project in Muscogee County. The project construction consists of the construction of a 10 to 12 foot multi use trail beginning at Cooper Creek Park and extending to Psalmond Ro | Transportation Enhancements | 2010-08-27 | 2010-10-21 | 2012-06-30 | 2011-11-01 | 1175017.9 | 12.000 | 0009601
2912 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | APPLING |  | 01 | 0009603 | This project will replace two bridges in Appling County. The replacement of the bridges at SR 4/US 1 at Blackwater Creek and Sweetwater Creek will be constructed in conjunction with a roadway widenin | Bridge Replacement | 2010-01-06 | 2010-01-20 | 2012-08-31 |  | 1080619.77 | 1.000 | 0009603
2913 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 08 | 0009604 | This project is a roadway widening project in Newton County. The project is to widen SR 142 from south of SR 12/US 278 to CR 72/Industrial Boulevard. The project ties to I-20 at the SR 142 interchan | Pavement Widening | 2010-01-12 | 2010-03-01 | 2012-10-31 |  | 12486733.91 | 1.110 | 0009604
2914 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | APPLING |  | 01 | 0009605 | This project is a roadway widening project in Appling County. The project will widen and reconstruct US 1/SR 4 from the Bacon County line north to SR 15. From the Bacon County line to CR 493, the US | Pavement Widening | 2010-01-06 | 2010-01-20 | 2012-08-31 |  | 31591082.32 | 9.100 | 0009605
2915 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009606 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 2509/WALTON WAY from SR 4 to SR 10 for a total project length of 1.09 miles. | Pavement Improvement | 2010-08-30 | 2010-09-29 | 2011-07-31 | 2011-07-12 | 562504.78 | 1.090 | 0009606
2916 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009607 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 1507/WALTON WAY from SR 4 to County Road 2623/JOHNS ROAD for a total project length of 1.71 miles. | Pavement Improvement | 2010-08-30 | 2010-09-29 | 2011-07-31 | 2011-07-12 | 571012.51 | 1.710 | 0009607
2917 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009608 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 1507/WALTON WAY from County Road 2623/JOHNS RD to County Road 1505/JACKSON RD for a total project length of 3.34 miles. | Pavement Improvement | 2010-08-30 | 2010-09-29 | 2011-07-31 | 2011-07-12 | 700801.97 | 3.340 | 0009608
2918 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | 0009609 | This project is a roadway maintenance repaving project in Richmond County. This project is the milling and resurfacing of County Road 475/LANEY WALKER BLVD from SR 28 to County Road 476/NEW SAVANNAH RD for a total project length of 2.73 miles. | Pavement Improvement | 2010-08-30 | 2010-09-29 | 2011-07-31 | 2011-07-12 | 873141.01 | 2.730 | 0009609
2919 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | 0009610 | This project is a safety project in Augusta/Richmond County. This project will upgrade traffic signal equipment and upgrade pedestrian accomodations at the following intersections in the City of Augu | Safety/Traffic Management | 2010-06-25 | 2011-01-11 | 2011-07-31 | 2011-12-15 | 2726605.67 | 1.040 | 0009610
2920 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009621 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 164/FLOWING WELLS ROAD from County Road 573/WHEELER ROAD to SR 104 for a total project length of 1.46 miles. | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 279472.77 | 1.460 | 0009621
2921 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009622 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 221/SOUTH OLD BELAIR ROAD from SR 383 to SR 232 for a total project length of 3.29 miles. | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 627287.11 | 3.290 | 0009622
2922 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009623 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 1236/EVANS-TO-LOCKS ROAD from SR 104 to SR 28 for a total project length of 2.59 miles. | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 516864.85 | 2.590 | 0009623
2923 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009624 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of County Road 176/OLD EVANS RD from SR 104 to the CSX Railroad Crossing (Crossing #633755T) for a total project length of 0.59 miles. | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 433701.43 | 0.590 | 0009624
2924 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COLUMBIA | AUGUSTA (SC) | 10 | 0009625 | This project is a roadway maintenance repaving project in Columbia County. This project is the milling and resurfacing of SR 28 from County Road 1236/EVANS-TO-LOCKS ROAD to SAVANNAH RIVER for a total project length of 3.92 miles. | Pavement Improvement | 2010-06-14 | 2010-07-01 | 2011-06-30 | 2010-12-31 | 694049.06 | 3.920 | 0009625
2925 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | BUTTS |  | 08 | 0009632 | This project will construct pasing lanes on State Route 42 in Butts County. The project will construct two passing lanes along a 3.08-mile stretch of SR 42/US 23 between the cities of Jackson and Jen | New Construction | 2010-01-29 | 2010-03-31 | 2012-01-31 |  | 7308819.57 | 3.079 | 0009632
2926 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TERRELL |  | 02 | 0009634 | This project is a bridge replacement on a county road in Terrell County. Project construction will replace the structurally deficient bridge at Sasser-Herod Road 164, over Chickasawhatchee Creek. T | Bridge Replacement | 2010-01-21 | 2010-02-15 | 2011-09-30 | 2011-05-10 | 1143296.85 | 0.550 | 0009634
2927 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TERRELL |  | 02 | 0009635 | This project is a bridge replacement on a county road in Terrell County. Project construction will replace the structurally deficient bridge at CR 164/Sasser-Herod Road over Brantley Creek. The exist | Bridge Replacement | 2010-01-21 | 2010-02-15 | 2011-09-30 | 2011-05-10 | 960229.2 | 0.470 | 0009635
2928 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | 0009636 | The proposed project will provide sidewalks with curb and gutter drainage, lighting, benches, trash receptacles, thermoplastic striping at cross walks, and bicycle parking. The project limits include Main Street from Towne Lake Parkway to Serenade Lane. | Transportation Enhancements | 2010-08-16 | 2010-06-17 | 2011-12-31 | 2011-12-08 | 965323.8 | 0.630 | 0009636
2929 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 06 | 0009638 | This project is a roadway widening project in Cobb County. The project will widen SR 120/Roswell Road from SR 120 Alternate to Bridgegate Drive. The initial 22% of the project is located within the | Pavement Improvement | 2010-02-05 | 2010-03-08 | 2012-12-31 |  | 10216130.63 | 1.820 | 0009638
2930 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 0009641 | This project will construct a new roadway in DeKalb County. The project consists of extending the existing Lithonia Industrial Boulevard on new location between South Stone Mountain Lithonia Road to | Pavement Widening | 2010-03-11 | 2010-03-17 | 2012-09-30 |  | 18666021.45 | 1.330 | 0009641
2931 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0009642 | This project will replace a structurally deficient bridge on County Road 467 in Paulding County. Construction will replace the bridge and approaches on County Road 467/Bakers Bridge Road over Sweetwa | Bridge Replacement | 2010-03-02 | 2010-03-17 | 2011-05-31 | 2011-09-29 | 2195289.94 | 0.430 | 0009642
2932 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0009680 | This project consists of road resurfacing on East McIntosh Road beginning at Old Atlanta Road and extending to North Hill Street. | Pavement Improvement | 2010-03-19 | 2010-05-12 | 2010-08-31 | 2010-07-19 | 234245.62 | 1.320 | 0009680
2933 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0009682 | This project consists of road resurfacing on Old Atlanta Road beginning at the Griffin City limits and extending to the Henry County line. | Pavement Improvement | 2010-03-19 | 2010-05-12 | 2010-08-31 | 2010-07-19 | 641965.28 | 5.250 | 0009682
2934 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | 0009683 | This project consists of road resurfacing at the following locations: on Old Atlanta Road from an asphalt joint north of Beatty Street to Griffin City limits, on West Popular Street from New Orleans S | Pavement Improvement | 2010-03-19 | 2010-05-12 | 2010-08-31 | 2010-07-19 | 175020.2 | 1.650 | 0009683
2935 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TIFT |  | 08 | 0009686 | This project is the replacement of a structurally deficient bridge in Tift County. Construction will replace the bridge on County Road 411/Salem Church Road at Ty Ty Creek with a new reinforced concr | Bridge Replacement | 2010-03-02 | 2010-03-04 | 2011-04-30 | 2010-12-15 | 2362947.56 | 0.760 | 0009686
2936 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | PUTNAM |  | 10 | 0009687 | This project is the widening and reconstruction of US 441 (SR 24) in Putnam County beginning just north of CR 245/Cay Road and ending at US 129/SR 44 at the Eatonton Bypass for a distance of 8.3 miles | Pavement Widening | 2010-03-19 | 2010-04-20 | 2012-05-31 |  | 34550070.72 | 8.300 | 0009687
2937 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CATOOSA | CHATTANOOGA (TN) | 09 | 0009692 | This project is a roadway maintenance repaving project in Catoosa County. This project is the milling and resurfacing of County Road 385/KEITH ROAD from SR 2 to LITTLE TIGER CREEK for a total project length of 2.44 miles. | Pavement Improvement | 2010-12-29 | 2011-03-04 | 2011-05-31 | 2011-04-13 | 294472.88 | 2.440 | 0009692
2938 | GEORGIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | CATOOSA | CHATTANOOGA (TN) | 09 | 0009693 | This project is a roadway maintenance repaving project in Catoosa County. This project is the milling and resurfacing of County Road 171/Poplar Springs Rd from County Road 390/Three Notch Rd to SR 151 for a total project length of 3.5 miles. | Pavement Improvement | 2010-05-27 | 2010-07-12 | 2010-09-30 | 2010-08-25 | 584439.96 | 3.500 | 0009693
2939 | GEORGIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | GEORGIA | BROOKS |  | 02 | 0009701 | This project is a bridge replacement project in Brooks County. The proposed project consists of the replacement of a narrow and structurally deficient bridge on CR 305 over Pride Branch. The existin | Bridge Replacement | 2010-03-02 | 2010-03-22 | 2011-04-30 | 2011-03-25 | 1821022.77 | 0.379 | 0009701
2940 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 0009703 | This project is a safety improvement in Atlanta. The project will construct a landscaped median along Ponce de Leon Avenue between Peachtree Street and Juniper Street to improve safety for pedestria | Safety/Traffic Management | 2011-03-17 |  | 2012-08-01 |  | 2250000 | 0.000 | 0009703
2941 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 0009704 | This project is an operational and safety improvement in Fulton County. This project is located at the intersection of S.R. 140/Holcomb Bridge Road and Barnwell Road/C.R. 107 in Roswell. Currently, S | Pavement Improvement | 2010-04-08 | 2010-06-22 | 2010-10-31 | 2012-02-17 | 271111.43 | 0.100 | 0009704
2942 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 07 | 0009706 | This project is a preliminary engineering project in Newton County. This project will perform the engineering plans and environmental analysis for the widening of County Road 43/Almon Road from the Rockdale County Line to I-20. | Other | 2010-06-10 | 2010-08-01 | 2012-12-31 |  | 500000 | 2.200 | 0009706
2943 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 07 | 0009707 | This project is a safety improvement in Newton County. This project will construct signal and intersection improvements at State Route 212 at County Road 19/Oak Hill Road. | Pavement Improvement | 2010-10-25 |  | 2011-09-30 | 2011-07-28 | 111875.7 | 0.400 | 0009707
2944 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON | ATLANTA | 07 | 0009708 | This project is a maintenance resurfacing project in Newton County. This project will resurface County Road 510/Gum Creek Road from State Route 81 to County Road 98/Ellis Road. The total project length is 2.51 miles. | Pavement Improvement | 2010-10-25 | 2010-11-17 | 2011-09-30 | 2011-03-08 | 399289.75 | 2.510 | 0009708
2945 | GEORGIA | Underway | C200,C240 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0009827 | This project is an Interstate widening project in Bibb County. This project will widen I-75 from two to three 12-foot travel lanes in each direction between Pierce Avenue and Arkwright Road. The proj | Pavement Widening | 2010-06-15 | 2010-08-18 | 2014-03-30 |  | 31168949.25 | 3.300 | 0009827
2946 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | 0010124 | This project is an operational improvement in Cobb County. This project will construct additional turning capacity at the Wade Green Road exit on I-75. This project will help alleviate congestion at the interchange. | Pavement Improvement | 2010-06-08 | 2010-07-06 | 2010-10-31 | 2010-10-31 | 663237.12 | 0.400 | 0010124
2947 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 04 | 0010198 | This project is a maintenance resurfacing construction project in Gwinnett County. This project will resurface three local county roads: 1.) COUNTY ROAD 1954/PEACHTREE INDUSTRIAL BOULEVARD FROM PLEA | Pavement Improvement | 2010-09-28 | 2010-10-07 | 2011-07-31 | 2010-11-22 | 2000000 |  | 0010198
2948 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 13 | 0010239 | This is a bridge construction project in DeKalb County. This project will construct a new bridge and approaches on Linecrest Road over Conley Creek. The new bridge will be 354 ft. long and 49 ft. wid | New Construction | 2010-12-29 | 2011-02-25 | 2012-04-30 | 2012-04-28 | 5299298.4 |  | 0010239
2949 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0010240 | This project is a new roadway in Paulding County. The proposed project is located on new location and begins at the intersection of Bill Carruth Parkway with SR 92 and extends northeast to tie into e | New Construction | 2011-01-25 | 2011-01-27 | 2012-07-15 |  | 13415196.1 |  | 0010240
2950 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | COOK |  | 01 | 0011061 | This project is a bridge replacement in Cook County. This project will replace the structurally deficient bridge on SR 7/US 41 over Giddens Mill Creek with a new reinforced concrete bridge. The exis | Bridge Replacement | 2009-09-24 | 2009-09-24 | 2010-09-30 | 2010-09-29 | 2009428.44 | 0.209 | 0011061
2951 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | PIKE |  | 03 | 0051034 | This project is a safety intersection improvement in Pike County. The purpose of this project is to improve the safety and operation by realigning the intersection of SR 18/SR 109 and SR 74. Current | Pavement Improvement | 2009-09-30 | 2009-10-29 | 2010-07-31 | 2010-07-30 | 1401078.13 | 0.520 | 0051034
2952 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | 0057017 | This is a bridge replacement project in Cherokee County. This project will replace a narrow and structurally deficient bridge on Howell Bridge Road (CR 107) over Sharp Mountain Creek, 2 miles southwe | Bridge Replacement | 2009-10-26 | 2009-11-30 | 2010-12-31 | 2010-08-12 | 1483456.43 | 0.130 | 0057017
2953 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COLQUITT |  | 02 | 0071028 | This project will replace the structurally deficient bridge on CR 186/Hagin Still Road over the Ochlockonee River in Colquitt County. The bridge is located southeast of the city of Doerun. The 140'x | Bridge Replacement | 2009-09-24 | 2009-09-28 | 2010-08-31 | 2010-08-02 | 1235527.02 | 0.230 | 0071028
2954 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | LOWNDES | VALDOSTA | 01 | 0073033 | This project will acquire right of way for a future construction project in the City of Valdosta in Lowndes County. The project will purchase the necessary land for the future construction of the ove | Other | 2010-09-22 | 2010-09-22 | 2013-09-30 |  | 7053399 |  | 0073033
2955 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | 00SW004 | This project will construct sidewalks on Holcomb Bridge Road in Fulton County. The construction proposes to add 5' sidewalks 2' behind the back of the existing curb on both sides of Holcomb Bridge Ro | Transportation Enhancements | 2009-11-16 | 2009-11-16 | 2010-08-31 |  | 1258115.94 | 0.490 | 00SW004
2956 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 00TS047 | This project is a safety and operational improvement in the City of Columbus in Muscogee County. This project is the installation of fiber optic communications cable and closed circuit television (CC | Safety/Traffic Management | 2010-02-11 | 2010-07-20 | 2011-06-30 |  | 1034304.2 | 0.000 | 00TS047
2957 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | MUSCOGEE | COLUMBUS (AL) | 02 | 00TS048 | This project is a safety and operational improvement in the City of Columbus in Muscogee County. The Columbus Regional Traffic Control Center (TCC) will provide the core communications and infrastruc | Safety/Traffic Management | 2010-02-11 | 2010-07-20 | 2011-06-30 |  | 689336.84 | 0.000 | 00TS048
2958 | GEORGIA | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | DOUGHERTY | ALBANY | 02 | 0133005 | This project is a roadway widening in Dougherty County. This project widens and reconstructs SR 234/Gillionville Road from Eight Mile Road to Lockett Station Road. The existing two lane roadway wil | Pavement Widening | 2009-08-19 | 2009-09-25 | 2011-09-30 |  | 7651900.03 | 2.170 | 0133005
2959 | GEORGIA | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0161092 | This project will acquire right of way for a future construction project in the City of Macon in Bibb County. The project will purchase the necessary land for the future construction of improvements | Other | 2010-09-22 | 2010-09-22 |  |  | 3833500 |  | 0161092
2960 | GEORGIA | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0161104 | This project will acquire right of way for a future construction project in the City of Macon in Bibb County. The project will purchase the necessary land for the future construction of improvements | Other | 2010-09-22 | 2010-09-22 | 2015-09-30 |  | 9182106.65 |  | 0161104
2961 | GEORGIA | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0161131 | This project will acquire right of way for a future construction project in the City of Macon in Bibb County. The project will purchase the necessary land for the future construction of improvements | Other | 2010-09-22 | 2010-09-22 |  |  | 790500 |  | 0161131
2962 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | PAULDING | ATLANTA | 11 | 0181070 | This is an intersection safety project in Paulding County. This intersection improvement is located 8.2 miles southwest of the City of Dallas on SR 61 at the intersection with County Road 472 and Cou | Pavement Improvement | 2010-03-02 | 2010-05-11 | 2010-12-31 | 2011-02-18 | 1441955.14 | 0.550 | 0181070
2963 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | TERRELL |  | 02 | 0291032 | This project is the reconstruction and rehabilitation of SR 49 in Terrell County north of the city of Dawson. The project limits begin at the junction with SR 45 and continue for 3.14 miles. SR 49 cur | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2011-04-30 |  | 3960447.86 | 2.980 | 0291032
2964 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | WILKINSON |  | 08 | 0540019 | This project is the construction of the North Gordon Bypass, a new roadway, from SR 57 at the Twiggs/Wilkinson County Line to SR 243 at Lake Tchucoloako. The total length of project is 7.2 miles. The | New Construction | 2009-09-01 | 2009-10-26 | 2012-07-31 |  | 33387811.03 | 7.200 | 0540019
2965 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | 0641049 | This is a bridge replacement project in Chatham County. This project will replace the US 17/SR 25 bridge over Norfolk Southern Railroad approximately 5.5 miles north of Savannah in Port Wentworth. T | Bridge Replacement | 2009-07-27 | 2009-07-28 | 2012-05-31 |  | 4243981.55 | 0.230 | 0641049
2966 | GEORGIA | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0661036 | This project will construct auxiliary lanes on SR 87 in Bibb County. The project will reconstruct SR 87/US 23 from an existing four-lane roadway with a 40-ft depressed median with rural shoulders to | Pavement Improvement | 2009-09-24 | 2009-11-12 | 2011-04-30 |  | 8359335.95 | 2.120 | 0661036
2967 | GEORGIA | Underway | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | 0752177 | This project will acquire right of way for a future construction project in the City of Macon in Bibb County. The project will purchase the necessary land for the future construction of improvements | Other | 2010-09-22 | 2010-09-22 | 2013-09-01 |  | 136000 |  | 0752177
2968 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0852176 | This project is the construction of an Advanced Traffic Management System along Interstate 85 in Gwinnett County. The proposed project involves the installation of fiber optic cable and High Density | Safety/Traffic Management | 2009-09-18 | 2010-01-09 | 2010-10-31 | 2010-10-31 | 2164670.45 | 4.910 | 0852176
2969 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | 0998001 | This project will rehabilitate and improve the safety at the bridge over I-85 and widening of SR 324 approaching the bridge in Gwinett County. This project replaces the two-lane bridge on Gravel Springs Road with a four-lane bridge. | Bridge Replacement | 2009-09-04 | 2009-10-02 | 2012-05-31 |  | 11912476 | 0.800 | 0998001
2970 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | 1631020 | This project is an intersection improvement in Henry County. The project will install signalization of a stop condition intersection and the addition of left and right turn lanes to SR 81 at the inte | Safety/Traffic Management | 2010-01-08 | 2010-01-20 | 2010-11-05 | 2010-11-05 | 564071.31 | 0.250 | 1631020
2971 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CLAYTON | ATLANTA | 13 | 6751001 | This project will install the NaviGAtor system along I-675 from I-75 to I-285 in Clayton, Dekalb and henry Counties. Included in the project will be two changeable message signs, vehicle detection co | Safety/Traffic Management | 2009-08-18 | 2009-08-18 | 2010-12-31 | 2011-04-30 | 1894362.88 | 10.700 | 6751001
2972 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | 7532950 | This project is a bridge replacement in Douglas County. The proposed project consists of replacing the existing structurally deficient bridge (48.43 Suff. Rating) along County Road 815/Anneewakee Roa | Bridge Replacement | 2009-09-24 | 2009-10-23 | 2010-12-31 | 2010-12-16 | 1876015.68 | 0.419 | 7532950
2973 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | 9014024 | This project is a culvert replacement in Dekalb County. The proposed project will replace the existing box culvert and wooden pedestrian bridge on SR 155/Candler Road at Shoal Creek with a larger con | Bridge Replacement | 2009-09-23 | 2009-11-12 | 2011-03-31 |  | 1394072.48 | 0.260 | 9014024
2974 | GEORGIA | Underway | C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | 9161001 | The proposed project would replace the existing Mitchell Street Bridge located over CSX Railroad between Techwood Drive and Spring Street. The existing bridge is in need of replacement due to inadequa | Bridge Replacement | 2010-01-05 | 2010-03-29 | 2012-05-31 |  | 8559194.8 | 0.578 | 9161001
2975 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | 9398001 | This project is the construction of intersection improvements on Kings Highway at Central Church Road in Douglas County. The project will provide a separate left turn bay for westbound movements onto | Safety/Traffic Management | 2009-09-18 | 2009-11-12 | 2011-04-30 | 2011-03-01 | 709598.68 | 0.330 | 9398001
2976 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | JASPER |  | 08 | M000355 | This project will construct maintenance improvements in Jasper County. This project consists of drainage improvements at the intersection of State Route 83 and Church Street in the City of Monticello | Pavement Improvement | 2010-10-25 | 2011-02-01 | 2011-09-30 | 2011-11-30 | 201098.85 |  | M000355
2977 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BULLOCH |  | 12 | M003694 | This project is a maintenance construction project in Bulloch County. This project is the resurfacing of SR 26. This section of SR 26 needs resurfacing because the existing pavement is deteriorating. SR 26 was last resurfaced in 1998. | Pavement Improvement | 2010-01-19 | 2010-07-30 | 2010-10-31 | 2010-10-26 | 2055114.84 | 10.810 | M003694
2978 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | ROCKDALE | ATLANTA | 04 | M003836 | This is a maintenance construction project in Rockdale County. This project is the milling and resurfacing of SR 162 from the Newton County Line to County Road 666/Dogwood Drive. This section of SR | Pavement Improvement | 2009-07-17 | 2009-08-13 | 2010-05-31 | 2009-10-02 | 375211.24 | 2.390 | M003836
2979 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | EFFINGHAM |  | 12 | M003841 | This project is a maintenance construction project in Effingham County. This project is the resurfacing of SR 26. This section of SR 26 needs resurfacing because the existing pavement is deteriorating. SR 26 was last resurfaced in 1981. | Pavement Improvement | 2010-01-12 | 2010-06-16 | 2010-08-31 | 2010-08-30 | 1238031.3 | 5.390 | M003841
2980 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JACKSON |  | 10 | M003862 | This project is a maintenance construction project in Jackson County. This project is the resurfacing of SR 82. This section of SR 82 needs resurfacing because the existing pavement is deteriorating. SR 82 was last resurfaced in 1998. | Pavement Improvement | 2009-07-20 | 2010-01-15 | 2010-05-31 | 2010-05-26 | 919166.88 | 6.200 | M003862
2981 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | QUITMAN |  | 02 | M003896 | This project is a maintenance construction project in Quitman and Randolph Counties. This project is the milling and resurfacing of SR 50. This section of SR 50 needs resurfacing because the existing | Pavement Improvement | 2009-06-19 | 2010-01-15 | 2010-03-31 | 2010-03-31 | 2400679.95 | 11.260 | M003896
2982 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COFFEE |  | 01 | M003897 | This is a maintenance construction project in Coffee County. This project is the milling and resurfacing of SR 31/US 441 from SR 135 to City Street 787/McNeal Drive. This section of SR 31 needs resur | Pavement Improvement | 2009-07-06 | 2009-08-26 | 2010-04-30 | 2010-01-27 | 619287.72 | 2.400 | M003897
2983 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | DOUGHERTY | ALBANY | 02 | M003898 | This project is a maintenance construction project in Dougherty County. The project is the milling and resurfacing of SR 133 from SR 91 to the Lee County Line. This section of SR 133 needs resurfacin | Pavement Improvement | 2009-06-19 | 2009-07-30 | 2010-01-31 | 2009-09-30 | 212840.33 | 1.070 | M003898
2984 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MADISON |  | 10 | M003906 | This is a maintenance construction project in Madison County. The project is the resurfacing of SR 98 from SR 8/US 29 to SR 72. Ths section of SR 98 needs resurfacing because the existing pavement is deteriorating. SR 98 was last resurfaced in 1983. | Pavement Improvement | 2009-06-25 | 2009-07-25 | 2010-03-31 | 2009-09-25 | 727428.34 | 7.400 | M003906
2985 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TOWNS |  | 10 | M003907 | This is a maintenance construction project in Towns County. The project is the milling and rsurfacing of SR 75 from SR 2 to the North carolina State Line. This section of SR 75 needs resurfacing beca | Pavement Improvement | 2009-06-19 | 2009-08-17 | 2010-03-31 | 2009-11-03 | 499471.21 | 3.400 | M003907
2986 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | M003908 | This is a maintenance construction project in Hall County. The project is the resurfacing of SR 283 from SR 60 to SR 52/Dahlonega Highway. This section of SR 283 needs resurfacing because the existin | Pavement Improvement | 2009-06-25 | 2009-08-24 | 2010-04-30 | 2009-11-20 | 1256437.78 | 9.300 | M003908
2987 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MONTGOMERY |  | 03 | M003909 | This project is a maintenance construction project in Jeff Davis and Montgomery Counties. This project is the resurfacing of SR 135. This section of SR 135 needs resurfacing because the existing pave | Pavement Improvement | 2009-07-17 | 2010-01-29 | 2010-05-31 | 2010-06-04 | 3005126.83 | 18.570 | M003909
2988 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | M003910 | This project is a maintenance construction project in Chatham County. This project is the milling and resurfacing of SR 307. This section of SR 307 needs resurfacing because the existing pavement is deteriorating. SR 307 was last resurfaced in 1988. | Pavement Improvement | 2009-06-30 | 2010-02-10 | 2010-04-30 | 2010-04-30 | 1218927.47 | 5.940 | M003910
2989 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 12 | M003911 | This project is a maintenance construction project in Chatham County. This project is the milling and resurfacing of SR 30. This section of SR 30 needs resurfacing because the existing pavement is deteriorating. SR 30 was last resurfaced in 1975. | Pavement Improvement | 2009-06-30 | 2010-02-10 | 2010-04-30 | 2010-04-30 | 145754.78 | 0.980 | M003911
2990 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BACON |  | 01 | M003914 | This project is a maintenance construction project in Bacon County. This project is the milling and resurfacing of SR 32. This section of SR 32 needs resurfacing because the existing pavement is deteriorating. SR 32 was last resurfaced in 1998. | Pavement Improvement | 2009-06-30 | 2009-12-17 | 2010-03-31 | 2010-03-31 | 1104555.89 | 4.560 | M003914
2991 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHARLTON |  | 01 | M003916 | This is a maintenance construction project in Charlton County. The project is the resurfacing of SR 4/US 1 from north of SR 4 to the Ware County Line. This section of SR 4 needs resurfacing because t | Pavement Improvement | 2009-06-25 | 2009-07-13 | 2010-04-30 | 2010-01-15 | 3662131.81 | 11.730 | M003916
2992 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHARLTON |  | 01 | M003917 | This is a maintenance construction project in Charlton County. This project is the resurfacing of SR 40 Connector from SR 40 to SR 4. This section of SR 40 Connector needs resurfacing because the exis | Pavement Improvement | 2009-06-25 | 2009-07-13 | 2010-04-30 | 2010-01-15 | 184320.81 | 1.330 | M003917
2993 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WALKER |  | 09 | M003920 | This project is a maintenance construction project in Walker County. This project is the milling and resurfacing of SR 1 Businesss. This section of SR 1 Business needs resurfacing because the existin | Pavement Improvement | 2009-07-06 | 2009-09-10 | 2010-04-30 | 2010-04-30 | 721762.53 | 3.340 | M003920
2994 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BARTOW |  | 11 | M003921 | This is a maintenance construction project in Bartow County. This project is the milling and resurfacing of SR 3 from south of Peachtree Street to north of MLK Jr. Drive in Cartersville. This sectio | Pavement Improvement | 2009-06-25 | 2009-08-18 | 2010-04-30 | 2010-03-31 | 629628.01 | 1.630 | M003921
2995 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | M003923 | This project is a maintenance construction project in Cherokee County. This project is the resurfacing on SR 140. This section of SR 140 needs resurfacing because the existing pavement is deteriorating. SR 140 was last resurfaced in 1990. | Pavement Improvement | 2009-06-25 | 2009-09-08 | 2010-03-31 | 2010-03-31 | 1639784.29 | 10.610 | M003923
2996 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | SUMTER |  | 02 | M003932 | This is a maintenance construction project in Sumter County. This project is the milling and resurfacing of SR 27 West from SR 27 to SR 3/US 19 in Americus. This section of SR 27 West needs resurfaci | Pavement Improvement | 2009-06-25 | 2009-08-02 | 2009-12-31 | 2009-11-23 | 553607.37 | 2.130 | M003932
2997 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | SUMTER |  | 02 | M003933 | This is a maintenance construction project in Sumter County. This project is the milling and resurfacing of SR 27 from SR 3/US 19 to SR 27 West/SR 30 in Americus. This section of SR 27 needs resurfac | Pavement Improvement | 2009-06-25 | 2009-08-02 | 2009-12-31 | 2009-11-23 | 587913.19 | 2.136 | M003933
2998 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | M003935 | This project is a maintenance construction project in Richmond County. This project is the milling and resurfacing of SR 28. This section of SR 28 needs resurfacing because the existing pavement is deteriorating. SR 28 was last resurfaced in 1995. | Pavement Improvement | 2009-10-26 | 2010-02-21 | 2010-06-30 | 2010-04-30 | 953238.52 | 2.720 | M003935
2999 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DODGE |  | 03 | M003938 | This is a maintenance construction project in Dodge County. This project is the milling and resurfacing of SR 117 from south of Front Street to Sugar Creek Bridge. This section of SR 117 needs resurf | Pavement Improvement | 2009-06-22 | 2009-07-09 | 2010-03-31 | 2009-10-29 | 2143580.71 | 13.620 | M003938
3000 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JEFFERSON |  | 12 | M003941 | This project is a maintenance construction project in Jefferson County. This project is the milling and resurfacing of SR 4. This section of SR 4 needs resurfacing because the existing pavement is deteriorating. SR 4 was last resurfaced in 2000. | Pavement Improvement | 2009-10-26 | 2010-04-29 | 2010-08-31 | 2010-08-26 | 3438984.42 | 13.610 | M003941
3001 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | M003942 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 9 from the Chattahoochee River to Marietta Highway. This section of SR 9 needs resurfaci | Pavement Improvement | 2009-06-25 | 2009-08-02 | 2010-04-30 | 2010-01-11 | 294065.27 | 1.210 | M003942
3002 | GEORGIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | M003943 | This is a maintenance construction project in Clayton and Fulton Counties. This project is the milling and resurfacing of SR 3/US 19 from Interstate 285 to City Street 3096/Cleveland Avenue. This sec | Pavement Improvement | 2009-06-26 | 2009-07-07 | 2010-03-31 | 2009-11-09 | 926853.22 | 4.170 | M003943
3003 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 06 | M003945 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 9 from Abernathy Road to the Chattahoochee River. This section of SR 9 needs resurfacing | Pavement Improvement | 2009-06-25 | 2009-08-02 | 2010-04-30 | 2010-01-11 | 1380129.96 | 5.200 | M003945
3004 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | M003946 | This project is a maintenance construction project in DeKalb and Gwinnett Counties. This project is the milling and resurfacing of SR 10. This section of SR 10 needs resurfacing because the existing | Pavement Improvement | 2009-08-14 | 2010-04-16 | 2010-06-30 | 2010-08-25 | 3210565.33 | 3.830 | M003946
3005 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 13 | M003947 | This project is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 14 Spur. This section of SR 14 Spur needs resurfacing because the existing pavem | Pavement Improvement | 2009-08-07 | 2010-03-05 | 2010-06-30 | 2010-05-20 | 623958.16 | 1.610 | M003947
3006 | GEORGIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | M003948 | This is a maintenance construction project in Fulton County. This project is the resurfacing of SR 139 from West Whitehall Street to County Road 4176/Cascade Avenue. This section of SR 139 needs resu | Pavement Improvement | 2009-06-19 | 2009-08-11 | 2010-03-31 | 2009-10-09 | 374760.91 | 1.210 | M003948
3007 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | M003949 | This is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 54 from north of I-285 to University Avenue. This section of SR 54 needs resurfacing bec | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2010-06-30 | 2010-04-08 | 1249406.17 | 5.870 | M003949
3008 | GEORGIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 13 | M003950 | This project is a maintenance construction project in Fulton County. This project is the milling and resurfacing of SR 92. This section of SR 92 needs resurfacing because the existing pavement is deteriorating. SR 92 was last resurfaced in 2002. | Pavement Improvement | 2009-06-25 | 2009-09-23 | 2010-03-31 | 2009-12-03 | 830939.77 | 3.830 | M003950
3009 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | M003957 | This project is a maintenance construction project in Hall County. This project is the resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deteriorating. SR 11 was last resurfaced in 1997. | Pavement Improvement | 2009-06-25 | 2009-09-10 | 2010-04-30 | 2009-12-16 | 1151859.25 | 3.000 | M003957
3010 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DAWSON |  | 09 | M003958 | This project is a maintenance construction project in Dawson County. This project is the resurfacing of SR 53. This section of SR 53 needs resurfacing because the existing pavement is deteriorating. SR 53 was last resurfaced in 1998. | Pavement Improvement | 2009-06-25 | 2009-11-19 | 2010-03-31 | 2010-04-29 | 1216249.24 | 6.800 | M003958
3011 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HABERSHAM |  | 10 | M003959 | This project is a maintenance construction project in Habersham County. This project is the resurfacing of SR 384. This section of SR 384 needs resurfacing because the existing pavement is deteriorating. SR 384 was last resurfaced in 1999. | Pavement Improvement | 2009-06-25 | 2009-11-02 | 2010-03-31 | 2009-12-04 | 607850.87 | 4.200 | M003959
3012 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FRANKLIN |  | 10 | M003960 | This is a maintenance construction project in Franklin County. This project is the resurfacing of SR 51 from SR 59 to County Road 168/Hale Crossing Road. This section of SR 51 needs resurfacing becau | Pavement Improvement | 2009-06-25 | 2009-08-25 | 2010-03-31 | 2009-10-29 | 956633.95 | 9.900 | M003960
3013 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WHITE |  | 09 | M003961 | This is a maintenance construction project in Habersham and White Counties. The project is the resurfacing of SR 356 from SR 17 in White County to SR 197 in Habersham County. This section of SR 356 n | Pavement Improvement | 2009-06-25 | 2009-07-20 | 2010-04-30 | 2009-11-03 | 1576840.87 | 10.830 | M003961
3014 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FORSYTH | ATLANTA | 09 | M003964 | This project is a maintenance construction project in Forsyth County. This project is the milling and resurfacing of SR 9. This section of SR 9 needs resurfacing because the existing pavement is deteriorating. SR 9 was last resurfaced in 2004. | Pavement Improvement | 2009-06-25 | 2009-09-30 | 2010-03-31 | 2010-02-08 | 1863277.68 | 9.800 | M003964
3015 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | STEPHENS |  | 10 | M003965 | This project is a maintenance construction project in Banks, Franklin and Stephens Counties. This project is the resurfacing of SR 63. This section of SR 63 needs resurfacing because the existing pav | Pavement Improvement | 2009-07-21 | 2009-09-08 | 2010-05-31 | 2010-01-04 | 1766787.98 | 12.630 | M003965
3016 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BANKS |  | 10 | M003966 | This project is a maintenance construction project in Banks County. This project is the resurfacing of SR 164. This section of SR 164 needs resurfacing because the existing pavement is deteriorating. SR 164 was last resurfaced in 1993. | Pavement Improvement | 2009-06-25 | 2009-11-04 | 2010-04-30 | 2010-01-07 | 694742.2 | 4.800 | M003966
3017 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | M003967 | This is an Interstate 575 maintenance construction project in Cobb and Cherokee Counties. This project is the milling and resurfacing of I-575/SR 417 from I-75 in Cobb County to the Etowah River in C | Pavement Improvement | 2009-06-25 | 2009-07-13 | 2010-05-31 | 2009-11-12 | 16297046.6 | 19.790 | M003967
3018 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MARION |  | 02 | M003968 | This is a maintenance construction project in Marion County. This project is the milling and resurfacing of SR 137 from City Street 505/McDuffie Street to the Taylor County line. This section of SR 1 | Pavement Improvement | 2009-06-25 | 2009-09-09 | 2010-04-30 | 2009-12-04 | 1330615.64 | 10.530 | M003968
3019 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CRAWFORD |  | 02 | M003969 | This is a maintenance construction project in Crawford and Peach Counties. The project is the milling and resurfacing of SR 7 from SR 96 in Peach County to SR 22/US 80 in Crawford County. This sectio | Pavement Improvement | 2009-07-17 | 2009-08-06 | 2010-04-30 | 2009-10-28 | 2179878.11 | 14.370 | M003969
3020 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | SCHLEY |  | 02 | M003970 | This project is a maintenance construction project in Schley and Sumter Counties. This project is the milling and resurfacing of SR 153. This section of SR 153 needs resurfacing because the existing | Pavement Improvement | 2009-06-25 | 2010-02-11 | 2010-04-30 | 2010-04-30 | 1283555.96 | 8.100 | M003970
3021 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HENRY | ATLANTA | 03 | M003971 | This is a maintenance construction project in Henry County. This project is the milling and resurfacing of SR 155 from the Spalding County line to SR 20/SR 81. This section of SR 155 needs resurfacin | Pavement Improvement | 2009-06-25 | 2009-08-04 | 2010-04-30 | 2010-02-25 | 1741736.54 | 8.800 | M003971
3022 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JASPER |  | 08 | M003972 | This project is a maintenance construction project in Jasper County. This project is the milling and resurfacing of SR 83. This section of SR 83 needs resurfacing because the existing pavement is deteriorating. SR 83 was last resurfaced in 1985. | Pavement Improvement | 2009-06-25 | 2009-08-31 | 2010-04-30 | 2010-04-30 | 1854234.74 | 12.790 | M003972
3023 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | M003973 | This project is a maintenance construction project in Richmond County. This project is the milling and resurfacing of SR 4. This section of SR 4 needs resurfacing because the existing pavement is deteriorating. SR 4 was last resurfaced in 1992. | Pavement Improvement | 2009-08-20 | 2009-10-20 | 2010-06-30 | 2010-05-31 | 3651665.3 | 10.200 | M003973
3024 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JASPER |  | 08 | M003974 | This is a maintenance construction project in Jasper County. This project is the milling and resurfacing of SR 16 from the Butts County line to SR 11 South. This section of SR 16 needs resurfacing be | Pavement Improvement | 2009-06-25 | 2009-08-03 | 2010-04-30 | 2009-10-22 | 1430257.97 | 8.950 | M003974
3025 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | PUTNAM |  | 10 | M003975 | This project is a maintenance construction project in Putnam County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is deteriorating. SR 16 was last resurfaced in 1987. | Pavement Improvement | 2009-06-19 | 2009-09-28 | 2010-04-30 | 2010-04-30 | 1591401.64 | 8.300 | M003975
3026 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TWIGGS |  | 08 | M003976 | This project is a maintenance construction project in Bleckley, Laurens and Twiggs Counties. This project is the concrete slab replacement of I-16/SR 404. This slab replacement of I-16 is needed becau | Pavement Improvement | 2009-11-19 | 2010-02-02 | 2011-05-31 | 2012-03-09 | 22877913.19 | 15.320 | M003976
3027 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHATHAM | SAVANNAH | 01 | M003977 | This project is an interstate resurfacing project in Bryan and Chatham counties on I-95. This section of I-95 needs resurfacing because the existing pavement is deteriorating. I-95/SR 405 was last resurfaced in 1997. | Pavement Improvement | 2010-01-21 | 2010-06-01 | 2010-12-31 | 2011-05-20 | 8428494.63 | 11.700 | M003977
3028 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WARE |  | 01 | M003978 | This is a maintenance construction project in Ware County. This project is the milling and resurfacing of SR 4 Business/US 1 from south of County Road 341/Short Street to north of County Road 255/Smi | Pavement Improvement | 2009-06-25 | 2009-07-20 | 2010-04-30 | 2009-10-07 | 988515.6 | 5.790 | M003978
3029 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | EFFINGHAM |  | 12 | M003979 | This project is a maintenance construction project in Effingham County. This project is the resurfacing of SR 17. This section of SR 17 needs resurfacing because the existing pavement is deteriorating. SR 17 was last resurfaced in 1999. | Pavement Improvement | 2009-06-30 | 2009-09-15 | 2010-04-30 | 2009-12-15 | 692915.25 | 4.120 | M003979
3030 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | CHARLTON |  | 01 | M003980 | This project is a maintenance construction project in Brantley and Charlton Counties. This project is the resurfacing of SR 23. This section of SR 23 needs resurfacing because the existing pavement is deteriorating. SR 23 was last resurfaced in 1994. | Pavement Improvement | 2009-07-06 | 2010-02-17 | 2010-04-30 | 2010-08-02 | 3231244.89 | 23.150 | M003980
3031 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BRYAN |  | 01 | M003981 | This project is a maintenance construction project in Bryan County. This project is the resurfacing of SR 25. This section of SR 25 needs resurfacing because the existing pavement is deteriorating. SR 25 was last resurfaced in 1992. | Pavement Improvement | 2009-08-20 | 2009-11-19 | 2010-06-30 | 2010-04-26 | 1604170.73 | 4.280 | M003981
3032 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | ROCKDALE | ATLANTA | 04 | M003983 | This is a maintenance construction project in Rockdale County. This project is the resurfacing of SR 20 from County Road 435/Sigman Road to SR 138. This section of SR 20 needs resurfacing because the | Pavement Improvement | 2009-06-25 | 2009-07-08 | 2010-04-30 | 2009-08-25 | 282533.36 | 1.340 | M003983
3033 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | ROCKDALE | ATLANTA | 04 | M003984 | This project is a maintenance construction project in Rockdale County. This project is the resurfacing of SR 20. This section of SR 20 needs resurfacing because the existing pavement is deteriorating. SR 20 was last resurfaced in 1990. | Pavement Improvement | 2009-08-07 | 2009-09-08 | 2010-06-30 | 2010-05-20 | 2602999.5 | 6.990 | M003984
3034 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DE KALB | ATLANTA | 04 | M003985 | This project is a maintenance construction project in DeKalb County. This project is the resurfacing of SR 236/LaVista Road. This section of SR 236 needs resurfacing because the existing pavement is deteriorating. SR 236 was last resurfaced in 1988. | Pavement Improvement | 2009-08-17 | 2009-09-08 | 2010-06-30 | 2010-06-04 | 951396.82 | 2.400 | M003985
3035 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COBB | ATLANTA | 11 | M003986 | This project is a maintenance construction project in Cobb County. This project is the resurfacing of SR 360. This section of SR 360 needs resurfacing because the existing pavement is deteriorating. SR 360 was last resurfaced in 1984. | Pavement Improvement | 2009-08-07 | 2010-04-11 | 2010-06-30 | 2010-06-30 | 413662.76 | 2.970 | M003986
3036 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | M003987 | This project is a maintenance construction project in Bibb County. This project is the resurfacing of SR 87. This section of SR 87 needs resurfacing because the existing pavement is deteriorating. SR 87 was last resurfaced in 1997. | Pavement Improvement | 2010-01-21 | 2010-03-16 | 2010-08-31 | 2010-09-02 | 2263901.33 | 14.460 | M003987
3037 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | M003988 | This project is a maintenance construction project in Bibb County. This project is the resurfacing of SR 49. This section of SR 49 needs resurfacing because the existing pavement is deteriorating. SR 49 was last resurfaced in 1989. | Pavement Improvement | 2010-01-21 | 2010-03-16 | 2010-08-31 | 2010-09-02 | 66326.32 | 0.270 | M003988
3038 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WEBSTER |  | 02 | M003989 | This project is a maintenance construction project in Marion and Webster Counties. This project is the resurfacing of SR 41. This section of SR 41 needs resurfacing because the existing pavement is deteriorating. SR 41 was last resurfaced in 1996. | Pavement Improvement | 2009-07-20 | 2010-04-05 | 2010-05-31 | 2010-05-31 | 1679983.13 | 12.570 | M003989
3039 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TAYLOR |  | 02 | M003990 | This project is a maintenance construction project in Crawford and Taylor Counties. This project is the resurfacing of SR 128. This section of SR 128 needs resurfacing because the existing pavement is deteriorating. SR 128 was last resurfaced in 1999. | Pavement Improvement | 2009-06-25 | 2010-03-01 | 2010-04-30 | 2010-04-30 | 2164467.83 | 14.090 | M003990
3040 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | HARRIS |  | 03 | M003991 | This is a maintenance construction project in Harris County. This project is the resurfacing of SR 18 from SR 219 to SR 1/US 27. This section of SR 18 needs resurfacing because the existing pavement is deteriorating. SR 18 was last resurfaced in 1993. | Pavement Improvement | 2009-06-25 | 2009-08-06 | 2010-04-30 | 2009-11-10 | 1674600.99 | 11.480 | M003991
3041 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | GREENE |  | 10 | M003992 | This is a maintenance construction project in Greene County. The project is the resurfacing of SR 44 from the Putnam County line to SR 12. This section of SR 44 needs resurfacing because the existing | Pavement Improvement | 2009-06-19 | 2009-08-11 | 2010-04-30 | 2009-11-16 | 2181083.77 | 11.450 | M003992
3042 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 12 | M003993 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 56 Spur. This section of SR 56 Spur needs resurfacing because the existing pavement is deteriorating. SR 56 Spur was last resurfaced in 1995. | Pavement Improvement | 2009-11-30 | 2010-04-12 | 2010-09-30 | 2010-06-18 | 2296796.29 | 6.580 | M003993
3043 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | NEWTON |  | 08 | M003994 | This project is a maintenance construction project in Newton County. This project is the resurfacing of SR 142. This section of SR 142 needs resurfacing because the existing pavement is deteriorating. SR 142 was last resurfaced in 1988. | Pavement Improvement | 2010-01-05 | 2010-02-01 | 2010-08-31 | 2010-09-24 | 1219852.67 | 8.300 | M003994
3044 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JASPER |  | 08 | M003995 | This project is a maintenance construction project in Jasper County. This project is the resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is deteriorating. SR 16 was last resurfaced in 1994. | Pavement Improvement | 2010-01-21 | 2010-03-03 | 2010-08-31 | 2010-08-30 | 1495888.73 | 8.600 | M003995
3045 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | LOWNDES | VALDOSTA | 02 | M003998 | This project is an interstate resurfacing project in Lowndes County. This project is the milling and resurfacing of I-75/SR 401. This section of I-75 needs resurfacing because the existing pavement is deteriorating. I-75 was last resurfaced in 1995. | Pavement Improvement | 2010-01-14 | 2010-04-26 | 2010-12-31 | 2010-12-31 | 19987728.08 | 18.050 | M003998
3046 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BRYAN |  | 01 | M004000 | This project is a maintenance construction project in Bryan County. This project is the resurfacing of SR 30/US 280. This section of SR 30 needs resurfacing because the existing pavement is deteriorating. SR 30 was last resurfaced in 1992. | Pavement Improvement | 2009-07-20 | 2009-09-16 | 2010-05-31 | 2010-04-30 | 1845487.01 | 8.850 | M004000
3047 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WHEELER |  | 01 | M004001 | This project is a maintenance construction project in Montgomery and Wheeler Counties. This project is the resurfacing of SR 30. This section of SR 30 needs resurfacing because the existing pavement is deteriorating. SR 30 was last resurfaced in 1997. | Pavement Improvement | 2009-07-17 | 2009-10-09 | 2010-05-31 | 2010-01-12 | 1859265.88 | 11.520 | M004001
3048 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WHEELER |  | 01 | M004003 | This project is a maintenance construction project in Wheeler County. This project is the resurfacing of SR 126. This section of SR 126 needs resurfacing because the existing pavement is deteriorating. SR 126 was last resurfaced in 1998. | Pavement Improvement | 2009-07-20 | 2010-04-07 | 2010-05-31 | 2010-06-08 | 1653201.91 | 12.090 | M004003
3049 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | WILKES |  | 10 | M004006 | This project is a maintenance construction project in Lincoln and Wilkes Counties. This project is the resurfacing of SR 47. This section of SR 47 needs resurfacing because the existing pavement is deteriorating. SR 47 was last resurfaced in 1995. | Pavement Improvement | 2009-09-21 | 2010-04-22 | 2010-07-31 | 2010-07-09 | 2217730.8 | 15.690 | M004006
3050 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | EMANUEL |  | 12 | M004011 | This project is a maintenance construction project in Emmanuel County. This project is the resurfacing of SR 297. This section of SR 297 needs resurfacing because the existing pavement is deteriorating. SR 297 was last resurfaced in 1997. | Pavement Improvement | 2010-01-29 | 2010-06-08 | 2010-08-31 | 2010-08-31 | 1869884.29 | 9.930 | M004011
3051 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | M004012 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 104. This section of SR 104 needs resurfacing because the existing pavement is deteriorating. SR 104 was last resurfaced in 1991. | Pavement Improvement | 2009-11-23 | 2010-06-02 | 2010-06-30 | 2010-07-27 | 110170.87 | 0.450 | M004012
3052 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | RICHMOND | AUGUSTA (SC) | 10 | M004013 | This project is a maintenance construction project in Richmond County. This project is the resurfacing of SR 104 East. This section of SR 104 East needs resurfacing because the existing pavement is deteriorating. SR 104 East was last resurfaced in 1991. | Pavement Improvement | 2009-11-23 | 2010-06-02 | 2010-06-30 | 2010-07-27 | 83759.02 | 0.440 | M004013
3053 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | FRANKLIN |  | 10 | M004014 | This projects provides maintenance construction on I-85 in Franklin and Hart Counties. This project is the milling and resurfacing of I-85/SR 403 from south of SR 17 in Franklin County to the South C | Pavement Improvement | 2009-09-03 | 2010-04-12 | 2010-07-31 | 2010-06-03 | 5329099.85 | 7.120 | M004014
3054 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HALL | GAINESVILLE | 09 | M004015 | This project is a maintenance construction project in Hall County. This project is the removal of selected concrete slabs on SR 365. The reason for removal and replacement of the selected concrete sl | Pavement Improvement | 2009-07-29 | 2009-11-12 | 2010-05-31 | 2010-06-09 | 2044514.37 | 7.970 | M004015
3055 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HOUSTON | WARNER ROBINS | 08 | M004020 | This project is a maintenance construction project in Houston County. This project is the milling and resurfacing of SR 127. This section of SR 127 needs resurfacing because the existing pavement is deteriorating. SR 127 was last resurfaced in 1991. | Pavement Improvement | 2010-01-19 | 2010-02-19 | 2010-08-31 | 2010-06-29 | 128526.09 | 0.750 | M004020
3056 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HOUSTON | WARNER ROBINS | 08 | M004021 | This project is a maintenance construction project in Houston County. This project is the resurfacing of SR 11 Business. This section of SR 11 Business needs resurfacing because the existing pavement | Pavement Improvement | 2009-08-17 | 2010-04-05 | 2010-04-30 | 2010-05-13 | 761011.16 | 4.500 | M004021
3057 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | PULASKI |  | 08 | M004025 | This project is a maintenance construction project in Pulaski County. This project is the resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deteriorating. SR 11 was last resurfaced in 1996. | Pavement Improvement | 2009-11-23 | 2010-07-15 | 2010-09-30 | 2010-09-30 | 1689883.06 | 10.580 | M004025
3058 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MERIWETHER |  | 03 | M004027 | This project is a maintenance construction project in Meriwether County. This project is the resurfacing of SR 85. This section of SR 85 needs resurfacing because the existing pavement is deteriorating. SR 85 was last resurfaced in 1996. | Pavement Improvement | 2009-12-04 | 2010-06-01 | 2010-09-30 | 2010-08-27 | 1645987.83 | 11.100 | M004027
3059 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOOLY |  | 02 | M004028 | This project is a maintenance construction project in Dooly County. This project is the resurfacing of SR 27. This section of SR 27 needs resurfacing because the existing pavement is deteriorating. SR 27 was last resurfaced in 1988. | Pavement Improvement | 2009-11-23 | 2010-08-16 | 2010-09-30 | 2010-09-30 | 1863860.66 | 11.760 | M004028
3060 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | FAYETTE | ATLANTA | 03 | M004029 | This project is a maintenance construction project in Fayette County. This project is the resurfacing of SR 85. This section of SR 85 needs resurfacing because the existing pavement is deteriorating. SR 85 was last resurfaced in 1996. | Pavement Improvement | 2009-11-19 | 2010-06-07 | 2010-09-30 | 2010-09-30 | 2065892.07 | 9.880 | M004029
3061 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | M004030 | This project is a maintenance construction project in Bibb County. This project is the milling and resurfacing of SR 11. This section of SR 11 needs resurfacing because the existing pavement is deteriorating. SR 11 was last resurfaced in 1999. | Pavement Improvement | 2009-11-19 | 2010-05-18 | 2010-08-31 | 2010-09-02 | 1272250 | 5.330 | M004030
3062 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | COWETA | ATLANTA | 03 | M004031 | This project is a maintenance construction project in Coweta County. This project is the resurfacing of SR 154. This section of SR 154 needs resurfacing because the existing pavement is deteriorating. SR 154 was last resurfaced in 1996. | Pavement Improvement | 2009-11-24 | 2010-04-30 | 2010-09-30 | 2010-08-12 | 1434654.23 | 8.360 | M004031
3063 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | UPSON |  | 03 | M004032 | This project is a maintenance construction project in Lamar and Upson Counties. This project is the resurfacing of SR 36. This section of SR 36 needs resurfacing because the existing pavement is deteriorating. SR 36 was last resurfaced in 1998. | Pavement Improvement | 2009-11-19 | 2010-08-17 | 2010-09-30 | 2010-10-14 | 2538255 | 15.030 | M004032
3064 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | LAMAR |  | 03 | M004033 | This project is a maintenance construction project in Lamar and Monroe Counties. This project is the resurfacing of SR 7. This section of SR 7 needs resurfacing because the existing pavement is deteriorating. SR 7 was last resurfaced in 1999. | Pavement Improvement | 2009-11-19 | 2010-06-22 | 2010-09-30 | 2010-09-30 | 2262804.83 | 15.000 | M004033
3065 | GEORGIA | Completed | C200,C240 | Highway Infrastructure Investment Grant | GEORGIA | SPALDING | ATLANTA | 03 | M004034 | This project is a maintenance construction project in Spalding County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is deteriorating. SR 16 was last resurfaced in 1999. | Pavement Improvement | 2010-01-05 | 2010-07-26 | 2010-06-30 | 2010-08-31 | 1273339.14 | 4.090 | M004034
3066 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | HOUSTON | WARNER ROBINS | 08 | M004035 | This project is a maintenance construction project in Houston County. This project is the milling and resurfacing of SR 247. This section of SR 247 needs resurfacing because the existing pavement is deteriorating. SR 247 was last resurfaced in 1994. | Pavement Improvement | 2010-01-19 | 2010-02-19 | 2010-08-31 | 2010-06-29 | 1296822.32 | 8.570 | M004035
3067 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | PEACH |  | 02 | M004036 | This project is a maintenance construction project in Peach County. This project is the milling and resurfacing of SR 247 Connector. This section of SR 247 Connector needs resurfacing because the exi | Pavement Improvement | 2010-01-20 | 2010-04-19 | 2010-07-31 | 2010-06-14 | 549412.6 | 3.010 | M004036
3068 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BUTTS |  | 08 | M004037 | This project is a maintenance construction project in Butts County. This project is the milling and resurfacing of SR 16. This section of SR 16 needs resurfacing because the existing pavement is deteriorating. SR 16 was last resurfaced in 1999. | Pavement Improvement | 2010-01-05 | 2010-04-19 | 2010-06-30 | 2010-06-30 | 367643.47 | 1.340 | M004037
3069 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | JONES |  | 08 | M004038 | This project is a maintenance construction project in Jones County. This project is the resurfacing of SR 44. This section of SR 44 needs resurfacing because the existing pavement is deteriorating. SR 44 was last resurfaced in 1998. | Pavement Improvement | 2010-01-21 | 2010-02-26 | 2010-10-31 | 2010-09-30 | 2265748.5 | 14.580 | M004038
3070 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | TAYLOR |  | 02 | M004039 | This project is a maintenance construction project in Taylor County. This project is the resurfacing of SR 22. This section of SR 22 needs resurfacing because the existing pavement is deteriorating. SR 22 was last resurfaced in 1994. | Pavement Improvement | 2010-01-05 | 2010-03-01 | 2010-08-31 | 2010-08-13 | 1023496 | 6.180 | M004039
3071 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BRANTLEY |  | 01 | M004040 | This project is a maintenance construction project in Brantley County. This project is the resurfacing of SR 520. This section of SR 520 needs resurfacing because the existing pavement is deteriorating. SR 520 was last resurfaced in 1998. | Pavement Improvement | 2009-08-07 | 2010-05-03 | 2010-06-30 | 2010-06-30 | 860179.41 | 3.500 | M004040
3072 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | DOUGLAS | ATLANTA | 13 | M004047 | This project is a maintenance construction project in Douglas County. This project is the milling and resurfacing of 1.7 miles of SR 92 from Durelee Lane/City Street 597 to Malone Street/City street | Pavement Improvement | 2010-05-27 | 2010-07-06 | 2011-03-31 | 2010-08-10 | 440596.76 | 1.730 | M004047
3073 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | GWINNETT | ATLANTA | 07 | M004052 | This project is a maintenance construction project in Gwinnett County. This project is the milling and resurfacing of 5.8 miles of SR 20 from west of Peachtree Industrial Boulevard/County Road 1954 t | Pavement Improvement | 2010-05-21 | 2010-09-07 | 2011-03-31 | 2010-12-03 | 1812083.31 | 5.800 | M004052
3074 | GEORGIA | Completed | C250 | Highway Infrastructure Investment Grant | GEORGIA | WHEELER |  | 01 | M004078 | This is a maintenance construction project in Telfair and Wheeler counties. This project is the resurfacing of SR 19. This section of SR 19 needs resurfacing because the existing pavement is deteriorating. SR 19 was last resurfaced in 1998. | Pavement Improvement | 2010-03-19 | 2010-09-13 | 2011-01-31 | 2011-01-21 | 804196.34 | 19.160 | M004078
3075 | GEORGIA | Completed | C230 | Highway Infrastructure Investment Grant | GEORGIA | CHEROKEE | ATLANTA | 06 | M004079 | This project is a maintenance construction project in Cherokee County. This project is the resurfacing of 4.7 miles of SR 369 from SR 20 to the Forsyth County line. This section of SR 369 needs res | Pavement Improvement | 2010-05-27 | 2010-06-27 | 2011-03-31 | 2010-09-30 | 1041773.67 | 4.720 | M004079
3076 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | M004172 | This project is a maintenance resurfacing project in Baldwin County. This project is the milling and resurfacing of State Route 112 in Milledgeville. This section of State Route 112 needs resurfacing | Pavement Improvement | 2010-11-08 | 2011-03-08 | 2011-06-30 | 2011-06-20 | 900622.27 |  | M004172
3077 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | IRWIN |  | 08 | M004199 | This is a maintenance construction project in Irwin County. This project is the resurfacing of SR 32. This section of SR 32 needs resurfacing because the existing pavement is deteriorating. SR 32 was last resurfaced in 1997. | Pavement Improvement | 2011-01-27 | 2011-06-27 | 2011-11-30 | 2011-10-14 | 967400 |  | M004199
3078 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | IRWIN |  | 08 | M004200 | This is a maintenance construction project in Ben Hill and Irwin Counties. This project is the resurfacing of SR 32. This section of SR 32 needs resurfacing because the existing pavement is deteriorating. SR 32 was last resurfaced in 1997. | Pavement Improvement | 2011-01-27 | 2011-06-27 | 2011-11-30 | 2011-10-14 | 680784 |  | M004200
3079 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MACON |  | 02 | M004210 | This is a maintenance construction project in Macon County. This project is the resurfacing of SR 240. This section of SR 240 needs resurfacing because the existing pavement is deteriorating. SR 240 was last resurfaced in 1983. | Pavement Improvement | 2011-01-27 | 2011-05-02 | 2011-10-31 | 2011-09-05 | 566300 |  | M004210
3080 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | BIBB | MACON | 08 | M004212 | This is a maintenance construction project in Bibb and Jones Counties. This project is the resurfacing of SR 49. This section of SR 49 needs resurfacing because the existing pavement is deteriorating. SR 49 was last resurfaced in 1990. | Pavement Improvement | 2011-01-26 | 2011-04-20 | 2011-10-31 | 2011-09-19 | 1610000 |  | M004212
3081 | GEORGIA | Completed | C240 | Highway Infrastructure Investment Grant | GEORGIA | MITCHELL |  | 02 | M004213 | This is a maintenance construction project in Mitchell County. This project is the resurfacing of SR 65. This section of SR 65 needs resurfacing because the existing pavement is deteriorating. SR 65 was last resurfaced in 2001. | Pavement Improvement | 2011-01-18 | 2011-02-17 | 2011-10-31 | 2011-07-29 | 1542000 |  | M004213
3082 | GEORGIA | Completed | C250,C240 | Highway Infrastructure Investment Grant | GEORGIA | JOHNSON |  | 12 | M004236 | This is a maintenance construction project in Johnson County. This project is the resurfacing of SR 78. This section of SR 78 needs resurfacing because the existing pavement is deteriorating. SR 78 was last resurfaced in 1999. | Pavement Improvement | 2010-12-29 | 2011-04-19 | 2011-10-31 | 2011-10-10 | 1509053.2 |  | M004236
3083 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | BALDWIN |  | 12 | M004277 | This is a maintenance construction project in Baldwin County. This project is the resurfacing of SR 299. This section of SR 299 needs resurfacing because the existing pavement is deteriorating. SR 299 was last resurfaced in 1988. | Pavement Improvement | 2010-12-30 | 2011-07-05 | 2011-09-30 | 2011-09-29 | 608338.89 |  | M004277
3084 | GEORGIA | Underway | C240 | Highway Infrastructure Investment Grant | GEORGIA | DOOLY |  | 02 | M004282 | This project is a an interstate rehabilitation project on I-75 in Dooly County. The proposed project involves the replacement of the existing concrete pavement and asphalt shoulders along I-75. The | Pavement Improvement | 2010-10-29 | 2011-01-06 | 2012-12-31 |  | 24277727.35 |  | M004282
3085 | GEORGIA | Completed | C200 | Highway Infrastructure Investment Grant | GEORGIA | WAYNE |  | 01 | M004287 | This is a maintenance construction project in Wayne County. This project is the resurfacing of SR 23. This section of SR 23 needs resurfacing because the existing pavement is deteriorating. SR 23 was last resurfaced in 1999. | Pavement Improvement | 2010-12-29 | 2011-06-01 | 2011-10-31 | 2011-08-12 | 1064124.74 |  | M004287
3086 | GEORGIA | Completed | C240,C230 | Highway Infrastructure Investment Grant | GEORGIA | FULTON | ATLANTA | 05 | M004420 | This project is a an interstate rehabilitation project on I-75 in Atlanta in Cobb and Fulton Counties. This project includes resurfacing, bridge joint maintenance and guardrail upgrades along I-75 be | Pavement Improvement | 2010-12-29 | 2011-01-28 | 2011-08-31 | 2011-05-17 | 14000631.39 |  | M004420
3087 | HAWAII | Underway | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 01 | 0001036 | Install and Upgrade traffic signals, including ADA improvements, signs, markings and interconnects (Komo Mai St & Hoomalu St, Waiakamilo Rd & McNeil St, N Beretania St & Aala St, Kiluea Ave, Lanikuha | Safety/Traffic Management | 2009-12-21 | 2009-12-21 | 2013-02-01 |  | 3670845.6 |  | 0001036
3088 | HAWAII | Completed | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 01 | 0001045 | Provide auxiliary power needed to support critical operations during prolonged power outages due to emergencies. | Safety/Traffic Management | 2010-04-30 | 2010-04-30 | 2010-07-28 | 2011-01-20 | 270774 |  | 0001045
3089 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU |  | 02 | 0011250 | Upgrade the Farrington Highway and Makakilo Separation structures over the H-1 freeway to better resist earthquake damage. (Farrington Hwy Separation) | Bridge Improvement | 2009-07-13 | 2009-07-13 | 2010-01-04 | 2009-12-16 | 834579.19 | 0.000 | 0011250
3090 | HAWAII | Underway | C240,C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 01 | 0011262 | Install longitudinal dowels into concrete sections, repair and smoothen concrete pavement at two major locations on the Interstate Route H-1 freeway from MP 2.4 to 3.46 and MP 24.9 to 26.4. | Pavement Improvement | 2010-01-29 | 2010-01-29 | 2011-08-15 |  | 6350000 |  | 0011262
3091 | HAWAII | Completed | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 0031079 | Upgrade the H-3 Mokapu Boulevard Interchange structure to better resist earthquake damage. | Bridge Improvement | 2010-11-08 | 2010-11-08 | 2011-06-17 | 2011-06-02 | 393000 |  | 0031079
3092 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | HAWAII |  | 02 | 0191042 | Replacement of non-ADA compliant sidewalks and ramps along Mamalahoa Highway in Waimea, Hawaii. | Transportation Enhancements | 2011-03-18 | 2011-03-18 | 2011-07-27 | 2012-02-24 | 841010 |  | 0191042
3093 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | HAWAII |  | 02 | 0192059 | Remove and dispose of lead-based paint and rust from steel members and paint them. Work also includes repairing/replacing steel members that need repair work. (Kukaiau Bridge MP33.6, Kuwaikahi Bridge | Bridge Improvement | 2009-09-08 | 2009-09-08 | 2011-04-07 | 2010-12-23 | 4301949.3 | 14.200 | 0192059
3094 | HAWAII | Completed | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 01 | 0300112 | Provide left turning lanes on Harding Avenue for traffic turning into the H-1 Freeway on-ramps to reduce congestion relief and improve traffic safety. | Pavement Widening | 2010-11-15 | 2010-11-15 | 2011-10-01 | 2012-08-02 | 1921488.27 | 0.510 | 0300112
3095 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0311011 | Extend the life of the pavement and provide a smooth surface in areas that are starting to show distress by removal of the top layer and repaving. | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2010-02-23 | 2010-04-20 | 2872100.47 |  | 0311011
3096 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0321009 | Replace and/or modify the existing bridge girders to provide additional clearance. | Bridge Improvement | 2010-04-02 | 2010-04-02 | 2010-06-02 | 2010-09-09 | 1913695.27 |  | 0321009
3097 | HAWAII | Completed | C250 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0360010 | Extending the life of the pavement and provide a smooth surface in areas that are starting to show distress by providing a surface seal. | Pavement Improvement | 2009-08-26 | 2009-08-26 | 2009-10-29 | 2009-12-18 | 526005.59 | 3.320 | 0360010
3098 | HAWAII | Completed | C250,C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0460014 | Resurface and reconstruct damaged areas of the pavement. Safety (including guardrail and shoulder improvements) and ADA improvements could be included. | Pavement Improvement | 2009-08-26 | 2009-08-26 | 2009-10-22 | 2009-12-18 | 2688406 | 1.960 | 0460014
3099 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0470006 | Extend the life of the pavement and provide a smooth surface in areas that are starting to show distress by removal of the top pavement layer and repaving. | Pavement Improvement | 2009-08-26 | 2009-08-26 | 2009-10-29 | 2010-01-12 | 1031504.87 | 5.790 | 0470006
3100 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0480003 | Resurface and reconstruct damaged areas of the pavement. Safety (including guardrail and shoulder improvements) on Farrington Avenue (2.44 miles) and Puupeela Avenue (1.21 miles) | Pavement Improvement | 2009-12-10 | 2009-12-10 | 2010-03-16 | 2010-04-23 | 5311211.67 | 3.650 | 0480003
3101 | HAWAII | Underway | C240 | Highway Infrastructure Investment Grant | HAWAII | KAUAI |  | 02 | 0501036 | Kaumualii Highway, Route 50, from just west of the Lihue Mill Bridge to Rice Street will be widened from an undivided two-lane highway to a divided four-lane highway. Improvements include widening t | Pavement Widening | 2012-04-13 | 2012-04-13 | 2015-03-30 |  | 22724978.84 |  | 0501036
3102 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | KAUAI |  | 02 | 0561052 | Reconstruct weakened pavement areas, cold plane, resurface, adjust utility boxes, & install guardrails, pavement markings, & traffic signs on Kuhio Hwy, Rte 56, between MP 9.0 and MP 10.0. | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2009-10-13 | 2009-11-05 | 774398.04 | 1.000 | 0561052
3103 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | KAUAI |  | 02 | 0583001 | Reconstruct weakened pavement areas, remove existing surface and repave, adjust utilities, and install guardrails, pavement markings, and traffic signs on Maalo Road, Route 583 | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2009-09-29 | 2009-11-12 | 608365.73 | 1.000 | 0583001
3104 | HAWAII | Underway | C220,C200 | Highway Infrastructure Investment Grant | HAWAII | KAUAI |  | 02 | 0700049 | Approximately 2 miles of 12-foot wide, 6-inch thick concrete bike/pedestrian path. Project starts at the south side of the Wailua River bridge on Kuhio Hwy to the intersection of Kuhio Hwy/Kuloloku Road. | Transportation Enhancements | 2011-11-01 | 2011-11-01 | 2012-10-15 |  | 4120000 |  | 0700049
3105 | HAWAII | Completed | C240,C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 0831042 | Replace existing South Punaluu Stream Bridge with new concrete bridge. | Bridge Replacement | 2009-08-26 | 2009-08-26 | 2011-09-01 | 2012-04-13 | 15298509.74 | 0.000 | 0831042
3106 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 0900074 | Extend the life of the pavement and provide a smooth surface on Lower Main Street and Kanaloa Avenue by placing a surface seal. Project limits are; Lower Main Street - Waiehu Beach Road to Hala Place | Pavement Improvement | 2011-02-14 | 2011-02-14 | 2011-05-13 | 2011-06-03 | 500864.45 |  | 0900074
3107 | HAWAII | Underway | C240,C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 0951001 | Widen Kalaeloa Blvd. to six lanes from the O.R. and L. right-of-way to Lauwiliwili Street. Also signalize Lauwiliwili Street/Kalaeloa Blvd intersection. | Pavement Widening | 2010-11-05 | 2010-11-05 | 2012-02-01 |  | 5376455.41 | 0.130 | 0951001
3108 | HAWAII | Completed | C200,C240 | Highway Infrastructure Investment Grant | HAWAII | HAWAII |  | 02 | 1880001 | Construction of a new 1.6 mile, 2 lane, Ane Keohokalole Highway from Palani Road to Puohulihuli Street, reconstruction of 0.4 miles of the existing roadway from Puohulihuli Street to the West Hawaii C | New Construction | 2010-03-29 | 2010-03-29 | 2012-01-20 | 2012-07-10 | 33815615.08 |  | 1880001
3109 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 3190001 | Remove the existing pavement surface on Ohukai Road between Hukulii Place and Hoalike Street and install new pavement. Utility covers will be adjusted and the road will be restriped. | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2010-05-21 | 2010-07-08 | 344462.15 |  | 3190001
3110 | HAWAII | Completed | C240 | Highway Infrastructure Investment Grant | HAWAII | MAUI |  | 02 | 3405002 | Reconstruction and beautification of Market Street from Kahawai Street to Makuhau Road. Install drainage system, street lights, landscaping and irrigation. | Pavement Improvement | 2009-11-27 | 2009-11-27 | 2010-12-01 | 2011-04-13 | 2421989.55 | 0.170 | 3405002
3111 | HAWAII | Underway | C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 7139001 | Construct various improvements including drainage, parking, roadway and pedestrian/bike improvements. | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2011-09-28 |  | 3577527 | 0.520 | 7139001
3112 | HAWAII | Underway | C240,C230 | Highway Infrastructure Investment Grant | HAWAII | HONOLULU | HONOLULU | 02 | 8915002 | This project will consist of roadway improvements along Kamokila Boulevard and Kapolei Parkway. Construction will generally consist of removal and replacement of existing asphalt concrete pavement, r | Pavement Improvement | 2011-07-28 | 2011-07-28 | 2011-11-25 |  | 2380000 |  | 8915002
3113 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO |  | 01 | 4110137 | This project will add a climbing lane up the Whitebird Grade by widening 2.6 miles of US-95 in Idaho County. | Pavement Widening | 2009-03-03 | 2009-07-17 | 2015-09-30 | 2010-06-30 | 3909447.73 | 2.619 | 4110137
3114 | IDAHO | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO |  | 01 | 4110138 | This project includes the complete removal and replacement of pavement and base on 12 miles of US-95 north of Grangeville in Idaho County. | Pavement Improvement | 2009-09-15 | 2010-06-08 | 2015-09-30 |  | 3570710 | 9.059 | 4110138
3115 | IDAHO | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI |  | 01 | 5110137 | This project is to reconstruct the last 3.2 mile segment of US-95 in the City of Hayden in Kootenai County | Pavement Widening | 2009-06-02 | 2010-02-23 | 2015-09-30 |  | 9179072 | 4.460 | 5110137
3116 | IDAHO | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK | POCATELLO | 02 | 7261100 | This project will repair or replace critical elements of the Custer Street Bridge in Bannock County. Improvements to the bridge deck and girders will extend the surface life of the structure and maintain a smooth driving surface. | Bridge Improvement | 2009-11-30 | 2010-04-26 | 2015-09-30 | 2010-09-24 | 370077 | 0.000 | 7261100
3117 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | GEM |  | 01 | 8001100 | This project will reconstruct and overlay 0.1 miles of Main Street and provide handicap accessible sidewalks in the City of Emmett, Gem County. | Pavement Improvement | 2009-09-22 | 2010-04-19 | 2015-09-30 | 2010-10-07 | 717389.2 | 0.129 | 8001100
3118 | IDAHO | Underway | C220,C250,C240 | Highway Infrastructure Investment Grant | IDAHO | BONNER |  | 01 | A001222 | This project will replace the Dover Bridge, an aging and deficient bridge, on US-95 in Bonner County. | New Bridge Construction | 2009-04-22 | 2009-07-01 | 2015-09-30 |  | 29205614.75 | 1.660 | A001222
3119 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A002352 | This project will widen and pave 4 miles of State Highway 11 in Clearwater County between the cities of Wieppe and Pierce. | Pavement Improvement | 2010-02-28 | 2010-06-18 | 2015-09-30 | 2010-11-04 | 4178863 | 4.114 | A002352
3120 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK |  | 02 | A007806 | This project will upgrade 31 miles of Southbound I-15 in Bannock County by laying an asphalt overlay, seal coat, and fog coat over the existing pavement. The project will also include deck repair at four locations along the roadway. | Pavement Improvement | 2009-11-30 | 2010-04-19 | 2015-09-30 | 2010-09-28 | 3705784 | 5.000 | A007806
3121 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK |  | 02 | A007840 | This project will upgrade 31 miles of Northbound I-15 in Bannock County by laying an asphalt overlay, seal coat, and fog coat over the existing pavement. The project will also include deck repair at four locations along the roadway. | Pavement Improvement | 2009-09-15 | 2010-04-19 | 2015-09-30 | 2010-09-28 | 3957694.47 | 5.000 | A007840
3122 | IDAHO | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | FREMONT |  | 02 | A008624 | This project will add passing lanes in a mountainous area near Henry's Lake by widening 6.4 miles of US-20. | Pavement Widening | 2009-04-22 | 2009-07-31 | 2015-09-30 | 2010-08-26 | 2618165 | 6.370 | A008624
3123 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CANYON, PAYETTE |  | 01 | A008955 | This project will repair the concrete pavement to provide a smooth driving surface on 5 miles of I-84 in Payette and Canyon Counties The project also includes repair and replacement of deficient guardrail. | Pavement Improvement | 2009-09-15 | 2010-05-10 | 2015-09-30 | 2012-12-05 | 8115162 | 5.030 | A008955
3124 | IDAHO | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | JEFFERSON |  | 02 | A009387 | This project will reconstruct 1.7 miles of SH-48 in Rigby including new curb & gutter and handicap accessible sidewalks to the high school. | Pavement Widening | 2009-04-22 | 2009-08-10 | 2015-09-30 | 2010-08-26 | 4166084 | 1.710 | A009387
3125 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO, LEWIS |  | 01 | A009795 | This project will repair the bridge deck and seal the driving surface on the bridge crossing Lawyers Creek on US-95 on the county line between Idaho and Lewis County. | Bridge Improvement | 2009-09-15 | 2010-06-07 | 2015-09-30 | 2010-08-02 | 125861.67 | 0.173 | A009795
3126 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A009796 | This project will repair the bridge deck and preserve the driving surface with skid resistance aggregate and epoxy on State Highway 7 in the City of Orofino in Clearwater County. | Bridge Improvement | 2009-11-30 | 2010-06-07 | 2015-09-30 | 2010-08-02 | 233707.7 | 0.049 | A009796
3127 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A009797 | This project will repair the bridge deck and seal the driving surface on the bridge crossing the North Fork Clearwater River on State Highway 7 in Clearwater County. | Bridge Improvement | 2009-11-30 | 2010-06-07 | 2015-09-30 | 2010-08-02 | 42310.3 | 0.000 | A009797
3128 | IDAHO | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA |  | 01 | A010489 | This project consists of constructing continuous sidewalk, to be in complliance with the Americans with Disabilities Act, on the east and west sides of a 0.3 mile section of West 8th Street in the City of Meridian. | Transportation Enhancements | 2009-05-28 | 2010-06-22 | 2015-09-30 | 2010-08-06 | 162294 | 0.454 | A010489
3129 | IDAHO | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 01 | A010537 | This project takes place at 7 locations throughout Ada County and will overlay a total of 11 miles of existing roadways including handicap accessible sidewalk ramps. | Pavement Improvement | 2009-11-30 | 2010-06-15 | 2015-09-30 | 2010-11-17 | 2513134.84 | 12.510 | A010537
3130 | IDAHO | Underway | C200 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK | POCATELLO | 02 | A010584 | This project will add one additional lane by widening 1.2 miles of congested urban interstate from the Chubbuck Interchange on I-86 to the Pocatello Creek Interchange on I-15 in Bannock County. | Pavement Improvement | 2009-04-22 | 2009-09-29 | 2015-09-30 |  | 10138499 | 1.200 | A010584
3131 | IDAHO | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | TWIN FALLS |  | 02 | A010917 | This project will eliminate traffic congestion in Twin Falls by constructing a new 5.1 mile long, 4-lane US-93 bypass, around the west side of the city. | New Construction | 2009-04-22 | 2009-09-05 | 2015-09-30 | 2010-12-22 | 21280930 | 5.070 | A010917
3132 | IDAHO | Completed | C250,C220 | Highway Infrastructure Investment Grant | IDAHO | LATAH |  | 01 | A011031 | This project will add passing lanes in the Moscow Mountain area by widening 1.3 miles of US 95 in Latah County. | Pavement Widening | 2009-04-22 | 2009-07-07 | 2015-09-30 | 2010-06-16 | 3350536.02 | 1.338 | A011031
3133 | IDAHO | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | BINGHAM |  | 02 | A011097 | This project will mill and overlay Bergener, Bridge and Judicial Streets from the Snake river Bridge to Main Street in the City of Blackfoot | Pavement Improvement | 2010-02-17 | 2010-08-02 | 2015-09-30 | 2010-08-19 | 1036492 | 2.286 | A011097
3134 | IDAHO | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | LATAH |  | 01 | A011558 | This project will add a thin lift overlay on 6.2 miles of State Highway 9 in Latah County. | Pavement Improvement | 2009-09-15 | 2010-05-03 | 2015-09-30 | 2010-07-15 | 1551360.67 | 6.222 | A011558
3135 | IDAHO | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | CANYON |  | 01 | A011584 | This project is to realign and reconstruct the west leg of the intersection of Franklin and 21st Avenue in the City of Caldwell in Canyon County. The project includes curb, gutter and handicap accecssbile sidewalks. | Pavement Widening | 2009-11-30 | 2010-01-13 | 2015-09-30 | 2010-07-15 | 1155376 | 0.132 | A011584
3136 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BONNEVILLE, JEFFERSON |  | 02 | A011673 | This project will improve user operating conditions on an 8.5 mile segment of I-15 in Bonneville County by leveling the pavement, adding a plantmix overlay, and finishing with a seal coat and fog coat. | Pavement Improvement | 2009-09-15 | 2010-04-26 | 2015-09-30 | 2010-08-25 | 1463957.36 | 8.475 | A011673
3137 | IDAHO | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI | COEUR D ALENE | 01 | A011867 | This project will widen and completely reconstruct 0.5 miles of Hanley Avenue between Government Way and a new roundabout on 4th Street in the City of Dalton Gardens in Kootenai County. | Pavement Improvement | 2009-11-30 | 2010-06-21 | 2015-09-30 | 2010-08-19 | 499706 | 0.490 | A011867
3138 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | NEZ PERCE | LEWISTON | 01 | A011917 | This project will seal coat the existing pavement and provide a skid resistant surface on 14 miles of local streets throughout the City of Lewiston. | Pavement Improvement | 2009-11-30 | 2010-06-15 | 2015-09-30 | 2010-08-24 | 676076.36 | 0.000 | A011917
3139 | IDAHO | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK | POCATELLO | 02 | A011918 | This project will remove and replace existing bridge joints on Gould Street Bridge in the City of Pocatello and improve pavement markings along the roadway. | Bridge Improvement | 2009-11-30 | 2010-04-20 | 2015-09-30 | 2010-09-07 | 401665 | 0.229 | A011918
3140 | IDAHO | Underway | C200 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A011919 | This project funded the purchase of one van for public transportation in Pocatello. | Other | 2009-11-30 |  | 2015-09-30 |  | 12535 | 0.000 | A011919
3141 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BONNEVILLE | IDAHO FALLS | 02 | A011920 | This project will seal coat the existing pavement and provide a skid resistant surface on 5.6 miles of local streets throughout Idaho Falls. | Pavement Improvement | 2009-05-28 | 2010-07-19 | 2015-09-30 | 2010-08-05 | 721474 | 5.598 | A011920
3142 | IDAHO | Completed | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA |  | Multiple | A011922 | This project takes place at 16 locations throughout Ada County and will overlay a total of 20 miles of existing roadways to improve operating conditions, preserve structural capacity, and extend the useful life of the roadways. | Pavement Improvement | 2009-11-30 | 2010-05-07 | 2015-09-30 | 2010-08-04 | 3117819 | 20.380 | A011922
3143 | IDAHO | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA |  | Multiple | A011924 | This project will improve the network for pedestrians throughout Ada County by improving existing sidewalks, pedestrian ramps, and curb & gutter sections at up to 122 intersections within the cities of Boise, Meridian, Eagle | Transportation Enhancements | 2009-11-30 | 2010-08-16 | 2015-09-30 | 2010-11-11 | 384109 | 0.000 | A011924
3144 | IDAHO | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 02 | A011925 | This project will construct a pedestrian bridge across the Boise River east of Veterans Memorial Parkway. | Transportation Enhancements | 2009-11-30 | 2010-08-23 | 2015-09-30 | 2010-11-19 | 529754 | 0.000 | A011925
3145 | IDAHO | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 02 | A011926 | This project will improve the network for pedestrians within Downtown Boise by improving existing sidewalks, pedestrian ramps, and curb and gutter sections at up to 49 intersections so they are in conformance with the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-06-01 | 2015-09-30 | 2010-08-10 | 490288 | 0.000 | A011926
3146 | IDAHO | Underway | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 01 | A011932 | This project will provde aesthetically pleasing landscaping to the newly constructed Ten Mile Interchange on I-84 in Canyon County. | Transportation Enhancements | 2009-06-16 | 2010-06-17 | 2015-09-30 |  | 856221 | 1.000 | A011932
3147 | IDAHO | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | BOUNDARY |  | 01 | A011935 | This project will overlay 3 miles of Deep Creek Loop, a two lane roadway, in Boundary County to provide a safer traveling surface and prolong the life of the asphalt. | Pavement Improvement | 2009-05-11 | 2010-08-30 | 2015-09-30 |  | 542919 | 10.557 | A011935
3148 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | SHOSHONE |  | 01 | A011936 | This project will overlay the existing pavement to improve roadway surface smoothness and will provide stormwater drainage pathways on 0.8 mile of Nine Mile Road in Shoshone County. | Pavement Improvement | 2009-05-11 | 2010-07-28 | 2015-09-30 | 2010-09-01 | 373054 | 2.273 | A011936
3149 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BENEWAH |  | 01 | A011937 | This project will pave the existing gravel roadway on 1.3 miles of the Benewah Creek Road corridor in Benewah County. | Pavement Improvement | 2009-05-11 | 2010-09-07 | 2015-09-30 | 2010-09-27 | 382669 | 1.640 | A011937
3150 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | SHOSHONE |  | 01 | A011938 | This project will include repair of the existing pavement with a new pavement overlay on a 0.5 mile long segment in the City of Wallace in Shoshone County. | Pavement Improvement | 2009-05-11 | 2010-07-28 | 2015-09-30 | 2010-09-01 | 251176 | 0.912 | A011938
3151 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A011939 | This project includes a pavement seal coat on 14 miles of Cavendish Road in Clearwater County. | Pavement Improvement | 2009-05-11 | 2010-07-27 | 2015-09-30 | 2010-09-30 | 465427 | 14.345 | A011939
3152 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A011940 | This project will pave on top of existing gravel roadway on 0.8 miles of Musselshell Road in Clearwater County. | Pavement Improvement | 2009-05-11 | 2010-07-06 | 2015-09-30 | 2010-07-19 | 446395 | 1.500 | A011940
3153 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CLEARWATER |  | 01 | A011941 | This project will increase the life of the pavement on 2.6 miles of roadway in the City of Orofino in Clearwater County by adding asphalt leveling and a seal coat to provide skid resistance. | Pavement Improvement | 2009-05-11 | 2010-08-24 | 2015-09-30 | 2010-10-01 | 252133 | 6.300 | A011941
3154 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO |  | 01 | A011942 | This project will remove and replace the pavement and aggregate base on 0.7 mile of local road in the City of Cottonwood, Idaho County, to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 2009-05-11 | 2010-07-14 | 2015-09-30 | 2010-08-24 | 586583 | 0.722 | A011942
3155 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | PAYETTE |  | 01 | A011943 | This project will improve traffic flow and pedestrian safety near local schools in the City of Fruitland in Payette County with a pavement overlay, installing handicap accessible sidewalks, and improving crosswalks on 0.5 mile of local road. | Pavement Improvement | 2009-05-11 | 2010-06-07 | 2015-09-30 | 2010-07-19 | 453285 | 1.108 | A011943
3156 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CANYON |  | 01 | A011944 | This project in Canyon County will repair the existing pavement and add a new asphalt overlay on a 1.5 mile segment of Notus Road from State Highway 19 to Red Top Road. | Pavement Improvement | 2009-05-11 | 2010-08-13 | 2015-09-30 | 2010-08-31 | 508472 | 2.000 | A011944
3157 | IDAHO | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | GEM |  | 01 | A011945 | This project consists of an asphalt overlay on a 4 mile segment of the Ola Highway in Gem County to increase pavement longevity, improve the ride quality, and provide a safer road surface for the traveling public. | Pavement Improvement | 2009-05-11 | 2010-07-26 | 2015-09-30 | 2010-08-08 | 528199 | 7.000 | A011945
3158 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | ADAMS |  | 01 | A011946 | This project will overlay 1.6 miles and sealcoat 1.2 miles of Indian Valley Road in Adams County to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 2009-05-11 | 2010-06-14 | 2015-09-30 | 2010-07-10 | 496036 | 7.070 | A011946
3159 | IDAHO | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | LINCOLN |  | 02 | A011947 | This project will overlay 1.7 miles and sealcoat 2.9 miles of 600 West Road in Lincoln County to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 2009-05-11 | 2010-08-09 | 2015-09-30 | 2010-09-17 | 536196 | 4.561 | A011947
3160 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CASSIA |  | 02 | A011948 | This project will remove and recycle the existing pavement and gravel base on 1.2 miles of Old Highway 81 South Road in Cassia County to provide a safe and durable driving surface. | Pavement Improvement | 2009-05-11 | 2010-08-01 | 2015-09-30 | 2010-08-12 | 516695 | 3.468 | A011948
3161 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | TWIN FALLS |  | 02 | A011949 | This project will improve 0.2 mile of Center Street in the City of Kimberly, Twin Falls County, by removing the deteriorated roadway, constructing a new base, and laying new pavement. | Pavement Improvement | 2009-05-11 | 2010-04-26 | 2015-09-30 | 2010-06-24 | 463354 | 0.370 | A011949
3162 | IDAHO | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | CAMAS |  | 02 | A011950 | This project in the City of Fairfield, Camas County, will repair areas of distressed pavement, install an overlay, and perform minor storm drainage improvements at intersections along 0.6 mile of Soldier Road. | Pavement Improvement | 2009-05-11 | 2010-05-17 | 2015-09-30 |  | 522650 | 0.610 | A011950
3163 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK | POCATELLO | 02 | A011951 | This project will remove and recycle the existing pavement and gravel base on a 1.2 mile segment of Mink Creek Road in Bannock County and will include both minor widening and an overlay. | Pavement Improvement | 2009-05-11 | 2010-09-13 | 2015-09-30 | 2010-09-28 | 505800 | 1.933 | A011951
3164 | IDAHO | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | CARIBOU |  | 02 | A011952 | This project will improve the roadway and increase safety by adding new pedestrian crossing lights, replacing drainage structures, and adding a pavement overlay on 0.4 mile of local road in the City of Bancroft, Caribou County. | Pavement Improvement | 2009-05-11 | 2010-06-07 | 2015-09-30 | 2010-08-26 | 328820 | 0.426 | A011952
3165 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | POWER |  | 02 | A011953 | This project will remove and recycle the existing pavement and gravel base on a 1 mile section of South Pleasant Valley Road in Power County. | Pavement Improvement | 2009-05-11 | 2010-07-16 | 2015-09-30 | 2010-07-29 | 508545 | 2.029 | A011953
3166 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BANNOCK |  | 02 | A011954 | This project will repair and overlay 0.4 mile of local roadway pavement and provide a new pedestrian crossing with crossing lights to improve user operating conditions on East Main Street in the City of Lava Hot Springs, Bannock County. | Pavement Improvement | 2009-05-11 | 2010-08-09 | 2015-09-30 | 2010-08-26 | 262509.91 | 0.419 | A011954
3167 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | FREMONT |  | 02 | A011955 | This project will seal coat the existing pavement and provide a skid resistant surface on a 4.5 mile segment of the Teton Highway in Fremont County. | Pavement Improvement | 2009-05-11 | 2010-07-01 | 2015-09-30 | 2010-07-12 | 239843 | 4.543 | A011955
3168 | IDAHO | Completed | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | CUSTER |  | 02 | A011956 | This project in Custor County will repair a 3.1 mile segment of Trail Creek Road and extend the pavement life by adding a thin overlay to the pavement. | Pavement Improvement | 2009-05-11 | 2010-06-02 | 2015-09-30 | 2010-07-07 | 614906 | 2.000 | A011956
3169 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | FREMONT |  | 02 | A011957 | This project will repair and overlay 0.5 mile of pavement on Main Street in City of St.Anthony, Fremont County and will include minor drainage improvements, replacement of traffic signal detection loops, and adjustments to manholes and valves. | Pavement Improvement | 2009-05-11 | 2010-04-28 | 2015-09-30 | 2010-06-28 | 621140 | 1.410 | A011957
3170 | IDAHO | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | CLARK |  | 02 | A011958 | This project will replace the asphalt gutter with a concrete gutter and will overlay the roadway to improve user operating conditions on a 0.5 mile segment of Main Street in the City of Dubois, Clark County. | Pavement Improvement | 2009-05-11 | 2010-09-13 | 2015-09-30 |  | 408706 | 0.865 | A011958
3171 | IDAHO | Underway | C220 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A011960 | This project will provide for curation and management of artifacts including consolidation of the Hatwaii archaeological collection. This project will develop public outreach on archaeological displays. | Transportation Enhancements | 2009-06-16 | 2009-09-22 | 2015-09-30 |  | 167929 | 0.000 | A011960
3172 | IDAHO | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | BOISE |  | 01 | A011961 | This project is to construct a wildlife/game crossing under US-21 in Boise County. | New Bridge Construction | 2009-06-16 | 2010-07-15 | 2015-09-30 | 2010-09-22 | 1102680.74 | 0.000 | A011961
3173 | IDAHO | Underway | C220 | Highway Infrastructure Investment Grant | IDAHO | FREMONT |  | 02 | A011963 | This project is a study to determine a solution to numerous wildlife/vehicle collisions on US-20 in Fremont County. | Other | 2009-10-28 |  | 2015-09-30 |  | 643576 | 20.000 | A011963
3174 | IDAHO | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A011964 | This project will construct 940 handicap ramps in Districts 1, 2, & 3 in accordance with the requirements of the Americans with Disabilities Act. It will be split into five separate projects for construction. | Other | 2009-06-16 |  | 2015-09-30 | 2011-02-17 | 196209.99 | 0.000 | A011964
3175 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI |  | 01 | A011976 | This project is to repair 10 structures on Interstate 90 between Post Falls and the Washington State border in Kootenai County. These structures will have the top of the deck removed and replaced with a concrete overlay. | Bridge Improvement | 2009-11-30 | 2010-04-26 | 2015-09-30 | 2010-06-22 | 3742743.08 | 4.600 | A011976
3176 | IDAHO | Completed | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI |  | 01 | A011979 | This project will construct 89 handicap ramps in the Coeur D'Alene area of District 1, in Benewah, Kootenai and Shoshone Counties, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-05-10 | 2015-09-30 | 2010-09-07 | 622601.77 | 0.000 | A011979
3177 | IDAHO | Underway | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | BONNER |  | 01 | A011980 | This project will construct 90 handicap ramps in the Sandpoint area of District 1, in Bonner County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-07-06 | 2015-09-30 |  | 796283.78 | 0.000 | A011980
3178 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | LATAH |  | 01 | A011981 | This project will construct 132 handicap ramps in the northern area of District 2, in Latah County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-05-03 | 2015-09-30 | 2010-09-22 | 892628.22 | 0.000 | A011981
3179 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | IDAHO |  | 01 | A011982 | This project will construct 80 handicap ramps in the southern area of District 2, in Idaho County, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-04-26 | 2015-09-30 | 2010-08-02 | 460042.93 | 0.000 | A011982
3180 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | CANYON, GEM, PAYETTE, ADA |  | 01 | A011983 | This project will construct 127 handicap ramps in District 3, in Canyon, Gem, & Payette Counties, in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2009-11-30 | 2010-03-29 | 2015-09-30 | 2010-08-10 | 341465.29 | 0.000 | A011983
3181 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI, SHOSHONE |  | 01 | A011986 | This project is to repair 9 structures on Interstate 90 between Post Falls and the Montana State border in Kootenai & Shoshone Counties. These structures will have the top of the deck removed and replaced with a concrete overlay. | Bridge Improvement | 2010-02-03 | 2010-06-11 | 2015-09-30 | 2010-08-27 | 3953001.98 | 30.783 | A011986
3182 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BLAINE |  | 02 | A012074 | This project will patch and repair the concrete driving surface of the Big Wood River Bridge in Blaine County south of the City of Ketchum. | Bridge Improvement | 2010-05-24 | 2010-09-20 | 2015-09-30 | 2010-09-27 | 94290.15 | 0.000 | A012074
3183 | IDAHO | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A012206 | This project will construct handicap ramps in Districts 5 and 6 in accordance with the requirements of the Americans with Disabilities Act. It will be split into two separate projects for construction. | Other | 2010-02-03 |  | 2015-09-30 |  | 118127.36 | 0.000 | A012206
3184 | IDAHO | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | Multiple | A012207 | This project will construct 248 handicap ramps in Ada County in accordance with the requirements of the Americans with Disabilities Act. | Transportation Enhancements | 2010-02-28 | 2010-08-30 | 2015-09-30 |  | 740250 | 0.000 | A012207
3185 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | Multiple | A012208 | This project takes place at 9 locations throughout Ada County and will overlay a total of 7 miles of existing roadways to improve operating conditions, preserve structural capacity, and extend the useful life of the roadways. | Other | 2010-02-28 | 2010-08-30 | 2015-09-30 | 2010-10-18 | 1298271 | 7.190 | A012208
3186 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | Multiple | A012209 | This project will improve the network for pedestrians and people with disabilities in Downtown Boise by improving existing sidewalks and 55 pedestrian ramps at up to 14 intersections so they are in conformance with the Americans with Disabilities Act | Transportation Enhancements | 2010-02-03 | 2010-08-09 | 2015-09-30 | 2010-08-31 | 187400 | 0.000 | A012209
3187 | IDAHO | Underway | C220,C240 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A012217 | This project will construct 122 handicap ramps in the Cities of Aberdeen, Blackfoot, and Grace of District 5 in accordance with the requirements of the Americans with Disabilities Act in Bingham and Caribou County. | Transportation Enhancements | 2010-05-24 |  | 2015-09-30 |  | 1173708 | 0.000 | A012217
3188 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | STATEWIDE |  |  | A012218 | This project will construct 68 handicap ramps in the Cities of Rigby and Salmon of District 6 in accordance with the requirements of the Americans with Disabilities Act in Lemhi and Jefferson County. | Transportation Enhancements | 2010-05-24 | 2010-09-13 | 2015-09-30 | 2010-11-17 | 743423.3 | 0.000 | A012218
3189 | IDAHO | Completed | C240 | Highway Infrastructure Investment Grant | IDAHO | BONNEVILLE | IDAHO FALLS | 02 | A012227 | This project will seal coat the existing pavement and provide a skid resistant surface on 4.9 miles of local streets throughout Idaho Falls. | Pavement Improvement | 2010-02-03 | 2010-07-22 | 2015-09-30 | 2010-08-05 | 535404 | 4.732 | A012227
3190 | IDAHO | Underway | C240 | Highway Infrastructure Investment Grant | IDAHO | JEROME |  | 02 | A012228 | This project will remove and recycle the existing pavement and gravel base on 1.5 miles of North Road in Jerome County to provide a safe and durable driving surface. | Pavement Improvement | 2010-05-24 |  | 2015-09-30 |  | 661081 | 1.560 | A012228
3191 | IDAHO | Underway | C250,C240 | Highway Infrastructure Investment Grant | IDAHO | KOOTENAI |  | 01 | A012232 | This project will remove and replace the pavement and aggregate base on 5.2 miles of local road near the City of Coeur d'Alene, Kootenai County, to improve the driving surface and extend the life of the pavement. | Pavement Improvement | 2010-09-02 | 2011-05-23 | 2015-09-30 |  | 1572524 | 4.358 | A012232
3192 | IDAHO | Completed | C200 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 01 | A012250 | This project will remove and replace 15 traffic signal controllers between Overland Road and Chinden Blvd. on Curtis Road within Ada County to improve traffic flow and air quality. | Safety/Traffic Management | 2010-09-02 | 2011-08-15 | 2015-09-30 | 2011-09-23 | 214950.06 | 2.500 | A012250
3193 | IDAHO | Underway | C200,C240 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | Multiple | A012254 | This project will coordinate 53 traffic signals on six major arterials within Ada County to improve traffic flow and air quality. | Safety/Traffic Management | 2010-06-29 |  | 2015-09-30 |  | 244407.92 | 30.000 | A012254
3194 | IDAHO | Completed | C200 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 01 | A012255 | This project will remove and replace 14 traffic signal controllers between Cole Road and Cloverdale Road on both sides of Ustick Road within Ada County to improve traffic flow and air quality. | Safety/Traffic Management | 2010-09-02 | 2011-08-15 | 2015-09-30 | 2011-09-23 | 214168.2 | 7.000 | A012255
3195 | IDAHO | Underway | C490 | OJT/SS | IDAHO | CANYON, ADA |  | Multiple | A012260 | This project provides funding for a statewide training program for returning disabled veterans. Vetrans will be trained to drive trucks and obtain a CDL license or become a certified flagger with marketable skills in highway construction. | Other | 2010-01-08 |  | 2015-09-30 |  | 99274.35 | 0.000 | A012260
3196 | IDAHO | Completed | C490 | OJT/SS | IDAHO | STATEWIDE |  |  | A012262 | This project provides funding for construction safety training for minority, women, Native American and other disadvantaged individuals working on transportation related construction projects in Idaho. | Other | 2010-03-15 |  | 2015-09-30 | 2011-06-03 | 55448 | 0.000 | A012262
3197 | IDAHO | Completed | C240,C230 | Highway Infrastructure Investment Grant | IDAHO | ADA | BOISE CITY | 02 | C009818 | This project, in the City of Boise, the existing I-84 Vista Interchange will be reconstructed into a Single Point Urban Interchange. | Pavement Widening | 2009-04-22 | 2009-07-07 | 2015-09-30 | 2010-09-28 | 21506202.2 | 1.200 | C009818
3198 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 17 | 000S617 | This project will extend the pavement life by resurfacing a section of US 30 near the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2009-08-30 | 2009-09-11 | 782424.21 | 2.330 | 000S617
3199 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 000S618 | This project will extend the pavement life by resurfacing a section of US 20 Business Route in the city of Freeport (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-10-30 | 2009-07-16 | 389189.69 | 1.350 | 000S618
3200 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 000S619 | This project will extend the pavement life by resurfacing 12 miles of US 6 between the cities of Geneseo and Atkinson (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-10-30 | 2009-09-11 | 2720252.95 | 29.280 | 000S619
3201 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 000S620 | This project will extend the pavement life by resurfacing sections of US 20 and IL 26 near the city of Freeport (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-09-30 | 2009-11-13 | 1837174.95 | 6.420 | 000S620
3202 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 000S628 | This project will extend the pavement life by resurfacing a section of IL 2 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-26 | 2009-10-30 | 2010-04-20 | 1095782.71 | 17.930 | 000S628
3203 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S630 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 7 (Southeast Illinois). | Safety/Traffic Management | 2009-04-28 | 2009-06-22 | 2009-12-30 | 2009-09-15 | 745277.15 | 0.000 | 000S630
3204 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S631 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 1 (Northeast Illinois). | Safety/Traffic Management | 2009-04-23 | 2009-05-12 | 2010-07-30 | 2010-07-31 | 907824.38 | 0.000 | 000S631
3205 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S633 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 3 (East-Central Illinois). | Safety/Traffic Management | 2009-07-30 | 2009-08-10 | 2010-07-30 | 2010-07-30 | 574011.55 | 0.000 | 000S633
3206 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S634 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout District 4 (West-Central Illinois) | Safety/Traffic Management | 2009-05-06 | 2009-05-16 | 2010-07-30 | 2010-06-19 | 432884 | 0.000 | 000S634
3207 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S637 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 7 (Southeast Illinois). | Safety/Traffic Management | 2009-05-06 | 2009-07-28 | 2010-07-30 | 2009-08-30 | 343186.98 | 0.000 | 000S637
3208 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S639 | This project consists of a safety and traffic enhancement by upgrading pavement markings throughout IDOT District 9 (Southern Illinois). | Safety/Traffic Management | 2009-05-06 | 2009-08-31 | 2010-07-30 | 2009-11-02 | 477059.89 | 0.000 | 000S639
3209 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S640 | This project consists of improving safety by upgrading guardrail terminals to current standard throughout IDOT District 1 (Northeast Illinois). | Safety/Traffic Management | 2009-04-30 | 2009-06-23 | 2009-11-30 | 2009-11-16 | 817169.16 | 0.000 | 000S640
3210 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S644 | This project consists of improving safety by upgrading guardrail terminals to current standard throughout District 4 (West-Central Illinois) | Safety/Traffic Management | 2009-04-28 | 2009-05-08 | 2009-12-30 | 2009-11-03 | 721808.89 | 0.000 | 000S644
3211 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S645 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 9 (Southern Illinois). | Safety/Traffic Management | 2009-04-28 | 2009-05-21 | 2009-12-30 | 2010-01-13 | 683695.91 | 0.000 | 000S645
3212 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MONTGOMERY |  | 19 | 000S646 | This project will extend the pavement life by resurfacing various streets in Nokomis, Il in Montgomery County (West-Central Illinois). | Pavement Improvement | 2009-04-30 | 2010-05-03 | 2010-07-30 | 2011-10-21 | 924307.95 | 3.270 | 000S646
3213 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 000S647 | This project will extend the pavement life by resurfacing DesPlaines Avenue from 26th to 31st Street in the Village of Riverside in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-18 | 2009-08-30 | 2009-06-29 | 345016.9 | 0.510 | 000S647
3214 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 000S648 | This project consists of improving safety by upgrading guardrail to current standards throughout IDOT District 3 (East-Central Illinois). | Safety/Traffic Management | 2009-07-30 | 2009-08-24 | 2009-12-30 | 2009-12-04 | 1031644.46 | 0.000 | 000S648
3215 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S649 | This project will extend the pavement life by resurfacing numerous roadway sections in Southern Cook County (Northeastern Illinois) | Pavement Improvement | 2009-06-01 | 2009-06-23 | 2009-09-30 | 2009-07-31 | 911289.06 | 0.000 | 000S649
3216 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S650 | This project will extend the pavement life by resurfacing numerous roadway sections in Central Cook County (Northeastern Illinois) | Pavement Improvement | 2009-06-01 | 2009-06-29 | 2009-11-30 | 2009-11-13 | 1577940.6 | 0.000 | 000S650
3217 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S651 | This project will extend the pavement life by resurfacing numerous roadway sections in Northern Cook County (Northeastern Illinois) | Pavement Improvement | 2009-06-01 | 2009-06-05 | 2009-10-30 | 2009-12-03 | 1022357.4 | 0.000 | 000S651
3218 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 000S652 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Kane County (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-22 | 2009-09-30 | 2009-08-13 | 453708.18 | 0.000 | 000S652
3219 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 000S653 | This project will extend the pavement life by resurfacing numerous roadway sections in Will County (Northeastern Illinois). | Pavement Improvement | 2009-06-02 | 2009-06-15 | 2009-10-30 | 2009-10-12 | 1397082.45 | 0.000 | 000S653
3220 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S654 | This project will extend the pavement life by resurfacing numerous roadway sections in DuPage County (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-11-30 | 2009-09-30 | 2302963.54 | 0.000 | 000S654
3221 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S655 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout McHenry County (Northeastern Illinois). | Pavement Improvement | 2009-06-02 | 2009-06-09 | 2009-09-30 | 2009-07-24 | 623454.17 | 0.000 | 000S655
3222 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S656 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Lake County (Northeastern Illinois). | Pavement Improvement | 2009-06-02 | 2009-06-12 | 2009-11-30 | 2009-09-29 | 2512642.94 | 0.000 | 000S656
3223 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S657 | This project will extend the pavement life by milling, patching and resurfacing various locations throughout Lake County (Northeastern Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-12 | 2009-11-30 | 2009-12-08 | 2010293.64 | 0.000 | 000S657
3224 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 000S658 | This project will substantially improve the roadway, traffic congestion and safety by constructing a new interchange to replace the old interchange in Troy, Illinois (Southwest Illinois) | Pavement Improvement | 2009-08-05 | 2009-08-17 | 2012-07-30 |  | 24594122.19 | 0.010 | 000S658
3225 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 000S659 | This project will improve safety and operations by removal of old ramp structures and extention of existing ramps and other roadway improvements on I-94/90 from Hubbard's Cave to I-290 in the City of Chicago. (Northeastern Illinois). | Pavement Improvement | 2009-05-20 | 2009-06-15 | 2009-11-30 |  | 13054148.61 | 1.180 | 000S659
3226 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 000S660 | This project will extend the pavement life by milling, patching and resurfacing 2 miles of Dempster Street from US 41 to McCormick Blvd in Skokie and Chicago Avenue to Judson Avenue in Evanston in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-14 | 2009-11-30 | 2010-12-02 | 1564125.3 | 2.070 | 000S660
3227 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 000S662 | This project will extend the pavement life by resurfacing 3.04 miles of Touhy Ave from Northwest highway to Central Avenue in the Village of Niles and Cities of Chicago and Park Ridge in Cook County, (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-12 | 2009-09-30 | 2009-10-03 | 2182315.95 | 3.180 | 000S662
3228 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 000S680 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on CH 23 over Jack Creek at Toulon which is approximately 30 miles northwest of the City of Peoria ( West-Central Illinois) | Pavement Improvement | 2009-07-30 | 2009-08-10 | 2009-11-30 | 2009-10-27 | 1873371.58 | 10.570 | 000S680
3229 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENDERSON |  | 17 | 000S681 | This project will extend the pavement life by providing for surface improvements at 2 locations on US Route 34 near the City of Gulfport and the Mississippi River (West-Central Illinois) | Pavement Improvement | 2009-08-11 | 2009-08-13 | 2009-09-30 | 2009-10-06 | 611731.05 | 4.380 | 000S681
3230 | ILLINOIS | Completed | C250,C220 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 000S685 | This project will extend the pavement life by resurfacing 3.0 miles on US Route 6 in Channahon and Rockdale (Northeast Illinois). | Pavement Improvement | 2009-10-29 | 2010-04-30 | 2010-08-30 | 2010-10-01 | 1354399.86 | 3.940 | 000S685
3231 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MARSHALL |  | 18 | 000S802 | This project will extend the pavement life by resurfacing and adding safety improvements to 15 miles of Illinois Routes 89 and 17 in Marshall and Putnam Counties (West-Central Illinois). | Pavement Improvement | 2010-04-21 | 2010-04-22 | 2010-10-30 | 2010-08-16 | 700000 | 14.940 | 000S802
3232 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 000S829 | Rem & Rep structure carrying IL 251 over Spring Creek Rd & Rem/ repl bridge deck on structure carrying Forest Hills Rd over IL 251 in Rockford. Section 1-HBR & 1-2 HB-D | Pavement Improvement | 2010-12-10 | 2011-03-21 | 2011-10-30 |  | 497380.31 | 0.010 | 000S829
3233 | ILLINOIS | Completed | C490 | OJT/SS | ILLINOIS | STATEWIDE |  |  | 0011106 | To provide training in highway construction industry trade and life skills, financial assistance (stipends) for transportation/child care, and construction tools/clothing/safety equipment, as identifi | Other | 2010-05-01 | 2010-05-03 | 2011-06-30 | 2011-06-30 | 1189635 | 0.000 | 0011106
3234 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 0022070 | This project will extend the pavement life by providing for 7.21 miles pavement repairs and resurfacing on Illinois Route 78 approximately 20 miles west of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-09-30 | 2009-07-27 | 2133300.98 | 7.540 | 0022070
3235 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA |  | 18 | 0022071 | This project will extend the pavement life by providing for 3.06 miles of pavement repairs and resurfacing on Ilinois Route 78 west of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-08 | 2009-08-30 | 2009-06-13 | 1022359.09 | 3.060 | 0022071
3236 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 0022072 | This project will extend the pavement life by providing for 9.2 miles of pavement repairs and resurfacing on Illinois Route 78 aproximately 20 miles west of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-01 | 2009-09-30 | 2009-07-29 | 1661932.91 | 9.190 | 0022072
3237 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STARK |  | 18 | 0022075 | This project will extend the pavement life by resurfacing 9.7 miles of Illinois Route 78 approximately 20 miles northwest of Peoria (West-Central Illinois) | Pavement Improvement | 2009-07-30 | 2009-08-03 | 2009-12-30 | 2009-10-15 | 2461526.75 | 19.360 | 0022075
3238 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CLINTON |  | 19 | 0027038 | This project will substantially improve the roadway by constructing a new bridge over Lost Creek on Sand Ridge Road near Ferrin, Illinois (Southwest Illinois) | Bridge Replacement | 2009-07-27 | 2009-09-14 | 2009-10-30 | 2009-11-12 | 50000 | 0.200 | 0027038
3239 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0031030 | This project will extend the bridge life by milling, resurfacing and repairing the bridge deck and making other roadway improvements on Winnetka Rd. over the North branch of the Chicago River in Cook County. (Northeastern Illinois) | Bridge Improvement | 2010-03-16 | 2010-04-02 | 2010-10-30 | 2010-08-01 | 242214 | 0.030 | 0031030
3240 | ILLINOIS | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | BOONE |  | 16 | 0032106 | This project will extend the pavement life by resurfacing sections of Poplar Grove Road in Boone County (Northwest Illinois). | Pavement Improvement | 2009-09-15 | 2009-10-07 | 2009-10-30 | 2009-11-14 | 398954 | 10.780 | 0032106
3241 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE WITT |  | 15 | 0039027 | This project will enhance safety by upgrading signs to current standards throughout DeWitt County (East-Central Illinois). | Safety/Traffic Management | 2010-06-01 | 2010-06-01 | 2011-07-30 | 2010-12-15 | 76193.62 | 0.000 | 0039027
3242 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | DE WITT |  | 15 | 0039028 | Preliminary engineering for the prepaation of a sign inventory in DeWitt county, 09-00000-00-SG | Other | 2009-08-10 | 2009-08-10 | 2010-10-30 | 2009-12-31 | 32550 | 0.000 | 0039028
3243 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041093 | This project consists of providing engineering design for a future township bridge improvement over the Kaskaskia River (East-Central Illinois). | Other | 2009-09-30 | 2009-11-01 | 2010-12-30 | 2011-10-31 | 63445.88 | 0.010 | 0041093
3244 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041094 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE OVER SCATTERING FORK, SECTION 07-03122-01-EG | Other | 2009-09-30 | 2009-10-01 | 2010-07-30 | 2011-05-05 | 34770 | 0.020 | 0041094
3245 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041095 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE OVER THE KASKASKIA RIVER NEAR FLICKLIN, SECTION 09-05123-01EG | Other | 2009-09-30 | 2009-11-01 | 2010-12-30 | 2011-11-07 | 104296.19 | 0.000 | 0041095
3246 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041096 | PRELIMINARY ENGINEERING FOR THE REPLACEMENT OF THE STRUCTURE CARRYING TR 218 OVER BRUSHY FORK, DOUGLAS COUNTY SECTION 07-08119-01-EG | Other | 2009-09-30 | 2009-10-05 | 2010-10-30 | 2011-01-06 | 52019 | 0.030 | 0041096
3247 | ILLINOIS | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS |  | 15 | 0041097 | This project will enhance safety by upgrading signs to current standards throughout Douglas County (East-Central Illinois). | Safety/Traffic Management | 2010-04-15 | 2010-04-15 | 2011-04-30 |  | 72420 | 0.000 | 0041097
3248 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 0041130 | This project will extend the pavement life by resurfacing 7.9 miles of IL 17 in western Kankakee County (East-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-26 | 2009-08-30 | 2009-08-07 | 1744277.41 | 8.100 | 0041130
3249 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | EDWARDS |  | 19 | 0047032 | This project will substantially improve the roadway by constructing a new bridge over Bear Creek on County Highway 4 near Samsville in Edwards County (Southeast Illinois). | Bridge Replacement | 2010-03-01 | 2010-04-30 | 2010-06-30 | 2010-06-30 | 133611.17 | 0.010 | 0047032
3250 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | EDWARDS |  | 19 | 0047033 | This project will substantially improve the roadway by constructing a new bridge over Butter Creek on Township Road 185 near Albion (Southeast Illinois) | Bridge Replacement | 2010-10-18 | 2010-10-25 | 2011-05-30 | 2010-11-29 | 31067 | 0.010 | 0047033
3251 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HAMILTON |  | 19 | 0065051 | This project will extend the pavement life by resurfacing numerous roadway sections in Whtie County. (Southern Illinois) | Pavement Improvement | 2010-02-22 | 2010-05-01 | 2010-05-30 | 2010-07-22 | 264944 | 0.010 | 0065051
3252 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | JO DAVIESS |  | 16 | 0065104 | This project will extend the pavement life by resurfacing 5.3 miles on Stagecoach Trail near the city of Warren (Northwest Illinois). | Pavement Improvement | 2009-10-27 | 2010-05-17 | 2010-12-30 | 2010-06-02 | 375743 | 9.340 | 0065104
3253 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 0067079 | This project will extend the pavement life by milling and resurfacing a portion of Jefferson Street in the City of Springfield (West-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-04-30 | 2009-09-30 | 2009-08-14 | 828924.18 | 2.880 | 0067079
3254 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CASS |  | 18 | 0067080 | This project will substantially improve the roadway by reconstructing two box culverts and repairing another one on Illinois Route 125 near Bluff Springs (West-Central Illinois) | Pavement Improvement | 2009-05-04 | 2009-05-05 | 2010-05-30 | 2010-06-08 | 2042797.98 | 2.700 | 0067080
3255 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | IROQUOIS |  | 15 | 0071115 | This project will extend pavement life by resurfacing 4.2 miles of IL 54 near the city of Thawville (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-07-20 | 2009-10-30 | 2009-08-12 | 880320.15 | 4.570 | 0071115
3256 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LOGAN |  | 18 | 0071116 | This project will extend the pavement life by resurfacing a portion of Illinois Route 54 northeast of Mt. Pulaski in Logan County (West-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-14 | 2009-09-30 | 2009-08-20 | 1442589.51 | 6.890 | 0071116
3257 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SCHUYLER |  | 18 | 0073104 | Pavement reconstruct with brick paver wearing surface sidewalk, lighting, streetscape and lighting improvements in Rushville. Section 05-00017-00-FP | Transportation Enhancements | 2011-01-06 | 2011-03-07 | 2012-05-30 | 2011-12-08 | 563972 | 0.000 | 0073104
3258 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CARROLL |  | 16 | 0077103 | This project will extend the pavement life by resurfacing sections of County Highways 4 and 25 in Carroll County (Northwest Illinois). | Pavement Improvement | 2009-09-11 | 2009-09-24 | 2009-10-30 | 2009-10-23 | 309728 | 20.560 | 0077103
3259 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JEFFERSON |  | 19 | 0081059 | This project will extend the pavement life by resurfacing 1.32 miles of County Highway 42/43 in Jefferson County.(Southern Illinois) | Pavement Improvement | 2010-03-01 | 2010-05-03 | 2010-06-30 | 2010-05-19 | 413197 | 1.240 | 0081059
3260 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JERSEY |  | 17 | 0083047 | This project will improve safety by replacing an existing bridge over Otter Creek near Fieldon, Illinois (Southwest Illinois) | Bridge Replacement | 2010-03-01 | 2010-06-01 | 2010-07-30 | 2010-09-03 | 242119.48 | 0.010 | 0083047
3261 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | EDGAR |  | 15 | 0091071 | This project will extend the pavement life by resurfacing 4.5 miles of Illinois 16 approximately 25 miles southeast of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-08 | 2010-03-30 | 2010-08-30 | 2010-05-18 | 2280573.99 | 29.060 | 0091071
3262 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | Multiple | 0095126 | This project will substantially improve the roadway by constructing a new bridge over Finch Creek on County Highway 16 east of Galesburg (West-Central Illinois) | Bridge Replacement | 2009-08-03 | 2009-08-17 | 2009-11-30 | 2009-10-05 | 255000 | 0.020 | 0095126
3263 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 18 | 0095133 | This project will substantially improve the roadway by constructing a new bridge over Swab Run Creek in eastern Knox County, approximately 20 miles southeast of Galesburg (West-Central Illinois) | Bridge Replacement | 2009-12-17 | 2010-05-17 | 2010-06-30 | 2010-07-08 | 146886.21 | 0.010 | 0095133
3264 | ILLINOIS | Completed | C220,C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 00D1691 | This project will substantially improve mobility by constructing a new prefabricated pedestrian bridge over Buffalo Creek & construct a 0.14 mile shared use path between Dundee Road & Glendale Rd in t | Transportation Enhancements | 2009-09-15 | 2009-10-05 | 2010-05-30 | 2010-09-02 | 271795 | 0.000 | 00D1691
3265 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 00D1701 | This project will provide for pedestrain safety by improving the sidewalk, pedestrain lighting and signage adjacent to Roosevelt Road in Westchester, (Northeastern Illinois) | Transportation Enhancements | 2009-09-10 | 2009-09-17 | 2010-05-30 | 2010-12-03 | 246034.86 | 0.700 | 00D1701
3266 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 00D1710 | This project will provide for pedestrian safety by constructing a new Pedestrain path from Three Oaks Road through Cary Grove Park to District 26 Cary Jr High School (Northeast Illinois). | Transportation Enhancements | 2010-01-26 | 2010-04-01 | 2010-09-30 | 2010-12-11 | 537983.8 | 0.000 | 00D1710
3267 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | ROUND LAKE BEACH | 02 | 00D1761 | This project will provide for pedestrian safety by streetscaping Lake Park Ave from 51st St. to 57th St. in the City of Chicago. (Northeastern Illinois) | Bridge Improvement | 2011-11-26 | 2011-06-11 | 2012-11-30 |  | 2050000 | 0.010 | 00D1761
3268 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 00D1779 | This project will provide for pedestrian safety by removing an existing pedestrian path and constructing a new path with lighting and landscaping from Lee St. north for 1.08 miles in the Evanston Lake | Transportation Enhancements | 2010-05-24 | 2010-09-07 | 2011-12-30 | 2011-07-18 | 598867 | 0.000 | 00D1779
3269 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 00D1795 | This project consists of a safety and traffic enhancement by installing 1.63 miles of new lighting and streetscape improvements on Miner Street, Oakton Street and Lee Street corridors in Des Plaines, Cook County (Northeastern Illinois). | Transportation Enhancements | 2009-12-10 | 2010-03-16 | 2010-10-30 | 2012-02-22 | 800000 | 0.000 | 00D1795
3270 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 00D1808 | Install street lighting along FAP 348 (Harlem Ave. / IL 43) from 70th St to 93rd St in Bridgeview. Section 06-00054-00-LT | Transportation Enhancements | 2010-12-01 | 2011-03-12 | 2012-08-30 | 2012-11-10 | 1580800 | 2.800 | 00D1808
3271 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 00D1809 | This project will enhance the roadway by installing landscape improvements of select medians, embankments, planting of trees, shrubs, and flowers, on 4.1 miles of Harlem Avenue from 191st St. to 159th | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-08-30 | 2012-08-06 | 851389 | 0.600 | 00D1809
3272 | ILLINOIS | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 00D1810 | This project will substantially improve the roadway by reconstructing a section IL 137 by providing new asphalt pavement and other roadway improvements in Winthrop Harbor. (Northeast Illinois) | Transportation Enhancements | 2010-01-26 | 2010-01-27 | 2011-06-30 |  | 1372162 | 0.130 | 00D1810
3273 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 00D2131 | This project consists of a substantial transportation improvement by construction of a new concrete bicycle and pedestrian path and other associated improvements between the cities of Rock Island and Moline (Northwest Illinois). | Transportation Enhancements | 2009-11-18 | 2010-05-10 | 2009-05-30 | 2010-10-22 | 446000 | 0.000 | 00D2131
3274 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 00D2132 | Sidewalks, landscaping & lighting along River Drive from 25th to 34th in Moline (WIU Rivertech Streetscape) Section 06-00234-00-LS | Transportation Enhancements | 2010-10-20 | 2011-07-19 | 2011-05-30 | 2011-12-12 | 615381 | 0.000 | 00D2132
3275 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 00D2133 | Pedestrian Riverwalk, sidewalks (2) Pedestrian structures, amphitheatre area, retaining walls, lighting and landscaping. Section 06-00543-00-BT | Transportation Enhancements | 2011-02-24 | 2011-04-11 | 2015-09-30 | 2012-11-27 | 1261230 | 0.000 | 00D2133
3276 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 00D2139 | This project will substantially improve pedestrian safety by constructing a new pedestrian bridge over the Pecatonic River in the city of Freeport and repair of a timber bridge in Stephenson County (Northwest Illinois). | Transportation Enhancements | 2009-12-22 | 2010-03-01 | 2011-10-30 | 2011-10-23 | 1141394 | 0.000 | 00D2139
3277 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 00D2140 | This project will improve pedestrian and bicycle safety by constructing a multi-use path, sidewalks and other related items at Howell Park in the city of Dixon (Northwest Illinois). | Transportation Enhancements | 2010-04-07 | 2010-04-07 | 2010-08-30 | 2011-10-05 | 341481 | 0.000 | 00D2140
3278 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 00D3058 | This project will substantially improve pedestrian trafficabilty by constructing sidewalk and two bridges near Riverfront Park in the city of Marseilles (East-Central Illinois). | Transportation Enhancements | 2010-02-26 | 2010-07-06 | 2011-12-30 | 2011-06-01 | 207303 | 0.000 | 00D3058
3279 | ILLINOIS | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 00D3059 | This project will improve safety by installing lighting and signing along IL 113 in the village of Diamond (East-Central Illinois). | Transportation Enhancements | 2010-04-23 | 2010-09-09 | 2011-12-30 |  | 301413 | 1.000 | 00D3059
3280 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | STARK |  | 18 | 00D4102 | This project will enhance safety and aesthetics by reconstructing sidewalks and installing lighting at the instersection of Illinois Routes 17 and 91 in Stark County (West-Central Illinois). | Transportation Enhancements | 2010-05-04 | 2010-07-19 | 2010-09-30 | 2010-09-29 | 208400 | 0.230 | 00D4102
3281 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 00D4103 | This project will enhance pedestrian safety by constructing sidewalks and replacing curb and gutter along 0.75 mile of Pfeiffer Road in Bartonville, Peoria County (West-Central Illinois). | Transportation Enhancements | 2010-05-18 | 2010-05-28 | 2010-08-30 | 2010-08-13 | 533925 | 0.750 | 00D4103
3282 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 00D5090 | This project will provide for pedestrian and bicycle safety by constructing a 4-mile multi-use path on the southwest side of Bloomington (Central Illinois). | Transportation Enhancements | 2010-05-18 | 2010-05-20 | 2010-08-30 | 2010-09-17 | 1414447 | 0.000 | 00D5090
3283 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 17 | 00D6089 | This project consists of substantial transportation improvement by constructing new pavement with concrete pavers, new sidewalks, decorative lighting, and planting beds on Capital Avenue between 5th | Transportation Enhancements | 2010-03-18 | 2010-03-18 | 2010-08-30 | 2012-03-04 | 1796318 | 0.160 | 00D6089
3284 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 00D6090 | This project will substantially improve the community by providing a new bicycle and pedestrian path in Sangamon County(West-Central Illinois) | Transportation Enhancements | 2010-06-29 | 2010-07-07 | 2012-07-30 | 2010-08-30 | 2513840 | 0.000 | 00D6090
3285 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 17 | 00D7036 | This project will provide landscaping for the Farm Progress Grounds in Decatur (Southeast Illinois). | Transportation Enhancements | 2009-10-29 | 2010-04-12 | 2010-05-30 | 2010-06-13 | 74400 | 0.000 | 00D7036
3286 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | CLINTON |  | 19 | 00D8124 | This project will provide pedestrian and bicycle accommodations along old US Route 50 from Memorial Drive to Madison Drive in the town of Breese, IL (Southwest Illinois) | Transportation Enhancements | 2010-12-22 | 2011-07-15 | 2011-07-30 | 2011-11-17 | 172045 | 0.000 | 00D8124
3287 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 00D8131 | This project will add new sidewalk, replace broken curb and gutter add lighting o the streets and adjust the stop lights to operate more efficiently on various streets throughout the city of East St. Louis, Illinois(Southwest Illinois) | Transportation Enhancements | 2009-12-10 | 2010-05-11 | 2010-10-30 | 2010-11-12 | 676786 | 0.000 | 00D8131
3288 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | GALLATIN |  | 19 | 00D9084 | This project will enhance pedestrian and bicycle accommodations by constructing a bike trail accessing the Gallatin County Visitors Center in Gallatin County (Southern Illinois). | Transportation Enhancements | 2010-04-28 | 2010-04-28 | 2010-10-30 | 2012-11-24 | 782960 | 0.000 | 00D9084
3289 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 00D9094 | This project will enhance pedestrian and bicycle accommodations by constructing a bike trail connection between the cities of Eldorado and Harrisburg (Southern Illinois). | Transportation Enhancements | 2010-04-23 | 2010-04-23 | 2011-05-30 | 2012-12-20 | 1256795 | 0.000 | 00D9094
3290 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 00D9096 | LAND ACQUISITION FOR THE CONSTRUCTION OF A BIKE/PED TRAIL TO CONNECT ELDORADO TO HARRISBURG, SECTION 06-00082-00-BT | Transportation Enhancements | 2009-09-14 | 2011-03-02 | 2009-10-30 | 2011-03-02 | 22500 | 0.000 | 00D9096
3291 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0109052 | This project will extend the structure life by providing new exterior paint on two county highway bridges in McDonough County (West-Central Illinois). | Bridge Improvement | 2010-04-06 | 2010-04-16 | 2010-06-30 | 2010-05-28 | 77947 | 0.020 | 0109052
3292 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 0113029 | This project will provide for pedestrian safety by constructing a 1.13 mile multi-use bike trail in Chenoa, approximately 25 miles north of Bloomington (East-Central Illinois) | Transportation Enhancements | 2009-08-04 | 2009-08-07 | 2009-10-30 | 2009-10-01 | 10685.46 | 0.000 | 0113029
3293 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MASON |  | 18 | 0125018 | This project consists of a safety and traffic enhancement by upgrading pavement markings on various routes throughout Mason County (West-Central Illinois). | Safety/Traffic Management | 2010-04-15 | 2010-06-01 | 2010-05-30 | 2010-07-29 | 81099.91 | 0.000 | 0125018
3294 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | POPE |  | 19 | 0132130 | This project will extend the pavement life by milling, patching and resurfacing 3.61 miles of IL145 in Pope county, Illinois (Southern Illinois). | Pavement Improvement | 2009-06-02 | 2009-07-01 | 2009-08-30 | 2009-08-31 | 985175.18 | 3.750 | 0132130
3295 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA |  | 18 | 0143050 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on County Highway 15 over Spoon River approximately 30 miles northwest of Peoria (West-Central Illinois) | Bridge Improvement | 2009-09-08 | 2009-09-28 | 2010-07-30 | 2010-10-05 | 379741 | 0.020 | 0143050
3296 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | PULASKI |  | 12 | 0153030 | This project will substantially improve the roadway by constructing a new bridge over Pulaski Slough on Morris Road in Pulaski County, Illinois (Southern Illinois Illinois) | Bridge Replacement | 2009-08-27 | 2009-09-21 | 2009-10-30 | 2009-11-16 | 157081 | 0.020 | 0153030
3297 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 0167058 | This project will extend the pavement life by resurfacing a portion of a Sangamon County road near Springfield (West-Central Illinois). | Pavement Improvement | 2009-10-14 | 2009-10-12 | 2010-03-30 | 2010-04-28 | 1636269.35 | 11.200 | 0167058
3298 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 0167059 | This project will substantially improve the roadway by constructing a new intersection and signals along with other roadway improvements at Village Center Drive and Business 55 in Sherman (West-Central Illinois). | Pavement Improvement | 2010-04-19 | 2010-06-01 | 2010-07-30 | 2010-12-03 | 280212 | 0.010 | 0167059
3299 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 0169103 | This project will extend the pavement life by resurfacing 3.6 miles of US 52 near the city of Troy Grove (East-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-27 | 2009-09-30 | 2009-08-10 | 682587.86 | 3.630 | 0169103
3300 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 0174118 | This project will substantially improve the roadway by constructing a new bridge over Big Indian Creek on County Highway 6 in Dekalb County (East-Central Illinois). | Bridge Replacement | 2009-07-30 | 2009-08-10 | 2009-12-30 | 2009-11-05 | 314054 | 10.020 | 0174118
3301 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | STARK |  | 18 | 0175023 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on CH 23 over Jack Creek at Toulon which is approximately 30 miles northwest of the City of Peoria ( West-Central Illinois) | Bridge Replacement | 2009-09-15 | 2009-09-16 | 2009-10-30 | 2009-11-12 | 184642 | 0.010 | 0175023
3302 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 0179032 | This project will enhance safety by widening the pavement to accommodate left and right turn lanes into Tazewell County facilities on Illinois Route 9 approximately 10 miles south of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-26 | 2010-07-30 | 2010-08-25 | 420000 | 0.010 | 0179032
3303 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 0179106 | This project will extend the pavement life by resurfacing 3 miles of South 1st Street in Dekalb County (East-Central Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-18 | 2010-05-30 | 2010-06-04 | 547560 | 3.310 | 0179106
3304 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | UNION |  | 12 | 0181048 | This project will substantially improve the roadway by replacing the existing bridge carrying Kratzinger Hollow Rd over Green Creek near Jonesboro, Illinois (Southern Illinois) | Bridge Replacement | 2010-03-10 | 2010-05-06 | 2010-06-30 | 2010-06-07 | 115000 | 0.010 | 0181048
3305 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 0185103 | This project will extend the pavement life by resurfacing sections of Ambot Road and Walton Road in Lee County (Northwest Illinois). | Pavement Improvement | 2009-12-09 | 2010-05-11 | 2010-07-30 | 2010-07-06 | 433493 | 6.350 | 0185103
3306 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WARREN |  | 17 | 0187038 | This project consists of a safety and traffic enhancement by upgrading roadway signs throughout Warren County (West-Central Illinois) | Safety/Traffic Management | 2009-12-14 | 2009-12-24 | 2010-11-30 | 2010-09-29 | 270457.3 | 0.000 | 0187038
3307 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0188120 | This project will extend pavement life by resurfacing 2 miles of County Highway 8 in Bureau County (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-09-30 | 2009-10-07 | 292800 | 4.000 | 0188120
3308 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | OGLE |  | 16 | 0189108 | This project will extend the pavement life by resurfacing sections of Freeport Road in Ogle County (Northwest Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-24 | 2009-09-30 | 2009-10-23 | 574019 | 21.470 | 0189108
3309 | ILLINOIS | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO |  | 16 | 0201027 | This project consists of improving safety by upgrading guardrail to current standards throughout Winnebago County (Northwest Illinois). | Safety/Traffic Management | 2009-10-29 | 2009-11-09 | 2009-12-30 | 2010-01-07 | 220186.31 | 0.000 | 0201027
3310 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MERCER |  | 17 | 0206116 | This project will prepare for a drainage improvement project on County Highway 4 in Henry County (West-Central Illinois). | Other | 2009-10-27 | 2009-10-27 | 2010-03-30 | 2010-03-01 | 65786.28 | 1.310 | 0206116
3311 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MERCER |  | 17 | 0206117 | This project will extend the pavement life by resurfacing and replacing culverts along a section of County Highway 4 in Mercer County (West-Central Illinois). | Pavement Improvement | 2010-04-20 | 2010-04-30 | 2010-08-30 | 2010-07-23 | 286259 | 1.310 | 0206117
3312 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0209003 | This item provides construction engineering service for inspection and oversight for the improvement of I-94 from Martin Luther King Drive to 159th Street in Chicago, Cook County. | Other | 2009-04-30 | 2009-04-30 | 2011-07-30 | 2011-06-05 | 2714990 | 9.000 | 0209003
3313 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0209004 | This item provides design engineering services for the development of plans and specifications for the construction of I-290 from Thorndale Ave to Grand Ave; I-290 from I-88 to I-94/90 and I-355 from | Other | 2009-05-18 | 2009-05-18 | 2011-05-30 | 2011-03-09 | 3786482.69 | 14.000 | 0209004
3314 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0209005 | This item provides construction engineering service for inspection and oversight of the project on I-57 to replace 7 bridge decks in Cook and Will Counties (Northeast Illinois) | Other | 2009-05-15 | 2009-05-15 | 2010-02-28 | 2011-01-28 | 1300000 | 0.000 | 0209005
3315 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 0209006 | This item provides construction engineering service for inspection and oversight of the ramp modification project on I-94/90 from Hubbard's Cave to I-290 and the bridge deck replacement project at 26t | Other | 2009-05-07 | 2009-05-07 | 2011-02-28 |  | 1189458 | 0.000 | 0209006
3316 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0209007 | This item provides construction engineering service for inspection and oversight of the project for bridge improvement I-90/94 in Chicago (Northeast Illinois) | Other | 2009-05-11 | 2009-05-11 | 2010-12-30 |  | 702536 | 0.000 | 0209007
3317 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0209008 | This item provides construction engineering service for inspection and oversight of the project to resurface 159th Street in Homer Glen (Northeast Illinois) | Other | 2009-06-02 | 2009-06-02 | 2010-02-28 | 2011-06-05 | 573998.67 | 30.000 | 0209008
3318 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0209009 | This item provides construction engineering service for inspection and oversight of the project to resurface Burnham Avenue in Calumet City (Northeast Illinois) | Other | 2009-05-05 | 2009-05-05 | 2010-02-28 | 2011-06-05 | 784742.88 | 0.000 | 0209009
3319 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0209010 | This item provides construction engineering service for inspection and oversight of the project to resurface Lemont Road in Lemont (Northeast Illinois) | Other | 2009-04-30 | 2009-04-30 | 2012-12-30 | 2010-12-10 | 710068 | 0.000 | 0209010
3320 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209013 | This item provides preliminary engineering services for the development of projects in the District 1 area (Northeast Illinois) | Other | 2009-06-02 | 2009-06-02 | 2011-12-30 | 2011-06-01 | 3999948.01 | 0.000 | 0209013
3321 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209014 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 2009-05-15 | 2009-05-15 | 2012-12-30 | 2010-12-01 | 399986.3 | 0.000 | 0209014
3322 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209015 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 2009-05-15 | 2009-05-15 | 2012-12-30 | 2010-12-01 | 299479.98 | 0.000 | 0209015
3323 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209016 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 2 (Northwest Illinois). | Other | 2009-05-12 | 2009-05-12 | 2012-12-30 | 2010-12-01 | 299869.55 | 0.000 | 0209016
3324 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209017 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 4 (West-Central Illinois). | Other | 2009-06-02 | 2009-06-02 | 2011-12-30 | 2012-06-15 | 1700000 | 0.000 | 0209017
3325 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209018 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 5 (East-Central Illinois). | Other | 2009-05-18 | 2009-05-18 | 2012-12-30 | 2010-01-05 | 500000 | 0.000 | 0209018
3326 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 0209019 | This project will ensure quality infrastructure by providing engineering oversight during construction of a highway interchange on Interstate 55/70 in Madison County (Southwest Illinois). | Other | 2009-06-25 | 2009-06-25 | 2012-05-30 |  | 2313381 | 0.000 | 0209019
3327 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209020 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 2009-05-20 | 2009-05-20 | 2012-05-30 |  | 500000 | 0.000 | 0209020
3328 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209021 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 2009-06-11 | 2009-06-11 | 2012-05-30 |  | 500000 | 0.000 | 0209021
3329 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209022 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 2009-05-15 | 2009-05-15 | 2012-05-30 | 2010-08-31 | 500000 | 0.000 | 0209022
3330 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209023 | This contract will assist the state DOT in inspection of Fedral Aid projects in construction | Other | 2009-05-15 | 2009-05-15 | 2012-05-30 | 2011-10-24 | 500000 | 0.000 | 0209023
3331 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209024 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 2009-05-18 | 2009-05-18 | 2011-12-30 | 2011-12-01 | 299684.97 | 0.000 | 0209024
3332 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209025 | This contract will assist the state DOT in inspection of Federal Aid projects in construction | Other | 2009-05-18 | 2009-05-18 | 2011-05-30 | 2012-04-20 | 299935.55 | 0.000 | 0209025
3333 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STATEWIDE |  |  | 0209026 | This project provides Quality Assurance on pavement resurfacing on projects statewide in Illinois | Other | 2009-05-29 | 2009-05-29 | 2012-05-30 |  | 300000 | 0.000 | 0209026
3334 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 0209027 | This project will ensure quality infrastructure by providing engineering oversight during construction of highway improvement projects in IDOT District 4 (West-Central Illinois). | Other | 2009-06-26 | 2009-06-26 | 2011-12-30 | 2012-05-11 | 1599947 | 0.000 | 0209027
3335 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 0236104 | Bridge rehabilitation remove and replace deck beams to the structure carrying FAS 236 (CH 5) over the South.. Section 10-00150-00-BR | Bridge Improvement | 2010-12-15 | 2011-05-02 | 2011-06-30 | 2011-05-31 | 30159.5 | 0.010 | 0236104
3336 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 0239102 | This project will extend the pavement life by resurfacing sections of County Highways 39 and 24 in Henry County (Northwest Illinois). | Pavement Improvement | 2010-03-01 | 2010-06-01 | 2010-06-30 | 2010-06-29 | 375367.45 | 3.460 | 0239102
3337 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0242114 | This project will extend pavement life by providing a surface treatment on 9.5 miles of County Highway 16 in Bureau County (East-Central Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2009-09-30 | 2009-09-15 | 128800 | 28.380 | 0242114
3338 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0244101 | This project will extend pavement life by providing a surface treatment on 7.8 miles of County Highway 9 in Bureau County (East-Central Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-15 | 2009-09-30 | 2009-09-27 | 83792 | 12.780 | 0244101
3339 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL |  | 14 | 0281101 | This project will extend the pavement life by resurfacing a section of County Highway 19 in Kendall County (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-10-05 | 2009-10-30 | 2009-10-20 | 361760 | 3.050 | 0281101
3340 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 0287106 | This project will substantially improve the roadway by constructing a new bridge over the Mazon River on County Highway C29 in Grundy County (East-Central Illinois). | Bridge Replacement | 2010-03-01 | 2010-07-06 | 2010-11-30 | 2011-05-13 | 333347 | 0.010 | 0287106
3341 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 0294108 | This project will extend the pavement life by providing for 13.05 miles of pavement removal and resurfacing on Old U.S. Route 66 north of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-10-30 | 2009-10-29 | 3075370.29 | 16.770 | 0294108
3342 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON, GRUNDY |  | 11 | 0298103 | This project will extend pavement life by resurfacing 7 miles of Old US 66 between the cities of Dwight and Gardener (East-Central Illinois). | Pavement Improvement | 2009-05-11 | 2009-06-15 | 2009-10-30 | 2009-10-19 | 1983365.17 | 14.280 | 0298103
3343 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 0301058 | This project will extend the pavement life by resurfacing a section of US 20 in western Stephenson County (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-07-27 | 2009-11-30 | 2009-11-13 | 1655501.24 | 5.860 | 0301058
3344 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0303042 | This project will extend the pavement life by resurfacing 5.21 miles on IL 173 from Lake County Line to US 12 in the Villages of Fox Lake and Richmond (Northeastern Illinois) | Pavement Improvement | 2009-04-30 | 2009-05-18 | 2009-08-30 | 2009-08-11 | 1861530.67 | 5.460 | 0303042
3345 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 0303043 | This project will extend the pavement life by resurfacing a section of IL 251 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-26 | 2009-10-30 | 2009-07-17 | 498240.41 | 2.960 | 0303043
3346 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 0303044 | This project will extend the pavement life by resurfacing sections of IL 251 in the city of Loves Park (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-09-30 | 2009-08-21 | 963894.35 | 3.180 | 0303044
3347 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JERSEY |  | Multiple | 0304042 | This project will extend the pavement life by milling, patching and resurfacing Grafton, Illinois (Southwest Illinios). | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2009-11-30 | 2009-10-07 | 2671744.35 | 8.360 | 0304042
3348 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JERSEY, MADISON | ST. LOUIS (MO)-IL | Multiple | 0304043 | This project will extend the pavement life by milling, patching and resurfacing near Alton, Illinois (Southwest Illinios). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-11-30 | 2009-10-07 | 2024824.77 | 6.560 | 0304043
3349 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0305038 | This project will substantially improve the roadway by reconstructing a section of Palatine Rd by widening the road, providing new asphalt pavement and other roadway improvements in Palatine (Northeastern Illinois) | Pavement Improvement | 2010-04-28 | 2010-04-28 | 2011-05-30 | 2012-01-07 | 7434961.91 | 0.800 | 0305038
3350 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY |  | 16 | 0305041 | This project will extend the pavement life by milling, patching, resurfacing and striping 2.34 miles on US 14 from Bunker Hill Rd to Park Lane Dr in unincorporated McHenry | Pavement Improvement | 2009-05-06 | 2009-05-26 | 2009-09-30 | 2009-07-30 | 631892.25 | 2.350 | 0305041
3351 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND |  | 17 | 0308035 | This project will extend the pavement life by resurfacing 4.4 miles of IL 81 near the city of Cambridge (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-27 | 2010-06-30 | 2011-05-12 | 4145854.26 | 4.410 | 0308035
3352 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 0310130 | Construction of two new structures carrying IL Route 255 over Humbert Road in Godfrey, IL (Southwest Illinois) | Pavement Widening | 2009-07-16 | 2009-09-14 | 2011-10-30 |  | 4892208.46 | 0.770 | 0310130
3353 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | SCHUYLER |  | 18 | 0310131 | This project will extend the pavement life by resurfacing a portion of US Route 67 near Rushville (West-Central Illinois). | Pavement Improvement | 2009-04-17 | 2009-04-23 | 2009-10-30 | 2009-10-29 | 3703886.22 | 9.860 | 0310131
3354 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0310132 | This project will extend the pavement life by resurfacing 3.5 miles of US 67 near the city of Milan (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-20 | 2009-10-30 | 2009-10-09 | 3631151.19 | 3.480 | 0310132
3355 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CASS |  | 18 | 0310134 | This project will extend the pavement life by resurfacing and updating guardrail to a portion of US Route 67 from Beardstown to 3 miles north of Meredosia (West-Central Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-04 | 2009-09-30 | 2009-08-13 | 2447155.29 | 9.960 | 0310134
3356 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0311037 | This project will extend the pavement life by resurfacing 4.1 miles on US Route 34 in the City of Downers Grove (Northeast Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-01 | 2009-10-30 | 2009-09-26 | 2682617.34 | 3.370 | 0311037
3357 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0311039 | This project will extend the pavement life by resurfacing 2.09 miles on US Route 34 in Napreville (Northeast Illinois). | Pavement Improvement | 2009-10-16 | 2010-04-14 | 2010-07-30 | 2010-09-16 | 1341100.45 | 4.300 | 0311039
3358 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0315055 | This project will extend the pavement life by providing surface improvements on a 0.57 mile section of U.S. Route 136 in Macomb (West-Central Illinois) | Pavement Improvement | 2009-07-30 | 2009-08-10 | 2009-11-30 | 2009-11-12 | 599706.52 | 1.140 | 0315055
3359 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | OGLE |  | 16 | 0316035 | This project will extend the pavement life by resurfacing a section of US 52 and IL 26 near the city of Polo (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-18 | 2009-07-30 | 2009-07-21 | 363285.85 | 1.270 | 0316035
3360 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | Multiple | 0317080 | This project will extend the pavement life by providing for 7.3 miles of pavement repairs and resurfacing on U.S. Route 24 north of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-04 | 2009-08-30 | 2009-07-02 | 1696469.4 | 7.280 | 0317080
3361 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DOUGLAS, PIATT |  | 15 | 0323026 | This project will extend the pavement life by providing for 9.6 miles of pavement removal and resurfacing on U.S. Route 36 south of Champaign (East-Central Illinois) | Pavement Improvement | 2009-04-23 | 2009-05-06 | 2009-09-30 | 2009-08-10 | 2479001.73 | 9.780 | 0323026
3362 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 0325051 | This project will extend the bridge life by replacing the bridge deck and making other bridge improvements at the intersection of US Route 45 and Illinois Route 16 in Mattoon (Southeast Illinois). | Bridge Improvement | 2010-02-24 | 2010-03-08 | 2010-11-30 | 2011-06-24 | 3006880.32 | 0.040 | 0325051
3363 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 0326077 | This project will extend the pavement life by resurfacing 10.9 miles of IL 47 near the city of Mazon (East-Central Illinois). | Pavement Improvement | 2009-06-08 | 2009-08-17 | 2009-10-30 | 2009-11-02 | 2355015.69 | 11.020 | 0326077
3364 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON, GRUNDY |  | Multiple | 0326078 | This project will extend the pavement life by resurfacing 15.6 miles of IL 47 between the cities of Dwight and Saunemin (East-Central Illinois). | Pavement Improvement | 2009-06-02 | 2009-06-08 | 2010-05-30 | 2009-11-06 | 3899088.31 | 15.490 | 0326078
3365 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0326079 | This project will extend the pavement life by milling, patching, resurfacing and striping 3.55 miles on US 30/IL 47 from US 30/IL 56 to Kendall County lines in the Village of Sugar Grove (Northeaster | Pavement Improvement | 2009-05-18 | 2009-05-26 | 2009-08-30 | 2009-09-09 | 1955152.42 | 5.880 | 0326079
3366 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 0327043 | This project consists of 2.61 miles of resurfacing which will extend the pavement life by milling, patching and resurfacing in Marion County, Illinois (Southwest Illinios). | Pavement Improvement | 2009-05-04 | 2009-05-13 | 2009-09-30 | 2009-07-30 | 792533.86 | 2.720 | 0327043
3367 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | IROQUOIS |  | 15 | 0329106 | This project will extend the pavement life by resurfacing a section of County Highway 10 in Iroquois County (East-Central Illinois). | Pavement Improvement | 2010-02-22 | 2010-04-13 | 2010-06-30 | 2010-06-25 | 645683 | 5.700 | 0329106
3368 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL |  | 11 | 0330050 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on us Route 45 over Forked Creek 2.1 miles south of Manhattan Monee Road (Northeast Illinois). | Bridge Improvement | 2009-05-11 | 2009-07-13 | 2009-09-30 | 2011-11-19 | 245139.8 | 0.010 | 0330050
3369 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL |  | 11 | 0330051 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 45/52 over south Branch of Forked Creek 0.5 miles south of Joliet Road near Peotone (Northeast Illinois). | Bridge Improvement | 2009-05-11 | 2009-07-13 | 2009-09-30 | 2009-12-11 | 241853.94 | 0.010 | 0330051
3370 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 0330052 | This project will extend the pavement life by resurfacing a section of IL 17 near the city of Aroma (East-Central Illinois). | Pavement Improvement | 2009-06-01 | 2009-08-03 | 2009-09-30 | 2009-10-13 | 2993807.34 | 4.300 | 0330052
3371 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 04 | 0330053 | This project will extend the pavement life by resurfacing 1.66 miles of Mannheim Rd in theVillages of Hillside, Melrose Park, and Stone Park, (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-08 | 2009-10-30 | 2009-09-18 | 1592173.81 | 1.430 | 0330053
3372 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0330054 | This project will extend the pavement life by resurfacing 1.22 miles of US 12/45 from Prospect Avenue to Walnut Avenue in the City of DesPlaines in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-09-30 | 2009-09-02 | 735694.24 | 1.140 | 0330054
3373 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0330055 | This project will extend the pavement life by resurfacing 1.20 miles of US 12/45 from US 12 (Rand Rd) to Walnut Avenue within the City of DesPlaines in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-09-30 | 2009-09-02 | 912549.95 | 3.210 | 0330055
3374 | ILLINOIS | Underway | C240 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 0331048 | This project will substantially improve mobility by constructing a new four lane roadway and new bridge over west Harrisburg drainage ditch which will rerout a protion of IL13 around Harrisburg, Illinois (Southern Illinois). | New Construction | 2009-06-01 | 2009-07-13 | 2011-08-30 |  | 14183910.09 | 5.500 | 0331048
3375 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 0331050 | This project will substantially improve the roadway by constructing a new bridge over Mud Creek on IL 13 in Jackson County, Illinois (Southern Illinois) | Bridge Replacement | 2009-10-22 | 2009-11-02 | 2011-10-30 | 2011-09-03 | 1865415.6 | 0.040 | 0331050
3376 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0332091 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on IL 1 over Trim Creek 1 mile south of Beecher (Northeast Illinois). | Pavement Improvement | 2009-05-11 | 2009-06-23 | 2010-07-30 | 2010-10-20 | 695876.22 | 0.010 | 0332091
3377 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0334018 | This project will extend the pavement life by milling, patching and resurfacing 1.13 miles on US Rt. 12 (Main St) from Wisconsin State Line to IL 73 (Kenosha Rd) in the Village of Richmond (Northeastern Illinois) | Pavement Improvement | 2009-06-01 | 2009-06-22 | 2009-09-30 | 2009-08-14 | 453639.51 | 1.120 | 0334018
3378 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0335011 | This project will extend the pavement life by resurfacing 3.91 miles on IL 176 between Nish Rd and IL 31in the Villages of Crystal Lake and Prairie Grove (Northeastern Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-08-30 | 2009-08-18 | 1288150.05 | 3.890 | 0335011
3379 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0335012 | This project will extend the pavement life by milling, patching, resurfacing and striping 1.44 miles on IL 60 from IL 21(Milwaukee Ave) to west of I-94(Tri-State Tollway) in the Villages of Libertyville and Vernon Hills(Northeastern Illinois) | Pavement Improvement | 2009-06-01 | 2009-06-19 | 2009-11-30 | 2009-09-19 | 970128.99 | 1.700 | 0335012
3380 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0335013 | This project will extend the pavement life by milling, patching and resurfacing 2.96 miles on IL Rt 176 and IL 60/83 from west of Thorngate Dr to IL 60/83 and from IL 176 to Midlothian Rd in Mundelein (Northeastern Illinois). | Pavement Improvement | 2009-10-23 | 2010-04-14 | 2010-06-30 | 2010-07-29 | 1219266.35 | 5.960 | 0335013
3381 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0338036 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL 59 at four structures in West Chicago (Northeast Illinois). | Bridge Improvement | 2009-05-04 | 2009-06-01 | 2009-10-30 | 2009-12-03 | 1070936.11 | 1.990 | 0338036
3382 | ILLINOIS | Completed | C200,C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0338037 | This project will improve safety and traffic operations by reconstructing the intersection of IL 59 and US Route 30 in Plainfield (Northeast Illinois) | Pavement Improvement | 2009-06-16 | 2009-06-19 | 2011-05-30 | 2012-05-26 | 7903047.94 | 0.010 | 0338037
3383 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0338038 | This project will extend the pavement life by resurfacing 5.80 miles on IL 59 in West Chicago (Northeast Illinois). | Pavement Improvement | 2009-10-28 | 2010-03-17 | 2010-08-30 | 2010-08-31 | 3889619.88 | 12.580 | 0338038
3384 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0338039 | This project will extend the pavement life by milling, patching and resurfacing 2.45 miles on IL Rt 59/Hough street from IL 22 to Lake-Cook Rd in Barrington (Northeastern Illinois). | Pavement Improvement | 2009-10-27 | 2010-04-12 | 2010-07-30 | 2010-09-02 | 906298.26 | 5.000 | 0338039
3385 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | FORD |  | 15 | 0340103 | This project will substantially improve the roadway by constructing new bridges over creeks on County Highway 26 southwest of the city of Paxton (East-Central Illinois). | Bridge Replacement | 2009-09-08 | 2009-09-23 | 2010-05-30 | 2009-12-07 | 319891 | 0.020 | 0340103
3386 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0341045 | This project will extend the pavement life by resurfacing 1.43 miles of Touhy Avenue (IL 72) from Lee Street to the DesPlaines River Road in the Villages of Des Plaines and Rosemont in Cook County. (Northeastern Illnois). | Pavement Improvement | 2009-04-23 | 2009-05-12 | 2009-08-30 | 2009-08-19 | 1312389.16 | 1.700 | 0341045
3387 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0341046 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL 72 over I-90 in Gilberts in Northeastern Illinois | Bridge Improvement | 2009-06-01 | 2009-06-08 | 2009-09-30 | 2009-12-07 | 725497.89 | 0.010 | 0341046
3388 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0341047 | This project will extend the pavement life by milling, patching and resurfacing 0.98 miles of Il 72 in the Village of Hoffman Estates in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-08-07 | 2009-08-14 | 2009-10-30 | 2010-03-12 | 1225099.36 | 2.120 | 0341047
3389 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0347021 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on Il 38 over Kress Creek in West Chicago (Northeast Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-08-30 | 2009-10-29 | 383598.44 | 0.010 | 0347021
3390 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0348042 | This project will extend the bridge life by partial and full depth patching of the bridge deck, bridge deck overlay, joint repair, and making other roadway improvements to the IL 43 bridge over Stoney | Bridge Improvement | 2009-06-01 | 2009-06-22 | 2009-10-30 | 2009-12-01 | 697058.16 | 0.010 | 0348042
3391 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL |  | 14 | 0349013 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on US Rt. 30 over River St in Montgomery (Northeastern Illinois) | Bridge Improvement | 2009-04-23 | 2009-06-25 | 2009-08-30 | 2009-10-29 | 445859.2 | 0.020 | 0349013
3392 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL, KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 0349014 | This project will extend the pavement life by milling, resurfacing and striping 2.78 miles on US Rt.30 from IL Rt 47 to Orchard Rd in the Village of Montgomery (Northeastern Illinois) | Pavement Improvement | 2009-05-18 | 2009-05-26 | 2009-08-30 | 2009-10-29 | 1019149.52 | 3.540 | 0349014
3393 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 0349114 | This project will substantially improve the roadway by replacing two bridges on County Highway 10 north of Weston in Livingston County (East-Central Illinois). | Bridge Replacement | 2010-03-02 | 2010-04-01 | 2010-08-30 | 2010-09-10 | 623639 | 0.020 | 0349114
3394 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0350029 | This project will extend the pavement life by resurfacing 1.69 miles of IL 50 (Cicero Avenue) from IL 19 (Irving Road) to I-94 in the City of Chicago. | Pavement Improvement | 2009-04-23 | 2009-05-11 | 2009-09-30 | 2009-11-30 | 1558990.02 | 3.060 | 0350029
3395 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0350030 | This project will extend the pavement life by resurfacing 2.92 miles of US 41/IL 50 from Foster Street to Touhy Avenue in Lincolnwood in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-18 | 2009-10-30 | 2009-12-01 | 2265153.23 | 2.910 | 0350030
3396 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 0350031 | This project will extend pavement life by resurfacing 0.847 miles of US 41 from Old Orchard Road to Central Avenue in the Villages of Skokie and Wilmette in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-08-30 | 2009-08-27 | 651426.3 | 0.820 | 0350031
3397 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0350032 | This project will extend the life of the pavement by resurfacing 1.512 miles of Cicero Avenue (IL 50) from 34th Street to 46th Street and drainage improvements at IL 50 under I-55 within Cicero & Chicago, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-07-27 | 2009-09-15 | 2009-10-30 | 2009-12-02 | 1382759.2 | 1.460 | 0350032
3398 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0351018 | This project will substantially improve the roadway by reconstructing 1.92 miles of US 6 (159th street) from I-294 (Tri-State Tollway) to IL 1 (Halsted Street) in Harvey and Markham in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-06-11 | 2009-06-12 | 2011-07-30 | 2011-12-12 | 18883703.23 | 2.330 | 0351018
3399 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0351019 | This project will extend the pavement life by resurfacing 4.78 miles on IL 7 in Homer Glen (Northeast Illinois). | Pavement Improvement | 2009-05-21 | 2009-06-09 | 2009-11-30 | 2009-09-29 | 1557324.92 | 5.180 | 0351019
3400 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 0351020 | This project will extend the pavement life by milling, patching and resurfacing 2.59 miles of US 6 / IL 7 (159th St) from Will-Cook Rd to US 45 in the Village of Orland Park in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-05-21 | 2009-06-09 | 2009-10-30 | 2009-07-15 | 808496.85 | 2.980 | 0351020
3401 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0352010 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on IL Rt 137 over Des Plaines River in Libertyville (Northeastern Illinois) | Bridge Improvement | 2009-04-30 | 2009-05-06 | 2009-09-30 | 2009-09-10 | 604593.79 | 0.010 | 0352010
3402 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 0352012 | This project will extend the pavement life by milling, patching, resurfacing, curb and gutter 2.52 miles on IL 137 from Martin Luther King Dr to west of US Rt. 41 in the Village of North Chicago (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-23 | 2009-10-30 | 2009-11-09 | 2389866.12 | 2.510 | 0352012
3403 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0353014 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on US 30 over IL 394 in the Village of Ford Heights in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-09-08 | 2010-04-16 | 2010-11-30 | 2011-09-14 | 2943917.06 | 0.020 | 0353014
3404 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WOODFORD |  | 18 | 0358102 | This project will substantially improve the roadway by replacing multiple drainage structures on and reconstructing 2.26 miles of County Highway 1 approximately 25 miles northeast of Peoria (West-Central Illinois) | Pavement Improvement | 2009-07-24 | 2009-08-17 | 2010-07-30 | 2010-10-12 | 466776 | 6.000 | 0358102
3405 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KANE, COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0360010 | This project will extend the pavement life by milling, patching and resurfacing 1.95 miles on IL 25 (Dundee ave) from I-90(Northwest Tollway) to IL 72(Higgins Rd) in the Villages of Dundee and Elgin (Northeastern Illinois) | Pavement Improvement | 2009-06-11 | 2009-06-18 | 2009-11-30 | 2009-12-07 | 1762847.87 | 2.030 | 0360010
3406 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WOODFORD |  | 18 | 0367105 | Thie project will extend the pavement life by resurfacing a 2.5 mile section of County Highway 23 east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-03 | 2010-04-19 | 2010-06-30 | 2010-05-05 | 302173 | 3.120 | 0367105
3407 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARSHALL |  | 18 | 0369106 | This project will extend the pavement life by resurfacing 2 miles of County Highway 1 in Marshall County, approximately 25 miles northeast of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-09 | 2010-05-20 | 2010-05-30 | 2010-06-02 | 267610 | 2.000 | 0369106
3408 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0370007 | This project will extend the pavement life by resurfacing 1.52 miles Western Avenue from 87th to 99th Street. (Northeastern Illinois). | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2009-10-30 | 2009-08-28 | 1487273.46 | 2.920 | 0370007
3409 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA |  | 18 | 0386105 | This project will extend the pavement life by resurfacing 3.3 miles of Kickapoo-Edwards Road just west of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-03 | 2010-04-14 | 2010-05-30 | 2010-09-28 | 129720 | 3.270 | 0386105
3410 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 0391018 | This project will extend the pavement life by patching 19 miles of Interstate 39 trhough Lee County (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-26 | 2009-08-30 | 2009-08-28 | 1157799.72 | 19.230 | 0391018
3411 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 0391026 | This project will extend the bridge life by deck patching, placement of permanent protective shielding and other roadway improvements on 39th Street (Perhing Road) over S. Racine Avenue and Norfolk an | Bridge Improvement | 2009-04-28 | 2009-05-26 | 2009-08-30 | 2009-09-24 | 242959.67 | 0.010 | 0391026
3412 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 0392007 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 26th Street and Frontage Road B over the Franklin Connector which connects Stevenson Expr | Bridge Improvement | 2009-04-23 | 2009-07-20 | 2010-11-30 | 2011-07-01 | 5854169.45 | 0.020 | 0392007
3413 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0415107 | This project will extend the pavement life by resurfacing 0.5 miles of County Highway 13 in McDonough County (West-Central Illinois). | Pavement Improvement | 2010-03-02 | 2010-03-12 | 2010-05-30 | 2010-06-16 | 132000 | 0.510 | 0415107
3414 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HENDERSON |  | 17 | 0418113 | This project will improve the roadway by providing new concrete pavement on a section of County Highway 15 in Henderson County (West-Central Illinois). | Pavement Improvement | 2010-03-30 | 2010-04-09 | 2010-06-30 | 2010-10-05 | 229282 | 3.000 | 0418113
3415 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | HANCOCK |  | 17 | 0428103 | This project will extend the pavement life by resurfacing a portion Hancock County Highway 11 from Basco, IL to five miles west of Basco (West-Central Illinois). | Pavement Improvement | 2009-09-10 | 2009-09-18 | 2009-12-30 | 2010-04-21 | 476459 | 10.000 | 0428103
3416 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0436107 | This project will extend the pavement life by resurfacing 0.5 miles of County Highway 1 in McDonough County (West-Central Illinois). | Pavement Improvement | 2010-03-08 | 2010-03-18 | 2010-05-30 | 2010-06-16 | 132000 | 1.020 | 0436107
3417 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SCHUYLER |  | 18 | 0454104 | This project will substantially improve the roadway by constructing a new bridge over Dutchmans Creek on County Highway 8 near Browning in Schuyler County (West-Central Illinois). | Bridge Replacement | 2010-05-18 | 2010-08-12 | 2010-08-30 | 2010-12-09 | 243160 | 0.010 | 0454104
3418 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 0467106 | This project will extend the pavement life by resurfacing 3 miles of Allentown Rd approximately 10 miles southeast of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-20 | 2010-06-30 | 2010-05-06 | 446467 | 2.840 | 0467106
3419 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 0468102 | This project will extend the pavement life by resurfacing 7 blocks of Minier Avenue in Minier, southeast of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-21 | 2010-05-30 | 2010-04-28 | 155000 | 0.600 | 0468102
3420 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 0470107 | This project will extend the pavement life by providing for 1.4 miles of resurfacing on Dee Mack Road east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-05-01 | 2010-05-30 | 2010-06-09 | 320000 | 3.000 | 0470107
3421 | ILLINOIS | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 0478106 | This project will substantially improve 0.74 mile of County Highway 29 by providing new concrete pavement and other roadway improvements north of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-07-24 | 2009-08-06 | 2010-01-30 | 2010-05-07 | 1080835 | 0.020 | 0478106
3422 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 0494102 | This project will extend the pavement life by providing for 2.42 miles pavement repairs and resurfacing on Horse Farm Road in LeRoy, southeast of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-09-08 | 2009-09-14 | 2009-11-30 | 2009-11-05 | 510000 | 4.840 | 0494102
3423 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 0496106 | This project will substantially improve the roadway by constructing a new bridge on County Highway 14 over the Middle Branch approximately 50 miles northeast of Champaign (East-Central Illinois) | Bridge Replacement | 2009-12-07 | 2010-03-15 | 2010-09-30 | 2010-07-28 | 505094 | 0.010 | 0496106
3424 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO |  | 16 | 0505024 | This project will extend the pavement life and improve drainage by resurfacing and replacing culverts along a section of IL 75 in the city of Rockton (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-25 | 2010-10-30 | 2010-10-15 | 1865419.88 | 11.320 | 0505024
3425 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 0513103 | This project will extend the pavement life with 10.4 miles of pavement repairs on Chicago Street approximately 20 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2009-04-23 | 2009-06-11 | 2009-09-30 | 2009-08-19 | 844802.75 | 9.720 | 0513103
3426 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | BOONE |  | 16 | 0525115 | This project will extend the pavement life by resurfacing 5.4 miles of US 20 near the city of Belvidere (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-10-30 | 2009-08-21 | 1628081.27 | 5.450 | 0525115
3427 | ILLINOIS | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 0531108 | This project will substantially improve the roadway by reconstructing and widening County Highway 18 south of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-10 | 2010-04-05 | 2010-10-30 | 2011-05-14 | 674106 | 13.920 | 0531108
3428 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0535001 | This project will extend the pavement life by milling, patching anfd resurfacing 6.59 miles on IL 60/83 between IL Rt 20(Belvidere Rd) and IL 176 in the Villages of Mundelein, Ivanhoe, Volo and Round Lake Park (Northeastern Illinois) | Pavement Improvement | 2009-06-01 | 2009-06-20 | 2010-05-30 | 2009-11-23 | 2092946.58 | 6.880 | 0535001
3429 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | PIATT |  | 15 | 0535102 | This project will extend the pavement life by resurfacing a section of Shady Rest Road approximately 15 miles west of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-22 | 2010-03-29 | 2010-08-30 | 2010-08-13 | 276697 | 1.560 | 0535102
3430 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | DE WITT |  | 15 | 0543105 | This project will substantially improve the roadway by constructing a new bridge on Parnell Road over Salt Creek approximately 25 miles south of Bloomington (East-Central Illinois) | Bridge Improvement | 2009-12-14 | 2010-03-15 | 2010-08-30 | 2010-10-25 | 7515.79 | 0.010 | 0543105
3431 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 18 | 0548103 | This project will substantially improve the roadway by replacing a new bridge over Lake Fork Creek on County Highway 58 west of Maroa (West-Central Illinois) | Bridge Replacement | 2009-12-14 | 2010-04-19 | 2010-06-30 | 2010-08-30 | 328230 | 0.010 | 0548103
3432 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0556233 | This project will address noise issues with the construction of noise walls along I-55 in Romeoville and Planfield (Northeast Illinois) | Transportation Enhancements | 2009-09-14 | 2009-09-24 | 2011-05-30 | 2012-07-21 | 8546818.35 | 6.570 | 0556233
3433 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0556234 | This project will address noise issues with the construction of noise walls along I-55 in Joliet and Planfield (Northeast Illinois) | Transportation Enhancements | 2009-10-07 | 2009-10-17 | 2011-05-30 | 2011-06-04 | 8162557.2 | 7.930 | 0556234
3434 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0556238 | Not in FMIS | Pavement Improvement | 2010-05-18 | 2010-06-01 | 2010-11-30 | 2011-09-06 | 4425119.87 | 0.020 | 0556238
3435 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LOGAN |  | 18 | 0559102 | This project will extend the bridge life by rehabilitating the bridge deck and making other improvements on County Highway 2 two miles north of Lincoln (West-Central Illinois). | Bridge Improvement | 2010-04-09 | 2010-04-28 | 2010-08-30 | 2010-08-17 | 368344 | 0.010 | 0559102
3436 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 0561029 | This project will substantially improve the roadway by constructing new bridges over creeks on IL 2 near Sauk Valley College (Northwest Illinois). | Bridge Replacement | 2009-12-08 | 2010-04-05 | 2010-11-30 | 2010-10-15 | 2000982.56 | 0.030 | 0561029
3437 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 16 | 0565003 | This project will extend the pavement life by resurfacing 2.9 miles of IL 136 near the city of Fulton (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-18 | 2009-10-30 | 2009-09-11 | 1284750.45 | 3.210 | 0565003
3438 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 0567098 | This project will extend the pavement life by resurfacing 5.3 miles of IL 38 east of the city of Dekalb (East-Central Illinois). | Pavement Improvement | 2009-06-01 | 2009-07-06 | 2009-09-30 | 2009-09-03 | 1894158.35 | 10.600 | 0567098
3439 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MASON |  | 18 | 0567115 | This project will extend the pavement life by providing a surface treatment on a section of County Highway 20 near Forest City in Mason County (West-Central Illinois). | Pavement Improvement | 2009-08-27 | 2009-09-08 | 2009-09-30 | 2009-10-01 | 229661 | 3.830 | 0567115
3440 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 0567126 | This project will extend the pavement life by resurfacing 2.2 miles of IL 38 in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 2009-08-11 | 2009-08-31 | 2010-07-30 | 2010-05-19 | 1829377.42 | 4.340 | 0567126
3441 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 0572149 | This project will extend the pavement life by milling, rubblizing, patching and resurfacing 8.68 miles of Interstate 57 in Franklin County Illinois (Southern Illinios). | Pavement Improvement | 2009-04-28 | 2009-07-13 | 2009-08-30 | 2009-08-31 | 8982883.85 | 8.680 | 0572149
3442 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 0574128 | This project will extend the pavement life by resurfacing a portion of Interstate 57 from south of Arcola to Mattoon (Southeast Illinois). | Pavement Improvement | 2009-05-20 | 2009-06-09 | 2010-08-30 | 2010-08-24 | 21644677.63 | 10.870 | 0574128
3443 | ILLINOIS | Underway | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | MENARD |  | 18 | 0574209 | This project will substantially improve the roadway by designing plans for reconstructing a section of County Highway 2 near Petersburg (West-Central Illinois). | Other | 2010-08-01 | 2010-10-01 | 2011-06-30 |  | 224677 | 6.160 | 0574209
3444 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CASS |  | 18 | 0575312 | This project will substantially improve the roadway by constructing a new bridge over Middle Creek on County Highway 12 near Newmansville (West-Central Illinois). | Bridge Replacement | 2010-04-15 | 2010-06-01 | 2010-08-30 | 2010-10-19 | 212157 | 0.010 | 0575312
3445 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK |  | 01 | 0577277 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 112th Place over I-57 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-06-01 | 2009-06-04 | 2009-11-30 | 2010-07-03 | 2695246.92 | 0.010 | 0577277
3446 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577278 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 103rd Street over I-57 in Chicago. (Northeastern Illinois). | Bridge Improvement | 2009-05-04 | 2009-06-01 | 2009-11-30 | 2010-10-28 | 2035725.16 | 0.010 | 0577278
3447 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0577279 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on North Peotone/Joliet Road over I-57in Peotone (Northeast Illinois). | Bridge Improvement | 2009-05-11 | 2009-07-20 | 2009-09-30 | 2009-11-05 | 416352.79 | 0.010 | 0577279
3448 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577280 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the 115th Street over I-57 in Chicago, Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-04-23 | 2009-05-11 | 2009-11-30 | 2010-10-15 | 2803515.13 | 0.010 | 0577280
3449 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577281 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 125th Street over I-57 in Calumet Township. (Northeastern Illinois). | Bridge Improvement | 2009-04-28 | 2009-05-24 | 2009-11-30 | 2010-06-08 | 1559048.19 | 0.010 | 0577281
3450 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0577282 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on 111th Street over I-57 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-06-01 | 2010-04-01 | 2010-09-30 | 2011-06-18 | 2934155.15 | 0.010 | 0577282
3451 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0577283 | This project will extend the bridge life by repairing the bridge deck and new deck overlay to 0.06 miles of the 167th Street bridge over I-57 in the Cities of Oark Park and Country Club Hills in Cook County, (Northeastern Illinois). | Bridge Improvement | 2009-06-22 | 2009-07-17 | 2009-10-30 | 2010-04-27 | 599680.68 | 0.010 | 0577283
3452 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0577285 | This project will extend the pavement life by milling, patching and resurfacing 7.2 miles of I-57 from the Will Co Line to 175th St in the Villages of Country Cub Hills, Matteson, Bremen, and Richton Park in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-23 | 2010-03-26 | 2010-08-30 | 2010-10-05 | 12102830.73 | 14.480 | 0577285
3453 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0587024 | This project will extend the pavement life by resurfacing 6.2 miles of IL 92 between the cities of Ohio and Walnut (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-01 | 2009-08-30 | 2009-07-23 | 1872317.64 | 5.910 | 0587024
3454 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 0592052 | This project will extend the pavement life by milling, patching and resurfacing 1.78 miles in St. Clair County, IL (Southwest Illinois) | Pavement Improvement | 2009-05-11 | 2009-05-15 | 2009-10-30 | 2009-09-04 | 808855.39 | 1.780 | 0592052
3455 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PIKE |  | 18 | 0598102 | This project will extend the pavement life by resurfacing a 3.57 mile section of County Highway 2 from Baylis to New Salem in Pike County (West-Central Illinois). | Pavement Improvement | 2010-04-01 | 2010-04-28 | 2010-06-30 | 2010-07-07 | 452500 | 3.060 | 0598102
3456 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SCOTT |  | 18 | 0605107 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on County Highway 3 over Wolf Run Creek northwest of Bluffs (West-Central Illinois). | Bridge Improvement | 2010-04-27 | 2010-07-26 | 2010-06-30 | 2010-12-06 | 162350 | 0.010 | 0605107
3457 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0607078 | This project will extend the pavement life by resurfacing 1.11 miles on US Routes 52/30/6 in Joliet (Northeast Illinois). | Pavement Improvement | 2009-05-11 | 2009-05-21 | 2009-08-30 | 2009-09-26 | 592221.76 | 1.160 | 0607078
3458 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0607079 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 30 over Hickory Creek in Joliet (Northeast Illinois). | Bridge Improvement | 2009-05-11 | 2009-06-15 | 2009-09-30 | 2009-10-15 | 329999.7 | 0.010 | 0607079
3459 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 0611014 | This project will extend the pavement life by resurfacing 4 miles of IL 92 in the city of Rock Island (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-08 | 2009-08-30 | 2009-07-23 | 648677.93 | 2.340 | 0611014
3460 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 0611015 | This project will extend the pavement life by resurfacing a section of IL 81 near the city of Andover (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-08-30 | 2009-06-17 | 384371.34 | 0.720 | 0611015
3461 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MASON |  | 18 | 0614030 | This project will extend the pavement life by milling, patching, and resurfacing a portion of Illinois Route 78 from Havana to Saidora (West-Central Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-08 | 2009-11-30 | 2010-03-24 | 5268038.33 | 13.610 | 0614030
3462 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 0618003 | This project will extend pavement life by providing for 6.8 miles of surface improvements on IL Rte. 41 east of the City of Macomb which is approximately 50 miles west of the City of Peoria (West-Central Illinois) | Pavement Improvement | 2009-07-30 | 2009-08-13 | 2009-11-30 | 2009-11-02 | 1475854.58 | 12.680 | 0618003
3463 | ILLINOIS | Completed | C250,C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | Multiple | 0627106 | This project will extend the pavement life by providing a surface treatment on a section of County Highway 37 and 31 in Sangamon County (West-Central Illinois). | Pavement Improvement | 2010-08-05 | 2010-08-30 | 2010-06-30 | 2010-12-01 | 507319 | 9.250 | 0627106
3464 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 0630006 | This project will extend the pavement life by providing for 4.84 miles of pavement repairs and resurfacing on IL Route 100 near the City of Bryant which is approximately 35 miles southwest of the City of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-04 | 2009-08-30 | 2009-07-18 | 898945.73 | 4.970 | 0630006
3465 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL |  | 11 | 0631015 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on IL 102 over Rayns Creek southeast of Wilmington (Northeast Illinois). | Bridge Improvement | 2009-04-28 | 2009-06-08 | 2009-09-30 | 2009-10-14 | 238149.41 | 0.010 | 0631015
3466 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 0638010 | This project will extend the pavement life by resurfacing a section of US 6 in the city of Geneseo (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-08-30 | 2009-07-31 | 624614.88 | 2.290 | 0638010
3467 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 0638013 | This project will substantially improve the roadway by constructing a new bridge over Hennepin Canal on IL 82 near the city of Geneseo (Northwest Illinois). | Bridge Replacement | 2009-12-08 | 2010-04-05 | 2010-11-30 | 2010-11-05 | 1512229 | 0.020 | 0638013
3468 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 0642123 | This project will substantially improve the roadway by constructing a new section of roadway near Mattoon (Southeast Illinois). | New Construction | 2009-07-22 | 2009-08-10 | 2010-10-30 | 2010-11-04 | 307906 | 2.260 | 0642123
3469 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | STARK |  | 18 | 0643204 | This project will extend the pavement life by providing for 3.4 miles of pavement repair and resurfacing on IL Route 17 at Toulon which is approximately 30 miles northwest of the City of Peoria ( West-Central Illinois) | Pavement Improvement | 2009-07-30 | 2009-08-03 | 2009-09-30 | 2009-08-21 | 502367.71 | 6.940 | 0643204
3470 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHRISTIAN |  | 19 | 0645112 | This project will extend the pavement life by resurfacing and other improvements on approximately six miles of County Highway 1 near Vanderville (West-Central Illinois). | Pavement Improvement | 2010-04-27 | 2010-06-01 | 2010-08-30 | 2010-10-22 | 420098 | 9.190 | 0645112
3471 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 17 | 0646069 | This project will extend the pavement life by resurfacing a section of IL 40 in the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 2009-05-04 | 2009-09-08 | 2009-11-30 | 2010-05-06 | 1119300.53 | 1.250 | 0646069
3472 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MARSHALL, STARK |  | 18 | 0646070 | This project will extend the pavement life by providing for 4.43 miles of pavement repair and resurfacing on IL Route 40 and IL Route 17 approximately 25 miles north of the City of Peoria (West-Central Illinois) | Pavement Improvement | 2009-07-30 | 2009-08-10 | 2009-10-30 | 2009-11-10 | 1163946.27 | 8.070 | 0646070
3473 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JO DAVIESS |  | 16 | 0650008 | This project will improve drainage by replacing 2 culverts on IL 78 in Jo Daviess County. | Bridge Improvement | 2010-03-03 | 2010-05-03 | 2010-09-30 | 2010-11-12 | 646110.45 | 0.030 | 0650008
3474 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE, PUTNAM |  | Multiple | 0653028 | This project will extend the pavement life by resurfacing 6.5 miles of IL 18 between the cities of Magnolia and Lostant (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-22 | 2009-09-30 | 2009-08-10 | 1273129.8 | 12.130 | 0653028
3475 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 0662063 | This project will substantially improve the roadway by reconstructing the intersection of IL Route 4 and Monroe/Old Jacksonville Rd. by providing new pavement and other roadway improvements in Springfield (West-Central Illinois). | Pavement Improvement | 2010-03-01 | 2010-04-15 | 2011-05-30 | 2011-10-26 | 2174000 | 3.370 | 0662063
3476 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CUMBERLAND |  | 15 | 0662102 | This project will extend the pavement life by resurfacing and other improvements on FAS Route 662 in Cumberland County (Southeast Illinois). | Pavement Improvement | 2010-04-09 | 2010-04-20 | 2010-08-30 | 2010-05-14 | 252088 | 1.200 | 0662102
3477 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WARREN |  | 17 | 0665013 | This project will extend the pavement life by providing for 5.08 miles of pavement repair and resurfacing along IL Route 116 near the City of Roseville which is approximately 60 miles west of the City of Peoria (West-Cental Illinois) | Pavement Improvement | 2009-07-27 | 2009-08-10 | 2009-10-30 | 2009-09-19 | 1085914.56 | 10.120 | 0665013
3478 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX, FULTON |  | 17 | 0665014 | This project provides for 8.3 miles of pavement repairs and resurfacing, extending the pavement life, on Illinois Route 116 near the City of St. Augustine which is approximately 40 miles west of the City of Peoria (West-Central Illinois) | Pavement Improvement | 2009-07-27 | 2009-08-06 | 2009-11-30 | 2009-11-09 | 2514670.91 | 14.560 | 0665014
3479 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WOODFORD |  | 18 | 0673024 | This project will extend the pavement life by resurfacing of 5.90 miles of IL Routes 116 and 117 near the west city limits of the City of Roanoke which is approximately 20 mile east of the City of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-07 | 2009-10-30 | 2009-07-16 | 2207309.24 | 6.120 | 0673024
3480 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 0674111 | This project will substantially improve the roadway by replacing a box culvert on Fish Hatchery Road near Paradise (Southeast Illinois). | Bridge Improvement | 2009-05-21 | 2009-06-17 | 2009-07-30 | 2009-07-02 | 162702.01 | 0.010 | 0674111
3481 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | EDGAR |  | 15 | 0678106 | This project will substantially improve the roadway by reconstructing and resurfacing a section of County Highway 21, approximately 50 miles southeast of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-17 | 2010-07-19 | 2010-06-30 | 2010-09-23 | 336991 | 2.710 | 0678106
3482 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 0681037 | This project wil substantially improve the roadway by reconstructing a section of IL 116 in the village of Cullom. | Pavement Improvement | 2009-04-30 | 2009-06-22 | 2010-05-30 | 2010-06-15 | 3061067.67 | 0.890 | 0681037
3483 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 0681038 | This project will extend the pavement life by resurfacing the road and replacing curb and gutter in the village of Saunemin (East-Central Illinois). | Pavement Improvement | 2010-04-07 | 2010-05-06 | 2011-06-30 | 2010-11-29 | 616988 | 0.650 | 0681038
3484 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HANCOCK |  | 17 | 0685028 | This project will extend the pavement life by resurfacing a portion of Illinois Route 9 in Hancock County from Dallas City to LaHarpe (West-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-11 | 2009-10-30 | 2009-10-29 | 3527422.24 | 13.280 | 0685028
3485 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 0693065 | Remvl & repl of structure carrying IL 9 over Mackinaw River Trib 0.3 mil W of Mackinaw inc. pvmnt rem/rep, earthwork, HMA overlay etc. Sect. 119BR-2 BR | Bridge Replacement | 2011-01-03 | 2011-01-13 | 2011-09-30 | 2011-09-15 | 913271.79 | 0.010 | 0693065
3486 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CRAWFORD |  | 15 | 0696107 | This project will substantially improve the roadway by constructing a new bridge over Bennett Creek on County Highway 6 near Robinson in Crawford County (Southeast Illinois). | Bridge Replacement | 2009-12-28 | 2009-12-28 | 2010-07-30 | 2010-06-29 | 186600 | 0.200 | 0696107
3487 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CRAWFORD |  | 15 | 0696108 | Resurface FAS 696 (CH 6) from IL RTE 33 North for 1.55 miles in Crawford County. Section 10-00095-00-RS | Pavement Improvement | 2010-12-16 | 2011-06-10 | 2011-06-30 | 2011-07-14 | 30159.5 | 1.600 | 0696108
3488 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 0697030 | This project will extend the life of the roadway by providing for 6.5 miles of pavement repairs, resurfacing, and bridge deck repairs on Illinois Route 9 in Vermilion County at the Indiana border (East-Central Illinois) | Pavement Improvement | 2009-05-15 | 2009-06-15 | 2009-10-30 | 2009-10-08 | 2085502.67 | 6.630 | 0697030
3489 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | Multiple | 0701184 | This project will extend the pavement life by milling, patching and resurfacing 3. 67 miles of Interstate 55/70 from Canteen Creek to just north of Il 157. In addition this project will include brid | Pavement Improvement | 2010-02-22 | 2010-03-29 | 2010-08-30 | 2011-03-16 | 9577498.24 | 10.930 | 0701184
3490 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | JASPER |  | 19 | 0704138 | This project will substantially improve the roadway by reconstructing a section of County Highway 6 near Gila in Jasper County (Southeast Illinois). | Pavement Improvement | 2009-08-03 | 2009-08-11 | 2009-10-30 | 2009-09-02 | 299807 | 3.500 | 0704138
3491 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 0709024 | This project will extend the pavement life by providing for 3.8 miles of pavement repairs and resurfacing on U.S. Route 136 north of Champaign (East-Central Illinois) | Pavement Improvement | 2009-05-04 | 2009-05-29 | 2009-08-30 | 2009-07-29 | 956727.74 | 3.800 | 0709024
3492 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 0711010 | This project will extend the life of the roadway by providing for 7.6 miles of pavement repairs, resurfacing, and culvert replacement on Illinois Route 119 in Vermilion County at the Indian border (East-Central Illinois) | Pavement Improvement | 2009-05-06 | 2009-05-18 | 2009-10-30 | 2009-10-05 | 1935511.91 | 7.780 | 0711010
3493 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | EFFINGHAM |  | 19 | 0711108 | This project will extend the pavement life by adding new shoulders and resurfacing a portion of County Highway 25 south of Altamont (Southeast Illinois) | Pavement Improvement | 2009-09-16 | 2009-10-07 | 2009-12-30 | 2009-11-09 | 361611 | 8.000 | 0711108
3494 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | FAYETTE |  | 17 | 0712106 | This project will substantially improve the roadway by replacing and repairing several culverts on County Highway 24 in Fayette County (Southeast Illinois). | Bridge Improvement | 2009-08-24 | 2009-09-08 | 2009-12-30 | 2010-08-13 | 410144 | 6.240 | 0712106
3495 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SHELBY |  | 19 | 0713111 | This project will substantially improve the roadway by reconstructing a section of Michigan and Logan Streets by providing new concrete pavement and other roadway improvements in Tower Hill (Southeast Illinois). | Pavement Improvement | 2009-12-10 | 2010-03-09 | 2010-08-30 | 2010-09-27 | 487714 | 0.820 | 0713111
3496 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MONTGOMERY |  | 17 | 0721219 | This project will substantially improve the roadway by reconstructing a new bridge over East Fork of Shoal Creek on County Highway 8 near Filmore (West-Central Illinois) . | Bridge Replacement | 2009-12-14 | 2010-06-14 | 2010-08-30 | 2011-05-10 | 368721 | 0.010 | 0721219
3497 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 0725005 | This project will extend the pavement life by resurfacing 0.9 miles of Illinois Route 10 in Champaign (East-Central Illinois). | Pavement Improvement | 2010-03-15 | 2010-04-12 | 2010-06-30 | 2010-06-01 | 708435.25 | 2.000 | 0725005
3498 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 0726058 | This project will extend the pavement life by milling, patching and resurfacing 6.58 miles of IL 148 in Franklin County, Illinois (Southern Illinios). | Pavement Improvement | 2009-04-28 | 2009-06-08 | 2009-09-30 | 2009-10-01 | 2446918.04 | 13.450 | 0726058
3499 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 0734042 | This project will extend the pavement life by resurfacing a section of IL 251 in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-26 | 2009-08-30 | 2009-07-22 | 318933.82 | 0.630 | 0734042
3500 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | GREENE |  | 17 | 0738107 | This project will improve roadway quality by milling and resurfacing County Highway 10 in Greene County (Southwest Illinois). | Pavement Improvement | 2010-03-19 | 2010-05-17 | 2010-05-30 | 2011-04-29 | 336388 | 1.500 | 0738107
3501 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 15 | 0741094 | This project will extend the pavement life by resurfacing a portion of Illinois Route 105 through the City of Decatur (Southeast Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-27 | 2009-10-30 | 2009-11-23 | 2385691.68 | 3.050 | 0741094
3502 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0741096 | This project will extend the structural life by completing repairs on the viaducts carrying Interstate 74 over IL 92 in the city of Moline (Northwest Illinois). | Bridge Improvement | 2009-04-30 | 2009-05-11 | 2009-08-30 | 2009-09-04 | 756407.74 | 0.020 | 0741096
3503 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 0741097 | This project will extend the pavement life by resurfacing a section of Interstate 74 and completing bridge repairs on several structures in the city of Moline (Northwest Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-11 | 2010-10-30 | 2010-12-03 | 11442129.66 | 5.750 | 0741097
3504 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | PIATT |  | 15 | 0741098 | This project will extend the pavement life by providing for 12.6 miles of pavement repairs and resurfacing on Illinois Route 105 west of Decatur (East-Central Illinois) | Pavement Improvement | 2009-04-30 | 2009-05-20 | 2009-10-30 | 2009-08-27 | 2921806.75 | 12.660 | 0741098
3505 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 0742127 | This project will substantially improve the roadway by constructing new bridges over Opheim Road on Interstate 74 and other roadway improvements north of the city of Woodhull (Northwest Illinois). | Bridge Improvement | 2009-12-08 | 2010-04-05 | 2010-11-30 | 2010-11-02 | 3466511.46 | 0.610 | 0742127
3506 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | Multiple | 0744238 | This project will extend the pavement life by providing for 4.24 miles of pavement repairs and resurfacing on Interstate 74 in Bloomington (East-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-04 | 2010-08-30 | 2010-05-14 | 7205166.81 | 4.610 | 0744238
3507 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA |  | 18 | 0744239 | This project will extend the pavement life by providing for 6.12 miles of pavement removal and resurfacing on a section of Interstate 74 approximately 7 miles west of the City of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-04-29 | 2009-11-30 | 2009-08-14 | 7967475.6 | 5.720 | 0744239
3508 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 0744240 | This project will extend the pavement life by providing for 6.41 miles of pavement repairs, resurfacing, and other improvements to Interstate 74 just east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2009-11-30 | 2009-08-14 | 7872358.65 | 6.730 | 0744240
3509 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | Multiple | 0745079 | This project will extend the pavement life by resurfacing a portion of Illinois Route 104 to the east from Quincy (West-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-18 | 2009-11-30 | 2009-11-30 | 4666894.14 | 5.870 | 0745079
3510 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN, PIATT |  | 15 | 0745158 | This project will extend the pavement life by providing for 4.6 miles of pavement repairs, resurfacing, safety improvements on Interstate 74 west of Champaign (East-Central Champaign) | Pavement Improvement | 2009-05-06 | 2009-05-28 | 2009-10-30 | 2009-09-02 | 3374493.73 | 10.950 | 0745158
3511 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MOULTRIE, DOUGLAS |  | 15 | 0749022 | This project will extend the pavement life by resurfacing and adding shoulders to Illinois Route 133 through Arthur, Douglas County (East-Central Illinois). | Transportation Enhancements | 2010-04-09 | 2010-05-10 | 2010-08-30 | 2010-07-02 | 113877 | 1.140 | 0749022
3512 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 0753036 | This project will extend the pavement life by resurfacing a portion of Illinois Route 104 near Waverly (West-Central Illinois). | Pavement Improvement | 2009-04-30 | 2009-07-27 | 2009-11-30 | 2010-08-13 | 2118638.78 | 2.100 | 0753036
3513 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CALHOUN |  | 17 | 0754113 | This project will extend the pavement life by milling, patching and resurfacing of County Highway 1 from the Village of Hardin city limits to Lincoln Valley Road in Calhoun County, Illinois (Southwest Illinios). | Pavement Improvement | 2009-12-29 | 2010-06-01 | 2010-05-30 | 2010-07-01 | 142719 | 0.640 | 0754113
3514 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | SHELBY |  | 19 | 0766005 | This project will extend the pavement life by resurfacing a portion of Illinois Route 32 west of Oblong (Southeast Illinois). | Pavement Improvement | 2009-04-23 | 2009-04-30 | 2009-10-30 | 2009-06-23 | 2075179.07 | 13.000 | 0766005
3515 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CUMBERLAND |  | 15 | 0773008 | This project will extend the pavement life by resurfacing a portion of Illinois Route 121 in Greenup (Southeast Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-18 | 2009-09-30 | 2009-07-03 | 1378480.65 | 5.180 | 0773008
3516 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BOND |  | 19 | 0777114 | This project will extend the pavement life by resurfacing Sorento Road from New Douglas road to Crane Road in Sorento, Illinois (Southwest Illinois). | Pavement Improvement | 2009-11-03 | 2010-03-01 | 2010-05-30 | 2010-07-07 | 197632.86 | 5.650 | 0777114
3517 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CLINTON |  | 19 | 0778106 | This project will improve driving quality by milling and resurfacing County Highway 14 in Clinton County (Southwest Illinois). | Pavement Improvement | 2010-03-01 | 2010-06-02 | 2010-05-30 | 2010-06-18 | 327104 | 4.240 | 0778106
3518 | ILLINOIS | Completed | C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 0778107 | This project will extend the pavement life by resurfacing St. Rose Road from the city of Highland to the Clinton County line in Madison County (Southwest Illinois). | Pavement Improvement | 2010-05-10 | 2010-05-12 | 2010-06-30 | 2010-06-22 | 422778.23 | 3.110 | 0778107
3519 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BOND |  | 19 | 0779105 | Planning and design engineering to replace the bridge carrying North Pokey Road over Indian Creek in Bond County, IL (Southwest Illinois) | Other | 2010-05-24 | 2010-05-24 | 2010-12-30 | 2011-08-30 | 34691.57 | 0.010 | 0779105
3520 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CRAWFORD |  | 15 | 0781030 | This project will extend the pavement life by resurfacing a portion of Illinois Route 33 west of Oblong (Southeast Illinois). | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2010-07-30 | 2010-12-10 | 6162844.79 | 2.520 | 0781030
3521 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 0788004 | This project will substantially improve the roadway by reconstructing a section of Illinois Route 3 by providing new pavement and other roadway improvements in Venice (Southwest Illinois). | New Construction | 2009-06-16 | 2009-10-12 | 2011-08-30 | 2011-03-03 | 3755356.36 | 1.260 | 0788004
3522 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WASHINGTON |  | 19 | 0788112 | This project will improve driving quality by patching, resurfacing, and upgrading pavement markings along County Highway 24 near Hoyleton, Illinois (Southwest Illinois). | Pavement Improvement | 2010-03-01 | 2010-07-06 | 2010-07-30 | 2011-06-28 | 340000 | 4.000 | 0788112
3523 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CLAY |  | 19 | 0801230 | Preliminary engineering for a structure replacement over Laws Creek east of Ingram in Clay County. Section 09-00082-00-BR | Other | 2009-06-19 | 2009-06-22 | 2010-04-30 | 2010-05-31 | 47000 | 0.000 | 0801230
3524 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CLAY |  | 19 | 0801231 | This project will substantially improve the roadway by constructing a new bridge over Laws Creek on East Dundas Lane near Ingraham(Southeast Illinois). | Bridge Replacement | 2010-04-19 | 2010-05-20 | 2010-09-30 | 2010-08-18 | 230366 | 0.010 | 0801231
3525 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | RICHLAND |  | 19 | 0801232 | This project will extend the pavement life by resurfacing and other improvements on East Dundas Lane near Dundas (Southeast Illinois). | Pavement Improvement | 2010-04-21 | 2010-05-07 | 2010-05-30 | 2010-05-19 | 229556 | 1.190 | 0801232
3526 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 0802064 | This project will extend the pavement life by resurfacing 7.5 miles of Interstate 80 near the city of Seatonville (East-Central Illinois). | Pavement Improvement | 2009-05-21 | 2009-06-08 | 2009-10-30 | 2009-07-16 | 3681905.14 | 7.360 | 0802064
3527 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 0803130 | This project will extend the pavement life by resurfacing 30 miles of Interstate 80 in LaSalle County (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-17 | 2009-08-30 | 2009-06-01 | 1174180.11 | 29.990 | 0803130
3528 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 0803131 | This project will extend the pavement life by providing a surface treatment on 6.3 miles of Interstate 80 in western Grundy County (East-Central Illinois). | Pavement Improvement | 2009-05-11 | 2009-06-15 | 2009-07-30 | 2009-07-16 | 1500910.6 | 6.300 | 0803131
3529 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 0805071 | This project will extend the pavement life by resurfacing 6.125 miles of I-80 from 80th Ave to I-290 in the Tinley Park, Country Club Hills, and Hazel Crest. (Northeastern Illinois). | Pavement Improvement | 2009-10-27 | 2010-04-05 | 2010-08-30 | 2010-12-30 | 15821320 | 13.110 | 0805071
3530 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LAWRENCE |  | 19 | 0805108 | This project will extend the pavement life by widening and resurfacing 3.5 miles of County Highway 9 in Lawrence County (Southeast Illinois). | Pavement Improvement | 2010-03-01 | 2010-04-28 | 2010-07-30 | 2010-07-13 | 284790 | 3.590 | 0805108
3531 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CLARK |  | 15 | 0832013 | This project will extend the pavement life by providing a surface treatment on a seven mile section of IL Route 49 from Casey to the Cumberland County Line (Southeastl Illinois). | Pavement Improvement | 2010-03-10 | 2010-06-01 | 2010-06-30 | 2010-07-19 | 405162.69 | 14.000 | 0832013
3532 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 0836028 | This project will extend the pavement life by providing for 5.7 miles of pavement removal and resurfacing on Illinois Route 49 southeast of Champaign (East-Central Illinois) | Pavement Improvement | 2009-05-06 | 2009-05-11 | 2009-08-30 | 2009-07-01 | 1083541.33 | 5.980 | 0836028
3533 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL |  | 11 | 0840061 | This project will extend the pavement life by resurfacing 3.33 miles on IL 50north of Peotone (Northeast Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-05 | 2009-09-30 | 2009-07-31 | 1455187.96 | 4.110 | 0840061
3534 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | IROQUOIS |  | 15 | 0840062 | This project will extend the pavement life by resurfacing 10.7 miles of IL 49 near the city of Crescent City (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-08 | 2009-10-30 | 2009-08-05 | 2099137.03 | 10.800 | 0840062
3535 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0840063 | This project will extend the pavement life by resurfacing 2.06 miles on IL 50 in Monee/Peotone (Northeast Illinois). | Pavement Improvement | 2009-10-16 | 2010-04-12 | 2010-06-30 | 2010-06-18 | 1041653.69 | 2.900 | 0840063
3536 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 0846019 | This project will extend the pavement life by resurfacing 6.4 miles of IL 53 near the city of Gardener (East-Central Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-13 | 2009-10-30 | 2009-10-09 | 1812639.8 | 6.300 | 0846019
3537 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 0852011 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements on US Route 52 over Jackson Creek 4 miles southeast of IL 53 (Northeast Illinois). | Pavement Improvement | 2009-04-28 | 2009-06-09 | 2009-08-30 | 2009-11-15 | 284227.44 | 0.010 | 0852011
3538 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 0856025 | This project will extend the pavement life by resurfacing 2.65 miles on IL 7 in Joliet and Crest Hill (Northeast Illinois). | Pavement Improvement | 2009-10-23 | 2010-06-22 | 2010-07-30 | 2010-08-31 | 1456928.81 | 9.930 | 0856025
3539 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PERRY |  | 12 | 0865106 | This project will extend the pavement life by resurfacing approximately 1 mile of Old DuQuoin Rd in DuQuoin. (Southern Illinois) | Pavement Improvement | 2010-02-22 | 2010-05-01 | 2010-05-30 | 2010-06-14 | 249928 | 2.880 | 0865106
3540 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 0866007 | This project will substantially improve the roadway by resurfacing 4.41 miles, widening, installing traffic signals and drainage improvements on IL 83 from Wisconsin State line to Petite Lake Rd in th | Pavement Improvement | 2009-08-24 | 2009-09-08 | 2011-05-30 | 2011-12-06 | 14333988.5 | 9.240 | 0866007
3541 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 0869036 | This project will improve safety by replacing an existing bridge on IL 34 near Benton, Illinois (Southern Illinois) | Bridge Replacement | 2010-02-24 | 2010-05-03 | 2010-11-30 | 2011-08-02 | 730800.14 | 0.040 | 0869036
3542 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 0870011 | This project will extend the pavement life by resurfacing 1.06 miles on IL 53 in the City of Lombard (Northeast Illinois). | Pavement Improvement | 2009-04-30 | 2009-05-18 | 2009-08-30 | 2009-12-12 | 444851.03 | 0.990 | 0870011
3543 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITE |  | 15 | 0877013 | This project will substantially improve the roadway by constructing a new bridge over a tributary of Can Creek on IL 141 in White County, Illinois (Southern Illinois) | Bridge Replacement | 2009-12-10 | 2010-01-18 | 2010-11-30 | 2010-12-10 | 815676.5 | 0.200 | 0877013
3544 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | Multiple | 0881018 | This project will extend the pavement life by resurfacing 7.9 miles of Interstate 88 near the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 2009-05-11 | 2009-05-26 | 2009-10-30 | 2009-10-09 | 3922669.19 | 8.450 | 0881018
3545 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JOHNSON |  | 19 | 0885040 | This project will extend the pavement life by milling, patching and resurfacing 8.46 miles of IL 146 in Johnson County, Illinois (Southern Illinios). | Pavement Improvement | 2009-06-02 | 2009-06-25 | 2009-08-30 | 2009-08-26 | 1557257.01 | 8.780 | 0885040
3546 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WHITE |  | 15 | 0887108 | Grade slopes and place riprap to prevent erosion for 0.55 miles on County Highway 7 in White County, Illinois (Southern Illinois) | Pavement Improvement | 2009-09-09 | 2009-10-08 | 2009-10-30 | 2009-11-09 | 234834.84 | 2.000 | 0887108
3547 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WHITE |  | 15 | 0887109 | Grade slopes and place riprap to prevent erosion for 0.26 miles on County Highway 7 in White County, Illinois (Southern Illinois) | Pavement Improvement | 2009-12-10 | 2009-12-15 | 2010-05-30 | 2010-01-26 | 66757 | 0.450 | 0887109
3548 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | GALLATIN |  | 19 | 0888122 | This project will extend the pavement life by resurfacing 4.48 of County Highway 3 in Gallatin Coutny, Illinois (Southern Illinois). | Pavement Improvement | 2009-07-30 | 2009-11-09 | 2009-10-30 | 2009-12-22 | 190041 | 9.000 | 0888122
3549 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 0898107 | This project will extend the pavement life by resurfacing Harco Road from IL 13 to Brushy Creek Road in Saline County (Southern Illinois). | Pavement Improvement | 2009-12-17 | 2010-05-03 | 2010-07-30 | 2010-05-14 | 286154 | 4.390 | 0898107
3550 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0904117 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the Sayre Avenue Bridge over I-90 in Chicago in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-04-23 | 2009-06-08 | 2010-09-30 | 2011-07-09 | 2925184.16 | 0.010 | 0904117
3551 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 0904118 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on the Central Avenue Bridge over I-90 in the City of Chicago, Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-04-28 | 2009-05-18 | 2009-11-30 | 2011-05-03 | 2738721.57 | 0.010 | 0904118
3552 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 0915102 | This project will extend the pavement life by milling, patching and resurfacing 1.57 miles of Grand Tower Road in Jackson County, Illinois (Southern Illinios). | Pavement Improvement | 2009-07-30 | 2009-08-27 | 2009-10-30 | 2009-10-20 | 382828 | 1.590 | 0915102
3553 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JOHNSON |  | 19 | 0924124 | This project will extend the pavement life by resurfacing 1.99 miles of Lick Creek road south from Williamson county line in Johnson County. (Southern Illinois). | Pavement Improvement | 2010-08-05 | 2010-08-10 | 2010-06-30 | 2010-08-27 | 237061 | 1.400 | 0924124
3554 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | UNION |  | 12 | 0926112 | This project will extend the pavement life by resurfacing St. Johns Road from the city of Dongola to IL127 in Union County (Southern Illinois). | Pavement Improvement | 2010-04-12 | 2010-05-11 | 2010-06-30 | 2010-11-18 | 131915 | 5.680 | 0926112
3555 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MASSAC |  | 19 | 0931110 | This project will extend the pavement life by resurfacing 1.35 miles of County Highway 11 in Massac County, Illinois (Southern Illinois). | Pavement Improvement | 2009-09-10 | 2009-10-05 | 2009-10-30 | 2009-11-04 | 176112 | 2.700 | 0931110
3556 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HARDIN |  | 19 | 0934106 | Resurface FAS 934 (Karbers Ridge Rd) from 3.9 miles east of IL RTE 34 easterly for 4.5 miles to the county line. Section 06-00025-00-RS | Pavement Improvement | 2010-12-16 | 2011-04-05 | 2011-06-30 | 2011-05-31 | 126711 | 4.300 | 0934106
3557 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0943416 | This project will extend the pavement life by resurfacing 6.97 miles of I-94 (Bishop Ford Expressway) from Martin Luther King Drive to 130th Street (south of Dolton Avenue) in Chicago in Cook County. | Pavement Improvement | 2009-05-07 | 2009-05-18 | 2010-08-30 | 2010-09-22 | 14032252.99 | 5.260 | 0943416
3558 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 0943417 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements on I-94 over the Little Calumet River and Greenwood Ave. Additionally, the project will sub | Pavement Improvement | 2009-04-29 | 2009-05-11 | 2010-05-30 | 2010-09-22 | 12817333.94 | 4.290 | 0943417
3559 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | ALEXANDER |  | 12 | 0946107 | This project will extend the pavement life by resurfacing 3.99 miles of Miller City Road in Alexander County, Illinois (Southern Illinois). | Pavement Improvement | 2009-07-30 | 2009-09-09 | 2009-10-30 | 2009-10-20 | 184896 | 8.000 | 0946107
3560 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 16 | 1225115 | This project will extend the pavement life by resurfacing sections of Albany Road in western Whiteside County (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-10-12 | 2009-11-30 | 2009-11-05 | 505781 | 9.180 | 1225115
3561 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 1238009 | This project will extend the pavement life by resurfacing 2.83 miles on IL 176 from Midlothian to IL 21 in the Villages of Libertyville and Mundelein (Northeastern Illinois) | Pavement Improvement | 2009-10-21 | 2010-04-12 | 2010-07-30 | 2010-09-18 | 1078944.4 | 7.280 | 1238009
3562 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 1238010 | This project will extend the pavement life by resurfacing 1.17 miles on IL 176 from IL Rt. 21 to St. Mary's Rd in the Village of Libertyville (Northeastern Illinois). This project will also improve b | Pavement Improvement | 2009-10-23 | 2010-04-05 | 2010-08-30 | 2010-10-02 | 778656.97 | 2.930 | 1238010
3563 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PUTNAM |  | 18 | 1254110 | This project will extend the pavement life by resurfacing 2 miles of County Highway 16 in Putnam County (West-Central Illinois). | Pavement Improvement | 2010-04-07 | 2010-04-19 | 2010-05-30 | 2010-04-23 | 137702 | 1.920 | 1254110
3564 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE, COOK, MCHENRY |  | Multiple | 1270004 | This project will extend the pavement life by milling, patching and resurfacing 4.25 miles on Lake-cook Rd from Kane, McHenry, cook county line to Old Hart Rd in Barrington Hills (Northeastern Illinois). | Pavement Improvement | 2009-12-07 | 2010-05-03 | 2010-06-30 | 2010-08-16 | 1048072.7 | 9.060 | 1270004
3565 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 1299109 | This project will extend pavement life by resurfacing a section of County Highway 7 in northern Kankakee County (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-14 | 2009-09-30 | 2009-10-08 | 431841 | 6.560 | 1299109
3566 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1319001 | This project will extend the pavement life by 1.45 miles of resurfacing of Ballard Rd from Rand Rd easterly to Greenwood Ave in the Villages of DesPlaines, Glenview, Niles, Park Ridge, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-28 | 2010-04-19 | 2010-06-30 | 2010-11-23 | 656141.33 | 3.780 | 1319001
3567 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 1323114 | This project will extend the pavement life by resurfacing 7 miles of IL 115 near the city of Kankakee (East-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-06-08 | 2009-10-30 | 2009-08-07 | 1290092.37 | 9.800 | 1323114
3568 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1332015 | This project will extend the pavement life by resurfacing 3.27 miles of IL 43 (Oakton St) from South DesPlaines Road to US 14 (Caldwell Ave) in Park Ridge & Niles in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-11 | 2009-11-30 | 2009-11-14 | 3101154.93 | 3.270 | 1332015
3569 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1340009 | This project will extend the pavement life by resurfacing 0.8 miles of Touhy Ave from IL50 to US41 and from Lawndale Ave to Kimball Ave in Village of Lincolnwood, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-28 | 2010-06-07 | 2010-06-30 | 2010-10-23 | 623113.94 | 2.260 | 1340009
3570 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 1363004 | This project will extend the pavement life by resurfacing 0.98 miles of Gunnison St. from IL 43 (Harlem Ave) to Nagle Ave in Chicago and the Village of Harwood Heights in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-11-03 | 2010-04-09 | 2010-06-30 | 2010-06-17 | 802260.56 | 2.000 | 1363004
3571 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 1365112 | This project will extend the pavement life by resurfacing 5 miles of County Highway 33 in LaSalle County (East-Central Illinois). | Pavement Improvement | 2010-02-19 | 2010-07-19 | 2010-06-30 | 2010-08-19 | 729886 | 6.030 | 1365112
3572 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 1380106 | This project will extend the pavement life by providing for 3.4 miles of pavement repairs and resurfacing of Illinois Route 91 just north of Peoria (West-Central Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-17 | 2009-11-30 | 2009-10-10 | 1225314.17 | 6.980 | 1380106
3573 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 1395003 | This project will extend the pavement life by resurfacing 1.40 miles of Chicago Avenue from Lake St to Thatcher Rd in Melrose Park & Maywood in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-04 | 2009-08-30 | 2009-07-20 | 718415.48 | 1.470 | 1395003
3574 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 1458103 | This project will extend the pavement life by resurfacing a section of County Highway 6 near the City of Canton, approximately 25 miles southwest of Peoria (West-Central Illinois) | Pavement Improvement | 2010-02-19 | 2010-04-27 | 2010-07-30 | 2010-09-07 | 488725 | 2.000 | 1458103
3575 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 1459004 | This project will extend the pavement life by resurfacing 2.95 miles of 26th Street from IL 43 to IL 50 in Berwyn & Cicero in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-18 | 2009-09-30 | 2009-08-31 | 1271977.9 | 3.110 | 1459004
3576 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL |  | 18 | 1464103 | This project wil extend the pavement life by providing for 0.41 mile of pavement removal and resurfacing on Locast Street in Delavan, south of Peoria (West-Central Illinois). | Pavement Improvement | 2009-09-14 | 2010-07-06 | 2009-09-30 | 2010-07-08 | 125000 | 0.680 | 1464103
3577 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 1467006 | This project will extend the pavement life by milling, patching and resurfacing 0.55 miles on 31st Street from IL 171 to DesPlaines Avenue and also on 31st St. from Golfview Rd to IL 171 in the Villag | Pavement Improvement | 2009-04-28 | 2009-05-25 | 2009-07-30 | 2009-06-29 | 254965.07 | 0.620 | 1467006
3578 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1467007 | This project will extend the pavement life by milling, patching and resurfacing 3.61 miles of 31st St from Wolf Rd to IL 171 in the Villages of Westchester, Brookfield, LaGrange Park. (Northeastern Illinois). | Pavement Improvement | 2009-09-09 | 2009-11-07 | 2010-07-30 | 2010-07-03 | 1912289.16 | 7.380 | 1467007
3579 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 1488004 | This project will extend the pavement life with 2.58 miles of milling, resurfacing, patching, curb & gutter, pavement marking & detector loops on 47th St from DuPage County line to East Ave, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-08-30 | 2010-10-21 | 1442223.12 | 6.060 | 1488004
3580 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 1527012 | This project will substantially improve the roadway network by constructing four new bridges and rehabilitation of an existing bridge. Two of the new bridges are located at IL Rt 25/Dunham and IL Rt 2 | New Construction | 2009-07-27 | 2009-08-18 | 2011-05-30 | 2011-10-22 | 1100000 | 0.000 | 1527012
3581 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 1566002 | This project will extend the life of the pavement by surface removal, pavement patching, guardrail removal and replacement, pavement marking on 2.46 miles of 95th st from IL 171 (Archer Ave) to US 45 (LaGrange Road) in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-05-06 | 2009-05-18 | 2009-08-30 | 2009-07-03 | 780486.71 | 2.540 | 1566002
3582 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | BROWN |  | 18 | 1583103 | This project will substantially improve the roadway by constructing a new bridge over Logan Creek on County Highway 3A near Ripley (West-Central Illinois). | Bridge Improvement | 2010-07-30 | 2010-10-04 | 2011-05-30 | 2011-05-19 | 188402 | 0.010 | 1583103
3583 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MASON |  | 18 | 1595103 | FAS 1595 (CH 19) - 4 miles southwest of Mason City at Sleepy Hollow Ditch-Bridge replacement. PE - Phase I | Other | 2009-11-06 | 2009-11-06 | 2010-07-30 | 2011-03-31 | 26681 | 0.010 | 1595103
3584 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 1614104 | This project will extend the pavement life by resurfacing a portion of County Highway 32 in Morgan County and adding lighting at an intersection for a safety improvement near Jacksonville (West-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-11-30 | 2010-05-07 | 328970 | 3.890 | 1614104
3585 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 1618001 | This project will extend the life of the pavement by resurfacing 0.72 miles of 175th Street from Governor's Highway to the intersection of 175th Street and Dixie Hwy in the Village of Homewood in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-05-06 | 2009-07-15 | 2009-08-30 | 2009-09-12 | 240159.29 | 0.750 | 1618001
3586 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CLARK |  | 15 | 1660105 | This project will substantially improve the roadway by reconstructing a new structure over Hawks Creek one mile west of Dennison in Clark County (Southeast Illinois) | Bridge Improvement | 2010-04-27 | 2010-06-07 | 2010-07-30 | 2010-08-30 | 349298 | 0.020 | 1660105
3587 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | 17 | 1721002 | This project will extend the pavement life by patching and resurfacing a portion Interstate 172 around Quincy, Illinois (West-Central Illinois). | Pavement Improvement | 2009-05-04 | 2009-05-12 | 2010-08-30 | 2011-02-26 | 14584587.03 | 9.410 | 1721002
3588 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | CLINTON |  | 19 | 1784105 | This project will extend the pavement life by milling, patching and resurfacing 5.5 miles of County Highway 5 near Centralia, Illinois (Southwest Illinios). | Pavement Improvement | 2009-08-12 | 2009-10-01 | 2009-12-30 | 2009-12-04 | 70000 | 11.040 | 1784105
3589 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 1790103 | This project will extend the pavement life by milling, patching and resurfacing County Highway 32 from Jefferson Road to I-57 in Marion County, Illinois (Southwest Illinios). | Pavement Improvement | 2009-08-05 | 2009-08-17 | 2009-10-30 | 2009-10-14 | 367987 | 4.530 | 1790103
3590 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WABASH |  | 15 | 1819107 | This project will extend the pavement life by resurfacing a portion of Goodson Orchard Road in Wabash County (Southeast Illinois). | Pavement Improvement | 2010-01-04 | 2010-04-14 | 2010-06-30 | 2010-05-14 | 147866 | 3.250 | 1819107
3591 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MONROE |  | 12 | 1858103 | This project will extend the pavement life by providing a surface treatment on 2.18 miles of County Highway 12 from IL156 to County Highway 6 near Valmeyer, Illinois (Southwest Illinois) | Pavement Improvement | 2009-08-25 | 2009-08-31 | 2009-09-30 | 2009-10-16 | 149789 | 4.180 | 1858103
3592 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | RANDOLPH |  | 12 | 1870108 | This project will extend the pavement life by resurfacing Wine Hill Road from Welge Road to County Highway 5 near Steelville, Illinois (Southwest Illinois). | Pavement Improvement | 2009-12-14 | 2010-05-03 | 2010-06-30 | 2010-07-14 | 405449 | 2.920 | 1870108
3593 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 1881114 | This project will extend the pavement life by resurfacing approximately 3.75 miles of Park Street Road in Franklin County.(Southern Illinois) | Pavement Improvement | 2010-02-22 | 2010-05-01 | 2010-06-30 | 2010-08-04 | 352969 | 3.720 | 1881114
3594 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 1887106 | This project will extend the pavement life by resurfacing Saraville Road from Crab Orchard road to Ewing Road in Williamson County, Illinois (Southern Illinois). | Pavement Improvement | 2009-12-17 | 2010-04-01 | 2010-06-30 | 2010-05-14 | 373706.16 | 2.800 | 1887106
3595 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 1908001 | This project will extend the pavement life by milling, patching and resurfacing 7.8 miles of IL 151 in Jackson County, Illinois (Southern Illinios). | Pavement Improvement | 2009-04-28 | 2009-05-12 | 2009-10-30 | 2009-08-21 | 2103336.12 | 7.840 | 1908001
3596 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | POPE |  | 19 | 1930119 | This project will extend the pavement life by resurfacing Bay City Road from IL Route 146 south for 4.3 miles in Pope County (Southern Illinois). | Pavement Improvement | 2010-04-12 | 2010-05-10 | 2010-06-30 | 2010-06-23 | 180207 | 4.000 | 1930119
3597 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 2051001 | This project will extend the pavement life by resurfacing 3 miles of Winneshiek Road in Stephenson County (Northwest Illinois). | Pavement Improvement | 2010-03-08 | 2010-06-22 | 2010-05-30 | 2010-07-13 | 393026 | 3.170 | 2051001
3598 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 2356003 | This project will extend the pavement life by resurfacing, improving storm sewers and traffic signals on Sheridan Road from Burnham Place to Chicago Ave in the City of Evanston, Illinois (Northeastern Illinois). | Pavement Improvement | 2010-08-13 | 2010-08-23 | 2011-06-30 | 2011-08-24 | 202807 | 0.810 | 2356003
3599 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | MARSHALL |  | 18 | 2370114 | This project will extend the pavement life by providing for 7.0 miles of removal and replacement of roadway surface on IL Route 26 near the City of Lacon which is approximately 25 miles north of the City of Peoria (West-Central Illinois) | Pavement Improvement | 2009-04-28 | 2009-05-08 | 2009-08-30 | 2009-07-10 | 1388345.16 | 7.010 | 2370114
3600 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | Multiple | 2592102 | This project will extend the pavement life by resurfacing six miles of Adams County Highway near Loraine (West-Central Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-24 | 2009-10-30 | 2009-09-17 | 527967 | 12.000 | 2592102
3601 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 2612002 | This project will extend the bridge life by adding a new deck overlay, new joints, repairing the backwall of the north abutment and making other roadway improvements on Lemont Road over Des Plaines River in Lemont, Cook County. (Northeastern Illinois) | Bridge Improvement | 2009-04-28 | 2009-05-28 | 2010-01-30 | 2010-01-30 | 4554512.63 | 0.010 | 2612002
3602 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | MOULTRIE |  | 15 | 2660101 | This project will substantially improve the roadway by reconstructing a section of County Highway 19 near Sullivan in Moultrie County (Southeast Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-16 | 2009-10-30 | 2009-10-06 | 262058 | 2.540 | 2660101
3603 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2697005 | This project will extend the bridge life by bridge deck patching and overlay on Willow Springs Road over the DesPlaines River and I&M Canal in the Village of Willow Springs in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-06-01 | 2009-06-15 | 2009-11-30 | 2010-10-23 | 4877955.21 | 0.010 | 2697005
3604 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 2706103 | This project will extend the pavement life by milling, patching and resurfacing 1.63 miles on IL Rt 43 (Waukegan Rd) from IL Rt 60 to Gage Lane in the Villages of Lake Forest and Lake Bluff (Northeastern Illinois). | Pavement Improvement | 2009-10-23 | 2010-04-13 | 2010-07-30 | 2010-07-12 | 932171.28 | 3.300 | 2706103
3605 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 2711016 | This project will extend the pavement life by resurfacing 3.24 miles on IL Rt 131 from IL Rt 120 to just south of IL Rt 137 in the City of North Chicago (Northeastern Illinois) | Pavement Improvement | 2009-05-06 | 2009-05-18 | 2009-09-30 | 2009-09-16 | 2699345.33 | 3.090 | 2711016
3606 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 2714010 | This project will extend the pavement life by resurfacing 0.55 miles of 25th Avenue from Belmont Ave to Addison Street in the Village of Franklin Park in Cook County. (Northeasern Illinois). | Pavement Improvement | 2009-06-01 | 2009-10-13 | 2009-08-30 | 2009-12-04 | 404669.38 | 0.500 | 2714010
3607 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2719001 | This project will extend the pavement life by milling, patching and resurfacing 0.74 miles of East Avenue between 47th and 55th Streets in Summit (Northeastern Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-25 | 2009-09-30 | 2009-08-29 | 339873.28 | 1.000 | 2719001
3608 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACOUPIN |  | 17 | 2729105 | This project will extend the pavement life by resurfacing and other improvements on County Highway 3 at IL Route 4 east in Macoupin County (West-Central Illinois). | Pavement Improvement | 2010-04-12 | 2010-05-17 | 2011-08-30 | 2011-10-19 | 598281 | 4.480 | 2729105
3609 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 2759003 | This project will extend the pavement life by resurfacing 1.29 miles of DesPlaines Avenue from Randolph Street to Roosevelt Road in Forrest Park in Cook Co. (Northeastern Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-04 | 2009-09-30 | 2009-07-10 | 919906.65 | 1.340 | 2759003
3610 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 2759004 | This project will extend pavement life by resurfacing 1.038 miles of Des Plaines Avenue from Roosevelt Road to Cermak Road within the Village of Forest Park in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-28 | 2010-04-15 | 2010-06-30 | 2010-05-28 | 640186.16 | 2.140 | 2759004
3611 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 2806050 | Struct repl/rehab or deck repl from Miss. River to Airport Rd in Milan. Section 81-1(B-1,HB,HB-1,HB-2,VB,VB1)R | Pavement Improvement | 2011-02-24 | 2011-03-21 | 2012-11-30 |  | 174438 | 0.010 | 2806050
3612 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WAYNE |  | 19 | 2821108 | This project will substantially improve the roadway by replacing the bridge over Martin Creek on County Highway 7 near Geff in Wayne County (Southeast Illinois) | Bridge Improvement | 2010-03-15 | 2010-04-06 | 2010-07-30 | 2010-08-22 | 344768.38 | 0.010 | 2821108
3613 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 2831002 | This project will extend the bridge life by making full depth deck repairs, structural repairs, deck overlay, and other roadway improvements to the Kedzie Avenue bridge over the Cal-Sag Channel in Robbins in Cook County. (Northeastern Illinois). | Bridge Improvement | 2009-10-23 | 2010-03-22 | 2010-08-30 | 2010-12-03 | 1315670.06 | 0.030 | 2831002
3614 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 2843006 | This project will extend the life of the pavement by resurfacing 1.07 miles of Dixie Highway just north of 183rd Street to Governor's Highway in Village of Homewood, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-06-02 | 2009-07-02 | 2009-10-30 | 2009-10-14 | 485050.98 | 1.080 | 2843006
3615 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 2907002 | This project will extend the pavement life by resurfacing 1.15 miles of State Street from 60th Street to 69th Street within the City of Chicago in Cook County. (Northeastern, Illinois). | Pavement Improvement | 2009-10-16 | 2010-04-12 | 2010-07-30 | 2011-04-23 | 933790.84 | 1.440 | 2907002
3616 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 2943016 | This project will extend the bridge life by overlaying the bridge deck and making other roadway improvements to the Burnham Avenue bridge over State Street, Indiana Harbor Beltway and CSX Railroad and | Bridge Improvement | 2009-05-04 | 2009-05-06 | 2009-10-30 | 2010-08-12 | 5764394.93 | 0.010 | 2943016
3617 | ILLINOIS | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 3033001 | This project will provide for pedestrian & bicyclist safety by constructing the DuPage River Bike & Pedestrian Trail from IL Route 59 & Riverview Park to the Prairie Creek Development in the Plainfiel | Transportation Enhancements | 2010-06-01 | 2010-06-01 | 2010-10-30 |  | 1574949 | 0.000 | 3033001
3618 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 3523006 | This project will extend the pavement life by milling, patching and resurfacing 2.6 miles on US 12 from 3rd Avenue to US 12/45 and along Rand Rd from Des Plaines River Road to Lundgren Ave in Des Plaines in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-06-02 | 2009-06-13 | 2009-10-30 | 2009-11-06 | 1927842.05 | 2.220 | 3523006
3619 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 3592005 | This project will extend the pavement life by milling, patching and resurfacing 0.94 mile of Brainard Avenue from Burnham Ave to the Indiana State line in the Village of Burnham in Cook County. (Northeastern, Illinois). | Pavement Improvement | 2009-06-01 | 2009-06-23 | 2009-09-30 | 2010-10-27 | 365144.42 | 1.080 | 3592005
3620 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 4068002 | This project will extend the pavement life by resurfacing various roads in the village of Manteno (East-Central Illinois). | Pavement Improvement | 2010-05-20 | 2010-09-27 | 2010-10-30 | 2011-09-09 | 246398 | 0.350 | 4068002
3621 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 4097005 | Transportation enhancement and road improvements necessary for Downtown Plaza improvements in Jacksonville, IL * | Transportation Enhancements | 2010-03-15 | 2010-03-16 | 2011-05-30 | 2011-11-05 | 1413770 | 0.000 | 4097005
3622 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACOUPIN |  | 17 | 5001003 | This project will substantially improve the roadway by reconstructing a section of Main Street by providing new concrete pavement and other roadway improvements in Staunton (West-Central Illinois) | Pavement Improvement | 2010-12-13 | 2011-03-14 | 2011-11-30 | 2011-12-02 | 25160 | 0.190 | 5001003
3623 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CASS |  | 18 | 5002021 | This project will extend the pavement life by resurfacing a portion of Cass County Highway 7 from western edge of Beardstown for five miles to the west (West-Central Illinois). | Pavement Improvement | 2009-09-15 | 2009-10-19 | 2009-11-30 | 2010-07-09 | 170449 | 1.460 | 5002021
3624 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | BOONE |  | 16 | 5004010 | This project will extend the pavement life by resurfacing a section of Newburg Road and other roadway improvements in the city of Belvidere (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-23 | 2009-11-30 | 2010-05-20 | 500000 | 5.600 | 5004010
3625 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 5005011 | This project will substantially improve the roadway by reconstructing a section of North DuQuoin Street by providing new concrete pavement and other roadway improvements from McFall St. to the Interst | Pavement Improvement | 2010-04-12 | 2010-05-03 | 2011-05-30 | 2010-10-27 | 229732 | 0.720 | 5005011
3626 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 5007022 | This project will extend the pavement life by providing for pavement repairs and resurfacing on Elm Street and Walnut Street in the City of Canton, approximately 25 miles southwest of Peoria (West-Central Illinois) | Pavement Improvement | 2009-09-08 | 2009-09-18 | 2009-10-30 | 2010-08-23 | 257027 | 2.250 | 5007022
3627 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FULTON |  | 17 | 5007023 | This project will provide for pedestrian safety by constructing 6 blocks of new concrete sidewalk along the north side of Ash Street in the City of Canton, approximately 25 miles southwest of Peoria (West-Central Illinois) | Safety/Traffic Management | 2009-09-22 | 2009-09-28 | 2009-12-30 | 2009-12-01 | 200586 | 1.720 | 5007023
3628 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 5008024 | This project will substantially improve mobility by constructing the missing section that connects Marion Street together by providing new concrete pavement, curb and gutter and sidewalk in the city of Carbondale, Illinois (Southern Illinois) | New Construction | 2009-09-10 | 2009-09-23 | 2010-08-30 | 2010-06-02 | 370215.46 | 0.000 | 5008024
3629 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 5008025 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Carbondale, Illinois (Southern Illinois). | Pavement Improvement | 2009-07-30 | 2009-08-03 | 2009-10-30 | 2009-10-28 | 400271.25 | 1.010 | 5008025
3630 | ILLINOIS | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACOUPIN |  | 17 | 5009005 | This project will extend the pavement life by widening and resurfacing North Broad Street from Haig St. to Shad Rd. in the Carlinville (West-Central Illinois). | Pavement Improvement | 2010-08-19 | 2011-05-11 | 2010-08-30 |  | 183150 | 1.550 | 5009005
3631 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WHITE |  | 15 | 5010010 | This project will extend the pavement life by resurfacing numerous roadway sections in the village of Carmi, Illinois (Southern Illinois). | Pavement Improvement | 2009-10-27 | 2010-05-10 | 2009-12-30 | 2010-07-19 | 160359.29 | 0.740 | 5010010
3632 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011263 | This project will extend the pavement life by resurfacing and repair broken curb and gutter on Lindenthal Ave. from Washington st. to Poplar St. in the City of Highland, IL (Southwest Illinois). | Pavement Improvement | 2009-08-03 | 2009-08-24 | 2009-09-30 | 2009-09-14 | 152387.23 | 0.440 | 5011263
3633 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011267 | Preliminary engineering for the milling and resurfacing of Madison Ave. in Edwardsville. Section 09-00099-00-RS | Other | 2009-06-18 | 2009-06-22 | 2010-04-30 | 2010-04-01 | 33987.55 | 2.000 | 5011267
3634 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011268 | This project consists of milling and resurfacing along Madison Avenue in Edwardsville, Illinois (Southwest Illinois). Other improvements include constructing curbs, sidewalks, and ramps compliant with the American with Disabilities Act. | Pavement Improvement | 2010-01-11 | 2010-06-07 | 2011-12-30 | 2010-10-07 | 254182 | 0.510 | 5011268
3635 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011269 | This project consists of patching, resurfacing, and widening of Fosterburg Road in Alton, Illinois (Southwest Illinois) Additionally, the construction of a culvert will improve roadway drainage. | Pavement Improvement | 2010-03-01 | 2010-03-26 | 2010-08-30 | 2010-12-03 | 368968.07 | 0.500 | 5011269
3636 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011270 | This project will extend the pavement life by milling, patching and resurfacing .25 miles of Ostle Dr. from Newport Dr. to Waverly Dr. in Collinsville, Illinois (Southwest Illinios). | Pavement Improvement | 2009-09-23 | 2009-09-23 | 2010-05-30 | 2010-06-29 | 165000 | 0.270 | 5011270
3637 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011271 | This project will extend the pavement life by milling, patching and resurfacing Main St. from Shamrock Ave. to Lakeside Ave. in the city of East Alton, Illinois (Southwest Illinios). | Pavement Improvement | 2009-11-23 | 2009-12-21 | 2010-06-30 | 2010-08-11 | 350662 | 0.500 | 5011271
3638 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011272 | This project will improve driving quality by resurfacing and upgrading pavement markings along Glen Carbon Road in the Village of Glen Carbon, Illinois (Southwest Illinois). | Pavement Improvement | 2010-04-27 | 2010-04-27 | 2010-06-30 | 2010-09-13 | 257920 | 1.050 | 5011272
3639 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011274 | This project will extend the pavement life by resurfacing Maryville Road from St. Clair Ave. to Terminal Ave. in Granite City, Illinois (Southwest Illinois). | Pavement Improvement | 2009-12-29 | 2010-07-05 | 2011-12-30 | 2010-09-27 | 373029.76 | 0.460 | 5011274
3640 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011275 | This project will enhance pedestrian safety by constructing a 10 wide pedestrian walkway with concrete barrier on Ohio Ave. from IL Route 203 to Old Madison Road in the City of Madision, St. Clair County (Southwest Illinois). | Safety/Traffic Management | 2010-05-03 | 2010-05-10 | 2010-06-30 | 2010-06-24 | 140238 | 0.180 | 5011275
3641 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011276 | Preliminary engineering for the resurfacing of West Main Street (Glen Carbonn Road) in the village of Glen Carbon. Section 09-00018-01-RS | Other | 2009-06-18 | 2009-06-22 | 2009-10-30 | 2010-10-31 | 26905 | 2.000 | 5011276
3642 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011277 | Project consists of concrete pavement widening, construction of concrete curb and gutter and installation of storm sewer along Frank Scott Parkway West from Belleville West Parkway to Concordia Church | Pavement Improvement | 2009-09-10 | 2009-09-21 | 2010-05-30 | 2010-04-30 | 655297 | 4.120 | 5011277
3643 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011278 | This project will extend the pavement life by milling, patching and resurfacing Broadway Ave. from Klein Ave. to State Street in city of Venice (Southwest Illinois). | Pavement Improvement | 2010-05-03 | 2010-05-12 | 2010-06-30 | 2010-07-24 | 312916.77 | 0.600 | 5011278
3644 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011279 | Construct new sidewalk, Replace broken sidewalk and upgrade sidewalk/street crossings to accommodate those with disabilities along Monroe St. from St. Louis St. to Marner Park in the city of Lebanon, Illinois. (Southwest Illinois) | Safety/Traffic Management | 2009-09-14 | 2009-10-05 | 2010-04-30 | 2010-04-15 | 282000 | 1.470 | 5011279
3645 | ILLINOIS | Completed | C250,C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011280 | This project will extend the pavement life by milling, patching and resurfacing of 9th street from Airline Drive to north of Old Edwardsville Road in the city of Wood River, IL (Southwest Illinois). | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-06-30 | 2010-05-25 | 244542 | 1.430 | 5011280
3646 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011284 | Roadway reconstruction and add sidewalks on FAU 9283 (Hill Ave) from Kingshighway to Vassar Ave in Village of Washington Park. | Pavement Improvement | 2010-05-25 | 2010-08-02 | 2011-12-30 | 2011-11-25 | 303966 | 0.130 | 5011284
3647 | ILLINOIS | Completed | C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | MONROE | ST. LOUIS (MO)-IL | 12 | 5011285 | This project consists of patching and resurfacing 0.35 miles of Palmer Road in the City of Columbia, Illinois (Southwest Illinois). Additionally, wider shoulders will improve safety. | Pavement Improvement | 2010-03-02 | 2010-05-24 | 2010-06-30 | 2010-08-02 | 233597 | 0.460 | 5011285
3648 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MONROE | ST. LOUIS (MO)-IL | 12 | 5011286 | This roadway widening project includes 0.27 miles of resurfacing and the addition of a new right turn lane from Maeystown Road onto IL 156 in Waterloo, Illinois (Southwest Illinois) Additionally, new sidewalks and curb and gutter will be installed. | Pavement Improvement | 2010-03-02 | 2010-04-26 | 2010-06-30 | 2010-07-28 | 220000 | 0.260 | 5011286
3649 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011287 | This project will extend the pavement life by milling, patching and resurfacing 1.36 miles of Doris Ave. from Range Lane to Jerome Lane in the city of Cahokia, IL (Southwest Illinois). | Pavement Improvement | 2010-03-18 | 2010-03-18 | 2010-07-30 | 2010-07-14 | 327200 | 1.400 | 5011287
3650 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011290 | This project will extend the pavement life by milling, patching and resurfacing Pontoon Rd from Breckenridge Ln. to IL111 in Pontoon Beach, Illinois(Southwest Illinios). | Pavement Improvement | 2009-08-25 | 2009-08-25 | 2010-05-30 | 2010-05-10 | 243795 | 1.550 | 5011290
3651 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011291 | This project will improve safety by providing pedestrians a signal to stop traffic and safely cross Monroe St. in the city of Lebenon. (Southwest Illinois) | Safety/Traffic Management | 2010-04-23 | 2010-04-23 | 2010-05-30 | 2010-10-22 | 44832 | 0.010 | 5011291
3652 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011292 | This project will extend the pavement life by milling, patching and resurfacing .44 miles of Frontage Road from Harvestyme Lane to clara Dr. in Troy, Illinois (Northwest Illinios). | Pavement Improvement | 2009-10-29 | 2010-01-26 | 2010-05-30 | 2010-06-08 | 86566 | 0.540 | 5011292
3653 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011293 | This project will extend the pavement life by resurfacing 6th street from IL 143 to Rohm Place in the city of Wood River, Illinois(Southwest Illinois). | Pavement Improvement | 2009-12-22 | 2010-03-23 | 2010-05-30 | 2010-06-04 | 225386 | 0.590 | 5011293
3654 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011294 | This project will extend the pavement life by resurfacing, replace broken curb and gutter and sidewalks on Church Road from IL Route 157 to 50th St. in Centreville, IL (Southwest Illinois) . | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-08-30 |  | 446797 | 1.240 | 5011294
3655 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011295 | This project will extend the pavement life by milling, patching and resurfacing of 17th street from Russell Ave. to East Broadway Ave. in the city of East St. Louis (Southwest Illinois). | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-07-30 | 2010-08-17 | 441427 | 0.780 | 5011295
3656 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011296 | This project consists of milling and resurfacing on a section of Union Hill Road in the City of Fairview Heights, Illinois (Southwest Illinois). Other improvements include constructing new sidewalks and curb and gutter. | Pavement Improvement | 2010-03-01 | 2010-03-08 | 2010-07-30 | 2010-08-10 | 307200 | 0.440 | 5011296
3657 | ILLINOIS | Completed | C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 5011297 | This project will substantially improve the roadway by reconstructing a section of Concordia Church Road from IL route 158 to Frank Scott Parkway by providing new full depth bituminous pavement and ot | Pavement Improvement | 2010-06-30 | 2010-07-12 | 2010-11-30 | 2011-09-08 | 1264080 | 0.930 | 5011297
3658 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 19 | 5011299 | This project enhances the aesthetics of the roadway by planting trees along Governors Parkway from Troy road to IL route 143 in Madison County (Southwest Illinois). | Transportation Enhancements | 2010-08-05 | 2010-11-08 | 2010-05-30 | 2010-11-12 | 32320 | 2.670 | 5011299
3659 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011300 | This project enhances the aesthetics of th eroadway by planting trees along IL Route 3 from Rock Road to 20th Street in Granite City, Madison County (Southwest Illinois). | Transportation Enhancements | 2010-05-18 | 2010-11-01 | 2010-05-30 | 2010-11-03 | 19640 | 0.660 | 5011300
3660 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MADISON | ST. LOUIS (MO)-IL | 12 | 5011324 | Resurfacing of State St., curb and gutter repair, sidewalk repair from 14th St. to Broadway Ave. | Pavement Improvement | 2010-08-05 | 2010-11-01 | 2010-12-30 | 2011-08-30 | 532910 | 1.050 | 5011324
3661 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5012017 | This project will extend the pavement life by resurfacing Brookside Ave. from 15th street to 17th street in Wamac, Illinois (Southwest Illinois). | Pavement Improvement | 2009-11-18 | 2010-04-19 | 2010-05-30 | 2010-04-30 | 41880 | 0.130 | 5012017
3662 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5012018 | Replace broken sidewalk and upgrade sidewalk/street crossings to accommodate those with disabilities at various locations along US Route 51 between Mcbriarty st. and Pearct St in Central City, Illinois (Southwest Illinois) | Safety/Traffic Management | 2010-03-10 | 2010-04-04 | 2010-06-30 | 2010-04-27 | 40132.42 | 1.540 | 5012018
3663 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5012019 | This project will extend the pavement life by milling, patching and resurfacing various streets in the City of Centralia, Illinois (Southwest Illinois). | Pavement Improvement | 2010-05-07 | 2010-05-03 | 2010-07-30 | 2010-07-30 | 427484 | 1.110 | 5012019
3664 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 5013016 | This project will extend the pavement life by resurfacing numerous roadway sections in the City of Charleston (Southeast Illinois). | Pavement Improvement | 2009-09-10 | 2009-10-21 | 2009-11-30 | 2009-11-17 | 340000 | 0.000 | 5013016
3665 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 5013017 | This project will extend the pavement life by resurfacing numerous roadway sections in Charleston, Coles County (Southeast Illinois). | Pavement Improvement | 2010-06-29 | 2010-08-05 | 2010-06-30 | 2010-10-01 | 319711 | 1.350 | 5013017
3666 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | RANDOLPH |  | 12 | 5014009 | This project will extend the pavement life by resurfacing numerous roadway sections in the City of Chester, Illinois (Southwest Illinois). | Pavement Improvement | 2010-01-13 | 2010-04-28 | 2010-05-30 | 2010-06-09 | 253416 | 0.730 | 5014009
3667 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE WITT |  | 15 | 5015004 | This project will extend the pavement life by resurfacing 5 blocks of Washington Street in Clinton, approximately 25 miles south of Bloomington (East-Central Illinois) | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2010-08-30 | 2010-08-18 | 188678.99 | 0.310 | 5015004
3668 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 5016037 | This project will extend the pavement life by resurfacing a section of Denmark Road in Danville, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-10 | 2010-03-30 | 2010-07-30 | 2010-05-18 | 700000 | 2.880 | 5016037
3669 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 5016038 | This project will substantially improve Voorhees Street by constructing a new bridge over the CSX railroad and providing 0.8 mile of resurfacing in Danville, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-05 | 2010-10-30 | 2010-11-18 | 700000 | 1.000 | 5016038
3670 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 5016039 | This project will extend the pavement life by resurfacing 0.8 mile of Main Street in Westville, approximately 35 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2010-01-08 | 2010-04-19 | 2010-06-30 | 2010-06-18 | 217531 | 0.990 | 5016039
3671 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5017040 | This project will extend the pavement life by resurfacing a section of Fairview Drive in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 2009-08-12 | 2009-09-03 | 2009-10-30 | 2009-10-03 | 565839.09 | 2.920 | 5017040
3672 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5017041 | This project will substantially improve the roadway by reconstructing the intersection of Plank Road and Lindgren Road in the city of Sycamore (East-Central Illinois). | Pavement Improvement | 2010-03-19 | 2010-04-19 | 2011-12-30 | 2011-09-30 | 479848.85 | 0.200 | 5017041
3673 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5017042 | This project will substantially improve the roadway by constructing a new intersection at Dresser Road and Normal Road in the city of Dekalb (East-Central Illinois). | Pavement Improvement | 2010-03-19 | 2010-04-19 | 2010-08-30 | 2010-08-27 | 438589 | 0.010 | 5017042
3674 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LEE |  | 14 | 5018015 | This project will substantially improve the roadway by reconstructing a section of Hennepin Avenue by providing new concrete intersections, pavement and other roadway improvements in Dixon (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-04-28 | 2010-09-30 | 2010-10-01 | 482180 | 0.200 | 5018015
3675 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PERRY |  | 12 | 5019007 | This project will extend the pavement life by milling, patching and resurfacing 0.55 miles of Cole Street from Division St. to Line St. in the city of DuQuoin, Illinois (Southern Illinois). | Pavement Improvement | 2009-10-22 | 2009-11-16 | 2010-12-30 | 2009-12-17 | 196971.02 | 0.520 | 5019007
3676 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | EFFINGHAM |  | 19 | 5021025 | This project will substantially improve the roadway by constructing a section of Veterans Drive by providing new concrete pavement in Effingham (Southeast Illinois). | Pavement Improvement | 2009-12-17 | 2010-03-08 | 2010-09-30 | 2010-10-16 | 374589 | 0.100 | 5021025
3677 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WAYNE |  | 19 | 5022012 | This project will substantially improve the roadway by constructing a new box culvert over a branch of Pond Creek on East 4th Street in Fairfield, Wayne County (Southeast Illinois). | Bridge Replacement | 2010-05-19 | 2010-06-03 | 2010-08-30 | 2010-09-01 | 163973 | 0.010 | 5022012
3678 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CLAY |  | 19 | 5023010 | This project will substantially improve the roadway by reconstructing a section of Worthey Steet by providing new concrete pavement and other roadway improvements in Flora, Clay County (Southeast Illinois). | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-09-30 | 2010-08-20 | 153840 | 0.250 | 5023010
3679 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 5024026 | This project will extend the pavement life and complete other roadway improvements by resurfacing and sidewalk improvements to numerous sections of streets in the city of Freeport (Northwest Illinois). | Pavement Improvement | 2009-10-07 | 2009-10-13 | 2010-06-30 | 2010-07-07 | 745728.02 | 3.200 | 5024026
3680 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | STEPHENSON |  | 16 | 5024027 | This project will extend the pavement life by resurfacing Lincoln Boulevard from Whistler Avenue to Saxby Avenue in the city of Freeport (Northwest Illinois). | Pavement Improvement | 2010-09-16 | 2010-09-22 | 2010-10-30 | 2010-10-13 | 39065 | 0.430 | 5024027
3681 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 17 | 5025043 | This project will substantially improve the roadway by reconstructing and providing additional roadway improvements for a 1/4 mile section of Carl Sandburg Drive in the City of Galesburg (West-Central Illinois) | Pavement Improvement | 2009-07-27 | 2009-07-30 | 2009-10-30 | 2009-09-01 | 249851.17 | 0.720 | 5025043
3682 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 17 | 5025044 | This project will improve a section of Knox Street by providing a new surface, sidewalks, and drainage improvements in the City of Galesburg (West-Central Illinois) | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2009-11-30 | 2009-10-16 | 471930.71 | 1.340 | 5025044
3683 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 17 | 5025046 | This project will improve a 1/2 mile section of South Seminary Street by providing a new surface, sidewalks, and drainage improvements in the City of Galesburg (West-Central Illinois) | Pavement Improvement | 2009-10-20 | 2009-10-30 | 2010-05-30 | 2010-04-30 | 279099 | 1.020 | 5025046
3684 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KNOX |  | 17 | 5025047 | This project will substantially improve the roadway by reconstructing 0.25 miles of State Street in the City of Galesburg, Knox County (West-Central Illinois). | Pavement Improvement | 2010-02-24 | 2010-02-19 | 2010-06-30 | 2010-05-23 | 44000 | 0.010 | 5025047
3685 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 14 | 5026011 | This project will extend the pavement life by providing a surface treatment on numerous roadway sections in the city of Geneseo (Northwest Illinois). | Pavement Improvement | 2009-08-27 | 2010-05-03 | 2010-05-30 | 2010-05-27 | 186759.61 | 0.000 | 5026011
3686 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SALINE |  | 19 | 5027012 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Harrisburg. (Southern Illinois) | Pavement Improvement | 2010-03-01 | 2010-04-27 | 2010-06-30 | 2010-06-07 | 298243 | 0.450 | 5027012
3687 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 5029010 | This project will extend the pavement life by milling, patching and resurfacing East Herrin Street from IL route 148 to 5th street in the city of Herrin (Southern Illinois). | Pavement Improvement | 2010-08-15 | 2010-09-01 | 2010-06-30 | 2010-10-22 | 353746.86 | 0.620 | 5029010
3688 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 5029011 | This project consists of improving safety by upgrading traffic signs to current standard throughout the village of Energy, Illinois (Southern Illinois). | Safety/Traffic Management | 2009-11-13 | 2009-11-13 | 2010-10-30 | 2010-03-01 | 20614 | 0.000 | 5029011
3689 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | VERMILION |  | 15 | 5031008 | This project will extend the pavement life by resurfacing 0.8 mile of North Market Street in Hoopeston, approximately 50 miles northeast of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-28 | 2010-04-05 | 2010-09-30 | 2010-08-03 | 180428 | 0.870 | 5031008
3690 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 5032028 | This project will extend the pavement life by resurfacing a portion of the Village of South Jacksonville's East Vandalia Road (West-Central Illinois). | Pavement Improvement | 2009-09-10 | 2009-10-27 | 2010-07-30 | 2010-04-22 | 105111 | 0.880 | 5032028
3691 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MORGAN |  | 18 | 5032029 | This project will extend the pavement life by resurfacing and other improvements on Lafayette Street in Jacksonville, Morgan County (West-Central Illinois). | Pavement Improvement | 2010-04-12 | 2010-05-10 | 2010-07-30 | 2010-07-26 | 603111 | 0.900 | 5032029
3692 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JERSEY |  | 19 | 5033009 | – This project will provide for pedestrian accommodations by constructing a sidewalk along Fairgrounds Ave. from Cemetery Road to June Street and along June Street from Fairgrounds Ave. to East Carpenter Street in Jerseyville, IL (Southwest Illinois). | Safety/Traffic Management | 2010-04-29 | 2010-06-24 | 2010-07-30 | 2011-04-08 | 194560 | 1.040 | 5033009
3693 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5036025 | This project will extend the pavement life by resurfacing a section of Richard Moyle Sr. Highway in the city of Oglesby (East-Central Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2009-09-30 | 2009-10-12 | 110314 | 2.060 | 5036025
3694 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5036026 | This project will extend the pavement life and improve pedestrian safety by resurfacing and reconstructing sidewalks for numerous roadway sections in the city of Peru (East-Central Illinois). | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-12-30 | 2010-06-29 | 256514.01 | 1.660 | 5036026
3695 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5036027 | This project will extend the pavement life by resurfacing various streets in the city of LaSalle (East-Central Illinois). | Pavement Improvement | 2010-02-24 | 2010-04-19 | 2010-06-30 | 2010-05-12 | 292651 | 0.000 | 5036027
3696 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LOGAN |  | 18 | 5038013 | This project will extend the pavement life by resurfacing College Street from 8th to 11th and State St. from Kickapoo St to 4th Street in Lincoln (West-Central Illinois). | Pavement Improvement | 2010-06-01 | 2010-06-24 | 2010-07-30 | 2011-04-29 | 390507 | 1.530 | 5038013
3697 | ILLINOIS | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LOGAN |  | 18 | 5038014 | Land acquisition for an improvement to 5th street in Lincoln, Section 10-00081-01-LA | Other | 2011-11-01 | 2010-11-01 | 2010-11-30 |  | 7561.82 | 1.400 | 5038014
3698 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MONTGOMERY |  | 19 | 5039010 | This project will extend the pavement life by resurfacing State St from IL Route 16 to Ferdon St in Litchfield (West-Central Illinois). | Pavement Improvement | 2010-11-04 | 2011-05-04 | 2010-07-30 | 2011-08-10 | 25160 | 0.290 | 5039010
3699 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 5040009 | This project will substantially improve the roadway by reconstructing a section of Ward Street with new concrete pavement and other roadway improvements in the City of Macomb which is approximately 60 | Pavement Improvement | 2009-08-03 | 2009-08-19 | 2010-08-30 | 2010-10-19 | 376800 | 1.020 | 5040009
3700 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCDONOUGH |  | 17 | 5040010 | This project will substantially improve the roadway by reconstructing a section of Ward Street with new concrete pavement and other roadway improvements, including sidewalk, in the City of Macomb appr | Pavement Improvement | 2009-10-23 | 2009-11-02 | 2010-08-30 | 2010-09-03 | 229517 | 0.260 | 5040010
3701 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 5041022 | LAND ACQUISITION FOR THE WIDENING OF MORGAN AVE. FROM CORBON ST. TO NORTH RUSSELL ST IN MARION, SECTION 08-00105-00-FP | Other | 2009-08-26 | 2009-08-26 | 2009-10-30 | 2011-03-01 | 90000 | 0.000 | 5041022
3702 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WILLIAMSON |  | 12 | 5041023 | This project will extend the pavement life by resurfacing numerous roadway sections in the City of Marion (Southern Illinois). | Pavement Improvement | 2010-08-05 | 2010-08-12 | 2010-06-30 | 2010-09-13 | 428114 | 0.000 | 5041023
3703 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | COLES |  | 15 | 5042018 | This project will extend the pavement life by resurfacing numerous roadway sections and sidewalks in Mattoon, Coles County (Southeast Illinois). | Pavement Improvement | 2010-04-21 | 2010-05-26 | 2010-07-30 | 2010-07-14 | 553262 | 0.000 | 5042018
3704 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5044011 | This project will extend the pavement life by widening and resurfacing a section of West Main Street in the city of Mendota (East-Central Illinois). | Pavement Improvement | 2010-02-24 | 2010-03-24 | 2010-09-30 | 2010-05-20 | 219962 | 0.620 | 5044011
3705 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MASSAC |  | 19 | 5045008 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Metropolis, Illinois (Southern Illinois). | Pavement Improvement | 2009-09-09 | 2009-10-05 | 2009-10-30 | 2009-11-04 | 196066 | 0.000 | 5045008
3706 | ILLINOIS | Underway | C220 | Highway Infrastructure Investment Grant | ILLINOIS | MASSAC |  | 19 | 5045009 | This project will enhance pedestrian and bicycle accommodations by constructing a bike trail from Fort Massac State Park to Strawberry Road in Massac County (Southern Illinois). | Transportation Enhancements | 2010-04-12 | 2010-05-10 | 2012-05-30 |  | 2092088 | 0.340 | 5045009
3707 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WARREN |  | 17 | 5046007 | This project will extend the pavement life by resurfacing 0.60 mile of North Main Street in Monmouth, west of Galesburg (West-Central Illinois) | Pavement Improvement | 2009-09-09 | 2009-09-21 | 2009-12-30 | 2009-11-06 | 297669 | 1.100 | 5046007
3708 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY |  | 11 | 5047008 | This project will extend the pavement life and complete other roadway improvements by resurfacing numerous roadway sections in the city of Morris (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-28 | 2009-10-30 | 2009-10-08 | 322320.96 | 0.000 | 5047008
3709 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WABASH |  | 15 | 5048020 | This project will extend the pavement life by resurfacing a portion of 3rd Street in Mt. Carmel (Southeast Illinois). | Pavement Improvement | 2009-10-16 | 2009-10-26 | 2009-12-30 | 2009-11-12 | 241438 | 1.520 | 5048020
3710 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JEFFERSON |  | 19 | 5049023 | This project will substantially improve the roadway by reconstructing a section of North Davidson Ave from Illinois Route 15 north approx. 1 mile by providing new concrete pavement and other roadway i | Pavement Improvement | 2010-04-22 | 2010-05-22 | 2010-07-30 | 2011-06-22 | 492101 | 0.300 | 5049023
3711 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JACKSON |  | 12 | 5050013 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Murphysboro, Illinois (Southern Illinois). | Pavement Improvement | 2009-12-10 | 2010-03-04 | 2010-06-30 | 2010-06-04 | 262974 | 0.700 | 5050013
3712 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | RICHLAND |  | 19 | 5051011 | This project will substantially improve the roadway by reconstructing a section of Butler Street by providing new concrete pavement and other roadway improvements in Olney, Richland County (Southeast Illinois). | Pavement Improvement | 2010-04-29 | 2010-06-15 | 2010-09-30 | 2010-10-21 | 261069 | 0.250 | 5051011
3713 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5052026 | This project will extend the pavement life by resurfacing various streets in the city of Ottawa (East-Central Illinois). | Pavement Improvement | 2010-02-19 | 2010-04-21 | 2010-07-30 | 2010-06-04 | 559312.85 | 0.000 | 5052026
3714 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHRISTIAN |  | 17 | 5053006 | This project will substantially improve the roadway by reconstructing a section of Chestnett Street by providing new concrete pavement and other roadway improvements in Pana (West-Central Illinois). | Pavement Improvement | 2010-06-10 | 2010-07-13 | 2010-07-30 | 2011-05-19 | 169811 | 0.170 | 5053006
3715 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY |  | 17 | 5053012 | This project will extend the pavement life and improve pedestrian safety by resurfacing numerous roadway sections and construction of sidewalks in the city of Kewanee (Northwest Illinois). | Pavement Improvement | 2009-10-16 | 2010-05-03 | 2010-05-30 | 2010-06-24 | 389394.12 | 1.140 | 5053012
3716 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | EDGAR |  | 15 | 5054008 | This project will extend the pavement life by resurfacing 1 block of Crawford Street in Paris, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2009-10-14 | 2009-10-14 | 2010-05-30 | 2010-07-06 | 51833 | 0.140 | 5054008
3717 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | EDGAR |  | 15 | 5054009 | This project will extend the pavement life by resurfacing 4 blocks of Wood Street and Court Street in Parkis, approximately 30 miles east of Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-09 | 2010-04-01 | 2010-06-30 | 2011-03-04 | 195375 | 0.440 | 5054009
3718 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL |  | 14 | 5055001 | This project will extend pavement life by resurfacing a section of Center Street in the city of Plano (East-Central Illinois). | Pavement Improvement | 2009-10-16 | 2010-04-15 | 2010-05-30 | 2010-05-24 | 323440 | 1.210 | 5055001
3719 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 5056016 | This project will extend the pavement life and improve pedestrian safety by resurfacing Aurora Street and construction of sidewalks in the city of Kewanee (East-Central Illinois).” | Pavement Improvement | 2010-09-07 | 2010-09-13 | 2010-11-30 | 2010-11-15 | 125509 | 0.340 | 5056016
3720 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LIVINGSTON |  | 15 | 5056017 | This project will extend pavement life by resurfacing a section of Deerfield Road in the city of Pontiac (East-Central Illinois). | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-12-30 | 2009-12-01 | 221422 | 2.020 | 5056017
3721 | ILLINOIS | Completed | C250 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 5057006 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Princeton (East-Central Illinois). | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2010-07-30 | 2010-04-30 | 194608 | 0.000 | 5057006
3722 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | 17 | 5058030 | This project will extend the pavement life by resurfacing numerous roadway sections in Quicy in Adams County (West-Central Illinois). | Pavement Improvement | 2010-03-02 | 2010-07-06 | 2010-08-30 | 2010-11-08 | 990825.42 | 0.000 | 5058030
3723 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | ADAMS |  | 17 | 5058031 | This project will extend the pavement life by resurfacing Bonansinga Dr between Cedar St & Kochs Ln in Quincy (West-Central Illinois). | Pavement Improvement | 2010-08-19 | 2010-09-08 | 2010-07-30 | 2010-11-30 | 220982 | 1.320 | 5058031
3724 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5059013 | This project will extend the pavement life by resurfacing approximately 1.5 miles of Flessner Avenue and Pacesetter Drive in Rantoul, north of Champaign (East-Central Illinois) | Pavement Improvement | 2009-09-15 | 2009-09-15 | 2010-06-30 | 2010-05-17 | 350000 | 1.470 | 5059013
3725 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CRAWFORD |  | 15 | 5060008 | This project will substantially improve the roadway by constructing a section of North Allen Street by providing new concrete pavement and other roadway improvements in Robinson (Southeast Illinois). | Pavement Improvement | 2009-12-17 | 2010-04-08 | 2010-08-30 | 2010-06-30 | 206350 | 0.080 | 5060008
3726 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | OGLE |  | 16 | 5061013 | This project will extend the pavement life and improve pedestrian safety by resurfacing and improving sidewalk on sections of Lincoln Highway and 4th Avenue in the city of Rochelle (Northwest Illinois). | Pavement Improvement | 2010-06-17 | 2010-07-26 | 2010-06-30 | 2010-10-01 | 320082 | 0.420 | 5061013
3727 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 17 | 5062027 | This project will extend the pavement life and improve pedestrian safety by resurfacing the roadway and replacing the sidewalk for a section of 12th Avenue in the city of Rock Falls (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-06-03 | 2010-08-30 | 2010-08-27 | 291000 | 0.930 | 5062027
3728 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WHITESIDE |  | 17 | 5062028 | This project will extend the pavement life by resurfacing sections of Avenue G and 16th Avenue in the city of Sterling (Northwest Illinois). | Pavement Improvement | 2010-09-02 | 2010-09-07 | 2011-05-30 | 2010-11-08 | 475691 | 1.180 | 5062028
3729 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5064014 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Salem, Illinois (Southwest Illinois). | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2009-09-30 | 2009-12-04 | 219353 | 0.000 | 5064014
3730 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MARION |  | 19 | 5064015 | This project will extend the pavement life by resurfacing South Marion Street from East Lake street to the County Fairgrounds in the city of Salem (Southwest Illinois) | Pavement Improvement | 2010-05-04 | 2010-07-12 | 2010-05-30 | 2010-07-22 | 19877 | 0.240 | 5064015
3731 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | BUREAU |  | 11 | 5065006 | This project will extend the pavement life and improve pedestrian safety by resurfacing and reconstructing sidewalks for a section of St. Paul Street in the city of Spring Valley (East-Central Illinois). | Pavement Improvement | 2009-07-24 | 2009-08-01 | 2009-10-30 | 2009-11-01 | 163278 | 0.380 | 5065006
3732 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 5066014 | This project will extend the pavement life by resurfacing a section of Oakley Avenue in the city of Streator (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-10-05 | 2010-06-30 | 2010-05-25 | 437897 | 1.520 | 5066014
3733 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHRISTIAN |  | 19 | 5067017 | This project will extend the pavement life by resurfacing and other improvements on Spresser Street in Taylorville, Christian County (West-Central Illinois). | Pavement Improvement | 2010-04-19 | 2010-06-07 | 2010-07-30 | 2010-12-03 | 345641 | 2.280 | 5067017
3734 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FAYETTE |  | 19 | 5068024 | This project will substantially improve the roadway by reconstructing a section of Coles Street by providing new concrete pavement and other roadway improvements in Vandalia (Southeast Illinois). | Pavement Improvement | 2009-12-14 | 2010-04-22 | 2010-07-30 | 2010-07-16 | 210978 | 0.260 | 5068024
3735 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | IROQUOIS |  | 15 | 5069005 | This project will extend the pavement life and improve pedestrian safety by resurfacing the roadway and replacing the sidewalks on sections of 5th Street, 8th Street, and Elm Street in the city of Watseka (East-Central Illinois). | Pavement Improvement | 2010-02-25 | 2010-02-25 | 2010-08-30 | 2010-05-28 | 171000 | 1.140 | 5069005
3736 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | FRANKLIN |  | 12 | 5071014 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of West Frankfort. (Southern Illinois). | Pavement Improvement | 2010-02-22 | 2010-03-22 | 2010-06-30 | 2010-05-05 | 247911 | 1.190 | 5071014
3737 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074081 | This project will substantially improve the roadway by reconstructing a section of 30th Street in the city of Rock Island (Northwest Illinois). | Pavement Improvement | 2010-03-03 | 2010-04-22 | 2010-09-30 | 2010-09-25 | 877027 | 0.950 | 5074081
3738 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND |  | 17 | 5074082 | This project will extend the pavement life by resurfacing a section of First Street in the city of Coal Valley (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-28 | 2009-10-30 | 2009-11-06 | 174439 | 2.200 | 5074082
3739 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074083 | This project will substantially improve the roadway by reconstructing a section of 5th Avenue and other roadway improvements in the city of Moline (Northwest Illinois). | Pavement Improvement | 2010-03-01 | 2010-04-19 | 2011-05-30 | 2010-11-23 | 967284 | 0.150 | 5074083
3740 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074084 | This project will extend the pavement life by resurfacing a section of 12th Avenue in the city of East Moline (Northwest Illinois). | Pavement Improvement | 2010-03-03 | 2010-04-05 | 2010-07-30 | 2010-06-30 | 473631 | 1.500 | 5074084
3741 | ILLINOIS | Completed | C200,C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074085 | This project will extend the pavement life by resurfacing a section of 221st Street in Rock Island County (Northwest Illinois). | Pavement Improvement | 2010-03-03 | 2010-06-24 | 2010-07-30 | 2010-08-06 | 555482 | 3.630 | 5074085
3742 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | ROCK ISLAND | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5074086 | This project will extend the pavement life by resurfacing a section of 10th Street in the city of Silvis (Northwest Illinois). | Pavement Improvement | 2010-03-03 | 2010-04-22 | 2010-06-30 | 2010-07-15 | 351635 | 1.560 | 5074086
3743 | ILLINOIS | Completed | C200,C240 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5076007 | This project will extend the pavement life by resurfacing a section of Railroad Street in the city of Sandwich (East-Central Illinois). | Pavement Improvement | 2010-03-10 | 2010-08-09 | 2010-05-30 | 2010-08-19 | 164207.9 | 0.510 | 5076007
3744 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | BOND |  | 19 | 5078007 | This project will extend the pavement life by resurfacing South Fourth Street from US 40 to Franklin street in the city of Greenville (Southwest Illinois) | Pavement Improvement | 2010-06-17 | 2010-07-19 | 2010-10-30 | 2011-06-07 | 254311 | 1.010 | 5078007
3745 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | UNION |  | 12 | 5080004 | This project will extend the pavement life by milling, patching and resurfacing 0.7 miles ofHeacock Street in the village of Jonesboro, Illinois (Southern Illinios). | Pavement Improvement | 2009-10-22 | 2009-11-02 | 2010-12-30 | 2009-12-30 | 207003.22 | 0.730 | 5080004
3746 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 5082008 | LAND ACQUISITION FOR THE RECONSTRUCTION OF GORDON DRIVE FROM RAMBLEWOOD TO MAU DRIVE IN CHATHAM, SECTION 06-00028-00-WR | Other | 2009-09-29 | 2010-10-01 | 2009-11-30 | 2011-02-01 | 17981 | 0.530 | 5082008
3747 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 5082009 | This project will extend culvert and roadway life by extending the length of the culvert and adding an additional culvert along with drainage improvements on Gordon Drive over Grindstone Creek in Chatham, Sangamon County(West-Central Illinois). | Bridge Improvement | 2010-03-23 | 2010-03-23 | 2010-08-30 | 2011-01-23 | 482019 | 0.010 | 5082009
3748 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PERRY |  | 12 | 5084003 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Pickneyville. (Southern Illinois) | Pavement Improvement | 2010-02-22 | 2010-05-01 | 2010-06-30 | 2010-07-01 | 165274 | 0.520 | 5084003
3749 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | PIATT |  | 15 | 5090001 | This project will extend the life of the roadway by replaceing a culvert on Buchanan Street in Monticello, Piatt County (East-Central Illinois). | Bridge Improvement | 2010-03-01 | 2010-04-19 | 2010-06-30 | 2010-05-14 | 113133.15 | 0.100 | 5090001
3750 | ILLINOIS | Underway | C200 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 5092004 | This project wil substantially improve the roadway by reconstructing a section of Burns Road West in the city of Bourbonnais. | New Construction | 2009-08-04 | 2009-08-04 | 2010-07-30 |  | 1875750 | 2.020 | 5092004
3751 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093139 | This project consists of providing engineering design for a future highway improvement on Northmoor Road in the city of Peoria (West-Central Illinois). | Other | 2009-07-16 | 2009-07-16 | 2009-09-30 |  | 173272 | 0.000 | 5093139
3752 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093140 | This project will extend the pavement life by removing existing pavement and resurfacing 0.91 mile of Parkway Drive in Pekin, just south of Peoria (West-Central Illinois) | Pavement Improvement | 2009-10-28 | 2010-04-26 | 2009-12-30 | 2010-05-18 | 432276 | 2.300 | 5093140
3753 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093141 | This project will extend the pavement life by providing for pavement removal and resurfacing on North Main Street in Morton, just east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-10-28 | 2010-06-01 | 2010-07-30 | 2010-06-24 | 212838 | 0.620 | 5093141
3754 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093142 | This project will extend the pavement life by provide for pavement removal and resurfacing of a 0.51 mile section of Heading Avenue in West Peoria (West-Central Illinois) | Pavement Improvement | 2009-09-25 | 2009-09-29 | 2009-09-30 | 2009-10-10 | 60800 | 1.040 | 5093142
3755 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093143 | This project will extend the pavement life by resurfacing a 0.5 mile section of Garfield Avenue in Bartonville, just south of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-26 | 2010-06-30 | 2010-05-06 | 80564 | 0.490 | 5093143
3756 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093144 | This project will extend the pavement life by providing for 0.39 mile of pavement removal and resurfacing on North Prospect Road in Peoria (West-Central Illinois) | Pavement Improvement | 2009-09-25 | 2009-10-05 | 2009-10-30 | 2009-11-18 | 84714 | 0.940 | 5093144
3757 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093145 | This project will extend the pavement life by providing for 0.38 mile of pavement removal and resurfacing on Fischer Avenue just south of Peoria (West-Central Illinois) | Pavement Improvement | 2009-09-14 | 2009-09-23 | 2009-09-30 | 2009-09-30 | 69558 | 0.800 | 5093145
3758 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093146 | This project will extend the pavement life by providing for 0.64 mile of pavement removal and resurfacing on Highview Road in East Peoria (West-Central Illinois) | Pavement Improvement | 2009-08-04 | 2009-09-01 | 2009-09-30 | 2010-12-10 | 294083 | 1.160 | 5093146
3759 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093147 | This project will extend the pavement life by providing for 3 blocks of pavement repairs and resurfacing in South Pekin, just south of Peoria (West-Central Illinois) | Pavement Improvement | 2009-10-28 | 2010-04-19 | 2009-12-30 | 2010-05-15 | 103724.21 | 2.980 | 5093147
3760 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | TAZEWELL | PEORIA | 18 | 5093148 | This project will extend the pavement life by resurfacing 1 mile of Hillcrest Drive and Wilmor Road in the City of Washington, east of Peoria (West-Central Illinois) | Pavement Improvement | 2009-12-14 | 2010-04-21 | 2010-05-30 | 2010-04-26 | 168113 | 1.130 | 5093148
3761 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093149 | This project will extend the pavement life by resurfacing 0.5 miles of Truitt Avenue in Peoria County (West-Central Illinois). | Pavement Improvement | 2010-02-19 | 2010-04-07 | 2010-06-30 | 2010-04-26 | 181366 | 0.770 | 5093149
3762 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | PEORIA | PEORIA | 18 | 5093153 | This project will substantially improve the roadway by reconstructing a section of Northmoor Road by providing new pavement and other roadway improvements in Peoria (West-Central Illinois). | Pavement Improvement | 2010-03-08 | 2010-04-01 | 2010-11-30 | 2011-12-31 | 2391543 | 0.320 | 5093153
3763 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | DE KALB |  | 14 | 5094001 | This project will extend the pavement life by resurfacing numerous streets in the city of Genoa (East-Central Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-28 | 2009-11-30 | 2009-10-28 | 162552 | 1.780 | 5094001
3764 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099087 | This project will extend the pavement life by resurfacing a section of West Riverside Boulevard in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-12-15 | 2010-05-03 | 2010-08-30 | 2010-08-20 | 385511.32 | 0.440 | 5099087
3765 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099088 | This project will extend the pavement life by resurfacing numerous roadway sections in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2009-10-29 | 2010-05-03 | 2010-06-30 | 2010-09-17 | 825125.28 | 2.560 | 5099088
3766 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099090 | This project will extend the pavement life by resurfacing a section of Mill Road in the city of Cherry Valley (Northwest Illinois). | Pavement Improvement | 2009-12-15 | 2010-05-03 | 2010-05-30 | 2010-05-07 | 48250 | 0.180 | 5099090
3767 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099091 | This project will widen and install traffic signals at the intersection of Ralston Road and Blue Bonnet Drive in Winnebago County (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-27 | 2010-09-30 | 2010-09-30 | 703838 | 0.010 | 5099091
3768 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099092 | This project will extend the pavement life by resurfacing a section of Westfield Road in the city of Winnebago (Northwest Illinois). | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-10-30 | 2009-10-30 | 66750 | 1.000 | 5099092
3769 | ILLINOIS | Completed | C250,C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099093 | This project will extend the pavement life by resurfacing sections of Willowbrook Road in Winnebago County (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-24 | 2009-10-30 | 2010-06-04 | 188490 | 2.000 | 5099093
3770 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099094 | This project will extend the pavement life by resurfacing a section of McDonald Road in the city of Roscoe (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-14 | 2009-09-30 | 2009-10-07 | 92618.33 | 1.000 | 5099094
3771 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099095 | This project will extend the pavement life by resurfacing sections of Windsor Road and Riverside Boulevard in the city of Loves Park (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-21 | 2009-10-30 | 2009-11-09 | 455689.36 | 1.520 | 5099095
3772 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099096 | This project will extend the pavement life by resurfacing sections of Machesney Road and Mitchell Road in the village of Machesney Park (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-18 | 2010-05-30 | 2010-06-17 | 178714.98 | 1.720 | 5099096
3773 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099097 | This project will extend the pavement life and improve safety by resurfacing the road and replacing the sidewalk on Longwood Street in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-03 | 2010-08-30 | 2010-08-10 | 516086.51 | 0.320 | 5099097
3774 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099098 | This project will extend the pavement life of two roadways by resurfacing sections of Alpine Road, West State Street, and South Central Avenue in the city of Rockford (Northwest Illinois). | Pavement Improvement | 2010-02-24 | 2010-05-03 | 2010-10-30 | 2010-09-17 | 971771.39 | 1.860 | 5099098
3775 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5099101 | Resurface FAU 5045 (Spring Rock Rd) from Imperial Oaks Dr to Mulford Rd in Rockford. Section 10-00576-00-RS | Pavement Improvement | 2010-10-15 | 2011-05-02 | 2011-06-30 | 2011-07-15 | 388829.87 | 0.780 | 5099101
3776 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | SANGAMON |  | 18 | 5146078 | This project will substantially improve the roadway by reconstructing a section of Meadowbrook Road by providing new concrete pavement and other roadway improvements in Springfield(West-Central Illinois). | Pavement Improvement | 2011-02-24 | 2011-03-30 | 2011-08-30 | 2011-09-30 | 201775 | 0.430 | 5146078
3777 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 17 | 5169042 | This project will extend the bridge life by repairing various bridge piers and making other bridge improvements on Garfield Bridge in the City of Decatur (Southeast Illinois). | Bridge Improvement | 2009-08-03 | 2009-08-10 | 2009-11-30 | 2010-04-14 | 792000 | 0.020 | 5169042
3778 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 15 | 5169043 | This project will substantially improve the roadway by constructing a new section of Fletcher Park Boulevard by providing new concrete pavement in Mt.Zion (Southeast Illinois). | New Construction | 2009-12-14 | 2010-03-31 | 2010-10-30 | 2011-05-18 | 1229600 | 0.570 | 5169043
3779 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 18 | 5169044 | This project will substantially improve the roadway by constructing two new bridges over Stevens Creek and the Tributary on County Highway 20 near Forsyth in Macon County (Southeast Illinois). | Bridge Replacement | 2010-04-19 | 2010-06-07 | 2010-12-30 | 2010-11-19 | 480000 | 0.020 | 5169044
3780 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MACON |  | 17 | 5169045 | This project will substantially improve the roadway by constructing a new bridge over Stevens Creek on MacArthur near Decatur in Macon County (Southeast Illinois). | Bridge Replacement | 2010-03-19 | 2010-04-12 | 2011-05-30 | 2010-11-23 | 447408 | 0.010 | 5169045
3781 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5181040 | This project will substantially improve the roadway by widening 1.5 miles of Windsor Road in Urbana to 4 lanes and providing for other roadway and safety improvements (East-Central Illinois) | Pavement Widening | 2009-06-05 | 2009-07-13 | 2011-06-30 | 2011-10-20 | 2150000 | 2.710 | 5181040
3782 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5181044 | This project will substantially improve the north leg of the 1st Street and Windsor Street intersection with concrete widening and other roadway improvements in Champaign (East-Central Illinois) | Safety/Traffic Management | 2009-08-01 | 2009-08-01 | 2009-11-30 | 2009-12-09 | 337278.19 | 1.530 | 5181044
3783 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5181045 | This project consists of providing engineering design for a future highway improvement on Prospect Avenue in the city of Savoy (East-Central Illinois). | Other | 2009-08-26 | 2009-09-01 | 2010-08-30 | 2011-05-31 | 331226 | 0.880 | 5181045
3784 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | CHAMPAIGN |  | 15 | 5181046 | This project will extend the pavement life by resurfacing 1.25 miles of Kirby Avenue in Champaign (East-Central Illinois) | Pavement Improvement | 2009-12-10 | 2010-06-09 | 2010-08-30 | 2010-08-05 | 1096861.02 | 1.070 | 5181046
3785 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | JO DAVIESS |  | 16 | 5206004 | This project will extend the pavement life by resurfacing a section of 2nd Street in the city of East Dubuque (Northwest Illinois). | Pavement Improvement | 2010-03-08 | 2010-04-26 | 2010-06-30 | 2010-05-21 | 88354 | 0.100 | 5206004
3786 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 5227046 | This project will substantially improve the roadway by reconstructing, widening, and adding other roadway improvements to 0.5 mile of Hamilton Road in Bloomington. | Pavement Improvement | 2009-12-15 | 2010-02-16 | 2011-06-30 | 2012-03-22 | 834472 | 0.100 | 5227046
3787 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 5227050 | This project will provide safety enhancements by installing traffic signals at the intersection of Hershey Road and College Avenue in Bloomington (East-Central Illinois) | Safety/Traffic Management | 2009-12-10 | 2010-03-17 | 2010-05-30 | 2010-04-28 | 172835.69 | 0.010 | 5227050
3788 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 5227051 | This project will extend the pavement life by resurfacing 1 mile of Ireland Grove Road in Bloomington (East-Central Illinois) | Pavement Improvement | 2009-12-03 | 2010-04-06 | 2010-10-30 | 2010-07-06 | 470000 | 0.930 | 5227051
3789 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | MCLEAN |  | 15 | 5227053 | This project will substantially improve 1 block of Virginia Avenue by reconstructing the roadway with concrete pavement, adding other roadway improvements, and replacing the structure over Sugar Creek in Bloomington (East-Central Illinois) | Bridge Replacement | 2009-12-14 | 2010-04-05 | 2010-10-30 | 2011-06-01 | 1414977 | 0.010 | 5227053
3790 | ILLINOIS | Completed | C200 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO |  | 16 | 5291011 | This project will extend the pavement life by resurfacing a section of East Union Street in the city of Rockton (Northwest Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-10 | 2009-10-30 | 2009-10-16 | 279191.55 | 1.840 | 5291011
3791 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5291016 | This project will extend the pavement life by resurfacing a section of Hononegah Road east of IL Route 2 in Winnebago County (Northwest Illinois). | Pavement Improvement | 2010-08-30 | 2010-09-02 | 2011-07-30 | 2011-06-15 | 384467 | 2.120 | 5291016
3792 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WINNEBAGO | ROCKFORD | 16 | 5291017 | Resurface FAU 9874 (Rood Ave) from Moore St to South Bluff Rd in South Beloit. Section 10-00037-00-RS | Pavement Improvement | 2011-02-18 | 2011-08-23 | 2011-05-30 | 2011-10-19 | 218505 | 0.340 | 5291017
3793 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | HENRY | DAVENPORT-ROCK ISLAND-MOLINE (IA) | 17 | 5789005 | This project will extend the pavement life by resurfacing a section of US 6 near the city of Colona (Northwest Illinois). | Pavement Improvement | 2009-04-28 | 2009-05-07 | 2009-08-30 | 2009-05-28 | 289996.23 | 1.060 | 5789005
3794 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 6000201 | This project will extend the pavement life and provide for pedestrian safety by resurfacing, repairing sidewalk, improving traffic signals and streetscaping of Congress Parkway from Wells St. to Michi | Pavement Improvement | 2010-09-17 | 2010-11-20 | 2012-05-30 |  | 9000000 | 0.480 | 6000201
3795 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000282 | Painting of bridges and viaducts (2009 Program) - Contract A Chicago 08-E6106-00-PA | Bridge Improvement | 2011-08-04 | 2011-10-03 | 2011-10-30 |  | 911500 | 0.000 | 6000282
3796 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000284 | This project will extend the pavement life by resurfacing numerous roadway sections in the Far South area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-12-30 | 2010-09-07 | 3860000 | 10.000 | 6000284
3797 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000285 | This project will extend the pavement life by resurfacing numerous roadway sections in the South area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 2009-07-08 | 2009-08-03 | 2009-12-30 | 2010-10-13 | 9353000 | 22.000 | 6000285
3798 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000286 | This project will extend the pavement life by resurfacing numerous roadway sections in the Central area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 2009-07-08 | 2009-07-07 | 2009-12-30 | 2010-05-29 | 5875000 | 12.000 | 6000286
3799 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000287 | This project will extend the pavement life by resurfacing numerous roadway sections in the North area of the City of Chicago in Cook County, Il. (Northeastern Illinois) | Pavement Improvement | 2009-07-01 | 2009-07-07 | 2009-12-30 |  | 9555000 | 18.000 | 6000287
3800 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 6000292 | This project will extend the pavement life by milling, patching and resurfacing Chicago Ave. from Laramie Ave to Grand Ave, in the City of Chicago, IL (Northeastern Illinois). | Pavement Improvement | 2009-11-04 | 2010-03-23 | 2011-11-30 |  | 5753000 | 2.870 | 6000292
3801 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 6000293 | This project will extend the pavement life by resurfacing LaSalle Dr from Clark St. to Lake Shore Dr. (Northeast Illinois) | Pavement Improvement | 2010-04-05 | 2010-06-10 | 2010-09-30 |  | 9356632 | 0.410 | 6000293
3802 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000294 | This project will provide for pedestrian safety by constructing sidewalk ramps that are in compliance with the Americans with Disabilities Act in various locations on the south side of Chicago. (Northeastern Illinois) | Pavement Improvement | 2010-09-17 | 2011-08-06 | 2010-11-30 |  | 4337806 | 0.000 | 6000294
3803 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000295 | This project will provide for pedestrian safety by constructing sidewalk ramps that are in compliance with the Americans with Disabilities Act in various locations on the north side of Chicago. (Northeastern Illinois) | Pavement Improvement | 2010-09-17 | 2011-06-11 | 2010-11-30 |  | 3197721 | 0.000 | 6000295
3804 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000296 | This project will provide for pedestrian safety by constructing sidewalk ramps that are in compliance with the Americans with Disabilities Act in various locations on the far south side of Chicago. (Northeastern Illinois) | Pavement Improvement | 2010-09-17 | 2011-06-11 | 2010-11-30 | 2011-10-15 | 1135807 | 0.000 | 6000296
3805 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000297 | This project will provide for pedestrian safety by constructing sidewalk ramps that are in compliance with the Americans with Disabilities Act in various locations in the central part of the City Chicago. (Northeastern Illinois) | Pavement Improvement | 2010-09-17 | 2011-06-11 | 2010-11-30 | 2012-06-18 | 1685515 | 0.000 | 6000297
3806 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000310 | Arterial Street Resurfacing Project #56 Central Area in Chicago Section 07-B6117-00-RS | Pavement Improvement | 2011-08-29 | 2011-09-02 | 2012-11-30 |  | 4131092 | 0.000 | 6000310
3807 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | STATEWIDE | Multiple | 6000312 | Arterial street resurfacing Project No 58 - Far South Area in Chicago. Section 07-B6119-00-RS | Pavement Improvement | 2011-09-12 | 2011-09-12 | 2011-08-30 |  | 5531981 | 0.000 | 6000312
3808 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000313 | Arterial Street Resurfacing Project #57 South Area in Chicago section 07-B6118-00-RS | Pavement Improvement | 2011-10-03 | 2011-10-10 | 2011-07-30 |  | 4131093 | 0.000 | 6000313
3809 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000315 | Arterial street resurfacing Project No 55 North Area in Chicago. Section 07-B6116-00-RS | Pavement Improvement | 2011-08-29 | 2011-08-29 | 2011-11-30 |  | 4131092 | 0.000 | 6000315
3810 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 6000334 | Painting of bridges & viaducts (2009 Program) Contract B in Chicago. Section 08-E9101-00-PA. | Bridge Improvement | 2011-08-04 | 2011-10-03 | 2011-10-30 |  | 1921763 | 0.000 | 6000334
3811 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | LA SALLE |  | 11 | 6120001 | This project will extend the pavement life by resurfacing a section of IL 178 near the city of Utica (East-Central Illinois). | Pavement Improvement | 2009-04-23 | 2009-05-21 | 2009-08-30 | 2009-06-12 | 290585.59 | 0.780 | 6120001
3812 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | KANKAKEE |  | 11 | 6176002 | This project will substantially improve the roadway by reconstructing a section of Armour Road in the city of Bourbonnais (East-Central Illinois). | Pavement Improvement | 2009-06-01 | 2010-04-05 | 2010-07-30 | 2011-11-21 | 4683342 | 1.250 | 6176002
3813 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 8003322 | This project will substantially improve the roadway by reconstructing Cemetary Rd between Washington St and Tri-State Parkway in the Village of Gurnee (Northeastern Illinois) | Pavement Improvement | 2009-09-15 | 2009-11-01 | 2010-11-30 | 2010-10-13 | 4828105 | 2.940 | 8003322
3814 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 8003516 | This project will extend the pavement life by milling, patching and resurfacing 0.16 miles of Ridgewood Rd. in Riverside, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-01 | 2010-06-14 | 2011-05-30 | 2010-08-13 | 158391.11 | 0.130 | 8003516
3815 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 8003593 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to Madison Street in Villa Park (Northeast Illinois). | Safety/Traffic Management | 2009-10-19 | 2009-11-09 | 2010-06-30 | 2009-12-12 | 229134.55 | 0.900 | 8003593
3816 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 8003809 | This project will substantially improve the roadway by reconstructing a section of Wright Blvd by widening the road, providing new pavement and other roadway improvements in the Village of Schaumburg, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-03 | 2010-03-26 | 2010-05-30 | 2011-07-02 | 752264 | 0.860 | 8003809
3817 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 8003870 | This project will substantially improve the roadway by reconstructing a section of Wilmot Rd between Gordon Terrace and Deerfield Rd in the Village of Deerfield (Northeastern Illinois) by widening the | Pavement Improvement | 2009-06-12 | 2009-08-01 | 2009-11-30 | 2010-05-19 | 1661505.85 | 2.000 | 8003870
3818 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 8003888 | This project will provide for pedestrian/bicycle safety by constructing a new shared use path adjacent to Washington Street in Naperville (Northeast Illinois). | Transportation Enhancements | 2009-08-18 | 2009-08-31 | 2010-05-30 | 2010-10-19 | 1623500 | 0.000 | 8003888
3819 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003067 | This project will extend the life of the pavement by resurfacing Lawndale Ave from 47th St to Ogden Ave in Lyons in Cook County. | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2010-06-30 | 2010-06-07 | 428848.29 | 0.730 | 9003067
3820 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003176 | This project will extend the pavement life by resurfacing 0.99 miles of East Ave from Cermak Rd to Roosevelt Rd in Berwyn. (Northeastern Illinois). | Pavement Improvement | 2009-12-10 | 2010-04-01 | 2010-04-30 | 2010-06-16 | 732016.56 | 0.970 | 9003176
3821 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003193 | This project will extend the pavement life by resurfacing, pavement markings, removing and replacing curb, gutter and sidewalks to assist persons with disabilities. This project is located on Deaan St | Pavement Improvement | 2009-08-07 | 2009-09-21 | 2009-11-30 | 2009-11-05 | 248127.83 | 2.010 | 9003193
3822 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003199 | This project will extend the pavement life by milling, patching and resurfacing Wilson St from Randall Rd to Raddant Rd in the city of Batavia (Northeastern Illinois) | Pavement Improvement | 2009-07-15 | 2009-07-15 | 2009-08-30 | 2009-11-23 | 849742.59 | 5.140 | 9003199
3823 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003218 | This project will extend the pavement life by resurfacing 0.51 miles of 63rd Street from LaGrange Rd to East Ave in Hodgkins in Cook County. (Northeastern Illinois). | Pavement Improvement | 2009-11-10 | 2009-11-10 | 2010-05-30 | 2010-05-11 | 241462.53 | 0.520 | 9003218
3824 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003224 | This project will extend the pavement life by milling, patching, resurfacing and striping McDonald Rd from Burlington Rd to Kendall Rd in the village of Campton Hills (Northeastern Illinois) | Pavement Improvement | 2009-07-01 | 2009-08-24 | 2009-11-30 | 2009-11-04 | 260186.33 | 2.970 | 9003224
3825 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003225 | This project will extend the pavement life by milling, patching, resurfacing and striping on Summit St from Dundee Ave to Hiawatha Drive in the city of Elgin (Northeastern Illinois) | Pavement Improvement | 2009-08-26 | 2009-09-21 | 2009-12-30 | 2009-11-30 | 664549.68 | 1.200 | 9003225
3826 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003252 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Farnsworth Ave from Reckinger Rd to Molitor Rd in the City of Aurora (Northeastern Illinois) | Pavement Improvement | 2009-07-09 | 2009-08-24 | 2009-10-30 | 2010-09-21 | 563238.09 | 1.830 | 9003252
3827 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003254 | This project will extend the pavement life by milling, patching and resurfacing 0.93 mile of Addison Road in the Village of Villa Park, DuPage County (Northeastern Illinois). | Pavement Improvement | 2010-02-22 | 2010-05-03 | 2010-06-30 | 2010-07-19 | 598484.23 | 1.090 | 9003254
3828 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003278 | This project will extend the pavement life by milling, patching and resurfacing 0.98 miles of Central Park Ave. in Evergreen Park, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-03 | 2010-04-12 | 2010-07-30 | 2010-06-18 | 500000 | 1.000 | 9003278
3829 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003292 | This project will extend the pavement life by resurfacing Blackhawk Trail from Plainfield Rd. to Wolf Rd. in the village of Indian Head Park, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-22 | 2009-10-07 | 2009-11-30 | 2010-07-01 | 308965.57 | 1.720 | 9003292
3830 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003299 | This project will extend the pavement life by resurfacing, installing relief sewer, patching, curb & gutter, sidewalks, water main replacement on Sheridan Rd. from South Blvd to Main St. in the city of Evanston, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-08-27 | 2009-09-10 | 2010-06-30 | 2010-11-04 | 1320000 | 1.220 | 9003299
3831 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003301 | This project will extend the pavement life by resurfacing and side walk repairs to accommodate people with disabilties on Washington St from Williams St to Main St in in the Village of Carpentersville (Northeastern Illinois) | Pavement Improvement | 2009-09-08 | 2009-09-21 | 2009-10-30 | 2009-11-06 | 151273.1 | 0.840 | 9003301
3832 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003302 | This project will extend the pavement life by resurfacing 1.11 miles of Prairie Ave from 47th St to Burlington Ave, curb & gutter replacement, patching & sanitary sewer replacement all located in the | Pavement Improvement | 2009-12-10 | 2010-01-25 | 2010-06-30 | 2011-06-23 | 738673.45 | 1.120 | 9003302
3833 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003303 | This project will extend the pavement life by resurfacing 0.53 miles of Brainard Ave. from Harding Ave. to 31st St. in LaGrange Park, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2009-11-30 | 2009-11-12 | 319989 | 1.000 | 9003303
3834 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003304 | This project will extemd the pavement life by resurfacing 0.68 miles of Irving Park Rd. from Madison Dr. to Bartlett Rd. in the village of Streamwood, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-09 | 2009-09-28 | 2009-11-30 | 2009-11-06 | 388381.91 | 1.680 | 9003304
3835 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003305 | This project will extend the pavement life by resurfacing 0.7 miles of 10th St./Wilmette Ave. from Sheridan Road to Lake Avenue in Wilmette, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-09 | 2010-04-20 | 2010-06-30 | 2010-06-26 | 371629 | 0.700 | 9003305
3836 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003306 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Sundown Rd from McLean Bvld to IL 31 in the Village of South Elgin (Northeastern Illinois) | Pavement Improvement | 2009-10-16 | 2009-10-16 | 2010-06-30 | 2011-10-31 | 494678.13 | 0.990 | 9003306
3837 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003307 | This project will extend the bridge life by replacing the bridge deck and making other roadway improvements and repairs to the structure carrying Old Willow Road over the Middle Fork of the north bran | Bridge Improvement | 2009-12-22 | 2010-04-05 | 2010-06-30 | 2010-05-07 | 54807 | 0.020 | 9003307
3838 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003308 | This project will extend the pavement life by milling, patching and resurfacing 0.73 miles of Pfingsten Rd. in Northbrook, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-03 | 2010-07-12 | 2011-05-30 | 2010-08-23 | 453045.75 | 1.070 | 9003308
3839 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003309 | This project will extend the pavement life by resurfacing 1.47 miles of Overlook Drive from Waukegan Road to Golf Road, in the Village of Golf in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-10 | 2009-11-07 | 2009-12-30 | 2009-11-27 | 185093.88 | 1.720 | 9003309
3840 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003311 | This project will extend the pavement life by resurfacing on Bull Valley Rd from Shelby Court to Valley Hill Rd in the Village of Bull Valley (Northeastern Illinois) | Pavement Improvement | 2009-10-16 | 2010-05-03 | 2011-05-30 | 2010-06-19 | 210766.17 | 5.060 | 9003311
3841 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003313 | This project will substantially improve the roadway by reconstructing a section of US 14 at E. Main Street by providing new pavement and other roadway improvements in the City of Cary (Northeast Illinois). | Pavement Improvement | 2010-06-08 | 2010-07-29 | 2010-08-30 | 2011-05-27 | 262000 | 0.100 | 9003313
3842 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003315 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on Algonquin Rd between Plum Tree Rd and US 14 in the Village of Fox River Grove (Northeastern Illinois) | Pavement Improvement | 2009-10-16 | 2009-10-16 | 2010-06-30 | 2010-05-25 | 187560.96 | 0.850 | 9003315
3843 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003316 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement of 1.22 miles onKaneville Rd from Randall Rd to IL Rt 38 in the Village of Geneva(Northeastern Illinois) | Pavement Improvement | 2009-12-14 | 2009-12-14 | 2010-06-30 | 2010-10-14 | 765556.78 | 2.500 | 9003316
3844 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003317 | This project will extend the pavement life by resurfacing on Wondermere Rd from Greenwood Rd to Thompson Rd in the Village of Greenwood (Northeastern Illinois) | Pavement Improvement | 2009-09-01 | 2009-09-01 | 2009-10-30 | 2010-01-31 | 256131.32 | 3.330 | 9003317
3845 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003318 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on State St from IL Rt 72 to north of Keyes Ave in Hampshire (Northeastern Illinois) | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-06-30 | 2011-06-24 | 452644.69 | 1.600 | 9003318
3846 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003319 | This project will extend the pavement life by resurfacing 0.44 miles of 9th Ave from Roosevelt Rd to Bataan Drive in the Village of Maywood in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2010-05-30 | 2010-07-28 | 470000 | 1.320 | 9003319
3847 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003320 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings and detector loop replacement on Douglas Rd between Montgomery Rd a | Pavement Improvement | 2009-12-16 | 2009-12-16 | 2010-06-30 | 2010-12-16 | 479143.03 | 1.340 | 9003320
3848 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003321 | This project will extend the pavement life by resurfacing Lehigh Ave from Oakton Street to Lincoln Avenue in the Village of Morton Grove in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-29 | 2010-05-10 | 2010-05-30 | 2010-06-14 | 356937 | 0.780 | 9003321
3849 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003322 | This project will extend the pavement life by resurfacing Montrose Ave from east of Cumberland Ave to Canfield Ave in the Village of Norridge in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-21 | 2009-11-01 | 2009-12-30 | 2010-06-15 | 258577.49 | 0.490 | 9003322
3850 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003323 | This project will extend the pavement life by resurfacing on Prairie St from west of US Rt 30/IL Rt 47 to Gordon Rd in the Village of Sugar Grove (Northeastern Illinois) | Pavement Improvement | 2009-12-22 | 2010-04-26 | 2010-06-30 | 2010-12-16 | 622771.88 | 3.840 | 9003323
3851 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003324 | This project will extend the pavement life by resurfacing 0.51 miles of Westchester Blvd from Canterbury St to Roosevelt Rd in the Village of Westchester in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-08 | 2009-11-01 | 2010-05-30 | 2010-09-19 | 388466.7 | 2.040 | 9003324
3852 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003326 | This project will extend the pavement life by resurfacing 1.2 miles of Central Rd from Huber Lane to Harlem Avenue in Glenview in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-08 | 2009-10-05 | 2009-12-30 | 2010-08-31 | 514416.18 | 2.880 | 9003326
3853 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003327 | This project will extend the pavement life by resurfacing Division St. from 25th Ave to 14th Ave in Melrose Park in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-11-06 | 2009-11-06 | 2010-06-30 | 2010-09-21 | 347227.55 | 1.010 | 9003327
3854 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003329 | This project will extend the life of the pavement by resurfacing 0.90 miles of Dundee Ave from Lake Cook Rd. to IL Route 59 in Barrington, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-10-29 | 2009-12-07 | 2010-05-30 | 2010-05-25 | 291288.56 | 0.900 | 9003329
3855 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003332 | The project consists of improving safety by installing traffic signals and resurfacing the intersection at Chicago-Heights Glenwood Rd and Holbrook Rd in the Village of Glenwood, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-01-26 | 2010-03-01 | 2010-08-30 | 2011-06-02 | 326479 | 0.010 | 9003332
3856 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003333 | This project consists of improving safety by installing street lighting along Broadway Ave in the City of Harvey, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-07-30 | 2011-06-02 | 408345 | 0.540 | 9003333
3857 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003334 | This project consists of improving safety by installing street lighting along 138th St in the Village of Riverdale, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-07-30 | 2011-06-20 | 369505 | 1.260 | 9003334
3858 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003335 | This project consists of improving safety by installing street lighting along Bernice Rd in the City of Lansing, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-01-08 | 2010-01-08 | 2011-05-30 | 2011-05-31 | 283947.39 | 1.350 | 9003335
3859 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003336 | This project consists of improving safety by installing emergency vehicle pre-emption equipment at 13 various intersections in the Village of Dolton, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-07-30 | 2010-08-31 | 114278 | 0.000 | 9003336
3860 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003337 | This project will extend the pavement life by milling, patching and resurfacing 0.99 miles of East End Ave. in Chicago Heights, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-01-08 | 2010-01-01 | 2010-06-30 | 2010-07-01 | 758423 | 1.020 | 9003337
3861 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003338 | This project will substantially improve the roadway by reconstructing a section of Western Ave by providing new concrete pavement and other roadway improvements in Blue Island, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-07-30 | 2011-05-31 | 300566 | 0.040 | 9003338
3862 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003340 | This project will substantially improve the roadway by widening IL 43 from 243 ft north of 71st Street for 0.329 miles to the north in the Village of Bridgeview in Cook County (Northeastern Illinois). | Pavement Improvement | 2010-01-20 | 2010-03-15 | 2010-06-30 | 2010-07-10 | 500000 | 0.010 | 9003340
3863 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003341 | This project will improve safety by installing lighting on Ridge Road and McEvilly Road in the village of Minooka (East-Central Illinois). | Safety/Traffic Management | 2010-05-11 | 2010-10-07 | 2011-05-30 | 2011-03-25 | 169800 | 1.220 | 9003341
3864 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003342 | This project will extend the pavement life by patching and resurfacing 173rd St/Elm Dr. in Hazel Crest, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-02-16 | 2010-04-01 | 2010-12-30 | 2011-10-30 | 325575.41 | 0.630 | 9003342
3865 | ILLINOIS | Completed | C220,C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003343 | This project will enhance the roadway by installing 1.4 miles of tree planting, sidewalk improvements, pedestrian signals and lighting and signing along 95th St. (US 12/20) from 76th Avenue 88th St. in Hickory Hills (Norheastern Illinois). | Safety/Traffic Management | 2010-02-19 | 2010-02-20 | 2010-11-30 | 2011-06-30 | 745693 | 1.450 | 9003343
3866 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003344 | This project will extend the pavement life by milling, patching and resurfacing Madison St. in the Village of Bellwood, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-02-24 | 2010-04-09 | 2010-06-30 | 2010-07-22 | 258450.91 | 0.510 | 9003344
3867 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003345 | This project will extend the life of the pavement by resurfacing N. Oak Ave from W Bartlett Ave to US 20 & resurfacing W. Bartlett Ave from IL 59 to Western Ave, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-12-14 | 2009-12-17 | 2010-07-30 | 2010-10-16 | 1347367 | 1.740 | 9003345
3868 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003349 | This project will extend the life of the pavement by resurfacing Thatcher Ave. from Central Ave. to Chicago Ave. in the village of River Forest, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2009-10-30 | 2009-11-14 | 267629.81 | 0.980 | 9003349
3869 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003352 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings on Ringwood Rd between Spring Grove Rd and Johnsburg Rd in the village of Johnsburg (Northeastern Illinois) | Pavement Improvement | 2009-10-26 | 2009-10-26 | 2010-06-30 | 2010-06-07 | 253107 | 2.440 | 9003352
3870 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003353 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 0.90 miles on Ridge Rd between Deerwood Trail and IL Rt 120 in the City of McHenry (Northeastern Illinois) | Pavement Improvement | 2009-10-27 | 2009-10-27 | 2010-06-30 | 2010-05-22 | 242990 | 2.880 | 9003353
3871 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003354 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 1.27 miles on Valley View Rd between Crystal Lake Rd and IL Rt 1 | Pavement Improvement | 2009-09-09 | 2009-09-28 | 2009-10-30 | 2009-10-21 | 227223.99 | 3.900 | 9003354
3872 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003355 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of 1.40 miles on Ringwood Rd between McCullom Lake Rd and Devonshir | Pavement Improvement | 2009-10-27 | 2009-10-27 | 2010-06-30 | 2010-05-22 | 236816 | 6.280 | 9003355
3873 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003356 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of on East Wonder Lake Rd between McCullom Lake Rd and Burnard Mill | Pavement Improvement | 2009-12-10 | 2010-05-03 | 2010-05-30 | 2010-06-01 | 258510 | 1.610 | 9003356
3874 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003357 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement on Huntington Dr North from Stonegate Rd to Hanson Rd in the Village of Algonquin (Northeastern Illinois) | Pavement Improvement | 2009-09-08 | 2009-09-21 | 2009-10-30 | 2009-11-21 | 262105 | 2.070 | 9003357
3875 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003358 | This project will extend the pavement life by resurfacing, some curb, gutter and sidewalk replacement including handicap ramps on 1.0 mile on Kreutzer Rd from Smith Rd to Northwestern Railroad tracks in the Village of Huntley (Northeastern Illinois) | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-10-30 | 2009-11-19 | 183632.11 | 0.880 | 9003358
3876 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003359 | This project will extend the life of the pavement by resurfacing Fullerton Ave. from Webster St. to 76th Ave. in Elmwood Park, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2009-11-30 | 2010-11-23 | 257054.4 | 1.000 | 9003359
3877 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003360 | This project will provide for pedestrian safety by constructing a sidewalk extension adjacent to Manhattan Road in the Village of Manhattan, Will County (Northeastern Illinois). | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-06-30 | 2010-07-31 | 94000.22 | 0.350 | 9003360
3878 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003361 | This project will extend the pavement life by resurfacing 0.81 miles on 135th Street in Romeoville (Northeast Illinois). | Pavement Improvement | 2009-12-08 | 2010-01-11 | 2010-06-30 | 2010-05-03 | 355059.47 | 2.020 | 9003361
3879 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003362 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to Rathje Road in Peotone (Northeast Illinois). | Safety/Traffic Management | 2009-12-17 | 2010-01-13 | 2010-06-30 | 2011-05-31 | 37706.85 | 0.230 | 9003362
3880 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003363 | This project will extend the pavement life by resurfacing on Sauk Trail in Frankfort (Northeast Illinois). | Pavement Improvement | 2009-01-13 | 2009-01-13 | 2010-06-30 | 2010-07-26 | 190000 | 1.000 | 9003363
3881 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003364 | This project will extend the pavement life by resurfacing 99th St. from Oak Park Avenue to Ridgeland Avenue in Chicago Ridge in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-08-19 | 2009-10-03 | 2009-12-30 | 2010-04-01 | 332911.12 | 0.280 | 9003364
3882 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003366 | This project will enhance mobility by constructing a 10-foot wide asphalt pedestrian path for the Stony Creek Trail from Austin Ave to Mansfield Ave in Oak Lawn, Cook County (Northeastern Illinois). | Transportation Enhancements | 2010-03-31 | 2010-03-31 | 2011-05-30 | 2011-07-07 | 373434 | 0.000 | 9003366
3883 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003367 | This project consists of improving safety by installing street lighting along Sauk Trail in the City of Lansing, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-03-16 | 2010-07-26 | 2010-08-30 |  | 310171 | 0.890 | 9003367
3884 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003368 | This project will extend the life of the pavement by resurfacing Green Bay Rd. from Park Ave to Scott Ave in Glencoe in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-12-10 | 2010-05-10 | 2010-06-30 | 2010-08-07 | 524845.16 | 1.280 | 9003368
3885 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003369 | This project will extend the pavement life by resurfacing on Barreville Rd from north village limits to Ames Rd in the Village of Prairie Grove (Northeastern Illinois) | Pavement Improvement | 2009-12-28 | 2010-05-03 | 2010-05-30 | 2010-05-21 | 246401.04 | 0.720 | 9003369
3886 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003370 | This project will improve safety by lighting 0.5 miles of US Route 30 in Mokena (Northeast Illinois) | Safety/Traffic Management | 2009-11-19 | 2010-04-20 | 2011-05-30 | 2011-05-16 | 258742 | 0.030 | 9003370
3887 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003371 | This project will extend the pavement life by resurfacing 0.5 miles on Gaylord Road in Crest Hill (Northeast Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-11 | 2009-10-30 | 2010-04-01 | 133414.38 | 1.530 | 9003371
3888 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003372 | This project will extend the pavement life by resurfacing 0.7 miles of 167th Street from 88th Ave to Hobart Ave in Orland Hills, Cook County (Northeastern Illinois). | Pavement Improvement | 2010-04-19 | 2010-05-10 | 2010-07-30 | 2010-08-07 | 366562.23 | 0.710 | 9003372
3889 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003373 | This project will extend the pavement life by resurfacing on 151st Street in Homer Glen (Northeast Illinois). | Pavement Improvement | 2009-09-08 | 2009-09-28 | 2009-10-30 | 2010-01-22 | 324520.7 | 3.000 | 9003373
3890 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003374 | This project will extend the life of the pavement by resurfacing 0.80 miles of Tower Road from Hibbard Road to Sheridan Road excluding Green Bay Road & Sheridan Road intersections, minor curb repair a | Pavement Improvement | 2009-10-29 | 2010-05-17 | 2011-05-30 | 2010-12-08 | 341861.61 | 0.890 | 9003374
3891 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003375 | This project will extend the pavement life by milling, patching and resurfacing 0.49 miles of Laramie Ave. in Oak Forest, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-19 | 2010-04-26 | 2010-06-30 | 2010-06-01 | 240956.25 | 0.500 | 9003375
3892 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003376 | This project will extend the life of the pavement by resurfacing 0.97 miles of Main St. from IL 50 to Crawford Avenue in Skokie in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-12-28 | 2010-04-01 | 2010-06-30 | 2010-09-15 | 764963.74 | 1.000 | 9003376
3893 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003377 | This project will improve mobility and safety by installing traffic signals & interconnections at the intersection of 127th St & Timberline Drive in Lemont in Cook County (Northeastern Illinois). | Safety/Traffic Management | 2009-12-08 | 2010-03-08 | 2010-06-30 | 2010-06-10 | 204073 | 0.010 | 9003377
3894 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003378 | This project will provide for pedestrian safety by removal & replacement of existing sidewalk with ADA ramps, and new curb & gutter along Roberts Road from 97th st to 111th St. and along 111th St from | Safety/Traffic Management | 2009-10-29 | 2009-12-21 | 2010-06-30 | 2010-06-21 | 294000 | 6.940 | 9003378
3895 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003379 | This project will extend the pavement life by milling, patching and resurfacing 0.48 miles of Flossmoor Rd. in Flossmoor, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-30 | 2010-04-21 | 2010-06-30 | 2010-08-11 | 148255.72 | 0.470 | 9003379
3896 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003380 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to IL 59 in Naperville (Northeast Illinois). | Safety/Traffic Management | 2010-01-04 | 2010-04-21 | 2010-07-30 | 2010-11-20 | 736796.07 | 3.160 | 9003380
3897 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003381 | This project will extend the pavement life by patching and resurfacing Church Road in the Village of Beecher, Will County (Northeastern Illinois). | Pavement Improvement | 2009-12-29 | 2010-03-01 | 2010-06-30 | 2010-05-18 | 89806 | 1.000 | 9003381
3898 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003382 | This project will extend the life of the pavement by resurfacing 0.28 miles of Franklin Ave from Ruby St to Rose St / 25th St in Franklin Park in Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2010-05-30 | 2010-06-29 | 316791.41 | 0.540 | 9003382
3899 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003383 | This project will extend the pavement life by resurfacing on Drauden Road in Plainfield (Northeast Illinois). | Pavement Improvement | 2009-12-08 | 2010-04-06 | 2010-05-30 | 2010-10-11 | 139610 | 0.990 | 9003383
3900 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003384 | This project will extend the pavement life by milling, patching and resurfacing 0.78 miles of 135th St. in Crestwood, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-04-14 | 2010-05-17 | 2010-07-30 | 2010-10-22 | 225000 | 1.010 | 9003384
3901 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003385 | This project will improve mobility by constructing a sidewalk adjacent to Harlem Ave between 119th St and 131st St., on McCarthy Road between 76th Ave and 123rd St., and on 135th St. from Ridgeland to | Safety/Traffic Management | 2010-05-10 | 2010-06-22 | 2010-08-30 | 2011-05-28 | 265303 | 2.070 | 9003385
3902 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003386 | This project will extend the pavement life by milling, patching and resurfacing Burlington Ave from Brainard Ave to Kensington Ave in Lagrange, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-02-22 | 2010-06-07 | 2010-06-30 | 2010-10-17 | 263759.02 | 0.270 | 9003386
3903 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003387 | This project will extend the pavement life by resurfacing Central Ave from 70th Place to a point 1200 feet south of 73rd St in Bedford Park in Cook County (Northeastern Illinois). | Pavement Improvement | 2010-02-08 | 2010-04-22 | 2010-08-30 | 2010-10-04 | 452759.38 | 1.010 | 9003387
3904 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003389 | This project will extend the pavement life by resurfacing 1.10 miles on Thomas Dillon Drive in Channahon (Northeast Illinois). | Pavement Improvement | 2009-10-23 | 2010-04-27 | 2009-12-30 | 2010-05-04 | 154769.61 | 1.120 | 9003389
3905 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003390 | This project will enhance mobility by constructing a 0.4 mile multi-use path on the east side of 104th Ave from 167th St to 163rd Place in the Village of Orland Park, Cook County (Northeastern Illinois). | Transportation Enhancements | 2010-04-29 | 2010-05-09 | 2010-08-30 | 2010-11-10 | 261163.61 | 0.000 | 9003390
3906 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003391 | This project will extend the pavement life by milling, patching and resurfacing 0.51 mile of Clarendon Hills Road in the Village of Willowbrook, DuPage County (Northeastern Illinois). | Pavement Improvement | 2010-05-12 | 2010-06-09 | 2010-05-30 | 2010-06-29 | 192039.67 | 0.500 | 9003391
3907 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003392 | This project will provide for pedestrian safety by constructing a new sidewalks adjacent to Harlem Ave, 107th St, and Ridgeland Ave in Worth, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-04-08 | 2010-05-26 | 2010-07-30 | 2010-10-16 | 213195.83 | 0.830 | 9003392
3908 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003393 | This project will extend the pavement life by milling, patching and resurfacing 0.49 miles of Kostner Ave. in Crestwood, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-03 | 2010-04-15 | 2010-06-30 | 2010-07-09 | 175447.86 | 1.000 | 9003393
3909 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003394 | This project will extend the pavement life by resurfacing 0.39 miles of 34th St. from Union Ave to Holeman Ave in South Chicago Heights, Cook County (Northeastern Illinois). | Pavement Improvement | 2009-09-17 | 2010-04-26 | 2010-12-30 | 2011-10-30 | 368018 | 0.370 | 9003394
3910 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003395 | This project will improve mobility by constructing 1.0 miles of sidewalk on the east side of Kedzie Ave from 153rd St to 159th St. in the City of Markham, Cook County (Northeastern Illinois). | Safety/Traffic Management | 2010-05-24 | 2010-05-24 | 2011-01-30 | 2011-01-05 | 215157.82 | 2.640 | 9003395
3911 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003396 | This project will extend the pavement life by resurfacing on Wallin Drive in Plainfield (Northeast Illinois). | Pavement Improvement | 2009-12-08 | 2010-04-06 | 2010-05-30 | 2010-10-11 | 147752 | 1.010 | 9003396
3912 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003397 | This project will extend pavement life by milling, patching and resurfacing an eight block section of Janes Avenue in the City of Woodridge (Northeastern Illinois). | Pavement Improvement | 2010-03-02 | 2010-04-02 | 2010-06-30 | 2010-05-21 | 434085.18 | 2.000 | 9003397
3913 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003398 | This project will extend the pavement life by patching, milling and resurfacing Woodridge Drive from Hobson Road to Center Drive in the Village of Woodridge (Northeastern Illinois). | Pavement Improvement | 2010-10-28 | 2011-04-12 | 2011-05-30 | 2011-05-28 | 119900 | 0.680 | 9003398
3914 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003399 | This project will extend the life of the bridge carrying Whitehall Ave over Addison Creek by removing existing superstructure & replace with wide flange steel beam & concrete deck & roadway improvemen | Bridge Improvement | 2010-03-31 | 2010-03-31 | 2010-07-30 | 2011-10-31 | 494764 | 0.200 | 9003399
3915 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003400 | This project will extend the pavement life by milling, patching and resurfacing 1.02 mile of Lies Road in the Village of Carol Stream, DuPage County (Northeastern Illinois). | Pavement Improvement | 2010-02-19 | 2010-05-03 | 2010-07-30 | 2010-12-18 | 549326.51 | 1.010 | 9003400
3916 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003403 | This project will extend the pavement life by milling and resurfacing Powis Road from North Avenue to Smith Road in the City of West Chicago (Northeastern Illinois). | Pavement Improvement | 2010-06-10 | 2010-07-06 | 2010-09-30 | 2010-10-01 | 232025.8 | 1.150 | 9003403
3917 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003405 | This project will extend the pavement life by milling and resurfacing Joliet Street from IL Route 59 to Geneva Street in the City of West Chicago (Northeastern Illinois). | Pavement Improvement | 2010-05-18 | 2010-06-28 | 2010-08-30 | 2010-09-25 | 581269.77 | 2.080 | 9003405
3918 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003406 | This project will extend the pavement life by milling and resurfacing Arbor Avenue from Washington Street to Hawthorne Lane in the City of West Chicago (Northeastern Illinois). | Pavement Improvement | 2010-08-03 | 2010-08-05 | 2010-08-30 | 2010-11-19 | 303786 | 1.040 | 9003406
3919 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003408 | This project will extend the pavement life by milling and resurfacing 1.21 miles of Bruce Road and 163rd Street in the City of Lockport (Northeastern Illinois). | Pavement Improvement | 2010-03-01 | 2010-06-09 | 2010-06-30 | 2010-09-25 | 382947.64 | 1.880 | 9003408
3920 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003410 | This project will extend the pavement life by milling, patching and resurfacing 1.02 mile of St. Charles Road in the City of Elmhurst (Northeastern Illinois). | Pavement Improvement | 2010-02-22 | 2010-05-03 | 2010-06-30 | 2010-07-10 | 348645.69 | 0.510 | 9003410
3921 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003411 | This project will extend the pavement life by patching, milling and resurfacing Vallette Street from Spring Road to Poplar Avenue in the City of Elmhurst, DuPage County (Northeastern Illinois) | Pavement Improvement | 2010-09-16 | 2011-05-02 | 2010-11-30 | 2011-10-27 | 785000 | 0.980 | 9003411
3922 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003412 | This project will substantially improve the roadway by reconstruction a section of First Street from Myrtle Avenue to Clara Place in the City of Elmhurst (Notheastern Illinois). | Pavement Improvement | 2010-04-29 | 2010-06-01 | 2010-06-30 | 2010-12-22 | 310000 | 0.730 | 9003412
3923 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003417 | This project will extend the pavement life by milling and resurfacing 1.13 miles of Park Boulevard and Lambert Road in the Village of Glen Ellyn, DuPage County (Northeastern Illinois). | Pavement Improvement | 2010-05-20 | 2010-06-14 | 2010-07-30 | 2011-09-02 | 570767.96 | 1.090 | 9003417
3924 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003418 | This project will enhance mobility by constructing a new sidewalk on Governors Highway from Sauk Trail to Maple Ave, from Poplar Ave to north Maple Ave, from 400 feet south of Sauk Trail to Sauk Trail | Safety/Traffic Management | 2010-06-08 | 2010-08-01 | 2011-05-30 | 2011-04-16 | 95859.45 | 0.630 | 9003418
3925 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003419 | This project consists of improving safety and traffic enhancement by 0.78 miles of traffic signal modernization on US Rt 14 from Dole Ave to Devonshire Lane/Kieth Ave in Crystal Lake (Northeastern Illinois) | Safety/Traffic Management | 2009-12-03 | 2010-03-02 | 2010-07-30 | 2010-10-26 | 270551 | 0.770 | 9003419
3926 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003420 | This project will extend the pavement life with 3.0 miles of concrete pavement patching, asphalt overlay, shoulder rehabilitation, new pipe underdrains, sidewalk removal & replacement on E. Frontage R | Pavement Improvement | 2009-09-21 | 2009-10-01 | 2010-07-30 | 2010-05-28 | 2822101 | 7.890 | 9003420
3927 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003421 | This project will extend the pavement life by milling, patching and resurfacing 1.1 miles of St. Charles Road from Illinois Route 53 to Grace Street in the Village of Lombard, DuPage County (Northeastern Illinois). | Pavement Improvement | 2010-05-26 | 2010-06-29 | 2010-08-30 | 2011-05-07 | 47063 | 1.480 | 9003421
3928 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003422 | This project will extend the pavement life by milling, patching and resurfacing 127th St from 80th Ave to 123rd St and 121st St from Southwest Highway to 80th Ave in Palos Park, Illinois (Northeastern Illinois). | Pavement Improvement | 2010-02-24 | 2010-02-24 | 2011-05-30 | 2011-03-08 | 216147.92 | 0.640 | 9003422
3929 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003423 | This project will extend the pavement life by milling, patching and resurfacing 0.76 miles of Gilbert Ave. in Western Springs, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-01 | 2010-03-17 | 2010-06-30 | 2010-06-22 | 465811.9 | 0.780 | 9003423
3930 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003424 | This project will extend the pavement life by resurfacing numerous roadway sections in DuPage County (Northeastern Illinois). | Pavement Improvement | 2009-12-08 | 2010-05-10 | 2010-07-30 | 2010-08-26 | 353999.41 | 2.210 | 9003424
3931 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003425 | This project will extend the pavement life by resurfacing 1.09 miles on Gardield Street in Hinsdale (Northeast Illinois) | Pavement Improvement | 2009-12-09 | 2010-04-05 | 2010-11-30 | 2011-11-01 | 1378106.68 | 1.010 | 9003425
3932 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003426 | This project will extend the pavement life by milling, patching and resurfacing 187th St. from Dixie Highway to Riegel Rd in Homewood, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-03 | 2010-04-12 | 2010-06-30 | 2010-06-03 | 210281 | 0.660 | 9003426
3933 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003428 | This project will extend the pavement life by milling, patching and resurfacing 139th St. from Crawford Ave to Coopers Grove Rd in Robbins, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-01-08 | 2010-05-01 | 2010-08-30 | 2010-08-19 | 713000 | 2.420 | 9003428
3934 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003429 | This project will extend the pavement life by milling, patching and resurfacing 0.69 miles of Woodlawn Ave. in Ford Heights, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-01-08 | 2010-03-01 | 2010-07-30 | 2010-09-14 | 399347.48 | 1.360 | 9003429
3935 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003430 | This project will provide for pedestrian safety by constructing a new sidewalks adjacent to Algonquin Rd from Seymour Ave to Mt. Prospect Rd. in Des Plaines, Illinois (Northeastern Illinois) | Safety/Traffic Management | 2010-02-24 | 2010-04-05 | 2010-07-30 | 2010-05-17 | 139672.24 | 0.700 | 9003430
3936 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003431 | This project will extend the pavement life by resurfacing University Parkway from Crawford Avenue to Steger-Monee Road in the Village of University Park, Will County (Northeastern Illinois). | Pavement Improvement | 2010-03-31 | 2010-05-06 | 2010-07-30 | 2011-12-05 | 371573 | 2.420 | 9003431
3937 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003436 | This project will extend the pavement life by resurfacing 0.91 miles on Boughton Road in Bolingbrook (Northeast Illinois). | Pavement Improvement | 2009-10-01 | 2009-10-12 | 2009-12-30 | 2009-11-27 | 618177.12 | 3.210 | 9003436
3938 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003438 | This project consists of improving safety by upgrading traffic signals on Schmidt Road at the intersection with Remington Boulevard in the Village of Bolingbrook, Will County (Northeastern Illinois). | Safety/Traffic Management | 2010-01-26 | 2010-01-26 | 2010-06-30 | 2011-06-07 | 274260.46 | 0.010 | 9003438
3939 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003439 | This project will extend the pavement life by resurfacing and improve safety and traffic enhancement by upgrading pavement markings of on Oak St between Crystal Lake Rd and Burr St in the village of Lake in the Hills (Northeastern Illinois) | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2010-06-30 | 2010-05-29 | 217318.92 | 0.720 | 9003439
3940 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003440 | This project will extend the pavement life by resurfacing on Shick Road in Bloomingdale (Northeast Illinois). | Pavement Improvement | 2009-10-29 | 2010-04-15 | 2010-07-30 | 2010-08-07 | 1331335 | 0.930 | 9003440
3941 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003441 | Lake County will add new pavement, curbs and gutters on Pheasant Ridge Rd near Old Mill Rd in Lake Zurich. | Pavement Improvement | 2010-08-19 | 2010-09-29 | 2010-08-30 | 2010-10-11 | 119000 | 0.410 | 9003441
3942 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003442 | This project will extend the pavement life by milling, patching and resurfacing Edina Blvd. from 21st street to Shiloh Blvd. (Northeast Illinios). | Pavement Improvement | 2010-01-12 | 2010-01-12 | 2010-05-30 | 2011-07-29 | 197679 | 0.480 | 9003442
3943 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003443 | This project will extend the pavement life by resurfacing Old Barrington Road from Cuba Rd to IL 22 in the City of North Barrington (Northeastern Illinois). | Pavement Improvement | 2010-03-02 | 2010-04-27 | 2010-06-30 | 2010-06-07 | 235139 | 1.020 | 9003443
3944 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003445 | This project will substantially extend the pavement life by resurfacing, landscaping and improve safety and traffic enhancement by upgrading pavement markings of on Raffel Rd from Il Rt 120 Banford Rd in the City of Woodstock (Northeastern Illinois) | Pavement Improvement | 2009-12-10 | 2010-05-03 | 2010-06-30 | 2010-08-21 | 270551 | 0.250 | 9003445
3945 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003449 | This project will extend the pavement life by milling, patching and resurfacing 0.48 miles on Garfield St from McKinley St to Old Orchard Rd in Harvard (Northeastern Illinois). | Pavement Improvement | 2009-12-07 | 2010-03-15 | 2010-03-30 | 2010-06-07 | 212714.24 | 0.450 | 9003449
3946 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003450 | Lake County will add new pavement, curb and gutter and sidewalk on Lake street between IL Rt 120 and Center Street. | Pavement Improvement | 2010-06-17 | 2010-09-20 | 2011-05-30 | 2011-07-12 | 260174.43 | 0.410 | 9003450
3947 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003452 | This project will extend the pavement life by milling, patching and resurfacing Deerpath Rd near Deer Park, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-02 | 2010-04-27 | 2010-05-30 | 2010-06-07 | 118480 | 0.420 | 9003452
3948 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003453 | Lake County will replace curb and gutter and Sidewalk on Old Checker Rd near Buffalo grove Rd. | Pavement Improvement | 2010-06-17 | 2010-09-16 | 2010-10-30 | 2011-09-30 | 296100 | 0.800 | 9003453
3949 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003454 | This project will extend the pavement life by milling, patching and resurfacing Telegraph Rd near Bannnockburn, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-02 | 2010-05-15 | 2010-06-30 | 2010-09-28 | 248616 | 1.000 | 9003454
3950 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003456 | This project will extend the pavement life by resurfacing a four block section of Laurel Ave in the City of Highland Park (Northeast Illinois). | Pavement Improvement | 2010-03-02 | 2010-05-03 | 2010-06-30 | 2010-06-19 | 136394 | 0.370 | 9003456
3951 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003457 | This project will extend the pavement life by milling, patching and resurfacing Sheridan Rd near Highwood, Illinois (Northeast Illinios). | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-06-30 | 2011-11-30 | 437566 | 1.180 | 9003457
3952 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003458 | This project will extend the pavement life by milling, patching and resurfacing Deerpath Drive near Lindenhurst, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-01 | 2010-05-03 | 2010-05-30 | 2010-12-15 | 169230 | 0.520 | 9003458
3953 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003459 | This project will extend the pavement life by milling, patching and resurfacing Saunders Road near Riverwood, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-02 | 2010-04-28 | 2010-06-30 | 2010-06-10 | 331128 | 1.450 | 9003459
3954 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003461 | Village of Wauconda will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of pavement from Bonner Rd to Gossell Rd | Pavement Improvement | 2010-02-19 | 2010-06-01 | 2011-05-30 | 2010-10-22 | 231818 | 1.450 | 9003461
3955 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003462 | This project will extend the pavement life by milling, patching and resurfacing Jackson Street near Waukegan, Illinois (Northeast Illinios). | Pavement Improvement | 2010-03-15 | 2010-04-19 | 2010-07-30 | 2010-07-24 | 661320 | 2.600 | 9003462
3956 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003465 | This project will extend the pavement life by milling and resurfacing various roadway sections in the City of Joliet (Northeastern Illinois). | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-07-30 | 2011-10-01 | 1221541.45 | 0.000 | 9003465
3957 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003466 | This project will extend the pavement life by resurfacing 3.65 miles on River Road near Wilmington (Northeast Illinois). | Pavement Improvement | 2009-12-28 | 2010-04-05 | 2010-07-30 | 2010-06-17 | 1163221.42 | 3.700 | 9003466
3958 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003467 | Lake County will replace pavement and improve shoulders on Fairfield Rd between IL 176 and Old Mchenry Rd. | Pavement Improvement | 2010-06-17 | 2010-08-01 | 2010-09-30 | 2010-11-20 | 1202009.3 | 3.550 | 9003467
3959 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003471 | This project will extend the pavement life by resurfacing, pavement patching and curb and gutter replacement on Central Ave from Church Street to Golf Road in the Village of Morton Grove, Illinois (Northeastern Illinois). | Pavement Improvement | 2010-08-05 | 2010-09-20 | 2010-08-30 | 2010-11-08 | 222807 | 0.500 | 9003471
3960 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 9003472 | This project consists of improving safety by installation of a complete street lighting system along Algonquin Rd, Golf Rd and New Wilke Road in the City of Rolling Meadows, IL (Northeastern Illinois) | Safety/Traffic Management | 2010-11-30 | 2011-07-16 | 2011-08-30 | 2012-10-13 | 979739 | 3.260 | 9003472
3961 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003475 | This project will extend the pavement life by milling, patching and resurfacing Chapel Hill Rd near Johnsburg, Illinois (Northeast Illinois). | Pavement Improvement | 2010-05-12 | 2010-06-14 | 2010-06-30 | 2010-10-13 | 262105 | 2.000 | 9003475
3962 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003476 | This project will extend the pavement life by milling, patching and resurfacing Rawson Bridge Rd near Port Barrington, Illinois (Northeast Illinios). | Pavement Improvement | 2010-04-29 | 2010-04-30 | 2010-06-30 | 2010-10-30 | 221979.63 | 0.010 | 9003476
3963 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003478 | This project consists of improving safety and traffic enhancement by installing street lighting along IL Route 113 from Center Road to Mitchell Street in the City of Braidwood (Northeastern Illinois). | Safety/Traffic Management | 2010-06-17 | 2011-04-09 | 2010-07-30 | 2011-11-04 | 68000 | 0.250 | 9003478
3964 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003481 | This project will extend the pavement life by milling, patching and resurfacing 0.46 miles of Glenview Road between Waukegan Road and Chatham Road in Glenview, Illinois (Northeastern Illinios). | Pavement Improvement | 2010-11-15 | 2011-04-09 | 2010-10-30 | 2011-07-02 | 179173 | 0.460 | 9003481
3965 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003486 | This project will extend the pavement life by milling and resurfacing various roadway sections in the Village of New Lenox, Will County (Northeastern Illinois). | Pavement Improvement | 2010-04-19 | 2010-05-26 | 2010-06-30 | 2010-06-26 | 247119.24 | 0.000 | 9003486
3966 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003489 | This project will extend pavement life by resurfacing 0.4 miles of Devon Avenue from Higgins Rd to I-294 in the Village of Rosemont in Cook County (Northeastern Illinois). | Pavement Improvement | 2010-03-31 | 2010-03-31 | 2010-06-30 | 2011-01-17 | 428715.38 | 0.360 | 9003489
3967 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003490 | This project will extend pavement life by resurfacing numerous roadway sections in DuPage County including Gary Ave, Naperville Rd, Lemont Rd, Ferry Rd and Diehl Rd. (Northeastern Illinois) | Pavement Improvement | 2010-03-19 | 2010-04-14 | 2010-08-30 | 2010-09-04 | 3443994 | 0.000 | 9003490
3968 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003497 | Lake County will replace pavement on Deerpath Rd Resurface from IL Route 60 to Marimac Lane in the village of Vernon Hills. | Pavement Improvement | 2010-08-19 | 2010-09-07 | 2010-08-30 | 2010-10-15 | 273000 | 1.470 | 9003497
3969 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | GRUNDY | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003498 | This project will provide for pedestrian safety by constructing sidewalks and ramps along various streets in the village of Coal City (East-Central Illinois). | Safety/Traffic Management | 2010-06-29 | 2010-10-11 | 2010-05-30 | 2010-11-16 | 60934.02 | 0.000 | 9003498
3970 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003500 | This project will extend the pavement life by resurfacing 0.5 miles of Montrose Ave from Sayre Ave to Forest Preserve Ave in the Village of Harwood Heights, Cook County (Northeastern Illinois). | Pavement Improvement | 2010-04-09 | 2010-05-27 | 2010-05-30 | 2010-06-12 | 200396 | 0.480 | 9003500
3971 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 07 | 9003505 | This project will extend the pavement life by resurfacing 0.4 miles of Ridgeland Ave from Roosevelt Rd to Garfield St., and 1.0 miles from Division St. to North Ave in Oak Park, Cook County (Northeastern Illinois). | Pavement Improvement | 2010-04-09 | 2010-04-30 | 2010-06-30 | 2010-08-07 | 533231 | 0.920 | 9003505
3972 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 10 | 9003507 | Resurface FAU 2666 (Main St) from IL Route 22 to Buffalo Grove Rd in Buffalo Grove. Section 09-00096-00-RS | Pavement Improvement | 2010-07-27 | 2010-11-10 | 2011-12-30 | 2010-12-19 | 188388 | 0.670 | 9003507
3973 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003513 | This project will provide for pedestrian safety by replacing sidewalks along Kankakee Street from Baltimore Street to Kankakee River Drive in the City of Wilmington (Northeastern Illinois). | Safety/Traffic Management | 2010-03-12 | 2010-04-01 | 2010-05-30 | 2010-06-15 | 52410 | 0.800 | 9003513
3974 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003515 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to County Line Road in Burr Ridge (Northeast Illinois). | Safety/Traffic Management | 2010-01-08 | 2010-08-30 | 2011-05-30 | 2011-05-27 | 200384.23 | 0.550 | 9003515
3975 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | Multiple | 9003516 | This project substantially improve the roadway by reconstructing Broadway Ave from Iowa Street to Division Street and will extend the pavement life by resurfacing Broadway Ave from Lake Street to Iowa | Pavement Improvement | 2010-08-05 | 2010-09-02 | 2010-09-30 | 2010-11-17 | 592817 | 0.490 | 9003516
3976 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003522 | This project will enhance the roadways by supplying, delivering & installing 324 native trees on Cicero Avenue, Crawford Avenue, Devon Avenue, Lincoln Avenue, Pratt Avenue, Touhy Avenue & McCormick Av | Transportation Enhancements | 2010-04-21 | 2011-05-09 | 2010-06-30 | 2011-05-18 | 140300 | 0.000 | 9003522
3977 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003524 | This project will extend the pavement life by widening, milling and resurfacing Center Road from Laraway Road to Sauk Trail in the Village of Frankfort (Northeastern Illinois). | Pavement Improvement | 2010-08-23 | 2010-10-19 | 2011-06-30 | 2012-01-11 | 1000000 | 0.760 | 9003524
3978 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003525 | This project will extend the pavement life by milling, patching and resurfacing 173rd St from Old Brennan Highway to Cicero Ave. in Country Club Hills, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-29 | 2010-04-16 | 2010-05-30 | 2010-04-30 | 180205.1 | 0.360 | 9003525
3979 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003526 | This project will extend the pavement life by resurfacing Raven Road from Seil Road to Valencia Drive in the Village of Shorewood, Will County (Northeastern Illinois). | Pavement Improvement | 2010-04-19 | 2010-05-12 | 2010-06-30 | 2010-09-20 | 143650 | 0.350 | 9003526
3980 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003528 | This project will provide for pedestrian safety by constructing a new Pedestrain path and bridge adjacent to Thornmeadow Rd. in Riverwoods, (Northeast Illinois). | Bridge Improvement | 2010-05-18 | 2010-06-08 | 2010-09-30 | 2011-08-02 | 969592.69 | 0.250 | 9003528
3981 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003529 | This project will provide for pedestrian safety by constructing a new sidewalk adjacent to IL Route 72 in West Dundee, IL , (Northeast Illinois). | Transportation Enhancements | 2010-05-07 | 2010-07-12 | 2010-08-30 | 2010-11-17 | 133630 | 0.130 | 9003529
3982 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003537 | This project will extend the pavement life by milling, patching and resurfacing 0.63 miles of Orchard Dr. in Park Forest, Illinois (Northeastern Illinois) | Pavement Improvement | 2010-03-30 | 2010-05-05 | 2010-06-30 | 2010-08-25 | 285017.97 | 0.670 | 9003537
3983 | ILLINOIS | Completed | C220 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 09 | 9003547 | This project will improve aesthetics by streetscaping 0.47 miles of US 41 including lighting, sidewalk repair, curb and gutter repair and resurfacing in Skokie, Illinois (Northeastern Illinois) | Transportation Enhancements | 2010-04-15 | 2010-09-13 | 2011-08-30 | 2011-11-05 | 790336 | 0.490 | 9003547
3984 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003549 | This project will improve aesthetics by planting trees and streetscaping along various routes including Roberts Rd, 111th St, Kean Ave, and 103rd St in Palos Hills, Illinois (Northeastern Illinois). | Transportation Enhancements | 2010-03-25 | 2010-03-17 | 2010-06-30 | 2011-05-14 | 150920 | 5.790 | 9003549
3985 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003550 | This project will extend the pavement life by milling, patching and resurfacing Batavia Road in the City of Warrenville (Norteastern Illinois). | Pavement Improvement | 2010-02-19 | 2010-04-15 | 2010-06-30 | 2010-07-26 | 534920 | 1.150 | 9003550
3986 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 05 | 9003556 | This project will extend the pavement life by resurfacing, curb and gutter replacement, sidewalk replacement and patching on Armitage Ave from Wolf Road to Mannheim Road in the Village of Northlake, Illinois (Northeastern Illinois). | Pavement Improvement | 2010-07-15 | 2010-09-07 | 2011-12-30 | 2010-12-16 | 450265.66 | 1.050 | 9003556
3987 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 06 | 9003569 | This project will extend the pavement life by resurfacing Biesterfield Rd from Rohlwing Rd to the I-290 Ramps in Elk Grove Village, IL (Northeastern Illinois) | Pavement Improvement | 2010-11-23 | 2011-04-01 | 2011-06-30 | 2011-11-04 | 313517 | 0.010 | 9003569
3988 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003574 | This project will improve safety by installing 0.31 miles of new lighting along Burnham Ave from Brainard Ave north to Burnham Ave bridge in Burnham, Cook County (Northeastern Illinois). | Safety/Traffic Management | 2010-03-31 | 2010-03-31 | 2011-06-30 | 2012-12-01 | 187783 | 0.080 | 9003574
3989 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003575 | This project will extend the life of the pavement by resurfacing 0.9 miles of Vincennes Rd from Halsted St. Thornton Rd in the Village of Phoenix in Cook County (Northeastern Illinois). | Pavement Improvement | 2010-08-09 | 2010-09-07 | 2011-06-30 | 2010-11-29 | 475000 | 0.530 | 9003575
3990 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | DU PAGE | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003576 | This project consists of improving safety and traffic enhancement by installing street lighting at the intersection of IL Route 83 and Plainfield Road in the Village of Willowbrook, DuPage County (Northeastern Illinois). | Safety/Traffic Management | 2010-05-18 | 2010-07-01 | 2010-07-30 | 2011-05-04 | 174489.43 | 0.010 | 9003576
3991 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003584 | City of Batavia will resurafce and will add curb & gutter & sidewalk replacement on Western Ave from Mckee St to Fabyan Parkway. | Pavement Improvement | 2010-09-02 | 2010-09-28 | 2010-10-30 | 2010-10-19 | 249468.15 | 0.720 | 9003584
3992 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003606 | This project will extend the pavement life by patching and resurfacing 0.29 miles of Wentworth/Atlantic Avenue from 142nd Street to 144th Street in Riverdale, IL (Northeastern Illinois) | Pavement Improvement | 2010-09-22 | 2010-10-04 | 2011-12-30 | 2011-08-16 | 158177.95 | 0.280 | 9003606
3993 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003608 | City of South Elgin will resurface and will add curb & gutter & sidewalk repair on Spring Street | Pavement Improvement | 2010-07-27 | 2010-10-12 | 2011-12-30 | 2010-12-20 | 235828.79 | 0.610 | 9003608
3994 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003616 | City of Hampshire will add new pavement on Dietrich Rd from US 20 to Hampshire. | Pavement Improvement | 2010-09-14 | 2010-09-30 | 2010-12-30 | 2010-12-06 | 115449.95 | 0.140 | 9003616
3995 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | MCHENRY | CHICAGO-NORTHWESTERN INDIANA (IN) | 16 | 9003635 | Mchenry County will improve safety and operations by adding turning lanes at the intersection of Three Oaks Rd and Silver Lake Road in the village of Cary. | Pavement Improvement | 2010-09-16 | 2010-10-21 | 2011-12-30 | 2011-12-30 | 300889 | 0.010 | 9003635
3996 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | LAKE | CHICAGO-NORTHWESTERN INDIANA (IN) | 08 | 9003640 | This project will extend the pavement life by milling, patching and resurfacing on FAU 184 (Hawthorne Dr) from Cedar Lake Road to Rollins Rd in Round Lake Beach (Northeast-Illinois) | Pavement Improvement | 2010-03-29 | 2010-05-03 | 2010-06-30 | 2010-12-23 | 163435 | 0.950 | 9003640
3997 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003644 | City of Elgin will add new pavement, curb & gutter, sidewalk repair on Big Timber Rd from McLean Blvd to IL 31. | Pavement Improvement | 2010-09-07 | 2010-09-20 | 2010-10-30 | 2011-06-21 | 324263 | 1.070 | 9003644
3998 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 04 | 9003645 | This project will extend the pavement life by resurfacing, curb and gutter, sidewalk and driveway replacement of 0.30 miles of Austin Blvd from Ogden Ave to 29th Street in the Cicero, Illinois (Northeastern Illinois). | Pavement Improvement | 2010-07-15 | 2010-07-15 | 2010-09-30 | 2010-12-08 | 536973 | 0.360 | 9003645
3999 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003646 | City of Campton Hills will add new pavement on McDonald Rd from Phar Lap Dr to Cloverfield Circle. | Pavement Improvement | 2010-09-22 | 2010-09-22 | 2010-11-30 | 2011-07-07 | 130813 | 0.890 | 9003646
4000 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003651 | This project will extend the pavement life by milling, patching and resurfacing 0.48 miles of Harwood Avenue in Homewood, Illinois (Northeastern Illinois). | Pavement Improvement | 2010-09-09 | 2010-09-27 | 2010-09-30 | 2010-10-16 | 112492 | 0.570 | 9003651
4001 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003652 | This project will extend the pavement life by milling, patching and resurfacing 0.65 miles of Harwood Avenue and Maple Road between Ashland Avenue and Dixie Highway in Homewood, Illinois (Northeastern Illinios). | Pavement Improvement | 2010-09-02 | 2010-10-05 | 2011-05-30 | 2011-04-23 | 193979 | 0.630 | 9003652
4002 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003662 | City ofAurora will add new pavement, curb & gutter & sidewalk replacemen on Indian Trail Dr from Highland Ave to Randall Rd. | Pavement Improvement | 2010-08-30 | 2010-09-01 | 2010-12-30 | 2011-12-12 | 70228 | 1.030 | 9003662
4003 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003663 | This project will provide for pedestrian safety by constructing a sidewalk along 119th St. between Pulaksi Rd. and Kostner Ave. in Alsip, IL. (Northeastern Illinois) | Safety/Traffic Management | 2010-08-25 | 2010-10-01 | 2010-11-30 | 2011-07-25 | 102513 | 0.500 | 9003663
4004 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003664 | This project will provide for pedestrian safety by streetscaping Roberts Road, including sidewalk replacement and landscaping from 99th Street to 87th Street in the City of Hickory Hills. (Northeastern Illinois) | Transportation Enhancements | 2011-02-08 | 2011-04-09 | 2011-05-30 | 2012-08-02 | 133000 | 1.640 | 9003664
4005 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 01 | 9003665 | This project will extend the pavement life by patching and resurfacing 88th Avenue from 159th Street to 171st Street in the Village of Orland Park, IL (Northeastern Illinois) | Pavement Improvement | 2010-10-22 | 2011-05-02 | 2011-06-30 | 2011-09-17 | 296000 | 1.500 | 9003665
4006 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003666 | City of Sugar Grove will resurface on Granart Rd from Whildin Rd to Dugan Rd. | Pavement Improvement | 2010-10-22 | 2010-04-30 | 2010-11-30 | 2011-09-03 | 146780 | 0.380 | 9003666
4007 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 13 | 9003667 | This project will provide for pedestrian safety by constructing a sidewalk along McCarthy Road between Woodcrest Lane and Walker Road. in Lemont, IL. (Northeastern Illinois) | Safety/Traffic Management | 2010-08-25 | 2011-05-20 | 2010-11-30 |  | 79545 | 0.360 | 9003667
4008 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 02 | 9003668 | This project will extend the pavement life by patching and resurfacing 1.17 miles of Prince Drive (I-94 frontage road) from 170st Street to Woodlawn East Avenue in the South Holland, IL (Northeastern Illinois) | Pavement Improvement | 2010-09-10 | 2010-12-01 | 2011-05-30 | 2011-08-07 | 424413.56 | 1.170 | 9003668
4009 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003669 | This project consists of improving safety and traffic enhancement by installing street lighting along 191st Street from 80th Avenue to Harlem Avenue in the Village of Tinley Park (Northeastern Illinois). | Safety/Traffic Management | 2010-06-17 | 2010-09-07 | 2010-10-30 | 2011-08-30 | 479199 | 0.150 | 9003669
4010 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003670 | This project consists of improving safety by installation of a modern roadway lighting system along Harlem Avenue (IL 43) from 71st Street to the North of 70th Street and also including the East and W | Safety/Traffic Management | 2010-10-27 | 2012-01-18 | 2011-05-30 |  | 133000 | 0.780 | 9003670
4011 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003671 | This project will extend the pavement life by patching and resurfacing 103rd Street from Austin Avenue to Central Avenue in Oak Lawn, IL (Northeastern Illinois) | Pavement Improvement | 2010-12-06 | 2011-04-30 | 2010-11-30 | 2011-10-12 | 133000 | 0.490 | 9003671
4012 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003672 | This project consists of improving safety by modernization of traffic signals including removal and replacement of signal heads, pedesrtian signal heads and pedestrian push buttons at the intersection | Safety/Traffic Management | 2010-11-18 | 2011-05-07 | 2010-11-30 | 2011-10-29 | 46190 | 0.010 | 9003672
4013 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | WILL | CHICAGO-NORTHWESTERN INDIANA (IN) | 11 | 9003675 | This project will extend the pavement life by patching, milling and resurfacing Burville Road from Dixie Highway to west of State Street in the Village of Crete (Northeastern Illinois). | Pavement Improvement | 2010-10-12 | 2011-04-16 | 2011-05-30 | 2011-07-05 | 361764 | 1.170 | 9003675
4014 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | COOK | CHICAGO-NORTHWESTERN INDIANA (IN) | 03 | 9003676 | This project will provide for pedestrian safety by reconstructing a sidewalk including ADA ramps along 103rd Street between 88th Avenue and Harlem Avenue (IL 43) in Palos Hills, IL. (Northeastern Illinois) | Safety/Traffic Management | 2010-10-18 | 2011-03-30 | 2010-11-30 | 2011-05-14 | 129862.49 | 2.010 | 9003676
4015 | ILLINOIS | Completed | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KANE | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003679 | City of Geneva will add new pavement and do sidewalk repair on Anderson Blvd from IL Route 38 to Gray St. | Pavement Improvement | 2010-09-24 | 2010-10-02 | 2010-11-30 | 2010-11-13 | 294314 | 0.650 | 9003679
4016 | ILLINOIS | Underway | C230 | Highway Infrastructure Investment Grant | ILLINOIS | KENDALL | CHICAGO-NORTHWESTERN INDIANA (IN) | 14 | 9003686 | City of Montgomery will improve the pavement by resurfacing, patching, curb & gutter & sidewalk replacement on Lakewood Creek Dr from Avalon Ln to US 30. | Pavement Improvement | 2010-09-22 | 2010-09-22 | 2010-11-30 |  | 280421.9 | 0.580 | 9003686
4017 | ILLINOIS | Completed | C240 | Highway Infrastructure Investment Grant | ILLINOIS | ST CLAIR | ST. LOUIS (MO)-IL | 12 | 9251010 | This project will extend the pavement life by milling, patching and resurfacing in Belleville, Illinois (Southwestwest Illinios). | Pavement Improvement | 2009-05-11 | 2009-06-03 | 2009-08-30 | 2009-07-02 | 170311.96 | 0.700 | 9251010
4018 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0003610 | This project will add turn lanes, widen the intersection, and install a new signal at SR 56 and Dubois County Rd 500W. | Safety/Traffic Management | 2009-06-18 | 2009-08-03 | 2010-06-30 | 2010-06-29 | 99623.96 | 0.010 | 0003610
4019 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART |  | 03 | 0013180 | This project will improve drainage by replacing the structure on SR 15 over a branch of Preston Miles' ditch in Elkhart County. | Pavement Improvement | 2009-06-18 | 2009-07-14 | 2009-10-23 | 2009-11-11 | 1041816.68 | 0.010 | 0013180
4020 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0014130 | This project will improve drainage by replacing the structure on US 41 over Jane Feddeler Ditch in Lake County. | Pavement Improvement | 2009-05-13 | 2009-06-24 | 2009-08-31 | 2009-08-22 | 576957.31 | 0.010 | 0014130
4021 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SULLIVAN |  | 08 | 0100974 | This project is a bridge rehabilitation where the wearing surface of the deck will be removed and repalced on SR 154 at the bridge over Turman Creek, 2.17 miles W of SR 63 in Sullivan county. | Bridge Improvement | 2010-03-24 | 2010-04-24 | 2010-11-30 | 2010-11-10 | 591309.71 | 0.010 | 0100974
4022 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | VANDERBURGH | EVANSVILLE (KY) | 08 | 0101271 | This is a road reconstruction project that will widen the road on Oak Hill Rd from US 41 to 0.32 mi N of SR 62 at Pigeon Creek in Vanderburgh county. This is Phase one of a multi-phase improvement to increase capaicty of oak Hill Road. | Pavement Improvement | 2010-01-28 | 2010-02-26 | 2011-06-30 | 2011-07-18 | 5016264.34 | 3.000 | 0101271
4023 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HENRY |  | 06 | 0101426 | This project will improve the surface and rebuild sections of the bridge on SR 109 over I-70 in Henry County. | Bridge Improvement | 2009-07-15 | 2009-07-15 | 2010-10-29 | 2010-10-29 | 1773465.75 | 0.010 | 0101426
4024 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0101500 | This project will improve drainage by replacing the structure on US 6 over Kiefer Ditch in Elkhart County. | Pavement Improvement | 2009-09-09 | 2010-07-08 | 2010-10-01 | 2010-09-30 | 495073.4 | 0.100 | 0101500
4025 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0101530 | This project will add turn lanes and imrpove the intersection at US 33 and SR 109 in Noble County. | Pavement Widening | 2009-06-22 | 2009-08-31 | 2009-11-20 | 2009-11-20 | 376701.01 | 0.100 | 0101530
4026 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0173058 | This project will plant wildflowers and native vegetation along US 41at US 41 and Gibson County Road 550. | Transportation Enhancements | 2009-07-21 | 2009-08-24 | 2010-08-01 | 2009-12-02 | 88281.25 | 0.670 | 0173058
4027 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE, STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0196049 | This project will replace the pavement on US 41 in Lake County from 1 mile south of US12/US20 to north of US12/20 and includes sewer replacement and modernization to provide a new road. | Pavement Improvement | 2010-05-05 | 2010-05-19 | 2010-10-01 | 2010-12-10 | 2322827 | 1.010 | 0196049
4028 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0200067 | This project will improve drainage by replacing the structure over Swygman ditch on US 24 in White County. | Safety/Traffic Management | 2009-11-17 | 2010-01-15 | 2010-04-30 | 2010-04-27 | 47576.92 | 0.100 | 0200067
4029 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0200071 | This project will improve drainage by replacing the structure on US 24 over Winters ditch in White County. | Safety/Traffic Management | 2009-11-17 | 2010-01-15 | 2010-04-30 | 2010-04-27 | 65401 | 0.100 | 0200071
4030 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | UNION |  | 06 | 0200195 | This project will repair and restore the pavement and replace signs on US 27 from the Ohio State line north 3.6 miles in Union county. | Safety/Traffic Management | 2009-04-15 | 2009-08-05 | 2012-02-10 | 2011-11-16 | 24857.51 | 3.560 | 0200195
4031 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0200364 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Safety/Traffic Management | 2009-06-17 | 2009-07-16 | 2010-08-31 | 2010-09-17 | 37742.17 | 0.020 | 0200364
4032 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY, JOHNSON |  | 05 | 0200539 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | Safety/Traffic Management | 2009-05-12 | 2009-07-22 | 2011-07-11 | 2011-08-04 | 26276.41 | 11.550 | 0200539
4033 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 0200606 | This project will extend the traffic management system of closed circuit TV used for traffic management in Indianapolis. | Safety/Traffic Management | 2009-06-11 | 2009-07-16 | 2010-11-15 | 2010-10-15 | 3592423.77 | 18.420 | 0200606
4034 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0200884 | This project will add lanes to SR 1 from I-69 in Allen County to Tonkel Road. | Pavement Widening | 2009-06-01 | 2009-07-15 | 2011-08-13 | 2011-09-29 | 383532.87 | 0.100 | 0200884
4035 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0200890 | This project will improve drainage by replacing the small drainage structure on US 27 over Swartz ditch, 2.9 miles north of SR 218 in Adams County. | Pavement Improvement | 2010-01-21 | 2010-06-22 | 2010-10-30 | 2010-10-20 | 652513.98 | 0.100 | 0200890
4036 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0200894 | This project will improve drainage by replacing the small drainage structure on SR 301 over Vera Cruz Sewer, 0.6 miles north of SR 116 in Wells County. | Pavement Improvement | 2009-08-20 | 2010-05-03 | 2010-08-21 | 2010-06-04 | 228238.4 | 0.010 | 0200894
4037 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0200918 | This is Bridge Replacement, Concrete on SR427, Bridge over Fish Creek, 3.92 miles N of SR 1 | Bridge Replacement | 2010-12-14 | 2011-03-10 | 2011-10-31 | 2011-10-27 | 526607.52 | 0.040 | 0200918
4038 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WABASH |  | 05 | 0200919 | This project will improve drainage by replacing the small drainage structure on SR 13 over Sharp ditch , 1.8 miles north of US 24 in Wabash County. | Pavement Improvement | 2009-04-17 | 2009-06-10 | 2009-08-07 | 2009-08-26 | 397717.32 | 0.010 | 0200919
4039 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0200932 | This is a bridge rehabilitation project, on SR 101 on the bridge over Maumee River, 1.08 miles N of US 24 in Allen county , where the deck surface is removed and replaced to extend the life of the bridge deck. | Bridge Improvement | 2009-12-11 | 2010-03-18 | 2010-08-21 | 2010-06-29 | 732889.94 | 0.010 | 0200932
4040 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0200934 | This project will replace the existing bridge with a new wider structure for Dekalb county road 11A over I-69, 2.8 miles S of SR 8. | Bridge Improvement | 2009-11-18 | 2010-04-01 | 2010-11-30 | 2011-05-05 | 3177881.13 | 0.010 | 0200934
4041 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0200987 | This is a trail project to proviide facilities for pedestrians and bicycles project in the city of Bloomington Jackson Creek Trail in Monroe county. This is phase one of a multi phase project and uses enhancement funds. | Transportation Enhancements | 2010-02-22 | 2010-03-31 | 2010-07-16 | 2010-10-14 | 374753.06 | 0.612 | 0200987
4042 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BENTON |  | 01 | 0201203 | This project will improve the surface and rebuild sections of the bridge on US 41 over KB&S Railroad and US 52 in Benton County. | Bridge Replacement | 2009-04-29 | 2009-05-11 | 2009-11-15 | 2010-04-22 | 1672180.92 | 0.040 | 0201203
4043 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BENTON |  | 01 | 0201204 | This project will improve the surface and rebuild sections of the bridge on US 41 over KB&S Railroad and US 52 in Benton County. | Bridge Replacement | 2009-04-29 | 2009-05-11 | 2009-11-15 | 2010-04-22 | 1131818.29 | 0.040 | 0201204
4044 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 0201213 | This project will improve the surface and rebuild sections of the bridge on SR 75 over Kilmore Creek in Clinton County. | Bridge Improvement | 2009-05-27 | 2009-06-15 | 2009-08-31 | 2009-10-02 | 438235.02 | 0.010 | 0201213
4045 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | OHIO |  | 09 | 0201245 | This project will improve the surface and rebuild sections of the bridge on SR 56 over Laughery Creek in Ohio County. | Bridge Improvement | 2009-05-16 | 2009-07-31 | 2011-08-01 | 2011-08-19 | 5423974.97 | 0.180 | 0201245
4046 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0242029 | This project will add turn lanes, widen the intersection, and install a new signal at SR 56 and Dubois County Rd 500W. | Pavement Widening | 2009-06-18 | 2009-08-03 | 2010-06-30 | 2010-06-29 | 639905.85 | 0.010 | 0242029
4047 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | DE KALB, ALLEN | FORT WAYNE | 03 | 0300084 | This project will improve sections and extend the life of I-69 from 0.86 miles North of SR 1 to 9.87 miles North of SR 1 with a pavement surface overlay. | Pavement Improvement | 2009-08-18 | 2009-08-24 | 2009-10-31 | 2009-11-11 | 2474090.6 | 8.680 | 0300084
4048 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0300092 | This project will improve safety and extend the life of the bridge(s) on County Road 68 over I-69 in DeKalb County. | Bridge Improvement | 2009-04-02 | 2009-04-13 | 2009-08-31 | 2009-08-18 | 438945.26 | 0.100 | 0300092
4049 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0300093 | This project will improve safety and extend the life of the bridge(s) on County Road 60 over I-69 in DeKalb County. | Bridge Improvement | 2009-04-02 | 2009-04-13 | 2009-08-31 | 2009-08-18 | 307061.66 | 0.100 | 0300093
4050 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0300556 | This project will build a new bridge over Richland Creek on SR54, 1.32 miles E US 231 in Green county, east of Bloomfield to improve drainage and load carrying capacity. | New Bridge Construction | 2010-03-24 | 2010-04-28 | 2011-11-05 | 2011-11-02 | 667110.13 | 0.010 | 0300556
4051 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300758 | This is a safety project, at 121st Street and US 41 in Hammond, Lake county, to modernize the traffic signals . | Safety/Traffic Management | 2010-05-05 | 2010-05-19 | 2010-10-01 | 2010-12-10 | 66022.64 | 0.010 | 0300758
4052 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300759 | This is a safety project, at 119st Street and US 41 in Hammond, Lake county, to modernize the traffic signals in conjunction with the street modernization project. | Safety/Traffic Management | 2010-05-05 | 2010-05-19 | 2010-10-01 | 2010-12-10 | 59803.13 | 0.010 | 0300759
4053 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300760 | This is a safety project ,at 117th Street at US 41 in Lake Co perform Traffic Signals Modernization work in conjunction with the ARRA street modernization contract. | Safety/Traffic Management | 2010-05-05 | 2010-05-19 | 2010-10-01 | 2010-12-10 | 39413.97 | 0.350 | 0300760
4054 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0300761 | This is a Safety project,at US 12/20 (Indianapolis Blvd.)/114th Street (Sec V); to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-05-05 | 2010-05-19 | 2010-10-01 | 2010-12-10 | 107604.5 | 0.040 | 0300761
4055 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0300942 | This project will rebuild the US 20 and I-69 interchange in Steuben county to improve traffic flow. | Pavement Widening | 2009-06-01 | 2009-06-12 | 2010-10-15 | 2010-10-12 | 3676824.73 | 0.690 | 0300942
4056 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0301057 | This project will improve safety and extend the life of the bridge(s) on SR 10 over Clarence Baker Ditch in Marshall County. | Bridge Improvement | 2009-04-17 | 2009-06-08 | 2009-11-22 | 2009-07-16 | 214456.84 | 0.010 | 0301057
4057 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0301140 | This is a Reconstruction (no added capacity) project, at SR 19 - Branch of Armey Ditch, 11.1 miles N of US 30; to perform Small Structure Replacement work. | Pavement Improvement | 2009-12-30 | 2010-06-15 | 2010-08-13 | 2010-07-22 | 337040.39 | 0.100 | 0301140
4058 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0301152 | This is a Small Structure project, at Over Dennis Ditch, 1.7 miles N of Lafayette Center interchange; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-09-20 | 2010-10-02 | 2010-10-25 | 161900 | 0.100 | 0301152
4059 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PARKE |  | 08 | 0322001 | This project will improve drainage by repairing pipes in Parke County 3 miles South of SR 234. | Pavement Improvement | 2009-07-22 | 2009-09-11 | 2010-08-30 | 2010-08-27 | 679684.15 | 0.130 | 0322001
4060 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0400133 | This project will replace and restore the pavement on Michigan Road in Jefferson County near the Town of Madison. | Pavement Improvement | 2009-07-15 | 2009-09-09 | 2010-06-07 | 2010-09-20 | 1233716 | 0.750 | 0400133
4061 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 04 | 0400322 | This project will improve the surface and rebuild sections of the bridge on SR 37 over the abandoned Railroad, 3.5 miles South of SR 45 in Monroe County. | Bridge Improvement | 2009-05-13 | 2009-06-12 | 2010-06-26 | 2010-05-10 | 697938.5 | 0.010 | 0400322
4062 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0400324 | This project will improve the surface and rebuild sections of the bridge on SR 37 over the abandoned Railroad, 3.5 miles South of SR 45 in Monroe County. | Bridge Improvement | 2009-05-13 | 2009-06-12 | 2010-06-26 | 2010-05-10 | 671638.17 | 0.010 | 0400324
4063 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | OWEN |  | 08 | 0400568 | This project will correct a slide condition along SR 243 south of the Owen / Putnam County line. | Pavement Improvement | 2009-07-22 | 2009-09-24 | 2010-09-30 | 2010-06-30 | 441058.81 | 0.070 | 0400568
4064 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT, HUNTINGTON |  | 05 | 0400614 | This project will improve sections and extend the life of I-69 from 1.84 mi S of Huntington Co Ln to 1.55 mi South of SR 124 with a pavement surface overlay. | Pavement Improvement | 2009-07-07 | 2009-08-12 | 2009-10-24 | 2009-10-06 | 2012104.66 | 7.320 | 0400614
4065 | INDIANA | Underway | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0400711 | This is a reconstruction project, at Cline Ave from Ridge Rd to 45th St., to perform intersection improvements adding turn lanes for better traffic flow and safety. | Pavement Improvement | 2010-04-15 | 2010-04-27 | 2011-05-31 |  | 4056240.33 | 0.860 | 0400711
4066 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0400997 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment of SR 25. | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2012-07-27 | 1288872.55 | 0.010 | 0400997
4067 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0400999 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment of SR 25. | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2012-07-27 | 641003.28 | 0.120 | 0400999
4068 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0401000 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment of SR 25. | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2012-07-27 | 1193676.61 | 0.120 | 0401000
4069 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE, BENTON |  | Multiple | 0401007 | This project will improve sections and extend the life of US 52 in Benton county from SR 352 to US 231 with a asphalt preventive maintenance surface overlay. | Pavement Improvement | 2009-03-24 | 2009-04-15 | 2009-11-15 | 2009-11-23 | 3823682.05 | 11.340 | 0401007
4070 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0401105 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge over Perry-Oakley Ditch, 1.09 miles N of US 27; to perform Bridge Rehabilitation Or Repair work. | Bridge Improvement | 2010-03-25 | 2010-05-10 | 2010-10-30 | 2010-10-21 | 207259.77 | 0.100 | 0401105
4071 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0401139 | This project will improve the surface and rebuild sections of the bridge on SR 258 over White River in Jackson County. | Bridge Improvement | 2009-06-05 | 2009-06-08 | 2009-10-16 | 2009-09-15 | 996973.79 | 0.010 | 0401139
4072 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0401149 | This is a Small Structure project, at SR 39 - 1.25 miles N of E jct of SR 10; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-06-08 | 2010-06-30 | 2010-07-14 | 43140 | 0.010 | 0401149
4073 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0401150 | This is a Small Structure project, at SR 39 - 2.25 miles N of E jct of SR 10; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-06-08 | 2010-06-30 | 2010-07-14 | 37500 | 0.010 | 0401150
4074 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | DE KALB, ALLEN | FORT WAYNE | 03 | 0401216 | This project will improve drainage by repairing pipes on I-69 from 0.86 miles North of SR 1 to 9.87 miles North of SR 1 in Allen and Dekalb Counties. | Pavement Improvement | 2009-08-18 | 2009-08-24 | 2009-10-31 | 2009-11-11 | 976353.5 | 8.680 | 0401216
4075 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0401287 | This project will beautify the roadside by planting native grasses and wildflowers along US 52 near the SR 443 bridge and Happy Hollow Road in West Lafayette. | Transportation Enhancements | 2009-06-09 | 2009-07-01 | 2011-06-30 | 2009-12-07 | 30682.26 | 0.010 | 0401287
4076 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0426013 | This project will improve sections and extend the life of US 50 from SR 37 to "E" street in Bedford, Lawrence county with a preventive maiantenance asphalt overlay. | Pavement Improvement | 2009-03-23 | 2009-04-20 | 2009-08-29 | 2009-08-20 | 976603.3 | 1.770 | 0426013
4077 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0431065 | This project will plant wildflowers and native vegetation along SR 67 south of Bruceville in Knox County. | Transportation Enhancements | 2009-07-21 | 2009-08-24 | 2010-08-01 | 2010-05-19 | 29733.7 | 0.280 | 0431065
4078 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0452010 | This project will add lanes to SR 1 from I-69 in Allen County to Tonkel Road. | Pavement Widening | 2009-06-01 | 2009-07-15 | 2011-08-13 | 2011-09-29 | 11098193.76 | 1.850 | 0452010
4079 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0500283 | This project will improve sections and extend the life of SR 39 in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-08-18 | 2009-08-29 | 2009-11-15 | 2009-10-31 | 1275218.04 | 7.110 | 0500283
4080 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0500597 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment of SR 25. | New Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2012-07-27 | 25154875.12 | 0.120 | 0500597
4081 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0500819 | This project will build a new the bike and pedestrian facilities on Tracy Trail from Summerfield Park to Craig Park in the Greenwood area in Johnson county. | Transportation Enhancements | 2009-12-16 | 2010-03-22 | 2010-10-29 | 2010-11-05 | 829013 | 0.010 | 0500819
4082 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | VANDERBURGH | EVANSVILLE (KY) | 08 | 0500938 | This project will plant wildflowers and native vegetation along I-164 at I-164 and SR 62 in Vanderburgh County. | Transportation Enhancements | 2009-07-21 | 2009-08-21 | 2010-08-01 | 2010-04-16 | 51846.75 | 0.170 | 0500938
4083 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0500965 | This project will replace and restore the pavement on Brown Avenue, from Wabash Avenue to Locust Street, in Vigo County. | Pavement Widening | 2009-09-15 | 2009-10-06 | 2010-06-30 | 2011-03-24 | 1536019.28 | 0.380 | 0500965
4084 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0501203 | This is a Maintenance project for HMA Overlay, Preventive Maintenance on I469, From I-69 N Jct to 4.25 miles E of I-69 (Bridge over Wheelock Road). | Pavement Improvement | 2010-12-22 | 2011-05-19 | 2011-10-15 | 2011-08-17 | 892857.77 | 4.260 | 0501203
4085 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | BOONE | INDIANAPOLIS | 04 | 0501249 | This is a Maintenance Resurfacing project, at I-65 to I 465; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-02-19 | 2010-05-24 | 2010-10-30 | 2010-09-01 | 2300071.17 | 4.130 | 0501249
4086 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0565014 | This project will replace a large culvert with a new bridge on SR54 as part of contract SB-30551 reconstruction project at the bridge over Ritter Ditch, East of US 231 in Greene County. | Pavement Widening | 2010-03-24 | 2010-04-28 | 2011-11-05 | 2011-11-02 | 923845.75 |  | 0565014
4087 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLAY |  | 08 | 0600085 | This project will improve sections and extend the life of SR 246 from SR 159 to SR 157 in Clay County with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-05-11 | 2009-06-30 | 2009-07-01 | 815276.57 | 6.620 | 0600085
4088 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0600233 | This project will improve sections and extend the life of Sr 3 with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-06-02 | 2009-08-07 | 2009-07-23 | 1318239.42 | 10.940 | 0600233
4089 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD | KOKOMO | 05 | 0600338 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Construction | 2009-06-01 | 2009-07-10 | 2011-06-15 | 2011-06-15 | 8918680.32 | 2.000 | 0600338
4090 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0600501 | This project repairs a drainage pipe on SR 39 , 1.48 miles south of SR 8 in Starke county by re-lining the culver instead of replacing it. | Other | 2010-04-14 | 2010-06-08 | 2010-06-30 | 2010-07-14 | 37500 | 0.010 | 0600501
4091 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD | KOKOMO | 05 | 0600566 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Bridge Construction | 2009-06-01 | 2009-07-10 | 2011-06-15 | 2011-06-15 | 1734801.49 | 0.010 | 0600566
4092 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0600605 | This project will improve sections and extend the life of SR 48 from Curry Pike to E of SR 37 in Bloomington with a pavement surface overlay. | Pavement Improvement | 2009-04-15 | 2009-05-08 | 2009-08-02 | 2009-08-17 | 512306.74 | 0.560 | 0600605
4093 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0600651 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | New Construction | 2009-05-26 | 2009-06-23 | 2010-11-15 | 2012-04-02 | 9669603.35 | 0.010 | 0600651
4094 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0600653 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | Bridge Replacement | 2009-05-26 | 2009-06-23 | 2010-11-15 | 2012-04-02 | 2431747.71 | 0.070 | 0600653
4095 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0600654 | This is part of the I-465 added lanes and reconstruction project on the Westside of Indianapolis and will rebuild the US136 / I-465 interchange. | Bridge Replacement | 2009-05-26 | 2009-06-23 | 2010-11-15 | 2012-04-02 | 2457379.37 | 0.010 | 0600654
4096 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE, BROWN |  | 09 | 0600667 | This is a project repairs drainage pipes under SR 46 in various locations in Seynour district by relining the old culverts instead of replacing them. | Safety/Traffic Management | 2010-03-01 | 2010-03-26 | 2010-07-30 | 2010-05-25 | 144294.15 | 15.000 | 0600667
4097 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0600803 | This project will improve drainage by replacing the structure on US 231, 3 miles South of the South junction with SR 32 in Montgomery County. | Pavement Improvement | 2009-03-24 | 2009-05-18 | 2009-06-13 | 2009-06-09 | 45853.99 | 0.200 | 0600803
4098 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | OWEN |  | 08 | 0621004 | This is a bridge replacement at the bridge over Meadow Brook Creek on US 231 south of SR 46 in Owen county to replace a deficient bridge | Bridge Replacement | 2010-04-09 | 2010-09-27 | 2010-09-17 | 2011-04-18 | 620500 | 0.010 | 0621004
4099 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY, JOHNSON |  | Multiple | 0684011 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | Pavement Widening | 2009-05-12 | 2009-07-22 | 2011-07-11 | 2011-08-04 | 13291723.99 | 11.280 | 0684011
4100 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0710027 | This proejct will extend the pavement life on SR 23 in St Joseph county from SR 933 to Campeau St ; by doing asphalt resurface preventive maintenance work. | Pavement Improvement | 2010-02-22 | 2010-03-29 | 2010-07-31 | 2010-06-30 | 874458 | 2.190 | 0710027
4101 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710031 | This project will improve sections and extend the life of US 20 in East Chicago with a pavement surface overlay. | Pavement Improvement | 2009-06-17 | 2009-07-21 | 2009-09-30 | 2009-11-21 | 1641443.95 | 2.560 | 0710031
4102 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710034 | This project will improve the pavement on SR 149 from the junstion of SR 130 to the junction of US 20. | Pavement Improvement | 2009-04-08 | 2009-05-04 | 2009-11-13 | 2009-07-27 | 1362731.25 | 5.130 | 0710034
4103 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0710040 | This project will improve sections and extend the life of SR-23 from SR 4 to Olive Street in St Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-06-05 | 2009-08-14 | 2009-11-01 | 2009-10-16 | 1593244.25 | 11.790 | 0710040
4104 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PULASKI |  | 02 | 0710042 | This project will improve sections and extend the life of US 35 from SR 14 to SR 10 in Pulaski County with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-05-18 | 2009-10-16 | 2009-08-05 | 1407322.75 | 10.030 | 0710042
4105 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0710043 | This project will improve sections and extend the life of US 24 from the north junction with US 35 to the south junction with US 35 and on SR 29 from US 24 to Burlington Ave. near Logansport in Cass County with a pavement surface overlay. | Pavement Improvement | 2009-03-23 | 2009-05-07 | 2009-07-31 | 2009-07-29 | 1651219.54 | 1.610 | 0710043
4106 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH |  | 02 | 0710044 | This is a Maintenance Resurfacing project , From Georgia St in Walkerton to US 31 to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-03-04 | 2010-06-15 | 2010-08-31 | 2010-08-31 | 2885743.46 | 9.240 | 0710044
4107 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0710046 | This project will extend the pavement lief on SR 10 - from SR 110 to US 231 by doing asphalt resurface preventive maintenance work. | Pavement Improvement | 2010-04-08 | 2010-04-23 | 2010-06-18 | 2010-06-15 | 647470.4 | 6.210 | 0710046
4108 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710053 | This project will improve sections and extend the life of US 30 in Lake County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-02 | 2009-11-15 | 2010-05-11 | 3113611.16 | 5.390 | 0710053
4109 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0710054 | This project will improve sections and extend the life of US 41 from US 231 to 77th Ave with a pavement surface overlay. | Pavement Improvement | 2009-08-27 | 2009-09-04 | 2009-10-31 | 2009-11-16 | 1668661.62 | 3.990 | 0710054
4110 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE |  | 01 | 0710058 | This project will improve sections and extend the life of SR 53 from 93rd Ave to South of 73rd Ave with a pavement surface overlay. | Pavement Improvement | 2009-05-13 | 2009-08-03 | 2009-10-16 | 2009-10-12 | 891077.64 | 2.430 | 0710058
4111 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0710074 | This project will stop erosion and correct a slide occurring on the west side of US 50 south of the East Fork White River Bridge in lawrence County. | Safety/Traffic Management | 2009-06-04 | 2009-07-23 | 2009-08-14 | 2009-08-05 | 162340.8 | 0.100 | 0710074
4112 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0710107 | This project will improve safety and extend the life of the bridge(s) on Hursh Road over I-69 in Allen County. | Bridge Improvement | 2009-04-02 | 2009-04-13 | 2009-08-31 | 2009-08-18 | 277824.96 | 0.010 | 0710107
4113 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0710108 | This is a preventive maintenance resurfacing project, on SR 57 - From 1.32 miles North of junction of US 50/US 150 to the sounth junction of SR 58 to do a thin asphalt resurface to extend the life of the pavment in Daviess county | Pavement Improvement | 2009-11-18 | 2010-02-25 | 2010-10-01 | 2010-09-30 | 3378948.72 | 38.320 | 0710108
4114 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0710115 | This project will extend the service life of the pavement on I-65, 2 mile north of US 321 to north of SR 14 in Jasper county with a preventive maintenance resurfacing project. | Pavement Improvement | 2009-09-15 | 2009-10-22 | 2010-08-20 | 2010-07-22 | 3009802.03 | 9.750 | 0710115
4115 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0710141 | This project will improve safety and extend the life of the bridge(s) on I-69 over Wabash River in Huntington County. | Bridge Improvement | 2009-05-13 | 2009-07-07 | 2009-10-31 | 2010-08-06 | 1452773.4 | 0.040 | 0710141
4116 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0710144 | This project will install new cable barrier in the median along I-69 in Dekalb County to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-05-16 | 2009-08-05 | 2009-10-31 | 2009-10-14 | 378646.31 | 4.320 | 0710144
4117 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VIGO, HENDRICKS, MORGAN |  | Multiple | 0710147 | This project will install new cable barrierin the median on I-70 in Vigo, Hendricks, and Morgan Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-06-10 | 2009-07-23 | 2009-09-12 | 2009-10-20 | 1038142.84 | 4.480 | 0710147
4118 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS, MARION |  | Multiple | 0710148 | This project will install new cable barrier in the median along I-74 in Hendricks and Marion Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-04-29 | 2009-06-04 | 2009-07-31 | 2009-07-31 | 546197.09 | 7.780 | 0710148
4119 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK, SHELBY, JOHNSON, JACKSON |  | Multiple | 0710150 | This project will install new cable guardrail in the median along I-65 in Johnson and Shelby Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-06-15 | 2009-06-26 | 2009-10-31 | 2009-10-21 | 3562796.08 | 89.630 | 0710150
4120 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD |  | 09 | 0710151 | This project will install new cable guardrailin the median along I-64 in Floyd County to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-06-15 | 2009-06-26 | 2009-10-31 | 2009-10-21 | 247197.71 | 9.840 | 0710151
4121 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK, FLOYD |  | 09 | 0710152 | This project will install new cable guardrail in the median along I-265 in Clark and Floyd Counties to prevent crossover head-on collisions. | Safety/Traffic Management | 2009-06-15 | 2009-06-26 | 2009-10-31 | 2009-10-21 | 465639.47 | 12.030 | 0710152
4122 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0710163 | This project will improve sections and extend the life of I-465 in Marion county with a pavement surface overlay from 3.23 miles North of I-74 to 5.12 miles North of I-74. | Pavement Improvement | 2009-06-16 | 2009-07-30 | 2009-11-15 | 2009-09-30 | 1432396.31 | 1.900 | 0710163
4123 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SWITZERLAND |  | 09 | 0710169 | This project will improve sections and extend the life of SR 56 from Oday Road to Rio Vista Lane in Switzerland county with a pavement surface overlay. | Pavement Improvement | 2009-10-07 | 2010-05-11 | 2010-08-13 | 2010-08-09 | 2096128.11 | 21.050 | 0710169
4124 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0710203 | This is a Safety project, at Parkside School sidewalk - This is a 2006 Safe Routes to School (SRTS) project that beyond the avaialbe funding of the SRTS program that will provide sidewalks to Parkside | Safety/Traffic Management | 2009-11-30 | 2010-04-26 | 2010-06-19 | 2010-06-18 | 159604.78 | 0.010 | 0710203
4125 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0710285 | This project will extend the pavement life on SR 157 from north of US 231 to the jct with SR 48 in Greene county by doing asphalt resurface with 2 layers | Pavement Improvement | 2009-10-14 | 2009-10-21 | 2009-11-15 | 2009-11-14 | 474251.94 | 2.410 | 0710285
4126 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS, KNOX |  | 08 | 0710390 | This project will improve sections and extend the life of SR 58 from SR 67 to SR 57 in Knox and Daviess Counties with a pavement surface overlay. | Pavement Improvement | 2009-03-23 | 2009-07-08 | 2009-09-20 | 2009-09-17 | 886313.48 | 6.390 | 0710390
4127 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0710394 | This project will improve sections and extend the life of US 231 from just north of US 136 in Crawfordsville to 1/2 mile north of I-74 in Montgomery County with a pavement surface overlay. | Pavement Improvement | 2009-06-03 | 2009-06-23 | 2009-11-06 | 2009-12-05 | 2918726.09 | 3.130 | 0710394
4128 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT, JACKSON |  | 09 | 0710432 | This project will improve sections and extend the life of US 31 from SR 56 to SR 250 in Jackson and Scott Counties with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-04-03 | 2009-11-16 | 2009-09-14 | 1526188.61 | 12.970 | 0710432
4129 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) |  | 0710470 | This project will install new signal loop detectors to improve traffic flow at 5 intersection along US 30 in Northwest Indiana | Safety/Traffic Management | 2009-04-14 | 2009-05-29 | 2009-08-31 | 2009-11-14 | 350684.29 | 0.020 | 0710470
4130 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK, MADISON |  | Multiple | 0710492 | This project will improve sections and extend the life of SR 9 in Hancock and Madison Counties with a pavement surface overlay. | Pavement Improvement | 2009-06-02 | 2009-07-10 | 2009-08-28 | 2009-08-28 | 1556750 | 10.810 | 0710492
4131 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0710502 | This project will improve sections and extend the life of SR 3 from South junction with SR 7 South of Vernon to US 50 with a pavement surface overlay. | Pavement Improvement | 2009-05-13 | 2009-06-20 | 2009-08-31 | 2009-08-14 | 528503.93 | 1.580 | 0710502
4132 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE | CHICAGO-NORTHWESTERN INDIANA (IL) |  | 0710510 | This project will install new signal loop detectors to improve traffic flow at 5 intersection along US 30 in Northwest Indiana | Safety/Traffic Management | 2009-04-29 | 2009-05-18 | 2009-08-31 | 2009-10-22 | 259019.3 | 0.020 | 0710510
4133 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK |  | 05 | 0710541 | This project will improve sections and extend the life of US 40 with a pavement surface overlay. | Pavement Improvement | 2009-06-02 | 2009-06-27 | 2009-08-07 | 2009-08-06 | 820500 | 3.120 | 0710541
4134 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI |  | 05 | 0710581 | This project will improve the surface and rebuild sections of the bridge on US 31 over the abandoned CSX Railroad, 1 miles South of US 50 in Ohio County. | Bridge Replacement | 2009-04-17 | 2009-04-22 | 2010-06-26 | 2009-11-22 | 302275.53 | 0.010 | 0710581
4135 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI |  | 05 | 0710582 | This project will improve the surface and rebuild sections of the bridge on US 31 over the abandoned CSX Railroad, 1 miles South of US 50 in Ohio County. | Bridge Replacement | 2009-04-17 | 2009-04-22 | 2010-06-26 | 2009-11-22 | 725926.81 | 0.010 | 0710582
4136 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON, BOONE |  | 04 | 0710622 | This project will improve sections and extend the life of I-65 with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-04-20 | 2009-10-31 | 2009-10-30 | 4238380.65 | 9.780 | 0710622
4137 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0710650 | This project will patch deteriorated pavement areas and seal cracks on SR 37 near Mitchell. | Pavement Improvement | 2009-03-31 | 2009-05-05 | 2009-09-18 | 2009-06-30 | 398694.16 | 8.010 | 0710650
4138 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0710670 | This project will improve sections and extend the life of US 31 from SR 252 to Youngs Creek Bridge in Johnson county with a pavement surface overlay. | Pavement Improvement | 2009-08-18 | 2010-03-24 | 2010-08-13 | 2010-07-15 | 1567134.24 | 12.570 | 0710670
4139 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0710694 | This project will improve sections and extend the life of SR 56 in Washington County with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-04-02 | 2009-08-01 | 2009-07-23 | 989946.05 | 9.870 | 0710694
4140 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0710700 | This is a Maintenance Resurfacing project, at US 50 - 6.08 miles W of SR 241 to 1.88 miles E of SR 241; to perform PCCP Cleaning and Sealing Joints work. | Pavement Improvement | 2009-10-23 | 2010-04-01 | 2010-08-28 | 2010-08-18 | 640854.6 | 7.860 | 0710700
4141 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0710823 | This project will improve sections and extend the life of SR 54 from SR 58 to SR 37 with a pavement surface overlay. | Pavement Improvement | 2009-07-07 | 2010-05-10 | 2010-11-01 | 2010-10-04 | 602982.8 | 10.470 | 0710823
4142 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WARRICK |  | 08 | 0710824 | This project will improve sections and extend the life of SR 61 from 0.8 Mi. N of SR 62 to S of SR 68 in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-03-19 | 2009-04-28 | 2009-12-18 | 2009-09-18 | 1531554.06 | 10.130 | 0710824
4143 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0710833 | This project will improve sections and extend the life of SR 1 in Steuben County with a pavement surface overlay. | Pavement Improvement | 2009-06-05 | 2009-08-19 | 2009-10-31 | 2009-10-31 | 1339756.9 | 12.920 | 0710833
4144 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PIKE |  | 08 | 0710835 | This project will improve sections and extend the life of SR 56 from South junction with SR 61 to SR 257 in Pike county with a preventive maintenance pavement surface overlay. | Pavement Improvement | 2009-06-16 | 2009-09-08 | 2010-06-30 | 2010-06-04 | 1266971.48 | 8.310 | 0710835
4145 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0710839 | This is a Maintenance Resurfacing project, From 5.49 miles W of SR 15 -W jct (Middleton Run Rd), to 0.10 miles W of SR 13; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-04-26 | 2010-05-17 | 2010-10-01 | 2010-10-12 | 3807660.75 | 11.890 | 0710839
4146 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0710840 | This is a Safety project, at SR-218 1163' E of CR 600E (EB) 24+64 and 70' E of Maple Street (WB) 25+11; to perform New Flasher Installation work. | Safety/Traffic Management | 2010-02-22 | 2010-03-12 | 2010-04-30 | 2010-03-18 | 12462.5 | 0.470 | 0710840
4147 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HARRISON | LOUISVILLE (KY)-IN | 09 | 0710884 | This project will extend the bridge life by repainting bridge beams at I-64 over Blue River and Blue Road in Harrison County. | Bridge Improvement | 2009-06-19 | 2010-02-19 | 2010-08-28 | 2010-04-15 | 442871.28 | 0.010 | 0710884
4148 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0710886 | This project will improve sections and extend the life of SR 19 near the I-80/I-90 Toll Road in Elkhart Co. with a pavement surface overlay. | Pavement Improvement | 2009-06-05 | 2009-07-16 | 2009-10-02 | 2009-09-30 | 1764668.42 | 2.790 | 0710886
4149 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0710888 | This project will extend the life of the pavement on SR 19 from I-80/90 Toll Road to the Michigan state line by resurfcing the road with 2 lays of asphalt overlay. | Pavement Improvement | 2010-04-08 | 2010-05-10 | 2010-10-08 | 2010-07-29 | 1864577.13 | 1.690 | 0710888
4150 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0710917 | This project will upgrade and improve the traffic signals at US 231 and the SR 32/ SR 47 junction in Montgomery County. | Safety/Traffic Management | 2009-06-09 | 2009-06-30 | 2009-06-27 | 2009-07-14 | 23230.1 | 0.020 | 0710917
4151 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BLACKFORD |  | 06 | 0710921 | This project will improve sections and extend the life of SR 26 from 0.84 mile East of SR 3(Little Lick Creek) to SR 167 with a pavement surface overlay. | Pavement Improvement | 2009-06-02 | 2009-08-24 | 2009-11-13 | 2009-11-13 | 775559.91 | 7.140 | 0710921
4152 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0710928 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge over Limberlost Creek, 2.37 miles N of US 27, East of Bryant; to perform Bridge Deck Reconstruction & Widening work. | Bridge Improvement | 2010-03-25 | 2010-05-10 | 2010-10-30 | 2010-10-21 | 1007811.33 | 0.010 | 0710928
4153 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0710933 | This project will improve sections and extend the life of SR 26 from SR 13 to I-69 with a pavement surface overlay. | Pavement Improvement | 2009-08-27 | 2009-09-15 | 2009-10-16 | 2009-10-26 | 1085506.69 | 14.420 | 0710933
4154 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD | KOKOMO | 05 | 0710943 | This is the second of a series of projects to re-align US 31 around Kokomo, Indiana.This phase of the project will construct bridges and fill for the Kokomo bypass. | New Bridge Construction | 2009-06-01 | 2009-07-10 | 2011-06-15 | 2011-06-15 | 774131.29 | 0.010 | 0710943
4155 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL, HOWARD |  | Multiple | 0710948 | This project will improve sections and extend the life of SR 22 from SR 29 to 11.48 miles East of SR 29 with a pavement surface overlay. | Pavement Improvement | 2009-06-16 | 2009-08-07 | 2009-11-13 | 2009-10-17 | 1648972.11 | 11.510 | 0710948
4156 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | HARRISON |  | 09 | 0711000 | This project will move the Historic Rothrock Mill bridge from it's current location to storage for preservation purposes. | Transportation Enhancements | 2009-06-19 | 2009-07-13 | 2009-08-15 | 2009-07-27 | 41800.09 | 0.010 | 0711000
4157 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0711020 | This project will improve sections and extend the life of US 24 with a pavement surface overlay. | Pavement Improvement | 2009-04-15 | 2009-05-30 | 2009-07-31 | 2009-06-25 | 394030 | 1.350 | 0711020
4158 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0711022 | This project will improve sections and extend the life of SR 15 with a pavement surface overlay. | Pavement Improvement | 2009-03-24 | 2009-05-01 | 2009-07-17 | 2009-07-16 | 315308.54 | 0.990 | 0711022
4159 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE, STATEWIDE |  | 03 | 0711024 | This project will improve sections and extend the life of SR 9 with a pavement surface overlay. | Pavement Improvement | 2009-03-31 | 2009-05-26 | 2009-10-31 | 2009-09-17 | 545972.88 | 1.830 | 0711024
4160 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ORANGE |  | 09 | 0800005 | This project will improve drainage by repairing pipes at SR 145, between 1.6 Miles North TO 9.8 Miles North of SR 164 in Orange County. | Pavement Improvement | 2009-04-13 | 2009-05-14 | 2009-10-30 | 2009-06-29 | 258979.75 | 8.180 | 0800005
4161 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0800006 | This project will improve sections and extend the life of SR 164 with a pavement surface overlay. | Pavement Improvement | 2009-04-30 | 2009-06-08 | 2009-09-18 | 2009-08-14 | 173051.83 | 0.930 | 0800006
4162 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0800086 | This project will improve sections and extend the life of SR 62 from IL/IN State line to 1.96 miles East of SR 69 with a pavement surface overlay. | Pavement Improvement | 2009-07-23 | 2010-03-23 | 2010-11-10 | 2010-08-31 | 1571712.39 | 8.760 | 0800086
4163 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0800101 | This is Bridge Replacement, Other Construction on I465, EB 82nd Street over I-465 | Bridge Replacement | 2010-11-01 | 2010-12-28 | 2011-10-15 | 2012-04-09 | 1470000 | 0.010 | 0800101
4164 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0800122 | This is a Maintenance Resurfacing project, at SR 56 - Jct with SR 257 to the W jct of US 231; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2010-03-19 | 2010-07-01 | 2010-07-13 | 1187302.65 | 10.120 | 0800122
4165 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0800125 | This project will improve sections and extend the life of US 50 from 4.09 miles East of SR 37 to junction with SR 446 with a pavement surface overlay. | Pavement Improvement | 2009-07-07 | 2010-05-10 | 2010-11-01 | 2010-10-04 | 688431.96 | 5.560 | 0800125
4166 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0800142 | This is a Small Structure project, at Over the ditch at the Interchange, 0.15 miles N of I-469 S jct; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-09-20 | 2010-10-02 | 2010-10-25 | 593400 | 0.010 | 0800142
4167 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0800158 | This project will improve sections and extend the life of US-6 from SR 19 to SR 15 in Elkhart County with a pavement surface overlay. | Pavement Improvement | 2009-06-03 | 2009-07-08 | 2009-10-09 | 2009-10-07 | 956280.17 | 6.970 | 0800158
4168 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0800162 | This project will improve sections and extend the life of US 41 in Huntington County with a pavement surface overlay | Pavement Improvement | 2009-07-06 | 2009-08-19 | 2009-10-23 | 2009-11-04 | 2202419 | 8.800 | 0800162
4169 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WABASH, WHITLEY |  | Multiple | 0800176 | This is a Maintenance Resurfacing project, at SR 114 - From 1.66 miles E of SR 13 (EEL River) to SR 105; to perform asphalt resurface, Functional work. | Pavement Improvement | 2009-12-10 | 2010-04-09 | 2010-08-13 | 2010-08-12 | 1890052.25 | 7.390 | 0800176
4170 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0800177 | This project will improve sections and extend the life of SR 227 from CSX R/R to US 27 with a pavement surface overlay. | Pavement Improvement | 2009-07-22 | 2009-08-20 | 2009-11-20 | 2009-11-04 | 446746.86 | 2.870 | 0800177
4171 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0800191 | This project will improve sections and extend the life of US 27 from. 1.12 miles North of I-70 at East fork of Whitewater River to 5.71 miles North of I-70 at Fountain Circle with a pavement surface overlay. | Pavement Improvement | 2009-07-22 | 2009-08-20 | 2009-11-20 | 2009-11-20 | 855629.12 | 3.960 | 0800191
4172 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0800196 | This project will improve lighting on I-69 at Airport Expressway in Allen County. | Safety/Traffic Management | 2009-07-10 | 2009-08-18 | 2009-11-30 | 2009-11-13 | 71877.05 | 0.760 | 0800196
4173 | INDIANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | HENRY |  | 06 | 0800200 | This project is road surface treatment for US 36 in Greenfield District, from 3.67 miles west of State Road 3 to west ramps of State Road 3. | Pavement Improvement | 2009-08-25 | 2009-09-04 | 2009-10-16 | 2009-10-16 | 436627.17 | 3.590 | 0800200
4174 | INDIANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0800203 | This project will improve sections and extend the life of US 27 in the Town of Portland with a pavement surface overlay. | Pavement Improvement | 2009-07-07 | 2009-08-20 | 2009-10-15 | 2009-11-07 | 652936.73 | 5.160 | 0800203
4175 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0800219 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge # 12-64-05413-A (WBL) over Burns Ditch (0.94 miles W of SR 249); to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2010-03-23 | 2010-10-01 | 2011-07-15 | 2011-07-30 | 1843982.32 | 0.010 | 0800219
4176 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0800220 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge # 12-64-05413-A (EBL) over Burns Ditch (0.94 miles W of SR 249); to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2010-03-23 | 2010-10-01 | 2011-07-15 | 2011-07-30 | 1133827.62 | 0.010 | 0800220
4177 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 0800237 | This project will extend the bridge life by repainting bridge beams at various locations in Crawfordsville. | Bridge Improvement | 2009-04-25 | 2009-05-28 | 2009-09-30 | 2009-08-25 | 434958.8 | 0.010 | 0800237
4178 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0800260 | This project will improve sections and extend the life of US 35 from 1.65 miles East of SR 15 (10th St) to 0.24 miles East of I-69 and on SR 22 with a pavement surface overlay. | Pavement Improvement | 2009-06-16 | 2009-08-26 | 2009-10-24 | 2009-10-24 | 739294.69 | 7.200 | 0800260
4179 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0800389 | This project will patch deteriorated pavement areas and seal cracks on US 31 4.11 mi. N of SR 250 in Jackson County. | Pavement Improvement | 2009-03-26 | 2009-06-09 | 2009-07-15 | 2009-07-10 | 146826.45 | 0.960 | 0800389
4180 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0800434 | This project will improve sections and extend the life of SR 10 with a pavement surface overlay. | Pavement Improvement | 2009-04-09 | 2009-05-12 | 2009-06-26 | 2009-06-05 | 332090.99 | 7.990 | 0800434
4181 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL | SOUTH BEND (MI) | 02 | 0800438 | This project will improve sections and extend the life of SR 17 with a pavement surface overlay. | Pavement Improvement | 2009-04-16 | 2009-09-08 | 2009-11-01 | 2009-10-21 | 292790.44 | 1.680 | 0800438
4182 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0800439 | This project will improve sections and extend the life of SR 23 with a pavement surface overlay. | Pavement Improvement | 2009-04-16 | 2009-07-10 | 2009-11-06 | 2009-08-04 | 241745.43 | 6.480 | 0800439
4183 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0800440 | This project will improve sections and extend the life of SR 16 with a pavement surface overlay. | Pavement Improvement | 2009-04-16 | 2009-05-18 | 2009-06-30 | 2009-06-26 | 474528.03 | 14.400 | 0800440
4184 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0800475 | This project will improve sections and extend the life of SR 25 with a pavement surface overlay. | Pavement Improvement | 2009-03-24 | 2009-05-01 | 2009-07-17 | 2009-07-16 | 164391.63 | 0.570 | 0800475
4185 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW | COLUMBUS | 06 | 0800516 | This project will add turn lanes, nodernize the signal, and widen the intersection at SR 11and Bartholomw county Road 450S. | Safety/Traffic Management | 2009-05-06 | 2009-06-01 | 2010-08-15 | 2010-11-01 | 41055.8 | 0.010 | 0800516
4186 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0800517 | This project will install fiber optic lines from the Indianapolis Traffic Management Center to downtown Indianapolis to improve the closed circuit TV system used for traffic management. | Safety/Traffic Management | 2009-06-11 | 2009-06-29 | 2010-05-28 | 2010-03-18 | 714614.44 | 7.620 | 0800517
4187 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0800753 | This project will improve sections and extend the life of SR 245 from junction with SR 70 to 3.50 miles South of SR 162 with a pavement surface overlay. | Pavement Improvement | 2009-07-23 | 2010-03-01 | 2011-11-01 | 2010-10-01 | 640303.87 | 9.030 | 0800753
4188 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0800766 | This project will improve sections and extend the life of SR 161 from Ky State Line to SR 66 with a pavement surface overlay. | Pavement Improvement | 2009-07-23 | 2010-03-01 | 2011-11-01 | 2010-10-01 | 1807885.98 | 8.290 | 0800766
4189 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0800817 | This project will improve sections and extend the life of SR 168 from US 41 to SR 57 with a pavement surface overlay. | Pavement Improvement | 2009-07-23 | 2009-08-26 | 2010-05-31 | 2009-11-04 | 1478864.47 | 9.400 | 0800817
4190 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0800821 | This project will improve sections and extend the life of SR 69 from 2.48 miles South of West junction with SR 66 to 0.1 miles North of I-64 with a pavement surface overlay. | Pavement Improvement | 2009-07-09 | 2009-08-06 | 2010-08-01 | 2009-11-25 | 1307218.59 | 8.840 | 0800821
4191 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE, WHITE | LAFAYETTE-WEST LAFAYETTE | 04 | 0800831 | This project will improve sections and extend the life of SR 43 in Tippecanoe & White Counties with a pavement surface overlay | Pavement Improvement | 2009-04-09 | 2009-08-20 | 2009-07-31 | 2009-10-10 | 373458.7 | 4.760 | 0800831
4192 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WELLS, ALLEN |  | Multiple | 0800939 | This is a Maintenance Resurfacing project, at From 2.44 miles N of US 224 (CR850N, Ossian, Wells Co) to I-469 (Allen Co); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-18 | 2010-09-02 | 2010-11-06 | 2010-11-19 | 1273931.28 | 6.040 | 0800939
4193 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0800962 | This project will extend the bridge life by repainting bridge beams at I-70 in Wayne County. | Bridge Improvement | 2009-08-20 | 2009-09-16 | 2009-11-24 | 2009-10-25 | 335616 | 0.010 | 0800962
4194 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0800967 | This is a pavement resurfacing project on SR15, 2 miles north of US 20 to SR 120 in Bristol in Elkhart county that will lay 2 lays of asphalt to extend the life of the pavement, | Pavement Improvement | 2010-04-26 | 2010-05-17 | 2010-10-01 | 2010-10-12 | 466215.25 | 1.860 | 0800967
4195 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE, DE KALB |  | 03 | 0800974 | This is a Maintenance Resurfacing project, at US 6 - From SR 3 E jct (Kendallville) to I-69; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-05-17 | 2010-10-31 | 2011-05-16 | 2499046.86 | 12.020 | 0800974
4196 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WHITLEY, HUNTINGTON |  | Multiple | 0800975 | This project will improve sections and extend the life of US 24 in Huntington county from 1.66 Miles east of SR 9 est junction (Meridian Rd) to 0.75 miles east of SR 114 with a preventive maintenance pavement surface overlay. | Pavement Improvement | 2009-07-07 | 2009-09-07 | 2009-10-23 | 2009-10-22 | 2559703.48 | 10.640 | 0800975
4197 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0800984 | This project will improve sections and extend the life of US 24 in Allen County with a pavement surface overlay | Pavement Improvement | 2009-03-25 | 2009-08-17 | 2009-09-03 | 2009-09-04 | 619717.05 | 4.180 | 0800984
4198 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0800986 | This is a Maintenance Resurfacing project, at SR 116 N jct to 2.44 miles N of US 224 (CR 850 N); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-03-24 | 2010-06-07 | 2010-08-28 | 2010-11-20 | 1098409.91 | 7.470 | 0800986
4199 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0810040 | This is a Safety project, at US 231 - at Parrish Avenue, Comm No 01-045-388; to perform Traffic Signals, New Or Modernized work. | Safety/Traffic Management | 2010-01-05 | 2010-01-29 | 2010-05-31 | 2010-03-11 | 98595.22 | 0.010 | 0810040
4200 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAGRANGE |  | 03 | 0810097 | This is a Maintenance Resurfacing project, at E US 20 - From 0.20 miles E of SR 9 to 4.28 miles E of SR 3 (Lagrange/Steuben Co Line).; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-29 | 2010-06-29 | 2010-10-31 | 2010-08-30 | 1359665.96 | 11.350 | 0810097
4201 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JAY, ADAMS |  | 06 | 0810099 | This is a Maintenance Resurfacing project, at Jct of SR 18/67 (Jay Co) to 1.04 miles S of SR 124 (Adams Co).; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-04-13 | 2010-05-04 | 2010-08-14 | 2010-08-13 | 1189917.08 | 13.050 | 0810099
4202 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI, WABASH, HUNTINGTON |  | 05 | 0810100 | This is a Maintenance Resurfacing project, at SR 19 (Miami Co) to SR 5 (Huntington Co).; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-15 | 2010-04-14 | 2010-10-01 | 2010-10-04 | 2715926.46 | 25.450 | 0810100
4203 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 0810108 | This project will improve the pavement markings in the LaPorte Area. | Safety/Traffic Management | 2009-04-16 | 2009-06-15 | 2009-11-12 | 2009-08-21 | 217958.7 | 0.010 | 0810108
4204 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WARRICK |  | 08 | 0810123 | This project will improve drainage by repairing pipes at I-64, 1 mile East of SR 161 in Warrick County. | Pavement Improvement | 2009-05-12 | 2009-06-10 | 2009-11-15 | 2009-07-30 | 116971.2 | 0.010 | 0810123
4205 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CRAWFORD, WARRICK |  | Multiple | 0810124 | This project will improve drainage by repairing pipes at I-64 from 5 miles East of I-164 to 1 mile West of SR 66 in Crawford and Warren Counties. | Pavement Improvement | 2009-05-12 | 2009-06-10 | 2009-11-15 | 2009-07-30 | 103675 | 0.030 | 0810124
4206 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITLEY |  | 03 | 0810228 | This is a Maintenance Resurfacing project, at SR 114 - From SR 105 to SR 9; to perform asphalt resurface, Functional work. | Pavement Improvement | 2009-12-16 | 2010-04-08 | 2010-10-22 | 2010-08-26 | 1860626.47 | 7.890 | 0810228
4207 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0810240 | This project will mitigate the environmental impacts of relocating a stream as part of the US 20 curve correction project, adding 370' of stream length, creating a floodplain and planting native vegetation. | Other | 2009-06-18 | 2009-08-24 | 2010-06-30 | 2011-05-07 | 92975 | 0.010 | 0810240
4208 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0810254 | This project will extend the bridge life by repainting bridge beams at SR 55 over Big Pine Creek in Warren County. | Bridge Improvement | 2009-09-01 | 2009-10-08 | 2009-11-15 | 2009-11-12 | 248875.68 | 0.010 | 0810254
4209 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0810342 | This project will improve sections and extend the life of US-31 from Youngs Creek Bridge to Westview Dr in Johnson County with a pavement surface overlay. | Pavement Improvement | 2009-04-16 | 2009-05-14 | 2009-07-31 | 2009-07-29 | 636472.7 | 0.650 | 0810342
4210 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE, CLINTON |  | 04 | 0810387 | This project will improve drainage by repairing pipes at I-64 in Posey, Spencer and Vanderburgh Counties. | Pavement Improvement | 2009-05-22 | 2009-06-15 | 2009-06-30 | 2009-07-07 | 238601.65 | 1.970 | 0810387
4211 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PUTNAM |  | 08 | 0810388 | This project will improve sections and extend the life of SR 243 in Putnam County with a pavement surface overlay. | Pavement Improvement | 2009-05-13 | 2009-06-09 | 2009-07-01 | 2009-07-06 | 593817.69 | 4.010 | 0810388
4212 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0810390 | This project will improve sections and extend the life of US 421 in Jefferson County with a pavement surface overlay | Pavement Improvement | 2009-05-22 | 2009-06-24 | 2009-10-09 | 2009-08-26 | 596194.04 | 7.900 | 0810390
4213 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0810391 | This project will improve sections and extend the life of SR 57 in Jefferson County with a pavement surface overlay. | Pavement Improvement | 2009-05-22 | 2009-06-25 | 2009-07-31 | 2009-07-28 | 211151.98 | 2.590 | 0810391
4214 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE, BROWN |  | 09 | 0810411 | This project will improve sections and extend the life of SR 46 from SR 446 to SR 135 with a pavement surface overlay. | Pavement Improvement | 2009-05-13 | 2009-06-16 | 2009-08-31 | 2009-08-28 | 1784927.67 | 22.210 | 0810411
4215 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0810412 | This project will improve sections and extend the life ofS R-258 from SR 58 to Elm St in Jackson County with a pavement surface overlay. | Pavement Improvement | 2009-06-01 | 2009-08-04 | 2009-11-13 | 2009-10-06 | 1186796.91 | 12.340 | 0810412
4216 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS, JEFFERSON |  | 09 | 0810413 | This project will improve sections and extend the life of SR 7 from 1.52 miles North of Clifty Creek Drive to SR 3 with a pavement surface overlay. | Pavement Improvement | 2009-05-09 | 2009-08-13 | 2009-11-13 | 2009-10-31 | 1696103.37 | 14.970 | 0810413
4217 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS, JEFFERSON |  | 09 | 0810414 | This project will improve sections and extend the life of SR 250 from SR-3 to SR-7 with a pavement surface overlay. | Pavement Improvement | 2009-10-07 | 2010-03-10 | 2010-06-30 | 2010-05-06 | 678627.24 | 9.940 | 0810414
4218 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0810415 | This project will improve sections and extend the life of SR-46 from SR 1 to US 52 in Dearborn County with a pavement surface overlay. | Pavement Improvement | 2009-07-28 | 2009-08-28 | 2009-10-16 | 2009-09-30 | 513103.76 | 5.300 | 0810415
4219 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0810431 | This project will improve sections and extend the life of US 31 from the Fulton/Miami County Line to Old US 31 with a pavement surface overlay. | Pavement Improvement | 2009-06-09 | 2009-07-14 | 2009-07-18 | 2009-08-11 | 462865.34 | 3.800 | 0810431
4220 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0810432 | This project will improve sections and extend the life of US 35 through the town of Knox with a pavement surface overlay. | Pavement Improvement | 2009-06-17 | 2009-07-18 | 2009-07-31 | 2009-08-29 | 304785.34 | 2.610 | 0810432
4221 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0810453 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Pavement Improvement | 2009-06-17 | 2009-07-16 | 2010-08-31 | 2010-09-17 | 501810.51 | 1.020 | 0810453
4222 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 0810532 | This project will improve pavement markings in the LaPorte Area. | Safety/Traffic Management | 2009-06-19 | 2009-07-06 | 2009-09-11 | 2009-09-03 | 318376 | 0.010 | 0810532
4223 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0810598 | This project will construct canal boat support facilities for the Wabash and Erie Canal in the City of Delphi. | Transportation Enhancements | 2009-06-19 | 2009-11-10 | 2010-05-22 | 2010-04-29 | 398376.28 | 0.010 | 0810598
4224 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 02 | 0818022 | This project will improve the surface and rebuild sections of the bridge on US 421 over Little Monon Creek in White County. | Bridge Replacement | 2009-03-21 | 2009-04-16 | 2009-08-28 | 2009-10-26 | 668112.1 | 0.010 | 0818022
4225 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0887013 | This project will add turn lanes and widen the intersection at SR 32 and Rangeline Road in Madison County. | Pavement Improvement | 2009-07-08 | 2009-08-24 | 2010-07-31 | 2010-08-09 | 1920914 | 0.120 | 0887013
4226 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900008 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | New Bridge Construction | 2009-05-12 | 2009-07-22 | 2011-07-11 | 2011-08-04 | 252212.4 | 0.010 | 0900008
4227 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | POSEY, VANDERBURGH, SPENCER |  | Multiple | 0900048 | This project will improve drainage by repairing pipes at I-64 in Posey, Spencer and Vanderburgh Counties. | Pavement Improvement | 2009-05-12 | 2009-06-10 | 2009-11-15 | 2009-07-30 | 727204.41 | 45.010 | 0900048
4228 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0900049 | This is a Facilities for Pedestrians and Bicycles project, at Jasper Multi-Use Path - Ph 2; from W 20th St to 30th St; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2009-11-23 | 2010-03-17 | 2010-07-15 | 2010-07-09 | 422671.06 | 0.010 | 0900049
4229 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900079 | This project will improve sections and extend the life of US 52 in West Lafayette with a pavement surface overlay. | Pavement Improvement | 2009-06-03 | 2009-06-15 | 2009-11-28 | 2010-03-29 | 3633372.97 | 5.500 | 0900079
4230 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE |  | 02 | 0900082 | This is a Maintenance Resurfacing project, at US 35 - from Severs Rd to East Jct with US 20; to perform asphalt resurface, Functional work. | Pavement Improvement | 2009-10-08 | 2009-10-12 | 2010-08-13 | 2010-08-06 | 1681597.77 | 4.120 | 0900082
4231 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900083 | This project will build a new road from Amos Road to McKay Road in Shelby County. | New Construction | 2009-08-11 | 2009-08-28 | 2010-09-01 | 2010-09-12 | 1925233.13 | 0.763 | 0900083
4232 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NEWTON |  | 01 | 0900084 | This project will improve sections and extend the life of US 41 in Newton County with a pavement surface overlay. | Pavement Improvement | 2009-06-09 | 2009-07-17 | 2009-08-28 | 2009-09-10 | 1468123.44 | 11.880 | 0900084
4233 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900086 | This project will improve sections and extend the life of SR 106 in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-06-17 | 2009-09-09 | 2009-10-16 | 2009-10-16 | 449322.76 | 5.260 | 0900086
4234 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900087 | This project will improve sections and extend the life of US 6 in Marshall County with a pavement surface overlay | Pavement Improvement | 2009-06-17 | 2009-09-02 | 2009-10-02 | 2009-10-12 | 358345.84 | 5.410 | 0900087
4235 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900092 | This project will improve sections and extend the life of old US 52 on Old US-52 from IR-74 to West Harrison Corporate Limitswith a pavement surface overlay. | Pavement Improvement | 2009-07-27 | 2009-08-21 | 2009-11-03 | 2009-10-30 | 310752.1 | 2.420 | 0900092
4236 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900093 | This project will improve sections and extend the life of York Ridge Road from SR-1 to North Dearborn Road with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-04-09 | 2010-06-30 | 2010-06-04 | 650901.55 | 7.440 | 0900093
4237 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900095 | This project will improve sections and extend the life of North Hogan Road from SR 350 to Hogan Road in Dearborn County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-09 | 2010-07-15 | 234751.67 | 11.890 | 0900095
4238 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900096 | This project will improve sections and extend the life of North Dearborn from Ripley county line to SR1 in Dearborn County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-09 | 2010-07-15 | 142274.82 | 7.560 | 0900096
4239 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900119 | This project will replace and restore the pavement on US-40, at Brown Blvd, Terre Haute, in Vigo County. | Pavement Widening | 2009-09-15 | 2009-10-06 | 2010-06-30 | 2011-03-24 | 83633.1 | 0.100 | 0900119
4240 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900122 | This project will improve drainage by repairing pipes at I-70, .10 mile East of SR 46 in Vigo County. | Safety/Traffic Management | 2009-06-25 | 2009-07-01 | 2009-08-15 | 2009-08-24 | 623351.95 | 0.100 | 0900122
4241 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON, HENDRICKS, MARION, BOONE | INDIANAPOLIS | Multiple | 0900129 | This project will install traffic cameras on I-465, I-65, I-70 and I-74. | Other | 2009-06-11 | 2009-08-05 | 2010-05-28 | 2009-11-06 | 475151 | 23.110 | 0900129
4242 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900133 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment of SR 25. | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2012-07-27 | 1464516.93 | 0.010 | 0900133
4243 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900134 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment of SR 25. | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2012-07-27 | 543423.11 | 0.010 | 0900134
4244 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900135 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment of SR 25. | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2012-07-27 | 734550.61 | 0.010 | 0900135
4245 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 0900136 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment of SR 25. | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2012-07-27 | 893652.86 | 0.010 | 0900136
4246 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN | CINCINNATI | Multiple | 0900144 | This project will improve sections and extend the life of SR 148 from SR-48 to Maple Street with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-03-22 | 2010-07-16 | 2010-06-29 | 796973.87 | 9.170 | 0900144
4247 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0900145 | This project will improve sections and extend the life of SR 56 from East Junction of SR-62 to Crooked Creek Bridgewith a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-03-05 | 2010-07-16 | 2010-06-01 | 582189.29 | 2.560 | 0900145
4248 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RIPLEY |  | 09 | 0900146 | This is a Maintenance Resurfacing project, at Jefferson/Ripley CL to US-50; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-04-12 | 2010-09-01 | 2010-11-15 | 2010-11-10 | 950393.7 | 12.570 | 0900146
4249 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900147 | This is a Maintenance Resurfacing project, at SR 235 - to US-50; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-07 | 2009-11-02 | 2009-11-15 | 2010-04-13 | 747103.1 | 7.530 | 0900147
4250 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN |  | 09 | 0900159 | This project will improve sections and extend the life of Ridge Ave. from Decker Ave to Robinson Avenue with a pavement surface overlay. | Pavement Improvement | 2009-07-15 | 2009-08-07 | 2009-09-30 | 2009-09-23 | 79526.63 | 0.420 | 0900159
4251 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0900176 | This project will improve sections and extend the life of SR 10 in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-08-20 | 2009-09-21 | 2009-11-15 | 2009-11-14 | 1365218.07 | 6.810 | 0900176
4252 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900177 | This is a Reconstruction (no added capacity) project, at 7th Street and Springhill Road; to perform Intersect. Improv. W/ Added Turn Lanes work. | Pavement Improvement | 2010-04-08 | 2010-04-23 | 2010-08-28 | 2011-04-14 | 991533.27 | 0.010 | 0900177
4253 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE, PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900211 | This project will patch deteriorated pavement areas and seal cracks on I-94 from 1.5 mi. E of I-65 to SR 249 in Lake and Porter Counties. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 1134807.66 | 15.760 | 0900211
4254 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CARROLL, CASS |  | 02 | 0900218 | This is a Maintenance Restoration & Rehabilitation project, at SR 25 - from SR 218 in Delphi to Logansport; to perform Crack Sealing work. | Pavement Improvement | 2010-01-22 | 2010-05-20 | 2010-06-30 | 2010-10-14 | 349276.84 | 20.260 | 0900218
4255 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900219 | This project will patch deteriorated pavement areas and seal cracks on US 20 from SR 912 to Bridge St. in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 68420 | 9.880 | 0900219
4256 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0900229 | This is a Maintenance Resurfacing project, at SR-135 to 1.4 miles W Pekin; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-04-12 | 2010-06-30 | 2010-07-07 | 1064631.73 | 6.140 | 0900229
4257 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0900231 | This is a Maintenance Resurfacing project, at East of Jim Day Road to Washington /Scott CL; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-06-24 | 2010-09-30 | 2010-10-11 | 1877561.22 | 10.880 | 0900231
4258 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DECATUR, FRANKLIN |  | 06 | 0900232 | This is a Maintenance Resurfacing project, at 0.7 miles E of US-421 to the Batesville CL; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-04-14 | 2010-07-15 | 2010-07-27 | 1827164.82 | 13.630 | 0900232
4259 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON |  | 05 | 0900238 | This project will replace and restore the pavement, bridges, and signs along SR 44 from I-65 to the west city limits of Shelbyville. | New Bridge Construction | 2009-05-12 | 2009-07-22 | 2011-07-11 | 2011-08-04 | 242787.2 | 0.010 | 0900238
4260 | INDIANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | DECATUR |  | 06 | 0900260 | This is a Maintenance Resurfacing project, at I-74 to Seymour District/Greenfield District Line; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-07 | 2010-07-20 | 2010-11-15 | 2010-11-15 | 1217013.89 | 6.020 | 0900260
4261 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0900296 | This project will improve safety and extend the life of the bridge(s) on County Road 211 over I-64 in Perry County. | Bridge Improvement | 2009-07-07 | 2009-09-17 | 2010-06-30 | 2010-07-16 | 419566 | 0.214 | 0900296
4262 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900297 | This project will improve safety and extend the life of the bridge(s) on US 41 over Main Street in Knox County. | Bridge Improvement | 2009-07-10 | 2010-08-04 | 2010-07-31 | 2010-10-29 | 322096.46 | 0.122 | 0900297
4263 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900298 | This project will improve safety and extend the life of the bridge(s) on US 41 over Main Street in Knox County. | Bridge Improvement | 2009-07-10 | 2010-08-04 | 2010-07-31 | 2010-10-29 | 308896.52 | 0.122 | 0900298
4264 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0900299 | This project will improve safety and extend the life of the bridge(s) on SR 157 over White River in Green County. | Bridge Improvement | 2009-07-24 | 2009-09-22 | 2010-06-30 | 2010-07-08 | 938275.61 | 0.742 | 0900299
4265 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | OWEN |  | 08 | 0900300 | This project will improve safety and extend the life of the bridge(s) on US 231 over Fish Creek in Owen County. | Bridge Improvement | 2009-07-24 | 2009-09-22 | 2010-06-30 | 2010-07-08 | 615291.8 | 0.225 | 0900300
4266 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0900301 | This project will improve safety and extend the life of the bridge(s) on SR 124 over Brock Creek in Huntington County. | Bridge Improvement | 2009-07-07 | 2009-08-21 | 2009-10-30 | 2009-10-22 | 271400.3 | 0.680 | 0900301
4267 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0900302 | This project will improve safety and extend the life of the bridge(s) on County Road 300 South over I-69 in Huntington County. | Bridge Improvement | 2009-07-07 | 2009-08-21 | 2009-10-30 | 2009-10-22 | 421012.07 | 0.208 | 0900302
4268 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW |  | 06 | 0900303 | This project will improve safety and extend the life of the bridge(s) on US 31 over Little Sand Creek in Bartholomew County. | Bridge Improvement | 2009-10-09 | 2010-04-05 | 2010-10-31 | 2010-10-14 | 655702 | 0.108 | 0900303
4269 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW |  | 06 | 0900304 | This project will improve safety and extend the life of the bridge(s) on SR 46 over the abandoned Railroad in Bartholomew County. | Bridge Improvement | 2009-10-09 | 2010-04-05 | 2010-10-31 | 2010-10-14 | 660012.93 | 0.010 | 0900304
4270 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BROWN |  | 09 | 0900305 | This project will improve safety and extend the life of the bridge(s) on SR 45 over Beanblossom Creek in Brown County. | Bridge Improvement | 2009-07-07 | 2010-06-07 | 2010-10-29 | 2010-09-15 | 506351.86 | 0.125 | 0900305
4271 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BROWN |  | 09 | 0900306 | This project will improve safety and extend the life of the bridge(s) on SR 45 over Beanblossom Creek in Brown County. | Bridge Improvement | 2009-07-07 | 2010-06-07 | 2010-10-29 | 2010-09-15 | 465000 | 0.010 | 0900306
4272 | INDIANA | Completed | C250,C240 | Highway Infrastructure Investment Grant | INDIANA | DECATUR |  | 06 | 0900307 | This project will improve safety and extend the life of the bridge(s) on SR 3 over Clifty Creek in Decatur County. | Bridge Improvement | 2009-07-07 | 2010-06-16 | 2010-11-19 | 2010-11-12 | 760685.65 | 0.010 | 0900307
4273 | INDIANA | Completed | C250,C200 | Highway Infrastructure Investment Grant | INDIANA | RIPLEY |  | 09 | 0900308 | This project will improve safety and extend the life of the bridge(s) on US 50 over Laughery Creek in Ripley County. | Bridge Improvement | 2009-08-18 | 2010-04-01 | 2010-11-19 | 2010-07-02 | 730256.8 | 0.010 | 0900308
4274 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900309 | This project will improve safety and extend the life of the bridge(s) on SR 3 over the abandoned Railroad in Scott County. | Bridge Improvement | 2009-07-24 | 2010-04-01 | 2010-09-20 | 2010-08-09 | 500410.02 | 0.217 | 0900309
4275 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VERMILLION |  | 08 | 0900310 | This project will improve safety and extend the life of the bridge(s) on SR 63 over Brouiletts Creek in Vermillion County. | Bridge Improvement | 2009-08-18 | 2010-04-09 | 2010-10-15 | 2010-10-21 | 775788 | 0.421 | 0900310
4276 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900311 | This project will improve safety and extend the life of the bridge(s) on SR 263 over Redwood Creek in Warren County. | Bridge Improvement | 2009-07-17 | 2009-09-10 | 2010-07-18 | 2010-05-19 | 644125.4 | 0.150 | 0900311
4277 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VERMILLION |  | 08 | 0900312 | This project will improve safety and extend the life of the bridge(s) on SR 71 over Little Vermillion River in Vermillion County. | Bridge Improvement | 2009-08-18 | 2010-04-09 | 2010-10-15 | 2010-10-21 | 455103 | 0.150 | 0900312
4278 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900314 | This project will patch deteriorated pavement areas and seal cracks on I-65 from SR 2 to US 231 in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 584240 | 7.380 | 0900314
4279 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE, PORTER, MARSHALL, LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900315 | This project will patch deteriorated pavement areas and seal cracks on US 30 from the Lake/Porter County Line to SR 17 in LaPorte, Marshall, Porter and Starke Counties. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 196604.8 | 50.080 | 0900315
4280 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900316 | This project will patch deteriorated pavement areas and seal cracks on US 30 from US 41 to SR 55 in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 106556.8 | 5.710 | 0900316
4281 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900317 | This project will patch deteriorated pavement areas and seal cracks on I-94 from SR 249 to SR 49 in Porter County. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 154256 | 7.080 | 0900317
4282 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | MICHIGAN CITY | 02 | 0900318 | This project will patch deteriorated pavement areas and seal cracks on I-94 from US 35 to the Michigan State Line in LaPorte County. | Pavement Improvement | 2009-07-22 | 2009-08-31 | 2009-11-13 | 2010-06-29 | 87648 | 5.850 | 0900318
4283 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW | COLUMBUS | 06 | 0900321 | This project will improve sections and extend the life of 25th St. from CR 350 E to SR 9 with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-09 | 2009-11-15 | 2009-10-07 | 496214.92 | 4.300 | 0900321
4284 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | PARKE |  | 08 | 0900322 | This project will improve the surface and rebuild sections of the bridge on SR 47 at Turkey Run in Parke County. | Bridge Improvement | 2009-07-11 | 2009-09-16 | 2009-11-15 | 2009-11-06 | 292449.49 | 0.317 | 0900322
4285 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900323 | This project will improve the surface and rebuild sections of the bridge on US 136 at the Wabash River in Warren County. | Bridge Improvement | 2009-07-07 | 2009-09-10 | 2009-09-30 | 2009-09-30 | 471268.58 | 0.935 | 0900323
4286 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900327 | This project will patch deteriorated pavement areas and seal cracks on US 231 from SR 912 to Bridge St. in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 19543.2 | 6.300 | 0900327
4287 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900329 | This project will patch deteriorated pavement areas and seal cracks on SR 2 from Cline Ave. to SR 53 in Porter County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 55274 | 13.400 | 0900329
4288 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900331 | This project will patch deteriorated pavement areas and seal cracks on US 41 from Huehn St. to 0.25 mi.. N. of Sheffield Ave. in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 32000.5 | 2.570 | 0900331
4289 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900333 | This project will patch deteriorated pavement areas and seal cracks on US 12 from W. of Calumet Ave. to the Illinois State Line. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 29005 | 1.310 | 0900333
4290 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900334 | This project will improve sections and extend the life of Howard County Road 200N from 1350 East to the county line with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 24133.69 | 0.010 | 0900334
4291 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900335 | This project will patch deteriorated pavement areas and seal cracks on US 12 from Schrage Ave. to the lift bridge S. of Riley Road in Lake County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 89212.8 | 1.450 | 0900335
4292 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900336 | This project will improve the surface and rebuild sections of the bridge on SR 912 over I-80 in Lake County. | Bridge Improvement | 2009-09-14 | 2010-05-03 | 2010-06-30 | 2010-06-08 | 298381.48 | 0.010 | 0900336
4293 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900337 | This project will improve the surface and rebuild sections of the bridge on SR 912 over I-80 in Lake County. | Bridge Improvement | 2009-09-14 | 2010-05-03 | 2010-06-30 | 2010-06-08 | 300423.28 | 0.010 | 0900337
4294 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900339 | This project will patch deteriorated pavement areas and seal cracks on US 20 from SR 249 to US 20/I-94 in Porter County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 59245.7 | 3.540 | 0900339
4295 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900340 | This project will improve sections and extend the life of Howard County Road 200W from County Road 200North to County Road 325 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 72715.54 | 1.200 | 0900340
4296 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900341 | This project will improve the surface and rebuild sections of the bridge on US 41 over Brown Ditch in Lake County. | Bridge Improvement | 2009-09-14 | 2009-10-12 | 2009-10-31 | 2009-10-21 | 23904.4 | 0.880 | 0900341
4297 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900343 | This project will improve the surface and rebuild sections of the bridge on US 41 over Brown Ditch in Lake County. | Bridge Improvement | 2009-09-14 | 2009-10-12 | 2009-10-31 | 2009-10-21 | 23110 | 0.880 | 0900343
4298 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900344 | This project will patch deteriorated pavement areas and seal cracks on US 31 from US 20 to the Michigan State Line in St. Joseph County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 75948 | 3.840 | 0900344
4299 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900345 | This project will improve the surface and rebuild sections of the bridge on US 41 over Singleton Ditch in Lake County. | Bridge Improvement | 2009-09-14 | 2009-10-12 | 2009-10-31 | 2009-10-21 | 22380 | 0.940 | 0900345
4300 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900346 | This project will improve the surface and rebuild sections of the bridge on US 41 over Singleton Ditch in Lake County. | Bridge Improvement | 2009-09-14 | 2009-10-12 | 2009-10-31 | 2009-10-21 | 22550 | 0.940 | 0900346
4301 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL | SOUTH BEND (MI) | 02 | 0900347 | This project will patch deteriorated pavement areas and seal cracks ON US 6 from 0.5 mi. W of SR 106 to 0.5 mi. E of SR 106 in Marshall County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 27450 | 4.140 | 0900347
4302 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900348 | This project will improve the surface and rebuild sections of the bridge on US 50 at Vernon Fork Muscatatuck River in Jennings County. | Bridge Improvement | 2009-09-17 | 2010-06-10 | 2010-07-31 | 2010-07-27 | 260883.08 | 0.010 | 0900348
4303 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900349 | This project will patch deteriorated pavement areas and seal cracks on US 12 from SR 249 to SR 149 bridge in Porter County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 19910.4 | 1.980 | 0900349
4304 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | HARRISON |  | 09 | 0900350 | This project will improve the surface and rebuild sections of the bridge on SR 135 at Lick Run Creek in Harrison County. | Bridge Improvement | 2009-07-20 | 2009-08-20 | 2009-09-26 | 2009-09-14 | 495227.43 | 0.122 | 0900350
4305 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW |  | 06 | 0900351 | This project will improve the surface and rebuild sections of the bridge on I-65 over Driftwood River in Bartholomew County. | Bridge Improvement | 2009-08-18 | 2010-05-27 | 2010-10-01 | 2010-07-09 | 594008.86 | 0.010 | 0900351
4306 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW |  | 06 | 0900352 | This project will improve the surface and rebuild sections of the bridge on I-65 over Driftwood River in Bartholomew County. | Bridge Improvement | 2009-08-18 | 2010-05-27 | 2010-10-01 | 2010-07-09 | 433965.37 | 0.010 | 0900352
4307 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900353 | This project will improve the surface and rebuild sections of the bridge on US 50 over Wabash River in Knox County. | Bridge Improvement | 2009-07-15 | 2009-08-14 | 2009-10-15 | 2009-08-31 | 52897.74 | 0.010 | 0900353
4308 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | MICHIGAN CITY | 02 | 0900354 | This project will patch deteriorated pavement areas and seal cracks on SR 212 from US 12 to US 20 in LaPorte County. | Pavement Improvement | 2009-07-22 | 2009-08-10 | 2009-11-13 | 2009-11-13 | 32000.5 | 3.360 | 0900354
4309 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900355 | This project will improve the surface and rebuild sections of the bridge on US 50 over Wabash River in Knox County. | Bridge Improvement | 2009-07-15 | 2009-08-14 | 2009-10-15 | 2009-08-31 | 52307.59 | 0.010 | 0900355
4310 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0900356 | This project will improve the surface and rebuild sections of the bridge on US 50 over White River in Lawrence County. | Bridge Improvement | 2009-07-15 | 2009-08-14 | 2009-10-15 | 2009-08-31 | 41930.71 | 0.930 | 0900356
4311 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0900357 | This project will improve sections and extend the life of Arba Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2010-04-19 | 2010-06-04 | 2010-05-28 | 350293.36 | 3.580 | 0900357
4312 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0900358 | This project will improve the surface and rebuild sections of the bridge on US 50 over White River in Lawrence County. | Bridge Improvement | 2009-07-15 | 2009-08-14 | 2009-10-15 | 2009-08-31 | 40828.81 | 0.930 | 0900358
4313 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900363 | This project will extend the bridge life by repainting bridge beams at I-64 over SR 111 & Main Street in Floyd County. | Bridge Improvement | 2009-10-29 | 2010-01-04 | 2010-09-25 | 2010-07-26 | 929455.22 | 0.020 | 0900363
4314 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900364 | This is a Maintenance Restoration & Rehabilitation project, at SR 25 - from Logansport to SR 16; to perform Crack Sealing work. | Pavement Improvement | 2010-01-22 | 2010-05-20 | 2010-06-30 | 2010-10-14 | 103467.42 | 11.420 | 0900364
4315 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900365 | This project will extend the bridge life by repainting bridge beams at I-64 over Southern Railroad in Floyd County. | Bridge Improvement | 2009-10-29 | 2010-01-04 | 2010-09-25 | 2010-07-26 | 870968.87 | 0.020 | 0900365
4316 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900366 | This project will extend the bridge life by repainting bridge beams at I-64 over SR 111 & Main Street in Floyd County. | Bridge Improvement | 2009-10-29 | 2010-01-04 | 2010-09-25 | 2010-07-26 | 1498546.9 | 0.020 | 0900366
4317 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NEWTON |  | 01 | 0900367 | This is a Maintenance Restoration & Rehabilitation project, at US 41 - from SR 114 to SR 14; to perform Crack Sealing work. | Pavement Improvement | 2010-01-22 | 2010-05-20 | 2010-06-30 | 2010-10-14 | 54573.04 | 5.310 | 0900367
4318 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0900368 | This project will extend the bridge life by repainting bridge beams at I-65 at Riverside Drive & Market Street in Clark County. | Bridge Improvement | 2009-08-03 | 2009-09-23 | 2009-11-01 | 2009-11-15 | 570539.54 | 0.648 | 0900368
4319 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900371 | This is a Maintenance Restoration & Rehabilitation project, at US 31 - from SR 110 to 0.1mi S of SR 10; to perform Crack Sealing work. | Pavement Improvement | 2010-01-22 | 2010-05-20 | 2010-06-30 | 2010-10-14 | 140273.82 | 4.730 | 0900371
4320 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VANDERBURGH | EVANSVILLE (KY) | 08 | 0900384 | This is a Facilities for Pedestrians and Bicycles project, at Greenway bike/ped trail from Franklin St to Maryland St (Sect 3-C2); to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-01 | 2010-06-01 | 2011-06-15 | 2011-09-22 | 1892569 | 0.010 | 0900384
4321 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0900406 | This project will upgrade and improve the traffic signals at various locations in the town of Westfield. | Safety/Traffic Management | 2009-11-23 | 2009-12-21 | 2010-03-01 | 2010-02-23 | 65210.2 | 0.010 | 0900406
4322 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900423 | This is a Maintenance Resurfacing project, at SR 4 - On Maple Avenue from Monroe Street (SR4) to Rose Street; to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 97094.97 | 0.300 | 0900423
4323 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900424 | This is a Maintenance Resurfacing project, at City of LaPorte on Park Street from Norfolk/Southern RR to McClung Road; to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 50971.96 | 0.270 | 0900424
4324 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900425 | This is a Maintenance Resurfacing project, at 1st Street from Central Avenue to J Street (SR 2); to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 63481.47 | 0.320 | 0900425
4325 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900426 | This is a Maintenance Resurfacing project, at 1st Street from J Street (SR 2) to Indiana Avenue (US 35); to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 219215.5 | 0.580 | 0900426
4326 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0900427 | This is a Maintenance Resurfacing project, at Street from 10th Street to 18th Street; to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-05 | 2010-06-01 | 2010-05-24 | 97874.83 | 0.500 | 0900427
4327 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900429 | This is a Maintenance Resurfacing project, at 73rd Avenue from Clark Street to I-65 overpass; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-07-16 | 2010-07-31 | 2010-09-03 | 644120.51 | 3.500 | 0900429
4328 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900430 | This is a Maintenance Resurfacing project, at Madison Street/Harrison Street from US 30 to 53rd Avenue; to perform Surface Treatment work. | Pavement Improvement | 2010-01-15 | 2010-03-30 | 2010-06-30 | 2010-05-12 | 327191.87 | 3.610 | 0900430
4329 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CRAWFORD |  | 09 | 0900434 | This project will improve drainage by repairing pipes at I-64 in Crawford County. | Pavement Improvement | 2009-07-16 | 2009-08-31 | 2010-06-01 | 2010-04-14 | 1561004.65 | 11.280 | 0900434
4330 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VANDERBURGH |  | 08 | 0900436 | This project will improve drainage by repairing pipes at SR 66 in Crawford County. | Other | 2009-07-06 | 2009-08-31 | 2009-10-15 | 2009-09-24 | 735970.32 | 3.990 | 0900436
4331 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900441 | This project will complete the restoration of the Bremen Train Depot. | Transportation Enhancements | 2009-12-16 | 2010-01-25 | 2010-10-31 | 2010-10-29 | 289960.37 | 0.010 | 0900441
4332 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900442 | This project will improve the Marshall County Historical Museum. | Transportation Enhancements | 2010-01-08 | 2010-02-24 | 2010-10-31 | 2010-11-23 | 393189.06 | 0.010 | 0900442
4333 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900443 | This is a Historic Preservation project to update and preserve the streetscape on at Central Ave. from 119th to 116th and on Oliver St, from 119th to 117th in the town of Whiting, Lake county. | Transportation Enhancements | 2010-01-14 | 2010-04-13 | 2010-06-30 | 2010-06-02 | 257318.84 | 0.630 | 0900443
4334 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900448 | This project will replace the bridge deck on SR 23 over Mishawaka Ave in St Joseph County. | Bridge Improvement | 2009-08-18 | 2009-10-09 | 2010-05-15 | 2010-05-14 | 727822.5 | 0.146 | 0900448
4335 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 04 | 0900449 | This project will improve safety and extend the life of the bridge(s) on SR 341 over Coal Creek in Fountain County. | Bridge Improvement | 2009-07-17 | 2009-09-10 | 2010-07-18 | 2010-05-19 | 357212.5 | 0.710 | 0900449
4336 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PARKE |  | 08 | 0900450 | This project will improve safety and extend the life of the bridge(s) on US 41 over Big Raccoon Creek in Parke County. | Bridge Improvement | 2009-07-07 | 2010-04-07 | 2010-07-31 | 2010-07-16 | 795594.75 | 0.384 | 0900450
4337 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WABASH |  | 05 | 0900451 | This project will improve safety and extend the life of the bridge(s) on Sr 13 over Paw Paw Creek in Wabash County. | Pavement Improvement | 2009-07-07 | 2009-08-05 | 2009-10-30 | 2009-08-27 | 144530.47 | 0.420 | 0900451
4338 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0900452 | This project will improve safety and extend the life of the bridge(s) on SR 4 over Rock Run Creek in Elkhart County. | Bridge Improvement | 2009-08-18 | 2009-09-14 | 2009-10-23 | 2009-10-21 | 121166.6 | 0.440 | 0900452
4339 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0900453 | This project will improve safety and extend the life of the bridge on SR 218 over Wagley Farlow Ditch in Adams County by removing and replacing the wearing surface of the deck. | Bridge Improvement | 2009-07-07 | 2009-09-03 | 2009-10-30 | 2009-10-29 | 310982.85 | 0.030 | 0900453
4340 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0900469 | This project will improve sections and extend the life of County Road 900North from 200 west to 300 east in Jasper County with a pavement surface overlay. | Pavement Improvement | 2009-12-31 | 2010-04-14 | 2010-06-05 | 2010-06-02 | 455193.8 | 5.040 | 0900469
4341 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0900470 | This project will improve sections and extend the life of County Road 400West from Northern County limits to intersection at SR 10 in Jasper County with a pavement surface overlay. | Pavement Improvement | 2009-12-31 | 2010-04-14 | 2010-06-05 | 2010-06-02 | 560204.92 | 6.670 | 0900470
4342 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900472 | This is a Maintenance Resurfacing project, at Kennedy Avenue from the Toll Road to Michigan Avenue; to perform Surface Treatment work. | Pavement Improvement | 2010-01-19 | 2010-03-25 | 2010-06-09 | 2010-05-13 | 363065.78 | 2.000 | 0900472
4343 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900473 | This is a Landscaping project, at E Columbus Drive from Cline Avenue to Main Street; to perform Landscaping work. | Transportation Enhancements | 2010-03-26 | 2010-04-02 | 2010-06-15 | 2010-11-11 | 99538.87 | 0.900 | 0900473
4344 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900474 | This is a Safety project, at E Columbus Drive from Cline Avenue to Main Street; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-26 | 2010-04-02 | 2010-06-15 | 2010-11-11 | 329757.93 | 0.900 | 0900474
4345 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900493 | This project will improve sections and extend the life of 9A Road from SR 31 to King Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 16609.25 | 0.733 | 0900493
4346 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900496 | This project will improve sections and extend the life of Lincoln Highway from King Road to Fir Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-06 | 2010-06-30 | 2009-12-14 | 566060.81 | 5.910 | 0900496
4347 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900500 | This project will improve sections and extend the life of 4th Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 5861.81 | 0.254 | 0900500
4348 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900501 | This project will improve sections and extend the life of King Road from Plymouth-Goshen Trail to 4th Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 77825.02 | 3.697 | 0900501
4349 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900502 | This project will improve sections and extend the life of Plymouth-Goshen Trail from Linden Road to King Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 17565.74 | 0.733 | 0900502
4350 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900514 | This project will improve sections and extend the life of Lincoln Highway from Fir Road to Elm Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-06 | 2010-06-30 | 2009-12-14 | 81746.03 | 1.042 | 0900514
4351 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900518 | This is a Maintenance Resurfacing project, at Wisconsin St. from Old Ridge Road to 10th Street; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-06-05 | 2010-06-09 | 299416.25 | 0.970 | 0900518
4352 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900520 | This is a New Construction Roadway project, at Lake Park Avenue from Ridge Road (37th Ave) to Old Ridge Road; to perform Surface Treatment work. | New Construction | 2010-01-08 | 2010-06-28 | 2010-06-30 | 2010-08-09 | 177948.94 | 0.920 | 0900520
4353 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900521 | This is a Maintenance Resurfacing project, at 3rd Street from S LaSalle St to Main Street; to perform Surface Treatment work. | Pavement Improvement | 2009-10-13 | 2009-11-05 | 2009-11-21 | 2009-11-23 | 266385.27 | 1.500 | 0900521
4354 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | BROWN |  | 09 | 0900535 | This project will improve sections and extend the life of Gatesville Rd. from SR 135 to Salt Cree with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-05-03 | 2010-07-01 | 2010-06-11 | 339147.08 | 6.330 | 0900535
4355 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | BROWN |  | 09 | 0900536 | This project will improve sections and extend the life of Christiansburg Rd. Rd from SR 135 S to Bells with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-05-03 | 2010-07-01 | 2010-06-11 | 238087.69 | 4.060 | 0900536
4356 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900537 | This project will improve sections and extend the life of Bicknell Slab Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-24 | 2009-11-30 | 2009-11-22 | 539391.24 | 8.030 | 0900537
4357 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900538 | This project will improve sections and extend the life of Sixth St in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-08 | 2009-11-30 | 2009-11-11 | 139489.1 | 1.530 | 0900538
4358 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900539 | This project will improve sections and extend the life of Sixth Street Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-24 | 2009-11-30 | 2009-11-22 | 196066.53 | 2.900 | 0900539
4359 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0900540 | This project will improve sections and extend the life of Cannelburt Rd in Daviess County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-11-30 | 2009-10-29 | 306500.38 | 3.200 | 0900540
4360 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0900541 | This is a Maintenance Resurfacing project, at NW 11th St to NW 5th St; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-08-31 | 2010-10-18 | 70314.86 | 0.430 | 0900541
4361 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900542 | This is a Maintenance Resurfacing project, at 12th St to Main St; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-08-31 | 2010-10-18 | 127834.08 | 0.730 | 0900542
4362 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0900543 | This is a Maintenance Resurfacing project, at 5th St to 12th St; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-08-31 | 2010-10-18 | 68407.98 | 1.030 | 0900543
4363 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0900545 | This is a Maintenance Resurfacing project, at Kopp Lane from Hallmark Blvd to Eastern Blvd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-09 | 2010-04-07 | 2010-07-19 | 91014.04 | 0.720 | 0900545
4364 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0900546 | This project will improve sections and extend the life of Old SR 245 with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-09-25 | 2009-11-30 | 2009-11-24 | 582496.64 | 3.890 | 0900546
4365 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0900547 | This project will improve the traffic signs in Daviess County. | Safety/Traffic Management | 2009-09-01 | 2010-01-18 | 2009-12-31 | 2010-03-31 | 317221.5 | 0.010 | 0900547
4366 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0900548 | This project will improve sections and extend the life of French Ridge Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-14 | 2009-11-30 | 2009-11-09 | 475602.57 | 5.150 | 0900548
4367 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0900549 | This project will improve sections and extend the life of Leopold Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-14 | 2009-11-30 | 2009-11-09 | 546200.24 | 6.900 | 0900549
4368 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900550 | This project will improve sections and extend the life of South Michigan St. in Marshall County with a pavement surface overlay | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 292820.96 | 4.283 | 0900550
4369 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900551 | This project will improve sections and extend the life of Miami Highway from SR 106 to the county line in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 42123.04 | 2.039 | 0900551
4370 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0900554 | This is a Maintenance Resurfacing project, at North Main Street from TP&W railroad tracks N 2,665 feet; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-02-22 | 2010-03-31 | 2010-07-01 | 2010-06-24 | 268352.11 | 0.500 | 0900554
4371 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 0900555 | This is a Maintenance Resurfacing project, at North Illinois Street from TP&W railroad N 2,660 feet; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-02-22 | 2010-03-31 | 2010-07-01 | 2010-06-24 | 206935.48 | 0.400 | 0900555
4372 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900556 | This project will improve sections and extend the life of Monterey Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 36552.76 | 1.687 | 0900556
4373 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0900558 | This is a Small Structure project, at I-69 & I-469 Interchange Ramp"D",Pipe #7, EB to SB I-69, 0.18 Miles S. of I-469; to perform Pipe Lining work. | Other | 2010-04-14 | 2010-09-20 | 2010-10-02 | 2010-10-25 | 44400 | 0.100 | 0900558
4374 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900560 | This project will improve sections and extend the life of Road 600S with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2010-05-18 | 2010-06-30 | 2010-08-12 | 558472.41 | 5.520 | 0900560
4375 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900561 | This project will improve sections and extend the life of Road 75W in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-10-14 | 2010-04-02 | 2009-10-15 | 2010-06-09 | 254296.79 | 1.750 | 0900561
4376 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900562 | This project will improve sections and extend the life of Road 700E with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-10-12 | 2009-12-18 | 638387.39 | 5.500 | 0900562
4377 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900563 | This project will improve sections and extend the life of Road 400S in Cass County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-10-12 | 2009-12-18 | 53499.41 | 0.500 | 0900563
4378 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900564 | This project will improve sections and extend the life of Road 200E in Cass County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2010-05-18 | 2010-06-30 | 2010-06-18 | 280012.35 | 3.000 | 0900564
4379 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0900566 | This project will improve sections and extend the life of Old SR 45 in Spencen County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-09-25 | 2009-11-30 | 2009-11-24 | 387969.28 | 3.790 | 0900566
4380 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0900567 | This project will improve sections and extend the life of Fulda Shortcut Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-09-25 | 2009-11-30 | 2009-11-24 | 220751.47 | 4.180 | 0900567
4381 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SPENCER |  | 09 | 0900568 | This project will improve sections and extend the life of Road 800 E in Spencer County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-09-25 | 2009-11-30 | 2009-11-24 | 121839.45 | 2.280 | 0900568
4382 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0900572 | This project will replace and restore the pavement on Nucor Road in Crawfordsville. | Pavement Improvement | 2009-09-03 | 2009-08-03 | 2009-11-15 | 2009-11-18 | 588633.74 | 5.860 | 0900572
4383 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900573 | This project will improve sections and extend the life of Road 350 E in Gibson County with a pavement surface overlay | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-11-30 | 2009-10-19 | 464734.47 | 5.300 | 0900573
4384 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONTGOMERY |  | 04 | 0900574 | This project will replace and restore the pavement on Old SR 55 in Wingate. | Pavement Improvement | 2009-09-03 | 2009-08-03 | 2009-11-15 | 2009-11-18 | 963868.51 | 10.920 | 0900574
4385 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900575 | This project will improve sections and extend the life of Road 550 E in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-11-30 | 2009-10-19 | 400716.23 | 3.510 | 0900575
4386 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900576 | This project will improve sections and extend the life of Road 350 S in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-11-30 | 2009-10-19 | 225187.43 | 2.620 | 0900576
4387 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900577 | This project will improve sections and extend the life of CR 50 S/Old Boonville HWY in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-06 | 2009-11-30 | 2009-11-30 | 201964.34 | 2.100 | 0900577
4388 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900578 | This project will improve sections and extend the life of Road 350S/Vann Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-06 | 2009-11-30 | 2009-11-30 | 355597.27 | 3.900 | 0900578
4389 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900579 | This project will improve sections and extend the life of Road 25w/Yankeetown Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-06 | 2009-11-30 | 2009-11-30 | 59422.22 | 0.700 | 0900579
4390 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900580 | This project will improve sections and extend the life of Old SR 66 in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-06 | 2009-11-30 | 2009-11-30 | 142584.85 | 1.800 | 0900580
4391 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900581 | This project will improve sections and extend the life of CR 800N/Elberfeld Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-16 | 2009-11-30 | 2009-11-30 | 118101.74 | 1.100 | 0900581
4392 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0900582 | This project will improve sections and extend the life of Rd 1100S/North Rd in Warrick County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-16 | 2009-11-30 | 2009-11-30 | 121332.76 | 1.700 | 0900582
4393 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS | INDIANAPOLIS | 04 | 0900584 | This is a Maintenance Restoration & Rehabilitation project, at US 40 - In Plainfield from the East end of the Bridge over White Lick Creek to Carr Rd; to perform Road Reconstruction work. | Pavement Improvement | 2009-09-18 | 2009-10-05 | 2010-11-12 | 2011-05-26 | 2391134.09 | 1.080 | 0900584
4394 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900585 | This project will improve sections and extend the life of 2nd St in Knox County with a pavement surface overlay | Pavement Improvement | 2009-09-15 | 2009-10-30 | 2009-11-30 | 2009-11-19 | 92455.5 | 0.625 | 0900585
4395 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900599 | This project will improve sections and extend the life of Old SR 132 in Madison County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-30 | 2009-10-02 | 306308.7 | 5.220 | 0900599
4396 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900605 | This project will restore the pavement on Madison County Road 600 W with a new surface course. | Pavement Improvement | 2009-09-14 | 2009-09-22 | 2009-10-30 | 2009-10-26 | 311854.78 | 3.830 | 0900605
4397 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900606 | This project will improve sections and extend the life of Northport Rd. from SR 9 to Angling Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-23 | 2009-10-31 | 2009-10-17 | 294529.38 | 2.850 | 0900606
4398 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900607 | This project will improve sections and extend the life of Madison County Road 100E with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-30 | 2009-10-02 | 84810.6 | 1.080 | 0900607
4399 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900608 | This project will improve sections and extend the life of 8th St. in Madison County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2009-10-30 | 2009-10-02 | 267037.3 | 4.330 | 0900608
4400 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900609 | This project will improve sections and extend the life of Shelby County Road 400E on the east side of Shelbyville with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-26 | 2009-11-02 | 2009-11-01 | 705434.18 | 0.010 | 0900609
4401 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | PUTNAM |  | 08 | 0900610 | This project will replace and restore the pavement on Indiana Street in Greencastle. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-11-15 | 2009-10-13 | 61850.75 | 0.540 | 0900610
4402 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 04 | 0900612 | This project will improve sections and extend the life of N Perry St in Fountain County with a pavement surface overlay | Pavement Improvement | 2009-09-01 | 2009-09-29 | 2009-11-15 | 2010-06-24 | 221094.57 | 0.520 | 0900612
4403 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON |  | 05 | 0900613 | This is a Maintenance Resurfacing project, at From SR 32 to SR 47 in Washington & Adams Townships IN; to perform Pavement, Other work. | Pavement Improvement | 2009-11-23 | 2010-04-23 | 2010-05-28 | 2010-05-25 | 442696.27 | 6.070 | 0900613
4404 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0900614 | This project will replace and restore the pavement on County Road 800E, from CR-100N to CR-1200N, in Rush County. | Pavement Improvement | 2009-09-01 | 2009-11-16 | 2009-10-30 | 2009-11-25 | 100552.48 | 0.990 | 0900614
4405 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0900615 | This project will replace and restore the pavement on County Road 800E, from CR-600N to CR-900N, in Rush County. | Pavement Improvement | 2009-09-01 | 2009-11-16 | 2009-10-30 | 2009-11-25 | 244409.25 | 3.000 | 0900615
4406 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK |  | 05 | 0900616 | This project will replace and restore the pavement on County Road 1050E, from US-40 to SR-650N, in Hancock County. | Pavement Improvement | 2009-09-01 | 2009-10-13 | 2009-10-30 | 2009-11-06 | 431006.31 | 5.690 | 0900616
4407 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK |  | 05 | 0900617 | This project will replace and restore the pavement on County Road 600E, from US-40 to SR-234, in Hancock County. | Pavement Improvement | 2009-09-01 | 2009-10-13 | 2009-10-30 | 2009-11-06 | 568377.18 | 6.110 | 0900617
4408 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | LAWRENCE |  | 04 | 0900624 | This project will improve sections and extend the life of Main St/Hoosier Ave with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-19 | 2009-11-30 | 2009-11-18 | 242821.91 | 0.280 | 0900624
4409 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SULLIVAN |  | 08 | 0900626 | This project will improve sections and extend the life of CR 925N/CR 450W/CR 1100 N with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-07 | 2009-11-30 | 2009-11-30 | 586794.18 | 8.540 | 0900626
4410 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SULLIVAN |  | 08 | 0900628 | This project will improve sections and extend the life of Old US 41 in Sullivan County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-07 | 2009-11-30 | 2009-11-30 | 294187.65 | 4.200 | 0900628
4411 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900635 | This project will restore the pavement on Madison County Road 1100 N with a new surface course. | Pavement Improvement | 2009-09-14 | 2009-09-22 | 2009-10-30 | 2009-10-26 | 202051.35 | 4.000 | 0900635
4412 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900637 | This is a Safety project, at Hausfledt Lane at CSX Railroad Crossing; to perform Railroad Protection work. | Safety/Traffic Management | 2010-01-06 | 2011-05-04 | 2010-05-13 | 2011-05-20 | 471428 | 0.040 | 0900637
4413 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON |  | 06 | 0900638 | This project will restore the pavement on Madison County Road 1100 N with a new surface course. | Pavement Improvement | 2009-09-14 | 2009-09-22 | 2009-10-30 | 2009-10-26 | 390592.05 | 5.500 | 0900638
4414 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900639 | This project will improve the traffic signals on Market Street from State St to Vincennes Street. | Safety/Traffic Management | 2010-02-01 | 2010-02-08 | 2010-05-14 | 2010-04-09 | 327809.26 | 1.300 | 0900639
4415 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPTON |  | 05 | 0900642 | This project will improve sections and extend the life of Division Rd. from US 31 to SR 1 with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-10-30 | 2009-10-28 | 433627.27 | 4.960 | 0900642
4416 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPTON |  | 05 | 0900643 | This project will improve sections and extend the life of South Ash St. from SR 28 to Railroad with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-10-30 | 2009-10-28 | 42457.45 | 1.008 | 0900643
4417 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0900644 | This project will improve traffic signals from Spring Street to State Street in New Albany, Floyd county. | Safety/Traffic Management | 2010-02-01 | 2010-02-08 | 2010-05-14 | 2010-04-09 | 277980.07 | 1.300 | 0900644
4418 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900647 | This project will improve sections and extend the life of Howard County Road 1350 East from CR 200 North to CR 400 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 154362.09 | 2.000 | 0900647
4419 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900648 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 1000 East to County Road 1200 East with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 103108.36 | 2.000 | 0900648
4420 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900650 | This project will improve sections and extend the life of Road 300 W in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-10-14 | 2010-04-02 | 2009-10-15 | 2010-06-09 | 129189.32 | 1.170 | 0900650
4421 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900651 | This project will improve sections and extend the life of Bicycle Rd with a pavement surface overlay. | Pavement Improvement | 2009-10-14 | 2010-04-02 | 2009-10-15 | 2010-06-09 | 399347.3 | 3.940 | 0900651
4422 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900652 | This project will improve sections and extend the life of Road 100N in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2010-06-15 | 2009-12-23 | 11417.16 | 0.120 | 0900652
4423 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900655 | This project will improve sections and extend the life of Road 700W in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2010-06-15 | 2009-12-23 | 314863.21 | 6.110 | 0900655
4424 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CARROLL |  | 02 | 0900656 | This project will improve sections and extend the life of Meridian Rd in Carroll County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-20 | 2010-06-15 | 2009-12-23 | 411985.15 | 3.010 | 0900656
4425 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900657 | This project will replace and restore the pavement on Loganspot Road, from Longtree to SR-1100E, in Cass County. | Pavement Improvement | 2009-09-01 | 2009-09-18 | 2009-10-12 | 2009-12-18 | 641031.41 | 7.500 | 0900657
4426 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900660 | This is a Maintenance Resurfacing project, at Southeastern Avenue from Columbia to 175th St.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-06 | 2010-09-03 | 2010-09-30 | 2010-10-07 | 580852.15 | 1.330 | 0900660
4427 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900661 | This is a Maintenance Resurfacing project, at 45th Avenue from Kennedy to Kleinman; to perform Surface Treatment work. | Pavement Improvement | 2010-01-20 | 2010-09-03 | 2010-09-30 | 2010-10-05 | 340503.85 | 1.230 | 0900661
4428 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900663 | This is a Maintenance Resurfacing project, at Main Street from Wood Ave to Chase St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-05 | 2010-06-01 | 2010-06-30 | 2010-06-25 | 322700.15 | 2.490 | 0900663
4429 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900671 | This project will improve sections and extend the life of 9A Road from city limits to SR 31 in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-06 | 2010-06-30 | 2009-12-14 | 98051.42 | 1.142 | 0900671
4430 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0900672 | This project will improve sections and extend the life of Plymouth-Goshen Trail from city limits to Lilac Road in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 21436.96 | 0.020 | 0900672
4431 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JASPER |  | 01 | 0900673 | This is a Maintenance Resurfacing project, at CR 700 S from 1200W to 3315' West of CR 900W; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-31 | 2010-04-14 | 2010-06-05 | 2010-05-28 | 242489.4 | 2.410 | 0900673
4432 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900674 | This is a Maintenance Resurfacing project, at Kennedy Avenue from Main Street to Junction Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-06 | 2010-07-15 | 2010-08-15 | 2010-09-20 | 254248.74 | 1.470 | 0900674
4433 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900675 | This is a Maintenance Resurfacing project, at 77th Avenue from US 41 to Austin Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-06 | 2010-07-15 | 2010-08-15 | 2010-09-20 | 164673.77 | 1.230 | 0900675
4434 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900676 | This is a Maintenance Resurfacing project, at Lincolnwood Avenue/Old Lincoln Highway from US 30 to 77th Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-06 | 2010-07-15 | 2010-08-15 | 2010-09-20 | 104863.39 | 0.800 | 0900676
4435 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900681 | This project will improve sections and extend the life of Howard County 850 East from County Road 200 North to County Road 400 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 107006.21 | 2.000 | 0900681
4436 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900682 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 700 West to County Road 710 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 6749.21 | 0.140 | 0900682
4437 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900683 | This project will improve sections and extend the life of Howard County Road 400 North from County Road 750 West to County Road 800 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 24723.93 | 0.500 | 0900683
4438 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900684 | This project will improve sections and extend the life of Howard County Road 1150W from CR 400 North to CR 600 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 94897.52 | 2.000 | 0900684
4439 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900685 | This project will improve sections and extend the life of Howard County Road 750W from SR 22 to County Road 200 North with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 59959.84 | 1.000 | 0900685
4440 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900686 | This project will improve sections and extend the life of Howard County Road 750W with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 122964.18 | 2.200 | 0900686
4441 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900687 | This project will improve sections and extend the life of Howard County Road 750 West from County Road 220 South to Russiaville town limits with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 70920.41 | 1.500 | 0900687
4442 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900688 | This project will improve sections and extend the life of Howard County Road 600 South from County Road 800 West to County Road 870 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 33972.08 | 0.800 | 0900688
4443 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900689 | This project will improve sections and extend the life of Howard County Road 220 South from County Road 750 West to County Road 766 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 7226.35 | 0.130 | 0900689
4444 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900690 | This project will improve sections and extend the life of Howard County Road 750 West from Russioville Town limits to County Road 500 South with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 34754.77 | 0.700 | 0900690
4445 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0900691 | This project will improve sections and extend the life of Howard County Road 250 South from from County Road 600 West to County Road 750 West with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 77286.7 | 1.500 | 0900691
4446 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLAY |  | 08 | 0900692 | This project will replace and restore the pavement on Bowling Green Poland Road, from SR-46 to SR-42, in Clay County. | Pavement Improvement | 2009-09-01 | 2009-09-30 | 2009-11-15 | 2009-11-13 | 631318.18 | 6.720 | 0900692
4447 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900693 | This project will replace and restore the pavement on Monroe Street, from Franklin Street to South 3rd Street, in Warren County. | Pavement Improvement | 2009-09-01 | 2009-09-22 | 2009-11-15 | 2010-06-24 | 292750.65 | 1.170 | 0900693
4448 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900694 | This project will replace and restore the pavement on Cotton Drive from Singhurst Street to SR-159, in Vigo County. | Pavement Improvement | 2009-09-02 | 2009-10-15 | 2009-11-15 | 2009-11-18 | 207440.79 | 0.750 | 0900694
4449 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900695 | This project will replace and restore the pavement on Rio Grande Avenue, from Baldwin Street to Twin Beach Street, in Vigo County. | Pavement Improvement | 2009-09-02 | 2009-10-15 | 2009-11-15 | 2009-11-18 | 195315.58 | 2.355 | 0900695
4450 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PUTNAM |  | 08 | 0900696 | This project will improve sections and extend the life of Walnut Road from the West Greencastle City Limits to West County Line Road in Putnam County with a pavement surface overlay. | Pavement Improvement | 2009-09-03 | 2009-09-22 | 2009-11-15 | 2009-12-01 | 904903.55 | 8.000 | 0900696
4451 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900697 | This is a preventive maintenance resurfacing project, at CR17 from North of CR18 to South of Verdant road in elkhart county to extend the service life of the pavement. | Pavement Improvement | 2009-12-16 | 2010-07-19 | 2010-08-15 | 2010-09-08 | 138360.99 | 0.600 | 0900697
4452 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900698 | This is a Maintenance Resurfacing project, at CR 17 from 900' N of Verdant to SR 120; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-07-19 | 2010-08-15 | 2010-09-08 | 530303.59 | 1.800 | 0900698
4453 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900699 | This is a Maintenance Resurfacing project, at CR 17 from CR 6 to CR 4; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-07-19 | 2010-08-15 | 2010-09-08 | 198591.03 | 1.000 | 0900699
4454 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900700 | This is a Maintenance Resurfacing project, at CR 45 from Fenmore Ave to CR 13; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-07-19 | 2010-08-15 | 2010-09-08 | 190244.13 | 2.100 | 0900700
4455 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0900701 | This project will replace and restore the pavement on Rosedale Road, from Rio Grande Avenue to Lambert Street, in Vigo County. | Pavement Improvement | 2009-09-02 | 2009-10-15 | 2009-11-15 | 2009-11-18 | 335034.96 | 3.710 | 0900701
4456 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0900702 | This is a Facilities for Pedestrians and Bicycles project, at SR 3 from Water St. to Park St.; to perform Enhancement work. | Transportation Enhancements | 2009-12-31 | 2010-03-05 | 2010-10-01 | 2010-09-24 | 634688.66 | 0.040 | 0900702
4457 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | VERMILLION |  | 08 | 0900704 | This project will replace and restore the pavement on Main Street, from 50' North of the RR tracks to North of the City limits, in Vermillion County. | Pavement Improvement | 2009-09-11 | 2009-10-05 | 2009-11-15 | 2010-05-14 | 292097.19 | 0.568 | 0900704
4458 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900709 | This is a Maintenance Resurfacing project, at SR 62 to Middle Mt Vernon Rd.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-03-30 | 2010-08-31 | 2010-06-03 | 198372.3 | 2.100 | 0900709
4459 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900710 | This is a Maintenance Resurfacing project, at Creamery Rd to SR 66; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-03-30 | 2010-08-31 | 2010-06-03 | 441892.1 | 4.900 | 0900710
4460 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900711 | This project will improve sections and extend the life of Springfield Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-30 | 2009-10-31 | 735695.82 | 9.300 | 0900711
4461 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0900712 | This project will improve sections and extend the life of Road 210 in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-11-07 | 2009-10-21 | 101416.38 | 1.300 | 0900712
4462 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0900713 | This project will improve sections and extend the life of Road 625E in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-11-07 | 2009-10-21 | 89028.43 | 1.200 | 0900713
4463 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0900714 | This project will improve sections and extend the life of Toto Rd in Starke County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-01 | 2009-11-07 | 2009-10-21 | 602464.54 | 8.300 | 0900714
4464 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900716 | This is a Maintenance Resurfacing project, at 101st(Joliet St.) from US 41 to Parish Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-02-22 | 2010-08-13 | 2010-09-30 | 2010-09-07 | 247099.39 | 1.150 | 0900716
4465 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900717 | This project will improve sections and extend the life of County Road 600West from US 6 to county road 1200 north in Noble County with a pavement surface overlay. | Pavement Improvement | 2009-09-10 | 2009-09-16 | 2009-09-30 | 2009-09-30 | 133384.95 | 4.800 | 0900717
4466 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900718 | This project will improve sections and extend the life of Baseline Road from SR 3 to county road 1200 East in Noble County with a pavement surface overlay. | Pavement Improvement | 2009-09-10 | 2009-09-16 | 2009-09-30 | 2009-09-30 | 30540.55 | 1.500 | 0900718
4467 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900720 | This project will improve the surface and rebuild sections of the bridge on County Road 900 South over Big Blue River in Shelby County. | Bridge Improvement | 2009-09-15 | 2010-04-09 | 2010-07-30 | 2010-05-13 | 60502.5 | 0.010 | 0900720
4468 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BOONE |  | 04 | 0900721 | This project will improve sections and extend the life of Elizaville Road from the Lebanon City Limits to County Road 500 East in Boone County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-05 | 2009-11-15 | 2009-11-11 | 532719.27 | 6.500 | 0900721
4469 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BOONE |  | 04 | 0900722 | This project will improve sections and extend the life of County Road 1200East from County Road 300 South to SR 32 in Boone County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-05 | 2009-11-15 | 2009-11-11 | 66160.22 | 3.000 | 0900722
4470 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BOONE |  | 04 | 0900723 | This project will improve sections and extend the life of County Road 400East from County Road 300 South to SR 32 in Boone County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-05 | 2009-11-15 | 2009-11-11 | 248995.7 | 2.900 | 0900723
4471 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BOONE |  | 04 | 0900724 | This project will improve sections and extend the life of County Road 25West from the Hendricks County Line to County Road 250 South in Boone County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-05 | 2009-11-15 | 2009-11-11 | 388735.98 | 5.600 | 0900724
4472 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900727 | This project will improve sections and extend the life of Bicknell-Oaktown Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-24 | 2009-11-30 | 2009-11-22 | 70107.97 | 1.280 | 0900727
4473 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KNOX |  | 08 | 0900728 | This project will improve sections and extend the life of Hart Street Rd in Knox County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-24 | 2009-11-30 | 2009-11-22 | 365159.72 | 5.370 | 0900728
4474 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900735 | This project will improve sections and extend the life of River Rd in Warren County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-15 | 2009-12-03 | 193054.36 | 0.110 | 0900735
4475 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900736 | This project will improve sections and extend the life of Independence Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-15 | 2009-12-03 | 487453.32 | 5.530 | 0900736
4476 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WARREN |  | 08 | 0900737 | This project will improve sections and extend the life of Rd 300N in Warren County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-15 | 2009-12-03 | 1341777.4 | 13.430 | 0900737
4477 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900738 | This project will improve sections and extend the life of Angling Road from Northport Road to Kendallville City Limits in Noble County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-03 | 2009-10-16 | 2009-10-24 | 259978.68 | 3.000 | 0900738
4478 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 0900739 | This is a Maintenance Resurfacing project, at Old SR 28 to Mulberry City limits; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-25 | 2010-06-30 | 2010-06-30 | 578218.02 | 5.800 | 0900739
4479 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0900740 | This project will improve sections and extend the life of Albion Road from US 33 to the Albion City Line in Noble County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-03 | 2009-10-16 | 2009-10-24 | 549995.39 | 7.000 | 0900740
4480 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SHELBY |  | 05 | 0900741 | This project will improve the surface and rebuild sections of the bridge on County Road 900 South over Big Blue River in Shelby County. | Bridge Improvement | 2009-09-15 | 2010-04-09 | 2010-07-30 | 2010-05-13 | 32037.49 | 0.010 | 0900741
4481 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 0900742 | This is a Maintenance Resurfacing project, at SR 38 to Kelly Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-25 | 2010-06-30 | 2010-06-30 | 244115.46 | 5.000 | 0900742
4482 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 0900743 | This is a Maintenance Resurfacing project, at CR 100 N to CR 600 N.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-25 | 2010-06-30 | 2010-06-30 | 351415.89 | 3.500 | 0900743
4483 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE |  | 02 | 0900745 | This is a Maintenance Resurfacing project, at CR 500 W from SR 2 to Johnson Rd.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-08 | 2010-03-30 | 2010-05-15 | 2010-04-22 | 481582.56 | 3.700 | 0900745
4484 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900771 | This is a Maintenance Resurfacing project, at CR 150 N/100 N/50N from SR 11 to US 50; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-22 | 2009-11-15 | 2009-11-12 | 322891.51 | 6.650 | 0900771
4485 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900772 | This project will improve the pavement from county road 300 north to county road 100 west. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 172031.99 | 2.990 | 0900772
4486 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900775 | This is a Maintenance Resurfacing project, at 300 N from CR 800 E to CR 850 E; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-03-25 | 2010-06-15 | 2010-06-03 | 35677.44 | 0.500 | 0900775
4487 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900778 | This project will improve sections and extend the life of Lower New Harmony Rd with a pavement surface overlay. | Other | 2009-09-01 | 2009-09-25 | 2009-11-30 | 2009-10-30 | 19953.75 | 1.000 | 0900778
4488 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900779 | This project will improve sections and extend the life of O'Donnel Rd/Brittle Bank Rd in Posey County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-30 | 2009-10-30 | 92811.38 | 0.400 | 0900779
4489 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900780 | This is a Maintenance Resurfacing project, at Co Road 30 - Basher Road from Reliance Rd to US 33.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-30 | 2010-06-08 | 2010-08-06 | 2010-08-07 | 151647.53 | 1.480 | 0900780
4490 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | POSEY |  | 08 | 0900781 | This project will improve sections and extend the life of Main street (Old SR 69) with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-25 | 2009-11-30 | 2009-10-30 | 8290 | 1.200 | 0900781
4491 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | Multiple | 0900782 | This is a preventive maintenance resurfacing project, on 8th Street from College Avenue to Lincoln Ave in Goshen to extend the pavement surface life. | Pavement Improvement | 2009-11-30 | 2010-06-08 | 2010-08-06 | 2010-08-07 | 215772.27 | 1.410 | 0900782
4492 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900783 | This project will improve sections and extend the life of Embree St in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-09-30 | 2009-09-29 | 142805.24 | 0.689 | 0900783
4493 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900784 | This project will improve sections and extend the life of Makemson Ave in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-09-30 | 2009-09-29 | 15214.16 | 0.133 | 0900784
4494 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GIBSON |  | 08 | 0900785 | This project will improve sections and extend the life of Seminary St in Gibson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2009-09-30 | 2009-09-29 | 34381.58 | 0.294 | 0900785
4495 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0900786 | This is a Maintenance Resurfacing project, at Lincoln Avenue from Indiana Avenue to Chicago Ave.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-18 | 2010-08-06 | 2010-08-20 | 94565.25 | 0.229 | 0900786
4496 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 0900794 | This is a Maintenance Resurfacing project, at 5th Street to 4th St.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-10 | 2010-08-31 | 2010-10-18 | 54193.65 | 0.500 | 0900794
4497 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900796 | This project will improve the pavement on county road 500 south from SR 39 to 830 East. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 219247.13 | 3.810 | 0900796
4498 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0900797 | This project will improve sections and extend the life of County Road 715West from SR 44 to BAse Road in Rush County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-10-14 | 2009-11-14 | 2009-10-20 | 169809.2 | 2.360 | 0900797
4499 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900798 | This project will improve the pavement 0n 600 south from 830 east to 1025 east. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 95646.67 | 1.590 | 0900798
4500 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FAYETTE |  | 06 | 0900799 | This project will improve sections and extend the life of Veterans Memorial Highway from SR 121 to SR 1 in Fayette County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-10-14 | 2009-11-13 | 2009-11-23 | 96258.85 | 0.950 | 0900799
4501 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0900802 | This project will improve sections and extend the life of old US 30 from the west county line to 350W in Kosciusko county with a preventive maintenance asphalt overlay. | Pavement Improvement | 2009-09-14 | 2009-10-07 | 2010-07-16 | 2010-07-12 | 687735.01 | 8.000 | 0900802
4502 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0900803 | This project will improve sections and extend the life of Old US 30 from current US 30 to the east County line road in Kosciusko county | Pavement Improvement | 2009-09-14 | 2009-10-07 | 2010-07-16 | 2010-07-12 | 768649.19 | 8.000 | 0900803
4503 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900806 | This project will improve the pavement on county road 850 east from 410 north to 200 north. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 135130.33 | 2.220 | 0900806
4504 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0900807 | This is a Maintenance Resurfacing project, at CR 200 N from US 50 to Bridge 91 over White River; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-03-25 | 2010-06-15 | 2010-06-03 | 53260.97 | 0.870 | 0900807
4505 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900809 | This project will improve the pavement on county road 150 south from SR 7 to county road 250 east. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 67492.94 | 0.580 | 0900809
4506 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900810 | This is a Maintenance Resurfacing project, at Roosevelt Road from Vale Park Road to LaPorte Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-07-01 | 2010-08-11 | 594444.98 | 1.770 | 0900810
4507 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900811 | This is a Maintenance Resurfacing project, at Calumet Avenue from GT&W RR (CN RR) to Vale Park Rd.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-07-01 | 2010-08-11 | 312690.97 | 1.150 | 0900811
4508 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900812 | This is a Maintenance Resurfacing project, at Joliet Road from SR 130 to Hayes Leonard Road (SR 150W); to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-07-01 | 2010-08-11 | 203117.59 | 1.150 | 0900812
4509 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900813 | This is a Safety project, at Valparaiso High School - Campbell St. at Vale Park Rd. & John Glenn Dr. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 21309.27 | 0.010 | 0900813
4510 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900814 | This is a Safety project, at Ben Franklin Middle School - Campbell St. at Ridgeland Ave N & Haas St. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 7046.65 | 0.010 | 0900814
4511 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900815 | This is a Safety project, at Northview Elementary School-Campbell St at Roane Ln N & Roseland Terrace S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 12526.98 | 0.010 | 0900815
4512 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900816 | This is a Safety project, at Parkview Elementary School-Roosevelt Rd. at Oak St N & Chicago St. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 9563.13 | 0.010 | 0900816
4513 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900817 | This is a Safety project, at Thomas Jefferson Middle School-Roosevelt Rd. at Glendale Blv. N & Illinois St. S; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 9563.13 | 0.010 | 0900817
4514 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900818 | This is a Safety project, at Central Elementary School - Morgan Blvd at Erie St.; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-03-05 | 2010-05-12 | 2010-07-01 | 2010-05-27 | 8947.99 | 0.010 | 0900818
4515 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900819 | This is a Scenic or Historic Highway Programs project, at Indiana Ave. between Lafayette St. & Washington St.; Lafayette-SR 130 to Indiana, to perform Enhancement work. | Transportation Enhancements | 2010-04-06 | 2010-04-23 | 2010-06-30 | 2010-08-27 | 258791.1 | 0.010 | 0900819
4516 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900823 | This is a Maintenance Resurfacing project, at CR 265 W/300 W from CR 70 S to US 50; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 59270.85 | 0.870 | 0900823
4517 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900824 | This is a Maintenance Resurfacing project, at CR 300 N from SR 3 to CR 600 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 234630.92 | 4.480 | 0900824
4518 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0900825 | This project will improve sections and extend the life of Jasper-Dubois Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-11-30 | 2009-12-03 | 748081.44 | 6.940 | 0900825
4519 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DUBOIS |  | 09 | 0900826 | This project will improve sections and extend the life of Rd 1100S in Dubois County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-11-30 | 2009-12-03 | 439834.62 | 5.330 | 0900826
4520 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900833 | This project will extend the life of the pavement on CR 350 N from CR 75 W to 90 E in Jenning county by doing asphalt resurface as Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 96059.05 | 1.650 | 0900833
4521 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900834 | This project will improve the pavement on CR 500 North from SR 3 to Base Road. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 155070.05 | 1.500 | 0900834
4522 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900835 | This project will improve the pavement on CR 550 East/ 600 East from county road 150 south to US 50. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 284003.6 | 5.230 | 0900835
4523 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900840 | This is a Maintenance Resurfacing project, at Oak Hill Road from US 20 to SR 49; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-04-07 | 2010-05-28 | 2010-05-26 | 194683.24 | 1.100 | 0900840
4524 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | Multiple | 0900841 | This is a Maintenance Resurfacing project, at Waverly Road from I-94 bridge abutment to US 12; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-04-08 | 2010-05-28 | 2010-05-25 | 208432.23 | 1.100 | 0900841
4525 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900842 | This is a Maintenance Resurfacing project, at Meridian Road, from US 6 to CR 1050 N; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-06-01 | 2010-05-07 | 265346.52 | 2.500 | 0900842
4526 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900843 | This is a Maintenance Resurfacing project, at CR 700N from Swanson road to Willowcreek Rd.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-01 | 2010-06-01 | 2010-05-07 | 97424.24 | 0.740 | 0900843
4527 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 0900844 | This is a Maintenance Resurfacing project, at North Calumet Road, from US 6 to Chesterton Town Limits; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-03-22 | 2010-07-01 | 2010-04-27 | 243891.2 | 1.230 | 0900844
4528 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 0900846 | This is a Maintenance Resurfacing project, at Division Road from SR 49 to 0.5 mi E of SR 49; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-07-07 | 2010-06-30 | 2010-07-16 | 107519.21 | 0.500 | 0900846
4529 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 0900848 | This is a Maintenance Resurfacing project, at CR 250W from Kankakee River to SR 8; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-06-30 | 2010-07-01 | 2010-07-16 | 286233.96 | 2.520 | 0900848
4530 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 0900849 | This is a Maintenance Resurfacing project, at Division Road from CR 400E to CR 575 E; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-07-07 | 2010-07-02 | 2010-07-16 | 189763.8 | 1.760 | 0900849
4531 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900851 | This is a Maintenance Resurfacing project, at Samuelson Road from 750 ft. South of Indiana Toll Road to Portage Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-15 | 2010-04-13 | 2010-06-01 | 2010-05-27 | 162562.74 | 1.050 | 0900851
4532 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900852 | This is a Maintenance Resurfacing project, at Central Avenue from Bridge over Willowcreek to Elm St.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-15 | 2010-04-13 | 2010-06-01 | 2010-05-27 | 156007.61 | 0.830 | 0900852
4533 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900853 | This is a Maintenance Resurfacing project, at Swanson Road from CR 700N to US 6; to perform Surface Treatment work. | Pavement Improvement | 2010-01-15 | 2010-04-13 | 2010-06-01 | 2010-05-27 | 211337.27 | 0.940 | 0900853
4534 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900855 | This is a Landscaping project, at Intersection of Willowcreek Rd & Country Side Pk Entrance on US 6 - Landscaping; to perform Landscaping work. | Transportation Enhancements | 2010-01-15 | 2010-04-05 | 2010-05-15 | 2010-05-14 | 85511.15 | 0.010 | 0900855
4535 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900856 | This is a Maintenance Resurfacing project, at Fir Road from McKinley Avenue to Spur line of Railroad; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-06-10 | 2010-09-30 | 2010-09-28 | 64603.59 | 0.850 | 0900856
4536 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900857 | This is a Maintenance Resurfacing project, at McKinley Avenue (US 20) from Division Street to Home St.; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-06-10 | 2010-09-30 | 2010-09-28 | 304493.53 | 1.290 | 0900857
4537 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900858 | This is a Safety project, at SR 933 - City Wide Traffic Signal Modernization; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2009-12-31 | 2010-02-01 | 2010-09-30 | 2010-03-23 | 282557.16 | 0.010 | 0900858
4538 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE |  | 01 | 0900860 | This is a Safety project, at Various roadways within the town of Winfield; to perform Signing work. | Safety/Traffic Management | 2010-02-22 | 2010-04-13 | 2010-04-30 | 2010-04-20 | 33561.99 | 0.010 | 0900860
4539 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE |  | 01 | 0900862 | This is a Maintenance Resurfacing project, at Randolph Street from 129th Avenue to 123rd Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-08-11 | 2010-07-31 | 2010-08-30 | 98462.18 | 0.880 | 0900862
4540 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900864 | This is a Maintenance Resurfacing project, at Twyckenham Drive from Rockne Drive to South Bend Avenue (SR 23); to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 174928.66 | 0.706 | 0900864
4541 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900865 | This is a Maintenance Resurfacing project, at Western Avenue from Walnut Street to Chapin St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 238542.75 | 0.400 | 0900865
4542 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900866 | This is a Maintenance Resurfacing project, at McKinley Avenue from 500ft East of Ironwood Drive to Preston Dr.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 145765.73 | 0.638 | 0900866
4543 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900867 | This is a Maintenance Resurfacing project, at Western Avenue from Lombardy Drive to Albert Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 114693.34 | 0.278 | 0900867
4544 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900868 | This is a Maintenance Resurfacing project, at Edison Road from Ironwood Drive to Hickory Rd.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 229667.43 | 0.952 | 0900868
4545 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900869 | This is a Maintenance Resurfacing project, at Ireland Road from East of Miami Street to Ironwood Dr.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 222483.43 | 0.866 | 0900869
4546 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900870 | This is a Maintenance Resurfacing project, at Portage Avenue from 370' N of Cleveland Road to Appaloosa Ln.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 86365.36 | 0.489 | 0900870
4547 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900871 | This is a Maintenance Resurfacing project, at Ireland Road from St. Joseph Street to High St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 128937.28 | 0.492 | 0900871
4548 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900872 | This is a Maintenance Resurfacing project, at Portage Avenue from Elwood Avenue to Lathrop St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 241847.6 | 1.050 | 0900872
4549 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900873 | This is a Maintenance Resurfacing project, at Lincolnway W from Chapin Street to Olive St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-08-30 | 2010-07-20 | 391219.1 | 1.356 | 0900873
4550 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900874 | This is a Maintenance Resurfacing project, at Main Street from Chippewa Street to Sample St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-10-21 | 2010-04-05 | 2010-07-15 | 2010-07-29 | 414470.8 | 1.991 | 0900874
4551 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900876 | This is a Safety project, at Sample Street and Mayflower Road Intersection; to perform Signs, Lighting, Signals And Markings work. | Safety/Traffic Management | 2010-02-22 | 2010-03-18 | 2010-06-15 | 2010-04-30 | 30497.75 | 0.010 | 0900876
4552 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900877 | This is a Safety project, at Angela Avenue and North Shore Drive Intersection; to perform Traffic Signal Maintenance work. | Safety/Traffic Management | 2010-02-22 | 2010-03-18 | 2010-06-15 | 2010-04-30 | 27775 | 0.010 | 0900877
4553 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900885 | This is a Maintenance Resurfacing project, at CR 800 W from 825 S to SR 250; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 88976.43 | 1.470 | 0900885
4554 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900886 | This is a Maintenance Resurfacing project, at CR 825 S from CR 800 W to CR 900 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 96791.11 | 1.130 | 0900886
4555 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900889 | This project will improve the pavement on County Road 90 west/95 west from county road 115 to Base Road. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 94768.93 | 0.950 | 0900889
4556 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0900890 | This is a Maintenance Resurfacing project, at County Road 10 - John Weaver Parkway from CR 10 to CR 6; to perform Resurface over Asphalt Pavement work. | Pavement Improvement | 2010-01-21 | 2010-04-29 | 2010-08-31 | 2010-08-20 | 373840.12 | 2.250 | 0900890
4557 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0900891 | This is a Maintenance Resurfacing project, at Beardsley Ave from Nappanee St to 100' W of Beech St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-21 | 2010-04-29 | 2010-08-31 | 2010-08-20 | 50018.7 | 1.190 | 0900891
4558 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | OHIO |  | 09 | 0900897 | This is a Maintenance Resurfacing project, at Cass Union Rd from Aberdeen Rd/SR 56 to SR 262; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-05 | 2010-06-30 | 2010-05-24 | 358550.36 | 6.600 | 0900897
4559 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | OHIO |  | 09 | 0900898 | This is a Maintenance Resurfacing project, at Hartford pike from Woods Ridge Road to Nelson Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-08 | 2010-06-30 | 2010-05-24 | 156143.96 | 1.700 | 0900898
4560 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | OHIO |  | 09 | 0900899 | This is a Maintenance Resurfacing project, at Nelson Rd from Hartford Pike to Rising Sun Limits; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-08 | 2010-06-30 | 2010-05-24 | 476532.42 | 3.700 | 0900899
4561 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900900 | This project will improve sections and extend the life of Centenary Rd. from Henderson Ford Road to 1 mile South of SR 144 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 277355.96 | 3.400 | 0900900
4562 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900901 | This project will improve sections and extend the life of old SR 37 from Martinsville City Limits to SR 37 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 111468.8 | 1.700 | 0900901
4563 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900902 | This project will improve sections and extend the life of Paragon Rd. from SR 67 to SR 37 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 286593.27 | 5.700 | 0900902
4564 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0900904 | This is a Maintenance Resurfacing project, at Lancaster St from Adams St to Bond St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-11 | 2010-06-12 | 2010-03-30 | 53499.82 | 1.000 | 0900904
4565 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0900905 | This is a Maintenance Resurfacing project, at Western Ave from Decker Dr.; to Midway St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-11 | 2010-06-12 | 2010-03-30 | 35310.83 | 0.400 | 0900905
4566 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WELLS |  | 06 | 0900906 | This is a Maintenance Resurfacing project, at Midway St from Western Ave.; to W Washington St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-11 | 2010-06-12 | 2010-03-30 | 88840.16 | 0.250 | 0900906
4567 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900911 | This is a project, at Joliet Street (93rd Avenue) at US 41; to perform Storm Sewer Repair Or Replacement work. | Other | 2010-03-04 | 2010-05-26 | 2010-07-31 | 2010-09-03 | 375915.85 | 0.010 | 0900911
4568 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900915 | This is a Safety project, at SR 933 - Various locations City wide; to perform Sign Modernization (Series Of Units) work. | Safety/Traffic Management | 2009-12-31 | 2010-08-24 | 2010-09-30 | 2010-11-09 | 68709.01 | 0.010 | 0900915
4569 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900916 | This project will improve sections and extend the life of Rueben Dr. from Old SR 37 to SR 37 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 33596.3 | 0.500 | 0900916
4570 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900917 | This project will improve sections and extend the life of Rob Hill Rd fROM SR 39 TO SR 67 with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 244217.24 | 3.400 | 0900917
4571 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 0900918 | This project will improve sections and extend the life of Blue Bluff Rd. from Centerton Rd. to Bridge with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-07-19 | 2010-08-30 | 2010-08-31 | 92905.41 | 1.200 | 0900918
4572 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900923 | This is a Maintenance Resurfacing project, at Third St. from Cherry St. to Montgomery St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 54497.62 | 0.562 | 0900923
4573 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0900927 | This is Added Travel Lanes on I465, 82nd St from 0.2 mi W of I-465 to 0.14 mi E of I-465 | Pavement Widening | 2010-11-01 | 2010-12-28 | 2011-10-15 | 2012-04-09 | 2347714.92 | 0.010 | 0900927
4574 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900929 | This is a Maintenance Resurfacing project, at Montgomery St from Main St to Third St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 72205.42 | 0.180 | 0900929
4575 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900930 | This project will improve the pavement on county road 500 east from county road 560 north to the county line. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 344662.67 | 6.140 | 0900930
4576 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900931 | This project will improve the pavement on Base Road/ County Road 20 West near North Vernon. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-07-01 | 2010-06-30 | 158550.61 | 3.090 | 0900931
4577 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900932 | This is a Maintenance Resurfacing project, at CR-115S from CR-75W to Vernon; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-29 | 2010-06-01 | 2010-06-25 | 64543.51 | 0.010 | 0900932
4578 | INDIANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | JENNINGS |  | 09 | 0900935 | This project will improve sections and extend the life of Greensburg Street from US 50 to Woodlaen Drive in Jennings County with a pavement surface overlay. | Pavement Improvement | 2009-11-23 | 2010-03-08 | 2010-07-15 | 2010-06-18 | 44291.19 | 0.440 | 0900935
4579 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0900937 | This is a Maintenance Resurfacing project, at US 41 to SR 341; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-20 | 2010-07-15 | 2010-07-14 | 477898.98 | 3.000 | 0900937
4580 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0900938 | This is a Maintenance Resurfacing project ,at SR 341 to Fountain/Montgomery County Line; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-20 | 2010-07-15 | 2010-07-14 | 272184.84 | 5.000 | 0900938
4581 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0900939 | This is a Maintenance Resurfacing project, at Covington City Limits to US 41; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-20 | 2010-07-15 | 2010-07-14 | 826726.43 | 7.800 | 0900939
4582 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900940 | This is a Maintenance Resurfacing project, at Main St from Lake Rd to Montgomery St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 150521.35 | 1.500 | 0900940
4583 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0900941 | This project will improve sections and extend the life of Michigan Road from West Street to Green Road in Jefferson County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-17 | 2009-11-15 | 2009-10-07 | 164209.29 | 1.890 | 0900941
4584 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900944 | This project will improve the traffic signs in the town of Galveston in Cass County. | Safety/Traffic Management | 2009-09-15 | 2009-10-26 | 2009-11-30 | 2009-11-23 | 41888.73 | 0.010 | 0900944
4585 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900945 | This project will improve the traffic signs in the town of Royal Center in Cass County. | Safety/Traffic Management | 2009-09-15 | 2009-10-26 | 2009-11-30 | 2009-11-23 | 5221.19 | 0.010 | 0900945
4586 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0900946 | This project will improve the traffic signs in the town of Walton in Cass County. | Safety/Traffic Management | 2009-09-15 | 2009-10-26 | 2009-11-30 | 2009-11-23 | 10075.69 | 0.010 | 0900946
4587 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900948 | This project will improve sections and extend the life of Patterson Rd from Watkins St to Kenilworth Rd with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 74686.15 | 0.700 | 0900948
4588 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900949 | This project will improve sections and extend the life of Beech Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 79231.77 | 0.750 | 0900949
4589 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900950 | This project will improve sections and extend the life of Timothy Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 53896.63 | 0.500 | 0900950
4590 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900952 | This project will improve sections and extend the life of Tamarach Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 396092.45 | 3.600 | 0900952
4591 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900953 | This project will improve sections and extend the life of Kern Rd in St Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 170869.44 | 1.900 | 0900953
4592 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900954 | This project will improve sections and extend the life of Oak Rd from New Rd to Roosevelt Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 195944.75 | 2.000 | 0900954
4593 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900955 | This project will improve sections and extend the life of Walkerton Trail from 0.01 MI S of Georgia St to 0.1 MI S of SR 23 with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 95534.15 | 0.800 | 0900955
4594 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900956 | This project will improve sections and extend the life of Main St in Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 30644.32 | 0.120 | 0900956
4595 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900957 | This project will improve sections and extend the life of Washington St in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 24899.42 | 0.100 | 0900957
4596 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900958 | This project will improve sections and extend the life of Patterson Rd from 0.04 MI E of Beeckler Court to Watkins St with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 21998.43 | 0.090 | 0900958
4597 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900959 | This project will improve sections and extend the life of Walkerton Trail in St. Joseph county from Spruce Rd to 0.1 MI S of Georgia St with a preventive maintenance pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 132570.87 | 0.050 | 0900959
4598 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900960 | This project will improve sections and extend the life of Mayflower Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 26719.91 | 0.300 | 0900960
4599 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900961 | This project will improve sections and extend the life of Sumption Trail in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 46175.6 | 0.800 | 0900961
4600 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900962 | This project will improve sections and extend the life of Oak Rd from Roosevelt Rd to Kern Rd in St. Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 56716.64 | 1.000 | 0900962
4601 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900963 | This project will improve sections and extend the life of Beech Rd in Joseph County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-01 | 2010-06-30 | 2010-06-10 | 149295.99 | 3.200 | 0900963
4602 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900964 | This project will improve traffic signs in Walkerton in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 50414.87 | 0.010 | 0900964
4603 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900965 | This project will improve the traffic signs in North Liberty in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 38045.14 | 0.010 | 0900965
4604 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900966 | This project will improve the signs in New Carlisle in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 48885.14 | 0.010 | 0900966
4605 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900967 | This project will improve the traffic signs in Lakeville in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 35355.85 | 0.010 | 0900967
4606 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0900968 | This project will improve the traffic signs in St Joseph County. | Safety/Traffic Management | 2009-09-15 | 2010-03-15 | 2010-06-30 | 2010-06-09 | 148249.03 | 0.010 | 0900968
4607 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900969 | This is a Maintenance Resurfacing project, at Morse Street from 149th to Lowell Corp Limits; to perform Surface Treatment work. | Pavement Improvement | 2010-01-11 | 2010-05-19 | 2010-06-30 | 2010-07-20 | 536728.84 | 3.360 | 0900969
4608 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0900970 | This is a Maintenance Resurfacing project, at Cedar Lake Road form 121st to 133rd; to perform Surface Treatment work. | Pavement Improvement | 2010-01-12 | 2010-04-23 | 2010-06-30 | 2010-07-20 | 262314.46 | 1.640 | 0900970
4609 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PIKE |  | 08 | 0900982 | This is a Maintenance Resurfacing project, at E Old SR 64 - SR 257 to CR 1100E; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-04 | 2010-08-31 | 2010-06-25 | 250364.52 | 3.700 | 0900982
4610 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PIKE |  | 08 | 0900983 | This is a Maintenance Resurfacing project, at CR 500E to SR 257; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-05-04 | 2010-08-31 | 2010-06-25 | 105812.74 | 1.560 | 0900983
4611 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0900987 | This is a trail construction project for pedestrians and bicycles at Tell City Riverfront, 1,800' south of Washington St to 3,400' north of the plaza in Tell City in Perry county using enhancement funds. | Transportation Enhancements | 2009-12-18 | 2010-05-19 | 2010-08-31 | 2010-10-19 | 430736.91 | 1.010 | 0900987
4612 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900988 | This project will improve sections and extend the life of Dekalb County Road 48 with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-06 | 2010-10-31 | 2010-06-07 | 231953.6 | 1.600 | 0900988
4613 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900991 | This is a Maintenance Resurfacing project, at Elm St from Lake Rd to SR 56; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 93718.73 | 1.000 | 0900991
4614 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900993 | This project will improve sections and extend the life of Wayne Street from Cedar Street to Walnut Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 145818.95 | 0.770 | 0900993
4615 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0900994 | This is a Maintenance Resurfacing project, at Arlington Ave. from 38th St. to 56th St.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-03-01 | 2010-06-30 | 2010-06-30 | 1562333.39 | 2.000 | 0900994
4616 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0900995 | This is a Maintenance Resurfacing project, at Beechwood and Allen St. from SR 56 to US 31; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 31415.53 | 0.460 | 0900995
4617 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900996 | This project will improve sections and extend the life of N. Commerce Drive in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 36035.67 | 0.210 | 0900996
4618 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900997 | This project will improve sections and extend the life of Center Street from US 6 to Rope Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 52177.97 | 0.480 | 0900997
4619 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900998 | This project will improve sections and extend the life of Rope Street from Center Street to SR 427 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 72891.25 | 0.470 | 0900998
4620 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0900999 | This project will improve sections and extend the life of Walnut Street from Albright Street to SR 39 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 43813.57 | 0.250 | 0900999
4621 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901000 | This project will improve sections and extend the life of Walnut Street from Center Street to Wayne Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-09-04 | 2009-09-30 | 2009-10-02 | 45097.81 | 0.250 | 0901000
4622 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901004 | This is a Maintenance Resurfacing project, at Colfax Street from Belshaw Road to 231st Ave.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-06-04 | 2010-06-02 | 603706.9 | 4.900 | 0901004
4623 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901005 | This is a Maintenance Resurfacing project, at 231st Avenue from Monon Road to Colfax St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-06-04 | 2010-06-02 | 300548.26 | 2.850 | 0901005
4624 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0901021 | This is a Maintenance Resurfacing project, at Cherry St. from US 31 to Third St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 36405.8 | 0.610 | 0901021
4625 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0901022 | This is a Maintenance Resurfacing project, at Wardell St from US 31 to Third St.; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-02-24 | 2010-04-16 | 2010-07-25 | 2010-06-11 | 71376.98 | 0.610 | 0901022
4626 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0901023 | This project will improve sections and extend the life of County Road 400North from County Road 850 East to County Road 900 East in Howard County with a pavement surface overlay. | Transportation Enhancements | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 39469.5 | 0.500 | 0901023
4627 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PERRY |  | 09 | 0901024 | This is a Maintenance Resurfacing project, at Gerald Rd (CR 10) to SR 70; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-04-14 | 2010-08-31 | 2010-07-21 | 361512.65 | 3.900 | 0901024
4628 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901026 | This project will improve sections and extend the life of New Market Road from SR 3 to Zimmerman Road in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-29 | 2010-04-30 | 2009-11-02 | 191540.64 | 3.100 | 0901026
4629 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901027 | This project will improve sections and extend the life of Camp Creek-Bethlehem Road from Flint Road to Bethlehem New Washington in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-08-20 | 2009-09-29 | 2009-11-13 | 2009-10-22 | 166794.26 | 3.070 | 0901027
4630 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901029 | This project will improve sections and extend the life of Charlestown-Memphis Road from US 31 to SR 160 in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-10-09 | 2009-10-30 | 2010-04-30 | 2009-11-20 | 298381.34 | 5.900 | 0901029
4631 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0901030 | This project will improve sections and extend the life of County Road 750West from County Road 300 North to County Road 400 North in Howard County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 57809.87 | 1.000 | 0901030
4632 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD |  | 05 | 0901031 | This project will improve sections and extend the life of County Road 100North from County Road 400 East to County Road 500 East in Howard County with a pavement surface overlay. | Pavement Improvement | 2009-09-14 | 2009-09-24 | 2009-11-13 | 2009-11-13 | 68854.09 | 1.000 | 0901031
4633 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON |  | 05 | 0901032 | This is a Maintenance Resurfacing project, at 146th St from Hamilton/Boone County line to Ditch Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-14 | 2010-06-18 | 2010-06-03 | 259078.66 | 3.050 | 0901032
4634 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901036 | This project will improve sections and extend the life of Salisbury Road from Nolands Fork Road to Williamsburg Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-13 | 2009-11-03 | 155421.92 | 0.650 | 0901036
4635 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901037 | This project will improve sections and extend the life of 37th Street from Hodgin Road to US 40 in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-20 | 2009-11-10 | 544186.16 | 1.140 | 0901037
4636 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901038 | This project will improve sections and extend the life of Industries Road from Williamsburg Pike to Union Pike in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-06 | 2009-11-03 | 219725.43 | 0.610 | 0901038
4637 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901039 | This project will improve sections and extend the life of Southway 31 in Fulton County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-05 | 2009-11-25 | 2009-10-16 | 115530.27 | 1.100 | 0901039
4638 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901040 | This is a Maintenance Resurfacing project, at Old US 31 N from CR 350N to SR 110; to perform Surface Treatment work. | Pavement Improvement | 2009-10-14 | 2009-10-26 | 2010-06-30 | 2009-11-23 | 447315.1 | 4.700 | 0901040
4639 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901041 | This is a Maintenance Resurfacing project, at Greenwood Avenue between SR 231 and SR 55; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-16 | 2010-04-14 | 2010-06-01 | 2010-06-01 | 233169.05 | 2.560 | 0901041
4640 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901042 | This is a Maintenance Resurfacing project, at Court Street from the North side of Town Square to 121st. St.; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-12-16 | 2010-04-14 | 2010-06-01 | 2010-06-01 | 346231.85 | 1.280 | 0901042
4641 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901043 | This is a Maintenance Resurfacing project, at 49th Avenue from Broadway to Grant; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-03-31 | 2010-06-01 | 2010-06-01 | 253100.22 | 0.750 | 0901043
4642 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901044 | This is a Maintenance Resurfacing project, at 15th Avenue from I-65 to Martin Luther King Dr.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-04-06 | 2010-06-01 | 2010-06-01 | 201811.89 | 0.650 | 0901044
4643 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901045 | This is a Maintenance Resurfacing project, at 35th Avenue from Broadway to Martin Luther King Dr.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-03-31 | 2010-06-01 | 2010-06-01 | 401067.83 | 0.930 | 0901045
4644 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901046 | This is a preventive maintenanc eresurfacing project, at Olson Road from CR 700 W to SR 17 in Fulton county to provide 1 inch of asphalt to extend the pavement life. | Pavement Improvement | 2009-10-14 | 2009-10-26 | 2010-06-30 | 2009-11-23 | 206332.77 | 3.500 | 0901046
4645 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901047 | This project will improve sections and extend the life of Wabash Ave with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-10-05 | 2009-11-25 | 2009-10-16 | 108235.99 | 1.600 | 0901047
4646 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901048 | This is a Maintenance Resurfacing project, at CR 550 S from CR 1200 W(Fulton/Pulaski Co Line) to SR 17; to perform Surface Treatment work. | Pavement Improvement | 2009-10-14 | 2009-10-26 | 2010-06-30 | 2009-11-23 | 167279.28 | 2.800 | 0901048
4647 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 0901049 | This is a Maintenance Resurfacing project, at CR 600 S from SR 25 to CR 250 E; to perform Surface Treatment work. | Pavement Improvement | 2009-10-14 | 2009-10-26 | 2010-06-30 | 2009-11-23 | 163888.4 | 2.800 | 0901049
4648 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901050 | This project will improve sections and extend the life of Engle Road from St John Road to Floyd County in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-27 | 2010-04-30 | 2009-11-09 | 104538.65 | 1.220 | 0901050
4649 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901051 | This is a Maintenance Resurfacing project, at Hibernia Rd. from SR 62 to Charlestown Bethlehem Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2009-10-20 | 2009-11-13 | 2009-11-02 | 100050.8 | 1.430 | 0901051
4650 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901052 | This project will improve sections and extend the life of Marble Hill Road from SR 62 to Gill Road in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-29 | 2010-04-30 | 2009-11-02 | 132586.95 | 1.720 | 0901052
4651 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0901057 | This is a Maintenance Resurfacing project, at Old State Rd 62 from US 421 to SR 62; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2009-10-26 | 2009-11-15 | 2009-11-14 | 135612.23 | 1.970 | 0901057
4652 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901059 | This is a Maintenance Resurfacing project, at Main Street from CR 800 to the RR Tracks at the town limit; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-05-28 | 2010-06-25 | 2010-06-25 | 357838.25 | 1.340 | 0901059
4653 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0901060 | This project will improve the pavement with a preventive maintenance resurface on Base Road/County Road 25 East from White River to SR 2 in Jackson county. | Pavement Improvement | 2010-02-20 | 2010-03-25 | 2010-07-01 | 2010-06-09 | 484067.47 | 5.670 | 0901060
4654 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901062 | This project will improve sections and extend the life of Martinsburg Knob Road from Borden Greenville Road to Washington County in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-08 | 2009-11-13 | 2009-11-04 | 183308.07 | 3.690 | 0901062
4655 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901063 | This project will improve sections and extend the life of New Hope Church Road from Bethlehem Road to Jefferson County in Clark County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-29 | 2010-04-30 | 2009-11-02 | 79685.42 | 1.100 | 0901063
4656 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901065 | This is a Maintenance Resurfacing project, at 38th Street from 460 feet E of Adams Street/SR 15 to S Todd Street to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 557324.66 | 1.680 | 0901065
4657 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901066 | This is a Maintenance Resurfacing project, at Adams Street from 29th street to 26th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 119170.52 | 0.350 | 0901066
4658 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901067 | This is a Maintenance Resurfacing project, at Nebraska Street from 26th Street to 23rd Street to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 477712.38 | 1.480 | 0901067
4659 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0901068 | This is a Maintenance Resurfacing project, at Adams Street from Railroad Tracks S of 11th Street to 3rd St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 226375.74 | 0.580 | 0901068
4660 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901069 | This is a Maintenance Resurfacing project, at Washington Street from 38th street to Wabash Ave.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-11-12 | 2010-07-02 | 2010-09-20 | 959542.41 | 2.670 | 0901069
4661 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901070 | This project will improve sections and extend the life of Kem Road from Miller Avenue to Wabash Avenue in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-13 | 2009-10-31 | 2009-11-08 | 246550.42 | 1.030 | 0901070
4662 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901071 | This is a Maintenance Resurfacing project, at Allisonville Rd from Fall Creek Rd to 46th St.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-24 | 2010-06-04 | 2010-06-30 | 2010-08-20 | 210312.41 | 0.050 | 0901071
4663 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901072 | This is a Maintenance Resurfacing project, at 62nd St from Keystone Ave to Allisonville Rd.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-03-15 | 2010-06-30 | 2010-07-01 | 482262.69 | 1.300 | 0901072
4664 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901073 | This is a Maintenance Resurfacing project, at State St from I-265 to Green Valley Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-04-09 | 2010-06-19 | 2010-06-18 | 265600 | 0.730 | 0901073
4665 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901074 | This is a Maintenance Resurfacing project, at Old SR 37 S, from SR 37 to Rogers St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-03-29 | 2010-07-30 | 2010-05-24 | 180715.53 | 0.950 | 0901074
4666 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901076 | This is a preventive maintenance resurfacing project, at Old SR 37 N in Monroe county , from Whisnand Rd to Wylie Rd. to extend the life of the pavement. | Pavement Improvement | 2009-11-23 | 2010-04-08 | 2010-07-30 | 2010-08-18 | 236894.85 | 2.340 | 0901076
4667 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901077 | This is a Maintenance Resurfacing project, at Monroe Dam Rd, from SR 37 to Strain Ridge Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-29 | 2010-07-30 | 2010-05-27 | 106402.11 | 0.773 | 0901077
4668 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901078 | This is a Maintenance Resurfacing project, at Rockport Road from Victor Pike to May Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-06 | 2010-07-30 | 2010-07-29 | 352592.83 | 3.128 | 0901078
4669 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901079 | This is a Maintenance Resurfacing project, at Fairfax Road, from Pointe Rd to Dillman Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-05 | 2010-07-30 | 2010-07-22 | 660035.73 | 4.720 | 0901079
4670 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901080 | This is a Bridge Replacement (no added capacity) project, at Bridge over Lick Creek in Sarah Bolton Park; to perform Bridge Replacement, Special work. | Bridge Replacement | 2010-02-22 | 2010-04-06 | 2010-09-03 | 2010-09-02 | 341363.39 | 0.010 | 0901080
4671 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901081 | This is a preventive maintenance resurfacing project, at Greenfield Avenue (formerly SR 238) in Hamilton county to extend the pavement life. | Pavement Improvement | 2009-12-31 | 2010-05-17 | 2010-06-30 | 2010-06-29 | 279543.94 | 2.880 | 0901081
4672 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901082 | This is a Maintenance Resurfacing project, at Emerson Ave from 38th St to 56th St.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-03-18 | 2010-09-30 | 2010-09-24 | 1490522 | 2.000 | 0901082
4673 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901083 | This is a Maintenance Resurfacing project, at Paoli Pike from Hilltop Rd to 267 feet W of Boe Creek Dr.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-31 | 2010-05-22 | 2010-07-21 | 259358.57 | 1.970 | 0901083
4674 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901084 | This is a Maintenance Resurfacing project, at Georgetown-Greenville Road from Church Rd.; to Harrison St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-25 | 2010-04-08 | 2010-06-12 | 2010-06-07 | 363000 | 6.500 | 0901084
4675 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901086 | This project will improve sections and extend the life of Garthwaite Road in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 100685.68 | 1.120 | 0901086
4676 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901087 | This project will improve sections and extend the life of County Road 300South from County Road 300 West to SR 37 in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 218205.79 | 3.000 | 0901087
4677 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901088 | This project will improve sections and extend the life of County Road 600East from SR 18 to County Road 700 North in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 467332.26 | 6.760 | 0901088
4678 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901089 | This project will improve sections and extend the life of County Road 200North from County Road 300 East to County Road 600 East in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 218843.62 | 3.000 | 0901089
4679 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901090 | This project will improve sections and extend the life of County Road 400East from Walnut Creek to County Road 200 South in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 98260.27 | 1.500 | 0901090
4680 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901091 | This project will improve sections and extend the life of County Road 950East from Matthews Town Limits to SR 26 in Grant County with a pavement surface overlay. | Pavement Improvement | 2009-09-02 | 2009-10-01 | 2009-11-07 | 2009-12-02 | 224068.95 | 2.270 | 0901091
4681 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARSHALL |  | 02 | 0901093 | This project will improve sections and extend the life of Olive Trail from 13th Road to Overmyer Drive in Marshall County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2010-04-21 | 2010-07-02 | 2010-06-30 | 66651.01 | 3.709 | 0901093
4682 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | BLACKFORD |  | 06 | 0901096 | This project will improve sections and extend the life of Wabash Avenue from Kickapoo Street to Park Avenue in Blackford County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-12 | 2009-10-30 | 2009-10-27 | 73667.35 | 0.300 | 0901096
4683 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901097 | This project will improve sections and extend the life of County Road 40 from SR 1 to State Line in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-01 | 2009-10-30 | 2009-11-04 | 255271.27 | 3.400 | 0901097
4684 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901098 | This project will improve sections and extend the life of Auburn Drive from Diehl Drive to Wayne Street in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-06 | 2009-10-31 | 2009-11-04 | 153639.84 | 1.420 | 0901098
4685 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901099 | This project will improve sections and extend the life of Main Street from Gates Cove to County Road 36 in Dekalb County with a pavement surface overlay. | Pavement Improvement | 2009-09-01 | 2009-10-06 | 2009-10-31 | 2009-11-04 | 153688.07 | 1.420 | 0901099
4686 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS | INDIANAPOLIS | 04 | 0901100 | This is a Maintenance Resurfacing project, at From 2500 N. Dan Jones to approx. 3000 S. Dan Jones Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-02-22 | 2010-05-01 | 2010-05-05 | 1062064.84 | 4.200 | 0901100
4687 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS | INDIANAPOLIS | 04 | 0901101 | This is a Safety project, at CR 200 N & Ronald Reagan Pkwy.; to perform Traffic Signals, New Or Modernized work. | Safety/Traffic Management | 2009-10-23 | 2009-11-16 | 2010-06-30 | 2010-03-24 | 169869.75 | 0.010 | 0901101
4688 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901102 | This is a Maintenance Resurfacing project, at Wiggins St. to just south of Robinison St.; to perform Resurface over Asphalt Pavement work. | Pavement Improvement | 2009-11-23 | 2010-05-18 | 2010-06-30 | 2010-07-02 | 260920.91 | 0.530 | 0901102
4689 | INDIANA | Completed | C220,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901106 | This is a Facilities for Pedestrians and Bicycles project, at New trail from Clarendon Dr. to Edgewater Dr. paralled to Carrigan Rd.; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-05-14 | 2010-07-12 | 2010-11-15 | 2011-05-06 | 1263268.75 | 0.305 | 0901106
4690 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901110 | This is a Bridge Rehabilitation (no added capacity) project, at Emerson Ave. over CSX Railroad; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2009-12-30 | 2010-02-22 | 2010-07-31 | 2010-06-23 | 383562.79 | 0.028 | 0901110
4691 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901112 | This is a Maintenance Resurfacing project, between Battleground Town limits & Tyler Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-05 | 2010-03-19 | 2010-06-30 | 2010-05-13 | 247152.52 | 0.040 | 0901112
4692 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901113 | This is a Maintenance Resurfacing project, at Ridge Road from Colfax Avenue to Grant St.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-13 | 2010-04-30 | 2010-06-30 | 2010-07-23 | 967860.55 | 2.990 | 0901113
4693 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0901122 | This is a Maintenance Resurfacing project, at NW 21st St to Front St.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-08-31 | 2010-07-06 | 70179.83 | 0.760 | 0901122
4694 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0901123 | This is a Maintenance Resurfacing project, at US 50 to W Main St.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-08-31 | 2010-07-06 | 43893.86 | 0.380 | 0901123
4695 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0901124 | This is a Maintenance Resurfacing project, at Jackson St to Wykoff Ln.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-08-31 | 2010-07-06 | 40996.12 | 0.380 | 0901124
4696 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DAVIESS |  | 08 | 0901125 | This is a Maintenance Resurfacing project, at Field Ave to NW 21st St.; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-08-31 | 2010-07-06 | 45965.06 | 0.510 | 0901125
4697 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 0901126 | This is a Maintenance Resurfacing project, at Leota Rd from Boatman Rd to US 31; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-29 | 2010-05-31 | 2010-05-06 | 156789.65 | 2.200 | 0901126
4698 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901127 | This is a Maintenance Restoration & Rehabilitation project, at 56th St. from Boy Scout Rd. to Ciato Rd.; to perform Pavement, Other work. | Pavement Improvement | 2010-04-01 | 2010-06-03 | 2010-08-15 | 2010-08-05 | 233325 | 0.500 | 0901127
4699 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901128 | This is a Bridge Rehabilitation (no added capacity) project, at Westfield Blvd. over White River; to perform Bridge Deck Overlay work. | Bridge Improvement | 2009-12-30 | 2010-02-22 | 2010-07-31 | 2010-06-23 | 327808.54 | 0.096 | 0901128
4700 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901129 | This is a Maintenance Resurfacing project, at Edwardsville-Galena Rd from Oaks Road to Bridge over Little Indian Creek; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-16 | 2010-05-05 | 2010-07-19 | 191300 | 3.600 | 0901129
4701 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0901130 | This is a Maintenance Resurfacing project at Washington Blvd from Mulberry St. to Market St. to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-30 | 2009-11-02 | 2009-11-30 | 2009-11-19 | 52646.81 | 0.340 | 0901130
4702 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901131 | This is a Maintenance Resurfacing project, at Tibbs Ave. from 16th St. to Lafayette Rd.; to perform Partial 3-R work. | Pavement Improvement | 2009-12-31 | 2010-04-12 | 2010-08-16 | 2010-07-12 | 323096.07 | 1.200 | 0901131
4703 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901132 | This is a Maintenance Resurfacing project, at Thompson Rd. from Emerson Ave. to Franklin Rd.; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-03-03 | 2010-08-16 | 2010-09-22 | 1199315.16 | 3.400 | 0901132
4704 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901133 | This is a Maintenance Resurfacing project, at Southeastern Ave. from Raymond St. to Sheridan Ave.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-02 | 2010-10-04 | 2012-03-30 | 1275406.63 | 0.080 | 0901133
4705 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901134 | This is a Maintenance Resurfacing project, at Sam Jones Parkway from I-465 to I-70; to perform Partial 3-R work. | Pavement Improvement | 2009-12-31 | 2010-04-12 | 2010-08-16 | 2010-07-12 | 656540.94 | 1.300 | 0901134
4706 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901136 | This is a Maintenance Resurfacing project, at Central Avenue from Benton Street to County Line Rd.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-19 | 2010-04-06 | 2010-06-09 | 2010-08-02 | 486985.59 | 3.000 | 0901136
4707 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE |  | 02 | 0901137 | This is a Maintenance Resurfacing project, at Wozniak Road from SR 2 to CR 400 N; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-06 | 2010-04-06 | 2010-05-15 | 2010-05-05 | 1019878 | 7.300 | 0901137
4708 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901138 | This is a Reconstruction (no added capacity) project, at Summit, Between Wirtz Road and Jennings Place; to perform Other Type Project (Miscellaneous) work. | Pavement Improvement | 2010-02-25 | 2010-06-13 | 2010-07-01 | 2010-07-20 | 166791.85 | 0.010 | 0901138
4709 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | PULASKI |  | 02 | 0901139 | This project will improve sections and extend the life of County Road 500S outh from Market Street to county road 1050 west in Pulaski County with a pavement surface overlay. | Pavement Improvement | 2009-12-31 | 2010-07-23 | 2010-08-27 | 2010-08-17 | 91016.58 | 3.860 | 0901139
4710 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901140 | This is a Maintenance Resurfacing project, at Wabash Avenue from Calumet Road to Waverly Rd.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-13 | 2010-07-01 | 2010-06-04 | 105466.09 | 0.600 | 0901140
4711 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901141 | This is a Maintenance Resurfacing project, at 11th Street from CR 1100 N to Porter Ave.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-13 | 2010-07-01 | 2010-06-04 | 133054.67 | 0.910 | 0901141
4712 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901142 | This is a Maintenance Resurfacing project, at Porter Avenue from 15th St. to 23rd St.; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-13 | 2010-07-01 | 2010-06-04 | 84335.06 | 0.520 | 0901142
4713 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WASHINGTON |  | 09 | 0901145 | This is a Maintenance Resurfacing project, at SR 135 - Market St. from Washington Blvd to Alpine St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-30 | 2009-11-02 | 2009-11-30 | 2009-11-19 | 91557.87 | 0.720 | 0901145
4714 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901148 | This is a Maintenance Resurfacing project, at Raymond St. from Shelby St. to Southeastern Ave.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-02 | 2010-10-04 | 2012-03-30 | 2847684.79 | 3.600 | 0901148
4715 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901149 | This is a Bridge Rehabilitation (no added capacity) project, at Holt Rd. bridge over Big Eagle Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2009-12-03 | 2010-06-01 | 2010-09-30 | 2010-09-28 | 822708.1 | 0.068 | 0901149
4716 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901151 | This is a Maintenance Resurfacing project, at Franklin Way/Rd. from 21st St. to 30th St.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-02 | 2010-10-04 | 2012-03-30 | 465877.43 | 1.000 | 0901151
4717 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901152 | This is a Bridge Rehabilitation (no added capacity) project, at Cumberland Rd. over White River; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-02-22 | 2010-06-01 | 2010-09-01 | 2010-07-30 | 394253.67 | 0.095 | 0901152
4718 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901153 | This is a Maintenance Resurfacing project, at Walnut St. from Southport Rd. to Stop 10 Rd.; to perform Resurface PCC Pavement (Partial 3/R Standards) work. | Pavement Improvement | 2010-01-13 | 2010-06-11 | 2010-08-16 | 2010-08-16 | 126422.55 | 0.542 | 0901153
4719 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901154 | This is a Maintenance Resurfacing project, at Lantern Rd. from South St. to Lantern Wood Dr.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 116207.65 | 0.750 | 0901154
4720 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WABASH |  | 05 | 0901155 | This project will improve sections and extend the life of County Road 250South from Old Sr 15 to America Road in Wabash County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2010-05-06 | 2010-06-18 | 2010-06-18 | 441936.72 | 4.940 | 0901155
4721 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901156 | This is a Maintenance Resurfacing project, at Hague Rd. from 96th St. to 116th St.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 200546.17 | 2.000 | 0901156
4722 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901157 | This is a Maintenance Resurfacing project, at Cumberland Rd. from 121st St. to 141st St.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 177334.09 | 2.000 | 0901157
4723 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901159 | This is a Maintenance Resurfacing project, at Cumberland Rd. from 106th St. to High Point Ridge; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 115761.02 | 0.800 | 0901159
4724 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901160 | This is a Maintenance Resurfacing project, at Brooks School Rd. from 96th St. to 116th St.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 125908.34 | 2.000 | 0901160
4725 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901162 | This is a Maintenance Resurfacing project, at 106th St. from Hague Rd. to Cumberland Rd.; to perform Pavement, Other work. | Pavement Improvement | 2009-11-19 | 2010-06-14 | 2010-08-07 | 2010-08-13 | 193097.39 | 2.000 | 0901162
4726 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901163 | This is a Maintenance Resurfacing project, at Hazel Dell Blvd. (see project listing for full description); to perform Partial 3-R work. | Pavement Improvement | 2010-03-05 | 2010-03-30 | 2010-09-07 | 2010-10-01 | 1644093.48 | 2.100 | 0901163
4727 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901165 | This is a Maintenance Restoration & Rehabilitation project, at 75th St.-Pennsyl. St. to College Ave. & sign repl. fr. Spring Mill to College Ave.; to perform Road Rehabilitation work. | Pavement Improvement | 2009-12-16 | 2010-06-02 | 2010-06-01 | 2010-09-07 | 88510.75 | 0.600 | 0901165
4728 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BLACKFORD |  | 06 | 0901166 | This project will improve sections and extend the life of Park Avenue from Gilkey Ave to Mill Street in Blackford County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-26 | 2010-05-29 | 2009-11-13 | 129392.86 | 1.500 | 0901166
4729 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901167 | This is a Maintenance Resurfacing project, at Elmwood Ave. from E. of Emerson Ave. to W. of Arlington Ave.; to perform Pavement, Other work. | Pavement Improvement | 2009-12-31 | 2010-05-11 | 2010-06-30 | 2010-06-16 | 115088.25 | 1.100 | 0901167
4730 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0901168 | This is a Maintenance Resurfacing project, at Greensburg Rd. from 510 East to 450 E; to perform Pavement, Other work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-05-14 | 2010-05-13 | 102996.8 | 0.800 | 0901168
4731 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0901169 | This is a Maintenance Resurfacing project, at Morgantown Rd. from CR 600N to Fairview Rd.; to perform Pavement, Other work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-05-14 | 2010-05-13 | 292854.81 | 3.880 | 0901169
4732 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0901170 | This is a Maintenance Resurfacing project, at CR 144 from CR 500N to Bargersville City limits; to perform Pavement, Other work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-05-14 | 2010-05-13 | 193734.92 | 2.290 | 0901170
4733 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | 04 | 0901171 | This is a Maintenance Resurfacing project, at County Road 800 N - Olive Branch Rd. from 400 West to SR 135; to perform Pavement, Other work. | Pavement Improvement | 2009-12-16 | 2010-04-20 | 2010-05-14 | 2010-05-13 | 84675.38 | 0.850 | 0901171
4734 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MORGAN | INDIANAPOLIS | 04 | 0901172 | This is a Maintenance Resurfacing project, at Mann Rd. from Landersdale Rd. to the Marion County Line; to perform Partial 3-R work. | Pavement Improvement | 2009-12-31 | 2010-04-15 | 2010-08-30 | 2010-05-04 | 118123.8 | 1.260 | 0901172
4735 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901173 | This is a Maintenance Resurfacing project, at McGallliard Rd. from Wheeling Ave. to Riverside Ave.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-07-02 | 2010-10-01 | 2010-10-01 | 863097.34 | 1.550 | 0901173
4736 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901174 | This is a Maintenance Resurfacing project,at Tillotson Ave from Riverside Ave to SR 332/McGalliard Rd.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-06-24 | 2010-10-01 | 2010-10-05 | 769371.87 | 1.270 | 0901174
4737 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901175 | This project will improve sections and extend the life of Kepler Road from Jacksonburg Road to Washington Road in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-06 | 2009-10-22 | 255826.24 | 1.880 | 0901175
4738 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901176 | This project will improve sections and extend the life of Pottershop Road from Abington to US 27 in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-23 | 2009-10-23 | 2009-10-17 | 61955.3 | 0.160 | 0901176
4739 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901177 | This is a Maintenance Resurfacing project, at SR 38 - Centerville Road (S-8189) from SR 38 to We Oler Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-18 | 2010-05-18 | 2010-06-04 | 2010-06-02 | 496792.17 | 4.440 | 0901177
4740 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901178 | This project will improve sections and extend the life of Jacksonburg Road from Swoveland Road to SR 38 in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-23 | 2009-11-13 | 2009-10-30 | 151417.78 | 1.000 | 0901178
4741 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901179 | This project will improve sections and extend the life of Pottershop Road from Pennville Road to Abington in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2010-06-04 | 2009-10-17 | 58265.45 | 0.270 | 0901179
4742 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901180 | This project will improve sections and extend the life of Pennville Road from Fayette County line to US 40 in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-06 | 2009-11-02 | 792048.02 | 6.770 | 0901180
4743 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901181 | This project will improve sections and extend the life of Centerville Road from I-70 to SR 38 with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-12 | 2009-11-13 | 2009-11-09 | 221065 | 1.520 | 0901181
4744 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901182 | This project will improve sections and extend the life of South L Street in Wayne County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-09-21 | 2009-11-25 | 2009-11-10 | 637193.83 | 1.520 | 0901182
4745 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901183 | This proejct will extend the life of the bridge by doing bridge maintenance and repair on the deck on Keystone Avenue bridge over Fall Creek in Marion county. | Bridge Improvement | 2010-02-22 | 2010-04-05 | 2010-07-31 | 2010-07-31 | 647694.28 | 0.100 | 0901183
4746 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK |  | 05 | 0901188 | This is a Bridge Rehabilitation (no added capacity) project, at I 70 - 5.75 mi W of SR 9; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2009-10-09 | 2010-05-25 | 2010-08-13 | 2010-08-09 | 391787.5 | 0.196 | 0901188
4747 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 0901198 | This is a Maintenance Resurfacing project, at 300 N from CR 100 W to White River; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-03-25 | 2010-06-15 | 2010-06-03 | 205666.14 | 3.220 | 0901198
4748 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0901200 | This is a Maintenance Resurfacing project, at Deputy Pike from SR 7 to SR 3; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-01 | 2010-07-31 | 2010-08-20 | 937456 | 13.100 | 0901200
4749 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901201 | This project will replace existing sidewalks and place new sidewalks in St. Joe, Indiana . | Safety/Traffic Management | 2009-09-15 | 2009-10-26 | 2010-05-27 | 2010-04-27 | 105294.2 | 0.360 | 0901201
4750 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901203 | This project will improve sections and extend the life of Dekalb County Road 35 with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-06 | 2010-10-31 | 2010-06-07 | 140468.71 | 5.300 | 0901203
4751 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | CLAY |  | 08 | 0901208 | This is a Maintenance Resurfacing project, at I-70 - From Center Point to Harmony; to perform Partial 3-R work. | Pavement Improvement | 2009-12-16 | 2010-03-18 | 2010-06-30 | 2010-05-27 | 823382.98 | 8.000 | 0901208
4752 | INDIANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901209 | This project will resurface the County Road 350N between Morehouse Road And West Lafayette City Limits in Tippecanoe County. | Pavement Improvement | 2010-04-10 | 2010-06-21 | 2010-06-30 | 2010-06-28 | 83384.14 | 0.260 | 0901209
4753 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901210 | This is a Maintenance Resurfacing project, at Mooresville Rd from Raceway Rd to West Newton; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-05 | 2010-08-09 | 2010-07-06 | 620770.47 | 2.400 | 0901210
4754 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901211 | This is a Maintenance Resurfacing project, at Mooresville Rd from Southport Rd to High School Rd.; to perform Partial 3-R work. | Pavement Improvement | 2009-11-23 | 2010-04-05 | 2010-08-09 | 2010-07-06 | 229184.07 | 0.040 | 0901211
4755 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0901212 | This is a Maintenance Resurfacing project, at SR 29 - Burlington Avenue from Clinton Street to Cliff Dr.; to perform Surface Treatment work. | Pavement Improvement | 2010-02-23 | 2010-03-15 | 2010-06-02 | 2010-06-10 | 362696.44 | 0.940 | 0901212
4756 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CASS |  | 02 | 0901213 | This is a Maintenance Resurfacing project, at Main Street from Coles Street to US24/35; to perform Surface Treatment work. | Pavement Improvement | 2010-02-23 | 2010-03-15 | 2010-06-02 | 2010-06-10 | 204812.92 | 1.600 | 0901213
4757 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901216 | This is a Maintenance Resurfacing project, at Woodyard Rd from Curry Pike to Vernal Pike; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-24 | 2010-04-06 | 2010-07-30 | 2010-07-29 | 101414.43 | 1.310 | 0901216
4758 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901218 | This is a Maintenance Resurfacing project, at Old SR 37 South, from Rogers St to Rhorer Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-24 | 2010-04-06 | 2010-07-30 | 2010-07-29 | 232525.9 | 1.670 | 0901218
4759 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901220 | This is a Maintenance Resurfacing project, at That Road, from SR 37 to Rogers St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-24 | 2010-04-06 | 2010-07-30 | 2010-07-29 | 163852.75 | 1.360 | 0901220
4760 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 05 | 0901224 | This is a Maintenance Resurfacing project, at Southport Rd. from Sherman Dr. to Gray Rd.; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-03-03 | 2010-08-16 | 2010-09-22 | 286848.1 | 0.400 | 0901224
4761 | INDIANA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901227 | This is a Maintenance Resurfacing project, from 0.15 miles W of SR 19 to 0.1 miles W of SR 13; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-03-24 | 2010-03-26 | 2010-10-01 | 2010-10-13 | 7934392.25 | 19.630 | 0901227
4762 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901228 | This is a Maintenance Resurfacing project, at Lynhurst Dr from Kentucky Ave to I-70; to perform Partial 3-R work. | Pavement Improvement | 2009-12-31 | 2010-04-12 | 2010-08-16 | 2010-07-12 | 186396.84 | 1.200 | 0901228
4763 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901229 | This is a preventive maintenance resurfacing project, at Mendenhall Rd from Camby Rd to SR 67 in Marion county to extend the service life of the pavement. | Pavement Improvement | 2009-11-23 | 2010-04-05 | 2010-08-09 | 2010-07-06 | 268010.46 | 1.200 | 0901229
4764 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901230 | This is a Maintenance Resurfacing project, at Meridian St. from Thompson Rd. to I-465; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-03-03 | 2010-08-16 | 2010-09-22 | 599699.62 | 0.600 | 0901230
4765 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901231 | This is a Maintenance Resurfacing project, at 38th St from German Church Rd to Carroll Rd.; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-05-11 | 2010-06-30 | 2010-09-10 | 209246.5 | 1.000 | 0901231
4766 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901233 | This is a Maintenance Resurfacing project, at Arlington Ave. from Shelbyville Rd.; to Thompson Rd. to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-03-03 | 2010-08-16 | 2010-09-22 | 618488.12 | 1.300 | 0901233
4767 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901234 | This is a Maintenance Resurfacing project, at Carroll Rd from 46th St to 56th St.; to perform Partial 3-R work. | Pavement Improvement | 2010-03-05 | 2010-06-01 | 2010-06-30 | 2010-06-25 | 310676.88 | 1.000 | 0901234
4768 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901235 | This is a Maintenance Resurfacing project, at 116th St from 0.35 mi E. of Eller Rd to 2.4 mi W of I-69; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-05-13 | 2010-07-31 | 2010-08-30 | 157808.07 | 0.020 | 0901235
4769 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901236 | This is a Maintenance Resurfacing project, at Towne Rd from 96th St to 116th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-29 | 2010-07-31 | 2010-08-17 | 132028.91 | 2.050 | 0901236
4770 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901237 | This is a Maintenance Resurfacing project, at 146th St from Ditch Rd to Springmill Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-05-14 | 2010-06-11 | 2010-06-16 | 107308.19 | 0.980 | 0901237
4771 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901238 | This is a Maintenance Resurfacing project, at Cumberland Rd from 96th St to 106th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-29 | 2010-07-31 | 2010-08-17 | 85078.56 | 1.020 | 0901238
4772 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901239 | This is a preventive maintenance resurfacing project, at Olio Rd from the bridge over Geist Reservoir to 126th St. in Hamilotn county to extendthe service life of the pavement. | Pavement Improvement | 2009-12-16 | 2010-05-13 | 2010-07-31 | 2010-08-30 | 393619.79 | 1.020 | 0901239
4773 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 0901240 | This is a Maintenance Resurfacing project, at CR 600W from CR 500N to CR 650N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-08-13 | 2010-10-01 | 2010-09-10 | 201620.71 | 1.470 | 0901240
4774 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 0901241 | This is a Maintenance Resurfacing project, at CR 300N from CR 700W to CR 800W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-08-13 | 2010-10-01 | 2010-09-10 | 63155.14 | 1.000 | 0901241
4775 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901242 | This is a Safety project, at SR 51 - SR 51(Lincoln St) at 10th St (SR 51); to perform Traffic Signals, New Or Modernized work. | Safety/Traffic Management | 2010-01-05 | 2010-02-01 | 2010-05-31 | 2010-03-18 | 76509.8 | 0.010 | 0901242
4776 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901243 | This is a Maintenance Resurfacing project, at County Highway 1100 W - CR-475S from Lagrange County line to CR-500S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 153755.28 | 0.800 | 0901243
4777 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901244 | This is a Maintenance Resurfacing project, at CR 500 S from CR 475 S to SR 327; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 61689.4 | 0.700 | 0901244
4778 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901245 | This is a Maintenance Resurfacing project, at N SR 327 - CR 500 N from SR-327 to CR 900 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 43744.5 | 0.500 | 0901245
4779 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901246 | This is a Maintenance Resurfacing project, at CR 900 W from CR 500 N to Orland Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 12330.41 | 0.100 | 0901246
4780 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901247 | This is a Maintenance Resurfacing project, at Orland Road from CR 900 W to CR 800 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 99917.79 | 1.000 | 0901247
4781 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901248 | This is a Maintenance Resurfacing project, at CR 800 W from Orland Rd (N Junction) to Orland Rd.; (S Junction) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 11466.08 | 0.100 | 0901248
4782 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901249 | This is a Maintenance Resurfacing project, at Orland Rd from CR 800 W to CR 675 N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 160328.49 | 1.400 | 0901249
4783 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901250 | This is a Maintenance Resurfacing project, at Kimble Rd from CR 550 W to Orland Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 27060.05 | 0.350 | 0901250
4784 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901252 | This is a Maintenance Resurfacing project, at Fox Lake Rd from Menges Rd to CR 200 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 258583.26 | 2.100 | 0901252
4785 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901253 | This is a Maintenance Resurfacing project, at CR 200 W from Fox Lake Rd to US 20; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 6430.07 | 0.300 | 0901253
4786 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901254 | This is a Maintenance Resurfacing project, at Menges Rd from Waymire Rd to Fox Lake Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 55312.58 | 0.700 | 0901254
4787 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901255 | This is a Maintenance Resurfacing project, at Waymire Rd from Menges Rd to CR 150W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 116774.27 | 1.300 | 0901255
4788 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 0901256 | This is a Maintenance Resurfacing project, at E SR 120 - Van Guilder Road from SR-120; to North Baker St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-15 | 2010-04-08 | 2010-05-27 | 2010-06-18 | 139393.18 | 1.600 | 0901256
4789 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901271 | This is a Maintenance Restoration & Rehabilitation project, at N Charles Ave from W Water Street to SR 67; to perform Pavement, Other work. | Pavement Improvement | 2009-12-04 | 2010-09-14 | 2010-06-25 | 2010-09-17 | 56993.52 | 0.500 | 0901271
4790 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901272 | This is a Maintenance Resurfacing project, at Lincoln Street from N Franklin Street to US 27 (Meridian Street); to perform Pavement, Other work. | Pavement Improvement | 2009-11-23 | 2010-10-14 | 2010-06-25 | 2010-10-14 | 22495.74 | 0.170 | 0901272
4791 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | Multiple | 0901278 | This is a Maintenance Resurfacing project, at Whiteland Rd from CR 75W to the New Whiteland City limits; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-04-13 | 2010-05-14 | 2010-05-14 | 94201.01 | 0.770 | 0901278
4792 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | Multiple | 0901279 | This is a Maintenance Resurfacing project, at Smokey Row Rd from CR 500W to SR 135; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-04-13 | 2010-05-14 | 2010-05-14 | 208365.43 | 2.000 | 0901279
4793 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | JOHNSON | INDIANAPOLIS | Multiple | 0901280 | This is a Maintenance Resurfacing project, at Stones Crossing Rd from CR 500W to CR 600W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-04-13 | 2010-05-14 | 2010-05-14 | 96502.04 | 1.030 | 0901280
4794 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | WARRICK | EVANSVILLE (KY) | 08 | 0901281 | This is a trail project for pedestrians and bicycles on the Rivertown Trail Phase IIA at Old Lock and Dam to Belle Rive Drive in Newburgh in Warrick county using enhancement funds | Transportation Enhancements | 2010-03-08 | 2010-03-15 | 2010-10-01 | 2011-12-12 | 870394.97 | 0.010 | 0901281
4795 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901283 | This is a Facilities for Pedestrians and Bicycles project, at 106th St from Penns Pkwy to Rangeline Rd/ College Ave fr I-465 to 105th St.; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-01 | 2010-07-16 | 2010-08-31 | 2010-10-05 | 219450 | 2.180 | 0901283
4796 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901284 | This is a Maintenance Resurfacing project, at Country Club Rd from Country Club Dr S to Hackleman St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-08-01 | 2010-03-22 | 144895.43 | 0.990 | 0901284
4797 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901285 | This is a Maintenance Resurfacing project, at Harrison St from Sheridan St to Dubois Dr.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-08-01 | 2010-03-22 | 49582.91 | 0.320 | 0901285
4798 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901286 | This is a Maintenance Resurfacing project, at Winona Ave from 200' E of Bronson St to McKinley St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-08-01 | 2010-03-22 | 110450.99 | 0.720 | 0901286
4799 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 0901287 | This is a Maintenance Resurfacing project, at Rozella Rd from Brookview Ave to SR 15; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-08-01 | 2010-03-22 | 53202.99 | 0.600 | 0901287
4800 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901288 | This is a Facilities for Pedestrians and Bicycles project, at Along 146th St from Cherry Tree Rd to River Rd.; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-01 | 2010-05-26 | 2010-06-30 | 2010-07-09 | 139680.25 | 1.290 | 0901288
4801 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901289 | This is a Maintenance Resurfacing project, at 234th St from the Cicero Corp limits to Overdorf Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-07-30 | 2010-08-17 | 179116.73 | 1.780 | 0901289
4802 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901290 | This is a Maintenance Resurfacing project, at Olio Rd from 126th St to 136th St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-05-12 | 2010-06-30 | 2010-08-20 | 236058.43 | 1.000 | 0901290
4803 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901299 | This is a Maintenance Resurfacing project, at Carroll Road from US 33 to Hand Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 253880.63 | 4.350 | 0901299
4804 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901300 | This is a Maintenance Resurfacing project, at Ferguson Rd from Bluffton Road to Winchester Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 104458.03 | 1.880 | 0901300
4805 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901301 | This is a Maintenance Resurfacing project, at Yellow River Road from Hadley Road to O'Day Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 49421.35 | 0.620 | 0901301
4806 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901302 | This is a Maintenance Resurfacing project, at O'Day Road from Yellow River Road to US 33; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 433474.84 | 4.810 | 0901302
4807 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901303 | This is a Maintenance Resurfacing project, at Dawkins Road from Doyle Road to Main Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-29 | 2010-08-21 | 2010-08-23 | 999100.74 | 9.070 | 0901303
4808 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901313 | This project will extedn the life of the road by performing perventive maiantenance resurfacing on Albany St from Miller St to CR 50S in Delaware county. | Pavement Improvement | 2010-03-11 | 2010-07-28 | 2010-08-15 | 2010-10-04 | 52485.11 | 0.250 | 0901313
4809 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901314 | This project will resurface the County Road 600W from SR 332 to Lone Beech Bridge in Delaware County. | Pavement Improvement | 2010-04-13 | 2010-05-14 | 2010-07-30 | 2010-07-01 | 315531.72 | 0.100 | 0901314
4810 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901315 | This is a Maintenance Resurfacing project, at Old SR 67 (Fuson Rd) from SR 67 to Cowan Rd; to perform Partial 3-R work. | Pavement Improvement | 2010-02-22 | 2010-06-29 | 2010-08-15 | 2010-07-19 | 385784.82 | 1.800 | 0901315
4811 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901316 | This is a Maintenance Resurfacing project, at Hart Street from 81st Street N to US 30; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-19 | 2010-05-31 | 2010-06-01 | 579254.81 | 2.100 | 0901316
4812 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901317 | This is a Maintenance Resurfacing project, at Calumet Avenue from US 30 N to intersection of Main Street; to perform Surface Treatment work. | Pavement Improvement | 2010-01-05 | 2010-04-19 | 2010-05-31 | 2010-06-01 | 17629.06 | 2.030 | 0901317
4813 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0901323 | This project will improve sections and extend the life of County Road 900North from SR 9 to county road 600 east in Huntington County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-29 | 2010-06-12 | 2010-05-04 | 537504.82 | 7.140 | 0901323
4814 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0901324 | This project will improve sections and extend the life of County Road 300West from county road 1200 south to county road 300 south in Huntington County with a pavement surface overlay. | Pavement Improvement | 2009-09-15 | 2009-10-29 | 2010-06-12 | 2010-05-04 | 678721.3 | 9.010 | 0901324
4815 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 0901325 | This project will improve sections and extend the life of County Road 800North from county road 1000 west to SR 9 in Huntington County with a pavement surface overlay. | Pavement Improvement | 2009-10-14 | 2009-10-28 | 2010-06-12 | 2010-03-24 | 595937.2 | 9.040 | 0901325
4816 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901336 | This is a Maintenance Resurfacing project, at Kern Road from York Road to Ironwood Road to; perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-02-22 | 2010-10-15 | 2010-10-30 | 2010-10-23 | 95116.89 | 0.500 | 0901336
4817 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901337 | This is a Maintenance Resurfacing project, at Fir Road from Day Road to Brick Road (exluding intersections); to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 195575.51 | 2.700 | 0901337
4818 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901338 | This is a Maintenance Resurfacing project, at Miami Road from Roosevelt Road to 0.7 miles south of Orchard Heights Drive; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 52748.56 | 0.600 | 0901338
4819 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901339 | This is a Maintenance Resurfacing project, at Adams Road from Ironwood Road to Gumwood Road ;to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-03-01 | 2010-08-23 | 2010-10-30 | 2010-10-30 | 223239.69 | 2.000 | 0901339
4820 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901340 | This is a Maintenance Resurfacing project, at Ironwood Road from Auten Road to State Line Road; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-05-20 | 2010-08-15 | 2010-06-30 | 114258.82 | 1.000 | 0901340
4821 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901341 | This is a Maintenance Resurfacing project, at Portage Road from 0.4 miles north of Bendix Drive to IN/MI State Line; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 259988.33 | 1.600 | 0901341
4822 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901342 | This is a Maintenance Resurfacing project, at Ireland Road from SR 23 to Locust Road; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 153261.06 | 2.000 | 0901342
4823 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901343 | This is a Maintenance Resurfacing project, at Brick Road from Gumwood Road to Fir Road; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-06-15 | 2010-10-30 | 2010-07-14 | 116373.37 | 1.000 | 0901343
4824 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901344 | This is a Maintenance Resurfacing project, at Ash Road from SR 933 to Elsie Avenue; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 199887.4 | 1.400 | 0901344
4825 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901345 | This is a Maintenance Resurfacing project, at Ironwood Road from Douglas Road to indiana Toll Road; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 84988.69 | 0.500 | 0901345
4826 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901346 | This is a Maintenance Resurfacing project, at Mayflower Road from the UAB, 0.3 miles north of Sumption Trail, to SR 23; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 33113.49 | 0.500 | 0901346
4827 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901347 | This is a Maintenance Resurfacing project, at Locust Road from Madison Road to Jackson Road to; perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 262227.2 | 2.900 | 0901347
4828 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901348 | This is a Maintenance Resurfacing project, at I-80 - Juniper Road from 0.3 miles north of Douglas Rd. to Cleveland Road; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 64125.26 | 0.700 | 0901348
4829 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901351 | This is a Maintenance Resurfacing project, at Beech Road from 0.5 miles S of Harrison road to .07 miles S of Adams St.; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 78529.76 | 0.500 | 0901351
4830 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901352 | This is a Maintenance Resurfacing project, at Grant Road from US 20/US31 By-Pass to Mayflower Road; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 60090.72 | 0.800 | 0901352
4831 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901353 | This is a Safety project, at County wide (urban areas only) sign replacement; to perform Safety Revisions work. | Safety/Traffic Management | 2009-12-16 | 2010-02-12 | 2010-07-31 | 2010-04-27 | 171299.73 | 0.010 | 0901353
4832 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901354 | This project will improve roadway safety in the town of Osceola. | Safety/Traffic Management | 2009-12-16 | 2010-02-12 | 2010-07-31 | 2010-04-27 | 36517.01 | 0.010 | 0901354
4833 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901355 | This is a Maintenance Resurfacing project, at Edison Road from Quince Road to Sundown Road; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 209393.94 | 2.100 | 0901355
4834 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901356 | This is a Maintenance Resurfacing project, at Township 23 North, Range 4 West; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-10 | 2010-06-30 | 2010-06-25 | 299624.65 | 1.570 | 0901356
4835 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901357 | This is a Maintenance Resurfacing project, at Beech Road from Ireland Road to 0.5 miles S of Harrison Road; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-03-01 | 2010-08-23 | 2010-10-30 | 2010-10-30 | 38853.12 | 1.000 | 0901357
4836 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901358 | This is a Maintenance Resurfacing project, at Beech Road from SR 933 to .07 miles south of Adams Street; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2010-04-14 | 2010-08-15 | 2010-08-13 | 36104.42 | 0.260 | 0901358
4837 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901362 | This is a Maintenance Resurfacing project, at CR 200 S from Blaine Pike to Boundry Pike; to perform Pavement, Other work. | Pavement Improvement | 2009-10-13 | 2010-05-18 | 2010-07-30 | 2010-08-09 | 218336.18 | 2.080 | 0901362
4838 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901365 | This is a Maintenance Resurfacing project, at CR 300 N from Pennville LIMITS TO US 27; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-06-18 | 2010-07-30 | 2010-07-29 | 727410.05 | 9.132 | 0901365
4839 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901366 | This is a Maintenance Resurfacing project, at CR 400 S from CR 1150 W to SR 1; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-05-18 | 2010-07-30 | 2010-08-09 | 218650.14 | 2.470 | 0901366
4840 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901367 | This is a Maintenance Resurfacing project, at CR 1150 W from Dunkirk to CR 900 S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-07-13 | 2010-07-30 | 2010-08-05 | 315196.36 | 3.820 | 0901367
4841 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901374 | This is a Maintenance Restoration & Rehabilitation project, at West Water Street from Western City Limit to US 27 (Meridian Street); to perform Patch And Rehab Bituminous Pavement work. | Pavement Improvement | 2009-12-30 | 2010-10-11 | 2010-06-28 | 2011-05-20 | 139689.15 | 1.500 | 0901374
4842 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901375 | This is a Maintenance Restoration & Rehabilitation project, at W. High Street from N. Middle Street to US 27 (Meridian Street); to perform Patch And Rehab Bituminous Pavement work. | Pavement Improvement | 2009-12-30 | 2010-10-11 | 2010-06-28 | 2011-05-16 | 68967.54 | 0.370 | 0901375
4843 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | JAY |  | 06 | 0901379 | This project will patch and restore and overlay North Wayne St from SR 26 to East Votaw Street in Portland, Jay county to extend the life of the pavement. | Pavement Improvement | 2009-12-30 | 2010-10-11 | 2010-06-25 | 2011-05-18 | 55408.38 | 0.490 | 0901379
4844 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901384 | This is a Maintenance Resurfacing project, at CR 800 E from Glenwood to CR 250 N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2009-11-04 | 2009-10-30 | 2009-11-11 | 118535.6 | 1.320 | 0901384
4845 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901386 | This is a Maintenance Resurfacing project, at CR 800 E from Orange Pike to Glenwood; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-03-17 | 2010-07-30 | 2010-04-29 | 223263.41 | 2.670 | 0901386
4846 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901388 | This is a Maintenance Resurfacing project, at Fort Wayne from E. 3rd St to E. 11th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-03-19 | 2010-06-25 | 2010-04-29 | 168332.25 | 0.900 | 0901388
4847 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | RUSH |  | 06 | 0901390 | This is a Maintenance Resurfacing project, at Conard-Harcourt Way from SR 3 to E. 11th Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-10-13 | 2010-03-19 | 2010-06-25 | 2010-04-29 | 166626 | 0.840 | 0901390
4848 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901409 | This is a Maintenance Resurfacing project, at From 1.90 Miles West of SR 15 to SR 15; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-03-23 | 2010-07-12 | 2010-08-13 | 2010-08-13 | 369087.7 | 1.870 | 0901409
4849 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI, FULTON |  | Multiple | 0901410 | This is a Maintenance Resurfacing project, at SR 19 - From US 24 to 0.25 miles S of SR 14 (South limits of Akron); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-15 | 2010-04-05 | 2010-10-08 | 2010-10-04 | 2051607.86 | 18.900 | 0901410
4850 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE, ELKHART | ELKHART-GOSHEN | Multiple | 0901411 | This is a Maintenance Resurfacing project, at From jct. US 33/SR 13 to 0.17 miles E of SR 5; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-03-23 | 2010-04-12 | 2010-07-31 | 2010-06-24 | 926767.38 | 5.470 | 0901411
4851 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901416 | This is a Safety project, at Edwardsville-Galena Rd from Old Vincennes Rd to Country Trace Lane; to perform Pavement Markings work. | Safety/Traffic Management | 2010-02-22 | 2010-04-16 | 2010-05-15 | 2010-08-06 | 67033.9 | 0.380 | 0901416
4852 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901418 | This is a Safety project, at Old Vincennes Rd from Partridge Place to Pebble Creek Dr; to perform Pavement Markings work. | Safety/Traffic Management | 2010-02-22 | 2010-04-16 | 2010-05-15 | 2010-08-06 | 37535.3 | 0.840 | 0901418
4853 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 0901428 | This is a Facilities for Pedestrians and Bicycles project, at Former Erie RR right of way between North Judson and Town of Ora in Starke Co; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-01 | 2010-05-18 | 2011-10-15 | 2010-12-21 | 1028182.99 | 6.250 | 0901428
4854 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901439 | This is a Maintenance Resurfacing project, at Between CR 800 S & US 52; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-05 | 2010-03-18 | 2010-06-30 | 2010-04-26 | 141907.03 | 0.683 | 0901439
4855 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901441 | This is a Maintenance Resurfacing project, at Between CR 510 S & CR 430 S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-04-21 | 2010-05-29 | 2010-05-28 | 166109.45 | 0.867 | 0901441
4856 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901449 | This is a Maintenance Resurfacing project, at Main St from Ensley Ave to North St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-23 | 2010-04-12 | 2010-08-15 | 2010-11-01 | 457970.85 | 0.950 | 0901449
4857 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 08 | 0901455 | This is a Facilities for Pedestrians and Bicycles project, at Covington Circle Trail - Ph II; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-24 | 2010-03-23 | 2010-07-10 | 2010-07-10 | 718659 | 3.100 | 0901455
4858 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901458 | This is a Maintenance Resurfacing project, at From Union Township line to Old US 231; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-16 | 2010-04-21 | 2010-05-29 | 2010-05-28 | 118836.71 | 1.020 | 0901458
4859 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | PULASKI |  | 02 | 0901465 | This is a trail project on an abandoned RR right of way for pedestrians and bicycles at rail banked corridor along US 35 between Star City and north of Royal Center in Cass/Pulaski Co's using enhancement funds. | Transportation Enhancements | 2009-12-31 | 2010-03-16 | 2010-11-19 | 2010-12-03 | 2263793 | 15.690 | 0901465
4860 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901466 | This is a Maintenance Resurfacing project, at Beverly Drive from Eaton Avenue to US 12 (Mt. Baldy); to perform Surface Treatment work. | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-06-01 | 2010-04-21 | 271350.65 | 3.730 | 0901466
4861 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901468 | This is a preventive maintenance resurfacing project, on North "D" Street from 1st to 10th Streetin Gas City, Grant county to extend the service llife of the pavement. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 222928.14 | 1.010 | 0901468
4862 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901469 | This is a Maintenance Resurfacing project, at 5th Street from South "H" Street to North "D" Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 148395.63 | 0.780 | 0901469
4863 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901470 | This is a Maintenance Resurfacing project, at South "D" Street from 1st to 3rd Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 65330.73 | 0.210 | 0901470
4864 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901471 | This is a preventive maintenance resurfacing project, at 3rd Street from South "H" Street to SR 22 in Gas City, Grant county. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 151437 | 0.510 | 0901471
4865 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901472 | This is a Maintenance Resurfacing project, at 7th Street from SR 22 to North "D" Street; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-11 | 2010-06-26 | 2010-07-14 | 56267.52 | 0.250 | 0901472
4866 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901473 | This is a trail project for pedestrians and bicycles on the over 6500 feet of side walks on Ralph Sechler Dr., Spencer St, School St, Hart St and other streets in the town of St Joe, and is Phase 3 of a multi phase project using enhancement funds. | Transportation Enhancements | 2010-01-06 | 2010-03-01 | 2010-08-15 | 2010-07-26 | 275862.02 | 0.360 | 0901473
4867 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901480 | This is a Facilities for Pedestrians and Bicycles project, at New York Street from 9th St to 12th Street in Elkhart, Elkart county. This 1 of 3 projects top provide pedestrian facilities under contract SR-30435. | Transportation Enhancements | 2009-11-30 | 2010-04-26 | 2010-06-19 | 2010-06-18 | 40910.58 | 0.230 | 0901480
4868 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901481 | This is a Facilities for Pedestrians and Bicycles project, at 11th St from New York Ave to East Burdick St in Elkhart, Elkhart county. This 1 of 3 projects to provide pedestrian facilites under contract SR-30435. | Transportation Enhancements | 2009-11-30 | 2010-04-26 | 2010-06-19 | 2010-06-18 | 33412.68 | 0.140 | 0901481
4869 | INDIANA | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901482 | This is a preventive maintenance resurfacing project, at Piqua Rd from East of Monroe St to CR 700E (State Line) in Adams county; to perform asphalt resurface, Preventive Maintenance work. This 1 of | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 576946.53 | 7.070 | 0901482
4870 | INDIANA | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901483 | This is a pavement preventive maintenance resurfacing project, at CR 1200 S from CR 500 E to CR 700 E (State Line) in Adams county to perform Chip Seal work that will extend the life of the road. This | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 32281.09 | 1.930 | 0901483
4871 | INDIANA | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901484 | This is a preventive maintenance resurfacing project, at CR 100 E (High St ) from north of US 33 to north of abandoned RR (City Limits) in Adams county to perform asphalt resurface to extend the life of the road. 1of 5 projects on contract SR-32611. | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 89272.39 | 1.040 | 0901484
4872 | INDIANA | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901485 | This is a preventive maintenance resurfacing project, at CR 500 E (Old SR 116) from CR 1200 South to CR 1100 South to perform Chip Seal work to extend the life of the pavement. This 1 of 5 proejcts on contract SR-32611 pavement resurfacing. | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 18338.15 | 1.050 | 0901485
4873 | INDIANA | Underway | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901486 | This is a preventive maintenance resurfacing project, on County Road 1050/1100 from south of Hale St (Town Limits) to County Road 500East in Adams county to perform, Chip Seal work to extend the life of the road. This 1 of 5 projects on contract SR-32611. | Pavement Improvement | 2010-04-13 | 2010-07-15 | 2010-08-14 |  | 102933.42 | 6.200 | 0901486
4874 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901487 | This is a Maintenance Resurfacing project,at Centerville Rd from 900 feet S of Temple Dr,N 3.38 miles to the S ramp to I-70 ;to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-18 | 2010-03-25 | 2010-06-11 | 2010-06-11 | 1011110.45 | 3.410 | 0901487
4875 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901494 | This is a Maintenance Resurfacing project, at Quincy Street from N. Peters St to N. 2nd St to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-18 | 2010-06-30 | 2010-08-18 | 171935.7 | 0.700 | 0901494
4876 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DE KALB |  | 03 | 0901495 | This project will extend the pavement life with a preventive maintenance resurfacing project on South Rd from N. 2nd St to 0.1 mile E of Taylor Rd. in Garrett, Dekalb county. | Pavement Improvement | 2010-04-01 | 2010-05-18 | 2010-06-30 | 2010-08-18 | 74456 | 0.560 | 0901495
4877 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901496 | This is a Maintenance Resurfacing project, at Woodburn Road from Hetrick Road to State Road 101 (Main St.) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-09-22 | 2010-10-30 | 2010-11-01 | 157574.85 | 0.500 | 0901496
4878 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901497 | This is a Maintenance Resurfacing project, at Woodburn Road from State Road 101 (Fahlsing Rd.) to Brobst Rd.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-09-22 | 2010-10-30 | 2010-11-01 | 56120.75 | 0.500 | 0901497
4879 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 03 | 0901498 | This is a Maintenance Resurfacing project, at Bull Rapids Rd from SR 101 (Main St.) to 0.33 mile N of Ash St (City limits) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-06 | 2010-09-22 | 2010-10-30 | 2010-11-01 | 100975.18 | 0.700 | 0901498
4880 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 0901502 | This is a Maintenance Resurfacing project, at CR 300 N from CR 300 W to CR 200 W, 0.50 miles N of I-70; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-08-23 | 2010-10-01 | 2010-09-30 | 87509.14 | 1.000 | 0901502
4881 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 0901503 | This is a Maintenance Resurfacing project, at CR 300 N from CR 400 W to CR 300 W, 0.5 miles N of I-70; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-08-23 | 2010-10-01 | 2010-09-30 | 86747.6 | 1.000 | 0901503
4882 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | MICHIGAN CITY | 02 | 0901505 | This is a Preventive Maintenance Resurfacing project, at Coolspring Avenue from Roeske Avenue (Michigan City Corp Limit) to Johnson Road in Laprot county to extend the life of the pavement.. | Pavement Improvement | 2010-02-24 | 2010-04-15 | 2010-07-01 | 2010-06-29 | 329390.4 | 0.600 | 0901505
4883 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0901506 | This is a Maintenance Resurfacing project, at S. Walnut St from Wylie to Country Club to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-12 | 2010-06-26 | 2010-06-18 | 616601.33 | 1.690 | 0901506
4884 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901517 | This is a Maintenance Resurfacing project, at Pendleton Ave from High St to Reformatory Rd; to perform Surface Treatment work. | Pavement Improvement | 2009-12-31 | 2010-06-01 | 2010-07-30 | 2010-07-23 | 142600 | 0.760 | 0901517
4885 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901518 | This is a Maintenance Resurfacing project, at Harrison St from 3rd St to Norfolk Southern RR crossing; to perform Surface Treatment work. | Pavement Improvement | 2010-01-06 | 2010-08-19 | 2010-06-30 | 2010-09-02 | 197721 | 0.920 | 0901518
4886 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901519 | This is a Maintenance Resurfacing project, at CR 50 W from SR 38 to Anderson C L; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 281629.13 | 4.100 | 0901519
4887 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901521 | This is a Maintenance Resurfacing project, at CR 100 W from SR 128 to CR 1100 N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 221297.08 | 3.100 | 0901521
4888 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901522 | This is a Maintenance Resurfacing project, at CR 1100 N from SR 9 to CR 100 E; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 56177.6 | 1.100 | 0901522
4889 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901523 | This is a Maintenance Resurfacing project, at CR 1100 N from CR 200 W to CR 100 W; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 83358 | 1.100 | 0901523
4890 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901524 | This is a Maintenance Resurfacing project, at New Columbus Ave from CR 600S to CR 400S; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-21 | 2010-10-01 | 2010-09-02 | 169100.19 | 2.100 | 0901524
4891 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901529 | This is a Maintenance Resurfacing project, at Cumberland Rd from Field Dr to Allisonville Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-05-25 | 2010-06-30 | 2010-08-18 | 116794.02 | 0.970 | 0901529
4892 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901530 | This is a Maintenance Resurfacing project, at Boden Rd between SR 38 and Greenfield Ave to; perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-06 | 2010-07-31 | 2010-07-14 | 113029.07 | 2.080 | 0901530
4893 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HAMILTON | INDIANAPOLIS | 05 | 0901531 | This is a Maintenance Resurfacing project, at Little Chicago Rd between SR 38 and Carrigan Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-08 | 2010-07-31 | 2010-07-16 | 159921.82 | 1.650 | 0901531
4894 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901533 | This is a Maintenance Resurfacing project, at Diamond St from Main St to Sherman St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 234868.67 | 0.610 | 0901533
4895 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901535 | This is a Maintenance Resurfacing project, at Mitchell St from Weston Ave to Orchard St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 106251.51 | 0.470 | 0901535
4896 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901538 | This is a Maintenance Resurfacing project, at Iddings St from Main St to Town St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 42310.1 | 0.280 | 0901538
4897 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | Multiple | 0901540 | This is a Maintenance Resurfacing project, at Business SR 37 from Old SR 37 North; to SR 37 to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-05-07 | 2010-07-30 | 2010-07-23 | 199088.36 | 1.764 | 0901540
4898 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901542 | This is a Maintenance Resurfacing project, at Fair St from Wayne St to US 6; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 69979.72 | 0.280 | 0901542
4899 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLARK | LOUISVILLE (KY)-IN | 09 | 0901547 | This is a Maintenance Resurfacing project, at Old SR 62 - Brown Station Way from Randolph Avenue to Silver Creek; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-03-30 | 2010-06-30 | 2010-06-28 | 617504.42 | 1.800 | 0901547
4900 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | NOBLE |  | 03 | 0901551 | This is a Maintenance Resurfacing project, at Main St from High St to US 6 to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-08-31 | 2010-11-02 | 9602.4 | 0.070 | 0901551
4901 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901552 | This is a Maintenance Resurfacing project, at Hartzell Rd from RR tracks (approx. 1600' south of Rose Ave) to Rose Ave; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 37464.34 | 0.300 | 0901552
4902 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901553 | This is a Maintenance Resurfacing project, at Rose Ave; from Green St. to Linden Rd to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 54110.65 | 0.610 | 0901553
4903 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901554 | This is a Maintenance Resurfacing project, at Landin Rd from N River Rd to Maysville Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 272728.08 | 1.890 | 0901554
4904 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901555 | This is a Maintenance Resurfacing project, at New Haven Ave from Meyer Rd to SR 930; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 90325.99 | 0.730 | 0901555
4905 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901556 | This is a Maintenance Resurfacing project, at Rose Ave from Hartzell Rd to Landin Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 52047.51 | 0.580 | 0901556
4906 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901557 | This is a preventive maintenance resurfacing project on Minnich Rd from Seiler Rd to SR 930 in Fort wayne , Allen county to extend the service life of the road. | Pavement Improvement | 2009-11-23 | 2010-05-15 | 2010-06-26 | 2010-08-18 | 167092.1 | 1.150 | 0901557
4907 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901558 | This is a Maintenance Resurfacing project, at Summit St from Bensman Ave to Linden Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 55587.48 | 0.480 | 0901558
4908 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901559 | This is a Maintenance Resurfacing project, at Lincoln Hwy from 365' E of Green St; to City Limits (1320' W of Doyle St) to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-05-27 | 2010-07-30 | 2010-08-31 | 121119.5 | 1.100 | 0901559
4909 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS | INDIANAPOLIS | 04 | 0901561 | This project will resurface the County Road 100N from Richfield Drive to Kinross Drive in Hendricks County. | Pavement Improvement | 2010-04-10 | 2010-05-05 | 2010-07-30 | 2010-05-27 | 215983.5 | 1.500 | 0901561
4910 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901563 | This project is a preventive maintenance resurfacing project, on Old US Hwy 231 - From County Road 500 South to County Road 350 South in Tippecanoe county to extend the life of the pavement. | Pavement Improvement | 2009-12-16 | 2010-04-21 | 2010-05-29 | 2010-05-28 | 219533.2 | 1.443 | 0901563
4911 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901571 | This is a Maintenance Resurfacing project, at 45th Street from State Line east to Highland Line; to perform Surface Treatment work. | Pavement Improvement | 2009-12-16 | 2010-04-06 | 2010-06-01 | 2010-06-03 | 557135.49 | 2.400 | 0901571
4912 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | CHICAGO-NORTHWESTERN INDIANA (IL) | 02 | 0901600 | This is a Maintenance Resurfacing project, at Schultz Road from CR 600W to CR 400W; to perform Surface Treatment work. | Pavement Improvement | 2009-11-23 | 2009-11-24 | 2009-12-01 | 2009-12-17 | 287065.77 | 2.120 | 0901600
4913 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE | MICHIGAN CITY | 02 | 0901619 | This proejct replaces and repairs storm sewers, at Michigan Blvd from US 12 to Carroll Avenue in Michigan City, LaPorte county to correct and improve drainage of the road. | Other | 2010-05-05 | 2010-06-18 | 2010-09-01 | 2010-08-18 | 1735143.59 | 1.860 | 0901619
4914 | INDIANA | Completed | C250,C240 | Highway Infrastructure Investment Grant | INDIANA | CRAWFORD |  | 09 | 0901627 | This is a Maintenance Resurfacing project, at SR 164 to SR 56; to perform Surface Treatment, Ultrathin Bonded Wearing Course work. | Pavement Improvement | 2010-04-09 | 2010-06-07 | 2010-07-31 | 2010-07-16 | 1804511.4 | 13.670 | 0901627
4915 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901628 | This is a Maintenance Resurfacing project, at From US 52 to SR 38; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-05 | 2010-03-19 | 2010-06-30 | 2010-05-13 | 243723.82 | 0.696 | 0901628
4916 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901629 | This is a Maintenance Resurfacing project, at Between SR 26 and US 52; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-20 | 2010-07-31 | 2010-08-20 | 1359216 | 1.620 | 0901629
4917 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901631 | This is a Maintenance Resurfacing project, at Aboite Center Rd from West Hamilton Rd to Homestead Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 112564.9 | 1.260 | 0901631
4918 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901632 | This is a Maintenance Resurfacing project, at Bass Road from W Co Ln Road to Scott Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 232207.72 | 3.260 | 0901632
4919 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901633 | This is a preventive maintenance resurfacing project on Covington Road from West County Line Road to Braemar Drivein Allen county to extend the service life of the pavement. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 210460.33 | 1.870 | 0901633
4920 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901634 | This is a Maintenance Resurfacing project, at West Hamilton Road frm US 24 to Bass Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 537182.32 | 5.630 | 0901634
4921 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901635 | This is a Maintenance Resurfacing project, at Leesburg Road from Kroemer Road to Beineke Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-04-01 | 2010-06-26 | 2010-07-01 | 62911.9 | 1.020 | 0901635
4922 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901636 | This project will improve the traffic signs in the town of Indian Village. | Safety/Traffic Management | 2009-12-16 | 2010-02-12 | 2010-07-31 | 2010-04-27 | 3169.67 | 0.010 | 0901636
4923 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901637 | This project will improve the traffic signs in the town of Roseland. | Safety/Traffic Management | 2009-12-16 | 2010-02-12 | 2010-07-31 | 2010-04-27 | 23814.19 | 0.010 | 0901637
4924 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901648 | This is a Maintenance Resurfacing project, at US 36 - From Pendleton Pike to 79th St; to perform Pavement, Other work. | Pavement Improvement | 2010-04-01 | 2010-07-06 | 2010-08-13 | 2010-07-30 | 245105.28 | 2.320 | 0901648
4925 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901649 | This is a Maintenance Resurfacing project, at Carroll Rd. from 75th St. to 79th St.; to perform Pavement, Other work. | Pavement Improvement | 2010-01-13 | 2010-05-07 | 2010-07-10 | 2010-07-12 | 191066.95 | 0.500 | 0901649
4926 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DEARBORN | CINCINNATI | 09 | 0901652 | This is a Maintenance Resurfacing project, at Nowlin Avenue from Rand Aven. to Meadowcreek Drive; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-04-02 | 2010-06-25 | 2010-06-04 | 139653.6 | 0.010 | 0901652
4927 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS |  | 04 | 0901655 | This is a Facilities for Pedestrians and Bicycles project, at From SR 267 to CR 300 N and from Ronald Reagan Pkwy; to Raceway Rd to perform Enhancement work. | Transportation Enhancements | 2010-04-13 | 2010-04-26 | 2010-11-15 | 2011-06-14 | 3334104.27 | 0.010 | 0901655
4928 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901656 | This is a Maintenance Resurfacing project, at Liverpool Road from New Jersey Street to Deep River; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-19 | 2010-05-10 | 2010-09-15 | 2010-10-05 | 464343.79 | 0.230 | 0901656
4929 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI, FULTON |  | Multiple | 0901663 | This project will build a trail for pedestrians and bicycles on Nickel Plate Trail: from Lovers Lane north of Peru im Miami county to Wabash Road in Rochester in Fulton County. | Transportation Enhancements | 2010-02-22 | 2010-03-19 | 2010-10-15 | 2010-12-08 | 4413712.7 | 17.000 | 0901663
4930 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0901685 | This project builds new sidewalks in 17 locations in Bloomington, Monroe county using enhancement funds. | Other | 2010-02-22 | 2010-03-15 | 2010-05-14 | 2010-04-30 | 293006.58 | 1.200 | 0901685
4931 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 0901686 | This is a Landscaping project, at Madison Riverfront Dev-Phase 2: Bankstab, Scenic, Docking; to perform Landscaping work. | Transportation Enhancements | 2010-02-18 | 2010-03-16 | 2010-12-15 | 2011-05-17 | 915468.75 | 0.010 | 0901686
4932 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | ELKHART |  | 03 | 0901687 | This is a trail project for pedestrians and bicycles project on the Pumpkinvine Trail and is Phase 5C located from 1300' south of CR 22 to US 20 in Elkhart county using enhancement funds. | Transportation Enhancements | 2010-03-04 | 2010-03-31 | 2010-08-20 | 2011-06-08 | 1088731.18 | 0.040 | 0901687
4933 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901689 | This is a Maintenance Resurfacing project, at 34th St from Arlington Avenue to Shadeland Avenue; to perform Partial 3-R work. | Pavement Improvement | 2010-04-07 | 2010-05-21 | 2010-10-31 | 2010-10-04 | 389420.63 | 1.000 | 0901689
4934 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 05 | 0901690 | This is a Maintenance Resurfacing project, at Davis Rd from Vandergriff Rd to Troy Ave; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-07-16 | 2010-11-01 | 2010-10-29 | 191427.53 | 0.700 | 0901690
4935 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901691 | This is a Maintenance Resurfacing project, at Edgewood Ave from Shelbyville Rd to Five Points Rd; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-07-16 | 2010-11-01 | 2010-10-29 | 583175.71 | 1.300 | 0901691
4936 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0901692 | This is a Maintenance Resurfacing project, at Five Points Rd from Shelbyville Rd to Southeastern Ave; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-07-16 | 2010-11-01 | 2010-10-29 | 547726.16 | 4.300 | 0901692
4937 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901693 | This proejct will place muliple lays of asphalt to increase strength and extend the life of the pavement on Harding St from Morris St to Oliver Ave in Marion county. | Pavement Improvement | 2010-04-07 | 2010-07-09 | 2010-08-02 | 2010-09-13 | 305066.6 | 0.500 | 0901693
4938 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901694 | This project rebuilds the pavement with multi-lays of asphalt on Lafayette Rd from 71st St to County Line Rd in Indianapolis, Marion county. | Pavement Improvement | 2010-04-10 | 2010-05-11 | 2010-09-11 | 2010-09-21 | 1821723.24 | 3.600 | 0901694
4939 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901695 | This is a Maintenance Resurfacing project, at Morris St from Lynhurst Dr to Westbrook Ave; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-06-25 | 2010-07-01 | 2010-09-07 | 185287.08 | 0.500 | 0901695
4940 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 05 | 0901697 | This is a Maintenance Resurfacing project, at Senour St from Thompson Rd to Troy Ave; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-07-16 | 2010-11-01 | 2010-10-29 | 242614.61 | 2.000 | 0901697
4941 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901712 | This is a Bridge Rehabilitation (no added capacity) project, at Mann Rd over Dollar Hide Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-05-17 | 2010-10-31 | 2010-09-29 | 264255.81 | 0.100 | 0901712
4942 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901713 | This is a Bridge Rehabilitation (no added capacity) project, at Emerson Avenue over Brookside Creek; to perform Bridge Rehabilitation Or Repair work. | Bridge Improvement | 2010-04-01 | 2010-05-17 | 2010-10-31 | 2010-09-29 | 264201.27 | 0.100 | 0901713
4943 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901714 | This is a Bridge Rehabilitation (no added capacity) project, at Country Club Rd over Cox Ditch; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-04-22 | 2010-10-31 | 2010-07-02 | 244583.44 | 0.100 | 0901714
4944 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901716 | This is a Bridge Rehabilitation (no added capacity) project, at Bridgeport Rd over White Lick Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-04-22 | 2010-10-31 | 2010-07-02 | 247883.69 | 0.100 | 0901716
4945 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901717 | This is a Bridge Rehabilitation (no added capacity) project, at Bridgeport Rd over Salem Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-04-22 | 2010-10-31 | 2010-07-02 | 152878.34 | 0.100 | 0901717
4946 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 04 | 0901718 | This is a Bridge Rehabilitation (no added capacity) project, at Bridgeport Rd over Shiloh Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-04-22 | 2010-10-31 | 2010-07-02 | 101900.2 | 0.100 | 0901718
4947 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901722 | This is a Maintenance Resurfacing project, at Liberty Mills Road frm W Co Ln Road to Amber Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 216179.98 | 1.790 | 0901722
4948 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901723 | This is a Maintenance Resurfacing project, at Muldoon Road frm Ferguson Road to Winchester Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 74286.16 | 1.320 | 0901723
4949 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901724 | This is a Maintenance Resurfacing project, at Smith Road from Airport Expressway to 120 feet N of Knoll Road (N&S Railroad); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 182986.38 | 2.410 | 0901724
4950 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901725 | This is a Maintenance Resurfacing project, at Wallen Road frm Huguenard Road to Hanauer Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 53393.7 | 0.930 | 0901725
4951 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901726 | This is a Maintenance Resurfacing project, at Washington Center Road frm O'Day Road to Kroemer Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 111648.86 | 1.790 | 0901726
4952 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901727 | This is a Maintenance Resurfacing project, at Winchester Road frm Ferguson Road to Lower Huntington Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 120039.47 | 1.970 | 0901727
4953 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901728 | This is a Maintenance Resurfacing project, at Yohne Road frm Branstrator Rd to Smith Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-11-23 | 2010-03-31 | 2010-08-14 | 2010-08-14 | 147472.32 | 2.530 | 0901728
4954 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901731 | This is a Bridge Rehabilitation (no added capacity) project, at 56th St over Indian Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-05-17 | 2010-10-31 | 2010-09-29 | 182156.01 | 0.100 | 0901731
4955 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901733 | This is a Bridge Rehabilitation (no added capacity) project, at Mann Road over Mann Creek; to perform Bridge Deck Overlay work. | Bridge Improvement | 2010-04-01 | 2010-05-17 | 2010-10-31 | 2010-09-29 | 237870.92 | 0.100 | 0901733
4956 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901734 | This is a Special Bridge project, on the CF&E Railroad over the St Marys River in Adams County, to replace a steel girder to provide an improved rail line for economic development to an industrial area. This 1 of 2 projects under contract SB-32787 | Bridge Improvement | 2010-03-05 | 2010-03-23 | 2010-08-28 | 2011-11-11 | 2548764.85 | 0.050 | 0901734
4957 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901738 | This is a preventive maintenance resurfacing project on West 38th St from Raible Ave to Oakwood Blvd in Anderson, in Madison county to extend the service life of the road. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 128458.58 | 0.400 | 0901738
4958 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901739 | This is a Maintenance Resurfacing project, at W 25th St from Raible Ave to Park Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 72248.85 | 1.000 | 0901739
4959 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901740 | This is a Maintenance Resurfacing project, at Raible Ave from W 38th St to W 30th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 97332.64 | 0.700 | 0901740
4960 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901741 | This is a Maintenance Resurfacing project, at Park Rd from W 53rd St to W 25th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 174964.32 | 2.000 | 0901741
4961 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901742 | This is a Maintenance Resurfacing project, at Main St from 53rd St to 65th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 69697.33 | 1.000 | 0901742
4962 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901743 | This is a Maintenance Resurfacing project, at Lindberg Rd from Alexandria Pike to Rangeline Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 176131.43 | 2.020 | 0901743
4963 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901744 | This is a Maintenance Resurfacing project, at E 38th St from SR 9/Scatterfield Rd to Rangeline Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 70076.86 | 1.000 | 0901744
4964 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901745 | This is a Maintenance Resurfacing project, at Cross St from SR 9/Scatterfield Rd to Rangeline Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 120762.71 | 1.400 | 0901745
4965 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901746 | This is a Maintenance Resurfacing project, at Columbus Ave from 53rd St to 67th St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 97353.17 | 1.100 | 0901746
4966 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901747 | This is a Maintenance Resurfacing project, at Alexandria Pike from University Blvd. to SR 9/Scatterfield Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 144770.45 | 1.800 | 0901747
4967 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901748 | This is a Maintenance Resurfacing project, at W 53rd St from CSX Railroad Crossing to Layton Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-06-18 | 2010-10-01 | 2010-11-06 | 127703.66 | 1.600 | 0901748
4968 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD |  | 09 | 0901750 | This is a Maintenance Resurfacing project, at Scottsville Rd from Martin Road to the Clark County line; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-04-23 | 2010-05-05 | 2010-07-23 | 368400 | 4.330 | 0901750
4969 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 0901754 | This is a part of a special project, at the CF&E Railroad crossing on US 27, south of Adams St in Adams county to improve an old railroad crossing to imporve the rail line for an idustiral area. T | Bridge Improvement | 2010-03-05 | 2010-03-23 | 2010-08-28 | 2011-11-11 | 263879.2 | 0.020 | 0901754
4970 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901756 | This is a Safety project, at Approx 70 signalized intersections within Lafayette; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2009-12-31 | 2010-02-18 | 2010-07-31 | 2010-07-13 | 608115.55 | 0.100 | 0901756
4971 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RIPLEY |  | 09 | 0901757 | This is a Bridge Rehabilitation (no added capacity) project, at SR 48 - SR 48 over Laughery Creek, 1.70 miles E of SR 229; to perform Bridge Deck Replacement work. | Bridge Improvement | 2009-12-30 | 2010-03-15 | 2010-09-17 | 2010-09-15 | 523689.1 | 0.010 | 0901757
4972 | INDIANA | Completed | C220,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901776 | This is a Facilities for Pedestrians and Bicycles project, at Covington Rd Trail: from Sycamore Hills Dr to Scott Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-01-06 | 2010-03-18 | 2010-08-14 | 2010-10-29 | 529006.1 | 0.600 | 0901776
4973 | INDIANA | Completed | C220,C250 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 0901777 | This is a trail construction project, for the Cardinal Greenway Trail: from Troy Ave to CR 400 Wrian Facilities work in th city of Marion in Grant county using enhancement funds | Transportation Enhancements | 2010-01-06 | 2010-04-27 | 2010-09-01 | 2010-10-25 | 434534.1 | 2.000 | 0901777
4974 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RANDOLPH |  | 06 | 0901781 | This is a Maintenance Resurfacing project, at From the Little Mississinewa River to the Ohio State Line; to perform Surface Treatment, Microsurface work. | Pavement Improvement | 2010-04-07 | 2010-08-06 | 2010-08-14 | 2010-08-20 | 157759.01 | 0.920 | 0901781
4975 | INDIANA | Completed | C220,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901783 | This is a Facilities for Pedestrians and Bicycles project, at Covington Rd Trail: from Eggeman Rd to Sycamore Hills Dr; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-22 | 2010-03-18 | 2010-08-14 | 2010-11-22 | 578440.6 | 0.450 | 0901783
4976 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901785 | This is a Maintenance Resurfacing project, at Vermillion Drive/127th Street from Cline Avenue E to Fairbanks Avenue; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-01-11 | 2010-06-03 | 2010-06-30 | 2010-09-18 | 251128.26 | 0.840 | 0901785
4977 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901786 | This is a Maintenance Resurfacing project, at W Jefferson Blvd from 725' SW of Lutheran Hospital Ent. to 500'. NE of Illinois; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-08 | 2010-03-29 | 2010-06-26 | 2010-08-27 | 993909.84 | 3.950 | 0901786
4978 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901787 | This is a Maintenance Resurfacing project, at Wayne St from Broadway to Coombs St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-29 | 2010-05-27 | 2010-11-18 | 388452.81 | 1.340 | 0901787
4979 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901788 | This is a Maintenance Resurfacing project, at Berry St from Broadway to Coombs St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-29 | 2010-05-27 | 2010-11-18 | 329224.71 | 1.350 | 0901788
4980 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901789 | This is a Maintenance Resurfacing project, at Washington Blvd from Broadway to Clay St to; perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-29 | 2010-05-27 | 2010-11-18 | 216630.05 | 0.820 | 0901789
4981 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901790 | This is a Maintenance Resurfacing project, at Jefferson Blvd from Calhoun St to Clay St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-03-29 | 2010-05-27 | 2010-11-18 | 92395.17 | 0.330 | 0901790
4982 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901793 | This is a trail project on the Cardinal Greenway & Main St, Randolph, Losantville, IN- Cardinal & Davis Meyersin Wayne county using enhancement funds. | Transportation Enhancements | 2010-04-06 | 2010-05-17 | 2011-04-15 | 2010-11-01 | 1712258.77 | 0.010 | 0901793
4983 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | WAYNE |  | 06 | 0901795 | This is a Facilities for Pedestrians and Bicycles project, at Cardinal Greenway & Martindale Creek, Wayne County, Economy IN; to perform Enhancement work. | Transportation Enhancements | 2010-02-22 | 2010-05-24 | 2010-09-30 | 2010-11-09 | 323246.65 | 0.010 | 0901795
4984 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901796 | This is a Maintenance Resurfacing project, at Randolph Street from 109th Avenue to 101st Avenue; to perform Surface Treatment work. | Pavement Improvement | 2010-01-27 | 2010-05-10 | 2010-06-01 | 2010-05-20 | 52157.06 | 1.000 | 0901796
4985 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901797 | This is a Maintenance Resurfacing project, at 109th Avenue from Colorado Street to Randolph Street; to perform Surface Treatment work. | Pavement Improvement | 2010-01-27 | 2010-05-10 | 2010-06-01 | 2010-05-20 | 43702.15 | 3.000 | 0901797
4986 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0901808 | This is a Safety project, at Intersection of 4th St and College Ave; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-03-23 | 2010-04-14 | 2010-08-15 | 2011-08-18 | 205727.96 | 0.010 | 0901808
4987 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | 0901809 | This is a Safety project, at Intersection of 4th St and Walnut St; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-03-23 | 2010-04-14 | 2010-08-15 | 2011-08-18 | 180669.42 | 0.010 | 0901809
4988 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901810 | This is a Maintenance Resurfacing project, at Diebold Rd from Clinton St to SR 1; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-01 | 54530.59 | 0.650 | 0901810
4989 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901811 | This is a Maintenance Resurfacing project, at Hosler Rd frm Tonkel Rd to Halter Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-05-12 | 2010-08-21 | 2010-08-02 | 185465.87 | 2.200 | 0901811
4990 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901812 | This is a Maintenance Resurfacing project, at Hursh Rd frm Auburn Rd to Tonkel Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-01 | 128772.88 | 1.780 | 0901812
4991 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901813 | This is a Maintenance Resurfacing project, at Union Chapel Rd frm Corbin Rd to Coldwater Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-01 | 69961.36 | 0.500 | 0901813
4992 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901814 | This is a Maintenance Resurfacing project, at Union Chapel Rd frm Coldwater Rd to Auburn Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-05-12 | 2010-08-21 | 2010-08-02 | 135830.54 | 0.970 | 0901814
4993 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901815 | This is a Maintenance Resurfacing project, at Union Chapel Rd frm Tonkel Rd to 160' W of Old Union Chapel; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-05-12 | 2010-08-21 | 2010-08-02 | 179324.86 | 2.000 | 0901815
4994 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901818 | This is a Maintenance Resurfacing project, at Central Avenue from I-65 to MLK Drive; to perform Surface Treatment work. | Pavement Improvement | 2010-04-09 | 2010-10-13 | 2010-09-30 | 2010-11-03 | 199796.63 | 1.340 | 0901818
4995 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901820 | This is a Maintenance Resurfacing project, at 35th Avenue from Chase Street to Grant Street; to perform Surface Treatment work. | Pavement Improvement | 2010-04-09 | 2010-10-13 | 2010-09-30 | 2010-11-03 | 124879.84 | 0.730 | 0901820
4996 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MADISON | ANDERSON | 06 | 0901823 | This is a Maintenance Resurfacing project, at CR 200E from SR 32 to CR 800N; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-17 | 2010-08-15 | 2010-08-07 | 643595.68 | 8.100 | 0901823
4997 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901824 | This is a Maintenance Resurfacing project, at Old Hobart Road from Miller Avenue to US 20; to perform Surface Treatment work. | Pavement Improvement | 2010-04-09 | 2010-10-13 | 2010-09-30 | 2010-11-03 | 158855.2 | 0.680 | 0901824
4998 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901825 | This is a Maintenance Resurfacing project, at E State Blvd: from Anthony Blvd to Hobson Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-04-02 | 2010-06-26 | 2010-11-07 | 386584.6 | 0.880 | 0901825
4999 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0901826 | This is a Maintenance Resurfacing project, at E State Blvd from Hobson Rd to Coliseum Blvd (SR 930); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2009-12-31 | 2010-04-02 | 2010-06-26 | 2010-11-07 | 221536.04 | 0.520 | 0901826
5000 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901828 | This is a trail project for pedestrians and bicycles ont the Trail along 71st St from Eagle Creek North gate to Twelve Oaks Blvd on Indianapolis west side in Marion county | Transportation Enhancements | 2010-04-23 | 2010-10-15 | 2010-10-31 | 2011-10-06 | 920711.46 | 0.840 | 0901828
5001 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901831 | This is a Facilities for Pedestrians and Bicycles project, at NYC Rail to Trail: Wallen Rd to Till Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-23 | 2010-03-18 | 2010-08-28 | 2010-10-12 | 605979.67 | 0.490 | 0901831
5002 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901833 | This is a preventive maintenance resurfacing project, at East Rudisill Blvd from Calhoun St to South Anthony Blvd Fort Wayne, Allen county to perform asphalt resurface to extend the life of the stree | Pavement Improvement | 2009-12-31 | 2010-03-18 | 2010-06-26 | 2010-11-18 | 452791.05 | 1.050 | 0901833
5003 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901834 | This is a project provide for pedestrians and bicycles on West Rudisill Blvd from Broadway to Calhoun Street in Fort Wayne in Allen county using enhancement money. This is 1 of 2 projects under contract SR-32869. | Transportation Enhancements | 2009-12-31 | 2010-03-18 | 2010-06-26 | 2010-11-18 | 181481.68 | 1.050 | 0901834
5004 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901835 | This is a Maintenance Resurfacing project, at Samuelson Road from Robbins Road to 750 Ft South of Indiana Toll Rd; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-05-25 | 2010-07-01 | 2010-07-20 | 116754.84 | 0.700 | 0901835
5005 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901836 | This is a Safety project, at Various intersections on Campbell St., Calumet Ave, Silhavy and LaPorte Ave; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2009-12-31 | 2010-01-21 | 2010-07-01 | 2010-02-18 | 78205.25 | 0.010 | 0901836
5006 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901837 | This is a Maintenance Resurfacing project, at Nebo Rd from SR 332 to River Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-05-12 | 2010-08-15 | 2010-06-23 | 286828.36 | 2.200 | 0901837
5007 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901839 | This is a Maintenance Resurfacing project, at Doyle Rd frm Dawkins Rd to Edgerton Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-09 | 38690.33 | 0.500 | 0901839
5008 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901840 | This is a Maintenance Resurfacing project, at Halter Rd frm St Joe Rd to Cedar St; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-09 | 42201.99 | 0.520 | 0901840
5009 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901841 | This is a Maintenance Resurfacing project, at Wayne Trace frm Tillman Rd to 450' S of Philley Ave (Ft Wayne City Limits); to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-09 | 135742.77 | 1.650 | 0901841
5010 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901842 | This is a Maintenance Resurfacing project, at Wheelock Rd frm Flutter Rd to St Joe Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-21 | 2010-09-09 | 157286.46 | 1.780 | 0901842
5011 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 02 | 0901848 | This is a Maintenance Resurfacing project, at Old US 33 from Ash Road to SR 19; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-07-16 | 2010-08-15 | 2010-08-14 | 677966.77 | 3.100 | 0901848
5012 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901849 | This is a Maintenance Resurfacing project, at CR 30 from CR 13 to CR 15; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-07-16 | 2010-08-15 | 2010-08-14 | 86113.32 | 1.000 | 0901849
5013 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901850 | This is a Facilities for Pedestrians and Bicycles project, at Covington Rd Trail: Beal Taylor Ditch to Eggeman Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-22 | 2010-03-18 | 2010-08-14 | 2010-11-09 | 436132 | 0.170 | 0901850
5014 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FAYETTE |  | 06 | 0901862 | This is Surface Treatment, Thin HMA Overlay on SR1, From South City Limits to North City Limits of Connersville | Pavement Improvement | 2010-10-29 | 2011-04-08 | 2011-08-12 | 2011-07-06 | 315000 | 7.170 | 0901862
5015 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901867 | This is a Maintenance Resurfacing project, at Bypass Road from West Lexington to 550 feet west of Nappanee; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-08 | 2010-05-12 | 2010-07-01 | 2010-07-09 | 119522.44 | 0.490 | 0901867
5016 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901868 | This is a Maintenance Resurfacing project, at Old US 20 from Oak Manor Place to Bypass Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-08 | 2010-05-12 | 2010-07-01 | 2010-07-09 | 54277.28 | 0.360 | 0901868
5017 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901869 | This is a Maintenance Resurfacing project, at Lexington Avenue from Bypass Road to 370' W of 22nd St.; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-08 | 2010-05-12 | 2010-07-01 | 2010-07-09 | 78671.46 | 0.460 | 0901869
5018 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901870 | This is a Maintenance Resurfacing project, at County Road 13 - Jeanwood from 100' N of East Lake Drive N to C.R. 6; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-01-06 | 2010-06-25 | 2010-08-01 | 2010-07-06 | 126939.43 | 1.080 | 0901870
5019 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FLOYD | LOUISVILLE (KY)-IN | 09 | 0901871 | This is a Safety project, at Intersection of Pearl St. and Elm St.; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-03-23 | 2010-04-20 | 2010-06-16 | 2010-07-07 | 127102.64 | 0.010 | 0901871
5020 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 0901877 | This is a Maintenance Resurfacing project, at Bremen Highway from Ireland Road to US 20 By-Pass; to perform Surface Treatment work. | Pavement Improvement | 2010-02-22 | 2010-05-11 | 2010-09-30 | 2010-06-15 | 158503.46 | 0.450 | 0901877
5021 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901878 | This is a Reconstruction (no added capacity) project, at Middlebury St: from Main St to Zollinger Rd; to perform Other Roadside Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-07-19 | 2010-08-06 | 2010-08-19 | 175611.5 | 0.890 | 0901878
5022 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901879 | This is a PreventiveMaintenance Resurfacing project, at Dierdorff Rd (CR 27) from CR 40 to Kercher Rd in Elkhart county that will exend the life of the pavement. | Pavement Improvement | 2010-02-22 | 2010-07-02 | 2010-08-06 | 2010-08-04 | 104187.92 | 1.010 | 0901879
5023 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 0901880 | This is a Maintenance Resurfacing project, at Clinton St: from 410' West of Tanglewood Dr to Green Rd; to perform Other Roadside Maintenance work. | Pavement Improvement | 2010-02-22 | 2010-07-13 | 2010-08-06 | 2010-08-18 | 148718.81 | 0.570 | 0901880
5024 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ALLEN |  | 06 | 0901914 | This is a Bridge Rehabilitation (no added capacity) project, at Bridge # 268 over St Mary's River on Bostick Rd (Pedestrian); to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2010-04-10 | 2010-05-21 | 2010-10-30 | 2010-11-19 | 1223204.5 | 0.040 | 0901914
5025 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 0901915 | This is a Maintenance Resurfacing project, at 93rd Ave.- Cline to Marquette, Deodor to Hart St and White Oak to W of Columbia; to perform Surface Treatment, Thin asphalt resurface work. | Pavement Improvement | 2010-04-01 | 2010-08-06 | 2010-08-01 | 2010-09-07 | 320852.9 | 2.770 | 0901915
5026 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | VIGO | TERRE HAUTE | 08 | 0901923 | This is a Maintenance Resurfacing project, at From US 41 to 7th St; to perform Partial 3-R work. | Pavement Improvement | 2010-04-01 | 2010-06-21 | 2010-07-30 | 2010-08-05 | 79737.73 | 0.400 | 0901923
5027 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901926 | This is a Facilities for Pedestrians and Bicycles project, at Fort Wayne Rivergreenway Maintenance-Boardwalk decking & Bridge hand Rails; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-01-06 | 2010-03-15 | 2010-06-26 | 2010-08-06 | 292076.01 | 0.390 | 0901926
5028 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901930 | This is a Maintenance Resurfacing project, at Carroll Rd from 79th St to 86th St; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-04-01 | 2010-07-06 | 2010-08-13 | 2010-08-10 | 303874.44 | 1.000 | 0901930
5029 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 0901931 | This is a Maintenance Resurfacing project, at Carroll Rd from Pendleton Pike to 75th St; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-04-01 | 2010-07-06 | 2010-08-13 | 2010-08-10 | 88201.69 | 0.200 | 0901931
5030 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901939 | This project is a preventive naintenance resurfacing project on Bluffton Road from Liberty Dr to Old Trail Road in Allen county to extend the service life of the pavement. | Pavement Improvement | 2010-02-22 | 2010-06-01 | 2010-06-26 | 2010-07-01 | 162361.58 | 0.510 | 0901939
5031 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901944 | This is a Maintenance Resurfacing project, at N River Rd from Corporate Limits (1,500' W of Landin Rd) to 570' Wof Landin Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-07-15 | 2010-08-14 | 2010-08-19 | 31959.5 | 0.180 | 0901944
5032 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901945 | This is a preventive maintenance project which will extend the service life of the road, on Moeller Rd from West of Quail Creek Blvd to the city limits west of Woodland Dr in Allen county. | Pavement Improvement | 2010-04-01 | 2010-07-15 | 2010-08-14 | 2010-08-19 | 56044.16 | 0.410 | 0901945
5033 | INDIANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901946 | This project will upgrade the traffic signals on Kossuth Street at 16th Street And 18th Street in Tippecanoe County. | Safety/Traffic Management | 2010-05-21 | 2010-06-24 | 2010-08-31 | 2010-06-30 | 18680.5 | 0.100 | 0901946
5034 | INDIANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901947 | This project will upgrade the traffic signals at 26th Street And Earl/hedgewood in Tippecanoe County. | Safety/Traffic Management | 2010-05-21 | 2010-06-24 | 2010-08-31 | 2010-06-30 | 53988.5 | 0.100 | 0901947
5035 | INDIANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | 0901948 | This project will upgrade the traffic signals at 36th Street And At Shenandoah in Tippecanoe County. | Safety/Traffic Management | 2010-05-21 | 2010-06-24 | 2010-08-31 | 2010-06-30 | 50175.4 | 0.100 | 0901948
5036 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RANDOLPH |  | 06 | 0901950 | This proejct clears the right of way in preparation for a major road reconstruction project on Parcels 17 and 35 to remove and demolish buildings on SR 32 in Randolf county on the east side of Winchester. | Other | 2010-03-24 | 2010-03-30 | 2010-04-15 | 2010-04-14 | 21812.5 | 0.220 | 0901950
5037 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901954 | This is a Facilities for Pedestrians and Bicycles project, at NYC Rail to Trail: Till Rd to 0.4 miles N of Till Rd; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-02-22 | 2010-04-01 | 2010-08-28 | 2010-09-22 | 536636.34 | 0.400 | 0901954
5038 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | DELAWARE | MUNCIE | 06 | 0901981 | This is a Safety project, at Madison St at 29th St and 26th St; to perform Traffic Signals Modernization work. | Safety/Traffic Management | 2010-04-27 | 2010-05-25 | 2010-06-25 | 2010-08-31 | 193786.4 | 0.010 | 0901981
5039 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901995 | This is a Maintenance Resurfacing project, at North River Rd from Landin Rd to I-469; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 128378.93 | 1.450 | 0901995
5040 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901996 | This is a Maintenance Resurfacing project, at Thomas Rd from RR Xing 3100' North of Illinois Rd to Bass Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 65247.49 | 0.370 | 0901996
5041 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901997 | This is a Maintenance Resurfacing project, at Monroeville Road from US 27 to Marion Center Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 98193.65 | 1.310 | 0901997
5042 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901998 | This is a Maintenance Resurfacing project, at Scott Road from RR Crossing 725' South of Seegar Blvd to Bass Rd; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 40300.26 | 0.350 | 0901998
5043 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0901999 | This is a Maintenance Resurfacing project, at Knoll Road from Smith Road to Ardmore Avenue; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 55867.54 | 1.000 | 0901999
5044 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0902000 | This is a Maintenance Resurfacing project, at Seiler Road from Adams Center Road to Green Road; to perform asphalt resurface, Preventive Maintenance work. | Pavement Improvement | 2010-04-01 | 2010-06-09 | 2010-08-14 | 2010-09-01 | 225029.23 | 2.480 | 0902000
5045 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | Multiple | 0902011 | This is Bridge Replacement, Other Construction on I465, WB 82nd St over I465 | Bridge Replacement | 2010-11-01 | 2010-12-28 | 2011-10-15 | 2012-04-09 | 1050000 | 0.010 | 0902011
5046 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0902180 | This is a Safety project, at Guardrail upgrades to various bridges in Northeast Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 2010-04-01 | 2010-05-07 | 2010-08-21 | 2010-06-25 | 104749 | 1.000 | 0902180
5047 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0902181 | This is a Safety project, at Guardrail upgrades to various bridges in Northwest Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 2010-04-01 | 2010-05-06 | 2010-08-21 | 2010-07-12 | 132833.16 | 1.000 | 0902181
5048 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | 03 | 0902182 | This is a Safety project, at Guardrail upgrades to various bridges in Southeast Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 2010-04-01 | 2010-06-03 | 2010-08-21 | 2010-06-21 | 90639.14 | 1.000 | 0902182
5049 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ALLEN | FORT WAYNE | Multiple | 0902183 | This is a Safety project, at Guardrail upgrades to various bridges in Southwest Allen Co (See Log); to install New Guard Rail work. | Safety/Traffic Management | 2010-04-01 | 2010-05-05 | 2010-08-21 | 2010-07-08 | 67410.9 | 1.000 | 0902183
5050 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | RANDOLPH |  | 06 | 1004017 | This project will replace the bridge on SR 32 over Sparrow Creek in Randolph County.. | Bridge Replacement | 2009-05-13 | 2009-07-29 | 2009-11-20 | 2009-11-20 | 867750 | 0.010 | 1004017
5051 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005675 | This is Roadside Maintenance, Herbicide, Various Counties - at various locations within the Crawfordsville District. | Transportation Enhancements | 2010-10-20 | 2011-08-01 | 2012-09-30 | 2012-09-25 | 250760.67 | 0.010 | 1005675
5052 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005726 | This is Roadside Maintenance, Herbicide, Various Counties - at various locations along two lane roads in the Angola, Elkhart and FtWayne Subdistricts | Transportation Enhancements | 2010-10-12 | 2011-06-02 | 2011-06-15 | 2011-06-27 | 106096.76 | 0.030 | 1005726
5053 | INDIANA | Underway | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005729 | This is Roadside Maintenance, Landscaping, various counties, at various locations along I-65, I-70, I-74 and SR 63 within the Crawfordsville District | Transportation Enhancements | 2010-10-12 | 2011-03-29 | 2011-07-01 |  | 479792.5 | 0.010 | 1005729
5054 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005730 | This is Roadside Maintenance, Herbicide, Various Counties - at various locations within the LaPorte District. | Transportation Enhancements | 2010-10-20 | 2011-09-13 | 2011-11-30 | 2011-11-19 | 306318.85 | 0.030 | 1005730
5055 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005731 | This is Roadside Maintenance, Herbicide, Various Counties - at various locations within the LaPorte District. | Transportation Enhancements | 2010-10-12 | 2011-09-29 | 2011-11-30 | 2011-11-28 | 119125 | 0.030 | 1005731
5056 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | STATEWIDE |  |  | 1005732 | This is Roadside Maintenance, Landscaping, Marshall County, at various locations along US 31 and US 30 Interchange | Transportation Enhancements | 2010-10-12 | 2011-02-23 | 2012-06-01 | 2012-06-01 | 174700 | 0.030 | 1005732
5057 | INDIANA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | INDIANA | GREENE |  | 08 | 1005845 | This is a rail road grade crossing repair project for multiple crossings in the towns of Jasonville,Dugger, & Linton in Greene County within a corridor streching 10.6 miles. | Safety/Traffic Management | 2011-01-20 | 2011-05-02 | 2011-10-15 | 2011-12-31 | 4904255 | 0.010 | 1005845
5058 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | 04 | 1441044 | This is a Maintenance Resurfacing project, at From 4th St, 1.02 miles W of E jct with US 231, to E jct with US 231; to perform asphalt resurface, Functional work. | Pavement Improvement | 2010-05-19 | 2010-07-06 | 2010-10-31 | 2011-06-17 | 2618383.48 | 0.990 | 1441044
5059 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 1475040 | This project will improve drainage by replacing the structure on US 35 ofer Laramore Ditch in Starke County. | Pavement Improvement | 2009-06-04 | 2009-08-04 | 2009-11-01 | 2009-11-30 | 755990.17 | 0.010 | 1475040
5060 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LA PORTE |  | 02 | 1477002 | This is a Safety project, at US 35 - At Schultz Rd, 0.14 mile N of I-80/90 Underpass; to perform Sight Distance Improvement work. | Safety/Traffic Management | 2009-10-08 | 2009-10-12 | 2010-08-13 | 2010-08-06 | 909249.18 | 0.270 | 1477002
5061 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 1531031 | This is a Bridge Replacement (capacity added) project, at Bridge over Little Buck Creek, 1.16 miles S of I-465; to perform Bridge Replacement, Other Construction work. | Bridge Replacement | 2010-02-20 | 2010-03-15 | 2011-08-02 | 2011-10-12 | 3130889 | 0.110 | 1531031
5062 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 1621002 | This project will add turn lanes and improve the intersection of US 19 and county road 42 in Elkhart County. | Pavement Widening | 2009-08-18 | 2010-04-01 | 2010-06-30 | 2010-07-21 | 812909 | 0.010 | 1621002
5063 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 1810014 | This is a Reconstruction (no added capacity) project, at SR 15 - Over Wolf Lake Drain, 2.65 miles N of US 33; to perform Small Structure, Replacement work. | Pavement Improvement | 2009-10-14 | 2010-07-28 | 2010-10-01 | 2010-09-17 | 479931.03 | 0.010 | 1810014
5064 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 1941018 | This project will improve and widen intersections along SR 8 and SR 49 in Porter County. | Safety/Traffic Management | 2009-08-27 | 2009-10-22 | 2010-06-29 | 2010-11-23 | 1947964 | 0.930 | 1941018
5065 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 2127112 | This project will widn US 6 in Elkhart County with the installation of sidewalks along the North side of the road and a wider median. | Pavement Widening | 2009-07-17 | 2010-03-03 | 2010-10-22 | 2010-11-12 | 4949108 | 0.940 | 2127112
5066 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | WHITLEY |  | 03 | 2192034 | This is a Reconstruction (no added capacity) project, at US 33 - At Clingerman Avenue, 0.5 mile N of SR 205; to perform Curve Correction work. | Pavement Improvement | 2009-09-08 | 2009-10-21 | 2010-06-18 | 2010-06-11 | 302904 | 0.100 | 2192034
5067 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | 2195026 | This project will construct a median left turn lane on US 33 near US 20 in Dunlap, Elkhart County. New pavement, drainage structures, signals and signs will be placed and a bridge widened. | New Construction | 2009-03-27 | 2009-07-23 | 2011-10-07 | 2011-11-18 | 10765478.72 | 5.420 | 2195026
5068 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | UNION |  | 06 | 2493013 | This project will repair and restore the pavement and replace signs on US 27 from the Ohio State line north 3.6 miles in Union county. | Pavement Widening | 2009-04-15 | 2009-08-05 | 2012-02-10 | 2011-11-16 | 9345892.93 | 3.580 | 2493013
5069 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | GRANT |  | 05 | 3227023 | This project will improve the sight distance at SR 26 and county road 750 south in Grant County. | Pavement Improvement | 2009-07-07 | 2009-08-21 | 2009-11-13 | 2010-04-19 | 925540.16 | 0.200 | 3227023
5070 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FULTON |  | 02 | 3325007 | This project will replace the bridge on SR 17 over Starr Ditch in Fulton County. | Bridge Replacement | 2009-04-17 | 2009-07-06 | 2009-11-14 | 2009-09-25 | 556948.74 | 0.010 | 3325007
5071 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | HANCOCK | INDIANAPOLIS | 05 | 3630005 | This is a trail project for pedestrians and bicycles on the Pennsy Trail from just East of German Church Road to Mt. Comfort Road ( Hancock county road 600 W) using enhanacment funds. | Transportation Enhancements | 2010-03-04 | 2010-03-31 | 2010-11-15 | 2010-11-11 | 1641150 | 2.000 | 3630005
5072 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HENDRICKS |  | 04 | 3632005 | This project will improve the surface and rebuild sections of the bridge on US 40 over White Lick Creek in Hendricks County. | Pavement Improvement | 2009-03-24 | 2009-04-20 | 2009-11-24 | 2010-06-30 | 2847000 | 0.010 | 3632005
5073 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SULLIVAN |  | 08 | 3677012 | This project will improve the intersection on SR 54 and add turn lanes at County Road 50 South, 1 mile West of SR 159. | Pavement Improvement | 2009-05-08 | 2009-07-14 | 2010-04-17 | 2010-03-19 | 717361.6 | 0.110 | 3677012
5074 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ADAMS |  | 06 | 3801006 | This is a Bridge Replacement (no added capacity) project, at Bridge over Smith-Shoemaker Ditch, 2.1 miles E of US 27; to perform Bridge Replacement work. | Bridge Replacement | 2010-03-23 | 2010-07-19 | 2010-10-16 | 2010-09-21 | 684476.62 | 0.010 | 3801006
5075 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | SCOTT |  | 09 | 4072004 | This project will replace the bridge on SR 356 over Town Creek in Scott County. | Bridge Replacement | 2009-03-19 | 2009-04-07 | 2009-10-31 | 2009-10-23 | 627953.34 | 0.200 | 4072004
5076 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 04 | 4223005 | This project will replace and restore the pavement, storm sewers, and water lines on US 136 in Covington. | Pavement Improvement | 2009-06-17 | 2009-07-16 | 2010-08-31 | 2010-09-17 | 3270050.51 | 1.020 | 4223005
5077 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW | COLUMBUS | 06 | 4303009 | This project will add turn lanes, nodernize the signal, and widen the intersection at SR 11and Bartholomw county Road 450S. | Pavement Improvement | 2009-05-06 | 2009-06-01 | 2010-08-15 | 2010-11-01 | 1202944.2 | 0.010 | 4303009
5078 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | CLINTON |  | 04 | 4312005 | This project will improve the sight distance at SR 75 and county road 700 north in Clinton County. | Safety/Traffic Management | 2009-06-03 | 2009-06-24 | 2009-11-15 | 2009-11-21 | 1206807.56 | 0.860 | 4312005
5079 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MORGAN |  | 04 | 4455005 | This project will replace and restore the pavement on SR 42 in Morgan County from Monrovia to Martinsville. | Pavement Improvement | 2009-06-04 | 2009-07-07 | 2010-11-20 | 2011-07-21 | 7339345 | 11.960 | 4455005
5080 | INDIANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | INDIANA | STARKE |  | 02 | 4475002 | This project will improve drainage by replacing the structure over Cannon ditch on SR 8 in Starke County | Pavement Improvement | 2009-08-19 | 2009-09-30 | 2009-10-31 | 2009-11-15 | 346456.39 | 0.010 | 4475002
5081 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FOUNTAIN |  | 04 | 4923003 | This project will improve the surface and rebuild sections of the bridge on SR 341 over I-74 in Fountain County. | Bridge Improvement | 2009-03-23 | 2009-04-03 | 2009-07-31 | 2009-08-05 | 1220119 | 0.010 | 4923003
5082 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HENRY |  | 06 | 5133003 | This is a Bridge New Construction project, at 5.36 miles N of US 40; to perform New Br, Precast 3 Sided Culvert work. | New Bridge Construction | 2010-03-23 | 2010-05-18 | 2010-10-30 | 2011-05-15 | 404395.98 | 0.228 | 5133003
5083 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HENRY |  | 06 | 5133004 | This project replaces a old small drainage culvert on SR 103, 4 miles north of US 40 in Henry county. | Pavement Improvement | 2010-03-23 | 2010-05-18 | 2010-10-30 | 2011-05-15 | 425503.02 | 0.239 | 5133004
5084 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH |  | 02 | 5171008 | This project will improve drainage by replacing the structure on SR 331 over Madison Township Ditch in St. Joseph County. | Pavement Improvement | 2009-03-24 | 2009-06-01 | 2009-08-29 | 2009-08-07 | 618614.21 | 0.010 | 5171008
5085 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MIAMI |  | 05 | 5252007 | This project will improve drainage by replacing the structure on SR 16 over Washonis Creek in Miami County. | Pavement Improvement | 2009-09-08 | 2009-10-19 | 2010-09-03 | 2010-07-14 | 397020.7 | 0.100 | 5252007
5086 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JEFFERSON |  | 09 | 5639005 | This project will improve the sight distance at SR 250 and Scott Ridge Road in Jefferson County. | Safety/Traffic Management | 2009-05-08 | 2009-07-17 | 2009-09-25 | 2009-11-25 | 681704.39 | 0.010 | 5639005
5087 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 8571960 | This is a Reconstruction (no added capacity) project, at US 41 - At 93rd Ave, 1.9 miles N of US 231; to perform Intersection Improvement work. | Pavement Improvement | 2009-06-30 | 2009-07-28 | 2009-10-31 | 2009-12-02 | 2009237.54 | 0.010 | 8571960
5088 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART |  | 03 | 9031815 | This project will improve drainage by replacing the structure on SR 19 over Fisher-Gordon Ditch in Elkhart County. | Pavement Improvement | 2009-05-18 | 2009-07-22 | 2009-10-09 | 2009-10-21 | 526058.11 | 0.100 | 9031815
5089 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | HARRISON |  | 09 | 9032075 | This project will improve drainage by replacing a pipe on SR 11 on the East side of Elizabeth. | Pavement Improvement | 2009-07-09 | 2009-07-31 | 2009-10-17 | 2009-10-08 | 272187.22 | 0.010 | 9032075
5090 | INDIANA | Completed | C200 | Highway Infrastructure Investment Grant | INDIANA | HUNTINGTON |  | 05 | 9301060 | This project will improve drainage by replacing the structure on SR 5 over Loon Creek in Huntington County. | Pavement Improvement | 2009-08-14 | 2009-09-15 | 2009-10-23 | 2009-11-13 | 491081.17 | 0.010 | 9301060
5091 | INDIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 9381900 | This is a road reconstruction project that will completly reconstruct the road and add lanes to increase the capacity of the road on Miami St from Kern Rd to Jackson Rd in St Joseph county. | Pavement Widening | 2010-04-22 | 2010-05-03 | 2010-10-15 | 2010-11-22 | 1891030.49 | 1.040 | 9381900
5092 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9610820 | This project will replace the bridge on SR 312 over the Indiana Harbor Canal in Lake County. | Bridge Replacement | 2009-06-18 | 2009-07-06 | 2009-10-31 | 2009-11-01 | 1942446.84 | 0.010 | 9610820
5093 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | STEUBEN |  | 03 | 9803670 | This project will rebuild the US 20 and I-69 interchange in Steuben county to improve traffic flow. | Bridge Replacement | 2009-06-01 | 2009-06-12 | 2010-10-15 | 2010-10-12 | 1994588.32 | 0.490 | 9803670
5094 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | 9901720 | This project will replace the bridge on Locust Road over US 20 in St Joseph County. | Bridge Replacement | 2009-06-03 | 2009-06-16 | 2009-09-18 | 2009-11-17 | 2926297.42 | 0.090 | 9901720
5095 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER |  | 01 | 9901740 | This project will replace the bridge on SR 49 over Pleasant Township Ditch in Porter County. | Bridge Replacement | 2009-05-13 | 2009-06-26 | 2009-10-31 | 2009-10-29 | 758632.98 | 0.010 | 9901740
5096 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | MARTIN |  | 08 | 9903160 | This is a Reconstruction (no added capacity) project, at 3.38 miles E of SR 650; to perform Small Structure Replacement work. | Pavement Improvement | 2010-03-24 | 2010-04-14 | 2010-07-31 | 2010-09-02 | 681346.01 | 0.100 | 9903160
5097 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | FRANKLIN |  | 06 | 9924012 | This is a Bridge Replacement (no added capacity) project, at Bridge #94 over E Fork Blue Creek, carrying Blue Creek; to perform Br Repl, Comp.Cont.Pres.Conc. I-Beam work. | Bridge Replacement | 2010-04-01 | 2010-04-12 | 2010-10-01 | 2010-10-07 | 829328.76 | 0.010 | 9924012
5098 | INDIANA | Completed | C250 | Highway Infrastructure Investment Grant | INDIANA | KOSCIUSKO |  | 03 | 9943052 | This is a Bridge New Construction project, at Bridge over Waubee Drain, 3.39 miles S of US 6; to perform New Bridge, Other Construction work. | New Bridge Construction | 2010-02-20 | 2010-03-26 | 2010-09-25 | 2010-09-28 | 647849.2 | 0.010 | 9943052
5099 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9945111 | This is a trail project for pedestrians and bicycles and is the Phase 1 of the Bike Network in Crown Point, Lake county using enhancement funds. | Transportation Enhancements | 2010-02-24 | 2010-03-22 | 2010-10-15 | 2011-10-28 | 899763.55 | 0.010 | 9945111
5100 | INDIANA | Completed | C220 | Highway Infrastructure Investment Grant | INDIANA | WHITE |  | Multiple | 9991027 | This project builds a new trail for pedestrians and bicycle, at Tioga Bridge as a bike/ped crossing over Lake Freeman and Tippecanoe River in White county. | Transportation Enhancements | 2010-01-19 | 2010-03-22 | 2010-10-15 | 2010-10-09 | 1082406.81 | 0.010 | 9991027
5101 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999193 | This project will extend the bridge life by repainting bridge beams at SR 49 over US 30 and SR 2 in Porter County. | Bridge Improvement | 2009-05-13 | 2009-06-30 | 2009-09-03 | 2009-09-03 | 346415.56 | 0.010 | 9999193
5102 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | PORTER | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999194 | This project will extend the bridge life by repainting bridge beams at Calumet Ave over SR 49 and US 6 in Porter County. | Bridge Improvement | 2009-05-13 | 2009-06-30 | 2009-09-09 | 2009-09-04 | 347985.54 | 0.010 | 9999194
5103 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | 9999228 | This project will upgrade and modernize the traffic signal at US 41 and 93rd Avenue in Lake County. | Safety/Traffic Management | 2009-06-30 | 2009-07-28 | 2009-10-31 | 2009-12-02 | 105696.65 | 0.010 | 9999228
5104 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 9999231 | This project will add turn lanes and improve the intersection of SR 25 at county road 575 west and county road 500 west in Tippecanoe County. | Pavement Widening | 2009-04-15 | 2009-05-04 | 2009-10-31 | 2009-11-05 | 1314059.37 | 1.120 | 9999231
5105 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | JACKSON |  | 09 | 9999235 | This project will improve sections and extend the life of SR 11 from SR 250 to US 50 in Jackson County with a pavement surface overlay. | Pavement Improvement | 2009-09-11 | 2009-09-28 | 2009-11-30 | 2010-05-27 | 1076072.1 | 8.010 | 9999235
5106 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE |  | 04 | 9999236 | This is phase I of the Hoosier Heartland project in TippecanoeCounty, extending from County Road 750E to the Norfolk Southern Railroad. The project includes eight new bridges along the new alignment of SR 25. | New Bridge Construction | 2009-06-15 | 2009-08-04 | 2011-10-31 | 2012-07-27 | 1025634.93 | 0.010 | 9999236
5107 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | MARION | INDIANAPOLIS | 07 | 9999241 | This is a Bridge Rehabilitation (no added capacity) project, at 21st Street over Big Eagle Creek; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2009-12-03 | 2010-06-01 | 2010-09-30 | 2010-09-28 | 546435.69 | 0.064 | 9999241
5108 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | ST JOSEPH | SOUTH BEND (MI) | 02 | A500030 | This is Bridge Replacement - STR NO 331-71-8899, Precast 3 sided box culvert, one span, total length 20', St Joseph County on US 331 over Grimes Ditch, 4.86 miles south of SR933. | Bridge Replacement | 2010-10-08 | 2011-03-16 | 2011-06-04 | 2011-05-13 | 110869.63 | 0.030 | A500030
5109 | INDIANA | Completed | C230 | Highway Infrastructure Investment Grant | INDIANA | LAKE | CHICAGO-NORTHWESTERN INDIANA (IL) | 01 | A501115 | This is Demolition of Bridge and Ramp D, Lake County - on SR 912 at Riley Road | Other | 2010-10-18 | 2010-12-02 | 2011-03-28 | 2011-03-28 | 1020473.75 | 0.010 | A501115
5110 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | HOWARD | KOKOMO | 05 | A600560 | This project is the 4th phase of a road reconstruction project that will totally reconstruct the pavement and add travel lanes on Dixon Road from Sycamore to Judson in Kokomo, Howard county. | Pavement Widening | 2010-04-15 | 2010-05-05 | 2012-08-31 | 2011-11-19 | 2107988 | 1.207 | A600560
5111 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | ELKHART | ELKHART-GOSHEN | 03 | A710953 | This is a Bridge Rehabilitation (no added capacity) project, at Indiana Ave historic bridge, on Indiana Ave where it crosses Elkhart River; to perform Bridge Maintenance And Repair work. | Bridge Improvement | 2010-05-12 | 2010-06-05 | 2010-10-15 | 2011-07-27 | 479577.57 | 0.030 | A710953
5112 | INDIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | INDIANA | MONROE | BLOOMINGTON | 09 | A901422 | This is a Facilities for Pedestrians and Bicycles project, at B-Line Trail phase 2; to perform Bike/Pedestrian Facilities work. | Transportation Enhancements | 2010-04-21 | 2010-05-17 | 2011-06-29 | 2011-09-07 | 2057179.92 | 2.400 | A901422
5113 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | BARTHOLOMEW | COLUMBUS | 06 | G195003 | This is a Maintenance Restoration & Rehabilitation project, at 17th St from US 31 to Central Ave; to perform Road Reconstruction work. | Pavement Improvement | 2010-01-13 | 2010-02-22 | 2011-10-31 | 2011-11-23 | 1661117 | 1.000 | G195003
5114 | INDIANA | Completed | C240 | Highway Infrastructure Investment Grant | INDIANA | TIPPECANOE | LAFAYETTE-WEST LAFAYETTE | 04 | L720015 | This project will build a new bridge on US 52 over the Norfolk Southern Railroad, 2 miles South of SR 25 in Tippecanoe County. | New Bridge Construction | 2009-06-05 | 2009-08-20 | 2010-11-30 | 2010-11-23 | 6291766.4 | 0.010 | L720015
5115 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE | OMAHA (NE)-IA | 05 | 000R001 | This project will provide grading, drainage, paving, electrical and lighting for an intermodal facility owned by the Iowa Interstate Railroad in Council Bluffs. The facility is located northeast of th | Other | 2010-02-11 | 2010-04-05 | 2010-12-01 | 2011-01-28 | 2000000 | 0.000 | 000R001
5116 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | FAYETTE |  | 01 | 000R002 | This project will replace track ballast and ties on 14 miles of D&W Railroad track between Dewar and Oelwein to improve operational efficiency and safety. | Other | 2010-01-06 | 2010-05-03 | 2010-12-01 | 2010-08-23 | 764200 | 0.000 | 000R002
5117 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | 000R003 | This ARRA project will construct part of a new rail based industrial park being developed by the Clinton Regional Development Corporation. Rail construction includes: construction of a 10,000 feet pas | New Bridge Construction | 2010-02-23 | 2010-02-23 | 2010-12-01 | 2011-07-06 | 2090186.83 | 0.000 | 000R003
5118 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 000R004 | This project will upgrade the electrical components of the swing span railroad bridge over the Mississippi River between Keokuk, Iowa and Hamilton, Illinois. The project updates the electrical system | Transportation Enhancements | 2010-02-23 | 2010-08-23 | 2010-12-01 | 2011-03-17 | 120500 | 0.000 | 000R004
5119 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | PAGE |  | 05 | 0022044 | This project will provide an improved driving surface by widening and resurfacing 2.0 miles of Iowa Highway 2 from W State Street to S 16th Street in Clarinda with hot-mix asphalt. | Pavement Improvement | 2009-03-30 | 2009-04-06 | 2009-11-01 | 2010-01-05 | 848817 | 1.900 | 0022044
5120 | IOWA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | IOWA | DECATUR, RINGGOLD |  | 05 | 0024043 | This project will provide an improved driving surface by widening and resurfacing 11.51 miles of Iowa Highway 2 from Kellerton east to I-35 with Hot-Mix Asphalt. This project also includes the replacement of five bridges along Highway 2. | Pavement Improvement | 2010-11-01 | 2011-03-30 | 2011-07-01 | 2011-08-18 | 3076622.76 |  | 0024043
5121 | IOWA | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | DAVIS |  | 02 | 0028035 | This project will provide an improved driving surface by widening and resurfacing with hot-mix asphalt 4.9 miles of Iowa Highway 2/US Highway 63 through Bloomfield from the west junction of these highways to their east junction. | Pavement Improvement | 2009-06-29 | 2009-07-20 | 2010-07-01 | 2010-05-13 | 3651402.77 | 5.000 | 0028035
5122 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | PLYMOUTH |  | 05 | 0031075 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 3/South Dakota 50 over the Big Sioux River 0.5 miles North and 1.7 miles West of Westfield, Iowa. | Bridge Replacement | 2009-03-06 | 2009-03-30 | 2009-11-01 | 2010-11-19 | 1842961 | 0.000 | 0031075
5123 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | BUENA VISTA |  | 05 | 0032053 | This project will replace a bridge, which is in poor condition and narrow with a new bridge. The bridge is on Iowa 3 over Brooke Creek 6.1 miles West of US 71 or approximately 10 miles Northwest of Storm Lake. | Bridge Replacement | 2009-07-31 | 2010-04-19 | 2010-11-01 | 2011-07-27 | 782441 | 0.000 | 0032053
5124 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 0064152 | This project will reconstruct and widen approximately 900 feet of 111th Street south and west of the intersection with US Highway 6 (Hickman Road) in the City of Clive. The project will include concr | Pavement Improvement | 2010-01-05 | 2010-07-23 | 2010-12-01 | 2011-06-15 | 586698 | 0.250 | 0064152
5125 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | WEBSTER, CALHOUN |  | 04 | 0074017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 11.7 miles of Iowa Highway 7 from 0.5 miles west of the Calhoun County Line to US Highway 169 in Calhoun County. | Pavement Improvement | 2009-03-26 | 2009-04-13 | 2009-12-01 | 2009-12-28 | 5364499 | 11.900 | 0074017
5126 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | OSCEOLA |  | 05 | 0092021 | This project will improve the driving surface by applying an unbonded portland cement concrete overlay on approximately 8.6 miles of Iowa Highway 9 from just west of Polk Avenue to just east of Tanager Avenue in Osceola County. | Pavement Improvement | 2009-03-30 | 2009-05-04 | 2009-11-01 | 2010-01-19 | 4865289 | 8.800 | 0092021
5127 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 0132615 | Polk County is constructing a 0.4 mile extension of Adventureland Drive NW. The project will widen Adventureland Drive NW from a 2-lane roadway to a 4-lane roadway with median, sidewalk, and left-tur | Pavement Improvement | 2009-09-14 | 2009-09-22 | 2010-12-01 | 2010-08-30 | 706977 | 0.300 | 0132615
5128 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY | AMES | 04 | 0155662 | This project is in the city of Ames on George W. Carver Avenue from Stange Road to Bloomington Road. The project consists of one inch of hot-mix asphalt stress relief course and six inches of concret | Pavement Improvement | 2009-09-28 | 2009-10-12 | 2010-12-01 | 2011-03-09 | 717794 | 0.900 | 0155662
5129 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY | AMES | 04 | 0155664 | This project is in the city of Ames on Lincoln Way from Hickory Drive to just past Marshall Avenue. The project consists of milling the existing surface, patching problem areas, resurfacing with hot- | Pavement Improvement | 2009-08-27 | 2009-09-18 | 2010-12-01 | 2009-12-29 | 530759.85 | 0.300 | 0155664
5130 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | STORY | AMES | 04 | 0155665 | This project will provide for the construction of .6 miles of the Skunk River Trail that will run along the west side of South Skunk River from just south of East 13th Street in South River Valley Par | Transportation Enhancements | 2009-08-27 | 2009-09-18 | 2010-12-01 | 2010-11-15 | 175728 | 0.600 | 0155665
5131 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY | AMES | 04 | 0155668 | This project consists of milling and resurfacing with asphalt 0.44 miles of roadway along Duff Avenue from 7th Street N. to 13th Street in Ames, Iowa. | Pavement Improvement | 2010-01-14 | 2010-09-16 | 2010-12-01 | 2011-10-25 | 497038.42 | 0.440 | 0155668
5132 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | WAPELLO |  | 02 | 0161017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 5.3 miles of Iowa Highway 16 from US Highway 34 to north city limit of Eldon in Wapello County. | Pavement Improvement | 2009-04-01 | 2009-04-06 | 2009-12-01 | 2009-10-07 | 1837373 | 5.500 | 0161017
5133 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | DAVIS, WAPELLO, VAN BUREN |  | 02 | 0161018 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 0.16 miles of Iowa Highway 16 from north city limit of Eldon to 9th Street in Wapello County. | Pavement Improvement | 2009-04-01 | 2009-04-06 | 2009-12-01 | 2009-10-07 | 1450974.35 | 4.300 | 0161018
5134 | IOWA | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | CALHOUN |  | 04 | 0203083 | Grading of relocated US 20 in Iowa, from the east Sac County line to County Road N-33 in Calhoun County, 2.6 miles. | New Construction | 2010-03-01 | 2010-04-12 | 2010-12-01 | 2012-02-15 | 2874975.12 | 4.200 | 0203083
5135 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CHICKASAW |  | 04 | 0241017 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 6.75 miles of Iowa Highway 24 from east city limit of New Hamp | Pavement Improvement | 2009-04-03 | 2009-04-20 | 2009-11-01 | 2010-09-07 | 3200829 | 7.800 | 0241017
5136 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CHICKASAW, WINNESHIEK |  | 04 | 0241020 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay with cold-in-place recycling on approximately 6 miles of Iowa Highway 24 from the west city limit of Lawler to County Road V-68 in Chickasaw County. | Pavement Improvement | 2009-04-03 | 2009-04-20 | 2009-11-01 | 2010-09-07 | 2566288 | 6.300 | 0241020
5137 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CASS |  | 05 | 0285612 | This project replaces the bridge supports, which are in very poor condition, to extend the service life of the bridge. The bridge is located on Nishna Street over an unnamed creek just South of 29th Street in Atlantic. | Bridge Improvement | 2009-10-12 | 2009-11-02 | 2009-12-01 | 2010-05-20 | 92520 | 0.000 | 0285612
5138 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CASS |  | 05 | 0285613 | This project is in Atlantic, Iowa on South Olive Street from East 14th Street to East 22nd Street. The project consists of pavement rehabilitation which will provide a smoother ride and improved drainage. | Pavement Improvement | 2010-01-21 | 2010-07-15 | 2010-12-01 | 2010-11-01 | 175000 | 0.500 | 0285613
5139 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | FREMONT |  | 05 | 0291068 | This project will replace two bridges, which are in poor condition, with new bridges. The bridges are on Interstate 29 over Plum Creek 0.5 miles South of Exit #20, or approximately 28 miles South of Council Bluffs. | Bridge Replacement | 2009-03-06 | 2009-03-30 | 2009-11-01 | 2010-12-22 | 2085104.95 | 0.000 | 0291068
5140 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | FREMONT |  | 05 | 0291069 | This project will replace two bridges, which are in poor condition with new bridges. The bridges are on Interstate 29 over County Road J24 at Exit #20, approximately 27 miles South of Council Bluffs. | Bridge Replacement | 2009-03-06 | 2009-03-30 | 2009-11-01 | 2010-12-22 | 2797514 | 0.000 | 0291069
5141 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | FREMONT |  | 05 | 0291075 | On Interstate 29 in Fremont County Iowa, from 1.5 mile north of county road J-26 north to 1.5 mile north of county road J-24, a nine-inch concrete overlay will be placed on the northbound lanes and a | Pavement Improvement | 2009-03-06 | 2009-03-30 | 2009-11-01 | 2010-12-22 | 10718757.44 | 4.200 | 0291075
5142 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MILLS |  | 05 | 0292054 | This project will replace two bridges, which are in poor condition, with new bridges. The bridges are on Interstate 29 over St. Mary’s Creek 1 mile South of Exit #42, or approximately 5 miles South of Council Bluffs. | Bridge Replacement | 2009-03-06 | 2009-03-23 | 2009-11-01 | 2011-01-31 | 1725946.67 | 0.000 | 0292054
5143 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MILLS |  | 05 | 0292065 | On Interstate 29 in Mills County, Iowa, from 3 miles north of the north junction with US Highway 34 to the Pottawattamie County line, a nine-inch concrete overlay will be placed on the northbound lane | Pavement Improvement | 2009-03-06 | 2009-03-23 | 2009-11-01 | 2011-01-31 | 11742272 | 6.000 | 0292065
5144 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONONA, HARRISON |  | 05 | 0295100 | The Iowa DOT is reconstruction of I-29 from Exit 95, which services Little Sioux, Iowa, to Exit 112, which services Onawa, Iowa. The project includes the reconstruction of the grade and Portland Ceme | Pavement Improvement | 2009-04-23 | 2009-05-04 | 2010-11-01 | 2011-11-08 | 43053354.2 | 18.100 | 0295100
5145 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONONA |  | 05 | 0296167 | This project provides for a six inch hot-mix asphalt overlay on the north and southbound lanes of Interstate 29 in Monona County, Iowa, from just north of Iowa 175 north to the Woodbury County line. This will create a smoother and stronger surface. | Pavement Improvement | 2009-06-29 | 2009-07-31 | 2010-09-01 | 2011-01-06 | 21420732.55 | 13.500 | 0296167
5146 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONONA |  | 05 | 0296182 | This project will replace a bridge, which is in poor condition with a new bridge. The bridge is on Interstate 29 southbound over Robinson Creek approximately 3.5 miles South of Exit#127 near Sloan. | Bridge Replacement | 2009-03-06 | 2009-06-22 | 2009-11-01 | 2010-08-11 | 1150196.78 | 0.000 | 0296182
5147 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | TAMA |  | 03 | 0306151 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 11.9 miles of US Highway 30 from just east of M Avenue to Iowa Highway 21 in Tama and Benton Counties. | Pavement Improvement | 2009-06-26 | 2009-07-17 | 2010-07-01 | 2010-07-21 | 4014290.57 | 11.900 | 0306151
5148 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | 0351105 | This project will replace two bridges, which are in poor condition and have inadequate clearance over Interstate 35, with new bridges. The bridges are on US 34 over Interstate 35 in Osceola. | Bridge Replacement | 2009-03-06 | 2009-04-01 | 2009-11-01 | 2011-09-13 | 1735442.16 | 0.000 | 0351105
5149 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | 0351111 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of the southbound lanes of I-35. The project begins approximately one mile north of Exit 22, which services Van Wert, Iowa, and e | Pavement Improvement | 2009-03-30 | 2009-04-07 | 2009-11-01 | 2011-01-10 | 15304219 | 9.500 | 0351111
5150 | IOWA | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | 0351112 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of the northbound lanes of I-35. The project begins approximately one mile north of Exit 22, which services Van Wert, Iowa, and e | Pavement Improvement | 2009-08-06 | 2010-04-05 | 2010-11-01 | 2011-02-01 | 8471001 | 9.500 | 0351112
5151 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | 0351116 | The Iowa DOT is replacing the Portland Cement Concrete (PCC) pavement of US Highway 34 at the interchange of I-35 and US Highway 34; Exit 33 which services Osceola, Iowa. The project is approximately | Bridge Replacement | 2009-03-06 | 2009-04-01 | 2009-11-01 | 2011-09-13 | 1626415 | 0.400 | 0351116
5152 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | WARREN |  | 04 | 0352337 | This project provides for a four inch hot-mix asphalt overlay on the north and southbound lanes of Interstate 35 in Warren County Iowa, from the Clarke County line north to 2 miles south of Iowa 92 ne | Pavement Improvement | 2009-04-13 | 2009-05-05 | 2009-11-01 | 2010-08-02 | 16990416.07 | 11.300 | 0352337
5153 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLAYTON |  | 01 | 0523031 | This project includes performing cracking and seating of the existing portland cement concrete pavement and then applying a hot-mix asphalt overlay on approximately 9.0 miles of US Highway 52 from jus | Pavement Improvement | 2009-08-17 | 2009-08-24 | 2010-09-01 | 2010-12-20 | 3596503.3 | 9.000 | 0523031
5154 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLAYTON |  | 01 | 0523032 | This project will resurface eight miles of US 52 from Guttenberg to Garnavillo with six inches of hot-mix asphalt to improve pavement condition. | Pavement Improvement | 2009-08-17 | 2009-08-24 | 2010-09-01 | 2010-12-20 | 3307754.31 | 7.500 | 0523032
5155 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 0587631 | In Bettendorf, Iowa on 23rd Street from Grant Street to Central Avenue. This project will be constructed in three stages to minimize impact on residents in the area. The street will be graded and pa | Pavement Improvement | 2009-05-29 | 2009-06-08 | 2009-12-01 | 2010-12-22 | 739272 | 0.320 | 0587631
5156 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611122 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 2009-03-06 | 2009-04-08 | 2009-11-01 | 2009-07-07 | 126319 | 0.000 | 0611122
5157 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611124 | The project is part of the grading of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-Pass. This project is for the grading of the new alignment which will be | New Construction | 2009-03-06 | 2009-04-01 | 2010-09-01 | 2011-07-21 | 8245240 | 2.200 | 0611124
5158 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611129 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 2009-03-06 | 2009-04-06 | 2009-11-01 | 2011-02-01 | 519311.63 | 0.000 | 0611129
5159 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611132 | The project is part of the grading of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-Pass. This project is for the grading of the new alignment which will be | New Construction | 2009-03-06 | 2009-04-06 | 2010-09-01 | 2011-02-01 | 4912339 | 1.700 | 0611132
5160 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611162 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 2009-03-06 | 2009-04-06 | 2009-11-01 | 2011-02-01 | 250148.28 | 0.000 | 0611162
5161 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 0611165 | The project is part of the new alignment of US Highway 61 by the Iowa DOT which is known as the Fort Madison By-pass. This project is for the construction of a new Reinforced Concrete Single Box Culv | New Construction | 2009-03-06 | 2009-03-18 | 2009-11-01 | 2009-06-02 | 295767.6 | 0.000 | 0611165
5162 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MAHASKA |  | 03 | 0633078 | This project will mill, widen, and resurface 9 miles of US 63 from New Sharon south to 210th Street North with five inches of hot-mix asphalt to improve pavement condition and safety. The widening wi | Pavement Improvement | 2009-07-17 | 2009-07-17 | 2010-07-01 | 2010-08-30 | 7302569.2 | 9.200 | 0633078
5163 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | DECATUR, CLARKE |  | 05 | 0691038 | This project will widen and resurface 31 miles of US 69 from Osceola south to Interstate 35 west of Davis City with three inches of hot-mix asphalt to improve pavement condition and safety. | Pavement Improvement | 2009-04-01 | 2009-04-21 | 2009-11-01 | 2009-10-28 | 4892118.84 | 33.000 | 0691038
5164 | IOWA | Completed | C240,C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 0694092 | This project will mill 1.5 inches and resurface with 4.5 inches of hot-mix asphalt on US 69 from Iowa 160 (Oralabor Road) north1.7 miles to First Street in Ankeny to improve pavement condition. | Pavement Improvement | 2009-10-02 | 2010-05-03 | 2010-12-01 | 2011-01-25 | 1045635.37 | 1.690 | 0694092
5165 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | PAGE, MONTGOMERY |  | 05 | 0711030 | This project will widen and resurface 17 miles of US 71 from Iowa 2 near Clarinda north to the intersection with US 34 north of Villisca with three inches of hot-mix asphalt to improve pavement condit | Pavement Improvement | 2009-03-30 | 2009-04-14 | 2009-11-01 | 2010-03-03 | 6189082 | 17.200 | 0711030
5166 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | SAC, CARROLL |  | 05 | 0715068 | This project will mill and replace two inches of the existing hot mix asphalt surface on approximately 12 miles of US 71 from just north of Carroll to the junction of Iowa 175 in Auburn to improve pavement condition. | Pavement Improvement | 2009-04-20 | 2009-05-21 | 2009-11-01 | 2009-10-12 | 1395963.34 | 10.500 | 0715068
5167 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | POLK |  | 03 | 0747603 | This multi-use path will be constructed as an alternative mode of transportation in the city of Bondurant, in Polk county. The path is along Second Street from 450 ft west of Mallard Point Circle NW to 600 ft east of Lincoln Street NE. | Transportation Enhancements | 2009-08-26 | 2009-08-26 | 2010-12-01 | 2012-01-30 | 389313.69 | 0.779 | 0747603
5168 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BOONE |  | 04 | 0750627 | This project consistes of two roadways in Boone, Iowa: South Marshall Street from Hancock Drive to Crestwood Drive and Industrial Park Road from Linn Street to Argo Street. Both projects consist of p | Pavement Improvement | 2010-01-29 | 2010-04-01 | 2010-12-01 | 2011-06-14 | 465545.99 | 0.600 | 0750627
5169 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JOHNSON | IOWA CITY | 02 | 0801600 | This project is in Iowa City, Iowa on Hawkins Drive from the University of Iowa Hospital to Carver Hawkeye Arena. The project consists of pavement rehabilitation and widening which will provide a smoother ride and improved drainage. | Pavement Improvement | 2010-02-11 | 2010-02-01 | 2010-12-01 | 2012-05-18 | 200000 | 0.400 | 0801600
5170 | IOWA | Completed | C220,C240 | Highway Infrastructure Investment Grant | IOWA | JOHNSON | IOWA CITY | 02 | 0806285 | Construction of a recreational trail in Iowa City along IA 1 (N. Dodge Street) from Act Circle NE to Northgate Dr., 0.64 miles. The project includes construction of a pedestrian bridge over Interstate 80. | Transportation Enhancements | 2010-03-19 | 2010-04-19 | 2010-12-01 | 2011-12-08 | 1252603 | 0.630 | 0806285
5171 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE |  | 05 | 0921059 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 92 over Keg Creek approximately 2.7 miles West of Treynor. | Bridge Replacement | 2009-03-20 | 2009-04-06 | 2009-11-01 | 2010-10-05 | 1139901.2 | 0.000 | 0921059
5172 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE |  | 05 | 0921060 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 92 over Middle Silver Creek approximately 0.1 miles West of Treynor. | Bridge Replacement | 2009-03-20 | 2009-04-06 | 2009-11-01 | 2010-10-05 | 1279850 | 0.000 | 0921060
5173 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | DES MOINES |  | 02 | 0977632 | This project is in Burlington, Iowa on Mt. Pleasant Street from U.S. 61 to Osborn Street. The project consists of milling the existing surface down to the concrete subbase and paving two and a half i | Pavement Improvement | 2009-09-03 | 2009-09-14 | 2010-12-01 | 2010-09-13 | 1348289.68 | 1.500 | 0977632
5174 | IOWA | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | LINN | CEDAR RAPIDS | 02 | 1001061 | IA 922/U.S. Business Route 151 (1st Avenue) and Collins Road will be widened in Cedar Rapids, Iowa. The project will start at 40th Steet Dr. SE for 1.3 miles ending at Tama Street SE. Widening will | Pavement Widening | 2009-12-16 | 2010-04-19 | 2010-12-01 |  | 2832566 | 0.273 | 1001061
5175 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | 1040602 | Camanche, Iowa on Washington Boulevard from US 67 to 22nd Avenue. The project consists of pavement rehabilitation which will provide a smoother ride and improved drainage. | Pavement Improvement | 2010-01-15 | 2010-04-28 | 2010-12-01 | 2010-11-08 | 168623 | 0.600 | 1040602
5176 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | WARREN | DES MOINES | 04 | 1105603 | Carlisle, Iowa on South 1st Street from Highway 5 to School Street. The project consists of pavement rehabilitation which will provide a smoother ride and improved drainage. Better accommodations fo | Pavement Improvement | 2010-02-24 | 2010-08-02 | 2010-12-01 | 2012-07-06 | 446670 | 0.300 | 1105603
5177 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CARROLL |  | 05 | 1125612 | Carroll, Iowa on Clark Street from extended Anthony Street to 7th Street. The project consists of milling the existing surface and resurfacing with hot-mix asphalt. The three and a half inch overlay | Pavement Improvement | 2009-12-08 | 2010-06-16 | 2010-12-01 | 2012-08-30 | 808258 | 0.700 | 1125612
5178 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | DUBUQUE |  | 01 | 1147603 | Cascade, Iowa on Tyler Street Northeast from 1st Avenue to just past Macomber Road. The project consists of milling the existing surface and resurfacing with three-inches of hot-mix asphalt providing a smoother ride and improved drainage. | Pavement Improvement | 2009-12-23 | 2010-06-04 | 2010-12-01 | 2011-11-10 | 64456 | 0.700 | 1147603
5179 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK |  | 01 | 1185641 | This project consists of replacing the pavement of multiple roadways in Cedar Falls, Iowa: State Street from East 2nd Street to East 4th Street, East 2nd Street from Main Street to State Street and Ea | Pavement Improvement | 2009-10-19 | 2010-04-01 | 2010-12-01 | 2012-08-21 | 699000 | 0.430 | 1185641
5180 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK |  | 01 | 1185642 | This two phase Trail widening and resurfacing project is located along the North and South sides of the Cedar River in the city of Cedar Falls in Blackhawk County. Phase I, North Riverside Trail , ru | Transportation Enhancements | 2009-10-15 | 2010-08-30 | 2010-12-01 | 2011-04-12 | 207500 | 1.939 | 1185642
5181 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CHEROKEE |  | 05 | 1272618 | Cherokee, Iowa on North River Road from the city limits to the River Road Bridge. The project consists of a four inch hot-mix asphalt overlay with mail box turnouts and driveway/intersection fillets which will provide for a smoother ride on the roadway. | Pavement Improvement | 2009-06-16 | 2009-07-20 | 2009-12-01 | 2009-12-07 | 180000 | 0.900 | 1272618
5182 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONONA, WOODBURY |  | 05 | 1412041 | To improve safety and winter driving conditions this project will grade four miles along Iowa 141. The project starts at the Woodbury and Monona County Line just southeast of Smithland and ends 4 mil | Pavement Improvement | 2009-03-27 | 2009-04-20 | 2009-11-01 | 2010-06-01 | 2271717 | 2.700 | 1412041
5183 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | 1415619 | Clinton County is extending 19th Avenue, approximately 1.9 miles, in the city of Clinton, Iowa, from Mill Creek Parkway east to Springdale Drive. The project is a new 4-lane Portland Cement Concrete (PCC) urban roadway with median and sidewalks. | Pavement Improvement | 2009-12-23 | 2010-05-17 | 2010-12-01 | 2012-06-12 | 815053 | 0.350 | 1415619
5184 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | BUCHANAN |  | 01 | 1503058 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Iowa 150 over Bear Creek approximately 3.3 mile South of Independence. | Bridge Replacement | 2009-03-06 | 2009-03-26 | 2009-12-01 | 2010-10-14 | 983635 | 0.000 | 1503058
5185 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | JOHNSON | IOWA CITY | 02 | 1557634 | This project is the construction of the .3 mile extension of 1st Avenue Trail along the west side of 1st Avenue from Country Club Drive north to Oakdale Blvd. in the city of Coralville in Johnson Coun | Transportation Enhancements | 2010-02-23 | 2010-05-17 | 2010-12-01 | 2012-05-29 | 382549 | 0.289 | 1557634
5186 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1631080 | This project involves improvements at the intersection of Iowa Highway 163 and NE 75th Street in Pleasant Hill in Polk County, including the addition of portland cement concrete turn lanes and signal | Safety/Traffic Management | 2009-06-16 | 2009-06-22 | 2009-12-01 | 2009-12-14 | 750000 | 0.300 | 1631080
5187 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE | OMAHA (NE)-IA | 05 | 1642657 | The city of Council Bluffs, Iowa, is reconstructing College Road from US Highway 6 southeast and west to Valley View Drive. The project will replace approximately 0.96 miles of the existing roadway w | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-12-01 | 2010-08-03 | 2163357 | 1.500 | 1642657
5188 | IOWA | Completed | C240,C230 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE | OMAHA (NE)-IA | 05 | 1642658 | The city of Council Bluffs, Iowa is repairing the transverse joints on 35th Street from Nebraska Avenue to 23rd Avenue. The project will extend the life of the existing Portland Cement Concrete (PCC) | Pavement Improvement | 2009-12-02 | 2010-04-12 | 2010-12-01 | 2010-07-09 | 478467.01 | 3.000 | 1642658
5189 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE |  | 05 | 1642659 | The new construction of a Bicycle Pedestrian Trail along the east side of 13th Street between Avenue A and Avenue H in the city of Council Bluffs in Pottawattamie county. This project will increase s | Transportation Enhancements | 2009-10-15 | 2009-10-26 | 2010-12-01 | 2011-07-25 | 200000 | 0.510 | 1642659
5190 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | POTTAWATTAMIE | OMAHA (NE)-IA | 05 | 1642660 | For the reconstruction and improvement of multipule segments of a series of bicycle and pedestrian trails connecting the city of Council Bluffs urban and rural areas in Pottawattamie county. The spe | Transportation Enhancements | 2010-02-08 | 2010-04-14 | 2010-12-01 | 2011-05-20 | 480218.38 | 8.540 | 1642660
5191 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | RINGGOLD |  | 05 | 1691038 | This project is located on US 169 in Ringgold County from the intersection with Iowa 2 in Mount Ayr north 13 miles to the Union County line. The project will recycle three inches of the existing pave | Pavement Improvement | 2009-07-10 | 2010-04-05 | 2010-07-01 | 2011-10-19 | 4382345 | 12.900 | 1691038
5192 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | UNION |  | 05 | 1692021 | This project is located on US 169 in Union County, starting in Afton and proceeding south approximately 9 miles to the Union/Ringgold county line near Shannon City. The project will recycle three inc | Pavement Improvement | 2009-07-10 | 2010-04-05 | 2010-07-01 | 2011-10-19 | 3373398 | 8.700 | 1692021
5193 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | UNION |  | 05 | 1710609 | Creston, Iowa on East Prairie Street from Cherry Street to Mulberry Street. The project consists of a two inch hot-mix asphalt overlay which will provide a smoother ride on the roadway. The Poplar St | Pavement Improvement | 2009-08-27 | 2009-09-10 | 2010-12-01 | 2009-10-29 | 62778 | 0.100 | 1710609
5194 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 1827659 | This project consists of a number of different sections on multiple roadways in Davenport, Iowa: Jersey Ridge Road, Northwest Boulevard, Division Street, Locust Street, and Rockingham Road in three lo | Pavement Improvement | 2009-06-08 | 2009-07-20 | 2009-12-01 | 2012-02-14 | 1183107 | 2.477 | 1827659
5195 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 1827660 | The City of Davenport will patch the existing pavement at the intersection of Eastern Avenue and 53rd Street and Pine Street from 53rd Street to Northwest Boulevard to improve pavement conditions. Th | Pavement Improvement | 2009-06-11 | 2009-06-17 | 2009-12-01 | 2011-05-18 | 800000 | 0.000 | 1827660
5196 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 1827661 | This project will consist of constructing a new raised median along US Highway 67 from Iowa Street to Gaines Street and along US Highway 61 from Gaines Street to Marquette Street in the City of Davenp | Pavement Improvement | 2010-01-26 | 2010-04-19 | 2010-12-01 | 2012-05-18 | 267842.79 | 0.900 | 1827661
5197 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | 1855613 | De Witt, Iowa on 11th Street from 6th Avenue to Humeston Road. The roadway will be milled and overlaid with two inches of hot-mix asphalt which will provide a smoother ride. Selected sidewalk ramps a | Pavement Improvement | 2009-06-01 | 2009-06-17 | 2009-12-01 | 2011-03-07 | 201885 | 0.490 | 1855613
5198 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945753 | Des Moines, Iowa on 6th Avenue from University Avenue to the Des Moines River Bridge. The roadway will be milled and problem areas will be patched as necessary. Traffic signal loops will be replaced | Pavement Improvement | 2009-05-27 | 2009-07-26 | 2009-12-01 | 2009-12-15 | 497395.63 | 0.900 | 1945753
5199 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | WARREN | DES MOINES | 04 | 1945754 | Des Moines, Iowa on Fleur Drive/Blue Street from Beardsley Street to Southwest 9th Street. The existing roadway surface will be milled before being overlaid with five inches of asphalt. The five inc | Pavement Improvement | 2009-05-27 | 2009-06-15 | 2009-12-01 | 2009-08-05 | 496951 | 1.200 | 1945754
5200 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945755 | Des Moines, Iowa on McKinley Avenue from Fleur Drive to South Union Street. The existing roadway surface will be milled and the traffic signal loop detectors will be replaced before being overlaid wi | Pavement Improvement | 2009-08-17 | 2009-09-29 | 2010-12-01 | 2010-08-16 | 284646.71 | 1.500 | 1945755
5201 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945756 | This project is in the city of Des Moines on Southeast 5th Street from East County Line Road to East Army Post Road. Three inches of hot-mix asphalt will be placed to improve driving quality and safety. | Pavement Improvement | 2009-08-17 | 2009-09-14 | 2010-12-01 | 2010-08-16 | 442928.36 | 1.000 | 1945756
5202 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945757 | This project is in the city of Des Moines on McKinley Avenue from South Union Street to Southeast 5th Street. The project consists of widening and placement of a 10-inch portland cement concrete surf | Pavement Improvement | 2009-08-17 | 2010-04-01 | 2010-12-01 | 2011-11-15 | 1286228 | 0.300 | 1945757
5203 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945758 | In Polk county, the city of Des Moines will improve safety, driving quality, and capacity through portland cement concrete pavement widening with hot-mix asphalt resurfacing along Army Post Road fro | Pavement Improvement | 2009-12-07 | 2010-04-05 | 2010-12-01 | 2011-10-12 | 1024411.64 | 0.200 | 1945758
5204 | IOWA | Underway | C220,C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 1945759 | The construction of the Principal Riverwalk multi-purpose trail extensions run along the West side of Des Moines River from Grand Avenue south to Walnut Street and from Court Avenue south to Vine Stre | Transportation Enhancements | 2009-10-06 | 2009-12-02 | 2010-12-01 |  | 2849000 | 0.200 | 1945759
5205 | IOWA | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | DUBUQUE | DUBUQUE (IL) | 01 | 2100646 | The city of Dubuque, Iowa, is purchasing the right-of-way for the construction of a new roadway to be known as the Southwest Arterial. The roadway will connect US highway 20 to US Highway 61. The pro | Other | 2009-09-10 | 2009-09-10 | 2010-12-01 | 2009-09-10 | 2909534 | 6.200 | 2100646
5206 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | DUBUQUE |  | 01 | 2160609 | This project replaces the bridge supports, which are in poor condition, to extend the service life of the bridge. The project also improves the aesthetics of the bridge to blend with the 1st Street i | Bridge Improvement | 2009-12-07 | 2010-03-31 | 2010-12-01 | 2011-11-10 | 156901 | 0.000 | 2160609
5207 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | BENTON |  | 03 | 2186045 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on US 218 over Pratt Creek approximately 7.5 miles West of Vinton. | Bridge Replacement | 2009-03-06 | 2009-04-20 | 2009-11-01 | 2010-10-22 | 976593.24 | 0.000 | 2186045
5208 | IOWA | Completed | C240,C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | 2290609 | In Scott county, the city of Eldridge will improve safety and mobility with hot-mix asphalt widening along 1st Street north of Trails Road and south of Fisher Court for .24 miles. | Pavement Improvement | 2009-10-13 | 2009-10-21 | 2010-12-01 | 2010-11-08 | 140000 | 3.100 | 2290609
5209 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | 2290610 | This project provides for the design and engineering of a multi-use trail that will run along the east side of County Road Y-64 from north of the city limits of Eldridge to south of the city limits of | Other | 2009-12-08 | 2009-12-08 | 2010-12-01 | 2011-09-08 | 90152.21 | 0.000 | 2290610
5210 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JEFFERSON |  | 02 | 2465617 | The city of Fairfield, Iowa is reconstructing Kirkwood Avenue from 5th Street east to 2nd Street which has deteriorated beyond maintenance repairs. The 0.23 mile long project replaces the old roadway | Pavement Improvement | 2009-06-24 | 2009-08-31 | 2009-12-01 | 2010-06-18 | 278789.13 | 0.200 | 2465617
5211 | IOWA | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | LEE |  | 02 | 2697618 | In Lee county, the city of Fort Madison will improve traffic management, safety, mobility, and carrying capacity. These enhancements will be made with structural improvements to pavement and the addit | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2010-12-01 | 2010-12-16 | 550000 | 0.010 | 2697618
5212 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 3125607 | In Polk county, the city of Grimes will improve driving quality, capacity, and safety along South James Street, beginning south of 6th Street and ending north of Urbandale approximately 2.0 miles. Th | Pavement Improvement | 2009-08-10 | 2009-08-24 | 2010-12-01 | 2011-01-31 | 1000000 | 2.200 | 3125607
5213 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | POWESHIEK |  | 03 | 3127622 | In Poweshiek county, the city of Grinnell will improve driving quality and safety through hot-mix asphalt resurfacing with milling along two sections of road; one along 8th Avenue from West Street (I | Pavement Improvement | 2009-07-06 | 2009-09-10 | 2009-12-01 | 2010-06-28 | 196400 | 1.000 | 3127622
5214 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | IDA |  | 05 | 3650603 | In Ida county, the city of Ida Grove will improve driving quality and safety by patching Moorehead Avenue, from 2nd Street to Ohio Street (Iowa 59), with portland cement concrete before placing a hot-mix asphalt overlay. | Pavement Improvement | 2009-06-01 | 2009-09-08 | 2009-12-01 | 2010-02-03 | 200000 | 0.000 | 3650603
5215 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WARREN |  | 04 | 3680612 | The City of Indianola will improve approximately ¾ of a mile of North Y Street between Iowa Highway 92 and West Euclid Avenue by replacing the existing granular surface with a new concrete pavement. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2009-12-01 | 2009-10-26 | 494331 | 0.730 | 3680612
5216 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JOHNSON | IOWA CITY | 02 | 3715643 | In Johnson county, the city of Iowa City will improve driving quality and safety through hot-mix asphalt resurfacing with milling along South Riverside Drive (Old Highway 218) beginning south of High | Pavement Improvement | 2009-08-24 | 2009-09-01 | 2010-12-01 | 2010-09-16 | 600000 | 1.600 | 3715643
5217 | IOWA | Completed | C240,C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 3827611 | This project will involve widening of the existing pavement on approximately 0.8 miles of Northwest 86th Street from Chamberry Boulevard to Northwest 62nd Avenue in the City of Johnston. The new conc | Pavement Improvement | 2010-01-26 | 2010-04-01 | 2010-12-01 | 2011-11-22 | 1144528 | 0.800 | 3827611
5218 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARION |  | 03 | 4040606 | In Marion county, the city of Knoxville will improve driving quality and safety through hot-mix asphalt resurfacing with milling along two sections of road. One along South Roche Street from Robinson | Pavement Improvement | 2009-06-11 | 2009-10-05 | 2009-12-01 | 2009-12-14 | 296950 | 0.688 | 4040606
5219 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | 4252601 | This project provides preliminary and final design engineering for the Mississippi River Trail (MRT) that will run along U.S. Highway 67 from the Eastern most city limits of Bettendorf to the Northern | Other | 2009-12-08 | 2009-12-08 | 2010-12-01 | 2010-08-10 | 214190 | 0.000 | 4252601
5220 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | DELAWARE |  | 01 | 4682621 | In Delaware county, the city of Manchester will improve driving quality and safety through hot-mix asphalt resurfacing along East Main Street from Brewer Street to Bailey Drive. | Pavement Improvement | 2009-11-03 | 2010-05-05 | 2010-12-01 | 2010-07-23 | 210309 | 0.370 | 4682621
5221 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JACKSON |  | 01 | 4742615 | In Jackson county, the city of Maquoketa will enhance safety and drainage with improvements to portland cement concrete curb and gutter along North Main Street from Grove Street to Quarry Street. Imp | Pavement Improvement | 2009-05-29 | 2009-07-22 | 2009-12-01 | 2010-08-13 | 244514 | 0.400 | 4742615
5222 | IOWA | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775620 | Marion, Iowa intends to improve North 35th Street from Tower Terrace Road to Indian Creek Road. Improvements will include patching of the existing roadway pavement and grading and construction of bicycle/pedestrian facilities. | New Construction | 2010-01-27 | 2010-03-22 | 2010-12-01 |  | 1274994 | 0.686 | 4775620
5223 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775621 | Marion, Iowa intends to reconstruct North 10th Street from Indian Creek Road to Tower Terrace Road. Reconstruction will include intersection modifications, pavement widening, culvert replacement, tra | Pavement Improvement | 2010-01-27 | 2010-04-05 | 2010-12-01 | 2012-07-23 | 1228500 | 0.700 | 4775621
5224 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775622 | Marion, Iowa will improve the Central Business District between North 10th Street from 7th Avenue to 8th Avenue. Construction includes updating traffic signals and lighting to improve safety and provide for a better flow of traffic. | Safety/Traffic Management | 2010-02-25 | 2010-06-07 | 2010-12-01 | 2012-06-22 | 280000 | 0.660 | 4775622
5225 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775623 | Marion, Iowa intends to improve the intersection of Armar Drive and Highway 100. Intersection modifications will include traffic signal upgrades and concrete paving/widening. | Safety/Traffic Management | 2010-02-25 | 2010-07-07 | 2010-12-01 | 2011-11-10 | 450000 | 0.000 | 4775623
5226 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | 4775624 | Marion, Iowa intends to improve the safety at the intersection of South 22nd Street and Highway 100 by installing new traffic signals, adding left turn lanes and extending existing left turn lanes. | Pavement Improvement | 2010-02-25 | 2010-07-06 | 2010-12-01 | 2012-06-22 | 371360 | 0.000 | 4775624
5227 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARSHALL |  | 04 | 4797612 | In Marshall county, the city of Marshalltown will improve driving quality and safety by resurfacing along Iowa Avenue West, for 70 feet west of Parker Avenue to 648 feet east of south 6th street, with hot-mix asphalt. | Pavement Improvement | 2009-09-09 | 2009-09-24 | 2010-12-01 | 2010-01-11 | 449376.89 | 3.000 | 4797612
5228 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MUSCATINE |  | 02 | 5330619 | In Muscatine county, the city of Muscatine will improve road safety, drainage, capacity and driving quality. Improvements will be obtained through replacement of portland cement concrete pavement, ce | Pavement Improvement | 2009-06-18 | 2009-08-10 | 2009-12-01 | 2010-08-05 | 733544 | 0.600 | 5330619
5229 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY |  | 04 | 5405607 | In Story county, the city of Nevada will improve the driving surface, and extend the service life of the pavement along W 4th Street, at U.S. Highway 30 heading north 1.0 mile to 1st Street, by resurfacing the facility with hot-mix asphalt. | Pavement Improvement | 2009-05-27 | 2009-08-10 | 2009-12-01 | 2009-11-12 | 245333 | 0.980 | 5405607
5230 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JASPER |  | 03 | 5482611 | This project is on East 31st Street North and North 19th Avenue East from 1st Avenue east to East 19th Street in Newton. The project will improve the driving surface and extend the service life of th | Pavement Improvement | 2009-09-21 | 2009-09-23 | 2010-06-06 | 2010-05-03 | 620472 | 1.910 | 5482611
5231 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | 5557614 | This project will improve traffic flow and safety on Iowa 965 in North Liberty by constructing traffic signals at its intersection with Cherry Street. | Safety/Traffic Management | 2010-02-24 | 2010-04-27 | 2010-12-01 | 2011-10-17 | 285000 | 0.000 | 5557614
5232 | IOWA | Completed | C240,C230 | Highway Infrastructure Investment Grant | IOWA | WARREN | DES MOINES | 04 | 5587602 | This project will improve access to new development by converting an existing three-way “T” intersection of Colonial Parkway and Iowa Highway 28 within the City of Norwalk into a four-way intersection | Pavement Improvement | 2010-03-15 | 2010-05-11 | 2010-12-01 | 2011-10-11 | 300000 | 0.300 | 5587602
5233 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WAPELLO |  | 02 | 5825637 | This project will increase capacity, improve safety and mobility along Lake Road in the city of Ottumwa in Wapello County. The project begins at the city limits along Lake Road and heads north for 1.5 miles to Mary Street. | Pavement Improvement | 2009-06-15 | 2009-10-05 | 2009-12-01 | 2010-04-08 | 632498 | 1.500 | 5825637
5234 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WAPELLO |  | 02 | 5825638 | In Wapello county, the city of Ottumwa will conduct structural enhancements including hot-mix asphalt resurfacing and portland cement concrete patching along .74 miles of roadway on Madison Avenue f | Pavement Improvement | 2009-06-15 | 2009-10-05 | 2009-12-01 | 2010-04-08 | 361255.93 | 1.000 | 5825638
5235 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARION |  | 03 | 5947613 | In Marion county, the city of Pella will replace deteriorating pavement on Independence Street heading south along Oskaloosa Street to southeast 9th Street. Smoother longer lasting pavement will be provided to enhance driving quality and safety. | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2010-12-01 | 2011-11-16 | 323163 | 1.000 | 5947613
5236 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | DALLAS |  | 04 | 5970610 | This project will be rehabilitating the pavement along three roadways within the City of Perry totaling approximately 0.96 miles: Park Street from 1st Avenue to the east edge of Violet Hill Cemetery, | Pavement Improvement | 2009-05-21 | 2009-06-22 | 2009-12-01 | 2009-11-04 | 269251.35 | 0.900 | 5970610
5237 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | 6247601 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 0.75 miles of Lost Grove Road in the City of Princeton from US Highway 67 west 3960 feet. | Pavement Improvement | 2010-03-29 | 2010-08-04 | 2010-12-01 | 2011-09-06 | 249820 | 0.800 | 6247601
5238 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK | WATERLOO | 01 | 6342600 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 1.1 miles of County Route D-22/ Dubuque Road from the west to the east city limits of the City of Raymond. | Pavement Improvement | 2009-07-10 | 2009-08-17 | 2009-12-01 | 2010-08-27 | 711914.81 | 1.131 | 6342600
5239 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY |  | 05 | 6890606 | The City of Sergeant Bluff will reconstruct approximately 0.3 miles of South Lewis Boulevard from 1st Street to Topaz Drive. The new concrete driving surface will improve ride quality and reduce maintenance costs. | Pavement Improvement | 2009-06-08 | 2009-08-03 | 2009-12-01 | 2010-08-19 | 537483.46 | 0.290 | 6890606
5240 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SIOUX | SIOUX CITY (NE-SD) | 05 | 7055621 | This project will be rehabilitating the pavement along three roadways within the City of Sioux Center totaling 0.65 miles: 2nd Avenue from 4th Street SW to 3rd Street NW, 3rd Street NE from 1st Avenue | Pavement Improvement | 2009-05-18 | 2009-09-10 | 2009-12-01 | 2010-03-17 | 370399 | 0.650 | 7055621
5241 | IOWA | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY | SIOUX CITY (NE-SD) | 05 | 7057662 | The City of Sioux City will reconstruct and widen approximately ½ mile of South Martha Street from Stone Avenue to Gordon Drive. The new concrete driving surface will improve ride quality and capacity. | Pavement Improvement | 2009-06-25 | 2009-06-12 | 2009-12-01 |  | 792853 | 0.470 | 7057662
5242 | IOWA | Underway | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY | SIOUX CITY (NE-SD) | 05 | 7057663 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on five sections of roadway within the City of Sioux City totaling 12.5 blocks: 3rd Street from Water Street | Pavement Improvement | 2009-06-09 | 2009-06-29 | 2009-12-01 |  | 495533 | 0.880 | 7057663
5243 | IOWA | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | CLAY |  | 05 | 7170619 | The city of Spencer Iowa is reconstructing West 11th Street from Grand Avenue west to 7th Avenue West, approximately 0.5 miles. The existing Portland Cement Concrete (PCC) roadway will be removed and | Pavement Improvement | 2010-03-08 | 2010-04-05 | 2010-12-01 | 2010-11-29 | 217026 | 0.500 | 7170619
5244 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | 7855606 | This project will replace existing deteriorated pavement with new full-depth portland cement concrete pavement patches on Sunset Street from Koser Avenue to Highland Drive and Melrose Avenue from Sunset Street to George Street in University Heights. | Pavement Improvement | 2010-01-29 | 2010-06-09 | 2010-12-01 | 2010-12-16 | 49481.41 | 0.000 | 7855606
5245 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 7875632 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on approximately 1 mile of Iowa 100th Street from Douglas Avenue to Hickman Road in Urbandale. | Pavement Improvement | 2010-01-21 | 2010-07-28 | 2010-12-01 | 2011-01-31 | 1200000 | 0.990 | 7875632
5246 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK | WATERLOO | 01 | 8155708 | This project will provide an improved driving surface by applying a hot-mix asphalt overlay on four sections of roadway within the City of Waterloo totalling 1.93 miles: Broadway Street from Donald St | Pavement Improvement | 2009-05-22 | 2009-07-20 | 2009-12-01 | 2009-12-28 | 1431482.09 | 1.900 | 8155708
5247 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK | WATERLOO | 01 | 8155709 | This project provides for construction of a bicycle and pedestrian trail on the south bank of the Cedar River from West 6th Street to West 18th Street in the city of Waterloo in Blackhawk County. Thi | Transportation Enhancements | 2010-01-26 | 2010-06-01 | 2010-12-01 | 2012-02-23 | 484866.72 | 1.069 | 8155709
5248 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BREMER |  | 01 | 8190623 | This project will upgrade traffic signals on Highway 3 (Bremer Avenue) in Waverly, Iowa at the following intersections; 15th Street West, 10th Street West, 6th Street West, 4th Street West, 1st Street | Safety/Traffic Management | 2009-12-23 | 2010-04-12 | 2010-12-01 | 2011-02-07 | 394997.5 | 0.000 | 8190623
5249 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | 8477610 | This project will improve the driving surface by milling the existing surface and then applying a hot-mix asphalt overlay on approximately 1.6 miles of 73rd Street from Center Street to Hickman Road in the city of Windsor Heights in Polk County. | Pavement Improvement | 2009-06-16 | 2009-07-08 | 2010-12-01 | 2009-10-30 | 538000 | 1.600 | 8477610
5250 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | ADAIR |  | 05 | C001071 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on 200th street over the West Fork of the Middle Nodaway River 0.5 miles East of Bridgewater. | Bridge Replacement | 2009-06-17 | 2009-06-30 | 2009-12-01 | 2010-04-13 | 312195 | 0.100 | C001071
5251 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | ADAMS |  | 05 | C002054 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2.8 miles of County Route N26 from the town of Nodaway to US highway 34 in Adams County. | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-12-01 | 2009-09-08 | 217179 | 2.800 | C002054
5252 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | APPANOOSE |  | 02 | C004077 | This project consists of applying a hot mix asphalt overlay at two locations in Appanoose County. One location is approximately 2.8 miles on County Route T14 from Iowa Highway 2 to just north of the | Pavement Improvement | 2009-07-08 | 2009-09-21 | 2009-12-01 | 2009-12-02 | 581000 | 3.300 | C004077
5253 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | APPANOOSE |  | 02 | C004078 | This project provides for construction of a box culvert extension over Ham Creek on the south side of county road J18 east of Honey Creek Resort State Park, north of Rathbun Lake in Appanoose county. | Transportation Enhancements | 2009-07-08 | 2009-07-20 | 2009-06-01 | 2010-08-30 | 150000 | 0.260 | C004078
5254 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | APPANOOSE |  | 02 | C004079 | For the new construction of a 7 mile multi-use trail on the northern border of Rathbun Lake in Appanoose County. The trail will serve as an alternative mode of transportation from county road J18 to Prairie Ridge campground. | Transportation Enhancements | 2009-08-31 | 2009-08-31 | 2010-12-01 | 2012-01-30 | 1188552.5 | 8.294 | C004079
5255 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | APPANOOSE |  | 02 | C004086 | This project will improve the Lake Rathbun Trail System in Appanoose County by adding 8.29 miles of granular surface trail as well as benches and a latrine. The proposed improvements will run from be | Transportation Enhancements | 2010-10-10 | 2011-07-05 | 2011-12-01 | 2012-01-30 | 431595 |  | C004086
5256 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | BENTON |  | 03 | C006078 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 5.7 miles of County Route | Pavement Improvement | 2009-08-24 | 2009-09-21 | 2010-12-01 | 2011-04-29 | 888727 | 5.500 | C006078
5257 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BLACK HAWK |  | 01 | C007116 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 2.8 miles of County Route | Pavement Improvement | 2009-06-11 | 2009-09-28 | 2009-12-01 | 2010-01-04 | 778935.38 | 3.500 | C007116
5258 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | BOONE |  | 04 | C008053 | The project is located on Boone County Route R-21 which is also known as Nature Road. Boone County is placing Hot Mix Asphalt Resurfacing over Cold In-Place Recycling of the existing asphalt surface | Pavement Improvement | 2009-05-13 | 2009-08-31 | 2009-12-01 | 2009-10-14 | 558263 | 6.500 | C008053
5259 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BREMER |  | 01 | C009061 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 3.6 miles of County Route | Pavement Improvement | 2009-07-20 | 2009-09-14 | 2009-12-01 | 2009-11-24 | 650000 | 3.500 | C009061
5260 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | BUCHANAN |  | 01 | C010067 | This project will improve the driving surface and extend the life of the pavement by applying an unbonded concrete overlay on approximately 6.8 miles of County Route D22 from County Route V65 to Golf Course Boulevard in Buchanan County. | Pavement Improvement | 2009-05-13 | 2009-05-26 | 2009-12-01 | 2010-09-09 | 1730000 | 7.000 | C010067
5261 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | BUENA VISTA |  | 05 | C011067 | This project will improve the driving surface and extend the life of the pavement by applying an unbonded concrete overlay on approximately 1.6 miles of 600th Street (East Milwaukee Road) from Geising | Pavement Improvement | 2009-05-14 | 2009-05-26 | 2009-12-01 | 2010-09-09 | 706026.08 | 1.500 | C011067
5262 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CALHOUN |  | 04 | C013079 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 12 miles of County Route D15 from the Sac/Calhoun County line to Iowa Highway 4 in Calhoun County. | Pavement Improvement | 2009-08-24 | 2009-09-21 | 2010-12-01 | 2010-08-23 | 2000000 | 12.000 | C013079
5263 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CARROLL |  | 05 | C014124 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 7 miles of County Route N41 from US Highway 30 to Count | Pavement Improvement | 2009-05-20 | 2009-07-06 | 2009-12-01 | 2009-10-09 | 1000000 | 9.900 | C014124
5264 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | CARROLL |  | 05 | C014126 | For the reconstruction of a 13.5 mile segment of the Sauk Rail Trail from the city of Maple River Junction, which is just north of Highway 30, in Carroll County through the city of Breda towards the c | Transportation Enhancements | 2009-09-24 | 2010-04-13 | 2010-06-12 | 2011-05-17 | 1000000 | 12.900 | C014126
5265 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CASS |  | 05 | C015050 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 6.4 miles of County Route G35 from County Route N28 to Iowa Highway 148 in Cass County. | Pavement Improvement | 2009-07-02 | 2009-07-06 | 2009-12-01 | 2009-10-20 | 1500000 | 6.500 | C015050
5266 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CEDAR |  | 02 | C016078 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 4.1 miles of County Route | Pavement Improvement | 2009-08-17 | 2010-06-18 | 2010-12-01 | 2010-11-29 | 773396 | 4.500 | C016078
5267 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CERRO GORDO |  | 04 | C017059 | This project includes performing cracking and seating of the existing concrete pavement and then doing a hot mix asphalt overlay. The work will be done on County Route B30 from the city of Mason City | Pavement Improvement | 2009-05-28 | 2009-09-08 | 2009-12-01 | 2009-10-19 | 1009770.74 | 4.500 | C017059
5268 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CHEROKEE |  | 05 | C018054 | This project will improve the driving surface and extend the life of the pavement by milling the existing surface and then applying a hot mix asphalt overlay on approximately 3 miles of County Route M | Pavement Improvement | 2009-05-27 | 2009-09-02 | 2009-12-01 | 2010-06-28 | 500000 | 3.000 | C018054
5269 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | CLARKE |  | 05 | C020071 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2 miles of County Route H45 at three separate locations between I35 and County Route R25 in Clarke County. | Pavement Improvement | 2009-07-10 | 2009-09-08 | 2009-12-01 | 2010-07-19 | 748000 | 1.000 | C020071
5270 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | CLINTON |  | 01 | C023082 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay with cold-in-place recycling on approximately 10.7 miles of County Route | Pavement Improvement | 2009-06-03 | 2009-08-03 | 2009-12-01 | 2010-10-21 | 524593 | 6.000 | C023082
5271 | IOWA | Completed | C250,C200 | Highway Infrastructure Investment Grant | IOWA | CRAWFORD |  | 05 | C024088 | The project is located on Crawford County Route (CCR) M55 (330th Street) and CCR E53 (S Avenue). Crawford County is replacing the existing Portland Cement Concrete roadway surface with a new Portland | Pavement Improvement | 2009-05-14 | 2009-06-22 | 2009-12-01 | 2010-03-23 | 1391865.1 | 6.800 | C024088
5272 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | DALLAS |  | 04 | C025075 | The project is located on Dallas County Route (DCR) R16 (R Avenue). Dallas County is replacing the existing Portland Cement Concrete roadway surface with a new Portland Cement Concrete roadway surfac | Pavement Improvement | 2009-06-03 | 2009-07-08 | 2009-12-01 | 2009-10-26 | 726674 | 4.200 | C025075
5273 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | DECATUR |  | 05 | C027042 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 1.9 miles of County Route J14 from Interstate 35 to US Highway 69 in Decatur County. | Pavement Improvement | 2009-07-01 | 2009-09-08 | 2009-12-01 | 2009-09-28 | 368000 | 2.000 | C027042
5274 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | DELAWARE |  | 01 | C028067 | This project will provide an improved driving surface, extension of the life of the pavement, and improved site drainage by applying a hot mix asphalt overlay with cold-in-place recycling and the repl | Pavement Improvement | 2009-05-21 | 2009-07-27 | 2009-12-01 | 2010-07-22 | 525953 | 3.000 | C028067
5275 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | DICKINSON |  | 05 | C030037 | This project will improve the driving surface and enhance safety by applying an unbonded concrete overlay and doing necessary shoulder work on approximately 4.2 miles of County Route M27 from 190th Street to Iowa Highway 9 in Dickinson County. | Pavement Improvement | 2009-06-11 | 2009-07-16 | 2009-12-01 | 2010-06-07 | 1417702 | 4.200 | C030037
5276 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | DICKINSON |  | 05 | C030039 | This project provides for resurfacing and renovation of various segments of Spine and Poyzer Trails in the cities of Milford, Arnolds Park, Okoboji, Spirit Lake, and Orleans in Dickinson County. The | Transportation Enhancements | 2010-01-11 | 2010-05-04 | 2010-12-01 | 2011-03-24 | 186365 | 8.540 | C030039
5277 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | DUBUQUE |  | 01 | C031061 | This project involves replacement of four bridges along Farley Road from Aitchison Road to the City of Cascade. | Bridge Replacement | 2010-02-18 | 2010-03-22 | 2010-12-01 | 2012-07-23 | 506011 | 0.540 | C031061
5278 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | EMMET |  | 04 | C032038 | This project will provide an improved driving surface and extend the life of the pavement by applying a hot mix asphalt overlay on approximately 2.9 miles of County Route N22 from County Route A17 to the Iowa/Minnesota state line in Emmet County. | Pavement Improvement | 2009-05-21 | 2009-07-17 | 2009-12-01 | 2009-10-12 | 470749.42 | 2.900 | C032038
5279 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | EMMET |  | 04 | C032039 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2 miles of Emmet County Route A22 (170th Ave.) from the Dickinson/Emmet County line east to the Es | Pavement Improvement | 2009-05-21 | 2009-07-17 | 2009-12-01 | 2009-10-12 | 597840 | 3.300 | C032039
5280 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | FAYETTE |  | 01 | C033106 | This project consists of applying a concrete overlay on Fayette County Route V68 (W Ave.) from U.S. Highway 18 northerly to 3rd St. in the city of Waucoma. The project also includes a concrete overla | Pavement Improvement | 2009-05-21 | 2009-05-28 | 2009-12-01 | 2010-11-12 | 1920000 | 8.000 | C033106
5281 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | FLOYD |  | 04 | C034077 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 7.5 miles of Floyd County Route B60 (270th St.) from the Cerro Gordo/Floyd County line east to Indigo Ave./West St. in the city of Marble Rock. | Pavement Improvement | 2009-05-15 | 2009-06-30 | 2009-12-01 | 2009-08-10 | 1268424.36 | 7.400 | C034077
5282 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | FRANKLIN |  | 04 | C035057 | This project will improve safety along approximately ¾ mile of Franklin County Route S56 (Timber Ave.) from Iowa Highway 3 north to 155th St. on the south limits of the city of Hansell. The existing | Pavement Improvement | 2009-05-20 | 2009-09-21 | 2009-12-01 | 2009-12-28 | 210459.95 | 1.000 | C035057
5283 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | GRUNDY |  | 03 | C038085 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2 miles of Grundy County Route T19 (F Ave.) from 1st Street in the city of Wellsburg north, past U | Pavement Improvement | 2009-05-21 | 2009-06-01 | 2009-12-01 | 2010-08-10 | 502117.32 | 2.500 | C038085
5284 | IOWA | Completed | C220,C240 | Highway Infrastructure Investment Grant | IOWA | GRUNDY |  | 03 | C038086 | This project provides for construction of the East Lake Trail on the east side of Grundy County Lake located SW of interchange U.S. Highway 20 & County Road T-55 (Union Ave.) which is just SW of the c | Transportation Enhancements | 2009-12-02 | 2009-12-02 | 2010-12-01 | 2012-03-06 | 410875.01 | 0.780 | C038086
5285 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | GUTHRIE |  | 05 | C039052 | This project provides for resurfacing and construction of 5.7 miles of the Raccoon River Valley Trail from Clay Street in the city of Panora to the Trailhead in the city of Yale both in Guthrie county | Transportation Enhancements | 2009-06-04 | 2009-06-04 | 2010-12-01 | 2012-03-03 | 782454.72 | 5.340 | C039052
5286 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HAMILTON |  | 04 | C040052 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road R27 over the Boone River 5 miles North of Webster City. | Bridge Replacement | 2009-05-11 | 2009-05-26 | 2009-12-01 | 2010-04-06 | 600000 | 0.100 | C040052
5287 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HANCOCK |  | 04 | C041096 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 3.4 miles of Hancock County Route B20 (285th St./Quail Ave./290th St.) from Hancock County Route R | Pavement Improvement | 2009-05-28 | 2009-07-30 | 2009-12-01 | 2009-10-06 | 356466.18 | 3.500 | C041096
5288 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HARDIN |  | 04 | C042064 | This project will provide an improved driving surface and reduce future roadway maintenance on Hardin County Route S56 from Iowa Highway 175 northerly to Hardin County Route D35 in Steamboat Rock. Th | Pavement Improvement | 2009-05-21 | 2009-06-01 | 2009-12-01 | 2010-08-10 | 699400 | 4.500 | C042064
5289 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HARRISON |  | 05 | C043068 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Harrison County Route F32 from U.S. Highway 30 in Woodbine east 4.6 miles to Harrison County Route L66 (Toledo Ave.). | Pavement Improvement | 2010-01-08 | 2010-05-10 | 2010-12-01 | 2011-02-10 | 1020000 | 4.100 | C043068
5290 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HENRY |  | 02 | C044064 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5.8 miles of Henry County Route J20 (Salem Road) from Ash Avenue in the city of Hillsboro easterly | Pavement Improvement | 2009-06-08 | 2009-09-07 | 2009-12-01 | 2009-10-06 | 1138000 | 5.000 | C044064
5291 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | HOWARD |  | 04 | C045059 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5 miles of Howard County Route V26 (Jade Ave.) from Iowa Highway 9 north to Howard County Route A2 | Pavement Improvement | 2009-05-21 | 2009-05-26 | 2009-12-01 | 2009-07-01 | 960000 | 5.000 | C045059
5292 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | IDA |  | 05 | C047045 | The project is located on Ida County Route (ICR) M15 (240th Street). Ida County is replacing the existing Portland Cement Concrete (PCC) roadway surface with a new PCC roadway surface which includes | Pavement Improvement | 2009-07-02 | 2009-08-03 | 2009-12-01 | 2010-03-31 | 500000 | 1.470 | C047045
5293 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | IOWA |  | 03 | C048056 | This project will provide an improved driving surface and reduce future roadway maintenance on Iowa County Route F67 (325th St.) from Iowa County Route V52 (H Ave.) easterly to North Knoll Ridge St. i | Pavement Improvement | 2009-06-16 | 2009-06-18 | 2009-12-01 | 2010-09-16 | 773396 | 6.500 | C048056
5294 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JACKSON |  | 01 | C049046 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 1.3 miles of Jackson County Route Y53 (Hurstville Road) from Pershing Road in the city of Maquoke | Pavement Improvement | 2009-07-20 | 2009-08-06 | 2009-12-01 | 2010-02-05 | 167439 | 2.600 | C049046
5295 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JACKSON |  | 01 | C049047 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 2.6 miles of Jackson County Route D55 (300th St.) from ¼ mile east of U.S. Highway 61 east to 400 | Pavement Improvement | 2009-07-20 | 2009-08-06 | 2009-12-01 | 2010-02-05 | 400000 | 2.500 | C049047
5296 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JASPER |  | 03 | C050087 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 5.2 miles of Jasper County Route T38 from Mahaska/Jasper County line north to the Skunk River Brid | Pavement Improvement | 2009-07-02 | 2009-09-14 | 2009-12-01 | 2011-02-21 | 850142 | 5.100 | C050087
5297 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JEFFERSON |  | 02 | C051043 | This project will replace a narrow bridge with a new bridge. The bridge is on County Road V64/Douds Road over Lick Creek approximately 3 miles South of Libertyville. | Bridge Replacement | 2009-12-11 | 2010-04-12 | 2010-12-01 | 2010-10-26 | 347681 | 0.100 | C051043
5298 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | C052090 | This project will reconstruct approximately 0.8 miles of Johnson County Route F12 (120th St.) and 1.1 miles of Iowa Highway 965 near the city of Swisher. County Route F12 will be rebuilt from 925 fee | Pavement Improvement | 2009-12-29 | 2010-04-19 | 2010-12-01 | 2012-08-28 | 556302 | 0.600 | C052090
5299 | IOWA | Underway | C240 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | C052093 | This project consists of applying a concrete overlay on Johnson County Route W64 (Oak Crest Hill Road) from the Washington/Johnson County line northerly to the south city limit of Hills (approximately | Pavement Improvement | 2009-12-14 | 2010-05-04 | 2010-12-01 |  | 556302 | 0.800 | C052093
5300 | IOWA | Completed | C220 | Highway Infrastructure Investment Grant | IOWA | JOHNSON |  | 02 | C052094 | This project provides for construction of the 1.5 mile extension of Dubuque Street Trail along Dubuque Street (County Road W-66) from West Overlook Road northwest to 275th Street just southeast of th | Transportation Enhancements | 2009-08-17 | 2009-09-07 | 2009-12-01 | 2012-01-24 | 252000 | 1.300 | C052094
5301 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | JONES |  | 01 | C053066 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Jones County Route E34 (Fairview Rd.) from Quaker Ln. (just east of the ci | Pavement Improvement | 2009-10-16 | 2010-04-08 | 2010-12-01 | 2012-08-13 | 863137 | 2.800 | C053066
5302 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | KEOKUK |  | 03 | C054082 | This project will improve drainage along and under Keokuk County Route V5G by replacing multiple pipe culverts under the 2.8 miles of roadway from Iowa Highway 149 to Iowa Highway 78 in the city of Ollie. | Pavement Improvement | 2009-08-24 | 2010-05-06 | 2010-12-01 | 2010-12-03 | 380278 | 11.200 | C054082
5303 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | KOSSUTH |  | 04 | C055128 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 10 miles of Kossuth County Route R14 (240th Ave.) from U.S. Highway 18 (near the city of Wesley) n | Pavement Improvement | 2009-07-28 | 2009-08-03 | 2009-12-01 | 2009-10-07 | 1428688 | 11.000 | C055128
5304 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | LINN |  | 02 | C057102 | This project will provide an improved driving surface and reduce future roadway maintenance by applying a concrete overlay to Linn County Route W45 (Troy Mills Rd.) from just north of Linn County Rout | Pavement Improvement | 2009-05-20 | 2009-08-24 | 2009-12-01 | 2010-04-07 | 895052.04 | 2.700 | C057102
5305 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | LOUISA |  | 02 | C058039 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 12.6 miles of Louisa County Route X99 from just east of the Iowa River Bridge (near the city of Wa | Pavement Improvement | 2009-07-02 | 2009-09-14 | 2009-12-01 | 2009-10-13 | 1300000 | 12.500 | C058039
5306 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | LUCAS |  | 03 | C059045 | This project will provide an improved driving surface by applying an asphalt overlay on approximately 0.9 miles of Albia Road (475th Lane) in the city of Chariton from S. 5th Street southeasterly to U.S. Highway 34. | Pavement Improvement | 2009-10-21 | 2009-10-27 | 2009-12-01 | 2010-05-25 | 399000 | 1.000 | C059045
5307 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MADISON |  | 04 | C061083 | This project will provide an improved driving surface by applying an asphalt overlay to various locations on Madison County Route G4R (Cumming Road) between Quail Ridge Trail (approximately 6 miles no | Pavement Improvement | 2009-06-03 | 2009-09-21 | 2009-12-01 | 2011-05-18 | 569170 | 3.500 | C061083
5308 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MAHASKA |  | 03 | C062066 | This project will replace the existing deteriorating pavement with new concrete pavement on approximately 2.2 miles of Osburn Avenue from Iowa Highway 23 to Iowa Highway 92 in Mahaska County. The new | Pavement Improvement | 2009-06-02 | 2009-08-31 | 2009-12-01 | 2010-02-03 | 852647 | 2.100 | C062066
5309 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARION |  | 03 | C063096 | This project will provide an improved driving surface by applying an asphalt overlay on Marion County Route G71 from Iowa Highway 5 southeasterly to the approximately ¼ mile north of 2nd Street in the | Pavement Improvement | 2009-05-01 | 2009-05-07 | 2009-12-01 | 2009-06-17 | 314043 | 5.000 | C063096
5310 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARION |  | 03 | C063097 | This project will provide an improved driving surface by applying an asphalt overlay on Marion County Route G76 from 1.5 miles east of Marion County Route S45 (southeast of the city of Melcher-Dallas) | Pavement Improvement | 2009-05-01 | 2009-05-08 | 2009-12-01 | 2009-06-17 | 311651 | 1.500 | C063097
5311 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MARSHALL |  | 04 | C064109 | Marshall County will resurface 3.5 miles of County Road E-67 with new asphalt between Underwood and Yates Avenue west of the City of Gilman. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2009-05-14 | 2009-05-25 | 2009-12-01 | 2009-08-03 | 781815.52 | 3.500 | C064109
5312 | IOWA | Completed | C220,C240 | Highway Infrastructure Investment Grant | IOWA | MILLS |  | 05 | C065074 | This project provides for reconstruction of two segments of the Wabash Trace Nature Trail through and near the cities of Silver City and Malvern both in Mills County. The first segment begins southea | Transportation Enhancements | 2010-03-09 | 2010-05-24 | 2010-12-01 | 2011-07-25 | 538338.52 | 2.770 | C065074
5313 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MITCHELL |  | 04 | C066039 | Mitchell County will overlay 2 miles of County Road A-23 with new concrete between Walnut Avenue and Addison Avenue northeast of the City of McIntire. This project will improve driving quality and significantly extend the life of the road. | Pavement Improvement | 2009-05-21 | 2009-09-14 | 2009-12-01 | 2009-12-28 | 400000 | 2.000 | C066039
5314 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MONONA |  | 05 | C067062 | The project is located on Monona County Road (MCR) E60. Monona County is improving the existing gravel roadway with a drainage system and new gravel surface. The project is located approximately 3.6 | Pavement Improvement | 2009-05-26 | 2009-07-06 | 2009-12-01 | 2010-03-17 | 456691.22 | 1.700 | C067062
5315 | IOWA | Completed | C250 | Highway Infrastructure Investment Grant | IOWA | MONROE |  | 03 | C068063 | Monroe County will widen and resurface 1.6 miles of County Road H-35 with new asphalt south of the City of Albia. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2009-06-16 | 2009-09-14 | 2009-12-01 | 2010-06-18 | 624000 | 1.600 | C068063
5316 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | MONTGOMERY |  | 05 | C069039 | Montgomery County will overlay 1.7 miles of County Road H-54 with new concrete east of the City of Colburg to Iowa Highway 48. This project will improve driving quality and significantly extend the life of the road. | Pavement Improvement | 2009-11-23 | 2010-07-12 | 2010-12-01 | 2011-03-09 | 405610 | 2.200 | C069039
5317 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | MUSCATINE |  | 02 | C070049 | Muscatine County will resurface 2.5 miles of County Road F-70 with new asphalt between County Road X-54 and Iowa Highway 38 north of the City of Muscatine. Four inches of the existing asphalt road wil | Pavement Improvement | 2009-07-17 | 2009-10-26 | 2009-12-01 | 2009-10-28 | 733544 | 2.500 | C070049
5318 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | PALO ALTO |  | 04 | C074092 | Palo Alto County will widen and resurface 2 miles of County Road N-20 with new asphalt between the northern city limits of Ruthven and the intersection of County Road B-25 and 355th Avenue. This proje | Pavement Improvement | 2009-05-20 | 2009-09-22 | 2009-12-01 | 2010-08-10 | 659874 | 2.000 | C074092
5319 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | PLYMOUTH |  | 05 | C075120 | Plymouth County will resurface 3 miles of County Road C-12 with new asphalt between County Road K-22 and County Road K-30 east of the City of Craig. Three inches of the existing asphalt road will be r | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2009-12-01 | 2010-03-12 | 375000 | 3.000 | C075120
5320 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | PLYMOUTH |  | 05 | C075121 | Plymouth County will resurface 1 mile of County Road K-30 with new asphalt between County Road C-12 and 100th Street north of the City of Craig. Three inches of the existing asphalt road will be recyc | Pavement Improvement | 2009-06-05 | 2009-06-01 | 2009-12-01 | 2010-03-12 | 125000 | 1.000 | C075121
5321 | IOWA | Completed | C240 | Highway Infrastructure Investment Grant | IOWA | PLYMOUTH |  | 05 | C075122 | Plymouth County will replace 5.4 miles of County Road K-22 with new concrete between the Woodbury County border and County Road C-60 north of the City of Sioux City. This project will improve driving quality and significantly extend the life of the road. | Pavement Improvement | 2009-11-20 | 2010-04-07 | 2010-12-01 | 2011-02-24 | 1189278 | 5.500 | C075122
5322 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | POLK | DES MOINES | 03 | C077168 | Polk County will resurface 5.7 miles of Northwest/Northeast 118th Avenue with new asphalt between Northwest Sheldahl Drive and U.S. Highway 69 east of the City of Polk City. This project will improve | Pavement Improvement | 2009-05-06 | 2009-05-14 | 2009-12-01 | 2009-06-18 | 1950000 | 5.500 | C077168
5323 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | POLK |  | 03 | C077169 | Polk County will resurface 3.5 miles of various city roads with new asphalt. Locations include Northwest 110th Avenue between Iowa Highway 17 and Northeast 121st Street northwest of the City of Des Mo | Pavement Improvement | 2009-05-06 | 2009-05-14 | 2009-12-01 | 2009-06-18 | 418779 | 3.500 | C077169
5324 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | POWESHIEK |  | 03 | C079041 | Poweshiek County will resurface 2.7 miles of County Road F-62 with new asphalt between the Jasper County border and Iowa Highway 146 west of the City of Searsboro. Four inches of the existing asphalt | Pavement Improvement | 2009-07-06 | 2009-09-21 | 2009-12-01 | 2011-04-21 | 619700 | 3.000 | C079041
5325 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | RINGGOLD |  | 05 | C080049 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road P64 over a tributary to Lotts Creek 3.7 miles Southwest of Kellerton. | Bridge Replacement | 2009-08-12 | 2009-08-14 | 2010-12-01 | 2010-05-06 | 312555 | 0.000 | C080049
5326 | IOWA | Completed | C230 | Highway Infrastructure Investment Grant | IOWA | SCOTT | DAVENPORT-ROCK ISLAND-MOLINE (IL) | 01 | C082039 | Scott County will resurface 5.1 miles of County Road Y-48 with new asphalt between Iowa Highway 22 and County Road F-65 west of the City of Davenport. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2009-05-26 | 2009-06-18 | 2009-12-01 | 2010-09-02 | 2100000 | 4.000 | C082039
5327 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | C082042 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road F33/St. Ann’s Road over Mason Creek approximately 3 miles Northwest of Long Grove. | Bridge Replacement | 2009-09-21 | 2009-10-02 | 2010-12-01 | 2010-09-16 | 299524.5 | 0.000 | C082042
5328 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | C082044 | The project is for the replacement of a Reinforced Concrete Box (RCB) Culvert, Single Box, by Scott County. The existing RCB Culvert had deteriorated, and the structure no longer serves the drainage | New Bridge Construction | 2009-09-21 | 2009-09-26 | 2010-12-01 | 2011-09-01 | 134516 | 0.090 | C082044
5329 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SCOTT |  | 01 | C082046 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on County Road Y48/Maysville Road over Hickory Creek approximately 1.5 miles Southeast of Maysville. | Bridge Replacement | 2009-09-28 | 2010-03-24 | 2010-06-01 | 2011-05-09 | 288203.93 | 0.020 | C082046
5330 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SHELBY |  | 05 | C083046 | Shelby County will resurface 5.6 miles of County Road F-58 with new asphalt between Maple Road and County Road M-47 south of the City of Harlen. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2009-08-17 | 2009-08-24 | 2010-12-01 | 2010-12-14 | 1400000 | 5.600 | C083046
5331 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SIOUX |  | 05 | C084130 | Sioux County will resurface 4.9 miles of County Road L-14 with new asphalt between U.S. Highway 18 and the Lyon County border north of the City of Boyden. Three inches of the existing asphalt road wil | Pavement Improvement | 2009-05-18 | 2009-07-27 | 2009-12-01 | 2009-12-18 | 985471.84 | 5.000 | C084130
5332 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | SIOUX |  | 05 | C084132 | This project will replace a bridge, which is in poor condition and narrow, with a new bridge. The bridge is on Harrison Avenue over a small stream 1 mile east and 3.5 miles South of Maurice. | Bridge Replacement | 2009-05-18 | 2009-08-03 | 2009-12-01 | 2009-12-18 | 330396.12 | 0.010 | C084132
5333 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | STORY |  | 04 | C085102 | Story County will resurface 4 miles of County Road E-29 with new asphalt between U.S. Highway 65 and the Marshall County border north of the City of Colo. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2009-05-20 | 2009-07-20 | 2009-12-01 | 2009-09-17 | 858307 | 4.000 | C085102
5334 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | TAMA |  | 03 | C086074 | Tama County will resurface 9.8 miles of various county roads south of the City of Tama with new asphalt. Locations include County Road E-69 between Iowa Highway 146 and U.S. Highway 63, and County Roa | Pavement Improvement | 2009-06-17 | 2009-08-03 | 2009-12-01 | 2011-04-05 | 966635.42 | 10.000 | C086074
5335 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | TAYLOR |  | 05 | C087037 | This project will install longitudinal subdrains along both sides of the existing roadway for Taylor County Road N44 from the Missouri State Line north for 4.3 miles to Taylor County Road J55. The su | Pavement Improvement | 2010-01-12 | 2010-07-23 | 2010-12-01 | 2010-08-11 | 199866.48 | 3.500 | C087037
5336 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | TAYLOR |  | 05 | C087038 | This project will install longitudinal subdrains along both sides of the existing roadway for Taylor County Road P14 from the Missouri State Line north for 2.7 miles to Taylor County Road J55 and on T | Pavement Improvement | 2010-01-12 | 2010-07-13 | 2010-12-01 | 2010-08-11 | 152496 | 3.500 | C087038
5337 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | UNION |  | 05 | C088040 | Union County will resurface 3 miles of County Road P-33 with new asphalt between County Road H-17 and Adair-Union Street north of the City of Creston. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2009-05-12 | 2009-05-19 | 2009-12-01 | 2009-08-19 | 437751 | 3.000 | C088040
5338 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | VAN BUREN |  | 02 | C089057 | Van Buren County will remove the top three inches of existing pavement on County Road V-64 and resurface it with new asphalt between Iowa Highway 16 and the Jefferson-Van Buren County line west of the | Pavement Improvement | 2009-05-14 | 2009-06-03 | 2009-12-01 | 2009-08-20 | 320993 | 3.400 | C089057
5339 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WAPELLO |  | 02 | C090060 | Wapello County will resurface 3.8 miles of various county roads near the City of Ottumwa with new asphalt. Locations include County Road H-21 between Blackhawk Road and County Road H-27, and County Ro | Pavement Improvement | 2009-05-15 | 2009-05-08 | 2009-12-01 | 2009-09-16 | 423752 | 12.500 | C090060
5340 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WARREN |  | 04 | C091081 | Warren County will resurface 3.2 miles of County Road S-23 with new asphalt between County Road G-24 and Iowa Highway 5 west of the City of Hartford. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2009-05-18 | 2009-06-08 | 2009-12-01 | 2009-10-28 | 576146 | 3.200 | C091081
5341 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WASHINGTON |  | 02 | C092075 | Washington County will overlay 4.2 miles of County Road W-64 with new concrete between 160th Street and Iowa Highway 22 east of the City of Riverside. This project will improve driving quality and significantly extend the life of the road. | Pavement Improvement | 2009-05-14 | 2009-08-24 | 2009-12-01 | 2009-09-28 | 732691 | 5.600 | C092075
5342 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WEBSTER |  | 04 | C094082 | This project will repair a bridge, which is in poor condition, by replacing the bridge deck. The bridge is on County Road C66 over Lizard Creek 5 miles West of Clare. | Bridge Improvement | 2009-07-01 | 2009-07-20 | 2009-12-01 | 2010-02-11 | 350000 | 0.060 | C094082
5343 | IOWA | Completed | C200,C240 | Highway Infrastructure Investment Grant | IOWA | WEBSTER |  | 04 | C094083 | Webster County will resurface 2.4 miles of County Road D-14 with new asphalt between U.S. Highway 169 and County Road P-56 north of the City of Wahkonsa. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2010-02-11 | 2010-05-26 | 2010-12-01 | 2011-03-24 | 934867 | 2.500 | C094083
5344 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WINNEBAGO |  | 04 | C095055 | Winnebago County will resurface 3.7 miles of County Road R-60 with new asphalt between U.S. Highway 69 and the southern city limits of Scarville. This project will improve driving quality by providing a more smooth riding surface. | Pavement Improvement | 2009-05-13 | 2009-06-15 | 2009-12-01 | 2009-07-17 | 532664.81 | 3.700 | C095055
5345 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WINNESHIEK |  | 04 | C096101 | Winneshiek County will overlay 2.2 miles of County Road V-68 with new concrete between the Fayette County border and Iowa Highway 24 in the City of Jackson Junction. This project will improve driving quality and significantly extend the life of the road. | Pavement Improvement | 2009-05-21 | 2009-05-28 | 2009-12-01 | 2010-11-12 | 664000 | 2.200 | C096101
5346 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY |  | 05 | C097107 | This project will mill and place three and a half inches of hot-mix asphalt for 1.6 miles of Correctionville Road from Sioux City’s city limits to just past Buchanan Ave. The project will create a smoother road. | Pavement Improvement | 2009-05-26 | 2009-07-14 | 2009-12-01 | 2010-09-27 | 626318.87 | 1.800 | C097107
5347 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WOODBURY |  | 05 | C097108 | This project will mill and place four inches of pavement on county road L-37 for approximately 10.7 miles from near Danbury, IA to county road D-38. The project will improve pavement condition and safety. | Pavement Improvement | 2009-06-02 | 2009-08-24 | 2009-12-01 | 2010-09-27 | 500000 | 10.000 | C097108
5348 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WORTH |  | 04 | C098050 | This project places a concrete overlay on a bridge deck to extend the service life of the bridge. The bridge is located on 410th Street over the Shell Rock River 1.5 miles east of Kensett. | Bridge Improvement | 2009-08-12 | 2010-04-14 | 2010-12-01 | 2010-07-07 | 48417.6 | 0.030 | C098050
5349 | IOWA | Completed | C200 | Highway Infrastructure Investment Grant | IOWA | WORTH |  | 04 | C098051 | This project places a concrete overlay on a bridge deck to extend the service life of the bridge. The bridge is located on 495th Street over the Shell Rock River approximately 1 mile West and 2.5 miles North of Northwood. | Bridge Improvement | 2009-08-12 | 2010-04-14 | 2010-12-01 | 2010-07-07 | 32695.6 | 0.020 | C098051
5350 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | SHAWNEE | TOPEKA | 02 | 0705215 | This project will plant wildflowers within KDOT R/W at the Topeka: I-70/KTA Interchange to provide beautification along I-70. | Transportation Enhancements | 2010-11-22 | 2010-11-22 | 2010-12-06 | 2010-11-22 | 14670.2 |  | 0705215
5351 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | 0706047 | This project will plant wildflowers within KDOT right-of-way at the I-70/I-435 interchange Kansas City and Edwardsville. | Transportation Enhancements | 2010-11-22 | 2010-11-23 | 2010-11-29 | 2010-11-23 | 16771.48 |  | 0706047
5352 | KANSAS | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | 1351209 | This project will reconstruct the I-135/KTA/47th St. interchange and 47th St from Broadway to Lulu St in the city of Wichita. This work will improve traffic capacity, operation and safety on these routes. | Pavement Widening | 2009-08-20 | 2009-08-20 | 2011-02-24 | 2012-07-02 | 16564397.77 | 0.001 | 1351209
5353 | KANSAS | Underway | C240,C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | 1351214 | This project repairs bridge expansion joints and provides a polymer overlay to bridges 0.22 and 0.23 miles north of Macart Road and the two bridges at I-135/Pawnee Avenue junction in the City of Wichi | Bridge Improvement | 2010-01-14 | 2010-01-14 | 2011-11-17 |  | 983060.23 |  | 1351214
5354 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | 2351196 | This project will plant wildflowers within KDOT right-of-way at the I-235/K-96 interchange in Wichita. | Transportation Enhancements | 2010-12-16 | 2010-12-16 | 2010-12-23 | 2010-12-17 | 15959.97 |  | 2351196
5355 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | 4353359 | This project will widen and reconstruct Woodend Avenue to provide additional turn lanes in the city of Edwardsville in Wyandotte County. This work will improve traffic capacity, operations, and safety. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-09-14 | 2011-11-30 | 775000 | 0.001 | 4353359
5356 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | 4353360 | This project will plant wildflowers within KDOT R/W at the Lenexa: I-435/K-10 Interchange to provide beautification along I-435. | Transportation Enhancements | 2010-11-22 | 2010-11-23 | 2010-12-06 | 2010-11-24 | 27794.19 |  | 4353360
5357 | KANSAS | Completed | C240,C230 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | 4353363 | Ultrathin Bonded Asphalt Surface (UBAS) on driving lanes and conventional seal on shoulders. This project will include the interchange ramps and pavement markings. | Pavement Improvement | 2011-08-02 | 2011-08-02 | 2011-09-06 | 2011-09-19 | 1000000 |  | 4353363
5358 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | A004601 | This project provides traffic signals and intersection improvements to the US-54/167th Street intersection in the City of Goddard/Wichita in Sedgwick County – improving both traffic flow and safety. | Safety/Traffic Management | 2010-05-27 | 2010-08-31 | 2011-12-23 | 2011-10-17 | 500000 |  | A004601
5359 | KANSAS | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | RILEY |  | 02 | A041001 | The State will proceed with Right of Way & Utility Relocation activities and final plan development for this project. K-18 will be improved to a freeway section that will improve traffic capacity, operation and safety along K-18. | Other | 2010-08-30 |  |  |  | 16200000 | 7.344 | A041001
5360 | KANSAS | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | KANSAS | RILEY |  | 02 | A041003 | This project will construct a 4-Lane Freeway Section on K-18 in Riley County with an interchange at K-114. This work will improve traffic capacity, operation and safety along K-18. | Pavement Widening | 2010-02-10 | 2010-02-10 | 2012-12-31 |  | 69598606.36 | 3.866 | A041003
5361 | KANSAS | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | A100604 | This project will reconstruct 47th Street from Lulu Street to Hydraulic Avenue in the city of Wichita from a 4-lane to 5-lane roadway. This reconstruction will increase both capacity and safety related to the roadway. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2011-05-06 |  | 650000 |  | A100604
5362 | KANSAS | Completed | C490 | OJT/SS | KANSAS | STATEWIDE |  |  | A116910 | This project will provide skill training for women and minorities in highway construction work in central Kansas for Federal Fiscal Year 2010. | Other | 2009-09-24 | 2009-09-24 |  | 2011-09-16 | 224600 |  | A116910
5363 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | OSAGE |  | 02 | A120102 | This project will replace an abandoned RR bridge with a pedestrian bridge that is part of the KANZA Rails to Trails Conservancy trail network in Osage Co. This work will improve safety for trails users & increase the hor. and vert. clearances on US-75. | Transportation Enhancements | 2010-06-01 | 2010-06-01 | 2010-10-19 | 2011-07-07 | 901198.03 | 0.001 | A120102
5364 | KANSAS | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | GOVE |  | 01 | A153401 | This project will replace the pavement on K-23, provide a 28 ft. roadway and replace guardrail as warranted to improve safety along K-23 in Gove County. | Pavement Improvement | 2009-02-23 | 2009-02-23 | 2010-09-06 |  | 4142957.06 | 8.000 | A153401
5365 | KANSAS | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | GOVE |  | 01 | A153402 | This project will replace the pavement on K-23, provide a 28 ft. roadway and replace guardrail as warranted to improve safety along K-23 in Gove County. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2010-08-15 | 2010-08-14 | 4813954.26 | 9.600 | A153402
5366 | KANSAS | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | STATEWIDE |  |  | A181001 | The project will improve defects in approximately 42 bridges along the NKCR route in northwest Kansas and rehabilitate the approach track to these bridges as warranted. | Safety/Traffic Management | 2010-03-15 | 2010-04-19 | 2011-01-07 | 2012-01-23 | 343825.05 |  | A181001
5367 | KANSAS | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | REPUBLIC |  | 01 | A181201 | This project construct 2000 ft. of siding and a new switch into the Nesika Energy Plant in the city of Scandia that will enable the Nesika Energy Plant to ship by rail and access national markets for their product. | Safety/Traffic Management | 2010-04-19 | 2010-04-19 | 2011-02-09 | 2010-12-22 | 371000 |  | A181201
5368 | KANSAS | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | A181401 | This project will add 7,200 ft. of rail siding/pass track that will improve rail traffic flow and increase operation efficiency for elevators outside the city of Wichita. | Safety/Traffic Management | 2010-04-26 | 2010-04-26 | 2011-04-07 | 2010-12-10 | 967820 |  | A181401
5369 | KANSAS | Completed | C240 | Highway Infrastructure Investment Grant | KANSAS | RENO |  | 01 | A183901 | This project will construct storage tracks at the Siemens Nachelle Facility in the city of Hutchinson that will enable the company to ship by rail and provide for a more efficient operation. | Safety/Traffic Management | 2010-03-03 | 2010-04-19 | 2012-02-22 | 2011-06-06 | 844800 |  | A183901
5370 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | CHEROKEE |  | 02 | C000501 | County road surfacing improvements in Cherokee county on hwy 66 from Riverton south to Lowell. | Pavement Improvement | 2010-07-31 | 2010-07-31 | 2011-09-05 | 2011-03-31 | 227294.71 |  | C000501
5371 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | COMANCHE |  | 01 | C421801 | This project will replace a bridge on County Road 155, 1.0 mile West of Coldwater in Comanche County - improving structural and/or safety concerns. | Bridge Replacement | 2009-11-01 | 2009-11-01 | 2010-05-05 | 2010-06-12 | 385969.78 |  | C421801
5372 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | COWLEY |  | 04 | C422001 | This project will provide a 2 inch asphalt overlay on County Road 164 from Udall to County Road 18 in Cowley County, improving rideability and surface condition. | Pavement Improvement | 2009-08-14 | 2009-08-14 | 2009-11-03 | 2009-10-30 | 877500 |  | C422001
5373 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ELLIS |  | 01 | C422801 | This project will replace a bridge 5.6 miles South and 0.8 miles West of the city of Walker in Ellis County - improving structural and/or safety concerns. | Bridge Replacement | 2009-10-28 | 2009-11-16 | 2010-05-24 | 2010-06-30 | 475933.3 |  | C422801
5374 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | C424801 | This project will replace a bridge on 143rd Street over Captain Creek in Johnson County - improving structural and/or safety concerns. | Bridge Replacement | 2010-03-01 | 2010-03-01 | 2010-09-27 | 2011-10-08 | 701636.03 |  | C424801
5375 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | DICKINSON |  | 01 | C447801 | This project will replace a bridge on Old US Highway 40, 3.5 miles West of Highway 15 in Dickinson County - improving structural and/or safety concerns. | Pavement Improvement | 2010-01-01 | 2010-01-11 | 2010-11-05 | 2011-04-30 | 644400 |  | C447801
5376 | KANSAS | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | SHAWNEE | TOPEKA | 02 | C448901 | This project is a storm sewer and culvert project on NorthWest 46th Street Between US Highway 75 and NorthWest Fielding Road in Shawnee County that will improve drainage. | Pavement Widening | 2010-03-01 | 2010-03-10 | 2010-11-05 |  | 2170228.23 |  | C448901
5377 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ATCHISON |  | 02 | C453901 | This project will replace a bridge 4.0 miles North and 4.4 miles East of the city of Shannon in Atchison County - improving structural and/or safety concerns. | Bridge Replacement | 2009-11-18 | 2009-11-18 | 2010-09-10 | 2010-09-15 | 216000 |  | C453901
5378 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | WABAUNSEE |  | 01 | C454901 | This project will replace a bridge 5.0 miles East and 0.9 miles North of Eskridge in Wabaunsee County - improving structural and/or safety concerns. | Bridge Replacement | 2010-03-30 | 2010-03-30 | 2011-06-07 | 2010-12-17 | 332415.01 |  | C454901
5379 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | C455101 | This project will redeck a bridge 1.4 miles East of the city of Jarbalo in Leavenworth County - improving surface conditions. | Bridge Replacement | 2009-09-01 | 2009-09-01 | 2011-02-08 | 2010-04-30 | 389138.53 |  | C455101
5380 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BARBER |  | 01 | C455201 | This project will replace a bridge 2.0 miles East of the city of Hazelton on Rural Secondary Route 1381 - improving structural and/or safety concerns. | Bridge Replacement | 2009-11-02 | 2009-11-19 | 2011-04-12 | 2010-07-20 | 292272 |  | C455201
5381 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | POTTAWATOMIE |  | 02 | C455301 | This project will rehabilitate a bridge 2.0 miles North of the city of Manhattan Over the Big Blue River in Pottawatomie County - improving structural and/or safety concerns. | Bridge Replacement | 2009-12-17 | 2009-12-17 | 2011-04-12 | 2010-09-30 | 472662.1 |  | C455301
5382 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ROOKS |  | 01 | C455401 | This project resurfaces 2.6 Miles of Rural Secondary Route 916 and 1729 in the City of Woodston in Rooks County - improving surface conditions. | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2011-02-08 | 2009-12-31 | 310000 |  | C455401
5383 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | HARPER |  | 04 | C455501 | This project will provide a 4-inch overlay on NE 160th Road (Rural Secondary Route 641) near the city of Conway Springs in Harper County - improving surface conditions. | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2011-03-08 | 2010-07-09 | 510000 |  | C455501
5384 | KANSAS | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | KINGMAN |  | 04 | C455601 | This project will provide a 2-inch overlay on Rural Secondary Route 1704 (vicinity of US-54 South) in Kingman County - improving surface conditions. | Pavement Improvement | 2009-11-23 | 2010-05-01 | 2011-04-12 |  | 369381.39 |  | C455601
5385 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | RICE |  | 01 | C455701 | This project will provide a 2-inch mill (removal of exiting pavement) and asphalt overlay on Main Street ( Rural Secondary Route 983) in the city of Bushton in Rice County - improving surface condition. | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2011-05-09 | 2010-05-14 | 346547.58 |  | C455701
5386 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BUTLER |  | 04 | C455801 | This project will rehabilitate a bridge 1.5 miles West of the city of Benton and 1.7 miles North over the White Water Creek in Butler County - improving structural and/or safety concerns. | Bridge Replacement | 2010-02-17 | 2010-02-17 | 2011-06-07 | 2011-09-14 | 687750 |  | C455801
5387 | KANSAS | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | RENO |  | 01 | C455901 | This project will provide an asphalt overlay on 4th Avenue (Rural Secondary Route-636) from K-14 E to K-96 4th Avenue Interchange in Hutchinson in Reno County - improving surface conditions. | Pavement Improvement | 2009-12-02 | 2010-06-18 | 2011-04-12 |  | 517593 |  | C455901
5388 | KANSAS | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | HARVEY |  | 04 | C456001 | This project will replace a bridge on Kansas Avenue, 1.1 miles North and 0.5 miles East of Newton, in Harvey County - improving structural and/or safety concerns. | Bridge Replacement | 2010-04-16 | 2010-04-16 | 2011-07-11 |  | 575000 |  | C456001
5389 | KANSAS | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | BARTON |  | 01 | C456101 | This project will provide a maintenance resurfacing of Rural Secondary Route 462 from Great Bend West city limits West to NorthWest 60th Avenue in Great Bends in Barton County - improving surface conditions. | Pavement Improvement | 2010-03-08 | 2010-03-30 | 2011-03-08 |  | 560000 |  | C456101
5390 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ANDERSON |  | 02 | C456201 | This project will rehabilitate a bridge on Rural Secondary Route1389 4.0 miles South and 1.7 miles East of the city of Harris in Anderson County - improving structural and/or safety concerns. | Bridge Improvement | 2009-07-31 | 2009-07-31 | 2011-05-17 | 2009-12-31 | 54022.05 |  | C456201
5391 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | CHAUTAUQUA |  | 04 | C456301 | This project will provide a 2.5-inch asphalt overlay on Independence Road (Rural Secondary Route 97) for 3.5 Miles in Chautauqua County - improving surface conditions. | Pavement Improvement | 2009-08-27 |  | 2011-01-04 | 2010-12-16 | 413353.05 |  | C456301
5392 | KANSAS | Completed | C250,C200 | Highway Infrastructure Investment Grant | KANSAS | CHEROKEE |  | 02 | C456401 | This project will provide a 2-inch asphalt surfacing for 5 miles on Rural Secondary Route 1791 in Cherokee County from US-400 East to the Missouri State - improving surface conditions. | Pavement Improvement | 2010-07-31 | 2010-07-31 | 2011-09-05 | 2011-03-31 | 382429.1 |  | C456401
5393 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | FRANKLIN |  | 02 | C456501 | This project will provide a 2-inch asphalt overlay on John Brown Road (Rural Secondary Route 1066/259) Between Kentucky Road and Florida in Franklin County - improving surface conditions. | Pavement Improvement | 2009-08-27 | 2009-08-27 | 2011-01-04 | 2010-04-09 | 481205.76 |  | C456501
5394 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | GREENWOOD |  | 01 | C456601 | This project will provide a 2-inch asphalt overlay on Rural Secondary Route 291 from the city of Hamilton to the city of Virgil in Greenwood County - improving surface conditions. | Pavement Improvement | 2009-10-22 | 2009-10-22 | 2011-01-04 | 2009-11-06 | 490000 |  | C456601
5395 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ELK |  | 04 | C456701 | This project will provide an asphalt resurfacing of Kansas Street in the city of Longton from US Highway 160 to 6th Street - improving surface conditions. | Pavement Improvement | 2009-08-07 | 2009-11-11 | 2011-01-04 | 2010-07-29 | 104048.15 |  | C456701
5396 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | LINCOLN |  | 01 | C456801 | This project will provide grading and drainage structure work on Rural Secondary Route 394 (3.5 miles North of K-18 North of the city of Beverly) in Lincoln County - improving structural and drainage deficiencies. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-04-12 | 2010-05-27 | 88594.27 |  | C456801
5397 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | ELLSWORTH |  | 01 | C456901 | This project will provide an asphalt overlay on Low Road from the city of Ellsworth to the city of Kanopolis in Ellsworth County - improving surface conditions. | Pavement Improvement | 2010-01-11 | 2010-01-11 | 2011-03-08 | 2010-07-09 | 493000 |  | C456901
5398 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | MORRIS |  | 01 | C457001 | This project will provide a bridge rehabilitation (to include abutment, deck repair, and patching on the Bridge Over Rock Creek, 0.3 Miles North of the city of Dunlap, in Morris County - improving surface conditions. | Bridge Replacement | 2010-03-11 | 2010-03-11 | 2011-04-12 | 2010-12-09 | 218500 |  | C457001
5399 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | MARION |  | 01 | C457101 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on Cedar Street from Hudson North to US-56 in the city of Marion in Marion County - improving surface conditions. | Pavement Improvement | 2010-01-13 | 2010-01-13 | 2011-05-09 | 2010-07-29 | 160433.74 |  | C457101
5400 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | MITCHELL |  | 01 | C457201 | This project will provide crack repair and an asphalt overlay of Rural Secondary Routes 466 and 1029 south of the city of Glen Elder - improving surface conditions. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2011-02-08 | 2010-06-02 | 443749.74 |  | C457201
5401 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | WASHINGTON |  | 01 | C457301 | This project will provide grading and resurfacing of Rural Secondary Route 1100 through the city of Hanover from K-234 in Washington County - improving surface deficiencies and conditions. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2011-04-12 | 2010-12-07 | 351000 |  | C457301
5402 | KANSAS | Underway | C250 | Highway Infrastructure Investment Grant | KANSAS | SALINE |  | 01 | C457401 | This project will replace a bridge on Kipp Road 0.1 miles North and 0.5 miles East of the city of Kipp in Saline County - improving structural and/or safety concerns. | Bridge Replacement | 2010-01-01 | 2010-02-01 | 2011-03-08 |  | 315000 |  | C457401
5403 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | HAMILTON |  | 01 | C457501 | This project will provide a 3 inch overlay for 2 miles of Rural Secondary Road 308 from US Highway 50 south for 2 miles in Hamilton County -- improving surface conditions. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2011-09-05 | 2010-09-10 | 359303.18 |  | C457501
5404 | KANSAS | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | GRANT |  | 01 | C457601 | This project will provide surfacing work and railroad crossing improvements in the city of Ulysses on US-160 from the railroad tracks east of K-25 - improving safety and surfacing conditions. | Safety/Traffic Management | 2010-03-18 | 2010-03-18 | 2011-07-11 |  | 478489 |  | C457601
5405 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | SEWARD |  | 01 | C457701 | This project will provide turn lanes for US-54 Sallie Road and US-83/Sallie Road in the city of Liberal in Seward County - improving safety. | Pavement Improvement | 2010-07-01 | 2010-07-01 | 2011-06-07 | 2010-09-07 | 366179 |  | C457701
5406 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | STANTON |  | 01 | C457801 | This project will provide a 3-inch asphalt overlay on Rural Secondary Route 1664 in Stanton County - improving surface conditions. | Pavement Improvement | 2010-09-13 | 2010-09-13 | 2011-03-08 | 2010-10-21 | 448000 |  | C457801
5407 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | SCOTT |  | 01 | C457901 | This project will provide a 4-inch overlay of Federal Aid Secondary route 1898 2 miles West of K-95 Highway in Scott County - improving surface conditions. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2011-02-08 | 2009-11-23 | 453333.41 |  | C457901
5408 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | NEOSHO |  | 02 | C458001 | This project will provide grading, surfacing, and bridge work on Rural Secondary Route 168 East of Shaw Road for 3.5 miles in Neosho County - improving surface and structural conditions. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2011-05-09 | 2012-02-15 | 500000 |  | C458001
5409 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | C458101 | This project will provide milling and asphalt overlay on Rock Road from Oak Knoll 5.5 miles North of 63rd Street South in Wichita area in Sedgwick County - improving surface conditions. | Pavement Improvement | 2010-05-20 | 2010-05-20 | 2011-04-12 | 2011-01-31 | 1335163.31 |  | C458101
5410 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | C458401 | This project will provide a mill and overlay to 295th Street in Sedgwick County west from 21st Street to 61st Street north - improving surface condition | Pavement Improvement | 2010-05-20 | 2010-06-14 | 2011-09-06 | 2011-02-04 | 698414.37 |  | C458401
5411 | KANSAS | Underway | C490 | OJT/SS | KANSAS | STATEWIDE |  |  | K507010 | This project will provide skill training for women and minorities in highway construction work in northeast Kansas for Federal Fiscal Year 2010. | Other | 2009-11-03 | 2009-11-03 |  |  | 200402 |  | K507010
5412 | KANSAS | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | K825107 | This project will add two lanes, reconstruct the 95th Street interchange and add noise walls to selected section in the city of Overland Park. This work will improve traffic capacity, operation and safety on US-69. | Pavement Widening | 2009-06-05 | 2009-06-05 | 2012-01-10 |  | 29793303.63 | 1.841 | K825107
5413 | KANSAS | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | K825111 | This project will add two lanes & reconstruct US-69 and widen I-35 in the city of Overland Park. This work will improve traffic capacity, operation and safety on US-69 and I-35. | Pavement Widening | 2001-06-26 | 2001-06-26 | 2012-01-11 |  | 55461425.11 | 1.137 | K825111
5414 | KANSAS | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | MCPHERSON |  | 01 | K825301 | This project will construct a 4-Lane partial access controlled improvement with a bypass at the city of Inman. This work will improve traffic capacity, operation and safety along K-61. | Pavement Widening | 2009-05-06 | 2009-05-06 | 2011-11-23 |  | 33111588.91 | 7.430 | K825301
5415 | KANSAS | Underway | C240 | Highway Infrastructure Investment Grant | KANSAS | MCPHERSON |  | 01 | K825302 | This project will construct a 4-Lane partial access controlled improvement. This work will improve traffic capacity, operation and safety along K-61. | Pavement Widening | 2009-05-06 | 2009-05-06 | 2011-11-23 |  | 33068299.42 | 7.060 | K825302
5416 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | K921806 | This project will extend operation of the Operation Green Light System to improve intersection traffic signal coordination on regional arterial routes in the bi-state Kansas City Metropolitan area. Includes 19 cities, 2 counties in KS & 3 counties in MO. | Other | 2009-07-28 | 2009-07-28 | 2011-07-04 |  | 950000 |  | K921806
5417 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N037301 | This project will widen College Blvd from 4 to 6 lanes from Pflumm Road to US-69 in Overland Park in Johnson County - improving both capacity and safety. | Pavement Widening | 2009-06-25 | 2009-06-25 | 2009-09-08 | 2010-11-24 | 1000000 |  | N037301
5418 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | BUTLER | WICHITA | 04 | N039001 | This project will improve Andover Road to 5 lanes with a center turn lane, curb and gutter, and a 10-ft bide/ped sidewalk from Harry Street to 1100 Feet South of US-54 in the city of Andover in Butler County - improving both capacity and safety. | Pavement Widening | 2009-09-18 | 2009-09-18 | 2010-07-09 | 2012-08-31 | 1234800 |  | N039001
5419 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N046701 | This project will widen 87th Street from 4 to 6 lanes from Renner Blvd. to Ridgeview Road in the city of Lenexa in Johnson County - improving capacity and safety. | Pavement Widening | 2009-12-07 | 2009-12-15 | 2010-09-10 |  | 3000000 |  | N046701
5420 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N047801 | This project will reconstruct the existing 127th Street from 2 lanes to 4 lanes from Mur-Len to Black Bob in the city of Olathe in Johnson County - improving both capacity and safety. | Pavement Widening | 2010-02-16 | 2010-02-16 | 2011-02-03 |  | 3500000 |  | N047801
5421 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N047901 | This project will remove and replace curb and sidewalks, mill and overlay, and replace traffic loops on 103rd Road from State Line Road to Mission Road in the city of Leawood in Johnson County - improving surface and drainage conditions. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2011-09-05 |  | 925305.34 |  | N047901
5422 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N048001 | This project will convert 4-lane cross section to 3-lane, install sidewalks & curbs, mill and resurface Roe Avenue from West 63rd Street North to Shawnee Mission Parkway in the city of Mission in Johnson County - improving surface conditions and safety. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-06-07 | 2011-12-30 | 921921 |  | N048001
5423 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N048101 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on College Blvd From Benson Street to Nall Avenue in the city of Overland Park in Johnson County - improving surface conditions. | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2011-03-08 | 2010-10-28 | 2800000 |  | N048101
5424 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N048201 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on Merriam Drive from Johnson Drive to Shawnee Mission Parkway in the city of Merriam in Johnson County -- improving surface conditions. | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2011-09-05 | 2011-08-15 | 150000 |  | N048201
5425 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N048301 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on Merriam Drive From 57th Street to Antioch Road in the city of Merriam in Johnson County -- improving surface conditions. | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2011-09-05 | 2011-05-27 | 245294.56 |  | N048301
5426 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | N048501 | This project will remove and replace curbs, inlets, guardrails, concrete medians and rehabilitate the pavement on State Avenue from 69th Street to 47th Street - improving surface conditions, drainage, and safety. | Pavement Improvement | 2010-01-19 | 2010-01-19 | 2011-05-09 | 2012-05-30 | 4239055.77 |  | N048501
5427 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N048601 | This project will replace the Ford Street Bridge, made roadway improvements, and provide pedestrian sidewalks in the city of Valley Center in Sedgwick County - improving structural and safety concerns. | Bridge Replacement | 2010-10-04 | 2010-10-04 | 2011-06-07 |  | 838604.65 |  | N048601
5428 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N048701 | This project will replace 148-ft bridge with flood wall across Chisholm Creek N of 49th Street N of Broadway Avenue in the city of Park city in Sedgwick County. | Bridge Replacement | 2010-02-02 | 2010-02-04 | 2011-05-09 | 2011-05-12 | 1297647.96 |  | N048701
5429 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N048801 | This project will provide a full-depth reconstruction of the roadway to the bottom of the base, adding 7 inches of pavement, and striping of West Grand Ave. from Meridian Ave. to North Main Street in | Pavement Improvement | 2009-08-12 | 2010-04-02 | 2011-05-09 |  | 707659.82 |  | N048801
5430 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | N049001 | This is a roadway reconstruction project with curb and gutter, storm drainage, and sidewalks on South 138th Street From Metro Avenue North to Kansas in the city of Bonner Springs in Wyandotte County - | New Construction | 2010-04-01 | 2010-04-01 | 2011-05-09 | 2010-07-31 | 145920.92 |  | N049001
5431 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N049101 | This project will provide improvements (signals, raised medians, markings, etc.) to the existing Intersection of US56 and Old 56 Highway in the city of Gardner in Johnson County - improving safety. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-05-09 | 2011-04-12 | 414537.49 |  | N049101
5432 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N049701 | This project will provide a mill (removal of existing pavement) and overlay of Broadway-Central to 12th Street in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2011-04-25 | 2011-02-28 | 433349 |  | N049701
5433 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N049801 | This project will provide a mill (removal of exiting pavement) and asphalt overlay on 55th Street from Merriam Drive to Switzer Road in the city of Merriam in Johnson County -- improving surface conditions. | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2011-09-05 | 2011-05-27 | 50000 |  | N049801
5434 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N049901 | This project will resurface Madison Avenue Between K-15 and Rock Road in the city of Derby in Sedgwick County - improving surface conditions. | Pavement Improvement | 2010-05-05 | 2010-05-05 | 2011-03-08 | 2011-01-31 | 367517.87 |  | N049901
5435 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N050001 | This project will provide concrete pavement replacement on Hillside from 9th Street to 12 Street in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 2009-12-01 | 2009-12-01 | 2011-04-25 | 2011-02-28 | 758347 |  | N050001
5436 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N050101 | This project will provide concrete pavement replacement on Washington from 1st Street to Central Avenue in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 2009-12-01 | 2010-01-11 | 2011-04-25 | 2011-02-28 | 412406 |  | N050101
5437 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N050201 | This project will reconstruct the existing 2-lane asphalt mat to a 5-lane road (including sidewalks, signals, and drainage) on Maize Road from Pawnee Avenue to Kellogg in the city of Wichita in Sedgwi | New Construction | 2010-02-01 | 2010-02-01 | 2011-06-08 | 2010-10-29 | 3324598 |  | N050201
5438 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N050301 | This project will reconstruct the existing 2-lane facility to a 3-lane road (including sidewalks and drainage) on Hydraulic Avenue from Harry Street to Kellogg in city of Wichita in Sedgwick County - | New Construction | 2010-02-02 | 2010-02-02 | 2011-06-06 |  | 2724651 |  | N050301
5439 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N050401 | This project will provide a mill (removal of existing pavement) and overlay (to include curbs, sidewalks, ADA ramps) on Nieman Road from 59th Street to Shawnee Mission Parkway in the city of Shawnee i | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2011-05-11 |  | 227151.54 |  | N050401
5440 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N050501 | This project will provide a mill (removal of existing pavement) and overlay (to include curbs, sidewalks, ADA ramps, repairing bridge approaches on 83rd Street from Hedge Lane Terrace to Monticello Te | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2011-05-11 |  | 158560.64 |  | N050501
5441 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | N050601 | This project will provide a mill (removal of existing pavement) and overlay (to include curbs, sidewalks, ADA ramps) on Quivira Road From 64th Street to 77th Street in the city of Shawnee in Johnson County - improving surface conditions and safety. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2011-05-11 |  | 642641.24 |  | N050601
5442 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N051001 | This project will provide a mill (removal of existing pavement) and overlay on Woodlawn Avenue from Harry Street to Lincoln Street in the city of Wichita in Sedgwick County - improving surface conditions. | Pavement Improvement | 2011-03-19 | 2011-03-19 | 2012-04-18 |  | 150000 |  | N051001
5443 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N051101 | This project provides one mile of surfacing overlay to 13th Street from Maize Road to Tyler Road in the city of Wichita in Sedgwick County – improving ride. | Pavement Improvement | 2011-07-05 | 2011-07-05 | 2011-09-15 |  | 250000 |  | N051101
5444 | KANSAS | Underway | C230 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | N051401 | This project will be providing surfacing improvements to Harry Street from Greenwich Road to 127th Street in the City of Wichita -- improving rideability and safety. | New Construction | 2010-05-10 | 2010-05-10 | 2011-09-05 |  | 999836.86 |  | N051401
5445 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | COWLEY |  | 04 | T028301 | This project will construct a pedestrian/bike path in Arkansas City along the levee from Paris Park to S. Summit and ACPC Park. | Transportation Enhancements | 2010-04-04 | 2010-04-04 | 2011-12-12 | 2011-12-16 | 1500000 |  | T028301
5446 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | SHAWNEE | TOPEKA | 02 | T032301 | This project will construct a ten-foot bike/pedestrian path on the Landon Trail from 26th Street to 45th Street in the city of Topeka, Kansas. | Transportation Enhancements | 2011-03-15 | 2011-03-15 | 2011-08-25 | 2012-03-31 | 780302.92 |  | T032301
5447 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | FORD |  | 01 | T032501 | This project will construct a pedestrian/bike path along US-50 from 14th Street East to 6th Avenue in Dodge City in Ford County. | Transportation Enhancements | 2010-05-14 | 2010-05-14 | 2011-04-25 | 2011-05-25 | 373703.8 |  | T032501
5448 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | NEOSHO |  | 02 | T033101 | This project will provide improvements to downtown Erie, KS along Main St from Fourth St, north to State St, then west on State St to US Highway 59, to include brick paver accents, curb and gutter, lighting, landscaping and sidewalk amenities. | Transportation Enhancements | 2009-10-16 | 2009-10-16 | 2010-11-03 | 2011-02-28 | 618985.5 |  | T033101
5449 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | GREENWOOD |  | 04 | T033401 | Restore part of the interior and exterior and establish a transportation museum/welcome center in the former bus depot of the Greenwood Hotel at 300 N Main | Transportation Enhancements | 2009-09-10 | 2009-09-10 | 2011-01-04 | 2011-09-16 | 1246246.43 |  | T033401
5450 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | FRANKLIN |  | 02 | T033801 | This project will rehabilitate six railroad trestles, in various stages of disrepair, on the Midland Railway track located between Montana and Pawnee Roads in Franklin County. | Transportation Enhancements | 2010-02-03 | 2010-02-03 | 2010-10-04 | 2010-12-23 | 291760 |  | T033801
5451 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | DOUGLAS | LAWRENCE | 03 | T033901 | This project will remove an existing asphalt overlay, provide restoration of historic brick streets and reconstruction of four intersections on New York Street from 9th Street to 12th Street in Lawrence, Kansas. | Transportation Enhancements | 2009-12-21 | 2009-12-21 | 2010-10-04 | 2010-10-31 | 674778.32 |  | T033901
5452 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | RILEY |  | 02 | T034001 | Restore portions of interior of the historic Isaac Goodnow house in Manhattan, KS including stabilization work on the stairs & interior walls & surface restoration with historically appropriate plaster work, wallpaper, painting, flooring & carpeting. | Transportation Enhancements | 2009-11-19 | 2009-11-19 | 2010-10-04 | 2011-06-23 | 113519 |  | T034001
5453 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | RICE |  | 01 | T034101 | This project will install 2 brick masonry Welcome Portal Signs on the north & south entrances to the city on Broadway (K-14, K-96) with landscaping & a concrete walkway along the west side of Broadway from the north Welcome Portal Sign to Forest Avenue | Transportation Enhancements | 2010-04-09 | 2010-04-09 | 2010-12-02 | 2010-09-22 | 69390 |  | T034101
5454 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | STEVENS |  | 01 | T034201 | Project to provide new sidewalks w/ brick pavers, lighting, raised planters, ADA ramps, crosswalks, landscaping, irrigation, fence, benches & trash cans along Main St (US Hwy 56) from 5th to 7th St & along 6th St, from Jackson to Monroe St in Hugoton, KS. | Transportation Enhancements | 2009-11-20 | 2009-11-20 | 2010-10-04 | 2010-11-26 | 1208858.41 | 0.001 | T034201
5455 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | WYANDOTTE | KANSAS CITY (MO) | 03 | T034401 | This project will provide streetscape improvements from the Kansas Highway 7 off ramp, along Front Street (Kansas Highway 32) to Elm Street, in Bonner Springs, Kansas, and will include decorative street lighting, signs and landscaping. | Transportation Enhancements | 2009-12-14 | 2009-12-14 | 2010-11-03 | 2011-03-04 | 226056.5 |  | T034401
5456 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | MIAMI |  | 02 | T034501 | Project will include concrete & concrete paver sidewalk surface w/ retaining wall, trash cans, bike rack, lighting, signing, pavement markings and landscape improvements to downtown Osawatomie, KS along Main St from 6th, east to 205 feet east of 5th St. | Transportation Enhancements | 2010-01-14 | 2010-01-14 | 2010-10-04 | 2010-11-17 | 649940 |  | T034501
5457 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | FRANKLIN |  | 02 | T034601 | This project will provide lighting along the Prairie Spirit Rail Trail between 5th and 23rd Streets a distance of up to approximately 11,300 linear feet, in Ottawa, KS, with the installation of L.E.D. lighting fixtures and poles. | Transportation Enhancements | 2010-02-08 | 2010-02-08 | 2010-11-03 | 2010-08-02 | 153500 |  | T034601
5458 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | DOUGLAS | LAWRENCE | 03 | T034701 | This project will remove an existing six-foot asphalt path and construct a ten-foot concrete path on the south side of Clinton Parkway from east of Wakarusa Drive to K-10 highway in Lawrence, Kansas. | Transportation Enhancements | 2009-12-18 | 2009-12-18 | 2010-10-04 | 2010-11-23 | 800750 |  | T034701
5459 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | SEDGWICK | WICHITA | 04 | T034801 | This project will construct a concrete ped/bike path from 111th St, along the Mulvane Sports Complex (MSC), then connect to existing path & another path section from 111th St south along Webb Road to the Cedar Brook neighborhood. | Transportation Enhancements | 2009-10-19 | 2009-10-19 | 2010-10-04 | 2010-04-07 | 158485.69 |  | T034801
5460 | KANSAS | Completed | C220 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | T035001 | This project will construct a 1.3 mile extension of the South Indian Creek Trail, from Southdowns Park, to Hampton Park & an extension of 159th St trail to connect to Chisholm Trail Jr High, & include signage demarcating the historic Santa Fe Trail. | Transportation Enhancements | 2010-01-26 | 2010-01-26 | 2010-12-02 | 2010-12-28 | 569445.55 |  | T035001
5461 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | HARVEY |  | 04 | U000401 | This project will provide resurface and rehabilitation on the Main Street Bridge in Halstead in Harvey County - improving structural and surface conditions. | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2010-07-12 | 2010-07-08 | 323557.65 |  | U000401
5462 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | DOUGLAS | LAWRENCE | 02 | U204101 | This project will be a reconstruction of the Intersection of North 2nd Street and Locust Street in the City of Lawrence in Douglas County - improving surface condition and safety. | Safety/Traffic Management | 2009-07-20 | 2009-07-28 | 2010-10-13 | 2010-08-26 | 2000000 |  | U204101
5463 | KANSAS | Completed | C230 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | U214201 | This project will remove and replace concrete approach lanes, provide a mill (removal of existing pavement) and overlay, and make ADA modifications on US-56 to 47th Street on US-169 (Rainbow BLVD) in | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-06-01 | 2010-09-30 | 1204006.53 |  | U214201
5464 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | U223201 | This project will provide a variable mill (removal of existing pavement) and overlay on RS-348 (Nelson/ West 8th Street) From RailRoad to Morgan Street in the city of Edgerton in Johnson County - improving surface conditions. | Pavement Improvement | 2009-10-22 | 2009-10-24 | 2011-03-08 | 2010-03-12 | 139352.07 |  | U223201
5465 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | JOHNSON | KANSAS CITY (MO) | 03 | U223301 | This project will provide a 2-inch mill (removal of existing pavement) and overlay (to include signage and markings) on Kill Creek Road (RS-346) from 83rd to K-10 in the city of Desoto in Johnson County - improving surface conditions. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2011-04-12 | 2010-07-28 | 330102.09 |  | U223301
5466 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223401 | This project will provide a surface overlay, aggregate shoulders, pavement markings, storm sewer improvements on 147th Street from South of Cottonwood Drive North to 4H Road in the city of Lansing in | Pavement Improvement | 2009-10-01 | 2009-10-01 | 2011-03-08 | 2011-03-31 | 231528.6 |  | U223401
5467 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223501 | This project will provide a pedestrian signal on US Highway 24 at NorthStar Drive in the city of Tonganoxie in Leavenworth County - improving safety. | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2011-02-08 | 2010-08-31 | 23800 |  | U223501
5468 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | JEFFERSON |  | 02 | U223601 | This project will provide an overlay to Jefferson Street from Walnut to City Limits in the city of Oskaloosa in Jefferson County - improving surface conditions. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2009-11-09 | 2009-11-03 | 30801.32 |  | U223601
5469 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | DONIPHAN |  | 02 | U223701 | This project will provide surfacing and culvert work (replacing the Reinforced Concrete Bridge) on Old US-36 (RS-2128) just west of Elm Street in the city of Highland in Doniphan County - improving surface conditions and drainage. | Pavement Improvement | 2009-11-18 | 2009-11-18 | 2011-04-12 | 2010-07-31 | 208726.54 |  | U223701
5470 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U223901 | This project will provide storm sewer improvements on 4th Street at K-7/73and Spruce K-92 in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2011-04-12 | 2011-07-31 | 226263.56 |  | U223901
5471 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U224001 | This project will provide storm sewer improvements on 5th Ave and Doniphan in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2011-04-12 | 2011-03-31 | 89586 |  | U224001
5472 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LEAVENWORTH | KANSAS CITY (MO) | 02 | U224101 | This project will provide storm sewer improvements on 10th Street and Wellington in the city of Leavenworth in Leavenworth County - improving drainage. | Pavement Improvement | 2009-11-02 | 2009-11-02 | 2011-04-12 | 2011-03-31 | 124435 |  | U224101
5473 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | POTTAWATOMIE |  | 02 | U224201 | This project will provide realignment of the intersection, surfacing, adding double left-turn lanes, and upgrading the traffic signals at the Intersection of US 24 and McCall Road in the city of Manha | Safety/Traffic Management | 2010-02-15 | 2010-02-15 | 2011-06-13 | 2012-01-29 | 1000000 |  | U224201
5474 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | RUSSELL |  | 01 | U224301 | This project will provide a reconstruction of US 281 Highway (Fossil Street) from East 9th to Union Pacific RR in the city of Russell in Russell County - improving surface conditions. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-04-12 | 2011-03-17 | 291438.36 |  | U224301
5475 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | WALLACE |  | 01 | U224401 | This project will provide a mill (removal of existing pavement) and overlay on Highway K-27 from North Front Street to Third Street in the city of Sharon Springs in Wallace County - improving surface conditions. | Pavement Improvement | 2010-05-06 | 2010-05-31 | 2011-04-12 | 2010-06-24 | 120555.18 |  | U224401
5476 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | PAWNEE |  | 01 | U224501 | This project will provide a 1-inch mill (removal of existing pavement) and 2 inch overlay on Northeast Trail Street from the US-56 junction east to 11th Street in the city of Larned in Pawnee County - improving surface conditions. | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2011-07-11 | 2011-04-05 | 209947.62 |  | U224501
5477 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BARTON |  | 01 | U224601 | This project will provide grading and concrete pavement surfacing on US 281 (Main Street) from 3rd Street to the RailRoad Tracks in the city of Hoisington in Barton County - improving surface conditions. | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2011-07-11 | 2010-12-16 | 476588.21 | 0.234 | U224601
5478 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | RENO |  | 01 | U224701 | This project will provide a bridge replacement on 4th Ave. over Monroe Street in the city of Hutchinson in Reno County - improving structural concerns. | Bridge Replacement | 2010-02-01 | 2010-03-08 | 2011-05-09 | 2011-02-15 | 480558.62 |  | U224701
5479 | KANSAS | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | BARTON |  | 01 | U224801 | This project will provide a reconstruction of McKinley Street in the city of Great Bends in Barton County - improving structural and surface conditions. | Pavement Improvement | 2010-02-15 | 2010-03-22 | 2011-05-09 |  | 488000 |  | U224801
5480 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | PRATT |  | 01 | U224901 | This project will provide a 4-inch mill (removal of existing pavement) and overlay between the railroad crossing at US-281 and Maple Street and the north city limits of the city of Pratt in Pratt County - improving surface conditions. | Pavement Improvement | 2010-01-21 | 2010-03-20 | 2011-06-06 | 2010-05-21 | 122672.08 |  | U224901
5481 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BUTLER |  | 04 | U225001 | This project will provide an asphalt overlay on 6th Avenue and Boyer Avenue from K-254 to Metcalf Road in the city of El Dorado in Butler County - improving surface conditions. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2011-06-07 | 2011-04-22 | 750000 |  | U225001
5482 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BARBER |  | 01 | U225101 | This project will provide curb and gutter replacement on K-2 and East Main in the city of Kiowa in Barber County - improving drainage. | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2011-10-10 | 2010-11-30 | 253655.06 |  | U225101
5483 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | SUMNER |  | 04 | U225201 | This project will provide culvert replacement and surfacing work at the Hillside Street Bridge over the Rock Island Slough in the city of Wellington in Sumner County - improving drainage and surface conditions. | New Bridge Construction | 2010-03-05 | 2010-03-05 | 2011-06-07 | 2010-09-27 | 289157.61 |  | U225201
5484 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | MONTGOMERY |  | 04 | U225301 | This project will provide an asphalt overlay on 4th Avenue (RS-809) from US 75 to Wood Street in the city of Caney in Montgomery County - improving surface conditions. | Pavement Improvement | 2009-08-07 | 2009-10-12 | 2011-01-04 | 2010-06-21 | 111174.35 |  | U225301
5485 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | BOURBON |  | 02 | U225401 | This project will provide an asphalt overlay and curb work on SW National Street from Linker Street to Wall Street in the city of Fort Scott in Bourbon County - improving surface conditions. | Pavement Improvement | 2009-10-01 | 2009-10-06 | 2011-01-04 | 2010-12-01 | 228180 |  | U225401
5486 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | MIAMI |  | 02 | U225501 | This project will provide an asphalt overlay on 8th Street from the North City Limits to Main Street in the city of Osawatomie in Miami County - improving surface conditions. | Pavement Improvement | 2009-10-01 | 2009-10-30 | 2011-01-04 | 2010-02-05 | 72243.91 |  | U225501
5487 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | CRAWFORD |  | 02 | U225601 | This project will provide an asphalt overlay on Broadway Street from Centennial to Williams in the city of Pittsburg in Crawford County - improving surface conditions. | Pavement Improvement | 2009-08-27 | 2009-08-27 | 2011-01-04 | 2010-07-31 | 205982.81 |  | U225601
5488 | KANSAS | Underway | C200 | Highway Infrastructure Investment Grant | KANSAS | CHASE |  | 01 | U225701 | This project will provide an asphalt overlay on 5th Street from West of Cedar Street to State Street in the city of Concordia in Cloud County - improving surface conditions. | Pavement Improvement | 2010-02-11 | 2010-03-01 | 2011-06-07 |  | 425283 |  | U225701
5489 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | DICKINSON |  | 01 | U225801 | This project will provide a mill (removal of existing pavement) and overlay on US-56B from the South City Limits to 4th Street in the city of Herington in Dickinson County - improving surface conditions. | Pavement Improvement | 2010-07-20 | 2010-07-20 | 2011-05-09 | 2010-08-11 | 331835.48 |  | U225801
5490 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | FORD |  | 01 | U225901 | This project will provide expansion joint replacement on the bridge on 14th Ave. over the Arkansas River in the city of Dodge City - improving structural conditions. | Bridge Replacement | 2010-05-03 | 2010-05-03 | 2011-07-11 | 2011-03-11 | 99000 |  | U225901
5491 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | LABETTE |  | 02 | U226001 | This project will provide intersection improvements at US 59 and Flynn Drive in the city of Parsons in Labette County - improving safety and economic development associated with the Flynn Industrial Park. | Safety/Traffic Management | 2010-03-17 | 2010-03-17 | 2011-06-07 | 2011-03-05 | 400346.26 |  | U226001
5492 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | GRAY |  | 01 | U226101 | This project provide concrete pavement on US-50 from Fifth Street east for 2.5 blocks in the city of Cimarron in Gray County - improving surface conditions. | Pavement Improvement | 2010-05-24 | 2010-06-09 | 2011-05-10 | 2010-10-13 | 742833.23 | 0.959 | U226101
5493 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | OTTAWA |  | 01 | U226201 | This project will provide a mill (removal of existing pavement) and overlay on Rock Street from Intersection K-106 to North City Limits of city of Minneapolis in Ottawa County - improving surface conditions. | Pavement Improvement | 2010-06-09 | 2010-06-09 | 2011-04-11 | 2010-11-08 | 135913.82 |  | U226201
5494 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | MARION |  | 01 | U226301 | This project will provide an asphalt overlay on Ash Street 1st Street to 3rd Street in the city of Hillsboro in Marion County - improving surface conditions. | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2011-06-07 | 2011-02-07 | 412900 |  | U226301
5495 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | OSAGE |  | 02 | U226401 | This project will provide a mill (removal of existing pavement) and overlay and curb & gutter work on US-56 from the South City Limit to Santa Fe Avenue West on K-31 in the city of Burlingame in Osage County - improving surface conditions and drainage. | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-04-12 | 2010-06-28 | 493465 |  | U226401
5496 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | SHERMAN |  | 01 | U226501 | This project will provide roadway reconstruction/surfacing of K-27/US- 24 Business North of I-70 in the city of Goodland in Sherman County - improving structural and surface conditions. | Pavement Improvement | 2010-06-02 | 2010-06-02 | 2011-09-06 | 2011-03-29 | 491395.9 |  | U226501
5497 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | HODGEMAN |  | 01 | U226601 | This project will provide a mill (removal of existing pavement) and overlay on RS226 in the city of Hanston in Hodgeman County - improving surface conditions. | Pavement Improvement | 2010-01-29 | 2010-04-12 | 2011-05-10 | 2010-05-28 | 99206.95 |  | U226601
5498 | KANSAS | Completed | C250 | Highway Infrastructure Investment Grant | KANSAS | MORTON |  | 01 | U226701 | This project will provide a mill (removal of existing pavement) and inlay on North Street from Baca Ave. East to Border Ave. in the city of Elkhart in Morton County - improving surface conditions. | Pavement Improvement | 2010-09-13 | 2010-09-13 | 2011-04-12 | 2010-09-29 | 355615 |  | U226701
5499 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | PHILLIPS |  | 01 | U226801 | This project will provide reconstruction of the intersection at State Street and 2nd Street in the city of Phillipsburg in Phillips County -- improving surface condition and safety. | Pavement Improvement | 2010-02-02 | 2010-02-02 | 2011-06-07 | 2010-08-13 | 318200 |  | U226801
5500 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | DONIPHAN |  | 02 | U226901 | This project will provide a mill (removal of existing pavement) and overlay on RS-2163 (Locust) from Last Chance to the North City Limits in the city of Troy in Doniphan County - improving surface conditions. | Pavement Improvement | 2010-03-29 | 2010-03-29 | 2011-05-10 | 2011-02-23 | 695249.3 |  | U226901
5501 | KANSAS | Completed | C200 | Highway Infrastructure Investment Grant | KANSAS | WOODSON |  | 02 | U227001 | This project will provide an asphalt overlay on US-75 from the South City Limits 700 feet North in the city of Yates Center in Woodson County - improving surface conditions. | Pavement Improvement | 2010-03-26 | 2010-03-26 | 2011-06-07 | 2011-01-28 | 345778 |  | U227001
5502 | KENTUCKY | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | EDMONSON |  | 02 | 0051031 | WIDENING OF 2.4 MILES OF EXISTING KY 101 ROADWAY IN EDMONSON COUNTY BETWEEN RHODA AND CHALYBEATE, BEGINNING AT MILEPOINT 0.485 AND EXTENDING TO MILEPOINT 2.85. | Pavement Improvement | 2009-10-30 | 2010-04-07 | 2010-12-01 |  | 4857859.16 | 2.365 | 0051031
5503 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE |  | 06 | 0114004 | CONSTRUCTION OF NEWTOWN PIKE ROADWAY EXTENSION FROM MAIN STREET TO VERSAILLES ROAD IN LEXINGTON, KENTUCKY. | New Construction | 2009-07-10 | 2009-07-10 | 2010-12-01 | 2011-02-09 | 12100000 | 0.519 | 0114004
5504 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 0114005 | UTILITY RELOCATION FUNDING FOR THE CONSTRUCTION OF NEWTOWN PIKE ROADWAY EXTENSION FROM MAIN STREET TO VERSAILLES ROAD IN LEXINGTON, KENTUCKY. | Other | 2009-12-08 | 2009-12-08 | 2010-12-31 | 2012-06-29 | 1000000 | 0.519 | 0114005
5505 | KENTUCKY | Underway | C250 | Highway Infrastructure Investment Grant | KENTUCKY | CLINTON |  | 05 | 0139002 | PHASE I OF THE CONSTRUCTION OF THE ALBANY BYPASS IN CLINTON COUNTY; (BRIDGE AND CULVERT SECTION) BEGINNING AT BATES DELK ROAD AND EXTENDING NORTHWARD 1.53 MILES TO 450 FEET SOUTH OF CHURNTOP ROAD. | New Construction | 2010-03-24 | 2010-03-24 | 2011-05-31 |  | 3182233.6 | 1.534 | 0139002
5506 | KENTUCKY | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | BREATHITT |  | 05 | 0151065 | RECONSTRUCTION AND RELOCATION OF KY 15 ROADWAY FROM KY-15 AT JACKSON, KENTUCKY TO A POINT 0.43 MILES NORTH OF KY 15 IN BREATHITT COUNTY. | Pavement Improvement | 2009-10-30 | 2009-10-30 | 2012-05-01 |  | 11073292.84 | 0.430 | 0151065
5507 | KENTUCKY | Underway | C250,C240 | Highway Infrastructure Investment Grant | KENTUCKY | BREATHITT |  | 05 | 0151066 | RECONSTRUCTION AND RELOCATION OF KY 15 ROADWAY FROM 0.43 MILES NORTH OF KY 15 AT JACKSON, KENTUCKY TO 0.31 MILES SOUTH OF STILL HOUSE HOLLOW IN BREATHITT COUNTY. | Pavement Improvement | 2009-05-21 | 2009-08-31 | 2011-02-01 |  | 23059255.94 | 1.700 | 0151066
5508 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | LETCHER |  | 05 | 0151067 | CONSTRUCTION OF LEFT TURN LANE ON KY-15 AT THE END OF EXISTING WHITESBURG BYPASS WEST OF WHITESBURG, KENTUCKY IN LETCHER COUNTY. | Safety/Traffic Management | 2009-05-20 | 2009-08-06 | 2010-07-30 | 2010-08-31 | 1780000 | 0.270 | 0151067
5509 | KENTUCKY | Underway | C250 | Highway Infrastructure Investment Grant | KENTUCKY | MONROE |  | 01 | 0159006 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-90 ROADWAY FROM 0.34 MILES SOUTH OF BUSHONG ROAD MILEPOINT 12.75 AND EXTENDING NORTHERLY TO 0.68 MILES SOUTH OF CYCLONE ROAD AT MILEPOINT 17.45 IN MONROE COUNTY. | Pavement Improvement | 2009-05-04 | 2009-06-29 | 2011-11-15 |  | 6950972.87 | 4.700 | 0159006
5510 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | LYON, CALDWELL |  | 01 | 0242066 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-24 EAST BOUND AND WEST BOUND LANES FROM 0.5 MILE EAST OF KY-293 AT MILEPOINT 45.133 IN LYON COUNTY TO KY-139 AT MILEPOINT 65.300 IN CALDWELL COUNTY. | Pavement Improvement | 2009-04-03 | 2009-05-18 | 2009-11-09 | 2009-11-09 | 11526812 | 20.167 | 0242066
5511 | KENTUCKY | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | CAMPBELL | CINCINNATI (OH) | 04 | 0272109 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF US 27 ROADWAY FROM SOUTH OF KY-154 AT MILEPOINT 1.9 TO CAMPBELL COUNTY PARK AT MILEPOINT 5.0 IN CAMPBELL COUNTY. | Pavement Widening | 2009-05-04 | 2009-08-25 | 2011-11-30 |  | 27620000 | 3.200 | 0272109
5512 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | KENTON | CINCINNATI (OH) | 04 | 0273013 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF 12TH STREET ROADWAY FROM I-75 TO SCOTT STREET IN COVINGTON, KENTUCKY IN KENTON COUNTY. | Pavement Improvement | 2009-05-22 | 2009-05-22 | 2011-11-01 | 2012-01-13 | 7586554 | 0.470 | 0273013
5513 | KENTUCKY | Underway | C240,C230 | Highway Infrastructure Investment Grant | KENTUCKY | KENTON | CINCINNATI (OH) | 04 | 0273014 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF 12TH STREET ROADWAY FROM I-75 TO SCOTT STREET IN COVINGTON, KENTUCKY IN KENTON COUNTY. | Pavement Improvement | 2009-07-02 | 2009-10-19 | 2011-07-01 |  | 2175306 | 0.220 | 0273014
5514 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | HARDIN | RADCLIFF-ELIZABETHTOWN | 02 | 0401068 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-144 ROADWAY TO PROVIDE HORIZONTAL AND VERTICAL REALIGNMENT OF EXISTING ROADWAY BETWEEN MILEPOINTS 0.8 TO MILEPOINT 1.1 JUST WEST OF KY-1500 AT VINE GROVE, KENTUCKY IN HARDIN COUNTY. | Safety/Traffic Management | 2009-09-16 | 2010-03-01 | 2010-06-30 | 2010-07-10 | 223819.4 | 0.300 | 0401068
5515 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | HARDIN | RADCLIFF-ELIZABETHTOWN | 02 | 0401071 | Safety improvements along KY 220 between milepoint 13.2 to milepoint 13.3 in Hardin county, Kentucky at the southeast intersection of KY 220 and KY 1600 in Rineyville, Kentucky. | Safety/Traffic Management | 2010-02-23 | 2010-02-23 | 2010-08-30 | 2010-10-07 | 557814.95 | 0.100 | 0401071
5516 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON |  | 03 | 0655098 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-65 IN JEFFERSON COUNTY FROM FERN VALLEY ROAD AT MILEPOINT 128.13 TO MILEPOINT 131.89. | Pavement Improvement | 2009-07-02 | 2009-07-02 | 2010-12-15 | 2011-03-16 | 18000000 | 3.160 | 0655098
5517 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | TRIGG |  | 01 | 0801075 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF US 68/KY 80 ROADWAY BETWEEN MILEPOINT 0.243 TO MILEPOINT 8.284 IN THE LAND BETWEEN THE LAKES AREA OF TRIGG COUNTY. | Pavement Widening | 2009-04-30 | 2009-05-30 | 2010-11-15 | 2010-11-30 | 30000000 | 7.791 | 0801075
5518 | KENTUCKY | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | CLINTON |  | 05 | 1271100 | RECONSTRUCTION OF 3.5 MILES OF US 127 IN CLINTON COUNTY BEGINNING AT THE ALBANY BYPASS AND EXTENDING NORTH TO KY 90. | Pavement Improvement | 2009-11-19 | 2010-03-10 | 2011-10-01 |  | 17940774.45 | 4.240 | 1271100
5519 | KENTUCKY | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | WASHINGTON |  | 02 | 1501096 | CONSTRUCTION OF NEW SPRINGFIELD NORTHWEST BYPASS FROM KY 555 TO US 150 NORTHWEST OF SPRINGFIELD, KENTUCKY. | New Construction | 2009-05-05 | 2009-08-12 | 2011-06-01 |  | 13421653.83 | 3.475 | 1501096
5520 | KENTUCKY | Underway | C200,C240 | Highway Infrastructure Investment Grant | KENTUCKY | ROCKCASTLE |  | 05 | 1501097 | RECONSTRUCTION OF 6 MILES OF US 150 IN ROCKCASTLE COUNTY BEGINNING AT BRODHEAD, KY AND EXTENDING EAST TO US 461 AT MT. VERNON, KY. | Pavement Improvement | 2009-10-29 | 2010-02-08 | 2011-12-01 |  | 23088172.4 | 6.310 | 1501097
5521 | KENTUCKY | Underway | C200 | Highway Infrastructure Investment Grant | KENTUCKY | NELSON |  | 02 | 1501098 | RECONSTRUCTION/RELOCATION OF 3 MILES OF US 31E IN NELSON COUNTY NORTH OF BARDSTOWN, KY BEGINNING AT KY 509 AND EXTENDING NORTH TO WHITESIDE DRIVE. | Pavement Improvement | 2009-12-29 | 2010-04-01 | 2011-07-31 |  | 7114802.28 | 3.070 | 1501098
5522 | KENTUCKY | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | ROCKCASTLE, LINCOLN |  | 05 | 1501099 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF APPROXIMATELY 7.2 MILES OF US-150 ROADWAY FROM CRAB ORCHARD, KENTUCKY IN LINCOLN COUNTY TO BRODHEAD, KENTUCKY IN ROCKCASTLE COUNTY. | Pavement Improvement | 2009-04-07 | 2009-06-08 | 2010-12-01 |  | 25448598 | 14.300 | 1501099
5523 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 2641164 | GRIND PAVEMENT AND REHABILITATION OF PAVEMENT ON I-264 IN LOUISVILLE, KENTUCKY FROM NEWBURG ROAD AT MILEPOINT 13.710 TO BRECKINRIDGE LANE AT MILEPOINT 18.410 IN JEFFERSON COUNTY. | Pavement Improvement | 2009-09-04 | 2009-10-13 | 2010-06-15 | 2010-11-08 | 11778000 | 5.700 | 2641164
5524 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON |  | 03 | 2641166 | PAVEMENT REHABILITATION TO MILL 1"" OF EXISTING PAVEMENT AND TO RESURFACE WITH THIN OVERLAY ON I-264 EAST BOUND & WEST BOUND FROM MILEPOINT 22.61 TO I-71 AT MILEPOINT 22.97. | Pavement Improvement | 2009-07-01 | 2010-05-03 | 2010-06-30 | 2010-10-18 | 301574.28 | 0.360 | 2641166
5525 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 2652023 | REPAIR AND GRIND EXISTING PAVEMENT ON I-265 IN JEFFERSON COUNTY FROM MILEPOINT 18.8 NEAR EXIT 19 AND EXTENDING NORTH TO MILEPOINT 23.4 NEAR EXIT 23. | Pavement Improvement | 2009-12-30 | 2010-04-07 | 2010-10-31 | 2010-11-05 | 3846696.7 | 4.560 | 2652023
5526 | KENTUCKY | Completed | C200 | Highway Infrastructure Investment Grant | KENTUCKY | MARION |  | 02 | 3000786 | CONSTRUCTION OF A NEW ROADWAY CONNECTOR FROM THE INTERSECTION OF THE US-68/LEBANON NORTHERN BYPASS (KY 2154) AND EXTENDING SOUTHEAST TO INDUSTRIAL DRIVE IN LEBANON, KENTUCKY IN MARION COUNTY, BEING APPROXIMATELY 1.3 MILES IN LENGTH. | New Construction | 2009-04-07 | 2009-05-21 | 2010-07-01 | 2010-06-22 | 4000000 | 1.300 | 3000786
5527 | KENTUCKY | Completed | C950 | Ferryboat | KENTUCKY | CRITTENDEN |  | 01 | 3000807 | The project will reduce service delays by providing construction and rehabiliation of the ferry landing at Cave-in-Rock Ferry which crosses the Ohio river at KY91 NW of the City of Marion in Crittenden County. | Other | 2010-11-18 | 2010-11-22 | 2010-12-22 | 2010-12-15 | 81204.72 |  | 3000807
5528 | KENTUCKY | Completed | C950 | Ferryboat | KENTUCKY | MONROE |  | 01 | 3000808 | The project will replace the aging ferry tugboat and trailer for the Turkey Neck Bend Ferry which crosses the Cumberland River on KY 214 east of Tompkinsville in Monroe County. | Other | 2010-09-15 | 2010-09-15 |  | 2012-01-31 | 300000 |  | 3000808
5529 | KENTUCKY | Underway | C950 | Ferryboat | KENTUCKY | BUTLER |  | 01 | 3000809 | The project will provide a new ferry barge at the Reeds Ferry which carried KY269 over the Green River approvimately 25 miles NW of Bowling Green in Butler County. | Other | 2011-12-01 |  | 2012-06-01 |  | 300000 |  | 3000809
5530 | KENTUCKY | Completed | C220 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001329 | CONSTRUCT A PEDESTRIAN CROSSWALK INTERSECTING 2ND STREET AND 3RD STREET, CROSSING THROUGH FREEDOM PARK, PART OF THE UNIVERSITY OF LOUISVILLE BELKNAP CAMPUS, AT CARDINAL BOULEVARD AND THIRD AND SECOND | Transportation Enhancements | 2009-08-27 | 2009-08-27 | 2010-06-01 | 2012-12-15 | 1612000 | 0.000 | 3001329
5531 | KENTUCKY | Completed | C220 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON |  | 03 | 3001339 | CONSTRUCTION OF PEDESTRIAN AND SAFETY IMPROVEMENTS INCLUDING SIDEWALKS, LANDSCAPING, AND SIGNAL IMPROVEMENTS ALONG US 60A (EASTERN PARKWAY) AT 3RD STREET IN LOUISVILLE, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 2009-07-02 | 2009-08-18 | 2010-06-01 | 2010-06-15 | 2888182.29 | 0.200 | 3001339
5532 | KENTUCKY | Completed | C240,C230 | Highway Infrastructure Investment Grant | KENTUCKY | BULLITT | LOUISVILLE (IN) | 02 | 3001343 | PAVEMENT REHABILITATION TO MILL AND GRIND EXISTING PAVEMENT, AND RESURFACE KY-1526 (KNOB CREEK ROAD) FROM KY-44 TO OLD BROOKS HILL ROAD (KY 2672) IN BULLITT COUNTY BEING APPROXIMATELY 4.9 MILES IN LENGTH. | Pavement Improvement | 2009-10-01 | 2010-05-17 | 2010-05-31 | 2010-06-02 | 315641.13 | 4.900 | 3001343
5533 | KENTUCKY | Completed | C240,C230 | Highway Infrastructure Investment Grant | KENTUCKY | BULLITT | LOUISVILLE (IN) | 02 | 3001344 | PAVEMENT REHABILITATION TO MILL AND GRIND EXISTING PAVEMENT, AND RESURFACE KY 1526 (BELLS MILL ROAD) FROM KY 44 TO KY 61 IN BULLITT COUNTY BEING APPROXIMATELY 3.9 MILES IN LENGTH. | Pavement Improvement | 2009-10-01 | 2010-05-17 | 2010-05-31 | 2010-06-02 | 277458.56 | 3.972 | 3001344
5534 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001346 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1672) | Transportation Enhancements | 2010-02-05 | 2010-06-07 | 2010-11-15 | 2010-12-03 | 407224.57 | 0.000 | 3001346
5535 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001347 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1673) | Transportation Enhancements | 2010-03-22 | 2010-03-22 | 2010-10-10 | 2011-12-09 | 1750000 |  | 3001347
5536 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001348 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1674) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-09-01 | 2010-09-20 | 179807.17 | 0.000 | 3001348
5537 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001349 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1675) | Transportation Enhancements | 2010-02-05 | 2010-08-24 | 2010-11-01 | 2010-11-15 | 80234 | 0.000 | 3001349
5538 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001350 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1676) | Transportation Enhancements | 2010-02-05 | 2010-06-25 | 2010-11-01 | 2010-11-15 | 87373 | 0.000 | 3001350
5539 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001351 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1677) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-10-29 | 130699.94 | 0.000 | 3001351
5540 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001352 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1678) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-08-02 | 141112.99 | 0.000 | 3001352
5541 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001353 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1679) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-08-09 | 126504.71 | 0.000 | 3001353
5542 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001354 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1680) | Transportation Enhancements | 2010-02-05 | 2010-05-28 | 2010-11-15 | 2010-12-15 | 104381.56 | 0.000 | 3001354
5543 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001355 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1681) | Transportation Enhancements | 2010-02-05 | 2010-10-20 | 2010-11-01 | 2010-11-15 | 74302.8 | 0.000 | 3001355
5544 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001356 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1682) | Transportation Enhancements | 2010-02-05 | 2010-10-13 | 2010-11-01 | 2010-11-15 | 89434.89 | 0.000 | 3001356
5545 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001357 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1683) | Transportation Enhancements | 2010-02-05 | 2010-09-14 | 2010-11-01 | 2010-11-15 | 74289.87 | 0.000 | 3001357
5546 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001358 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1684) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-08-31 | 108196.26 | 0.000 | 3001358
5547 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001359 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1685) | Transportation Enhancements | 2010-02-05 | 2010-05-19 | 2010-08-19 | 2010-09-15 | 121005.5 | 0.000 | 3001359
5548 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001360 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1686) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-08-10 | 102119.94 | 0.000 | 3001360
5549 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001361 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1687) | Transportation Enhancements | 2010-02-05 | 2010-05-11 | 2010-11-01 | 2010-10-04 | 101035 | 0.000 | 3001361
5550 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001362 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1688) | Transportation Enhancements | 2010-02-05 | 2010-06-01 | 2010-11-15 | 2010-12-15 | 130259 | 0.000 | 3001362
5551 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001363 | The Jefferson County- Louisville Metro Government will sponsor this project to construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1689) | Transportation Enhancements | 2010-02-05 | 2010-08-23 | 2010-11-15 | 2011-01-31 | 493530 | 0.000 | 3001363
5552 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001364 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1690) | Transportation Enhancements | 2010-03-26 | 2010-03-26 | 2010-11-15 | 2010-11-15 | 193410.79 | 0.000 | 3001364
5553 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001365 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1691) | Transportation Enhancements | 2010-02-05 | 2010-06-29 | 2010-11-01 | 2010-11-15 | 101788.6 | 0.000 | 3001365
5554 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001366 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1692) | Transportation Enhancements | 2010-02-05 | 2010-07-19 | 2010-11-01 | 2010-11-06 | 130187.73 | 0.000 | 3001366
5555 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001367 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1693) | Transportation Enhancements | 2010-02-05 | 2010-05-18 | 2010-11-01 | 2010-11-15 | 88899.03 | 0.000 | 3001367
5556 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001368 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1694) | Transportation Enhancements | 2010-02-05 | 2010-12-02 | 2010-11-01 | 2010-12-31 | 80996.44 | 0.000 | 3001368
5557 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001369 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1695) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-12-31 | 26919.47 | 0.000 | 3001369
5558 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001370 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1696) | Transportation Enhancements | 2010-02-05 | 2010-10-08 | 2010-11-15 | 2011-02-21 | 71434.99 | 0.000 | 3001370
5559 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001371 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1697) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-12-31 | 33517.28 | 0.000 | 3001371
5560 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001372 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1698) | Transportation Enhancements | 2010-02-05 | 2010-10-07 | 2010-11-15 | 2010-11-15 | 109073.18 | 0.000 | 3001372
5561 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001373 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1699) | Transportation Enhancements | 2010-02-05 | 2010-06-23 | 2010-11-01 | 2010-11-15 | 88367.17 | 0.000 | 3001373
5562 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001374 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1700) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2011-01-24 | 98327.5 | 0.000 | 3001374
5563 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001375 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1701) | Transportation Enhancements | 2010-03-26 | 2010-03-26 | 2010-11-15 | 2010-12-20 | 163919.72 | 0.000 | 3001375
5564 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001376 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1702) | Transportation Enhancements | 2010-02-05 | 2010-05-17 | 2010-11-15 | 2010-12-15 | 143764.89 | 0.000 | 3001376
5565 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001377 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1703) | Transportation Enhancements | 2010-02-05 | 2010-05-19 | 2010-11-15 | 2010-12-15 | 131519.3 | 0.000 | 3001377
5566 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001378 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1704) | Transportation Enhancements | 2010-02-05 | 2010-07-30 | 2010-11-01 | 2010-11-15 | 79446.4 | 0.000 | 3001378
5567 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001379 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1705) | Transportation Enhancements | 2010-02-05 | 2010-09-21 | 2010-11-01 | 2010-11-15 | 79723.04 | 0.000 | 3001379
5568 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001380 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1706) | Transportation Enhancements | 2010-03-26 | 2010-03-26 | 2010-11-15 | 2010-12-15 | 178751.5 | 0.000 | 3001380
5569 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001381 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1707) | Transportation Enhancements | 2010-02-05 | 2010-06-07 | 2010-11-15 | 2010-12-15 | 121714.81 | 0.000 | 3001381
5570 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001382 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1708) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-09-01 | 2010-10-29 | 144523.28 | 0.000 | 3001382
5571 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001383 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1709) | Transportation Enhancements | 2010-02-05 | 2010-05-03 | 2010-11-15 | 2010-12-15 | 751784.8 | 0.000 | 3001383
5572 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001384 | The Jefferson County- Louisville Metro Government will sponsor this project to replace existing sidewalks and curbs to meet ADA (American Disabilities Act) compliance along various streets in the City of Louisville (KIPDA ID 1715) | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2011-01-07 | 855189.41 | 0.000 | 3001384
5573 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001385 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1710) | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-11-10 | 667518.39 | 0.000 | 3001385
5574 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001386 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1711) | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2011-02-16 | 551169.64 | 0.000 | 3001386
5575 | KENTUCKY | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001387 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1712) | Pavement Improvement | 2010-02-05 | 2010-06-03 | 2010-09-01 |  | 526622.15 | 0.000 | 3001387
5576 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001388 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1713) | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-08-31 | 2010-11-02 | 585151.54 | 0.000 | 3001388
5577 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001389 | The Jefferson County- Louisville Metro Government will sponsor this project to improve the surface of various streets in the City of Louisville (KIPDA ID 1714) | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-08-31 | 2010-08-28 | 512143.55 | 0.000 | 3001389
5578 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 3001390 | RECONSTRUCTION OF APPROXIMATELY 1,443 HANDICAP RAMPS AND 1,570 FEET OF SIDEWALKS IN THE CITY OF JEFFERSONTOWN, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2011-04-29 | 1338238 | 0.000 | 3001390
5579 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001391 | The Jefferson County- Louisville Metro Government will construct new sidewalks to meet ADA (American Disabilities Act) compliance along various streets in the city of Louisville (KIPDA ID # 1671). | Transportation Enhancements | 2010-03-26 | 2010-03-26 | 2010-11-15 | 2010-12-15 | 243099.32 | 0.000 | 3001391
5580 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 3001392 | PAVEMENT REHABILITATION BY MILLING THE EXISTING SURFACE, AND REPLACING WITH A MINIMUM OF 1.5 INCHES OF ASPHALT SURFACE TO EXTEND THE PAVEMENT LIFE OF PLANTSIDE DRIVE FROM BLUEGRASS PARKWAY TO KY 1819 | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-10-01 | 2010-07-28 | 246167.08 | 0.000 | 3001392
5581 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | OLDHAM | LOUISVILLE (IN) | 04 | 3001393 | CONSTRUCT 1,400 FEET OF SIDEWALK ALONG NORTH SIDE OF KY 22 FROM KY 329 TO KY 329 BYPASS, AND CONSTRUCT 400 FEET OF SIDEWALK ALONG KY 146 FROM FLOYDSBURG ROAD TO THE NEW CRESTWOOD ELEMENTARY SCHOOL, IN CRESTWOOD, KENTUCKY IN OLDHAM COUNTY. | Transportation Enhancements | 2010-02-05 | 2010-07-08 | 2010-10-15 | 2010-09-10 | 114211.81 | 0.000 | 3001393
5582 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | OLDHAM | LOUISVILLE (IN) | 04 | 3001394 | INSTALL GUARDRAILS ALONG ROADWAYS AT VARIOUS LOCATIONS IN OLDHAM COUNTY KENTUCKY. | Safety/Traffic Management | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-11-27 | 52164.6 | 0.000 | 3001394
5583 | KENTUCKY | Completed | C220 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 3001395 | Streetscape project in Jefferson county, Kentucky in downtown Louisville, Kentucky along Second Street for improvements to traffic intersections, sidewalks, accessibility/mobility, landscaping, lighti | Transportation Enhancements | 2010-02-19 | 2010-02-19 | 2010-12-31 | 2010-10-07 | 2400000 | 0.000 | 3001395
5584 | KENTUCKY | Completed | C220 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 3001397 | Bikeway and safety improvement project in Jefferson county, Kentucky in downtown Louisville, Kentucky along Third Street and Eastern Parkway for: (1) construction of new University of Louisville entr | Transportation Enhancements | 2010-02-19 | 2010-02-19 | 2010-12-31 | 2012-03-01 | 2000000 | 0.000 | 3001397
5585 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | Multiple | 3001399 | Transit project in Jefferson county for the Transit Authority of River City (TARC) to purchase paratransit vehicles; purchase 18 cut-away paratransit vehicles, and purchase 7 paratransit mini-vans. | Other | 2011-02-24 | 2011-03-01 | 2012-12-31 | 2012-01-26 | 1820244.69 | 0.000 | 3001399
5586 | KENTUCKY | Underway | C220 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE |  | 06 | 3003241 | STRUCTURAL REPAIRS AND INSTALLATION OF COMPONENTS FOR THE RESTORATION AND CONVERSION OF THE KENTUCKY HORSE PARK'S ""BIG BARN"" TO SERVE AS VISITOR CENTER AND CARRIAGE MUSEUM AT THE KENTUCKY HORSE PARK IN LEXINGTON, KENTUCKY IN FAYETTE COUNTY. | Transportation Enhancements | 2010-07-27 | 2010-08-05 | 2011-01-02 |  | 993667.71 | 0.000 | 3003241
5587 | KENTUCKY | Underway | C220,C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 3003243 | Transportation Enhancement project in Fayette county, Kentucky at Lexington, Kentucky for the construction of Legacy Trail Phase I from Berea road at Ironworks Pike to Newtown Pike at Citation Bouleva | Transportation Enhancements | 2010-03-03 | 2010-03-18 | 2010-08-31 |  | 3275371.5 | 6.400 | 3003243
5588 | KENTUCKY | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 3003244 | Transportation Enhancement project at Fayette county, Kentucky in Lexington, Kentucky for the construction of Legacy Trail phase 2 from Citation Boulevard to Loudon Avenue. | Transportation Enhancements | 2010-03-03 | 2010-03-03 | 2010-08-31 |  | 2004632.5 | 2.100 | 3003244
5589 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 3003245 | Transportation Enhancement project in Fayette county, Kentucky at Lexington, Kentucky for the construction of the downtown streetscape project to improve mobility along Vine street from South Broadway (mp 14.149) to Rose St (mp 13.569). | Pavement Improvement | 2010-02-05 | 2010-04-05 | 2010-08-20 | 2012-01-12 | 1295000 | 0.000 | 3003245
5590 | KENTUCKY | Underway | C200 | Highway Infrastructure Investment Grant | KENTUCKY | BARREN |  | 02 | 3013012 | CONSTRUCTION OF NEW GLASGOW OUTER LOOP ROADWAY FROM US-68 TO THE LOUIE B. NUNN PARKWAY EAST OF GLASGOW, KENTUCKY. | New Construction | 2009-05-21 | 2009-07-22 | 2011-04-01 |  | 15678931 | 1.200 | 3013012
5591 | KENTUCKY | Underway | C200,C240 | Highway Infrastructure Investment Grant | KENTUCKY | DAVIESS |  | 02 | 3023014 | RECONSTRUCTION AND RELOCATION OF THE EXISTING EAST US-60 BYPASS AT OWENSBORO, KENTUCKY (EAST COUNTY CORRIDOR) BEGINNING AT REID ROAD AND EXTENDING NORTHEAST TO EXISTING US 60 EAST OF OWENSBORO, KENTUCKY. | Pavement Improvement | 2009-07-02 | 2009-08-24 | 2013-02-15 |  | 35535419.92 | 2.200 | 3023014
5592 | KENTUCKY | Underway | C220 | Highway Infrastructure Investment Grant | KENTUCKY | NELSON |  | 02 | 3025006 | Transportation Enhancement project in Nelson county, Kentucky at Bardstown, Kentucky for Phase I and Phase II construction of streetscape improvements including sidewalks, curb ramps, and widening the | Transportation Enhancements | 2010-02-19 | 2010-02-19 | 2011-04-15 |  | 2539000 | 0.000 | 3025006
5593 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | BULLITT | LOUISVILLE (IN) | 02 | 5116024 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-61 ROADWAY FROM SOUTH OF JOHN HARPER HIGHWAY (BROOKS ROAD MILEPOINT 19.33) TO THE EXISTING 4-LANE SECTION SOUTH OF CARDINAL AVENUE AT MILEPOINT 210.5 IN BULLITT COUNTY. | Pavement Widening | 2009-05-04 | 2009-06-30 | 2010-05-15 | 2010-05-14 | 4651014.75 | 0.720 | 5116024
5594 | KENTUCKY | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | NELSON |  | 02 | 5121010 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF KY-245 ROADWAY FROM MILEPOINT 6.5 AT INTERSECTION OF KY-332 NORTH OF BARDSTOWN AND EXTENDING NORTHWEST TO MILEPOINT 7.6 TO THE FLAGET HOSPITAL SITE IN BARDSTOWN, KENTUCKY IN NELSON COUNTY. | Pavement Widening | 2009-05-20 | 2009-08-12 | 2010-07-15 |  | 3815760.2 | 1.193 | 5121010
5595 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | WHITLEY |  | 05 | 5147019 | ASPHALT SURFACING FOR THE RECONSTRUCTED SECTION OF KY 92 ROADWAY FROM CORNBREAD BRANCH NEAR OLD JELLICO ROAD AT MILEPOINT 4.4 AND EXTENDING EAST TO BRIER CREEK BRIDGE AT MILEPOINT 8.4 IN WHITLEY COUNTY. | Pavement Improvement | 2009-05-01 | 2009-07-13 | 2010-06-30 | 2010-06-16 | 6020000 | 5.500 | 5147019
5596 | KENTUCKY | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | MCCREARY |  | 05 | 5147020 | RECONSTRUCTION AND RELOCATION OF KY 92 ROADWAY BETWEEN MILEPOINT 16.6 TO MILEPOINT 21.5 IN MCCREARY COUNTY. | Pavement Improvement | 2009-10-30 | 2009-12-01 | 2011-08-15 |  | 14670000 | 4.900 | 5147020
5597 | KENTUCKY | Underway | C200 | Highway Infrastructure Investment Grant | KENTUCKY | KNOX, WHITLEY |  | 05 | 5155009 | CONSTRUCTION OF A NEW ROADWAY CONNECTOR FROM KY-6 AT WOODBINE IN WHITLEY COUNTY EXTENDING NORTHEAST TO THE CORBIN BYPASS IN KNOX COUNTY, BEING APPROXIMATELY 1.2 MILES IN LENGTH. | New Construction | 2009-05-01 | 2009-05-01 | 2010-09-01 |  | 6790000 | 0.000 | 5155009
5598 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | OLDHAM | LOUISVILLE (IN) | 04 | 5162019 | CONSTRUCT 1,644 FEET OF SIDEWALKS, WHICH WILL BE 4 FEET IN WIDTH WITH FIVE-FOOT PASSING AREAS TO MEET ADA STANDARDS, ALONG THE SOUTH SIDE OF KY 146 FROM DOGWOOD LANE EXTENDING WEST TO FOLEY AVENUE IN THE CITY OF PEWEE VALLEY IN OLDHAM COUNTY. | Transportation Enhancements | 2010-02-05 | 2010-06-10 | 2010-11-01 | 2010-11-15 | 97520.22 | 0.310 | 5162019
5599 | KENTUCKY | Completed | C250 | Highway Infrastructure Investment Grant | KENTUCKY | GALLATIN |  | 04 | 5170014 | SAFETY IMPROVEMENTS, REHABILITATION OF PAVEMENT, AND CONSTRUCT NEW BRIDGE DECK WITH BARRIER WALLS ON EXISTING US 127 BIG SUGAR BRIDGE BETWEEN MILEPOINT 3.88 TO MILEPOINT 3.98 IN GALLATIN COUNTY. | Bridge Improvement | 2009-04-03 | 2009-06-15 | 2009-08-13 | 2009-08-13 | 447986.93 | 0.100 | 5170014
5600 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | MADISON |  | 06 | 5192004 | CONSTRUCTION OF LEFT TURN LANES AT THE US25 AND KY1156 INTERSECTION AT RICHMOND, KENTUCKY IN MADISON COUNTY. | Safety/Traffic Management | 2009-06-30 | 2009-09-10 | 2010-06-18 | 2010-06-18 | 910000 | 0.020 | 5192004
5601 | KENTUCKY | Completed | C200 | Highway Infrastructure Investment Grant | KENTUCKY | FRANKLIN |  | 06 | 5196010 | RECONSTRUCTION AND SAFETY IMPROVEMENTS OF APPROXIMATELY 2.3 MILES OF US 421 ROADWAY FROM EXISTING US-60/KY 676 INTERCHANGE TO 1600 FEET EAST OF CHENAULT INDUSTRIAL ROAD IN FRANKLIN COUNTY. | Pavement Widening | 2009-05-04 | 2009-07-14 | 2010-08-26 | 2010-11-15 | 9934478.4 | 1.790 | 5196010
5602 | KENTUCKY | Completed | C250 | Highway Infrastructure Investment Grant | KENTUCKY | KNOTT |  | 05 | 5339006 | CONSTRUCT LEFT TURN LANE AND IMPROVE SIGHT DISTANCE ON KY 160 AT THE INTERSECTION OF KY 3391 NEAR THE KNOTT COUNTY CENTRAL HIGH SCHOOL IN KNOTT COUNTY, KENTUCKY. | Safety/Traffic Management | 2009-12-30 | 2010-03-16 | 2010-08-15 | 2010-09-28 | 1495000 | 0.236 | 5339006
5603 | KENTUCKY | Completed | C240,C230 | Highway Infrastructure Investment Grant | KENTUCKY | HENDERSON | EVANSVILLE (IN) | 01 | 7970012 | Provide safety improvements by widening of us 41a at Henderson, Kentucky in Henderson County between milepoint 14.48 to 14.68 to construct two-way left turn lane. | Pavement Improvement | 2009-11-20 | 2010-03-19 | 2010-08-14 | 2010-09-02 | 1134685.09 | 0.200 | 7970012
5604 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | HENDERSON |  | 01 | 7997004 | Provide safety improvement by widening of Watson lane at us 41a at Henderson, Kentucky in Henderson County between milepoint 1.098 to 1.167 to accommodate two approach lanes and one receiving lane. | Pavement Improvement | 2009-11-19 | 2010-03-03 | 2010-06-04 | 2010-06-04 | 287961.36 | 0.069 | 7997004
5605 | KENTUCKY | Underway | C240 | Highway Infrastructure Investment Grant | KENTUCKY | BOONE | CINCINNATI (OH) | 04 | 8200009 | RECONSTRUCTION OF 1.6 MILES OF KY 237 IN BOONE COUNTY FROM US 42 AT GUN POWDER BEGINNING AT MILEPOINT 1.581 AND EXTENDING NORTHWEST TO WOODCREEK DRIVE NEAR MILEPOINT 3.166. | Pavement Widening | 2010-05-10 | 2010-06-10 | 2012-05-01 |  | 5731742.27 | 1.605 | 8200009
5606 | KENTUCKY | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | FAYETTE | LEXINGTON-FAYETTE | 06 | 8591002 | PHASE 1B OF THE WIDENING OF 0.7 MILES OF LIBERTY ROAD/TODDS ROAD IN LEXINGTON, KENTUCKY BEGINNING AT THE INTERSECTION OF MAN O'WAR BLVD AND EXTENDING EAST TO FOREST HILL DRIVE. | Pavement Improvement | 2009-10-30 | 2010-03-22 | 2010-09-15 |  | 470000 | 0.696 | 8591002
5607 | KENTUCKY | Underway | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 8723011 | EXTENDING EXISTING BLANKENBAKER PARKWAY (KY 913) AS 5 LANE ROADWAY IN JEFFERSON COUNTY FROM THE BLANKENBAKER ACCESS ROAD TO TAYLORSVILLE ROAD (KY 155). | Pavement Widening | 2009-11-20 | 2010-02-08 | 2011-07-15 |  | 6000700 | 0.600 | 8723011
5608 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 8724018 | INSTALLATION OF BICYCLE LANES ALONG TAYLORSVILLE ROAD BETWEEN MCMAHAN BOULEVARD AND HURSTBOURNE PARKWAY IN LOUISVILLE, KENTUCKY IN JEFFERSON COUNTY. | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-15 | 2010-06-23 | 63709.72 | 1.582 | 8724018
5609 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 8738031 | The Jefferson County- Louisville Metro Government will construct new sidewalks to meet ADA (American Disabilities Act) compliance along the east side of the Preston Highway from Gilmore Lane to Kremer Avenue in the city of Louisville (KIPDA ID # 1670). | Transportation Enhancements | 2010-02-05 | 2010-02-05 | 2010-11-01 | 2010-11-18 | 104634.85 | 0.358 | 8738031
5610 | KENTUCKY | Completed | C230 | Highway Infrastructure Investment Grant | KENTUCKY | JEFFERSON | LOUISVILLE (IN) | 03 | 8893001 | WIDEN EXISTING ROADS (NO ADDITIONAL TRAVEL LANES), ADD SIDEWALKS, CONSTRUCT DRAINAGE IMPROVEMENTS, AND INSTALL LANDSCAPING ALONG MAIN STREET FROM KY 1819 (WATTERSON TRAIL) TO THE WESTERN CITY LIMIT AN | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-09-15 | 2010-11-15 | 200072.11 | 0.108 | 8893001
5611 | KENTUCKY | Completed | C240 | Highway Infrastructure Investment Grant | KENTUCKY | GRAYSON |  | 02 | 9001011 | PAVEMENT REHABILITATION OF THE EASTBOUND LANES OF THE WESTERN KENTUCKY PARKWAY IN GRAYSON COUNTY FROM 0.9 MILES EAST OF CROW HOLLOW ROAD BRIDGE, BEGINNING AT MILEPOINT 114.9 AND EXTENDING EAST TO THE GRAYSON COUNTY - HARDIN COUNTY LINE AT MILEPOINT 119.70 | Pavement Improvement | 2009-05-20 | 2009-08-04 | 2009-09-13 | 2009-09-13 | 1100000 | 2.150 | 9001011
5612 | LOUISIANA | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | CADDO | SHREVEPORT | 04 | 0021013 | This project will build 5.5 miles of new interstate highway from LA 173 to LA 1. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas State Line in Caddo Parish. | New Construction | 2010-09-01 | 2010-09-28 | 2013-02-23 |  | 5644146.94 |  | 0021013
5613 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | CADDO |  | 04 | 0021021 | This project will build 3.2 miles of new interstate highway from US 71(S) to LA 2. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas State Line in Caddo Parish. | New Construction | 2009-11-16 | 2010-02-14 | 2011-11-26 |  | 9658943.61 | 3.153 | 0021021
5614 | LOUISIANA | Underway | C250 | Highway Infrastructure Investment Grant | LOUISIANA | WASHINGTON |  | 01 | 002S613 | These Washington Parish projects near Bogalusa will replace four existing structurally deficient timber bridges located on Burt Road and Claiborne Street. | Bridge Replacement | 2009-08-03 | 2009-08-05 | 2010-04-17 |  | 1696987.4 |  | 002S613
5615 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | JEFFERSON | NEW ORLEANS | 03 | 0105370 | This project is Phase 2 of 2 for the imporvement of the existing Interstate 10/Causeway Blvd interchange. The project includes the construction of new flyover ramps to improve the flow of traffic between Causeway Blvd. and I-10 in Jefferson Parish. | Pavement Widening | 2009-08-04 | 2009-11-09 | 2012-04-27 |  | 51729364.18 | 0.380 | 0105370
5616 | LOUISIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | LOUISIANA | ASCENSION | BATON ROUGE | 03 | 0302505 | This project will construct a sidewalk near East Ascension High School in the city of Gonzales to provide pedestrian access to parks, businesses, civic facilities as well as Bayou Francois in Ascension Parish. | Transportation Enhancements | 2010-03-22 | 2010-03-22 | 2010-06-14 | 2010-08-03 | 472446.83 | 0.511 | 0302505
5617 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ASCENSION | BATON ROUGE | 03 | 0309511 | This project includes patching deteriorated pavement and placing an asphalt overlay along LA 73 in Ascension Parish from US61(N) to the East Baton Rouge Parish Line. | Pavement Improvement | 2010-06-05 | 2010-07-08 | 2010-09-16 | 2010-09-24 | 1509512.36 | 2.880 | 0309511
5618 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ASSUMPTION | HOUMA | 03 | 0409500 | This project will construct left turn lanes on LA 1 to turn onto LA 1247 in Assumption Parish, LA. | Pavement Improvement | 2010-05-21 | 2010-06-21 | 2010-08-02 | 2010-07-22 | 242031.22 | 0.590 | 0409500
5619 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | BOSSIER | SHREVEPORT | 04 | 0809508 | This project will rebuild 2.1 miles of pavement on Stockwell Road in Bossier Parish. | Pavement Improvement | 2010-06-01 | 2010-06-25 | 2010-09-10 | 2010-09-17 | 1179268.41 | 2.100 | 0809508
5620 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | BOSSIER | SHREVEPORT | 04 | 0809509 | This project will replace cracked and deteriorated concrete along Green Acres Boulevard in Bossier Parish from La.3 (Benton Road) east to La. 3105 (Airline Drive). | Pavement Improvement | 2010-08-23 | 2010-09-22 | 2010-11-10 | 2010-11-17 | 344278.97 | 0.590 | 0809509
5621 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | CADDO | SHREVEPORT | 04 | 0905504 | This project will build 4.6 miles of new interstate highway from Mira-Myrtis Road to LA 168. This is one of eleven segments totaling 37 miles needed to connect I-49 from Shreveport to the Arkansas State Line in Caddo Parish. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2010-08-11 |  | 32554028.02 | 4.660 | 0905504
5622 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | CADDO | SHREVEPORT | 04 | 0909507 | This project will remove the deteriorated asphalt, make repairs,and place a new asphalt overlay Woolworth Road from Colquitt Road to the Shreveport City Limits in Caddo Parish. | Pavement Improvement | 2010-08-09 | 2010-08-24 | 2010-10-12 | 2010-10-14 | 757497.19 |  | 0909507
5623 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1008534 | This project will rehabilitate approximately 9.6 miles of Intetstate 210 from the east end of the Calcasieu River Bridge to Interstate 10 on the east side of Lake Charles in Calcasieu Parish. The first 2.4 mile segment from the bridge to Lake Street will | Pavement Improvement | 2009-11-09 | 2010-02-17 | 2010-12-19 | 2011-05-31 | 19842022.7 | 9.580 | 1008534
5624 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1009516 | The City of Lake Charles will repair 2 miles of Broad Street from Entreprise to Interstate 210 by placing new asphalt on the exisitng pavement in Calcasieu Parish. | Pavement Improvement | 2010-07-07 | 2010-07-29 | 2010-10-07 | 2010-12-17 | 1751513.23 | 2.236 | 1009516
5625 | LOUISIANA | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1009517 | The City of Lake Charles will repair approximately a half mile of West McNesse Street from Weaver Street to Nelson Street and 2 miles of the pavement on Weaver Street from Sale Street to Ham Reid Stree by placing new asphalt on the existing pavement. | Pavement Improvement | 2010-06-08 | 2010-06-08 | 2011-04-14 |  | 2935232.84 |  | 1009517
5626 | LOUISIANA | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1009521 | The City of Lake Charles will repair 1 mile of pavement by placing new asphalt on the existing pavement from Hodge Street to 7th Street in Calcasieu Parish. | Pavement Improvement | 2010-06-08 | 2010-06-08 | 2010-09-25 |  | 574207.33 |  | 1009521
5627 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | CALCASIEU | LAKE CHARLES | 07 | 1009522 | This project will remove the existing pavement and construct 1.25 miles of new concrete pavement on the 5 lane segment of LA 14 from LA 3092 to LA 3186 in Calcasieu Parish. | Pavement Improvement | 2010-07-28 | 2010-08-16 | 2010-12-20 | 2011-09-09 | 4359560.19 |  | 1009522
5628 | LOUISIANA | Underway | C250,C240 | Highway Infrastructure Investment Grant | LOUISIANA | IBERIA |  | 03 | 1104011 | This project will build a new bridge on US 90 at LA 85 in Iberia Parish as part of the upgrading of US 90 to become part of I-49 from Lafayette to New Orleans. | New Construction | 2009-03-03 | 2009-03-03 | 2012-09-06 |  | 29440823.1 | 1.170 | 1104011
5629 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | CATAHOULA |  | 05 | 1308502 | This project is located at the northern and southern city limits of Sicily Island in Catahoula Parish along LA 15 and will providie landscaping along the reconstructed section of LA 15 through Sicily Island. | Transportation Enhancements | 2009-07-11 | 2009-10-21 | 2009-12-23 | 2011-04-15 | 179117.58 | 0.231 | 1308502
5630 | LOUISIANA | Completed | C250 | Highway Infrastructure Investment Grant | LOUISIANA | CONCORDIA |  | 05 | 1508500 | This project will remove approximately 7 miles of the deteriorated pavement along US 425 and place new asphalt from US 65 to Foules in Concordia and Catahoula Parishes. | Pavement Improvement | 2009-09-12 | 2009-10-06 | 2009-12-29 | 2010-03-19 | 1918368.02 | 0.266 | 1508500
5631 | LOUISIANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | LOUISIANA | DE SOTO |  | 04 | 1602501 | This project will establish a trailhead with informational signage and parking area for automobiles and bicycles along LA 191 (approx. 650? south of the intersection of US 84 and LA 191) in the Toledo Bend Forest Scenic Byway in Desoto Parish. | Transportation Enhancements | 2010-06-28 | 2010-06-28 | 2010-08-16 | 2010-08-12 | 269235.53 | 0.020 | 1602501
5632 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | EAST BATON ROUGE | BATON ROUGE | 06 | 1704507 | This project located near Central, LA in East Baton Rouge Parish includes clearing, removing trees and buildings and placing soil, and two new bridges over Beaver Bayou for the new Central Thruway from Frenchtown Road to Sullivan Road. | New Construction | 2010-03-01 | 2010-03-31 | 2011-08-17 | 2011-10-04 | 7959841.76 |  | 1704507
5633 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | EAST BATON ROUGE |  | 06 | 1709503 | The project is located in Baton Rouge and consists of widening Interstate-10 from four to six lanes from the Seigen Lane Interchange to the Highland Road Interchange. | Pavement Widening | 2009-03-03 | 2009-03-10 | 2013-01-12 |  | 68536102.49 | 2.000 | 1709503
5634 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | EAST BATON ROUGE | BATON ROUGE | 06 | 1709523 | This project consists of constructing the Central Thruway which will be a concrete roadway in East Baton Rouge Parish from Florida Blvd. to the South end of Sullivan Rd. | Pavement Improvement | 2010-06-14 | 2010-07-14 | 2011-01-10 | 2011-08-31 | 1599471.18 | 0.010 | 1709523
5635 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | EVANGELINE |  | 07 | 2002502 | These Evangeline Parish projects on Red Fox Lane and 1st Street in Chataignier will replace the existing deficient timber bridges with a new concrete box culvert and a new concrete bridge. | Bridge Replacement | 2009-06-22 | 2009-06-22 | 2010-11-26 |  | 637190.85 |  | 2002502
5636 | LOUISIANA | Completed | C250 | Highway Infrastructure Investment Grant | LOUISIANA | JACKSON |  | 05 | 2508503 | This Jackson Parish project will place new asphalt along 6 miles of the existing two lanes on US 167 lanes from Quitman to the Lincoln Parish line. | Pavement Improvement | 2009-08-01 | 2009-08-18 | 2010-02-02 | 2010-03-22 | 2936311.04 | 6.060 | 2508503
5637 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | JEFFERSON | NEW ORLEANS | 03 | 2602528 | This Jefferson Parish project will remove the deteriorated pavement and place new asphalt along approximately 0.34 miles of Lapalco Boulevard beginning at Manhattan Boulevard and ending at Bayou Fatma. | Pavement Improvement | 2010-07-06 | 2010-07-19 | 2010-09-13 | 2010-10-25 | 1233867.36 |  | 2602528
5638 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | JEFFERSON | NEW ORLEANS | 03 | 2603521 | This project will overlay Segnette Blvd. from Lapalco Blvd. to US 90B in Jefferson Parish. | Pavement Improvement | 2010-11-22 | 2010-11-29 | 2011-04-18 | 2011-05-23 | 2166809.76 |  | 2603521
5639 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2803519 | This project will construct a shared use path with landscaping and lighting. The project begins near the Ira Nelson Horticulture Center proceeds to Cajundome Blvd then parallels Cajundome Blvd to Eraste Landry Road. | Transportation Enhancements | 2010-11-04 | 2010-12-06 | 2011-07-18 | 2012-11-01 | 61589.48 | 0.000 | 2803519
5640 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2804512 | This project will construct dedicated right and left turning lanes at the intersection of LA 3184 and Banks Street in the City of Lafayette. | Pavement Improvement | 2010-11-08 | 2010-12-01 | 2011-01-12 | 2011-02-21 | 278460 | 0.145 | 2804512
5641 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2808504 | This project will stabilize the roadway base and resurface the roadway on LA 733 from the junction at US 167 to the junction at LA 92. This project is located in Lafayette Parish. | Pavement Improvement | 2010-06-15 | 2010-08-02 | 2011-01-17 | 2011-07-13 | 2496470.96 | 4.426 | 2808504
5642 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809500 | This project will overlay University Ave. (La. 182) from Pinhook Road (La. 182) to Cameron St.(U.S. 90) in the City of Lafayette. | Pavement Improvement | 2011-05-06 | 2011-10-03 | 2011-11-21 | 2012-02-29 | 724183.11 | 1.845 | 2809500
5643 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809507 | This Lafayette Parish project includes removing the exisiting deteriorated pavement, repairs, and placing new asphalt and shoulders along approximately 2 miles of LA 724 from Althea Drive to US 90. | Pavement Improvement | 2010-06-19 | 2010-09-30 | 2010-11-25 | 2011-03-02 | 1232187.36 | 1.948 | 2809507
5644 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809508 | This project will construct an addditional westbound left-turn lane at Pinhook and Carmel (LA 94) in Lafayette, LA. | Pavement Widening | 2010-06-02 | 2010-09-21 | 2010-10-19 | 2010-10-28 | 246604.16 | 0.001 | 2809508
5645 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809511 | This Lafayette Parish project will remove the deteriorated pavement, make repairs, and place new asphalt at the intersection of University Avenue (LA 182) and Cameron (US 90). | Pavement Improvement | 2010-07-06 | 2010-09-01 | 2010-12-22 | 2012-02-24 | 2503458.6 |  | 2809511
5646 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809513 | This Lafayette Parish project will remove the deteriorated pavement, make repairs, and place new asphalt at the intersection of North University (LA 182) at Cameron (US 90). | Pavement Improvement | 2010-07-06 | 2010-09-01 | 2010-12-22 | 2012-02-24 | 187586.23 | 0.157 | 2809513
5647 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2809519 | This Lafayette Parish project will build a traffic roundabout at the intersection of Bonin Road and Milton Avenue (LA 92). | New Construction | 2010-06-05 | 2010-06-14 | 2010-08-09 | 2011-02-18 | 570987.84 |  | 2809519
5648 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFAYETTE | LAFAYETTE | 07 | 2810504 | This project will overlay University Ave. (La. 182) from Railroad St. (Carencro) to I-49 in the City of Lafayette. | Pavement Improvement | 2010-10-11 | 2010-10-18 | 2010-12-20 | 2011-01-31 | 1385755.17 | 2.190 | 2810504
5649 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE |  | 03 | 2909501 | This Lafourche Parish project will construct a new vertical lift bridge with concrete towers to replace the existing deficient pontoon bridge. The new bridge will be constructed on a realigned section of roadway to remove a bottleneck. | Bridge Replacement | 2009-05-20 | 2009-05-20 | 2013-05-15 |  | 33807457.58 | 0.570 | 2909501
5650 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909504 | This project provides for the placement of new asphalt and new roadway striping along the existing 2 lane highway of LA 1 from just south of US 90 to Mathews in Lafourche Parish. The roadway will have 3 lanes inlcluding a continuous left turn lane. | Pavement Improvement | 2010-06-17 | 2010-08-11 | 2010-11-03 | 2011-01-18 | 1961153.54 | 2.450 | 2909504
5651 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909505 | Turn lanes will be installed at intersection of LA 1 and LA 308 in Lafourche Parish. | Pavement Improvement | 2010-06-27 | 2010-07-08 | 2010-08-05 | 2010-08-15 | 487429.56 | 0.001 | 2909505
5652 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909506 | The project consists of repairs and new ashpalt on the following streets in Lafourche Parish: Audubon Ave. (S. Acadia - Erwin Dr.), Menard St. (Audubon - Goode St.), Ridgefield Road (LA 1 - Plantation Rd.), and Tiger Drive (LA 1 - Parish Road) | Pavement Improvement | 2010-05-19 | 2010-06-01 | 2010-08-25 | 2010-08-26 | 1367241.87 | 3.500 | 2909506
5653 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909507 | New lighting and signs will be installed along LA 1 in the Town of Lockport in Lafourche Parish. | Safety/Traffic Management | 2010-05-26 | 2010-08-10 | 2010-09-28 | 2010-12-08 | 101586.9 | 0.001 | 2909507
5654 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | LAFOURCHE | HOUMA | 03 | 2909513 | This project consists of a new 6 foot bike and walking path in the city of Thibodaux from Bayou Lane to LA 648 (Percy Brown Rd.) in Lafourche Parish. The project will provide pedestrian access to a major corridor, state highway, and local road systems. | Transportation Enhancements | 2010-05-18 | 2010-05-18 | 2010-07-20 | 2010-08-05 | 208727.45 | 0.001 | 2909513
5655 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | LIVINGSTON | BATON ROUGE | 06 | 3207500 | This project consists of the removal of existing concrete sidewalks and replacement with decorative concrete pavers and is located on LA 15 (Range Road) from East Railroad Avenue and LA 1032 (Centerville Street NW) in Denham Spring, LA. | Transportation Enhancements | 2010-06-10 | 2010-07-12 | 2010-10-04 | 2011-03-07 | 257932.3 | 0.163 | 3207500
5656 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | LIVINGSTON | BATON ROUGE | 06 | 3207506 | This project provides for pavement repair and new asphalt along portions of LA 1024 in Livingston Parish. | Pavement Improvement | 2010-03-30 | 2010-03-31 | 2010-09-01 | 2010-11-15 | 2336000 | 5.440 | 3207506
5657 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | LIVINGSTON | BATON ROUGE | 06 | 3209505 | This Design-Build project consists of widening the mainline of I-12 in Denham Spring, LA from four lanes to six lane from Pete's Hwy. to Juban Interchange in the eastbound direction, and from the Amit | New Construction | 2009-03-03 | 2009-11-08 | 2012-09-06 |  | 28887265.24 | 2.080 | 3209505
5658 | LOUISIANA | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | 3602513 | This project consists of the reconstruction of the existing roadway with new concrete pavement on Fleur De Lis Blvd from from Veterans Memorial Blvd to North of 30th St in Orleans Parish. | Pavement Improvement | 2009-11-11 | 2010-01-09 | 2010-10-16 |  | 7238577.42 |  | 3602513
5659 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | 3609501 | This project will replace deteriorated and missing sections of fence and landscaping along the fence line along portions of Interstate 10 in New Orleans East, Orleans Parish. | Transportation Enhancements | 2010-09-13 | 2010-10-13 | 2011-03-02 | 2011-04-28 | 1575194.16 | 5.010 | 3609501
5660 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA |  | 05 | 3701525 | This Ouachita Parish project on Caples Road will replace the existing deficient timber bridge over Longs Creek with a new concrete bridge. | Bridge Replacement | 2009-07-31 | 2009-07-31 | 2010-02-07 |  | 577623.46 |  | 3701525
5661 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA |  | 05 | 3701526 | This Ouachita Parish project on Sam Head Road will replace the existing deficient timber bridge over Bogaloosa Creek with a new concrete bridge. | Bridge Replacement | 2009-09-08 | 2009-10-10 | 2010-01-08 | 2010-06-23 | 326869.34 |  | 3701526
5662 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3707516 | The scope of the project is to patch the concrete pavement from the junction of LA 143 and LA 34 to the junction of LA 143 and US 80 and the junction of LA 143 and US 80 to the junction of LA 143 and LA 616 | Pavement Improvement | 2010-11-22 | 2011-01-03 | 2011-04-04 | 2011-10-20 | 1977385.83 | 1.558 | 3707516
5663 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709503 | This Ouchita Parish project will widen Oliver Road from two lanes to three lanes and place new asphalt pavement, beginning at LA 840-6 to Tower Drive. The project will also fill a 7 foot deep ditch adjacent to Oliver Road. | Pavement Improvement | 2010-06-20 | 2010-07-20 | 2010-11-23 | 2010-03-14 | 1749886.62 | 0.000 | 3709503
5664 | LOUISIANA | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709504 | This work will repair and place new asphalt and striping along approximately 5.4 miles of the following streets in Ouachita Parish: Crosely St. - between Cypress and Black Bayou Canal. Downing Pines Rd. - between I-20 and Thomas Rd. North 7 th. St. | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2010-09-27 |  | 1959694.07 | 4.210 | 3709504
5665 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709505 | This project will reconstruct and place new asphalt on Good Hope Road from LA 616 (Arkansas Road) to T. John Road in Ouachita Parish. | Pavement Improvement | 2010-06-09 | 2010-06-10 | 2010-07-22 | 2011-11-02 | 737008.54 | 0.777 | 3709505
5666 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709506 | This project will place new asphalt of Dellwood Drive in the town of Richwood (Ouachita Parish) from US 165 to Blackwood Drive. | Pavement Improvement | 2010-08-11 | 2010-08-11 | 2010-09-29 | 2011-11-02 | 462291.29 | 0.538 | 3709506
5667 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709507 | This project will place new ashpalt on Louisiana Avenue in Ouachita Parish from Wallace Dean Road to Wallace Road. | Pavement Improvement | 2010-06-09 | 2010-06-09 | 2010-07-21 | 2011-11-02 | 238835.18 | 0.250 | 3709507
5668 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709508 | This project in Ouachita Parish will place new asphalt pavement on Vancil Road from LA 838 to US 80. | Pavement Improvement | 2010-06-09 | 2010-06-14 | 2010-07-26 | 2011-11-02 | 769710.27 | 1.184 | 3709508
5669 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709509 | This project will plalce new asphalt on Hadley Street in Ouachita Parish from Nutland Road to approximately 0.5 miles west. | Pavement Improvement | 2010-08-11 | 2010-08-08 | 2010-09-05 | 2011-11-02 | 417792.24 | 0.482 | 3709509
5670 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709512 | Riverside Dr. (Park Ave. to Louisville Ave.) - Repair roadway and place new asphalt from Bres St. to Louisville. Washington St.- (Walnut to North 14 th St.) Remove deteriorated concrete and replace with new concrete. | Pavement Improvement | 2010-07-09 | 2010-08-08 | 2010-10-17 | 2010-10-19 | 683497.16 | 0.880 | 3709512
5671 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | OUACHITA | MONROE | 05 | 3709513 | The City of Monroe will place new asphalt on approximately 1.4 miles of Riverside Drive from Park Avenue to Louisiville in Ouachita Parish. | Pavement Improvement | 2010-07-09 | 2010-08-18 | 2010-09-15 | 2010-09-29 | 652679.95 | 0.001 | 3709513
5672 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | PLAQUEMINES | NEW ORLEANS | 03 | 3809500 | This project will widen the roadway and place new asphalt along portions of Woodland Hwy (LA 406) in Plaquemines Parish. | Pavement Widening | 2010-06-01 | 2010-07-06 | 2010-08-24 | 2011-10-21 | 1190336.45 | 1.858 | 3809500
5673 | LOUISIANA | Underway | C950 | Ferryboat | LOUISIANA | STATEWIDE |  |  | 3809504 | This project will replace the Plaquemine Parish Ferry boat engines with energy efficient and alternative fuel engines. These engines will improve emissions from the ferry. | Other | 2011-10-10 | 2011-10-12 | 2012-04-09 |  | 1936097.25 |  | 3809504
5674 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | RAPIDES | ALEXANDRIA | 05 | 4003530 | This project will construct sidewalks in the Town of Woodworth along Castor Plunge Road from Mason Rue Drive to Langston Drive, US 165 from Castor Plunge Road to a point approximately 1700' south of C | Transportation Enhancements | 2010-06-12 | 2010-06-24 | 2010-08-19 | 2010-11-08 | 262448.67 | 0.200 | 4003530
5675 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | RAPIDES | ALEXANDRIA | 05 | 4007507 | The scope of the project is to remove 6 in of the asphalt pavement and overlay the travelway with 6 inches of asphaltic concrete from the junction of US 167 and the southern junction of LA 3225 to the junction of US 167 and the northern junction of LA 322 | Other | 2010-10-28 | 2011-04-11 | 2011-10-10 | 2012-06-05 | 1064598.29 | 4.187 | 4007507
5676 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | RAPIDES | ALEXANDRIA | 05 | 4008508 | This project will remove and upgrade with new impacts attenuator in four sites in Alexandria, LA. The locations of the sites are I-49 (2 sites), US 167 (1 site)), and US 71 (1 site). | Safety/Traffic Management | 2010-05-10 | 2010-06-09 | 2010-07-28 | 2010-07-27 | 308975.34 | 0.000 | 4008508
5677 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | 4409500 | This St. Bernard Parish project will improve drainage on LA 46 near Fortification Canal and ends at Paris Road. | Pavement Improvement | 2010-08-08 | 2010-10-13 | 2011-03-09 | 2012-03-02 | 2235726.96 | 1.250 | 4409500
5678 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST CHARLES | NEW ORLEANS | 03 | 4502500 | This project will construct a bike and walking path on the St. Charles Parish West Bank Mississippi River levee between Davis Drive in Luling to Elm Street in Hahnville. | Transportation Enhancements | 2009-09-08 | 2009-10-08 | 2009-12-10 | 2010-10-12 | 1759187.28 |  | 4502500
5679 | LOUISIANA | Completed | C240,C230 | Highway Infrastructure Investment Grant | LOUISIANA | ST CHARLES | NEW ORLEANS | 03 | 4508502 | This poject will place new asphalt along 1.4 miles of LA 3127 in Saint Charles Parish between Log mile 9.7 and Interstate 310 in St. Charles Parish. | Pavement Improvement | 2010-01-25 | 2010-02-24 | 2010-04-07 | 2010-04-14 | 861400.98 | 1.210 | 4508502
5680 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST MARTIN |  | 03 | 5003501 | This St. Martin Parish project in the City of Breaux Bridge on Refinery Road will replace the existing deficient timber bridge over Bayou Teche with a new concrete bridge. | Bridge Replacement | 2009-06-15 | 2009-06-15 | 2010-03-15 |  | 1970496.09 |  | 5003501
5681 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5204526 | This project will construct sidewalks in the Town of Abita Springs along LA 435 (Main Street) from Hickory Street to Pine Street, Level Street from LA 36 to Magnolia Street and along the old railroad | Transportation Enhancements | 2010-08-06 | 2010-08-31 | 2010-12-14 | 2011-11-02 | 238941.19 | 0.343 | 5204526
5682 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5204528 | This St. Tammany Parish project will improve access at the LA 59 and Interstate 12 interchange by providing new turn lanes on LA 59 and widening of the ramp onto I-12. | Pavement Improvement | 2009-08-22 | 2009-11-02 | 2010-03-22 | 2010-08-16 | 2792816.87 | 0.530 | 5204528
5683 | LOUISIANA | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5207509 | This project will construct of a new two-lane roadway along I-10 between US190B and LA 433 in Slidell. | New Construction | 2010-12-07 | 2010-12-10 | 2011-12-30 |  | 3175428.1 | 1.015 | 5207509
5684 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5208511 | This project located in the City of Covington, LA in St. Tammany Parish involve milling and overlaying the asphalt section of the roadway and cleaning and sealing the joints and cracks in the concrete roadway of 1.595 miles of U.S. 190 Business. | Pavement Improvement | 2010-05-14 | 2010-06-08 | 2010-08-03 | 2010-10-08 | 784342.25 | 1.595 | 5208511
5685 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209503 | This St. Tammany Parish project located near Pearl River will widen the existing I-59 exit and entrance ramps and portions of LA 1090 at I-59. The project will provide additional turn lanes at the exit ramps, and left turn lanes on LA 1090. | Pavement Improvement | 2009-09-08 | 2009-09-17 | 2009-10-29 | 2010-12-16 | 1360168.24 | 0.440 | 5209503
5686 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5209504 | This St. Tammany Parish project will improve traffic operations by constructing turn lanes and widening ramps at the US 11/I-12 interchange in Slidell, LA. | Pavement Improvement | 2009-09-25 | 2009-10-26 | 2010-06-13 |  | 5486782.65 | 1.430 | 5209504
5687 | LOUISIANA | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5209505 | This St. Tammany Parish project is located in Covington and will construct an additional left turn lane for Northbound US 190 traffic turning onto westbound Park Drive. | Pavement Widening | 2010-07-06 | 2010-07-06 | 2011-05-12 |  | 402363.6 | 0.380 | 5209505
5688 | LOUISIANA | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209506 | This St. Tammansy Parish project located in Slidell will construct a right turn lane from LA 1090 on to Brownswitch Road. | Pavement Improvement | 2010-06-24 | 2010-06-24 | 2011-05-23 |  | 817013.29 | 0.194 | 5209506
5689 | LOUISIANA | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209507 | This St. Tammany Parish project located in Slidell will convert the existing intersection of LA 1091 and Brownswitch Road into a traffic roundabout. | Pavement Widening | 2010-06-24 | 2010-06-24 | 2011-01-07 |  | 1260101.2 | 0.110 | 5209507
5690 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5209508 | This project is located in the Covington/ Madisonville area of St. Tammany Parish. The project will construct additional left and right turn lanes at LA 21 and Brewster Road. | Pavement Widening | 2010-07-26 | 2010-07-26 | 2010-11-08 | 2011-10-14 | 1575045.82 | 0.000 | 5209508
5691 | LOUISIANA | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209509 | This St. Tammany Parish project is located in Slidell and includes widening LA 433 to provide additional right turn lanes onto I-10 and Voters Road. | Pavement Widening | 2010-07-06 | 2010-08-09 | 2011-08-03 |  | 1824168.37 |  | 5209509
5692 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | MANDEVILLE-COVINGTON | 01 | 5209511 | This St. Tammany Parish project is located near Covington and includes new pavement and turn lanes at the I-12/ LA 21 interchange. | Pavement Widening | 2010-07-26 | 2010-07-26 | 2011-02-11 | 2011-10-14 | 5096119.07 | 0.680 | 5209511
5693 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209528 | This project in Slidell, LA in St. Tammany Parish will overlay LA 433 from 3.4 Mi South of US 190 to 1.06 Mi North US 11. This project is joint with federal project number ERP1(149)(150)(151) & ARR-5209(529). | Pavement Improvement | 2010-07-13 | 2010-08-12 | 2010-12-30 | 2011-08-01 | 1916541.4 | 6.460 | 5209528
5694 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | ST TAMMANY | SLIDELL | 01 | 5209529 | This project in Slidell, LA in St. Tammany Parish will overlay LA 1090 from 0.15 Mi North of US 190 to the I-59 Ramps. This project is joint with federal project number ERP1(149)(150)(151) & ARR-5209(528). | Pavement Improvement | 2010-07-13 | 2010-08-12 | 2010-12-30 | 2011-08-01 | 991470.86 | 4.300 | 5209529
5695 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | TANGIPAHOA |  | 01 | 5302508 | The Tangipahoa Parish project in the City of Hammond on J.W. Davis Road will replace the existing deficient timber bridge over a canal with a concrete bridge. | Bridge Replacement | 2009-06-29 | 2009-06-29 | 2010-03-10 |  | 1110196.58 |  | 5302508
5696 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | TANGIPAHOA |  | 01 | 5302509 | This Tangipahoa Parish project on Little Italy Road will replace the existing deficient timber bridge over a creek with a concrete bridge. | Bridge Replacement | 2009-06-29 | 2009-08-17 | 2010-02-08 | 2010-02-03 | 509169.94 |  | 5302509
5697 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | TANGIPAHOA |  | 01 | 5302510 | This project in Tangipahoa Parish on Bennett Road will replace the existing deficient concrete bridge over Natalbany Creek with a new concrete bridge. | Bridge Replacement | 2009-07-09 | 2009-07-09 | 2010-01-04 |  | 661884.18 |  | 5302510
5698 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | TANGIPAHOA |  | 01 | 5302511 | This project in Tangipahoa Parish on Cooper Road will replace the existing deficient timber bridge over Cooper Creek with a new concrete bridge. | Bridge Replacement | 2009-07-13 | 2009-07-28 | 2009-12-05 | 2010-01-28 | 473240.56 |  | 5302511
5699 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | TERREBONNE | HOUMA | 03 | 5509505 | This Terrebonne Parish project will repair and place new asphalte along approximately 5.4 miles of the following streets: Alma Street, Country Drive, Klondyke Road, Southdown Mandalay Road, Westside Boulevard. | Pavement Improvement | 2010-06-04 | 2010-07-08 | 2010-08-26 | 2010-08-30 | 965547.61 | 4.510 | 5509505
5700 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | TERREBONNE | HOUMA | 03 | 5509506 | This project in Terrebonne Parish will repair and replace 7.3 miles of existing concrete pavement on the following roads: Acadian Avenue , Alma Street , Bayou Gardens Blvd., Corporate Drive, and Dunn Street. | Pavement Improvement | 2010-07-28 | 2010-08-27 | 2010-12-24 | 2011-08-03 | 1695458.33 | 0.001 | 5509506
5701 | LOUISIANA | Underway | C200 | Highway Infrastructure Investment Grant | LOUISIANA | TERREBONNE | HOUMA | 03 | 5509507 | This project in Terrebonne Parish will construct turn lanes at the following 10 intersections: Bayou Gardens at West Park, Corporate Dr. at MLK Blvd., Corporate Dr. at West Tunnel Blvd., Coteau Rd. at West Park, Country Estate at Coteau Rd., Polk St. at H | Pavement Improvement | 2010-06-02 | 2010-06-02 | 2011-02-24 |  | 1084116.71 | 0.001 | 5509507
5702 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | TERREBONNE | HOUMA | 03 | 5510501 | This project in Terrebonne Parish will repair and replace 4.2 miles of existing concrete pavement on various roads in Terrebonne parish. | Pavement Improvement | 2010-10-15 | 2010-11-15 | 2011-04-11 | 2011-05-02 | 1628084.53 | 0.010 | 5510501
5703 | LOUISIANA | Underway | C230 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | 6033009 | This Orleans Parish project consists of reconstructing and widening of Earhart Boulevard from Hamilton St to Fern St. | Pavement Improvement | 2009-11-11 | 2010-01-04 | 2012-10-07 |  | 12622195.91 |  | 6033009
5704 | LOUISIANA | Completed | C230 | Highway Infrastructure Investment Grant | LOUISIANA | WEST BATON ROUGE | BATON ROUGE | 06 | 6109503 | In West Baton Rouge Parish, a ramp will be added to the LA 1 northbound acceleeration lane at Emily Drive. | Pavement Widening | 2010-04-20 | 2010-04-26 | 2010-06-07 | 2010-09-30 | 382928.79 | 0.240 | 6109503
5705 | LOUISIANA | Underway | C240 | Highway Infrastructure Investment Grant | LOUISIANA | WEST CARROLL |  | 05 | 6204500 | This West Carroll Parish project on Lingo Loop Road will replace the existing deficient timber bridge over Mill Bayou with a new concrete bridge. | Bridge Replacement | 2009-08-05 | 2009-08-05 | 2010-03-06 |  | 400743.18 | 0.157 | 6204500
5706 | LOUISIANA | Completed | C240 | Highway Infrastructure Investment Grant | LOUISIANA | WEST CARROLL |  | 05 | 6204501 | This West Carroll Parish project on Wood Road will ieplace the existing deficient timber bridge over Alligator Bayou with a new concrete bridge. | Bridge Replacement | 2009-09-02 | 2009-10-12 | 2010-02-04 | 2010-05-19 | 385020.95 | 0.000 | 6204501
5707 | LOUISIANA | Completed | C200 | Highway Infrastructure Investment Grant | LOUISIANA | RAPIDES | ALEXANDRIA | 05 | 7869002 | Susek Drive is an existing two lane roadway in the northeast portion of Pineville, Louisiana in Rapides Parish. 2.2 miles of the roadway is to be reconstructed to two 12 foot lanes with curbs. The pro | Pavement Improvement | 2009-09-14 | 2009-10-14 | 2010-11-18 | 2011-02-25 | 9508463.65 | 0.151 | 7869002
5708 | LOUISIANA | Underway | C950 | Ferryboat | LOUISIANA | STATEWIDE |  |  | 9909525 | This Iberville Parish project will replace the existing landing barge of the Plaquemine/Sunshine Ferry winch system with a hydraulically actuated ramps to provide a more reliable operation. | Other | 2012-01-23 |  | 2012-05-28 |  | 615000 |  | 9909525
5709 | LOUISIANA | Completed | C240,C950 | Highway Infrastructure Investment Grant | LOUISIANA | STATEWIDE |  |  | 9909526 | This project will replace the existing navigational radar systems on both the Plaquemine/Sunshine Ferry and the St. Francisville/New Roads Ferry with a modern systems that will provide a safer operation. | Other | 2010-01-25 | 2010-01-25 | 2010-06-24 | 2010-09-30 | 300000 |  | 9909526
5710 | LOUISIANA | Completed | C950 | Ferryboat | LOUISIANA | STATEWIDE |  |  | 9909527 | This Iberville Parish project will replace the existing main engine reduction gears on the M/V Ascension and will provide improved vessel speed and reliability. | Other | 2010-03-15 | 2010-07-29 | 2010-09-09 | 2010-09-15 | 305832.75 |  | 9909527
5711 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1048 | This Orelans Parish project consists of removing deteriorated pavement and placing new asphalt and striping on Leon C Simon Dr from London Ave Canal to Elysian Fields Ave. in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 | 2012-05-24 | 95456.18 |  | ERP1048
5712 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1050 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Mirabeau Ave from St. Bernard Ave to Elysian Fields Ave. in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 | 2012-05-24 | 607341.22 |  | ERP1050
5713 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1051 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Filmore Ave from St. Bernard Ave to Elysian Fields Ave. in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 | 2012-05-24 | 662825 |  | ERP1051
5714 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1052 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on St. Bernard Ave from I-610 to Filmore Ave. in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 | 2012-05-24 | 531334.23 |  | ERP1052
5715 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1053 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Paris Ave from I-610 to Mirabeau Ave. in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 | 2012-05-24 | 560927.71 |  | ERP1053
5716 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1054 | This Orleans Parish project consists of project consists of removing deteriorated pavement and placing new asphalt and striping on Elysian Fields from Lakeshore Dr to US 90 in New Orleans. | Transportation Enhancements | 2009-11-20 | 2009-12-03 | 2011-04-18 | 2012-05-24 | 1003155.45 |  | ERP1054
5717 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1056 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Carrolton Avenue at I-10 and Claiborne Avenue (US 90) in the City of New Orleans. | Transportation Enhancements | 2010-01-08 | 2010-01-17 | 2010-06-16 | 2010-09-29 | 492080.83 |  | ERP1056
5718 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1057 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Carrolton Avenue at Claiborne (US 90) and St. Charles Avenues in the City of New Orleans. | Transportation Enhancements | 2010-01-08 | 2010-01-17 | 2010-06-16 | 2010-09-29 | 814802.06 |  | ERP1057
5719 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1063 | This Orleans Parish project will construct sidewalks on Nashville from Claiborne to Tchoupitoulas in New Orleans. | Transportation Enhancements | 2009-10-06 | 2009-11-09 | 2010-05-28 | 2010-12-04 | 974878 |  | ERP1063
5720 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1067 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Lasalle St. from Poydras St. to Tulane Ave. in New Orleans, LA. The project will overlay the street and add onstreet parking. | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 428346.32 |  | ERP1067
5721 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1068 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Gravier St. from Loyola Ave. to St. Peters St. in New Orleans, LA. | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 22036.72 |  | ERP1068
5722 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1069 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Common St. from Loyola Ave. to St. Peters St. in New Orleans, LA. The project will overlay the street and parking lane. | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 776930.93 |  | ERP1069
5723 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1071 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Magazine St. from Canal St. to US 90 Hwy. in New Orleans, LA. The project will overlay the street and parking lane. | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 270462.51 |  | ERP1071
5724 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1072 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Camp St.. from Canal St. to US 90 Hwy. in New Orleans, LA. The project will overlay the street and parking lane. | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 334956.83 |  | ERP1072
5725 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1075 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Loyola Ave. from Canal Street to US 90 Hwy. in New Orleans, LA. The project will overlay the street and parking lanes. | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 1607566.25 |  | ERP1075
5726 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ORLEANS | NEW ORLEANS | 02 | ERP1076 | This project will construct sidewalks, bike lanes, signs, striping and pavement markings on Poydras St. from Lasalle St. to Loyola Ave. in New Orleans, LA. The project will overlay the street. T | Transportation Enhancements | 2009-10-12 | 2009-11-03 | 2010-08-30 |  | 3772.32 |  | ERP1076
5727 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1084 | This project will provide for the construction of sidewalks on Mehle Avenue in the city of Arabi (St. Bernard Parish) from LA 46 to LA 39. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 103019.91 |  | ERP1084
5728 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1120 | This project will provide for the construction of sidewalks on Rowley Boulevard in the city of Arabi (St. Bernard Parish) from LA 46 to LA 39. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 164364.32 |  | ERP1120
5729 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1122 | This project will provide for the construction of sidewalks on Cougar Drive in the city of Arabi (St. Bernard Parish) from Benjamin Street to Genet Drive. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 238095.66 |  | ERP1122
5730 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1124 | This project will provide for the construction of sidewalks on East Genie Street in the city of Chalmette (St. Bernard Parish) from Golden Drive to Palmisano Boulevard. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 158820.61 |  | ERP1124
5731 | LOUISIANA | Underway | C220 | Highway Infrastructure Investment Grant | LOUISIANA | ST BERNARD | NEW ORLEANS | 03 | ERP1125 | This project will provide for the construction of sidewalks on Packenham Drive in the city of Chalmette ( St. Bernard Parish) from North Derbigny Street to West Genie Street. | Transportation Enhancements | 2010-02-01 | 2010-02-15 | 2010-07-13 |  | 125304.41 |  | ERP1125
5732 | LOUISIANA | Completed | C220 | Highway Infrastructure Investment Grant | LOUISIANA | STATEWIDE |  |  | LA03003 | This project will provide four informational kiosks in the towns of Vivian, Plain Dealing, Sarepta, and Homer in Caddo, Bossier, Webster, Claiborne Parishes. | Transportation Enhancements | 2009-08-18 | 2009-09-28 | 2010-06-07 | 2010-03-11 | 204285.98 | 0.001 | LA03003
5733 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1001700 | Lisbon, Sabattus, Rt 9. Reconstruction of 6.75 miles of Route 9 beginning 0.33 of a mile northerly of Route 196 and extending northeasterly 6.75 miles to the Maine Turnpike Overpass. Work involves grading, paving, drainage and guardrail improvements. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2011-07-31 | 2011-07-31 | 9564965.26 | 6.750 | 1001700
5734 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1015800 | Portland, Veranda Street Bridge, Replacement of Veranda Street Overpass Bridge over Canadian Railroad | Bridge Improvement | 2009-05-06 | 2009-05-06 | 2010-02-28 | 2010-02-28 | 1440783.72 | 0.000 | 1015800
5735 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | HANCOCK |  | 02 | 1107200 | Ellsworth, Route 1A. Reconstruction of 2.67 miles of Route 1A beginning at the Rabbit Road and extending southeasterly 2.67 miles to 0.15 of a mile northerly of the Old Bangor Road. Work includes grading, paving, drainage and guardrail improvements. | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2011-06-30 | 2011-06-30 | 6920925.54 | 2.670 | 1107200
5736 | MAINE | Completed | C220 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND | PORTLAND | 01 | 1184400 | Portland, Bayside Trail. This project will design an extension of the Portland Trails system through the Bayside area of Portland along the abandoned Union Branch Rail Line extending from the Eastern Promenade Trail near Tukey's Bridge to Preble Street. | Transportation Enhancements | 2009-08-11 | 2009-08-11 | 2009-09-30 | 2009-09-30 | 800000 |  | 1184400
5737 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | WALDO |  | 01 | 1267600 | Lincolnville, Knights Hill Culvert Replacement on Route 52 over Meservy Brook | Bridge Improvement | 2009-05-21 | 2009-05-21 | 2009-10-12 | 2009-10-12 | 250875.15 | 0.000 | 1267600
5738 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1273700 | Auburn, Joline Drive Intersection Improvement with a signal at the intersection of Center Street, Joline Street, and Stetson Street | Safety/Traffic Management | 2009-05-28 | 2009-05-28 | 2009-12-31 | 2009-12-31 | 567134.95 | 0.000 | 1273700
5739 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1277700 | Turner, Route 117. Reconstruction of 2.39 miles of Route 117 including grading, paving, drainage and guardrail improvements. | Pavement Improvement | 2009-07-22 | 2009-07-22 | 2009-09-20 | 2009-09-20 | 2625486.46 | 2.390 | 1277700
5740 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1305900 | Auburn, Joline Drive. Reconstruction of 0.18 of a mile beginning at Center Street and extending westerly to Turner Street. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-11-30 | 2009-11-30 | 375053.37 | 0.180 | 1305900
5741 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1306100 | Lewiston, Russell Street. Reconstruction of 0.51 miles beginning at the convergence of the ramps to Main Street, extending easterly to Robinson Gardens. This project will include construction of left-turn storage lanes to improve safety. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-11 | 2009-10-11 | 2319473.41 | 0.510 | 1306100
5742 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1308500 | Biddeford, Route 111. Highway resurfacing beginning at Main Street (Route 9) and extending westerly 0.97 of a mile to 0.10 of a mile easterly of Marshall Avenue. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 480144.37 | 0.970 | 1308500
5743 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1308600 | Biddeford, Route 9. Highway resurfacing beginning at Parkside and extending 0.95 of a mile to Alfred Street. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 402115.46 | 0.950 | 1308600
5744 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1310400 | Portland, Auburn Street. Intersection improvement with signal located at the intersection of Auburn Street and Lyseth Moore Drive. | Safety/Traffic Management | 2009-07-02 | 2009-07-02 | 2009-12-31 | 2009-12-31 | 249274.85 | 0.000 | 1310400
5745 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1311100 | Saco, North Street. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile northerly of Park Street and extending 1.00 mile to 0.34 of a mile southerly of Hillview Avenue. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 261078.23 | 1.000 | 1311100
5746 | MAINE | Completed | C220 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1334100 | Biddeford-Kennebunk, Eastern Trail, Construct a bicycle/pedestrian trail from Rt. 111 in Biddeford to Route 35 in Kennebunk. | Transportation Enhancements | 2009-09-14 | 2009-09-14 | 2010-07-31 | 2010-07-31 | 1466570.32 |  | 1334100
5747 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1480600 | Portland, Cumberland Avenue. Highway resurfacing beginning at Franklin Arterial and extending 0.29 of a mile to Elm Street. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-09-30 | 2009-09-30 | 135249.13 | 0.290 | 1480600
5748 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1480700 | Westbrook, Eisenhower Drive. Highway resurfacing beginning at Saco Street and extending 0.88 of a mile to Spring Street. Includes shoulder resurfacing. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-08-31 | 2009-08-31 | 571096.46 | 0.870 | 1480700
5749 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | YORK |  | 01 | 1480800 | Saco, Beach Street-Ferry Road. Pave a 3/4" hot mix asphalt overlay beginning at North Street and extending 1.11 miles to Pine Ridge Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 220068.84 | 1.110 | 1480800
5750 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1480900 | Falmouth, Brook Road. Pave a 1 1/4" hot mix asphalt overlay beginning at the Westbrook town line and extending 0.74 of a mile to the Leighton Road. The project will include drainage and the installation of curbing | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-08-31 | 2009-08-31 | 510643.74 | 0.480 | 1480900
5751 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1481100 | Portland, Westbrook Street. Pave a 1 1/4" hot mix asphalt overlay beginning at the Westbrook town line and extending 0.89 miles to Congress Street. Project includes alteration of 24 catch basins and replacement of approximately 1,000 feet of curbing. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-09-30 | 2009-06-16 | 270039.73 | 0.890 | 1481100
5752 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | SAGADAHOC |  | 01 | 1511450 | Interstate I-295 Northbound, Brunswick to Gardiner. This project involves reconstruction of the roadway including grinding and rubblizing the existing concrete roadway, grading and paving, drainage and safety improvements. | Pavement Improvement | 2009-03-03 | 2009-03-03 | 2009-10-10 | 2009-10-10 | 33454719.51 | 23.880 | 1511450
5753 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1511460 | Interstate I-295 Northbound, Topsham to Gardiner. This project involves building the crossovers from the northbound lanes to the southbound lanes as part of the traffic detour for the I-295 northbound reconstruction project. | Safety/Traffic Management | 2009-03-30 | 2009-03-30 | 2009-10-06 | 2009-10-06 | 1750713.75 |  | 1511460
5754 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | LINCOLN |  | 01 | 1561300 | Damariscotta, Salt Bay Steel Culvert Bridge Replacement over Oyster Creek, located on Belvedere Road at the Damariscotta-Nobleboro town line. | Bridge Replacement | 2009-05-29 | 2009-05-29 | 2009-10-08 | 2009-10-08 | 556041.3 | 0.000 | 1561300
5755 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1561400 | Hallowell, Second Street Bridge Rehabilitation over Maine Central Railroad. Replace existing deck and repair concrtete bridge abutments and retaining walls. | Bridge Replacement | 2009-05-05 | 2009-05-05 | 2010-03-30 | 2010-03-30 | 1141869.82 | 0.000 | 1561400
5756 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1562700 | Township 2 Region 8, Lincoln Spur Bridge Deck Replacement located over Interstate 95 northbound and southbound. Replace existing deck and install new safety barriers. | Bridge Improvement | 2009-04-24 | 2009-04-24 | 2009-10-11 | 2009-10-11 | 1381645.06 | 0.000 | 1562700
5757 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | HANCOCK |  | 02 | 1568900 | Sullivan, Route 1. Intersection Improvements including construction of a bypass lane located at the intersection of Route 1 and the Ashville Road. | Safety/Traffic Management | 2009-06-24 | 2009-06-24 | 2009-08-31 | 2009-08-31 | 333762.89 | 0.000 | 1568900
5758 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | OXFORD |  | 02 | 1571600 | Lovell, Main Street. Pave a 3/4" hot mix asphalt overlay beginning 0.82 of a mile north of Christian Hill Road and extending northerly 1.66 miles to 0.12 of a mile south of West Lovell Road. | Pavement Improvement | 2009-04-14 | 2009-04-14 | 2009-10-09 | 2009-10-09 | 314135.24 | 1.660 | 1571600
5759 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1571900 | Sebago, Sebago Road. Pave a 3/4" hot mix asphalt overlay beginning at Shore Road and extending northerly 0.90 miles to 0.17 of a mile northerly of Woodland Road. | Pavement Improvement | 2009-04-14 | 2009-04-14 | 2009-10-09 | 2009-10-09 | 256174.01 | 0.910 | 1571900
5760 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1572000 | Standish, Route 114. Pave a 3/4" hot mix asphalt overlay eginning 0.16 of a mile north of Route 35 and extending northerly 6.50 miles to 0.94 of a mile south of the Standish-Sebago town line. | Pavement Improvement | 2009-04-14 | 2009-04-14 | 2009-10-09 | 2009-10-09 | 1113743.39 | 6.500 | 1572000
5761 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1573700 | Clinton, Baker Street. Pave a 3/4" hot mix asphalt overlay beginning at Route 11 and extending northerly 1.16 miles. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-05 | 2009-10-05 | 412622.83 | 1.160 | 1573700
5762 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1573900 | Fairfield, Route 23. Pave a 3/4" hot mix asphalt overlay beginning at Route 201 and extending northerly 0.65 of a mile to 0.19 of a mile northerly of Pishon Ferry Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 109772.21 | 0.650 | 1573900
5763 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1574600 | Oakland, Fairfield Street. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile northerly of Greeley Street and extending northerly 0.85 of a mile to 0.30 of a mile northerly of Municipal Drive. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-06 | 2009-10-06 | 149679.76 | 0.850 | 1574600
5764 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1574700 | Oakland, Pleasant Street. Pave a 3/4" hot mix asphalt overlay beginning at Oak Street and extending easterly 0.37 of a mile to Route 11. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 84434 | 0.370 | 1574700
5765 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1575000 | Randolph, Route 9. Pave a 3/4" hot mix asphalt overlay beginning 0.05 of a mile westerly of the Chelsea-Randolph town line and extending easterly 3.67 miles to 0.10 of a mile easterly of the Augusta-Chelsea town line. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-05 | 2009-10-05 | 644358.28 | 3.590 | 1575000
5766 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1575700 | Waterville, Oak Street. Pave a 3/4" hot mix asphalt overlay beginning at Main Street and extending easterly 0.46 of a mile to College Avenue. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-05 | 2009-10-05 | 118203.23 | 0.460 | 1575700
5767 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | FRANKLIN |  | 02 | 1576500 | Eustis, Route 27. Pave a 3/4" hot mix asphalt overlay beginning 0.03 of a mile south of Route 16 and extending northerly 1.26 miles. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-09-30 | 2009-09-30 | 225493.06 | 1.260 | 1576500
5768 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1577000 | Jackman, Route 6. Pave a 3/4" hot mix asphalt overlay beginning 2.19 miles westerly of the Long Pond Twp town line and extending easterly 2.19 miles. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 606204.53 | 2.190 | 1577000
5769 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | PISCATAQUIS |  | 02 | 1577400 | Sapling Township., Rockwood Road. Pave a 3/4" hot mix asphalt overlay beginning 0.05 of a mile westerly of the Sapling Township-Big Moose Township town line and extending easterly 6.10 miles to 0.46 of a mile westerly of Ski Resort Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 1108456.26 | 6.100 | 1577400
5770 | MAINE | Completed | C250,C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1579000 | Palmyra, Ell Hill Road. Pave a 3/4" hot mix asphalt overlay beginning at Somerset Avenue and extending northerly 6.27 miles to 0.03 of a mile northerly of Ford Hill Road. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-10 | 2009-10-10 | 1200725.15 | 6.270 | 1579000
5771 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | AROOSTOOK |  | 02 | 1579700 | Caswell, Van Buren Road. Pave a 3/4" hot mix asphalt overlay beginning 0.29 of a mile southerly of the Hamlin town line and extending northerly 5.69 miles to 1.18 miles southerly of Albert Cyr Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-08 | 2009-10-08 | 1626515.89 | 5.620 | 1579700
5772 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1581400 | Auburn, Turner Street. Pave a 3/4" hot mix asphalt overlay beginning at Center Street and extending northerly 1.08 miles to 0.30 of a mile southerly of Mount Auburn Avenue. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-07-31 | 2009-07-31 | 441956.29 | 1.080 | 1581400
5773 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1583000 | Gardiner, Water Street. Pave a 3/4" hot mix asphalt overlay beginning at Cobbossee Avenue and extending easterly 1.10 miles to Route 201. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-09 | 2009-10-09 | 266094.14 | 1.100 | 1583000
5774 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1583100 | Litchfield, Route 9. Pave a 3/4" hot mix asphalt overlay beginning 0.17 of a mile westerly of the Huntington Hill Road and extending easterly 3.99 miles to 0.06 of a mile westerly of the Bog Hill Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-09 | 2009-10-09 | 710362.86 | 4.010 | 1583100
5775 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1583200 | Oakland, Route 11. Grind and remove 1 1/4" of existing pavement and replace with a 1 1/4" hot mix asphalt overlay beginning at Route 23 and extending northerly 4.46 miles to 0.01 of a mile northerly of Winter Street. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-11 | 2009-10-11 | 832344.31 | 4.460 | 1583200
5776 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | KENNEBEC |  | 01 | 1584000 | West Gardiner, Lewiston Road. Pave a 1 1/4" hot mix asphalt overlay beginning 0.42 of a mile westerly of the I-95 Exit 102 On-ramp and extending easterly 1.69 miles to 0.11 of a mile westerly of the West Gardiner-Gardiner town line. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-09 | 2009-10-09 | 694099.47 | 1.690 | 1584000
5777 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1584300 | Fairfield, Norridgewock Road. Grind and remove 1 1/4" of the existing pavement and replace with a 1 1/4" hot mix asphalt overlay beginning 1.87 miles west of Routes 104/139 and extending westerly 4.75 miles to 0.16 of a mile west of Bigelow Hill Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-07 | 2009-10-07 | 982929.08 | 4.750 | 1584300
5778 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | FRANKLIN |  | 02 | 1584900 | New Sharon, Route 27. Pave a 3/4" hot mix asphalt overlay beginning 0.38 of a mile southerly of York Hill Road and extending northerly 2.65 miles to Route 2. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-10 | 2009-10-10 | 503054.29 | 2.650 | 1584900
5779 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1585100 | Bangor, Broadway. Pave a 3/4" hot mix asphalt overlay beginning at the Interstate 95 southbound Exit 185 ramps and extending northerly 0.65 of a mile to Grandview Avenue. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-08 | 2009-10-08 | 195400.46 | 0.560 | 1585100
5780 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1585300 | Bangor, Hogan Road. Grind and remove 1 1/4" of existing asphalt and replace with a 1 1/4" of hot mix asphalt overlay beginning 0.10 miles southerly of the intersection of Mt. Hope and extending north | Pavement Improvement | 2009-07-08 | 2009-07-08 | 2009-08-31 | 2009-08-31 | 365424.16 | 1.240 | 1585300
5781 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | WASHINGTON |  | 02 | 1586200 | East Machias, Route 1. Pave a 3/4" hot mix asphalt overlay beginning 0.37 of a mile northerly of Chase Mills Road and extending northerly 1.00 mile to 0.47 of a mile northerly of the Whiting town line. | Pavement Improvement | 2009-07-21 | 2009-07-21 | 2010-06-30 | 2010-06-30 | 248400.68 | 1.000 | 1586200
5782 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1587500 | Pittsfield, Park Street. Grind and remove 1 1/4" of existing asphalt and replace with a 1 1/4" hot mix asphalt overlay beginning at North Main Street and extending northerly 0.19 of a mile to Somerset Avenue. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-10 | 2009-10-10 | 59466.89 | 0.190 | 1587500
5783 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1588200 | Auburn, Route 202. Pave a 3/4" hot mix asphalt overlay beginning at Minot Avenue and extending northerly 0.68 of a mile to Lisbon Street. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-07-31 | 2009-07-31 | 326182.83 | 0.680 | 1588200
5784 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | ANDROSCOGGIN |  | 02 | 1588500 | Auburn, Minot Avenue. Pave a 3/4" hot mix asphalt overlay beginning at High Street and extending northerly 0.51 of a mile to Court Street. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-07-31 | 2009-07-31 | 237075.93 | 0.510 | 1588500
5785 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1589100 | Interstate I-295 Southbound, Freeport. Work involves replacing culvert underneath I-295 Exit 22 on and off ramps. | Bridge Improvement | 2009-07-07 | 2009-07-07 | 2009-10-31 | 2009-10-31 | 157702.76 | 0.060 | 1589100
5786 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1590100 | Portland, Forest Avenue. Grind and remove 1 1/4" existing asphalt and replace with 1 1/4" hot mix asphalt beginning at Warren Avenue and extending northerly 1.15 miles to Castine Avenue. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-09-30 | 2009-09-30 | 622405.85 | 0.980 | 1590100
5787 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1590300 | Interstate I-295 Southbound, Portland. Paving 0.42 miles beginning 0.13 of a mile north of the Washington Avenue Southbound on-ramp. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-08-31 | 2009-08-31 | 78623.69 | 0.420 | 1590300
5788 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | LINCOLN |  | 01 | 1591800 | Edgecomb, Route 1. Pave a 3/4" hot mix asphalt overlay beginning 0.08 of a mile northerly of Eddy Road and extending northerly 1.02 miles to 0.05 of a mile northerly of Cochran Road. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-07 | 2009-10-07 | 468887.16 | 1.020 | 1591800
5789 | MAINE | Underway | C240 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1593200 | Caratunk, Route 201. Pave a 3/4" hot mix asphalt overlay beginning 3.74 miles southerly of the The Forks Plantation town line and extending northerly 3.77 miles. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 |  | 591821.06 | 3.770 | 1593200
5790 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | FRANKLIN |  | 02 | 1593300 | Farmington, Route 2. Grind and remove 1 1/4" of existing pavement and replace with 1 1/4" of hot mix as[halt beginning 500 feet west of the bridge to Prescott Street; Route 2/4/27 intersection to Hil | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2009-10-10 | 2009-10-10 | 524745.26 | 2.870 | 1593300
5791 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1593600 | Moose River, Route 201. Pave a 3/4" hot mix asphalt overlay beginning 0.26 of a mile northerly of Sandy Stream Road and extending northerly 13.65 miles to the Canadian border. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 2219537 | 13.650 | 1593600
5792 | MAINE | Completed | C250 | Highway Infrastructure Investment Grant | MAINE | SOMERSET |  | 02 | 1594100 | West Forks Plantation., Route 201. Pave a 3/4" hot mix asphalt overlay beginning 0.16 of a mile southerly of the Parlin Pond Township town line and extending northerly 13.62 miles to 2.60 miles northerly of the Parlin Pond Township-Jackman town line. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-10 | 2009-10-10 | 2181878.85 | 13.620 | 1594100
5793 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1594300 | Bangor, Broadway (Route 15). Pave a 3/4" hot mix asphalt overlay beginning 325' easterly of the I-95 northbound Exit 185 ramps and extending northerly 0.23 of a mile to the I-95 southbound Exit 185 ramps. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-08 | 2009-10-08 | 81914.56 | 0.230 | 1594300
5794 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1594800 | Hampden, Route 202. Pave a 3/4" hot mix asphalt overlay beginning at Western Avenue and extending northerly 4.02 miles to the Interstate 395 Exit 2 eastbound ramps. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2009-10-08 | 2009-10-08 | 853852.54 | 4.020 | 1594800
5795 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1595300 | Interstate I-95 Southbound, Mattamiscontis Township to Howland. 10.37 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-07 | 2009-10-07 | 4388130.22 | 10.370 | 1595300
5796 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1595400 | Interstate I-95 Southbound, Township 2 Region 8 NWP to Mattamiscontis Township. 7.06 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2009-10-06 | 2009-10-06 | 2486534.02 | 7.060 | 1595400
5797 | MAINE | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | MAINE | HANCOCK |  | 02 | 1669600 | Deer Isle-Sedgwick Bridge Substructure Rehabilitation over Eggemoggin Reach, located on the Deer Isle-Sedgwick town line. Repair bridge tower piers. | Bridge Improvement | 2009-09-16 | 2009-09-16 | 2010-10-31 | 2010-10-31 | 10238467.29 | 0.000 | 1669600
5798 | MAINE | Completed | C200 | Highway Infrastructure Investment Grant | MAINE | KNOX |  | 01 | 1674500 | South Thomaston, Spruce Head Bridge Replacement on Island Road. | Bridge Replacement | 2009-08-19 | 2009-08-19 | 2010-05-31 | 2010-05-31 | 2222968.88 | 0.000 | 1674500
5799 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1677500 | Interstate I-95 Southbound, Howland to Old Town. 15.6 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2010-10-07 | 2010-10-07 | 4428050.2 | 15.600 | 1677500
5800 | MAINE | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | MAINE | AROOSTOOK |  | 02 | 1681910 | Interstate I-95 Northbound - highway resurfacing beginning 2.86 miles north of the Oakfield/Smryna town line and extends northerly 13.64 miles to the Canadian border. | Pavement Improvement | 2010-02-04 | 2010-05-15 | 2010-10-31 | 2010-10-31 | 6493467.9 |  | 1681910
5801 | MAINE | Completed | C240 | Highway Infrastructure Investment Grant | MAINE | PENOBSCOT |  | 02 | 1682200 | Interstate I-95 Southbound, Township 2 Region 9 NWP to Township 2 Region 8 NWP. 8.22 miles of highway resurfacing involving paving, drainage, and guardrail improvements. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2010-10-07 | 2010-10-07 | 2424889.95 | 8.220 | 1682200
5802 | MAINE | Completed | C200,C240 | Highway Infrastructure Investment Grant | MAINE | WASHINGTON |  | 02 | 1698300 | Lubec, Route 189. Pave a 1-1/4" hot mix asphalt overlay beginning at the intersection of Route 1 and extending easterly approximately 6.7 miles. | Pavement Improvement | 2009-07-21 | 2009-07-21 | 2010-06-30 | 2010-06-30 | 3697666.25 | 11.190 | 1698300
5803 | MAINE | Completed | C220 | Highway Infrastructure Investment Grant | MAINE | CUMBERLAND |  | 01 | 1700800 | South Portland-Portland, Long Creek Watershed. Pavement treatment on Maine Mall Road designed to enhance treatment of stormwater runoff in an urban impaired stream watershed as recommended by the Long Creek Watershed Planning Initiative. | Other | 2009-06-29 | 2009-06-29 | 2009-12-31 | 2009-12-31 | 1655990.68 |  | 1700800
5804 | MAINE | Completed | C490 | OJT/SS | MAINE | STATEWIDE |  |  | 1736501 | On the Job Training/Support Services to fund apprenticeships and training centers for underrepresented or disadvantaged people pursuing careers in transportation, engineering or construction. | Other | 2010-04-28 | 2010-04-29 | 2010-09-30 | 2010-09-30 | 351408.62 |  | 1736501
5805 | MAINE | Underway | C950 | Ferryboat | MAINE | CUMBERLAND |  | 01 | 1745500 | Capital Equipment Purchase of a new ferry vessel that will be used by the Casco Bay Island Transit District. | Other | 2010-11-19 | 2009-11-20 | 2011-12-30 | 2013-06-30 | 4531000 |  | 1745500
5806 | MAINE | Completed | C950 | Ferryboat | MAINE | CUMBERLAND |  | 01 | 1745510 | Replacement of the fender systems for the CBITD piers. | Other | 2010-09-23 | 2011-09-21 | 2012-09-30 | 2012-09-30 | 450000 |  | 1745510
5807 | MAINE | Completed | C950 | Ferryboat | MAINE | WALDO |  | 01 | 1763400 | Rehabilitation of the Maine State Ferry Service's pier structure and the Islesboro and Lincolnville locations. | Other | 2009-11-19 | 2009-11-20 | 2011-12-30 | 2011-12-30 | 1725149.45 |  | 1763400
5808 | MAINE | Completed | C250,C200 | Highway Infrastructure Investment Grant | MAINE | PISCATAQUIS |  | 02 | A001000 | Dover-Foxcroft, Route 15. Reconstruction of 1.29 miles of Route 15 including drainage, paving, re-alignment of side roads, guardrail and safety improvements. | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2010-06-30 | 2010-06-30 | 2542213.02 | 1.290 | A001000
5809 | MARYLAND | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | TALBOT |  | 01 | 0003124 | Talcot County will be replacing the concrete box culvert and reconstructing the approach roadway on Dutchman's Lane. | Pavement Improvement | 2009-12-01 |  |  |  | 885000 |  | 0003124
5810 | MARYLAND | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 06 | 0003125 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This project is in Harford County. | Pavement Improvement | 2010-05-17 | 2010-05-17 |  |  | 908000 |  | 0003125
5811 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | QUEEN ANNES |  | 01 | 0003126 | Queen Anne's County will remove the existing pavement and resurface. They will also widen the roadway shoulders. This work will be done on Tanyard Road from MD 305 to Whitemarsh Road. | Safety/Traffic Management | 2010-02-20 |  |  |  | 715306 |  | 0003126
5812 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY | CUMBERLAND (WV) | 06 | 0003127 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This project is on Cash Valley Road in Allegheny County. | Pavement Improvement | 2009-09-17 |  |  |  | 691347 |  | 0003127
5813 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ST MARYS |  | 05 | 0003129 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This project is on Pe | Pavement Improvement | 2009-09-17 |  |  |  | 330150 |  | 0003129
5814 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 0003130 | This project willrepair Allegheny Highland Trail Bridge over New Hope Road in Allegheny County. | Bridge Improvement | 2009-09-17 |  |  |  | 130000 |  | 0003130
5815 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 0003132 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This project is on Ro | Pavement Improvement | 2009-09-18 |  |  |  | 399652 |  | 0003132
5816 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 0003134 | Maryland State Highway will be replacing the deteriorated Berwyn Creek concrete bridge deck with a new deck under their bridge system preseveration program. | Bridge Improvement | 2010-03-18 | 2010-03-18 |  |  | 671987 |  | 0003134
5817 | MARYLAND | Underway | C950 | Ferryboat | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 03 | 0003141 | Baltimore City will purchase two new ferry boats and rehabilitate the existing pier to accomodate these two new boats in the Inner Harbor area of Baltimore. | Other | 2010-06-04 |  |  |  | 1400000 |  | 0003141
5818 | MARYLAND | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 01 | 0003146 | Harford County will be constructing a roundabout at Wheel Road and Laurel Bush Road. In additon to the roundabout work on 500 feet of Wheel Road will be done which includes culvert replacement, retaining walls, storm drains, and erosion sediment control. | Safety/Traffic Management | 2010-02-05 |  |  |  | 780000 |  | 0003146
5819 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | QUEEN ANNES |  | 01 | 0003150 | Queen Anne's County will remove and resurface the existing pavement. They will also widen the shoulders of the roadway. This work will be on Carmichael Road from Arrington Road to Overlook Drive. | Safety/Traffic Management | 2010-02-02 |  |  |  | 203669 |  | 0003150
5820 | MARYLAND | Completed | C490 | OJT/SS | MARYLAND | STATEWIDE |  |  | 0003169 | Various Trainings in order to retrain individuals for other new skills in needed Highway related work positions | Other | 2011-04-11 | 2011-04-11 | 2011-09-30 | 2011-09-30 | 240000 |  | 0003169
5821 | MARYLAND | Underway | C950 | Ferryboat | MARYLAND | BALTIMORE CITY |  | 07 | 0003180 | Purchase/Lease Right of Way for Ferry Boat Project at Inner Harbor in Downtown Baltimore | Other | 2010-08-18 | 2010-08-18 | 2035-08-18 |  | 190000 |  | 0003180
5822 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ANNE ARUNDEL |  | 01 | 000A368 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-06-22 | 2009-09-29 | 2011-11-01 |  | 4612024 |  | 000A368
5823 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | CALVERT |  | 05 | 000A369 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be performed at various locations in Calvert County. | Pavement Improvement | 2009-05-05 | 2009-05-14 | 2011-11-01 |  | 5117038 |  | 000A369
5824 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 000A370 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be performed at various locations in Charles County. | Pavement Improvement | 2009-04-29 | 2009-05-20 | 2011-11-01 |  | 4612050 |  | 000A370
5825 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ST MARYS |  | 05 | 000A371 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be performed at various locations in St. MAry's County. | Pavement Improvement | 2009-05-20 | 2009-06-11 | 2011-12-01 |  | 6140665 |  | 000A371
5826 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ANNE ARUNDEL |  | 05 | 000A373 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-07-16 | 2009-10-15 | 2011-12-01 |  | 6938533 |  | 000A373
5827 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A375 | This is a signalization project. Signals and Reconstructs in District 3. This contract is required for routine capital signal improvement efforts in District 3. | Safety/Traffic Management | 2009-08-20 | 2009-09-30 |  |  | 5251090 |  | 000A375
5828 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CECIL |  | 01 | 000A379 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be performed at various locations in Cecil County. | Pavement Improvement | 2009-06-09 | 2009-09-20 | 2011-12-01 |  | 3408022 |  | 000A379
5829 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | KENT |  | 01 | 000A380 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be performed at various locations in Kent County. | Pavement Improvement | 2009-05-20 | 2009-06-15 | 2011-11-01 |  | 2306012 |  | 000A380
5830 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | QUEEN ANNES |  | 01 | 000A381 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be performed at various locations in Queen Anne's County. | Pavement Improvement | 2009-05-20 | 2009-06-09 | 2011-12-01 |  | 3828006 |  | 000A381
5831 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | TALBOT |  | 01 | 000A382 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be performed at various locations in Talbot County. | Pavement Improvement | 2009-05-05 | 2009-06-10 | 2011-11-01 |  | 2288019 |  | 000A382
5832 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A385 | This project will improve interstate lighting and enhance safety at various interchanges. | Safety/Traffic Management | 2010-01-16 | 2010-02-26 |  |  | 7691200 |  | 000A385
5833 | MARYLAND | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A386 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Dorchester, Somerset, Wicomico, and Worcester Coun | Transportation Enhancements | 2009-06-24 | 2009-10-05 | 2012-06-01 |  | 4088800 |  | 000A386
5834 | MARYLAND | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A387 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Montgomery and Prince George’s Counties. This work | Transportation Enhancements | 2009-06-16 | 2009-07-22 | 2012-07-01 |  | 3612818 |  | 000A387
5835 | MARYLAND | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A388 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Baltimore and Harford Counties. This work will add | Transportation Enhancements | 2009-06-23 | 2009-08-11 | 2011-06-01 |  | 2623097 |  | 000A388
5836 | MARYLAND | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A389 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Anne Arundel, Calvert, Charles, and St. Mary’s Cou | Transportation Enhancements | 2009-07-14 | 2009-08-03 | 2011-06-01 |  | 1904467 |  | 000A389
5837 | MARYLAND | Underway | C220,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A390 | This work is for placement and/or removal and replacement of concrete sidewalk; concrete curb and combination curb and gutter at various locations in Carroll, Frederick, and Howard Counties. This work | Transportation Enhancements | 2009-07-16 | 2009-07-27 | 2011-06-01 |  | 1987656 |  | 000A390
5838 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | DORCHESTER |  | 01 | 000A395 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. Various locations in Dorchester County will be improved. | Pavement Improvement | 2009-03-11 | 2009-03-30 | 2010-12-01 |  | 2903015 |  | 000A395
5839 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | SOMERSET |  | 01 | 000A396 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Somerset County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-03-11 | 2009-03-30 | 2010-12-01 |  | 3106037 |  | 000A396
5840 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | WICOMICO |  | 01 | 000A397 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Wicomico County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-04-08 | 2009-06-28 | 2010-12-01 |  | 3623001 |  | 000A397
5841 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | WORCESTER |  | 01 | 000A398 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Worcester County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-03-11 | 2009-05-10 | 2010-12-01 |  | 3606058 |  | 000A398
5842 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A400 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Dorchester, Somerset, Wicomico, and Worcester Counties. The work may als | Safety/Traffic Management | 2009-06-09 | 2009-12-16 | 2011-12-01 |  | 379808 |  | 000A400
5843 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A401 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Caroline, Cecil, Kent, Queen Anne’s and Talbot Counties. The work may al | Safety/Traffic Management | 2009-06-09 |  | 2012-01-01 |  | 299042 |  | 000A401
5844 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A402 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Montgomery County and Prince George’s Counties. The work may also includ | Safety/Traffic Management | 2009-06-03 |  | 2011-12-01 |  | 468485 |  | 000A402
5845 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A403 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Baltimore and Harford Counties. The work may also include installation o | Safety/Traffic Management | 2009-05-20 | 2009-12-01 | 2012-01-01 |  | 441541 |  | 000A403
5846 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A404 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Anne Arundel, Calvert, Charles, and St Mary’s Counties Counties. The wor | Safety/Traffic Management | 2009-05-20 | 2009-06-08 | 2011-12-01 |  | 597345 |  | 000A404
5847 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A405 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them at various locations in Carroll, Frederick, and Howard Counties. The work may also include instal | Safety/Traffic Management | 2009-05-21 | 2009-09-14 | 2012-01-01 |  | 580636 |  | 000A405
5848 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 000A406 | This project involves resurfacing and pavement preservation of various locations in Allegheny County. The project will improve ride and improve deterirating sections of the highway. Work will be dodne by Maryland State Highway. | Pavement Improvement | 2009-06-09 | 2009-07-17 | 2012-01-30 |  | 3471080 |  | 000A406
5849 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE |  | 02 | 000A407 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be perfromed at various locations in Baltimore County. | Pavement Improvement | 2009-10-07 |  |  |  | 5112046 |  | 000A407
5850 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE |  | 03 | 000A408 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-10-07 | 2010-03-23 |  |  | 5412023 |  | 000A408
5851 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | CARROLL |  | 06 | 000A409 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be perfromed at various locations in Carroll County. | Pavement Improvement | 2009-05-18 | 2009-07-06 | 2011-12-01 |  | 2958005 |  | 000A409
5852 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 02 | 000A410 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be perfromed at various locations in Harford County. | Pavement Improvement | 2009-06-09 | 2009-08-05 | 2011-12-01 |  | 6612006 |  | 000A410
5853 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 08 | 000A411 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-20 | 2009-06-15 | 2011-12-01 |  | 8476015 |  | 000A411
5854 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 000A412 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-27 | 2009-07-16 | 2011-12-01 |  | 8677714 |  | 000A412
5855 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES |  | 04 | 000A413 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-06-15 | 2009-10-09 | 2011-12-01 |  | 8166050 |  | 000A413
5856 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 000A414 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be pe | Pavement Improvement | 2009-05-20 | 2009-06-29 | 2011-12-01 |  | 7640063 |  | 000A414
5857 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | WASHINGTON |  | 06 | 000A415 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be perfromed at various locations in Washington County. | Pavement Improvement | 2009-05-20 | 2009-07-17 | 2011-12-01 |  | 3078053 |  | 000A415
5858 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 000A416 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be perfromed at various locations in Frederick County. | Pavement Improvement | 2009-05-21 | 2009-06-29 | 2011-12-01 |  | 7026051 |  | 000A416
5859 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 000A417 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be perfromed at various locations in Garrett County. | Pavement Improvement | 2009-06-09 | 2009-08-03 | 2011-12-01 |  | 2623007 |  | 000A417
5860 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | HOWARD |  | 07 | 000A418 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. At some locations, i | Pavement Improvement | 2009-05-18 | 2009-07-26 | 2011-12-01 |  | 6372010 |  | 000A418
5861 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A419 | This project will repair concrete pavement and curb at Truck Weigh/Inspection Stations due to severely cracked roadway surface. Project will also improve geometric and drainage. This is a statewide project. | Pavement Improvement | 2009-06-09 | 2009-07-28 | 2012-07-01 |  | 844595 |  | 000A419
5862 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 000A420 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. This work will be performed at various locations in Caroline County. | Pavement Improvement | 2009-06-09 | 2009-06-22 | 2011-12-01 |  | 2516042 |  | 000A420
5863 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 000A421 | Maryland State Highway will clean and paint ten bridges in Prince George's County as part of its bridge system preservation program. This project will extend the life of the existing bridges. | Bridge Improvement | 2009-03-11 | 2009-05-18 | 2010-06-01 |  | 1789806 |  | 000A421
5864 | MARYLAND | Completed | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | Multiple | 000A422 | Cleaning and painting bridges for longer service life on US 1, MD201, MD202, MD212 and MD500 | Bridge Improvement | 2009-03-30 | 2009-05-11 | 2010-05-01 | 2009-12-03 | 1742046 |  | 000A422
5865 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A423 | This project will improve safety for the travelling public. Maryland State Highway will rehabilitate existing substandard traffic barrier at various locations in Baltimore and Harford Counties. InB | Safety/Traffic Management | 2009-06-10 | 2009-07-13 | 2011-01-01 | 2010-02-02 | 729530 |  | 000A423
5866 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A424 | Maryland State Highway will upgrade guard rails at various locations in Anne Arundel, Calvert, Charles and St. Mary's Counties. This project will will improve safety for the travelling public. In An | Safety/Traffic Management | 2009-06-15 | 2009-06-29 | 2011-01-01 | 2010-03-16 | 823241 |  | 000A424
5867 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A425 | This project will improve safety for motorists by upgrading existing guardrails at various locations in Garrett, Washington, Carroll, Frederick and Howard Counties. | Safety/Traffic Management | 2009-06-09 | 2009-08-24 | 2011-01-01 |  | 1904760 |  | 000A425
5868 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A426 | This project will improve safety for motorists by upgrading existing guardrails at various locations in Montgomery and prince George's Counties. | Safety/Traffic Management | 2009-06-15 | 2009-08-17 | 2011-01-01 | 2010-06-29 | 852738 |  | 000A426
5869 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A427 | This project will install and upgrade signing at various locations. This project will improve safety of motorist. | Safety/Traffic Management | 2009-03-16 | 2009-07-01 | 2012-04-01 |  | 5677537 |  | 000A427
5870 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A428 | Maryland State Highway will install new median traffic barrier and rehabilitate non-compliance traffic barrier on approximately 17 mile section of US50 in Dorchester, Somerset, Wicomico and Worcester | Safety/Traffic Management | 2009-06-15 | 2010-01-04 | 2011-01-01 |  | 1530969 |  | 000A428
5871 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A429 | Maryland State Highway will rehabilitate existing substandard traffic barrier at various locations in Cecil (along 17 miles of US40), Queen Anne's (along 15.5 miles of US50) and Talbot (along 21 miles | Safety/Traffic Management | 2009-07-13 | 2009-07-27 | 2011-01-01 |  | 2283767 |  | 000A429
5872 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A430 | This contract will provide for upgrades to camera video detection for the traffic control timing of the different phases of operation. It will install traffic detection at signalized intersections in SHA districts 1,2,4 and 5. | Safety/Traffic Management | 2009-06-16 | 2009-06-30 | 2011-07-01 |  | 1824752 |  | 000A430
5873 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A431 | This project is for dynamic message signs deployment to ncrease CHART's (Maryland State's traffic operation's center) information dissemmation capibilities. | Safety/Traffic Management | 2009-07-28 | 2010-04-07 | 2012-08-01 |  | 3410470 |  | 000A431
5874 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A432 | This project will install battery backups and other signal improvements throughout the state districts. | Safety/Traffic Management | 2009-10-21 | 2010-03-17 | 2011-08-31 |  | 5370992 |  | 000A432
5875 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A433 | This contract will provide for upgrades to camera video detection for the traffic control timing of the different phases of operation. | Safety/Traffic Management | 2009-06-25 | 2009-07-13 | 2011-08-01 |  | 1672809 |  | 000A433
5876 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A434 | This project will install battery backups and other signal improvements throughout the state districts. | Safety/Traffic Management | 2009-08-13 | 2009-09-07 | 2011-09-01 |  | 5141587 |  | 000A434
5877 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A443 | This project will install containerized trees and seedlings at various locations including, but not limited to 34 sites throughout Baltimore, | Transportation Enhancements | 2009-07-13 | 2009-09-10 | 2011-09-30 |  | 367839 |  | 000A443
5878 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A445 | This project will install sign lighting system at various locations to improve safety for motorists. | Safety/Traffic Management | 2009-08-25 | 2009-09-02 | 2011-09-01 |  | 2443595 |  | 000A445
5879 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A446 | This project will install and establish trees at various locations in Anne Arundel, Calvert, Charles and Saint Mary Counties. This work involves the removal of dead or invasive species, as well as, | Transportation Enhancements | 2009-12-23 |  |  |  | 245907 |  | 000A446
5880 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A447 | This project will plant trees and bare root seedlings at various locations including, but not limited to 25 sites throughout Caroline, Dorchester, Kent, Queen Anne’s, Talbot, Wicomico and Worcester Counties. | Transportation Enhancements | 2009-10-07 | 2009-11-09 | 2011-09-01 |  | 251958 |  | 000A447
5881 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A448 | This project will install and establish reforestation trees and shrubs at various locations throughout Prince Georges's and Montgomary Counties. Project will remove dead or invasive plants and install Beaver Protection Tree Shelter at specified locations. | Transportation Enhancements | 2009-08-05 | 2009-09-29 | 2010-08-01 |  | 221260 |  | 000A448
5882 | MARYLAND | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK | FREDERICK | 06 | 000A452 | This project, located in Frederick County, is for vegetation management, invasive species removal, and installation, care, and establishment of reforestation and landscape plantings in the interchange of IS-70 and IS-270. | Transportation Enhancements | 2009-08-05 | 2010-01-07 | 2011-08-01 |  | 496980 | 0.280 | 000A452
5883 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | HOWARD |  | 07 | 000A455 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Howard County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2010-04-22 | 2010-04-22 |  |  | 2993000 |  | 000A455
5884 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE | BALTIMORE,MD | 02 | 000A481 | This project involves traffic signal reconstruction in Baltimore County at MD7, MD157 and MD7. | Safety/Traffic Management | 2009-10-14 | 2009-10-28 | 2011-11-30 |  | 1720765 |  | 000A481
5885 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | ANNE ARUNDEL | BALTIMORE,MD | 02 | 000A486 | This project involves traffic signal reconstruction in Anne Arundel County at MD 2 and MD210. | Safety/Traffic Management | 2009-11-25 | 2010-01-04 | 2011-12-31 |  | 1621285 |  | 000A486
5886 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CALVERT |  | 05 | 000A487 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. The project is for re | Pavement Improvement | 2009-09-11 |  |  |  | 1343000 |  | 000A487
5887 | MARYLAND | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 06 | 000A488 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Harford County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-12-22 | 2010-05-17 |  |  | 1464000 |  | 000A488
5888 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | QUEEN ANNES |  | 01 | 000A490 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them or install new guard rails at various locations in Queen Anne's County. This project wil limprove safety for motorists. | Safety/Traffic Management | 2009-09-17 |  |  |  | 194025 |  | 000A490
5889 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES |  | Multiple | 000A491 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Prince George's County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-17 |  |  |  | 3870485 |  | 000A491
5890 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES |  | Multiple | 000A492 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Prince George's County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-17 |  |  |  | 3526515 |  | 000A492
5891 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 000A494 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Frederick County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2010-04-12 | 2010-04-12 |  | 2009-08-01 | 2406346 |  | 000A494
5892 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 000A495 | This project involves cleaning and painting bridges in Frederick County for longer service life. | Bridge Improvement | 2009-09-17 |  |  |  | 492148 |  | 000A495
5893 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CARROLL |  | 06 | 000A497 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Carroll County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-17 |  |  |  | 2715000 |  | 000A497
5894 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | WASHINGTON |  | 06 | 000A499 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Washington County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-03 | 2010-04-27 |  |  | 2303000 |  | 000A499
5895 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | SOMERSET |  | 01 | 000A500 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Somerset County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2010-04-05 | 2010-04-05 |  |  | 642000 |  | 000A500
5896 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 000A502 | This Baltimore City Citywide project will furnish all the labor and materials needed for the reconstruction of various traffic signals at existing intersections throughout the City. | Safety/Traffic Management | 2010-09-07 |  |  |  | 3878542 |  | 000A502
5897 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | WORCESTER |  | 01 | 000A503 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Worcester County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-17 |  |  |  | 1319000 |  | 000A503
5898 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ANNE ARUNDEL | BALTIMORE,MD | Multiple | 000A504 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Anne Arundel County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-17 |  |  |  | 6043000 |  | 000A504
5899 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE |  | Multiple | 000A505 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Baltimore County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-17 | 2010-04-28 |  |  | 8129000 |  | 000A505
5900 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 000A507 | This project will install Signs in Various Locations in Caroline County to improve safety. | Safety/Traffic Management | 2009-09-17 |  |  |  | 136419 |  | 000A507
5901 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 000A508 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Garrett County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-17 |  |  |  | 1204000 |  | 000A508
5902 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | DORCHESTER |  | 01 | 000A509 | This project will install pavement markings at various locations in Dorchester County to improve safety. | Safety/Traffic Management | 2009-09-18 |  |  |  | 47762 |  | 000A509
5903 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | DORCHESTER |  | 01 | 000A510 | Maryland State Highway will resurface at various locations in Dorchester County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Widening | 2009-09-17 |  |  |  | 1015238 |  | 000A510
5904 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | CECIL | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 000A511 | Maryland State Highway will resurface at various locations in Cecil County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2010-05-17 |  |  |  | 1504000 |  | 000A511
5905 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 000A512 | This project will install pavement markings at various locations in Caroline County to improve safety. | Safety/Traffic Management | 2009-09-17 |  |  |  | 192691 |  | 000A512
5906 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 000A514 | Maryland State Highway will resurface at various locations in Charles County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-18 |  |  |  | 1228000 |  | 000A514
5907 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY |  | Multiple | 000A515 | Maryland State Highway will either replace guardrails not meeting the current standards or repair them or install new guardrails at various locations in MOntgomery County. This project will improve safety for motorist. | Safety/Traffic Management | 2009-09-17 |  |  |  | 248220 |  | 000A515
5908 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY |  | Multiple | 000A516 | This project wil upgrade traffic signals at various locations in Montgomery County. This project will improve safety for motorists. | Safety/Traffic Management | 2009-09-17 |  |  |  | 441981 |  | 000A516
5909 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY |  | Multiple | 000A517 | This project wil install traffic signs at various locations in Montgomery County. This project will improve safety for motorists. | Safety/Traffic Management | 2009-09-17 |  |  |  | 236104 |  | 000A517
5910 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | Multiple | 000A518 | Maryland State Highway will resurface at various locations in Montgomery County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-17 |  |  |  | 6744000 |  | 000A518
5911 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A520 | Maryland State Highway through our Maryland Transit Authority will be replacing eight existing railroad crossings at various locations throughout the State. | Safety/Traffic Management | 2009-12-31 | 2010-01-11 | 2010-08-01 | 2011-03-31 | 524715 |  | 000A520
5912 | MARYLAND | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 000A522 | This project wil install ADA Sidewalks at various locations in the Town of La Plata and address ADA non-compliance elements along Charles County's roadway system. | Safety/Traffic Management | 2009-09-07 |  |  |  | 96425 |  | 000A522
5913 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | WICOMICO |  | 01 | 000A523 | Maryland State Highway will resurface at various locations in Wicomico County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-21 |  |  |  | 1795000 |  | 000A523
5914 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | KENT |  | 01 | 000A524 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer at various locations in Kent County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-09-21 |  |  |  | 540000 |  | 000A524
5915 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 000A525 | Town of Indian Head will be replacing existing sidewalks and upgrading to meet ADA compliance. The town is working through Charles County in the use of the County's ARRA funds. | Safety/Traffic Management | 2009-10-15 |  |  |  | 42963 |  | 000A525
5916 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 000A526 | This project will clean and paint 12 bridges on various routes in Anne Arndel, Calvert, Charles, and St Mary's Counties. These processes will extend the life of the structures. | Bridge Improvement | 2010-01-21 |  |  |  | 1800277 |  | 000A526
5917 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 000A529 | Maryland State Highway will mill, resurface, line stripe, and install guardrail on I-95/I495 from MD 5 to South of D'Arcy Road and MD 4 to South of Old Marlboro Road. | Pavement Improvement | 2010-04-20 |  |  |  | 4105745 |  | 000A529
5918 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 000A537 | Baltimore City will be milling and resurfacing various routes within the city limits. They will also be replacing curb and gutter, sidewalks, and pedestrian ramps. New pavement markings and striping | Pavement Improvement | 2016-08-16 |  |  |  | 2465406 |  | 000A537
5919 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 000A539 | Baltimore City will be installing updated street and pedestrian lightings with minor curb and sidewalk replacement work done where necessary. | Safety/Traffic Management | 2010-09-07 |  |  |  | 786651 |  | 000A539
5920 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 0682033 | Maryland State Highway will perfrom patching and install a new layer that will enhance pavement life and provide smoother surface. In addition, the project will enhance safety by upgrading guradrails | Pavement Improvement | 2009-06-08 | 2009-07-07 | 2009-12-01 | 2009-11-10 | 3208302 | 3.420 | 0682033
5921 | MARYLAND | Completed | C250,C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 0682034 | Maryland State Highway will Maryland State Highway will either replace guardrails not meeting the current standards or repair them or install new guardrails as needed. This project will improve safety for motorists. | Safety/Traffic Management | 2009-04-20 | 2009-05-11 | 2009-12-01 | 2009-07-10 | 1251301 | 9.400 | 0682034
5922 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 0682035 | Maryland State Highway will replace existing substandard weatherized traffic barrier along the roadside and median with galvanized traffic barrier on 17 mile section of Interstate 68 (from west of Hil | Safety/Traffic Management | 2009-07-07 | 2009-08-10 | 2011-01-01 | 2010-06-14 | 3474459 | 17.000 | 0682035
5923 | MARYLAND | Completed | C200 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 0682036 | This project will establish turfgrass in selected bare and eroded areas on MD 36 to Garrett County Line. | Transportation Enhancements | 2009-08-25 | 2009-09-14 | 2009-11-30 | 2009-10-30 | 344651 | 3.230 | 0682036
5924 | MARYLAND | Completed | C200 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 0703055 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. In addition, the proj | Pavement Improvement | 2009-06-15 | 2009-08-12 | 2009-10-01 | 2009-11-13 | 3550530 | 6.860 | 0703055
5925 | MARYLAND | Completed | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE |  | 03 | 0832214 | Maryland State Highway will improve sections of Interstate 83 (from MOunt Carmel Road to PA State line) and associated ramps in Baltimore County by removing few inches of existing roadway and adding | Pavement Improvement | 2009-06-24 | 2009-07-13 | 2010-08-01 | 2009-12-01 | 3734298 | 2.800 | 0832214
5926 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 0952267 | This project includes work to remove invasive species and install reforestation and landscape plantings along roadsides and within median and quadrant sections of the US 50 / I-495/95 Interchange, loc | Transportation Enhancements | 2009-08-13 | 2009-10-22 | 2011-10-01 |  | 638968 |  | 0952267
5927 | MARYLAND | Underway | C220 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 0953182 | Lanscaping using invasive plant control and native plant establishment on I-95 from I-495 to MD212 and from MD109 to MD100. Invasive plant species will be removed and native meadow plants will be planted in its place. | Transportation Enhancements | 2009-04-29 | 2009-05-11 | 2011-06-01 |  | 414357 |  | 0953182
5928 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 1015005 | This project in Allegheny County will widen the roadway to a minium 18' width, perfrom surface overlay, construct two retaining walls to minimize grading impacts, and complete drainage improvements on | Pavement Improvement | 2010-02-16 | 2010-04-01 |  |  | 3057478 |  | 1015005
5929 | MARYLAND | Completed | C200 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 1016006 | Maryland State Highway will resurface at various locations in Allegany County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Improvement | 2009-07-23 | 2009-08-24 | 2010-02-01 | 2009-11-17 | 752460 | 0.790 | 1016006
5930 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 1051025 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. The project is locate | Pavement Improvement | 2009-06-09 | 2009-07-27 | 2009-11-01 | 2009-10-09 | 2386657 | 10.200 | 1051025
5931 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 1074009 | This project will improve roadway characterstics (geometrics improvements) in Frederick County at Fingerboard Rd and Ijamsville Rd/Big Woods Rd toimprove safety. | Pavement Improvement | 2009-04-23 | 2009-07-24 | 2010-03-01 |  | 1768873 | 0.300 | 1074009
5932 | MARYLAND | Completed | C230 | Highway Infrastructure Investment Grant | MARYLAND | HOWARD | BALTIMORE,MD | 07 | 1091062 | Maryland State Highway will resurface in Howard County that will enhance pavement life and provide smoother surface. Limited roadway widening may be perfromed as needed. | Pavement Improvement | 2009-08-14 | 2009-09-09 | 2010-05-01 | 2010-03-19 | 2352421 | 2.630 | 1091062
5933 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 1194004 | This a bridge replacement project in Prince George's County. | Bridge Replacement | 2009-10-07 | 2010-06-25 | 2010-12-31 |  | 1461126 |  | 1194004
5934 | MARYLAND | Underway | C250,C240 | Highway Infrastructure Investment Grant | MARYLAND | ST MARYS |  | 05 | 1216001 | Saint Mary's County will replace the existing hydraulically and structurally inadequate culverts, (4) with aluminum box culverts, with greater hydraulic capacity culverts on the Mechanicsville Road over the Chaptico Creek. | Bridge Improvement | 2009-09-17 |  |  |  | 1165850 |  | 1216001
5935 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 07 | 1251034 | Baltimore City will resurface Orleans Street from Central Avenue to Wolfe Street for pavement preservation. This project will include updating sidewalks, traffic barriers, storm drains, and roadway l | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2010-07-01 |  | 7082521 |  | 1251034
5936 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CECIL | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 1251044 | Maryland State Highway is correcting inadequate drainage then resurfacing and restriping the roadway on the southern approach to Big Elk Creek. | Pavement Improvement | 2010-02-18 |  |  |  | 403459 |  | 1251044
5937 | MARYLAND | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD | ABERDEEN-HAVRE DE GRACE-BEL AIR | 02 | 1257001 | Maryland State Highway will mill and resurface the existing roadway, repair existing drainage, upgrade the existing traffic barrier and end treatments, and then restripe the roadway on MD 462 from MD 132 to bridge over Carsins Run. | Pavement Improvement | 2010-01-12 | 2010-07-08 |  |  | 610784 |  | 1257001
5938 | MARYLAND | Completed | C250 | Highway Infrastructure Investment Grant | MARYLAND | CECIL |  | 01 | 1266003 | This project, located in Cecil County, is for the construction of a 121’ x 77’ expansion of the ride sharing facility at MD 222 and Blythedale Road.This carpool lot in Cecil County has reached 85% cap | Pavement Widening | 2009-06-22 | 2009-07-13 | 2009-12-01 | 2009-12-11 | 330214 | 0.000 | 1266003
5939 | MARYLAND | Underway | C220 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE |  |  | 1271048 | This project will eradicate or control invasive plants on US 301 in Queen Anne's, Kent and Cecil Counties from US50/301 split to the Delaware line. Native meadow plants will be planted in place of in | Transportation Enhancements | 2009-06-15 | 2009-07-16 | 2011-07-01 |  | 115953 |  | 1271048
5940 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | DORCHESTER |  | 01 | 1301141 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with the new layer that will enhance pavement life and provide smoother surface. This project is | Pavement Improvement | 2009-06-15 | 2009-09-09 | 2009-10-01 | 2009-11-13 | 1048512 | 4.490 | 1301141
5941 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | TALBOT |  | 01 | 1301142 | Maryland State Highway will improve sections of US 50 (from MD 662B to MD 309) in Talbot County by removing few inches of existing roadway and adding a new pavement layer that will wear longer and min | Pavement Improvement | 2009-07-06 | 2009-07-20 | 2010-08-01 | 2009-12-11 | 2507804 | 4.090 | 1301142
5942 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 1311003 | This project will reconstruct 5th Avenue from Market Street to .89 miles South in Town of Denton in Caroline County. This project will enhance pavement life and improve ride. | Pavement Widening | 2009-09-17 |  |  |  | 631890 |  | 1311003
5943 | MARYLAND | Completed | C250,C240 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 2011027 | Maryland State Highway will remove existing layer of the deteriorated pavement surface and replace it with new layer that will enhance pavement life and provide smoother surface. In addition, the pr | Pavement Improvement | 2009-06-15 | 2009-08-17 | 2010-03-01 | 2009-11-16 | 1066347 | 1.580 | 2011027
5944 | MARYLAND | Completed | C250 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 2011028 | This project will resurface US219 from .15 Miles North of MD 42 to Bumble Bee Rd to enhance roadway life and improve ride. | Pavement Improvement | 2009-03-11 | 2009-03-25 | 2009-10-01 | 2009-07-28 | 1581985 | 2.170 | 2011028
5945 | MARYLAND | Completed | C250,C240 | Highway Infrastructure Investment Grant | MARYLAND | GARRETT |  | 06 | 2061022 | Maryland State Highway will resurface MD135 from Chestnut Grove Road to Lee Road in Garrett County that will enhance pavement life and provide smoother surface. | Pavement Improvement | 2009-04-01 | 2009-05-09 | 2010-02-01 | 2009-10-07 | 1858550 | 3.260 | 2061022
5946 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY |  | 06 | 2111011 | Maryland State Highway and West Virgina DOT are working on this project together with West Virginia being the lead state. Maryland State Highway portion of this project is to provide a new lift stati | Other | 2009-11-03 |  |  |  | 750000 |  | 2111011
5947 | MARYLAND | Completed | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | WASHINGTON |  | 06 | 2211014 | This project will add a right turn lane on MD65 at MD63 (lower vertical crest) to facilitate traffic movement and improve safety. | Pavement Improvement | 2009-09-03 | 2009-09-29 | 2010-06-30 | 2010-06-18 | 769980 | 0.150 | 2211014
5948 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY |  | 08 | 2331009 | This project will install street lighting on MD 124 - Air Park Road and Rosewood Manor Lane to imprve safety. | Other | 2009-09-17 |  |  |  | 819695 |  | 2331009
5949 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | CARROLL |  | 06 | 2341039 | Maryland State Highway is doing this project in Carroll County. It is a geometric improvement project that involves the construction of separate left turn and deceleration lanes, traffic signal upgrades and resurfacing on MD 26 at Klee Mill Road. | Pavement Improvement | 2009-10-07 | 2009-10-20 | 2010-06-30 | 2010-06-15 | 1438087 |  | 2341039
5950 | MARYLAND | Completed | C200 | Highway Infrastructure Investment Grant | MARYLAND | CARROLL |  | 06 | 2371018 | Ramp widening (geometric improvement) at MD27 at MD140 ramps. This project will improve safety. | Pavement Improvement | 2009-09-11 | 2009-09-28 | 2010-06-30 | 2010-06-08 | 740740 | 0.230 | 2371018
5951 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 2451032 | MD 410 to wayne Avenue - Traffic Signal Reconstruction for safety. | Safety/Traffic Management | 2009-12-23 | 2010-01-11 |  |  | 1103573 |  | 2451032
5952 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 2491025 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD650 from Milestone Drive to Venice Drive to enhance roadway life and smoothness. | Pavement Improvement | 2009-03-03 | 2009-03-16 | 2010-02-01 |  | 2149158 | 1.170 | 2491025
5953 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | STATEWIDE | WASHINGTON (DC-MD-VA) |  | 2491026 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD650 from MD410 to Holton Lane to enhance roadway life and smoothness. | Pavement Improvement | 2009-09-29 | 2009-11-18 |  |  | 1444164 | 0.830 | 2491026
5954 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 2491027 | Maryland State Highway will widen and resurface MD 650 from the DC line to MD 140 to enhance the pavement life, provide higher degree of safety, and provide smoother ride surface. | Pavement Improvement | 2010-03-18 | 2010-04-19 |  |  | 1893497 |  | 2491027
5955 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 2511062 | Maryland State will perfrom patching, removal of surface (as needed) and resurface US 1 from MD410 to Albion Road to enhance roadway life, safety and smoothness. | Pavement Improvement | 2010-03-02 | 2010-04-30 | 2010-06-30 |  | 839177 | 0.520 | 2511062
5956 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 2541010 | Maryland State will perfrom patching, removal of surface (as needed) and resurface MD214 from Cindy lane to Brightseat Road to enhance roadway life, safety and smoothness. | Pavement Improvement | 2009-06-24 | 2009-09-29 | 2010-08-01 |  | 1925417 | 1.980 | 2541010
5957 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | FREDERICK |  | 06 | 2707175 | Maryland State will perfrom patching, removal of surface (as needed) and resurface Northbound I270 from Structure 1007901 Bennett Creek to Structure 1007801 MD 80 to enhance roadway life, safety and smoothness. | Pavement Improvement | 2009-03-26 | 2009-05-11 | 2009-09-01 | 2009-08-01 | 895503 | 1.260 | 2707175
5958 | MARYLAND | Completed | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 3001044 | Change Order added to exisiting ongoing | Bridge Improvement | 2010-08-31 | 2010-08-31 | 2012-02-28 | 2012-01-31 | 3022193 |  | 3001044
5959 | MARYLAND | Completed | C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 3001045 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 2009-06-09 | 2009-06-23 | 2010-01-01 | 2010-05-11 | 918268 | 2.470 | 3001045
5960 | MARYLAND | Underway | C200,C240 | Highway Infrastructure Investment Grant | MARYLAND | CAROLINE |  | 01 | 3001046 | Maryland State Highway will widen 1.3 mile section of MD 404 in Caroline County. The project will add two westbound lanes, aa 34 foot median and will reconstruct existing lanes. Project will add lef | Pavement Widening | 2009-09-09 | 2009-09-28 |  |  | 2437935 | 1.320 | 3001046
5961 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 07 | 3009010 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Hilton Street from Frederick Avenue to Mulberry Street to enhance roadway life and smoothness. | Pavement Improvement | 2009-07-15 | 2009-07-13 | 2009-12-01 |  | 1092705 |  | 3009010
5962 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 07 | 3019006 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Park Heights Avenue from NorthernPArkway to Garrison Bulevard to enhance roadway life and smoothness. | Pavement Improvement | 2009-10-15 | 2009-10-05 |  |  | 1619916 |  | 3019006
5963 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 3200001 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Frankford Avenue from Sinclair Lane to Moravia Park Drive to enhance roadway life and smoothness. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-12-01 |  | 1051681 |  | 3200001
5964 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | 02 | 3206005 | Baltimore City will rehabilitate (make it to last longer) Argonne Drive Bridge. | Bridge Improvement | 2010-01-10 | 2010-02-15 |  |  | 6528294 |  | 3206005
5965 | MARYLAND | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | WORCESTER |  | 01 | 3311012 | Maryland State Highway will resurface MD 528 from 9th Street to 28th Street in Ocean City to eenhance the pavement life and provide smoother ride surface. | Pavement Improvement | 2010-04-02 | 2010-04-22 |  |  | 832716 |  | 3311012
5966 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE CITY | BALTIMORE,MD | Multiple | 3341002 | Baltimore City will remove existing layer of the deteriorated pavement surface and replace it with new layer on Northern Parkway from Falls Road to Park Heights Avenue to enhance roadway life and smoothness. | Pavement Improvement | 2009-06-22 | 2009-07-15 | 2010-05-01 |  | 7572091 |  | 3341002
5967 | MARYLAND | Underway | C200 | Highway Infrastructure Investment Grant | MARYLAND | HARFORD |  | 01 | 3631001 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 2009-06-22 | 2009-07-28 | 2009-12-01 |  | 1340539 | 2.140 | 3631001
5968 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 08 | 4952276 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In ad | Pavement Improvement | 2009-07-16 | 2009-08-03 | 2010-06-01 |  | 7609004 | 3.920 | 4952276
5969 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 5008021 | This project will add second left turn lane on Southbound MD410 at MD 500 to facilitate traffic movement and reduce congestions and enhance safety. | Pavement Improvement | 2010-01-08 | 2010-02-01 |  |  | 1120639 | 0.500 | 5008021
5970 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 5008022 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. This p | Pavement Improvement | 2009-10-14 | 2010-03-09 | 2010-03-31 |  | 1921697 | 1.120 | 5008022
5971 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 5010013 | Maryland State Highway is doing this project in Montgomery County. It is a geometric improvement that will extend left tun lanes on MD 28, as well as add another turning lane on MD 28. The project i | Pavement Improvement | 2009-10-14 | 2009-12-07 | 2010-09-30 |  | 1066445 |  | 5010013
5972 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 04 | 5018026 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 2009-06-09 | 2009-07-16 | 2011-12-01 |  | 3434916 | 1.760 | 5018026
5973 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 5019021 | MAryland State Highway will be replacing the deteriorating concrete bridge decks on MD 201 ND and MD 201 SB with new decks as part of its bridge system preservation program. | Bridge Improvement | 2010-02-22 | 2010-03-15 |  |  | 5878653 |  | 5019021
5974 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | MONTGOMERY | WASHINGTON (DC-MD-VA) | 06 | 5035004 | Maryland State Highway will remove existing layer of the deteriorated pavement surface (as necessary) and replace it with new layer that will enhance pavement life and provide smoother surface. In a | Pavement Improvement | 2009-08-11 | 2009-10-11 | 2010-03-01 |  | 1865847 | 1.540 | 5035004
5975 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | Multiple | 5067010 | This project will replace existing deteriorating pavement surface ( MD 212, Riggs Road from Washington D.C. line to Sargent Road) in Prince George's County with new pavement surface. It will also mak | Pavement Improvement | 2009-10-23 | 2009-11-06 | 2010-09-30 |  | 1835894 | 0.930 | 5067010
5976 | MARYLAND | Underway | C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 05 | 5067011 | This project will improve safety at MD212 at Allview Drive/Evans Trail by making Geometric improvements. | Pavement Improvement | 2009-09-22 | 2009-11-02 |  |  | 1250441 |  | 5067011
5977 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | PRINCE GEORGES | WASHINGTON (DC-MD-VA) | 04 | 5096001 | Maryland State Highway will replace the deteriorating concrete bridge deck on Forestville Raod over I-95 with a new deck as part of its bridge sytem preservation program. | Bridge Improvement | 2010-05-05 | 2010-06-17 |  |  | 1720857 |  | 5096001
5978 | MARYLAND | Underway | C240,C230 | Highway Infrastructure Investment Grant | MARYLAND | BALTIMORE | BALTIMORE,MD | 07 | 6956346 | Maryland State Highway will replace the deteriorated bridge at I-695 over MD 26 (Liberty Road) with a new one as part of its bridge system preservation program. | Bridge Replacement | 2010-02-08 | 2010-04-01 |  |  | 21788103 |  | 6956346
5979 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | ALLEGANY | CUMBERLAND (WV) | 06 | 7509004 | Maryland State Highway Will reconstruct Maryland Avenue from Jefferson Street to Short Street in Allegany County. | Pavement Improvement | 2009-09-17 | 2009-11-15 |  |  | 562653 |  | 7509004
5980 | MARYLAND | Underway | C240 | Highway Infrastructure Investment Grant | MARYLAND | CHARLES |  | 05 | 8502004 | This project will improve safety on Smallwood Drive Westbound at McDaniel Road in Charles County by making geometric improvements. | Pavement Improvement | 2009-09-18 |  |  |  | 180960 |  | 8502004
5981 | MASSACHUSETTS | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | STATEWIDE | Multiple | 001S899 | The project includes the construction of a new interchange (Exit 8 1/2) on Route 24 in Freetown and construction of new access roadways east to the proposed Fall River Executive Park and west to South | Pavement Improvement | 2009-11-30 | 2009-11-30 |  |  | 32686850 |  | 001S899
5982 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | PLYMOUTH | TAUNTON | 09 | 001S917 | This project will resurface Route 18/28 from Bridgewater Center to the Middleborough Rotary (intersection of Route 44) and make drainage improvements. | Pavement Improvement | 2009-04-23 | 2009-04-23 |  | 2010-07-17 | 2516982.17 |  | 001S917
5983 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 001S918 | The project will begin at the Adams/Cheshire town boundary (MM 66.3) and will end just north of Commonwealth Avenue (MM 67.8) for a project length of approximately 1.5 miles. MassHighway will resurfac | Pavement Improvement | 2009-04-23 | 2009-04-23 |  | 2010-08-26 | 1993215.1 | 1.500 | 001S918
5984 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BARNSTABLE | HYANNIS | 10 | 001S919 | This project will resurface Route 6 (Scenic Highway) from the intersection with Nightingale Pond Road to just east of the intersection with Bourndale Road in the Town of Bourne. | Pavement Improvement | 2009-04-23 | 2009-04-23 |  | 2009-12-03 | 1201414.11 | 2.410 | 001S919
5985 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | NEW BEDFORD | 04 | 001S920 | Resurface Route 6 from west of the Dartmouth town line (milemarker 20.9±) to the Fall River city line (milemarker 16.3±), a distance of approximately 4.6 miles. | Pavement Improvement | 2009-04-30 | 2009-04-30 |  | 2010-10-08 | 4038977.22 | 4.650 | 001S920
5986 | MASSACHUSETTS | Completed | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 001S921 | In the Town of Barre, this project will resurface Route 122 and a section of Rte 62. The state highway section of the project begins just west of Pleasant Street (milemarker 48.265) and proceeds weste | Pavement Improvement | 2009-05-14 | 2009-05-22 | 2009-11-04 | 2010-05-31 | 1761644.82 |  | 001S921
5987 | MASSACHUSETTS | Completed | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BARNSTABLE | HYANNIS | 10 | 001S922 | In Barnstable: Perform resurfacing and related work on the state-owned sections of Route 6A, from milemarker 8.12 to milemarker 16.56, a distance of approximately 8.5 miles. Also included in the proj | Pavement Improvement | 2009-07-02 | 2009-07-02 |  | 2010-11-17 | 2749456.14 | 8.430 | 001S922
5988 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX |  | 07 | 001S923 | This project will resurface a section of Route 2 in Lincoln. Work includes guardrail, painting and signage. | Pavement Improvement | 2009-05-14 | 2009-05-14 |  | 2009-10-16 | 1348853.49 | 3.050 | 001S923
5989 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 001S924 | This project will resurface Route 2 in Concord from Walden to the Sudbury town line and from Nine Acre Corner road to Elm Street. Work includes guardrail, painting and signage. | Pavement Improvement | 2009-05-07 | 2009-05-07 |  | 2010-10-29 | 3735036.83 | 1.050 | 001S924
5990 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 03 | 001S925 | Mill and resurface Route 6 in Swansea from the Somerset town line to the Rehoboth town line. Work on this project also includes the repair of frost heaves and the reconstruction of existing sidewalks. | Pavement Improvement | 2009-04-23 | 2009-04-23 |  | 2010-06-18 | 3258844.55 | 5.500 | 001S925
5991 | MASSACHUSETTS | Completed | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BARNSTABLE | HYANNIS | 10 | 001S926 | Mill and resurface Route 6A in Dennis from the Yarmouth Town Line to the Brewster Town Line, a distance of approximately 4.3 miles. | Pavement Improvement | 2009-06-25 | 2009-06-25 |  | 2010-05-30 | 1331843.51 | 4.280 | 001S926
5992 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK |  | 09 | 001S927 | This is a Pavement Preservation Project for Route 24 in Avon and Stoughton. | Pavement Improvement | 2009-07-31 | 2009-07-31 |  |  | 4804043.47 | 4.000 | 001S927
5993 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 07 | 001S931 | Replace traffic and guide signs on Interstate 95 (Route 128) between US 3 (Exit 32) in Lexington and I-93 (Exit 37) in Reading, including applicable signage on intersecting roadways. | Safety/Traffic Management | 2009-04-23 | 2009-04-23 | 2011-04-23 | 2011-04-23 | 3052820.26 |  | 001S931
5994 | MASSACHUSETTS | Completed | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 001S932 | Mill and resurface Route 32 (Main Street) from the Ware/New Braintree town line (milemarker 22.383) to just past the New Braintree/Hardwick town line (milemarker 23.38), a distance of approximately 1 | Pavement Improvement | 2009-05-14 | 2009-05-14 |  | 2009-11-30 | 518065.21 | 0.940 | 001S932
5995 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | FRANKLIN | FITCHBURG-LEOMINSTER | 01 | 001S933 | In Gill and Wendell: Work under this project will consist of milling the existing paved surface and repaving with 2" of HMA modified top course material. Work will also include repairs/upgrades to gua | Pavement Improvement | 2009-04-30 | 2009-04-30 |  | 2010-07-31 | 2559522.66 |  | 001S933
5996 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | Multiple | 001S934 | This project takes place in a number of locations between Westfield and Easthampton. The project will consist of milling the existing paved surface of Route 5 & 10 and repaving with 2" of HMA modified | Pavement Improvement | 2009-05-21 | 2009-05-21 |  | 2010-09-30 | 3322780.37 |  | 001S934
5997 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 03 | 001S935 | This project will commence at Route 140 in Shrewsbury and continue in a westerly direction to Massasoit Road in Worcester, a distance of approximately 3.5 miles. | Pavement Improvement | 2009-11-27 | 2009-11-27 |  |  | 2275123.57 | 3.230 | 001S935
5998 | MASSACHUSETTS | Underway | C220 | Highway Infrastructure Investment Grant | MASSACHUSETTS | FRANKLIN |  | 01 | 001S936 | The focus of the Northfield Street Improvement Project is to reconstruct sidewalks on Main Street and Parker Avenue in Northfield from a point north of the intersection with River Street continuing no | Transportation Enhancements | 2009-05-07 | 2009-05-07 |  |  | 1060412.75 |  | 001S936
5999 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE | PITTSFIELD | 01 | 001S937 | In Lenox: Reconstruction of State Highway from the Route 7 intersection north for approximately 1.25 miles to the end of the State Highway just south of the intersection with Route 183. Included in th | Pavement Improvement | 2009-06-25 | 2009-06-25 |  |  | 3670203.6 | 1.300 | 001S937
6000 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 001S938 | The proposed project consists of improvements to the Route 7/Route 8 Connector Road (formerly Berkshire Mall Drive), from the vicinity of the intersection with Route 7 to the vicinity of the intersect | Pavement Improvement | 2010-02-25 | 2010-02-25 |  |  | 7914429 |  | 001S938
6001 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NANTUCKET |  | 10 | 001S941 | This project in Nantucket consists of the mill and resurface of Milestone Road from just west of rotary that intersects Orange Street, Sparks Avenue, and Old South Road, to just east of rotary that intersects Post Office Road. | Pavement Improvement | 2009-05-21 | 2009-05-21 |  | 2010-11-29 | 3810640.15 |  | 001S941
6002 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | 01 | 001S942 | The purpose of this project is to resurface portions of Route 9 in Belchertown and Ware. Work will also include repairs/upgrades to guardrail end treatments as needed and new pavement markings. Beche | Pavement Improvement | 2009-05-21 | 2009-05-21 |  | 2010-12-03 | 4684551.59 |  | 001S942
6003 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 001S945 | The proposed scope for this project consists of micro-milling Route 8 shoulders and partially into travel lanes, installing a stress absorbing interlayer (SAMI) over the travel lanes, and applying a h | Pavement Improvement | 2009-05-14 | 2009-05-14 |  | 2009-11-30 | 994619.91 |  | 001S945
6004 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | PLYMOUTH |  | Multiple | 001S946 | In Brockton: Reconstruct Route 27, Pleasant Street, West Street and Westgate Mall Road. Work includes minor widening, geometric improvements, new traffic signals and interconnection of signalized intersections. | Pavement Improvement | 2009-07-30 | 2009-07-30 |  |  | 2811883 |  | 001S946
6005 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 001S947 | This project proposes to resurface Route 7 in New Ashford and Lanesborough with hot-mix asphalt, and would also include repairing/improving the drainage system, resetting guardrail, upgrading guardrai | Pavement Improvement | 2009-05-07 | 2009-05-07 |  | 2009-11-03 | 1878942.31 |  | 001S947
6006 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | WORCESTER, MA-CT | 03 | 001S949 | The proposed work under this project consists of bridge reconstruction, widening, guardrail installation and all other work on Water Street from its intersection with Bolton Street and Harris Street t | Bridge Replacement | 2009-09-10 | 2009-09-10 |  |  | 3178282.53 |  | 001S949
6007 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 001S952 | Resurface Route 2 in Harvard and Littleton from the vicinity of the Littleton Road Bridge to the Boxborough town line, a distance of approximately 4.4 miles. Work includes minor box widening to extend | Pavement Improvement | 2009-04-30 | 2009-04-30 |  | 2010-08-23 | 4807700.24 | 4.550 | 001S952
6008 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | 01 | 001S953 | The project involves roadway and sidewalk rehabilitation on town-owned Elm Street in the Town of Hatfield, and includes coldplaning, roadway reclamation, hot mix asphalt paving, replacement of sidewal | Pavement Improvement | 2009-07-09 | 2009-07-09 |  | 2009-11-30 | 700710.08 |  | 001S953
6009 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 001S954 | The proposed expansion of the Newburyport Park & Ride facility will add 105 parking spaces. Work will include the construction of a soil nail retaining wall, upgrades to the existing lighting, as well | Safety/Traffic Management | 2009-08-13 | 2009-08-13 |  |  | 3958204 | 0.000 | 001S954
6010 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN |  | 02 | 001S955 | This project consists of demolishing and replacing the Red Bridge Road Bridge over the Utilities Canal in Wilbraham. The new bridge will be a superstructure replacement constructed on an improved alig | Bridge Improvement | 2009-07-23 | 2009-07-23 |  | 2010-09-01 | 1607313.01 |  | 001S955
6011 | MASSACHUSETTS | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 001S959 | ERP-001S(959)X, Lawrence - Bridge Reconstruction #L-04-009, Hampshire Street over the Spicket River. | Bridge Replacement | 2009-10-01 | 2009-10-01 | 2011-10-01 | 2011-10-01 | 2210083.39 |  | 001S959
6012 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | FITCHBURG-LEOMINSTER | 01 | 001S961 | The Project limits are Route 2 in Westminster from Wyman Road/Village Inn Road (Exit 26), easterly into Fitchburg, to the Junction of Route 31 in Fitchburg, a distance of approximately 2.6 miles. The | Pavement Improvement | 2009-08-07 | 2009-08-07 |  |  | 7375759.69 | 2.260 | 001S961
6013 | MASSACHUSETTS | Underway | C220 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | Multiple | 001S962 | This multi-use recreational rail trail project starts at Ferry Street in Easthampton and ends at Earle Street in Northampton, for a total length of 4,400 Meters. It links the Manhan Bike Trail in Eas | Transportation Enhancements | 2009-09-03 | 2009-09-03 |  |  | 4126573.02 |  | 001S962
6014 | MASSACHUSETTS | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 001S963 | This project includes new traffic signals, landscape and streetscape elements, including brick pavers, trees and street furniture. | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2011-03-27 | 2011-03-27 | 2218828 |  | 001S963
6015 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX |  | 05 | 001S964 | The Town of Westford is proposing to widen approximately 3,000 feet of Littleton Road (Route 110). The existing cross section contains one lane in each direction with an additional left turn lane for | Pavement Improvement | 2009-08-06 | 2009-08-06 |  |  | 2751702.98 |  | 001S964
6016 | MASSACHUSETTS | Underway | C220,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 001S965 | This project will make safety and mobility improvements at four major intersections along the Dorchester Avenue corridor; Andrews Square, Glover's Corner, Fields Corner and Peabody Square. Improvemen | Pavement Improvement | 2009-11-17 | 2009-11-17 |  |  | 15274303 |  | 001S965
6017 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 001S966 | Work consists of resurfacing and related work in various locations in the city Boston | Pavement Improvement | 2010-01-28 | 2010-01-28 |  |  | 2749371.99 |  | 001S966
6018 | MASSACHUSETTS | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 001S967 | The purpose of this project is to improve access to the Jackson Street School by constructing new sidewalks, constructing a new access ramp to the nearby bikepath, installing 4' chain link fence at sc | Transportation Enhancements | 2009-10-01 | 2009-10-01 |  | 2010-09-30 | 592527.08 |  | 001S967
6019 | MASSACHUSETTS | Completed | C200,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | DUKES, BARNSTABLE | HYANNIS | 10 | 001S989 | Replace and realign the existing ferry slip at the Hyannis Terminal, including constructing a new dedicated berth for the Authority’s high-speed passenger vessel. Other work under this project includ | Other | 2009-06-13 | 2009-06-13 | 2010-04-01 | 2010-04-01 | 5019950.19 |  | 001S989
6020 | MASSACHUSETTS | Underway | C250 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 001S995 | The scope of work for the proposed project is to reconstruct Athol Richmond Road in the Town of Royalston from Elm Avenue in Royalston to the New Hampshire state border. The length of the roadway is a | Pavement Improvement | 2009-11-27 | 2009-11-27 |  |  | 1000000 |  | 001S995
6021 | MASSACHUSETTS | Underway | C220,C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S015 | MassHighway proposes to construct the North Bank Bridge over the MBTA Commuter Rail tracks providing a bicycle/pedestrian connection from East Cambridge to City Square Charlestown and the Boston Harbo | Transportation Enhancements | 2009-11-30 | 2009-11-30 |  |  | 29557203 |  | 002S015
6022 | MASSACHUSETTS | Completed | C200 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 002S022 | This project proposes to utilize pavement preservation techniques to resurface approximately 11.4 miles of various Federal-Aid eligible roadways (NHS and non-NHS) in North Adams. | Pavement Improvement | 2010-01-14 | 2010-01-14 |  | 2010-10-21 | 2475676.6 |  | 002S022
6023 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 002S026 | This project proposes to reconstruct Bridge Street (Route 1A) from the Beverly Salem Bridge to Washington Street. The project includes, sidewalks, curbing, trees and pavement markings. | Pavement Improvement | 2009-12-17 | 2009-12-17 |  |  | 7381521 |  | 002S026
6024 | MASSACHUSETTS | Underway | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 02 | 002S034 | This Footprint Road project in Southbridge involves milling and resurfacing, selected full-depth construction and minor box widening to provide a uniform width. (3.25 mi) | Pavement Improvement | 2009-12-10 | 2009-12-10 |  |  | 1999928.33 |  | 002S034
6025 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 002S053 | Fiber optic connectivity at three locations. Dist 4 via Rte 2 to MBTA Alewife station in Cambridge, Newton rest area on Rte 128 to MBTA riverside station, MEMA bunker to MTA toll plaza in Framingham. | Safety/Traffic Management | 2009-12-17 | 2009-12-17 |  |  | 1400000 |  | 002S053
6026 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S055 | Upgrade of the TOC and BTD video systems to IP based virtual matrix switching system. | Safety/Traffic Management | 2009-12-10 | 2009-12-10 |  |  | 1000000 |  | 002S055
6027 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK |  | Multiple | 002S056 | The design of communication equipment at five locations to increase bandwidth and allow for single CCTV connections for viewing for the City of Boston. | Safety/Traffic Management | 2009-12-10 | 2009-12-10 |  |  | 402958 |  | 002S056
6028 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK |  | Multiple | 002S057 | The design of up to 37 CCTV at signalized intersections throughout the city of Boston. | Safety/Traffic Management | 2009-12-17 | 2009-12-17 |  |  | 681576 |  | 002S057
6029 | MASSACHUSETTS | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 002S071 | Projects ERP-002S(071)X & STP-002S(071)X Ludlow, Sigal & Intersection Improvements at East St & Chapin St. | Pavement Improvement | 2010-01-14 | 2010-01-14 | 2010-10-11 | 2010-10-11 | 220028 |  | 002S071
6030 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | PLYMOUTH | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S072 | The purpose of this project is to reconstruct North Street from Pleasant Street to Village Gate Drive. The project will involve full depth reconstruction of North Street with approximately a four foot | Pavement Improvement | 2010-01-21 | 2010-01-21 |  |  | 1026713 |  | 002S072
6031 | MASSACHUSETTS | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | PLYMOUTH | HYANNIS | 04 | 002S073 | The purpose of this project is to rehabilitate the existing pavement surface on Routes 6 & 28 in Wareham from just east of Mogan Way easterly to the Wareham/Bourne Town Line. | Pavement Improvement | 2010-01-28 | 2010-01-28 |  | 2010-09-05 | 569761.38 |  | 002S073
6032 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | PROVIDENCE-PAWTUCKET-WARWICK (RI) | Multiple | 002S074 | The work for the Route 24 bridge over Bedford Street shall consist of reconstructing the bridge and approach wearing surface; replacing the reinforced concrete deck slab; extending the proposed deck a | Bridge Improvement | 2010-01-28 | 2010-01-28 |  |  | 2838394.39 |  | 002S074
6033 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 002S075 | The work consists of the landscape improvements along the side slopes and embankments along I-91, from Broad Street to State Street; the design of an irrigation system; and sidewalk and landscaping im | Transportation Enhancements | 2010-02-18 | 2010-02-18 |  |  | 1347556.02 |  | 002S075
6034 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S076 | This project involves the installation of a new fully actuated traffic signal system with appropriate phasing and timing for peak hour demands, including an exclusive pedestrian phase, to improve safety. | Safety/Traffic Management | 2010-02-04 | 2010-02-04 |  |  | 920996.21 |  | 002S076
6035 | MASSACHUSETTS | Completed | C200 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | 01 | 002S077 | Work under this project will consist of micromilling 1.5” from the existing paved surface and repaving with a 1.5” asphalt standard top course and a 0.75" paver placed friction course. Work will also | Pavement Improvement | 2010-02-11 | 2010-02-11 |  | 2010-09-23 | 1177737.73 |  | 002S077
6036 | MASSACHUSETTS | Underway | C250 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 002S078 | Bridge Replacement (O-02-005) (Concrete) Route 122 (Worcester Road) over Muddy Pond Brook. (ARRA Project) | Bridge Improvement | 2010-01-14 | 2010-01-14 |  |  | 946505.51 |  | 002S078
6037 | MASSACHUSETTS | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 002S079 | Project will consist of milling and resurfacing Burnett Road from New Lombard Road (near the Turnpike entrance) to the Ludlow Town Line for a total length of 1.7 miles. | Pavement Improvement | 2010-01-21 | 2010-01-21 |  | 2010-07-20 | 1005092.97 |  | 002S079
6038 | MASSACHUSETTS | Underway | C200 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 002S080 | The project limits are Route 140 in Gardner from 1000 feet north of Route 101 and continuing 1.6 miles north to Stone Street. The project consists of milling and resurfacing, and related work. | Pavement Improvement | 2010-02-11 | 2010-02-11 |  |  | 1588212.62 |  | 002S080
6039 | MASSACHUSETTS | Underway | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE |  | 01 | 002S081 | This project begins at the Westhampton Town Line and proceeds north-westerly for 3.08 miles to the intersection of South Street. The roadway currently exhibits potholes, alligator and block cracking, | Pavement Improvement | 2010-02-11 | 2010-02-11 |  |  | 2293099.89 |  | 002S081
6040 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 10 | 002S082 | This 1900-foot project includes roadway and sidewalk reconstruction and new traffic signals along the new alignment from the end of the Highway Division's Phase I project to the project limit west of | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 5349693.18 |  | 002S082
6041 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S083 | An 8'-10'-wide stabilized aggregate path, asphalt and elevated boardwalk are planned on both the eastern and western sides of Alewife Brook between Route 2 and Mystic Valley Parkway. In order to avoid | Transportation Enhancements | 2010-03-25 | 2010-03-25 |  |  | 4576901 |  | 002S083
6042 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 07 | 002S084 | Clippership Drive is currently two lanes with a sweeping alignment that encourages excessive speeds near an elderly housing complex. The master plan for Medford Square proposes to reduce the roadway | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2010-11-26 | 2010-11-26 | 726145 |  | 002S084
6043 | MASSACHUSETTS | Underway | C220,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 002S085 | The City of Somerville is proposing a series of transportation improvements to address vehicular access and public safety associated with new development opportunities planned within Assembly Square. These improvements include the following locations: • | Pavement Improvement | 2010-03-31 | 2010-03-31 |  |  | 14902367.6 |  | 002S085
6044 | MASSACHUSETTS | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 01 | 002S086 | The purpose of this project is to improve vehicular and pedestrian safety and promote efficient traffic operation along Main Street, Broad Street, South Broad Street and Park Square. | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 5440281 |  | 002S086
6045 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPSHIRE | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 02 | 002S087 | The project will resurface Route 47 (Hadley Street) in South Hadley from Ferry Street northerly to the Hadley Town Line. Work will include new pavement markings and the reconstruction of approximately 3,000 feet of asphalt sidewalk. | Pavement Improvement | 2010-02-11 | 2010-02-11 |  |  | 922788.54 |  | 002S087
6046 | MASSACHUSETTS | Completed | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | HAMPDEN | SPRINGFIELD-CHICOPEE-HOLYOKE (CT) | 01 | 002S088 | This project consists of resurfacing Westfield Road (Rte 202) from the Westfield City Line at Old County Road to Ashley Road for a total length of approximately 2.1 miles. | Pavement Improvement | 2010-02-18 | 2010-02-18 |  | 2010-07-10 | 1102890.49 |  | 002S088
6047 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S089 | The proposed Nonantum Road project will narrow the roadway to two 11-foot travel lanes for most of the stretch between Galen Street in Watertown and the Brook Street/North Beacon Street intersection | Pavement Improvement | 2010-03-11 | 2010-03-11 |  |  | 6360344 |  | 002S089
6048 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE | PITTSFIELD | 01 | 002S090 | The proposed project consists of pavement preservation measures to resurface approximately 8.5 miles of roadways curb to curb on First Street, Baker Road, Holmes Road and Valentine Road. The limits o | Pavement Improvement | 2010-03-18 | 2010-03-18 |  | 2010-10-01 | 2163528.48 |  | 002S090
6049 | MASSACHUSETTS | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 07 | 002S091 | Route 9 will be resurfaced from approximately the Southborough/Framingham Line easterly to the Natick/Wellesley Line. The work is to include milling & resurfacing; wheelchair ramp upgrades; additional | Pavement Improvement | 2010-03-25 | 2010-03-25 |  |  | 12175608 |  | 002S091
6050 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 08 | 002S092 | This project will reconstruct Washington Street, including traffic signal upgrades, landscaping and sidewalks/wheelchair ramps. | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 1258737 |  | 002S092
6051 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BRISTOL | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 03 | 002S096 | This project consists of resurfacing, reconstruction and safety improvements on city-owned Route 152 in the City of Attleboro. This project is Phase II of the city's plans to reconstruct Route 152 fr | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 1342771.52 |  | 002S096
6052 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S099 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 2010-01-28 | 2010-01-28 |  |  | 3061868.02 |  | 002S099
6053 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S100 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 2010-02-04 | 2010-02-04 |  |  | 2854342.94 |  | 002S100
6054 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S101 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 2010-02-04 | 2010-02-04 |  |  | 2190369.56 |  | 002S101
6055 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | SUFFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | Multiple | 002S102 | Work consists of resurfacing and related work at various locations in the city of Boston | Pavement Improvement | 2010-02-04 | 2010-02-04 |  |  | 3268703.63 |  | 002S102
6056 | MASSACHUSETTS | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | PROVIDENCE-PAWTUCKET-WARWICK (RI) | 02 | 002S103 | The purpose of this project is to improve traffic safety and operations for motorists and pedestrians. The proposed improvements for Pulaski Boulevard include widening the roadway, rehabilitating the | Pavement Improvement | 2010-01-28 | 2010-01-28 |  |  | 9945210.3 |  | 002S103
6057 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S104 | This is a State Highway resurfacing project including new pavement, guardrail, painting and signage. | Pavement Improvement | 2010-01-21 | 2010-01-21 |  |  | 1880221 |  | 002S104
6058 | MASSACHUSETTS | Underway | C200,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | FRANKLIN |  | 01 | 002S106 | This project consists of safety improvements and upgrades along Route 2 in the Town of Orange for a length of approximately 5 miles. This project includes widening the shoulder, extending the existin | Pavement Improvement | 2010-03-18 | 2010-03-18 |  |  | 15197734 |  | 002S106
6059 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 002S107 | The project includes realignment and signal installation at the following locations; Walnut Street at I-95 Southbound Ramps and Colonial Golf Club Site Drive (Exit 43); Walnut Street at I-95 Northboun | Pavement Improvement | 2010-03-11 | 2010-03-11 |  |  | 5815090.75 |  | 002S107
6060 | MASSACHUSETTS | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 10 | 002S112 | Work will consist of the demolition of two separate buildings. Parcel C-5, 1565 – 1597 Hancock Street, will be completely demolished and removed. Parcel C-6, 1570 Hancock Street, will be partially dem | Other | 2010-03-25 | 2010-03-25 |  |  | 1586582.09 |  | 002S112
6061 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER |  | 01 | 002S113 | The project consists of coldplaning and resurfacing sections of Route 32 from Upper Church Street northerly to the Barre Town Line for an approximate distance of 6 miles. | Pavement Improvement | 2010-02-25 | 2010-02-25 |  | 2010-09-23 | 1356678.03 |  | 002S113
6062 | MASSACHUSETTS | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | WORCESTER, MA-CT | 02 | 002S114 | The Project extends along Route 146 in Uxbridge, from just north of the Chocolog Road interchange, northerly about 4.4 miles to the Douglas Town Line, then continuing another 0.3± miles in Douglas to | Pavement Improvement | 2010-03-04 | 2010-03-04 |  |  | 7968585.08 |  | 002S114
6063 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | STATEWIDE |  |  | 002S116 | This project will add equipment at existing facilities to create a shared Wide Area Network (WAN) to transport voice, video and data for all transportation agencies. The technology employed will be e | Safety/Traffic Management | 2010-11-18 | 2010-11-18 | 2011-06-27 | 2011-06-27 | 25000 |  | 002S116
6064 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 002S118 | Resurfacing the pavement and related work on Route 114 from Route 1 in Danvers to Route 128 in Peabody for an approximate project length of 2.078 miles. | Pavement Improvement | 2010-03-25 | 2010-03-25 |  |  | 2226702.33 |  | 002S118
6065 | MASSACHUSETTS | Underway | C200 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 002S155 | Roadway Reconstruction and Related Work on a Section of West Street (Route 183) . (ARRA Project) | Pavement Improvement | 2010-09-01 | 2010-09-01 |  |  | 612000 |  | 002S155
6066 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 002S158 | Roadway Reconstruction and Related Work on a Section of Parkhurst Road. (ARRA Project) | Pavement Improvement | 2010-08-26 | 2010-08-26 |  |  | 1825531 |  | 002S158
6067 | MASSACHUSETTS | Underway | C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | ESSEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 06 | 002S170 | Intersection Improvements and Related Work (Including Traffic Signals) Lynnfield Street (Route 129) at Millard and Parker Hill Avenues and Den Quarry Road (ARRA Project) | Pavement Improvement | 2010-09-17 | 2010-09-17 |  |  | 729866.08 |  | 002S170
6068 | MASSACHUSETTS | Underway | C240,C230 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 07 | 002S175 | Roadway Reconstruction and Related Work on a Section of Forest Street. (ARRA Project) | Pavement Improvement | 2010-09-30 | 2010-09-30 |  |  | 1683076 |  | 002S175
6069 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S183 | Roadway Reconstruction and Related Work on a Section of Union Street. (ARRA Project) | Pavement Improvement | 2010-09-30 | 2010-09-30 |  |  | 2762730.51 |  | 002S183
6070 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | NORFOLK | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 09 | 002S185 | Roadway Reconstruction and Related Work on a Section of Route 138 (Turnpike Street). (ARRA Project) | Pavement Improvement | 2010-10-07 | 2010-10-07 |  |  | 1236009.06 |  | 002S185
6071 | MASSACHUSETTS | Underway | C250,C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | BERKSHIRE |  | 01 | 002S214 | Roadway Reconstruction and Related Work on a Section of Middlefield Road (Skyline Trail). (ARRA Project) | Pavement Improvement | 2010-11-26 | 2010-11-26 |  |  | 3343280 |  | 002S214
6072 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | MIDDLESEX | BOSTON-LAWRENCE-HAVERHILL(MA-NH-RI) | 05 | 002S219 | Roadway Reconstruction and Related Work on a Section of River Road and Merrimac Drive. (ARRA Project) | Pavement Improvement | 2010-11-26 | 2010-11-26 |  |  | 4997198 |  | 002S219
6073 | MASSACHUSETTS | Completed | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | STATEWIDE |  |  | 002S220 | PROJECT ERP-002S(220), Districts 1, 2, 3, & 6 Fiber Enhancement Rte I-90 (ITS) | Safety/Traffic Management | 2010-11-18 | 2010-11-18 | 2011-06-27 | 2011-06-27 | 1547770 |  | 002S220
6074 | MASSACHUSETTS | Underway | C240 | Highway Infrastructure Investment Grant | MASSACHUSETTS | WORCESTER | WORCESTER, MA-CT | 03 | 002S230 | Blackstone Canal District Streetscape Improvements. (ARRA Project) | Transportation Enhancements | 2010-11-04 | 2010-11-04 |  |  | 6748312 |  | 002S230
6075 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0833038 | 1.25 miles of roadway reconstruction of North Williamston Road from Sherwood Road to the city limits of Williamston in Ingham County. This project includes tree removals and drainage improvements. | Other | 2009-03-23 | 2009-03-26 | 2009-08-21 | 2009-08-21 | 23000 | 1.250 | 0833038
6076 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0833039 | 2.0 miles of pavement resurfacing of North Williamston Road from Sherwood Road to Haslett Road just north of the city of Williamston in Ingham County. This project will improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2009-03-23 | 2009-03-26 | 2009-08-21 | 2009-08-21 | 200000 | 1.999 | 0833039
6077 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | ALCONA |  | 01 | 0901004 | MDOT will resurface 5 miles of US-23 from Everett Rd to Black River Rd in the vicinity of Ossineke. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-05-05 | 2009-08-05 | 3267100.18 | 9.832 | 0901004
6078 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | ALCONA |  | 01 | 0901005 | MDOT will resurface 4.5 miles of M-72 from M-65 to west of O'Donnell Rd in the Huron National Forest. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2009-10-10 | 2009-10-14 | 1248007.56 | 4.310 | 0901005
6079 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALCONA |  | 01 | 0901006 | The Alcona County Road Commission will resurface 2.5 miles of East Black River Rd from US-23 to Lakeshore Rd east of the village of Lost Lake Woods. This will improve the driving quality by making the road smoother. | Other | 2009-07-09 | 2009-07-09 | 2015-12-31 | 2010-08-05 | 331618 | 2.949 | 0901006
6080 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 0902006 | This pavement project in Alger County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-14 | 2009-06-01 | 2010-04-01 |  | 93591 | 4.901 | 0902006
6081 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 0902007 | This pavement project in Alger County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-14 | 2009-06-01 | 2010-04-01 |  | 93591 | 5.039 | 0902007
6082 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 0902008 | This pavement project on Rock River Road in the Village of Chatham will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-14 | 2009-06-01 | 2010-04-01 |  | 27765.54 | 1.519 | 0902008
6083 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903321 | MDOT will resurface 7 miles of I-196, from 71st Street to 118th Avenue in Allegan County, just north of South Haven. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2012-12-31 | 2010-06-04 | 19479645.08 | 13.961 | 0903321
6084 | MICHIGAN | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN | HOLLAND | 06 | 0903322 | MDOT is installing median cable guardrail on 7 miles of I-196, from 71st Street to 118th Avenue in Allegan County, just north of South Haven, to improve safety. | Safety/Traffic Management | 2009-04-02 | 2009-04-02 | 2010-12-31 | 2010-06-04 | 640856.27 | 6.980 | 0903322
6085 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903323 | MDOT will renovate the Glenn Rest Area on I-196 in Allegan County, to improve convenience and service to stopping motorists. | Other | 2009-04-02 | 2009-04-02 | 2011-05-30 | 2010-06-04 | 2040721.74 | 0.939 | 0903323
6086 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903324 | MDOT will make repairs on the bridge carrying I-196 over 71st Street in Allegan County, just north of South Haven, to make the bridge last longer. | Bridge Replacement | 2009-04-02 | 2009-04-02 | 2011-05-30 | 2010-06-04 | 353286.56 | 0.000 | 0903324
6087 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903327 | "The City of Allegan will resurface 2.3 miles of Babylon Road from River Street to M-40 in the city. This will improve the driving quality by making the road smoother. | Other | 2009-08-12 | 2009-09-22 | 2009-10-24 | 2009-10-17 | 120000 | 2.305 | 0903327
6088 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 0903333 | "The Allegan County Road Commisssion will resurface 4.2 miles of 109th Avenue from 48th Street to 56th Street, in the southwest part of Allegan County. | Pavement Improvement | 2009-10-06 | 2009-10-11 | 2009-11-13 | 2009-11-07 | 831422.52 | 4.209 | 0903333
6089 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALPENA |  | 01 | 0904009 | The Alpena County Road Commission resurface 3 miles of Leer Rd from Mellon Rd to Carr Rd in south of the village of Posen. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-28 | 2010-06-09 | 2011-06-30 | 2010-06-28 | 318026.74 | 3.013 | 0904009
6090 | MICHIGAN | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ANTRIM |  | 01 | 0905006 | MDOT will resurface 1.4 miles of M-88 from South Eckhardt Rd to South Central Lake in the vicinity of Bellaire. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-09-11 |  | 627752.67 | 1.361 | 0905006
6091 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ANTRIM |  | 01 | 0905007 | MDOT will resurface 12 miles of M-66 from US-131 west to Lillac Creek in the vicinity of Mancelona. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2011-03-03 | 2010-08-23 | 521199.94 | 11.977 | 0905007
6092 | MICHIGAN | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ARENAC |  | 01 | 0906004 | West of the City of Pinconning on M-65/Maple Ridge Road southeast quadrant and on M-61/I-75 southwest quadrant, there was the improvement to the park and ride lot to encourage ridesharing and reduce the number of cars on the roadway. | Other | 2009-04-02 | 2009-04-02 | 2010-12-01 |  | 78116.25 | 0.000 | 0906004
6093 | MICHIGAN | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ARENAC |  | 01 | 0906005 | Repairs will be made at the US-23 bridge over Big Creek North of the City of Standish to make the bridge last longer. | Bridge Improvement | 2009-04-03 | 2009-04-03 | 2010-04-01 |  | 61671.16 | 0.000 | 0906005
6094 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | BARAGA |  | 01 | 0907010 | This paving of road and shoulders and installed rumble strips project on US-41 south of the City of L'Anse will improve safety and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-10-21 | 2009-10-14 | 179863.05 | 1.503 | 0907010
6095 | MICHIGAN | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | BARAGA |  | 01 | 0907011 | This paving of road and shoulders and installed rumble strips project south of the City of L'Anse will improve safety and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-10-20 | 2009-10-14 | 1799533.59 | 11.355 | 0907011
6096 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 0909009 | There is 52.76 miles of shoulder widening within the Cities of Standish, Omer, and Augres to improve mobility and reduce congestion. | Transportation Enhancements | 2009-04-23 | 2009-04-23 | 2011-01-01 | 2009-09-17 | 3850080.15 | 52.875 | 0909009
6097 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 0909012 | Bay City is perfoming 0.19 miles of roadway realignment and intersection modifications on Marquette Avenue to improve safety. | Pavement Improvement | 2009-06-02 | 2009-08-24 | 2010-06-01 | 2010-05-28 | 480000 | 0.486 | 0909012
6098 | MICHIGAN | Underway | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 0909018 | Within Bay City, MDOT will replace I-75 from Squaconning Creet to Hotchkiss to improve safety and increase mobility. | Pavement Improvement | 2009-09-03 | 2009-09-03 | 2013-09-19 |  | 15825489.51 | 3.687 | 0909018
6099 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BAY |  | 01 | 0909019 | Within Bay City, MDOT will replace I-75 from Squaconning Creet to Hotchkiss to improve safety and increase mobility. | Bridge Improvement | 2010-01-25 | 2010-02-09 | 2013-09-19 |  | 2613680.91 | 0.000 | 0909019
6100 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 0909020 | Within Bay City, MDOT will replace M-84 over Squaconning Creek and Dutch Creek to improve safety and increase mobility. | Bridge Replacement | 2009-04-13 | 2009-04-13 | 2013-09-19 |  | 3060406.05 | 0.000 | 0909020
6101 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | SAGINAW | 01 | 0909021 | This is reconstructing 4.49 miles on 6 bridges to improve safety and increase capacity. | Pavement Widening | 2003-01-28 | 2003-01-28 | 2013-12-08 |  | 14290649.06 | 3.261 | 0909021
6102 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 0911332 | "The City of St. Joseph will resurface 0.13 miles of Park St. from Lake Boulevard to Main Street in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-13 | 2009-09-08 | 2011-07-27 | 2009-10-30 | 204996.7 | 0.134 | 0911332
6103 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 0911335 | MDOT is installing median cable guardrail on 18 miles of I-94, from US-12 to I-94 BL near Bridgeman in Berrien County, just south of the Benton Harbor - St. Joseph metropolitan area, to improve safety. | Safety/Traffic Management | 2009-05-29 | 2009-05-29 | 2010-11-08 | 2011-09-23 | 3307031.67 | 36.096 | 0911335
6104 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 0911351 | "The Berrien County Road Commisssion will resurface 1.8 miles of Glenlord Road from I-94 BL to Cleveland Avenue and from Lincoln to M-139, through Stevensville and Shoreham, on the south side of the B | Pavement Improvement | 2009-06-30 | 2009-08-03 | 2009-09-01 |  | 75559.85 | 3.538 | 0911351
6105 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0911352 | "The Berrien County Road Commisssion will resurface 4 miles of Range Line Rd. from Walton Road north, between Buchanan and Berrien Springs in Berrrien County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-07-14 | 2009-09-01 |  | 68534.59 | 4.044 | 0911352
6106 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911353 | "The Berrien County Road Commisssion will resurface sections of Coloma Road and Range Line Road totalling 5 miles in northwest and southern Berrrien County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-07-20 | 2010-03-01 |  | 91004.42 | 5.044 | 0911353
6107 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911354 | "The Berrien County Road Commisssion will resurface sections of Red Arrow Highway, Warren Woods Road and Shawnee Road totalling 4.2 miles in the southern part of Berrrien County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-08-03 | 2010-03-01 |  | 89165.81 | 4.221 | 0911354
6108 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911355 | "The Berrien County Road Commisssion will resurface sections of Hagar Shore, Blue Star Highway and Paul Avenue totalling 5.5 miles in the northwest corner of Berrrien County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-07-20 | 2010-03-01 |  | 77153.97 | 4.828 | 0911355
6109 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 0911359 | "The Berrien County Road Commisssion will resurface 8 miles of Pipestone Road, Nickerson Avenue, Sodius Parkway and Red Arrow Highway in the area south and east of the Benton Harbor - St. Joseph metro | Pavement Improvement | 2010-01-14 | 2010-07-13 | 2011-07-27 | 2010-07-18 | 610228.95 | 7.982 | 0911359
6110 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911363 | "The City of Watervliet will resurface 0.41 miles of East St. Joseph Avenue from M-140 to Lewis in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-02 | 2010-06-14 | 2010-08-15 | 2010-07-29 | 153914.67 | 0.414 | 0911363
6111 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911364 | "The village of Baroda will resurface 0.21 miles of Hills Road. from the village limits to 1st Street in the village. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-05 | 2010-04-12 | 2011-07-27 | 2010-06-01 | 93494.14 | 0.214 | 0911364
6112 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 0911368 | "The Berrien County Road Commisssion will resurface 0.46 miles of Cleveland Avenue from Rocky Weed Rd. northward near Stevensville, just south of the Benton Harbor - St. Joseph metropolitan area. Thi | Pavement Improvement | 2010-02-24 | 2010-07-06 |  | 2010-09-08 | 198625.46 | 0.462 | 0911368
6113 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0911373 | MDOT will resurface 0.31 miles of US-12 BR, from Grant Street to the St. Joseph River in Niles. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-18 | 2009-05-18 | 2010-06-04 | 2010-06-04 | 327187.17 | 0.603 | 0911373
6114 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912010 | "The Branch County Road Commisssion will resurface 5.5 miles of Jonesville Road from Fremont Road to the Hillsdale County Line, east of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-04 | 2009-08-01 | 2010-03-01 |  | 85200 | 5.462 | 0912010
6115 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912011 | "The Branch County Road Commisssion will resurface 3.6 miles of North Fremont Road from Corless Road to US-12, just east of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-04 | 2009-08-01 | 2010-03-01 |  | 35365.93 | 3.606 | 0912011
6116 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912012 | "The Branch County Road Commisssion will resurface 5.6 miles of Burr Oak Road from Bronson city limits to the St. Joseph County Line, in Branch County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-04 | 2009-07-27 | 2010-03-01 |  | 79182.79 | 5.629 | 0912012
6117 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912013 | "The Branch County Road Commisssion will resurface sections of Dunks Rd., Creamery Rd. and Railroad Rd. totalling 6.1 miles in the northwest corner of the county. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-04 | 2009-08-01 | 2010-03-01 |  | 85500 | 6.086 | 0912013
6118 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912014 | The Branch County Road Commisssion will resurface 5.6 miles of Orland Road and Southern Road, from Rierson Road to Dewsenberry Road, in the southwest part of the county. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-09 | 2009-07-16 | 2010-04-01 |  | 57378 | 5.565 | 0912014
6119 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912015 | "The Branch County Road Commisssion will resurface 4 miles of Marshall Road from Newton Road to Girard Rd, just north of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-24 | 2009-09-23 | 2010-09-15 |  | 68522 | 4.036 | 0912015
6120 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912016 | "The Branch County Road Commisssion will repair one mile of Marshall Road from Newton Road to State Rd, just north of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-29 | 2009-09-22 | 2009-09-30 |  | 13055 | 1.004 | 0912016
6121 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912018 | "The City of Coldwater will repair various sections of W. Pearl Street totalling 8.9 miles in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-13 | 2009-09-22 | 2009-10-12 | 2009-10-12 | 52133 | 8.982 | 0912018
6122 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 0912019 | "The Branch County Road Commisssion will resurface 2.5 miles of River road from Garfield Road to US-12 and from US-12 to Narrows Road, in the city of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-13 | 2009-08-27 | 2009-10-05 | 2009-10-05 | 47550.54 | 2.516 | 0912019
6123 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913222 | "The City of Battle Creek will resurface 1 mile of Beckley Road from Helmer Road to Stone Jug Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-04 | 2009-09-15 | 2011-07-27 | 2009-10-29 | 178650.2 | 1.012 | 0913222
6124 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913223 | "The City of Battle Creek will resurface 1 mile of Capital Avenue SW from Beckley Road to the city limits. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-04 | 2009-09-15 | 2009-10-29 | 2009-10-29 | 187342.47 | 1.001 | 0913223
6125 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913224 | "The City of Battle Creek will resurface 1.7 miles of Jackson Street from M-37 to Bedford Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-04 | 2009-09-15 | 2009-10-29 | 2009-10-29 | 361852.38 | 1.692 | 0913224
6126 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 0913225 | The Calhoun County Road Commission is building sidewalks and ADA ramps on 1.5 miles of M-96 from Columbia Avenue to I-94 BL in the city of Battle Creek, to improve pedestrian mobility and safety. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-25 | 2010-06-25 | 268455.06 | 1.463 | 0913225
6127 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 0913229 | The Calhoun County Road Commission will resurface 3 miles ofN Drive N from 12 Mile Road to 15 Mile Road, east of Battle Creek. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2011-07-27 | 2009-10-07 | 441159.36 | 2.976 | 0913229
6128 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913231 | The Calhoun County Road Commission will resurface 1.9 miles of Bellevue Road from Verona Road to McAllister, in the Battle Creek urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-02 | 2009-10-16 | 2011-07-27 | 2009-11-18 | 270981.98 | 1.869 | 0913231
6129 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913232 | The Calhoun County Road Commission will resurface 0.6 miles of Beadle Lake Road from B Drive N to Division Drive, in the Battle Creek urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-17 | 2009-09-30 | 2011-07-27 | 2009-10-29 | 167331.71 | 0.600 | 0913232
6130 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 0913233 | "The City of Marshall will resurface 0.56 miles of North Kalamazoo Avenue from Brewer Street to Linden Street in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-23 | 2009-10-01 | 2009-11-15 | 2009-11-13 | 122215.07 | 0.559 | 0913233
6131 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 0913234 | "The City of Springfield will resurface 1.3 miles of Harmonia Road from M-37 to Evergreen in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-28 | 2009-09-08 | 2011-07-27 | 2010-10-29 | 312218.59 | 1.344 | 0913234
6132 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914019 | The Cass County Road Commission will resurface 1.8 miles of Ironwood Drive from Redfield Street to Bell Road, in the Niles urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-09 | 2010-08-02 | 2010-08-30 |  | 38423.52 | 1.760 | 0914019
6133 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914020 | The Cass County Road Commission will resurface 0.2 miles of Redfield Road from Adamsville Road to Mason Township, in the Niles urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-09 | 2010-08-02 | 2010-08-30 |  | 11715.31 | 0.192 | 0914020
6134 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914021 | The Cass County Road Commission will resurface 0.5 miles of Matthews Street from Dailey Road to Cherry Grove Road, in the Dowagiac urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-10-01 | 2009-10-31 |  | 50000 | 0.503 | 0914021
6135 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914022 | The Cass County Road Commisssion will resurface 3.7 miles of Decatur Road from M-60 to Kelsey Lake Road, near Cassopolis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-08-31 | 2010-04-01 |  | 87279.15 | 3.717 | 0914022
6136 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914023 | The Cass County Road Commisssion will resurface 3 miles of Brownsville Street from M-62 to Crooked Creek Road,south of Cassopolis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-08-31 | 2010-04-01 |  | 73916 | 2.962 | 0914023
6137 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914024 | "The Cass County Road Commission will resurface various sections of Pine Lake, Monette and Dailey Streets totalling 7.3 miles in the southwest part of the county. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-08-31 | 2010-04-01 |  | 77650 | 2.640 | 0914024
6138 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914025 | The Cass County Road Commisssion will resurface 1.7 miles of Indian Lake Road fromCrystal Springs to Smith Lake Road, between Niles and Dowagiac. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-08-31 | 2010-05-01 |  | 32041 | 1.716 | 0914025
6139 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914026 | "The Cass County Road Commission will resurface various sections of Marcellus Highway totalling 0.9 miles in thenorth part of the county. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-08-31 | 2010-04-01 |  | 82515.97 | 3.845 | 0914026
6140 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914027 | The Cass County Road Commission will resurface 0.18 miles of Middle Crossing Road from Yaw Street to the city limits, in the Dowagiac urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-08 | 2010-08-02 | 2010-08-27 | 2009-09-28 | 20000 | 0.180 | 0914027
6141 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914031 | The Cass County Road Commission will resurface 1.4 miles of Huntly Road from Holly Street to Barron Lake Road, in the Niles urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-20 | 2009-08-31 | 2009-09-15 |  | 27500 | 1.360 | 0914031
6142 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914032 | The Cass County Road Commission will resurface 2.7 miles of Beebe Road from US-12 to Runkle Road and from Redfield Street to US-12, in the Niles urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-20 | 2009-08-31 | 2009-09-15 |  | 61948 | 2.798 | 0914032
6143 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 0914033 | The Cass County Road Commisssion will resurface 4 miles of Dewey Lake Street from M-51 to Glenwood road, in the northeast part of the county. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-20 | 2010-07-19 | 2010-07-30 |  | 64625.83 | 3.959 | 0914033
6144 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 0914034 | The Cass County Road Commission will resurface 2.5 miles of Pine Lake Road from M-60 to Anderson Road, in the Niles urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-21 | 2009-08-31 | 2009-09-15 |  | 31578 | 1.584 | 0914034
6145 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 0916011 | MDOT will resurface 1.2 miles of US-23 from M-27 to the Little Black River in the village of Cheboygan. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-27 | 2009-05-27 | 2009-09-18 | 2009-11-06 | 748233.49 | 1.172 | 0916011
6146 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 0916013 | One and a quarter miles of Trowbridge Rd will be resurfaced from the Sturgeon River bridge to South Straights Hwy in the Village of Wolverine. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-10 | 2010-05-12 | 2010-06-11 | 2010-05-20 | 14440.65 | 1.258 | 0916013
6147 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 0916014 | Four tenths of a mile of South Straights Hwy will be resurfaced from Cedar St to the north village limits of the Village of Wolverine. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-10 | 2010-05-12 | 2010-06-11 | 2010-05-20 | 52250.24 | 0.408 | 0916014
6148 | MICHIGAN | Underway | C250 | Highway Infrastructure Investment Grant | MICHIGAN | CLARE |  | 04 | 0918007 | There will be 5.41 miles of paved pathway in the village of Farwell on the Pere Marquette Rail Trail for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-04-02 | 2009-04-02 | 2010-04-30 |  | 804661.79 | 5.409 | 0918007
6149 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON | LANSING | 08 | 0919009 | Near the city of Bath in Clinton County, MDOT will improve the driving surface of 6.5 miles of I-96 with a concrete restoration project. | Pavement Improvement | 2009-05-01 | 2009-05-01 | 2011-06-16 | 2009-10-09 | 1706751.76 | 16.097 | 0919009
6150 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 0919010 | Near the City of Dewitt, The Clinton County Road Commission is resurfacing 1 mile of West Alward Road from US-127BR to Williams Road to improve driving quality and make the road smoother. | Pavement Improvement | 2009-08-03 | 2009-08-11 | 2009-09-18 | 2009-09-18 | 159489.66 | 1.004 | 0919010
6151 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON | LANSING | 08 | 0919011 | In the city of Dewitt, over 1/2 mile of West Main Street will be resurfaced from Norris Road to Scott Street to improve ride quality and make the roadway smoother. Improvements include new sidewalk to improve pedestrian mobilty and safety. | Pavement Improvement | 2009-08-03 | 2009-08-24 |  | 2009-10-02 | 190414.02 | 0.602 | 0919011
6152 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON | LANSING | 08 | 0919012 | Near the city of Dewitt, The Clinton County Road Commission is resurfacing 1 mile of East Clark Road from US-127BR to Wood Road to improve driving quality and make the road smoother. | Pavement Improvement | 2009-08-03 | 2009-08-19 | 2009-09-18 | 2009-09-18 | 276430.83 | 1.003 | 0919012
6153 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 0919013 | Close to the villages of Hubbardston and Pewamo, the Clinton county Road Commission will improve 4 miles of pavement on West Colony Road from the West Clinton County Line to Tallman Road. | Pavement Improvement | 2009-06-02 | 2009-06-22 | 2009-09-01 |  | 65955.65 | 3.945 | 0919013
6154 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 0919014 | In Bath Township, the Clinton County Road Commission will resurface 1/2 mile of East Clark Road from Webster Road to the east to improve driving quality and make the road smoother. | Pavement Improvement | 2009-08-14 | 2009-09-01 | 2009-09-18 | 2009-09-18 | 118367.91 | 0.500 | 0919014
6155 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON | LANSING | 08 | 0919015 | MDOT is reconstructing nearly 7 miles of I-96 in Clinton and Eaton Counties to improve driver mobility and make the roadway safer and smoother. This project is the 5000th Recovery Act project and is from Wacousta Road to the Saginaw Highway interchange. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2013-06-30 |  | 44809061.06 | 15.835 | 0919015
6156 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 0919021 | 4 miles of East Colony Road is being resurfaced north of St. Johns to make the roadway smoother and improve ride quality. | Pavement Improvement | 2009-08-05 | 2009-08-11 | 2009-08-31 | 2009-08-31 | 68354.97 | 4.013 | 0919021
6157 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CRAWFORD |  | 01 | 0920009 | The Crawford County Road Commission will resurface 1.7 miles of South Wakely Bridge Rd from M-72 to The Au Sable River in the Huron National Forest near Grayling. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-03 | 2009-09-21 | 2009-10-30 | 2009-11-10 | 194524.15 | 1.664 | 0920009
6158 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CRAWFORD |  | 01 | 0920010 | MDOT will resurface 2.4 miles of M-93 from Camp Grayling to M-72 in the vicinity of Grayling. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2010-06-25 | 2010-06-25 | 371766.66 | 2.606 | 0920010
6159 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CRAWFORD |  | 01 | 0920013 | MDOT will resurface 5 miles of I-75 from south of the NYC RR to north of M-93 in the vicinity of Grayling. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-02 | 2009-06-02 | 2011-05-05 | 2010-10-05 | 3332348.34 | 5.319 | 0920013
6160 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 0921011 | This intersection project at US-2 and US-41 in the City of Rapid River will increase safety and improve the pavement condition which will make for a smoother ride. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-10-18 | 2010-10-01 | 1458863.81 | 1.165 | 0921011
6161 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 0921014 | This pavement project on County Road 513 in Delta County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-19 | 2010-01-04 | 2010-10-31 | 2010-08-27 | 137968.24 | 11.418 | 0921014
6162 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 0922007 | This Center Left-Turn lane project on M-95 in Sagola will improve safety and increase mobility. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2010-10-18 | 2009-10-09 | 373727.53 | 0.363 | 0922007
6163 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 0922008 | This pavement project on Balsam Street in the City of Kingsford will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-09-01 | 2009-09-28 | 2009-10-20 | 2009-10-19 | 222475.03 | 0.497 | 0922008
6164 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | EATON | LANSING | 07 | 0923010 | In Eaton County just outside of city of Lansing limits , 2.41 miles of Creyts Road is to be resurfaced from Lansing Road to I-496. This work will improve driving quality and make the road smoother. | Pavement Improvement | 2009-06-29 | 2009-07-13 | 2009-10-30 | 2009-07-30 | 667891.65 | 2.414 | 0923010
6165 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | EATON | LANSING | 07 | 0923012 | In the City of Grand Ledge, just over 1/4 miles of Brookside Drive from Timbercreek Street to South Street will be reconstructed to improve rideability and make the roadway smoother. | Pavement Improvement | 2009-07-31 | 2009-08-03 | 2009-09-14 | 2009-09-17 | 204723.78 | 0.349 | 0923012
6166 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | EATON | LANSING | 07 | 0923013 | In the City of Grand Ledge, 1/4 miles of Timber Creek Drive from Saginaw highway to Brookside Drive will be reconstructed to improve rideabilty and make the roadway smoother. | Pavement Improvement | 2009-07-31 | 2009-08-03 | 2009-09-14 | 2009-09-17 | 188445.44 | 0.284 | 0923013
6167 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 0923015 | In the City of Eaton Rapids, MDOT is working on building a streetscape project on South Clinton Trail and South Main Street (State Routes M-99 & M-50) The work will be from just west of Hallawood Lan | Pavement Improvement | 2009-06-17 | 2009-06-17 | 2012-09-20 |  | 2503080.71 | 1.385 | 0923015
6168 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 0923016 | The City of Eaton Rapids in Eaton County will beautify its downtown by building this streetscape. The streetscape will include new brick pavers, lighting, decorative sidewalk and and additional landscaping enhancements. | Transportation Enhancements | 2009-06-10 | 2009-06-10 | 2012-09-20 |  | 842075.88 | 0.397 | 0923016
6169 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | EATON | LANSING | 07 | 0923017 | In Eaton County just outside of city of Lansing limits , 1/2 mile of Creyts Road is to be resurfaced from Saginaw highway to the north. This work will improve driving quality and make the road smoother. | Pavement Improvement | 2009-10-07 | 2010-07-23 | 2010-05-31 | 2010-07-26 | 103341.62 | 0.499 | 0923017
6170 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EMMET |  | 01 | 0924008 | The Emmet County Road Commission will resurface three quarters of a mile of Mitchell Rd from Division Rd east 3900 ft in the vicinity of Petoskey. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2009-10-19 | 2009-10-19 | 155000 | 0.654 | 0924008
6171 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EMMET |  | 01 | 0924009 | The Emmet County Road Commission will resurface 2.3 miles of W Conway Rd from Heydey St to Clayton Rd in Little Traverse Township. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-01 | 2009-05-01 | 2009-11-15 | 2009-11-06 | 348268.4 | 2.331 | 0924009
6172 | MICHIGAN | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 0925015 | Just west of the city of Flint, MDOT will repair M-13 over Mistequay Creek to make the bridge last longer. | Bridge Improvement | 2009-04-02 | 2009-04-02 | 2011-04-01 |  | 187704.94 | 0.000 | 0925015
6173 | MICHIGAN | Underway | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 0925016 | Just west of the city of Flint, MDOT will repair 12.2 miles of M-13 to extend the service life of the existing pavement. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2011-01-15 |  | 4980018.63 | 12.395 | 0925016
6174 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 0925018 | Within the City of Fenton, MDOT will resurface parking lot on US-23 to improve the quality of the parking surface and extend the life of the road pavement. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2010-12-31 | 2009-08-25 | 94674.25 | 0.000 | 0925018
6175 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925021 | The MDOT will design roadway and bridge improvements to I-475 from the I-75 and I-69 interchange south of Flint north 6.6 miles. | Other | 2009-05-14 | 2009-05-14 | 2009-12-31 |  | 825251.03 |  | 0925021
6176 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925023 | Near the city of Flint, MDOT is upgrading 1.16 miles of pavement on Pasadena Avenue from I-75 to the Flint city limits, Genesee County. This will improve the ride quality of the road. | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2010-08-15 |  | 1536295 | 1.087 | 0925023
6177 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925024 | There will be 1.10 miles of pavement repair on Clio Road from Pierson Road to Carpenter Road to improve safety and increase mobility. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-08-15 |  | 1356636.75 | 0.997 | 0925024
6178 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 0925032 | Genesee County is resurfacing 0.99 miles on Irish Road from Richfield Road northerly to Carpenter Road to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-23 | 2009-06-23 | 2010-08-15 | 2010-06-30 | 624753 | 0.925 | 0925032
6179 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925038 | Genesee County will repair the pavement of 0.83 miles on Morrish Road from I-69 to the Canadian National Railway railroad tracks in the city of Swartz Creek to improve the driving quality of the road. | Pavement Improvement | 2009-07-02 | 2009-07-02 | 2010-08-15 | 2009-12-31 | 251247.76 | 0.918 | 0925038
6180 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925041 | In the City of Fenton in Genesee County there is 1.16 miles of resurfacing on Silver Parkway from Owen Road to Silver Lake Road to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-10-23 | 2009-10-26 | 2010-10-30 | 2010-06-30 | 1180758.17 | 0.912 | 0925041
6181 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925046 | In the city of Flint there is 0.95 miles of road reconstruction on Kettering Gateway from I-69 to Chevrolet Avenue to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2011-05-27 | 2011-05-27 | 2315955.02 | 0.640 | 0925046
6182 | MICHIGAN | Underway | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 0925054 | In Genesee County, MDOT will perform a Design Build reconstruction of 4 bridge structures on I-475 from the south interchange to I-69 including Hill road and Bristol Road over I-475 and I-475 over Maple Road to improve safety. | Pavement Improvement | 2009-09-18 | 2009-09-18 | 2012-12-31 |  | 19523521.35 | 14.929 | 0925054
6183 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GLADWIN |  | 01 | 0926009 | The County of Gladwin is resurfacing 2.02 miles of roadway to improve the driving quality of the Knox Road from Shock Road easterly to Dundas Road. | Pavement Improvement | 2009-09-02 | 2009-10-05 | 2009-11-07 | 2009-11-11 | 387200 | 1.987 | 0926009
6184 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 0927008 | This pavement project on US-2 in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-01 | 2009-05-01 | 2010-10-18 | 2009-10-02 | 1843722.08 | 16.204 | 0927008
6185 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 0927014 | This pavement and guardrail project on US-45 in Gogebic County will improve the safety and ride quality of the road. | Pavement Improvement | 2009-08-13 | 2009-08-13 | 2010-10-18 | 2010-07-15 | 1874469.38 | 12.415 | 0927014
6186 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0928008 | East 8th St in Traverse City will be resurfaced for over a half mile from garfield to Woodmere St. This will improve the driving quality by making the road smoother. | Other | 2009-10-19 | 2010-04-12 | 2010-06-23 | 2010-07-14 | 210000 | 0.605 | 0928008
6187 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0928010 | The Grand Traverse County Road Commission will place new pavement markings at various locations on county roads in the county to provide more visible markings. | Safety/Traffic Management | 2009-10-08 | 2010-05-18 | 2010-06-18 | 2010-05-26 | 277500 | 1.434 | 0928010
6188 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0928011 | The Grand Traverse County Road Commission will place new pavement symbols at various locations on county roads in the county to provide safer roadways. | Safety/Traffic Management | 2009-08-13 | 2009-09-18 | 2010-08-30 | 2010-08-27 | 80032.6 | 1.434 | 0928011
6189 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0928012 | The Grand Traverse County Road Commission will resurface 3.2 miles of karlin Rd from M-137 to Nessen Rd south of the village of Green Lake. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-17 | 2010-06-01 | 2010-07-02 | 2010-06-29 | 401809.51 | 3.000 | 0928012
6190 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRATIOT |  | 04 | 0929208 | Near the city of Alma there will be 4.05 miles of resurfacing on Lumberjack Road from M-46 northerly to North County Line Road to improve driving quality by making the road smoother. | Other | 2009-12-22 | 2010-04-27 | 2010-08-13 | 2010-08-13 | 446327 | 4.057 | 0929208
6191 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GRATIOT |  | 04 | 0929210 | The city of Alma is resurfacing 8.92 miles on M-46 from the Gratiot/Montcalm County line easterly to west of US-127BR to improve driving quality by making the road smoother. | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2012-02-01 | 2010-11-01 | 1648382.16 | 8.920 | 0929210
6192 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930012 | 5.29 miles of South Waldron Road from Territorial Road northerly to Prattville Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness through the community of Waldron, Hillsdale County. | Pavement Improvement | 2009-05-28 | 2009-06-30 | 2010-03-01 |  | 69889.47 | 5.291 | 0930012
6193 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930013 | 2.75 miles of Church Road from Waldon Road to US-127 will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness east of the city of Hillsdale, Hillsdale County. | Pavement Improvement | 2009-05-28 | 2009-06-29 | 2010-03-01 |  | 44312.91 | 2.754 | 0930013
6194 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930014 | 2.91 miles of North Adams Road from the Village of Jonesville to Mimes Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness in Hillsdale County. | Pavement Improvement | 2009-05-28 | 2009-06-11 | 2010-03-01 |  | 93387.72 | 2.914 | 0930014
6195 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930015 | 3.0 miles of North Adam Road will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, South of the City of Jackson in Hillsdale County. | Pavement Improvement | 2009-05-28 | 2009-06-01 | 2010-03-01 |  | 91506.45 | 3.004 | 0930015
6196 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930016 | 3 miles of East Bacon Road will have a Chip and Seal treatment from Peterson Road to Osseo Road east of the village of Hillsdale, Hillsdale County. The work will preserve the pavement life and improve pavement smoothness. | Pavement Improvement | 2009-05-28 | 2009-06-29 | 2010-03-01 |  | 83859 | 2.993 | 0930016
6197 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 0930017 | 5 miles of South Allen Road from Bankers Road to US-12 will have a Chip and Seal treatment to preserve pavement life and improve pavement smoothness. This proejct is located just west of the city of Hillsdale in Hillsdale County. | Pavement Improvement | 2009-06-02 | 2009-06-29 | 2010-03-01 |  | 93791.85 | 4.960 | 0930017
6198 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931007 | This paving project on US-41 east of the City of Houghton will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2009-06-22 | 2009-06-22 | 353754.39 | 2.046 | 0931007
6199 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931008 | This pavement project on US-41 in Houghton County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-10-18 | 2009-06-22 | 328382.32 | 2.654 | 0931008
6200 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931009 | This shoulder paving and guardrail installation project on M-26 in Houghton County will serve cyclists, joggers and other non-motorized users and will improve safety. | Transportation Enhancements | 2009-04-02 | 2009-04-02 | 2009-08-18 | 2009-08-18 | 176732.89 | 2.443 | 0931009
6201 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931010 | This paving project on M-26 in the Village of Lake Linden will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-10-18 | 2009-08-18 | 472359 | 2.577 | 0931010
6202 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931014 | This pavement project on Erickson Drive in the Houghton Urban Area will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-31 | 2009-09-23 | 2009-10-15 | 2009-10-15 | 90000 | 0.450 | 0931014
6203 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931015 | This pavement project on 6th Street in the City of Larium will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-31 | 2009-09-23 | 2009-10-15 | 2009-10-15 | 115000 | 0.361 | 0931015
6204 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 0931017 | This pavement project on Sharon Ave. in the Houghton Urban Area will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-09-01 | 2009-09-22 | 2009-10-15 | 2009-10-15 | 88521.77 | 0.480 | 0931017
6205 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 0932213 | North of Sebewaing, MDOT is upgrading 3.6 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-04-14 | 2009-04-14 | 2011-03-31 |  | 140515.08 | 3.588 | 0932213
6206 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 0932214 | West of Port Austin, MDOT is upgrading 4.8 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-04-16 | 2009-04-16 | 2011-03-31 | 2010-05-21 | 293993.36 | 4.886 | 0932214
6207 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 0932219 | There will be 2.68 miles of resurfacing on Atwater Road from Parisville Road easterly to west of Ruth Road to improve the driving quality of the road by making the road smoother. | Pavement Improvement | 2009-07-22 | 2009-08-29 | 2009-09-30 | 2009-09-16 | 355560.72 | 2.940 | 0932219
6208 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 0932220 | Near the city of Sebewaing there are 16.28 miles sidewalk improvements on M-25 from south of Huron Line Road northeasterly to south of Myers Road, from south of Orchard Street northerly to south of De | Transportation Enhancements | 2009-05-29 | 2009-05-29 | 2010-03-31 | 2009-09-19 | 324892.76 | 3.793 | 0932220
6209 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933024 | Near the community of Haslett MI, just over 1/4 miles of Marsh Road will be resurfaced from Baker Street to the north Ingham County Line. This project will improve rideabilty and make the roadway smoother. | Pavement Improvement | 2009-07-02 | 2009-07-27 | 2009-07-31 | 2010-07-28 | 85831.39 | 0.340 | 0933024
6210 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0933025 | Between the cities of Leslie and Eaton Rapids in Ingham County, 6.0 miles of Bellevue Road will have Chip and Seal treatment to preserve pavement life and improve pavement rideabilty. | Pavement Improvement | 2009-05-05 | 2009-07-07 | 2009-09-01 |  | 93999.72 | 6.149 | 0933025
6211 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0933026 | South of Mason in Ingham County, Barnes Road will have Chip and Seal treatment from South College Road to South Meridian Road to preserve pavement life and improve pavement rideability. This project will encompass 6.25 miles of roadway. | Pavement Improvement | 2009-05-05 | 2009-07-20 | 2009-09-01 |  | 93999.85 | 6.474 | 0933026
6212 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933028 | 0.95 miles of South Washington Road from West Jolly Road to Miller Road will be resurfaced in the City of Lansing. Improvements include ADA sidewalk ramp upgrades for increased pedestrian access and mobility. | Pavement Improvement | 2009-08-05 | 2009-08-05 |  | 2009-09-25 | 323264.04 | 0.948 | 0933028
6213 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933029 | In the City of East Lansing, 1 mile of East Mount Hope Avenue will be reconstructed along the southern limits of the city. The new roadway will improve rideablity and improve drainage features. | Pavement Improvement | 2009-07-22 | 2009-07-29 | 2009-10-02 | 2009-10-08 | 681219.99 | 1.471 | 0933029
6214 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 0933030 | West of the Village of Stockbridge, 4.75 miles of Morton and Heeney Roads will have Chip and Seal treatment to preserve pavement life and improve rideability. | Pavement Improvement | 2009-05-21 | 2009-07-20 | 2009-09-01 |  | 62576.43 | 4.079 | 0933030
6215 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933032 | 0.45 miles of Michigan Avenue from US-127 to Friendship Court will be resurfaced in the City of Lansing. Improvements include concrete curb & gutter and sidewalk replacement. The work will improve roadway rideability and pavement smoothness. | Pavement Improvement | 2009-08-05 | 2009-08-17 | 2009-09-21 | 2010-08-25 | 456655.26 | 0.788 | 0933032
6216 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933034 | Near Williamston in Ingham county, MDOT will resurface about 8 miles of I-96 to improve driving quality by making the road smoother. | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2012-03-01 | 2009-11-15 | 3259504.55 | 17.302 | 0933034
6217 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933036 | In the community of Holt in Ingham County, 1.37 miles of West Holt Road from Heatherton Drive to Thornburn Street will be resurfaced to improve rideabilty and make the roadway smoother. | Pavement Improvement | 2009-07-07 | 2009-09-01 | 2009-11-15 | 2010-10-19 | 766216.73 | 1.329 | 0933036
6218 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 0933037 | Near the community of Haslett MI, 1/2 miles of Marsh Road will be resurfaced from Tihart Road to just north of Franklin Street in Ingham County. This project will improve rideabilty and make the roadway smoother. | Pavement Improvement | 2009-09-21 | 2009-10-01 | 2010-05-31 | 2010-12-08 | 501073.56 | 0.789 | 0933037
6219 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 0934011 | The MDOT will resurface 4 miles of M-66 near the City of Ionia. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-12-31 | 2009-06-29 | 894235.57 | 3.902 | 0934011
6220 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 0934014 | The City of Ionia will resurface over a half mile of West Adams Street from M-66 to Jackson Street in the City of Ionia. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-08-31 |  | 2009-09-25 | 259020.75 | 0.691 | 0934014
6221 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 0937007 | Within the City of Mt. Pleasant, MDOT will repair 4.85 miles of US-127 south of the Blanchard Road interchange to extend the service life of the existing road as well as make repairs to the bridge to extend the service life of the bridge. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2011-12-01 |  | 10705176.85 | 10.526 | 0937007
6222 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 0937012 | The City of Rosbush is reconstructing 3.00 miles on Vernon Road from Winn Road easterly to Vandecar Road and from Lincoln Road easterly to Mission Road to improve driving quality by making the road smoother. | Pavement Improvement | 2009-10-05 | 2009-10-09 | 2009-11-06 | 2009-11-12 | 472051 | 3.004 | 0937012
6223 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON |  | 07 | 0938221 | In Jackson County, the County Road Commission will reconstruct East Michigan Avenue from Fox Road to Gillett's Lake Road to improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-04 | 2009-08-17 |  | 2009-11-03 | 624776.04 | 0.755 | 0938221
6224 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 0938222 | In the city of Jackson, Jackson County, the city will resurface 1/2 mile of Ganson Street from Cooper Street to East Avenue. The project will include sidewalk repairs and new ADA ramps to improve pedestrian mobility and safety. | Pavement Improvement | 2009-08-26 | 2009-09-08 |  | 2009-11-03 | 286346.77 | 0.461 | 0938222
6225 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 0938223 | In the city of Jackson, Jackson County, the city will resurface 1/2 mile of West Morrell Street from Brown Street to West Avenue. The project will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-09-08 |  | 2009-11-03 | 300068.85 | 0.502 | 0938223
6226 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 0938224 | In the city of Jackson, Jackson County, the city will reconstruct just under 1/2 mile of North Jackson Street from Glick Highway to Ganson Street to improve driving quality by making the road smoother. | Pavement Improvement | 2009-12-23 | 2010-04-05 | 2010-07-30 | 2010-07-26 | 529102.09 | 0.371 | 0938224
6227 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 0938241 | In Jackson County, the County Road Commission will resurface Springport Road from Shirley Drive to Airport Road to improve just over a mile of road to improve drive quality by making the road smoother. | Pavement Improvement | 2010-02-03 | 2010-05-05 |  | 2010-07-09 | 695624.57 | 1.273 | 0938241
6228 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939011 | MDOT will reconstruct the interchange of I-94 at Westnedge Avenue to a new design and will reconstruct and add a lane in each direction to 1.9 miles of I-94, between Oakland Drive and Lovers Lane, in the Kalamazoo urbanized area. | Pavement Widening | 2009-04-07 | 2009-04-07 | 2012-12-31 |  | 46802075.36 | 5.516 | 0939011
6229 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939012 | "The City of Portage will resurface 1.6 miles of E. Centre Avenue from Portage Road to Westnedge Avenue in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-22 | 2009-07-08 | 2011-07-27 | 2009-09-10 | 900000 | 1.612 | 0939012
6230 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939013 | "The City of Portage will resurface 0.75 miles of E. Kilgore Road from Westnedge Avenue to Grand Elk RR in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-07-20 | 2011-07-27 | 2009-10-16 | 647541.67 | 0.743 | 0939013
6231 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939015 | The Kalamazoo County Road Commisssion will resurface 2.6 miles of S Avenue from Sprinkle Road to 29th Street, in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-31 | 2009-08-24 | 2011-07-27 | 2009-10-21 | 940291.85 | 2.579 | 0939015
6232 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939016 | The Kalamazoo County Road Commisssion will resurface 1 mile of S. 8th Street from R Avenue to Q Avenue, in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-03 | 2009-08-24 | 2011-07-27 | 2009-10-19 | 320496.79 | 1.001 | 0939016
6233 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO |  | 06 | 0939017 | The Kalamazoo County Road Commisssion will resurface 1 mile of N. 12th Street from D Avenue to C Avenue, in the Kalamazoo urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-03 | 2009-08-24 | 2011-07-27 | 2009-10-19 | 395590.35 | 1.005 | 0939017
6234 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939022 | "The City of Kalamazoo will resurface 1.15 miles of E. Cork Street from Westnedge Avenue to Lovers Lane in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-10 | 2009-09-21 |  |  | 493397.75 | 1.151 | 0939022
6235 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939023 | "The City of Kalamazoo will resurface 0.6 miles of Reed Street from Burdick Avenue to Portage Avenue in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-10 | 2009-09-21 |  |  | 194445.25 | 0.606 | 0939023
6236 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939024 | "The City of Kalamazoo will resurface 0.4 miles of S. Burdick Street from Cork Street to Crescent in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-10 | 2009-09-21 |  |  | 179661.5 | 0.434 | 0939024
6237 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939025 | "The City of Kalamazoo will resurface 1.1 miles of Lovers Lane from Cork Street to Kilgore Road in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-10 | 2009-09-21 |  |  | 254334.05 | 1.073 | 0939025
6238 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939026 | "The City of Kalamazoo will resurface 0.25 miles of N. Edwards Street from South Street to Kalamazoo Avenue in the city. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-15 | 2009-09-22 | 2010-05-14 |  | 330192.5 | 0.252 | 0939026
6239 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 0939032 | "The village of Schoolcraft will resurface 1 mile of E. Eliza Street from west village limits to 14th Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-10-20 | 2009-10-21 | 2011-07-27 | 2010-06-14 | 221992.58 | 0.987 | 0939032
6240 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALKASKA |  | 04 | 0940007 | The Kalkaska County Road Commission will resurface 5 miles of County Highway 612 from the east county line to Blue Lake Rd and Darke to Rogers Rd . This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-18 | 2010-06-07 | 2010-06-11 | 2010-06-12 | 285637.3 | 4.687 | 0940007
6241 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941141 | The City of Wyoming will resurface one mile of Prairie Parkway from Byron Center to Burlingame Avenue in the City of Wyoming. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-13 | 2009-07-13 | 2009-09-30 | 2009-10-01 | 461140.4 | 1.000 | 0941141
6242 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941142 | The City of Wyoming will resurface two miles of Burlingame Avenue from 52 Street to 36th Street in the City of Wyoming. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-13 | 2009-07-13 | 2009-09-30 | 2009-10-01 | 847806.13 | 2.030 | 0941142
6243 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941143 | The City of Walker will resurface a half mile of Veteran's Memorial Drive from Riverbend to Maynard Avenue in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-02 | 2009-07-06 | 2009-08-31 | 2009-08-11 | 107983.75 | 0.499 | 0941143
6244 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941144 | The City of Walker will resurface 0.1 of a mile of Three Mile Road from Alpine Avenue to the I-196 exit ramp in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-29 | 2009-07-15 | 2009-08-31 | 2009-08-11 | 269634.14 | 0.130 | 0941144
6245 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941146 | The Kent County Road Commission will resurface two and three quarters of a mile of 5 Mile Road from Gavin Lake Road to Lincoln Lake Road in Kent County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-14 | 2009-09-14 | 2009-09-25 | 2009-10-16 | 672341.54 | 2.745 | 0941146
6246 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941147 | The MDOT will make repairs to the bridges at US-131and Pine Island Drive, Post Road, and 10 Mile Rd to make the bridges last longer. | Bridge Improvement | 2009-04-23 | 2009-04-23 | 2010-12-31 | 2009-11-12 | 1651287.13 | 0.000 | 0941147
6247 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941149 | The City of Grand Rapids will resurface a half mile of Leonard Street from Nixon Street to Collingsdale Avenue in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-30 | 2009-07-13 | 2011-06-15 | 2010-11-13 | 1273577.98 | 0.535 | 0941149
6248 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941150 | The City of Grandville will resurface 0.2 of a mile of Potomac Avenue from 44th Street to Century Center in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-22 | 2009-09-14 | 2009-09-30 | 2009-10-21 | 68678.74 | 0.224 | 0941150
6249 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941151 | The City of Grandville will resurface 0.2 of a mile of Kenowa Avenue from the south City limits to Stonehenge Drive in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-22 | 2009-09-14 | 2009-09-30 | 2009-10-21 | 76696 | 0.170 | 0941151
6250 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941152 | The City of Grandville will resurface 0.4 of a mile of 44th Street from Potomac Avenue to Rivertown Parkway in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-22 | 2009-09-14 | 2009-09-30 | 2009-10-21 | 79502 | 0.373 | 0941152
6251 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941153 | The City of Grandville will resurface 0.1 of a mile of 44th Street from Kenowa Avenue to the I-196 ramp in the City of Grandville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-22 | 2009-09-14 | 2009-09-30 | 2009-10-21 | 79502 | 0.114 | 0941153
6252 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941156 | The City of East Grand Rapids will resurface a 0.3 miles of Lake Drive from the west city limits to Plymouth Road in the City of East Grand Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-30 | 2009-08-03 | 2009-10-31 | 2009-10-30 | 332036 | 0.330 | 0941156
6253 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941158 | The Kent County Road Commission will resurface over 1.5 miles of Patterson Avenue from 44th Street to M-37 in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-11 | 2009-08-13 | 2010-05-15 | 2009-11-04 | 1100000 | 1.596 | 0941158
6254 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941159 | The Kent County Road Commission will resurface two and half miles of 84th Street from Cherry Valley Avenue to Whitneyville Avenue in Kent County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-17 | 2009-08-04 | 2009-10-31 | 2009-10-19 | 606650.43 | 2.508 | 0941159
6255 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941162 | The City of East Grand Rapids will resurface a quarter of a mile of Breton Avenue from the norht city limits to Burton Street in East Grand Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-03 | 2009-08-10 | 2010-06-11 | 2010-06-11 | 300000 | 0.251 | 0941162
6256 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941166 | The MDOT will make repairs to the bridge at M-57 over the White Pine Trail north of Grand Rapids to make the bridge last longer. | Bridge Improvement | 2009-05-28 | 2009-05-28 | 2011-03-31 | 2010-05-21 | 532283.83 | 0.000 | 0941166
6257 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 0941172 | The MDOT is deploying ITS technology on M-6 at I-196, I-96 and at M-11 and M-6 in Kent County, Grand Rapids area to improve mobility and reduce congestion | Safety/Traffic Management | 2009-06-15 | 2009-06-15 | 2011-01-01 |  | 958408.89 | 46.718 | 0941172
6258 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941176 | The MDOT is integrating ITS technoligies on US-131, I-96 and I-196 at 31 locations around Kent County in the Grand Rapids area to improve mobility and reduce congestion. | Safety/Traffic Management | 2009-06-23 | 2009-06-23 | 2012-07-15 |  | 307584.59 | 0.000 | 0941176
6259 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 0941177 | The MDOT will make repairs to the bridge at M-11 over the Grand River in the City of Walker to make the bridge last longer. | Bridge Improvement | 2009-06-23 | 2009-06-23 | 2010-12-31 | 2010-05-01 | 699844.45 | 0.000 | 0941177
6260 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941179 | The City of Grand Rapids will beautify Madison Avenue and Hall Street in the vicinity of Adams St and in the vicinity of Jefferson Ave by building this streetscape. | Pavement Improvement | 2009-10-15 | 2009-11-16 | 2012-09-30 | 2011-09-30 | 660369.34 | 1.373 | 0941179
6261 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941187 | The MDOT will widen almost 4 miles of I-196 freeway from the Grand River East to Fuller Avenue in the Grand Rapids area to improve mobility and reduce congestion | Pavement Widening | 2009-08-18 | 2009-08-18 | 2013-05-31 |  | 28687610.13 | 13.090 | 0941187
6262 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941188 | The MDOT will replace 2 miles of I-196 freeway lighting from the Grand River East to Fuller Avenue in the Grand Rapids area to improve driver visibility. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2011-09-21 |  | 541784.06 | 3.876 | 0941188
6263 | MICHIGAN | Underway | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941189 | The MDOT will replace the I-196 bridges over Lafayette Avenue in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 2009-09-30 | 2009-09-30 | 2011-06-01 |  | 2489775.9 | 0.000 | 0941189
6264 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941190 | The MDOT will replace the Coit Avenue bridge over I-196 in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 2009-08-18 | 2009-08-18 | 2012-12-31 |  | 2679687.79 | 0.000 | 0941190
6265 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 0941203 | The City of Kent City will resurface 0.2 miles of South Main Street from Ball Creek Road to M-46/17 Mile Road in the City of Kent City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-06-22 | 2010-07-06 | 2010-09-10 | 2010-09-09 | 70000 | 0.161 | 0941203
6266 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941206 | The Kent County Road Commission will resurface one and a half miles of Leonard Street from M-44 to Crahen Street in Grand Rapids Township. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-01-14 | 2010-06-14 | 2010-07-30 | 2010-07-30 | 477806.86 | 1.494 | 0941206
6267 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 0941211 | The City of Grand Rapids will resurface 0.2 miles of Lake Drive from Cherry Street to Fuller Avenue in the City of Grand Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-21 | 2010-04-19 | 2010-06-30 | 2010-06-30 | 167553.5 | 0.212 | 0941211
6268 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KEWEENAW |  | 01 | 0942131 | This pavement project on Eagle Harbor Road in Keweenaw County will improve the drive quality and make the road smoother. | Other | 2010-01-14 | 2010-06-10 | 2010-07-01 | 2010-06-24 | 164462 | 3.510 | 0942131
6269 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAKE |  | 02 | 0943229 | The Lake County Road Commission will resurface 5 miles of South Hawkins Rd from US-10 south in the vicinity of Reed City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-02 | 2009-08-03 | 2010-03-01 |  | 91940 | 4.987 | 0943229
6270 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAKE |  | 02 | 0943230 | The Lake County Road Commission will resurface 6 miles of W Star Lake Drive around Star Lake in the Manistee National Forest southwest of the village of Baldwin. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-02 | 2009-08-03 | 2010-03-01 |  | 93284.61 | 6.047 | 0943230
6271 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAKE |  | 02 | 0943231 | The Lake County Road Commission will resurface 5 miles of E 92nd St and S BroadwayRd from S Forman to 96th and from 72nd to 92nd St in the Manistee National Forest. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-02 | 2009-08-03 | 2010-03-01 |  | 88948.07 | 4.797 | 0943231
6272 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAKE |  | 02 | 0943232 | The Lake County Road Commission will resurface 4 miles of West 52nd St from the Baldwin Village limits westward. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-04 | 2009-08-03 | 2010-03-01 |  | 73501 | 3.629 | 0943232
6273 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 0944088 | In the city of Fenton, MDOT is resurfacing existing car pool lots at the US-23 exit to Silver Lake Road, on M-24 north of Barnes Lake Road, on M-90 between Brush Street and Baldwin Avenue, and on M-24 | Pavement Improvement | 2009-04-17 | 2009-04-17 | 2010-12-31 |  | 61606.17 | 0.000 | 0944088
6274 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 0944089 | Within the City of North Branch, MDOT will resurface parking lot on M-90 to improve the quality of the parking surface and extend the life of the road pavement. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2010-12-31 |  | 22729.22 | 0.000 | 0944089
6275 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 0944092 | The city of Lapeer will reconstruct 0.31miles on N Saginaw Street to improve the driving quality by making the road smoother. | Other | 2010-02-10 | 2010-04-05 | 2010-08-13 | 2010-07-28 | 240000 | 0.215 | 0944092
6276 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LEELANAU |  | 04 | 0945329 | MDOT will resurface 16.5 miles of M-72 from the Village of Empire to Bugai Rd. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-09 | 2009-06-09 | 2011-05-05 | 2010-06-24 | 932630.33 | 16.401 | 0945329
6277 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LEELANAU |  | 04 | 0945330 | The MDOT will construct a passing relief lane on M-72 from Cedar Run Rd to Goodrick Rd west of Traverse City. This will allow safer driving operations on M-72. | Pavement Widening | 2009-06-30 | 2009-06-30 | 2011-05-05 | 2010-07-09 | 1409246.4 | 1.124 | 0945330
6278 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LEELANAU |  | 04 | 0945332 | The Leelanau County Road Commission will resurface 1.5 miles of County Road 651 from Hohnke Rd to M-22 in the vicinity of Empire. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-18 | 2009-08-18 | 2010-06-04 | 2010-06-03 | 271725 | 1.585 | 0945332
6279 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON |  | 08 | 0947010 | 8.3 miles of resurfacng of US-23 from I-96 to M-59 just north of Brighton in Livingston County. This project will provide for improved rideability and increased pavement smoothness. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-02-09 | 2009-10-10 | 3118815.4 | 16.563 | 0947010
6280 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON |  | 08 | 0947011 | A new Carpool lot will be constructed at Burkhart Road just west of M-59 near the I-96 Interchange west of Howell. This lot will encourage ridesharing and reduce the number of cars on the roadway. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-30 | 2010-09-30 | 165675.41 | 0.020 | 0947011
6281 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947012 | MDOT will improve mobility and reduce congestion with installation of an Intelligent Transportation System (ITS) along I-96 from the city of Fowlerville easterly to the Oakland/Livingston County line | Safety/Traffic Management | 2009-06-15 | 2009-06-15 | 2010-12-31 |  | 533441.41 | 69.774 | 0947012
6282 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947015 | This project will provide for 1.5 miles of pavement resurfacing on East Grand River Avenue from Lake Chemung to 1/3 of a mile east of Hughes Road between the cities of Howell and Brighton in Livingsto | Pavement Improvement | 2009-09-18 | 2009-09-22 | 2010-06-30 | 2009-11-16 | 1157821.59 | 1.517 | 0947015
6283 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947016 | This project will provide for 0.40 miles of pavement resurfacing on Main Street from Third Avenue to Grand River Avenue in the city of Brighton, Livingston County. This will provide for improved pavement rideability and increased pavement smoothness. | Pavement Improvement | 2009-09-21 | 2009-10-13 |  | 2009-11-03 | 254732.5 | 0.402 | 0947016
6284 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON |  | 08 | 0947018 | This project will provide for 2 miles of pavement resurfacing on Old US-23 from Dean Road to Faussett, north of the city of Brighton in Livingston County. This will provide for improved pavement rideability and increased pavement smoothness. | Pavement Improvement | 2010-01-14 | 2010-05-10 |  | 2010-07-09 | 387535.68 | 2.056 | 0947018
6285 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947020 | This project will provide for 1.1 miles of pavement resurfacing on North Michigan Avenue from Grand River Avenue to M-59 in the city of Howell, Livingston County. This will provide for improved pavement rideability and increased pavement smoothness. | Pavement Improvement | 2009-10-07 | 2009-10-16 | 2009-11-14 | 2009-11-25 | 289075.98 | 1.104 | 0947020
6286 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON | SOUTH LYON-HOWELL-BRIGHTON | 08 | 0947021 | 1/3 of a mile of Walnut Street is being resurfaced from Maple Street to Clinton Street in the City of Howell, Livingston County to make the roadway smoother and improve ride quality. | Pavement Improvement | 2009-10-07 | 2009-10-16 | 2009-11-14 | 2009-11-25 | 100587.13 | 0.349 | 0947021
6287 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACKINAC |  | 01 | 0949011 | This pavement and Rumble Strip project on US-2 in Mackinac County will improve safety and make the road smoother. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-10-18 | 2009-10-01 | 2541340.8 | 6.012 | 0949011
6288 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950035 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of 12 Mile Road in Macomb County. | Pavement Improvement | 2009-07-27 | 2009-08-03 | 2009-09-30 | 2010-10-05 | 477842.61 | 0.465 | 0950035
6289 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB |  | 10 | 0950036 | Resurfacing to maintain the pavement condition and improve ride quality of ramps at I-94 at 9 Mile Road, 10 Mile Road, and 23 Mile Road, and on M-19 in the city of St. Clair Shores by MDOT. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2011-06-30 | 2009-11-20 | 523547.97 | 0.897 | 0950036
6290 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950037 | Resurfacing to maintain the pavement condition and improve ride quality of Ten Mile Road in Eastpointe. | Pavement Improvement | 2009-08-04 | 2009-08-15 | 2009-11-30 | 2009-11-30 | 318522.68 | 0.505 | 0950037
6291 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950038 | One mile of resurfacing to maintain the pavement condition and improve ride quality of 10 Mile Road in East Pointe and Center Line. | Pavement Improvement | 2009-08-04 | 2009-08-15 | 2009-11-30 | 2009-11-30 | 468171.04 | 0.839 | 0950038
6292 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB |  | 10 | 0950040 | Resurfacing to maintain the pavement condition and improve ride quality of M-19 near Richmond by MDOT. | Pavement Improvement | 2009-05-29 | 2009-05-29 | 2011-06-30 | 2009-11-20 | 2093831.25 | 4.112 | 0950040
6293 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB |  | 10 | 0950041 | Three miles of microsurfacing to preserve the pavement condition and improve ride quality of North Avenue and 26 Mile Road in Macomb County. | Pavement Improvement | 2009-09-08 | 2009-09-16 | 2009-10-30 | 2009-10-08 | 293071.55 | 3.321 | 0950041
6294 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950045 | 2 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along 15 Mile Road in Sterling Heights by MDOT. | Pavement Improvement | 2009-09-10 | 2009-09-14 | 2010-06-30 | 2010-09-21 | 2065023.01 | 2.226 | 0950045
6295 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950046 | Two and a half miles of resurfacing to maintain the pavement condition and improve ride quality of M-3 in Mount Clemens by MDOT. | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-06-01 | 2010-12-21 | 4278652.53 | 1.705 | 0950046
6296 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950051 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Schoenherr Road in Macomb County. | Pavement Improvement | 2009-10-06 | 2009-10-14 | 2009-11-01 | 2009-11-05 | 282091.8 | 1.002 | 0950051
6297 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950058 | 2 mile application of a preventive maintenace treatment to improve safety, smoothness, and extend the service life of the existing pavement on Washington Street in New Baltimore by MDOT. | Pavement Improvement | 2009-12-23 | 2010-05-12 | 2010-05-28 | 2010-05-28 | 267913.12 | 2.094 | 0950058
6298 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950059 | 2 miles of resurfacing to maintain the pavement condition and improve ride quality of 14 Mile Road in Sterling Heights. | Pavement Improvement | 2010-02-02 | 2010-04-21 | 2010-07-31 | 2010-07-26 | 1402973.96 | 0.940 | 0950059
6299 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 0950060 | Resurfacing to maintain the pavement condition and improve ride quality of 14 Mile Road in Clinton. | Pavement Improvement | 2010-02-02 | 2010-04-21 | 2010-07-31 | 2010-07-26 | 1116941.32 | 1.370 | 0950060
6300 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MANISTEE |  | 02 | 0951308 | The Mainistee County Road Commission will resurface 4 miles of Stronach Rd from M-55 to Eastlake Rd in the vicinity of the Village of Eastlake in the Manistee National Forest. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-17 | 2009-09-26 | 2009-11-01 | 2010-10-08 | 362028 | 3.564 | 0951308
6301 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MANISTEE |  | 02 | 0951309 | The Mainistee County Road Commission will resurface 1 miles of Stronach Rd from US-31 to Grant south of the the City of Manistee. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-17 | 2009-09-26 | 2009-11-01 | 2010-10-08 | 56829.78 | 0.927 | 0951309
6302 | MICHIGAN | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952006 | This pavement project on US-41 in the City of Marquette will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 |  | 2009-06-10 | 512700.28 | 2.056 | 0952006
6303 | MICHIGAN | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952007 | This pavement resurfacing and rumble strip project on US-41 in the City of Marquette will improve safety and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-10-18 | 2009-06-03 | 473005.46 | 1.930 | 0952007
6304 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952009 | This roundabout project in Marquette County at the intersection of US-41/M-28 and Front Street will improve safety. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2011-10-21 | 2010-08-20 | 3433920.95 | 4.224 | 0952009
6305 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952014 | This paving project on County Road 557 in Marquette County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-09-28 | 2010-06-21 | 2010-08-01 | 2010-07-31 | 641383.21 | 2.207 | 0952014
6306 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952016 | This pavement project on Champion Street in the City of Marquette will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-28 | 2009-09-08 | 2010-08-15 | 2010-07-03 | 465000 | 0.360 | 0952016
6307 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952020 | This pavement project on M-94 in Marquette County will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-08-04 | 2009-08-04 |  | 2011-07-28 | 730059.32 | 9.499 | 0952020
6308 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 0952025 | This pavement project on M-28 BR in the City of Ishpeming will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-05-11 | 2009-05-11 |  | 2010-06-30 | 406520.44 | 3.901 | 0952025
6309 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MASON |  | 02 | 0953021 | MDOT will resurface 0.5 miles of US-10 at Dowland St in the vicinity of the Lake Michigan Car Ferry in Ludington. This will improve the driving quality by making the road smoother and provide better access to the ferry. | Pavement Improvement | 2009-06-04 | 2009-06-04 | 2011-05-05 | 2009-11-06 | 349651.65 | 0.470 | 0953021
6310 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MASON |  | 02 | 0953024 | The City of Ludington will design improvements to 0.2 miles of South Williams St from Ludington Ave to Filer St in Ludington so as to improve the driving quality by making the road smoother. | Other | 2009-08-18 | 2009-08-25 | 2010-06-25 | 2010-01-25 | 13248 |  | 0953024
6311 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954007 | The MDOT will resurface 2 miles of US-131BR/M-20 from US-131 east to Northland Drive near the City of Big Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-03-30 | 2009-09-25 | 440527.94 | 3.630 | 0954007
6312 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954008 | The MDOT will resurface 2 miles of US-131BR/M-20 from US-131 east to Northland Drive near the City of Big Rapids. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2010-03-30 | 2009-08-05 | 810015.65 | 4.356 | 0954008
6313 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954009 | The MDOT will make repairs to the bridge at Old State Road over US-131 near the Village of Stanwood to make the bridge last longer. | Bridge Improvement | 2009-05-21 | 2009-05-21 | 2010-12-31 |  | 597081.11 | 0.000 | 0954009
6314 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954010 | The Mecosta County Road Commission will resurface 20 Mile Road from 60th Ave to 50th Ave west of the Village of Barryton. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-24 | 2009-10-01 | 2009-11-14 | 2009-11-14 | 87420.72 | 1.008 | 0954010
6315 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954011 | Improvements will be made to guard rail on Arthur Road from 10th Avenue to Costabella Road west of the Village of Lake Isabella to improve safety. | Pavement Improvement | 2009-06-24 | 2009-10-01 | 2009-11-14 | 2009-11-14 | 121716.85 | 1.002 | 0954011
6316 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 0954012 | The Mecosta County Road Commission will resurface Pierce Road from front St to 110th Ave in the village of Stanwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-24 | 2009-10-01 | 2009-11-14 | 2009-11-14 | 233284 | 7.333 | 0954012
6317 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 0956007 | Within the cities of Midland, Auburn and Bay, MDOT will be upgrading 16 bridge decks on US-10 from Sturgeon Road easterly to I-75 and on M-20/US-10BR from Saginaw Road easterly to Waldo Road to make the bridges last longer. | Bridge Improvement | 2009-05-29 | 2009-05-29 | 2011-04-11 |  | 277823.6 | 0.000 | 0956007
6318 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 0956009 | The city of Midland will resurface 2.8 miles on Gordonville Road to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-24 | 2009-07-24 | 2009-10-30 | 2010-09-15 | 548649.37 | 9.392 | 0956009
6319 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 0956010 | In the city of Midland there is 17.20 miles of resurfacing on Smith Crossing Road, Freeland Road, Pine River Road, Nine Mile Road, Shepherd Road, Gordonville Road, Jefferson Road, Prairie Road, Eastma | Pavement Improvement | 2009-07-30 | 2009-07-30 | 2009-10-30 | 2010-09-15 | 341111.26 | 8.757 | 0956010
6320 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 0956011 | The city of Midland will resurface 4.16 miles on M-20 from west of Meridian Road easterly to east of Vance Road to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-29 | 2009-09-29 | 2012-02-01 | 2010-08-05 | 1837630.28 | 4.015 | 0956011
6321 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MISSAUKEE |  | 04 | 0957004 | The Missaukee Couth Road Commission willl resurface 5.5 miles of Falmouth/Hildebrand/Cadilac/Lucas Rds between M-66 and Dikerson Rd in the vicinity of Cadilac. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-10-12 | 2009-10-19 | 2010-06-12 | 2009-10-27 | 277431.16 | 5.530 | 0957004
6322 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 0958011 | 0.39 miles of pavement resurfacing on West 7th Street from Telegraph Road to Union Street in the city of Monroe, Monroe County. This project will improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2009-09-17 | 2009-10-05 | 2009-11-01 | 2009-11-01 | 154753.89 | 0.780 | 0958011
6323 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 0958012 | 0.17 miles of pavement resurfacing on Riverview Avenue from Scottwood Street to Maywood Street in the city of Monroe, Monroe County. This project will improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2009-09-15 | 2009-09-28 | 2009-11-15 | 2009-11-03 | 184262.69 | 0.173 | 0958012
6324 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959004 | The MDOT will resurface seven and a half miles of M-91 from north of Colby Rd to north of Kedalville Rd near the village of Lakeview. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-22 | 2009-04-02 | 2009-11-14 | 2009-08-04 | 406541.43 | 7.455 | 0959004
6325 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959008 | The Moncalm County Road Commission will resurface South Youngman Rd from M-57 to Harlow Rd east of Greenville. This will improve the driving quality by making the road smoother. | Pavement Widening | 2009-08-12 | 2009-08-13 | 2009-09-18 | 2009-11-02 | 85143.78 | 0.757 | 0959008
6326 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959009 | The MDOT will resurface seven miles of M-57 from Berridge Rd to east of M-66 near the City of Greenville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-26 | 2009-07-01 | 2010-03-30 | 2009-07-31 | 874005.49 | 7.053 | 0959009
6327 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959010 | The MDOT will resurface six miles of M-46 from US-131 to west of Amble Rd near the village of Lakeview. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-04 | 2009-06-04 | 2010-03-30 | 2009-09-02 | 746003.4 | 5.945 | 0959010
6328 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 0959011 | The Montcalm County Road Commission will resurface South Vickeryville Rd from Stanton Rd to Sidney Rd. near the village of Stanton. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-17 | 2009-09-22 | 2009-10-30 | 2009-10-27 | 440419.07 | 2.689 | 0959011
6329 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON |  | 02 | 0961134 | The MDOT will make repairs to the bridge at Fruitport Rd over I-96 and the bridge at Russell Rd over US-31in Muskegon County to make the bridges last longer. | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2011-09-21 | 2010-08-30 | 1414742.12 | 0.000 | 0961134
6330 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON |  | 02 | 0961135 | The MDOT will build a roundabout at M-37 and M-46 intersection and resurface M-37 from M-46 to Moon Rd for 2 miles west of the village of Casanovia to improve safety and road smoothness. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2012-12-31 |  | 3396704.86 | 3.977 | 0961135
6331 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961138 | The City of Muskegon will resurface a half mile of Laketon Ave from Peck St to Wood St. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-27 | 2009-08-18 | 2009-11-15 | 2009-11-21 | 800000 | 0.504 | 0961138
6332 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961139 | The City of Whitehall will resurface 3 tenths of a mile of Mears Ave from Lincoln Rd to Misco Drive. This will improve driving quality by making the road smoother. Needed utility work will also be done at this time by the city. | Pavement Improvement | 2009-09-03 | 2009-09-08 | 2009-10-16 | 2009-11-06 | 200000 | 0.285 | 0961139
6333 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961140 | The City of Montague will resurface a block of Old Channel Trail from Dowling St to Church St. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-09-02 | 2009-09-30 | 2009-09-26 | 35539.31 | 0.073 | 0961140
6334 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961141 | The City of Montegue will resurface a one tenth of a mile of Dowling St from Meade St to Ferry St. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-09-02 | 2010-12-31 | 2009-09-26 | 50000 | 0.111 | 0961141
6335 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961142 | The City of Muskegon will resurface 0.4 mile of Summit Ave from west of Henry St to Coolidge Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-31 | 2009-09-08 | 2010-12-31 | 2009-09-30 | 178180.35 | 0.355 | 0961142
6336 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961143 | The City of Norton Shores will resurface 0.8 miles of Pontaluna Rd Grand Haven Rd to Wood Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-25 | 2009-09-08 | 2010-12-31 | 2010-11-13 | 503211 | 0.769 | 0961143
6337 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0961150 | The City of North Muskegon will resurface 0.6 miles of Ruddiman Drive from Center St to Whitehall Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 2010-02-16 | 2010-04-27 | 2010-05-28 | 2010-06-11 | 200000 | 0.599 | 0961150
6338 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963182 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Crooks Road in Oakland County. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-11-15 | 2010-11-23 | 802000 | 1.145 | 0963182
6339 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963183 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Campbell Road in Madison Heights and Royal Oak. | Pavement Improvement | 2009-05-14 | 2009-07-27 | 2012-09-01 |  | 1153712.67 | 0.990 | 0963183
6340 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963184 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Orchard Lake Road in Oakland County. | Pavement Improvement | 2009-07-31 | 2009-08-18 | 2009-10-23 | 2009-11-24 | 415000 | 1.012 | 0963184
6341 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND |  | 09 | 0963185 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Square Lake Road in Bloomfield Township by MDOT. | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2012-12-31 | 2010-05-10 | 5706880.5 | 2.563 | 0963185
6342 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963196 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of 10 Mile Road in Oakland County. | Pavement Improvement | 2009-08-10 | 2009-08-13 | 2009-10-09 | 2009-10-27 | 512000 | 0.536 | 0963196
6343 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963197 | Resurfacing to maintain the pavement condition and improve ride quality of Rochester Road in Clawson. | Pavement Improvement | 2009-07-31 | 2009-08-17 | 2009-10-02 | 2009-10-16 | 350000 | 0.510 | 0963197
6344 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963199 | 5.6 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along M-59 in Rochester Hills by MDOT. | Pavement Widening | 2009-06-02 | 2009-06-02 | 2013-01-19 |  | 56150066.45 | 11.892 | 0963199
6345 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963208 | 2 miles of resurfacing to maintain the pavement condition and improve ride quality of M-59 in Pontiac. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-06-30 |  | 11372044.48 | 6.259 | 0963208
6346 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963209 | Resurfacing to maintain the pavement condition and improve ride quality of East Progress Drive in Madison Heights by MDOT. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2010-12-15 | 2010-11-13 | 405273.61 | 0.832 | 0963209
6347 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963211 | Two miles of resurfacing to maintain the pavement condition and improve ride quality of Orchard Lake Road in Oakland County. | Pavement Improvement | 2009-09-03 | 2009-09-08 | 2010-06-15 | 2010-06-15 | 1749000 | 2.095 | 0963211
6348 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963212 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Crooks Road in Oakland County. | Pavement Improvement | 2009-08-28 | 2009-09-10 | 2015-12-31 | 2010-06-22 | 879000 | 1.235 | 0963212
6349 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963215 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Novi Road in Novi. | Pavement Improvement | 2009-09-10 | 2009-09-16 | 2009-11-02 | 2009-11-17 | 827000 | 1.004 | 0963215
6350 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963220 | 2 miles of concrete pavement repairs to maintain the pavement condition and improve ride quality of Halsted Road in Farmington Hills. | Pavement Improvement | 2009-07-22 | 2009-07-22 | 2010-09-25 | 2010-10-12 | 1100070.48 | 1.622 | 0963220
6351 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963224 | Resurfacing to maintain the pavement condition and improve ride quality of Nine Mile Road in Novi. | Pavement Improvement | 2009-09-24 | 2009-10-03 | 2010-06-15 | 2010-07-17 | 328000 | 1.026 | 0963224
6352 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963225 | Three miles of resurfacing to maintain the pavement condition and improve ride quality of Meadowbrook Road in Novi. | Pavement Improvement | 2009-09-24 | 2009-10-03 | 2010-06-15 | 2010-07-17 | 340000 | 1.000 | 0963225
6353 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963226 | Resurfacing to maintain the pavement condition and improve ride quality of Nine Mile Road in Novi. | Pavement Improvement | 2009-09-24 | 2009-10-03 | 2010-06-15 | 2010-07-17 | 340000 | 1.038 | 0963226
6354 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963239 | Bridge replacement to improve safety and maintain mobility of Opdyke Road over M-59 in Pontiac by MDOT. | Bridge Improvement | 2009-08-18 | 2009-08-18 | 2013-01-19 | 2010-07-30 | 2774492.05 | 0.000 | 0963239
6355 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963240 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Cass Avenue in Pontiac by MDOT. | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-05-05 | 2010-09-01 | 1832013.03 | 1.183 | 0963240
6356 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 0963264 | One mile of resurfacing to maintain the pavement condition and improve ride quality of John R Road in Troy. | Pavement Improvement | 2010-02-04 | 2010-04-01 | 2010-07-02 | 2010-07-08 | 837000 | 1.028 | 0963264
6357 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OCEANA |  | 02 | 0964332 | The MDOT will make repairs to the bridge at Taylor Rd over US-131 in Oceana County to make the bridge last longer. | Bridge Improvement | 2009-05-29 | 2009-05-29 | 2011-03-31 | 2010-05-17 | 676421.28 | 0.000 | 0964332
6358 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OCEANA |  | 02 | 0964340 | The Oceana County Rd Commission will resurface 3 miles of West Shelby Rd from 52nd Ave to 40th Ave west of the Village of Shelby. This will improve the driving quality of the raodway | Other | 2010-02-26 | 2010-05-03 | 2010-05-28 | 2010-06-03 | 446345 | 3.026 | 0964340
6359 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 0965009 | MDOT will repair 10.6 miles of I-75 from the south Ogemaw County line to Cook Rd and from Ski Park Rd to the north county linein Ogemaw County to extend the service life of the existing roadway. | Pavement Improvement | 2008-12-30 | 2008-12-30 | 2009-06-18 | 2009-06-18 | 897731.5 | 11.057 | 0965009
6360 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 0965010 | MDOT will design repairs to drainage culverts along I-75 in Ogemaw County to improve drainage and extend the life of the roadway drainage structures. | Other | 2009-04-23 | 2009-04-23 |  |  | 9046.69 |  | 0965010
6361 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 0965011 | MDOT will fix drainage culverts along I-75 in Ogemaw County to improve drainage and extend the life of the roadway drainage structures. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-06-01 | 2010-06-01 | 1104499.82 | 10.034 | 0965011
6362 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ONTONAGON |  | 01 | 0966008 | This paving project on M-64 from Silver City to The City of Ontonagon will improve the drive quality and make the road smoother. | Pavement Improvement | 2009-04-02 | 2009-04-02 | 2010-10-18 | 2009-10-02 | 2576015.29 | 11.840 | 0966008
6363 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 0967010 | MDOT will design the resurfacing of 2 miles of US-10 from the west county line of Osceola to the US-131 interchange in the vicinity of Reed City. This will improve the driving quality by making the road smoother. | Other | 2009-04-29 | 2009-04-29 |  |  | 46696.66 |  | 0967010
6364 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 0967011 | MDOT will resurface 2 miles of US-10 from the west county line of Osceola to the US-131 interchange in the vicinity of Reed City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2011-03-03 | 2010-10-15 | 1257647.3 | 1.890 | 0967011
6365 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 0967015 | The Osceola County Road Commission will resurface 4 and a quarter miles of 200th Ave from 20 Mile Rd to the county line in the vicinity of the village of Tustin. This will improve the driving quality by making the road smoother. | Other | 2009-07-29 | 2009-10-27 | 2010-10-30 | 2011-03-24 | 146233 | 4.263 | 0967015
6366 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 0968003 | The Oscoda County Road Commission will replace the bridge on Waterwheel Court over Big Creek to improve safety and increase mobility. | Bridge Replacement | 2009-09-23 | 2010-03-17 | 2010-07-30 | 2010-08-03 | 87616.5 | 0.309 | 0968003
6367 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTSEGO |  | 01 | 0969014 | MDOT will resurface 5 miles of M-32 from east of Krys Rd to Turtle Lake Rd east of Gaylord. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2009-10-08 | 2009-10-08 | 385285.55 | 9.855 | 0969014
6368 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTSEGO |  | 01 | 0969016 | The Otsego County Road Commission will reconstruct 1.5 miles of Charles Brink Rd from E of Championship Dr to Opal Lake Rd in the vicinity of Otsego Lake. This will improve the driving quality by making the road smoother. | Other | 2009-09-18 | 2009-09-21 | 2009-11-13 | 2009-11-13 | 331098 | 1.565 | 0969016
6369 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | HOLLAND | 02 | 0970019 | Almost 2 miles of Lakewood Blvd from River Ave to 120th Ave will be resurfaced in Holland Township. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-25 | 2009-07-01 | 2009-07-31 | 2009-07-29 | 580277.36 | 1.704 | 0970019
6370 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970020 | Five miles of 48th Ave will be resurfaced near the City of Hudsonville and in Georgetown Township from Chicago Drive to Bauer Rd. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-26 | 2009-07-01 | 2009-08-14 | 2009-08-26 | 1144923.47 | 4.672 | 0970020
6371 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 0970022 | The City of Holland will resurface almost 2 miles of Lakewood Blvd from River Ave to 120th Ave. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-26 | 2009-07-01 | 2009-08-14 | 2009-07-30 | 439912.71 | 1.965 | 0970022
6372 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 0970024 | The MDOT will make repairs to the I-196 bridges over 48th St near the City of Grandville to make the bridges last longer. | Bridge Improvement | 2009-04-28 | 2009-04-28 | 2010-12-31 | 2010-08-26 | 622318.66 | 0.000 | 0970024
6373 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 0970026 | The MDOT will resurface 6 miles of I-96 from M-104 to 68th Ave in the vicinity of Spring Lake. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2011-04-01 | 2009-09-01 | 1558066.92 | 11.106 | 0970026
6374 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0970034 | The Ottawa County Road Commission will resurface 2 miles of Lake michigann Dr from Lakeshore Ave to US-31. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-23 | 2009-07-30 | 2009-09-11 | 2009-08-13 | 342132.32 | 1.960 | 0970034
6375 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970037 | The MDOT will resurface 1 mile of I-196 BL from US-31 east to the Macatawa River near the City of Holland. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-09 | 2009-06-09 | 2010-03-30 | 2009-11-30 | 358122.14 | 1.355 | 0970037
6376 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970038 | The MDOT will resurface 9 miles of I-196 from 64th Ave to Kenowa Ave near Hudsonville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-10 | 2009-06-10 | 2011-09-21 | 2010-06-08 | 2406902.54 | 13.499 | 0970038
6377 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970039 | The MDOT will resurface 11 miles of M-45 from US-31 east to 68th Ave near the city of Grand Haven. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-06-10 | 2009-06-10 | 2010-03-30 | 2009-10-02 | 1428909.36 | 11.095 | 0970039
6378 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0970040 | The City of Grand Haven will resurface three quarters of a mile of Robbins Rd from just east of US-31 to Beechtree St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-22 | 2009-09-25 | 2010-12-31 | 2010-06-29 | 230691 | 0.721 | 0970040
6379 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0970041 | The City of Spring Lake will resurface 0. 2 miles of West Springlake Rd from Smith's Bridge to Bayberry Dr. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-26 | 2009-09-08 | 2009-10-31 | 2009-11-30 | 200000 | 0.220 | 0970041
6380 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 0970044 | The MDOT will resurface a half mile of US-31 south bound from the Grand River bascule bridge to 3rd St including M-104 in the city of Ferrysburg. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-10 | 2009-07-10 | 2010-06-30 | 2009-10-05 | 264725.75 | 0.905 | 0970044
6381 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | MUSKEGON-MUSKEGON HEIGHTS | 02 | 0970051 | The City of Spring Lake will resurface 0. 2 miles of Jackson St at Exchange St and at West Savidge (M-104). This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-19 | 2010-04-05 | 2010-06-25 | 2010-06-15 | 183407.05 | 0.162 | 0970051
6382 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 0970053 | The MDOT will make repairs to the I-96 bridge over west bound M-11 near the City of Grand Rapids to make the bridge last longer. | Bridge Improvement | 2010-02-16 | 2010-03-02 | 2011-03-31 | 2010-07-01 | 239412.06 | 0.000 | 0970053
6383 | MICHIGAN | Completed | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ROSCOMMON |  | 04 | 0972006 | The MDOT is upgrading the guard rail along 17.5 miles of US-127 in Roscommon County from Snow Bowl Rd north to I-75 to improve safety. | Safety/Traffic Management | 2009-04-02 | 2009-04-02 | 2009-07-10 | 2009-07-10 | 232098.65 | 30.285 | 0972006
6384 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973027 | In the city of Saginaw, MDOT is making repairs on M-46 to make the bridge last longer. | Bridge Improvement | 2009-05-11 | 2009-05-11 | 2011-02-20 | 2010-11-15 | 996127.45 | 0.000 | 0973027
6385 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973028 | Within the city of Saginaw, MDOT will reconstruct 1.20 miles of M-13 to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-29 | 2009-05-29 | 2012-09-19 | 2012-09-19 | 5789128.68 | 1.258 | 0973028
6386 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973030 | The City of Saginaw is resurfacing 1.48 miles on Outer Drive to improve driving quality by making the road smoother. | Pavement Improvement | 2009-08-14 | 2009-08-17 | 2009-11-13 | 2009-11-23 | 1844073 | 1.484 | 0973030
6387 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973033 | The City of Chesaning is resurfacing 7 miles on S Hemlock Road to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 80000 | 10.750 | 0973033
6388 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973034 | The Saginaw County Road Commission is resurfacing 5.105 miles on Ditch Road south of Chesaning to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 80716.1 | 5.105 | 0973034
6389 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973035 | The City of Frankenmuth is resurfacing 5.03 miles on S Dehmel Road to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 80000 | 4.949 | 0973035
6390 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973036 | The City of Bridgeport is resurfacing 5.37 miles on Busch Rd & Moorish Rd to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 85000 | 5.348 | 0973036
6391 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973037 | The Saginaw County Road Commission is resurfacing 3.9 miles on Fergus Road from Sharon Rd to Bishop Rd near the Village of St. Charles to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-05-01 |  | 67368.88 | 3.943 | 0973037
6392 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 0973038 | In Tittabawassee Township there is 5 miles of resurfacing on Mackinaw Rd & Lawndale Rd to improve driving quality by making the road smoother. | Pavement Improvement | 2009-07-07 | 2009-07-13 | 2010-04-01 |  | 80000 | 4.996 | 0973038
6393 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973041 | In the city of Saginaw there will be 0.98 miles reconstruction on East Genesee Avenue from Franklin Street to Janes Street to improve the driving quality and make the road smoother. | Pavement Improvement | 2009-12-22 | 2010-03-08 | 2012-09-18 |  | 934074 | 0.427 | 0973041
6394 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973042 | The city of Saginaw will beautify 0.45 miles along W Genesee Avenue. | Transportation Enhancements | 2009-12-22 | 2010-03-08 | 2012-09-18 |  | 510000 | 0.427 | 0973042
6395 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973051 | The city of Saginaw will reconstruct 0.51 miles on North Woodbridge Street from Houghton Avenue to Davenport Avenue to improve the driving quality by making the road smoother. | Other | 2010-02-01 | 2010-04-26 | 2010-10-23 |  | 400000 | 0.555 | 0973051
6396 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW | SAGINAW | 04 | 0973053 | There is 15.39 miles of resurfacing on M-46 from Towerline Road easterly to west of M-15 and on M-84 from M-58 (State Street) northerly to north of Pierce Road to improve the driving quality by making the road smoother. | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2012-03-01 | 2010-10-08 | 3374881.08 | 15.434 | 0973053
6397 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | SANILAC |  | 10 | 0974004 | North of Port Sanilac, MDOT is upgrading 6.8 miles to create a paved pathway on M-25 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-05-29 | 2009-05-29 | 2010-03-31 | 2009-09-19 | 402983.46 | 6.824 | 0974004
6398 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 0975013 | This shoulder paving project on County Road 498 in Schoolcraft County will improve safety. | Pavement Improvement | 2009-05-11 | 2009-07-27 | 2010-03-01 |  | 91271 | 3.958 | 0975013
6399 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 0975014 | This shoulder paving project on Thunder Lake Road in Schoolcraft County will improve safety. | Pavement Improvement | 2009-05-11 | 2009-08-17 | 2010-03-01 |  | 91680 | 10.314 | 0975014
6400 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 0975016 | This shoulder paving project on County Road 436 in Schoolcraft County will improve safety. | Pavement Improvement | 2009-09-01 | 2009-09-16 | 2010-09-30 | 2010-08-31 | 93904 | 2.998 | 0975016
6401 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 0976208 | Near the city of Perry in Shiawausee county, MDOT will improve the driving surface of nearly 8 miles of I-96 with a resurfacing project. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2011-06-16 |  | 3682328.68 | 15.748 | 0976208
6402 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 0976211 | 0.2 of a mile of pavement resurfacing of East King Street from North Dewey Street to North Gould Street, in the city of Owosso, Shiawausee County. This project will improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2009-08-28 | 2009-10-02 | 2009-11-01 | 2009-11-05 | 100000 | 0.250 | 0976211
6403 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 0976212 | 0.14 miles of pavement resurfacing of North Park Street from M-21 to Mason Street, in the city of Owosso, Shiawausee County. This project will improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2009-08-28 | 2009-10-02 | 2009-11-01 | 2009-11-05 | 100000 | 0.135 | 0976212
6404 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 0976213 | 0.24 miles of pavement resurfacing on Maple Street from M-71 to Main Street near the City of Durand, Shiawausee County. Improvements will enhance pavement rideability and increase pavement smoothness. | Pavement Improvement | 2009-09-25 | 2009-09-28 | 2009-11-30 | 2009-10-28 | 52000 | 0.244 | 0976213
6405 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 0977015 | The Michigan Department of Transportation will realign and make improvements to numerous local streets that cross under the Blue Water Bridge in Port Huron. The project will improve local traffic move | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2011-10-01 | 2011-09-19 | 839466.23 | 0.618 | 0977015
6406 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 0977029 | 0.3 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along Collard Drive in Marysville. | Pavement Improvement | 2010-01-06 | 2010-06-15 | 2011-05-30 | 2010-10-07 | 399774.48 | 0.288 | 0977029
6407 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR |  | 10 | 0977031 | One mile of resurfacing to maintain the pavement condition and improve ride quality of Dryden Road in St. Clair County. | Pavement Improvement | 2009-09-03 | 2009-10-21 | 2009-10-30 | 2009-11-13 | 213948 | 1.031 | 0977031
6408 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 0977035 | Half mile of resurfacing to maintain the pavement condition and improve ride quality of Riverside Drive in Port Huron. | Pavement Improvement | 2009-08-25 | 2009-09-03 | 2009-10-30 | 2009-10-19 | 279566.02 | 0.573 | 0977035
6409 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 0977040 | 10 miles of resurfacing to maintain the pavement condition and improve ride quality of M-25 in St. Clair by MDOT. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2011-04-11 | 2010-10-15 | 6196432.86 | 10.708 | 0977040
6410 | MICHIGAN | Underway | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR |  | 10 | 0977042 | Bridge replacement to improve safety and maintain mobility of I-94 over the Belle River in St. Clair County by MDOT. | Bridge Replacement | 2009-12-02 | 2009-12-02 | 2012-10-08 |  | 6401261.78 | 0.000 | 0977042
6411 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR |  | 10 | 0977044 | 3.6 miles of complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty on I-94 in St. Clair County. | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2013-01-19 |  | 19217011.84 | 4.479 | 0977044
6412 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 0979010 | MDOT is upgrading 6.0 miles to create a paved pathway on M-15 for cyclists, walkers, and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2009-06-02 | 2009-06-02 | 2010-03-31 | 2009-09-19 | 417499.15 | 6.047 | 0979010
6413 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 0979014 | In the village of Mayville, Tuscola County there will be 0.20 miles of roadway reconstruction on Industrial Park Road at M-24 to improve the driving quality and make the road smoother. | Pavement Improvement | 2009-09-28 | 2009-10-05 | 2010-06-01 | 2010-11-17 | 49790.9 | 0.120 | 0979014
6414 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 0980009 | "The City of Hartford will resurface 0.5 miles of W. Main Street from the city limits to Center Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-20 | 2009-09-21 | 2011-07-27 | 2009-10-21 | 178400.27 | 0.501 | 0980009
6415 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 0980013 | "The village of Decatur will resurface 0.4 miles of N. Phelps Street (CR 653) from the village limits to Cedar Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-08-28 | 2009-09-16 | 2011-07-27 | 2010-05-25 | 295294.75 | 0.417 | 0980013
6416 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 0980020 | "The village of Paw Paw will resurface 0.9 miles of East Michigan Avenue from the E. village limits to Kalamazoo Street. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-10-02 | 2009-10-09 | 2011-07-27 |  | 135000 | 0.933 | 0980020
6417 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW |  | 07 | 0981027 | 5.50 miles of pavement resurfacing on I-94 from the Freer Road easterly to Parker Road, west of Ann Arbor in Washtenaw County. This project includes ramp reconstruction, drainage improvements and fre | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2012-12-31 | 2011-09-19 | 14711194.72 | 11.000 | 0981027
6418 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW |  | 07 | 0981028 | 6.62 miles of pavement resurfacing on I-94 from the west Washtenaw County line easterly to Freer Road. This project includes ramp reconstruction, drainage improvements and freeway shoulder widening. | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2012-12-31 | 2011-09-19 | 3476957.68 | 13.240 | 0981028
6419 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981031 | 0.35 miles of pavement resurfacing and drainage improvements on North Ann Arbor Street from US-12 to Bennett Street in the City of Saline, Washtenaw County. | Pavement Improvement | 2009-08-04 | 2009-08-31 | 2009-10-02 |  | 202053.33 | 0.350 | 0981031
6420 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981035 | Throughout Washtenaw County the cracks in the pavement will be sealed to extend the life of the pavement. | Pavement Improvement | 2009-07-29 | 2009-09-01 | 2010-09-01 |  | 27220 | 7.795 | 0981035
6421 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981036 | 6.56 miles of roadway will be resurfaced in Washtenaw county, north of the City of Ann Arbor at multiple locations. North Territorial Road from Webster Church to Whitmore Lake, North Territorial Road | Pavement Improvement | 2009-07-29 | 2009-07-29 | 2010-09-01 | 2010-09-01 | 610740.59 | 6.146 | 0981036
6422 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981037 | 5.44 miles of pavement repair in the city of Ann Arbor area. This project will provide for improved rideability and increased pavement smoothness on Jackson Road from Honey Creek Drive to Wagner Road | Pavement Improvement | 2009-07-29 | 2010-06-01 | 2010-08-01 | 2010-08-01 | 88259.15 | 5.435 | 0981037
6423 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981038 | 11 miles of pavement resurfacing at various locations thourghout Washtenaw County to improve pavement rideability and pavement smoothness. Locations include Ann Arbor Road from Zeeb Road to West Ann | Pavement Improvement | 2009-07-29 | 2010-01-13 | 2010-09-01 | 2010-12-23 | 1007882.17 | 13.065 | 0981038
6424 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981039 | 2.36 miles of Loer Road from Textile Road to W Ellsworth Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, south of the City of Ann Arbor in Washtenaw County. | Pavement Improvement | 2009-07-29 | 2009-09-01 | 2010-09-01 |  | 43026 | 2.364 | 0981039
6425 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981040 | 2.43 miles of pavement resurfacing on Huron River Drive along the scenic Huron River between the Village of Dexter and the City of Ann Arbor in Washtenaw County. Improvements will provide for increas | Pavement Improvement | 2009-07-29 | 2009-07-20 | 2010-09-01 | 2010-12-23 | 250000 | 2.426 | 0981040
6426 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981042 | 2.0 miles of Baker Road from I-94 to Dan Hoey Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, West of the City of Ann Arbor in Washtenaw County. | Pavement Improvement | 2009-08-04 | 2009-09-01 | 2010-09-01 | 2010-09-01 | 49700 | 2.055 | 0981042
6427 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981043 | 1.78 miles of Ann Arbor-Saline Road from Oak Valley Drive to Maple Road and Maple Road from Ann Arbor-Saline Road to Saline City limits will have a Chip and Seal treatment to preserve pavement life an | Pavement Improvement | 2009-08-04 | 2009-09-01 | 2010-09-01 | 2010-09-01 | 82098 | 1.778 | 0981043
6428 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981044 | 2.0 miles of Dexter Ann Arbor Road from Dan Hoey Road to Zeeb Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, West of the City of Ann Arbor in Washtenaw County. | Pavement Improvement | 2009-08-04 | 2009-09-01 | 2010-09-01 | 2010-09-01 | 48387 | 2.112 | 0981044
6429 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981050 | 2.23 miles of Miller Road from Dexter Ann Arbor Road to Wagner Road will be Crackfilled with a Chip and Seal treatment to preserve pavement life and improve pavement smoothness, west of the City of Ann Arbor in Washtenaw County. | Pavement Improvement | 2009-08-13 | 2009-09-01 | 2010-09-01 | 2010-09-01 | 45554.16 | 2.229 | 0981050
6430 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 0981061 | This project will provide for traffic signal upgrades on Packard Road from the East Eisenhower Parkway to East Stadium Blvd. This work will improve traffic safety, ease congestion and increase traffi | Safety/Traffic Management | 2009-09-21 | 2010-03-15 | 2010-09-19 | 2010-08-27 | 185242.62 | 1.309 | 0981061
6431 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982054 | MDOT will repair and resurface . 9 miles of US-24 in Redford Township in Wayne County to improve driving quality and increase service life | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2011-12-31 | 2009-09-17 | 1001762.8 | 0.921 | 0982054
6432 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982055 | MDOT will resurface .8 miles of US-24 in the City of Flat Rock to improve the driving quality and extend the service life of the road | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-09-01 | 2009-09-24 | 360996.73 | 0.816 | 0982055
6433 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982057 | MDOT will landscape and replace fence on . 6 miles of I-75 in the City of Hamtamck Wayne County which will beautify the drive and make it safer. | Transportation Enhancements | 2009-05-14 | 2009-05-14 | 2011-09-19 |  | 746902.79 | 1.553 | 0982057
6434 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982058 | MDOT will rehabilitate 7 bridges in the City of Detroit on I-96 to make the bridges last longer | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2015-12-31 | 2011-09-01 | 11857012.74 | 0.000 | 0982058
6435 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982059 | MDOT will repair the I-96 under Underwood Avenue bridge in the City of Detroit to make the bridge last longer | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2010-12-17 |  | 1179301.38 | 0.000 | 0982059
6436 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982060 | MDOT will rehabilitate 3 bridges in the City of Detroit on I-96 to make the bridges last longer | Bridge Improvement | 2009-05-19 | 2009-05-19 | 2010-12-31 | 2010-08-27 | 3657578.71 | 0.000 | 0982060
6437 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982061 | The City of Westland will reconstruct the Newburgh and Warren intersection in the City of Westland to improve the driving quality and safety | Pavement Improvement | 2009-05-19 | 2009-05-19 | 2010-07-31 | 2010-07-12 | 681745.36 | 0.005 | 0982061
6438 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982064 | MDOT is removing 2 railroad bridges over I-96 in the City of Detroit because they are no longer used | Bridge Improvement | 2009-05-21 | 2009-05-21 | 2010-12-31 |  | 942473.11 | 0.000 | 0982064
6439 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982066 | 1 mile of Warren Road in the City of Dearborn Heights will be resurfaced by Wayne County to improve the driving quality and increase the road service life | Pavement Improvement | 2009-05-21 | 2009-05-21 | 2011-01-15 | 2009-11-24 | 883108.26 | 0.994 | 0982066
6440 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982067 | MDOT will construct a sound will at I-96 and US-24 to reduce road sounds to adjacent properties | Other | 2009-05-29 | 2009-05-29 | 2012-09-20 |  | 4568501.39 | 1.615 | 0982067
6441 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982076 | The City of Grosse Point will resurface .4 miles of St Clair Road to improve driving quality and increase road service life | Pavement Improvement | 2009-07-31 | 2009-08-22 | 2009-10-30 | 2009-11-09 | 324883.76 | 0.388 | 0982076
6442 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | ANN ARBOR | 13 | 0982082 | MDOT will repair and resurface the ramps on I-94 at Belleville road in Van Buren Township Wayne County to improve the driving quality and increase service life | Pavement Improvement | 2009-06-04 | 2009-06-04 | 2010-12-31 | 2009-11-01 | 640420.53 | 0.944 | 0982082
6443 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | STATEWIDE | 13 | 0982083 | MDOT will repair and resurface the ramps on I-94 at Haggerty Road in Van Buren Township Wayne County to improve the driving quality and increase service life | Pavement Improvement | 2009-06-04 | 2009-06-04 | 2010-12-31 | 2009-11-01 | 582237.98 | 0.839 | 0982083
6444 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE |  | 13 | 0982098 | MDOT will repair and resurface 6.3 miles of non motorized path along I-275 in Wayne County for cyclists, walkers and joggers to promote alternate modes of transportation | Transportation Enhancements | 2009-04-01 | 2009-04-01 | 2013-01-19 |  | 4655955.12 | 12.530 | 0982098
6445 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982100 | The City of Grosse Point Shores will resurface .4 miles of Vernier Road to improve driving quality and increase service life | Pavement Improvement | 2009-07-07 | 2009-10-14 | 2010-10-30 | 2010-09-15 | 180887.59 | 0.364 | 0982100
6446 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982108 | MDOT will replace pumping equipment on I-94 in the City of Dearborn Wayne County to insure rainwater will not interfere with traffic | Pavement Improvement | 2009-07-21 | 2009-07-21 | 2010-12-31 | 2011-07-12 | 1038050.36 | 0.324 | 0982108
6447 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982113 | MDOT will rehabilitate the M-8 under Joseph Campau bridge to make the bridge last longer | Bridge Improvement | 2009-09-16 | 2009-09-16 | 2011-12-31 | 2011-09-01 | 1724905.14 | 0.226 | 0982113
6448 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982114 | MDOT will repair the M-8 under Charest Avenue walkover bridge to make the bridge last longer | Bridge Improvement | 2009-05-11 | 2009-05-11 | 2011-12-31 | 2011-09-01 | 194264.47 | 0.048 | 0982114
6449 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982115 | MDOT will rehabilitate the M-8 under Goddard Avenue bridge to make the bridge last longer | Bridge Improvement | 2009-07-24 | 2009-07-24 | 2011-12-31 | 2011-09-01 | 1714610.1 | 0.262 | 0982115
6450 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982116 | MDOT will resurface 1.4 miles of M-8 in the City of Detroit to improve driving quality and extend service life of the road | Pavement Improvement | 2009-07-24 | 2009-07-24 | 2015-12-31 | 2011-09-01 | 13260674.38 | 2.722 | 0982116
6451 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982117 | MDOT will rehabilitate 5 bridges on M-8 to make the bridges last longer | Bridge Improvement | 2009-09-16 | 2009-09-16 | 2011-12-31 | 2011-09-01 | 583657.03 | 0.000 | 0982117
6452 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982121 | Wayne County will resurface .5 Miles of Merriman Road in the Cities of Westland and Livonia to improve driving quality and increase service life | Pavement Improvement | 2009-07-29 | 2009-12-18 | 2010-08-31 | 2010-08-27 | 795644.91 | 0.516 | 0982121
6453 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982122 | The City of Livonia will resurface .5 miles of Lyndon Road to improve driving quality and increase service life | Pavement Improvement | 2009-07-29 | 2010-06-18 | 2013-03-15 | 2010-09-30 | 675000 | 0.502 | 0982122
6454 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982123 | Wayne County will resurface .6 miles of 7 Mile Road to improve driving quality and increase service life | Pavement Improvement | 2009-07-30 | 2009-07-30 | 2010-09-30 | 2010-09-24 | 595694.51 | 0.625 | 0982123
6455 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982124 | MDOT will repair and resurface .4 miles of US-12 in the City of Dearborn to improve the driving quality and increase service life | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2011-12-31 | 2011-06-02 | 2449807.27 | 3.025 | 0982124
6456 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982130 | MDOT will install an active speed warning system on the I-94 Ebd ramp to I-96 in the City of Detroit which will improve safety | Safety/Traffic Management | 2009-10-06 | 2009-10-06 | 2012-11-15 |  | 476061.37 | 0.070 | 0982130
6457 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982131 | MDOT will install an active speed warning system on the I-94 Wbd ramp to I-96 in the City of Detroit which will improve safety | Safety/Traffic Management | 2009-10-06 | 2009-10-06 | 2012-11-15 |  | 395535.08 | 0.108 | 0982131
6458 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982136 | MDOT will repair 2 railroad bridges over M-85 in the City of Detroit to make the bridges last longer | Bridge Improvement | 2009-05-11 | 2009-05-11 | 2010-12-17 | 2010-05-25 | 960584.5 | 0.000 | 0982136
6459 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982141 | MDOT will repair and resurface 6 miles of M-39 in the cities of Detroit and Dearborn to improve driving quality and increase service life | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2011-12-31 | 2010-05-24 | 3161887.26 | 11.939 | 0982141
6460 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982152 | The City of Detroit is resurfacing portions of Seven Mile, Conner, McNichols, East Vernor, Mt Elliot, Mack and Warren Roads to improve driving quality and increase service life | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2010-11-02 | 2012-05-04 | 4562400.24 | 0.360 | 0982152
6461 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982153 | The City of Detroit is resurfacing portions of E. Congress, E. Lafayette, E. Larned, Clark, Chicago and Puritan Roads to improve driving quality and increase service life | Pavement Improvement | 2009-08-20 | 2010-04-15 | 2010-11-02 | 2011-08-31 | 2870051.21 | 6.576 | 0982153
6462 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982154 | The City of Detroit is resurfacing portions of Meyers, Burt, Southfield Service Drive, Lodge Service Drive and Livernois Roads to improve driving quality and increase service life | Pavement Improvement | 2009-08-20 | 2010-03-03 | 2010-11-02 | 2011-08-31 | 3942896.29 | 7.267 | 0982154
6463 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982170 | Wayne County will resurface 1.5 Miles of Middlebelt Road in the City of Romulus to improve driving quality and increase service life | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-11-30 | 2010-11-28 | 1558682.52 | 1.501 | 0982170
6464 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 0982173 | Wayne County will will reconstruct and widen to 5 lanes 1.4 miles of Canton Center Road in Canton Township to improve safety and ease congestion | Pavement Widening | 2009-09-16 | 2009-09-16 | 2010-11-19 | 2011-09-21 | 3867492 | 1.000 | 0982173
6465 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WEXFORD |  | 02 | 0983019 | The MDOT is replacing the US-131 bridge over the Manistee River in the City of Manistee to improve safety and increase mobility. | Bridge Replacement | 2009-06-04 | 2009-06-04 | 2010-07-02 | 2010-06-18 | 168088.04 | 0.110 | 0983019
6466 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984075 | The MDOT is undertaking areawide pavement repairs on 14 miles of roadway in Howard City area to improve the pavement condition and extend pavement life. | Pavement Improvement | 2009-04-28 | 2009-04-28 | 2009-11-14 | 2009-09-03 | 202569.95 | 19.420 | 0984075
6467 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984076 | The MDOT is undertaking areawide pavement repairs on nearly 18 miles of roadway in the Grand Region area to improve the pavement condition and extend pavement life. | Pavement Improvement | 2009-05-05 | 2009-05-05 | 2010-06-30 | 2009-10-07 | 289336.54 | 23.773 | 0984076
6468 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984084 | The 8 weather towers, called an Environmental Sensor Station are designed to aid motorists and the Michigan Department of Transportation (MDOT), and are expected to be particularly helpful in the winter. | Safety/Traffic Management | 2009-05-05 | 2009-05-05 | 2009-10-30 | 2009-10-30 | 1049296.51 | 1.600 | 0984084
6469 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE | DETROIT,MI |  | 0984088 | Throughout the Detroit Metropolitan Freeway System the automated traffic control system will receive upgrades to its equipment. This will lessen freeway congestion and improve safety. | Other | 2009-06-04 | 2009-06-04 | 2015-12-31 |  | 7000000 | 0.000 | 0984088
6470 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 0984100 | MDOT will repair 27 miles of M-37, US-131, and US-31 at various locations in Grand Traverse Countyto extend the service life of the existing roadways. | Pavement Improvement | 2009-04-17 | 2009-04-17 |  | 2010-05-28 | 166419.94 | 27.206 | 0984100
6471 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984103 | At numerous Statewide locations along US-23 and M-55 the guardrail will be replaced with upgraded guardrail to improve safety | Safety/Traffic Management | 2009-06-17 | 2009-06-17 | 2010-05-28 | 2010-06-10 | 332305.86 | 29.150 | 0984103
6472 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984107 | The weather tower and message sign project will consist of 12 Environmental Sensor Stations and 10 Dynamic Message Signs in 4 Counties and will improve safety and mobility. | Safety/Traffic Management | 2009-07-07 | 2009-07-07 | 2010-12-31 | 2011-07-13 | 1697447.25 | 7.711 | 0984107
6473 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 0984108 | The MDOT is installing environmental sensors in the North Region at various locations to monitor environmental conditions in the Region. | Safety/Traffic Management | 2009-07-07 | 2009-07-07 | 2010-12-31 | 2011-07-13 | 1478323.2 | 13.966 | 0984108
6474 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE | DETROIT,MI |  | 0984133 | Establishing a protective security fence around five towers in Oakland, Macomb and St. Clair Counties by MDOT. | Safety/Traffic Management | 2009-08-17 | 2009-08-17 | 2011-11-07 | 2009-12-02 | 36510.68 | 0.001 | 0984133
6475 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 1002010 | This pavement project near Wetmore on road FF 13 at M28 S will smooth the road and improve ride quality | Pavement Improvement | 2010-02-09 | 2010-05-01 | 2010-09-15 | 2010-07-31 | 51386 | 2.626 | 1002010
6476 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ALGER |  | 01 | 1002012 | This project will improve safety by replacing the guardrail on M-94 Chatham to Munising in Alger County | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2010-08-27 | 2010-08-27 | 400560.13 | 10.200 | 1002012
6477 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN | HOLLAND | 06 | 1003005 | The Allegan County Road Commisssion will resurface one mile of 40th Street from Washington Avenue to Lincoln Avenue, in the city of Holland. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-11 | 2010-03-29 | 2010-09-15 | 2010-10-06 | 797585 | 1.987 | 1003005
6478 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN | HOLLAND | 06 | 1003007 | The Allegan County Road Commisssion will resurface 2.8 miles of 136th Avenue from 58th Street to Blue Star Highway just north of the ciy of Saugatuck in Allegan county. | Pavement Improvement | 2010-03-26 | 2010-05-03 | 2010-07-01 | 2010-06-14 | 476387.5 | 2.785 | 1003007
6479 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALLEGAN |  | 06 | 1003008 | This 1.4 mile long pavement project on in Plainwell on Main Street from South City Limits to Norfolk Southern Rail will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-29 | 2010-05-14 | 2011-07-27 | 2010-06-29 | 205000 | 1.252 | 1003008
6480 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ALPENA |  | 01 | 1004003 | The Alpena County Road Commission will resurface 1.5 miles of Misery Bay Rd from the Lafarge property to the east city limits of Alpena. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-26 | 2010-03-02 | 2011-06-30 | 2010-06-07 | 290000 | 0.764 | 1004003
6481 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ANTRIM |  | 01 | 1005006 | This 8 mile long pavement project on E Torch Lake/Alden Rd/Comfort South County Line to M8 8will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-22 | 2010-05-19 | 2010-06-30 | 2010-06-21 | 366683 | 8.679 | 1005006
6482 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ARENAC |  | 01 | 1006005 | Arenac County will repave 3 miles of Turner Rd from Herr Rd-Tonkey Rd Arenac County | Pavement Improvement | 2010-05-05 | 2010-06-21 | 2010-07-23 | 2010-09-07 | 234154 | 3.012 | 1006005
6483 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BARAGA |  | 01 | 1007003 | This 1.6 mile long pavement project on Skanee Road in Baraga County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-04-02 | 2010-07-27 | 2010-08-22 | 2010-08-22 | 330310 | 1.525 | 1007003
6484 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | BARAGA |  | 01 | 1007004 | MDOT will relocate 1.6 miles of US-41 in rural Baraga County. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-24 | 2010-02-24 | 2010-10-22 | 2010-10-08 | 2502056.07 | 1.621 | 1007004
6485 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BARRY |  | 03 | 1008007 | This tenth mile long pavement project in Hastings on South Jefferson Street from Green Street to Grand Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-27 | 2010-07-06 | 2011-07-27 | 2010-09-15 | 107000 | 0.126 | 1008007
6486 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BARRY |  | 03 | 1008009 | This pavement project near Middleville on Finkbeiner Road from Cherry Valley Road to M-37 will make the pavement smoother and improve ride quality. | Pavement Improvement | 2010-02-24 | 2010-07-01 | 2011-07-01 | 2011-07-11 | 950833.04 | 1.250 | 1008009
6487 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 1009009 | The City of Essexville will resurface 0.4 mile of Borton Ave from Caroline St to Scheurmann St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-04-29 | 2010-06-14 | 2010-07-30 | 2010-07-30 | 218461.58 | 0.392 | 1009009
6488 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 1009013 | This 2 mile long pavement project on Wilder Road from I-75 to M-13 and M-13 to Patterson Road in the City of Bay City will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-28 | 2010-06-01 | 2010-08-13 | 2010-11-10 | 450000 | 4.042 | 1009013
6489 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 1009015 | This 2 mile long pavement project in Bay City on Truman Parkway/Woodside Avenue from Saginaw River to Woodside/McEwan will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-28 | 2010-06-01 | 2010-08-13 | 2010-11-10 | 707085 | 0.657 | 1009015
6490 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY |  | 01 | 1009016 | This pavement project near Bay City on S 7 Mile Rd from Hotchkiss Rd to Salzburg Rd will smooth the road and improve ride quality. | Pavement Improvement | 2010-02-17 | 2010-06-03 | 2010-09-17 | 2010-09-10 | 305483.41 | 1.009 | 1009016
6491 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY |  | 01 | 1009017 | This pavement project near Bay City on Hotchkiss Rd from 7 Mile Rd to Carter Rd will smooth the road and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-07-01 | 2010-09-03 | 2010-08-16 | 65887 | 4.871 | 1009017
6492 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BAY | BAY CITY | 01 | 1009020 | About 1 mile of pavement resurfacing of Bay-Arenac Drive from Monitor Road to 2 Mile Road outside of Bay City. This project will improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2010-08-31 | 2010-09-14 | 2011-06-30 | 2010-10-11 | 78681 | 1.442 | 1009020
6493 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BENZIE |  | 02 | 1010003 | About 2 miles of County Road 708 from M22 to Platte River near the City of Honor in Benzie County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 2010-02-10 | 2010-07-14 | 2010-07-30 | 2010-07-30 | 77134.29 | 2.146 | 1010003
6494 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BENZIE |  | 02 | 1010004 | Aboutt 5 miles of River Rd from M22 to Benzonia West Village Limit in Benzie County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 2010-02-10 | 2010-07-14 | 2010-07-30 | 2010-07-30 | 157013.47 | 5.241 | 1010004
6495 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BENZIE |  | 02 | 1010009 | Benzie County will resurface six miles of N Manistee County Line Rd from US31 to Kurick Road | Other | 2010-02-10 | 2010-07-14 | 2010-07-30 | 2010-07-30 | 23634 | 6.214 | 1010009
6496 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 1011003 | "The village of Eau Claire will resurface 0.84 miles of E. Main Street throughout the limits of the village. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-05 | 2010-09-02 | 2010-06-18 | 2010-11-10 | 92500 | 0.837 | 1011003
6497 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 1011005 | The Allegan County Road Commisssion will resurface one mile of 40th Street from Washington Avenue to Lincoln Avenue, in the city of Holland. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-26 | 2010-03-29 | 2013-08-07 | 2010-10-08 | 671000 | 0.229 | 1011005
6498 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 1011007 | A quarter mile of Lake St from Fifth Street to Eleventh Street in the city of Niles will be repaved to improve smoothness and ride quality. | Pavement Improvement | 2010-03-04 | 2010-04-26 |  | 2010-09-17 | 64677.93 | 0.289 | 1011007
6499 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 1011008 | The Berrien County Road Commisssion will resurface 0.63 miles of E. Main Street from Maple Street to 17th Street in the city of Niles. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-04 | 2010-04-26 | 2011-07-27 | 2010-09-17 | 159112.05 | 0.629 | 1011008
6500 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | BENTON HARBOR | 06 | 1011013 | This quarter mile long pavement project in St. Joseph on Broad St from Lake Blvd. to State St. will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-01 | 2010-04-19 | 2011-07-27 | 2010-06-16 | 42626 | 0.270 | 1011013
6501 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 1011014 | This 4 mile long pavement project in Berrien County on W Shawnee Rd from Burgoyne Road to Cleveland Avenue will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-06-29 | 2010-09-15 | 2010-08-06 | 47665.8 | 3.961 | 1011014
6502 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN |  | 06 | 1011015 | The Berrien County Road Commisssion will resurface 0.19 miles of North Main Street from Mars Street to Hamilton Street in the Niles metropolitan area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-06-14 | 2010-06-21 | 2011-07-27 | 2010-08-20 | 92500 | 0.191 | 1011015
6503 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | BERRIEN | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 1011043 | A new surface will be put on Niles-Buchanan Road near Niles Michigan. This will improve the ride quality. | Pavement Improvement | 2010-08-18 | 2011-06-01 | 2011-07-01 | 2011-08-09 | 66268.18 | 3.875 | 1011043
6504 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 1012004 | The Branch County Road Commisssion will resurface 0.28 miles of North Michigan Avenue from Smith Street to Seeley Street in the city of Coldwater. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-04-09 | 2010-05-14 | 2011-07-27 | 2010-05-26 | 146979 | 0.278 | 1012004
6505 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | BRANCH |  | 07 | 1012005 | A pavement improvement project in Branch County near the city of Colwater on Central road from Bloack Road to South Angola Road and on Warren Road from Lake Drive to Fremont road will smooth the road and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-08-10 | 2010-09-15 | 2010-08-19 | 71993.32 | 5.471 | 1012005
6506 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 1013012 | The Calhoun County Road Commission will resurface 0.8 miles of Meachem Road from Upton to Capital in the Battle Creek urbanized area. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-04-28 | 2010-05-03 | 2011-07-27 | 2010-06-15 | 162477.79 | 0.781 | 1013012
6507 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 1013013 | This half mile pavement project on Riverside Dr Burnham St. Territorial Rd. will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-28 | 2010-05-03 |  | 2010-06-15 | 78412.19 | 0.288 | 1013013
6508 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 1013014 | This half mile long pavement project on Watson Street from Eaton to Maple Street in Albion will make the road smoother and improve ride quality. | Pavement Improvement | 2010-03-25 | 2010-07-12 | 2011-07-27 | 2010-09-02 | 162623.06 | 0.503 | 1013014
6509 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 1013017 | The Calhoun County Road Commission will resurface 0.7 miles of 6 1/2 Mile Road from B Drive N to Christian Drive | Pavement Improvement | 2010-05-28 | 2010-06-01 | 2011-07-27 | 2010-07-06 | 176098.36 | 0.774 | 1013017
6510 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN |  | 07 | 1013020 | This mile long pavement project in Calhoun County on N Dr N from 15 Mile Rd to 16 Mile Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-28 | 2010-06-01 | 2011-07-27 | 2010-06-22 | 109313.64 | 1.028 | 1013020
6511 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CALHOUN | BATTLE CREEK | 07 | 1013034 | "Resurface, curb & gutter/0.06 mi of hot mix asphalt resurfacing, storm sewer, and concrete curb, gutter, sidewalks, and ADA ramps on Hamblin Road at Jackson Road in the city of Battle Creek, Calho | Pavement Improvement | 2010-09-23 | 2010-10-07 | 2011-07-27 | 2010-11-11 | 69985.47 | 0.187 | 1013034
6512 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 1014003 | The Cass County Road Commisssion will resurface 1.2 miles of Dixon Road from Indian Lake Road to M-152, in the northwest part of the county. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-10-21 | 2010-07-19 | 2010-07-30 | 2010-07-29 | 20682.78 | 1.197 | 1014003
6513 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CASS |  | 06 | 1014004 | City of Dowagiac will repave Middle Crossing Road from West Prairie Ronde to City Limits | Pavement Improvement | 2010-02-08 | 2010-09-15 | 2010-10-15 | 2010-10-15 | 50000 | 0.270 | 1014004
6514 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | CASS | SOUTH BEND-MISHAWAKA, IN-MI | 06 | 1014005 | The Cass County Road Commission will resurface 0.6 miles of Gumwood Road from the state line to Redfield Street | Pavement Improvement | 2010-02-17 | 2010-07-06 | 2011-07-27 | 2010-08-24 | 241685.41 | 0.630 | 1014005
6515 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHARLEVOIX |  | 01 | 1015003 | The Charlevoix County Road Commission will resurface 2.5 miles of Peninsula Rd from Advance Rd to Reich Rd in the vicinity of East Jordane. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-05-06 | 2010-05-26 | 2010-07-02 | 2010-07-22 | 340911 | 2.438 | 1015003
6516 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 1016006 | Four tenths of a mile of West Central Ave will be resurfaced from Nicolet to Huron in the Village of Mackinaw City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-22 | 2010-04-26 | 2010-05-27 | 2010-05-21 | 284181.11 | 0.352 | 1016006
6517 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 1016008 | The Village of Mackinaw City will build a paved pathway on the Mackinaw City Rail to Trail route for cyclists walkers and joggers to promote alternative modes of transportation. | Transportation Enhancements | 2010-06-15 | 2010-06-30 | 2010-08-13 | 2011-07-29 | 805648.8 | 0.082 | 1016008
6518 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHEBOYGAN |  | 01 | 1016012 | This pavement project in Cheboygan on S Western Ave from city line to Lincoln Ave will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-09 | 2010-06-28 | 2010-07-16 | 2010-07-16 | 63911.72 | 1.016 | 1016012
6519 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017003 | This pavement project on Riverside Drive in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-01-05 | 2010-05-17 | 2010-07-02 | 2010-06-24 | 573808.58 | 4.986 | 1017003
6520 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017007 | This pavement project at Kincheloe AFB in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-03-26 | 2010-05-06 | 2010-07-30 | 2010-07-27 | 135000 | 0.572 | 1017007
6521 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017009 | This pavement project on Oak Street in Chippewa County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-04-01 | 2010-05-24 | 2010-07-15 | 2010-07-13 | 288244.98 | 0.969 | 1017009
6522 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017011 | This pavement and Rumble Strip project on M-129 in Chippewa County will improve safety and make the road smoother. | Pavement Improvement | 2010-01-28 | 2010-01-28 | 2012-12-31 | 2010-11-05 | 4099773 | 7.251 | 1017011
6523 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017013 | This pavement project in Chippewa County on H40 (Main & Albert) from M63 Westerly-S of South Street will smooth the road and improve ride quality | Pavement Improvement | 2010-04-22 | 2010-05-12 | 2010-10-29 | 2010-08-13 | 108457.42 | 0.578 | 1017013
6524 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017014 | This guardrail installation project on M-48 in Chippewa County will improve safety. | Other | 2009-05-11 | 2009-05-11 | 2010-06-25 | 2010-06-28 | 158391.49 | 24.000 | 1017014
6525 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | CHIPPEWA |  | 01 | 1017015 | This shoulder paving project on M-28 in Chippewa County will improve safety. | Pavement Improvement | 2010-04-22 | 2010-07-14 | 2010-09-03 | 2010-09-03 | 1191547.56 | 10.769 | 1017015
6526 | MICHIGAN | Underway | C950 | Ferryboat | MICHIGAN | CHIPPEWA |  | 01 | 1017029 | Dock Upgrades | Other | 2010-07-12 |  | 2012-07-16 |  | 1175000 | 2.135 | 1017029
6527 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLARE |  | 04 | 1018007 | Just outside the City of Clare in Clare County there will be 2.0 miles of resurfacing on E. Beaverton Rd to improve driving quality by making the road smoother. | Pavement Improvement | 2010-03-12 | 2010-04-26 | 2010-06-11 | 2010-06-08 | 449771 | 2.001 | 1018007
6528 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | CLARE |  | 04 | 1018011 | A bike trail will be built on the Pere Marquette Rail Trail east of Evart for walkers and cyclists. | Transportation Enhancements | 2010-02-23 | 2010-02-23 | 2012-02-01 | 2010-11-18 | 753890.46 | 15.620 | 1018011
6529 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 1019004 | This pavement project on N Lansing St BR 127 to Walker in St. Johns will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-01 | 2010-06-28 | 2010-07-02 | 2010-08-12 | 78215.65 | 0.117 | 1019004
6530 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 1019005 | This pavement project on W Howe Rd Grange to Wacousta will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-09-07 | 2010-09-17 | 2010-09-17 | 67457 | 4.887 | 1019005
6531 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CLINTON |  | 08 | 1019006 | In the City of St. Johns | Pavement Improvement | 2010-06-10 | 2010-06-19 | 2010-08-10 | 2010-08-12 | 47000 | 0.436 | 1019006
6532 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | CRAWFORD |  | 01 | 1020006 | This pavement project near Grayling on W County Road from east of North Stephan Bridge Rd to west of KP Rd will smooth the road and improve ride quality. | Pavement Improvement | 2010-01-01 | 2010-01-01 | 2010-06-25 | 2010-07-13 | 67316.58 | 0.978 | 1020006
6533 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 1021011 | This pavement prjoect from Ludington St to 8th Avenue in the City of Escanaba will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-06-11 | 2010-07-06 | 2010-09-24 | 2010-11-04 | 300000 | 0.733 | 1021011
6534 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 1021012 | This pavement improvement project in Delta County near the town of Gulliver on County Road 432 will rebuild a little over one mile of pavment and improve the ride quality. | Pavement Improvement | 2010-06-30 | 2010-08-16 | 2010-10-15 | 2010-09-28 | 199394.58 | 1.207 | 1021012
6535 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DELTA |  | 01 | 1021023 | Resurface, Crack Fill and Chip | Pavement Improvement | 2010-08-18 | 2011-05-01 | 2011-06-30 | 2011-08-12 | 94000 | 5.371 | 1021023
6536 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 1022006 | This pavement project on County Road 569 in Dickinson County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-02-26 | 2010-05-12 | 2010-08-28 | 2010-07-29 | 277036.3 | 1.465 | 1022006
6537 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 1022009 | This pavement project on West Ludington Street in the City of Iron Mountain will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-05-25 | 2010-06-01 | 2010-09-20 | 2010-10-19 | 92100.6 | 0.185 | 1022009
6538 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | DICKINSON |  | 01 | 1022018 | Culvert Replacement | Pavement Improvement | 2010-07-30 | 2010-09-13 | 2010-10-31 | 2010-11-04 | 32785.7 | 5.516 | 1022018
6539 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023004 | In the City of Eaton Rapids just under 1/2 mile of State Street will be reconstructed from West of Miller Drive to the City Limits. Work will include reconstructing the roadway and building a left turn lane to facilitate traffic movement and improve tra | Pavement Improvement | 2010-04-02 | 2010-06-14 |  | 2010-07-02 | 110000 | 0.389 | 1023004
6540 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023005 | This pavement project on S Cochran Rd Butterfield to Five Point Highway will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-07-14 | 2010-07-12 | 71300 | 5.047 | 1023005
6541 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023006 | This pavement project on E Five Point Hwy Freeman to Narrow Lake Road will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-08-31 | 2010-08-30 | 66400 | 4.552 | 1023006
6542 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023007 | This pavement project on W Five Point Hwy Lacey Lake Road to Battle Creek Road will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-08-31 | 2010-08-16 | 68200 | 4.808 | 1023007
6543 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023008 | This pavement project on W Vermontville Hwy Hager Road to Vertmontville will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-08-05 | 2010-08-02 | 34600 | 2.373 | 1023008
6544 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023009 | This pavement project on N Cochran Rd M-50 to Pinch Street will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-07-31 | 2010-07-21 | 47180 | 3.293 | 1023009
6545 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023010 | This pavement project on N Canal Rd Bentley to Vermontville Highway will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-08-31 | 2010-08-23 | 79300 | 5.526 | 1023010
6546 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023011 | This pavement project on Mulliken Rd M-50 to Cochran will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-07-31 | 2010-07-22 | 76440 | 5.423 | 1023011
6547 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023012 | This pavement project on N Cochran Rd Mt. Hope to M-43; M-43 to Eaton Highway will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-23 | 2010-06-14 | 2010-07-21 | 2010-07-21 | 59000 | 4.030 | 1023012
6548 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EATON |  | 07 | 1023013 | In the City of Potterville in Eaton County 1/4 mile of East Main Street will be reconstructed from Hartel Road (State Route M-100) to Dawn Court. Work will include sidewalk improvements and drainage improvements. | Pavement Improvement | 2010-03-11 | 2010-06-21 | 2010-08-27 | 2010-08-27 | 220000 | 0.218 | 1023013
6549 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | EMMET |  | 01 | 1024013 | Resurfacing | Pavement Improvement | 2010-09-13 | 2010-09-21 | 2010-10-29 | 2010-10-08 | 62878.19 | 2.996 | 1024013
6550 | MICHIGAN | Completed | C200,C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 1025003 | In Genesee County, MDOT will repair 8.11 miles on M-15 from the Oakland County line northerly to south of I-69 to extend the service life of the existing road. | Pavement Improvement | 2009-03-31 | 2009-03-31 | 2011-01-21 | 2010-06-25 | 1299810.28 | 8.243 | 1025003
6551 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE |  | 05 | 1025009 | The MDOT will make repairs to the bridge at M-11 over the Grand River in the City of Walker to make the bridge last longer. | Transportation Enhancements | 2010-04-19 | 2010-04-29 | 2011-09-15 |  | 935890.15 | 0.182 | 1025009
6552 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025020 | Four tenths of a mile of Elms Rd from River Rd to Flusing Rd in the City of Flushing will be resurfaced. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-03-31 | 2009-03-31 | 2011-04-01 | 2010-09-03 | 607702.56 | 0.524 | 1025020
6553 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025021 | One mile of Davison Rd from Genesee Rd to Belsay Rd in the City of Burton will be resurfaced. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-22 | 2009-12-22 | 2010-08-15 | 2010-06-29 | 725856.48 | 0.999 | 1025021
6554 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025024 | This pavement project in Flint on Perry Road From Terrace Drive to City Limits will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-28 | 2010-05-06 | 2010-09-01 | 2010-08-24 | 140861 | 0.336 | 1025024
6555 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025026 | The City of Flushing is resurfacing 0.3 miles of Terrace Street from River Road to Main Street. This project will improve the pavement condition and ride quality. | Pavement Improvement | 2010-06-29 | 2010-07-02 | 2010-10-10 | 2010-08-25 | 152280 | 0.242 | 1025026
6556 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | GENESEE | FLINT | 05 | 1025075 | Resurface | Pavement Improvement | 2010-12-14 | 2011-04-13 | 2011-07-01 | 2011-05-30 | 111607.49 | 0.169 | 1025075
6557 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 1027004 | About 1/2 mile of Johnson Rd from Colby St to Bessemer City Limits, in Gogebic County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 2010-04-14 | 2010-06-21 | 2010-08-20 | 2010-07-13 | 63728.76 | 0.315 | 1027004
6558 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 1027006 | This paving project on Prison Camp Road in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-04-08 | 2010-06-28 | 2010-10-15 | 2010-07-08 | 241062.5 | 1.606 | 1027006
6559 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GOGEBIC |  | 01 | 1027007 | This pavement project on North Lake Street in Gogebic County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-06-18 | 2010-08-30 | 2010-10-15 | 2010-11-09 | 120000 | 0.250 | 1027007
6560 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 1028008 | New pavement markings will be placed in Traverse City on various roadways to improve roadway delineation. | Safety/Traffic Management | 2010-05-25 | 2010-08-23 | 2010-09-30 | 2010-09-28 | 127870.92 | 1.090 | 1028008
6561 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRAND TRAVERSE |  | 04 | 1028011 | This project will improve safety by renewing the pavement striping throughout Grand Traverse County. | Safety/Traffic Management | 2010-06-03 | 2010-06-07 | 2010-07-02 | 2010-06-08 | 34998.91 | 1.154 | 1028011
6562 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRATIOT |  | 04 | 1029006 | From the St. Louis north city limit northerly to McGregor Road in Gratiot County there will be 0.76 miles reconstruction on Riverside Drive to improve the driving quality of the roadway. | Pavement Improvement | 2010-01-22 | 2010-04-06 | 2010-08-13 | 2010-06-18 | 299266.73 | 0.790 | 1029006
6563 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | GRATIOT |  | 04 | 1029015 | Resurface | Pavement Improvement | 2010-06-10 | 2010-08-23 | 2010-08-31 | 2010-08-31 | 17000 | 1.001 | 1029015
6564 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 1030004 | 10.43 miles of South Meridian Road (US-127) from the Ohio State line north to M-34 will be resurfaced to improve pavement rideability and increase pavement smoothness. This project will include drainage and safety improvements. | Pavement Improvement | 2009-10-29 | 2009-10-29 | 2011-04-01 | 2010-11-12 | 6229866.88 | 10.430 | 1030004
6565 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 1030008 | This pavement project in Hillsdale on East Fayette Street from Hillsdale to Oake will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-02 | 2010-06-11 | 2010-07-24 | 2010-08-19 | 170000 | 0.213 | 1030008
6566 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HILLSDALE |  | 07 | 1030010 | This pavement project on Squawfield Road from US-127 to Waldron Road in rural Hillsdale County will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-08-12 | 2010-09-30 | 2010-09-14 | 41679.54 | 2.987 | 1030010
6567 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 1031008 | This pavement project in Owosso on Pike River Rd from Chassell/Painesdale Rd- to Lower Worham Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-01 | 2010-05-06 | 2010-09-24 | 2010-09-24 | 434256.37 | 1.565 | 1031008
6568 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 1031009 | This pavement project in Houghton on Campus Drive from Poplar Street to Elevation Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-23 | 2010-04-28 | 2010-10-15 | 2010-08-16 | 90000 | 0.123 | 1031009
6569 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | HOUGHTON |  | 01 | 1031011 | This guardrail installation project on M-26 in Houghton County will improve safety. | Other | 2010-02-23 | 2010-02-23 |  | 2010-09-15 | 59094.52 | 0.789 | 1031011
6570 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | HURON |  | 10 | 1032008 | The Huron County Road Commission will resurface 2 and a quarter miles of French Line Rd from the east Village limits of Ubly to Verona Rd. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-04-01 | 2010-08-30 | 2010-09-15 | 2010-09-15 | 278144 | 2.237 | 1032008
6571 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM |  | 08 | 1033005 | 0.20 miles of North Williamston Road from I-96 to the north in Ingham County near the city of Williamston will be resurfaced to improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2010-04-23 | 2010-05-10 |  | 2010-05-28 | 92000 | 0.200 | 1033005
6572 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 1033009 | This pavement project on W Holmes Rd Berwick to Plesant Grove will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-08 | 2010-06-14 | 2010-08-27 | 2010-08-16 | 551424.39 | 0.841 | 1033009
6573 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 1033010 | 1.33 Miles of Edgewood Blvd will be reconstructed in the city of Lansing from South Washington Avenue to South Cedar Street Improvements will improve roadway rideability and make the roadway smoother. | Pavement Improvement | 2010-01-20 | 2010-06-28 | 2010-11-30 | 2011-11-11 | 731384.29 | 2.463 | 1033010
6574 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 1033011 | 1.7 miles of North Waverly Road from West Willow Street to North Grand River Avenue will be resurfaced in Lansing. The roadway will have improved rideablity and the improved smoothness. | Bridge Improvement | 2010-05-19 | 2010-06-02 | 2010-09-03 | 2010-10-22 | 996268.14 | 1.487 | 1033011
6575 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | INGHAM | LANSING | 08 | 1033046 | mill and resurface | Pavement Improvement | 2010-09-10 | 2011-05-09 | 2011-06-12 | 2011-06-10 | 102189.79 | 0.511 | 1033046
6576 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 1034004 | The Ionia County Road Commission will resurface three quarters of a of Mill Street from Bridge Street to the Village of Saranac. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-24 | 2010-05-04 | 2010-06-12 | 2010-06-25 | 239737 | 0.754 | 1034004
6577 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 1034005 | At various loacation on Hall Street in Belding | Pavement Improvement | 2010-04-14 | 2010-07-06 | 2010-07-30 | 2010-07-30 | 110000 | 0.359 | 1034005
6578 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 1034011 | 1.7 miles of North Waverly Road from West Willow Street to North Grand River Avenue will be resurfaced in Lansing. The roadway will have improved rideablity and the improved smoothness. | Pavement Improvement | 2010-01-01 | 2010-01-01 | 2010-11-12 | 2011-06-30 | 239736 | 1.001 | 1034011
6579 | MICHIGAN | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | IONIA |  | 03 | 1034014 | This two and a half mle long pavement project on M-21 from east of the Kent / Ionia County line to Pinckney Road will make the pavement smoother and improve ride quality | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2012-03-31 | 2010-10-07 | 1003691.7 | 2.759 | 1034014
6580 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IOSCO |  | 01 | 1035003 | The Iosco County Road Commission will resurface three quarters of a mile of North Skeel Ave from F-41 to Arrow St in the Huron National Forest. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-08 | 2010-06-03 | 2011-06-30 | 2010-06-24 | 135000 | 0.719 | 1035003
6581 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IOSCO |  | 01 | 1035004 | The Iosco County Road Commission will resurface 2.5 miles of Rollway Rd from M-65 to Liberty Rd in the Huron National Forest west of Oscoda. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-09 | 2010-05-18 | 2011-06-30 | 2010-06-21 | 353290 | 2.419 | 1035004
6582 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IRON |  | 01 | 1036006 | A little over 2 miles of CR651 from W Sunset Lake Rd-Noren Rd near the city of Iron River in Iron County will be repaved to improve ride quality and make the road smoother. | Pavement Improvement | 2010-04-26 | 2010-06-01 | 2010-06-30 | 2010-06-30 | 213058.22 | 2.210 | 1036006
6583 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | IRON |  | 01 | 1036007 | This pavement project on Lay Ave. in the City of Iron River will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-03-23 | 2010-06-25 | 2010-08-13 | 2010-08-06 | 183884.27 | 0.675 | 1036007
6584 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 1037004 | The City of Mt. Pleasant is resurfacing 1.01 miles on South Mission Street to improve driving quality by making the road smoother. | Pavement Improvement | 2010-03-10 | 2010-05-03 | 2010-05-28 | 2010-05-24 | 188041.91 | 1.010 | 1037004
6585 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 1037005 | The City of Rosbush is resurfacing 0.94 miles on E. Broomfield Road to improve driving quality by making the road smoother. | Pavement Improvement | 2010-03-23 | 2010-06-08 | 2010-06-25 | 2010-06-14 | 50000 | 0.940 | 1037005
6586 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ISABELLA |  | 04 | 1037006 | The City of Mt. Pleasant is resurfacing 0.219 miles on East Michigan Street to improve driving quality by making the road smoother. | Pavement Improvement | 2010-06-11 | 2010-06-28 | 2010-09-01 | 2010-09-02 | 311637.68 | 0.219 | 1037006
6587 | MICHIGAN | Underway | C250,C240 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON |  | 07 | 1038005 | I-94 near the city of Jackson in Jackson County from East of Sargent Road to the Washtenaw County Line will be rebuilt to improve mobility and reduce congestion | Pavement Improvement | 2009-10-26 | 2009-10-26 | 2012-05-02 |  | 31470300 | 22.952 | 1038005
6588 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 1038006 | The Amtrak Depot in Jackson will be rehabilitated.. | Transportation Enhancements | 2012-05-24 | 2012-05-29 | 2012-09-30 |  | 938000 | 0.000 | 1038006
6589 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 1038010 | This pavement project on W Argyle St from Wisner Street to West Avenue | Pavement Improvement | 2010-05-18 | 2010-08-02 |  | 2010-09-09 | 288351.49 | 0.253 | 1038010
6590 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | JACKSON | JACKSON | 07 | 1038014 | This pavement project near the city of Jackson on Spring Arbor Rd., from Mc Cain Road to west of Robinson Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-01 | 2010-06-21 |  | 2010-08-22 | 236975.07 | 1.211 | 1038014
6591 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO |  | 06 | 1039009 | A path for walkers and cyclists will be built on Kalamazoo River Valley Trail | Transportation Enhancements | 2009-11-18 | 2010-04-05 | 2012-10-31 |  | 1708230.65 | 6.105 | 1039009
6592 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 1039011 | To improve safety this project will realign the intersection of Texas Drive @ 8th Street | Pavement Improvement | 2010-04-09 | 2010-04-19 | 2011-07-27 | 2010-05-27 | 268563.4 | 0.062 | 1039011
6593 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO |  | 06 | 1039012 | This pavement project on Mercury Dr From MN Avenue to East County Line will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-27 | 2010-08-04 | 2010-08-19 | 2010-09-09 | 32384.65 | 2.185 | 1039012
6594 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO |  | 06 | 1039013 | This pavement project on C Avenue 24th Street and AB Avenue from D Avenue to AB Aven will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-27 | 2010-07-26 | 2010-08-06 | 2010-09-09 | 88089.66 | 3.375 | 1039013
6595 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 1039015 | This pavement project in Kalamazoo on W Michigan Ave Sprague to the west line of Section 21 will smooth the road and improve ride quality. | Pavement Improvement | 2010-06-25 | 2010-07-26 |  |  | 129441 | 0.270 | 1039015
6596 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALAMAZOO | KALAMAZOO | 06 | 1039042 | Mill and resurface | Pavement Improvement | 2010-09-10 | 2011-07-07 | 2010-09-15 | 2011-07-11 | 17931 | 1.007 | 1039042
6597 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KALKASKA |  | 04 | 1040205 | This pavement project in Kalkaska County on County Highway 612 from Darke Rd W 1/2 Mile will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-17 | 2010-06-08 | 2010-06-11 | 2010-06-11 | 27944.53 | 0.499 | 1040205
6598 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041007 | About a mile of Lake Drive From Fuller Avenue to Calton Avenue in the City of Gran in Kent County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 2009-10-26 | 2010-04-19 | 2010-07-31 | 2010-07-16 | 147293.63 | 0.190 | 1041007
6599 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 1041017 | The MDOT will resurface a half mile of the John J. Oostema Boulevard from Patterson Avenue to Gateway Drive at the Gerald Ford International Airport in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-26 | 2010-04-26 | 2010-06-30 | 2010-06-30 | 764860.66 | 1.178 | 1041017
6600 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041018 | The MDOT will replace the Diamond Avenue bridge over I-196 in Grand Rapids to improve safety and increse mobility. | Bridge Replacement | 2009-12-01 | 2009-12-01 | 2015-03-09 | 2011-08-01 | 2331959.13 | 0.000 | 1041018
6601 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041020 | The MDOT will repair almost 2 miles of M-11 from Division Avenue to kalamazoo Avenue in the City of Grand Rapids to extend the service life of the existing road. | Pavement Improvement | 2009-04-01 | 2009-04-01 | 2012-03-30 | 2010-03-29 | 2151929.63 | 1.849 | 1041020
6602 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041021 | The City of Grand Rapids is building sidewalks to improve pedestrian mobility along M-11 from Division Avenue to Kalamazoo Avenue | Pavement Improvement | 2010-03-24 | 2010-03-24 | 2012-03-31 | 2010-03-29 | 1397544.52 | 1.924 | 1041021
6603 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041022 | The Kent County Road Commission will widen three quarters of a West River Drive from Jupitor Road to the Rogue River Bridge in Kent County. This will improve mobility and the driving quality. | Pavement Improvement | 2010-04-16 | 2010-04-19 | 2010-08-15 | 2010-07-13 | 1510820.41 | 0.754 | 1041022
6604 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041024 | The City of Kentwood will resurface a 0.8 miles of East Paris Avenue from Sparks Drive to Burton Street in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-29 | 2010-05-03 | 2010-06-19 | 2010-09-25 | 537967.7 | 0.792 | 1041024
6605 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041027 | The City of Rockford will resurface a quarter mile Main Street from Division Street to Courtland Street in the City of Rockford. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-04-16 | 2010-05-14 | 2010-05-28 | 2010-05-28 | 127500 | 0.238 | 1041027
6606 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041028 | The City of Kentwood will resurface a 0.4 miles of Barden Drive from East Paris Avenue to M-37 in the City of Kentwood. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-26 | 2010-05-03 | 2010-06-11 | 2010-06-01 | 238505 | 0.353 | 1041028
6607 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041033 | This pavement project in Grand Rapids on Scribner Avenue From US-131 off ramp to Webster Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-23 | 2010-05-10 | 2010-07-01 | 2010-07-01 | 131395.23 | 0.438 | 1041033
6608 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041034 | This pavement project in Grand Rapids on Turner Avenue From Leonard Street to 6th Street. Grand Rapids will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-23 | 2010-05-10 | 2010-07-01 | 2010-07-01 | 79929.14 | 0.551 | 1041034
6609 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 1041036 | This pavement project in Kent County on Cannonsburg Road from From Giles Avenue to Meyers Lake Avenue will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-29 | 2010-05-04 | 2010-07-30 | 2010-06-10 | 142761 | 2.860 | 1041036
6610 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | KENT |  | 03 | 1041037 | This pavement project on _will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-29 | 2010-05-06 | 2010-06-18 | 2010-08-28 | 120000 | 0.903 | 1041037
6611 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041038 | Grand Rapids will repave Hall Street From US-131 SB ramps to Grandville Avenue GR | Pavement Improvement | 2010-06-15 | 2010-06-17 | 2010-06-30 | 2010-06-30 | 110121.77 | 0.162 | 1041038
6612 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041039 | The MDOT will make repairs to the bridge at 44th Street over I-196 in the City Grandville area to make the bridge last longer. | Bridge Improvement | 2009-05-11 | 2009-04-21 | 2011-03-01 | 2010-06-17 | 463317.5 | 0.000 | 1041039
6613 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041040 | The City of Walker will resurface a half mile of Veteran's Memorial Drive from Riverbend to Maynard Avenue in the City of Walker. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-06-10 | 2010-06-28 | 2010-08-11 | 2010-08-30 | 852998.39 | 1.338 | 1041040
6614 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041053 | This pavement project in Jackson on W Argyle St from West to Wisner will smooth the road and improve ride quality | Pavement Improvement | 2010-06-22 | 2010-07-06 | 2010-07-30 | 2010-07-30 | 213925.38 | 3.951 | 1041053
6615 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041115 | Rotomill/resurface | Pavement Improvement | 2011-01-06 | 2011-05-02 | 2011-06-10 | 2011-06-10 | 370705.85 | 0.506 | 1041115
6616 | MICHIGAN | Underway | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | KENT | GRAND RAPIDS | 03 | 1041127 | Bridge Replacement, Add Lanes | Bridge Replacement | 2010-09-20 | 2010-09-20 | 2013-01-31 |  | 4600000 | 0.324 | 1041127
6617 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 1044006 | From the southern Macomb County line northerly to the northern village limit of Almont and from the northern village limit northerly to just south of I-69 in Lapeer County there will be 6.20 miles of | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2012-02-01 | 2010-11-19 | 1284955.19 | 6.570 | 1044006
6618 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LAPEER |  | 10 | 1044011 | The city of Imlay will reconstruct 0.94 miles on Imlay City road to improve the driving quality by making the road smoother. | Pavement Improvement | 2010-06-15 | 2010-07-09 | 2010-10-15 | 2010-10-07 | 721039 | 1.371 | 1044011
6619 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046006 | This pavement project in Adrian on Sutton Road form Occidental to Green will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-10 | 2010-04-05 | 2010-09-03 | 2010-08-31 | 258333 | 1.144 | 1046006
6620 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046007 | 1/4 of a mile of North Ottawa Street is being resurfaced from M-50 to Evans Street in the City of Tecumseh | Pavement Improvement | 2010-06-11 | 2010-07-08 | 2010-08-13 | 2010-08-17 | 80333 | 0.284 | 1046007
6621 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046008 | This pavement project in Adrian on McKenzie Street from Maumee Street to Maple Avenue will smooth the road and improve ride quality. | Pavement Improvement | 2010-06-24 | 2010-07-12 | 2010-07-30 | 2010-07-26 | 215313.83 | 0.376 | 1046008
6622 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046009 | 1.0 miles of pavement resurfacing of North Evan Street from Burt Road to the city limits of Tecumseh | Pavement Improvement | 2010-06-11 | 2010-07-08 | 2010-08-13 | 2010-08-17 | 151072.5 | 0.572 | 1046009
6623 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LENAWEE |  | 07 | 1046010 | The community of Clinton will reconstruct 1 mile of Tecumseh/Clinton Road. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-07-01 | 2010-07-12 | 2011-06-01 | 2011-07-07 | 573122.96 | 1.322 | 1046010
6624 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LIVINGSTON |  | 08 | 1047018 | Rehabilitate Roadway | Pavement Improvement | 2010-12-15 | 2011-05-10 |  | 2011-06-03 | 361687 | 1.007 | 1047018
6625 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | LUCE |  | 01 | 1048006 | This pavement project on County Road 405 in Luce County will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-04-28 | 2010-06-08 | 2010-10-08 | 2010-07-12 | 279120.54 | 2.283 | 1048006
6626 | MICHIGAN | Completed | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | LUCE |  | 01 | 1048007 | This shoulder paving project on M-28 in Luce County will improve safety. | Pavement Improvement | 2010-02-23 | 2010-02-23 | 2010-10-18 | 2010-09-03 | 901132.04 | 5.977 | 1048007
6627 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACKINAC |  | 01 | 1049003 | This pavement project on M-134 from east of the I-75 Overpass to west of 3 M will make the road smoother and improve ride quality | Pavement Widening | 2009-10-15 | 2009-10-15 | 2010-10-18 | 2010-09-02 | 2359356.51 | 13.535 | 1049003
6628 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MACKINAC |  | 01 | 1049012 | This pavement project in Mackinac County on Borgstrom Rd US2-H40 will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-05 | 2010-06-01 | 2010-08-17 | 2010-08-30 | 400284 | 4.740 | 1049012
6629 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050006 | MDOT will rebuild concrete barrier and landscaping along I-696 from Gratiot Road to I-75 in Metro Detroit in Macomb County to improve safety | Pavement Improvement | 2010-01-25 | 2009-04-28 | 2013-12-31 |  | 10593585.3 | 17.407 | 1050006
6630 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050007 | Pavement patching to extend the service life of the existing road throughout Macomb County. | Pavement Improvement | 2010-03-11 | 2010-04-06 | 2010-07-31 | 2010-08-04 | 2862651.74 | 15.494 | 1050007
6631 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050008 | Resurfacing to maintain the pavement condition and improve ride quality of Calahan Road in Roseville. | Pavement Improvement | 2010-03-25 | 2010-04-05 | 2010-06-15 | 2010-06-16 | 366047.54 | 0.508 | 1050008
6632 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB |  | 10 | 1050009 | This pavement project on Division Street M-19 to Grand Trunk Railroad will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-03 | 2010-08-09 | 2010-08-30 | 2010-08-30 | 95000 | 0.406 | 1050009
6633 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050010 | Complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along North Fulton in Macomb County. | Pavement Improvement | 2010-04-14 | 2010-04-27 | 2011-09-16 | 2011-09-16 | 517426.48 | 0.427 | 1050010
6634 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050012 | Resurfacing to maintain the pavement condition and improve ride quality of South Main Street in Mt. Clemens. | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-06-01 | 2010-06-18 | 318321.95 | 0.348 | 1050012
6635 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050013 | Resurfacing to maintain the pavement condition and improve ride quality of Rathbone Street in Mt. Clemens. | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-06-01 | 2010-06-18 | 116341.9 | 0.264 | 1050013
6636 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050014 | Resurfacing to maintain the pavement condition and improve ride quality of Hayes Avenue in Eastpointe. | Pavement Improvement | 2010-05-13 | 2010-05-12 | 2010-08-28 | 2010-10-21 | 771921.15 | 0.510 | 1050014
6637 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050015 | Resurfacing to maintain the pavement condition and improve ride quality of | Pavement Improvement | 2010-06-03 | 2010-06-10 | 2011-05-30 | 2011-03-03 | 1250000 | 0.515 | 1050015
6638 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050016 | Macomb County will reconstruct Kelly SB from Toepfer to 8 Mile to improve driving quality by making the road smoother | Pavement Improvement | 2010-05-24 | 2010-06-01 | 2010-09-18 | 2010-12-21 | 1128751.38 | 1.642 | 1050016
6639 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050039 | Resurface road | Pavement Improvement | 2011-02-15 | 2011-04-15 | 2011-06-30 | 2011-09-13 | 776818 | 0.449 | 1050039
6640 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050040 | Resurface road | Pavement Improvement | 2011-02-15 | 2011-04-15 | 2011-06-30 | 2011-09-13 | 249183 | 0.323 | 1050040
6641 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MACOMB | DETROIT,MI | 10 | 1050053 | Resurface road | Pavement Improvement | 2010-10-27 | 2011-05-02 |  | 2011-06-01 | 187339.74 | 0.997 | 1050053
6642 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MANISTEE |  | 02 | 1051009 | The City truck route in the City of Mainistee will be resurfaced for 1 mile from 10th St to 16th St. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-04-14 | 2010-06-01 | 2010-07-02 | 2010-07-02 | 110000 | 0.900 | 1051009
6643 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MANISTEE |  | 02 | 1051011 | The Manistee County Road Commission is replacing a bridge on 9 Mile Road east of the Village of Kaleva. This will improve safety and mobility. | Pavement Improvement | 2010-02-24 | 2010-06-01 | 2010-10-01 | 2010-09-30 | 36296 | 0.080 | 1051011
6644 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 1052005 | This pavement project on County Road 545 US41 South 0.5 will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-14 | 2010-07-21 | 2010-10-01 | 2010-09-29 | 90650.41 | 0.540 | 1052005
6645 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MARQUETTE |  | 01 | 1052006 | This pavement project on Croix Street in the City of Negaunee will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-07-23 | 2010-07-29 | 2010-08-28 | 2010-09-03 | 222944.66 | 0.486 | 1052006
6646 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MASON |  | 02 | 1053003 | This pavement project on Qrtrlne/SgrGrv/Reek/Bnsn/Hwly County Line to .25 Mi S of Lak will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-22 | 2010-07-21 | 2010-08-31 | 2010-08-13 | 342215.76 | 18.239 | 1053003
6647 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MASON |  | 02 | 1053004 | This pavement project in Ludington on South Williams Street from Ludington Avenue to Filer Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-29 | 2010-05-10 | 2010-06-25 | 2010-06-25 | 171252 | 0.144 | 1053004
6648 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MECOSTA |  | 04 | 1054007 | The City of Big Rapids will resurface a half mile of Bronson Ave from Maple to Milton in the City of Big Rapids. This will improve the driving by making the road smoother. | Pavement Improvement | 2010-04-08 | 2010-07-13 | 2010-08-20 | 2010-08-10 | 206951.98 | 1.358 | 1054007
6649 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055006 | Almost 2 miles of County Road 352 from CR577 to Hallfrisch Road near the city of Stephenson in Menominee County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 2010-02-22 | 2010-08-10 | 2010-09-03 | 2010-09-03 | 268649.11 | 1.871 | 1055006
6650 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055008 | This pavement project on River Road in the Village of Stephenson will improve the drive quality and make the road smoother. | Pavement Improvement | 2010-03-09 | 2010-08-17 | 2010-08-31 | 2010-08-31 | 109572.81 | 0.359 | 1055008
6651 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055009 | Menominee County will repave County Road 581 from 0.17 Mi W of River Rd to CR577 | Pavement Improvement | 2010-02-22 | 2010-08-12 | 2010-09-03 | 2010-09-03 | 66460.55 | 1.274 | 1055009
6652 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055012 | This pavement project in Menominee on 14th Avenue from 1st Street to 13th Street will smooth the road and improve ride quality | Pavement Improvement | 2010-06-01 | 2010-08-16 | 2010-08-15 | 2010-11-12 | 175000 | 0.456 | 1055012
6653 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MENOMINEE |  | 01 | 1055019 | Resurface | Pavement Improvement | 2010-08-25 | 2010-09-02 | 2010-10-01 | 2010-10-01 | 81000 | 1.464 | 1055019
6654 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MIDLAND |  | 04 | 1056008 | This pavement project in Midland on North Saginaw Road from S.B.S. RR Xing to 3752 Feet North and Austin to J will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-09 | 2010-06-14 | 2010-09-03 | 2010-09-03 | 470000 | 0.630 | 1056008
6655 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MISSAUKEE |  | 04 | 1057008 | This pavement project in Missaukee County on N Lucas Rd from Manistee River to County Line will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-30 | 2010-06-15 | 2010-06-25 | 2010-06-16 | 60072.5 | 1.884 | 1057008
6656 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058010 | There will be a culvert rehabilitation of the culvert at the Springbrook Drain at Sterns Road in southern Monroe county south of the city of Luna Pier. This project will provide to effect county drain drainage while improving the drain crossing at Sterns | Pavement Improvement | 2010-01-27 | 2010-05-10 | 2010-07-16 | 2010-07-01 | 334074.86 | 0.037 | 1058010
6657 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058012 | This pavement project in Monroe County on LaPlaisance Road from Sixth Street to Jones Avenue will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-06 | 2010-07-26 | 2010-07-31 | 2010-10-25 | 280000 | 0.348 | 1058012
6658 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058013 | Monroe County will repave Erie Road from US-24 to M-125 | Pavement Improvement | 2010-02-08 | 2010-02-10 | 2010-09-30 | 2010-12-06 | 9600 | 0.557 | 1058013
6659 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058014 | This project near Temperance will smooth the pavement at the intersection of Jackman Road and Smith Road to improve the ride quality. | Pavement Improvement | 2010-02-17 | 2010-03-05 | 2010-10-07 | 2010-10-14 | 91117.5 | 0.048 | 1058014
6660 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058015 | Various pavements county wide will be resurfaced in Monroe County to smooth the roads and improve ride quality. | Pavement Improvement | 2010-02-17 | 2010-03-05 | 2010-10-07 | 2010-09-01 | 32943.24 | 1.651 | 1058015
6661 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058016 | This project will resurface the roadway at 2 locations; on Laplaissance Road from Dunbar Road to Jones Avenue in the city of Monroe | Pavement Improvement | 2010-02-17 | 2010-04-30 | 2010-11-25 | 2010-10-15 | 219071.83 | 1.593 | 1058016
6662 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | DETROIT,MI | 15 | 1058017 | 0.14 miles of pavement resurfacing on Fort Road from South Huron River Drive to the Wayne County Line in northern Monroe County. This project will improve pavement rideability and increase pavement smoothness. | Pavement Improvement | 2010-02-17 | 2010-05-04 | 2010-11-25 | 2010-10-15 | 30106.02 | 0.137 | 1058017
6663 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE |  | 15 | 1058018 | Various pavements county wide will be resurfaced in Monroe County to smooth the roads and improve ride quality. | Pavement Improvement | 2010-02-17 | 2010-03-05 | 2010-10-07 | 2010-11-09 | 152810.11 | 5.009 | 1058018
6664 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE |  | 15 | 1058019 | This project will provide for 1/2 mile of pavement resurfacing on North Dixie Highway from the Fermi Railroad crossing to Post Road north of the city of Monroe in Monroe County. This will provide for improved pavement rideability and increased pavement s | Pavement Improvement | 2010-02-17 | 2010-03-05 | 2010-09-30 | 2010-10-14 | 67051.5 | 0.503 | 1058019
6665 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058020 | Various pavements county wide will be resurfaced in Monroe County to smooth the roads and improve ride quality. | Pavement Improvement | 2010-02-17 | 2010-06-21 | 2010-10-07 | 2010-09-01 | 4160 | 6.135 | 1058020
6666 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058021 | This project will provide for 3/4 of a mile of pavement resurfacing on Albain Road from the Railroad crossing to M-125 in the city of Monroe in Monroe County. This will provide for improved pavement rideability and increased pavement smoothness. | Pavement Improvement | 2010-02-17 | 2010-05-04 | 2010-11-25 | 2010-10-15 | 67844.59 | 0.735 | 1058021
6667 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | MONROE | 15 | 1058022 | This project will provide for 1.29 miles of pavement resurfacing on North Dixie Highway from Ternes Drive to Hurd Road in the city of Monroe | Pavement Improvement | 2010-07-12 | 2010-07-20 | 2010-11-12 | 2010-10-28 | 219000 | 1.288 | 1058022
6668 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE |  | 15 | 1058023 | Chip and Seal treatment at 3 locations in Monroe County. Sterns Road from M-125 to Summit Raod | Pavement Improvement | 2010-02-19 | 2010-02-23 | 2010-09-30 |  | 75047.31 | 5.635 | 1058023
6669 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE |  | 15 | 1058024 | This project will provide for 1.94 miles of pavement resurfacing on Luna Pier Road from M-125 to I-75 west of the city of Luna Pier in southern Monroe County. This will provide for improved pavement rideability and increased pavement smoothness. | Pavement Improvement | 2010-02-19 | 2010-03-05 | 2010-09-13 | 2010-08-12 | 166214.87 | 1.939 | 1058024
6670 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058025 | MDOT is resurfacing the pavement and shoulders of 1.43 miles of M-125 from the Michigan/Ohio State Line to Sterns Road. This project will improve the pavement condition and ride quality. | Pavement Improvement | 2010-02-23 | 2010-02-23 | 2010-09-02 | 2010-09-01 | 173748.17 | 1.430 | 1058025
6671 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | TOLEDO (OH) | 15 | 1058026 | The Monroe County Road Commission will be resurfacing 0.6 miles of Lewis Avenue from the Ann Arbor Railroad Crossing to Pickard Avenue. This project will improve the pavement condition and ride quality. | Pavement Improvement | 2010-02-23 | 2010-03-05 | 2010-10-13 | 2010-10-14 | 151197.72 | 0.602 | 1058026
6672 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | MONROE | STATEWIDE | 15 | 1058031 | Resurface | Pavement Improvement | 2010-04-07 | 2010-04-20 | 2010-11-25 | 2010-10-15 | 162776.82 | 2.040 | 1058031
6673 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059009 | This pavement project in Montcalm County on Newcosta/Mt Hope/Sidney Rds from Pakes-Cond;M66-Derby;M82-Kndvlle will improve the drive quality and make the road smoother | Pavement Improvement | 2010-07-09 | 2010-07-21 | 2010-07-30 | 2010-07-28 | 25364.9 | 13.545 | 1059009
6674 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059010 | This pavement project in Montcalm County on County Road 510/Sidney Rd from Derby Rd to Sheridan Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-08-16 | 2010-08-27 | 2010-08-19 | 53622.42 | 3.015 | 1059010
6675 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059011 | This pavement project in Montcalm County on Lake Montcalm Rd NW from Sheridan Road to Wyman Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-07-12 | 2010-08-27 | 2010-08-05 | 36397.33 | 2.050 | 1059011
6676 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059012 | This pavement project in Montcalm County on S Mount Hope Rd from Stanton Rd to Condensary Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-07-29 | 2010-08-27 | 2010-08-19 | 70877 | 6.186 | 1059012
6677 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059013 | This pavement project in Greenvile on Hillcrest Street from north M-57 to Grove Street will smooth the road and improve ride quality. | Pavement Improvement | 2010-05-20 | 2010-07-12 | 2010-07-31 | 2010-08-14 | 65120 | 0.309 | 1059013
6678 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTCALM |  | 04 | 1059014 | This project in rural Montcalm County will resurface 3.3 miles of pavement on N. Lakeview Rd./Newcosta Rd. improving the ride quality. | Pavement Improvement | 2010-02-23 | 2010-07-21 | 2010-08-27 | 2010-08-24 | 55732 | 3.388 | 1059014
6679 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTMORENCY |  | 01 | 1060006 | Over 3 miles of County Road 624 from CR459 to Ess Lake Road near the city of Hillman in Montmorency County will be repaved to improve ride quality and make the road smoother | Other | 2009-10-23 | 2009-11-01 | 2010-08-15 | 2010-06-11 | 10475.5 |  | 1060006
6680 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTMORENCY |  | 01 | 1060008 | This pavement project in Montmorency County on County Road 624 from CR459 to Ess Lake Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-04-05 | 2011-06-30 | 2011-06-11 | 266568.37 | 3.051 | 1060008
6681 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MONTMORENCY |  | 01 | 1060009 | This countywide Pavement Marking project in rural Montmorency County will improve traffic operations. | Safety/Traffic Management | 2010-06-29 | 2010-09-17 | 2011-06-30 | 2010-09-21 | 36569.82 | 1.289 | 1060009
6682 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 1061305 | The MDOT is installing cable guard rail on US-31 from Airline Rd north to Marquette Ave in the Cities of Norton Shores and Muskegon to improve safety. | Safety/Traffic Management | 2009-10-15 | 2009-10-15 | 2011-06-30 | 2011-09-13 | 717712.24 | 10.075 | 1061305
6683 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 1061308 | The City of Norton Shores will resurface a half mile of Sherman Ave from Peck St to Riordan St. This will improve driving quality by making the road smoother. | Pavement Improvement | 2010-03-11 | 2010-04-29 | 2010-06-11 | 2010-06-07 | 199133.92 | 0.442 | 1061308
6684 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 1061314 | The City of Whitehall will resurface a 0.8 miles of White Lake Dr from Whitehall Rd to Hyde Park Rd. This will improve driving quality by making the road smoother. | Pavement Improvement | 2010-05-21 | 2010-05-25 |  | 2010-06-04 | 124318.75 | 0.794 | 1061314
6685 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON |  | 02 | 1061316 | Eight miles of Scenic Drive in the City of North Muskegon will be resurfaced from Fenner Rd to South Shore Drive. This will improve driving quality by making the road smoother. | Pavement Improvement | 2010-06-17 | 2010-06-28 |  | 2010-11-05 | 1276972.65 | 9.527 | 1061316
6686 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | MUSKEGON | MUSKEGON-MUSKEGON HEIGHTS | 02 | 1061349 | Resurface | Pavement Improvement | 2010-10-29 | 2011-04-20 |  | 2011-05-09 | 102632 | 0.500 | 1061349
6687 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | NEWAYGO |  | 02 | 1062006 | A little over 3 miles of Alger Road from 128th Street to Moore Road near the city of Grant in Newaygo County will be repaved to improve ride quality and make the road smoother | Other | 2009-10-23 | 2010-03-23 | 2010-07-30 | 2010-08-06 | 20253.11 |  | 1062006
6688 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | NEWAYGO |  | 02 | 1062007 | North Stone Rd will be resurfaced for one half mile from Main St to 44th St in the village of Fremont.. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-24 | 2010-05-17 | 2010-06-11 | 2010-05-26 | 95000 | 0.500 | 1062007
6689 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | NEWAYGO |  | 02 | 1062009 | Newaygo County will do a pavement project on Alger Road 128th from Street to Moore Road to improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-03-23 | 2010-07-30 | 2010-08-06 | 587372.46 | 2.013 | 1062009
6690 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063003 | Complete pavement replacement to restore a safe smooth driving surface and maintain the mobilty along US-24 in Bloomfield Township by MDOT. | Pavement Improvement | 2010-01-19 | 2010-01-19 | 2013-01-19 | 2011-08-29 | 7849832.73 | 1.930 | 1063003
6691 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063008 | This pavement project on Joslyn Ave Walton to North City Limits will improve the drive quality and make the road smoother | Pavement Improvement | 2010-03-24 | 2010-07-07 | 2010-10-01 | 2010-10-01 | 263000 | 0.540 | 1063008
6692 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063009 | Resurfacing to maintain the pavement condition and improve ride quality of Wayne Street in Pontiac. | Pavement Improvement | 2010-03-24 | 2010-05-26 | 2010-07-02 | 2010-07-01 | 187000 | 0.321 | 1063009
6693 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063010 | New pedestrian bridge to improve safety and pedestrian access over US-24 in Pontiac. | Transportation Enhancements | 2010-07-15 | 2010-07-27 | 2010-11-15 | 2011-07-18 | 1960239.16 | 0.125 | 1063010
6694 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063011 | Resurfacing to maintain the pavement condition and improve ride quality of 12 Mile Road in Lathrup Village. | Pavement Improvement | 2010-03-30 | 2010-05-10 | 2010-09-30 | 2010-09-10 | 1031000 | 0.987 | 1063011
6695 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063013 | Resurfacing to maintain the pavement condition and improve ride quality of Centerpoint Parkway in Pontiac. | Pavement Improvement | 2010-04-20 | 2010-05-10 | 2010-08-25 | 2010-08-25 | 638489.58 | 1.282 | 1063013
6696 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063014 | Resurfacing to maintain the pavement condition and improve ride quality of Opdyke Road in Auburn Hills. | Pavement Improvement | 2010-04-14 | 2010-04-17 | 2010-08-01 | 2010-07-28 | 811756.29 | 1.059 | 1063014
6697 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063015 | Resurfacing to maintain the pavement condition and improve ride quality of Middlebelt Road in Farmington Hills. | Pavement Improvement | 2010-04-01 | 2010-04-19 | 2010-08-30 | 2010-10-08 | 1033000 | 1.982 | 1063015
6698 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063016 | Resurfacing to maintain the pavement condition and improve ride quality of Middlebelt Road in Farmington Hills. | Pavement Improvement | 2010-04-01 | 2010-04-19 | 2010-08-30 | 2010-10-08 | 673000 | 2.003 | 1063016
6699 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063017 | This pavement project on Inkster Road from 9 Mile to 11 Mile in the City of Southfield will improve the drive quality and make the road smoother | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2010-10-15 |  | 1964000 | 1.000 | 1063017
6700 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | SOUTH LYON-HOWELL-BRIGHTON | 09 | 1063019 | This pavement project in South Lyonon Nine Mile Road from Dean Drive to Pontiac Trail will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-26 | 2010-06-18 | 2010-09-30 | 2010-09-16 | 509000 | 0.473 | 1063019
6701 | MICHIGAN | Completed | C200,C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063020 | This pavement project in Oakland County Countywide at 3 locations in Oakland County will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-06 | 2010-07-08 | 2010-08-25 | 2010-09-10 | 817280.24 | 6.233 | 1063020
6702 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND |  | 09 | 1063021 | This pavement project in Oakland County on Grange Hall Road from West Village Limits to North Holly Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-06 | 2010-07-08 | 2010-08-25 | 2010-09-10 | 91737.8 | 0.622 | 1063021
6703 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063022 | This pavement project in Ferndale on Fern Avenue From Chesterfield to Intermodal Ave will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2010-09-13 | 2010-09-26 | 287679.64 | 0.187 | 1063022
6704 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063023 | This pavement project in Ferndale on Chesterfield From Fair to Fern will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2010-09-13 | 2010-09-26 | 173533.06 | 0.526 | 1063023
6705 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063024 | Resurfacing to maintain the pavement condition and improve ride quality of Cooley Lake Road in Waterford. | Pavement Improvement | 2010-05-06 | 2010-05-07 | 2010-11-12 | 2010-11-09 | 1121451.71 | 0.472 | 1063024
6706 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063025 | Resurfacing to maintain the pavement condition and improve ride quality of White Lake Road in Clarkston. | Pavement Improvement | 2010-05-13 | 2010-05-19 | 2010-09-01 | 2010-10-15 | 986000 | 0.937 | 1063025
6707 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063026 | Paving Ray Road east of M-24 to Oxford Road in Oakland County. | Pavement Improvement | 2010-06-11 | 2010-06-21 | 2010-10-15 | 2010-10-15 | 1284335.47 | 0.704 | 1063026
6708 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063027 | Resurfacing to maintain the pavement condition and improve ride quality of Hilton Road in Detroit. | Pavement Improvement | 2010-05-20 | 2010-06-29 | 2010-09-01 | 2010-09-07 | 475000 | 0.518 | 1063027
6709 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063029 | This pavement project near Farmington on Orchard Lake Road from 12 Mile Road to 13 Mile Road will smooth the road and improve ride quality | Pavement Improvement | 2010-05-12 | 2010-05-19 | 2010-08-20 | 2010-08-13 | 864000 | 0.372 | 1063029
6710 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063030 | This pavement project in Pontiac on Walton Road from Joslyn to East City Limits will smooth the road and improve ride quality | Pavement Improvement | 2010-05-20 | 2010-07-06 | 2010-10-29 | 2010-10-29 | 716000 | 1.487 | 1063030
6711 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063031 | This pavement project in Farmington Hills on Grand River Avenue from Haggerty to Ten Mile Road will smooth the road and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-06-24 | 2010-09-25 | 2010-12-02 | 1253938.76 | 0.260 | 1063031
6712 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063032 | This pavement project on Main Street from 13 Mile Road to Chippewa in Royal Oak will smooth the road and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-08-02 | 2010-10-30 | 2011-09-09 | 391000 | 0.462 | 1063032
6713 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063033 | This pavement project on Lincoln Street from Campbell to Stephenson in Royal Oak will smooth the road and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-06-16 | 2010-11-30 | 2010-11-24 | 506000 | 0.499 | 1063033
6714 | MICHIGAN | Completed | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063035 | The City of Hazel Park in Metro Detroit will be resurfacing 2.56 miles of the Chrysler Service Drive between 8 Mile Rd. and 9 Mile Rd. This project will improve pavement condition and ride quality. | Pavement Improvement | 2010-02-23 | 2010-07-12 | 2010-11-14 | 2011-05-11 | 1168000 | 2.539 | 1063035
6715 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | OAKLAND | DETROIT,MI | 09 | 1063044 | Resurface, Rehab, or Restore | Pavement Improvement | 2010-04-01 | 2010-07-12 | 2010-11-14 | 2011-05-11 | 1017000 | 2.117 | 1063044
6716 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 1065006 | The Ogemaw County Road Commission will resurface a half mile of Sage Lake Rd from Harrison Rd to the village limits of Prescott. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-24 | 2010-08-02 | 2010-08-27 | 2010-08-06 | 27757.04 | 0.370 | 1065006
6717 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 1065007 | The Ogemaw County Road Commission will resurface 5.5 miles of West State Rd from Fairview Rd to M-33 east of West Branch. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-10 | 2010-07-23 | 2010-08-27 | 2010-08-05 | 270234.93 | 5.490 | 1065007
6718 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OGEMAW |  | 01 | 1065015 | Resurface | Pavement Improvement | 2011-02-18 | 2011-02-18 | 2011-06-24 | 2011-06-24 | 40096 | 0.601 | 1065015
6719 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ONTONAGON |  | 01 | 1066007 | This pavement project on East Shore Rd 4.0 Mi S of M28 to 7.5 Mi S will improve the drive quality and make the road smoother | Pavement Improvement | 2010-06-02 | 2010-09-01 | 2010-10-15 | 2010-10-08 | 335005.56 | 3.559 | 1066007
6720 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ONTONAGON |  | 01 | 1066008 | This guardrail installation project on M-26 in Ontonagon County will improve safety. | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2010-09-17 | 2010-09-30 | 506702.94 | 31.324 | 1066008
6721 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | ONTONAGON |  | 01 | 1066009 | The culvert project on M-28 in Ontonagon and Dickinson Counties will improve drainage and safety | Pavement Improvement | 2010-02-17 | 2010-02-17 | 2010-07-30 | 2010-07-15 | 160624.63 | 0.000 | 1066009
6722 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 1067006 | A little over 4 miles of River/115th/4 Mile Rpad snear the city of Evart in Osceola County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 2009-10-21 | 2010-05-17 | 2010-07-01 | 2011-04-04 | 228703.25 | 4.143 | 1067006
6723 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | OSCEOLA |  | 04 | 1067016 | HMA Paving of Rail Trail | Transportation Enhancements | 2011-01-13 | 2011-01-13 | 2012-02-01 | 2011-07-22 | 119470.94 | 10.981 | 1067016
6724 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 1068005 | The Oscoda County Road Commission will replace a drainage culvert on Cherry Creek Rd 200 ft west of West Camp Ten Rd to improve drainage and extend the life of the roadway. | Pavement Improvement | 2010-02-09 | 2010-03-19 | 2010-07-30 | 2010-08-03 | 59083 | 0.384 | 1068005
6725 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 1068006 | The Oscoda County Road Commission will replace a drainage culvert on East Kittle Rd 100 ft east of Caldwell Rd to improve drainage and extend the life of the roadway. | Pavement Improvement | 2010-02-09 | 2010-04-08 | 2010-08-30 | 2010-08-03 | 24610 | 0.565 | 1068006
6726 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 1068007 | The Oscoda County Road Commission will replace a drainage culvert on East Kittle Rd 800 ft east of M-33 to improve drainage and extend the life of the roadway. | Pavement Improvement | 2010-02-09 | 2010-04-08 | 2010-10-31 | 2010-10-11 | 55413 | 0.786 | 1068007
6727 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OSCODA |  | 01 | 1068008 | The Oscoda County Road Commission will replace a drainage culvert on Zimowske Rd 900 ft east of Mishler Rd to improve drainage and extend the life of the roadway. | Pavement Improvement | 2010-02-17 | 2010-04-08 | 2010-07-30 | 2010-08-03 | 20945 | 1.043 | 1068008
6728 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTSEGO |  | 01 | 1069003 | 0.3 miles of Meecher Rd from Anna Dr to Buddy Ave will be resurfaced west of Gaylord . This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2010-06-04 | 2010-06-02 | 150000 | 0.304 | 1069003
6729 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | HOLLAND | 02 | 1070006 | Zeeland County will repave 104th Avenue from Paw Paw Drive to I-196 BL in Holland | Pavement Improvement | 2010-03-23 | 2010-04-19 | 2010-07-16 | 2010-10-07 | 506085 | 0.284 | 1070006
6730 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 1070008 | The MDOT will resurface 3.5 miles of M-104 from 144th Ave east to I-96 near Spring Lake. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-05-11 | 2009-05-11 | 2012-03-31 | 2010-09-20 | 895094.03 | 3.468 | 1070008
6731 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA |  | 02 | 1070009 | This pavement project near Eastmanville on 68th Ave from Leonard Street to I-96 will smooth the road and improve ride quality | Pavement Improvement | 2010-06-01 | 2010-06-15 | 2010-07-09 | 2010-07-10 | 163866 | 2.731 | 1070009
6732 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | GRAND RAPIDS | 02 | 1070013 | The MDOT will resurface 2 miles of M-121 from 40th Ave to Rush Creek near Hudsonville. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-02-17 | 2010-02-17 | 2012-03-31 | 2011-08-08 | 2627197.9 | 4.029 | 1070013
6733 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | OTTAWA | HOLLAND | 02 | 1070064 | Resurface | Pavement Improvement | 2010-12-14 | 2011-05-03 | 2011-06-10 | 2011-06-16 | 246572.47 | 1.009 | 1070064
6734 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | PRESQUE ISLE |  | 01 | 1071003 | The Presque Isle County Road Commission will resurface 1.5 miles of East Heythaler Highway from US-23 to County Road 451 south of Rogers City. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-24 | 2010-05-10 | 2011-06-30 | 2010-06-04 | 352152 | 1.442 | 1071003
6735 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | PRESQUE ISLE |  | 01 | 1071009 | HMA Reconstruction | Pavement Improvement | 2010-09-20 | 2010-09-20 | 2012-03-20 |  | 154118.74 | 1.380 | 1071009
6736 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ROSCOMMON |  | 04 | 1072006 | Over 2 miles of US Old 27 from Mary Road to Yeager Road near the city of Houghton Lake in Roscommon County will have its shoulder widened to improve safety and improve mobility | Pavement Improvement | 2009-10-26 | 2009-10-26 | 2010-07-15 | 2010-06-28 | 118487.28 | 2.218 | 1072006
6737 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ROSCOMMON |  | 04 | 1072014 | Rosscommon County will repave M 76 from Madision St-Artesia Beach Rd | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-11-12 | 2010-12-22 | 414854.37 | 1.884 | 1072014
6738 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ROSCOMMON |  | 04 | 1072015 | The Roscommon County Road Commission is resurfacing 0.8 miles of Loxley Road in the community of Houghton Lake to improve the ride quality of the road. | Pavement Improvement | 2010-06-17 | 2010-08-17 | 2010-09-01 | 2010-08-25 | 44289.61 | 0.819 | 1072015
6739 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073006 | In the city of Saginaw, MDOT will resurface 8.78 miles on M-81 from Indiantown Road easterly to Wadsworth Avenue to improve the driving quality of the roadway. | Pavement Improvement | 2009-10-15 | 2009-10-15 | 2012-12-31 | 2010-07-02 | 1168846.36 | 8.780 | 1073006
6740 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073007 | This pavement project on Ditch Rd Briggs Rd to Sheridan Rd will improve the drive quality and make the road smoother | Pavement Improvement | 2009-11-10 | 2010-08-05 | 2010-08-12 | 2010-08-12 | 65000 | 3.972 | 1073007
6741 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073008 | In Thomas Township there is 5.31 miles of resurfacing on Brant Fordney & Ring Roads to improve driving quality by making the road smoother. | Pavement Improvement | 2009-11-10 | 2010-08-04 | 2010-08-11 | 2010-08-11 | 66000 | 4.287 | 1073008
6742 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073009 | In Thomas Township there is 4.18 miles of resurfacing on Fordney & Hemlock Roads to improve driving quality by making the road smoother. | Pavement Improvement | 2009-11-10 | 2010-08-03 | 2010-08-05 | 2010-08-05 | 70000 | 4.188 | 1073009
6743 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SAGINAW |  | 04 | 1073010 | The City of SaginawThomas Township & Saginaw Township is resurfacing 5.33 miles on various locations from River through Midland Road to improve driving quality by making the road smoother. | Pavement Improvement | 2009-11-10 | 2010-08-02 | 2010-08-04 | 2010-08-04 | 80993.12 | 5.131 | 1073010
6744 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SANILAC |  | 10 | 1074006 | This pavement project on West French Line Road over the Elk Creek Bridge in Sanilac County will improve the drive quality and make the road smoother | Bridge Replacement | 2010-04-02 | 2010-05-19 | 2010-07-16 | 2010-07-12 | 357422 | 0.865 | 1074006
6745 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SANILAC |  | 10 | 1074007 | This pavement project in Sandusky on Cambell Road from Industrial Road to Miller Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-01 | 2010-06-22 | 2010-07-31 | 2010-08-09 | 293769.33 | 0.098 | 1074007
6746 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 1075003 | This shoulder paving project on County Road 442 in Schoolcraft County will improve safety. | Pavement Improvement | 2009-10-21 | 2010-06-14 | 2010-09-30 | 2010-09-30 | 94000 | 4.039 | 1075003
6747 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SCHOOLCRAFT |  | 01 | 1075006 | Schoolcraft county will resurface County Road 442 from US-2 to M-149 to make the road smoother and improve the ride quality. | Pavement Improvement | 2009-12-11 | 2010-07-01 | 2010-09-30 |  | 11952 | 6.410 | 1075006
6748 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 1076003 | Almost 3 miles of S Delaney Rd near the city of Owosso in Shiawassee County will be repaved to improve ride quality and make the road smoother | Pavement Improvement | 2010-02-19 | 2010-04-26 | 2010-05-29 | 2010-05-25 | 508914 | 2.681 | 1076003
6749 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 1076007 | This pavement project near Ann Arbor on Shiawassee Street from Walnut Street to 100' south of St Mary Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-17 | 2010-06-14 |  | 2010-08-05 | 180000 | 0.120 | 1076007
6750 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 1076008 | This pavement project near Ann Arbor on Shiawassee Street from Walnut Street to 100' south of St Mary Street will improve the drive quality and make the road smoother | Transportation Enhancements | 2010-06-08 | 2010-06-09 | 2010-08-30 | 2010-11-11 | 50000 | 0.202 | 1076008
6751 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | SHIAWASSEE |  | 04 | 1076009 | 0.26 miles of pavement resurfacing on East Main Street from the Mercer Street to the East City limits of Durand | Pavement Improvement | 2010-06-08 | 2010-06-14 |  | 2010-10-14 | 52000 | 0.258 | 1076009
6752 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077216 | Resurfacing to maintain the pavement condition and improve ride quality of Scott Avenue in Port Huron. | Pavement Improvement | 2010-02-19 | 2010-05-03 | 2010-07-31 | 2010-06-15 | 137792.9 | 0.101 | 1077216
6753 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077223 | Resurfacing to maintain the pavement condition and improve ride quality of Fred W. Moore Highway in St. Clair. | Pavement Improvement | 2010-03-30 | 2010-04-26 | 2010-07-02 | 2010-07-08 | 241538.02 | 0.277 | 1077223
6754 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077227 | This project will improve drainage by replacing a culvert at Ravenswood Road At Michigan Avenue to Huffman Drain | Pavement Improvement | 2010-04-23 | 2010-05-10 | 2010-08-20 | 2010-08-20 | 264882.59 | 0.160 | 1077227
6755 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077229 | This pavement project in St. Clair on St. Clair Highway from Oak Street to Palmer Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-03 | 2010-05-14 | 2010-07-31 | 2010-09-01 | 314607.27 | 0.311 | 1077229
6756 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077230 | Resurfacing to maintain the pavement condition and improve ride quality of Fred W. Moore Highway in St. Clair. | Pavement Improvement | 2010-06-08 | 2010-07-29 | 2010-10-10 | 2010-09-17 | 423922.72 | 0.051 | 1077230
6757 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST CLAIR | PORT HURON | 10 | 1077247 | Resurface | Pavement Improvement | 2010-11-17 | 2011-05-11 | 2012-05-31 | 2011-08-04 | 843981.83 | 0.711 | 1077247
6758 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078004 | The St. Joseph County Road Commisssion is installing pavement marking to improve safety on 223 miles of roads throughout the county. | Pavement Improvement | 2010-04-20 | 2010-04-30 | 2011-07-27 | 2010-10-12 | 142091.33 | 8.070 | 1078004
6759 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078006 | The St. Joseph County Road Commisssion will resurface 3 miles of Bent Road from M-216 to Dutch Settlement Road in the northwest corner of the county. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-22 | 2010-07-22 | 2010-08-02 | 2010-08-02 | 41760 | 3.048 | 1078006
6760 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078007 | The St. Joseph County Road Commisssion will resurface 7.8 miles of Featherstone Road from M-66 to Engle Road north of Sturgis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2009-12-22 | 2010-07-22 | 2010-08-03 | 2010-08-03 | 86117 | 7.790 | 1078007
6761 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078008 | The City of Sturgis will resurface 0.6 miles of North Centerville Road from West Lafayette Road to Haines Boulevard in the city. This will improve the driving quality by making the road smoother. | Other | 2010-04-16 | 2010-04-27 | 2011-07-27 | 2010-06-11 | 125000 | 0.622 | 1078008
6762 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078009 | The St. Joseph County Road Commisssion will resurface 0.5 miles of Big Hill Road from M-12 to Lafayette Road in Sturgis. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-01-27 | 2010-03-01 | 2011-07-27 | 2010-08-26 | 130000 | 0.532 | 1078009
6763 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | ST JOSEPH |  | 06 | 1078010 | This pavement project on Spring Street from West Michigan to Millard Street will make the road smoother and improve ride quality | Pavement Improvement | 2010-06-01 | 2010-06-28 | 2011-07-27 | 2010-10-01 | 185000 | 0.181 | 1078010
6764 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 1079006 | The Tuscola County Road Commission will replace the West Cass City Rd bridge over the Allen drain to improve safety and mobility. | Bridge Replacement | 2010-02-01 | 2010-04-05 | 2010-08-28 | 2010-06-25 | 342711 | 0.489 | 1079006
6765 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 1079007 | The Tuscola County Road Commission will resurface 2 miles of Irish Rd from Willard to Birch Run south of the Village of Millington. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-03-04 | 2010-08-12 | 2010-08-31 | 2010-08-27 | 288453.37 | 2.027 | 1079007
6766 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 1079009 | The community of Caro is resurfacing 0.94 miles of Hooper Street to improve the pavement condition and ride quality of the road. | Pavement Improvement | 2010-05-03 | 2010-07-06 | 2010-09-30 | 2010-08-23 | 100000 | 0.943 | 1079009
6767 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | TUSCOLA |  | 05 | 1079010 | The community of Mayville is resurfacing 0.5 miles of Fulton Street to improve the pavement condition and ride quality of the road. | Pavement Improvement | 2010-06-01 | 2010-06-14 | 2010-08-15 | 2010-07-14 | 90198 | 0.504 | 1079010
6768 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 1080008 | The Van Buren County Road Commisssion is building a paved pathway for 0.33 miles along the Kal-Haven State Trail from 10th Street (Kalamazoo Street) to CR 655 in Bloomingdale for cyclists walkers and joggers to promote alternative modes of transportatio | Transportation Enhancements | 2009-12-23 | 2010-05-03 | 2011-07-27 |  | 900000 | 0.333 | 1080008
6769 | MICHIGAN | Underway | C200,C240 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 1080009 | MDOT will resurface 1.5 miles of M-40 from St. Joseph Avenue to Power Plant Road in Paw Paw. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-01-19 | 2010-01-19 | 2011-11-22 |  | 2308760.33 | 1.460 | 1080009
6770 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 1080011 | The Van Buren County Road Commisssion will resurface 0.3 miles of 73rd Street from Phoenix Street to the Tractor Supply Store in South Haven. This will improve the driving quality by making the road smoother. | Pavement Improvement | 2010-07-20 | 2010-08-16 | 2013-08-07 | 2010-10-22 | 125000 | 0.280 | 1080011
6771 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | VAN BUREN |  | 06 | 1080014 | This project Van Buren County will replace the culbert on CR653/29th St Over North Branch of Paw Paw River to improve drainage and safety. | Bridge Replacement | 2010-04-23 | 2010-07-07 | 2013-08-07 | 2010-08-30 | 164336.25 | 0.219 | 1080014
6772 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081002 | 2.28 miles of nonmotorized path expansion at various location throughout the city of Ann Arbor. This project will enhance nonmotorized and pedestrian mobilty and safety throughout 34 locations throughout the city. | Safety/Traffic Management | 2009-12-09 | 2010-08-02 | 2011-05-06 |  | 250000 | 2.278 | 1081002
6773 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | DETROIT,MI | 07 | 1081003 | The Historic Freighthouse in Ypsilant will receive a makeover. | Transportation Enhancements | 2010-03-01 | 2010-03-19 | 2010-05-28 | 2010-07-05 | 270465.81 | 0.000 | 1081003
6774 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW |  | 07 | 1081004 | This pavement project in Milan on Marvin Street from the County Street to Michigan Miller Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-16 | 2010-06-30 | 2010-07-30 | 2010-08-13 | 125000 | 0.362 | 1081004
6775 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081005 | This pavement project in Ann Arbor on Wagner Road from Ann Arbor-Saline Road to Liberty Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 82600 | 2.412 | 1081005
6776 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081006 | This pavement project in Ypsilanti on Textile Road from Deer Creek Drive to Stony Creek Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 34100 | 1.468 | 1081006
6777 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081007 | This pavement project in Ann Arbor on Scio Church Road from Zeeb Road to Tessmer Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 19198.65 | 0.752 | 1081007
6778 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081008 | This pavement project in Ann Arbor on Zeeb Road from Pratt Road to Scio Road will improve the drive quality and make the road smoother | Pavement Improvement | 2010-01-08 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 40600 | 0.595 | 1081008
6779 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081009 | This pavement project will improve the drive quality and make the road smoother at four locations in the Ann Arbor area. | Pavement Improvement | 2010-01-12 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 409200 | 1.380 | 1081009
6780 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081010 | This pavement project on Ellsworth from Maple Road to State will make the road smoother and improve ride quality | Pavement Improvement | 2010-01-12 | 2010-04-01 | 2010-12-31 | 2010-12-31 | 387700 | 2.040 | 1081010
6781 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081011 | Washtenaw County will repave Dexter Ann Arbor Road From Kensington to Meadow View in Dexter | Pavement Improvement | 2010-04-01 | 2010-06-14 | 2010-07-26 | 2010-09-14 | 100000 | 0.241 | 1081011
6782 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081014 | This pavement project in Washtenaw County on Mansfield Street from Westmoorland Street to Congress Street will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-04-02 | 2010-09-20 | 2010-11-01 | 502469.15 | 0.321 | 1081014
6783 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081015 | This pavement project in Washtenaw County on College Place from West Cross to Forest will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-03 | 2010-04-02 | 2010-08-27 | 2010-09-16 | 204000 | 0.105 | 1081015
6784 | MICHIGAN | Underway | C240,C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081017 | Ann Arbor will repave Plymouth and Green Roads from Nixon to US-23 & Plymouth to Hubbard | Pavement Improvement | 2010-02-08 | 2010-06-03 | 2013-12-28 |  | 2232914.38 | 1.756 | 1081017
6785 | MICHIGAN | Completed | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | DETROIT,MI | 07 | 1081027 | Historic Preservation | Transportation Enhancements | 2010-08-03 | 2010-08-16 | 2010-10-15 | 2010-10-20 | 124863.42 | 0.000 | 1081027
6786 | MICHIGAN | Underway | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW |  | 07 | 1081038 | Overlay | Pavement Improvement | 2010-09-02 | 2011-04-01 | 2011-12-31 |  | 49377 | 0.500 | 1081038
6787 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WASHTENAW | ANN ARBOR | 07 | 1081044 | Overlay and Mill | Pavement Improvement | 2010-09-10 | 2011-04-01 | 2011-12-31 |  | 497457.02 | 14.623 | 1081044
6788 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082009 | Detroit is building a mile of paved pathway for cyclists, walkers, and joggers to promote alternative modes of transportation | Transportation Enhancements | 2009-10-26 | 2009-10-26 | 2012-11-15 |  | 1946988.29 | 0.824 | 1082009
6789 | MICHIGAN | Underway | C950 | Ferryboat | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082012 | This project is for the design of an off-shore wharf to receive ferryboat passengers on the Detroit river at the ferryboat terminal | Other | 2009-04-01 | 2010-01-31 | 2010-12-15 |  | 599205 |  | 1082012
6790 | MICHIGAN | Completed | C950 | Ferryboat | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082013 | This project is for the design of a terminal building expansion to receive ferryboat passengers on the Detroit River | Other | 2009-04-01 | 2010-01-19 | 2010-10-01 | 2011-08-15 | 210250 |  | 1082013
6791 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082014 | The City of Romulus will resurface 4.7 miles of Huron River Drive to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2009-11-18 | 2010-09-15 | 2010-09-15 | 627115.37 | 3.670 | 1082014
6792 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082015 | The City of Dearborn will resurface .7 miles of the Southfield Service Drive SBd to improve driving quality and increase service life | Pavement Improvement | 2009-11-25 | 2010-03-22 | 2010-10-31 | 2010-10-31 | 267073.51 | 0.464 | 1082015
6793 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082016 | The City of Grosse Point Farms will resurface .2 miles of Fisher Road to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2010-06-21 | 2010-10-30 | 2011-08-01 | 78822 | 0.213 | 1082016
6794 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082017 | The City of Detroit is resurfacing portions of Dickerson Van Dyke Antoinette. Fourteenth Trumbull Schaeffer Wyoming Southfield Service West Vernor Fullerton Hayes Dequindre and East Forest Roads to improve driving quality and increase service li | Pavement Improvement | 2009-11-18 | 2010-04-15 | 2010-11-02 | 2011-12-09 | 5103729 | 10.093 | 1082017
6795 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082018 | The City of Romulus will resurface .1 miles of Shook Road to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2009-11-18 | 2010-09-15 | 2010-10-01 | 590913.88 | 0.897 | 1082018
6796 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082019 | The City of Wayne will resurface .6 miles of Newburgh Road to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2009-11-18 | 2010-07-01 | 2010-07-01 | 512208.86 | 0.558 | 1082019
6797 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082020 | The City of Dearborn will resurface .2 miles of the Southfield Service Drive SBd to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2010-03-22 | 2010-10-31 | 2010-10-31 | 103168.14 | 0.180 | 1082020
6798 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082021 | The City of Dearborn will resurface .5 miles of Miller Road to improve driving quality and increase service life | Pavement Improvement | 2010-03-12 | 2010-03-22 | 2010-10-31 | 2010-10-31 | 402000 | 0.502 | 1082021
6799 | MICHIGAN | Completed | C950 | Ferryboat | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082022 | This project is for the construction of a terminal building expansion to receive ferryboat passengers on the Detroit River | Other | 2009-04-01 | 2010-01-19 | 2010-10-01 | 2011-08-15 | 1000000 | 0.129 | 1082022
6800 | MICHIGAN | Completed | C950 | Ferryboat | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082023 | This project is for the construction of an off-shore wharf to receive ferryboat passengers on the Detroit river at the ferryboat terminal | Other | 2009-04-01 | 2010-01-31 | 2010-12-15 | 2011-08-15 | 5305000 | 0.129 | 1082023
6801 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082024 | The City of Grosse Point Farms will resurface .5 miles of Jefferson Avenue to improve driving quality and increase service life | Pavement Improvement | 2009-11-18 | 2010-03-22 | 2010-10-30 | 2011-08-01 | 228134.02 | 0.456 | 1082024
6802 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082025 | The City of Wyandotte will resurface .2 miles of Oak Street in Wyandotte to improve the driving quality and increase the road service life | Pavement Improvement | 2009-11-25 | 2009-11-25 | 2010-10-15 | 2010-10-01 | 206918.13 | 0.225 | 1082025
6803 | MICHIGAN | Underway | C220 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082026 | The City of Detroit will beautify .4 miles of its downtown on Monroe and Brush Streets by building a streetscape | Transportation Enhancements | 2010-03-23 | 2010-04-05 | 2012-09-30 |  | 1489002.77 | 0.401 | 1082026
6804 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082035 | The City of Detroit will rehabilitate the Larned Street over Dequindre Cut bridge to make the bridge last longer | Bridge Replacement | 2010-01-06 | 2010-04-15 | 2011-05-02 | 2011-06-02 | 1200000 | 0.100 | 1082035
6805 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082036 | 2 Miles of Five Mile Road in the City of Detroit will be resurfaced to improve driving quality and increase service life | Pavement Improvement | 2010-01-12 | 2010-06-11 | 2010-11-30 | 2010-11-01 | 1300000 | 1.997 | 1082036
6806 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082037 | Wayne County in Canton Township will resurface the Warren Road and Lilley Road intersection to improve the driving quality and increase the road service life | Pavement Improvement | 2010-01-12 | 2010-05-24 | 2010-11-15 | 2010-11-08 | 881000 | 0.012 | 1082037
6807 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082038 | Wayne County will resurface 1.0 Miles of Van Born Road fromTelegraph Road to Monroe Road to improve driving quality and increase service life | Pavement Improvement | 2010-01-12 | 2010-04-28 | 2010-09-30 | 2010-09-28 | 1272440.41 | 1.001 | 1082038
6808 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082040 | Wayne County will replace the Goddard Extension over Merriman Road bridge to improve safety and increase moblility | Bridge Replacement | 2010-01-27 | 2010-01-27 | 2010-11-30 | 2011-06-30 | 1070230.04 | 0.020 | 1082040
6809 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082045 | MDOT will repave US-12 in Wayne County from 28th Street to Rosa Parks to improve the drive quality and make the road smoother | Pavement Improvement | 2010-04-05 | 2010-04-26 | 2011-12-31 | 2011-11-01 | 4561259.68 | 1.779 | 1082045
6810 | MICHIGAN | Completed | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082046 | MDOT will repave US-12 in Wayne County from Livernois to 28th Street to improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2012-12-31 | 2011-11-01 | 2909719.02 | 0.835 | 1082046
6811 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE |  | 13 | 1082048 | This pavement project in Wayne County on Judd from at Haggerty will improve the drive quality and make the road smoother | Pavement Improvement | 2010-02-08 | 2010-05-18 | 2010-11-30 | 2011-05-25 | 231808.67 | 0.518 | 1082048
6812 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082050 | This pavement project on Lake Shore Drive from Moross Road to Vernier Road will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-10 | 2010-08-02 | 2010-11-30 | 2010-11-19 | 2163906.49 | 4.163 | 1082050
6813 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082052 | This pavement project on Third Street from Vinewood to Northline will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-06-23 | 2013-03-15 | 2011-10-19 | 255410.75 | 0.451 | 1082052
6814 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082053 | This pavement project on Wayne Road Ramps At Michigan Avenue will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-05-11 | 2010-11-30 | 2010-11-08 | 173129.55 | 0.136 | 1082053
6815 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082054 | This pavement project on Edward N. Hines Drive from Ann Arbor Trail to Merriman Road will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-08-23 | 2010-11-30 | 2010-10-27 | 954872.94 | 3.339 | 1082054
6816 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082055 | This pavement project on Middlebelt Road from Cherry Hill Road to Warren in Garden City will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-08-02 | 2010-11-30 | 2011-11-04 | 2504684.12 | 0.968 | 1082055
6817 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082057 | This pavement project on Joy Road from Inkster to Beech Daly will make the road smoother and improve ride quality | Pavement Improvement | 2010-02-17 | 2010-07-19 | 2010-09-30 | 2010-09-17 | 1030039.34 | 0.911 | 1082057
6818 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082058 | This project in Detroit will upgrade the traffic signal at 29 locations on Jefferson Avenue to improve traffic flow and enhance safety. | Safety/Traffic Management | 2010-06-25 | 2010-08-02 | 2010-12-15 | 2011-10-11 | 1384609.62 | 2.188 | 1082058
6819 | MICHIGAN | Underway | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082129 | "Streetscape improvements 0.29 mi of pavement removal, cold milling, curb and gutter, storm sewer, hot mix asphalt paving, concrete sidewalks, concrete building vault reconstruction, street lighting | Pavement Improvement | 2010-06-21 | 2010-07-15 | 2012-09-30 |  | 1950000 | 0.289 | 1082129
6820 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082204 | Mid-block crossing | Safety/Traffic Management | 2011-06-20 | 2011-06-27 | 2011-09-30 | 2012-05-29 | 277357.53 | 0.978 | 1082204
6821 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082205 | Construct concrete median | Safety/Traffic Management | 2011-06-20 | 2011-06-27 | 2011-09-30 | 2012-05-29 | 87671 | 0.398 | 1082205
6822 | MICHIGAN | Completed | C230 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082206 | Constuct Concrete median | Safety/Traffic Management | 2011-06-20 | 2011-06-27 | 2011-09-30 | 2012-05-29 | 155121 | 0.496 | 1082206
6823 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | WAYNE | DETROIT,MI | 13 | 1082208 | Reconstruct | Pavement Improvement | 2010-09-20 | 2010-09-20 | 2013-12-31 |  | 5027105.37 | 6.467 | 1082208
6824 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WEXFORD |  | 02 | 1083006 | This pavement project in Wexford County on Various Roads at Various Locations will improve the drive quality and make the road smoother | Pavement Improvement | 2010-05-05 | 2010-08-16 | 2010-08-01 | 2010-09-22 | 364707.22 | 27.243 | 1083006
6825 | MICHIGAN | Completed | C200 | Highway Infrastructure Investment Grant | MICHIGAN | WEXFORD |  | 02 | 1083007 | This pavement project on Boon Road from Mitchell Street to the west will make the road smoother and improve ride quality | Pavement Improvement | 2010-06-15 | 2010-06-21 | 2010-07-01 | 2010-06-29 | 185948.44 | 0.933 | 1083007
6826 | MICHIGAN | Underway | C240 | Highway Infrastructure Investment Grant | MICHIGAN | STATEWIDE |  |  | 1084044 | At various locations in metropolitan Detroit this project will install protective fences and security for power towers to improve safety. | Safety/Traffic Management | 2009-05-11 | 2009-05-11 | 2013-01-31 |  | 2606740 | 0.000 | 1084044
6827 | MICHIGAN | Underway | C490 | OJT/SS | MICHIGAN | STATEWIDE |  |  | JT10001 | OBD/OBJ Program | Other | 2010-05-05 | 2010-05-05 | 2011-09-01 |  | 960584 | 0.004 | JT10001
6828 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | TODD, WADENA |  | Multiple | 09ES001 | Remove and replace pavement on State Highway 10 from Wadena to Staples. Add turn lanes, replace signs, pave shoulders, install rumble strips and lighting and improve pedestrian crossings. | Pavement Improvement | 2009-03-23 | 2009-05-01 | 2009-07-15 | 2009-07-16 | 7312124 | 21.757 | 09ES001
6829 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BIG STONE |  | 07 | 09ES002 | Placement of asphalt pavement on State Highway 75 form Graceville to Ortonville. | Pavement Improvement | 2009-04-23 | 2009-05-04 | 2009-07-31 | 2009-07-02 | 5143074 | 19.036 | 09ES002
6830 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MILLE LACS |  | 08 | 09ES003 | Remove and replace pavement on State Highway 169 from Princeton to Milaca. | Pavement Improvement | 2009-03-11 | 2009-05-01 | 2009-09-25 | 2009-10-15 | 4163703 | 13.696 | 09ES003
6831 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | RICE |  | 02 | 09ES004 | Replace pavement, add new median guardrail and improve water drainage pipes on northbound and southbound lanes of I-35 through Faribault. | Pavement Improvement | 2009-05-04 | 2009-05-11 | 2009-09-11 | 2009-09-22 | 4769068 | 4.875 | 09ES004
6832 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES006 | Construct guardrail improvements on State Highways throughout south central and western Minnesota to improve safety. | Safety/Traffic Management | 2009-04-16 | 2009-05-04 | 2009-08-04 | 2009-07-09 | 471228.93 | 78.092 | 09ES006
6833 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES007 | Replace guardrail on State Highways throughout southeast Minnesota. | Safety/Traffic Management | 2009-04-17 | 2009-05-11 | 2009-10-01 | 2009-11-10 | 1600638.66 | 217.325 | 09ES007
6834 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MOWER, OLMSTED |  | 01 | 09ES008 | Replace pavement, upgrade guardrail and improve water drainage pipes on eastbound I-90 from Stewartville to 8.6 miles west. | Pavement Improvement | 2009-04-17 | 2009-05-04 | 2009-07-05 | 2009-06-24 | 2108897 | 8.633 | 09ES008
6835 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | FREEBORN |  | 01 | 09ES009 | Replace pavement on I-90, upgrade guardrail and improve water drainage pipes from Albert Lea to Alden. | Pavement Improvement | 2009-03-23 | 2009-05-01 | 2009-09-30 | 2010-07-14 | 17117366 | 10.045 | 09ES009
6836 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WINONA |  | 01 | 09ES010 | Replace existing pavement, upgrade guardrail and improve water drainage pipes on westbound I-90 from east of State Highway 74 to west of State Highway 43. | Pavement Improvement | 2009-06-10 | 2009-06-22 | 2009-08-28 | 2009-08-24 | 4511492 | 14.099 | 09ES010
6837 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS, TODD |  | Multiple | 09ES011 | Install cable median barrier on I-94 from Sauk Centre to the Douglas/Todd County Line. | Safety/Traffic Management | 2009-03-23 | 2009-05-01 | 2009-09-20 | 2011-07-25 | 1493013.22 | 11.955 | 09ES011
6838 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES012 | Install hazardous curve signs at various locations on State Highways 1, 38, 65, and 217 in Itasca, Koochiching and St Louis Counties in Northeast Minnesota. | Safety/Traffic Management | 2009-04-23 | 2009-05-11 | 2009-06-21 | 2009-05-21 | 45740 | 48.909 | 09ES012
6839 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WINONA |  | 01 | 09ES013 | Replace existing pavement, upgrade guardrail and improve water drainage pipes on eastbound and westbound I-90 from Nadine to Dakota. | Pavement Improvement | 2009-04-27 | 2009-07-13 | 2009-10-23 | 2009-10-08 | 3016818 | 4.996 | 09ES013
6840 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SIBLEY |  | 07 | 09ES014 | Remove and replace pavement on State Highway 93 from Liqueur to Highway 169. | Pavement Improvement | 2009-04-15 | 2009-05-11 | 2009-08-07 | 2009-07-15 | 437312 | 0.830 | 09ES014
6841 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | KANDIYOHI |  | 07 | 09ES015 | Resurface Highway 23 from County Road 31 near New London to County Road 6 near Paynesville in Kandiyohi County. | Pavement Improvement | 2009-03-23 | 2009-05-01 | 2009-10-12 | 2009-10-09 | 1202117 | 6.652 | 09ES015
6842 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | AITKIN |  | 08 | 09ES016 | Resurfacing and safety improvements on State Highway 65 from State Highway 210 in McGregor to south of Big Sandy River Bridge. | Pavement Improvement | 2009-06-10 | 2009-06-17 | 2009-08-21 | 2009-09-03 | 5161594 | 11.395 | 09ES016
6843 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | LAKE |  | 08 | 09ES017 | Skid prevention in Silver Cliff and Lafayette Tunnels on Highway 61 north of Two Harbors. | Safety/Traffic Management | 2009-04-24 | 2009-04-27 | 2009-05-26 | 2009-05-02 | 78722 | 3.720 | 09ES017
6844 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | CARLTON |  | 08 | 09ES018 | Install plantings to create a living snow fence to prevent blowing snow from crossing two bridges on I-35 South of Carlton. | Transportation Enhancements | 2009-03-19 | 2009-06-01 | 2009-07-01 | 2009-09-21 | 77971 | 0.000 | 09ES018
6845 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 09ES019 | Reinforced concrete pavement on State Highway 169 from South of County Road 5 to west of County Road 67 near Chisholm where underground mining had occurred. | Pavement Improvement | 2009-06-04 | 2009-06-08 | 2010-06-25 | 2009-10-26 | 7799584 | 0.740 | 09ES019
6846 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BELTRAMI, CASS, STATEWIDE |  | Multiple | 09ES020 | Replace traffic signal at State Highway 197 and Ridgeway Avenue in Bemidji and at State Highway 2 and Grant Utley Avenue in Cass Lake. | Safety/Traffic Management | 2009-07-07 | 2009-08-10 | 2009-08-15 | 2009-09-29 | 317685 | 0.000 | 09ES020
6847 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | PENNINGTON, MARSHALL |  | 07 | 09ES021 | Resurface State Highway 1 from Warren to Thief River Falls. | Pavement Improvement | 2009-03-11 | 2009-05-01 | 2009-10-01 | 2010-02-28 | 6632798 | 26.896 | 09ES021
6848 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | BELTRAMI |  | 07 | 09ES022 | Lowering roadway by removal of bridges over abandoned railroad tracks along with additional safety improvements on State Highway 2 in Bemidji. | Pavement Improvement | 2009-07-23 | 2009-07-23 | 2009-09-30 | 2009-09-30 | 2251659 | 0.863 | 09ES022
6849 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS, WRIGHT |  | 06 | 09ES023 | Repair pavement on I-94 from Clearwater to Monticello. | Pavement Improvement | 2009-03-18 | 2009-05-01 | 2009-08-19 | 2009-08-08 | 6312466 | 47.868 | 09ES023
6850 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS |  | 06 | 09ES024 | Remove and replace pavement and paint bridge at County Road 143 and I-94. Remove and replace pavement and paint bridge at County road 186 and I-94. | Bridge Improvement | 2009-03-18 | 2009-05-01 | 2009-10-15 | 2009-09-24 | 1590108.46 | 48.949 | 09ES024
6851 | MINNESOTA | Completed | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | OTTER TAIL, GRANT |  | 07 | 09ES025 | Concrete resurfacing and rest area preservation on I-94 north of Fergus Falls to Grant County line. | Pavement Improvement | 2009-05-04 | 2009-05-11 | 2010-06-18 | 2010-06-10 | 8762711 | 20.797 | 09ES025
6852 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | MOWER |  | 01 | 09ES026 | Replace west bound exit ramp bridge on I-90 into Austin. | Bridge Replacement | 2009-05-08 | 2009-07-17 | 2010-09-01 | 2010-11-16 | 5075891 | 19.229 | 09ES026
6853 | MINNESOTA | Underway | C220,C200 | Highway Infrastructure Investment Grant | MINNESOTA | NICOLLET |  | 01 | 09ES029 | Replace utilities, reconstruct pavement and install signal and pedestrian crossing on State Highway 169 in St. Peter. | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2010-07-25 |  | 16422468 | 1.594 | 09ES029
6854 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | JACKSON |  | 01 | 09ES031 | Parking lot and sidewalk improvements at two rest areas on I-90 near Jackson. | Pavement Improvement | 2009-09-11 | 2009-09-21 | 2009-09-27 | 2009-10-10 | 344287.42 | 0.556 | 09ES031
6855 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHIPPEWA |  | 07 | 09ES033 | Resurface Highway 7 from Montevideo to Clara City in Chippewa County. | Pavement Improvement | 2009-03-18 | 2009-05-01 | 2009-08-28 | 2009-09-18 | 8897248 | 15.238 | 09ES033
6856 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES034 | Guardrail replacement at various locations in Southwest Minnesota | Safety/Traffic Management | 2009-06-30 | 2009-06-30 | 2010-06-30 | 2009-10-23 | 921855 | 33.993 | 09ES034
6857 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | REDWOOD |  | 07 | 09ES035 | Resurface Highway 68 from Milroy to Wabash in Redwood County. | Pavement Improvement | 2009-03-11 | 2009-08-01 | 2009-11-02 | 2009-10-20 | 2219889 | 15.322 | 09ES035
6858 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO, ISANTI |  | 08 | 09ES036 | Remove and replace pavement on State Highway 95 from east of Cambridge to the Isanti/Chisago County Line, including culvert replacement. | Pavement Improvement | 2009-03-11 | 2009-05-01 | 2009-08-07 | 2009-07-22 | 2771586 | 9.669 | 09ES036
6859 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | DULUTH-SUPERIOR (WI) | 08 | 09ES039 | Resurface State Highway 194 from northwest of Anderson Road to northwest of Masada Ave in the Duluth Heights neighborhood of Duluth. | Pavement Improvement | 2009-05-06 | 2009-05-26 | 2009-07-15 | 2009-07-02 | 1571611.56 | 1.857 | 09ES039
6860 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | DULUTH-SUPERIOR (WI) | 08 | 09ES040 | Roadway Resurfacing, curb & gutter removal and replacement, sidewalks, lighting and safety improvements on Highway 23 from East of 130th Street to North of County Road 3 in the Gary and Fond Du Lac neighborhoods in Duluth. | Pavement Improvement | 2009-06-05 | 2009-06-15 | 2009-09-30 | 2009-10-20 | 3469216 | 3.881 | 09ES040
6861 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 09ES041 | Pavement reconstruction and bridge rehabilitation on State Highway 53 from north of Highway 194 to north of Highway 33. | Pavement Improvement | 2009-06-05 | 2009-06-11 | 2009-10-30 | 2010-06-12 | 12582156 | 13.632 | 09ES041
6862 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES042 | Rest area sign replacement at five locations on Highway 2. | Safety/Traffic Management | 2009-06-01 | 2009-07-06 | 2009-08-28 | 2009-07-16 | 115134.4 | 0.000 | 09ES042
6863 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ITASCA |  | 08 | 09ES043 | Resurfacing on Highway 2 west of Deer River from County Road 18 to west of Highway 6, and on Highway 6 north of Deer River. | Pavement Improvement | 2009-04-16 | 2009-06-01 | 2009-10-30 | 2010-06-30 | 4031685 | 16.960 | 09ES043
6864 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MILLE LACS |  | 08 | 09ES046 | Remove and replace pavement on Highway 169 from Rum River rest area to south of Omani. | Pavement Improvement | 2009-04-08 | 2009-05-01 | 2009-07-24 | 2009-08-13 | 4788587 | 7.686 | 09ES046
6865 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MILLE LACS |  | 08 | 09ES047 | Replace bridge on Highway 23 over the Rum River in Milaca. | Bridge Replacement | 2009-04-20 | 2009-06-01 | 2009-11-13 | 2009-11-13 | 1692300 | 0.598 | 09ES047
6866 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ISANTI |  | 08 | 09ES048 | Replace bridge on Highway 95 over the Rum River west of Cambridge. | Bridge Replacement | 2009-04-20 | 2009-05-01 | 2009-11-13 | 2009-11-06 | 1410631 | 0.042 | 09ES048
6867 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | KANABEC |  | 08 | 09ES049 | Remove and replace bridge on State Highway 107 over the Snake River in Garston. | Bridge Replacement | 2009-04-20 | 2009-06-01 | 2009-11-13 | 2009-11-04 | 1322178 | 0.034 | 09ES049
6868 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES050 | Improve road safety and operations by coordinating 85 traffic signals in Big Lake, Brainerd, Baxter, Elk River, Monticello, St. Cloud and St. Michael. | Safety/Traffic Management | 2009-08-26 | 2009-08-26 | 2011-04-27 | 2011-04-27 | 413094 |  | 09ES050
6869 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DOUGLAS |  | 07 | 09ES052 | Install a traffic signal at I-94 and State Highway 27 in Alexandria. | Safety/Traffic Management | 2009-04-10 | 2009-07-01 | 2009-09-07 | 2009-08-21 | 227909 | 0.000 | 09ES052
6870 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | OTTER TAIL |  | 07 | 09ES053 | Install a traffic signal at State Highway 210 and Redwood Lane in Fergus Falls. | Safety/Traffic Management | 2009-08-19 | 2009-09-12 | 2009-10-28 | 2010-05-20 | 380084 | 0.000 | 09ES053
6871 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | WILKIN |  | 07 | 09ES054 | Install railroad gates and signals at State Highway 9 west of Nashua. | Safety/Traffic Management | 2009-06-10 | 2009-08-03 | 2010-06-15 | 2010-04-30 | 115403 | 0.000 | 09ES054
6872 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEVENS |  | 07 | 09ES055 | Install railroad gates, signals cantilevers at State Highway 28 southwest of Morris. | Safety/Traffic Management | 2009-05-06 | 2009-08-03 | 2010-05-12 | 2010-04-09 | 263338 | 0.001 | 09ES055
6873 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | FARIBAULT, FREEBORN |  | 01 | 09ES059 | Remove and replace pavement on I-90 between Alden and State Highway 22. | Pavement Improvement | 2009-06-10 | 2009-06-16 | 2009-09-30 | 2009-11-17 | 3800615.97 | 7.111 | 09ES059
6874 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | ROCK |  | 01 | 09ES060 | Build new state entrance sign at the South Dakota border on I-90 at the Beaver Creek rest area. | Transportation Enhancements | 2009-04-28 | 2009-08-01 | 2009-10-01 | 2009-11-10 | 66806 | 0.000 | 09ES060
6875 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MORRISON |  | 08 | 09ES061 | Plant living snow fence on Highway 371 in Crow Wing and Morrison Counties. | Transportation Enhancements | 2009-04-08 | 2009-05-01 | 2009-07-01 | 2009-06-18 | 119698 | 1.340 | 09ES061
6876 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | DULUTH-SUPERIOR (WI) | 08 | 09ES063 | Preserve the historic Aerial lift bridge over the Duluth Shipping Canal on Park Point, replacing lead based paint, structural steel and concrete elements. | Transportation Enhancements | 2009-08-19 | 2009-09-22 | 2011-03-20 | 2011-04-06 | 4900000 | 0.100 | 09ES063
6877 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | MINNEAPOLIS-ST. PAU, MN | 08 | 09ES064 | Resurfacing, curb and drainage repairs on the Rice Lake Road from Arrowhead Road to Masada Avenue in Duluth. | Pavement Improvement | 2009-07-21 | 2009-08-06 | 2009-09-18 | 2009-09-18 | 1178846 | 2.330 | 09ES064
6878 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | AITKIN |  | 08 | 09ES066 | Replace bridge on County Road 14 northeast of Highway 65, north of McGregor in Aitkin County. | Bridge Replacement | 2009-06-18 | 2009-07-01 | 2009-10-23 | 2010-07-07 | 1180574 | 0.100 | 09ES066
6879 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HUBBARD |  | 08 | 09ES067 | Replacement of bridge on County Road 9 over the Schoolcraft River, about 10 miles southwest of Bemidji in Hubbard County. | Bridge Replacement | 2009-07-01 | 2009-06-16 | 2009-10-16 | 2009-09-28 | 416683.9 | 0.100 | 09ES067
6880 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | KITTSON |  | 07 | 09ES068 | Replacement of bridge on County Road 1 over the North Branch of Two Rivers, north of Hillock in Kittson County. | Bridge Replacement | 2009-06-16 | 2009-06-22 | 2009-11-01 | 2009-11-04 | 798862.3 | 0.100 | 09ES068
6881 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BELTRAMI |  | 07 | 09ES069 | Rehabilitate surface, new curb and gutter, replace sewers and fix water lines on Irvine Ave from 3rd St. to State Highway 197 in Bemidji. | Pavement Improvement | 2009-06-30 | 2009-07-06 | 2009-11-01 | 2010-05-26 | 1453985.36 | 1.400 | 09ES069
6882 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MARSHALL |  | 07 | 09ES070 | West of Grille on County Road 7, replace bridge with a box culvert in Marshall County. | Bridge Replacement | 2009-06-03 | 2009-08-05 | 2009-08-07 | 2009-08-25 | 65352.5 | 0.050 | 09ES070
6883 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MARSHALL |  | 07 | 09ES071 | Replace timber bridge on County Road 15 over the Snake River with two culverts, West of Warren in Marshall County. | Bridge Replacement | 2009-07-17 | 2009-08-03 | 2009-09-04 | 2009-09-23 | 537484.97 | 0.100 | 09ES071
6884 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | MORRISON |  | 08 | 09ES072 | Reconstruction of Lindbergh Drive from State Highway 27 to the North city limits in Little Falls. | Pavement Improvement | 2009-08-21 | 2009-08-24 | 2009-11-15 | 2009-11-02 | 894236.24 | 0.997 | 09ES072
6885 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | ISANTI |  | 08 | 09ES073 | Replace bridge on County Road 6 over Stanch field Creek West of Grandee in Isanti County. | Bridge Replacement | 2009-08-17 | 2009-08-26 | 2009-12-25 | 2009-11-20 | 356317.47 | 0.100 | 09ES073
6886 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MORRISON |  | 08 | 09ES074 | Reconstruct County Road 203 beginning at Highway 10 and add additional asphalt surface on County Road 203 to County Road 2 in Morrison County, south of Motley. | Pavement Improvement | 2009-05-27 | 2009-06-15 | 2009-10-10 | 2009-09-02 | 626164 | 3.980 | 09ES074
6887 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BECKER |  | 07 | 09ES075 | Replace existing bridge with three culverts on County Highway 7, north of Lake Park in Becker County. | Bridge Replacement | 2009-08-31 | 2009-08-28 | 2009-09-09 | 2009-09-17 | 296085.97 | 0.100 | 09ES075
6888 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DOUGLAS |  | 07 | 09ES076 | Resurface County Road 7 from the north city limits of Brandon to the south city limits of Millersville in Douglas County. | Pavement Improvement | 2009-05-29 | 2009-05-29 | 2009-07-31 | 2009-06-19 | 813899 | 6.730 | 09ES076
6889 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SWIFT |  | 07 | 09ES077 | Replace bridge with two culverts on County Road 33 over Mud Creek, North East of Murdock in Swift County. | Bridge Replacement | 2009-07-01 | 2009-07-13 | 2009-08-15 | 2009-08-10 | 244039.21 | 0.040 | 09ES077
6890 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | TRAVERSE |  | 07 | 09ES078 | Place asphalt pavement and gravel shoulders on County Road 6 from the South Dakota State line to Highway 75, north of Wheaton in Traverse County. | Pavement Improvement | 2009-06-16 | 2009-06-18 | 2009-09-15 | 2009-08-09 | 1441828 | 1.390 | 09ES078
6891 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | STEELE |  | 01 | 09ES079 | Replace Cedar Avenue bridge over Maple Creek in Owatonna; also replace two railroad crossing signals. | Pavement Improvement | 2009-07-15 | 2009-08-04 | 2010-07-16 | 2009-11-25 | 1365638 | 0.100 | 09ES079
6892 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | GOODHUE |  | 02 | 09ES080 | Reconstruct County Highway 1 in Red Wing, including bridge replacement, new pavement, drainage pipe replacement, and new storm sewer in Goodhue County. | Pavement Improvement | 2009-06-09 | 2009-06-09 | 2009-11-30 | 2010-07-08 | 1784727 | 1.160 | 09ES080
6893 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | JACKSON |  | 01 | 09ES081 | Replace bridge on County Road 20 southwest of Okabena in Jackson County. | Bridge Replacement | 2009-07-16 | 2009-07-27 | 2009-10-02 | 2009-12-08 | 326354.34 | 0.100 | 09ES081
6894 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASECA |  | 01 | 09ES082 | Replace bridge on County Road 3 over the Le Sueur River south of Janesville in Waseca County. | Bridge Replacement | 2009-07-21 | 2009-07-23 | 2009-11-15 | 2009-11-05 | 609994 | 0.100 | 09ES082
6895 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASECA |  | 01 | 09ES083 | Replace bridge with culvert to carry Losco Creek under County Road 3, northeast of Janesville in Waseca County. | Bridge Replacement | 2009-07-21 | 2009-09-21 | 2009-10-30 | 2009-11-03 | 328827.47 | 0.110 | 09ES083
6896 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | NOBLES |  | 01 | 09ES084 | Resurface County Road 1 from Brewster to Kin brae in Nobles County. | Pavement Improvement | 2009-06-04 | 2009-08-24 | 2009-09-21 | 2009-09-18 | 1521460.06 | 8.310 | 09ES084
6897 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | BLUE EARTH |  | 01 | 09ES085 | Construct a new bridge on a new roadway on County Road 12 over the DM&E RR in east Mankato in Blue Earth County | New Bridge Construction | 2009-08-19 | 2009-08-24 | 2010-09-24 | 2010-11-11 | 3073030.26 | 0.570 | 09ES085
6898 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHIPPEWA |  | 07 | 09ES086 | Replace bridge on County Road 32, southeast of the City of Milan in Chippewa County. | Bridge Replacement | 2009-06-08 | 2009-07-27 | 2009-10-23 | 2009-11-05 | 476489 | 0.100 | 09ES086
6899 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | LYON |  | 07 | 09ES087 | Replace bridge on County Road 3 over the south branch of the Yellow Medicine River, south of Minnesota in Lyon County. | Bridge Replacement | 2009-06-19 | 2009-06-24 | 2009-11-15 | 2009-09-01 | 305095.31 | 0.050 | 09ES087
6900 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | MCLEOD |  | 07 | 09ES088 | Replace timber bridge on County Road 7 over High Island County Road south of Stewart in McLeod County. | Bridge Replacement | 2009-06-01 | 2009-06-15 | 2009-08-24 | 2009-09-10 | 317742.12 | 0.100 | 09ES088
6901 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | LINCOLN |  | 07 | 09ES089 | Resurface County Road 6 from South County Line to Highway 14, 3 miles south of Tyler. Resurface County Road 9 from County Road 1 to County Road 2, West of Verdi. Resurface County Road 11 from County Road 8 to east county line in Lincoln County. | Pavement Improvement | 2009-05-21 | 2009-05-19 | 2009-06-16 | 2009-06-05 | 792677.8 | 4.010 | 09ES089
6902 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RENVILLE |  | 07 | 09ES090 | Replace bridge on County Road 9 over Chetamba Creek in Renville County. | Bridge Replacement | 2009-06-24 | 2009-06-24 | 2009-09-30 | 2009-10-02 | 332116.25 | 0.100 | 09ES090
6903 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | YELLOW MEDICINE |  | 07 | 09ES091 | Replace bridge on County Road 3 over Lac Qui Parle River in Yellow Medicine County. | Bridge Replacement | 2009-06-10 | 2009-08-10 | 2009-08-21 | 2009-11-10 | 209872 | 0.100 | 09ES091
6904 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ITASCA |  | 08 | 09ES092 | Complete reconstruction, including utilities on 7th Avenue Southeast from 17th Street Southeast to 33rd Street Southeast in Grand Rapids. | Pavement Improvement | 2009-06-03 | 2009-06-04 | 2010-07-15 | 2009-10-15 | 1498036.33 | 1.535 | 09ES092
6905 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BELTRAMI |  | 07 | 09ES093 | Resurface County Road 23 from County Highway 29 to County Highway 32 in Beltrami County. | Pavement Improvement | 2009-06-18 | 2009-06-22 | 2009-07-10 | 2009-07-10 | 776124.27 | 4.820 | 09ES093
6906 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CLEARWATER |  | 07 | 09ES094 | Resurfacing County Road 5 from Clearbrook to the Red Lake Reservation line in Clearwater County. | Pavement Improvement | 2009-06-19 | 2009-06-22 | 2009-07-09 | 2009-07-09 | 1240119.69 | 8.830 | 09ES094
6907 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | TODD |  | 07 | 09ES095 | Resurfacing on County Road 2 from Highway 28 to County Road 11 northeast of Sauk Center in Todd County. | Pavement Improvement | 2009-06-18 | 2009-06-25 | 2009-09-11 | 2009-08-21 | 866884.64 | 10.600 | 09ES095
6908 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SHERBURNE |  | 06 | 09ES096 | Replace bridge on County Road 5 over St. Francis River south of Sherburne County Road 3. | Bridge Replacement | 2009-06-04 | 2009-06-04 | 2009-10-02 | 2009-09-16 | 469472 | 0.110 | 09ES096
6909 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | WRIGHT |  | 06 | 09ES097 | Reconstruction and widening including curb and gutter and recreational trail on Jamison Ave from County Road 119 to County Road 18 in St. Michael. | Pavement Improvement | 2009-06-22 | 2009-06-23 | 2009-10-16 | 2009-11-05 | 2136105.37 | 1.451 | 09ES097
6910 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | OTTER TAIL |  | 07 | 09ES098 | Resurface and add shoulders to County Road 1 from Sophus Anderson Rd to County Road 10 east of Fergus Falls in Ottertail County. | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2009-09-30 | 2009-09-02 | 1206813.06 | 5.080 | 09ES098
6911 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | OTTER TAIL |  | 07 | 09ES099 | Replace bridge over Otter Tail River on Concord Street in Fergus Falls. | Bridge Replacement | 2009-06-30 | 2009-07-06 | 2010-06-26 | 2010-05-24 | 776855 | 0.100 | 09ES099
6912 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | YELLOW MEDICINE |  | 07 | 09ES100 | Resurface County Road 8 from Highway 67 to County Road 5, north of Clarkfield in Yellow Medicine County. | Pavement Improvement | 2009-06-03 | 2009-07-08 | 2009-09-18 | 2009-08-27 | 907551.7 | 3.990 | 09ES100
6913 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | KANDIYOHI, RENVILLE |  | 07 | 09ES101 | Resurface County Road 2, south of County Road 77 to Highway 7 in Renville and Kandiyohi Counties. | Pavement Improvement | 2009-05-28 | 2009-06-30 | 2010-08-01 | 2009-11-12 | 2254661.99 | 1.920 | 09ES101
6914 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 09ES103 | Resurfacing on St. Louis County Road 4 from Arrowhead Road to Martin Road in Duluth. | Pavement Improvement | 2009-06-26 | 2009-07-29 | 2009-10-09 | 2009-09-23 | 1838992.37 | 3.420 | 09ES103
6915 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS |  | 06 | 09ES104 | Reconstruction and widening of Pinecone road from County Road 120 to County Road 134 in St. Cloud, including roundabouts. | Pavement Improvement | 2009-08-17 | 2009-08-20 | 2010-05-30 | 2009-11-12 | 1469770.03 | 0.600 | 09ES104
6916 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STEARNS |  | 06 | 09ES105 | Extending 28th Ave from State Highway 23 to County Road 137 in the City of Waite Park. | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2010-07-16 | 2010-09-03 | 2433666 | 1.300 | 09ES105
6917 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | OLMSTED | ROCHESTER | 01 | 09ES106 | Replace 4th Street bridge over Bear Creek in Rochester. | Bridge Replacement | 2009-08-26 | 2009-09-01 | 2010-10-15 | 2010-11-15 | 2742179.39 | 0.100 | 09ES106
6918 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES107 | Replace deteriorated landscaping at the state entry signs at the US/Canada border on Highway 61 near Grand Portage, and the Minnesota/Wisconsin border on I-535 and Highway 2 in Duluth. | Transportation Enhancements | 2009-04-16 | 2009-06-01 | 2011-11-15 | 2010-03-23 | 132579 | 0.000 | 09ES107
6919 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | FREEBORN |  | 01 | 09ES122 | Replacing landscaping around Entering and Leaving Minnesota Signs on I-35 at the Iowa Border near Albert Lea. | Transportation Enhancements | 2009-05-13 | 2009-08-01 | 2009-10-01 | 2010-07-21 | 60642 | 0.000 | 09ES122
6920 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 08 | 09ES124 | Plant living snow fence on I-35 at County Road 17 south of North Branch. | Transportation Enhancements | 2009-04-24 | 2009-04-24 | 2010-11-01 | 2010-11-01 | 79895 | 0.000 | 09ES124
6921 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 08 | 09ES125 | Remove and replace pavement on I-35 north of North Branch; repair drainage and replace lighting and pavement at the Goose Creek Rest Area. | Pavement Improvement | 2009-07-08 | 2009-07-09 | 2009-10-30 | 2009-11-11 | 9096643 | 7.113 | 09ES125
6922 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 09ES126 | Reconstruct State Highway 5 from south of State Highway 36 to Manning Avenue. Drainage improvements were made through this section and west to I-694. | Pavement Improvement | 2009-04-24 | 2009-08-04 | 2009-10-03 | 2010-05-30 | 2066476 | 7.414 | 09ES126
6923 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA, HENNEPIN | MINNEAPOLIS-ST. PAU, MN | Multiple | 09ES127 | Replace lighting on Highway 100 from 50th in Edina to Excelsior Boulevard in St. Louis Park. Replace lighting on Highway 100 from I-494 to Vernon Avenue in Edina. Replace lighting on I-35W from Cliff Road in Eagan to 106th Street in Burnsville. | Safety/Traffic Management | 2009-04-24 | 2009-06-01 | 2010-05-20 | 2009-11-02 | 2296429 | 5.137 | 09ES127
6924 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA, STATEWIDE | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES128 | Remove and replace 2 traffic signals on State Highway 13 in Burnsville. | Safety/Traffic Management | 2009-05-22 | 2009-08-01 | 2009-11-06 | 2009-11-06 | 493780 | 0.262 | 09ES128
6925 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 09ES130 | Rebuild the cable median barrier on I-94 from I-494 in Maple Grove to the Crow River. | Safety/Traffic Management | 2009-04-24 | 2009-06-01 | 2009-09-07 | 2009-09-09 | 1239274 | 10.873 | 09ES130
6926 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES131 | Remove and replace pavement at the north junction of I-35E and I-35W, including extending a merge lane on I-35. | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-10-30 | 2009-10-30 | 5793909 | 25.670 | 09ES131
6927 | MINNESOTA | Underway | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES132 | Plant landscaping on I-494 from State Highway 5 to I-394. | Other | 2009-05-28 | 2009-08-01 | 2012-10-30 |  | 573664 | 7.522 | 09ES132
6928 | MINNESOTA | Completed | C250,C240 | Highway Infrastructure Investment Grant | MINNESOTA | POLK |  | 07 | 09ES133 | Replace the bridge over the Red River and approaches on County Road 9 in Polk County. | Bridge Replacement | 2009-09-11 | 2009-09-02 | 2010-10-01 | 2011-10-05 | 6763057 | 0.010 | 09ES133
6929 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | CASS |  | 08 | 09ES134 | Resurface Sucker Bay Road in Cass County and install Rail Road crossing signal and gates at BNSF Rail Road. | Safety/Traffic Management | 2010-01-15 | 2010-01-20 | 2010-09-30 | 2010-10-15 | 152352.63 |  | 09ES134
6930 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | CLAY | FARGO-MOORHEAD (ND) | 07 | 09ES135 | Restore landscaping at state entry sign in Moorhead. | Transportation Enhancements | 2009-06-04 | 2009-08-01 | 2009-10-19 | 2009-11-05 | 65879 | 0.300 | 09ES135
6931 | MINNESOTA | Underway | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES136 | Construct State Highway 610 from County Road 81 to State Highway 169 in Maple Grove and Brooklyn Park. | Pavement Widening | 2009-05-14 | 2009-08-01 | 2012-06-01 |  | 28871118.09 | 3.226 | 09ES136
6932 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES137 | Remove and replace traffic signals and lighting on state highways and interstate throughout the Twin Cities region. | Safety/Traffic Management | 2009-05-27 | 2009-07-01 | 2009-12-28 | 2009-12-03 | 1148823.09 | 25.444 | 09ES137
6933 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES138 | Add a traffic lane to the ramp from westbound I-494 to westbound US 212. | Pavement Improvement | 2009-07-23 | 2009-08-17 | 2009-09-23 | 2009-11-08 | 1275463 | 0.758 | 09ES138
6934 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES139 | Separate existing westbound and eastbound I-494 interchange ramps as they merge onto I-35E southbound. | Safety/Traffic Management | 2009-07-23 | 2009-08-07 | 2009-09-21 | 2009-09-12 | 810113.69 | 0.386 | 09ES139
6935 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES140 | Install Fiber Optic cable throughout the Twin Cities region on state highways and interstate. | Safety/Traffic Management | 2009-05-27 | 2009-08-01 | 2010-10-31 | 2010-10-31 | 1246688 |  | 09ES140
6936 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES141 | Install pavement markings throughout the Twin Cities region on state highways and interstate. | Pavement Improvement | 2009-05-27 | 2009-08-01 | 2009-11-15 | 2010-07-30 | 998124.43 | 14.581 | 09ES141
6937 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 09ES143 | Remove and replace lighting on US 169 from I-494 to I-94. | Safety/Traffic Management | 2009-05-27 | 2009-08-01 | 2010-06-19 | 2010-05-01 | 4364758.17 | 15.652 | 09ES143
6938 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES145 | In Rosemount and Inver Grove Heights, resurface road and repair four bridges on Highway 52 from County Road 42 to Highway 55 in Dakota County. | Pavement Improvement | 2009-10-06 | 2009-10-13 | 2010-06-04 | 2010-05-01 | 3600475.62 | 3.613 | 09ES145
6939 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 09ES146 | Remove and replace pavement on State Highway 95 from Stillwater 16 to State Highway 97. | Pavement Improvement | 2009-06-22 | 2009-09-08 | 2010-06-04 | 2010-06-01 | 4971163 | 15.320 | 09ES146
6940 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES147 | Installation of changeable message signs in the Minneapolis-St. Paul Metro area. | Safety/Traffic Management | 2009-09-03 | 2009-09-09 | 2010-05-13 | 2010-05-13 | 1470917 | 0.000 | 09ES147
6941 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 09ES148 | Storm tunnel restoration on I-35E at Shepard Road in St. Paul. | Pavement Improvement | 2009-10-21 | 2009-10-21 | 2010-05-31 | 2010-05-12 | 1592665 | 0.475 | 09ES148
6942 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA, RAMSEY | MINNEAPOLIS-ST. PAU, MN | 06 | 09ES149 | Resurfacing of US 10 from State Highway 65 in Blaine to North of junction with I-35W in Shoreview. | Pavement Improvement | 2010-03-04 | 2010-04-19 | 2010-09-03 | 2010-09-17 | 8684334 | 2.975 | 09ES149
6943 | MINNESOTA | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES155 | Landscaping along I-94 from I-494 in Maple Grove to Brooklyn Blvd in Brooklyn Park, Hennepin County. | Transportation Enhancements | 2009-08-03 | 2009-08-03 | 2012-10-31 |  | 210494 | 5.510 | 09ES155
6944 | MINNESOTA | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES156 | Landscape Highway 212 interchange at State Highway 101 and at Carver County Road 17 (Powers Blvd) in Chanhassen in Carver County. | Transportation Enhancements | 2009-08-03 | 2009-08-03 | 2012-10-30 |  | 236776 | 0.000 | 09ES156
6945 | MINNESOTA | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES157 | Landscape Highway 212 interchange at Carver County Road 10 (Engler Blvd) and Carver County Road 11 in Chaska, Carver County. | Transportation Enhancements | 2009-08-03 | 2009-08-03 | 2012-10-30 |  | 358078 | 0.000 | 09ES157
6946 | MINNESOTA | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES158 | Landscape Highway 212 at Hennepin County Road 4 and Dell Road in Eden Prairie. | Transportation Enhancements | 2009-08-03 | 2009-08-03 | 2012-10-30 |  | 201631 | 0.000 | 09ES158
6947 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO | MINNEAPOLIS-ST. PAU, MN | 08 | 09ES159 | Reconstruct interchange of Highway 95 and I-35 in North Branch, Chisago County. | Pavement Improvement | 2009-11-16 | 2009-11-19 | 2010-11-20 | 2010-11-13 | 3765286 | 1.045 | 09ES159
6948 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES161 | In Rosemount and Inver Grove Heights of Dakota County, resurface, revise signals and improve accessibility on 6 miles of Highway 3 from County Road 42 to Highway 149 in northbound and southbound lanes. | Pavement Improvement | 2010-03-03 | 2010-05-10 | 2010-06-30 | 2010-11-04 | 2777456.05 | 6.341 | 09ES161
6949 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES162 | Replace concrete, replace lighting, and add acceleration lane to I-94 from the Crow River in Rogers to I-494 in Maple Grove. | Pavement Improvement | 2010-02-17 | 2010-05-03 | 2010-09-24 | 2010-11-11 | 2636508 | 4.245 | 09ES162
6950 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES163 | Resurface shoulders on Highway 252 from I-694 to Highway 610 in Brooklyn Park, to accommodate buses. Project also replaced curb and gutter and updated pedestrian facilities. | Safety/Traffic Management | 2009-10-14 | 2010-02-01 | 2010-10-01 | 2010-10-15 | 2848375 | 4.456 | 09ES163
6951 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES165 | Replace lighting on Highway 62 from State Highway 212 in Eden Prairie to Gleason Road in Edina. | Safety/Traffic Management | 2009-10-19 | 2010-02-01 | 2010-05-28 | 2010-12-09 | 827898 | 1.212 | 09ES165
6952 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE |  |  | 09ES166 | Guardrail upgrades at various locations around the east Minneapolis-St. Paul Metro area. | Safety/Traffic Management | 2009-09-12 | 2010-05-01 | 2010-07-17 | 2010-07-12 | 288884 |  | 09ES166
6953 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 09ES167 | Guardrail upgrades at various locations around the west Minneapolis-St. Paul Metro area. | Safety/Traffic Management | 2009-08-24 | 2010-04-01 | 2010-07-03 | 2010-05-11 | 232723 |  | 09ES167
6954 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT |  | 02 | 09ES168 | Preserve historic bridge in downtown Shakopee as non-motorized Minnesota River crossing in Scott County. | Transportation Enhancements | 2009-10-26 | 2010-02-01 | 2010-09-17 | 2011-08-01 | 5557690 |  | 09ES168
6955 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA | MINNEAPOLIS-ST. PAU, MN | 06 | 09ES169 | Reconstruct interchange at I-35 and County Road 14. | Pavement Improvement | 2009-12-04 | 2010-01-26 | 2011-06-30 | 2011-06-30 | 6825000 | 1.041 | 09ES169
6956 | MINNESOTA | Completed | C240,C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 09ES171 | Construct interchange at Highway 7 & Wooddale Avenue including pedestrian walkway and trail in St. Louis Park. | New Bridge Construction | 2009-09-25 | 2009-09-29 | 2010-11-01 | 2010-11-10 | 3465000 | 0.129 | 09ES171
6957 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | CLAY | FARGO-MOORHEAD (ND) | 07 | 09ES173 | Reconstruct 20th Street between 12th Avenue South and 24th Avenue South replacing pavement, curb and gutter and storm sewer. | Other | 2009-08-26 | 2009-08-28 | 2009-11-13 | 2010-07-02 | 1098380 | 0.420 | 09ES173
6958 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | CLAY | FARGO-MOORHEAD (ND) | 07 | 09ES174 | Repair and repaint bridge over the Red River on Center Avenue in Moorhead. | Bridge Improvement | 2009-09-21 | 2009-10-05 | 2010-07-01 | 2010-08-18 | 909806 | 0.100 | 09ES174
6959 | MINNESOTA | Completed | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 09ES175 | Construct asphalt pavement on the Mesabi Trail system from the Giants Ridge recreation area near Biwabik to State Highway 135. Including pedestrian bridge over Narrows between Sabin Lake and Wynne. | Transportation Enhancements | 2009-12-22 | 2010-04-26 | 2010-09-15 | 2012-08-06 | 1407835 |  | 09ES175
6960 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 09ES176 | Realign and widen County Road 10 from County Road 101 to West of Peony Lane in Maple Grove. | Pavement Widening | 2009-09-02 | 2009-09-03 | 2010-11-15 | 2011-07-01 | 3064000 | 0.610 | 09ES176
6961 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 09ES179 | Constructing a paved surface on a new alignment for County Road 21 from County Road 42 in Prior Lake to County Road 16 in Shakopee in Scott County. | Pavement Improvement | 2009-11-12 | 2009-11-16 | 2011-11-11 | 2011-09-20 | 7324000 | 4.761 | 09ES179
6962 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES001 | Construct pedestrian and bike trail connections to Anderson Memorial Trail in Arden Hills. | Transportation Enhancements | 2010-03-24 | 2010-03-29 | 2010-06-25 | 2010-09-03 | 288326 |  | 10ES001
6963 | MINNESOTA | Completed | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES002 | Provide a wider pedestrian path from the Cedar Lake Bike Trail system to the new downtown Minneapolis ballpark. | Transportation Enhancements | 2009-11-05 | 2009-11-06 | 2010-05-31 | 2009-11-30 | 695067 |  | 10ES002
6964 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER |  | 02 | 10ES005 | Construct a pedestrian and bike Dakota Rail Trail from East County Line to City of Mayer in Carver County. | Transportation Enhancements | 2010-03-26 | 2010-04-06 | 2010-12-31 | 2011-08-10 | 550680 |  | 10ES005
6965 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES006 | Construct Sam Morgan Trail, a pedestrian and bike trail, from I-35E to State Highway 5 in St. Paul. | Transportation Enhancements | 2010-05-26 | 2010-06-01 | 2010-08-30 | 2010-09-10 | 448800 |  | 10ES006
6966 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN |  | 05 | 10ES007 | Improve the Bryant Avenue Pedestrian Bridge over Minnehaha Creek in Minneapolis. | Transportation Enhancements | 2010-05-05 | 2010-05-05 | 2010-09-02 | 2010-12-02 | 382000 |  | 10ES007
6967 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY, WASHINGTON | MINNEAPOLIS-ST. PAU, MN | Multiple | 10ES009 | Provide bridge for Gateway State Trail users over Highway 120 in the Cities of North St. Paul and Oakdale. | Transportation Enhancements | 2010-03-11 | 2010-05-17 | 2010-08-22 | 2010-12-10 | 1257903 |  | 10ES009
6968 | MINNESOTA | Completed | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES010 | Construct a pedestrian and bike trail along County Road 10 from Brooklyn Blvd to State Highway 100 in Brooklyn Center. | Transportation Enhancements | 2010-03-17 | 2010-04-19 | 2010-10-15 | 2010-08-15 | 2000000 |  | 10ES010
6969 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES011 | Construct turn lanes on County Road 30 at the Compost Site Access in Mayer. | Safety/Traffic Management | 2010-05-07 | 2010-05-10 | 2010-07-31 | 2010-06-04 | 96000 | 0.200 | 10ES011
6970 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES012 | Install a signal at intersection of State Highway 41 and 2nd Street and concrete median at 1st, 3rd, and 5th streets in Chaska. | Safety/Traffic Management | 2010-02-25 | 2010-05-24 | 2010-09-03 | 2010-10-22 | 485272 | 0.215 | 10ES012
6971 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON |  | 06 | 10ES015 | Construct bridge and retaining walls for County Road 83 on the overpass of I-35 in Washington County. | Pavement Improvement | 2010-04-06 | 2010-04-12 | 2011-06-01 | 2010-11-22 | 5000000 | 0.200 | 10ES015
6972 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA |  | 05 | 10ES016 | Reconstruct pedestrian bridge crossing State Highway 65 and approaches in the vicinity of 49th Avenue in Columbia Heights. | Bridge Replacement | 2010-04-12 | 2010-04-12 | 2011-06-15 | 2010-10-22 | 1925678 |  | 10ES016
6973 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES017 | Construct intersection control at Mendota Heights Road at Vistation Drive and at Lake Drive in Mendota Heights. | Safety/Traffic Management | 2010-02-16 | 2010-06-14 | 2011-07-01 | 2010-08-20 | 310000 | 0.690 | 10ES017
6974 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES018 | Resurface and stripe for bike lanes on 61st Avenue from Main Street to Central Avenue in Fridley. | Pavement Improvement | 2010-04-20 | 2010-05-03 | 2010-06-18 | 2010-07-30 | 262500 | 1.270 | 10ES018
6975 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES019 | Resurface four sections of county roads in Carver County: County Road 10, County Road 15 and County Road 17. | Pavement Improvement | 2009-09-10 | 2009-11-01 | 2009-11-01 | 2009-11-16 | 856367.32 | 0.330 | 10ES019
6976 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | CARVER | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES020 | Reconstruct State Highway 25 from White Street to State Street in Watertown. | Pavement Improvement | 2010-03-23 | 2010-05-10 | 2010-07-31 | 2010-07-09 | 704000 | 0.230 | 10ES020
6977 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES021 | Construct overpass from I-94 westbound to Highway 101 northbound over South Diamond Lake Road in Rogers. | New Bridge Construction | 2010-03-11 | 2010-04-06 | 2010-10-29 | 2010-11-16 | 3780000 | 0.348 | 10ES021
6978 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 10ES023 | Minor road improvements including curb repair, utility repair, and resurfacing at various locations of Public Road 101 in Woodbury. | Pavement Improvement | 2010-02-02 | 2010-05-20 | 2010-09-30 | 2010-09-13 | 1250250 | 2.660 | 10ES023
6979 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES024 | Resurface 140th Street West from 134th Street to Guild Avenue and Garden View Drive from 140th Street to Walnut Street. This project will also include spot repair of deteriorated storm sewer, sanitary sewer and water lines. | Pavement Improvement | 2010-06-11 | 2010-06-14 | 2010-09-16 | 2010-08-27 | 561000 | 1.201 | 10ES024
6980 | MINNESOTA | Completed | C240,C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES025 | Rehabilitate bridge on 42nd Ave. North/37th Avenue northeast from Lyndale Avenue north to St. Anthony Parkway in Minneapolis. | Bridge Improvement | 2010-03-08 | 2010-04-05 | 2011-08-31 | 2010-08-24 | 9539619 | 0.331 | 10ES025
6981 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES026 | Upgrade 56 existing signal systems in Coon Rapids, including new lenses, pedestrian lights with count down timers and revised pedestrian signs. | Safety/Traffic Management | 2009-10-07 | 2009-11-23 | 2010-03-01 | 2010-04-26 | 180000 |  | 10ES026
6982 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES027 | Reconstruct County Road 73 from County Road 42 to Bonaire Path. | Pavement Improvement | 2010-04-02 | 2010-04-07 | 2010-10-07 | 2010-08-28 | 2146506.35 | 1.000 | 10ES027
6983 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES028 | Campus Drive/26th Avenue from County Road 61 to Sycamore Lane in Plymouth: Resurface from County Road 61 to Teakwood Lane and reconstruct from Teakwood lane to Sycamore Lane. | Pavement Improvement | 2010-02-23 | 2010-05-07 | 2010-06-10 | 2010-06-04 | 346560 | 0.395 | 10ES028
6984 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES029 | Resurface and stripe Hadley Avenue from Hudson Boulevard North to 11th Street North in Oakdale. | Pavement Improvement | 2010-02-26 | 2010-04-26 | 2010-05-06 | 2010-05-10 | 273766.1 | 1.118 | 10ES029
6985 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES030 | Resurface Holyoke/Highview Avenue from Heritage Drive to Dodd Boulevard in Lakeville. | Pavement Improvement | 2009-10-06 | 2009-10-07 | 2010-08-01 | 2009-11-20 | 812121.7 | 1.252 | 10ES030
6986 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES031 | Street lighting replacement, reconstruction of sidewalk on Shoreline Boulevard and Commerce Boulevard from east city limits to west city limits in Mound. | Safety/Traffic Management | 2010-05-25 | 2010-06-01 | 2010-10-15 | 2010-11-01 | 630000 | 2.040 | 10ES031
6987 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | ANOKA | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES032 | Resurfacing of Terrance Road from County Road 8 to Sanburnol Drive and Able Street from County Road 8 to County Road 10. | Pavement Improvement | 2010-04-15 | 2010-04-26 | 2010-10-08 | 2010-10-25 | 1468480 | 1.160 | 10ES032
6988 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES033 | Construct right lane and bypass lane on State Highway 244 at Old Wildwood Road in Mahtomedi. | Safety/Traffic Management | 2010-02-16 | 2010-05-03 | 2010-07-30 | 2010-06-10 | 156000 | 0.051 | 10ES033
6989 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 10ES034 | Resurfacing and storm sewer work on Washington Avenue from State Highway 36 to Orleans in Stillwater. | Pavement Improvement | 2010-02-16 | 2010-05-19 | 2010-06-30 | 2010-06-17 | 265968.28 | 0.529 | 10ES034
6990 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES035 | Reconstruct the pavement, improve and construct additional storm sewer, replace failing water main, complete spot repair of sanitary sewer, replace portions of curb and gutter and widen portions of existing sidewalk on Winnetka Avenue from Bass Lake Road | Pavement Improvement | 2009-10-28 | 2010-04-12 | 2011-07-01 | 2010-10-08 | 778723 | 0.490 | 10ES035
6991 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES036 | Construct a pedestrian bridge over Highway 169 and trail connection from Appolossa Ave to Vierling Drive on Fuller Street in Shakopee. | Transportation Enhancements | 2010-01-22 | 2010-05-26 | 2010-07-01 | 2010-08-20 | 700000 |  | 10ES036
6992 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES037 | Construct two trail bridges over State Highway 7 and County Road 92 and connection of paved regional trail between bridges and the Carver County/Hennepin County Line. | Transportation Enhancements | 2010-03-03 | 2010-03-03 | 2010-08-16 | 2011-07-29 | 2703661.6 |  | 10ES037
6993 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA |  | 02 | 10ES038 | Reconstruct Dakota County Road 96 from West of 11th Avenue to State Highway 3, with paved shoulders and right turn lanes at intersections. | Pavement Improvement | 2009-10-19 | 2009-10-23 | 2010-08-01 | 2010-07-02 | 1677104.31 | 0.490 | 10ES038
6994 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES039 | Construction of South Frontage Road from County Road 5 to County Road 3 and South Street from US 169 to O'Brien Parkway in Belle Plaine. | Pavement Improvement | 2010-03-11 | 2010-03-18 | 2011-07-11 | 2010-09-03 | 1555922.03 | 0.200 | 10ES039
6995 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES040 | Install new traffic control signal system at the intersection of County Road 42 and McKenna Road in Prior Lake. | Safety/Traffic Management | 2009-12-14 | 2010-04-09 | 2010-07-01 | 2010-05-05 | 154486.51 | 0.020 | 10ES040
6996 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 10ES041 | Roadway resurfacing and drainage improvements on US 2 west of Duluth. | Pavement Improvement | 2009-09-29 | 2009-10-07 | 2010-07-15 | 2010-07-17 | 3677037 | 14.556 | 10ES041
6997 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | AITKIN |  | 08 | 10ES042 | Replace a deficient and deteriorated bridge located north of Aitkin on County Highway 1 in Aitkin County. | Bridge Replacement | 2009-11-18 | 2010-04-05 | 2010-10-11 | 2010-08-12 | 861171.89 | 0.240 | 10ES042
6998 | MINNESOTA | Completed | C250,C240 | Highway Infrastructure Investment Grant | MINNESOTA | SIBLEY |  | 07 | 10ES043 | Upgrade railroad from Green Isle to Gaylord. | Safety/Traffic Management | 2010-03-03 | 2010-05-11 | 2010-07-31 | 2010-09-23 | 2675000 |  | 10ES043
6999 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | PINE |  | 08 | 10ES044 | Replace failed piers on closed St Croix Valley railroad bridge over Snake river in Pine County. | Bridge Improvement | 2009-10-05 | 2009-10-05 | 2010-01-31 | 2010-06-16 | 1030026 |  | 10ES044
7000 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES045 | Reconstruct County Road D from Flandrau Street to White Bear Avenue in Ramsey County including, dedicated turn lanes, and traffic signals. | Pavement Improvement | 2009-12-02 | 2010-04-19 | 2010-10-15 | 2010-09-29 | 2449882 | 0.560 | 10ES045
7001 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | MARSHALL |  | 07 | 10ES046 | Replace bridge on County Road 5 over the Tamarac River in Stephen in Marshall County. | Bridge Replacement | 2009-12-29 | 2010-04-12 | 2010-11-20 | 2010-09-17 | 1115117.5 | 0.080 | 10ES046
7002 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES047 | Curb ramps, sidewalk, pedestrian crossings on State Highway 47 from I-35W to 27th Avenue Northeast in Minneapolis. | Transportation Enhancements | 2010-02-08 | 2010-06-21 | 2010-08-01 | 2010-07-30 | 437563 | 2.811 | 10ES047
7003 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES048 | Curb ramps, sidewalk, pedestrian crossings on State Highway 5 from Davern St. in St. Paul to McKnight Road in Maplewood and on US 61 from State Highway 5 to Wheelock Parkway in St. Paul. | Transportation Enhancements | 2010-02-09 | 2010-04-14 | 2010-08-15 | 2010-09-14 | 1191786 | 11.470 | 10ES048
7004 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 10ES049 | Minneapolis-St. Paul metrowide upgrades to comply with the Americans with Disabilities Act. | Safety/Traffic Management | 2010-03-17 | 2010-05-03 | 2010-07-15 | 2010-07-30 | 618035.99 | 16.583 | 10ES049
7005 | MINNESOTA | Completed | C490 | OJT/SS | MINNESOTA | STATEWIDE |  |  | 10ES050 | Provide Commercial Drivers License training and certification for women and minorities. | Other | 2009-09-22 | 2009-12-15 | 2010-09-06 | 2010-11-30 | 286812 |  | 10ES050
7006 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | SIBLEY |  | 07 | 10ES051 | Resurface Sibley County Road 2 from County Road 7 to Gibbon north. | Pavement Improvement | 2010-06-09 | 2010-07-01 | 2010-08-20 | 2010-10-12 | 2744704.85 | 0.210 | 10ES051
7007 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | WADENA |  | 08 | 10ES052 | Replace bridge on County Road 2 over the Patridge River in Wadena County. | Bridge Replacement | 2010-01-04 | 2010-06-07 | 2010-09-01 | 2010-09-03 | 352680 | 0.133 | 10ES052
7008 | MINNESOTA | Completed | C240,C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 03 | 10ES053 | Resurface and update existing guardrail and drainage systems on I-94 from the Crow River in Rogers to I-494 in Maple Grove. | Pavement Improvement | 2010-02-08 | 2010-04-12 | 2010-10-29 | 2011-09-30 | 17705371 | 7.798 | 10ES053
7009 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | FILLMORE |  | 01 | 10ES054 | Resurfacing of Root River Trail from Fountain to Lanesboro. | Transportation Enhancements | 2010-03-29 | 2010-06-07 | 2010-07-30 | 2010-07-28 | 700000 |  | 10ES054
7010 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | BLUE EARTH |  | 01 | 10ES055 | Construct New Roadway On County Road 12 from County Highway 26 to County Highway 3 including County Highway 3 intersection in Mankato. | New Construction | 2010-05-19 | 2010-05-20 | 2010-11-01 | 2011-11-04 | 2000000 | 6.654 | 10ES055
7011 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES056 | Change lane configuration on northbound to westbound 35E/694 Ramp. | Safety/Traffic Management | 2010-01-13 | 2010-06-01 | 2010-06-21 | 2010-06-15 | 133515 | 0.000 | 10ES056
7012 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES057 | US 61 from Cannon St to 4th St in Hastings - replace pavement and install Americans with Disabilities Act pedestrian improvements. | Pavement Improvement | 2010-02-18 | 2010-05-17 | 2010-07-23 | 2010-08-24 | 822185 | 2.027 | 10ES057
7013 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES058 | Pedestrian & bike trail pavement replacement from Minnehaha Avenue to Century Avenue in Maplewood. | Transportation Enhancements | 2010-04-30 | 2010-05-17 | 2010-09-16 | 2011-06-09 | 1291544 | 1.336 | 10ES058
7014 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN | MINNEAPOLIS-ST. PAU, MN | 05 | 10ES059 | 5 separate Paving ramp meter bypass lanes at 5 separate locations on State Highway 100 from the south limits of Robbinsdale to France Avenue North. | Pavement Improvement | 2010-01-20 | 2010-07-19 | 2010-08-27 | 2010-08-27 | 530603.47 | 0.792 | 10ES059
7015 | MINNESOTA | Completed | C230 | Highway Infrastructure Investment Grant | MINNESOTA | STATEWIDE | MINNEAPOLIS-ST. PAU, MN |  | 10ES060 | Metrowide - Put in new LED lamps and refurbish control room video wall. | Safety/Traffic Management | 2010-01-20 | 2010-02-03 | 2010-05-17 | 2010-05-17 | 669614 |  | 10ES060
7016 | MINNESOTA | Underway | C240,C230 | Highway Infrastructure Investment Grant | MINNESOTA | SCOTT | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES061 | Design and build of interchange and over pass of State Highway 13 from State Highway 169 to just east of Louisiana Avenue. | New Bridge Construction | 2011-03-30 | 2011-05-10 | 2012-06-15 |  | 4319117.1 | 0.972 | 10ES061
7017 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | HENNEPIN |  | 03 | 10ES062 | Resurface both bridges, westbound off ramp over Light Rail Transit and City Street and over I35W in Minneapolis on I-94. | Bridge Improvement | 2010-03-04 | 2010-06-21 | 2010-08-19 | 2010-08-19 | 1405126.71 | 0.169 | 10ES062
7018 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES063 | Modify ramps and widen two bridges on I-694 at I-35W in New Brighton and Arden Hills. | Pavement Improvement | 2009-11-20 | 2010-02-01 | 2010-10-11 | 2010-10-22 | 2713667 | 0.436 | 10ES063
7019 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 10ES065 | Unbonded concrete overlay, guardrail, rehabilitate bridges, cable median barrier, drainage improvements on I-694 from I-94 to 50th Street. | Pavement Improvement | 2010-03-17 | 2010-04-19 | 2010-10-01 | 2010-10-21 | 13395746 | 4.939 | 10ES065
7020 | MINNESOTA | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | WASHINGTON | MINNEAPOLIS-ST. PAU, MN | 06 | 10ES066 | Resurface Highway 61 from Highway 10 to St. Paul Park Road in Cottage Grove and St. Paul Park. | Pavement Improvement | 2010-06-10 | 2010-06-14 | 2010-10-15 |  | 17323825 | 8.373 | 10ES066
7021 | MINNESOTA | Completed | C200,C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS |  | 08 | 10ES069 | Permanent repairs to failing sheet piling at the Port of Duluth. | Other | 2010-04-13 | 2010-05-25 | 2011-06-20 | 2010-11-03 | 1595090 |  | 10ES069
7022 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RAMSEY | MINNEAPOLIS-ST. PAU, MN | 04 | 10ES070 | Replace pavement, drainage, shoulder reconstruction on I-94 From State Highway 280 to Western Avenue in St. Paul. | Pavement Improvement | 2010-04-28 | 2010-05-10 | 2010-08-20 | 2010-10-25 | 10900606 | 4.338 | 10ES070
7023 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | DAKOTA | MINNEAPOLIS-ST. PAU, MN | 02 | 10ES071 | North of Cannon Falls on US 52 replace existing RR signals and add advance warning signs. | Safety/Traffic Management | 2009-11-23 | 2009-11-23 | 2009-12-30 | 2010-01-26 | 285193 | 0.500 | 10ES071
7024 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | RICE |  | 02 | 10ES072 | Replace bridge over Falls Creek on County Road 23 north of State Highway 60. | Bridge Replacement | 2010-04-21 | 2010-05-19 | 2010-08-27 | 2010-08-12 | 348739.67 | 0.090 | 10ES072
7025 | MINNESOTA | Completed | C250 | Highway Infrastructure Investment Grant | MINNESOTA | LE SUEUR, RICE |  | 02 | 10ES074 | Pavement replacement on State Highway 60 from State Highway 13 to State Highway 21. | Pavement Improvement | 2009-12-29 | 2010-04-01 | 2010-10-29 | 2010-11-03 | 3697823 | 15.064 | 10ES074
7026 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CROW WING |  | 08 | 10ES075 | On County Road 20 from North Ahrens Hill Rd to County Highway 49 in Crow Wing Co. Reconstruct to urban standards that include grading, surfacing, storm sewer & slope reinforcement. | Pavement Improvement | 2010-04-07 | 2010-04-19 | 2010-09-03 | 2010-08-30 | 1913731 | 0.935 | 10ES075
7027 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO |  | 08 | 10ES076 | Overly State Highway 243 from State Highway 95 to the St. Croix River and also rehabilitate the St. Croix River Bridge and approaches. | Pavement Improvement | 2010-01-12 | 2010-03-01 | 2010-07-31 | 2010-07-28 | 685352 |  | 10ES076
7028 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | CASS |  | 08 | 10ES077 | Resurface State Highway 84 from State Highway 371 to County Road 2, including upgrading pedestrian ramps in Pine River. | Transportation Enhancements | 2010-03-25 | 2010-04-26 | 2010-05-27 | 2010-05-20 | 150672.38 | 0.346 | 10ES077
7029 | MINNESOTA | Completed | C220 | Highway Infrastructure Investment Grant | MINNESOTA | AITKIN |  | 08 | 10ES078 | Replace sidewalks and pedestrian ramps to meet the Americans with Disabilities Act requirements. | Transportation Enhancements | 2010-04-20 | 2010-05-03 | 2010-05-28 | 2010-06-03 | 210044 | 0.440 | 10ES078
7030 | MINNESOTA | Completed | C220,C240 | Highway Infrastructure Investment Grant | MINNESOTA | ST LOUIS | DULUTH-SUPERIOR (WI) | 08 | 10ES079 | Restoration of Lester River Bridge on State Highway 61 between 60th and 61st Avenues in East Duluth. | Transportation Enhancements | 2010-06-10 | 2010-06-14 | 2010-10-01 | 2010-09-05 | 100000 | 0.132 | 10ES079
7031 | MINNESOTA | Completed | C200 | Highway Infrastructure Investment Grant | MINNESOTA | WRIGHT |  | 06 | 10ES081 | Resurface and replace deteriorating curbs and gutters on State Highway 25 from Interstate 94 to the Mississippi river in Monticello. | Pavement Improvement | 2010-06-15 | 2010-08-01 | 2010-10-15 | 2010-12-14 | 792826 | 0.851 | 10ES081
7032 | MINNESOTA | Underway | C200 | Highway Infrastructure Investment Grant | MINNESOTA | OLMSTED | ROCHESTER | 01 | 10ES082 | Repair median and resurface pavement on State Highway 14 from State Highway 52 to Marion Road in Rochester. Improve intersection of State Highway 14 and County Road 36; revise signals at 3rd Avenue SE. | Pavement Improvement | 2011-03-30 | 2011-05-02 | 2011-09-02 |  | 841290.89 | 3.185 | 10ES082
7033 | MINNESOTA | Completed | C490 | OJT/SS | MINNESOTA | STATEWIDE |  |  | 10ES083 | Provide heavy construction training for women and minorities. | Other | 2010-06-23 | 2010-06-28 | 2011-08-31 | 2012-09-14 | 739200 |  | 10ES083
7034 | MINNESOTA | Underway | C490 | OJT/SS | MINNESOTA | STATEWIDE |  |  | 10ES084 | Provide Roads Opportunities and Diversity Success training program. | Other | 2010-09-15 | 2010-09-15 |  |  | 173232 |  | 10ES084
7035 | MINNESOTA | Completed | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO |  | 08 | 10ES085 | Reconstruct pavement on County Road 15 from south of 240th Street to south of 253rd Street in Chisago city. | Pavement Improvement | 2010-09-15 | 2010-09-20 | 2011-06-24 | 2011-09-01 | 2837597.65 | 1.080 | 10ES085
7036 | MINNESOTA | Underway | C240 | Highway Infrastructure Investment Grant | MINNESOTA | CHISAGO |  | 08 | 10ES086 | Pavement preservation and safety improvements to Interstate 35 north of State Highway 8 to State Highway 95 in North Branch. | Pavement Improvement | 2010-11-18 | 2011-05-08 | 2011-07-25 |  | 9529596 | 15.416 | 10ES086
7037 | MINNESOTA | Underway | C200 | Highway Infrastructure Investment Grant | MINNESOTA | REDWOOD |  | 07 | 10ES087 | Restoration of Historic Retaining wall and Guardrail on State Highway 19 in Redwood County. | Transportation Enhancements | 2010-08-09 | 2011-02-01 | 2011-09-16 |  | 310300 | 0.031 | 10ES087
7038 | MINNESOTA | Underway | C220,C250 | Highway Infrastructure Investment Grant | MINNESOTA | CROW WING |  | 08 | 10ES088 | Construct dewatering system to allow repair of the Historic Garrison Concourse’s overlook wall along Trunk Highway 169 in Garrison. | Transportation Enhancements | 2010-08-27 | 2010-09-01 | 2011-11-30 |  | 551966.97 | 0.000 | 10ES088
7039 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | ATTALA |  | 02 | 0004017 | "This project will resurface and extend the life of the pavement on two sites in Attala county. The first site 25.6 miles in length on Vaiden French Camp Road just south of French Camp and the other | Pavement Improvement | 2009-07-20 | 2009-08-20 | 2010-02-11 | 2009-11-10 | 1183400 | 31.000 | 0004017
7040 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0012024 | The city of Batesville will install traffic signals and make other improvements at various locations. MS Hwy 6 at Lakewood/Power Dr.; MS Hwy 6 at Keating/Woodland Rd.; and MS Hwy 6 at US Hwy 51. This | Safety/Traffic Management | 2010-02-11 | 2010-02-11 | 2010-12-31 | 2011-06-22 | 255255 | 0.066 | 0012024
7041 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 0013040 | In Rankin county the city of Brandon resurface Crossgates Drive from Crossgates Blvd. east 1000 feet, resurface Marquette Road from Highway 80 to Region 8 Building, resurface North College Street from | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-02-23 | 490044 | 0.196 | 0013040
7042 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | COPIAH |  | 02 | 0015029 | This project will resurface and extend the life of the pavement on Carter Hill Road from Old Port Gibson Road to Dentville Road and on Browns Wells Road from Sylvarena Road to 0.7 miles south of Highway 28 near Dentville, Copiah county. | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-08-31 | 2009-11-23 | 456620 | 12.800 | 0015029
7043 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0018026 | The county of Forrest will resurface Monroe Rd, 42 Bypass to Travis Rd, Elks Lake Road, Hwy 98 to Hwy 49, Glendale ve/Eatonville Rd to Monroe Rd to I-59. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-01 | 2010-03-09 | 2010-05-05 | 2010-05-13 | 596903 | 15.008 | 0018026
7044 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | NOXUBEE |  | 03 | 0023071 | This project will resurface and extend the life of the pavement on US 45 from the Kemper County Line to Brooksville in Noxubee county. | Pavement Improvement | 2009-04-10 | 2009-06-01 | 2010-07-06 | 2010-07-13 | 11987698 | 22.188 | 0023071
7045 | MISSISSIPPI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0024041 | This project will construct additional lanes on US 45 from Carson Raod to 4 miles south of US 82 in Lowndes county. | New Construction | 2010-11-12 | 2011-01-19 | 2012-09-28 | 2012-09-28 | 5395447 | 6.500 | 0024041
7046 | MISSISSIPPI | Completed | C240,C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 0025033 | The city of Clinton will replace 4 bridges: Kickapoo Road over Bogue Chitto Creek, Clinton-Tennin Road over Straight Fence Creek, McRaven Road over Smith creek, and Magnolia Road over Branch-Bogue Chitto Creek, Hinds county. | Bridge Replacement | 2009-12-23 | 2009-12-23 | 2010-12-31 | 2011-04-18 | 1722106 | 0.000 | 0025033
7047 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE |  | 01 | 0025065 | This project will resurface and extend the life of the pavement for approximately 8 miles on US Highway 45 between New Wren and the Lee County Line, Monroe county. | Pavement Improvement | 2009-07-09 | 2009-09-22 | 2010-03-30 | 2010-05-03 | 3508915 | 7.233 | 0025065
7048 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 0025068 | The county of Hinds will resurface Siwell Road from Raymond Road to McCluer Road, resurface Terry Road from Siwell Road to Gary Road, resurface West Northside Drive from I-20 to Norrell Road, resurfa | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-07-23 | 2011-02-23 | 1108159 | 7.592 | 0025068
7049 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | HOLMES |  | 02 | 0026007 | This project will replace a bridge on Old Highway 49 over Tchula Lake near the town of Tchula, Holmes county. | Bridge Replacement | 2010-03-15 | 2010-03-16 | 2011-01-27 | 2011-06-09 | 816866 | 0.160 | 0026007
7050 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS |  | 02 | 0027012 | The town of Bolton will resurface Bolton-Brownsville Road from I-20 South 1300 feet. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2011-06-30 | 2011-04-11 | 110263 | 1.166 | 0027012
7051 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | ALCORN |  | 01 | 0028014 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas on the Alcorn County Welcome Center, Alcorn county. | Transportation Enhancements | 2009-10-08 | 2011-03-03 | 2010-07-16 | 2011-05-02 | 186700 | 0.000 | 0028014
7052 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | ITAWAMBA |  | 01 | 0029027 | This project will replace a bridge over Cummings Creek on Cummings Street north of Fulton, Itawamba county. | Bridge Replacement | 2010-02-12 | 2010-02-16 | 2010-09-18 | 2011-05-18 | 666899 | 0.300 | 0029027
7053 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | PASCAGOULA-MOSS POINT | 04 | 0031086 | This project will widen, add turn lanes and resurface US 90 from SR 57 to the West Pascagoula River Bridge in Jackson county. | Pavement Improvement | 2009-08-06 | 2009-08-10 | 2010-08-31 | 2011-03-01 | 10799800 | 3.230 | 0031086
7054 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON |  | 04 | 0031144 | This project will construct walking trails, parking, landscaping, and lighting to connect with the multi use path on the Bay St. Louis Bridge, Harrison county. | Transportation Enhancements | 2010-03-11 | 2010-03-11 | 2010-12-31 | 2011-01-21 | 1339307 | 0.413 | 0031144
7055 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON |  | 04 | 0031145 | This project will construct walking trails, parking, landscaping, and lighting to connect with the multi use path for the Biloxi Bay Bridge, Jackson county. | Transportation Enhancements | 2010-03-11 | 2010-03-11 | 2010-12-31 | 2011-01-21 | 322596 | 0.299 | 0031145
7056 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 0031147 | The city of Pass Christian will install street lighting along US 90 from Market Street to Davis Avenue. This project will improve traffic operations and safety. | Safety/Traffic Management | 2010-03-03 | 2010-03-03 | 2010-12-31 | 2011-05-03 | 124473 | 0.315 | 0031147
7057 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 0031148 | The city of Gulfport will install street lighting along US 90 from Cowan Road to Debuys Road. This project will improve traffic and safety. | Safety/Traffic Management | 2010-05-01 | 2010-05-28 | 2010-12-31 | 2012-02-24 | 788494 | 1.585 | 0031148
7058 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | MARSHALL |  | 01 | 0047320 | This project will reconstruct and add new pavement for 0.9 miles on the Chickasaw Trail Industrial Park Access Road approx. 6 miles north of Byhalia, Marshall county. | Pavement Improvement | 2009-11-23 | 2009-11-23 | 2010-05-17 | 2011-07-07 | 242645 | 1.000 | 0047320
7059 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0054032 | This project will replace the bridge over McLvor Canal on Mt. Level Road in Panola county. This project is located approx. 4 miles west of Sardis. | Bridge Replacement | 2009-07-02 | 2009-07-02 | 2009-12-22 | 2010-07-15 | 712698 | 0.200 | 0054032
7060 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0054034 | This project will replace the bridge over Bobo Creek on Benson Herron Road 1.5 miles southwest from the town of Courtland, Panola county. | Bridge Replacement | 2009-07-02 | 2009-07-02 | 2009-11-08 | 2010-04-29 | 295986 | 0.190 | 0054034
7061 | MISSISSIPPI | Completed | C200,C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 0061035 | The county of Rankin will resurface Spillway Road from Mill Creek Bridge to Eagle Point, Overlay Thomasville Road from Monterey Road east for 2.2 miles, Old Hwy 49 from Cleary Road north for 2.87 mile | Pavement Improvement | 2010-02-26 | 2010-02-26 | 2010-06-30 | 2012-02-06 | 1195568 | 8.904 | 0061035
7062 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | SHARKEY |  | 02 | 0063010 | This project will resurface various roads in the town of Anguilla, Sharkey county. | Pavement Improvement | 2009-05-04 | 2009-05-05 | 2010-09-10 | 2009-08-04 | 102200 | 5.600 | 0063010
7063 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ITAWAMBA |  | 01 | 0063036 | This project will upgrade US 78 to interstate standards from the east end of the Tenn-Tom Bridge to the Alabama State Line. This includes shoulder paving, guardrail upgrade, rumble strips and fencing. | Pavement Improvement | 2009-04-09 | 2009-04-20 | 2009-08-28 | 2009-08-21 | 3878121 | 13.050 | 0063036
7064 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LEE |  | 01 | 0063037 | This project will upgrade approximately 5 miles of US Highway 78 in Tupelo to interstate standards McCullough Boulevard @ Belden to US 45. This includes shoulder paving, guardrail upgrade, rumble strips and fencing. | Pavement Improvement | 2009-06-11 | 2009-06-26 | 2009-09-16 | 2009-11-06 | 2976283 | 4.657 | 0063037
7065 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | ITAWAMBA |  | 01 | 0063038 | This project will add new landscaping to the US 78 Tremont Welcome Center on the North Bound Lane in Itawamba county. | Transportation Enhancements | 2010-09-09 | 2010-09-14 | 2011-06-24 | 2011-06-16 | 100000 | 0.000 | 0063038
7066 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | TALLAHATCHIE |  | 02 | 0068100 | This project will resurface and extend the life of the pavement on 14 different roads in the town of Webb, Tallahatchie county: Main Street Extension, 5th Street, Deere Avenue, Plow Street, John Stree | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2009-12-29 | 2010-02-16 | 47000 | 2.900 | 0068100
7067 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON |  | 02 | 0070017 | The city of Canton will resurface North Old Canton Road from the City Limits to US 51; Walnut Street from Dinkins Street to Peace Street; and West North Street from Canal Street to MLK Drive. This pro | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2010-12-31 | 2011-04-08 | 352421 | 1.591 | 0070017
7068 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ALCORN |  | 01 | 0071074 | This project will resurface and extend the life of the pavement for approximately 15 miles on US Highway 72 between the Tippah County Line and State Route 2, Alcorn county. | Pavement Improvement | 2009-07-09 | 2009-08-07 | 2009-11-30 | 2010-05-20 | 6927600 | 14.778 | 0071074
7069 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | COAHOMA |  | 02 | 0080026 | The city of Clarksdale will resurface Florence Avenue, Martin Luther King, Jr. Boulevard, New Africa Road, Oakridge Road, and Maple Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-12-31 | 2011-04-07 | 696763 | 4.492 | 0080026
7070 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | COVINGTON |  | 03 | 0082093 | This project will resurface and extend the life of the pavement on approximately 18 miles of US Highway 49 northbound lanes from Seminary to the Simpson County Line in Covington county. | Pavement Improvement | 2009-04-09 | 2009-04-20 | 2009-09-29 | 2009-11-04 | 3872279 | 16.782 | 0082093
7071 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | SIMPSON |  | 03 | 0082094 | This project will resurface and extend the life of the pavement for approximately 6 miles of US Highway 49 beginning 15.9 miles north of the Covington county line then running north for 5.6 miles near Mendenhall, Simpson county. | Pavement Improvement | 2009-08-06 | 2009-08-13 | 2009-11-25 | 2010-03-08 | 2588614 | 5.611 | 0082094
7072 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | SIMPSON |  | 03 | 0082095 | This project will resurface and extend the life of the pavement for approximately 16 miles on US Highway 49 beginning at the Covington county line and continuing north, Simpson county. Northbound lanes only. | Pavement Improvement | 2009-08-06 | 2009-08-11 | 2010-12-31 | 2011-04-14 | 3611542 | 15.892 | 0082095
7073 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | YAZOO |  | 02 | 0084061 | This project will resurface and extend the life of the pavement on US Highway 49 between the Madison County Line and Bentonia in Yazoo county. | Pavement Improvement | 2009-04-08 | 2009-05-12 | 2009-08-07 | 2009-09-24 | 2377574 | 5.005 | 0084061
7074 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LEFLORE |  | 02 | 0085028 | This project will resurface and extend the life of the pavement for approximately 11 miles on US 49 from US 82 to SR 8, Leflore County. | Pavement Improvement | 2009-08-06 | 2009-08-06 | 2009-12-07 | 2010-03-16 | 3907605 | 15.650 | 0085028
7075 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON |  | 04 | 0101133 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-10 East rest area, Jackson county. | Transportation Enhancements | 2010-03-11 | 2010-03-11 | 2010-03-31 | 2012-02-15 | 1011100 | 0.000 | 0101133
7076 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PONTOTOC |  | 01 | 0102008 | The city of Pontotoc will resurface Industrial Drive/South Industrial Circle east of First National Bank on Hwy 15 to intersection of Bolton Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 | 2011-03-17 | 169993 | 0.951 | 0102008
7077 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0110023 | The city of Columbus will resurface Military Rd between 18th & 3rd; 7th between Bluecutt and 18th; Willowbrook between 5th & 7th; MS 12 between Lehmberg & US 82; Island between W Br. End & Dead End; W | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2011-06-30 | 2011-05-12 | 716183 | 4.396 | 0110023
7078 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0110024 | This project will stripe and resurface Military Road between Ridge Rd. and Hwy 82 and Bell Ave/ Airline Rd. between Hwy 69 and S. 25th St./Martin Luther King Jr. Drive in the city of Columbus, Lowndes | Pavement Improvement | 2010-03-31 | 2010-03-31 | 2011-06-30 | 2012-03-19 | 383785 | 0.000 | 0110024
7079 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0113076 | This project will resurface and extend the life of the pavement for approximately 9 miles on US Highway 82 between near Military Road in Columbus and the Alabama State Line, Lowndes county. | Pavement Improvement | 2009-07-09 | 2009-07-20 | 2009-10-13 | 2009-11-06 | 3334125 | 8.249 | 0113076
7080 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | ALCORN |  | 01 | 0120015 | The city of Corinth will resurface and stripe Fulton Drive from Linden to Shiloh Rd; Fulton Drive from Hwy 72 south to city limits; and Alcorn Drive from Hwy 72 to Linden Street. This project will mak | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-04-26 | 2010-05-20 | 589662 | 1.635 | 0120015
7081 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | PEARL RIVER |  | 04 | 0124040 | This project will replace four bridges over Hobolochito Creek on Burned Bridge-Pine Grove Road west of Picayune, Pearl River county. | Bridge Replacement | 2009-08-24 | 2009-08-24 | 2010-04-06 | 2011-02-09 | 2199700 | 0.900 | 0124040
7082 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | WALTHALL |  | 03 | 0142060 | This project will resurface and extend the life of the pavement on approximately 6 miles of U.S. Highway 98 between the Pike County Line and Tylertown in Walthall county. | Pavement Improvement | 2009-04-09 | 2009-04-13 | 2009-08-12 | 2009-09-24 | 3061304 | 6.081 | 0142060
7083 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | WALTHALL |  | 03 | 0142061 | This project will resurface and extend the life of the pavement on approximately 5 miles of US Highway 98 from the west end of the Tylertown bypass to the east end of the Tylertown bypass, Walthall county. | Pavement Improvement | 2009-06-11 | 2009-08-14 | 2009-09-02 | 2009-10-29 | 1702338 | 4.391 | 0142061
7084 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAMAR |  | 04 | 0142063 | This project will resurface and improve the safety of US 98 from State Route 589 to Weathersby Road in Lamar county. | Pavement Improvement | 2009-10-08 | 2009-11-03 | 2010-09-30 | 2011-09-14 | 8354134 | 5.878 | 0142063
7085 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ADAMS |  | 03 | 0151054 | This project will resurface and extend the life of the pavement on US 84 from US 61 Intersection to the Franklin county line, Adams county. | Pavement Improvement | 2009-07-24 | 2009-07-30 | 2009-11-30 | 2009-12-08 | 4207644 | 10.053 | 0151054
7086 | MISSISSIPPI | Underway | C220,C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ADAMS |  | 03 | 0151060 | This project will install aesthetic street and bridge lighting and traffic cameras on the bridge over the Mississippi River in Natchez in Adams county. | Transportation Enhancements | 2009-07-09 | 2009-07-22 | 2010-12-31 |  | 1702600 | 2.496 | 0151060
7087 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | FRANKLIN |  | 03 | 0151063 | This project will resurface and extend the life of the pavement on approximately 8 miles of U.S. Hwy 84 west the Bude/Meadville By-Pass in Franklin county. | Pavement Improvement | 2009-03-31 | 2009-04-28 | 2009-09-30 | 2009-08-13 | 4239662 | 8.715 | 0151063
7088 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | BOLIVAR, SUNFLOWER |  | 02 | 0161029 | This project will construct 2 additional lanes on State Route 8 between Cleveland and Ruleville in Bolivar and Sunflower Counties. | Pavement Widening | 2009-06-11 | 2009-06-19 | 2010-07-09 | 2012-05-09 | 7629692 | 7.872 | 0161029
7089 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | BOLIVAR, SUNFLOWER |  | 02 | 0161033 | This project will resurface and extend the life of the pavement on State Route 8 from the Bolivar county Hospital to Ruleville, Bolivar and Sunflower county. | Pavement Improvement | 2009-07-09 | 2009-08-06 | 2009-10-09 | 2009-12-15 | 2416348 | 8.654 | 0161033
7090 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | AMITE, PIKE |  | 03 | 0168010 | This project will reconstruct the existing pavement, replace utilities, and improve safety on State Route 570 from .58 miles west of the Pike county line to the Pike county line and on State Route 570 | Pavement Improvement | 2009-07-30 | 2009-08-26 | 2011-05-17 | 2011-06-03 | 6372500 | 3.553 | 0168010
7091 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LEFLORE |  | 02 | 0180017 | The city of Greenwood will resurface Claiborne Street from US 82 to Grand Boulevard, Poplar Street from Claiborne to Park, and Garrard Avenue from US 82 to Sycamore Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-04-18 | 659169 | 2.350 | 0180017
7092 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | GRENADA |  | 01 | 0190005 | The city of Grenada will resurface Vance Road from Townes Ave to Browns Creek Bridge and Jackson Avenue from US 51 to Monroe St. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-01-28 | 517732 | 3.433 | 0190005
7093 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0193008 | The city of Petal will resurface Hillcrest Loop and Carterville Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-01 | 2010-03-10 | 2010-04-30 | 2010-05-13 | 455204 | 4.084 | 0193008
7094 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | SCOTT |  | 03 | 0202079 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the rest area on I-20 East and West Bound Rest Areas, Scott County. | Transportation Enhancements | 2009-11-05 | 2009-10-26 | 2010-07-31 | 2011-08-03 | 1056100 | 0.000 | 0202079
7095 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST, LAMAR |  | 04 | 0210017 | This project will install overhead message signs, traffic cameras, and other traffic monitoring devices on US 49, US 98 & I-59 in Hattiesburg, Forrest county. | Other | 2009-11-05 | 2009-12-15 | 2011-06-30 | 2011-06-07 | 3826379 | 21.422 | 0210017
7096 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0210021 | The city of Hattiesburg will construct a bikepath beginning Construction of a park along the Leaf River and construction of a multi-use trail. This project will improve bike access. | Transportation Enhancements | 2010-05-10 | 2010-05-10 | 2011-06-30 | 2012-01-09 | 490794 | 0.080 | 0210021
7097 | MISSISSIPPI | Underway | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0210022 | This project will add a new bikeway from US 49 to the University of Southern Mississippi. Forrest County | Transportation Enhancements | 2010-03-25 | 2010-03-25 | 2011-06-30 |  | 880400 | 0.047 | 0210022
7098 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 0211105 | The city of Horn Lake will construct a sidewalk along Goodman Rd. from Horn Lake Rd. to Hurt Rd. and pave Tulane Rd. from Nail Rd to Goodman Rd. This project will improve pedestrian access along Goodman Road. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-12-31 | 2012-01-09 | 418027 | 2.550 | 0211105
7099 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 0211106 | The city of Horn Lake will install a traffic signal and make other improvements at Goodman Road and Windchase Drive. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 2010-02-22 | 2010-02-22 | 2010-12-31 | 2011-09-19 | 170550 | 0.010 | 0211106
7100 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JONES |  | 04 | 0221072 | This project will resurface and extend the life of the pavement approximately 2 miles in length on State Route 15 from 115th Street to Old Highway 15 in Laurel, Jones. | Pavement Improvement | 2009-04-08 | 2009-04-09 | 2009-06-04 | 2009-05-11 | 1202383 | 2.287 | 0221072
7101 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 0221073 | This project will resurface and extend the life of the pavement for approximately 6.2 miles on State Route 15 from the intersection of State Route 67 going north. Harrison county. | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2010-06-07 | 2008-07-01 | 940000 | 6.143 | 0221073
7102 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | CHICKASAW |  | 01 | 0223023 | This project will resurface and extend the life of the pavement for approximately 9 miles on State Route 15 between Houston and the Pontotoc county line, Chickasaw county. | Pavement Improvement | 2009-07-09 | 2009-07-16 | 2009-09-25 | 2009-11-06 | 2222728 | 9.385 | 0223023
7103 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | PERRY |  | 04 | 0224034 | This project will replace a bridge on State Route 29 over Black Creek in Perry county. | Bridge Improvement | 2009-06-01 | 2009-06-01 | 2010-12-31 | 2011-05-26 | 4258100 | 0.092 | 0224034
7104 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MARSHALL |  | 01 | 0230008 | The city of Holly Springs will resurface College Street from Boundary to Memphis Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-01-12 | 261488 | 0.672 | 0230008
7105 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | ATTALA |  | 02 | 0232047 | This project will resurface and extend the life of the pavement on State Route 35 multilane section in Kosciusko from Natchez Trace Parkway to State Route 12, approximately 3 miles, Attala county. | Pavement Improvement | 2009-09-10 | 2009-10-22 | 2010-02-26 | 2010-02-02 | 1250021 | 2.444 | 0232047
7106 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | WAYNE |  | 04 | 0233013 | This project is a base repair, leveling, and overlay project along Clara-Buckatuna Road for 4.92 miles, Wayne county. This project will make the road smoother and will extend the life of the pavement. | Pavement Improvement | 2010-06-01 | 2010-07-07 | 2010-09-29 | 2011-04-29 | 192139 | 4.920 | 0233013
7107 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | SUNFLOWER |  | 02 | 0240009 | The city of Indianola will resurface BB King, Westside Avenue, and Wiggins Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-06-30 | 2011-07-18 | 536340 | 2.744 | 0240009
7108 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 0250034 | The city of Jackson will resurface Northside Drive from Medgar Evers Boulevard to Jackson City Limits and Maddox Road from MS 18 to John R. Lynch Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-04-28 | 2010-04-28 | 2011-06-30 | 2011-10-28 | 2763700 | 10.541 | 0250034
7109 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | NEWTON, NESHOBA |  | 03 | 0261076 | This project will construct additional lanes on State Route 19 between the Lauderdale County Line and SR 492 in Newton and Neshoba county. | Pavement Widening | 2009-04-06 | 2009-04-15 | 2012-02-01 | 2012-01-24 | 34406000 | 7.147 | 0261076
7110 | MISSISSIPPI | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LINCOLN |  | 03 | 0275017 | This project will resurface, improve drainage, and extend the life of the pavement on approx. 7.2 miles of the Eddiceton-Caseyville Road in the Homochitto National Forrest located approx. ten miles west of Brookhaven, Lincoln county. | Pavement Improvement | 2009-11-09 | 2009-11-30 | 2011-02-24 | 2012-02-02 | 1668230 | 8.000 | 0275017
7111 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 0291004 | The city of Flowood will resurface 1.95 miles of Old Brandon Road from Hwy 80 to Pearl River Bridge and the addition of a left-turn lane along Treetops Blvd. at the existing intersection with Top Stre | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-02-23 | 510808 | 1.992 | 0291004
7112 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PIKE |  | 03 | 0310013 | The city of McComb will resurface and perform sidewalk Improvements to Pearl River Avenue, South Magnolia Street and Summit Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2011-06-30 | 2011-05-12 | 760469 | 1.830 | 0310013
7113 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO |  | 01 | 0311018 | This project will replace 4 bridges on MS Highway 305 from Cockrum to Lewisburg in Desoto county. | Bridge Replacement | 2009-07-09 | 2009-07-09 | 2011-08-03 | 2011-11-14 | 7551300 | 1.430 | 0311018
7114 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HANCOCK | BILOXI-GULFPORT | 04 | 0321034 | The city of Bay St. Louis will install street lighting along Hwy 43 from Longfellow Road to I-10. This project will improve traffic operations and safety along this section of roadway. | Safety/Traffic Management | 2010-02-08 | 2010-02-08 | 2010-12-31 | 2011-05-03 | 732709 | 4.889 | 0321034
7115 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | ADAMS |  | 03 | 0340034 | The city of Natchez will resurface Pearl Street, Commerce Street, Rankin Street, Washington Street, Canal Street, State Street and Melrose Avenue. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-06-30 | 2011-05-27 | 565281 | 2.101 | 0340034
7116 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | UNION |  | 01 | 0350012 | The city of New Albany will resurface and stripe Carter Ave. between Camp Ave. and Main St; on Bankhead Street between Camp Ave. and Glade Ave.; and replace a box culvert on Carter Avenue. This projec | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-06-30 | 2011-03-23 | 165234 | 0.483 | 0350012
7117 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAFAYETTE |  | 01 | 0360009 | The city of Oxford will resurface Jackson Avenue, Old Taylor Road (8601), Old Taylor Road (9426) and Belk Drive. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 | 2011-05-12 | 421873 | 1.363 | 0360009
7118 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | JEFFERSON DAVIS |  | 03 | 0371051 | This project will resurface and extend the life of the pavement on State Route 13 from north of the Marion County Line to US 84, Jefferson Davis county. | Pavement Improvement | 2009-07-09 | 2009-07-06 | 2009-09-30 | 2009-10-08 | 1642149 | 9.334 | 0371051
7119 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | NESHOBA |  | 03 | 0390009 | The city of Philadelphia will resurface Herman Alford Blvd. from Pecan Ave to 250 feet South of Saxon Airport Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2011-06-30 | 2011-01-14 | 279334 | 0.565 | 0390009
7120 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | SIMPSON |  | 03 | 0392050 | This project will replace a bridge over the Middle Prong- Silver Creek on the Rockport-Shivers and Mount Zion Road 2.5 miles north of the Jefferson Davis/Simpson county line, Simpson County. | Bridge Replacement | 2009-07-07 | 2009-08-07 | 2009-12-01 | 2010-09-16 | 516694 | 0.300 | 0392050
7121 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PEARL RIVER |  | 04 | 0400023 | The city of Picayune will resurface North Main Street between West Canal Street and E. 4th Street' Beech Street between Will Street and Palentine Rd., and Palestine Rd and Crosby St. between West Cana | Pavement Improvement | 2010-03-01 | 2010-03-02 | 2010-04-22 | 2010-05-11 | 378056 | 4.081 | 0400023
7122 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | OKTIBBEHA |  | 03 | 0420017 | The city of Starkville will resurface: N. Montgomery St., University Drive, Jackson Street, Louisville Street, Yellow Jacket Drive and S. Montgomery Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-06-30 | 2011-02-08 | 603987 | 4.405 | 0420017
7123 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | OKTIBBEHA |  | 03 | 0420018 | This project will stripe and resurface Whitfield St. between Greensboro St. and Ave. of Patriots; and Louisville St. between Lynn Lane and Industrial Park Road in the city of Starkville, Oktibbeha co | Pavement Improvement | 2010-03-31 | 2010-03-31 | 2011-06-30 | 2010-12-17 | 157713 | 0.000 | 0420018
7124 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | BOLIVAR |  | 02 | 0432015 | This project will resurface and extend the life of the pavement on approximately 11 miles of State Route 1 north of Rosedale in Bolivar county. | Pavement Improvement | 2009-05-19 | 2009-05-21 | 2009-07-24 | 2009-08-07 | 2959122 | 10.736 | 0432015
7125 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WARREN |  | 02 | 0440010 | The city of Vicksburg will resurface Wisconsin Avenue Overlay from Bazinsky Road to Interstate 20 and will resurface Clay Street from Cherry Street to Mission 66. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-02-23 | 644013 | 1.732 | 0440010
7126 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | WARREN |  | 02 | 0440011 | The city of Vicksburg conduct interior renovations and make purchases of museum exhbits, Warren County. | Transportation Enhancements | 2010-08-27 | 2010-08-27 | 2011-12-31 | 2012-02-02 | 1781142 | 0.000 | 0440011
7127 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONTGOMERY |  | 02 | 0470010 | The city of Winona will resurface Fairgrounds Street from Railroad Crossing to a point 1250 feet North of Railroad Crossing and Pecan Street from Fairgrounds St. to US Hwy 82 (begin State Maintenance) | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-06-30 | 2011-02-23 | 158869 | 1.083 | 0470010
7128 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | YAZOO |  | 02 | 0480036 | The city of Yazoo will resurface Grady Ave from Mike Espy Dr to 9th, Lamar Ave from W 2nd St to 15th St., MLK Dr from 1st to 9th St. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2011-06-30 | 2011-04-04 | 470640 | 2.174 | 0480036
7129 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | COPIAH |  | 02 | 0541050 | This project will resurface and extend the life of the pavement on approximately 10 miles of State Route 27 north of Georgetown in Copiah county. | Pavement Improvement | 2009-04-09 | 2009-04-28 | 2009-07-15 | 2009-07-31 | 3193584 | 9.969 | 0541050
7130 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | PIKE |  | 03 | 0551094 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 welcome center, Pike County | Transportation Enhancements | 2010-03-11 | 2009-12-16 | 2010-10-13 | 2010-10-14 | 396000 | 0.000 | 0551094
7131 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | COPIAH |  | 02 | 0551095 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Rest Area in Copiah County - North Bound Lanes. | Transportation Enhancements | 2009-12-03 | 2009-12-03 | 2010-08-31 | 2011-05-20 | 760900 | 0.000 | 0551095
7132 | MISSISSIPPI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | HOLMES |  | 02 | 0552201 | This project will resurface and extend the life of the pavement on approximately 22.4 miles of I-55 between State Route 17 and the Carroll County Line, Holmes county. | Pavement Improvement | 2010-05-06 | 2010-08-12 | 2011-10-21 | 2010-12-08 | 10570800 | 22.871 | 0552201
7133 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | HOLMES |  | 02 | 0552210 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the rest area on I-55 Northbound north of Durant, Holmes county. | Transportation Enhancements | 2009-10-01 | 2009-10-22 | 2010-07-30 | 2011-05-05 | 467600 | 0.000 | 0552210
7134 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | CARROLL |  | 02 | 0553083 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Rest Area near Vaiden, Carroll county. | Transportation Enhancements | 2009-10-08 | 2009-10-12 | 2010-07-12 | 2010-06-30 | 257119 | 0.000 | 0553083
7135 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO |  | 01 | 0554091 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-55 Desoto County Rest Area, Desoto county. | Transportation Enhancements | 2009-12-03 | 2009-12-18 | 2010-10-15 | 2011-11-17 | 498300 | 0.000 | 0554091
7136 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0554092 | This project will add new landscaping onto the Interstate 55 Rest Area on the North and South Bound Lanes in Panola county. | Transportation Enhancements | 2011-03-10 | 2011-03-14 | 2012-02-01 | 2011-11-15 | 90958 | 0.000 | 0554092
7137 | MISSISSIPPI | Completed | C220,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | STATEWIDE |  |  | 0554093 | This project will add new landscaping to along ths side of the I-55 North and South Bound lanes throughout the Mississippi Deparment of Transportation's District 2. This includes the counties of ........... | Transportation Enhancements | 2010-06-10 | 2010-08-17 | 2011-06-30 | 2011-08-02 | 374700 | 248.347 | 0554093
7138 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN |  | 03 | 0561068 | This project will resurface and extend the life of the pavement on State Route 25 from State Route 471 to State Route 43 in Rankin county. | Pavement Improvement | 2009-04-10 | 2009-06-27 | 2010-05-07 | 2010-07-07 | 8833500 | 10.195 | 0561068
7139 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | COAHOMA |  | 02 | 0571004 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the Delma Furniss Hospitality Station, Coahoma county. | Transportation Enhancements | 2009-10-08 | 2009-10-14 | 2010-09-14 | 2010-09-23 | 263800 | 0.000 | 0571004
7140 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | PEARL RIVER |  | 04 | 0591105 | This is a design build project which will add shoulders to 12 bridges on I-59 from the Louisiana state line to Poplarville, Pearl River County. | Bridge Improvement | 2009-08-10 | 2009-08-11 | 2010-12-31 | 2011-12-15 | 10000000 | 0.633 | 0591105
7141 | MISSISSIPPI | Completed | C220 | Highway Infrastructure Investment Grant | MISSISSIPPI | PEARL RIVER |  | 04 | 0591106 | This project will add new landscaping, irrigation, benches, sidewalks, and picnic areas to the I-59 welcome center, Pearl River Co. | Transportation Enhancements | 2009-05-07 | 2009-05-07 | 2011-12-31 | 2010-11-17 | 439900 | 0.000 | 0591106
7142 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE |  | 03 | 0593084 | This project will build a new interchange at I-20/59 and Hawkins Rd. & 23rd Ave in Meridian in Lauderdale county. This project will add new pavement, street lights, and bridge construction. | New Construction | 2009-07-09 | 2009-07-09 | 2011-07-29 | 2011-10-26 | 15311899 | 0.064 | 0593084
7143 | MISSISSIPPI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE, NEWTON |  | 03 | 0593090 | This project is a design build project which will extend the I-59/I-20 merge lanes in Lauderdale county. Also, this project will add shoulders to 6 bridges on I-20 in Newton county. | Bridge Improvement | 2009-01-16 | 2009-01-16 | 2010-12-15 | 2011-12-15 | 9999999 | 6.335 | 0593090
7144 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | WASHINGTON |  | 02 | 0622027 | This project will resurface and extend the life of the pavement for approximately 10 miles on State Route 438 from US 61 through Arcola to Highway 1, Washington county. | Pavement Improvement | 2009-06-11 | 2009-06-17 | 2009-09-04 | 2009-09-24 | 2418334 | 9.673 | 0622027
7145 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | WINSTON |  | 01 | 0679004 | This project will resurface and extend the life of the pavement on Ellison Ridge Road for approx 4 miles in length located 7 miles northeast of Noxapater, Winston county. | Pavement Improvement | 2009-06-26 | 2009-07-09 | 2009-10-01 | 2009-10-05 | 409900 | 4.150 | 0679004
7146 | MISSISSIPPI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0681017 | State Route 69 from Plymouth Road to Highway 69 south and SR 182 from State Route 69 to the Alabama state line for 9.67 miles, Lowndes county. This project will resurface and extend the life of the pavement in Lowndes county. | Pavement Improvement | 2010-05-10 | 2010-05-25 | 2010-11-19 | 2010-11-18 | 3534132 | 0.000 | 0681017
7147 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | PANOLA |  | 01 | 0703016 | This project will resurface and extend the life of the pavement for approximately 11 miles on eastbound lanes for State Route 6 east of Batesville, Panola county. | Pavement Improvement | 2009-08-04 | 2009-08-06 | 2009-12-14 | 2010-02-24 | 2979976 | 11.916 | 0703016
7148 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE |  | 03 | 0741010 | This project will resurface and extend the life of the pavement on State Route 39 From I-20 to 52nd Street in Meridian, Lauderdale county. | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-11-24 | 2010-01-22 | 3638275 | 3.864 | 0741010
7149 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE, CLAY |  | 01 | 0791029 | This project will resurface and extend the life of the pavement on US 45 Alternative from West Point to one mile north of State Route 25, Monroe and Clay county. | Pavement Improvement | 2009-07-09 | 2009-07-14 | 2009-11-09 | 2009-12-01 | 4257606 | 8.187 | 0791029
7150 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LOWNDES |  | 01 | 0791030 | This project will resurface and extend the life of the pavement on US 45 Alternative from 9 miles north of the Noxubee County Line to the Clay county line, Lowndes county. | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-10-19 | 2010-01-11 | 2533578 | 6.625 | 0791030
7151 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE, CHICKASAW |  | 01 | 0792015 | This project will resurface and extend the life of the pavement on approximately 9 miles of US 45 Alternative between State Route 8 and the northern Monroe county line, Monroe and Chickasaw county. | Pavement Improvement | 2009-07-09 | 2009-07-29 | 2009-11-23 | 2010-01-11 | 3694157 | 8.847 | 0792015
7152 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAFAYETTE |  | 01 | 0793002 | This project will replace a bridge on State Route 331 over Yocona River near State Route 334 in Lafayette county. | Bridge Replacement | 2009-07-09 | 2009-07-09 | 2011-04-08 | 2011-05-18 | 3960000 | 1.109 | 0793002
7153 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 0801015 | This project will resurface and extend the life of the pavement on US 49 from Edwards St. to 31st. Avenue in Hattiesburg, Forrest county. | Pavement Improvement | 2009-07-09 | 2009-07-10 | 2009-11-30 | 2010-03-12 | 7545174 | 5.835 | 0801015
7154 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | TISHOMINGO |  | 01 | 0948008 | This project will resurface and extend the life of the pavement on State Route 365 from the Prentiss/Tishomingo County Line to US 72 in Tishomingo county | Pavement Improvement | 2009-07-09 | 2009-07-03 | 2009-09-02 | 2009-09-10 | 1418166 | 6.569 | 0948008
7155 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | PERRY |  | 04 | 1152001 | This project will replace the existing bridge on State Route 198 over Dickey Creek near Beaumont in Perry county. | Bridge Replacement | 2009-07-09 | 2009-07-13 | 2010-03-31 | 2010-05-21 | 1469900 | 0.038 | 1152001
7156 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | OKTIBBEHA |  | 03 | 2714001 | This project will replace two bridges, first bridge over Glen Creek and second bridge over Tobacco Juice Creek, along Poorhouse Road 3 miles south of Starkville, Oktibbeha county. | Pavement Improvement | 2009-12-21 | 2010-01-05 | 2010-09-21 | 2011-11-02 | 1246904 | 1.300 | 2714001
7157 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | YALOBUSHA, CALHOUN |  | 01 | 2791008 | This project will replace 9 bridges on State Route 32 from Water Valley to State Route 330 in Yalobusha and Calhoun county. | Bridge Replacement | 2009-08-06 | 2009-08-14 | 2011-02-18 | 2011-05-24 | 5923600 | 0.137 | 2791008
7158 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | TATE |  | 01 | 2920001 | This project will construct two additional lanes on US 51 between Senatobia and Coldwater in Tate county. | New Construction | 2009-10-08 | 2009-10-08 | 2012-02-01 | 2012-02-01 | 10497777 | 2.999 | 2920001
7159 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | TATE |  | 01 | 5512002 | The city of Senatobia will resurface East Main Street from SR 4 to Park Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 | 2011-03-17 | 217140 | 0.489 | 5512002
7160 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WAYNE |  | 04 | 5583001 | The city of Waynesboro will resurface West Avenue from MS 184 to Turner Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-01 | 2010-03-04 | 2010-04-27 | 2010-06-15 | 128359 | 0.856 | 5583001
7161 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | COPIAH |  | 02 | 5604001 | The city of Crystal Springs will resurface and add sidewalk ramps on Newton Street between Georgetown Street and Harmony Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-06-30 | 2011-02-23 | 210757 | 0.380 | 5604001
7162 | MISSISSIPPI | Underway | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | TIPPAH |  | 01 | 5659002 | The city of Ripley will resurface a section of Main Street from Highway 15 and extending northerly, approximately 0.75 miles to Highway 15. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2010-06-30 |  | 143707 | 0.579 | 5659002
7163 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MARION |  | 04 | 6034005 | The city of Columbia will resurface and stripe Main Street beginning approx. 500 feet west of the intersection of Broad St. and High School Ave. and then west and north to Lafayette Street. This proje | Pavement Improvement | 2009-11-17 | 2009-11-17 | 2010-06-30 | 2011-04-29 | 236954 | 0.519 | 6034005
7164 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WASHINGTON |  | 02 | 6922001 | The city of Greenville will resurface Tennessee Gas Road from Main Street to Highway 1. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-12-31 | 2011-05-12 | 1078008 | 1.135 | 6922001
7165 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON | JACKSON | 02 | 6980001 | The city of Flora will resurface First Street from US 49 to US 49. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-08-29 | 344483 | 2.663 | 6980001
7166 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON | JACKSON | 02 | 6988001 | The city of Madison will resurface North Old Canton Road from Sowell Road to Canton City Limits. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-02 | 2010-03-02 | 2010-12-31 | 2011-05-11 | 337949 | 1.870 | 6988001
7167 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 03 | 7037001 | The town of Terry will resurface Cunningham Avenue from I-55 to Railroad Avenue. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-05-11 | 267604 | 0.677 | 7037001
7168 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE |  | 01 | 7163001 | The city of Aberdeen will resurface Chestnut Street from Hwy 45/25 to Hwy 145. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-08 | 2010-02-15 | 2011-06-30 | 2010-03-30 | 158068 | 0.650 | 7163001
7169 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WASHINGTON |  | 02 | 7221002 | The city of Greenville will add left turn lanes at the intersection of Reed Road and Main Street. This project will improve traffic operations and safety. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-12-31 | 2011-05-12 | 523897 | 0.020 | 7221002
7170 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 7272006 | The city of Pearl at Old Brandon Road will install a traffic signal and make other improvements at the intersection at Bierdeman Road and at Patton Drive. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 2010-02-22 | 2010-02-22 | 2011-06-30 | 2011-10-28 | 181433 | 0.008 | 7272006
7171 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 7314022 | This project will improve safety and traffic operations by installing a traffic signal installation at the intersection of US Hwy 80 and Shaw Road in Hinds county. | Safety/Traffic Management | 2009-06-11 | 2009-09-08 | 2009-09-25 | 2009-11-23 | 130456 | 0.001 | 7314022
7172 | MISSISSIPPI | Completed | C240 | Highway Infrastructure Investment Grant | MISSISSIPPI | HINDS | JACKSON | 02 | 7314023 | This project will resurface and extend the life of the pavement on US 80 from Springridge Road to Terry Road, Hinds county. | Pavement Improvement | 2009-07-09 | 2009-07-22 | 2009-11-24 | 2009-05-07 | 5826874 | 7.909 | 7314023
7173 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN | JACKSON | 03 | 7336004 | The city of Pearl will resurface Pirates Cove Road from Hwy 80 to Pearl High School Entrance. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2011-06-30 | 2011-03-25 | 294874 | 1.060 | 7336004
7174 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON | JACKSON | 03 | 7354001 | The city of Madison will resurface Highland Colony Parkway -South Bound - between Madison Avenue and Broadmoor Baptist Church. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 | 2011-04-08 | 387782 | 1.006 | 7354001
7175 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | MADISON | JACKSON | 03 | 7354002 | The city of Ridgeland will resurface Highland Colony Parkway from Steed Road north 3000 feet. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-07-18 | 373578 | 0.559 | 7354002
7176 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PIKE |  | 03 | 7570004 | This project will reconstruct the existing pavement and replace utilities and improve safety on State Route 570 from West limits of McComb East .9 miles in Pike county. | Pavement Improvement | 2009-07-30 | 2009-08-26 | 2011-05-17 | 2011-06-03 | 1804680 | 0.876 | 7570004
7177 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 7829002 | The city of Biloxi will construct a right turn lane and intersection and signal upgrades on Division Street at Bohn Avenue and the I-110 on-ramp. This project will improve traffic operations and safety at this intersection. | Safety/Traffic Management | 2010-04-15 | 2010-04-15 | 2010-12-31 | 2011-09-21 | 547360 | 0.013 | 7829002
7178 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 7861002 | The city of Southaven will improve safety and traffic operations by installing traffic signals at two intersections along Getwell Road. Getwell Road at Central Parkway and Getwell Road at Nail Road in Desoto County | Safety/Traffic Management | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-03-22 | 277916 | 0.022 | 7861002
7179 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 7862003 | The city of Olive Branch will widen Stateline Road from two to three lanes, between Alexander Road and Hacks Cross Road. This project will improve traffic operations and safety. | Pavement Widening | 2010-02-26 | 2010-02-26 | 2010-12-31 | 2012-01-09 | 692373 | 1.004 | 7862003
7180 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 7868005 | The city of Southaven will resurface Airways Boulevard from Hwy 302 to the Mississippi/Tennessee state line. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-01-12 | 645419 | 2.232 | 7868005
7181 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO |  | 01 | 7886001 | The city of Hernando will resurface Commerce Street from US 51 east to the Illinois Central Railroad Crossing. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-04 | 2010-02-04 | 2010-12-31 | 2011-03-24 | 196357 | 1.233 | 7886001
7182 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | DE SOTO | MEMPHIS (TN-AR) | 01 | 7904001 | The city of Olive Branch will install a traffic signal and make other improvements at the intersection of Pigeon Roost Road and Hwy 305. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2010-12-31 | 2011-05-12 | 215436 | 0.011 | 7904001
7183 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | CLAY |  | 01 | 7950001 | The city of West Point will resurface Lone Oak Drive from approximately East Oak Ridge Drive to Lone Oak Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-06-30 | 2010-12-03 | 306944 | 0.749 | 7950001
7184 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | BOLIVAR |  | 02 | 8032005 | The city of Cleveland will construct sidewalks along Court Street and North Street. This project will improve pedestrian access along these roads. | Safety/Traffic Management | 2010-02-11 | 2010-02-11 | 2010-12-31 | 2012-01-09 | 990183 | 0.606 | 8032005
7185 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JONES |  | 04 | 8063001 | The city of Laurel will replace a bridge on 5th Avenue over Gardiner Creek. | Bridge Replacement | 2010-02-19 | 2010-02-19 | 2011-06-30 | 2011-03-24 | 132829 | 0.013 | 8063001
7186 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JONES |  | 04 | 8077001 | The city of Laurel will install a traffic signal and make other improvements at the intersection of Beacon Street and Mason Street. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 2010-02-22 | 2010-02-22 | 2011-06-30 | 2011-03-24 | 151341 | 0.017 | 8077001
7187 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JONES |  | 04 | 8093001 | The city of Laurel will resurface 16th Avenue from King Street to Ferrill Street and will resurface 16th Ave from Ellisville Boulevard to Lee Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-03 | 2010-03-04 | 2010-04-16 | 2010-04-30 | 146087 | 0.123 | 8093001
7188 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE |  | 03 | 8134001 | The city of Meridian will replace a bridge over Sowashee Creek. This project will improve traffic safety. | Bridge Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2011-04-14 | 994222 | 0.014 | 8134001
7189 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LAUDERDALE |  | 03 | 8161001 | The city of Meridian will make safety upgrades, replace lighting, and other enhancements to the 26th Avenue viaduct. This project willextend the life of the structure and improve safety. | Pavement Improvement | 2010-02-10 | 2010-02-10 | 2010-12-31 | 2012-10-01 | 841872 | 0.149 | 8161001
7190 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LEE |  | 01 | 8193007 | The city of Tupelo will build a new bridge to extend Eason Boulevard over Town Creek and Kings Creek. | Bridge Improvement | 2009-09-15 | 2009-09-15 | 2011-06-30 | 2011-08-15 | 1227688 | 0.145 | 8193007
7191 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | FORREST | HATTIESBURG | 04 | 8762002 | The city of Hattiesburg will resurface W. Pine Street from Broadway Drive to Hwy 49S. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-04-30 | 2010-05-13 | 483078 | 1.113 | 8762002
7192 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | ATTALA |  | 02 | 8930001 | The city of Kosciusko will resurface Love Road from South Natchez Street to South Huntington Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2011-06-30 | 2011-05-19 | 201425 | 0.719 | 8930001
7193 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | PASCAGOULA-MOSS POINT | 04 | 8943002 | The city of Pascagoula will replace a bridge and resurface the pavement on Old Mobile Highway between 14th Street and Chicot Street. This project will make the road smoother and extend the life of the | Pavement Improvement | 2010-02-19 | 2010-02-19 | 2010-12-31 | 2011-05-12 | 816189 | 0.794 | 8943002
7194 | MISSISSIPPI | Completed | C250 | Highway Infrastructure Investment Grant | MISSISSIPPI | MARSHALL |  | 01 | 9025100 | This project will add pavement to 2.1 miles of the North Holly Springs Industrial Bypass Road just north of Holly Springs. This project will make the road smoother and extend the life of the pavement. | New Construction | 2009-09-28 | 2009-09-28 | 2010-06-16 | 2011-04-20 | 1637100 | 2.100 | 9025100
7195 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9044001 | The city of Biloxi will install street lighting along MS Hwy 67 from the Tchoutacabouffa River north to the City Limits. This project will improve traffic operations and safety. | Safety/Traffic Management | 2010-02-11 | 2010-02-11 | 2010-12-31 | 2011-05-12 | 249486 | 0.906 | 9044001
7196 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | BILOXI-GULFPORT | 04 | 9064008 | The county of Jackson will add a right turn lane and make sidewalk improvements on Beachview Rd and Old Spanish Trail; and install traffic signals on Old Spanish Trail at Beachview Drive and at Hansha | Safety/Traffic Management | 2010-02-26 | 2010-02-26 | 2010-12-31 | 2011-07-11 | 522479 | 0.035 | 9064008
7197 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9082002 | The city of Long Beach will replace a bridge on Klondyke Road, which crosses Canal No. 1. This project will improve traffic safety. | Bridge Replacement | 2010-02-19 | 2010-02-19 | 2010-12-31 | 2011-07-08 | 599524 | 0.013 | 9082002
7198 | MISSISSIPPI | Underway | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9082003 | The city of Long Beach will install traffic signals and make other intersection improvements at the intersection of Klondyke Road and 28th Street. This project will improve traffic operations and safety | Safety/Traffic Management | 2010-03-30 | 2010-03-30 | 2011-01-30 |  | 461588 | 0.013 | 9082003
7199 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HANCOCK | BILOXI-GULFPORT | 04 | 9137002 | The county of Hancock will resurface and make other repairs to Kiln-Waveland Cutoff Road from US 90 to Hwy 603. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-09-01 | 2010-09-07 | 2011-01-31 | 2011-06-08 | 747106 | 1.431 | 9137002
7200 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9183001 | The city of D'Iberville will replace a bridge over the bayou on Gorenflo Road, south of Borries Street. This project will improve traffic safety. | Bridge Replacement | 2010-03-30 | 2010-03-30 | 2010-12-31 | 2011-05-12 | 430420 | 0.013 | 9183001
7201 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | PASCAGOULA-MOSS POINT | 04 | 9192001 | The city of Gautier will install a traffic signal at the intersection of Ladnier Road and Old Spanish Trail. This project will improve traffic operations at this intersection. | Safety/Traffic Management | 2010-02-26 | 2010-02-26 | 2010-12-31 | 2011-01-10 | 131030 | 0.009 | 9192001
7202 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9371011 | The city of Gulfport will replace a bridge over Fritz Creek on Old Lorraine Road. This project will improve traffic safety. | Bridge Improvement | 2010-02-19 | 2010-02-19 | 2010-12-31 | 2011-05-12 | 171655 | 0.058 | 9371011
7203 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON | BILOXI-GULFPORT | 04 | 9375005 | The city of Biloxi will resurface Beauvoir Road, from US 90 to Pass Road. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-05-03 | 2010-05-11 | 2010-06-16 | 2010-08-06 | 181524 | 0.744 | 9375005
7204 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | JACKSON | PASCAGOULA-MOSS POINT | 04 | 9393001 | The city of Moss Point will resurface Amoco Road from Hwy 63 west 1000 feet. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2011-03-01 | 2011-03-24 | 2011-04-07 | 2011-04-27 | 84500 | 1.191 | 9393001
7205 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | LINCOLN |  | 03 | 9518003 | The city of Brookhaven will resurface Brookway Boulevard beginning at the east end of State Maintenance just east of I-55 and then east to US Hwy 51. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-05 | 2010-02-05 | 2010-06-30 | 2011-05-18 | 342652 | 0.990 | 9518003
7206 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | MONROE |  | 01 | 9569003 | The city of Amory will resurface Waterway Drive from Hwy 278 to 5th Ave. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-06-30 | 2010-12-16 | 249621 | 0.832 | 9569003
7207 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | PRENTISS |  | 01 | 9629002 | The city of Booneville will install a traffic signal and make other improvements at the intersection along N. 2nd Street at Hwy 4, College Street, Veterans (George E. Allen Drive) and Cunningham Boule | Safety/Traffic Management | 2010-03-01 | 2010-03-01 | 2010-10-01 | 2011-11-09 | 437789 | 0.110 | 9629002
7208 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WASHINGTON |  | 02 | 9670003 | The city of Leland will resurface North Broad Street from 8th Street to the City Limits. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-06-30 | 2011-03-16 | 158583 | 0.566 | 9670003
7209 | MISSISSIPPI | Completed | C200 | Highway Infrastructure Investment Grant | MISSISSIPPI | WINSTON |  | 01 | 9674008 | The city of Louisville will resurface South Church Street from Hwy 15 to Armstrong Street. This project will make the road smoother and extend the life of the pavement. | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2011-06-30 | 2010-12-17 | 267133 | 1.553 | 9674008
7210 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | RANKIN, HINDS, MADISON | JACKSON | 03 | 9999510 | This project takes place in the following three counties: Hinds, Madison, and Rankin. This project will resurface and extend the lives of Louis Wilson Drive in Brandon from US Highway 80 to MS Hwy 18; | Pavement Improvement | 2010-08-05 | 2010-08-19 | 2010-10-29 | 2010-11-09 | 742311 | 0.000 | 9999510
7211 | MISSISSIPPI | Completed | C230 | Highway Infrastructure Investment Grant | MISSISSIPPI | HARRISON, JACKSON | BILOXI-GULFPORT | 04 | 9999610 | This project will resurface and extend the life of the pavement on various sites in Jackson and Harrison county. City of Gulfport - Mill & Overlay 14th St from 27th Ave to 28th Ave & from 21st Ave to | Pavement Improvement | 2010-11-08 | 2010-11-09 | 2011-07-15 | 2011-09-14 | 1001409 |  | 9999610
7212 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CASS |  | 04 | 0021032 | This project consist of a thin lift asphalt overlay from Commercial Street to Route ZZ in Cass and Johnson counties | Pavement Improvement | 2009-09-08 | 2009-07-29 | 2009-12-01 | 2009-08-19 | 546942.61 | 14.656 | 0021032
7213 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | LACLEDE |  | 04 | 0052029 | This project consists of constucting a five lane roadway on Route 5, Laclede County to improve safety and improve capacity. | Pavement Widening | 2010-03-01 | 2010-03-01 | 2010-11-15 | 2010-11-12 | 2709120 | 2.250 | 0052029
7214 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | CAMDEN |  | 04 | 0053053 | This project consist of widening Route 5 to three lanes through Sunrise Beach in Camden county | Pavement Widening | 2009-06-15 | 2009-06-15 | 2010-05-28 | 2010-08-26 | 835469.39 | 0.900 | 0053053
7215 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PUTNAM |  | 06 | 0054025 | This project consist of resurfacing roadway from Iowa State line to Route 136 - Putnam county | Pavement Improvement | 2010-02-08 | 2010-04-01 | 2010-11-01 | 2010-06-11 | 490711.37 | 8.435 | 0054025
7216 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BENTON |  | 04 | 0072039 | This project consist of rehabilitation of bridges on Route 7 over Truman Lake (Osage Arm Bridge and Grand River Arm Bridge) in Benton county | Bridge Improvement | 2009-06-15 | 2009-06-18 | 2010-10-15 | 2010-10-26 | 5153860.63 | 2.000 | 0072039
7217 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | 0091014 | This project consists of rehabilitation of the Heart of America bridge over the Missouri River, including addition of a bicycle and pedistrian facility, on Route 9 in Clay county. | Pavement Improvement | 2010-02-01 | 2010-06-07 | 2010-12-01 | 2010-10-28 | 455549.99 | 0.400 | 0091014
7218 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE | KANSAS CITY (KS)-MO | 06 | 0091015 | This project consists of interchange improvements, building ramps and roundabout from SB Rte. 9 to Briarcliff in Clay county. | Pavement Improvement | 2010-01-04 | 2010-01-25 | 2011-12-01 | 2011-10-14 | 2500000 | 0.941 | 0091015
7219 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE | KANSAS CITY (KS)-MO | 06 | 0091016 | This project consists of a bridge replacement on Route 9 over the White Aloe Branch in Platte county south of Route FF. | Bridge Replacement | 2010-01-04 | 2010-06-09 | 2011-12-01 | 2011-05-16 | 105000 | 0.113 | 0091016
7220 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | RAY |  | 04 | 0134027 | This project consist of resurfacing roadway from the Caldwell county Line to Route 10 at the City of Richmond - Ray county | Pavement Improvement | 2010-03-08 | 2010-08-17 | 2010-11-01 | 2010-12-20 | 1149943.86 | 18.597 | 0134027
7221 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CALDWELL |  | 06 | 0134028 | This project consist of replacing bridge deck over Route 36 in Hamilton - Caldwell county | Bridge Replacement | 2010-03-08 | 2010-06-02 | 2010-08-01 | 2010-07-30 | 596676.92 | 0.081 | 0134028
7222 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MONROE |  | 09 | 0151011 | This project consist of pavement and shoulder improvements from Route 154 north junction to 1.1 miles north of Route 22 in Monroe and Audrain counties | Pavement Improvement | 2009-05-18 | 2009-09-15 | 2009-12-01 | 2009-11-30 | 2433862.06 | 24.572 | 0151011
7223 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | AUDRAIN |  | 09 | 0151012 | This project consist of pavement improvements from 1.1 miles north of Route 22 to 0.2 miles north of Route 54 in Audrain county | Pavement Improvement | 2009-07-06 | 2009-08-18 | 2009-12-01 | 2009-10-17 | 796130.05 | 5.038 | 0151012
7224 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | TEXAS |  | 08 | 0171009 | This project consist of a thin lift asphalt overlay from Route 106 in Summersville to Route 60 in Mt. View in Texas and Howell counties | Pavement Improvement | 2009-06-08 | 2009-07-09 | 2009-12-01 | 2009-07-27 | 564176.21 | 13.251 | 0171009
7225 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | HOWELL |  | 08 | 0171010 | This project consist of a thin lift asphalt overlay from Route 60 in Mt. View to Route 160 in Howel county | Pavement Improvement | 2009-06-08 | 2009-07-08 | 2009-12-01 | 2009-09-15 | 860642.49 | 19.349 | 0171010
7226 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MILLER |  | 09 | 0172010 | This project consist of replacement of bridge over the Osage River one mile east of Tuscumbia in Miller county, project involves bridge J0719 | Bridge Replacement | 2009-02-17 | 2009-02-23 | 2010-10-01 | 2010-11-05 | 8291095.03 | 0.591 | 0172010
7227 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MILLER |  | 09 | 0172011 | This project consist of a thin lift asphalt overlay from Route 54 to Brush Creek in Cole and Miller counties | Pavement Improvement | 2009-06-08 | 2009-06-12 | 2009-12-01 | 2009-07-23 | 831658.73 | 19.266 | 0172011
7228 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | SHANNON |  | 08 | 0191008 | This project consist of roadway resurfacing on Route 19 from Route 106 to .4 miles north of Route F in Eminence and on Route 106 from Route 19 to 1.3 miles west of Route 19 - Shannon county | Pavement Improvement | 2010-02-08 | 2010-04-05 | 2010-12-01 | 2010-11-10 | 149724.18 | 2.230 | 0191008
7229 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | CRAWFORD |  | 09 | 0192017 | This project consist of resurfacing roadway from .6 miles north of Route 8 to Route 19 South in Steelville - Crawford county | Pavement Improvement | 2010-03-08 | 2010-07-14 | 2010-12-01 | 2010-07-30 | 111960.35 | 1.200 | 0192017
7230 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | MONTGOMERY |  | 09 | 0194012 | This project consists of asphalt resurfacing from near Route B (just north of Montgomery City) to 1.7 miles south of Route I-70. | Pavement Improvement | 2010-01-04 | 2010-04-15 | 2010-12-01 | 2010-07-29 | 2140300 | 8.792 | 0194012
7231 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WASHINGTON |  | 08 | 0211018 | This project consist of pavement improvements from 1.7 miles south of Route 8 in Potosi to Route N in Iron county | Pavement Improvement | 2009-06-08 | 2009-06-24 | 2009-11-01 | 2010-05-12 | 2264378.25 | 21.247 | 0211018
7232 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MARION |  | 09 | 0243033 | This project consists of bridge rehabilitation over the North fabius river .9 miles north of Route 6 near Taylor. | Bridge Improvement | 2010-03-08 | 2010-04-05 | 2010-12-01 | 2010-10-28 | 1843000 | 0.200 | 0243033
7233 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MARIES |  | 09 | 0281009 | This project consist of a thin lift asphalt overlay from Route 63 to Dixon in Maries and Pulaski counties | Pavement Improvement | 2009-04-06 | 2009-06-09 | 2009-12-01 | 2009-07-02 | 815732.51 | 16.964 | 0281009
7234 | MISSOURI | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | 0291111 | This project consists of extensive pavement repair, hot in place recycle and asphalt resurfacing from Rte. 273 near Platte City for 18 miles (North and South) to Vivion Road, new rumble strip and pavement marking throughout the project. | Pavement Improvement | 2009-05-04 | 2009-05-18 | 2009-11-01 | 2009-09-29 | 11834247 | 34.857 | 0291111
7235 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | 0292155 | This project consist of resurfacing roadway from Route 169 (Belt Highway) to Route 371 (22nd Street) in St. Joseph - Buchanan county | Pavement Improvement | 2010-03-18 | 2010-04-01 | 2010-11-01 | 2010-04-19 | 373642.1 | 1.773 | 0292155
7236 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | 0311005 | This project consist of a thin lift asphalt overlay from Route 36 to Route 169 in Buchanan county | Pavement Improvement | 2009-07-06 | 2009-10-28 | 2010-10-01 | 2009-11-24 | 308549.72 | 6.222 | 0311005
7237 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | DENT |  | 08 | 0322017 | This project consist of resurfacing roadway from .2 mile west of Route 72 to 2.5 miles east of Route 72 in the City of Salem - Dent county | Pavement Improvement | 2010-03-08 | 2010-03-23 | 2010-12-01 | 2010-04-28 | 488236.2 | 2.700 | 0322017
7238 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | ST FRANCOIS |  | 08 | 0323019 | This project consist of rehabilitation of the existing pavement on Route 32 (Karsh Blvd) from Route OO to Route 67 in the City of Farmington - St. Francois county | Pavement Improvement | 2010-03-08 | 2010-04-26 | 2010-12-01 | 2010-12-02 | 1021279 | 2.823 | 0323019
7239 | MISSOURI | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | WAYNE |  | 08 | 0341035 | The project consists of adding shoulders, repaving, and several new alignments between Piedmont and Patterson. The alignment will change several curves and eliminate at least one 's' curve. A three | Pavement Widening | 2008-11-17 | 2008-11-17 | 2011-12-01 |  | 12735200 | 13.349 | 0341035
7240 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BOLLINGER |  | 08 | 0341036 | This project consist of resurfacing roadway in Marble Hill - Bollinger county | Pavement Improvement | 2010-03-08 | 2010-06-21 | 2010-09-01 | 2010-12-02 | 513735.61 | 2.589 | 0341036
7241 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CLINTON |  | 06 | 0352082 | This project consists of asphalt resurfacing on I-35 north of Shoal Creek to north of Route 116 near Lathrop. | Pavement Improvement | 2009-02-17 | 2009-02-17 | 2009-12-15 | 2010-08-30 | 14754615 | 7.057 | 0352082
7242 | MISSOURI | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | LINN |  | 06 | 0362077 | This project consist of a thin lift asphalt overlay from Route 36 to Route 11 in Linn county | Pavement Improvement | 2009-06-08 | 2009-08-06 | 2009-12-01 | 2009-09-09 | 197445.03 | 1.772 | 0362077
7243 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LAWRENCE |  | 07 | 0391022 | This project consist of a thin lift asphalt overlay from Route 60 to 1.5 miles north of Route 248 in Barry and Lawrence county | Pavement Improvement | 2009-04-06 | 2009-04-14 | 2009-12-01 | 2009-11-20 | 475300.14 | 12.113 | 0391022
7244 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CARROLL |  | 06 | 0411003 | This project consist of pavement and shoulder improvements from Route 24 to Route 240 in Saline and Carroll counties | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-12-01 | 2009-06-30 | 1575664.74 | 17.680 | 0411003
7245 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | SALINE |  | 04 | 0411004 | This project consist of a thin lift asphalt overlay from Route 240 to Route TT in Saline county | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-12-01 | 2009-05-26 | 511733.26 | 10.268 | 0411004
7246 | MISSOURI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | PHELPS |  | 08 | 0442223 | This project consist of major pavement rehabilitation/reconstruction on westbound lanes from Business Loop 44 (Rolla) to Sugartree Road Interchange in Phelps county | Pavement Improvement | 2009-07-06 | 2009-09-08 | 2009-12-01 | 2009-12-01 | 10378900.69 | 8.213 | 0442223
7247 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PULASKI |  | 04 | 0442224 | This project consist of an asphalt mill and fill from SP 44 to Route H/I-44 in St. Robert/Waynesville in Pulaski county | Pavement Improvement | 2009-07-06 | 2009-10-16 | 2009-12-01 | 2009-11-09 | 911377.3 | 5.620 | 0442224
7248 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CRAWFORD |  | 09 | 0443100 | This project consist of pavement rehabilitation on westbound lanes from 0.6 miles west of Route H to the Phelps County line in Crawford county | Pavement Improvement | 2009-06-08 | 2009-09-21 | 2009-12-01 | 2009-11-14 | 888525.09 | 12.507 | 0443100
7249 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN |  | 09 | 0443101 | This project consist of rebuilding of pavement from Viaduct Street to Route 100 West in Franklin county | Pavement Widening | 2009-08-10 | 2009-08-21 | 2010-10-01 | 2010-11-02 | 16945578.18 | 5.072 | 0443101
7250 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | 0451025 | This project consist of a thin lift asphalt overlay from Route 273 to Spur 45 south in Platte county | Pavement Improvement | 2009-06-08 | 2009-10-05 | 2009-12-01 | 2009-10-21 | 507200 | 11.890 | 0451025
7251 | MISSOURI | Completed | C240,C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 04 | 0501042 | This project will complete a diamond interchange at Route 50 and Bynum Road in Jackson county. | New Construction | 2010-03-29 | 2010-03-29 | 2010-12-01 | 2010-12-01 | 4157306.95 | 0.100 | 0501042
7252 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | COLE |  | 04 | 0503078 | This project consist of pavement treatment on westbound lanes from Truman Blvd. To west of Truman Blvd. - Cole county | Pavement Improvement | 2010-03-08 | 2010-04-13 | 2010-12-01 | 2010-05-03 | 328862.64 | 1.539 | 0503078
7253 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PERRY |  | 08 | 0512016 | This project consist of pavement improvements from I-55 to Route 72 in Perry and Bollinger counties | Pavement Improvement | 2009-06-08 | 2009-06-24 | 2009-11-01 | 2010-05-04 | 1766282.57 | 16.297 | 0512016
7254 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | HENRY |  | 04 | 0521007 | This project consist of a thin lift asphalt overlay from the St. Clair county line to Route 13 in Henry county | Pavement Improvement | 2009-06-08 | 2009-07-29 | 2009-12-01 | 2009-10-30 | 566857.15 | 15.143 | 0521007
7255 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BATES |  | 04 | 0521008 | This project consist of a thin lift asphalt overlay from Route BB to 1.6 miles east of Route W in Bates county | Pavement Improvement | 2009-06-08 | 2009-07-29 | 2009-12-01 | 2009-11-30 | 194615.17 | 5.268 | 0521008
7256 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST CLAIR |  | 04 | 0521009 | This project consist of a thin lift asphalt overlay from 1.0 miles west of Route P to 1.8 miles east of Route A in St. Clair county | Pavement Improvement | 2009-06-08 | 2009-07-29 | 2009-12-01 | 2009-11-30 | 213769.83 | 4.741 | 0521009
7257 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | COLE |  | 04 | 0543155 | This project consist of pavement improvements from the Missouri River Bridge to .25 miles west of Stadium Blvd. in Jefferson City. Project includes ramps at Route 50-54-63 interchange (tri- level) - Cole county | Pavement Improvement | 2010-03-08 | 2010-04-13 | 2010-12-01 | 2010-05-24 | 935730.6 | 3.300 | 0543155
7258 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CALLOWAY |  | 09 | 0543156 | This project consist of resurfacing westbound lanes from Holts Summit to the Missouri River Bridge in Jefferson City - Callaway county | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2010-12-01 | 2010-11-29 | 1219596.6 | 5.184 | 0543156
7259 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | NEW MADRID |  | 08 | 0551134 | This project consist of pavement rehabilitation of north and south bound lanes from Route 84 to Scott county in New Madrid county | Pavement Improvement | 2009-02-17 | 2009-05-12 | 2010-10-31 | 2010-10-30 | 15743400 | 46.834 | 0551134
7260 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PEMISCOT |  | 08 | 0551135 | This project consist of pavement rehabilitation on the northbound lanes from the Arkansas state line to I-155 in Pemiscot county | Pavement Improvement | 2009-06-08 | 2009-06-24 | 2010-07-30 | 2010-07-28 | 16220964 | 15.282 | 0551135
7261 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | NEW MADRID |  | 08 | 0551136 | The construction of a new Welcome Center on I-55 at Marston | Transportation Enhancements | 2009-01-23 | 2009-01-23 | 2011-11-15 | 2011-07-05 | 5768950 | 0.300 | 0551136
7262 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON |  | 03 | 0552086 | This project consists of adding lands and widening or rplacing two bridges on Route 55 between north of Route M and north of Route Z in Jefferson county. | Pavement Widening | 2010-03-08 | 2010-03-08 | 2011-12-01 | 2011-05-13 | 13539119.84 | 4.509 | 0552086
7263 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ATCHISON |  | 06 | 0591025 | This project consist of a thin lift asphalt overlay from the Iowa state line to Route 136 in Atchison county | Pavement Improvement | 2009-06-08 | 2009-06-29 | 2009-12-01 | 2009-09-30 | 713109.87 | 9.908 | 0591025
7264 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARRY |  | 07 | 0601030 | The jobs combine to provide new surface and alternating passing lane improvements for 22 plus miles of a 25 mile stretch of Route 60 in Barry, Lawrence, Christian, and Greene Counties. As designed, J | Pavement Improvement | 2009-02-17 | 2009-07-08 | 2009-11-01 | 2010-11-20 | 222135.57 | 17.617 | 0601030
7265 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARRY |  | 07 | 0601031 | The jobs combine to provide new surface and alternating passing lane improvements for 22 plus miles of a 25 mile stretch of Route 60 in Barry, Lawrence, Christian, and Greene Counties. As designed, J | Pavement Improvement | 2009-02-17 | 2009-07-08 | 2009-11-01 | 2010-11-20 | 8392901.26 | 15.894 | 0601031
7266 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | 0602067 | This project consists of improvements at the James River Freeway and National Avenue interchange. | Pavement Widening | 2009-09-23 | 2009-09-23 | 2011-12-01 | 2010-09-23 | 4569532 | 0.474 | 0602067
7267 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CARTER |  | 08 | 0603095 | This project consist of ADA sidewalk improvements on Business 60 from Oliver Street to Alexander Street in Van Buren, 0.98 miles. | Transportation Enhancements | 2010-01-04 | 2010-03-01 | 2010-05-14 | 2010-03-18 | 101771 | 0.098 | 0603095
7268 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | TEXAS |  | 08 | 0603096 | This project consist of resurfacing roadway from Route 181 to Route 60 in Cabool - Texas county | Pavement Improvement | 2010-02-08 | 2010-09-17 | 2010-12-01 | 2010-09-17 | 147400 | 2.666 | 0603096
7269 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LEWIS |  | 09 | 0614137 | This project consist of a thin lift asphalt overlay from Route 961 to Route B in LaGrange - Lewis county | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-11-01 | 2010-09-15 | 93900 | 1.776 | 0614137
7270 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MISSISSIPPI |  | 08 | 0621022 | This project consist of a thin lift asphalt overlay from Route B in Bertrand to the City of Charleston in Mississippi county | Pavement Improvement | 2009-06-08 | 2009-06-16 | 2009-12-01 | 2009-07-27 | 325653.65 | 5.856 | 0621022
7271 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | HOWELL |  | 08 | 0631029 | This project consist of an asphalt mill and fill from Route 63 North to Broadway in West Plains in Howell county | Pavement Improvement | 2009-07-06 | 2009-10-28 | 2009-12-01 | 2009-11-23 | 526470.69 | 1.801 | 0631029
7272 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | ADAIR |  | 09 | 0634066 | This is the first in a series of two projects to construct an Alternate Route 63 around Kirksville Missouri. This project runs from the North edge of Kirksville to Route 6, just east of Kirksville. | New Construction | 2009-08-03 | 2009-08-12 | 2011-12-01 | 2011-11-23 | 17491350.38 | 8.500 | 0634066
7273 | MISSOURI | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | 0652063 | This project consist of widening route to six lanes from Business 65 (Chestnut Expressway) to Route D (Sunshine Street) in Greene County | Pavement Widening | 2009-08-24 | 2009-08-24 | 2011-12-01 |  | 8475485.52 | 2.027 | 0652063
7274 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | 0652064 | This project consist of widening route to six lanes from Route D (Sunshine Street) to Route 60 (James River Freeway) in Greene County | Pavement Widening | 2009-08-24 | 2009-08-24 | 2011-12-01 | 2011-09-02 | 2985865.5 | 3.466 | 0652064
7275 | MISSOURI | Underway | C240,C230 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | 0652065 | This project consist of widening route to six lanes from Business 65 (Chestnut Expressway) to Route D (Sunshine Street) in Greene County | Pavement Widening | 2009-08-24 | 2009-08-24 | 2011-12-01 |  | 9701900 | 2.027 | 0652065
7276 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | DALLAS |  | 04 | 0652066 | This project consist of adding a center turn lane for 1.0 mile north of Route 32 in Dallas county | Pavement Widening | 2010-01-04 | 2010-09-21 | 2010-12-01 | 2010-10-28 | 1016100 | 1.000 | 0652066
7277 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BENTON |  | 04 | 0653088 | This project consist of rehabilitation of bridge on Route 65 over the Osge River near Warsaw in Benton county | Bridge Improvement | 2009-06-15 | 2009-06-18 | 2010-10-15 | 2010-10-26 | 1386858.25 | 0.144 | 0653088
7278 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | JASPER |  | 07 | 0661017 | This project consist of resurfacing disconnected section from Geneva Avenue to Duquesne Road in Joplin - Jasper county | Pavement Improvement | 2010-03-08 | 2010-10-27 | 2010-12-01 | 2010-12-07 | 226846.87 | 0.887 | 0661017
7279 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUTLER |  | 08 | 0671018 | This project consist of intersection improvements at Business Route 67, OR 67 and Industrial Park Bypass - Butler county | Pavement Improvement | 2010-03-08 | 2010-06-03 | 2010-11-01 | 2010-08-17 | 671400.58 | 0.200 | 0671018
7280 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS |  | 01 | 0673109 | This project consists of ADA sidwalk improvements from I-270 to Old St. Charles Rd and on Route AC from Route 67 (Lindbergh) to I-270 in St. Louis county | Transportation Enhancements | 2009-09-08 | 2009-09-28 | 2010-05-01 | 2010-06-23 | 1912955.05 | 7.500 | 0673109
7281 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | 0691013 | This project consist of a thin lift asphalt overlay from the Clinton county line to Route 92 in Clay county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-11-25 | 328587.39 | 6.017 | 0691013
7282 | MISSOURI | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON |  | 06 | 0701179 | This project consist of constructing a new half diamond interchange at Route 40 - I435, replacement of Blue Ridge cut off bridge over I-70, add lanes to I-70, and modification to some ramps in Jackson county | New Construction | 2009-10-07 | 2009-10-07 | 2012-03-01 |  | 34077640.17 | 5.437 | 0701179
7283 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON |  | 04 | 0701190 | This project consist of rehabilitating eastbound bridges from Troost to Route 40 in Jackson county | Bridge Improvement | 2010-03-08 | 2010-03-08 | 2011-12-01 | 2011-08-23 | 6673400 | 26.000 | 0701190
7284 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LAFAYETTE |  | 04 | 0702101 | This project consists of resurfacing of the roadway and shoulders on eastbound and westbound Interstate 70 from the Lafayette County line to Odessa. | Pavement Improvement | 2009-05-04 | 2009-06-15 | 2009-12-01 | 2010-03-01 | 7178338.73 | 20.230 | 0702101
7285 | MISSOURI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | COOPER |  | 06 | 0703217 | This project consist of pavement improvements on the westbound lanes from 0.3 miles east of Route B to the Saline county line in Cooper county | Pavement Improvement | 2009-04-06 | 2009-06-12 | 2009-12-01 | 2009-11-12 | 8262515.78 | 17.100 | 0703217
7286 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | 0703218 | This project consist of a thin lift asphalt overlay from Route 63 north connector to Route Z in Boone county | Pavement Improvement | 2009-06-08 | 2009-08-10 | 2009-12-01 | 2009-09-30 | 283369.62 | 5.340 | 0703218
7287 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | 0703220 | This project consist of a thin lift resurfacing from Route E west to the end of state maintenance in the City of Columbia - Boone county | Pavement Improvement | 2010-03-08 | 2010-04-06 | 2010-12-01 | 2010-07-16 | 142257.35 | 2.000 | 0703220
7288 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY |  | 01 | 0705314 | This project consist of pavement improvements from I-44/I-55 to Washington Ave. in St. Louis City | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2009-12-01 | 2010-06-18 | 5092700 | 0.570 | 0705314
7289 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARTON |  | 04 | 0712061 | This project consists of constructing a new interchange at Route 71 and 126. Work includes grading, asphalt pavement and new bridge. | New Construction | 2009-06-22 | 2009-06-22 | 2010-10-01 | 2010-07-07 | 4643989 | 3.805 | 0712061
7290 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARTON |  | 04 | 0712062 | This project consists of constructing a new interchange at Route 71 and DD/EE. Work includes grading, asphalt pavement and new bridge. | New Construction | 2009-07-06 | 2009-07-13 | 2010-10-01 | 2010-08-09 | 3667300 | 3.059 | 0712062
7291 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARTON |  | 04 | 0712063 | This project consists of constructing a new interchange at Route 71 and V/C. Work includes grading, asphalt pavement and new bridge. | New Construction | 2009-07-06 | 2009-07-13 | 2010-10-01 | 2010-07-21 | 3744287 | 6.200 | 0712063
7292 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BATES |  | 04 | 0713045 | This project consists of the construction of an overpass with on and off ramps at the junction of Highway 71 and Highway 52 East. Two other bridges will be built as part of this project. One will re | New Construction | 2009-07-06 | 2009-08-18 | 2010-10-01 | 2010-09-30 | 5063473.34 | 2.904 | 0713045
7293 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | MADISON |  | 08 | 0722020 | This project consist of resurfacing roadway through the City of Fredricktown - Madison county | Pavement Improvement | 2010-03-08 | 2010-04-26 | 2010-12-01 | 2010-12-02 | 481500 | 1.995 | 0722020
7294 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | TANEY |  | 07 | 0761014 | This project consist of ADA sidewalk improvements from Roark Valley Road to Gretna (Branson) in Taney county | Transportation Enhancements | 2009-07-27 | 2009-08-19 | 2009-12-01 | 2009-11-19 | 675976.35 | 2.864 | 0761014
7295 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | TANEY |  | 07 | 0761015 | This project consists of construction of a roundabout and new bridge over Lake Taneycomo. | New Bridge Construction | 2009-06-23 | 2009-06-23 | 2011-12-01 | 2011-12-16 | 8943704.39 | 0.210 | 0761015
7296 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | TANEY |  | 07 | 0761017 | This project consist of ADA ramps from Shepherd of the Hills Expressway to Gretna Road I the City of Branson - Taney county | Transportation Enhancements | 2010-10-04 | 2010-11-01 | 2011-05-26 | 2011-05-09 | 39419.33 | 1.233 | 0761017
7297 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BENTON |  | 04 | 0831001 | This project consist of rehabilitation of bridge on Route 83 over Truman Lake near Mockingbird Road in Benton county | Bridge Improvement | 2009-06-15 | 2009-06-18 | 2010-10-15 | 2010-10-26 | 2364845.86 | 0.500 | 0831001
7298 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | NEWTON |  | 07 | 0861007 | This project consist of improvements on existing pavement and shoulders with the addition of rumble strips from Route P to 0.2 miles west of Route 71 in Newton county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-11-02 | 802960.38 | 9.952 | 0861007
7299 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BARRY |  | 07 | 0861008 | This project consist of improvements on existing pavement and shoulders with the addition of rumble strips from Route F to 2.9 miles east of Route H in Barry county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-11-02 | 922994.44 | 11.596 | 0861008
7300 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PULASKI |  | 04 | 1037004 | This project consist of roadway resurfacing on Route 133 from Route 7 to the railroad tracks and resurfacing Route 7 from Route 133 to Route A in Richland - Pulaski county | Pavement Improvement | 2010-03-08 | 2010-09-30 | 2010-12-01 | 2010-09-30 | 100380.81 | 1.303 | 1037004
7301 | MISSOURI | Completed | C250,C200 | Highway Infrastructure Investment Grant | MISSOURI | WEBSTER |  | 04 | 1045005 | This project consist of a thin lift asphalt overlay from Route 60 to south of railroad in Webster county | Pavement Improvement | 2009-06-08 | 2009-09-09 | 2009-12-01 | 2009-10-10 | 32417.41 | 1.190 | 1045005
7302 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | RIPLEY |  | 08 | 1098007 | This project consist of resurfacing roadway from Route 160 to Route E in Doniphan - Ripley county | Pavement Improvement | 2010-03-08 | 2010-04-21 | 2010-07-01 | 2010-06-01 | 336848.84 | 4.064 | 1098007
7303 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CAPE GIRARDEAU |  | 08 | 1130006 | This project consist of rehabilitating pavement surface from I-55 to Kingshighway in Cape Girardeau county | Pavement Improvement | 2009-07-06 | 2009-07-24 | 2009-08-14 | 2009-09-04 | 520520.09 | 1.703 | 1130006
7304 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUTLER |  | 08 | 1200003 | This project consist of a thin lift asphalt overlay from County Road 462 to Route 67 in Butler county | Pavement Improvement | 2009-04-06 | 2009-06-09 | 2009-12-01 | 2009-06-29 | 362742.14 | 8.183 | 1200003
7305 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RIPLEY |  | 08 | 1206005 | This project consist of a thin lift asphalt overlay from Route V west of Doniphan to Route 160 in Doniphan in Ripley county | Pavement Improvement | 2009-04-06 | 2009-08-31 | 2009-12-01 | 2009-10-15 | 762576.55 | 14.548 | 1206005
7306 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUTLER |  | 08 | 1221003 | This project consist of a thin lift asphalt overlay from Route WW in Poplar Bluff to Route 158 in Butler county | Pavement Improvement | 2009-04-06 | 2009-06-09 | 2009-12-01 | 2009-06-29 | 267090.49 | 5.628 | 1221003
7307 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CAPE GIRARDEAU |  | 08 | 1271004 | This project consist of resurfacing roadway from the Jackson city limits to Route 61 - Cape Girardeau county | Pavement Improvement | 2010-03-08 | 2010-06-21 | 2010-09-01 | 2010-08-27 | 392852.67 | 2.277 | 1271004
7308 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CAPE GIRARDEAU |  | 08 | 1277002 | This project consist of resurfacing and improving shoulders from Lasalle Ave to Lexington Ave. in Cape Girardeau county | Pavement Improvement | 2009-11-09 | 2010-03-15 | 2010-12-01 | 2011-02-22 | 2357519.01 | 4.200 | 1277002
7309 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PEMISCOT |  | 08 | 1286003 | This project consist of a thin lift asphalt overlay from Route 164 to the Arkansas state line in Pemiscot county | Pavement Improvement | 2009-05-08 | 2009-05-08 | 2009-12-01 | 2009-06-05 | 364909.97 | 6.465 | 1286003
7310 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PEMISCOT |  | 08 | 1321002 | This project consist of a thin lift asphalt overlay from Route U to Route 164 in Pemiscot county | Pavement Improvement | 2009-05-08 | 2009-05-08 | 2009-12-01 | 2009-06-05 | 467598.93 | 6.091 | 1321002
7311 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | HOLT |  | 06 | 1324003 | This project consist of a thin lift asphalt overlay on Spur 113 in Holt County from Route 113 to Route A and on Route A in Nodaway County from Spur 113 to Route 71 | Pavement Improvement | 2009-07-06 | 2009-08-24 | 2010-07-01 | 2009-09-24 | 680396.98 | 11.702 | 1324003
7312 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ATCHISON |  | 06 | 1361059 | This project involves painting, redeck and bridge repairs of the Missouri River brige at Brownville, NE | Bridge Improvement | 2009-08-31 | 2009-08-31 | 2011-12-01 | 2012-08-03 | 4868280 | 0.600 | 1361059
7313 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PUTNAM |  | 06 | 1362025 | This project consist of a thin lift asphalt overlay from Route 63 to Route N in Schuyler and Putnam counties | Pavement Improvement | 2009-04-06 | 2009-04-10 | 2009-12-01 | 2009-05-06 | 842800.72 | 8.334 | 1362025
7314 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PUTNAM |  | 06 | 1362026 | This project consist of resurfacing roadway from Route 5 to Route N - Putnam county | Pavement Improvement | 2010-02-08 | 2010-04-01 | 2010-11-01 | 2010-06-11 | 1024836.77 | 17.839 | 1362026
7315 | MISSOURI | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS |  | 02 | 1411029 | This project consist of right of way acquisition to relocate and construct Route 141 from Route 40 to Route 340 (Olive Blvd). In cooperation with St. Louis County, construct Route 141 from Route 340 (Olive Blvd) to Route 364 (Page Ave) | New Construction | 2009-08-19 | 2009-08-19 | 2012-03-01 |  | 56700078 | 2.700 | 1411029
7316 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS |  | 01 | 1411034 | This project consist of grading for the utility relocation at Route 340 in St. Louis county | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2010-05-01 | 2010-04-30 | 743385.45 | 0.500 | 1411034
7317 | MISSOURI | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON |  | 04 | 1501010 | This project consists of grading, drainage and new concrete pavement to construct a divided 4 lane highway on Route 9 from Horridge Road to Route 291 in Lee's Summit. | Pavement Widening | 2009-09-08 | 2009-09-08 | 2011-11-01 |  | 14101900 | 3.426 | 1501010
7318 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE |  |  | 1600706 | This project consist of resurfacing in communities with populations less than 5,000 in Barton and Jasper | Pavement Improvement | 2010-03-15 | 2010-05-03 | 2010-10-01 | 2010-10-08 | 266916.67 | 0.000 | 1600706
7319 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BATES |  | 04 | 1600707 | This project consist of resurfacing in communities with populations less than 5,000 in Bates County. Project split from 7S0010B. | Pavement Improvement | 2010-03-15 | 2010-10-18 | 2010-10-01 | 2010-10-29 | 173083.46 | 0.000 | 1600707
7320 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | ST CLAIR |  | 04 | 1600708 | This project consist of resurfacing in communities with populations less than 5,000 in St. Clair county. | Pavement Improvement | 2010-03-15 | 2010-06-10 | 2010-10-01 | 2010-06-30 | 214405.4 | 0.000 | 1600708
7321 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | BARRY |  | 07 | 1600709 | This project consist of resurfacing in communities with populations less than 5,000 in Barry County. | Pavement Improvement | 2010-03-15 | 2010-05-11 | 2010-10-01 | 2010-06-02 | 123123.57 | 0.000 | 1600709
7322 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | PEMISCOT |  | 08 | 1641008 | This project consist of a thin lift asphalt overlay from Route D to Route DD in Pemiscot county | Pavement Improvement | 2009-05-08 | 2009-05-08 | 2009-12-01 | 2009-06-01 | 99361.37 | 1.725 | 1641008
7323 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | 1691086 | A $1.1 million contract awarded to St. Joseph Fuel Oil & Manufacturing Company for two miles of sidewalk improvements. Included are new upgrades to the existing sidewalk and adding curb ramps to accom | Transportation Enhancements | 2009-08-10 | 2009-08-10 | 2009-12-01 | 2009-12-04 | 1133856.23 | 2.023 | 1691086
7324 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ANDREW |  | 06 | 1692021 | This project consist of pavement and shoulder improvements from Route 31 to I-29 in Dekalb, Andrew, and Buchanan counties | Pavement Improvement | 2009-07-06 | 2009-09-25 | 2009-12-01 | 2009-11-30 | 2787343.94 | 21.438 | 1692021
7325 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | SALINE |  | 04 | 2401019 | This project consist of a thin lift asphalt overlay from east of Route 65 to Route 41 in Saline county | Pavement Improvement | 2009-03-30 | 2009-03-30 | 2009-12-01 | 2009-06-30 | 73420.03 | 0.391 | 2401019
7326 | MISSOURI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | HOWARD |  | 06 | 2401020 | This project consist of pavement and shoulder improvements from Route 5 to Route 40 in Howard county | Pavement Improvement | 2009-06-08 | 2009-09-28 | 2009-12-01 | 2009-12-01 | 1072711.37 | 12.800 | 2401020
7327 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | STONE |  | 07 | 2651001 | This project consist of a thin lift asphalt overlay from Route 76 to Route 165 in Stone and Taney counties | Pavement Improvement | 2009-04-06 | 2009-04-14 | 2009-12-01 | 2009-05-04 | 282036.46 | 5.364 | 2651001
7328 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | 2661012 | This project consist of a thin lift asphalt overlay from Route AB to Farm Road 107 in Greene county | Pavement Improvement | 2009-06-08 | 2009-07-14 | 2009-12-01 | 2009-08-19 | 64386.58 | 1.324 | 2661012
7329 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 06 | 3372402 | City of Independence - 39th Street Improvements from Noland to Chrysler, three lane, curb and guttering and sidewalks | Pavement Widening | 2010-11-22 | 2010-11-22 | 2012-03-01 | 2011-11-16 | 1088224.81 |  | 3372402
7330 | MISSOURI | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES |  | 02 | 3641032 | This project consist of extending Page Ave. from 0.3 miles west of Harvester to 0.6 miles east of Central School Road at Woodstream in St. Charles county | New Construction | 2009-10-05 | 2009-10-22 | 2011-12-01 |  | 20063948.85 | 0.300 | 3641032
7331 | MISSOURI | Underway | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES |  | 02 | 3641033 | This project consist of extending Page Ave. from 0.6 miles east of Central School Road at Woodstream to 0.3 miles wet of Central School Road in St. Charles county | New Construction | 2009-10-05 | 2009-10-22 | 2011-12-01 |  | 22795858.16 | 0.900 | 3641033
7332 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | 3641034 | This project consist of grading, paving, bridge and one-way outer roads from .3 miles west of Central School Road to Mid Rivers Mall Drive - St. Charles county | Pavement Improvement | 2010-03-01 | 2010-03-10 | 2011-12-01 | 2011-08-15 | 6065000 | 1.300 | 3641034
7333 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE |  |  | 4500205 | This project consist of cold in Place Recycling on various routes in Nodaway, Caldwell, Harrison, DeKalb, Daviess,Worth, Andrew and Gentry counties | Pavement Improvement | 2009-06-08 | 2009-06-23 | 2009-10-01 | 2009-11-09 | 3490059.09 | 0.000 | 4500205
7334 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | 5417603 | St. Louis City will be street enhancements on Cherokee Street from Nebraska to Jefferson. This consist of streetscape improvements, sidewalk reconstruction w/landscaping, pedestrian lighting, and street furniture | Transportation Enhancements | 2010-07-06 | 2010-07-16 | 2010-12-01 | 2011-05-24 | 705556.89 | 0.400 | 5417603
7335 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | 5421602 | This project consist of a design study for the Goodfellow Blvd. roadway. | Pavement Widening | 2010-09-03 | 2010-09-03 | 2011-12-01 |  | 1966365.76 | 0.000 | 5421602
7336 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY |  | 01 | 5500664 | "St.Louis City will be doing enhancements on Manchester Road from Taylor Ave. to Sarah Ave. This consist of sidewalk widening, removal and relocation of curbs to create four 11'-6"" lanes, pedestrian | Transportation Enhancements | 2010-01-07 | 2010-01-07 | 2011-12-01 | 2011-07-13 | 1311873.89 | 0.700 | 5500664
7337 | MISSOURI | Completed | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | 5595611 | St.Louis City will be doing Phase 2 of the Salisbury Street enhancements from N. Florissant to 11th Street. This consist of reconstructing sidewalks and ramps, new pedestrian lighting, curb repair, la | Transportation Enhancements | 2010-01-08 | 2010-01-08 | 2011-05-15 | 2011-01-26 | 854053.88 | 0.400 | 5595611
7338 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | 5602602 | St. Louis City will be widening bridge over Union Pacific RR tracks, including iimprovements to intersections with southbound I-55 off ramp (Loughborough Ave over Union Pacific Railroad) | Bridge Replacement | 2010-05-24 | 2010-07-12 | 2011-12-01 | 2011-08-30 | 631032 | 0.110 | 5602602
7339 | MISSOURI | Underway | C240,C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | 5603602 | St. Louis City will be doing asphalt resurfacing and constructing retaining walls and culverts on the Tucker Street Bridge from O'Fallon St. to Washington Avenue | Pavement Widening | 2010-01-08 | 2010-01-08 | 2011-12-01 |  | 17387181 | 0.665 | 5603602
7340 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | 6201602 | The City of Union has received additional funds for improvments on the Church Street project including sidewalks, paved approaches, curb and gutter, utility adjustments and retaining walls from Route 50 to Independence Drive | Transportation Enhancements | 2009-05-04 | 2009-07-01 | 2009-10-30 | 2009-10-30 | 207932 | 1.200 | 6201602
7341 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | 6202601 | This project consist of a bridge replacement over Boone Creek at Sapsucker Road in Franklin County. | Bridge Replacement | 2010-11-01 | 2010-11-01 | 2011-12-01 | 2011-07-25 | 444309.03 | 0.150 | 6202601
7342 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | 7203601 | Jefferson County will be doing roadway improvemetns from Lion's Den Camp Rd to Binning Road. | Pavement Widening | 2010-07-19 | 2010-07-19 | 2011-12-01 | 2011-07-31 | 1296516.83 | 0.820 | 7203601
7343 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | 7305604 | The City of St. Peters will be installing new traffic signals and pedestrian facilities at St. Peters-Howell Road / Toelle Road. | Safety/Traffic Management | 2010-11-03 | 2011-01-17 | 2011-04-15 | 2011-05-18 | 208832.47 | 0.100 | 7305604
7344 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | 7401020 | This project consist of pavement improvements on westbound and eastbound lanes from Broadway to Route 63 in Boone county | Pavement Improvement | 2009-07-13 | 2009-07-13 | 2009-10-05 | 2009-09-10 | 1916857.02 | 5.303 | 7401020
7345 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | 7591001 | This project consists of pavement repair and resurfacing the roadway and shoulders on Route 759 Buchanan county. | Pavement Improvement | 2010-02-01 | 2010-04-26 | 2010-12-01 | 2010-07-29 | 2045965.47 | 2.118 | 7591001
7346 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | STONE |  | 07 | 9900832 | In Gelena, the city will be doing sidewalk improvements around the square along 4th Street, Maple Street, and Main Street | Transportation Enhancements | 2009-10-15 | 2009-11-01 | 2010-09-01 | 2010-08-20 | 249971.43 | 0.150 | 9900832
7347 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | OZARK |  | 08 | 9900840 | In Gainsville, the city will be doing sidewalk rehabilitation and construction near the square and along various city streets | Transportation Enhancements | 2010-01-29 | 2010-02-16 | 2010-09-01 | 2010-10-11 | 113780 | 0.350 | 9900840
7348 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | 9900860 | This project will provide scoping and final design to improve safety and capacity of Route CC from Main Street in the City of Nixa to Route NN/J in the City of Ozark. | Other | 2009-09-21 | 2009-09-28 | 2011-12-01 |  | 900000 | 3.700 | 9900860
7349 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN | ST. JOSEPH (KS) | 06 | ES01001 | This project consist of constructing a new truck staging area along Stockyard Expressway and intersections improvements in the St. Joseph Regional Port area | Pavement Widening | 2009-07-17 | 2009-08-27 | 2010-11-01 | 2010-10-20 | 1097188.28 | 0.000 | ES01001
7350 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | NODAWAY |  | 06 | ES01002 | The City of Maryville will be constructing Phase A-II, which is a walking/biking trail located within the city limits of Maryville. This trail will be 3760 ft. in length and 6' to 8' in wide with a concrete surface. | Transportation Enhancements | 2009-09-11 | 2009-09-11 | 2010-10-15 | 2010-08-29 | 284421.34 | 0.712 | ES01002
7351 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN | ST. JOSEPH (KS) | 06 | ES01003 | "The Urban Trail System incorporates the construction of 10' wide, 6"" thick concrete pavement for use as a high-volume, shared-use trail. This specific phase constitutes the first component of a two | Transportation Enhancements | 2010-04-05 | 2010-04-05 | 2010-10-15 | 2010-09-30 | 186902.41 | 0.316 | ES01003
7352 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CHARITON |  | 06 | ES02002 | The City of Brunswick will be replacing existing sidewalks along Route 24 from Polk Street to Adams Street | Transportation Enhancements | 2009-10-13 | 2009-10-14 | 2010-07-01 | 2010-07-27 | 412126.01 | 0.712 | ES02002
7353 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | WARREN |  | 09 | ES03002 | City will construct a new ADA (Americans with Disabilities Act) compliant sidewalk, which will provide connectivity of Marthasville?s ?Uptown? section to the ?Downtown? section. There will be replace | Transportation Enhancements | 2009-09-23 | 2009-10-01 | 2010-07-31 | 2010-07-31 | 57549.52 | 0.150 | ES03002
7354 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | LEWIS |  | 09 | ES03003 | City will remove old, deteriorated existing sidewalks with safe new sidewalks, which will be constructed to American with Disabilities Act (ADA) Standards. The five-foot-wide sidewalk will connect th | Transportation Enhancements | 2009-08-07 | 2009-08-07 | 2010-12-31 | 2011-01-31 | 64706.96 | 0.090 | ES03003
7355 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | PIKE |  | 09 | ES03004 | City will install historic/ornamental lighting in the downtown district. The new lighting will be in the vicinity of Lewis Street, Clark Street and 4th Street (State Route B) | Transportation Enhancements | 2009-09-14 | 2009-09-14 | 2010-12-15 | 2010-12-15 | 96035 | 0.400 | ES03004
7356 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | MONROE |  | 09 | ES03005 | The City of Paris will replace existing sidewalk with new sidewalk that will be constructed to American with Disabilities Act (ADA) Standards. There will also be the installation of historic lightin | Transportation Enhancements | 2009-08-20 | 2009-08-20 | 2010-12-15 | 2011-01-03 | 76026.24 | 0.600 | ES03005
7357 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | MONTGOMERY |  | 09 | ES03007 | The City of Jonesburg proposes to remove 982 linear feet of existing sidewalk and construct 4? concrete sidewalk that will be constructed to American with Disabilities Act (ADA) Standards. The sidewa | Transportation Enhancements | 2009-10-19 | 2009-10-19 | 2010-07-31 | 2010-07-31 | 59048.69 | 0.190 | ES03007
7358 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CLAY | KANSAS CITY (KS)-MO | 06 | ES04001 | The City of Gladstone will be doing landscaping, decorative lighting, crosswalks and other scenic corridor improvements along North Oak Trafficway from NE 69th Street to NE 71st Street | Pavement Improvement | 2009-09-18 | 2009-09-22 | 2009-10-24 | 2009-10-24 | 305097.35 | 1.510 | ES04001
7359 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | Multiple | ES04002 | The City of Blue Springs will be doing mill, asphalt overlay, and curb pavement markings at Adams Dairy Parkway from Duncan to Moreland School Road | Pavement Improvement | 2009-10-21 | 2009-10-21 | 2009-11-16 | 2009-11-16 | 378061 | 0.400 | ES04002
7360 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CLAY | KANSAS CITY (KS)-MO | 06 | ES04003 | The City of Liberty will be putting in additional curbs, lane width and improvements of medians of Kansas Street, Liberty Drive, and Mill Street | Pavement Improvement | 2009-10-12 | 2009-10-13 | 2009-11-18 | 2009-11-18 | 378061 | 0.803 | ES04003
7361 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04004 | The City of Raytown will be doing removal and replacement of deteriorated curbs and sidewalk. There will also be construction of new curbs and sidewalks at varius location throughout Raytown | Pavement Improvement | 2010-06-09 | 2010-06-10 | 2010-12-01 | 2011-01-13 | 377971.28 | 2.745 | ES04004
7362 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE | KANSAS CITY (KS)-MO | 06 | ES04005 | This project consist of construction of left turn lanes at Route AA in the City of Riverside - Platte county | New Construction | 2010-03-08 | 2010-03-24 | 2010-06-11 | 2010-07-21 | 303942 | 0.304 | ES04005
7363 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 04 | ES04006 | In Pleasant Hill, the city will be doing milling and overlay work on Business Route 7, Country Club Drive, and Sugarland Drive | Pavement Improvement | 2010-06-01 | 2010-06-03 | 2010-12-01 | 2010-07-01 | 186131.95 | 1.500 | ES04006
7364 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 06 | ES04007 | Jackson County will be replacing failing deck and upgrading guardrail system on Blue Mills Bridge | Bridge Improvement | 2010-02-15 | 2010-02-15 | 2010-12-01 | 2010-07-27 | 378061 | 0.049 | ES04007
7365 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 04 | ES04008 | In Harrisonville, the city will be doing milling and overlay work on North Independence, South Street, North Commercial Street, and South Independence | Pavement Improvement | 2010-03-01 | 2010-04-12 | 2010-08-01 | 2010-11-21 | 280051.93 | 1.760 | ES04008
7366 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04009 | The City of Grandview will be reconstruction 2000 ft of the rural section of 2nd Street to connect with 1600 ft long 3rd Street being constructed on a new alignment | Pavement Widening | 2010-06-15 | 2010-06-16 | 2011-06-11 | 2011-07-18 | 378061 | 0.340 | ES04009
7367 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 05 | ES04010 | In Belton, the city will be doing milling and overlay work on Cambridge Road, Prospect Avenue, Kentucky Street, 163rd Street, and North Scott Avenue | Pavement Improvement | 2010-07-29 | 2010-07-29 | 2010-12-01 | 2010-08-25 | 350328.06 | 2.468 | ES04010
7368 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04011 | The City of Lee's Summit will be constructing Todd George Road between two existing arterials and as an outer road associated with the Strother Road Interchange currently under construction | New Construction | 2010-07-12 | 2010-07-16 | 2011-12-01 | 2011-10-27 | 1183191.48 | 2.600 | ES04011
7369 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 04 | ES04012 | In Raymore, the city will be doing milling and overlay work on M-58 Highway | Pavement Improvement | 2010-06-01 | 2010-07-15 | 2010-08-30 | 2010-11-10 | 342672.2 | 0.010 | ES04012
7370 | MISSOURI | Underway | C240,C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04015 | Kansas City will be replacing Troost Bridge at Volker Blvd. | Pavement Widening | 2010-05-10 | 2010-05-10 | 2012-03-01 |  | 8876831.5 | 0.490 | ES04015
7371 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE | KANSAS CITY (KS)-MO |  | ES04016 | Signal retiming/synchronization, vehicle detection on creitical intersection, cameras added, Operation Green Light location expansion, new communication tower and upgrades to the wireless backbone. | Safety/Traffic Management | 2009-08-26 | 2009-08-27 | 2011-12-31 | 2012-08-01 | 3595750.5 | 0.000 | ES04016
7372 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 06 | ES04017 | The City of Independence will be creating a Major North-South divided four lane street. The new roadway will have open ditches, sidewalk, and a shared bicycle/pedestrian path to reconnect city and social networks | New Construction | 2010-03-15 | 2010-03-29 | 2011-12-01 | 2011-05-02 | 2567583.54 | 0.800 | ES04017
7373 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04019 | The City of Independence will be widening Jackson Drive from Holke Road to M-78 Highway from the existing 2 lanes to 4. There will also be installation of curb, gutter, sidewalk, and shared use path | Pavement Widening | 2010-02-01 | 2010-02-03 | 2011-12-01 | 2011-08-23 | 1015161.45 | 0.604 | ES04019
7374 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04020 | Kansas City will be constructing traffic signals at five intersections: 31st Street at Southwest Trafficway, The Paseo, Benton Blvd, Cleveland Avenue, and Jackson Avenue | Safety/Traffic Management | 2010-04-26 | 2010-04-26 | 2010-12-01 | 2010-07-12 | 712622.4 | 0.000 | ES04020
7375 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04021 | Kansas City will be rehabilitating the current Traffic Operation buidling and purchase of equipment for Traffic Operations activities | Safety/Traffic Management | 2010-09-27 | 2010-09-27 | 2010-12-01 | 2011-06-05 | 750000 | 0.000 | ES04021
7376 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04022 | The City of Blue Springs will be construction traffic signals at two intersections: 39th Street and Broadway Blvd and 39th Street and Roanake Road | Safety/Traffic Management | 2010-03-15 | 2010-03-15 | 2010-12-01 | 2011-01-12 | 400000 | 0.000 | ES04022
7377 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE | KANSAS CITY (KS)-MO |  | ES04023 | A planning study to develop detailed transit implementation, phasing, and costing information to support expanded local, county, and retional service implementation. | Other | 2009-08-12 | 2009-08-12 | 2011-12-31 |  | 258820 | 0.000 | ES04023
7378 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04024 | "The City of Kansas City will be constructing a 10"" wide 1600 ft trail, which will connect to the existing trail " | Transportation Enhancements | 2010-04-15 | 2010-04-15 | 2010-12-01 | 2010-12-15 | 313753.73 | 0.490 | ES04024
7379 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04025 | The City of Raytown will be replacing sidewalks and will be doing construction of new 5' wide sidewalks | Transportation Enhancements | 2010-10-26 | 2010-10-26 | 2010-12-01 | 2011-05-11 | 514488.43 | 4.000 | ES04025
7380 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04026 | The City of Blue Springs will be doing an expansion of Ward Park Trail. This will consist of removal and reasphalt of the existing 1 mile long trail, extending trail 500 ft and widen existing trail 4 ft to 8ft surface | Transportation Enhancements | 2010-09-01 | 2010-09-07 | 2010-12-01 | 2010-12-23 | 56458.85 | 1.000 | ES04026
7381 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 04 | ES04027 | The City of Raytown will be reconstructing a 6.2 mile bicycle and pedestrian trail at Longview Lake | Transportation Enhancements | 2010-02-15 | 2010-02-15 | 2010-12-01 | 2011-07-21 | 250000 | 6.200 | ES04027
7382 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04028 | The City of Lee's Summit will be construction 0.7 miles of multi-use 10' wide trail along Todd George Road to connect to existing multi-use trail on both north and south | Transportation Enhancements | 2010-05-03 | 2010-05-14 | 2010-12-01 | 2011-03-25 | 148502.44 | 0.460 | ES04028
7383 | MISSOURI | Completed | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | CLAY | KANSAS CITY (KS)-MO | 06 | ES04029 | The City of Gladstone will be doing mill and overlay work on Broadway from Englewood Road to north city limits | Transportation Enhancements | 2010-10-12 | 2010-10-21 | 2010-12-01 | 2011-06-12 | 272963.65 | 0.250 | ES04029
7384 | MISSOURI | Completed | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04030 | The City of Independence will be connecting the 1.6 mile asphalt multi-use train in Waterfall Park with the 14 mile multi-use 10' wide Little Blue Trace Trail | Transportation Enhancements | 2010-07-12 | 2010-07-13 | 2010-12-01 | 2011-04-15 | 420000 | 0.490 | ES04030
7385 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CASS | KANSAS CITY (KS)-MO | 04 | ES04031 | The City of Cleveland will be doing construction and replacement of 5' wide sidewalks along the north and south sides of Main Street/State Highway Y | Transportation Enhancements | 2010-07-12 | 2010-07-14 | 2010-12-31 | 2011-04-15 | 115526.98 | 0.660 | ES04031
7386 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | ES04032 | The City of Weston will be constructing new 5' wide sidewalks on 5th Street | Transportation Enhancements | 2009-09-17 | 2009-09-17 | 2010-12-01 | 2011-02-14 | 74423.82 | 0.090 | ES04032
7387 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | LAFAYETTE |  | 04 | ES04034 | The City of Higginsville will be constructing new 5' wide sidewalks on Fairground Park/Grandview Elementary Sidewalks | Transportation Enhancements | 2009-08-19 | 2009-08-19 | 2010-12-01 | 2010-12-17 | 150587.83 | 0.570 | ES04034
7388 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | HENRY |  | 04 | ES04035 | This project consist of sidewalk improvements on Route 18 from east of 9th Street to west of Pawnee Street in the City of Clinton | Transportation Enhancements | 2009-09-11 | 2009-09-21 | 2010-08-15 | 2010-07-30 | 137910.8 | 0.428 | ES04035
7389 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | ES04036 | City of Kearney will be installing street lights, 5' sidewalks, fence handrail landscape along Main Street | Transportation Enhancements | 2009-09-25 | 2009-09-25 | 2010-12-01 | 2011-01-24 | 116539.3 | 0.220 | ES04036
7390 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04037 | Enhancements to channel & roadway project at Brush Creek & Troost, including: landscaping, signage, lighting, benches, trash receptacles, trail connection from creek to street @ NW corner of Paseo & Volker Blvds. | Transportation Enhancements | 2010-10-07 | 2010-10-12 | 2011-12-01 | 2011-04-21 | 1342721.23 | 1.000 | ES04037
7391 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JACKSON | KANSAS CITY (KS)-MO | 05 | ES04038 | The improvements for West Front Street will be a 4-lane divided roadway built to boulevard standards. The project limits will be the Grand Boulevard Diamond Interchange (I-29/35 under construction) to the east. | New Construction | 2010-10-13 | 2010-10-13 | 2011-12-01 | 2011-06-24 | 2314441.33 | 0.700 | ES04038
7392 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE | COLUMBIA | 09 | ES05003 | In Columbia, the city will be building a raiload bridge over Route 63 north of Route B in Boone county | Safety/Traffic Management | 2009-07-30 | 2009-08-17 | 2010-10-01 | 2010-10-07 | 3350137.6 | 0.200 | ES05003
7393 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BENTON |  | 04 | ES05004 | Construction of the Steamboat Landing Trail in the City of Warsaw. This project includes a pedestrian trail, landscaping, and lighting along the north side of the harbor connecting Drake Harbor to the Osage Trail | Transportation Enhancements | 2010-03-10 | 2010-03-10 | 2010-10-01 | 2010-10-29 | 260476 | 0.000 | ES05004
7394 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | ES05005 | The City of Hallsville will be constructing sidewalks along Ricketts Road, Sunrise Drive, Fairview Street, and Route OO | Transportation Enhancements | 2010-06-28 | 2010-07-01 | 2010-10-01 | 2011-04-28 | 288528.75 | 0.000 | ES05005
7395 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | MARIES |  | 09 | ES05006 | The City of Belle will be replacing old broken sidewalk on Third St. from Tellman Ave. to Linn Ave. Also included are new sidewalks on Third St. from Johnson Ave. to Apple Ave and along Fourth St. between Johnson Ave. and Oak Ave | Transportation Enhancements | 2010-02-10 | 2010-03-01 | 2010-10-01 | 2010-04-22 | 66467 | 0.000 | ES05006
7396 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CAMDEN |  | Multiple | ES05007 | The City of Osage Beach will be constructing new sidewalks along the west side of Rte 54 from Redbud Road to Zebra Road and along the east side of Rte 54 from Zebra Road to Hatchery Road | Transportation Enhancements | 2010-02-17 | 2010-02-18 | 2010-10-01 | 2010-06-10 | 319605 | 0.760 | ES05007
7397 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | ES05008 | This project consist of MDNR bridge rehabilitation on Katy Trail over Moniteau Creek near Rocheport - Boone county | Transportation Enhancements | 2010-03-15 | 2011-01-10 | 2011-12-01 | 2012-02-03 | 504701 | 0.000 | ES05008
7398 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | COOPER |  | 06 | ES05009 | This project consist of MDNR culvert rehabilitation on Katy Trail over an unnamed creek, near Pleasant Green - Cooper county | Transportation Enhancements | 2010-03-15 | 2010-10-12 | 2010-10-01 | 2010-11-09 | 199700 | 0.000 | ES05009
7399 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES |  | 02 | ES05010 | This project consist of MDNR bridge replacement on Katy Trail over Little Femme Osage Creek, near Defiance - St. Charles county | Transportation Enhancements | 2010-03-15 | 2011-09-09 | 2012-01-01 | 2012-04-23 | 249000 | 0.000 | ES05010
7400 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES |  | 02 | ES05011 | This project consist of MDNR construction of approximately 2.5 miles of new Katy Trail from St. Charles to Machens - St. Charles County | Transportation Enhancements | 2010-03-15 | 2010-09-21 | 2010-10-01 | 2010-11-29 | 382805.42 | 0.000 | ES05011
7401 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06001 | Goodfellow-Skinker Asphalt Overlay and Pedestrian Improvements . Design Study - Engineering Design Study -pedestrian facilities,streetscaping elements, and reconfiguration of the MO T / Front Street intersection. | Other | 2009-07-10 | 2009-07-10 | 2010-12-01 | 2010-09-10 | 319106.53 | 0.200 | ES06001
7402 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06002 | Franklin County will be doing a pedestrian/bike path along the west side of Route T from Great Oaks Drive to Labadie Elementary School | Transportation Enhancements | 2009-07-10 | 2009-07-10 | 2011-11-29 | 2011-08-26 | 277897.1 | 0.600 | ES06002
7403 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06003 | The City of Pacific will be doing sidewalk and lighting improvements on West Osage Street. This will consist of street lighting, street trees, retaining walls from Indian Warpath Drive to North 7th Street | Safety/Traffic Management | 2010-08-15 | 2010-09-20 | 2011-11-29 |  | 701695.54 | 1.700 | ES06003
7404 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06004 | The City of Sullivan will be doing Phase 2 on East Vine Street, which consist of asphalt resurfacing, curb and gutter, sidewalks from McKinley Street to Hughes Ford Road | Pavement Improvement | 2010-09-27 | 2010-09-28 | 2011-11-29 | 2011-05-31 | 750236.22 | 0.500 | ES06004
7405 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06006 | The City of Washington will be doing asphalt resurfacing on various streets: W. Eighth Street, W. Main Street, Grand Avenue, Pottery Road, Old Route 100, Route 47 to Stafford Street | Pavement Improvement | 2009-08-07 | 2009-08-07 | 2009-10-01 | 2009-10-02 | 659355.23 | 3.000 | ES06006
7406 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06007 | The City of Crystal City will be doing aphalt resurfacing on Crystal City Heights Road from Missouri Ave. to Commercial Blvd | Pavement Improvement | 2009-08-19 | 2009-08-19 | 2010-02-10 | 2010-02-10 | 369773.76 | 1.400 | ES06007
7407 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | FRANKLIN | ST. LOUIS (IL) | 09 | ES06008 | Washington Special Road Distrct will be doning asphalt resurfacing on Bieker Road from S. Pointe Road to the Washington City limits. | Pavement Improvement | 2009-08-27 | 2009-08-27 | 2010-07-31 | 2010-07-30 | 192368 | 4.000 | ES06008
7408 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06009 | Jefferson County will be doing asphalt resurfacing on Antire Road from High Ridge Blvd. to the St. Louis County line | Pavement Improvement | 2009-12-15 | 2010-05-11 | 2010-08-27 | 2010-07-06 | 310289 | 3.960 | ES06009
7409 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06010 | Jefferson County will be installing guradrail on Old Lemay Ferry Road from Route M to Wedde Road | Safety/Traffic Management | 2010-05-10 | 2010-05-11 | 2010-12-01 | 2010-05-24 | 118646.97 | 0.430 | ES06010
7410 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06011 | Jefferson County will be doing asphalt resurfacing on River Street Road from Route K to Route 61/67 | Pavement Improvement | 2009-11-19 | 2009-11-23 | 2010-03-24 | 2010-03-24 | 50120.52 | 0.220 | ES06011
7411 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06012 | The City of De Soto will be doing asphalt resurfacing, concrete slab replacement, curb ramp replacement, curb and gutter, and street trees on Amvets Drive from S. Main Street to Route 21 | Pavement Improvement | 2010-02-24 | 2010-03-03 | 2010-08-31 | 2010-08-15 | 855706.1 | 1.100 | ES06012
7412 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06013 | Jefferson County will be doing asphalt resurfacing on Flucom Road from Route 67 to De Soto city limits | Pavement Improvement | 2010-03-30 | 2010-03-30 | 2010-06-25 | 2010-04-21 | 444224.57 | 4.380 | ES06013
7413 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06014 | Jefferson County will be doing asphalt resurfacing on Klondike (South) Road from Route E to McClain Street | Pavement Improvement | 2010-01-20 | 2010-03-29 | 2010-10-01 | 2010-04-20 | 441823 | 1.800 | ES06014
7414 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06015 | Festust Special Road District will be doing asphalt resurfacing on Scenic Dr., County Road, Cherry Ln., Scenic - Herculaneum city limits to Festus city limit, Cherry - Route Z to County Rd., County Road - Cherry Lane Drive to Route Z | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2010-10-01 | 2009-10-05 | 419493.88 | 3.000 | ES06015
7415 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | JEFFERSON | ST. LOUIS (IL) | 03 | ES06016 | Jefferson County will be reconstructing and adding a center turn lane on Little Brennan Road from Route 30 to Gravois Road | Pavement Widening | 2010-05-10 | 2010-05-10 | 2011-04-01 | 2010-07-07 | 191719.39 | 0.100 | ES06016
7416 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS | ST. LOUIS (IL) | 02 | ES06017 | St. Louis County will be construction and completing the Maryland Heights Expressway Connector (4 lane freeway) from Page Ave. (Rte. 364) to Olive Blvd. (Rte. 340) | New Bridge Construction | 2010-04-19 | 2010-04-19 | 2012-09-01 |  | 20000000 | 2.500 | ES06017
7417 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06018 | The City of Cottleville will be constructing a new traffice signal at Route N and Brittany Cove | Pavement Widening | 2009-08-21 | 2009-08-21 | 2010-12-01 | 2010-08-30 | 157553.96 | 0.100 | ES06018
7418 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06019 | The City of O'Fallon will be doing asphalt Resurfacing on Main (Rte.M), Sonderen, East Pitman: Main St. (Rte. M) - I-70 to 3rd St., Sonderen - Wabash Ave. to I-70, East Pitman St. - Main St. to Sonderen | Pavement Improvement | 2009-09-01 | 2009-09-01 | 2010-05-28 | 2010-05-05 | 599433.15 | 1.320 | ES06019
7419 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06020 | The City of St. Charles will be doing Phase 2 on the Fifth Street Corridor, which consist of widen lanes from three to five from First Capiol to Tompkins Street | Pavement Widening | 2010-03-10 | 2010-03-10 | 2010-08-01 | 2010-11-09 | 318002 | 0.120 | ES06020
7420 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 09 | ES06021 | St. Charles County will be installing a shared use lane on Route 94 from Defiance Road to Walnut Springs Road | Pavement Widening | 2009-09-08 | 2009-09-08 | 2010-10-01 | 2010-08-10 | 430000 | 0.500 | ES06021
7421 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06022 | The City of St. Peters will be doing traffic signal improvements on Mid Rivers Mall Drive from Cottleville Rd. to Cottleville Parkway. This will consist of installing video detection amd sidewalk repairs | Pavement Improvement | 2010-10-07 | 2010-11-29 | 2011-03-31 | 2011-03-18 | 321307.77 | 0.740 | ES06022
7422 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS | ST. LOUIS (IL) | 02 | ES06023 | Great Streets Demonstration Project - Manchester Road - Rte. 141 to Rte. 109Engineering Planning and Design Study of entrances and exits and traffic flow. | Other | 2009-09-08 | 2009-09-10 | 2010-09-08 | 2011-02-23 | 1100000 | 5.000 | ES06023
7423 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS | ST. LOUIS (IL) | 01 | ES06024 | Engineering Design Study of Great Streets Demonstration Project - Natural Bridge Rd. - Lucas & Hunt Rd. to UMSL South Metrolink Station in Normandy | Other | 2009-10-13 | 2009-10-19 | 2012-01-31 |  | 998644.49 | 0.750 | ES06024
7424 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06025 | Great Streets Demostration Project on South Grand from Arsenel to McDonald in City of St. Louis to improve entrances and exits and traffic flow. | Other | 2009-07-10 | 2009-07-10 | 2011-12-01 |  | 886103.02 | 0.400 | ES06025
7425 | MISSOURI | Underway | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06026 | Grand Center/Grand Blvd. Streetscape- Lindell to Page Ave.Sidewalk improvements, new pedestrian signs, crosswalks and traffic calming | Transportation Enhancements | 2009-08-12 | 2009-08-12 | 2011-12-01 |  | 2000000 | 0.660 | ES06026
7426 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06027 | St. Louis City will be doing improvements to South Grand from Arsenal to McDonald by installing a pedestrian signal and update sidewalks | Pavement Widening | 2010-01-15 | 2010-01-15 | 2011-12-01 |  | 1503740.28 | 0.400 | ES06027
7427 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06028 | St. Louis City will be doing streetscapes on Vandeventer Avenue, Kingshighway to Shaw; segment of Accomac. They will be adding pedestrian signal, solar powered lighting, and rain garden | Pavement Widening | 2009-08-12 | 2009-08-12 | 2010-12-01 | 2011-04-28 | 733225.84 | 0.450 | ES06028
7428 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06029 | The Land Clearance for Development Authority for the City of St. Louis will be doing reconstruction, reconstruct and new construction of sidewalks, improved railroad crossings, signal improvements at | Pavement Widening | 2009-07-29 | 2009-07-29 | 2011-12-01 |  | 2645406.76 | 0.600 | ES06029
7429 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06030 | St. Louis City will be doing repairs to Compton Avenue over Union Pacific Railroad from Chouteau to Spruce and bridge repairs | Bridge Improvement | 2010-01-08 | 2010-01-08 | 2011-08-01 | 2011-03-01 | 1255915.02 | 0.500 | ES06030
7430 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06031 | St. Louis City will be doing pedestrian lighting enhancements on Dr. Martin Luther King Road from Arlington West to city limits | Transportation Enhancements | 2010-06-07 | 2010-08-02 | 2011-12-01 |  | 949875.15 | 1.600 | ES06031
7431 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06032 | St. Louis City will be adding new pedestrian lighting on Manchester Road from Taylor Ave. to Sarah Ave. | Transportation Enhancements | 2010-01-07 | 2010-01-07 | 2011-07-01 | 2011-05-13 | 981044.13 | 0.670 | ES06032
7432 | MISSOURI | Underway | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06033 | St. Louis City will be doing signal interconnect/Upgrade on Morgan Ford Road. This will consist of 11 signalized intersections from Arsenal Street to City limits. Interconneect traffic signals, signal timing progression | Safety/Traffic Management | 2009-07-24 | 2009-07-24 | 2011-12-31 |  | 1477016.57 | 3.740 | ES06033
7433 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06034 | The Land Clearance for Development Authority of the City of St. Louis will be doing mill/resurfacesurfacing and new curbs, bumpouts, sidewalks, ramps, lighting, and signals on North Sarah Street from Belle to Page | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2011-12-31 | 2011-07-29 | 1115709.55 | 0.260 | ES06034
7434 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06035 | St. Louis City will be doing overlay and pedestrian improvements on Good Fellow/Skinker. This will consist of asphalt mill and overlay, sidewalk improvements, new ADA compliant curb ramps, and striping | Pavement Improvement | 2009-08-12 | 2009-08-12 | 2011-12-31 | 2011-09-16 | 3099218.74 | 7.300 | ES06035
7435 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 03 | ES06036 | South Broadway Streetscape - Courtois to Upton St..Traffic calming measures, access management, new lighting, sidewalks | Pavement Widening | 2009-08-12 | 2009-08-12 | 2010-03-01 | 2011-03-31 | 1005197.06 | 0.280 | ES06036
7436 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 02 | ES06037 | The City of Dardenne Prairie will be doing an intersection realignment at Post/Hanley and MO N | Pavement Widening | 2010-04-05 | 2010-05-17 | 2010-12-01 | 2010-08-26 | 371662.43 | 0.100 | ES06037
7437 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | ST CHARLES | ST. LOUIS (IL) | 09 | ES06038 | City of Lake St. Louis will be connecting the pedestrian and bike pathway from Northshire Lane to Prospect Village Drive | Transportation Enhancements | 2010-02-18 | 2010-03-30 | 2010-06-01 | 2010-05-21 | 41590.2 | 0.210 | ES06038
7438 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST LOUIS CITY | ST. LOUIS (IL) | 01 | ES06040 | This project invovles the stabilization of the existing port muncipal dock at the St. Louis City Regional Port | Other | 2009-09-23 | 2009-09-23 | 2011-04-01 | 2011-03-16 | 387991.46 | 0.000 | ES06040
7439 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JASPER | JOPLIN | 07 | ES07001 | In Joplin, the city will be constructing a pedestrian and bicycle trail connecting the Frisco Greenway Trail to the intersection of Florida Avenue and Newman Road | Transportation Enhancements | 2010-02-11 | 2010-02-15 | 2010-09-01 | 2010-08-27 | 439500 | 1.500 | ES07001
7440 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JASPER | JOPLIN | 07 | ES07002 | In Carl Junction, the city will be doing the design and construction of a pedestrian and bicycle trail from Briarbrook Drive to Copper Oaks Drive. The beginning of this project starts where the previously built Thom's Station Trail, Phase 2 ends | Transportation Enhancements | 2009-08-06 | 2009-08-06 | 2010-09-01 | 2010-08-12 | 172999.58 | 0.670 | ES07002
7441 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | JASPER | JOPLIN | 07 | ES07003 | In Webb City, the city will be purchasing materials for the establishment of the Route 66 themed Welcome Center in Webb City | Transportation Enhancements | 2009-11-20 | 2009-11-20 | 2010-08-31 | 2010-08-24 | 25790.98 | 0.000 | ES07003
7442 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08001 | The City of Strafford will be constructing sidewalks along McCabe St. from Washington Avenue to just west of Cedar Drive in front of Strafford Schools. | Transportation Enhancements | 2010-02-16 | 2010-03-01 | 2010-06-16 | 2010-06-01 | 65074 | 0.000 | ES08001
7443 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | ES08002 | In Ozark, the city will be doing surface improvements by paving the existing Frisco Highline Trail from Springfield to Willard | Transportation Enhancements | 2009-12-11 | 2010-01-14 | 2010-01-01 | 2010-05-04 | 77475.65 | 0.200 | ES08002
7444 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08003 | This project includes the construction of sidewalks along Highway Z from the existing Frisco Highline trail to the Willard Recreation Center in the City of Willard. | Transportation Enhancements | 2009-10-16 | 2009-10-19 | 2010-01-01 | 2009-12-14 | 78375 | 0.600 | ES08003
7445 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08004 | This project will pave an existing segment of the Frisco Highline Trail from Willard to 3 miles north of Springfield | Transportation Enhancements | 2009-11-05 | 2009-11-06 | 2010-06-01 | 2009-11-24 | 186482 | 0.000 | ES08004
7446 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | ES08006 | This project will provide an analysis of existing and projected traffic in order to develop an efficient traffic plan on 3rd Street from Jackson St. to Church St. | Other | 2009-09-08 | 2009-09-08 | 2010-09-01 | 2010-03-25 | 13188 | 0.200 | ES08006
7447 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | ES08007 | This project consists of a Transportation Planning Study to determine priority corridors and priority projects with some prelminary scoping of transportation projects within the boundaries of the City of Ozark. | Other | 2009-09-23 | 2009-09-23 | 2010-09-01 | 2010-07-26 | 38039 | 0.000 | ES08007
7448 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08008 | In Battlefield, the city will be constructing sidewalks along Cloverdale from Elm North | Transportation Enhancements | 2009-11-04 | 2009-11-30 | 2010-09-01 | 2010-01-27 | 57691 | 0.000 | ES08008
7449 | MISSOURI | Completed | C230 | Highway Infrastructure Investment Grant | MISSOURI | CHRISTIAN | SPRINGFIELD | 07 | ES08009 | This project will provide final design to improve safety and capacity at the intersection of Highway 160 & Highway 14 in the City of Nixa. | Other | 2009-08-11 | 2009-08-25 | 2010-11-01 | 2010-10-08 | 119913 | 5.700 | ES08009
7450 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | POLK |  | 07 | ES08010 | This project will pave a segment of the existing Frisco Highline Trail near Bolivar and pave the Wishart trailhead. | Transportation Enhancements | 2009-11-05 | 2009-11-06 | 2010-06-01 | 2010-04-19 | 151753.7 | 1.000 | ES08010
7451 | MISSOURI | Completed | C220,C230 | Highway Infrastructure Investment Grant | MISSOURI | GREENE | SPRINGFIELD | 07 | ES08011 | Ozark Greenways will be paving the current aggregate Frisco Highline Trail from Farm Road 115 to the trailhead in Springfield. | Transportation Enhancements | 2010-05-18 | 2010-06-21 | 2010-06-01 | 2010-07-20 | 136782.9 | 0.000 | ES08011
7452 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | PHELPS |  | 08 | ES09001 | The City of St. James will replace inadequate and unsafe sidewalk and extend sidewalk where none exists, along Highway 68 from the downtown south to the city limits and on east and west Scioto Streets | Transportation Enhancements | 2009-12-12 | 2009-12-18 | 2010-01-12 | 2010-04-11 | 114166.3 | 0.750 | ES09001
7453 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | TEXAS |  | 08 | ES09002 | The City of Houston is constructing 1.1 miles of new five foot sidewalk along Airport Road, Lone Star Drive, and Westwood Drive on city owned property at the Houston Memorial Airport. The sidewalk is Phase 5 of the Village Trail of Houston, MO | Transportation Enhancements | 2009-10-23 | 2009-11-12 | 2009-12-01 | 2009-12-23 | 142096.84 | 1.100 | ES09002
7454 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CAPE GIRARDEAU |  | 08 | ES10001 | This project involves the construction of a high-water rail line that will allow port rail to operate during high-water events | Other | 2009-11-16 | 2009-11-16 | 2011-12-01 | 2012-02-24 | 890960.02 | 0.000 | ES10001
7455 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | NEW MADRID |  | 08 | ES10002 | This project involves extending a rail spur to a site for a new tenant. This includes rail extension, switch, crossings, and siding. | Safety/Traffic Management | 2009-09-30 | 2009-11-16 | 2010-07-01 | 2010-04-01 | 687888.2 | 0.000 | ES10002
7456 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STE GENEVIEVE |  | 03 | ES10003 | This project involves construction of phase 1 on a new port, which involves excavation and site developments. | Other | 2009-04-01 | 2009-04-01 | 2011-12-01 | 2012-02-28 | 931816.81 | 0.000 | ES10003
7457 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | ST FRANCOIS |  | 08 | ES10004 | The City of Farmington will be doing constructing on sidewalks on North Fleming Ave., St. Genevieve Ave., Forster Street, Franklin Street, and Walton Drive | Transportation Enhancements | 2010-06-01 | 2010-07-17 | 2010-08-29 | 2010-10-05 | 208807.77 | 1.740 | ES10004
7458 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | DUNKLIN |  | 08 | ES10005 | The City of Malden will be doing Phase II, which consists of renovation of downtown of sidewalks. This consist of Main St. from Douglas to Marion, main St from Madison to Decatur, and Laclede from Madison to Decatur | Transportation Enhancements | 2010-05-21 | 2010-05-26 | 2010-10-13 | 2010-07-16 | 85988.16 | 0.500 | ES10005
7459 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | NEW MADRID |  | 08 | ES10006 | The City of New Madrid will be doing sidewalk construction on Crisler Street, Mott Street, Capitol Street, Waters Street, Main Street | Transportation Enhancements | 2010-04-29 | 2010-06-01 | 2010-09-28 | 2010-09-29 | 103111.19 | 0.600 | ES10006
7460 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | PERRY |  | 08 | ES10007 | The City of Perryville will be doing sidewalk construction on Schindler Road, State Street, Bredall Street, Waters Street, Rosati Court, Zeno Street, Bruce Street, Drury Lane | Transportation Enhancements | 2010-05-06 | 2010-06-01 | 2010-09-02 | 2010-09-08 | 207040.45 | 1.000 | ES10007
7461 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | BUTLER |  | 08 | ES10008 | The City of Poplar Bluff will be doing sidewalk construction on Poplar Street, Fifth Street, and Vine Street. There will be curb and gutter improvements on Vine Street. Construction of trail connecting Hendrickson Park to Bacon Memorial Park | Transportation Enhancements | 2010-05-25 | 2010-06-10 | 2010-09-28 | 2010-10-05 | 154629 | 1.000 | ES10008
7462 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | STODDARD |  | 08 | ES10009 | The City of Puxico will be doing sidewalk improvements on South East L. Hawks Street, East Owen Ave., South Hickman Street, and West Richard Ave. | Transportation Enhancements | 2010-04-19 | 2010-06-09 | 2010-08-26 | 2010-08-27 | 79045.95 | 0.280 | ES10009
7463 | MISSOURI | Completed | C950 | Ferryboat | MISSOURI | LEWIS |  | 09 | FB03006 | This project involves port capital improvements. These improvements include making the existing road and staging area concrete, installing public restrooms and storage depot, and improving existing docking ramp | Other | 2010-01-05 | 2010-01-05 | 2012-03-01 | 2012-08-04 | 174531.6 | 0.000 | FB03006
7464 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STE GENEVIEVE |  | 03 | FB08001 | This project is located at the Port of New Bourbon and consit of a ferry boat berthing, bank stabiization an construction of a mooring structure in Ste. Genevieve C | Other | 2009-04-01 | 2010-04-18 | 2012-03-01 | 2012-02-28 | 68183.19 | 0.000 | FB08001
7465 | MISSOURI | Underway | C950 | Ferryboat | MISSOURI | MISSISSIPPI |  | 08 | FB10010 | This project invovles the installation of new enginees and coolers on an existing tug, and the purchase of a new barge. | Other | 2010-02-08 | 2010-02-22 | 2012-03-12 |  | 957500 | 0.000 | FB10010
7466 | MISSOURI | Completed | C490 | OJT/SS | MISSOURI | STATEWIDE |  |  | FY09005 | The project is part of an ongoing program that is designed to increase participation among minorities, women and disadvantaged individuals in the highway construction workforce and train and prepare i | Other | 2010-01-13 | 2010-01-13 | 2011-12-31 | 2011-08-16 | 145000 | 0.000 | FY09005
7467 | MISSOURI | Completed | C490 | OJT/SS | MISSOURI | BOONE |  | 09 | FY09006 | The project is part of an ongoing program that provides minorities, women and disadvantaged individuals the educational experiences to enhance work maturity skills, GED attainment, tools, equipment an | Other | 2010-01-13 | 2010-01-13 | 2011-12-31 | 2011-08-24 | 190433.54 | 0.000 | FY09006
7468 | MISSOURI | Completed | C490 | OJT/SS | MISSOURI | JACKSON |  | 04 | FY10005 | This project consist of on the job training, supportive services, OJT/SS program in Kansas C | Other | 2010-07-27 | 2010-07-27 | 2011-12-31 | 2011-11-01 | 231038.3 | 0.000 | FY10005
7469 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ATCHISON |  | 06 | S001011 | This project consist of a thin lift asphalt overlay from Route 136 to I-29 in Atchison county | Pavement Improvement | 2009-06-08 | 2009-06-29 | 2009-10-01 | 2009-09-30 | 267860.32 | 3.750 | S001011
7470 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | NODAWAY |  | 06 | S004007 | This project consist of a thin lift asphalt overlay from Route 148 to Route E in Nodaway county | Pavement Improvement | 2009-07-06 | 2009-08-24 | 2010-07-01 | 2009-09-24 | 395140.08 | 8.133 | S004007
7471 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | NODAWAY |  | 06 | S006009 | This project consist of resurfacing roadway from Maryville west city limits to east city limits - Nodaway county | Pavement Improvement | 2010-03-08 | 2010-05-28 | 2010-12-01 | 2010-08-25 | 493913.06 | 2.299 | S006009
7472 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ATCHISON |  | 06 | S007006 | This project consist of a thin lift asphalt overlay from Route C to Route 136 in Atchison county | Pavement Improvement | 2009-06-08 | 2009-06-29 | 2009-10-01 | 2009-09-30 | 593013.14 | 9.881 | S007006
7473 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ANDREW |  | 06 | S029004 | This project consist of a thin lift asphalt overlay from Route 48 to Route E in Andrew county | Pavement Improvement | 2009-07-06 | 2009-08-24 | 2010-07-01 | 2009-10-21 | 420917.25 | 7.984 | S029004
7474 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | S042005 | This project consist of a thin lift asphalt overlay to improve pavement condition from Route 6 to Route OO, near Clarksdale - Buchanan/Dekalb county | Pavement Improvement | 2010-03-08 | 2010-04-01 | 2010-11-01 | 2010-04-08 | 412652.93 | 8.253 | S042005
7475 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | S058005 | This project consist of a thin lift asphalt overlay from Route 371 to Route MM in Buchanan county | Pavement Improvement | 2009-07-06 | 2009-09-25 | 2010-07-01 | 2009-11-30 | 213527.81 | 4.036 | S058005
7476 | MISSOURI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | CLINTON |  | 06 | S067011 | This project consist of a thin lift asphalt overlay from Route 69 to Route H in Clinton county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-12-03 | 599812.81 | 11.022 | S067011
7477 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BUCHANAN |  | 06 | S083013 | "This project consists of concrete pavement repair to the existing concrete roadway and a 3-3/4"" asphalt overlay over the existing concrete roadway along with a 3-3/4"" asphalt overlay of the existin | Pavement Improvement | 2009-08-10 | 2009-09-10 | 2009-12-01 | 2009-11-30 | 1886410.39 | 2.400 | S083013
7478 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LIVINGSTON |  | 06 | S111009 | This project consist of a thin lift asphalt overlay from the Daviess County line to Route 65 in Livingston county | Pavement Improvement | 2009-06-08 | 2009-08-06 | 2009-11-01 | 2009-09-09 | 1228044.9 | 12.130 | S111009
7479 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | MACON |  | 09 | S116007 | This project consist of a thin lift asphalt overlay from Route 63 to Route 156 in LaPlata in Macon county | Pavement Improvement | 2009-04-06 | 2009-04-10 | 2009-12-01 | 2009-04-15 | 74654.59 | 0.916 | S116007
7480 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MACON |  | 09 | S124007 | This project consist of a thin lift asphalt overlay in Macon County from Route 63 to the Knox county line | Pavement Improvement | 2009-04-06 | 2009-04-10 | 2009-12-01 | 2009-04-24 | 541918.62 | 8.989 | S124007
7481 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S148003 | This project consist of resurfacing roadway from Business 63 to Route 63 - Randolph county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-06-08 | 148171.91 | 1.067 | S148003
7482 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S152001 | This project consist of resurfacing roadway from Business 63 to Route 63 - Randolph county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-07-21 | 115390.4 | 1.096 | S152001
7483 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LEWIS |  | 09 | S182010 | This project consist of a thin lift asphalt overlay from Route 67 in Ewing to Route 61 - Lewis county | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-11-01 | 2010-09-28 | 560300 | 12.576 | S182010
7484 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | SCHUYLER |  | 06 | S189007 | This project consist of a thin lift asphalt overlay from the Iowa state line to Route 63 in Schuyler county | Pavement Improvement | 2009-04-06 | 2009-04-10 | 2009-12-01 | 2009-04-25 | 547629.5 | 8.502 | S189007
7485 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MARION |  | 09 | S192003 | This project consist of a thin lift asphalt overlay on Route W from Route 61 north junction to Route 61 south junction, and Route 61 outer road from Route W to 0.3 miles south of Route W in Marion county | Pavement Improvement | 2009-04-06 | 2009-05-12 | 2009-12-01 | 2009-06-02 | 179958.87 | 3.378 | S192003
7486 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S197005 | This project consist of resurfacing roadway from Macon county line to Route JJ - Randolph county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-06-28 | 885200 | 13.515 | S197005
7487 | MISSOURI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S203003 | This project consist of resurfacing roadway from County Road 103 to Route 24 - Randolph county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-06-08 | 141559.17 | 2.225 | S203003
7488 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RANDOLPH |  | 09 | S205005 | This project consist of a thin lift asphalt overlay from Business Route 63 to Route B in Randolph county | Pavement Improvement | 2009-06-08 | 2009-10-23 | 2009-12-01 | 2009-10-28 | 577607.51 | 9.560 | S205005
7489 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MONROE |  | 09 | S206007 | This project consist of a thin lift asphalt overlay from Route 24 to Route J in Ralls and Monroe counties | Pavement Improvement | 2009-04-06 | 2009-05-12 | 2009-12-01 | 2009-05-28 | 228386.46 | 4.006 | S206007
7490 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | S209017 | This project consist of resurfacing roadway from Route TT to I-70 Drive SW in the City of Columbia - Boone county | Pavement Improvement | 2010-03-08 | 2010-04-06 | 2010-12-01 | 2010-07-16 | 47499.67 | 1.113 | S209017
7491 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | SHELBY |  | 09 | S233005 | This project consist of a thin lift asphalt overlay from Business Route 36 to Route 24 in Shelby and Monroe counties | Pavement Improvement | 2009-06-08 | 2009-10-23 | 2009-12-01 | 2009-11-10 | 1123546.94 | 22.130 | S233005
7492 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | MONROE |  | 09 | S249007 | This project consist of a thin lift asphalt overlay from Route 24 in Madison to the Audrain county line - Monroe county | Pavement Improvement | 2010-02-08 | 2010-05-04 | 2010-11-01 | 2010-06-08 | 434212.05 | 9.725 | S249007
7493 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LINCOLN |  | 02 | S258009 | This project consist of a thin lift asphalt overlay from Route O to north junction to Route UU in Silex - Lincoln county | Pavement Improvement | 2010-02-08 | 2010-05-24 | 2010-11-01 | 2010-06-08 | 478200 | 10.886 | S258009
7494 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LINCOLN |  | 02 | S264004 | This project consist of a thin lift asphalt overlay from Old Route 61 to Route W in Lincoln county | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-01 | 2009-07-13 | 305352.49 | 6.361 | S264004
7495 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LINCOLN |  | 02 | S270004 | This project consist of a thin lift asphalt overlay from Route Y to Route 47 in Lincoln county | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-01 | 2009-06-25 | 261982.39 | 5.259 | S270004
7496 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | AUDRAIN |  | 09 | S273003 | This project consist of a thin lift asphalt overlay from Route V in Vandalia to Roue K east junction - Audrain county | Pavement Improvement | 2010-02-08 | 2010-05-24 | 2010-11-01 | 2010-07-15 | 375800 | 10.886 | S273003
7497 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LEWIS |  | 09 | S283005 | This project consist of a thin lift asphalt overlay from Route E to Route 6 in LaBelle - Lewis county | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-11-01 | 2010-04-08 | 377400 | 8.183 | S283005
7498 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | S286005 | This project consist of pavement improvements on Route 273 from Route JJ to I-29 and Spur 92 from Route 273 to Route 92 in Platte county | Pavement Improvement | 2009-06-08 | 2009-10-05 | 2009-12-01 | 2009-11-30 | 566545.02 | 4.907 | S286005
7499 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PLATTE |  | 06 | S290005 | This project consist of a bridge replacement over I-29 in Platte City. Project involves bridge A0200 | Bridge Replacement | 2010-03-08 | 2010-04-01 | 2010-10-01 | 2010-07-22 | 1117203.88 | 0.010 | S290005
7500 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RALLS |  | 09 | S301018 | This project consist of a thin lift asphalt overlay from Route EE to Route 154 in Ralls county | Pavement Improvement | 2009-04-06 | 2009-05-12 | 2009-12-01 | 2009-05-20 | 414988.04 | 7.713 | S301018
7501 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RALLS |  | 09 | S301019 | This project consist of a thin lift asphalt overlay from Route J to Route 19 in Ralls county | Pavement Improvement | 2009-04-06 | 2009-05-12 | 2009-12-01 | 2009-05-19 | 248345.13 | 4.684 | S301019
7502 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | CLAY |  | 06 | S304023 | A $1.2 million contract awarded to Musselman and Hall Contractors, LLC for nearly three miles of sidewalk improvements. Included are new upgrades to the existing sidewalk and adding curb ramps to acco | Transportation Enhancements | 2009-08-10 | 2009-08-10 | 2010-02-01 | 2009-12-01 | 1373073.14 | 2.623 | S304023
7503 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STATEWIDE |  |  | S321005 | This project consist of a thin lift asphalt overlay from Route 47 to the Warren County line in Lincoln County, and from the Lincoln County line to I-70 north outer road in Warren county | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-01 | 2009-09-30 | 542103.37 | 11.537 | S321005
7504 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | LINCOLN |  | 02 | S321006 | This project consist of a thin lift asphalt overlay from Route Z to Route E in Silex - Lincoln county | Pavement Improvement | 2010-02-08 | 2010-05-24 | 2010-11-01 | 2010-05-27 | 198700 | 4.456 | S321006
7505 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PIKE |  | 09 | S328004 | This project consist of a thin lift asphalt overlay from Business 61 in Bowling Green to County Road 486 - Pike county | Pavement Improvement | 2010-02-08 | 2010-05-24 | 2010-11-01 | 2010-09-10 | 130700 | 2.360 | S328004
7506 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | S340011 | This project consist of resurfacing roadway from North Fork Creek in the City of Columbia to Route J in Boone county | Pavement Improvement | 2010-03-08 | 2010-04-06 | 2010-12-01 | 2010-07-16 | 474752.55 | 8.900 | S340011
7507 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | S342002 | This project consist of resurfacing roadway from Route K to the end of maintenance in the City of Columbia - Boone county | Pavement Improvement | 2010-03-08 | 2010-04-06 | 2010-12-01 | 2010-07-16 | 98189.77 | 18.597 | S342002
7508 | MISSOURI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | RAY |  | 04 | S349005 | This project consist of a thin lift asphalt overlay from Route C to Route 10 in Ray county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-12-03 | 281304.36 | 5.763 | S349005
7509 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | RAY |  | 04 | S351005 | This project consist of a thin lift asphalt overlay from Route U to Route 10 in Ray county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-12-03 | 231387.71 | 5.117 | S351005
7510 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | BOONE |  | 09 | S375003 | This project consist of a thin lift asphalt overlay from Route 124 to I-70 | Pavement Improvement | 2009-06-08 | 2009-08-10 | 2009-12-01 | 2009-11-03 | 856658.77 | 19.186 | S375003
7511 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | CALLOWAY |  | 09 | S383010 | This project will widen Route OO in Callaway couty to three lanes to add capacity and improve safty in holts Summit. | Pavement Widening | 2009-09-15 | 2009-09-15 | 2010-12-01 | 2010-11-17 | 449716.85 | 0.841 | S383010
7512 | MISSOURI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | LAFAYETTE |  | 04 | S388005 | This project consist of a thin lift asphalt overlay from Gillespie Drive to Route O in LaFayette county | Pavement Improvement | 2009-04-06 | 2009-10-30 | 2009-12-01 | 2009-12-03 | 552746.39 | 12.287 | S388005
7513 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WARREN |  | 09 | S417004 | This project consist of improvements on intersection and outer road, which is located 0.2 miles south of I-70 in Warren county | Pavement Improvement | 2010-02-08 | 2010-02-08 | 2010-12-01 | 2010-09-30 | 509306.58 | 0.631 | S417004
7514 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WARREN |  | 09 | S429007 | This project consist of a thin lift asphalt overlay from Route T to Route 94 in Warren and St. Charles counties | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-01 | 2009-07-23 | 179695.27 | 3.500 | S429007
7515 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S434005 | This project consist of intersection improvements at Winchester Road in Sedalia in Pettis county | Pavement Improvement | 2010-01-04 | 2010-04-01 | 2010-12-01 | 2010-06-10 | 354059.03 | 0.300 | S434005
7516 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S434006 | This project consist of resurfacing roadway from the railroad tracks to Route 65 in Sedalia in Pettis county | Pavement Improvement | 2010-03-08 | 2010-04-13 | 2010-12-01 | 2010-10-22 | 326363.51 | 1.336 | S434006
7517 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S434007 | This project consist of resurfacing roadway from west of Route 65 to Quisenberry Road in the City of Sedalia - Pettis county | Pavement Improvement | 2010-03-08 | 2010-04-14 | 2010-12-01 | 2010-05-21 | 86346.1 | 2.000 | S434007
7518 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S434008 | This project consist of resurfacing various roadways within the Missouri State fairgrounds in the City of Sedalia - Pettis county | Pavement Improvement | 2010-03-08 | 2010-04-14 | 2010-12-01 | 2010-05-06 | 212019.54 | 0.003 | S434008
7519 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | JOHNSON |  | 04 | S467005 | This project consist of pavement improvements from Route 50 to Route 2 in Johnson county | Pavement Improvement | 2009-06-08 | 2009-08-18 | 2009-12-01 | 2009-10-14 | 1258926.82 | 16.143 | S467005
7520 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | COLE |  | 04 | S490010 | This project consists of improvements at the intersection of Route 50 and Route 179 in Jefferson City. | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2011-07-01 | 2010-11-01 | 6912335.67 | 0.300 | S490010
7521 | MISSOURI | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | MONITEAU |  | 04 | S498006 | This project consist of pavement improvements from Route AA to Route 52 in Cole, Moniteau, and Morgan counties | Pavement Improvement | 2009-05-26 | 2009-06-10 | 2009-12-01 | 2009-08-28 | 2071328.66 | 21.100 | S498006
7522 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | PETTIS |  | 04 | S539008 | This project consist of a thin lift resurfacing from the intersection of 28th street and Ingrm Avenue to Route V, south of Sedalia - Pettis county | Pavement Improvement | 2010-03-08 | 2010-04-14 | 2010-12-01 | 2010-05-03 | 319800 | 8.010 | S539008
7523 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | COOPER |  | 06 | S567005 | This project consist of a thin lift resurfacing from Route 135 to old Route 50 - Cooper county | Pavement Improvement | 2010-03-08 | 2010-04-14 | 2010-12-01 | 2010-05-14 | 306439.9 | 7.838 | S567005
7524 | MISSOURI | Completed | C200,C240 | Highway Infrastructure Investment Grant | MISSOURI | COOPER |  | 06 | S573009 | This project consist of pavement improvements from I-70 to Main Street (old Route B) in the City of Booneville - Cooper county | Pavement Improvement | 2010-02-08 | 2010-03-22 | 2010-11-01 | 2010-07-06 | 1644521.53 | 3.406 | S573009
7525 | MISSOURI | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | MONITEAU |  | 04 | S579017 | This project consist of a thin lift asphalt overlay from Route O to Route C in Moniteau county | Pavement Improvement | 2009-06-08 | 2009-06-12 | 2009-12-01 | 2009-10-19 | 552815.17 | 10.500 | S579017
7526 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | MILLER |  | 09 | S579018 | This project consist of resurfacing roadway from Salem Road to Route 54 in the City of Eldon - Miller county | Pavement Improvement | 2010-03-08 | 2010-05-03 | 2010-12-01 | 2010-06-04 | 122219.51 | 2.331 | S579018
7527 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | MILLER |  | 09 | S583009 | This project consist of resurfacing roadway from Salem Road to Route 52 in the City of Eldon - Miller county | Pavement Improvement | 2010-03-03 | 2010-05-03 | 2010-12-01 | 2010-06-04 | 79907.87 | 1.301 | S583009
7528 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | ST FRANCOIS |  | 08 | S638004 | This project consist of a thin lift asphalt overlay from the Washington County line to the City of Bonne Terre in St. Francois county | Pavement Improvement | 2009-06-08 | 2009-09-03 | 2009-12-01 | 2009-09-16 | 181075 | 5.219 | S638004
7529 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | ST FRANCOIS |  | 08 | S638005 | This project consist of a thin lift asphalt overlay from the City of Bonne Terre to Route 67 in St. Francois county | Pavement Improvement | 2009-06-08 | 2009-09-03 | 2009-12-01 | 2009-09-16 | 104275.83 | 1.788 | S638005
7530 | MISSOURI | Completed | C220 | Highway Infrastructure Investment Grant | MISSOURI | IRON |  | 08 | S670010 | This project consistes of ADA sidewalk improvements on Route M from Shepherd Mountain Road to Burnett Street in Ironton, 0.275 miles. | Transportation Enhancements | 2010-01-04 | 2010-03-29 | 2010-06-01 | 2010-04-20 | 122869.5 | 0.282 | S670010
7531 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | VERNON |  | 04 | S706003 | This project consist of a thin lift asphalt overlay from Route 54 to 0.9 mile north of Highland in Vernon county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-04-27 | 111147.54 | 2.377 | S706003
7532 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | VERNON |  | 04 | S708004 | This project consist of a thin lift asphalt overlay from Business 71 to County Road 507 in Vernon county | Pavement Improvement | 2009-04-20 | 2009-04-18 | 2009-12-01 | 2009-05-07 | 110527.8 | 2.489 | S708004
7533 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | VERNON |  | 04 | S710009 | This project consist of a thin lift asphalt overlay from Route 54 to Route F in Vernon county | Pavement Improvement | 2009-04-18 | 2009-04-20 | 2009-12-01 | 2009-04-27 | 259900.93 | 5.913 | S710009
7534 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | POLK |  | 04 | S736004 | This project consist of a thin lift asphalt overlay from Route 123 to Route 13 in Polk county | Pavement Improvement | 2009-06-08 | 2009-07-14 | 2009-12-01 | 2009-09-14 | 333600 | 10.900 | S736004
7535 | MISSOURI | Completed | C250 | Highway Infrastructure Investment Grant | MISSOURI | WASHINGTON |  | 08 | S755002 | This project consist of resurfacing roadway from Route 8 to Route 21 in Potosi - Washington county | Pavement Improvement | 2010-03-08 | 2010-04-26 | 2010-12-01 | 2010-10-28 | 90998.66 | 1.518 | S755002
7536 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | JASPER |  | 07 | S770004 | This project consist of a thin lift asphalt overlay from Route J to Route 66 in Jasper county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-06-18 | 208244.24 | 4.446 | S770004
7537 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | JASPER |  | 07 | S776011 | This project consist of widening Route FF to include a center two-way left turn lane form US 71 to Prigmor Avenue in Jasper/Newton counties | Pavement Improvement | 2009-08-03 | 2009-09-30 | 2010-11-01 | 2010-07-01 | 1939830.56 | 1.169 | S776011
7538 | MISSOURI | Completed | C200 | Highway Infrastructure Investment Grant | MISSOURI | JASPER | JOPLIN | 07 | S776012 | This project consists of constructing new signalized intersection and turn lanes on route FF, one mile east of Route 71. Work includes grading, asphalt pavement and new signals. | Pavement Improvement | 2009-05-29 | 2009-05-29 | 2010-11-01 | 2010-07-01 | 1376841.2 | 0.200 | S776012
7539 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STE GENEVIEVE |  | 03 | S805002 | This project consists of bridge replacement, asphalt overlay and shoulder widening on Route B in Ste Genevieve county. | Pavement Widening | 2010-02-25 | 2010-02-25 | 2010-12-01 | 2010-11-19 | 2924762.15 | 13.756 | S805002
7540 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | STE GENEVIEVE |  | 03 | S811005 | This project consist of a thin lift asphalt overlay from Route 51 to Route 61 in Ste. Genevieve and Perry counties | Pavement Improvement | 2009-06-08 | 2009-09-03 | 2009-12-01 | 2009-09-12 | 329807.35 | 6.844 | S811005
7541 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | JASPER |  | 07 | S853002 | This project consist of a thin lift asphalt overlay from Route Z to Route P in Jasper county | Pavement Improvement | 2009-04-18 | 2009-04-18 | 2009-12-01 | 2009-06-18 | 169926.73 | 3.959 | S853002
7542 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WRIGHT |  | 08 | S926008 | This project consist of a thin lift asphalt overlay from Hartville to Route 95 - Wright county | Pavement Improvement | 2010-02-08 | 2010-09-17 | 2010-12-01 | 2010-09-17 | 568200 | 12.949 | S926008
7543 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | S938008 | This project consist of a thin lift asphalt overlay from Route AB to Route 160 in Greene county | Pavement Improvement | 2009-06-08 | 2009-07-14 | 2009-12-01 | 2009-08-19 | 260617.29 | 5.417 | S938008
7544 | MISSOURI | Completed | C250,C240 | Highway Infrastructure Investment Grant | MISSOURI | WEBSTER |  | 04 | S946008 | This project consist of a thin lift asphalt overlay from Route 60 to 1.0 mile west of Route FF in Webster county | Pavement Improvement | 2009-06-08 | 2009-09-09 | 2009-12-01 | 2009-09-25 | 51870.58 | 1.780 | S946008
7545 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | S947011 | This project consist of a thin lift asphalt overlay from south of Route KK to north of Valley Water Mill Road in Greene county | Pavement Improvement | 2009-06-08 | 2009-09-11 | 2009-12-01 | 2009-12-01 | 158145.83 | 3.857 | S947011
7546 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | POLK |  | 04 | S947012 | This project consist of pavement and shoulder improvements from Route 32 to Route WW in Polk and Greene counties | Pavement Improvement | 2009-06-08 | 2009-09-11 | 2009-12-01 | 2009-12-01 | 1273000 | 20.570 | S947012
7547 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | GREENE |  | 07 | S953005 | This project consist of a thin lift asphalt overlay from Route 160 to Route 266 in Greene county | Pavement Improvement | 2009-06-08 | 2009-07-14 | 2009-12-01 | 2009-08-19 | 297598.83 | 6.121 | S953005
7548 | MISSOURI | Completed | C240 | Highway Infrastructure Investment Grant | MISSOURI | WEBSTER |  | 04 | S967004 | This project consist of a thin lift asphalt overlay from Route AD to Business Route 60 in Webster county | Pavement Improvement | 2009-06-08 | 2009-09-09 | 2009-12-01 | 2009-09-25 | 163937.35 | 5.683 | S967004
7549 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | MCCONE, CARTER, PHILLIPS, DAWSON, PRAIRIE, WIBAUX, VALLEY |  | 01 | 0002874 | Glendive District multiple location culvert replacement, abandonment, and major maintenance project. | Bridge Improvement | 2010-02-22 | 2010-04-09 | 2011-01-20 | 2011-12-07 | 2545862 |  | 0002874
7550 | MONTANA | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 0015090 | Construct New Bypass segment - US 93 to Airport Road | New Construction | 2009-12-21 | 2009-12-28 | 2011-12-20 | 2012-02-24 | 8148323 |  | 0015090
7551 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 0015091 | Construct New Bypass segment - Airport Road to Foys Lake Road | New Construction | 2009-11-30 | 2010-02-03 | 2011-12-20 | 2011-11-29 | 5361624 |  | 0015091
7552 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 0015092 | Construct New Bypass segment - Foys Lake Road to US 2 | New Construction | 2009-11-30 | 2010-02-03 | 2011-12-20 | 2011-11-29 | 7780165 |  | 0015092
7553 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 0016073 | Wetland mitigation in the NW quadrant of the I-90 East Main Street Interchange in Bozeman. | Other | 2009-07-06 | 2009-08-03 | 2009-12-01 | 2010-01-04 | 297781.83 |  | 0016073
7554 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 0025050 | Reconstruction of existing Wylie Drive in Lewis & Clark County. | Safety/Traffic Management | 2009-08-03 | 2009-08-03 | 2010-12-20 | 2010-10-26 | 1160898 |  | 0025050
7555 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | TETON |  | 01 | 0032033 | Replacement of the US 89 Big Muddy Creek Bridge, North of Bynum | Bridge Replacement | 2009-07-20 | 2009-09-10 | 2010-12-20 | 2011-12-14 | 2571581 | 0.400 | 0032033
7556 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | GLACIER |  | 01 | 0034013 | Overlay, Slope Flattening & Widening on US 89 within the Blackfeet Reservation | Pavement Improvement | 2009-07-06 | 2009-07-13 | 2010-12-20 | 2011-09-19 | 10519169.04 | 8.930 | 0034013
7557 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | PARK |  | 01 | 0034026 | Off site wetland mitigation reserve for Watershed #13 - Upper Yellowstone in Park County | Other | 2009-07-20 | 2009-09-09 | 2009-12-01 | 2010-06-10 | 390806.9 |  | 0034026
7558 | MONTANA | Completed | C220,C240 | Highway Infrastructure Investment Grant | MONTANA | LAKE |  | 01 | 0052152 | Construct a Bicycle/Pedestrian Overcrossing Bridge over US 93 in Pablo. | Transportation Enhancements | 2010-04-26 | 2010-05-03 | 2011-01-01 | 2012-04-09 | 2732433.36 | 0.000 | 0052152
7559 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | RAVALLI |  | 01 | 0071118 | Reconstruct and widen approximately 1.8 miles of US-93 near Stevensville | Pavement Widening | 2009-08-12 | 2009-08-17 | 2010-12-20 | 2010-12-09 | 5405512 | 1.855 | 0071118
7560 | MONTANA | Underway | C200,C240 | Highway Infrastructure Investment Grant | MONTANA | ROOSEVELT |  | 01 | 0110062 | Reconstructing 6.8 miles of US 2, starting 6.69 miles east of Brockton in Roosevelt County. | Pavement Improvement | 2010-11-16 | 2010-11-17 | 2012-12-20 |  | 6802132.02 | 6.790 | 0110062
7561 | MONTANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | MONTANA | PARK |  | 01 | 0111051 | 4.7 mile mill and ovelay of P-11 northeast of Livingston | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-12-20 | 2011-01-31 | 2762413 | 4.700 | 0111051
7562 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | MADISON |  | 01 | 0131045 | Replacement of an existing irrigation siphon with a culvert on US 287 south of Cameron | Pavement Improvement | 2009-10-05 | 2009-10-21 | 2010-06-01 | 2010-05-25 | 349126.76 | 0.000 | 0131045
7563 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | SILVER BOW |  | 01 | 0152081 | Replace I-15 Structures near Butte. | Pavement Improvement | 2010-04-05 | 2010-04-12 | 2012-12-20 | 2012-12-28 | 7302564 | 1.311 | 0152081
7564 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 0154089 | I 15 Dearborn Rest Area Replacement | Safety/Traffic Management | 2009-08-14 | 2010-01-08 | 2010-12-20 | 2012-07-28 | 3698786 |  | 0154089
7565 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | CARTER |  | 01 | 0271009 | Bridge Replacement Project on MT 7 North of Ekalaka | Pavement Improvement | 2009-08-03 | 2009-09-15 | 2010-12-20 | 2011-12-29 | 2236426 | 0.000 | 0271009
7566 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | FALLON |  | 01 | 0272019 | Reconstruction of the existing roadway and structure work on MT 7 | Pavement Improvement | 2009-09-21 | 2009-09-28 | 2011-12-20 | 2012-10-05 | 7061998 | 5.321 | 0272019
7567 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | DANIELS |  | 01 | 0322016 | 14.2 mile chip seal on MT 13 in Daniels County north of Scoby | Pavement Improvement | 2009-06-15 | 2009-06-29 | 2009-12-20 | 2009-12-21 | 450273.2 | 14.292 | 0322016
7568 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | SHERIDAN |  | 01 | 0341009 | 15.3 mile overlay on MT 16 between Plentywood and the Port of Raymond in Sheridan County. | Pavement Improvement | 2009-08-17 | 2010-06-01 | 2010-12-20 | 2010-11-19 | 2612251 | 15.300 | 0341009
7569 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | LAKE, SANDERS, FLATHEAD |  | 01 | 0361011 | Reconstruct a 10 mile segment of MT-28, beginning at milepost 26.1 and ending approximately 10 miles west of Dayton. | Pavement Improvement | 2010-03-01 | 2010-03-02 | 2012-12-20 | 2011-12-27 | 6465635 | 10.000 | 0361011
7570 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | BIG HORN |  | 01 | 0371033 | Mill and fill 5.5 miles of US 212 in Big Horn County and within the Northern Cheyenne Reservation. | Pavement Improvement | 2009-07-17 | 2009-07-21 | 2010-12-20 | 2009-12-04 | 2144398.99 | 5.580 | 0371033
7571 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | ROSEBUD |  | 01 | 0391039 | 8.1 mile pavement preservation, minor widening & pavement marking/guardrail upgrade on MT 39 in Rosebud County, just north of the Northern Cheyenne Reservation. | Pavement Improvement | 2009-06-08 | 2009-06-12 | 2009-12-20 | 2009-12-08 | 1360255.2 | 8.168 | 0391039
7572 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | DAWSON |  | 01 | 0512004 | 9 mile overlay on MT 200 west of Richey, in Dawson County | Pavement Improvement | 2009-06-22 | 2009-07-13 | 2009-12-20 | 2009-12-21 | 1989865.8 | 9.030 | 0512004
7573 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 0602073 | Reconstruct 0.65 mile segment of 10th Avenue South - between 26th and 20th St in Great Falls | Pavement Widening | 2010-03-15 | 2010-03-15 | 2011-12-20 | 2012-01-05 | 3870925 | 0.650 | 0602073
7574 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | JEFFERSON |  | 01 | 0691027 | Widen and overlay the existing MT 69 roadway south of Elk Horn Road, south east of Boulder. | Pavement Improvement | 2010-03-08 | 2010-04-05 | 2011-12-20 | 2011-11-16 | 7195220 | 9.500 | 0691027
7575 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 0861040 | 14.6 mile chip seal on MT 86 northeast of Bozeman in Gallatin County. | Pavement Improvement | 2009-07-06 | 2009-07-13 | 2009-12-20 | 2009-10-22 | 830804.85 | 14.630 | 0861040
7576 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 0906087 | Reconstruction of the I-90 East Three Forks Interchange | Pavement Improvement | 2009-10-05 | 2009-10-19 | 2011-12-20 | 2011-02-02 | 3437768 | 0.265 | 0906087
7577 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | SWEET GRASS |  | 01 | 0907089 | 5 mile mill and resurface of I 90 in Sweet Grass County | Pavement Improvement | 2009-08-17 | 2010-04-05 | 2010-12-20 | 2010-11-22 | 2703657 | 5.003 | 0907089
7578 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 0908157 | Cold mill and overlay I -90 at the Pinehills Interchange and 3.2 miles to the west. | Pavement Improvement | 2009-08-05 | 2009-08-08 | 2009-12-20 | 2009-12-04 | 1152304.1 | 3.285 | 0908157
7579 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE, BIG HORN |  | 01 | 0909098 | 13.3 mile full width overlay of I 90. Ramps will be cold milled and overlaid. The rest area parking lot will be crack sealed and s&c. | Pavement Improvement | 2009-06-01 | 2009-08-13 | 2010-12-20 | 2010-12-01 | 8170364 | 13.300 | 0909098
7580 | MONTANA | Completed | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE |  | 01 | 0941068 | Mill, overlay, and seal & cover a 12.1 mile segment of the I-94 roadway and bridge decks fromPompey's Pillar to Waco, east of Billings | Pavement Improvement | 2010-07-06 | 2010-09-21 | 2011-12-20 | 2011-12-27 | 4307668 | 12.122 | 0941068
7581 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | CUSTER, ROSEBUD, DAWSON, WIBAUX |  | 01 | 0943059 | I 94 Bridge Deck Rehabilitation In Rosebud County | Bridge Improvement | 2009-08-03 | 2009-08-10 | 2010-12-20 | 2011-11-01 | 5498221 | 0.000 | 0943059
7582 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | WIBAUX |  | 01 | 0947028 | 6.2 mile mill and fill on I 94 east of Wibaux, in Wibaux County. | Pavement Improvement | 2009-07-20 | 2009-07-21 | 2009-12-20 | 2009-10-22 | 1078036.68 | 6.298 | 0947028
7583 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 1011004 | Reconstruction of the Smelter Ave. & 10th St. North Intersection | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-12-20 | 2010-11-23 | 1920221 | 0.000 | 1011004
7584 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 1028004 | 1.4 mile overlay on Hardin Road in Billings | Pavement Improvement | 2009-06-01 | 2009-06-26 | 2010-06-01 | 2010-09-14 | 484031 | 1.460 | 1028004
7585 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 1031009 | Reconstruct an approximate 1.7 mile segment of Shilo Road from 2 lane to 4 lane - Billings | Pavement Widening | 2009-06-01 | 2009-06-15 | 2010-12-20 | 2011-09-20 | 9301727 | 1.714 | 1031009
7586 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 1031011 | Reconstruct the remaining 2.11 mile segment of Shiloh Road - Billings | Pavement Widening | 2009-11-02 | 2009-11-13 | 2011-12-20 | 2011-12-08 | 5356482 | 2.117 | 1031011
7587 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE | BILLINGS | 01 | 1099068 | Includes constructing a 200 foot long tunnel and approximately 300 feet of hard surface for a bike/ped facility under Main Street at Alkali Creek in Billings. | Transportation Enhancements | 2010-07-07 | 2010-07-07 | 2011-01-01 | 2010-12-13 | 1000000 | 0.001 | 1099068
7588 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | SILVER BOW |  | 01 | 1806008 | 0.7 mile mill and fill on Front Street in Butte | Pavement Improvement | 2009-06-22 | 2009-06-23 | 2010-12-20 | 2010-12-20 | 1531273 | 0.700 | 1806008
7589 | MONTANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | MONTANA | SILVER BOW |  | 01 | 1810004 | Seal and Cover existing roadway on Grand Avenue -between Florence and Continental in Butte | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2010-12-20 | 2011-11-17 | 1293112 | 1.300 | 1810004
7590 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | PHILLIPS |  | 01 | 2081006 | Reconstruction of 9.4 miles of Secondary 208 between Whitewater and US 191 | Pavement Improvement | 2009-11-30 | 2010-03-29 | 2012-12-20 | 2012-08-10 | 5849877 | 9.424 | 2081006
7591 | MONTANA | Underway | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 2351009 | Reconstruct the remaining section of State Secondary 235 east of MT 85, from mile point 0.00 to 1.95 (Love Lane), Gallatin County. | Pavement Improvement | 2010-11-16 | 2010-12-20 | 2012-12-20 |  | 4220424 | 1.950 | 2351009
7592 | MONTANA | Completed | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | GALLATIN |  | 01 | 2351011 | Reconstruct existing State Secondary 235 east of MT 85 | Pavement Improvement | 2009-10-05 | 2009-10-29 | 2010-12-20 | 2012-02-08 | 5199155 | 2.550 | 2351011
7593 | MONTANA | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | LINCOLN |  | 01 | 2601005 | 3.5 mile chip seal on S 260 north of Libby | Pavement Improvement | 2009-07-06 | 2009-07-07 | 2009-12-20 | 2009-10-05 | 167705.45 | 3.500 | 2601005
7594 | MONTANA | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | GRANITE |  | 01 | 2711010 | 2.3 mile chip seal on S 271 northeast of Drummond in Powell County | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2009-12-20 | 2009-09-11 | 98178.62 | 2.300 | 2711010
7595 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 2791013 | Installing post mounted flashers at the intersection of S-279 & S 231 north of Helena | Safety/Traffic Management | 2009-08-03 | 2009-08-20 | 2009-11-01 | 2010-04-19 | 29952.02 | 0.800 | 2791013
7596 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 2801019 | Installing post mounted flashers on York Road northeast of Helena | Safety/Traffic Management | 2009-08-03 | 2009-08-20 | 2009-11-01 | 2010-04-19 | 31339.73 | 0.200 | 2801019
7597 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | MEAGHER |  | 01 | 2941008 | Reconstruction of the roadway and structure work on State Secondary 294 | Pavement Improvement | 2010-01-04 | 2010-03-02 | 2011-12-20 | 2012-01-11 | 4001426 | 2.120 | 2941008
7598 | MONTANA | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | CARBON |  | 01 | 3081026 | 7.7 mile overlay on S-308 in Carbon County west of Belfry | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-12-20 | 2009-12-23 | 1271776.2 | 7.700 | 3081026
7599 | MONTANA | Completed | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | CARTER |  | 01 | 3231029 | Pave State Secondary 323 from RP 24.83 to 37.1 This is the section that is currently under contract with a total reconstruct to a all weather gravel surface. | Pavement Improvement | 2009-07-06 | 2009-07-16 | 2010-12-20 | 2012-12-19 | 8103869 | 12.274 | 3231029
7600 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 3275813 | 2.6 mile seal and cover on a state highway west of Missoula. | Pavement Improvement | 2009-07-06 | 2009-07-07 | 2009-12-20 | 2009-10-27 | 254647.34 | 2.600 | 3275813
7601 | MONTANA | Completed | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | STILLWATER |  | 01 | 4211004 | Reconstruction of the existing roadway and constructing bus turn arounds on State Secondary 421 7 km E. of Columbus | Pavement Improvement | 2009-10-05 | 2009-10-23 | 2010-12-20 | 2011-11-08 | 3404820 | 2.732 | 4211004
7602 | MONTANA | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 4241008 | 4.6 mile chip seal on S 424 west of Kalispell | Pavement Improvement | 2009-06-29 | 2009-06-30 | 2009-12-20 | 2009-08-20 | 164937.05 | 4.610 | 4241008
7603 | MONTANA | Completed | C250,C240 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 4301008 | Reconstruction of the existing roadway and structure work on Canyon Ferry Road | Pavement Improvement | 2009-10-05 | 2009-10-09 | 2011-12-20 | 2012-08-10 | 7387082 | 4.200 | 4301008
7604 | MONTANA | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | FLATHEAD |  | 01 | 5031010 | 3.5 mile chip seal on S 503 southwest of Kalispell | Pavement Improvement | 2009-06-29 | 2009-06-30 | 2009-12-20 | 2009-08-20 | 125547.93 | 3.500 | 5031010
7605 | MONTANA | Completed | C250 | Highway Infrastructure Investment Grant | MONTANA | MINERAL, MISSOULA |  | 01 | 5071008 | 2.4 mile mill and fill on S 507 east of Alberton, Missoula County | Pavement Improvement | 2009-06-22 | 2009-07-22 | 2009-12-20 | 2009-10-26 | 418403.68 | 2.498 | 5071008
7606 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5205024 | 0.9 mile overlay on River Drive in Great Falls | Pavement Improvement | 2009-07-20 | 2009-08-17 | 2009-12-20 | 2010-02-10 | 532924.54 | 0.940 | 5205024
7607 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5208002 | 0.7 mile overlay of Park Drive in Great Falls. | Pavement Improvement | 2009-07-20 | 2009-08-10 | 2009-12-20 | 2010-02-10 | 323973.6 | 0.700 | 5208002
7608 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5209005 | 0.6 mile overlay of 6th Street in Great Falls. | Pavement Improvement | 2009-07-20 | 2009-08-10 | 2009-12-20 | 2010-02-10 | 258322.6 | 0.610 | 5209005
7609 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5210018 | 0.18 mile mill and fill on 1st Avenue NW of River Drive in Great Falls | Pavement Improvement | 2009-07-20 | 2009-08-17 | 2009-12-20 | 2010-02-10 | 277683.91 | 0.180 | 5210018
7610 | MONTANA | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5299080 | Multiple Location sidewalk Improvment Project - Great Falls | Transportation Enhancements | 2009-06-22 | 2009-07-06 | 2010-02-01 | 2010-09-08 | 1045346.64 |  | 5299080
7611 | MONTANA | Completed | C220,C200 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5299081 | Phase 3 of a Multiple Location sidewalk Improvment Project - Great Falls | Transportation Enhancements | 2009-09-14 | 2009-09-17 | 2010-07-01 | 2011-01-10 | 500455.83 |  | 5299081
7612 | MONTANA | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5299086 | Construction of approx. 2300 ln ft of asphalt and concrete paths including fencing, drainage culverts, signing, striping and retaining wall in Great Falls. | Transportation Enhancements | 2009-10-16 | 2009-10-16 | 2010-09-01 | 2010-03-30 | 340275.96 |  | 5299086
7613 | MONTANA | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | CASCADE | GREAT FALLS | 01 | 5299087 | Construction of approx. 1800 ln ft of asphalt bicycle/pedestrian pathway along the Missouri River in Great Falls. | Transportation Enhancements | 2010-06-01 | 2010-06-02 | 2010-11-01 | 2010-12-15 | 659724.04 |  | 5299087
7614 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 5802012 | Widneing 1.09 mile segment of Custer Avenue in Helena | Pavement Improvement | 2009-07-06 | 2009-08-03 | 2009-12-20 | 2010-09-09 | 623101 | 1.090 | 5802012
7615 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 5805013 | 0.3 mile mill and fill on Benton Ave in Helena | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2009-12-20 | 2010-02-09 | 226091.31 | 0.300 | 5805013
7616 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | LEWIS AND CLARK |  | 01 | 5822002 | 0.83 mile overlay on Hauser Blvd in Helena | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2009-12-20 | 2010-02-09 | 403276.24 | 0.830 | 5822002
7617 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | YELLOWSTONE |  | 01 | 6905002 | Reconstruct the existing 8th Ave Roadway in Laurel | Pavement Improvement | 2009-11-16 | 2010-01-22 | 2011-12-20 | 2012-06-29 | 2508204 | 0.640 | 6905002
7618 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | PARK |  | 01 | 7406007 | 0.7 mile mill and fill on Chinook and Gallatin Street in Livingston | Pavement Improvement | 2009-06-15 | 2009-06-18 | 2009-12-20 | 2009-11-23 | 214020.37 | 0.710 | 7406007
7619 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8105014 | 0.8 mile mill and fill on Russell Street in Missoula | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-12-20 | 2009-11-05 | 143343.5 | 0.800 | 8105014
7620 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8107019 | 0.17 mile mill and fill on Orange Street in Missoula | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-12-20 | 2009-11-05 | 78367.49 | 0.173 | 8107019
7621 | MONTANA | Completed | C200,C240 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8109002 | On the Scott Street overpass in Missoula, Bridge deck repair and replacing the surface with a high strength epoxy concrete. | Bridge Improvement | 2009-07-13 | 2009-07-22 | 2010-07-01 | 2010-06-07 | 1974836.74 | 0.000 | 8109002
7622 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8113006 | 0.3 mile mill and fill on Higgins Street in Missoula | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-12-20 | 2009-11-05 | 115275.18 | 0.340 | 8113006
7623 | MONTANA | Completed | C220,C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8117006 | Higgins/Hill/Beckwith Intersection & Signal Improvement in Missoula | Pavement Improvement | 2009-06-15 | 2009-06-17 | 2009-12-20 | 2009-12-18 | 693643.94 | 0.000 | 8117006
7624 | MONTANA | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8119001 | Design and construction of sidewalks, bike lanes, and period lighting. The proejct is in Missoula along both sides of Higgins Avenue between Broadway and Railroad Streets. | Transportation Enhancements | 2010-04-26 | 2010-04-26 | 2010-12-01 | 2010-10-15 | 1250000 |  | 8119001
7625 | MONTANA | Completed | C200 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8120005 | 2 mile mill and fill on South Avenue in Missoula | Pavement Improvement | 2009-06-01 | 2009-06-15 | 2009-12-20 | 2009-11-05 | 624945.36 | 2.000 | 8120005
7626 | MONTANA | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8123001 | Design and construct a bicycle and pedstrian path in the Missoula Urbanized Area along the south side of Mullan Road between Flyn Lane and Cote Lane. | Transportation Enhancements | 2010-04-12 | 2010-04-12 | 2010-10-01 | 2010-08-04 | 600000 |  | 8123001
7627 | MONTANA | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8199088 | Installation of accessible curb ramps on existing sidewalks at multiple locations within the City of Missoula. | Transportation Enhancements | 2010-06-14 | 2010-06-24 | 2010-10-01 | 2010-10-21 | 350000 |  | 8199088
7628 | MONTANA | Completed | C220 | Highway Infrastructure Investment Grant | MONTANA | MISSOULA | MISSOULA | 01 | 8199089 | Design and construct sidewalks and bike paths in Missoula - on both sides of Greenough Drvie between Madison St and Wateworks Hill Trailhead. | Transportation Enhancements | 2010-05-25 | 2010-06-15 | 2010-10-01 | 2010-08-06 | 189570 |  | 8199089
7629 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | BLAINE |  | 01 | 9003032 | Replacement of an off system bridge & approaches in Blaine County. | Bridge Replacement | 2009-06-22 | 2009-07-10 | 2010-12-20 | 2010-10-28 | 2402036 |  | 9003032
7630 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | BLAINE |  | 01 | 9003039 | Bridge Replacement 7 KM west of Harlem | Bridge Replacement | 2010-01-04 | 2010-02-04 | 2011-12-20 | 2010-11-18 | 2364675 |  | 9003039
7631 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | DEER LODGE |  | 01 | 9012131 | Replace existing structure over the Clark Fork, 2 KM East of Warm Springs | Bridge Replacement | 2009-11-02 | 2010-03-22 | 2010-12-20 | 2010-10-13 | 397816 | 0.000 | 9012131
7632 | MONTANA | Completed | C240 | Highway Infrastructure Investment Grant | MONTANA | FALLON |  | 01 | 9013015 | Off-system Bridge Replacement Project North West of Baker in Fallon County | Pavement Improvement | 2009-08-03 | 2009-09-15 | 2010-12-20 | 2011-12-29 | 684245 | 0.000 | 9013015
7633 | MONTANA | Completed | C490 | OJT/SS | MONTANA | LAKE |  | 01 | STWD016 | Purchase, transport and set up equipment and software that will be used to provide and support state of the art training. | Other | 2009-09-01 |  | 2010-09-01 | 2011-10-01 | 707847 |  | STWD016
7634 | MONTANA | Completed | C490 | OJT/SS | MONTANA | ROOSEVELT |  | 01 | STWD017 | Provide on the job training in highway construction industry, equipment operating, and transportation to targeted groups in highway construction workforce. | Other | 2009-09-01 |  | 2010-09-01 | 2011-05-01 | 334320 |  | STWD017
7635 | NEBRASKA | Underway | C220 | Highway Infrastructure Investment Grant | NEBRASKA | BUFFALO |  | 03 | 0010060 | Restore a historic depot in the park in Pleasanton. Exterior work to include new foundation, windows, roof, gutters, and siding. Interior work to include new insulation, repair of floors, wall and tr | Transportation Enhancements | 2010-04-22 | 2012-04-12 | 2010-12-11 |  | 312118 |  | 0010060
7636 | NEBRASKA | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | DAKOTA | SIOUX CITY (IA-SD) | 01 | 0022028 | This projects constructs an 8' concrete trail as a safe crossing from the Tri-State Trail under the Missouri River bridge on US-77 | Transportation Enhancements | 2010-04-28 | 2010-09-13 | 2010-08-07 | 2011-08-24 | 396223 |  | 0022028
7637 | NEBRASKA | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | DODGE |  | 01 | 0027052 | This project will replace existing street lights located on Main Street from 5th to 1st Streets with historic replica lighting in Fremont. | Transportation Enhancements | 2010-01-15 | 2011-01-17 | 2010-10-30 | 2011-05-23 | 132804 |  | 0027052
7638 | NEBRASKA | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 0028091 | This project restores the brick pavement and replaces granite curbs in the historic Old Market District of downtown Omaha, bringing back the original historical flavor of this popular shopping and entertainment district. | Transportation Enhancements | 2010-04-29 | 2010-09-22 | 2010-11-27 | 2011-05-11 | 668408.18 |  | 0028091
7639 | NEBRASKA | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | KEARNEY |  | 03 | 0050035 | This project will construct an 8-foot-wide pedestrian and bicycle trail connecting the Axtell City Park and Axtell School at the edge of downtown, with the Natures Mosaic Recreation Area 3,000 feet no | Transportation Enhancements | 2010-04-06 | 2010-10-05 | 2010-10-30 | 2011-04-14 | 208516 |  | 0050035
7640 | NEBRASKA | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | KNOX |  | 01 | 0054015 | Construct a 10' wide crushed concrete trail between Gavin's Point Dam and the community of Aten. | Transportation Enhancements | 2011-02-17 | 2011-11-15 | 2011-11-05 | 2012-05-18 | 13670.61 |  | 0054015
7641 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 0064125 | 12.1 miles of asphalt resurfacing and bridge repair west of Hastings, including the spurs to Juniata and the Hastings Regional Center. | Pavement Improvement | 2009-05-07 | 2009-05-14 | 2009-11-28 | 2010-05-04 | 3665228 | 9.860 | 0064125
7642 | NEBRASKA | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | PLATTE |  | 03 | 0071030 | This project will construct a 10-foot-wide concrete pedestrian and bicycle trail approximately one mile in length, connecting the existing Wilderness Park Trail and the Robert Bob White Trail on the o | Transportation Enhancements | 2009-11-19 | 2010-09-27 | 2010-06-19 | 2011-04-01 | 366930 |  | 0071030
7643 | NEBRASKA | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | THURSTON |  | 01 | 0087010 | This project constructs a one mile long, 8' wide concrete trail connecting the Heritage Store and the Thunder Way subdivision in Winnebago, providing a safe and efficient route for pedestrians and bicyclists. | Transportation Enhancements | 2010-12-29 | 2011-03-28 | 2011-07-11 | 2011-11-14 | 559438 |  | 0087010
7644 | NEBRASKA | Underway | C220 | Highway Infrastructure Investment Grant | NEBRASKA | WASHINGTON |  | 02 | 0089024 | Construct 10' wide concrete trail from the Blair Deerfield Lions Trail to the Dana College recreation fields, a distance of 0.9 mile | Transportation Enhancements | 2010-03-04 | 2010-08-23 | 2010-10-30 |  | 435371 |  | 0089024
7645 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | BUFFALO |  | 03 | 0102115 | This resurfacing project will bring this roadway to a state of good repair. It will address pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-09-22 | 2010-06-21 | 2010-10-30 | 2010-11-02 | 1282168.59 | 10.000 | 0102115
7646 | NEBRASKA | Completed | C220 | Highway Infrastructure Investment Grant | NEBRASKA | HALL |  | 03 | 0112116 | This project provides for installation of landscaping along Highway N-11 along the Loup River Scenic Byway. It includes landscape areas in the downtown corridor (2.5 blocks); and a 20-foot wide lands | Transportation Enhancements | 2010-01-27 | 2010-04-01 | 2010-05-29 | 2011-05-10 | 149078 | 0.000 | 0112116
7647 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | JEFFERSON |  | 03 | 0151113 | Replacement of 2 deficient bridges south of Fairbury on N-15. The structure at reference post 3.07 is over a stream. The second structure at R.P 4.53 is over Rose Creek. | Bridge Replacement | 2009-05-04 | 2009-05-18 | 2011-04-30 | 2010-06-14 | 2966171 | 0.000 | 0151113
7648 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | HOLT |  | 03 | 0204117 | The project consists of resurfacing the existing 24 foot roadway and 8 foot surfaced shoulders on US-20 just southeast of the city of O'Neill and continuing southeast 5.14 miles. The project will mill | Pavement Improvement | 2009-11-25 | 2010-07-22 | 2010-10-30 | 2010-09-10 | 1347689 | 5.020 | 0204117
7649 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | ANTELOPE |  | 03 | 0205111 | The project consists of resurfacing the existing 24 foot roadway and 8 foot surfaced shoulders of US-20 from Royal to Plainview and for a short length on S-2B. The project along US-20 will mill off f | Pavement Improvement | 2009-12-11 | 2010-07-06 | 2010-10-30 | 2010-10-20 | 4969422.85 | 14.150 | 0205111
7650 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | PHELPS |  | 03 | 0233105 | Asphalt resurfacing of the 6.96 miles of N-23 between Loomis and Holdrege. The existing 4' shoulders will be widened to 6' with 2' being surfaced. | Pavement Improvement | 2009-07-17 | 2009-09-14 | 2010-07-31 | 2010-05-26 | 2321500.42 | 6.960 | 0233105
7651 | NEBRASKA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEBRASKA | BUFFALO |  | 03 | 0304148 | This project is on US-30 from Avenue B to Avenue E and from Avenue I to Avenue L in the city of Kearney. The existing narrorw raised median will be widened to 15 feet to accommodate turn lanes. To acc | Pavement Improvement | 2009-06-08 | 2009-07-13 | 2010-07-24 | 2010-07-27 | 2294674.97 | 0.220 | 0304148
7652 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | WASHINGTON |  | 02 | 0307116 | This project consists of concrete repair and diamond grinding on US-30 from US-75 in Blair east 1.8 miles to the Missouri River Bridge | Pavement Improvement | 2010-04-16 | 2010-07-06 | 2010-10-02 | 2010-11-30 | 460750 |  | 0307116
7653 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | MADISON |  | 01 | 0325106 | "Improvements of this project east of Madison will include the vertical realignment of N-32 at the bridge over Union Creek at R.P. 36.73, which will be replaced along with raising the highway grade 9 | Bridge Replacement | 2009-09-23 | 2010-03-01 | 2010-11-13 | 2010-12-03 | 3506055.46 | 0.740 | 0325106
7654 | NEBRASKA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEBRASKA | HALL |  | 03 | 0344131 | "This project is located on US-34 and US-281 just south of and in the city of Grand Island. It extends from just north of the I-80 interchange to just south of Capital Avenue for a total lenth of 8.33 | Pavement Improvement | 2009-06-03 | 2009-07-13 | 2010-07-31 | 2011-05-24 | 6504399 | 5.060 | 0344131
7655 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 0346139 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement, bridge and guardrail deficiencies with an asphalt overlay, bridge repair and new guardrail. | Pavement Improvement | 2009-07-13 | 2009-07-27 | 2010-06-19 | 2010-07-07 | 2049649 | 2.490 | 0346139
7656 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 0346140 | Urban asphalt resurfacing on ""O"" Street from 15th St. to 25th St.; from 29th St. to 44th St. and from Wedgewood Dr. to 84th St. in Lincoln" | Pavement Improvement | 2010-03-18 | 2010-05-03 | 2011-05-13 | 2011-10-11 | 1711546 |  | 0346140
7657 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DAKOTA |  | 01 | 0354118 | This bridge replacement project will bring this roadway to a state of good repair. It will replace two deficient bridges and rehabilitate another bridge. | Bridge Replacement | 2009-06-03 | 2009-06-22 | 2010-10-30 | 2010-12-03 | 1944384 | 0.000 | 0354118
7658 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 0387106 | This project reconstructs the busy West Center Road between 156th St. and 148th St. in Omaha to a 4-lane divided roadway in Omaha, providing a safer and more efficient segment. | Pavement Widening | 2010-04-26 | 2010-05-10 | 2011-10-31 | 2012-04-25 | 7470191 |  | 0387106
7659 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | OTOE |  | 01 | 0502128 | This resurfacing and bridge project will bring this roadway to a state of good repair. It will improve safety by eliminating surface and bridge deficiencies through an asphalt overlay and bridge rehabilitation. | Pavement Improvement | 2009-03-25 | 2009-03-31 | 2010-07-31 | 2010-09-28 | 4907360 | 9.460 | 0502128
7660 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | VALLEY |  | 03 | 0704107 | This project is located on N-70 near Arcadia. The existing 275' bridge with a 28' roadway will be widened and rehabilitated with a new south span and new superstructure. The rehabilitated bridge will | Bridge Improvement | 2009-05-11 | 2009-05-18 | 2010-08-21 | 2010-11-19 | 1715054.58 | 0.000 | 0704107
7661 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | KIMBALL |  | 03 | 0712109 | This resurfacing project will bring this roadway to a state of good repair by providing a new, wider driving surface. | Pavement Improvement | 2009-06-03 | 2009-06-29 | 2009-11-21 | 2010-02-02 | 4357760.11 | 14.860 | 0712109
7662 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | WASHINGTON |  | 01 | 0753115 | This urban project in Blair adds a 2' curb and gutter section with storm sewer and inlets. This will allow for the future construction of a 10' sidewalk / bike trail on the south side of US-75 from Deer field Drive to North 25th Street. | Pavement Improvement | 2010-04-07 | 2010-06-28 | 2010-09-10 | 2010-10-01 | 458420 | 0.250 | 0753115
7663 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | THURSTON |  | 01 | 0754108 | This project is a combination of new construciton and reconstruction with two new bridges being built on new alignment. The purpose of the project is to improved safety by bringing bridges and the driving surface to current standards. | Bridge Replacement | 2010-03-02 | 2010-03-15 | 2011-09-17 | 2011-10-19 | 1995848 | 0.910 | 0754108
7664 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DEUEL |  | 03 | 0802090 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies through an asphalt overlay. | Pavement Improvement | 2009-05-04 | 2009-06-15 | 2010-07-24 | 2010-06-01 | 6317477.58 | 9.820 | 0802090
7665 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | CHEYENNE |  | 03 | 0802093 | This rehabilitation and restoration project will bring this roadway to a state of good repair. It will extend the life and improve the surface condition of the existing pavement. | Pavement Improvement | 2009-05-11 | 2009-06-15 | 2009-10-03 | 2009-09-21 | 1296575.95 | 24.850 | 0802093
7666 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DEUEL |  | 03 | 0803119 | The improvements on this project will consist of concrete pavement repairs to the existing dual 24' roadway, plus the 3' inside and 10' outside shoulders. The existing inside shoulders and roadway wil | Pavement Improvement | 2009-12-02 | 2010-05-03 | 2010-10-30 | 2011-05-15 | 4074809 | 4.220 | 0803119
7667 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | KEITH |  | 03 | 0803135 | This project rehabilitates Interstate 80 between the Brule and Ogallala interchanges by milling the surface and placing new asphaltic concrete. | Pavement Improvement | 2009-12-17 | 2010-04-26 | 2010-10-09 | 2010-11-01 | 3894955.12 | 10.810 | 0803135
7668 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | KEITH |  | 03 | 0803139 | This project rehabilitates Interstate 80 between the Ogallala and Roscoe interchanges by milling the surface and placing new asphaltic concrete. | Pavement Improvement | 2010-01-20 | 2010-03-11 | 2010-08-28 | 2010-10-21 | 3200876.7 | 6.680 | 0803139
7669 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | LINCOLN |  | 03 | 0804104 | This rehabilitation project will bring this roadway to a state of good repair, by preserving the structure (the interchange over I-80) and providing an improved driving surface. | Bridge Improvement | 2009-03-23 | 2009-05-18 | 2009-10-03 | 2009-12-02 | 1315548 | 0.000 | 0804104
7670 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DAWSON |  | 03 | 0804129 | This rehabilitation project will bring this roadway to a state of good repair, by preserving the structure (the interchange over I-80) and providing an improved driving surface. | Bridge Improvement | 2009-04-28 | 2009-06-08 | 2009-10-03 | 2010-04-14 | 1050940 | 0.000 | 0804129
7671 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | LINCOLN |  | 03 | 0804133 | This restoration and rehabilitation project will bring this roadway to a state of good repair. It will extend the life and improve the surface condition of the existing pavement. | Pavement Improvement | 2009-07-23 | 2009-09-08 | 2010-08-07 | 2010-06-22 | 1743620.93 | 5.870 | 0804133
7672 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DAWSON |  | 03 | 0805069 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-03-25 | 2009-06-15 | 2009-09-05 | 2010-05-04 | 6137997.94 | 10.490 | 0805069
7673 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | HALL |  | 03 | 0806097 | This project will resurface 11.61 miles of I-80 between the Wood River and West Grand Island Interchanges. Improvements consist of joint repair, pavement repair, milling and resurfacing with asphalt a | Pavement Improvement | 2009-06-08 | 2009-07-06 | 2010-06-26 | 2010-08-16 | 4920928.08 | 11.630 | 0806097
7674 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 0809889 | This reconstruction project will bring this roadway to a state of good repair and will improve the level of service (traffic flow). This expansion of I-80 on the Nebraska side is occurring in conjunct | Pavement Widening | 2009-07-09 | 2009-08-10 | 2012-06-02 | 2012-05-01 | 16486652 | 2.230 | 0809889
7675 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | YORK |  | 03 | 0812142 | The project begins 0.6 miles north of US-34 north of York and continues 7.2 miles north, including 0.6 miles at the S-93 junction. It consists of asphaltic concrete resurfacing of the roadway and shou | Pavement Improvement | 2010-01-06 | 2010-04-05 | 2010-10-30 | 2010-10-19 | 2712263 |  | 0812142
7676 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | THOMAS |  | 03 | 0833106 | This bridge project will bring this roadway to a state of good repair and will improve mobility and safety, by eliminating existing at-grade rail and highway crossings (over the BNSF RR) in close prox | Bridge Replacement | 2009-04-01 | 2009-05-04 | 2010-07-17 | 2011-05-23 | 6943648 | 1.660 | 0833106
7677 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | CHERRY |  | 03 | 0834113 | The scope of this project consists of resurfacing US Highway 83 (US-83) for approximately 10 miles. The project will be milled and constructed using 4 inches of High RAP Base which contains a high Rec | Pavement Improvement | 2009-11-25 | 2010-07-12 | 2010-10-02 | 2010-11-18 | 3227940.17 | 10.050 | 0834113
7678 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | LOUP |  | 03 | 0913107 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-06-08 | 2009-08-24 | 2009-10-31 | 2009-11-05 | 1980080.52 | 8.470 | 0913107
7679 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | PLATTE |  | 03 | 0915121 | This resurfacing project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-05-14 | 2009-06-01 | 2009-09-05 | 2009-09-01 | 3436352.76 | 11.950 | 0915121
7680 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | COLFAX |  | 01 | 0916111 | This resurfacing project brought this roadway to a state of good repair. It addressed pavement deficiencies with an asphalt overlay, including milling off 2" of old asphalt surfacing and replacing wi | Pavement Improvement | 2009-05-14 | 2009-06-22 | 2009-10-31 | 2009-08-21 | 2395805.74 | 16.710 | 0916111
7681 | NEBRASKA | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | BANNER |  | 03 | 1035006 | This project is on a county road 5.55 miles north and 10.5 miles west of Harrisburg, continuing north 4.0 miles to the county line. It consists of an asphalt resurfacing of the 22' roadway and rehabilitation of the 4' earth shoulders. | Pavement Improvement | 2010-03-25 | 2010-08-23 | 2010-10-16 | 2010-10-09 | 1170489 |  | 1035006
7682 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DIXON |  | 01 | 1164102 | This bridge replacement project will bring this roadway to a state of good repair. It is replacing a 52-year old structure. | Bridge Replacement | 2009-05-04 | 2009-05-18 | 2009-10-31 | 2009-12-04 | 328419.66 | 0.000 | 1164102
7683 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | THAYER |  | 03 | 1365111 | Milling and asphalt resurfacing of 4.2 miles of US-136 from 1.7 miles west of Gilead to the Thayer/Jefferson county line. | Pavement Improvement | 2009-03-25 | 2009-06-03 | 2009-10-31 | 2009-09-30 | 1444929.28 | 5.020 | 1365111
7684 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | GAGE |  | 01 | 1366116 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-04-29 | 2009-06-25 | 2009-10-31 | 2010-05-08 | 3059751.25 | 9.410 | 1366116
7685 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | JEFFERSON |  | 01 | 1366118 | This project will bring this roadway to a state of good repair. It addresses pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-03-25 | 2009-06-19 | 2009-10-31 | 2009-10-21 | 2762944.64 | 8.100 | 1366118
7686 | NEBRASKA | Underway | C240 | Highway Infrastructure Investment Grant | NEBRASKA | NEMAHA |  | 01 | 1367122 | This bridge rehabilitation project will bring this roadway to a state of good repair. It will extend the life and improve the safety of the existing bridge by repairing and rehabilitating the structu | Bridge Improvement | 2009-10-05 | 2009-08-31 | 2011-12-01 |  | 3245529 | 0.000 | 1367122
7687 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | FRONTIER |  | 03 | 1575003 | This project is on a county road 9.5 miles south and 9.0 miles east of Stockville, continuing north 3.1 miles. It consists of an asphalt resurfacing of the 22' roadway and rehabilitation of the 4' earth shoulders. | Pavement Improvement | 2010-01-25 | 2011-06-21 | 2010-10-30 | 2011-08-24 | 906458 |  | 1575003
7688 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | KEYA PAHA |  | 03 | 1710004 | This project is on a county road 4.7 miles north and 2.8 miles west of Springview, extending 3.0 miles east. It consists of an asphalt resurfacing of the 22.5' roadway and rehabilitation of the 4' earth shoulders. | Pavement Improvement | 2010-03-09 | 2010-08-12 | 2010-10-02 | 2010-10-13 | 939271 |  | 1710004
7689 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | THOMAS |  | 03 | 1755013 | This project is on a county road 3.5 miles north of Halsey, extending 4.2 miles north. It consists of an asphalt resurfacing of the 20' roadway and rehabilitation of the 4' earth shoulders. | Pavement Improvement | 2010-05-04 | 2011-05-09 | 2010-10-30 | 2011-07-25 | 1067830 |  | 1755013
7690 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ROCK |  | 03 | 1810005 | Asphalt resurfacing of a county road 8.4 miles south and 4.9 miles east of Bassett, continuing 4.7 miles southeasterly. | Pavement Improvement | 2011-01-18 | 2011-08-10 | 2011-10-29 | 2012-05-04 | 893517 |  | 1810005
7691 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | HALL |  | 03 | 2235005 | This project consists of the paving of the northbound lanes of Locust Street from I-80 north 2.9 miles to Grand Island. | Pavement Improvement | 2010-04-22 | 2010-05-13 | 2010-08-21 | 2010-10-28 | 3355633 |  | 2235005
7692 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | HOLT |  | 03 | 2280005 | Replace a deficient bridge on a county road 14.2 miles east of O'Neill, crossing the middle branch of Verdigris Creek with a twin 9' x 8' x 88' concrete box culvert. | Pavement Improvement | 2010-01-25 | 2010-03-29 | 2010-06-19 | 2010-07-09 | 252522 |  | 2280005
7693 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | HOLT |  | 03 | 2814118 | The scope of this project consists of resurfacing the existing 24' asphalt roadway and 8' surfaced shoulders of US-281 near the city of O'Neill (approximately 7.5 miles in length). The project will m | Pavement Improvement | 2009-11-25 | 2010-07-12 | 2010-10-09 | 2010-09-03 | 2065563.47 | 7.410 | 2814118
7694 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | JEFFERSON |  | 01 | 3005008 | This project consists of a 3 inch asphaltic concrete overlay of an existing bituminous road. The project includes earth shoulder construction to match the pavement rise along both sides of the road. T | Pavement Improvement | 2010-01-07 | 2011-03-31 | 2010-10-30 | 2011-05-05 | 756007 |  | 3005008
7695 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | GAGE |  | 01 | 3265004 | New 30' x 28' concrete slab bridge over Plum Creek 0.7 miles south of Barneston. | Bridge Replacement | 2010-01-26 | 2010-03-22 | 2010-11-27 | 2011-06-06 | 837486 |  | 3265004
7696 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 3340007 | This project consists of replacing a deficient bridge box culvert. This bridge is a 4-barrel 10 foot by 26 foot concrete box culvert. It will be replaced with a 4-barrel 14 foot by 61 foot concrete | Bridge Replacement | 2010-04-20 | 2010-06-21 | 2010-10-02 | 2010-10-28 | 310884 |  | 3340007
7697 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | SAUNDERS |  | 01 | 3430006 | The project is the replacement of a deficient bridge with a triple 16' x 16' x 18' concrete box culvert. It is located on a county road (Highway Avenue) on the southern edge of Prague, crossing Cottonwood Creek. | Bridge Replacement | 2010-02-03 | 2010-03-29 | 2010-11-27 | 2011-08-05 | 567100 |  | 3430006
7698 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 3770003 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2010-03-09 | 2010-09-20 | 2010-10-30 | 2010-10-21 | 560000 |  | 3770003
7699 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | Multiple | 3772001 | This project improves safety and mobility by reconfiguring the intersection and installing traffic signals. | Safety/Traffic Management | 2010-07-27 | 2010-10-04 | 2010-10-30 | 2010-11-08 | 242268 |  | 3772001
7700 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 01 | 3787003 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with joint repair and an asphalt overlay. | Pavement Improvement | 2010-03-09 | 2010-08-30 | 2010-10-30 | 2010-10-20 | 610700 |  | 3787003
7701 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | BOX BUTTE |  | 03 | 3854129 | This resurfacing project will bring this roadway to a state of good repair. It is addressing pavement deficiencies with an asphalt overlay. | Pavement Improvement | 2009-04-29 | 2009-08-10 | 2009-10-31 | 2009-11-23 | 3022607.93 | 7.910 | 3854129
7702 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 4809776 | This is a new 311' x 58' bridge on US-75 southbound over 30th St. and the exit ramps in Omaha. | Bridge Replacement | 2009-08-19 | 2009-08-31 | 2011-06-11 | 2011-06-11 | 1680143 | 0.000 | 4809776
7703 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 4809777 | Rehabilitation of the I-480 183' x 72' steel girder bridge over 24th St. in Omaha | Bridge Improvement | 2009-08-19 | 2009-08-31 | 2011-06-11 | 2011-06-11 | 1600854 | 0.000 | 4809777
7704 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 4809778 | This project is the reconstruction of the I-480 / US-75 southbound interchange in Omaha. Work consists of grading, mechanically stabilized earth walls, culverts, three bridge removals, guardrail, fencing, traffic signals and lighting. | Pavement Improvement | 2009-08-19 | 2009-08-31 | 2011-06-11 | 2011-06-11 | 13146340 | 0.880 | 4809778
7705 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 4809787 | This project is the widening and rehabilitiation of the southbound US-75 bridge over Burt St. and Cuming St. in Omaha. The new structure will be 532' long and 58' wide. | Bridge Improvement | 2009-08-19 | 2009-08-31 | 2011-06-11 | 2011-06-11 | 3262610 | 0.000 | 4809787
7706 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5003008 | This project improves safety and mobility by constructing a 4-lane divided roadway. | Pavement Widening | 2010-03-16 | 2010-03-22 | 2010-10-08 | 2010-10-29 | 2592465 |  | 5003008
7707 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5006005 | This project is to replace the 50+ year old traffic signals, poles and mast arms at the intersection of Harvell Drive and Fort Crook Road in the City of Bellevue. The work included is to install new s | New Construction | 2010-02-18 | 2010-09-27 | 2010-10-30 | 2010-11-01 | 135800 |  | 5006005
7708 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5011013 | This project is to install traffic warning signals for the intersection of 108th Street and Chandler Road in La Vista. | New Construction | 2010-02-25 | 2010-10-04 | 2010-10-30 | 2011-02-14 | 30000 |  | 5011013
7709 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5012009 | The scope of the project consists of dowel bar retrofitting, diamond grinding, and texturing on Giles Road, beginning at 108th St and ending approximately 200 feet southeast of Southport Parkway in th | Pavement Improvement | 2010-02-25 | 2010-08-09 | 2010-10-30 | 2011-04-07 | 970700 |  | 5012009
7710 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5027001 | This reconstruction project will bring this urban street to a state of good repair. | Pavement Improvement | 2010-12-16 | 2011-03-21 | 2011-06-25 | 2012-11-19 | 765864 |  | 5027001
7711 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5049004 | Resurfacing urban streets at city-wide locations in Omaha | Pavement Improvement | 2010-12-09 | 2011-05-09 | 2011-09-10 | 2012-06-06 | 354725 |  | 5049004
7712 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5052003 | This project improves safety and mobility by installing traffic signals. | Safety/Traffic Management | 2010-03-25 | 2010-08-10 | 2010-10-08 | 2010-09-30 | 239056.3 |  | 5052003
7713 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5093001 | This project improves safety and mobility by installing traffic signals. | Safety/Traffic Management | 2010-03-25 | 2011-04-04 | 2010-11-19 | 2011-06-16 | 332605 |  | 5093001
7714 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5095003 | This asphalt resurfacing project will bring urban streets at city-wide locations to a state of good repair. | Pavement Improvement | 2010-03-01 | 2010-05-17 | 2010-10-29 | 2010-09-07 | 2553806.33 |  | 5095003
7715 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 5097002 | This project improves safety and mobility by installing traffic signals. | Safety/Traffic Management | 2010-03-25 | 2010-06-14 | 2010-09-01 | 2010-08-06 | 263630.01 |  | 5097002
7716 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5106001 | This project improves safety and mobility for pedestrians by replacing sidewalks and adding ADA-approved ramps. | Pavement Improvement | 2010-04-28 | 2010-06-01 | 2010-10-02 | 2010-11-24 | 837240 |  | 5106001
7717 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5106002 | This asphalt resurfacing project will bring this urban street to a state of good repair. | Pavement Improvement | 2010-03-22 | 2010-09-20 | 2010-10-30 | 2011-06-24 | 257773.08 |  | 5106002
7718 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5109007 | This project is to replace the 50+ year old traffic signals, poles and mast arms at the intersection of Harvell Drive and Galvin Road in the City of Bellevue. The work included is to install new signa | New Construction | 2010-02-16 | 2010-09-07 | 2010-10-30 | 2010-10-07 | 136531 |  | 5109007
7719 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | SARPY | OMAHA (IA) | 02 | 5145001 | This asphalt resurfacing project will bring these urban roadways into a good state of repair. | Pavement Improvement | 2010-03-24 | 2010-08-02 | 2010-09-18 | 2011-07-07 | 1190700 |  | 5145001
7720 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5220003 | Asphalt resurfacing on A Street between 63rd St. and Imperial Drive and on Van Dorn St. from Normal Blvd. to 70th St. in Lincoln. | Pavement Improvement | 2010-01-26 | 2010-04-12 | 2010-09-30 | 2011-10-11 | 662985 |  | 5220003
7721 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5236002 | Asphalt resurfacing on P St. between 18th St. and 27th St., P St. between 17th St. and 27th St. and on Northwest 1st St. between Highland Blvd. and West Fletcher Ave. in Lincoln." | Pavement Improvement | 2010-02-28 | 2010-04-27 | 2011-09-30 | 2011-11-22 | 926670 |  | 5236002
7722 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5239008 | Pavement markings at various locations city-wide in Lincoln | Safety/Traffic Management | 2010-12-01 | 2011-06-20 | 2011-09-30 | 2012-04-25 | 754507 |  | 5239008
7723 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5244007 | Asphalt resurfacing and ADA approved curb ramps on Holdrege Street from 33rd St. to 47th St. in Lincoln | Pavement Improvement | 2010-02-28 | 2011-05-31 | 2011-08-12 | 2011-09-29 | 916546 |  | 5244007
7724 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5244008 | Asphalt resurfacing and ADA approved curb ramps on Holdrege Street from 70th St. to 79th St. in Lincoln | Pavement Improvement | 2010-02-28 | 2011-04-11 | 2011-08-12 | 2011-10-31 | 809396 |  | 5244008
7725 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5247011 | Asphalt resurfacing on Holdrege St. from 19th St to 25th St; on Cornhusker Hwy from Russell Dr. to 70th St.; on 70th St. from Adams St. to Aylesworth St.; on Vine St. from 70th St. to Sierra Dr. and on Adams St. from I-180 to 14th St. in Lincoln. | Pavement Improvement | 2010-02-28 | 2010-05-17 | 2011-09-30 | 2011-11-21 | 1129378 |  | 5247011
7726 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5247012 | 0.64 mile of asphalt resurfacing and curb ramp replacement on 70th St. from Aylesworth St. south to Vine St. in Lincoln | Pavement Improvement | 2010-02-28 | 2011-05-23 | 2011-08-12 | 2011-10-31 | 740069 |  | 5247012
7727 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5250003 | Asphalt resurfacing on Adams St. from 57th St. to 62nd St. in Lincoln | Pavement Improvement | 2010-02-02 | 2010-06-07 | 2010-07-23 | 2011-10-31 | 463377 |  | 5250003
7728 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5254009 | This project consists of bridge rehabilitation for the Superior Street Bridge over Salt Creek just west of 40th Street in Lincoln. The existing steel girder structure is 293 feet long and 50 feet wid | Bridge Improvement | 2010-01-27 | 2010-03-22 | 2010-08-15 | 2011-06-20 | 271922 |  | 5254009
7729 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | LANCASTER | LINCOLN | 01 | 5280001 | This asphalt resurfacing project will bring the roadway into a good state of repair. It is located on Saltillo Rd., from Highway US-77 to South 70th St. in Lincoln, Nebraska. | Pavement Improvement | 2010-06-15 | 2010-08-02 | 2010-10-30 | 2010-10-05 | 884155 |  | 5280001
7730 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | DAKOTA | SIOUX CITY (IA-SD) | 01 | 5305008 | This project improves safety by providing new intersection lighting. | New Construction | 2010-04-06 | 2010-09-13 | 2010-11-27 | 2011-04-21 | 950657 |  | 5305008
7731 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | DAKOTA | SIOUX CITY (IA-SD) | 01 | 5305009 | This project improves safety and mobility by installing traffic signals at urban intersections. | Safety/Traffic Management | 2010-03-04 | 2010-10-19 | 2010-11-27 | 2011-04-22 | 177781 |  | 5305009
7732 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 5505003 | 0.81 mile of asphalt resurfacing, four intersections and curb ramps on Baltimore Avenue from 2nd St. to 12th st. in Hastings | Pavement Improvement | 2010-02-28 | 2010-06-07 | 2010-08-28 | 2010-10-01 | 559708.17 |  | 5505003
7733 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 5512008 | 0.24 mile of asphalt resurfacing and curb ramp replacements on 7th Street, from Baltimore Ave. to Oswego Ave. in Hastings | Pavement Improvement | 2010-02-18 | 2010-05-17 | 2010-10-30 | 2010-06-15 | 137328.84 |  | 5512008
7734 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 5514003 | 0.49 mile of asphalt resurfacing, three intersections and curb ramps on 9th Street from Burlington Ave. to Baltimore Ave. in Hastings. | Pavement Improvement | 2010-02-18 | 2010-05-20 | 2010-10-30 | 2010-06-26 | 347025.15 |  | 5514003
7735 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 5527001 | 0.56 mile of asphalt resurfacing on Showboat Blvd. between 7th and 12th Streets in Hastings. | Pavement Improvement | 2010-01-29 | 2010-04-12 | 2010-10-30 | 2010-05-25 | 236744.29 |  | 5527001
7736 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | SCOTTS BLUFF |  | 03 | 5709003 | Urban reconstruction of 0.43 mile of Avenue B from South Beltline Highway to Overland Drive in Scottsbluff | Pavement Improvement | 2010-04-27 | 2010-07-26 | 2010-11-27 | 2010-11-22 | 950808 |  | 5709003
7737 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | SCOTTS BLUFF |  | 03 | 5724002 | Concrete reconstruction of 0.34 mile of D Street between Rundell Rd. and Lockwood Rd. in Gering | Pavement Improvement | 2010-04-19 | 2010-08-23 | 2010-10-30 | 2010-11-22 | 368695.86 |  | 5724002
7738 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | BUFFALO |  | 03 | 5922003 | Urban reconstruction of 39th St. between Pony Express and Avenue M in Kearney | Pavement Improvement | 2010-04-15 | 2010-06-01 | 2010-11-27 | 2011-05-03 | 2418216 |  | 5922003
7739 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | PLATTE |  | 03 | 6074005 | Construct 2 lanes of concrete pavement for 1.6 miles on Lost Creek Parkway between US-81 and 48th Ave. in Columbus | New Construction | 2010-04-26 | 2010-08-23 | 2011-07-01 | 2011-08-23 | 2398778 |  | 6074005
7740 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | REDWILLOW |  | 03 | 6156002 | Reconstruction of 0.72 mile of West J Street from West 10th St. to Norris Ave. in McCook. Project inlcudes storm sewers, sidewalks, ADA ramps and traffic signals. | Pavement Improvement | 2009-07-22 | 2009-07-27 | 2009-12-05 | 2009-11-13 | 1071992 |  | 6156002
7741 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | OTOE |  | 01 | 6204004 | Reconstruction of 0.24 mile of 11th Corso between 10th and 11th Streets in Nebraska City. | Pavement Improvement | 2010-04-19 | 2010-05-03 | 2010-07-17 | 2011-11-30 | 575330 |  | 6204004
7742 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | OTOE |  | 01 | 6210003 | Asphalt resurfacing and installation of decorative crosswalks for 0.49 mile of Central Ave. between 11th and 6th Streets in Nebraska City. | Pavement Improvement | 2010-02-16 | 2010-07-14 | 2010-10-30 | 2011-08-02 | 603601 |  | 6210003
7743 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | OTOE |  | 01 | 6218001 | Urban widening and reconstruction of 11th Street between 10th and 14th Corsos in Nebraska City | Pavement Improvement | 2010-04-19 | 2010-05-03 | 2010-09-11 | 2011-11-30 | 1249502 |  | 6218001
7744 | NEBRASKA | Underway | C200 | Highway Infrastructure Investment Grant | NEBRASKA | YORK |  | 01 | 6305001 | 0.5 mile of urban reconstruction on Nebraska Ave. between 4th and 14th Streets in York. | Pavement Improvement | 2010-04-22 | 2010-04-28 | 2011-12-03 |  | 2198101 |  | 6305001
7745 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | CASS |  | 01 | 6403002 | 0.16 mile of asphalt resurfacing on 15th St. between Ave. A and Ave. C in Plattsmouth. | Pavement Improvement | 2010-03-18 | 2010-10-18 | 2010-10-30 | 2010-11-04 | 131467 |  | 6403002
7746 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | CASS |  | 01 | 6403003 | Urban reconstruction on 15th St. between 1st Ave. and Main St. in Plattsmouth | Pavement Improvement | 2010-03-18 | 2010-10-25 | 2010-11-20 | 2010-11-12 | 76963 |  | 6403003
7747 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | DAWSON |  | 03 | 6556004 | 0.7 mi of urban reconstruction on 13th St., from Hampton St. to Airport Rd. in Lexington | Pavement Improvement | 2010-11-22 | 2011-06-06 | 2011-11-19 | 2011-11-07 | 1292608 |  | 6556004
7748 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | PHELPS |  | 03 | 6602001 | Urban reconstruciton of 0.52 mile of 11th ave. between Sherman St. and Lincoln St. in Holdrege. | Pavement Improvement | 2010-04-19 | 2010-07-12 | 2010-11-27 | 2011-08-19 | 1623819 |  | 6602001
7749 | NEBRASKA | Underway | C200 | Highway Infrastructure Investment Grant | NEBRASKA | SALINE |  | 01 | 6904001 | Urban reconstruction of 0.95 mile of East 13th St. between Hawthorn St. and the east city limits of Crete. | Pavement Improvement | 2010-04-19 | 2010-10-25 | 2010-11-27 |  | 2213114 |  | 6904001
7750 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | COLFAX |  | 01 | 6954001 | Asphalt resurfacing of 0.44 mile of 9th St. between B St. and G St. in Schuyler | Pavement Improvement | 2010-02-25 | 2010-11-08 | 2010-11-27 | 2011-07-29 | 432349 |  | 6954001
7751 | NEBRASKA | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | ADAMS |  | 03 | 7001014 | Replacement of a deficient bridge with a new 83' x 28' steel girder structure. The project is located 4 miles south and 0.8 mile west of Juniata, crossing the west branch of 32 mile Creek | Bridge Replacement | 2010-01-27 | 2010-09-07 | 2010-11-27 | 2011-05-03 | 481073 |  | 7001014
7752 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | DODGE |  | 01 | 7027008 | The project entails a new 140' x 28' concrete slab bridge over Cuming Creek, 2.5 miles north and 0.8 mile east of Scribner. | Bridge Replacement | 2010-02-17 | 2010-09-09 | 2010-11-27 | 2011-08-01 | 673908 |  | 7027008
7753 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 7028044 | New bridge over Thomas Creek on a county road 2.1 miles east and 0.5 mile north of Bennington. | Bridge Replacement | 2010-03-18 | 2010-09-07 | 2010-11-27 | 2011-03-22 | 534791 |  | 7028044
7754 | NEBRASKA | Completed | C250,C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 7028045 | New bridge over a stream on a county road 2.0 miles north and 0.1 mile east of Valley. | Bridge Replacement | 2010-03-18 | 2010-12-13 | 2010-11-27 | 2011-10-10 | 469421 |  | 7028045
7755 | NEBRASKA | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | FILLMORE |  | 01 | 7030033 | New bridge over a tributary of Turkey Creek on a county road 2.6 miles east of Geneva. | Bridge Replacement | 2010-04-13 | 2010-05-17 | 2010-11-27 | 2011-07-28 | 442906 |  | 7030033
7756 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | FRANKLIN |  | 03 | 7031012 | New twin 9' x 9' x 52' concrete box culvert on the Bostwick irrigation canal 1.5 miles east of Naponee | Bridge Replacement | 2010-01-26 | 2010-12-05 | 2010-11-20 | 2011-04-04 | 100216 |  | 7031012
7757 | NEBRASKA | Completed | C250 | Highway Infrastructure Investment Grant | NEBRASKA | JOHNSON |  | 01 | 7049021 | New 232' x 28' pre-stressed concrete girder bridge over the middle branch of the Big Nemaha River on a county road 2.0 miles west of Sterling. | Bridge Replacement | 2010-01-21 | 2010-03-22 | 2010-11-27 | 2011-04-13 | 904229 |  | 7049021
7758 | NEBRASKA | Completed | C200 | Highway Infrastructure Investment Grant | NEBRASKA | NANCE |  | 03 | 7063006 | New bridge over Horse Creek 1.8 miles south and 8.6 miles west of Fullerton | Bridge Replacement | 2010-11-23 | 2011-08-15 | 2011-11-26 | 2012-05-14 | 531944 |  | 7063006
7759 | NEBRASKA | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | NUCKOLLS |  | 03 | 7065021 | Triple 3.66m x 18.5m concrete box culvert on Oak Creek 1.0 mile south of Oak on a county road. | Bridge Replacement | 2010-02-02 | 2010-08-30 | 2010-11-27 | 2010-12-15 | 302190 |  | 7065021
7760 | NEBRASKA | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEBRASKA | PHELPS |  | 03 | 7069015 | Triple 10' x 8' concrete box culvert on the Central Nebraska Public Power Irrigation District canal on a county road 1 miles west of Funk | Bridge Replacement | 2010-01-25 | 2010-10-18 | 2010-11-27 | 2011-04-13 | 151854 |  | 7069015
7761 | NEBRASKA | Completed | C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS | OMAHA (IA) | 02 | 7941001 | The project consists of the removal of the upper 2 inches of the existing asphaltic concrete (asphalt) pavement to remove rutting on seven segments of 2 and 3-lane rural roadways, including turn lanes | Pavement Improvement | 2010-02-12 | 2010-10-06 | 2010-10-30 | 2010-11-16 | 1860020 |  | 7941001
7762 | NEBRASKA | Completed | C240 | Highway Infrastructure Investment Grant | NEBRASKA | CLAY |  | 03 | S18B104 | This project is on the Edgar Spur from N-14 to the city of Edgar, a length of 4.0 miles. The scope consists of resurfacing and widening the existing roadway to provide a 24' roadway with 1' surfaced s | Pavement Improvement | 2009-04-07 | 2009-05-11 | 2009-10-31 | 2010-08-21 | 1947585 | 3.990 | S18B104
7763 | NEBRASKA | Completed | C250,C220,C200,C230 | Highway Infrastructure Investment Grant | NEBRASKA | DOUGLAS, LANCASTER, STATEWIDE | STATEWIDE | Multiple | STWD093 | This project assists counties, municipalilties and metropolitan planning organizations in completing requirements for environmental documentation on ARRA projects. Six consulting engineering firms are engaged in this task and have begun their work. | Other | 2009-07-09 | 2009-07-09 | 2013-07-30 | 2010-03-01 | 997500 | 0.000 | STWD093
7764 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CHURCHILL |  | 02 | 0001097 | The Nevada Department of Transportation in coordination with Churchill County will resurface the existing asphalt with three inches of new asphalt and fog seal. This will improve driving quality by re | Pavement Improvement | 2010-08-23 | 2010-08-23 | 2010-09-13 | 2010-09-08 | 316096 |  | 0001097
7765 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CHURCHILL |  | 02 | 0001098 | The Nevada Department of Transportation in coordination with the City of Fallon will microsurface Baily Street, Whitaker Street, West Fifth Street East Street, Stillwater Avenue and Center Street. Thi | Pavement Improvement | 2010-08-23 | 2010-08-23 | 2010-09-13 | 2010-09-08 | 153055 |  | 0001098
7766 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003115 | The City of Boulder City will resurface approximately 1.3 miles of the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-06-20 | 2010-06-20 | 998056.65 |  | 0003115
7767 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003116 | The City of Las Vegas will construct intersection improvements including traffic signals, lighting, median islands and sidewalk improvements at various intersections within the city to provide safer and more efficient intersections. | Safety/Traffic Management | 2010-08-09 | 2010-09-20 | 2011-07-18 | 2012-02-07 | 1314752 |  | 0003116
7768 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003117 | The City of North Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-03-01 | 2010-03-01 | 2010-06-29 | 2010-10-08 | 2752865 |  | 0003117
7769 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003118 | The City of Henderson will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-03-29 | 2010-03-30 | 2010-08-01 | 2010-07-13 | 840814 |  | 0003118
7770 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | Multiple | 0003119 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-01-19 | 2010-01-25 | 2010-09-17 | 2010-09-08 | 1209550 |  | 0003119
7771 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | Multiple | 0003120 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-01-19 | 2010-01-25 | 2010-09-17 | 2010-09-08 | 942171 |  | 0003120
7772 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003121 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-01-19 | 2010-01-25 | 2010-09-17 | 2010-09-08 | 647543 |  | 0003121
7773 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003122 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-01-19 | 2010-01-25 | 2010-09-17 | 2010-09-08 | 1150411 |  | 0003122
7774 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003123 | The City of Henderson will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-12-13 | 2010-09-16 | 2582000 |  | 0003123
7775 | NEVADA | Completed | C200 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003124 | The City of Henderson will reconstruct approximately 1.7 miles of the existing roadway. This will improve driving quality by widening the road, which will make the road safer and extend Volunteer Blvd to the Executive Airport Entrance. | Pavement Improvement | 2010-04-14 | 2010-05-03 | 2010-10-14 | 2010-11-18 | 1084976 |  | 0003124
7776 | NEVADA | Completed | C200 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003125 | Clark County will resurface the top four inches of approximately 3.5 miles of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smo | Pavement Improvement | 2010-09-20 | 2010-09-27 | 2011-01-18 | 2011-02-15 | 2893198 |  | 0003125
7777 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003126 | The City of Mesquite will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-01-28 | 2010-02-26 | 749979.1 |  | 0003126
7778 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003127 | The City of Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life | Pavement Improvement | 2010-03-15 | 2010-03-15 | 2011-01-24 | 2011-12-08 | 1390263 |  | 0003127
7779 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003129 | Clark County will resurface the top four inches of approximately 1.8 miles of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smo | Pavement Improvement | 2010-07-12 | 2010-07-26 | 2010-10-31 | 2010-09-01 | 1758565.46 |  | 0003129
7780 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003130 | Clark County will resurface the top four inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing approximately eight miles. This extends the life of Lamb Blvd, T | Pavement Improvement | 2010-08-17 | 2010-08-17 | 2010-12-15 | 2011-01-20 | 5136061.65 |  | 0003130
7781 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003131 | Clark County will reconstruct 15 existing bus stops along Maryland Parkway between east Reno and Sahara. | Transportation Enhancements | 2010-01-24 | 2010-01-24 | 2010-02-25 | 2010-03-10 | 321080.3 |  | 0003131
7782 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | Multiple | 0003133 | Clark County will resurface the top four inches of approximately 3.2 miles of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smo | Pavement Improvement | 2010-07-06 | 2010-07-06 | 2010-10-04 | 2010-10-08 | 3349157.56 |  | 0003133
7783 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | Multiple | 0003134 | The City of Las Vegas will construct intersection improvements including traffic signals, lighting, median islands and sidewalk improvements at the intersections of Bonanza Road and Tonopah Ave. and S | Safety/Traffic Management | 2010-10-11 | 2010-10-20 | 2011-04-09 | 2012-02-07 | 775671 |  | 0003134
7784 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 02 | 0003140 | The City of Mesquite will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 2010-04-26 | 2010-05-18 | 2010-06-25 | 2010-06-30 | 202658.4 |  | 0003140
7785 | NEVADA | Completed | C950 | Ferryboat | NEVADA | CLARK | LAS VEGAS | 01 | 0003141 | The City of North Las Vegas will resurface the top inch of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-08-02 | 2010-08-24 | 2010-10-31 | 2010-11-23 | 2135830 |  | 0003141
7786 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0003142 | The City of Las Vegas will resurface the three inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the | Pavement Improvement | 2010-05-17 | 2010-05-28 | 2010-09-20 | 2010-09-08 | 1609058 |  | 0003142
7787 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 03 | 0003143 | The City of Henderson will resurface the top two inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2010-07-21 | 2010-07-06 | 337230 |  | 0003143
7788 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | DOUGLAS |  | 02 | 0005018 | The Nevada Department of Transportation in coordination with Douglas County will resurface the existing asphalt with a two inches of new asphalt. This will improve driving quality by resurfacing the r | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-09-30 | 2010-08-31 | 511571 |  | 0005018
7789 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0007033 | The City of Elko will resurface the top inche of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of | Pavement Improvement | 2010-05-05 | 2010-05-05 | 2010-08-09 | 2010-08-18 | 868135 |  | 0007033
7790 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | ESMERALDA |  | 02 | 0009005 | The Nevada Department of Transportation will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-12-06 |  | 2011-05-31 | 2011-08-28 | 582401 |  | 0009005
7791 | NEVADA | Completed | C250 | Highway Infrastructure Investment Grant | NEVADA | EUREKA |  | 02 | 0011036 | Eureka County will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of 11th Street from SR278 to County Road 101. | Pavement Improvement | 2010-05-19 | 2010-07-19 | 2010-08-06 | 2010-08-19 | 370980.2 |  | 0011036
7792 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0013019 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade sur | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2010-01-04 | 2010-05-03 | 1588585 |  | 0013019
7793 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0013021 | The Nevada Department of Transportation will resurface the existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend th | Pavement Improvement | 2010-10-25 | 2010-10-26 | 2011-06-30 | 2011-09-27 | 363273.12 |  | 0013021
7794 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0013022 | The Nevada Department of Transportation will coldmill 3 inches depth of existing asphalt pavement and place a 5 inch plantmix asphalt overlay with cape seal. This will improve driving quality by resur | Pavement Improvement | 2010-10-25 | 2010-10-26 | 2011-06-30 | 2011-09-27 | 939475.34 |  | 0013022
7795 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | LANDER |  | 02 | 0015015 | The Nevada Department of Transportation will resurface the existing asphalt with new asphalt, replace substandard street lights and repair damaged curb. This will improve driving quality by updating t | Pavement Improvement | 2010-08-23 | 2010-08-23 | 2010-10-01 | 2010-09-23 | 343332.03 |  | 0015015
7796 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | LINCOLN |  | 02 | 0017019 | The Nevada Department of Transportation will Place a chip seal on 6.2 miles of Rose Valley Rd,West of Ursine in Lincoln County, Nevada. to extend its service life. | Pavement Improvement | 2010-10-12 | 2011-06-06 | 2011-05-31 | 2011-06-30 | 426960 |  | 0017019
7797 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | LYON |  | 02 | 0019019 | The Nevada Department of Transportation will place Geotextile Fabric and a 2.5 inch overlay with fog seal on 1.9 miles of Six Mile Canyon Rd. to restore the pavement structure and extend its service life in Lyon County. | Pavement Improvement | 2010-11-01 | 2011-06-13 | 2010-12-31 | 2011-07-08 | 501913.64 |  | 0019019
7798 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | LYON |  | 02 | 0019020 | The Nevada Department of Transportation in coordination with the City of Fernley will preserve and extend the pavement life of various city streets by placing a slurry seal over the existing roadway. | Pavement Improvement | 2010-09-13 | 2010-09-14 | 2010-09-28 | 2010-09-17 | 132568.68 |  | 0019020
7799 | NEVADA | Completed | C250 | Highway Infrastructure Investment Grant | NEVADA | MINERAL |  | 02 | 0021045 | Nye County will preserve and extend the pavement life of a section of Gamebird Rd. by placing a 3.5 inch asphalt overlay on the existing roadway. | Safety/Traffic Management | 2010-12-13 | 2010-12-13 | 2011-12-31 | 2011-03-30 | 148749.44 |  | 0021045
7800 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | NYE |  | 02 | 0023011 | Nye County will preserve and extend the pavement life of a section of Gamebird Rd. by placing a 3.5 inch asphalt overlay on the existing roadway. | Pavement Improvement | 2010-10-04 | 2010-10-27 | 2010-10-15 | 2010-11-03 | 533738 |  | 0023011
7801 | NEVADA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEVADA | CARSON CITY | CARSON CITY | 02 | 0025016 | Carson City will preserve and extend the pavement life of several city streets by placing a thin asphalt/slurry overlay on the existing roadways | Pavement Improvement | 2010-05-03 | 2010-05-12 | 2010-10-01 | 2010-07-01 | 662374.05 |  | 0025016
7802 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | PERSHING |  | 02 | 0027016 | The Nevada Department of Transportation will add sidewalks to increase the safety of pedestrians and make routes ADA compliant on 0.71 miles of roads in Lovelock, Nevada. | Transportation Enhancements | 2010-08-02 | 2010-08-02 | 2010-08-31 | 2010-08-27 | 118742.17 |  | 0027016
7803 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | PERSHING |  | 02 | 0027017 | The Nevada Department of Transportation in coordination with Pershing County will preserve and extend the pavement life of about 1.5 miles of Grass Valley Rd. south of Dutchman Dr. by placing a 3 inch asphalt overlay on the existing roadway. | Pavement Improvement | 2010-10-25 | 2010-10-26 | 2011-06-30 | 2011-09-27 | 363798.71 |  | 0027017
7804 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | STOREY |  | 02 | 0029013 | The Nevada Department of Transportation in coordination with Storey County will preserve and extend the pavement life of about 2.7 miles of Six Mile Canyon Rd. in various locations by placing a 2.5 in | Pavement Improvement | 2010-11-01 | 2011-06-13 | 2010-12-31 | 2011-07-08 | 418378.32 |  | 0029013
7805 | NEVADA | Completed | C220 | Highway Infrastructure Investment Grant | NEVADA | CARSON CITY, LYON |  | 02 | 0032071 | The Nevada Commission for the Reconstruction of the V&T Railway will construct just over one mile of railroad track along of the historic Virginia and Truckee Railway roadbed on existing railroad grade. | Transportation Enhancements | 2009-07-16 | 2009-07-21 | 2009-11-04 | 2009-11-06 | 2033873.63 |  | 0032071
7806 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | WHITE PINE |  | 02 | 0033014 | The Nevada Department of Transportation will place a slurry seal on 3 miles of streets in Ely, Nevada to extend their service life. | Pavement Improvement | 2010-05-24 | 2010-06-28 | 2010-10-11 | 2010-11-17 | 191503 |  | 0033014
7807 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | WHITE PINE |  | 02 | 0033015 | The Nevada Department of Transportation will construct curb, gutter, sidewalk on the south side of the street on SR 221 Chestnut St. from 6th St. to 10th St to provide pedestrian enhancements in Carlin, Nevada. | Pavement Improvement | 2010-05-24 | 2010-06-28 | 2010-10-11 | 2010-11-17 | 593083 |  | 0033015
7808 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK |  | 02 | 0151140 | NDOT will use asphalt overlay on I-15 From CA/NV Stateline to Milepost 17.00 (CL0.00 to CL17.00) as part of the pavement preservation program. | Pavement Improvement | 2009-11-23 | 2010-05-17 | 2010-09-06 | 2010-12-23 | 8379233 | 16.000 | 0151140
7809 | NEVADA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 02 | 0152039 | NDOT will use asphalt overlay on I-15 from .369 MN of East Mesa Intg. To 1.033 MW of the Bunkerville Intg. from 1.033 MW of Bunkerville Intg. To 1.889 MS of West Mesquite Intg. as part of the pavement preservation program. | Pavement Improvement | 2010-05-10 | 2010-05-17 | 2010-09-10 | 2010-11-08 | 5325006.5 |  | 0152039
7810 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0221004 | The Nevada Department of Transportation in coordination with the City of Carlin will construct curb, gutter, sidewalk on the south side of the street on SR 221 Chestnut St. from 6th St. to 10th St. | Transportation Enhancements | 2010-07-27 | 2010-07-27 | 2010-08-24 | 2010-08-15 | 213766.45 |  | 0221004
7811 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0223002 | The Nevada Department of Transportation in coordination with the City of Wells will construct pedestrian improvements including curb, gutter, sidewalk on the east side of the street on SR 223 Humboldt St from I 80 to Sixth St. | Transportation Enhancements | 2010-07-26 | 2010-07-26 | 2010-08-27 | 2010-09-02 | 175500 |  | 0223002
7812 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0289001 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2010-01-04 | 2010-05-03 | 1011170 |  | 0289001
7813 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | STATEWIDE |  |  | 0318013 | The Nevada Department of Transportation will generally cold in place recycle 3 inches depth of existing asphalt pavement, a 3 inch plantmix asphalt overlay with open grade surface course, or 8 inch ro | Pavement Improvement | 2009-07-13 | 2009-07-27 | 2010-02-22 | 2010-09-24 | 14016262 |  | 0318013
7814 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CHURCHILL |  | 02 | 0801165 | The Nevada Department of Transportation will cold mill 1.5 inches depth of existing asphalt pavement and place a plantmix asphalt overlay with open grade surface course. This will improve driving qual | Pavement Improvement | 2009-12-21 | 2010-05-17 | 2010-06-21 | 2011-04-12 | 10820369 |  | 0801165
7815 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | PERSHING |  | 02 | 0802052 | NDOT will preserve and extend the pavement life of about 14 miles of I-80 by milling 1 inch of existing pavement and replacing it with 3 inches of new asphalt and an open-graded wearing course. | Pavement Improvement | 2009-06-08 | 2009-06-08 | 2009-12-07 | 2010-09-16 | 12349915 |  | 0802052
7816 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | LANDER |  | 02 | 0803059 | The Nevada Department of Transportation will construct 8 inch roadbed modification with 5.5 inches of plantmix asphalt with open grade surface course. This will improve driving quality by resurfacing | Pavement Improvement | 2009-07-20 | 2009-08-17 | 2009-10-26 | 2009-11-30 | 2007907.83 |  | 0803059
7817 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK |  | 02 | 0932002 | NDOT will use asphalt overlay on US93 from 15.82 miles N of I15 at Garnet Interchange to the CL/LN County Line (CL67.83 to CL86.59) as part of the pavement preservation program. | Pavement Improvement | 2009-09-14 | 2010-04-05 | 2010-09-13 | 2011-06-10 | 6088224.21 | 19.000 | 0932002
7818 | NEVADA | Completed | C250 | Highway Infrastructure Investment Grant | NEVADA | LINCOLN |  | 02 | 0932004 | The Nevada Department of Transportation will construct will pedestrian improvements including curb, gutter and sidewalk on US 93 from .50 MW of SR 317 to .05 MW of SR 317. | Transportation Enhancements | 2009-11-20 | 2009-11-20 | 2010-10-08 | 2010-10-10 | 136017 |  | 0932004
7819 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | WHITE PINE |  | 02 | 0934016 | The Nevada Department of Transportation will resurface the top three inches of existing asphalt with new asphalt. This will improve driving quality by resurfacing the road, which will make the road sm | Pavement Improvement | 2010-05-24 | 2010-06-28 | 2010-10-11 | 2010-11-17 | 9921759 |  | 0934016
7820 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0935006 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 3 inch plantmix asphalt overlay with open grade surface course. This will imp | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-07 | 2010-08-10 | 9811830.43 |  | 0935006
7821 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 0935007 | The Nevada Department of Transportation will construct a approximately 66 feet wide by 162 feet long precast concrete arch overpass in a location with a history of many animal/vehicle collisions and a | New Bridge Construction | 2009-08-10 | 2009-09-09 | 2009-11-28 | 2010-08-09 | 1075515 |  | 0935007
7822 | NEVADA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEVADA | ELKO |  | 02 | 093A004 | The Nevada Department of Transportation in coordination with the City of West Wendover will construct curb, gutter, sidewalk on the east side of the street on US 93A from W. Wendover Blvd to I 80 WB Off ramp. | Transportation Enhancements | 2010-08-16 | 2010-08-16 | 2010-09-16 | 2010-09-15 | 183090 |  | 093A004
7823 | NEVADA | Underway | C220,C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK |  | 03 | 0951041 | NDOT will build a Visitor's Center on US 95 to enhance the experience of the travelling public. | Transportation Enhancements | 2009-07-15 | 2009-07-15 | 2011-02-16 |  | 3389007 | 0.000 | 0951041
7824 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0952054 | NDOT will use asphalt overlay on US 95 from 0.737 MN of SR157, Charleston Park Road, to 7.716 MN of SR156, Lee Canyon Road, as part of the pavement preservation program. | Pavement Improvement | 2010-05-10 | 2010-05-17 | 2011-03-17 | 2011-07-07 | 24772969 |  | 0952054
7825 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 0952055 | NDOT will perform landscaping on US95 from Martin Luther King Blvd. to Rainbow Blvd. | Transportation Enhancements | 2009-09-21 | 2009-09-29 | 2010-07-05 | 2009-11-30 | 3477042 |  | 0952055
7826 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | NYE |  | 02 | 0952056 | NDOT will use asphalt overlay on US 95 from 1.63 mi S of Jackass Flat to 0.62 mi N of SR 160. MP NY6.98 - NY14.38 as part of the pavement preservation program. | Pavement Improvement | 2009-09-14 | 2009-09-14 | 2009-11-23 | 2009-11-16 | 2161370.54 | 7.000 | 0952056
7827 | NEVADA | Completed | C250 | Highway Infrastructure Investment Grant | NEVADA | MINERAL |  | 02 | 0954015 | The Nevada Department of Transportation in coordination with Mineral County expects to improve traffic management and pedestrian safety at the intersection of US 95 and SR 359 in Hawthorne by upgrading the traffic signal and making ADA improvements. | Safety/Traffic Management | 2010-12-13 | 2010-12-20 | 2011-12-31 | 2011-03-30 | 19080.42 |  | 0954015
7828 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | MINERAL |  | 02 | 0954016 | 3 inch cold in place recycle, 3 inch PBS overlay | Pavement Improvement | 2011-01-18 |  | 2011-06-30 | 2011-10-03 | 3301774 |  | 0954016
7829 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0956007 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2010-01-04 | 2010-05-03 | 1191458 |  | 0956007
7830 | NEVADA | Completed | C240 | Highway Infrastructure Investment Grant | NEVADA | HUMBOLDT |  | 02 | 0956008 | The Nevada Department of Transportation will cold in place recycle 3 inches depth of existing asphalt pavement and place a 1 inch leveling course, a 3 inch plantmix asphalt overlay with open grade su | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2010-01-04 | 2010-05-03 | 3256353 |  | 0956008
7831 | NEVADA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEVADA | DOUGLAS, CARSON CITY | CARSON CITY | 02 | 3951021 | The Nevada Department of Transportation in coordination with Douglas County will widen US 395 in the northbound direction for approximately 6000 feet from Sunridge Dr. east to Lupin Dr. This will all | Pavement Widening | 2010-04-26 | 2010-04-26 | 2010-10-08 | 2010-10-22 | 3018798 |  | 3951021
7832 | NEVADA | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | NEVADA | CARSON CITY | CARSON CITY |  | 3951022 | NEVADA DEPARTMENT OF TRANSPORTATION WILL PERFORM LANDSCAPING ON US395, CARSON CITY BYPASS, AT 5TH STREET GRADE SEPARATION AND FAIRVIEW INTERCHANGE. | Transportation Enhancements | 2010-07-12 | 2010-10-25 | 2010-09-10 | 2011-09-16 | 1314644 |  | 3951022
7833 | NEVADA | Completed | C230 | Highway Infrastructure Investment Grant | NEVADA | CLARK | LAS VEGAS | 01 | 5151036 | Landscaping | Transportation Enhancements | 2010-12-20 | 2011-01-31 | 2011-04-22 | 2011-06-06 | 1001178 |  | 5151036
7834 | NEVADA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEVADA | WASHOE | RENO | 02 | 5801029 | The NDOT and the Regional Transportation Commission (RTC) of Washoe County will reconfigure the existing Neil Rd. Interchange to a split diamond configuration with Meadowood Mall Way and extend Meadowood Mall Way under I-580. | New Construction | 2010-05-17 | 2010-06-14 | 2012-02-21 |  | 18473423 |  | 5801029
7835 | NEVADA | Completed | C490 | OJT/SS | NEVADA | STATEWIDE |  |  | FY09002 | Work necessary to train minorities, women and disadvantaged individuals to become commercial vehicle operators | Other | 2011-04-12 | 2011-04-12 | 2012-12-31 | 2011-12-31 | 240428 |  | FY09002
7836 | NEW HAMPSHIRE | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000091 | The Winnipesaukee River Trail Phase 2B project extends an existing 3 mile bicycle and pedestrian trail facility by providing signs for a temporary connection from Park Street in Northfield to Morrison | Transportation Enhancements | 2010-02-09 | 2010-05-17 | 2010-08-30 | 2010-11-16 | 429646.25 | 1.000 | A000091
7837 | NEW HAMPSHIRE | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH |  | 02 | A000094 | In Hillsborough, on route US 202/NH 9, a historic stone arch bridge will be preserved and resurfaced to better accommodate pedestrians and bicycles | Transportation Enhancements | 2009-10-20 | 2010-05-10 | 2010-06-14 | 2010-07-23 | 150045 | 0.000 | A000094
7838 | NEW HAMPSHIRE | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH | NASHUA | 02 | A000095 | In Hudson, the town will be building almost a mile of new sidewalk and a nearly mile long bicycle lane on Route 102 between Evergreen Drive and Megan. | Transportation Enhancements | 2009-07-17 | 2010-07-19 | 2010-07-01 | 2010-09-30 | 357000 | 0.000 | A000095
7839 | NEW HAMPSHIRE | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 02 | A000127 | On I-93 near Exit 3 in the Salem and Windham area, new northbound and southbound travel lanes will be constructed to improve safety and relieve congestion. | New Construction | 2009-05-07 | 2009-06-17 | 2011-11-01 | 2012-03-15 | 27885145.95 | 2.200 | A000127
7840 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH |  | 01 | A000258 | This project will widen the FE Everett Turnpike to provide improved access to and from the Manchester-Boston Regional Airport. | Pavement Widening | 2009-04-16 | 2009-05-11 | 2011-06-01 | 2011-07-06 | 9615508.68 | 2.900 | A000258
7841 | NEW HAMPSHIRE | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH |  | 02 | A000341 | In Bennington, this project will provide over a half-mile of sidewalk with crosswalks, and will clearly separate these facilities from vehicular traffic and parking to improve pedestrian access and safety. | Transportation Enhancements | 2009-07-22 | 2009-08-10 | 2010-05-01 | 2010-09-30 | 601600.1 | 0.000 | A000341
7842 | NEW HAMPSHIRE | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000342 | This project in Boscawen will provide new sidewalks on Main Street through the route US3/4 intersection and along King Street. New crosswalks and pedestrian signals will enhance pedestrian safety at the US3/4 intersection. | Transportation Enhancements | 2009-08-19 | 2009-09-24 | 2010-05-01 | 2010-05-27 | 431935.96 | 0.000 | A000342
7843 | NEW HAMPSHIRE | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STRAFFORD |  | 01 | A000345 | On Durham's Main Street near the downtown area and the University of New Hampshire, this project will improve bicycle and pedestrian access and mobility by providing over a mile of new sidewalks, sepa | Transportation Enhancements | 2009-11-13 | 2009-12-08 | 2010-09-30 | 2010-08-30 | 758258.55 | 0.000 | A000345
7844 | NEW HAMPSHIRE | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | BELKNAP |  | 01 | A000349 | This project will provide around 1.5 miles of trail within an active rail corridor for bicyclists and pedestrians that will run from Main Street in Laconia to Elm Street in Lakeport. Improvements will | Transportation Enhancements | 2009-08-31 | 2009-09-03 | 2009-12-01 | 2010-06-22 | 575980.5 | 0.000 | A000349
7845 | NEW HAMPSHIRE | Completed | C200 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH | MANCHESTER | 01 | A000390 | This project consists of earthwork west of the Merrimack River for Manchester Airport Access Road. | New Construction | 2009-07-17 | 2009-08-05 | 2011-06-01 | 2010-11-08 | 4110519.37 | 0.620 | A000390
7846 | NEW HAMPSHIRE | Completed | C220,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM |  | 02 | A000558 | The Windham Depot project will provide a restored historic train depot that will function as a combined visitor center, museum and way station at the head of a 4 mile bicycle and pedestrian trail from Windham to Salem. | Transportation Enhancements | 2010-03-02 | 2010-03-15 | 2010-07-15 | 2010-07-15 | 219755 | 0.000 | A000558
7847 | NEW HAMPSHIRE | Completed | C220 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | HILLSBOROUGH |  | 02 | A000566 | This project in Litchfield will help improve pedestrian and bicycle access and mobility by building nearly 2 miles of pedestrian and bike trail along Albuquerque Avenue. | Transportation Enhancements | 2009-09-10 | 2009-09-25 | 2010-05-15 | 2010-05-17 | 372477.25 | 0.000 | A000566
7848 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM |  | 01 | A000620 | In Epping and Exeter, this project will provide new pavement on a 9.5 mile section of State Route 101 between Exit 6 and the Squamscott River Bridge in Exeter. | Pavement Improvement | 2009-04-02 | 2009-04-10 | 2009-08-01 | 2009-11-03 | 7073670.8 | 9.740 | A000620
7849 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000837 | This project will provide a thin layer of new pavement on about 7 miles of I-89 roadway from Exit 12A to Exit 13 in the New London and Grantham area. | Pavement Improvement | 2009-05-07 | 2009-06-04 | 2009-09-01 | 2009-09-22 | 1032533.01 | 6.086 | A000837
7850 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000838 | This project will provide crack filling and will provide a thin layer of new pavement on 4.9 miles of I-393 from I-93 to it's ending point in the Concord area. | Pavement Improvement | 2009-06-18 | 2009-06-24 | 2009-09-01 | 2009-11-03 | 817740 | 3.197 | A000838
7851 | NEW HAMPSHIRE | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000839 | This project provides new pavement to 5.4 miles of I-93 from Exit 14 to Exit 17 from the Concord area to Canterbury. Guardrail posts will also be replaced to improve safety. | Pavement Improvement | 2009-06-18 | 2009-06-24 | 2010-10-01 | 2010-09-29 | 5356186 | 6.170 | A000839
7852 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000840 | This project in the Sanbornton area provides new pavement on a 4 mile section of I-93 from north of Exit 19 in Northfield to Exit 22 in Sanbornton. The project also includes some bridge rehabilitation work. | Pavement Improvement | 2009-05-21 | 2009-06-29 | 2010-06-01 | 2010-07-28 | 2188626 | 6.270 | A000840
7853 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | GRAFTON |  | 02 | A000841 | This project provides new pavement on 7 miles of I-93 from Plymouth to Thornton, just south of the Exit 27 interchange north to the railroad bridge. | Pavement Improvement | 2009-05-21 | 2009-06-09 | 2009-10-01 | 2009-10-14 | 747127.22 | 7.830 | A000841
7854 | NEW HAMPSHIRE | Completed | C200 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI | 01 | A000842 | This Portsmouth area project provides new pavement and some bridge deck and guardrail improvements for safety on about 1 and a half miles of I-95 from the Portsmouth traffic circle to the bridge over the Piscataqua River. | Pavement Improvement | 2009-07-17 | 2009-07-30 | 2010-08-01 | 2010-09-01 | 3470149.15 | 12.966 | A000842
7855 | NEW HAMPSHIRE | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | GRAFTON |  | 02 | A000843 | This project provides new pavement and bridge improvements on 5.4 miles of I-93 from Exit 30 to Exit 32 in the Woodstock and Lincoln areas. | Pavement Improvement | 2009-07-17 | 2009-07-30 | 2011-08-26 | 2011-09-02 | 9082359.5 | 58.275 | A000843
7856 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000845 | This project is located in the New Hampton and Ashland and will provide new pavement and bridge improvements on about 6 miles of I-93. | Pavement Improvement | 2009-05-21 | 2009-06-04 | 2010-06-01 | 2010-08-11 | 3924108.25 | 6.083 | A000845
7857 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | MERRIMACK |  | 02 | A000846 | This New London area project on 5 miles of I-89 provides new pavement from Exit 11 north to Exit 12A. | Pavement Improvement | 2009-04-02 | 2009-04-21 | 2010-08-01 | 2010-09-24 | 5315917 | 6.310 | A000846
7858 | NEW HAMPSHIRE | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000871 | This project provides new pavement on various roadways in the counties of Coos, Carroll, and Grafton. | Pavement Improvement | 2009-04-02 | 2009-05-05 | 2009-09-01 | 2009-11-04 | 3297522.19 | 56.580 | A000871
7859 | NEW HAMPSHIRE | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000872 | This project is located along multiple sections of roadway within the counties of Grafton, Sullivan, and Merrimack. The project involves the resurfacing of approx. 48 miles of various roadways.; all | Pavement Improvement | 2009-04-02 | 2009-05-14 | 2009-09-02 | 2009-11-02 | 3161306.53 | 47.180 | A000872
7860 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000873 | This project provides about 48 miles of new pavement along many sections of roadway in Carroll, Grafton, and Belknap counties. | Pavement Improvement | 2009-04-16 | 2009-05-27 | 2009-09-03 | 2009-10-26 | 3118908.13 | 47.260 | A000873
7861 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000874 | This project provides new pavement and safety improvements on about 41 miles of multiple sections of roadway in Cheshire and Hillsborough counties. | Pavement Improvement | 2009-05-07 | 2009-05-20 | 2009-09-01 | 2010-07-13 | 2710153.4 | 40.630 | A000874
7862 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A000875 | This project provides about 28 miles of new pavement on various sections of roadway in Merrimack, Hillsborough and Rockingham counties. | Pavement Improvement | 2009-05-07 | 2009-05-28 | 2009-09-01 | 2009-08-26 | 3009237.13 | 35.320 | A000875
7863 | NEW HAMPSHIRE | Completed | C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE | BOSTON(NH)LAWREN-HAVERH,MA(MA-NH-RI |  | A000876 | This project provides new pavement and intersection safety improvements on various roadways in Rockingham and Strafford counties. | Pavement Improvement | 2009-05-07 | 2009-06-11 | 2009-09-01 | 2009-11-09 | 2941966.74 | 43.380 | A000876
7864 | NEW HAMPSHIRE | Completed | C200 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | GRAFTON |  | 02 | A000947 | This project on I-89 provides a more efficient I-89/NH 12A interchange at Exit 20 in Lebanon. The project includes bridge and ramp improvements for the interchange, including the bridge over the K-Mart Upper Valley Plaza Connector. | Pavement Widening | 2009-10-08 | 2009-10-13 | 2011-10-28 | 2012-05-03 | 14717629.33 | 0.900 | A000947
7865 | NEW HAMPSHIRE | Completed | C200 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A001014 | This project consists of 18 miles of roadway resurfacing in Cheshire, Hillsborough, and Sullivan counties. | Pavement Improvement | 2010-03-11 | 2010-04-08 | 2010-08-20 | 2010-06-28 | 973593 | 18.550 | A001014
7866 | NEW HAMPSHIRE | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | STATEWIDE |  |  | A001015 | This project consists of 42 miles of roadway resurfacing in Hillsborough, Merrimack, and Rockingham counties. | Pavement Improvement | 2010-03-11 | 2010-04-13 | 2010-08-20 | 2010-09-23 | 2118692 | 41.490 | A001015
7867 | NEW HAMPSHIRE | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM |  | 01 | A001016 | This project consists of 41 miles of raodway resurfacing in Strafford and Rockingham counties. | Pavement Improvement | 2010-03-11 | 2010-06-11 | 2010-08-20 | 2010-08-12 | 1243349 | 41.280 | A001016
7868 | NEW HAMPSHIRE | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | COOS |  | 02 | A001031 | This project consists of 72 miles of roadway resurfacing in Coos, Carroll, Grafton, Merrimack, and Sullivan counties. | Pavement Improvement | 2010-04-14 | 2010-04-23 | 2009-09-10 | 2010-10-13 | 4336142.4 | 72.700 | A001031
7869 | NEW HAMPSHIRE | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW HAMPSHIRE | ROCKINGHAM |  | 01 | A001049 | This project provides about 8 miles of roadway resurfacing, new guardrail and drainage improvements from Exeter to Hampton. | Pavement Improvement | 2010-02-09 | 2010-03-09 | 2010-09-10 | 2010-11-10 | 3287471.07 | 8.836 | A001049
7870 | NEW JERSEY | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | CAPE MAY |  | 02 | 0007109 | The Route 52 Causeway Contract B project replaces the two bridges located closest to Somers Point and Ocean City at Ship Channel and Beach Thorofare, respectively, with high level (55' clearance) brid | Bridge Replacement | 2009-07-10 | 2009-08-11 | 2012-01-25 |  | 73141235 | 1.090 | 0007109
7871 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 02 | 0012110 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2010-05-10 | 2010-08-02 | 2013-09-30 | 2010-11-19 | 843907 | 2.000 | 0012110
7872 | NEW JERSEY | Completed | C200 | Highway Infrastructure Investment Grant | NEW JERSEY | ATLANTIC |  | 02 | 0016157 | This project will replace deteriorated pavement with new pavement along 4.5 miles of Route 30 in Hammonton and Mullica Townships in Atlantic County NJ. | Pavement Improvement | 2009-07-08 | 2009-08-24 | 2009-12-01 | 2009-09-28 | 2219021.71 | 4.400 | 0016157
7873 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 0016158 | This project will relieve flooding on Route 30 for 1.5 miles by upgrading pavement and replaceing the inlets, pipes and basins in Township of Pennsauken and City of Camden, Camden County. | Pavement Improvement | 2009-08-24 | 2009-09-21 | 2010-09-14 | 2010-11-10 | 9969216 | 1.650 | 0016158
7874 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 13 | 0018154 | The project will provide some full depth repairs, milling and overlay to either match existing grade or provide an increase in profile grade. | Pavement Improvement | 2010-11-30 | 2011-04-15 | 2011-09-09 | 2011-08-22 | 6000000 | 8.050 | 0018154
7875 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN |  | 03 | 0019110 | The project will extend the life of the bridge by including deck repair and curb repair on the entire deck (2.75 miles) of Rt.72 over the Manhawkin Bay in Townships of Stafford and Ship Bottom, Ocean County. | Bridge Improvement | 2009-09-04 | 2009-09-16 | 2010-07-23 | 2010-04-22 | 4863700 | 2.150 | 0019110
7876 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN |  | 03 | 0022105 | This project provides for the preservation of pavement on this section of Route 37. It consists of milling and overlay to either match the existing grade or will provide a two to three inch increase in the profile grade to improve roadway drainage. | Pavement Improvement | 2010-07-29 | 2010-08-25 | 2011-01-24 | 2010-11-24 | 4692264 | 5.950 | 0022105
7877 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN |  | 03 | 0022106 | This section of Route 37 has a bridge structure that crosses over Barnegat Bay. This project will provides for patching the existing deck as required and will preserve the exiting deck with an overla | Pavement Improvement | 2010-07-28 | 2010-09-17 | 2011-06-28 | 2011-04-29 | 3689892 | 2.030 | 0022106
7878 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 04 | 0025101 | The project includes full depth repairs, milling and overlay to match existing grade. | Pavement Improvement | 2010-12-22 | 2011-03-04 | 2011-07-25 | 2011-05-24 | 1756199 | 3.910 | 0025101
7879 | NEW JERSEY | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 06 | 0029163 | This project will design the work to replace the bridge deck of Route 18 over Route 1 in the city of New Brunswick, Middlesex County. | Other | 2009-09-01 | 2009-09-01 | 2012-05-08 |  | 1231172 | 0.500 | 0029163
7880 | NEW JERSEY | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | 04 | 0029166 | Rt 18, Pavement Rehabilitation, Monmouth County, Construction. | Pavement Improvement | 2011-01-14 | 2011-02-07 | 2011-11-18 | 2011-11-19 | 4141796 | 11.600 | 0029166
7881 | NEW JERSEY | Completed | C200,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 12 | 0031124 | This project will replace deteriorated pavement with new pavement and improve water drainage along 1 one mile of Route 29 in West Amwell Township & City of Lambertville in Hunterdon County. | Pavement Improvement | 2009-08-19 | 2009-09-14 | 2010-10-04 | 2010-07-23 | 3247858 | 1.020 | 0031124
7882 | NEW JERSEY | Completed | C200 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON |  | 12 | 0031125 | This project is the utility relocaitons associated with the Route 29 project in West Amwell Township & City of Lambertville in Hunterdon County. | Other | 2009-08-19 | 2009-09-14 | 2010-10-04 | 2010-07-23 | 168405 | 1.020 | 0031125
7883 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON |  | 09 | 0033274 | This project will paint two Route 1&9(Truck) movable bridges over the Hackensack and Passaic Rivers in the cities of Newark, Jersey City and Kearny, Hudson and Essex County. | Pavement Improvement | 2009-07-16 | 2009-11-02 | 2011-12-31 | 2011-11-30 | 31115257 | 1.060 | 0033274
7884 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER |  | 12 | 0033277 | This project will replace deteriorated pavement with new pavement along 2 miles of Route 1 in both northbound and southbound directions located in the Townships of Lawrence and West Windsor, Mercer County. | Pavement Improvement | 2009-07-30 | 2009-08-04 | 2009-10-30 | 2010-03-18 | 3753866 | 2.020 | 0033277
7885 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 06 | 0034109 | This project will replace the bridge decks of Rt 440 NB over Ramp WI and Ramp WK over CR 514. Both bridges are within the interchange of RT 440, CR 514 and NJTA exit 10. in the township of Edison, Middlesex County. | Pavement Improvement | 2009-09-01 | 2009-09-15 | 2010-06-01 | 2010-07-26 | 4804851 | 0.270 | 0034109
7886 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 13 | 0034110 | This project will design the work to replace the bridge deck of Route 440 Ramp V over Boggs Street, West Side Avenue, State Street and NJ transit in the city of Perth Amboy, Middlesex County. | Other | 2009-07-30 | 2009-10-09 | 2010-09-01 | 2011-04-05 | 1038189 | 0.230 | 0034110
7887 | NEW JERSEY | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION |  | 10 | 0040168 | This project will replace the Route 22 bridge over the Conrail railroad and Liberty Avenue and improve safety by eliminating the substandard roadway features in Hillside Township, Union County. | Bridge Replacement | 2010-04-26 | 2010-05-26 | 2013-02-15 |  | 25556508 | 0.460 | 0040168
7888 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 09 | 0056151 | This project will design the work for a bridge deck replacement for Route 4 over Flat Rock Road in Englewwod City Bergen County | Other | 2009-08-31 | 2009-08-31 | 2010-09-30 | 2011-11-22 | 410961 | 0.200 | 0056151
7889 | NEW JERSEY | Completed | C200,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CAPE MAY | ATLANTIC CITY | 02 | 0102113 | Cape May County will be preserving two of it's bridges structural integrity and extend their useful life by re-painting the crossings. | Bridge Improvement | 2010-08-16 | 2010-08-23 | 2013-09-30 | 2011-11-30 | 4395971 | 0.000 | 0102113
7890 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SALEM | ATLANTIC CITY | 02 | 0145101 | Salem County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on 2 miles | Pavement Improvement | 2010-08-30 | 2010-10-02 | 2013-09-30 | 2010-11-16 | 595605 | 4.180 | 0145101
7891 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0158104 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 2009-11-11 | 2009-11-19 | 2012-02-17 | 2009-11-30 | 338079.49 | 1.500 | 0158104
7892 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0158105 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-04-05 | 2010-04-05 | 2012-02-17 | 2010-04-21 | 415976.08 | 1.090 | 0158105
7893 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0158106 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-07-06 | 2010-07-06 | 2012-02-17 | 2010-08-10 | 290420.16 | 1.000 | 0158106
7894 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0160109 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2012-02-17 | 2010-05-04 | 314326 | 1.550 | 0160109
7895 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0160110 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-07-01 | 2010-07-19 | 2012-02-17 | 2010-08-20 | 199354.71 | 0.570 | 0160110
7896 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 02 | 0161103 | Gloucester County will install a new traffic signal to reduce travel delays, provide pedestrian crossings, and allow emergency access for the Fire Department. The project will also provide a new pave | Other | 2010-04-14 | 2010-04-17 | 2013-09-30 | 2010-09-24 | 286861 | 0.060 | 0161103
7897 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 0164101 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2010-09-27 | 2010-09-27 | 2013-09-30 | 2010-12-02 | 512445 | 1.400 | 0164101
7898 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | 0165101 | Morris County will improve two intersections along Ridgedale Ave to improve traffic flow, increase safety for pedestrians, and provide emergency access for the fire department. | Other | 2010-06-14 | 2010-06-28 | 2013-09-30 | 2011-12-27 | 262561 | 0.200 | 0165101
7899 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 0169101 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2009-11-09 | 2009-11-09 | 2013-09-30 | 2010-05-07 | 454516.08 | 1.100 | 0169101
7900 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | Multiple | 0169102 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2010-06-21 | 2010-07-06 | 2013-09-30 | 2010-08-27 | 1281241 | 2.500 | 0169102
7901 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | 0177106 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2009-11-02 | 2009-11-23 | 2013-09-30 | 2010-05-05 | 2618616 | 7.200 | 0177106
7902 | NEW JERSEY | Underway | C250,C200 | Highway Infrastructure Investment Grant | NEW JERSEY | ATLANTIC |  | 02 | 0181112 | This project will replace the Tuckahoe Road Bride over the NJ Tranist Cape May Branch in the City of Estell Manor, Atlantic County. | Bridge Replacement | 2010-03-02 | 2010-03-08 | 2013-09-30 |  | 4779469 | 0.200 | 0181112
7903 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN | ALLENTOWN-BETHLEHEM-EASTON (PA) | 05 | 0378108 | Warren County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Other | 2010-03-18 | 2010-04-01 | 2012-02-17 | 2010-06-10 | 682081 | 3.040 | 0378108
7904 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN | NEW YORK-NORTHEASTERN NJ (NY) | 05 | 0378109 | Warren County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Other | 2010-03-18 | 2010-04-01 | 2012-02-17 | 2010-06-10 | 2184329.31 | 0.000 | 0378109
7905 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 05 | 0386103 | Sussex County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Pavement Improvement | 2010-05-11 | 2010-05-19 | 2012-02-17 | 2010-07-06 | 1013716.23 | 5.100 | 0386103
7906 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 05 | 0393108 | Sussex County will be rehabilitating the roadway to provide structural improvements and a new driving surface. This will improve driving quality by rehabilitating the road, which will make the road | Pavement Improvement | 2010-06-28 | 2010-07-01 | 2012-02-17 | 2010-08-13 | 734257 | 3.540 | 0393108
7907 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX |  | 10 | 0785101 | This project will replace deteriorated pavement with new pavement and improve safety along nearly 2 miles of I-78 in the City of Newark, Essex County. | Pavement Improvement | 2009-07-20 | 2009-08-31 | 2010-11-10 | 2011-04-01 | 15323524 | 1.430 | 0785101
7908 | NEW JERSEY | Completed | C200 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON |  | 07 | 0785102 | This project will design the work to replace the bridge deck of I-78 ramp A, over I-78 in Township of Clinton Hunterdon County. | Other | 2009-08-31 | 2009-08-31 | 2010-09-01 | 2010-09-09 | 407158.89 | 0.500 | 0785102
7909 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN |  | 05 | 0785103 | This project will remove the existing concrete slabs and replace with new pavement for nearly 1 mile on I-78 in Greenwich Township, Warren County. | Pavement Improvement | 2009-08-18 | 2009-09-14 | 2010-08-01 | 2010-05-11 | 4136329 | 0.540 | 0785103
7910 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 07 | 0785104 | The project will replace the existing deck on the I-78 Ramp 'A' over I-78 structure (Str. #1018-150). | Bridge Improvement | 2010-12-14 | 2011-02-01 | 2011-10-18 | 2011-07-26 | 1324369 | 0.060 | 0785104
7911 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC |  | 08 | 0805087 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 6 miles on I-80 Eastbound from West of Madison Ave to Polifly Road in the Counties of Bergen and Passaic. | Pavement Improvement | 2009-07-16 | 2009-08-19 | 2011-09-02 | 2010-11-01 | 17443481 | 6.500 | 0805087
7912 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX |  | 11 | 0805088 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 8 miles on I-80 westbound form East of South Beverwyck Road to West | Pavement Improvement | 2009-06-02 | 2009-06-24 | 2010-03-12 | 2010-06-30 | 9081406 | 7.700 | 0805088
7913 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS |  | 11 | 0805090 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and repairing bridge supports for the I-80 EB and WB bridges over Berkshire Valley Road in Roxbury Morris County. | Bridge Improvement | 2009-07-07 | 2009-07-29 | 2010-06-11 | 2012-04-13 | 10752697 | 0.590 | 0805090
7914 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC |  | 08 | 0805091 | This project will paint 5 bridges on Route I-80 in the Counties of Bergen, Essex, Passaic, Warren and Essex. | Pavement Improvement | 2009-09-14 | 2009-11-05 | 2010-12-05 | 2011-07-26 | 8099115 | 0.280 | 0805091
7915 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CUMBERLAND | ATLANTIC CITY | 02 | 1019113 | Cumberland County will repair the concrete joints and concrete sections along the curbs to allow for an asphalt overlay. This will improve driving quality by resurfacing the road, which will make the | New Construction | 2010-03-17 | 2010-03-17 | 2013-09-30 | 2011-01-04 | 650535.7 | 0.480 | 1019113
7916 | NEW JERSEY | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER |  | 04 | 1958056 | This project will replace existing deteriorating pavement with new pavement, upgrade guardrails and improve water drainage on nearly 5 miles on I-195 from the New Jersey Turnpike to just East of Imlay | Pavement Improvement | 2010-04-09 | 2010-04-21 | 2010-11-12 | 2010-10-14 | 10580678 | 7.540 | 1958056
7917 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX |  | 08 | 2806103 | This project will paint 16 bridges on Route I-280 between mile points 12.7 to 14.5 in the Cities of Newark, Orange, East and West Orange, Essex County | Pavement Improvement | 2009-07-28 | 2009-09-21 | 2011-08-15 | 2010-12-31 | 9000754 | 1.720 | 2806103
7918 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX |  | 10 | 2806105 | This project will paint 17 bridges on Route I-280 between mile points 7.5 to 11.1 in the Cities of Newark, Orange, East and West Orange, Essex County | Pavement Improvement | 2009-07-27 | 2009-11-02 | 2011-08-15 | 2011-08-05 | 6822484 | 3.620 | 2806105
7919 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 06 | 2873080 | This project will replace existing deteriorating bridge decks and pavement with new pavement, upgrade guardrails and improve water drainage on nearly 7 miles on I-287 NB and SB in Piscataway, Middlesex County and Franklin, Somerset County. | Pavement Improvement | 2009-09-14 | 2009-09-17 | 2011-11-09 | 2011-05-31 | 35871958 | 7.000 | 2873080
7920 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS |  | 11 | 2873081 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck for the I-287 NB bridge over Route 46 in Parsippany-Troy Hills, Morris County. | Pavement Improvement | 2009-07-10 | 2009-08-03 | 2009-09-30 | 2009-11-23 | 1679926.07 | 0.000 | 2873081
7921 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | SALEM |  | 02 | 2952121 | This project will address the painting needs for 49 bridges on the Route I-295 corridor in Gloucester and Salem Counties. | Pavement Improvement | 2009-08-31 | 2009-10-19 | 2010-09-01 | 2010-06-20 | 1924745 | 0.000 | 2952121
7922 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 2952123 | This project will replace existing deteriorating bridge decks and pavement with new pavement, upgrade guardrails and improve water drainage on nearly 8 miles on I-295 NB and SB in West Deptford, Deptf | Pavement Improvement | 2009-06-29 | 2009-06-29 | 2012-07-20 | 2012-05-22 | 78835000 | 7.900 | 2952123
7923 | NEW JERSEY | Underway | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 2952124 | This project provides the funding for the ROW acquisition to allow for the construction of a new alignment that carries I-295 mainline through the interchange of Route 42 and I-76 in Bellmawr and Mt. Ephriam, Camden and Gloucester Counties. | Other | 2010-05-18 | 2010-05-18 | 2012-03-06 |  | 4807500 | 3.620 | 2952124
7924 | NEW JERSEY | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER |  | 01 | 4001161 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-07-19 | 2010-07-19 | 2012-02-17 |  | 299040 | 0.000 | 4001161
7925 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | TRENTON (PA) | 01 | 4037107 | Gloucester County will resurface the top two and a half inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smooth | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2013-09-30 | 2010-09-27 | 408495 | 0.900 | 4037107
7926 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 4145110 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-04-05 | 2010-05-07 | 2012-02-17 | 2010-12-13 | 290030.36 | 0.000 | 4145110
7927 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 4184101 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-05-17 | 2010-06-16 | 2012-02-17 | 2011-05-15 | 303447 | 0.000 | 4184101
7928 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN |  | 01 | 4187101 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-06-09 | 2010-07-26 | 2013-09-30 | 2011-05-15 | 359234 | 0.000 | 4187101
7929 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON |  | 04 | 4395101 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and repairing bridge supports for the Main St. (CR 543) over Rt. 206 bridge in Townships of Columbus and Manfield, Burlington County. | Pavement Improvement | 2009-08-26 | 2009-10-28 | 2010-11-09 | 2010-08-18 | 1778130 | 0.020 | 4395101
7930 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 12 | 5036109 | Mercer County will improve the safety of three intersections by removing traffic signal poles from the center of the road, pedestrian enhancements, and operation improvements. | Safety/Traffic Management | 2010-11-12 | 2010-12-15 | 2013-09-30 | 2011-06-03 | 421324 | 0.360 | 5036109
7931 | NEW JERSEY | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | 7044101 | This project will resurface 4 miles of roadway and improve water drainage from mile point 0 to mile point 4 on Route 35 in Berkely Township, Seside Heights, Seaside Park and Toms River, Ocean County. | Other | 2009-06-17 | 2009-08-31 | 2010-11-01 | 2012-11-25 | 1491129 | 4.000 | 7044101
7932 | NEW JERSEY | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | 7044102 | This project will resurface 5 miles of roadway and improve water drainage from mile point 4 to mile point 9 on Route 35 in Toms River, Lavallette and Mantoloking, Ocean County. | Other | 2009-05-20 | 2009-05-20 | 2010-10-01 |  | 1498266 | 5.000 | 7044102
7933 | NEW JERSEY | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | 12 | 7207103 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-09-22 | 2010-09-22 | 2013-09-30 |  | 901246 | 0.500 | 7207103
7934 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX |  | 07 | 7269101 | This project will extend the life of the bridge and improve safety replacing the existing deteriorated deck and in the Township of Woodbridge, Middlesex County. | Bridge Improvement | 2009-08-28 | 2009-08-27 | 2010-09-01 | 2010-08-20 | 2949930 | 0.300 | 7269101
7935 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 06 | 7390103 | Union County will replace signal equipment and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicle traffic. | Safety/Traffic Management | 2010-08-17 | 2010-11-08 | 2013-09-30 |  | 565805 | 0.060 | 7390103
7936 | NEW JERSEY | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION |  | Multiple | 7510101 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-04-23 | 2011-06-01 | 2013-09-30 |  | 1015894 | 0.000 | 7510101
7937 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 07 | 7543104 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicle traffic. | Safety/Traffic Management | 2010-06-08 | 2010-06-21 | 2013-09-30 |  | 341694 | 0.300 | 7543104
7938 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | 7675115 | This project will design the work for a new bridge over the Hackensack River in Jersey City and Kearny, Hudson County. | Other | 2009-04-14 | 2009-08-27 | 2010-12-23 |  | 3471845 | 0.300 | 7675115
7939 | NEW JERSEY | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | 7675116 | This project will design the work for the approaches and a new bridge and over the Hackensack River in Jersey City and Kearny, Hudson County. | Other | 2009-08-04 | 2009-08-04 | 2011-03-23 |  | 9716313 | 0.600 | 7675116
7940 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS |  | 11 | 7741139 | This project will design the work to replace the bridge deck of County route 665 (Salem Street) over Route 10 over Randolph, Morris County. | Other | 2009-08-31 | 2009-08-31 | 2011-06-01 | 2011-08-02 | 611284.72 | 0.110 | 7741139
7941 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS |  | 11 | 7789102 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck and is located in the Township of Montville, Morris County. in addition this project will | Bridge Improvement | 2009-07-14 | 2009-07-31 | 2010-04-26 | 2009-12-23 | 1338510 | 0.010 | 7789102
7942 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 09 | 7802160 | This project will replace two bridges at the intersection of Route 46 over Main Street , improve safety and drainage in the Borough of Lodi, Bergen County. | Pavement Improvement | 2009-05-28 | 2009-06-15 | 2012-09-01 | 2012-01-03 | 30817985 | 0.420 | 7802160
7943 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 09 | 7802163 | This project is the utility relocaitons associated with the Route 46 over Main Street in the Borough of Lodi, Bergen County. | Other | 2009-05-28 | 2009-06-18 | 2012-09-01 | 2011-10-30 | 2644220 | 0.420 | 7802163
7944 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON |  | 10 | 7811116 | This project will replace deteriorated pavement with new pavement along 1.5 miles of Route 440 in both northbound and southbound directions from JFK Blvd. to 22nd street. The project is located in the City of Bayonn, Hudson County. | Pavement Improvement | 2009-07-28 | 2009-08-11 | 2009-11-19 | 2010-02-03 | 2904758 | 1.400 | 7811116
7945 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | 7851102 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at mult | Pavement Improvement | 2011-03-22 | 2011-03-22 | 2013-09-30 |  | 3630361 | 0.000 | 7851102
7946 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 09 | 8112137 | This project will extend the life of the bridge and improve safety by replacing the existing deteriorated deck of the Roff Avenue Bridge over Route 46 in Palisades Park, Bergen County. | Bridge Improvement | 2009-08-17 | 2009-11-02 | 2010-11-05 | 2010-08-06 | 2052177 | 0.000 | 8112137
7947 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC |  | 08 | 8112138 | This project will improve safety and extend the life of the Grove Street (CR 623) bridge over Route 46 in Clifton Passaic County, by replacing the existing deteriorated deck, and repairing bridge supports. | Pavement Improvement | 2009-08-26 | 2009-10-14 | 2010-10-20 | 2010-11-12 | 3967255 | 0.100 | 8112138
7948 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 09 | 8112139 | This project is the utility relocaitons associated with the Roff Avenue bridge over Route 46 in Palisades Park, Bergen County. | Other | 2009-08-17 | 2009-11-04 | 2010-11-05 | 2010-08-06 | 261101 | 0.020 | 8112139
7949 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN |  | 05 | 8669101 | This project will extend the life of the bridge and improve safety and drainage by replacing the existing deteriorated deck and repairing bridge supports in Township of Mahwah, Bergen County NJ. | Bridge Improvement | 2009-06-18 | 2009-06-18 | 2009-08-14 | 2009-08-31 | 634674.85 | 0.030 | 8669101
7950 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | A00S961 | This project will improve the park appearance, promote and enhance pedestrian activities, and beautify the landscape. | Other | 2010-05-18 | 2010-05-18 | 2012-02-17 | 2010-06-17 | 111863.16 | 0.000 | A00S961
7951 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | STATEWIDE |  |  | B00S688 | The Statewide project will provide safety enhancement at hazardous highway-rail grade crossings to improve rail road crossing safety, improve visibility of traffic stripes and pavement markings, and i | Safety/Traffic Management | 2010-01-11 | 2010-02-26 | 2011-12-28 | 2011-11-18 | 1197121 | 0.000 | B00S688
7952 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON |  | 13 | B00S719 | This project will improve the walkway appearance, promote and enhance pedestrian activities, and beautify the landscape. | Transportation Enhancements | 2010-01-28 | 2010-01-28 | 2013-09-30 | 2011-02-11 | 1861064.57 | 0.000 | B00S719
7953 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | STATEWIDE |  |  | B00S785 | This project (Contract #10) will provide guiderail down the middle of the roadway on 5.14 miles of Route 18 and 4.64 miles of Route I-95 in the Counties of Mercer, Middlesex, Monmouth. | Safety/Traffic Management | 2009-08-17 | 2009-09-30 | 2010-07-01 | 2010-07-22 | 3337794 | 8.220 | B00S785
7954 | NEW JERSEY | Completed | C240 | Highway Infrastructure Investment Grant | NEW JERSEY | STATEWIDE |  |  | B00S786 | This project (Contract #11) will provide guiderail down the middle of the roadway on 5.14 miles of Route 18 and 4.64 miles of Route I-95 in the Counties of Mercer, Middlesex, Monmouth. | Other | 2009-08-24 | 2009-09-14 | 2010-11-01 | 2010-05-26 | 1203889 | 6.600 | B00S786
7955 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 05 | B00S793 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-20 | 2010-05-21 | 2013-09-30 | 2011-11-29 | 1122024 | 7.790 | B00S793
7956 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S794 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-07-01 | 2010-07-06 | 2013-09-30 | 2011-12-21 | 717055 | 3.760 | B00S794
7957 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S795 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-08-02 | 2010-08-03 | 2013-09-30 |  | 526642 | 3.500 | B00S795
7958 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S796 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-31 | 2010-08-04 | 2013-09-30 |  | 421770 | 1.760 | B00S796
7959 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S797 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-17 | 2010-05-19 | 2013-09-30 | 2011-08-16 | 473998 | 2.030 | B00S797
7960 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S798 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-21 | 2010-05-21 | 2013-09-30 | 2011-12-09 | 679886 | 3.590 | B00S798
7961 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S799 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-06-28 | 2010-06-28 | 2013-09-30 | 2011-09-09 | 559538 | 5.050 | B00S799
7962 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S800 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-06-21 | 2010-07-06 | 2013-09-30 |  | 416506 | 1.370 | B00S800
7963 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S801 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-06-07 | 2011-07-22 | 2013-09-30 | 2011-06-24 | 904327 | 4.640 | B00S801
7964 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S802 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2013-09-30 | 2011-08-23 | 547322 | 3.390 | B00S802
7965 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S803 | Passaic County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother a | Pavement Improvement | 2010-05-19 | 2010-06-17 | 2013-09-30 | 2012-02-21 | 2265243 | 10.300 | B00S803
7966 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S804 | Sussex County will improve safety over Glen Brook by replacing the bridge. | New Bridge Construction | 2010-06-02 | 2010-08-09 | 2013-09-30 | 2010-10-20 | 449510 | 0.050 | B00S804
7967 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S805 | Sussex County will improve safety over the Sparta Glen Brook by replacing the bridge. | Bridge Replacement | 2010-06-08 | 2010-06-11 | 2013-09-30 | 2011-06-14 | 901238 | 0.090 | B00S805
7968 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S806 | Sussex County will extend the service life of the existing pavement and improve safety by providing a new asphalt surface. Additionally, new pavement markings will be installed to aid in night-time driving and old signs will be replaced. | Pavement Improvement | 2010-07-15 | 2010-10-25 | 2012-02-17 | 2010-11-15 | 55800 | 0.930 | B00S806
7969 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S814 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-04-12 | 2010-04-12 | 2012-02-17 | 2010-04-23 | 288685.87 | 1.300 | B00S814
7970 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S815 | Morris County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Other | 2010-04-12 | 2010-04-12 | 2012-02-17 | 2010-04-23 | 382145.76 | 1.730 | B00S815
7971 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | SOMERSET | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S816 | Somerset County will resurface the existing asphalt roadway with new asphalt on multiple County roads. This will improve driving quality by resurfacing the road, which will make the road smoother and | Transportation Enhancements | 2009-10-19 | 2009-10-21 | 2013-09-30 | 2010-11-30 | 4171290 | 15.300 | B00S816
7972 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | Multiple | B00S826 | Gloucester County will upgrade over 100 traffic signals to include new pedestrian signals. These signals will include count down timer displays. Count down timer displays provide additional informat | Other | 2010-05-25 | 2010-06-01 | 2013-09-30 | 2010-12-03 | 852080 | 0.000 | B00S826
7973 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S827 | Hunterdon County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and exten | Pavement Improvement | 2010-06-29 | 2010-06-29 | 2013-09-30 | 2010-08-26 | 1034394.46 | 6.850 | B00S827
7974 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S828 | Hunterdon County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and exten | Pavement Improvement | 2010-06-29 | 2010-07-06 | 2012-02-17 | 2010-10-28 | 1207278.05 | 6.600 | B00S828
7975 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CUMBERLAND | ATLANTIC CITY | 02 | B00S829 | Cumberland County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2013-09-30 | 2010-12-31 | 2350000 | 10.000 | B00S829
7976 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S830 | Ocean County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother and | Pavement Improvement | 2010-03-18 | 2010-02-18 | 2012-02-17 | 2010-07-23 | 2474126.51 | 9.500 | B00S830
7977 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S831 | Ocean County will upgrade the existing end treatments of the guide rails on 82 bridges to extruder end sections. This will bring each bridge with guide rail to current standards and enhances the safety at the bridges. | Safety/Traffic Management | 2010-01-18 | 2010-01-19 | 2012-02-17 | 2010-03-23 | 744896 | 1.000 | B00S831
7978 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S832 | Middlesex County will resurface the existing asphalt roadway with new asphalt on multiple County roadways. This will improve driving quality by resurfacing the road, which will make the road smoother | Pavement Improvement | 2010-06-01 | 2010-06-07 | 2013-09-30 |  | 5570022 | 16.000 | B00S832
7979 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MIDDLESEX | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S833 | Middlesex County will upgrade or install guiderail along many of the County's roadways to prevent vehicles from leaving the roadside and becoming involved in more hazardous collisions which in turn promotes safety. | Safety/Traffic Management | 2010-06-23 | 2010-07-06 | 2013-09-30 |  | 4185748 | 8.300 | B00S833
7980 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S834 | Essex County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at multi | Pavement Improvement | 2010-04-01 | 2010-04-14 | 2013-09-30 | 2011-09-21 | 10134682 | 17.500 | B00S834
7981 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S835 | Morris County will upgrade the intersection to improve traffic flow and increase safety for pedestrians. | Other | 2010-06-04 | 2010-06-28 | 2013-09-30 | 2010-12-15 | 178819 | 0.100 | B00S835
7982 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 11 | B00S836 | Morris County will improve two intersections along Littleton Road to improve traffic flow and increase safety for pedestrians. | Other | 2010-06-14 | 2010-06-28 | 2012-02-17 | 2010-10-25 | 153537 | 0.050 | B00S836
7983 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | TRENTON (PA) | 04 | B00S838 | Mercer County will upgrade the pavement markings to regulate and guide traffic movements which in turn promotes safety. | Transportation Enhancements | 2011-01-30 | 2011-02-15 | 2013-09-30 | 2011-06-03 | 276718 | 0.000 | B00S838
7984 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN | TRENTON (PA) | 01 | B00S839 | Camden County will upgrade guiderail along many of the County's roadways to prevent vehicles from leaving the roadside and becoming involved in more hazardous collisions which in turn promotes safety. | Safety/Traffic Management | 2010-09-15 | 2010-09-27 | 2013-09-30 | 2011-08-15 | 1083401 | 0.000 | B00S839
7985 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | B00S840 | The City of Camden will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at | Safety/Traffic Management | 2010-07-26 | 2010-08-09 | 2013-09-30 | 2011-05-30 | 1681602 | 1.900 | B00S840
7986 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S846 | Monmouth County will resurface the existing asphalt roadway with new asphalt on multiple County roads. This will improve driving quality by resurfacing the road, which will make the road smoother and | Pavement Improvement | 2010-08-25 | 2010-08-30 | 2013-09-30 |  | 4960878 | 19.000 | B00S846
7987 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | 12 | B00S847 | Monmouth County will extend the life of the bridge and improve safety over the Manalapan Brook by reconstructing the bridge, rehabilitating the Millhurst Dam, and re-aligning CR 527. | Bridge Replacement | 2010-10-07 | 2010-10-11 | 2013-09-30 |  | 3261000 | 0.140 | B00S847
7988 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MONMOUTH | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S848 | Monmouth County will upgrade the traffic signal equipment at multiple intersections within the County. The project will benefit vehicular and pedestrian traffic, reduce total vehicle delay, reduce ga | Pavement Improvement | 2010-10-29 | 2010-11-01 | 2013-09-30 |  | 3193298 | 0.000 | B00S848
7989 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | TRENTON (PA) | 12 | B00S849 | This project will replace existing outdated Walk/Don't Walk signals with Manual of Uniform Traffic Control Devices compliant pedestrian indications. These indications will provide users with better i | Transportation Enhancements | 2010-10-22 | 2010-10-25 | 2013-09-30 | 2011-05-15 | 274800 | 0.000 | B00S849
7990 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 04 | B00S850 | Mercer County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at 12 d | Pavement Improvement | 2010-10-22 | 2010-10-25 | 2013-09-30 | 2011-07-29 | 2157900 | 0.000 | B00S850
7991 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S857 | City of Elizabeth will upgrade the intersection traffic signal equipment. The project will benefit vehicular and pedestrian traffic. | Safety/Traffic Management | 2010-08-17 | 2010-09-21 | 2013-09-30 | 2011-08-12 | 696003 | 0.000 | B00S857
7992 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S858 | Bergen County will extend the life of the bridge and improve safety over the Hackensack River by rehabilitating the bridge, reconstructing the approach spans, and upgrading the electrical equipment. | Bridge Improvement | 2010-06-23 | 2010-06-24 | 2013-09-30 | 2012-07-20 | 17788000 | 0.000 | B00S858
7993 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S862 | Hudson County will realign and widen the roadway to accommodate increased traffic and improve safety. | Pavement Widening | 2010-09-01 | 2010-09-03 | 2013-09-30 |  | 500000 | 0.000 | B00S862
7994 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S863 | Hudson County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 2010-07-28 | 2010-08-11 | 2013-09-30 |  | 977034 | 0.000 | B00S863
7995 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 03 | B00S864 | Ocean County will replace the Beach Boulevard Bridge along the existing alignment. | Bridge Replacement | 2010-02-01 | 2010-02-01 | 2013-09-30 | 2010-11-30 | 4658943 | 0.250 | B00S864
7996 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 04 | B00S865 | Ocean County will be preserving its bridge's structural integrity and extend its useful life by re-painting the crossing. | Bridge Improvement | 2010-03-08 | 2010-03-08 | 2012-02-17 | 2010-06-24 | 487726.96 | 0.100 | B00S865
7997 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S870 | Union City will beautify the roadway environment by providing a new driving surface, sidewalks, pedestrian crossings and curb ramps, landscaping, and new pavement markings. | Safety/Traffic Management | 2010-05-17 | 2010-08-16 | 2013-09-30 |  | 912988 | 0.000 | B00S870
7998 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S878 | Hudson County will upgrade 9 traffic signals to include new pedestrian signals. These signals will include count down timer displays. Count down timer displays provide additional information to pede | Safety/Traffic Management | 2010-07-28 | 2010-10-12 | 2013-09-30 | 2011-01-03 | 321932 | 0.000 | B00S878
7999 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S879 | Hudson County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend t | Pavement Improvement | 2010-07-28 | 2010-08-23 | 2013-09-30 |  | 849910 | 0.000 | B00S879
8000 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S890 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life on at mult | Pavement Improvement | 2010-06-02 | 2010-06-29 | 2013-09-30 | 2011-08-11 | 153301 | 0.000 | B00S890
8001 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 13 | B00S895 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Pavement Improvement | 2010-05-03 | 2010-05-10 | 2013-09-30 | 2010-07-23 | 718953 | 0.000 | B00S895
8002 | NEW JERSEY | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | B00S898 | This project will restore and rehabilitate the historic Glassboro Train Station. | Transportation Enhancements | 2012-07-09 | 2012-07-10 | 2013-09-30 | 2013-05-30 | 810834 | 0.000 | B00S898
8003 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER |  | 04 | B00S901 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-07-30 | 2010-08-30 | 2013-09-30 | 2011-05-31 | 994646 | 0.630 | B00S901
8004 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON | TRENTON (PA) | 04 | B00S909 | Burlington County will resurface the top two inches of existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and exte | Pavement Improvement | 2010-07-19 | 2010-07-19 | 2013-09-30 | 2011-07-30 | 2237000 | 11.900 | B00S909
8005 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MORRIS | NEW YORK-NORTHEASTERN NJ (NY) | 05 | B00S914 | Morris County will upgrade four miles of railroad track to improve safety and efficiency. | Other | 2010-05-28 | 2010-06-02 | 2013-09-30 | 2011-05-11 | 5411450 | 0.000 | B00S914
8006 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S915 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicle traffic. | Safety/Traffic Management | 2010-08-17 | 2010-10-25 | 2013-09-30 |  | 366019 | 0.000 | B00S915
8007 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S916 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicle traffic. | Safety/Traffic Management | 2010-08-17 | 2010-10-22 | 2013-09-30 |  | 245100 | 0.400 | B00S916
8008 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S918 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicle traffic. | Safety/Traffic Management | 2010-08-17 | 2010-10-29 | 2013-09-30 |  | 420325 | 0.000 | B00S918
8009 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S933 | Union County will extend the service life of the existing pavement and improve safety by providing a new asphalt surface. Additionally, new pavement markings will be installed to aid in night-time driving and old signs will be replaced. | Pavement Improvement | 2010-06-25 | 2010-06-30 | 2013-09-30 |  | 3745500 | 0.000 | B00S933
8010 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN |  | 05 | B00S936 | This project will promote and enhance pedestrian activities including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-09-08 | 2010-09-24 | 2013-09-30 | 2010-11-10 | 62604 | 0.290 | B00S936
8011 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC | NEW YORK-NORTHEASTERN NJ (NY) | 08 | B00S946 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-05-18 | 2010-06-14 | 2013-09-30 | 2011-11-16 | 221400 | 0.380 | B00S946
8012 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | SUSSEX |  | 11 | B00S949 | This project will improve and beautify appearance, promote and enhance pedestrian activities, and include sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-08-09 | 2010-09-23 | 2013-09-30 | 2011-08-04 | 337121 | 0.260 | B00S949
8013 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN |  | 03 | B00S950 | This project will promote and enhance pedestrian activities including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-10-01 | 2010-10-04 | 2013-09-30 | 2011-06-02 | 444481 | 0.300 | B00S950
8014 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S952 | Hudson County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the roadway life. | Pavement Improvement | 2010-07-20 | 2010-07-22 | 2013-09-30 |  | 516039 | 0.000 | B00S952
8015 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | CUMBERLAND | ATLANTIC CITY | 02 | B00S953 | This project will restore the Bivalve Shipping Sheds. | Transportation Enhancements | 2010-05-24 | 2010-05-25 | 2013-09-30 | 2011-02-08 | 1250000 | 0.000 | B00S953
8016 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | UNION | NEW YORK-NORTHEASTERN NJ (NY) | Multiple | B00S958 | Union County will replace signal equipment, crosswalk striping, and install pedestrian signal heads with countdown timers to improve traffic flow and increase safety of pedestrian, bicycle, and vehicle traffic. | Safety/Traffic Management | 2010-07-18 | 2010-09-22 | 2013-09-30 |  | 1118000 | 0.000 | B00S958
8017 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | SOMERSET | NEW YORK-NORTHEASTERN NJ (NY) | 07 | B00S959 | This project will improve, promote, and enhance pedestrian/bicycle activities. | Transportation Enhancements | 2010-06-08 | 2010-07-19 | 2013-09-30 | 2011-02-08 | 2591113 | 0.540 | B00S959
8018 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 05 | B00S967 | This project will improve the historic train station on Garber Square and Franklin Avenue. | Transportation Enhancements | 2010-09-14 | 2010-09-14 | 2013-09-30 | 2011-04-28 | 376000 | 0.000 | B00S967
8019 | NEW JERSEY | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON |  | 07 | B00S969 | This project will facilitate additional trail corridor through the acquisition of right of way to promote and enhance pedestrian activities. | Transportation Enhancements | 2010-02-18 |  | 2013-09-30 |  | 636000 | 0.000 | B00S969
8020 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | CAMDEN | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | B00S983 | Camden County will upgrade guiderail along many of the County's roadways to prevent vehicles from leaving the roadside and becoming involved in more hazardous collisions which in turn promotes safety. | Safety/Traffic Management | 2010-10-15 | 2010-12-01 | 2013-09-30 | 2011-12-15 | 1158803 | 0.000 | B00S983
8021 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | PASSAIC |  | 08 | B00S984 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-05-19 | 2010-07-06 | 2013-09-30 | 2011-11-16 | 323937 | 0.660 | B00S984
8022 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 09 | B00S986 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-10-22 | 2010-11-23 | 2013-09-30 | 2012-04-03 | 446247 | 0.200 | B00S986
8023 | NEW JERSEY | Underway | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | HUDSON |  | 13 | B00S987 | Construction of the continuation of the Hudson River Waterfront Walkway in Jersey City. | Transportation Enhancements | 2012-03-07 | 2012-03-08 | 2013-09-30 | 2013-03-08 | 2861476 | 0.000 | B00S987
8024 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | BERGEN | NEW YORK-NORTHEASTERN NJ (NY) | 05 | B00S989 | This project will restore and rehabilitate the historic Demarest Railroad Depot. | Transportation Enhancements | 2010-10-26 | 2010-12-02 | 2013-09-30 | 2011-10-03 | 186500 | 0.000 | B00S989
8025 | NEW JERSEY | Completed | C200,C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S990 | City of Newark will resurface the existing asphalt roadway with new asphalt on multiple City roadways. This will improve driving quality by resurfacing the road, which will make the road smoother and | Pavement Improvement | 2010-11-12 | 2010-11-15 | 2013-09-30 | 2011-12-01 | 4199085 | 9.910 | B00S990
8026 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S992 | City of Newark will upgrade the intersection traffic signal equipment. The project will benefit vehicular and pedestrian traffic, reduce total vehicle delay, reduce gasoline consumption, reduce air pollution, and reduce electricity consumption. | Safety/Traffic Management | 2011-03-11 | 2011-03-08 | 2013-09-30 | 2011-09-30 | 329122 | 0.000 | B00S992
8027 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | ESSEX | NEW YORK-NORTHEASTERN NJ (NY) | 10 | B00S993 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2011-02-24 | 2011-03-09 | 2013-09-30 | 2012-09-05 | 1839583 | 0.250 | B00S993
8028 | NEW JERSEY | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | MERCER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 12 | B00S994 | Mercer County will provide accessibility to all users along various roadways within the County by installing curb ramps to meet the American with Disabilities Act regulations. | Safety/Traffic Management | 2010-10-22 | 2010-10-25 | 2012-02-17 | 2011-07-29 | 359500 | 0.000 | B00S994
8029 | NEW JERSEY | Completed | C220 | Highway Infrastructure Investment Grant | NEW JERSEY | WARREN | ALLENTOWN-BETHLEHEM-EASTON (PA) | 05 | B00S995 | This project will improve the street appearance, promote and enhance pedestrian activities, and beautify the landscape, including sidewalk and crosswalk enhancements. | Transportation Enhancements | 2010-06-28 | 2010-07-12 | 2013-09-30 | 2011-05-11 | 868424 | 0.320 | B00S995
8030 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | B00S999 | Gloucester County will resurface the existing asphalt roadway with new asphalt. This will improve driving quality by resurfacing the road, which will make the road smoother and extend the life of the | Pavement Improvement | 2010-09-20 | 2010-09-27 | 2013-09-30 | 2011-05-16 | 890452 | 1.700 | B00S999
8031 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 04 | C00S001 | Burlington County will improve vehicular and pedestrian traffic by upgrading 15 intersections. This work will include replacing the traffic signal equipment, timing and phasing improvements, and link | Safety/Traffic Management | 2010-07-26 | 2010-08-02 | 2013-09-30 | 2011-08-30 | 4368450 | 0.000 | C00S001
8032 | NEW JERSEY | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | C00S014 | Gloucester County will improve safety over Great Egg Harbor River by replacing the bridge. | Bridge Replacement | 2010-09-20 | 2010-09-27 | 2013-09-30 | 2011-03-18 | 1069840 | 0.020 | C00S014
8033 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | BURLINGTON | STATEWIDE | 04 | C00S060 | Delaware River Heritage Trail. | Transportation Enhancements | 2011-07-22 | 2012-03-01 | 2013-09-30 |  | 1385200 | 0.000 | C00S060
8034 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | C00S109 | Resurfacing and various safety improvements. | Pavement Improvement | 2011-04-28 | 2011-05-03 | 2013-09-30 | 2011-06-06 | 900000 | 2.300 | C00S109
8035 | NEW JERSEY | Underway | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | C00S110 | Resurfacing and various safety improvements. | Pavement Improvement | 2011-08-01 | 2011-08-01 | 2013-09-30 |  | 1500000 | 3.500 | C00S110
8036 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | GLOUCESTER | PHILADELPHIA-WILMINGTON(PA-DE-NJ-MD | 01 | C00S111 | Resurfacing and various safety improvements. | Pavement Improvement | 2011-10-10 | 2011-10-17 | 2013-09-30 | 2011-11-08 | 1100000 | 1.300 | C00S111
8037 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | OCEAN | NEW YORK-NORTHEASTERN NJ (NY) | 04 | PLHD001 | Ocean County will improve the intersection to improve traffic flow and increase safety. | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2012-02-17 | 2010-09-21 | 188345.73 | 0.400 | PLHD001
8038 | NEW JERSEY | Completed | C230 | Highway Infrastructure Investment Grant | NEW JERSEY | HUNTERDON | NEW YORK-NORTHEASTERN NJ (NY) | 12 | TCSP004 | Reconstruction of Park Avenue. | Other | 2010-09-27 | 2010-09-27 | 2013-09-30 | 2011-08-05 | 1023000 | 0.000 | TCSP004
8039 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | EDDY |  | 02 | 0062004 | Project consists of construction of two new lanes on US62/180 (northbuond lanes) between White City and Carlsbad to allow for a four lane highway. Project consists of new roadway, shoulders, striping, | Pavement Widening | 2009-04-08 | 2009-04-08 | 2010-10-07 | 2010-08-25 | 14038283.54 | 10.000 | 0062004
8040 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA | LAS CRUCES | 02 | 0102111 | The I-10 six lane project will provide a total of (3) lanes for both east and west bound traffic, the additional lanes will be constructed within NMDOT ROW, this project is 18.3 miles in length, sta | Pavement Widening | 2009-11-30 | 2009-12-23 | 2011-07-13 | 2011-07-11 | 10000000 | 20.400 | 0102111
8041 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | GRANT |  | 02 | 0356005 | The project will include rebuilding and aligning of the curb and gutter, sidewalks, lighting and improvements so that people with disabilities will be able to use the sidewalks. It will, also, includ | Pavement Improvement | 2010-02-02 | 2010-03-08 | 2010-06-16 | 2010-08-12 | 349999.99 |  | 0356005
8042 | NEW MEXICO | Completed | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO | ALBUQUERQUE | 03 | 0403104 | The City of Albuquerque proposes to construct a trail which would connect existing facilities to enhance the multi-modal transportation network | Transportation Enhancements | 2009-10-26 | 2009-10-26 | 2010-07-26 | 2011-01-18 | 4056007.91 |  | 0403104
8043 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 01 | 0403168 | Reconstruction of I-40 and West Central consists of construction of a new overpass over I-25, new on and off ramps, new construction of Paseo Del Volcan and Central Avenue, and re-alignment of Central Avenue and the existing southwest frontage road. | Pavement Widening | 2009-04-28 | 2009-04-28 | 2010-10-24 | 2010-06-10 | 14800000 | 1.000 | 0403168
8044 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | 0511097 | This project will reconstruction the four lanes of US 84/285 from Arroyo Seco to La Puebla and adds a two-way frontage road on both sides of the highway. | Pavement Widening | 2009-05-27 | 2009-05-27 | 2010-10-10 | 2010-10-27 | 13400652.8 | 2.900 | 0511097
8045 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | 0511098 | This project will reconstruct the four lanes of US 84/285 highway and adds medians from Dandy Burger South to the Dreamcatcher Theater. It will also add a new traffic signal at the Upper San Pedro intersection. | Pavement Improvement | 2009-04-08 | 2009-04-08 | 2010-06-15 | 2010-08-25 | 8507094.26 | 1.500 | 0511098
8046 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | 0649036 | This project will construct 2 new lanes on US64/87 from Des Moines to Capulin, converting this portion of US64/87 to a 4-lane facility. This is Phase Vi of a seven Phase project to widen US64/87 to 4-lanes from Raton to Clayton. | New Construction | 2009-08-12 | 2009-08-12 | 2011-01-26 | 2011-09-22 | 25662731.53 | 16.000 | 0649036
8047 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | OTERO |  | 02 | 0821026 | Structural evaluation, preservation of sound timbers and replacement of decayed/missing timbers. | Transportation Enhancements | 2009-08-26 | 2009-08-26 | 2009-09-29 | 2009-09-29 | 249747 |  | 0821026
8048 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | 1271015 | Project consists of total reconstruction of a 14.4 mile segment of NM128 between Carlsbad and Jal on an offset new alignment. Project will consist of new roadway, shoulders, striping, permanent signing, intersection improvements and new fence. | Pavement Improvement | 2009-04-13 | 2009-04-13 | 2010-05-19 | 2010-05-13 | 8076093.46 | 14.110 | 1271015
8049 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | LINCOLN |  | 02 | 3801206 | Bridge Replacement of the Priest Gulch Bridge on US380 at Milepost 96.3 in the Lincoln Historic District In Lincoln County approximately 60 miles west of Roswell | Pavement Improvement | 2010-03-16 | 2010-04-05 | 2010-10-08 | 2010-12-15 | 1175028.91 |  | 3801206
8050 | NEW MEXICO | Underway | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL | ALBUQUERQUE | 03 | 4007003 | This project will complete Stage II of the Paseo Del Volcan corridor within the city of Rio Rancho. The project will consist of a new 2-lane facility including lighting, bridges, and various drainage structures within the project termini. | Pavement Widening | 2009-08-06 | 2009-08-10 | 2011-02-11 |  | 14000000 |  | 4007003
8051 | NEW MEXICO | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | 4911011 | This project will provide two new traveling lanes to make the US 491 roadway a four lane facility. This is one segment of 9 segments to four lane US 491 from MP 15.7 to MP 84.7. | New Construction | 2009-06-30 | 2009-06-30 | 2010-05-04 |  | 21624989 | 8.000 | 4911011
8052 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | 4911031 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. Project will also provide intersection improvements for better turning movements in Tohatchi, New Mexico. | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2010-03-04 | 2010-07-09 | 7904666.11 | 13.900 | 4911031
8053 | NEW MEXICO | Completed | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL | ALBUQUERQUE | 03 | 5119001 | Reconstruct 2 lanes & add/improve sidewalks. Add center double left turn lanes & add deceleration lane for new school bus access. | Pavement Improvement | 2010-01-11 | 2010-01-25 | 2010-07-24 | 2010-06-25 | 1852573.23 |  | 5119001
8054 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | RIO ARRIBA |  | 03 | 5348002 | To construct road improvements to Industrial Park Road for its entire length of 1.1 miles in Espanola that includes added lanes, drainage improvements, pedestrian facilities, utilities, curb and gutter and access management. | Pavement Improvement | 2009-10-07 | 2009-10-07 | 2010-06-16 | 2010-07-07 | 1250000 |  | 5348002
8055 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | GRANT |  | 02 | 7517010 | This project will consist of improving (paving) the roadway on Diaz Avenue from Cul de Sac North to E. Street. In addition, it will include inspection and oversight. | Pavement Improvement | 2010-02-16 | 2010-03-01 | 2010-08-29 | 2010-09-24 | 390000 |  | 7517010
8056 | NEW MEXICO | Underway | C220,C200,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES02107 | The work to be completed on this project will rehabilitate & reconstruct a highly deteriorated roadway to include; pavement, curb, gutter, sidewalks, storm drain systems, roadway lighting & traffic signal improvements. | Pavement Improvement | 2011-03-16 | 2011-04-01 | 2012-02-20 |  | 1280406.61 |  | ES02107
8057 | NEW MEXICO | Underway | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO | ALBUQUERQUE | 01 | ES03184 | "The City of Albuquerque proposes to expand its Advanced Transportation Management System with the installation of the communication infrastructure for the following corridors: 1) Alameda Blvd. from | Safety/Traffic Management | 2009-12-09 | 2010-01-11 | 2010-07-10 |  | 2651176 |  | ES03184
8058 | NEW MEXICO | Underway | C250,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SOCORRO |  | 02 | ES03966 | Interstate 25 Bridge/Roadway Reconstruction; The purpose of the project is to replace bridge superstructure components and decks that are showing signs of wear. Currently, the existing bridges that | Pavement Improvement | 2011-01-13 | 2011-02-03 | 2011-10-26 |  | 898393.76 |  | ES03966
8059 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | ROOSEVELT |  | 02 | ES04049 | Enhancements such as; Bushes, Trees Sidewalks & ADA Ramps | Transportation Enhancements | 2010-04-05 | 2010-04-06 | 2010-07-06 | 2010-05-27 | 236588.86 |  | ES04049
8060 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | LUNA |  | 02 | ES11140 | Installation of a left turning lane | Pavement Widening | 2010-02-15 | 2010-04-05 | 2010-08-02 | 2010-06-10 | 143503.76 |  | ES11140
8061 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SIERRA |  | 02 | ES11150 | Landscaping, pedestrian facilities, & base course. | Transportation Enhancements | 2010-02-15 | 2010-02-15 | 2010-04-08 | 2010-04-15 | 87252.98 |  | ES11150
8062 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11160 | Installation of landscaping materials and erosion control measures | Transportation Enhancements | 2010-02-17 | 2010-03-10 | 2010-05-19 | 2010-07-08 | 178881.23 |  | ES11160
8063 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11170 | Construct eight bus shelters | Transportation Enhancements | 2010-02-09 | 2010-03-01 | 2010-04-14 | 2010-07-21 | 71000 |  | ES11170
8064 | NEW MEXICO | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11180 | Project will consist of milling & removing 2.5" of old asphalt on driving & passing lanes and replace with 2.5" Hot Mix Asphalt, Open Graded Friction Course and fog seal shoulders. | Pavement Improvement | 2010-03-09 | 2010-03-18 | 2010-06-11 |  | 3188866.13 |  | ES11180
8065 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | HIDALGO |  | 02 | ES11200 | This project will include making roadway improvements to NM 494 from mile post 0 to mile post 1.7. Existing old pavement will be removed and replaced with new pavement. Sidewalks, curb and gutter, d | Pavement Improvement | 2010-02-04 | 2010-02-16 | 2010-04-27 | 2010-05-24 | 400000 |  | ES11200
8066 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11210 | This project will include roadway improvements by adding more pavement on top of the existing pavement on Calle del Norte from NM 28 to Tres Sendas. In addition, it will include inspection and oversight. | Pavement Improvement | 2010-02-23 | 2010-03-15 | 2010-04-30 | 2010-06-09 | 500000 |  | ES11210
8067 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LUNA |  | 02 | ES11220 | Reconstruction to include pedestrian facilities | Pavement Improvement | 2009-12-22 | 2010-01-03 | 2010-11-08 | 2011-03-24 | 850000 |  | ES11220
8068 | NEW MEXICO | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES11230 | Sidewalks, curb & gutter, drainage structures, storm drains, bike lanes & pedestrian facilities. | Pavement Improvement | 2010-02-10 | 2010-03-15 | 2010-11-30 |  | 2000000 |  | ES11230
8069 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | GRANT |  | 02 | ES11240 | This project will include grinding down existing old pavement and replacing with new pavement on 12th Street from Gold Street to Mississippi Street. In addition, it will include inspection and oversi | Pavement Improvement | 2010-02-02 | 2010-02-03 | 2010-05-03 | 2010-08-26 | 503315.66 |  | ES11240
8070 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SOCORRO |  | 02 | ES11250 | This project will include inspection and oversight of pavement rehabilitation and maintenance, grinding down existing asphalt and replacing with new material on California Street from mile post 0 to mile post 4.0. | Pavement Improvement | 2010-04-01 | 2010-04-01 | 2010-11-26 | 2010-09-21 | 618952.71 |  | ES11250
8071 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SIERRA |  | 02 | ES11260 | This project will include new pavement on the I-25 Business Loop (Old US 85) from Ashbaugh at mile post 0 to Morgan at mile post 3.9. Construction will include management and pedestrian facilities. | Pavement Improvement | 2010-02-22 | 2010-03-01 | 2010-07-28 | 2010-06-30 | 580402.2 |  | ES11260
8072 | NEW MEXICO | Completed | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA | EL PASO, TX-NM | 02 | ES11270 | Project will improve the roadway surface on NM 213 which is a heavily traveled route between El Paso, Chaparral, White Sands Missile Range, and Jct. NM 404 to Interstate 10 and Anthony, NM | Pavement Improvement | 2010-02-25 | 2010-03-10 | 2010-04-21 | 2010-03-18 | 910093.51 |  | ES11270
8073 | NEW MEXICO | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | HIDALGO |  | 02 | ES11400 | This seven mile maintenance project includes removing 2 inches of the existing pavement and replacing it with new pavement. The purpose of this project is to improve the quality of the roadway surface | Pavement Improvement | 2010-04-06 | 2010-06-01 | 2010-08-03 |  | 1832326.25 |  | ES11400
8074 | NEW MEXICO | Underway | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA | EL PASO, TX-NM | 02 | ES11420 | Work on the project will include placing a hot mix asphalt overlay on an existing roadway with tapered edges to create a smooth transition surface from the roadway onto the shoulders. It also include | Pavement Improvement | 2011-01-13 | 2011-02-03 | 2011-03-31 |  | 124520.66 |  | ES11420
8075 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21070 | This project will include downtown beautification consisting of new pavement, lighting, crosswalks, sidewalks, curb and gutter and landscaping on NM 176 from mile post 34.9 to milepost 35.4 and on NM 248 from milepost 0 to milepost 0.5. | Transportation Enhancements | 2010-02-05 | 2010-02-08 | 2010-06-27 | 2010-08-30 | 249747 |  | ES21070
8076 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | OTERO |  | 02 | ES21190 | This project will include the removal of an old bridge and construction of a new bridge to replace the old bridge on 9th Street and Washington Street. | Pavement Improvement | 2010-01-13 | 2010-01-19 | 2010-03-10 | 2010-03-31 | 139291.52 |  | ES21190
8077 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CHAVES |  | 02 | ES21200 | This project will include grinding down old pavement and replacing with new pavement along an existing paved road. The project is located on West Brasher Road from the entrance of the City’s municipal land fill to the intersection of South Sunset Avenue. | Pavement Improvement | 2010-02-19 | 2010-03-15 | 2010-06-04 | 2010-07-01 | 831489 |  | ES21200
8078 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21210 | This project includes new pavement on Ninth Street from Avenue D to Polk Avenue. | Pavement Improvement | 2010-01-18 | 2010-01-19 | 2010-08-19 | 2010-04-22 | 559365.66 |  | ES21210
8079 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21220 | Mill, check sub-base, relay and add 4 inches of asphalt. | Pavement Improvement | 2010-03-16 | 2010-03-29 | 2010-06-27 | 2010-08-19 | 789914.56 |  | ES21220
8080 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21230 | 10 feet wide concrete multi-use trail with landscape, pedestrian lighting and americans with disabilites act intersection improvements | Transportation Enhancements | 2010-02-08 | 2010-02-15 | 2010-03-26 | 2010-03-31 | 249747 |  | ES21230
8081 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LINCOLN |  | 02 | ES21240 | This project will consist of new pavement on Paradise Canyon from Suddeth Drive to Country Club Drive. | Pavement Improvement | 2010-04-28 | 2010-05-03 | 2010-06-02 | 2010-05-12 | 295523.78 |  | ES21240
8082 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CHAVES |  | 02 | ES21250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-03-22 | 2010-03-29 | 2010-05-28 | 2010-04-28 | 813504.77 |  | ES21250
8083 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | EDDY |  | 02 | ES21260 | This project will include new pavement on Greene Street from Canal to Moore Drive. | Pavement Improvement | 2010-02-18 | 2010-03-03 | 2010-07-21 | 2010-07-15 | 831489 |  | ES21260
8084 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | OTERO |  | 02 | ES21270 | This project will include the construction of accessible sidewalks and ramps, and driveways for people with disabilities on 1st Street from White Sands to Florida and 10th Street from Cuba to College. | Transportation Enhancements | 2010-02-02 | 2010-05-09 | 2010-02-08 | 2010-06-18 | 196509.23 |  | ES21270
8085 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 03 | ES21280 | Bridge replacement on Hull Street spanning over Burlington Northern Santa Fe Railroad | Bridge Replacement | 2009-11-24 | 2010-01-04 | 2010-10-31 | 2010-11-19 | 831489 | 0.300 | ES21280
8086 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 03 | ES21300 | Project consists of landscaping at the intersection of US60/70/84 intersection at the New Mexico/Texas State Line in the Town of Texico in Curry County. Project will include trees, shrubs, flowers, Am | Transportation Enhancements | 2010-04-20 | 2010-05-05 | 2010-07-30 | 2010-07-27 | 293709.22 | 1.000 | ES21300
8087 | NEW MEXICO | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 02 | ES21310 | Project will rehabilitate a section of NM 209 between Broadview and Grady in Curry County. Project consists of milling full width the existing roadway and a Hot mix asphalt overlay. | Pavement Improvement | 2010-04-28 | 2010-05-20 | 2010-08-12 | 2010-11-22 | 1655443.03 | 6.000 | ES21310
8088 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LEA |  | 02 | ES21320 | Pavement reconstruction including milling excavation, subgrade base course, asphalt treated base, hot-mix asphalt and minor concrete. | Pavement Improvement | 2010-01-15 | 2010-01-25 | 2010-07-24 | 2010-10-29 | 831489 | 1.000 | ES21320
8089 | NEW MEXICO | Completed | C250,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | ROOSEVELT |  | 03 | ES21330 | Project consists of rehabilitating a four-mile section of NM 88 east of the City of Portales in Roosevelt County. The typical section will be process, placed and compacted and then overlayed with a 2.5 inch Hot Mix Asphalt Overlay. | Pavement Improvement | 2010-04-01 | 2010-04-23 | 2010-09-10 | 2010-06-28 | 1504718.88 | 5.400 | ES21330
8090 | NEW MEXICO | Underway | C220,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | DONA ANA |  | 02 | ES21350 | This project will consist of improving the road pavement and drainage on East Berino Road from NM 478 to Stern Drive. It will, also, include curb and gutter, sidewalks, storm drainage installation an | Pavement Improvement | 2010-04-26 | 2010-05-10 | 2011-02-03 |  | 2168207 |  | ES21350
8091 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 03 | ES21360 | Project will consist of full lane width milling and removal of the existing pavement and replacing full width Hot Mix Asphalt overlay south of Portales in Roosevelt County. | Pavement Improvement | 2010-02-05 | 2010-02-25 | 2010-06-18 | 2010-07-14 | 4242583.9 |  | ES21360
8092 | NEW MEXICO | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | CURRY |  | 02 | ES21420 | The project will include grinding the existing pavement, putting it back in place and compacting it. Then the existing roadway will receive a new asphalt pavement overlay. | Pavement Improvement | 2010-03-15 | 2010-04-04 | 2010-06-25 | 2010-07-15 | 2354145.7 |  | ES21420
8093 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | EDDY |  | 02 | ES21560 | The project consists of approximately one (1) mile of Project Pavement Reconstruction of deteriorated roadway on 26th Street in Artesia which begins at junction of NM 82 and 26th Street and proceeds n | Pavement Improvement | 2011-01-17 | 2011-01-17 | 2011-07-16 | 2011-05-28 | 831488.51 |  | ES21560
8094 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 02 | ES31110 | The Village of Bosque Farms proposes to enhance 21 side street accesses onto Bosque Loop Road by providing road improvements by re-aligning, resurfacing with Hot mix Asphalt , and constructing a secti | Pavement Improvement | 2010-04-28 | 2010-05-03 | 2010-06-18 | 2010-06-03 | 63000 |  | ES31110
8095 | NEW MEXICO | Underway | C220,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 01 | ES31120 | This project is a joint effort between the City of Belen and The Mid Region Council of Governments. The project will provide Pedestrian Access to the Rail Runner Station by constructing an Americans | Transportation Enhancements | 2010-06-16 | 2010-06-21 | 2011-01-14 |  | 2410012.2 | 14.000 | ES31120
8096 | NEW MEXICO | Underway | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 03 | ES31130 | This project will improve safety for motorists by resurfacing with Hot Mix Asphalt, widening travel lanes, providing acceleration/deceleration lanes, providing lighting and improving access to busine | Pavement Improvement | 2010-07-08 | 2010-07-23 | 2011-03-27 |  | 2000000 |  | ES31130
8097 | NEW MEXICO | Underway | C250,C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 03 | ES31140 | This project will improve safety for motorists within the limits of Cochiti Pueblo by resurfacing with Hot Mix Asphalt, providing roadside safety enhancements, constructing an offset multi-use trail w | Pavement Improvement | 2010-07-08 | 2010-07-23 | 2010-09-03 |  | 1500000 |  | ES31140
8098 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 03 | ES31150 | This project will provide a new signalized/lighted intersection for the Pueblo of Isleta’s Service Center. The Service Center is the Pueblo’s main housing of emergency personnel and other support staff. | Pavement Improvement | 2010-07-15 | 2010-08-06 | 2011-01-23 | 2010-12-10 | 878722 |  | ES31150
8099 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 01 | ES31160 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-04-06 | 2010-04-05 | 2010-06-04 | 2010-06-16 | 4915479.95 |  | ES31160
8100 | NEW MEXICO | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 02 | ES31200 | This project will mill a portion of the surfacing, and overlay with new pavement, for a distance of 4 miles. New signing and striping will be installed. NM 6 is a rural two lane highway | Pavement Improvement | 2010-12-14 | 2010-12-31 | 2011-02-14 |  | 849986.29 |  | ES31200
8101 | NEW MEXICO | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 03 | ES31210 | This project will mill a portion of the surfacing, and overlay with new pavement, for a distance of 5 miles. New signing and striping will be installed. NM 16 is a 2 lane rural highway. | Pavement Improvement | 2010-12-14 | 2010-12-31 | 2011-02-14 |  | 813721.88 |  | ES31210
8102 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | ES41170 | The project will provide parking capacity, land and street scaping that will promote the heritage and tourism benefits along US 64 for approximately 1/2 mile. | Transportation Enhancements | 2010-06-29 | 2010-06-29 | 2010-08-27 | 2010-08-04 | 125000 |  | ES41170
8103 | NEW MEXICO | Underway | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN MIGUEL |  | 03 | ES41180 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Transportation Enhancements | 2010-10-19 | 2010-10-25 | 2011-05-31 |  | 937015 |  | ES41180
8104 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | ES41190 | The project will upgrade signing, striping, curb and gutter, sidewalk, drainage structures, and pavement that will enhance safety and improve existing pavement. | Pavement Improvement | 2010-06-02 | 2010-06-21 | 2010-09-21 | 2010-10-05 | 762000 |  | ES41190
8105 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | GUADALUPE |  | 01 | ES41200 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 2010-09-29 | 2010-10-11 | 2011-11-09 | 2011-02-18 | 312355.26 |  | ES41200
8106 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN MIGUEL |  | 03 | ES41210 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-08-13 | 2010-08-13 | 1944135.31 |  | ES41210
8107 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | ES41220 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 2010-07-07 | 2010-07-22 | 2010-09-22 | 2010-09-22 | 763077.01 |  | ES41220
8108 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | COLFAX |  | 03 | ES41230 | The project is pavement rehabilitation, signing and striping that will improve existing roadway features and extend the life of the pavement. | Pavement Improvement | 2010-09-20 | 2010-09-21 | 2010-11-21 | 2010-10-29 | 600000 |  | ES41230
8109 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | QUAY |  | 03 | ES41240 | The project will upgrade signing, striping, curb and gutter, sidewalk, drainage structures, and pavement that will enhance safety and improve existing pavement. | Pavement Improvement | 2010-03-08 | 2010-03-08 | 2010-08-23 | 2010-10-03 | 1785000 |  | ES41240
8110 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | UNION |  | 03 | ES41250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-02-04 | 2010-02-25 | 2010-05-21 | 2010-09-25 | 3387428.67 |  | ES41250
8111 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | GUADALUPE |  | 01 | ES41360 | This project will crack seal 28.5 miles of Interstate 40 in Quay County, 30.7 miles of US 54 in Quay County, and 5.6 miles of US 84 in Guadalupe County | Pavement Improvement | 2010-03-15 | 2010-04-05 | 2010-06-25 | 2010-06-08 | 1211432.17 |  | ES41360
8112 | NEW MEXICO | Underway | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | GUADALUPE |  | 01 | ES41370 | Project will include the rehabilitation with spot reconstruction of I-40 from MP 248.3 to MP 255.3. Work will include: milling of existing roadway full-width; Full depth and partial depth reconstruct | Pavement Improvement | 2010-11-08 | 2010-11-24 | 2010-03-18 |  | 2231007 |  | ES41370
8113 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | LOS ALAMOS |  | 03 | ES51140 | Rehabilitate & reconstruct highly deteriorated roadway to include; pavement, curb, gutter, sidewalks, storm drain systems & roadway lighting. | Pavement Widening | 2009-04-29 | 2009-05-11 | 2010-03-01 | 2009-11-06 | 1901033.83 |  | ES51140
8114 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | ES51260 | The New Mexico Department of Transportation will resurface the top three inches of existing asphalt in the southbound driving lanes of US 491 with 3” of new Hot Mix Asphalt. This will improve driving | Pavement Improvement | 2010-02-04 | 2010-02-25 | 2010-10-01 | 2010-10-18 | 3373157.8 |  | ES51260
8115 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | TORRANCE |  | 01 | ES51270 | Repair cracks in pavement and repave roadway | Pavement Improvement | 2010-03-02 | 2010-03-25 | 2010-10-01 | 2010-10-01 | 1720849.16 |  | ES51270
8116 | NEW MEXICO | Underway | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | CATRON |  | 02 | ES61150 | This project will beautify the downtown area of the Village of Reserve and will also install a needed drainage system. | Transportation Enhancements | 2010-07-14 | 2010-07-26 | 2010-12-22 |  | 1033609 |  | ES61150
8117 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 01 | ES61160 | This project will replace the existing old bridge with a new prefabricated bridge. | Bridge Improvement | 2010-03-11 | 2010-03-11 | 2010-05-31 | 2010-05-28 | 166645.61 |  | ES61160
8118 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 03 | ES61170 | This project will replace the existing old bridge with a new prefabricated bridge. | Bridge Improvement | 2010-03-11 | 2010-03-11 | 2010-05-31 | 2010-07-02 | 180288.37 |  | ES61170
8119 | NEW MEXICO | Underway | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61180 | This project will widen an existing bridge on a Zuni Reservation route near the city of Zuni, New Mexico. | Bridge Improvement | 2010-07-12 | 2010-07-12 | 2011-01-08 |  | 736582 |  | ES61180
8120 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61190 | This project will replace the existing old bridge with a new concrete bridge. | Pavement Widening | 2010-03-19 | 2010-03-29 | 2010-11-29 | 2010-10-18 | 1636194.71 |  | ES61190
8121 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | CIBOLA |  | 02 | ES61200 | This project will replace the existing old bridge with a new concrete bridge. | Bridge Replacement | 2009-12-28 | 2010-01-04 | 2010-05-04 | 2010-09-30 | 760516.18 |  | ES61200
8122 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 02 | ES61250 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-01-13 | 2010-02-03 | 2010-04-04 | 2010-07-17 | 3967200.35 |  | ES61250
8123 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61260 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. | Pavement Improvement | 2010-03-16 | 2010-04-05 | 2010-06-25 | 2010-08-18 | 1811053.07 |  | ES61260
8124 | NEW MEXICO | Completed | C250 | Highway Infrastructure Investment Grant | NEW MEXICO | CIBOLA |  | 02 | ES61320 | This project will remove the existing asphalt paved section and replace it with a new asphalt overlay. | New Construction | 2010-06-30 | 2010-07-19 | 2010-10-26 | 2010-09-01 | 1199999.88 |  | ES61320
8125 | NEW MEXICO | Completed | C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61330 | This project will replace the existing old bridge with a new concrete bridge. | Bridge Replacement | 2010-04-06 | 2010-04-23 | 2010-09-10 | 2010-11-04 | 1717198.73 |  | ES61330
8126 | NEW MEXICO | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 03 | ES61340 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. This project is located in on NM 264 in McKinley County from mile post 13.1 to 14.6. | Pavement Improvement | 2010-12-02 | 2010-12-02 | 2011-01-18 | 2011-12-14 | 1478092.98 |  | ES61340
8127 | NEW MEXICO | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW MEXICO | MCKINLEY |  | 02 | ES61350 | This project will mill out the existing pavement section and will replace the milled portion of the roadway with a new asphalt overlay. This project is located in on NM 118 in McKinley County from mile post 23.5 to 24.5. | Pavement Improvement | 2010-12-22 | 2010-12-31 | 2011-02-25 | 2011-10-24 | 1441783.42 |  | ES61350
8128 | NEW MEXICO | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | VALENCIA |  | 03 | ESA3310 | Construction of an asphalt multiuse asphalt trail on the East frontage of NM 314 to connect the Rail Runner Station with NM 6. The project also involves the construction of a Bike/Pedestrian RR crossi | Transportation Enhancements | 2010-09-19 | 2010-10-04 | 2011-03-04 |  | 1092715 |  | ESA3310
8129 | NEW MEXICO | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 03 | ESA3312 | Intersection Pedestrian Improvements to Court house Road, including the construction of new ramps, new pedestrian push button stations, enhanced crosswalk markings. It also includes a concrete walkwa | Transportation Enhancements | 2010-09-20 | 2010-09-27 | 2010-03-25 |  | 698446.76 |  | ESA3312
8130 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL |  | 01 | ESA3320 | The purpose of the project will consist of the installation of lighting between the Southern Boulevard intersection and US 550 within the City of Rio Rancho and the town of Bernalillo. The lighting w | Transportation Enhancements | 2010-03-15 | 2010-03-25 | 2010-06-18 | 2010-09-08 | 846422.86 |  | ESA3320
8131 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 01 | ESA3330 | The project will consist of the repaving of the Multi use trail from Central to Montgomery. The project will also consist of various improvements from Central to Tramway Terrace which include the upgr | Transportation Enhancements | 2010-04-20 | 2010-05-05 | 2010-08-19 | 2010-12-23 | 770784.35 |  | ESA3330
8132 | NEW MEXICO | Underway | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO |  | 01 | ESA3331 | This project will reconstruct and improve sections of an existing Bike/Pedestrian Trail within the City of Albuquerque. The safety of the trail will be improved by widening the rail to 12’, building r | Transportation Enhancements | 2011-01-18 | 2011-02-03 | 2011-07-17 |  | 482984.43 |  | ESA3331
8133 | NEW MEXICO | Completed | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | BERNALILLO | ALBUQUERQUE | 01 | ESA3550 | This project will reconstruct the existing Bike/Pedestrian Trail along the Rio Grande within the City of Albuquerque. The improvements involve the removal and replacement of the existing pavement, on | Transportation Enhancements | 2011-01-06 | 2011-01-10 | 2011-03-25 | 2011-07-06 | 920283.28 |  | ESA3550
8134 | NEW MEXICO | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | ESF1050 | The City of Aztec is developing an East Arterial to alleviate heavy truck traffic through it's Main Street (US 550). The arterial will intersect at the south end of town and will traverse east and the | Pavement Improvement | 2010-04-05 | 2010-04-05 | 2010-10-02 |  | 1700000 |  | ESF1050
8135 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | ESF1070 | This project is a widening and intersection improvements for Wildflower Parkway from Browning Parkway to Yarrow Street in Farmington that includes bike paths, new sidewalks and turning lanes. | Transportation Enhancements | 2010-03-25 | 2010-04-12 | 2010-09-09 | 2010-11-30 | 1347265.7 |  | ESF1070
8136 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | ESF1080 | For reconstruction of West Maple Street in Bloomfield to include removal of existing pavement, adding curb and gutter, lighting, sidewalk, new asphalt, and removal and replacement of utilities from US 550 to South Church Street. | Pavement Improvement | 2010-04-28 | 2010-05-10 | 2010-10-16 | 2010-12-15 | 900000 |  | ESF1080
8137 | NEW MEXICO | Underway | C230 | Highway Infrastructure Investment Grant | NEW MEXICO | SANDOVAL | ALBUQUERQUE | 01 | ESL3311 | This project will resurface and reconstruct the multi-use trail along Camino Don Tomas Road in the Town of Bernalillo. Also it will relocate and provide a water system to include irrigation lines to t | Pavement Improvement | 2012-01-23 | 2012-01-30 | 2012-04-30 |  | 1062005.77 |  | ESL3311
8138 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | ESS1010 | This project will provide landscaping of all medians on Rodeo Road from Galisteo Street to Camino Carlos Rey. | Transportation Enhancements | 2009-09-22 | 2009-09-22 | 2009-11-30 | 2010-06-11 | 132313.01 |  | ESS1010
8139 | NEW MEXICO | Completed | C220 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | ESS1020 | This project will pave a small portion of the Santa Fe Rail Trail in Santa Fe County from Interstate Highway 25 southerly to Rabbit Road. | Transportation Enhancements | 2010-04-07 | 2010-04-07 | 2010-08-13 | 2010-05-04 | 67159.58 |  | ESS1020
8140 | NEW MEXICO | Underway | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SANTA FE |  | 03 | ESS1030 | This project will involve cold milling the existing pavement on Airport Road from Cerrillos Road to Calle Debra, inlaying a new pavement, sidewalk and Americans with Disabilities Act ramp improvements and traffic signal system improvements. | Pavement Improvement | 2010-05-21 | 2010-06-01 | 2010-10-30 |  | 2222022.33 |  | ESS1030
8141 | NEW MEXICO | Completed | C200 | Highway Infrastructure Investment Grant | NEW MEXICO | SAN JUAN |  | 03 | F100030 | A complete bridge replacement for Bridge #8116 located on San Juan County Road 2900 at mile marker 6.20 situated between the City of Aztec and the community of Cedar Hill. | Bridge Replacement | 2010-04-05 | 2010-04-05 | 2010-08-05 | 2010-12-15 | 903955.02 |  | F100030
8142 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0016263 | Completely renovating 3.5 miles of New York Route 112 in Brookhaven, Suffolk County to improve the safety for the approximately 20,000 motorists, pedestrians and bicyclists who use the roadway daily. The project includes new plantings and storm-water runo | Pavement Improvement | 2009-08-06 | 2009-08-06 | 2011-11-10 | 2011-12-23 | 40151314 | 3.000 | 0016263
8143 | NEW YORK | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0757523 | A project to construct the ferry terminal bulkhead and make site improvements at the Glen Cove Ferry Terminal in the City of Glen Cove, Town of North Hempstead, Nassau County. | Other | 2010-04-26 | 2010-04-26 | 2011-05-02 |  | 10743372 | 0.000 | 0757523
8144 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 02 | 0758463 | Provide new bike lanes and improved pedestrian facilities, including new sidewalks and crosswalks, on Prospect Avenue between Brush Hollow Road and Cantiague Rock Road in New Cassel, in the Town of North Hempstead, Nassau County. | Safety/Traffic Management | 2009-11-17 | 2009-11-17 | 2011-12-23 | 2011-12-23 | 5000000 | 0.000 | 0758463
8145 | NEW YORK | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 02 | 0758583 | Reconstruct Walt Whitman Road in the Town of Huntington | Pavement Improvement | 2010-01-01 | 2010-01-01 | 2010-11-04 |  | 5409198 | 0.000 | 0758583
8146 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759353 | Further expand Nassau County central computerized traffic signal system. | Safety/Traffic Management | 2011-03-21 | 2011-03-21 | 2012-03-01 |  | 2609826 | 0.000 | 0759353
8147 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759373 | A project to clean, paint, and thereby preserve the integrity of four bridges accessing Hempstead Lake Park in the Village of Rockville Centre, Nassau County. | Bridge Improvement | 2010-03-31 | 2010-03-31 | 2011-04-22 | 2011-04-22 | 3068016 | 0.000 | 0759373
8148 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | 03 | 0759383 | A project to provide safety, pavement and drainage improvements on Cedar Swamp Road in Glen Cove, Town of North Hempstead, Nassau County. | Pavement Improvement | 2010-03-26 | 2010-03-26 | 2012-01-27 | 2012-01-27 | 3194991.31 | 0.000 | 0759383
8149 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759393 | Resurface select local roads in Nassau County. The existing deteriorated pavement surface will be removed and replaced with new asphalt and pavement markings. | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-06-08 | 2010-04-19 | 3247150 | 0.000 | 0759393
8150 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759403 | Resurface select local roads in Nassau County. The existing deteriorated pavement surface will be removed and replaced with new asphalt and pavement markings. | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-06-08 | 2010-04-19 | 3156305 | 0.000 | 0759403
8151 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759413 | A project to construct a seven-mile shared-use bike path in Mitchell Park, Nassau County. The new, shared-use path will provide a non-motorized transportation facility that connects multiple recreational areas in the heart of Nassau County. | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-12-02 | 2010-12-02 | 2234972 | 0.000 | 0759413
8152 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 02 | 0759423 | Recondition, preserve asphalt pavement and improve drainage on Commack Road, County Road 4, between Nicolls Road and Polo Street in the towns of Babylon and Huntington, Suffolk County. | Pavement Improvement | 2009-09-07 | 2009-09-07 | 2011-04-20 | 2010-12-15 | 3490879 | 0.000 | 0759423
8153 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 02 | 0759433 | Rehabilitate the roadway pavement and make needed drainage improvements on County Route 67 between the Long Island Expressway (LIE/I495) and County Route 17 in the Town of Islip, Suffolk County. | Pavement Improvement | 2009-09-24 | 2009-09-24 | 2011-11-08 | 2011-11-08 | 3839003 | 3.650 | 0759433
8154 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759443 | A project to remove the top layer of worn, distressed pavement on Long Island Expressway service roads between Exit 59 and 63 in the towns of Islip and Brookhaven, Suffolk County, and replace it with new asphalt to improve the roadway durability. | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2011-11-18 | 2011-11-18 | 6146220 | 6.800 | 0759443
8155 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759453 | A project to remove the top layer of worn, distressed pavement on Long Island Expressway service roads between Exit 54 and 59 in the towns of Islip and Brookhaven, Suffolk County, and replace it with new asphalt to improve the roadway durability. | Pavement Improvement | 2009-09-22 | 2009-09-22 | 2010-10-13 | 2010-10-13 | 7583701 | 7.500 | 0759453
8156 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759483 | A pavement marking project in Nassau County. | Safety/Traffic Management | 2011-05-25 | 2011-05-25 | 2012-03-01 |  | 1075800 | 0.000 | 0759483
8157 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 01 | 0759543 | Implementing an alternative transportation path for bicycle and pedestrian use to connect the areas of activity centers throughout the town of Riverhead. | Transportation Enhancements | 2009-09-15 |  | 2014-02-05 |  | 3158000 | 0.000 | 0759543
8158 | NEW YORK | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0759553 | A pavement marking project in Nassau County on Atlantic Avenue and Merrick Road. | Safety/Traffic Management | 2011-05-25 | 2011-05-25 | 2012-03-01 |  | 2066680 | 0.000 | 0759553
8159 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | NASSAU |  | Multiple | 0759563 | A pavement marking project in Nassau County on Old Country Road in Mineola and Garden City and Glen Cove Road, Main Street, and Forest Avenue in Oyster Bay. | Safety/Traffic Management | 2011-05-25 | 2011-05-25 | 2012-03-01 |  | 2142800 | 0.000 | 0759563
8160 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808183 | Improve roadway storm water run off, clean and repair or replace drainage basins to locations on NY25A, Nassau County, NY RT102, Nassau County, NY RT25A, Suffolk County, & Robert Moses Causeway, Suffolk County. | Other | 2009-08-12 | 2009-08-12 | 2010-10-31 | 2010-05-17 | 411963 | 0.510 | 0808183
8161 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808193 | Resurface approximately nine miles of State roadways in Nassau and Suffolk counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. Needed drainage cleaning and repairs to improve th | Pavement Improvement | 2009-06-26 | 2009-06-26 | 2010-10-29 | 2010-12-03 | 9192216 | 7.710 | 0808193
8162 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808393 | Much-needed concrete pavement repairs to sections of distressed, aging roadway systems throughout Nassau and Suffolk counties to improve pavement smoothness, reduce accidents and maintain pavement integrity. Repairs will take place on Meadowbrook Parkway | Pavement Improvement | 2009-06-24 | 2009-06-24 | 2009-11-16 | 2009-12-22 | 2014395 | 23.590 | 0808393
8163 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0808503 | Clean the steel of 10 bridges in Babylon, Brookhaven and Islip in Suffolk County to eliminate corrosion and rust and to paint the structures. These preventative-maintenance repairs will maintain the bridges structural reliability. | Bridge Improvement | 2009-06-15 | 2009-06-15 | 2010-09-30 | 2010-09-30 | 5309630 | 0.000 | 0808503
8164 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0808541 | Designing pavement repairs of State highways in Nassau and Suffolk counties, in the towns of Babylon, Islip, Hempstead, Riverhead, Brookhaven and North Hempstead. | Other | 2010-03-05 | 2010-03-05 | 2011-12-16 |  | 205380 | 15.110 | 0808541
8165 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808543 | Designing pavement repairs of State highways in Nassau and Suffolk counties, in the towns of Babylon, Islip, Hempstead, Riverhead, Brookhaven and North Hempstead. | Pavement Improvement | 2010-03-05 | 2010-03-05 | 2012-02-09 | 2012-02-09 | 20043945 | 15.110 | 0808543
8166 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 0808551 | Upgrade approximately 900 traffic signals in Nassau and Suffolk counties by replacing existing incandescent lights with more energy efficient Light Emitting Diode (LED) bulbs to reduce energy use and improve the environment. The project includes installin | Safety/Traffic Management | 2009-08-20 | 2009-08-20 | 2011-04-25 |  | 100000 | 0.000 | 0808551
8167 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 0808553 | Upgrade approximately 900 traffic signals in Nassau and Suffolk counties by replacing existing incandescent lights with more energy efficient Light Emitting Diode (LED) bulbs to reduce energy use and improve the environment. The project includes installin | Safety/Traffic Management | 2009-08-20 | 2009-08-20 | 2011-10-18 | 2011-10-18 | 4951041 | 0.000 | 0808553
8168 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 0808561 | Upgrade the outdated, 22-year-old original technology that operates 53 out of 190 motorist information signs operated by NYSDOT INFORM's transportation management center. The project will increase the reliability of the variable message, real-time travel | Other | 2010-03-30 | 2010-03-30 | 2011-03-31 | 2011-08-26 | 5366 | 0.000 | 0808561
8169 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 0808563 | Upgrade the outdated, 22-year-old original technology that operates 53 out of 190 motorist information signs operated by NYSDOT INFORM's transportation management center. The project will increase the reliability of the variable message, real-time travel | Safety/Traffic Management | 2010-03-30 | 2010-03-30 | 2011-08-26 | 2011-08-26 | 2611165 | 0.000 | 0808563
8170 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0808621 | Designing pavement repairs of State highways in Nassau and Suffolk counties, targeting sections of the NY 231 and the Sagtikos Parkway. | Other | 2010-03-18 | 2010-03-18 | 2011-01-21 |  | 30423 | 19.500 | 0808621
8171 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 0808643 | Preserve the Stony Brook Mill Pond as a fragile aquatic resource and better protect motorists from roadway flooding conditions on NY Route 25A (North Country Road) in Stony Brook, Town of Brookhaven, Suffolk County. Accumulated sediment will be removed fr | Other | 2009-10-01 | 2009-10-01 | 2010-12-21 | 2010-06-30 | 922963 | 1.600 | 0808643
8172 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | SUFFOLK | NEW YORK-NORTHEASTERN NJ (NJ) | 01 | 0935613 | Calverton Enterprise Park Rail Spur in the Town of Riverhead. Rehabilitate Freight rail access to Calverton Industrial Park from the LIRR Main line. The rail spur is 2.3 miles from the LIRR main line along the south side of Connecticut Ave across Grumman | Other | 2010-01-27 | 2010-01-27 | 2012-02-17 |  | 4800000 | 0.000 | 0935613
8173 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1753373 | Relocate the Maxwell Road intersection with Albany Shaker Road in the town of Colonie, Albany County 800 feet to the east, away from the existing intersection. The existing intersection will remain, but only for right turns to and from Albany Shaker and M | Pavement Widening | 2009-09-23 | 2009-09-23 | 2010-11-30 | 2010-10-11 | 5158409 | 0.000 | 1753373
8174 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 1754523 | A project to provide pedestrian and bicycle access to the Troy-Menands Bridge. | Transportation Enhancements | 2010-04-09 | 2010-04-09 | 2011-03-14 | 2010-10-27 | 1107534 | 0.010 | 1754523
8175 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ESSEX |  | 22 | 1755123 | Replace the bridge carrying Haselton Road over West Branch Ausable River, Town of Wilmington. | Bridge Replacement | 2009-11-16 | 2009-11-16 | 2010-09-25 | 2010-11-15 | 1510000 | 0.000 | 1755123
8176 | NEW YORK | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | WASHINGTON |  | 20 | 1755153 | Replace the bridge carrying Clinton Street, Saunders Street and Division Street over the Delaware and Hudson Railroad in the Village of Whitehall in Washington County. This rail line serves the area as a major north/south rail connection between the Unite | Bridge Replacement | 2009-09-01 | 2009-09-01 | 2011-11-03 | 2011-06-30 | 5167794 | 0.000 | 1755153
8177 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 22 | 1755213 | Replace the County Route 3/Warrensburg Road Bridge over Stony Creek in the Town of Stony Creek, Warren County. | Bridge Replacement | 2009-06-05 | 2009-06-05 | 2010-04-30 | 2010-12-07 | 1458010 | 0.010 | 1755213
8178 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1755933 | A project to construct Spring Run Trail, a multi-use path, from Congress Park to I-87 in the City of Saratoga Springs. | Transportation Enhancements | 2010-03-05 | 2010-03-05 | 2010-06-30 | 2010-11-15 | 2070003 | 0.000 | 1755933
8179 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756353 | Replace the bridge over the Fifth Branch of the Mohawk River in the City of Cohoes, Albany County. A new five-span steel bridge will be constructed on existing bridge alignment, including reconstruction of the Oliver Street/Cedar Street Extension intersec | Bridge Replacement | 2009-07-28 | 2009-07-28 | 2010-11-04 | 2010-12-31 | 7883000 | 0.090 | 1756353
8180 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756593 | Reconstruction of 19th Street in the City of Watervliet in Albany County. 19th Street carries New York State Touring Route 2 through the City between the Congress Street Bridge and the City Line and serves as the major east/west artery with direct connect | Pavement Improvement | 2009-07-29 | 2009-07-29 | 2010-11-08 | 2010-11-24 | 6639194 | 1.170 | 1756593
8181 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1756613 | Reconstruct Delaware Avenue for the 1.6 miles between Madison Avenue and the bridge over the New York State Thruway linking Albany and Delmar, Albany County. The project will include curb, drainage and utility work, as well as sidewalk, sign and signal im | Pavement Improvement | 2009-04-09 | 2009-04-09 | 2010-10-31 | 2011-04-15 | 15525612 | 1.630 | 1756613
8182 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RENSSELAER | ALBANY-SCHENECTADY-TROY | 21 | 1756623 | Reconstruction of NY Route 2 from 5th Avenue to 11th Street in the City of Troy | Pavement Widening | 2009-09-28 | 2009-09-28 | 2010-12-22 | 2011-06-10 | 6982070 | 0.000 | 1756623
8183 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 22 | 1757073 | A bridge replacement project of County Road 43 (Geyser Road) over the D and H Railroad. | Bridge Improvement | 2010-02-12 | 2010-02-12 | 2010-11-01 | 2010-10-29 | 1766000 | 0.000 | 1757073
8184 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RENSSELAER |  | 22 | 1757083 | Replace the bridge carrying Caretaker Road over the Walloomsac River in the town of Hoosick, Rensselaer County. This bridge, built in 1900, accesses a historic site, the Bennington Battlefield. Without this work, the bridge will be closed, causing inconve | Bridge Replacement | 2009-08-11 | 2009-08-11 | 2009-12-31 | 2010-05-21 | 1178732 | 0.000 | 1757083
8185 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GREENE |  | 20 | 1757123 | Replacement of the bridge carrying New Baltimore Road over Hannacrois Creek in the Town of New Baltimore in Greene County. The existing box-beam bridge, built in 1972 and owned by Greene County, continues to deteriorate and is beyond the rehabilitation st | Bridge Replacement | 2009-07-29 | 2009-07-29 | 2009-12-31 | 2009-12-03 | 1210932 | 0.010 | 1757123
8186 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 22 | 1757143 | Reconstruct a portion of Church Street -- State Touring Route 9N -- in the city of Saratoga Springs, Saratoga County. The project will improve Church Street between West Avenue and North Van Rensselaer Street, a distance of about one-half mile. Church Str | Pavement Improvement | 2009-09-11 | 2009-09-11 | 2010-11-19 | 2010-11-19 | 2705782 | 0.000 | 1757143
8187 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 20 | 1757173 | Replace the Grist Mill Road Bridge over Stony Creek in the Town of Stony Creek, Warren County. | Bridge Replacement | 2009-06-05 | 2009-06-05 | 2010-04-30 | 2010-04-21 | 987827 | 0.010 | 1757173
8188 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | ESSEX |  | 20 | 1758333 | Rehabilitation of Essex County Route 84, Blue Ridge Road, between the Adirondack Northway and State Route 28N in the towns of Newcomb, Minerva and North Hudson in Essex County. This county road, measuring approximately 15 miles, serves as a major connecto | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2009-08-01 | 2009-10-15 | 3372180 | 17.360 | 1758333
8189 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 20 | 1758613 | The second phase of the reconstruction of Bay Street in the City of Glens Falls in Warren County. This deteriorating city street is a major north-south route linking the City and the Town of Queensbury. It also serves as a transit route with access to a c | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2010-06-30 | 2010-07-23 | 2509672 | 1.030 | 1758613
8190 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 22 | 1758623 | A project to complete the Zim Smith Trail in the towns of Ballston and Malta in Saratoga County. The project will construct 2 miles of pedestrian trail and connect two existing trails between Oak Street in Ballston Spa and Eastline Road in Malta. The pr | Transportation Enhancements | 2009-11-24 | 2009-11-24 | 2010-06-30 | 2010-11-21 | 660896 | 0.000 | 1758623
8191 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 1758633 | Convert a historic 1921 Canal Motorship into a floating museum with exhibits that will travel to ports across New York State. | Transportation Enhancements | 2011-09-13 | 2011-09-13 | 2012-08-10 |  | 3139000 | 0.000 | 1758633
8192 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | ESSEX |  | 22 | 1758643 | Ticonderoga Train Trestle Conversion and Historic Trail Conversion in the Town of Ticonderoga. | Transportation Enhancements | 2011-04-27 | 2011-04-27 | 2014-05-14 |  | 325000 | 0.000 | 1758643
8193 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1758673 | Washington Avenue Pavement Resurfacing, Washington Avenue, Fuller Road to I-90, Jermain Street to North Main Avenue, Ontario Streen to Lark Street. | Pavement Improvement | 2009-09-25 | 2009-09-25 | 2009-11-30 | 2009-11-30 | 2313725 | 0.000 | 1758673
8194 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1758683 | Resurfacing and American's With Disabilities Act Compliance on County Road 52, Elm Avenue, Delmar Bypass and Feura Bush Road in the Town Of Bethlehem. | Pavement Improvement | 2009-11-05 | 2009-11-05 | 2009-11-30 | 2009-11-19 | 202842 | 0.000 | 1758683
8195 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RENSSELAER | ALBANY-SCHENECTADY-TROY | 21 | 1758693 | Pavement Resurfacing of County Route 145, Oakwood Avenue. | Pavement Improvement | 2009-09-25 | 2009-09-25 | 2009-11-30 | 2010-06-30 | 847655 | 1.320 | 1758693
8196 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758703 | River Road / Providence Avenue Resurfacing, River Road/Rosendale Road to General Electric Circle, General Electric Circle to Route 146, Route 146 to Schenectady City Line, Town of Niskayuna. | Pavement Improvement | 2010-05-18 | 2010-05-18 | 2009-11-30 | 2010-11-11 | 1035147 | 0.000 | 1758703
8197 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758713 | Resurfacing of Rosendale Road/River Road in the Town of Niskayuna. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2009-11-30 | 2010-07-16 | 346571 | 0.000 | 1758713
8198 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1758723 | Pavement resurfacing of Van Vanken Avenue, Nott Street to Maxon Road in the City of Schenectady. | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-11-30 | 2010-09-23 | 1051513 | 0.000 | 1758723
8199 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SARATOGA | ALBANY-SCHENECTADY-TROY | 20 | 1758733 | Resurface Saratoga County Route 108, Dunning Street, between State Route 9 and State Route 9P in the town of Malta, Saratoga County. The project will remove and replace deteriorating pavement and construct Americans With Disabilities Act (ADA)-compliant s | Pavement Improvement | 2009-10-07 | 2009-10-07 | 2009-11-30 | 2009-11-05 | 312472 | 0.000 | 1758733
8200 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GREENE |  | 20 | 1758743 | Resurface Greene County Route 28, Schoharie Turnpike, between U.S. Route 9W in the town of Athens and Second Street in the village of Athens. The project will remove and replace deteriorating pavement and construct ADA-compliant sidewalk ramps. | Pavement Improvement | 2009-10-02 | 2009-10-02 | 2009-12-02 | 2009-11-20 | 291576 | 0.000 | 1758743
8201 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 20 | 1758753 | Road Resurfacing and Americans With Disabilities Act Compliance on County Route 34, Glenwood Avenue, Glen Street to Bay Road in the Town of Queensbury. | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2010-06-25 | 2010-07-03 | 151489 | 0.000 | 1758753
8202 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WARREN |  | 20 | 1758763 | Resurfacing And Americans With Disabilities Act Compliance on County Route 28, Corinth Road, Indiana Avenue to Vandusen Drive in the Town of Queensbury. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2010-04-30 | 2010-06-11 | 206500 | 0.000 | 1758763
8203 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WASHINGTON | GLENS FALLS | 20 | 1758773 | Resurfacing project along county Route 42 (Basin Road), State Rt 196 to State R7 197. Resurfacing and Americans with disabilities Act. Town of Kingsbury and Fort Edward. | Pavement Improvement | 2010-05-19 | 2010-05-19 | 2010-09-20 | 2010-06-11 | 444375 | 0.000 | 1758773
8204 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WASHINGTON | GLENS FALLS | 20 | 1758783 | Sumpter and Allen Streets Resurfacing. Village of Hudson Falls. | Pavement Improvement | 2010-05-19 | 2010-05-19 | 2010-09-20 | 2010-06-18 | 87518 | 0.000 | 1758783
8205 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 1807993 | Pavement improvements on Route 5 in Albany, Schenectady and the towns of Colonie, Albany County, and Niskayuna, Schenectady County. Work also will include the installation at 159 intersections of ramps and sidewalk transitions compliant with the federal A | Pavement Improvement | 2009-09-15 | 2009-09-15 | 2010-09-15 | 2010-12-02 | 7382043 | 6.840 | 1807993
8206 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 1808173 | Resurface Albany, Rensselaer, Saratoga and Schenectady counties. Locations include: State Route 9 in Halfmoon, Clifton Park and Malta between State Route 146 and Crescent Avenue; State Route 20 in Guilderland between State Route 146 and west of Johnston | Pavement Improvement | 2009-08-27 | 2009-08-27 | 2010-10-31 | 2010-10-31 | 9030380 | 24.070 | 1808173
8207 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALBANY | ALBANY-SCHENECTADY-TROY | 21 | 1935773 | Wharf and dock repairs at the Port of Albany in the City of Albany. | Other | 2009-12-14 | 2009-12-14 | 2011-08-08 | 2011-11-11 | 4907115 | 0.000 | 1935773
8208 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHENECTADY | ALBANY-SCHENECTADY-TROY | 21 | 1941253 | Rehabilitation of the Existing Schenectady Trail | Transportation Enhancements | 2009-11-18 | 2009-11-18 | 2010-10-29 | 2010-09-30 | 1230000 | 0.000 | 1941253
8209 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | HERKIMER |  | 24 | 2012043 | Rehabilitate the bridge carrying Route 169 over the CSX railroad and the Erie Canal in the City of Little Falls, Herkimer County. The project will include repairing deteriorated concrete and repaving the bridge deck. | Bridge Improvement | 2009-05-27 | 2009-05-27 | 2010-06-30 | 2010-06-30 | 1310466 | 0.000 | 2012043
8210 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | ONEIDA |  | 23 | 2650303 | Sylvan Beach Pedestrain Connection Project, ARRA Transportation Enhancement Project, Village of Sylvan Beach. | Transportation Enhancements | 2011-08-04 | 2011-08-04 | 2011-11-10 | 2011-11-10 | 730620 | 0.000 | 2650303
8211 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | HERKIMER |  | 24 | 2650313 | Mohawk Streen Beautification Enhancement Project, ARRA Transportation Enhancement Project, Village of Herkimer. | Transportation Enhancements | 2010-07-26 | 2010-07-26 | 2010-10-29 | 2010-10-29 | 796785 | 0.000 | 2650313
8212 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | HERKIMER |  | 24 | 2650323 | Main Street Streetscape Enhancement Project, ARRA Transportation Enhancement Project, Village of Dolgville. | Transportation Enhancements | 2011-07-21 | 2011-07-21 | 2012-06-29 | 2012-06-29 | 1000000 | 0.370 | 2650323
8213 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | MONTGOMERY |  | 21 | 2650333 | CHURCH AND MAIN STREETSCAPE ENHANCEMENT PROJECT, VI LLAGE OF CANAJOHARIE. | Transportation Enhancements | 2010-10-21 | 2010-10-21 | 2012-08-30 | 2012-08-30 | 1000000 | 0.180 | 2650333
8214 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2804843 | Paint and wash bridges carrying state highways in Oneida, Madison, Herkimer, Hamilton, Fulton and Montgomery counties. These preventative maintenance treatments will inhibit deterioration and extend the useful life of the bridges. | Bridge Improvement | 2009-04-29 | 2009-04-29 | 2009-11-30 | 2009-11-30 | 2119629 | 0.000 | 2804843
8215 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2804853 | Paint and wash bridges carrying state highways in Oneida, Madison, Herkimer, Hamilton, Fulton and Montgomery counties. These preventative maintenance treatments will inhibit deterioration and extend the useful life of the bridges. | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2009-11-30 | 2009-11-30 | 311357 | 0.000 | 2804853
8216 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | ONEIDA | UTICA-ROME | 24 | 2804893 | Resurface Routes 5A and 69 in the City of Rome, Town of Whitestown and villages of Oriskany, Yorktown and Whitesboro in Oneida County. The project will include repaving, traffic signal replacement and new sidewalk construction. | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2009-12-18 | 2009-12-18 | 2688900 | 14.760 | 2804893
8217 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ONEIDA | UTICA-ROME | 24 | 2805083 | Replace the bridge joints on five structures along Interstate 790 in the City of Utica, Oneida County. This preventative maintenance project will maintain the bridges structural reliability. | Bridge Improvement | 2009-05-19 | 2009-05-19 | 2009-11-30 | 2009-07-09 | 420485 | 0.000 | 2805083
8218 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST0043 | Paint 14 bridges, one in Fulton County, four in Herkimer County, two in Montgomery County and seven in Oneida County. The structural steel elements of each bridge will be commercially sandblasted to eliminate rust and corrosion and then painted. Routine m | Bridge Improvement | 2010-03-15 | 2010-03-15 | 2010-05-14 | 2010-07-30 | 2472409 | 0.000 | 2ST0043
8219 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST0123 | Repair or replace deficient sidewalks in 20 municipalities in Fulton, Hamilton, Herkimer, Madison, Montgomery and Oneida counties. New, concrete sidewalks will be installed and ramps will be updated with curb cuts and detectable warnings in order to | Safety/Traffic Management | 2010-02-10 | 2010-02-10 | 2010-11-19 | 2010-11-19 | 2643708 | 13.990 | 2ST0123
8220 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | HAMILTON |  | 23 | 2ST0343 | Replace the bridge carrying Big Brook Road over Lake Abanake in the town of Indian Lake, Hamilton County. The existing structure will be replaced with a higher bridge to accommodate boat traffic in this vacation community. | Bridge Replacement | 2009-09-17 | 2009-09-17 | 2010-12-13 | 2010-12-13 | 694178 | 0.000 | 2ST0343
8221 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST0413 | A project to provide various safety improvements in the cities of Amsterdam, Johnstown, Gloversville, Little Falls, Oneida, Sherrill, Rome and Utica, in Montgomery, Fulton, Herkimer, Madison and Oneida counties. Improvements include guiderail repair or r | Safety/Traffic Management | 2010-02-15 | 2010-02-15 | 2010-09-28 | 2010-09-28 | 555357 | 2.430 | 2ST0413
8222 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST1003 | Resurface approximately three miles of Route 5S from the Herkimer County Line to Sanders Road in the town of Minden, Montgomery County and resurface approximately 5.5 miles of Route 29 from Vail Mills in the Town of Mayfield to the Saratoga County Line in | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-11-30 | 2009-10-08 | 767497 | 8.900 | 2ST1003
8223 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | HERKIMER | UTICA-ROME | 24 | 2ST1013 | Resurface highways in Herkimer County, including approximately 1.5 miles of Route 5S from Main Street in Frankfort to Route 51 in Ilion; approximately three miles of Route 28 from Route 8 to Comstock Bridge in the Town of Russia; and approximately one-h | Pavement Improvement | 2010-04-01 | 2010-04-01 | 2010-07-23 | 2010-07-23 | 1510958 | 4.350 | 2ST1013
8224 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | ONEIDA | UTICA-ROME | Multiple | 2ST1023 | Rehabilitate several state highways in Oneida County, including resurfacing approximately 16 miles of various highways and approximately five miles of shoulders along I-790 in Oneida County. In the urban areas, the top layer of worn deteriorated pavement | Pavement Improvement | 2009-10-01 | 2009-10-01 | 2010-09-10 | 2010-09-10 | 4186448 | 35.580 | 2ST1023
8225 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2ST2003 | Rehabilitate pavement at 14 sites in the cities of Amsterdam, Montgomery County; Johnstown and Gloversville, Fulton County; and Little Falls, Herkimer County. Work will consist primarily of milling and resurfacing pavement surfaces, new pavement marking | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2010-10-01 | 2010-10-01 | 3416317 | 0.000 | 2ST2003
8226 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONTGOMERY |  | 21 | 2V09513 | Resurface Route 67 through the towns of Amsterdam and Mohawk in Montgomery County. This preventive maintenance project will seal the asphalt surface to prevent water from entering cracks in the pavement, extending its lifespan. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2010-06-30 | 2009-09-03 | 131680 | 3.070 | 2V09513
8227 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2V09613 | Resurface approximately 15 miles of Routes 8, 12 and 20 through the towns of Trenton, Steuben, Forestport and Cazenovia in Oneida County and the Town of Brookfield, Madison County. This preventive maintenance project will seal the asphalt surface to preve | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2010-06-30 | 2009-09-10 | 774881 | 11.510 | 2V09613
8228 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 2V09713 | Resurface approximately nine miles of Route 12B in the towns of Marshall and Kirkland, Oneida County, and the towns of Madison and Augusta, Madison County. This preventive maintenance project will seal the asphalt surface to prevent water from entering cr | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-30 | 2009-10-05 | 553650 | 9.000 | 2V09713
8229 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3155243 | Replace two bridges on State Route 90 in Cayuga County. One bridge is over Little Salmon Creek in the Town of Genoa and the other is over Paines Creek in the Town of Ledyard. This project will remove these bridges from the deficient bridge inventory. | Bridge Replacement | 2009-10-13 | 2009-10-13 | 2010-12-01 | 2010-11-16 | 3332044 | 0.010 | 3155243
8230 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA |  | 25 | 3501423 | Replacement of the bridge carrying Bartell Road over Interstate 81 in the Town of Cicero, Onondaga County. The new bridge will increase safety and capacity. | Bridge Replacement | 2009-05-21 | 2009-05-21 | 2010-01-28 | 2010-12-16 | 7206178 | 0.100 | 3501423
8231 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA | SYRACUSE | 25 | 3601923 | Resurface almost five miles of Interstate 690 eastbound and westbound from the Teall Avenue interchange to the Interstate 481 interchange. This essential maintenance in the City of Syracuse, Onondaga County, includes guiderail upgrades and drainage and la | Pavement Improvement | 2009-05-25 | 2009-05-25 | 2010-09-01 | 2010-08-26 | 8820468 | 11.320 | 3601923
8232 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA | SYRACUSE | 25 | 3602033 | Resurface Route 20 in Madison County and Onondaga County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2009-07-28 | 2010-10-28 | 1034905 | 8.600 | 3602033
8233 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3602043 | Paving Route 11 in the Town of Hastings, Onondaga County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-09-02 | 2009-09-02 | 303719 | 2.500 | 3602043
8234 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 24 | 3602063 | Resurface Route 79 from the Tioga County line to Besner Hill in the Town of Caroline, Tompkins County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-01 | 2009-09-09 | 1230176 | 7.000 | 3602063
8235 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 24 | 3602073 | Resurface Route 79 through the towns of Ithaca and Enfield, Tompkins County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-06-24 | 2010-06-24 | 981857 | 8.460 | 3602073
8236 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3602106 | Paving Route 34, Cayuga County | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-08-17 | 2010-08-17 | 468447 | 3.600 | 3602106
8237 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3602113 | Paving Route 104A, Cayuga County Line To Oswego County | Pavement Improvement | 2010-05-08 | 2010-05-08 | 2010-05-22 | 2010-05-22 | 371960 | 2.780 | 3602113
8238 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SENECA |  | 24 | 3602313 | Paving Route 96 to Village of Waterloo, Seneca County | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2010-05-18 | 2010-06-18 | 673157 | 6.240 | 3602313
8239 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3602353 | Paving Route 34, County Route 43B at Venice Center to Skillet/Mosher Road. Towns of Scipio and Venice, Cayuga County | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2009-07-28 | 2010-09-07 | 858711 | 5.970 | 3602353
8240 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3602393 | Paving Route 38, Hamlet of Cascade to Wyckoff Road, Towns of Venice & Scipio, Cayuga County | Pavement Improvement | 2010-07-15 | 2010-07-15 | 2009-07-28 | 2010-07-29 | 836536 | 6.950 | 3602393
8241 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CORTLAND |  | 24 | 3602403 | Paving Route 11/41, City of Cortland to Village of McGraw, Town of Cortlandville, Cortland County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-10-19 | 844054 | 5.660 | 3602403
8242 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SENECA |  | 24 | 3602493 | Paving Route 414, Fayette South Town Line to Village of Seneca Falls, Towns of Fayette and Seneca Falls, Seneca County | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2009-07-28 | 2010-06-25 | 691645 | 5.790 | 3602493
8243 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA |  | 25 | 3752893 | Rehabilitate the Dorwin Avenue bridge over Onondaga Creek in the City of Syracuse, Onondaga County. The bridge deck and superstructure will be removed and replaced with a new multi-girder steel superstructure and cast-in-place concrete deck. | Bridge Improvement | 2009-08-03 | 2009-08-03 | 2010-07-16 | 2010-07-16 | 1296269 | 0.020 | 3752893
8244 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONONDAGA | SYRACUSE | 25 | 3752983 | Reconstruct Taft Road from South Bay Road to Northern Boulevard in the town of Clay and Cicero, Onondaga County. The project will rehabilitate and widen Taft Road from South Bay Road to Church Street into a five-lane roadway with a center turn lane, and w | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2011-08-19 | 2011-06-13 | 8434943 | 3.100 | 3752983
8245 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 24 | 3753733 | Reconstruct County Route 121, Warren Road, from Route 13 to North Asbury Road in the Village and Town of Lansing, Tompkins County. The safety-improvement project will include new asphalt and fresh pavement markings. | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2011-03-01 | 2010-10-30 | 5306318 | 2.970 | 3753733
8246 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SENECA |  | 24 | 3754223 | A project sponsored by Seneca County to replace the Brewer Road bridge over Black Brook. This project will remove this bridge from the deficient bridge inventory. | Bridge Replacement | 2009-09-01 | 2009-09-01 | 2011-02-01 | 2010-05-04 | 350000 | 0.000 | 3754223
8247 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SENECA |  | 24 | 3754273 | County Route 43, Dawson Corners over Boardman Creek in Seneca County. | Bridge Replacement | 2010-02-01 | 2010-02-01 | 2010-09-03 | 2010-09-02 | 716400 | 0.000 | 3754273
8248 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CORTLAND |  | 24 | 3754543 | A project sponsored by Cortland County to reconstruct 1.7 miles of Page Green Road (County Route 122) from Congden Lane to New York Route 392. This project is the third phase of an effort to rebuild Page Green Road from the City of Cortland to Route 392. | Pavement Improvement | 2010-07-08 | 2010-07-08 | 2012-04-02 | 2011-10-21 | 1617000 | 0.000 | 3754543
8249 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3754923 | A project sponsored by the Town of Mentz, Cayuga County, to replace the Haiti Road Bridge over the Seneca River. This project will remove this bridge from the deficient bridge inventory. | Bridge Replacement | 2010-03-11 | 2010-03-11 | 2011-05-02 | 2010-10-20 | 1271760 | 0.000 | 3754923
8250 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 22 | 3755043 | Replace and Upgrade the traffic signal at the College Ave/Dryden Rd Intersection, City Of Ithaca. | Safety/Traffic Management | 2010-02-24 | 2010-02-24 | 2010-09-13 | 2010-09-08 | 220000 | 0.000 | 3755043
8251 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 3804963 | Clean and paint nine different state bridges in Cayuga, Oswego, and Onondaga counties. This project will protect the structural integrity of the steel and improve the aesthetic appearance of each bridge. | Bridge Improvement | 2009-07-23 | 2009-07-23 | 2010-05-14 | 2010-05-15 | 1774117 | 0.010 | 3804963
8252 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | TOMPKINS | ITHACA | 24 | 3950423 | A Transportation Enhancement Program (TEP) project to reinforce the structural integrity of the pedestrian bridge across Six Mile Creek between Columbia Street and Ferris Street in the city of Ithaca, Tompkins County. | Transportation Enhancements | 2010-08-16 | 2010-08-16 | 2011-11-03 |  | 1077628 | 0.000 | 3950423
8253 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | CORTLAND |  | 24 | 3950463 | A Transportation Enhancement Program (TEP) project to complete the restoration of a former rail depot, including interior and exterior renovations, such as installation of parking, sidewalks and, construction of an access road in the town of Truxton, Cort | Transportation Enhancements | 2009-06-26 |  | 2013-08-27 |  | 409734 | 0.000 | 3950463
8254 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CORTLAND |  | 24 | 3M07283 | Paving Route 222, Cortlandville, Cortland/Tompkins County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-09-21 | 541845 | 3.500 | 3M07283
8255 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3M07293 | Paving Route 11, Town of Parish- Oswego County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-09-08 | 369775 | 0.000 | 3M07293
8256 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CAYUGA |  | 24 | 3M07303 | Paving Route 104, Towns of Sterling & Victory, Cayuga County | Pavement Improvement | 2010-06-15 | 2010-06-15 | 2009-07-28 | 2010-09-05 | 1048002 | 4.000 | 3M07303
8257 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3M07323 | Paving Route 104, Town and Village of Hannibal, Oswego County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-10-14 | 468560 | 0.000 | 3M07323
8258 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OSWEGO |  | 23 | 3M07333 | Paving Route 104, Village of Hannibal, Oswego County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-07-28 | 2009-10-30 | 864098 | 3.100 | 3M07333
8259 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 3M09043 | Rehabilitate multiple state-owned bridges in Cayuga, Cortland, Onondaga, Oswego and Seneca counties. This project will improve the overall condition and safety of multiple state-owned bridges. | Bridge Improvement | 2009-11-03 | 2009-11-03 | 2010-02-26 |  | 2140952 | 0.000 | 3M09043
8260 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4005503 | Resurfacing of Route 5 from the Village of Lima to Ontario County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-28 | 206212 | 2.170 | 4005503
8261 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4005573 | Resurfacing of Route 5 from the Village of Avon to the Village of Lima | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-09-07 | 531400 | 5.530 | 4005573
8262 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4015343 | Resurface a portion of State Route 15 from Route 252 to I-390 in the towns of Brighton and Henrietta, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. Needed drainage cl | Pavement Improvement | 2009-07-24 | 2009-07-24 | 2009-11-30 | 2009-11-30 | 2077780 | 1.800 | 4015343
8263 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4019563 | Resurfacing of Route 19 from Route 78 to Route 19a - Town of Gainseville | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-14 | 275426 | 2.030 | 4019563
8264 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4021223 | Resurfacing of Route 21 from Route 332 to Route 96 - City of Canandaigua | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2010-06-30 | 2010-08-11 | 857104 | 7.200 | 4021223
8265 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4021243 | Resurfacing of Route 21 from Griesha Hill Road to Bopple Hill Road | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2010-06-30 | 2010-07-29 | 621768 | 10.920 | 4021243
8266 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4031393 | Replace the Route 31F bridge over Irondequoit Creek in the Town of Perinton. (BIN 1022120) | Bridge Replacement | 2009-12-17 | 2009-12-17 | 2012-05-25 | 2012-05-25 | 1260000 | 0.000 | 4031393
8267 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORLEANS |  | 26 | 4031763 | Resurfacing of Route 31 from Niagara County to Salt Works Road | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-09-08 | 269285 | 2.400 | 4031763
8268 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | Multiple | 4031793 | Resurface a portion of State Route 31F from Route 250 in the village of Fairport to the Wayne County line in the town of Perinton, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2009-10-29 | 2009-10-31 | 1212139 | 3.780 | 4031793
8269 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | Multiple | 4031823 | RESURFACING OF VARIOUS FA ROUTES REGIONWIDE RT 31 | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-21 | 658620 | 7.560 | 4031823
8270 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4036173 | Construction of a Genesee Valley Greenway Trail bridge over the Genesee River at Route 36 in the towns of Mt. Morris and Leicester, Livingston County. This new pedestrian bridge will make continuous a significant portion of the trail facility. | Bridge Improvement | 2009-08-12 | 2009-08-12 | 2011-01-05 | 2011-11-10 | 1875478 | 0.000 | 4036173
8271 | NEW YORK | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4036183 | Resurface a portion of State Route 36 from the Steuben County line to Route 63 and from Route 63 to Route 436 in town of Dansville, Livingston County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pav | Pavement Improvement | 2009-05-14 | 2009-05-14 | 2009-10-19 | 2009-10-19 | 696345 | 2.320 | 4036183
8272 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4036213 | Resurfacing of Route 36 from Route 20 to Route 5 | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-19 | 592182 | 7.380 | 4036213
8273 | NEW YORK | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4039493 | Install edge drain on State Route 39 from Route 98 to Eagle Road in towns of Arcade and Eagle, Wyoming County. Edge drain will improve the proper draining of storm-water runoff and aid in prevention of flooding conditions. | Pavement Improvement | 2009-05-26 | 2009-05-26 | 2009-07-10 | 2009-08-31 | 676473 | 6.190 | 4039493
8274 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4039523 | Resurfacing of Route 39, Wyoming County | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-11 | 550525 | 5.650 | 4039523
8275 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4064103 | Resurfacing of Route 64 from Route 5 & 20 in Ontario/Monroe County | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2011-03-25 | 2010-08-24 | 651608 | 14.450 | 4064103
8276 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4064113 | Resurfacing of Route 64 from Dugway Road To Route 5&20 | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2009-10-30 | 2009-08-04 | 671961 | 7.010 | 4064113
8277 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | GENESEE |  | 26 | 4077063 | Resurface a portion of State Route 77 from Route 20 to Route 5 and on Route 5 from Route 33 to the Corfu village line in the towns of Darien and Pembroke and the village of Corfu, Genesee County. The top layer of worn, deteriorated pavement will be remove | Pavement Improvement | 2009-05-26 | 2009-05-26 | 2009-12-14 | 2009-12-14 | 3461434 | 16.040 | 4077063
8278 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4088183 | Resurfacing of Route 88 from Village of Newark to Route 104 | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2009-10-30 | 2009-10-05 | 393185 | 12.250 | 4088183
8279 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4096513 | Resurface a portion of State Route 96 from Kreag Road in the town of Perinton, Monroe County, to Route 64 in the town of Pittsford, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavemen | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2009-11-19 | 2009-11-19 | 1002454 | 2.610 | 4096513
8280 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 26 | 4096523 | Resurface a portion of State Route 96 from Rt. 88 to Lester Road in the village of Phelps, Ontario County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. Needed drainage cleaning and | Pavement Improvement | 2009-07-23 | 2009-07-23 | 2009-09-03 | 2009-09-03 | 374949 | 1.800 | 4096523
8281 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GENESEE | ROCHESTER | 26 | 4098393 | Repave Rt. 98 between Rt. 5 (Main St.) and Noonan Drive in the City of Batavia, Genesee County. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-18 | 2009-09-18 | 484184 | 1.180 | 4098393
8282 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 26 | 4104423 | Resurface a portion of State Route 104 from Route 259 to Route 261 in the towns of Greece and Parma, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. Needed drainage cle | Pavement Improvement | 2009-07-14 | 2009-07-14 | 2009-10-12 | 2009-10-12 | 1316452 | 2.010 | 4104423
8283 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4246083 | Resurfacing of Route 246 from Route 39 to the North Village Line | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2009-10-30 | 2009-08-06 | 136309 | 1.010 | 4246083
8284 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4256063 | Paving on Route 256 from Sliker Hill Road to Route 20A | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-10-26 | 1074321 | 9.830 | 4256063
8285 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 26 | 4259063 | Resurface a portion of State Route 259 from Colby Street to Big Ridge Road in town of Ogden and village of Spencerport, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2009-10-29 | 2009-10-08 | 1518780 | 1.670 | 4259063
8286 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 26 | 4261063 | Resurfacing of Route 261 from Route 104 to Route 18 | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2009-10-30 | 2009-08-31 | 249623 | 2.620 | 4261063
8287 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GENESEE |  | 26 | 4262063 | Resurfacing of Route 262 from Route 98 to Route 237 | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-09-17 | 502595 | 6.510 | 4262063
8288 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO | ROCHESTER | 24 | 4332053 | Repave Rt. 332 from Rt. 5 & 20 to Chapel Street in the City of Canandaigua, Ontario County. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-10-31 | 2009-09-24 | 1825407 | 3.420 | 4332053
8289 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4354063 | Resurfacing of Route 354 from Erie County Line to Route 98 | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2009-10-30 | 2009-08-18 | 1111548 | 11.210 | 4354063
8290 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4364023 | Resurfacing of Route 364 from Gateway Road to Route 5/20 | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-08-20 | 365998 | 5.290 | 4364023
8291 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4390553 | Resurface a portion of Interstate 390 from the New York State Thruway to the interchange of Interstate 590 in the town of Henrietta, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh paveme | Pavement Improvement | 2009-08-25 | 2009-08-25 | 2010-08-31 | 2010-08-05 | 2150005 | 5.070 | 4390553
8292 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4488043 | Resurfacing of Route 488 from Route 21 To Route 96, Ontario County. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2011-03-25 | 2009-09-16 | 265423 | 9.130 | 4488043
8293 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | Multiple | 4531063 | Resurface a portion of State Route 531 from Route 36 in the town of Ogden, Monroe County, to I-490 in the town of Gates, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 2009-07-07 | 2009-07-07 | 2010-11-20 | 2009-11-02 | 2099046 | 7.560 | 4531063
8294 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4754183 | An enhancement project to create Artwalk on University Avenue from Goodman St. to Union St and on Goodman St. from East Ave. to Circle St. and for Artwalk 2- Urban Trail Extension on University Avenue from Prince St. to Goodman Street in the city of Roche | Transportation Enhancements | 2011-05-31 | 2011-05-31 | 2011-05-17 |  | 3839000 | 0.000 | 4754183
8295 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | ROCHESTER |  | 4805653 | Apply a preventative maintenance treatment to seal cracks in the pavement along various state highways in Genesee and Monroe counties. This type of work keeps the highway system in a state of good repair. | Pavement Improvement | 2009-07-16 | 2009-07-16 | 2010-03-10 | 2009-08-25 | 271710 | 0.000 | 4805653
8296 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | ROCHESTER |  | 4805693 | Wash bridges and seal bridge decks at selected locations in Wayne, Ontario, Monroe, Livingston, Orleans, Genesee and Wyoming counties. This type of work keeps the system in a state of good repair. | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2009-08-26 | 2009-08-27 | 433412 | 0.000 | 4805693
8297 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | ROCHESTER |  | 4805733 | Regionwide Resurfacing Of Rural/Low Volume Highways | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2011-02-25 | 2010-06-02 | 513066 | 0.000 | 4805733
8298 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 26 | 4947213 | Resurfacing of Route 947A -Lake Ontario State Parkway | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2010-08-30 | 2010-09-08 | 755877 | 6.790 | 4947213
8299 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | GENESEE |  | 26 | 4LS0003 | A Genesee County project to resurface a portion of Batavia-Stafford Town Line Road from Route 33 to Assemblyman R. Steven Hawley Drive, and a portion of Assemblyman R. Steven Hawley Drive from Bank Street Road to Batavia-Stafford Town Line Road in the tow | Pavement Improvement | 2009-08-01 | 2009-08-01 | 2009-12-30 | 2009-08-21 | 298185 | 0.000 | 4LS0003
8300 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4LS0023 | A Livingston County project to resurface a portion of Sliker Hill Road from Route 256 to Route 15 in the town of Conesus, and a portion of Perry Road from Route 36 to Route 20A in the town of Leicester, Livingston County. The top layer of worn, deteriorat | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2009-12-31 | 2009-11-30 | 1355329 | 0.000 | 4LS0023
8301 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4LS0043 | A village of Dansville project to resurface a portion of Maple Avenue from Route 63 to Route 36 in the village of Dansville, Livingston County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement m | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2010-06-04 | 2010-10-29 | 370500 | 0.000 | 4LS0043
8302 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4LS0073 | A village of Geneseo project to resurface a portion of Lima Road from North Street to Geneseo village line in the village of Geneseo, Livingston County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh p | Pavement Improvement | 2009-10-12 | 2009-10-12 | 2010-04-30 | 2009-11-10 | 195050 | 0.000 | 4LS0073
8303 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0083 | Upgrade bridges on Driving Park, East Main Street, Main Street, Court Street, Elmwood Avenue, Lake Avenue, Andrews Street and Ford Street in the City of Rochester, Monroe County, with appropriate preventive and corrective maintenance treatments. This type | Bridge Improvement | 2009-07-20 | 2009-07-20 | 2010-01-06 | 2009-12-31 | 1450439 | 0.000 | 4LS0083
8304 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0153 | A city of Rochester project to resurface a portion of Thurston Road from Brooks Avenue to Chili Avenue in the city of Rochester, Monroe County. A thin layer of asphalt will be placed on top of the existing surface to extend the life of the road. Minor pav | Pavement Improvement | 2010-04-15 | 2010-04-15 | 2011-08-18 | 2010-08-23 | 1905248 | 0.000 | 4LS0153
8305 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0163 | A City of Rochester project to reconstruct a portion of East Henrietta Road from Mount Hope Avenue to the Erie Canal in the city of Rochester, Monroe County. The existing pavement will be completely excavated and rebuilt. | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2011-10-05 | 2010-10-30 | 2142000 | 0.000 | 4LS0163
8306 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE |  | 28 | 4LS0223 | A city of Rochester project to resurface Byron Street from South Avenue to S. Clinton Avenue in the city of Rochester, Monroe County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 2010-04-13 | 2010-04-13 | 2011-02-21 | 2010-09-02 | 2141000 | 0.000 | 4LS0223
8307 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0263 | A city of Rochester project to replace sections of hazardous sidewalks in multiple locations within the city limits, Monroe County. Replacing sidewalks that are in disrepair will improve the service life and provide a better experience for pedestrians and | Transportation Enhancements | 2010-04-05 | 2010-04-05 | 2010-08-05 | 2010-08-05 | 981000 | 0.000 | 4LS0263
8308 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0273 | Streetscape Enhancements on North Clinton Avenue | Other | 2009-11-01 | 2009-11-01 | 2010-09-17 | 2010-10-12 | 1787556 | 0.000 | 4LS0273
8309 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4LS0323 | A Monroe County project to resurface Chili Center Coldwater Road from Route 33A to Westside Drive in the town of Chili, Elmgrove Road from Route 33 to Route 531 in the town of Gates, North Greece Road from Route 18 to Frisbee Hill Road in the town of Gree | Pavement Improvement | 2009-08-25 | 2009-08-25 | 2010-09-20 | 2010-09-18 | 3400000 | 0.000 | 4LS0323
8310 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE |  | 26 | 4LS0343 | Resurface various roads owned by Monroe County including: Dewey Avenue, Long Pond Road, English Road, East Ridge Road, North Goodman Street, Thomas Avenue, Culver Road, Panorama Trail, and Old Ridge Road in various municipalities in Monroe County. The top | Pavement Improvement | 2009-07-29 | 2009-07-29 | 2009-12-30 | 2010-09-03 | 5920520 | 0.000 | 4LS0343
8311 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | Multiple | 4LS0363 | Preventative maintenance projects on Monroe County bridges. The Flynn Road bridge in the town of Greece and the Brick School House bridge in the town of Hamlin will be deck sealed; the Redman Road and North Hamlin Road bridges in the town of Hamlin will | Bridge Improvement | 2009-09-23 | 2009-09-23 | 2009-12-31 | 2009-10-10 | 323308 | 0.000 | 4LS0363
8312 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 25 | 4LS0633 | A Monroe County project to replace signs in various municipalities around the County. | Other | 2010-02-10 | 2010-02-10 | 2011-07-18 | 2010-05-27 | 296102 | 0.000 | 4LS0633
8313 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4LS0653 | A city of Canandaigua project to resurface a portion of Lakeshore Drive from Muar Street to S. Main Street in the city of Canandaigua, Ontario County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pav | Pavement Improvement | 2009-09-03 | 2009-09-03 | 2010-07-16 | 2009-11-05 | 159726 | 0.000 | 4LS0653
8314 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO | ROCHESTER | 24 | 4LS0663 | A city of Canandaigua project to replace the West Avenue Bridge over Sucker Brook in the city of Canandaigua, Ontario County. | Bridge Replacement | 2009-09-03 | 2009-09-03 | 2010-04-09 | 2010-05-20 | 552117 | 0.000 | 4LS0663
8315 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ONTARIO |  | 24 | 4LS0673 | An Ontario County project to resurface County Road 41 from State Route 332 to County Road 8 in the town of Farmington, Bankert Road from State Route 96 to County Road 13 in the town of Phelps and County Road 6 from County Road 4 to State Routes 5&20 in th | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2009-12-30 | 2010-07-23 | 2404687 | 0.000 | 4LS0673
8316 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORLEANS |  | Multiple | 4LS0703 | An Orleans County project to replace signs in various municipalities around the county. | Other | 2009-07-28 | 2009-07-28 | 2011-02-21 | 2009-09-25 | 194427 | 0.000 | 4LS0703
8317 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0713 | A town of Arcadia to locally administer a project to make element-specific repairs to the Van Buren Street Bridge over CSX Railroad in the town of Arcadia, Wayne County. The deck will be sealed and worn bridge joints and bearings will be replaced as neede | Bridge Improvement | 2009-08-25 | 2009-08-25 | 2010-03-16 | 2010-03-31 | 409426 | 0.000 | 4LS0713
8318 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0723 | Resurface a portion of Lake Bluff Road from Route 104 to Ridge Road in the town of Sodus, Wayne County and a portion of Newark Marion Road from Lyon Road to the gravel pit in the town of Palmyra, Wayne County. The surface treatment of oil and stone will e | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2009-12-30 | 2009-09-04 | 177000 | 0.000 | 4LS0723
8319 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0743 | A Wayne County project to resurface a portion of Ridge Road from East Williamson hamlet to Van Slyke Road in the town of Sodus, Wayne County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement mar | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2010-06-17 | 2010-06-14 | 340000 | 0.000 | 4LS0743
8320 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0753 | A Wayne County project to replace the bridge deck on the Christian Holler Road bridge over Salmon Creek in the town of Sodus, Wayne County. | Bridge Improvement | 2010-03-23 | 2010-03-23 | 2010-06-11 | 2010-06-11 | 225894 | 0.000 | 4LS0753
8321 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0763 | Resurface a portion of Atlantic Avenue from Downs Road to Route 350 in the town of Walworth, Wayne County. The top layer of worn, deteriorated pavement will be removed and replaced with new surface and fresh pavement markings. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2009-12-30 | 2009-10-30 | 87153 | 0.650 | 4LS0763
8322 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0773 | A town of Williamson project to replace the sidewalks on Ridge Road in the hamlet of Williamson, Wayne County. Replacing sidewalks that are in disrepair will improve the service life and provide a better experience for pedestrians and people who use a whe | Transportation Enhancements | 2010-05-17 | 2010-05-17 | 2010-06-30 | 2010-06-16 | 93933 | 0.000 | 4LS0773
8323 | NEW YORK | Underway | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | WAYNE |  | 25 | 4LS0783 | A village of Palmyra project to reconstruct a portion of Route 21 (Canandaigua Street) from southern village line to Route 31 in the village of Palmyra, Wayne County. The existing pavement will be completely excavated and rebuilt. | Pavement Improvement | 2010-04-17 | 2010-04-17 | 2011-08-17 |  | 2191618 | 0.000 | 4LS0783
8324 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WYOMING |  | 26 | 4LS0793 | Resurface a portion of Bixby Hill Road from Route 39 to the Cattaraugus county line in the town of Arcade, Wyoming County. The top layer of worn, deteriorated pavement will be removed and replaced with a new surface and fresh pavement markings. | Pavement Improvement | 2009-06-25 | 2009-06-25 | 2009-12-30 | 2009-09-21 | 697382 | 1.000 | 4LS0793
8325 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4LS0873 | Lehigh Valley Trail Extension, from Genesee Valley Greenway to River Road and from Rochester Junction to Clover Street, Enhancement Project in the Town of Mendon, Monroe County. | Transportation Enhancements | 2011-04-26 | 2011-04-26 | 2011-11-25 |  | 523000 | 0.000 | 4LS0873
8326 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 28 | 4LS0893 | A city of Rochester to locally administer a preventative maintenance project to paint and deck seal the Lake Avenue Bridge over CSX Railroad in the city of Rochester, Monroe County. Painting and sealing the bridge deck will preserve the condition | Bridge Improvement | 2009-09-28 | 2009-09-28 | 2010-08-17 | 2009-11-26 | 61358 | 0.000 | 4LS0893
8327 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | LIVINGSTON |  | 26 | 4LS0923 | Highway Preventative Maintenance, County Road 10, Geneseo Village Line to Maple Beach Road (County Road 44) in the Towns of Geneseo and Groveland, Livingston County. | Pavement Improvement | 2010-06-08 | 2010-06-08 | 2010-08-02 |  | 2232247 | 0.000 | 4LS0923
8328 | NEW YORK | Completed | C220,C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE |  | Multiple | 4LS0943 | A project to construct 7.3 miles of paved shoulders to provide for safe bicycle and pedestrian use along Jackson Rd in Penfield and Webster and Stone Rd in Henrietta and Pittsford. | Transportation Enhancements | 2011-04-04 | 2011-04-04 | 2011-08-17 | 2011-08-17 | 1489400 | 0.000 | 4LS0943
8329 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4LSA303 | Resurface various roads owned by Monroe County including: Brighton-Henrietta Town Line Road, South Winton Road, Calkins Road, Creek Street, Whalen Road, Five Mile Line Road, Whitney Road, Philips Road in various municipalities in Monroe County. The top la | Pavement Improvement | 2009-07-31 | 2009-07-31 | 2010-06-30 | 2010-09-10 | 5478638 | 0.000 | 4LSA303
8330 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | MONROE | ROCHESTER | 29 | 4T47103 | Install detectable warning fields at more than 800 locations across the seven-county region. The installation of plastic tiles containing raised bumps will help alert pedestrians with visual impairments that they are about to enter an intersection. These | Other | 2009-08-11 | 2009-08-11 | 2009-10-15 | 2009-10-16 | 304466 | 0.000 | 4T47103
8331 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5006743 | Rehabilitate approximately 6.5 miles of Interstate 86 eastbound in the towns of Randolph and Cold Springs and the village of Randolph, all in Cattaraugus County. The project is addressing deteriorating pavement conditions. | Other | 2009-07-31 | 2009-07-31 | 2010-01-29 | 2009-10-30 | 1018824 | 6.310 | 5006743
8332 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5006753 | Rehabilitate approximately 12 miles of Interstate 86 in the Towns of Sherman, North Harmony, and Ellery, in Chautauqua County. Eleven miles eastbound and 1 mile westbound will be improved. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2011-08-12 | 2011-07-15 | 4949516 | 11.630 | 5006753
8333 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5017283 | Replace two culverts on NY Route 242 in the towns of Ellicottville and Little Valley, Cattaraugus County. This project will eliminate culvert deficiencies and ensure good structural condition. | Other | 2009-06-23 | 2009-06-23 | 2010-01-29 | 2009-10-30 | 1287584 | 0.000 | 5017283
8334 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5019233 | Repave two sections of NY Route 265 (Military Road) in Erie County. Section 1 is .4 miles in length and extends from Fletcher Street to Tonawanda Creek in the city of Tonawanda, Erie County. Section 2 is 1.5 miles in length and extends from Kenmore Avenue | Pavement Improvement | 2009-08-21 | 2009-08-21 | 2010-01-29 | 2009-10-31 | 1244894 | 1.940 | 5019233
8335 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5050963 | A bridge replacement project in the city of Niagara Falls of I-190 over the LaSalle arterial ramps. The project also includes repaving and guiderail improvements on I-190. | Pavement Improvement | 2010-02-26 | 2010-02-26 | 2011-12-30 | 2012-09-14 | 4072362 | 0.770 | 5050963
8336 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5058393 | Conduct a bridge replacement and highway resurfacing and reconstruction project in the city of Jamestown, Chautauqua County. The objective of the project is to replace the Washington Street Bridge over the Chadakoin River and the Western New York and Penn | Bridge Replacement | 2009-10-06 | 2009-10-06 | 2011-06-17 | 2011-05-31 | 4011173 | 0.500 | 5058393
8337 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5086283 | A project to reconstruct into a modern roundabout the intersection of State Route 324 (Grand Island Boulevard) and Stahley Road in the Town of Grand Island, Erie County. The project will address safety and intersection capacity concerns. | Pavement Improvement | 2010-03-03 | 2010-03-03 | 2011-05-19 | 2011-05-25 | 1909800 | 0.000 | 5086283
8338 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5101793 | Repair culverts on US Route 219 and NY Route 400 in the towns of Boston and Concord, Erie County. This preventative maintenance work will eliminate corrosion and restore drainage elements to a state of good repair. | Other | 2009-07-01 | 2009-07-01 | 2009-12-29 | 2009-10-08 | 842715 | 4.700 | 5101793
8339 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5111903 | Replace the bridge for NY Route 20 over Bell Creek in the Town of Westfield, Chautauqua County. The existing bridge will be replaced with 3-side precast concrete bridge. | Bridge Replacement | 2010-01-04 | 2010-01-04 | 2010-10-28 | 2010-09-30 | 1042868 | 0.000 | 5111903
8340 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5470243 | Rehabilitate the stone facade of a notable bridge carrying NY Route 198, the Scajaquada Expressway, over NY Route 384 in the City of Buffalo, Erie County. The bridge is located in the historic site of Delaware Park, which was designed by landscape archite | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2011-02-04 | 2010-11-12 | 2483814 | 0.000 | 5470243
8341 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5512463 | Route 33 Retaining Wall Railing and Corridor Enhancements | Other | 2009-10-23 | 2009-10-23 | 2012-01-19 | 2011-11-29 | 4613632 | 2.750 | 5512463
8342 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5580393 | Replace two highway ramp bridges at the Interstate I-190/ I-290 interchange in the Town of Tonawanda, Erie County. New bridges will be installed on new alignments to the north of the existing bridges, eliminating structural deficiencies of the existing tw | Bridge Replacement | 2009-11-06 | 2009-11-06 | 2012-04-24 | 2011-12-31 | 2075732 | 0.000 | 5580393
8343 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 26 | 5755473 | Reconstruct Maple Road for 1.6 miles from Route 62 to Flint Road -- the entrance to State University of New York at Buffalo -- in the Town of Amherst, Erie County. The project will also reconstruct and widen North Bailey Avenue for 0.4 miles from Maple R | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2011-07-25 | 2011-06-20 | 7000000 | 0.430 | 5755473
8344 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5755993 | Construct four new local roads in support of the Inner Harbor Redevelopment Plan, City of Buffalo, Erie County. The four roads are Lloyd, Hanover, Perry, and Prime Slip. | New Construction | 2009-09-22 | 2009-09-22 | 2011-12-19 | 2010-12-08 | 1900000 | 0.000 | 5755993
8345 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5756293 | A pavement resurfacing project including sidewalk and snow storage improvement on Porter Avenue in the city of Buffalo. | Pavement Improvement | 2010-07-23 | 2010-07-23 | 2011-12-30 | 2011-11-22 | 850000 | 0.000 | 5756293
8346 | NEW YORK | Underway | C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5757173 | A roadway reconstruction project on portions of 10th Street and Cedar Avenue in the city of Niagara Falls. | Pavement Improvement | 2010-04-12 | 2010-04-12 | 2013-11-01 |  | 1330000 | 0.000 | 5757173
8347 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 5757213 | Replace the Cedar Street Bridge over Tonawanda Creek in the town of Newstead, Erie County, and the town of Royalton, Niagara County. The bridge is in poor condition and will be reconstructed so that it can remain open. | Bridge Replacement | 2009-08-11 | 2009-08-11 | 2011-07-21 | 2011-07-21 | 2055000 | 0.000 | 5757213
8348 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5757223 | A bridge replacement project of Drum Seaman Road over Johnson Creek in the town of Hartland. | Bridge Replacement | 2010-02-16 | 2010-02-16 | 2010-11-15 | 2010-11-15 | 790000 | 0.000 | 5757223
8349 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5757823 | Repave portions of three local streets in the city of Buffalo, Erie County, to address deteriorating pavement conditions. The streets are: Grant Street, Amherst Street, and Hertel Avenue. | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2010-12-15 | 2010-10-21 | 431077 | 0.000 | 5757823
8350 | NEW YORK | Completed | C220,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5758893 | Repave a 2.2 mile section of South Park Avenue, from Bailey Avenue to the Buffalo city line, in the city of Buffalo, Erie County. Sidewalks and lighting will also be improved along this corridor. | Transportation Enhancements | 2010-04-12 | 2010-04-12 | 2011-12-30 | 2011-11-07 | 1125000 | 0.000 | 5758893
8351 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5759143 | A project to conduct sidewalk and curb replacement along nine local streets in the City of Buffalo, Erie County. The streets are: Abbott Street from Cazenovia Street to Red Jacket Street; Austin Street from Tonawanda Street to Niagara Street; Colvin Av | Transportation Enhancements | 2010-05-07 | 2010-05-07 | 2010-10-21 | 2010-10-21 | 399047 | 0.000 | 5759143
8352 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5759153 | A project to repave nine local streets in the city of Buffalo, Erie County, to address deteriorating pavement conditions. The streets are: Abbott Street from Cazenovia Street to Red Jacket Street; Austin Street from Tonawanda Street to Niagara Street; C | Pavement Improvement | 2010-02-11 | 2010-02-11 | 2011-05-04 | 2010-08-31 | 1155530 | 0.000 | 5759153
8353 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759213 | Repave 1.6 miles of Main Street (NY Route 104) from Ontario Street to Pierce Street in the city of Niagara Falls, Niagara County ( Main Street, Walnut Avenue to Ontario Avenue; 11th Street, Lockport Street to Ontario Avenue; and Ontario Avenue, Lockpor | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2009-12-15 | 2009-12-31 | 848109 | 0.000 | 5759213
8354 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759223 | Repave 0.4 miles of Packard Road from Niagara Falls Bou levard to the CSX Bridge in the City of Niagara Falls, Niagara County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2011-04-01 | 2010-07-28 | 952000 | 0.000 | 5759223
8355 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5759233 | Repave 1.6 miles of Pine Avenue US Route 62 to Main Street (NY Route 104) in the city of Niagara Falls, Niagara County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2010-08-17 | 2010-07-30 | 1317372 | 0.000 | 5759233
8356 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759243 | Repave a two-mile section of Townline Road from Beach Ridge Road to the Bridge Over Bull Creek in the towns of Pendleton and Wheatfield in Niagara County to address deteriorating pavement conditions. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-10-29 | 2010-10-31 | 2480000 | 1.700 | 5759243
8357 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759253 | Conduct guide rail end replacements at approximately 50 locations throughout Niagara County to meet current federal standards. | Other | 2010-03-08 | 2010-03-08 | 2010-06-10 | 2010-07-02 | 141148 | 0.000 | 5759253
8358 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 29 | 5759263 | Repave a 3.1 mile section of Hartland Road, from Townline Road to Lake Road (NY Route 18), in the town of Somerset, Niagara County. The roadway will be paved to address deteriorating pavement conditions. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-12-14 | 2009-09-29 | 401627 | 2.950 | 5759263
8359 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759273 | Repave a one-mile section of Nash Road from Cherry Hill Road to Steig Road in the town of Wheatfield, Niagara County. The paving address deteriorating pavement conditions. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-12-14 | 2010-07-02 | 564330 | 0.930 | 5759273
8360 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5759283 | Improve storm water management along Tonawanda Creek Road in the Town of Pendleton, Niagara County. | Other | 2009-08-10 | 2009-08-10 | 2009-12-14 | 2009-11-18 | 81833 | 1.810 | 5759283
8361 | NEW YORK | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5759293 | Repave 4.1 miles of NY Route 430 from County Route 128/44 to County Route 13 in the Town of Ellery, Chautauqua County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-10-20 | 2009-10-20 | 2010-06-30 | 2010-06-04 | 877000 | 0.000 | 5759293
8362 | NEW YORK | Underway | C250 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5759303 | Repave 5.6 miles of Hunt Road (County Route 82/32) from County Route 43 to the Jamestown city line in the towns of Busti, Ellicott, and North Harmony, in Chautauqua County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-10-06 | 2009-10-06 | 2010-01-06 |  | 1099696 | 0.000 | 5759303
8363 | NEW YORK | Underway | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5759313 | Repave 1.7 miles of State Route 417 (West State Street) from the Olean city line to State Route 16 in the City of Olean, Cattaraugus County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-10-20 | 2009-10-20 | 2010-09-27 |  | 931122 | 1.700 | 5759313
8364 | NEW YORK | Underway | C200 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5759323 | Repave 0.2 miles of Doughty Street from the NY Route 60 to Lincoln Avenue in the City of Dunkirk, Chautauqua County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-10-19 | 2009-10-19 | 2010-07-15 |  | 433635 | 0.000 | 5759323
8365 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5759343 | Repave 1.2 miles of County Route 4 (Broadway Road) in the Town of Persia. Repave 2.84 miles of CR 83 (Old Buffalo Road)and 0.9 miles of CR19 (Five Mile Road) in Town of Allegany,Cattaraugus County. The project will address deteriorating pavement condition | Pavement Improvement | 2009-09-03 | 2009-09-03 | 2009-10-09 | 2009-10-08 | 1077556 | 0.000 | 5759343
8366 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5759363 | Repave 2.1 miles of NY Route 417 (Wildwood Avenue) from Linwood Avenue to the east City line in the City of Salamanca, Cattaraugus County. The project will address deteriorating pavement conditions. | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2010-11-15 | 2010-09-14 | 1256000 | 0.000 | 5759363
8367 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5759413 | Enhancement project that will construct a two-classroom building for traffic and personal safety instruction at the Chautauqua Children's Safety Education Village in the town of North Harmony, Chautauqua County. The village, which is being developed at th | Transportation Enhancements | 2009-09-15 | 2009-09-15 | 2011-03-01 | 2011-03-31 | 1736354 | 0.000 | 5759413
8368 | NEW YORK | Completed | C220,C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5759423 | ENHANCEMENTS TO OUTER HARBOR; SOUTH PARK AVE, TIFF STREET, TIFF STREET PIER, TIMES BEACH, GALLAGER BEACH, CITY OF BUFFALO; SIDEWALK, BOARDWALK, FISHING PIER, PARKING AND SEATING AREAS, BICYCLE/PEDESTRIAN SIGNAL AND TRAIL, LANDSCAPE, LIGHTING | Transportation Enhancements | 2010-06-29 | 2010-06-29 | 2012-05-31 | 2012-05-31 | 1075281 | 0.000 | 5759423
8369 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5759433 | UNION SHIP CANAL PROMEMADE - IMPROVE WESTERN END OF UNION SHIP CANAL. CONSTRUCT BOARDWALK AND PROMENADE WITH BENCHES, ARCHITECTUAL LIGHTING, FISH CLEANING TABLES AND RAISED LETTERING INFORMATIONAL DISPLAYS | Transportation Enhancements | 2010-04-06 | 2010-04-06 | 2012-12-15 | 2012-12-15 | 2000000 | 0.000 | 5759433
8370 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | Multiple | 5759523 | A project to upgrade and repair bridge joints on six bridges in the towns of Lockport, Newfane, Niagara, Pendleton, Wilson, and Wheatfield. | Bridge Improvement | 2010-05-01 | 2010-05-01 | 2010-05-21 | 2010-05-21 | 216917 | 0.000 | 5759523
8371 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 28 | 5805903 | Replace nine traffic signals and 41 pedestrian signals at various locations in Erie County. | Other | 2009-08-21 | 2009-08-21 | 2012-03-08 | 2011-10-31 | 891570 | 0.000 | 5805903
8372 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5806113 | Replace selected signs on state highways throughout the City of Buffalo, towns of Amherst and Cheektowaga and Village of Williamsville, Erie County. | Other | 2009-07-03 | 2009-07-03 | 2010-12-31 | 2010-11-02 | 397000 | 0.000 | 5806113
8373 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5807623 | Repair and replace bridge joints along Interstate 290 in the towns of Tonawanda and Amherst, Erie County. Joints require periodic repair to prevent water from penetrating onto other bridge elements, causing corrosion. Repairing bridge joints extends the | Bridge Improvement | 2009-10-23 | 2009-10-23 | 2011-01-06 | 2010-11-08 | 200000 | 0.000 | 5807623
8374 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5807653 | Paint eight bridges in various locations in the city of Buffalo and town of Tonawanda, Erie County. The bridge painting is preventive maintenance. | Bridge Improvement | 2009-02-16 | 2009-02-16 | 2010-08-30 | 2010-07-10 | 537000 | 0.000 | 5807653
8375 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | BUFFALO-NIAGARA FALLS, NY |  | 5807683 | A project to paint and seal eight bridges in Erie and Niagara counties. Painting bridges and sealing their supportive members and decks is preventive maintenance done to keep water from penetrating other structural elements on the bridge, causing c | Bridge Improvement | 2010-01-18 | 2010-01-18 | 2010-08-27 | 2010-07-31 | 1000000 | 0.000 | 5807683
8376 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | BUFFALO-NIAGARA FALLS, NY |  | 5808233 | Install approximately 285 detectable warnings at various locations in the city of Buffalo and the town of Cheektowaga in Erie County, and the city of Niagara Falls and the town of Wheatfield in Niagara County. Detectable warnings are installed on sidewalk | Transportation Enhancements | 2009-08-21 | 2009-08-21 | 2010-01-11 | 2009-11-09 | 263066 | 0.000 | 5808233
8377 | NEW YORK | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5810433 | Resurface approximately three miles of pavement on US Route 219 and NY Route 417 in the City of Salamanca, Cattaraugus County, and Allegany Reservation of the Seneca Nation of Indians. The top layer of worn, deteriorated pavement will be removed and repla | Pavement Improvement | 2009-07-02 | 2009-07-02 | 2009-09-30 | 2009-08-25 | 978714 | 6.240 | 5810433
8378 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5810463 | Mill and repave highway access ramps with a single course overlay. Ramp locations, all in Erie County, include: N.Y. Route 78 in the towns of Clarence and Amherst, N.Y. Route 263 in the town of Amherst, N.Y. Route 33 in the town of Cheektowaga, N.Y. Route | Other | 2009-07-23 | 2009-07-23 | 2009-10-19 | 2009-09-30 | 474226 | 1.460 | 5810463
8379 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5810473 | Resurface approximately 1.5 miles of pavement on NY Route 78 in the Village of Depew and towns of Lancaster and Cheektowaga, Erie County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement marking | Pavement Improvement | 2009-05-28 | 2009-05-28 | 2009-10-22 | 2009-09-30 | 726874 | 1.440 | 5810473
8380 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 28 | 5810513 | Repave Route 957A, Robert Moses Parkway, from Interstate 190 to JB Daly Boulevard in the City of Niagara Falls, Niagara County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings to exten | Pavement Improvement | 2009-07-23 | 2009-07-23 | 2009-12-10 | 2009-10-23 | 1172173 | 3.230 | 5810513
8381 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | Multiple | 5810563 | Clean and repair closed drainage systems along State Routes 198, 78, 277, 5 and 425 in the towns of Tonawanda, Amherst and Clarence and the city of Buffalo, Erie County. Collapsed drainage structures that are encountered during cleaning will be repaired. | Other | 2009-08-06 | 2009-08-06 | 2009-12-29 | 2009-11-04 | 261041 | 5.040 | 5810563
8382 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 5810613 | Replace two overhead sign structures on State Route 400 in the towns of West Seneca and Elma and also install a 511 system signage region-wide. 511 is the state's latest traveler-advisory system. With one phone call, motorists can obtain real-time acciden | Other | 2009-08-12 | 2009-08-12 | 2010-08-27 | 2010-07-29 | 528419 | 0.000 | 5810613
8383 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE |  | Multiple | 5810623 | Replace joints on various bridges along the NY Route 33 corridor in the city of Buffalo and town of Cheektowaga, Erie County. | Bridge Improvement | 2009-07-03 | 2009-07-03 | 2010-01-06 | 2009-11-30 | 501454 | 0.000 | 5810623
8384 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 5810723 | Install signs for bike route 517 in Erie, Niagara, and Chautauqua counties. The project also includes sidewalk construction at the intersection of State Route 263 and State Route 270 in the Town of Amherst, and along State Route 354 from French Lea Road t | Transportation Enhancements | 2009-10-27 | 2009-10-27 | 2010-08-27 | 2010-05-12 | 318340 | 0.000 | 5810723
8385 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5V09133 | Repave portions of State Route 394 totaling 6.2 miles in the towns of Cold Spring, Conewango, Napoli and Randolph and the village of East Randolph, in Cattaraugus County. The new pavement will address deteriorating pavement conditions. | Pavement Improvement | 2009-10-08 | 2009-10-08 | 2011-02-15 | 2009-10-20 | 574789 | 6.160 | 5V09133
8386 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5V09153 | Repave a five-mile portion of U.S. Route 62, from the Chautauqua County line to Youngs Road in the towns of Conewango and Leon, Cattaraugus County. | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2011-02-15 | 2010-06-30 | 342468 | 3.100 | 5V09153
8387 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5V09163 | Conduct pavement crack sealing on approximately 100 miles of roads throughout Cattaraugus County. Asphalt pavement will be cleaned and sealant will be applied. | Pavement Improvement | 2009-09-01 | 2009-09-01 | 2009-12-15 | 2009-10-21 | 220061 | 0.000 | 5V09163
8388 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 5V09213 | Repave approximately 21 miles of Interstate 86 in the towns of Ellery, Ellicott and Poland, the village of Falconer and the city of Jamestown in Chautauqua County, and the town and village of Randolph in Cattaraugus County. This portion of I-86 is showing | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2011-01-03 | 2010-08-19 | 1487524 | 21.340 | 5V09213
8389 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | CATTARAUGUS |  | 29 | 5V09223 | Repave a 2.5 mile bypass from Interstate 86 to NY Route 430 in the town of Ellery and village of Bemus Point, Chautauqua County. A single course overlay will be applied to address deteriorating pavement conditions. | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2011-01-31 | 2010-06-02 | 338446 | 1.620 | 5V09223
8390 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CHAUTAUQUA |  | 27 | 5V09253 | Conduct pavement crack sealing on approximately 100 miles of roads throughout Chautauqua County. Asphalt pavement will be cleaned and sealant will be applied. | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2009-12-15 | 2009-10-22 | 260285 | 0.000 | 5V09253
8391 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09323 | Seal pavement cracks on federal aid-eligible routes in northern Erie County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pavement's service life. | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2011-01-31 | 2010-06-15 | 128297 | 0.000 | 5V09323
8392 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09413 | Repave a 0.8 mile portion of US Route 20, from Cazenovia Creek to Seneca Street (NY Route 16) in the towns of West Seneca and Elma, Erie County. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2011-01-31 | 2010-06-30 | 229321 | 1.540 | 5V09413
8393 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE |  | 27 | 5V09423 | Repave a one-mile portion of U.S. Route 20A (Quaker Street) in the village of Orchard Park, Erie County. The project will address deteriorating pavement conditions. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt | Pavement Improvement | 2009-09-21 | 2009-09-21 | 2009-09-15 | 2009-09-21 | 109955 | 1.020 | 5V09423
8394 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09433 | Repave a 5.8-mile-long section of N.Y. Route 39 in Erie County, from N.Y. Route 75 in the town of Collins to Trevett Road in the town of Concord. The project will address deteriorating pavement conditions. The top layer of worn, deteriorated pavement will | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2011-01-31 | 2010-10-05 | 350922 | 5.770 | 5V09433
8395 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09443 | Repave a 3.5-mile-long portion of N.Y. Route 249 in the Town of North Collins, Erie County. The project will address deteriorating pavement conditions. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pa | Pavement Improvement | 2010-08-20 | 2010-08-20 | 2009-09-15 | 2009-09-25 | 733595 | 3.480 | 5V09443
8396 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ERIE | BUFFALO-NIAGARA FALLS, NY | 27 | 5V09463 | Seal pavement cracks on federal aid-eligible routes in southern Erie County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pavements service life. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2011-01-31 | 2010-07-09 | 225621 | 0.000 | 5V09463
8397 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09513 | Repave a 3.7-mile-long portion of N.Y. Route 425 in the town of Cambria, Niagara County. The paving will extend from Upper Mountain Road to N.Y. Route 104. It will address deteriorating pavement conditions. The top layer of worn, deteriorated pavement wil | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-15 | 2009-09-11 | 450559 | 3.740 | 5V09513
8398 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09523 | Repave a 10.4-mile-long portion of N.Y. Route 77 in the towns of Lockport and Royalton, Niagara County. The project will extend from N.Y. Route 31 to the Genesee County line. It will address deteriorating pavement conditions. The top layer of worn, deteri | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-15 | 2009-10-15 | 1109897 | 10.440 | 5V09523
8399 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09533 | Repave a 5.8-mile-long portion of NY Route 429 in Niagara County. The project will extend from Lockport Road in the town of Wheatfield to N.Y. Route 104 in the towns of Cambria and Lockport, where the centerline of the road is the municipal boundary. The | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-15 | 2009-10-20 | 964862 | 5.810 | 5V09533
8400 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | NIAGARA | BUFFALO-NIAGARA FALLS, NY | 26 | 5V09543 | Seal pavement cracks on federal aid-eligible routes in Niagara County. Sealing surface cracks in asphalt helps prevent moisture from infiltrating beneath the pavement surface, extending the pavements service life. The project is scheduled for completion t | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2010-06-15 | 2009-10-06 | 135253 | 0.000 | 5V09543
8401 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6008513 | Build embankment and pavement on a five-mile section of relocated US Route 15 in the Town of Lindley, Steuben County. This project is the first phase of a staged project to build a four lane highway which will be designated Interstate 99. | Other | 2009-09-14 | 2009-09-14 | 2012-08-30 | 2012-08-30 | 6056978.47 | 0.000 | 6008513
8402 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | YATES |  | 29 | 6011163 | A highway resurfacing project on Rt 54A from Branchport to Penn Yan in the town of Jerusalem and the village of Penn Yan in Yates County. | Pavement Improvement | 2010-03-23 | 2010-03-23 | 2010-11-04 | 2010-11-04 | 5380608 | 5.940 | 6011163
8403 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHUYLER |  | 29 | 6017213 | Replace the bridge carrying State Route 224 over Catharine Creek in the village of Montour Falls, Schuyler County. | Bridge Improvement | 2010-01-13 | 2010-01-13 | 2010-11-17 | 2010-11-17 | 1645644 | 0.000 | 6017213
8404 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6021143 | Replace the bridge carrying State Route 244 over the north branch of Phillips Creek in the town of Amity, Allegany County. | Bridge Replacement | 2010-01-14 | 2010-01-14 | 2011-05-26 | 2011-05-26 | 1422790 | 0.000 | 6021143
8405 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6037173 | Replace the bridge on Route 415 over Wolf Run Creek in the town of Campbell, Steuben County. | Bridge Replacement | 2009-05-20 | 2009-05-20 | 2009-12-30 | 2009-11-18 | 1612046 | 0.000 | 6037173
8406 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6056233 | Replace the bridge carrying State Route 417 over Dyke Creek in the town of Andover, Allegany County. | Bridge Replacement | 2010-01-12 | 2010-01-12 | 2010-11-15 | 2010-11-15 | 1340584 | 0.000 | 6056233
8407 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6066843 | Replace the I-86 bridge over Route 415 in the town of Painted Post, Steuben County. | Bridge Replacement | 2009-05-15 | 2009-05-15 | 2011-06-01 | 2011-06-02 | 4874526 | 0.000 | 6066843
8408 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | CHEMUNG | ELMIRA | 29 | 6753763 | A project to replace the county Route 43 bridge over Sing Sing Creek in the town of Big Flats, Chemung County. | Bridge Replacement | 2010-04-01 | 2010-04-01 | 2011-04-15 | 2011-12-19 | 1047279 | 0.000 | 6753763
8409 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | CHEMUNG | ELMIRA | 29 | 6754133 | A project to reconstruct Washington Avenue, from Davis Street to Walnut Street, in the city of Elmira, Chemung County. | Pavement Improvement | 2009-12-07 | 2009-12-07 | 2011-06-30 | 2011-06-30 | 644000 | 0.000 | 6754133
8410 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6754293 | Resurface seven miles of County Route 12 from the Village of Alfred to State Route 417 in the towns of Andover, Ward, and Alfred, Allegany County. Existing pavement will be overlaid to provide a smooth surface and prolong the life of the pavement. | Pavement Improvement | 2009-08-20 | 2009-08-20 | 2009-11-30 | 2009-09-04 | 795179 | 0.000 | 6754293
8411 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHUYLER |  | 29 | 6754303 | Resurface 2.5 miles of County Route 16 from Meads Hill Road to Townsend Road in the Town of Dix, Schuyler County. The existing pavement will be resurfaced to provide a smooth surface and prolong the life of the pavement. | Pavement Improvement | 2009-10-01 | 2009-10-01 | 2009-11-30 | 2009-10-05 | 240430 | 0.000 | 6754303
8412 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | YATES |  | 29 | 6754313 | Resurface 1.8 miles of County Route 32 from County Route 29 to County Route 33 in the Town of Jerusalem, Yates County. Existing pavement will be overlaid to provide a smooth surface and prolong the life of the pavement. | Pavement Improvement | 2010-05-13 | 2010-05-13 | 2009-11-30 | 2010-05-19 | 183208 | 0.000 | 6754313
8413 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6754323 | Resurface 1.9 miles of County Route 14 from County Route 15 south in the Town of Bath, Steuben County. The existing pavement will be recycled and resurfaced with new asphalt. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2009-11-30 | 2009-09-03 | 227514 | 0.000 | 6754323
8414 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6754333 | Resurface 3.3 miles of County Route 14 from County Route 69 north in the towns of Bath and Howard, Steuben County. The existing pavement will be recycled and resurfaced with new asphalt. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2009-11-30 | 2009-09-02 | 434224 | 0.000 | 6754333
8415 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6754343 | Resurface four-tenths of a mile of East Avenue from Main Street to Addison Street in the Village of Arkport, Steuben County. The existing deteriorated pavement surface will be removed and replaced with new asphalt and fresh pavement markings. | Pavement Improvement | 2009-09-18 | 2009-09-18 | 2009-11-30 | 2009-09-21 | 80104 | 0.000 | 6754343
8416 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6754353 | Resurface 1.2 miles of streets in the City of Hornell, Steuben County. The project will overlay the existing pavement on portions of Thatcher, North Church, Erie, Center, and Adsit Streets to provide a smooth surface and prolong the life of the pavement. | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-11-30 | 2009-09-09 | 150885 | 0.000 | 6754353
8417 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN | ELMIRA | 29 | 6754443 | Resurface two-tenths of a mile of West Third Street in the City of Corning, Steuben County. The existing deteriorated pavement surface, from Walnut Street to State Street, will be removed and replaced with new asphalt. | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-11-30 | 2009-10-06 | 19835 | 0.000 | 6754443
8418 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN | ELMIRA | 29 | 6754453 | Resurface one-tenth of a mile of East Third Street from Cedar Street to Pine Street in the City of Corning, Steuben County. The existing deteriorated pavement surface will be removed and replaced with new asphalt. | Pavement Improvement | 2009-08-11 | 2009-08-11 | 2009-11-30 | 2009-10-06 | 17540 | 0.000 | 6754453
8419 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN | ELMIRA | 29 | 6754463 | Resurface four-tenths of a mile of West William Street from Pulteney Street to Bissell Avenue in the City of Corning, Steuben County. The existing deteriorated pavement surface will be removed and replaced with new asphalt. | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-11-30 | 2009-10-06 | 79584 | 0.000 | 6754463
8420 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6754483 | A TEP project to complete the Genesee Valley Greenway in the village of Cuba, Allegany County. The project will include improving existing trail, constructing two new footbridges, installing gates and signage, building a parking lot and installing bicycle | Transportation Enhancements | 2011-02-01 | 2011-02-01 | 2011-08-25 | 2011-08-25 | 589400 | 0.000 | 6754483
8421 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6754493 | A TEP project to enhance landscaping and to replace or install new light fixtures and sidewalks, sidewalk ramps and pavement markings in the village of Andover, Allegany County. | Transportation Enhancements | 2011-01-10 | 2011-01-10 | 2011-06-17 | 2011-06-17 | 513500 | 0.000 | 6754493
8422 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6803963 | Rehabilitate culverts in various locations in the towns of Urbana and Pulteney, Steuben County. | Pavement Improvement | 2009-04-20 | 2009-04-20 | 2010-05-30 | 2009-07-28 | 915925 | 0.000 | 6803963
8423 | NEW YORK | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804183 | Wash bridges and seal bridge decks at various locations in Allegany and Steuben counties. | Bridge Improvement | 2009-05-14 | 2009-05-14 | 2009-09-30 | 2009-10-30 | 584282 | 0.000 | 6804183
8424 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804223 | A project to remove hazardous trees along select state rights-of-way in Allegany, Schuyler, Steuben, and Yates counties. | Other | 2010-02-01 | 2010-02-01 | 2010-05-30 | 2010-03-10 | 229199 | 0.000 | 6804223
8425 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804233 | Sidewalk Reconstruction for ADA compliance, Montour Falls, Addison, Southport. | Transportation Enhancements | 2009-10-27 | 2009-10-27 | 2010-06-30 | 2010-04-15 | 186044 | 1.370 | 6804233
8426 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | YATES |  | 29 | 6804263 | A project resurface 30 miles of state Routes 14, 14A, 245, 409 in Schuyler and Yates counties. | Pavement Improvement | 2010-03-04 | 2010-03-04 | 2010-12-15 | 2010-07-28 | 1933641 | 5.710 | 6804263
8427 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804273 | Rock Slope Remediation of 10 sites in Allegany & Steuben Counties. | Other | 2010-03-17 | 2010-03-17 | 2010-05-28 | 2010-04-21 | 366505 | 0.100 | 6804273
8428 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804283 | Paint bridges on I-86 and I-390 at various locations in Allegany and Steuben counties. | Bridge Improvement | 2009-08-25 | 2009-08-25 | 2010-10-31 |  | 1085544 | 0.000 | 6804283
8429 | NEW YORK | Completed | C250 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 6804293 | Rehabilitate bridges in various locations in Allegany and Steuben counties. | Bridge Improvement | 2009-07-07 | 2009-07-07 | 2009-10-31 | 2009-11-19 | 444923 | 0.000 | 6804293
8430 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ALLEGANY |  | 29 | 6804333 | Repair 21 culverts on Interstate 86 in the towns of Cuba and Friendship, Allegany County. The project includes drainage structure replacement and culvert relining. | Other | 2009-08-13 | 2009-08-13 | 2010-06-30 | 2010-05-17 | 937268 | 0.000 | 6804333
8431 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | STEUBEN |  | 29 | 6935223 | A project to repair two Bath & Hammondsport Railroad bridges over Niles Creek and Moores Creek in the town of Avoca, Steuben County. | Bridge Improvement | 2010-10-20 | 2010-10-20 | 2011-11-29 | 2011-11-29 | 625000 | 0.000 | 6935223
8432 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 23 | 7752473 | Replace the County Route 39 Bridge over the Grasse River in the Town of Louisville, St. Lawrence County. This project involves replacing the historic stone arch bridge with a steel structure adjacent to the existing bridge. A historic plaque will document | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2010-10-13 | 2010-10-13 | 3467929 | 0.000 | 7752473
8433 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LEWIS |  | 23 | 7752543 | A project to replace the Sweeney Road bridge over the East Branch of Fish Creek in the Town of West Turin, Lewis County. The new bridge will be built next to the existing structure and will have wider travel lanes and shoulders, improving safety for moto | Bridge Replacement | 2009-12-23 | 2009-12-23 | 2010-09-14 | 2010-09-14 | 725857 | 0.000 | 7752543
8434 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | JEFFERSON |  | 23 | 7752583 | A project to replace the Lisk Bridge carrying County Route 69 over Sandy Creek in the Town of Adams, Jefferson County. The new structure will be built adjacent to the existing bridge. Improvements will increase sight distance along the corridor and enha | Bridge Replacement | 2009-11-26 | 2009-11-26 | 2010-11-24 | 2010-11-24 | 2359999.53 | 0.000 | 7752583
8435 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 23 | 7752913 | Replace the Willow Street Bridge over the Salmon River in the Village of Malone, Franklin County. This project involves replacing the existing steel structure with a concrete structure at the same location. Included in the project will be the installation | Bridge Replacement | 2009-08-04 | 2009-08-04 | 2010-12-08 | 2010-12-08 | 1270618 | 0.000 | 7752913
8436 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | LEWIS |  | 23 | 7752973 | Pave County Route 29, West Road, in the Town of Martinsburg, Lewis County. This project involves the rehabilitation of nearly three miles of roadway from Cemetery Road to State Route 26. | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2009-10-15 | 2011-08-04 | 990038 | 0.000 | 7752973
8437 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7753023 | Replace the Narrows Road Bridge over the Chateaugay Narrows in the Town of Ellenburg, Clinton County. The new bridge will have increased vertical clearance, allowing for easier movement of recreational boats along this stretch of the Chateaugay Narrows. | Bridge Replacement | 2010-04-01 | 2010-04-01 | 2010-07-23 |  | 1364000 | 0.000 | 7753023
8438 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7753033 | Replace the Silver Lake Road Bridge over the Saranac River in the Town of Black Brook, Clinton County. The existing steel bridge will be replaced with a concrete structure at the same location. | Bridge Replacement | 2009-09-23 | 2009-09-23 | 2011-08-24 | 2011-08-24 | 1539682 | 0.000 | 7753033
8439 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7753083 | A bridge replacement project of Slosson Road over Little Chazy River in Clinton County. | Bridge Replacement | 2010-05-03 | 2010-05-03 | 2011-08-03 | 2011-08-03 | 774000 | 0.000 | 7753083
8440 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7753103 | Resurface approximately one mile of Oak Street, a Plattsburgh city street, and one mile of North Catherine Street (State Route 22), also in Plattsburgh. The streets, which run parallel to each other, will be improved from Broad Street to Boynton Avenue. T | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-11-02 | 2009-10-16 | 218812 | 3.330 | 7753103
8441 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | JEFFERSON |  | 23 | 7753113 | Resurface Arsenal Street and Washington Street in the City of Watertown | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2011-06-16 | 2011-06-16 | 260114 | 1.790 | 7753113
8442 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804393 | Replace five intersection signal systems in Clinton, Franklin and Jefferson counties. These signal improvements will maximize travel efficiency at the intersections as well as provide an added measure of safety to the traveling public. | Safety/Traffic Management | 2009-12-04 | 2009-12-04 | 2010-11-18 | 2010-10-11 | 624067 | 0.000 | 7804393
8443 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804453 | Restore the protective paint on eight bridges in Jefferson and St. Lawrence counties. Structures to be addressed in the contract include Interstate bridges on I-81 in Jefferson County, as well as a pair of bridges on State Route 58 in St. Lawrence County. | Bridge Improvement | 2009-07-14 | 2009-07-14 | 2009-12-18 | 2009-11-25 | 2897462 | 0.000 | 7804453
8444 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804553 | Provide much-needed maintenance to approximately 500 miles of highway in Lewis, Jefferson, St. Lawrence, Franklin and Clinton counties. This work involves cleaning and sealing cracks in the pavement that contribute to deterioration of the highway surface. | Pavement Improvement | 2009-07-03 | 2009-07-03 | 2010-09-28 | 2010-09-27 | 1060415 | 0.000 | 7804553
8445 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804573 | Rehabilitate four large culverts in Jefferson and St. Lawrence counties. The culverts are located on State Routes 72, 184 and 342 and will be receiving new linings as well as inlet and outlet cleanings to allow for the more efficient movement of water. | Pavement Improvement | 2009-05-15 | 2009-05-15 | 2010-08-10 | 2009-11-30 | 2626327 | 0.000 | 7804573
8446 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804733 | Clean and repaint nine state highway bridges in order to extend their useful service life. The project includes bridges carrying State Routes 22, 37, 37 C, 420 and 458 and U.S. Route 11 in Franklin, Clinton and St. Lawrence counties. | Bridge Improvement | 2010-04-06 | 2010-04-06 | 2010-12-14 | 2010-11-30 | 3273155 | 0.000 | 7804733
8447 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7804763 | Repair bridges in Lewis, Jefferson, St. Lawrence, Franklin and Clinton counties. This work will help curb deterioration and improve overall bridge conditions. | Bridge Improvement | 2010-05-03 | 2010-05-03 | 2011-09-13 | 2011-07-29 | 2054181 | 0.000 | 7804763
8448 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 24 | 7805033 | Provide needed maintenance work to two bridges in St. Lawrence County. One structure is on State Route 11B and crosses the East Branch of the St. Regis River while the second is on State Route 420 and crosses over the Racquette River. This project involve | Bridge Improvement | 2009-06-03 | 2009-06-03 | 2010-01-20 | 2009-11-18 | 1306928 | 0.000 | 7805033
8449 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7805053 | Replacing deteriorated guide rail in the Adirondack Park in Clinton Franklin and St. Lawrence counties. | Safety/Traffic Management | 2009-07-03 | 2009-07-03 | 2009-11-20 | 2009-11-21 | 1139464 | 0.000 | 7805053
8450 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 7805213 | Reconstruct 1.5 miles of sidewalks and approximately 100 sidewalk ramps to bring them into compliance with federal Americans with Disabilities Act guidelines. Construction will focus on sidewalks and ramps in the Village of Massena and Hamlet of Madrid, S | Other | 2009-07-31 | 2009-07-31 | 2010-09-13 | 2010-06-17 | 754862 | 0.000 | 7805213
8451 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 23 | 7805243 | A TEP project in the village of Rouses Point, Clinton County, will restore the National Register-listed Delaware and Hudson Railroad Station. In addition to replacing the roof, the restoration is expected to include repairing drainage, chimney work and fa | Transportation Enhancements | 2012-08-03 | 2012-08-03 | 2013-02-21 |  | 833000 | 0.000 | 7805243
8452 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | JEFFERSON |  | 23 | 7805253 | A TEP project in Sackets Harbor, Jefferson County, to build six miles of non-motorized, multi-use trail in and around the village of Sackets Harbor. The trail system will link existing local historical landmarks, such as the Sackets Harbor Battlefield, wi | Transportation Enhancements | 2012-10-01 | 2012-10-01 | 2012-11-14 |  | 495000 | 0.500 | 7805253
8453 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 23 | 7805273 | A TEP project to build a multi-use trail to link the Market Street retail corridor with both Clarkson University and SUNY Potsdam in Potsdam, St. Lawrence County. The trail will connect to Sandstoner Park and the Potsdam Commerce Park and help to integrat | Transportation Enhancements | 2010-09-22 | 2010-09-22 | 2011-10-20 | 2011-10-20 | 1450000 | 0.570 | 7805273
8454 | NEW YORK | Underway | C950 | Ferryboat | NEW YORK | CLINTON |  | 23 | 7805281 | LAKE CHAMPLAIN TRANSPORTATION COMPANY FERRY SLIP SLIP RECONCONSTRUCTION, TOWN OF PLATTSBURGH, CLINTON CO. (ARRA FERRY BOAT DISCRETIONARY FUNDS) | Other | 2009-09-17 |  | 2013-02-28 |  | 289200 | 0.000 | 7805281
8455 | NEW YORK | Underway | C950 | Ferryboat | NEW YORK | CLINTON |  | 23 | 7805283 | LAKE CHAMPLAIN TRANSPORTATION COMPANY FERRY SLIP SLIP RECONCONSTRUCTION, TOWN OF PLATTSBURGH, CLINTON CO. (ARRA FERRY BOAT DISCRETIONARY FUNDS) | Other | 2012-07-23 | 2012-07-23 | 2012-10-02 |  | 2210800 | 0.000 | 7805283
8456 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | JEFFERSON |  | 23 | 7BRD083 | Construct two new traffic lanes and enhance shoulders on Interstate 81 on Wellesley Island in the Town of Orleans, Jefferson County. The improvements will help expedite border crossing movements and enhance security at the Thousand Islands Bridge. | Pavement Widening | 2009-08-20 | 2009-08-20 | 2010-09-02 | 2009-12-30 | 1484414 | 0.180 | 7BRD083
8457 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 24 | 7V09113 | Resurface 1.3 Miles of Route 374, Village of Dannemora | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-30 | 2009-10-08 | 174356 | 1.300 | 7V09113
8458 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 24 | 7V09123 | Resurface 1.4 Miles of Route 9, Village of Champlain | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-09-23 | 156028 | 1.400 | 7V09123
8459 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CLINTON |  | 24 | 7V09133 | Resurface 0.4 Miles Of Route 2U, US Route 11 - Vermont State Line | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-08-28 | 68719 | 0.400 | 7V09133
8460 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 24 | 7V09243 | Resurface 4.8 Miles Of Route 374, Chateaugay - Brainardsville | Pavement Improvement | 2010-05-01 | 2010-05-01 | 2011-10-21 | 2011-10-21 | 1013610 | 4.800 | 7V09243
8461 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 24 | 7V09293 | Resurface 2.0 Miles of Route 3, Saint Lawrence County -Tupper Lake | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-09-16 | 249135 | 2.000 | 7V09293
8462 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 24 | 7V09294 | Resurface 9.2 Miles Of Route 11, Malone - Chateaugay | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-09-09 | 1127487 | 9.200 | 7V09294
8463 | NEW YORK | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | FRANKLIN |  | 24 | 7V09295 | Resurface 0.8 Miles Of Route 30, Malone, Elm Street & Constable Street | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 |  | 1366220 | 0.500 | 7V09295
8464 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 24 | 7V09594 | Resurface 3.9 Miles Of Route 68, Pierrepont - Colton | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-10-19 | 331072 | 3.900 | 7V09594
8465 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ST LAWRENCE |  | 24 | 7V09595 | Resurface 1.1 Miles Of Route 184, Heuvelton Village (Union St) | Pavement Improvement | 2009-08-10 | 2009-08-10 | 2009-10-16 | 2009-08-14 | 130181 | 1.070 | 7V09595
8466 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | COLUMBIA |  | 20 | 8001443 | Rehabilitate the Route 9G bridge over the Roeliff Jansen Kill in the Town of Germantown, Columbia County. | Bridge Improvement | 2009-10-06 | 2009-10-06 | 2011-11-23 | 2011-11-30 | 7041732 | 0.100 | 8001443
8467 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8010683 | A project to install a stormwater treatment system along Route 9, adjacent the Wappingers Lake in the Village of Wappingers Falls, Dutchess County. The new system will help to reduce pollutants entering the lake from the highway. | Other | 2009-11-26 | 2009-11-26 | 2011-03-28 | 2010-07-02 | 386741 | 0.290 | 8010683
8468 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 19 | 8029053 | A pavement overlay project of Route 123 in the city of Rye in Westchester County. | Pavement Improvement | 2010-02-12 | 2010-02-12 | 2010-09-24 | 2010-06-07 | 331114 | 1.490 | 8029053
8469 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 22 | 8062123 | Provide much-needed general maintenance of four bridges carrying Interstate 84 in the Town of Newburgh, Orange County. The work will extend the service life of the structures. | Bridge Improvement | 2009-09-07 | 2009-09-07 | 2010-12-15 | 2010-11-30 | 742023 | 0.000 | 8062123
8470 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8093573 | Replace the Palisades Interstate Parkway bridge over Route 202 in the towns of Haverstraw and Ramapo, Rockland County. | Bridge Replacement | 2009-06-11 | 2009-06-11 | 2012-05-11 | 2011-12-30 | 15477026 | 1.520 | 8093573
8471 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8099413 | Install an automated traffic management system on the Cross County Parkway in Westchester County. The new system will include acoustic vehicle detectors that will communicate with the regional Transportation Management Center, located in Hawthorne, Westch | Safety/Traffic Management | 2009-05-29 | 2009-05-29 | 2011-08-23 | 2010-08-31 | 5493251 | 122.460 | 8099413
8472 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8177323 | Construct new bluestone sidewalks along Route 209 in the Hamlet of Stone Ridge located in the Town of Marbletown, Ulster County. The project will restore the historic sidewalk, repave a nearly one mile section of highway, and install a new traffic signal | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2010-05-28 | 2010-05-31 | 2914138 | 0.960 | 8177323
8473 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | POUGHKEEPSIE-NEWBURGH | Multiple | 8239163 | A project to reconstruct almost two miles of Robinson Avenue (Route 9W) in the City of Newburgh, Orange County. | Pavement Improvement | 2010-03-25 | 2010-03-25 | 2011-01-31 | 2011-11-01 | 8352000 | 1.870 | 8239163
8474 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8327363 | A project to improve sidewalks and crosswalks at the intersection of Main Street (Route 9D) and Spring Street in the Village of Wappingers Falls, Dutchess County. The project will improve pedestrian access and safety. | Safety/Traffic Management | 2010-05-13 | 2010-05-13 | 2010-12-03 | 2010-12-03 | 158035 | 0.090 | 8327363
8475 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS |  | 20 | 8505203 | Construct a new park-and-ride lot on Route 199 in the Town of Rhinebeck, Dutchess County. The new facility will accommodate 35 parking spaces. And will include lighting and landscaping. | Other | 2009-10-06 | 2009-10-06 | 2010-08-31 | 2011-11-30 | 311875 | 0.100 | 8505203
8476 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | BRIDGEPORT-STAMFORD-MILFORD(CT-NY) | 19 | 8561363 | A pavement resurfacing project of Route 35 from Mead Street to Boutonville Road in the town of Lewisboro in Westchester County. | Pavement Improvement | 2010-08-09 | 2010-08-09 | 2011-03-22 | 2010-12-31 | 377098 | 2.270 | 8561363
8477 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 20 | 8753783 | Replace the Leedsville Road (County Road 2) bridge over the Webutuck Tributary in the Town of Amenia, Dutchess County. | Bridge Replacement | 2009-12-28 | 2009-12-28 | 2011-10-03 | 2010-08-03 | 593000 | 0.000 | 8753783
8478 | NEW YORK | Underway | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8755143 | New Paltz Road/Conrail Bridge Repleacement in the Town of Lloyd. | Bridge Replacement | 2010-03-21 | 2010-03-21 | 2011-01-31 |  | 2224115 | 0.000 | 8755143
8479 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 20 | 8755813 | Replace the Crum Elbow Road, County Road 41, bridge over the Fallkill Creek in the Town of Hyde Park, Dutchess County. | Bridge Replacement | 2010-04-15 | 2010-04-15 | 2010-12-13 | 2010-09-30 | 1110520 | 0.000 | 8755813
8480 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8756193 | Replace the Main Street bridge over the Rondout Creek in the Town of Wawarsing, Ulster County. | Bridge Replacement | 2009-09-08 | 2009-09-08 | 2011-06-30 | 2011-07-15 | 4519656 | 0.000 | 8756193
8481 | NEW YORK | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8756673 | Replace the Popham Road Bridge over the Metro-North Railroad tracks in the Village of Scarsdale, Westchester County. | Bridge Replacement | 2009-08-25 | 2009-08-25 | 2010-06-30 |  | 13006683 | 0.010 | 8756673
8482 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | COLUMBIA |  | 20 | 8757184 | A project to replace the Hall Hill Road bridge over the Roeliff Jansen Kill in the Town of Ancram, Columbia County. | Bridge Replacement | 2010-03-24 | 2010-03-24 | 2011-01-31 | 2010-11-30 | 1355000 | 0.000 | 8757184
8483 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS |  | 19 | 8757253 | Rehabilitate the Lime Kiln Road bridge over the Ten Mile River in the Town of Dover, Dutchess County. The project will include cleaning and painting bridge members, waterproofing the bridge deck, repairing concrete, and installing sidewalks and guide rail | Bridge Improvement | 2009-09-24 | 2009-09-24 | 2012-02-01 |  | 1610100 | 0.020 | 8757253
8484 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | COLUMBIA |  | 20 | 8757613 | A project to replace the Empire Road bridge over the Roeliff Jansen Kill in the Town of Copake, Columbia County. | Bridge Replacement | 2010-03-24 | 2010-03-24 | 2011-01-31 |  | 1057000 | 0.000 | 8757613
8485 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | POUGHKEEPSIE-NEWBURGH | 18 | 8757723 | Replace the Odell Avenue Bridge over abandoned railroad tracks in the City of Yonkers, Westchester County. | Bridge Replacement | 2009-04-01 | 2009-04-01 | 2010-03-30 | 2010-05-26 | 1619219 | 0.020 | 8757723
8486 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 17 | 8757733 | Replace the South First Avenue Bridge over the Metro-North Railroad tracks in the City of Mount Vernon, Westchester County. | Bridge Replacement | 2009-09-08 | 2009-09-08 | 2011-04-12 | 2011-04-13 | 7616157 | 0.000 | 8757733
8487 | NEW YORK | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 22 | 8757873 | A project to replace the Hoffman Street bridge over Metro-North Railroad in the City of Poughkeepsie, Dutchess County. | Bridge Replacement | 2010-06-30 | 2010-06-30 | 2013-01-31 |  | 9939683 | 0.000 | 8757873
8488 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE |  | 22 | 8757933 | Replace the Petticoate Lane bridge over the Shawagunkill in the Town of Crawford, Orange County. (BIN 3344340) | Bridge Replacement | 2010-04-15 | 2010-04-15 | 2010-10-29 |  | 1396000 | 0.000 | 8757933
8489 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8758023 | Rehabilitate the Beckley Drive bridge over the Fantine Kill in the Town of Wawarsing, Ulster County. | Bridge Replacement | 2010-04-19 | 2010-04-19 | 2010-10-29 | 2010-10-15 | 1135000 | 0.000 | 8758023
8490 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8759123 | Provide new pavement markings along select highways throughout Dutchess County. The new pavement markings will improve roadway safety by increasing their reflectivity and better delineating the travel lanes. | Other | 2009-09-25 | 2009-09-25 | 2011-11-30 | 2011-11-07 | 644492 | 0.000 | 8759123
8491 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8759143 | A project for a new/improved bicycle facility on the Hudson Valley Rail Trail from Haviland Road to Commercial Avenue in the town of Lloyd. | Transportation Enhancements | 2010-03-30 | 2010-03-30 | 2011-12-13 | 2010-12-15 | 2610000 | 0.000 | 8759143
8492 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 19 | 8759163 | Construction of a Park and Ride lot in the Village of Kiryas Joel. | Transportation Enhancements | 2009-12-29 | 2009-12-29 | 2012-04-13 | 2011-07-01 | 1452194 | 0.000 | 8759163
8493 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | POUGHKEEPSIE-NEWBURGH | 19 | 8759473 | A project to improve East Shore Road in the Town of Warwick, Orange County. Pavement, drainage and retaining wall improvements will be made as part of the project. | Pavement Widening | 2010-03-11 | 2010-03-11 | 2011-01-31 |  | 839000 | 0.000 | 8759473
8494 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 19 | 8759493 | Phase 6 of a project to provide new sidewalks and rehabilitate existing sidewalks in the Village of Kiryas Joel, Orange County . The project will improve pedestrian access and safety. | Other | 2010-04-12 | 2010-04-12 | 2011-01-31 | 2010-08-12 | 501000 | 0.000 | 8759493
8495 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8759793 | A project to perform pavement rehabilitation along County Roads 27, 93, 114, 35 and 77 in the towns of East Fishkill, Fishkill, Wappingers Falls and Poughkeepsie, Dutchess County. | Pavement Improvement | 2010-02-02 | 2010-02-02 | 2010-11-30 | 2010-10-30 | 3387957 | 0.000 | 8759793
8496 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8760193 | Construct a pedestrian walkway along the Rondout Creek waterfront from Ravine Street to Route 9W in the City of Kingston, Ulster County. The project will build approximately .25 miles of walkway and 400 feet of bulkhead along the creek. | Transportation Enhancements | 2009-09-16 | 2009-09-16 | 2010-04-29 | 2010-04-27 | 200000 | 0.000 | 8760193
8497 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 19 | 8760533 | Improve intersection lighting along the Bronx River Parkway in Westchester County. The intersections include Virginia Road, Parkway Holmes Road, Fisher Lane, Old Tarrytown Road, and Strathmore Road. | Other | 2009-08-17 | 2009-08-17 | 2010-06-30 | 2010-07-31 | 320294 | 0.000 | 8760533
8498 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760543 | Upgrade 60 traffic signals at select locations in Westchester County. | Other | 2009-08-17 | 2009-08-17 | 2010-06-30 | 2010-07-31 | 301001 | 0.000 | 8760543
8499 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760553 | Install an automated traffic management system on the Bronx River Parkway in Westchester County. The new system will include in-pavement vehicle detectors capable of monitoring traffic volume and speed. | Other | 2009-08-17 | 2009-08-17 | 2009-12-31 | 2010-07-31 | 579151 | 0.000 | 8760553
8500 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760563 | Replace guide rail at select locations in Westchester County. | Other | 2009-08-17 | 2009-08-17 | 2010-01-29 | 2010-07-22 | 862118 | 0.000 | 8760563
8501 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760573 | A project to paint 10 local bridges at select locations throughout Rockland County. | Bridge Improvement | 2010-03-18 | 2010-03-18 | 2010-09-29 | 2010-09-29 | 831565 | 0.000 | 8760573
8502 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760583 | Replace roadside guiderail at select locations on local roadways throughout Rockland County. | Other | 2009-09-23 | 2009-09-23 | 2010-10-08 | 2010-10-08 | 600395 | 0.000 | 8760583
8503 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | Multiple | 8760593 | Upgrade and modernize existing traffic and pedestrian signal equipment in the City of Yonkers, Westchester County. | Safety/Traffic Management | 2009-09-23 | 2009-09-23 | 2010-07-02 | 2010-08-31 | 865904 | 0.000 | 8760593
8504 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760623 | A project to rehabilitate Creek Road pavement from the Poughkeepsie city line to Cottage Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 2010-04-07 | 2010-04-07 | 2011-01-31 | 2011-08-15 | 1479667 | 0.000 | 8760623
8505 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760653 | Rehabilitate the pavement along Buckingham Avenue from East Cedar Street to Fulton Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2009-12-31 | 2010-10-26 | 180898 | 0.000 | 8760653
8506 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760663 | Rehabilitate the pavement along Fairview Avenue from the Poughkeepsie city line to Fulton Street in the Town of Poughkeepsie, Dutchess County. | Pavement Improvement | 2010-04-07 | 2010-04-07 | 2011-05-02 | 2010-10-26 | 617000 | 0.000 | 8760663
8507 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 19 | 8760683 | Orange County Paving | Pavement Improvement | 2010-02-23 | 2010-02-23 | 2011-10-03 |  | 2641829 | 0.000 | 8760683
8508 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 19 | 8760803 | A project to repave Peenpack Trail in the Town of Deerpark, Orange County. | Transportation Enhancements | 2009-12-21 | 2009-12-21 | 2011-10-03 | 2010-09-10 | 310140 | 0.000 | 8760803
8509 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 22 | 8760813 | Paint 20 bridges at select locations throughout Orange County. This preventative-maintenance project will enhance the bridges structural integrity. | Bridge Improvement | 2010-05-03 | 2010-05-03 | 2010-07-22 | 2010-07-22 | 655283 | 0.000 | 8760813
8510 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ROCKLAND | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760833 | Resurface select local roadways throughout the Town of Clarkstown, Rockland County. | Pavement Improvement | 2009-10-07 | 2009-10-07 | 2010-09-30 | 2010-03-19 | 618689 | 0.000 | 8760833
8511 | NEW YORK | Underway | C230 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8760843 | A sidewalk/pedestrian improvement project throughout the city of Rye in Westchester County. Includes work on sidewalks, pedestrian signals, and curb cuts. | Safety/Traffic Management | 2010-03-22 | 2010-03-22 | 2011-01-31 |  | 678000 | 0.000 | 8760843
8512 | NEW YORK | Completed | C230 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 19 | 8760853 | A pavement rehabilitation project on Sheafe Road, from South Road to Channingville Road, in the town of Poughkeepsie. | Pavement Improvement | 2010-04-07 | 2010-04-07 | 2011-10-03 | 2010-07-20 | 761784 | 0.000 | 8760853
8513 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8780383 | Construction of Sidewalks along Route 44/55 in Gardiner | Transportation Enhancements | 2010-02-02 |  | 2012-03-30 |  | 893000 | 0.140 | 8780383
8514 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | 22 | 8780423 | $2.4 million in ARRA funding for an enhancement project to construct a single-shaft elevator and a stairway from ground level to the Walkway Over the Hudson bridge near Water Street in the city of Poughkeepsie, Dutchess County. Construction is e | Transportation Enhancements | 2009-07-16 |  | 2010-12-31 |  | 2400000 | 0.000 | 8780423
8515 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | POUGHKEEPSIE-NEWBURGH |  | 8809883 | Paint the steel superstructure of four bridges and provide localized, spot painting on 57 other bridges along Interstate 84 in Dutchess, Putnam, and Orange counties. This preventative-maintenance project will preserve the bridges structural integrity. | Bridge Improvement | 2010-08-06 | 2010-08-06 | 2012-06-15 | 2012-06-15 | 1870000 | 0.000 | 8809883
8516 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 18 | 8810893 | Provide much-needed general maintenance of 18 bridges along Interstate 684 in Westchester County, helping to extend the service life of the structures. | Bridge Improvement | 2009-06-30 | 2009-06-30 | 2012-03-05 | 2011-09-09 | 14958837 | 0.000 | 8810893
8517 | NEW YORK | Completed | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | STATEWIDE |  | 8810903 | Repave approximately 18 miles of state roadway in Columbia, Dutchess and Putnam counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings to extend the service life of pavement. | Pavement Improvement | 2009-06-18 | 2009-06-18 | 2011-04-12 | 2009-12-28 | 5493732 | 11.120 | 8810903
8518 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 8810993 | Repave approximately 22 miles of state roadway in Orange and Ulster counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings to extend the service life of pavement. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-09-23 | 2010-01-15 | 4398529 | 10.060 | 8810993
8519 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | 8811003 | Repave approximately 34 miles of state roadway in Westchester and Rockland counties. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings to extend the service life of pavement. | Pavement Improvement | 2009-06-10 | 2009-06-10 | 2010-05-12 | 2009-12-18 | 5680674 | 14.370 | 8811003
8520 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | WESTCHESTER | NEW YORK-NORTHEASTERN NJ (NJ) | 19 | 8811123 | Pavement Resurfacing on the Taconic State Parkway Southbound | Pavement Improvement | 2009-09-18 | 2009-09-18 | 2010-09-14 | 2010-05-17 | 4099359 | 3.300 | 8811123
8521 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DUTCHESS | POUGHKEEPSIE-NEWBURGH | Multiple | 8811283 | A preventative maintenance project in Dutchess County on Rt 44/55 AND RT 9G. | Pavement Improvement | 2010-02-25 | 2010-02-25 | 2010-12-31 | 2010-12-31 | 4389924 | 7.170 | 8811283
8522 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8811293 | Repave approximately four miles of Route 28 between Route 212 and Route 214 in the Town of Shandaken, Ulster County. The top layer of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement markings to extend the servi | Pavement Improvement | 2009-07-23 | 2009-07-23 | 2010-03-04 | 2009-10-15 | 1406523 | 3.430 | 8811293
8523 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ORANGE | NEWBURGH | 22 | 8811303 | Rebuild existing sidewalks and curb ramps along South Street from Dubois Street to Liberty Street in the City of Newburgh, Orange County. The project will improve pedestrian access and safety. | Safety/Traffic Management | 2009-11-11 | 2009-11-11 | 2010-11-05 | 2010-11-05 | 317000 | 0.240 | 8811303
8524 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | ULSTER |  | 22 | 8811363 | A pavement resurfacing project on Rt 28 from Route 375 to Route 28A and Route 214 to Delaware County line in towns of Hurley, Olive, and Shandaken. | Pavement Improvement | 2010-03-10 | 2010-03-10 | 2011-08-16 | 2010-11-03 | 7008723 | 22.900 | 8811363
8525 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9009253 | A TEP pedestrian safety project along State Route 7 in the town of Cobleskill, Schoharie County. The project will add new sidewalks, bicycle facilities, crosswalks, traffic signals, and a landscaped median along Route State 7 in front of the State Univers | Transportation Enhancements | 2011-09-09 | 2011-09-09 | 2011-11-30 |  | 1403841 | 0.500 | 9009253
8526 | NEW YORK | Underway | C220 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9009273 | A TEP project to construct new pedestrian facilities and a scenic overlook to provide pedestrian access to the waterfront in the village of Hancock, Delaware County. | Transportation Enhancements | 2012-04-30 | 2012-04-30 | 2012-09-19 |  | 564000 | 0.570 | 9009273
8527 | NEW YORK | Completed | C220 | Highway Infrastructure Investment Grant | NEW YORK | SULLIVAN |  | 22 | 9009283 | A TEP project to construct pedestrian facilities in the village of Monticello, Sullivan County. The project will include repairing existing sidewalk and building new sidewalk to connect residential areas, businesses, and the Monticello Central School. | Transportation Enhancements | 2010-11-30 | 2010-11-30 | 2011-07-27 | 2011-07-27 | 273885 | 0.500 | 9009283
8528 | NEW YORK | Underway | C220,C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME |  | 22 | 9009293 | Construct a new multi-use trail between Main St. and Castle Gardens in the Town of Vestal, Broome county. | Transportation Enhancements | 2009-07-01 |  | 2013-03-08 |  | 1803000 | 0.000 | 9009293
8529 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9014463 | This project will use a Mill and Fill treatment to resurface this section of Route 206 in the Town of Walton. | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2010-11-30 | 2010-10-23 | 1075000 | 4.330 | 9014463
8530 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9028103 | This project will resurface sections of Rtes. 23 and 30 in the Village of Grand Gorge | Pavement Improvement | 2010-05-24 | 2010-05-24 | 2012-11-30 | 2010-10-28 | 135000 | 0.710 | 9028103
8531 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | TIOGA | BINGHAMTON | 22 | 9038193 | Resurface State Route 434 from the Court Street Bridge to the eastern intersection with Marshland Road in the Village and Town of Owego, Tioga County. This project will improve 11 miles of pavement, replace one traffic signal, and upgrade guide railing. | Pavement Improvement | 2009-09-30 | 2009-09-30 | 2010-08-26 | 2010-08-26 | 5255867 | 11.080 | 9038193
8532 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TIOGA | BINGHAMTON | 24 | 9067323 | Resurface State Route 17 between Pumpelly Creek in the Village of Owego and the Broome County line in the Town of Owego, Tioga County.The top layer of 42 miles of worn, deteriorated pavement will be removed and replaced with new asphalt and fresh pavement | Pavement Improvement | 2009-08-31 | 2009-08-31 | 2010-08-13 | 2010-08-13 | 8047442 | 10.590 | 9067323
8533 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | TIOGA |  | 22 | 9067333 | Resurface State Route 17 between the Chemung County Line and Sackett's Creel in the Village of Waverly and towns of Barton and Nichols, Tioga County. This project will improve 40 miles of pavement, rehabilitate eight large culverts and upgrade guide raili | Pavement Improvement | 2009-09-04 | 2009-09-04 | 2010-07-21 | 2010-07-21 | 5579038 | 10.000 | 9067333
8534 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | BROOME |  | 22 | 9067343 | Resurface 18 miles of State Route 17 in the Town of Windsor in Broome County. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-05-28 | 2010-05-28 | 1815137 | 4.460 | 9067343
8535 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9125083 | This project will resurface this section of Rtes. 30A and 20 to restore the riding surface in the Town of Esperance. | Pavement Improvement | 2010-06-10 | 2010-06-10 | 2010-08-20 | 2010-06-16 | 207659 | 1.830 | 9125083
8536 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9358093 | Rehabilitate approaches to seven bridges carrying Interstate 88 in Schoharie County. Guide rail will also be improved at these locations. | Bridge Improvement | 2009-07-28 | 2009-07-28 | 2010-10-13 | 2010-10-13 | 2165328 | 0.000 | 9358093
8537 | NEW YORK | Completed | C250,C240 | Highway Infrastructure Investment Grant | NEW YORK | CHENANGO |  | 24 | 9752543 | Replace the bridge carrying County Route 34 over Johnson Creek in the Town of Norwich, Chenango County. | Bridge Replacement | 2009-09-14 | 2009-09-14 | 2010-06-15 | 2010-06-15 | 921802 | 0.000 | 9752543
8538 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753413 | Paint the bridge carrying County Route 48 over the Susquehanna River in the Town of Vestal and Village of Endicott, Broome County. | Bridge Improvement | 2010-04-13 | 2010-04-13 | 2010-06-29 | 2010-06-18 | 2535000 | 0.000 | 9753413
8539 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753423 | Rehabilitee the bridge carrying Arch Street over the Norfolk-Southern Railroad in the Village of Johnson City, Broome County. | Bridge Improvement | 2009-09-30 | 2009-09-30 | 2010-10-14 | 2010-02-17 | 72811 | 0.000 | 9753423
8540 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753433 | A project to culvert replacement project on Barlow Road over Acre Creek in the Town of Kirkwood, Broome County. | Other | 2010-05-01 | 2010-05-01 | 2010-08-11 | 2010-06-30 | 207000 | 0.000 | 9753433
8541 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | TIOGA | BINGHAMTON | 24 | 9753443 | Replace the bridge carrying South side Drive over Pumpelly Creek in the town and village of Owego, Tioga County. | Bridge Replacement | 2010-04-15 | 2010-04-15 | 2010-11-17 | 2010-11-17 | 1500000 | 0.000 | 9753443
8542 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME |  | 22 | 9753453 | A project to replace the bridge carrying Mason Road over Tracey Creek in the Town of Vestal, Broome County. | Bridge Replacement | 2010-02-11 | 2010-02-11 | 2010-08-12 | 2010-10-30 | 560000 | 0.000 | 9753453
8543 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME |  | 22 | 9753463 | Resurface County Route 44, Vestal Road, from Jensen Road to Orchid Street in the Town of Vestal, Broome County. | Pavement Improvement | 2010-03-05 | 2010-03-05 | 2010-09-01 | 2010-06-02 | 346000 | 0.000 | 9753463
8544 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753473 | Resurface Main Street from Front Street to the western city line in the City of Binghamton, Broome County. | Pavement Improvement | 2009-09-30 | 2009-09-30 | 2009-11-23 | 2009-12-03 | 734602 | 1.670 | 9753473
8545 | NEW YORK | Underway | C200 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9753483 | A project to resurface Vestal Avenue from the Vestal-Endicott Bridge to East Main Street in the Village of Endicott, Broome County. | Pavement Improvement | 2010-01-26 | 2010-01-26 | 2010-08-06 |  | 51542 | 0.000 | 9753483
8546 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9753493 | Resurface approximately one mile of County Route 7 from the Sullivan County line to Beaver Kill Road in the Town of Colchester, Delaware County. | Pavement Improvement | 2009-09-10 | 2009-09-10 | 2009-07-30 | 2009-09-24 | 330050 | 0.950 | 9753493
8547 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9753503 | Resurface County Route 21 from Leland Hull Road to Oak Hill Road in the Town of Franklin, Delaware County. | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2010-08-09 | 2010-08-09 | 476995 | 0.000 | 9753503
8548 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CHENANGO |  | 24 | 9753513 | Install new signage on County Routes 5, 10A, 25, 32, 32A, 32B, 33, 34, 35, 36 and 44 in Chenango County. | Safety/Traffic Management | 2009-07-27 | 2009-07-27 | 2010-06-01 | 2009-11-16 | 127758 | 0.000 | 9753513
8549 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 24 | 9753523 | Highway Resurfacing on County Route 31, Springfield Hill Road to Route 20, Town of Springfield. | Pavement Improvement | 2010-06-01 | 2010-06-01 | 2010-08-31 | 2010-09-23 | 331252 | 0.000 | 9753523
8550 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 20 | 9753533 | Highway Resurfacing on County Route 33, Village of Cooperstown to Route 166, Town of Middlefield. | Pavement Improvement | 2009-09-16 | 2009-09-16 | 2009-10-26 | 2009-10-26 | 751843 | 0.000 | 9753533
8551 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SULLIVAN |  | 22 | 9753543 | Paint 22 local bridges in Sullivan County. | Bridge Improvement | 2009-09-17 | 2009-09-17 | 2010-09-01 | 2010-09-01 | 2160608 | 0.000 | 9753543
8552 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 24 | 9753553 | A project to rehabilitate the bridge carrying Spring Street in the Town of Butternuts, Otsego County. | Bridge Improvement | 2010-06-30 | 2010-06-30 | 2010-09-03 | 2010-09-06 | 420000 | 0.000 | 9753553
8553 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9753563 | Repave nearly 10 miles of County Route 1, Mineral Springs Road, in the Town of Richmondville and the Town and Village of Cobleskill, Schoharie County. | Pavement Improvement | 2009-09-23 | 2009-09-23 | 2010-01-29 | 2009-12-31 | 1112996 | 0.000 | 9753563
8554 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SULLIVAN |  | 22 | 9753573 | Replace approximately 132 signs on various county roads in Sullivan County. | Other | 2009-10-20 | 2009-10-20 | 2010-01-07 | 2009-12-18 | 91995 | 0.000 | 9753573
8555 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SULLIVAN |  | 22 | 9753583 | Upgrade five traffic signals in the towns of Fallsburg, Highland, Rockland and Tusten in Sullivan County. | Safety/Traffic Management | 2009-10-12 | 2009-10-12 | 2009-12-23 | 2009-12-23 | 119458 | 0.000 | 9753583
8556 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9753591 | Culvert replacement project on County Route 8 in the Town of Cobleskill, Schoharie County. | Other | 2009-09-23 | 2009-09-23 | 2010-03-18 | 2010-07-30 | 28355 | 0.000 | 9753591
8557 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | SCHOHARIE |  | 21 | 9753593 | Culvert replacement project on County Route 8 in the Town of Cobleskill, Schoharie County. | Pavement Improvement | 2009-09-23 | 2009-09-23 | 2010-03-18 | 2010-07-30 | 238837 | 0.000 | 9753593
8558 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 24 | 9753643 | A project to resurface East Street from Irving Place to Graduate Avenue in the City of Oneonta, Otsego County. | Pavement Improvement | 2010-07-12 | 2010-07-12 | 2010-08-12 | 2010-08-11 | 200000 | 0.000 | 9753643
8559 | NEW YORK | Completed | C200 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 24 | 9753653 | A project to resurface Grand Street from Division Street to Main Street and Division Street from James Georgeson Avenue to Grand Street in the City of Oneonta, Otsego County. | Pavement Improvement | 2010-07-27 | 2010-07-27 | 2010-08-12 | 2010-08-11 | 106000 | 0.000 | 9753653
8560 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9753663 | Rehabilitation of CR 21 in the Town of Franklin | Pavement Improvement | 2010-03-11 | 2010-03-11 | 2010-08-13 | 2010-08-13 | 394524 | 0.000 | 9753663
8561 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | CHENANGO |  | 24 | 9753673 | Rehabilitation of CR 44 within the Towns of N. Norwich and Plymouth | Pavement Improvement | 2010-05-15 | 2010-05-15 | 2010-05-19 | 2010-05-19 | 266125 | 0.000 | 9753673
8562 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | OTSEGO |  | 23 | 9805603 | Rehabilitate twelve culverts along Interstate 88 in the Towns of Otego, Oneonta, Milford and Maryland, Otsego County. | Pavement Improvement | 2009-08-04 | 2009-08-04 | 2010-11-30 | 2010-11-30 | 3038177 | 81.930 | 9805603
8563 | NEW YORK | Completed | C200,C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | BINGHAMTON |  | 9805633 | Paint 25 bridges on State Route 17 in Broome and Tioga counties in the towns of Vestal, Candor, Nichols, Barton and the Village of Waverly. The work will be entirely funded by ARRA. Bridge painting helps to preserve the structural integrity and delay dete | Bridge Improvement | 2009-07-27 | 2009-07-27 | 2010-11-15 | 2010-11-15 | 7342928 | 0.000 | 9805633
8564 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 9805643 | Replace signage on state highways in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. Signs that are no longer in compliance with federal and state standards will be updated. | Safety/Traffic Management | 2009-08-12 | 2009-08-12 | 2010-08-31 | 2010-08-31 | 839624 | 0.000 | 9805643
8565 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BROOME | BINGHAMTON | 22 | 9805653 | Bring sidewalks and curbs at select locations in the Town of Union and the villages of Johnson City and Endicott, Broome County, into compliance with Americans with Disabilities Act guidelines. | Safety/Traffic Management | 2009-07-21 | 2009-07-21 | 2009-11-30 | 2010-05-28 | 505195 | 0.000 | 9805653
8566 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 9805663 | Perform bridge maintenance at various locations in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. The projects will be entirely funded by ARRA. This work includes repairs to bridge elements such as bridge joints, bearings, app | Bridge Improvement | 2009-08-26 | 2009-08-26 | 2010-10-20 | 2010-10-20 | 1000000 | 0.000 | 9805663
8567 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 9805673 | Perform bridge maintenance at various locations in Broome, Chenango, Delaware, Otsego, Schoharie, Sullivan and Tioga counties. The projects will be entirely funded by ARRA. This work includes repairs to bridge elements such as bridge joints, bearings, app | Other | 2009-08-26 | 2009-08-26 | 2010-10-20 | 2010-10-20 | 1084624 | 0.000 | 9805673
8568 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | DELAWARE |  | 20 | 9805713 | Remove hazardous trees in south Delaware County. Removal of these trees will increase safety for the traveling public. | Safety/Traffic Management | 2009-07-23 | 2009-07-23 | 2009-08-07 | 2009-08-07 | 574326 | 0.000 | 9805713
8569 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | 9805813 | A project to remove and replace curb ramps and sidewalks that are not in compliance with the Americans With Disabilities Act. | Safety/Traffic Management | 2010-02-12 | 2010-02-12 | 2010-11-18 | 2010-11-18 | 421752 | 0.000 | 9805813
8570 | NEW YORK | Completed | C490 | OJT/SS | NEW YORK | STATEWIDE |  |  | CRBU012 | The Youth Construction Initiative Program provides on the job training in hard and soft skills necessary for a career in construction to vocation oriented 11th and 12th graders. The program is located in eight schools from Buffalo to Newburgh | Other | 2010-09-15 | 2010-09-15 |  | 2011-11-30 | 1354794 |  | CRBU012
8571 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X731303 | A project to improve access on the Staten Island Expressway (I-278) between the Verrazano Narrows Bridge toll plaza and Renwick Avenue in Richmond County. Improvements will include the construction of five new ramps, relocation of two ramps, reconfigurat | Bridge Replacement | 2010-06-24 | 2010-06-24 | 2013-10-31 |  | 39793056 | 1.150 | X731303
8572 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | X751064 | Rehabilitate the Brooklyn Bridge in Kings and New York counties. The project will repair and widen the ramps leading to the bridge in Brooklyn and Manhattan and the entire bridge will be repainted. The impr ovements to the ramps, which are in poor conditi | Bridge Improvement | 2010-01-29 | 2010-01-29 | 2014-04-22 |  | 30000000 | 0.000 | X751064
8573 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | QUEENS | NEW YORK-NORTHEASTERN NJ (NJ) | 12 | X770613 | Rehabilitation of the Greenpoint Avenue Bridge over Newton Creek In Kings County. The project will replace deteriorated bridge deck material with a light weight grid deck. Replacement of cracked members, joints and the resurfacing of the approach pavemen | Bridge Improvement | 2010-04-05 | 2010-04-05 | 2011-02-03 | 2011-02-03 | 2500000 | 0.000 | X770613
8574 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BRONX | NEW YORK-NORTHEASTERN NJ (NJ) | 16 | X770623 | Painting and maintenance to extend the useful life of Bruckner Expressway Bridges in the Bronx County. | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2011-04-29 | 2011-04-29 | 3500000 | 0.000 | X770623
8575 | NEW YORK | Underway | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | X770633 | Rehabilitation of 12 concrete and steel bridges in Bronx, Kings, New York , Queens and Richmond counties. The work will include deck overlay, sidewalk improvements, joint sealing, painting, washing, upgrading piers and abutments, and crack sealing. | Bridge Improvement | 2010-05-10 | 2010-05-10 | 2013-05-06 |  | 2500000 | 0.000 | X770633
8576 | NEW YORK | Underway | C240,C230 | Highway Infrastructure Investment Grant | NEW YORK | NEW YORK | NEW YORK-NORTHEASTERN NJ (NJ) | 15 | X770643 | A project to mechanically and electrically rehabilitate the Wards Island pedestrian bridge. | Bridge Improvement | 2010-06-14 | 2010-06-14 | 2013-03-15 |  | 1500000 | 0.000 | X770643
8577 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | X805933 | Replace sign panels on highway s in Bronx, Kings, New York, Queens and Richmond counties. Approximately 150 overhead and 11 ground-mounted sign panels that are exhibiting deterioration, have lost reflectivity or do not meet required federal standards will | Safety/Traffic Management | 2009-10-20 | 2009-10-20 | 2011-07-31 | 2011-07-05 | 2206029 | 0.000 | X805933
8578 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | X806253 | Repair and resurface approximately 45 miles of pavement on highways in Bronx, New York and Queens counties. In Bronx County, work will be done on the Major Deegan Expressway southbound lanes from the Mosholu Parkway to Fordham Road and on the Bruckner Exp | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2012-01-31 | 2012-01-31 | 23100670 | 10.850 | X806253
8579 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X806383 | Park & Ride Lot Expansion at Huguenot Ave, Richmond County | Transportation Enhancements | 2009-10-01 | 2009-10-01 | 2010-10-15 | 2010-08-13 | 1965565 | 0.000 | X806383
8580 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | RICHMOND | NEW YORK-NORTHEASTERN NJ (NJ) | 13 | X806393 | Park & Ride Lot Expansion (Adding 159 Spaces) at Eltingville Transit Center- Richmond County | Other | 2009-09-07 | 2009-09-07 | 2010-09-09 | 2010-10-29 | 2475075 | 0.000 | X806393
8581 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE |  |  | X806463 | Repairs to Various State Highway Bridges- Richmond, Kings, Queens, New York and Bronx Counties | Bridge Improvement | 2009-10-20 | 2009-10-20 | 2012-12-31 | 2012-12-31 | 8426208 | 0.000 | X806463
8582 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | STATEWIDE | NEW YORK-NORTHEASTERN NJ (NJ) |  | X806533 | THIS PROJECT WILL REPLACE SIGN PANELS, OVERHEAD AND GROUND MOUNTED, IN POOR CONDITION ON STATE HIGHWAYS WITH PANELS CONFORMING TO THE MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES. | Safety/Traffic Management | 2009-12-23 | 2009-12-23 | 2011-04-29 | 2011-03-25 | 1714204 | 18.010 | X806533
8583 | NEW YORK | Underway | C950 | Ferryboat | NEW YORK | RICHMOND |  | 13 | X823343 | A project to rehabilitate and upgrade the Staten Island Ferry terminal and dock to improve safety, efficiency, and reliability. | Other | 2011-04-04 | 2011-04-04 | 2013-12-30 |  | 4000000 | 0.000 | X823343
8584 | NEW YORK | Completed | C240 | Highway Infrastructure Investment Grant | NEW YORK | BRONX |  | Multiple | XM09063 | Painting of South Bound Bruckner Expressway viaduct and ramps between RFK bridges and Sheridan Expressway to arrest the deterioration of the structure and extend its service life. | Bridge Improvement | 2010-04-14 | 2010-04-14 | 2012-07-02 | 2012-06-30 | 20000000 | 0.000 | XM09063
8585 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FRANKLIN |  | Multiple | 0001122 | This project will repave US 1 in Franklin County from Wake County line to NC 56 to improve road condition. Includes TIP project U-5125. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-10-30 | 2010-08-23 | 2072895 | 17.040 | 0001122
8586 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LEE |  | Multiple | 0001123 | This project will repave US 1 in Lee County from US 1 Business to Farrell Road to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-11-20 | 2010-03-29 | 2116024 | 10.220 | 0001123
8587 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MOORE |  | Multiple | 0001124 | This project will add paved shoulders on US 1 in Moore County from Morganton Road to Aiden Road to enhance safety. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-11-20 | 2011-04-20 | 1292031 | 16.370 | 0001124
8588 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | VANCE |  | 02 | 0001133 | This project will repave the following roadways in Vance County to improve road condition: US 1 in Kittrell, US 1/158 Business from Henderson to the Warren County line, NC 39 from Rock Springs Road to | Pavement Improvement | 2009-12-21 | 2010-06-02 | 2010-10-15 | 2011-02-10 | 2000000 | 24.050 | 0001133
8589 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 000S531 | Preliminary engineering to rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for motorists. | Other | 2009-04-29 | 2009-04-29 |  | 2010-03-03 | 325250 | 0.000 | 000S531
8590 | NORTH CAROLINA | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 02 | 000S533 | Construct the Neuse River Greenway in Smithfield which includes a ten foot paved greenway from Wake County Line to Sam's Branch parallel to the Neuse River in Johnston County. This section of greenwa | Transportation Enhancements | 2010-01-19 | 2010-06-16 | 2011-09-21 |  | 1519294 | 3.000 | 000S533
8591 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHOWAN |  | 01 | 000S534 | This project will clean and paint the structural steel on Bridge #26 over US 17 Bypass on SR 1234, Bridge #28 over US17 Bypass on SR 1319, Bridge #27 over NC 32 on US17 Bypass and Bridge #30 over the | Bridge Improvement | 2009-06-15 | 2009-06-15 | 2011-11-04 | 2011-10-27 | 517165 | 0.000 | 000S534
8592 | NORTH CAROLINA | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHOWAN |  | 01 | 000S536 | This project will relocate the lighthouse to a new foundation system, complete required hazardous material abatement, perform structural repairs, historic restoration and stabilization of the lighthou | Transportation Enhancements | 2009-06-15 | 2009-08-17 | 2010-10-06 |  | 841215 | 0.000 | 000S536
8593 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DAVIDSON |  | Multiple | 000S538 | This project will repave the following roadways in Davidson County to improve road condition: NC 62 from NC 109 to the Randolph County line, NC 109 from Denton Road to north of Ben Lee Road, NC 150 f | Pavement Improvement | 2009-05-22 | 2009-05-22 | 2009-11-01 | 2009-12-02 | 1784410 | 13.560 | 000S538
8594 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DAVIE |  | Multiple | 000S540 | This project will repave the following roadways in Davidson and Davie Counties to improve road condition: US 64 from Lake Louise Golf Course to east of the Yadkin River, US 64-601 from US 158 to US 6 | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2009-11-30 | 2010-10-26 | 3211948 | 18.436 | 000S540
8595 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROWAN |  | Multiple | 000S541 | This project will repave various roadways in Rowan County, including the following, to improve road condition: Section of US 52, Section of NC 150, Section of NC 152, Section of NC 801, Sections of 8 secondary roads. | Pavement Improvement | 2009-05-22 | 2009-05-22 | 2009-11-30 | 2011-01-24 | 4454164 | 38.693 | 000S541
8596 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STOKES |  | 05 | 000S542 | This project will repave various roadways in Stokes County, including the following, to improve road condition: US 52 from King City limits to Surry County line, Section of NC 65, Section of NC 66, Section of NC 2681 and Sections of 5 secondary roads. | Pavement Improvement | 2009-06-12 | 2009-06-12 | 2009-11-30 | 2011-04-15 | 3222130 | 31.790 | 000S542
8597 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 000S564 | This project will provide for upgrades for traffic signals including the replacement of incandescent bulbs with LED inserts in signal heads, upgrade of undersized signal heads with LED signal heads an | Safety/Traffic Management | 2009-10-19 | 2010-02-12 | 2010-09-30 |  | 532669 | 0.000 | 000S564
8598 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 000S568 | This project will repave Northwest Boulevard and construct sidewalk in Winston-Salem / Forsyth County to improve road condition and provide pedestrian accommodation. | Pavement Improvement | 2009-09-09 | 2009-09-09 | 2010-04-30 |  | 276738 | 0.000 | 000S568
8599 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HARNETT |  | 02 | 000S574 | The project (ER-5100F) will preliminary engineer Roadside Environmental Rehabilitation/Renovation projects in Highway Division 6 (Fayetteville). | Other | 2009-11-01 |  |  |  | 4270 | 0.000 | 000S574
8600 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE |  |  | 000S577 | These funds will provide the preliminary engineering for the project that will renovate the landscape enhancement for the I-85 Rest Area in Davidson County and the I-40/US-52 landscape initiative in Forsyth County. | Other | 2009-08-05 | 2009-08-05 |  |  | 4273 | 0.000 | 000S577
8601 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE |  |  | 000S582 | The project will install landscape enhancement planting in Columbus at the US 74 and I-26 Interchange in Polk County and at the intersection of US 64 and Jones Cove Road in Haywood County. | Transportation Enhancements | 2009-08-20 | 2010-01-12 | 2010-03-26 | 2010-05-25 | 94683 | 0.110 | 000S582
8602 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 000S588 | This project provides for the construction of a 10 foot multi-use asphalt trail including bridge over Jones Creek for the Twin Creeks Park Greenway in Orrange County. This is a locally administered project by Orange County. | Transportation Enhancements | 2009-09-22 | 2010-03-01 | 2010-08-26 | 2011-06-10 | 429457 | 0.000 | 000S588
8603 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 000S593 | Rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for motorists. | Bridge Improvement | 2009-08-12 | 2010-04-20 | 2010-08-15 | 2011-07-22 | 4109972 | 0.000 | 000S593
8604 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 000S594 | Rehabilitate bridge decks on I-26, I-240, US 25/70, Island Road, US 19/23 (future I-26), I-40 and SR 1001 to extend the life of the structures and improve ride quality for motorists. | Bridge Improvement | 2009-11-16 | 2010-06-28 | 2011-09-30 | 2012-09-11 | 7031435 | 0.000 | 000S594
8605 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 000S596 | This project will provide alternate fuel vehicles to serve homebound individuals or those with no personal means of transportation while promoting environmental health by reducing carbon emissions in | Other | 2009-11-17 | 2010-04-02 | 2011-10-31 |  | 736989 | 0.000 | 000S596
8606 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 000S597 | This project provides for the purchase of a transit bus fueled by compressed natural gas (CNG), and the construction of a CNG fueling station in Henderson County. | Other | 2009-08-31 | 2010-02-22 | 2010-09-20 |  | 641347 | 0.000 | 000S597
8607 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON |  | 11 | 000S605 | The project will install flowering tree seedlings for reforestation at the following locations: I-26 at US 25 in Henderson County, I-26 at US 74 in Polk County, US 64 from US 74 to NC 141 in Cherokee | Transportation Enhancements | 2009-09-09 | 2009-12-11 | 2010-02-26 | 2010-03-29 | 187531 | 11.370 | 000S605
8608 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 000S610 | The project (U-5195) will upgrade dynamic message signs at various locations in Forsyth county. | Safety/Traffic Management | 2009-12-17 | 2010-03-02 | 2010-10-01 | 2011-03-21 | 500000 | 0.000 | 000S610
8609 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE |  |  | 000S656 | ER-5100R - This Project Will Provide For (Statewide) Special Storm Water Management For Eroding Slopes Across North Carolina. | Transportation Enhancements | 2010-08-26 | 2010-10-28 | 2010-12-30 | 2011-01-04 | 20000 | 0.000 | 000S656
8610 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0011015 | This project will resurface NC 11 Business in Hertford County from NC 11 to the Aulander East City Limits to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2011-01-24 | 264966 | 2.100 | 0011015
8611 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0011017 | This project will resurface NC 11in Hertford County from SR 1130 (Modlin Hatchery Road) southward for 2.6 miles to the Bridge over Ahoskie Creek to improve road condition. | Pavement Improvement | 2010-01-04 | 2010-10-26 | 2011-06-30 | 2011-03-09 | 410604 | 2.600 | 0011017
8612 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0011018 | This project will clean and paint the structural steel on Bridge #39 over the Roanoke River on NC 11 in Martin County to extend the life of the structure. | Bridge Improvement | 2009-11-24 | 2010-03-17 | 2010-12-15 | 2010-10-05 | 400833 | 0.000 | 0011018
8613 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 0011020 | R-5220 - This Project Will Mill And Resurface NC 11/55 From The Neuse River Bridge To The Railroad Tracks in Lenoir County, North Carolina. | Pavement Improvement | 2010-08-05 | 2011-06-22 | 2011-08-19 | 2011-08-05 | 192500 | 0.400 | 0011020
8614 | NORTH CAROLINA | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HYDE |  | Multiple | 0012036 | This project will resurface NC 12 from the Northern Ferry Dock to Ocracoke Village in Hyde County to improve road condition. Widen paved shoulders to accommodate bicycles will be added on a 3.26 mile | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-08-20 | 2010-08-28 | 2271442 | 12.980 | 0012036
8615 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HYDE |  | Multiple | 0012037 | This project will construct a multi-use asphalt trail adjacent to NC 12 from Ocracoke Village to the National Park Service Campground in Hyde County to enhance pedestrian and bicycle access and safety. | Transportation Enhancements | 2009-06-15 | 2009-06-15 | 2010-08-20 | 2011-04-20 | 611594 | 3.100 | 0012037
8616 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | 03 | 0012039 | This project will resurface NC 12 from National Park Service Boundary South of Salvo to 8 miles south of the National Park Service Boundary in Dare County to improve road condition. | Pavement Improvement | 2010-01-12 | 2010-10-05 | 2011-06-11 | 2010-11-19 | 1000000 | 8.000 | 0012039
8617 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0013028 | This project will strengthen and resurface US 13 in Hertford County from SR 1130 (Modlin Hatchery Road) to NC 461 to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-10-30 | 2009-12-18 | 487951 | 4.200 | 0013028
8618 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0013029 | Replace deficient bridges #12 and #25 carrying US 13 over Ahoskie Creek and Ahoskie Creek Overflow in Hertford County. | Bridge Replacement | 2009-04-21 | 2009-04-21 | 2011-10-28 | 2011-10-27 | 3060409 | 0.230 | 0013029
8619 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0013031 | This project will resurface US 13-US 17 from the Roanoke River to Saint Francis Road in Bertie County to improve road condition. | Pavement Improvement | 2009-11-10 | 2010-04-05 | 2010-06-15 | 2010-08-31 | 1048436 | 4.920 | 0013031
8620 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0013032 | This project will level existing pavement and resurface US 13/US 17 in Bertie County from SR 1106( St. Francis Road) to SR 1102 (Pleasant Oak Road) to improve road condition. | Pavement Improvement | 2009-11-10 | 2010-04-05 | 2010-06-15 | 2010-08-31 | 786267 | 3.440 | 0013032
8621 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GREENE |  | 01 | 0013036 | R-5222 - This Project Will Mill and Resurface US 13-NC 903 In Snow Hill From NC 58 To NC 91 And Resurface SR1255 (N.W.Second Street) From US 13-NC 903 To US 258 In Greene County, North Carolina. | Pavement Improvement | 2010-08-16 | 2011-06-13 | 2011-08-19 | 2011-08-07 | 561591 | 1.690 | 0013036
8622 | NORTH CAROLINA | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GRANVILLE, ORANGE |  | Multiple | 0015020 | This project will repave US 15 in Granville County from Tar River Road south of Oxford to Industry Drive in Oxford to improve road condition. | Pavement Improvement | 2009-11-16 | 2010-08-11 | 2010-10-15 | 2011-04-26 | 3075347 | 8.630 | 0015020
8623 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0015026 | Thie project provides for the construciton of the Morgan Creek Greenway, Phase I, to improve pedestrian access from US 15/501 (Culbeth Road) to Smith Level Road in Orange County. This project is locally administered by Orange County. | Transportation Enhancements | 2009-10-14 | 2010-03-01 | 2011-03-01 |  | 347488 | 0.000 | 0015026
8624 | NORTH CAROLINA | Underway | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHATHAM | DURHAM | Multiple | 0015027 | Preliminary engineering for pedestrian enhancements to traffic signals and sidewalks on East and/or the west side of US 15-501 in the Cole Park area north to the Orange County line using the existing | Transportation Enhancements | 2009-06-23 | 2009-07-09 | 2010-06-15 |  | 145077 | 2.338 | 0015027
8625 | NORTH CAROLINA | Underway | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHATHAM | DURHAM | Multiple | 0015028 | This project will renovate the existing landscape enhancement US 421 & US 64 in Chatham County. | Transportation Enhancements | 2009-06-23 | 2009-07-09 | 2010-06-15 |  | 29009 | 2.338 | 0015028
8626 | NORTH CAROLINA | Underway | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0015029 | This projet provides for the construction of sidewalk ro increase pedestrain safety and mobility on US 15/501/NC 54 from SR 1902 (Manning Drive) to Old Mason Farm Road in Orange County. This is a locally administered project by the Town of Chapel Hill. | Transportation Enhancements | 2009-09-21 | 2010-01-13 | 2010-06-24 |  | 142613 | 0.280 | 0015029
8627 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0015030 | The project (R-5164C) will resurface US 15/501 Business south from NC 98 to US 15/501 Business; US 15/501 Business north from US 15/501 to NC 98, US 15/501 Business from US 15/501 to SR 1361 (Vickers | Pavement Improvement | 2009-12-17 | 2010-05-19 | 2010-09-15 | 2010-12-10 | 960790 | 2.900 | 0015030
8628 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0015031 | The project (ER-5100GE) will provide plantings on US 15/501 at Erwin Road/Europa Drive intersection in Orange county. | Transportation Enhancements | 2009-11-10 |  | 2012-04-30 | 2012-04-30 | 40540 | 0.000 | 0015031
8629 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0016045 | This project inlcudes landscaping on NC 16 within construction project limits from South of SR 2948 (Marvin School Road) in Uniton County to South of I-185 in Mecklenburg County to enhance aesthetics of the roadway. | Transportation Enhancements | 2009-04-10 | 2011-02-03 | 2011-03-18 |  | 73664 | 3.350 | 0016045
8630 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION | CHARLOTTE | Multiple | 0016046 | This project includes turning lane radius improvements, traffic signal upgrades and a railroad crossing upgrade in Waxhaw on NC 16 at the NC 75 intersection to improve intersection operations and safe | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2010-09-17 |  | 689768 | 0.000 | 0016046
8631 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILKES |  | 05 | 0016047 | This project will rehabilitate pavement and improve guardrail on NC 16 N from SR 1559 (Old NC 16) to the Ashe County line in Wilkes County to improve road condition and safety. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-31 | 2010-08-23 | 1652051 | 9.350 | 0016047
8632 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ASHE |  | 05 | 0016048 | This project will rehabilitate pavement and improve guardrail on NC 16 from NC 88 to the Virginia line in Ashe County to improve road condition and safety. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2009-12-31 |  | 2311563 | 13.125 | 0016048
8633 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0017089 | This project will mill asphalt from existing pavement and resurface US 17 Business in Williamston from NC 125 to 0.7 miles east to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2009-12-02 | 190643 | 0.660 | 0017089
8634 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PERQUIMANS |  | 01 | 0017090 | This project will resurface US 17 in Perquimans County from SR 1101 (Bear Swamp Road) to SR 1302 (Union Hall Road) to improve road condition. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2012-11-16 |  | 2648375 | 15.400 | 0017090
8635 | NORTH CAROLINA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER, BRUNSWICK |  | 07 | 0017097 | Construct US 17 Bypass (Future I-140) from NC 87 to US 74-76 in Brunswick County. Route will be a four lane divided freeway to alleviate congestion on surrounding roadways. | New Bridge Construction | 2009-10-13 | 2010-03-29 | 2013-10-15 |  | 14725487 | 6.100 | 0017097
8636 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PASQUOTANK |  | 01 | 0017098 | This project will resurface four sections of the US 17 Bypass of Elizabeth City to eliminate ponding of water on roadway and improve safety conditions.. | Pavement Improvement | 2009-11-24 | 2010-09-14 | 2010-10-01 | 2010-09-24 | 231511 | 2.300 | 0017098
8637 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PASQUOTANK |  | 01 | 0017100 | The project (ER-5100AC) will provide reforestation on US 17 (Elizabeth City Bypass) in Pasquotank county. | Transportation Enhancements | 2009-10-28 | 2010-12-13 | 2010-12-31 | 2010-12-22 | 42000 | 7.400 | 0017100
8638 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROBESON |  | 07 | 0017101 | The project will renovate and improve existing landscape enhancement in Maxton at the NC 71 and I-74 Interchange in Robeson County | Transportation Enhancements | 2009-09-24 | 2010-03-03 | 2010-04-30 | 2010-05-09 | 61654 | 0.000 | 0017101
8639 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PASQUOTANK |  | 01 | 0017104 | ER-5100AE - This project will provide Czip Planting at the US 17 Bypass/US 17 Interchange in Pasquotank County, North Carolina. | Transportation Enhancements | 2010-02-09 |  |  | 2011-12-31 | 85500 | 0.000 | 0017104
8640 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PERQUIMANS |  | 01 | 0017105 | The project (ER-5100AF) will repair critical eroding slopes on US 17 in Perquimans county. | Transportation Enhancements | 2009-11-24 |  | 2011-07-30 |  | 138333 | 30.376 | 0017105
8641 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0017106 | B-4576 - Replace Bridge #6 On US 17 Southbound Over Ready Branch in Martin County, North Carolina. | Bridge Replacement | 2010-02-18 | 2010-07-30 | 2011-11-30 | 2011-10-18 | 1185000 | 0.000 | 0017106
8642 | NORTH CAROLINA | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ONSLOW |  | 03 | 0017111 | U-4007B - This project will add additional turn lanes by improving grading, drainage, paving, structures, signal, retaining wall, and culvert extension on Western Parkway from 1300 feet South of Count | Pavement Widening | 2010-09-14 | 2010-12-17 | 2013-09-15 |  | 11421295 | 2.014 | 0017111
8643 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALLEGHANY |  | 05 | 0018014 | This project will add a left turn lane on NC 18 from SR 1173 (Tayson Rd) to SR 1138 (Osborne Rd) and realign Osborne Rd to improve safety and mobility. | Pavement Improvement | 2010-03-15 | 2010-04-07 | 2010-08-15 | 2011-01-24 | 408783 | 0.540 | 0018014
8644 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MONTGOMERY |  | 08 | 0024036 | Widen NC 24-27 in Biscoe / Montgomery County, between US 220A and Future I-73/74, to enhance safety and mobility. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2011-08-01 | 2011-09-29 | 4541752 | 0.909 | 0024036
8645 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MOORE |  | Multiple | 0024037 | This project will widen NC 24-27 in Moore County and add turn lanes, from Montgomery County line to NC 705, to enhance safety and mobility. | Pavement Widening | 2009-03-26 | 2009-03-26 | 2010-06-25 | 2011-05-10 | 3313779 | 9.400 | 0024037
8646 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0024038 | This project will inlcude landscaping in Albemarle within the construction project limits from East of Big Bear Creek to SR 1963 (St. Martin Road) to enhance aesthics when ,otorists enter the Albemarle city limits in Stanly County. | Transportation Enhancements | 2009-06-08 | 2010-11-17 | 2010-12-31 | 2011-02-10 | 85580 | 5.800 | 0024038
8647 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0024042 | This project includes resurfacing NC 740 from SR 1730 (Vickers Store Rd) to Island in Stanly County. Milling and resurfacing NC 24/27 from NC 740 to Bird St in Stanly County. Pavement rehabilitation | Pavement Improvement | 2009-11-17 |  | 2010-07-30 | 2011-01-24 | 1919233 | 7.280 | 0024042
8648 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DUPLIN, ONSLOW |  | 03 | 0024046 | R-5218 - This Project Will Mill And Resurface NC 24 From NC 24 Business-Kenansville Bypass In Duplin County To US 258 AT Jarman's Fork In Onslow County, North Carolina. | Pavement Improvement | 2010-08-23 | 2010-11-01 | 2012-11-12 | 2012-12-11 | 2238256 | 40.710 | 0024046
8649 | NORTH CAROLINA | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 0025025 | Preliminary engineering for the installation of trees, shrubs, and flowering plants as well as hardscape items and native grasses in Asheville on future I-26, Exit 23, interchange in Woodfin and I-2 | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2011-06-30 | 2011-05-07 | 214051 | 0.000 | 0025025
8650 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | 05 | 0029044 | This project will repair and rehabilitate concrete pavement and shoulders on US 29 in Rockingham County from Guilford County line to Troublesome Creek to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-10-16 | 2011-01-24 | 1712661 | 3.890 | 0029044
8651 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0029045 | Repair bridge expansion joints on 8 structures: Bridge 23 on US 29 Business, Bridge 116 on SR 2600, Bridge 134 on NC 700, Bridge 168 on NC 14/87, Bridge 169 on NC 770, Bridge 124 on SR 2177, Bridge 1 | Bridge Improvement | 2009-07-28 | 2009-12-29 | 2010-05-29 | 2010-03-04 | 109031 | 0.045 | 0029045
8652 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0029046 | The project will install landscape enhancement plantings in Greensboro on US 29 from SR 4240 (Lee Street) to 16th Street in Guilford County. Includes TIP project ER-5100GC. | Transportation Enhancements | 2009-10-22 | 2010-01-26 | 2012-04-30 | 2012-04-30 | 131715 | 3.100 | 0029046
8653 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0029047 | Upgrade Electrical Wiring System And Replace Metal Breakaway Poles On US 29 From I-40/I-85 Business To Phillips Avenue In Guilford County, North Carolina | Safety/Traffic Management | 2010-01-22 |  | 2010-12-31 | 2011-07-15 | 488216 | 3.100 | 0029047
8654 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0029048 | The project (U-5202) will upgrade fiberglass poles with metal breakaway poles and install high mast lighting at interchanges on US 29 from Phillips Avenue to north of SR 2835 (McKnight Mill Road) in Guilford county. | Pavement Improvement | 2009-12-21 |  | 2011-07-31 | 2011-07-18 | 612560 | 1.500 | 0029048
8655 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0035005 | This project will resurface NC 35 in Northampton County from US 158 to SR 1545 (Buck Boone Road) to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-11-13 | 2010-04-21 | 261007 | 2.200 | 0035005
8656 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PERQUIMANS |  | 01 | 0037002 | The project will replace Culvert #6 with a new aluminum culvert for Burnt Mill Creek on NC 37 at the Perquimans/Chowan County Line in Perquimans County. | Bridge Replacement | 2009-08-17 | 2009-08-17 | 2010-07-31 | 2010-09-21 | 337120 | 0.000 | 0037002
8657 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JONES |  | Multiple | 0041030 | R-5224 - This Project Will Widen And Resurface NC 41-58 From The Intersection Of NC 41-58 -SR 1300 (Middle Road) To The Pavement Change In Jones County, North Carolina. | Pavement Improvement | 2010-08-13 | 2011-08-01 | 2011-08-19 | 2011-12-02 | 700000 | 2.000 | 0041030
8658 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | Multiple | 0042020 | This project provides improvements to increase safety and mobility on NC 42 at the intersection with SR 1010 (Cleveland Road) in Johnston County. | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2010-12-14 | 2012-09-04 | 760513 | 0.000 | 0042020
8659 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 0043012 | This project adds sidewalks along the southwest side of NC43 in Greenville from US 264A to Red Banks Road in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-08-18 | 2009-09-11 | 2010-04-29 |  | 60090 | 0.500 | 0043012
8660 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CRAVEN |  | 01 | 0043013 | This project will resurface and do minimal widening on NC 43 from US 17 South to Bosch Boulevard in Craven County to improve road condition. | Pavement Improvement | 2009-09-21 | 2010-06-07 | 2010-11-15 | 2011-03-21 | 2349765 | 8.600 | 0043013
8661 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WASHINGTON |  | 01 | 0045004 | This project will replace deficient Bridge #1 over a canal on NC 45/99 0.6 miles north of the Hyde County line in Washington County. | Bridge Improvement | 2009-08-05 | 2009-08-05 | 2010-06-28 | 2010-08-23 | 347334 | 0.000 | 0045004
8662 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0045006 | This project will perform concrete and steel repairs to the bridge supports, replace five leaking construction joints and finger joints at the ends of the bridge span and clean & paint structural ste | Bridge Replacement | 2009-12-21 |  | 2011-06-30 | 2011-02-17 | 1991990 | 0.000 | 0045006
8663 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0048006 | This project will resurface NC 48 in Northampton County from SR 1200 (James Jones Road) to the Gaston East City Limits to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-11-13 | 2010-04-21 | 221144 | 2.660 | 0048006
8664 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PERSON |  | 13 | 0049027 | This project will repave the following roadways in Person County to improve road condition: NC 49 from south of Salem Church Road to Hassell Horton Road, NC 49 from Roxboro southern city limits to US 158, US 158 from NC 49 to Dee Long Road | Pavement Improvement | 2009-11-09 | 2010-08-09 | 2010-11-01 | 2011-01-24 | 1501401 | 8.630 | 0049027
8665 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE | RALEIGH |  | 0050011 | This project will perform a comprehensive Corridor Study on NC 50 From I-540 in Wake County to the City of Creedmoor in Granville County to identify alternatives for easing congestion and managing are | Other | 2009-09-24 | 2010-01-21 | 2010-12-31 |  | 200000 | 0.000 | 0050011
8666 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | 08 | 0051028 | This project will widen NC 51 from the South Carolina state line to SR 3645 (Downs Circle) in Mecklenburg County to improve safety and mobility. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2010-11-24 |  | 5521529 | 1.063 | 0051028
8667 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 0051030 | U-5199 - This project will lengthen the left turn lanes on NC 51 at NC 51 at Fullwood Lane and Monroe Road in Matthews, Mecklenbug county, North Carolina. | Pavement Improvement | 2010-01-21 | 2010-08-19 | 2010-08-27 |  | 205000 | 0.000 | 0051030
8668 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 0052033 | This project will rehabilitate pavement on US 52 from Stokes County line to SR 1815 (Cooke School Rd) in Surry County to improve road condition. | Pavement Improvement | 2009-08-05 | 2009-10-13 | 2010-06-15 |  | 3247234 | 31.960 | 0052033
8669 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STOKES |  | 05 | 0052036 | The project (R-5174A) will overlay existing pavement with an ultrathin bonded wearing course on US from the King city limits to the Surry county line in Stokes county. | Pavement Improvement | 2009-12-17 | 2010-04-01 | 2010-08-15 | 2011-04-19 | 100000 | 9.610 | 0052036
8670 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0052037 | The project (ER-5100JE) will landscape US 52 and NC 24/27/73 interchange in Albemarle, Stanley county. | Transportation Enhancements | 2009-12-15 | 2010-12-20 | 2010-12-31 | 2010-12-31 | 35000 | 0.000 | 0052037
8671 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0052038 | The project (ER-5100JG) will replace Bradford Pear trees on US 52 at various location in Stanley county. | Transportation Enhancements | 2009-12-30 | 2010-11-02 | 2010-12-31 | 2011-02-10 | 50000 | 0.000 | 0052038
8672 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HARNETT | RALEIGH | Multiple | 0055041 | This project will resurface NC 55 from NC 210 to SR 1415 (Rawls Church Raod) to imporve road condition in Harnett County. | Pavement Improvement | 2009-09-09 | 2010-01-27 | 2010-07-16 |  | 335204 | 0.480 | 0055041
8673 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0055042 | This project will add turn lanes on NC 55 in Durham at the Riddle Road intersection to enhance safety and improve mobility. | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2009-10-30 | 2011-03-21 | 209254 | 0.000 | 0055042
8674 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0057004 | This project will repave NC 57 and add two foot paved shoulders in Orange County from NC 86 to SR 1544 (Pearson Road) to improve road condition. | Pavement Improvement | 2009-08-04 | 2010-04-05 | 2010-07-30 | 2010-09-10 | 1214026 | 6.340 | 0057004
8675 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CARTERET |  | 01 | 0058011 | Construct the Emerald Isle Bike Path in Emerald Isle which includes a 10 feet multiuse path along NC58 from Black Skimmer Drive (MP 19) to the Regional Beach Access (MP 15) and future site of the new | Transportation Enhancements | 2009-07-16 | 2010-01-04 | 2010-06-30 |  | 420406 | 2.000 | 0058011
8676 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0062008 | Repair bridge expansion joints four (4) structures: Bridge 12 on NC 62, Bridge 109 on SR 2309, Bridge 115 on SR 1154 and Bridge 75 on SR 1158 in Alamance County to extend the life of the structures. | Bridge Improvement | 2009-08-05 | 2009-08-05 | 2010-05-29 | 2010-03-19 | 41333 | 0.000 | 0062008
8677 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0064117 | This project will mill asphalt from existing pavement and resurface US 64 in Martin County from the Jamesville East City Limit to west of Sweetwater Creek to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-10-01 | 2009-12-02 | 3018256 | 19.420 | 0064117
8678 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0064118 | This project will resurface US 64 from Edgecombe County Line to US 64 Alternate in Williamston in Martin County to improve road condition. | Pavement Improvement | 2009-05-06 | 2009-05-06 | 2010-11-15 | 2011-05-03 | 6440404 | 36.800 | 0064118
8679 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TYRRELL |  | Multiple | 0064119 | This project will resurface US 64 in Tyrrell County from the Bridge over the Alligator River westward for 3 miles to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-08-24 | 2009-11-13 | 2010-01-22 | 313642 | 3.000 | 0064119
8680 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 0064120 | This project will repave US 64 and US 264 in Wake and Franklin Counties from US 64 / US 264 interchange to Nash County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-11-01 | 2010-07-27 | 7064073 | 30.920 | 0064120
8681 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALEXANDER |  | 05 | 0064121 | This project will resurface US 64 from NC 90 in Iredell County to NC 90 in Alexander County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-10-16 | 2010-08-23 | 2332896 | 18.120 | 0064121
8682 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH |  | Multiple | 0064122 | This project will resurface US 64 from the Franklin County Line to Winstead Avenue in Nash County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-15 | 2010-08-23 | 3822795 | 46.360 | 0064122
8683 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | EDGECOMBE, NASH |  | Multiple | 0064123 | This project will resurface US 64 from Winstead Avenue in Nash County to the Tar River Bridge in Edgecombe County to improve road condition. | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2009-11-15 | 2010-07-26 | 7800701 | 38.420 | 0064123
8684 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | Multiple | 0064125 | This project will clean and paint the structural steel of Bridge #9 (Old Manns Harbor Bridge) carrying US 64 over Croatan Sound in Dare County to extend the life of the structure. | Bridge Replacement | 2009-06-15 | 2009-06-15 | 2011-11-04 | 2010-12-01 | 3365787 | 0.000 | 0064125
8685 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | Multiple | 0064126 | This project will construct a stormwater wetland at the corner of US64/264 Business and Greenville Street in Manteo, NC in Dare County. This saltwater wetland will be used to treat stormwater runoff | Other | 2009-09-24 | 2009-09-24 | 2010-05-11 |  | 252719 | 0.000 | 0064126
8686 | NORTH CAROLINA | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | EDGECOMBE |  | 02 | 0064130 | This is the preliminary engineering for the project that will focus efforts to improve enhancement of the landscape at the interchanges US 64 / US 258 and US 64 / McNair Road in Halifax County. | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2010-12-15 | 2010-12-15 | 88754 | 0.000 | 0064130
8687 | NORTH CAROLINA | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH |  | Multiple | 0064131 | This is the preliminary engineering for the project that will improve the landscape at the interchanges US 64 / Buck Leonard Boulevard and I-95 / NC 481 in Nash and Halifax Counties. | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2010-12-15 | 2010-12-15 | 98712 | 0.000 | 0064131
8688 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MARTIN |  | 01 | 0064132 | This project will mill asphalt pavement from US 64 Alt. in Williamston and resurface with new asphalt pavement from SR 1446 (Sycamore St.) to SR 1445 (Main Street) to improve road condition. | Pavement Improvement | 2009-09-24 | 2010-06-17 | 2010-11-30 | 2010-10-05 | 643996 | 2.600 | 0064132
8689 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TYRRELL |  | 03 | 0064135 | This project will provide concrete repairs to the bridge supports and clean & paint the structural steel on Bridge #7 over the Alligator River on US 64 at the Tyrrell/Dare County Line to extend the life of the structure. | Bridge Improvement | 2009-12-16 | 2010-04-01 | 2011-06-30 | 2011-08-25 | 1268230 | 0.000 | 0064135
8690 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MACON |  | 11 | 0064137 | The project (R-5203) will construct left turn lanes on US 64 at the intersections of SR 1516 (Sanders Road), SF 1517 (Bethel Church Road) and SR 1533 (Walnet Creek Road) in Macon county. | Pavement Improvement | 2009-11-19 | 2009-12-02 | 2010-07-30 | 2010-10-26 | 552931 | 0.611 | 0064137
8691 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TYRRELL, WASHINGTON |  | Multiple | 0064138 | The project (ER-511AD) will provide reforestation using Atlantic White Cedar on US 64 in Washington and Tyrell counties. | Transportation Enhancements | 2009-09-24 | 2010-01-25 | 2010-02-28 | 2010-08-23 | 76486 | 0.000 | 0064138
8692 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0065007 | Replace deficient bridge Number 54 carrying NC 65 over Rock House Creek in Rockingham County. | Bridge Replacement | 2009-11-09 | 2010-02-08 | 2010-11-01 | 2011-04-11 | 1283747 | 0.000 | 0065007
8693 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0068012 | This project will repave, widen and add trun lanes on NC 68 in Guilford County from SR 2011 (Edgefield Road) south of Oak Ridge to NC 65 north of Stokesdale to improve road condition. | Pavement Widening | 2009-07-21 | 2010-04-12 | 2010-07-31 | 2011-01-24 | 1572439 | 4.380 | 0068012
8694 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0068013 | This project provides for improvements at the intersection of NC 68 (Westchester Avenue) and Burton Street of adding turn lanes, revising the signals and improving draininge to increase safety and mob | Pavement Improvement | 2009-09-23 | 2010-01-11 | 2010-11-06 |  | 281500 | 0.000 | 0068013
8695 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0068014 | This project provides for improvements at the intersection of NC 68 (Westchester Avenue) and Clinard Farms Road of adding turn lanes and improving draininge to increase safety and mobility in Guilford | Pavement Improvement | 2009-09-23 | 2010-01-11 | 2010-11-06 |  | 44363 | 0.000 | 0068014
8696 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CLAY |  | 11 | 0069006 | The project (R-5204) will construct a center turn lane and improve access management on NC 69 from north of US 64 to south of SR 1118 in Clay county. | Pavement Improvement | 2010-01-12 | 2010-03-22 | 2011-06-30 | 2011-09-23 | 1512370 | 1.004 | 0069006
8697 | NORTH CAROLINA | Underway | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 03 | 0070121 | This project will provide improvements to increase safety and mobility on US 70 Business at the SR 1553 (Shotwell Road) intersection in Johnston County. | Pavement Improvement | 2009-07-07 | 2010-03-01 | 2010-04-15 |  | 70134 | 0.000 | 0070121
8698 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0070127 | Repair bridge expansion joints on one (1) structure: Bridge 6 on US 70 in Orange County to extend the life of the structure. | Bridge Improvement | 2009-07-28 | 2010-01-25 | 2010-05-29 | 2010-01-28 | 22410 | 0.000 | 0070127
8699 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0070129 | This project will repave US 70 (Church Street) in Burlington / Alamance County, from SR 1716 (Graham-Hopedale Road) to NC 62 to improve road condition. Includes TIP project R-5175B. | Pavement Improvement | 2009-08-17 | 2010-03-17 | 2010-09-17 | 2011-03-09 | 1897335 | 11.170 | 0070129
8700 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 02 | 0070134 | The project (ER-5100DE) will provide roadside landscape enhancement and establishment on US 70 (Clayton Bypass) in Johnston county. | Transportation Enhancements | 2009-12-28 | 2010-08-06 | 2011-12-15 | 2011-12-14 | 318423 |  | 0070134
8701 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0070140 | R-5164E - This project will resurface US 70 Business from Buchanan Street to 9th street; US 15-501 from Enterprise Street to NC 751; US 70 Business from Great Jones Street to Main Street; SR 2295 (Sou | Pavement Improvement | 2010-08-23 | 2011-04-01 | 2011-09-02 | 2011-12-01 | 400000 | 7.530 | 0070140
8702 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 0073019 | Replace deficient bridge carrying NC 73 over Long Creek in Stanly County. | Bridge Replacement | 2009-03-02 | 2009-03-02 | 2010-12-31 | 2010-12-01 | 3020655 | 0.000 | 0073019
8703 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CABARRUS |  | Multiple | 0073020 | "This project includes construction to repair drainage and pavement issues in Mount Pleasant on NC 73 from east of the City Limits to SR 1411 (Cold Springs Road) as follows: Project 1: Removes the ex | Pavement Improvement | 2009-06-02 | 2009-06-02 | 2010-09-17 | 2011-02-10 | 531623 | 11.004 | 0073020
8704 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 0073021 | Widen NC 73 from US 21 to NC 115 in Mecklenburg County to improve safety and mobility. | Pavement Widening | 2009-09-21 | 2009-09-21 | 2012-11-15 |  | 21684048 | 1.190 | 0073021
8705 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RICHMOND |  | 08 | 0073022 | B-4614 - This project will replace bridge 41 on NC 73 over Naked Creek in Richmond county, North Carolina. | Bridge Replacement | 2010-02-09 | 2010-06-02 | 2010-09-17 | 2011-04-20 | 685046 | 0.000 | 0073022
8706 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CLEVELAND |  | 10 | 0074104 | This project will resurface US 74 from SR 1170 (Lucas Rd) to West Lee in Cleveland County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-02 | 2010-07-26 | 1436373 | 3.066 | 0074104
8707 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SWAIN |  | 11 | 0074105 | This project will rehabilitate pavement on US 74 from SR 1159 (Spring St) to the Jackson County line in Swain County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-12-15 | 2011-03-21 | 6108843 | 9.740 | 0074105
8708 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ANSON |  | 08 | 0074108 | This project will include pavement rehabilitation, paved shoulders, and guardrail on US 74 westbound from beginning of divided highway west of SR 1259 to Union County line in Anson County, improving road condition and safety. | Pavement Improvement | 2009-09-09 | 2010-05-07 | 2010-07-02 | 2010-11-18 | 3002394 | 10.800 | 0074108
8709 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ANSON |  | 08 | 0074109 | The project (U-5196) will mill and surface US 74 from NC 109 to west of North Park Road in Anson county. | Pavement Improvement | 2010-01-07 | 2010-10-28 | 2010-11-15 | 2011-03-23 | 310012 | 1.480 | 0074109
8710 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ANSON, UNION |  | Multiple | 0074110 | The project (ER-5100JF) will replace Bradford Pear trees on US 74 at various locations in Anson and Union counties. | Transportation Enhancements | 2009-12-29 | 2010-10-18 | 2010-12-31 | 2011-02-10 | 75000 |  | 0074110
8711 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LEE |  | 03 | 0078004 | This project will widen NC 78 in Sanford / Lee County, from Tramway to beyond St. Andrews Road, to enhance safety and mobility. | Pavement Widening | 2009-03-26 | 2009-03-26 | 2010-04-30 | 2011-03-21 | 1939063 | 2.450 | 0078004
8712 | NORTH CAROLINA | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CASWELL |  | Multiple | 0086008 | This project will repave NC 86 in Caswell County from NC 119 to US 158, including shoulders, to improve road condition. | Pavement Improvement | 2009-08-04 | 2010-07-19 | 2010-08-06 | 2010-11-06 | 1379720 | 7.813 | 0086008
8713 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0086010 | R-5178B - This project will mill, resurface and replace curb and gutter on NC 86 from SR 1010 (Franklin Street) to Cameron Avenue in Chapel Hill, Orange county, North Carolina. | Pavement Improvement | 2009-08-04 |  | 2010-08-13 | 2011-03-21 | 181152 | 0.200 | 0086010
8714 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | 06 | 0087022 | This project provides for the replacement of existing signal poles & mast arms at the NC 87 (Webb Avenue) and Elmira Street intersection to improve road conditions in Alamance County. | Other | 2009-08-05 | 2009-08-05 | 2010-02-16 |  | 2484 | 0.620 | 0087022
8715 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BLADEN |  | 07 | 0087024 | The project (ER-5100FF) will provide Czip planting on NC 87 north from SR 1356 (Pearl Lloyd Road) to SR 1308 (Old NC 20) in Bladen county. | Transportation Enhancements | 2010-01-04 | 2010-05-17 | 2010-06-11 | 2010-06-16 | 45000 | 0.470 | 0087024
8716 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALLEGHANY |  | 05 | 0093003 | This project will rehabilitate pavement on NC 93 from US 221 to SR 1337 (Mt. Carmel Rd) in Alleghany County to improve road condition. This project includes TIP R-5157. | Pavement Improvement | 2009-06-22 | 2009-07-01 | 2010-07-01 | 2011-04-20 | 1208490 | 10.000 | 0093003
8717 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0098025 | This project will repave NC 98 in Durham County from Junction Road to Sherron Road to improve road condition. | Pavement Widening | 2009-05-13 | 2009-05-13 | 2010-05-14 | 2011-05-16 | 732133 |  | 0098025
8718 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FRANKLIN |  | 02 | 0098026 | This project will repave the following roadways in Franklin County to improve road condition: NC 98 from US 401 to Bunn and US 1A from US 1 to NC 56 in Franklinton. | Pavement Improvement | 2009-11-09 |  | 2010-11-01 |  | 2395402 | 9.830 | 0098026
8719 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CUMBERLAND | FAYETTEVILLE | Multiple | 0100017 | This project will perform grading and construct the bridges on the future I-295 Fayetteville Outer Loop in Cumberland County from Bragg Boulevard to Murchison Road for a four lane divided highway. Pa | Pavement Widening | 2009-04-21 | 2009-04-21 | 2012-07-01 |  | 54501720 | 1.390 | 0100017
8720 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JACKSON |  | 11 | 0107011 | The project (R-5202) will widen pavement and shoulders, improve drainage and construct a left turn late on NC 107 at SR 1145 in Jackson county. | Pavement Improvement | 2010-01-06 | 2010-03-22 | 2010-11-01 | 2012-08-23 | 2463331 | 0.784 | 0107011
8721 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILKES |  | 05 | 0115005 | R-5159 - This project will widenen and rehabilitate pavement on NC 115 from US 421 to the Iredell county line in Wilkes county, North Carolina. | Pavement Improvement | 2010-02-05 | 2010-05-04 | 2010-11-15 |  | 3749661 | 8.100 | 0115005
8722 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0119003 | This project will repave NC 119 with two foot shoulders in Alamance County from the Mebane north city limits to the Caswell County line to improve road condition. | Pavement Improvement | 2009-11-16 | 2010-03-18 | 2010-05-17 | 2011-03-21 | 1783990 | 9.998 | 0119003
8723 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GRAHAM |  | 11 | 0129002 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 10 over East Buffaloe Creek on US 129 in Graham County to extend the life of the structure. | Bridge Improvement | 2009-10-15 | 2009-10-15 | 2010-09-30 | 2011-03-21 | 992812 | 0.000 | 0129002
8724 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHEROKEE |  | 11 | 0141005 | This project will rehabilitate pavement on NC 141 from US 64 to US 74 in Cherokee County to improve road condition. | Pavement Improvement | 2009-07-08 | 2009-07-08 | 2010-11-15 | 2010-11-23 | 2468528 | 16.220 | 0141005
8725 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0147003 | R-5164D - This project will resurface NC 147 from the concrete/asphalt joint West of Exit 14 (Swift Avenue) to the concrete/asphalt North of Exit 7 (TW Alexander Drive) in Durham County, North Carolina. | Pavement Improvement | 2010-08-23 | 2011-03-15 | 2011-11-01 | 2012-09-27 | 1040000 | 13.600 | 0147003
8726 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CAMDEN |  | Multiple | 0158040 | This project will widen US 158-NC 34 from East of the Pasquotank River in Elizabeth City to North of Havenwood Road in Camden County from two lanes to multi-lanes to improve traffic operations and improve safety. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2011-08-01 | 2012-03-11 | 7057343 | 3.855 | 0158040
8727 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | Multiple | 0158042 | This project will perform renovations to the existing buildings at the Kitty Hawk Rest Area on US 158 including replacement of wall tile and plumbing fixtures, addition of an ADA compliant family rest | Pavement Improvement | 2009-05-26 | 2009-05-26 | 2010-03-20 | 2010-10-26 | 312280 | 0.000 | 0158042
8728 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0158043 | This project will resurface US 158 from Halifax County Line to multi-lane section west of Hertford County Line in Northampton County to improve road condition. | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2011-11-15 | 2011-12-14 | 7420805 | 28.190 | 0158043
8729 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0158048 | The project (ER-5100AA) will renovate existing plantings and add additional plant material on US 158 Business from SR 1300 (Wise Store Road) to 0.2 miles east of SR 1335 (Lance Road) and along US 258 | Transportation Enhancements | 2009-10-28 | 2010-04-26 | 2011-05-31 | 2011-05-31 | 78967 | 1.899 | 0158048
8730 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0158049 | ER-5100AB - This project will provide for the installation of enhancement plantings at three ""Welcome to Garysburg"" signs on US 158, US 301 and NC 46 in Northampton county, North Carolina." | Transportation Enhancements | 2010-02-09 | 2010-05-20 | 2011-05-31 | 2011-05-31 | 31969 | 0.000 | 0158049
8731 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ONSLOW |  | 03 | 0172012 | R-5219 - This Project Will Construct Right Turn Lanes On NC 172 and NC 210 Northbound At The Intersection Of The Two Roads In Sneads Ferry, Onslow County, North Carolina | Safety/Traffic Management | 2010-08-08 | 2010-10-04 | 2010-11-10 | 2010-11-10 | 140000 | 0.000 | 0172012
8732 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON |  | 11 | 0176006 | This project will rehabilitate pavement on US 176 from NC 225 to US 25 in Henderson County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-12-15 | 2010-07-26 | 2488322 | 4.980 | 0176006
8733 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RICHMOND |  | 08 | 0177003 | The project will install landscape enhancement plantings at the NC 177 and SR1900 Battlet Dairy Road interchange in Richmond County. | Transportation Enhancements | 2009-09-21 | 2009-11-30 | 2009-02-26 | 2010-02-09 | 20523 | 0.000 | 0177003
8734 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | AVERY |  | Multiple | 0194010 | This project will rehabilitate pavement and widen NC 194 from US 221 to US 19 E in Avery County to improve road condition and safety. | Pavement Improvement | 2009-06-22 | 2009-06-22 | 2010-06-01 | 2011-05-10 | 1030620 | 4.200 | 0194010
8735 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | AVERY |  | 10 | 0194013 | R-2710 - This project will resurface and improve safety by improving grading, drainage, paving, signal and retaining wall on NC 194 from Banner Elk in Avery County to Valle Crucis in Watauga County, North Carolina. | Pavement Improvement | 2010-08-23 | 2010-11-09 | 2012-06-15 | 2012-11-14 | 5740000 | 5.500 | 0194013
8736 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BEAUFORT |  | Multiple | 0207002 | The project (ER-5100BD) will provide picnic tables with shelters, bike rack with concrete pad and concrete trash cans at the Bayview Beach Ferry Terminal in Beaufort county. | Transportation Enhancements | 2009-10-23 |  | 2010-03-15 | 2010-04-13 | 27601 | 0.000 | 0207002
8737 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TRANSYLVANIA |  | 11 | 0215004 | This project will install and revise guardrail on NC 215 from US 64 to the Haywood County line in Transylvania County to improve safety. | Safety/Traffic Management | 2009-05-13 | 2009-05-13 | 2010-08-01 | 2010-07-28 | 2257227 | 16.820 | 0215004
8738 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION |  | Multiple | 0218008 | This project will rehabilitate pavement on NC 218 from east of I-485 to west of US 601 in Mecklenburg and Union Counties to improve road condition. | Pavement Improvement | 2009-06-16 | 2009-07-08 | 2009-09-30 | 2009-12-18 | 1736308 | 6.960 | 0218008
8739 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION |  | Multiple | 0218009 | This project will rehabilitate pavement on NC 218 from east of US 601 to west of NC 205 in Union County to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-10-30 | 2010-12-01 | 3080356 | 10.930 | 0218009
8740 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION |  | Multiple | 0218010 | This project will rehabilitate pavement on NC 218 from east of NC 205 to US 74 in Anson and Union Counties to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-11-20 | 2010-12-01 | 3381139 | 13.650 | 0218010
8741 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION | CHARLOTTE | Multiple | 0218011 | Widening for turn lanes on NC 218 @ NC 205, Also widening for turn lanes on US 601 @ NC 218. | Pavement Widening | 2009-05-07 | 2009-05-07 | 2009-09-30 |  | 567418 | 0.000 | 0218011
8742 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION |  | Multiple | 0218012 | This project will construct three filtration basins and a stormwater wetland for the purpose of treating stormwater runoff, from the intersection of US 601 and NC 218 in Union County, before discharging to Goose Creek. | Other | 2009-09-15 | 2009-09-15 | 2010-02-15 | 2010-03-01 | 138349 | 0.000 | 0218012
8743 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0220041 | This project will repave US 220 in Rockingham County from NC 135 to the Virginia State line to improve road condition. Includes TIP project R-5180 | Pavement Improvement | 2009-09-08 | 2010-08-02 | 2010-09-24 | 2011-05-25 | 2835099 | 18.640 | 0220041
8744 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RANDOLPH |  | 06 | 0220044 | Landscape Planting Renovation on US 220 At US 64 And SR 1713 (Albemarle Road) Interchanges In Randolph County, North Carolina | Transportation Enhancements | 2009-10-29 | 2010-02-09 | 2010-03-31 | 2010-04-08 | 126142 | 0.000 | 0220044
8745 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 0224013 | Perform grading and construct the bridges on C. Felix Harvey Parkway in Lenoir County from US 70 to US 258 for a four lane divided highway. Paving contract will be done as a separate project in the future. | New Construction | 2009-05-08 | 2009-05-08 | 2012-08-01 |  | 42926208 | 0.000 | 0224013
8746 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CRAVEN |  | Multiple | 0229010 | The project (ER-5100BA) will implement plantings at the intersections of US 70 and Pembroke Avenue, Glenburnie Avenue, NC 41 AND US 17; intersection of NC 43 Bypass and NC55, Broad Street median; and along US 17 in Craven county. | Transportation Enhancements | 2009-09-21 | 2010-02-22 | 2010-12-31 | 2010-12-22 | 264130 | 0.000 | 0229010
8747 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 0240002 | Rehabilitate pavement on I-240 from US 70 to I-40 in Buncombe County to improve road condition. | Pavement Improvement | 2010-01-13 | 2010-03-29 | 2011-09-15 | 2011-10-25 | 1000000 | 5.930 | 0240002
8748 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 0240003 | This project will construct three filtration basin systems for treating stormwater runoff, from I-240, near mile marker 6, just west of Chuns Cove Road, in Asheville, NC before discharging to Ross Cre | Other | 2009-11-05 | 2010-04-16 | 2010-07-02 | 2010-07-02 | 291849 | 0.000 | 0240003
8749 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 0241004 | R-5221 - This Project Will Mill, Resurface and Widen NC 241 Two (2) Feet From NC 11 In Pink Hill To End of Curb And Gutter in Duplin County Line In Lenoir County, North Carolina. | Pavement Improvement | 2010-08-05 | 2011-03-11 | 2011-08-19 | 2011-04-20 | 455000 | 1.470 | 0241004
8750 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NORTHAMPTON |  | 01 | 0258015 | This project will mill asphalt from existing pavement and resurface US 258 from Roanoke River to NC 305 in Northampton County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-11-01 | 2010-01-22 | 1034928 | 7.450 | 0258015
8751 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GREENE |  | 01 | 0258017 | This project will resurface and do minimal widening on US 258 from Contentnea Creek to NC 123 in Greene County to improve road condition. | Pavement Improvement | 2009-09-21 | 2010-08-24 | 2010-11-15 | 2011-04-07 | 1269268 | 4.000 | 0258017
8752 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PAMLICO |  | 03 | 0259002 | The project (ER-5100BC) will provide picnic tables with shelters, bike rack with concrete pad and concrete trash cans at the Minnessott Beach Ferry Terminal in Pamlico county. | Transportation Enhancements | 2009-10-23 | 2010-02-23 | 2010-03-15 | 2010-04-13 | 28176 | 0.000 | 0259002
8753 | NORTH CAROLINA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 0261083 | Mill areas where potholes, cracking and/or delamination of the asphalt surface has occurred and resurface to promote the life of the roadway surface on I-26 from mile post 31 to mile post 37 in Buncombe County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2010-09-30 | 2011-07-22 | 6772227 | 5.360 | 0261083
8754 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | POLK |  | 11 | 0261085 | This project provides for preconstruction activities to rehabilitate the pavement on I-26 from milepost 61 to milepost 71 in Polk County to improve road condition. | Pavement Improvement | 2009-07-08 | 2009-07-08 | 2010-09-30 | 2011-04-29 | 7011743 | 27.570 | 0261085
8755 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DARE |  | Multiple | 0264039 | This project will resurface US 264 in Dare County from SR 1100 (Stumpy Point Road) to the Navy Range to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2010-01-22 | 350033 | 2.870 | 0264039
8756 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 0264042 | This project adds an additional turn lane on US 264 in Greenville at the intersection of Stantonsburg Road and Arlington Blvd in Pitt County to ease congestion and improve safety. This is a locally administered project by the City of Greenville. | Pavement Widening | 2009-08-18 | 2009-09-08 | 2010-05-14 |  | 5097 | 0.000 | 0264042
8757 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILSON |  | Multiple | 0264043 | This project will resurface US 264 from NC 58 to the Greene County Line in Wilson County to improve road condition. | Pavement Improvement | 2009-09-09 | 2010-08-05 | 2010-11-01 | 2011-06-09 | 4016081 | 16.400 | 0264043
8758 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH, WILSON |  | Multiple | 0264045 | This project will resurface US 264 from the Wake County Line to US 264 Alternate in Nash and Wilson Counties to improve road condition. | Pavement Improvement | 2009-11-10 | 2010-04-17 | 2010-10-01 | 2010-10-29 | 3213406 | 25.800 | 0264045
8759 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 0264046 | The project (ER-5100BB) will provide tree planting on US 264 and US 258 in Farmville, Pitt county. | Transportation Enhancements | 2009-11-02 | 2010-03-15 | 2010-12-15 | 2010-11-23 | 110231 | 0.000 | 0264046
8760 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BEAUFORT |  | Multiple | 0264048 | R-5223 - This Project Will Widen And Resurface US 264 From SR 1718 (Yeatesville Road) To SR 1714 (Seed Tick Neck Road) In Beaufort County, North Carolina. | Pavement Widening | 2010-08-23 | 2011-04-18 | 2011-08-19 | 2011-09-16 | 770000 | 2.100 | 0264048
8761 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | 09 | 0274007 | This project will widen NC 274 from SR 1484 (Maine Ave) to NC 275 in Gaston County to improve safety and mobility. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2011-07-01 | 2011-11-21 | 5450259 | 1.261 | 0274007
8762 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | TRANSYLVANIA |  | 11 | 0276008 | This project will rehabilitate pavement and install paved shoulders on US 276 from Pisgah Forest to Brevard in Transylvania County to improve road condition and safety. | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2010-05-15 | 2010-10-26 | 2040315 | 6.768 | 0276008
8763 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0305001 | This project will mill asphalt from existing pavement, overlay with an asphalt surface treatment (mat & seal) and resurface the pavement of NC 305 NC 305 from US 13 to NC 11 in Bertie County to improve road condition. | Pavement Improvement | 2009-05-06 | 2009-05-06 | 2010-07-01 | 2010-09-16 | 1977315 | 12.450 | 0305001
8764 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0308004 | This project will resurface NC 308 in Windsor from King Street to Sterlingworth Street to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2011-01-24 | 92507 | 0.270 | 0308004
8765 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0308005 | This project will resurface NC 308 in Bertie County from the Kelford East City Limits to the Kelford West City Limits to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2011-01-24 | 132297 | 1.000 | 0308005
8766 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 0308006 | This project will resurface NC 308 in Bertie County from SR 1119 (Jack Branch Road) to SR 1247 (Mount Olive Road) to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-13 | 2011-01-24 | 158601 | 1.720 | 0308006
8767 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0311026 | This project includes the preparation of an environmental document for the replacement of the interchange at US 311 & NC 68 in High Point in Guilford County. This is a locally administered project by the City of High Point. | Other | 2009-08-18 | 2009-08-21 | 2002-12-31 |  | 475000 | 0.000 | 0311026
8768 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0311027 | This project will modify two existing hazardous spill basins and construct a linear filtration basin to collect the runoff from the bridge over the Oak Hollow Reservoir located on US-311/SR-1979 in Gu | Other | 2009-11-04 |  | 2010-10-30 | 2011-07-13 | 68568 | 0.000 | 0311027
8769 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CALDWELL |  | 10 | 0321020 | This project will rehabilitate pavement on US 321 from SR 1178 (Hibriten Dr SE) to city limits of Lenoir in Caldwell County to improve road condition. | Pavement Improvement | 2009-06-01 | 2009-08-31 | 2009-10-30 | 2011-01-24 | 478748 | 2.320 | 0321020
8770 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CATAWBA |  | 10 | 0321021 | The project (ER-5100LB) will provide reforestation of trees on US 321 northbound and southbound from the lincoln county line to the NC 127 interchange in Catawba county. | Transportation Enhancements | 2009-10-28 | 2010-02-10 | 2011-04-29 | 2010-03-25 | 55000 | 23.722 | 0321021
8771 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER |  | 07 | 0332034 | This project will construct a 0.6 mile long asphalt multi-use path in Wilmington along South 17th Street between the Cameron Art Museum and Halyburton Park and an 0.2 mile long asphalt multi-use path | Transportation Enhancements | 2009-08-03 | 2010-02-01 | 2010-07-01 | 2012-02-07 | 300180 | 0.000 | 0332034
8772 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER |  | 07 | 0332035 | This project will construct a 2.6 mile long asphalt multi-use path in Wilmington between Randall Parkway and Converse Road, parallel to Rosemont Avenue, Caswell Street, Park Avenue and Independence Bo | Transportation Enhancements | 2009-05-28 | 2010-03-01 | 2010-09-01 | 2012-02-07 | 1620000 | 0.000 | 0332035
8773 | NORTH CAROLINA | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER |  | 07 | 0332039 | EB-5118CA - This project Will Construct Phase III of the Wilmington Cross-City Trail, A Multi-Use Path Between South College Road And The Autumn Hall Mixed Use Development In Wilmington, New Hanover County, North Carolina. | Transportation Enhancements | 2010-09-23 | 2011-02-17 | 2011-08-16 |  | 1362267 | 0.000 | 0332039
8774 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 0401200 | This project will improve drainage and?complete minor landscape improvements to the I-40 west bound rest area building in Haywood County at MM 10. | Transportation Enhancements | 2009-07-27 | 2010-01-26 | 2010-03-26 | 2010-05-25 | 25444 | 0.350 | 0401200
8775 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 0401204 | Rehabilitate pavement on I-40 from SR 2838 (Exit 55) to mile post 67 in Buncombe County to improve road condition. | Pavement Improvement | 2009-11-17 | 2010-02-01 | 2010-10-30 | 2011-07-22 | 8340778 | 11.720 | 0401204
8776 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0401206 | Widen US 401 in Wake County between Neuse River and Louisburg Road near Rolesville, to enhance safety and mobility. | Pavement Widening | 2009-11-09 | 2010-02-19 | 2011-12-31 | 2011-12-06 | 9917986 | 3.695 | 0401206
8777 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 0401210 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 124 over SR 1338 ON I-40 in Haywood County to extend the life of the structure. | Bridge Improvement | 2009-10-15 | 2009-10-15 | 2010-01-31 | 2010-10-05 | 720385 | 0.000 | 0401210
8778 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 0401211 | This project provides for bridge deck rehabilitation and special latex modified concrete for Bridge 205 over SR 1364 ON I-40 in Haywood County to extend the life of the structure. | Bridge Improvement | 2009-10-28 | 2009-11-20 | 2010-01-31 | 2010-10-05 | 407385 | 0.000 | 0401211
8779 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 0401212 | The project (I-5140) will replace six dynamic message signs on Interstate 40 at milepost 33.4 (east and westbound), milepost 28.7 (east and westbound), milepost 21 (westbound), and milepost 0.7 (eastbound) in Haywood county. | Safety/Traffic Management | 2009-11-02 | 2010-02-22 | 2010-08-27 |  | 672744 | 0.000 | 0401212
8780 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BURKE |  | 10 | 0402142 | This project will resurface the roadway with an asphalt microsurface (a thinner yet extremely durable treatment) to extend the life of the road and provide improved rideability on I-40 from mile post | Pavement Improvement | 2009-04-16 | 2009-04-17 | 2010-10-29 | 2011-03-30 | 9583890 | 23.830 | 0402142
8781 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CATAWBA |  | 10 | 0402146 | This project will renovate the existing pair of?rest area?buildings located on I-40, west of Claremont into vending,?security offices?and storage, construct a new pair of restroom buildings with dual | Pavement Improvement | 2010-01-13 | 2010-03-30 | 2011-04-01 | 2011-06-10 | 1408843 | 0.000 | 0402146
8782 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BURKE |  | 10 | 0402149 | ER-5100MB - This project will provide sod seeding and tree plantings on I-40 from milepost 95 to milepost 119 in Burke county, North Carolina. | Transportation Enhancements | 2010-01-21 | 2010-05-24 | 2011-05-03 | 2011-05-03 | 176000 | 2.010 | 0402149
8783 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MCDOWELL |  | 11 | 0402150 | K-4909 - This project will renovate rest area pair, including grounds, parking facilities and buildings to include dual restrooms and ADA compliant family restrooms on I-40 in McDowell County, North Carolina. | Transportation Enhancements | 2010-07-15 | 2010-10-01 | 2011-09-30 | 2012-04-24 | 1905285 | 0.000 | 0402150
8784 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | IREDELL |  | Multiple | 0402154 | ER-5100LD - This Project Will Provide For Interchange Enhancement Plantings On I-40 At Exits 148 and 150 In Iredell County, North Carolina. | Transportation Enhancements | 2010-08-23 | 2010-12-13 | 2011-01-31 | 2011-03-08 | 100000 | 0.000 | 0402154
8785 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0403122 | Resurface I-40 from Clemmonsville Road to US 311 in Winston-Salem / Forsyth County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-09-15 | 2010-05-25 | 1786443 | 3.500 | 0403122
8786 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 0403123 | Resurface I-40/85 from Rock Creek Dairy Road in Guilford County to University Drive in Alamance County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-10-30 | 2010-04-21 | 4416766 | 8.294 | 0403123
8787 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0403124 | Resurface I-40 from Harper Road to Jonestown Road in Forsyth County to improve road condition. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-06-15 | 2010-10-05 | 3107926 | 9.200 | 0403124
8788 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 0403125 | Replace damaged/missing reflectors in pavement lane markers on I-40/85 in Guilford County, between I-40 and I-85 junction east of Greensboro to beyond Mount Hope Church Road, to improve nighttime visibility. | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2010-05-01 | 2010-10-26 | 28638 | 2.000 | 0403125
8789 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0403126 | The project will install landscape enhancement in Burlington at the interchange of I-40/85 and SR 1226 (University Drive) in Alamance County. | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2011-12-15 | 2012-05-21 | 105369 | 0.000 | 0403126
8790 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0403127 | The project will renovate multiple landscape beds in Winston Salem along I-40 and install flowering trees along US-52 in Forsyth County. | Transportation Enhancements | 2009-12-04 | 2009-12-10 | 2011-03-31 | 2011-02-14 | 507010 | 22.060 | 0403127
8791 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0403128 | The project (ER-5100GG) will provide landscape rehabilitation on Interstate 40/Interstate 85 at the NC 87 interchange in Alamance county. | Transportation Enhancements | 2009-12-21 | 2010-03-01 | 2012-05-28 | 2012-05-28 | 67999 | 0.000 | 0403128
8792 | NORTH CAROLINA | Completed | C250,C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SAMPSON, DUPLIN |  | Multiple | 0405052 | Resurface I-40 from east of Newton Grove in Sampson County to east of Warsaw in Duplin County to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2010-11-15 | 2011-07-21 | 13130961 | 41.760 | 0405052
8793 | NORTH CAROLINA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 02 | 0405053 | This projects provides for the resurfacing of I-40 from west of Morgan Road to the Sampson County Line in Johnston County to improve road condition. | Pavement Improvement | 2009-04-10 | 2009-04-10 | 2010-11-15 | 2010-10-05 | 2647220 | 22.000 | 0405053
8794 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DUPLIN |  | 03 | 0405054 | The project (I-5001A) will repave Interstate 40 from milepost 369.4 in Duplin county to milepost 389.5 in Pender county to improve road condition. | Pavement Improvement | 2009-12-16 | 2010-02-08 | 2011-05-31 | 2012-09-30 | 1000000 | 40.180 | 0405054
8795 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER, SAMPSON, DUPLIN, PENDER |  | Multiple | 0405055 | The project (ER-5100CA) will provide wildflower seeding and mulching on Interstate 40 in New Hanover, Pender, Duplin and Sampson counties. | Transportation Enhancements | 2009-10-09 | 2010-02-08 | 2010-04-02 | 2010-03-16 | 160787 |  | 0405055
8796 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAYNE |  | Multiple | 0414004 | This project will install a computerized central signal system in the City of Goldsboro to synchronize the traffic signals to improve traffic flow. | Safety/Traffic Management | 2009-08-05 | 2009-08-05 | 2012-02-01 | 2012-02-15 | 3622986 | 0.000 | 0414004
8797 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WATAUGA |  | 05 | 0421047 | This project will widen US 421 (King Street) from NC 194 to US 321 in Watauga County to improve safety and mobility. | Other | 2009-05-06 | 2009-05-06 | 2011-12-31 |  | 16987363 | 1.098 | 0421047
8798 | NORTH CAROLINA | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LEE |  | 02 | 0421050 | Construct section of Sanford Bypass between NC 42 and NC 87 south of Sanford, to reduce congestion and improve mobility. | New Construction | 2009-11-09 | 2010-02-22 | 2012-11-15 |  | 27757178 | 0.000 | 0421050
8799 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0421053 | This project will repave US 421 in Guilford County from the Randolph County line to north of SR 3485 (Harmont Drive) to improve road condition. | Pavement Improvement | 2009-10-13 | 2010-03-08 | 2010-09-03 | 2011-03-21 | 2994071 | 19.920 | 0421053
8800 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHATHAM |  | Multiple | 0421055 | The project (ER-5100HC) will provide landscape renovation planting and plant bed restoration on US 421 at US 64 and US 421 at SR 1362 (Piney Grove Church Road) in Chatham county. | Transportation Enhancements | 2009-10-23 | 2010-01-30 | 2010-03-31 | 2010-03-31 | 96361 | 0.000 | 0421055
8801 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0421057 | The project (U-5144B) wil mill, rehabilitate pavement and resurface two lanes northbound and two lanes southbound of US 421 from pavement joint at the ramps at Lesisville to the Yadkin county line in Forsyth county. | Pavement Improvement | 2009-12-17 | 2010-05-09 | 2010-09-30 | 2011-01-24 | 500000 | 8.186 | 0421057
8802 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILKES |  | 05 | 0421058 | The project (ER-5100KA) will provide reforestation and manual clearing on US 421 From SR 1765 (Unifi Industrial Road) in Yadkin County to the Boome Town limits in Wataugh County in Wilkes County. | Transportation Enhancements | 2009-10-22 | 2010-01-27 | 2010-04-23 | 2010-08-23 | 93043 | 33.760 | 0421058
8803 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILKES |  | 05 | 0421060 | ER-5100KB - This project will renovate and enhance landscape plantings on US 421 at the interchanges with NC 268, NC 16/18 South and SR 1001 (Brushy Mountain Road) in Wilkesboro in Wilkes county, North Carolina. | Transportation Enhancements | 2010-01-21 | 2010-08-30 | 2011-12-17 | 2011-12-17 | 106799 | 0.000 | 0421060
8804 | NORTH CAROLINA | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NEW HANOVER |  | 07 | 0421063 | ER-5100CB - This project will remove vegetation and supplement seeding & plantings within the medians and shoulders in the vacinity of the battleship on US 421/17/74/76 interchange in New Hanover county, North Carolina. | Transportation Enhancements | 2010-02-01 | 2010-12-02 | 2012-08-31 | 2012-08-31 | 731500 | 0.000 | 0421063
8805 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | 04 | 0440006 | Remove sections of concrete pavement and replace with asphalt to improve road condition. | Pavement Improvement | 2009-03-26 | 2009-04-15 | 2010-06-30 | 2011-05-01 | 4024603 | 5.000 | 0440006
8806 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 0440007 | Resurface I-440 Beltline in Raleigh from Wade Avenue to Wake Forest Road to improve road condition | Pavement Improvement | 2009-03-26 | 2009-03-26 | 2009-12-31 | 2010-06-18 | 3709163 | 10.000 | 0440007
8807 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0440008 | This project consists of cleaning and painting bridges in Raleigh along I-440 including bridge numbers, 249 (Glen Eden), 252 (Ridge Road), 139 (US 401), 287 (US 1), and 288 (US 410 SBL) to extend lifespan. | Bridge Improvement | 2009-08-24 | 2010-04-14 | 2010-10-31 | 2011-02-24 | 896775 | 0.000 | 0440008
8808 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 0440009 | This project provides for the installation of a Wireless Camera System on the Northern Section of I-440 in Raleigh to improve response to traffic congestion in Wake County. | Safety/Traffic Management | 2009-04-30 | 2009-04-30 | 2010-03-02 | 2010-03-17 | 382761 | 3.680 | 0440009
8809 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0485016 | This project will construct a filtration basin/wetland at NC 51/I-485 to treat stormwater runoff from NC 51 in Mecklenburg County helping to prevent pollutants from entering into a tributary of Clear Creek. | Other | 2009-10-15 | 2009-10-15 | 2010-04-30 | 2010-04-19 | 148065 | 0.000 | 0485016
8810 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0485025 | ER-5100JD - This project will reforestate at various locations on I-485 from US 74 East to I-85 North in Mecklenburg county, North Carolina. | Transportation Enhancements | 2010-01-21 |  | 2011-03-18 |  | 40000 | 26.540 | 0485025
8811 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0501014 | This project will repave Duke Street in Durham from Horton Road to Hudson Street to improve road condition. | Pavement Widening | 2009-05-13 | 2009-05-13 | 2010-05-14 | 2011-05-16 | 777500 |  | 0501014
8812 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0501015 | This project will install a traffic signal in Apex at the Intersection of SR 1010 (Center Street) and SR 1011 (North Salem Street) to improve safety. This is a locally administered project by the Town of Apex. | Safety/Traffic Management | 2009-09-17 | 2010-04-14 | 2010-05-14 |  | 30791 | 0.000 | 0501015
8813 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0503007 | This project will construct a portion of the Black Creek Greenway pedestrian and bicycle facilities from the Credit Union near the intersection of Chapel Hill Road and Northwest Maynard Road to the Sh | Transportation Enhancements | 2009-09-21 | 2010-03-01 | 2010-10-26 |  | 1299000 | 0.000 | 0503007
8814 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0505034 | This project will provide for traffic signal upgrades in Durham including pedestrian installed equipment at various locations for the city maintained signals to improve operating efficiency and safety | Safety/Traffic Management | 2009-09-22 | 2010-01-15 | 2010-09-12 |  | 122702 | 0.000 | 0505034
8815 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0505036 | The project provides for the installation of a new traffic signal in Durham at Northpoint Drive at Home Depot Entrance and Dehaven?s Entrance to improve safety in Durham County. TIP U-5150 is include | Safety/Traffic Management | 2009-09-22 | 2010-01-15 | 2010-09-12 |  | 339690 | 0.000 | 0505036
8816 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0505037 | This project provides for the installation of a new signal on Renaissance Parkway at the ATT Crossing and at the Mall Site Drive to improve access and safety in Durham County. This project includes T | Safety/Traffic Management | 2009-09-22 | 2010-01-15 | 2010-09-12 |  | 207640 | 0.000 | 0505037
8817 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505039 | This project will remove the free flow traffic turn lane in Durham at the intersection of SR 1670 (Greer Street) and Miami Boulevard to improve safety a the intersection in Durham County. This is a locally administered project by the City of Durham. | Pavement Improvement | 2009-09-16 | 2010-05-11 | 2010-07-02 |  | 44789 | 0.000 | 0505039
8818 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505040 | The project will provide for replacement of trees in Durham along Duke and Gregson streets to improve neighborhood appearance in Durham County. This is a locally administered project by the City of Durham. | Transportation Enhancements | 2009-09-21 | 2010-01-10 | 2010-04-10 |  | 89792 | 0.000 | 0505040
8819 | NORTH CAROLINA | Underway | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505042 | This project will construct neighborhood accesses to the Third Fork Creek Greenway to improve community access in Durham County. This is a locally administered project by the City of Durham. | Transportation Enhancements | 2009-09-22 | 2010-01-18 | 2010-10-15 |  | 731367 | 0.000 | 0505042
8820 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505043 | This project will resurface asphalt on the North-South Greenway Trail in Durham from Lavender Street to Murray Avenue to improve pavement life and ride quality in Durham County. U-4726HI includes TIP | Transportation Enhancements | 2009-09-16 | 2010-05-07 | 2010-07-31 |  | 330488 | 0.000 | 0505043
8821 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM | DURHAM | 02 | 0505050 | U-3804 - This project will widen to multi-lanes by improving grading, paving, drainage and installing signals on SR 1321 (Hillandale Road) from I-85 to north of SR 1407 (Carver Avenue) in Durham County, North Carolina. | Pavement Widening | 2010-06-16 | 2010-09-30 | 2012-06-15 | 2012-12-10 | 2658263 | 0.836 | 0505050
8822 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | Multiple | 0520028 | This project will construct the Neuse River Greenway pedestrian and bicycle facilities from Falls Lake Dam to the South Soccer Complex on SR 2006 (Perry Creek Road) in Wake County. This project is locally administered by the City of Raleigh. | Transportation Enhancements | 2009-08-28 | 2010-01-19 | 2011-03-19 |  | 3250000 | 0.000 | 0520028
8823 | NORTH CAROLINA | Completed | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0520038 | EB-4978 - This Project Will Construct The Edwards Mill Road Greenway, A Multi-use Path On Edwards Mill Road Extension From Reedy Creek Road to Trinity Road in Wake County, North Carolina. | Transportation Enhancements | 2010-09-20 | 2011-02-28 | 2011-10-15 | 2011-10-25 | 425000 | 0.000 | 0520038
8824 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0527006 | This project provides for the construction of the Dunn Creek Greenway to improve pedestrain access and safety from Smith Creek Soccer Center to the NC 98 Bypass in Wake County. This is a locally administered project by the Town of Wake Forrest. | Transportation Enhancements | 2009-09-16 | 2010-01-22 | 2010-07-23 |  | 450000 | 0.000 | 0527006
8825 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0529001 | This project provides for the construction of crosswalks at Athird and Main Streets to improve pedestrain safety and mobility in Wake County. This is a locally administered project by the Town of Wendell. | Transportation Enhancements | 2009-09-10 | 2010-02-01 | 2010-03-13 |  | 33810 | 0.000 | 0529001
8826 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0529002 | This project provides for the construction of 4500 feet of sidewalk in Wendell along Third Street and Buffaloe Road to improve pedestrian access to the park in Wake County. This is a locally administered project by the Town of Wendell. | Transportation Enhancements | 2009-08-14 | 2010-02-15 | 2010-06-30 |  | 375749 | 0.300 | 0529002
8827 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0532003 | This project constructs sidewalk in Zebulon on West Judd Street from North Wakfield Street to North Church Street in Wake County. This is a locally administered project by the Town of Zebulon. | Transportation Enhancements | 2009-09-08 | 2010-02-08 | 2010-04-08 |  | 71923 | 0.000 | 0532003
8828 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0540015 | Widen ramp from I-540 west to I-40 west in Durham and Wake Counties, and add merge lane on I-40 westbound between I-540 and Page Road in Durham County, to reduce congestion. | Pavement Improvement | 2009-12-17 | 2010-04-01 | 2010-12-31 |  | 3835029 | 7.767 | 0540015
8829 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 0540016 | Resurface I-540 in Wake County from north of I-40 to US 70 to improve road condition | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2010-05-27 | 2011-01-24 | 2569522 | 3.800 | 0540016
8830 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 0540018 | The project will provide for landscape enhancement in Knightdale at the interchange of I-540 and US 64 in Wake County. This is a locally administered project by the Town of Knightdale. | Transportation Enhancements | 2009-09-16 | 2010-03-24 | 2010-06-13 |  | 117128 | 0.000 | 0540018
8831 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HERTFORD |  | 01 | 0561020 | This project will widen and resurface NC 561 from NC 11 to Northampton County in Hertford County to improve road condition. | Pavement Widening | 2009-07-20 | 2011-03-01 | 2011-06-30 | 2011-06-30 | 1919494 | 10.210 | 0561020
8832 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0700008 | This project will repave NC 700 in Rockingham County from the Dan River to SR 1902 (Dibrell Road) to improve road condition. | Pavement Improvement | 2010-03-01 | 2010-04-15 | 2010-05-29 | 2011-01-24 | 870044 | 8.671 | 0700008
8833 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | 06 | 0701018 | This project provides for the replacement of existing signal poles & mast arms at the SR 1300 (University Drive) and Rural Retreat Road intersection to improve road conditions in Alamance County. Includes TIP projects U-5154, U-5165, U-5166. | Safety/Traffic Management | 2009-08-05 | 2009-08-05 | 2011-06-30 | 2011-04-13 | 409512 | 0.000 | 0701018
8834 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701019 | This project provides for the replacement of existing signal poles & mast arms at the SR 1300 (University Drive) and Bonner Bridge Road intersection to improve road conditions in Alamance County. | Other | 2009-08-04 | 2009-08-04 | 2009-10-09 | 2009-10-09 | 455 | 0.000 | 0701019
8835 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BLADEN |  | Multiple | 0701020 | This project will construct bicycle lanes on US 701 between Elizabethtown and White Lake for approximately 6 miles by widening the existing paved shoulder to four feet on both sides in Bladen County. | Transportation Enhancements | 2009-08-07 | 2009-08-07 | 2010-06-01 | 2010-03-08 | 466764 | 5.300 | 0701020
8836 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701022 | This project provides for the construction of sidewalks, including curb and gutter to improve pedestrian mobility and safety on Piedmont Street from SR 1785 (Sellars Mill Road) to the Cummings High S | Transportation Enhancements | 2009-09-21 | 2010-03-27 | 2010-03-20 |  | 25611 | 0.000 | 0701022
8837 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701023 | This project provides for the construction of sidewalk and the installation of pedestrian signals to improve pedestrian safety and mobility on US 70 (Church Street)/SR 1158 (Huffman Mill Rd) from SR | Transportation Enhancements | 2009-12-21 | 2010-04-05 | 2010-06-30 | 2010-11-10 | 52463 | 0.000 | 0701023
8838 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701024 | This project provides for the construction of an ADA-compliant crosswalk and sidewalk to improve pedestrian mobility and safety on SR 1158 (Huffman Mill Road) and Forestdale Drive in Alamance County. | Transportation Enhancements | 2009-12-21 | 2010-04-05 | 2010-06-30 | 2010-11-10 | 53208 | 0.000 | 0701024
8839 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701025 | EB-5118GE - This project will construct sidewalks along Huffman Mill Road including a crosswalk at South Church Street in Burlington, Alamance county, North Carolina. | Other | 2010-02-09 |  |  |  | 16200 | 0.000 | 0701025
8840 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 0701026 | EB-5118GF - This project will construct sidewalks along Forestdale Drive including a crosswalk at Huffman Mill Road in Burlington, Alamance county, North Carolina. | Other | 2010-02-09 |  |  |  | 3762 | 0.000 | 0701026
8841 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0702015 | This project provides for the construction of Bus Stop Shelters to improve pedestrain mobility and safety at various locations in Carboro in Orange County. This is a locally administered project by the Town of Carrboro. | Transportation Enhancements | 2009-07-29 | 2009-08-27 | 2010-06-23 |  | 76357 | 0.000 | 0702015
8842 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0702016 | This project proivdes for the construction of sidewalk on one side of Ashe Street from West Main Street to Shelton Street in Carrboro in Orange County. This is a locally administered project by the Town of Carrboro. | Other | 2009-09-09 | 2010-03-18 | 2010-06-28 |  | 128659 | 0.000 | 0702016
8843 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0702017 | This project provides for the construction of sidewalk on one side of Bim Street from SR 1005 (Jones Ferry Rd) to Fidelity Street in Carrboro in Orange County. This is a locally administered project by the Town of Carrboro. | Transportation Enhancements | 2009-09-09 | 2010-03-18 | 2010-06-28 |  | 144238 | 0.000 | 0702017
8844 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0703014 | This project will upgrade the citywide traffic signal system at 124 intersections and install fiber optic communications cable in Chapel Hill / Orange County to reduce congestion and emissions and improve mobility. | Safety/Traffic Management | 2009-08-05 | 2009-08-05 | 2012-08-01 |  | 5686446 | 0.000 | 0703014
8845 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0703015 | This project provides for the construction of ADA Ramps to improve pedestrian mobility and safety at seven (7) selected locations in Chapel Hill in Orange County. This is a locally administered project by the Town of Chapel Hill. | Transportation Enhancements | 2009-09-21 | 2010-01-13 | 2010-06-24 |  | 50000 | 0.000 | 0703015
8846 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0703016 | This project proides for the construction of raised crosswalks and traffic calming devices at eight (8) selected locations in Chapel Hill in Orange County. This is a locally administered project by the Town of Chapel Hill. | Safety/Traffic Management | 2009-09-21 | 2010-01-13 | 2010-06-24 |  | 64372 | 0.000 | 0703016
8847 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE | DURHAM | 04 | 0703017 | This project provides for the construction of pedestrian safety improvements, pedestrain refuge islands, at one (1) location on NC 86 (Martin Luther King, Jr. Drive) and four (4) locations on east Fra | Transportation Enhancements | 2009-07-29 | 2009-08-05 | 2010-06-24 |  | 403550 | 0.000 | 0703017
8848 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0705004 | This project provides for the construction of sidewalk to improve pedestrian mobility on the West side of Oak Street from East Trollinger Street to Truitt Drive in Guildford County. This is a locally administered project by the Town of Elon. | Transportation Enhancements | 2009-12-08 | 2010-03-08 | 2010-06-07 |  | 53894 | 0.200 | 0705004
8849 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0708022 | This project provides for the construction of Phases IV and V of the Bicentenial Greenway, multi-use path and sidewalk, to improve pedestrin safety and mobility, from Ballinger Road to Market Street i | Transportation Enhancements | 2009-08-28 | 2010-03-31 | 2011-05-28 | 2011-10-25 | 548112 | 0.000 | 0708022
8850 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0708023 | This project provides for the construction of intersection improvements and sidewalk and widening Lake Jeanette Road from Lawndale Drive to SR 2348 (Bass Chapel Road/Elm Street) to improve safety and | Pavement Widening | 2009-09-17 | 2010-02-08 | 2011-05-23 |  | 2960151 | 0.000 | 0708023
8851 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0708024 | This project provides for the construction of pedestrain improvements by replacing the median turn lane on South Elm-Sugene Street from JJ Drive to Vandalia Road to improve safety and mobility in Gree | Pavement Improvement | 2009-09-01 | 2010-01-25 | 2010-09-15 |  | 1678417 | 0.000 | 0708024
8852 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | Multiple | 0708025 | This project will repave Holden Road from SR 4121 (High Point Road) to Pinecroft Road, Cone Boulevard form Elm Street to Summitt Avenue, Friendly Avenue from Radience Drive to Elam Avenue and Smith St | Pavement Improvement | 2009-08-04 | 2010-03-23 | 2010-09-03 | 2011-02-23 | 1264826 | 0.000 | 0708025
8853 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0710021 | The project (EB-5118GH) will construct Sidewalks on the north side of SR 1486 (Lexington Avenue) from the High Point Greenway to SR 1471 (Montlieu Avenue) and on the south side from the High Point Gre | Transportation Enhancements | 2009-12-21 | 2010-03-15 | 2010-05-15 | 2011-02-10 | 107136 | 0.200 | 0710021
8854 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0711011 | This project provides for the construction of sidewalks to improve pedestrian safety and mobility on Nash Street, Faucette Mill Street, Revere Road, Hayes Street, Union Street, Eno Street and Allison | Transportation Enhancements | 2009-09-22 | 2010-03-01 | 2010-12-21 |  | 319459 | 0.000 | 0711011
8855 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0729002 | This project provides for the acquisition of right-of-way to construct trailhead parking area to access the Lake Brandt Greenway on US 220 North of Strawberry Road in Guildofrd County. This is a locally administered project bu the Town of Summerfield. | Transportation Enhancements | 2009-08-18 | 2010-05-27 | 2010-12-31 | 2011-02-24 | 266008 | 0.000 | 0729002
8856 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHATHAM | DURHAM | 02 | 0751023 | This project will construct left turn lanes and a traffic signal on NC-751 at the intersection of O'Kelly Church Road in Chatham County to ease congestion. | Safety/Traffic Management | 2009-08-18 | 2010-03-16 | 2009-04-30 | 2010-10-26 | 393000 | 0.000 | 0751023
8857 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROCKINGHAM |  | Multiple | 0770003 | This project will construct curb & gutter and sidewalk to improve pedestrian mobility on the north side of NC 770 from Westridge Apartments to SR 1405 (South Glenn Street) in Rockingham County. Thi | Transportation Enhancements | 2009-11-09 | 2010-03-05 | 2010-05-15 | 2011-02-10 | 295703 | 1.500 | 0770003
8858 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 0771192 | Rehabilitate pavement on I-77 from US 21 (Exit 79) to milepost 84 in Surry and Yadkin Counties to improve road condition. | Pavement Improvement | 2009-04-21 | 2009-04-21 | 2009-12-31 | 2010-11-01 | 3497918 | 10.200 | 0771192
8859 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0771194 | The project (I-5128) will paint bridges at selected locations on Interstate 77 from Nations Ford Road to Catawba Avenue in Mecklenburg county. | Other | 2009-05-13 |  |  |  | 2708 | 0.000 | 0771194
8860 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | YADKIN |  | Multiple | 0771195 | Rehabilitate pavement on I-77 from Iredell County line to south of SR 1125 (Asbury Church Rd) in Yadkin County to improve road condition. | Pavement Improvement | 2009-09-08 | 2010-05-07 | 2010-07-01 | 2010-10-27 | 1057392 | 6.240 | 0771195
8861 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 0771196 | Rehabilitate pavement on I-77 from mile post 88.4 to mile post 90 in Surry County to improve road condition. | Pavement Improvement | 2009-08-06 | 2009-08-06 | 2009-11-20 | 2010-10-05 | 336992 | 3.200 | 0771196
8862 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 0771197 | Paint bridges carrying I-77 over NC 89 and I-74 eastbound lane in Surry County to extend the life of the structures. | Bridge Improvement | 2009-05-01 | 2010-08-11 | 2010-10-23 | 2011-02-10 | 586574 | 0.000 | 0771197
8863 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 0771198 | This project will construct a linear wetland at the I-77 Welcome Center in Mecklenburg County, NC. The purpose of this project is to treat stormwater runoff from the Welcome Center parking lot helpin | Other | 2009-12-07 |  | 2010-03-01 | 2010-03-11 | 87218 | 0.000 | 0771198
8864 | NORTH CAROLINA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | IREDELL |  | Multiple | 0771199 | This project will construct a stormwater wetland, at the I-77SB Rest Area in Iredell County, to treat stormwater runoff from the Rest Area and a portion of the roadway before discharging into Lake Nor | Other | 2009-10-30 | 2010-02-08 | 2010-04-30 |  | 125071 | 0.000 | 0771199
8865 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | IREDELL |  | Multiple | 0771200 | The project will install landscape enhancement plantings at the I-77 and Langtree Road interchange in Iredell County. | Transportation Enhancements | 2009-08-05 | 2009-08-05 | 2009-12-15 | 2009-12-29 | 148120 | 0.000 | 0771200
8866 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0771201 | This project provides for the cleaning and painting of bridges 136, 120 and 85 on I-77 from Nations Ford Road to Catawba Avenue in Mecklenburg County to extend the life of the structures. | Bridge Improvement | 2009-09-09 | 2010-06-23 | 2011-08-05 |  | 1033000 | 0.000 | 0771201
8867 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LEE |  | Multiple | 0837005 | This project will construct the Endor Iron Furnace Greenway in Sanford which is a 10 feet wide paved asphalt multi-use greenway trail from Kiwanis Family Park on Carbonton Road to Boone Drive (approxi | Transportation Enhancements | 2009-08-14 | 2010-01-12 | 2010-10-12 |  | 554171 | 0.000 | 0837005
8868 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | Multiple | 0851114 | Interchange Planings On I-85 At Exit 26 In Belmont In Gaston County, North Carolina | Transportation Enhancements | 2010-01-21 | 2010-03-15 | 2011-04-29 | 2010-05-07 | 89696 | 0.000 | 0851114
8869 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CLEVELAND |  | 10 | 0851116 | I-5403 - This Project Will Mill And Fill I-85 From The South Carolina State Line To Milepost 7.2 In Cleveland County And Refurbish The Ramps At Exit 22 In Gastonia, Gaston County, North Carolina. | Pavement Improvement | 2010-08-13 | 2011-02-22 | 2011-06-24 | 2011-06-24 | 3465883 | 14.970 | 0851116
8870 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CABARRUS |  | Multiple | 0852067 | This project will rehabilitate existing pavement on I-85 from US 29/601 to NC 73 in Cabarrus County to improve road condition. | Pavement Improvement | 2009-03-27 | 2009-03-27 | 2009-10-30 | 2009-12-18 | 2647031 | 6.680 | 0852067
8871 | NORTH CAROLINA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | Multiple | 0852068 | Mill and resurface I-85 from mile post 21.8 to mile post 23.5 in Gaston County to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2009-11-02 | 2010-04-21 | 1007108 | 3.600 | 0852068
8872 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 0852069 | This project will construct a wetland and provide credit for excess stabilization on the Northbound side of I-85 near the bridge crossing over Mallard Creek in Mecklenburg County. The purpose is to t | Other | 2009-10-19 | 2010-04-06 | 2009-04-30 | 2010-04-29 | 29113 | 0.000 | 0852069
8873 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CABARRUS |  | Multiple | 0852070 | This project will renovate the existing pair of?rest area buildings located on I-85, west of Concord at Mile Post 59 into vending,?security offices?and storage, construct a new pair of restroom buildi | Pavement Improvement | 2009-08-05 | 2009-12-01 | 2010-10-15 |  | 1719300 | 0.000 | 0852070
8874 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 0853195 | This project provides for resurfacing I-85 in Guilford County from US 29-70/Business 85 to Groometown Road to improve road condition. | Pavement Improvement | 2009-04-15 | 2009-04-15 | 2010-08-13 | 2010-12-01 | 2684768 | 2.800 | 0853195
8875 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DAVIDSON |  | 06 | 0853200 | This project will renovate the existing pair of?rest area located on I-85, south of Thomasville at Mile Post 100 into vending,?security offices?and storage, construct a new pair of restroom buildings | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2010-08-15 | 2010-12-17 | 1944158 | 0.000 | 0853200
8876 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD | GREENSBORO | 06 | 0853201 | Install pavement marking reflectors and replace damaged/missing reflectors on I-85 in Guilford County, between Groomtown Road (milepost 131) and I-40 / I-85 junction east (milepost 120) of Greensboro, to improve nighttime visibility. | Pavement Improvement | 2009-08-05 | 2009-09-24 | 2010-05-01 | 2010-10-26 | 441444 | 22.000 | 0853201
8877 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 0853202 | Install pavement marking reflectors and replace damaged/missing reflectors on I-85 in Guilford County, between NC 62 near Archdale and Business 85 in Greensboro, to improve nighttime visibility. | Pavement Improvement | 2009-08-05 | 2009-09-24 | 2010-05-01 | 2010-10-26 | 101102 | 6.000 | 0853202
8878 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0853204 | The project will provide reforestation along I-73 and I-85 at Various Locations in Guilford County, south of Greensboro | Transportation Enhancements | 2009-11-17 |  | 2012-04-30 | 2012-06-01 | 58432 | 0.000 | 0853204
8879 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DAVIDSON |  | Multiple | 0853205 | The project will renovate landscaping south of Thomasville at the I-85 Rest Area Vietnam Memorial in Davidson County. | Transportation Enhancements | 2009-12-02 | 2009-12-07 | 2011-03-31 | 2011-03-10 | 60000 | 0.000 | 0853205
8880 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 0853206 | The proejct (ER-5100GF) wil provide corridor plantings on Interstate 85 from Groometown Road (milepost 120) to I-85/I-85 Business (milepost 118) in Guilford county. | Transportation Enhancements | 2009-12-21 | 2010-03-09 | 2012-05-28 | 2012-05-28 | 85000 | 2.000 | 0853206
8881 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 0854113 | Resurface I-85 in Orange County from I-40 / I-85 interchange to SR 1006 (Orange Grove Road) to improve road condition. | Pavement Improvement | 2009-09-08 | 2010-04-11 | 2010-07-16 | 2011-04-20 | 1881209 | 1.466 | 0854113
8882 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 0854114 | The project (R-5164A) will mill asphalt from existing pavement and resurface on Interstate 85 from the Orange county line to SR 1401 (Cole Mill Road); NC 147 from I-85 to the end of asphalt roadway ne | Pavement Improvement | 2009-12-17 | 2010-08-04 | 2010-12-16 | 2011-08-23 | 5575120 | 19.432 | 0854114
8883 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0909004 | This project constructs 481 square yards of sidewalk in Kernersville along the west side of Oakhurst Drive from Cherry St north past Lambeth Farm Lane to enhance pedestrian safety in Forsyth County. | Transportation Enhancements | 2009-07-14 | 2010-05-20 | 2010-06-30 |  | 54140 | 0.000 | 0909004
8884 | NORTH CAROLINA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROWAN |  | Multiple | 0914027 | This project will construct the Grants Creek Greenway Bicycle Trail in Salisbury which is a 12 feet wide, paved greenway trail from Hogan's Valley Way to Forestdale Drive in Rowan County. This is a locally administered project by the City of Salisbury. | Transportation Enhancements | 2010-01-06 | 2010-11-08 | 2011-03-07 |  | 493764 | 0.000 | 0914027
8885 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0918068 | This projects constructs new sidewalk & installs one bus shelter and required retaining walls in Winston-Salem on east side of New Walkertown Road from Waterworks Road to Spaulding Drive to enhance pe | Transportation Enhancements | 2009-08-14 | 2010-03-01 | 2010-03-02 |  | 110643 | 0.000 | 0918068
8886 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0918069 | This project constructs new sidewalk and installs two bus shelters in Winston-Salem on east side of Peters Creek Parkway from Brewer Road to the existing sidewalk and from existing sidewalk to the bus | Transportation Enhancements | 2009-08-14 | 2009-09-24 | 2010-03-02 |  | 83569 | 0.000 | 0918069
8887 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0918070 | This project provides intersection improvements in Winston-Salem along Shattalon Drive intersections from Murray Road to Bright Oak Avenue to improve safety in Forsyth County. This is a locally administered project by the City of Winston-Salem. | Safety/Traffic Management | 2009-06-23 | 2009-09-24 | 2010-08-25 |  | 292000 | 0.400 | 0918070
8888 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0923003 | This project will construct 725 feet of sidewalk in Walkertown on East Friendly Road from SR 2004 (Main Street) to Willoughby Drive with high visibility improvements to the Friendly Road/Walkertown El | Transportation Enhancements | 2009-06-05 | 2010-01-06 | 2010-03-05 |  | 28790 | 0.000 | 0923003
8889 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0923004 | This project will construct 617 feet of 5 feet wide concrete sidewalk in Walkertown on the east shoulder of Morris Street between Old Hollow Road (NC 66) and New Walkertown Road (US 311) to enhance pe | Transportation Enhancements | 2009-07-14 | 2010-02-08 | 2010-03-05 |  | 23050 | 0.000 | 0923004
8890 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0926003 | This project constructs 5,750 feet of sidewalk and required storm drainage in the Village of Clemmons on Middlebrook Drive between Idols Road and Greenbrook Drive to enhance pedestrian safety in Forsy | Transportation Enhancements | 2009-07-02 | 2010-01-25 | 2010-04-24 |  | 153819 | 1.100 | 0926003
8891 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0927003 | This project constructs a roundabout in Lewisville at the Lewisville-Concord Church Road/US 421/Williams Road intersection to improve safety in Forsyth County. This is a locally administered project by the Town of Lewisville. | Pavement Improvement | 2010-01-21 | 2010-05-19 | 2010-11-30 | 2011-04-20 | 322765 | 0.020 | 0927003
8892 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CUMBERLAND |  | Multiple | 0951080 | This the preliminary engineering for the project that will renovate and improve existing landscape enhancements at the interchange of I-95 and NC 87 in Cumberland County. | Other | 2009-07-13 | 2009-07-13 |  |  | 186 | 0.350 | 0951080
8893 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROBESON |  | 07 | 0951081 | The project will renovate and improve existing landscape enhancement along I-95 between Mile Post 4 through 30 in Robeson County | Transportation Enhancements | 2009-09-24 | 2009-12-29 | 2010-02-27 | 2010-03-22 | 110633 | 0.000 | 0951081
8894 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CUMBERLAND |  | Multiple | 0951082 | The project (ER-5100FD) will renovate plantings on Interstate 95 and NC 87 at exit 46 in Cumberland county. | Transportation Enhancements | 2009-10-23 | 2010-03-22 | 2010-05-28 | 2010-05-21 | 210170 | 0.350 | 0951082
8895 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ROBESON |  | 07 | 0951083 | The project (ER-5100FE) will provide reforestation on Interstate 95 from mile marker 3 to mile marker 5 in Robeson county. | Transportation Enhancements | 2009-10-28 | 2010-03-22 | 2010-04-02 | 2010-03-25 | 11875 | 2.000 | 0951083
8896 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | Multiple | 0952114 | Resurface I-95 from North of US 70 to North of Main Street in Johnston County to improve road condition. | Pavement Improvement | 2009-09-11 | 2010-03-31 | 2010-08-01 | 2011-12-01 | 2217715 | 14.600 | 0952114
8897 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CUMBERLAND |  | Multiple | 0952115 | This project will provide landscape enhancement at the I-95 Rest Area near Mile Post 48 in Cumberland County. | Transportation Enhancements | 2009-09-24 |  | 2012-06-24 | 2012-07-31 | 122322 | 0.000 | 0952115
8898 | NORTH CAROLINA | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WILSON |  | Multiple | 0953104 | This is the preliminary engineering for the project that will focus on landscape enhancement at the interchanges US 264/US 264 Alt & I-95 / US 264 in Wilson County. | Transportation Enhancements | 2009-07-09 | 2009-07-09 | 2010-12-15 |  | 152990 | 0.070 | 0953104
8899 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STATEWIDE |  |  | 0953105 | This project provides for pavement rehabilitation and resurfacing I-95 from south of the Nash County line (Milepost 123) in Wilson County to south of NC 58 (Milepost 128) in Nash County to improve road condition. | Pavement Improvement | 2009-09-09 | 2010-05-26 | 2010-08-15 | 2011-04-05 | 1507260 | 9.000 | 0953105
8900 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH |  | 05 | 0999007 | This project constructs sidewalk in Rural Hall on NC 66 between Paso Street and Wall Street and constructs sidewalk and curb and gutter along Park Street between NC 66 and Church Street to improve ped | Transportation Enhancements | 2009-06-12 | 2010-03-01 | 2010-05-14 |  | 147316 | 0.200 | 0999007
8901 | NORTH CAROLINA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 1001052 | The project (E-4129B) will construct the Snyder Greenway from Salisbury Avenue to Depot Street in Albemarle, Stanley county. | Transportation Enhancements | 2009-11-02 | 2010-03-08 | 2010-06-23 |  | 281777 | 0.000 | 1001052
8902 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1003085 | This project will design the upgrade and expansion of Charlotte's Intelligent Transportation System (ITS) Communications backbone which will provide for on-the-fly remote operation of Traffic Signaliz | Safety/Traffic Management | 2009-05-06 | 2009-05-21 | 2011-12-22 |  | 1227777 | 0.000 | 1003085
8903 | NORTH CAROLINA | Underway | C220,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1003086 | This project includes the construction of two miles of the Toby Creek Greenway in Charlotte from Mallard Creek Greenway near US 29 to University Blvd (NC 49) to improve pedestrian access in Mecklenbur | Transportation Enhancements | 2009-09-22 | 2009-09-22 | 2011-01-27 |  | 1239772 | 0.000 | 1003086
8904 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1003089 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the South Charlotte area including surveillance system along Providence Road, Ballentyne Commons Parkway and NC 51 | Safety/Traffic Management | 2009-09-09 | 2009-09-09 | 2010-10-15 |  | 629362 | 0.000 | 1003089
8905 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 1003090 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the Northwest Charlotte area including surveillance system along Beatties Ford Road, Sunset Road, Statesville Road | Safety/Traffic Management | 2009-05-19 | 2009-10-15 | 2010-12-15 |  | 1037565 | 0.000 | 1003090
8906 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 1003091 | This project will include the installation of the Traffic Signal Fiber Optic Cable in the University area (Northwest Charlotte) including surveillance system along W. T. Harris, The Plaza, North Tryon | Safety/Traffic Management | 2009-10-15 | 2009-10-15 | 2010-12-15 |  | 1018904 | 0.000 | 1003091
8907 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1003093 | The project (EB-5118JC) will construct pedestrian signals and crosswalk markings at various locations in Charlotte, Mecklenburg County. | Transportation Enhancements | 2009-10-14 | 2009-10-20 | 2010-11-19 |  | 374624 | 0.000 | 1003093
8908 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 1003094 | The project (EB-5118JD) will install a sidewalk along Shasta Lane from Randolph Road to Sardis Road in Charlotte, Mecklenburg county. | Transportation Enhancements | 2009-10-20 | 2009-10-20 | 2010-08-15 |  | 348697 | 0.000 | 1003094
8909 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 1004039 | This project will repave Old Oxford Road in Durham County from Roxboro Street to Granville County line to improve road condition. | Pavement Widening | 2009-05-13 | 2009-05-13 | 2010-05-14 | 2010-12-01 | 1946021 | 16.620 | 1004039
8910 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1006034 | The project (EB-5118JB) will construct the West Branch Rocky River Greenway from River Ford Drive eastward along West Branch Rocky River for 1.1 miles in Davidson, Mecklenburg county. | Transportation Enhancements | 2009-10-20 | 2009-10-20 | 2011-04-07 |  | 517767 | 0.000 | 1006034
8911 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | UNION | CHARLOTTE | Multiple | 1008020 | This project will construct left turn lanes in Indian trail on Unionville Indian Trail Road at the intersection with Faith Church Road in Union County to improve safety. | Pavement Improvement | 2009-05-13 | 2009-05-13 | 2009-12-11 | 2010-04-14 | 299675 | 0.000 | 1008020
8912 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 1013002 | This project includes milling existing asphalt, patching existing asphalt, repaving existing roadway, thermoplastic long life pavement markings in Matthews from North Trade Street/Matthews-Mint Hill R | Pavement Improvement | 2009-08-18 | 2009-08-19 | 2010-06-01 |  | 653571 | 1.110 | 1013002
8913 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 1031007 | The project (EB-5118JA) will construct sidewalks on Wilgrove-Mint Hill Road from NC 51 to Jim Harper Lane in Mint Hill, Mecklenburg county. | Transportation Enhancements | 2009-10-09 | 2010-03-05 | 2010-05-31 |  | 113656 | 0.800 | 1031007
8914 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CABARRUS |  | Multiple | 1034015 | "This enhancement project will Install a Pedestrian Tunnel in Kanapolis under SR 1691 (Loop Road) to connect the City Park and Research Campus and install an 84"" Stormwater pipe to improve area drain | Transportation Enhancements | 2010-01-21 | 2011-03-14 | 2011-12-09 | 2012-05-21 | 600000 | 0.000 | 1034015
8915 | NORTH CAROLINA | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | IREDELL |  | 05 | 1100024 | Widen Brawley School Rd from Centre Church Rd to I-77 in Iredell County to improve safety and mobility. | Pavement Widening | 2009-09-15 | 2009-11-30 | 2013-07-01 |  | 22964090 | 1.203 | 1100024
8916 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GATES |  | 01 | 1100025 | This project will replace deficient Bridge #32 over Trotman Creek on SR 1100 (Carters Road) in Gates County. | Bridge Replacement | 2009-12-28 | 2010-06-21 | 2011-08-11 | 2011-09-20 | 881091 | 0.000 | 1100025
8917 | NORTH CAROLINA | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 1107016 | This project will widen Old Fayetteville Road to accommodate pedestrain, bicycle and transit traffic in Carrboro / Orange County from NC 54 to Stroud Lane to provide bike lanes, sidewalks and bus turnouts. | Transportation Enhancements | 2009-06-22 | 2009-06-22 | 2010-09-15 | 2010-11-17 | 800000 | 0.450 | 1107016
8918 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1133006 | This project adds sidewalks along the south side of SR 1133 (Main Street) in Winterville from Graham Street to Railroad Street in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-07-24 | 2009-09-11 | 2010-10-23 |  | 68463 | 0.400 | 1133006
8919 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1133007 | This project adds sidewalks along the south side of SR 1133 (Main Street) in Winterville from Mill Street to Winterville Parkway in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-07-24 | 2009-09-11 | 2010-10-23 |  | 55000 | 0.200 | 1133007
8920 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 1138016 | Paint bridges carrying SR 1138 (CC Camp Rd), SR 1131, SR 1122 (Dobbins Mill Rd), SR 1001, and SR 1345 over I-77 in Surry County to extend the life of the structures. | Bridge Improvement | 2009-05-01 | 2010-08-11 | 2010-10-23 | 2011-02-10 | 963149 | 0.000 | 1138016
8921 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1149007 | This project adds sidewalks along SR 1149 (Lee Street/Old NC 11) in Ayden from West Barwick Street to Allen Drive in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-07-14 | 2009-09-11 | 2010-08-18 |  | 75500 | 0.300 | 1149007
8922 | NORTH CAROLINA | Underway | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1149008 | This project adds sidewalks along the west side of SR 1149 (Lee Street/Old NC 11) in Ayden from the northernmost intersection of Countryaure Drive to First Street in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-09-11 | 2009-09-11 | 2010-08-18 |  | 142405 | 1.100 | 1149008
8923 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MADISON |  | 11 | 1151008 | B-3488 - This project will replace bridge #142 on SR 1151 over Big Pine Creek in Madison county, North Carolina. | Bridge Replacement | 2010-02-01 | 2010-09-27 | 2011-08-01 | 2011-12-06 | 590000 | 0.000 | 1151008
8924 | NORTH CAROLINA | Completed | C220,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | Multiple | 1213020 | EB-5119 - This project will construct the Carolina Thread Trail; Downtown Connector to Highland Rail Trail in Gastonia, Gaston county, North Carolina. | Transportation Enhancements | 2010-02-16 | 2010-09-07 | 2010-11-19 | 2011-12-10 | 850000 | 0.000 | 1213020
8925 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 1221013 | This project will replace deficient Bridge #36 over Connaritsa Swamp on SR 1221 (Charles Taylor Road) in Bertie County. | Bridge Replacement | 2009-08-21 | 2009-08-31 | 2011-02-16 | 2011-04-05 | 644792 | 0.013 | 1221013
8926 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CURRITUCK |  | Multiple | 1222012 | Replace deficient bridge carrying Tullis Creek Road over Shingle Landing Creek in Currituck County. | Bridge Replacement | 2009-03-02 | 2009-03-02 | 2009-12-01 | 2010-07-26 | 649494 | 0.000 | 1222012
8927 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BERTIE |  | 01 | 1260002 | This project will replace deficient Bridge #16 over the Cashie River on SR 1260 (Republican Road) in Bertie County. | Bridge Replacement | 2009-08-21 | 2009-08-31 | 2010-10-22 | 2011-04-20 | 791672 | 0.000 | 1260002
8928 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302043 | This project will provide safe, efficient mobility for bicyclist while making much needed repairs to Coxe Avenue in the Asheville in Buncombe County. Includes TIP project U-5177. | Transportation Enhancements | 2009-08-24 | 2010-04-15 | 2010-09-17 |  | 246340 | 0.000 | 1302043
8929 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302044 | This is an enhancement project to provide trees, shrubs and other landscape items in the downtown central business district and a Gateway locations on Lexington and Clingman Avenues, College Street me | Transportation Enhancements | 2009-08-28 | 2010-03-01 | 2010-05-04 |  | 85217 | 0.000 | 1302044
8930 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302046 | This project will provide and promote safe pedestrian facilities including the upgrade of traffic signals to for pedestrian use along Fairview Road at heavily traveled intersections in Asheville in Buncombe County. | Transportation Enhancements | 2009-08-18 | 2010-04-01 | 2010-05-04 |  | 67481 | 0.000 | 1302046
8931 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302047 | This City of Asheville plans to build sidewalks to fill in gaps along city streets and NCDOT facilities to provide safe, effective pedestrian mobility to communities and businesses within Asheville in Buncombe County. | Transportation Enhancements | 2009-09-09 | 2010-05-11 | 2010-09-17 |  | 502458 | 0.000 | 1302047
8932 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1302048 | This project includes repaving Kimberly Avenue from Edwin Place to Gracelyn Road and is focused at providing safe, efficient mobility for bicyclist while making much needed repairs in Asheville in Buncombe County. | Pavement Improvement | 2009-12-03 | 2010-03-09 | 2010-10-15 |  | 598994 | 0.000 | 1302048
8933 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 1302050 | This project consist of installing a pedestrian crosswalk with signals to allow safe travel between two schools located on either side of Overlook Road (SR 3503) in Buncombe County. | Transportation Enhancements | 2009-10-19 | 2010-03-30 | 2010-03-19 | 2010-04-19 | 7430 | 0.000 | 1302050
8934 | NORTH CAROLINA | Completed | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE |  | 11 | 1302051 | This project consist of installing sidewalk and wheelchair ramps at SR 3503 (Overlook Road) at Pinchot Drive in Buncombe County. This project is in conjunction with E-5105A. | Transportation Enhancements | 2009-10-19 | 2009-12-14 | 2010-02-19 | 2010-03-26 | 21769 | 0.000 | 1302051
8935 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MITCHELL |  | 10 | 1303007 | The project (EL-5107) will construct concrete sidewalks on SR 1260 (South Mitchell Avenue) from Bowman Middle School to NC 226 and along NC 226 from SR 1260 to SR 1211 (Cane Creek Road) in Bakersville, Mitchell county. | Transportation Enhancements | 2009-12-29 | 2010-05-11 | 2010-08-06 | 2010-08-05 | 100551 | 0.000 | 1303007
8936 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1305006 | This project will extend existing sidewalk along the US 70 in Black Mountain from Blue Ridge Road to Grovestone Road to promote walkability from surrounding neighborhoods to businesses along this rou | Transportation Enhancements | 2009-08-11 | 2010-03-22 | 2010-07-31 |  | 224971 | 1.270 | 1305006
8937 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BUNCOMBE | ASHEVILLE | 11 | 1305007 | Preliminary engineering for the Flat Creek Greenway from Cotton Avenue for Charlotte Street as a part of a larger plan to promote multimodal forms of transportation in the Town of Black Mountain and surrounding area in Buncombe County. | Transportation Enhancements | 2009-08-11 | 2009-08-19 | 2011-06-30 |  | 196503 | 0.000 | 1305007
8938 | NORTH CAROLINA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ALAMANCE |  | Multiple | 1306020 | This project will widen SR 1306 (Mebane Street) in Burlington / Alamance County from Huffman Mill Road to Chapel Hill Road to four naes with a divided media to enhance safety and improve mobility. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2011-08-15 |  | 13386283 | 2.563 | 1306020
8939 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | YANCEY |  | 11 | 1307004 | This project includes construction of 850 feet of sidewalk in Burnsville to include curb and gutter and drainage items to connect with existing sidewalks and provide safe pedestrian travel along Mitchell Branch Road (SR 1373) in Yancey County. | Transportation Enhancements | 2009-10-28 | 2010-03-15 | 2010-05-21 | 2010-10-05 | 189956 | 0.000 | 1307004
8940 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH |  | Multiple | 1316012 | Replace deficient bridge Number 82 carrying SR 1316/SR 1612 over Cypress Creek in Nash County. | Bridge Replacement | 2009-08-05 | 2009-08-05 | 2010-09-26 | 2010-10-26 | 744331 | 0.000 | 1316012
8941 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MCDOWELL |  | 11 | 1316013 | The project (EL-5106) will construct concrete sidewalks on SR1001 (Sugar Hill Road) from SR 1168 (Reid Street) to Wilhemenia Street in Maron, McDowell county. | Transportation Enhancements | 2009-12-29 | 2010-05-11 | 2010-08-06 | 2010-08-05 | 27953 | 0.100 | 1316013
8942 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GATES |  | 01 | 1320009 | B-4521 - This project will replace bridge #26 on SR 1320 over Duke Swamp in Gates county, North Carolina. | Bridge Replacement | 2010-02-18 |  | 2012-04-09 | 2011-11-18 | 675000 | 0.000 | 1320009
8943 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 1321005 | This project will repave Hillandale Road / Fulton Street in Durham from I-85 to Erwin Road to improve road condition. | Pavement Widening | 2009-05-18 | 2009-05-18 | 2010-05-14 | 2010-12-01 | 442239 |  | 1321005
8944 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1323004 | This project adds sidewalks along the east side of SR 1323 (Arlington Boulevard) in Greenville from SR 1467 (Stantonsburg Road) to US 13 in Pitt County to improve pedestrian safety. | Transportation Enhancements | 2009-08-18 | 2009-09-11 | 2010-04-15 |  | 83471 | 0.000 | 1323004
8945 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BRUNSWICK |  | 07 | 1357005 | This project will realign the intersection of Smith Avenue and NC 130 in Brunswick County to eliminate the offset condition to improve safety and congestion. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2010-12-31 | 2012-06-18 | 6702506 | 1.225 | 1357005
8946 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | CHEROKEE |  | 11 | 1393004 | Replace deficient bridge carrying SR 1393 (Rocky Creek-Wakefield Roads) over Junaluska Creek in Cherokee County. | Bridge Replacement | 2009-04-17 | 2009-04-17 | 2009-11-15 | 2011-02-10 | 416208 | 0.000 | 1393004
8947 | NORTH CAROLINA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SURRY |  | 05 | 1396002 | Paint bridges carrying SR 1396 (Pine Ridge Rd), SR 1602, and SR 1649 (Clyde Hayes Rd) over I-77 in Surry County to extend the life of the structures. | Bridge Improvement | 2009-05-01 | 2010-08-11 | 2010-10-23 | 2011-02-10 | 385910 | 0.000 | 1396002
8948 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1413010 | This project will construct a new road around the Oakdale Cemetery in Hendersonville and will provide access from US 64 to Hendersonville Elementary and Middle schools without disturbing the cemetery | Other | 2009-08-31 | 2009-11-05 | 2010-07-01 |  | 362999 | 0.200 | 1413010
8949 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1429003 | This project will construct the Cane Creek Greenway in Fletcher which includes a 10 feet multi-use greenway trail along the banks of Cane Creek to enhance pedestrian access in Henderson County. This | Transportation Enhancements | 2009-09-21 | 2010-01-13 | 2010-06-30 |  | 213738 | 0.000 | 1429003
8950 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1429004 | This project will construct a sidewalk in Fletcher along St. Johns Road from US 25 to Fanning Bridge Road to enhance pedestrian access within the Town of Fletcher in Henderson County. This is a locally administered project by the Town of Fletcher. | Transportation Enhancements | 2009-09-21 | 2010-01-13 | 2010-06-30 |  | 343615 | 0.660 | 1429004
8951 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1429005 | U-5184 - This project will construct the Cane Creek Greenway in Fletcher, Henderson county, North Carolina | Other | 2010-02-11 |  |  |  | 40636 | 0.000 | 1429005
8952 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HENDERSON | ASHEVILLE | 11 | 1430006 | This project will construct a brick paver sidewalk in the Village of Flat Rock along US 225 and Little River Road to enhance pedestrian access within the central historic area of the Village in Haywoo | Transportation Enhancements | 2009-09-23 |  |  |  | 56034 | 0.000 | 1430006
8953 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HALIFAX |  | Multiple | 1434004 | Replace deficient bridge Number 24 carrying SR 1434 over Quankey Creek in Halifax County. | Bridge Replacement | 2010-03-15 | 2010-03-01 | 2010-07-01 | 2010-08-23 | 504723 | 0.000 | 1434004
8954 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE | RALEIGH | Multiple | 1435008 | The project (R-5169B) will mill, strengthen, and resurface SR 1435 (Old Raleigh Road) from Mason Street to SR 1521 (Lake Pine Drive) and SR 1521 (Lake Pine Drive) from SR 1435 (Old Raleigh Road) to US 64 in Wake county. | Pavement Improvement | 2009-12-15 | 2010-05-03 |  | 2011-04-20 | 451655 | 2.500 | 1435008
8955 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1467002 | U-5212 - This Project Will Mill And Resurface SR 1467 (Stantonsburg Road) From US 13-NC 11 To The End Of Curb And Gutter & Resurface From The End Of Curb And Gutter To SR 1204 (B'S Barbeque Road) In Greenville, Pitt County, North Carolina. | Pavement Improvement | 2010-08-05 | 2011-07-11 | 2011-08-19 | 2011-11-03 | 770000 | 1.700 | 1467002
8956 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 1486002 | This project will repave SR 1486/1768 (Lexington Avenue) from Montlieu Avenue to US 311 Business in High Point in Guilford County to improve ride quality and extend pavement life. | Pavement Improvement | 2009-09-14 |  | 2009-11-15 | 2011-01-24 | 512835 | 2.240 | 1486002
8957 | NORTH CAROLINA | Underway | C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD | ASHEVILLE | 11 | 1499003 | Preliminary engineering for the construction of sidewalks along Moody Farm Road terminating at Soco Road (US 19) enhancing pedestrian access within the Town of Maggie Valley in Haywood County. This i | Transportation Enhancements | 2009-08-19 | 2009-08-19 | 2010-11-29 |  | 940952 | 1.880 | 1499003
8958 | NORTH CAROLINA | Underway | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD | ASHEVILLE | 11 | 1499004 | Maggie Valley: Two Pedestrian Bridges At Jonathan Creek Along Moody Farm Road (SR 1307) In Haywood County, North Carolina | Transportation Enhancements | 2009-09-23 | 2010-04-01 | 2010-11-09 |  | 687970 | 0.000 | 1499004
8959 | NORTH CAROLINA | Completed | C250,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | BRUNSWICK |  | 07 | 1500007 | R-5216 - This Project Will Mill And Resurface SR 1500 (Midway Road) From NC 211 To US 17 Business And SR 1401 (Galloway Road) and US 17 Business to US 17 Bypass in Brunswick County, North Carolina. | Pavement Improvement | 2010-08-18 | 2011-02-01 | 2011-08-31 | 2011-10-07 | 2800000 | 7.750 | 1500007
8960 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 1515009 | B-4570 - This project will replace bridge #79 on SR 1544 over Gum Swamp Creek in Lenior county, North Carolina. | Bridge Replacement | 2010-02-11 | 2010-05-10 | 2010-09-24 | 2010-09-16 | 669494 | 0.000 | 1515009
8961 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 1538007 | This project will provide for the realignment, resurfacing, sidewalks and drainiage improvements on SR 1538 (Deep River Road) at Sunset Hollow Drive to NC 68 (Eastchester Drive) at Lake Forest Drive o | Pavement Improvement | 2009-09-23 | 2010-01-11 | 2010-11-06 |  | 1462343 | 0.500 | 1538007
8962 | NORTH CAROLINA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 1542009 | This project will relocate a portion of SR 1542 (Ridge St) and extend SR 1542 on new location from existing Ridge Street west of SR 1545 (Mountain View Church Rd) to SR 1549 (Airport Rd) in Stanly County to improve safety and mobility. | New Construction | 2009-03-02 | 2009-03-02 | 2010-12-31 | 2012-11-26 | 3969746 | 0.000 | 1542009
8963 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | LENOIR |  | Multiple | 1544005 | B-4604 - This project will replace bridge #13 on SR 1753 over Indian Wells Swamp in Pitt county, North Carolina. | Bridge Replacement | 2010-02-18 | 2010-06-17 | 2010-10-14 | 2010-11-05 | 472103 | 0.000 | 1544005
8964 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RANDOLPH |  | Multiple | 1547008 | This project will make improvements to increase mobility and safety at the intersection of SR 1547 (Finch Farm Road) at the intersection of SR 1533 (Mountain Road) and SR 3106 (Kennedy Road) in Trinity in Randolph County. | Other | 2009-09-17 | 2009-09-17 |  |  | 135000 | 0.000 | 1547008
8965 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | FORSYTH, STOKES | WINSTON-SALEM | 05 | 1611007 | Widen Doral Drive / Main Street in Forsyth and Stokes Counties, between Tobaccoville and King, to enhance safety and mobility. | Pavement Widening | 2009-04-27 | 2009-04-27 | 2011-08-15 | 2011-12-16 | 14684035 | 1.020 | 1611007
8966 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ANSON |  | 08 | 1627009 | Replace deficient bridge carrying SR 1627 (Pinkston-River Rd.) over Winston-Salem Southbound Railroad in Anson County. Includes TIP project B-4410 (replace bridge #307). | Bridge Replacement | 2009-06-22 | 2009-06-22 | 2011-09-01 | 2011-08-26 | 2874117 | 0.000 | 1627009
8967 | NORTH CAROLINA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 1666002 | This project provides for the installation of sidewalk in Durham on SR 1666 (Dearborn Drive) from SR 1004 (Old Oxford Highway) to Ruth Street to improve pedestrian access and safety in Durham County. | Transportation Enhancements | 2009-09-16 | 2010-05-04 | 2011-05-02 |  | 579977 | 6.130 | 1666002
8968 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | SCOTLAND |  | Multiple | 1674005 | This project will widen Lauchwood Drive in Laurinburg / Scotland County from US 15-401 Business to US 501 to improve traffic flow. | Pavement Widening | 2009-03-02 | 2009-03-02 | 2010-07-15 | 2010-10-09 | 2724877 | 1.200 | 1674005
8969 | NORTH CAROLINA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1708008 | This project provides for the construction of SR 1708 (Fire tower Road) from SR 1709 (Corey Road) to NC 43 to improve safety and mobility in Pitt County. This is a locally administered project by the City of Greenville. | Pavement Improvement | 2009-10-19 | 2010-03-15 | 2010-08-31 | 2011-01-24 | 344032 | 1.040 | 1708008
8970 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | WAKE |  | 04 | 1728004 | This project will repave the following roadways in Wake County to improve road condition: Wade Avenue from Faircloth Street to Capital Boulevard (Raleigh), Old Raleigh Road from Gregson Drive to Mason Street (Apex). | Pavement Improvement | 2009-08-05 | 2009-08-05 | 2010-06-11 | 2011-05-10 | 1497307 | 2.500 | 1728004
8971 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | ORANGE |  | 04 | 1733016 | U-3306 - This project will provide corridor upgrade (part on new location) by improving grading, paving, drainage and installing signals, curb & gutter, retaining wall and sidewalks on SR 1733 (Weaver | New Construction | 2010-06-16 | 2010-09-07 | 2013-06-15 |  | 6695450 | 2.838 | 1733016
8972 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | PITT |  | 01 | 1753003 | B-4568 - This project will replace bridge #67 on SR 1515 over Falling Creek in Lenior county, North Carolina. | Bridge Replacement | 2010-02-18 | 2010-07-13 | 2010-11-09 | 2011-03-15 | 666600 | 0.000 | 1753003
8973 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GASTON |  | Multiple | 1800006 | B-4519 - This project will replace Bridge #155 on SR 1800 over Little Long Creek in Gaston county, North Carolina. | Bridge Replacement | 2010-02-19 | 2010-04-19 | 2010-08-20 | 2010-08-18 | 546428 | 0.000 | 1800006
8974 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 1853001 | The project (R-4436GED) will implement environmental restoration and pollution abatement at the NCDOT west maintenance yard on Sandy Camp Road in Guilford county. | Other | 2009-11-04 |  | 2010-10-30 | 2010-10-08 | 146719 | 0.000 | 1853001
8975 | NORTH CAROLINA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | HAYWOOD |  | 11 | 1890003 | B-2988 - This project will replace bridge #13 on SR 1890 over East Fork of Pigeon River in Haywood county, North Carolina. | Bridge Replacement | 2010-02-19 | 2010-07-12 | 2011-10-14 |  | 905724 | 0.000 | 1890003
8976 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RUTHERFORD |  | Multiple | 1913003 | B-4633 - This project will replace bridge #32 on SR 1913 over Webbs Creek in Rutherford county, North Carolina. | Bridge Replacement | 2010-02-19 | 2010-12-10 | 2011-08-01 | 2011-12-06 | 732303 | 0.000 | 1913003
8977 | NORTH CAROLINA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH CAROLINA | JOHNSTON |  | 03 | 1923009 | This project will extend Booker Dairy Road from US 70 Business to Buffalo Road in Johnston County. Route will be a two lane roadway with a new bridge over the Neuse River. | New Construction | 2009-04-09 | 2009-04-09 | 2011-12-31 |  | 11673744 | 0.000 | 1923009
8978 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | NASH |  | 01 | 1945005 | Replace deficient bridge Number 69 carrying SR 1945 over Toisnot Swamp in Nash County. | Bridge Replacement | 2009-09-11 | 2009-09-11 | 2010-05-24 | 2010-07-15 | 898370 | 0.000 | 1945005
8979 | NORTH CAROLINA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RANDOLPH |  | 06 | 1952001 | The project (U-5194) will improve the intersections of SR 1952 (High Point Street) at SR 1950 (Academy Street) and SR 1989 (Tiger's Den Road) and the Walmart entrance in Randolph county. | Other | 2009-11-09 | 2010-04-26 | 2011-05-01 | 2011-06-21 | 1180122 | 0.400 | 1952001
8980 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | STANLY |  | 08 | 1968003 | Replace deficient bridge carrying SR 1968 (St. Martin Rd.) over Long Creek in Stanly County. | Bridge Replacement | 2010-01-12 | 2010-04-05 | 2010-11-15 | 2011-02-10 | 1041814 | 0.000 | 1968003
8981 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | 06 | 1970001 | Repair bridge expansion joints on 12 structures: Bridge 12 on SR 1970, Bridge 274 on US 220, Bridge 136 on SR 2254, Bridge 220 on SR 1547, Bridge 757 on US 311 Business, Bridge 287 on US 70 (Wendover | Bridge Improvement | 2009-08-05 | 2009-08-05 | 2010-05-29 | 2010-05-09 | 194826 | 0.000 | 1970001
8982 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | DURHAM |  | 02 | 1978003 | This project will repave US 158 Bypass in Granville County from US 15 to US 158 Business to improve road condition. | Pavement Widening | 2009-05-13 | 2009-05-13 | 2010-05-14 | 2010-12-22 | 186954 |  | 1978003
8983 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | RUTHERFORD |  | Multiple | 2169001 | The project will realign Brick Store Road (SR 2194) to intersect across from Pine Ridge Rd (SR 2159) and with Oakland Rd (SR 2193) at the existing signal in Forrest City in Rutherford County. The pur | Pavement Improvement | 2009-10-19 | 2010-02-23 | 2010-10-22 | 2010-07-22 | 633052 | 0.000 | 2169001
8984 | NORTH CAROLINA | Completed | C240,C230 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG | CHARLOTTE | Multiple | 2693002 | This project includes the construction of a roundabout in Davidson at the intersection of SR-2420 (East Rocky River Road) and SR 2693 (Davidson-Concord Road) to improve safety In Mecklenburg County. | Safety/Traffic Management | 2009-05-13 | 2009-05-13 | 2009-10-23 | 2010-01-27 | 482893 | 0.000 | 2693002
8985 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | GUILFORD |  | Multiple | 2825001 | The project (R-4436GD) will implement environmental restoration and pollution abatement at the NCDOT east maintenance yard on Camp Burton Road in Guilford county. | Other | 2009-09-24 |  | 2010-10-30 | 2010-10-08 | 135511 | 0.000 | 2825001
8986 | NORTH CAROLINA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH CAROLINA | MECKLENBURG |  | Multiple | 4497001 | U-5198 - This project will mill and resurface SR 4497 (Independence Point Parkway) from NC 51 to Matthews-Mint Hill Road in Matthews, Mecklenburg county, North Carolina. | Pavement Improvement | 2010-01-21 | 2010-07-14 | 2010-08-27 | 2010-12-01 | 212000 | 0.450 | 4497001
8987 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 0002017 | This Barnes County project is a enhancement project to restore the Midland Continental Depot in Wimbledon. | Transportation Enhancements | 2010-07-12 | 2010-07-30 | 2011-02-01 |  | 240531 | 0.000 | 0002017
8988 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 0008027 | This Bismarck project is an enhancement project to contstruct a shared use path at United Tribes Technical College. | Transportation Enhancements | 2010-03-01 | 2010-05-17 | 2010-07-31 |  | 170925 | 0.000 | 0008027
8989 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS |  |  | 0009030 | This Cass County project is a Structure Replacement project on a Off-System Bridge at Maple River, 6 miles East & 6 miles south of Alice. | Bridge Replacement | 2009-06-01 | 2009-08-20 | 2009-10-03 | 2010-05-11 | 487890.38 | 0.047 | 0009030
8990 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON |  |  | 0030039 | This Morton Count project is an enhancement project to construct a bike/ped facility for the Lewis and Clark Trail Phase III. | Transportation Enhancements | 2010-07-13 | 2010-07-27 | 2010-11-06 |  | 202733.99 | 0.000 | 0030039
8991 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | TOWNER |  |  | 0048010 | This Towner County project is a Structure Replacement project on Off-System Bridge Off-System - 2 Miles South & 1 Mile West of Cando. | Bridge Replacement | 2009-08-10 | 2009-09-28 | 2009-10-31 | 2010-05-04 | 271667.36 | 0.047 | 0048010
8992 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 0221069 | This Barnes County project is a Microsurfacing on CMC 221 - From10 Miles South of Valley City, N to preserve the pavement structure. | Pavement Improvement | 2009-06-23 | 2009-09-03 | 2009-09-15 | 2011-01-19 | 452095.04 | 9.607 | 0221069
8993 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BOTTINEAU |  |  | 0520055 | This Bottineau County project is a Microsurfacing on CMC 0520 - From the Souris River, E to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-06-23 | 2009-09-01 | 2010-02-03 | 233058.04 | 4.560 | 0520055
8994 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BOTTINEAU |  |  | 0547058 | This Bottineau project is an enhancement project to complete surfacing of a shared use path at Lake Metigoshe from Sam Mill corner north. | Transportation Enhancements | 2010-03-09 | 2010-06-02 | 2010-10-15 |  | 353663.26 | 0.000 | 0547058
8995 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS |  |  | 0918055 | This Cass County project is a Thin Lift Overlay on CMC 0918 - From 8 Miles West of ND 18, E to preserve the pavement structure. | Pavement Improvement | 2009-06-01 | 2009-06-11 | 2009-08-28 | 2010-04-16 | 995719 | 8.039 | 0918055
8996 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CAVALIER |  |  | 1017061 | This Cavalier County project is a Chip Seal Coat on CMC 1017 - From ND 5, N to Wales to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-08-03 | 2009-09-01 | 2010-06-11 | 221875.23 | 8.966 | 1017061
8997 | NORTH DAKOTA | Underway | C250,C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRANT |  |  | 1031012 | This NDDOT project is a thin overlay on ND 31 from the State Line north to Jct 21 to preserve the pavement structure. | Pavement Improvement | 2010-08-24 | 2010-09-09 | 2010-10-16 |  | 3745091.02 |  | 1031012
8998 | NORTH DAKOTA | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | LOGAN |  |  | 1034013 | This NDDOT project is a thin overlay on ND 34 from W Napoleon east to the south junction of ND 30, to preserve the pavement. | Pavement Improvement | 2011-01-03 | 2011-06-02 | 2011-10-15 |  | 1700000 |  | 1034013
8999 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | LOGAN |  |  | 1034015 | This NDDOT project is an intersection improvement project at the junction of ND 30 and ND 34, to improve safety. | Safety/Traffic Management | 2011-01-03 | 2011-06-02 | 2011-10-15 |  | 154771.15 |  | 1034015
9000 | NORTH DAKOTA | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | 1083071 | This NDDOT project is a structure replacement project on US 83, to replace the Sterling Railroad separation. | Bridge Replacement | 2010-02-09 | 2010-04-14 | 2011-11-05 |  | 1916030.87 | 0.100 | 1083071
9001 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | 1083078 | This NDDOT project is a surcharge project prior to a structure replacment project on US 83 for the Sterline Railroad separation. | Pavement Improvement | 2010-02-09 | 2010-04-14 | 2010-08-07 |  | 425389.69 | 0.100 | 1083078
9002 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1083086 | This Bismarck project is a Mill & Asphalt Overlay, Curb & Gutter, Marking and Video Detection on Bismarck - 7th Street from Bismarck Expressway to Boulevard Avenue to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-14 | 2009-08-10 | 2009-10-15 |  | 658920 | 1.470 | 1083086
9003 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1083087 | This Bismarck project is a Mill & Asphalt Overlay, Curb & Gutter, Marking and Video Detection on Bismarck - 9th Street from Bismarck Expressway to Boulevard Avenue to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-14 | 2009-08-24 | 2009-10-15 |  | 403664 | 1.470 | 1083087
9004 | NORTH DAKOTA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | 1083088 | This NDDOT project is a thin overlay on US 83 from Bismarck north to south of Wilton to preserve the pavement structure. | Pavement Improvement | 2010-03-16 | 2010-08-16 | 2010-10-15 |  | 5765967.84 | 19.866 | 1083088
9005 | NORTH DAKOTA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1083093 | This NDDOT project is a thin overlay on US 83 from Bismarck north to 57th Ave to preserve the pavement structure. | Pavement Improvement | 2010-03-16 | 2010-08-26 | 2010-10-15 |  | 474671.08 | 1.492 | 1083093
9006 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | KIDDER |  |  | 1094121 | This NDDOT project is a Mill & Hot Bituminous Pavement on I 94 - From County Line E TO Dawson to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-04-20 | 2010-09-19 |  | 3857048.25 | 15.574 | 1094121
9007 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | KIDDER |  |  | 1094122 | This NDDOT project is a Mill & Hot Bituminous Pavement on I 94 - From County Line TO E Dawson Interchange to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-04-20 | 2010-09-19 |  | 4552591.12 | 15.684 | 1094122
9008 | NORTH DAKOTA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | DICKEY |  |  | 1112062 | This Dickey County project is a shoulder widening and aggregate project on CMC 1112 - 9 miles west of ND 1, east to widen the pavement structure. | Pavement Improvement | 2010-05-07 | 2010-08-16 | 2010-09-25 | 2011-10-11 | 818289.17 | 4.104 | 1112062
9009 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | DIVIDE |  |  | 1249059 | This Divide County project is a Chip Seal Coat on CMC 1249 - From 9 & 18 Miles South of Noonan, N to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-07-22 | 2009-09-01 | 2010-02-18 | 159553 | 6.127 | 1249059
9010 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | EMMONS |  |  | 1515051 | This Emmons County project is a Hot Bituminous Pavement on CMC 1515 - 0.5 miles south of ND 32, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-27 | 2009-09-09 | 2009-10-01 | 2010-04-13 | 153116.46 | 0.500 | 1515051
9011 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | FOSTER |  |  | 1613054 | This Foster County project is a microsurface on CMC 1613 from ND 9 north to preserve the pavement structure. | Pavement Improvement | 2010-02-22 | 2010-06-21 | 2010-09-15 | 2011-03-29 | 484716 | 16.969 | 1613054
9012 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRANT |  |  | 1919054 | This Grant County project is a grading project on CMC 1919 from 26 miles south of Heil, north, to reconstruct the pavement structure. | Pavement Improvement | 2010-03-04 | 2010-06-21 | 2010-10-15 | 2011-03-21 | 488291.63 | 2.000 | 1919054
9013 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | 1981086 | This Bismarck project is a Hot Bituminous Pavement and Curb & Gutter on Bismarck - North 19th Street from 75' N of E Century Ave to Oregon Dr to rehabilitate the pavement structure. | Pavement Improvement | 2009-08-17 | 2009-09-02 | 2010-08-01 |  | 745124.68 | 0.280 | 1981086
9014 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1981088 | This Bismarck project is a Concrete Pavement Repair and Mill & Overlay on Bismarck - West Main Avenue from Washington Street to Memorial Highway to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-23 | 2009-07-16 | 2010-08-01 |  | 1367500 | 0.880 | 1981088
9015 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1981089 | This Bismarck project is a Mill & Asphalt Overlay on Bismarck - South Washington Street from Bismarck Expressway to 175' south of Billings Drive to rehabilitate the pavement structure. | Pavement Improvement | 2009-08-17 | 2009-09-28 | 2010-08-01 |  | 594755 | 1.000 | 1981089
9016 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH | BISMARCK-MANDAN |  | 1981091 | This Bismarck Project is an enhancement project to construct a bike/ped facility along South Washington Street. | Transportation Enhancements | 2010-03-23 | 2010-07-26 | 2010-10-29 |  | 314257.56 | 0.000 | 1981091
9017 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988026 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - Division St NE from Collins Ave to 8th Ave NE to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-08-03 | 2009-09-18 |  | 300000 | 0.511 | 1988026
9018 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988028 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 14th St NE from Collins Ave to 3rd Avenue NE to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-08-26 | 2009-09-18 |  | 150000 | 0.246 | 1988028
9019 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988029 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 3rd Ave NE from 5th St NE to 14th St NE to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-08-17 | 2009-09-18 |  | 250000 | 0.390 | 1988029
9020 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON |  |  | 1988030 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - 27th St NW from 12th Ave NW to 8th Ave NW to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-10-08 | 2010-06-30 |  | 123151.86 | 0.231 | 1988030
9021 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988031 | This Mandan project is a Mill & Asphalt Overlay, Concrete Pavement Repair and Patching on Mandan - Old Red Trail from Sunset Drive to Collins Avenue to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-09 | 2009-10-08 | 2010-06-30 |  | 332512.89 | 0.795 | 1988031
9022 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON | BISMARCK-MANDAN |  | 1988032 | This Mandan Project is an enhancement project to construct a bike/ped facility from Main St/Mandan Ave south to 3rd St Trolley Station. | Transportation Enhancements | 2010-04-19 | 2010-06-23 | 2010-10-15 |  | 385438.36 | 0.000 | 1988032
9023 | NORTH DAKOTA | Underway | C250,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2001053 | This NDDOT project is a Thin Lift Overlay on ND 1 - From W Jct I-94 N To Jct ND 26-DAZEY to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-03 | 2010-10-02 |  | 3911839.54 | 19.329 | 2001053
9024 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | LOGAN, MCINTOSH, LA MOURE |  |  | 2013028 | This NDDOT project is a Thin Lift Overlay on ND 13 - From JCT 30 East To E JCT 56 to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-09-17 | 2009-10-17 | 2010-04-29 | 2098744.99 | 19.763 | 2013028
9025 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | KIDDER |  |  | 2094081 | This NDDOT project is a Hot Bituminous Pavement on I 94 - From E Dawson Interchange To Crystal Springs to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-17 | 2010-10-02 | 2011-05-03 | 2533804.27 | 11.863 | 2094081
9026 | NORTH DAKOTA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2094082 | This NDDOT project is a Hot Bituminous Pavement on I 94 - From W Eckelson E To E ND 1-OAKES to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-17 | 2010-10-02 |  | 2887483.15 | 13.168 | 2094082
9027 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | HETTINGER |  |  | 2117056 | This Hettinger County project is a Hot Bituminous Pavement on CMC 2117 - 0.8 Miles N of ND 21, N to rehabilitate the pavement structure. | Pavement Improvement | 2010-01-07 | 2010-05-20 | 2010-10-01 | 2011-03-25 | 484084 | 5.000 | 2117056
9028 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | KIDDER |  |  | 2215054 | This Kidder County project is a Hot Bituminous Pavement on CMC 2215 - From 5 Miles South of ND 36, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-24 | 2009-09-23 | 2009-10-02 | 2010-04-26 | 687270.6 | 5.170 | 2215054
9029 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | LA MOURE |  |  | 2281034 | This NDDOT project is a Microsurfacing and Chip Seal on US 281 - From Edgeley To 1.345 MI N JCT 46 to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-24 | 2009-09-19 | 2009-12-29 | 709552.95 | 20.274 | 2281034
9030 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STUTSMAN |  |  | 2281036 | This Jamestown project is a Concrete Pavement Repair, Dowel Bar Retrofit, and Grinding on Jamestown - US 281 from 17th St SW to 4th Ave SW to rehabilitate the pavement structure. | Pavement Improvement | 2010-01-06 | 2010-05-17 | 2010-10-15 | 2011-04-13 | 518528.31 | 0.460 | 2281036
9031 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCHENRY |  |  | 2511055 | This McHenry County project is a Microsurfacing on CMC 2511 - From 7 Miles North of Granville, N to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-06-16 | 2009-09-01 | 2010-02-03 | 249923.3 | 5.006 | 2511055
9032 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCKENZIE |  |  | 2755053 | This McKenzie County project is a Hot Bituminous Pavement on CMC 2755 - From 4.5 Miles North of Keene, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-29 | 2009-08-19 | 2009-09-01 | 2011-03-01 | 264525 | 6.275 | 2755053
9033 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCLEAN |  |  | 2800009 | This McLean County project is a Microsurfacing on CMC 2828, 2836, & 2879 - County Wide to preserve the pavement structure. | Pavement Improvement | 2009-06-29 | 2009-07-09 | 2009-09-19 | 2010-03-24 | 317756.65 | 12.176 | 2800009
9034 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STUTSMAN |  |  | 2987031 | This Jamestown project is a Mill and Overlay, Signing, Striping, and Mailbox Post Replacement on Jamestown - 3rd Street E from BNSF Railroad to 87th Avenue SE to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-18 | 2009-09-05 | 2010-03-16 | 679198.39 | 2.880 | 2987031
9035 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2990024 | This Valley City project is a Mill & Asphalt Overlay on Valley City - Wintershow Road from 4th Avenue SW to 5th Avenue SE to rehabilitate the pavement structure. | Pavement Improvement | 2010-03-17 | 2010-06-14 | 2010-08-28 | 2011-03-30 | 227253.36 | 0.538 | 2990024
9036 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2990025 | This Valley City project is a Chip Seal Coat on Valley City - 7th Street SE from 5th Avenue SE to 12th Avenue SE to preserve the pavement structure. | Pavement Improvement | 2010-03-17 | 2010-06-14 | 2010-08-28 | 2011-03-30 | 29283.79 | 0.473 | 2990025
9037 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2990026 | This Valley City project is a Mill & Asphalt Overlay on Valley City - 2nd Street NW from 9th Avenue NW to Central Avenue to rehabilitate the pavement structure. | Pavement Improvement | 2010-03-17 | 2010-06-14 | 2010-08-28 | 2011-03-30 | 189045.57 | 0.545 | 2990026
9038 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BARNES |  |  | 2990027 | This Valley City project is a Mill & Asphalt Overlay on Valley City - 2nd Street NE from 3rd Ave NE to 6th Ave NE to rehabilitate the pavement structure. | Pavement Improvement | 2010-03-17 | 2010-06-14 | 2010-08-28 | 2011-03-30 | 93562.75 | 0.191 | 2990027
9039 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MORTON |  |  | 3000009 | This Morton County project is a Chip Seal Coat on CMC 3003 & 3006 - County Wide to preserve the pavement structure. | Pavement Improvement | 2009-08-03 | 2009-08-28 | 2009-09-01 | 2010-06-11 | 357242.46 | 14.485 | 3000009
9040 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RAMSEY |  |  | 3002099 | This NDDOT project is a Concrete Pavement Repair, Dowel Bar Retrofit and Grinding on US 2 - From Mauvais Coulee To Channel A to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-06-01 | 2010-09-15 | 2011-03-22 | 4151429.31 | 14.704 | 3002099
9041 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3002106 | This NDDOT project is a Thin Lift Overlay on US 2 - From Rugby E To Near Leeds to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-08-02 | 2010-10-02 | 2011-04-07 | 3430640.19 | 23.993 | 3002106
9042 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3003023 | This NDDOT project is a Hot Bituminous Pavement on ND 3 - From Rugby N TO JCT 66-Fonda to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-26 | 2009-06-24 | 2009-10-10 | 2010-04-13 | 4583614.25 | 22.957 | 3003023
9043 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BENSON |  |  | 3019042 | This NDDOT project is a thin overlay on ND 19 from Esmond east to junction ND 30 to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-07-13 | 2010-10-09 | 2011-04-11 | 1710162.57 | 12.564 | 3019042
9044 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BENSON |  |  | 3019046 | This NDDOT project is a thin overlay on ND 19 from Benson County line to Esmond to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-07-13 | 2010-10-09 | 2011-04-11 | 600617.01 | 4.082 | 3019046
9045 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RAMSEY |  |  | 3019047 | This Devils Lake project is a Mill & Asphalt Overlay on Devils Lake - ND 19 from US 2 to ND 20 (Asphalt Portion only) to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-26 | 2009-08-22 | 2009-10-01 | 2010-08-12 | 69016.01 | 0.182 | 3019047
9046 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3019050 | This NDDOT project is a thin overlay on ND 19 from junction ND 3 to the county line to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-07-13 | 2010-10-09 | 2011-04-11 | 764230.72 | 4.698 | 3019050
9047 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 3020081 | This Devils Lake project is a Mill & Asphalt Overlay on Devils Lake - ND 20 from US 2 to (RP 104.408) Urban Limits (exception 3rd St NW to 6th St NE) to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-26 | 2009-08-05 | 2009-10-01 | 2010-08-12 | 647824 | 1.504 | 3020081
9048 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RAMSEY |  |  | 3020086 | This Devils Lake project is an enhancement project to install entrance welcome signage at the city of Devils Lake at ND 20 north and south of town. | Transportation Enhancements | 2010-03-02 | 2010-05-10 | 2010-06-25 |  | 160297 | 0.000 | 3020086
9049 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MOUNTRAIL |  |  | 3100009 | This Mountrail County project is a Chip Seal Coat on CMC 3114, 3133, 3136, & 3143 - County Wide to preserve the pavement structure. | Pavement Improvement | 2009-07-21 | 2009-08-21 | 2009-09-04 |  | 264592 | 11.835 | 3100009
9050 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | NELSON |  |  | 3204064 | This Nelson County project is a Chip Seal Coat on CMC 3204 - From ND 1, E to preserve the pavement structure. | Pavement Improvement | 2009-05-22 | 2009-08-05 | 2009-08-15 | 2011-04-19 | 251632.09 | 9.993 | 3204064
9051 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PEMBINA |  |  | 3428053 | This Pembina County project is a Structure Replacement project on CMC 3428 - 6 Miles West of Pittsburg. | Bridge Replacement | 2009-07-13 | 2009-07-28 | 2009-10-31 | 2011-10-21 | 296822.75 | 0.100 | 3428053
9052 | NORTH DAKOTA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3521058 | This Pierce County project is a Chip Seal Coat on CMC 3521 - City of Rugby to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-07-23 | 2009-09-01 | 2010-04-30 | 100003.62 | 2.807 | 3521058
9053 | NORTH DAKOTA | Completed | C250 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PIERCE |  |  | 3521059 | This Pierce County project is a Chip Seal Coat on CMC 3521 - City of Rugby CMC 3521 Spur to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-07-24 | 2009-09-01 | 2010-04-30 | 33650.85 | 1.116 | 3521059
9054 | NORTH DAKOTA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RAMSEY |  |  | 3627061 | This Ramsey County project is a grading, widening, and HBP project on CMC 3627 - From the Benson County Line, N, to reconstruct the pavement structure. | Pavement Improvement | 2010-02-22 | 2010-05-31 | 2010-09-25 |  | 253804 | 3.244 | 3627061
9055 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RANSOM |  |  | 3705055 | This Ransom County project is a Chip Seal Coat on CMC 3705 - 8 miles south of ND 46, N to preserve the pavement structure. | Pavement Improvement | 2009-06-16 | 2009-08-25 | 2009-09-01 | 2010-02-18 | 185632 | 8.022 | 3705055
9056 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 3913054 | This Richland County project is a Hot Bituminous Pavement on CMC 3913 - 4 miles north of Barney, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-09-14 | 2009-10-02 | 2010-04-19 | 407833 | 4.000 | 3913054
9057 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4002084 | This NDDOT project is a Thin Lift Overlay on US 2 - From 3 Miles W Jct 52 E TO 1 Mile W Jct 83 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-03 | 2010-10-02 | 2011-06-07 | 2218137.19 | 14.192 | 4002084
9058 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4002092 | This NDDOT project is a Thin Lift Overlay on US 2 - From 3 Miles West of Jct 52 East TO 1 Mile West Jct 83 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-03 | 2010-10-02 | 2011-06-07 | 2175567.35 | 13.934 | 4002092
9059 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | ROLETTE |  |  | 4006060 | This Rolette County project is a Hot Bituminous Pavement on CMC 4006 - From 5.7 Miles West of St. John, E to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-26 | 2009-07-24 | 2009-10-09 | 2010-03-24 | 796362 | 5.667 | 4006060
9060 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | ROLETTE |  |  | 4006062 | This Rolette County project is an enhancement project to complete surfacing of a shared use path near St. John from the Horse Arena to town | Transportation Enhancements | 2010-03-02 | 2010-07-14 | 2010-10-15 |  | 94048.95 | 0.000 | 4006062
9061 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MOUNTRAIL |  |  | 4023009 | This NDDOT project is a Thin Lift Overlay on ND 23 - From JCT 8 East To Makoti to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-17 | 2009-10-10 | 2011-07-15 | 2103446.74 | 23.896 | 4023009
9062 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4023010 | This NDDOT project is a Thin Lift Overlay on ND 23 - From Makoti E To JCT US 83 to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-17 | 2009-10-10 | 2011-07-15 | 2420967.48 | 24.869 | 4023010
9063 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCLEAN, MOUNTRAIL |  |  | 4037012 | This NDDOT project is a Thin Lift Overlay on ND 37 - From JCT 23-Parshall-S TO 1 MI W ND 1804 to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-10 | 2009-10-10 | 2010-03-24 | 1880576.02 | 15.693 | 4037012
9064 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCLEAN |  |  | 4037013 | This NDDOT project is a Thin Lift Overlay on ND 37 - From 1 MI W JCT 1804 E & S TO Emmet Corner to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-10 | 2009-10-10 | 2010-03-24 | 2916300.13 | 28.112 | 4037013
9065 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCLEAN |  |  | 4083053 | This NDDOT project is a Grading, Base and Asphalt Pavement project on US 83 - From Near JCT 37 N TO 0.6 MI N Max Southbound to reconstruction the existing pavement. | Pavement Improvement | 2009-04-21 | 2009-05-20 | 2009-10-17 | 2011-07-01 | 8507134.56 | 13.358 | 4083053
9066 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | SARGENT |  |  | 4124052 | This Sargeant County project is a Hot Bituminous Pavement project on CMC 4124 - From 3.5 Miles East of ND 32, E, to rehabilitate the pavement. | Pavement Improvement | 2010-03-02 | 2010-06-30 | 2010-09-18 | 2011-03-22 | 211998 | 1.993 | 4124052
9067 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | SARGENT |  |  | 4125059 | This Sargeant County project is a Hot Bituminous Pavement project on CMC 4125 - From 1 Mile North of County Line, N, to rehabilitate the pavement. | Pavement Improvement | 2010-03-02 | 2010-06-30 | 2010-09-18 | 2011-03-22 | 317996 | 3.019 | 4125059
9068 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 4510060 | This Stark County project is a Thin Lift Overlay on CMC 4510 - From South Heart, East to preserve the pavement structure. | Pavement Improvement | 2009-07-07 | 2009-08-12 | 2009-10-16 | 2010-02-01 | 680000 | 4.871 | 4510060
9069 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRIGGS |  |  | 4612051 | This Steele County project is a Chip Seal Coat on CMC 4612 - Griggs co ln, east to ND 32 to preserve the pavement structure. | Pavement Improvement | 2009-07-07 | 2009-07-20 | 2009-09-01 | 2010-03-05 | 136481 | 8.000 | 4612051
9070 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STUTSMAN |  |  | 4718058 | This Stutsman County project is a Chip Seal Coat on CMC 4718 - From Buchanan, E to preserve the pavement structure. | Pavement Improvement | 2009-06-16 | 2009-07-14 | 2009-09-01 | 2010-02-18 | 143265.59 | 7.141 | 4718058
9071 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STUTSMAN |  |  | 4718059 | This Stutsman County project is a Chip Seal Coat on CMC 4718 - From ND 20, E to preserve the pavement structure. | Pavement Improvement | 2009-06-16 | 2009-07-14 | 2009-09-01 | 2010-02-18 | 160737.27 | 8.010 | 4718059
9072 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989070 | This Minot project is a Mill & Asphalt Overlay on Minot - 31st Ave SW from Broadway to 16th St SW to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-08-03 | 2010-07-01 | 2010-05-10 | 324719.19 | 1.009 | 4989070
9073 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989071 | This Minot project is a Mill & Asphalt Overlay on Minot - 4th Ave NW from Broadway to Bypass to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-08-03 | 2010-07-01 | 2010-05-10 | 701334 | 1.822 | 4989071
9074 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989072 | This Minot project is a Chip Seal Coat on Minot - 11th Ave S from Hiawatha to 16th St SW to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 84452.18 | 1.391 | 4989072
9075 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989073 | This Minot project is a Chip Seal Coat on Minot - 31st Ave SE from Broadway to 13th St SE to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 41050.83 | 0.987 | 4989073
9076 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989075 | This Minot project is a Mill & Asphalt Overlay on Minot - 3rd St NE from Hillcrest to Airport to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-08-04 | 2010-07-01 | 2010-05-10 | 123639.92 | 0.502 | 4989075
9077 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989076 | This Minot project is a Chip Seal Coat on Minot - 3rd St NE from Hillcrest to 5th Ave NE to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 37791.25 | 0.417 | 4989076
9078 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989077 | This Minot project is a Asphalt Overlay on Minot - 11th Ave SE from 31st St SE to 42nd St SE to rehabilitate the pavement structure. | Pavement Improvement | 2009-12-30 | 2010-06-04 | 2010-10-15 | 2011-03-07 | 143555.72 | 0.739 | 4989077
9079 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989078 | This Minot project is a Asphalt Overlay on Minot - 31st St SE from Burdick Expressway to 11th Ave SE to rehabilitate the pavement structure. | Pavement Improvement | 2009-12-30 | 2010-06-04 | 2010-10-15 | 2011-03-07 | 35548.07 | 0.254 | 4989078
9080 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989079 | This Minot project is a Mill & Asphalt Overlay on Minot - Railway Ave from 5th St NE to 13th St NE to rehabilitate the pavement structure. | Pavement Improvement | 2009-12-30 | 2010-06-07 | 2010-10-15 | 2011-03-07 | 240825.13 | 0.530 | 4989079
9081 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989080 | This Minot project is a Chip Seal Coat on Minot - 27th St from Burdick to Railway Ave to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 39592.51 | 0.657 | 4989080
9082 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989081 | This Minot project is a Chip Seal Coat on Minot - 21st Ave NW from US 83 Bypass to 20th St NW to preserve the pavement structure. | Pavement Improvement | 2009-07-17 | 2009-08-03 | 2009-09-01 | 2011-03-01 | 41305.06 | 0.625 | 4989081
9083 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989082 | This Minot project is an interior reconstruction of the Amtrak Depot in Minot - 401 1st Avenue SW. | Transportation Enhancements | 2010-03-01 | 2010-04-26 | 2010-10-01 |  | 477000 | 0.000 | 4989082
9084 | NORTH DAKOTA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 4989084 | This Minot project is a mill and bituminous pavement overlay project on 16th St SW from 20th Ave SW to 4th Ave SW, to rehabilitate the pavement. | Pavement Improvement | 2010-03-16 | 2010-06-07 | 2010-10-16 |  | 601928.25 | 1.360 | 4989084
9085 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WALSH |  |  | 5000009 | This Walsh County project is a Chip Seal Coat on CMC 5018 & 5047 - County Wide to preserve the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-07-28 | 2009-09-01 | 2010-04-29 | 296960.46 | 12.494 | 5000009
9086 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5008033 | This NDDOT project is a Thin Lift Overlay on ND 8 - From 1.4 Miles N County Line N Through Richardton to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-08-06 | 2010-10-09 | 2011-09-28 | 2297739.22 | 16.821 | 5008033
9087 | NORTH DAKOTA | Underway | C250,C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BOWMAN |  |  | 5012038 | This NDDOT project is a thin overlay on US 12 from Rhame to Bowman, to preserve the pavement. | Pavement Improvement | 2011-01-03 | 2011-10-10 | 2011-10-15 |  | 1700000 |  | 5012038
9088 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5022085 | This Dickinson project is a Slurry Seal on Dickinson - ND 22 from 8th Street SW to Heart River Bridge to rehabilitate the pavement structure. | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-09-19 | 2010-01-13 | 119278.57 | 0.682 | 5022085
9089 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BILLINGS |  |  | 5085055 | This NDDOT project is a thin overlay on US 85 from Belfield north to near Gorham junction to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-07-19 | 2010-10-16 |  | 2941631.98 | 14.610 | 5085055
9090 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5094045 | This NDDOT project is a PCC Pavement Recycle project on I 94 - From Youngmans Butte to near Eagles Nest to reconstruction the existing pavement. | Pavement Improvement | 2009-03-24 | 2009-05-01 | 2009-10-17 | 2011-03-15 | 19179650.07 | 9.193 | 5094045
9091 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5094055 | This NDDOT project is a I-94 landscaping enhancement near Dickinson - I-94 from Exit 59 to Exit 64. | Transportation Enhancements | 2009-11-10 | 2010-04-22 | 2010-10-29 |  | 253126.85 | 5.011 | 5094055
9092 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BILLINGS |  |  | 5094067 | This NDDOT project is a Slurry Seal on I 94 - From Fryburg To Belfield to preserve the pavement structure. | Pavement Improvement | 2009-04-07 | 2009-08-17 | 2009-09-01 | 2010-01-21 | 580075.65 | 7.175 | 5094067
9093 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WARD |  |  | 5153056 | This Ward County project is a Chip Seal Coat on CMC 5153 - From 4 Miles East of Surrey, N & from 17 Miles South & 1 Mile west of Sawyer, N to preserve the pavement structure. | Pavement Improvement | 2009-06-29 | 2009-07-07 | 2009-09-01 | 2009-11-10 | 626623 | 26.021 | 5153056
9094 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 5351053 | This Williams County project is a Hot Bituminous Pavement on CMC 5351 - FROM From 4 Miles South of US 2, N to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-02 | 2009-06-25 | 2009-10-01 | 2010-04-16 | 439452.04 | 3.968 | 5351053
9095 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5983038 | This Dickinson project is a Slurry Seal on Dickinson - ND 22 Frontage Roads from 8th Street SW to Heart River Bridge to rehabilitate the pavement structure. | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-09-19 | 2010-01-13 | 76312.33 | 0.500 | 5983038
9096 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5983039 | This Dickinson project is a Slurry Seal on Dickinson - 4th Avenue E from Villard to Museum Drive to rehabilitate the pavement structure. | Pavement Improvement | 2009-09-08 | 2009-09-08 | 2009-09-19 | 2010-01-13 | 119986.8 | 1.100 | 5983039
9097 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STARK |  |  | 5983040 | This Dickinson project is a Mill & Asphalt Overlay on Dickinson - 21st Street W from 10th Avenue W to 10th Ave E to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-21 | 2009-10-16 | 2010-05-14 | 647614.68 | 1.447 | 5983040
9098 | NORTH DAKOTA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STATEWIDE |  |  | 5999009 | This NDDOT project is the placement of rumble stripes on various highways within the Dickinson District, to improve safety. | Safety/Traffic Management | 2011-01-05 | 2011-04-15 | 2011-08-13 |  | 1606647.9 |  | 5999009
9099 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | NELSON |  |  | 6002078 | This NDDOT project is a Thin Lift Overlay on US 2 - From Michigan Bypass E To County Line? to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-04-29 | 2010-10-02 | 2011-05-23 | 1545715.19 | 10.189 | 6002078
9100 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PEMBINA |  |  | 6066016 | This NDDOT project is a Thin Lift Overlay on ND 66 - From S Jct 81-St. Thomas E TO I-29 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-27 | 2010-10-02 | 2011-05-23 | 1454818.11 | 11.975 | 6066016
9101 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CAVALIER |  |  | 6066017 | This NDDOT project is a Thin Lift Overlay on ND 66 - From District Boundary E TO N Jct 32 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-27 | 2010-10-02 | 2011-05-23 | 687281.16 | 8.033 | 6066017
9102 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PEMBINA |  |  | 6066018 | This NDDOT project is a Mill & Asphalt Overlay on ND 66 - From S JCT 32-Gardar E To Crystal to rehabilitate the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-27 | 2010-10-02 | 2011-05-23 | 1127031.12 | 8.127 | 6066018
9103 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | PEMBINA |  |  | 6066019 | This NDDOT project is a Thin Lift Overlay on ND 66 - From Crystal E To N Jct 81 St. Thomas to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-27 | 2010-10-02 | 2011-05-23 | 1279442.51 | 10.943 | 6066019
9104 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WALSH |  |  | 6985042 | This Grafton project is a Mill & Asphalt Overlay on Grafton - 5th Street from McHugh Avenue to Burgamott Avenue to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-12 | 2009-06-16 | 2009-10-02 | 2010-06-02 | 314166.29 | 0.600 | 6985042
9105 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WALSH |  |  | 6985043 | This Grafton project is a Chip Seal Coat on Grafton Urban Roads - 10 Sites to preserve the pavement structure. | Pavement Improvement | 2009-07-02 | 2009-07-08 | 2009-09-01 | 2010-07-30 | 209850 | 4.000 | 6985043
9106 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WALSH |  |  | 6985044 | This Grafton Project is an enhancement project to construct a bike/ped facility along ND 17 from School Road west and along Colette Ave from ND 17 south to School Road . | Transportation Enhancements | 2010-03-17 | 2010-07-14 | 2010-10-08 |  | 359491.6 | 0.000 | 6985044
9107 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986087 | This Grand Forks project is a Signals and Pavement Marking on Grand Forks - Intersection of 47th Ave S and Washington Street to preserve the pavement structure. | Pavement Improvement | 2009-06-17 | 2009-07-22 | 2009-11-01 | 2010-07-08 | 370460.42 | 0.060 | 6986087
9108 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986088 | This Grand Forks project is a Sign Replacement project on various Streets. | Other | 2009-11-03 | 2010-04-13 | 2010-07-01 | 2011-04-29 | 244972.59 | 9.118 | 6986088
9109 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986089 | This Grand Forks project is a concrete panel replacement and mill and bituminous pavement overlay project on Cherry Street from 25th Ave S to 47th Ave S, to rehabilitate the pavement. | Pavement Improvement | 2010-02-16 | 2010-07-06 | 2010-09-29 | 2011-04-11 | 874443.93 | 1.464 | 6986089
9110 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986090 | This Grand Forks project is a Chip Seal Coat on Grand Forks - University Avenue from 3rd Street N to State Street to preserve the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-03 | 2009-09-01 | 2010-01-15 | 257324.19 | 2.420 | 6986090
9111 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986091 | This Grand Forks project is a Chip Seal Coat on Grand Forks - Mill Road from Gateway Drive N to Urban limit to preserve the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-03 | 2009-09-01 | 2010-01-15 | 57000 | 1.560 | 6986091
9112 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS |  |  | 6986092 | This Grand Forks project is a Chip Seal Coat on Grand Forks - 20th Street N from Gateway Drive to University Avenue to preserve the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-03 | 2009-09-01 | 2010-01-15 | 37551.33 | 0.730 | 6986092
9113 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986093 | This Grand Forks project is a Chip Seal Coat on Grand Forks - 20th Street S from 24th Avenue S to 32nd Avenue to preserve the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-03 | 2009-09-01 | 2010-01-15 | 25319.27 | 0.480 | 6986093
9114 | NORTH DAKOTA | Completed | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986096 | This Grand Forks project is a Concrete Pavement Repair and Mill & Overlay on Grand Forks - 8th Avenue N from 3rd Street N to Columbia Road to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-08-06 | 2009-10-01 | 2010-06-23 | 365000 | 1.060 | 6986096
9115 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986097 | This Grand Forks project is a concrete panel replacement and mill and bituminous pavement overlay project on 13th Avenue S from Cherry Street to Columbia Road, to rehabilitate the pavement. | Pavement Improvement | 2010-02-16 | 2010-08-05 | 2010-11-19 | 2011-04-14 | 467635.16 | 0.928 | 6986097
9116 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986099 | This Grand Forks project is a Concrete Pavement Repair on Grand Forks - 17th Avenue S from Washington Street to 42nd Ave S to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-15 | 2009-07-27 | 2009-10-01 | 2010-06-23 | 636153.18 | 1.960 | 6986099
9117 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS | GRAND FORKS (MN) |  | 6986100 | This Grand Forks Project is an enhancement project to construct a bike/ped facility along south 42nd street from 11th Ave S to 17th Ave S. | Transportation Enhancements | 2010-02-16 | 2010-05-20 | 2010-09-29 |  | 95709 | 0.000 | 6986100
9118 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCKENZIE |  |  | 7023027 | This NDDOT project is a Hot Bituminous Pavement on ND 23 - From Watford City East TO JCT 73 to rehabilitate the pavement structure. | Pavement Improvement | 2009-05-05 | 2009-06-29 | 2009-10-10 | 2010-07-01 | 3591431.71 | 16.408 | 7023027
9119 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | MCKENZIE |  |  | 7023029 | This NDDOT project is a Thin Lift Overlay on ND 23 - From JCT 73 N&E TO Reservation Boundary to preserve the pavement structure. | Pavement Improvement | 2009-05-05 | 2009-06-29 | 2009-10-10 | 2010-07-01 | 1906034.96 | 19.291 | 7023029
9120 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7804034 | This NDDOT project is a Thin Lift Overlay on ND 1804 - From Beaver Creek W TO E BN Overpass to preserve the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-19 | 2009-10-10 | 2010-07-07 | 3287409.1 | 29.029 | 7804034
9121 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993030 | This Williston project is a Mill & Asphalt Overlay, Curb Ramps, and Driveways on Williston - 22nd St from 2nd Avenue West to University Ave to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-26 | 2009-07-07 | 2009-10-02 | 2010-04-27 | 240000 | 0.487 | 7993030
9122 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993031 | This Williston project is a Mill & Asphalt Overlay, Curb Ramps, Sidewalks, and Driveways on Williston - 22nd St E from University Ave to 12th Ave E (E Dakota Parkway) to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-26 | 2009-07-07 | 2009-10-02 | 2010-04-27 | 108686 | 0.330 | 7993031
9123 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993032 | This Williston project is a Mill & Asphalt Overlay, Sidewalk, Driveway, Valley Gutters, Curb Ramps on Williston - 26th St W from 6th Ave W to 16th Ave W to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-26 | 2009-07-07 | 2009-10-02 | 2010-05-25 | 260000 | 0.675 | 7993032
9124 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993033 | This Williston project is a Mill & Asphalt Overlay, Sidewalk, Driveway, Valley Gutters, Curb Ramps on Williston - West 2nd Avenue W Frontage Road from 6th Ave W to 42nd Street to rehabilitate the pavement structure. | Pavement Improvement | 2009-06-26 | 2009-07-08 | 2009-10-02 | 2010-05-25 | 157203.52 | 0.700 | 7993033
9125 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993035 | This Williston project is a Railroad Park enhancement and landscaping project at Railroad Park - 1 South Main Street. | Transportation Enhancements | 2009-12-23 | 2010-05-17 | 2010-11-12 |  | 210000 | 0.000 | 7993035
9126 | NORTH DAKOTA | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | WILLIAMS |  |  | 7993038 | This Williston project is a Pavement Reconstruction project on Williston - Main St from Amtrak Depot to Front St to reconstruction the existing pavement. | Pavement Improvement | 2009-12-23 | 2010-05-17 | 2010-11-12 |  | 250000 | 0.039 | 7993038
9127 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8010034 | This Fargo project is a Mill & Asphalt Overlay on Fargo - Main Avenue from 2nd Street N to 25th Street to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-29 | 2009-08-19 | 2009-10-01 |  | 495000 | 1.540 | 8010034
9128 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | SARGENT |  |  | 8011022 | This NDDOT project is a Thin Lift Overlay on ND 11 - From N Jct 32 To S JCT 32-Forman to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-12 | 2010-09-19 | 2011-03-31 | 122241.07 | 1.314 | 8011022
9129 | NORTH DAKOTA | Underway | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8011023 | This NDDOT project is a thin overlay on ND 11 from Lidgerwood east to Hankinson to preserve the pavement structure. | Pavement Improvement | 2010-01-20 | 2010-05-18 | 2010-10-09 |  | 1674622.76 | 12.693 | 8011023
9130 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8029099 | This NDDOT project is a Concrete Pavement Repair on I 29 - From ND 13 N TO Christine Interchange to rehabilitate the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-10 | 2009-09-26 | 2011-02-17 | 1348123.13 | 21.572 | 8029099
9131 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8029104 | This NDDOT project is a Concrete Pavement Repair on I 29 - From ND 13 N TO Christine Interchange to rehabilitate the pavement structure. | Pavement Improvement | 2009-03-24 | 2009-06-16 | 2009-09-26 | 2011-02-17 | 1638890.34 | 21.570 | 8029104
9132 | NORTH DAKOTA | Completed | C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | SARGENT |  |  | 8032028 | This NDDOT project is a Thin Lift Overlay on ND 32 - From SD Line to S. Jct. ND 11 to preserve the pavement structure. | Pavement Improvement | 2009-10-06 | 2010-05-12 | 2010-09-19 | 2011-03-31 | 1078471.64 | 10.196 | 8032028
9133 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8094073 | This NDDOT project is a lighting and structural repair project to improve a pedestrian underpass. | Transportation Enhancements | 2011-01-28 | 2011-05-11 | 2011-07-02 |  | 32927.11 |  | 8094073
9134 | NORTH DAKOTA | Underway | C200,C240 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8984108 | This Fargo project is a concrete pavement reconstruction project on 45th St from 26th Ave S to 52nd Ave S to include grading, storm drains, sanitary sewer, lighting, and signals to reconstruct the existing pavement. | Pavement Improvement | 2010-03-22 | 2010-03-31 | 2010-10-15 |  | 4212312.06 | 2.470 | 8984108
9135 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8984113 | This Fargo project is a Structure Replacement project on Fargo - 38th St Bridge over Drain 27. | Bridge Replacement | 2009-12-14 | 2010-02-02 | 2010-09-03 | 2011-09-08 | 719895.06 | 0.091 | 8984113
9136 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8984114 | This Fargo project is a Structure Widening project on Fargo - 45th St at Drain 27. | Bridge Improvement | 2009-12-14 | 2010-02-15 | 2010-09-03 | 2011-05-19 | 317000 | 0.022 | 8984114
9137 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8984116 | This Fargo project is a Mill & Asphalt Overlay on Fargo - 25th Street from 32nd Avenue S to Rose Coulee to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-29 | 2009-07-29 | 2009-08-22 | 2011-05-12 | 362500 | 1.487 | 8984116
9138 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | BISMARCK-MANDAN |  | 8984118 | This Fargo project is a Asphalt Overlay and Concrete Pavement Repair on Fargo - Old HWY 81 from Dakota Dr to Co. Rd 20 to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-29 | 2009-09-21 | 2009-10-01 |  | 380000 | 1.940 | 8984118
9139 | NORTH DAKOTA | Underway | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | BISMARCK-MANDAN |  | 8984119 | This Fargo project is a City wide pavement marking project to restore pavement markings. | Pavement Improvement | 2009-07-20 | 2009-07-27 | 2009-10-15 |  | 400000 | 10.075 | 8984119
9140 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991021 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 6th Street S from Dakota Ave. to 11th Ave. S. to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-12 | 2009-10-02 | 2010-05-11 | 102000 | 0.658 | 8991021
9141 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991022 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 4th Avenue S from 6th St. S to 11th St. S to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-12 | 2009-10-02 | 2010-05-11 | 41000 | 0.340 | 8991022
9142 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991023 | This Wahpeton project is a Concrete Pavement Repair on Wahpeton - 2nd Avenue N from 2nd St. N to 11th St. N to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-12 | 2009-10-02 | 2010-05-11 | 56000 | 0.698 | 8991023
9143 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991024 | This Wahpeton project is a Pavement Patching and Seal Coat on Wahpeton - 7th Street N from 8th Ave N to 16th Ave N to preserve the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 47540.84 | 0.747 | 8991024
9144 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991025 | This Wahpeton project is a Chip Seal Coat on Wahpeton - 4th Street N from 2nd Ave N to ND 210 to preserve the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 119164.28 | 1.690 | 8991025
9145 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991026 | This Wahpeton project is a Mill & Asphalt Overlay on Wahpeton - 11th Street N from 16th Ave N to ND 210 to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 142504.43 | 0.487 | 8991026
9146 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991027 | This Wahpeton project is a Pavement Patching and Mill & Asphalt Overlay on Wahpeton - 7th Street N from 2nd Ave N to 8th Ave N to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 119400 | 0.435 | 8991027
9147 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | RICHLAND |  |  | 8991028 | This Wahpeton project is a Pavement Patching and Mill & Asphalt Overlay on Wahpeton - 11th Street N from Dakota to B Ave to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-20 | 2009-08-03 | 2009-10-02 | 2010-11-08 | 106984 | 0.794 | 8991028
9148 | NORTH DAKOTA | Completed | C200 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS |  |  | 8992031 | This West Fargo project is a Mill & Asphalt Overlay on West Fargo, 6 locations to rehabilitate the pavement structure. | Pavement Improvement | 2009-07-06 | 2009-07-15 | 2009-08-15 | 2011-08-08 | 1226294 | 5.240 | 8992031
9149 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CASS | FARGO-MOORHEAD (MN) |  | 8992033 | This West Fargo Project is an enhancement project to construct a bike/ped facility from Sheyenne River to 9th St West. | Transportation Enhancements | 2010-03-29 | 2010-06-21 | 2010-08-15 |  | 247238.2 | 0.000 | 8992033
9150 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | STATEWIDE |  |  | 9999248 | This NDDOT project is a project to update the history of the NDDOT. | Transportation Enhancements | 2010-04-06 | 2010-04-20 | 2011-05-30 |  | 267747 | 0.000 | 9999248
9151 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | CAVALIER |  |  | A010032 | This Langdon project is an enhancement project to install entrance welcome signage at the city of Langdon. | Transportation Enhancements | 2010-03-01 | 2010-05-11 | 2010-08-01 |  | 140376.4 | 0.000 | A010032
9152 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | TRAILL |  |  | T0UR035 | This NDDOT project is an enhancement project to rehabilitate the Viking Bridge northwest of Portland. | Transportation Enhancements | 2010-01-20 | 2010-03-09 | 2010-10-01 |  | 529912.15 | 0.000 | T0UR035
9153 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | GRAND FORKS |  |  | T0UR036 | This North Dakota Parks and Recreation project is an enhancement project to contruct a new pedestrian briridge at Turtle River State Park. | Transportation Enhancements | 2010-03-03 | 2010-07-20 | 2010-10-29 |  | 325775.84 | 0.000 | T0UR036
9154 | NORTH DAKOTA | Underway | C220 | Highway Infrastructure Investment Grant | NORTH DAKOTA | BURLEIGH |  |  | T0UR037 | This SHSND project is a enhancement project to Camp Hancock Locomotive at Camp Hancock in Bismarck - Main Avenue near 2nd Street. | Transportation Enhancements | 2010-03-30 | 2010-05-30 | 2010-07-15 |  | 206421.39 | 0.000 | T0UR037
9155 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | 0H03001 | This project is for preliminary engineering for a multi use bike and hike trail along the north bank of the Ohio River | Transportation Enhancements | 2009-12-08 | 2010-03-15 | 2011-07-15 | 2012-04-13 | 1582588.75 | 6.690 | 0H03001
9156 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E031995 | This is a preservation project on I-75 from North Cove bridge to Cecilia. It will prevent future pavement decay on this priority route. The resurfacing project will prolong the life of I-75 between Be | Pavement Improvement | 2009-08-25 | 2009-09-08 | 2009-10-15 | 2009-11-08 | 1133582.59 | 2.700 | E031995
9157 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CRAWFORD |  | 04 | E032086 | This project will resurface approximately 11.50 miles of SR 4 from the north corporation limit of the city of Bucyrus to the Seneca County line. It includes bridge work at seven locations. | Pavement Improvement | 2009-08-20 | 2009-09-16 | 2010-07-30 | 2010-08-30 | 3146444.09 | 11.330 | E032086
9158 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E032369 | This project is to reconstruct the 15th street bridge over ABC railroad in Barberton | Bridge Replacement | 2009-09-11 | 2009-09-11 | 2011-06-30 | 2011-09-26 | 268000 | 0.000 | E032369
9159 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LAKE | CLEVELAND, OH | 14 | E033177 | In the City of Willowick this project is to upgrade and interconnet the traffic signal system at approximately 15 locations along Lakshore Blvd, Vine St and E 305th Street to improve safety. | Safety/Traffic Management | 2010-04-05 | 2010-05-20 | 2011-09-30 | 2012-05-30 | 1205290 | 0.010 | E033177
9160 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | JACKSON |  | 06 | E035110 | This is a four-lane minor rehabilitation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Jackson County. The project includes re | Pavement Improvement | 2009-08-18 | 2009-08-28 | 2010-10-31 | 2011-06-08 | 8982693.38 | 9.690 | E035110
9161 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLERMONT |  | 02 | E035574 | Painting of Clinton U.S. 68 bridge over Cowan Creek; Clinton U.S. 68 over Anderson Ford; Wilmington Road bridge over I-71 in Warren; Stubbs Mills Road bridge over I-71 in Warren. | Bridge Improvement | 2009-08-12 | 2009-08-21 | 2010-06-01 | 2010-10-29 | 1291031.92 | 0.000 | E035574
9162 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PREBLE |  | 08 | E035896 | Repave portions of SR 732; also resurface Eaton-Oxford Rd., CR 29, in from the Morning Sun Outpost | Pavement Improvement | 2009-10-02 | 2010-04-22 | 2010-06-30 | 2010-07-14 | 2252153.73 | 13.540 | E035896
9163 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 12 | E036406 | This project includes the resurfacing of State Route 16 from mile marker 19.72 near the 21st Street bridge east to mile marker 23.66 near the Dayton Road Intersection. The project also includes the re | Pavement Improvement | 2009-09-03 | 2009-09-08 | 2010-10-30 | 2010-12-17 | 6230065.56 | 6.300 | E036406
9164 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | JACKSON |  | 18 | E036464 | This is a preservation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Jackson County. The project will resurface 11.45 miles (2 | Pavement Improvement | 2009-08-19 | 2009-09-21 | 2009-10-31 | 2009-11-30 | 1501677.14 | 11.450 | E036464
9165 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E036720 | This project is to rahabilitate the West 77th Street bridge over Norfolk Southern Railroad and GCRTA located between Franklin Ave and Madison Ave in Cleveland | Bridge Replacement | 2009-11-02 | 2010-01-06 | 2011-06-30 | 2012-01-26 | 1509000 |  | E036720
9166 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E040008 | Improving travel and providing better connectivity is what this project will do. 5 miles of roadway will be resurfaced from the Montgomery/Miami county line to Tipp City in Miami County. | Pavement Improvement | 2009-06-25 | 2009-07-08 | 2009-09-30 | 2009-08-21 | 1800000 | 4.840 | E040008
9167 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ATHENS |  | 06 | E040367 | The project is a five-mile, two-lane resurfacing project which includes two miles of SR 682 in Athens County and six miles of SR 356 in Vinton County. | Pavement Improvement | 2009-07-01 | 2009-08-21 | 2010-06-15 | 2010-09-13 | 728540.48 | 12.520 | E040367
9168 | OHIO | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | TUSCARAWAS |  | 18 | E040567 | Replace existing bridge constructed in 1906 over the Tuscarawas River between Front Street and Broadway in the city of Dover with a new multi-span, multi-beam bridge with sidewalks and pedestrian rail | Bridge Improvement | 2009-08-05 | 2009-09-18 | 2011-06-30 | 2011-02-18 | 810944 | 0.060 | E040567
9169 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | HANCOCK |  | 04 | E040571 | Pave deteriorated sections along Interstate 75 in Hancock County, starting at State Route 613 north to the Wood County line. | Pavement Improvement | 2009-06-12 | 2009-07-06 | 2009-08-30 | 2009-08-22 | 1128068.62 | 2.810 | E040571
9170 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | HARDIN |  | 04 | E040577 | Repave route SR37 from the Hancock County line to the Wyandot County line through the village of Forest and SR53 from the North Corporation limit of Kenton to SR37 in Hardin County due to pavement deterioration | Pavement Improvement | 2009-07-08 | 2009-08-27 | 2009-10-01 | 2009-10-20 | 291000 | 12.870 | E040577
9171 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 05 | E040597 | This project in southern Lorain County replaces 2 structures west of the Village of Wellington. The first is a 133' structure over the West Branch of the Black River, 0.57-mile west of Quarry Road and | Bridge Replacement | 2009-12-01 | 2010-02-22 | 2011-09-01 | 2010-10-25 | 1000000 | 0.080 | E040597
9172 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 13 | E040717 | The project includes the complete reconstruction of 6.5 miles of Interstate 76 east of its interchange with Interstate 71 in Medina County. The project ends at the western side of the State Route 57 i | Pavement Improvement | 2010-04-14 | 2010-04-15 | 2011-09-30 | 2011-11-29 | 14883240.88 | 7.000 | E040717
9173 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LORAIN | CLEVELAND, OH | 05 | E040910 | This project will widen the lanes of CR61 by 1' each side and add 4' paved shoulder. | Pavement Improvement | 2010-06-16 | 2010-08-05 | 2011-10-28 | 2011-10-31 | 1875065 | 2.650 | E040910
9174 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E050142 | This project is to create a 4 lane divided roadway at Austin Pike to Washinton Church Road in Montgomery County. This project will also construct a recreation trail on the north side of the roadway. | Pavement Widening | 2010-04-06 | 2010-04-26 | 2011-06-30 | 2011-07-29 | 1999999.96 | 1.030 | E050142
9175 | OHIO | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | LOGAN |  | 07 | E050427 | This project will replace beams, deck, substructure and widen the structure over Great Miami River. | Bridge Improvement | 2010-04-14 | 2010-04-20 | 2010-11-30 | 2010-11-17 | 1341353.99 | 0.000 | E050427
9176 | OHIO | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E050443 | To improve this major distribution link in East Central Ohio, this project will resurface approximately 3 miles of State Route 16 in Muskingum County and almost 10 miles of State Route 16 in Coshocton | Pavement Improvement | 2009-06-26 | 2009-07-06 | 2009-10-01 | 2009-12-03 | 2791601.89 | 13.000 | E050443
9177 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | MERCER |  | 08 | E050631 | This project will correct deficiencies in the bridge as part of an Ohio Department of Transportation (ODOT) initiative to ?Fix it First.? Preserving this bridge on SR 118 in Mercer County by removing | Bridge Improvement | 2009-07-21 | 2009-08-27 | 2009-09-30 | 2009-10-04 | 205790 | 0.000 | E050631
9178 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HOCKING |  | 06 | E050633 | This project is a nine mile, two-lane resurfacing project using an asphalt overlay on SR-180 in Hocking county | Pavement Improvement | 2009-09-03 | 2010-05-10 | 2010-07-15 | 2010-06-25 | 961651.6 | 9.160 | E050633
9179 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PICKAWAY |  | 07 | E051164 | This project rehabilitates nine bridges on US 23 throughout Pickaway County. Original construction of these bridges was in the 1950s. Rehabilitation includes resurfacing or replacement of the bridge decks and other maintenance including painting. | Bridge Improvement | 2009-07-24 | 2009-07-24 | 2010-09-30 | 2010-11-24 | 9566695.96 | 0.580 | E051164
9180 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E051227 | Construct bicycle/pedestrian bridge at Deer Creek Dam spill way in Stark County | Transportation Enhancements | 2009-08-12 | 2009-09-14 | 2010-06-30 | 2010-09-10 | 611485 |  | E051227
9181 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 07 | E051293 | Bridge maintenance projects on the Broad Street bridge over I-71 including backwall repair, new barrier wall, vandal fence and curb ramps. | Bridge Improvement | 2009-09-02 | 2009-10-26 | 2010-05-31 | 2010-09-02 | 714080 | 0.010 | E051293
9182 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E051296 | Kettering Boulevard from the Moraine North Corp Line to the Moraine South Corp Line-Reconfigure right turn drop lanes, replace existing bridge, install sidewalk, resurface the existing roadway. | Pavement Improvement | 2010-05-13 | 2010-04-22 | 2010-10-30 | 2011-07-22 | 375000 | 1.870 | E051296
9183 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E051298 | Reconstruction 5 lanes of MOT CR 99 from Stonequarry Road to Cresthill Drive in Vandalialanes. | Pavement Improvement | 2009-07-21 | 2009-09-16 | 2010-05-31 | 2010-09-02 | 126392 | 0.450 | E051298
9184 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E060146 | In Gahanna at the IR270/SR317 (Hamilton Road) Interchange complete interchange ramp modifications by adding two lanes to the east bound exit ramd and one lane to the west bound exit ramp. Also will ex | Pavement Improvement | 2010-04-29 | 2010-05-03 | 2010-10-31 | 2011-05-31 | 1985651.56 | 1.070 | E060146
9185 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SENECA |  | 05 | E060167 | Bridge replacement on State Route 67, near State Route 100, in Seneca County. This project will provide a new bridge structure. | Bridge Replacement | 2009-06-26 | 2009-08-25 | 2010-09-30 | 2010-09-17 | 1575119.1 | 0.090 | E060167
9186 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E060194 | Construct a bikepath from Sutton Avenue to Four Mile Road along north side of Kellogg Avenue including a spur into Kellogg Park on the south side of Kellogg Ave. near Four Mile Road; utilizing the cro | Transportation Enhancements | 2010-05-12 | 2010-06-21 | 2010-08-30 | 2011-05-16 | 463000 | 1.450 | E060194
9187 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E060228 | Construction of new bridge over Mahoning River to replace current RR bridge | New Bridge Construction | 2010-03-26 | 2010-03-26 | 2010-10-01 | 2010-11-03 | 703610.06 |  | E060228
9188 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 13 | E060255 | This project is to construct a pedestrian trail along Ohio and Erie Canal Towpath, in downtown Akron. | Transportation Enhancements | 2010-05-27 | 2010-06-07 | 2010-12-31 | 2012-09-12 | 2500000 | 0.000 | E060255
9189 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TUSCARAWAS |  | 18 | E060275 | This project is to construct a new interchange off I-77 at CR 80 in Dover to help relieve congestion at the existing I-77 interchanges in Dover and Strasburg. This interchange will provide improved ac | New Construction | 2009-08-27 | 2009-09-16 | 2011-06-30 | 2011-08-24 | 2162071.79 | 1.740 | E060275
9190 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E060304 | Replacement of the North Street Bridge in the Village of Plymouth. The existing bridge is in very poor condition, has an ODOT bridge appraisal rating of 2P and a load limit of 20 tons. The project inc | Bridge Replacement | 2009-07-09 | 2009-09-08 | 2009-10-29 | 2009-10-29 | 210000 | 0.020 | E060304
9191 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HANCOCK |  | 04 | E060317 | Add turn lanes on the north and west approaches of the intersection at SR 568 and Township Road 236 | Safety/Traffic Management | 2009-08-20 | 2009-08-31 | 2009-10-31 | 2011-10-01 | 475500 | 0.220 | E060317
9192 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CRAWFORD |  | 04 | E060342 | This project involves the full reconstruction of State Route 4/State Route 98 (Sandusky Avenue) through Downtown Bucyrus. The 0.51 mile long project begins at Charles Avenue and concludes at the Sandu | Pavement Improvement | 2009-08-03 | 2009-08-03 | 2010-10-27 | 2010-12-21 | 4415193.86 | 0.550 | E060342
9193 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E060344 | This is the third in a series of projects to reconstruct, widen and improve safety along the U.S. Route 224 corridor through the City of Willard. The project will replace 1400 linear feet of two lane | Pavement Improvement | 2010-05-24 | 2010-06-05 | 2010-10-31 | 2011-07-11 | 1200000 | 0.450 | E060344
9194 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E060378 | Resurface almost six miles of SR 147, from Belmont to SR 9 near Centerville, and over six miles of SR 149 from SR 9 at Warnock to Belmont. | Pavement Improvement | 2009-08-10 | 2009-08-31 | 2009-10-30 | 2010-07-17 | 895883.03 | 11.980 | E060378
9195 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LAKE | CLEVELAND, OH | 14 | E060405 | This project is for reconstruction of Fairgrounds Road from SR-84 to Woodland Road in Concord and Painesville Twps. | Pavement Improvement | 2010-03-26 | 2010-03-29 | 2011-09-30 | 2011-10-24 | 2633490.88 | 1.140 | E060405
9196 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E060436 | This project is for the reconstruction of Secor Road in Toledo from Monroe St to Laskey Rd. It will also modify the configuration of the intersection of Secor Rd and Sylvania Ave to improve traffic | Pavement Improvement | 2010-02-04 | 2010-03-17 | 2010-11-12 | 2011-10-07 | 2880000 | 1.090 | E060436
9197 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | BROWN |  | 02 | E060440 | This project is to maintain and preserve the pavement by making the necessary repairs and overlaying the existing pavement with asphalt concrete on SR-32 from Clermont/Brown Co. Line to .017 miles east of US68 overpass | Pavement Improvement | 2010-02-09 | 2010-03-17 | 2010-09-30 | 2010-11-03 | 4093235.94 | 5.800 | E060440
9198 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PERRY |  | 18 | E060540 | Modernizing a main connector for residents and businesses to the major cities of Zanesville in Muskingum County and Lancaster in Fairfield County, this project will resurface 14 miles of highly-travelled sections of U.S. Route 22 in Perry County. | Pavement Improvement | 2009-06-25 | 2009-08-20 | 2009-10-15 | 2009-09-30 | 1535913.92 | 7.500 | E060540
9199 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 18 | E060550 | As part of the Ohio Department of Transportation?s ?Fix it First? initiative, this project will help correct deficiencies in the bridges at two locations on U.S. 40 in Licking and Muskingum counties. | Bridge Improvement | 2009-09-03 | 2009-09-08 | 2010-09-15 | 2010-07-19 | 286812.12 | 0.040 | E060550
9200 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | PUTNAM |  | 05 | E060605 | Repave routes SR189 and SR190 through the village of Ft. Jennings from the west corporation limits to US224 and SR694 from SR115 to the west corporation limit of the village of Glandorf in Putnam County due to pavement deterioration | Pavement Improvement | 2009-06-25 | 2009-09-25 | 2009-10-31 | 2009-11-06 | 958437.3 | 9.620 | E060605
9201 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | MIAMI |  | 08 | E060683 | This is a streetscape project for three intersections and will included landscaping, upgrading lighting, and adding other enhancement items. | Transportation Enhancements | 2011-03-23 | 2011-07-01 | 2011-11-15 | 2012-08-14 | 456828 | 0.480 | E060683
9202 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 13 | E060754 | This project is the resurfacing of I-77 from Ghent Road to the Richfield Village corporation line. Project also includes minor repairs (sealing and patching) to six bridges, including two over Ira Road, two over Yellow Creek and two over Bath Road. | Pavement Improvement | 2010-04-14 | 2010-04-23 | 2010-11-30 | 2010-10-19 | 2734471.35 | 4.170 | E060754
9203 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | AUGLAIZE |  | 04 | E060946 | This project is to resurface the existing roadway with asphalt concrete on SR-362 in Auglaize county from the Shelby/Auglaize county line to the Village of Minster and in Shelby county from Lake Loram | Pavement Improvement | 2009-06-11 | 2009-07-21 | 2009-08-31 | 2009-08-19 | 476000 | 3.370 | E060946
9204 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E060950 | This project is to rehabilitate the Aetna Road Bridge over the CSX tracks in the City of Cleveland | Bridge Improvement | 2010-03-29 | 2010-05-17 | 2010-10-30 | 2012-04-19 | 1048230 | 1.120 | E060950
9205 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SHELBY |  | 08 | E060967 | This project is to resurface the existing roadway with asphalt concrete on SR47 from 0.59 mile East of SR66 to Kuther Road in Shelby county | Pavement Improvement | 2009-09-02 | 2009-09-15 | 2009-10-31 | 2009-11-05 | 1239028.25 | 8.170 | E060967
9206 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | SANDUSKY |  | 05 | E070033 | This project is for resurfacing SR125 in Scioto County. | Pavement Improvement | 2011-01-31 | 2011-04-25 | 2011-07-31 | 2011-07-19 | 683450.87 |  | E070033
9207 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HIGHLAND |  | 03 | E070048 | This is a preservation project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Highland County. The project will resurface U.S. Route 62 | Pavement Improvement | 2009-06-25 | 2009-09-09 | 2009-10-31 | 2009-12-08 | 488841.23 | 12.020 | E070048
9208 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LAWRENCE |  | 06 | E070064 | This project will replace a deficient structure situated over Dick Creek, at the 5.78-mile marker on state Route 217, just west of the route?s junction with state Route 378. This project is necessary | Bridge Replacement | 2009-08-04 | 2009-08-17 | 2009-10-31 | 2009-11-24 | 349960 |  | E070064
9209 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | SCIOTO |  | 06 | E070067 | This project will replace a deficient structure situated over Gas Hollow and located at the 1.28-mile marker on U.S. Route 52 (just east of Township Road 97 and the Adams-Scioto County line) and inclu | Bridge Replacement | 2009-07-01 | 2009-07-13 | 2009-10-31 | 2009-12-18 | 726871.92 |  | E070067
9210 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GEAUGA |  | 14 | E070129 | Resurfacing of State Route 700 from U.S. 422 to State Route 168 in Troy and Burton Townships. | Pavement Improvement | 2009-09-02 | 2010-04-15 | 2010-07-15 | 2011-09-19 | 951745.13 | 5.040 | E070129
9211 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E070130 | This project includes the resurfacing of approximately 7 miles of State Route 60 from the Morgan County line to the south corporation limit of Duncan Falls in Muskingum County. | Pavement Improvement | 2009-08-24 | 2009-09-08 | 2009-10-16 | 2009-10-19 | 1449185.43 | 8.150 | E070130
9212 | OHIO | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | MADISON |  | 15 | E070248 | This project is for the extension of sidewalks, brick pavers, street lights, benches, trees, and trash receptacles on Main Street. | Transportation Enhancements | 2011-01-19 | 2011-02-28 | 2011-09-30 | 2011-12-31 | 600000 |  | E070248
9213 | OHIO | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | PICKAWAY |  | 15 | E070267 | The Rickenbacker area, 10 miles southeast of Columbus, includes Rickenbacker International Airport, the Rickenbacker Intermodal Terminal and an industrial area. Building a new road that includes bette | New Construction | 2010-05-17 | 2010-05-24 | 2012-07-30 | 2012-06-13 | 8512002.76 | 0.010 | E070267
9214 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLERMONT |  | 02 | E070273 | Resurface portions of SR 232 in Clermont County to include just over 10 miles of roadway. | Pavement Improvement | 2009-08-18 | 2009-10-06 | 2010-07-30 | 2010-04-28 | 540548.55 | 10.190 | E070273
9215 | OHIO | Completed | C220,C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E070274 | This project involves the West Main Street (Business US 35) Streetscape including trees, shrubs, and masonry walls.and gateway sign. | Transportation Enhancements | 2010-09-13 | 2010-10-30 | 2010-12-03 | 2011-11-15 | 295139.68 | 0.190 | E070274
9216 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E070284 | Resurface over 14 miles of SR 148 from SR 145 to SR 7 at Powhatan Point in Belmont County; resurface over four miles of SR 164 in Carroll County from SR 9 at Kilgore to SR 43 at Amsterdam; and resurfa | Pavement Improvement | 2009-08-31 | 2010-04-19 | 2010-07-31 | 2011-08-20 | 2741278.84 | 19.020 | E070284
9217 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E070294 | Replace SR 148 bridge deck just west of the junction with SR 7 near Steinersville. | Bridge Improvement | 2009-08-27 | 2010-03-31 | 2010-07-15 | 2011-07-22 | 210583.55 | 0.010 | E070294
9218 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E070304 | Resurface just over five miles of SR 149 from the village of Flushing in Belmont County to the village of New Athens in Harrison County, as well as resurfacing just under a mile of SR 9 in New Athens. | Pavement Improvement | 2009-07-01 | 2009-08-13 | 2009-09-30 | 2009-12-01 | 809655.81 | 6.150 | E070304
9219 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E070362 | This project will upgrade of the existing traffic control at the intersection of Coy Rd and Starr Ave, in the City of Oregon, from all-way stop to a fully actuated traffic signal. | Other | 2010-02-17 | 2010-06-08 | 2010-06-16 | 2011-07-07 | 194201 | 0.040 | E070362
9220 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | ASHLAND |  | 16 | E070379 | This project will rehabilitate a deficient 160-foot bridge over Claremont Avenue, 0.25-mile south of Baney Road. | Bridge Improvement | 2009-07-17 | 2009-07-28 | 2010-09-15 | 2010-09-29 | 1175274.8 | 0.020 | E070379
9221 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLERMONT |  | 02 | E070407 | This project is to replace the bridge that carries SR 276 over Kain Run in Clermont county. | Pavement Improvement | 2009-07-01 | 2009-08-03 | 2009-10-30 | 2009-10-06 | 326082.73 |  | E070407
9222 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E070412 | In Clinton county replace Culvert on SR 124 and SR 350 | Pavement Improvement | 2009-08-20 | 2010-08-14 | 2009-11-01 | 2010-12-08 | 220369.81 | 0.100 | E070412
9223 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BUTLER |  | 08 | E070422 | This project will resurface portions of US 27 for approximately 15 miles. | Pavement Improvement | 2009-09-10 | 2009-09-11 | 2009-10-15 | 2010-06-02 | 2281937.33 | 14.940 | E070422
9224 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E070513 | This project will alleviate safety concerns by widening State Route 2 in Lucas County at the Howard Road intersection, with exclusive left and right turn lanes. Work will also provide wider medians an | Safety/Traffic Management | 2010-05-20 | 2010-06-03 | 2010-10-22 | 2011-06-23 | 2227275.21 | 1.100 | E070513
9225 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E070634 | Rehab existing single span steel beam bridge, originally built in 1952. Reconstruction of bridge/approach railing with decorative stone face wall. Installation of bridge lighting. Drainage improvement | Transportation Enhancements | 2009-09-17 | 2009-08-10 | 2009-12-31 | 2009-12-25 | 400000 | 0.460 | E070634
9226 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GEAUGA | CLEVELAND, OH | 14 | E070642 | Resurface Washington Street from the County line to Chillicothe Rd. (SR-306) in the Village of South Russell and Bainbridge Twp | Pavement Improvement | 2009-08-19 | 2009-08-10 | 2009-12-01 | 2009-11-25 | 363187.4 | 2.180 | E070642
9227 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GEAUGA | CLEVELAND, OH | 13 | E070646 | This project is to resurface Wilson Mills Road from County Line Rd. to Chillicothe Road (SR-306) in Chester Twp in Geauga county | Pavement Improvement | 2009-08-19 | 2009-08-17 | 2009-12-01 | 2010-02-12 | 499885.18 | 2.750 | E070646
9228 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CHAMPAIGN |  | 07 | E070751 | This project is to resurface the existing roadway with asphalt concrete on SR-55 in Champaign county from the junction of SR-560 to the Urbana west county line. | Pavement Improvement | 2009-06-25 | 2009-08-31 | 2009-09-30 | 2009-09-30 | 424299.72 | 3.430 | E070751
9229 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MEDINA | CLEVELAND, OH | 13 | E070779 | In Medina county on CR 97 (Greenwich Road) - from SR 3 to SR 57 resurface existing pavement and add paved shoulders to provide a new pavement surface and preserve the pavement structure | Pavement Improvement | 2010-05-25 | 2010-06-30 | 2010-10-29 | 2010-11-23 | 2000765.45 | 5.550 | E070779
9230 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MEDINA | CLEVELAND, OH | 13 | E070780 | In Medina county on Marks Road (CR 22) - from Fenn Road (CR 70) to Hamilton Road (CR 76) resurface existing pavement and add paved shoulders to provide a new pavement surface and preserve the pavement structure | Pavement Improvement | 2009-08-07 | 2009-09-21 | 2009-10-16 | 2009-10-23 | 529091.57 | 1.840 | E070780
9231 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | DARKE |  | 08 | E070781 | The project will resurface 4.5 miles of SR 571 near the Darke/Miami County Line, specifically between the City Greenville and the Village of West Milton. This route is heavily traveled by truck traffi | Pavement Improvement | 2009-06-16 | 2009-08-17 | 2009-09-30 | 2009-09-08 | 510000 | 4.150 | E070781
9232 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MEDINA | CLEVELAND, OH | 13 | E070785 | This project is to resurface CR 19 (Lake Road) - from CR 50 (Chippewa Road) to SR 162 (Wedgewood Road) which will include adding paved shoulders to provide a new pavement surface and preserve the pavement structure | Pavement Improvement | 2009-08-07 | 2009-09-21 | 2009-10-16 | 2009-11-03 | 336748.47 | 1.540 | E070785
9233 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | LOGAN |  | 04 | E070856 | The project will replace the bridge on SR 274 over the Great Miami River, which is two miles west of SR 235. The original structure was built in 1954 and is being replaced because of its age as well a | Bridge Replacement | 2009-06-26 | 2009-07-20 | 2009-10-30 | 2009-11-06 | 843508.79 |  | E070856
9234 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | NOBLE |  | 06 | E070920 | This is a two-lane resurfacing project using an asphalt overlay treatment. | Pavement Improvement | 2010-12-22 | 2011-05-02 | 2011-07-15 | 2011-06-22 | 850453.62 |  | E070920
9235 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | CHAMPAIGN |  | 04 | E070928 | This project will resurface the existing roadway on State Route 29 between State Route 560 and State Route 296 as well as the roadway on State Route 187 between the Madison / Champaign County Line and State Route 29. | Pavement Improvement | 2010-03-19 | 2010-05-03 | 2010-10-15 | 2010-07-12 | 586055.43 | 8.390 | E070928
9236 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | DARKE |  | 08 | E070933 | This project is to resurface SR503 from the Preble/Darke county line to SR121 | Pavement Improvement | 2009-08-04 | 2009-09-15 | 2009-10-31 | 2009-11-09 | 1006737.21 | 9.290 | E070933
9237 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GUERNSEY |  | 18 | E070951 | Interstate 77 is a major North-South economic corridor for eastern Ohio. This project will upgrade and rehabilitate approximately 2.5 miles of I-77 through Guernsey County. | Pavement Improvement | 2009-06-26 | 2009-07-01 | 2009-10-15 | 2009-08-28 | 1604000 | 2.510 | E070951
9238 | OHIO | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | FAIRFIELD |  | 07 | E070952 | In Fairfield county resurface SR 204 from SR 256 to SR 158 and SR 204A from IR 70 to SR 204 | Pavement Improvement | 2010-03-17 | 2010-05-04 | 2010-10-15 | 2010-09-09 | 1719897.05 | 11.650 | E070952
9239 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PERRY |  | 18 | E070959 | This project calls for the replacement of a deficient bridge deck located over Penn Central railroad on SR 93. This project is necessary for the safety of the traveling public, as well as to preserve and maintain the integrity of the route. | Bridge Improvement | 2009-06-25 | 2009-07-06 | 2009-10-31 | 2010-08-13 | 1187087.81 | 0.020 | E070959
9240 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E071098 | Resurfacing SR 7 from Midlothian Blvd. to Indianola Ave; nearly one-half mile of U.S. 62 from Williamson Ave. to Hadnett Drive, and three-quarter miles of SR 625 from Midlothian Blvd. to U.S. 62. | Pavement Improvement | 2009-08-04 | 2009-08-14 | 2009-10-15 | 2009-10-27 | 753036.11 | 1.980 | E071098
9241 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E071109 | This is a safety project to reconstruct and rehabilitate sections of SR153 in Louisville including new curbs, gutters, sidewaly pavement widening west of California and Signals at California | Other | 2009-06-16 | 2009-06-16 | 2012-12-31 | 2012-12-26 | 330000 | 1.090 | E071109
9242 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E071111 | The project is for the slope repair and reconstruction on I-271 at two locations between the Ohio Turnpike and Brandywine Road. | Pavement Improvement | 2009-06-24 | 2009-07-20 | 2009-12-01 | 2009-12-16 | 754120.55 | 0.020 | E071111
9243 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E080046 | This project is to construct Superstreet intersection at Hamilton Mason Road and SR 4B with associated widening on SR 4B, including tapers. | Pavement Improvement | 2010-05-10 | 2010-05-10 | 2011-10-28 | 2011-10-27 | 577562.84 | 0.620 | E080046
9244 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E080099 | Bridge deck replacement and painting of the SR 11 twin bridges over Indian Run between U.S. 224 and Western Reserve Road. | Bridge Improvement | 2009-08-04 | 2009-08-14 | 2010-10-15 | 2010-11-24 | 1755873.09 | 0.000 | E080099
9245 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 13 | E080129 | The project will replace a deficient 68-foot, three-span bridge on State Route 301, over Rudd Creek, north of the Village of Spencer. | Bridge Replacement | 2009-06-09 | 2010-03-31 | 2010-08-15 | 2010-08-18 | 391432.6 | 0.040 | E080129
9246 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 13 | E080130 | This project involves the replacement of a deficient 38-foot bridge structure over the Carpenter Ditch, 0.17 mile north of Jason Road. | Bridge Replacement | 2009-06-11 | 2009-06-18 | 2010-10-29 | 2010-04-12 | 427996.38 | 0.010 | E080130
9247 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E080160 | This project will resurface US Route 62 from SR 44 to State Street. Project also includes minor bridge work (patching and sealing) to six structures, two over Beech Creek, one over the Nimishillen Cre | Pavement Improvement | 2010-05-20 | 2010-05-26 | 2010-12-31 | 2010-11-17 | 3416393.19 | 5.370 | E080160
9248 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CLERMONT | CINCINNATI (KY) | 02 | E080245 | This project is to resurface SR 125 from near I-275 to SR 132 in Clermont County. | Pavement Improvement | 2010-08-31 | 2010-09-03 | 2010-10-15 | 2010-11-19 | 202450.72 | 6.230 | E080245
9249 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LORAIN | CLEVELAND, OH | 13 | E080278 | In Loraine county, resurface CR 57 (Russia Road) from SR 58 to CR 231 (Oberlin Elyria Road) | Pavement Improvement | 2009-11-12 | 2010-01-07 | 2010-10-29 | 2011-05-23 | 1584000 | 4.910 | E080278
9250 | OHIO | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E080481 | This project is to rebuild Fifteen Signalized Intersections Throughout The City, Including Poles, Vehicle Signals, Pedestrian Signals And Cable. | Safety/Traffic Management | 2010-06-17 | 2010-06-11 | 2011-12-01 |  | 379921 | 0.120 | E080481
9251 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E080491 | This project is to upgrade 7 signalized intersections to current standards and establish signal interconnection/coordination. | Safety/Traffic Management | 2010-11-23 | 2011-03-17 | 2011-08-31 | 2012-03-30 | 260000 |  | E080491
9252 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | NOBLE |  | 06 | E080504 | This is a two-Lane resurfacing project using an asphalt overlay treatment on SR145 in Washington and Noble counties. Work includes raised pavement markers, pavement marking and berm conditioning. | Pavement Improvement | 2010-03-03 | 2010-07-06 | 2010-10-15 | 2010-10-20 | 2890937.52 | 24.770 | E080504
9253 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E080519 | Great Miami River Bikeway from Old Springfield Road north to Kyle Park in Tipp City-Construct a missing link on the River Corridor Bikeway. | Transportation Enhancements | 2010-06-15 | 2010-08-24 | 2009-10-30 | 2012-04-02 | 263276 |  | E080519
9254 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E080527 | Resurfacing of ten miles of U.S. Route 30 East Canton and Minerva. Extensive pavement repairs and guardrail replacement are included. There is also some minor work being done to the bridges in this se | Pavement Improvement | 2010-04-14 | 2010-04-21 | 2010-10-31 | 2010-11-16 | 2715184.43 | 10.410 | E080527
9255 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E080541 | Realignment of four sets of railroad tracks to the south of the present location along US 50 in Cincinnati, Ohio. Track realignment is necessary to permit maintenance of traffic for the future roadwa | Pavement Improvement | 2009-12-01 | 2010-01-05 | 2011-06-30 | 2011-03-31 | 1075000 | 0.100 | E080541
9256 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | SHELBY |  | 04 | E080582 | This project is to replace a heavily deteriorated 9'x5' concrete culvert. The project is located 0.87 miles east of the Darke/Shelby county line. This section of SR 47 runs between the Village of Versailles and the City of Sidney. | Pavement Improvement | 2009-06-05 | 2009-07-21 | 2009-08-31 | 2009-08-05 | 133217.78 | 0.010 | E080582
9257 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | COLUMBIANA |  | 17 | E080586 | Resurface nearly five miles of SR 45, from McCracken Rd. south of Salem to U.S. 62 in Salem, and resurface just over 12 miles of SR 558 from SR 45 at Teegarden to SR 517 at East Fairfield, and from SR 7 at East Fairfield to SR 46 south of New Waterford. | Pavement Improvement | 2009-09-02 | 2010-04-07 | 2010-07-31 | 2010-12-01 | 1044653.48 | 17.110 | E080586
9258 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CARROLL |  | 18 | E080587 | This project includes the resurfacing of approximately five miles of SR 39 in Carroll County and almost eight miles of SR 39 and SR 44 in Columbiana County. | Pavement Improvement | 2009-07-01 | 2009-07-20 | 2009-09-18 | 2009-12-02 | 1486660 | 13.070 | E080587
9259 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CARROLL |  | 18 | E080588 | Almost three miles of SR 183 will be resurfaced, including just over a mile in Carroll County, from the Tuscarawas County line to the Stark County line at Magnolia, and about a mile and a half in Tusc | Pavement Improvement | 2009-08-04 | 2009-09-12 | 2009-10-15 | 2009-12-02 | 361029.35 | 2.850 | E080588
9260 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 05 | E080613 | The project includes the reconstruction and resurfacing of 1.2 miles of East River Street in the City of Elyria. This includes the replacement of concrete curb & gutter, upgrading existing sidewalk, r | Pavement Improvement | 2010-03-15 | 2010-03-26 | 2010-10-29 | 2011-09-30 | 1457759 | 1.160 | E080613
9261 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | COLUMBIANA |  | 17 | E080657 | Replace existing box beam bridge on SR 154, located approximately one mile east of SR 7 at Rogers, with a steel beam superstructure. | Bridge Improvement | 2009-08-25 | 2010-02-22 | 2010-07-15 | 2010-09-17 | 550225.5 | 0.500 | E080657
9262 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LORAIN | CLEVELAND, OH | 13 | E080683 | This project is to upgrade State Route 611 to three lanes in Loraine County to provide adquate capacity. | Pavement Improvement | 2010-03-26 | 2010-03-16 | 2011-06-30 | 2011-12-02 | 4540176 | 2.810 | E080683
9263 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WAYNE |  | 16 | E080696 | This project will rehabilitate a 282' bridge on State Route 539 over Interstate 71 in northwestern Wayne County. The project is between Ruff Road and Palmer Road. The SR-539/I-71 interchange is south | Bridge Replacement | 2009-09-09 | 2010-04-16 | 2010-10-15 | 2010-11-19 | 1266772.69 | 0.010 | E080696
9264 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | ERIE |  | 05 | E080699 | This project will replace twin 10-foot arch bridges on SR-61 over Old Woman?s Creek, 0.15-mile east of the south juncture with State Route 113. | Pavement Improvement | 2009-06-12 | 2009-07-24 | 2009-10-15 | 2009-10-02 | 314234.94 | 0.020 | E080699
9265 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HARRISON |  | 18 | E080712 | Fifteen miles of asphalt resurfacing and base repairs on SR 9 as well as six miles of asphalt resurfacing and chip sealing on SR 799 in Harrison County. | Pavement Improvement | 2009-07-17 | 2009-07-20 | 2009-10-15 | 2010-06-04 | 2706796 | 21.070 | E080712
9266 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GREENE |  | 07 | E080736 | This project is to resurface U.S. 35 from the Montgomery/Greene county line to the US 35/I-675 interchange | Bridge Improvement | 2009-08-28 | 2009-09-29 | 2010-07-31 | 2011-06-01 | 5845640.96 | 1.090 | E080736
9267 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | DARKE |  | 08 | E080747 | The project will reconstruct and lower USR 36 just west of Arcanum-Bears Mill Road to improve visibility and intersection safety. Due to the high accident rate at this intersection, the road grade wil | Safety/Traffic Management | 2009-06-12 | 2009-07-07 | 2009-09-30 | 2009-07-21 | 105981.5 | 0.090 | E080747
9268 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 11 | E080755 | The project is a minor rehabilitation of Interstate 271, from Wilson Mills Road to Interstate 90 in Cuyahoga County and Lake County. The work includes replacement of overhead signs. | Pavement Improvement | 2009-07-20 | 2009-07-20 | 2010-10-15 | 2010-09-30 | 8309390.72 | 4.310 | E080755
9269 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E080757 | This safety related resurfacing project on SR 2 will provide motorists with safer access to Interstate 475 from the Spring Meadows shopping corridor. The safety project includes updated pavement marki | Safety/Traffic Management | 2009-08-12 | 2009-09-09 | 2009-12-15 | 2009-12-01 | 137437.18 | 0.430 | E080757
9270 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E080763 | Resurfacing 7.88 miles of U.S. 20 from SR 11 to the Norfolk and Southern Railroad. | Pavement Improvement | 2009-06-26 | 2009-07-14 | 2009-10-15 | 2009-11-30 | 2593472.23 | 7.880 | E080763
9271 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MEIGS |  | 06 | E080790 | The project focuses on pavement surfacing of a 7-mile portion of SR 7 through Meigs County. The two-lane micro-surfacing will improve pavement deficiencies and pavement conditions, thereby enhancing the structural surface of the road. | Pavement Improvement | 2009-06-25 | 2009-06-29 | 2010-06-30 | 2009-08-31 | 1289972.42 | 7.290 | E080790
9272 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WASHINGTON |  | 06 | E080793 | Six miles of SR 60 in Washington County is being resurfaced. The work includes resurfacing on both lanes of the project. | Pavement Improvement | 2009-08-20 | 2009-09-03 | 2009-10-31 | 2009-10-26 | 1112788.13 | 6.090 | E080793
9273 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | WYANDOT |  | 04 | E080796 | Grind and pave deteriorated pavement on US23 from County Road 62 to the CSX railroad in Wyandot county | Pavement Improvement | 2009-06-25 | 2009-07-06 | 2009-10-10 | 2009-11-02 | 500000 | 3.480 | E080796
9274 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONROE |  | 06 | E080827 | An eight-mile stretch of SR 379 in Monroe County will be resurfaced. The project includes resurfacing work on both lanes of the roadway. | Pavement Improvement | 2009-08-12 | 2009-10-07 | 2010-06-30 | 2010-06-29 | 231815.37 | 8.070 | E080827
9275 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E080895 | Resurfacing I-77 from the US 30 interchange to the SR 800/Cleveland Avenue interchange. Resurfacing of various ramps at both the US 30 and the SR 800/Cleveland Ave. interchanges. The project also includes guardrail replacement and minor bridge work. | Pavement Improvement | 2009-06-15 | 2009-06-15 | 2010-07-01 | 2010-06-25 | 2939729 | 1.050 | E080895
9276 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | WOOD |  | 09 | E081010 | This project is a 2-Lane resurfacing project with pavement repairs on SR-582 from the Village of Luckey west corp line to US-23 | Pavement Improvement | 2010-03-09 | 2010-04-16 | 2010-08-06 | 2010-11-10 | 937766.71 | 4.340 | E081010
9277 | OHIO | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | SANDUSKY |  | 05 | E081011 | This project is on SR-600 from Wood County Line to US-20 and SR-300 in Gibsonburg. A 2-Lane resurfacing project with pavement repairs of SR-600 from Wood County Line to US-20 in Sandusky County and SR-300 in Gisonburg. | Pavement Improvement | 2010-04-06 | 2010-06-01 | 2010-08-06 | 2010-11-12 | 3298923.4 | 10.820 | E081011
9278 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E081028 | Minor rehabilitation/resurfacing with two deck overlays from Gypsy Ln in Niles to Girard city limits. | Pavement Improvement | 2010-06-08 | 2010-06-17 | 2010-10-31 | 2010-11-15 | 250000 | 2.950 | E081028
9279 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CHAMPAIGN |  | 07 | E081032 | In Champaign county, replace 23 foot bridge over Jumping Run with minimal approach work. | Bridge Replacement | 2009-09-02 | 2009-09-28 | 2009-10-31 | 2009-12-09 | 309269.07 |  | E081032
9280 | OHIO | Underway | C240,C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E081064 | State Route 4 was built in the late 1960s as a 2 lane highway, but tremendous business growth in the area has led to congestion and has limited future economic potential. This latest phase of the bypa | Pavement Widening | 2010-05-07 | 2010-05-10 | 2012-04-13 |  | 6291933 | 1.600 | E081064
9281 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E081068 | This project is for resurfacing North Fairfield Road in Greene County. | Pavement Improvement | 2011-03-25 | 2011-03-15 | 2011-08-31 | 2011-11-14 | 827728.82 | 1.140 | E081068
9282 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HAMILTON |  | 01 | E081077 | Improve the pavement condition of Interstate 75 from south of SR 126 to south of the Lockland corporation. Project includes several minor bridge rehabilitations. | Pavement Improvement | 2009-08-04 | 2009-08-11 | 2010-08-01 | 2011-11-15 | 6246995.65 | 2.490 | E081077
9283 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E081127 | Chip seal will be used as a preventive maintenance treatment to extend the pavement life on almost seven miles of SR 379 in Belmont County, between the Monroe and Noble county lines. Additionally, it | Pavement Improvement | 2009-08-18 | 2010-05-27 | 2010-08-30 | 2010-08-25 | 111015.62 | 9.400 | E081127
9284 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CARROLL |  | 18 | E081129 | Chip seal will be used as a preventive maintenance treatment to extend the pavement life on about 18 miles of two-lane roadways in Carroll and Columbiana counties. Six miles of SR 9 in Carroll County | Pavement Improvement | 2009-07-08 | 2009-08-10 | 2009-10-31 | 2009-11-06 | 572426.23 | 17.600 | E081129
9285 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 13 | E081175 | In Summit county on Waterloo Road, From US224 to Portage Line Road this project is to improve the road by making pavement repairs and resurfacing the full width of the roadway , applying pavement markings and installing raised pavement markers | Pavement Improvement | 2010-05-10 | 2010-07-26 | 2010-10-31 | 2010-12-20 | 663695 | 1.670 | E081175
9286 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E081178 | This project is a Streetscape project within the Village of Glendale. The project will include paver brick sidewalks, decorative lighting, updated street furniture (park benches, trash receptacles), s | Transportation Enhancements | 2010-07-27 | 2010-08-02 | 2010-10-29 | 2010-12-16 | 287718 | 0.010 | E081178
9287 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E090047 | Resurface State Route 380 from Greene County to Highland County | Pavement Improvement | 2009-09-17 | 2010-04-05 | 2010-07-01 | 2010-06-15 | 1827182.08 | 9.710 | E090047
9288 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090071 | This project is to resurface Michigan St. (SR-25D) from Lafayette St. to Madison Ave in Toledo | Pavement Improvement | 2010-02-02 | 2010-03-22 | 2010-11-19 | 2010-11-15 | 1004570.45 | 0.440 | E090071
9289 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090118 | Resurfacing of SR 800 from the Tuscarawas County line to south of Faircrest Street in Canton and Pike Townships and in the Village of East Sparta. | Pavement Improvement | 2009-07-01 | 2009-07-20 | 2009-12-01 | 2009-10-08 | 1256052.25 | 7.030 | E090118
9290 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E090187 | Resurface State Route 72 from Highland County to Greene County to improve pavement condition. | Pavement Improvement | 2009-06-25 | 2009-07-08 | 2009-10-30 | 2009-10-28 | 2955680.41 | 14.000 | E090187
9291 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONROE |  | 18 | E090192 | The project is a seven-mile, two-lane resurfacing project of SR 7 in Monroe County, including four miles of SR 7 in Washington County. | Pavement Improvement | 2009-09-02 | 2009-09-30 | 2009-10-31 | 2010-08-03 | 2332721.93 | 12.460 | E090192
9292 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MORGAN |  | 18 | E090196 | Ten miles of SR 376 in Morgan County are being resurfaced. The project includes resurfacing work on both lanes of the highway. | Pavement Improvement | 2009-08-10 | 2009-08-12 | 2010-06-30 | 2009-10-02 | 1313282.43 | 9.730 | E090196
9293 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090220 | This project involves landscape enhancement along outer edge of SR 4 roadway pavement by installing brick pavers, shrubs and retaining wall at gateway sign. | Transportation Enhancements | 2010-10-13 | 2010-10-28 | 2011-10-01 | 2011-10-01 | 14040 | 0.500 | E090220
9294 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | MEIGS |  | 06 | E090248 | This project begins 0.05 mi. N of 6th Street and SR 124 intersection. It includes upgrades to Starmill Park in Racine. Work includes parking lot resurfacing, walking track lighting, park entrance upg | Transportation Enhancements | 2010-05-17 | 2010-06-09 | 2010-10-29 | 2010-12-10 | 731804.06 |  | E090248
9295 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MERCER |  | 05 | E090250 | This project includes pavement planing, shoulder stabilization, and resurfacing the existing roadway on SR29 and SR707 with Asphalt Concrete. | Pavement Improvement | 2010-02-24 | 2010-04-21 | 2010-10-15 | 2010-07-02 | 1610789.56 | 17.320 | E090250
9296 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E090289 | This project is to renovate the existing steel railroad bridge with a new deck and railing for bicycles and walkers. The old railroad corridor is owned by the Lorain County Metropolitan Park District. | Transportation Enhancements | 2010-09-27 | 2010-12-11 | 2011-06-24 | 2011-05-09 | 283522.8 |  | E090289
9297 | OHIO | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | ALLEN |  | 04 | E090292 | Repair and replace sections of deteriorated safety median wall barrier on both Interstate 75 in Allen County and U.S. Route 68 in Hancock County. Excessive deterioration of the existing concrete walls has resulted in a growing safety concern. | Safety/Traffic Management | 2009-07-01 | 2009-07-27 | 2009-10-01 | 2009-10-15 | 875273.76 | 4.650 | E090292
9298 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GEAUGA | CLEVELAND, OH | 13 | E090309 | This project is resurface Wilson Mills Road from Chillicothe Road (SR-306) to Heath Rd. in Chester Township | Pavement Improvement | 2009-08-19 | 2009-08-17 | 2009-12-01 | 2009-11-25 | 405387.99 | 2.200 | E090309
9299 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E090320 | The project will repair two of Wilmington?s most traveled streets, Main and Locust street as well as install curbs and gutter. In addition to the semi-truck traffic that travels these two streets, the | Pavement Improvement | 2010-03-11 | 2010-03-25 | 2010-10-15 | 2011-04-30 | 2608430.55 | 3.420 | E090320
9300 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090325 | This project is to resurface U.S. Route 62 from Sugar Creek to Navarre. | Pavement Improvement | 2009-06-16 | 2009-06-16 | 2009-12-01 | 2010-06-02 | 1736714.46 | 5.260 | E090325
9301 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | AUGLAIZE |  | 04 | E090342 | This project involves pavement planing and resurfacing the existing roadway of SR 67 with Asphalt Concrete. | Pavement Improvement | 2010-02-18 | 2010-04-19 | 2010-09-30 | 2010-06-25 | 1404594.87 | 10.690 | E090342
9302 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E090343 | This project will resurface the existing roadway with asphalt concrete on US-40 from the Preble / Montgomery county line to the west corporation limit of Clayton. | Pavement Improvement | 2010-03-16 | 2010-06-08 | 2012-08-15 | 2010-11-02 | 900000 | 6.220 | E090343
9303 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 05 | E090357 | This project will provide various ?finishing touches? on the Veterans? Glass City Skyway. The project will provide funding for the installation of permanent inspection platforms. Work will also includ | Bridge Improvement | 2010-04-05 | 2010-04-26 | 2010-10-29 | 2010-09-16 | 1549690 | 2.000 | E090357
9304 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E090373 | Resurfacing four miles of I-680 from SR 11 to Steel Street. Project also includes minor bridge work. | Pavement Improvement | 2009-07-27 | 2009-07-27 | 2010-06-30 | 2010-09-22 | 4051803.15 | 4.060 | E090373
9305 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GREENE |  | 07 | E090375 | This project will resurface I-675 from SR 235 to the Clark County line and resurface SR 444 at I-675 interchange | Bridge Improvement | 2009-09-17 | 2009-09-21 | 2010-06-01 | 2011-07-20 | 4854049.01 | 3.240 | E090375
9306 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | VAN WERT |  | 05 | E090387 | Repave route SR49 in Van Wert and Paulding County from US30 to the south corporation limit of Payne due to pavement deterioration | Pavement Improvement | 2009-06-12 | 2009-09-08 | 2009-11-04 | 2009-10-30 | 675236.63 | 8.260 | E090387
9307 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | CLARK |  | 07 | E090400 | Improving the roadways and making sure the access points are ADA compliant is what this project will do for the city of Springfield. Five roadways in all will be resurfaced and new new ADA curb ramps | Pavement Improvement | 2010-04-13 | 2010-04-01 | 2010-07-20 | 2010-11-22 | 909053.76 | 3.180 | E090400
9308 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLARK |  | 07 | E090401 | This is Clark County?s longest bridge and is in need of repair. The project will rehabilitate the structure and paint the Dayton Road bridge over the Norfolk Southern railroad near the Greene County L | Bridge Improvement | 2010-03-10 | 2010-03-01 | 2010-11-01 | 2010-11-16 | 331030.23 | 0.000 | E090401
9309 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 13 | E090427 | This project will replace a deficient 12-foot structure over small creek in Medina County on SR 421, .25 miles west of SR 85. | Pavement Improvement | 2009-08-24 | 2010-07-28 | 2011-10-14 | 2011-11-01 | 668947.93 | 0.040 | E090427
9310 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090439 | This project is to rehabilitate the State Street bridge in downtown Akron. | Other | 2009-09-17 | 2009-09-17 | 2011-10-31 |  | 500000 | 0.010 | E090439
9311 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ADAMS |  | 02 | E090442 | This is a four-lane preventive maintenance (preservation) project necessary to maintain the integrity of the existing route and the infrastructure of the state highway system in Adams County. The proj | Pavement Improvement | 2009-09-02 | 2010-04-20 | 2010-08-31 | 2010-09-13 | 3483829.51 | 13.700 | E090442
9312 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090485 | Resurface South Maple Avenue from Doris Drive to Dayton Yellow Springs Road-Asphalt. | Pavement Improvement | 2009-09-10 | 2009-09-25 | 2010-03-08 | 2009-10-13 | 239165.46 | 1.200 | E090485
9313 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL |  | 13 | E090491 | This is a safety project to install pedestrian lighting along Mahoning Ave between High Street and Summit Street. | Safety/Traffic Management | 2010-03-03 | 2010-06-29 | 2010-08-31 | 2010-11-30 | 203438.84 | 0.520 | E090491
9314 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WARREN |  | 03 | E090503 | Resurface Clearcreek-Franklin Road from approximately 160 feet south of Whispering Pines to Pennyroyal Road. | Pavement Improvement | 2010-01-07 | 2010-04-23 | 2010-08-01 | 2010-05-13 | 164616.57 | 0.760 | E090503
9315 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | GREENE |  | 07 | E090504 | Resurface Dayton-Yellow Springs Road from Kauffman Avenue to Ironwood Drive to improve pavement condition | Pavement Improvement | 2009-10-23 | 2009-10-07 | 2010-05-28 | 2009-11-16 | 209858.39 | 0.640 | E090504
9316 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | CLINTON |  | 06 | E090505 | This paving project would improve U.S. 68 through the city of Wilmington, another of the city?s most heavily used streets by car and truck traffic. The project would replace the curb, gutter and pavem | Pavement Improvement | 2010-04-21 | 2010-05-11 | 2010-11-01 | 2010-10-14 | 880119 | 0.960 | E090505
9317 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HAMILTON |  | 01 | E090506 | This project constructs Phase 2 of the Banks Intermodal Facility and the surrounding street network. The Banks Intermodal Facility, in conjunciton with the Riverfront Transit Center, will serve as Ci | New Construction | 2010-06-10 | 2010-06-14 | 2011-09-30 | 2012-02-29 | 8000000 | 0.330 | E090506
9318 | OHIO | Completed | C240,C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090507 | Project will design and construct Freedom Way between Rosa Parks and Race Street, Mehring Way between Main Street and Elm Street, and relocate and construct components of a new utility distribution li | New Construction | 2010-03-29 | 2010-03-15 | 2010-11-15 | 2012-02-23 | 6500000 | 0.320 | E090507
9319 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | MORGAN |  | 18 | E090508 | The majority of bridges in Morgan County accommodate mostly truck, car and school bus traffic. All but one bridge in Morgan County spans a river or waterway. Some of the bridges are as old as 1914 and | Bridge Improvement | 2009-07-22 | 2009-07-27 | 2009-10-15 | 2009-09-21 | 94366.38 | 0.000 | E090508
9320 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MORGAN |  | 18 | E090509 | Safety studies have indicated that guardrail is needed along 11,000 feet of roadway that parallels the Muskingum River. Slopes in these areas are very steep and guardrail would protect vehicles from going down the embankment. | Safety/Traffic Management | 2009-09-18 | 2009-10-19 | 2009-10-15 | 2009-11-03 | 120155 | 10.950 | E090509
9321 | OHIO | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | WASHINGTON |  | 06 | E090511 | Resurfacing over seven miles of Marietta city streets, reconstructing 100 ADA curb ramps along city streets, and limited drainage improvements. Includes various sections on Acme, Colegate, Front, Gilm | Pavement Improvement | 2009-08-20 | 2009-09-03 | 2010-06-30 | 2010-08-06 | 1067710.19 | 9.000 | E090511
9322 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | GALLIA |  | 06 | E090512 | The project will focus on the resurfacing of 5.25 miles of Gallia County roads, thereby reducing maintenance needs and providing structural strength for all local travelers. The roads are as follows: | Pavement Improvement | 2009-07-17 | 2009-09-03 | 2010-06-30 | 2009-09-24 | 352552.41 | 5.010 | E090512
9323 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | VINTON |  | 18 | E090513 | This project will focus on resurfacing over ten miles of Vinton County roads, reducing maintenance needs and providing structural strength for all local travelers. | Pavement Improvement | 2009-06-24 | 2010-04-22 | 2010-06-30 | 2010-06-07 | 408383.12 | 4.440 | E090513
9324 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090515 | Resurfacing from Walnut St to the Crab Creek Bridge. | Pavement Improvement | 2010-03-26 | 2010-04-14 | 2009-12-31 | 2010-06-10 | 406516.74 | 0.420 | E090515
9325 | OHIO | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | OHIO | ALLEN |  | 04 | E090516 | This railroad grade separation underpass project in the city of Lima?s south side is located on Vine St. between Main St. and Central Ave. The project is being constructed in conjunction with IGCC (Li | New Bridge Construction | 2009-05-18 | 2010-05-10 | 2011-11-01 | 2012-07-11 | 12665306.94 |  | E090516
9326 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E090517 | The KROC Center is a $66 million community center under construction in the Keowee/Webster Street area of Dayton. The $66 million is also being invested to renovate a very large historic home once cov | Pavement Improvement | 2009-10-06 | 2009-09-08 | 2009-11-02 | 2009-12-01 | 349497.57 | 0.830 | E090517
9327 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E090518 | As the largest city in Montgomery County, Dayton has more than 150,000 residents. This project will improve the safety of five major thoroughfares that are deteriorating and will continue to unless im | Pavement Improvement | 2009-10-22 | 2009-10-09 | 2009-11-30 | 2010-05-07 | 1414900.9 | 5.610 | E090518
9328 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E090519 | This project will restore and preserve a major thoroughfare for residents and businesses using the heavily traveled James H. McGee Boulevard. Construction work will resurface the boulevard and make re | Pavement Improvement | 2010-04-26 | 2010-03-29 | 2010-10-29 | 2011-07-01 | 1049433.51 | 0.310 | E090519
9329 | OHIO | Completed | C220,C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090520 | In the Central Business District in Dayton-Add gateway features, resurface, curb and sidewalk repair, add tree lawn on several main corridors. | Pavement Improvement | 2010-06-09 | 2010-05-17 | 2010-10-29 | 2011-06-28 | 3182141.57 | 2.190 | E090520
9330 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E090523 | New Box Beam Superstructure replacement over the Tuscarawas River | Bridge Replacement | 2010-03-03 | 2010-03-01 | 2010-07-31 | 2010-08-31 | 747654.49 | 0.010 | E090523
9331 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E090524 | This is to resurface Tod Ave. from south corp. limits to West Market St in Warren | Pavement Improvement | 2010-05-17 | 2010-06-04 | 2010-09-30 | 2010-07-30 | 342500.6 | 1.000 | E090524
9332 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E090525 | This project is to resurface Hallock Young Road from SR 45 east to Austintown Warren Rd in Trumbull county. | Pavement Improvement | 2010-03-22 | 2010-03-22 | 2010-07-01 | 2010-07-20 | 522779.65 | 0.660 | E090525
9333 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090526 | Resurfacing from Presidential Drive to Mathews Rd in Mahoning County | Pavement Improvement | 2009-11-12 | 2009-09-14 | 2009-12-31 | 2009-11-04 | 918568.7 | 1.450 | E090526
9334 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090527 | Resurfacing from SR 616 west to city corp. limits. Also includes Handicap ramps installed with associated sidewalk and curbing, catch basin inlet adjustments. | Pavement Improvement | 2010-03-08 | 2010-03-08 | 2009-09-01 | 2010-06-11 | 291108.46 | 0.890 | E090527
9335 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E090528 | The EastPointe Industrial Park on State Route 93 in Muskingum County is a 1200 acre business park home to several major distribution centers. This project will construct a left turn lane to accommodate the new southern entrance of the business park. | Pavement Widening | 2010-04-01 | 2010-07-06 | 2010-09-30 | 2010-09-03 | 938610 | 0.700 | E090528
9336 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E090529 | Zanesville is the county seat for Muskingum County, and this project will improve four major thoroughfares in Zanesville. The streets are Dryden, Pershing, Dresden and Ridge. The project will also imp | Pavement Improvement | 2010-03-08 | 2010-05-24 | 2010-08-31 | 2010-09-25 | 726262.1 | 3.840 | E090529
9337 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 12 | E090530 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. Bayer and the City of Newark requested Federal Stimulus funds for the replacement of a crossing surface on a | Safety/Traffic Management | 2009-09-01 | 2009-09-25 | 2010-07-31 | 2009-09-28 | 100000 | 0.100 | E090530
9338 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | MORROW |  | 04 | E090531 | The project will replace the traffic signal at US Route 42 and State Route 529 in Cardington in Morrow County. The traffic signal is old and outdated. | Safety/Traffic Management | 2010-01-04 | 2010-03-22 | 2010-07-31 | 2010-05-28 | 85000 | 0.020 | E090531
9339 | OHIO | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | MARION |  | 04 | E090532 | Marion County is in a unique position in that its industrial base is on the west side of the county, yet the major route for moving commerce is located on the east side of Marion. The Northwest Indust | New Construction | 2010-01-04 | 2009-12-14 | 2010-12-31 | 2011-10-14 | 5100000 |  | E090532
9340 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | MADISON |  | 15 | E090533 | Xenia Road is also County Road 12 in the southern part of Madison County between the Clark County line and State Route 56 near London. This project will replace the bridge that is currently deficient. | Bridge Replacement | 2010-03-30 | 2010-05-24 | 2010-12-31 | 2010-08-18 | 393680 | 0.100 | E090533
9341 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 12 | E090534 | This project is to rehabilitate Camp Chase Railroad's railroad bridge over West Broad Street (US40) in Franklin Co. This work will encompass concrete patching, replacement, painting, vegetation contr | Other | 2010-03-31 | 2010-05-01 | 2010-10-01 | 2010-12-08 | 300000 |  | E090534
9342 | OHIO | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 15 | E090535 | As part of the City of Columbus Capital Improvement plan, the project will convert several one-way downtown streets to accommodate both directions of traffic in an effort to be more user friendlier fo | Pavement Widening | 2010-04-19 | 2010-04-20 | 2011-12-31 | 2011-11-09 | 5500000 | 0.770 | E090535
9343 | OHIO | Underway | C220,C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 12 | E090536 | Parsons Avenue and Livingston Avenue surround the campus of Nationwide Children?s Hospital in Columbus. This project widens Livingston Avenue between Ohio Avenue and Ninth Street and Parsons Avenue be | Pavement Widening | 2010-06-01 | 2010-06-21 | 2012-07-31 |  | 15804875.51 | 1.080 | E090536
9344 | OHIO | Completed | C200,C230 | Highway Infrastructure Investment Grant | OHIO | DELAWARE | COLUMBUS | 12 | E090537 | The project connects a recently constructed commercial shopping area with the US 36 corridor and provides the surrounding properties with improvements and necessary access for additional development o | New Construction | 2010-04-21 | 2010-05-07 | 2011-09-30 | 2010-12-30 | 3465177 | 0.350 | E090537
9345 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 18 | E090540 | Install pavement markings on Mall Road and Banfield Road to increase safety. These are two of Belmont County highest volume of traffic roadways, and the pavement markings are very hard to maintain, be | Pavement Improvement | 2010-06-11 | 2010-08-22 | 2010-09-30 | 2010-08-30 | 27848.41 | 1.300 | E090540
9346 | OHIO | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | BELMONT |  | 06 | E090541 | Install a traffic control device at the intersection of State Route 7 and State Route 148 in the village of Powhatan Point. There are currently stop signs at this intersection because the traffic sign | Safety/Traffic Management | 2009-06-11 | 2009-06-11 | 2010-10-01 | 2010-12-08 | 122000 | 0.020 | E090541
9347 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | CARROLL |  | 18 | E090542 | The project will install new energy efficient traffic signals with integrated traffic demand devices in an effort to reduce traffic idling and fuel waste. With the installation of five new traffic sig | Safety/Traffic Management | 2009-06-05 | 2009-06-05 | 2010-10-01 | 2011-08-03 | 565794.25 | 0.100 | E090542
9348 | OHIO | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | HOLMES |  | 18 | E090543 | Repair and resurface over a mile of State Route 39 from Grant St. to Port Washington Rd. in the village of Millersburg as well as two miles of State Route 83 from Jackson St. to the western village co | Pavement Improvement | 2010-01-07 | 2010-04-01 | 2010-10-01 | 2010-10-19 | 222266.93 | 13.070 | E090543
9349 | OHIO | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | JEFFERSON |  | 18 | E090544 | SR 43 (Washington St) was built with concrete pavement in 1973 and is currently in very poor condition. The roadway is a four-lane, east-west arterial through the city, carrying approximately 15-18,00 | Pavement Improvement | 2009-08-07 | 2010-06-22 | 2011-09-30 | 2012-04-04 | 6713765.5 | 1.090 | E090544
9350 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TUSCARAWAS |  | 18 | E090545 | Renovation of three existing bridges on the county system, including steel beam repair and painting, deck repair, repair of waterproofing, and repair of wearing surface. The three bridges are located | Bridge Replacement | 2010-03-17 | 2010-05-07 | 2010-10-01 | 2010-09-28 | 1178514.5 | 0.100 | E090545
9351 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | ADAMS |  | 02 | E090547 | This project calls for resurfacing County Road 70 (Lloyd Road) and County Road 18 (Blue Creek Road), for a total of 0.90 miles of a Rural Major Collector Route and 4.38 miles of a Rural Minor Collecto | Pavement Improvement | 2010-03-19 | 2010-06-02 | 2010-06-30 | 2010-06-28 | 101066.97 | 0.950 | E090547
9352 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ROSS |  | 07 | E090548 | The project will rehabilitate and correct deficiencies of the U.S Rail in the city of Jackson. This rail service is crucial for business in rural, Appalachian Ohio serving two of the poorest counties, Jackson and Vinton. | Safety/Traffic Management | 2009-12-02 | 2009-12-02 | 2010-12-31 | 2010-12-11 | 1775347.21 |  | E090548
9353 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | SCIOTO |  | 06 | E090549 | It is proposed to resurface approximately 10 miles of roadway along county roads 28, 53, 1, 163 and 15. The project also includes milling where necessary, signs and pavement marking installation. This | Pavement Improvement | 2010-04-21 | 2010-07-01 | 2010-06-30 | 2010-08-30 | 1200000 | 8.670 | E090549
9354 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | HENRY |  | 05 | E090553 | The replacement and widening of the existing bridge along Oakwood Avenue in Napoleon will restore legal load limits to the structure, allowing for larger vehicles and trucks to use this potential hauling route. | Bridge Replacement | 2009-08-19 | 2009-08-31 | 2009-11-27 | 2010-10-11 | 400000 | 0.010 | E090553
9355 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | FULTON |  | 05 | E090554 | Resurfacing of State Route 66, S. Defiance Street, within the Village of Archbold from West Barre Road (CR C) north to the Norfolk-Southern Railway. This section of roadway was reconstructed by ODOT i | Pavement Improvement | 2010-03-17 | 2010-05-24 | 2010-07-30 | 2010-10-15 | 240000 | 0.420 | E090554
9356 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E090556 | Otter Creek Road is an important trucking route. This $3 million project reconstructs the concrete pavement and adds a new asphalt overlay to Otter Creek Road between Corduroy Road and Bay Shore Road, repairing massive cracking along the roadway. | Pavement Improvement | 2010-02-17 | 2010-04-12 | 2010-10-15 | 2011-07-15 | 2998709.1 | 2.160 | E090556
9357 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | OTTAWA |  | 09 | E090557 | This outdated bridge was built in 1954. By upgrading and rehabilitating this bridge, carrying Billman Road over Cedar Creek in Allen Township, this bridge will safely carry traffic in Allen Township for at least 40 more years. | Bridge Replacement | 2010-06-02 | 2010-08-01 | 2010-07-30 | 2011-06-24 | 292365 | 0.010 | E090557
9358 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | WILLIAMS |  | 05 | E090558 | Construction of this overhead bridge crane and conveyor system will render the Port Authority's Intermodal Facility fully operational. This bridge crane will be able to transload cargo from a barge on | Other | 2010-04-14 | 2010-05-17 | 2010-10-15 | 2010-10-19 | 393610.42 | 0.000 | E090558
9359 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E090559 | Norfolk Southern is committed to revise the layout of Airline Yard to increase the capacity from 30,000 lifts per year to 60,000 lifts per year, while minimizing any disruption of the adjacent rail line. | Other | 2010-07-01 | 2010-07-01 | 2012-03-01 |  | 6814000 |  | E090559
9360 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090560 | This is a project to upgarde signalization at 13 intersections in Lucas County and to perform necessary related work. | Safety/Traffic Management | 2009-09-14 | 2010-03-17 | 2009-12-18 | 2010-08-27 | 420000 | 0.010 | E090560
9361 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WOOD | TOLEDO (MI) | 09 | E090562 | This is a project to improve lighting from intersection of Bacon St & SR-65 to 2600 feet northeast, in the City of Rossford. | Safety/Traffic Management | 2010-05-10 | 2011-03-07 | 2010-08-13 | 2012-05-25 | 219270 | 0.490 | E090562
9362 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E090563 | This project will replace the Gibbs Road Bridge in Norwalk Township, east of the City of Norwalk. There is minimal road work involved; however the existing bridge is in poor condition. The ODOT bridge | Bridge Replacement | 2009-12-17 | 2010-03-12 | 2010-10-29 | 2010-05-25 | 208590.24 | 0.050 | E090563
9363 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | HURON |  | 05 | E090564 | The project will replace the deteriorated Ogan Rd Bridge, west of the Village of Wakeman. The existing 1-span steel beam bridge has a clear span of 28' and a width of 20'; has a bridge rating of 3P7 a | Bridge Replacement | 2009-07-09 | 2009-07-20 | 2010-10-29 | 2009-10-07 | 220000 | 0.130 | E090564
9364 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 13 | E090565 | The project proposes to mill and resurface 0.422 miles of South Broadway Ave., between Cooper Foster Parkway (State Route 611) and the State Route 2 interchange, in the City of Lorain. Other work incl | Pavement Improvement | 2010-04-29 | 2010-05-07 | 2010-10-29 | 2010-07-06 | 435760.5 | 0.780 | E090565
9365 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 13 | E090566 | Repair, Reconstruct and Resurface about 1.4 miles of Gateway Blvd., from Lake Ave. to Infirmary Rd. The roadway varies from 2 to 3 lanes (24 to 36 feet wide). This is a major arterial through the city | Pavement Improvement | 2010-03-15 | 2010-05-07 | 2010-10-29 | 2010-11-10 | 584998 | 1.220 | E090566
9366 | OHIO | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 13 | E090567 | The project involves the continued re-development of Lorain?s waterfront on a portion of a U.S. Army Corps of Engineers 58-acre dredge disposal site. The project is part of a plan to diversify Lorain? | Transportation Enhancements | 2009-09-14 | 2010-06-24 | 2010-10-29 | 2011-05-21 | 3281892.16 |  | E090567
9367 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | RICHLAND |  | 04 | E090568 | This project will renovate approximately 4700 centerline feet of existing streetscape in downtown Mansfield, including widening a section of State Route 430 and improving traffic congestion near State | Transportation Enhancements | 2010-04-08 | 2010-03-26 | 2010-10-29 | 2011-04-06 | 960808.05 | 1.060 | E090568
9368 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | RICHLAND |  | 04 | E090569 | Project consists of construction of approx. 3000' of new 29' curb & gutter street for an industrial park. Approx. 500' of existing street will be rebuilt on new vertical alignment to provide a safer i | New Construction | 2010-02-11 | 2010-04-12 | 2010-10-29 | 2010-12-02 | 1284248.88 | 1.080 | E090569
9369 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | MUSKINGUM |  | 18 | E090570 | This project involves overhauling and rehabilitating the overpasses carrying Zane Grey Road (County Road 199) and Moose Eye Road (County Road 436) over Interstate 70. To ensure continued safety for tr | Bridge Improvement | 2009-08-19 | 2009-08-31 | 2010-07-31 | 2010-07-23 | 1643207.67 | 0.080 | E090570
9370 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090574 | Union Boulevard from I-70 to National Road-Smooth sealing of the roadway. | Pavement Improvement | 2009-08-12 | 2009-09-17 | 2010-12-15 | 2009-11-04 | 200000 | 1.500 | E090574
9371 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090575 | This project is to pave Evanston Road from CR 25A easterly to the CSX RR tracks in Tipp City. | Pavement Improvement | 2009-09-03 | 2009-08-29 | 2009-09-30 | 2009-12-14 | 205140.12 | 1.590 | E090575
9372 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090576 | Plane and resurface West Stanfield Road from South Stanfield Road to 300' west of Industry Court. | Pavement Improvement | 2009-10-07 | 2009-10-16 | 2009-11-15 | 2010-03-24 | 76473.59 | 0.250 | E090576
9373 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090577 | Plane and resurface South Stanfield Road from State Route 41 to West Stanfield Road. | Pavement Improvement | 2009-10-07 | 2009-10-16 | 2009-12-15 | 2010-03-24 | 102667.4 | 0.380 | E090577
9374 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090578 | Wilmington Pike from Smithville Road to the Kettering North Corp Line -Mill the existing roadway, repair concrete pavement base, resurface and install new pavement markings, including raised pavement markers. | Pavement Improvement | 2009-11-10 | 2009-11-03 | 2010-07-02 | 2010-08-13 | 504277.85 | 1.000 | E090578
9375 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090579 | Various locations in Huber Heights-Rehab pavement at the following locations: Taylorsville Road from State Route 202 to Gentry Lane and from Wildcat Road to Timbercrest Drive; Powell Road from the wes | Pavement Improvement | 2009-11-23 | 2010-05-03 | 2010-06-15 | 2010-08-13 | 445399.26 | 0.530 | E090579
9376 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090580 | Maue Road from Heincke Road to Byers Road-Pavement milling, adjustment of valve boxes and manholes, crack sealing and asphalt overlay, and new pavement markings. | Pavement Improvement | 2010-05-12 | 2010-05-17 | 2010-06-08 | 2010-11-02 | 389400 | 1.190 | E090580
9377 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090581 | Olive Road from Salem Avenue to Main Street-Repair existing curbs as needed, pavement planing, full depth repairs, pavement overlay, new curbs and pavement markings. | Pavement Improvement | 2010-06-08 | 2010-07-19 | 2010-06-18 | 2011-06-08 | 792000 | 1.990 | E090581
9378 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090582 | Stonequarry Road from the Vandaila West Corp Line to the East Line of the Ashbury Farms Subdivision-Mill and resurface the roadway, water valves and manholes will be adjusted to grade, construct ADA curb ramps, striping and curb replacement. | Pavement Improvement | 2010-04-14 | 2010-05-17 | 2010-05-31 | 2010-07-13 | 267455.37 | 1.150 | E090582
9379 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090583 | Wolf Creek Street from McMaken Lane to Market Street-Mill and overlay roadway, including restriping and improving curb ramps. | Pavement Improvement | 2009-10-01 | 2010-04-28 | 2009-10-30 | 2010-06-18 | 200000 | 1.430 | E090583
9380 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090584 | Spinning Road from Airway Road to Linden Avenue-Slurry seal of the existing pavement with some full depth base repairs, utility manhole and valve adjustments and thermoplastic striping. | Pavement Improvement | 2010-01-08 | 2010-03-24 | 2010-05-31 | 2010-10-08 | 331397.73 | 2.030 | E090584
9381 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090585 | Paragon Road from Congress Park to Normandy Road and Paragon Road from Alex-Bell Road to Grants Trail-Street resurfacing. | Pavement Improvement | 2009-10-27 | 2010-05-07 | 2009-10-15 | 2010-06-02 | 205282 | 0.720 | E090585
9382 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090587 | Various locations in the City of Clayton-Install up to 179 handicap accessible ramps in two areas in the city. | Transportation Enhancements | 2010-03-16 | 2010-04-05 | 2010-05-31 | 2010-06-18 | 244468.08 |  | E090587
9383 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090588 | West Central Avenue from Miami Avenue to Walnut Street and Miami Avenue from Central Avenue to Hydraulic Road-Pavement planing and repaving to eliminate rutting and support heavy loads. Sections of cu | Pavement Improvement | 2010-03-05 | 2010-03-25 | 2010-06-15 | 2010-07-22 | 300960.44 | 0.150 | E090588
9384 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090589 | Patterson Boulevard/Riverside Drive Bridge over the Great Miami River-Replace backwalls, rehab main superstructure steel immediately adjacent to the backwalls and replace minor bracing members adjacent to the backwalls. | Bridge Improvement | 2010-03-17 | 2010-05-03 | 2010-11-29 | 2010-11-19 | 460800 | 0.030 | E090589
9385 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090590 | Little York Road Bridge over the Great Miami River-Replace the prestressed box beams due to beam delaminations and strand failure. | Bridge Replacement | 2010-05-27 | 2010-08-23 | 2010-11-05 | 2011-01-27 | 1294397.88 | 0.500 | E090590
9386 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090591 | Shoup Mill Road Bridge over the Stillwater River-Remove paint from the structural steel and reapply. Repair damaged guardrail. | Bridge Improvement | 2010-04-26 | 2010-07-06 | 2010-11-30 | 2011-01-27 | 573436.65 |  | E090591
9387 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090592 | Bigger Road from State Route 725 to the Centerville North Corp Line-Mill and resurface the existing roadway, maintenance to the curb, sidewalk and shared use path. Upgrade ramps to meet ADA compliance. | Pavement Improvement | 2009-10-22 | 2009-10-12 | 2010-07-12 | 2010-07-02 | 638526 | 1.040 | E090592
9388 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090593 | Washington Road from a point 1,200' north of State Route 41, north to Drake Road-Shoulder stabilization and asphalt overlay. | Pavement Improvement | 2010-03-10 | 2010-05-19 | 2010-07-30 | 2010-07-26 | 771717.64 | 1.000 | E090593
9389 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E090594 | Plane and resurface North Elm Street from State Route 41 to the Troy City Limits. | Pavement Improvement | 2009-10-07 | 2009-10-05 | 2009-11-30 | 2009-10-28 | 148373.42 | 0.380 | E090594
9390 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090595 | Various locations in Oakwood-Replace current curb ramps with ADA compliant ramps and associated work. | Safety/Traffic Management | 2010-01-07 | 2010-04-05 | 2010-05-31 | 2010-06-30 | 184209 | 2.840 | E090595
9391 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090598 | This project is for the rehabilitation of Main Street between I-277 and Firestone Blvd. This I-277 Corridor project involves reconstruction of four lanes of pavement on South Main Street in South Akro | Pavement Improvement | 2010-05-26 | 2010-08-02 | 2011-06-30 | 2012-04-18 | 4775323.77 | 0.620 | E090598
9392 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 11 | E090599 | This project is to repair the bridge surface and sidewalks on the Center Street Lift Bridge over the Cuyahoga River channel in the City of Cleveland. | Bridge Improvement | 2010-05-21 | 2010-05-27 | 2010-09-30 | 2012-08-28 | 2845462.91 | 0.100 | E090599
9393 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 11 | E090600 | This project consists of the reconstruction of E. 12th Street between from Superior Avenue to Chester Avenue in the City of Cleveland. Work includes removal of existing sidewalk, pavement planning and | Transportation Enhancements | 2010-06-08 | 2010-04-20 | 2010-09-30 | 2010-08-27 | 413619.14 | 0.490 | E090600
9394 | OHIO | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 11 | E090601 | In Cleveland, this project is to rehabilitate the Willow Street bridge over the Cuyahoga River channel | Bridge Improvement | 2010-04-23 | 2010-04-23 | 2010-09-30 |  | 3392348.88 | 0.030 | E090601
9395 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LICKING | COLUMBUS | 12 | E090604 | This project is in downtown Pataskala, Sidewalks, install ADA ramps and replace sidewalks. | Safety/Traffic Management | 2010-04-14 | 2010-04-26 | 2010-07-31 | 2010-08-05 | 184218.24 | 0.890 | E090604
9396 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E090605 | In Franklin County, resurfacing and pavement reconstruction of various roadways. Locations include Alkire Road from MAD County to Big Darby Creek; Brice Road from Chatterton Road to Refugee Road; Cas | Pavement Improvement | 2009-10-06 | 2009-09-11 | 2010-10-01 | 2010-02-15 | 1856743.46 | 12.870 | E090605
9397 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090606 | This project is along Alum Creek near Sunbury Rd from Mock Rd to Innis Rd at Innis Park. MORPC stimulus project funded 100% up to $3.0 M2.2 mile Muliti-use path, including three bridges and two neighborhood connector paths. | Transportation Enhancements | 2010-01-26 | 2010-02-08 | 2011-10-15 | 2011-05-31 | 3000000 |  | E090606
9398 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090607 | This project is in Reynoldsburg. Trail from Civic Park trailhead to Blackoak Drive. Civic Park multi-purpose trail.Blacklick Creek Greenway mulit-use path from Civic Park trailhead to Blackoak Drive. | Transportation Enhancements | 2010-04-29 | 2010-07-06 | 2011-06-01 | 2010-09-24 | 317219.2 |  | E090607
9399 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E090609 | Approximately 9000' of new sidewalks on school bus routes. Glenn Avenue: Tremont to Northwest; Waltham Road: Hampshire Road to Cambridge Blvd; Tremont Road: Pemberton Drive to Private Road; Mountview | Transportation Enhancements | 2010-01-04 | 2010-03-30 | 2010-11-01 | 2010-07-15 | 416000 |  | E090609
9400 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090610 | This project is in New Albany. Intersection of SR-605 and Walton Parkway. Install a new traffic signalization systsem including posts and mast arms. Repair pavement deficiencies, overlay 1.5" asphalt for 100,000 sq ft and restripe pavement. | Safety/Traffic Management | 2010-01-26 | 2010-04-01 | 2010-11-01 | 2010-10-15 | 343813.26 | 0.050 | E090610
9401 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E090611 | This project is in Hilliard. Intersection of CR-3/Avery Rd and Northwest Parkway. Intersection upgrade including sidewalks, multi-use path, and street lighting - Avery Rd and Norwest Pkwy. | Pavement Improvement | 2010-03-26 | 2010-04-05 | 2011-06-01 | 2010-12-13 | 918663.43 | 0.020 | E090611
9402 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090612 | This project is in Plain Twp. CR546/Dublin Granville Rd over Sugar Run. Just W of Harlem Road. Replace superstructure - concrete slab deck and rehab work to abutments and pier. | Bridge Improvement | 2010-04-13 | 2010-08-01 | 2011-06-01 | 2010-10-15 | 355179.7 | 0.010 | E090612
9403 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | DELAWARE | COLUMBUS | 12 | E090613 | Replace deck and superstructure members.Modify or replace bridge abutments.Possible piers work, minor roadway approach work, guardrail replacement. Vilage of Galena. South Old 3C Highway over Hoover Reservoir. | Bridge Improvement | 2010-01-21 | 2010-07-06 | 2010-10-01 | 2010-09-30 | 659753 | 0.040 | E090613
9404 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090614 | This project is in Whitehall. From Broad St to Mayflower Blvd. Yearling Road Reconstruction Phase 3Signalization, street lighting, storm sewer, ADA sidewalk, and traffic signal improvements. | Pavement Improvement | 2010-04-21 | 2010-05-03 | 2011-09-01 | 2010-10-21 | 2258044.16 | 0.450 | E090614
9405 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090615 | This project is in Blendon Twp. CR-18/Central College Rd over Big Walnut Creek. 0.27 mi E of Sunbury Rd. MORPC funded stimulus project for $960,000.Replace existing superstructure - prestressed box b | Bridge Improvement | 2010-03-17 | 2010-04-19 | 2011-06-01 | 2010-08-01 | 910000 | 0.080 | E090615
9406 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090616 | This project is in Bexley. Urban core ADA Accessibility.Sidewalks, curb ramps, sidewalk improvements, and traffic signal improvements for better ADA accessibility. | Transportation Enhancements | 2010-03-15 | 2010-04-19 | 2011-09-01 | 2011-11-08 | 800779.9 | 2.430 | E090616
9407 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090633 | This is a project to rehabilitate George Hardy Dr., From Tiffin Ave to Saint Lawrence Dr in the Port of Toledo; and to perform necessary related work | Pavement Widening | 2010-03-29 | 2010-05-07 | 2010-08-13 | 2010-10-20 | 901337.85 |  | E090633
9408 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090634 | This is a project to mill and fill Illinois Ave (US-20A) in the City of Maumee from Ford St to west of Conant St (US-20) and to perform necessary related work. | Pavement Improvement | 2010-02-11 | 2010-05-31 | 2010-07-30 | 2010-06-15 | 448004 | 0.860 | E090634
9409 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WOOD | TOLEDO (MI) | 05 | E090635 | This project is to resurface S. Main St (SR-25) in the City of Bowling Green from Clay St to Dill Ave; The project includes some curb and curb ramp replacements. The sidewalk on the east side | Pavement Improvement | 2010-03-17 | 2010-06-03 | 2010-08-31 | 2010-10-15 | 501851.88 | 0.450 | E090635
9410 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090636 | This project is to to resurface Hill Ave, in the City of Toledo, from Westwood Ave to Detroit Ave. | Pavement Improvement | 2009-11-09 | 2010-03-29 | 2010-11-19 | 2010-09-21 | 1175000 | 0.830 | E090636
9411 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090637 | This project is to resurface South Ave, in the City of Toledo, from Airport Hwy (SR-2) to Detroit Ave (US-24) | Pavement Improvement | 2009-11-17 | 2010-05-10 | 2010-05-21 | 2010-06-22 | 202522 | 0.210 | E090637
9412 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WOOD | TOLEDO (MI) | 09 | E090638 | This project is to improve the intersection of Curtice Rd and Bradner Rd in the City of Northwood | Safety/Traffic Management | 2010-04-27 | 2010-06-11 | 2010-06-11 | 2010-11-08 | 61506 | 0.010 | E090638
9413 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090639 | The project includes rehabilitating the existing Frank Boulevard including a reconstructed intersection with White Pond Drive | Pavement Improvement | 2010-06-03 | 2010-04-19 | 2010-12-31 | 2011-05-11 | 2156644.31 | 0.440 | E090639
9414 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090650 | This project is on Galbraith from Deer Park West Corp line to Blue Ash Road to resurface and restore pavement, curbs, improve drainage, and replace traffic loops | Pavement Improvement | 2009-12-10 | 2010-03-29 | 2010-07-02 | 2010-10-28 | 523840 | 0.540 | E090650
9415 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090653 | This project involves Troy Ave and Morse Road. Resurfacing, curb replacement, base repairs, inlet reconstruction and storm sewer to restore roadway intergrity and ride quality and improve drainage. | Pavement Improvement | 2010-01-07 | 2010-03-29 | 2010-09-15 | 2010-09-15 | 207799.43 | 0.350 | E090653
9416 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E090656 | There are four interrelated and interdependent highway infrastructure projects within this important regional transportation center. The project along SR 45 begins at the intersection of I-90 and SR 4 | Safety/Traffic Management | 2010-06-15 | 2010-08-03 | 2010-12-31 | 2011-12-15 | 622073 | 0.130 | E090656
9417 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E090658 | Reconstruction and paving of North Eagle Street in the city of Geneva. | Pavement Improvement | 2009-07-09 | 2009-07-09 | 2010-09-30 | 2010-09-01 | 450000 | 0.500 | E090658
9418 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E090659 | This project is for the resurfacing and improvements to Middle Road. The area is heavily traveled and located in a major manufacturing area. | Pavement Improvement | 2010-05-05 | 2010-06-09 | 2010-09-30 | 2010-09-20 | 769764 | 4.680 | E090659
9419 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E090660 | The Norfolk Southern Line relocation entails the relocation of rail line in conjunction with the $900,000,000 steel mill expansion. The project will free up 100 acres for future growth and development. | Safety/Traffic Management | 2009-11-02 | 2009-11-06 | 2011-12-15 | 2010-06-11 | 3464899.32 |  | E090660
9420 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090661 | The Fulton Road/Park Dr. NW Intersection Improvement includes the widening and addition of turn lanes to Park Drive north and south of Fulton Rd. NW; full width road pavement reconstruction with concr | Safety/Traffic Management | 2010-04-01 | 2010-05-03 | 2010-09-30 | 2011-01-26 | 368994.98 | 0.010 | E090661
9421 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090662 | The Sherrick Road stabilization project includes the injection of High Density Polyurethane (HDPE) Foam columns to stabilize the sanitary sewer trench; install ADA compliant curb ramps; and the profil | Pavement Improvement | 2010-02-17 | 2010-05-03 | 2010-12-01 | 2010-08-20 | 1072305.53 | 0.720 | E090662
9422 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090663 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project will involve three (3) crossings in Hartville and the surrounding area. One of the crossings wa | Safety/Traffic Management | 2009-11-12 | 2009-11-12 | 2010-08-31 |  | 540000 | 0.010 | E090663
9423 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090664 | This project is Wheeling Lake Erie Rail Line track rehabilitation in Stark, Portage, Jefferson, Wayne, Lorain, Tuscarawas, and Cuyahoga counties | Other | 2009-09-08 | 2009-09-08 | 2010-12-15 | 2010-10-22 | 1200000 |  | E090664
9424 | OHIO | Completed | C220,C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090665 | The city of Akron is proposing to hydro-demo and resurface approximately 24,500 squar yards of the Y-Bridge deck from Perkins to the northern limits of the bridges along with other minor associated br | Bridge Improvement | 2009-11-25 | 2010-03-29 | 2011-05-01 | 2011-12-22 | 6326527.82 | 0.920 | E090665
9425 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E090666 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. The communities of Hudson, Macedonia and Northfield Center requested Federal Stimulus Funds to pursue a quie | Safety/Traffic Management | 2010-03-03 | 2010-06-02 | 2011-03-03 | 2010-11-04 | 168323 | 0.010 | E090666
9426 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E090668 | Resurfacing Olive St from Ohio Ave to northern corp. limits in the Village of McDonald | Pavement Improvement | 2009-11-12 | 2010-04-27 | 2010-08-01 | 2010-05-13 | 182752.56 | 0.500 | E090668
9427 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090669 | Resurfacing 12th street from Robinson Rd to Coitsville Rd in the city of Campbell. | Pavement Improvement | 2009-11-25 | 2009-12-23 | 2010-09-01 | 2010-06-11 | 335339.66 | 1.220 | E090669
9428 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090677 | This project involves Dining Lane to Catalina Apartments west driveway. Resurface, curb replacement, base repairs and inlet reconstruction to restore roadway integrity and ride quality and improve drainage. | Pavement Improvement | 2010-01-08 | 2010-03-29 | 2010-09-15 | 2010-08-20 | 239881.89 | 1.100 | E090677
9429 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090679 | This project consists of 2 parts. Part one will replace a 700 foot bridge over the Scioto River with minimal appraoch work. This new bridge will connect to Rich Street and to reconstruct Washington Bl | Pavement Improvement | 2010-02-19 | 2010-03-03 | 2011-08-31 | 2012-07-10 | 2076961.6 | 0.210 | E090679
9430 | OHIO | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | PORTAGE | AKRON | 14 | E090680 | This project is to replace or rehabilitate the bridge over the Cuyahoga River and CSX. It will also improve the Crain Ave intersection | Bridge Replacement | 2009-07-31 | 2009-09-18 | 2012-12-01 |  | 3000000 | 0.090 | E090680
9431 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ROSS |  | 18 | E090681 | State Route 104 is currently a two-lane highway between U.S. Route 35 and the new state Route 207 extension to U.S. Route 23, and it serves as the northwest bypass of Chillicothe. The project consists | Pavement Improvement | 2009-07-01 | 2009-07-02 | 2010-09-30 | 2010-10-31 | 6530215.42 | 3.760 | E090681
9432 | OHIO | Underway | C200 | Highway Infrastructure Investment Grant | OHIO | HOCKING |  | 06 | E090683 | This is part 2 of 3 for the Nelsonville By-Pass Project. The portion of this project is for preliminary engineering and right of way activities. | New Construction | 2009-09-29 | 2009-10-07 | 2012-03-03 |  | 46212804.42 | 4.560 | E090683
9433 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090684 | In Lucas county, widening of Wheeling Street from Navarre (SR2) to Pickle Road. This includes widening the bridge over I-280 in the City of Oregon | Pavement Widening | 2010-05-05 | 2010-06-21 | 2011-11-18 | 2012-08-02 | 1533310.28 | 0.510 | E090684
9434 | OHIO | Completed | C220,C200 | Highway Infrastructure Investment Grant | OHIO | DEFIANCE |  | 05 | E090685 | This project is to widen and add concrete islands to SR-66 corridor through Defiance. This activity will reduce the high rate of accidents caused by unsafe turning along the city?s busiest business c | Pavement Widening | 2010-02-02 | 2010-02-24 | 2010-10-31 | 2010-11-12 | 3193503.37 | 1.440 | E090685
9435 | OHIO | Underway | C240,C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E090686 | Construct a grade separation at Columbia Road (SR-252) and the CSX Railroad Company tracks in the City of Olmsted Falls, from north of Sprague Road to the Ohio Turnpike (IR-80). | New Bridge Construction | 2009-03-27 | 2009-07-21 | 2011-06-30 |  | 7693000 | 0.350 | E090686
9436 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 12 | E090687 | This project provides for the realignment and reconstruction of Waterworks Road and Deo Drive at State Route 13 and relocation and improvement the existing Railroad crossing. | Safety/Traffic Management | 2010-03-31 | 2010-04-08 | 2010-10-31 | 2010-11-05 | 1800000 | 0.500 | E090687
9437 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | HOCKING |  | 06 | E090688 | The US 33 Corridor is a designated National Highway System route that extends from Michigan to Virginia and includes the Nelsonville Bypass. This construction project will focus on the west end of a n | New Construction | 2009-09-14 | 2009-09-21 | 2013-10-18 |  | 94317302.53 | 3.040 | E090688
9438 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | UNION | COLUMBUS | 07 | E090691 | This project takes place at the Intersection of SR-161, CR1(Industrial Parkway) and CR24 (Post Rd). MORPC stimulus project for $1,000,000.Realignment of 2050' of Industrial Parkway on north side of S | New Construction | 2009-11-02 | 2009-11-15 | 2012-10-01 | 2011-07-29 | 1000000 | 0.820 | E090691
9439 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090692 | Resurfacing from Main St to Beloit Village limit with ADA compliant intersections. | Pavement Improvement | 2009-08-04 | 2009-08-27 | 2009-10-30 | 2009-10-06 | 161158.41 | 0.750 | E090692
9440 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | LICKING |  | 12 | E090703 | The project begins at SR79 at the intersection of South High Street and terminates at the North end in a cul-de-sac created when the new SR79 was created. A two lane roadway (formerly SR79) passes thr | Pavement Improvement | 2010-02-16 | 2010-05-17 | 2010-08-31 | 2010-08-02 | 335989.27 | 1.720 | E090703
9441 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | SHELBY |  | 08 | E090705 | This project is to install new curb ramps and driveway aprons using brick pavers & stamped concrete on State Street in Shelby County. | Transportation Enhancements | 2011-01-28 | 2011-03-21 | 2011-11-15 | 2011-11-03 | 374306 | 0.140 | E090705
9442 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LAKE |  | 14 | E090708 | This section of four lane roadway, which is on the federal aid system, was rated in the ?poor? category during a 2006 pavement condition rating performed by our local Metropolitan Planning Organizatio | Pavement Improvement | 2010-06-02 | 2010-06-07 | 2010-09-30 | 2011-03-07 | 2528188.52 | 3.030 | E090708
9443 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | PREBLE |  | 08 | E090709 | Replace small culvert; existing culvert is an 84? by 40? cast-in-place concrete culvert in Preble county | Pavement Improvement | 2009-06-19 | 2009-07-31 | 2009-08-15 | 2009-08-07 | 129940.63 | 0.010 | E090709
9444 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090710 | In Butler county, resurface sections of Tylersville and River Roads and replace striping. | Pavement Improvement | 2009-08-05 | 2009-09-08 | 2010-04-02 | 2009-12-08 | 1857217.45 | 6.000 | E090710
9445 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CLERMONT | CINCINNATI (KY) | 02 | E090711 | This project is to resuface county roads in Clermont county and add curb and ADA curb ramps on Buckwheat Road | Pavement Improvement | 2009-10-20 | 2009-08-26 | 2010-06-11 | 2009-12-18 | 2464300 | 32.480 | E090711
9446 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090712 | Construct second phase of Access Road from Union Road to State Route 380, south and west of US 35 and Route 68 interchange. | New Construction | 2009-11-06 | 2009-12-14 | 2011-04-18 | 2011-07-15 | 1350905.49 |  | E090712
9447 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090713 | Overlay of pavement, striping and berm repair of Valley Road from Upper Bellbrook Road to US 35 | Pavement Improvement | 2009-09-02 | 2009-09-11 | 2010-04-16 | 2009-09-18 | 182714.87 | 1.790 | E090713
9448 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090714 | This project is to resurface a portion of Blue Rock Road in Hamilton county. This will include base repair and replacing guardrail. | Pavement Improvement | 2010-03-17 | 2010-04-19 | 2010-05-30 | 2010-10-15 | 500000 | 1.350 | E090714
9449 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090715 | This project is to microsurface Cornell Road from the bridge over I-71 to the bridge over I-275. This will include new pavement marking and curb ramps. | Pavement Improvement | 2009-09-29 | 2009-09-18 | 2010-05-01 | 2009-10-16 | 95520.86 | 0.680 | E090715
9450 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090716 | Resurface a portion of the Reed Hartman Hwy. Also, perform pavement repair, curb & gutter repair, replace signal loops with video detection, replacing pavement striping, place new RPMs, and where ap | Pavement Improvement | 2009-08-12 | 2009-08-10 | 2010-04-02 | 2009-11-13 | 675121.57 | 1.200 | E090716
9451 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WARREN | CINCINNATI (KY) | 02 | E090717 | Resurfacing of Kings Island Drive from the theater entrance to Western Row Road. | Pavement Improvement | 2009-11-25 | 2009-11-16 | 2010-03-17 | 2010-05-06 | 307880 | 1.200 | E090717
9452 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090718 | This project is for resurfacing, curb replacement, base repairs and inlet reconstruction on Harrison Ave from Section Road to Lovell Avenue to restore roadway integrity | Pavement Improvement | 2009-11-06 | 2009-10-09 | 2010-08-13 | 2010-06-01 | 526465.82 | 1.000 | E090718
9453 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090719 | This project is in the city of Middleton on Sutphin between Grand Avenue to Central Avenue to resurface, spot curb and gutter repair, and ensurecurb ramps to be ADA compliant. | Pavement Improvement | 2010-05-04 | 2010-06-07 | 2010-08-10 | 2010-09-28 | 716542.94 | 0.920 | E090719
9454 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090720 | This project is in Middleton on University Blvd from Reinartz Blvd. to Briel to resurface, spot curb and gutter repair, and ADA compliant curb ramps | Pavement Improvement | 2010-04-07 | 2010-04-19 | 2010-09-02 | 2010-09-28 | 1920838.04 | 0.380 | E090720
9455 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WARREN | DAYTON | 03 | E090721 | Various locations on State Route 73 and State Route 741 in Springboro-Replace existing traffic signal lamps with LED lamps. Install three battery backups and interconnect three traffic signals between | Safety/Traffic Management | 2010-01-07 | 2010-08-10 | 2010-12-01 | 2010-12-30 | 173090.66 | 0.010 | E090721
9456 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WARREN | DAYTON | 02 | E090722 | Franklin-Trenton Road from the Franklin West Corp Line to Park Ave.-Resurface roadway including restriping and making curb ramps ADA compliant. | Pavement Improvement | 2009-12-09 | 2010-04-13 | 2010-06-23 | 2010-05-03 | 201991.86 | 1.800 | E090722
9457 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090723 | From the intersection of Miami Avenue and South Detroit Street to 150' east of the intersection of Hill Street and South Detroit Street-Realign and widen sidewalks, replacing and aligning curb ramps, | Transportation Enhancements | 2010-04-22 | 2010-03-26 | 2010-12-01 | 2010-04-09 | 17264.36 |  | E090723
9458 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WARREN | CINCINNATI (KY) | 02 | E090724 | In Warren county, on Columbia road and various county roads resurface, stripe, and add berm and curb ramp. | Pavement Improvement | 2009-12-09 | 2010-04-02 | 2010-12-01 | 2010-06-17 | 1750678.44 | 1.000 | E090724
9459 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090726 | In the village of Terrace Park on US 50 from Milford/Terrace Park Corp Line to Elm St. catch basin repair, curb replacement, install curb ramps as required, sidewalk replacement where necessary, impr | Safety/Traffic Management | 2010-03-16 | 2010-03-18 | 2010-09-30 | 2010-09-28 | 716127.65 | 1.400 | E090726
9460 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090727 | East Main Street from Whiteman Street to Collier Street-Streetscape improvements that include curbs, replacing sidewalks, driveway apron improvements, aesthetic enhancements in the form of tree remova | Transportation Enhancements | 2010-04-23 | 2010-04-19 | 2010-12-01 | 2010-08-23 | 178360.36 | 0.100 | E090727
9461 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090728 | Colonel Glenn Highway from the west corp. of Beavercreek to National Road-Mill and resurface the roadway. Includes base repairs, pavement markings, restoration of traffic signal loops, curb ramp upgrades and installation of raised pavement markers. | Pavement Improvement | 2010-02-02 | 2010-04-06 | 2010-08-13 | 2010-05-28 | 306972.14 | 0.490 | E090728
9462 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E090729 | Creekside Trail from the Beavercreek WCL to the Beavercreek East Corp Line -Resurface the bikepath, install top soil berms, upgrade curb remps at crossing, replace/repair expansion joints on path bridge over I-675. | Transportation Enhancements | 2010-01-27 | 2010-04-19 | 2010-08-13 | 2010-07-28 | 190248 |  | E090729
9463 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090730 | On Northland Blvd in Springdale, repair the concrete base, extend the west bound turn lane, widen the east boun turn land, curb replacement, catch basin repair, resurfacing, and a pedestrian walkway. | Pavement Improvement | 2010-04-29 | 2010-04-26 | 2010-12-01 | 2010-10-15 | 876221.37 | 0.820 | E090730
9464 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090731 | This project is on Mosteller Rd from Sharon Road to 400 ft south of Kemper to resurface, replace curbs, base repairs, and inlet construction | Pavement Improvement | 2010-04-29 | 2010-04-19 | 2010-10-01 | 2011-04-29 | 699499.99 | 1.020 | E090731
9465 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E090732 | In Cincinnati replacement and expansion of the existing computerized traffic control system interconnect cabling. The current cable is telephone grade twisted pair wire and the project will replace this cable with fiber optic communications cable. | Other | 2010-04-22 | 2010-07-27 | 2010-09-10 | 2012-08-17 | 1148265.13 |  | E090732
9466 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090734 | This project is to complete the construction of missing segments of the multi us path within the Oxford Community Park | Pavement Improvement | 2010-04-27 | 2010-05-14 | 2010-10-30 | 2010-08-27 | 184268.82 |  | E090734
9467 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E090747 | This project is in Columbus and includes various routes in the City of Columbus. Regional resurfacing program in City of Columbus. | Pavement Improvement | 2009-09-09 | 2009-09-08 | 2010-06-15 | 2010-08-15 | 2308108 | 6.200 | E090747
9468 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | DELAWARE | COLUMBUS | 12 | E090748 | In Delaware County, resurfacing and pavement reconstruction of various county roads and city streets. Locations include London Road in the City of Delaware from US42 north 0.10 miles; Liberty Street | Pavement Improvement | 2009-10-08 | 2009-10-02 | 2010-10-01 | 2010-05-30 | 1795005 | 14.070 | E090748
9469 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 11 | E090751 | Widening of the ramp from I-490 eastbound to I-77 northbound and re-facing of the outside parapets on the I-77 bridge over U.S. 422 (Orange Avenue) and East 30th Street. The work includes replacement | Bridge Improvement | 2009-05-18 | 2009-06-02 | 2009-10-31 | 2010-05-14 | 2561008.82 | 0.840 | E090751
9470 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WOOD |  | 09 | E090752 | This project consists of replacing the current bridge deck surface on the Disalle bridge crossing the Maumee River. Additional bridge work will be performed at Miami Street overpass and railroad bridg | Bridge Improvement | 2009-06-15 | 2009-06-15 | 2010-10-15 | 2011-06-10 | 5585106.13 | 0.820 | E090752
9471 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HARRISON |  | 18 | E090753 | Three bridges on U.S. 22 (eastbound U.S. 22, westbound U.S. 22, and the westbound on-ramp to U.S. 22) over an abandoned railroad just west of SR 9 in Cadiz Township will be removed and replaced with e | Bridge Replacement | 2009-05-26 | 2009-06-30 | 2009-11-15 | 2010-06-11 | 910619.13 | 0.030 | E090753
9472 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN |  | 12 | E090754 | Resurface two miles of US 40 between Hague Avenue and Central Avenue in Columbus including the ramp from I-70 eastbound to Broad Street and the ramp from Broad Street to I-70 westbound. | Pavement Improvement | 2010-06-01 | 2010-07-06 | 2010-08-31 | 2011-06-09 | 654980 | 1.960 | E090754
9473 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TUSCARAWAS |  | 18 | E090755 | Resurfacing nearly four miles of U.S. 250 from SR 800 at Dennison to the Harrison County line, and just over a mile of SR 800 from Thornwood Park in Dennison to U.S. 250. | Pavement Improvement | 2009-07-17 | 2009-09-11 | 2009-10-15 | 2010-05-11 | 1039889.3 | 4.990 | E090755
9474 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LOGAN |  | 04 | E090756 | This project is to resurface Main Street in Bellefontaine from Lake Street (SLM 7.32) to Water Street (SLM 7.94) with asphalt concrete. | Pavement Improvement | 2009-06-25 | 2009-09-16 | 2009-09-15 | 2009-10-13 | 227525 | 0.620 | E090756
9475 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 10 | E090757 | The project calls for a complete ramp replacement at the Interstate 480/West 130th Street interchange in the city of Cleveland. The work will include a complete replacement of aging pavements. | Pavement Improvement | 2009-08-27 | 2009-09-25 | 2010-06-30 | 2010-05-28 | 782661.35 |  | E090757
9476 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | ASHLAND |  | 16 | E090767 | This project will replace the bridge over Jerome Fork on SR89 in Ashland County. | Bridge Replacement | 2009-06-26 | 2009-08-17 | 2010-08-15 | 2010-02-01 | 388030.82 | 0.040 | E090767
9477 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | PORTAGE | AKRON | 14 | E090769 | This project is to resurface Chestnut street from Ravenna South Corp to State Route 14. | Pavement Improvement | 2010-04-19 | 2010-04-26 | 2010-08-31 | 2010-10-04 | 616000 | 2.570 | E090769
9478 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | PORTAGE | AKRON | 14 | E090770 | This project is for the consturction of curbs and gutters with some storm sewer on SR 305 from State Route 700 to East Corp limit. | Pavement Improvement | 2010-02-24 | 2010-05-13 | 2010-07-31 | 2010-07-30 | 143600 | 0.480 | E090770
9479 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090771 | In the City of Norton, Summit County, rehabilitation of 2.59 miles of Greenwich Road beginning at the Medina County line and ending at Cleveland-Massillon Road. Included in the rehabilitation are mill | Pavement Improvement | 2010-03-29 | 2010-03-29 | 2010-09-30 | 2010-07-28 | 469724.32 | 3.300 | E090771
9480 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090772 | This project invloves reconstruction, Including traffic signal upgrade on Summit CR 512 from Triplett Boulevard to East Market Street. | Pavement Improvement | 2010-04-19 | 2010-04-05 | 2010-12-31 | 2011-10-15 | 2224006 | 1.160 | E090772
9481 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090773 | This project invloves Mogadore Road at Cleveland Avenue, with removal of retaining wall, and increasing turning radius. | Safety/Traffic Management | 2010-03-24 | 2010-04-30 | 2010-06-30 | 2010-07-06 | 54729.72 | 0.010 | E090773
9482 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090779 | This project invloves resurfacing of Liberty Road from Cannon Road to Cuyahoga County line. | Pavement Improvement | 2009-11-06 | 2009-10-05 | 2010-08-31 | 2010-04-30 | 444263.97 | 2.540 | E090779
9483 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090780 | This project involves Reconstruction and Adding turn lanes on Summit CR 145 from Wyoga Lake Road to Allen Road. | Pavement Widening | 2009-06-05 | 2010-03-01 | 2010-12-31 | 2011-04-11 | 2534693.05 | 1.170 | E090780
9484 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E090781 | This project involves Wheatley Road at Brecksville Road. Construct turn lanes. Install new traffic signal. Upgrade existing signal. | Safety/Traffic Management | 2010-06-23 | 2010-08-09 | 2010-09-30 | 2011-06-13 | 239800 | 0.030 | E090781
9485 | OHIO | Completed | C250,C240 | Highway Infrastructure Investment Grant | OHIO | ASHLAND |  | 16 | E090785 | This project will replace a deficient 3-span steel beam bridge over the Muddy Fork on State Route 302, 0.19 mile west of Township Road 63, in Perry Township. This is east of the community known as Red Haw. | Bridge Replacement | 2009-06-25 | 2009-08-31 | 2010-07-15 | 2009-11-06 | 424648 | 0.030 | E090785
9486 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | WAYNE |  | 16 | E090786 | This project will rehabilitate a deficient bridge on SR 301 in Wayne county over Interstate 71. | Bridge Improvement | 2009-07-17 | 2010-04-26 | 2010-10-15 | 2011-05-11 | 1418988.31 | 0.010 | E090786
9487 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E090787 | This project is in the city of Monroe to install new signal at Britton and improve signal at intersection of Cincinnati Dayton Road and SR 63 by adding backplates, led heads, and dilemma zone detection. | Safety/Traffic Management | 2010-06-04 | 2010-08-03 | 2010-11-01 | 2011-07-01 | 543960 | 0.290 | E090787
9488 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E090788 | To provide access to work for low income individuals not able otherwise to hold a job. Some of these services are provided directly by GCRTA and some are contracted to other area transportation providers. | Other | 2009-09-23 | 2009-09-23 | 2011-09-23 | 2010-08-31 | 1863358 |  | E090788
9489 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090789 | This project is to resurface Telegraph Rd (US-24) from Alexis Rd (SR-184) to just south of the Michigan State Line in the City of Toledo. | Pavement Improvement | 2009-11-09 | 2010-05-05 | 2010-05-28 | 2010-06-18 | 315000 | 0.530 | E090789
9490 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E090790 | This project is to resurface Detroit Ave (US-24) in the City of Toledo from I-75 near Monroe St to Central Ave (SR-120). | Pavement Improvement | 2009-11-09 | 2010-05-07 | 2010-06-04 | 2010-08-31 | 570000 | 0.860 | E090790
9491 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 10 | E090792 | Track rehabilitation work to reduce derailment expenses and help railroad provide reliable service to two rail-dependent businesses that employ a total of 50 people. | Other | 2010-05-27 | 2010-06-01 | 2010-10-01 | 2010-08-31 | 66988 |  | E090792
9492 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | KNOX |  | 18 | E090793 | Knox and Muskingum Counties are considered smaller to medium sized counties with populations that have grown in the last decade. The average driver in these counties spends between 16 and 26 minutes i | Bridge Improvement | 2009-08-28 | 2009-09-04 | 2009-10-31 | 2009-12-03 | 1100000 | 0.460 | E090793
9493 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LAWRENCE |  | 06 | E090794 | The project will construct access roads to allow for better access handling between Ohio River barges, rail and highway freight and spur the development of the South Point Inter-modal Transfer Facilit | Other | 2010-04-01 | 2010-04-15 | 2010-10-04 | 2011-12-30 | 1211028.62 |  | E090794
9494 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090795 | In Hamilton county on Galbraith Rd from Daly Road to Winton, remove and replace pavement with ajacent curbs and sidewalk. Also replace the signal Galbraith and Mockingbird. | Pavement Improvement | 2010-04-23 | 2010-04-29 | 2010-10-15 | 2011-03-30 | 1528181.01 | 0.590 | E090795
9495 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090797 | The project consists of infrastructure repairs along Woodman Drive from north of US 35 and Linden Avenue to the community of Beavercreek. The improvement work in both areas include milling and asphalt | Pavement Improvement | 2010-03-31 | 2010-05-10 | 2010-05-31 | 2010-12-03 | 1373617.39 | 2.160 | E090797
9496 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PIKE |  | 02 | E090798 | The project will improve the cloverleaf interchange at U.S. Route 23 and the exit for the Portsmouth Gaseous Diffusion Plant (A-Plant), south of Piketon, by creating access to the west side and into t | Pavement Improvement | 2010-05-03 | 2010-05-19 | 2010-10-31 | 2011-06-16 | 1420005.74 | 0.010 | E090798
9497 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LORAIN |  | 05 | E090799 | This project consists of a safety upgrade for quiet zone in North Ridgeville. | Safety/Traffic Management | 2010-10-04 | 2010-10-04 | 2012-05-11 | 2012-05-11 | 800000 |  | E090799
9498 | OHIO | Completed | C250 | Highway Infrastructure Investment Grant | OHIO | WAYNE |  | 16 | E090800 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project involves five grade crossings on the W&LE rail line between Smithville and Orrville. All five c | Safety/Traffic Management | 2009-09-16 | 2009-10-20 | 2010-06-17 | 2010-06-13 | 793842.51 |  | E090800
9499 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | CLARK |  | 07 | E090801 | This project expands the existing investment by the State of Ohio and the West Central Ohio Port Authority (WESTCO) by improving bridge and track conditions on the rail lines. | Other | 2009-11-04 | 2009-11-12 | 2011-12-31 | 2010-11-20 | 1000000 |  | E090801
9500 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | COLUMBIANA |  | 17 | E090802 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project will install state-of-the-art warning devices and a new high-type grade crossing surface at the grade crossing on US30. | Safety/Traffic Management | 2010-02-18 | 2010-06-04 | 2010-06-30 | 2010-07-02 | 250000 |  | E090802
9501 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 13 | E090803 | The City of Medina obtained a long-term lease for this line in 1985, and has been working with numerous public and private partners to rehabilitate the line. Shippers along the line have consistently | Other | 2011-09-23 | 2011-09-23 | 2011-12-31 | 2011-12-21 | 949794.62 |  | E090803
9502 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | PORTAGE | AKRON | 14 | E090807 | In the City of Aurora (Portage Co.), widening and resurfacing of 2.15 miles of SR 43 (North Aurora Road) including new storm sewer, curb and gutter, water mains, traffic signals, signing and pavement markings. | Pavement Improvement | 2009-07-17 | 2009-08-31 | 2010-12-31 | 2011-12-15 | 1000000 | 2.010 | E090807
9503 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA, SUMMIT |  | Multiple | E090808 | This is a two-part project to install a new intelligent transportation system. Part 1 (Cuyahoga, Lorain, Medina, Summit, Portage & Lake Counties) includes the putting in place of approximately 83 traf | Safety/Traffic Management | 2009-08-21 | 2009-10-21 | 2011-09-30 |  | 19895582.82 |  | E090808
9504 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LAKE | CLEVELAND, OH | 14 | E090811 | Traffic signal and widening improvements along SR-91 in Willougby Hills. | Safety/Traffic Management | 2010-04-05 | 2010-05-18 | 2010-09-30 | 2011-06-01 | 862360 | 2.380 | E090811
9505 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 10 | E090812 | This project is located in the City of Cleveland on Lorain Avenue between the City of Cleveland west corporation limit and Groveland Avenue. This project is a streetscape improvement that includes new | Transportation Enhancements | 2010-06-08 | 2010-06-14 | 2010-10-30 | 2011-09-15 | 1450410.56 | 0.530 | E090812
9506 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | GEAUGA | CLEVELAND, OH | 14 | E090813 | In Geauga county this project will resurface Auburn Road from Kinsman Rd. to Fairmount Rd. in Newbury Twp | Pavement Improvement | 2009-12-01 | 2010-05-24 | 2010-06-30 | 2010-09-01 | 279635.46 | 1.770 | E090813
9507 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LAKE | CLEVELAND, OH | 14 | E090820 | This project is to resurface Lake Road in Madison Twp. | Pavement Improvement | 2011-03-10 | 2011-04-04 | 2011-12-02 | 2011-12-12 | 557556.82 | 0.890 | E090820
9508 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E090846 | In Stark County, CR-98, from SR-241(Wales Ave.) to Brunerdale Ave. Widen existing road to four lanes with curb and gutters. Increase to 5 lanes at all major intersections. Includes Storm Sewer and traffic signals. | Pavement Widening | 2009-06-15 | 2009-09-21 | 2010-12-31 | 2011-12-01 | 4800000 | 2.540 | E090846
9509 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E090848 | Resurfacing of Fairground Blvd from SR 46 east to city limits. Resurfacing of Herbert Rd from the east city limits to the west city limits. | Pavement Improvement | 2010-03-24 | 2010-05-03 | 2010-08-31 | 2010-06-24 | 300533.64 | 1.150 | E090848
9510 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STATEWIDE |  |  | E090851 | This project provides long term rail improvements to the State of Ohio-owned Panhandle Rail line including the repair and rehabilitation of bridges, rail and a tunnel. | Other | 2010-04-13 | 2010-06-01 | 2010-10-31 | 2011-06-17 | 7349941 |  | E090851
9511 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | STATEWIDE |  |  | E090852 | The project consists of five rail line impediments between Rickenbacker and Sharonville and on-site improvements at the Rickenbacker Terminal that when complete will allow for the movement of double-s | Other | 2010-06-11 | 2010-08-30 | 2012-03-01 |  | 4100000 |  | E090852
9512 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | STATEWIDE |  |  | E090854 | Railroad tie replacement and other related track work to rehabilitate RJ Corman-owned lines in Western Ohio. Overall, the RJC Western Ohio lines generated 4,274 (2005), 4,541 (2006), and 3,648 (2007) | Other | 2009-11-18 | 2009-11-30 | 2010-10-31 | 2012-08-06 | 1300000 |  | E090854
9513 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LICKING | COLUMBUS | 12 | E090856 | The resurfacing of Taylor Rd (TR36) from SR16 north to Havens Corners Rd and the resurfacing of Palmer Road (TR169) from Mink Road west to the Reynoldsburg Corporation. | Pavement Improvement | 2010-03-02 | 2010-06-07 | 2010-11-30 | 2010-08-06 | 421785 | 4.810 | E090856
9514 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FAIRFIELD | COLUMBUS | 07 | E090857 | The resurfacing of sections or various federal aid routes within Fairfield County - Twsp Rd 223 (Wagram Rd) from Taylor Rd north to the county line. County Rd 13 (Baisl-Western Rd) from CR18 east to C | Pavement Improvement | 2010-05-03 | 2010-07-06 | 2010-11-30 | 2010-07-29 | 514815 | 5.620 | E090857
9515 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL |  | 13 | E090859 | The Mahoning Avenue Resurfacing and Lighting Project includes resurfacing the asphalt pavement. The alignment will follow existing and include curb ramp construction in accordance with ADA standards. | Pavement Improvement | 2010-05-17 | 2010-08-24 | 2009-12-31 | 2011-01-10 | 490993.73 | 1.720 | E090859
9516 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E090869 | Planing and resurfacing of 1.78 miles of High Street from Mahoning Ave to Chestnut; incidental curb and walk replacement. | Pavement Improvement | 2010-05-17 | 2010-09-09 | 2010-08-31 | 2010-10-27 | 385300.72 | 0.590 | E090869
9517 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E090870 | Roadway resurfacing and repair on Trumbull Ave from the City of Girard to SR 193. Roadway resurfacing and repair on West Liberty St from Four Mile Run Rd to Salt Springs Rd. Roadway resurfacing and | Pavement Improvement | 2010-05-05 | 2010-05-06 | 2010-09-30 | 2010-08-10 | 423396.36 | 2.430 | E090870
9518 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E090871 | Resurfacing Austintown Warren Road from Burnett East Rd to the City of Warren south corp. limits in Trumbell county. | Pavement Improvement | 2010-05-10 | 2010-06-05 | 2010-07-31 | 2010-08-04 | 229888.96 | 1.170 | E090871
9519 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E090872 | Roadway resurfacing and repair on Carson Salt Springs Rd from railroad to Austintown Warren Rd. Roadway resurfacing and repair on Austintown Warren Rd from Village of Lordstown to Carson Salt Springs | Pavement Improvement | 2010-04-14 | 2010-05-19 | 2010-08-31 | 2010-08-20 | 439857.56 | 2.730 | E090872
9520 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E090875 | This project is in Amberely Village to surface, replace damaged curb, repair pavement distressed areas, repair damaged inlets, install ADA compliant ramps where needed, upgrade existing traffic signal | Pavement Improvement | 2010-04-19 | 2010-06-21 | 2010-10-30 | 2010-11-04 | 870388.51 | 1.490 | E090875
9521 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 08 | E090876 | This project will improve grade crossing safety at railroad crossings in the State of Ohio. This project involves upgrading circuitry and warning devices on six (6) crossings in Montgomery and Warren | Safety/Traffic Management | 2010-02-01 | 2010-03-01 | 2010-12-31 | 2012-04-27 | 1000000 |  | E090876
9522 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | STARK |  | 16 | E090877 | This project will improve safety at railroad crossings and highway intersections in proximity to active rail grade crossing warning devices in the State of Ohio. This project was originally identified | Safety/Traffic Management | 2010-05-10 | 2010-08-01 | 2012-03-01 |  | 2500000 |  | E090877
9523 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 12 | E090879 | In Franklin County, resurfacing and pavement reconstruction of various roadways. Locations include Alum Creek Drive from Big Walnut Creek to Rathmell Road; Cambridge Blvd from Riverside Drive to Arli | Pavement Improvement | 2010-04-13 | 2010-04-21 | 2010-07-31 | 2010-11-15 | 1829848.59 | 11.670 | E090879
9524 | OHIO | Completed | C240,C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E090906 | This project is for the rehabilitation of Northlawn Avenue Bridge in the City of Moraine. | Bridge Improvement | 2010-11-01 | 2010-12-15 | 2011-06-10 | 2011-06-07 | 324000 |  | E090906
9525 | OHIO | Completed | C200 | Highway Infrastructure Investment Grant | OHIO | VAN WERT |  | 05 | E090911 | This project proposes to install lights and gates at 5 railroad crossings in Delphos. These crossings are: S. Pierce St., AAR DOT # 532743U; S. Franklin St., AAR DOT # 532744B; S. Main St., AAR DOT # | Safety/Traffic Management | 2009-09-02 | 2010-06-28 | 2011-01-08 | 2010-09-29 | 778600 |  | E090911
9526 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | PORTAGE |  | 17 | E090927 | This project replaces the Brady Lake Road bridge over the CSX Railroad and Breakneck Creek in Franklin Township, Portage County. | Bridge Replacement | 2009-09-16 | 2010-01-04 | 2009-12-31 | 2011-06-17 | 1124000 | 0.010 | E090927
9527 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LAWRENCE |  | 06 | E090992 | The project will construct access roads to allow for better access handling between Ohio River barges, rail and highway freight and spur the development of the South Point Inter-modal Transfer Facilit | Other | 2010-05-26 | 2011-07-01 | 2010-11-30 | 2012-07-31 | 2388971.38 |  | E090992
9528 | OHIO | Completed | C250,C200 | Highway Infrastructure Investment Grant | OHIO | FAYETTE |  | 07 | E091007 | In Fayette County, pavement repairs and resurfacing of SR 734 beginning at Greene county line and ending at SR 38. Included in this distance is State Street (also known as SR 41 & SR 734) through the Village of Jeffersonville. | Pavement Improvement | 2010-02-11 | 2010-07-19 | 2010-09-30 | 2010-09-30 | 980126.7 | 13.590 | E091007
9529 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | STARK | CANTON | 16 | E091023 | This project will resurface County Route 66 from 12th Street to 50th Street. | Pavement Improvement | 2010-05-10 | 2010-05-17 | 2010-06-30 | 2011-01-26 | 102345.5 | 3.440 | E091023
9530 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | MAHONING |  | 17 | E091027 | This project involves construction of inter-modal facility and new railroad tracks at Brier Hill Industrial Park. | Other | 2011-07-15 | 2011-08-17 | 2012-06-30 |  | 16535100.68 |  | E091027
9531 | OHIO | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | LORAIN | CLEVELAND, OH | 13 | E091030 | To fund a transportation brokerage in Lorain County to receive and redirect requests for work trips to eligible transportation providers | Other | 2010-01-04 | 2010-01-04 | 2012-01-04 |  | 140000 |  | E091030
9532 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 13 | E091052 | This project is in Summit county South Main St. Intersection, Widen North and South approaches. Convert Southbound right turn lane into a through/right lane. Upgrade of signal control. | Other | 2010-06-09 | 2009-10-26 | 2011-09-30 |  | 200000 | 0.020 | E091052
9533 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E091103 | This project takes place at Vine Street from Mitchell Avenue to Elmwood Place South Corp Line. It consists of resurfacing with asphaltic concrete and restriping. | Pavement Improvement | 2010-04-16 | 2010-04-16 | 2010-10-01 | 2010-10-29 | 739162.34 | 2.110 | E091103
9534 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E091106 | From the southern terminus of Hempstead Station Drive, north along Hempstead Station Drive to Stroop Road then east along Stroop to the southwest corner of the Stroop/Wilmington Pike intersection-Cons | Transportation Enhancements | 2009-11-23 | 2009-11-09 | 2009-09-30 | 2010-04-12 | 179792 |  | E091106
9535 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 13 | E091125 | In the city of Green, widen and resuface of Arlington road. Also adding turn lanes, signal coordinate and drainage improvments. This project also includes the realignment of Jarvis Road | Safety/Traffic Management | 2010-03-08 | 2010-04-05 | 2011-09-01 | 2012-08-23 | 2000000 | 1.380 | E091125
9536 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E091126 | This project is a bridge replacement taking place over Penn Central Rail Road. | Bridge Replacement | 2010-06-02 | 2010-06-14 | 2010-08-31 | 2011-06-16 | 350000 | 0.000 | E091126
9537 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E091159 | This project is In the Port of Toledo from Sinclair Ave to John Carey Dr. It is for the reconstruction of a portion of St. Lawrence Drive, and the realignment of a portion of St. Lawrence Drive which | New Construction | 2010-03-29 | 2010-04-13 | 2010-11-26 | 2011-07-07 | 1985975.58 |  | E091159
9538 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E091161 | The project involves the Toledo shipyard. It is to extend an existing Rail Road spur into the shipyard allowing steel and other material supporting shipyard operations to be shipped and delivered via rail and to perform necessary related work. | Other | 2010-04-14 | 2010-04-20 | 2011-12-31 | 2010-07-19 | 131730 |  | E091161
9539 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | LUCAS |  | 09 | E091162 | This project involves the port of Toledo, General Cargo Facility # 1. It is to repair, maintain and enhance the on dock rail capability at the Port's general cargo facility # 1 and to perform necessary related work. | Other | 2010-07-20 | 2010-08-03 | 2011-12-31 | 2011-08-10 | 4385421 |  | E091162
9540 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MEDINA |  | 16 | E091189 | This project will replace the bridge over CSXs railroad tracks at Mud Lake Rd. in Creston, in Medina County. This project is a part of CSX's National Gateway project to allow for double stack clearance. | Pavement Improvement | 2010-12-13 | 2011-04-06 | 2012-03-01 | 2012-11-20 | 1642355.49 |  | E091189
9541 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | SUMMIT |  | 14 | E091190 | The bridge over CSX's railroad tracks at Park Street in Akron, in Summit County, will be removed for this project. This project is a part of CSX's National Gateway project to allow for double stack clearance. | Other | 2010-08-13 | 2010-09-24 | 2012-03-01 | 2011-12-09 | 492623 |  | E091190
9542 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | PORTAGE |  | 17 | E091192 | This project will replace the bridge over CSX's railroad tracks at Rock Spring Road in Newton Falls, located in Portage County. This project is a part of CSX's National Gateway project to allow for double stack clearance. | Bridge Replacement | 2010-08-22 | 2010-09-24 | 2012-03-01 |  | 5027898 | 0.000 | E091192
9543 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL |  | 14 | E091193 | The 5th Street bridge in Niles, over CSX's railroad tracks through Trumbull County, will be replaced for this project. This project is a part of CSX's National Gateway project to allow for double stack clearance. | Other | 2010-12-16 | 2011-03-01 | 2012-03-01 | 2012-05-21 | 2255300 |  | E091193
9544 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E091204 | National Road in Vandalia from I-75 to just east of Brown School Road-Remove and replace trees, add decorative tree grates, decorative lights, replace sidewalk, pavers, drive aprons an upgrade bus stops with street furniture. | Transportation Enhancements | 2010-05-20 | 2010-05-25 | 2010-10-29 | 2010-11-19 | 921971.14 | 0.330 | E091204
9545 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 11 | E091217 | This project is in Cleveland from Prospect Avenue to Euclic Avenue. It involves East 14th Street Streetscape: Sidewalks, paving, trees, plants and benches. | Transportation Enhancements | 2010-06-11 | 2010-04-20 | 2010-10-30 | 2011-03-18 | 1923151.12 | 0.280 | E091217
9546 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY |  | 03 | E091251 | In Montgomery county, widen Byers Road from 2 to 5 lanes and Relocate To The West To Form A Four-Leg Intersection With The Northern Most Section of Wood Rd. | Pavement Widening | 2010-06-16 | 2010-05-26 | 2011-06-30 | 2011-12-28 | 4000000 | 2.000 | E091251
9547 | OHIO | Underway | C230 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA | CLEVELAND, OH | 10 | E091267 | The project consists of reconstructing approximately 2.44 miles of Bainbridge Road within the City of Solon. The work includes a new flexible pavement, integral bike lanes, and a new curb. | Pavement Improvement | 2010-01-21 | 2010-04-05 | 2011-09-30 |  | 12606660.97 | 2.460 | E091267
9548 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E091291 | This project will resurface and rehab Girard-I80/SR11 to Girard south corp. limit. It will include planing the entire roadway, repairing and widening sub-standard lane widths, pavement marking applic | Pavement Improvement | 2010-01-14 | 2010-03-30 | 2010-12-31 | 2010-11-10 | 800000 | 1.320 | E091291
9549 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E091335 | This project is to resurface Mahoning Ave from SR45 east to Lipkey Road. | Pavement Improvement | 2010-06-08 | 2010-05-10 | 2010-09-30 | 2010-08-02 | 516920.53 | 1.770 | E091335
9550 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E091336 | This project is to resurface Tibbets Wick from US422 east to SR 11. | Pavement Improvement | 2010-06-11 | 2010-06-26 | 2010-09-30 | 2010-08-10 | 299892.19 | 1.350 | E091336
9551 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MAHONING | YOUNGSTOWN-WARREN | 17 | E100023 | This project is to resurface Glenwood Avenue from Falls Avenue to Mahoning Avenue . | Pavement Improvement | 2010-10-22 | 2010-09-16 | 2010-11-15 | 2010-10-15 | 322202.67 | 0.740 | E100023
9552 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | DELAWARE |  | 12 | E100027 | This project is the construction of a grade separation with the CSX Railroad. | New Construction | 2010-05-03 | 2010-05-03 | 2011-09-30 | 2011-09-12 | 7214696.7 | 0.340 | E100027
9553 | OHIO | Completed | C240,C950 | Highway Infrastructure Investment Grant | OHIO | OTTAWA |  | 05 | E100048 | This project is a Ferry Boat Stimulus (ARRA) funded project to repair deteriorating commercial dock and to replace passenger and freight terminal building. | Other | 2010-08-19 | 2010-08-23 | 2010-10-31 | 2011-08-29 | 870000 |  | E100048
9554 | OHIO | Completed | C220,C200 | Highway Infrastructure Investment Grant | OHIO | CLARK |  | 07 | E100102 | This project includes streetscape and resurfacing Fountain Street from the bridge over Buck Creek to McCreight Ave. | Transportation Enhancements | 2010-05-25 | 2010-05-17 | 2010-09-11 | 2010-11-29 | 789552.21 | 0.620 | E100102
9555 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | PORTAGE |  | 13 | E100106 | This project will involve railroad improvements and rehabilitation at milepost 120 and 103.95 on National Gateway in Kent Ohio. | Other | 2010-07-30 | 2011-04-04 | 2011-06-30 |  | 8790235 |  | E100106
9556 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | FULTON |  | 09 | E100110 | This project is a Tier 1 Railroad Grade Separation project for Hallett Ave/Norfolk Southern in the Village of Swanton with offset alignment. | Safety/Traffic Management | 2010-05-18 | 2010-08-23 | 2011-11-01 |  | 7900000 | 0.000 | E100110
9557 | OHIO | Completed | C200,C240 | Highway Infrastructure Investment Grant | OHIO | SENECA |  | 05 | E100111 | This project is a Tier 1 Railroad Grade Separation and the construction of Jones Rd / CSX RR in the city of Fostoria. | Other | 2010-05-05 | 2010-06-23 | 2011-11-30 | 2011-11-15 | 1084158.99 | 0.050 | E100111
9558 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | HAMILTON |  | 02 | E100123 | This project is Phase 2 of the Hamilton Interstate 75 corridor improvement project. The scope of this project includes replacing the Monmouth Street overpass, and converting the roadway to a through s | Bridge Replacement | 2010-02-25 | 2010-03-11 | 2011-10-18 | 2011-09-30 | 7192394.16 | 0.000 | E100123
9559 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E100141 | This project is to construction a 6 leg roundabout including sight distance to the Northeast Avenue approach in Tallmage. This is the intersection of Howe Road/Northeast Avenue/Munroe Road | Pavement Improvement | 2010-03-16 | 2010-04-12 | 2010-05-03 | 2011-03-02 | 268800 | 0.100 | E100141
9560 | OHIO | Completed | C240 | Highway Infrastructure Investment Grant | OHIO | UNION |  | 07 | E100220 | The project will replace the 1913 bridge with a modern covered bridge bringing tourism to the country which will be highlighted at the County?s Annual Covered Bridge Festival. | Bridge Replacement | 2010-04-08 | 2010-04-17 | 2010-12-31 | 2010-11-15 | 377000 | 0.010 | E100220
9561 | OHIO | Underway | C220,C240 | Highway Infrastructure Investment Grant | OHIO | CUYAHOGA |  | 11 | E100247 | The Cleveland Innerbelt Modernization Plan is focused on improving safety, reducing congestion and traffic delays, and modernizing interstate travel along I-71, I-77 and I-90 through Downtown Clevelan | Bridge Replacement | 2010-09-17 | 2011-02-01 | 2014-06-30 |  | 79700793.43 | 2.000 | E100247
9562 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MONTGOMERY | DAYTON | 03 | E100295 | This project is intended to preserve roadway in the City of Kettering. It will include replacing pavement and installation of tree lawns with trees and new sidewalks. It will also include updating | Pavement Improvement | 2010-04-13 | 2010-05-03 | 2010-11-30 | 2011-12-21 | 1345519.34 | 0.100 | E100295
9563 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | WOOD | TOLEDO (MI) | 05 | E100300 | This is a TMACOG ARRA stimulus funded project to resurface East Poe Rd, in the City of Bowling Green, from Tarragon Dr to Dunbridge Rd, a distance of about 1.12 mile; perform full depth repairs where needed; perform necessary related work. | Pavement Improvement | 2011-04-11 | 2011-05-17 | 2011-07-22 | 2011-07-22 | 750198.52 | 1.530 | E100300
9564 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E100306 | This is Project 1 of Alum Creek/Groveport Rd upgrade to widen Alum Creek from N of Rathmel Rd to I-270. | Pavement Improvement | 2010-09-23 | 2010-08-30 | 2010-11-30 | 2012-03-30 | 1207809 | 0.490 | E100306
9565 | OHIO | Completed | C220,C230 | Highway Infrastructure Investment Grant | OHIO | GREENE | DAYTON | 07 | E100356 | This project is for Streetscape including trees, shrubs, and breakaway poles for flags. | Transportation Enhancements | 2010-09-13 | 2010-10-08 | 2010-12-31 | 2011-11-09 | 282044 | 0.330 | E100356
9566 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E100403 | This project is to resurface Sharon Road in Warren County From SR7 to Yankee Run Road (1.88 miles). | Pavement Improvement | 2010-10-12 | 2010-10-14 | 2010-11-15 | 2010-11-03 | 441662.14 | 1.560 | E100403
9567 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | BUTLER | CINCINNATI (KY) | 08 | E100432 | This project is to conduct environmental analysis for proposed widening of SR 4 bypass from two lanes to 4 lanes , with turn lanes as required, and proposed Bobmeyer Road extension from Airport to SR | Pavement Widening | 2010-07-07 | 2010-07-14 | 2011-09-30 | 2011-10-21 | 1702293 | 0.860 | E100432
9568 | OHIO | Underway | C490 | OJT/SS | OHIO | STATEWIDE |  |  | E100459 | This project is for the OJT/SS Program through FY 2010 and will be used to provide construction career/job fairs, tools, work boots, clothing, medical examinations/drug testing and seminars/training t | Other | 2012-01-01 | 2012-01-01 | 2012-12-31 |  | 318416 |  | E100459
9569 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | SUMMIT | AKRON | 14 | E100467 | This project is the Summit County Hilbish Avenue Bridge replacement over Springfield Lake outlet. | Bridge Replacement | 2010-12-15 | 2011-06-15 | 2011-07-15 | 2011-08-26 | 132166.31 | 0.010 | E100467
9570 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | AUGLAIZE |  | 08 | E100538 | This project is for resurfacing the intersection of SR66 and SR119 in Auglaize County. | Transportation Enhancements | 2011-05-12 | 2011-04-18 | 2012-09-30 | 2012-10-12 | 1200000 | 0.070 | E100538
9571 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | LUCAS | TOLEDO (MI) | 09 | E100539 | This project is to upgrade sign reflectivity through the replacement of overhead-mounted lane-control and street name signs in the City of Toledo. | Other | 2011-02-17 | 2011-05-12 | 2011-10-01 | 2011-07-05 | 183155.79 | 0.010 | E100539
9572 | OHIO | Completed | C220 | Highway Infrastructure Investment Grant | OHIO | DEFIANCE |  | 05 | E100605 | This project includes decorative lighting, streetscape furniture, replacing trees in Treelawn, and replacing deteriorated bricks and sidewalks. | Transportation Enhancements | 2010-11-19 | 2010-11-29 | 2011-05-01 | 2011-07-29 | 986964 |  | E100605
9573 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | MIAMI | DAYTON | 08 | E100657 | This project is for resurfacing on Washington Avenue in Miami County. | Pavement Improvement | 2010-10-05 | 2010-10-08 | 2010-11-30 | 2010-12-13 | 194045.41 | 1.140 | E100657
9574 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 02 | E100796 | This is a streetscape project that will include gateway signage, medians being constructed, and landscaping. | Transportation Enhancements | 2011-05-05 | 2011-06-14 | 2011-10-14 | 2011-10-14 | 464818.22 |  | E100796
9575 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 13 | E100809 | Analyzing existing bridge structures to determine their current load carrying capacity and entering the results of this load rating analysis into the statewide bridge inventory database. | Other | 2011-03-23 | 2011-03-23 | 2013-03-23 | 2012-06-14 | 100000 |  | E100809
9576 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | TRUMBULL | YOUNGSTOWN-WARREN | 14 | E100810 | Analyzing existing bridge structures to determine their current load carrying capacity and entering the results of this load rating analysis into the statewide bridge inventory database. | Other | 2011-03-23 | 2011-03-23 | 2013-03-23 | 2012-02-22 | 123746.8 |  | E100810
9577 | OHIO | Underway | C240,C230 | Highway Infrastructure Investment Grant | OHIO | HAMILTON | CINCINNATI (KY) | 01 | E101007 | This project is to replace the superstructure and widen as necessary. | Bridge Improvement | 2010-12-10 | 2010-12-15 | 2012-07-31 |  | 6407444.02 |  | E101007
9578 | OHIO | Completed | C230 | Highway Infrastructure Investment Grant | OHIO | FRANKLIN | COLUMBUS | 15 | E101027 | This project is for the reconstruction of the existing road including adding 2 to 3 lanes, street lighting, and a sidewalk. | Pavement Widening | 2011-02-28 | 2011-03-28 | 2012-09-30 | 2012-05-31 | 1269286.33 |  | E101027
9579 | OHIO | Underway | C240 | Highway Infrastructure Investment Grant | OHIO | ASHTABULA |  | 14 | E101110 | This project is to replace the pavement on Interstate Route 90 in Ashtabula County. It also includes bridge work. | Pavement Improvement | 2011-01-31 | 2011-03-25 | 2013-08-29 |  | 28760000 |  | E101110
9580 | OKLAHOMA | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM001 | Resurface 6.50 miles of concrete pavement on east and westbound I-40 from MP 281.67 to MP 288.22 and replace the east and westbound Dirty Creek bridges. | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2011-01-21 |  | 27178471 | 6.550 | STIM001
9581 | OKLAHOMA | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LE FLORE |  | 02 | STIM008 | Roadway construction of the remaining 2 lanes of a 4 lane facility from SH-9A extending east to SH-112 to add capacity for an existing two lane facility and replace structurally obsolete and/or defient bridges. | Bridge Replacement | 2009-09-14 | 2009-12-01 | 2010-09-13 |  | 5968238 | 1.800 | STIM008
9582 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ATOKA |  | 02 | STIM009 | Roadway and Bridge construction of a new 2 lane facility offset to an existing 2 lane facility from 0.33 miles West of the Atoka and Pushmataha County Line extending East into Atoka County 1.82 miles.. | Pavement Widening | 2009-04-27 | 2009-04-27 | 2009-11-22 | 2010-08-13 | 3818000 | 1.820 | STIM009
9583 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | GARVIN |  | 04 | STIM010 | This project will extend the life of the pavement and significantly improves ride quality on 6.57 miles of I-35 by stabalizing the existing pavement. Project begins at SH-29 and extends to SH-19. | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2010-11-27 | 2010-09-30 | 24530000 | 6.570 | STIM010
9584 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | SEMINOLE |  | 05 | STIM011 | Full depth concrete pavement reconstruction for 2.47 miles on I-40 in Seminole County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-13 | 2009-07-07 | 2010-01-28 | 2010-01-27 | 3030000 | 2.470 | STIM011
9585 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCLAIN |  | 04 | STIM013 | Asphalt pavement resurfacing and bridge repair on I-44 in McClain County. This project was resurfaced within existing right of ways and no lanes were added. | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-09-23 | 2009-07-10 | 6760000 | 7.500 | STIM013
9586 | OKLAHOMA | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM015 | "This project overlays the existing concrete pavement with a concrete overlay. Also, 2 additional lanes are being added injunction with reconstructing the existing bridges The project starts at Mile Marker 125 and extends to Mile Marker 136 on I-40. " | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2011-08-09 |  | 30000000 | 4.000 | STIM015
9587 | OKLAHOMA | Underway | C200,C240 | Highway Infrastructure Investment Grant | OKLAHOMA | KAY |  | 03 | STIM019 | This project reconstructs the pavement surfacing upgrades the bridges and installs cable barrier in the median. The project starts at Mile Marker 224.4 and extends to Mile Marker 229.3 on I-35. | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2011-03-02 |  | 21586000 | 4.900 | STIM019
9588 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | BECKHAM |  | 03 | STIM024 | "This project replaces deteriorated bridge decks and improves deteriorated pavement for eight miles of I-40 near Sayre, OK. " | Pavement Improvement | 2009-04-27 | 2009-05-01 | 2010-01-21 | 2009-11-11 | 13379000 | 8.000 | STIM024
9589 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM028 | This project seals cracks and overlays the existing asphalt pavement. The project starts at Guymon and extends east 7.0 miles on US- 412 | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-09-23 | 2010-05-11 | 6249000 | 7.300 | STIM028
9590 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CIMARRON |  | 03 | STIM031 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at 7.5 miles east of Jct. with US-287 on US-64 and extends 14.5 miles east. | Pavement Improvement | 2009-06-09 | 2009-07-28 |  | 2009-11-13 | 6539700 | 8.000 | STIM031
9591 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM033 | This project crack seals and overlays the existing asphalt pavement. The project starts at the Texas/Cimarron County Line and extends east 4.5 miles on US-64 north of Guymon. | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-09-03 | 2009-09-16 | 3567000 | 4.500 | STIM033
9592 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ELLIS |  | 03 | STIM034 | This project installs a new bridge on US -283 over 25 mile creek 0.5 miles north of the Jct with State Highway 15 | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-11-22 | 2009-12-01 | 3464300 | 0.750 | STIM034
9593 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | COMANCHE |  | 04 | STIM037 | "This project replaces the deficient bridge over Beaver Creek for the west bound lanes of State Highway 7 west of Lawton, OK. " | Bridge Replacement | 2009-04-27 | 2009-05-06 | 2009-12-02 | 2009-10-02 | 2241000 | 0.381 | STIM037
9594 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CARTER |  | 04 | STIM038 | "This project replaces a deficient bridge over Red Oak Creek on US 70 west of Ardmore, OK. " | Bridge Replacement | 2009-04-27 | 2009-04-27 | 2009-12-22 | 2010-05-22 | 1272000 | 0.250 | STIM038
9595 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | STEPHENS |  | 04 | STIM039 | "This project constructs a new interchange at US 81 and Bois D'Arc Avenue in Duncan, OK to provide four lanes of Bois D'Arc Avenue at this location. " | Pavement Widening | 2009-06-01 | 2009-06-01 | 2010-02-25 | 2010-04-06 | 4954000 | 0.440 | STIM039
9596 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CARTER |  | 04 | STIM040 | "This project widens about 3 miles of US 70 from two lanes to four lanes east of the Jefferson County line west of Ardmore, OK. " | Pavement Improvement | 2009-04-27 | 2009-04-27 | 2009-12-22 | 2010-05-22 | 5344000 | 3.080 | STIM040
9597 | OKLAHOMA | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM047 | "This project is located on the north bound lanes of Interstate 244 beginning at the U.S. Highway 75 interchange extending north to the U.S. Highway 64 interchange (also referred to as the west leg of | Bridge Improvement | 2009-06-08 | 2009-06-08 | 2011-01-08 |  | 10750000 | 1.176 | STIM047
9598 | OKLAHOMA | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM048 | "This project is located on the south bound lanes of Interstate 244 beginning at the U.S. Highway 75 interchange extending north to the U.S. Highway 64 interchange (also referred to as the west leg of | Bridge Improvement | 2009-06-08 | 2009-06-08 | 2011-01-08 |  | 20616000 | 1.124 | STIM048
9599 | OKLAHOMA | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM049 | "This project is located on the east bound lanes of Interstate 244 beginning at the U.S. Highway 64 interchange extending east to the U.S. Highway 75 interchange (also referred to as the north leg of | Bridge Improvement | 2009-06-08 | 2009-06-08 | 2011-01-08 |  | 14900000 | 1.754 | STIM049
9600 | OKLAHOMA | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM050 | "This project is located on the west bound lanes of Interstate 244 beginning at the U.S. Highway 64 interchange extending east to the U.S. Highway 75 interchange (also referred to as the north leg of | Bridge Improvement | 2009-06-08 | 2009-06-08 | 2011-01-08 |  | 17200000 | 1.751 | STIM050
9601 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA |  | 01 | STIM061 | "This project will replace the pavement approaching the State Highway 151 bridges over State Highway 51 and SL/SF railroad, replace the both deteriorated bridges and install new safety barriers. The | Bridge Replacement | 2009-06-01 | 2009-05-27 | 2010-03-27 | 2009-11-22 | 6059000 | 0.250 | STIM061
9602 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | NOWATA |  | 02 | STIM062 | "This project will resurface 6.0 mile of U.S. Highway 169 beginning at the Kansas State Line by replacing 2 to 4 inches of existing asphalt with 4 inches of new asphalt which results in a smoother rid | Pavement Widening | 2009-07-06 | 2009-07-23 | 2009-09-03 | 2009-09-17 | 3535000 | 6.000 | STIM062
9603 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | WOODS |  | 03 | STIM063 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 4.5 miles north of the Woods/Major County Line on US-281 and entends south 3.7 miles | Pavement Improvement | 2009-07-06 | 2009-04-29 | 2009-08-24 | 2009-05-18 | 706900 | 3.700 | STIM063
9604 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM064 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 5.3 miles southwest of the Junction with State Highway 94 on State Highway 54 and entends northeast 5.0 miles. | Pavement Improvement | 2009-07-22 | 2009-10-01 |  | 2009-10-28 | 1090729 | 5.000 | STIM064
9605 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM065 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 9.8 miles northeast of the Texas State line on US 54 miles entends 1.6 miles to the Goodwell City limits | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-03 | 2009-10-29 | 792900 | 1.600 | STIM065
9606 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM066 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 11.4 miles northeast of the Texas State line on US 54 miles entends 7.0 miles. | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-03 | 2009-10-29 | 1409500 | 7.000 | STIM066
9607 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | WOODS |  | 03 | STIM067 | This project resurfaces the existing asphalt pavement with an asphalt overlay. The project begins 4.6 miles east of the Jct US-281 on State Highway 45 and entends east 3.5 miles. | Pavement Improvement | 2009-07-06 | 2009-04-29 | 2009-08-24 | 2009-05-18 | 598700 | 3.500 | STIM067
9608 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CUSTER |  | 03 | STIM069 | "This project resurfaces about 6 miles of US 183 north of Clinton, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-24 | 2009-08-28 |  | 2009-09-30 | 1197383 | 5.960 | STIM069
9609 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CUSTER |  | 03 | STIM070 | "This project resurfaces about 5 miles of US 183 north of Clinton, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-24 | 2009-08-28 |  | 2009-09-30 | 938475 | 4.660 | STIM070
9610 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | JACKSON |  | 04 | STIM071 | "This project resurfaces about 8 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2009-09-08 | 2009-08-19 | 997900 | 7.700 | STIM071
9611 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TILLMAN |  | 03 | STIM086 | "This project resurfaces about 4 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2009-09-08 | 2009-08-19 | 795600 | 3.920 | STIM086
9612 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TILLMAN |  | 03 | STIM087 | "This project resurfaces about 7 miles of the west bound lanes of US 62 east of Altus, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-01 | 2009-06-01 | 2009-09-08 | 2009-08-19 | 1463000 | 7.130 | STIM087
9613 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ROGERS |  | 02 | STIM088 | This project extends the service life of the pavement by removing 2 inches of asphalt and placing 2 inches of new asphalt on U.S. Highway 412 beginning at the McClelan Kerr Navigation Channel extending east 5.02 miles | Pavement Improvement | 2009-07-06 | 2009-07-30 | 2009-10-03 | 2009-09-29 | 1452092.1 | 5.020 | STIM088
9614 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OKFUSKEE |  | 02 | STIM093 | This project resurfaces about 8 miles of I-40 east of the Seminole County line to improve the smoothness of the road and to extend it's life. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-06-09 | 2009-08-31 |  | 2009-12-04 | 3380000 | 8.000 | STIM093
9615 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | POTTAWATOMIE |  | 05 | STIM095 | Asphalt pavement resurfacing for 7.72 miles on I-40 in Seminole County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-06 | 2009-05-18 | 2009-08-19 | 2009-08-06 | 1296700 | 7.720 | STIM095
9616 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | SEMINOLE |  | 05 | STIM096 | Resurface I-40 from the Pottawatomie county line going east about 6.5 miles. | Pavement Improvement | 2009-07-06 | 2009-05-18 | 2009-08-19 | 2009-08-06 | 1086200 | 6.460 | STIM096
9617 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MURRAY |  | 04 | STIM120 | This project resurfaces about 7 miles of I-35 north of the Carter County line to improve the smoothness of the road and to extend it's life. | Pavement Improvement | 2009-04-27 | 2009-05-26 | 2009-07-20 | 2009-10-01 | 4927000 | 6.560 | STIM120
9618 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CARTER |  | 04 | STIM121 | "This project resurfaces about 8 miles of US 70 east of Ardmore, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-06-09 | 2009-11-09 |  | 2010-06-17 | 2915633 | 8.000 | STIM121
9619 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ATOKA |  | 02 | STIM150 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 1.44 miles to 3.80 miles North of State Highway to repair deteriorating pavement section. | Pavement Improvement | 2009-04-20 | 2009-04-21 | 2009-10-16 | 2009-08-27 | 696712.16 | 3.800 | STIM150
9620 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | BRYAN |  | 02 | STIM152 | Asphalt pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.21 miles to 5.26 miles North of Oklahoma-Texas State Line for Southbound and Northbound Lanes to repair deteriorating pavement section. | Pavement Improvement | 2009-07-06 | 2009-07-22 | 2009-09-18 | 2010-05-26 | 3935957.84 | 5.260 | STIM152
9621 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM153 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at Mile Marker 108 and entends to Mile Marker 115 on I-40 west of Oklahoma city | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-18 | 2009-09-24 | 1716300 | 7.000 | STIM153
9622 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM154 | This project resurfaces the existing asphalt pavement with an asphlat overlay The project starts at Mile Marker 115 and entends to Mile Marker 118 on I-40 west of Oklahoma city | Pavement Improvement | 2009-07-06 | 2009-07-06 | 2009-09-18 | 2009-09-24 | 922650 | 4.200 | STIM154
9623 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | GARVIN |  | 04 | STIM156 | Asphalt pavement resurfacing for 8.01 miles on State Highway 76 in Garvin County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-06 | 2009-05-29 | 2009-08-09 | 2009-07-08 | 1128800 | 8.010 | STIM156
9624 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | HASKELL |  | 02 | STIM157 | "13.85 miles of 9.5"" thick of concrete patching and concrete surface smoothing at varies locations in Haskell county. These project were reconstructed within existing right of ways and no lanes were added. " | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 201830.67 | 1.070 | STIM157
9625 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM158 | Concrete pavement reconstrcution of the driving lanes and shoulder along SH-2 beginning 14 miles north of Haskell County line and going north approximately 2 miles. | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 460649.1 | 1.750 | STIM158
9626 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OKMULGEE |  | 02 | STIM159 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-75 beginning at I-40 and going north approximately 2.5 miles. | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 857500 | 2.440 | STIM159
9627 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER |  | 01 | STIM163 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-69 beginning 0.5 miles north of SH-51 and going north approximately 8 miles. | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 1770370.23 | 7.840 | STIM163
9628 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER |  | 01 | STIM164 | Concrete pavement reconstrcution of the driving lanes and shoulder along US-69 beginning 1/4 miles south of SH-51 and going north approximately 1 mile. | Pavement Improvement | 2009-04-27 | 2009-05-04 | 2009-11-22 | 2009-11-20 | 393800 | 0.750 | STIM164
9629 | OKLAHOMA | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LE FLORE |  | 02 | STIM169 | "Roadway and Bridge Construction of driving lanes and shoulder on an offset alignment of along US Highway 59 from State Highway West to 5.26 miles North of Junction to increase the capacity and update | Pavement Widening | 2009-09-08 | 2009-07-06 | 2010-11-01 |  | 12000000 | 5.000 | STIM169
9630 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | HUGHES |  | 02 | STIM172 | Asphalt pavement resurfacing for 1.96 miles on U.S. Highway 270B in Hughes County. Part of this project include full depth concrete patching. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-06 | 2009-06-16 | 2009-08-04 | 2009-09-02 | 387000 | 1.960 | STIM172
9631 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM173 | "This project resurfaces about 8 miles of SH-105 in Lincoln County, OK between US-177 and SH-18 to improve the smoothness of the road and to extend it's life. This project was reconstructed within existing right of ways and no lanes were added." | Pavement Improvement | 2009-07-06 | 2009-07-02 | 2009-08-04 | 2009-09-22 | 985000 | 7.970 | STIM173
9632 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM174 | Asphalt pavement resurfacing for 5.05 miles on State. Highway 18 in Lincoln County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-06 | 2009-07-13 | 2009-08-04 | 2009-09-04 | 487000 | 5.050 | STIM174
9633 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MAYES |  | 02 | STIM175 | "This project will provide a smother ride and extend the service life of the pavement by rehabilitating the existing concrete pavement. Improvements include patching deteriorated sections, adding sup | Pavement Improvement | 2009-06-01 | 2009-07-28 | 2009-09-28 | 2009-09-30 | 1871300 | 4.500 | STIM175
9634 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | NOBLE |  | 03 | STIM176 | Resurface both directions of I-35 starting about 1 mile north of the Payne county line and going north 6 miles. | Pavement Improvement | 2009-07-06 | 2009-07-17 | 2009-08-19 | 2009-09-03 | 1255000 | 6.000 | STIM176
9635 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM177 | This project will extend the life of the pavement and significantly improves ride quality on 3.5 miles of I-235 in Oklahoma City by stabalizing the existing pavement. | Pavement Improvement | 2009-04-27 | 2009-05-18 | 2009-07-25 | 2009-08-17 | 2538647.59 | 3.470 | STIM177
9636 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | PITTSBURG |  | 02 | STIM178 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.00 miles to 3.0 miles North of County Line for Southbound and Northbound Lanes to repair deteriorating pavement section. | Pavement Improvement | 2009-04-20 | 2009-04-21 | 2009-10-16 | 2009-08-27 | 1571640 | 3.000 | STIM178
9637 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | PITTSBURG |  | 02 | STIM179 | Concrete pavement reconstrcution of the driving lanes and shoulder along US Highway 69 from 0.30 miles to 4.65 miles North of Atoka County Line for Southbound Lanes and from 3.08 miles to 6.0 miles No | Pavement Improvement | 2009-04-20 | 2009-04-21 | 2009-10-16 | 2009-08-27 | 2121700 | 4.650 | STIM179
9638 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | ROGERS |  | 02 | STIM180 | This project extends the service life of the pavement by removing 2 inches of asphalt and placing 3 inches of new asphalt on State Highway 266 beginning at State Highway 167 extending east approximately 6.0 miles. | Pavement Improvement | 2009-07-06 | 2009-07-30 | 2009-10-03 | 2009-09-29 | 934507.9 | 6.000 | STIM180
9639 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | SEMINOLE |  | 05 | STIM181 | Asphalt pavement resurfacing for 4.76 miles on State Highway 56 in Seminole County. Part of this project include full depth concrete patching. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-07-06 | 2009-06-30 | 2009-09-03 | 2010-02-19 | 935000 | 4.760 | STIM181
9640 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | TILLMAN |  | 04 | STIM182 | "This project resurfaces about 4 miles of US 183 south of Frederick, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-07-06 | 2009-07-09 | 2009-08-04 | 2009-07-28 | 713900 | 4.050 | STIM182
9641 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | MAYES |  | 02 | STIM183 | This project will replace a deteriorated county bridge on EW-58 over Chouteau Creek located approximately 0.3 mile south and 2.3 miles east of Chouteau. | Bridge Replacement | 2009-09-08 | 2009-09-29 | 2010-03-06 | 2010-04-16 | 968697 | 0.060 | STIM183
9642 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | MAYES |  | 02 | STIM184 | This project replaces a deteriorated bridge over Brushy Creek located approximately 2.2 miles south and 2.5 miles west of the U.S. Highway 412/69 junction. | Bridge Replacement | 2009-09-08 | 2009-10-05 | 2010-01-05 | 2010-05-05 | 289172 | 0.020 | STIM184
9643 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA |  | 01 | STIM185 | This project replaces a deteriorated county bridge over Delaware Creek overflow on Cincinnati Avenue located 0.5 mile south of 86th Street North in Tulsa. | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2010-01-29 | 2010-06-23 | 940731 | 0.400 | STIM185
9644 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | WASHINGTON |  | 01 | STIM186 | This project will replace a low water crossing on N-401 over Unnamed Creek located 0.6 miles south and 4.2 miles east of the U.S. Highway 75/ Kansas Border junction. | Bridge Replacement | 2009-08-03 | 2009-07-24 | 2010-03-30 | 2010-11-05 | 616000 | 0.020 | STIM186
9645 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | WASHINGTON |  | 01 | STIM187 | This project will replace a low water crossing with a new bridge on N-400 over Brush Creek located approximately 0.8 mile south and 2.0 miles east of the U.S. Highway / State Highway 10 junction. | New Bridge Construction | 2009-08-03 | 2009-07-24 | 2010-03-30 | 2010-11-05 | 471400 | 0.200 | STIM187
9646 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | ADAIR |  | 02 | STIM188 | Construct a new bridge on Peavine Road about 4 miles north of junction US-59/SH-51. Additional right of way was acquired to construct this project. | New Bridge Construction | 2009-09-08 | 2009-09-08 | 2010-01-25 | 2010-04-23 | 584000 | 0.250 | STIM188
9647 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | CHEROKEE |  | 02 | STIM189 | Replace the bridge over the Telmay Hollow creek in Cherokee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-08-03 | 2009-07-27 | 2009-10-31 | 2009-12-21 | 288000 | 0.230 | STIM189
9648 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | MCINTOSH |  | 02 | STIM190 | Replace the bridge over the Flat Rock creek creek in McIntosh county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-09-08 | 2009-08-10 | 2009-12-06 | 2009-12-16 | 335000 | 0.250 | STIM190
9649 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM191 | Replace the bridge over Cloud creek north and east of Boyton in Muskogee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-11-30 | 2009-11-30 | 2010-04-28 | 2010-08-21 | 418449 | 0.365 | STIM191
9650 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | OKMULGEE |  | 02 | STIM192 | Replace the bridge over the unnamed creek creek that is about 4 miles east and 2 miles north of US-75 in Okmulgee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-09-08 | 2009-07-13 | 2010-01-05 | 2009-12-18 | 320000 | 0.200 | STIM192
9651 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | SEQUOYAH |  | 02 | STIM193 | Construct a new bridge over the Prairie Creek just south and west of Akins in Sequoyah county. Additional right of way was acquired to construct this project. | New Bridge Construction | 2009-12-07 | 2009-09-08 | 2010-04-05 | 2010-04-28 | 300000 | 0.250 | STIM193
9652 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER |  | 01 | STIM194 | Replace the bridge 1 mile north and 4 miles west of the junction of US-69 and SH-51 in Wagoner county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-08-03 | 2009-07-22 | 2009-10-31 | 2009-10-28 | 220000 | 0.125 | STIM194
9653 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | BRYAN |  | 02 | STIM195 | County Bridge Constrcution of the driving lanes and shoulders over Island Bayou and Island Bayou Tributaries located 2.60 miles North of State Highway 78 on NS 380 Section Line Road to replace a struc | Bridge Replacement | 2009-08-03 | 2009-08-17 | 2009-11-30 | 2010-05-04 | 558000 | 0.400 | STIM195
9654 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | BRYAN |  | 02 | STIM196 | County Bridge Constrcution of the driving lanes and shoulders over Red Ranch Creek located 1.00 miles North and 1.50 miles East of the Town of Smith-Lee to replace a strucutrally defecient or obsolete local government bridge (off system). | Bridge Replacement | 2009-08-03 | 2009-08-17 | 2009-11-30 | 2010-05-04 | 381000 | 0.300 | STIM196
9655 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | LATIMER |  | 02 | STIM197 | County Bridge Constrcution of the driving lanes and shoulders over Peachland Creek located 0.70 miles North and 2.00 miles West of the Town of Bengal to replace a strucutrally defecient or obsolete local government bridge (off system). | Bridge Replacement | 2009-08-03 | 2009-08-14 | 2009-11-30 | 2010-01-20 | 535000 | 0.200 | STIM197
9656 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | LE FLORE |  | 02 | STIM198 | County Bridge Constrcution of the driving lanes and shoulders over Fourche Maline Creek located 1.50 miles North and 2.30 miles East of the Town of LeFLore to replace a strucutrally defecient or obsolete local government bridge (off system). | Bridge Replacement | 2009-10-05 | 2009-06-10 | 2010-03-03 | 2010-01-27 | 1000376.12 | 0.500 | STIM198
9657 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | PITTSBURG |  | 02 | STIM199 | County Bridge Constrcution of the driving lanes and shoulders over Unnamed Creek located 2.00 miles North and 3.70 miles West of the Town of Quinton to replace a strucutrally defecient or obsolete local government bridge (off system). | Bridge Replacement | 2009-10-05 | 2009-06-25 | 2010-02-01 | 2010-01-19 | 329623.88 | 0.300 | STIM199
9658 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | COAL |  | 02 | STIM200 | Replace the bridge over Coal Creek thats about 2 miles east and 2 miles south of Lehigh | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2010-01-29 | 2010-08-06 | 295400 | 0.200 | STIM200
9659 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | COAL |  | 02 | STIM201 | Replace the bridge over the tributary to Keel Creek that is about 8 miles north and 7 miles east of Coalgate. | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2010-01-29 | 2010-08-06 | 162000 | 0.200 | STIM201
9660 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | HUGHES |  | 02 | STIM202 | Replace the bridge over the Big creek that is about 4 miles east of Allen in Hughes county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-09-08 | 2009-08-17 | 2010-01-05 | 2010-05-05 | 429292 | 0.300 | STIM202
9661 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM203 | Replace the bridge over the Spring creek about a mile west of US-177 junction SH-66 in Lincoln county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2009-11-30 | 2009-12-18 | 259200 | 0.300 | STIM203
9662 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | OKFUSKEE |  | 02 | STIM204 | Replace the bridge over the Harrican creek that is about 3 miles south of Micawber in Okfuskee county. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-08-03 | 2009-06-05 | 2009-11-30 | 2009-09-14 | 421400 | 0.240 | STIM204
9663 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | PONTOTOC |  | 04 | STIM205 | Replace the bridge over the Grayson Creek that is about 2 miles south and 7 miles east of SH-59a junction SH-3w. | Bridge Replacement | 2009-09-08 | 2009-09-01 | 2010-04-05 | 2010-05-25 | 387159 | 0.020 | STIM205
9664 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | PONTOTOC |  | 04 | STIM206 | Replace the bridge over the Mill creek that is about 0.5 miles north and 2 miles east of Fittstown. Additional right of way was acquired to construct this project. | Bridge Replacement | 2009-09-08 | 2009-09-01 | 2010-04-05 | 2010-05-25 | 275105 | 0.020 | STIM206
9665 | OKLAHOMA | Completed | C250 | Highway Infrastructure Investment Grant | OKLAHOMA | POTTAWATOMIE |  | 05 | STIM207 | "Replace the bridge over the Popshego creek that is about 3 miles east of St. Louis, Oklahoma. Additional right of way was acquired to construct this project." | Bridge Replacement | 2009-09-08 | 2009-09-09 | 2010-01-05 | 2010-04-16 | 491743 | 0.020 | STIM207
9666 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GARVIN |  | 04 | STIM208 | Replace the bridge over the unnamed creek that is about 3.5 miles north of SH-7. | Bridge Replacement | 2009-08-03 | 2009-07-01 | 2009-11-30 | 2009-11-12 | 544000 | 0.300 | STIM208
9667 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN |  | 03 | STIM209 | Replace the bridge on EW-81 over Blue Creek about 4 miles west of Meridian. | Bridge Replacement | 2009-08-03 | 2009-07-01 | 2009-11-30 | 2009-11-25 | 400000 | 0.210 | STIM209
9668 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | MURRAY |  | 04 | STIM210 | Replace the bridge over Guy Sandy Creek that is about 8 miles north and a mile west of Sulphur in Murray County. | Bridge Replacement | 2009-10-05 | 2009-10-05 | 2010-02-01 | 2010-04-13 | 600000 | 0.250 | STIM210
9669 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | PAYNE |  | 03 | STIM211 | Replace the bridge over Clear Creek that is about 2 miles east and 7 miles south of the junction of I-35 and SH-51 | Bridge Replacement | 2009-08-03 | 2009-07-21 | 2009-10-31 | 2009-11-19 | 400000 | 0.250 | STIM211
9670 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM212 | This project installs a new bridge and approaches on a county bridge 3.9 miles west and 1 mile south of Piedmont | Bridge Replacement | 2009-08-03 | 2009-06-12 | 2009-12-30 | 2009-12-31 | 462972 | 0.200 | STIM212
9671 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM213 | This project installs a new box culvert and approaches on a county road 2 miles north and 3.6 mile east of Geary | Bridge Replacement | 2009-08-03 | 2009-06-12 | 2009-12-30 | 2009-12-31 | 166877 | 0.200 | STIM213
9672 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | COTTON |  | 04 | STIM214 | "This project replaces the deficient county bridge over East Cache Creek near Walters, OK. " | Bridge Replacement | 2009-08-03 | 2009-07-20 | 2009-11-30 | 2009-12-21 | 239425 | 0.250 | STIM214
9673 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | JEFFERSON |  | 04 | STIM215 | "This project replaces the deficient county bridge over Mud Creek near Ringling, OK. " | Bridge Replacement | 2009-08-03 | 2009-05-29 | 2009-12-30 | 2009-10-23 | 477024 | 0.250 | STIM215
9674 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOVE |  | 02 | STIM216 | This project replaces a low water crossing with a new bridge over Simon Creek northeast of the intersection of State Highways 76 and 32. | New Bridge Construction | 2009-08-03 | 2009-08-11 | 2009-12-30 | 2010-04-16 | 519881 | 0.120 | STIM216
9675 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | STEPHENS |  | 04 | STIM217 | "This project replaces the deficient county bridge over Deer Creek southeast of Comanche, OK. " | Bridge Replacement | 2009-10-05 | 2009-09-08 | 2010-05-02 | 2010-05-10 | 382956 | 0.010 | STIM217
9676 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | STEPHENS |  | 04 | STIM218 | "This project replaces the deficient county bridge over Stage Stand Creek southwest of Duncan, OK. " | Bridge Replacement | 2009-10-05 | 2009-09-08 | 2010-05-02 | 2010-05-10 | 452164 | 0.010 | STIM218
9677 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BECKHAM |  | 03 | STIM219 | "This project replaces a deficient county bridge over Buffalo Creek located about 7.5 miles north of Erick, OK. " | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2009-11-30 | 2009-12-16 | 709380.4 | 0.010 | STIM219
9678 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CUSTER |  | 03 | STIM220 | "This project replaces the deficient county bridge over Barnitz Creek northwest of Clinton, OK. " | Bridge Replacement | 2009-08-03 | 2009-08-03 | 2009-10-31 | 2010-01-12 | 439978.03 | 0.200 | STIM220
9679 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | DEWEY |  | 03 | STIM221 | "This project replaces the deficient county bridge over the South Canadian River northwest of Oakwood, OK. " | Bridge Replacement | 2009-10-05 | 2009-09-16 | 2010-04-02 | 2010-03-19 | 1726572 | 0.379 | STIM221
9680 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GREER |  | 03 | STIM222 | "This project replaces the deficient county bridge over Unnamed Creek southwest of Willow, OK. " | Bridge Replacement | 2009-10-05 | 2009-08-12 | 2010-01-02 | 2009-11-17 | 348518.43 | 0.010 | STIM222
9681 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | TILLMAN |  | 04 | STIM223 | "This project replaces the deficient county bridge over Deep Red Creek southeast of Loveland, OK. " | Bridge Replacement | 2009-08-03 | 2009-07-28 | 2009-11-30 | 2009-12-01 | 442728.6 | 0.200 | STIM223
9682 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | ALFALFA |  | 03 | STIM224 | This project resurfaces the existing asphalt pavement with and asphalt overlay on county road ( NS-271) 1.0 miles west Goltry and extends north 2.1 miles | Pavement Improvement | 2009-08-03 | 2009-07-06 | 2009-10-01 | 2009-09-01 | 491864 | 2.200 | STIM224
9683 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BEAVER |  | 03 | STIM225 | This project installs a new bridge and approaches on a county road ( NS-146) 7.0 miles east and 3.5 miles south of Elmwood | Bridge Replacement | 2009-08-03 | 2009-07-28 | 2010-03-30 | 2010-03-17 | 480040 | 0.200 | STIM225
9684 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CIMARRON |  | 03 | STIM226 | This project rehabitates the existing bridge over the Beaver River on a county road ( NS-13) 1.2 miles north of Felt | Bridge Improvement | 2009-08-03 | 2009-08-03 | 2009-10-31 | 2009-09-04 | 267370 | 0.010 | STIM226
9685 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GARFIELD |  | 03 | STIM227 | This project installs a new bridge and approaches on a county road ( NS-188) 0.6 miles north and 6.6 miles east of Waukomis | Bridge Replacement | 2009-08-03 | 2009-07-06 | 2009-12-30 | 2009-11-12 | 539870 | 0.250 | STIM227
9686 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GRANT |  | 03 | STIM228 | This project installs a new bridge and approaches on a county bridge over Sand Creek 1.0 miles north and 1.5 miles east of the junction with State Highway 11 and State Highway 132. | Bridge Replacement | 2009-08-03 | 2009-09-01 | 2009-12-30 | 2010-01-26 | 510378 | 0.250 | STIM228
9687 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GRANT |  | 03 | STIM229 | This project resurfaces the existing asphalt pavement with and asphalt overlay on a county road 5.3 miles south of Pond Creek and extends north 5.3 miles | Pavement Improvement | 2009-08-03 | 2009-08-06 | 2009-11-30 | 2009-06-08 | 514500 | 5.300 | STIM229
9688 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | KINGFISHER |  | 03 | STIM230 | This project installs a new bridge and reconstruct the roadway approaches on a county bridge 4.5 miles west State Highway74F in Cashion | Bridge Replacement | 2009-08-03 | 2009-09-08 | 2009-12-30 | 2010-02-19 | 564045 | 0.200 | STIM230
9689 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | NOBLE |  | 03 | STIM231 | This project installs a new bridge and approaches on county road over Red Rock Creek 4.5 miles west of the Junction with US 77 and State Highway 15 | Bridge Replacement | 2009-08-03 | 2009-07-09 | 2009-12-30 | 2009-11-06 | 764687 | 0.200 | STIM231
9690 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BEAVER |  | 03 | STIM232 | This project installs a new bridge and approaches on county road over Bull Creek 3.0 miles west and 3.4 miles north of the junction with State Highway 3 and US 83 at Byran Corner | Bridge Replacement | 2009-08-03 | 2009-07-28 | 2010-03-30 | 2010-03-17 | 439600 | 0.100 | STIM232
9691 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 03 | STIM235 | This project installs a new bridge and approaches on county road over a unnamed creek 15.0 miles east and 7.0 miles south of Okarche | Bridge Replacement | 2009-12-07 | 2009-11-18 | 2010-03-06 | 2010-04-02 | 241370.37 | 0.250 | STIM235
9692 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM236 | Installation of traffic signals and signal interconnection on 24th West Avenue beginning at State Highway 9 extending North to Tecumseh Road in Norman. | Safety/Traffic Management | 2009-08-03 | 2009-08-03 | 2009-10-01 | 2011-01-05 | 476193.85 | 0.010 | STIM236
9693 | OKLAHOMA | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | NOBLE |  | 03 | STIM237 | This project resurfaces and widens the existing asphalt pavement with an concrete overlay The project starts at Mile Marker 198 and entends to Mile Marker 203 on I-35 north of Perry | Pavement Widening | 2009-09-08 | 2009-08-10 | 2010-12-21 |  | 8474000 | 5.000 | STIM237
9694 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN |  | 03 | STIM238 | This project resurfaces the existing asphalt pavement with a Ultrathin MicroSurfacing preventive maintenance treatment The project starts at at the Kingfisher County Line on State Highway 3 east of Okarche and entends southeast 15.5 miles toward OKC | Pavement Improvement | 2009-06-05 | 2009-08-31 |  | 2009-11-25 | 2493352.41 | 15.540 | STIM238
9695 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | GARFIELD |  | 03 | STIM239 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the Major County Line on US 60 and extends east 5.0 miles toward Enid | Pavement Improvement | 2009-06-05 | 2009-08-10 |  | 2009-10-16 | 2201741 | 5.000 | STIM239
9696 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | WASHITA |  | 03 | STIM240 | "This project widens 2.5 miles of US 183 from two lanes to four lanes just south of Cordell, OK. " | Pavement Widening | 2009-08-03 | 2009-08-03 | 2010-01-19 | 2010-05-08 | 3781000 | 2.500 | STIM240
9697 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | BLAINE |  | 03 | STIM241 | "This project resurfaces about 8 miles of US 270 west of Watonga, OK to improve the smoothness of the road and to extend it's life. " | Pavement Improvement | 2009-05-29 | 2009-08-19 |  | 2009-09-29 | 2778000 | 7.900 | STIM241
9698 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM263 | Reconstruct, widen, and replace traffic signals at the intersection of E 131ST STREET & MEMORIAL | Safety/Traffic Management | 2010-08-02 | 2010-08-02 | 2011-04-28 |  | 817379.1 | 0.300 | STIM263
9699 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM264 | Resurface Elm Place from New Orleans St. to Florence St. | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-06-30 | 2010-08-16 | 823348.4 | 1.000 | STIM264
9700 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM265 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt at the intersection of Elm Place and Houston Street in Broken Arrow. The project also upgrades existing wheelchair ramps. | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-06-30 | 2010-08-16 | 222405 | 0.250 | STIM265
9701 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM266 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Kenosha Street from Main Street to Sixth Street in Broken Arrow. This | Pavement Improvement | 2010-02-01 | 2009-11-16 | 2010-05-31 | 2010-03-31 | 236578 | 0.500 | STIM266
9702 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM267 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Kenosha Street from Hickory Court to Aspen Avenue in Broken Arrow. The project also upgrades existing wheelchair ramps. | Pavement Improvement | 2010-02-01 | 2009-11-16 | 2010-05-31 | 2010-03-31 | 295984 | 0.500 | STIM267
9703 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM268 | Resurface intersection of 9th Street and Houston Street | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-06-30 | 2010-08-16 | 198538 | 0.250 | STIM268
9704 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM269 | Installation of traffic signals at the intersection of Albany Street and Stone Ridge Drive in Broken Arrow. | Safety/Traffic Management | 2010-01-04 | 2010-03-15 | 2010-04-03 | 2010-10-31 | 104331 | 0.125 | STIM269
9705 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM270 | Installation of traffic signals at the intersection of New Orleans and 9th Street in Broken Arrow. | Safety/Traffic Management | 2010-01-04 | 2010-03-15 | 2010-04-03 | 2010-10-31 | 86505 | 0.125 | STIM270
9706 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM271 | Installation of traffic signals at the intersection of Elm Place and Stonewood Drive in Broken Arrow. | Safety/Traffic Management | 2010-01-04 | 2010-03-15 | 2010-04-03 | 2010-10-31 | 109921 | 0.010 | STIM271
9707 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | ROGERS | TULSA | 01 | STIM272 | Installation of traffic signals at the intersection of Cherokee and South School Access in Catoosa. | Safety/Traffic Management | 2010-02-01 | 2010-04-21 | 2010-05-31 | 2010-08-10 | 142975 | 0.125 | STIM272
9708 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER | TULSA | 01 | STIM273 | Installation of traffic signals at the intesection of 141st Street and State Highway 51 in Coweta. | Safety/Traffic Management | 2010-02-01 | 2010-06-11 | 2010-05-01 | 2010-06-17 | 9653 | 0.125 | STIM273
9709 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER | TULSA | 01 | STIM274 | Resurface 151st St. from Division to SH-72 | Pavement Improvement | 2010-02-01 | 2010-06-11 | 2010-05-01 | 2010-06-17 | 34507 | 0.250 | STIM274
9710 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CREEK | TULSA | 01 | STIM275 | "GRADE, DRAIN & SURFACE WEST 81ST STREET SOUTH FROM SH-66 WEST TO FRANKHOMA ROAD" | Pavement Widening | 2010-08-02 | 2010-09-07 | 2011-01-28 |  | 1496904.67 | 1.000 | STIM275
9711 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM276 | RESURFACE 5TH STREET OVERLAY | Pavement Improvement | 2010-04-19 | 2010-05-25 | 2010-06-02 |  | 115650 | 0.500 | STIM276
9712 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM278 | This project will resurface the pavement of Airport Access Road from Euchee Creek Boulevard to West Shellcreek Road in Sand Springs by placing 2 to 2-3/4 inches of new asphalt which results in a smoother ride and extends the service life of the pavement. | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-11-18 | 2010-04-20 | 472877 | 3.000 | STIM278
9713 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CREEK | TULSA | 03 | STIM279 | This project will remove and replace the 6 inch concrete pavement on East Line Street from Mission Street to Moccasin Place in Sapulpa. | Pavement Improvement | 2009-11-02 | 2009-11-03 | 2010-03-01 | 2010-03-12 | 450828 | 0.500 | STIM279
9714 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM281 | This project includes pavement and driveway repairs and will resurface the pavement to Mohawk Boulevard from Cincinnati Avenue to Hartford Avenue in Tulsa by placing 2 inches of new asphalt. The proj | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2010-02-01 | 2010-04-01 | 762026 | 0.500 | STIM281
9715 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM282 | Pavement reconstruction and drainage improvements on Yale Avenue from Admiral Place to Pine Street in Tulsa. | Pavement Improvement | 2010-01-04 | 2010-02-08 | 2010-08-01 |  | 1111505.31 | 1.000 | STIM282
9716 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM283 | "This project includes full depth concrete repairs and complete concrete pavement replacement on Southwest Boulevard from 23rd Street South to the Arkansas River Bridge in Tulsa. This project also re | Pavement Improvement | 2009-11-30 | 2009-11-30 | 2010-09-25 | 2011-03-03 | 1940282 | 0.750 | STIM283
9717 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM284 | This project will extend the service life of the pavement by removing 2-3/4 inches of asphalt and placing 3 inches of new asphalt on Sheridan Road from 111th Street South to Admiral Boulevard in Tulsa | Pavement Improvement | 2010-01-04 | 2010-02-02 | 2011-03-29 |  | 1301812.65 | 1.000 | STIM284
9718 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM285 | "This project improves safety by adding paved shoulders and will extend the service life of the pavement by removing 3"" of existing asphalt and placing 3"" of new asphalt pavement. The project is lo | Pavement Improvement | 2010-03-15 | 2010-04-14 | 2010-12-24 | 2010-09-16 | 718372 | 0.350 | STIM285
9719 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM286 | This project will extend the service life of the pavement by removing 3 inches of asphalt and placing 3 inches of new asphalt on Sheridan Road from 11th Street South to 21st Street South in Tulsa. The project also upgrades and existing water line. | Pavement Improvement | 2010-01-04 | 2010-02-02 | 2011-03-29 |  | 1362389.45 | 1.000 | STIM286
9720 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM287 | This project will extend the service life of the pavement and makes driveway repairs to East 31st Street South from just west of South 132nd East Avenue to just east of South 140th East Avenue in Tuls | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2010-04-02 | 2010-06-04 | 387454 | 1.000 | STIM287
9721 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM288 | "This project will extend the service life of the pavement by removing 3-1/2"" of existing asphalt and placing 3"" of new asphalt pavement. The project also includes bridge deck repairs, upgrades an | Pavement Improvement | 2010-01-11 | 2010-01-11 | 2010-11-06 | 2011-01-30 | 1374172 | 1.000 | STIM288
9722 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM289 | "This project removes and replaces the existing pavement on East 41st Street from Interstate 44 to Sheridan Road and South Yale Avenue from 31st Street South to 36st Street South in Tulsa. The projec | Pavement Improvement | 2010-01-11 | 2010-01-11 | 2010-09-07 |  | 1841843 | 0.750 | STIM289
9723 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OSAGE |  | 03 | STIM290 | This project will extend the service life of the pavement by placing 3 inches of new asphalt pavement on U.S. Highway 60 beginning 0.75 mile east of the Osage/Kay County Line extending east 4.44 miles. | Pavement Improvement | 2009-07-06 | 2009-07-01 | 2009-07-28 | 2009-08-06 | 1169214.61 | 4.440 | STIM290
9724 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OSAGE |  | 03 | STIM291 | This project will extend the service life of the pavement by removing 1 inch of asphalt pavement and placing 2 inches of new asphalt pavement on State Highway 99 beginning 0 .86 mile north of the State Highway 99/20 junction extending north 4.17 miles. | Pavement Improvement | 2009-07-06 | 2009-06-24 | 2009-08-05 | 2009-08-25 | 616161.88 | 4.170 | STIM291
9725 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | PAWNEE |  | 03 | STIM293 | "This project will extend the service life of the pavement by patching the existing concrete pavement, installing supports at the joints, and grinding the surface to provide a smooth ride on U.S. High | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2009-12-14 | 2010-09-23 | 2162178.12 | 7.650 | STIM293
9726 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | PAWNEE |  | 03 | STIM294 | "This project will extend the service life of the pavement by patching the existing concrete pavement, installing supports at the joints, and grinding the surface to provide a smooth ride on U.S. High | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2009-12-14 | 2010-09-23 | 1212445.39 | 6.700 | STIM294
9727 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM295 | Asphalt pavement resurfacing for 2.77 miles on I-40 in Muskogee County. This project was reconstructed within existing right of ways and no lanes were added. | Pavement Improvement | 2009-06-05 | 2009-08-24 |  | 2009-10-09 | 2313529 | 4.390 | STIM295
9728 | OKLAHOMA | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | COMANCHE | LAWTON | 04 | STIM296 | "This project repairs 5 bridges, reconstructs deteriorated pavement, and improves safety features for about 2.5 miles of I-44 in Lawton, OK. " | Pavement Improvement | 2009-08-24 | 2009-08-24 | 2010-08-18 |  | 14217384 | 1.520 | STIM296
9729 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM297 | Resurface Rockwell Ave from NW 16th to NW 23rd and resurface NW 36th from Rockwell to Hammond | Pavement Improvement | 2010-02-18 | 2010-03-23 |  | 2010-06-17 | 414237 | 1.000 | STIM297
9730 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCLAIN | OKLAHOMA CITY | 04 | STIM298 | RESURFACE BLANCHARD ARRA: FROM SH-76 TO COUNTY LINE ROAD | Pavement Improvement | 2010-04-26 | 2010-04-27 | 2010-05-25 | 2010-05-25 | 135724.58 | 0.900 | STIM298
9731 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CIMARRON |  | 03 | STIM299 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the Junction with US 287 and extends east 7.5 miles on US 412 | Pavement Improvement | 2009-06-09 | 2009-07-28 |  | 2009-11-13 | 2150000 | 7.500 | STIM299
9732 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM300 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts at the on County Line road in the Cashion Area and extends from Seward Road to Forest Hill Road | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2009-12-11 | 2010-02-12 | 176426 | 1.000 | STIM300
9733 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM301 | RESURFACE NE 23RD FROM HENNEY RD TO CHOCTAW RD | Pavement Improvement | 2010-07-26 | 2010-07-26 | 2010-09-08 | 2010-09-30 | 323286 | 0.010 | STIM301
9734 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM302 | Resurface Etowah road from 108th Ave to 180th Ave SE. | Pavement Improvement | 2009-08-12 | 2009-08-31 |  | 2010-04-23 | 717297 | 6.000 | STIM302
9735 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 04 | STIM303 | "This project will resurface 1.75 miles of road in Del City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2010-02-01 | 2009-11-23 | 2010-03-02 | 2010-04-05 | 233637.29 | 1.750 | STIM303
9736 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM304 | "RESURFACE EDMOND ARRA: MULTIPLE LOCATIONS ON KELLY AVE, DANFORTH, EDMOND RD & 15TH STREET" | Pavement Improvement | 2010-05-04 | 2010-05-24 |  | 2010-10-13 | 1683176 | 4.700 | STIM304
9737 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM305 | This project will resurface 1 mile of road in the vicinity of Forrest Park in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 147302 | 1.000 | STIM305
9738 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM306 | Resurface Coltrane rodade from Seward road to Lakeshore Drive. | Pavement Improvement | 2010-04-01 | 2010-03-24 | 2010-04-30 | 2010-04-26 | 271669 | 1.500 | STIM306
9739 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM307 | Resurface Reno Avenue from Harrah Road to Pottawatomie Road | Pavement Improvement | 2010-04-05 | 2010-03-15 | 2010-05-19 | 2010-04-07 | 197078 | 1.500 | STIM307
9740 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM308 | This project will resurface 1.5 miles of Main Street in Jones to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 131157 | 1.500 | STIM308
9741 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM309 | Resurface Pensylvania avenue from Oklahoma Couty line north into logan county | Pavement Improvement | 2009-09-28 | 2009-09-28 | 2009-12-11 | 2010-02-12 | 443708 | 1.700 | STIM309
9742 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 04 | STIM400 | Resurface multiple locations in Midwest City on SE 29th and NE 10th. | Pavement Improvement | 2010-07-12 | 2010-07-20 | 2010-11-28 |  | 239175 | 2.000 | STIM400
9743 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM401 | Resurface Janeway and Santa Fe from NW 12th to NW 27th | Pavement Improvement | 2009-08-12 | 2009-08-31 |  | 2010-04-23 | 600303 | 2.000 | STIM401
9744 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 04 | STIM403 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts is on N Sara Rd in Mustang and extends from State Highwy 152 to SW 59th Street and South Mustage Frontage Road.. | Pavement Improvement | 2009-08-19 | 2009-10-16 |  | 2009-10-30 | 279620 | 2.000 | STIM403
9745 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM404 | TRAFFIC SIGNALS NE 23RD AT NICHOLS (TRAFFIC SIGNALS) | Transportation Enhancements | 2010-07-26 | 2010-07-26 | 2010-08-25 | 2010-10-01 | 70367 | 0.010 | STIM404
9746 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM405 | This project will resurface 1 mile of road in the vicinity of Nicoma Park in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 60197 | 1.000 | STIM405
9747 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM406 | Resurface Etowah road from 48th Ave SE to US-77 | Pavement Improvement | 2010-04-05 | 2010-03-22 | 2010-05-04 | 2010-04-05 | 191001.74 | 2.500 | STIM406
9748 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM407 | "Asphalt pavement resurfacing of portions of Eufaula Street, Flood Avenue, Jenkins Avenue, Lindsey Street, Porter Avenue, and University Boulevard in Cleveland County. This project was reconstructed within existing right of ways and no lanes were added. " | Pavement Improvement | 2009-08-12 | 2009-08-31 |  | 2010-04-23 | 1142437 | 3.740 | STIM407
9749 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM408 | "This project will resurface 5 miles of Memorial Road through north east Oklahoma City and Edmond to improve ride quality and extend the life of the pavement. In addition, new curb ramps will be installed. " | Pavement Improvement | 2009-08-13 | 2009-08-24 |  | 2009-11-16 | 1355644 | 5.000 | STIM408
9750 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM409 | "This project will resurface 8 miles of road in north west Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-12-18 |  | 3179188 | 8.000 | STIM409
9751 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM410 | "This project will resurface 1.7 miles of road in north west Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-08-19 | 2009-08-31 |  | 2010-06-09 | 652692 | 1.700 | STIM410
9752 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM411 | "This project will resurface 3 miles of May Avenue in south Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-08-19 | 2009-08-31 |  | 2010-06-09 | 966992 | 3.000 | STIM411
9753 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM412 | "This project will resurface 3.5 miles of Shields Boulevard in south Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-07-27 | 2009-07-20 | 2009-11-23 | 2010-01-13 | 1514850 | 3.500 | STIM412
9754 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM413 | Resurface multiple locations on Penn and May in the areas of SW 89th and SW 119th. | Pavement Improvement | 2009-07-27 | 2009-07-20 | 2009-11-23 | 2010-01-13 | 1416273 | 5.000 | STIM413
9755 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM414 | "This project will resurface 6 miles of road in Oklahoma City to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-09-28 | 2009-09-15 | 2009-11-26 |  | 2202725 | 6.000 | STIM414
9756 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM415 | This project will resurface 6.3 miles of Midwest Boulevard in north east Oklahoma City to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 2274617 | 6.300 | STIM415
9757 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM416 | This project will resurface 3 miles of road north of Luther to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 522272 | 3.000 | STIM416
9758 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 03 | STIM417 | This project resurfaces the existing asphalt pavement with an asphalt overlay The project starts is on Piedmont Rd in Mustang and extends from Arrowhead Road to Apache Street. | Pavement Improvement | 2009-07-27 | 2009-08-03 | 2009-08-26 | 2009-08-24 | 188523 | 1.000 | STIM417
9759 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 04 | STIM418 | This project will resurface 1 mile of road south of Spencer to improve ride quality and extend the life of the pavement. | Pavement Improvement | 2009-10-12 | 2010-03-17 | 2010-05-09 | 2010-08-27 | 117961 | 1.000 | STIM418
9760 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM419 | "This project will resurface 1 mile of Penn Avenue in the city of Village to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramps. " | Pavement Improvement | 2009-08-19 | 2009-08-31 |  | 2010-06-09 | 278129 | 1.000 | STIM419
9761 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM420 | "This project will resurface 0.5 mile of road in the city of Warr Acres to improve ride quality and extend the life of the pavement. In addition, the City will install new curb ramp " | Pavement Improvement | 2010-02-01 | 2010-02-01 | 2010-03-02 | 2010-04-14 | 116229.34 | 0.500 | STIM420
9762 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 03 | STIM421 | Resurface Cornwell from NW10th to Vandement. | Pavement Improvement | 2010-05-03 | 2010-05-03 | 2010-08-30 | 2010-09-02 | 676877 | 1.000 | STIM421
9763 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM422 | This project will extend the service life of the pavement by removing 2 inches of asphalt and placing 2 inches of new asphalt on East 2nd Street from Main Street to Adams Street in Sand Springs. | Pavement Improvement | 2009-10-05 | 2009-10-05 | 2009-11-18 | 2010-04-20 | 185046 | 0.500 | STIM422
9764 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCLAIN | OKLAHOMA CITY | 04 | STIM423 | Redeck and rehabilitation of US-62 bridge and approaches over H.E. Bailey Turnpike (I-44) in McClain County. This project was reconstructed within existing right of ways and no lanes were added. | Bridge Improvement | 2010-03-01 | 2010-03-01 | 2010-04-29 | 2010-09-28 | 392075.65 | 0.010 | STIM423
9765 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCLAIN | OKLAHOMA CITY | 04 | STIM424 | Installation of traffic signals on U.S. Highway 77 at the intesections of State Highway 74 and State Highway 39. | Safety/Traffic Management | 2010-02-08 | 2010-02-08 | 2010-05-08 | 2010-05-14 | 163803.18 | 0.010 | STIM424
9766 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | GRADY | OKLAHOMA CITY | 04 | STIM425 | INTERSECTION MOD. & TRAF. SIGNALS TUTTLE ARRA: INTERSECTION OF SH-37 & CIMARRON ROAD | Transportation Enhancements | 2010-05-03 | 2010-04-28 | 2010-07-16 |  | 225000 | 0.010 | STIM425
9767 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 04 | STIM427 | Resurface SE 15th from Douglas Blvd to Post Road. | Pavement Improvement | 2010-05-03 | 2010-05-04 | 2010-06-01 | 2010-06-08 | 351192 | 1.000 | STIM427
9768 | OKLAHOMA | Completed | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | CIMARRON |  | 03 | STIM428 | This project reconstructs the existing pavement with a new asphalt pavement. The project starts 7.0 miles south of the juncton with US 64 on US 287 and extends 0.8 miles | Pavement Improvement | 2009-08-17 | 2009-08-17 | 2010-02-12 | 2010-04-27 | 2084606 | 0.830 | STIM428
9769 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN |  | 03 | STIM429 | This project installs a new bridge and approaches on a county bridge over Wof Creek 2.0 miles north and 2.2 miles east of the junction with State Highway 74 and State Highway 74C. | Bridge Replacement | 2009-10-28 | 2009-11-30 | 2010-04-03 | 2010-03-19 | 172636 | 0.250 | STIM429
9770 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | MURRAY |  | 04 | STIM430 | "This project replaces the deficient county bridge over Eight Mile Creek near Hennepin, OK. " | Bridge Replacement | 2009-12-07 | 2009-11-30 | 2010-04-05 | 2010-03-19 | 247000 | 0.250 | STIM430
9771 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | ALFALFA |  | 03 | STIM431 | This project installs a new bridge and approaches on a county bridge over West Clay Creek on county road( NS 262) 1.0 miles east and 2.7 miles north of SH-8 junction with US-64 | Bridge Replacement | 2010-01-05 | 2010-01-05 | 2010-05-04 | 2010-06-24 | 511965 | 0.200 | STIM431
9772 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | OSAGE |  | 03 | STIM432 | This project replaces a deteriorated bridge on EW-33 over Cander Creek located 0.2 mile south and 1.3 miles east of Wolco. | Bridge Replacement | 2010-03-22 | 2010-03-08 | 2010-10-17 | 2010-12-23 | 430812 | 0.400 | STIM432
9773 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LATIMER |  | 02 | STIM433 | County Bridge Constrcution of the driving lanes and shoulders over Bear Creek located 0.50 miles North and 0.50 miles East of the Town of Lodi to replace a strucutrally defecient or obsolete local government bridge (off system). | Bridge Replacement | 2010-04-05 | 2010-04-05 | 2010-08-02 | 2010-08-11 | 125149 | 0.500 | STIM433
9774 | OKLAHOMA | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CHEROKEE |  | 02 | STIM434 | PEDESTRIAN IMPROVEMENTS HULBERT ARRA: SH-51 RIDER LN TO HALF BLOCK EAST OF THE POST OFFICE | Transportation Enhancements | 2010-08-02 | 2010-09-20 | 2010-10-30 |  | 366699 | 0.100 | STIM434
9775 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM435 | PEDESTRIAN IMPROVEMENTS COUNCIL HILL ARRA: SH-72 FROM 4TH ST TO 8TH ST (WEST SIDE ONLY) | Transportation Enhancements | 2010-04-05 | 2010-03-23 | 2010-07-02 | 2010-05-06 | 133395 | 0.100 | STIM435
9776 | OKLAHOMA | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM436 | PEDESTRIAN IMPROVEMENTS PORUM ARRA SH-2 FROM HALF BLOCK NORTH OF OSAGE SOUTH TO CHEROKEE AVE | Transportation Enhancements | 2010-08-02 | 2010-11-05 | 2010-10-30 |  | 348474 | 0.100 | STIM436
9777 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | SEQUOYAH |  | 02 | STIM437 | PEDESTRIAN IMPROVEMENTS VIAN ARRA US-64 FROM BLACKSTONE TO KENNEDY; SH-82 FROM MAIN TO SEQUOYAH | Transportation Enhancements | 2010-04-05 | 2010-04-05 | 2010-06-03 | 2010-08-23 | 441911 | 0.100 | STIM437
9778 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MUSKOGEE |  | 02 | STIM438 | PEDESTRIAN IMPROVEMENTS BOYNTON ARRA SH-72 FROM LUCILLE AVE NORTH TO NORTH OF KENEFICK AVE | Transportation Enhancements | 2010-04-05 | 2010-03-23 | 2010-07-02 | 2010-05-06 | 89298 | 0.100 | STIM438
9779 | OKLAHOMA | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | HASKELL |  | 02 | STIM439 | PEDESTRIAN IMPROVEMENTS KINTA ARRA SH-31 FROM HOYT TO MAIN; SH-2 FROM 4TH ST TO NORTH OF 2ND ST | Transportation Enhancements | 2010-04-05 | 2010-04-05 | 2010-06-03 |  | 161325 | 0.100 | STIM439
9780 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | LE FLORE |  | 02 | STIM441 | PEDESTRIAN IMPROVEMENTS TALIHINA ARRA US-271 FROM 1ST ST TO DUKE ST 1/2 BLOCK NORTH ON SH-1 | Transportation Enhancements | 2010-04-05 | 2010-03-11 | 2010-06-03 | 2010-06-02 | 128467 | 0.100 | STIM441
9781 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MCCURTAIN |  | 02 | STIM442 | PEDESTRIAN IMPROVEMENTS BROKEN BOW ARRA US-70 FROM PARK DR TO CHATA RD; US-259 FROM US-70 NORTH 0.4 MI (WEST SIDE ONLY) | Transportation Enhancements | 2010-04-05 | 2010-03-25 | 2010-06-03 | 2010-07-20 | 239644 | 0.100 | STIM442
9782 | OKLAHOMA | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MARSHALL |  | 04 | STIM445 | PEDESTRIAN IMPROVEMENTS KINGSTON ARRA US-70 FROM MAYTUBBY ST TO HANEY ST; US-70B FROM US-70 TO 1ST ST | Transportation Enhancements | 2010-04-05 | 2010-04-01 | 2010-08-02 |  | 457323 | 0.100 | STIM445
9783 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM446 | PEDESTRIAN IMPROVEMENTS AGRA ARRA SH-18 HAYES ST TO WASHINGTON ST | Transportation Enhancements | 2010-04-05 | 2010-04-09 | 2010-06-03 | 2010-07-12 | 144663 | 0.100 | STIM446
9784 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | LINCOLN |  | 03 | STIM447 | PEDESTRIAN IMPROVEMENTS TRYON ARRA SH-105 FROM OKLAHOMA ST TO 1ST ST | Transportation Enhancements | 2010-05-03 | 2010-05-11 | 2010-07-31 | 2010-10-12 | 237215 | 0.100 | STIM447
9785 | OKLAHOMA | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | SEMINOLE |  | 05 | STIM448 | PEDESTRIAN IMPROVEMENTS SASAKWA ARRA SH-56 FROM PINE ST TO CHESTNUT ST | Transportation Enhancements | 2010-05-03 | 2010-05-05 | 2010-08-30 |  | 148764 | 0.100 | STIM448
9786 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | GARVIN |  | 04 | STIM449 | PEDESTRIAN IMPROVEMENTS MAYSVILLE ARRA SH-19/SH-74 EAST TO PINE ALLEY | Transportation Enhancements | 2010-07-12 | 2010-06-28 | 2010-09-10 | 2011-01-14 | 95958 | 0.100 | STIM449
9787 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | KAY |  | 03 | STIM452 | PEDESTRIAN IMPROVEMENTS TONKAWA ARRA US-77/US-60B FROM GRAND AVE TO PARK AVE & MAIN ST TO PUBLIC ST | Transportation Enhancements | 2010-05-03 | 2010-04-19 | 2010-07-01 | 2011-01-28 | 317386 | 0.100 | STIM452
9788 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | KINGFISHER |  | 03 | STIM453 | PEDESTRIAN IMPROVEMENTS OKARCHE ARRA US-81 FROM IOWA ST NORTH TO MISSOURI (EAST SIDE ONLY) & MEMORIAL (WEST SIDE) | Transportation Enhancements | 2010-04-05 | 2010-04-26 | 2010-06-03 | 2010-08-17 | 304492 | 0.100 | STIM453
9789 | OKLAHOMA | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | KINGFISHER |  | 03 | STIM454 | PEDESTRIAN IMPROVEMENTS HENNESSEY ARRA US-81 FROM IOWA ST SOUTH TO 6TH ST | Transportation Enhancements | 2010-07-05 | 2010-08-11 | 2010-10-02 | 2011-01-08 | 778345 | 0.100 | STIM454
9790 | OKLAHOMA | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN |  | 03 | STIM455 | PEDESTRIAN IMPROVEMENTS CRESCENT ARRA SH-74 FROM NORTH LOCUST ST SOUTH TO WEST ADAMS ST | Transportation Enhancements | 2010-07-19 | 2010-07-19 | 2010-10-16 | 2010-11-18 | 355410 | 0.100 | STIM455
9791 | OKLAHOMA | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN |  | 03 | STIM456 | PEDESTRIAN IMPROVEMENTS LANGSTON ARRA SH-OB FROM WASHINGTON ST EAST TO MARTIN LUTHER KING ST | Transportation Enhancements | 2010-05-03 | 2010-05-03 | 2010-07-31 | 2010-11-27 | 1357120 | 0.010 | STIM456
9792 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | KINGFISHER |  | 03 | STIM457 | PEDESTRIAN IMPROVEMENTS KINGFISHER ARRA US-81 NORTH OF SH-33 RECONSTRUCTION OF THREE INTERSECTIONS | Transportation Enhancements | 2010-04-05 | 2010-04-13 | 2010-06-03 | 2010-10-19 | 494012 | 0.870 | STIM457
9793 | OKLAHOMA | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | HARMON |  | 03 | STIM458 | PEDESTRIAN IMPROVEMENTS HOLLIS ARRA US-62 FROM MAIN ST EAST TO 1ST ST | Transportation Enhancements | 2010-07-19 | 2010-08-25 | 2010-10-16 |  | 452793 | 0.100 | STIM458
9794 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | BECKHAM |  | 03 | STIM459 | PEDESTRIAN IMPROVEMENTS SAYRE ARRA SH-152/US-283 EAST TO COURTHOUSE SQUARE; US-283 FROM MAIN ST NORTH TO US-66 | Transportation Enhancements | 2010-03-01 | 2010-04-26 | 2010-04-29 | 2010-08-10 | 441823 | 0.100 | STIM459
9795 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | DEWEY |  | 03 | STIM460 | PEDESTRIAN IMPROVEMENTS VICI ARRA SH-51 FROM SPECK ST EAST TO BROWN ST **CERT** | Transportation Enhancements | 2010-04-05 | 2010-03-09 | 2010-06-03 | 2010-05-10 | 299649 | 0.100 | STIM460
9796 | OKLAHOMA | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BLAINE |  | 03 | STIM461 | PEDESTRIAN IMPROVEMENTS CANTON ARRA SH-51 FROM GRANT ST TO LINCOLN ST; SH-58 FROM MAIN ST TO PARK ST | Transportation Enhancements | 2010-07-05 | 2010-06-07 | 2010-10-02 |  | 595704 | 0.100 | STIM461
9797 | OKLAHOMA | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | GREER |  | 03 | STIM462 | PEDESTRIAN IMPROVEMENTS MANGUM ARRA SH-34 FROM EAST JACKSON ST TO EAST SOUTH ST | Transportation Enhancements | 2010-08-02 | 2010-08-03 | 2010-10-30 |  | 478252 | 0.100 | STIM462
9798 | OKLAHOMA | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | KIOWA |  | 03 | STIM463 | PEDESTRIAN IMPROVEMENTS HOBART ARRA US-183 | Transportation Enhancements | 2010-07-05 | 2010-07-06 | 2010-10-02 | 2010-11-02 | 491751 | 1.000 | STIM463
9799 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | TEXAS |  | 03 | STIM464 | PEDESTRIAN IMPROVEMENTS HARDESTY ARRA US-412 FROM 2ND ST WEST TO 6TH ST | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-04-29 | 2010-05-18 | 197303 | 0.100 | STIM464
9800 | OKLAHOMA | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | ELLIS |  | 03 | STIM465 | PEDESTRIAN IMPROVEMENTS SHATTUCK ARRA US-283 FROM GRAND AVE SOUTH TO 10TH ST | Transportation Enhancements | 2010-05-03 | 2010-05-03 | 2010-07-01 |  | 559449 | 0.100 | STIM465
9801 | OKLAHOMA | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | ELLIS |  | 03 | STIM466 | PEDESTRIAN IMPROVEMENTS GAGE ARRA SH-46 FROM NORTH ST SOUTH TO SH-46/SH-15 JCT | Transportation Enhancements | 2010-07-12 | 2010-07-14 | 2010-09-10 |  | 109804 | 0.100 | STIM466
9802 | OKLAHOMA | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | ALFALFA |  | 03 | STIM467 | PEDESTRIAN IMPROVEMENTS GOLTRY ARRA SH-45 FROM 7TH ST SOUTH TO 1/4 MI SOUTH OF MAIN ST | Transportation Enhancements | 2010-07-19 | 2010-08-16 | 2010-10-16 |  | 454528 | 0.100 | STIM467
9803 | OKLAHOMA | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | BEAVER |  | 03 | STIM468 | PEDESTRIAN IMPROVEMENTS FORGAN ARRA US-270 FROM TEXAS ST TO MISSISSIPPI AVE | Transportation Enhancements | 2010-04-19 | 2010-04-06 | 2010-06-17 | 2010-08-02 | 658984 | 0.100 | STIM468
9804 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | JEFFERSON |  | 04 | STIM469 | PEDESTRIAN IMPROVEMENTS WAURIKA ARRA SH-5 FROM ANDERSON AVE SOUTH TO US-70 | Transportation Enhancements | 2010-03-01 | 2010-03-01 | 2010-04-29 | 2010-06-10 | 236578 | 0.100 | STIM469
9805 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | GRADY |  | 04 | STIM470 | PEDESTRIAN IMPROVEMENTS POCASSET ARRA US-81 FROM 1ST ST SOUTH TO 5TH ST | Transportation Enhancements | 2010-04-05 | 2010-03-01 | 2010-06-03 | 2010-03-19 | 127638 | 0.100 | STIM470
9806 | OKLAHOMA | Underway | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | COTTON |  | 04 | STIM471 | PEDESTRIAN IMPROVEMENTS TEMPLE ARRA SH-65 FROM OREGON ST SOUTH TO OKLAHOMA ST | Transportation Enhancements | 2010-07-12 | 2010-07-12 | 2010-10-09 |  | 440815 | 0.100 | STIM471
9807 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | GRADY |  | 04 | STIM472 | PEDESTRIAN IMPROVEMENTS RUSH SPRINGS ARRA SH-17/SH-81B JCT TO SH-81 | Transportation Enhancements | 2010-04-05 | 2010-03-01 | 2010-07-03 | 2010-05-05 | 152435 | 0.100 | STIM472
9808 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | JEFFERSON |  | 04 | STIM473 | PEDESTRIAN IMPROVEMENTS HASTINGS ARRA SH-5 FROM COMMERCIAL AVE TO 4TH ST | Transportation Enhancements | 2010-05-03 | 2010-05-03 | 2010-07-01 | 2010-11-09 | 163191 | 0.100 | STIM473
9809 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | CADDO |  | 03 | STIM474 | "PEDESTRIAN IMPROVEMENTS CEMENT ARRA US-277(SH-19) FROM ""F"" AVE WEST TO ONE BLK WEST OF MAIN ST " | Transportation Enhancements | 2010-05-03 | 2010-06-01 | 2010-07-01 | 2010-06-18 | 113608 | 0.100 | STIM474
9810 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | CARTER |  | 04 | STIM475 | PEDESTRIAN IMPROVEMENTS GENE AUTRY ARRA SH-53A FROM GRANT AVE TO MILL ST (WEST SIDE ONLY) | Transportation Enhancements | 2010-04-05 | 2010-03-29 |  | 2010-06-10 | 95369 | 0.100 | STIM475
9811 | OKLAHOMA | Completed | C220,C200 | Highway Infrastructure Investment Grant | OKLAHOMA | CREEK |  | 01 | STIM476 | PEDESTRIAN IMPROVEMENTS MOUNDS ARRA US-75A FROM 9TH ST TO 14TH ST | Transportation Enhancements | 2010-07-05 | 2010-07-05 | 2010-10-02 | 2010-12-02 | 238017 | 0.200 | STIM476
9812 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | NOWATA |  | 02 | STIM477 | PEDESTRIAN IMPROVEMENTS NOWATA ARRA US-60 FROM DELAWARE OAK ST | Transportation Enhancements | 2010-05-03 | 2010-04-26 | 2010-07-01 | 2010-06-21 | 189298 | 0.100 | STIM477
9813 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | OSAGE |  | 03 | STIM478 | PEDESTRIAN IMPROVEMENTS FAIRFAX ARRA SH-18 FROM WALNUT ST TO MULBERRY ST | Transportation Enhancements | 2010-07-05 | 2010-06-21 | 2010-09-03 | 2010-12-17 | 200199 | 0.100 | STIM478
9814 | OKLAHOMA | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | OTTAWA |  | 02 | STIM479 | PEDESTRIAN IMPROVEMENTS QUAPAW ARRA US-69A FROM 1ST ST SOUTH TO 4TH ST | Transportation Enhancements | 2010-07-05 | 2010-07-06 | 2010-10-02 |  | 382625 | 0.100 | STIM479
9815 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | MAYES |  | 02 | STIM480 | PEDESTRIAN IMPROVEMENTS LOCUST GROVE ARRA US-412A FROM BROADWAY EAST TO CHEROKEE ST | Transportation Enhancements | 2010-07-05 | 2010-07-09 | 2010-10-02 | 2010-10-14 | 223695 | 0.100 | STIM480
9816 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | HASKELL |  | 02 | STIM481 | Replace the bridge over San Bois Creek about 1 mile south and 2 miles west of Kinta. | Bridge Replacement | 2010-03-01 | 2010-03-16 | 2010-06-28 | 2010-08-04 | 255379.54 | 0.220 | STIM481
9817 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM482 | Intersection modifications and installation of traffic signals at 21st Street and Sheridan Road in Tulsa. | Pavement Improvement | 2010-01-04 | 2010-02-02 | 2011-03-29 |  | 652209.95 | 0.010 | STIM482
9818 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM483 | RESURFACE BRYANT AVE BEG @ SH-37 & EXT NORTH TO N.E. 27TH ST & S.E. 34TH ST FR BRYANT AVE. TO SOONER RD. | Pavement Improvement | 2010-03-24 | 2010-06-23 |  |  | 851806 | 4.000 | STIM483
9819 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | WAGONER |  | 01 | STIM484 | PEDESTRIAN IMPROVEMENTS PORTER ARRA SH-51B FROM HALE ST SOUTH 6 BLK TO BELAIRE ST | Transportation Enhancements | 2010-04-05 | 2010-03-18 | 2010-06-18 | 2010-07-08 | 377227 | 0.500 | STIM484
9820 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | PITTSBURG |  | 02 | STIM485 | PEDESTRIAN IMPROVEMENTS KIOWA ARRA US-69 START & END AT THE CURB & GUTTER BOTH SIDES OF ROAD 8/10 MI LONG | Transportation Enhancements | 2010-04-05 | 2010-04-13 | 2010-08-02 | 2010-08-13 | 511485 | 0.800 | STIM485
9821 | OKLAHOMA | Underway | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | OTTAWA |  | 02 | STIM489 | PEDESTRIAN IMPROVEMENTS MIAMI ARRA US-69 FROM C ST SW TO A ST SW 4 BLK; SH-10 FROM A ST SW EAST 1.5 BLK | Transportation Enhancements | 2010-04-05 | 2010-05-05 | 2010-06-03 |  | 460384 | 0.100 | STIM489
9822 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM490 | RESURFACE S.E. 44TH STREET BEG @ BRYANT AVE. & EXTEND EAST TO SOONER ROAD IN DEL CITY & OKLAHOMA CITY | Pavement Improvement | 2010-04-19 | 2010-04-19 | 2010-05-18 | 2010-06-25 | 600229 | 2.000 | STIM490
9823 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CANADIAN | OKLAHOMA CITY | 04 | STIM491 | RESURFACE MORGAN ROAD BEG @ S.W. 89TH STREET & EXTEND NORTH TO S.W. 59TH STREET IN MUSTANG. | Pavement Improvement | 2010-05-17 | 2010-05-17 | 2010-06-15 | 2010-06-08 | 210466 | 2.000 | STIM491
9824 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM492 | RESURFACE KELLY AVE BEG @ WATERLOO ROAD & EXTEND NORTH TO CO RD(EW-88) | Pavement Improvement | 2010-04-26 | 2010-04-26 | 2010-05-25 | 2010-06-15 | 111305 | 1.000 | STIM492
9825 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM493 | RESURFACE MAIN STREET BEG @ STATE STREET & EXTEND EAST 0.5 MILE | Pavement Improvement | 2010-05-17 | 2010-05-10 | 2010-07-15 | 2010-07-21 | 87399 | 0.500 | STIM493
9826 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM494 | RESURFACE JONES ARRA: N.E. 36TH STREET BEG @ COLTRANE & EXT TO BARTREL RD | Pavement Improvement | 2010-05-17 | 2010-05-10 | 2010-07-15 | 2010-07-21 | 71068 | 1.000 | STIM494
9827 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM495 | RESURFACE LUTHER ARRA: LUTHER ROAD BEG @ EDMOND ROAD & EXT NORTH TO DANFORTH RD | Pavement Improvement | 2010-05-17 | 2010-05-10 | 2010-07-15 | 2010-07-21 | 188000 | 1.100 | STIM495
9828 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM497 | "RESURFACE SPENCER ARRA: SPNCR RD FR NE 36TH EXT N TO NE 50TH; SDWLKS & ADA RMPS FR NE 23RD TO NE 36TH ON SPNCR RD**CERT**(DEL FR 02-10, ADD TO 03-10;PLAN REV)" | Pavement Improvement | 2010-07-05 | 2010-07-16 | 2010-08-18 | 2010-09-16 | 89918 | 1.000 | STIM497
9829 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM499 | RESURFACE WARR ACRES ARRA: MACARTHUR AVE BEG @ NW 63RD ST & EXT NORTH TO N.W. EXPRESSWAY | Pavement Improvement | 2010-04-19 | 2010-05-21 | 2010-05-18 | 2010-05-27 | 217107 | 0.800 | STIM499
9830 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | LOGAN | OKLAHOMA CITY | 03 | STIM500 | RESURFACE GUTHRIE ARRA: WALNUT AVE FROM NOBLE TO MANSUR | Pavement Improvement | 2010-08-02 | 2010-08-02 | 2010-08-22 | 2010-09-20 | 46150 | 0.200 | STIM500
9831 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM501 | RESURFACE OKC ARRA: ANDERSON RD BEG @ S.E. 149TH ST. & EXT NORTH TO S.E. 89TH ST. | Pavement Improvement | 2010-05-17 | 2010-08-17 | 2010-06-30 | 2010-12-16 | 1304447 | 4.000 | STIM501
9832 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM502 | RESURFACE OKC ARRA: MERIDIAN AVE BEG AT S.W. 54TH ST. & EXT NORTH TO S.W. 29TH ST. | Pavement Improvement | 2010-06-07 | 2010-06-07 | 2010-07-06 | 2010-07-29 | 489821 | 1.600 | STIM502
9833 | OKLAHOMA | Completed | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | GRANT |  | 03 | STIM503 | "GRADE,DRAINING,BRIDGE & SURFACE CO. BR. OVER POND CR., 3 MI. N. AND 4.9 MI. E. OF THE SH-11/SH-11A JCT (FORMERLY BRO-127D(100)CO) " | Bridge Replacement | 2010-05-03 | 2010-04-12 | 2010-08-30 | 2010-09-10 | 95480 | 0.100 | STIM503
9834 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CLEVELAND | OKLAHOMA CITY | 04 | STIM504 | "GRADE,DRAINING,BRIDGE & SURFACE ROBINSON STREET AT THE BURLINGTON NORTHERN SANTE FE RAILROAD CROSSING, IN NORMAN " | Pavement Improvement | 2010-08-02 | 2010-06-14 | 2011-11-09 |  | 1888512 | 0.200 | STIM504
9835 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM505 | RESURFACE BROKEN ARROW ARRA: HOUSTON ST(81ST STREET SOUTH) BEG @ ASPEN AVE(145TH E. AVE) & EXT TO ELM PLACE(161ST E. AVE) | Pavement Improvement | 2010-07-05 | 2010-07-06 | 2010-08-18 |  | 435076 | 1.000 | STIM505
9836 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM506 | PAVEMENT REHABILITATION JENKS ARRA: MAIN STREET - RAILROAD EAST TO 4TH STREET | Pavement Improvement | 2010-08-02 | 2010-08-02 | 2010-10-30 |  | 141815 | 0.300 | STIM506
9837 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM507 | INTERSECT MODIF OWASSO ARRA: EAST 86TH STREET NORTH TO GARNETT ROAD INTERSECTION | Safety/Traffic Management | 2010-07-16 | 2010-09-09 |  | 2010-11-05 | 239679 | 0.100 | STIM507
9838 | OKLAHOMA | Completed | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | CREEK | TULSA | 01 | STIM508 | PAVEMENT REHABILITATION SAPULPA ARRA: 71ST ST SOUTH FROM RIVA RIDGE ROAD EAST TO 41ST STREET | Pavement Improvement | 2010-08-02 | 2010-09-20 | 2010-10-01 | 2010-12-10 | 209634.6 | 0.500 | STIM508
9839 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM510 | PAVEMENT REHABILITATION TULSA ARRA: 61ST STREET - YALE TO SHERIDAN | Pavement Improvement | 2010-10-04 | 2010-10-25 | 2011-03-12 |  | 1154002.81 | 1.000 | STIM510
9840 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM511 | PAVEMENT REHABILITATION TULSA ARRA: RIVERSIDE DRIVE FROM 68TH STREET TO 71ST STREET SOUTH | Safety/Traffic Management | 2010-10-04 | 2010-10-04 | 2011-01-31 |  | 332646.88 | 0.300 | STIM511
9841 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM512 | RESURFACE BROKEN ARROW ARRA: FLORENCE ST(111TH ST S) BEG @ OLIVE AVE(129TH E. AVE) & EXT TO ASPEN AVE(145TH E. AVE) | Pavement Improvement | 2010-07-05 | 2010-07-05 | 2010-10-02 |  | 310801 | 1.000 | STIM512
9842 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM513 | RESURFACE BROKEN ARROW ARRA: 23RD ST(COUNTY LINE) BEG @ JASPER ST(131ST ST S) & EXT TO YAZOO ST(141ST ST S) | Pavement Improvement | 2010-07-05 | 2010-07-05 | 2010-10-02 |  | 282225 | 1.000 | STIM513
9843 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM514 | PEDESTRIAN IMPROVEMENTS TULSA ARRA: LEWIS AVE FROM 21ST STREET TO 31ST STREET | Pavement Improvement | 2010-10-04 | 2010-10-04 | 2011-07-30 |  | 1019671.73 | 1.000 | STIM514
9844 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM515 | PEDESTRIAN IMPROVEMENTS TULSA ARRA: UNION AVE FROM 71ST STREET TO 81ST STREET | Pavement Improvement | 2010-08-30 | 2010-09-13 | 2010-11-27 |  | 668664.01 | 1.000 | STIM515
9845 | OKLAHOMA | Completed | C220 | Highway Infrastructure Investment Grant | OKLAHOMA | MURRAY |  | 04 | STIM516 | PEDESTRIAN IMPROVEMENTS SULPHUR ARRA SH-7 FROM 9TH ST EAST 0.521 MI TO FIRST ST | Transportation Enhancements | 2010-07-12 | 2010-07-12 | 2010-09-10 | 2010-10-29 | 298566 | 0.521 | STIM516
9846 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA | OKLAHOMA CITY | 05 | STIM517 | "GRADE, DRAIN & SURFACE WIDEN POST ROAD, BEGIN AT SE 15TH AND EXTEND NORTH TO RENO AVE." | Pavement Widening | 2010-10-04 | 2010-10-04 | 2011-07-10 |  | 2743619 | 1.000 | STIM517
9847 | OKLAHOMA | Underway | C230 | Highway Infrastructure Investment Grant | OKLAHOMA | TULSA | TULSA | 01 | STIM518 | INTERSECTION MOD. & TRAF. SIGNALS INTERSECTION MOD & TRAFFIC SIGNALS @ EAST ADMIRAL PLACE & SOUTH GARNETT ROAD. | Safety/Traffic Management | 2010-11-01 | 2010-11-08 | 2010-12-30 |  | 505184.44 | 0.250 | STIM518
9848 | OKLAHOMA | Underway | C250,C240 | Highway Infrastructure Investment Grant | OKLAHOMA | MAJOR |  | 03 | STIM519 | Bridge replacement and redo approaches of US-281 over Griever Creek approx. 5.0 miles north of junction of US-281 and US-60E | Bridge Replacement | 2010-08-02 | 2010-06-25 | 2011-05-03 |  | 2203565 | 1.000 | STIM519
9849 | OKLAHOMA | Underway | C200 | Highway Infrastructure Investment Grant | OKLAHOMA | POTTAWATOMIE |  | 05 | STIM525 | Railroad Rehabilation - Replacement of railroad ties, culverts, and bridge decking north out of Shawnee | Other | 2010-09-21 | 2010-10-01 |  |  | 4000000 | 0.010 | STIM525
9850 | OKLAHOMA | Underway | C240 | Highway Infrastructure Investment Grant | OKLAHOMA | OKLAHOMA |  | 05 | STIM526 | Railroad Rehabilation - Stabilize the river banks & THE railroad bed along the OKC to Shawnee spur (multiple locations) | Other | 2010-07-21 | 2010-08-02 |  |  | 4000000 | 0.010 | STIM526
9851 | OKLAHOMA | Underway | C200,C240 | Highway Infrastructure Investment Grant | OKLAHOMA | BECKHAM |  | 03 | STIM527 | Resurface I-40 eastward from mile marker 22 to approximatly mile marker 25. | Pavement Improvement | 2010-06-07 | 2010-06-10 | 2010-10-04 |  | 3036915 | 2.360 | STIM527
9852 | OKLAHOMA | Completed | C250,C200,C240 | Highway Infrastructure Investment Grant | OKLAHOMA | GARFIELD |  | 03 | STIM528 | Reconstruct US-81 beginning at the Kingfisher C/L & extending north approximately 7.2 miles resurfacing both the north and south lanes | Pavement Widening | 2010-08-02 | 2010-07-29 | 2011-01-28 | 2010-11-30 | 2110225 | 7.200 | STIM528
9853 | OKLAHOMA | Underway | C490 | OJT/SS | OKLAHOMA | OKLAHOMA |  | 05 | STIM529 | Transportation Infrastructure Project for the Oklahoma Department of Transportation identified as On-the-job Training and Support Services. | Other | 2012-02-28 |  |  |  | 96180 |  | STIM529
9854 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 0000183 | Enhance safety to pedestrians and bicyclists by repaving the EWEB Bike Path between Pioneer Parkway and 31st street in Eugene. | Other | 2009-05-11 | 2009-05-11 |  | 2009-06-18 | 1766.48 |  | 0000183
9855 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | 0100030 | Pave Salem Ave between Sherman St and the UP railroad crossing in Albany to improve safety and extend pavement life. | Pavement Improvement | 2009-07-14 | 2009-07-22 | 2009-08-31 | 2010-03-24 | 1040874.6 |  | 0100030
9856 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | 0100031 | Pave Salem Ave between Sherman St and the UP railroad crossing in Albany to improve safety and extend pavement life. | Other | 2009-04-28 | 2009-04-28 |  |  | 3129.4 |  | 0100031
9857 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | 0305019 | Improves safety on Hersey St between Oak St and Ann St in Ashland by reconstructing sidewalks. | Transportation Enhancements | 2009-07-14 | 2009-08-05 | 2009-10-31 | 2009-11-20 | 192069.3 |  | 0305019
9858 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 0305020 | Pave several city streets in Ashland to improve safety and extend pavement life. | Other | 2009-04-15 | 2009-04-15 |  | 2009-07-16 | 20095.52 |  | 0305020
9859 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | 0305021 | Improves safety on Hersey St between Oak St and Ann St in Ashland by reconstructing sidewalks. | Other | 2009-04-15 | 2009-04-15 |  |  | 3986.69 |  | 0305021
9860 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 0305022 | Pave several city streets in Ashland to improve safety and extend pavement life. | Pavement Improvement | 2009-08-11 | 2009-09-22 | 2009-10-31 | 2009-10-30 | 389776.33 |  | 0305022
9861 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | 0315006 | Pave several city streets in Astoria to improve safety and extend pavement life. | Pavement Improvement | 2010-03-03 | 2010-07-20 | 2010-08-31 | 2010-08-05 | 195779 |  | 0315006
9862 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | 0315007 | Pave several city streets in Astoria to improve safety and extend pavement life. | Other | 2009-07-23 | 2009-07-23 |  | 2010-02-04 | 20000 |  | 0315007
9863 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | 0330007 | Improve pedestrian and bicycle safety by adding sidewalks, curb cuts and drainage on OR 99E between Main St and 4th Street in Aurora. | Transportation Enhancements | 2009-07-24 | 2010-01-13 | 2009-10-15 | 2010-03-10 | 128175.52 | 0.090 | 0330007
9864 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | 0330008 | Improve pedestrian and bicycle safety by adding sidewalks, curb cuts and drainage on OR 99E between Main St and 4th Street in Aurora. | Other | 2009-06-25 | 2009-06-25 |  | 2009-06-26 | 344.11 | 0.090 | 0330008
9865 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | BAKER |  | 02 | 0365020 | Construct a pedestrian/bicycle shared use path on the Leo Adler Memorial Parkway between Madison St and Court St in Baker City. | Transportation Enhancements | 2009-11-23 | 2010-05-11 | 2010-09-30 | 2010-10-09 | 217064 |  | 0365020
9866 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535022 | Pave Hall Blvd between Hart Rd and Ridgecrest Dr in Beaverton to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2009-12-18 | 46671.81 |  | 0535022
9867 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535023 | Improve pedestrian safety and access by constructing sidewalks and ADA ramps on Laurelwood Ave and 87th Ave in Beaverton. | Other | 2009-07-08 | 2009-07-08 |  | 2010-01-21 | 212580.97 |  | 0535023
9868 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535024 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Other | 2009-08-05 | 2009-08-05 |  |  | 117929.99 |  | 0535024
9869 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535026 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Safety/Traffic Management | 2009-08-28 | 2009-08-28 | 2011-04-30 |  | 274380 |  | 0535026
9870 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535027 | Pave Hall Blvd between Hart Rd and Ridgecrest Dr in Beaverton to improve safety and extend pavement life. | Pavement Improvement | 2009-12-18 | 2010-02-23 | 2010-05-15 | 2010-05-06 | 517883.67 |  | 0535027
9871 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535028 | Improve pedestrian safety and access by constructing sidewalks and ADA ramps on Laurelwood Ave and 87th Ave in Beaverton. | Transportation Enhancements | 2010-02-19 | 2010-03-16 | 2010-07-15 | 2010-06-22 | 418307.38 |  | 0535028
9872 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535029 | Improve mobility and traffic flow on Farmington Rd and Cedar Hills Blvd in Hillsborro by upgrading to new 2070 traffic signal controllers, new local signal control software and retiming the signals. | Safety/Traffic Management | 2010-03-05 | 2010-07-07 | 2010-09-03 | 2010-08-06 | 251008.24 |  | 0535029
9873 | OREGON | Completed | C240,C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 0535032 | PAVEMENT PRESERVATION. GRIND AND REPLACE WITH 4-7" OF LEVEL 3 HMAC | Pavement Improvement | 2010-07-06 | 2010-08-20 | 2010-11-30 | 2010-11-12 | 642947.87 |  | 0535032
9874 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | 0580035 | Pave several city streets in Bend to improve safety and extend pavement life. | Pavement Improvement | 2009-09-18 | 2010-04-30 | 2010-06-30 | 2010-06-08 | 1125940.16 |  | 0580035
9875 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES | BEND | 02 | 0580036 | Pave several city streets in Bend to improve safety and extend pavement life. | Other | 2009-05-04 | 2009-05-04 |  | 2009-07-13 | 50014.3 |  | 0580036
9876 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 05 | 1075005 | Improve vehicle and pedestrian safety and extend pavement life by paving and adding curbs and sidewalk on North Knights Bridge Rd between Knights Bridge and N Grant St in Canby. | Other | 2009-06-22 | 2009-06-22 |  | 2010-03-11 | 19124.86 |  | 1075005
9877 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 05 | 1075006 | Improve vehicle and pedestrian safety and extend pavement life by paving and adding curbs and sidewalk on North Knights Bridge Rd between Knights Bridge and N Grant St in Canby. | Pavement Improvement | 2010-04-21 | 2010-06-16 | 2010-08-17 | 2010-12-17 | 305507.14 |  | 1075006
9878 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HARNEY |  | 02 | 1240011 | Pave Pine St between 1st St and 6th St in Central Point to improve safety and extend pavement life. | Safety/Traffic Management | 2010-02-04 | 2010-08-02 | 2010-07-31 | 2010-08-26 | 337276.31 |  | 1240011
9879 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 1240012 | Pave Pine St between 1st St and 6th St in Central Point to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2010-01-14 | 24877.49 |  | 1240012
9880 | OREGON | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | WASCO |  | 02 | 1342003 | Improves safety and access on US 30 at the Brewery Grade intersection in The Dalles by reconstructing intersection to a round-about. | Pavement Improvement | 2009-07-09 | 2009-08-25 | 2010-05-01 | 2010-06-03 | 2524023.94 | 0.410 | 1342003
9881 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | 1525004 | Pave North 10th St between Central Ave and Cedar Ave in Coos County to improve safety and extend pavement life. | Pavement Improvement | 2009-10-09 | 2009-11-30 | 2009-11-30 | 2010-05-07 | 332720.29 |  | 1525004
9882 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON |  | 01 | 1555007 | Improve pavement, add curbs, sidewalks and signals to enhance safety and reduce wear and tear on OR Hwy 8 in Cornelius. | Other | 2009-04-09 | 2009-04-09 |  | 2009-06-16 | 24265.33 |  | 1555007
9883 | OREGON | Completed | C240,C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 1555008 | Improve pavement, add curbs, sidewalks and signals to enhance safety and reduce wear and tear on OR Hwy 8 in Cornelius. | Pavement Improvement | 2008-05-22 | 2008-06-09 | 2009-02-28 | 2009-09-10 | 495659 |  | 1555008
9884 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 1555011 | Improve safety and extend the life of the pavement by sealing craks and repaving several streets in Cornelius. | Other | 2009-08-21 | 2009-08-21 |  | 2010-02-11 | 21474.9 |  | 1555011
9885 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | BENTON | CORVALLIS | 04 | 1580031 | Pave several city streets in Corvallis to improve safety and extend pavement life. | Pavement Improvement | 2009-08-28 | 2009-09-08 |  |  | 736145.54 |  | 1580031
9886 | OREGON | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | 1580032 | Enhance safety to pedestrians and bicyclists by repaving the Corvallis-Phillomath multi-use bicycle and pedestrian path in Benton County. | Pavement Improvement | 2009-07-09 | 2009-07-29 |  |  | 251120.55 |  | 1580032
9887 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | BENTON | CORVALLIS | 04 | 1580034 | Pave Western Ave between 7th and 17th St and 5th St between Western and 9th Ave in Corvallis to improve safety and extend pavement life. | Pavement Improvement | 2010-01-14 | 2010-05-18 |  |  | 407711.55 |  | 1580034
9888 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | 1580041 | The City proposes to re-surface the existing street, which includes two travel lanes, bike lanes and loop detectors. | Pavement Improvement | 2010-01-05 | 2010-02-05 |  |  | 112514.39 |  | 1580041
9889 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 1595004 | Improve safety on South 8th St and Woodson Bridge approaches in Cottage Grove by adding curb, gutter, sidewalks and paved shoulders. | Other | 2009-08-13 | 2009-08-13 |  | 2010-02-11 | 5188.99 |  | 1595004
9890 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 1595005 | Improve safety on South 8th St and Woodson Bridge approaches in Cottage Grove by adding curb, gutter, sidewalks and paved shoulders. | Pavement Improvement | 2010-03-08 | 2010-04-07 | 2010-09-30 | 2010-05-14 | 175361.27 |  | 1595005
9891 | OREGON | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 1595007 | Completely disassemble the structure and then rebuild it using as much of the original materials as possible, and maintain the historical integrity of the bridge. | Transportation Enhancements | 2010-11-19 | 2011-01-14 | 2011-11-30 | 2012-05-01 | 489329.64 |  | 1595007
9892 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 1770002 | Pave several city streets in Dallas to improve safety and extend pavement life. | Pavement Improvement | 2009-08-06 | 2009-08-24 | 2009-10-02 | 2009-09-16 | 351894.04 |  | 1770002
9893 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 1770003 | Pave several city streets in Dallas to improve safety and extend pavement life. | Other | 2009-06-04 | 2009-06-04 |  | 2009-07-16 | 697.26 |  | 1770003
9894 | OREGON | Underway | C220 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 2385052 | Enhances bridge and trail elements to improve usage of the Delta Ponds multi-use path between Goodpasture Island and Robin Hood Ln in Eugene. | Other | 2007-05-17 | 2007-05-17 |  |  | 60027.44 |  | 2385052
9895 | OREGON | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 2385059 | Improves access to the Eugene train depot by adding sidewalk and lighting to the pedestrian access. | Transportation Enhancements | 2009-07-13 | 2009-08-03 | 2009-10-31 | 2010-06-30 | 139245.05 |  | 2385059
9896 | OREGON | Underway | C220 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385060 | Enhances bridge and trail elements to improve usage of the Delta Ponds multi-use path between Goodpasture Island and Robin Hood Ln in Eugene. | Transportation Enhancements | 2009-08-10 | 2009-08-24 |  |  | 1229085.82 |  | 2385060
9897 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385061 | Complete pavement preservation project on Garfeield St between W 6th Ave and W 11th Ave in Eugene to improve safety and extend the life of the pavement. | Other | 2009-05-21 | 2009-05-21 |  |  | 31625.82 |  | 2385061
9898 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385063 | Complete pavement preservation project on Crescent Ave between Gamefarm Rd and Shadowview in Eugene to improve safety and extend the life of the pavement. | Other | 2009-06-19 | 2009-06-19 |  | 2009-11-19 | 6000 |  | 2385063
9899 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385064 | Complete pavement preservation project on High St between 3rd Ave and 17th Ave in Eugene to improve safety and extend the life of the pavement. | Other | 2009-06-19 | 2009-06-19 |  |  | 43268.18 |  | 2385064
9900 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 2385068 | Complete pavement preservation project on 11th Ave between Garfield and Tyinn and 13th Ave between Alder and Washington in Eugene to improve safety and extend the life of the pavement. | Pavement Improvement | 2010-07-07 | 2010-07-06 |  |  | 691951.33 |  | 2385068
9901 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 2605001 | Pave several city streets in Florence to improve safety and extend pavement life. | Other | 2009-04-29 | 2009-04-29 |  | 2009-12-10 | 15000 |  | 2605001
9902 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | 2605002 | Pave several city streets in Florence to improve safety and extend pavement life. | Pavement Improvement | 2010-01-06 | 2010-05-07 | 2010-05-31 | 2010-08-05 | 186437 |  | 2605002
9903 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 2620003 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Other | 2006-04-04 | 2006-04-04 |  | 2009-06-17 | 86399.5 |  | 2620003
9904 | OREGON | Completed | C220,C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 2620004 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Transportation Enhancements | 2008-04-04 | 2008-04-28 | 2008-12-31 | 2010-01-11 | 1325945.17 |  | 2620004
9905 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 2620005 | Expand sidewalk improvements for safer pedestrian access along pedestrian route between 19th Ave and Pacific Ave in Forest Grove. | Other | 2007-08-29 | 2007-08-29 |  |  | 9222.45 |  | 2620005
9906 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 2900008 | Pave several city streets in Gladstone to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  |  | 66989.51 |  | 2900008
9907 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 2900009 | Pave several city streets in Gladstone to improve safety and extend pavement life. | Pavement Improvement | 2010-03-04 | 2010-05-06 | 2010-07-30 | 2010-07-14 | 721679.79 |  | 2900009
9908 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 02 | 3055403 | Pave several city streets in Grants Pass to improve safety and extend pavement life. | Other | 2009-06-05 | 2009-06-05 |  | 2010-01-14 | 60000 |  | 3055403
9909 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 04 | 3055404 | Pave several city streets in Grants Pass to improve safety and extend pavement life. | Pavement Improvement | 2010-02-01 | 2010-05-03 | 2010-05-31 | 2010-06-15 | 513254.73 |  | 3055404
9910 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 02 | 3055405 | CONSTRUCT 6 NEW TRANSIT SHELTERS | Other | 2009-09-11 | 2009-09-11 |  | 2012-10-20 | 65000 |  | 3055405
9911 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 3125034 | Improve safety and access to vehicles, bicycles and pedestrians on 242nd and Hogan Rd between Glisan St and Stark St by widening the seciton of road and adding four travel lanes, center turn lane, bicycle lanes and sidewalks. | Other | 2009-06-11 | 2009-06-11 |  | 2009-10-22 | 34032.76 |  | 3125034
9912 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 3125035 | Improve safety and access to vehicles, bicycles and pedestrians on 242nd and Hogan Rd between Glisan St and Stark St by widening the seciton of road and adding four travel lanes, center turn lane, bicycle lanes and sidewalks. | Pavement Improvement | 2009-11-24 | 2010-02-01 | 2009-09-30 | 2010-10-15 | 1709952.39 |  | 3125035
9913 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 3205001 | Extend the life of the pavement on city streets in Happy Valley by sealing and resurfacing several minor arterial streets. | Other | 2009-05-15 | 2009-05-15 |  | 2010-02-04 | 80051.09 |  | 3205001
9914 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 03 | 3205002 | Extend the life of the pavement on city streets in Happy Valley by sealing and resurfacing several minor arterial streets. | Pavement Improvement | 2010-03-05 | 2010-08-23 | 2010-10-31 | 2010-10-21 | 708367.81 |  | 3205002
9915 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | 3370003 | Pave Feedville Rd and Kelli blvd between OR 395 and Cook Industrial site in Umatilla County to improve safety and extend pavement life. | Pavement Improvement | 2009-12-22 | 2010-07-23 | 2010-07-31 | 2010-07-30 | 297706.65 |  | 3370003
9916 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | 3370004 | Pave Feedville Rd and Kelli blvd between OR 395 and Cook Industrial site in Umatilla County to improve safety and extend pavement life. | Other | 2009-07-29 | 2009-07-29 |  | 2009-07-31 | 14067.89 |  | 3370004
9917 | OREGON | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 3410013 | MULTI-USE PATH THAT CONNECTS TO QUATAMA LRT STATION | Other | 2010-07-26 | 2010-07-26 | 2012-03-22 | 2012-02-22 | 138000 |  | 3410013
9918 | OREGON | Completed | C250,C240 | Highway Infrastructure Investment Grant | OREGON | MORROW |  | 02 | 3650003 | Enhance pedestrian and bicycle safety by constructing sidewalks, bike lanes, and a planter strip with street trees along 1st St and Main Ave in Irrigon. | Transportation Enhancements | 2009-07-09 | 2009-07-23 | 2009-10-31 | 2010-12-15 | 1527961.59 |  | 3650003
9919 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | MORROW |  | 02 | 3650004 | Enhance pedestrian and bicycle safety by constructing sidewalks, bike lanes, and a planter strip with street trees along 1st St and Main Ave in Irrigon. | Other | 2009-05-13 | 2009-05-13 |  | 2009-06-18 | 94570.28 |  | 3650004
9920 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 3700009 | Improve bicycle and pedestrian safety and mobility by adding bike lanes and sidewalks to C St in Jacksonville. | Other | 2009-05-14 | 2009-05-14 |  | 2010-01-21 | 58000 |  | 3700009
9921 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | 3700010 | Improve bicycle and pedestrian safety and mobility by adding bike lanes and sidewalks to C St in Jacksonville. | Transportation Enhancements | 2010-02-19 | 2010-03-08 | 2010-08-31 | 2010-08-04 | 180500 |  | 3700010
9922 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | 3850008 | Pave Dearborn Ave and Chemawa Rd in Keizer to improve safety and extend pavement life. | Pavement Improvement | 2010-04-06 | 2010-08-27 | 2010-09-15 | 2010-09-15 | 96539.43 |  | 3850008
9923 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | 3850009 | Pave Dearborn Ave and Chemawa Rd in Keizer to improve safety and extend pavement life. | Other | 2010-03-22 | 2010-03-22 |  | 2010-03-04 | 199.89 |  | 3850009
9924 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | KLAMATH |  | 02 | 3970018 | Improve safety of pedestrian connections to the bus and train station in Klamath Falls by restoring fencing, adding lighting and crossing enhancements. Improves mobility by repaving Spring St. | Transportation Enhancements | 2009-06-10 | 2009-07-13 | 2009-09-30 | 2009-10-14 | 136097.56 |  | 3970018
9925 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UNION |  | 02 | 4035014 | Pave Spruce St between Monroe Ave and Z avenue in LaGrande to improve safety and extend pavement life. | Pavement Improvement | 2010-02-11 | 2010-06-19 | 2010-07-31 | 2010-06-25 | 230822.74 |  | 4035014
9926 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UNION |  | 02 | 4035015 | Pave Spruce St between Monroe Ave and Z avenue in LaGrande to improve safety and extend pavement life. | Other | 2009-07-20 | 2009-07-20 |  | 2010-01-14 | 11574.51 |  | 4035015
9927 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 4055009 | Pave Royce and McNary St in Lake Oswego to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2010-02-04 | 83490.87 |  | 4055009
9928 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 4055010 | Pave Royce and McNary St in Lake Oswego to improve safety and extend pavement life. | Pavement Improvement | 2010-03-08 | 2010-05-06 | 2010-07-30 | 2010-07-12 | 395394.88 |  | 4055010
9929 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | 4165007 | Pave 2nd St and Airport Rd in Lebanon to improve safety and extend pavement life. | Pavement Improvement | 2010-02-23 | 2010-04-23 | 2010-07-31 | 2010-07-30 | 253672.93 |  | 4165007
9930 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | 4165008 | Pave 2nd St and Airport Rd in Lebanon to improve safety and extend pavement life. | Other | 2009-07-01 | 2009-07-01 |  | 2010-01-28 | 43112.92 |  | 4165008
9931 | OREGON | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | 4500006 | Pave several city streets in McMinnville to improve safety and extend pavement life. | Pavement Improvement | 2009-07-16 | 2009-08-13 | 2010-05-28 | 2009-10-20 | 739314.74 |  | 4500006
9932 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | 4500007 | Pave several city streets in McMinnville to improve safety and extend pavement life. | Other | 2009-06-18 | 2009-06-18 |  | 2009-06-19 | 7924.48 |  | 4500007
9933 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 03 | 4865010 | Improve pedestrian safety and access by reconstructing sidewalks, streetscape, and curb extensions on Jackson St between Main St and 21st Ave in Clackamas. | Other | 2009-08-05 | 2009-08-05 |  | 2010-03-04 | 159573.74 |  | 4865010
9934 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLATSOP | PORTLAND (WA) | 01 | 4865013 | Improve pedestrian safety and access by reconstructing sidewalks, streetscape, and curb extensions on Jackson St between Main St and 21st Ave in Clackamas. | Transportation Enhancements | 2010-04-15 | 2010-05-28 | 2010-10-29 | 2010-11-24 | 759522.05 |  | 4865013
9935 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 4955001 | Pave Stadium Dr and Jackson St in Monmouth to improve safety and extend pavement life. | Pavement Improvement | 2010-01-11 | 2010-05-11 | 2010-06-30 | 2010-08-19 | 153925.36 |  | 4955001
9936 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 4955002 | Pave Stadium Dr and Jackson St in Monmouth to improve safety and extend pavement life. | Other | 2009-08-10 | 2009-08-10 |  | 2009-10-12 | 2170.49 |  | 4955002
9937 | OREGON | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | GRANT |  | 02 | 5025101 | Install additional lights on Main Street in Mt. Vernon to improve pedestrian safety. | Transportation Enhancements | 2009-02-24 | 2009-03-30 | 2009-10-23 | 2009-08-14 | 99964 | 0.500 | 5025101
9938 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | 5210002 | Pave several city streets in Newberg to improve safety and extend pavement life. | Other | 2009-10-30 | 2009-10-30 |  | 2010-02-11 | 34745.71 |  | 5210002
9939 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | YAMHILL |  | 01 | 5210003 | Pave several city streets in Newberg to improve safety and extend pavement life. | Pavement Improvement | 2010-03-18 | 2010-06-21 | 2010-08-15 | 2010-11-11 | 449218.33 |  | 5210003
9940 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | 5245004 | Improve safety and access with repairs to sidewalks, curb and gutter, paving, and lighting on Bay Blvd in Newport. | Pavement Improvement | 2009-08-17 | 2009-09-08 | 2010-06-30 | 2010-06-30 | 583000 |  | 5245004
9941 | OREGON | Underway | C200,C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | 5245005 | Improve safety and access with repairs to sidewalks, curb and gutter, paving, and lighting on Bay Blvd in Newport. | Other | 2009-04-15 | 2009-04-15 |  |  | 11671.95 |  | 5245005
9942 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 5245006 | Improve safety and extend pavement life on several city streets in Talent and Phoenix by paving, addind additional signage and signals. | Pavement Improvement | 2009-08-11 | 2009-10-12 | 2009-11-16 | 2010-02-23 | 381548.97 |  | 5245006
9943 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | 5245007 | Pave several city streets in Newport to improve safety and extend pavement life. | Other | 2009-05-21 | 2009-05-21 |  |  | 2315.29 |  | 5245007
9944 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | 5245008 | Pave several city streets in Newport to improve safety and extend pavement life. | Pavement Improvement | 2009-08-07 | 2009-09-01 | 2009-10-16 | 2009-10-20 | 191502.45 |  | 5245008
9945 | OREGON | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | 5300006 | Pave Sherman Ave between Newmark St and City Limits in North Bend to improve safety and extend pavement life. | Pavement Improvement | 2010-03-01 | 2010-06-28 | 2010-07-30 | 2010-11-17 | 233212.82 |  | 5300006
9946 | OREGON | Completed | C220,C200,C240 | Highway Infrastructure Investment Grant | OREGON | MALHEUR |  | 02 | 5490003 | Enhance safety by widening and repaving roadway, and installing sidewalks and curbs on N Oregon St between Idaho Ave and NW 1st St in Ontario. | Pavement Improvement | 2009-07-06 | 2009-07-24 | 2009-11-30 | 2010-10-22 | 1991199.17 |  | 5490003
9947 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 5520019 | Improve vehicle and pedestrian safety, mobility and traffic flow on Warner Milne Rd between Beaversreek and Mollala in Oregon City buy realigning the intersection, updating signal timing and adding sidewalks. | Safety/Traffic Management | 2009-08-18 | 2009-09-21 | 2010-05-14 | 2010-08-20 | 1152241.94 |  | 5520019
9948 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 03 | 5520020 | Enhance safety on historic McLoughlin Promenade multi-use path between 7th St and S 1st St in Oregon City by restoring historing walls, including wall caps and joints, handrails, stairs and tunnel. | Transportation Enhancements | 2009-07-09 | 2009-08-20 | 2010-09-01 | 2010-06-29 | 1065721 |  | 5520020
9949 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 5520023 | Improve vehicle and pedestrian safety, mobility and traffic flow on Warner Milne Rd between Beaversreek and Mollala in Oregon City buy realigning the intersection, updating signal timing and adding sidewalks. | Other | 2009-04-27 | 2009-04-27 |  | 2009-08-31 | 14151.71 |  | 5520023
9950 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | 5715013 | Pave Tutuilla Rd between US 395 (Southgate) and SW Athens Way in Umatilla County to improve safety and extend pavement life. | Pavement Improvement | 2010-01-07 | 2010-06-30 | 2010-07-31 | 2010-09-21 | 357100.17 |  | 5715013
9951 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | UMATILLA |  | 02 | 5715014 | Pave Tutuilla Rd between US 395 (Southgate) and SW Athens Way in Umatilla County to improve safety and extend pavement life. | Other | 2009-07-29 | 2009-07-29 |  | 2009-07-31 | 19959.51 |  | 5715014
9952 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 01 | 5900175 | Improve safety and mobility for motorists, pedestrians and bicyclists and extend pavement life by reconstructing roadway, sidewalks and bikelanes on NW 23rd Ave between Lovejoy and Burnside. | Safety/Traffic Management | 2010-01-04 | 2010-01-04 |  |  | 432000 |  | 5900175
9953 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900197 | Complete pavement preservation project on several streets in SE Portland to improve safety and extend the life of the pavement. | Pavement Improvement | 2010-03-22 | 2010-03-25 |  |  | 2092098.68 |  | 5900197
9954 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900199 | Improve safety and accessibility in southwest and east Portland with curb cuts and sidewalks on variuos streets. | Pavement Improvement | 2010-04-12 | 2010-05-26 |  |  | 1218729.31 |  | 5900199
9955 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900201 | Improve bicycle safety and mobility by adding striping, signage and wayfinding to the Portland bicycle boulevard project. | Other | 2009-07-21 | 2009-07-21 |  | 2009-11-10 | 70332.39 |  | 5900201
9956 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 01 | 5900202 | Improve interesection safety and access by adding a right turn lane from 82nd Ave to westbound Columbia Blvd in Portland. | Other | 2009-07-20 | 2009-07-20 | 2011-06-30 | 2011-06-30 | 200000 |  | 5900202
9957 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900203 | Pave Springwater Trail between UPRR Bridge and the East City border in Portland to improve safety and extend the life of the pavement. | Other | 2009-07-21 | 2009-07-21 |  |  | 99358.25 |  | 5900203
9958 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900204 | Complete pavement preservation project on several streets in SE Portland to improve safety and extend the life of the pavement. | Other | 2009-08-05 | 2009-08-05 |  | 2009-12-07 | 15291.99 |  | 5900204
9959 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900205 | Pave Springwater Trail between UPRR Bridge and the East City border in Portland to improve safety and extend the life of the pavement. | Pavement Improvement | 2010-03-18 | 2010-05-06 |  |  | 1151766.06 |  | 5900205
9960 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900207 | Improve safety and accessibility in southwest and east Portland with curb cuts and sidewalks on variuos streets. | Other | 2009-08-05 | 2009-08-05 |  | 2009-12-07 | 175906.11 |  | 5900207
9961 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 01 | 5900212 | Improve bicycle, pedestrian and motorist safety by replacing street lighting on several city streets around Keller Auditorium in downtown Portland. | Safety/Traffic Management | 2011-01-17 | 2011-01-17 |  |  | 5334620.02 |  | 5900212
9962 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900215 | Improve bicycle safety and mobility by adding striping, signage and wayfinding to the Portland bicycle boulevard project. | Transportation Enhancements | 2010-03-09 | 2010-03-31 |  |  | 705487.85 |  | 5900215
9963 | OREGON | Underway | C220 | Highway Infrastructure Investment Grant | OREGON | MULTNOMAH | PORTLAND (WA) | 03 | 5900216 | Improve multi-modal access for patrons of Amtrak, light rail transit, streetcar, inter-city and city bus by making facility improvements at Union Station. | Transportation Enhancements | 2010-06-10 | 2010-06-10 |  |  | 873741.75 |  | 5900216
9964 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | 5985008 | Improve mobility and safety by adding 2nd Street egress to OR 126 (3rd St) in Prineville. | Other | 2009-03-24 | 2009-03-24 |  | 2009-06-16 | 4126.71 |  | 5985008
9965 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | 5985009 | Improve mobility and safety by adding 2nd Street egress to OR 126 (3rd St) in Prineville. | New Construction | 2009-07-13 | 2009-08-24 | 2009-10-31 | 2010-04-28 | 280974.72 |  | 5985009
9966 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | 5985010 | Pave several city streets in Prineville to improve safety and extend pavement life. | Pavement Improvement | 2009-08-05 | 2009-09-02 | 2009-09-15 | 2009-11-10 | 218674.6 |  | 5985010
9967 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | 5985011 | Pave several city streets in Prineville to improve safety and extend pavement life. | Other | 2009-03-24 | 2009-03-24 |  |  | 3312.4 |  | 5985011
9968 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | 6120009 | Improve safety by reconstructing 5th St between SW Glacier and Jackpine in Redmond. Project includes paving, stormwater system, curb repair and sidewalks. | Other | 2009-02-23 | 2009-02-23 |  |  | 3468 | 1.020 | 6120009
9969 | OREGON | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | 6120010 | Improve safety by reconstructing 5th St between SW Glacier and Jackpine in Redmond. Project includes paving, stormwater system, curb repair and sidewalks. | Pavement Improvement | 2009-07-07 | 2009-08-03 | 2010-06-30 | 2010-07-08 | 3657957.62 | 1.020 | 6120010
9970 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | 6365002 | Pave Garden Valley Blvd between Stewart Pkwy and West City Line in Roseburg to improve safety and extend pavement life. | Pavement Improvement | 2010-02-22 | 2010-07-02 | 2010-07-15 | 2010-07-30 | 658791 |  | 6365002
9971 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | 6460002 | Improve vehcile and pedestrian safety and extend pavement life on Columbia Blvd between US 30 and 1st St in St. Helens by paving and adding sidewalks, curb and gutter. | Pavement Improvement | 2010-02-17 | 2010-07-06 | 2010-06-30 | 2010-07-21 | 204384.94 |  | 6460002
9972 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | 6460003 | Improve vehcile and pedestrian safety and extend pavement life on Columbia Blvd between US 30 and 1st St in St. Helens by paving and adding sidewalks, curb and gutter. | Other | 2009-08-14 | 2009-08-14 |  | 2010-01-21 | 59452.06 |  | 6460003
9973 | OREGON | Underway | C220 | Highway Infrastructure Investment Grant | OREGON | POLK |  | 05 | 6490071 | Preserve investment in Union Street Rail Road bridge shared use path in Salem by removing lead based paint and re-painting upper portion of the bridge. | Other | 2009-05-11 | 2009-05-11 |  |  | 20213.81 |  | 6490071
9974 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | 6490072 | Pave sections of Hyacinth St, Chemawa Rd, Cordon Rd, Hawthorne Ave and Kuebler Blvd in Salem to improve safety and extend pavement life. | Other | 2009-08-13 | 2009-08-13 |  |  | 252944.92 |  | 6490072
9975 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | 6490073 | Pave sections of Hyacinth St, Chemawa Rd, Cordon Rd, Hawthorne Ave and Kuebler Blvd in Salem to improve safety and extend pavement life. | Pavement Improvement | 2010-03-08 | 2010-03-25 | 2010-09-30 | 2011-05-27 | 3572578.61 |  | 6490073
9976 | OREGON | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | 6490075 | Preserve investment in Union Street Rail Road bridge shared use path in Salem by removing lead based paint and re-painting upper portion of the bridge. | Transportation Enhancements | 2009-10-16 | 2009-11-09 | 2010-05-15 | 2011-09-30 | 2066707.9 |  | 6490075
9977 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | POLK | SALEM | 05 | 6490077 | Improve bicycle and pedestrian safety and mobility by improving the bike / ped path in Wallace Marine Park from the Union St Bridge to Glen Creek Rd. | Other | 2009-11-24 | 2009-11-24 | 2013-06-20 |  | 50000 |  | 6490077
9978 | OREGON | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | 6550002 | Improve safety along road by removing and replacing curb, gutter, sidewalk and street trees along US 30 between Old Portland Rd and Crown Zellerbach Rd in Scappoose. | Transportation Enhancements | 2009-07-15 | 2009-08-05 | 2009-09-30 | 2009-10-30 | 251291 | 1.030 | 6550002
9979 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | 6550003 | Improve safety along road by removing and replacing curb, gutter, sidewalk and street trees along US 30 between Old Portland Rd and Crown Zellerbach Rd in Scappoose. | Other | 2009-04-15 | 2009-04-15 |  | 2009-06-18 | 59079.34 | 1.030 | 6550003
9980 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 6710003 | Pave Sherwood Blvd between 3rd St and Langer Dr in Sherwood to improve safety and extend pavement life. | Other | 2009-08-26 | 2009-08-26 |  | 2010-02-11 | 23666.88 |  | 6710003
9981 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960020 | Complete pavement preservation project on Pioneer Parkway between Hayden Bridge and Q St in Springfield to improve safety and extend pavement life. | Other | 2009-07-01 | 2009-07-01 |  |  | 68314.84 |  | 6960020
9982 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960021 | Complete pavement preservation project on Pioneer Parkway between Hayden Bridge and Q St in Springfield to improve safety and extend pavement life. | Pavement Improvement | 2010-03-26 | 2010-04-20 | 2010-10-29 | 2010-10-26 | 1968740.17 |  | 6960021
9983 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960029 | Improve safety and traffic flow on several city streets in Springfield retiming traffic signals. | Safety/Traffic Management | 2010-01-12 | 2010-05-18 | 2010-06-25 | 2010-06-25 | 177132.21 |  | 6960029
9984 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960030 | Improve safety on several city streets in Springfield by replacing low pressure sodium lights with high pressure sodium and metal halide lights. | Other | 2009-08-10 | 2009-08-10 |  | 2009-11-19 | 15800.2 |  | 6960030
9985 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | 6960031 | Improve safety and traffic flow on several city streets in Springfield retiming traffic signals. | Other | 2009-08-13 | 2009-08-13 |  |  | 12210.42 |  | 6960031
9986 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON | MEDFORD | 02 | 7250009 | Improve safety and extend pavement life on several city streets in Talent and Phoenix by paving, addind additional signage and signals. | Other | 2009-04-16 | 2009-04-16 |  | 2009-07-16 | 43161.49 |  | 7250009
9987 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | WASHINGTON | PORTLAND (WA) | 01 | 7365007 | Pave Bonita, Durham and 72nd Ave in Tigard to improve safety and extend pavement life. | Other | 2009-08-21 | 2009-08-21 |  | 2010-02-11 | 46057.84 |  | 7365007
9988 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8015000 | Pave Salamo Rd between Barrington Dr and Rosemont in West Linn to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2010-03-04 | 84710.75 |  | 8015000
9989 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8015001 | Pave Salamo Rd between Barrington Dr and Rosemont in West Linn to improve safety and extend pavement life. | Pavement Improvement | 2010-04-01 | 2010-06-14 | 2010-08-30 | 2010-09-30 | 1049813.73 |  | 8015001
9990 | OREGON | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8015002 | Improve pedestrian and bicycle safety and mobility by construcing the West Linn Trainl bike / ped path. | Other | 2009-11-24 | 2009-11-24 | 2013-03-31 |  | 250000 |  | 8015002
9991 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8280005 | Improve vehicle, bicycle and pedestrian safety on Barber St between Boberg Rd and Boones Ferry Rd in Wilsonville by widening to allow for bike lanes and sidewalks on both sides and a center turn lane. | Other | 2009-08-26 | 2009-08-26 |  | 2010-03-11 | 24499.83 |  | 8280005
9992 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 05 | 8280006 | Improve vehicle, bicycle and pedestrian safety on Barber St between Boberg Rd and Boones Ferry Rd in Wilsonville by widening to allow for bike lanes and sidewalks on both sides and a center turn lane. | Transportation Enhancements | 2010-04-19 | 2010-06-03 | 2010-11-17 | 2010-12-24 | 623424.35 |  | 8280006
9993 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HARNEY |  | 02 | C001011 | Pave Wingville Ln from mile point 0 to milp point 4.76 in Baker County to improve safety and extend pavement life. | Pavement Improvement | 2010-03-01 | 2010-07-07 | 2010-09-01 | 2010-09-10 | 419158.93 |  | C001011
9994 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | BAKER |  | 02 | C001012 | Pave Wingville Ln from mile point 0 to milp point 4.76 in Baker County to improve safety and extend pavement life. | Other | 2009-07-21 | 2009-07-21 |  | 2009-07-31 | 13271.77 |  | C001012
9995 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | C003035 | Pave Alpine Rd in Benton County to improve safety and extend pavement life. | Pavement Improvement | 2009-07-20 | 2009-07-20 |  |  | 317997.56 |  | C003035
9996 | OREGON | Underway | C240 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | C003036 | Improve safety to pedestrians and bicyclists by repaving the Campus Way multi-use bicycle and pedestrian path between 35th St and 53rd St in Corvallis. | Pavement Improvement | 2009-07-02 | 2009-07-06 |  |  | 76200.62 |  | C003036
9997 | OREGON | Underway | C200,C240 | Highway Infrastructure Investment Grant | OREGON | BENTON |  | 04 | C003037 | Pave Springhill Dr between Buena Vista Rd and Independence Hwy to improve safety and extend pavement life. | Pavement Improvement | 2010-03-10 | 2010-07-06 |  |  | 135902.44 |  | C003037
9998 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS |  | 05 | C005060 | REALIGN & WIDEN STAFFORD RD - WIDEN MOUNTAIN RD FOR SEPARATE LEFT & RIGHT TURN LANES | Safety/Traffic Management | 2011-01-31 | 2011-01-31 |  | 2011-09-29 | 553531.22 |  | C005060
9999 | OREGON | Underway | C200,C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 03 | C005066 | Pave King Rd between Witchita and 82nd Ave in Clackamas County to improve safety and extend pavement life. | Pavement Improvement | 2010-05-29 | 2010-05-29 |  |  | 591764.35 |  | C005066
10000 | OREGON | Underway | C200,C230 | Highway Infrastructure Investment Grant | OREGON | CLACKAMAS | PORTLAND (WA) | 03 | C005067 | Pave Sunnyside Rd between 82nd Ave and 122nd Ave to improve safety and extend pavement life. Improve traffic flow andmobility by replacing traffic signals and controllers and adding video detection at 8 intersections. | Pavement Improvement | 2010-05-29 | 2010-08-05 |  |  | 1174987.43 |  | C005067
10001 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | C007023 | Pave Lewis & clark Rd between Tucker Creek Rd and Lyngstad Heights Rd in Clatsop County to improve safety and extend pavement life. | Other | 2009-06-11 | 2009-06-11 |  | 2009-09-10 | 17125.84 |  | C007023
10002 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | C007024 | Pave Lewis & clark Rd between Tucker Creek Rd and Lyngstad Heights Rd in Clatsop County to improve safety and extend pavement life. | Pavement Improvement | 2009-12-09 | 2010-04-19 | 2010-06-15 | 2010-06-07 | 542394 |  | C007024
10003 | OREGON | Completed | C220 | Highway Infrastructure Investment Grant | OREGON | CLATSOP |  | 01 | C007025 | Improve pedestrian and bicycle safety and access by constructing shared-use paths, rest/view sites, and gazebo shelters on the Port of Astoria Pedestrian Access Paths. | Transportation Enhancements | 2010-02-16 | 2010-04-05 | 2010-07-30 | 2010-08-06 | 432686.09 |  | C007025
10004 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | C009055 | Pave Apiary Rd between mile point 14 and mile point 19 in Columbia County to improve safety and extend pavement life. | Other | 2009-06-09 | 2009-06-09 |  | 2009-09-10 | 50947.86 |  | C009055
10005 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COLUMBIA |  | 01 | C009056 | Pave Apiary Rd between mile point 14 and mile point 19 in Columbia County to improve safety and extend pavement life. | Safety/Traffic Management | 2009-10-09 | 2010-05-10 | 2010-07-15 | 2010-07-12 | 728584.14 |  | C009056
10006 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011057 | Pave and add additional signage to Central Blvd between OR 42 and 10th St in Coos County to improve safety and extend pavement life. | Pavement Improvement | 2010-02-26 | 2010-06-29 | 2010-09-05 | 2010-09-24 | 424459.2 |  | C011057
10007 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011058 | Pave and add additional signage to Central Blvd between OR 42 and 10th St in Coos County to improve safety and extend pavement life. | Other | 2009-06-12 | 2009-06-12 |  | 2010-02-04 | 60000 |  | C011058
10008 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011059 | Repair the Anson Rogers Bridge on South Coos River Rd in Coos County to improve safety and extend the life of the bridge. | Other | 2009-06-10 | 2009-06-10 |  | 2010-01-14 | 50000 |  | C011059
10009 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011060 | Pave Sherman Ave between Newmark St and City Limits in North Bend to improve safety and extend pavement life. | Other | 2009-08-14 | 2009-08-14 |  | 2010-02-04 | 1748.6 |  | C011060
10010 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | COOS |  | 04 | C011061 | Repair the Anson Rogers Bridge on South Coos River Rd in Coos County to improve safety and extend the life of the bridge. | Bridge Improvement | 2010-02-03 | 2010-03-23 | 2010-08-31 | 2010-08-16 | 358969.86 |  | C011061
10011 | OREGON | Completed | C250,C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | C013015 | Pave Lone Pine Rd and Smith Rock Way in Crook County to improve safety and extend pavement life. | Pavement Improvement | 2010-01-12 | 2010-04-09 | 2010-06-11 | 2010-06-11 | 531411.53 |  | C013015
10012 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | CROOK |  | 02 | C013016 | Pave Lone Pine Rd and Smith Rock Way in Crook County to improve safety and extend pavement life. | Other | 2009-05-05 | 2009-05-05 |  | 2009-10-26 | 23351.47 |  | C013016
10013 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | C017013 | Pave Huntington Rd and Riverview Rd between South Century Drive and Burgess Rd in Deschutes County to improve safety and extend pavement life. | Pavement Improvement | 2009-08-27 | 2009-09-30 | 2009-10-15 | 2009-10-19 | 1074637.3 |  | C017013
10014 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DESCHUTES |  | 02 | C017014 | Pave Huntington Rd and Riverview Rd between South Century Drive and Burgess Rd in Deschutes County to improve safety and extend pavement life. | Other | 2009-05-03 | 2009-05-03 |  | 2009-06-15 | 19841.7 |  | C017014
10015 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | C019036 | Pave Dillard Hwy between mile point .71 and mile point 5.85 in Douglas County to improve safety and extend pavement life. | Other | 2009-06-14 | 2009-06-14 |  | 2009-09-24 | 28087.55 |  | C019036
10016 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | DOUGLAS |  | 04 | C019037 | Pave Dillard Hwy between mile point .71 and mile point 5.85 in Douglas County to improve safety and extend pavement life. | Pavement Improvement | 2009-10-09 | 2010-03-12 | 2010-05-01 | 2010-09-02 | 1511627.46 |  | C019037
10017 | OREGON | Completed | C250 | Highway Infrastructure Investment Grant | OREGON | GRANT |  | 02 | C023007 | Pave County Rd 51 (Adams Rd) between MP 0 and MP 3.24 to improve safety and extend pavement life. | Pavement Improvement | 2010-03-18 | 2010-05-14 | 2010-07-31 | 2010-06-30 | 336793.25 |  | C023007
10018 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HARNEY |  | 02 | C025019 | Place chip seal on Silver Creek Rd and Green House Ln in Harney County to improve safety and extend pavement life. | Pavement Improvement | 2009-09-16 | 2010-06-21 | 2009-10-31 | 2010-11-15 | 405634.17 |  | C025019
10019 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HARNEY |  | 02 | C025021 | Place chip seal on Silver Creek Rd and Green House Ln in Harney County to improve safety and extend pavement life. | Other | 2009-07-21 | 2009-07-21 |  | 2009-10-31 | 5750.58 |  | C025021
10020 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HOOD RIVER |  | 02 | C027013 | Pave Belmont Dr and Cooper Spur Rd in Hood River County to improve safety and extend pavement life. | Other | 2009-05-15 | 2009-05-15 |  | 2010-02-04 | 45392.74 |  | C027013
10021 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | HOOD RIVER |  | 02 | C027014 | Pave Belmont Dr and Cooper Spur Rd in Hood River County to improve safety and extend pavement life. | Pavement Improvement | 2010-03-09 | 2010-06-28 | 2010-07-31 | 2010-07-30 | 381026.26 |  | C027014
10022 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | C029058 | Pave several county roads in Jackson County to improve safety and extend pavement life. | Other | 2009-04-29 | 2009-04-29 |  | 2009-08-20 | 84998.86 |  | C029058
10023 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | C029059 | Improve pedestrian and bicycle safety and access by constructing a shared use path on Barnett Rd in Jackson County. | Transportation Enhancements | 2009-10-07 | 2009-11-16 | 2010-07-31 | 2011-07-11 | 1058176.46 |  | C029059
10024 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JACKSON |  | 02 | C029061 | Pave several county roads in Jackson County to improve safety and extend pavement life. | Pavement Improvement | 2009-09-10 | 2009-10-06 | 2010-07-31 | 2009-11-19 | 1390796.14 |  | C029061
10025 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JEFFERSON |  | 02 | C031004 | Pave Lone Pine Rd from mile point 0 to mile point 3.7 in Jefferson County to improve safety and extend pavement life. | Pavement Improvement | 2009-09-03 | 2009-10-01 | 2009-10-23 | 2009-11-20 | 432188.52 |  | C031004
10026 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JEFFERSON |  | 02 | C031005 | Pave Lone Pine Rd from mile point 0 to mile point 3.7 in Jefferson County to improve safety and extend pavement life. | Other | 2009-05-05 | 2009-05-05 |  | 2009-06-22 | 15527.2 |  | C031005
10027 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 02 | C033031 | Pave Old Hwy 99 from mile point 0 to mile point .67 in Josephine County to improve safety and extend pavement life. | Other | 2009-06-04 | 2009-06-04 |  |  | 1386.94 |  | C033031
10028 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | JOSEPHINE |  | 04 | C033032 | Pave Old Hwy 99 from mile point 0 to mile point .67 in Josephine County to improve safety and extend pavement life. | Pavement Improvement | 2009-08-17 | 2009-09-28 | 2009-10-31 | 2009-10-30 | 203616.56 |  | C033032
10029 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | KLAMATH |  | 02 | C035024 | Improve safety on Washburn Way between Crosby and Joe Wright Rd in Klamath Falls by paving and adding additional signage. | Other | 2009-05-01 | 2009-05-01 |  | 2009-06-08 | 55810.71 |  | C035024
10030 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | KLAMATH |  | 02 | C035025 | Improve safety on Washburn Way between Crosby and Joe Wright Rd in Klamath Falls by paving and adding additional signage. | Pavement Improvement | 2009-08-10 | 2009-09-09 | 2009-10-23 | 2009-10-23 | 963054.55 |  | C035025
10031 | OREGON | Completed | C240 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | C039027 | Enhance safety to pedestrians and bicyclists by repaving the EWEB Bike Path between Pioneer Parkway and 31st street in Eugene. | Pavement Improvement | 2009-07-15 | 2009-07-20 | 2009-09-30 | 2009-09-30 | 308191.66 |  | C039027
10032 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | C039028 | Pave Clear Lake Rd and Marcola Rd in Lane County to improve safety and extend pavement life. | Other | 2009-05-07 | 2009-05-07 |  | 2009-11-19 | 75420.85 |  | C039028
10033 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LANE |  | 04 | C039029 | Pave Clear Lake Rd and Marcola Rd in Lane County to improve safety and extend pavement life. | Pavement Improvement | 2009-12-17 | 2010-08-12 | 2010-10-01 | 2011-09-23 | 1542383.08 |  | C039029
10034 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | C039030 | Complete pavement preservation project on River Rd, 23rd St and Coburg Rd in Eugene to improve safety and extend the life of the pavement. | Other | 2009-06-04 | 2009-06-04 |  | 2009-11-19 | 69037.57 |  | C039030
10035 | OREGON | Completed | C200,C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | C039031 | Complete pavement preservation project on River Rd, 23rd St and Coburg Rd in Eugene to improve safety and extend the life of the pavement. | Pavement Improvement | 2009-12-17 | 2010-07-06 | 2010-10-01 | 2010-09-14 | 1055896.58 |  | C039031
10036 | OREGON | Underway | C230 | Highway Infrastructure Investment Grant | OREGON | LANE | EUGENE | 04 | C039032 | Complete pavement preservation project on W 1st Ave between Seneca Rd and Bertelsen Rd in Eugene to improve safety and extend the life of the pavement. | Other | 2009-06-11 | 2009-06-11 |  |  | 23055.89 |  | C039032
10037 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | C041009 | Pave Northbank Rd and Schooner Creek Rd in Lincoln County to improve safety and extend pavement life. | Other | 2009-05-05 | 2009-05-05 |  | 2009-07-16 | 44063.54 |  | C041009
10038 | OREGON | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | LINCOLN |  | 05 | C041010 | Pave Northbank Rd and Schooner Creek Rd in Lincoln County to improve safety and extend pavement life. | Pavement Improvement | 2009-08-24 | 2009-09-11 | 2009-10-15 | 2009-10-21 | 933391.46 |  | C041010
10039 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | C043021 | Pave Stayton-Scio Rd and Oakville Rd in Linn County to improve safety and extend pavement life. | Other | 2009-05-07 | 2009-05-07 |  | 2009-08-27 | 42692.83 |  | C043021
10040 | OREGON | Completed | C200,C240 | Highway Infrastructure Investment Grant | OREGON | LINN |  | 04 | C043022 | Pave Stayton-Scio Rd and Oakville Rd in Linn County to improve safety and extend pavement life. | Pavement Improvement | 2009-09-17 | 2009-09-21 | 2009-11-07 | 2009-11-24 | 1354437.17 |  | C043022
10041 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | MALHEUR |  | 02 | C045025 | Pave Foothill Dr, Halliday St and Railroad Ave in Malheur County to improve safety and extend pavement life. | Pavement Improvement | 2010-02-05 | 2010-05-04 | 2010-09-30 | 2010-06-03 | 676056.07 |  | C045025
10042 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | MALHEUR |  | 02 | C045026 | Pave Foothill Dr, Halliday St and Railroad Ave in Malheur County to improve safety and extend pavement life. | Other | 2009-01-14 | 2009-01-14 |  | 2009-07-31 | 12689.19 |  | C045026
10043 | OREGON | Underway | C200,C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047041 | Pave several county roads in Marion County and Young St in Woodburn to improve safety and extend pavement life. | Pavement Improvement | 2009-08-28 | 2010-06-15 | 2010-06-30 |  | 1457103.99 |  | C047041
10044 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047042 | Pave sections of Auburn Rd, Hazelgreen Rd, State St, Turner Rd, Center St, Ward Dr and Brown Rd in Marion County (Salem and Keizer) to improve safety and extend pavement life. | Other | 2009-06-05 | 2009-06-05 |  | 2009-07-23 | 2253.58 |  | C047042
10045 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047043 | Pave sections of Auburn Rd, Hazelgreen Rd, State St, Turner Rd, Center St, Ward Dr and Brown Rd in Marion County (Salem and Keizer) to improve safety and extend pavement life. | Pavement Improvement | 2009-08-28 | 2009-10-26 | 2010-06-30 | 2010-08-17 | 1263509.55 |  | C047043
10046 | OREGON | Underway | C200 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | C047044 | Pave several county roads in Marion County and Young St in Woodburn to improve safety and extend pavement life. | Other | 2009-06-19 | 2009-06-19 |  |  | 9999.57 |  | C047044
10047 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047047 | Upgrade signals at Lancaster Dr and Durbin to improve safety and traffic flow. | Other | 2009-07-27 | 2009-07-27 |  | 2010-02-11 | 47458.89 |  | C047047
10048 | OREGON | Completed | C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047048 | Upgrade signals at Lancaster Dr and Durbin to improve safety and traffic flow. | Safety/Traffic Management | 2010-03-23 | 2010-09-10 | 2010-09-30 | 2011-05-27 | 367813.43 |  | C047048
10049 | OREGON | Completed | C950 | Ferryboat | OREGON | MARION |  | 05 | C047049 | Improve access by replacing Buena Vista Ferry Boat and make improvements to ferry terminal. | Other | 2010-06-30 | 2010-06-30 |  | 2010-07-22 | 532840.41 |  | C047049
10050 | OREGON | Completed | C950 | Ferryboat | OREGON | MARION |  | 05 | C047050 | Improve access by replacing Buena Vista Ferry Boat and make improvements to ferry terminal. | Other | 2010-08-17 | 2010-09-17 | 2011-02-18 | 2011-06-22 | 1544528.01 |  | C047050
10051 | OREGON | Completed | C240,C230 | Highway Infrastructure Investment Grant | OREGON | MARION | SALEM | 05 | C047051 | Pave Cordon Rd, Garfield St, Harrison St and Cleaveland in Salem to improve safety and extend pavement life. | Pavement Improvement | 2010-03-31 | 2010-06-07 | 2010-09-15 | 2010-08-09 | 322494.75 |  | C047051
10052 | OREGON | Completed | C200 | Highway Infrastructure Investment Grant | OREGON | MARION |  | 05 | C047052 | Pave Cordon Rd, Garfield St, Harrison St and Cleaveland in Salem to improve safety and extend pavement life. | Other | 2010-01-13 | 2010-01-13 |  | 2010-03-04 | 2203.46 |  | C047052
10053 | OREGON | Completed | C950 | Ferryboat | OREGON | MARION |  | 05 | C047055 | Improve access by replacing Buena Vista Ferry Boat and make improvements to ferry terminal. | Other | 2010-10-11 | 2010-10-11 |  | 2010-07-22 | 1146079.99 |  | C047055